## PROJECTS
Project Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Construction Project Type Name | State Name | Country Name | Project Number | Project Title | Sub-Project Number | Diverted Funds Total Amount | Diverted Funds Recipient Text | Diverted Funds Recipient RPSUID Text | Construction Start Date | Original Construction Completion Date | Current Construction Completion Date | Construction Percent Complete | Current RPA Placed-In-Service Date | Project Remarks
2015-09-08 | 2010 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 |  |  |  |  | 2011-06-17 | 2014-11-23 | 2016-12-22 | 0.77
2015-09-08 | 2011 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083008 | Repair Central Heat And Power Plant Boiler |  |  |  |  | 2011-06-17 | 2014-11-24 | 2016-12-22 | 0.77
2015-09-08 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) |  | 19165000 | ALUA073006B;WWYK143004A;YWHG111005;ZHTV053302; |  | 2012-06-26 | 2013-11-20 | 2015-11-11 | 0.91
2015-09-08 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083005 | Dormitory (168 RM) |  |  |  |  | 2014-08-26 | 2014-03-20 | 2016-08-15 | 0.24
2015-09-08 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV063501 | AMARG Hangar |  |  |  |  | 2011-09-12 | 2013-03-11 | 2016-02-26 | 0.95
2015-09-08 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093000 | F-35 Academic Training Center |  | 2406080 | PRQE145121;SGBP100904C; |  | 2012-11-05 | 2013-06-28 | 2015-05-29 | 1 | 2014-12-22
2015-09-08 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV113002 | HC-130J Aerial Cargo Facility |  | 2000000 | YWHG111005; |  | 2011-11-09 | 2012-09-21 | 2015-10-31 | 0.95 | 2013-09-13
2015-09-08 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV103006P1 | EC-130H Simulator/Training Operations |  | 4333000 | LKTC093101;WWYK143004A; |  | 2013-02-10 | 2013-10-07 | 2015-08-01 | 1 | 2014-10-17
2015-09-08 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120011 | F-35 Squad Ops/AMU 2 |  |  |  |  | 2013-10-08 | 2012-11-30 | 2015-01-12 | 1 | 2015-01-12
2015-09-08 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV123002 | HC-130J Joint Use Fuel Cell |  |  |  |  | 2013-01-10 | 2014-04-24 | 2015-07-20 | 1 | 2015-05-21
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | FBNV133500 | T-10 Engine Test Cell (AMARG) |  |  |  |  | 2014-08-12 | 2013-07-29 | 2015-11-30 | 0.35
2015-09-08 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093007 | Construct Addition, Field Training Facility, B936 |  |  |  |  | 2014-12-01 | 2015-07-07 | 2015-09-30 | 0.63
2015-09-08 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) |  | 1200000 | CADJ140004; |  | 2015-06-15 | 2016-02-14 | 2016-03-15 | 0.3
2015-09-08 | 2015 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX103005 | Construct Flightline Fillstands |  |  |  |  | 2015-06-01 | 2016-11-22 | 2016-11-23 | 0.02
2015-09-08 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK113005 | C-130J Flight Simulator Addition |  |  |  |  | 2014-10-21 | 2015-03-20 | 2015-10-21 | 0.39
2015-09-08 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK103006 | C-130J Fuel Systems Maintenance Hangar |  | 2000000 | KRSM103012; |  | 2013-07-23 | 2014-11-19 | 2015-10-28 | 0.83
2015-09-08 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | NKAK113003 | C130J Propeller Repair Training Facility |  |  |  |  | 2014-02-28 | 2015-02-20 | 2015-02-20 | 0.75
2015-09-08 | 2013 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY133001 | Civil Engineer Administration/Operations Facility |  |  |  |  | 2014-07-09 | 2016-03-30 | 2016-03-30 | 0.14
2015-09-08 | 2014 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 3000000 | CADJ140004; |  | 2014-08-27 | 2016-08-26 | 2017-02-21 | 0.08
2015-09-08 | 2011 | Air Force Active | Major Military Construction | COLORADO | UNITED STATES | XQPZ084017 | Const Center For Character & Leadership Development |  |  |  |  | 2013-01-15 | 2014-08-29 | 2015-09-30 | 0.94
2015-09-08 | 2014 | Air Force Active | Unspecified Minor Military Construction | COLORADO | UNITED STATES | XQPZ124003 | Const Perm ECP-Pine Drive |  |  |  |  | 2015-04-13 | 2015-12-09 | 2016-01-25 | 0.22
2015-09-08 | 2010 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT033003 | Consol Communications Facility |  |  |  |  | 2011-01-03 | 2011-11-09 | 2015-09-01 | 0.95 | 2014-09-12
2015-09-08 | 2011 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT113001 | C-5M/C-17 Maintenance Training Facility, Ph 2 |  |  |  |  | 2012-07-02 | 2012-05-30 | 2014-10-31 | 1 | 2014-05-12
2015-09-08 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | NVZR033702 | Consolidated Communications Facility |  |  |  |  | 2010-08-11 | 2013-07-26 | 2014-12-31 | 1 | 2013-12-13
2015-09-08 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073902 | F-35 Hydrant Refueling System Phase 1 |  |  |  |  | 2010-10-07 | 2011-02-28 | 2014-10-31 | 1 | 2013-10-30
2015-09-08 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073904 | F-35 JP-8 Flightline Fillstands |  |  |  |  | 2010-10-07 | 2010-12-30 | 2014-10-31 | 1 | 2013-10-30
2015-09-08 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073905 | F-35 JP-8 West Side Bulk Fuel Tank Upgrades |  |  |  |  | 2010-10-07 | 2010-12-30 | 2014-10-31 | 1 | 2013-10-30
2015-09-08 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA061726 | F-35 POL Ops Facility |  |  |  |  | 2010-10-07 | 2010-12-30 | 2014-10-31 | 1 | 2013-09-30
2015-09-08 | 2011 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | SXHT053001 | Air Force Technical Applications Center |  |  |  |  | 2012-01-23 | 2015-06-30 | 2016-03-01 | 0.98 | 2014-03-03
2015-09-08 | 2013 | Air Force Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | FTFA123000 | Advanced Energetics Development Office Facility |  |  |  |  | 2014-12-05 | 2014-07-25 | 2015-12-08 | 0.35
2015-09-08 | 2013 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair |  |  |  |  | 2013-08-21 | 2014-07-20 | 2015-05-29 | 1 | 2015-06-10
2015-09-08 | 2014 | Air Force Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | FTFA073007 | CNST Modular Storage Magazines |  |  |  |  | 2015-02-05 | 2015-10-13 | 2016-02-09 | 0.26
2015-09-08 | 2014 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103007 | F-22 Muntions Storage Complex |  |  |  |  | 2015-07-13 | 2016-10-25 | 2016-10-25 | 0.02
2015-09-08 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | ACC123184 | Air Support Operations Center |  |  |  |  | 2013-11-07 | 2014-05-01 | 2015-09-25 | 0.95
2015-09-08 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | QSEU103008 | HC-130J Simulator Facility |  |  |  |  | 2013-08-12 | 2014-10-15 | 2015-04-29 | 1 | 2014-12-19
2015-09-08 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility |  |  |  |  | 2014-11-19 | 2015-02-18 | 2015-11-23 | 0.02
2015-09-08 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | UHHZ123001 | Convert Cooler Area B/660 To AFLCMC/WFM C-17 Program Office |  |  |  |  | 2015-02-11 | 2016-05-11 | 2016-05-11 | 0.02
2015-09-08 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY983202 | Air Freight Terminal Complex |  |  |  |  | 2012-07-18 | 2014-03-31 | 2015-06-26 | 1 | 2015-06-12
2015-09-08 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility |  | 2100000 | ZHTV053302; |  | 2012-05-14 | 2013-10-23 | 2015-03-31 | 1 | 2014-08-15
2015-09-08 | 2013 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY123010 | Guam Strike Fuel Systems Maintenance Hangar |  |  |  |  | 2015-03-25 | 2017-04-16 | 2017-04-16 | 0.08
2015-09-08 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility |  |  |  |  | 2014-10-24 | 2016-07-20 | 2016-07-20 | 0.25
2015-09-08 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY133027 | Guam Strike Tanker Gp Maint Hangar/Amu/Sqd Ops (Incr 1) |  |  |  |  | 2015-02-01 | 2017-03-08 | 2017-03-08 | 0.1
2015-09-08 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY143760 | Hardened Structures For POL Fuel Systems |  |  |  |  | 2014-12-01 | 2016-04-12 | 2016-05-30 | 0.06
2015-09-08 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW113003 | PRTC - Red Horse Airfield Operations Facility (TFI) |  |  |  |  | 2015-03-06 | 2016-07-08 | 2016-07-08 | 0.15
2015-09-08 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW133005 | PRTC Silver Flag Fire Rescue & Emergency Management Training |  |  |  |  | 2015-03-30 | 2017-02-01 | 2017-02-01 | 0.09
2015-09-08 | 2015 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW113008 | PRTC - Combat Communications Infrastructure Facility |  |  |  |  | 2015-07-17 | 2016-06-21 | 2017-06-01 | 0.05
2015-09-08 | 2015 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059006 | PRTC - Red Horse Logistics Facility |  |  |  |  | 2015-03-07 | 2016-04-10 | 2016-04-10 | 0.18
2015-09-08 | 2015 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW143031 | PRTC Satellite Fire Station |  |  |  |  | 2015-03-06 | 2016-07-30 | 2016-07-30 | 0.18
2015-09-08 | 2010 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD063003 | Ground Control Tower |  |  |  |  | 2013-02-20 | 2011-10-28 | 2015-08-05 | 1 | 2015-08-05
2015-09-08 | 2014 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  |  |  |  | 2014-08-21 | 2014-08-29 | 2015-12-07 | 0.05
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction | INDIANA | UNITED STATES | CTGB102040 | Addition to BOWST Simulator |  |  |  |  | 2012-08-10 | 2013-04-08 | 2013-04-08 | 0.35
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145142 | KC-46A 1-Bay Maintenance Hangar |  | 3000000 | SGBP100904C; |  | 2014-09-19 | 2016-05-27 | 2017-03-10 | 0.56
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar |  | 10500000 | SGBP100904C; |  | 2014-08-10 | 2016-01-05 | 2017-03-10 | 0.56
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar |  | 19000000 | SGBP100904C; |  | 2014-09-30 | 2015-12-26 | 2017-03-10 | 0.21
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145121 | KC-46A ADAL Flight Simulator Buildings |  |  |  |  | 2015-03-30 | 2016-04-19 | 2016-03-30 | 0.13
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145138 | KC-46A Alter Aircraft Parking Apron |  | 600000 | PRQE145121; |  | 2014-08-18 | 2016-06-24 | 2017-03-10 | 0.29
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems |  | 2500000 | SGBP100904C; |  | 2014-09-02 | 2015-12-17 | 2015-12-19 | 0.92
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145137 | KC-46A Alter Miscellaneous Facilities |  |  |  |  | 2014-07-12 | 2015-02-28 | 2015-04-30 | 0.99 | 2015-07-15
2015-09-08 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) |  |  |  |  | 2014-10-30 | 2015-07-24 | 2015-10-15 | 0.47
2015-09-08 | 2015 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155118 | KC-46A Adal Mobility Bag Storage Expansion |  |  |  |  | 2015-05-05 | 2016-02-05 | 2016-02-05 | 0.02
2015-09-08 | 2015 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155124 | KC-46A Alter Taxiway Foxtrot |  |  |  |  | 2015-05-12 | 2016-11-02 | 2016-11-21 | 0.14
2015-09-08 | 2015 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145118 | KC-46A Fuselage Trainer |  |  |  |  | 2015-05-05 | 2016-05-04 | 2016-11-07 | 0.02
2015-09-08 | 2012 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB105002 | Mission Support Group Complex |  |  |  |  | 2012-03-26 | 2013-06-17 | 2015-09-16 | 0.99 | 2014-12-23
2015-09-08 | 2010 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF063009 | Replace Munitions Storage Area |  |  |  |  | 2011-06-23 | 2011-12-16 | 2016-01-09 | 0.91
2015-09-08 | 2013 | Air Force Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | AJXF106000 | Construct Taxiway To North Of ACA Facility Bldg 2489 |  |  |  |  | 2015-04-09 | 2016-04-08 | 2016-05-08 | 0.02
2015-09-08 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF103010 | Construct Helicopter Operations Facility |  |  |  |  | 2015-01-26 | 2017-03-09 | 2017-03-09 | 0.02
2015-09-08 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  |  |  |  | 2014-07-07 | 2016-04-13 | 2017-04-13 | 0.23
2015-09-08 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111005 | Force Support Squadron Facility |  |  |  |  | 2012-09-07 | 2013-09-09 | 2014-11-07 | 1 | 2013-09-30
2015-09-08 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG071005 | WSA Security Control Facility |  |  |  |  | 2012-03-16 | 2013-09-06 | 2015-09-10 | 0.99 | 2014-08-15
2015-09-08 | 2014 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111010 | WSA: Construct Two New MOP Igloos |  |  |  |  | 2014-08-11 | 2015-11-13 | 2016-01-10 | 0.75
2015-09-08 | 2010 | Air Force Active | Major Military Construction | MONTANA | UNITED STATES | NZAS003000A | Upgrade Weapons Storage Area |  |  |  |  | 2013-12-09 | 2012-02-29 | 2015-10-30 | 0.94 | 2015-07-31
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NEBRASKA | UNITED STATES | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  |  |  |  | 2012-10-15 | 2016-02-15 | 2016-09-12 | 0.55
2015-09-08 | 2011 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC113102 | UAS Airfield Fire/Crash Rescue Station |  |  |  |  | 2012-06-15 | 2013-02-28 | 2014-11-06 | 1 | 2014-07-14
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103003 | Communications Network Control Center |  | 800000 | ZHTV053302; |  | 2012-12-01 | 2014-05-22 | 2015-07-31 | 0.99 | 2014-05-01
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103010 | F-35 Add/Alter Engine Shop |  | 572000 | WWYK143004A; |  | 2014-01-15 | 2013-06-15 | 2014-12-01 | 1 | 2014-09-02
2015-09-08 | 2013 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC133101 | RPA Mission Complex Physical Protection System |  |  |  |  | 2014-08-19 | 2015-08-19 | 2015-10-15 | 0.89
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF083002 | Dormitory |  |  |  |  | 2014-07-11 | 2016-09-27 | 2016-09-27 | 0.11
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103005 | F-35A ADAL AME Storage Facility |  |  |  |  | 2014-08-27 | 2016-02-18 | 2016-02-18 | 0.24
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar |  |  |  |  | 2015-03-03 | 2015-12-16 | 2016-03-01 | 0.61
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103006 | F-35A Parts Store |  | 1400000 | CADJ140004; |  | 2015-04-30 | 2016-01-06 | 2016-04-12 | 0.41
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC073101 | Land Acquisition |  |  |  |  | 2014-09-02 | 2016-05-28 | 2016-05-28 | 0.02
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF113005 | RPA Weapons School |  | 2000000 | CADJ140004; |  | 2014-08-12 | 2016-06-01 | 2016-06-01 | 0.4
2015-09-08 | 2015 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF133001 | F-22 Flight Simulator Facility |  |  |  |  | 2015-07-09 | 2017-01-19 | 2017-02-15 | 0.02
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV093108 | AFNWC Sustainment Center |  | 1100000 | ZHTV053302; |  | 2012-07-09 | 2014-04-30 | 2015-03-06 | 1 | 2015-05-20
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD013003 | Child Development Center |  |  |  |  | 2012-11-08 | 2012-06-15 | 2015-11-15 | 0.99 | 2014-06-14
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD113005 | F-16 Academic Training Facility |  |  |  |  | 2012-09-28 | 2013-07-12 | 2015-10-15 | 0.99 | 2014-05-01
2015-09-08 | 2013 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD123004 | MQ-9 Maintenance Hangar |  | 1225000 | KRSM103012; |  | 2013-08-30 | 2014-11-28 | 2015-02-23 | 1 | 2014-09-22
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ013004 | Airman And Family Readiness Center |  |  |  |  | 2015-06-11 | 2015-06-23 | 2016-06-10 | 0.02
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073050 | Dormitory (144 Rm) |  |  |  |  | 2014-08-14 | 2015-07-15 | 2016-08-21 | 0.53
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 |  |  |  |  | 2014-08-25 | 2016-02-08 | 2016-02-08 | 0.33
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073023A | Satellite Dining Facility |  |  |  |  | 2015-01-27 | 2016-11-19 | 2016-11-19 | 0.31
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH083003 | C-130 Flight Simulator |  |  |  |  | 2013-04-30 | 2014-01-15 | 2015-01-09 | 1 | 2015-04-23
2015-09-08 | 2012 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock |  |  |  |  | 2012-05-22 | 2014-02-11 | 2015-03-09 | 1 | 2015-03-09
2015-09-08 | 2013 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092011 | B-52 Add/Alter Munitions Age Facility |  |  |  |  | 2013-06-19 | 2014-08-21 | 2014-12-11 | 1 | 2014-12-11
2015-09-08 | 2014 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092013 | B-52 Munitions Storage Igloos |  |  |  |  | 2014-07-15 | 2014-10-01 | 2016-01-06 | 0.6
2015-09-08 | 2014 | Air Force Active | Major Military Construction | OHIO | UNITED STATES | ZHTV053302 | Add/Alter Foreign Materiel Exploitation Laboratory |  |  |  |  | 2015-07-13 | 2016-11-16 | 2017-01-06 | 0.02
2015-09-08 | 2010 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | XTLF033303 | Control Tower |  |  |  |  | 2010-10-05 | 2012-02-12 | 2016-01-25 | 0.99
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | AGGN123002P | Communications Network Control Center Consolidation |  |  |  |  | 2014-03-10 | 2014-03-31 | 2015-07-07 | 0.95
2015-09-08 | 2013 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 |  |  |  |  | 2013-06-07 | 2015-08-03 | 2015-07-17 | 1 | 2015-07-17
2015-09-08 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu |  |  |  |  | 2015-01-14 | 2015-12-24 | 2016-06-05 | 0.42
2015-09-08 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143004 | KC-46A FTU FTC Simulator Facility Phase 1 |  |  |  |  | 2014-06-19 | 2015-10-12 | 2016-04-30 | 0.61
2015-09-08 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 |  |  |  |  | 2014-06-19 | 2015-10-12 | 2016-05-30 | 0.48
2015-09-08 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS |  |  |  |  | 2014-07-30 | 2015-11-12 | 2015-10-29 | 0.97 | 2015-04-13
2015-09-08 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | WWYK143004A | KC46A Land Acquisition |  |  |  |  | 2015-02-04 | 2015-05-19 | 2015-06-15 | 1 | 2015-02-26
2015-09-08 | 2008 | Air Force Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | VLSB083007 | Base Infrastructure |  |  |  |  | 2008-10-27 | 2016-06-02 | 2016-06-02 | 0.99 | 2010-03-08
2015-09-08 | 2014 | Air Force Active | Major Military Construction | TENNESSEE | UNITED STATES | ACC123183 | Air Support Operations Center |  |  |  |  | 2014-09-29 | 2015-08-03 | 2015-12-13 | 0.44
2015-09-08 | 2009 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R1 | BMT Recruit Dormitory |  |  |  |  | 2009-10-06 | 2013-04-23 | 2014-12-10 | 1 | 2012-11-21
2015-09-08 | 2009 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS093002 | CNS Addition To Child Development Center (Cdc) B8210 |  |  |  |  | 2010-04-05 | 2011-02-22 | 2014-12-11 | 1 | 2012-08-20
2015-09-08 | 2010 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility |  |  |  |  | 2010-05-05 | 2011-09-01 | 2014-11-26 | 1 | 2012-10-31
2015-09-08 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 |  |  |  |  | 2011-09-05 | 2013-06-30 | 2015-09-30 | 0.99 | 2015-03-15
2015-09-08 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R3 | Recruit Dormitories Phase 3 |  | 4894000 | KRSM103011; |  | 2011-11-11 | 2012-12-28 | 2016-12-15 | 0.9 | 2015-06-06
2015-09-08 | 2012 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R4 | BMT Recruit Dormitory, Phase IV |  |  |  |  | 2013-01-26 | 2013-10-01 | 2016-06-30 | 0.85
2015-09-08 | 2013 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083008 | Dormitory (96 Rm) |  |  |  |  | 2014-03-15 | 2014-12-25 | 2015-12-20 | 0.52
2015-09-08 | 2014 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 |  |  |  |  | 2014-05-15 | 2015-06-09 | 2015-09-15 | 0.98 | 2015-06-30
2015-09-08 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM113028 | F-35 Adal Building 118 For Flight Simulator |  |  |  |  | 2014-01-29 | 2012-10-29 | 2015-07-30 | 0.99
2015-09-08 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103012 | F-35 Adal Hangar 45W/AMU |  |  |  |  | 2014-01-27 | 2015-07-21 | 2016-03-21 | 0.55
2015-09-08 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103030 | F-35A Modular Storage Magazines |  |  |  |  | 2014-01-27 | 2012-10-29 | 2015-10-25 | 0.99
2015-09-08 | 2014 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103011 | F-35 ADAL Hangar 45E/AMU |  |  |  |  | 2014-05-20 | 2015-10-14 | 2015-10-15 | 0.99
2015-09-08 | 2010 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | MUHJ053008 | West & Lasalle Gates Force Protection/Access |  |  |  |  | 2010-07-07 | 2011-04-28 | 2015-12-03 | 0.99 | 2013-07-19
2015-09-08 | 2012 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | WACC120007 | AIT Barracks Complex, Ph 2 |  | 10112000 | LKTC093101;WWYK143004A;ZHTV053302; |  | 2012-10-23 | 2014-04-01 | 2014-11-19 | 1 | 2014-10-29
2015-09-08 | 2012 | Air Force Active | Major Military Construction | WASHINGTON | UNITED STATES | GJKZ860009 | Wing Headquarters |  |  |  |  | 2013-03-18 | 2014-01-15 | 2015-04-10 | 1 | 2014-03-07
2015-09-08 | 2013 | Air Force Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | GJKZ130025 | ADAL, Physiological Tng Fac, Convert To PMEL; B2145 |  |  |  |  | 2015-01-27 | 2015-12-17 | 2015-12-17 | 0.03
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | AFGHANISTAN | ATUH110101 | Consolidated Rigging Facility |  |  |  |  | 2011-10-03 | 2012-03-14 | 2015-01-17 | 1 | 2014-05-21
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | AFGHANISTAN | ATUH110104 | Fighter Hangar |  |  |  |  | 2011-08-31 | 2012-03-14 | 2015-01-17 | 1 | 2014-05-21
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | AFGHANISTAN | ATUH110103 | Medevac Ramp Expansion/ Fire Station |  |  |  |  | 2011-07-28 | 2012-03-14 | 2015-01-17 | 1 | 2014-05-21
2015-09-08 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17001 | Aircraft Apron/Taxiway And Maintenance Shelters |  |  |  |  | 2012-05-15 | 2013-01-27 | 2015-01-07 | 1 | 2015-01-07
2015-09-08 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17002 | Combat Aircraft Loading Area |  |  |  |  | 2012-12-24 | 2014-01-16 | 2015-12-31 | 0.88
2015-09-08 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17004 | Expeditionary Lodging |  |  |  |  | 2013-03-15 | 2013-09-30 | 2015-12-31 | 0.99 | 2014-10-20
2015-09-08 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17003 | Parallel Taxiway Extension |  |  |  |  | 2012-12-24 | 2014-05-24 | 2015-12-31 | 0.98
2015-09-08 | 2008 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR084014 | Improve Family Housing, Ph E |  |  |  |  | 2013-07-08 | 2009-06-15 | 2015-03-16 | 1 | 2014-12-18
2015-09-08 | 2008 | Air Force Active | Military Family Housing |  | GERMANY | TYFR084034 | Replace Family Housing, Ph E |  |  |  |  | 2009-09-14 | 2009-09-15 | 2014-12-18 | 1 | 2011-12-15
2015-09-08 | 2010 | Air Force Active | Major Military Construction |  | GERMANY | TYFR053037 | Aerospace Ground Equipment Maintenance Complex |  |  |  |  | 2012-08-06 | 2013-07-06 | 2015-10-15 | 0.99
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR123063 | C-130J Flight Simulator Facility |  |  |  |  | 2014-01-06 | 2012-04-29 | 2015-09-15 | 0.99 | 2015-03-26
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | VYHK113003 | Catch Basin For Waste Water Treatment |  |  |  |  | 2012-10-01 | 2013-04-12 | 2014-11-22 | 1 | 2014-08-01
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR083001 | Deicing Fluid Storage & Dispensing Facility |  | 155000 | KRSM103011; |  | 2012-11-13 | 2011-08-17 | 2016-02-10 | 0.96
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFU083507R2 | Dormitory (128 Rm) |  |  |  |  | 2014-06-16 | 2013-03-06 | 2015-12-03 | 0.62
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR106261 | PL-1 Security Measures For Communications Compound |  |  |  |  | 2014-01-22 | 2014-12-12 | 2015-08-28 | 0.97
2015-09-08 | 2013 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR126175 | Expand AOC Parking Structure |  |  |  |  | 2014-08-08 | 2015-02-24 | 2015-09-30 | 0.97
2015-09-08 | 2013 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103032 | Dormitory (48 Pn) |  |  |  |  | 2013-08-15 | 2015-07-29 | 2015-07-29 | 0.99
2015-09-08 | 2014 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  |  |  |  | 2014-08-19 | 2016-06-17 | 2016-06-17 | 0.3
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | ITALY | ASHE083011 | Air Support Operations Squadron (ASOS) Facility |  | 1453000 | KRSM103011; |  | 2011-12-16 | 2013-06-06 | 2015-07-31 | 0.9
2015-09-08 | 2012 | Air Force Active | Major Military Construction |  | ITALY | ASHE163000 | Child Development Center Addition |  |  |  |  | 2013-04-01 | 2013-12-29 | 2014-12-03 | 1 | 2014-10-21
2015-09-08 | 2013 | Air Force Active | Major Military Construction |  | ITALY | ASHE103001 | F-16 Mission Training Center |  |  |  |  | 2015-05-04 | 2014-11-15 | 2016-06-01 | 0.02
2015-09-08 | 2011 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ114127 | Improve Family Housing, Ph 11 |  |  |  |  | 2012-10-24 | 2014-12-01 | 2015-09-14 | 0.99
2015-09-08 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 |  |  |  |  | 2013-06-04 | 2014-03-01 | 2015-11-20 | 0.95
2015-09-08 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA124002 | Improve MFH Infrastructure, Phase 1 |  |  |  |  | 2012-07-31 | 2014-11-13 | 2015-06-30 | 1 | 2015-06-30
2015-09-08 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 |  |  |  |  | 2013-08-29 | 2015-11-27 | 2016-01-04 | 0.7
2015-09-08 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA133001P2 | Improve Family Housing, Ph 2 |  |  |  |  | 2013-10-31 | 2015-06-21 | 2015-06-05 | 1 | 2015-06-05
2015-09-08 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA134001 | Improve Mfh Infrastructure, Phase 2 |  |  |  |  | 2013-10-29 | 2015-04-15 | 2015-10-06 | 0.88
2015-09-08 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA144002 | Improve MFH Infrastructure, Phase 3 |  |  |  |  | 2014-11-06 | 2016-11-10 | 2017-01-14 | 0.12
2015-09-08 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ144287 | Improve MFH Infrastructure, Phase 3 |  |  |  |  | 2014-08-04 | 2015-12-15 | 2016-04-06 | 0.37
2015-09-08 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALUA073008A | Facility Replacements |  |  |  |  | 2011-03-01 | 2010-06-30 | 2015-10-31 | 0.99
2015-09-08 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALDA053001B | Multi-Aircraft Maintenance Hanger |  |  |  |  | 2011-03-01 | 2009-10-30 | 2015-10-31 | 0.99
2015-09-08 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006A | Blatchford-Preston Complex Ph II |  |  |  |  | 2011-01-21 | 2012-02-15 | 2014-12-30 | 1 | 2014-12-30
2015-09-08 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA107000 | Coalition Compound Billeting |  |  |  |  | 2012-06-05 | 2013-11-30 | 2015-12-04 | 0.92
2015-09-08 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA103001 | Construct Network Control Center |  |  |  |  | 2012-08-19 | 2011-08-15 | 2015-08-03 | 1 | 2015-08-03
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006B | Blatchford-Preston Complex, Phase III |  |  |  |  | 2012-09-27 | 2013-03-31 | 2016-01-29 | 0.6
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113005 | C-17 Spare Parts Facility |  |  |  |  | 2013-08-15 | 2013-05-06 | 2016-06-30 | 0.42
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility |  |  |  |  | 2013-08-29 | 2013-08-15 | 2015-09-16 | 0.99
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113010 | Cryogenics Facility |  |  |  |  | 2013-08-15 | 2013-05-06 | 2016-06-30 | 0.42
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113012 | ELRS Storage Facility |  |  |  |  | 2013-08-15 | 2014-04-17 | 2016-06-30 | 0.42
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113009 | Entry Control Point |  |  |  |  | 2013-08-15 | 2013-05-06 | 2016-06-30 | 0.42
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA110032 | Fuel Truck Parking |  |  |  |  | 2013-08-15 | 2013-05-06 | 2016-06-30 | 0.42
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113002 | Fuels Laboratory |  |  |  |  | 2013-08-15 | 2013-05-06 | 2016-06-30 | 0.42
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113006 | High Mast Lighting |  |  |  |  | 2013-08-15 | 2013-05-06 | 2016-06-30 | 0.42
2015-09-08 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA113001 | Theater Communications Facility |  |  |  |  | 2012-06-01 | 2012-12-21 | 2016-03-31 | 0.75
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113034 | AFOSI Regional And Local Facility |  |  |  |  | 2013-08-28 | 2014-04-09 | 2015-11-15 | 0.98
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113027 | Air Defense Artillery Maintenance Facility |  |  |  |  | 2013-08-28 | 2014-04-09 | 2015-11-15 | 0.98
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113026 | C-130 Aircraft Maintenance Unit |  |  |  |  | 2013-09-12 | 2014-04-09 | 2016-06-30 | 0.23
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113032 | Precision Measurement Equipment Laboratory |  |  |  |  | 2013-08-28 | 2014-04-09 | 2015-11-15 | 0.98
2015-09-08 | 2008 | Air Force Active | Military Family Housing Improvement |  | TURKEY | LJYC084001 | Improve Family Housing 515 Units |  |  |  |  | 2012-03-08 | 2011-06-30 | 2016-03-16 | 0.61
2015-09-08 | 2009 | Air Force Active | Unspecified Minor Military Construction |  | TURKEY | AKNR041053 | CNS Replace Asf Admin Bldg 2621 |  |  |  |  | 2014-04-07 | 2011-05-12 | 2015-05-12 | 1 | 2015-03-26
2015-09-08 | 2010 | Air Force Active | Major Military Construction |  | TURKEY | LJYC003006 | Consolidated Community Center |  |  |  |  | 2013-01-15 | 2008-04-15 | 2015-07-27 | 1 | 2015-07-27
2015-09-08 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100031 | Construct Maintenance Operations Center And Command Post |  |  |  |  | 2011-09-19 | 2011-06-15 | 2015-10-30 | 0.96
2015-09-08 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100120 | Construct SatCom Facility |  |  |  |  | 2011-09-19 | 2011-09-15 | 2015-10-30 | 0.96
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120037 | Clinic |  |  |  |  | 2014-09-29 | 2014-10-05 | 2016-06-30 | 0.25
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF105000 | Dining Facility |  |  |  |  | 2012-10-03 | 2012-09-01 | 2014-12-01 | 0.15
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF110018 | EMSG Hq |  |  |  |  | 2012-10-03 | 2012-09-10 | 2014-12-01 | 0.15
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF124001 | EOD Facility |  |  |  |  | 2014-12-01 | 2014-10-05 | 2016-06-30 | 0.12
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120057 | Fire Protection Water Storage |  |  |  |  | 2014-09-15 | 2014-10-05 | 2015-10-30 | 0.72
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF080145 | Information Transfer Node |  |  |  |  | 2012-10-03 | 2012-10-30 | 2014-12-01 | 0.15
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF110019 | Kennel |  |  |  |  | 2012-10-03 | 2012-09-10 | 2014-12-01 | 0.15
2015-09-08 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | KYJM129022 | Add Simulator Bay, Building 191 |  |  |  |  | 2013-12-16 | 2014-09-26 | 2015-06-30 | 1 | 2015-06-30
2015-09-08 | 2012 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ120572 | Vehicle Maintenance Facility |  |  |  |  | 2014-09-22 | 2016-03-15 | 2015-07-31 | 0.82
2015-09-08 | 2013 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ099095 | Flight Simulator Facility |  |  |  |  | 2014-08-05 | 2015-07-31 | 2016-01-15 | 0.02
2015-09-08 | 2012 | Air Force Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX079003 | Red Horse Readiness And Training Facility |  |  |  |  | 2012-07-13 | 2013-03-01 | 2015-12-15 | 0.92
2015-09-08 | 2011 | Air National Guard | Major construction | ALABAMA | UNITED STATES | FAKZ959574 | Fuel Cell and Corrosion Control Hangar |  |  |  |  | 2011-10-12 | 2013-01-22 | 2015-08-31 | 1 | 2013-11-01
2015-09-08 | 2014 | Air National Guard | Major construction | ALABAMA | UNITED STATES | BRKR999147 | Add to and Alter Distributed Ground Station Facility |  |  |  |  | 2014-10-31 | 2016-10-23 | 2016-08-02 | 0.15 | 2016-08-02
2015-09-08 | 2011 | Air National Guard | Major construction | ARIZONA | UNITED STATES | HFHA069130 | TFI - Predator LRE Beddown |  |  |  |  | 2013-04-08 | 2014-06-02 | 2015-09-25 | 0.98 | 2015-02-13
2015-09-08 | 2012 | Air National Guard | Major construction | CALIFORNIA | UNITED STATES | QMSN019029 | Replace Pararescue Training Facility |  |  |  |  | 2012-11-25 | 2014-02-23 | 2015-03-13 | 1 | 2015-02-13
2015-09-08 | 2013 | Air National Guard | Major construction | CALIFORNIA | UNITED STATES | HAYW109006 | F-15 Conversion |  |  |  |  | 2013-11-01 | 2016-02-25 | 2016-01-20 | 0.85 | 2016-01-20
2015-09-08 | 2015 | Air National Guard | Major construction | CONNECTICUT | UNITED STATES | CEKT139004 | Construct C-130 Fuel Cell and Corrosion Control Facility |  |  |  |  | 2015-07-24 | 2016-12-05 | 2016-12-23 | 0.05 | 2016-12-23
2015-09-08 | 2011 | Air National Guard | Major construction | FLORIDA | UNITED STATES | LSGA029009A | Security Forces Training Facility |  |  |  |  | 2011-08-05 | 2012-12-03 | 2015-06-08 | 1 | 2015-04-08
2015-09-08 | 2012 | Air National Guard | Minor construction | GEORGIA | UNITED STATES | XDQU129062 | Vehicle Maintenance Addition |  |  |  |  | 2012-08-17 | 2013-02-13 | 2014-10-28 | 1 | 2013-09-30
2015-09-08 | 2011 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069209 | TFI - F-22 Hangar, Squadron Operations and AMU |  | 2001000 | KNMD069215; |  | 2011-07-15 | 2016-02-01 | 2016-01-11 | 0.98 | 2016-01-11
2015-09-08 | 2011 | Air National Guard | Minor construction | HAWAII | UNITED STATES | KNMD109032 | TFI- F-22 Beddown- Add to Communication Facility |  |  |  |  | 2012-06-17 | 2014-06-07 | 2014-11-25 | 1 | 2014-11-25
2015-09-08 | 2012 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron |  |  |  |  | 2012-08-08 | 2015-03-29 | 2015-06-24 | 1 | 2015-06-24
2015-09-08 | 2012 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069212 | TFI - F-22 Flight Simulator Facility |  |  |  |  | 2012-06-17 | 2014-06-07 | 2014-11-25 | 1 | 2014-11-25
2015-09-08 | 2012 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069213 | TFI - F-22 Weapons Load Crew Training Facility |  |  |  |  | 2012-06-17 | 2014-06-07 | 2014-11-25 | 1 | 2014-11-25
2015-09-08 | 2013 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD119001 | TFI - F-22 Combat Apron Addition |  |  |  |  | 2013-10-31 | 2015-04-24 | 2015-09-30 | 1 | 2015-09-30
2015-09-08 | 2012 | Air National Guard | Major construction | INDIANA | UNITED STATES | ATQZ099080 | A-10 Facility Conversion - Munitions Complex |  |  |  |  | 2014-08-27 | 2015-11-20 | 2015-12-31 | 0.42 | 2015-12-31
2015-09-08 | 2013 | Air National Guard | Minor construction | INDIANA | UNITED STATES | ATQZ099073 | MCCA: A-10 Conversion-Expand Arm/Disarm Apron-T/W Bravo |  |  |  |  | 2014-11-12 | 2016-05-21 | 2015-08-31 | 0.98 | 2015-07-09
2015-09-08 | 2014 | Air National Guard | Major construction | INDIANA | UNITED STATES | LDXF099060 | Add/Alter Bldg 37 for Distributed Common Grnd Stn |  |  |  |  | 2014-10-16 | 2016-02-28 | 2016-06-30 | 0.29 | 2016-06-30
2015-09-08 | 2012 | Air National Guard | Minor construction | MAINE | UNITED STATES | FKNN049094 | Pavements and Grounds Facility |  |  |  |  | 2012-09-19 | 2013-03-18 | 2014-11-14 | 1 | 2013-11-25
2015-09-08 | 2011 | Air National Guard | Major construction | MARYLAND | UNITED STATES | PJMS909928 | Replace Operations and Medical Training Facility |  |  |  |  | 2012-07-20 | 2013-10-18 | 2015-09-30 | 1 | 2014-02-28
2015-09-08 | 2012 | Air National Guard | Minor construction | MASSACHUSETTS | UNITED STATES | AXQD119004 | Add to and Alter Survival Equipment Shop |  |  |  |  | 2013-07-16 | 2014-02-07 | 2015-02-28 | 1 | 2015-01-31
2015-09-08 | 2012 | Air National Guard | Minor construction | MASSACHUSETTS | UNITED STATES | AXQD129074 | F 15 Shop Addition |  |  |  |  | 2015-01-13 | 2016-07-16 | 2016-06-17 | 0.03 | 2016-07-16
2015-09-08 | 2012 | Air National Guard | Major construction | MASSACHUSETTS | UNITED STATES | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities |  |  |  |  | 2013-09-24 | 2014-09-24 | 2015-09-04 | 0.75 | 2015-07-24
2015-09-08 | 2015 | Air National Guard | Major construction | MICHIGAN | UNITED STATES | MBMV129060 | RPA Beddown |  |  |  |  | 2015-05-07 | 2016-05-14 | 2016-05-06 | 0.14 | 2016-05-06
2015-09-08 | 2014 | Air National Guard | Minor construction | MISSOURI | UNITED STATES | ULYB112022 | Security Forces Admin and Storage Facility |  |  |  |  | 2014-10-29 | 2015-10-12 | 2016-05-05 | 0.77 | 2015-11-04
2015-09-08 | 2014 | Air National Guard | Major construction | MONTANA | UNITED STATES | JKSE129321 | Intra-Theater Airlift Conversion |  |  |  |  | 2014-10-20 | 2016-10-15 | 2016-09-15 | 0.54 | 2015-08-31
2015-09-08 | 2013 | Air National Guard | Major construction | NEW MEXICO | UNITED STATES | MHMV119001 | Alter Target Intelligence Facility |  |  |  |  | 2014-01-27 | 2015-01-27 | 2015-07-21 | 1 | 2015-07-21
2015-09-08 | 2012 | Air National Guard | Minor construction | NEW YORK | UNITED STATES | WKVB099052 | Add to Fire Station |  |  |  |  | 2015-06-26 | 2016-04-23 | 2016-06-28 | 0.03 | 2016-06-28
2015-09-08 | 2011 | Air National Guard | Major construction | NEW YORK | UNITED STATES | WHAY089079 | Base Defense Group Beddown |  |  |  |  | 2011-10-13 | 2013-05-05 | 2015-09-25 | 0.98 | 2014-09-05
2015-09-08 | 2011 | Air National Guard | Major construction | NEW YORK | UNITED STATES | FPBB109013 | TFI - Reaper Infrastructure Support |  |  |  |  | 2012-10-17 | 2013-10-12 | 2014-10-20 | 1 | 2014-06-16
2015-09-08 | 2014 | Air National Guard | Major construction | NEW YORK | UNITED STATES | FPBB129050 | MQ-9 Flight Training Unit Hangar |  |  |  |  | 2014-09-25 | 2015-08-04 | 2015-09-21 | 0.8 | 2015-09-21
2015-09-08 | 2011 | Air National Guard | Major construction | NORTH CAROLINA | UNITED STATES | WEFM089029 | Upgrade ASOS Facilities |  |  |  |  | 2011-10-24 | 2012-07-21 | 2015-07-01 | 1 | 2013-03-25
2015-09-08 | 2013 | Air National Guard | Minor construction | NORTH CAROLINA | UNITED STATES | FJRP079016 | BCE pavements and Grounds Facility |  |  |  |  | 2014-06-01 | 2015-03-03 | 2015-06-01 | 1 | 2015-06-01
2015-09-08 | 2012 | Air National Guard | Minor construction | OHIO | UNITED STATES | WAAR129078 | Relocate Main Gate |  |  |  |  | 2013-08-27 | 2014-02-23 | 2015-12-31 | 0.95 | 2014-10-31
2015-09-08 | 2013 | Air National Guard | Minor construction | OHIO | UNITED STATES | WYTD139000 | Construct Security Forces |  |  |  |  | 2014-07-08 | 2015-04-04 | 2015-09-30 | 0.95 | 2015-06-29
2015-09-08 | 2014 | Air National Guard | Major construction | OHIO | UNITED STATES | WAAR109002 | Alter Intelligence Operations Facility |  |  |  |  | 2014-12-01 | 2015-12-01 | 2016-01-08 | 0.65 | 2015-11-30
2015-09-08 | 2014 | Air National Guard | Minor construction | OKLAHOMA | UNITED STATES | XHZG129946 | Add to Fire Crash and Rescue Station, Building 403 |  |  |  |  | 2014-08-20 | 2015-08-15 | 2015-08-20 | 0.81 | 2015-08-20
2015-09-08 | 2013 | Air National Guard | Minor construction | OREGON | UNITED STATES | TQKD139018 | Relocate Base Boundary Fence |  |  |  |  | 2015-02-02 | 2015-08-01 | 2015-09-15 | 0.79 | 2015-09-15
2015-09-08 | 2012 | Air National Guard | Minor construction | OREGON | UNITED STATES | KJAQ119031 | Addition Squadron Operations Facility |  |  |  |  | 2014-03-12 | 2014-11-10 | 2015-09-25 | 1 | 2015-08-28
2015-09-08 | 2012 | Air National Guard | Minor construction | OREGON | UNITED STATES | TQKD129072 | Construct Alert Hangar Bay |  |  |  |  | 2014-09-03 | 2015-03-19 | 2015-09-15 | 0.95 | 2015-07-30
2015-09-08 | 2014 | Air National Guard | Major construction | PENNSYLVANIA | UNITED STATES | LKLW109037 | Communications Operations and Training Facility |  |  |  |  | 2014-10-16 | 2015-10-25 | 2015-10-25 | 0.35 | 2015-10-16
2015-09-08 | 2015 | Air National Guard | Major construction | PENNSYLVANIA | UNITED STATES | ZAWA159061 | RPA Operations Center |  |  |  |  | 2015-07-20 | 2016-02-15 | 2016-01-26 | 0.05
2015-09-08 | 2012 | Air National Guard | Minor construction | PUERTO RICO | PUERTO RICO | TUMR109004 | Joint Force HQ - ANG Share Fort Buchanan |  |  |  |  | 2013-11-25 | 2015-10-06 | 2015-10-14 | 0.7
2015-09-08 | 2014 | Air National Guard | Major construction | RHODE ISLAND | UNITED STATES | TWLR129077 | C-130J Flight Simulator Training Facility |  |  |  |  | 2015-03-15 | 2015-12-14 | 2015-11-14 | 0.27
2015-09-08 | 2014 | Air National Guard | Minor construction | SOUTH CAROLINA | UNITED STATES | PSTE129092 | Construct North Overrun |  |  |  |  | 2014-03-11 | 2014-12-24 | 2015-07-31 | 1 | 2014-12-08
2015-09-08 | 2011 | Air National Guard | Major construction | TENNESSEE | UNITED STATES | BKTZ069078 | TFI- Renovate Intel Squadron Facilities |  |  |  |  | 2013-12-02 | 2014-10-17 | 2015-06-15 | 1 | 2015-03-31
2015-09-08 | 2014 | Air National Guard | Major construction | TENNESSEE | UNITED STATES | PSXE109034 | TEC Expansion - Dormitory and Classroom Training Facility |  |  |  |  | 2014-07-22 | 2016-07-21 | 2016-07-20 | 0.38 | 2016-07-20
2015-09-08 | 2014 | Air National Guard | Minor construction | WASHINGTON | UNITED STATES | GJKZ129093 | Construct 2 Set DRBS Storage Facility |  |  |  |  | 2014-09-18 | 2015-03-17 | 2015-09-23 | 0.85 | 2015-09-23
2015-09-08 | 2011 | Air National Guard | Minor construction | WYOMING | UNITED STATES | DPEZ089083 | Relocate ROSC |  |  |  |  | 2012-04-25 | 2012-10-22 | 2015-05-29 | 1 | 2013-07-31
2015-09-08 | 2013 | Air National Guard | Major construction | WYOMING | UNITED STATES | DPEZ089017 | C-130 Flight Simulator Training Facility |  |  |  |  | 2013-09-27 | 2015-03-21 | 2015-11-27 | 0.98 | 2015-11-27
2015-09-10 | 2009 | Army Active | Major Military Construction |  | AFGHANISTAN | 72125 | SOF Alpha Ramp Facilities |  |  |  |  | 2010-03-17 | 2013-08-13 | 2014-07-26 | 0.98 | 2014-11-23
2015-09-10 | 2009 | Army Active | Major Military Construction |  | AFGHANISTAN | 72125 | SOF Alpha Ramp Facilities | 25 |  |  |  | 2010-03-17 | 2013-08-13 | 2014-07-26 | 0.98 | 2014-11-23
2015-09-10 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 71488 | Coalition Operation Center |  |  |  |  | 2012-03-16 | 2014-09-14 | 2015-12-06 | 0.99 | 2015-06-29
2015-09-10 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 71488 | Coalition Operation Center | 51 |  |  |  | 2012-03-16 | 2014-09-14 | 2015-12-06 | 0.99 | 2015-06-29
2015-09-10 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 72477 | USFOR-A Headquarters & Housing |  |  |  |  | 2011-09-09 | 2013-12-07 | 2014-11-10 | 0.97 | 2015-03-18
2015-09-10 | 2011 | Army Active | Major Military Construction |  | AFGHANISTAN | 71604 | Eastside Utilities Infrastructure |  |  |  |  | 2012-10-18 | 2014-06-05 | 2015-01-31 | 0.99 | 2015-03-13
2015-09-10 | 2011 | Army Active | Unspecified Minor Military Construction |  | AFGHANISTAN | 79762 | PRIMARY WASTE WATER TREATMENT |  |  |  |  | 2011-09-09 | 2013-12-07 | 2014-11-10 | 1 | 2015-03-18
2015-09-10 | 2011 | Army Active | Unspecified Minor Military Construction |  | AFGHANISTAN | 79770 | WATER WELL, POTABLE |  |  |  |  | 2011-09-09 | 2013-12-07 | 2014-11-10 | 1 | 2015-03-18
2015-09-10 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 71569 | Westside Utilities Infrastructure |  |  |  |  | 2012-12-12 | 2014-03-07 | 2014-09-01 | 0.99 | 2014-12-20
2015-09-10 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74067 | Construct Drainage System, Ph 3 |  |  |  |  | 2012-10-09 | 2014-06-01 | 2014-12-28 | 1 | 2015-02-17
2015-09-10 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74084 | Barracks, Ph 5 |  |  |  |  | 2012-06-08 | 2014-04-19 | 2014-11-17 | 1 | 2014-09-18
2015-09-10 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 80001 | Waste Management Complex (60 Tons) |  |  |  |  | 2012-11-14 | 2014-03-27 | 2014-12-15 | 1 | 2014-08-08
2015-09-10 | 2008 | Army Active | Major Military Construction |  | BULGARIA | 63714 | Base Camp |  |  |  |  | 2008-11-03 | 2014-09-03 | 2016-04-29 | 0.94 | 2015-06-08
2015-09-10 | 2008 | Army Active | Major Military Construction |  | BULGARIA | 63714 | Base Camp | 7 |  |  |  | 2008-11-03 | 2014-09-03 | 2016-04-29 | 0.94 | 2015-06-08
2015-09-10 | 2009 | Army Active | Major Military Construction |  | GERMANY | 53874 | Child Youth Services Center |  |  |  |  | 2012-08-14 | 2014-03-19 | 2014-04-11 | 0.98 | 2014-12-01
2015-09-10 | 2010 | Army Active | Military Family Housing |  | GERMANY | 71421 | Family Housing Replacement Construction |  |  |  |  | 2015-04-07 | 2017-04-23 | 2017-04-23 | 0.04
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 59434 | Physical Fitness Center |  |  |  |  | 2012-11-30 | 2014-11-28 | 2014-11-28 | 0.96 | 2014-12-18
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 60555 | Information Processing Center |  |  |  |  | 2012-06-18 | 2014-06-01 | 2014-11-07 | 0.99
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66465 | Confinement Facility |  |  |  |  | 2013-04-29 | 2014-12-15 | 2014-12-19 | 0.99 | 2014-11-20
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66595 | Barracks Complex |  |  |  |  | 2015-03-23 | 2017-09-28 | 2017-09-28 | 0.09
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66834 | Vehicle Maintenance Shop |  |  |  |  | 2011-12-12 | 2013-12-18 | 2015-07-31 | 0.96 | 2015-08-14
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68074 | Construct New ACP |  |  |  |  | 2014-03-05 | 2014-12-12 | 2014-12-12 | 1 | 2015-01-09
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68866 | Sensitive Compartmented Information Fac |  |  |  |  | 2013-02-13 | 2015-09-19 | 2015-10-31 | 0.38
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68866 | Sensitive Compartmented Information Fac | 93 |  |  |  | 2013-02-13 | 2015-09-19 | 2015-10-31 | 0.38
2015-09-10 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68866 | Sensitive Compartmented Information Fac | 94 |  |  |  | 2013-02-13 | 2015-09-19 | 2015-10-31 | 0.38
2015-09-10 | 2011 | Army Active | Military Family Housing |  | GERMANY | 71422 | Family Housing Replacement Construction |  |  |  |  | 2015-04-07 | 2015-09-24 | 2015-09-24 | 0.04
2015-09-10 | 2012 | Army Active | Major Military Construction |  | GERMANY | 55985 | Chapel |  |  |  |  | 2013-11-21 | 2016-03-23 | 2016-03-23 | 0.51
2015-09-10 | 2012 | Army Active | Major Military Construction |  | GERMANY | 57594 | Satellite Communications Center |  |  |  |  | 2014-03-14 | 2015-10-05 | 2015-12-19 | 0.7
2015-09-10 | 2012 | Army Active | Major Military Construction |  | GERMANY | 58925 | Satellite Communications Center |  |  |  |  | 2014-10-16 | 2016-07-07 | 2016-07-07 | 0.26
2015-09-10 | 2012 | Army Active | Major Military Construction |  | GERMANY | 61842 | Access Control Point |  |  |  |  | 2015-05-11 | 2016-12-01 | 2016-12-01 | 0.11
2015-09-10 | 2012 | Army Active | Major Military Construction |  | GERMANY | 69614 | Barracks |  |  |  |  | 2013-03-27 | 2014-12-31 | 2015-06-08 | 0.91 | 2015-03-06
2015-09-10 | 2012 | Army Active | Major Military Construction |  | GERMANY | 69615 | Barracks |  | 2210000 | 66745 |  | 2012-10-10 | 2014-08-27 | 2014-09-25 | 0.98 | 2014-10-25
2015-09-10 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78475 | Family Housing Improvements |  |  |  |  | 2015-01-16 | 2016-06-09 | 2016-06-09 | 0.11
2015-09-10 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78505 | Family Housing New Construction |  |  |  |  | 2013-08-07 | 2015-09-14 | 2015-09-14 | 0.68
2015-09-10 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78506 | Family Housing New Construction |  |  |  |  | 2013-09-30 | 2015-09-14 | 2015-09-14 | 0.81
2015-09-10 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78841 | Family Housing Improvements |  | 6885000 | 74861 |  | 2012-10-15 | 2018-10-29 | 2019-05-16 | 0.53
2015-09-10 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78841 | Family Housing Improvements | 231 | 6885000 | 74861 |  | 2012-10-15 | 2018-10-29 | 2019-05-16 | 0.53
2015-09-10 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 79097 | Family Housing Improvements |  |  |  |  | 2012-10-15 | 2018-04-02 | 2018-11-09 | 0.49
2015-09-10 | 2011 | Army Active | Major Military Construction |  | HONDURAS | 61383 | Barracks |  |  |  |  | 2012-01-10 | 2014-01-09 | 2014-09-24 | 0.98 | 2015-02-13
2015-09-10 | 2013 | Army Active | Major Military Construction |  | JAPAN | 62783 | Satellite Communications Facility |  |  |  |  | 2014-11-21 | 2021-06-09 | 2021-12-06 | 0.07
2015-09-10 | 2008 | Army Active | Major Military Construction |  | KOREA, SOUTH | 58784 | Barracks Complex |  |  |  |  | 2008-04-22 | 2014-09-07 | 2015-06-09 | 0.96
2015-09-10 | 2008 | Army Active | Major Military Construction |  | KOREA, SOUTH | 58784 | Barracks Complex | 4 |  |  |  | 2008-04-22 | 2014-09-07 | 2015-06-09 | 0.96
2015-09-10 | 2008 | Army Active | Major Military Construction |  | KOREA, SOUTH | 58784 | Barracks Complex | 5 |  |  |  | 2008-04-22 | 2014-09-07 | 2015-06-09 | 0.96
2015-09-10 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 72650 | Barracks |  |  |  |  | 2012-02-24 | 2015-12-05 | 2015-11-26 | 0.93
2015-09-10 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 72650 | Barracks | 208 |  |  |  | 2012-02-24 | 2015-12-05 | 2015-11-26 | 0.93
2015-09-10 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76235 | Barracks Complex |  | 16000000 | 66745, 80087 |  | 2012-02-09 | 2014-07-02 | 2014-12-03 | 1 | 2014-12-05
2015-09-10 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76235 | Barracks Complex | 212 | 16000000 | 66745, 80087 |  | 2012-02-09 | 2014-07-02 | 2014-12-03 | 1 | 2014-12-05
2015-09-10 | 2013 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76196 | Battalion Headquarters Complex |  |  |  |  | 2013-05-14 | 2015-06-09 | 2016-05-29 | 0.4
2015-09-10 | 2015 | Army Active | Military Family Housing |  | KOREA, SOUTH | 81230 | Family Housing New Construction |  |  |  |  | 2015-08-19 | 2018-04-28 | 2018-04-28 | 0
2015-09-10 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses |  | 11339000 | 58925, 62783 |  | 2013-10-25 | 2015-10-30 | 2015-10-30 | 0.69
2015-09-10 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses | 49 | 11339000 | 58925, 62783 |  | 2013-10-25 | 2015-10-30 | 2015-10-30 | 0.69
2015-09-10 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 61515 | Physical Fitness Facility |  |  |  |  | 2013-03-16 | 2014-12-06 | 2015-06-26 | 0.88
2015-09-10 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67113 | Aviation Complex, Ph 3A |  |  |  |  | 2012-06-14 | 2014-08-03 | 2014-10-09 | 1 | 2014-11-10
2015-09-10 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex |  |  |  |  | 2014-04-23 | 2016-09-06 | 2016-09-06 | 0.58
2015-09-10 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex | 315 |  |  |  | 2014-04-23 | 2016-09-06 | 2016-09-06 | 0.58
2015-09-10 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex | 316 |  |  |  | 2014-04-23 | 2016-09-06 | 2016-09-06 | 0.58
2015-09-10 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar |  |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 0.46
2015-09-10 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar | 334 |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 0.46
2015-09-10 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar | 335 |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 0.46
2015-09-10 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar | 336 |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 0.46
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 79679 | Materials Analysis Lab |  |  |  |  | 2014-07-28 | 2015-09-01 | 2015-09-01 | 0.85
2015-09-10 | 2010 | Army Active | Major Military Construction | ARKANSAS | UNITED STATES | 67106 | Fuse & Detonator Magazine, Depot Level |  |  |  |  | 2010-02-22 | 2012-02-22 | 2015-01-20 | 1 | 2013-01-31
2015-09-10 | 2009 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60859 | Water Treatment Plant |  |  |  |  | 2009-06-17 | 2010-12-09 | 2014-10-31 | 1 | 2011-07-24
2015-09-10 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 53789 | Advanced Individual Training Barracks |  |  |  |  | 2013-10-22 | 2015-01-05 | 2016-02-17 | 0.08
2015-09-10 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60285 | General Instruction Building |  |  |  |  | 2011-06-07 | 2015-07-14 | 2015-07-14 | 0.99 | 2014-09-08
2015-09-10 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60285 | General Instruction Building | 74 |  |  |  | 2011-06-07 | 2015-07-14 | 2015-07-14 | 0.99 | 2014-09-08
2015-09-10 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility |  |  |  |  | 2011-09-21 | 2016-06-30 | 2016-06-30 | 0.14
2015-09-10 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility | 80 |  |  |  | 2011-09-21 | 2016-06-30 | 2016-06-30 | 0.14
2015-09-10 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 56425 | General Instruction Building |  |  |  |  | 2012-11-06 | 2013-11-06 | 2014-05-11 | 0.9 | 2015-01-02
2015-09-10 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 62657 | Water Treatment Plant |  |  |  |  | 2012-10-19 | 2015-10-19 | 2016-01-12 | 0.87
2015-09-10 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76086 | Lightning Protection System |  |  |  |  | 2014-09-16 | 2015-11-10 | 2016-07-17 | 0.02
2015-09-10 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76091 | Engineering/Housing Maintenance Shop |  |  |  |  | 2014-10-08 | 2015-11-12 | 2015-11-12 | 0.36
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 81367 | EXPLOSIVES RECEIVING/SERVICE BUILDING, DEP |  |  |  |  | 2014-05-08 | 2015-05-08 | 2015-05-08 | 0.98
2015-09-10 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79652 | Radar Security and Support Facilities |  |  |  |  | 2012-09-27 | 2014-11-30 | 2014-11-30 | 0.95 | 2014-11-19
2015-09-10 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79652 | Radar Security and Support Facilities | 234 |  |  |  | 2012-09-27 | 2014-11-30 | 2014-11-30 | 0.95 | 2014-11-19
2015-09-10 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79749 | Forward Operating Site |  |  |  |  | 2012-07-25 | 2014-11-30 | 2015-02-18 | 0.64
2015-09-10 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79749 | Forward Operating Site | 236 |  |  |  | 2012-07-25 | 2014-11-30 | 2015-02-18 | 0.64
2015-09-10 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79749 | Forward Operating Site | 237 |  |  |  | 2012-07-25 | 2014-11-30 | 2015-02-18 | 0.64
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 65602 | Brigade Headquarters |  | 1700000 | 66745 |  | 2012-04-18 | 2015-02-08 | 2015-03-16 | 1 | 2014-08-15
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 65602 | Brigade Headquarters | 170 | 1700000 | 66745 |  | 2012-04-18 | 2015-02-08 | 2015-03-16 | 1 | 2014-08-15
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 65602 | Brigade Headquarters | 171 | 1700000 | 66745 |  | 2012-04-18 | 2015-02-08 | 2015-03-16 | 1 | 2014-08-15
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77264 | Barracks |  |  |  |  | 2013-05-29 | 2015-02-08 | 2015-03-16 | 0.99 | 2015-03-16
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77265 | Barracks |  |  |  |  | 2013-05-29 | 2015-02-08 | 2015-03-16 | 0.97 | 2015-03-16
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77302 | Control Tower |  |  |  |  | 2012-08-27 | 2015-02-08 | 2015-03-16 | 0.99 | 2014-03-31
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77302 | Control Tower | 223 |  |  |  | 2012-08-27 | 2015-02-08 | 2015-03-16 | 0.99 | 2014-03-31
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar |  | 1235000 | 55121 |  | 2012-08-23 | 2015-02-08 | 2015-03-16 | 1 | 2014-10-31
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar | 225 | 1235000 | 55121 |  | 2012-08-23 | 2015-02-08 | 2015-03-16 | 1 | 2014-10-31
2015-09-10 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar | 226 | 1235000 | 55121 |  | 2012-08-23 | 2015-02-08 | 2015-03-16 | 1 | 2014-10-31
2015-09-10 | 2013 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 59626 | Digital Multipurpose Training Range |  |  |  |  | 2013-09-18 | 2015-03-12 | 2015-08-06 | 0.97 | 2015-08-28
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81300 | AIRCRAFT MAINTENANCE HANGAR |  |  |  |  | 2013-10-29 | 2014-08-25 | 2014-12-22 | 1 | 2015-01-21
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 71221 | Fire Station |  |  |  |  | 2014-08-27 | 2016-02-18 | 2016-06-01 | 0.37
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building |  |  |  |  | 2014-08-21 | 2016-03-31 | 2016-05-29 | 0.35
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building | 342 |  |  |  | 2014-08-21 | 2016-03-31 | 2016-05-29 | 0.35
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar |  |  |  |  | 2014-08-18 | 2016-08-22 | 2016-09-08 | 0.37
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar | 344 |  |  |  | 2014-08-18 | 2016-08-22 | 2016-09-08 | 0.37
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar | 345 |  |  |  | 2014-08-18 | 2016-08-22 | 2016-09-08 | 0.37
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar | 346 |  |  |  | 2014-08-18 | 2016-08-22 | 2016-09-08 | 0.37
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar |  |  |  |  | 2014-07-22 | 2016-08-22 | 2016-09-16 | 0.16
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar | 348 |  |  |  | 2014-07-22 | 2016-08-22 | 2016-09-16 | 0.16
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar | 349 |  |  |  | 2014-07-22 | 2016-08-22 | 2016-09-16 | 0.16
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar | 350 |  |  |  | 2014-07-22 | 2016-08-22 | 2016-09-16 | 0.16
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77885 | Runway |  |  |  |  | 2014-07-01 | 2015-07-01 | 2015-11-08 | 0.61
2015-09-10 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 79618 | Simulator Building |  |  |  |  | 2014-08-20 | 2016-02-11 | 2016-06-08 | 0.2
2015-09-10 | 2015 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 81357 | Unmanned Aerial Vehicle Hangar |  |  |  |  | 2015-08-27 | 2017-01-18 | 2017-01-18 | 0
2015-09-10 | 2015 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 81357 | Unmanned Aerial Vehicle Hangar | 369 |  |  |  | 2015-08-27 | 2017-01-18 | 2017-01-18 | 0
2015-09-10 | 2013 | Army Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 78054 | Vehicle Storage Building, Installation |  |  |  |  | 2015-04-03 | 2016-09-24 | 2016-09-24 | 0.02
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE |  |  |  |  | 2014-07-15 | 2015-04-28 | 2015-07-31 | 0.97
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE | 303 |  |  |  | 2014-07-15 | 2015-04-28 | 2015-07-31 | 0.97
2015-09-10 | 2011 | Army Active | Major Military Construction | FLORIDA | UNITED STATES | 61533 | Command and Control Facility |  |  |  |  | 2011-09-20 | 2014-10-06 | 2014-10-06 | 1 | 2014-03-07
2015-09-10 | 2014 | Army Active | Major Military Construction | FLORIDA | UNITED STATES | 77539 | Automated Sniper Field Fire Range |  |  |  |  | 2014-12-17 | 2015-12-17 | 2015-12-17 | 0.38
2015-09-10 | 2010 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 66011 | Forensic Lab |  |  |  |  | 2010-08-23 | 2015-06-13 | 2015-06-13 | 1 | 2015-05-27
2015-09-10 | 2010 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 66011 | Forensic Lab | 33 |  |  |  | 2010-08-23 | 2015-06-13 | 2015-06-13 | 1 | 2015-05-27
2015-09-10 | 2010 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69150 | Training Battalion Complex |  |  |  |  | 2010-05-12 | 2015-01-26 | 2015-08-12 | 0.99 | 2011-12-21
2015-09-10 | 2010 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69150 | Training Battalion Complex | 40 |  |  |  | 2010-05-12 | 2015-01-26 | 2015-08-12 | 0.99 | 2011-12-21
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69830 | Aviation Unit Operations Complex |  |  |  |  | 2011-07-27 | 2015-08-01 | 2015-08-25 | 0.98 | 2015-04-28
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69830 | Aviation Unit Operations Complex | 98 |  |  |  | 2011-07-27 | 2015-08-01 | 2015-08-25 | 0.98 | 2015-04-28
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69830 | Aviation Unit Operations Complex | 99 |  |  |  | 2011-07-27 | 2015-08-01 | 2015-08-25 | 0.98 | 2015-04-28
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72324 | Trainee Barracks Ph 2 |  |  |  |  | 2011-08-18 | 2014-05-08 | 2014-09-12 | 0.98 | 2015-02-28
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72324 | Trainee Barracks Ph 2 | 115 |  |  |  | 2011-08-18 | 2014-05-08 | 2014-09-12 | 0.98 | 2015-02-28
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72324 | Trainee Barracks Ph 2 | 116 |  |  |  | 2011-08-18 | 2014-05-08 | 2014-09-12 | 0.98 | 2015-02-28
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72324 | Trainee Barracks Ph 2 | 117 |  |  |  | 2011-08-18 | 2014-05-08 | 2014-09-12 | 0.98 | 2015-02-28
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72457 | Training Battalion Complex, Ph 2 |  |  |  |  | 2011-10-13 | 2015-05-11 | 2015-05-11 | 0.99 | 2015-04-24
2015-09-10 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72457 | Training Battalion Complex, Ph 2 | 119 |  |  |  | 2011-10-13 | 2015-05-11 | 2015-05-11 | 0.99 | 2015-04-24
2015-09-10 | 2012 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69745 | Trainee Barracks Complex, Ph 3 |  | 690000 | 66745 |  | 2012-05-18 | 2014-08-23 | 2014-12-17 | 1 | 2013-11-22
2015-09-10 | 2012 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69745 | Trainee Barracks Complex, Ph 3 | 197 | 690000 | 66745 |  | 2012-05-18 | 2014-08-23 | 2014-12-17 | 1 | 2013-11-22
2015-09-10 | 2012 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69745 | Trainee Barracks Complex, Ph 3 | 198 | 690000 | 66745 |  | 2012-05-18 | 2014-08-23 | 2014-12-17 | 1 | 2013-11-22
2015-09-10 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 57794 | Digital Multipurpose Training Range |  |  |  |  | 2014-02-04 | 2015-04-30 | 2015-07-06 | 0.95
2015-09-10 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 73008 | Unmanned Aerial Vehicle Complex |  |  |  |  | 2013-11-06 | 2015-03-01 | 2015-06-25 | 0.93
2015-09-10 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 77416 | Ground Source Heat Transfer System |  |  |  |  | 2013-07-12 | 2015-01-03 | 2015-03-04 | 0.99 | 2015-04-16
2015-09-10 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 77419 | Ground Source Heat Transfer System |  |  |  |  | 2015-01-06 | 2016-12-26 | 2017-01-09 | 0.26
2015-09-10 | 2014 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 51868 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  |  | 2015-01-06 | 2016-12-26 | 2017-01-09 | 0.14
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | 85260 | Secure Operations Center |  |  |  |  | 2014-11-05 | 2015-11-05 | 2015-11-05 | 0.6
2015-09-10 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68786 | Brigade Complex |  |  |  |  | 2011-04-15 | 2014-03-14 | 2014-10-31 | 0.99 | 2015-03-31
2015-09-10 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68821 | Battalion Complex |  |  |  |  | 2011-04-15 | 2014-03-14 | 2014-10-31 | 0.97 | 2015-03-31
2015-09-10 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68822 | Battalion Complex |  | 12682000 | 68866 |  | 2011-04-15 | 2014-03-14 | 2014-10-31 | 1 | 2015-03-31
2015-09-10 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69308 | Infrastructure Expansion |  |  |  |  | 2011-04-15 | 2014-03-14 | 2014-10-31 | 0.97 | 2015-03-31
2015-09-10 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 52269 | Barracks |  | 5750000 | 65374, 78054 |  | 2011-10-17 | 2014-07-16 | 2015-05-22 | 0.99 | 2014-12-01
2015-09-10 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 56024 | Flood Mitigation |  |  |  |  | 2012-10-17 | 2014-10-14 | 2015-04-26 | 0.88 | 2015-06-30
2015-09-10 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64760 | Training Aids Center |  |  |  |  | 2012-10-31 | 2014-08-17 | 2014-09-26 | 0.9 | 2015-07-20
2015-09-10 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 65650 | Command and Control Facility, Ph 1 |  |  |  |  | 2012-04-03 | 2014-04-23 | 2015-02-20 | 0.98
2015-09-10 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 59581 | Centralized Wash Facility |  |  |  |  | 2012-02-08 | 2013-12-14 | 2014-09-16 | 0.99 | 2015-03-02
2015-09-10 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64967 | Child Development Center |  |  |  |  | 2012-03-23 | 2013-12-13 | 2015-09-30 | 0.98 | 2015-07-31
2015-09-10 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69489 | Combat Aviation Brigade Complex, Ph 1 |  |  |  |  | 2012-07-30 | 2015-05-27 | 2015-06-11 | 0.66
2015-09-10 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 66023 | Automated Infantry Platoon Battle Course |  |  |  |  | 2014-07-08 | 2016-09-09 | 2016-10-12 | 0.55
2015-09-10 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76586 | Barracks |  |  |  |  | 2013-07-23 | 2015-09-01 | 2016-06-01 | 0.75
2015-09-10 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76587 | Barracks |  |  |  |  | 2013-07-23 | 2015-09-01 | 2016-06-01 | 0.72
2015-09-10 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76903 | Combat Aviation Brigade Barracks |  |  |  |  | 2014-06-26 | 2017-01-13 | 2017-04-13 | 0.11
2015-09-10 | 2014 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 67157 | Command and Control Facility - Admin |  |  |  |  | 2015-09-08 | 2017-11-26 | 2017-11-26 | 0
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | 80992 | Upgrade Power Distribution |  |  |  |  | 2015-04-29 | 2016-10-20 | 2016-10-20 | 0.06
2015-09-10 | 2010 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 65133 | Brigade Complex |  |  |  |  | 2010-04-29 | 2015-03-08 | 2015-04-20 | 0.99 | 2015-04-17
2015-09-10 | 2010 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 65133 | Brigade Complex | 28 |  |  |  | 2010-04-29 | 2015-03-08 | 2015-04-20 | 0.99 | 2015-04-17
2015-09-10 | 2010 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 65133 | Brigade Complex | 29 |  |  |  | 2010-04-29 | 2015-03-08 | 2015-04-20 | 0.99 | 2015-04-17
2015-09-10 | 2010 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 65133 | Brigade Complex | 30 |  |  |  | 2010-04-29 | 2015-03-08 | 2015-04-20 | 0.99 | 2015-04-17
2015-09-10 | 2010 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 65133 | Brigade Complex | 31 |  |  |  | 2010-04-29 | 2015-03-08 | 2015-04-20 | 0.99 | 2015-04-17
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 2728 | Physical Fitness Facility |  |  |  |  | 2012-03-29 | 2016-09-09 | 2016-09-09 | 0.88 | 2014-11-24
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 2728 | Physical Fitness Facility | 130 |  |  |  | 2012-03-29 | 2016-09-09 | 2016-09-09 | 0.88 | 2014-11-24
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 59148 | Deployment Support Facility |  |  |  |  | 2012-04-10 | 2014-10-10 | 2014-10-10 | 1 | 2014-08-04
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 59148 | Deployment Support Facility | 148 |  |  |  | 2012-04-10 | 2014-10-10 | 2014-10-10 | 1 | 2014-08-04
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 61211 | Chapel |  | 620000 | 55121 |  | 2012-06-29 | 2014-10-28 | 2014-10-28 | 0.99 | 2014-10-27
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 61211 | Chapel | 151 | 620000 | 55121 |  | 2012-06-29 | 2014-10-28 | 2014-10-28 | 0.99 | 2014-10-27
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  |  |  |  | 2012-12-11 | 2015-07-31 | 2015-08-04 | 0.76
2015-09-10 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar | 201 |  |  |  | 2012-12-11 | 2015-07-31 | 2015-08-04 | 0.76
2015-09-10 | 2014 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 76024 | Simulations Center |  |  |  |  | 2014-09-02 | 2016-02-24 | 2016-05-09 | 0.14
2015-09-10 | 2012 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 69501 | Unmanned Aerial Vehicle Maintenance Hangar |  | 10000000 | 66745 |  | 2012-11-05 | 2014-09-06 | 2014-12-14 | 1 | 2014-12-15
2015-09-10 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 5924 | Automated Infantry Squad Battle Course |  |  |  |  | 2013-09-24 | 2014-09-24 | 2014-11-22 | 1 | 2014-09-23
2015-09-10 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex |  |  |  |  | 2013-07-15 | 2015-08-26 | 2015-09-07 | 0.92
2015-09-10 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex | 254 |  |  |  | 2013-07-15 | 2015-08-26 | 2015-09-07 | 0.92
2015-09-10 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 76239 | Unmanned Aerial Vehicle Complex |  |  |  |  | 2013-06-25 | 2015-04-26 | 2015-06-06 | 0.98 | 2015-06-17
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 77980 | Cantonment Area, Roads, Paved |  |  |  |  | 2014-09-24 | 2015-08-20 | 2015-09-19 | 0.54
2015-09-10 | 2014 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 78778 | Battlefield Weather Support Facility |  |  |  |  | 2014-06-27 | 2015-08-21 | 2015-10-09 | 0.53
2015-09-10 | 2015 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 73542 | Unmanned Aerial Vehicle Hangar |  |  |  |  | 2015-09-26 | 2017-05-18 | 2017-05-18 | 0
2015-09-10 | 2008 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 54785 | Child Development Center |  |  |  |  | 2011-09-23 | 2013-01-25 | 2014-12-21 | 0.98 | 2015-07-09
2015-09-10 | 2009 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 69199 | Unit Operations Facilities |  |  |  |  | 2010-11-03 | 2014-08-22 | 2014-08-22 | 0.99 | 2014-10-01
2015-09-10 | 2009 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 69199 | Unit Operations Facilities | 15 |  |  |  | 2010-11-03 | 2014-08-22 | 2014-08-22 | 0.99 | 2014-10-01
2015-09-10 | 2009 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 69199 | Unit Operations Facilities | 16 |  |  |  | 2010-11-03 | 2014-08-22 | 2014-08-22 | 0.99 | 2014-10-01
2015-09-10 | 2009 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 69199 | Unit Operations Facilities | 17 |  |  |  | 2010-11-03 | 2014-08-22 | 2014-08-22 | 0.99 | 2014-10-01
2015-09-10 | 2009 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 69199 | Unit Operations Facilities | 18 |  |  |  | 2010-11-03 | 2014-08-22 | 2014-08-22 | 0.99 | 2014-10-01
2015-09-10 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 17220 | Fire Station |  |  |  |  | 2013-11-06 | 2015-11-11 | 2016-02-02 | 0.47
2015-09-10 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex |  |  |  |  | 2012-05-15 | 2014-04-02 | 2015-07-02 | 0.99 | 2014-11-19
2015-09-10 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex | 164 |  |  |  | 2012-05-15 | 2014-04-02 | 2015-07-02 | 0.99 | 2014-11-19
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 81515 | CIDC FIELD OPERATIONS BUILDING |  |  |  |  | 2013-12-04 | 2014-12-04 | 2015-01-03 | 1 | 2015-01-06
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 82268 | Illinois Ave (PREPO) Yd |  |  |  |  | 2014-12-03 | 2015-04-02 | 2015-05-06 | 0.99 | 2015-07-08
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  |  |  |  | 2014-10-28 | 2015-10-23 | 2015-10-23 | 0.14
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 82371 | Power Plant Facility 994 |  |  |  |  | 2014-10-28 | 2015-09-07 | 2015-09-29 | 0.52
2015-09-10 | 2010 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 58625 | Satellite Communications Facility |  |  |  |  | 2010-03-06 | 2012-09-01 | 2015-11-11 | 1
2015-09-10 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 57595 | Wideband SATCOM Operations Center |  |  |  |  | 2011-09-06 | 2015-12-22 | 2015-12-22 | 0.95 | 2014-04-15
2015-09-10 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 57595 | Wideband SATCOM Operations Center | 69 |  |  |  | 2011-09-06 | 2015-12-22 | 2015-12-22 | 0.95 | 2014-04-15
2015-09-10 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65793 | Indoor Firing Range |  |  |  |  | 2011-10-13 | 2013-04-05 | 2014-08-11 | 1 | 2014-10-15
2015-09-10 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65793 | Indoor Firing Range | 85 |  |  |  | 2011-10-13 | 2013-04-05 | 2014-08-11 | 1 | 2014-10-15
2015-09-10 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 64939 | Applied Instruction Facility |  |  |  |  | 2012-11-20 | 2014-11-20 | 2016-01-04 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65755 | Brigade Complex |  |  |  |  | 2012-12-12 | 2015-12-12 | 2017-04-25 | 0.72
2015-09-10 | 2012 | Army Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 79846 | Electromag Interference Fac |  |  |  |  | 2014-10-20 | 2015-12-01 | 2015-12-01 | 0.01
2015-09-10 | 2012 | Army Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 80231 | Replace Oil Water Separators |  |  |  |  | 2014-11-03 | 2015-09-25 | 2015-09-25 | 0.02
2015-09-10 | 2014 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 81875 | Operations and Maintenance Facilities |  |  |  |  | 2014-05-23 | 2015-03-19 | 2015-08-11 | 0.96 | 2015-08-31
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 80477 | Fragmentation Simulation Lab |  |  |  |  | 2014-01-23 | 2015-07-17 | 2015-07-17 | 0.99
2015-09-10 | 2012 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 64365 | Vehicle Maintenance Facility |  |  |  |  | 2012-09-18 | 2014-08-25 | 2015-11-30 | 0.83 | 2014-09-19
2015-09-10 | 2012 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 64365 | Vehicle Maintenance Facility | 161 |  |  |  | 2012-09-18 | 2014-08-25 | 2015-11-30 | 0.83 | 2014-09-19
2015-09-10 | 2012 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 64365 | Vehicle Maintenance Facility | 162 |  |  |  | 2012-09-18 | 2014-08-25 | 2015-11-30 | 0.83 | 2014-09-19
2015-09-10 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 |  |  |  |  | 2013-06-25 | 2015-09-12 | 2015-10-16 | 0.98
2015-09-10 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 | 248 |  |  |  | 2013-06-25 | 2015-09-12 | 2015-10-16 | 0.98
2015-09-10 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 65679 | Vehicle Maintenance Shop |  |  |  |  | 2013-06-27 | 2015-04-08 | 2015-06-15 | 0.96
2015-09-10 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 66099 | Battalion Complex Facilities |  |  |  |  | 2013-07-01 | 2016-05-05 | 2016-05-23 | 0.71 | 2014-12-31
2015-09-10 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 66099 | Battalion Complex Facilities | 259 |  |  |  | 2013-07-01 | 2016-05-05 | 2016-05-23 | 0.71 | 2014-12-31
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE |  |  |  |  | 2012-12-10 | 2014-06-20 | 2015-09-01 | 0.93
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE | 287 |  |  |  | 2012-12-10 | 2014-06-20 | 2015-09-01 | 0.93
2015-09-10 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  |  |  |  | 2014-08-05 | 2016-08-04 | 2016-11-17 | 0.16
2015-09-10 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 | 323 |  |  |  | 2014-08-05 | 2016-08-04 | 2016-11-17 | 0.16
2015-09-10 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 | 324 |  |  |  | 2014-08-05 | 2016-08-04 | 2016-11-17 | 0.16
2015-09-10 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 75019 | Simulator Building |  |  |  |  | 2014-12-01 | 2015-12-01 | 2016-01-04 | 0.46
2015-09-10 | 2009 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66725 | Ballistic Evaluation Facility Ph 1 |  |  |  |  | 2012-12-04 | 2014-06-04 | 2015-07-17 | 0.69 | 2015-08-17
2015-09-10 | 2010 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66726 | Ballistic Evaluation Facility, Ph 2 |  |  |  |  | 2012-12-04 | 2014-06-04 | 2015-07-17 | 0.77 | 2015-08-17
2015-09-10 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center |  |  |  |  | 2012-12-04 | 2015-02-15 | 2015-08-04 | 0.96 | 2015-08-17
2015-09-10 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center | 246 |  |  |  | 2012-12-04 | 2015-02-15 | 2015-08-04 | 0.96 | 2015-08-17
2015-09-10 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 71675 | Flight Equipment Complex |  |  |  |  | 2014-01-15 | 2016-01-15 | 2016-01-15 | 0.61
2015-09-10 | 2011 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 57735 | Infantry Squad Battle Course |  |  |  |  | 2012-08-26 | 2014-02-22 | 2014-10-21 | 1 | 2014-10-21
2015-09-10 | 2011 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 59044 | Science Facility, Ph 2 |  |  |  |  | 2011-11-17 | 2015-11-14 | 2015-11-14 | 0.91
2015-09-10 | 2012 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 58005 | Ammunition Supply Point |  |  |  |  | 2012-05-18 | 2013-08-15 | 2014-11-14 | 1 | 2014-11-04
2015-09-10 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar |  |  |  |  | 2013-06-27 | 2015-12-02 | 2016-03-18 | 0.68
2015-09-10 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar | 295 |  |  |  | 2013-06-27 | 2015-12-02 | 2016-03-18 | 0.68
2015-09-10 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar | 296 |  |  |  | 2013-06-27 | 2015-12-02 | 2016-03-18 | 0.68
2015-09-10 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 79933 | Cadet Barracks | 79933 |  |  |  | 2013-08-26 | 2016-08-30 | 2016-09-11 | 0.42
2015-09-10 | 2014 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 79933 | Cadet Barracks, Incr 2 | 81186 |  |  |  | 2013-08-26 | 2016-08-30 | 2016-09-11 | 0.42
2015-09-10 | 2015 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 79933 | Cadet Barracks, Incr 3 | 81187 |  |  |  | 2013-08-26 | 2016-08-30 | 2016-09-11 | 0.42
2015-09-10 | 2015 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81349 | Unmanned Aerial Vehicle Hangar |  |  |  |  | 2015-06-22 | 2016-12-18 | 2016-12-18 | 0
2015-09-10 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex |  |  |  |  | 2011-11-21 | 2014-01-29 | 2015-04-18 | 0.99 | 2015-05-18
2015-09-10 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex | 57 |  |  |  | 2011-11-21 | 2014-01-29 | 2015-04-18 | 0.99 | 2015-05-18
2015-09-10 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex | 58 |  |  |  | 2011-11-21 | 2014-01-29 | 2015-04-18 | 0.99 | 2015-05-18
2015-09-10 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex | 59 |  |  |  | 2011-11-21 | 2014-01-29 | 2015-04-18 | 0.99 | 2015-05-18
2015-09-10 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex | 60 |  |  |  | 2011-11-21 | 2014-01-29 | 2015-04-18 | 0.99 | 2015-05-18
2015-09-10 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 57317 | Battalion Complex |  |  |  |  | 2011-11-21 | 2014-01-29 | 2015-01-09 | 0.99 | 2014-04-30
2015-09-10 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 57317 | Battalion Complex | 67 |  |  |  | 2011-11-21 | 2014-01-29 | 2015-01-09 | 0.99 | 2014-04-30
2015-09-10 | 2012 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69835 | Unmanned Aerial Vehicle Maintenance Hangar |  |  |  |  | 2015-01-05 | 2016-02-29 | 2016-04-04 | 0.18
2015-09-10 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 55121 | Aerial Gunnery Range |  |  |  |  | 2015-11-29 | 2017-11-28 | 2017-11-28 | 0.02
2015-09-10 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80066 | Controlled Humidity Warehouse, Installatio |  |  |  |  | 2013-11-06 | 2015-03-01 | 2015-03-20 | 0.96 | 2015-06-30
2015-09-10 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80087 | Storage Building, General Purpose |  |  |  |  | 2013-04-18 | 2014-08-11 | 2014-09-17 | 0.92 | 2015-05-08
2015-09-10 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80112 | Unmanned Aerial Vehicle Complex |  |  |  |  | 2015-05-26 | 2017-02-06 | 2017-02-06 | 0.03
2015-09-10 | 2014 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69624 | Command and Control Facility |  |  |  |  | 2014-08-27 | 2015-08-27 | 2015-09-14 | 0.84
2015-09-10 | 2011 | Army Active | Unspecified Minor Military Construction | OHIO | UNITED STATES | 74757 | Fire Alarm System |  |  |  |  | 2012-09-05 | 2013-08-01 | 2015-04-15 | 0.96
2015-09-10 | 2010 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 66545 | General Purpose Storage Building |  |  |  |  | 2010-11-22 | 2015-09-22 | 2015-12-31 | 0.96 | 2012-06-01
2015-09-10 | 2010 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 66545 | General Purpose Storage Building | 35 |  |  |  | 2010-11-22 | 2015-09-22 | 2015-12-31 | 0.96 | 2012-06-01
2015-09-10 | 2010 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 66545 | General Purpose Storage Building | 36 |  |  |  | 2010-11-22 | 2015-09-22 | 2015-12-31 | 0.96 | 2012-06-01
2015-09-10 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 1235 | Physical Fitness Facility |  |  |  |  | 2012-07-12 | 2014-04-10 | 2014-05-27 | 0.84 | 2015-08-17
2015-09-10 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 20697 | Chapel |  |  |  |  | 2012-09-20 | 2014-01-28 | 2014-01-28 | 0.8
2015-09-10 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58207 | Railroad Tracks |  |  |  |  | 2012-05-09 | 2013-10-06 | 2013-10-06 | 1 | 2015-02-18
2015-09-10 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58537 | Reception Station, Ph 1 |  |  |  |  | 2012-06-15 | 2014-03-26 | 2014-05-25 | 0.97 | 2014-12-02
2015-09-10 | 2010 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 69417 | Training Battalion Complex |  |  |  |  | 2010-07-27 | 2013-06-03 | 2015-02-18 | 1 | 2015-03-16
2015-09-10 | 2010 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 69417 | Training Battalion Complex | 42 |  |  |  | 2010-07-27 | 2013-06-03 | 2015-02-18 | 1 | 2015-03-16
2015-09-10 | 2011 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 53794 | Trainee Barracks Complex, Ph 1 |  |  |  |  | 2012-01-04 | 2013-08-04 | 2014-12-18 | 1 | 2014-11-25
2015-09-10 | 2011 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 53794 | Trainee Barracks Complex, Ph 1 | 63 |  |  |  | 2012-01-04 | 2013-08-04 | 2014-12-18 | 1 | 2014-11-25
2015-09-10 | 2011 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 53794 | Trainee Barracks Complex, Ph 1 | 64 |  |  |  | 2012-01-04 | 2013-08-04 | 2014-12-18 | 1 | 2014-11-25
2015-09-10 | 2011 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71119 | Training Aids Center |  |  |  |  | 2011-09-08 | 2013-03-01 | 2014-12-11 | 1 | 2014-10-14
2015-09-10 | 2012 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 62955 | Trainee Barracks Complex, Ph 2 |  | 8600000 | 80066 |  | 2012-07-23 | 2014-01-14 | 2014-11-06 | 1 | 2014-10-27
2015-09-10 | 2013 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 58970 | Trainee Barracks Complex 2, Ph 2 |  |  |  |  | 2013-12-04 | 2015-05-28 | 2015-08-22 | 0.95
2015-09-10 | 2011 | Army Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 66717 | Military Working Dog Kennel |  |  |  |  | 2013-08-27 | 2014-07-22 | 2014-08-29 | 0.99 | 2015-03-26
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 67194 | Simulations Center |  |  |  |  | 2012-04-10 | 2013-08-09 | 2013-12-30 | 0.99 | 2015-02-05
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex |  |  |  |  | 2011-07-13 | 2014-01-21 | 2015-01-05 | 1 | 2015-01-14
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex | 105 |  |  |  | 2011-07-13 | 2014-01-21 | 2015-01-05 | 1 | 2015-01-14
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex | 106 |  |  |  | 2011-07-13 | 2014-01-21 | 2015-01-05 | 1 | 2015-01-14
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex | 107 |  |  |  | 2011-07-13 | 2014-01-21 | 2015-01-05 | 1 | 2015-01-14
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71465 | Company Operations Facilities |  |  |  |  | 2011-07-13 | 2013-11-11 | 2014-12-12 | 1 | 2014-04-14
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71465 | Company Operations Facilities | 109 |  |  |  | 2011-07-13 | 2013-11-11 | 2014-12-12 | 1 | 2014-04-14
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex |  |  |  |  | 2011-07-13 | 2015-01-30 | 2015-07-01 | 0.88 | 2014-05-05
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex | 112 |  |  |  | 2011-07-13 | 2015-01-30 | 2015-07-01 | 0.88 | 2014-05-05
2015-09-10 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex | 113 |  |  |  | 2011-07-13 | 2015-01-30 | 2015-07-01 | 0.88 | 2014-05-05
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility |  |  |  |  | 2013-01-24 | 2014-07-18 | 2015-08-09 | 0.68
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex |  |  |  |  | 2012-09-05 | 2014-11-28 | 2015-05-30 | 0.9
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex | 168 |  |  |  | 2012-09-05 | 2014-11-28 | 2015-05-30 | 0.9
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 |  |  |  |  | 2012-04-24 | 2014-06-02 | 2014-07-11 | 0.91
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 | 182 |  |  |  | 2012-04-24 | 2014-06-02 | 2014-07-11 | 0.91
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69286 | Infrastructure |  |  |  |  | 2012-08-20 | 2013-09-13 | 2013-09-27 | 0.74
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69828 | Unmanned Aerial Vehicle Maintenance Hangar |  |  |  |  | 2014-08-27 | 2016-01-04 | 2016-01-13 | 0.56
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility |  |  |  |  | 2012-06-22 | 2015-01-25 | 2015-03-30 | 0.96
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility | 205 |  |  |  | 2012-06-22 | 2015-01-25 | 2015-03-30 | 0.96
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility | 206 |  |  |  | 2012-06-22 | 2015-01-25 | 2015-03-30 | 0.96
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility |  |  |  |  | 2012-06-22 | 2015-01-25 | 2015-03-30 | 0.95
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility | 218 |  |  |  | 2012-06-22 | 2015-01-25 | 2015-03-30 | 0.95
2015-09-10 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility | 219 |  |  |  | 2012-06-22 | 2015-01-25 | 2015-03-30 | 0.95
2015-09-10 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71120 | Training Aids Center |  |  |  |  | 2013-10-17 | 2015-04-10 | 2015-04-10 | 0.73
2015-09-10 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex |  |  |  |  | 2013-10-07 | 2016-01-04 | 2016-01-13 | 0.97 | 2015-07-31
2015-09-10 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex | 292 |  |  |  | 2013-10-07 | 2016-01-04 | 2016-01-13 | 0.97 | 2015-07-31
2015-09-10 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex | 293 |  |  |  | 2013-10-07 | 2016-01-04 | 2016-01-13 | 0.97 | 2015-07-31
2015-09-10 | 2014 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 74638 | Control Tower |  |  |  |  | 2015-04-28 | 2017-01-02 | 2017-01-02 | 0.02
2015-09-10 | 2014 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 81155 | Unmanned Aerial Vehicle Complex |  |  |  |  | 2014-12-18 | 2016-04-11 | 2016-04-11 | 0.25
2015-09-10 | 2012 | Army Active | Major Military Construction | UTAH | UNITED STATES | 55823 | Life Sciences Test Facility Addition |  |  |  |  | 2012-08-29 | 2015-02-15 | 2015-12-04 | 0.97
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | UTAH | UNITED STATES | 81106 | POLICE/MP STATION |  |  |  |  | 2013-10-18 | 2014-12-17 | 2015-06-15 | 0.7 | 2015-07-15
2015-09-10 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 61453 | Replace Fire Station |  |  |  |  | 2013-06-05 | 2014-11-27 | 2015-07-21 | 0.95 | 2015-06-15
2015-09-10 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 65726 | MOUT Collective Training Fac |  | 735000 | 53789 |  | 2012-01-20 | 2013-10-21 | 2014-10-24 | 0.99 | 2013-10-25
2015-09-10 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 57508 | Information Dominance Center, Ph 1 |  |  |  |  | 2013-08-19 | 2015-03-12 | 2015-11-08 | 0.83 | 2015-02-17
2015-09-10 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  |  | 2013-10-15 | 2015-10-15 | 2015-10-15 | 0.68
2015-09-10 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 | 243 |  |  |  | 2013-10-15 | 2015-10-15 | 2015-10-15 | 0.68
2015-09-10 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 | 244 |  |  |  | 2013-10-15 | 2015-10-15 | 2015-10-15 | 0.68
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80317 | WATER DISTRIBUTION LINES, POTABLE |  |  |  |  | 2014-01-13 | 2014-09-10 | 2015-04-30 | 0.54
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 81629 | AIR CONDITIONING/REFRIGERATION PLANT |  |  |  |  | 2013-10-17 | 2014-08-13 | 2014-11-11 | 1 | 2014-11-12
2015-09-10 | 2014 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  |  | 2014-10-09 | 2017-07-05 | 2017-07-05 | 0.07
2015-09-10 | 2009 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 69224 | Warrior in Transition (WT) Complex |  |  |  |  | 2009-11-20 | 2014-09-12 | 2015-04-30 | 1 | 2015-07-01
2015-09-10 | 2009 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 69224 | Warrior in Transition (WT) Complex | 20 |  |  |  | 2009-11-20 | 2014-09-12 | 2015-04-30 | 1 | 2015-07-01
2015-09-10 | 2009 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 69224 | Warrior in Transition (WT) Complex | 21 |  |  |  | 2009-11-20 | 2014-09-12 | 2015-04-30 | 1 | 2015-07-01
2015-09-10 | 2009 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 69224 | Warrior in Transition (WT) Complex | 22 |  |  |  | 2009-11-20 | 2014-09-12 | 2015-04-30 | 1 | 2015-07-01
2015-09-10 | 2010 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 74408 | Ft Lewis-McChord AFB Joint Access |  |  |  |  | 2013-09-25 | 2015-01-28 | 2015-05-15 | 0.99 | 2015-05-04
2015-09-10 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex |  |  |  |  | 2011-10-12 | 2015-10-24 | 2015-10-24 | 0.98
2015-09-10 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex | 121 |  |  |  | 2011-10-12 | 2015-10-24 | 2015-10-24 | 0.98
2015-09-10 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex | 122 |  |  |  | 2011-10-12 | 2015-10-24 | 2015-10-24 | 0.98
2015-09-10 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex | 123 |  |  |  | 2011-10-12 | 2015-10-24 | 2015-10-24 | 0.98
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 53637 | Brigade Complex, Ph 2 |  |  |  |  | 2012-06-29 | 2014-06-11 | 2015-03-12 | 0.99 | 2015-03-15
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 53637 | Brigade Complex, Ph 2 | 135 |  |  |  | 2012-06-29 | 2014-06-11 | 2015-03-12 | 0.99 | 2015-03-15
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 53637 | Brigade Complex, Ph 2 | 136 |  |  |  | 2012-06-29 | 2014-06-11 | 2015-03-12 | 0.99 | 2015-03-15
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 58046 | Operational Readiness Training Cplx, Ph 1 |  |  |  |  | 2013-05-21 | 2014-11-12 | 2015-02-08 | 0.95
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex |  |  |  |  | 2012-07-25 | 2015-04-08 | 2015-09-30 | 0.93 | 2015-04-30
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex | 157 |  |  |  | 2012-07-25 | 2015-04-08 | 2015-09-30 | 0.93 | 2015-04-30
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex | 158 |  |  |  | 2012-07-25 | 2015-04-08 | 2015-09-30 | 0.93 | 2015-04-30
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex | 159 |  |  |  | 2012-07-25 | 2015-04-08 | 2015-09-30 | 0.93 | 2015-04-30
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 |  |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 174 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 175 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 176 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 177 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 178 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 179 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 180 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-01 | 0.92
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76767 | Aviation Unit Complex, Ph 1A |  |  |  |  | 2012-07-09 | 2015-08-21 | 2015-09-10 | 0.97
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76767 | Aviation Unit Complex, Ph 1A | 214 |  |  |  | 2012-07-09 | 2015-08-21 | 2015-09-10 | 0.97
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B |  |  |  |  | 2012-11-29 | 2015-05-21 | 2015-09-02 | 0.92 | 2014-10-14
2015-09-10 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B | 216 |  |  |  | 2012-11-29 | 2015-05-21 | 2015-09-02 | 0.92 | 2014-10-14
2015-09-10 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 67545 | Convoy Live Fire Range |  |  |  |  | 2013-09-10 | 2015-01-03 | 2015-01-03 | 1 | 2014-11-21
2015-09-10 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 75165 | Waste Water Treatment Plant |  |  |  |  | 2014-03-03 | 2016-03-02 | 2016-04-18 | 0.58
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81320 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL |  |  |  |  | 2013-10-28 | 2014-10-28 | 2015-01-26 | 0.94 | 2015-02-19
2015-09-10 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 54106 | Automated Multipurpose Machine Gun Range |  |  |  |  | 2014-08-18 | 2016-02-09 | 2016-02-09 | 0.55
2015-09-10 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76776 | Airfield Operations Complex |  |  |  |  | 2015-05-18 | 2017-07-06 | 2017-07-06 | 0.02
2015-09-10 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76776 | Airfield Operations Complex | 338 |  |  |  | 2015-05-18 | 2017-07-06 | 2017-07-06 | 0.02
2015-09-10 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar |  |  |  |  | 2014-09-23 | 2016-03-16 | 2016-03-16 | 0.34
2015-09-10 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar | 340 |  |  |  | 2014-09-23 | 2016-03-16 | 2016-03-16 | 0.34
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80919 | Underground Electric Lines |  |  |  |  | 2015-02-13 | 2016-02-13 | 2016-02-13 | 0.24
2015-09-10 | 2014 | Army Active | Military Family Housing | WISCONSIN | UNITED STATES | 74861 | Family Housing New Construction |  |  |  |  | 2014-08-20 | 2016-08-09 | 2016-09-19 | 0.11
2015-08-31 | 2012 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010263 | Readiness Center, Ph2 |  |  |  |  | 2012-08-17 | 2014-09-17 | 2014-09-23 | 0.99 | 2015-02-06 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 011007 | National Guard Readiness Center, Add/Alt |  |  |  |  | 2013-12-31 | 2014-10-01 | 2014-12-19 | 0.95 | 2014-12-14
2015-08-31 | 2013 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010278 | Live Fire Shoot House |  |  |  |  | 2013-11-12 | 2014-11-11 | 2015-06-08 | 0.98 | 2015-06-08 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 011014 | National Guard Readiness Center Add/Alt |  |  |  |  | 2014-10-07 | 2015-12-10 | 2015-12-10 | 0.35 | 2015-12-10
2015-08-31 | 2012 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040294 | Readiness Center |  |  |  |  | 2012-09-12 | 2013-10-16 | 2014-01-31 | 0.05 | 2013-11-04 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 040669 | Underground Electrical Lines |  |  |  |  | 2014-05-05 | 2014-10-31 | 2014-10-31 | 0.01 | 2014-10-31
2015-08-31 | 2012 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050172 | Convoy Live Fire/Entry Control Point Range |  |  |  |  | 2012-11-07 | 2013-10-28 | 2014-07-15 | 0.99 | 2015-02-01 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | 050190 | Wash Platform, Installation |  |  |  |  | 2014-03-10 | 2014-06-23 | 2014-12-22 | 0.99 | 2014-12-09
2015-08-31 | 2013 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050139 | Field Maintenance Shop |  |  |  |  | 2013-08-30 | 2014-10-01 | 2014-10-01 | 1 | 2015-01-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050182 | Scout REECE Gunnery Complex |  |  |  |  | 2014-10-20 | 2015-06-30 | 2015-06-30 | 0.1 | 2015-06-30
2015-08-31 | 2010 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060115 | Readiness Center, PH 1 |  | 2900000 | 390263 |  | 2010-11-15 | 2012-02-06 | 2015-01-30 | 0.95 | 2013-10-07 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060429 | Combined Arms Collective Training Facility |  | 6700000 | 361103 |  | 2011-12-05 | 2012-06-29 | 2013-09-27 | 0.99 | 2013-06-15 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060170 | Field Maintenance Shop |  |  |  |  | 2012-11-08 | 2013-10-14 | 2014-06-06 | 0.35 | 2013-10-20 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 060432 | Barracks |  |  |  |  | 2012-10-15 | 2013-09-20 | 2014-10-30 | 0.99 | 2013-10-07 | FY07 Congressionally Directed, Used FY10 funds
2015-08-31 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060438 | Tactical Unmanned Aircraft System Facility |  |  |  |  | 2012-08-06 | 2013-10-28 | 2015-06-02 | 0.99 | 2013-11-11 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060413 | Maneuver Area Training & Equipment Site Ph 3 |  |  |  |  | 2013-10-21 | 2014-10-01 | 2015-10-15 | 0.97 | 2014-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 ($1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)}
2015-08-31 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080067 | Regional Training Institute |  |  |  |  | 2011-10-01 | 2014-10-18 | 2014-10-03 | 1 | 2014-12-15 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2,000 Formal Reprogramming $9,300 funds from FY10 project savings {PNs: 160120 ($6,000) & 350043 ($3,300)}
2015-08-31 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080093 | Barracks Complex (ORTC) |  |  |  |  | 2012-09-24 | 2013-10-28 | 2015-06-30 | 0.99 | 2015-02-02 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080206 | Tactical Unmanned Aircraft System Facility |  |  |  |  | 2012-11-05 | 2013-10-28 | 2015-04-30 | 1 | 2014-12-31 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090043 | Combined Support Maintenance Shop |  |  |  |  | 2014-04-26 | 2015-10-01 | 2015-10-09 | 0.72 | 2015-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090115 | RIP RAP |  |  |  |  | 2014-09-22 | 2015-03-31 | 2015-05-27 | 1 | 2015-03-31 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 450252)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100010 | Regional Training Institute Ph1 |  |  |  |  | 2013-09-23 | 2014-09-23 | 2014-12-04 | 0.99 | 2014-12-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), Construction is finish, project completion is pending all closeout documentation
2015-08-31 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120102 | Readiness Center |  |  |  |  | 2014-03-03 | 2015-07-26 | 2015-09-13 | 0.8 | 2015-09-13 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) & Formal Reprogramming $5,482 funds from FY12 project savings {PNs: 060009 ($4,452) & 240187 ($1,030)}
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120228 | Ready Building |  |  |  |  | 2013-10-14 | 2015-05-16 | 2015-09-23 | 0.68 | 2015-09-23
2015-08-31 | 2014 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120195 | Ready Building |  |  |  |  | 2014-04-14 | 2016-04-05 | 2016-04-05 | 0.6 | 2016-04-05
2015-08-31 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130123 | Readiness Center, Add/Alt |  |  |  |  | 2012-06-04 | 2013-09-30 | 2014-04-30 | 1 | 2013-09-30 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130127 | Readiness Center |  |  |  |  | 2011-12-01 | 2012-11-16 | 2012-11-16 | 0.98 | 2013-05-15 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130063 | Maneuver Area Training and Equipment Site, Ph 1 |  |  |  |  | 2012-10-19 | 2013-10-28 | 2015-08-15 | 0.75 | 2013-11-18 | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2015-08-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130068 | Readiness Center Ph 1 |  |  |  |  | 2012-09-14 | 2014-03-14 | 2014-10-14 | 1 | 2013-04-12 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130120 | Readiness Center |  |  |  |  | 2012-09-10 | 2013-10-28 | 2014-11-24 | 1 | 2013-11-18 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2010 | Army National Guard | Major Military Construction | GUAM | GUAM | 140300 | Readiness Center |  | 3000000 | 530035 |  | 2010-05-03 | 2012-03-05 | 2012-03-05 | 0.98 | 2012-04-12 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | GUAM | GUAM | 140040 | JFHQ Ph 4 |  |  |  |  | 2013-10-21 | 2014-10-20 | 2014-10-20 | 0.75 | 2014-10-20 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150023 | Army Aviation Support Facility Ph1 |  |  |  |  | 2014-11-12 | 2016-11-01 | 2016-11-01 | 0.23 | 2016-11-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2015-08-31 | 2011 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160093 | Barracks (ORTC), Ph 1 |  | 2600000 | 300216 |  | 2011-08-27 | 2013-02-28 | 2014-04-15 | 1 | 2013-10-03 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160100 | ORTC (Barracks) Ph2 |  |  |  |  | 2013-10-07 | 2014-08-01 | 2016-03-09 | 0.77 | 2014-08-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2010 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170611 | Readiness Center, Add/Alt |  |  |  |  | 2010-10-18 | 2011-09-14 | 2011-09-14 | 1 | 2012-03-31 | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2015-08-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ILLINOIS | UNITED STATES | 171005 | Battalion Maintenance Shelter |  |  |  |  | 2012-10-01 | 2013-10-31 | 2013-11-19 | 1 | 2013-09-23 | (NGB 593)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170033 | National Guard Readiness Center |  |  |  |  | 2014-07-21 | 2016-10-01 | 2016-11-01 | 0.18 | 2016-10-01
2015-08-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170127 | Aircraft Maintenance Hangar |  |  |  |  | 2014-07-21 | 2016-10-01 | 2016-11-01 | 0.18 | 2016-10-01
2015-08-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180012 | JFHQ Add/Alt |  |  |  |  | 2012-11-15 | 2013-10-28 | 2015-04-30 | 1 | 2014-05-04 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2.000 FY09 {PN: 040026} & Formal Reprogramming $7,271 funds from FY09 project savings {PNs: 040226 ($2,540), 180116 ($3,805), 180137 ($510) and 260211 ($416)}
2015-08-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180142 | Railhead Expansion & Container Facility |  |  |  |  | 2012-12-01 | 2014-06-07 | 2014-06-07 | 1 | 2014-06-07 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180156 | Deployment Processing Facility |  |  |  |  | 2012-12-01 | 2014-06-07 | 2014-06-07 | 0.96 | 2014-06-07 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180160 | Operations Readiness Training Complex 1 |  |  |  |  | 2012-12-01 | 2014-05-01 | 2014-05-01 | 1 | 2014-05-01 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180161 | Operations Readiness Training Complx 2 |  |  |  |  | 2012-12-01 | 2014-05-01 | 2014-05-01 | 1 | 2014-05-01 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180106 | Field Maintenance Shop |  |  |  |  | 2014-07-21 | 2014-12-25 | 2015-09-30 | 0.75 | 2014-12-25 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180144 | Armed Forces Reserve Center Add/Alt |  |  |  |  | 2014-04-21 | 2015-08-23 | 2015-05-29 | 0.89 | 2015-05-29 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200102 | Taxiway, Ramp & Hangar Alterations |  |  |  |  | 2013-07-22 | 2014-10-01 | 2014-07-04 | 0.7 | 2014-05-02 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | KANSAS | UNITED STATES | 200127 | Water Distribution Lines, Portable |  |  |  |  | 2014-04-07 | 2014-06-13 | 2015-04-02 | 0.95 | 2014-06-13
2015-08-31 | 2013 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210001 | Army Aviation Support Facility |  |  |  |  | 2013-07-08 | 2014-10-01 | 2015-05-31 | 0.94 | 2014-11-10 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220222 | Tactical Unmanned Aircraft System Facility |  |  |  |  | 2011-09-12 | 2012-07-30 | 2013-06-18 | 0.99 | 2012-12-11 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 220233 | Waste Water Treatment Facility |  |  |  |  | 2012-06-15 | 2013-06-17 | 2014-12-02 | 1 | 2013-07-15
2015-08-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220241 | National Guard Readiness Center |  |  |  |  | 2014-09-22 | 2016-10-30 | 2016-10-30 | 0.05 | 2016-10-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220243 | Jackson Barracks Billeting Replacement |  |  |  |  | 2014-07-25 | 2014-10-15 | 2014-10-15 | 1 | 2014-10-15 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $3,000 - PN: 450252, $2,700 - PN: 450353)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230046 | Readiness Center |  |  |  |  | 2012-09-26 | 2014-07-11 | 2015-09-30 | 0.97 | 2015-07-01 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230071 | Armed Forces Reserve Center |  |  |  |  | 2012-09-26 | 2014-10-12 | 2015-06-30 | 0.99 | 2015-03-23 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-08-31 | 2015 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230113 | National Guard Reserve Center |  |  |  |  | 2015-08-20 | 2018-01-01 | 2018-01-01 | 0.01 | 2018-01-01 | Using State procedures the contract number is the same as the project number plus -D to delineate Construction
2015-08-31 | 2011 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240186 | Tactical Unmanned Aircraft System Facility |  |  |  |  | 2012-06-01 | 2013-06-15 | 2014-11-21 | 1 | 2014-12-06 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240017 | Readiness Center Add/Alt |  |  |  |  | 2012-10-01 | 2014-09-22 | 2015-08-31 | 0.92 | 2015-06-20 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240187 | Readiness Center Add/Alt |  | 1030000 | 120102 |  | 2012-10-01 | 2014-09-22 | 2015-03-20 | 0.99 | 2015-03-01 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240193 | Readiness Center |  |  |  |  | 2012-10-01 | 2014-09-22 | 2015-09-15 | 0.81 | 2015-07-11 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 240194 | Combat Pistol/MP Firearms Qualification Course |  |  |  |  | 2015-06-01 | 2014-09-22 | 2015-12-18 | 0.2 | 2015-09-18
2015-08-31 | 2012 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250135 | Readiness Center |  |  |  |  | 2012-12-01 | 2013-10-28 | 2014-10-28 | 0.75 | 2013-11-18 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-08-31 | 2013 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250065 | Unit Training Equipment Site |  |  |  |  | 2014-04-07 | 2015-07-30 | 2015-10-15 | 0.35 | 2015-07-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250196 | Water Well, Non-Potable |  |  |  |  | 2013-06-03 | 2013-12-01 | 2013-12-01 | 0.01 | 2013-12-02
2015-08-31 | 2014 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250095 | Enlisted Barracks, Transient Training Addition |  |  |  |  | 2014-09-15 | 2016-11-01 | 2016-11-01 | 0.01 | 2016-11-01
2015-08-31 | 2014 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260051 | Enlisted Barracks, Transient Training |  |  |  |  | 2014-08-11 | 2016-10-01 | 2016-10-01 | 0.45 | 2016-10-01
2015-08-31 | 2012 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270266 | Multipurpose Machine Gun Range |  |  |  |  | 2012-09-17 | 2013-12-15 | 2014-06-01 | 0.99 | 2014-01-18 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,718)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270236 | Scout Reconnaissance Range |  |  |  |  | 2013-09-23 | 2015-10-01 | 2016-06-30 | 0.84 | 2015-08-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270238 | Readiness Center |  |  |  |  | 2013-09-30 | 2015-10-15 | 2015-10-28 | 0.87 | 2015-10-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270014 | National Guard Readiness Center |  |  |  |  | 2014-10-22 | 2016-04-15 | 2016-04-15 | 0.3 | 2016-04-15
2015-08-31 | 2014 | Army National Guard | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 281305 | Raw Sewage Lagoon and Oxidation Pond |  |  |  |  | 2014-09-30 | 2015-04-30 | 2015-07-15 | 0.99 | 2005-04-30
2015-08-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280272 | National Guard Readiness Center |  |  |  |  | 2014-07-14 | 2015-10-01 | 2015-10-01 | 0.01 | 2015-10-01
2015-08-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280423 | Water Supply/Treatment Building, Potable |  |  |  |  | 2014-08-15 | 2015-06-30 | 2015-06-30 | 0.1 | 2015-06-30
2015-08-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290176 | Regional Training Institute |  |  |  |  | 2013-12-09 | 2015-02-28 | 2015-07-21 | 0.98 | 2015-02-28 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290191 | National Guard Vehicle Maintenance Shop |  |  |  |  | 2015-05-12 | 2015-07-31 | 2015-10-31 | 0.94 | 2012-04-30
2015-08-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290221 | Aircraft Maintenance Hangar |  |  |  |  | 2015-06-26 | 2015-06-26 | 2015-10-06 | 0.52 | 2015-06-26
2015-08-31 | 2015 | Army National Guard | Major Military Construction | MONTANA | UNITED STATES | 300128 | National Guard Readiness Center Add/Alt |  |  |  |  | 2015-05-13 | 2017-05-31 | 2017-05-13 | 0.01 | 2017-05-31
2015-08-31 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320143 | Readiness Center |  | 3112000 | 060413 |  | 2010-10-25 | 2012-01-23 | 2013-04-19 | 0.99 | 2013-05-01 | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330034 | Classroom Facility (Regional Training Institute) |  |  |  |  | 2011-11-07 | 2013-06-01 | 2016-03-03 | 0.5 | 2016-01-23 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330035 | Barracks Facility (Regional Training Institute) |  |  |  |  | 2011-11-07 | 2013-06-01 | 2016-01-30 | 0.65 | 2015-11-23 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEW HAMPSHIRE | UNITED STATES | 330052 | Readiness Center, Add/Alt |  |  |  |  | 2012-10-07 | 2013-08-13 | 2013-08-13 | 1 | 2013-07-29 | (Closeout procedures are in progress)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340115 | Army Aviation Support Facility |  |  |  |  | 2012-09-19 | 2014-10-18 | 2015-01-31 | 0.99 | 2015-01-31 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340110 | Regional Training Institute |  |  |  |  | 2014-10-15 | 2016-02-12 | 2016-02-12 | 0.45 | 2016-02-12 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340130 | Communication Lines and Ductbank, Underground |  |  |  |  | 2014-10-03 | 2015-08-31 | 2015-08-31 | 0.07 | 2015-08-31 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360161 | National Guard Readiness Center Alteration |  |  |  |  | 2014-10-20 | 2016-05-30 | 2016-05-30 | 0.3 | 2016-05-30 | Formal Reprogramming $3,814 funds from FY11 project savings (PN: 090010)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition |  |  |  |  | 2014-10-06 | 2015-10-30 | 2015-12-04 | 0.55 | 2015-10-30
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition | 95 |  |  |  | 2014-10-06 | 2015-10-30 | 2015-12-04 | 0.55 | 2015-10-30
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition | 96 |  |  |  | 2014-10-06 | 2015-10-30 | 2015-12-04 | 0.55 | 2015-10-30
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380123 | RIP RAP |  |  |  |  | 2013-12-09 | 2014-08-30 | 2015-06-30 | 0.91 | 2014-08-30
2015-08-31 | 2015 | Army National Guard | Major Military Construction | NORTH DAKOTA | UNITED STATES | 380073 | National Guard Vehicle Maintenance Shop |  |  |  |  | 2015-07-13 | 2017-06-30 | 2017-06-30 | 0.01 | 2017-06-30
2015-08-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390230 | Readiness Center |  |  |  |  | 2013-08-01 | 2013-12-01 | 2015-03-13 | 0.99 | 2015-03-13 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390256 | Field Maintenance Shop Add/Alt |  |  |  |  | 2013-11-04 | 2014-07-02 | 2015-06-18 | 1 | 2015-03-10 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), NGB 593 being reviewed
2015-08-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390263 | Hutments |  |  |  |  | 2014-07-16 | 2015-06-15 | 2015-06-15 | 0.95 | 2015-06-15 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390292 | Sanitary Sewer |  |  |  |  | 2014-09-08 | 2016-07-31 | 2016-07-31 | 0.1 | 2016-07-31
2015-08-31 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400605 | Upgrade: Combined Arms Collective Training Facility |  |  |  |  | 2012-11-01 | 2014-02-19 | 2015-01-16 | 0.99 | 2014-03-07 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400606 | Live Fire Shoot House |  |  |  |  | 2012-11-01 | 2014-02-19 | 2014-06-28 | 0.99 | 2014-03-07 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400066 | Operations Readiness Training Complex |  |  |  |  | 2013-10-25 | 2014-10-01 | 2016-02-22 | 0.35 | 2014-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410026 | Readiness Center |  |  |  |  | 2012-12-01 | 2013-12-28 | 2014-03-20 | 1 | 2014-02-21 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2009 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420511 | Readiness Center, Add/Alt |  |  |  |  | 2011-09-26 | 2012-10-30 | 2015-05-31 | 0.99 | 2013-08-15 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 420542 | Controlled Access Secure Facility |  |  |  |  | 2014-10-30 | 2015-11-13 | 2015-11-21 | 0.15 | 2015-11-13 | SIOH all in-house; awaiting NPDES
2015-08-31 | 2014 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420051 | Aircraft Maintenance Instructional Building |  |  |  |  | 2014-10-20 | 2016-04-22 | 2016-04-22 | 0.12 | 2016-04-22
2015-08-31 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 436021 | Multi Purpose Machine Gun Range |  |  |  |  | 2014-09-15 | 2015-01-26 | 2015-09-14 | 0.66 | 2015-01-26 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 436023 | Live Fire Shoot House |  |  |  |  | 2011-11-07 | 2012-12-14 | 2012-12-14 | 0.65 | 2012-09-18 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430010 | Readiness Center |  |  |  |  | 2012-12-01 | 2013-10-28 | 2015-02-28 | 0.98 | 2014-12-05 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($40,565)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430081 | Readiness Center (JFHQ) |  |  |  |  | 2014-03-03 | 2015-09-18 | 2015-11-12 | 0.7 | 2015-09-18 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | PUERTO RICO | 430622 | Sanitary Sewer |  |  |  |  | 2014-09-15 | 2015-06-26 | 2015-06-26 | 0.01 | 2015-06-26
2015-08-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430804 | Refill Station Building |  |  |  |  | 2013-10-28 | 2015-05-08 | 2015-05-08 | 0.06 | 2015-05-08 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430806 | Readiness Center |  |  |  |  | 2014-02-10 | 2015-05-15 | 2015-06-19 | 0.01 | 2015-05-15 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430070 | Maneuver Area Training & Equipment Site Addition |  |  |  |  | 2014-09-15 | 2015-05-30 | 2015-05-30 | 0.01 | 2015-05-30
2015-08-31 | 2011 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440009 | United States Property and Fiscal Office |  |  |  |  | 2012-10-08 | 2014-04-17 | 2015-03-31 | 0.99 | 2015-01-31 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | 440053 | Access Control Point |  |  |  |  | 2015-01-06 | 2015-02-27 | 2015-02-27 | 0.01 | 2015-02-27
2015-08-31 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450252 | Army Aviation Support Facility, Add/Alt |  | 11000000 | 090115, 220241 and 220243 |  | 2011-02-07 | 2011-12-14 | 2013-05-01 | 0.99 | 2013-04-15 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2015-08-31 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450353 | Army Aviation Support Facility |  | 12100000 | 220241, 220243, and 530035 |  | 2010-11-17 | 2012-08-10 | 2013-06-21 | 0.75 | 2013-06-21 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450403 | Readiness Center, Add/Alt |  |  |  |  | 2012-10-01 | 2013-10-28 | 2013-10-28 | 0.1 | 2013-09-01 | PL 112-25 (Budget Control Act, 2011), State Purchase Number E24-9751-CA
2015-08-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450131 | National Guard Vehicle Maintenance Shop |  |  |  |  | 2014-10-06 | 2015-10-30 | 2017-05-06 | 0.1 | 2015-10-30
2015-08-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450283 | National Guard Readiness Center |  |  |  |  | 2014-10-06 | 2015-10-30 | 2015-10-30 | 0.01 | 2015-10-30
2015-08-31 | 2011 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460085 | Readiness Center |  |  |  |  | 2011-11-07 | 2013-01-14 | 2015-06-01 | 0.99 | 2013-03-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($18,225)
2015-08-31 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480175 | Armed Forces Reserve Center |  |  |  |  | 2011-01-24 | 2012-07-17 | 2015-07-01 | 1 | 2013-10-01 | PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-08-31 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480176 | Field Maintenance Shop, Joint |  |  |  |  | 2011-01-24 | 2012-07-17 | 2015-07-01 | 1 | 2013-10-01 | PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-08-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490076 | BEQ Facility (Regional Training Institute) |  |  |  |  | 2013-08-12 | 2014-10-01 | 2014-11-30 | 0.99 | 2014-11-10 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490444 | Regional Training Institute Ph2 |  |  |  |  | 2013-08-26 | 2014-09-30 | 2015-04-15 | 0.99 | 2014-09-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | UTAH | UNITED STATES | 490803 | Unheated Aircraft Storage Hangar |  |  |  |  | 2016-01-26 | 2016-01-26 | 2016-01-26 | 0.97 | 2016-01-26
2015-08-31 | 2015 | Army National Guard | Major Military Construction | VERMONT | UNITED STATES | 500036 | National Guard Vehicle Maintenance Shop |  |  |  |  | 2015-04-30 | 2015-10-31 | 2015-12-31 | 0.01 | 2015-10-31
2015-08-31 | 2010 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520014 | Regional Training Institute, PH 1 |  |  |  |  | 2010-07-01 | 2012-02-20 | 2013-04-23 | 0.99 | 2013-02-15 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520034 | Readiness Center (JFHQ) |  |  |  |  | 2011-11-01 | 2012-08-20 | 2013-08-01 | 1 | 2013-11-25 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | VIRGINIA | UNITED STATES | 510307 | Combined Arms Collective Training Facility |  |  |  |  | 2013-04-10 | 2014-10-09 | 2015-02-27 | 0.98 | 2015-04-10 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530022 | Combined Support Maintenance Shop |  |  |  |  | 2011-08-22 | 2012-11-03 | 2014-09-23 | 1 | 2013-12-12 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), State waiting on demolition of the old CSMS
2015-08-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530015 | Readiness Center |  |  |  |  | 2013-09-23 | 2015-08-20 | 2015-09-29 | 0.9 | 2015-08-28 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530035 | National Guard Readiness Center |  |  |  |  | 2014-10-06 | 2016-06-30 | 2016-06-30 | 0.3 | 2016-06-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2015-08-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540105 | Joint Interagency Training Education Center, PH 1 |  |  |  |  | 2009-10-01 | 2011-09-28 | 2014-09-30 | 0.99 | 2011-09-30 | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540206 | Multi-Purpose Building, PH II |  |  |  |  | 2010-02-01 | 2010-08-26 | 2013-03-31 | 1 | 2010-08-30 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2015-08-31 | 2012 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540085 | Readiness Center Ph1 |  |  |  |  | 2012-11-01 | 2014-11-12 | 2014-11-12 | 0.75 | 2014-08-25 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540075 | Readiness Center |  |  |  |  | 2014-04-07 | 2015-09-11 | 2015-09-11 | 0.7 | 2015-09-11 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550139 | Aircraft Parking |  |  |  |  | 2011-11-01 | 2012-10-29 | 2012-10-17 | 0.94 | 2012-10-09 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550245 | Tactical Unmanned Aircraft System Facility |  |  |  |  | 2012-07-01 | 2013-05-20 | 2014-05-30 | 0.99 | 2013-10-20 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2015-08-31 | 2013 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550142 | Field Maintenance Shop |  |  |  |  | 2013-10-28 | 2014-10-01 | 2015-06-15 | 0.99 | 2014-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560081 | National Guard Readiness Center |  |  |  |  | 2013-10-10 | 2015-03-31 | 2016-05-20 | 0.75 | 2015-08-22
2015-09-10 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 67652 | Army Reserve Center |  |  |  |  | 2015-04-24 | 2017-02-12 | 2017-02-12 | 0.01
2015-09-10 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 71482 | ORTC |  |  |  |  | 2014-03-19 | 2016-05-17 | 2016-05-27 | 0.33
2015-09-10 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72160 | UPH Barracks |  |  |  |  | 2013-11-18 | 2014-11-03 | 2015-02-23 | 0.99 | 2015-04-02
2015-09-10 | 2014 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72284 | TASS Training Center (TTC) |  |  |  |  | 2014-10-20 | 2016-05-22 | 2016-07-26 | 0.11
2015-09-10 | 2012 | Army Reserve | Major Military Construction | COLORADO | UNITED STATES | 67658 | Army Reserve Center |  |  |  |  | 2012-05-11 | 2013-10-18 | 2013-10-18 | 0.88
2015-09-10 | 2015 | Army Reserve | Major Military Construction | COLORADO | UNITED STATES | 81959 | Training Building Addition |  |  |  |  | 2015-08-16 | 2016-12-18 | 2016-12-18 | 0
2015-09-10 | 2010 | Army Reserve | Major Military Construction | CONNECTICUT | UNITED STATES | 69461 | Army Reserve Center/Land |  |  |  |  | 2011-11-29 | 2015-12-21 | 2016-01-29 | 0.49
2015-09-10 | 2010 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 69471 | Army Reserve Center/Land |  |  |  |  | 2012-05-22 | 2013-09-24 | 2013-10-06 | 0.92
2015-09-10 | 2011 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 74220 | Army Reserve Center/Land |  |  |  |  | 2011-10-21 | 2013-03-24 | 2013-09-17 | 1 | 2014-11-13
2015-09-10 | 2012 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67713 | Army Reserve Center |  |  |  |  | 2012-10-18 | 2014-07-10 | 2015-11-23 | 0.93
2015-09-10 | 2013 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67659 | Army Reserve Center |  |  |  |  | 2014-01-13 | 2015-11-04 | 2015-12-31 | 0.66
2015-09-10 | 2012 | Army Reserve | Major Military Construction | INDIANA | UNITED STATES | 67673 | Army Reserve Center |  |  |  |  | 2012-05-30 | 2015-01-29 | 2015-09-25 | 1 | 2014-09-22
2015-09-10 | 2011 | Army Reserve | Major Military Construction | IOWA | UNITED STATES | 70654 | Army Reserve Center |  |  |  |  | 2012-04-09 | 2013-08-12 | 2013-11-13 | 0.95 | 2015-04-15
2015-09-10 | 2013 | Army Reserve | Major Military Construction | MARYLAND | UNITED STATES | 68077 | Add/Alt Army Reserve Center |  |  |  |  | 2014-07-30 | 2016-05-30 | 2016-05-30 | 0.14
2015-09-10 | 2014 | Army Reserve | Major Military Construction | MARYLAND | UNITED STATES | 67663 | Army Reserve Center/Land |  |  |  |  | 2015-09-27 | 2017-08-27 | 2017-08-27 | 0.01
2015-09-10 | 2013 | Army Reserve | Major Military Construction | NEVADA | UNITED STATES | 67660 | Army Reserve Center/AMSA |  |  |  |  | 2013-07-10 | 2015-05-01 | 2015-05-01 | 0.98 | 2015-07-06
2015-09-10 | 2013 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71720 | Automated Infantry Squad Battle Course |  |  |  |  | 2013-07-17 | 2014-07-17 | 2015-06-30 | 0.99 | 2015-02-12
2015-09-10 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 65277 | Consolidated Dining Facility |  |  |  |  | 2014-04-23 | 2015-09-30 | 2015-09-30 | 0.4
2015-09-10 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 69669 | Central Issue Facility |  |  |  |  | 2014-07-07 | 2015-12-14 | 2015-12-14 | 0.2
2015-09-10 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71769 | Modified Record Fire Range |  |  |  |  | 2014-10-17 | 2016-04-09 | 2016-04-09 | 0.37
2015-09-10 | 2011 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69599 | Army Reserve Center/Land |  |  |  |  | 2012-10-25 | 2014-05-12 | 2014-05-15 | 0.98 | 2015-02-20
2015-09-10 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67691 | Army Reserve Center |  |  |  |  | 2012-06-01 | 2015-01-04 | 2015-05-30 | 0.97 | 2014-05-21
2015-09-10 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69432 | Army Reserve Center |  | 5845000 | 69562, 69422 |  | 2013-04-15 | 2014-07-29 | 2014-08-15 | 0.97 | 2014-11-12
2015-09-10 | 2012 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 67466 | Army Reserve Center/Land |  |  |  |  | 2012-10-10 | 2014-03-19 | 2014-06-12 | 0.66
2015-09-10 | 2014 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71900 | Army Reserve Center |  |  |  |  | 2014-12-02 | 2016-11-01 | 2016-11-14 | 0.23
2015-09-10 | 2010 | Army Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | 69430 | Army Reserve Center/Land |  |  |  |  | 2012-01-18 | 2013-11-08 | 2015-06-12 | 0.96
2015-09-10 | 2010 | Army Reserve | Major Military Construction | PUERTO RICO | PUERTO RICO | 69568 | Army Reserve Center/Land |  |  |  |  | 2011-11-15 | 2013-08-06 | 2013-11-16 | 0.94 | 2015-03-11
2015-09-10 | 2012 | Army Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 67672 | Army Reserve Center/Land |  |  |  |  | 2012-05-21 | 2013-09-23 | 2014-09-18 | 0.97 | 2014-10-20
2015-09-10 | 2010 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 75110 | Tactical Equipment Maintenance Facility |  |  |  |  | 2012-04-05 | 2013-09-12 | 2014-01-10 | 0.96 | 2015-01-30
2015-09-10 | 2011 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 69421 | Army Reserve Center/Land |  |  |  |  | 2012-08-21 | 2014-03-21 | 2014-05-01 | 0.26
2015-09-10 | 2011 | Army Reserve | Major Military Construction | VIRGINIA | UNITED STATES | 70641 | Army Reserve Center/Land |  |  |  |  | 2012-01-12 | 2013-05-06 | 2013-09-25 | 0.97 | 2014-10-30
2015-09-10 | 2013 | Army Reserve | Major Military Construction | WASHINGTON | UNITED STATES | 67715 | Army Reserve Center |  |  |  |  | 2013-07-11 | 2015-08-30 | 2015-08-30 | 0.94
2015-09-10 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 67689 | Central Issue Facility |  |  |  |  | 2013-07-08 | 2014-11-10 | 2015-08-20 | 0.98 | 2015-08-27
2015-09-10 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71997 | Dining Facility |  |  |  |  | 2013-10-02 | 2015-02-04 | 2015-04-01 | 0.93
2015-09-10 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 72088 | ECS TEMF |  | 5455000 | 69562 |  | 2013-07-08 | 2015-06-08 | 2015-06-08 | 0.77
2015-09-10 | 2014 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71999 | NCO Academy Dining Facility |  |  |  |  | 2014-04-22 | 2015-08-25 | 2015-09-19 | 0.87
2015-08-31 | 2013 | Defense Finance and Accounting Service | Major Military Construction | TEXAS | UNITED STATES | 80230 | DFAS Administration Building |  |  |  |  | 2013-09-11 | 2015-03-05 | 2015-12-02 | 0.56 | 2016-03-03
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 71653 | Hospital Replacement (ARRA) | 71653 |  |  |  | 2010-12-03 | 2014-01-07 | 2014-01-07 | 1 | 2013-10-17 | Multiple residual closeout issues.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 70354 | Hospital Replacement (Supplemental) | 70354 | 92680000 | FY13 - PN76558 |  | 2012-05-30 | 2015-03-16 | 2017-05-17 | 0.41 | 2017-07-16 | Significant changes in processes impacting water storage and the central utility plant are being resolved. Full impact of the changes on the project are unknown and continue to be addressed by the delivery team. Senior leadership continues to engage regularly to assist in resolution of project issues. Engineers continuously evaluating project design to identify concerns and remedies for way-ahead. Time impacts associated with past changes are currently in negotiation which should not result in considerable growth in time beyond previously reported. Senior leadership continues to engage regularly to assist in resolution of project issues. Team is working through engineering challenges impacting concrete decks. The MCX and Hospital CX are engaged to address concrete decks and engineering concerns. All other unaffected work activities are continuing per plan.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 72808 | Medical Clinic Replacement | 72808 |  |  |  | 2014-02-28 | 2015-03-16 | 2016-05-20 | 0.65 | 2016-01-05
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 51639 | USARIEM Replacement High Altitude Research Lab | 51639 | [8 empty] | Omaha District met with customers and City of Colorado Springs to coordinate design requirements and schedules during the week of 31 Aug 15. Expect request for P&D funds and AE award in near future.
2015-08-31 | 2015 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 72414 | Dental Clinic Replacement | 72414 | [8 empty] | Received FAD for $6M in FY11 funds on 4 Sep 15. The project Source Selection Evaluation Board (SSEB) has established an apparent "best value" des/bld MATOC contractor selectee. The request for authority to award, along with the preaward CWE is being prepared and should be available on Tuesday, 9/8/15. The DODM-MILCON portion of the preaward CWE will indicate a cost that will be above the project's DODM-MILCON Programmed Amount (PA), approx. 110% of PA. The preaward CWE will be based on full scope, including the demolition of the existing temporary Dental Clinic option.
2015-08-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | DELAWARE | UNITED STATES | 86204 | Medical Warehouse Add/Alt | 86204 | [8 empty] | Proposals due on 11SEP15. Evaulation schedule for 14-16 SEP
2015-08-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 75132 | Joint Navy-VA Project | 75132 |  |  |  | 2014-06-01 | 2014-10-15 | 2016-01-29 | 0.34 | 2016-01-29 | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2015-08-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 82358 | Veterinary Clinic Replacement | 82358 | [8 empty] | Cost reduction measures incorporated new HQCWE is $1.8M. DHA has increased PA to $1.9M. Received Authority to Advertise on 26 Apr 15. Advertised 09 Jul 15. Bids due on 11 Aug 15.
2015-08-31 | 2007 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 52330 | Clinic Replacement, Inc 1 | 52330 |  |  |  | 2007-09-04 | 2009-12-17 | 2011-06-05 | 1 | 2009-09-11 | Water intrusion problem update – Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. Construction Contractor reviewed their records and provided a response to AF reports 30 Jan 2015. A-E provided response on 2 Feb 2015. CESAM reviewed responses and is currently negotiating acquisition of building envelope specialist to prepare independent determination addressing the responsibilities of each party and estimate of damages by each party. Awarded pending. We expect initial findings within 180 days of award.
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 52330 | Clinic Replacement, Inc 2 | 67647 |  |  |  | 2007-09-04 | 2009-12-17 | 2011-06-05 | 1 | 2009-09-11 | See 52330, Clinic Replacement, Inc 1
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 79845 | Eglin Hospital Alteration (ARRA) | 79845 |  |  |  | 2011-10-31 | 2014-11-06 | 2015-07-28 | 0.99 | 2015-03-12 | Contract including all currently identified modifications is at 99.58% of PA. Hospital Command moved into new building Dec 19. Urology, ENT, Lab II, Surgery Phase III move in also completed mid December. Contractor currently working punch list in PET/CT. Scheduled acceptance Aug. 3. User requested equipment mod is only item outstanding. Joint Commissioning is competed and generated no action items for the project to correct.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 70597 | Medical Clinic | 70597 |  |  |  | 2012-10-17 | 2014-10-07 | 2014-10-07 | 1 | 2015-01-05 | Final document turnover in process. Performing post BOD changes at user request, PT room flooring, walk off matts, rear gate padlocks and door hardware. Final Pay anticipated April, 2015.
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) | 70235 |  |  |  | 2009-10-22 | 2013-02-03 | 2014-05-19 | 1 | 2014-05-19 | Commissioning of systems continues. Final TAB reports resubmitted and in review. Contingencies at District: $1,307.17. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 30 Oct 15. Benning DPW will assign # upon receipt of final 1354.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70482 | Health Clinic Addition/Alteration | 70482 | 1012000 | PN - 72414 |  | 2011-06-21 | 2013-06-20 | 2014-05-19 | 1 | 2013-11-29 | Contingencies at District: $0. CAT E&F remaining at Distirct: $0. Financial close-out underway.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 72292 | Hospital Addition/Alteration Phase 2 | 72292 | 11000000 | PN - 72754 |  | 2012-10-15 | 2016-10-14 | 2017-03-17 | 0.78 | 2017-06-14 | Contingencies at district: $361,300 of which $172,675 is for temp. swing space. Executed Option 5 on Trailer Lease. Approval to descope received 5 June 2015. Final inspection of ED complete. Contractor working on punch listfor ED.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 65270 | Hospital Replacement, Inc 1 | 65270 | 20119000 | FY13 - PN80308 FY10 - PN61401 |  | 2010-11-01 | 2014-10-15 | 2016-03-15 | 0.99 | 2014-03-18 | 3rd UXO found; work is stopped, but has restarted
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 55918 | Central Utility Plant | 55918 | 696000 | PN - 78146 |  | 2009-10-01 | 2011-02-07 | 2011-06-22 | 1 | 2011-06-22 | Residual closeout issues.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65030 | Naval Hospital Great Lakes Health Clinic Demolition | 65030 | 9210000 | PN - 67951 PN - 71325 PN - 77154 |  | 2012-09-12 | 2013-09-13 | 2014-08-08 | 1 | 2014-04-21
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 78143 | Navy Drug Lab Replacement | 78143 | 644000 | FY13-PN78146 |  | 2013-11-08 | 2015-01-15 | 2016-03-15 | 0.98 | 2015-04-15 | Drug Lab BOD Apr 2015, Second Contract to Demo Bldg 38H underway
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | KANSAS | UNITED STATES | 47298 | Hospital Replacement | 47298 | 44000000 | PN - 72754 |  | 2010-05-03 | 2013-07-23 | 2014-05-13 | 0.99 | 2015-07-01 | 8/24/15 Fort Riley Replacement Hospital. NWK sent letter to the Contractor asking for their projection for completion, particularly life safety deficiencies (necessary for BOD). Current CCD: 13 May 2014 Placement: 99% actual vs. 100% scheduled (as of June's pay estimate). Construction in progress: TAB/commissioning nearing completion (Two exhaust fans remain). Inspections continue. Final inspections are progressing. Numerous life safety deficiencies remain unaddressed. HFPA furniture install started 06 July. Comments: The contractor exceeded the required completion date of 13 May 2014. Liquidated damages are being withheld at $16,500 per calendar day. Corporate/senior manager engagement continues. No good estimate as to when BOD will actually occur. First patients will be in the building in mid-Jan. Ribbon cutting currently scheduled for 5 Jan 16.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70438 | Hospital Addition/Alteration | 70438 |  |  |  | 2012-08-22 | 2015-02-21 | 2015-10-27 | 0.97 | 2015-10-27 | The Contractor and his subs continue to make progress in renovation work. MILCON funds in the amount of $5,402,819 will be needed as the large claims that have been settled. Contract completion will be 27 Oct 2015. All work will be completed by this date. This funding will put the project $498,870 over the Sequestration PA of $55,886,000. (100.89% over PA). The final negotiations resolved concurrent delays: Case 58, Curtain wall $4,706,237 and 187 days. Case 65 Part II Med Air User change $0. Case 111 Part II Asbestos Insulation in Alt (Part 2 Final) $464,623 and 29 days.
2015-08-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 1 | 005V |  |  |  | 2008-07-01 | 2011-07-31 | 2012-09-15 | 1 | 2010-08-01
2015-08-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 2 | 005A |  |  |  | 2008-07-01 | 2011-07-31 | 2012-09-15 | 1 | 2010-08-01 | Not financially closed. Final invoicing for equipment.
2015-08-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 3 | 005B |  |  |  | 2008-07-01 | 2011-07-31 | 2012-09-15 | 1 | 2010-08-01
2015-08-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 64156 | USAMRICD Replacement, Inc 1 | 64156 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 0.99 | 2015-06-30 | Final BOD for Building E was 10 Jun 15 with a follow on contract to investigate and fix systems commissioning and fume hoods in the lab. Currently working to get Facility Dynamics Engineering under contract to troubleshoot and establish COAs/Solutions to resolve the problems; targeting contract award o/a 9 Sep 15. Project fiscal closeout will follow pending resolution of remaining punchlist items and settlement of outstanding requests for equitable adjustment.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77000 | Public Health Command Laboratory Replacement | 77000 | [8 empty] | Construction contract awarded 6 Aug 15 to Walsh Gilbane Joint Venture, 929 W Adams St, Chicago IL 60607-302115 in the amount of $209,917,000.00. Targeting issuance of contract NTP o/a 8 Sep 15.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77154 | Ambulatory Care Center, Inc 1 | 77154 |  |  |  | 2013-03-01 | 2016-12-06 | 2018-01-01 | 0.68 | 2016-11-01 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77154 | Ambulatory Care Center, Inc 2 | 81291 |  |  |  | 2013-03-01 | 2016-12-06 | 2018-01-01 | 0.68 | 2016-11-01 | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 | 65731 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 1 | 2010-08-31 | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 | 65731 |  |  |  | 2010-03-15 | 2013-06-01 | 2014-12-22 | 1 | 2014-11-01 | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC. $9,000 rescinded as a result of Sequestration (04/29/13).
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 1 | 2010-08-31
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  |  | 2010-10-01 | 2011-09-30 | 2011-09-30 | 1 | 2011-10-01
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  |  | 2010-03-15 | 2013-06-01 | 2014-12-22 | 1 | 2014-11-01 | Main Building $142,857,143 FY10 Increment Awarded at $100,375,000 on 5 Mar 10 ($109,567,007 funded per D. Pritchett 17 Mar 10 email)
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 3 | 67181 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 0.99 | 2015-06-30 | Full FY11 MILCON increment placed against contract.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 4 | 67182 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 0.99 | 2015-06-30 | Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 30 Apr 2015 for remainder of spaces. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Currently contracting for a third party investigation to provide options and COAs to address issues preventing E-Wing Labs from operating as intended. Estimated contract award date o/a 9 Sep 15.
2015-08-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 | 58395 |  |  |  | 2007-10-12 | 2008-06-13 | 2008-06-08 | 1 | 2008-07-23 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 | 58395 |  |  |  | 2008-08-19 | 2009-02-15 | 2009-02-13 | 1 | 2009-03-03 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 | 58395 |  |  |  | 2009-10-15 | 2010-04-13 | 2010-04-13 | 1 | 2010-04-13 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 | 58395 |  |  |  | 2008-12-05 | 2009-07-24 | 2009-07-24 | 1 | 2009-07-24 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 | 58395 |  |  |  | 2008-07-15 | 2011-05-06 | 2013-10-31 | 1 | 2013-12-06 | Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project.
2015-08-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 | 58395 |  |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 0.95 | 2017-07-01 | FY07. See FY2012 remarks. Contract active, but all funds on this increment obligated. Building to be operational NOV 2017.
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 2 | 63418 |  |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 0.95 | 2017-07-01 | FY 08. Contract completion date is 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 3 | 63419 |  |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 0.95 | 2017-07-01 | FY09. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract complete date is 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 0.95 | 2017-07-01 | FY10. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract completion date is 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  |  | 2008-07-15 | 2013-10-31 | 2013-10-31 | 1 | 2013-12-06 | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 5 | 65324 |  |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 0.95 | 2017-07-01 | FY11. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract completion date is 16 Dec 14; liquidated damages will be assessed. Approx $90,000 FY2011 P&D funds for parking design being returned.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 5 | 65324 |  |  |  | 2008-07-15 | 2013-10-31 | 2013-10-31 | 1 | 2013-12-06 | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 6 | 71101 |  |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 0.95 | 2017-07-01 | FY12. Scheduled 100%, Actual 95%. T&E change under negotiation with contractor. Re-installation of BSL4 lab coatings is 95% complete; cleaning smoke-damaged BSL3 area equipment, and commissioning remainder of facility. Plan is to accept admin, BSL2 and BSL3 labs Jun 2016 to start CDC certification and accept BSL4 labs Jul 2017. Contract completion 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 6 | 71101 | [8 empty] | DA memo dated 24 Jun 2015 and USACE design directive dated 25 Jun 2015 provided code 7 (D-B). DHA-conducted planning charrette was held week of 6 July 2015. Award of A-E task orders for borings and survey will be awarded by 30 Sep 2015 to obligate expiring FY11 P&D funds.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 6 | 71101 | [8 empty] | Contract being prepared for award. Maryland Dept of Environment requires USAG Ft Detrick to start Pond 7A construction for regional stormwater management. Project requirment was advertised as the base bid component of a combined solicitation with DODM Security Fencing/Equipment and MCA Entry Control Point projects as options due to site overlap.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 7 | 78210 |  |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 0 | 2017-07-01 | Utilities, DDC, Certification and related costs.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 8 | 78211 | [8 empty] | Remainder of certification costs this FY. South parking/demolition is budgeted for this PN but facilities are likely not able to be available for demolition until funds expire. We will coordinate a way ahead on this when main facility is closer to turnover.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 8 | 78211 | [8 empty] | Notional schedule shown; dependent on CDC/DA Safety certification of USAMRIID primary facility and vacation/decommissioning of existing buildings 1408/1412/1414/1415. Due to delay in main contract, projections for award are moved out 2 years.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61401 | Boundary Gate at Nallin Pond | 61401 |  |  |  | 2011-01-12 | 2013-01-10 | 2015-01-08 | 1 | 2014-12-31 | Remaining punchlist items completed. All pending modifications/REAs are settled. Project is in closeout phase.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61536 | Emergency Service Center | 61536 | 1028000 | FY14 - PN77922 |  | 2010-07-19 | 2012-09-16 | 2013-05-23 | 1 | 2013-05-23 | In fiscal closeout. Construction contract held open longer to address a warranty repair.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77116 | NNMC Parking Expansion | 77116 | 1854000 | PN - 72752 |  | 2012-06-18 | 2014-02-02 | 2014-07-18 | 1 | 2013-12-02 | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77115 | Transient Wounded Warrior Lodging | 77115 | 10111000 | OSD C project for NATO HQ, Brussels PN - 77116 PN - 72414 |  | 2012-06-18 | 2014-02-02 | 2014-07-18 | 1 | 2014-05-27 | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 73360 | Consolidated Logistics Facility | 73360 | 500000 | PN - 72414 |  | 2011-07-21 | 2014-01-06 | 2014-10-07 | 1 | 2014-10-07 | Targeting minor punchlist item completion Sep 2015. Potential in-scope mod (O&M Equipment move) pending upon receit of SRM funds.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 62886 | Information Services Facility Expansion | 62886 |  |  |  | 2012-03-19 | 2013-11-09 | 2015-02-10 | 1 | 2015-02-10 | Facility turned over to garrison. Punchlist is complete.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67949 | NIBC Security Fencing and Equipment | 67949 |  |  |  | 2012-04-02 | 2013-04-02 | 2013-04-01 | 1 | 2013-04-01 | Segment 1 - Project Closed. Segment 2 will be awarded on 18 Sept 15.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67949 | NIBC Security Fencing and Equipment | 67949 | [8 empty] | RTA date for Fence Segment 2 was 30 Jan 15. Work structured as contract option in combined solicitation with USAMRIID Replacement North Parking which establishes overall site contours for fence construction. Source selection complete. Requested award authority/funding; awaiting receipt.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67953 | Supplemental Water Storage | 67953 |  |  |  | 2011-07-20 | 2012-11-01 | 2015-10-30 | 0.98 | 2015-10-30 | % Complete (Scheduled/Actual): 100/98 Contractor having difficulty completing pump facility. LD's being assessed from 30 May 2014. BOD slipped due to contractor performance issues. Bonding company has been contacted. Tank has been filled and passed testing.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67951 | Water Treatment Plant Repair | 67951 |  |  |  | 2013-01-14 | 2014-07-08 | 2015-11-30 | 0.97 | 2015-11-30 | % Complete (Scheduled/Actual): 100/97 . Electrical subcontractor remains behind schedule.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 79554 | Child Development Center | 79554 | 2000000 | FY12 - PN67182 |  | 2013-03-01 | 2014-02-22 | 2014-06-02 | 1 | 2014-04-07
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71408 | Dental Clinic Replacement | 71408 |  |  |  | 2013-03-01 | 2016-12-06 | 2017-11-08 | 0 | 2017-01-06 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71507 | Branch Health Clinic Replacement | 71507 |  |  |  | 2014-04-30 | 2015-10-15 | 2016-02-12 | 0.47 | 2016-02-12
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80307 | Implement Base Installation Appearance Plan | 80307 |  |  |  | 2014-04-01 | 2015-04-08 | 2016-03-18 | 0.05 | 2016-03-18
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities | 80306 |  |  |  | 2013-10-15 | 2013-12-13 | 2014-03-25 | 1 | 2014-04-04 | Dosimetry Complete
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities | 80306
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80308 | Electrical Utility Upgrades | 80308 | 4500000 | FY10 - PN65270 |  | 2014-10-23 | 2016-02-12 | 2016-06-27 | 0.2 | 2016-06-27 | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80904 | Mechanical & Electrical Improvements | 80904 |  |  |  | 2015-05-31 | 2017-02-07 | 2017-02-07 | 0.01 | 2017-02-07
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80913 | Parking Garage | 80913 |  |  |  | 2014-11-30 | 2016-04-16 | 2016-05-09 | 0 | 2016-05-09
2015-08-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MISSISSIPPI | UNITED STATES | 478V | Community Hospital | 478V |  |  |  | 2010-01-01 | 2011-09-11 | 2012-10-11 | 1 | 2012-02-25 | Not financially closed. Final invoicing for equipment - working with DLA.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | MISSISSIPPI | UNITED STATES | 71503 | Branch Health Clinic | 71503 | 8300000 | PN - 72754 |  | 2012-09-01 | 2014-09-09 | 2016-01-31 | 0.75 | 2016-04-30 | Notification of contract termination 5 May 2015
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 71679 | Dental Clinic | 71679 | 234000 | FY13-PN72718 |  | 2013-12-02 | 2015-02-19 | 2015-02-19 | 1 |  | Facility remains unoccupied (may be a staffing issue). Field staff have been unable to get a date for aoccupancy from the User. Seasonal commissioning scheduled for 25 Aug 15. Contractor has responded to minor warranty items and punchlist. Contractor is also replacing 2 boiler flues (1 complete, 1 awaiting parts).
2015-08-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 80093 | Medical Ed. & Training Facility | 80093 |  |  |  | 2012-08-14 | 2013-11-14 | 2014-08-24 | 1 | 2014-09-10 | Switch gear was changed on 18 FEB 2015. Project complete. No punch list items. Contract/project closeout and Evaluation not completed. All else is done.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77979 | Medical/Dental Clinic Replacement | 77979 | 4000000 | FY09-PNS0013 |  | 2014-04-28 | 2018-02-10 | 2018-04-19 | 0.08 | 2018-01-08 | Submittal #3, 100% Bldg design, review meeting held 3-6 Aug 2015. Submittal #4, corrected Final Design, 11 Sep 2015. 100% Site/Civil package "For Construction" issued 9 July 2015. Mobilization began on 20 Jul 2015 and construction activity began on 29 Jul 2015. C-008 New PFD modification (mod), $659,996, executed 29 May 2015. PDT developed list of scope reductions as potential offsets to the cost of C-008. To date, $901,816 in modifications have been executed utilizing contingency funds. Current estimated value of offsets $500K. PDT has outlines potential cost saving modification for changes to Program for Design. Goal is to reduce overall cost impacts to $200K or less. Partial notice to proceed issued for Site/Civil work.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77922 | Medical Clinic Replacement | 77922 | 1900000 | FY14-PN81340 |  | 2014-10-27 | 2018-01-30 | 2018-01-30 | 0.1 | 2018-08-16 | Submittal #2 (65% Arch/MEP/Fire, 100% Foundation/Structural, IFC Civil/Site) Received 19 May 2015. Review completed, review conference held 15-19 Jun 15. Areas of concern with missing or incomplete information identified (several disciplines, mechanical and electrical). Submittal #3 scheduled for delivery on 23 Sep 2015 and formal conference scheduled for 20 Oct 15.
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 63864 | Health Clinic Add/Alt | 63864 | 1000000 | PN - 67647 |  | 2008-11-07 | 2011-02-18 | 2013-12-12 | 1 | 2012-12-01 | Financial closeout pending A-E Damages Resolution
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 59220 | Hospital Add/Alt (Supplemental) | 59220 | 5537000 | FY13 - PN76558 |  | 2011-10-26 | 2015-08-03 | 2015-08-03 | 0.99 | 2015-07-15 | Contract completion was 20 July 2015. Interior punchlist reduced to allow HFPA to move in 3 Aug as scheduled. Chilled water tie-in occurred 13 Aug. Numerous Mechanical and Curtain Wall punchlist remain. Expect 3 wks to resolve Mechanical issue and 6-8 wks on ext curtain wall. Ribbon Cutting Target date in 2 Oct 15.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70580 | Dental Clinic Addition /Alteration | 70580 |  |  |  | 2013-01-09 | 2015-01-09 | 2014-12-19 | 1 | 2014-12-19 | BOD 19 DEC 14. MOD work to repair Chiller line near completion (estimated completion of repair 9 SEP 15)
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70579 | Medical Clinic (SFCC) | 70579 | 1773000 | PN - 77154 PN - 79510 PN - 70438 |  | 2013-03-15 | 2015-03-06 | 2015-03-06 | 1 | 2015-03-05 | BOD 5 MAR 15. Remaining punchlist items all to be complete NLT 30 SEP 15.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 73776 | Soldier Specality Care Clinic | 73776 |  |  |  | 2014-01-06 | 2016-01-06 | 2016-01-06 | 0.73 | 2016-04-05 | Interior finishes near completion and rough-in of interior utilities continues.
2015-08-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81004 | Site Development, NiCOE | 81004 |  |  |  | 2012-08-01 | 2013-08-29 | 2013-08-29 | 1 | 2013-08-12 | Project is not financially closed.
2015-08-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81631 | NiCOE Satellite, Infrastructure Support | 81631 |  |  |  | 2014-06-30 | 2016-02-01 | 2016-02-01 | 0.71 | 2015-11-30 | The NiCOE Contractor (WM Jordan) on-going construction work on new clinic. WM Jordan has a weathered in roof, interior stud walls, primary duct work, and fire sprinkler mains installed. WM Jordan continues with masonry walls, electrical , communications, and plumbing rough-in. Site Contractor is installing curb and gutter in the Southern Parking Lot. Contingencies in district: $24,739.38
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71857 | Hospital Addition | 71857 | 14587000 | PN - 59215 PN - 00101 PN - 53577 PN - 77154 |  | 2010-12-03 | 2013-01-12 | 2013-07-15 | 1 | 2013-07-15 | Funds used for FY00 Settlement, Ft. Wainwright. Residual activity on project funding items.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 73599 | Hospital Renovation & MRI Addition (Cong Add) | 73599 | 5623000 | PN - 76558 |  | 2010-12-03 | 2015-01-02 | 2015-10-16 | 0.99 | 2015-08-11 | Active Project.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) | 69353 | 14458000 | OSD - C project FY14 - PN77922 |  | 2011-05-13 | 2012-10-12 | 2012-11-15 | 1 | 2012-11-15 | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14. Financial close-out underway.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 70351 | Hospital Alteration | 70351 | 23532000 | PN - 71820 PN - 71503 |  | 2012-09-13 | 2014-06-23 | 2016-01-15 | 0.83 | 2016-01-20 | Contingencies at District: $69,771.04. Contractor has been issued an Interim Marginal CCASS. Fire Alarm testing + ICRA inspection completed in Emergency Dept with no deficiencies. Ceramic tile + finishes nearing completion phase 7. Temporary ED trailers have were demolized on 25 Jul 15. Negotiations underway on DHA approved User Change to delete work on 2 floors from the contract.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 78144 | Medical Clinic Addition | 78144 |  |  |  | 2013-10-08 | 2015-03-17 | 2015-11-09 | 0.97 | 2015-09-11
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71325 | Medical Clinic Replacement | 71325 |  |  |  | 2013-10-24 | 2016-10-23 | 2016-12-22 | 0.22 | 2017-07-21 | Structural steel erection continues. Contingencies at District: $279,302.19. Cat E&F Equip funds at District: $1,723,000
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) | 72722 | 22793000 | FY13 - PN76558 |  | 2011-10-25 | 2014-09-09 | 2015-04-17 | 0.99 | 2015-03-18 | All mod work completed. Construction has been substantially complete since 17 Apr 2015. All physical work less plenum to be complete 18 Sep.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) | 72722 |  | FY13 - PN76558 |  | 2011-03-20 | 2011-04-01 | 2011-04-01 | 1 | 2011-04-01 | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) | 72722 |  | FY13 - PN76558 |  | 2011-07-01 | 2014-09-27 | 2015-03-18 | 0.99 | 2015-03-18 | Leased Swing Space awarded for risk mitigation.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) | 72722 | [8 empty] | Contracting working on construction award processing of this exterior plenum. Procurement Integrity Act limits further information relative to the selection process.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 62189 | Medical / Dental Clinic Replacement | 62189 | 7033000 | FY09 - PN00001 VCOE FY13 - PN76558 |  | 2009-06-01 | 2011-10-26 | 2012-02-09 | 1 | 2012-06-04 | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71317 | Medical Clinic Replacement | 71317 |  |  |  | 2013-12-06 | 2016-12-30 | 2017-11-07 | 0.68 | 2016-04-05
2015-08-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 81706 | NiCOE Satellite, Infrastructure Support | 81706 |  |  |  | 2014-09-15 | 2015-10-28 | 2015-10-28 | 0.82 | 2015-10-28 | The installation of the pad mounted transformer is complete as of 13 Jul 15. This completes all of phase II work. Phase III work is expected to begin on 2 Sep 15.
2015-08-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 1 | 64179 |  |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 1 | 2011-08-15 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2015-08-31 | 2009 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 2 | 64180 |  |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 1 | 2011-08-15 | See above.
2015-08-31 | 2010 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 3 | 69840 |  |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 1 | 2011-08-15 | See above.
2015-08-31 | 2011 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 4 | 70990 |  |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 1 | 2011-08-15 | See above.
2015-08-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64188 | Health Clinic | 64188 |  |  |  | 2008-06-30 | 2010-05-10 | 2010-05-10 | 1 | 2010-05-17 | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481 |  |  |  | 2013-05-29 | 2016-11-26 | 2017-01-01 | 0.34 | 2017-10-03 | NOTE 1 : Hospital - Construction Progress: Sch. 53% Act. 34%: Current contractual construction completion date is 1 Jan 2017. The estimated construction completion is currently 4th Q 2017 with a BOD of 3 Oct 2017. Placement to date: $217.0M as of 5 Aug 15. Momentum, subcontractor control, and quality continue to impact production. Reset meetings have been held at the Principal and field levels with the intent of revisiting the business rules and issue resolution processes for the remainder of the project in an attempt to regain trust among the execution level team. Still awating word on the possible $50M decrement to the FY16 increment being considered by Congress. If approved, an FY17 project would have to be created with a PA of $50M.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481 |  |  |  | 2011-11-02 | 2013-08-13 | 2013-08-29 | 1 | 2013-10-12 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481 |  |  |  | 2011-08-23 | 2012-07-05 | 2012-08-20 | 1 | 2012-12-31 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481 |  |  |  | 2012-08-28 | 2013-06-19 | 2013-06-11 | 1 | 2013-10-17 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481 |  |  |  | 2014-07-30 | 2014-09-28 | 2015-08-27 | 0.98 | 2015-08-27 | Sch. 98% Act. 98%. The contractor began construction 3 Nov 14. Pipe installation was completed on 26 Aug. Pavement was completed 27 Aug. Completion of the metering manhole still pending. Installation of the manhole will begin the week of 31 Aug with completion estimated to be the week of 7 Sep. 100% project completion currently scheduled for rmid September.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481 |  |  |  | 2012-09-04 | 2014-01-04 | 2014-01-04 | 1 | 2015-09-16 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481 | [6 empty] | 1 |  | Temp power costs.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 2 | 77251 |  |  |  | 2013-05-29 | 2016-11-26 | 2017-01-01 | 0.34 | 2018-05-26 | See Note 1 above.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 3 | 72786 |  |  |  | 2013-05-29 | 2016-11-26 | 2017-01-01 | 0.34 | 2018-05-26 | See Note 1 above.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 | 77163000 | FY09 - PN00180 |  | 2013-05-29 | 2016-11-26 | 2017-01-01 | 0.34 | 2018-05-26 | See Note 1 above.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 |  |  |  | 2013-10-21 | 2014-10-24 | 2014-10-24 | 1 | 2014-11-24 | Only the re-seeding of the Helipad area remains as a punchlist item; to be completed in Sep 2015.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 |  |  |  | 2014-07-30 | 2014-09-28 | 2015-08-10 | 0.81 | 2015-07-15 | Sch. 98% Act. 98%. The contractor began construction 3 Nov 14. Pipe installation was completed on 26 Aug. Pavement was completed 27 Aug. Completion of the metering manhole still pending. Installation of the manhole will begin the week of 31 Aug with completion estimated to be the week of 7 Sep. 100% project completion currently scheduled for rmid September.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 | [8 empty] | Parking Package “B”:(small business- LPTA) Est. Award: $5.5M •Solicitation Package is complete. •Proposed Award Date: FY16
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 |  |  |  | 2013-05-29 | 2016-11-26 | 2017-01-01 | 0.34 | 2018-05-26 | See Note 1 above.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 | [6 empty] | 0 |  | ACP Package: (small business-Best Value) Est. Award: $24.7M •Solicitation package is complete. •Proposed Award Date: FY16
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 | [6 empty] | 0 |  | No update this reporting period.
2015-08-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81047 |  |  |  | 2013-05-29 | 2016-11-26 | 2017-01-01 | 0.34 | 2018-05-26 | See Note 1 above.
2015-08-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81047 | [6 empty] | 0 |  | Landscaping Package: (small business-LPTA) Est. Award: $22.7M •Solicitation package is complete. •Proposed Award Date: FY16.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72754 | Ambulatory Care Center Phase 3, Inc 1 | 72754 |  |  |  | 2012-11-01 | 2014-07-29 | 2015-11-30 | 0.97 | 2016-04-06 | Note 2: 1. Construction Progress: Sch. 97%, Act. 97% 2. The current Ph 3 completion date is 30 Sept 2015 3. Including the estimated cost of pending modifications Ph 3 is within the BTR limit 4. The BOD will shift from 1 Oct to 22 Dec 2015
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 80793 | Ambulatory Care Center Phase 3, Inc 2 | 80793 |  |  |  | 2012-11-01 | 2014-07-29 | 2015-09-30 | 0.97 | 2016-04-06 | See Note 2 above.
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69626 | Burn Rehabilitation Center | 69626 |  |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 1 | 2011-08-15 | Contract closeout ongoing.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650 | 3850000 | FY09A - PN100040 |  | 2010-11-08 | 2014-05-31 | 2015-10-01 | 0.98 | 2015-10-01 | Sch. 100% Act. 97%. USACE has seen an increase in punchlist resolution the week of 31 Aug. QA team continues to push areas to be completed to ensure IO&T is not impacted. The commissioning process continues to identify control issues. All issues are being addressed, fixed and retested. Overall commissioning is approx 94% complete and “pull the plug” test is scheduled for 10 Sept. *Furniture - MILHOT continues to work in all three clinics, basement, and 1st floor; started 3rd floor the week of 31 Aug. * Site - There continues to be progress with site work, currently still tracking mid Nov for completion of last parking lot.
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650 |  |  |  | 2010-06-15 | 2012-02-25 | 2012-05-02 | 1 | 2012-06-02 | Construction 100% Complete
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650 |  |  |  | 2010-04-05 | 2010-05-30 | 2010-06-07 | 1 | 2010-06-30 | Construction 100% Complete
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650 |  |  |  | 2010-06-18 | 2010-10-18 | 2010-10-04 | 1 | 2010-10-05 | Construction 100% Complete
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650
2015-08-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650 |  |  |  | 2011-01-06 | 2012-06-29 | 2015-06-30 | 0.99 | 2013-12-15 | Contractor working on additional punchlist items and close out documentation.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 71318 | Dental Clinic Replacement | 71318 | 3144000 | FY14 - PN77922 |  | 2010-04-06 | 2012-01-06 | 2012-09-01 | 1 | 2012-04-30 | Retainage on the project recently paid, processing close out. The project funds have been returned.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center, Phase 1 | 72430 |  |  |  | 2010-10-04 | 2013-02-20 | 2013-08-30 | 1 | 2013-11-19 | 1. Phase 1B is complete and turned over to the Air Force. BOD was 19 Nov 13 and the Interim DD 1354 was signed by BCE on 5 Dec 13. The 1B warranty expired in Nov 2014. 2. Post Warranty Deficiencies: a. JE Dunn completed replacement of exterior stone block on the facade of 1B b. Repair of the concrete cracking in the garage (Ph 1A) was completed, but the work is under review c. JE Dunn’s plan to address the stone block on the parking garage is still pending d. JE Dunn has indicated they intend to address the Ph 1B bathrooms ABA/ADA Non-compliance; JED corrective action plan received on 8/26, reviewed by USACE and response sent to JED on 9/1.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center, Phase 1 | 72430 |  |  |  | 2010-10-04 | 2012-02-26 | 2012-11-30 | 1 | 2012-12-13 | Remarks noted above.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center Phase 2 | 72752 | 75054000 | FY11 - PN72727 FY11 - PN62886 FY14- PN77000 PN - 77000 |  | 2011-12-02 | 2013-10-01 | 2015-12-22 | 0.93 | 2016-04-06 | 1. Phase 2 is 93% complete / 93% scheduled 2. The Ph 2 BOD will shift as noted under Lackland ASC Ph 3 from 1 Oct to 22 Dec 2015 3. Including pending modifications the Ph 2 CWE remains within the current authorization A) resolution of generators may require additional modification to Ph 2 contract, and B) delivery of O2 for medical gas certification (action with 59th MW) *Generator Issues - risk is high to impact the BOD/IO start
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 51969 | Hospital Nutrition Care Department Add/Alt | 51969 |  |  |  | 2012-10-02 | 2014-10-30 | 2015-12-23 | 0.98 | 2015-10-31 | Final inspection held 28 Aug - 1 Sep; inspection failed due to several equipment problems . Manufacturers and installers on-site to troubleshoot. Working final punch list items. Nutrition Care transition scheduled to start 14 Sep and end 14 Oct. Back in business date is scheduled for 15 Oct but could slip (day for day) if equipment issues takes longer than 9 Sep to fix. Contractor filed seven claims in Nov 14 totaling $1.4M; KO denied; DCAA audit ongoing, Alternative Dispute Resolution (ADR) tentatively scheduled for 13-14 Oct 15.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81340 | SAMMC Hyperbaric Facility Addition | 81340 |  |  |  | 2015-07-10 | 2016-09-30 | 2016-09-30 | 0.14 | 2016-12-28 | Final design completed 20 Jul. Mass excavation delayed due to late approval of instation passes for workers and KTR awaiting approval of SWPPP
2015-08-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81423 | Medical Clinic Replacement (Reid Clinic) | 81423 |  |  |  |  | 2017-12-18 |  |  | 2018-03-16 | Contract awarded to J.E. Dunn construction (on SWL Air Force Medical MATOC) on 3 Sep 2015.
2015-08-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80792 | Site Development, NiCOE | 80792 |  |  |  | 2012-09-10 | 2013-05-31 | 2013-08-29 | 1 | 2013-06-30 | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Project financial closeout is ongoing. Update 03 AUG 2015: Received release of claims from American Water and returned all unobligated MIPR'd funds. Still waiting for return of unobligated MIPR'd funds requested by POC for Dominion Virginian Power. Once these funds are returned project will be closed out.
2015-08-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69427 | Hopsital Replacement, Inc 1 | 69427 |  |  |  | 2007-10-11 | 2011-03-01 | 2012-01-31 | 1 | 2011-08-01 | Project ready for closeout
2015-08-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69427 | Hopsital Replacement, Inc 4 | 69865 |  |  |  | 2007-10-11 | 2011-03-01 | 2012-01-31 | 1 | 2011-08-01 | All Unobligated funds $245K were returned. 1354 is being prepared.
2015-08-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69427 | Hopsital Replacement, Inc 5 | 77071 |  |  |  | 2007-10-11 | 2011-03-01 | 2012-01-31 | 1 | 2011-08-01 | See above.
2015-08-31 | 2010 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64241 | Dental Clinic | 64241 |  |  |  | 2010-05-18 | 2011-09-10 | 2012-12-06 | 1 | 2012-09-25 | Construction Contract and Project in Close Out Phase. Final 1354 for CIP Transfer is in process. Fiscal Closeout now 31 OCT 2015, along with PN 71251.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 71251 | Dental Clinic Replacement | 71251 | 146000 | PN - 72752 |  | 2011-05-17 | 2011-09-10 | 2012-12-06 | 1 | 2012-09-25 | Project and Contract is in Final Closeout phase. Final 1354 for CIP transfer is in process. Fiscal Closeout now 31 OCT 2015, along with Project # 64241.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 78146 | Veterinarian Facility | 78146 |  |  |  | 2014-02-28 | 2014-12-06 | 2015-11-06 | 0.97 | 2015-08-24
2015-08-31 | 2015 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 81430 | Hospital Add/CUP Replacement | 81430 |  |  |  | 2014-09-02 |  | 2015-11-21 | 0 |  | The construction contract will also include turnkey FFE and medical equipment increasing the procurement to > $50M. DHA supports Jan 2016 award. NAO has obtained and MOA to secure capacity on the SWL iDBIO MATOC for award.
2015-08-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80094 | Veterinary Clinic | 80094 |  |  |  | 2013-01-04 | 2014-07-05 | 2014-12-12 | 0.98 | 2014-12-12 | The ACO has forwarded a serial letter to the Contractor stating that all closeout items (including LEED) must be closed out by 30 Sept 2015. If the Contractor responds appropriately by 30 Sept 15, closeout will likely occur by mid December (16 Dec 15).
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 64473 | Medical/Dental Clinic | 64473 |  |  |  | 2008-09-30 | 2010-02-20 | 2010-03-17 | 1 | 2010-03-17 | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2015-08-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81627 | NiCOE Satellite, Infrastructure Support | 81627 | [8 empty] | NWS Design team has reviewed the CWE and will revise the depth of excavation. JBLM will allow disposal of contaminated and noon-contaminated soils on Post. Received $50K in additional P&D funds for design revisions on 4 Sep 15.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction |  | BAHRAIN | 81436 | Medical/Dental Clinic Replacement | 81436 | [8 empty] | Planned Aug 2015 award of a Design-Build contract with a one-year design period delayed to Dec 2015. Delay in advertisement/award due to site availability, pending completion of an on-going MCN project, the P908 Operations and Support Facilities. A large required security-related modification to this ongoing project is the primary cause of the schedule push. New site availability date is Nov 2016. Authority to Advertise received 25 Aug 15 and RFP was issued the same day.
2015-08-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction |  | GERMANY | 68974 | Computer Operations Center | 68974 |  |  |  | 2011-05-11 | 2011-01-31 | 2011-12-09 | 1 | 2011-12-09
2015-08-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction |  | GERMANY | 68974 | Computer Operations Center | 68974 |  |  |  | 2011-04-11 | 2011-01-31 | 2011-12-09 | 1 | 2011-12-09
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-01-13 | 2021-07-20 | 2022-03-30 | 0.05 |  | Environmental Compensation Also includes: Lots 7.2-7.4 Initial Compensation Measures - German government solicitation and award dates to German industry are estimated.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-01-20 | 2014-04-04 | 2014-04-04 | 0.99 |  | Lot 1 Temporary Construction Fence - Construction essentially completed April 2014, with remaining access from the east closed off as of 1 May 2015. FRG Security Contractor is on site and will monitor access from the L369 construction gate on the west side.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-06-16 | 2014-10-29 | 2015-01-21 | 1 | 2014-08-29 | Lot 2.1 Demolition, Site Clearing - Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Final inspection held on 21 Jan 2015, and final contract document provided by FRG (ABG7).
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2015-04-20 | 2016-04-30 | 2016-04-30 | 0 | 2016-04-30 | Lot 2.2 Mass Grading - Contract solicitation went out on 11 Dec 2014; bid opening was 10 Feb 2015. NAU signed the ABG4 (contract to FRG) on 20 Apr 2015, LBB to countersign and awarded to industry 22 Apr 2015. Contract amount is $5.3M, substantially less than expected. Contractor mobilization began on 18 May 2015.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2016-01-15 | 2016-12-15 | 2017-12-15 | 0 | 2016-01-15 | Lot 3.1 Utilities to site - original ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines and change to double-wall pipe through water protection zone. FRG anicipates solicitation release in Sep 2015, with award by Feb 2016. Construction originally targeted for completion Dec 2016; however, now reliant on Lot 3.7 and City of Ktown completion of 6km sewer line connection. Construction completion now targeted for Dec 2017.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-08-22 | 2015-03-30 | 2015-05-01 | 1 | 2015-03-30 | Lot 3.2 Traffic Light System - Traffic light system in operation since May 2015.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-10-08 | 2014-12-31 | 2014-12-31 | 1 | 2014-12-31 | Lot 3.3 Construction Sign - Completed in December 2013.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-08-11 | 2014-10-16 | 2014-10-16 | 1 | 2014-10-16 | Lot 3.4 Gas Line Relocation - Construction complete.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2016-05-30 | 2018-02-28 | 2018-02-28 | 0 | 2016-05-30 | Lot 3.5 Transformers/Substation - This portion of the ROBMCR project will be accomplished as a direct project through NAU. NAU currently coordinating D/B RFP package with target solicitation Jan/Feb 2016 and construction contract award targeted for May 2016.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2016-01-15 | 2016-12-15 | 2016-06-15 | 0 | 2016-06-15 | Lot 3.6 Water Connection to WZV-Weilerback system - The FRG will coordinate the connection requirements with water provider SWK. Dates forthcoming.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-12-10 | 2021-12-17 | 2022-03-30 | 0.01 | 2021-12-17 | Lot 3.9 Site Security - FRG awarded contract in Dec 2013. Security contractor has mobilized and began operation on-site starting 1 May 2015.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2015-11-30 | 2021-12-17 | 2022-03-30 | 0 | 2021-12-17 | 3.10 Site Logistics - Details to be determined by FRG; contract will be for execution of the entire internal and external construction site logistics.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2015-10-30 | 2016-04-30 | 2016-04-30 | 0 | 2016-04-30 | Lot 2.3 Landfill Remediation. No issues, on track for Oct 2015 award and construciton completion by 30 Apr 2016.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2014-10-23 | 2014-12-31 | 2014-12-31 | 1 | 2014-12-31 | Communications Cable relocation - Action 100% complete
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  |  |  | 2015-03-30 | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | Construction Additional Services
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  |  | 2016-07-15 | 2016-12-30 | 2017-12-30 | 0 | 2017-12-30 | Construction Measures, Roadways, & Site Utilities - FRG revising and coordinating lot requirements for campus roadways, utilities, and additional construction measures not included in current lot packages. Dates subject to change pending refinement of lots and corresponding schedules.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  |  | 2016-04-15 | 2016-04-15 | 2016-04-15 | 0 | 2018-04-15 | Lot 4 Access Control Point, Bridge, External Roadways - 65% OTS design review for Bridge held in August 2015; 65% OTS review for ACP to be conducted in late September 2015. Contract award targeted for June 2016, with construction completion December 2019. FRG coordinating construction sequencing with ACP, Bridge, and PIK L369 Traffic Circle; dates to be refined and adjusted as designs mature.
2015-08-31 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 3 | 72662 |  |  |  | 2017-04-30 | 2019-04-30 | 2019-04-30 | 0 | 2019-04-30 | Lot 5.1 Parking Structures, Campus Roadways - Previously included in MedCen 20% design. FRG kicked off post 20% design on 9 Dec 2014. The 35% design due in Sep 2016. This lot will be included in the cost savings discussions.
2015-08-31 | 2015 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 4/5 - 2015/2016 | 76872 |  |  |  | 2019-02-12 | 2021-12-08 | 2022-03-30 | 0 | 2022-11-08 | Medical Center (Bed Tower, D&T, Clinics, Admin) - US led 20% MedCen final design submitted 2 Aug 2013. USACE is transitioning design to FRG. FRG target for announcement of AE#2 selection is now September 2015, with award following the 21-day protest period in October 2015. FRG schedule dates are estimated at this time and will be refined as AE#2 progresses the design.
2015-08-31 | 2008 | Defense Health Agency | Major Military Construction |  | GERMANY | 52332 | Medical Clinic Replacement | 52332 |  |  |  | 2008-08-29 | 2012-05-15 | 2012-07-13 | 1 | 2011-10-08 | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. German government confirmed 23 Jun 2015 that resolution will not be this fiscal year.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66693 | Health/Dental Clinic Replacement | 66693 |  |  |  | 2014-02-03 | 2016-04-12 | 2016-04-12 | 0.71 | 2016-06-11 | Current work includes: Construction of interior drywall walls is ongoing (2nd flr), floor screed is ongoing (1st & 2nd flr). Electrical and mechanical rough-in is ongoing (1st flr & 2nd). Communications cabling is ongoing (1st & 2nd flr.), insulation of the ductwork is ongoing (1st & 2nd flr). Sprinkler and sanitary sewer line install is ongoing (1st & 2nd flr.). Install of radiators (1st flr.) install of wall plaster, interior walls (1st flr), and install of ceiling grid (1st flr) has begun.Install of vegetative roof is ongoing. CRITICAL - CAT E/F Equipment must be awarded by 30 Sep 2015 as funds expire for new obligations. MEDCOM is aware and believes they can meet this date (DLA contract being used for ~$460k). Anticipate receiving funds 3 Sep. German government negotiating commissioning modification.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66588 | Health Clinic Add/Alt | 66588 |  |  |  | 2013-04-08 | 2016-05-30 | 2016-09-04 | 0.75 | 2017-01-07 | Addition turned over 26 Jun 2015. Ribbon cutting for addition held 14 Aug 15. Renovation of the existing clinic began 11 Aug 15. Final construction completion (Renovation) may be delayed due to contractor delay request for 95 days. BauAmt currently evaluating delays.
2015-08-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction |  | JAPAN | 78853 | New Clinic Addition | 78853 | [8 empty] | DHA issued DA memo dated 22 Dec 2014 cancelled the FY11 project. FY11 funds ($46,355.39) were revoked on 24 Jul 2015. No unobligated funds remain. HQUSACE code 8 (Project Cancelled) design directive received 2 Sep 2015.
2015-08-31 | 2011 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 51740 | Health/Dental Clinic Replacement | 51740 | 6652000 | PN - 71634 PN - 77000 |  | 2011-08-26 | 2013-05-13 | 2014-04-23 | 1 | 2014-04-23 | The Carroll Dental Clinic OIC and NCOIC were in the lead for a ribbon cutting ceremony, however, per HFPO, a ceremony does not appear to be occurring. Awaiting final billing ($17,794.00) from DLA for LOGCAT F equipment training.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72420 | Medical/Dental Clinic Addition | 72420 |  |  |  | 2013-06-05 | 2015-02-25 | 2015-03-29 | 0.99 | 2015-05-06 | Contingency Amounts: District $1,811; HQ Mgmt $0. Final Inspection was completed and keys turned over 27 Mar 15. A simple ribbon cutting ceremony was conducted 6 May 2015. No invitations were sent to outside organizations. Completed pending modifications of LPG system in room 141, explosive proof fan in room 126, and exit lights at 2nd floor on 29 Jul 2015, and washer/disinfector in DIPC room on 13 Aug 2015. A modification to include Government Furnished Government Installed equipment in the BIM is being processed.
2015-08-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72419 | Hospital Addition/Alteration | 72419 |  |  |  | 2013-09-26 | 2017-08-08 | 2017-10-24 | 0.43 | 2018-01-08 | Contingency Amounts: District $253,034; HQ Mgmt $795,500. Ongoing work: TPO membrane for roofing, EIFS, Main electrical work, HVAC duct work, steel framing/drywall, upper level waste waterlines, and lower level wall painting.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement | 71550 | 205000 | PN - 14010 |  | 2010-12-14 | 2012-08-10 | 2012-09-28 | 1 | 2012-09-28 | Estimated financial closure: 31 Dec 2015. The base originally requested an additional $65,000 to replace the clinic main entrance doors. This was inadequate and a further $80,000 has been requested. Base will now have $145,000 to replace the doors. Update 02 Sept 2015: Base are ready to place the order for the structural survey and will advise of the programme accordingly.
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement | 71550 |  |  |  | 2013-07-01 | 2013-08-30 | 2013-08-30 | 1 | 2013-08-30
2015-08-31 | 2010 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement | 71550 |  |  |  | 2015-03-03 | 2015-01-30 | 2015-06-30 | 0 | 2012-09-28 | Contractor has queried the original steelwork design, DIO currently investigating the query. No progress on site until resolved. DIO cannot close main project until this local order is complete. Awaiting contractor to provide detail to support claim that original steelwork design is not to standard.
2015-08-31 | 2012 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 72727 | Medical/Dental Clinic Replacement | 72727 |  |  |  | 2014-05-06 | 2015-10-30 | 2016-01-08 | 0.85 | 2015-08-27 | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14. Contracting Officer has granted a nil cost extension of time to 25 Dec 2015 based on delays resulting from the original groundwork subcontractor withdrawing from the contract and from a national shortage of labour delaying the brickwork trade. Contractor has requested a further extension of time of 14 calendar days due to late information from SPAWAR. this is currently being reviewed by the Contracting Officer. Contracting Officer approved an extension of time to 8 Jan 2016. Construction complete and BOD achieved 27 August 2015. US Outfitting contractor SIOTS to carry out work under separate contract and to facilitate move from existing clinic (Building 140). VINCI will remobilise in November to demolish building 140 to complete the contract.
2015-08-31 | 2015 | Defense Information Systems Agency | Major Military Construction | ARIZONA | UNITED STATES | 15DISA01 | JITC Building 52120 Renovation | [9 empty] | PA: $1.871M. Design/Renovation of Garrison existing Bldg 52120 for JITC Fort Huachuca. USACE to conduct site survey 27-28 Apr 2015. Design charrette held 30 Jun 2015. The 65% design received. Comments due 14 Sept 2015.
2015-08-31 | 2015 | Defense Information Systems Agency | Major Military Construction | ARIZONA | UNITED STATES |  | Design of Bldgs 52101, 52110, 52111 for JITC | [9 empty] | PA: $745K. Design of Garrison existing Bldgs 52101, 52110, 52111 for JITC Fort Huachuca. Design charrette rescheduled Sept 2015. Design funding covered under consolidated FY15 Planning and Design Appropriation. USACE will schedule early FY16.
2015-08-31 | 2014 | Defense Information Systems Agency | Major Military Construction | HAWAII | UNITED STATES | 14DISA01 | DISA Pacific Facility Upgrade | [9 empty] | PA: $2.615M. NAVFAC preparing RFP for Design. RFP will take into consideration the Navy's Energy Project to replace the 2 existing chillers. Awaiting schedule dates for three (3) Day Charrette in early FY16.
2015-08-31 | 2013 | Defense Information Systems Agency | Major Military Construction | ILLINOIS | UNITED STATES | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  |  |  |  | 2014-03-01 | 2015-12-30 | 2016-03-11 | 0.76 |  | PA: $77.515M. 3 separate contracts: Soil Remediation; Construction; Demo Bldg 3189. Soil Remediation: COMPLETED; Construction ESC: 11 Mar 2016;. Demo of Bldg 3189 funding ($2.153M) provided to USACE on 30 Jun 2015.
2015-08-31 | 2015 | Defense Information Systems Agency | Major Military Construction |  | AUSTRALIA | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) | [9 empty] | PA: $9.6M. NAVFAC to construct Electronic Equip Bldg, Antenna Foundations for AN/GSB 52B Medium Satellite Earth Terminals. RFI issued 16 Apr 15. No responses. J&A approved. Awaiting DB RFP pkg ESC Oct 2016. Project ESC: FY18.
2015-08-31 | 2013 | Defense Information Systems Agency | Major Military Construction |  | GERMANY | 13DISA01 | DISA Europe Facility Upgrade | [7 empty] | 0 |  | PA: $2.224M. Contract awarded to Bauamt on 19 Aug 2015. Awaiting kick off meeting.
2015-08-31 | 2010 | Defense Intelligence Agency | Major Military Construction | ALABAMA | UNITED STATES | DIA10-002 | Replace MSIC Explosive Ordinance Exploitation (EOE) Complex |  |  |  |  | 2012-07-20 | 2014-01-20 | 2014-05-21 | 1 |  | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved. Contingency funds will be used in FY15 for within scope modifications.
2015-08-31 | 2008 | Defense Intelligence Agency | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 154207 | Emergency Backup Water System |  |  |  |  | 2009-10-03 | 2011-09-16 | 2012-01-20 | 1 | 2012-01-20 | Approp. - $1,012
2015-08-31 | 2011 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA11-002 | JBAB Paving of Gravel Parking Lot |  | 690000 | DIA10-001 |  | 2011-07-20 | 2012-07-18 | 2012-07-25 | 0.99 | 2012-07-25 | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000001 | DIAC Parking Garage Replacement |  |  |  |  | 2014-10-23 | 2016-03-02 | 2016-06-30 | 0.01 |  | Approp. - $13,645 - $793,156 CAT I obligated. Construction start 10 August 2015. Closures/reduction of available parking spaces in the West Parking Lot, street parking along Chappie James Boulevard, and in the North West parking lot in progress. Amount of $1.6M added to this project from Construction of the Remote Delivery Facility, DIA project DIA12000005 as a below threshhold realignment. Funds are committed awaiting contract award (obligation).
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000003 | DIAC Chilled Water Project for Data Center | [9 empty] | Estimates indicate project costs exceed programmed amounts. DIA initiating reprogramming action to move funds to UPS for Data Center. Awaiting reprogramming action approval.
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center | [9 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions to add funds from the DIAC Chiller project. Reprogamming action currently with OMB; expect approval soon.
2015-08-31 | 2013 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA13000001 | Parking Garage Demolition | [9 empty] | This line was reduced due to sequestration. The remaining funds are insufficient to complete demolition of the existing parking garage. DIA is currently exploring options. Contract is not awarded at this time.
2015-08-31 | 2012 | Defense Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | DIA12000005 | Construction of Remote Delivery Facility (RDF) Meeting SCIF Standards |  | 1600000 |  |  | 2013-10-10 | 2014-09-30 | 2015-07-31 | 0.98 |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Air barrier completed waiting for final testing; commissioning started 26 August 2015; R2 and R3 did not function properly; rescheduling new date. Awaiting Hood system install. Backpack sytem installed, tested and training provided 1 September 2015. Amount of $1.6M diverted to DIA Parking Garage Replacement, project DIA12000001 as a below threshhold re-alignment.
2015-08-31 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction |  | KOREA, SOUTH | DIA10-001 | FOB-K Renovation of Two Buildings to Include Administrative and SCIF Spaces |  |  |  |  | 2012-04-09 | 2013-10-09 | 2013-10-17 | 1 |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project closed out 10 May 2015.
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Major Military Construction | HAWAII | UNITED STATES | DSFH1401 | Alter Warehouse Space - JB PH Hickam |  |  |  |  | 2015-06-02 | 2016-10-14 | 2016-10-14 | 0 |  | wo# 1167459
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | HAWAII | UNITED STATES | DSFH1401 | Upgrade Administrative Space - JB PH Hickam | DSFH14U2 |  |  |  | 2015-06-02 | 2016-10-14 | 2016-10-14 | 0 |  | wo# 1362232
2015-08-31 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P646 | DSS Headquarters Addition |  |  |  |  | 2013-04-30 | 2014-07-22 | 2015-09-09 | 1 | 2014-09-26 | [Solicitation/Advertise Date: Phase I - 21-Sep-2012 Phase II - 20-Dec-2012]
2015-08-31 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P659 | Defense Access Road Improvements-Telegraph Rd |  |  |  |  | 2013-08-01 | 2014-08-01 | 2015-05-15 | 1 | 2015-05-15 | This project is being managed and funded via FHWA. [Solicitation/Advertise Date: Phase I - 22-Jan-2013 Phase II - 04-Apr-2013]. Placed in service date is the substantial completion date. Punchlist items remain.
2015-08-31 | 2014 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1404 | General Purpose Warehouse - Tracy |  |  |  |  | 2014-10-02 | 2016-02-25 | 2016-04-04 | 0.12
2015-08-31 | 2011 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX0802 | Replace Headquarters Facility - New Cumberland |  | 1950000 | FY13 Andersen / FY13 Grissom |  | 2012-08-30 | 2015-09-18 | 2016-01-29 | 0.9 | 2016-02-29
2015-08-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1202 | Replace General Purpose Warehouse - New Cumberland |  |  |  |  | 2014-01-14 | 2015-08-27 | 2015-07-20 | 0.97 | 2015-07-20 | 2853 Reprogramming
2015-08-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1203 | Upgrade Access Control Points - New Cumberland |  |  |  |  | 2013-11-01 | 2016-05-05 | 2016-09-18 | 0.32
2015-08-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1301 | Replace Communications Building - New Cumberland |  |  |  |  | 2014-10-31 | 2016-07-28 | 2016-08-03 | 0.22
2015-08-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland |  |  |  |  | 2014-07-11 | 2016-01-02 | 2016-03-06 | 0.29 |  | 2853 Reprogramming
2015-08-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC1103 | Replace Hydrant Fuel System - Davis Montham AFB |  |  |  |  | 2012-11-13 | 2014-11-03 | 2015-05-15 | 1 | 2015-04-09
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC13S4 | Replace Truck Unload Facility - Yuma |  |  |  |  | 2013-09-30 | 2014-08-03 | 2015-10-11 | 0.06 | 2015-10-11 | 2853 Reprogramming wo# 1124259
2015-08-31 | 2014 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | DESC14U2 | Replace Existing Refueler Parking Lot - Davis Monthan AFB |  |  |  |  | 2012-11-13 | 2014-11-03 | 2015-05-15 | 1 | 2015-04-09
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC 1306 | Replace Fuel Pier - Pt Loma |  |  |  |  | 2014-01-15 | 2017-10-14 | 2017-10-14 | 0.52 | 2017-10-14 | wo# 1124159
2015-08-31 | 2008 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INC #1 - NAV SUP Fleet Logistics Center, Point Loma San Diego |  |  |  |  | 2008-10-22 | 2013-09-23 | 2014-02-28 | 0.99 | 2014-01-17 | wo# 861477
2015-08-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) - NAV SUP Fleet Logistics Center, Point Loma San Diego |  | 3109000 | FY09 PH-H, FY10 Travis, FY13 New Cumberlan Sewage Treatment |  | 2011-03-22 | 2013-09-23 | 2014-02-28 | 0.99 | 2014-01-17 | wo#861477
2015-08-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) - Pt. Loma |  | 3770000 | FY13 New Cumberland Sewage Treatment, FY14 Tinker |  | 2011-03-30 | 2013-09-23 | 2014-02-28 | 0.99 | 2014-01-17 | wo#974938
2015-08-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma |  |  | FY13 Grissom |  | 2012-03-29 | 2013-09-23 | 2014-02-28 | 0.99 | 2014-01-17 | wo# 113174
2015-08-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1205 | Replace Fuel Facilities - San Clemente Is. |  |  |  |  | 2013-02-28 | 2015-03-24 | 2015-08-30 | 0.82 |  | 2853 Reprogramming wo# 973902
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1304 | Replace Fuel Storage - Edwards AFB |  |  |  |  | 2013-12-04 |  | 2017-03-07 | 0.82 | 2017-03-07
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC14U1 | Upgrades to Fuel Pier for Fire Protection - Pt Loma |  |  |  |  | 2014-06-30 | 2015-11-15 | 2015-11-15 | 1 |  | wo# 1170569
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | DELAWARE | UNITED STATES | DESC1305 | Replace Truck Off-Load Facility - Dover AFB |  |  |  |  | 2013-11-04 |  | 2015-04-28 | 0.78 | 2015-04-28
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City |  |  |  |  | 2014-06-30 | 2015-11-15 | 2015-11-15 | 0.74 | 2015-11-15 | wo# 1302082
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1391 | Construct Fuel Storage Facility - Hurlburt AFB |  |  |  |  | 2013-09-24 |  | 2015-12-25 | 0.86 | 2015-12-25
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC13S2 | Replace Fuel Pipeline - Tyndall AFB |  |  |  |  | 2015-01-27 | 2016-05-06 | 2016-08-05 | 0.44
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1402 | Replace Fuel Pipeline - Jacksonville |  |  |  |  | 2014-06-30 | 2015-10-10 | 2015-10-10 | 0.78 | 2015-10-10 | wo# 1163305
2015-08-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC1353 | Replace Hydrant Fuel System - Robins AFB |  |  |  |  | 2015-09-30 | 2017-09-27 | 2017-12-26 | 0
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC14S2 | Replace Ground Vehicle Fueling Facility - Moody AFB |  |  |  |  | 2014-05-07 | 2015-05-07 | 2015-12-24 | 0.82
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC1504 | Upgrade Fuel Island - Hunter AAF |  |  |  |  | 2014-10-16 | 2016-04-08 | 2016-07-07 | 0.22
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | GUAM | GUAM | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB |  |  |  |  | 2014-06-30 | 2016-02-06 | 2016-10-26 | 0.32 | 2016-09-06 | wo# 1125022
2015-08-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESC1551 | Upgrade fire Suppression and Ventilation System - Rd Hill; JB Pearl Harbor - Hickam |  |  |  |  | 2015-09-30 | 2018-07-08 | 2018-07-08 | 0 |  | wo# 1306143
2015-08-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESI1101 | Alter Warehouse Space - JB PH Hickam |  |  |  |  | 2012-08-13 | 2013-06-14 | 2014-04-29 | 0.99 | 2014-09-30 | wo# 972725
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | INDIANA | UNITED STATES | DESC1301 | Replace Hydrant Fuel system - Grissom ARB |  |  |  |  | 2015-09-30 | 2017-03-30 | 2017-03-30 | 0
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | LOUISIANA | UNITED STATES | DESC1390 | Upgrade Pumphouse - Barksdale AFB |  |  |  |  | 2013-09-09 | 2015-02-26 | 2015-02-26 | 1 | 2015-02-26 | wo# 1123107
2015-08-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | MASSACHUSETTS | UNITED STATES | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB |  | 1761000 | FY14 Iwakuni |  | 2013-06-18 | 2015-12-10 | 2016-02-08 | 0.9 |  | 2853 Reprogramming
2015-08-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | MICHIGAN | UNITED STATES | DESC1510 | Replace Fuel Distribution Facilities, Selfridge ANG |  |  |  |  | 2015-09-30 | 2018-01-16 | 2017-09-06 | 0
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW JERSEY | UNITED STATES | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst |  |  |  |  | 2014-11-18 | 2016-05-11 | 2016-08-09 | 0.02
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW MEXICO | UNITED STATES | DESC1407 | Replace Hydrant Fuel System, Holloman AFB |  |  |  |  | 2015-04-28 | 2017-01-10 | 2017-01-10 | 0
2015-08-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | NORTH CAROLINA | UNITED STATES | DESC1459 | Replace Hydrant Fuel System, Seymour Johnson AFB |  |  |  |  | 30 Spet 15 | 2017-03-30 | 2017-03-30 | 0
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NORTH DAKOTA | UNITED STATES | DESC1107 | Replace Fuel Pipeline - Minot AFB |  |  |  |  | 2014-08-11 | 2015-08-11 | 2015-08-19 | 0.92
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB |  |  |  |  | 2015-01-19 | 2017-05-23 | 2017-09-08 | 0.13 |  | 2853 Reprogramming
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | 43 |  |  |  | 2015-08-10 | 2016-10-23 | 2016-12-08 | 0 |  | 2853 Reprogramming
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1561 | Replace Refueler Parking, Altus AFB |  |  |  |  | 2014-07-11 | 2015-09-17 | 2015-08-07 | 0.49 | 2015-09-17
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | TENNESSEE | UNITED STATES | DESC1557 | Replace Ground Vehicle Fueling Facility - Arnold AFB |  |  |  |  | 2015-06-01 | 2016-10-05 | 2017-01-03 | 0
2015-08-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC0909 | Replace Fuel Pier - Craney Island |  | 3114000 | FY14 Tinker / FY13 Grissom |  | 2012-11-26 | 2014-06-03 | 2015-05-30 | 0.99 | 2015-09-04 | wo# 799865
2015-08-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC1515 | Replace and Alter Fuel Distribution Facilites, Craney Island DFSP |  |  |  |  | 2015-09-30 | 2017-06-26 | 2017-06-26 | 0 |  | wo# 1302502
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island |  |  |  |  | 2014-11-30 | 2016-04-22 | 2016-04-22 | 0.25 |  | wo#1140322
2015-08-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WEST VIRGINIA | UNITED STATES | DESC12S1 | Replace Hydrant Fuel System - Camp Dawson |  |  |  |  | 2012-07-03 |  | 2015-09-22 | 1 | 2015-09-22
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC1203 | Replace Fuel Pier - GTMO |  |  |  |  | 2013-10-28 | 2015-10-28 | 2015-09-28 | 0.51 | 2015-09-28 | wo# 1124257
2015-08-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC13S3 | Replace Truck Loading Facility - GTMO |  |  |  |  | 2013-10-28 | 2015-10-28 | 2015-10-28 | 0.38 | 2015-09-28 | wo# 1303226
2015-08-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC0503 | Hydrant Fuel System - Misawa AB |  | 2601000 | FY14 Tinker |  | 2013-02-01 | 2015-02-01 | 2015-05-13 | 1 | 2015-03-06
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC1401 | Construct Type III Hydrant Fueling system - Iwakuni MCAS |  |  |  |  | 2015-04-22 | 2018-10-20 | 2018-10-20 | 0
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC1503 | Replace Diesel Fuel Pumps - Yokosuka |  |  |  |  | 2015-05-15 | 2016-11-05 | 2016-07-19 | 0.01
2015-08-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC15S1 | Replace Ground Vehicle Fueling Facility - Atsugi |  |  |  |  | 2014-09-12 | 2015-07-24 | 2015-05-15 | 1 | 2015-07-09
2015-08-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | KOREA, SOUTH | DESC0907 | Hydrant Fuel System - Osan AB |  | 2151000 | FY12 New Cumberland General Purpose Warehous |  | 2010-08-27 | 2012-12-16 | 2015-04-30 | 0.99 | 2015-04-20
2015-08-31 | 2012 | DLA Defense Supply Center Philadelphia | Major Military Construction | PENNSYLVANIA | UNITED STATES | DSCP1201 | Upgrade HVAC System - Philadelphia |  |  |  |  | 2012-06-14 | 2013-07-17 | 2014-06-06 | 0.99 | 2014-04-29 | wo# 971006
2015-08-31 | 2014 | DLA Defense Supply Center Richmond | Major Military Construction | VIRGINIA | UNITED STATES | DSCR1401 | Operations Center Phase 1 |  |  |  |  | 2015-07-09 | 2018-07-08 | 2018-07-08 | 0
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM 856 07 | New Elementary School |  |  |  |  | 2012-08-01 | 2013-12-14 | 2014-07-09 | 0.99 | 2014-08-01
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00023 | Replace McBride Elementary School |  |  |  |  | 2013-12-11 | 2015-12-11 | 2016-03-23 | 0.53
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00023 | Replace McBride Elementary School | 28 |  |  |  | 2013-12-11 | 2015-12-11 | 2016-03-23 | 0.53
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00024 | Faith Middle School Addition |  |  |  |  | 2014-10-28 | 2016-01-21 | 2016-04-20 | 0.25
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00038 | Diamond Elementary School Replacement |  |  |  |  | 2014-10-15 | 2016-09-14 | 2017-01-07 | 0.15
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00050 | White Elementary School Replacement |  |  |  |  | 2014-12-16 | 2016-10-31 | 2017-01-29 | 0.13
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00028 | Replace Barkley Elementary School |  | 800000 | PA00033 | 2405 | 2014-03-27 | 2015-12-17 | 2016-05-16 | 0.51
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00026 | Replace Kingsolver/Pierce School |  |  |  |  | 2014-03-11 | 2015-11-11 | 2016-06-01 | 0.33
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00040 | Replace Marshall Elementary School |  |  |  |  | 2014-08-06 | 2016-03-28 | 2016-05-27 | 0.45
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00034 | Replace Fort Campbell High School |  |  |  |  | 2015-01-27 | 2017-02-25 | 2017-08-01 | 0.09
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction | MASSACHUSETTS | UNITED STATES | AM00027 | Replace Hanscom Middle School |  |  |  |  | 2014-02-11 | 2016-06-30 | 2016-08-19 | 0.55
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction | NEW YORK | UNITED STATES | AM2455205 | Construct Addition and Renovate West Point MS |  |  |  |  | 2011-11-28 | 2014-09-28 | 2014-03-17 | 1 | 2014-03-17 | Remove at end of FY15
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM8193 01 | Replace Elementary School (Antilles ES) |  |  |  |  | 2012-07-18 | 2014-04-19 | 2015-11-30 | 0.83
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM100801 | Replace Elementary School (Murray ES) |  |  |  |  | 2012-09-12 | 2014-04-03 | 2014-07-15 | 1 | 2014-08-25 | Remove at end of FY15
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AMD02051 | Replace Elementary School ( McNair ES) |  | 2056000 | AM00025, PA00033 | 65, 2405 | 2012-09-12 | 2014-04-03 | 2014-07-15 | 1 | 2014-08-25 | $1,443 supported AM0025 and $613 supported PA00033. Remove end of FY15
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00025 | Replace Delalio Elementary School |  |  |  |  | 2014-02-24 | 2016-06-01 | 2017-05-20 | 0.43 |  | The occupancy date 1 Jun 16 is for the BOD of the school. This is the completion of Phase 1 of the project. The school can be occupied at this time. The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00031 | Pope Holbrook Elementary School |  |  |  |  | 2015-02-11 | 2017-02-10 | 2017-05-11 | 0.06
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction | SOUTH CAROLINA | UNITED STATES | AM00037 | Replace Bolden-Galer Elementary School |  |  |  |  | 2015-08-18 | 2018-06-28 | 2018-06-28 | 0 |  | Project will be re-awarded to second highest bidder following original contractor being terminated for cause.
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction | VIRGINIA | UNITED STATES | AM2455206 | Replace/Consolidate Elementary Schools |  |  |  |  | 2012-09-29 | 2014-09-30 | 2015-06-01 | 1 | 2015-04-13 | Remove at end of FY15
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | BELGIUM | EUR 8318 09 | Replace School (SHAPE ES) |  |  |  |  | 2012-01-18 | 2014-04-17 | 2014-07-04 | 0.99 | 2014-07-04
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | BELGIUM | EUR 8318 09 | Replace School (SHAPE ES) | 11 |  |  |  | 2012-07-05 | 2015-07-23 | 2013-01-04 | 0.95 | 2012-12-05
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) |  |  |  |  | 2012-01-18 | 2014-04-17 | 2014-07-04 | 0.99 | 2014-07-04
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) | 17 |  |  |  | 2012-07-05 | 2015-07-23 | 2013-01-04 | 0.95 | 2012-12-05
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) | 18 |  |  |  | 2012-08-01 | 2015-01-13 | 2015-02-12 | 0.98 | 2015-02-12
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  |  |  |  | 2015-06-03 | 2018-03-01 | 2018-06-04 | 0.02
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 3 |  |  |  | 2015-06-03 | 2018-03-01 | 2018-06-04 | 0.02
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 4 |  |  |  | 2015-06-03 | 2018-03-01 | 2018-06-04 | 0.02
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) |  |  |  |  | 2011-05-09 | 2013-01-19 | 2013-09-25 | 1 | 2013-09-13 | Remove at end of FY15
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) |  | 1475000 | PA00033 | 2405 | 2013-07-29 | 2015-04-30 | 2015-08-25 | 0.95 | 2015-08-25
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) | 8 |  | PA00033 | 2405 | 2013-07-29 | 2015-04-30 | 2015-08-25 | 0.95 | 2015-08-25
2015-09-01 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) | 9 |  | PA00033 | 2405 | 2013-07-29 | 2015-04-30 | 2015-08-25 | 0.95 | 2015-08-25
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School (Boblingen HS) |  | 3999000 | PA00033 | 2405 | 2013-07-29 | 2015-04-30 | 2015-08-25 | 0.99 | 2015-08-25
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School (Boblingen HS) | 13 |  | PA00033 | 2405 | 2013-07-29 | 2015-04-30 | 2015-08-25 | 0.99 | 2015-08-25
2015-09-01 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School (Boblingen HS) | 14 |  | PA00033 | 2405 | 2013-07-29 | 2015-04-30 | 2015-08-25 | 0.99 | 2015-08-25
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00053 | Replace Elementary/Middle School (Ansbach EMS) |  |  |  |  | 2013-10-28 | 2015-03-10 | 2015-08-28 | 0.85
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00053 | Replace Elementary/Middle School (Ansbach EMS) | 25 |  |  |  | 2013-10-28 | 2015-03-10 | 2015-08-28 | 0.85
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School |  |  |  |  | 2015-04-30 | 2017-06-03 | 2017-09-07 | 0.18
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School | 33 |  |  |  | 2015-04-30 | 2017-06-03 | 2017-09-07 | 0.18
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School | 34 |  |  |  | 2015-04-30 | 2017-06-03 | 2017-09-07 | 0.18
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School | 35 |  |  |  | 2015-04-30 | 2017-06-03 | 2017-09-07 | 0.18
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00062 | Netzaberg Middle School Addition |  |  |  |  | 2014-06-05 | 2015-09-26 | 2015-11-10 | 0.72
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00062 | Netzaberg Middle School Addition | 42 |  |  |  | 2014-06-05 | 2015-09-26 | 2015-11-10 | 0.72
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB |  | 634000 | PA00033 | 2405 | 2013-03-26 | 2015-07-25 | 2015-10-18 | 1 | 2015-05-01 | Remove at end of FY15
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  |  |  |  | 2014-07-07 | 2016-10-24 | 2017-01-01 | 0.14
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 38 |  |  |  | 2014-07-07 | 2016-10-24 | 2017-01-01 | 0.14
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 39 |  |  |  | 2014-07-07 | 2016-10-24 | 2017-01-01 | 0.14
2015-09-01 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 40 |  |  |  | 2014-07-07 | 2016-10-24 | 2017-01-01 | 0.14
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00030 | Replace Zukeran Elementary School |  |  |  |  | 2014-10-23 | 2017-04-01 | 2017-06-20 | 0.05
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00027 | Replace Yokota High School |  |  |  |  | 2015-02-19 | 2018-12-21 | 2019-04-09 | 0
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00035 | Kadena Middle School Addition/Renovation |  |  |  |  | 2015-03-06 | 2016-10-02 | 2016-12-02 | 0
2015-09-01 | 2012 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00020 | Replace Elementary School (Osan ES) |  | 6444000 | PA00033 | 2405 | 2013-09-30 | 2015-12-09 | 2016-03-01 | 0.61
2015-09-01 | 2014 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00018 | Daegu Middle/High School Replacement |  |  |  |  | 2014-09-29 | 2016-10-03 | 2016-12-10 | 0.15
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974378 | SECURITY OPERATIONS COMPLEX |  |  |  |  | 2013-11-14 | 2015-07-31 | 2016-03-09 | 0.14665 | 2015-07-31
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974447A | AIRCRAFT MAINTENANCE HANGAR (JSF) |  |  |  |  | 2011-06-23 | 2012-10-08 | 2013-10-15 | 0.98584 | 2013-12-05
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) |  |  |  |  | 2011-06-23 | 2012-10-08 | 2013-10-15 | 0.99034 | 2013-12-05
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974533 | SIMULATOR FACILITY (JSF) |  | 1897000 | M67925001 |  | 2011-06-17 | 2012-06-02 | 2013-04-19 | 0.99014 | 2013-04-19
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974535 | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 5983000 | N684691400 |  | 2012-09-20 | 2014-07-07 | 2015-06-27 | 0.98958 | 2015-03-12
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) |  |  |  |  | 2012-04-03 | 2014-05-20 | 2014-12-03 | 0.99532 | 2014-12-17
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974546 | UTILITY UPGRADES (JSF) |  | 2879000 | M67925001 |  | 2011-06-21 | 2012-07-08 | 2013-06-14 | 0.98654 | 2013-06-14
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974566 | COMBAT AIRCRAFT LOADING APRON |  | 2574000 | Design |  | 2013-10-11 | 2014-09-22 | 2015-07-26 | 0.99188 | 2015-03-15
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) |  | 525000 | M67925001 |  | 2011-08-10 | 2012-07-25 | 2012-12-14 | 0.98936 | 2012-12-14
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974575 | AUXILIARY LANDING FIELD (JSF) |  | 11951000 | N42237636, FY 15 Prior Year Rescission, N32414547 |  | 2012-07-09 | 2013-06-25 | 2014-01-31 | 0.97683 | 2014-02-21
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974578 | VAN PAD RELOCATION (JSF) |  |  |  |  | 2011-09-26 | 2012-09-11 | 2012-09-11 | 0.99876 | 2013-01-22
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) |  |  |  |  | 2011-06-21 | 2012-07-08 | 2013-06-14 | 0.98631 | 2013-06-14
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243313 | ENTRY CONTROL POINT (GATE 5) |  |  |  |  | 2014-01-03 | 2015-04-29 | 2016-02-25 | 0.57054 | 2015-04-29
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243400 | MARINE CORPS ENERGY INITIATIVE |  |  |  |  | 2011-06-17 | 2012-06-17 | 2012-07-11 | 0.98146 | 2012-06-15
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811014 | TRUCK COMPANY OPERATIONS COMPLEX |  |  |  |  | 2011-10-06 | 2013-09-21 | 2015-08-15 | 0.96306 | 2015-09-14
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE |  | 760000 | N00246909 |  | 2012-04-06 | 2013-01-21 | 2013-08-05 | 0.89529 | 2013-08-05
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811040 | INTERSECTION BRIDGE AND IMPROVEMENTS |  |  |  |  | 2012-09-07 | 2013-09-27 | 2014-06-24 | 0.99667 | 2014-05-23
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811043 | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | M006811043A |  |  |  | 2010-11-12 | 2012-10-12 | 2015-08-21 | 0.75783 | 2015-09-22
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811044 | CONVEYANCE/WATER TREATMENT |  |  |  |  | 2012-10-13 | 2016-01-13 | 2016-12-02 | 0.45404 | 2016-12-06
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811045 | NEW POTABLE WATER CONVEYANCE |  | 16682000 | N684691400 |  | 2012-10-12 | 2016-03-31 | 2016-03-31 | 0.52692 | 2016-10-31
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811109 | BACHELOR ENLISTED QUARTERS, LAS FLORES |  | 1433000 | M670011349 |  | 2011-10-13 | 2013-10-13 | 2014-10-17 | 0.99665 | 2014-06-05
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811113 | BACHELOR ENLISTED QUARTERS, 24 AREA |  | 1752000 | M670011349 |  | 2011-10-13 | 2013-10-13 | 2014-10-17 | 0.99768 | 2014-06-05
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811176 | SAN JACINTO ROAD EXTENSION |  |  |  |  | 2014-10-08 | 2016-04-21 | 2016-04-21 | 0.12034 | 2016-04-21
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811200 | MARINE CORPS ENERGY INITIATIVE |  |  |  |  | 2011-08-09 | 2012-09-27 | 2012-12-31 | 0.9751 | 2012-12-06
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681310 | SMALL ARMS MAGAZINE, EDSON RANGE |  |  |  |  | 2011-06-21 | 2012-07-06 | 2015-01-21 | 0.98096 | 2015-01-29
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681532 | ARMORY, 1ST MARINE DIVISION |  |  |  |  | 2012-09-14 | 2013-12-24 | 2014-12-23 | 0.99813 | 2014-04-23
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204925 | DIP TANK CLEANING FACILITY |  |  |  |  | 2012-04-04 | 2013-09-27 | 2014-04-09 | 0.91689 | 2014-09-18
2015-08-31 | 2015 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204939 | ENGINE DYNAMOMETER FACILITY |  |  |  |  | 2015-04-14 |  |  | 0.069235
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399105 | TRACKED VEHICLE MAINTENANCE COVER |  |  |  |  | 2012-06-29 | 2014-03-22 | 2014-03-22 | 0.71213 | 2013-04-10
2015-08-31 | 2015 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399159 | CAMP WILSON INFRASTRUCTURE UPGRADES |  |  |  |  | 2015-04-29 | 2017-05-01 | 2017-05-01 | 0.0022846 | 2017-05-01
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE |  |  |  |  | 2011-06-17 | 2012-10-12 | 2013-06-17 | 0.99916 | 2014-04-24
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA |  |  |  |  | 2012-08-27 | 2014-09-02 | 2016-07-21 | 0.46751 | 2016-05-03
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399212 | CHILD DEVELOPMENT CENTER |  |  |  |  | 2012-06-19 | 2013-12-12 | 2015-09-01 | 0.91433 | 2015-05-19
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399541 | MULTI-PURPOSE BUILDING ADDITION |  |  |  |  | 2012-10-11 | 2014-04-20 | 2015-04-14 | 0.93018 | 2015-09-23
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399991 | LAND EXPANSION |  |  |  |  | 2015-01-29 |  |  | 0.37 | 2016-01-15
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604109 | CNAT/FRS AVIATION TRAINING AND BEQ |  | 15930000 | M67925001, N61151162, Sequestration Reprogramming |  | 2011-09-26 | 2014-01-08 | 2014-06-23 | 0.99312 | 2014-06-23
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604111 | MALS-39 MAINTENANCE HANGAR EXPANSION |  | 12329000 | M67925001 |  | 2011-07-06 | 2013-03-13 | 2013-10-29 | 0.86813 | 2013-10-29
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604113 | MV-22 AVIATION SIMULATOR BUILDING |  |  |  |  | 2013-06-27 | 2014-09-21 | 2014-09-21 | 0.99742 | 2014-09-18
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604114 | MV-22 DOUBLE HANGAR REPLACEMENT |  | 6761000 | N684691400 |  | 2012-08-03 | 2015-08-10 | 2015-12-29 | 0.91423 | 2015-12-02
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604116 | MV-22 AVIATION PAVEMENT |  | 856000 | N684691400 |  | 2012-07-26 | 2014-01-03 | 2015-03-27 | 0.76374 | 2015-09-04
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604117 | MV-22 AVIATION FUEL STORAGE |  |  |  |  | 2013-11-21 | 2013-10-07 | 2015-10-07 | 0.52371
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865152 | PARKING APRON/TAXIWAY EXPANSION |  | 28591000 | N50092499, N60191527, Design, N47608561 |  | 2011-10-04 | 2014-09-19 | 2014-09-19 | 0.99885 | 2015-07-01
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865181 | HANGAR 5 RENOVATIONS & ADDITION |  | 9166000 | Design |  | 2013-09-27 | 2015-09-28 | 2015-11-13 | 0.56282 | 2015-09-28
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865185 | HANGAR 4 ADDITION |  | 4000000 | M00681159, Design |  | 2011-10-04 | 2014-09-19 | 2014-09-19 | 0.99277 | 2015-07-01
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865192 | GTF-HANGAR MODIFICATION (HMT-302) |  | 33515000 | N50092499, Design, FY 15 Prior Year Rescission |  | 2011-10-04 | 2014-09-19 | 2014-09-19 | 0.98576 | 2015-07-01
2015-08-31 | 2011 | Marine Corps Active | Military Family Housing Improvement | DISTRICT OF COLUMBIA | UNITED STATES | M670291101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 |  |  |  |  | 2011-01-28 | 2011-05-13 | 2011-08-31 | 1 | 2011-05-12
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695005 | PAINT AND BLAST FACILITY |  |  |  |  | 2011-09-30 | 2013-05-16 | 2014-01-24 | 1 | 2014-03-10
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695012 | CONTAINER STAGING AND LOADING LOT |  |  |  |  | 2011-06-17 | 2013-12-05 | 2013-12-05 | 0.98512 | 2013-12-05
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695017 | HARDSTAND EXTENSION |  |  |  |  | 2011-06-17 | 2013-12-05 | 2013-12-05 | 0.99108 | 2013-12-05
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695022 | CONSOLIDATED WAREHOUSE FACILITY |  |  |  |  | 2011-06-17 | 2012-07-27 | 2013-12-20 | 1 | 2013-12-20
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695023 | WASHRACK EXPANSION |  |  |  |  | 2011-06-15 | 2012-11-19 | 2012-11-19 | 1 | 2013-06-10
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695024 | CONTAINER STORAGE LOT |  |  |  |  | 2011-06-17 | 2013-12-05 | 2013-12-05 | 0.99734 | 2013-12-05
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  |  |  |  | 2014-09-24 | 2016-01-25 | 2016-01-25 | 0.055818 | 2016-01-25
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004954 | CERS DISPATCH FACILITY |  |  |  |  | 2014-06-16 | 2015-06-02 | 2015-06-02 | 0.89272 | 2015-06-02
2015-08-31 | 2014 | Marine Corps Active | Military Family Housing Improvement | GUAM | GUAM | N61755H106 | WHOLE HOUSE REVITALIZATION PHASE II AT LOCKWOOD TERRACE |  |  |  |  | 2015-05-14 | 2017-08-13 | 2017-08-13 | 0.050684 | 2017-08-13
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557101 | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 | N41557101A |  |  |  | 2013-08-21 | 2015-07-12 | 2015-12-15 | 0.77373 | 2015-12-15
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  |  |  |  | 2014-05-21 | 2016-12-03 | 2016-12-03 | 0.156 | 2016-12-21
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557J200 | NORTH RAMP UTILITIES II |  |  |  |  | 2014-10-31 | 2016-09-02 | 2016-09-02 | 0.03 | 2016-10-03
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N61755204 | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | N61755204A | 19244000 | FY 15 Prior Year Rescission |  | 2012-12-12 | 2014-06-19 | 2014-09-30 | 0.96984 | 2014-09-29
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318006 | PHYSICAL FITNESS CENTER, CAMP SMITH |  |  |  |  | 2011-06-30 | 2013-03-07 | 2014-04-04 | 0.99919 | 2014-04-03
2015-08-31 | 2015 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318778 | ARMORY ADDITION AND RENOVATION |  |  |  |  | 2015-03-27 | 2017-08-09 | 2017-08-09 | 0 | 2017-08-09
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318816 | WATERFRONT OPERATIONS FACILITY |  |  |  |  | 2011-07-14 | 2013-11-16 | 2014-04-14 | 0.84424 | 2015-12-31
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318822 | MCAS OPERATIONS COMPLEX |  |  |  |  | 2012-05-02 | 2014-03-17 | 2014-12-29 | 0.9198 | 2014-12-29
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318852 | 3RD RADIO BATTALION COMPLEX |  |  |  |  | 2014-09-19 | 2016-10-04 | 2016-10-04 | 0.028884 | 2016-10-04
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318858 | BACHELOR ENLISTED QUARTERS |  | 17925000 | N60191527, N60191582, Sequestration Reprogramming |  | 2011-09-14 | 2014-08-21 | 2015-10-01 | 0.97073 | 2015-09-30
2015-08-31 | 2014 | Marine Corps Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | M0031886167 | TEMPORARY MEDICAL FACILITY SITE PREPARATION |  |  |  |  | 2015-01-05 | 2015-07-07 | 2015-08-14 | 0.8944 | 2015-10-16
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318864 | AIRCRAFT MAINTENANCE EXPANSION |  |  |  |  | 2014-04-30 | 2015-09-09 | 2015-09-09 | 0.81214 | 2015-09-09
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  |  |  |  | 2014-10-14 | 2016-12-18 | 2016-12-18 | 0.062893 | 2016-12-18
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318904 | MV-22 HANGAR AND INFRASTRUCTURE |  |  |  |  | 2013-12-31 | 2015-09-10 | 2015-09-29 | 0.69707 | 2016-03-29
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318905 | AIRCRAFT STAGING AREA |  |  |  |  | 2013-12-31 | 2015-09-10 | 2015-09-29 | 0.64536 | 2016-03-29
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  |  |  |  | 2015-04-28 | 2017-01-03 | 2017-01-03 | 0.0092053 | 2017-04-03
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318908 | MV-22 HANGAR |  |  |  |  | 2015-04-28 | 2017-01-03 | 2017-01-03 | 0.0010542 | 2017-04-03
2015-08-31 | 2012 | Marine Corps Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  |  |  |  | 2012-01-18 |  |  | 1
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146136 | BACHELOR ENLISTED QUARTERS |  |  |  |  | 2011-06-16 | 2013-07-07 | 2014-12-14 | 0.95673 | 2015-07-22
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146148 | MISSILE MAGAZINE |  |  |  |  | 2011-06-16 | 2012-07-10 | 2013-11-04 | 0.98811 | 2014-01-23
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND |  |  |  |  | 2013-09-19 | 2016-01-18 | 2016-04-30 | 0.63461 | 2016-04-30
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146164 | MARINER'S BAY LAND ACQUISITION BOGUE |  |  |  |  | 2011-07-15 |  |  | 0.93156
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146176 | STATION INFRASTRUCTURE UPGRADES |  |  |  |  | 2011-06-15 | 2012-11-25 | 2013-10-10 | 1 | 2013-10-10
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146601 | ARMORY |  |  |  |  | 2013-09-19 | 2015-04-08 | 2015-09-06 | 0.9792 | 2015-07-06
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY |  |  |  |  | 2012-03-29 | 2013-08-14 | 2014-11-24 | 0.96638 | 2014-04-29
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001003 | STAFF NCO ACADEMY FACILITIES |  |  |  |  | 2013-09-19 | 2015-09-01 | 2015-11-08 | 0.41759 | 2016-02-08
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC |  |  |  |  | 2011-06-16 | 2012-12-01 | 2015-09-15 | 0.97591 | 2015-09-15
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001030 | SQUAD BATTLE COURSE |  |  |  |  | 2012-07-05 | 2014-05-17 | 2015-01-24 | 0.97296 | 2015-01-24
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011034 | 2ND INTEL BN OPERATIONS COMPLEX |  | 1292000 | M67925001 |  | 2011-07-13 | 2014-02-28 | 2014-12-15 | 0.99437 | 2015-10-16
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO |  |  |  |  | 2011-07-13 | 2014-02-28 | 2014-12-15 | 0.94174 | 2015-10-16
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP |  |  |  |  | 2011-07-11 | 2012-08-20 | 2013-07-31 | 0.92403 | 2013-05-13
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  |  |  |  | 2011-07-13 | 2013-07-13 | 2015-04-11 | 0.96638 | 2015-07-31
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 689000 | M67925001 |  | 2011-09-14 | 2013-10-08 | 2014-06-24 | 1.0004 | 2015-08-30
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER |  |  |  |  | 2012-05-14 | 2014-07-24 | 2015-03-12 | 0.98571 | 2015-09-22
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 1421000 | M67925001 |  | 2011-09-14 | 2013-10-08 | 2014-06-24 | 0.99459 | 2015-08-30
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011256 | MESS HALL ADDITION, COURTHOUSE BAY |  |  |  |  | 2011-06-16 | 2012-11-25 | 2012-11-25 | 0.9848 | 2012-11-25
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011264 | UTILITY EXPANSION, HADNOT POINT |  |  |  |  | 2011-10-10 | 2013-10-22 | 2016-09-26 | 0.96133 | 2016-09-30
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011265 | UTILITY EXPANSION, FRENCH CREEK |  |  |  |  | 2011-10-10 | 2013-10-22 | 2016-09-26 | 0.88088 | 2016-09-30
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011267 | MESS HALL, FRENCH CREEK |  |  |  |  | 2011-06-16 | 2013-02-06 | 2014-03-07 | 0.80627 | 2014-03-07
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE |  |  |  |  | 2011-09-13 | 2013-09-07 | 2015-07-31 | 0.9948 | 2015-07-31
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK |  |  |  |  | 2011-06-16 | 2013-08-30 | 2015-06-16 | 0.99432 | 2015-06-01
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON |  |  |  |  | 2011-06-16 | 2013-08-13 | 2014-08-29 | 0.99626 | 2014-08-29
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  |  |  |  | 2011-07-13 | 2013-07-13 | 2015-04-11 | 0.99907 | 2015-07-31
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011323 | ARMORY II MEF, WALLACE CREEK |  | 4148000 | M00681159 |  | 2011-12-20 | 2013-07-13 | 2015-04-11 | 0.99648 | 2015-07-31
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011349 | SPECIAL OPERATIONS TRAINING COMPLEX |  |  |  |  | 2015-09-14 | 2017-03-21 | 2017-03-21 | 0 | 2017-03-21
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011353 | LANDFILL, PHASE 4 |  |  |  |  | 2014-09-08 | 2016-03-01 | 2016-03-01 | 0.60409 | 2016-03-01
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK |  |  |  |  | 2012-07-13 | 2014-07-29 | 2015-05-05 | 0.97471 | 2015-11-15
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011383 | BASE ENTRY POINT AND ROAD |  |  |  |  | 2012-04-17 | 2015-04-18 | 2016-09-14 | 0.89057 | 2016-09-14
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011384 | BASE ACCESS AND ROAD, PHASE 3 |  |  |  |  | 2012-04-17 | 2015-04-18 | 2016-09-14 | 0.6606 | 2016-09-14
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011400 | MARINE CORPS ENERGY INITIATIVE |  |  |  |  | 2011-06-14 | 2012-08-04 | 2014-01-16 | 0.99896 | 2013-06-21
2015-08-31 | 2012 | Marine Corps Active | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | M670011425 | OVERHEAD RANGE BAFFLE SYSTEM |  |  |  |  | 2013-03-06 | 2014-04-17 | 2014-11-29 | 0.96981 | 2014-11-29
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011445 | STEAM DECENTRALIZATION (CAMP JOHNSON) |  |  |  |  | 2015-02-06 | 2017-02-04 | 2017-02-04 | 0.40804 | 2017-02-04
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011447 | STEAM DECENTRALIZATION - HADNOT POINT |  |  |  |  | 2015-02-06 |  |  | 0.062717
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011448 | STEAM DECENTRALIZATION (BEQ NODES) |  |  |  |  | 2015-02-06 |  |  | 0.062198
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001674 | CORROSION CONTROL HANGAR |  |  |  |  | 2015-09-02 | 2017-03-11 | 2017-03-11 | 0 | 2017-03-11
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY |  |  |  |  | 2014-06-13 | 2015-12-20 | 2015-12-20 | 0.23404 | 2016-03-31
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001683 | HANGAR |  |  |  |  | 2011-06-17 | 2013-11-29 | 2015-06-15 | 0.95824 | 2015-06-15
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001687 | MV-22 MAINTENANCE HANGAR (HMLA) |  |  |  |  | 2011-06-17 | 2013-11-29 | 2015-06-15 | 0.99078 | 2015-06-15
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001705 | AIRCRAFT MAINTENANCE HANGAR AND APRON |  | 3690000 | N32414547 |  | 2012-06-12 | 2014-07-07 | 2015-08-11 | 0.99393 | 2015-08-11
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001710 | ORDNANCE LOADING AREA ADDITION |  | 326000 | N32414547 |  | 2012-06-12 | 2014-07-07 | 2015-08-11 | 0.9845 | 2015-08-11
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001711 | PERSONNEL ADMINISTRATION CENTER |  |  |  |  | 2013-09-20 | 2015-07-06 | 2015-12-24 | 0.79877 | 2015-12-24
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001726 | REGIONAL COMMUNICATION STATION |  |  |  |  | 2014-06-13 | 2015-12-20 | 2015-12-20 | 0.27137 | 2016-03-31
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M00263382 | FRONT GATE AT/FP IMPROVMENTS |  |  |  |  | 2013-10-30 | 2015-04-12 | 2015-10-11 | 0.81899 | 2015-10-11
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169420 | PHYSICAL FITNESS CENTER, BEAUFORT |  |  |  |  | 2011-09-21 | 2013-06-08 | 2013-07-16 | 0.99832 | 2013-05-24
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169427 | GROUND SUPPORT EQUIPMENT SHOP |  |  |  |  | 2013-08-22 | 2014-08-14 | 2015-01-20 | 1.0015 | 2015-09-04
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169442 | VERTICAL LANDING PADS FOR F-35B |  | 2444000 | N32414547 |  | 2012-04-13 | 2013-08-07 | 2013-09-27 | 0.99702 | 2013-10-21
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169444 | TRAINING AND SIMULATOR FACILITY |  |  |  |  | 2011-06-20 | 2014-03-11 | 2014-06-09 | 0.99875 | 2014-06-17
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169454 | F-35B AIRCRAFT HANGAR FOR FRS-2 |  |  |  |  | 2011-06-20 | 2014-03-11 | 2014-06-09 | 0.99818 | 2014-06-17
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169456 | SIMULATED LHD FLIGHT DECK |  |  |  |  | 2013-07-10 | 2014-07-11 | 2015-07-31 | 0.96537 | 2015-11-27
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  |  |  |  | 2014-08-29 | 2016-09-08 | 2016-10-03 | 0.23383 | 2016-09-08
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169472 | AIRFIELD SECURITY UPGRADES |  |  |  |  | 2013-07-15 | 2014-03-28 | 2015-10-24 | 0.85973 | 2014-10-28
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M002641406 | ATC TX/RX RELOCATION |  |  |  |  | 2015-05-15 | 2016-11-21 | 2016-11-21 | 0.011152 | 2016-11-21
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264541 | ADDITION, MCU RESEARCH CENTER |  | 3531000 | Sequestration Reprogramming |  | 2012-10-09 | 2014-08-16 | 2015-02-17 | 0.98308 | 2015-08-31
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR |  |  |  |  | 2012-09-25 | 2014-03-28 | 2014-12-09 | 0.98693 | 2015-12-31
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  |  |  |  | 2013-10-07 | 2016-11-06 | 2017-10-18 | 0.13421 | 2017-10-18
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 |  | 8039000 | Sequestration Reprogramming |  | 2012-12-14 | 2016-11-06 | 2017-10-18 | 0.62988 | 2017-10-18
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 |  |  |  |  | 2012-12-14 | 2016-11-06 | 2017-10-18 | 0.79494 | 2017-10-18
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION |  |  |  |  | 2012-08-10 | 2013-09-05 | 2014-12-30 | 0.89763 | 2015-06-12
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL |  |  |  |  | 2011-10-14 | 2013-08-09 | 2014-04-30 | 0.99601 | 2013-09-26
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264611 | BACHELOR ENLISTED QUARTERS |  |  |  |  | 2012-10-13 | 2014-10-16 | 2015-07-22 | 0.9861 | 2015-05-21
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264612 | ENLISTED DINING FACILITY |  |  |  |  | 2012-10-13 | 2014-10-16 | 2015-07-22 | 0.97442 | 2015-05-21
2015-08-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264615 | SNCO ACADEMIC FACILITY ADDITION |  |  |  |  | 2011-07-04 | 2012-12-21 | 2013-05-31 | 0.95594 | 2013-07-22
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264621 | EMBASSY SECURITY GROUP FACILITIES |  |  |  |  | 2013-03-14 | 2015-03-15 | 2015-09-08 | 0.81022 | 2015-08-15
2015-08-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264632 | ACADEMIC INSTRUCTION FACILITY |  | 2502000 | N47608561 |  | 2012-10-09 | 2014-08-16 | 2015-02-17 | 0.95182 | 2015-08-31
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264644 | WEAPONS TRAINING BATALLION MESS HALL |  |  |  |  | 2013-09-18 | 2015-04-22 | 2016-04-01 | 0.69908 | 2015-10-31
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212984 | REGIMENTAL HEADQUARTERS |  |  |  |  | 2013-09-13 | 2015-06-26 | 2015-11-09 | 0.68472 | 2015-12-21
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212985 | BACHELOR ENLISTED QUARTERS |  |  |  |  | 2013-09-13 | 2015-06-26 | 2015-11-09 | 0.67407 | 2015-12-21
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212986 | MOTOR TRANSPORTATION FACILITY |  |  |  |  | 2013-09-13 | 2015-03-23 | 2015-04-19 | 0.95804 | 2015-08-27
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212987 | SUPPLY WAREHOUSE FACILITY |  |  |  |  | 2013-09-13 | 2015-03-23 | 2015-04-19 | 0.9489 | 2015-08-27
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212989 | ARMORY |  |  |  |  | 2013-09-13 | 2015-03-23 | 2015-04-19 | 0.95793 | 2015-08-27
2015-08-31 | 2011 | Marine Corps Active | Military Family Housing |  | GUANTANAMO BAY NAVAL BASE | N605141403 | REPLACE BASE HOUSING |  |  |  |  | 2011-10-14 | 2014-03-16 | 2014-02-28 | 0.23715 | 2014-02-14
2015-08-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 |  |  |  |  | 2012-08-13 | 2013-11-23 | 2013-12-14 | 1 | 2013-12-13
2015-08-31 | 2013 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 |  |  |  |  | 2014-06-22 | 2015-10-13 | 2015-10-13 | 0.39013 | 2015-10-13
2015-08-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626131001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 |  |  |  |  | 2012-08-14 | 2014-12-20 | 2015-02-02 | 0.99723 | 2015-02-20
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613995 | MAINTENANCE HANGAR IMPROVEMENTS |  |  |  |  | 2014-06-06 | 2015-06-14 | 2015-06-14 | 0.55319 | 2015-06-14
2015-08-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH |  |  |  |  | 2014-08-08 | 2015-09-24 | 2015-09-24 | 0.63627 | 2015-09-24
2015-08-31 | 2014 | Marine Corps Active | Major Military Construction |  | JAPAN | M67400201 | AIRFIELD SECURITY UPGRADES |  |  |  |  | 2014-05-02 | 2015-10-26 | 2015-10-26 | 0.33151 | 2015-10-26
2015-08-31 | 2013 | Marine Corps Active | Unspecified Minor Military Construction |  | JAPAN | M67400305 | DEMOLISH 45 HOUSING UNITS, KISHABA HOUSING |  |  |  |  | 2014-10-09 | 2015-06-29 | 2015-06-29 | 0.84442 | 2015-06-29
2015-08-31 | 2011 | Marine Corps Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | M67399092 | TANK VEHICLE MAINTENANCE FACILITY |  |  |  |  | 2011-10-06 | 2012-09-21 | 2013-03-28 | 0.99899 | 2013-03-11
2015-08-31 | 2012 | Marine Corps Reserve | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | N00206501 | MILITARY WORKING DOG FACILITY |  |  |  |  | 2013-08-29 | 2014-05-22 | 2014-06-20 | 1 | 2014-06-20
2015-08-31 | 2014 | Marine Corps Reserve | Major Military Construction | MISSOURI | UNITED STATES | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  |  |  |  | 2014-09-05 | 2016-02-23 | 2016-02-23 | 0.10179 | 2016-02-23
2015-08-31 | 2013 | Marine Corps Reserve | Major Military Construction | NEW YORK | UNITED STATES | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY |  |  |  |  | 2013-09-19 | 2014-12-04 | 2015-10-26 | 0.30773 | 2015-11-04
2015-08-31 | 2012 | Marine Corps Reserve | Major Military Construction | TENNESSEE | UNITED STATES | M68479030 | RESERVE CENTER TRAINING CENTER - MEMPHIS |  |  |  |  | 2013-04-19 | 2015-02-17 | 2015-02-17 | 0.99001 | 2015-04-21
2015-08-31 | 2011 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | M68479060 | MARINE CORPS RESERVE CENTER |  |  |  |  | 2011-10-11 | 2013-02-08 | 2015-04-15 | 0.99785 | 2014-04-15
2015-08-31 | 2015 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | N00620234 | C-40 RESERVE MAINTENANCE HANGAR |  |  |  |  | 2015-08-12 | 2016-12-15 | 2016-12-15 | 0.00013147 | 2016-09-03
2015-08-31 | 2011 | Marine Corps Reserve | Military Family Housing Improvement |  | JAPAN | M626130501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 |  |  |  |  | 2011-10-06 | 2013-01-14 | 2013-02-28 | 1 | 2013-02-28
2015-08-31 | 2012 | Missile Defense Agency | Major Military Construction | ALABAMA | UNITED STATES | 633 | Von Braun Complex Phase IV |  |  |  |  | 2012-07-10 | 2014-07-10 | 2014-10-15 | 1 | 2014-06-26 | Awaiting Final 1354
2015-08-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  |  |  |  | 2014-07-07 | 2016-01-06 | 2016-01-06 | 0.85 |  | Awaiting Interim 1354
2015-08-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 22900000 | 646 |  | 2014-05-27 | 2016-05-31 | 2016-05-31 | 0.48 |  | Construction re-mobilized on 23 March 2015; Awaiting Interim 1354
2015-08-31 | 2010 | Missile Defense Agency | Major Military Construction | HAWAII | UNITED STATES | 627 | Aegis Ashore Missile Defense Test Complex |  |  |  |  | 2011-09-08 | 2011-11-18 | 2011-11-18 | 1 | 2011-11-18 | Clearing and Grubbing Only
2015-08-31 | 2010 | Missile Defense Agency | Major Military Construction | HAWAII | UNITED STATES | 627 | Aegis Ashore Missile Defense Test Complex | 4 |  |  |  | 2012-07-04 | 2013-09-12 | 2013-11-07 | 1 | 2013-08-29 | GMAC Construction - awaiting Interim 1354
2015-08-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 655 | Missile Test Vehicle Storage Facility |  |  |  |  | 2014-06-17 | 2014-12-11 | 2014-12-28 | 1 | 2014-12-16 | Awaiting Interim 1354
2015-08-31 | 2013 | Missile Defense Agency | Major Military Construction | NEW YORK | UNITED STATES | 639 | In-Flight Interceptor Data Terminal Complex |  | 1801000 | 630 |  | 2013-08-10 | 2014-11-28 | 2015-09-12 | 0.99 | 2015-02-04 | Awaiting Final 1354
2015-08-31 | 2014 | Missile Defense Agency | Major Military Construction |  | JAPAN | 648 | AN/TPY-2 Radar Site |  |  |  |  | 2014-05-27 | 2015-01-09 | 2015-02-20 | 1 | 2015-02-03 | RPSUID is pending as this is a new Installation.
2015-08-31 | 2013 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  |  |  |  | 2013-07-31 | 2015-08-30 | 2015-11-17 | 0.85 |  | RPSUID is pending as this is a new Installation; awaiting Interim 1354; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2015-08-31 | 2014 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 630 | Aegis Ashore Missile Defense System Complex, Incr #2 | 646 |  |  |  | 2013-07-31 | 2015-08-30 | 2015-11-17 | 0.85 |  | RPSUID is pending as this is a new Installation; awaiting Interim 1354; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2015-09-01 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | MISSOURI | UNITED STATES | NGA021 | Data Ctr West #1 Power & Cooling Upgrade |  | 1975000 |  | 190168 | 2012-08-06 | 2013-08-06 | 2014-01-21 | 0.99 | 2014-01-21 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 30 September 2015
2015-09-01 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | NGA013 | Technology Center Third Floor Fit-out |  | 1975000 | NGA021 | 170447 | 2012-11-02 | 2014-01-02 | 2014-05-30 | 0.99 | 2014-05-30 | Technology Center Third Floor Fit-out - project period of performance extended to 31 May 2015. USACE target closeout date is 31Dec15
2015-09-01 | 2007 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES |  | Infrastructure Increments 1-3; NGA HQ's | [5 empty] | 2013-06-15 | 31-Apr-2015 | 1 | 2011-09-15
2015-09-01 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 65416 | NGA Headquarters, SCIF, All Phases |  |  |  |  | 2007-09-06 | 2011-12-22 | 2015-11-21 | 0.99 | 2011-04-19
2015-08-31 | 2012 | National Security Agency | Major Military Construction | COLORADO | UNITED STATES | 23051 | Mountainview |  |  |  |  | 2012-11-02 | 2015-05-03 | 2015-11-30 | 0.99 | 2015-08-30 | BOD issued on 28 July 2015. Working on construction punch list items-estimated completion 30 Nov 2015.
2015-08-31 | 2012 | National Security Agency | Major Military Construction | COLORADO | UNITED STATES | 23051 | Mountainview | 16 |  |  |  | 2013-10-13 | 2014-02-14 | 2015-09-30 | 1 | 2014-04-30
2015-08-31 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 20489 23994 | MOD II |  |  |  |  | 2012-05-30 | 2014-01-30 | 2015-01-16 | 1 | 2014-03-03
2015-08-31 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 20489 23994 | MOD II (Phase 2) | 13 |  |  |  | 2013-11-26 | 2014-02-28 | 2014-04-28 | 1 | 2014-09-30
2015-08-31 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 20489 23994 | Whitelaw Wedge | 14 |  |  |  | 2012-07-18 | 2014-01-30 | 2014-12-23 | 1 | 2015-08-28
2015-08-31 | 2009 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  |  |  |  | 2010-09-21 | 2013-01-17 | 2014-04-18 | 0.99 | 2013-01-17
2015-08-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 37500000 | Due to a Congressional rescission of funds |  | 2010-09-21 | 2014-04-18 | 2015-10-12 | 0.98 | 2015-10-12
2015-08-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  |  |  |  | 2010-09-09 | 2011-09-26 | 2012-06-29 | 0.99 | 2012-06-29
2015-08-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  |  |  |  | 1915-11-09 | 2014-03-07 | 2015-05-04 | 0.999 | 2014-11-30 | Completing remaining punch list items.
2015-08-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17781 | Tordella Chilled Water Backup Storage |  |  |  |  | 2010-06-30 | 2011-08-20 | 2012-05-30 | 1 | 2012-05-30
2015-08-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17782 | R&E Chilled Water Backup Storage |  |  |  |  | 2011-11-07 | 2013-07-13 | 2015-11-30 | 0.78 | 2014-10-31 | Due to problems with financing issues between the USACE and Walsh, end date is 30 Nov 2015.
2015-08-31 | 2011 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 54500000 | Mountainview, South Campus Electrical Utility Plant | 1530 | 2011-10-04 | 2014-11-30 | 2015-10-31 | 0.991 | 2014-11-30 | Working in minor change orders and waiting for the demolition.
2015-08-31 | 2012 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 24649 | High Performance Computing Center 2 |  |  |  |  | 2013-03-13 | 2015-09-15 | 2015-10-20 | 0.95 | 2015-12-10 | Execution of Modification E/F - BGE Permanent Power Delay resulted in a Construction Completion Date extension of 51 calendar days from 20 Oct 2015 to 10 Dec 2015.
2015-08-31 | 2013 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 26170 | East Campus Building 1 (ECB1) |  |  |  |  | 2013-10-24 | 2015-10-11 | 2016-03-19 | 0.42 | 2017-03-19 | Data from RMS run 18 Aug 2015.
2015-08-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18052 | Power & Cooling Infrastructure Upgrade |  |  |  |  | 2011-03-31 | 2013-02-01 | 2014-05-14 | 1 | 2014-05-14
2015-08-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18053 | Power & Cooling Infrastructure Upgrade |  |  |  |  | 2012-01-31 | 2013-02-01 | 2014-05-31 | 1 | 2014-05-31
2015-08-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18054 | Power & Cooling Infrastructure Upgrade |  |  |  |  | 2012-11-30 | 2013-02-01 | 2014-08-31 | 0.92 | 2014-08-31 | Commissioning of system completed November 26, 2014.
2015-08-31 | 2011 | Navy Active | Major Military Construction | ALABAMA | UNITED STATES | N60508266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD |  |  |  |  | 2012-10-12 | 2014-09-28 | 2015-05-19 | 0.85502 | 2015-06-30
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | N60042116 | D5 MISSILE MOTOR MAGS MODS (NAVOBSSTA FLAGSTAFF AZ) |  |  |  |  | 2014-12-25 |  |  | 0
2015-08-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811046 | NORTH AREA WASTE WATER CONVEYANCE |  |  |  |  | 2014-12-09 | 2016-12-08 | 2016-12-08 | 0.01616 | 2016-12-08
2015-08-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245327 | BERTHING PIER 12 REPL & DREDGING |  | 1813000 | N61151162 |  | 2011-10-13 | 2013-10-22 | 2014-11-30 | 0.78456 | 2013-10-22
2015-08-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245405 | BACHELOR QUARTERS HOMEPORT ASHORE |  | 3179000 | N42237100 |  | 2011-10-14 | 2013-10-23 | 2013-12-03 | 1.0008 | 2013-12-03
2015-08-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245500 | LCS TRAINING FACILITY |  | 10760000 | N42237100 |  | 2013-10-14 | 2015-10-24 | 2016-01-09 | 0.72288 | 2016-01-09
2015-08-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246705 | FITNESS CENTER, NORTH ISLAND |  |  |  |  | 2012-08-21 | 2015-03-16 | 2015-08-26 | 0.99333 | 2015-07-27
2015-08-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246730 | BACHELOR QUARTERS |  |  |  |  | 2015-08-13 | 2015-01-12 | 2015-01-12 | 0.92225 | 2015-01-12
2015-08-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246750 | ROTARY HANGAR |  | 1557000 | N42237100 |  | 2012-02-14 | 2012-04-16 | 2014-03-11 | 1 | 2013-12-10
2015-08-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND |  | 1956000 | Design |  | 2012-07-17 | 2015-03-30 | 2015-10-18 | 0.9651 | 2016-01-05
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY |  |  |  |  | 2013-02-21 | 2014-01-31 | 2014-10-17 | 0.99869 | 2015-01-28
2015-08-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246909 | H-60S SIMULATOR TRAINING FACILITY |  |  |  |  | 2014-03-14 | 2015-03-15 | 2015-05-14 | 0.85142 | 2015-11-30
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246943 | POWER DISTRIBUTION TO OP-3 TO SUPPORT ELMR |  |  |  |  | 2014-09-30 |  |  | 0.39703
2015-08-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND |  |  |  |  | 2014-08-18 | 2016-02-10 | 2016-02-10 | 0.28667 | 2016-02-10
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N47609003 | EOD/TEU RANGE SUPPORT FACILITY |  |  |  |  | 2014-06-27 | 2015-06-26 | 2015-06-26 | 0.83367 | 2015-06-26
2015-08-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N60042260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  |  |  |  | 2011-10-13 |  |  | 1
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61014851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION |  |  |  |  | 2014-01-02 | 2014-10-17 | 2014-12-31 | 0.9993 | 2014-12-31
2015-08-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB |  |  |  |  | 2013-10-14 | 2016-04-17 | 2016-06-16 | 0.88914 | 2016-04-17
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61065240 | STANDARD MISSILE-6 ALL UP ROUND TEST FACILITY |  |  |  |  | 2015-04-30 | 2016-10-21 | 2016-10-21 | 0.024248
2015-08-31 | 2015 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N63042327 | F-35C OPERATIONAL TRAINING FACILITY |  |  |  |  | 2015-07-10 | 2016-10-17 | 2016-10-17 | 0.003822 | 2016-10-17
2015-08-31 | 2015 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N63042328 | F-35C FACILITY ADDITION AND MODIFICATION |  |  |  |  | 2015-06-25 | 2016-07-22 | 2016-07-22 | 0.0070678 | 2016-07-22
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042331 | WATER WELL |  |  |  |  | 2011-10-14 | 2012-10-01 | 2013-05-21 | 0.9969 | 2013-11-22
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 |  |  |  |  | 2012-09-12 | 2013-08-29 | 2013-08-29 | 1 | 2013-08-29
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT |  |  |  |  | 2012-10-12 | 2013-09-26 | 2014-03-05 | 1 | 2014-03-05
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042376 | VFA-94 HANGAR ALTERATIONS |  |  |  |  | 2014-10-11 | 2016-09-27 | 2017-06-04 | 0.11451 | 2016-09-27
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63406563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 |  |  |  |  | 2012-10-12 | 2013-09-27 | 2014-07-01 | 1 | 2014-06-23
2015-08-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232281 | AIRCRAFT ENGINE TEST PADS |  |  |  |  | 2014-06-26 | 2015-07-17 | 2015-07-17 | 0.70593 | 2015-11-30
2015-08-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232559 | E-2D AIRCREW TRAINING FACILITY |  |  |  |  | 2012-07-13 | 2014-06-25 | 2015-03-20 | 0.98155 | 2015-03-20
2015-08-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232593 | BAMS CONSOLIDATED MAINTENANCE HANGAR |  |  |  |  | 2015-01-30 | 2016-09-17 | 2016-09-17 | 0.056968 | 2016-09-30
2015-08-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232599 | UNACCOMPANIED HOUSING CONVERSION (PORT HUENEME) |  |  |  |  | 2014-12-08 | 2016-03-12 | 2016-03-12 | 0.87 | 2016-03-12
2015-08-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232900 | BAMS MAINTENANCE TRAINING FACILITY |  |  |  |  | 2013-09-10 | 2014-11-21 | 2015-10-18 | 0.55807 | 2014-11-21
2015-08-31 | 2014 | Navy Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | N684691400 | NAVSEA HQ RESTORATION |  |  |  |  | 2014-02-14 | 2015-01-31 | 2015-01-31 | 0.99909 | 2015-01-30
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N00204791 | HVAC JOINT AVIATION SURVIVAL TRAINING |  |  |  |  | 2012-10-13 | 2013-08-08 | 2013-08-08 | 1 | 2013-12-19
2015-08-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207153 | BAMS UAS OPERATOR TRAINING FACILITY |  | 1321000 | N42237100 |  | 2012-07-09 | 2013-12-17 | 2014-04-09 | 0.96069 | 2014-03-24
2015-08-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207624 | P-8A TRAINING FACILITY |  | 11437000 | N42237636, N42237100 |  | 2012-07-09 | 2013-12-17 | 2014-04-09 | 0.99847 | 2014-03-24
2015-08-31 | 2015 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207631 | P-8A RUNWAY THRESHOLDS AND TAXIWAYS |  |  |  |  | 2015-03-13 | 2016-04-19 | 2016-06-26 | 0.16059 | 2016-06-26
2015-08-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207654 | P-8A HANGAR UPGRADES |  |  |  |  | 2015-04-14 |  |  | 0.015086
2015-08-31 | 2013 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207655 | BAMS MISSION CONTROL COMPLEX |  |  |  |  | 2013-08-28 | 2014-12-27 | 2015-08-27 | 0.96808 | 2015-08-28
2015-08-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION |  |  |  |  | 2014-10-10 | 2016-04-19 | 2016-06-26 | 0.057679 | 2016-06-26
2015-08-31 | 2015 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207664 | MH-60 PARKING APRON |  |  |  |  | 2015-05-14 |  |  | 0
2015-08-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  |  |  |  | 2014-08-29 | 2016-01-07 | 2016-02-14 | 0 | 2016-01-07
2015-08-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201425 | LCS LOGISTICS SUPPORT FACILITY |  |  |  |  | 2014-06-13 | 2015-11-26 | 2016-01-10 | 0.80291 | 2015-11-26
2015-08-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS |  |  |  |  | 2012-08-29 | 2014-02-21 | 2015-03-02 | 0.62936 | 2015-12-18
2015-08-31 | 2015 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N60508278 | PAVEMENT LANDING SYSTEMS |  |  |  |  | 2015-08-05 | 2016-02-16 | 2016-02-16 | 0 | 2016-02-16
2015-08-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE |  |  |  |  | 2012-06-21 | 2015-06-15 | 2015-06-15 | 0.87956 | 2015-06-15
2015-08-31 | 2011 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N61007015 | CALIBRATION FACILITY LAND ACQUISITION |  |  |  |  | 2012-01-14 |  |  | 1
2015-08-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237601 | SECURITY ENCLAVE AND VEHICLE BARRIER |  | 5445000 | Sequestration Reprogramming |  | 2012-03-30 | 2013-09-07 | 2014-12-09 | 0.96891 | 2014-07-31
2015-08-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237620 | WATERFRONT EMERGENCY GENERATORS |  |  |  |  | 2011-09-02 | 2013-05-13 | 2015-06-02 | 0.99989 | 2015-06-01
2015-08-31 | 2012 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE |  |  |  |  | 2014-05-01 | 2017-04-16 | 2017-04-16 | 0.40736 | 2017-04-16
2015-08-31 | 2011 | Navy Active | Major Military Construction | GUAM | GUAM | N61755205 | DAR/DPRI-DEFENSE ACCESS ROAD IMPROVEMENTS (AGANA) |  |  |  |  | 2015-06-30 |  |  | 1
2015-08-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  |  |  |  | 2014-04-10 | 2016-04-25 | 2016-09-23 | 0.20905 | 2016-04-25
2015-08-31 | 2013 | Navy Active | Military Family Housing Improvement | GUAM | GUAM | N617551301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE |  |  |  |  | 2013-09-26 | 2015-09-09 | 2015-10-10 | 0.97142 | 2015-10-09
2015-08-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755425 | MODULAR STORAGE MAGAZINE |  |  |  |  | 2014-05-26 | 2016-06-11 | 2017-01-20 | 0.25624 | 2016-06-11
2015-08-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755518 | X-RAY WHARF IMPROVEMENTS |  |  |  |  | 2014-06-17 | 2016-10-20 | 2017-03-15 | 0.17308 | 2016-09-20
2015-08-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755566 | EMERGENT REPAIR FACILITY EXPANSION |  |  |  |  | 2014-04-24 | 2016-05-12 | 2016-06-29 | 0.33503 | 2016-05-12
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | GUAM | GUAM | N61755630 | HARDEN ELECTRICAL DISTRIBUTION LINE (POLARIS PT ROAD) |  |  |  |  | 2014-10-14 | 2015-12-24 | 2015-12-24 | 0.4581 | 2015-12-24
2015-08-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY |  |  |  |  | 2014-04-03 | 2016-04-11 | 2016-04-11 | 0.65098 | 2016-04-11
2015-08-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755638 | SIERRA WHARF IMPROVEMENTS |  |  |  |  | 2014-06-13 | 2015-03-26 | 2015-04-25 | 0.87167 | 2015-04-24
2015-08-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N61064400 | NORTH LOOP ELECTRICAL REPLACEMENT |  | 2776000 | N42237100 |  | 2012-03-29 | 2014-01-02 | 2014-12-31 | 0.87915 | 2013-12-24
2015-08-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813005 | JOINT POW/MIA ACCOUNTING, USPACOM |  |  |  |  | 2011-06-20 | 2013-07-05 | 2015-08-13 | 0.91161 | 2015-04-13
2015-08-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY |  |  |  |  | 2012-04-19 | 2013-11-16 | 2014-11-09 | 0.99007 | 2014-11-09
2015-08-31 | 2015 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813048 | SUBMARINE MANEUVERING ROOM TRAINER FACILITY |  |  |  |  | 2015-03-13 | 2016-10-04 | 2016-10-04 | 0.12834 | 2016-10-04
2015-08-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE |  |  |  |  | 2011-07-08 | 2012-08-15 | 2013-04-30 | 0.99994 | 2013-06-03
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813058 | ROCKFALL PROTECTION AT RED HILL |  |  |  |  | 2014-12-08 | 2016-05-18 | 2016-05-18 | 0.0084711 | 2016-05-18
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) |  |  |  |  | 2011-10-03 | 2012-12-24 | 2013-03-01 | 1 | 2013-03-01
2015-08-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813270 | DRYDOCK WATERFRONT FACILITY |  |  |  |  | 2014-03-03 | 2015-12-11 | 2015-12-11 | 0.15884 | 2016-12-30
2015-08-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  |  |  |  | 2014-07-14 | 2017-08-03 | 2017-12-18 | 0.36205 | 2017-10-27
2015-08-31 | 2012 | Navy Active | Major Military Construction | ILLINOIS | UNITED STATES | N00128816 | DECENTRALIZE STEAM SYSTEM |  |  |  |  | 2012-06-27 | 2016-07-14 | 2016-07-14 | 0.94679 | 2016-07-14
2015-08-31 | 2014 | Navy Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611407 | SITE IMPROVEMENTS - GENERAL OFFICERS QUARTERS A |  |  |  |  | 2014-10-14 | 2014-11-30 | 2015-07-30 | 0.035205
2015-08-31 | 2014 | Navy Active | Major Military Construction | MAINE | UNITED STATES | N32446266 | STRUCTURAL SHOPS CONSOLIDATION |  |  |  |  | 2015-08-31 | 2018-01-23 | 2018-01-23 | 5.2156e-05 | 2018-01-23
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  |  |  |  | 2014-10-14 |  |  | 0.2078
2015-08-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC |  |  |  |  | 2011-06-16 | 2012-07-30 | 2014-07-16 | 0.99432 | 2013-07-31
2015-08-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 |  |  |  |  | 2014-07-14 | 2016-04-01 | 2016-04-29 | 0.26703 | 2016-10-20
2015-08-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151162 | AGILE CHEMICAL FACILITY PHASE 2 |  |  |  |  | 2012-08-24 | 2014-06-16 | 2015-11-15 | 0.74152 | 2015-11-13
2015-08-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151222 | DECENTRALIZE STEAM SYSTEM |  |  |  |  | 2012-10-12 | 2015-11-06 | 2015-11-06 | 0.72746 | 2015-11-06
2015-08-31 | 2014 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61152001 | MARFORCYBERCOM HQ-OPS BUILDING |  |  |  |  | 2015-04-21 | 2017-05-04 | 2017-05-04 | 1.8253e-05 | 2017-05-04
2015-08-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N68469110 | REPLACE CONDEMNED COATINGS LABORATORY |  |  |  |  | 2012-09-11 | 2013-08-28 | 2014-05-30 | 0.99527 | 2014-04-24
2015-08-31 | 2013 | Navy Active | Major Military Construction | MISSISSIPPI | UNITED STATES | N63043317 | DINING FACILITY |  |  |  |  | 2013-12-31 | 2015-10-09 | 2015-10-09 | 0.38888 | 2016-01-29
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | N69213206 | CONSTRUCT DISPATCH CENTER |  |  |  |  | 2011-12-01 | 2013-01-25 | 2013-03-29 | 1 | 2013-03-26
2015-08-31 | 2013 | Navy Active | Major Military Construction | NEW JERSEY | UNITED STATES | N69213237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION |  |  |  |  | 2013-09-17 | 2014-11-27 | 2015-06-26 | 0.99634 | 2015-02-12
2015-08-31 | 2014 | Navy Active | Major Military Construction | OKLAHOMA | UNITED STATES | N83447136 | TACAMO E-6B HANGAR |  |  |  |  | 2014-10-14 | 2016-02-12 | 2016-03-02 | 0.095036 | 2016-04-27
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | OREGON | UNITED STATES | N00620246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY |  |  |  |  | 2013-10-14 | 2014-09-30 | 2014-12-19 | 0.98037 | 2015-01-21
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | N32414203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES |  |  |  |  | 2012-03-16 | 2012-09-13 | 2012-09-13 | 1 | 2012-08-28
2015-08-31 | 2015 | Navy Active | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  |  |  |  | 2015-06-01 | 2016-11-23 | 2016-11-23 | 0 | 2016-11-23
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | N32411056 | VPT TEST FACILITY |  |  |  |  | 2013-03-28 | 2013-10-31 | 2013-12-13 | 0.98569 | 2013-11-21
2015-08-31 | 2011 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411068 | ELECTROMAGNETIC SENSOR FACILITY |  |  |  |  | 2011-08-23 | 2013-08-22 | 2014-09-26 | 0.98136 | 2014-03-24
2015-08-31 | 2014 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411103 | HEWITT HALL RESEARCH CENTER |  |  |  |  | 2014-08-14 | 2015-12-16 | 2016-01-01 | 0.49833 | 2015-12-16
2015-08-31 | 2015 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  |  |  |  | 2015-08-05 |  |  | 0
2015-08-31 | 2014 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  |  |  |  | 2014-09-03 | 2018-06-20 | 2018-04-08 | 0.15428 | 2018-04-08
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241288 | WASTEWATER SYSTEM |  |  |  |  | 2014-04-11 | 2015-03-27 | 2015-05-27 | 0.96427 | 2015-07-17
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241294 | CONNECT TO KINGSVILLE WATER SYSTEM |  |  |  |  | 2012-10-08 | 2014-03-21 | 2014-08-25 | 0.98725 | 2014-08-25
2015-08-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443383 | CONTROLLED INDUSTRIAL FACILITY |  | 7621000 | N684691400 |  | 2012-06-14 | 2014-09-28 | 2015-04-06 | 0.4562 | 2016-02-16
2015-08-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443516 | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | N32443516A |  |  |  | 2011-04-14 | 2014-11-22 | 2015-10-02 | 0.77751 | 2016-02-29
2015-08-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE |  |  |  |  | 2013-12-11 | 2015-12-27 | 2015-12-27 | 0.8484 | 2016-02-23
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092199 | MSRON FOUR BOAT STORAGE BUILDING |  |  |  |  | 2012-12-28 | 2013-11-08 | 2013-11-15 | 0.99949 | 2013-11-15
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY |  |  |  |  | 2011-08-17 | 2012-09-30 | 2012-11-13 | 0.98442 | 2012-11-13
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG |  |  |  |  | 2011-11-18 | 2012-07-21 | 2013-05-31 | 1 | 2013-05-08
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 |  |  |  |  | 2013-03-14 | 2013-08-30 | 2013-09-29 | 0.85655 | 2013-09-12
2015-08-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N50092499 | POWER DISTRIBUTION UPGRADES |  |  |  |  | 2012-10-08 | 2014-10-09 | 2015-08-01 | 0.94914 | 2015-04-27
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092662 | EOD ESU TWO EXPEDITIONARY LOGISTICS OVERHAUL WAREHOUSE |  |  |  |  | 2014-08-20 | 2014-11-21 | 2015-01-20 | 0.24441 | 2015-01-20
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N57095101 | ROAD IMPROVEMENTS CAMP ALLEN AREA |  |  |  |  | 2011-02-28 | 2011-09-21 | 2012-01-27 | 1 | 2012-01-27
2015-08-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N57095197 | DECENTRALIZE STEAM SYSTEM |  |  |  |  | 2012-10-04 | 2015-05-08 | 2015-07-07 | 0.92479 | 2015-07-17
2015-08-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191513 | A SCHOOL BARRACKS |  | 5604000 | N42237100 |  | 2013-11-14 | 2015-12-16 | 2015-12-30 | 0.49979 | 2016-04-01
2015-08-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS |  |  |  |  | 2012-10-11 | 2014-10-12 | 2015-05-07 | 0.8128 | 2015-11-30
2015-08-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191582 | UNDERSEA SURVEILLANCE SCIF FACILITY |  |  |  |  | 2012-12-03 | 2013-11-29 | 2014-06-27 | 0.99991 | 2014-06-25
2015-08-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  |  |  |  | 2014-09-30 | 2016-10-25 | 2016-10-25 | 0.015352 | 2018-01-25
2015-08-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY |  |  |  |  | 2013-09-02 | 2015-03-12 | 2015-09-30 | 0.89723 | 2015-10-07
2015-08-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151372 | PHYSICAL FITNESS CENTER |  |  |  |  | 2013-10-11 | 2015-05-02 | 2015-09-16 | 0.94549 | 2015-09-16
2015-08-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688123 | BACHELOR QUARTERS, HOMEPORT ASHORE |  | 3084000 | N684691400 |  | 2012-09-14 | 2014-09-13 | 2015-05-31 | 0.98881 | 2015-07-16
2015-08-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  |  |  |  | 2014-07-14 | 2016-01-01 | 2016-01-01 | 0.14427 | 2016-01-01
2015-08-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE |  |  |  |  | 2011-06-28 | 2012-06-18 | 2012-11-07 | 1 | 2012-11-07
2015-08-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688862 | PIER 1 UPGRADES TO BERTH USNS COMFORT |  | 6185000 | M00681159, N42237100 |  | 2011-08-09 | 2012-08-09 | 2012-09-28 | 0.78992 | 2012-09-18
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING |  |  |  |  | 2011-07-04 | 2012-01-26 | 2012-04-30 | 1 | 2012-04-16
2015-08-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620239 | EA-18G FACILITY IMPROVEMENTS |  |  |  |  | 2014-09-08 | 2017-05-26 | 2017-05-26 | 0.13976 | 2017-05-26
2015-08-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620245 | EA-18G FLIGHT SIMULATOR FACILITY |  |  |  |  | 2013-06-27 | 2014-11-25 |  | 0.97
2015-08-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620251 | P-8A HANGAR AND TRAINING FACILITIES |  |  |  |  | 2014-08-04 | 2016-01-12 | 2016-01-26 | 0.26957 | 2016-01-26
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N00620257 | HANGAR 11 MODIFICATIONS FOR SEARCH AND RESCUE |  |  |  |  | 2014-09-16 |  |  | 0.9948
2015-08-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 |  |  |  |  | 2012-06-08 | 2013-12-24 | 2014-11-10 | 0.89045 | 2013-06-27
2015-08-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  |  |  |  | 2014-08-01 | 2016-02-16 | 2016-02-16 | 0.13414 | 2016-02-16
2015-08-31 | 2015 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436422 | INTEGRATED WATER TREATMENT SYSTEM DD 1, 2 & 5 |  |  |  |  | 2015-05-18 | 2016-10-25 | 2016-10-25 | 0.006549 | 2016-10-25
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436839 | RENOVATE LOWER BASE FIRE STATION |  |  |  |  | 2012-09-14 | 2013-08-31 | 2013-11-22 | 1 | 2013-08-31
2015-08-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436843 | CSDS-5 LABORATORY EXPANSION PHASE ! |  |  |  |  | 2011-06-17 | 2012-10-15 | 2015-02-16 | 0.94674 | 2013-09-24
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436855 | SUBMARINE BRIDGE TEAM SIMULATOR |  |  |  |  | 2015-07-14 |  |  | 0.0012799
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436857 | FLOATING LABORATORY, MOORING DOLPHINS |  |  |  |  | 2013-05-31 |  |  | 0.99976
2015-08-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER |  |  |  |  | 2011-06-17 | 2013-06-26 | 2014-08-28 | 0.99984 | 2013-07-10
2015-08-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436913 | EHW SECURITY FORCE FACILITY |  | 7933000 | N684691400 |  | 2012-02-14 | 2013-08-08 | 2014-02-16 | 0.75953 | 2014-06-11
2015-08-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N63402973 | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | N68436973F |  |  |  | 2010-11-24 | 2011-11-08 | 2012-10-29 | 0.97137 | 2012-06-01
2015-08-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436985 | WRA VEHICLE BARRIERS |  | 7587000 | N42237636 |  | 2012-02-24 | 2013-12-10 | 2014-06-30 | 0.85949 | 2013-12-11
2015-08-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436987 | EMERGENCY GENERATOR, LIMITED AREA |  |  |  |  | 2011-06-17 | 2013-06-26 | 2014-08-28 | 0.99415 | 2013-07-10
2015-08-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 |  |  |  |  | 2012-05-23 | 2016-01-09 | 2016-01-11 | 0.93143 | 2016-01-13
2015-08-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | N68436990A |  |  |  | 2012-11-15 | 2016-01-09 | 2016-01-11 | 0.76859 | 2016-01-13
2015-08-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990B |  |  |  | 2014-01-14 |  |  | 0.69422
2015-08-31 | 2015 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVES HANDLING WHARF #2 - INC 4 | N68436990C |  |  |  | 2015-01-22 |  |  | 0.12209
2015-08-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY |  | 15471000 | Sequestration Reprogramming |  | 2012-08-31 | 2016-02-29 | 2016-02-29 | 0.62926 | 2016-02-29
2015-08-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005954 | WATERFRONT DEVELOPMENT, PHASE 3 |  | 19865000 | Sequestration Reprogramming |  | 2012-03-14 | 2015-10-30 | 2015-10-30 | 0.93868 | 2015-10-30
2015-08-31 | 2012 | Navy Active | Major Military Construction |  | DIEGO GARCIA | N68539184 | POTABLE WATER PLANT MODERNIZATION |  |  |  |  | 2013-01-04 | 2015-07-30 | 2015-08-26 | 0.77839 | 2015-08-26
2015-08-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A219 | GENERAL WAREHOUSE |  |  |  |  | 2012-04-16 | 2013-12-26 | 2014-08-24 | 0.84199 | 2015-07-05
2015-08-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A227 | ARMORY |  |  |  |  | 2014-08-08 | 2015-09-28 | 2015-09-28 | 0.24538 | 2015-09-28
2015-08-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A912 | PAVE EXTERNAL ROADS |  |  |  |  | 2012-04-16 |  |  | 0.86302
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A917 | CRITICAL POWER FOR BULDING 200 |  |  |  |  | 2014-06-05 |  |  | 1
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A918 | CRITICAL POWER FOR BUILDING T-130 |  |  |  |  | 2014-06-05 |  |  | 1
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A919 | CRITICAL POWER FOR BLDGS 111, 113 AND 115 |  |  |  |  | 2014-06-05 |  |  | 1
2015-08-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A921 | UNACCOMPANIED HOUSING |  |  |  |  | 2014-10-15 | 2016-05-30 | 2016-07-25 | 0.31641 | 2016-07-25
2015-08-31 | 2013 | Navy Active | Major Military Construction |  | GREECE | N66691907 | AIRCRAFT PARKING APRON EXPANSION |  | 417000 | FY Prior Year Rescission |  | 2014-07-25 | 2016-05-15 | 2016-05-15 | 0.29519 | 2016-05-15
2015-08-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 |  |  |  |  | 2014-10-13 | 2016-02-02 | 2016-02-02 | 0.17089 | 2016-02-02
2015-08-31 | 2015 | Navy Active | Major Military Construction |  | JAPAN | M62613602 | SECURITY MODS DPRI MC167-T (CVW-5 E2D EA-18G) |  |  |  |  | 2015-05-11 | 2016-06-13 | 2016-06-13 | 0 | 2016-09-12
2015-08-31 | 2014 | Navy Active | Major Military Construction |  | JAPAN | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  |  |  |  | 2014-10-03 | 2017-01-17 | 2017-01-17 | 0.00036563 | 2017-01-17
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054012 | CONSTRUCT NACCC ADDITION |  |  |  |  | 2011-06-24 | 2012-04-13 | 2012-04-20 | 1 | 2012-04-20
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054022 | IKEGO YOUTH CENTER (IKEGO HSG AREA - 3087) |  |  |  |  | 2014-02-20 |  |  | 0.98
2015-08-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER |  |  |  |  | 2011-07-15 | 2012-12-03 | 2013-01-20 | 1 | 2013-01-17
2015-08-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) |  |  |  |  | 2012-08-01 | 2014-01-13 | 2014-01-13 | 1 | 2014-01-13
2015-08-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 |  |  |  |  | 2012-08-22 | 2014-10-07 | 2015-06-10 | 0.96829 | 2015-05-19
2015-08-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 |  |  |  |  | 2014-07-29 | 2016-02-21 | 2016-02-21 | 0.28296 | 2016-02-21
2015-08-31 | 2013 | Navy Active | Major Military Construction |  | JAPAN | N61056353 | BACHELOR QUARTERS |  |  |  |  | 2013-10-11 | 2017-07-29 | 2017-07-29 | 0 | 2017-07-29
2015-08-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR |  |  |  |  | 2012-10-10 | 2013-08-26 | 2013-11-22 | 1 | 2013-11-22
2015-08-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) |  |  |  |  | 2012-08-29 | 2013-12-09 | 2014-07-01 | 1 | 2014-07-01
2015-08-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES |  |  |  |  | 2013-12-15 | 2015-03-31 | 2015-05-05 | 0.95751 | 2015-05-04
2015-08-31 | 2011 | Navy Active | Major Military Construction |  | JAPAN | N61057203 | AVIATION SIMULATOR TRAINING FACILITY |  |  |  |  | 2011-08-12 | 2013-11-13 | 2013-11-13 | 0.97112 | 2013-11-13
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61057221 | HELO ALFS TEST ROOM, BUILDING 194 |  |  |  |  | 2014-08-20 | 2015-02-03 | 2015-05-19 | 0.91076 | 2015-05-15
2015-08-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) |  |  |  |  | 2014-10-14 |  |  | 0.049601
2015-08-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N627351102 | WHOLEHOUSE IMPROVEMENT |  |  |  |  | 2011-07-10 | 2012-10-17 | 2013-02-14 | 1 | 2013-01-18
2015-08-31 | 2013 | Navy Active | Major Military Construction |  | ROMANIA | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  |  |  |  | 2014-05-14 |  |  | 0.40484
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction |  | SINGAPORE | N61077123 | TEMPORARY LCS SUSTAINMENT FACILITY |  |  |  |  | 2012-12-20 | 2013-03-10 | 2013-03-10 | 0.93092 | 2014-01-15
2015-08-31 | 2012 | Navy Active | Military Family Housing Improvement |  | SPAIN | N628631201 | WHOLEHOUSE REVITALIZATION, LAS PALMERAS, PHASE 3 |  |  |  |  | 2015-03-27 |  |  | 0.021159
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863708 | CONSTRUCT LCAC BEACH ACCESS RAMP |  |  |  |  | 2013-10-13 | 2014-05-28 | 2014-06-20 | 0.97296 | 2014-06-20
2015-08-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863709 | GENERAL PURPOSE WAREHOUSE |  |  |  |  | 2013-09-06 | 2015-03-20 | 2015-03-20 | 0.66396 | 2015-08-15
2015-08-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863710 | HIGH EXPLOSIVE MAGAZINE |  | 3704000 | Design |  | 2013-09-06 | 2015-03-20 | 2015-03-20 | 0.63941 | 2015-08-15
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863733 | PROVIDE ELECTROMAGNETIC CALIBRATION COMPLEX |  |  |  |  | 2014-10-03 | 2014-11-22 | 2014-11-22 | 0.24945
2015-08-31 | 2011 | Navy Active | Major Military Construction |  | SPAIN | N62863897 | AIR TRAFFIC CONTROL TOWER |  | 2052000 | N42237100 |  | 2012-06-29 | 2014-09-03 | 2016-03-28 | 0.7963 | 2015-08-21
2015-08-31 | 2014 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | M68479031 | RESERVE BOAT MAINTENANCE AND STORAGE FACILITY |  |  |  |  | 2015-04-07 | 2016-03-23 | 2016-03-23 | 0.011821 | 2016-03-23
2015-08-31 | 2011 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | N00206477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY |  |  |  |  | 2011-06-17 | 2013-06-07 | 2014-02-12 | 0.953 | 2014-05-07
2015-08-31 | 2012 | Navy Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414860 | ARMED FORCES RESERVE CENTER, PITTSBURGH |  | 500000 | Design |  | 2012-08-14 | 2014-02-06 | 2014-05-31 | 0.99449 | 2014-05-31
2015-08-31 | 2013 | Navy Reserve | Major Military Construction | TEXAS | UNITED STATES | N83447047 | COMMERCIAL VEHICLE INSPECTION SITE |  |  |  |  | 2013-09-26 | 2014-11-06 | 2015-03-30 | 0.64219 | 2015-07-15
2015-08-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212543 | NAVELSG RESERVE FORCES MARSHALLING YARDS |  |  |  |  | 2013-01-30 | 2014-01-21 | 2014-01-21 | 1 | 2013-10-23
2015-08-31 | 2011 | Navy Reserve | Major Military Construction | VIRGINIA | UNITED STATES | N69212743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX |  | 558000 | Design |  | 2011-06-17 | 2013-04-27 | 2014-10-18 | 1 | 2013-10-18
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | ALASKA | UNITED STATES | P-531 | Cold Weather Maritime Training Facility |  |  |  |  | 2014-03-04 | 2015-04-15 | 2015-04-15 | 1 | 2015-05-06
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | ARIZONA | UNITED STATES | 53542 | Parachute Training Facility |  |  |  |  | 2014-11-09 | 2016-05-09 | 2016-05-07 | 0.24
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1049 | Range 130 Support Projects |  |  |  |  | 2013-06-03 | 2014-11-13 | 2015-11-13 | 0.42
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1174 | MWD Facility |  |  |  |  | 2012-10-03 | 2014-03-23 | 2014-11-14 | 0.99 | 2014-11-14
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-876 | Indoor Dynamic Shooting Facility | [5 empty] | 2016-10-01 | 2016-10-07 | 0.07
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-888 | Close Quarters Combat Range, Phase II | [5 empty] | 2016-09-30 | 2016-09-29 | 0.07
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 69446 | Group Support Battalion Detachment |  |  |  |  | 2014-08-27 | 2016-02-18 | 2016-04-20 | 0.24
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 76367 | SOF Battalion Operations Complex |  |  |  |  | 2014-09-04 | 2016-06-16 | 2016-10-01 | 0.14
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81483 | Mtn Climb/Rappel Tower (5UMC) |  |  |  |  | 2013-09-20 | 2014-10-15 | 2015-01-25 | 0.98 | 2014-11-26
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76366 | Company Operations Facility (GSTB) |  |  |  |  | 2012-09-12 | 2015-09-12 | 2016-04-26 | 0.93
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76371 | Company Operations Facility (GSB) |  |  |  |  | 2012-09-12 | 2015-09-12 | 2016-04-26 | 0.93
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 79440 | SOF Boat Docks |  |  |  |  | 2015-04-30 | 2016-08-22 | 2016-08-22 | 0
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV083002 | Add/Alter Operations Facility |  |  |  |  | 2014-09-02 | 2016-05-24 | 2016-10-20 | 0.14
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV103011 | SOF Simulator Facility |  |  |  |  | 2012-09-13 | 2013-12-24 | 2014-07-18 | 1 | 2014-07-18
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTFA113004 | SOF AvFID Ops and MX Facilities |  |  |  |  | 2013-11-05 | 2016-12-01 | 2017-05-14 | 0.7
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | NVZR083702 | Joint Special Operations University Facility |  |  |  |  | 2013-11-04 | 2015-09-15 | 2016-01-07 | 0.5
2015-08-31 | 2011 | Special Operations Command | Major Military Construction | GEORGIA | UNITED STATES | 65395 | Company Support Facility |  |  |  |  | 2011-12-27 | 2013-06-19 | 2014-07-31 | 0.99 | 2014-05-30
2015-08-31 | 2015 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 36977 | SOF System Integration Maintenance Office Facility |  |  |  |  | 2015-07-01 | 2017-06-10 | 2017-06-10 | 0
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66597 | Landgraf Hangar Extension |  |  |  |  | 2014-04-29 | 2015-10-21 | 2015-11-20 | 0.41
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66598 | Rotary Wing Hangar |  |  |  |  | 2012-04-16 | 2014-02-15 | 2015-04-29 | 0.99 | 2015-05-05
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 69447 | Group Support Battalion Detachment |  |  |  |  | 2014-04-14 | 2016-02-13 | 2016-05-15 | 0.66
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 76374 | MH-47 Hangar |  |  |  |  | 2014-08-27 | 2014-03-23 | 2014-08-29 | 1 | 2014-08-27
2015-08-31 | 2015 | Special Operations Command | Major Military Construction | NEVADA | UNITED STATES | P-418 | SOF Tactical GMV Maintenance Facility | [5 empty] | 2017-02-23 | 2017-02-23 | 0
2015-08-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063049 | Hangar / AMU (MC-130J) |  |  |  |  | 2011-10-11 | 2013-12-01 | 2014-05-02 | 0.99 | 2014-05-02
2015-08-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 7132 | 66362 |  | 2012-09-06 | 2013-07-17 | 2014-06-03 | 0.99 | 2014-06-03
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073014 | SOF C-130 Sq Ops Facility |  |  |  |  | 2014-07-11 | 2014-02-22 | 2014-07-11 | 1 | 2014-07-11
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073018 | SOF C-130 Wash Rack Hangar |  |  |  |  | 2014-09-09 | 2014-04-10 | 2014-08-29 | 1 | 2014-09-09
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073021 | SOF AMXS Facility |  |  |  |  | 2013-01-10 | 2014-12-22 | 2014-09-19 | 1 | 2014-09-22
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083012A | SOF Hangar/AMU |  |  |  |  | 2012-10-24 | 2014-12-23 | 2014-09-07 | 1 | 2014-10-02
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083013 | Combat Parking Apron |  |  |  |  | 2014-06-13 | 2015-08-13 | 2015-11-22 | 0.97
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083016 | SOF Squadron Operations Facility |  | 2293 | CZQZ063035 |  | 2012-11-09 | 2015-01-06 | 2014-05-30 | 1 | 2014-05-30
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NEW MEXICO | UNITED STATES | CZQZ100221 | Parachute Drying Tower (3 UMC) |  |  |  |  | 2014-07-28 | 2015-05-24 | 2015-08-21 | 0.98
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60272 | Communications Training Complex (SWCS) |  |  |  |  | 2012-09-12 | 2014-03-06 | 2015-05-29 | 0.96
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60821 | Squadron Headquarters Addition |  |  |  |  | 2012-06-06 | 2014-06-06 | 2015-07-04 | 1 | 2015-03-16
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 61064 | SOF Upgrade Training Facility |  |  |  |  | 2014-11-17 | 2016-05-10 | 2016-10-13 | 0.08
2015-08-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64484 | Operations Additions |  |  |  |  | 2011-08-25 | 2014-06-10 | 2015-10-21 | 0.99
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 65052 | Medical Support Addition |  |  |  |  | 2013-10-16 | 2015-08-25 | 2015-04-17 | 0.99 | 2015-01-23
2015-08-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 66362 | C4 Facility - JSOC |  |  |  |  | 2012-06-14 | 2014-01-31 | 2015-06-16 | 1 | 2015-01-05
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 68526 | SOF Engineer Training Facility |  |  |  |  | 2015-05-27 | 2017-04-07 | 2017-04-07 | 0
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69382 | Civil Affairs Battalion Complex |  |  |  |  | 2013-10-16 | 2015-08-14 | 2015-08-14 | 0.86
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69458 | Battalion Operations Complex |  | 1738 | 69445 |  | 2012-12-10 | 2014-06-03 | 2015-08-13 | 0.93
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69493 | Sustainment Bde Headquarters |  |  |  |  | 2014-06-18 | 2016-05-02 | 2016-09-25 | 0.37
2015-08-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69573 | Admin/Company Operations |  |  |  |  | 2011-10-27 | 2013-04-18 | 2013-11-21 | 0.99 | 2013-11-21
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69758 | Brigade Headquarters | [5 empty] | 2014-05-08 | 2015-12-28 | 0.68
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2896000 | 69445 |  | 2012-11-07 | 2014-05-01 | 2015-04-27 | 1 | 2015-04-27
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters | 25 |  |  |  | 2012-11-07 | 2015-03-01 | 2015-04-27 | 1 | 2015-04-27
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76364 | Battalion Operations Facility |  | 5000 | 69445 |  | 2012-12-04 | 2014-08-26 | 2015-12-15 | 0.93
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76375 | Civil Affairs Battalion Annexes |  |  |  |  | 2014-12-01 | 2016-07-23 | 2017-01-19 | 0.09
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76376 | Language and Cultural Center |  |  |  |  | 2015-01-09 | 2017-06-27 | 2018-01-15 | 0.06
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 79438 | Combat Medic Skills Sustainment Course Bldg |  |  |  |  | 2014-10-27 | 2016-04-19 | 2016-09-16 | 0.13
2015-08-31 | 2015 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 79456 | SOF Tactical Equipment Maintenance Facility (TEMF) |  |  |  |  | 2015-05-21 |  | 2017-09-27 | 0
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 79655 | SOF Training Facility (4UMC) |  |  |  |  | 2013-06-18 | 2014-10-15 | 2014-08-21 | 1 | 2014-10-01
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 80233 | SOF Live-Fire Training Tower (6UMC) |  |  |  |  | 2014-02-12 | 2015-05-15 | 2015-03-04 | 1 | 2015-03-04
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287a | Battalion Operations Complex |  |  |  |  | 2013-10-09 | 2015-05-13 | 2015-12-24 | 0.79
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287b | Battalion Operations Complex |  |  |  |  | 2014-11-20 | 2016-11-01 | 2016-11-01 | 0.14
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1218 | Marine Battalion Company/Team Facilities |  |  |  |  | 2014-02-20 | 2016-03-01 | 2016-01-23 | 0.54
2015-08-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1391 | SOF Sustainment Training Complex |  |  |  |  | 2014-09-13 | 2016-09-02 | 2016-09-02 | 0.21
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1393 | Survival Evasion Resistance Escape Trng Fac |  |  |  |  | 2014-02-20 | 2016-01-18 | 2016-01-23 | 0.54
2015-08-31 | 2015 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1396 | SOF Intel Ops Expansion | [5 empty] | 2017-03-09 | 2017-03-09 | 0
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1410 | SOF EOD Expansion (1UMC) |  |  |  |  | 2013-10-15 | 2014-09-22 | 2015-06-30 | 0.98
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1450 | Fires Platoon Storage Facility (7UMC) |  |  |  |  | 2014-03-13 | 2014-12-13 | 2015-07-17 | 0.97
2015-08-31 | 2014 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1469 | MSOB Support Facilities |  |  |  |  | 2014-09-30 | 2015-09-25 | 2015-11-24 | 0.39
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH043055 | SOF Training Facility |  |  |  |  | 2012-05-31 | 2013-11-22 | 2014-11-12 | 1 | 2014-10-29
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-164 | Logistics Support Facility |  |  |  |  | 2012-12-09 | 2014-07-24 | 2015-06-16 | 0.96
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-165 | CS/CSS Support Facility |  |  |  |  | 2014-10-06 | 2015-09-09 | 2015-11-26 | 0.79
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-473 | SEAL Team Operations Facility |  |  |  |  | 2014-08-13 | 2015-12-27 | 2015-12-27 | 0.54
2015-08-31 | 2012 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-504 | SOF Operational Vehicle Storage Facility (6UMC) |  |  |  |  | 2013-12-03 | 2014-10-20 | 2015-01-15 | 1 | 2015-04-18
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-564 | NSWG-4 Paraloft Addition (2UMC) |  |  |  |  | 2013-10-15 | 2014-12-31 | 2015-02-12 | 1 | 2015-02-12
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-769 | Building Renovation |  |  |  |  | 2013-01-02 | 2014-06-27 | 2015-02-20 | 0.99 | 2015-02-20
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-826 | Military Working Dog Facility |  |  |  |  | 2012-12-09 | 2014-07-24 | 2015-06-16 | 0.96
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 69257 | SOF Military Working Dog Kennel | [5 empty] | 2016-11-14 | 2016-11-14 | 0.3
2015-08-31 | 2013 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 69445 | SOF Battalion Operations Facility | [5 empty] | 2017-07-23 | 2017-07-23 | 0
2015-08-31 | 2012 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 76363 | Company Operations Facility |  |  |  |  | 2014-06-20 | 2014-04-01 | 2014-06-21 | 1 | 2014-06-20
2015-08-31 | 2014 | Special Operations Command | Major Military Construction |  | JAPAN | 78024 | SOF Facility Augmentation |  |  |  |  | 2015-07-01 | 2018-05-05 | 2018-05-05 | 0
2015-08-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | 61772 | Operations Complex |  |  |  |  | 2012-01-31 | 2013-04-25 | 2014-12-31 | 1 | 2015-01-21
2015-08-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033003 | Vehicle Maintenance Facility |  |  |  |  | 2012-01-31 | 2013-04-25 | 2015-03-05 | 1 | 2015-03-05
2015-08-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033005 | Storage Facility |  |  |  |  | 2012-01-31 | 2013-04-25 | 2014-12-31 | 1 | 2015-01-21
2015-08-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033019 | Air Operations Center |  |  |  |  | 2012-01-31 | 2013-04-25 | 2014-12-31 | 1 | 2015-01-21
2015-08-20 | 2011 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES | 80002 | Power Plant Modernization Phase 3 (WPP) |  | 4331051 | Budget Sequester: $4,001,00 Reprogramming: $330,051 to project 800003 |  | 2013-04-22 | 2016-05-11 | 2016-07-30 | 0.49 | 2016-07-30
2015-08-20 | 2014 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES | 80009 | Raven Rock Admin Facility Upgrade
2015-08-20 | 2014 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES | 80010 | Raven Rock Exterior Cooling Towers |  | 1000000 | Reprogramming: to project 800001
2015-08-20 | 2010 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80001 | Pentagon Electrical Upgrade |  |  |  |  | 2013-11-07 | 2015-02-05 | 2016-08-01 | 0.52 | 2016-08-01
2015-08-20 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80003 | Metro Entrance Facility/Visitor Screening Facility |  |  |  |  | 2013-11-01 | 2015-05-03 | 2016-02-29 | 0.59 | 2016-02-29
2015-08-20 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80004 | Secure Access Lane (SAL) |  |  |  |  | 2013-11-01 | 2015-05-01 | 2016-07-30 | 0.16 | 2016-07-30
2015-08-20 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80005 | Pentagon Heliport Control Tower/Fire Station |  | 798000 | Budget Sequester
2015-08-20 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80006 | Pentagon Memorial Pedestrian Plaza |  | 176000 | Budget Sequester
2015-08-20 | 2014 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80007 | PFPA Support Operations Center
2015-08-20 | 2014 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80008 | Boundary Channel Access Control Point
2015-08-20 | 2015 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80011 | Redundant Chilled Water Loop

## CONTRACTS
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Prime Contract Number | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date | Contract Remarks
2015-09-08 | 2014 | Air Force Active | ACC123183 |  | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143462 | 7200020.94 | 2016-02-20 | 2016-04-11
2015-09-08 | 2013 | Air Force Active | ACC123184 |  | 2013-03-14 | 2013-09-24 | Better Built Construction Serv | W912HN10D00530003 | 6458000 | 6704333 | 2015-05-01 | 2015-08-05
2015-09-08 | 2012 | Air Force Active | AETC120011 |  | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | W912PL13C0006 | 12358500 | 12904067 | 2014-09-26 | 2015-02-21
2015-09-08 | 2014 | Air Force Active | AETC176870 |  | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265367 | 3310071.35 | 2015-06-09 | 2015-06-30
2015-09-08 | 2012 | Air Force Active | AGGN123002P |  | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619171.54 | 1619171.54 | 2014-12-19 | 2014-12-19
2015-09-08 | 2014 | Air Force Active | AGGN143001 |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164308 | 1178891 | 2015-12-24 | 2015-12-24
2015-09-08 | 2014 | Air Force Active | AGGN143002 |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111892 | 7184142 | 2015-12-24 | 2016-01-12
2015-09-08 | 2014 | Air Force Active | AGGN143003 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645200 | 5645200 | 2015-10-12 | 2015-10-12
2015-09-08 | 2014 | Air Force Active | AGGN143004 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000000 | 11112754.93 | 2015-10-12 | 2015-11-14
2015-09-08 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 89918305 | 89918305 | 2017-04-16 | 2017-04-16
2015-09-08 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 96616619.3 | 96616619.3 | 2017-03-08 | 2017-03-08
2015-09-08 | 2014 | Air Force Active | AJJY143760 |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907700 | 17907700 | 2016-04-12 | 2016-04-12
2015-09-08 | 2014 | Air Force Active | AJJY153011 |  | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177269 | 6177269 | 2016-08-17 | 2016-08-17
2015-09-08 | 2012 | Air Force Active | AJJY983202 |  | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | N6274210D1308JQ01 | 30047253 | 33699699.75 | 2014-06-02 | 2015-07-01
2015-09-08 | 2010 | Air Force Active | AJXF063009 |  | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464830 | 10753260.37 | 2013-05-13 | 2013-05-25
2015-09-08 | 2014 | Air Force Active | AJXF103010 |  | 2014-08-15 | 2014-12-30 | The Haskell Company | N4008010D04910002 | 21754670 | 21754670 | 2017-04-05 | 2017-04-05
2015-09-08 | 2013 | Air Force Active | AJXF106000 |  | 2014-08-07 | 2015-03-04 | Heard Contracting | W912DR15C0010 | 2132837 | 2132837 | 2016-04-08 | 2016-04-08
2015-09-08 | 2009 | Air Force Active | AKNR041053 |  | 2011-02-22 | 2011-09-23 | MATOC Contractor | W912GB09D00690007 | 1367060 | 1367060 | 2013-02-09 | 2013-02-09
2015-09-08 | 2008 | Air Force Active | ALDA053001B |  | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 15238069 | 17873509.91 | 2012-08-22 | 2015-10-15
2015-09-08 | 2010 | Air Force Active | ALUA073006A |  | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | W912ER11C0001 | 35758850 | 37334850.11 | 2013-02-03 | 2014-12-30
2015-09-08 | 2011 | Air Force Active | ALUA073006B |  | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177236 | 34677440.18 | 2014-05-15 | 2014-06-29
2015-09-08 | 2011 | Air Force Active | ALUA073006B |  | 2014-09-02 | 2015-01-23 | Federal Contracting, Inc. | W912ER15C0003 | 4899425 | 4899425 | 2016-01-29 | 2016-01-29
2015-09-08 | 2008 | Air Force Active | ALUA073008A |  | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244838 | 31385349.09 | 2012-08-22 | 2015-10-15
2015-09-08 | 2010 | Air Force Active | ALUA103001 |  | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | W912ER12C0028 | 2579930.04 | 3160156.17 | 2013-09-08 | 2015-08-03
2015-09-08 | 2011 | Air Force Active | ALUA103012 |  | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | W912ER11D00010007 | 40848000 | 41717657.26 | 2015-10-03 | 2015-10-03
2015-09-08 | 2010 | Air Force Active | ALUA107000 |  | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272835 | 44788360.53 | 2014-04-06 | 2015-05-04
2015-09-08 | 2011 | Air Force Active | ALUA110032 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730623 | 1730623 | 2014-12-06 | 2014-12-06
2015-09-08 | 2011 | Air Force Active | ALUA113001 |  | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912567.09 | 10464450.14 | 2014-04-02 | 2014-06-11
2015-09-08 | 2011 | Air Force Active | ALUA113002 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557438 | 1557438 | 2014-12-06 | 2014-12-06
2015-09-08 | 2011 | Air Force Active | ALUA113005 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572399 | 1572399 | 2014-12-06 | 2014-12-06
2015-09-08 | 2011 | Air Force Active | ALUA113006 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573056 | 1573056 | 2014-12-06 | 2014-12-06
2015-09-08 | 2011 | Air Force Active | ALUA113009 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615612 | 615612 | 2014-12-06 | 2014-12-06
2015-09-08 | 2011 | Air Force Active | ALUA113010 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216400 | 1216400 | 2014-12-06 | 2014-12-06
2015-09-08 | 2011 | Air Force Active | ALUA113012 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615533 | 1615533 | 2014-12-06 | 2014-12-06
2015-09-08 | 2012 | Air Force Active | ALUA113026 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511518 | 1511518 | 2014-12-06 | 2014-12-06
2015-09-08 | 2012 | Air Force Active | ALUA113027 |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265194 | 1277795 | 2014-11-06 | 2014-12-06
2015-09-08 | 2012 | Air Force Active | ALUA113032 |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403744 | 1423578.75 | 2015-02-19 | 2015-02-24
2015-09-08 | 2012 | Air Force Active | ALUA113034 |  | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214606 | 1219631.89 | 2015-02-19 | 2015-02-19
2015-09-08 | 2011 | Air Force Active | ASHE083011 |  | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N3319107D02110002 | 7174169.76 | 8608122.48 | 2013-09-05 | 2015-03-15
2015-09-08 | 2013 | Air Force Active | ASHE103001 |  | 2014-03-06 | 2015-02-26 | Coop Muratori & Cementisti CMC Di Ravenn | N6247015C5005 | 1780234.26 | 1780234.26 | 2016-12-02 | 2016-12-02
2015-09-08 | 2012 | Air Force Active | ASHE163000 |  | 2012-06-06 | 2012-09-30 | Collodetto Angelo Costruzioni | N3319112R06220002 | 890232.58 | 988130.72 | 2013-12-29 | 2015-01-31
2015-09-08 | 2011 | Air Force Active | ATUH110101 |  | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest, JV, LLC | W912ER11D00130002 | 8364461 | 9345061.77 | 2012-09-08 | 2014-05-21
2015-09-08 | 2011 | Air Force Active | ATUH110103 |  | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest JV, LLC | W912ER11D00130002 | 9537395 | 7863428 | 2012-08-24 | 2014-05-21
2015-09-08 | 2011 | Air Force Active | ATUH110104 |  | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest IV, LLC | W912ER11D00130002 | 8305226 | 9188264.15 | 2012-08-24 | 2014-05-21
2015-09-08 | 2012 | Air Force Active | AWUB105002 |  | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998000 | 18717502.09 | 2013-11-24 | 2014-03-16
2015-09-08 | 2013 | Air Force Active | BAEY133001 |  | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947269 | 16020495.55 | 2016-03-30 | 2016-05-29
2015-09-08 | 2014 | Air Force Active | BAEY143000 |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699643 | 53699643 | 2016-11-04 | 2016-11-04
2015-09-08 | 2012 | Air Force Active | CTGB102040 |  | 2012-04-23 | 2012-08-03 | ITSI | FA6643-08-D-0005 | 1031327 | 1031327 | 2013-04-08 | 2013-04-08
2015-09-08 | 2014 | Air Force Active | CZQZ013004 |  | 2015-01-29 | 2015-05-18 | Speegle Construction Inc. | W912PP15C0006 | 5102200 | 5097100 | 2016-06-10 | 2016-06-10
2015-09-08 | 2014 | Air Force Active | CZQZ073023A |  | 2014-08-04 | 2014-12-05 | Speegle Construction Inc. | W912PP15C0001 | 7001000 | 7034068.17 | 2016-11-19 | 2016-11-22
2015-09-08 | 2014 | Air Force Active | CZQZ073050 |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19716709 | 19661648.55 | 2016-08-21 | 2016-08-21
2015-09-08 | 2011 | Air Force Active | DHAF080145 |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 1073822 | 146939.98 | 2013-10-03 | 2013-10-11
2015-09-08 | 2010 | Air Force Active | DHAF100031 |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671642 | 1986140.63 | 2012-02-28 | 2015-11-11
2015-09-08 | 2010 | Air Force Active | DHAF100120 |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136701 | 1184030.06 | 2012-02-28 | 2015-11-11
2015-09-08 | 2011 | Air Force Active | DHAF105000 |  | 2012-04-06 | 2012-07-31 | C Davis and Associates | W912ER12C0038 | 1003878 | 155733.6 | 2013-10-03 | 2013-10-11
2015-09-08 | 2011 | Air Force Active | DHAF110018 |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 1006756 | 191812 | 2013-10-03 | 2013-10-11
2015-09-08 | 2011 | Air Force Active | DHAF110019 |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 582994 | 128794.15 | 2013-10-03 | 2013-10-11
2015-09-08 | 2011 | Air Force Active | DHAF120037 |  | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhabi UAE) | W912BU13C0060 | 1514583 | 1625700 | 2015-01-20 | 2015-10-18
2015-09-08 | 2011 | Air Force Active | DHAF120057 |  | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120380 | 1179614 | 2014-11-24 | 2015-09-30
2015-09-08 | 2011 | Air Force Active | DHAF124001 |  | 2013-07-18 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1044893 | 1073954 | 2015-10-02 | 2015-12-21
2015-09-08 | 2011 | Air Force Active | FBNV063501 |  | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282136 | 23526207 | 2013-08-27 | 2014-09-24
2015-09-08 | 2012 | Air Force Active | FBNV103006P1 |  | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | W912PL12C0011 | 14347600 | 14990801 | 2014-07-30 | 2015-01-07
2015-09-08 | 2011 | Air Force Active | FBNV113002 |  | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223000 | 7534524 | 2013-05-02 | 2013-09-13
2015-09-08 | 2012 | Air Force Active | FBNV123002 |  | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | W912PL12C0018 | 12361000 | 12645529 | 2014-04-24 | 2015-05-21
2015-09-08 | 2012 | Air Force Active | FBNV133500 |  | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D01100001 | 1795000 | 1795000 | 2015-06-08 | 2015-09-28
2015-09-08 | 2010 | Air Force Active | FJXT033003 |  | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248940 | 11773483 | 2013-10-12 | 2014-10-21
2015-09-08 | 2011 | Air Force Active | FJXT113001 |  | 2011-03-09 | 2011-08-02 | Asset Group, Incorporated, Oklahoma City, Oklahoma | W912BU11C0024 | 2951817 | 2950318 | 2012-08-10 | 2012-11-06
2015-09-08 | 2010 | Air Force Active | FTFA061726 |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | W9127810C0074 | 4309000 | 4446687.97 | 2011-10-27 | 2014-06-26
2015-09-08 | 2014 | Air Force Active | FTFA073007 |  | 2014-07-24 | 2014-12-30 | Southeast Cherokee Constructio | W9127810D00780008 | 1457737 | 1457737 | 2016-02-05 | 2016-02-05
2015-09-08 | 2010 | Air Force Active | FTFA073902 |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | W9127810C0074 | 9452000 | 10701341.59 | 2011-07-15 | 2014-04-03
2015-09-08 | 2010 | Air Force Active | FTFA073904 |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | W9127810C0074 | 3217000 | 3422260 | 2011-10-07 | 2014-06-26
2015-09-08 | 2010 | Air Force Active | FTFA073905 |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | W9127810C0074 | 1464000 | 1534199 | 2011-06-15 | 2014-03-04
2015-09-08 | 2013 | Air Force Active | FTFA123000 |  | 2014-07-28 | 2014-10-30 | Barlovento LLC | W9127810D00720015 | 1756830 | 1756830 | 2015-12-05 | 2015-12-05
2015-09-08 | 2012 | Air Force Active | FTQW083005 |  | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061944 | 33161944 | 2016-08-15 | 2016-08-15
2015-09-08 | 2010 | Air Force Active | FTQW083007 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981132 | 28919519.5 | 2015-01-27 | 2016-12-22
2015-09-08 | 2011 | Air Force Active | FTQW083008 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981132 | 30286182.5 | 2015-01-27 | 2016-12-22
2015-09-08 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799228.84 | 1799228.84 | 2012-12-16 | 2012-12-16
2015-09-08 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978807.71 | 4978807.71 | 2013-08-28 | 2013-08-28
2015-09-08 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230292.49 | 3230292.49 | 2013-10-04 | 2013-10-04
2015-09-08 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805300 | 56392982.95 | 2014-06-19 | 2015-03-17
2015-09-08 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874106 | 2191910 | 2012-11-17 | 2012-11-17
2015-09-08 | 2013 | Air Force Active | GJKZ130025 |  | 2014-08-01 | 2014-12-31 | Ahtna Engineering | FA462013DB0040003 | 1698195 | 1698195 | 2015-12-17 | 2015-12-17
2015-09-08 | 2012 | Air Force Active | GJKZ860009 |  | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | W912DW12C0030 | 11957250 | 12620017 | 2014-01-21 | 2014-11-27
2015-09-08 | 2010 | Air Force Active | KNMD063003 |  | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | N6274209D1186HC08 | 7379329 | 5799126 | 2014-03-01 | 2014-04-22
2015-09-08 | 2014 | Air Force Active | KNMD142222 |  | 2013-11-18 | 2014-06-17 | SRB International LLC | N6274214C1312 | 2699000 | 2699000 | 2015-06-07 | 2015-06-07
2015-09-08 | 2014 | Air Force Active | KRSM103011 |  | 2013-07-22 | 2014-04-10 | CTI | W912PL14C0005 | 6587000 | 9361650.04 | 2015-10-14 | 2015-10-14
2015-09-08 | 2013 | Air Force Active | KRSM103012 |  | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781000 | 9728790.05 | 2015-07-21 | 2016-06-19
2015-09-08 | 2013 | Air Force Active | KRSM103030 |  | 2012-08-08 | 2013-12-17 | Zumwalt Construction, Inc. | W9123811D00260006 | 2028458 | 2033518.68 | 2015-07-21 | 2015-07-21
2015-09-08 | 2013 | Air Force Active | KRSM113028 |  | 2012-08-08 | 2013-12-17 | Creative Times, Inc. (CTI) | W9123811D00240002 | 3878926 | 3947868.62 | 2015-03-30 | 2015-04-24
2015-09-08 | 2012 | Air Force Active | KWRD013003 |  | 2012-05-18 | 2012-08-17 | Turner Atlantic Construction | W912PP12C0026 | 9843654 | 10234330.61 | 2014-05-17 | 2014-11-24
2015-09-08 | 2012 | Air Force Active | KWRD113005 |  | 2012-02-03 | 2012-06-13 | White Sands Construction | W912PP12C0017 | 4990320 | 5270436.56 | 2013-11-12 | 2014-11-21
2015-09-08 | 2013 | Air Force Active | KWRD123004 |  | 2013-03-01 | 2013-06-17 | HEW-Phelps | W912PP13C0019 | 20620000 | 20726768 | 2015-04-06 | 2015-04-06
2015-09-08 | 2010 | Air Force Active | LJYC003006 |  | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | W912GB09D00690003 | 7880644 | 8179697.2 | 2011-10-18 | 2013-03-30
2015-09-08 | 2008 | Air Force Active | LJYC084001 |  | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970022.5 | 42315654.53 | 2012-10-19 | 2016-09-30
2015-09-08 | 2014 | Air Force Active | LKTC073101 |  | 2014-07-18 | 2014-09-02 | USACE | W81EYN42417577 | 11450000 | 11450000 | 2014-12-01 | 2014-12-01
2015-09-08 | 2014 | Air Force Active | LKTC073101 |  | 2015-03-31 | 2015-08-14 | Penick-Nordic JV | W912PL10D00720003 | 3100312 | 3100312 | 2016-05-28 | 2016-05-28
2015-09-08 | 2011 | Air Force Active | LKTC113102 |  | 2010-12-10 | 2011-06-29 | Jaynes Corporation | W912PL11C0004 | 7345225 | 7478704 | 2013-02-28 | 2014-07-14
2015-09-08 | 2013 | Air Force Active | LKTC133101 |  | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643420 | 10828108 | 2015-08-19 | 2015-08-19
2015-09-08 | 2011 | Air Force Active | LXEZ114127 |  | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621760.1 | 66149551.02 | 2015-11-08 | 2015-11-08
2015-09-08 | 2011 | Air Force Active | LXEZ114127 |  | 2012-03-16 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) ** Appliances** | FA527012FA045 | 319431.6 | 319431.6 | 2012-12-11 | 2012-12-11
2015-09-08 | 2011 | Air Force Active | LXEZ114127 |  | 2012-01-03 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan)*Arch TestDigs* | FA527012P0058 | 50185.53 | 50185.53 | 2012-09-03 | 2012-09-03
2015-09-08 | 2011 | Air Force Active | LXEZ114127 |  | 2012-02-02 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT" | FA527012P0080 | 72005.05 | 72005.05 | 2012-09-24 | 2012-09-24
2015-09-08 | 2011 | Air Force Active | LXEZ114127 |  | 2013-12-13 | 2014-06-11 | OSC Solutions, Inc. (West Palm Beach, FL) **Appliances** | FA527014P0055 | 401356.5 | 401356.5 | 2014-09-09 | 2014-09-09
2015-09-08 | 2011 | Air Force Active | LXEZ114127 |  | 2011-09-21 | 2012-03-19 | OTIE Milwauke, WI; *Title 2 Contract support* | FA890308D87820014 | 1896559 | 1896559 | 2015-08-30 | 2015-08-30
2015-09-08 | 2012 | Air Force Active | LXEZ124285 |  | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706668.55 | 17706668.55 | 2016-05-10 | 2016-05-10
2015-09-08 | 2013 | Air Force Active | LXEZ134286 |  | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698072.72 | 14981191.76 | 2015-11-27 | 2016-02-08
2015-09-08 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288680.72 | 6312847.81 | 2015-08-27 | 2015-11-25
2015-09-08 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202135.96 | 4202135.96 | 2015-12-15 | 2015-12-15
2015-09-08 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473449.62 | 2473449.62 | 2014-07-23 | 2014-07-23
2015-09-08 | 2012 | Air Force Active | MHMV093108 |  | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | W912PP12C0016 | 21110000 | 21590355.25 | 2014-04-30 | 2014-10-23
2015-09-08 | 2014 | Air Force Active | MHMV103105B |  | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285500 | 21563582 | 2016-11-01 | 2016-11-28
2015-09-08 | 2013 | Air Force Active | MPLS083008 |  | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170185 | 17241355 | 2015-07-04 | 2015-07-04
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2012-05-20 | 2012-11-16 | CE-DawsonAlamo JV, LLC (SABER-Comm Cabinets) Pop w/in LB | FA304710D00120046 | 17278.18 | 17278.18 | 2012-12-16 | 2012-12-16
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2013-02-13 | 2013-08-12 | CE-JSR Inc. (SABER-MTI Offices+mod $6,392.52) PoP w/in SB | FA304710D00130003 | 236207.17 | 236207.17 | 2013-09-12 | 2013-09-12
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2010-08-01 | 2011-01-28 | COE-JSR Inc. (SB-Exterior Facilities) | W9126G-09-C-0000 | 6037485 | 6396881.32 | 2012-02-13 | 2012-02-13
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2009-07-09 | 2009-09-17 | COE-BalfourBeattySutterfieldPontikes JV (LB-Main Facilities) | W9126G-09-C-0054 | 46437194 | 54453578.26 | 2011-10-06 | 2012-01-03
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2013-03-18 | 2013-09-14 | COE-JSR Inc. (JOC-Stair Tread-Landing Retrofit) | W9126G12D00180017 | 216683.68 | 216683.68 | 2014-06-21 | 2014-06-21
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2013-04-18 | 2013-10-15 | COE-JSR Inc. (JOC-Running Track/Drill Pad Light) | W9126G12D00180019 | 98681.42 | 98681.42 | 2014-07-11 | 2014-07-11
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2013-06-18 | 2013-12-15 | COE-JSR Inc. (Stair Handrails Retrofit) PoP w/in SB | W9126G12D00180025 | 79753.46 | 79753.46 | 2014-01-15 | 2014-01-15
2015-09-08 | 2009 | Air Force Active | MPLS083737R1 |  | 2013-03-31 | 2013-09-27 | COE-JSR Inc. (SB-Gary Rd Finishes/FZ Fence Relocation) | W9126G13C00980004 | 86693 | 86693 | 2014-05-15 | 2014-05-15
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-05-09 | 2012-05-29 | AE RabaKistner Consultants-Sidewalk Survey $1865.12 | PNASA1205700 | 1889 | 1889 | 2012-06-09 | 2012-06-09
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2010-12-06 | 2014-11-10 | AE Merrick & Company-Tittle 2 Svs $59,036x3 | W9126G08D00060053 | 177108.46 | 177108.46 | 2015-09-05 | 2015-09-05
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-09-06 | 2012-10-19 | SB FPI, LLC/JSR Inc-Refencing | W9126G11C0009 | 175358.37 | 175358.37 | 2013-06-01 | 2013-06-01
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2010-12-06 | 2011-09-20 | LB SutherfielfPontikes, LLC-Main Facility Construction | W9126G11C0024 | 45885000 | 46365642.93 | 2013-10-31 | 2014-10-31
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2011-09-02 | 2011-11-08 | LB Koonz Brown & Root (DCF2 Ktr)-Free Zone Fence | W9126G11C0027 | 95464 | 95464 | 2011-12-08 | 2011-12-08
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-02-15 | 2014-06-25 | SVS-Am Eagle Protective Svs Corp-Gate Monitor, OY2 | W9126G12C0017P0002 | 100466.59 | 100466.59 | 2015-01-31 | 2015-01-31
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2013-03-18 | 2013-06-03 | SB FPI, LLC/JSR Inc-DCF2s Gary Rd portion 2/3 | W9126G13C0098 | 91850 | 91850 | 2013-11-06 | 2014-01-07
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2014-08-14 | 2014-10-10 | SB Red Cedar Enterprises Inc-Quadrangle Main 3/4 | W9126G14D00190007 | 3102034 | 3102034 | 2015-09-05 | 2015-09-05
2015-09-08 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-05-09 | 2012-08-09 | SB JSR Inc-Exterior Facilties & Grounds | W912BV11C0038 | 6886921 | 7284529.33 | 2014-04-04 | 2014-09-30
2015-09-08 | 2012 | Air Force Active | MPLS083737R4 |  | 2011-12-16 | 2012-10-31 | AE-Merrick&Company (E&D) | W9126G08D00060055 | 400152.76 | 400152.76 | 2013-11-06 | 2014-01-07
2015-09-08 | 2012 | Air Force Active | MPLS083737R4 |  | 2011-12-16 | 2013-07-17 | LB-SpawGlass Contractors, Inc. | W9126G12C0023 | 50528593 | 52394893 | 2014-11-26 | 2015-01-25
2015-09-08 | 2012 | Air Force Active | MPLS083737R4 |  | 2013-03-18 | 2013-06-03 | SB FPI/JSR Inc/DCF2 Ktr - Gary Rd 3/3 | W9126G13C0098 | 91850 | 91850 | 2013-11-06 | 2014-01-07
2015-09-08 | 2012 | Air Force Active | MPLS083737R4 |  | 2014-08-14 | 2014-10-10 | SB Red Cedar Enterprise Inc-Ext Facs/Kneewall/Quad | W9126G14D00190007 | 7301694 | 7301694 | 2016-01-03 | 2016-01-03
2015-09-08 | 2010 | Air Force Active | MPLS083737S1 |  | 2009-12-10 | 2010-02-11 | COE LB Lyda Swinerton (Whole Facility) | W9126G10C0017 | 23483610 | 25785282.23 | 2011-12-26 | 2012-05-10
2015-09-08 | 2010 | Air Force Active | MPLS083737S1 |  | 2010-04-12 | 2010-06-11 | COE SB JSR Inc. (Telecomm Ductbank) | W9126G10C0072 | 1409452 | 1601605.94 | 2011-06-03 | 2011-07-03
2015-09-08 | 2010 | Air Force Active | MPLS083737S1 |  | 2014-07-31 | 2014-09-29 | COE JOC Gideon Cntrg (Handrails/Screening Retrofit) | W9126G14D00570016 | 60931 | 60931 | 2015-09-29 | 2015-09-29
2015-09-08 | 2011 | Air Force Active | MPLS083737S2 |  | 2011-03-07 | 2012-10-31 | Merrick & Company (Tittle II Services) $59,036.40 | W9126G08D00060054 | 118073 | 118073 | 2015-04-24 | 2015-04-24
2015-09-08 | 2011 | Air Force Active | MPLS083737S2 |  | 2011-02-25 | 2011-06-30 | LB-KBR General Contract | W9126G11C0027 | 25985137.96 | 27613986.85 | 2013-04-20 | 2014-11-10
2015-09-08 | 2011 | Air Force Active | MPLS083737S2 |  | 2012-02-15 | 2014-01-16 | AEP Services Corp (Gate Monitor Svs 100K x 2 yrs | W9126G12C00170001 | 202008.24 | 202008.24 | 2015-01-31 | 2015-01-31
2015-09-08 | 2011 | Air Force Active | MPLS083737S2 |  | 2012-12-12 | 2013-06-03 | SB JSR Inc (Gary Rd Realign Pt 2of3) | W9126G13C0098 | 152927 | 155310 | 2014-01-18 | 2014-01-01
2015-09-08 | 2011 | Air Force Active | MPLS083737S2 |  | 2011-03-07 | 2015-04-24 | SB Gideon Contracting | W9126G14D00570019 | 54574.13 | 54574.13 | 2015-04-24 | 2015-04-24
2015-09-08 | 2009 | Air Force Active | MPLS093002 |  | 2013-04-16 | 2013-06-15 | JSR Inc. | FA301612D00050008 | 366514.14 | 375412.48 | 2013-12-27 | 2013-12-27
2015-09-08 | 2009 | Air Force Active | MPLS093002 |  | 2009-07-14 | 2009-08-31 | MAPCO, Inc. | W9126G09D00340002 | 5913251 | 6604890.78 | 2011-02-27 | 2012-11-27
2015-09-08 | 2010 | Air Force Active | MUHJ053008 |  | 2014-07-29 | 2014-09-29 | Homeland Contracting Corporation | F4A0012D00040013 | 231490.98 | 231490.98 | 2015-08-25 | 2015-08-25
2015-09-08 | 2010 | Air Force Active | MUHJ053008 |  | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185824 | 8498082.11 | 2012-01-26 | 2013-07-19
2015-09-08 | 2013 | Air Force Active | NKAK103006 |  | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869000 | 21464974 | 2015-07-23 | 2015-10-28
2015-09-08 | 2013 | Air Force Active | NKAK113003 |  | 2013-12-23 | 2014-02-21 | HGL Construction | FA446011D00075014 | 727000 | 727000 | 2015-02-28 | 2015-02-28
2015-09-08 | 2013 | Air Force Active | NKAK113005 |  | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218502.99 | 4235323.73 | 2015-10-21 | 2015-11-28
2015-09-08 | 2011 | Air Force Active | NUEX093000 |  | 2012-04-18 | 2012-08-30 | Archer Western Contractors | W912PL12C0017 | 43347122 | 48331271.86 | 2014-04-08 | 2015-04-06
2015-09-08 | 2011 | Air Force Active | NUEX093000 |  | 2014-07-27 | 2014-09-27 | KWR Construction, Inc | W912PL14D00300002 | 587608 | 587608 | 2015-01-27 | 2015-01-27
2015-09-08 | 2014 | Air Force Active | NUEX093007 |  | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699907 | 4699907 | 2015-07-07 | 2015-07-07
2015-09-08 | 2014 | Air Force Active | NUEX093011 |  | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513636 | 15698045 | 2016-02-14 | 2016-03-15
2015-09-08 | 2015 | Air Force Active | NUEX103005 |  | 2014-12-16 | 2015-04-30 | SAI-TALON JV | W912PL15C0005 | 13097800 | 13097800 | 2016-11-22 | 2016-11-22
2015-09-08 | 2010 | Air Force Active | NVZR033702 |  | 2010-05-19 | 2010-07-07 | Carothers Construction | W9127807D00260003 | 16517735 | 16824407.2 | 2013-07-26 | 2013-07-26
2015-09-08 | 2010 | Air Force Active | NZAS003000A |  | 2012-04-23 | 2012-11-28 | RSCI | W912DW13C0013 | 9474720 | 9462564 | 2014-11-28 | 2015-07-02
2015-09-08 | 2014 | Air Force Active | PAYZ130011 |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 245125000 | 245125000 | 2016-04-13 | 2016-04-13
2015-09-08 | 2014 | Air Force Active | PAYZ130011 |  | 2012-09-11 | 2015-04-10 | Clark Construction Group, LLC | W912DR15C0008 | 20623200 | 20623200 | 2016-07-30 | 2016-07-30
2015-09-08 | 2014 | Air Force Active | PRQE145117 |  | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924500 | 64191030 | 2016-01-05 | 2016-04-04
2015-09-08 | 2015 | Air Force Active | PRQE145118 |  | 2015-01-26 | 2015-04-03 | Hanke Constructors | W912DQ14D40030001 | 6389509 | 6389509 | 2016-05-04 | 2016-05-04
2015-09-08 | 2014 | Air Force Active | PRQE145121 |  | 2014-03-14 | 2015-03-02 | Aerostar SES, Inc | W912DQ15C4005 | 3061137 | 3061137 | 2016-04-19 | 2016-04-19
2015-09-08 | 2014 | Air Force Active | PRQE145136 |  | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100500 | 8268701 | 2015-12-17 | 2015-12-19
2015-09-08 | 2014 | Air Force Active | PRQE145137 |  | 2014-03-10 | 2014-06-27 | Red Cedar Enterprises, Inc | W912DQ13D40010002 | 838705 | 917758 | 2015-02-28 | 2015-02-28
2015-09-08 | 2014 | Air Force Active | PRQE145138 |  | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976000 | 976000 | 2017-03-10 | 2017-03-10
2015-09-08 | 2014 | Air Force Active | PRQE145142 |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200000 | 25524207 | 2017-01-19 | 2017-01-19
2015-09-08 | 2015 | Air Force Active | PRQE155118 |  | 2015-01-26 | 2015-04-03 | Hanke Constructors | W912DQ14D40030001 | 2286153 | 2286153 | 2016-05-04 | 2016-05-04
2015-09-08 | 2014 | Air Force Active | PRQE155119 |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959000 | 53806382 | 2015-12-26 | 2015-12-26
2015-09-08 | 2014 | Air Force Active | PRQE155122 |  | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306162 | 7315789 | 2015-10-15 | 2015-10-15
2015-09-08 | 2015 | Air Force Active | PRQE155124 |  | 2015-01-26 | 2015-04-17 | K&K Industries, Inc | W912DQ14D40090002 | 5679326 | 5679326 | 2016-11-02 | 2016-11-02
2015-09-08 | 2013 | Air Force Active | QJVF092011 |  | 2012-11-19 | 2013-05-31 | Rolac Contracting, Inc. | W9128F13C0008 | 4376727 | 4260351 | 2014-12-11 | 2014-12-11
2015-09-08 | 2012 | Air Force Active | QJVF092012 |  | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | W9128F12C0013 | 32123257 | 33445233 | 2014-10-09 | 2015-03-09
2015-09-08 | 2014 | Air Force Active | QJVF092013 |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540270 | 9510291 | 2016-01-06 | 2016-01-06
2015-09-08 | 2012 | Air Force Active | QKKA124002 |  | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | W912HV12C0003 | 19550171 | 20354985.64 | 2014-11-28 | 2015-07-15
2015-09-08 | 2013 | Air Force Active | QKKA133001P2 |  | 2013-05-16 | 2013-09-30 | Nishimatsu Construction Co., Ltd | FZ520513C0005 | 13989415.64 | 14084179.55 | 2015-06-21 | 2015-06-21
2015-09-08 | 2013 | Air Force Active | QKKA134001 |  | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336739 | 14750042.74 | 2015-09-23 | 2015-09-23
2015-09-08 | 2014 | Air Force Active | QKKA144002 |  | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302110 | 25302110 | 2017-01-14 | 2017-01-14
2015-09-08 | 2013 | Air Force Active | QSEU103008 |  | 2012-12-07 | 2013-06-28 | IBKI, Inc. Choctaw, MS | W912HN13C0011 | 7692387 | 7808669 | 2015-01-04 | 2015-04-08
2015-09-08 | 2014 | Air Force Active | QSEU123003 |  | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547470 | 1547470 | 2015-11-19 | 2015-11-19
2015-09-08 | 2014 | Air Force Active | RKMF083002 |  | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381000 | 30397469 | 2016-09-28 | 2016-10-05
2015-09-08 | 2012 | Air Force Active | RKMF103003 |  | 2011-11-17 | 2012-04-24 | A4 Construction | W912PL12C0008 | 9326701 | 9655444 | 2014-05-22 | 2014-09-06
2015-09-08 | 2014 | Air Force Active | RKMF103005 |  | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D01130012 | 4829984 | 4829984 | 2016-02-18 | 2016-02-18
2015-09-08 | 2014 | Air Force Active | RKMF103006 |  | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974014 | 7142028.64 | 2016-01-06 | 2016-03-01
2015-09-08 | 2014 | Air Force Active | RKMF103009 |  | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066000 | 8450619 | 2015-12-16 | 2015-12-31
2015-09-08 | 2012 | Air Force Active | RKMF103010 |  | 2011-11-17 | 2012-05-24 | Au Authum KI, Inc | W912PL10D01090001 | 1866780 | 1866780 | 2014-11-21 | 2014-11-21
2015-09-08 | 2014 | Air Force Active | RKMF113005 |  | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922700 | 14938360 | 2016-08-01 | 2016-08-01
2015-09-08 | 2015 | Air Force Active | RKMF133001 |  | 2015-01-22 | 2015-06-12 | CTI | W912PL15C0010 | 11361000 | 11361000 | 2017-01-19 | 2017-01-19
2015-09-08 | 2015 | Air Force Active | SAKW059006 |  | 2014-11-07 | 2015-03-07 | P&S Construction Inc | N4019210D28040025 | 2841600 | 2841600 | 2016-04-10 | 2016-04-10
2015-09-08 | 2012 | Air Force Active | SAKW059101 |  | 2011-12-30 | 2012-04-28 | Pacific West Builders | N4019210D28100003 | 9490730 | 9433610 | 2013-10-23 | 2014-10-15
2015-09-08 | 2014 | Air Force Active | SAKW113003 |  | 2014-01-23 | 2015-03-06 | P&S Construction Inc | N4019210D28040023 | 7050506.3 | 7050506.3 | 2016-07-08 | 2016-07-08
2015-09-08 | 2015 | Air Force Active | SAKW113008 |  | 2015-03-20 | 2015-06-30 | GSI-EA JV, LLC | N4019210D28090004 | 3586194 | 3586194 | 2016-06-21 | 2016-06-21
2015-09-08 | 2014 | Air Force Active | SAKW133005 |  | 2014-03-04 | 2015-03-05 | P & S Construction | N4019210D2804KB01 | 3587000 | 3587000 | 2017-02-06 | 2017-02-06
2015-09-08 | 2015 | Air Force Active | SAKW143031 |  | 2014-12-05 | 2015-03-06 | P&S Construction Inc | N4019210D28040024 | 6205000 | 6205000 | 2016-07-30 | 2016-07-30
2015-09-08 | 2012 | Air Force Active | SGBP100904C |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 524445324 | 534179793.95 | 2016-09-10 | 2016-09-12
2015-09-08 | 2011 | Air Force Active | SXHT053001 |  | 2013-12-03 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99768 | 99768 | 2014-09-30 | 2014-09-30
2015-09-08 | 2011 | Air Force Active | SXHT053001 |  | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231044.9 | 147800203.93 | 2015-12-02 | 2015-12-02
2015-09-08 | 2012 | Air Force Active | TMKH083003 |  | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | W912HN10D00630003 | 4630000 | 5033217.47 | 2014-01-15 | 2015-06-23
2015-09-08 | 2010 | Air Force Active | TYFR053037 |  | 2012-01-27 | 2012-06-15 | D & b Bau GmbH, Neustadt | W912GB-09-C0022 | 5745698.59 | 5997071.19 | 2013-07-06 | 2013-07-17
2015-09-08 | 2011 | Air Force Active | TYFR083001 |  | 2012-05-10 | 2012-09-26 | Peter Gross GmbH | W912GB-10-C-0001A | 2140702 | 2253365.66 | 2013-05-19 | 2013-05-19
2015-09-08 | 2008 | Air Force Active | TYFR084014 |  | 2013-01-25 | 2013-05-17 | MICKAN | C07-1003 | 4638820.2 | 4458133.41 | 2014-06-23 | 2014-12-18
2015-09-08 | 2008 | Air Force Active | TYFR084034 |  | 2008-08-04 | 2008-09-18 | LBB Kaiserslautern EBC | W912GB-08-C-0001 | 45686722.4 | 46119859.87 | 2010-12-01 | 2010-12-01
2015-09-08 | 2011 | Air Force Active | TYFR106261 |  | 2013-09-13 | 2013-11-13 | MICKAN | C11-4014 | 1840288.83 | 1840288.83 | 2014-12-12 | 2014-12-12
2015-09-08 | 2011 | Air Force Active | TYFR123063 |  | 2013-08-12 | 2013-11-13 | OBG Hochbau GmbH & Co. KG | W912GB10C0002 | 6163595.4 | 6561859.3 | 2014-11-06 | 2014-11-06
2015-09-08 | 2013 | Air Force Active | TYFR126175 |  | 2014-01-21 | 2014-07-23 | MICKAN Generalbau | C124019 | 1664151.13 | 1664151.13 | 2015-02-24 | 2015-02-24
2015-09-08 | 2011 | Air Force Active | TYFU083507R2 |  | 2013-08-30 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | 16251895.59 | 16251895.59 | 2015-07-15 | 2015-07-15
2015-09-08 | 2014 | Air Force Active | UHHZ123001 |  | 2014-08-01 | 2015-01-15 | Garbutt Construction Company | W912HN10D00340002 | 1779360.63 | 1779360.63 | 2016-05-11 | 2016-05-11
2015-09-08 | 2012 | Air Force Active | USAFE17001 |  | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | N3319109D01200011 | 6740135 | 6640535 | 2013-01-27 | 2015-01-07
2015-09-08 | 2012 | Air Force Active | USAFE17002 |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421000 | 43761850.4 | 2014-01-16 | 2015-08-15
2015-09-08 | 2012 | Air Force Active | USAFE17003 |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521530 | 10521530 | 2014-05-24 | 2014-05-24
2015-09-08 | 2012 | Air Force Active | USAFE17004 |  | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587915 | 27299359 | 2014-04-13 | 2015-01-27
2015-09-08 | 2008 | Air Force Active | VLSB083007 |  | 2008-07-31 | 2008-09-29 | Prime Ktr Golf Course CNS (Phase 1) | N6945008C2846 | 2771874 | 2827760 | 2009-09-29 | 2009-09-29
2015-09-08 | 2008 | Air Force Active | VLSB083007 |  | 2011-04-11 | 2011-06-10 | J2 Engineering (Phase 2) | N6945008D17820005 | 3446432 | 5339270.5 | 2012-10-10 | 2014-01-30
2015-09-08 | 2008 | Air Force Active | VLSB083007 |  | 2015-05-24 | 2015-07-23 | Bell & Carrington | W912HN15P0034 | 7320 | 7320 | 2017-07-22 | 2017-07-22
2015-09-08 | 2008 | Air Force Active | VLSB083007 |  | 2015-05-29 | 2015-07-28 | Property Solutions, LLC | W912HN15P0036 | 14350 | 14350 | 2017-01-18 | 2017-01-18
2015-09-08 | 2011 | Air Force Active | VYHK113003 |  | 2012-04-16 | 2012-07-31 | UVB BITBURG | 113003 | 1762200 | 1762200 | 2013-04-12 | 2013-04-12
2015-09-08 | 2012 | Air Force Active | WACC120007 |  | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | W9123608D00140003 | 33915149 | 34116778.35 | 2014-10-04 | 2014-10-29
2015-09-08 | 2014 | Air Force Active | WWCX103028 |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817608.89 | 39817608.89 | 2016-08-08 | 2016-08-08
2015-09-08 | 2013 | Air Force Active | WWCX103032 |  | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031649 | 24018115.04 | 2015-07-29 | 2015-07-29
2015-09-08 | 2013 | Air Force Active | WWYK120123A |  | 2013-03-06 | 2013-05-23 | Southwind Construction | W912BV12D00180003 | 1525212 | 1573679 | 2015-08-03 | 2015-08-03
2015-09-08 | 2014 | Air Force Active | WWYK143004A |  | 2015-01-27 | 2015-03-13 | BNJ Builders of Oklahoma City | W912BV11D00130007 | 496781 | 496781 | 2015-05-19 | 2015-05-19
2015-09-08 | 2013 | Air Force Active | XLWU103002 |  | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 12555018 | 13739178 | 2015-08-11 | 2016-02-29
2015-09-08 | 2014 | Air Force Active | XLWU103007 |  | 2015-03-10 | 2015-04-14 | Southeast Cherokee Construction | W9127810D00780009 | 9094468 | 9094468 | 2016-11-11 | 2016-11-11
2015-09-08 | 2011 | Air Force Active | XQPZ084017 |  | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995500 | 25471490 | 2014-09-29 | 2015-01-16
2015-09-08 | 2014 | Air Force Active | XQPZ124003 |  | 2014-12-03 | 2015-03-25 | John Bowman Incorporated (JBI) | W9128F12D00370011 | 1581000 | 1581000 | 2015-12-09 | 2015-12-09
2015-09-08 | 2010 | Air Force Active | XTLF033303 |  | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849633 | 9592033.15 | 2012-02-12 | 2012-06-29
2015-09-08 | 2012 | Air Force Active | YWHG071005 |  | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172600 | 4308791.16 | 2013-09-07 | 2014-08-15
2015-09-08 | 2012 | Air Force Active | YWHG111005 |  | 2012-06-01 | 2012-08-23 | Titan Construction Organizatio | W912DQ11D40150001 | 5388481 | 5625923 | 2013-09-07 | 2014-04-29
2015-09-08 | 2012 | Air Force Active | YWHG111005 |  | 2013-08-23 | 2013-12-18 | Mack Mechanical, Inc. | W912DQ14C4000 | 1814472 | 1895345 | 2014-09-24 | 2014-10-22
2015-09-08 | 2014 | Air Force Active | YWHG111010 |  | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817700 | 3828847 | 2015-12-04 | 2016-01-10
2015-09-08 | 2014 | Air Force Active | ZHTV053302 |  | 2015-03-11 | 2015-06-23 | Messer Construction | W912QR15C0012 | 24166000 | 24166000 | 2017-06-02 | 2017-06-02
2015-09-08 | 2012 | Air Force Reserve | DKFX079003 |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149000 | 9004770 | 2013-07-13 | 2014-03-09
2015-09-08 | 2013 | Air Force Reserve | KYJM129022 |  | 2013-06-07 | 2013-09-23 | CCI | W9127810D01180020 | 1552029 | 1591601.93 | 2014-09-26 | 2014-10-26
2015-09-08 | 2013 | Air Force Reserve | RVKQ099095 |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242986 | 5242986 | 2016-01-15 | 2016-01-15
2015-09-08 | 2012 | Air Force Reserve | RVKQ120572 |  | 2013-01-04 | 2014-08-22 | Oddo Construction Services | FA667014C0002 | 2087131 | 2087131 | 2016-03-15 | 2016-03-15
2015-09-08 | 2013 | Air National Guard | ATQZ099073 |  | 2014-05-29 | 2014-12-08 | E & B Paving, Inc | W912L91322101 | 1498405.16 | 1498405.16 | 2016-05-21 | 2015-08-31
2015-09-08 | 2012 | Air National Guard | ATQZ099080 |  | 2014-05-10 | 2014-08-27 | Patterson Horth, Inc. | W912L910D00090055 | 4241000 | 4241000 | 2015-11-20 | 2015-12-31
2015-09-08 | 2012 | Air National Guard | AXQD119004 |  | 2013-04-10 | 2013-07-12 | Cornerstone Construction Svs | W912SV10D00080004 | 1240639 | 1240639 | 2014-02-07 | 2015-02-28
2015-09-08 | 2012 | Air National Guard | AXQD129074 |  | 2014-09-12 | 2014-12-15 | Cutter Enterprises LLC | W912SV15C0001 | 1680218 | 1680218 | 2016-07-16 | 2016-06-17
2015-09-08 | 2011 | Air National Guard | BKTZ069078 |  | 2013-09-20 | 2013-11-21 | Codell Construction Company | W912L710D00060037 | 6600865.11 | 6600865.11 | 2014-10-17 | 2015-04-15
2015-09-08 | 2014 | Air National Guard | BRKR999147 |  | 2014-04-02 | 2014-08-13 | Southeast Cherokee Conwstruction, Inc | W912JA14C0001 | 8201275 | 8201275 | 2016-10-23 | 2016-08-02
2015-09-08 | 2015 | Air National Guard | CEKT139004 |  | 2015-02-17 | 2015-06-03 | Cutter Enterprises, LLC | W91ZRS15C0002 | 14859726 | 14859726 | 2016-12-05 | 2016-12-23
2015-09-08 | 2013 | Air National Guard | DPEZ089017 |  | 2013-08-28 | 2013-09-27 | Faith Enterprises | W912L313D00030001 | 5389532 | 5389532 | 2015-03-21 | 2015-11-27
2015-09-08 | 2011 | Air National Guard | DPEZ089083 |  | 2011-07-18 | 2012-04-11 | Recco, Inc. | W912L312C0003 | 1694655.8 | 1694655.8 | 2012-10-22 | 2015-05-29
2015-09-08 | 2011 | Air National Guard | FAKZ959574 |  | 2011-03-15 | 2011-07-22 | Lord and Son Constrution, Inc | W912JA11C0005 | 7558800 | 7558800 | 2013-01-22 | 2015-08-31
2015-09-08 | 2013 | Air National Guard | FJRP079016 |  | 2013-12-23 | 2014-04-07 | Showalter Construction | W9124209D0013N908 | 1281980 | 1281980 | 2015-03-03 | 2015-06-01
2015-09-08 | 2012 | Air National Guard | FKNN049094 |  | 2012-05-16 | 2012-09-12 | Cornerstone Construction | W912JD11D00070003 | 1306934.3 | 1306934.3 | 2013-03-18 | 2014-11-14
2015-09-08 | 2011 | Air National Guard | FPBB109013 |  | 2012-07-27 | 2012-10-17 | Black Horse Group | W912PQ12D00130003 | 2130798 | 2130798 | 2013-10-12 | 2014-10-20
2015-09-08 | 2014 | Air National Guard | FPBB129050 |  | 2014-07-17 | 2014-09-08 | R.J. Ortlieb | W912PQ12D00100008 | 4895886 | 4895886 | 2015-08-04 | 2015-09-21
2015-09-08 | 2014 | Air National Guard | GJKZ129093 |  | 2014-04-22 | 2014-08-12 | Pacific Tech Construction | W912K311D00030005 | 1758438.79 | 1758438.79 | 2015-03-17 | 2015-09-23
2015-09-08 | 2013 | Air National Guard | HAYW109006 |  | 2014-08-15 | 2014-10-26 | Cooper Chase | W912LA11D00040002 | 1261072.69 | 1261072.69 | 2016-02-25 | 2016-01-20
2015-09-08 | 2013 | Air National Guard | HAYW109006 |  | 2013-08-23 | 2013-09-27 | RS Morris Construction | W912LA11D00180010 | 4072484.43 | 4072484.43 | 2015-01-25 | 2015-07-10
2015-09-08 | 2013 | Air National Guard | HAYW109006 |  | 2013-08-23 | 2013-09-30 | RS Morris Cosntruction | W912LA11D00180011 | 2537752.69 | 2537752.69 | 2015-01-25 | 2015-06-23
2015-09-08 | 2011 | Air National Guard | HFHA069130 |  | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | W912L213C0001 | 10245000 | 10245000 | 2014-06-02 | 2015-09-25
2015-09-08 | 2014 | Air National Guard | JKSE129321 |  | 2014-09-24 | 2014-11-07 | Wadsworth Builders Co., Inc. | W9124V12D00090008 | 1261466.27 | 1261466.27 | 2015-10-03 | 2015-09-03
2015-09-08 | 2014 | Air National Guard | JKSE129321 |  | 2014-07-15 | 2014-10-28 | Guy Tabacco Construction Co.. | W9124V12D00110003 | 1441500 | 1441500 | 2015-09-13 | 2015-09-13
2015-09-08 | 2014 | Air National Guard | JKSE129321 |  | 2014-06-11 | 2014-09-16 | James Talcott Construction Inc | W9124V14C0004 | 20869050.39 | 20869050.39 | 2016-10-15 | 2016-09-15
2015-09-08 | 2012 | Air National Guard | KJAQ119031 |  | 2013-10-08 | 2014-01-29 | Anthem Builders, Inc | W912JV14C0002 | 1799954 | 1799954 | 2014-11-10 | 2015-09-25
2015-09-08 | 2011 | Air National Guard | KNMD069209 |  | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | W912J611C0002 | 42025000 | 42025000 | 2013-07-14 | 2015-01-30
2015-09-08 | 2011 | Air National Guard | KNMD069209 |  | 2015-06-04 | 2015-07-06 | Talion Construction | W912J613D00260002 | 300571 | 300571 | 2016-02-01 | 2016-01-11
2015-09-08 | 2012 | Air National Guard | KNMD069212 |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C0003 | 19896776.72 | 19896776.72 | 2014-06-07 | 2014-11-25
2015-09-08 | 2012 | Air National Guard | KNMD069213 |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | W912J612C0003 | 7405807.08 | 7405807.08 | 2014-06-07 | 2014-11-25
2015-09-08 | 2012 | Air National Guard | KNMD069216 |  | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | W9128A12C0007 | 10601446 | 10601446 | 2013-08-08 | 2015-03-29
2015-09-08 | 2012 | Air National Guard | KNMD069216 |  | 2013-03-04 | 2013-09-12 | Nan, Inc | W912J613C0006 | 2000000 | 2000000 | 2015-03-29 | 2015-06-24
2015-09-08 | 2011 | Air National Guard | KNMD109032 |  | 2012-01-04 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C0003 | 1798720.94 | 1798720.94 | 2014-06-07 | 2014-11-25
2015-09-08 | 2013 | Air National Guard | KNMD119001 |  | 2013-03-04 | 2013-09-12 | Nan Inc. | W912J613C0006 | 5593905.24 | 5593905.24 | 2015-04-24 | 2015-09-30
2015-09-08 | 2014 | Air National Guard | LDXF099060 |  | 2014-07-30 | 2014-09-22 | Patterson-Horth | W912L914D00110002 | 7071641 | 7071641 | 2016-02-28 | 2016-06-30
2015-09-08 | 2014 | Air National Guard | LKLW109037 |  | 2014-08-06 | 2014-09-25 | Lobar Associates | W912KC14C0008 | 7039937.69 | 7039937.69 | 2015-10-25 | 2015-10-25
2015-09-08 | 2011 | Air National Guard | LSGA029009A |  | 2010-11-12 | 2011-06-06 | Americaan Patriot Construction -IMC, LLC | W911YN11C0003 | 4166570.24 | 4166570.24 | 2012-12-03 | 2015-06-08
2015-09-08 | 2015 | Air National Guard | MBMV129060 |  | 2015-03-01 | 2015-04-15 | Beckering Construction | W912JB15C2007 | 5952943 | 5952943 | 2016-05-14 | 2016-05-06
2015-09-08 | 2013 | Air National Guard | MHMV119001 |  | 2013-05-22 | 2013-10-10 | K.L. HOUSE CONSTRUCTION CO. | W912J314C1001 | 4814602.21 | 4814602.21 | 2015-01-27 | 2015-07-21
2015-09-08 | 2011 | Air National Guard | PJMS909928 |  | 2011-08-17 | 2011-09-28 | Costello Construction of MD, Inc. | W912K611C0016 | 12358949 | 12358949 | 2013-10-18 | 2015-09-30
2015-09-08 | 2014 | Air National Guard | PSTE129092 |  | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W9124209D0003S401 | 1813699.86 | 1813699.86 | 2014-12-24 | 2015-07-31
2015-09-08 | 2014 | Air National Guard | PSXE109034 |  | 2014-04-15 | 2014-07-01 | Howard Pence, Inc | W912L714C0004 | 17303286.84 | 17303286.84 | 2016-07-21 | 2016-07-20
2015-09-08 | 2012 | Air National Guard | QMSN019029 |  | 2012-08-05 | 2012-09-26 | Flintco Construction | W912LA12C7025 | 26004068.23 | 26004068.23 | 2014-02-23 | 2015-03-13
2015-09-08 | 2012 | Air National Guard | SPBN079047 |  | 2013-05-08 | 2013-08-29 | Maron Construction Co. | W912SV13C0003 | 8178006 | 8178006 | 2014-09-24 | 2015-09-04
2015-09-08 | 2012 | Air National Guard | TQKD129072 |  | 2014-03-25 | 2014-07-22 | Total Site Services | W912JV14C0006 | 1802993.84 | 1802993.84 | 2015-03-19 | 2015-09-15
2015-09-08 | 2013 | Air National Guard | TQKD139018 |  | 2014-10-09 | 2014-12-16 | Port of Portland | W912JV1422150 | 130000 | 130000 | 2015-08-01 | 2015-09-15
2015-09-08 | 2013 | Air National Guard | TQKD139018 |  | 2014-11-03 | 2015-01-20 | Andrews Contracting Services | W912JV15C0001 | 912772.22 | 912772.22 | 2015-07-09 | 2015-08-01
2015-09-08 | 2012 | Air National Guard | TUMR109004 |  | 2013-04-30 | 2013-09-26 | R.B. Construction Group, Inc. | W912LR13C0001 | 1500000 | 1500000 | 2015-10-06 | 2015-10-14
2015-09-08 | 2014 | Air National Guard | TWLR129077 |  | 2014-07-25 | 2014-11-14 | MARON CONSTRUCTION CO., INC. | W912LD15C0001 | 6315747 | 6315747 | 2015-12-14 | 2015-11-14
2015-09-08 | 2014 | Air National Guard | ULYB112022 |  | 2014-07-30 | 2014-09-12 | E.L.Crawford Construction | W912NS14D00160002 | 1954163 | 1954163 | 2015-10-12 | 2016-05-05
2015-09-08 | 2014 | Air National Guard | WAAR109002 |  | 2014-07-02 | 2014-08-20 | AWA/Megen Joint Venture LLC | W9136414C0011 | 5944120.68 | 5944120.68 | 2015-12-01 | 2016-01-08
2015-09-08 | 2012 | Air National Guard | WAAR129078 |  | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | W9136413D00050002 | 1793652 | 1793652 | 2014-02-23 | 2015-12-31
2015-09-08 | 2011 | Air National Guard | WEFM089029 |  | 2011-04-19 | 2011-08-26 | DOT Construction | W9124209D00010904 | 1757761 | 1757761 | 2012-07-21 | 2015-07-01
2015-09-08 | 2011 | Air National Guard | WHAY089079 |  | 2011-07-30 | 2011-09-23 | APS Contractors Inc. | W912PQ11C0048 | 14041835 | 14041835 | 2013-05-05 | 2015-09-25
2015-09-08 | 2012 | Air National Guard | WKVB099052 |  | 2014-12-04 | 2015-03-25 | Regiment | W912PQ15C0003 | 2021340 | 2021340 | 2016-04-23 | 2016-06-28
2015-09-08 | 2013 | Air National Guard | WYTD139000 |  | 2014-02-05 | 2014-06-12 | K & T Construction and Supply, Inc | W9136413D00220007 | 1623818 | 1623818 | 2015-04-04 | 2015-09-30
2015-09-08 | 2012 | Air National Guard | XDQU129062 |  | 2012-05-24 | 2012-08-17 | Tyler Construction Group, Inc. | W912JM10D00040001 | 1499785.75 | 1499785.75 | 2013-02-13 | 2014-10-28
2015-09-08 | 2014 | Air National Guard | XHZG129946 |  | 2014-06-25 | 2014-08-20 | Magnum Constrution | W912L611D00010029 | 1979359 | 1979359 | 2015-08-15 | 2015-08-20
2015-09-08 | 2015 | Air National Guard | ZAWA159061 |  | 2015-03-01 | 2015-06-30 | Senate Builders | W912KC10D00170029 | 4185000 | 4185000 | 2016-02-15 | 2016-01-26
2015-09-10 | 2012 | Army Active | 1235 |  | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23139000 | 23149000 | 2014-04-10 | 2014-05-27
2015-09-10 | 2012 | Army Active | 2728 | 130 | 2011-12-09 | 2014-07-02 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 727000 | 727000 | 2016-09-09 | 2016-09-09
2015-09-10 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 11660000 | 11694000 | 2016-09-09 | 2016-09-09
2015-09-10 | 2012 | Army Active | 5034 |  | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603000 | 13268000 | 2014-07-18 | 2015-08-09
2015-09-10 | 2013 | Army Active | 5924 |  | 2013-01-22 | 2013-06-14 | Howard W. Pence, Inc. | W912QR-13-C-0020 | 3918000 | 3948000 | 2014-09-24 | 2014-11-22
2015-09-10 | 2012 | Army Active | 17220 |  | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12623000 | 12866000 | 2015-11-11 | 2016-02-02
2015-09-10 | 2012 | Army Active | 20697 |  | 2012-01-27 | 2012-08-30 | Liberty Mutual Insurance Company | W912BV-12-C-0018 | 13000000 | 13099000 | 2014-01-28 | 2014-01-28
2015-09-10 | 2013 | Army Active | 33771 | 243 | 2013-07-17 | 2014-09-03 | VISTA Construction LLC | W91236-14-C-0043 | 4055000 | 4055000 | 2015-10-15 | 2015-10-15
2015-09-10 | 2013 | Army Active | 33771 | 244 | 2013-07-17 | 2015-01-14 | Doyon Management Services, LLC | W91236-15-C-0017 | 14297000 | 14297000 | 2015-10-15 | 2015-10-15
2015-09-10 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650000 | 46545000 | 2015-10-15 | 2015-10-15
2015-09-10 | 2013 | Army Active | 51519 | 246 | 2013-05-16 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 2019000 | 2019000 | 2015-02-15 | 2015-08-04
2015-09-10 | 2013 | Army Active | 51519 |  | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959000 | 7227000 | 2015-02-15 | 2015-08-04
2015-09-10 | 2014 | Army Active | 51868 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 55619000 | 55956000 | 2016-12-26 | 2017-01-09
2015-09-10 | 2011 | Army Active | 52269 |  | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | W9128A-11-C-0016 | 25313000 | 43715000 | 2014-07-16 | 2015-05-22
2015-09-10 | 2011 | Army Active | 53555 | 57 | 2011-05-24 | 2011-12-09 | H-S Joint Venture, LLC | W91236-10-D-0011 | 10469000 | 10491000 | 2014-01-29 | 2015-04-18
2015-09-10 | 2011 | Army Active | 53555 | 58 | 2011-05-24 | 2011-09-16 | Atlantic Marine Construction Company, Inc | W912HN-07-D-0025 | 1158000 | 1210000 | 2014-01-29 | 2015-04-18
2015-09-10 | 2011 | Army Active | 53555 | 59 | 2011-05-24 | 2013-04-15 | Barnhill Contracting Company | W912HN-09-D-0045 | 68000 | 68000 | 2014-01-29 | 2015-04-18
2015-09-10 | 2011 | Army Active | 53555 | 60 | 2011-05-24 | 2011-09-19 | Polote Corp. | W912HN-10-D-0061 | 10869000 | 11295000 | 2014-01-29 | 2015-04-18
2015-09-10 | 2011 | Army Active | 53555 |  | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | W912HN-11-C-0013 | 15752000 | 16699000 | 2014-01-29 | 2015-04-18
2015-09-10 | 2014 | Army Active | 53584 |  | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036000 | 40304000 | 2017-07-05 | 2017-07-05
2015-09-10 | 2012 | Army Active | 53637 | 135 | 2012-02-21 | 2012-06-07 | Bristol General Contractors, LLC | W912DW-12-C-0032 | 19375000 | 21818000 | 2014-06-11 | 2015-03-12
2015-09-10 | 2012 | Army Active | 53637 | 136 | 2012-02-21 | 2012-11-09 | Megen Construction Co., INC. | W912HN-11-D-0047 | 14398000 | 14928000 | 2014-06-11 | 2015-03-12
2015-09-10 | 2012 | Army Active | 53637 |  | 2012-02-21 | 2012-06-14 | Archer Western Contractors, Ltd | W9126G-08-D-0046 | 14691000 | 14795000 | 2014-06-11 | 2015-03-12
2015-09-10 | 2011 | Army Active | 53789 |  | 2013-07-23 | 2013-09-30 | Halbert Construction Company, Inc. | W91238-13-C-0012 | 18519000 | 27700000 | 2015-01-05 | 2016-02-17
2015-09-10 | 2011 | Army Active | 53794 | 63 | 2011-07-15 | 2012-04-16 | H-S JOINT VENTURE, LLC | W91236-10-D-0011 | 10187000 | 11210000 | 2013-08-04 | 2014-12-18
2015-09-10 | 2011 | Army Active | 53794 | 64 | 2011-07-15 | 2012-07-03 | LIFECYCLE CONSTRUCTION SERVICES | W912HP-11-D-0016 | 2731000 | 2757000 | 2013-08-04 | 2014-12-18
2015-09-10 | 2011 | Army Active | 53794 |  | 2011-07-15 | 2011-08-30 | W. G. YATES & SONS CONSTRUCTION COMPANY | W9126G-09-D-0018 | 20250000 | 25608000 | 2013-08-04 | 2014-12-18
2015-09-10 | 2009 | Army Active | 53874 |  | 2009-07-31 | 2012-05-22 | LBB Kaiserslautern | W912GB-09-C-0036 | 5289000 | 6145000 | 2014-03-19 | 2014-04-11
2015-09-10 | 2014 | Army Active | 54106 |  | 2013-12-24 | 2014-05-28 | TSS-Garco Joint Venture | W912DW-14-C-0012 | 7716000 | 7731000 | 2016-02-09 | 2016-02-09
2015-09-10 | 2013 | Army Active | 54489 | 248 | 2013-04-11 | 2013-05-31 | Donald Maggi, Inc. | W912DQ-13-C-4010 | 11711000 | 12319000 | 2015-09-12 | 2015-10-16
2015-09-10 | 2013 | Army Active | 54489 |  | 2013-04-11 | 2013-08-15 | Caddell Construction Co. (DE), LLC | W912DQ-13-C-4024 | 33360000 | 34389000 | 2015-09-12 | 2015-10-16
2015-09-10 | 2008 | Army Active | 54785 |  | 2010-12-13 | 2011-08-05 | ASSET Group, Inc. | W9127S-11-C-6011 | 7835000 | 7946000 | 2013-01-25 | 2014-12-21
2015-09-10 | 2013 | Army Active | 55121 |  | 2014-10-21 | 2015-07-31 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 40866000 | 40866000 | 2017-11-28 | 2017-11-28
2015-09-10 | 2012 | Army Active | 55823 |  | 2012-04-12 | 2012-07-26 | Big-D Construction Corp | W91238-12-C-0024 | 22609000 | 29930000 | 2015-02-15 | 2015-12-04
2015-09-10 | 2012 | Army Active | 55985 |  | 2012-01-10 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15916000 | 16207000 | 2016-03-23 | 2016-03-23
2015-09-10 | 2011 | Army Active | 56024 |  | 2012-06-29 | 2012-09-25 | Nan, Inc. | W9128A-12-C-0019 | 21105000 | 22708000 | 2014-10-14 | 2015-04-26
2015-09-10 | 2012 | Army Active | 56425 |  | 2012-08-20 | 2012-09-29 | Souza Construction, Inc. | W91238-10-D-0010 | 2996000 | 3163000 | 2013-11-06 | 2014-05-11
2015-09-10 | 2011 | Army Active | 57317 | 67 | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | W912HN-11-C-0013 | 13850000 | 14717000 | 2014-01-29 | 2015-01-09
2015-09-10 | 2011 | Army Active | 57317 |  | 2011-05-24 | 2011-09-19 | Polote Corp. | W912HN-10-D-0061 | 3908000 | 4025000 | 2014-01-29 | 2015-01-09
2015-09-10 | 2012 | Army Active | 57508 |  | 2013-03-15 | 2013-07-22 | Hensel Phelps Construction Co. | W912DR-13-C-0035 | 39700000 | 44869000 | 2015-03-12 | 2015-11-08
2015-09-10 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565000 | 28253000 | 2015-10-05 | 2015-12-19
2015-09-10 | 2011 | Army Active | 57595 | 69 | 2015-05-07 | 2015-06-01 | Argo Systems LLC | W912DR-14-D-0019 | 734000 | 734000 | 2015-12-22 | 2015-12-22
2015-09-10 | 2011 | Army Active | 57595 |  | 2015-05-07 | 2011-08-08 | Lebolo-Watts Constructors 01 JV LLC | W912DR-11-C-0033 | 18392000 | 21010000 | 2015-12-22 | 2015-12-22
2015-09-10 | 2011 | Army Active | 57735 |  | 2011-12-21 | 2012-04-25 | Dynamic Construction of Northern New York, LLC | W912DS-12-C-0008 | 6675000 | 6946000 | 2014-02-22 | 2014-10-21
2015-09-10 | 2013 | Army Active | 57794 |  | 2012-12-26 | 2013-05-10 | Caddell Construction Co. (DE), LLC | W912HN-10-D-0044 | 19523000 | 19721000 | 2015-04-30 | 2015-07-06
2015-09-10 | 2012 | Army Active | 58005 |  | 2011-12-22 | 2012-04-17 | Black Horse Group LLC | W912DS-09-D-0004 | 4681000 | 4801000 | 2013-08-15 | 2014-11-14
2015-09-10 | 2012 | Army Active | 58046 |  | 2012-06-29 | 2013-04-01 | TSS-Garco Joint Venture | W912DW-12-C-0043 | 16416000 | 16346000 | 2014-11-12 | 2015-02-08
2015-09-10 | 2012 | Army Active | 58207 |  | 2011-11-29 | 2012-03-26 | McAlester Contract | DIRECT LABOR | 6324000 | 6324000 | 2013-10-06 | 2013-10-06
2015-09-10 | 2012 | Army Active | 58537 |  | 2011-11-21 | 2012-05-23 | Zachry Federal Construction Corporation | W912BV-12-C-0010 | 32234000 | 33080000 | 2014-03-26 | 2014-05-25
2015-09-10 | 2010 | Army Active | 58625 |  | 2009-10-09 | 2010-02-05 | Harkins Builders, Inc. | W912DR-10-C-0068 | 11717000 | 19350000 | 2012-09-01 | 2015-11-11
2015-09-10 | 2008 | Army Active | 58784 | 4 | 2012-02-02 | 2009-01-29 | Hanwha Engr. & Corporation Co., Ltd. | W912UM-09-C-0009 | 17815000 | 18941000 | 2014-09-07 | 2015-06-09
2015-09-10 | 2008 | Army Active | 58784 | 5 | 2012-02-02 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | W912UM-12-C-0057 | 5458000 | 6193000 | 2014-09-07 | 2015-06-09
2015-09-10 | 2008 | Army Active | 58784 |  | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32469000 | 35297000 | 2014-09-07 | 2015-06-09
2015-09-10 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2014-09-05 | DBA ARGE JV PGWM NETCOM | W912GB-14-C-0037 | 29010000 | 29233000 | 2016-07-07 | 2016-07-07
2015-09-10 | 2013 | Army Active | 58970 |  | 2013-04-29 | 2013-10-30 | ACC Construction Co., Inc | W912HP-14-C-0003 | 21786000 | 22001000 | 2015-05-28 | 2015-08-22
2015-09-10 | 2011 | Army Active | 59044 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270000 | 115589000 | 2015-11-14 | 2015-11-14
2015-09-10 | 2012 | Army Active | 59148 | 148 | 2012-02-01 | 2014-05-15 | Zieson Construction Company, LLC | W912DQ-13-D-4002 | 9000 | 9000 | 2014-10-10 | 2014-10-10
2015-09-10 | 2012 | Army Active | 59148 |  | 2012-02-01 | 2012-03-23 | Alexander-Weitz JV | W912DQ-11-D-4012 | 3901000 | 3998000 | 2014-10-10 | 2014-10-10
2015-09-10 | 2011 | Army Active | 59434 |  | 2010-12-01 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0040 | 14482000 | 15200000 | 2014-11-28 | 2014-11-28
2015-09-10 | 2012 | Army Active | 59581 |  | 2011-10-13 | 2012-01-27 | Watts Constructors, LLC | W9128A-12-C-0001 | 28300000 | 30397000 | 2013-12-14 | 2014-09-16
2015-09-10 | 2013 | Army Active | 59626 |  | 2013-05-31 | 2013-08-23 | NEU Security Services, LLC | W9128F-13-C-0016 | 14080000 | 16109000 | 2015-03-12 | 2015-08-06
2015-09-10 | 2011 | Army Active | 60285 | 74 | 2010-10-07 | 2014-12-09 | Romero General Construction Corp. | W91238-13-D-0009 | 441000 | 441000 | 2015-07-14 | 2015-07-14
2015-09-10 | 2011 | Army Active | 60285 |  | 2010-10-07 | 2011-05-18 | RQ Construction, LLC | W91238-11-C-0005 | 29886000 | 33123000 | 2015-07-14 | 2015-07-14
2015-09-10 | 2011 | Army Active | 60555 |  | 2010-12-16 | 2012-05-14 | Hessisches Baumanagement Wiesbaden | W912GB-08-C-0005 | 28606000 | 32928000 | 2014-06-01 | 2014-11-07
2015-09-10 | 2009 | Army Active | 60859 |  | 2008-12-04 | 2009-05-13 | Cushman Contracting Corporation | W91238-09-C-0009 | 4795000 | 6425000 | 2010-12-09 | 2014-10-31
2015-09-10 | 2012 | Army Active | 61211 | 151 | 2011-11-22 | 2014-08-29 | Zieson Construction Company, LLC | W912DQ-13-D-4002 | 20000 | 20000 | 2014-10-28 | 2014-10-28
2015-09-10 | 2012 | Army Active | 61211 |  | 2011-11-22 | 2012-05-31 | TMG Services, Inc. | W912DQ-12-C-4005 | 7090000 | 7300000 | 2014-10-28 | 2014-10-28
2015-09-10 | 2011 | Army Active | 61383 |  | 2011-05-18 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | W91278-11-C-0028 | 15147000 | 15633000 | 2014-01-09 | 2014-09-24
2015-09-10 | 2011 | Army Active | 61453 |  | 2012-08-06 | 2013-05-23 | TMG SERVICES, INC. Linda Frazier | W912DR-13-C-0030 | 6189000 | 6580000 | 2014-11-27 | 2015-07-21
2015-09-10 | 2012 | Army Active | 61515 |  | 2011-10-19 | 2012-11-07 | Bristol General Contractors, LLC | W911KB-13-C-0002 | 21813000 | 22240000 | 2014-12-06 | 2015-06-26
2015-09-10 | 2011 | Army Active | 61533 |  | 2011-05-10 | 2011-07-29 | Carothers Construction, Inc. | W91278-07-D-0026 | 34508000 | 44851000 | 2014-10-06 | 2014-10-06
2015-09-10 | 2013 | Army Active | 61810 | 254 | 2012-12-06 | 2013-05-29 | Orocon-Carothers JV1 | W912QR-13-C-0010 | 23451000 | 23838000 | 2015-08-26 | 2015-09-07
2015-09-10 | 2013 | Army Active | 61810 |  | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | W912QR-14-C-0007 | 25750000 | 25812000 | 2015-08-26 | 2015-09-07
2015-09-10 | 2012 | Army Active | 61842 |  | 2012-03-13 | 2015-04-20 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0004 | 11607000 | 9720000 | 2016-12-01 | 2016-12-01
2015-09-10 | 2012 | Army Active | 62657 |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100113000 | 100274000 | 2015-10-19 | 2016-01-12
2015-09-10 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 84367000 | 84367000 | 2021-06-09 | 2021-12-06
2015-09-10 | 2012 | Army Active | 62955 |  | 2012-02-16 | 2012-03-28 | CLARK CONSTRUCTION GROUP LLC | W9126G-11-D-0049 | 44267000 | 48090000 | 2014-01-14 | 2014-11-06
2015-09-10 | 2011 | Army Active | 63015 | 80 | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV | W91238-11-C-0010 | 34801000 | 3567000 | 2016-06-30 | 2016-06-30
2015-09-10 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W91238-14-C-0040 | 38915000 | 38915000 | 2016-06-30 | 2016-06-30
2015-09-10 | 2008 | Army Active | 63714 | 7 | 2008-06-20 | 2012-07-30 | PLANEX Ltd. | W912GB-12-D-0030 | 3904000 | 5755000 | 2014-09-03 | 2016-04-29
2015-09-10 | 2008 | Army Active | 63714 |  | 2008-06-20 | 2008-09-17 | Bilfinger Berger SE Sede Secondaria Italia | W912GB-08-C-0031 | 47980000 | 47574000 | 2014-09-03 | 2016-04-29
2015-09-10 | 2012 | Army Active | 64014 | 157 | 2012-08-14 | 2012-06-28 | M.A. Mortenson Company | W9126G-08-D-0045 | 19332000 | 19731000 | 2015-04-08 | 2015-09-30
2015-09-10 | 2012 | Army Active | 64014 | 158 | 2012-08-14 | 2013-01-03 | TSS-Garco Joint Venture | W912DW-13-C-0019 | 8912000 | 9125000 | 2015-04-08 | 2015-09-30
2015-09-10 | 2012 | Army Active | 64014 | 159 | 2012-08-14 | 2013-09-26 | MEGEN Construction Company, Inc. | W912HN-11-D-0047 | 7295000 | 8666000 | 2015-04-08 | 2015-09-30
2015-09-10 | 2012 | Army Active | 64014 |  | 2012-08-14 | 2012-09-21 | 3D Contracting Inc. | W912DW-12-C-0046 | 14649000 | 15247000 | 2015-04-08 | 2015-09-30
2015-09-10 | 2012 | Army Active | 64365 | 161 | 2012-02-03 | 2012-11-07 | Arch Insurance Company | W912DQ-11-D-4011 | 8541000 | 8804000 | 2014-08-25 | 2015-11-30
2015-09-10 | 2012 | Army Active | 64365 | 162 | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | W912DQ-12-D-4006 | 2493000 | 4123000 | 2014-08-25 | 2015-11-30
2015-09-10 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-08-23 | KCI Construction Company | W912DQ-12-C-4009 | 30970000 | 32860000 | 2014-08-25 | 2015-11-30
2015-09-10 | 2012 | Army Active | 64415 | 164 | 2011-12-16 | 2012-08-17 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 11857000 | 12236000 | 2014-04-02 | 2015-07-02
2015-09-10 | 2012 | Army Active | 64415 |  | 2011-12-16 | 2012-03-23 | Blackhawk Ventures, LLC | W9126G-09-D-0093 | 10283000 | 11234000 | 2014-04-02 | 2015-07-02
2015-09-10 | 2011 | Army Active | 64760 |  | 2012-06-29 | 2012-09-19 | SRB International LLC | W9128A-12-C-0013 | 13310000 | 13325000 | 2014-08-17 | 2014-09-26
2015-09-10 | 2012 | Army Active | 64939 |  | 2012-06-20 | 2012-09-24 | Grimberg/Amatea JV | W912DR-12-C-0023 | 30554000 | 35586000 | 2014-11-20 | 2016-01-04
2015-09-10 | 2012 | Army Active | 64967 |  | 2011-10-06 | 2012-02-27 | 57 Builders, Ltd. | W9128A-12-C-0002 | 9573000 | 10828000 | 2013-12-13 | 2015-09-30
2015-09-10 | 2010 | Army Active | 65133 | 28 | 2010-05-04 | 2010-03-16 | MW Builders Inc. | W9126G-08-D-0044 | 9389000 | 9420000 | 2015-03-08 | 2015-04-20
2015-09-10 | 2010 | Army Active | 65133 | 29 | 2010-05-04 | 2011-07-15 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 13542000 | 15413000 | 2015-03-08 | 2015-04-20
2015-09-10 | 2010 | Army Active | 65133 | 30 | 2010-05-04 | 2014-09-04 | Zieson Construction Company, LLC | W912DQ-13-D-4002 | 359000 | 362000 | 2015-03-08 | 2015-04-20
2015-09-10 | 2010 | Army Active | 65133 | 31 | 2010-05-04 | 2010-05-20 | McTech Corporation | W912HN-08-D-0026 | 6114000 | 6030000 | 2015-03-08 | 2015-04-20
2015-09-10 | 2010 | Army Active | 65133 |  | 2010-05-04 | 2010-06-17 | TEPA EC, LLC | W912HN-08-D-0022 | 9882000 | 11570000 | 2015-03-08 | 2015-04-20
2015-09-10 | 2012 | Army Active | 65374 | 168 | 2012-01-05 | 2013-01-07 | Turner Strategic Technologies, LLC | W91236-13-C-0017 | 8195000 | 8454000 | 2014-11-28 | 2015-05-30
2015-09-10 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503000 | 40477000 | 2014-11-28 | 2015-05-30
2015-09-10 | 2012 | Army Active | 65602 | 170 | 2012-02-07 | 2014-05-08 | HHI Corporation | W9128F-11-D-0026 | 147000 | 184000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2012 | Army Active | 65602 | 171 | 2012-02-07 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 610000 | 667000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2012 | Army Active | 65602 |  | 2012-02-07 | 2012-03-30 | Komada, LLC | W9128F-12-C-0008 | 9947000 | 11356000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2011 | Army Active | 65650 |  | 2011-11-04 | 2012-02-28 | Niking Corporation | W9128A-12-C-0003 | 46780000 | 49902000 | 2014-04-23 | 2015-02-20
2015-09-10 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18727000 | 19430000 | 2015-04-08 | 2015-06-15
2015-09-10 | 2011 | Army Active | 65726 |  | 2011-11-14 | 2012-01-03 | Jordan-Versar, LLC | W91236-08-D-0056 | 55547000 | 57539000 | 2013-10-21 | 2014-10-24
2015-09-10 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30762000 | 36912000 | 2015-12-12 | 2017-04-25
2015-09-10 | 2011 | Army Active | 65793 | 85 | 2011-06-17 | 2011-09-29 | Aisow Technologies Corporation | W912DR-08-D-0036 | 306000 | 316000 | 2013-04-05 | 2014-08-11
2015-09-10 | 2011 | Army Active | 65793 |  | 2011-06-17 | 2011-09-21 | John C. Grimberg Co., Inc. | W912DR-11-C-0018 | 7241000 | 8409000 | 2013-04-05 | 2014-08-11
2015-09-10 | 2010 | Army Active | 66011 | 33 | 2010-04-28 | 2014-09-28 | Trend Construction, Inc. | W912HN-12-D-0030 | 696000 | 696000 | 2015-06-13 | 2015-06-13
2015-09-10 | 2010 | Army Active | 66011 |  | 2010-04-28 | 2010-07-16 | Odyssey International, Inc. | W912HN-10-C-0044 | 7034000 | 7653000 | 2015-06-13 | 2015-06-13
2015-09-10 | 2013 | Army Active | 66023 |  | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345000 | 27341000 | 2016-09-09 | 2016-10-12
2015-09-10 | 2013 | Army Active | 66099 | 259 | 2012-12-19 | 2015-01-20 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 6228000 | 6304000 | 2016-05-05 | 2016-05-23
2015-09-10 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687000 | 14606000 | 2016-05-05 | 2016-05-23
2015-09-10 | 2012 | Army Active | 66206 | 174 | 2012-08-18 | 2013-08-02 | James Talcott Construction, Inc. | W912DW-10-D-1015 | 5769000 | 6297000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2012 | Army Active | 66206 | 175 | 2012-08-18 | 2012-09-28 | Vet Industrial, Inc. | W912DW-10-D-1021 | 4980000 | 5253000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2012 | Army Active | 66206 | 176 | 2012-08-18 | 2012-08-29 | Alutiiq Diversified Services, LLC | W912DW-12-C-0040 | 10525000 | 12966000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2012 | Army Active | 66206 | 177 | 2012-08-18 | 2012-09-28 | Bristol General Contractors, LLC | W912DW-12-D-1018 | 1979000 | 2354000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2012 | Army Active | 66206 | 178 | 2012-08-18 | 2013-12-24 | Burr-MZT Joint Venture | W912DW-14-C-0001 | 919000 | 983000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2012 | Army Active | 66206 | 179 | 2012-08-18 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6814000 | 7351000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2012 | Army Active | 66206 | 180 | 2012-08-18 | 2014-06-20 | Bristol General Contractors, LLC | W912DW-14-C-0015 | 5288000 | 6058000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2012 | Army Active | 66206 |  | 2012-08-18 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775000 | 14595000 | 2015-09-10 | 2016-04-01
2015-09-10 | 2011 | Army Active | 66465 |  | 2012-03-06 | 2013-03-07 | LBB Kaiserslautern | W912GB-09-C-0039 | 9933000 | 11010000 | 2014-12-15 | 2014-12-19
2015-09-10 | 2010 | Army Active | 66545 | 35 | 2010-05-17 | 2012-05-16 | Easky Construction, LLC | W912BV-09-D-2019 | 757000 | 757000 | 2015-09-22 | 2015-12-31
2015-09-10 | 2010 | Army Active | 66545 | 36 | 2010-05-17 | 2014-06-16 | Red Cedar Enterprises, Inc. | W912BV-13-D-0011 | 1581000 | 1870000 | 2015-09-22 | 2015-12-31
2015-09-10 | 2010 | Army Active | 66545 |  | 2010-05-17 | 2010-09-22 | Anderson Drace Joint Venture | W912BV-10-C-2007 | 11779000 | 12311000 | 2015-09-22 | 2015-12-31
2015-09-10 | 2011 | Army Active | 66595 |  | 2011-09-08 | 2015-01-19 | LBB Kaiserslautern | W912GB-09-C-0014 | 30046000 | 30051000 | 2017-09-28 | 2017-09-28
2015-09-10 | 2012 | Army Active | 66691 | 182 | 2011-12-24 | 2014-03-04 | Alamo City Constructors, Inc. | W9126G-10-D-0001 | 36000 | 43000 | 2014-06-02 | 2014-07-11
2015-09-10 | 2012 | Army Active | 66691 |  | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | W9126G-12-C-0015 | 40532000 | 40941000 | 2014-06-02 | 2014-07-11
2015-09-10 | 2011 | Army Active | 66717 |  | 2013-05-30 | 2013-08-05 | Sunlight Enterprises Co., Inc | W9126G-13-C-2005 | 1780000 | 1925000 | 2014-07-22 | 2014-08-29
2015-09-10 | 2009 | Army Active | 66725 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7202000 | 7661000 | 2014-06-04 | 2015-07-17
2015-09-10 | 2010 | Army Active | 66726 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757000 | 8982000 | 2014-06-04 | 2015-07-17
2015-09-10 | 2011 | Army Active | 66834 |  | 2010-12-01 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 16286000 | 20380000 | 2013-12-18 | 2015-07-31
2015-09-10 | 2010 | Army Active | 67106 |  | 2009-10-16 | 2010-01-22 | Carson & Associates, Inc. | W9127S-10-C-6008 | 18457000 | 21432000 | 2012-02-22 | 2015-01-20
2015-09-10 | 2012 | Army Active | 67113 |  | 2011-07-15 | 2012-06-07 | Watterson Construction Company | W911KB-12-C-0008 | 70591000 | 71467000 | 2014-08-03 | 2014-10-09
2015-09-10 | 2014 | Army Active | 67116 | 315 | 2013-08-28 | 2014-04-14 | Arctic-American JV | W911KB-14-C-0008 | 16180000 | 16131000 | 2016-09-06 | 2016-09-06
2015-09-10 | 2014 | Army Active | 67116 | 316 | 2013-08-28 | 2014-12-31 | ALCAN BUILDERS INC. | W911KB-15-C-0001 | 12375000 | 12390000 | 2016-09-06 | 2016-09-06
2015-09-10 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0019 | 14180000 | 14419000 | 2016-09-06 | 2016-09-06
2015-09-10 | 2014 | Army Active | 67157 |  | 2015-05-13 | 2015-08-18 | Watts Constructors, LLC | W9128A-15-C-0003 | 63500000 | 63500000 | 2017-11-26 | 2017-11-26
2015-09-10 | 2011 | Army Active | 67194 |  | 2010-11-18 | 2012-03-13 | Blackhawk Ventrues, LLC | W9126G-09-D-0093 | 14554000 | 15295000 | 2013-08-09 | 2013-12-30
2015-09-10 | 2013 | Army Active | 67545 |  | 2013-05-16 | 2013-08-22 | Vet Industrial Inc. | W912DW-10-D-1021 | 4991000 | 5424000 | 2015-01-03 | 2015-01-03
2015-09-10 | 2011 | Army Active | 68074 |  | 2013-05-30 | 2013-08-12 | Hessisches Baumanagement Wiesbaden | W912GB-09-C-0059 | 6768000 | 7865000 | 2014-12-12 | 2014-12-12
2015-09-10 | 2009 | Army Active | 68786 |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 26656000 | 30863000 | 2014-03-14 | 2014-10-31
2015-09-10 | 2009 | Army Active | 68821 |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 31084000 | 36184000 | 2014-03-14 | 2014-10-31
2015-09-10 | 2009 | Army Active | 68822 |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 9840000 | 11626000 | 2014-03-14 | 2014-10-31
2015-09-10 | 2011 | Army Active | 68866 | 93 | 2012-05-22 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | W912GB-11-D-0036 | 7198000 | 8645000 | 2015-09-19 | 2015-10-31
2015-09-10 | 2011 | Army Active | 68866 | 94 | 2012-05-22 | 2014-06-24 | OBG Engineering GmbH & Co. KG | W912GB-14-D-0019 | 90000 | 90000 | 2015-09-19 | 2015-10-31
2015-09-10 | 2011 | Army Active | 68866 |  | 2012-05-22 | 2013-01-23 | ECC International LLC | W912GB-13-C-0003 | 87011000 | 88605000 | 2015-09-19 | 2015-10-31
2015-09-10 | 2010 | Army Active | 69150 | 40 | 2009-11-24 | 2012-08-23 | Brasfield & Gorrie LLC | W912HN-10-D-0046 | 21400000 | 52976000 | 2015-01-26 | 2015-08-12
2015-09-10 | 2010 | Army Active | 69150 |  | 2009-11-24 | 2010-02-19 | Walbridge Aldinger Company | W912HN-07-D-0054 | 12239000 | 13951000 | 2015-01-26 | 2015-08-12
2015-09-10 | 2009 | Army Active | 69199 | 15 | 2010-07-15 | 2010-09-27 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 4321000 | 4496000 | 2014-08-22 | 2014-08-22
2015-09-10 | 2009 | Army Active | 69199 | 16 | 2010-07-15 | 2013-09-30 | Tunista Construction, LLC | W9126G-13-C-0080 | 605000 | 622000 | 2014-08-22 | 2014-08-22
2015-09-10 | 2009 | Army Active | 69199 | 17 | 2010-07-15 | 2010-09-24 | The Davis Group, Inc. | W912HN-08-D-0037 | 8333000 | 8367000 | 2014-08-22 | 2014-08-22
2015-09-10 | 2009 | Army Active | 69199 | 18 | 2010-07-15 | 2011-07-06 | Q.B.S., Inc. | W912HN-08-D-0038 | 6876000 | 7112000 | 2014-08-22 | 2014-08-22
2015-09-10 | 2009 | Army Active | 69199 |  | 2010-07-15 | 2010-09-29 | Bristol Design Build Services, LLC | W912HN-08-D-0027 | 7687000 | 7968000 | 2014-08-22 | 2014-08-22
2015-09-10 | 2009 | Army Active | 69224 | 20 | 2009-07-21 | 2011-03-24 | Doyon Project Services LLC | W9126G-11-C-0015 | 19863000 | 17754000 | 2014-09-12 | 2015-04-30
2015-09-10 | 2009 | Army Active | 69224 | 21 | 2009-07-21 | 2013-07-03 | Kevcon Inc. | W912DW-10-D-1016 | 3177000 | 3387000 | 2014-09-12 | 2015-04-30
2015-09-10 | 2009 | Army Active | 69224 | 22 | 2009-07-21 | 2013-09-03 | Doyon Management Services, LLC | W912DW-13-C-0043 | 2991000 | 3227000 | 2014-09-12 | 2015-04-30
2015-09-10 | 2009 | Army Active | 69224 |  | 2009-07-21 | 2009-09-16 | M.A. Mortenson Company | W9126G-08-D-0048 | 51973000 | 53657000 | 2014-09-12 | 2015-04-30
2015-09-10 | 2012 | Army Active | 69286 |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008000 | 8733000 | 2013-09-13 | 2013-09-27
2015-09-10 | 2009 | Army Active | 69308 |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 60385000 | 66324000 | 2014-03-14 | 2014-10-31
2015-09-10 | 2010 | Army Active | 69417 | 42 | 2009-11-03 | 2010-09-24 | BL Harbert International, LLC | W91278-07-D-0042 | 3800000 | 3875000 | 2013-06-03 | 2015-02-18
2015-09-10 | 2010 | Army Active | 69417 |  | 2009-11-03 | 2010-06-24 | Balfour Beatty Construction, LLC | W91236-10-C-0058 | 43614000 | 50094000 | 2013-06-03 | 2015-02-18
2015-09-10 | 2012 | Army Active | 69489 |  | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772000 | 56358000 | 2015-05-27 | 2015-06-11
2015-09-10 | 2012 | Army Active | 69501 |  | 2011-12-16 | 2012-09-27 | Archer Western Federal JV | W912QR-12-C-0058 | 40397000 | 45467000 | 2014-09-06 | 2014-12-14
2015-09-10 | 2012 | Army Active | 69614 |  | 2012-03-02 | 2013-03-27 | Staatliches Hochbauamt Amberg | W912GB-10-C-0043 | 17523000 | 18492000 | 2014-12-31 | 2015-06-08
2015-09-10 | 2012 | Army Active | 69615 |  | 2012-01-03 | 2012-09-27 | Bauamt Amberg-Sulzbach | W912GB-10-C-0007 | 17669000 | 17859000 | 2014-08-27 | 2014-09-25
2015-09-10 | 2014 | Army Active | 69624 |  | 2014-06-10 | 2014-07-21 | Brantley Construction Services, LLC | W912HN-10-D-0056 | 4720000 | 4941000 | 2015-08-27 | 2015-09-14
2015-09-10 | 2012 | Army Active | 69745 | 197 | 2011-12-16 | 2012-05-08 | Windamir Development, Inc | W9126G-12-C-0027 | 11839000 | 11839000 | 2014-08-23 | 2014-12-17
2015-09-10 | 2012 | Army Active | 69745 | 198 | 2011-12-16 | 2013-02-21 | SOCO Contracting Company, INC. | W9126G-13-C-0014 | 11020000 | 11415000 | 2014-08-23 | 2014-12-17
2015-09-10 | 2012 | Army Active | 69745 |  | 2011-12-16 | 2012-05-08 | Compton Construction Company, Inc. | W9126G-11-D-0076 | 7898000 | 7918000 | 2014-08-23 | 2014-12-17
2015-09-10 | 2012 | Army Active | 69828 |  | 2013-07-16 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 8830000 | 8867000 | 2016-01-04 | 2016-01-13
2015-09-10 | 2011 | Army Active | 69830 | 98 | 2010-12-23 | 2014-05-02 | Lunacon Engineering Group Corp | W912HN-13-D-0004 | 1073000 | 1100000 | 2015-08-01 | 2015-08-25
2015-09-10 | 2011 | Army Active | 69830 | 99 | 2010-12-23 | 2015-01-09 | SILER EXCAVATING LLC | W912HN-14-D-0010 | 54000 | 54000 | 2015-08-01 | 2015-08-25
2015-09-10 | 2011 | Army Active | 69830 |  | 2010-12-23 | 2011-06-22 | Sauer Inc. d/b/a Sauer Southeast | W91278-07-D-0030 | 27688000 | 29236000 | 2015-08-01 | 2015-08-25
2015-09-10 | 2012 | Army Active | 69834 | 201 | 2013-08-26 | 2012-11-01 | Arch Insurance Company | W912DQ-11-D-4011 | 5933000 | 6086000 | 2015-07-31 | 2015-08-04
2015-09-10 | 2012 | Army Active | 69834 |  | 2013-08-26 | 2014-01-07 | Law Company, Inc. | W912DQ-14-C-4003 | 20079000 | 20395000 | 2015-07-31 | 2015-08-04
2015-09-10 | 2012 | Army Active | 69835 |  | 2014-08-25 | 2014-12-05 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 30589000 | 31584000 | 2016-02-29 | 2016-04-04
2015-09-10 | 2011 | Army Active | 71119 |  | 2011-06-03 | 2011-08-03 | PENTACON, LLC | W912HP-11-D-0007 | 15000000 | 15992000 | 2013-03-01 | 2014-12-11
2015-09-10 | 2013 | Army Active | 71120 |  | 2013-03-08 | 2013-09-04 | PENTACON, LLC | W912DY-12-D-0030 | 21912000 | 22002000 | 2015-04-10 | 2015-04-10
2015-09-10 | 2014 | Army Active | 71221 |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542000 | 12934000 | 2016-02-18 | 2016-06-01
2015-09-10 | 2010 | Army Active | 71421 |  | 2010-08-01 | 2015-01-06 | LBB Niederlassung Idar-Oberstein | W912GB-10-C-0042 | 18945000 | 18966000 | 2017-04-23 | 2017-04-23
2015-09-10 | 2011 | Army Active | 71422 |  | 2011-07-18 | 2011-09-14 | LBB Niederlassung Idar-Oberstein | W912GB-09-C-0007 | 34935000 | 34972000 | 2015-09-24 | 2015-09-24
2015-09-10 | 2011 | Army Active | 71462 | 105 | 2011-01-24 | 2011-06-01 | Sundt Construction Inc | W9126G-09-D-0004 | 6819000 | 6957000 | 2014-01-21 | 2015-01-05
2015-09-10 | 2011 | Army Active | 71462 | 106 | 2011-01-24 | 2011-09-12 | McGoldrick Construction Services, Corp. | W9126G-09-D-0098 | 3097000 | 3448000 | 2014-01-21 | 2015-01-05
2015-09-10 | 2011 | Army Active | 71462 | 107 | 2011-01-24 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 8780000 | 9297000 | 2014-01-21 | 2015-01-05
2015-09-10 | 2011 | Army Active | 71462 |  | 2011-01-24 | 2011-09-30 | JAMA Constructors | W912HN-11-D-0044 | 6573000 | 8565000 | 2014-01-21 | 2015-01-05
2015-09-10 | 2011 | Army Active | 71465 | 109 | 2011-03-21 | 2011-06-01 | Sundt Construction Inc | W9126G-09-D-0004 | 289000 | 363000 | 2013-11-11 | 2014-12-12
2015-09-10 | 2011 | Army Active | 71465 |  | 2011-03-21 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 3049000 | 3463000 | 2013-11-11 | 2014-12-12
2015-09-10 | 2010 | Army Active | 71485 | 49 | 2013-06-21 | 2014-04-03 | Contrack International, Inc. | W912ER-14-C-0011 | 6749000 | 6749000 | 2015-10-30 | 2015-10-30
2015-09-10 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2013-09-27 | Contrack International, Inc. | W912ER-13-C-0032 | 49413000 | 55213000 | 2015-10-30 | 2015-10-30
2015-09-10 | 2010 | Army Active | 71488 | 51 | 2011-10-11 | 2014-08-30 | Inglett & Stubbs, International LTD | W5J9JE-14-P-0044 | 56000 | 56000 | 2014-09-14 | 2015-12-06
2015-09-10 | 2010 | Army Active | 71488 |  | 2011-10-11 | 2011-12-14 | Ch2m Hill-Yuksel Joint Venture | W912ER-11-D-0008 | 39962000 | 46779000 | 2014-09-14 | 2015-12-06
2015-09-10 | 2014 | Army Active | 71502 | 323 | 2014-03-06 | 2014-12-19 | Zieson Construction Co. | W912DQ-14-D-4000 | 4796000 | 4842000 | 2016-08-04 | 2016-11-17
2015-09-10 | 2014 | Army Active | 71502 | 324 | 2014-03-06 | 2014-12-18 | Zieson Construction Company, LLC | W912DQ-15-C-4004 | 14313000 | 14283000 | 2016-08-04 | 2016-11-17
2015-09-10 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777000 | 50530000 | 2016-08-04 | 2016-11-17
2015-09-10 | 2012 | Army Active | 71569 |  | 2012-08-24 | 2012-11-15 | Contrack International Inc. | W912ER-11-D-0009 | 11924000 | 10056000 | 2014-03-07 | 2014-09-01
2015-09-10 | 2011 | Army Active | 71604 |  | 2012-05-30 | 2012-09-04 | ANHAM-ICSS Joint Venture | W912ER-11-D-0003 | 26827000 | 25203000 | 2014-06-05 | 2015-01-31
2015-09-10 | 2011 | Army Active | 71639 | 112 | 2012-12-19 | 2011-06-01 | Sundt Construction Inc | W9126G-09-D-0004 | 6608000 | 6783000 | 2015-01-30 | 2015-07-01
2015-09-10 | 2011 | Army Active | 71639 | 113 | 2012-12-19 | 2013-09-30 | Bristol General Contractors, LLC | W9126G-13-C-0061 | 15175000 | 15251000 | 2015-01-30 | 2015-07-01
2015-09-10 | 2011 | Army Active | 71639 |  | 2012-12-19 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 11652000 | 12096000 | 2015-01-30 | 2015-07-01
2015-09-10 | 2013 | Army Active | 71675 |  | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751000 | 42904000 | 2016-01-15 | 2016-01-15
2015-09-10 | 2012 | Army Active | 71682 | 205 | 2011-12-19 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3844000 | 3844000 | 2015-01-25 | 2015-03-30
2015-09-10 | 2012 | Army Active | 71682 | 206 | 2011-12-19 | 2013-12-04 | Solis Constructors, Inc | W9126G-14-C-0006 | 5786000 | 5928000 | 2015-01-25 | 2015-03-30
2015-09-10 | 2012 | Army Active | 71682 |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 9669000 | 10202000 | 2015-01-25 | 2015-03-30
2015-09-10 | 2009 | Army Active | 72125 | 25 | 2009-11-05 | 2012-08-23 | Prime Projects Int'l (Const) Limited | W912ER-12-C-0040 | 5739000 | 8416000 | 2013-08-13 | 2014-07-26
2015-09-10 | 2009 | Army Active | 72125 |  | 2009-11-05 | 2010-01-30 | ALMCO Limited | W912ER-10-C-0013 | 9048000 | 2742000 | 2013-08-13 | 2014-07-26
2015-09-10 | 2011 | Army Active | 72324 | 115 | 2010-10-26 | 2011-09-09 | Leebcor Services, LLC | W91236-10-D-0020 | 6994000 | 7151000 | 2014-05-08 | 2014-09-12
2015-09-10 | 2011 | Army Active | 72324 | 116 | 2010-10-26 | 2011-09-29 | Anthony and Gordon Construction Company, Inc | W9126G-11-D-0075 | 7936000 | 7952000 | 2014-05-08 | 2014-09-12
2015-09-10 | 2011 | Army Active | 72324 | 117 | 2010-10-26 | 2011-08-04 | Atlantic Marine Construction Company, Inc | W912HN-07-D-0024 | 1614000 | 1649000 | 2014-05-08 | 2014-09-12
2015-09-10 | 2011 | Army Active | 72324 |  | 2010-10-26 | 2013-01-10 | Caddell Construction | W912HN-10-D-0044 | 20847000 | 21398000 | 2014-05-08 | 2014-09-12
2015-09-10 | 2011 | Army Active | 72457 | 119 | 2011-07-20 | 2014-10-24 | Turner Strategic Technologies, LLC | W912HN-13-D-0013 | 706000 | 706000 | 2015-05-11 | 2015-05-11
2015-09-10 | 2011 | Army Active | 72457 |  | 2011-07-20 | 2011-09-29 | IAP Design-Build, LLC | W912HN-10-D-0054 | 11084000 | 22116000 | 2015-05-11 | 2015-05-11
2015-09-10 | 2010 | Army Active | 72477 |  | 2011-03-28 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 47161000 | 32389000 | 2013-12-07 | 2014-11-10
2015-09-10 | 2012 | Army Active | 72650 | 208 | 2011-11-10 | 2012-02-27 | Hanmi C&E Co., LTD. | W912UM-11-D-0007 | 64000 | 4000 | 2015-12-05 | 2015-11-26
2015-09-10 | 2012 | Army Active | 72650 |  | 2011-11-10 | 2012-02-24 | Samsung C&T Corporation | W912UM-12-C-0012 | 27593000 | 28895000 | 2015-12-05 | 2015-11-26
2015-09-10 | 2011 | Army Active | 72854 | 121 | 2011-05-02 | 2011-09-28 | Innovative Technical Solutions, Inc. | W9126G-08-D-0085 | 8894000 | 11287000 | 2015-10-24 | 2015-10-24
2015-09-10 | 2011 | Army Active | 72854 | 122 | 2011-05-02 | 2014-04-30 | Maanilaq Services LLC | W912DW-14-C-0011 | 3373000 | 3366000 | 2015-10-24 | 2015-10-24
2015-09-10 | 2011 | Army Active | 72854 | 123 | 2011-05-02 | 2014-09-26 | Wm. Dickson Company | W912DW-14-C-0028 | 1628000 | 2325000 | 2015-10-24 | 2015-10-24
2015-09-10 | 2011 | Army Active | 72854 |  | 2011-05-02 | 2013-01-22 | Garco Construction, Inc. | W912DW-13-C-0020 | 36247000 | 39055000 | 2015-10-24 | 2015-10-24
2015-09-10 | 2013 | Army Active | 73008 |  | 2013-03-22 | 2013-08-15 | Caddell Construction CO. (DE), LLC | W912HN-10-D-0044 | 20726000 | 21072000 | 2015-03-01 | 2015-06-25
2015-09-10 | 2015 | Army Active | 73542 |  | 2015-01-23 | 2015-08-27 | Archer Western Federal JV | W912QR-15-C-0024 | 17724000 | 17724000 | 2017-05-18 | 2017-05-18
2015-09-10 | 2012 | Army Active | 74067 |  | 2012-04-27 | 2012-08-15 | ANHAM-ICSS JV | W912ER-11-D-0003 | 19903000 | 22734000 | 2014-06-01 | 2014-12-28
2015-09-10 | 2012 | Army Active | 74084 |  | 2011-12-05 | 2012-04-12 | Bryan 77 Construction JV | W912ER-11-D-0004 | 19331000 | 14239000 | 2014-04-19 | 2014-11-17
2015-09-10 | 2010 | Army Active | 74408 |  | 2013-02-12 | 2013-08-29 | TSS-Garco Joint Venture | W912DW-13-C-0040 | 7327000 | 8538000 | 2015-01-28 | 2015-05-15
2015-09-10 | 2014 | Army Active | 74638 |  | 2013-11-07 | 2015-04-02 | SGS, LLC | W9126G-15-C-0091 | 13978000 | 13978000 | 2017-01-02 | 2017-01-02
2015-09-10 | 2011 | Army Active | 74757 |  | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | W912QR-12-C-0050 | 1763000 | 3083000 | 2013-08-01 | 2015-04-15
2015-09-10 | 2014 | Army Active | 74861 |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862000 | 27706000 | 2016-08-09 | 2016-09-19
2015-09-10 | 2014 | Army Active | 75019 |  | 2014-08-28 | 2014-11-06 | Zieson Construction Company, LLC | W912DQ-15-C-4000 | 3497000 | 3515000 | 2015-12-01 | 2016-01-04
2015-09-10 | 2013 | Army Active | 75165 |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77477000 | 78753000 | 2016-03-02 | 2016-04-18
2015-09-10 | 2014 | Army Active | 76024 |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630000 | 15747000 | 2016-02-24 | 2016-05-09
2015-09-10 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072000 | 3118000 | 2015-11-10 | 2016-07-17
2015-09-10 | 2013 | Army Active | 76091 |  | 2014-05-15 | 2014-09-18 | Federal Solutions Group | W91238-14-C-0051 | 3212000 | 3212000 | 2015-11-12 | 2015-11-12
2015-09-10 | 2013 | Army Active | 76196 |  | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25853000 | 28861000 | 2015-06-09 | 2016-05-29
2015-09-10 | 2012 | Army Active | 76235 | 212 | 2012-02-02 | 2012-02-09 | Hanmi C&E Co., LTD. | W912UM-11-D-0007 | 18000 | 90000 | 2014-07-02 | 2014-12-03
2015-09-10 | 2012 | Army Active | 76235 |  | 2012-02-02 | 2012-04-06 | Fine Construction Co., Ltd. | W912UM-12-C-0022 | 28610000 | 29427000 | 2014-07-02 | 2014-12-03
2015-09-10 | 2013 | Army Active | 76239 |  | 2012-11-13 | 2013-05-31 | Archer Western Federal JV | W912QR-13-C-0012 | 16983000 | 17527000 | 2015-04-26 | 2015-06-06
2015-09-10 | 2013 | Army Active | 76586 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717000 | 32165000 | 2015-09-01 | 2016-06-01
2015-09-10 | 2013 | Army Active | 76587 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410000 | 39691000 | 2015-09-01 | 2016-06-01
2015-09-10 | 2014 | Army Active | 76601 | 334 | 2013-08-30 | 2014-04-08 | ANCOR, INC. | W911KB-14-C-0003 | 2651000 | 3283000 | 2016-03-21 | 2016-09-29
2015-09-10 | 2014 | Army Active | 76601 | 335 | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC | W911KB-14-C-0005 | 9525000 | 9780000 | 2016-03-21 | 2016-09-29
2015-09-10 | 2014 | Army Active | 76601 | 336 | 2013-08-30 | 2014-04-08 | C.I. Contractors INC. | W911KB-14-C-0010 | 5007000 | 6538000 | 2016-03-21 | 2016-09-29
2015-09-10 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25547000 | 25552000 | 2016-03-21 | 2016-09-29
2015-09-10 | 2012 | Army Active | 76767 | 214 | 2011-12-19 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6360000 | 6948000 | 2015-08-21 | 2015-09-10
2015-09-10 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | W9126G-08-D-0044 | 24162000 | 24502000 | 2015-08-21 | 2015-09-10
2015-09-10 | 2012 | Army Active | 76768 | 216 | 2012-08-20 | 2014-04-08 | Glen/Mar Construction, Inc. | W912DW-14-C-0009 | 4771000 | 5147000 | 2015-05-21 | 2015-09-02
2015-09-10 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | W912DW-12-C-0051 | 12950000 | 13975000 | 2015-05-21 | 2015-09-02
2015-09-10 | 2014 | Army Active | 76776 | 338 | 2015-03-23 | 2015-04-09 | Walsh Group Ventures | W912DW-15-C-0002 | 11319000 | 11333000 | 2017-07-06 | 2017-07-06
2015-09-10 | 2014 | Army Active | 76776 |  | 2015-03-23 | 2015-07-09 | Vet Industrial, Inc. | W912DW-15-C-0007 | 11893000 | 11893000 | 2017-07-06 | 2017-07-06
2015-09-10 | 2014 | Army Active | 76777 | 340 | 2014-06-25 | 2014-09-03 | The Renew Group, Inc. | W912DW-14-C-0017 | 1106000 | 1124000 | 2016-03-16 | 2016-03-16
2015-09-10 | 2014 | Army Active | 76777 |  | 2014-06-25 | 2014-08-26 | Archer Western Federal JV | W912DW-14-C-0023 | 36998000 | 37583000 | 2016-03-16 | 2016-03-16
2015-09-10 | 2013 | Army Active | 76903 |  | 2012-11-26 | 2014-05-13 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749000 | 69749000 | 2017-01-13 | 2017-04-13
2015-09-10 | 2012 | Army Active | 77187 | 218 | 2015-03-12 | 2012-03-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 | 5379000 | 4709000 | 2015-01-25 | 2015-03-30
2015-09-10 | 2012 | Army Active | 77187 | 219 | 2015-03-12 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3750000 | 3750000 | 2015-01-25 | 2015-03-30
2015-09-10 | 2012 | Army Active | 77187 |  | 2015-03-12 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7473000 | 8035000 | 2015-01-25 | 2015-03-30
2015-09-10 | 2014 | Army Active | 77262 | 342 | 2014-02-28 | 2014-08-28 | Medvolt, LLC | W9128F-14-C-0054 | 13195000 | 13941000 | 2016-03-31 | 2016-05-29
2015-09-10 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165000 | 17351000 | 2016-03-31 | 2016-05-29
2015-09-10 | 2012 | Army Active | 77264 |  | 2012-06-01 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 53767000 | 54845000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2012 | Army Active | 77265 |  | 2012-06-01 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 37229000 | 37947000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2012 | Army Active | 77302 | 223 | 2012-02-22 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 602000 | 658000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2012 | Army Active | 77302 |  | 2012-02-22 | 2012-08-02 | Hensel Phelps Construction Co. | W9128F-12-C-0048 | 10891000 | 12512000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2014 | Army Active | 77304 | 344 | 2014-05-22 | 2014-09-04 | John Bowman, Inc. | W9128F-13-D-0013 | 2288000 | 2313000 | 2016-08-22 | 2016-09-08
2015-09-10 | 2014 | Army Active | 77304 | 345 | 2014-05-22 | 2014-09-04 | Hartland/Mass JV LLC | W9128F-13-D-0014 | 3339000 | 3524000 | 2016-08-22 | 2016-09-08
2015-09-10 | 2014 | Army Active | 77304 | 346 | 2014-05-22 | 2014-07-16 | SEK JV | W9128F-13-D-0015 | 3133000 | 3520000 | 2016-08-22 | 2016-09-08
2015-09-10 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56721000 | 58004000 | 2016-08-22 | 2016-09-08
2015-09-10 | 2012 | Army Active | 77306 | 225 | 2012-01-17 | 2012-09-26 | Hensel Phelps Construction Company | W9128F-12-C-0085 | 195000 | 195000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2012 | Army Active | 77306 | 226 | 2012-01-17 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 2669000 | 2920000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2012 | Army Active | 77306 |  | 2012-01-17 | 2012-08-09 | Hensel Phelps Construction Co. | W9128F-12-C-0055 | 44801000 | 54672000 | 2015-02-08 | 2015-03-16
2015-09-10 | 2014 | Army Active | 77405 | 348 | 2014-07-09 | 2014-06-19 | Blackhorse Worldwide LLC | W9128F-13-D-0016 | 4214000 | 4704000 | 2016-08-22 | 2016-09-16
2015-09-10 | 2014 | Army Active | 77405 | 349 | 2014-07-09 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 891000 | 891000 | 2016-08-22 | 2016-09-16
2015-09-10 | 2014 | Army Active | 77405 | 350 | 2014-07-09 | 2015-01-16 | Agile Infrastructure Services, L.L.C. | W9128F-15-C-0002 | 2843000 | 2843000 | 2016-08-22 | 2016-09-16
2015-09-10 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585000 | 51715000 | 2016-08-22 | 2016-09-16
2015-09-10 | 2013 | Army Active | 77416 |  | 2013-04-04 | 2013-05-29 | R. C. Construction Co., Inc. | W912HN-10-D-0058 | 8295000 | 8490000 | 2015-01-03 | 2015-03-04
2015-09-10 | 2013 | Army Active | 77419 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 10400000 | 10400000 | 2016-12-26 | 2017-01-09
2015-09-10 | 2014 | Army Active | 77539 |  | 2014-07-17 | 2014-09-26 | Barlovento, LLC | W91278-10-D-0072 | 4711000 | 4711000 | 2015-12-17 | 2015-12-17
2015-09-10 | 2014 | Army Active | 77885 |  | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9833000 | 11431000 | 2015-07-01 | 2015-11-08
2015-09-10 | 2014 | Army Active | 77980 |  | 2014-08-12 | 2014-09-16 | FutureNet Group, Inc. | W912QR-09-D-0050 | 1636000 | 1657000 | 2015-08-20 | 2015-09-19
2015-09-10 | 2013 | Army Active | 78054 |  | 2014-07-08 | 2015-03-17 | Akima Construction Services, LLC | W912DR-15-C-0013 | 3358000 | 10015000 | 2016-09-24 | 2016-09-24
2015-09-10 | 2012 | Army Active | 78475 |  | 2013-05-22 | 2014-11-18 | Klebl GmbH | W912GB-15-C-0003 | 14632000 | 14632000 | 2016-06-09 | 2016-06-09
2015-09-10 | 2012 | Army Active | 78505 |  | 2012-04-06 | 2013-08-07 | Staatliches Hochbauamt Amberg | W912GB-11-C-0027 | 13549000 | 13780000 | 2015-09-14 | 2015-09-14
2015-09-10 | 2012 | Army Active | 78506 |  | 2012-04-10 | 2013-09-30 | Bauamt Amberg-Sulzbach | W912GB-11-C-0016 | 12815000 | 12905000 | 2015-09-14 | 2015-09-14
2015-09-10 | 2014 | Army Active | 78778 |  | 2013-12-24 | 2014-06-18 | TJC Engineering | W912QR-14-C-0018 | 4275000 | 4284000 | 2015-08-21 | 2015-10-09
2015-09-10 | 2012 | Army Active | 78841 | 231 | 2012-05-15 | 2013-05-09 | WAYSS & FREYTAG INGENIEURBAU AG | W912GB-12-D-0055 | 1168000 | 1590000 | 2018-10-29 | 2019-05-16
2015-09-10 | 2012 | Army Active | 78841 |  | 2012-05-15 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0018 | 20429000 | 21310000 | 2018-10-29 | 2019-05-16
2015-09-10 | 2012 | Army Active | 79097 |  | 2012-05-12 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0017 | 17917000 | 18916000 | 2018-04-02 | 2018-11-09
2015-09-10 | 2014 | Army Active | 79618 |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440000 | 8921000 | 2016-02-11 | 2016-06-08
2015-09-10 | 2012 | Army Active | 79652 | 234 | 2014-07-14 | 2014-07-28 | American Int'l Contractors Inc | W912ER-14-C-0021 | 1367000 | 1387000 | 2014-11-30 | 2014-11-30
2015-09-10 | 2012 | Army Active | 79652 |  | 2014-07-14 | 2012-08-20 | American Assurance Underwriters Group | W912ER-12-C-0046 | 3800000 | 4171000 | 2014-11-30 | 2014-11-30
2015-09-10 | 2014 | Army Active | 79679 |  | 2014-02-03 | 2014-06-10 | Au' Authum Ki, Inc | W912PL-10-D-0109 | 2984000 | 2984000 | 2015-09-01 | 2015-09-01
2015-09-10 | 2012 | Army Active | 79749 | 236 | 2012-06-15 | 2012-07-05 | EMTA CONSTRUCTION CO. INC. | W912GB-10-D-0020 | 320000 | 320000 | 2014-11-30 | 2015-02-18
2015-09-10 | 2012 | Army Active | 79749 | 237 | 2012-06-15 | 2013-03-19 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. | W912GB-12-D-0035 | 199000 | 199000 | 2014-11-30 | 2015-02-18
2015-09-10 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-08-30 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129000 | 12293000 | 2014-11-30 | 2015-02-18
2015-09-10 | 2011 | Army Active | 79762 |  | 2011-05-04 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 1387000 | 1387000 | 2013-12-07 | 2014-11-10
2015-09-10 | 2011 | Army Active | 79770 |  | 2011-05-13 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 1331000 | 1331000 | 2013-12-07 | 2014-11-10
2015-09-10 | 2012 | Army Active | 79846 |  | 2014-07-11 | 2014-09-28 | Kiewit Federal Group, Inc. | W912DR-11-D-0021 | 3195000 | 3195000 | 2015-12-01 | 2015-12-01
2015-09-10 | 2013 | Army Active | 79933 | 79933 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 166440000 | 2016-08-30 | 2016-09-11
2015-09-10 | 2014 | Army Active | 79933 | 81186 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 166440000 | 2016-08-30 | 2016-09-11
2015-09-10 | 2015 | Army Active | 79933 | 81187 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 166440000 | 2016-08-30 | 2016-09-11
2015-09-10 | 2013 | Army Active | 79980 | 287 | 2013-05-17 | 2012-09-30 | Zieson Construction Company, LLC | W912DQ-11-D-4007 | 15000 | 15000 | 2014-06-20 | 2015-09-01
2015-09-10 | 2013 | Army Active | 79980 |  | 2013-05-17 | 2013-07-17 | Huffman Construction, LLC | W912DQ-13-C-4018 | 1438000 | 1551000 | 2014-06-20 | 2015-09-01
2015-09-10 | 2012 | Army Active | 80001 |  | 2012-05-25 | 2012-08-21 | Bryan 77 Construction JV | W912ER-11-D-0004 | 24436000 | 23957000 | 2014-03-27 | 2014-12-15
2015-09-10 | 2013 | Army Active | 80066 |  | 2012-11-16 | 2013-09-20 | Tyler Construction Co., INC | W912HN-10-D-0060 | 6727000 | 6769000 | 2015-03-01 | 2015-03-20
2015-09-10 | 2013 | Army Active | 80087 |  | 2012-07-16 | 2013-03-22 | Tyler Construction Group, Inc. | W912HN-10-D-0060 | 9038000 | 9004000 | 2014-08-11 | 2014-09-17
2015-09-10 | 2013 | Army Active | 80112 |  | 2014-12-02 | 2015-04-23 | Sauer Inc. d/b/a Sauer Southeast | W91278-12-D-0039 | 10965000 | 10965000 | 2017-02-06 | 2017-02-06
2015-09-10 | 2013 | Army Active | 80113 | 292 | 2013-04-25 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 591000 | 611000 | 2016-01-04 | 2016-01-13
2015-09-10 | 2013 | Army Active | 80113 | 293 | 2013-04-25 | 2013-08-30 | Carntribe-Clement 8aJV #1, LLC | W912HN-11-D-0028 | 5994000 | 5977000 | 2016-01-04 | 2016-01-13
2015-09-10 | 2013 | Army Active | 80113 |  | 2013-04-25 | 2013-08-15 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491000 | 11454000 | 2016-01-04 | 2016-01-13
2015-09-10 | 2012 | Army Active | 80231 |  | 2014-07-25 | 2014-09-28 | East Coast Utility Contractors | W912DR-14-C-0041 | 1484000 | 1484000 | 2015-09-25 | 2015-09-25
2015-09-10 | 2013 | Army Active | 80246 | 295 | 2012-12-12 | 2013-06-17 | Black Horse Group LLC | W912DS-09-D-0004 | 21578000 | 22594000 | 2015-12-02 | 2016-03-18
2015-09-10 | 2013 | Army Active | 80246 | 296 | 2012-12-12 | 2013-11-25 | Upstate Construction Services, Inc. | W912DS-09-D-0005 | 17287000 | 17753000 | 2015-12-02 | 2016-03-18
2015-09-10 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 39587000 | 40327000 | 2015-12-02 | 2016-03-18
2015-09-10 | 2013 | Army Active | 80317 |  | 2013-08-14 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1791000 | 1523000 | 2014-09-10 | 2015-04-30
2015-09-10 | 2014 | Army Active | 80477 |  | 2013-04-22 | 2013-12-13 | The Clement Group, L.L.C. | W91278-11-D-0029 | 2341000 | 2345000 | 2015-07-17 | 2015-07-17
2015-09-10 | 2014 | Army Active | 80919 |  | 2014-08-12 | 2014-09-29 | Glen/Mar Construction, Inc. | W912DW-14-C-0029 | 1545000 | 1631000 | 2016-02-13 | 2016-02-13
2015-09-10 | 2014 | Army Active | 80992 |  | 2015-02-06 | 2015-03-24 | Red One Construction, LLC | W9128A-15-C-0002 | 1696000 | 1696000 | 2016-10-20 | 2016-10-20
2015-09-10 | 2013 | Army Active | 81106 |  | 2013-06-11 | 2013-09-27 | Zumwalt Construction, Inc. | W91238-11-D-0026 | 1882000 | 2431000 | 2014-12-17 | 2015-06-15
2015-09-10 | 2014 | Army Active | 81155 |  | 2014-05-02 | 2014-12-05 | SGS, LLC | W9126G-15-C-0005 | 32968000 | 32968000 | 2016-04-11 | 2016-04-11
2015-09-10 | 2015 | Army Active | 81230 |  | 2015-05-08 | 2015-07-27 | Yojin Construction & Engineering Co., Ltd. | W912UM-15-C-0015 | 43753000 | 43753000 | 2018-04-28 | 2018-04-28
2015-09-10 | 2013 | Army Active | 81300 |  | 2013-04-29 | 2013-09-12 | CMS of Colorado Springs, Inc. dba CMS | W9128F-13-C-0023 | 1731000 | 1850000 | 2014-08-25 | 2014-12-22
2015-09-10 | 2013 | Army Active | 81320 |  | 2013-08-08 | 2013-09-26 | Northcon, Inc. | W912DW-13-C-0047 | 1380000 | 1380000 | 2014-10-28 | 2015-01-26
2015-09-10 | 2015 | Army Active | 81349 |  | 2015-02-20 | 2015-06-04 | Upstate Construction SVCS, Inc. | W912DS-15-C-0008 | 19408000 | 19408000 | 2016-12-18 | 2016-12-18
2015-09-10 | 2015 | Army Active | 81357 | 369 | 2015-04-13 |  | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 804000 | 804000 | 2017-01-18 | 2017-01-18
2015-09-10 | 2015 | Army Active | 81357 |  | 2015-04-13 | 2015-07-07 | David Boland, Inc. | W9128F-15-C-0017 | 26149000 | 26149000 | 2017-01-18 | 2017-01-18
2015-09-10 | 2013 | Army Active | 81367 |  | 2013-12-18 | 2014-04-16 | Cyber Professional Solution Corp | W912PL-14-C-0006 | 1784000 | 1784000 | 2015-05-08 | 2015-05-08
2015-09-10 | 2013 | Army Active | 81431 | 303 | 2013-08-15 | 2014-09-30 | Portico Services | W912DR-14-C-0048 | 220000 | 245000 | 2015-04-28 | 2015-07-31
2015-09-10 | 2013 | Army Active | 81431 |  | 2013-08-15 | 2014-06-17 | PORTICO SERVICES, LLC | W912DR-14-C-0028 | 1793000 | 1850000 | 2015-04-28 | 2015-07-31
2015-09-10 | 2013 | Army Active | 81462 |  | 2014-08-21 | 2014-09-30 | Nan Inc | W9128A-12-D-0012 | 1556000 | 1556000 | 2015-10-23 | 2015-10-23
2015-09-10 | 2013 | Army Active | 81515 |  | 2013-05-21 | 2013-09-29 | Guyco, Inc. | W9126G-09-D-0095 | 1784000 | 1779000 | 2014-12-04 | 2015-01-03
2015-09-10 | 2013 | Army Active | 81629 |  | 2013-07-15 | 2013-09-27 | Team Henry Enterprises, LLC | W91236-13-D-0042 | 1089000 | 1133000 | 2014-08-13 | 2014-11-11
2015-09-10 | 2014 | Army Active | 81875 |  | 2013-12-02 | 2014-05-12 | Edifice-Schlosser JV, LLC | W912DR-14-C-0017 | 17891000 | 20707000 | 2015-03-19 | 2015-08-11
2015-09-10 | 2014 | Army Active | 82268 |  | 2014-07-22 | 2014-09-30 | Tarver Land Development, LLC | W9126G-14-C-0059 | 1749000 | 1793000 | 2015-04-02 | 2015-05-06
2015-09-10 | 2014 | Army Active | 82371 |  | 2015-03-28 | 2014-09-30 | San Juan Construction, Inc. | W9128A-12-D-0010 | 1597000 | 1587000 | 2015-09-07 | 2015-09-29
2015-09-10 | 2014 | Army Active | 85260 |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1725000 | 1744000 | 2015-11-05 | 2015-11-05
2015-08-31 | 2012 | Army National Guard | 010263 |  | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. | W912JA-12-C-0001 | 16413000 | 14492000 | 2014-09-17 | 2014-09-23 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 010278 |  | 2013-08-01 | 2013-08-27 | Hurst Construction, LLC | AC-13-C-0052-S | 5223000 | 5437000 | 2014-11-11 | 2015-06-08 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 011007 |  | 2013-09-24 | 2013-09-30 | Butler Construction Company, LLC. | AC-13-C-0051-S | 1920000 | 1904000 | 2014-10-01 | 2014-12-19
2015-08-31 | 2014 | Army National Guard | 011014 |  | 2014-08-14 | 2014-08-22 | Carmon Construction, Inc. | AC-14-C-0005-S | 4000000 | 3756000 | 2015-12-10 | 2015-12-10
2015-08-31 | 2012 | Army National Guard | 040294 |  | 2012-02-15 | 2012-08-16 | Haydon Building Corporation-Tem | M11-0045 | 17771000 | 17655000 | 2013-10-16 | 2014-01-31 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 040669 |  | 2013-09-23 | 2014-04-04 | Ludvik Electric | M13-0037 | 2000000 | 1833000 | 2014-10-31 | 2014-10-31
2015-08-31 | 2013 | Army National Guard | 050139 |  | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC | 9751312 | 6577000 | 5231000 | 2014-10-01 | 2014-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 050172 |  | 2012-02-14 | 2012-08-16 | USPFO - AK | 9751104 | 3500000 | 3604000 | 2013-10-28 | 2014-07-15 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | 050182 |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-B-0001 | 21000000 | 16758000 | 2015-06-30 | 2015-06-30
2015-08-31 | 2012 | Army National Guard | 050190 |  | 2013-09-12 | 2013-09-18 | Wilkins Construction, Inc. | W912JF-09-D-0016-0013 | 1195000 | 1759000 | 2014-06-23 | 2014-12-22
2015-08-31 | 2010 | Army National Guard | 060115 |  | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | W912LA-10-C-0009 | 30711000 | 23378000 | 2012-02-06 | 2015-01-30 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2015-08-31 | 2012 | Army National Guard | 060170 |  | 2012-06-19 | 2012-06-26 | Goshawk LLC | W912LA-12-C-0003 | 7985000 | 7482000 | 2013-10-14 | 2014-06-06 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 060413 |  | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793000 | 30625000 | 2014-10-01 | 2015-10-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 ($1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)}
2015-08-31 | 2011 | Army National Guard | 060429 |  | 2011-05-12 | 2011-09-20 | Cox Construction Company | W912LA-11-R-0005 | 12379000 | 11525000 | 2012-06-29 | 2013-09-27 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2015-08-31 | 2012 | Army National Guard | 060432 |  | 2012-06-27 | 2012-09-28 | WEP Enterprises | W912LA-11-D-0024 | 1400000 | 1131000 | 2013-09-20 | 2014-10-30 | FY07 Congressionally Directed, Used FY10 funds
2015-08-31 | 2012 | Army National Guard | 060438 |  | 2012-06-04 | 2012-07-20 | Red Mountain LLC | W912LA-12-C-0002 | 6114000 | 5257000 | 2013-10-28 | 2015-06-02 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835)
2015-08-31 | 2011 | Army National Guard | 080067 |  | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC | W912LC-11-C-0008 | 50886000 | 50932000 | 2014-10-18 | 2014-10-03 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2,000 Formal Reprogramming $9,300 funds from FY10 project savings {PNs: 160120 ($6,000) & 350043 ($3,300)}
2015-08-31 | 2012 | Army National Guard | 080093 |  | 2012-08-30 | 2012-09-04 | FSA & JKC Joint Venture One, LLC. | W912LC-12-C-0009 | 42228000 | 43823000 | 2013-10-28 | 2015-06-30 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 080206 |  | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. | W912LC-12-C-0012 | 3592000 | 3900000 | 2013-10-28 | 2015-04-30 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 090043 |  | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951000 | 30071000 | 2015-10-01 | 2015-10-09 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 090115 |  | 2014-08-28 | 2014-09-11 | Nutmeg Companies, Inc. | W91ZRS-12-D-0026-0005 | 3600000 | 1398000 | 2015-03-31 | 2015-05-27 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 450252)
2015-08-31 | 2013 | Army National Guard | 100010 |  | 2013-06-21 | 2013-07-25 | EDIS Company | 40325 | 5319000 | 5329000 | 2014-09-23 | 2014-12-04 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), Construction is finish, project completion is pending all closeout documentation
2015-08-31 | 2013 | Army National Guard | 120102 |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) | W911YN-11-2-2002 | 24827000 | 21104000 | 2015-07-26 | 2015-09-13 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) & Formal Reprogramming $5,482 funds from FY12 project savings {PNs: 060009 ($4,452) & 240187 ($1,030)}
2015-08-31 | 2014 | Army National Guard | 120195 |  | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | W911YN-13-2-2004 | 5700000 | 5300000 | 2016-04-05 | 2016-04-05
2015-08-31 | 2013 | Army National Guard | 120228 |  | 2013-09-05 | 2013-09-10 | Halfacre Construction Company | W911YN-13-2-2002 | 1939000 | 1920000 | 2015-05-16 | 2015-09-23
2015-08-31 | 2012 | Army National Guard | 130063 |  | 2012-01-12 | 2012-09-11 | J&S Construction Company, Inc. | W912JM-12-R-0011 | 19255000 | 20542000 | 2013-10-28 | 2015-08-15 | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2015-08-31 | 2012 | Army National Guard | 130068 |  | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC | 41100-044-0000082512 | 14457000 | 14123000 | 2014-03-14 | 2014-10-14 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 130120 |  | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. | 41100-044-0000082224 | 10991000 | 11239000 | 2013-10-28 | 2014-11-24 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 130123 |  | 2011-05-17 | 2012-04-17 | TEPA | W912JM-10-D-0018 | 10363000 | 10349000 | 2013-09-30 | 2014-04-30 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 130127 |  | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 41100-033-0000078159 | 16941000 | 16726000 | 2012-11-16 | 2012-11-16 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 140040 |  | 2013-08-22 | 2013-09-24 | NAVFAC Pacific | N40192-10-D-2800 | 8221000 | 8089000 | 2014-10-20 | 2014-10-20 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2010 | Army National Guard | 140300 |  | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | N40192-10-C-1335 | 20766000 | 20797000 | 2012-03-05 | 2012-03-05 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2015-08-31 | 2013 | Army National Guard | 150023 |  | 2013-10-25 | 2014-09-26 | Watts Constructors, LLC | W912J6-14-C-0003 | 32625000 | 33617000 | 2016-11-01 | 2016-11-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2015-08-31 | 2011 | Army National Guard | 160093 |  | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | W912J7-11-C-0002 | 17333000 | 13811000 | 2013-02-28 | 2014-04-15 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2015-08-31 | 2013 | Army National Guard | 160100 |  | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692000 | 38006000 | 2014-08-01 | 2016-03-09 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | 170033 |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2004-100 | 14000000 | 16000000 | 2016-10-01 | 2016-11-01
2015-08-31 | 2014 | Army National Guard | 170127 |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2003-100 | 28000000 | 30000000 | 2016-10-01 | 2016-11-01
2015-08-31 | 2010 | Army National Guard | 170611 |  | 2010-09-17 | 2010-09-22 | Capital Development Board | W91SMC-10-2-2001-100 | 5560000 | 4319000 | 2011-09-14 | 2011-09-14 | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2015-08-31 | 2012 | Army National Guard | 171005 |  | 2012-09-23 | 2012-09-24 | H&N Construction | W91SMC-10-2-2005 | 1210000 | 999000 | 2013-10-31 | 2013-11-19 | (NGB 593)
2015-08-31 | 2012 | Army National Guard | 180012 |  | 2012-09-18 | 2012-09-19 | F.A. WILHELM Construction, Inc. | MDI-SAB-13-C-0012 | 34971000 | 34919000 | 2013-10-28 | 2015-04-30 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2.000 FY09 {PN: 040026} & Formal Reprogramming $7,271 funds from FY09 project savings {PNs: 040226 ($2,540), 180116 ($3,805), 180137 ($510) and 260211 ($416)}
2015-08-31 | 2013 | Army National Guard | 180106 |  | 2013-09-23 | 2013-09-24 | Gamong Construction | MDI-SAB-14-C-0002 | 8705000 | 8545000 | 2014-12-25 | 2015-09-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 180142 |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 20908000 | 19069000 | 2014-06-07 | 2014-06-07 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 180144 |  | 2013-09-19 | 2013-09-20 | Ziolkowski Construction | MDI-SAB-14-C-0001 | 20311000 | 22016000 | 2015-08-23 | 2015-05-29 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 180156 |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 8878000 | 8255000 | 2014-06-07 | 2014-06-07 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 180160 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 24991000 | 26136000 | 2014-05-01 | 2014-05-01 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 180161 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 27000000 | 27520000 | 2014-05-01 | 2014-05-01 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 200102 |  | 2013-05-21 | 2013-06-14 | Senne & Co | W912JC-13-C-1307 | 9188000 | 8555000 | 2014-10-01 | 2014-07-04 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 200127 |  | 2013-09-16 | 2013-09-24 | Harbin Construction | W912JC-12-D-5308 | 1440000 | 1627000 | 2014-06-13 | 2015-04-02
2015-08-31 | 2013 | Army National Guard | 210001 |  | 2013-05-17 | 2013-06-04 | DW Wilburn | CT2 1300000269 | 30953000 | 26572000 | 2014-10-01 | 2015-05-31 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 220222 |  | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company | LA11-C-139 | 5470000 | 5018000 | 2012-07-30 | 2013-06-18 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 220233 |  | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. | LA12-C-117 | 2972000 | 2881000 | 2013-06-17 | 2014-12-02
2015-08-31 | 2013 | Army National Guard | 220241 |  | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300000 | 8937000 | 2016-10-30 | 2016-10-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353)
2015-08-31 | 2013 | Army National Guard | 220243 |  | 2013-07-25 | 2014-07-25 | Gibbs Construction | LA06-C-081 | 5700000 | 3817000 | 2014-10-15 | 2014-10-15 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $3,000 - PN: 450252, $2,700 - PN: 450353)
2015-08-31 | 2012 | Army National Guard | 230046 |  | 2012-04-05 | 2012-09-26 | ITSI Gibane | W912JD-12-C-0003 | 14390000 | 14919000 | 2014-07-11 | 2015-09-30 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 230071 |  | 2012-09-10 | 2012-09-26 | J.C.N. Construction Co, Inc. | W912JD-12-C-0002 | 23058000 | 24309000 | 2014-10-12 | 2015-06-30 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-08-31 | 2015 | Army National Guard | 230113 |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113-D | 32000000 | 32795000 | 2018-01-01 | 2018-01-01 | Using State procedures the contract number is the same as the project number plus -D to delineate Construction
2015-08-31 | 2012 | Army National Guard | 240017 |  | 2012-08-29 | 2012-09-11 | The Whiting-Turner Contracting Company | 001B3400152 | 15771000 | 12230000 | 2014-09-22 | 2015-08-31 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 240186 |  | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | N40080-10-D-0498 | 5480000 | 5587000 | 2013-06-15 | 2014-11-21 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 240187 |  | 2012-07-23 | 2012-09-11 | Harkins Builders | 001B3400154 | 10296000 | 8254000 | 2014-09-22 | 2015-03-20 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 240193 |  | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 001B3400155 | 9000000 | 10075000 | 2014-09-22 | 2015-09-15 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 240194 |  | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 1920000 | 1788000 | 2014-09-22 | 2015-12-18
2015-08-31 | 2013 | Army National Guard | 250065 |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279000 | 21242000 | 2015-07-30 | 2015-10-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | 250095 |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000000 | 20559000 | 2016-11-01 | 2016-11-01
2015-08-31 | 2012 | Army National Guard | 250135 |  | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc. | MIL1001-DC1 | 8986000 | 9630000 | 2013-10-28 | 2014-10-28 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-08-31 | 2013 | Army National Guard | 250196 |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District | W912W3-11-D-0069 | 2000000 | 1838000 | 2013-12-01 | 2013-12-01
2015-08-31 | 2014 | Army National Guard | 260051 |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000000 | 17645000 | 2016-10-01 | 2016-10-01
2015-08-31 | 2014 | Army National Guard | 270014 |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000000 | 18218000 | 2016-04-15 | 2016-04-15
2015-08-31 | 2013 | Army National Guard | 270236 |  | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. | 67879 | 12783000 | 13647000 | 2015-10-01 | 2016-06-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 270238 |  | 2013-08-08 | 2013-08-14 | LS Black Constructors | W912LM-13-C-0007 | 16443000 | 17523000 | 2015-10-15 | 2015-10-28 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 270266 |  | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. | WGO010008 | 4718000 | 4477000 | 2013-12-15 | 2014-06-01 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,718)
2015-08-31 | 2014 | Army National Guard | 280272 |  | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB22-14-C-0003-S | 4500000 | 4718000 | 2015-10-01 | 2015-10-01
2015-08-31 | 2014 | Army National Guard | 280423 |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000000 | 4613000 | 2015-06-30 | 2015-06-30
2015-08-31 | 2014 | Army National Guard | 281305 |  | 2014-09-24 | 2014-09-26 | Miller Enterprises | NGB22-14-C-0007-S | 1950000 | 1039000 | 2015-04-30 | 2015-07-15
2015-08-31 | 2013 | Army National Guard | 290176 |  | 2013-07-26 | 2013-08-01 | KCI Construction Company | T1203-01B | 17410000 | 15890000 | 2015-02-28 | 2015-07-21 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | 290191 |  | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01C | 9100000 | 7612000 | 2015-07-31 | 2015-10-31
2015-08-31 | 2014 | Army National Guard | 290221 |  | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 5000000 | 4459000 | 2015-06-26 | 2015-10-06
2015-08-31 | 2015 | Army National Guard | 300128 |  | 2015-04-14 | 2015-04-20 | Swank Enterprises - Valier | W9124V-08-2-2001 | 38000000 | 27573000 | 2017-05-31 | 2017-05-13
2015-08-31 | 2010 | Army National Guard | 320143 |  | 2010-09-26 | 2010-09-27 | The Penta Building Company | SPWB-09-C-14 | 25807000 | 19910000 | 2012-01-23 | 2013-04-19 | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2015-08-31 | 2011 | Army National Guard | 330034 |  | 2011-05-09 | 2011-08-25 | Eckman Construction Company, Inc. | W912TF-09-2-2001 | 20742000 | 19809000 | 2013-06-01 | 2016-03-03 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 330035 |  | 2011-05-09 | 2011-08-26 | Eckman Construction Company, Inc. | W912TF-09-2-2002 | 14880000 | 14005000 | 2013-06-01 | 2016-01-30 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 330052 |  | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 330052-GC | 1947000 | 1943000 | 2013-08-13 | 2013-08-13 | (Closeout procedures are in progress)
2015-08-31 | 2013 | Army National Guard | 340110 |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885000 | 32189000 | 2016-02-12 | 2016-02-12 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 340115 |  | 2012-02-15 | 2012-09-19 | Senate Builders & Const Manager | W912KN-12-C-0006 | 48795000 | 46289000 | 2014-10-18 | 2015-01-31 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 340130 |  | 2014-09-19 | 2014-09-26 | Rome Management Associates, LLC | W912KN-13-D-0029 | 2228000 | 1481000 | 2015-08-31 | 2015-08-31 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2015-08-31 | 2014 | Army National Guard | 360161 |  | 2014-09-17 | 2014-09-30 | Design Resources Group Architects, A.I.A, Inc. | 44573 | 34814000 | 33427000 | 2016-05-30 | 2016-05-30 | Formal Reprogramming $3,814 funds from FY11 project savings (PN: 090010)
2015-08-31 | 2013 | Army National Guard | 380053 | 95 | 2014-08-18 | 2014-09-24 | Peterson Mechanical, Inc. | AGND14-53 | 468000 |  | 2015-10-30 | 2015-12-04
2015-08-31 | 2013 | Army National Guard | 380053 | 96 | 2014-08-18 | 2014-09-24 | Grotberg Electrical, Inc. | AGND14-54 | 311000 |  | 2015-10-30 | 2015-12-04
2015-08-31 | 2013 | Army National Guard | 380053 |  | 2014-08-18 | 2014-09-24 | Smithco Inc. | AGND14-52 | 1194000 | 2000000 | 2015-10-30 | 2015-12-04
2015-08-31 | 2015 | Army National Guard | 380073 |  | 2015-05-28 | 2015-06-16 | T. F. Powers Construction Co. | AGND15-19 | 10800000 | 12487000 | 2017-06-30 | 2017-06-30
2015-08-31 | 2013 | Army National Guard | 380123 |  | 2013-09-02 | 2013-12-02 | Close Construction Company | AGND14-01 | 1688000 | 1889000 | 2014-08-30 | 2015-06-30
2015-08-31 | 2013 | Army National Guard | 390230 |  | 2013-04-01 | 2013-05-03 | Barton Marlow Company | ADJ-090001 | 11607000 | 8789000 | 2013-12-01 | 2015-03-13 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 390256 |  | 2013-06-07 | 2013-09-19 | Henderson Contractors, Inc. | W91364-13-D-0026 | 2998000 | 3017000 | 2014-07-02 | 2015-06-18 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), NGB 593 being reviewed
2015-08-31 | 2013 | Army National Guard | 390263 |  | 2014-05-12 | 2014-07-09 | KF Construction & Excavating LLC. | ADJ-140002 | 2900000 | 2676000 | 2015-06-15 | 2015-06-15 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2015-08-31 | 2014 | Army National Guard | 390292 |  | 2014-04-04 | 2014-09-04 | Rock Industries, Inc. | W91364-13-D-0003 | 5200000 | 5027000 | 2016-07-31 | 2016-07-31
2015-08-31 | 2013 | Army National Guard | 400066 |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29197000 | 27761000 | 2014-10-01 | 2016-02-22 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2015-08-31 | 2012 | Army National Guard | 400605 |  | 2012-01-12 | 2012-08-16 | Benham Companies, LLC | W90FYQ-09-D-0006-9J01 | 10343000 | 9308000 | 2014-02-19 | 2015-01-16 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 400606 |  | 2012-01-24 | 2012-08-15 | Benham Companies, LLC | W90FYQ-09-D-0006-9J02 | 2995000 | 3161000 | 2014-02-19 | 2014-06-28 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 410026 |  | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 410026D002 | 13800000 | 13190000 | 2013-12-28 | 2014-03-20 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | 420051 |  | 2014-07-09 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 33133000 | 33264000 | 2016-04-22 | 2016-04-22
2015-08-31 | 2009 | Army National Guard | 420511 |  | 2011-08-31 | 2011-09-15 | Lobar Incorporated | DGS 961-20.1 | 5282000 | 5738000 | 2012-10-30 | 2015-05-31 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-08-31 | 2013 | Army National Guard | 420542 |  | 2014-07-22 | 2014-10-24 | Miller Bros. Construction, Inc. | W912KC-14-R-0005 | 1896000 | 1908000 | 2015-11-13 | 2015-11-21 | SIOH all in-house; awaiting NPDES
2015-08-31 | 2012 | Army National Guard | 430010 |  | 2012-09-10 | 2012-09-18 | RB Construction Group Inc. | W912LR-12-C-0005 | 40565000 | 38365000 | 2013-10-28 | 2015-02-28 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($40,565)
2015-08-31 | 2014 | Army National Guard | 430070 |  | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600000 | 4418000 | 2015-05-30 | 2015-05-30
2015-08-31 | 2013 | Army National Guard | 430081 |  | 2013-06-27 | 2013-09-26 | RB Construction Group Inc. | W912LR-13-C-0001 | 18294000 | 17650000 | 2015-09-18 | 2015-11-12 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2015-08-31 | 2013 | Army National Guard | 430622 |  | 2014-04-04 | 2014-08-27 | Integrated Construction Services, Inc. | W912LR-14-B-2005 | 1535000 | 1897000 | 2015-06-26 | 2015-06-26
2015-08-31 | 2013 | Army National Guard | 430804 |  | 2013-06-25 | 2013-09-20 | Design Build S E | W912LR-13-C-0003 | 2128000 | 433000 | 2015-05-08 | 2015-05-08 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 430806 |  | 2013-06-06 | 2013-09-26 | Design Build S E | W912LR-13-C-0002 | 3675000 | 3667000 | 2015-05-15 | 2015-06-19 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 436021 |  | 2012-08-27 | 2012-08-29 | Eastern Construction and Electrical Inc. | W912LR-14-B-2004 | 9200000 | 9758000 | 2015-01-26 | 2015-09-14 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 436023 |  | 2011-07-21 | 2011-09-22 | Remex Co. | W912LR-11-B-0001 | 3077000 | 2562000 | 2012-12-14 | 2012-12-14 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 440009 |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 19316000 | 21433000 | 2014-04-17 | 2015-03-31 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project)
2015-08-31 | 2013 | Army National Guard | 440053 |  | 2014-08-15 | 2015-01-06 | J J Cardosi, Inc | W912LD-11-D-0016 | 1032000 | 1096000 | 2015-02-27 | 2015-02-27
2015-08-31 | 2014 | Army National Guard | 450131 |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | 460003 | 13000000 | 12632000 | 2015-10-30 | 2017-05-06
2015-08-31 | 2010 | Army National Guard | 450252 |  | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. | W912QG-10-C-0005 | 14759000 | 14078000 | 2011-12-14 | 2013-05-01 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2015-08-31 | 2014 | Army National Guard | 450283 |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | 460003 | 13000000 | 12401000 | 2015-10-30 | 2015-10-30
2015-08-31 | 2010 | Army National Guard | 450353 |  | 2010-09-23 | 2010-09-24 | Hendrick Construction | 460114576 | 27936000 | 27304000 | 2012-08-10 | 2013-06-21 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936)
2015-08-31 | 2012 | Army National Guard | 450403 |  | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. | 4600277403 | 4290000 | 4255000 | 2013-10-28 | 2013-10-28 | PL 112-25 (Budget Control Act, 2011), State Purchase Number E24-9751-CA
2015-08-31 | 2011 | Army National Guard | 460085 |  | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. | W912MM-06-2-20002 | 18255000 | 17797000 | 2013-01-14 | 2015-06-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($18,225)
2015-08-31 | 2010 | Army National Guard | 480175 |  | 2010-08-05 | 2010-12-03 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 16441000 | 14196000 | 2012-07-17 | 2015-07-01 | PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-08-31 | 2010 | Army National Guard | 480176 |  | 2010-08-05 | 2010-12-03 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 5700000 | 7021000 | 2012-07-17 | 2015-07-01 | PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-08-31 | 2013 | Army National Guard | 490076 |  | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 137861 | 14508000 | 15859000 | 2014-10-01 | 2014-11-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 490444 |  | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 137862 | 28772000 | 28414000 | 2014-09-30 | 2015-04-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2015-08-31 | 2013 | Army National Guard | 490803 |  | 2013-11-06 | 2014-07-18 | Keller Construction Inc. | 147589 | 2000000 | 1925000 | 2016-01-26 | 2016-01-26
2015-08-31 | 2015 | Army National Guard | 500036 |  | 2015-03-11 | 2015-04-06 | Spates Construction, Inc. | 0000000009999 | 4400000 | 4458000 | 2015-10-31 | 2015-12-31
2015-08-31 | 2012 | Army National Guard | 510307 |  | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | W912LQ-13-C-0001 | 8316000 | 8868000 | 2014-10-09 | 2015-02-27 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2010 | Army National Guard | 520014 |  | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. | W9127P-10-C-0001 | 19978000 | 19493000 | 2012-02-20 | 2013-04-23 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 520034 |  | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | W9127P-11-C-0005 | 24850000 | 22326000 | 2012-08-20 | 2013-08-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 530015 |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | W912DW-13-C-0044 | 33853000 | 31017000 | 2015-08-20 | 2015-09-29 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | 530022 |  | 2011-06-07 | 2011-06-23 | Pease & Sons, Inc. | 2009-205 G 1-1 | 24880000 | 24115000 | 2012-11-03 | 2014-09-23 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), State waiting on demolition of the old CSMS
2015-08-31 | 2013 | Army National Guard | 530035 |  | 2014-08-15 | 2014-08-20 | Absher Construction | 2013-295 G(2-1) | 26000000 | 23855000 | 2016-06-30 | 2016-06-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2015-08-31 | 2013 | Army National Guard | 540075 |  | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734000 | 14988000 | 2015-09-11 | 2015-09-11 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 540085 |  | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | DEK 13002 | 9991000 | 11545000 | 2014-11-12 | 2014-11-12 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2009 | Army National Guard | 540105 |  | 2009-09-24 | 2009-09-25 | The Whiting-Turner Contracting Company | DEFK10003 | 77500000 | 72200000 | 2011-09-28 | 2014-09-30 | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2009 | Army National Guard | 540206 |  | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | DEFK10004 | 4755000 | 4624000 | 2010-08-26 | 2013-03-31 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2015-08-31 | 2011 | Army National Guard | 550139 |  | 2011-08-16 | 2011-09-15 | Buteyn Peterson Construction Co. | NGB-47-11-C-0014 | 5689000 | 5960000 | 2012-10-29 | 2012-10-17 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | 550142 |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673000 | 9631000 | 2014-10-01 | 2015-06-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | 550245 |  | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. | NGB-47-12-C-0002 | 4250000 | 3935000 | 2013-05-20 | 2014-05-30 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2015-08-31 | 2014 | Army National Guard | 560081 |  | 2013-12-16 | 2014-03-11 | Layton Construction Company, Inc. | 13002900601 | 10200000 | 10124000 | 2015-03-31 | 2016-05-20
2015-09-10 | 2014 | Army Reserve | 65277 |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 11895000 | 12978000 | 2015-09-30 | 2015-09-30
2015-09-10 | 2012 | Army Reserve | 67466 |  | 2012-05-16 | 2012-09-18 | IKHANA, LL | W912QR-12-C-0055 | 16212000 | 16472000 | 2014-03-19 | 2014-06-12
2015-09-10 | 2013 | Army Reserve | 67652 |  | 2014-05-06 | 2015-03-31 | Cox Construction Co. | W912QR-15-C-0007 | 24044000 | 24084000 | 2017-02-12 | 2017-02-12
2015-09-10 | 2012 | Army Reserve | 67658 |  | 2011-11-29 | 2012-04-16 | Liberty Mutual Insurance Company | W912QR-12-C-0028 | 10545000 | 10690000 | 2013-10-18 | 2013-10-18
2015-09-10 | 2013 | Army Reserve | 67659 |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21779000 | 23005000 | 2015-11-04 | 2015-12-31
2015-09-10 | 2013 | Army Reserve | 67660 |  | 2012-12-28 | 2013-06-12 | MACNAK Korte Team LLC | W912QR-13-C-0014 | 16649000 | 18141000 | 2015-05-01 | 2015-05-01
2015-09-10 | 2014 | Army Reserve | 67663 |  | 2014-08-01 | 2015-08-28 | Sheffield Korte Joint Venture | W912QR-15-C-0027 | 20803000 | 20803000 | 2017-08-27 | 2017-08-27
2015-09-10 | 2012 | Army Reserve | 67672 |  | 2011-11-16 | 2012-03-29 | Group III Mgt. Inc | W912QR-12-C-0021 | 10123000 | 11126000 | 2013-09-23 | 2014-09-18
2015-09-10 | 2012 | Army Reserve | 67673 |  | 2012-02-14 | 2012-05-15 | Hunt Construction Group | W912QR-12-C-0029 | 44568000 | 48366000 | 2015-01-29 | 2015-09-25
2015-09-10 | 2013 | Army Reserve | 67689 |  | 2013-01-28 | 2013-06-14 | KEPA-TCI JV LLC | W912QR-13-C-0016 | 9302000 | 10113000 | 2014-11-10 | 2015-08-20
2015-09-10 | 2012 | Army Reserve | 67691 |  | 2011-11-16 | 2012-05-03 | SCMC, LLC | W912QR-12-C-0025 | 18167000 | 19497000 | 2015-01-04 | 2015-05-30
2015-09-10 | 2012 | Army Reserve | 67713 |  | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | W912QR-12-C-0068 | 13454000 | 15805000 | 2014-07-10 | 2015-11-23
2015-09-10 | 2013 | Army Reserve | 67715 |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31523000 | 32262000 | 2015-08-30 | 2015-08-30
2015-09-10 | 2013 | Army Reserve | 68077 |  | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890000 | 7890000 | 2016-05-30 | 2016-05-30
2015-09-10 | 2011 | Army Reserve | 69421 |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4504000 | 4564000 | 2014-03-21 | 2014-05-01
2015-09-10 | 2010 | Army Reserve | 69430 |  | 2011-07-28 | 2011-09-29 | Lobar Inc. | W912QR-11-C-0062 | 18388000 | 20326000 | 2013-11-08 | 2015-06-12
2015-09-10 | 2012 | Army Reserve | 69432 |  | 2012-12-21 | 2013-03-06 | MACNAK KORTE DESIGN BUILD LLC | W912QR-13-C-0009 | 14338000 | 14032000 | 2014-07-29 | 2014-08-15
2015-09-10 | 2010 | Army Reserve | 69461 |  | 2014-02-11 | 2014-07-10 | Carothers Construction, Inc. | W912QR-14-C-0024 | 13543000 | 17567000 | 2015-12-21 | 2016-01-29
2015-09-10 | 2010 | Army Reserve | 69471 |  | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | W912QR-12-C-0022 | 16009000 | 16320000 | 2013-09-24 | 2013-10-06
2015-09-10 | 2010 | Army Reserve | 69568 |  | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | W912QR-11-C-0046 | 12356000 | 12771000 | 2013-08-06 | 2013-11-16
2015-09-10 | 2011 | Army Reserve | 69599 |  | 2012-07-25 | 2012-09-25 | J. Kokolakis Contracting, Inc. | W912QR-12-C-0057 | 12465000 | 13312000 | 2014-05-12 | 2014-05-15
2015-09-10 | 2014 | Army Reserve | 69669 |  | 2014-01-31 | 2014-06-05 | Ranco Construction, Inc. | W912QR-14-C-0021 | 8783000 | 8872000 | 2015-12-14 | 2015-12-14
2015-09-10 | 2011 | Army Reserve | 70641 |  | 2011-08-18 | 2011-11-23 | Anthony & Gordon Construction Co, Inc. | W912QR-12-C-0004 | 13345000 | 13883000 | 2013-05-06 | 2013-09-25
2015-09-10 | 2011 | Army Reserve | 70654 |  | 2011-11-15 | 2012-03-14 | The Vertex Companies | W912QR-12-C-0014 | 9013000 | 9189000 | 2013-08-12 | 2013-11-13
2015-09-10 | 2013 | Army Reserve | 71482 |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56039000 | 61917000 | 2016-05-17 | 2016-05-27
2015-09-10 | 2013 | Army Reserve | 71720 |  | 2012-12-13 | 2013-06-28 | Eastern Construction & Electric, Inc. | W912QR-13-C-0015 | 3094000 | 3516000 | 2014-07-17 | 2015-06-30
2015-09-10 | 2014 | Army Reserve | 71769 |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653000 | 4658000 | 2016-04-09 | 2016-04-09
2015-09-10 | 2014 | Army Reserve | 71900 |  | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129000 | 22139000 | 2016-11-01 | 2016-11-14
2015-09-10 | 2013 | Army Reserve | 71997 |  | 2013-01-22 | 2013-08-23 | TCI Architects Engineers Contractor Inc. | W912QR-13-C-0026 | 7744000 | 8189000 | 2015-02-04 | 2015-04-01
2015-09-10 | 2014 | Army Reserve | 71999 |  | 2013-12-12 | 2014-03-31 | Wilson Brigadier Joint Venture | W912QR-14-C-0013 | 5905000 | 6688000 | 2015-08-25 | 2015-09-19
2015-09-10 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19101000 | 19621000 | 2015-06-08 | 2015-06-08
2015-09-10 | 2013 | Army Reserve | 72160 |  | 2013-03-28 | 2013-08-27 | Pre Con Industries, Inc. | W912QR-13-C-0027 | 4384000 | 4540000 | 2014-11-03 | 2015-02-23
2015-09-10 | 2014 | Army Reserve | 72284 |  | 2014-08-13 | 2014-09-30 | Bara Infoware Inc. | W912QR-14-C-0053 | 16187000 | 16164000 | 2016-05-22 | 2016-07-26
2015-09-10 | 2011 | Army Reserve | 74220 |  | 2011-05-19 | 2011-09-23 | Liberty Mutual Insurance Company | W912QR-11-C-0048 | 8916000 | 8956000 | 2013-03-24 | 2013-09-17
2015-09-10 | 2010 | Army Reserve | 75110 |  | 2011-10-04 | 2012-01-26 | Leetex Construction LLC | W912QR-12-C-0010 | 9470000 | 10447000 | 2013-09-12 | 2014-01-10
2015-09-10 | 2015 | Army Reserve | 81959 |  | 2015-03-06 | 2015-07-17 | ETD-TCG, LLC with RSP Architects | W912QR-15-C-0018 | 5215000 | 5215000 | 2016-12-18 | 2016-12-18
2015-08-31 | 2013 | Defense Finance and Accounting Service | 80230 |  | 2013-04-24 | 2013-07-30 | US Army COE Guyco, INC | W9127S-09-D-6006 | 12903000 | 12903000 | 2015-03-05 | 2015-12-02
2015-08-31 | 2008 | Defense Health Agency | 47298 | 47298 | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110000 | 282778000 | 2013-07-23 | 2014-05-13 | 8/24/15 Fort Riley Replacement Hospital. NWK sent letter to the Contractor asking for their projection for completion, particularly life safety deficiencies (necessary for BOD). Current CCD: 13 May 2014 Placement: 99% actual vs. 100% scheduled (as of June's pay estimate). Construction in progress: TAB/commissioning nearing completion (Two exhaust fans remain). Inspections continue. Final inspections are progressing. Numerous life safety deficiencies remain unaddressed. HFPA furniture install started 06 July. Comments: The contractor exceeded the required completion date of 13 May 2014. Liquidated damages are being withheld at $16,500 per calendar day. Corporate/senior manager engagement continues. No good estimate as to when BOD will actually occur. First patients will be in the building in mid-Jan. Ribbon cutting currently scheduled for 5 Jan 16.
2015-08-31 | 2013 | Defense Health Agency | 51639 | 51639 | [8 empty] | Omaha District met with customers and City of Colorado Springs to coordinate design requirements and schedules during the week of 31 Aug 15. Expect request for P&D funds and AE award in near future.
2015-08-31 | 2011 | Defense Health Agency | 51740 | 51740 | 2011-05-13 | 2011-08-26 | Ilsung Construction Co. Ltd. | W912UM-11-C-0024 | 9821000 | 10169000 | 2013-05-13 | 2014-04-23 | The Carroll Dental Clinic OIC and NCOIC were in the lead for a ribbon cutting ceremony, however, per HFPO, a ceremony does not appear to be occurring. Awaiting final billing ($17,794.00) from DLA for LOGCAT F equipment training.
2015-08-31 | 2012 | Defense Health Agency | 51969 | 51969 | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | W9126G-12-C-0050 | 28291000 | 29084000 | 2014-10-30 | 2015-12-23 | Final inspection held 28 Aug - 1 Sep; inspection failed due to several equipment problems . Manufacturers and installers on-site to troubleshoot. Working final punch list items. Nutrition Care transition scheduled to start 14 Sep and end 14 Oct. Back in business date is scheduled for 15 Oct but could slip (day for day) if equipment issues takes longer than 9 Sep to fix. Contractor filed seven claims in Nov 14 totaling $1.4M; KO denied; DCAA audit ongoing, Alternative Dispute Resolution (ADR) tentatively scheduled for 13-14 Oct 15.
2015-08-31 | 2007 | Defense Health Agency | 52330 | 52330 | 2007-02-16 | 2007-07-19 | Caddell Construction Co. Inc. | W91278-07-C-0037 | 40902000 | 45600000 | 2009-12-17 | 2011-06-05 | Water intrusion problem update – Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. Construction Contractor reviewed their records and provided a response to AF reports 30 Jan 2015. A-E provided response on 2 Feb 2015. CESAM reviewed responses and is currently negotiating acquisition of building envelope specialist to prepare independent determination addressing the responsibilities of each party and estimate of damages by each party. Awarded pending. We expect initial findings within 180 days of award.
2015-08-31 | 2008 | Defense Health Agency | 52330 | 67647 | 2007-02-16 | 2007-07-19 | Caddell Construction Co. Inc. | W91278-07-C-0037 | 32890000 | 42183000 | 2009-12-17 | 2011-06-05 | See 52330, Clinic Replacement, Inc 1
2015-08-31 | 2008 | Defense Health Agency | 52332 | 52332 | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929000 | 26866000 | 2012-05-15 | 2012-07-13 | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. German government confirmed 23 Jun 2015 that resolution will not be this fiscal year.
2015-08-31 | 2009 | Defense Health Agency | 55918 | 55918 | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034000 | 13672000 | 2011-02-07 | 2011-06-22 | Residual closeout issues.
2015-08-31 | 2007 | Defense Health Agency | 58395 | 58395 | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657000 | 2657000 | 2008-06-13 | 2008-06-08 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | 58395 | 58395 | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472000 | 1472000 | 2009-02-15 | 2009-02-13 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | 58395 | 58395 | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706000 | 706000 | 2010-04-13 | 2010-04-13 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | 58395 | 58395 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465000 | 2465000 | 2009-07-24 | 2009-07-24 | Work complete. Contracts closed.
2015-08-31 | 2007 | Defense Health Agency | 58395 | 58395 |  | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 2866000 | 2866000 | 2011-05-06 | 2013-10-31 | Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project.
2015-08-31 | 2007 | Defense Health Agency | 58395 | 58395 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 15736000 | 16161000 | 2014-05-31 | 2017-07-01 | FY07. See FY2012 remarks. Contract active, but all funds on this increment obligated. Building to be operational NOV 2017.
2015-08-31 | 2008 | Defense Health Agency | 58395 | 63418 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 131264000 | 138491000 | 2014-05-31 | 2017-07-01 | FY 08. Contract completion date is 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2009 | Defense Health Agency | 58395 | 63419 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 185526000 | 185630000 | 2014-05-31 | 2017-07-01 | FY09. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract complete date is 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2010 | Defense Health Agency | 58395 | 63420 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 94000000 | 100180000 | 2014-05-31 | 2017-07-01 | FY10. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract completion date is 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2010 | Defense Health Agency | 58395 | 63420 |  | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 496000 | 525000 | 2013-10-31 | 2013-10-31 | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-08-31 | 2011 | Defense Health Agency | 58395 | 65324 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 13497000 | 12893000 | 2014-05-31 | 2017-07-01 | FY11. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract completion date is 16 Dec 14; liquidated damages will be assessed. Approx $90,000 FY2011 P&D funds for parking design being returned.
2015-08-31 | 2011 | Defense Health Agency | 58395 | 65324 |  | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 638000 | 2013-10-31 | 2013-10-31 | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-08-31 | 2012 | Defense Health Agency | 58395 | 71101 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 66955000 | 85381000 | 2014-05-31 | 2017-07-01 | FY12. Scheduled 100%, Actual 95%. T&E change under negotiation with contractor. Re-installation of BSL4 lab coatings is 95% complete; cleaning smoke-damaged BSL3 area equipment, and commissioning remainder of facility. Plan is to accept admin, BSL2 and BSL3 labs Jun 2016 to start CDC certification and accept BSL4 labs Jul 2017. Contract completion 16 Dec 14; liquidated damages will be assessed.
2015-08-31 | 2012 | Defense Health Agency | 58395 | 71101 | 2015-03-09 | [7 empty] | DA memo dated 24 Jun 2015 and USACE design directive dated 25 Jun 2015 provided code 7 (D-B). DHA-conducted planning charrette was held week of 6 July 2015. Award of A-E task orders for borings and survey will be awarded by 30 Sep 2015 to obligate expiring FY11 P&D funds.
2015-08-31 | 2012 | Defense Health Agency | 58395 | 71101 | 2015-03-09 | [7 empty] | Contract being prepared for award. Maryland Dept of Environment requires USAG Ft Detrick to start Pond 7A construction for regional stormwater management. Project requirment was advertised as the base bid component of a combined solicitation with DODM Security Fencing/Equipment and MCA Entry Control Point projects as options due to site overlap.
2015-08-31 | 2013 | Defense Health Agency | 58395 | 78210 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 0 | 2014-05-31 | 2017-07-01 | Utilities, DDC, Certification and related costs.
2015-08-31 | 2014 | Defense Health Agency | 58395 | 78211 | [8 empty] | Remainder of certification costs this FY. South parking/demolition is budgeted for this PN but facilities are likely not able to be available for demolition until funds expire. We will coordinate a way ahead on this when main facility is closer to turnover.
2015-08-31 | 2014 | Defense Health Agency | 58395 | 78211 | [8 empty] | Notional schedule shown; dependent on CDC/DA Safety certification of USAMRIID primary facility and vacation/decommissioning of existing buildings 1408/1412/1414/1415. Due to delay in main contract, projections for award are moved out 2 years.
2015-08-31 | 2009 | Defense Health Agency | 59220 | 59220 | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500000 | 29404000 | 2015-08-03 | 2015-08-03 | Contract completion was 20 July 2015. Interior punchlist reduced to allow HFPA to move in 3 Aug as scheduled. Chilled water tie-in occurred 13 Aug. Numerous Mechanical and Curtain Wall punchlist remain. Expect 3 wks to resolve Mechanical issue and 6-8 wks on ext curtain wall. Ribbon Cutting Target date in 2 Oct 15.
2015-08-31 | 2010 | Defense Health Agency | 61401 | 61401 | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075000 | 10119000 | 2013-01-10 | 2015-01-08 | Remaining punchlist items completed. All pending modifications/REAs are settled. Project is in closeout phase.
2015-08-31 | 2010 | Defense Health Agency | 61536 | 61536 | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | W912DR-10-C-0087 | 13478000 | 13858000 | 2012-09-16 | 2013-05-23 | In fiscal closeout. Construction contract held open longer to address a warranty repair.
2015-08-31 | 2009 | Defense Health Agency | 62189 | 62189 | 2008-10-27 | 2009-04-03 | Hensel-Phelps Const. Co. | W912BV-09-D-2016 | 47615000 | 51375000 | 2011-10-26 | 2012-02-09 | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub.
2015-08-31 | 2011 | Defense Health Agency | 62886 | 62886 | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | W912DR-12-C-0004 | 4270000 | 4624000 | 2013-11-09 | 2015-02-10 | Facility turned over to garrison. Punchlist is complete.
2015-08-31 | 2008 | Defense Health Agency | 63864 | 63864 | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | W91DS-08-C-0019 | 27483000 | 35963000 | 2011-02-18 | 2013-12-12 | Financial closeout pending A-E Damages Resolution
2015-08-31 | 2009 | Defense Health Agency | 64156 | 64156 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398000 | 17027000 | 2013-06-01 | 2015-06-10 | Final BOD for Building E was 10 Jun 15 with a follow on contract to investigate and fix systems commissioning and fume hoods in the lab. Currently working to get Facility Dynamics Engineering under contract to troubleshoot and establish COAs/Solutions to resolve the problems; targeting contract award o/a 9 Sep 15. Project fiscal closeout will follow pending resolution of remaining punchlist items and settlement of outstanding requests for equitable adjustment.
2015-08-31 | 2008 | Defense Health Agency | 64179 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 107589000 | 135926000 | 2011-07-15 | 2013-05-01 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2015-08-31 | 2009 | Defense Health Agency | 64179 | 64180 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 265100000 | 279273000 | 2011-07-15 | 2013-05-01 | See above.
2015-08-31 | 2010 | Defense Health Agency | 64179 | 69840 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 13748000 | 243943000 | 2011-07-15 | 2013-05-01 | See above.
2015-08-31 | 2011 | Defense Health Agency | 64179 | 70990 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 37554000 | 85520000 | 2011-07-15 | 2013-05-01 | See above.
2015-08-31 | 2008 | Defense Health Agency | 64188 | 64188 | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | W9126G-08-C-0024 | 33382000 | 37382000 | 2010-05-10 | 2010-05-10 | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2015-08-31 | 2010 | Defense Health Agency | 64241 | 64241 | 2009-09-16 | 2010-05-04 | Forrester Construction Company | W912DR-10-C-0067 | 7541000 | 8818000 | 2011-09-10 | 2012-12-06 | Construction Contract and Project in Close Out Phase. Final 1354 for CIP Transfer is in process. Fiscal Closeout now 31 OCT 2015, along with PN 71251.
2015-08-31 | 2008 | Defense Health Agency | 64473 | 64473 | 2008-07-29 | 2008-09-18 | The Korte Company | 912DW-08-C-0018 | 17497000 | 18181000 | 2010-02-20 | 2010-03-17 | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2015-08-31 | 2012 | Defense Health Agency | 65030 | 65030 | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co. | N40083 12 C 0001 | 5835000 | 6195000 | 2013-09-13 | 2014-08-08
2015-08-31 | 2010 | Defense Health Agency | 65270 | 65270 | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133000 | 166787000 | 2014-10-15 | 2016-03-15 | 3rd UXO found; work is stopped, but has restarted
2015-08-31 | 2009 | Defense Health Agency | 65731 | 65731 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 6887870 | 7070197.9 | 2010-08-08 | 2010-08-31 | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC
2015-08-31 | 2009 | Defense Health Agency | 65731 | 65731 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 12000000 | 12658000 | 2013-06-01 | 2014-12-22 | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC. $9,000 rescinded as a result of Sequestration (04/29/13).
2015-08-31 | 2010 | Defense Health Agency | 65731 | 67180 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 461470 | 824748.6 | 2010-08-08 | 2010-08-31
2015-08-31 | 2010 | Defense Health Agency | 65731 | 67180 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30
2015-08-31 | 2010 | Defense Health Agency | 65731 | 67180 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 100375000 | 103745328.3 | 2013-06-01 | 2014-12-22 | Main Building $142,857,143 FY10 Increment Awarded at $100,375,000 on 5 Mar 10 ($109,567,007 funded per D. Pritchett 17 Mar 10 email)
2015-08-31 | 2011 | Defense Health Agency | 65731 | 67181 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 94608000 | 96044506.5 | 2013-06-01 | 2015-06-10 | Full FY11 MILCON increment placed against contract.
2015-08-31 | 2012 | Defense Health Agency | 65731 | 67182 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 31686000 | 2013-06-01 | 2015-06-10 | Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 30 Apr 2015 for remainder of spaces. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Currently contracting for a third party investigation to provide options and COAs to address issues preventing E-Wing Labs from operating as intended. Estimated contract award date o/a 9 Sep 15.
2015-08-31 | 2011 | Defense Health Agency | 66588 | 66588 | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 32103000 | 32103000 | 2016-05-30 | 2016-09-04 | Addition turned over 26 Jun 2015. Ribbon cutting for addition held 14 Aug 15. Renovation of the existing clinic began 11 Aug 15. Final construction completion (Renovation) may be delayed due to contractor delay request for 95 days. BauAmt currently evaluating delays.
2015-08-31 | 2011 | Defense Health Agency | 66693 | 66693 | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | W912GB-09-C-0029-NA | 34294000 | 34376000 | 2016-04-12 | 2016-04-12 | Current work includes: Construction of interior drywall walls is ongoing (2nd flr), floor screed is ongoing (1st & 2nd flr). Electrical and mechanical rough-in is ongoing (1st flr & 2nd). Communications cabling is ongoing (1st & 2nd flr.), insulation of the ductwork is ongoing (1st & 2nd flr). Sprinkler and sanitary sewer line install is ongoing (1st & 2nd flr.). Install of radiators (1st flr.) install of wall plaster, interior walls (1st flr), and install of ceiling grid (1st flr) has begun.Install of vegetative roof is ongoing. CRITICAL - CAT E/F Equipment must be awarded by 30 Sep 2015 as funds expire for new obligations. MEDCOM is aware and believes they can meet this date (DLA contract being used for ~$460k). Anticipate receiving funds 3 Sep. German government negotiating commissioning modification.
2015-08-31 | 2011 | Defense Health Agency | 67949 | 67949 | 2011-08-19 | 2012-02-14 | Rich Moe Enterprises, LLC | W912DR-12-C-0001 | 1701000 | 1701000 | 2013-04-02 | 2013-04-01 | Segment 1 - Project Closed. Segment 2 will be awarded on 18 Sept 15.
2015-08-31 | 2011 | Defense Health Agency | 67949 | 67949 | 2015-03-09 | [7 empty] | RTA date for Fence Segment 2 was 30 Jan 15. Work structured as contract option in combined solicitation with USAMRIID Replacement North Parking which establishes overall site contours for fence construction. Source selection complete. Requested award authority/funding; awaiting receipt.
2015-08-31 | 2011 | Defense Health Agency | 67951 | 67951 | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308000 | 15614000 | 2014-07-08 | 2015-11-30 | % Complete (Scheduled/Actual): 100/97 . Electrical subcontractor remains behind schedule.
2015-08-31 | 2011 | Defense Health Agency | 67953 | 67953 | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468000 | 3944000 | 2012-11-01 | 2015-10-30 | % Complete (Scheduled/Actual): 100/98 Contractor having difficulty completing pump facility. LD's being assessed from 30 May 2014. BOD slipped due to contractor performance issues. Bonding company has been contacted. Tank has been filled and passed testing.
2015-08-31 | 2009 | Defense Health Agency | 68974 | 68974 | 2011-02-01 | 2011-04-22 | Federal Republic of Germany | W912GB-09-D-0048 | 378000 | 402000 | 2011-01-31 | 2011-12-09
2015-08-31 | 2009 | Defense Health Agency | 68974 | 68974 | 2011-01-08 | 2011-03-14 | Wayss & Freytag |  | 1572000 | 1548000 | 2011-01-31 | 2011-12-09
2015-08-31 | 2010 | Defense Health Agency | 69353 | 69353 | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | W912HN-11-C-0002 | 14725000 | 15287000 | 2012-10-12 | 2012-11-15 | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14. Financial close-out underway.
2015-08-31 | 2007 | Defense Health Agency | 69427 | 69427 | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV | W91236-07-C-0053 | 649025000 | 9428000 | 2011-03-01 | 2012-01-31 | Project ready for closeout
2015-08-31 | 2007 | Defense Health Agency | 69427 | 69865 | 2007-06-12 | 2010-01-23 | Turner/Gilbane JV | W91236-07-C-0053 |  | 119266000 | 2011-03-01 | 2012-01-31 | All Unobligated funds $245K were returned. 1354 is being prepared.
2015-08-31 | 2007 | Defense Health Agency | 69427 | 77071 | 2007-06-12 | 2010-10-20 | Turner/Gilbane JV | W91236-07-C-0053 |  | 211800000 | 2011-03-01 | 2012-01-31 | See above.
2015-08-31 | 2008 | Defense Health Agency | 69626 | 69626 | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | W9126G-08-C-0036 | 18512000 | 19120000 | 2011-07-15 | 2013-05-01 | Contract closeout ongoing.
2015-08-31 | 2008 | Defense Health Agency | 70235 | 70235 | 2009-04-08 | 2009-09-28 | Turner Construction Company | W912HN-09-C-0045 | 230018000 | 275275000 | 2013-02-03 | 2014-05-19 | Commissioning of systems continues. Final TAB reports resubmitted and in review. Contingencies at District: $1,307.17. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 30 Oct 15. Benning DPW will assign # upon receipt of final 1354.
2015-08-31 | 2012 | Defense Health Agency | 70351 | 70351 | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400000 | 23770000 | 2014-06-23 | 2016-01-15 | Contingencies at District: $69,771.04. Contractor has been issued an Interim Marginal CCASS. Fire Alarm testing + ICRA inspection completed in Emergency Dept with no deficiencies. Ceramic tile + finishes nearing completion phase 7. Temporary ED trailers have were demolized on 25 Jul 15. Negotiations underway on DHA approved User Change to delete work on 2 floors from the contract.
2015-08-31 | 2009 | Defense Health Agency | 70354 | 70354 | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 159834000 | 188955000 | 2015-03-16 | 2017-05-17 | Significant changes in processes impacting water storage and the central utility plant are being resolved. Full impact of the changes on the project are unknown and continue to be addressed by the delivery team. Senior leadership continues to engage regularly to assist in resolution of project issues. Engineers continuously evaluating project design to identify concerns and remedies for way-ahead. Time impacts associated with past changes are currently in negotiation which should not result in considerable growth in time beyond previously reported. Senior leadership continues to engage regularly to assist in resolution of project issues. Team is working through engineering challenges impacting concrete decks. The MCX and Hospital CX are engaged to address concrete decks and engineering concerns. All other unaffected work activities are continuing per plan.
2015-08-31 | 2012 | Defense Health Agency | 70438 | 70438 | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company | W912QR-12-C-0036 | 43466000 | 51638000 | 2015-02-21 | 2015-10-27 | The Contractor and his subs continue to make progress in renovation work. MILCON funds in the amount of $5,402,819 will be needed as the large claims that have been settled. Contract completion will be 27 Oct 2015. All work will be completed by this date. This funding will put the project $498,870 over the Sequestration PA of $55,886,000. (100.89% over PA). The final negotiations resolved concurrent delays: Case 58, Curtain wall $4,706,237 and 187 days. Case 65 Part II Med Air User change $0. Case 111 Part II Asbestos Insulation in Alt (Part 2 Final) $464,623 and 29 days.
2015-08-31 | 2011 | Defense Health Agency | 70482 | 70482 | 2010-11-19 | 2011-06-03 | McCarthy Building Companies, Inc. | W912HN-11-C-0006 | 23050000 | 25062000 | 2013-06-20 | 2014-05-19 | Contingencies at District: $0. CAT E&F remaining at Distirct: $0. Financial close-out underway.
2015-08-31 | 2012 | Defense Health Agency | 70579 | 70579 | 2012-10-05 | 2013-02-13 | Structural Associates Inc. | W912DS-13-C-0022 | 9934000 | 9937000 | 2015-03-06 | 2015-03-06 | BOD 5 MAR 15. Remaining punchlist items all to be complete NLT 30 SEP 15.
2015-08-31 | 2012 | Defense Health Agency | 70580 | 70580 | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | W91DS-13-C-0002 | 4370000 | 4370000 | 2015-01-09 | 2014-12-19 | BOD 19 DEC 14. MOD work to repair Chiller line near completion (estimated completion of repair 9 SEP 15)
2015-08-31 | 2012 | Defense Health Agency | 70597 | 70597 | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | W91278-12-C-0028 | 8897000 | 9137000 | 2014-10-07 | 2014-10-07 | Final document turnover in process. Performing post BOD changes at user request, PT room flooring, walk off matts, rear gate padlocks and door hardware. Final Pay anticipated April, 2015.
2015-08-31 | 2011 | Defense Health Agency | 71251 | 71251 | 2009-09-16 | 2011-05-17 | Forrester Construction Company | W912DR-10-C-0067 | 2832000 | 3185000 | 2011-09-10 | 2012-12-06 | Project and Contract is in Final Closeout phase. Final 1354 for CIP transfer is in process. Fiscal Closeout now 31 OCT 2015, along with Project # 64241.
2015-08-31 | 2013 | Defense Health Agency | 71317 | 71317 | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744000 | 4114000 | 2016-12-30 | 2017-11-07
2015-08-31 | 2010 | Defense Health Agency | 71318 | 71318 | 2009-10-28 | 2010-02-26 | JE Dunn Construction Company | W9126G-08-D-0057 | 22680000 | 23591000 | 2012-01-06 | 2012-09-01 | Retainage on the project recently paid, processing close out. The project funds have been returned.
2015-08-31 | 2013 | Defense Health Agency | 71325 | 71325 | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536000 | 47116000 | 2016-10-23 | 2016-12-22 | Structural steel erection continues. Contingencies at District: $279,302.19. Cat E&F Equip funds at District: $1,723,000
2015-08-31 | 2012 | Defense Health Agency | 71408 | 71408 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688000 | 18689000 | 2016-12-06 | 2017-11-08 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2015-08-31 | 2012 | Defense Health Agency | 71503 | 71503 | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Construction | N69450 12 C 0754 | 19096000 | 21131000 | 2014-09-09 | 2016-01-31 | Notification of contract termination 5 May 2015
2015-08-31 | 2013 | Defense Health Agency | 71507 | 71507 | 2013-02-28 | 2013-12-18 | Turner Construction Company | N40080 14 C 0154 | 41408000 | 42190000 | 2015-10-15 | 2016-02-12
2015-08-31 | 2010 | Defense Health Agency | 71550 | 71550 | 2010-06-16 | 2010-12-14 | Vinci Construction UK Ltd. | CT/INT21/13625 | 13425000 | 12421000 | 2012-08-10 | 2012-09-28 | Estimated financial closure: 31 Dec 2015. The base originally requested an additional $65,000 to replace the clinic main entrance doors. This was inadequate and a further $80,000 has been requested. Base will now have $145,000 to replace the doors. Update 02 Sept 2015: Base are ready to place the order for the structural survey and will advise of the programme accordingly.
2015-08-31 | 2010 | Defense Health Agency | 71550 | 71550 | 2013-04-05 | 2013-06-15 | VolterFitzpatrick | DEUSF/13214 | 68000 | 68000 | 2013-08-30 | 2013-08-30
2015-08-31 | 2010 | Defense Health Agency | 71550 | 71550 | 2014-08-20 | 2014-08-25 | Vinci Facilities | CT/INT21/13625 | 69000 | 69000 | 2015-01-30 | 2015-06-30 | Contractor has queried the original steelwork design, DIO currently investigating the query. No progress on site until resolved. DIO cannot close main project until this local order is complete. Awaiting contractor to provide detail to support claim that original steelwork design is not to standard.
2015-08-31 | 2009 | Defense Health Agency | 71653 | 71653 | 2010-06-11 | 2010-09-01 | Clark/McCarthy, JV | N62473 10 C 0001 | 418039000 | 425895000 | 2014-01-07 | 2014-01-07 | Multiple residual closeout issues.
2015-08-31 | 2013 | Defense Health Agency | 71679 | 71679 | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture | W912DQ-13-C-4017 | 10687000 | 10505000 | 2015-02-19 | 2015-02-19 | Facility remains unoccupied (may be a staffing issue). Field staff have been unable to get a date for aoccupancy from the User. Seasonal commissioning scheduled for 25 Aug 15. Contractor has responded to minor warranty items and punchlist. Contractor is also replacing 2 boiler flues (1 complete, 1 awaiting parts).
2015-08-31 | 2008 | Defense Health Agency | 71857 | 71857 | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 31112000 | 32854000 | 2013-01-12 | 2013-07-15 | Funds used for FY00 Settlement, Ft. Wainwright. Residual activity on project funding items.
2015-08-31 | 2012 | Defense Health Agency | 72292 | 72292 | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778000 | 44473000 | 2016-10-14 | 2017-03-17 | Contingencies at district: $361,300 of which $172,675 is for temp. swing space. Executed Option 5 on Trailer Lease. Approval to descope received 5 June 2015. Final inspection of ED complete. Contractor working on punch listfor ED.
2015-08-31 | 2015 | Defense Health Agency | 72414 | 72414 | 2015-04-21 | [7 empty] | Received FAD for $6M in FY11 funds on 4 Sep 15. The project Source Selection Evaluation Board (SSEB) has established an apparent "best value" des/bld MATOC contractor selectee. The request for authority to award, along with the preaward CWE is being prepared and should be available on Tuesday, 9/8/15. The DODM-MILCON portion of the preaward CWE will indicate a cost that will be above the project's DODM-MILCON Programmed Amount (PA), approx. 110% of PA. The preaward CWE will be based on full scope, including the demolition of the existing temporary Dental Clinic option.
2015-08-31 | 2013 | Defense Health Agency | 72419 | 72419 | 2013-07-26 | 2013-09-26 | Seohee Construction Co. Ltd. | W912UM-13-C-0025 | 22361000 | 22423000 | 2017-08-08 | 2017-10-24 | Contingency Amounts: District $253,034; HQ Mgmt $795,500. Ongoing work: TPO membrane for roofing, EIFS, Main electrical work, HVAC duct work, steel framing/drywall, upper level waste waterlines, and lower level wall painting.
2015-08-31 | 2013 | Defense Health Agency | 72420 | 72420 | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. | W912UM-13-C-0018 | 8544000 | 9056000 | 2015-02-25 | 2015-03-29 | Contingency Amounts: District $1,811; HQ Mgmt $0. Final Inspection was completed and keys turned over 27 Mar 15. A simple ribbon cutting ceremony was conducted 6 May 2015. No invitations were sent to outside organizations. Completed pending modifications of LPG system in room 141, explosive proof fan in room 126, and exit lights at 2nd floor on 29 Jul 2015, and washer/disinfector in DIPC room on 13 Aug 2015. A modification to include Government Furnished Government Installed equipment in the BIM is being processed.
2015-08-31 | 2010 | Defense Health Agency | 72430 | 72430 | 2010-06-11 | 2010-08-19 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0005) | 41566000 | 45105000 | 2013-02-20 | 2013-08-30 | 1. Phase 1B is complete and turned over to the Air Force. BOD was 19 Nov 13 and the Interim DD 1354 was signed by BCE on 5 Dec 13. The 1B warranty expired in Nov 2014. 2. Post Warranty Deficiencies: a. JE Dunn completed replacement of exterior stone block on the facade of 1B b. Repair of the concrete cracking in the garage (Ph 1A) was completed, but the work is under review c. JE Dunn’s plan to address the stone block on the parking garage is still pending d. JE Dunn has indicated they intend to address the Ph 1B bathrooms ABA/ADA Non-compliance; JED corrective action plan received on 8/26, reviewed by USACE and response sent to JED on 9/1.
2015-08-31 | 2010 | Defense Health Agency | 72430 | 72430 | 2010-06-11 | 2010-08-31 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0006) | 23216000 | 24153000 | 2012-02-26 | 2012-11-30 | Remarks noted above.
2015-08-31 | 2011 | Defense Health Agency | 72430 | 72752 | 2011-05-20 | 2011-09-28 | Skanska USA Building Inc. | W9126G-11-C-0053 | 80558000 | 98456000 | 2013-10-01 | 2015-12-22 | 1. Phase 2 is 93% complete / 93% scheduled 2. The Ph 2 BOD will shift as noted under Lackland ASC Ph 3 from 1 Oct to 22 Dec 2015 3. Including pending modifications the Ph 2 CWE remains within the current authorization A) resolution of generators may require additional modification to Ph 2 contract, and B) delivery of O2 for medical gas certification (action with 59th MW) *Generator Issues - risk is high to impact the BOD/IO start
2015-08-31 | 2010 | Defense Health Agency | 72481 | 72481 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 7782000 | 11366000 | 2016-11-26 | 2017-01-01 | NOTE 1 : Hospital - Construction Progress: Sch. 53% Act. 34%: Current contractual construction completion date is 1 Jan 2017. The estimated construction completion is currently 4th Q 2017 with a BOD of 3 Oct 2017. Placement to date: $217.0M as of 5 Aug 15. Momentum, subcontractor control, and quality continue to impact production. Reset meetings have been held at the Principal and field levels with the intent of revisiting the business rules and issue resolution processes for the remainder of the project in an attempt to regain trust among the execution level team. Still awating word on the possible $50M decrement to the FY16 increment being considered by Congress. If approved, an FY17 project would have to be created with a PA of $50M.
2015-08-31 | 2010 | Defense Health Agency | 72481 | 72481 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-08-29 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | 72481 | 72481 | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488000 | 10635000 | 2012-07-05 | 2012-08-20 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | 72481 | 72481 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-06-11 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | 72481 | 72481 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960000 | 2800000 | 2014-09-28 | 2015-08-27 | Sch. 98% Act. 98%. The contractor began construction 3 Nov 14. Pipe installation was completed on 26 Aug. Pavement was completed 27 Aug. Completion of the metering manhole still pending. Installation of the manhole will begin the week of 31 Aug with completion estimated to be the week of 7 Sep. 100% project completion currently scheduled for rmid September.
2015-08-31 | 2010 | Defense Health Agency | 72481 | 72481 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2014-01-04 | Construction 100% Complete
2015-08-31 | 2010 | Defense Health Agency | 72481 | 72481 |  |  | Temp Electric Contract | W9126G-11-P | 46000 | 46000 |  |  | Temp power costs.
2015-08-31 | 2012 | Defense Health Agency | 72481 | 72786 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 69851000 | 72931000 | 2016-11-26 | 2017-01-01 | See Note 1 above.
2015-08-31 | 2013 | Defense Health Agency | 72481 | 76558 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 79914000 | 165837000 | 2016-11-26 | 2017-01-01 | See Note 1 above.
2015-08-31 | 2013 | Defense Health Agency | 72481 | 76558 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540000 | 657000 | 2014-10-24 | 2014-10-24 | Only the re-seeding of the Helipad area remains as a punchlist item; to be completed in Sep 2015.
2015-08-31 | 2013 | Defense Health Agency | 72481 | 76558 |  | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2014-09-28 | 2015-08-10 | Sch. 98% Act. 98%. The contractor began construction 3 Nov 14. Pipe installation was completed on 26 Aug. Pavement was completed 27 Aug. Completion of the metering manhole still pending. Installation of the manhole will begin the week of 31 Aug with completion estimated to be the week of 7 Sep. 100% project completion currently scheduled for rmid September.
2015-08-31 | 2013 | Defense Health Agency | 72481 | 76558 |  |  |  |  | 5562000 |  |  |  | Parking Package “B”:(small business- LPTA) Est. Award: $5.5M •Solicitation Package is complete. •Proposed Award Date: FY16
2015-08-31 | 2011 | Defense Health Agency | 72481 | 77251 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 68076000 | 68076000 | 2016-11-26 | 2017-01-01 | See Note 1 above.
2015-08-31 | 2014 | Defense Health Agency | 72481 | 77293 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 198148000 | 93144000 | 2016-11-26 | 2017-01-01 | See Note 1 above.
2015-08-31 | 2014 | Defense Health Agency | 72481 | 77293 | 2014-10-20 | 2014-12-10 | ACPs |  | 24755000 |  |  |  | ACP Package: (small business-Best Value) Est. Award: $24.7M •Solicitation package is complete. •Proposed Award Date: FY16
2015-08-31 | 2014 | Defense Health Agency | 72481 | 77293 |  | 2015-03-30 | CAT E Equipment |  | 33125000 |  |  |  | No update this reporting period.
2015-08-31 | 2015 | Defense Health Agency | 72481 | 81047 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 225199000 | 85171000 | 2016-11-26 | 2017-01-01 | See Note 1 above.
2015-08-31 | 2015 | Defense Health Agency | 72481 | 81047 | 2015-03-30 |  |  |  | 22616000 |  |  |  | Landscaping Package: (small business-LPTA) Est. Award: $22.7M •Solicitation package is complete. •Proposed Award Date: FY16.
2015-08-31 | 2009 | Defense Health Agency | 72722 | 72722 | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 76944000 | 84365000 | 2014-09-09 | 2015-04-17 | All mod work completed. Construction has been substantially complete since 17 Apr 2015. All physical work less plenum to be complete 18 Sep.
2015-08-31 | 2009 | Defense Health Agency | 72722 | 72722 | 2011-03-07 | 2011-03-20 | A1 Tree Service |  | 9600 | 9600 | 2011-04-01 | 2011-04-01 | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2015-08-31 | 2009 | Defense Health Agency | 72722 | 72722 | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp | W912QR-11-C-0027 | 5395000 | 5395000 | 2014-09-27 | 2015-03-18 | Leased Swing Space awarded for risk mitigation.
2015-08-31 | 2009 | Defense Health Agency | 72722 | 72722 | 2015-07-10 | [7 empty] | Contracting working on construction award processing of this exterior plenum. Procurement Integrity Act limits further information relative to the selection process.
2015-08-31 | 2012 | Defense Health Agency | 72727 | 72727 | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd. | CT/INT21/13487 | 11958000 | 11958000 | 2015-10-30 | 2016-01-08 | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14. Contracting Officer has granted a nil cost extension of time to 25 Dec 2015 based on delays resulting from the original groundwork subcontractor withdrawing from the contract and from a national shortage of labour delaying the brickwork trade. Contractor has requested a further extension of time of 14 calendar days due to late information from SPAWAR. this is currently being reviewed by the Contracting Officer. Contracting Officer approved an extension of time to 8 Jan 2016. Construction complete and BOD achieved 27 August 2015. US Outfitting contractor SIOTS to carry out work under separate contract and to facilitate move from existing clinic (Building 140). VINCI will remobilise in November to demolish building 140 to complete the contract.
2015-08-31 | 2012 | Defense Health Agency | 72754 | 72754 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 76038000 | 79370000 | 2014-07-29 | 2015-11-30 | Note 2: 1. Construction Progress: Sch. 97%, Act. 97% 2. The current Ph 3 completion date is 30 Sept 2015 3. Including the estimated cost of pending modifications Ph 3 is within the BTR limit 4. The BOD will shift from 1 Oct to 22 Dec 2015
2015-08-31 | 2013 | Defense Health Agency | 72808 | 72808 | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703000 | 19359000 | 2015-03-16 | 2016-05-20
2015-08-31 | 2011 | Defense Health Agency | 73360 | 73360 | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869000 | 19957000 | 2014-01-06 | 2014-10-07 | Targeting minor punchlist item completion Sep 2015. Potential in-scope mod (O&M Equipment move) pending upon receit of SRM funds.
2015-08-31 | 2009 | Defense Health Agency | 73599 | 73599 | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178000 | 29356000 | 2015-01-02 | 2015-10-16 | Active Project.
2015-08-31 | 2013 | Defense Health Agency | 73776 | 73776 | 2012-11-15 | 2013-12-18 | Structural Associates Inc. | W91DS-14-C-0003 | 11163000 | 10901000 | 2016-01-06 | 2016-01-06 | Interior finishes near completion and rough-in of interior utilities continues.
2015-08-31 | 2009 | Defense Health Agency | 74650 | 74650 | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989000 | 549904000 | 2014-05-31 | 2015-10-01 | Sch. 100% Act. 97%. USACE has seen an increase in punchlist resolution the week of 31 Aug. QA team continues to push areas to be completed to ensure IO&T is not impacted. The commissioning process continues to identify control issues. All issues are being addressed, fixed and retested. Overall commissioning is approx 94% complete and “pull the plug” test is scheduled for 10 Sept. *Furniture - MILHOT continues to work in all three clinics, basement, and 1st floor; started 3rd floor the week of 31 Aug. * Site - There continues to be progress with site work, currently still tracking mid Nov for completion of last parking lot.
2015-08-31 | 2009 | Defense Health Agency | 74650 | 74650 | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc |  | 10225000 | 11445000 | 2012-02-25 | 2012-05-02 | Construction 100% Complete
2015-08-31 | 2009 | Defense Health Agency | 74650 | 74650 | 2010-02-12 | 2010-03-08 | TTG Utilities, LP | W9126G-10-C-0032 | 301000 | 301000 | 2010-05-30 | 2010-06-07 | Construction 100% Complete
2015-08-31 | 2009 | Defense Health Agency | 74650 | 74650 | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc. | W912DY-05-D-0011 | 1040000 | 1040000 | 2010-10-18 | 2010-10-04 | Construction 100% Complete
2015-08-31 | 2009 | Defense Health Agency | 74650 | 74650 |  |  | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0002 |  | 10156000
2015-08-31 | 2009 | Defense Health Agency | 74650 | 74650 | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0003 | 17290000 | 15383000 | 2012-06-29 | 2015-06-30 | Contractor working on additional punchlist items and close out documentation.
2015-08-31 | 2011 | Defense Health Agency | 75132 | 75132 | 2013-06-14 | 2013-09-27 | Billy W. Jarrett Const Co. Inc. | N62470 13 MPS 0046 | 1797000 | 1899000 | 2014-10-15 | 2016-01-29 | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2015-08-31 | 2013 | Defense Health Agency | 76007 | 72661 |  | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 59786775 | 59786775 | 2016-12-30 | 2017-12-30 | Construction Measures, Roadways, & Site Utilities - FRG revising and coordinating lot requirements for campus roadways, utilities, and additional construction measures not included in current lot packages. Dates subject to change pending refinement of lots and corresponding schedules.
2015-08-31 | 2013 | Defense Health Agency | 76007 | 72661 |  | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 39286000 | 39286000 | 2016-04-15 | 2016-04-15 | Lot 4 Access Control Point, Bridge, External Roadways - 65% OTS design review for Bridge held in August 2015; 65% OTS review for ACP to be conducted in late September 2015. Contract award targeted for June 2016, with construction completion December 2019. FRG coordinating construction sequencing with ACP, Bridge, and PIK L369 Traffic Circle; dates to be refined and adjusted as designs mature.
2015-08-31 | 2014 | Defense Health Agency | 76007 | 72662 |  | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 60551000 | 60551000 | 2019-04-30 | 2019-04-30 | Lot 5.1 Parking Structures, Campus Roadways - Previously included in MedCen 20% design. FRG kicked off post 20% design on 9 Dec 2014. The 35% design due in Sep 2016. This lot will be included in the cost savings discussions.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 16787200 | 16787200 | 2021-07-20 | 2022-03-30 | Environmental Compensation Also includes: Lots 7.2-7.4 Initial Compensation Measures - German government solicitation and award dates to German industry are estimated.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 265000 | 265000 | 2014-04-04 | 2014-04-04 | Lot 1 Temporary Construction Fence - Construction essentially completed April 2014, with remaining access from the east closed off as of 1 May 2015. FRG Security Contractor is on site and will monitor access from the L369 construction gate on the west side.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 694489 | 1711694 | 2014-10-29 | 2015-01-21 | Lot 2.1 Demolition, Site Clearing - Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Final inspection held on 21 Jan 2015, and final contract document provided by FRG (ABG7).
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5320000 | 5320000 | 2016-04-30 | 2016-04-30 | Lot 2.2 Mass Grading - Contract solicitation went out on 11 Dec 2014; bid opening was 10 Feb 2015. NAU signed the ABG4 (contract to FRG) on 20 Apr 2015, LBB to countersign and awarded to industry 22 Apr 2015. Contract amount is $5.3M, substantially less than expected. Contractor mobilization began on 18 May 2015.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5000000 | 5000000 | 2016-12-15 | 2017-12-15 | Lot 3.1 Utilities to site - original ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines and change to double-wall pipe through water protection zone. FRG anicipates solicitation release in Sep 2015, with award by Feb 2016. Construction originally targeted for completion Dec 2016; however, now reliant on Lot 3.7 and City of Ktown completion of 6km sewer line connection. Construction completion now targeted for Dec 2017.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 141235 | 141235 | 2015-03-30 | 2015-05-01 | Lot 3.2 Traffic Light System - Traffic light system in operation since May 2015.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 17713 | 17713 | 2014-12-31 | 2014-12-31 | Lot 3.3 Construction Sign - Completed in December 2013.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 482902 | 482902 | 2014-10-16 | 2014-10-16 | Lot 3.4 Gas Line Relocation - Construction complete.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 19335000 | 19335000 | 2018-02-28 | 2018-02-28 | Lot 3.5 Transformers/Substation - This portion of the ROBMCR project will be accomplished as a direct project through NAU. NAU currently coordinating D/B RFP package with target solicitation Jan/Feb 2016 and construction contract award targeted for May 2016.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 1000000 | 1000000 | 2016-12-15 | 2016-06-15 | Lot 3.6 Water Connection to WZV-Weilerback system - The FRG will coordinate the connection requirements with water provider SWK. Dates forthcoming.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5339748 | 5339748 | 2021-12-17 | 2022-03-30 | Lot 3.9 Site Security - FRG awarded contract in Dec 2013. Security contractor has mobilized and began operation on-site starting 1 May 2015.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 2500000 | 2500000 | 2021-12-17 | 2022-03-30 | 3.10 Site Logistics - Details to be determined by FRG; contract will be for execution of the entire internal and external construction site logistics.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5000000 | 5000000 | 2016-04-30 | 2016-04-30 | Lot 2.3 Landfill Remediation. No issues, on track for Oct 2015 award and construciton completion by 30 Apr 2016.
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 1000 | 1000 | 2014-12-31 | 2014-12-31 | Communications Cable relocation - Action 100% complete
2015-08-31 | 2012 | Defense Health Agency | 76007 | 76007 |  | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 586000 | 586000 | 2021-12-30 | 2021-12-30 | Construction Additional Services
2015-08-31 | 2015 | Defense Health Agency | 76007 | 76872 |  | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 593454000 | 593454000 | 2021-12-08 | 2022-03-30 | Medical Center (Bed Tower, D&T, Clinics, Admin) - US led 20% MedCen final design submitted 2 Aug 2013. USACE is transitioning design to FRG. FRG target for announcement of AE#2 selection is now September 2015, with award following the 21-day protest period in October 2015. FRG schedule dates are estimated at this time and will be refined as AE#2 progresses the design.
2015-08-31 | 2014 | Defense Health Agency | 77000 | 77000 | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR-15-C-0015 | 209917000 | 221672000 |  |  | Construction contract awarded 6 Aug 15 to Walsh Gilbane Joint Venture, 929 W Adams St, Chicago IL 60607-302115 in the amount of $209,917,000.00. Targeting issuance of contract NTP o/a 8 Sep 15.
2015-08-31 | 2011 | Defense Health Agency | 77115 | 77115 | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133000 | 48899000 | 2014-02-02 | 2014-07-18 | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-08-31 | 2011 | Defense Health Agency | 77116 | 77116 | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 14030000 | 14392000 | 2014-02-02 | 2014-07-18 | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-08-31 | 2012 | Defense Health Agency | 77154 | 77154 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 197804000 | 138256000 | 2016-12-06 | 2018-01-01 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2015-08-31 | 2014 | Defense Health Agency | 77154 | 81291 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 |  | 66430000 | 2016-12-06 | 2018-01-01 | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2015-08-31 | 2014 | Defense Health Agency | 77922 | 77922 | 2014-02-25 | 2014-08-20 | Gilbane | W9127S-13-D-6000 DM01 | 45629000 | 47382000 | 2018-01-30 | 2018-01-30 | Submittal #2 (65% Arch/MEP/Fire, 100% Foundation/Structural, IFC Civil/Site) Received 19 May 2015. Review completed, review conference held 15-19 Jun 15. Areas of concern with missing or incomplete information identified (several disciplines, mechanical and electrical). Submittal #3 scheduled for delivery on 23 Sep 2015 and formal conference scheduled for 20 Oct 15.
2015-08-31 | 2013 | Defense Health Agency | 77979 | 77979 | 2013-09-03 | 2014-03-27 | JE Dunn + HWA | W9127S-13-D-6001 DM01 | 47044000 | 52953000 | 2018-02-10 | 2018-04-19 | Submittal #3, 100% Bldg design, review meeting held 3-6 Aug 2015. Submittal #4, corrected Final Design, 11 Sep 2015. 100% Site/Civil package "For Construction" issued 9 July 2015. Mobilization began on 20 Jul 2015 and construction activity began on 29 Jul 2015. C-008 New PFD modification (mod), $659,996, executed 29 May 2015. PDT developed list of scope reductions as potential offsets to the cost of C-008. To date, $901,816 in modifications have been executed utilizing contingency funds. Current estimated value of offsets $500K. PDT has outlines potential cost saving modification for changes to Program for Design. Goal is to reduce overall cost impacts to $200K or less. Partial notice to proceed issued for Site/Civil work.
2015-08-31 | 2013 | Defense Health Agency | 78143 | 78143 | 2013-01-14 | 2013-08-22 | Blinderman Constr Co. | N40083 13 C 0003 | 14864000 | 14884000 | 2015-01-15 | 2016-03-15 | Drug Lab BOD Apr 2015, Second Contract to Demo Bldg 38H underway
2015-08-31 | 2013 | Defense Health Agency | 78144 | 78144 | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354000 | 14777000 | 2015-03-17 | 2015-11-09
2015-08-31 | 2013 | Defense Health Agency | 78146 | 78146 | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254000 | 7477000 | 2014-12-06 | 2015-11-06
2015-08-31 | 2011 | Defense Health Agency | 78853 | 78853 | [8 empty] | DHA issued DA memo dated 22 Dec 2014 cancelled the FY11 project. FY11 funds ($46,355.39) were revoked on 24 Jul 2015. No unobligated funds remain. HQUSACE code 8 (Project Cancelled) design directive received 2 Sep 2015.
2015-08-31 | 2012 | Defense Health Agency | 79554 | 79554 | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200000 | 14457000 | 2014-02-22 | 2014-06-02
2015-08-31 | 2009 | Defense Health Agency | 79845 | 79845 | 2011-07-01 | 2011-09-23 | JE Dunn Construction Company | W9126G-08-D-0057 | 51133000 | 59456000 | 2014-11-06 | 2015-07-28 | Contract including all currently identified modifications is at 99.58% of PA. Hospital Command moved into new building Dec 19. Urology, ENT, Lab II, Surgery Phase III move in also completed mid December. Contractor currently working punch list in PET/CT. Scheduled acceptance Aug. 3. User requested equipment mod is only item outstanding. Joint Commissioning is competed and generated no action items for the project to correct.
2015-08-31 | 2011 | Defense Health Agency | 80093 | 80093 | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc. | W9126G-09-D-0105 | 1698000 | 1982000 | 2013-11-14 | 2014-08-24 | Switch gear was changed on 18 FEB 2015. Project complete. No punch list items. Contract/project closeout and Evaluation not completed. All else is done.
2015-08-31 | 2012 | Defense Health Agency | 80094 | 80094 | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc. | W912BV-12-C-0030 | 1692000 | 1710000 | 2014-07-05 | 2014-12-12 | The ACO has forwarded a serial letter to the Contractor stating that all closeout items (including LEED) must be closed out by 30 Sept 2015. If the Contractor responds appropriately by 30 Sept 15, closeout will likely occur by mid December (16 Dec 15).
2015-08-31 | 2013 | Defense Health Agency | 80306 | 80306 | 2013-07-25 | 2013-09-12 | G-W Management Servicxes Inc. | N40080 10 D 0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25 | Dosimetry Complete
2015-08-31 | 2013 | Defense Health Agency | 80306 | 80306 | 2014-03-15
2015-08-31 | 2013 | Defense Health Agency | 80307 | 80307 | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898000 | 4789000 | 2015-04-08 | 2016-03-18
2015-08-31 | 2013 | Defense Health Agency | 80308 | 80308 | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947000 | 27075000 | 2016-02-12 | 2016-06-27 | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2015-08-31 | 2012 | Defense Health Agency | 80792 | 80792 | 2012-06-18 | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service | W81W3G22363343 / 22443665 / 22443666 / 30793685 | 1600000 | 1690000 | 2013-05-31 | 2013-08-29 | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Project financial closeout is ongoing. Update 03 AUG 2015: Received release of claims from American Water and returned all unobligated MIPR'd funds. Still waiting for return of unobligated MIPR'd funds requested by POC for Dominion Virginian Power. Once these funds are returned project will be closed out.
2015-08-31 | 2013 | Defense Health Agency | 80793 | 80793 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22371000 | 2014-07-29 | 2015-09-30 | See Note 2 above.
2015-08-31 | 2014 | Defense Health Agency | 80904 | 80904 | 2014-01-30 | 2015-03-30 | Whiting Turner Contracting Co | N40080 15 C 0156 | 38490000 | 38490000 | 2017-02-07 | 2017-02-07
2015-08-31 | 2014 | Defense Health Agency | 80913 | 80913 | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835000 | 15835000 | 2016-04-16 | 2016-05-09
2015-08-31 | 2012 | Defense Health Agency | 81004 | 81004 | 2012-05-16 | 2012-06-05 | Sunland Builders, Inc. | N40085 09 D 9027 DO 0026 | 1363000 | 1452000 | 2013-08-29 | 2013-08-29 | Project is not financially closed.
2015-08-31 | 2014 | Defense Health Agency | 81340 | 81340 | 2014-03-17 | 2014-06-30 | Gilbane | W9127S-13-D-6000 DY01 | 11289000 | 11289000 | 2016-09-30 | 2016-09-30 | Final design completed 20 Jul. Mass excavation delayed due to late approval of instation passes for workers and KTR awaiting approval of SWPPP
2015-08-31 | 2015 | Defense Health Agency | 81423 | 81423 | 2015-03-20 | [5 empty] | 2017-12-18 |  | Contract awarded to J.E. Dunn construction (on SWL Air Force Medical MATOC) on 3 Sep 2015.
2015-08-31 | 2015 | Defense Health Agency | 81430 | 81430 |  |  | Ellerbe Becket & RLF JV | W912DY-09-D-0068 (AE-1) | 1279000 | 496000 |  | 2015-11-21 | The construction contract will also include turnkey FFE and medical equipment increasing the procurement to > $50M. DHA supports Jan 2016 award. NAO has obtained and MOA to secure capacity on the SWL iDBIO MATOC for award.
2015-08-31 | 2014 | Defense Health Agency | 81436 | 81436 | 2015-08-25 | [7 empty] | Planned Aug 2015 award of a Design-Build contract with a one-year design period delayed to Dec 2015. Delay in advertisement/award due to site availability, pending completion of an on-going MCN project, the P908 Operations and Support Facilities. A large required security-related modification to this ongoing project is the primary cause of the schedule push. New site availability date is Nov 2016. Authority to Advertise received 25 Aug 15 and RFP was issued the same day.
2015-08-31 | 2015 | Defense Health Agency | 81627 | 81627 | [8 empty] | NWS Design team has reviewed the CWE and will revise the depth of excavation. JBLM will allow disposal of contaminated and noon-contaminated soils on Post. Received $50K in additional P&D funds for design revisions on 4 Sep 15.
2015-08-31 | 2014 | Defense Health Agency | 81631 | 81631 | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc. | W912HN-11-D-0043-0044 | 1436000 | 1438000 | 2016-02-01 | 2016-02-01 | The NiCOE Contractor (WM Jordan) on-going construction work on new clinic. WM Jordan has a weathered in roof, interior stud walls, primary duct work, and fire sprinkler mains installed. WM Jordan continues with masonry walls, electrical , communications, and plumbing rough-in. Site Contractor is installing curb and gutter in the Southern Parking Lot. Contingencies in district: $24,739.38
2015-08-31 | 2014 | Defense Health Agency | 81706 | 81706 | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 1795000 | 1760000 | 2015-10-28 | 2015-10-28 | The installation of the pad mounted transformer is complete as of 13 Jul 15. This completes all of phase II work. Phase III work is expected to begin on 2 Sep 15.
2015-08-31 | 2013 | Defense Health Agency | 82358 | 82358 | 2015-07-09 | [7 empty] | Cost reduction measures incorporated new HQCWE is $1.8M. DHA has increased PA to $1.9M. Received Authority to Advertise on 26 Apr 15. Advertised 09 Jul 15. Bids due on 11 Aug 15.
2015-08-31 | 2014 | Defense Health Agency | 86204 | 86204 | 2015-08-04 | [7 empty] | Proposals due on 11SEP15. Evaulation schedule for 14-16 SEP
2015-08-31 | 2008 | Defense Health Agency | 005V | 005A | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2011-07-31 | 2012-09-15 | Not financially closed. Final invoicing for equipment.
2015-08-31 | 2008 | Defense Health Agency | 005V | 005B | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2011-07-31 | 2012-09-15
2015-08-31 | 2008 | Defense Health Agency | 005V | 005V | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 | 757737000 | 774314000 | 2011-07-31 | 2012-09-15
2015-08-31 | 2009 | Defense Health Agency | 478V | 478V | 2009-04-01 | 2009-11-10 | W.G. Yates & Sons Construction Co. | N69450 10 C 0763 | 38252000 | 42256000 | 2011-09-11 | 2012-10-11 | Not financially closed. Final invoicing for equipment - working with DLA.
2015-08-31 | 2013 | Defense Information Systems Agency | 13DISA01 |  |  | 2013-08-19 | Bauamt Reutlingen | W912GB-15-C-011 | 1714754 | 1714753.7 |  |  | PA: $2.224M. Contract awarded to Bauamt on 19 Aug 2015. Awaiting kick off meeting.
2015-08-31 | 2014 | Defense Information Systems Agency | 14DISA01 | [9 empty] | PA: $2.615M. NAVFAC preparing RFP for Design. RFP will take into consideration the Navy's Energy Project to replace the 2 existing chillers. Awaiting schedule dates for three (3) Day Charrette in early FY16.
2015-08-31 | 2015 | Defense Information Systems Agency | 15DISA01 | [9 empty] | PA: $1.871M. Design/Renovation of Garrison existing Bldg 52120 for JITC Fort Huachuca. USACE to conduct site survey 27-28 Apr 2015. Design charrette held 30 Jun 2015. The 65% design received. Comments due 14 Sept 2015.
2015-08-31 | 2015 | Defense Information Systems Agency | 15DISA02 | [9 empty] | PA: $9.6M. NAVFAC to construct Electronic Equip Bldg, Antenna Foundations for AN/GSB 52B Medium Satellite Earth Terminals. RFI issued 16 Apr 15. No responses. J&A approved. Awaiting DB RFP pkg ESC Oct 2016. Project ESC: FY18.
2015-08-31 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11 | PA: $77.515M. 3 separate contracts: Soil Remediation; Construction; Demo Bldg 3189. Soil Remediation: COMPLETED; Construction ESC: 11 Mar 2016;. Demo of Bldg 3189 funding ($2.153M) provided to USACE on 30 Jun 2015.
2015-08-31 | 2015 | Defense Information Systems Agency | [10 empty] | PA: $745K. Design of Garrison existing Bldgs 52101, 52110, 52111 for JITC Fort Huachuca. Design charrette rescheduled Sept 2015. Design funding covered under consolidated FY15 Planning and Design Appropriation. USACE will schedule early FY16.
2015-08-31 | 2008 | Defense Intelligence Agency | 154207 |  | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC | W912DR-09-D-0024 448-0156A-08 | 1012000 | 1012000 | 2011-09-16 | 2012-01-20 | Approp. - $1,012
2015-08-31 | 2010 | Defense Intelligence Agency | DIA10-001 |  | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd. | W912UM-11-C-0006/W912UM-12-C-004 | 4608000 | 5224000 | 2013-10-09 | 2013-10-17 | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project closed out 10 May 2015.
2015-08-31 | 2010 | Defense Intelligence Agency | DIA10-002 |  | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company | W91278-10-D-0064 0001 | 12000000 | 12003000 | 2014-01-20 | 2014-05-21 | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved. Contingency funds will be used in FY15 for within scope modifications.
2015-08-31 | 2011 | Defense Intelligence Agency | DIA11-002 |  | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture | N40080-06-D-0004-0081 | 2984000 | 2294000 | 2012-07-18 | 2012-07-25 | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000001 |  | 2014-06-16 | 2014-09-23 | Arriba | N4008-11-D-0496-0050/N0080-11-D-0495-0016 | 15186000 | 13358000 | 2016-03-02 | 2016-06-30 | Approp. - $13,645 - $793,156 CAT I obligated. Construction start 10 August 2015. Closures/reduction of available parking spaces in the West Parking Lot, street parking along Chappie James Boulevard, and in the North West parking lot in progress. Amount of $1.6M added to this project from Construction of the Remote Delivery Facility, DIA project DIA12000005 as a below threshhold realignment. Funds are committed awaiting contract award (obligation).
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000002 |  |  |  |  | N40080-09-D-0309-0018 |  |  |  |  | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions to add funds from the DIAC Chiller project. Reprogamming action currently with OMB; expect approval soon.
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000003 |  |  |  |  | N4008-09-D-0309-0017 |  |  |  |  | Estimates indicate project costs exceed programmed amounts. DIA initiating reprogramming action to move funds to UPS for Data Center. Awaiting reprogramming action approval.
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000005 |  | 2013-08-21 | 2013-09-25 | Heard Construction | W91236-09-D-0071:T044/W91236-13-C-0074 | 10758000 | 6058000 | 2014-09-30 | 2015-07-31 | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Air barrier completed waiting for final testing; commissioning started 26 August 2015; R2 and R3 did not function properly; rescheduling new date. Awaiting Hood system install. Backpack sytem installed, tested and training provided 1 September 2015. Amount of $1.6M diverted to DIA Parking Garage Replacement, project DIA12000001 as a below threshhold re-alignment.
2015-08-31 | 2013 | Defense Intelligence Agency | DIA13000001 | [9 empty] | This line was reduced due to sequestration. The remaining funds are insufficient to complete demolition of the existing parking garage. DIA is currently exploring options. Contract is not awarded at this time.
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | DSFH1401 | DSFH14U2 | 2014-12-08 | 2015-06-02 | Hako Plumbing Inc. | N62742-15-C-1310 | 2591000 | 2591000 | 2016-10-14 | 2016-10-14 | wo# 1362232
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | DSFH1401 |  | 2014-12-08 | 2015-06-02 | Hako Plumbing Inc. | N62742-15-C-1310 | 5664000 | 5664000 | 2016-10-14 | 2016-10-14 | wo# 1167459
2015-08-31 | 2012 | Defense Security Service | P646 |  | 2012-09-21 | 2013-03-29 | Hensel Phelps Construction Co. | N40080-13-C-0155 | 25149000 | 29009000 | 2014-07-22 | 2015-09-09 | [Solicitation/Advertise Date: Phase I - 21-Sep-2012 Phase II - 20-Dec-2012]
2015-08-31 | 2012 | Defense Security Service | P659 |  | 2013-01-22 | 2013-07-15 | Shirley Contracting Company, LLC | DTFH71‐13‐C‐00041 | 2967000 | 3171000 | 2014-08-01 | 2015-05-15 | This project is being managed and funded via FHWA. [Solicitation/Advertise Date: Phase I - 22-Jan-2013 Phase II - 04-Apr-2013]. Placed in service date is the substantial completion date. Punchlist items remain.
2015-08-31 | 2011 | DLA Defense Distribution Center | DDCX0802 |  | 2011-11-23 | 2012-08-17 | Walsh Construction | W912DR-12-C-011 | 80775000 | 82555000 | 2015-09-18 | 2016-01-29
2015-08-31 | 2012 | DLA Defense Distribution Center | DDCX1202 |  | 2012-09-17 | 2013-11-20 | Corothers Construction Inc. | W912DR-14-C-0005 | 24622000 | 25388000 | 2015-08-27 | 2015-07-20 | 2853 Reprogramming
2015-08-31 | 2012 | DLA Defense Distribution Center | DDCX1203 |  | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 15198000 | 15912000 | 2016-05-05 | 2016-09-18
2015-08-31 | 2013 | DLA Defense Distribution Center | DDCX1301 |  | 2014-05-15 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 6800000 | 6800000 | 2016-07-28 | 2016-08-03
2015-08-31 | 2013 | DLA Defense Distribution Center | DDCX1303 |  | 2013-06-13 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9658000 | 9758000 | 2016-01-02 | 2016-03-06 | 2853 Reprogramming
2015-08-31 | 2014 | DLA Defense Distribution Center | DDCX1404 |  | 2014-02-11 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 32930000 | 32930000 | 2016-02-25 | 2016-04-04
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC 1306 |  | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378000 | 66999000 | 2017-10-14 | 2017-10-14 | wo# 1124159
2015-08-31 | 2011 | DLA Defense Energy Support Center | DESC0503 |  | 2012-05-17 | 2012-09-22 | Tokyo Construction Co., Ltd. | W912HV-12-C-0013 | 25204000 | 25586000 | 2015-02-01 | 2015-05-13
2015-08-31 | 2008 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2008-09-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 52443000 | 52443000 | 2013-09-23 | 2014-02-28 | wo# 861477
2015-08-31 | 2010 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2011-03-22 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 79509000 | 131952000 | 2013-09-23 | 2014-02-28 | wo#861477
2015-08-31 | 2011 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2011-03-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 17400000 | 149352000 | 2013-09-23 | 2014-02-28 | wo#974938
2015-08-31 | 2012 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2012-03-29 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08C-7501 | 15512000 | 164864000 | 2013-09-23 | 2014-02-28 | wo# 113174
2015-08-31 | 2010 | DLA Defense Energy Support Center | DESC0907 |  | 2009-12-17 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844000 | 19369000 | 2012-12-16 | 2015-04-30
2015-08-31 | 2011 | DLA Defense Energy Support Center | DESC0909 |  | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | N40085-11-C-0001 | 28815000 | 34079000 | 2014-06-03 | 2015-05-30 | wo# 799865
2015-08-31 | 2012 | DLA Defense Energy Support Center | DESC1102 |  | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 25181000 | 25388000 | 2015-12-10 | 2016-02-08 | 2853 Reprogramming
2015-08-31 | 2012 | DLA Defense Energy Support Center | DESC1103 |  | 2012-05-04 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 18962000 | 18902000 | 2014-11-03 | 2015-05-15
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1107 |  | 2014-02-28 | 2014-06-12 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4056000 | 4166000 | 2015-08-11 | 2015-08-19
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC11U2 |  | 2014-03-28 | 2014-04-24 | Gilbane Federal | N62583-09-D-0129 | 1994000 | 1994000 | 2015-11-15 | 2015-11-15 | wo# 1302082
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC1203 |  | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366000 | 36366000 | 2015-10-28 | 2015-09-28 | wo# 1124257
2015-08-31 | 2012 | DLA Defense Energy Support Center | DESC1205 |  | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453000 | 27840000 | 2015-03-24 | 2015-08-30 | 2853 Reprogramming wo# 973902
2015-08-31 | 2012 | DLA Defense Energy Support Center | DESC12S1 |  | 2012-03-27 | 2012-07-05 | Kinley Construction Company | W9128F-10D-0052 | 1930000 | 2101000 |  | 2015-09-22
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC1301 |  |  | 2015-08-28 | Rockford Corporation | W912QR-15-C-0026 | 33997000 | 33997000 | 2017-03-30 | 2017-03-30
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC1303 |  | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364000 | 54533000 | 2016-02-06 | 2016-10-26 | wo# 1125022
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC1304 |  | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513000 | 20077000 |  | 2017-03-07
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC1305 |  | 2013-07-07 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800000 | 1800000 |  | 2015-04-28
2015-08-31 | 2015 | DLA Defense Energy Support Center | DESC1353 |  | 2015-03-13 | 2015-08-09 | Middle Eastern Builders | W912HN-12C-0016 | 17900000 | 17900000 | 2017-09-27 | 2017-12-26
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC1390 |  | 2012-10-30 | 2013-08-13 | Environmental Management Resources | N69450-10-D-0787 | 4311000 | 4455000 | 2015-02-26 | 2015-02-26 | wo# 1123107
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC1391 |  | 2012-12-24 | 2013-08-01 | Nova Group Inc. | W91278-13-C1001 | 15105000 | 15271000 |  | 2015-12-25
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC13S2 |  | 2014-08-20 | 2015-01-27 | Reliable Contracting Group, LLC | W91278-15-C-0005 | 8456000 | 8456000 | 2016-05-06 | 2016-08-05
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC13S3 |  | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961000 | 1961000 | 2015-10-28 | 2015-10-28 | wo# 1303226
2015-08-31 | 2013 | DLA Defense Energy Support Center | DESC13S4 |  | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322000 | 1454000 | 2014-08-03 | 2015-10-11 | 2853 Reprogramming wo# 1124259
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2015-02-27 | 2015-04-07 | Nippo Corporation | W912HV-15-C-005 | 32623000 | 32623000 | 2018-10-20 | 2018-10-20
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1402 |  | 2014-01-16 | 2014-04-17 | Industrial Power Systems | N69450-14-C-1255 | 5438000 | 5438000 | 2015-10-10 | 2015-10-10 | wo# 1163305
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1405 |  | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749000 | 8786000 | 2016-04-22 | 2016-04-22 | wo#1140322
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1407 |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP-15-C-003 | 21288000 | 21288000 | 2017-01-10 | 2017-01-10
2015-08-31 | 2015 | DLA Defense Energy Support Center | DESC1459 |  |  | 2015-08-12 | CB&I Federal Services LLC | W912HN-15-C-0017 | 5949000 | 5949000 | 2017-03-30 | 2017-03-30
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC14S2 |  | 2014-01-09 | 2014-04-14 | Pond Constructors Inc. | W9128F-14-D-0051 | 3780000 | 3942000 | 2015-05-07 | 2015-12-24
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC14U1 |  | 2014-06-01 | 2014-07-01 | CB&I Federal Services LLC | N62583-09-D-0130 TO-027 | 1994000 | 1994000 | 2015-11-15 | 2015-11-15 | wo# 1170569
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC14U2 |  | 2014-07-31 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 935000 | 935000 | 2014-11-03 | 2015-05-15
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1501 |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637000 | 8637000 | 2016-05-11 | 2016-08-09
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1502 | 43 | 2014-06-17 | 2015-05-04 | Rockford Corporation | W912BV-15-C-0017 | 4556000 | 4556000 | 2016-10-23 | 2016-12-08 | 2853 Reprogramming
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1502 |  | 2014-06-17 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0001 | 32060000 | 32060000 | 2017-05-23 | 2017-09-08 | 2853 Reprogramming
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1503 |  | 2014-10-03 | 2015-04-23 | Tokyo Construction Co., Ltd. | W912HV-15-C-0007 | 6244000 | 6244000 | 2016-11-05 | 2016-07-19
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1504 |  | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0011 | 13407000 | 13407000 | 2016-04-08 | 2016-07-07
2015-08-31 | 2015 | DLA Defense Energy Support Center | DESC1510 |  | 2015-02-02 | 2015-08-20 | Graco Construction Inc. | W912QR-15-C-0025 | 32592000 | 32592000 | 2018-01-16 | 2017-09-06
2015-08-31 | 2015 | DLA Defense Energy Support Center | DESC1515 |  | 2015-02-12 | 2015-08-31 | MEB General Contractors Inc. | N40085-15-C-0022 | 22944000 | 22944000 | 2017-06-26 | 2017-06-26 | wo# 1302502
2015-08-31 | 2015 | DLA Defense Energy Support Center | DESC1551 |  | 2014-10-29 | 2015-09-01 | Hensel phelps Constuction co | N62742-15-C-1308 | 42823000 | 42823000 | 2018-07-08 | 2018-07-08 | wo# 1306143
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1557 |  | 2014-07-28 | 2015-05-14 | Cape Env. Mgmt. | W9128F-10-D-0075 | 3471000 | 3471000 | 2016-10-05 | 2017-01-03
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC1561 |  | 2014-03-10 | 2014-06-12 | Rockford Corporation | W9128F-10-D-0050 | 1917000 | 1917000 | 2015-09-17 | 2015-08-07
2015-08-31 | 2014 | DLA Defense Energy Support Center | DESC15S1 |  | 2014-05-02 | 2014-07-29 | Ichibo Co. Ltd | W912HV-14-C-0002 | 1835000 | 1857000 | 2015-07-24 | 2015-05-15
2015-08-31 | 2012 | DLA Defense Energy Support Center | DESI1101 |  | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | N62478-11-D-4042/0004 | 5500000 | 6430000 | 2013-06-14 | 2014-04-29 | wo# 972725
2015-08-31 | 2012 | DLA Defense Supply Center Philadelphia | DSCP1201 |  | 2012-03-28 | 2012-06-01 | WU & Associates, Inc. | N40085-10-D-9451 | 4775000 | 7240000 | 2013-07-17 | 2014-06-06 | wo# 971006
2015-08-31 | 2014 | DLA Defense Supply Center Richmond | DSCR1401 |  | 2015-02-13 | 2015-06-12 | Hensel Phelps Constuction Co | W91236-15-C-0045 | 71969000 | 71969000 | 2018-07-08 | 2018-07-08
2015-09-01 | 2010 | DoD Education Activity | AM 856 07 |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764000 | 20564000 | 2013-12-14 | 2014-07-09
2015-09-01 | 2013 | DoD Education Activity | AM00023 | 28 | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2015-12-11 | 2016-03-23
2015-09-01 | 2013 | DoD Education Activity | AM00023 |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987000 | 33393000 | 2015-12-11 | 2016-03-23
2015-09-01 | 2014 | DoD Education Activity | AM00024 |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4897000 | 4904000 | 2016-01-21 | 2016-04-20
2015-09-01 | 2012 | DoD Education Activity | AM00025 |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339000 | 23973000 | 2016-06-01 | 2017-05-20 | The occupancy date 1 Jun 16 is for the BOD of the school. This is the completion of Phase 1 of the project. The school can be occupied at this time. The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2015-09-01 | 2012 | DoD Education Activity | AM00026 |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685000 | 33612000 | 2015-11-11 | 2016-06-01
2015-09-01 | 2013 | DoD Education Activity | AM00027 |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 32260000 | 33383000 | 2016-06-30 | 2016-08-19
2015-09-01 | 2013 | DoD Education Activity | AM00028 |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39362000 | 39710000 | 2015-12-17 | 2016-05-16
2015-09-01 | 2014 | DoD Education Activity | AM00031 |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278-12-D-0039/30132665 | 32124000 | 32124000 | 2017-02-10 | 2017-05-11
2015-09-01 | 2014 | DoD Education Activity | AM00034 |  | 2014-06-20 | 2014-11-10 | Walsh Group Ventures | W912QR-15-C-0001/34496304 | 50931000 | 50971000 | 2017-02-25 | 2017-08-01
2015-09-01 | 2014 | DoD Education Activity | AM00037 |  | 2014-07-25 | 2015-08-18 | Roy Anderson Corp | N6945014R17600005 | 35705000 | 41229000 | 2018-06-28 | 2018-06-28 | Project will be re-awarded to second highest bidder following original contractor being terminated for cause.
2015-09-01 | 2014 | DoD Education Activity | AM00038 |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40093000 | 39874000 | 2016-09-14 | 2017-01-07
2015-09-01 | 2014 | DoD Education Activity | AM00040 |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 34748000 | 35095000 | 2016-03-28 | 2016-05-27
2015-09-01 | 2014 | DoD Education Activity | AM00050 |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791000 | 31791000 | 2016-10-31 | 2017-01-29
2015-09-01 | 2011 | DoD Education Activity | AM100801 |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121826 | 14851000 | 16469000 | 2014-04-03 | 2014-07-15 | Remove at end of FY15
2015-09-01 | 2011 | DoD Education Activity | AM2455205 |  | 2011-07-18 | 2011-10-20 | Bernard Associates | W912DS-12-C-0001 / 25312318 | 23974000 | 26115000 | 2014-09-28 | 2014-03-17 | Remove at end of FY15
2015-09-01 | 2011 | DoD Education Activity | AM2455206 |  | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297000 | 43644000 | 2014-09-30 | 2015-06-01 | Remove at end of FY15
2015-09-01 | 2011 | DoD Education Activity | AM8193 01 |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968000 | 51299000 | 2014-04-19 | 2015-11-30
2015-09-01 | 2011 | DoD Education Activity | AMD02051 |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121890 | 16413000 | 17205000 | 2014-04-03 | 2014-07-15 | $1,443 supported AM0025 and $613 supported PA00033. Remove end of FY15
2015-09-01 | 2011 | DoD Education Activity | D9124-1 | 17 | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843000 | 6002000 | 2015-07-23 | 2013-01-04
2015-09-01 | 2011 | DoD Education Activity | D9124-1 | 18 | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28674000 | 29244000 | 2015-01-13 | 2015-02-12
2015-09-01 | 2011 | DoD Education Activity | D9124-1 |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260000 | 27251000 | 2014-04-17 | 2014-07-04
2015-09-01 | 2013 | DoD Education Activity | EU00043 | 33 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817338 | 3217000 | 3217000 | 2017-06-03 | 2017-09-07
2015-09-01 | 2013 | DoD Education Activity | EU00043 | 34 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 34787000 | 34919000 | 2017-06-03 | 2017-09-07
2015-09-01 | 2013 | DoD Education Activity | EU00043 | 35 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 635000 | 1084000 | 2017-06-03 | 2017-09-07
2015-09-01 | 2013 | DoD Education Activity | EU00043 |  | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817336 | 0 | 0 | 2017-06-03 | 2017-09-07
2015-09-01 | 2012 | DoD Education Activity | EU00053 | 25 | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11783771.7 | 12335000 | 2015-03-10 | 2015-08-28
2015-09-01 | 2012 | DoD Education Activity | EU00053 |  | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 575000 | 575000 | 2015-03-10 | 2015-08-28
2015-09-01 | 2012 | DoD Education Activity | EU00062 | 42 | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366000 | 5449000 | 2015-09-26 | 2015-11-10
2015-09-01 | 2012 | DoD Education Activity | EU00062 |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 283000 | 283000 | 2015-09-26 | 2015-11-10
2015-09-01 | 2010 | DoD Education Activity | EUR 8197 02 |  | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | W912GB-08-C-0046 / 14328568 | 15509459 | 17800000 | 2013-01-19 | 2013-09-25 | Remove at end of FY15
2015-09-01 | 2011 | DoD Education Activity | EUR 8268 02 | 13 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2015-04-30 | 2015-08-25
2015-09-01 | 2011 | DoD Education Activity | EUR 8268 02 | 14 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292874.4 | 2015-04-30 | 2015-08-25
2015-09-01 | 2011 | DoD Education Activity | EUR 8268 02 |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869322.1 | 47427000 | 2015-04-30 | 2015-08-25
2015-09-01 | 2010 | DoD Education Activity | EUR 8318 09 | 11 | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652185.3 | 1719194.7 | 2015-07-23 | 2013-01-04
2015-09-01 | 2010 | DoD Education Activity | EUR 8318 09 |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414633.6 | 33113000 | 2014-04-17 | 2014-07-04
2015-09-01 | 2010 | DoD Education Activity | EUR 8320 03 | 8 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513913.3 | 2015-04-30 | 2015-08-25
2015-09-01 | 2010 | DoD Education Activity | EUR 8320 03 | 9 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2015-04-30 | 2015-08-25
2015-09-01 | 2010 | DoD Education Activity | EUR 8320 03 |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46694923.3 | 51109000 | 2015-04-30 | 2015-08-25
2015-09-01 | 2010 | DoD Education Activity | EUR826708 | 3 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 39972656 | 3307000 | 3307000 | 2018-03-01 | 2018-06-04
2015-09-01 | 2010 | DoD Education Activity | EUR826708 | 4 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 45239562 | 0 | 0 | 2018-03-01 | 2018-06-04
2015-09-01 | 2010 | DoD Education Activity | EUR826708 |  | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 17387653 | 58111000 | 58111000 | 2018-03-01 | 2018-06-04
2015-09-01 | 2014 | DoD Education Activity | PA00018 |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28954000 | 29881000 | 2016-10-03 | 2016-12-10
2015-09-01 | 2012 | DoD Education Activity | PA00019 |  | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | W912HV-13-C-0002 / 29312081 | 9644000 | 9773000 | 2015-07-25 | 2015-10-18 | Remove at end of FY15
2015-09-01 | 2012 | DoD Education Activity | PA00020 |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187000 | 31160000 | 2015-12-09 | 2016-03-01
2015-09-01 | 2012 | DoD Education Activity | PA00027 |  | 2014-07-25 | 2014-12-24 | Daiwa Odakyu Construction - JDC JV | W912HV-15-C-0002/ 29312181 | 40547000 | 40547000 | 2018-12-21 | 2019-04-09
2015-09-01 | 2014 | DoD Education Activity | PA00030 |  | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476000 | 95476000 | 2017-04-01 | 2017-06-20
2015-09-01 | 2013 | DoD Education Activity | PA00033 | 38 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469000 | 2469000 | 2016-10-24 | 2017-01-01
2015-09-01 | 2013 | DoD Education Activity | PA00033 | 39 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612000 | 4612000 | 2016-10-24 | 2017-01-01
2015-09-01 | 2013 | DoD Education Activity | PA00033 | 40 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418000 | 62722000 | 2016-10-24 | 2017-01-01
2015-09-01 | 2013 | DoD Education Activity | PA00033 |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475000 | 1475000 | 2016-10-24 | 2017-01-01
2015-09-01 | 2014 | DoD Education Activity | PA00035 |  | 2014-09-23 | 2015-02-18 | Nippo Corporation | W912HV-15-C-0003 / 34596540 | 31459000 | 31459000 | 2016-10-02 | 2016-12-02
2015-08-31 | 2011 | Marine Corps Active | M00146136 |  | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | N4008511C4026 AWD | 42882000 | 42058000 | 2013-07-07 | 2014-12-14
2015-08-31 | 2011 | Marine Corps Active | M00146148 |  | 2010-10-21 | 2011-06-02 | SAUER, INC. | N4008511C4010 P00003 | 4779000 | 4779000 | 2012-07-10 | 2013-11-04
2015-08-31 | 2013 | Marine Corps Active | M00146163 |  | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091000 | 28123000 | 2016-01-18 | 2016-04-30
2015-08-31 | 2011 | Marine Corps Active | M00146164 |  |  | 2011-07-01 | NAVY STANDARD DOCUMENT | N4008509RP00103 | 4002000 | 3706000
2015-08-31 | 2011 | Marine Corps Active | M00146176 |  | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | N4008510D0261 0003 | 5850000 | 7300000 | 2012-11-25 | 2013-10-10
2015-08-31 | 2013 | Marine Corps Active | M00146601 |  | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0006 | 11782000 | 11639000 | 2015-04-08 | 2015-09-06
2015-08-31 | 2012 | Marine Corps Active | M00146991 |  | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0003 | 14067000 | 17447000 | 2013-08-14 | 2014-11-24
2015-08-31 | 2013 | Marine Corps Active | M00243313 |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974000 | 10698000 | 2015-04-29 | 2016-02-25
2015-08-31 | 2011 | Marine Corps Active | M00243400 |  | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | N6247310D5480 0012 | 9928000 | 9373000 | 2012-06-17 | 2012-07-11
2015-08-31 | 2013 | Marine Corps Active | M00263382 |  | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513000 | 11094000 | 2015-04-12 | 2015-10-11
2015-08-31 | 2014 | Marine Corps Active | M002641406 |  | 2014-12-18 | 2015-05-01 | BISCAYNE CONTRACTORS, INC. | N4008015C2007 | 4503000 | 4274000 | 2016-11-21 | 2016-11-21
2015-08-31 | 2011 | Marine Corps Active | M00264541 |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 31343000 | 29449000 | 2014-08-16 | 2015-02-17
2015-08-31 | 2012 | Marine Corps Active | M00264543 |  | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0020 | 11118000 | 11273000 | 2014-03-28 | 2014-12-09
2015-08-31 | 2013 | Marine Corps Active | M00264562 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462000 | 28948000 | 2016-11-06 | 2017-10-18
2015-08-31 | 2011 | Marine Corps Active | M00264566 |  | 2011-06-20 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 45465000 | 37555000 | 2016-11-06 | 2017-10-18
2015-08-31 | 2012 | Marine Corps Active | M00264567 |  | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222000 | 23971000 | 2016-11-06 | 2017-10-18
2015-08-31 | 2012 | Marine Corps Active | M00264571 |  | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | N4008010D0497 0011 | 6555000 | 7009000 | 2013-09-05 | 2014-12-30
2015-08-31 | 2011 | Marine Corps Active | M00264599 |  | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | N6274209D1174 JU01 | 34087000 | 30411000 | 2013-08-09 | 2014-04-30
2015-08-31 | 2012 | Marine Corps Active | M00264611 |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 32910000 | 31757000 | 2014-10-16 | 2015-07-22
2015-08-31 | 2012 | Marine Corps Active | M00264612 |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 5028000 | 5177000 | 2014-10-16 | 2015-07-22
2015-08-31 | 2011 | Marine Corps Active | M00264615 |  | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | N4008010D0493 0002 | 6836000 | 6730000 | 2012-12-21 | 2013-05-31
2015-08-31 | 2012 | Marine Corps Active | M00264621 |  | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081000 | 25554000 | 2015-03-15 | 2015-09-08
2015-08-31 | 2012 | Marine Corps Active | M00264632 |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 60736000 | 60289000 | 2014-08-16 | 2015-02-17
2015-08-31 | 2013 | Marine Corps Active | M00264644 |  | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168000 | 12093000 | 2015-04-22 | 2016-04-01
2015-08-31 | 2011 | Marine Corps Active | M00318006 |  | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | N6274209D1171 HC01 | 28891000 | 27854000 | 2013-03-07 | 2014-04-04
2015-08-31 | 2015 | Marine Corps Active | M00318778 |  | 2014-01-10 | 2015-03-13 | DAWSON-HAWAIIAN BUILDERS I | N6274215C1316 | 14825000 | 12725000 | 2017-08-09 | 2017-08-09
2015-08-31 | 2011 | Marine Corps Active | M00318816 |  | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 0006 | 16634000 | 15088000 | 2013-11-16 | 2014-04-14
2015-08-31 | 2012 | Marine Corps Active | M00318822 |  | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 HC01 | 52970000 | 51509000 | 2014-03-17 | 2014-12-29
2015-08-31 | 2014 | Marine Corps Active | M00318852 |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407000 | 17509000 | 2016-10-04 | 2016-10-04
2015-08-31 | 2011 | Marine Corps Active | M00318858 |  | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6247811C1492 AWD | 62691000 | 62762000 | 2014-08-21 | 2015-10-01
2015-08-31 | 2014 | Marine Corps Active | M0031886167 |  | 2014-07-31 | 2014-12-22 | CT JV | N6247814D4004 KB01 | 1667000 | 1632000 | 2015-07-07 | 2015-08-14
2015-08-31 | 2014 | Marine Corps Active | M00318864 |  | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | N6274214C1315 AWD | 16968000 | 15319000 | 2015-09-09 | 2015-09-09
2015-08-31 | 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720000 | 15168000 | 2016-12-18 | 2016-12-18
2015-08-31 | 2013 | Marine Corps Active | M00318904 |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 63056000 | 57974000 | 2015-09-10 | 2015-09-29
2015-08-31 | 2013 | Marine Corps Active | M00318905 |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 11118000 | 7846000 | 2015-09-10 | 2015-09-29
2015-08-31 | 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 | 47646000 | 24343000 | 2017-01-03 | 2017-01-03
2015-08-31 | 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 | 53999000 | 42798000 | 2017-01-03 | 2017-01-03
2015-08-31 | 2011 | Marine Corps Active | M006811014 |  | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | N6247311C0405 AWD | 52425000 | 50802000 | 2013-09-21 | 2015-08-15
2015-08-31 | 2012 | Marine Corps Active | M006811037 |  | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0002-PC000002 | 11746000 | 9688000 | 2013-01-21 | 2013-08-05
2015-08-31 | 2012 | Marine Corps Active | M006811040 |  | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | N6247309D1606 0009 | 11432000 | 14119000 | 2013-09-27 | 2014-06-24
2015-08-31 | 2011 | Marine Corps Active | M006811043 | M006811043A | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | N6247310C5011 PC000001 | 29295000 | 27020000 | 2012-10-12 | 2015-08-21
2015-08-31 | 2011 | Marine Corps Active | M006811044 |  | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | N6247312C5033 AWD | 98236000 | 83649000 | 2016-01-13 | 2016-12-02
2015-08-31 | 2012 | Marine Corps Active | M006811045 |  | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242000 | 67005000 | 2016-03-31 | 2016-03-31
2015-08-31 | 2011 | Marine Corps Active | M006811109 |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 36173000 | 33977000 | 2013-10-13 | 2014-10-17
2015-08-31 | 2011 | Marine Corps Active | M006811113 |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 41889000 | 39186000 | 2013-10-13 | 2014-10-17
2015-08-31 | 2013 | Marine Corps Active | M006811176 |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428000 | 4496000 | 2016-04-21 | 2016-04-21
2015-08-31 | 2011 | Marine Corps Active | M006811200 |  | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | N6247310D5483 0003 | 9779000 | 8147000 | 2012-09-27 | 2012-12-31
2015-08-31 | 2011 | Marine Corps Active | M00681310 |  | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | N6247309D1618 0004 | 3760000 | 3340000 | 2012-07-06 | 2015-01-21
2015-08-31 | 2012 | Marine Corps Active | M00681532 |  | 2012-04-23 | 2012-08-31 | A&D GC INC | N6247309D1658 0006 | 11201000 | 10485000 | 2013-12-24 | 2014-12-23
2015-08-31 | 2011 | Marine Corps Active | M60169420 |  | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | N6945011C1760 AWD | 14780000 | 14868000 | 2013-06-08 | 2013-07-16
2015-08-31 | 2013 | Marine Corps Active | M60169427 |  | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | N6945013D1761 0001 | 10936000 | 10811000 | 2014-08-14 | 2015-01-20
2015-08-31 | 2012 | Marine Corps Active | M60169442 |  | 2011-12-06 | 2012-03-30 | HEAD, INC. | N6945012C1758 AWD | 18987000 | 18048000 | 2013-08-07 | 2013-09-27
2015-08-31 | 2011 | Marine Corps Active | M60169444 |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 40940000 | 38777000 | 2014-03-11 | 2014-06-09
2015-08-31 | 2011 | Marine Corps Active | M60169454 |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 45398000 | 45881000 | 2014-03-11 | 2014-06-09
2015-08-31 | 2013 | Marine Corps Active | M60169456 |  | 2012-08-27 | 2013-06-26 | HEAD, INC. | N6945013C1773 AWD | 12302000 | 12024000 | 2014-07-11 | 2015-07-31
2015-08-31 | 2013 | Marine Corps Active | M60169465 |  | 2012-11-15 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643000 | 37529000 | 2016-09-08 | 2016-10-03
2015-08-31 | 2013 | Marine Corps Active | M60169472 |  | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | N6945013C1772 AWD | 11043000 | 13289000 | 2014-03-28 | 2015-10-24
2015-08-31 | 2012 | Marine Corps Active | M62204925 |  | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | N6247309D1616 0009 | 7970000 | 7893000 | 2013-09-27 | 2014-04-09
2015-08-31 | 2015 | Marine Corps Active | M62204939 |  | 2015-01-14 | 2015-03-31 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0003 | 15300000 | 15055000
2015-08-31 | 2012 | Marine Corps Active | M626130601 |  | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | N4008412D6501 0002 | 13357000 | 12685000 | 2013-11-23 | 2013-12-14
2015-08-31 | 2013 | Marine Corps Active | M626130901 |  | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | N4008414C5500 AWD | 17551000 | 16715000 | 2015-10-13 | 2015-10-13
2015-08-31 | 2012 | Marine Corps Active | M626131001 |  | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | N4008412D6501 0004 | 11335000 | 10958000 | 2014-12-20 | 2015-02-02
2015-08-31 | 2013 | Marine Corps Active | M62613995 |  | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT | N6274214MP00027 | 4947000 | 4926000 | 2015-06-14 | 2015-06-14
2015-08-31 | 2013 | Marine Corps Active | M62613996 |  | 2014-04-07 | 2014-07-25 | NAVY STANDARD DOCUMENT | N6274214MP00039 | 6304000 | 6304000 | 2015-09-24 | 2015-09-24
2015-08-31 | 2013 | Marine Corps Active | M62974378 |  | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316000 | 13776000 | 2015-07-31 | 2016-03-09
2015-08-31 | 2011 | Marine Corps Active | M62974447A |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 30492000 | 29303000 | 2012-10-08 | 2013-10-15
2015-08-31 | 2011 | Marine Corps Active | M62974460 |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 47715000 | 46254000 | 2012-10-08 | 2013-10-15
2015-08-31 | 2011 | Marine Corps Active | M62974533 |  | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0002 | 26438000 | 23252000 | 2012-06-02 | 2013-04-19
2015-08-31 | 2012 | Marine Corps Active | M62974535 |  | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | N6247308D8617 0004 | 32048000 | 32618000 | 2014-07-07 | 2015-06-27
2015-08-31 | 2012 | Marine Corps Active | M62974545 |  | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0003 | 79917000 | 79669000 | 2014-05-20 | 2014-12-03
2015-08-31 | 2011 | Marine Corps Active | M62974546 |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 40106000 | 36766000 | 2012-07-08 | 2013-06-14
2015-08-31 | 2013 | Marine Corps Active | M62974566 |  | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247309D1603 0013 | 12671000 | 12136000 | 2014-09-22 | 2015-07-26
2015-08-31 | 2011 | Marine Corps Active | M62974573 |  | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0002 | 19793000 | 16195000 | 2012-07-25 | 2012-12-14
2015-08-31 | 2012 | Marine Corps Active | M62974575 |  | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | N6247312C1802 AWD | 29475000 | 28622000 | 2013-06-25 | 2014-01-31
2015-08-31 | 2011 | Marine Corps Active | M62974578 |  | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | N6247309D1653 0003 | 15045000 | 14670000 | 2012-09-11 | 2012-09-11
2015-08-31 | 2011 | Marine Corps Active | M62974583 |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 54843000 | 54497000 | 2012-07-08 | 2013-06-14
2015-08-31 | 2013 | Marine Corps Active | M67001003 |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260000 | 28073000 | 2015-09-01 | 2015-11-08
2015-08-31 | 2011 | Marine Corps Active | M67001004 |  | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | N4008510D5329 0002 | 12906000 | 13460000 | 2012-12-01 | 2015-09-15
2015-08-31 | 2012 | Marine Corps Active | M67001030 |  | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0003 | 16292000 | 12459000 | 2014-05-17 | 2015-01-24
2015-08-31 | 2011 | Marine Corps Active | M670011034 |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 79767000 | 81260000 | 2014-02-28 | 2014-12-15
2015-08-31 | 2011 | Marine Corps Active | M670011240 |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 32625000 | 31043000 | 2014-02-28 | 2014-12-15
2015-08-31 | 2011 | Marine Corps Active | M670011246 |  | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | N4008510D0259 0007 | 6613000 | 6032000 | 2012-08-20 | 2013-07-31
2015-08-31 | 2011 | Marine Corps Active | M670011249 |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 43950000 | 44653000 | 2013-07-13 | 2015-04-11
2015-08-31 | 2011 | Marine Corps Active | M670011251 |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 40236000 | 38215000 | 2013-10-08 | 2014-06-24
2015-08-31 | 2012 | Marine Corps Active | M670011253 |  | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | N4008512C7719 AWD | 74707000 | 72185000 | 2014-07-24 | 2015-03-12
2015-08-31 | 2011 | Marine Corps Active | M670011254 |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 39788000 | 37937000 | 2013-10-08 | 2014-06-24
2015-08-31 | 2011 | Marine Corps Active | M670011256 |  | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0006 | 1499000 | 1379000 | 2012-11-25 | 2012-11-25
2015-08-31 | 2011 | Marine Corps Active | M670011264 |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 55206000 | 56337000 | 2013-10-22 | 2016-09-26
2015-08-31 | 2011 | Marine Corps Active | M670011265 |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 54795000 | 53402000 | 2013-10-22 | 2016-09-26
2015-08-31 | 2011 | Marine Corps Active | M670011267 |  | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | N4008511C4022 AWD | 24316000 | 21703000 | 2013-02-06 | 2014-03-07
2015-08-31 | 2011 | Marine Corps Active | M670011286 |  | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | N4008511C4008 AWD | 54720000 | 54828000 | 2013-09-07 | 2015-07-31
2015-08-31 | 2011 | Marine Corps Active | M670011317 |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4021 AWD | 43568000 | 41166000 | 2013-08-30 | 2015-06-16
2015-08-31 | 2011 | Marine Corps Active | M670011319 |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4020 AWD | 46005000 | 42201000 | 2013-08-13 | 2014-08-29
2015-08-31 | 2011 | Marine Corps Active | M670011322 |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 49005000 | 40346000 | 2013-07-13 | 2015-04-11
2015-08-31 | 2011 | Marine Corps Active | M670011323 |  | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | N4008511C4001 P00004 | 5941000 | 5414000 | 2013-07-13 | 2015-04-11
2015-08-31 | 2014 | Marine Corps Active | M670011349 |  | 2014-02-27 | 2015-08-31 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0014 | 25742000 | 24159000 | 2017-03-21 | 2017-03-21
2015-08-31 | 2014 | Marine Corps Active | M670011353 |  | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529000 | 13952000 | 2016-03-01 | 2016-03-01
2015-08-31 | 2012 | Marine Corps Active | M67001138 |  | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101000 | 26519000 | 2014-07-29 | 2015-05-05
2015-08-31 | 2012 | Marine Corps Active | M670011383 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235000 | 63721000 | 2015-04-18 | 2016-09-14
2015-08-31 | 2013 | Marine Corps Active | M670011384 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666000 | 32328000 | 2015-04-18 | 2016-09-14
2015-08-31 | 2011 | Marine Corps Active | M670011400 |  | 2010-10-08 | 2011-05-31 | URS-IAP LLC | N6247006D6009 0016-02 | 8868000 | 9567000 | 2012-08-04 | 2014-01-16
2015-08-31 | 2012 | Marine Corps Active | M670011425 |  | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008511D8026 0008 | 2297000 | 2215000 | 2014-04-17 | 2014-11-29
2015-08-31 | 2014 | Marine Corps Active | M670011445 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 2123000 | 1938000 | 2017-02-04 | 2017-02-04
2015-08-31 | 2014 | Marine Corps Active | M670011447 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 9605000 | 9045000
2015-08-31 | 2014 | Marine Corps Active | M670011448 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 15756000 | 14902000
2015-08-31 | 2014 | Marine Corps Active | M67001674 |  | 2014-02-03 | 2015-08-19 | BRISTOL GENERAL CONTRACTORS, LLC | N4008515C0320 AWD | 17032000 | 15836000 | 2017-03-11 | 2017-03-11
2015-08-31 | 2014 | Marine Corps Active | M67001676 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312000 | 13295000 | 2015-12-20 | 2015-12-20
2015-08-31 | 2011 | Marine Corps Active | M67001683 |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62154000 | 59573000 | 2013-11-29 | 2015-06-15
2015-08-31 | 2011 | Marine Corps Active | M67001687 |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62617000 | 59773000 | 2013-11-29 | 2015-06-15
2015-08-31 | 2012 | Marine Corps Active | M67001705 |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 57582000 | 65023000 | 2014-07-07 | 2015-08-11
2015-08-31 | 2012 | Marine Corps Active | M67001710 |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 7768000 | 7389000 | 2014-07-07 | 2015-08-11
2015-08-31 | 2013 | Marine Corps Active | M67001711 |  | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0018 | 6449000 | 5707000 | 2015-07-06 | 2015-12-24
2015-08-31 | 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159000 | 10039000 | 2015-12-20 | 2015-12-20
2015-08-31 | 2014 | Marine Corps Active | M67004934 |  | 2013-12-06 | 2014-09-10 | BLUEFORGE, LLC | N6945014D1271 0001 | 14685000 | 14309000 | 2016-01-25 | 2016-01-25
2015-08-31 | 2014 | Marine Corps Active | M67004954 |  | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | N6945012D1769 0005 | 1248000 | 1184000 | 2015-06-02 | 2015-06-02
2015-08-31 | 2011 | Marine Corps Active | M670291101 |  | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0001-07 | 41000 | 39000 | 2011-05-13 | 2011-08-31
2015-08-31 | 2012 | Marine Corps Active | M67399105 |  | 2012-03-06 | 2012-06-15 | ALLEN ENGINEERING CONTRACTOR, INC | N6247309D1654 0005 | 13925000 | 13367000 | 2014-03-22 | 2014-03-22
2015-08-31 | 2015 | Marine Corps Active | M67399159 |  | 2015-01-30 | 2015-04-15 | RQ-BERG JV | N6247310D5482 0009 | 28645000 | 26869000 | 2017-05-01 | 2017-05-01
2015-08-31 | 2011 | Marine Corps Active | M67399163 |  | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | N6247310C5007 PC000001 | 51987000 | 51437000 | 2012-10-12 | 2013-06-17
2015-08-31 | 2012 | Marine Corps Active | M67399177 |  | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819000 | 20150000 | 2014-09-02 | 2016-07-21
2015-08-31 | 2012 | Marine Corps Active | M67399212 |  | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | N6247310D5412 0006 | 21313000 | 20532000 | 2013-12-12 | 2015-09-01
2015-08-31 | 2012 | Marine Corps Active | M67399541 |  | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | N6247309D1655 0003 | 15610000 | 14744000 | 2014-04-20 | 2015-04-14
2015-08-31 | 2012 | Marine Corps Active | M67399991 |  | 2011-11-14 | 2015-01-15 | NAVY STANDARD DOCUMENT | N6247314MPRM002 | 2249000 | 2092000
2015-08-31 | 2014 | Marine Corps Active | M67400201 |  | 2013-11-08 | 2014-04-18 | NAVY STANDARD DOCUMENT | N6274214MP00024 | 2881000 | 2861000 | 2015-10-26 | 2015-10-26
2015-08-31 | 2013 | Marine Corps Active | M67400305 |  | 2013-07-10 | 2014-09-25 | NAVY STANDARD DOCUMENT | N6274214MP00043 | 1729000 | 1719000 | 2015-06-29 | 2015-06-29
2015-08-31 | 2011 | Marine Corps Active | M67604109 |  | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0434 AWD | 51999000 | 46315000 | 2014-01-08 | 2014-06-23
2015-08-31 | 2011 | Marine Corps Active | M67604111 |  | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | N6247310D5409 0003 | 47061000 | 33610000 | 2013-03-13 | 2013-10-29
2015-08-31 | 2013 | Marine Corps Active | M67604113 |  | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | N6247309D1619 0008 | 4380000 | 4121000 | 2014-09-21 | 2014-09-21
2015-08-31 | 2012 | Marine Corps Active | M67604114 |  | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0004 | 40539000 | 39102000 | 2015-08-10 | 2015-12-29
2015-08-31 | 2012 | Marine Corps Active | M67604116 |  | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | N6247309D1605 0012 | 14938000 | 11766000 | 2014-01-03 | 2015-03-27
2015-08-31 | 2012 | Marine Corps Active | M67604117 |  | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | N6247007D7000 FZN7 | 7437000 | 7225000 | 2013-10-07 | 2015-10-07
2015-08-31 | 2011 | Marine Corps Active | M67695005 |  | 2011-04-29 | 2011-09-16 | SAUER, INC. | N6945009D1277 0005 | 20345000 | 19809000 | 2013-05-16 | 2014-01-24
2015-08-31 | 2011 | Marine Corps Active | M67695012 |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3380000 | 2529000 | 2013-12-05 | 2013-12-05
2015-08-31 | 2011 | Marine Corps Active | M67695017 |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 12623000 | 7904000 | 2013-12-05 | 2013-12-05
2015-08-31 | 2011 | Marine Corps Active | M67695022 |  | 2010-11-22 | 2011-06-03 | SAUER, INC. | N6945009D1277 0003 | 13295000 | 11139000 | 2012-07-27 | 2013-12-20
2015-08-31 | 2011 | Marine Corps Active | M67695023 |  | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | N6945011D1259 0002 | 8877000 | 8449000 | 2012-11-19 | 2012-11-19
2015-08-31 | 2011 | Marine Corps Active | M67695024 |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3702000 | 3370000 | 2013-12-05 | 2013-12-05
2015-08-31 | 2012 | Marine Corps Active | M678611201 |  |  | 2012-01-04 | Awarded by Other Agency |  | 45000 | 45000
2015-08-31 | 2011 | Marine Corps Active | M67865152 |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 32816000 | 35501000 | 2014-09-19 | 2014-09-19
2015-08-31 | 2013 | Marine Corps Active | M67865181 |  | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0002 | 13634000 | 14571000 | 2015-09-28 | 2015-11-13
2015-08-31 | 2011 | Marine Corps Active | M67865185 |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 27121000 | 27825000 | 2014-09-19 | 2014-09-19
2015-08-31 | 2011 | Marine Corps Active | M67865192 |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 56417000 | 54610000 | 2014-09-19 | 2014-09-19
2015-08-31 | 2013 | Marine Corps Active | N41557101 | N41557101A | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | N6274210D1309 JQ01 | 24305000 | 19383000 | 2015-07-12 | 2015-12-15
2015-08-31 | 2014 | Marine Corps Active | N41557109 |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820000 | 57055000 | 2016-12-03 | 2016-12-03
2015-08-31 | 2014 | Marine Corps Active | N41557J200 |  | 2014-04-11 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 | 53014000 | 47830000 | 2016-09-02 | 2016-09-02
2015-08-31 | 2011 | Marine Corps Active | N605141403 |  | 2015-03-06 | 2011-09-30 | LAKESHORE TOLTEST JV, LLC | N6945011C1260 AWD | 35175000 | 38815000 | 2014-03-16 | 2014-02-28
2015-08-31 | 2011 | Marine Corps Active | N61755204 | N61755204A | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | N4019210D2803 0006 | 21579000 | 16529000 | 2014-06-19 | 2014-09-30
2015-08-31 | 2014 | Marine Corps Active | N61755H106 |  | 2013-11-14 | 2015-04-30 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 0002 | 24771000 | 23121000 | 2017-08-13 | 2017-08-13
2015-08-31 | 2013 | Marine Corps Active | N69212984 |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028000 | 10983000 | 2015-06-26 | 2015-11-09
2015-08-31 | 2013 | Marine Corps Active | N69212985 |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418000 | 17930000 | 2015-06-26 | 2015-11-09
2015-08-31 | 2013 | Marine Corps Active | N69212986 |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 5841000 | 5739000 | 2015-03-23 | 2015-04-19
2015-08-31 | 2013 | Marine Corps Active | N69212987 |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 6987000 | 6694000 | 2015-03-23 | 2015-04-19
2015-08-31 | 2013 | Marine Corps Active | N69212989 |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 3653000 | 3537000 | 2015-03-23 | 2015-04-19
2015-08-31 | 2011 | Marine Corps Reserve | M626130501 |  | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | N4008411C5504 AWD | 11626000 | 11102000 | 2013-01-14 | 2013-02-28
2015-08-31 | 2014 | Marine Corps Reserve | M67386139 |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019000 | 16070000 | 2016-02-23 | 2016-02-23
2015-08-31 | 2011 | Marine Corps Reserve | M67399092 |  | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | N6247309D1615 0041 | 6458000 | 6168000 | 2012-09-21 | 2013-03-28
2015-08-31 | 2012 | Marine Corps Reserve | M68479030 |  | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | N4008313C0019 AWD | 9006000 | 8567000 | 2015-02-17 | 2015-02-17
2015-08-31 | 2011 | Marine Corps Reserve | M68479060 |  | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0005 | 14630000 | 14206000 | 2013-02-08 | 2015-04-15
2015-08-31 | 2013 | Marine Corps Reserve | M68479130 |  | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911000 | 4900000 | 2014-12-04 | 2015-10-26
2015-08-31 | 2012 | Marine Corps Reserve | N00206501 |  | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | N6945013C5571 AWD | 1286000 | 1237000 | 2014-05-22 | 2014-06-20
2015-08-31 | 2015 | Marine Corps Reserve | N00620234 |  | 2014-12-30 | 2015-07-29 | SWINERTON BUILDERS | N4425515C6001 AWD | 59450000 | 28024000 | 2016-12-15 | 2016-12-15
2015-08-31 | 2010 | Missile Defense Agency | 627 | 4 | 2012-01-19 | 2012-06-04 | URS GROUP, INC | N62742-09-D-1174 | 59616000 | 69657000 | 2013-09-12 | 2013-11-07 | GMAC Construction - awaiting Interim 1354
2015-08-31 | 2010 | Missile Defense Agency | 627 |  | 2011-06-30 | 2011-08-03 | TOMCO CORP. | N62478-10-D-4024 | 294000 | 294000 | 2011-11-18 | 2011-11-18 | Clearing and Grubbing Only
2015-08-31 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 66900000 | 2015-08-30 | 2015-11-17 | Site Identifier is pending as this is a new Installation; awaiting Interim 1354; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2015-08-31 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 114560000 | 2015-08-30 | 2015-11-17 | Site Identifier is pending as this is a new Installation; awaiting Interim 1354; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2015-08-31 | 2012 | Missile Defense Agency | 633 |  | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | W91278-12-C-0017 | 51330000 | 59842000 | 2014-07-10 | 2014-10-15 | Awaiting Final 1354
2015-08-31 | 2014 | Missile Defense Agency | 634 |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300000 | 14193000 | 2016-01-06 | 2016-01-06 | Awaiting Interim 1354
2015-08-31 | 2013 | Missile Defense Agency | 639 |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584000 | 15270000 | 2014-11-28 | 2015-09-12 | Awaiting Final 1354
2015-08-31 | 2014 | Missile Defense Agency | 648 |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991000 | 15786000 | 2015-01-09 | 2015-02-20 | Site Identifier is pending as this is a new Installation.
2015-08-31 | 2014 | Missile Defense Agency | 649 |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838000 | 46800000 | 2016-05-31 | 2016-05-31 | Construction re-mobilized on 23 March 2015; Awaiting Interim 1354
2015-08-31 | 2010 | Missile Defense Agency | 655 |  | 2014-03-24 | 2014-05-09 | Arctic Slope Regional Corporation (ASRC) | W912DY-14-D-0042-0001 | 1832000 | 1832000 | 2014-12-11 | 2014-12-28 | Awaiting Interim 1354
2015-06-01 | 2008 | National Geospatial-Intelligence Agency | 65416 |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture | W912DR-07-C-0027 | 1409901000 | 1467244000 | 2011-12-22 | 2015-11-21
2015-06-01 | 2012 | National Geospatial-Intelligence Agency | NGA013 |  | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 32387000 | 39495000 | 2014-01-02 | 2015-01-31 | Technology Center Third Floor Fit-out - project period of performance extended to 31 May 2015
2015-06-01 | 2012 | National Geospatial-Intelligence Agency | NGA021 |  | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors |  | 8202000 | 11198000 | 2013-08-06 | 2015-01-31 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 30 September 2015
2015-06-01 | 2007 | National Geospatial-Intelligence Agency | [8 empty] | 2013-06-15 | 31-Apr-2015
2015-08-31 | 2010 | National Security Agency | 17781 |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700000 | 11700000 | 2011-08-20 | 2012-05-30
2015-08-31 | 2010 | National Security Agency | 17782 |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200000 | 3200000 | 2013-07-13 | 2015-11-30 | Due to problems with financing issues between the USACE and Walsh, end date is 30 Nov 2015.
2015-08-31 | 2011 | National Security Agency | 17866 |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900000 | 130751000 | 2014-11-30 | 2015-10-31 | Working in minor change orders and waiting for the demolition.
2015-08-31 | 2010 | National Security Agency | 17872 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223000 | 129078000 | 2014-04-18 | 2015-10-12
2015-08-31 | 2010 | National Security Agency | 18052 |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566000 | 8257000 | 2013-02-01 | 2014-05-14
2015-08-31 | 2010 | National Security Agency | 18053 |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095000 | 16448000 | 2013-02-01 | 2014-05-31
2015-08-31 | 2010 | National Security Agency | 18054 |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085000 | 7316000 | 2013-02-01 | 2014-08-31 | Commissioning of system completed November 26, 2014.
2015-08-31 | 2009 | National Security Agency | 21120 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060000 | 13760000 | 2013-01-17 | 2014-04-18
2015-08-31 | 2010 | National Security Agency | 21372 |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443000 | 4201000 | 2011-09-26 | 2012-06-29
2015-08-31 | 2012 | National Security Agency | 23051 | 16 | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621000 | 5627000 | 2014-02-14 | 2015-09-30
2015-08-31 | 2012 | National Security Agency | 23051 |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975000 | 131347000 | 2015-05-03 | 2015-11-30 | BOD issued on 28 July 2015. Working on construction punch list items-estimated completion 30 Nov 2015.
2015-08-31 | 2012 | National Security Agency | 24649 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589000 | 597460000 | 2015-09-15 | 2015-10-20 | Execution of Modification E/F - BGE Permanent Power Delay resulted in a Construction Completion Date extension of 51 calendar days from 20 Oct 2015 to 10 Dec 2015.
2015-08-31 | 2010 | National Security Agency | 25047 |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253000 | 5792000 | 2014-03-07 | 2015-05-04 | Completing remaining punch list items.
2015-08-31 | 2013 | National Security Agency | 26170 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91866000 | 99424000 | 2015-10-11 | 2016-03-19 | Data from RMS run 18 Aug 2015.
2015-08-31 | 2011 | National Security Agency | 20489 20489 23994 | 13 | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620000 | 2657000 | 2014-02-28 | 2014-04-28
2015-08-31 | 2011 | National Security Agency | 20489 20489 23994 | 14 | 2012-04-26 | 2012-06-18 | JAAT | W912HN-10-D-0063 | 15315000 | 16526000 | 2015-01-30 | 2014-12-23
2015-08-31 | 2011 | National Security Agency | 20489 20489 23994 |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657000 | 8867000 | 2014-01-30 | 2015-01-16
2015-08-31 | 2012 | Navy Active | M006811046 |  | 2014-08-28 | 2014-11-25 | ORION CONSTRUCTION CORPORATION | N6247310D5419 0012 | 75135000 | 43991000 | 2016-12-08 | 2016-12-08
2015-08-31 | 2014 | Navy Active | M626131403 |  | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545000 | 15632000 | 2016-02-02 | 2016-02-02
2015-08-31 | 2015 | Navy Active | M62613602 |  | 2014-11-21 | 2015-04-27 | NAVY STANDARD DOCUMENT | N6274215MP00014 | 4913000 | 4742000 | 2016-06-13 | 2016-06-13
2015-08-31 | 2014 | Navy Active | M678611407 |  |  | 2014-09-30 | QUALITY SUPPORT SERVICES, INC. | N4008314D1014 0003 | 75000 | 93000 | 2014-11-30 | 2015-07-30
2015-08-31 | 2012 | Navy Active | N00128816 |  | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491000 | 68901000 | 2016-07-14 | 2016-07-14
2015-08-31 | 2012 | Navy Active | N00204791 |  | 2012-07-25 | 2012-09-29 | R L BURNS INC. | N6945012C6343 AWD | 2038000 | 1975000 | 2013-08-08 | 2013-08-08
2015-08-31 | 2012 | Navy Active | N00207153 |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 2851000 | 2936000 | 2013-12-17 | 2014-04-09
2015-08-31 | 2012 | Navy Active | N00207624 |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 14194000 | 13889000 | 2013-12-17 | 2014-04-09
2015-08-31 | 2015 | Navy Active | N00207631 |  | 2014-04-01 | 2015-02-27 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 | 11078000 | 10270000 | 2016-04-19 | 2016-06-26
2015-08-31 | 2012 | Navy Active | N00207654 |  | 2012-12-20 | 2015-03-31 | HCR CONSTRUCTION INC | N6945015C1102 | 6448000 | 5666000
2015-08-31 | 2013 | Navy Active | N00207655 |  | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | N6945013C1257 AWD | 18180000 | 18991000 | 2014-12-27 | 2015-08-27
2015-08-31 | 2014 | Navy Active | N00207659 |  | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573000 | 9788000 | 2016-04-19 | 2016-06-26
2015-08-31 | 2015 | Navy Active | N00207664 |  | 2015-01-26 | 2015-04-30 | PHOENIX CONSTRUCTION SERVICES, INC. | N6945015C1104 | 7293000 | 6516000
2015-08-31 | 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151000 |  | 2016-01-07 | 2016-02-14
2015-08-31 | 2011 | Navy Active | N00245327 |  | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | N6247311C2850 AWD | 99132000 | 115870000 | 2013-10-22 | 2014-11-30
2015-08-31 | 2011 | Navy Active | N00245405 |  | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247311C2804 AWD | 72294000 | 69994000 | 2013-10-23 | 2013-12-03
2015-08-31 | 2013 | Navy Active | N00245500 |  | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553000 | 41155000 | 2015-10-24 | 2016-01-09
2015-08-31 | 2012 | Navy Active | N00246705 |  | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | N6247310D5409 0013 | 46630000 | 44494000 | 2015-03-16 | 2015-08-26
2015-08-31 | 2013 | Navy Active | N00246730 |  | 2013-05-29 | 2015-07-30 | HENSEL PHELPS CONSTRUCTION CO | N6247315C1614 | 74785000 | 5521000 | 2015-01-12 | 2015-01-12
2015-08-31 | 2011 | Navy Active | N00246750 |  | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | N6247312C1406 P00001 | 64063000 | 63863000 | 2012-04-16 | 2014-03-11
2015-08-31 | 2012 | Navy Active | N00246880 |  | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977000 | 57531000 | 2015-03-30 | 2015-10-18
2015-08-31 | 2012 | Navy Active | N00246896 |  | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | N6247311D0067 0004 | 1816000 | 1744000 | 2014-01-31 | 2014-10-17
2015-08-31 | 2013 | Navy Active | N00246909 |  | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088000 | 2968000 | 2015-03-15 | 2015-05-14
2015-08-31 | 2013 | Navy Active | N00246943 |  | 2014-05-06 | 2014-09-16 | NAVY STANDARD DOCUMENT | N6247014POR0018 | 1652000 | 1425000
2015-08-31 | 2014 | Navy Active | N00246957 |  | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904000 | 8510000 | 2016-02-10 | 2016-02-10
2015-08-31 | 2014 | Navy Active | N00620239 |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5004 | 29692000 | 27249000 | 2017-05-26 | 2017-05-26
2015-08-31 | 2013 | Navy Active | N00620245 |  | 2012-08-16 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0009 | 5679000 | 5973000 | 2014-11-25
2015-08-31 | 2013 | Navy Active | N00620246 |  | 2013-06-18 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | N4425513C7005 AWD | 1120000 | 1073000 | 2014-09-30 | 2014-12-19
2015-08-31 | 2014 | Navy Active | N00620251 |  | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5002 AWD | 84889000 | 80144000 | 2016-01-12 | 2016-01-26
2015-08-31 | 2014 | Navy Active | N00620257 |  | 2014-06-20 | 2014-09-02 | RORE, INC. | N4425514C8012 | 1424000 | 1384000
2015-08-31 | 2013 | Navy Active | N32411056 |  | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | N4008510D9450 0006 | 2332000 | 2331000 | 2013-10-31 | 2013-12-13
2015-08-31 | 2011 | Navy Active | N32411068 |  | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | N4008511C7231 AWD | 24394000 | 26541000 | 2013-08-22 | 2014-09-26
2015-08-31 | 2014 | Navy Active | N32411103 |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319000 | 13055000 | 2015-12-16 | 2016-01-01
2015-08-31 | 2011 | Navy Active | N32414203 |  | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | N4008512C5002 AWD | 1951000 | 1838000 | 2012-09-13 | 2012-09-13
2015-08-31 | 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 | 34317000 | 32014000 | 2016-11-23 | 2016-11-23
2015-08-31 | 2012 | Navy Active | N32443383 |  | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576000 | 32960000 | 2014-09-28 | 2015-04-06
2015-08-31 | 2011 | Navy Active | N32443516 | N32443516A | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | N4008510C3006 P00003 | 68459000 | 68874000 | 2014-11-22 | 2015-10-02
2015-08-31 | 2013 | Navy Active | N32443998 |  | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374000 | 28204000 | 2015-12-27 | 2015-12-27
2015-08-31 | 2014 | Navy Active | N32446266 |  | 2013-12-30 | 2015-08-17 | METHUEN CONSTRUCTION CO., INC | N4008515C8746 AWD | 31542000 | 29530000 | 2018-01-23 | 2018-01-23
2015-08-31 | 2011 | Navy Active | N3379A219 |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 7716000 | 8144000 | 2013-12-26 | 2014-08-24
2015-08-31 | 2014 | Navy Active | N3379A227 |  | 2014-02-26 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492000 | 4227000 | 2015-09-28 | 2015-09-28
2015-08-31 | 2011 | Navy Active | N3379A912 |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 3107000 | 3663000
2015-08-31 | 2014 | Navy Active | N3379A917 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1120000 | 1120000
2015-08-31 | 2014 | Navy Active | N3379A918 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1175000 | 1175000
2015-08-31 | 2014 | Navy Active | N3379A919 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1064000 | 1064000
2015-08-31 | 2014 | Navy Active | N3379A921 |  | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714000 | 19599000 | 2016-05-30 | 2016-07-25
2015-08-31 | 2014 | Navy Active | N41557625 |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710000 | 49717000 | 2016-04-25 | 2016-09-23
2015-08-31 | 2015 | Navy Active | N42237099 |  | 2013-12-10 | 2015-07-22 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 | 38595000 | 37267000
2015-08-31 | 2014 | Navy Active | N42237100 |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249000 | 121074000 | 2018-06-20 | 2018-04-08
2015-08-31 | 2011 | Navy Active | N42237601 |  | 2011-12-13 | 2012-03-16 | SAUER, INC. | N6945009D1277 0007 | 37278000 | 39759000 | 2013-09-07 | 2014-12-09
2015-08-31 | 2011 | Navy Active | N42237620 |  | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | N6945010D1271 0003 | 15010000 | 17004000 | 2013-05-13 | 2015-06-02
2015-08-31 | 2012 | Navy Active | N42237636 |  | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167000 | 54742000 | 2017-04-16 | 2017-04-16
2015-08-31 | 2014 | Navy Active | N47608262 |  | 2014-08-11 | 2014-09-30 | REILLY CONSTRUCTION, INC | N4008014D3014 AWD | 1453000 | 1405000
2015-08-31 | 2011 | Navy Active | N47608263 |  | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | N4008011C0154 AWD | 33033000 | 34871000 | 2012-07-30 | 2014-07-16
2015-08-31 | 2012 | Navy Active | N47608561 |  | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49890000 | 47571000 | 2016-04-01 | 2016-04-29
2015-08-31 | 2013 | Navy Active | N47609003 |  | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | N6247313D4608 0007 | 1896000 | 1792000 | 2015-06-26 | 2015-06-26
2015-08-31 | 2012 | Navy Active | N50092199 |  | 2012-10-31 | 2012-12-14 | JESSICO, INC | N4008511D3021 0008 | 970000 | 938000 | 2013-11-08 | 2013-11-15
2015-08-31 | 2011 | Navy Active | N50092201 |  | 2011-05-26 | 2011-08-03 | JESSICO, INC | N4008511C3026 AWD | 2085000 | 1989000 | 2012-09-30 | 2012-11-13
2015-08-31 | 2011 | Navy Active | N50092242 |  | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008512C7000 AWD | 1725000 | 1616000 | 2012-07-21 | 2013-05-31
2015-08-31 | 2013 | Navy Active | N50092255 |  | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008513C7711 AWD | 1925000 | 1890000 | 2013-08-30 | 2013-09-29
2015-08-31 | 2012 | Navy Active | N50092499 |  | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | N4008512C1704 AWD | 29520000 | 28699000 | 2014-10-09 | 2015-08-01
2015-08-31 | 2014 | Navy Active | N50092662 |  | 2014-05-09 | 2014-08-06 | DOYON MANAGEMENT SERVICES, LLC | N4008514D2102 0001 | 1020000 | 240000 | 2014-11-21 | 2015-01-20
2015-08-31 | 2011 | Navy Active | N57095101 |  | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | N4008509D5027 0003-PC000002 | 1381000 | 1326000 | 2011-09-21 | 2012-01-27
2015-08-31 | 2012 | Navy Active | N57095197 |  | 2012-04-17 | 2012-09-20 | SAUER, INC. | N4008509D5026 0004 | 27161000 | 27145000 | 2015-05-08 | 2015-07-07
2015-08-31 | 2014 | Navy Active | N60042116 |  |  | 2014-12-11 | NAVY STANDARD DOCUMENT | N6247315MPRM001 | 1725000 | 1560000
2015-08-31 | 2011 | Navy Active | N60042260 |  |  | 2011-09-29 | NAVY STANDARD DOCUMENT | N6247311RP00189 | 1421000 | 1658000
2015-08-31 | 2013 | Navy Active | N60191513 |  | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430000 | 29201000 | 2015-12-16 | 2015-12-30
2015-08-31 | 2012 | Navy Active | N60191527 |  | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599000 | 19141000 | 2014-10-12 | 2015-05-07
2015-08-31 | 2013 | Navy Active | N60191582 |  | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0003 | 4129000 | 4847000 | 2013-11-29 | 2014-06-27
2015-08-31 | 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446000 | 11313000 | 2016-10-25 | 2016-10-25
2015-08-31 | 2014 | Navy Active | N60201425 |  | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | N6945013D1765 0002 | 15842000 | 15292000 | 2015-11-26 | 2016-01-10
2015-08-31 | 2012 | Navy Active | N60201503 |  | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | N6945012C0757 AWD | 7518000 | 10315000 | 2014-02-21 | 2015-03-02
2015-08-31 | 2013 | Navy Active | N60241288 |  | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | N6945014C0763 AWD | 1790000 | 1682000 | 2015-03-27 | 2015-05-27
2015-08-31 | 2012 | Navy Active | N60241294 |  | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | N6945010D0776 0002 | 1658000 | 1549000 | 2014-03-21 | 2014-08-25
2015-08-31 | 2011 | Navy Active | N60508266 |  | 2012-07-05 | 2012-09-28 | HEAD, INC. | N6945012C0760 AWD | 29901000 | 32950000 | 2014-09-28 | 2015-05-19
2015-08-31 | 2015 | Navy Active | N60508278 |  | 2014-04-28 | 2015-07-22 | NAVY STANDARD DOCUMENT | N6247015MPS0050 | 1367000 | 1364000 | 2016-02-16 | 2016-02-16
2015-08-31 | 2012 | Navy Active | N60508927 |  | 2012-02-17 | 2012-06-07 | NAVY STANDARD DOCUMENT | N6247012MPS0048 | 18810000 | 20636000 | 2015-06-15 | 2015-06-15
2015-08-31 | 2011 | Navy Active | N61007015 |  |  | 2011-12-31 | NAVY STANDARD DOCUMENT | N6945011RP00148 | 3149000 | 3080000
2015-08-31 | 2012 | Navy Active | N61014851 |  | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | N6247314C2801 AWD | 1916000 | 1895000 | 2014-10-17 | 2014-12-31
2015-08-31 | 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458000 | 9458000 | 2017-01-17 | 2017-01-17
2015-08-31 | 2011 | Navy Active | N61054012 |  | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | N4008410D0014 0003 | 1380000 | 1256000 | 2012-04-13 | 2012-04-20
2015-08-31 | 2013 | Navy Active | N61054022 |  |  | 2014-02-06 | HIBIYA ENGINEERING LTD. | N4008410D0121 0035 | 840000 | 898000
2015-08-31 | 2011 | Navy Active | N610541101 |  | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | N4008411C0129 AWD | 17378000 | 16915000 | 2012-12-03 | 2013-01-20
2015-08-31 | 2012 | Navy Active | N610541201 |  | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | N4008412C0108 AWD | 19730000 | 18773000 | 2014-01-13 | 2014-01-13
2015-08-31 | 2012 | Navy Active | N610541202 |  | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | N4008412C0109 AWD | 9033000 | 9298000 | 2014-10-07 | 2015-06-10
2015-08-31 | 2013 | Navy Active | N610541305 |  | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791000 | 7305000 | 2016-02-21 | 2016-02-21
2015-08-31 | 2013 | Navy Active | N61056353 |  | 2013-01-24 | 2013-09-27 | NAVY STANDARD DOCUMENT | N6274213MP00015 | 5627000 | 70541000 | 2017-07-29 | 2017-07-29
2015-08-31 | 2012 | Navy Active | N610571201 |  | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | N4008412C8325 AWD | 5990000 | 5654000 | 2013-08-26 | 2013-11-22
2015-08-31 | 2012 | Navy Active | N610571202 |  | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | N4008412C0004 AWD | 17540000 | 14246000 | 2013-12-09 | 2014-07-01
2015-08-31 | 2013 | Navy Active | N610571302 |  | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | N4008414C8401 AWD | 12958000 | 12050000 | 2015-03-31 | 2015-05-05
2015-08-31 | 2011 | Navy Active | N61057203 |  | 2010-12-09 | 2011-07-29 | NAVY STANDARD DOCUMENT | N6274211MP00014 | 6764000 | 6442000 | 2013-11-13 | 2013-11-13
2015-08-31 | 2014 | Navy Active | N61057221 |  | 2014-06-12 | 2014-08-06 | NIHON MECCS CO., LTD. | N4008414C8302 AWD | 890000 | 812000 | 2015-02-03 | 2015-05-19
2015-08-31 | 2014 | Navy Active | N610581401 |  | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799000 | 21637000
2015-08-31 | 2012 | Navy Active | N61064400 |  | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | N6247811D4046 0005 | 6498000 | 5905000 | 2014-01-02 | 2014-12-31
2015-08-31 | 2013 | Navy Active | N61065229 |  | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447000 | 27999000 | 2016-04-17 | 2016-06-16
2015-08-31 | 2014 | Navy Active | N61065240 |  | 2015-02-23 | 2015-04-16 | TEEHEE ENGINEERING, INC. | N6247315C4204 | 1950000 | 1867000 | 2016-10-21 | 2016-10-21
2015-08-31 | 2013 | Navy Active | N61077123 |  | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | N4008413C9001 AWD | 755000 | 768000 | 2013-03-10 | 2013-03-10
2015-08-31 | 2011 | Navy Active | N61151162 |  | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | N4008012C2001 AWD | 34869000 | 47521000 | 2014-06-16 | 2015-11-15
2015-08-31 | 2012 | Navy Active | N61151222 |  | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984000 | 65203000 | 2015-11-06 | 2015-11-06
2015-08-31 | 2013 | Navy Active | N61151290 |  | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0007 | 14130000 | 14184000 | 2015-03-12 | 2015-09-30
2015-08-31 | 2013 | Navy Active | N61151372 |  | 2012-12-12 | 2013-09-27 | C.E.R. INC. | N4008010D0302 0021 | 11409000 | 10864000 | 2015-05-02 | 2015-09-16
2015-08-31 | 2014 | Navy Active | N61152001 |  | 2014-01-13 | 2015-04-07 | NAVY STANDARD DOCUMENT | N6247015MPC0032 | 109736000 | 106596000 | 2017-05-04 | 2017-05-04
2015-08-31 | 2013 | Navy Active | N617551301 |  | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 JQ02 | 26805000 | 25414000 | 2015-09-09 | 2015-10-10
2015-08-31 | 2011 | Navy Active | N61755205 |  |  | 2015-06-16 | OTHER - TRANSFER TO FEDERAL HIGHWAY ADMINISTRATION |  | 65236000 | 65236000
2015-08-31 | 2014 | Navy Active | N61755425 |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865000 | 47550000 | 2016-06-11 | 2017-01-20
2015-08-31 | 2014 | Navy Active | N61755518 |  | 2014-01-10 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085000 | 44320000 | 2016-10-20 | 2017-03-15
2015-08-31 | 2014 | Navy Active | N61755566 |  | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860000 | 27808000 | 2016-05-12 | 2016-06-29
2015-08-31 | 2014 | Navy Active | N61755630 |  | 2014-07-01 | 2014-09-30 | P&S CONSTRUCTION, INC. | N4019210D2804 0019 | 2000000 | 1925000 | 2015-12-24 | 2015-12-24
2015-08-31 | 2014 | Navy Active | N61755637 |  | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170000 | 14391000 | 2016-04-11 | 2016-04-11
2015-08-31 | 2014 | Navy Active | N61755638 |  | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | N4019210D2808 0009 | 1462000 | 1232000 | 2015-03-26 | 2015-04-25
2015-08-31 | 2013 | Navy Active | N62590400 |  | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | N6247014MPE0025 | 40018000 | 38282000
2015-08-31 | 2012 | Navy Active | N62688123 |  | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | N4008512C4572 AWD | 74854000 | 72267000 | 2014-09-13 | 2015-05-31
2015-08-31 | 2014 | Navy Active | N62688500 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365000 | 1199000 | 2016-01-01 | 2016-01-01
2015-08-31 | 2011 | Navy Active | N62688828 |  | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008511D6585 0001 | 1395000 | 1273000 | 2012-06-18 | 2012-11-07
2015-08-31 | 2011 | Navy Active | N62688862 |  | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | N4008511C0020 AWD | 3659000 | 2953000 | 2012-08-09 | 2012-09-28
2015-08-31 | 2011 | Navy Active | N627351102 |  | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | N4008411C0006 AWD | 8127000 | 6990000 | 2012-10-17 | 2013-02-14
2015-08-31 | 2011 | Navy Active | N62813005 |  | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274211C1300 AWD | 95540000 | 86376000 | 2013-07-05 | 2015-08-13
2015-08-31 | 2012 | Navy Active | N62813041 |  | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | N6247810D4022 0019 | 7708000 | 7642000 | 2013-11-16 | 2014-11-09
2015-08-31 | 2015 | Navy Active | N62813048 |  | 2014-10-20 | 2015-02-27 | JSR ECC, LLC | N6247814D4003 | 8667000 | 8100000 | 2016-10-04 | 2016-10-04
2015-08-31 | 2011 | Navy Active | N62813056 |  | 2011-02-04 | 2011-06-24 | FOPCO, INC | N6247810D4019 0006 | 7856000 | 9022000 | 2012-08-15 | 2013-04-30
2015-08-31 | 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810000 | 2654000 | 2016-05-18 | 2016-05-18
2015-08-31 | 2011 | Navy Active | N62813071 |  | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | N6247810D4020 0014 | 1559000 | 1446000 | 2012-12-24 | 2013-03-01
2015-08-31 | 2014 | Navy Active | N62813270 |  | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355000 | 20360000 | 2015-12-11 | 2015-12-11
2015-08-31 | 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970000 | 31384000 | 2017-08-03 | 2017-12-18
2015-08-31 | 2012 | Navy Active | N628631201 |  | 2014-04-29 | 2015-03-13 | SOCIEDAD ESPNOLA DE MONTAJES INDUSTRIALES SA DBA SEMI | N3319115C0817 | 13982000 | 13487000
2015-08-31 | 2012 | Navy Active | N62863708 |  | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | N3319110D0219 0009 | 1751000 | 1411000 | 2014-05-28 | 2014-06-20
2015-08-31 | 2013 | Navy Active | N62863709 |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 2446000 | 1945000 | 2015-03-20 | 2015-03-20
2015-08-31 | 2013 | Navy Active | N62863710 |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 5849000 | 6250000 | 2015-03-20 | 2015-03-20
2015-08-31 | 2014 | Navy Active | N62863733 |  | 2014-08-29 | 2014-09-19 | NEWIMAR SA | N3319110D1801 0283 | 1144000 | 888000 | 2014-11-22 | 2014-11-22
2015-08-31 | 2011 | Navy Active | N62863897 |  | 2012-01-13 | 2012-06-15 | SACYR SA | N3319112C0603 AWD | 19080000 | 18712000 | 2014-09-03 | 2016-03-28
2015-08-31 | 2011 | Navy Active | N63005908 |  | 2012-04-12 | 2012-08-17 | NAVY STANDARD DOCUMENT | N6247012MPE0064 | 41151000 | 40173000 | 2016-02-29 | 2016-02-29
2015-08-31 | 2011 | Navy Active | N63005954 |  | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT | N6247012MPE0005 | 40713000 | 40209000 | 2015-10-30 | 2015-10-30
2015-08-31 | 2015 | Navy Active | N63042327 |  | 2015-03-02 | 2015-06-26 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0007 | 21588000 | 21458000 | 2016-10-17 | 2016-10-17
2015-08-31 | 2015 | Navy Active | N63042328 |  | 2015-02-24 | 2015-06-11 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0006 | 17017000 | 15935000 | 2016-07-22 | 2016-07-22
2015-08-31 | 2011 | Navy Active | N63042331 |  | 2011-01-11 | 2011-09-30 | EPC CORPORATION | N6247310D5415 0012 | 2713000 | 2887000 | 2012-10-01 | 2013-05-21
2015-08-31 | 2012 | Navy Active | N63042363 |  | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | N6247312C3410 AWD | 1980000 | 1878000 | 2013-08-29 | 2013-08-29
2015-08-31 | 2012 | Navy Active | N63042364 |  | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | N6247312C3413 AWD | 2000000 | 1897000 | 2013-09-26 | 2014-03-05
2015-08-31 | 2014 | Navy Active | N63042376 |  | 2014-08-27 | 2014-09-27 | COPPERTOP LEDCOR JV | N6247313D4608 0014 | 1839000 | 1661000 | 2016-09-27 | 2017-06-04
2015-08-31 | 2013 | Navy Active | N63043317 |  | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851000 | 9292000 | 2015-10-09 | 2015-10-09
2015-08-31 | 2011 | Navy Active | N63402973 | N68436973F | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | N4425508C6003 PC000094 | 20026000 | 19522000 | 2011-11-08 | 2012-10-29
2015-08-31 | 2012 | Navy Active | N63406563 |  | 2012-06-20 | 2012-09-28 | NOVA R M F | N6247312D0245 0003 | 1939000 | 1875000 | 2013-09-27 | 2014-07-01
2015-08-31 | 2013 | Navy Active | N66691907 |  | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPAQOLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663000 | 13455000 | 2016-05-15 | 2016-05-15
2015-08-31 | 2012 | Navy Active | N68436419 |  | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | N4425510D5019 0002 | 13341000 | 10853000 | 2013-12-24 | 2014-11-10
2015-08-31 | 2014 | Navy Active | N68436420 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179000 | 10403000 | 2016-02-16 | 2016-02-16
2015-08-31 | 2015 | Navy Active | N68436422 |  | 2014-12-01 | 2015-05-04 | TRITON MARINE CONSTRUCTION CORP. | N4425514D9007 0003 | 12592000 | 11013000 | 2016-10-25 | 2016-10-25
2015-08-31 | 2012 | Navy Active | N68436839 |  | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | N4425509D4007 0017 | 1389000 | 1333000 | 2013-08-31 | 2013-11-22
2015-08-31 | 2011 | Navy Active | N68436843 |  | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | N4425510D5006 0005 | 16042000 | 16528000 | 2012-10-15 | 2015-02-16
2015-08-31 | 2014 | Navy Active | N68436855 |  | 2015-01-30 | 2015-06-30 | DOYON MANAGEMENT SERVICES, LLC | N4425515C8000 | 1951000 | 1825000
2015-08-31 | 2013 | Navy Active | N68436857 |  | 2013-01-16 | 2013-05-17 | NOVA GROUP INC | N4425510D5019 0003 | 3406000 | 3122000
2015-08-31 | 2011 | Navy Active | N68436910 |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 14315000 | 14798000 | 2013-06-26 | 2014-08-28
2015-08-31 | 2012 | Navy Active | N68436913 |  | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | N4425512C3007 AWD | 13485000 | 13577000 | 2013-08-08 | 2014-02-16
2015-08-31 | 2012 | Navy Active | N68436985 |  | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | N4425510D5008 0012 | 9338000 | 8948000 | 2013-12-10 | 2014-06-30
2015-08-31 | 2011 | Navy Active | N68436987 |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 11275000 | 10364000 | 2013-06-26 | 2014-08-28
2015-08-31 | 2013 | Navy Active | N68436990 | N68436990A | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 280041000 | 260072000 | 2016-01-09 | 2016-01-11
2015-08-31 | 2014 | Navy Active | N68436990 | N68436990B | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 24880000 | 15491000
2015-08-31 | 2015 | Navy Active | N68436990 | N68436990C | 2011-12-13 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 80735000 | 70746000
2015-08-31 | 2012 | Navy Active | N68436990 |  | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714000 | 77927000 | 2016-01-09 | 2016-01-11
2015-08-31 | 2012 | Navy Active | N68469110 |  | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0019 | 3805000 | 3997000 | 2013-08-28 | 2014-05-30
2015-08-31 | 2014 | Navy Active | N684691400 |  | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | N6247013D6019 JU01 | 48905000 | 48849000 | 2015-01-31 | 2015-01-31
2015-08-31 | 2012 | Navy Active | N68539184 |  | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101000 | 29406000 | 2015-07-30 | 2015-08-26
2015-08-31 | 2011 | Navy Active | N69212202 |  | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | N4008506D6009 0008 | 928000 | 950000 | 2012-01-26 | 2012-04-30
2015-08-31 | 2011 | Navy Active | N69213206 |  | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | N4008510D9451 0005 | 1630000 | 1633000 | 2013-01-25 | 2013-03-29
2015-08-31 | 2013 | Navy Active | N69213237 |  | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | N4008513C3513 AWD | 34005000 | 35164000 | 2014-11-27 | 2015-06-26
2015-08-31 | 2014 | Navy Active | N69232281 |  | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | N6247309D1657 0016 | 6106000 | 5789000 | 2015-07-17 | 2015-07-17
2015-08-31 | 2012 | Navy Active | N69232559 |  | 2012-03-21 | 2012-06-29 | A&D GC INC | N6247309D1658 0012 | 13210000 | 15242000 | 2014-06-25 | 2015-03-20
2015-08-31 | 2014 | Navy Active | N69232593 |  | 2014-04-30 | 2015-01-16 | I E PACIFIC INC | N6247309D1657 0019 | 18400000 | 17409000 | 2016-09-17 | 2016-09-17
2015-08-31 | 2014 | Navy Active | N69232599 |  |  | 2014-11-24 | NAVY STANDARD DOCUMENT | N6247314RP00165 | 33594000 | 30093000 | 2016-03-12 | 2016-03-12
2015-08-31 | 2013 | Navy Active | N69232900 |  | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301000 | 8762000 | 2014-11-21 | 2015-10-18
2015-08-31 | 2014 | Navy Active | N83447136 |  | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19401000 | 18703000 | 2016-02-12 | 2016-03-02
2015-08-31 | 2014 | Navy Reserve | M68479031 |  | 2014-12-12 | 2015-03-24 | ACCEL PACIFIC JV | N4008314D3232 WE01 | 3497000 | 3287000 | 2016-03-23 | 2016-03-23
2015-08-31 | 2011 | Navy Reserve | N00206477 |  | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | N6945011C0756 AWD | 13604000 | 14492000 | 2013-06-07 | 2014-02-12
2015-08-31 | 2012 | Navy Reserve | N32414860 |  | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | N4008312C0005 AWD | 12033000 | 12349000 | 2014-02-06 | 2014-05-31
2015-08-31 | 2012 | Navy Reserve | N69212543 |  | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | N4008511D6588 0006 | 738000 | 747000 | 2014-01-21 | 2014-01-21
2015-08-31 | 2011 | Navy Reserve | N69212743 |  | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008509D5019 0003 | 15431000 | 17547000 | 2013-04-27 | 2014-10-18
2015-08-31 | 2013 | Navy Reserve | N83447047 |  | 2013-01-22 | 2013-09-12 | KOMADA, LLC | N6945013D1767 0001 | 6894000 | 7669000 | 2014-11-06 | 2015-03-30
2015-08-31 | 2015 | Special Operations Command | 36977 |  | 2015-04-15 | 2015-08-20 | Walsh Group Ventures | W912Qr-15-R-0010 | 14851000 | 14851000 | 2017-06-10 | 2017-06-10
2015-08-31 | 2013 | Special Operations Command | 53542 |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546920 | 6546920 | 2016-05-09 | 2016-05-07
2015-08-31 | 2012 | Special Operations Command | 60272 |  | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN-10-D-0049 / 29371639 | 8290317 | 8466000 | 2014-03-06 | 2015-05-29
2015-08-31 | 2012 | Special Operations Command | 60821 |  | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN-10-D-0060 / 29389201 | 10605000 | 10926000 | 2014-06-06 | 2015-07-04
2015-08-31 | 2014 | Special Operations Command | 61064 |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951000 | 13951000 | 2016-05-10 | 2016-10-13
2015-08-31 | 2008 | Special Operations Command | 61772 |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30155148 | 16751000 | 17554951.7 | 2013-04-25 | 2014-12-31
2015-08-31 | 2011 | Special Operations Command | 64484 |  | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | W912HN-11-C-0010 / 29379991 | 13388000 | 15601000 | 2014-06-10 | 2015-10-21
2015-08-31 | 2013 | Special Operations Command | 65052 |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199999 | 3272000 | 2015-08-25 | 2015-04-17
2015-08-31 | 2011 | Special Operations Command | 65395 |  | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391578 | 15637173 | 2013-06-19 | 2014-07-31
2015-08-31 | 2011 | Special Operations Command | 66362 |  | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | W912HN-12-C-0009 / 29381338 | 41446000 | 44329000 | 2014-01-31 | 2015-06-16
2015-08-31 | 2013 | Special Operations Command | 66597 |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384894 | 3384894 | 2015-10-21 | 2015-11-20
2015-08-31 | 2012 | Special Operations Command | 66598 |  | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350000 | 35269000 | 2014-02-15 | 2015-04-29
2015-08-31 | 2014 | Special Operations Command | 68526 |  | 2014-03-26 | 2015-04-09 | Barlovento, LLC | W91278-10-D-0058-DQ01 | 10815034 | 10815034 | 2017-04-07 | 2017-04-07
2015-08-31 | 2013 | Special Operations Command | 69257 |  | 2014-03-11 | 2015-04-01 | Pease Construction, Inc. | W912DW-15-C-0003 | 4484160 | 4484160 | 2016-11-14 | 2016-11-14
2015-08-31 | 2013 | Special Operations Command | 69382 |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816000 | 25843000 | 2015-08-14 | 2015-08-14
2015-08-31 | 2013 | Special Operations Command | 69445 |  | 2013-02-01 | 2015-05-07 | RQ Construction LLC | W912DW-15-C-0006 | 45104000 | 45104000 | 2017-07-23 | 2017-07-23
2015-08-31 | 2014 | Special Operations Command | 69446 |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083965 | 15214000 | 2016-02-18 | 2016-04-20
2015-08-31 | 2013 | Special Operations Command | 69447 |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123180.2 | 22638000 | 2016-02-13 | 2016-05-15
2015-08-31 | 2012 | Special Operations Command | 69458 |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772305 | 16795000 | 2014-06-03 | 2015-08-13
2015-08-31 | 2013 | Special Operations Command | 69493 |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085000 | 23223000 | 2016-05-02 | 2016-09-25
2015-08-31 | 2011 | Special Operations Command | 69573 |  | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN-10-D-0058 / 29381912 | 8487000 | 9166000 | 2013-04-18 | 2013-11-21
2015-08-31 | 2012 | Special Operations Command | 69758 |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 15649974 | 16178000 | 2014-05-08 | 2015-12-28
2015-08-31 | 2012 | Special Operations Command | 71224 | 25 | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41071297 | 4506851.5 | 4506851.5 | 2015-03-01 | 2015-04-27
2015-08-31 | 2012 | Special Operations Command | 71224 |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525847 | 18786000 | 2014-05-01 | 2015-04-27
2015-08-31 | 2012 | Special Operations Command | 76363 |  | 2012-04-18 | 2012-08-30 | Adept-Absher 1 Joint Venture | W912DW-12-C-0037 / 27917342 | 18751000 | 19630000 | 2014-04-01 | 2014-06-21
2015-08-31 | 2012 | Special Operations Command | 76364 |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201303.1 | 33435007.1 | 2014-08-26 | 2015-12-15
2015-08-31 | 2012 | Special Operations Command | 76366 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673727 | 15674302 | 2015-09-12 | 2016-04-26
2015-08-31 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441000 | 36737000 | 2016-06-16 | 2016-10-01
2015-08-31 | 2012 | Special Operations Command | 76371 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092801 | 17144000 | 2015-09-12 | 2016-04-26
2015-08-31 | 2012 | Special Operations Command | 76374 |  | 2011-11-28 | 2012-05-07 | Hensel Phelps Construction Co. | W912QR-12-C-0035 / 28427841 | 32450000 | 34200000 | 2014-03-23 | 2014-08-29
2015-08-31 | 2014 | Special Operations Command | 76375 |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358000 | 27391000 | 2016-07-23 | 2017-01-19
2015-08-31 | 2014 | Special Operations Command | 76376 |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696668.3 | 51696668.3 | 2017-06-27 | 2018-01-15
2015-08-31 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | Nishimatsu Construction Co., Ltd. | W912HV-15-C-0004 | 46556000 | 46556000 | 2018-05-05 | 2018-05-05
2015-08-31 | 2014 | Special Operations Command | 79438 |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193631 | 7230000 | 2016-04-19 | 2016-09-16
2015-08-31 | 2014 | Special Operations Command | 79440 |  |  | 2015-04-30 | Blueforge, LLC | N69450-14-D-1271 | 3695800 | 3695800 | 2016-08-22 | 2016-08-22
2015-08-31 | 2015 | Special Operations Command | 79456 |  | 2015-05-21 | 2015-08-31 | Lifecycle Construction Services, LLC | W912HN-13-D-0002-DQ01 | 5798000 | 5798000 |  | 2017-09-27
2015-08-31 | 2013 | Special Operations Command | 79655 |  | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | W912PM-13-C-0003 | 1592000 | 1608000 | 2014-10-15 | 2014-08-21
2015-08-31 | 2013 | Special Operations Command | 80233 |  | 2013-06-16 | 2014-01-22 | Trend Construction, Inc. | W912HN-12-D-0030-DQ04 | 1531765.3 | 1570000 | 2015-05-15 | 2015-03-04
2015-08-31 | 2013 | Special Operations Command | 81483 |  | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F-13-C-0006 | 1513000 | 1643000 | 2014-10-15 | 2015-01-25
2015-08-31 | 2013 | Special Operations Command | 69287a |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907435 | 31092000 | 2015-05-13 | 2015-12-24
2015-08-31 | 2013 | Special Operations Command | 69287b |  | 2014-05-14 | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404000 | 23709000 | 2016-11-01 | 2016-11-01
2015-08-31 | 2008 | Special Operations Command | AFSOC033003 |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30136034 | 4575000 | 5123284.5 | 2013-04-25 | 2015-03-05
2015-08-31 | 2008 | Special Operations Command | AFSOC033005 |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154837 | 3603000 | 3766211.6 | 2013-04-25 | 2014-12-31
2015-08-31 | 2008 | Special Operations Command | AFSOC033019 |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154494 | 2931000 | 3078566.6 | 2013-04-25 | 2014-12-31
2015-08-31 | 2011 | Special Operations Command | CZQZ063049 |  | 2011-05-13 | 2011-09-09 | Speegle Construction | W912PP-11-C-0029 / 30594756 | 19432000 | 20310963.7 | 2013-12-01 | 2014-05-02
2015-08-31 | 2011 | Special Operations Command | CZQZ063052A |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13613730 | 13829042.1 | 2013-07-17 | 2014-06-03
2015-08-31 | 2012 | Special Operations Command | CZQZ073014 |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 25127091 | 7413000 | 7874824.1 | 2014-02-22 | 2014-07-11
2015-08-31 | 2012 | Special Operations Command | CZQZ073018 |  | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | W912PP-12-C-0025 / 30667913 | 9329000 | 9703739.4 | 2014-04-10 | 2014-08-29
2015-08-31 | 2012 | Special Operations Command | CZQZ073021 |  | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | W912PP-12-C-0033 / 25138433 | 14700000 | 14966268.4 | 2014-12-22 | 2014-09-19
2015-08-31 | 2012 | Special Operations Command | CZQZ083012A |  | 2012-04-20 | 2012-08-31 | Hensel Phelps | W912PP-12-C-0027 / 30858121 | 28160000 | 29105547 | 2014-12-23 | 2014-09-07
2015-08-31 | 2013 | Special Operations Command | CZQZ083013 |  | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP-14-C-0014 / 32077093 | 19481987.7 | 19871000 | 2015-08-13 | 2015-11-22
2015-08-31 | 2012 | Special Operations Command | CZQZ083016 |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 28791332 | 10615000 | 11040000 | 2015-01-06 | 2014-05-30
2015-08-31 | 2013 | Special Operations Command | CZQZ100221 |  | 2014-03-06 | 2014-07-01 | Speegle Construction | W912PP-14-C-0017 / 39136021 | 1547000 | 1572000 | 2015-05-24 | 2015-08-21
2015-08-31 | 2014 | Special Operations Command | FTEV083002 |  | 2014-05-26 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048867 | 7231000 | 2016-05-24 | 2016-10-20
2015-08-31 | 2012 | Special Operations Command | FTEV103011 |  | 2012-05-01 | 2012-08-09 | Barlovento LLC. | W91278-10-D-0072 | 5551000 | 5543000 | 2013-12-24 | 2014-07-18
2015-08-31 | 2013 | Special Operations Command | FTFA113004 |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942300 | 30121000 | 2016-12-01 | 2017-05-14
2015-08-31 | 2013 | Special Operations Command | NVZR083702 |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753024.6 | 25259000 | 2015-09-15 | 2016-01-07
2015-08-31 | 2012 | Special Operations Command | P-1049 |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129000 | 8767000 | 2014-11-13 | 2015-11-13
2015-08-31 | 2012 | Special Operations Command | P-1174 |  | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | N6247311D0068 #0003 | 3075000 | 3304000 | 2014-03-23 | 2014-11-14
2015-08-31 | 2013 | Special Operations Command | P-1218 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370000 | 46506000 | 2016-03-01 | 2016-01-23
2015-08-31 | 2014 | Special Operations Command | P-1391 |  | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333 #0004 | 27546924 | 27546924 | 2016-09-02 | 2016-09-02
2015-08-31 | 2013 | Special Operations Command | P-1393 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370000 | 46506000 | 2016-01-18 | 2016-01-23
2015-08-31 | 2015 | Special Operations Command | P-1396 |  | 2015-05-29 | 2015-08-17 | The Whiting-Turner Contracting Company | N40085-10-D-5330-0012 | 9129000 | 9129000 | 2017-03-09 | 2017-03-09
2015-08-31 | 2013 | Special Operations Command | P-1410 |  | 2013-09-04 | 2013-09-26 | Quadrant Construction, Inc | N4008510D0261 #0017 | 1566000 | 1612000 | 2014-09-22 | 2015-06-30
2015-08-31 | 2013 | Special Operations Command | P-1450 |  | 2013-12-20 | 2014-02-13 | Quadrant Construction, Inc | N4008510D0261 #0019 | 1459250 | 1516000 | 2014-12-13 | 2015-07-17
2015-08-31 | 2014 | Special Operations Command | P-1469 |  | 2014-08-20 | 2014-09-30 | Quadrant Construction, Inc | N4008510D0261/0022 | 2426000 | 2430000 | 2015-09-25 | 2015-11-24
2015-08-31 | 2012 | Special Operations Command | P-164 |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727000 | 18855000 | 2014-07-24 | 2015-06-16
2015-08-31 | 2013 | Special Operations Command | P-165 |  | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351000 | 10272000 | 2015-09-09 | 2015-11-26
2015-08-31 | 2015 | Special Operations Command | P-418 |  |  | 2015-08-18 | Harper Construction Company, Inc | N6247310D5406 #0006 | 18107000 | 18107000 | 2017-02-23 | 2017-02-23
2015-08-31 | 2012 | Special Operations Command | P-473 |  | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366000 | 27585000 | 2015-12-27 | 2015-12-27
2015-08-31 | 2012 | Special Operations Command | P-504 |  | 2013-03-12 | 2013-05-23 | Richard Brady & Associates, Inc. | N4008511D6591 #0010 | 1660000 | 1730000 | 2014-10-20 | 2015-01-15
2015-08-31 | 2012 | Special Operations Command | P-531 |  | 2012-04-30 | 2012-09-27 | Alutiiq Diversified Service, LLC | N4425512C3011 | 17449000 | 17449000 | 2015-04-15 | 2015-04-15
2015-08-31 | 2013 | Special Operations Command | P-564 |  | 2013-06-14 | 2013-09-27 | Royce Homeland JV, LLC | N4008512D6305 #0005 | 1308000 | 1383000 | 2014-12-31 | 2015-02-12
2015-08-31 | 2012 | Special Operations Command | P-769 |  | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022000 | 4067000 | 2014-06-27 | 2015-02-20
2015-08-31 | 2012 | Special Operations Command | P-826 |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139000 | 18855000 | 2014-07-24 | 2015-06-16
2015-08-31 | 2013 | Special Operations Command | P-876 |  |  | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290000 | 24440000 | 2016-10-01 | 2016-10-07
2015-08-31 | 2013 | Special Operations Command | P-888 |  |  | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489000 | 15440000 | 2016-09-30 | 2016-09-29
2015-08-31 | 2012 | Special Operations Command | TMKH043055 |  | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN-10-D-0063 / 25189640 | 4773799 | 4752737.4 | 2013-11-22 | 2014-11-12
2015-08-20 | 2010 | Washington Headquarters Services | 80001 |  | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power | HQ0034-13-C-0133 | 23269000 | 23912000 | 2015-02-05 | 2015-06-01
2015-08-20 | 2011 | Washington Headquarters Services | 80002 |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. | HQ0034-13-C-0062 | 43594000 | 45583775 | 2016-05-11 | 2016-07-30
2015-08-20 | 2011 | Washington Headquarters Services | 80003 |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. | W912DR-11-R-0060 | 5609000 | 6267000 | 2015-05-03 | 2015-05-03
2015-08-20 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC | W912DR-11-R-0062 | 5454000 | 5856000 | 2015-05-01 | 2015-10-01
2015-08-20 | 2012 | Washington Headquarters Services | 80005
2015-08-20 | 2012 | Washington Headquarters Services | 80006
2015-08-20 | 2014 | Washington Headquarters Services | 80007
2015-08-20 | 2014 | Washington Headquarters Services | 80008
2015-08-20 | 2014 | Washington Headquarters Services | 80009
2015-08-20 | 2014 | Washington Headquarters Services | 80010
2015-08-20 | 2015 | Washington Headquarters Services | 80011

## EXPENDITURES
Expenditure Data as of Date | Appropriation Fiscal Year | Project Sponsor Component Name | Appropriation Fund Type Name | Use of Funds | Aggregated Appropriated Amount | Aggregated Current Obligated Amount | Aggregated Current Expenditure Amount | Expenditure Remarks
2015-09-08 | 2006 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773860 | 281664955.24 | 281661594.32
2015-09-08 | 2006 | Air Force Active | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for GWOT Projects. | 63753948 | 57588280.05 | 57505133.04
2015-09-08 | 2006 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782960 | 26582678.6 | 26416375.03
2015-09-08 | 2006 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15769710 | 15283071.55 | 15073877.43
2015-09-08 | 2007 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232000 | 329301187.46 | 329290069.46
2015-09-08 | 2007 | Air Force Active | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for GWOT Projects. | 74021000 | 72886116.11 | 72116518.09
2015-09-08 | 2007 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064000 | 12889092.98 | 12691571
2015-09-08 | 2007 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000000 | 14163277.68 | 14163277.68
2015-09-08 | 2008 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 294262000 | 238661134.82 | 236102694.61
2015-09-08 | 2008 | Air Force Active | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for GWOT Projects. | 30148000 | 29576067.29 | 29329943.19
2015-09-08 | 2008 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210000 | 12161823.02 | 12161823.02
2015-09-08 | 2008 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000000 | 14081477.5 | 13525720.75
2015-09-08 | 2009 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513728 | 207210298.23 | 188661907.35
2015-09-08 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing. Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - | 609075 | 608958 | 608958
2015-09-08 | 2009 | Air Force Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105506000 | 103688595.89 | 102607616.55
2015-09-08 | 2009 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703000 | 7559999.58 | 7524947.8
2015-09-08 | 2009 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000000 | 14851799.04 | 14809361
2015-09-08 | 2010 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558000 | 59491556.55 | 59488561.81
2015-09-08 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 529950 | 510499 | 508572
2015-09-08 | 2010 | Air Force Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 87562000 | 87115702.21 | 85404622.03
2015-09-08 | 2010 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302000 | 1440578.32 | 1396578.32
2015-09-08 | 2010 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 20000000 | 19887857.27 | 19887857.27
2015-09-08 | 2011 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192950 | 55109438.22 | 53079800.63
2015-09-08 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 544424 | 514017 | 512601
2015-09-08 | 2011 | Air Force Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations; Design for OCO Projects | 63903328 | 63185595.52 | 59540366.96
2015-09-08 | 2011 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153000 | 3921567.97 | 3921567.97
2015-09-08 | 2011 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 17964000 | 17428514.61 | 17019730.06
2015-09-08 | 2012 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407000 | 22219236.83 | 21108236.25
2015-09-08 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 448450 | 434099 | 428829
2015-09-08 | 2012 | Air Force Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 78413000 | 77292813.83 | 72367714.89
2015-09-08 | 2012 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056000 | 4031298.21 | 4031298.21
2015-09-08 | 2012 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000000 | 19490392.32 | 16480010.49
2015-09-08 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936577 | 2620825.11 | 2149390.06
2015-09-08 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 468478 | 444703 | 410246
2015-09-08 | 2013 | Air Force Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 410408 | 374528.78 | 162544.15
2015-09-08 | 2013 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3951846 | 0 | 0
2015-09-08 | 2013 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 18175981 | 4060910.19 | 2333230.37
2015-09-08 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093000 | 40817398.3 | 5908901.3
2015-09-08 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 399595 | 313955 | 208277
2015-09-08 | 2014 | Air Force Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314000 | 10505258.38 | 9400832.23
2015-09-08 | 2014 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267000 | 0 | 0
2015-09-08 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448000 | 1693166.35 | 128158.69
2015-09-08 | 2015 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 352062 | 59493 | 1182
2015-09-08 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 10738000 | 7346345.95 | 2040694.01
2015-09-08 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22613000 | 0 | 0
2015-09-08 | 2006 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289570 | 5289120.12 | 5289120.12
2015-09-08 | 2006 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960000 | 3959999.57 | 3959999.57
2015-09-08 | 2007 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109000 | 5072462.94 | 5072462.94
2015-09-08 | 2007 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477000 | 4476971.58 | 4476971.58
2015-09-08 | 2008 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300000 | 5270797.76 | 5270797.76
2015-09-08 | 2008 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909000 | 4909000 | 4909000
2015-09-08 | 2009 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165000 | 6133583.38 | 6123256.47
2015-09-08 | 2009 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443000 | 5442927 | 5442927
2015-09-08 | 2010 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139000 | 8001719.25 | 5558647.04
2015-09-08 | 2010 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 800000 | 752889.81 | 752889.81
2015-09-08 | 2011 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649694 | 1521061.04 | 1521061.04
2015-09-08 | 2011 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2753482 | 2728949.37 | 2651597.22
2015-09-08 | 2012 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200000 | 2115219.77 | 2063355.89
2015-09-08 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5434000 | 4216309.59 | 3652628.23
2015-09-08 | 2013 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875201 | 2276981.81 | 1825736.87
2015-09-08 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997361 | 355600.04 | 35256.47
2015-09-08 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229000 | 1732941.2 | 274478.33
2015-09-08 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530000 | 0 | 0
2015-09-08 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892000 | 638161.42 | 10138.65
2015-09-08 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400000 | 0 | 0
2015-09-08 | 2006 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006000 | 28018596.99 | 28018596.99
2015-09-08 | 2006 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882000 | 6882000 | 6882000
2015-09-08 | 2007 | Air National Guard | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050000 | 19043340 | 19043339.39
2015-09-08 | 2007 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000000 | 5999999.88 | 5999999.88
2015-09-08 | 2008 | Air National Guard | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721000 | 10619035.33 | 10619035.33
2015-09-08 | 2008 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184000 | 14184000 | 14184000
2015-09-08 | 2009 | Air National Guard | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056000 | 19040835.96 | 18984459.95
2015-09-08 | 2009 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243000 | 34243000 | 34227813.75
2015-09-08 | 2010 | Air National Guard | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670441 | 19574210.93 | 19450189.65
2015-09-08 | 2010 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913559 | 44907226.19 | 42574403.4
2015-09-08 | 2011 | Air National Guard | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195572 | 8702932.15 | 8661046.09
2015-09-08 | 2011 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984000 | 7947051.52 | 7108494.38
2015-09-08 | 2012 | Air National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225000 | 11951767.02 | 11658816.13
2015-09-08 | 2012 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000000 | 8950494.19 | 5356803.27
2015-09-08 | 2013 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994721 | 3806510.19 | 3482701.36
2015-09-08 | 2013 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892214 | 4518058.37 | 2783916.72
2015-09-08 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400000 | 7598585.8 | 2783568.1
2015-09-08 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000000 | 9457661.37 | 1799030.77
2015-09-08 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700000 | 123612.26 | 0
2015-09-08 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6100000 | 2297361.41 | 0
2015-09-10 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000000 | 24000000 | 24000000
2015-09-10 | 2009 | Army Active | Leased Military Family Housing - Operations and Maintenance | Army Family Housing O&M | 21855000 | 21855000 | 21855000
2015-09-10 | 2009 | Army Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766000 | 220214000 | 219390000
2015-09-10 | 2009 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 576000 | 576000 | 524000
2015-09-10 | 2009 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 28750000 | 28394000 | 26129000
2015-09-10 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000000 | 25000000 | 25000000
2015-09-10 | 2010 | Army Active | Leased Military Family Housing - Operations and Maintenance | Army Family Housing O&M | 28393000 | 28392000 | 28387000
2015-09-10 | 2010 | Army Active | Overseas Contingency Operations | Unspecified Minor Construction for Projects < $2.M | 60100000 | 15687000 | 15686000
2015-09-10 | 2010 | Army Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499000 | 250432000 | 248403000
2015-09-10 | 2010 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 3936000 | 3935000 | 2503000
2015-09-10 | 2010 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 31250000 | 31246000 | 30375000
2015-09-10 | 2011 | Army Active | Host Nation Support | $29,944 Appropriated + $13,000 ATR Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 42944000 | 42933000 | 42905000
2015-09-10 | 2011 | Army Active | Leased Military Family Housing - Operations and Maintenance | Army Family Housing O&M | 37328000 | 37317000 | 37311000
2015-09-10 | 2011 | Army Active | Overseas Contingency Operations | Unspecified Minor Construction for Projects < $2.M | 78330000 | 1274000 | 1274000
2015-09-10 | 2011 | Army Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 308676000 | 263063000 | 258277000
2015-09-10 | 2011 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2036000 | 2002000 | 1367000
2015-09-10 | 2011 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 28704000 | 28699000 | 28680000
2015-09-10 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR + $9,000 ATR | 36000000 | 35940000 | 35314000
2015-09-10 | 2012 | Army Active | Leased Military Family Housing - Operations and Maintenance | Army Family Housing O&M | 34282000 | 34262000 | 34262000
2015-09-10 | 2012 | Army Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741000 | 214843000 | 197869000
2015-09-10 | 2012 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7897000 | 7737000 | 7328000
2015-09-10 | 2012 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 20000000 | 19685000 | 19394000
2015-09-10 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954000 | 33862000 | 33620000
2015-09-10 | 2013 | Army Active | Leased Military Family Housing - Operations and Maintenance | Army Family Housing O&M | 28086000 | 27897000 | 27858000
2015-09-10 | 2013 | Army Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46112000 | 45814000 | 43624000
2015-09-10 | 2013 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4635000 | 4436000 | 1800000
2015-09-10 | 2013 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 23720000 | 20190000
2015-09-10 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000000 | 22924000 | 22135000
2015-09-10 | 2014 | Army Active | Leased Military Family Housing - Operations and Maintenance | Army Family Housing O&M | 20228000 | 19788000 | 18859000
2015-09-10 | 2014 | Army Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575000 | 39247000 | 36229000
2015-09-10 | 2014 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4408000 | 842000 | 519000
2015-09-10 | 2014 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 22365000 | 12740000
2015-09-10 | 2015 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33000000 | 16581000 | 15223000
2015-09-10 | 2015 | Army Active | Leased Military Family Housing - Operations and Maintenance | Army Family Housing O&M | 7000000 | 6963000 | 4251000
2015-09-10 | 2015 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 18127000 | 13817000 | 12700000
2015-09-10 | 2015 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 1309000 | 0 | 0
2015-09-10 | 2015 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 2863000 | 116000
2015-08-31 | 2011 | Army National Guard | Planning and Design - Military Construction | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25604000 | 25592000 | 25592000 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2011 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14215000 | 14215000 | 14215000 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191000 | 19738000 | 19738000 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14149000 | 11562000 | 11562000 | PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17; Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 28155000 | 7039000 | 7039000 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013); PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14562000 | 14562000 | 14562000 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-08-31 | 2014 | Army National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930000 | 2671000 | 2671000 | PL 113-76 P&D Recission
2015-08-31 | 2014 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 12240000 | 3390000 | 3390000
2015-08-31 | 2015 | Army National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 17600000 | 6652000 | 6652000
2015-08-31 | 2015 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 13720000 | 1873000 | 1873000
2015-08-31 | 2012 | Defense Finance and Accounting Service | Planning and Design - Military Construction | Investigation and Design | 1992000 | 748000 | 709000
2015-08-31 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction | Construction | 15404000 | 14350000 | 7761000
2015-08-31 | 2009 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 171255000 | 170635000 | 166266000
2015-08-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 3979000 | 3979000 | 3979000
2015-08-31 | 2010 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 72679000 | 72465000 | 69380000
2015-08-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5547000 | 3984000 | 3984000
2015-08-31 | 2011 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 193126000 | 161964000 | 119199000
2015-08-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4673000 | 2736000 | 2711000
2015-08-31 | 2012 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 209957000 | 6012000 | 5215000
2015-08-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5930000 | 4737000 | 4719000
2015-08-31 | 2013 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 97411000 | 0 | 0
2015-08-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4608000 | 3435000 | 2491000
2015-08-31 | 2014 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 244000 | 0 | 0
2015-08-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 9578000 | 1002000 | 178000
2015-08-31 | 2015 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 105000 | 0 | 0
2015-08-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4100000 | 0 | 0
2015-08-31 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 79739000 | 62283000 | 19486000 | DISA Europe Facility Upgrades ($2,224); Construct New DISA Facility Scott AFB ($77,515)
2015-08-31 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2616000 |  |  | DISA Pacific Facility Upgrade
2015-08-31 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction |  | 12216000 |  |  | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) ($9,600); JITC Building 52120 Renovation ($1,871); P&D for design of JITC Buildings 52101, 52110, 52111 ($745K)
2015-08-31 | 2010 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for K-16 FOB-K renovation of two buildings to include Administrative and SCIF Spaces | 442000 | 0 | 442000 | Planning and Design MIPR sent to U.S. Army Engineer District, Far East for K-16 Design. MIPR has been fully executed.
2015-08-31 | 2012 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for DIAC Parking Garage Replacement; P&D for DIAC Chilled Water Project for Data Center ($125K) and P&D for DIAC Cooling Tower for Data Center ($105K); P&D for UPS for Data Center Installation; P&D for Construction of JUIAF RDF | 3260000 | 95000 | 2820000 | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $416K (CORRECTED AMOUNT) obligated as CAT I. Contract awarded on 23 September 2014.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 100% design completed.; Design complete.
2015-08-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of projects from 2012 to 2016 | 36093000 | 35907000 | 35907000
2015-08-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 4864000 | 4501000 | 4501000
2015-08-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34238000 | 34238000
2015-08-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2014 | 6312000 | 6312000 | 6312000
2015-08-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 27227000 | 27227000
2015-08-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2266000 | 2266000
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2015 to 2018 | 6978000 | 0 | 0
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2013 to 2016 | 7430000 | 0 | 0
2015-08-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction |  | 0 | 0 | 0
2015-08-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2015 to 2019 | 5932000 | 0 | 0
2015-09-03 | 2008 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI andFY 08/09/ 10/11/12 MILCON projects | 5159000 | 5159000 | 5158000 | RCI-Residential Communities Initiative
2015-09-03 | 2009 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13617000 | 13617000 | 12654000
2015-09-03 | 2009 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5000 | 4000 | 4000 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2015-09-03 | 2010 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 10/11/ 12/13 MILCON projects | 8829000 | 8755000 | 8722000 | Reflects Sequestration Reduction
2015-09-03 | 2011 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 11/12/ 13 MILCON projects | 78666000 | 76201000 | 65400000 | Reflects Sequestration Reduction
2015-09-03 | 2012 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 12/13 MILCON projects | 64551000 | 64128000 | 48361000 | Reflects Sequestration Reduction
2015-09-03 | 2013 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 13/14/15/16 MILCON projects | 97290000 | 95380000 | 52361000 | Reflects Sequestration Reduction
2015-09-03 | 2013 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3771000 | 7000 | 3764000 | Reflects Sequestration Reduction
2015-09-03 | 2014 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 14/15/16/17 MILCON projects | 75905000 | 12115000 | 56000
2015-09-03 | 2014 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5409000 | 0 | 0
2015-09-03 | 2015 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42387000 | 0 | 0
2015-09-03 | 2015 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 6846000 | 0 | 0
2015-08-31 | 2011 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 11087000 | 10801000 | 10771000
2015-08-31 | 2011 | Marine Corps Active | Planning and Design - Military Construction | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 853000 | 853000 | 850000
2015-08-31 | 2012 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 25327000 | 23639000 | 23639000
2015-08-31 | 2012 | Marine Corps Active | Planning and Design - Military Construction | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719000 | 719000 | 719000
2015-08-31 | 2013 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 17441000 | 16715000 | 6521000
2015-08-31 | 2013 | Marine Corps Active | Planning and Design - Military Construction | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455000 | 445000 | 434000
2015-08-31 | 2014 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 24253000 | 15632000 | 2693000
2015-08-31 | 2014 | Marine Corps Active | Planning and Design - Military Construction | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463000 | 462000 | 292000
2015-08-31 | 2015 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 15940000 | 0 | 0
2015-08-31 | 2015 | Marine Corps Active | Planning and Design - Military Construction | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 472000 | 75000 | 0
2015-08-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY13/14 | 2243000 | 2037000 | 1793000 | Supports the R&C Piping project at Fort Greely, AK and the Storage Facility, Meck Island. $1.186M transferred to DHA in April 2014 for swap of FY11 P&D funds. $205K returned to OSD in Sep 2014.
2015-08-31 | 2011 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY15-16 MILCON Projects | 1186000 | 1186000 | 1186000 | Funds tranferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2015-08-31 | 2012 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY13-14 MILCON Projects | 8368000 | 8368000 | 8124000 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2015-08-31 | 2013 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY13-14 MILCON Projects | 4191000 | 4191000 | 4062000 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2015-08-31 | 2014 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY14-16 MILCON Projects | 10891000 | 10891000 | 9820000 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2015-08-31 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000000 | 155000 | 23000 | Supports the Storage Facility, Meck Island project.
2015-08-31 | 2015 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY16-17 MILCON Projects | 58704000 | 17871000 | 4266000 | Supports design of the Aegis Ashore Poland site, Long Range Discrimination Radar System Complex, Clear AFS, AK, and IDT Switchgear Bldg, Fort Greely, AK.
2015-08-31 | 2015 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY15/16 | 2000000 | 0 | 0
2015-08-31 | 2011 | National Security Agency | Planning and Design - Military Construction | General P&D | 28094000 | 28094000 | 28094000
2015-08-31 | 2012 | National Security Agency | Planning and Design - Military Construction | High Performance Computing Center 2 | 11000000 | 10967230 | 5516930.8
2015-08-31 | 2012 | National Security Agency | Planning and Design - Military Construction | General P&D | 17483000 | 17478773.16 | 15627692.69
2015-08-31 | 2013 | National Security Agency | Planning and Design - Military Construction | General P&D | 7649000 | 7649000 | 1452636.34
2015-08-31 | 2014 | National Security Agency | Planning and Design - Military Construction | General P&D | 39400000 | 21173047.4 | 1074541.73
2015-08-31 | 2015 | National Security Agency | Planning and Design - Military Construction | General P&D | 599000 | 0 | 0
2015-08-31 | 2011 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 27773000 | 27603000 | 26139000
2015-08-31 | 2011 | Navy Active | Planning and Design - Military Construction | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 2340000 | 2340000 | 2229000
2015-08-31 | 2011 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 136314000 | 136216000 | 131181000 | [Component: Navy-MC Active]
2015-08-31 | 2011 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 20757000 | 20070000 | 18981000 | [Component: Navy-MC Active]
2015-08-31 | 2012 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 68661000 | 59245000 | 47623000
2015-08-31 | 2012 | Navy Active | Planning and Design - Military Construction | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2447000 | 2438000 | 2398000
2015-08-31 | 2012 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 83943000 | 83841000 | 81218000 | [Component: Navy-MC Active]
2015-08-31 | 2012 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 20919000 | 19806000 | 18510000 | [Component: Navy-MC Active]
2015-08-31 | 2013 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 42739000 | 34298000 | 23362000
2015-08-31 | 2013 | Navy Active | Planning and Design - Military Construction | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609000 | 1485000 | 929000
2015-08-31 | 2013 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 96888000 | 96582000 | 80108000 | [Component: Navy-MC Active]
2015-08-31 | 2013 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 15612000 | 13944000 | 10223000 | [Component: Navy-MC Active]
2015-08-31 | 2014 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 44716000 | 41298000 | 3269000
2015-08-31 | 2014 | Navy Active | Planning and Design - Military Construction | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975000 | 0 | 0
2015-08-31 | 2014 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638000 | 74843000 | 51597000 | [Component: Navy-MC Active]
2015-08-31 | 2014 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 19740000 | 18336000 | 6262000 | [Component: Navy-MC Active]
2015-08-31 | 2015 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
2015-08-31 | 2015 | Navy Active | Planning and Design - Military Construction | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0
2015-08-31 | 2015 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 33366000 | 25835000 | 24123000 | [Component: Navy-MC Active]
2015-08-31 | 2015 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 3582000 | 881000 | 0 | [Component: Navy-MC Active]
2015-08-31 | 2011 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1854000 | 1854000 | 1854000 | [Component: Navy-MC Reserve]
2015-08-31 | 2011 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 2194000 | 1662000 | 1548000 | [Component: Navy-MC Reserve]
2015-08-31 | 2012 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478000 | 2324000 | 2237000 | [Component: Navy-MC Reserve]
2015-08-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 1947000 | 1280000 | 1171000 | [Component: Navy-MC Reserve]
2015-08-31 | 2013 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995000 | 1994000 | 1991000 | [Component: Navy-MC Reserve]
2015-08-31 | 2013 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2015-08-31 | 2014 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2556000 | 2192000 | 2191000 | [Component: Navy-MC Reserve]
2015-08-31 | 2014 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2015-08-31 | 2015 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 2123000 | 0 | 0 | [Component: Navy-MC Reserve]
2015-08-31 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 4000000 | 27000 | 0 | [Component: Navy-MC Reserve]
2015-08-31 | 2011 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 26469000 | 26448000
2015-08-31 | 2011 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 7531000 | 7526000
2015-08-31 | 2012 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 30308000 | 28919000
2015-08-31 | 2012 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 8487000 | 8069000
2015-08-31 | 2013 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 25454000 | 17166000
2015-08-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 9216000 | 8946000
2015-08-31 | 2014 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 36866000 | 24104000
2015-08-31 | 2014 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5170000 | 2833000
2015-08-31 | 2015 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 24197000 | 0
2015-08-31 | 2015 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 10334000 | 0
2015-08-20 | 2011 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 2285000 | 2026548 | 1157423 | Sequester taken. Includes ECIP. Revised to deduct the $3,782K realigned and obligated on Pentagon Electrical Upgrade construction since it is no longer P&D
2015-08-20 | 2012 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4870000 | 3782531 | 1987270 | Sequester taken.
2015-08-20 | 2013 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 7508000 | 1942748 | 553207 | Sequester and recissions taken. Includes ECIP
2015-08-20 | 2014 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 6931000 | 0 | 0
2015-08-20 | 2015 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 1183000 | 0 | 0