## PROJECTS
Project Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Construction Project Type Name | State Name | Country Name | Project Number | Project Title | Sub-Project Number | Diverted Funds Total Amount | Diverted Funds Recipient Text | Construction Start Date | Original Construction Completion Date | Current Construction Completion Date | Construction Percent Complete | Current RPA Placed-In-Service Date
2022-07-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | California | United States | ACJP183018 | RELOCATE MAIN GATE ENTRY CONTROL POINT |  |  |  | 2021-08-30 | 2022-11-13 | 2022-11-13 | 2% | 2022-11-13
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Kuwait | AEWV171012 | Dining Facility Addition |  |  |  | 2019-03-27 | 2022-05-20 | 2022-05-20 | 100% | 2022-05-20
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN053009 | FIRE RESCUE CENTER |  |  |  | 2020-06-09 | 2020-05-14 | 2023-03-30 | 56% | 2023-03-30
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN123003 | DORMITORY (120 RM) |  |  |  | 2019-11-06 | 2020-12-01 | 2022-06-15 | 100% | 2022-06-15
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN173001 | KC-46A FTU FTC SIMULATOR FACILITY PHASE 2 |  |  |  | 2017-09-07 | 2019-03-07 | 2022-09-19 | 100% | 2022-09-19
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN213001 | KC-46A FTU Fuselage Trainer Phase 3 |  |  |  | 2018-04-29 | 2021-02-04 | 2022-02-24 | 100% | 2022-03-07
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Guam | AJJY073105P2 | APR - Munitions Storage Igloos, Phase 2 |  |  |  | 2022-01-06 | 2023-11-22 | 2023-11-22 | 1% | 2023-11-22
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Guam | AJJY073105P3 | APSI - MUNITIONS STORAGE IGLOOS PHASE 3 |  |  |  | 2020-10-16 | 2023-06-16 | 2023-06-16 | 68% | 2023-06-16
2022-07-31 | 2022 | Air Force Active | Major Military Construction |  | Guam | AJJY073105P4 | PDI: MUNITIONS STORAGE IGLOOS IV |  |  |  | 2022-06-30 | 2024-04-15 | 2024-04-30 | 1% | 2024-04-30
2022-07-31 | 2013 | Air Force Active | Major Military Construction |  | Guam | AJJY123010 | GUAM STRIKE FUEL SYSTEMS MAINTENANCE HANGAR |  |  |  | 2015-03-18 | 2017-11-21 | 2022-11-30 | 99% | 2022-05-11
2022-07-31 | 2014 | Air Force Active | Major Military Construction |  | Guam | AJJY133027 | PAR - TANKER GP MAINT HANGAR/AMU/SQD OPS |  |  |  | 2015-01-08 | 2017-01-30 | 2022-11-30 | 99% | 2022-05-11
2022-07-31 | 2015 | Air Force Active | Major Military Construction |  | Guam | AJJY133028 | PAR Low Observable/Corrosion Control/Composite Repair Shop |  |  |  | 2016-11-18 | 2018-09-20 | 2023-03-03 | 82% | 2023-03-03
2022-07-31 | 2022 | Air Force Active | Major Military Construction |  | Guam | AJJY163000 | PDI: AIRFIELD DAMAGE REPAIR WAREHOUSE |  |  |  | 2022-05-30 | 2023-11-06 | 2023-11-06 | 1% | 2023-11-06
2022-07-31 | 2019 | Air Force Active | Major Military Construction |  | Guam | AJJY183003 | 3 HAYMAN MUNITIONS STORAGE IGLOOS, MSA 2 |  |  |  | 2022-06-16 | 2024-01-29 | 2024-01-29 | 1% | 2024-01-29
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction |  | Guam | AJJY183017 | CONSOLIDATED CONTINGENCY CENTER |  |  |  | 2020-10-07 | 2022-06-25 | 2022-08-30 | 99% | 2022-06-25
2022-07-31 | 2021 | Air Force Active | Major Military Construction |  | Guam | AJJY203001 | STAND OFF WEAPONS COMPLEX, MSA 2 |  |  |  | 2021-04-04 | 2023-10-23 | 2023-11-17 | 33% | 2023-11-17
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Maryland | United States | AJXF093000 | CONSTRUCT 21 POINT ENCLOSED FIRING RANGE |  |  |  | 2018-09-12 | 2021-05-31 | 2022-07-12 | 100% | 2022-07-12
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Maryland | United States | AJXF133003 | CONSOLIDATED COMMUNICATIONS CENTER AJXF133003 |  |  |  | 2021-06-01 | 2026-02-23 | 2026-02-23 | 9% | 2026-02-23
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Maryland | United States | AJXF156000 | Vehicle Operations Facility |  |  |  | 2015-12-03 | 2023-07-11 | 2023-07-11 | 100% | 2023-07-11
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Maryland | United States | AJXF173021 | PRESIDENTIAL AIRCRAFT RECAPITALIZATION COMPLEX |  |  |  | 2018-08-19 | 2022-05-30 | 2022-08-30 | 95% | 2022-08-30
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Maryland | United States | AJXF173030 | SECOND TAXIWAY ACCESS HANGAR 20 - WHISKEY 6 |  |  |  | 2020-09-23 | 2022-02-27 | 2022-08-30 | 98% | 2022-08-30
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Qatar | ALUA113023 | Consolidated Squadron Operations Facility |  |  |  | 2019-10-28 | 2022-01-27 | 2022-01-27 | 100% | 2022-01-27
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Italy | ASHE143008 | GUARDIAN ANGEL OPERATIONS FACILITY |  |  |  | 2020-05-25 | 2021-07-26 | 2022-08-23 | 45% | 2022-08-23
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | ASPR150126 | ADD AIRFIELD SECURITY FENCE, FACILITY 779 |  |  |  | 2020-12-28 | 2022-01-20 | 2022-01-20 | 100% | 2022-01-20
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF164000 | DINING FACILITY |  |  |  | 2018-09-11 | 2020-03-04 | 2022-09-01 | 95% | 2022-09-01
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100A | OIR: MSAB - AIRFIELD PAVEMENTS |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100B | OIR: MSAB - ISR SHELTERS |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100C | OIR: MSAB - CAS REVETMENTS/SUNSHADES |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Jordan | ASVF183100D | OIR: MSAB - DORMITORY |  |  |  | 2019-04-05 | 2021-10-09 | 2021-10-09 | 100% | 2021-10-09
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100E | OIR: MSAB - CARGO MARSHALLING YARD FACILITY |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Jordan | ASVF183100F | OIR: MSAB - SUPPORTING FACILITIES/UTILITIES |  |  |  | 2018-08-22 | 2021-07-14 | 2022-07-12 | 100% | 2022-07-12
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Louisiana | United States | AWUB095000 | Consolidated Communication Facility |  |  |  | 2019-07-17 | 2022-05-20 | 2022-10-07 | 63% | 2022-10-07
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Louisiana | United States | AWUB105003 | FIRE STATION NO. 2 |  |  |  | 2018-08-01 | 2020-10-08 | 2021-02-23 | 100% | 2021-02-23
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Iceland | BIKF180001 | ERI: AIRFIELD REPAIRS AND UPGRADES |  |  |  | 2019-08-12 | 2020-04-15 | 2021-02-13 | 100% | 2021-02-13
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190001 | EDI: AIRFIELD UPGRADES - APRON EXPANSION |  |  |  | 2021-01-30 | 2023-03-05 | 2023-03-05 | 1% | 2023-03-06
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190002 | EDI: BEDDOWN SITE PREPARATION |  |  |  | 2021-01-30 | 2023-03-05 | 2023-03-05 | 1% | 2023-03-06
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190003 | EDI: AIRFIELD UPGRADES - DANGEROUS CARGO PAD |  |  |  | 2021-01-30 | 2023-03-05 | 2023-03-05 | 1% | 2023-03-06
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170001 | Construct Chabelley Access Road |  |  |  | 2018-08-05 | 2019-11-01 | 2022-01-27 | 100% | 2022-01-27
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170002 | Construct Parking Apron and Taxiway |  |  |  | 2018-08-05 | 2019-11-01 | 2022-02-22 | 100% | 2022-02-22
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Colorado | United States | CRWU093002 | SBIRS Operations Facility |  |  |  | 2019-02-12 | 2021-04-22 | 2022-08-16 | 99% | 2022-08-16
2022-07-31 | 2019 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | CRWU173001 | Large Vehicle Inspection Point (LVIP) |  |  |  | 2020-10-13 | 2021-12-12 | 2022-03-01 | 100% | 2022-03-01
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | United Arab Emirates | DHAF152900 | LARGE AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2019-09-26 | 2022-02-17 | 2022-08-23 | 90% | 2022-08-23
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | DXEB053005 | FIRE STATION |  |  |  | 2018-05-04 | 2020-04-07 | 2021-10-01 | 100% | 2020-07-31
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Estonia | EEEI150006 | ERI: Construct Bulk Fuel Storage |  |  |  | 2021-08-02 | 2023-04-28 | 2023-04-28 | 1% | 2023-01-01
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Estonia | EEEI180001 | ERI: POL CAPACITY PHASE 2 |  |  |  | 2021-08-02 | 2023-04-28 | 2023-04-28 | 1% | 2023-06-28
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | EEPZ1073283 | MODULAR FIRING RANGE |  |  |  | 2021-07-20 | 2022-12-08 | 2022-12-08 | 3% | 2022-12-08
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Poland | EPPW170003 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2017-11-27 | 2020-03-26 | 2021-01-27 | 100% | 2021-01-27
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Poland | EPPW190001 | EDI: MUNITIONS STORAGE AREA |  |  |  | 2022-05-19 | 2024-11-05 | 2024-11-05 | 1% | 2025-02-03
2022-07-31 | 2017 | Air Force Active | Military Family Housing Improvement |  | Japan | EVKP174535 | IMPROVE FAMILY HOUSING (NORTH FOSTER TOWERS) |  |  |  | 2021-09-01 | 2023-08-16 | 2024-08-31 | 12% | 2024-08-31
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Arizona | United States | FBNV033002 | UPL-Aerospace Ground Equipment (AGE) Complex |  |  |  | 2019-12-10 | 2022-07-01 | 2022-08-24 | 53% | 2022-08-24
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | FBNV163001 | Add/Alter MXG Engine Maintenance Facility |  |  |  | 2020-04-09 | 2021-06-25 | 2021-07-12 | 100% | 2021-07-12
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Delaware | United States | FJXT133000 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2020-04-24 | 2022-05-25 | 2023-04-30 | 47% | 2023-04-30
2022-07-31 | 2016 | Air Force Active | Unspecified Minor Military Construction | Texas | United States | FNWZ100071A | Military Working Dogs Facs - Multi |  |  |  | 2018-10-22 | 2019-10-22 | 2022-09-30 | 88% | 2022-09-30
2022-07-31 | 2017 | Air Force Active | Major Military Construction | California | United States | FSPM053503C | FLIGHT LINE FIRE STATION |  |  |  | 2018-06-20 | 2020-07-31 | 2020-07-31 | 100% | 2020-07-31
2022-07-31 | 2021 | Air Force Active | Major Military Construction | California | United States | FSPM1075894 | FLIGHT TEST ENGINEERING LABORATORY COMPLEX |  |  |  | 2022-03-30 | 2024-01-27 | 2024-01-27 | 1% | 2024-01-27
2022-07-31 | 2019 | Air Force Active | Major Military Construction | California | United States | FSPM173504 | Joint Simulation Environment Facility - Edwards |  |  |  | 2020-09-09 | 2022-08-09 | 2022-09-09 | 74% | 2022-09-09
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA033003 | Flightline Fire Station |  |  |  | 2018-01-29 | 2019-07-23 | 2021-02-26 | 100% | 2020-02-26
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA043000 | Advanced Munitions Technology Complex |  |  |  | 2019-05-01 | 2021-09-20 | 2022-09-30 | 97% | 2022-07-21
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA053017 | Dormitories Replace Dorm 19 |  |  |  | 2019-11-06 | 2021-11-05 | 2022-08-29 | 77% | 2022-11-27
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA093965 | F-35A Student Dormitory II |  |  |  | 2019-05-02 | 2021-05-01 | 2021-12-19 | 100% | 2022-01-01
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | FTFA133002 | CNST AT Entry Control Point North Gate |  |  |  | 2021-06-09 | 2022-09-01 | 2022-10-30 | 71% | 2022-10-30
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA143913 | F-35A Integrated Trng Center Academics Bldg |  |  |  | 2019-06-11 | 2021-06-10 | 2021-09-08 | 100% | 2021-09-08
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Florida | United States | FTFA163003 | F-35A Armament Research Facility Addition (B614) |  |  |  | 2018-11-01 | 2020-08-22 | 2021-07-14 | 100% | 2021-07-14
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA163007 | Cyberspace Test Facility |  |  |  | 2021-01-01 | 2023-09-18 | 2023-09-18 | 10% | 2023-09-18
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1053834 | F-35 Aircraft Maintenance Unit Admin Facility |  |  |  | 2019-08-05 | 2021-08-05 | 2022-12-31 | 98% | 2022-12-31
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1054329 | F-35 Conventional Munitions Maintenance Fac |  |  |  | 2019-10-16 | 2021-10-13 | 2022-11-30 | 95% | 2022-11-30
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1055646 | F-35 AME Storage Facility |  |  |  | 2021-09-09 | 2024-07-13 | 2024-07-13 | 12% | 2024-07-13
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170100 | F-35A ADAL FIELD TRAINING DETACHMENT (FTD) FACILITY |  |  |  | 2017-06-20 | 2019-07-01 | 2019-07-01 | 100% | 2019-07-01
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180107 | F-35A Consolidated Munitions Admin Facility |  |  |  | 2018-04-05 | 2020-05-14 | 2022-12-31 | 97% | 2022-12-31
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180109 | F-35A School Age Facility |  |  |  | 2019-03-12 | 2020-08-01 | 2020-09-25 | 100% | 2020-09-25
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180110 | F-35 CATM Range |  |  |  | 2021-09-16 | 2023-02-26 | 2023-02-26 | 15% | 2023-02-26
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW183001 | F-35A Aircraft Weather Shelter SQD #2 |  |  |  | 2018-06-15 | 2020-05-06 | 2021-03-18 | 100% | 2021-03-18
2022-07-31 | 2021 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM1081508 | B-21 2-Bay LO Restoration Facility |  |  |  | 2021-11-15 | 2024-11-01 | 2024-11-01 | 2% | 2024-11-01
2022-07-31 | 2022 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM1093477 | B-21 Formal Training Unit/AMU |  |  |  | 2022-07-21 | 2024-10-16 | 2024-10-16 | 1% | 2024-10-16
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FXSB982839 | ADD/ALTER AWACS ALERT HANGAR |  |  |  | 2020-04-16 | 2022-05-27 | 2022-08-30 | 98% | 2022-08-30
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN083004 | MISSILE TRANSFER FACILITY |  |  |  | 2017-06-15 | 2020-07-31 | 2020-08-06 | 100% | 2020-08-06
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN153001 | FE WARREN--WEAPON STORAGE FACILITY |  |  |  | 2019-02-20 | 2022-06-04 | 2023-03-05 | 37% | 2023-03-05
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Washington | United States | GJKZ040009 | SERE PIPELINE DORMITORY (150 RM) |  |  |  | 2019-02-22 | 2022-02-22 | 2022-03-31 | 100% | 2022-03-21
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Washington | United States | GJLK1053425 | ADD/ALTER Joint Personnel Recovery Agency Command & Control, Mission Support Facility |  |  |  | 2020-10-20 | 2022-10-20 | 2022-10-20 | 56% | 2022-10-20
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Colorado | United States | GLEN203001 | Consolidated Space Operations Facility |  |  |  | 2021-10-19 | 2025-05-31 | 2025-05-31 | 7% | 2025-05-31
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | North Dakota | United States | JFSD201120 | MUNITIONS MAINTENANCE AND INSPECTION FACILITY |  |  |  | 2021-08-18 | 2023-01-14 | 2023-01-14 | 6% | 2023-01-14
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Hawaii | United States | KNMD043004 | F-22 FIGHTER ALERT FACILITY |  |  |  | 2018-11-01 | 2020-10-22 | 2021-10-29 | 100% | 2021-09-21
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Utah | United States | KRSM1065068 | GBSD Mission Integration Facility |  |  |  | 2020-08-17 | 2022-05-20 | 2023-06-03 | 14% | 2023-06-03
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Utah | United States | KRSM113031 | Construct East Gate Canopy and Inspection Facility |  |  |  | 2021-01-19 | 2022-01-19 | 2022-08-21 | 90% | 2022-08-21
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Utah | United States | KRSM123009 | UTTR CONSOLIDATED MISSION CONTROL CENTER |  |  |  | 2021-03-24 | 2023-01-14 | 2023-01-14 | 46% | 2023-01-14
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Utah | United States | KRSM143003 | F-35A MUNITIONS MAINTENANCE COMPLEX |  |  |  | 2018-10-19 | 2022-07-15 | 2022-08-30 | 99% | 2022-08-30
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Utah | United States | KRSM183001 | Missile Storage Facility |  |  |  | 2021-08-25 | 2023-06-02 | 2023-06-02 | 6% | 2023-06-02
2022-07-31 | 2020 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD1055707 | NC3 SUPPORT WRM STORAGE/SHIPPING FACILITY |  |  |  | 2021-07-09 | 2022-09-20 | 2023-07-08 | 20% | 2023-07-08
2022-07-31 | 2018 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD143000 | RPA FIXED GROUND CONTROL STATION FACILITY |  |  |  | 2019-09-28 | 2019-09-25 | 2021-10-25 | 100% | 2021-10-25
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Bulgaria | LBPG150008 | ERI: FIGHTER RAMP EXTENSION |  |  |  | 2019-02-11 | 2024-03-19 | 2024-03-19 | 1% | 2024-05-16
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Bulgaria | LBPG150009 | ERI: CONSTRUCT SQUADRON OPERATIONS/OPERATION ALERT FACILITY |  |  |  | 2019-02-11 | 2022-02-11 | 2024-05-17 | 1% | 2024-07-11
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Turkey | LJYC133003 | AIRFIELD FIRE / CRASH RESCUE STATION |  |  |  | 2019-03-04 | 2023-04-12 | 2023-04-12 | 40% | 2023-07-14
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Turkey | LJYC183004 | REPLACE PERIMETER FENCE |  |  |  | 2019-06-11 | 2023-06-07 | 2023-06-07 | 40% | 2023-07-10
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | LKTC203101 | MQ-9 CPIP GCS Operations Facility |  |  |  | 2019-10-13 | 2022-05-23 | 2022-05-23 | 100% | 2022-05-23
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | LKTC203102 | MQ-9 CPIP Ops & Command Center Facility |  |  |  | 2019-11-13 | 2022-05-23 | 2022-05-23 | 100% | 2022-05-23
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150007 | ERI: EXTEND PARKING APRONS |  |  |  | 2018-01-17 | 2021-12-08 | 2022-09-15 | 1% | 2022-10-14
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150008 | ERI: CONSTRUCT MUNITIONS STORAGE AREA |  |  |  | 2018-01-17 | 2020-03-12 | 2021-12-14 | 100% | 2022-02-17
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150009 | ERI: CONSTRUCT ONE-BAY HANGAR |  |  |  | 2018-01-17 | 2021-12-08 | 2022-09-15 | 68% | 2022-10-28
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150010 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2020-04-21 | 2022-01-15 | 2022-11-20 | 66% | 2022-11-20
2022-07-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT190001 | EDI: DANGEROUS CARGO PAD |  |  |  | 2021-07-29 | 2023-08-16 | 2023-08-16 | 1% | 2024-09-10
2022-07-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT190002 | EDI: POL INCREASE CAPACITY |  |  |  | 2021-10-29 | 2024-11-04 | 2024-11-04 | 1% | 2024-12-24
2022-07-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT210001 | EDI-DABS-FEV STORAGE |  |  |  | 2021-09-28 | 2023-05-24 | 2023-05-24 | 1% | 2024-02-08
2022-07-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT210002 | EDI-AIRCRAFT PARKING APRON |  |  |  | 2021-12-01 | 2023-12-14 | 2023-12-14 | 1% | 2024-01-18
2022-07-31 | 2022 | Air Force Active | Major Military Construction |  | Japan | LXEZ1069456 | PDI: AIRFIELD DAMAGE REPAIR STORAGE FACILITIES |  |  |  | 2022-06-15 | 2024-08-30 | 2024-08-30 | 1% | 2024-08-30
2022-07-31 | 2016 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ154288 | IMPROVE FAMILY HSG INFRASTRUCTURE, PH 4 |  |  |  | 2018-11-26 | 2021-01-14 | 2023-01-30 | 98% | 2021-11-17
2022-07-31 | 2016 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ164289 | IMPROVE FAMILY HSG INFRASTRUCTURE, PH 5 |  |  |  | 2018-11-26 | 2021-01-14 | 2023-01-30 | 98% | 2023-01-30
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Japan | LXEZ183486 | AIRFIELD SECURITY BARRIERS |  |  |  | 2021-08-02 | 2022-12-07 | 2022-12-10 | 2% | 2022-12-10
2022-07-31 | 2018 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ184546 | IMPROVE FAMILY HOUSING, KAB SEBILLE MANOR (100 UN) |  |  |  | 2020-10-01 | 2023-02-28 | 2023-02-28 | 22% | 2023-02-28
2022-07-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173001 | VISITOR'S CENTER |  |  |  | 2021-12-02 | 2022-07-31 | 2022-08-30 | 85% | 2022-08-30
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173002 | ENTRY GATE INSPECTION AREA |  |  |  | 2020-06-15 | 2022-03-16 | 2022-06-08 | 100% | 2022-03-16
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173003 | COMMERCIAL VEHICLE INSPECTION |  |  |  | 2020-06-15 | 2022-03-16 | 2022-06-08 | 100% | 2022-03-16
2022-07-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | New Mexico | United States | MHMV053107 | LIGHTING FOR AIRCRAFT MAINTENANCE AND PARKING |  |  |  | 2021-05-04 | 2022-05-29 | 2022-11-05 | 57% | 2022-11-05
2022-07-31 | 2018 | Air Force Active | Major Military Construction | New Mexico | United States | MHMV083126A | Replace Fire Station 3 |  |  |  | 2020-12-31 | 2022-11-27 | 2023-04-25 | 40% | 2023-04-25
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R5 | BMT RECRUIT DORMITORY 5 |  |  |  | 2019-03-20 | 2022-01-22 | 2022-09-30 | 57% | 2022-09-30
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R6 | BMT RECRUIT DORMITORY 6 |  |  |  | 2020-05-10 | 2023-10-27 | 2022-12-15 | 10% | 2022-12-15
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737S3 | BMT CLASSROOMS/DINING FACILITY PHASE 3 |  |  |  | 2019-05-01 | 2022-01-20 | 2022-09-30 | 57% | 2022-09-30
2022-07-31 | 2016 | Air Force Active | Unspecified Minor Military Construction | Texas | United States | MPLS113003A | Telephone Maintenance Facility |  |  |  | 2019-05-02 | 2020-06-30 | 2021-06-03 | 100% | 2021-07-21
2022-07-31 | 2015 | Air Force Active | Major Military Construction | Texas | United States | MPLS3274JB | FIRE STATION |  |  |  | 2015-07-08 | 2020-06-03 | 2021-06-03 | 100% | 2021-06-18
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Texas | United States | MPYJ043895A | Aquatics tank |  |  |  | 2021-04-10 | 2022-11-01 | 2023-06-26 | 23% | 2023-06-26
2022-07-31 | 2019 | Air Force Active | Major Military Construction | New Jersey | United States | MSBL103000 | COMMERCIAL VEHICLE SECURITY ENTRY CONTROL POINT (ECP) |  |  |  | 2021-11-22 | 2023-05-16 | 2023-05-16 | 3% | 2023-07-21
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET143006 | CONSOLIDATED CORROSION CONTROL FACILITY |  |  |  | 2021-01-21 | 2024-02-05 | 2024-02-05 | 29% | 2024-02-05
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153501 | F-35A FLIGHT SIMULATOR FACILITY |  |  |  | 2019-07-18 | 2020-11-01 | 2022-08-19 | 99% | 2022-08-19
2022-07-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153503 | F-35A FUEL SYSTEM MAINTENANCE DOCK 2 BAY |  |  |  | 2020-09-04 | 2022-04-20 | 2023-10-14 | 72% | 2023-10-14
2022-07-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153504 | F-35A PARKING APRON |  |  |  | 2020-09-04 | 2022-02-28 | 2022-02-28 | 100% | 2022-02-28
2022-07-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153505 | F-35A AGE FACILITY |  |  |  | 2020-01-17 | 2021-04-01 | 2022-02-28 | 100% | 2022-02-28
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153506 | F-35A FIELD TRAINING DETACHMENT FACILITY |  |  |  | 2020-09-14 | 2022-02-19 | 2023-04-24 | 79% | 2023-04-24
2022-07-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153508 | F-35A 6-BAY HANGAR |  |  |  | 2020-11-09 | 2023-02-15 | 2023-02-05 | 11% | 2023-02-05
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153509 | F-35A INFRASTRUCTURE |  |  |  | 2020-04-09 | 2022-08-31 | 2022-08-31 | 85% | 2023-09-30
2022-07-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153511 | F-35A DORM |  |  |  | 2022-03-17 | 2023-06-23 | 2023-06-23 | 1% | 2023-06-23
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153513 | F-35A 6-BAY HANGAR |  |  |  | 2021-01-25 | 2023-03-10 | 2023-03-10 | 54% | 2023-03-10
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153514 | F-35A SQUADRON OPERATIONS AND AMU |  |  |  | 2019-07-28 | 2021-02-01 | 2023-09-15 | 80% | 2023-09-15
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  |  | MUHJ133000 | Air Force Targeting Center Facility |  |  |  | 2021-06-09 | 2024-10-16 | 2023-10-04 | 12% | 2023-10-04
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD083000 | Vandenberg Gate Complex |  |  |  | 2022-04-29 | 2024-04-20 | 2024-04-20 | 1% | 2024-04-20
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD153006 | MIT-Lincoln Laboratory (West Lab CSL/MIF) |  |  |  | 2019-11-18 | 2024-11-22 | 2024-11-22 | 5% | 2024-11-22
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK123007 | C-130H/J FUSELAGE TRAINER FACILITY |  |  |  | 2020-10-15 | 2022-10-15 | 2022-10-15 | 10% | 2022-10-15
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK153001 | DORMITORY (168 PN) |  |  |  | 2021-10-20 | 2023-12-04 | 2023-12-04 | 1% | 2023-12-04
2022-07-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | Arkansas | United States | NKAK193001 | Vandenberg Visitor Control Center |  |  |  | 2021-11-20 | 2022-11-20 | 2022-11-20 | 20% | 2022-11-20
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093016 | COMMUNICATIONS FACILITY |  |  |  | 2018-02-26 | 2020-06-10 | 2020-06-10 | 100% | 2020-06-10
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | NVZR153710 | KC135 Beddown Add Flt Simltr Training |  |  |  | 2020-03-20 | 2021-03-25 | 2021-12-30 | 100% | 2021-12-30
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Florida | United States | NVZR153711 | KC135 Beddown OG/MXG HQ |  |  |  | 2019-10-20 | 2021-05-11 | 2021-10-29 | 100% | 2021-10-27
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Montana | United States | NZAS043002 | TACTICAL RESPONSE FORCE ALERT FACILITY |  |  |  | 2018-08-22 | 2020-05-13 | 2020-08-31 | 100% | 2020-08-31
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Montana | United States | NZAS173001 | Relocate Missile Maintenance Dispatch Facility (MMDF) |  |  |  | 2019-06-25 | 2021-05-15 | 2021-10-12 | 100% | 2021-10-12
2022-07-31 | 2017 | Air Force Active | Major Military Construction |  | Australia | PAF150400 | APR EXPAND AIRCRAFT PARKING APRON |  |  |  | 2018-08-01 | 2019-10-15 | 2021-10-29 | 100% | 2020-12-17
2022-07-31 | 2018 | Air Force Active | Major Military Construction |  | Australia | PAF160600 | APR - BULK FUEL STORAGE TANKS |  |  |  | 2019-10-26 | 2022-09-01 | 2023-06-01 | 84% | 2023-06-01
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Australia | PAF180200 | APSI - JET FUEL STORAGE TANKS |  |  |  | 2022-07-26 | 2025-06-20 | 2025-06-20 | 1% | 2025-06-20
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Australia | PAF180300 | APSI - EARTH COVERED MAGAZINES |  |  |  | 2020-11-02 | 2022-04-20 | 2022-05-24 | 100% | 2022-05-24
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Northern Mariana Islands | PAF189021 | APSI - AIRFIELD DEVELOPMENT PHASE 1 |  |  |  | 2022-01-27 | 2025-10-09 | 2025-10-09 | 7% | 2025-10-09
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Northern Mariana Islands | PAF189022 | APSI - PARKING APRON |  |  |  | 2022-01-27 | 2025-10-09 | 2025-10-09 | 7% | 2025-10-09
2022-07-31 | 2015 | Air Force Active | Major Military Construction |  | Lithuania | PAYZ15001B | ERI: Improve Airfield Infrastructure |  |  |  | 2017-01-12 | 2021-08-15 | 2021-08-03 | 100% | 2021-08-15
2022-07-31 | 2015 | Air Force Active | Major Military Construction |  | Latvia | PAYZ15001C | ERI: Improve Airfield Infrastructure |  |  |  | 2017-01-12 | 2018-07-06 | 2021-05-04 | 100% | 2021-05-04
2022-07-31 | 2015 | Air Force Active | Major Military Construction |  | Italy | PAYZ15001H | ERI: Improve Weapons Storage Facility |  |  |  | 2017-12-04 | 2020-08-28 | 2023-08-18 | 64% | 2023-08-18
2022-07-31 | 2016 | Air Force Active | Major Military Construction |  | Japan | PAYZ16000B | Munitions Storage Igloos |  |  |  | 2020-10-07 | 2021-09-07 | 2021-12-22 | 100% | 2022-02-04
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Alabama | United States | PNQS072140 | JAG School Expansion |  |  |  | 2019-07-10 | 2020-12-31 | 2021-09-15 | 100% | 2021-09-15
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Alabama | United States | PNQS103165 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2019-12-03 | 2021-05-26 | 2021-12-10 | 100% | 2021-09-23
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Kansas | United States | PRQE055155 | Combat Arms Facility |  |  |  | 2018-10-24 | 2020-10-15 | 2021-06-30 | 100% | 2021-06-30
2022-07-31 | 2015 | Air Force Active | Unspecified Minor Military Construction | New Jersey | United States | PTFL106002 | ATFP-AIRFIELD FLIGHTLINE SECURITY ENHANCEMENT |  |  |  | 2019-10-01 | 2020-09-30 | 2021-02-19 | 100% | 2021-01-20
2022-07-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163001 | KC-46A ADAL B2319 FOR BOOM OPERATOR TRAINER |  |  |  | 2019-03-19 | 2021-11-03 | 2021-12-03 | 100% | 2021-12-03
2022-07-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163006 | KC-46A ADAL B3209 FOR FUSELAGE TRAINER |  |  |  | 2018-11-09 | 2019-11-09 | 2019-12-30 | 100% | 2019-12-30
2022-07-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163010 | KC-46A Alter BLDGS FOR OPS AND TFI AMU-AMXS |  |  |  | 2019-09-26 | 2021-05-07 | 2022-11-30 | 95% | 2022-11-30
2022-07-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163019 | KC-46A TWO BAY GENERAL PURPOSE MX HANGAR |  |  |  | 2019-08-23 | 2021-07-23 | 2022-11-30 | 95% | 2022-11-30
2022-07-31 | 2018 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF012005 | Indoor Firing Range |  |  |  | 2019-06-26 | 2020-06-30 | 2021-12-17 | 100% | 2021-12-17
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | North Dakota | United States | QJVF1058361 | Special Purpose Maintenance Facility |  |  |  | 2022-03-03 | 2023-03-31 | 2023-04-27 | 1% | 2023-04-27
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Georgia | United States | QSEU083023 | PERSONNEL RECOVERY 4-BAY HANGAR/HMU |  |  |  | 2020-10-29 | 2022-10-29 | 2022-10-29 | 7% | 2025-06-27
2022-07-31 | 2017 | Air Force Active | Military Family Housing Improvement |  | Spain | QUUG064001 | RENOVATE MFH UNITS 650 AND 658 |  |  |  | 2021-09-28 | 2022-12-08 | 2023-04-30 | 25% | 2023-04-30
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Nevada | United States | RKMF063004 | RED FLAG 5th GEN FACILITY ADDITION |  |  |  | 2019-08-13 | 2022-04-27 | 2022-08-30 | 98% | 2022-04-27
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103011 | F-35A MUNITIONS MAINTENANCE FACILITIES |  |  |  | 2020-01-30 | 2022-06-26 | 2022-09-30 | 79% | 2022-09-30
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | RKMF123009 | CRH Simulator |  |  |  | 2019-11-20 | 2021-07-02 | 2022-10-31 | 97% | 2022-10-31
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Nevada | United States | RKMF163007 | 365 ISR Group Consolidated Facility |  |  |  | 2020-12-08 | 2022-12-04 | 2023-05-07 | 3% | 2023-05-07
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Nevada | United States | RKMF173010 | HYDRAZINE FUEL STORAGE & SERVICING FACILITY |  |  |  | 2019-11-12 | 2020-09-30 | 2022-09-30 | 90% | 2022-09-30
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Nevada | United States | RKMF203001 | F-35A MUNITIONS ASSEMBLY CONVEYOR (MAC) FACILITY |  |  |  | 2020-12-01 | 2022-07-03 | 2022-08-30 | 70% | 2022-08-30
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | RKMF203007 | Joint Simulation Environment (JSE) - Nellis |  |  |  | 2020-08-03 | 2022-07-24 | 2022-08-23 | 8% | 2022-08-23
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP1047602 | PARKING LOT, USSTRATCOM |  |  |  | 2019-05-30 | 2020-08-21 | 2020-08-21 | 100% | 2020-08-21
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212904 | LOGISTICS READINESS SQUADRON CAMPUS |  |  |  | 2021-10-28 | 2023-07-20 | 2023-07-20 | 11% | 2023-07-20
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212907 | FLIGHTLINE HANGARS CAMPUS |  |  |  | 2022-01-25 | 2023-07-20 | 2023-09-20 | 1% | 2023-09-20
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212908 | LAKE CAMPUS |  |  |  | 2021-10-05 | 2023-03-29 | 2023-05-29 | 11% | 2023-05-29
2022-07-31 | 2019 | Air Force Active | Unspecified Minor Military Construction |  | Korea, South | SMYU073011 | MILITARY WORKING DOG KENNEL SUPPORTING FACILITY |  |  |  | 2019-09-30 | 2021-02-21 | 2021-08-30 | 100% | 2021-08-30
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | SXHT013001 | FIRE/CRASH RESCUE STATION |  |  |  | 2017-07-26 | 2019-03-12 | 2021-06-01 | 100% | 2021-06-01
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | SXHT023007 | MAIN GATE |  |  |  | 2022-06-22 | 2024-06-19 | 2024-06-19 | 2% | 2024-06-19
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | TDKA063002D | MWD Kennel Facility |  |  |  | 2019-09-09 | 2020-12-02 | 2020-12-28 | 100% | 2020-12-28
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Colorado | United States | TDKA143002 | SOCNORTH THEATER OPERATIONAL SUPPORT FACILITY |  |  |  | 2021-05-24 | 2023-09-11 | 2023-09-11 | 1% | 2023-09-11
2022-07-31 | 2012 | Air Force Active | Major Military Construction |  | Germany | TYFR063017 | DORMITORY (192 RM) |  |  |  | 2015-08-10 | 2017-06-27 | 2021-08-15 | 100% | 2021-08-15
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Texas | United States | TYMX103001 | REPAIR WING B OF AFPC FACILITY B499 |  |  |  | 2021-09-17 | 2023-03-07 | 2023-03-07 | 14% | 2023-03-07
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Georgia | United States | UHHZ163000 | COMMERCIAL VEHICLE VISITOR CONTROL FACILITY |  |  |  | 2020-06-18 | 2021-12-10 | 2021-12-10 | 100% | 2021-12-28
2022-07-31 | 2019 | Air Force Active | Major Military Construction | New York | United States | ULDF123001 | Anti-terrorism Perimeter Security/Entry Control Point |  |  |  | 2019-11-03 | 2021-04-23 | 2022-08-15 | 100% | 2022-08-30
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Illinois | United States | VDYD101053 | Consolidated Communications Facility Add/Alt |  |  |  | 2020-09-25 | 2023-10-12 | 2024-01-10 | 73% | 2023-12-27
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Illinois | United States | VDYD1055428 | Joint Operations & Mission Planning Center |  |  |  | 2021-08-02 | 2023-06-30 | 2023-06-30 | 16% | 2023-06-30
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Illinois | United States | VDYD1074289 | ADAL MAF Distributed Mission Operations; B5028 |  |  |  | 2021-04-27 | 2023-06-26 | 2023-06-26 | 58% | 2023-06-26
2022-07-31 | 2016 | Air Force Active | Major Military Construction | North Carolina | United States | VKAG013004R5 | AIR TRAFFIC CONTROL TOWER/BASE OPERATIONS FACILITY |  |  |  | 2019-08-14 | 2021-12-22 | 2021-11-15 | 100% | 2021-11-15
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | North Carolina | United States | VKAG193002 | Berkeley Gate Entry Control Point |  |  |  | 2021-04-11 | 2023-01-13 | 2023-01-03 | 47% | 2023-01-03
2022-07-31 | 2019 | Air Force Active | Major Military Construction | South Carolina | United States | VLSB193001 | CPIP MQ-9 MCE GROUP (MILCON) |  |  |  | 2021-02-02 | 2023-03-01 | 2023-03-01 | 74% | 2023-03-01
2022-07-31 | 2022 | Air Force Active | Major Military Construction | Texas | United States | VNVP063002 | Construct Child Development Center, B195 |  |  |  | 2022-08-20 | 2023-08-04 | 2023-08-04 | 1% | 2023-08-04
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK093003 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2017-05-17 | 2019-03-07 | 2021-04-14 | 100% | 2021-04-14
2022-07-31 | 2015 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK153005 | KC-46A TWO-BAY DEPOT MAINTENANCE HANGAR |  |  |  | 2017-05-11 | 2019-04-30 | 2021-11-19 | 100% | 2021-01-21
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Oklahoma | United States | WWYK173005 | IMPROVE LIBERATOR GATE |  |  |  | 2020-02-03 | 2022-09-30 | 2022-09-30 | 91% | 2022-09-30
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193001 | KC-46A Depot Maintenance Hangar |  |  |  | 2019-10-10 | 2022-08-14 | 2023-02-07 | 79% | 2023-02-07
2022-07-31 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193003 | E-3G MISSION AND FLIGHT SIMULATOR TRAINING FACILITY |  |  |  | 2019-03-05 | 2022-06-17 | 2022-06-17 | 100% | 2022-06-17
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193014 | KC-46A Depot Fuel Maintenance Hangar |  |  |  | 2019-10-23 | 2022-08-29 | 2023-02-22 | 79% | 2023-02-22
2022-07-31 | 2020 | Air Force Active | Major Military Construction | California | United States | XDAT1026962 | KC-46A ALTER B181/B185/B187 SQUAD OPS/AMU |  |  |  | 2019-03-20 | 2021-12-16 | 2022-04-30 | 100% | 2022-04-21
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | California | United States | XDAT1030576 | Construct and Expand Taxiway ALPHA and BRAVO |  |  |  | 2021-08-21 | 2021-08-21 | 2021-08-21 | 100% | 2021-08-21
2022-07-31 | 2020 | Air Force Active | Major Military Construction | California | United States | XDAT1046451 | KC-46A Regional Maintenance Training Facility |  |  |  | 2021-06-15 | 2023-03-10 | 2023-03-10 | 37% | 2023-03-10
2022-07-31 | 2018 | Air Force Active | Major Military Construction | California | United States | XDAT1051930 | KC-46A Aircraft 3-Bay Maintenance Hangar |  |  |  | 2020-12-30 | 2023-02-26 | 2023-02-26 | 83% | 2023-02-26
2022-07-31 | 2020 | Air Force Active | Major Military Construction | California | United States | XDAT1074510 | ADAL Aerial Port Squadron Materiel Warehouse |  |  |  | 2021-09-02 | 2023-12-11 | 2023-12-11 | 26% | 2023-12-11
2022-07-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | California | United States | XDAT173002 | KC-46A B564, AGE Covered Storage |  |  |  | 2021-06-30 | 2022-10-22 | 2022-10-22 | 37% | 2022-10-22
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU193004 | CONSTRUCT INDOOR CATM RANGE |  |  |  | 2022-05-05 | 2023-10-12 | 2024-04-24 | 2% | 2024-04-24
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU193005 | FIRE STATION #2 |  |  |  | 2019-12-10 | 2022-08-30 | 2022-12-14 | 67% | 2022-12-14
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU193006 | ACS Flight Simulator |  |  |  | 2019-12-03 | 2022-03-21 | 2022-08-30 | 98% | 2022-08-30
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203002 | CE/Contracting/USACE Complex |  |  |  | 2022-04-26 | 2025-09-27 | 2026-02-06 | 3% | 2026-02-06
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203004 | Dorm Complex |  |  |  | 2021-11-30 | 2024-12-24 | 2024-12-24 | 9% | 2024-12-24
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203006 | Child Development Center |  |  |  | 2020-10-16 | 2023-06-09 | 2022-12-15 | 73% | 2022-12-15
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203010 | 53 WEG Subscale Drone Facility |  |  |  | 2022-04-07 | 2024-07-30 | 2024-12-29 | 3% | 2024-12-29
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203011 | Flightline-MUNS Storage, 7000 Area |  |  |  | 2022-02-23 | 2024-01-18 | 2024-08-01 | 3% | 2024-08-01
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203012 | OSS/RADAR Approach Control Facility |  |  |  | 2022-06-15 | 2024-05-15 | 2024-10-02 | 1% | 2024-10-02
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203013 | Ops/Aircraft Maintenance Unit Hangar #1 |  |  |  | 2022-06-08 | 2024-12-16 | 2025-08-14 | 1% | 2025-08-14
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203014 | Ops/Aircraft Maintenance Unit Hangar #2 |  |  |  | 2022-06-08 | 2025-04-15 | 2025-12-12 | 1% | 2025-12-12
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203015 | Ops/Aircraft Maintenance Unit Hangar #3 |  |  |  | 2022-06-08 | 2025-08-13 | 2026-04-11 | 1% | 2026-04-11
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203016 | Maintenance Squadron Complex |  |  |  | 2022-06-01 | 2025-06-14 | 2026-02-10 | 1% | 2026-02-10
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203017 | Operations Group/Maintenance Group HQ |  |  |  | 2022-06-08 | 2025-05-15 | 2026-01-11 | 1% | 2026-01-11
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203018 | Aircraft Wash Rack |  |  |  | 2022-06-08 | 2025-08-11 | 2025-12-12 | 1% | 2025-12-12
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203019 | AIRCRAFT MX FUEL CELL HANGAR |  |  |  | 2022-06-08 | 2025-03-16 | 2025-11-12 | 1% | 2025-11-12
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203025 | Security Forces Mobility Storage Facility |  |  |  | 2021-08-04 | 2023-05-25 | 2023-06-25 | 25% | 2023-06-25
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203026 | MWR Facilities |  |  |  | 2022-06-08 | 2024-08-23 | 2025-01-03 | 1% | 2025-01-03
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203028 | Lodging Facilities |  |  |  | 2021-07-21 | 2024-08-08 | 2024-08-27 | 17% | 2024-08-27
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203030 | 325th Fighter Wing HQ Facility |  |  |  | 2021-08-26 | 2024-05-30 | 2024-07-01 | 20% | 2024-07-01
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203033 | Emergency Mgmt, Ops Center, Alt CP |  |  |  | 2021-09-22 | 2023-08-23 | 2023-11-21 | 12% | 2023-11-21
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203034 | Silver Flag Facilities |  |  |  | 2021-10-15 | 2023-12-27 | 2023-12-27 | 16% | 2023-12-27
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203038 | Weapons Load Training Hangar |  |  |  | 2022-06-08 | 2025-10-12 | 2026-06-10 | 1% | 2026-06-10
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203040 | Special Purpose Vehicle Maintenance |  |  |  | 2021-09-14 | 2024-05-15 | 2024-10-02 | 15% | 2024-10-02
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203041 | Aircraft Parking Apron |  |  |  | 2022-06-08 | 2024-12-16 | 2025-08-14 | 1% | 2025-08-14
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203044 | Simulator Facility |  |  |  | 2022-06-08 | 2024-12-16 | 2025-07-14 | 1% | 2025-07-14
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203045 | Site Development, Utilities, & Demo Phase 1 |  |  |  | 2022-05-17 | 2026-05-06 | 2026-10-23 | 1% | 2026-10-23
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203046 | Tyndall AFB Gate Complexes |  |  |  | 2021-09-23 | 2024-08-18 | 2024-11-13 | 15% | 2024-11-13
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203047 | Auxiliary Ground Equipment Facility |  |  |  | 2022-06-08 | 2025-02-14 | 2025-10-13 | 1% | 2025-10-13
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203050 | SITE DEVELOPMENT, UTILITIES, & DEMO PHASE 2 |  |  |  | 2022-05-17 | 2026-04-26 | 2026-10-23 | 1% | 2026-10-23
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ164001 | Air Force CyberWorx |  |  |  | 2020-10-13 | 2023-08-13 | 2024-01-08 | 13% | 2024-03-28
2022-07-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | XQPZ174006 | Expand Midfield Facility |  |  |  | 2021-03-29 | 2023-02-27 | 2023-05-28 | 14% | 2023-05-28
2022-07-31 | 2022 | Air Force Active | Major Military Construction | California | United States | XUMU193000 | GBSD STAGE PROCESSING FACILITY |  |  |  | 2022-06-09 | 2024-01-01 | 2024-01-01 | 1% | 2024-01-01
2022-07-31 | 2016 | Air Force Active | Military Family Housing Improvement |  | Germany | YANB144533 | FAMILY HOUSING MANAGEMENT FACILITY |  |  |  | 2020-04-04 | 2021-07-26 | 2024-05-23 | 16% | 2024-08-23
2022-07-31 | 2016 | Air Force Active | Major Military Construction | Missouri | United States | YWHG031002R2 | YWHG031002R2, Consolidated Stealth Operations & Nuclear Alert Facility |  |  |  | 2019-03-19 | 2021-09-15 | 2021-09-15 | 100% | 2021-09-15
2022-07-31 | 2020 | Air Force Active | Major Military Construction | Missouri | United States | YWHG1030692 | CONSOLIDATED VEHICLE MAINTENANCE FACILITY |  |  |  | 2021-07-29 | 2023-06-10 | 2023-09-01 | 4% | 2023-01-08
2022-07-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Missouri | United States | YWHG163100 | Force Support Squadron Annex |  |  |  | 2022-04-08 | 2023-07-28 | 2023-09-04 | 10% | 2023-06-01
2022-07-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | Missouri | United States | YWHG193001 | New ECP at LeMay Gate |  |  |  | 2021-09-21 | 2022-11-04 | 2022-11-04 | 25% | 2022-11-04
2022-07-31 | 2019 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV093301 | ADAL Intelligence Production Facility |  |  |  | 2020-11-04 | 2023-01-22 | 2023-01-22 | 12% | 2023-01-22
2022-07-31 | 2018 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV153201 | FIRE/CRASH RESCUE STATION |  |  |  | 2020-05-06 | 2021-09-03 | 2022-08-30 | 94% | 2022-08-30
2022-07-31 | 2020 | Air Force Active | Major Military Construction |  | Japan | ZNRE2031002 | APSI - FUEL RECEIPT AND DISTRIBUTION UPGRADES |  |  |  | 2022-03-03 | 2024-04-12 | 2024-04-12 | 2% | 2024-04-12
2022-07-31 | 2020 | Air Force Active | Military Family Housing Improvement |  | Japan | ZNRE204308 | Improve Family Housing Phase 8a |  |  |  | 2020-09-16 | 2023-01-05 | 2023-01-05 | 41% | 2023-01-05
2022-07-31 | 2022 | Air Force Active | Military Family Housing Improvement |  | Japan | ZNRE254300 | IMPROVE FAMILY HOUSING, YOKOTA AB PHASE 8 (45 UN) |  |  |  | 2022-05-18 | 2024-10-30 | 2024-10-30 | 1% | 2024-10-30
2022-07-31 | 2020 | Air Force Reserve | Major Military Construction | Maryland | United States | AJXF223744 | Aeromedical Evacuation Squadron Training/Admin. Facility |  |  |  | 2020-09-23 | 2022-05-26 | 2023-01-20 | 50%
2022-07-31 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Louisiana | United States | AWUB105005 | Missile Maintenance Facility |  |  |  | 2019-03-30 | 2020-03-31 | 2021-08-27 | 100%
2022-07-31 | 2019 | Air Force Reserve | Major Military Construction | Indiana | United States | CTGB169002 | Aerial Port Facility |  |  |  | 2019-08-26 | 2020-10-27 | 2022-05-13 | 100%
2022-07-31 | 2019 | Air Force Reserve | Major Military Construction | Indiana | United States | CTGB989003 | Aircraft Maintenance Hanger, Bldg. 437 |  |  |  | 2020-09-16 | 2022-05-04 | 2022-10-31 | 81%
2022-07-31 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Texas | United States | DDPM130007 | Munitions Training/Admin Facility |  |  |  | 2018-12-12 | 2020-09-14 | 2021-01-31 | 100%
2022-07-31 | 2021 | Air Force Reserve | Major Military Construction | Texas | United States | DDPM414396 | F-35A Flight Simulator |  |  |  | 2021-09-29 | 2024-09-30 | 2024-09-30 | 21%
2022-07-31 | 2021 | Air Force Reserve | Major Military Construction | Texas | United States | DDPM414415 | F-35A Squadron Ops/AMU |  |  |  | 2021-09-29 | 2024-09-30 | 2024-09-30 | 21%
2022-07-31 | 2016 | Air Force Reserve | Major Military Construction | Georgia | United States | FGWB009002 | Fire Station |  |  |  | 2017-12-13 | 2019-06-06 | 2022-03-09 | 100%
2022-07-31 | 2018 | Air Force Reserve | Major Military Construction | Hawaii | United States | KNMD624007 | Consolidated Training Facility |  |  |  | 2021-01-29 | 2022-07-11 | 2022-11-30 | 58%
2022-07-31 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Mississippi | United States | MAHG063004 | Aeromedical Staging Squadron Facility |  |  |  | 2019-12-11 | 2020-10-31 | 2021-08-30 | 100%
2022-07-31 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | California | United States | PDPG120514 | Satellite Fire Station |  |  |  | 2018-09-14 | 2019-11-08 | 2021-05-31 | 100%
2022-07-31 | 2021 | Air Force Reserve | Major Military Construction | Minnesota | United States | QJKL100004 | Aerial Port Facility |  |  |  | 2021-09-22 | 2023-09-22 | 2023-09-22 | 3%
2022-07-31 | 2019 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ079104 | Physical Fitness Center |  |  |  | 2019-09-02 | 2021-07-23 | 2021-12-08 | 100%
2022-07-31 | 2018 | Air Force Reserve | Major Military Construction | Florida | United States | SXHT103001 | Guardian Angel Facility |  |  |  | 2018-08-29 | 2020-07-19 | 2022-05-31 | 100%
2022-07-31 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Florida | United States | SXHT171217 | Addition To 39 RQS B 673 |  |  |  | 2020-03-01 | 2021-03-15 | 2021-08-12 | 100%
2022-07-31 | 2019 | Air Force Reserve | Major Military Construction | Florida | United States | SXHT203000 | HC-130J General Maintenance Hanger |  |  |  | 2022-06-05 | 2024-03-21 | 2024-04-01 | 3%
2022-07-31 | 2018 | Air Force Reserve | Major Military Construction | Georgia | United States | UHHZ073003 | Consolidated Mission Complex, Phase 2 |  |  |  | 2019-11-07 | 2021-11-26 | 2022-09-20 | 95%
2022-07-31 | 2020 | Air Force Reserve | Major Military Construction | Georgia | United States | UHHZ073005 | Consolidated Mission Complex, Phase 3 |  |  |  | 2021-03-18 | 2023-04-11 | 2023-06-24 | 35%
2022-07-31 | 2017 | Air Force Reserve | Major Military Construction | North Carolina | United States | VKAG159021 | KC-46A Construct Two Bay Corrosion/Fuel Cell Hangar |  |  |  | 2017-09-27 | 2020-09-09 | 2021-08-31 | 100%
2022-07-31 | 2018 | Air Force Reserve | Major Military Construction | North Carolina | United States | VKAG159026 | KC-46A ADAL Bldg. for Alternate Mission Equipment Storage |  |  |  | 2020-09-29 | 2022-07-08 | 2022-10-06 | 60%
2022-07-31 | 2018 | Air Force Reserve | Major Military Construction | Massachusetts | United States | YTPM059004 | Indoor Small Arms Range |  |  |  | 2019-11-04 | 2020-12-12 | 2021-08-12 | 100%
2022-07-31 | 2019 | Air Force Reserve | Major Military Construction | Massachusetts | United States | YTPM099001B | Regional ISO Maintenance Hanger |  |  |  | 2021-09-29 | 2023-09-29 | 2023-09-29 | 10%
2022-07-31 | 2021 | Air National Guard | Major Military Construction | Maryland | United States | AJXF189013 | F-16 Mission Training Center |  |  |  | 2022-07-15 | 2024-01-11 | 2023-12-11 | 1%
2022-07-31 | 2018 | Air National Guard | Unspecified Minor Military Construction | Connecticut | United States | CEKT149052 | Add Alter B10018 for Security Forces |  |  |  | 2018-12-18 | 2024-12-26 | 2022-04-30 | 98%
2022-07-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Wyoming | United States | DPEZ029038 | Security Forces Facility |  |  |  | 2021-12-03 | 2023-02-28 | 2023-02-21 | 21%
2022-07-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Wyoming | United States | DPEZ189031 | Combat Arms Training & Emergency Management |  |  |  | 2022-05-19 | 2023-08-08 | 2023-04-14 | 1%
2022-07-31 | 2021 | Air National Guard | Major Military Construction | Alabama | United States | FAKZ189019 | F-35 Simulator Facility |  |  |  | 2022-08-15 | 2024-06-29 | 2024-06-25 | 1%
2022-07-31 | 2021 | Air National Guard | Major Military Construction | Alabama | United States | FAKZ999088 | Base Supply Complex |  |  |  | 2022-08-15 | 2024-06-20 | 2024-05-21 | 1%
2022-07-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | North Carolina | United States | FJRP189050 | C-17 Munitions Storage Area Expansion |  |  |  | 2021-12-23 | 2022-08-20 | 2022-08-20 | 67%
2022-07-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | North Carolina | United States | FJRP199040 | C-17 Conv: Air Drop Facility |  |  |  | 2021-12-15 | 2023-03-10 | 2023-03-10 | 17%
2022-07-31 | 2018 | Air National Guard | Unspecified Minor Military Construction | Minnesota | United States | FMKM119035 | Add to Logistics Readiness B222 |  |  |  | 2021-04-19 | 2022-10-11 | 2022-12-31 | 76%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Minnesota | United States | FMKM179063 | Construct Small Arms Range |  |  |  | 2022-05-31 | 2022-10-31 | 2022-11-18 | 17%
2022-07-31 | 2018 | Air National Guard | Unspecified Minor Military Construction | New York | United States | HAAW179035 | ISR: ADAL Reaper Operations Center (B643) |  |  |  | 2020-07-30 | 2021-08-08 | 2022-09-01 | 95%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Illinois | United States | JLQN049119 | Construct New Fire Crash Rescue Station |  |  |  | 2019-06-01 | 2023-10-18 | 2022-08-01 | 96%
2022-07-31 | 2018 | Air National Guard | Major Military Construction | Oregon | United States | KJAQ159096 | Construct Indoor Range |  |  |  | 2021-03-19 | 2022-05-05 | 2022-09-01 | 95%
2022-07-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | Oregon | United States | KJAQ179127 | Construct Multi-Use Addition B127 |  |  |  | 2022-03-15 | 2023-03-15 | 2023-03-15 | 4%
2022-07-31 | 2021 | Air National Guard | Major Military Construction | North Dakota | United States | KKGA169022 | Consolidated RPA Operations Facility |  |  |  | 2021-07-20 | 2022-07-20 | 2023-03-10 | 44%
2022-07-31 | 2018 | Air National Guard | Unspecified Minor Military Construction | Hawaii | United States | KNMD179040 | MCCA Install 15 KVA Power Lines for Microgrid |  |  |  | 2019-05-14 | 2021-05-23 | 2023-02-01 | 90%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Hawaii | United States | KNMD189008 | 3rd Bay F-22 LO CRF B3408 |  |  |  | 2021-02-18 | 2023-03-05 | 2023-04-07 | 50%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Pennsylvania | United States | LKLW099101 | Replace Operations Training Dining Hall |  |  |  | 2020-01-07 | 2021-11-07 | 2021-12-27 | 98%
2022-07-31 | 2018 | Air National Guard | Major Military Construction | Mississippi | United States | LRXQ159097 | Construct Small Arms Range |  |  |  | 2021-10-19 | 2022-12-28 | 2023-02-13 | 11%
2022-07-31 | 2018 | Air National Guard | Major Military Construction | South Dakota | United States | LUXC099042 | Aircraft Maintenance Shops |  |  |  | 2022-04-25 | 2024-03-05 | 2024-02-04 | 0%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Virginia | United States | MUHJ179000 | Construct Cyber Ops Facility |  |  |  | 2021-02-20 | 2023-01-31 | 2022-12-01 | 50%
2022-07-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | Ohio | United States | PBXP169102 | Add Alter B403 for Corrosion Control |  |  |  | 2021-06-24 | 2022-02-26 | 2022-08-30 | 95%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Ohio | United States | PBXP929798 | Replace Fire Station |  |  |  | 2020-08-03 | 2022-05-25 | 2023-05-25 | 64%
2022-07-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | West Virginia | United States | PJVY199001 | Correct MILCON Fuel Cell Hangar Deficiencies, B305 |  |  |  | 2022-01-28 | 2025-05-12 | 2023-01-28 | 3%
2022-07-31 | 2019 | Air National Guard | Unspecified Minor Military Construction | South Carolina | United States | PSTE089064 | Add to and Alter Security Forces Building 979 |  |  |  | 2021-12-20 | 2023-10-30 | 2022-12-30 | 5%
2022-07-31 | 2018 | Air National Guard | Unspecified Minor Military Construction | South Carolina | United States | PSTE139022 | Add to Fire Station |  |  |  | 2019-11-05 | 2021-04-22 | 2022-06-30 | 77%
2022-07-31 | 2018 | Air National Guard | Major Military Construction | Tennessee | United States | PSXE999132 | Replace KC-135 Maintenance Hangar and Shops |  |  |  | 2019-08-22 | 2021-08-22 | 2022-12-30 | 98%
2022-07-31 | 2020 | Air National Guard | Major Military Construction | California | United States | QMSN199056 | Fuels Corrosion Control Hangar and Shops |  |  |  | 2021-05-03 | 2022-10-17 | 2023-02-13 | 53%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH059034 | NORTHCOM - Construct Alert Apron |  |  |  | 2021-03-11 | 2024-10-01 | 2023-03-31 | 65%
2022-07-31 | 2019 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH189009 | NORTHCOM - Construct Alert Facilities |  |  |  | 2021-03-11 | 2024-10-01 | 2023-03-31 | 65%
2022-07-31 | 2022 | Air National Guard | Unspecified Minor Military Construction | New Hampshire | United States | SZCQ169264 | ADD to Bldg 264, Squadron Operations |  |  |  | 2022-05-04 | 2023-11-03 | 2023-11-08 | 5%
2022-07-31 | 2018 | Air National Guard | Major Military Construction | Colorado | United States | TDKA169004 | Space Control Facility |  |  |  | 2021-03-26 | 2022-03-26 | 2022-12-18 | 63%
2022-07-31 | 2020 | Air National Guard | Major Military Construction | Puerto Rico | Puerto Rico | TUMR189003 | Hurricane Maria - Comm Facility |  |  |  | 2021-08-19 | 2024-01-29 | 2024-02-19 | 5%
2022-07-31 | 2020 | Air National Guard | Major Military Construction | Puerto Rico | Puerto Rico | TUMR189004 | Contingency Response Facility |  |  |  | 2021-08-19 | 2024-01-29 | 2024-02-19 | 5%
2022-07-31 | 2018 | Air National Guard | Major Military Construction | Missouri | United States | ULYB049040 | Replace Communications Facility |  |  |  | 2019-09-25 | 2021-03-23 | 2022-09-30 | 98%
2022-07-31 | 2020 | Air National Guard | Major Military Construction | Missouri | United States | ULYB169010 | C-130 Flight Simulator Facility |  |  |  | 2020-10-06 | 2022-03-31 | 2023-02-28 | 68%
2022-07-31 | 2020 | Air National Guard | Major Military Construction | Georgia | United States | XDQU109057 | Consolidated Joint Air Dominance Hangar Shops |  |  |  | 2020-10-27 | 2022-01-23 | 2022-12-31 | 75%
2022-07-31 | 2020 | Air National Guard | Major Military Construction | Wisconsin | United States | XGFG189001 | F-35 Simulator Facility-B424 |  |  |  | 2021-06-21 | 2023-01-07 | 2022-11-30 | 96%
2022-07-31 | 2020 | Air National Guard | Major Military Construction | Wisconsin | United States | XGFG189004 | Fighter Alert Shelters (F-35 bedown) |  |  |  | 2021-08-06 | 2022-11-11 | 2023-02-22 | 10%
2022-07-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Arizona | United States | XHEA189054 | MCCA: Construct AAS Runway 3-21 |  |  |  | 2021-08-30 | 2022-08-30 | 2022-11-27 | 15%
2022-07-31 | 2019 | Army Active | Major Military Construction | New Mexico | United States | 33584 | Information Systems Facility |  |  |  | 2021-05-25 | 2023-12-11 | 2024-11-22 | 11%
2022-07-31 | 2019 | Army Active | Major Military Construction | Kentucky | United States | 35782 | Digital Air/Ground Integration Range |  |  |  | 2020-02-06 | 2022-02-05 | 2023-03-30 | 79%
2022-07-31 | 2019 | Army Active | Major Military Construction | Hawaii | United States | 52203 | Rotary Wing Parking Apron |  |  |  | 2020-11-13 | 2022-08-03 | 2022-06-17 | 99%
2022-07-31 | 2018 | Army Active | Major Military Construction | Georgia | United States | 55112 | Air Traffic Control Tower |  |  |  | 2019-04-17 | 2020-10-08 | 2022-07-07 | 95% | 2022-07-07
2022-07-31 | 2018 | Army Active | Major Military Construction | Washington | United States | 55199 | Fire Station |  |  |  | 2019-12-10 | 2021-11-29 | 2022-05-22 | 93% | 2022-05-22
2022-07-31 | 2021 | Army Active | Major Military Construction | Georgia | United States | 55516 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  | 2021-07-15 | 2023-07-05 | 2023-07-05 | 24%
2022-07-31 | 2020 | Army Active | Major Military Construction | New York | United States | 59766 | Railhead |  |  |  | 2021-10-18 | 2023-10-18 | 2023-10-18 | 6%
2022-07-31 | 2014 | Army Active | Major Military Construction |  | Marshall Islands | 59779 | Pier |  | 2125000 | 92764 | 2016-08-17 | 2020-06-10 | 2024-12-12 | 85%
2022-07-31 | 2020 | Army Active | Major Military Construction | Virginia | United States | 60276 | Secure Operations and Admin Facility |  |  |  | 2021-06-01 | 2024-05-31 | 2024-05-31 | 12%
2022-07-31 | 2018 | Army Active | Major Military Construction | Washington | United States | 61147 | Confinement Facility |  |  |  | 2019-12-06 | 2022-08-22 | 2022-10-23 | 94%
2022-07-31 | 2019 | Army Active | Major Military Construction |  | Honduras | 61388 | Barracks |  |  |  | 2019-07-30 | 2022-07-14 | 2022-02-16 | 100% | 2022-02-16
2022-07-31 | 2017 | Army Active | Major Military Construction |  | Germany | 62380 | Training Support Center |  |  |  | 2018-02-22 | 2022-05-11 | 2023-07-15 | 76%
2022-07-31 | 2013 | Army Active | Major Military Construction |  | Japan | 62783 | Satellite Communications Facility |  |  |  | 2014-11-21 | 2021-06-09 | 2022-10-22 | 81%
2022-07-31 | 2020 | Army Active | Major Military Construction | Michigan | United States | 62856 | Substation |  |  |  | 2020-08-21 | 2022-10-28 | 2022-10-28 | 67%
2022-07-31 | 2019 | Army Active | Major Military Construction |  | Kuwait | 62866 | Vehicle Maintenance Shop |  | 14950000 | 86409, 88380 | 2019-09-30 | 2021-05-02 | 2022-06-30 | 94% | 2022-07-14
2022-07-31 | 2019 | Army Active | Major Military Construction | New Jersey | United States | 63054 | Munitions Disassembly Complex |  | 4300000 | 64026 | 2019-11-04 | 2021-11-03 | 2022-11-30 | 94%
2022-07-31 | 2019 | Army Active | Major Military Construction | Kentucky | United States | 64296 | Vehicle Maintenance Shop |  |  |  | 2022-05-02 | 2024-02-21 | 2024-02-21 | 0%
2022-07-31 | 2018 | Army Active | Major Military Construction | Florida | United States | 65699 | Multipurpose Range Complex |  |  |  | 2019-03-08 | 2020-10-28 | 2021-11-30 | 100% | 2020-10-13
2022-07-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 68530 | Barracks |  |  |  | 2015-11-18 | 2018-12-17 | 2022-12-15 | 98%
2022-07-31 | 2020 | Army Active | Major Military Construction | Kentucky | United States | 69347 | General Purpose Maintenance Shop |  | 6242000 | 68253, 77538 | 2020-06-11 | 2022-07-11 | 2022-11-16 | 89%
2022-07-31 | 2015 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility Complex |  |  |  | 2017-11-02 | 2021-11-07 | 2022-11-25 | 97% | 2022-05-18
2022-07-31 | 2018 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 3 | 58857 |  |  | 2017-11-02 | 2021-11-07 | 2022-11-25 | 97% | 2022-05-18
2022-07-31 | 2017 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 2 | 76593 |  |  | 2017-11-02 | 2021-11-07 | 2022-11-25 | 97% | 2022-05-18
2022-07-31 | 2019 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 4 | 76595 |  |  | 2017-11-02 | 2021-11-07 | 2022-11-25 | 97% | 2022-05-18
2022-07-31 | 2020 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 5 | 92340 |  |  | 2017-11-02 | 2021-11-07 | 2022-11-25 | 97% | 2022-05-18
2022-07-31 | 2017 | Army Active | Major Military Construction | Virginia | United States | 70935 | Vehicle Maintenance Shop |  |  |  | 2021-10-27 | 2024-04-24 | 2024-04-24 | 4%
2022-07-31 | 2020 | Army Active | Major Military Construction | Virginia | United States | 73391 | Adv Individual Training Barracks Cplx, Ph4 |  |  |  | 2020-11-03 | 2022-11-03 | 2022-11-03 | 82%
2022-07-31 | 2017 | Army Active | Major Military Construction | California | United States | 74877 | Access Control Point |  |  |  | 2021-09-02 | 2022-11-26 | 2023-02-24 | 4%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 75157 | Supply Support Activity |  |  |  | 2020-12-02 | 2022-02-25 | 2022-07-11 | 96% | 2022-07-10
2022-07-31 | 2016 | Army Active | Major Military Construction | Oklahoma | United States | 75661 | Reception Barracks Complex Ph2 |  |  |  | 2019-02-05 | 2020-12-26 | 2022-04-22 | 99% | 2022-01-05
2022-07-31 | 2018 | Army Active | Military Family Housing | Massachusetts | United States | 75718 | Family Housing Replacement Construction |  |  |  | 2019-06-03 | 2021-07-02 | 2022-02-18 | 99% | 2022-02-18
2022-07-31 | 2015 | Army Active | Major Military Construction | California | United States | 76093 | Access Control Point |  |  |  | 2019-07-08 | 2020-06-02 | 2022-05-27 | 98% | 2022-06-14
2022-07-31 | 2020 | Army Active | Major Military Construction | Alabama | United States | 76673 | Aircraft and Flight Equipment Building |  |  |  | 2021-01-04 | 2022-12-25 | 2022-12-25 | 78%
2022-07-31 | 2021 | Army Active | Major Military Construction | Hawaii | United States | 76897 | Aircraft Maintenance Hangar |  |  |  | 2021-10-13 | 2024-10-12 | 2024-10-12 | 17%
2022-07-31 | 2018 | Army Active | Major Military Construction | Arizona | United States | 77102 | General Instruction Building |  |  |  | 2018-12-13 | 2020-06-05 | 2022-01-25 | 99% | 2022-03-26
2022-07-31 | 2019 | Army Active | Major Military Construction | Colorado | United States | 77301 | Vehicle Maintenance Shop |  |  |  | 2019-09-03 | 2021-05-04 | 2021-10-15 | 100% | 2022-02-11
2022-07-31 | 2020 | Army Active | Major Military Construction | Colorado | United States | 77303 | Company Operations Facility |  |  |  | 2020-09-10 | 2022-06-12 | 2022-09-08 | 84%
2022-07-31 | 2017 | Army Active | Major Military Construction | Utah | United States | 77538 | Live Fire Exercise Shoothouse |  |  |  | 2018-08-31 | 2020-02-22 | 2022-02-16 | 100% | 2022-04-20
2022-07-31 | 2020 | Army Active | Major Military Construction | Washington | United States | 77728 | Information Systems Facility |  |  |  | 2020-07-14 | 2022-12-31 | 2023-05-26 | 75%
2022-07-31 | 2018 | Army Active | Major Military Construction | Virginia | United States | 77779 | Aircraft Maintenance Instructional Bldg |  |  |  | 2019-06-26 | 2021-02-15 | 2022-03-31 | 97% | 2022-02-28
2022-07-31 | 2018 | Army Active | Military Family Housing |  | Germany | 78713 | Family Housing New Construction |  |  |  | 2022-07-22 | 2023-09-18 | 2023-09-18 | 0%
2022-07-31 | 2019 | Army Active | Major Military Construction | New York | United States | 78804 | Engineering Center |  |  |  | 2021-01-04 | 2025-01-04 | 2025-04-02 | 30%
2022-07-31 | 2015 | Army Active | Unspecified Minor Military Construction | Louisiana | United States | 81234 | Fire Station Addition |  |  |  | 2018-09-27 | 2019-09-27 | 2022-08-31 | 78%
2022-07-31 | 2019 | Army Active | Unspecified Minor Military Construction | California | United States | 81316 | Library Main |  |  |  | 2020-08-18 | 2021-08-18 | 2022-01-31 | 100% | 2022-03-22
2022-07-31 | 2021 | Army Active | Unspecified Minor Military Construction | New Jersey | United States | 81352 | Igloo Storage Installation |  |  |  | 2021-12-01 | 2023-02-02 | 2023-01-25 | 55%
2022-07-31 | 2017 | Army Active | Military Family Housing |  | Korea, South | 81428 | Family Housing New Construction |  |  |  | 2017-09-08 | 2021-07-14 | 2021-12-30 | 100%
2022-07-31 | 2019 | Army Active | Military Family Housing |  | Korea, South | 81429 | Family Housing Replacement Construction |  |  |  | 2019-10-31 | 2022-09-05 | 2022-10-27 | 62%
2022-07-31 | 2019 | Army Active | Major Military Construction | North Carolina | United States | 82254 | Dining Facility |  |  |  | 2020-01-07 | 2021-06-30 | 2022-05-04 | 98% | 2022-05-04
2022-07-31 | 2015 | Army Active | Major Military Construction |  | Romania | 85711 | ERI: Multi Modal Improvements |  |  |  | 2017-12-15 | 2020-12-09 | 2022-08-01 | 99% | 2022-07-29
2022-07-31 | 2017 | Army Active | Major Military Construction | Georgia | United States | 85794 | Company Operations Facility |  |  |  | 2019-02-20 | 2020-06-14 | 2022-04-29 | 95% | 2022-05-30
2022-07-31 | 2019 | Army Active | Unspecified Minor Military Construction |  | Germany | 86019 | Animal Building |  |  |  | 2020-10-10 | 2022-09-27 | 2022-12-26 | 0%
2022-07-31 | 2015 | Army Active | Unspecified Minor Military Construction |  | Germany | 86094 | Child Development Center Addition |  |  |  | 2020-05-18 | 2021-09-05 | 2022-07-29 | 64% | 2022-07-29
2022-07-31 | 2020 | Army Active | Unspecified Minor Military Construction | Virginia | United States | 86215 | Ship Loading and Unloading Mockup |  |  |  | 2021-12-20 | 2022-12-20 | 2022-12-20 | 57%
2022-07-31 | 2015 | Army Active | Major Military Construction |  | Romania | 86404 | ERI: Hazardous Cargo Ramp |  |  |  | 2017-10-24 | 2019-12-13 | 2022-02-11 | 75% | 2022-02-11
2022-07-31 | 2016 | Army Active | Major Military Construction | Maryland | United States | 86409 | Access Control Point |  |  |  | 2020-10-27 | 2022-10-27 | 2022-11-09 | 56%
2022-07-31 | 2018 | Army Active | Unspecified Minor Military Construction | Washington | United States | 86518 | Aircraft Engine Test Building |  |  |  | 2019-08-15 | 2020-08-14 | 2022-05-06 | 92% | 2022-05-06
2022-07-31 | 2017 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction |  |  |  | 2017-10-31 | 2022-07-25 | 2023-02-17 | 93%
2022-07-31 | 2019 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 3 | 86877 |  |  | 2019-02-26 | 2022-07-25 | 2023-02-17 | 93%
2022-07-31 | 2020 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 4 | 91327 | 16300000 | 65981, 87092 | 2017-10-31 | 2020-11-12 | 2021-12-30 | 93% | 2022-03-28
2022-07-31 | 2018 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 2 | 91380 |  |  | 2017-10-31 | 2022-07-25 | 2023-02-17 | 93%
2022-07-31 | 2018 | Army Active | Major Military Construction | Alabama | United States | 86816 | Training Support Facility |  |  |  | 2019-10-21 | 2021-10-10 | 2022-09-17 | 81%
2022-07-31 | 2016 | Army Active | Major Military Construction |  | Germany | 86824 | Vehicle Maintenance Shop |  | 4000000 | 55199 | 2019-06-17 | 2023-06-03 | 2023-06-03 | 25%
2022-07-31 | 2018 | Army Active | Major Military Construction |  | Turkey | 86832 | Forward Operating Site |  |  |  | 2018-10-02 | 2022-03-25 | 2024-04-30 | 59%
2022-07-31 | 2016 | Army Active | Unspecified Minor Military Construction |  | Marshall Islands | 86914 | Storage Fuel Tank Repair |  |  |  | 2017-10-11 | 2018-12-12 | 2022-02-15 | 99% | 2022-07-02
2022-07-31 | 2018 | Army Active | Major Military Construction |  | Germany | 86991 | Administrative Building |  |  |  | 2020-04-03 | 2022-06-22 | 2023-03-19 | 81%
2022-07-31 | 2018 | Army Active | Military Family Housing | Georgia | United States | 87205 | Family Housing New Construction |  |  |  | 2021-02-26 | 2022-10-01 | 2022-10-01 | 91%
2022-07-31 | 2020 | Army Active | Major Military Construction | Texas | United States | 87807 | Barracks |  |  |  | 2021-08-19 | 2023-07-20 | 2023-08-03 | 8%
2022-07-31 | 2020 | Army Active | Major Military Construction | New York | United States | 87933 | Unmanned Aerial Vehicle Hangar |  |  |  | 2020-10-21 | 2022-10-11 | 2022-10-11 | 78%
2022-07-31 | 2016 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 87980 | Develop Good Hope Heavy Maunevuer Training |  |  |  | 2020-01-10 | 2021-01-09 | 2021-11-30 | 100% | 2022-04-07
2022-07-31 | 2020 | Army Active | Major Military Construction | Pennsylvania | United States | 88077 | General Instruction Building INC 1 |  |  |  | 2020-04-01 | 2023-04-01 | 2023-07-19 | 76%
2022-07-31 | 2021 | Army Active | Major Military Construction | Pennsylvania | United States | 88077 | General Instruction Building, Incr 2 | 96217 |  |  | 2021-06-07 | 2023-04-29 | 2023-04-29 | 76%
2022-07-31 | 2018 | Army Active | Major Military Construction | Texas | United States | 88380 | Vehicle Maintenance Shop |  |  |  | 2019-11-04 | 2021-08-15 | 2022-03-04 | 99% | 2022-01-28
2022-07-31 | 2020 | Army Active | Major Military Construction | Georgia | United States | 88410 | Aircraft Maintenance Hangar |  |  |  | 2021-08-11 | 2023-08-01 | 2023-08-01 | 21%
2022-07-31 | 2019 | Army Active | Major Military Construction |  | Poland | 88542 | EDI: Rail Extension and Railhead |  |  |  | 2019-10-30 | 2022-04-17 | 2022-06-01 | 100%
2022-07-31 | 2019 | Army Active | Major Military Construction | Georgia | United States | 88724 | Cyber Instructional Fac and Network Ctr |  |  |  | 2020-07-17 | 2022-07-07 | 2023-02-27 | 43%
2022-07-31 | 2020 | Army Active | Major Military Construction | Georgia | United States | 88725 | Cyber Instructional Fac (Admin/Command)INC |  |  |  | 2021-05-11 | 2024-04-25 | 2024-05-11 | 41%
2022-07-31 | 2020 | Army Active | Major Military Construction | North Carolina | United States | 89057 | Dining Facility |  |  |  | 2020-09-16 | 2022-03-10 | 2023-01-24 | 34%
2022-07-31 | 2017 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 89215 | Maneuver/Training Area Heavy Forces |  |  |  | 2020-01-10 | 2021-01-09 | 2021-11-30 | 100% | 2022-04-07
2022-07-31 | 2018 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 89946 | Engineer Research & Development |  |  |  | 2020-02-27 | 2021-05-22 | 2021-12-10 | 94% | 2021-12-10
2022-07-31 | 2018 | Army Active | Major Military Construction | Arizona | United States | 90351 | Ground Transport Equipment Building |  |  |  | 2021-04-21 | 2023-02-10 | 2023-02-10 | 32%
2022-07-31 | 2018 | Army Active | Major Military Construction | New York | United States | 90722 | Cemetery |  | 1300000 | 88724 | 2019-10-17 | 2021-09-01 | 2022-08-05 | 85% | 2021-10-08
2022-07-31 | 2018 | Army Active | Unspecified Minor Military Construction | North Carolina | United States | 91252 | Pedestrian Bridges |  |  |  | 2020-04-10 | 2021-05-15 | 2022-05-09 | 93% | 2022-05-12
2022-07-31 | 2019 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 91311 | Support Maintenance Warehouse |  |  |  | 2019-10-17 | 2020-12-10 | 2021-10-14 | 86% | 2021-10-20
2022-07-31 | 2020 | Army Active | Unspecified Minor Military Construction | Texas | United States | 91328 | Ready Building-Tactical Operations Center |  |  |  | 2020-11-09 | 2021-11-09 | 2023-02-26 | 8%
2022-07-31 | 2020 | Army Active | Unspecified Minor Military Construction | North Carolina | United States | 91397 | Field Research Facility Annex |  |  |  | 2020-11-20 | 2021-11-15 | 2022-09-02 | 72%
2022-07-31 | 2018 | Army Active | Unspecified Minor Military Construction | California | United States | 91528 | Brigade (BDE) Headquarters Building |  |  |  | 2019-09-12 | 2020-09-11 | 2022-06-28 | 97%
2022-07-31 | 2018 | Army Active | Unspecified Minor Military Construction |  | Romania | 91732 | Power Substation/Switching Station Bldg |  |  |  | 2018-10-30 | 2020-10-24 | 2022-05-13 | 78% | 2022-06-17
2022-07-31 | 2018 | Army Active | Major Military Construction | Hawaii | United States | 91742 | Operational Readiness Tng Cplx (Brks), Ph1 |  | 8500000 | 88724 | 2019-10-04 | 2021-09-23 | 2022-05-13 | 99% | 2022-05-13
2022-07-31 | 2020 | Army Active | Major Military Construction | Texas | United States | 91996 | Vehicle Bridge |  |  |  | 2020-11-19 | 2022-07-12 | 2022-09-13 | 85%
2022-07-31 | 2018 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 92022 | Battle Lab |  |  |  | 2019-08-22 | 2020-06-17 | 2022-03-01 | 88% | 2022-05-20
2022-07-31 | 2020 | Army Active | Unspecified Minor Military Construction | Mississippi | United States | 92422 | Target Assembly Facility Expansion |  |  |  | 2021-11-01 | 2022-11-01 | 2023-02-10 | 54%
2022-07-31 | 2019 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 92518 | Railroad Equipment/Engine Maintenance Shop |  |  |  | 2020-03-11 | 2022-03-11 | 2022-07-31 | 97%
2022-07-31 | 2019 | Army Active | Unspecified Minor Military Construction | Hawaii | United States | 93021 | Aviation Parts Storage |  |  |  | 2020-05-18 | 2022-01-08 | 2022-08-21 | 100% | 2022-05-08
2022-07-31 | 2019 | Army Active | Unspecified Minor Military Construction |  | Germany | 93209 | Aircraft Parts Storage |  |  |  | 2022-03-28 | 2023-03-29 | 2023-06-27 | 0%
2022-07-31 | 2021 | Army Active | Major Military Construction | Virginia | United States | 93322 | Training Support Facility |  |  |  | 2021-12-09 | 2024-01-28 | 2024-01-28 | 13%
2022-07-31 | 2021 | Army Active | Unspecified Minor Military Construction | New York | United States | 94363 | General Instruction Building, Thayer Swing |  |  |  | 2021-11-19 | 2023-05-21 | 2023-05-21 | 21%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 94606 | Yuma Project 2 |  |  |  | 2019-11-12 | 2021-06-08 | 2021-11-05 | 0%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 94607 | Yuma Project 10/27 |  |  |  | 2019-11-12 | 2021-06-08 | 2021-11-05 | 83%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 94608 | Yuma Project 3 |  |  |  | 2020-01-09 | 2021-01-08 | 2021-10-18 | 74%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 94609 | San Diego Project 4 |  |  |  | 2019-12-04 | 2021-03-03 | 2022-04-22 | 47%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 94610 | Yuma Project 6 |  |  |  | 2020-01-21 | 2021-07-20 | 2022-09-30 | 0%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 94611 | El Paso Project 2 |  |  |  | 2020-01-25 | 2021-01-25 | 2022-09-30 | 0%
2022-07-31 | 2019 | Army Active | Major Military Construction | Texas | United States | 94612 | El Paso Project 8 |  |  |  | 2020-01-25 | 2021-01-24 | 2022-09-30 | 0%
2022-07-31 | 2015 | Army Reserve | Major Military Construction | Wisconsin | United States | 67567 | Access Control Point/Mail/Freight Center |  |  |  | 2017-06-02 | 2019-12-22 | 2022-05-18 | 97% | 2022-05-18
2022-07-31 | 2018 | Army Reserve | Major Military Construction |  | Puerto Rico | 77074 | Army Reserve Center |  |  |  | 2019-10-30 | 2021-04-22 | 2022-12-30 | 86%
2022-07-31 | 2016 | Army Reserve | Major Military Construction | Mississippi | United States | 77163 | Army Reserve Center |  |  |  | 2019-11-01 | 2021-06-23 | 2022-09-20 | 73%
2022-07-31 | 2019 | Army Reserve | Major Military Construction | California | United States | 77268 | ECS Modified TEMF/ Warehouse |  |  |  | 2019-03-25 | 2020-11-21 | 2022-07-27 | 96% | 2022-07-20
2022-07-31 | 2019 | Army Reserve | Major Military Construction | Wisconsin | United States | 80690 | Transient Training Barracks |  |  |  | 2019-11-01 | 2021-08-22 | 2022-04-01 | 99% | 2022-04-01
2022-07-31 | 2021 | Army Reserve | Major Military Construction | Wisconsin | United States | 81564 | Scout Reconnaissance Range |  |  |  | 2022-02-16 | 2024-02-16 | 2024-02-16 | 9%
2022-07-31 | 2020 | Army Reserve | Major Military Construction | Wisconsin | United States | 81802 | Transient Training Barracks |  |  |  | 2020-10-28 | 2022-12-17 | 2022-12-17 | 95%
2022-07-31 | 2021 | Army Reserve | Major Military Construction | Florida | United States | 82197 | ECS TEMF / Warehouse |  |  |  | 2022-02-10 | 2024-01-31 | 2024-01-31 | 15%
2022-07-31 | 2016 | Army Reserve | Major Military Construction | Florida | United States | 85813 | AR Center/ AS Facility |  |  |  | 2017-11-03 | 2019-10-04 | 2022-06-01 | 96% | 2022-01-31
2022-07-31 | 2020 | Army Reserve | Major Military Construction | Delaware | United States | 86823 | Army Reserve Center |  |  |  | 2020-05-27 | 2022-03-28 | 2021-11-29 | 100% | 2022-01-11
2022-07-31 | 2022 | Army Reserve | Major Military Construction | Wisconsin | United States | 88554 | Collective Training BDE HQ |  |  |  | 2022-06-24 | 2023-12-16 | 2023-12-16 | 0%
2022-07-31 | 2018 | Army Reserve | Major Military Construction |  | Puerto Rico | 88731 | AR Center Training Building |  |  |  | 2019-06-28 | 2020-12-19 | 2022-05-06 | 98% | 2022-05-06
2022-07-31 | 2021 | Army Reserve | Major Military Construction | Massachusetts | United States | 88752 | Automated Multipurpose Machine Gun Range |  |  |  | 2022-02-18 | 2024-02-28 | 2024-02-28 | 1%
2022-07-31 | 2019 | Army Reserve | Major Military Construction | Washington | United States | 90202 | ECS Modified TEMF |  |  |  | 2020-09-22 | 2022-06-22 | 2022-06-22 | 66% | 2022-06-22
2022-07-31 | 2021 | Army Reserve | Unspecified Minor Military Construction | Texas | United States | 90896 | Rotary-Wing Landing Pad |  |  |  | 2021-09-15 | 2022-09-15 | 2022-09-15 | 8%
2022-07-31 | 2022 | Army Reserve | Unspecified Minor Military Construction | Virginia | United States | 92098 | Army Reserve Vehicle Maintenance Shop |  |  |  | 2022-01-26 | 2023-05-19 | 2023-05-19 | 0%
2022-08-12 | 2017 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14019 | Dental Clinic Replacement |  |  |  | 2018-07-20 | 2020-07-13 | 2021-10-07 | 100% | 2021-08-26
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | California | United States | 14021 | Ambulatory Care Center Replacement (Area 13) |  |  |  | 2020-01-02 | 2022-05-10 | 2022-08-15 | 99% | 2021-10-26
2022-08-12 | 2017 | Defense Health Agency | Major Military Construction |  | Japan | 14022 | TLAMM-P Medical Warehouse |  | 609000 | PN 14041 PN 80412 | 2017-10-26 | 2019-10-26 | 2020-11-30 | 100% | 2020-11-30
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14041 | Ambulatory Care Center/Dental Clinic Replacement (Hadnot Point) |  |  |  | 2019-10-12 | 2021-10-30 | 2022-08-15 | 99% | 2022-01-30
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14042 | Ambulatory Care Center/Dental Clinic Wallace Creek) |  |  |  | 2019-10-12 | 2021-10-30 | 2022-09-30 | 99% | 2022-08-30
2022-08-12 | 2008 | Defense Health Agency | Major Military Construction |  | Germany | 52332 | Medical Clinic Replacement |  |  |  | 2008-08-29 | 2012-05-15 | 2012-07-16 | 100% | 2011-10-08
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 |  |  |  | 2007-10-12 | 2008-06-13 | 2008-06-08 | 100% | 2008-07-23
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-01 |  |  | 2008-08-19 | 2009-02-15 | 2009-02-13 | 100% | 2009-03-03
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-02 |  |  | 2009-10-15 | 2010-04-13 | 2010-04-13 | 100% | 2010-04-13
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-03 |  |  | 2008-12-05 | 2009-07-24 | 2009-07-24 | 100% | 2009-07-24
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-04 |  |  | 2008-07-15 | 2011-05-06 | 2013-10-31 | 100% | 2013-12-06
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-05 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 2 | 63418 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 3 | 63419 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420-01 |  |  | 2008-07-15 | 2013-10-31 | 2016-12-06 | 100% | 2013-12-06
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324-01 |  |  | 2008-07-15 | 2013-10-31 | 2013-12-06 | 100% | 2013-12-06
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 100% | 2017-05-04
2022-08-12 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 100% | 2017-05-04
2022-08-12 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-02 |  |  | 2017-10-26 | 2018-10-26 | 2019-05-11 | 98% | 2019-07-03
2022-08-12 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 8 | 78211 |  |  | 2009-06-01 | 2014-05-31 | 2023-05-25 | 98% | 2023-03-27
2022-08-12 | 2009 | Defense Health Agency | Base Realignment and Closures | Maryland | United States | 64156 | USAMRICD Replacement, Inc 1 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2022-08-12 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2022-08-12 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 | 65731-01 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2022-08-12 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2022-08-12 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-01 |  |  | 2010-10-01 | 2011-09-30 | 2011-09-30 | 100% | 2011-10-01
2022-08-12 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-02 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2022-08-12 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 3 | 67181 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2022-08-12 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 4 | 67182 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2022-08-12 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66588 | Health Clinic Add/Alt |  |  |  | 2013-04-08 | 2016-05-30 | 2017-05-03 | 100% | 2017-05-10
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | Texas | United States | 67402 | Blood Processing Center |  |  |  | 2020-07-02 | 2022-04-03 | 2022-04-03 | 97% | 2022-04-03
2022-08-12 | 2013 | Defense Health Agency | Major Military Construction | South Carolina | United States | 71317 | Medical Clinic Replacement |  | 4898450 | PN 80306 | 2013-12-06 | 2016-12-30 | 2019-02-15 | 100% | 2016-12-02
2022-08-12 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 71325 | Medical Clinic Replacement |  |  |  | 2013-10-24 | 2016-10-23 | 2018-06-01 | 99% | 2018-06-08
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 71408 | Dental Clinic Replacement |  | 312000 | PN 71503 | 2013-03-01 | 2016-12-06 | 2019-02-15 | 100% | 2019-01-03
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic |  | 8300000 | PN 72754 | 2012-09-01 | 2014-09-09 | 2016-01-31 | 100% | 2016-04-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic | 71503-01 |  |  | 2016-08-25 | 2017-12-25 | 2019-05-10 | 100% | 2018-07-31
2022-08-12 | 2017 | Defense Health Agency | Major Military Construction | Maine | United States | 71509 | Medical/Dental Clinic Replacement |  |  |  | 2019-02-01 | 2021-01-24 | 2021-07-14 | 100% | 2021-08-31
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 |  |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 72251 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-01 |  |  | 2011-11-02 | 2013-08-13 | 2013-10-12 | 100% | 2013-10-12
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-02 |  |  | 2011-08-23 | 2012-07-05 | 2012-12-31 | 100% | 2012-12-31
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-03 |  |  | 2012-08-28 | 2013-06-19 | 2013-10-17 | 100% | 2013-10-17
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-04 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-05 |  |  | 2012-09-04 | 2014-01-04 | 2015-09-16 | 100% | 2015-09-16
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-06 |  |  | 2011-08-25 | 2011-11-01 | 2011-11-01 | 100% | 2011-11-01
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 3 | 72786 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-01
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-01 |  |  | 2013-10-21 | 2014-10-24 | 2014-10-24 | 100% | 2014-11-24
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-02 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293-01 |  |  | 2019-07-26 | 2020-10-18 | 2021-12-28 | 100% | 2021-12-28
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407-01 |  |  | 2019-12-04 | 2021-05-04 | 2021-05-04 | 100% | 2021-06-03
2022-08-12 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 7 | 81408 | 2500000 | PN 77000 PN 14040 | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Hospital Replacement, Increment 8 | 91301 | 2000000 | PN 77000 PN 80412 | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2022-08-12 | 2017 | Defense Health Agency | Major Military Construction | Texas | United States | 72738 | Medical/Dental Clinic Replacement |  | 741000 | PN 14040 PN 80412 | 2017-10-26 | 2020-10-31 | 2022-04-01 | 99% | 2022-04-01
2022-08-12 | 2020 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center |  |  |  | 2021-06-10 | 2021-09-26 | 2022-06-30 | 99% | 2022-06-30
2022-08-12 | 2020 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center | 72742-01 |  |  | 2022-01-10 | 2022-06-10 | 2022-08-31 | 95% | 2022-08-31
2022-08-12 | 2020 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center | 72742-02 |  |  | 2022-10-03 | 2023-03-24 | 2023-03-24 | 1% | 2023-03-24
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 2 | 80793 |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2022-08-12 | 2013 | Defense Health Agency | Major Military Construction | California | United States | 72808 | Medical Clinic Replacement |  | 1765000 | PN 80309 PN 72292 | 2014-02-28 | 2015-03-16 | 2017-04-28 | 100% | 2016-06-23
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  | 2016-02-28 | 2016-04-30 | 2017-04-30 | 100% | 2017-02-28
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72661, 72662-02 |  |  | 2018-09-07 | 2021-01-30 | 2022-09-30 | 99% | 2021-12-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 72661-01 |  |  | 2017-07-30 | 2021-03-31 | 2021-12-07 | 99% | 2021-07-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 72662-01 |  |  | 2023-06-30 | 2025-12-30 | 2025-12-30 | 1% | 2025-12-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-01 |  |  | 2014-01-20 | 2014-04-04 | 2014-04-04 | 100% | 2014-04-04
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-02 |  |  | 2014-06-16 | 2014-10-29 | 2015-01-21 | 100% | 2015-01-21
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-03 |  |  | 2015-04-20 | 2016-04-30 | 2017-07-30 | 100% | 2016-12-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-04 |  |  | 2016-06-15 | 2016-12-15 | 2017-12-15 | 100% | 2018-01-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-05 |  |  | 2014-08-22 | 2015-03-30 | 2015-05-01 | 100% | 2015-05-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-06 |  |  | 2014-10-08 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-07 |  |  | 2014-08-11 | 2014-10-16 | 2014-10-16 | 100% | 2014-10-16
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-08 |  |  | 2016-08-15 | 2016-10-30 | 2016-12-30 | 100% | 2016-12-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-09 |  |  | 2016-11-30 | 2020-03-30 | 2020-03-30 | 100% | 2020-03-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1, Incr 6 | 76007-10 |  |  | 2014-12-10 | 2025-12-30 | 2027-10-30 | 11% | 2025-12-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-13 |  |  | 2014-10-23 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 through Incr 8 | 76007-14 |  |  | 2015-03-30 | 2025-12-30 | 2027-10-30 | 2% | 2027-09-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 76007-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-12-30 | 100% | 2018-12-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 6 | 81412 |  |  | 2014-01-13 | 2025-12-30 | 2027-10-30 | 7% | 2025-12-30
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement Incr 2-9 | 95984 |  |  | 2021-12-30 | 2027-12-30 | 2027-12-30 | 1% | 2027-12-30
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | Georgia | United States | 76934 | Blood Donor Center Replacement |  |  |  | 2019-03-12 | 2021-03-14 | 2021-07-12 | 98% | 2021-09-13
2022-08-12 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement |  | 539000 | PN 81436 PN 14022 | 2015-09-08 | 2019-02-19 | 2023-02-01 | 99% | 2021-08-31
2022-08-12 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement Water Storage Tank | 77000-01 |  |  | 2021-12-07 | 2022-12-06 | 2022-12-06 | 1% | 2022-12-06
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 77140 | Blood Processing Center Replacement |  |  |  | 2019-03-26 | 2020-09-16 | 2021-10-29 | 99% | 2021-05-07
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 1 |  | 150000 | PN 71408 | 2013-03-01 | 2016-12-06 | 2022-09-30 | 99% | 2017-06-20
2022-08-12 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 2 | 81291 |  |  | 2013-03-01 | 2016-12-06 | 2022-09-30 | 99% | 2017-06-20
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition |  | 536000 | PN 67402 | 2016-12-14 | 2019-06-04 | 2022-08-26 | 98% | 2022-07-12
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition | 77986-01 |  |  | 2022-08-30 | 2023-07-30 | 2023-07-30 | 1% | 2023-07-30
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition | 77986-02 |  |  | 2023-04-01 | 2023-10-01 | 2023-10-01 | 1% | 2023-10-01
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | Colorado | United States | 77987 | Medical/Dental Clinic Addition/Alteration |  | 2110000 | PN 77140 PN 76934 | 2018-10-23 | 2021-06-17 | 2023-01-30 | 72% | 2021-08-16
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 78150 | Medical Clinic Replacement |  | 41463000 | PN 81430 PN 67402 PN 86557 | 2016-11-14 | 2018-12-21 | 2020-08-31 | 100% | 2020-07-31
2022-08-12 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities |  |  |  | 2013-10-15 | 2013-12-13 | 2014-03-25 | 100% | 2014-04-04
2022-08-12 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities | 80306-01 |  |  | 2018-11-07 | 2017-12-10 | 2018-08-31 | 100% | 2018-11-07
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 |  |  |  | 2016-06-16 | 2017-12-08 | 2019-03-29 | 100% | 2019-04-19
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 | 80412-01 | 2000000 | PN 86953 | 2018-02-28 | 2020-05-21 | 2020-11-20 | 99% | 2021-02-21
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 | 80412-02 |  |  | 2020-10-19 | 2023-02-06 | 2023-02-06 | 97% | 2022-06-01
2022-08-12 | 2017 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 1 |  |  |  | 2017-12-22 | 2019-05-10 | 2021-08-31 | 100% | 2021-03-17
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 2 | 81420 |  |  | 2020-07-01 | 2026-03-01 | 2027-05-13 | 32% | 2027-05-01
2022-08-12 | 2020 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 3 | 85667 |  |  | 2020-07-01 | 2026-03-01 | 2027-05-13 | 32% | 2027-05-01
2022-08-12 | 2020 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 4 | 90417 |  |  | 2020-07-01 | 2026-03-01 | 2027-05-13 | 32% | 2027-05-01
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction | Texas | United States | 81422 | Lackland Ambulatory Care Center Phase 4 |  | 2000000 | PN 78210 | 2018-10-24 | 2021-04-01 | 2023-06-19 | 86% | 2023-08-18
2022-08-12 | 2015 | Defense Health Agency | Major Military Construction | Virginia | United States | 81430 | Hospital Add/CUP Replacement |  |  |  | 2019-06-01 | 2021-03-18 | 2023-01-12 | 88% | 2022-09-12
2022-08-12 | 2014 | Defense Health Agency | Major Military Construction |  | Bahrain | 81436 | Medical/Dental Clinic Replacement |  | 4000000 | PN 80904 PN 78211 | 2016-04-20 | 2019-04-20 | 2020-01-20 | 99% | 2019-12-30
2022-08-12 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | Delaware | United States | 86204 | Armed Forces Medical Examiner Medical Warehouse Addition/Alteration |  |  |  | 2021-01-07 | 2022-02-03 | 2022-05-15 | 98% | 2022-06-14
2022-08-12 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | Colorado | United States | 86943 | NiCOE Satellite, Infrastructure Support |  |  |  | 2019-12-03 | 2021-06-15 | 2021-07-15 | 99% | 2022-02-25
2022-08-12 | 2016 | Defense Health Agency | Major Military Construction | Kentucky | United States | 86953 | Medical Clinic |  | 2000000 | PN 78211 | 2017-04-13 | 2021-06-23 | 2023-01-04 | 94% | 2021-11-16
2022-08-12 | 2018 | Defense Health Agency | Unspecified Minor Military Construction |  | Japan | 87208 | Medical Clinic Addition/Alteration, Building 704 |  |  |  | 2019-05-29 | 2020-08-21 | 2021-01-30 | 100% | 2020-12-15
2022-08-12 | 2019 | Defense Health Agency | Major Military Construction | North Carolina | United States | 89838 | Ambulatory Care CTR/Dental Clinic Replacement |  |  |  | 2019-09-30 | 2021-10-30 | 2023-01-31 | 89% | 2022-10-31
2022-08-12 | 2019 | Defense Health Agency | Major Military Construction |  | Cuba | 89839 | Working Dog Treatment Facility Replacement |  |  |  | 2022-01-11 | 2023-06-02 | 2023-09-07 | 5% | 2023-06-02
2022-08-12 | 2019 | Defense Health Agency | Major Military Construction | South Carolina | United States | 89902 | Consolidated Storage and Distribution Center |  |  |  | 2020-08-18 | 2022-09-03 | 2022-11-15 | 54% | 2022-11-15
2022-08-12 | 2020 | Defense Health Agency | Major Military Construction | California | United States | 89906 | Ambulatory Care Center Replacement (Area 21) |  |  |  | 2020-11-30 | 2022-10-30 | 2022-10-30 | 90% | 2022-10-30
2022-08-12 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 |  |  |  | 2019-10-14 | 2023-10-13 | 2023-10-25 | 67% | 2023-10-13
2022-08-12 | 2021 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 | 77168 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-25 | 67% | 2023-10-13
2022-08-12 | 2020 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 | 94335 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-25 | 67% | 2023-10-13
2022-08-12 | 2022 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 | 97762 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-25 | 67% | 2023-10-13
2022-08-12 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | South Carolina | United States | 93298 | High Altitude Airdrop Mission Support (HAAMS) |  |  |  | 2020-11-30 | 2021-09-10 | 2022-08-15 | 95% | 2022-07-27
2022-08-11 | 2021 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 01DISA21 | FTH - JITC LAB Building |  |  |  | 2021-09-10 | 2023-09-13 | 2023-12-31 | 6%
2022-08-11 | 2013 | Defense Information Systems Agency | Major Military Construction |  | Germany | 13DISA01 | DISA Europe Facility Upgrade |  |  |  | 2015-08-19 | 2016-12-31 | 2022-12-31 | 90%
2022-08-11 | 2014 | Defense Information Systems Agency | Major Military Construction | Hawaii | United States | 14DISA01 | DISA Pacific Facility Upgrade |  |  |  | 2018-01-11 | 2018-12-31 | 2022-08-30 | 99%
2022-08-11 | 2015 | Defense Information Systems Agency | Major Military Construction |  | Australia | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) |  |  |  | 2018-10-01 | 2019-03-31 | 2022-08-30 | 100%
2022-08-11 | 2013 | Defense Information Systems Agency | Major Military Construction | Illinois | United States | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  |  |  | 2014-03-01 | 2015-12-30 | 2016-03-11 | 100%
2022-08-25 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701A | CONSTRUCT WAREHOUSE OPEN STORAGE |  |  |  | 2018-06-26 | 2020-06-18 | 2021-05-24 | 99% | 2021-10-01
2022-08-25 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701B | CONSTRUCT WAREHOUSE |  |  |  | 2018-09-30 | 2020-09-30 | 2020-09-30 | 99% | 2021-10-01
2022-08-25 | 2019 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1901 | General Purpose Warehouse |  |  |  | 2019-07-31 | 2023-01-04 | 2023-01-30 | 90%
2022-08-25 | 2020 | DLA Defense Energy Support Center | Major Military Construction | South Dakota | United States | DECS1913 | Ellsworth Air Force Base Hydrgant Fuel System at Ellsworth AFB |  |  |  | 2020-09-28 | 2022-11-18 | 2022-11-30 | 40%
2022-08-25 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Indiana | United States | DESC1301 | Replace Hydrant Fuel system - Grissom ARB |  |  |  | 2015-09-17 | 2017-04-09 | 2021-04-25 | 100% | 2018-09-25
2022-08-25 | 2017 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC1513 | Replace JP-8 Fuel Storage Tanks, Patrick AFB, FL-Demolition&amp;&#x23;x2f&#x3b;New Construction |  |  |  | 2019-07-15 | 2020-09-15 | 2023-01-03 | 19% | 2021-06-30
2022-08-25 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Germany | DESC1603 | CONSTRUCT FUEL LINE NORTH TO SOUTH SIDE, SPANGDAHLEM AB |  |  |  | 2019-08-10 | 2020-08-10 | 2024-03-02 | 100% | 2020-12-07
2022-08-25 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Delaware | United States | DESC1605 | Construct Hydrant Fuel System, Dover AFB, DE |  |  |  | 2019-07-06 | 2020-01-06 | 2020-05-03 | 100% | 2020-05-23
2022-08-25 | 2018 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1608 | Consolidate Fuel Facilities at Shaw AFB, SC |  |  |  | 2019-06-13 | 2021-03-19 | 2021-03-01 | 99% | 2021-05-01
2022-08-25 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1609 | Ft Belvoir, Replace Ground Fueling Facility |  |  |  | 2019-07-15 | 2021-07-15 | 2021-11-30 | 99% | 2021-12-01
2022-08-25 | 2017 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1611 | REPLACE HYDRANT SYSTEM , Travis AFB |  |  |  | 2017-12-30 | 2020-03-10 | 2021-07-15 | 100% | 2020-07-24
2022-08-25 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Djibouti | DESC1701 | Construct Fuel Storage Facilities, Camp Lemonnie, Djibouti, Horn-of-Africa |  |  |  | 2017-03-13 | 2020-11-30 | 2021-09-24 | 95%
2022-08-25 | 2016 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1702 | CONSTRUCT DISTIBUTION PT. SE RAMP, CANNON AFB |  |  |  | 2017-12-07 | 2019-06-25 | 2019-08-03 | 100% | 2019-07-19
2022-08-25 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Diego Garcia | DESC1705 | IMPROVE WHARF REFUELING CAPABILITY Diego Garcia |  |  |  | 2017-06-30 | 2019-06-29 | 2021-10-24 | 100% | 2020-04-28
2022-08-25 | 2017 | DLA Defense Energy Support Center | Major Military Construction | Alaska | United States | DESC1707 | CONSTRUCT TRUCK OFFLOAD FACILITY |  |  |  | 2017-08-24 | 2018-12-15 | 2019-09-23 | 100% | 2018-12-06
2022-08-25 | 2018 | DLA Defense Energy Support Center | Major Military Construction |  | Guam | DESC1709 | Construct Fuel Truck Offload, Andersen AB |  |  |  | 2018-09-21 | 2019-12-15 | 2021-12-15 | 100% | 2021-07-15
2022-08-25 | 2018 | DLA Defense Energy Support Center | Major Military Construction | Utah | United States | DESC1714 | DESC 1714 Replace POL Pumphouse, Hill AFB |  |  |  | 2019-06-07 | 2021-07-12 | 2022-01-30 | 99% | 2022-01-31
2022-08-25 | 2019 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | California | United States | DESC17U3 | New Fuels lab-Point Loma |  |  |  | 2020-01-20 | 2021-01-15 | 2021-09-15 | 99%
2022-08-25 | 2018 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1805 | FY18 DLA DESC1805 Upgrade Fuel Wharf, Yokose Fuel Terminal, Japan SABO JAPAN |  |  |  | 2019-03-13 | 2021-04-21 | 2022-04-30 | 95%
2022-08-25 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC18S2 | Replace Bulk Diesel System,McAlester Army Ammo Plant |  |  |  | 2019-09-19 | 2021-02-26 | 2022-02-05 | 98% | 2021-10-26
2022-08-25 | 2018 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | Virginia | United States | DESC18U1 | Pier A Rebiuld, Craney Island, VA |  |  |  | 2019-03-13 | 2020-03-13 | 2022-02-28 | 100% | 2020-05-11
2022-08-25 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC1905 | Hot Refuel ReplacementJoint Base Lewis-McChord |  |  |  | 2019-08-19 | 2021-03-31 | 2021-11-16 | 98% | 2021-11-16
2022-08-25 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Ohio | United States | DESC1907 | Replace Hydrant Fueling System, Wright Patterson Air Force Base |  |  |  | 2021-05-06 | 2023-10-23 | 2024-04-20 | 6%
2022-08-25 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1909 | Replace Flight Line Aviation POL Yard, Joint Base Langley-Eustis |  |  |  | 2019-09-30 | 2020-12-31 | 2022-05-05 | 85%
2022-08-25 | 2020 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1912 | Construct Fuels Storage Complex for Air National Guard at Tulsa Airport |  |  |  | 2021-08-04 | 2023-01-31 | 2023-01-31 | 8%
2022-08-25 | 2019 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | Virginia | United States | DESC1914 | Replace Ground Vehicle Fuel Facility, Joint Base Langley-Eustis |  |  |  | 2019-06-17 | 2020-12-31 | 2021-09-30 | 95%
2022-08-25 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Texas | United States | DESC19I1 | Construct Aerospace Facility Joint Base San Antonio |  |  |  | 2019-08-07 | 2020-11-20 | 2022-02-28 | 99%
2022-08-25 | 2019 | DLA Defense Energy Support Center | Major Military Construction |  | Guam | DESC19S2 | Convert Bulk Tanks at Sasa Valley, Guam |  |  |  | 2019-11-04 | 2022-10-10 | 2023-03-03 | 88%
2022-08-25 | 2020 | DLA Defense Energy Support Center | Major Military Construction | Ohio | United States | DESC19S4 | Replace Fuel Facilities, Columbus Air Force Base |  |  |  | 2020-10-16 | 2021-10-15 | 2022-02-22 | 90%
2022-08-25 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC2002 | Bulk Fuel Storage Tanks Phase 1, Manchester, WA. |  |  |  | 2022-01-03 | 2024-01-20 | 2024-01-21 | 35%
2022-08-25 | 2020 | DLA Defense Energy Support Center | Major Military Construction | Rhode Island | United States | DESC20S1 | Replace Fuels Storage Complex, Warwick, Ri |  |  |  | 2021-05-25 | 2023-08-23 | 2023-05-25 | 5%
2022-08-25 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC2104A | Construct Retail Fuel Facilities &#x28;Lewis North&#x29;,Joint Base Lewis-McChord |  |  |  | 2022-03-01 | 2023-10-23 | 2024-04-20 | 15%
2022-08-25 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC2104B | Joint Base Lewis-McChord, Construct Retail Fuel Facilities |  |  |  | 2022-02-01 | 2023-05-16 | 2023-05-16 | 15%
2022-08-25 | 2015 | DLA Defense National Stockpile Center | Major Military Construction | Maryland | United States | DESC1507 | Construct Hydrant Fuel System Andrews AFB MD |  |  |  | 2016-10-31 | 2018-02-07 | 2019-11-13 | 100% | 2019-11-13
2022-08-25 | 2015 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1501 | Replace Access Control Point, Richmond |  |  |  | 2018-02-23 | 2019-08-12 | 2021-05-31 | 100% | 2021-06-01
2022-08-25 | 2020 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1901 | Replace DLA Avation Phase II Richmond,VA |  |  |  | 2021-01-28 | 2020-12-11 | 2024-03-05 | 30%
2022-08-01 | 2014 | DoD Education Activity | Major Military Construction | Virginia | United States | AM00021 | REPLACE QUANTICO MIDDLE/HIGH SCHOOL |  |  |  | 2017-12-04 | 2020-01-09 | 2020-10-13 | 51%
2022-08-01 | 2019 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00029 | Fort Campbell Middle School |  |  |  | 2021-02-01 | 2023-09-09 | 2023-11-15 | 20%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction | New York | United States | AM00033 | USMA - REPLACE WEST POINT ELEMENTARY SCHOOL (PN AM00033) |  |  |  | 2017-03-21 | 2020-03-05 | 2021-04-23 | 99% | 2020-01-06
2022-08-01 | 2014 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00046 | Design and Construct new Primary School at Hanscom | 246 |  |  | 2017-03-23 | 2019-09-09 | 2019-10-16 | 99% | 2019-08-16
2022-08-01 | 2017 | DoD Education Activity | Major Military Construction | Delaware | United States | AM00047 | AM00047 FY17 WELCH ES - DOVER AIR BASE MS AT DOVER AFB |  |  |  | 2019-03-30 | 2021-10-15 | 2022-04-29 | 44%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School |  | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2021-02-09 | 100%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 8 | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2021-02-09 | 100%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 9 |  |  | 2016-10-20 | 2020-06-10 | 2021-02-09 | 100%
2022-08-01 | 2015 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00051 | Lejeune High School Addition/Renovation |  |  |  | 2017-04-12 | 2020-03-28 | 2021-04-09 | 100%
2022-08-01 | 2015 | DoD Education Activity | Major Military Construction |  | United States | AM00103 | Consolidate/Replace W.T. Sampson Elementary School |  |  |  | 2016-07-01 | 2018-11-26 | 2021-10-09 | 100%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00110 | Replace/Renovate Maxwell ES/MS |  |  |  | 2017-04-12 | 2020-05-28 | 2022-09-01 | 92%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00110 | Replace/Renovate Maxwell ES/MS | 27 |  |  | 2017-04-12 | 2020-05-28 | 2022-09-01 | 92%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction |  | Spain | AM00115 | Rota Elementary and High School Additions |  |  |  | 2016-07-20 | 2019-03-27 | 2021-04-21 | 97%
2022-08-01 | 2021 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00182 | Replace Van Voorhis Elementary School |  |  |  | 2021-08-30 | 2025-09-28 | 2025-10-21 | 16%
2022-08-01 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School |  |  |  | 2017-01-09 | 2019-05-08 | 2019-07-01 | 97% | 2019-10-31
2022-08-01 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School | 89 |  |  | 2017-01-09 | 2019-05-08 | 2019-07-01 | 97% | 2019-10-31
2022-08-01 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School |  |  |  | 2016-09-12 | 2018-12-24 | 2019-03-15 | 99% | 2019-08-22
2022-08-01 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School | 45 |  |  | 2016-09-12 | 2018-12-24 | 2019-03-15 | 100% | 2019-08-22
2022-08-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 1 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 98% | 2021-05-12
2022-08-01 | 2017 | DoD Education Activity | Major Military Construction |  | Germany | EU00039 | Replace Sembach Middle/High School |  |  |  | 2019-07-08 | 2019-12-15 | 2019-12-15 | 10% | 2020-04-29
2022-08-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement |  |  |  | 2017-06-30 | 2020-01-12 | 2020-06-28 | 98% | 2021-03-26
2022-08-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00049 | Replace Hainerberg Elementary School |  |  |  | 2018-07-09 | 2021-07-23 | 2021-07-23 | 95% | 2021-04-23
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00051 | FY16 DoDEA-E EU00051 Replace Patch Elementary School | 51 |  |  | 2019-01-23 | 2021-01-23 | 2021-03-25 | 84%
2022-08-01 | 2015 | DoD Education Activity | Major Military Construction |  | Belgium | EU00064 | Replace Brussels Elementary/ High School |  |  |  | 2017-10-25 | 2020-10-24 | 2020-10-24 | 43%
2022-08-01 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00068 | Replace Grafenwoehr |  |  |  | 2018-09-12 | 2021-03-16 | 2021-06-08 | 90%
2022-08-01 | 2018 | DoD Education Activity | Major Military Construction |  | Italy | EU00117 | Vicenza High School Replacement |  |  |  | 2019-09-27 | 2022-01-27 | 2022-12-16 | 48%
2022-08-01 | 2017 | DoD Education Activity | Major Military Construction |  | Germany | EU00183 | Vilseck High School Field House |  |  |  | 2020-08-03 | 2021-04-29 | 2021-07-17 | 75% | 2022-04-20
2022-08-01 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00017 | Killin Elementary School Replacement/Renovation |  |  |  | 2017-01-11 | 2020-11-17 | 2022-11-23 | 90%
2022-08-01 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00022 | E.J King HS Addition/ Renovate |  |  |  | 2019-08-21 | 2022-08-05 | 2021-12-31 | 100% | 2021-09-10
2022-08-01 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00023 | FY15 DODS PA00023 Renovate Edgren High School, Misawa Air Base, Japan |  |  |  | 2017-02-07 | 2019-05-28 | 2020-01-24 | 98%
2022-08-01 | 2017 | DoD Education Activity | Major Military Construction |  | Japan | PA00032 | Replace Kadena ES |  |  |  | 2018-04-02 | 2021-02-15 | 2022-04-04 | 99%
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146130F | MOTOR TRANSPORTATION/COMM SHOP REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 17% | 2025-12-10
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146142F | FIRE STATIONS REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 16% | 2025-12-10
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146162F | PMO/H&HS & MWHS-2 HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 19% | 2025-12-10
2022-08-15 | 2015 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146193 | WATER TREATMENT PLANT REPLACEMENT |  |  |  | 2017-01-05 | 2020-02-28 | 2022-03-23 | 100% | 2022-02-08
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146194 | UNMANNED AIRCRAFT SYSTEM FACILITIES |  |  |  | 2016-09-14 | 2018-10-04 | 2019-01-29 | 100% | 2020-01-30
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146197 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2022-05-10 | 2025-06-24 | 2025-06-24 | 1% | 2025-06-25
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146199 | AIRCRAFT MAINTENANCE HANGAR - INC 1 |  |  |  | 2020-01-06 | 2022-07-14 | 2023-03-20 | 87% | 2022-11-29
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146222 | AIRFIELD SECURITY IMPROVEMENTS |  |  |  | 2019-05-02 | 2021-06-10 | 2021-06-10 | 90% | 2021-10-08
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146235 | FLIGHTLINE UTILITY MODERNIZATION - INC 1 |  |  |  | 2020-01-06 | 2022-07-14 | 2023-03-20 | 86% | 2022-11-29
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146246F | BT-11 RANGE OPERATIONS CENTER REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 1% | 2025-12-10
2022-08-15 | 2020 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M00146249 | MCAS CHERRY POINT PERIMETER SECURITY: SLOCUM/NUGENT |  |  |  | 2021-03-04 | 2022-03-05 | 2022-08-11 | 29% | 2022-08-09
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146254F | STATION ACADEMIC FACILITY/AUDITORIUM REPLACE |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 17% | 2025-12-10
2022-08-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M00146766 | F-35B LIFT SYSTEM REPAIR FACILITY |  |  |  | 2018-10-13 | 2020-01-08 | 2021-04-12 | 97% | 2021-04-01
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146990 | F-35B VERTICAL LIFT FAN TEST FACILITY |  |  |  | 2021-06-10 | 2023-05-01 | 2023-05-10 | 39% | 2023-05-10
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M00243312 | PMO FACILITY REPLACEMENT |  |  |  | 2022-02-03 | 2022-02-03 | 2022-08-22 | 1% | 2022-08-22
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263403 | RECRUIT RECONDITIONING CENTER & BARRACKS |  |  |  | 2018-08-14 | 2021-02-28 | 2022-03-18 | 80% | 2022-02-18
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263404 | RANGE IMPROVEMENTS & MODERNIZATION, PHASE 2 |  |  |  | 2019-07-24 | 2021-08-17 | 2022-03-23 | 82% | 2022-05-26
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264542 | TBS FIRE STATION BUILDING 533 REPLACEMENT |  |  |  | 2019-06-13 | 2020-10-30 | 2022-08-30 | 57% | 2022-09-15
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264588 | FULLER ROAD IMPROVEMENTS |  |  |  | 2018-10-13 | 2020-06-06 | 2021-04-09 | 100% | 2021-05-12
2022-08-15 | 2015 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264635 | AMMUNITION SUPPLY POINT EXPANSION |  |  |  | 2016-11-30 | 2018-03-25 | 2021-07-29 | 99% | 2021-07-27
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264677 | TECOM SCHOOLS ACADEMIC INSTRUCTION FACILITY |  |  |  | 2016-04-14 | 2018-01-05 | 2018-10-23 | 100% | 2019-12-02
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264719 | WARGAMING CENTER |  |  |  | 2021-04-05 | 2023-07-05 | 2023-07-05 | 1% | 2023-07-05
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264724 | AMMUNITION SUPPLY POINT UPGRADE, PHASE 2 |  |  |  | 2019-08-29 | 2021-01-30 | 2021-07-01 | 100% | 2021-07-01
2022-08-15 | 2020 | Marine Corps Active | Unspecified Minor Military Construction | Virginia | United States | M00264733 | RUNWAY 02 INSTRUMENT LANDING SYSTEM (ILS) |  |  |  | 2020-10-13 | 2021-11-10 | 2022-04-12 | 22% | 2022-08-01
2022-08-15 | 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318861 | FACILITY MODIFICATIONS FOR VMU, MWSD AND CH53E |  |  |  | 2015-09-15 | 2018-08-11 | 2021-02-03 | 99% | 2021-02-03
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318863 | AIRCRAFT MAINTENANCE HANGAR UPGRADES |  |  |  | 2016-10-03 | 2019-04-17 | 2020-03-07 | 100% | 2022-09-28
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318877 | MOKAPU GATE ENTRY CONTROL AT/FP COMPLIANCE |  |  |  | 2020-10-07 | 2022-01-07 | 2022-02-11 | 36% | 2022-07-01
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  |  |  | 2014-10-14 | 2016-12-18 | 2019-10-24 | 96% | 2019-10-28
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318887 | LHD PAD CONVERSIONS MV-22 LANDING PADS |  |  |  | 2019-01-11 | 2020-08-19 | 2021-01-25 | 100% | 2021-03-17
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318902 | AIRFIELD LIGHTING MODERNIZATION |  |  |  | 2016-12-02 | 2019-06-06 | 2021-08-13 | 98% | 2021-07-16
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  |  |  | 2015-04-28 | 2017-01-03 | 2021-12-20 | 100% | 2018-06-20
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318908 | MV-22 HANGAR |  |  |  | 2015-04-28 | 2017-01-03 | 2021-12-20 | 94% | 2018-06-20
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318923 | REGIMENTAL CONSOLIDATED COMM/ELEC FACILITY |  |  |  | 2017-09-04 | 2020-03-08 | 2022-05-21 | 100% | 2021-05-21
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318946 | CORROSION CONTROL HANGAR |  |  |  | 2019-06-14 | 2021-09-07 | 2022-08-27 | 83% | 2022-08-27
2022-08-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | M00318947 | MARINE CORPS TRAINING AREA BELLOWS PERIMETER SECURITY FENCE |  |  |  | 2022-04-08 | 2023-04-24 | 2023-04-24 | 1% | 2023-04-24
2022-08-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | M00318964 | RAPPEL TOWER TRAINING FACILITY |  |  |  | 2022-02-01 | 2023-04-19 | 2023-04-19 | 1% | 2023-06-19
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681079 | POTABLE WATER DISTRIBUTION IMPROVEMENTS |  |  |  | 2019-12-26 | 2022-05-30 | 2022-05-30 | 100% | 2022-11-01
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M006811090 | 1 MEF CONSOLIDATED INFORMATION CENTER |  |  |  | 2020-10-08 | 2024-01-07 | 2024-01-07 | 1% | 2024-01-07
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction | California | United States | M006811090A | 1 MEF CONSOLIDATED INFORMATION CENTER (INC) |  |  |  | 2021-04-06 | 2024-01-07 | 2024-01-07 | 1% | 2024-01-07
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction | California | United States | M006811130 | 1ST MARDIV OPERATIONS COMPLEX |  |  |  | 2021-03-04 | 2023-05-13 | 2023-05-22 | 1% | 2023-08-10
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M006811310 | AMMUNITION SUPPLY POINT UPGRADE |  |  |  | 2018-10-11 | 2020-10-10 | 2022-01-15 | 55% | 2023-06-01
2022-08-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M006811599 | STUART MESA ROAD SAFETY IMPROVEMENT |  |  |  | 2019-03-13 | 2020-02-26 | 2020-04-16 | 96% | 2020-04-16
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006811901 | AAV-ACV MAINTENANCE & WAREHOUSE FACILITY |  |  |  | 2019-05-16 | 2022-06-09 | 2022-12-09 | 64% | 2022-12-09
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M006812000 | 62 AREA MESS HALL AND CONSOLIDATED WAREHOUSE |  |  |  | 2020-12-31 | 2025-02-14 | 2025-02-14 | 1% | 2025-02-14
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681334 | SUPPLY WAREHOUSE SOI - WEST |  |  |  | 2019-09-05 | 2021-08-06 | 2021-10-13 | 100% | 2022-01-26
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006815001 | FULL MOTION TRAINER FACILITY |  |  |  | 2019-04-23 | 2020-10-15 | 2022-01-12 | 91% | 2022-01-12
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006815002 | ELECTRICAL UPGRADES |  |  |  | 2019-04-08 | 2020-03-30 | 2020-03-20 | 100% | 2020-03-19
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681574 | FIRE EMERGENCY RESPONSE STATION |  |  |  | 2019-09-05 | 2021-06-07 | 2021-12-10 | 85% | 2021-12-10
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | California | United States | M00681970 | AMMUNITION SUPPLY POINT FACILITIES PULGAS |  |  |  | 2016-01-13 | 2018-04-27 | 2020-11-27 | 100% | 2022-12-30
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169464 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2017-07-13 | 2020-07-13 | 2022-07-08 | 95% | 2022-06-29
2022-08-15 | 2022 | Marine Corps Active | Unspecified Minor Military Construction | South Carolina | United States | M60169492 | INSTRUMENT LANDING SYSTEM
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M62204930 | COMBAT VEHICLE REPAIR FACILITY |  |  |  | 2018-05-02 | 2020-05-02 | 2020-05-17 | 100% | 2020-09-22
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction |  | Japan | M626131005 | VTOL PAD - SOUTH
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction |  | Japan | M626131006 | KC130J ENLISTED AIRCREW TRAINER FACILITY
2022-08-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction |  | Japan | M626131010U | SEAWALL ACCESS |  |  |  | 2021-09-23 | 2022-07-06 | 2022-11-30 | 1% | 2022-11-30
2022-08-15 | 2017 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131701 | WHOLEHOUSE REVITALIZATION NORTH SIDE TOWNHOUSES PHASE 2
2022-08-15 | 2020 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626132001 | WHOLEHOUSE REVITALIZATION MIDRISE 1209 |  |  |  | 2021-02-25 | 2023-07-02 | 2023-07-02 | 7% | 2023-07-02
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M62613604 | SECURITY MODIFICATIONS - CVW5/MAG12 HQ
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974539 | ENLISTED DINING FACILITY & COMMUNITY BLDGS |  |  |  | 2018-07-17 | 2021-07-02 | 2022-04-04 | 93% | 2022-06-17
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974602 | AIRCRAFT MAINT. FACILITIES & APRON (SO. CALA) |  |  |  | 2017-08-10 | 2019-06-30 | 2020-06-22 | 100% | 2020-06-18
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974612 | VMX-22 MAINTENANCE HANGAR |  |  |  | 2019-06-27 | 2022-06-06 | 2023-05-17 | 73% | 2023-05-17
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011043 | WATER TREATMENT PLANT REPLACEMENT HADNOT PT
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011199F | CLB HEADQUARTERS FACILITIES REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 11% | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011203F | COURTHOUSE BAY FIRE STATION REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011280 | 2ND RADIO BN COMPLEX PHASE 1 |  |  |  | 2017-06-13 | 2019-06-24 | 2022-12-06 | 82% | 2022-12-06
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011300F | 2D TANK BN/CO HQ AND ARMORY REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 11% | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011312F | MCES APPLIED INSTRUCTION FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011320 | BACHELOR ENLISTED QUARTERS |  |  |  | 2018-10-12 | 2020-10-23 | 2021-11-05 | 77% | 2022-11-23
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011338F | II MEF SIMULATION/TRAINING CENTER REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-11-27 | 1% | 2026-01-22
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011387F | ONSLOW BEACH BRIDGE REPLACEMENT |  |  |  | 2020-08-07 | 2025-03-06 | 2025-03-06 | 26% | 2025-03-06
2022-08-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011479 | OUTDOOR INFANTRY IMMERSION TRAINER SITE PREP |  |  |  | 2019-06-28 | 2020-10-26 | 2021-09-30 | 100% | 2021-09-30
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011483 | ACV-AAV MAINTENANCE FACILITY UPGRADES |  |  |  | 2020-10-09 | 2021-09-28 | 2022-06-22 | 1% | 2022-06-22
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011495 | 10TH MARINES HIMARS COMPLEX |  |  |  | 2020-08-27 | 2023-03-05 | 2023-03-19 | 1% | 2023-03-19
2022-08-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011498 | WC504 MECHANICAL SYSTEM REPLACEMENT |  |  |  | 2018-11-28 | 2019-11-09 | 2022-07-29 | 100% | 2022-09-15
2022-08-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011503 | WC500 MECHANICAL SYSTEM REPLACEMENT |  |  |  | 2018-11-28 | 2019-11-09 | 2022-05-31 | 100% | 2022-07-29
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011505F | RAILROAD TRESTLE REPLACEMENT |  |  |  | 2020-08-07 | 2025-03-06 | 2025-03-06 | 15% | 2025-03-06
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011506F | NCIS FACILITIES REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011507F | WTBN HEADQUARTERS REPLACEMENT |  |  |  | 2020-09-29 | 2024-05-27 | 2025-01-07 | 1% | 2025-01-07
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011509F | 2D MARDIV REGIMENTAL HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 16% | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011512F | MCCSSS LOG OPS SCHOOL REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-11-27 | 1% | 2026-01-22
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011518F | HADNOT POINT FIRE STATION REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011519F | LSSS FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011520F | 1ST BN, 8TH MARINES BN HQ REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 11% | 2025-01-27
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011522F | 22D, 24TH, AND 26TH MEU HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 20% | 2025-01-27
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011524F | 2D TRANSPORTATION SUPPORT BN HQS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 12% | 2025-01-27
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011525F | ENVIRONMENTAL MANAGEMENT DIVISION REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 12% | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011527F | LOGCOM CSP WAREHOUSE REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-11-27 | 1% | 2026-01-22
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011529F | MC ADVISOR BATTALION HQS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2025-01-27 | 1% | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011533F | PMO FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011604F | OPEN MESS HALL REPAIR |  |  |  | 2022-06-14 | 2023-11-22 | 2023-11-22 | 1% | 2023-11-22
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800 | II MEF OPERATIONS CENTER REPLACEMENT |  |  |  | 2021-01-05 | 2026-07-23 | 2027-05-09 | 1% | 2026-03-20
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800A | II MEF OPERATIONS CENTER REPLACEMENT (INC) |  |  |  | 2021-03-16 | 2026-07-23 | 2027-05-09 | 1% | 2026-03-20
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800B | II MEF OPERATIONS CENTER REPLACEMENT (INC)
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011801 | 2ND MARDIV/2ND MLG OPS CENTER REPLACEMENT |  |  |  | 2021-01-05 | 2026-07-23 | 2027-05-09 | 1% | 2026-03-20
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001378F | CH-53K MAINTENANCE HANGAR REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2026-09-30 | 1% | 2026-09-30
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001686 | RADAR AIR TRAFFIC CONTROL FACILITY ADDITION |  |  |  | 2016-10-12 | 2018-04-06 | 2021-04-22 | 96% | 2021-03-30
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001695F | CNATT CLASSROOM BUILDING REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2026-09-30 | 1% | 2026-09-30
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001707F | BACHELOR ENLISTED QUARTERS REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2026-09-30 | 1% | 2026-09-30
2022-08-15 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001726 | REGIONAL COMMUNICATION STATION |  |  |  | 2014-06-13 | 2015-12-20 | 2019-02-01 | 98% | 2018-05-31
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001728F | C-12W AIRCRAFT MAINTENANCE HANGAR REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2026-09-30 | 1% | 2026-09-30
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001729 | OPERATIONAL TRAINER FACILITY |  |  |  | 2016-10-12 | 2018-04-06 | 2021-04-22 | 100% | 2021-03-30
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001883F | HADNOT POINT MESS HALL REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004947 | WELDING AND BODY REPAIR SHOP FACILITY |  |  |  | 2020-02-14 | 2022-05-04 | 2022-07-27 | 41% | 2022-07-27
2022-08-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | Georgia | United States | M67004971 | CONSTRUCT LOGCOM OPEN STORAGE LOT |  |  |  | 2018-03-29 | 2018-11-06 | 2019-07-05 | 100% | 2019-07-10
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004972 | GROUND SOURCE HEAT PUMPS |  |  |  | 2017-04-05 | 2019-01-28 | 2019-02-23 | 99% | 2022-06-30
2022-08-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | Georgia | United States | M67004976 | GATE 15 MOCK ROAD ENTRY CONTROL POINT |  |  |  | 2022-04-05 | 2023-07-15 | 2023-07-15 | 1% | 2023-07-15
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004977 | COMBAT VEHICLE WAREHOUSE |  |  |  | 2019-03-21 | 2021-04-29 | 2021-05-27 | 98% | 2021-03-02
2022-08-15 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | District Of Columbia | United States | M67029007 | Communications Center for Marine Barracks, Washington, DC |  |  |  | 2017-05-03 | 2018-04-19 | 2020-07-30 | 100% | 2019-12-23
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | California | United States | M673991232 | MICROGRID EXPANSION |  |  |  | 2017-10-10 | 2019-04-19 | 2021-04-23 | 100% | 2021-04-23
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67399192 | POTABLE WATER TREATMENT/BLENDING FACILITY |  |  |  | 2018-10-13 | 2021-09-28 | 2023-02-15 | 89% | 2022-10-31
2022-08-15 | 2015 | Marine Corps Active | Major Military Construction | California | United States | M67399222 | E-LMR SLICE COMMUNICATION TOWERS |  |  |  | 2016-09-14 | 2019-03-04 | 2020-02-14 | 100% | 2020-02-06
2022-08-15 | 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400213 | HANGAR & RINSE FACILITY MODERNIZATIONS
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M67400606 | MILITARY WORKING DOG FACILITIES (CAMP HANSEN) |  |  |  | 2016-09-29 | 2018-03-26 | 2021-11-19 | 100% | 2019-09-03
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction |  | Japan | M67400807 | AIRCRAFT MAINTENANCE COMPLEX
2022-08-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction |  | Japan | M67400901U | FORCE PROTECTION UPGRADES CVI GATE 4 CAMP FUJI |  |  |  | 2021-07-15 | 2022-03-14 | 2022-03-14 | 12% | 2022-07-29
2022-08-15 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M67604132 | ORDNANCE BULD-UP FACILITY |  |  |  | 2016-09-14 | 2017-10-30 | 2017-10-30 | 100% | 2017-12-18
2022-08-15 | 2020 | Marine Corps Active | Major Military Construction | Florida | United States | M67695009 | POLICE STATION AND EOC FACILITY REPLACEMENT |  |  |  | 2020-09-30 | 2022-03-25 | 2022-09-21 | 1% | 2022-12-16
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR - INC 1 |  |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 96% | 2020-06-26
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR - INC 2 | M67865198A |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 100% | 2020-06-26
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865203 | F-35 F-35 Aircraft Parking Apron |  |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 100% | 2020-06-26
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67865210 | F-35 SIMULATOR FACILITY |  |  |  | 2018-09-13 | 2020-05-20 | 2021-02-26 | 100% | 2021-01-20
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M67865222 | F-35 VERTICAL LANDING PADS AND TAXIWAY |  |  |  | 2019-03-28 | 2020-09-27 | 2021-02-06 | 100% | 2020-07-28
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M67865238 | AIRFIELD SECURITY IMPROVEMENTS |  |  |  | 2019-03-22 | 2020-04-06 | 2020-04-06 | 48% | 2019-11-25
2022-08-15 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865249 | COMMUNICATIONS COMPLEX & INFRASTRUCTURE UPGRADE |  |  |  | 2018-01-01 | 2019-09-24 | 2020-10-01 | 98% | 2020-08-19
2022-08-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M67865280 | ENTRY CONTROL POINT IMPROVEMENTS |  |  |  | 2021-07-14 | 2023-03-07 | 2023-07-14 | 17% | 2023-07-14
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557270 | ACE GYM & DINING |  |  |  | 2019-09-26 | 2022-03-25 | 2022-07-18 | 53% | 2022-10-07
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N41557280 | AVIATION ADMIN BUILDING |  |  |  | 2022-05-18 | 2024-08-22 | 2024-08-22 | 1% | 2024-08-22
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction |  | Guam | N41557290 | EARTH COVERED MAGAZINES |  |  |  | 2022-01-25 | 2025-01-10 | 2025-01-10 | 31% | 2025-01-28
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557295 | ORDNANCE OPS |  |  |  | 2019-09-30 | 2021-12-04 | 2021-12-04 | 77% | 2022-01-31
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557296 | ORDNANCE OPERATIONS ADMIN |  |  |  | 2021-03-31 | 2023-03-28 | 2023-08-06 | 1% | 2023-08-06
2022-08-15 | 2018 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557601 | AIRCRAFT MAINTENANCE HANGAR #2 |  |  |  | 2018-05-30 | 2020-10-02 | 2021-10-22 | 100% | 2022-03-15
2022-08-15 | 2016 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557715 | LIVE-FIRE TRAINING RANGE COMPLEX (NW FIELD) |  |  |  | 2017-09-07 | 2020-11-26 | 2023-01-08 | 81% | 2022-06-30
2022-08-15 | 2019 | Marine Corps Active | Major Military Construction |  | Guam | N41557735 | MACHINE GUN RANGE - INC 1 |  |  |  | 2021-10-12 | 2024-10-25 | 2024-10-25 | 1% | 2024-10-25
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159305 | 4TH MARINES REGIMENT FACILITIES |  |  |  | 2022-05-18 | 2024-08-22 | 2024-08-22 | 1% | 2024-08-22
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159306 | COMBAT LOGISTICS BATALLION-4 FACILITY |  |  |  | 2022-05-18 | 2024-09-06 | 2024-09-06 | 1% | 2024-09-06
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159307 | CONSOLIDATED ARMORY |  |  |  | 2022-04-28 | 2024-08-02 | 2024-08-02 | 1% | 2024-08-02
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159310 | INFANTRY BATTALION COMPANY HQ |  |  |  | 2022-05-11 | 2024-08-18 | 2024-08-18 | 1% | 2024-08-18
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159311 | CENTRAL FUEL STATION |  |  |  | 2021-03-29 | 2023-08-23 | 2023-08-23 | 1% | 2023-08-23
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159312 | DISTRIBUTION WAREHOUSE
2022-08-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159326 | PRINCIPAL END ITEM (PEI) WAREHOUSE |  |  |  | 2022-04-15 | 2024-07-25 | 2024-07-25 | 1% | 2024-07-25
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction |  | Guam | N61159802 | BASE WAREHOUSE |  |  |  | 2021-08-30 | 2023-12-07 | 2023-12-07 | 1% | 2023-12-07
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction |  | Guam | N61159803 | INDIVIDUAL COMBAT SKILLS TRAINING |  |  |  | 2021-08-27 | 2022-08-27 | 2022-09-04 | 1% | 2022-09-04
2022-08-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159804 | CENTRAL ISSUE FACILITY |  |  |  | 2021-04-05 | 2024-03-12 | 2024-03-12 | 1% | 2024-03-12
2022-08-15 | 2019 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | N62813216 | ELECTRICAL DISTRIBUTION INTERCONNECT |  |  |  | 2020-02-17 | 2020-12-29 | 2022-09-30 | 47% | 2022-09-30
2022-08-15 | 2018 | Marine Corps Reserve | Major Military Construction | Louisiana | United States | M67861650 | AIRCRAFT APRON, TAXIWAY & SUPPORT FACILITIES |  |  |  | 2019-04-02 | 2020-11-20 | 2020-11-20 | 100% | 2020-11-20
2022-08-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Louisiana | United States | M68479102 | MARINE CORPS RESERVE CENTER, BROOKLYN NY POV PARKING
2022-08-15 | 2017 | Marine Corps Reserve | Major Military Construction | Louisiana | United States | M68479135 | ELECTRIC FEEDER DUCTBANK |  |  |  | 2019-02-05 | 2020-01-28 | 2020-10-31 | 95% | 2020-11-04
2022-08-15 | 2021 | Marine Corps Reserve | Major Military Construction | Maryland | United States | M68479303 | RESERVE TRAINING CENTER, CAMP FRETTERD, MD |  |  |  | 2022-02-16 | 2024-09-17 | 2024-09-17 | 1% | 2024-09-17
2022-08-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Louisiana | United States | M68479811 | MCRC BROOKLYN FIRE PROTECTION SYSTEM AND ACCESS GATES
2022-08-15 | 2016 | Marine Corps Reserve | Major Military Construction | Virginia | United States | N50092152 | RESERVE TRAINING CENTER COMPLEX |  |  |  | 2019-10-14 | 2021-09-14 | 2022-02-04 | 86% | 2022-02-04
2022-08-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447091 | HANGAR 1050 ADDITION VMGR-234 PROP SHOP
2022-08-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447181 | HEADQUARTERS BUILDING ADDITION |  |  |  | 2020-10-09 | 2021-09-26 | 2021-09-26 | 1% | 2023-08-16
2022-08-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447222 | OVERHEAD COVER AT MARINE CORPS RESERVE CENTER, EL PASO |  |  |  | 2020-10-08 | 2021-09-21 | 2021-09-21 | 1% | 2022-01-12
2022-07-31 | 2013 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  |  |  | 2013-07-31 | 2015-08-30 | 2016-05-12 | 99% | 2017-04-13
2022-07-31 | 2014 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #2 | 646 |  |  | 2013-07-31 | 2015-08-30 | 2016-05-12 | 99% | 2017-04-13
2022-07-31 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  | 164000 | 657 | 2014-07-07 | 2016-01-06 | 2016-01-06 | 100% | 2016-01-06
2022-07-31 | 2016 | Missile Defense Agency | Major Military Construction |  | Poland | 640 | Aegis Ashore Missile Defense System Complex |  |  |  | 2016-03-14 | 2018-05-30 | 2023-01-26 | 95%
2022-07-31 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 653 | MDC Switchgear Facility |  | 379000 | 657 | 2017-08-31 | 2019-08-14 | 2021-09-29 | 94%
2022-07-31 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 657 | Long Range Discrimination Radar Complex, Phase 1 |  |  |  | 2017-06-05 | 2020-11-27 | 2020-09-29 | 100%
2022-07-31 | 2019 | Missile Defense Agency | Major Military Construction | Alaska | United States | 659 | Long Range Discrimination Radar Complex, Phase 2 |  |  |  | 2019-04-29 | 2021-06-30 | 2022-07-28 | 100%
2022-07-31 | 2017 | Missile Defense Agency | Unspecified Minor Military Construction |  | Israel | 673 | Integrated Electronic Security System (IESS) Installation & Security Infrastructure Upgrades |  |  |  | 2018-08-15 | 2019-05-31 | 2022-08-15 | 99%
2022-07-31 | 2018 | Missile Defense Agency | Major Military Construction | Alaska | United States | 674 | Missile Field #4 |  |  |  | 2018-04-25 | 2021-09-30 | 2022-11-30 | 92%
2022-07-31 | 2019 | Missile Defense Agency | Major Military Construction | Alaska | United States | 679 | Missile Field #1 Expansion |  |  |  | 2022-05-06 | 2023-10-21 | 2023-10-21 | 0%
2022-07-31 | 2021 | Missile Defense Agency | Major Military Construction | Alaska | United States | 680 | Communications Center |  |  |  | 2021-06-01 | 2023-01-31 | 2023-01-31 | 35%
2022-07-31 | 2021 | Missile Defense Agency | Unspecified Minor Military Construction |  | Turkey | 689 | Integrated Electronic Security System Installation and Security Infrastructure Upgrades |  |  |  | 2022-09-25 | 2023-10-01 | 2023-12-22 | 0%
2022-07-06 | 2021 | National Geospatial-Intelligence Agency | Unspecified Minor Military Construction | Missouri | United States | ARN13-0020 | NGA Arnold ACP |  |  |  | 2021-11-17 | 2023-11-17 | 2023-11-17 | 21%
2022-07-31 | 2018 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016A | Next NGA West (N2W) Complex, Ph. 1 |  |  |  | 2019-04-23 | 2023-10-19 | 2024-06-28 | 61%
2022-07-31 | 2018 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016A-IPO | IPO Temporary Facility associated with Next NGA West (N2W) Complex, Ph. 1 |  |  |  | 2019-07-10 | 2024-07-08 | 2024-07-08 | 67%
2022-07-31 | 2019 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016B | Next NGA West (N2W) Complex, Ph. 2 |  |  |  | 2019-04-23 | 2023-10-19 | 2024-06-28 | 56%
2022-07-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 30583 | East Campus Building 2 (ECB2) |  |  |  | 2016-07-18 | 2020-09-10 | 2022-02-23 | 99% | 2022-08-15
2022-07-31 | 2019 | National Security Agency | Major Military Construction | Maryland | United States | 32100 | Mission Support Operations Warehouse Facility |  |  |  | 2020-02-27 | 2022-11-17 | 2022-11-17 | 73% | 2022-11-17
2022-07-31 | 2022 | National Security Agency | Major Military Construction |  | United Kingdom | 34490 | RAF Menwith Hill Main Gate Rehabilitation |  |  |  | 2022-06-06 | 2023-05-24 | 2023-05-24 | 0%
2022-07-31 | 2017 | National Security Agency | Major Military Construction | Maryland | United States | 35161 | Access Control Facility |  |  |  | 2021-09-20 | 2024-03-28 | 2024-03-28 | 0%
2022-07-31 | 2019 | National Security Agency | Major Military Construction | Maryland | United States | 35168 | NSAW Recapitalization Building 3 |  |  |  | 2019-05-01 | 2023-04-30 | 2023-05-09 | 64% | 2023-05-09
2022-07-31 | 2022 | National Security Agency | Major Military Construction | Maryland | United States | 38440/38441 | Mission Operations and Records Center |  |  |  | 2022-06-23 | 2026-06-15 | 2026-06-15 | 0%
2022-07-31 | 2022 | National Security Agency | Major Military Construction | Maryland | United States | 38608 | NSAW Recapitalization Building 4 |  |  |  | 2022-05-11 | 2026-05-10 | 2026-05-10 | 0%
2022-08-15 | 2016 | Navy Active | Major Military Construction | California | United States | M006811220 | RAW WATER PIPELINE PENDLETON TO FALLBROOK |  |  |  | 2016-12-14 | 2019-03-30 | 2019-03-30 | 100% | 2019-10-02
2022-08-15 | 2016 | Navy Active | Major Military Construction |  | Japan | M62613603 | E-2D OPERATIONAL TRAINER COMPLEX |  |  |  | 2019-01-01 | 2020-07-08 | 2021-03-12 | 1% | 2021-03-12
2022-08-15 | 2014 | Navy Active | Major Military Construction | Illinois | United States | N00128714 | UNACCOMPANIED HOUSING |  |  |  | 2018-08-13 | 2020-08-14 | 2020-10-23 | 100% | 2020-10-23
2022-08-15 | 2017 | Navy Active | Major Military Construction | Illinois | United States | N00128714 | UNACCOMPANIED HOUSING | N00128714A |  |  | 2018-08-13 | 2020-08-14 | 2020-10-23 | 100% | 2020-10-23
2022-08-15 | 2020 | Navy Active | Major Military Construction | Connecticut | United States | N00129898 | SSN BERTHING PIER 32 |  |  |  | 2020-10-13 | 2022-10-26 | 2023-01-31 | 1% | 2023-01-31
2022-08-15 | 2016 | Navy Active | Major Military Construction | Florida | United States | N00204723 | A-SCHOOL UNACCOMPANIED HOUSING (CORRY STATION) |  |  |  | 2017-07-12 | 2019-10-16 | 2020-09-20 | 100% | 2021-02-10
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N00207674 | AIRCRAFT COMPONENT FACILITY |  |  |  | 2019-05-31 | 2020-10-13 | 2021-05-20 | 100% | 2021-04-30
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N00207711 | SECURITY FENCE - AGUADA BOUNDARY |  |  |  | 2019-09-27 | 2020-09-14 | 2020-09-14 | 100% | 2020-09-14
2022-08-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213211 | REPLACE AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2021-05-27 | 2023-12-29 | 2023-12-29 | 13% | 2023-12-29
2022-08-15 | 2021 | Navy Active | Major Military Construction | Florida | United States | N00213211A | REPLACE AIRCRAFT MAINTENANCE HANGAR (CTC)
2022-08-15 | 2014 | Navy Active | Major Military Construction | Florida | United States | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  |  |  | 2014-08-29 | 2016-02-08 | 2018-01-08 | 100% | 2017-07-28
2022-08-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N00213720 | AUTEC AUSTERE QUARTERS |  |  |  | 2019-10-10 | 2021-12-13 | 2023-06-29 | 19% | 2023-06-29
2022-08-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213731 | FIRE STATION |  |  |  | 2019-10-03 | 2020-11-30 | 2021-12-23 | 64% | 2022-10-15
2022-08-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213741 | NAVY GATEWAY INN & SUITES (NGIS) FACILITY |  |  |  | 2019-10-11 | 2022-01-17 | 2022-10-28 | 60% | 2022-10-28
2022-08-15 | 2018 | Navy Active | Major Military Construction | Texas | United States | N00216450 | CONSOLIDATED SQUADRON OPERATIONS & FLIGHT TRAINING BUILDING |  |  |  | 2018-09-19 | 2021-09-04 | 2022-07-08 | 41% | 2023-01-31
2022-08-15 | 2018 | Navy Active | Major Military Construction | Texas | United States | N00216485 | HAZARDOUS WASTE STORAGE AND TRANSFER FACILITY |  |  |  | 2018-09-05 | 2020-03-14 | 2021-01-30 | 95% | 2021-02-26
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N002450888 | HARBOR DRIVE SWITCHING STATION |  |  |  | 2019-04-11 | 2021-08-18 | 2022-10-06 | 80% | 2022-10-06
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N00245110 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2019-08-26 | 2021-03-23 | 2021-03-23 | 98% | 2021-05-31
2022-08-15 | 2017 | Navy Active | Major Military Construction | California | United States | N00245312 | UPGRADE PIER 10 TO 4160 VOLT |  |  |  | 2017-07-13 | 2018-09-30 | 2018-12-15 | 100% | 2018-12-12
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N00245440 | PIER 8 REPLACEMENT - INC 1 |  |  |  | 2019-06-28 | 2021-10-27 | 2021-10-31 | 100% | 2021-06-17
2022-08-15 | 2021 | Navy Active | Major Military Construction | California | United States | N00245443 | PIER 6 REPLACEMENT |  |  |  | 2021-05-14 | 2023-09-17 | 2023-09-17 | 1% | 2023-09-20
2022-08-15 | 2015 | Navy Active | Major Military Construction | California | United States | N00245800 | STEAM DISTRIBUTION SYSTEM DECENTRALIZATION |  |  |  | 2015-10-01 | 2017-10-01 | 2019-04-10 | 100% | 2019-04-10
2022-08-15 | 2017 | Navy Active | Unspecified Minor Military Construction | California | United States | N002461017 | Upgrades for MV-22 Depot Maintenance Program |  |  |  | 2017-10-12 | 2018-12-12 | 2018-12-12 | 100% | 2018-12-06
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N002461018 | CMV-22B AIRFIELD IMPROVEMENTS |  |  |  | 2019-08-08 | 2022-07-25 | 2022-07-25 | 64% | 2023-04-28
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N002461024 | NAVY V-22 HANGAR |  |  |  | 2020-06-25 | 2023-01-01 | 2023-03-03 | 1% | 2023-06-30
2022-08-15 | 2021 | Navy Active | Unspecified Minor Military Construction | California | United States | N00246762 | COMBAT AIRCRAFT LOADING AREA |  |  |  | 2021-11-18 | 2022-11-03 | 2022-11-03 | 1% | 2022-11-03
2022-08-15 | 2017 | Navy Active | Major Military Construction | California | United States | N00246947 | COASTAL CAMPUS ENTRY CONTROL POINT |  |  |  | 2017-04-13 | 2018-10-06 | 2020-03-31 | 100% | 2021-08-27
2022-08-15 | 2018 | Navy Active | Major Military Construction | California | United States | N00246988 | UNDERSEA RESCUE COMMAND OPERATIONS BUILDING |  |  |  | 2018-09-13 | 2021-03-22 | 2022-03-12 | 92% | 2022-10-05
2022-08-15 | 2017 | Navy Active | Major Military Construction | California | United States | N00246991 | COASTAL CAMPUS UTILITIES INFRASTRUCTURE |  | 4715000 | N32414547, M62613604 | 2017-04-13 | 2019-04-23 | 2021-04-30 | 100% | 2021-06-09
2022-08-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N00620240 | TRITON MISSION CONTROL FACILITY |  |  |  | 2017-08-23 | 2020-03-26 | 2021-01-19 | 100% | 2020-07-16
2022-08-15 | 2019 | Navy Active | Major Military Construction | Washington | United States | N00620253 | FLEET SUPPORT FACILITY |  |  |  | 2019-03-25 | 2020-11-28 | 2021-07-06 | 100% | 2021-06-01
2022-08-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N00620256 | E/A-18G MAINTENANCE HANGAR |  |  |  | 2019-02-13 | 2021-07-19 | 2021-10-29 | 96% | 2021-08-18
2022-08-15 | 2019 | Navy Active | Major Military Construction | Washington | United States | N00620258 | NEXT GENERATION JAMMER FACILITY |  |  |  | 2019-03-12 | 2021-03-08 | 2021-01-29 | 99% | 2021-01-29
2022-08-15 | 2019 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414106 | SUBMARINE PROPULSOR MANUFACTURING SUPPORT FAC |  |  |  | 2019-06-26 | 2022-02-13 | 2022-11-25 | 41% | 2022-12-30
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Pennsylvania | United States | N324141098 | SUBMARINE PROPULSOR MACHINE SHOP STAGING FACILITY |  |  |  | 2019-06-26 | 2022-02-13 | 2022-11-23 | 97% | 2022-11-28
2022-08-15 | 2015 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  |  |  | 2015-06-01 | 2017-01-12 | 2021-11-19 | 99% | 2022-07-27
2022-08-15 | 2019 | Navy Active | Major Military Construction | Virginia | United States | N32443256 | SHIPS MAINTENANCE FACILITY |  |  |  | 2021-12-13 | 2024-01-28 | 2024-01-28 | 1% | 2024-01-28
2022-08-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N32443257 | SHIP REPAIR TRAINING FACILITY |  |  |  | 2018-10-01 | 2021-06-18 | 2022-03-30 | 87% | 2022-06-24
2022-08-15 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATERFRONT UTILITIES |  |  |  | 2017-12-29 | 2021-04-15 | 2021-06-30 | 100% | 2021-06-30
2022-08-15 | 2017 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATER FRONT UTILITIES | N32443614A |  |  | 2017-12-29 | 2021-04-15 | 2021-06-30 | 100% | 2021-06-30
2022-08-15 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N32443653 | DRY DOCK FLOOD PROTECTION IMPROVEMENTS |  |  |  | 2020-09-18 | 2023-06-17 | 2023-07-13 | 1% | 2022-10-31
2022-08-15 | 2019 | Navy Active | Major Military Construction | Maine | United States | N324461074 | EXTEND PORTAL CRANE RAIL |  |  |  | 2019-12-05 | 2021-01-27 | 2022-04-15 | 69% | 2022-05-06
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Maine | United States | N324461088 | ENTRY CONTROL POINT MODERNIZATION |  |  |  | 2019-08-19 | 2020-10-31 | 2021-07-30 | 100% | 2021-07-30
2022-08-15 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446285 | UNACCOMPANIED HOUSING |  |  |  | 2017-07-13 | 2019-05-10 | 2021-01-21 | 100% | 2020-03-31
2022-08-15 | 2018 | Navy Active | Major Military Construction | Maine | United States | N32446293 | PAINT, BLAST AND RUBBER FACILITY |  |  |  | 2019-10-09 | 2022-08-09 | 2022-08-09 | 48% | 2023-06-15
2022-08-15 | 2014 | Navy Active | Major Military Construction | Maine | United States | N32446308 | NCTAMS VLF COMMERCIAL POWER CONNECTION |  | 1104000 | N68436993 | 2016-05-05 | 2018-10-25 | 2018-10-25 | 99% | 2018-10-25
2022-08-15 | 2019 | Navy Active | Major Military Construction | Maine | United States | N32446310 | DRY DOCK #1 SUPERFLOOD BASIN |  |  |  | 2019-12-05 | 2021-01-27 | 2022-04-15 | 83% | 2022-05-06
2022-08-15 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446371 | UTILITY IMPROVEMENTS FOR NUCLEAR PLATFORMS |  |  |  | 2018-04-13 | 2021-09-14 | 2021-09-14 | 100% | 2021-07-12
2022-08-15 | 2021 | Navy Active | Major Military Construction | Virginia | United States | N32446381 | MULTI-MISSION DRY DOCK #1 EXTENSION (INC) |  |  |  | 2021-08-27 | 2028-06-01 | 2028-06-01 | 1% | 2028-06-01
2022-08-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Maine | United States | N32446385 | COMMUNICATIONS ANTENNA |  |  |  | 2018-10-04 | 2019-10-08 | 2019-10-08 | 100% | 2019-10-15
2022-08-15 | 2017 | Navy Active | Major Military Construction |  | Djibouti | N3379A223 | OCO: MEDICAL/DENTAL FACILITY |  |  |  | 2018-07-12 | 2020-10-05 | 2022-07-31 | 95% | 2023-03-26
2022-08-15 | 2018 | Navy Active | Major Military Construction |  | Djibouti | N3379A505 | AIRCRAFT PARKING APRON EXPANSION |  |  |  | 2018-11-09 | 2020-06-18 | 2021-11-30 | 100% | 2022-07-31
2022-08-15 | 2021 | Navy Active | Major Military Construction | California | United States | N360423271 | F-35C SIMULATOR FACILITY & ELECTRICAL UPGRADES |  |  |  | 2021-04-08 | 2023-05-03 | 2023-10-16 | 61% | 2023-10-16
2022-08-15 | 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557230 | GSE SHOPS AT NORTH RAMP |  |  |  | 2015-12-01 | 2018-06-19 | 2019-01-29 | 100% | 2019-01-28
2022-08-15 | 2018 | Navy Active | Major Military Construction |  | Japan | N41557250 | MALS FACILITIES |  |  |  | 2018-10-08 | 2021-01-21 | 2021-07-27 | 97% | 2022-10-06
2022-08-15 | 2018 | Navy Active | Major Military Construction | Guam | Guam | N41557260 | CORROSION CONTROL HANGAR |  |  |  | 2018-10-05 | 2020-12-28 | 2021-07-27 | 87% | 2022-10-06
2022-08-15 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N41557635 | MUNICIPAL SOLID WASTE LANDFILL CLOSURE |  |  |  | 2017-08-15 | 2019-02-22 | 2022-01-09 | 100% | 2022-11-30
2022-08-15 | 2020 | Navy Active | Major Military Construction |  | Guam | N41557735A | MACHINE GUN RANGE (INC) |  |  |  | 2021-10-12 | 2024-10-25 | 2024-10-25 | 1% | 2024-10-25
2022-08-15 | 2017 | Navy Active | Major Military Construction | Guam | Guam | N41557H279 | REPLACE ANDERSEN HOUSING PH I |  |  |  | 2019-10-03 | 2022-07-05 | 2023-03-13 | 54% | 2023-03-13
2022-08-15 | 2018 | Navy Active | Major Military Construction | Guam | Guam | N41557H280 | REPLACE ANDERSEN HOUSING PH II |  |  |  | 2019-10-03 | 2022-07-05 | 2023-03-13 | 35% | 2023-03-13
2022-08-15 | 2019 | Navy Active | Major Military Construction | Guam | Guam | N41557H282 | REPLACE ANDERSEN HOUSING PH III |  |  |  | 2019-10-03 | 2022-07-05 | 2023-03-13 | 28% | 2023-03-13
2022-08-15 | 2015 | Navy Active | Major Military Construction | South Carolina | United States | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  |  |  | 2014-09-03 | 2018-06-20 | 2019-03-27 | 96% | 2020-05-13
2022-08-15 | 2017 | Navy Active | Unspecified Minor Military Construction | Georgia | United States | N42237671 | SUBMARINE BRIDGE TRAINER |  |  |  | 2018-01-30 | 2019-08-23 | 2019-11-22 | 100% | 2020-02-12
2022-08-15 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N47608265 | UCLASS RDT&E HANGAR |  |  |  | 2019-02-13 | 2020-09-28 | 2022-05-22 | 100% | 2022-11-30
2022-08-15 | 2017 | Navy Active | Unspecified Minor Military Construction | Maryland | United States | N47608421 | Inert Storage Building Replacement |  |  |  | 2017-10-11 | 2018-10-24 | 2020-06-16 | 100% | 2020-08-14
2022-08-15 | 2016 | Navy Active | Major Military Construction | Maryland | United States | N47608975 | UNACCOMPANIED HOUSING |  |  |  | 2018-04-27 | 2020-02-02 | 2020-07-23 | 100% | 2020-07-23
2022-08-15 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N47608975 | UNACCOMPANIED HOUSING | N47608975A |  |  | 2018-04-27 | 2020-02-02 | 2020-12-29 | 100% | 2020-12-29
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091900 | HANGAR 3 REPLACEMENT, APRON, TAXIWAY & UTILITIES FOR RDT&E |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091901 | INTEGRATION LABORATORY |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091902 | AIR OPERATIONS FACILITY & AIR TRAFFIC CONTROL TOWER |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091903 | MICHELSON MISSION SYSTEMS INTEGRATION LABORATORY |  |  |  | 2020-10-01 | 2022-11-04 | 2022-11-04 | 1% | 2022-11-04
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091904 | MICHELSON LABORATORY COMPLEX |  |  |  | 2021-07-09 | 2025-08-29 | 2025-08-29 | 1% | 2025-08-29
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091907 | AIRCRAFT PARKING APRON IN SUPPORT OF HANGAR 2 REPLACEMENT |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091908 | ADVANCED WARFARE HANGAR
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091911 | RANGE CONTROL COMPLEX |  |  |  | 2021-07-08 | 2024-01-22 | 2024-01-22 | 1% | 2024-01-22
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091914 | STRUCTUAL/AIRCRAFT FIRE AND RESCUE STATION |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091916 | COMMUNITY SUPPORT FACILITIES |  |  |  | 2020-09-17 | 2022-09-19 | 2022-09-19 | 1% | 2022-09-19
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091917 | CAST PROPELLANT MIX BUILDING
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091918 | ORDANCE TEST SUPPORT AND TECHNICAL SERVICES LABORATORY |  |  |  | 2021-03-17 | 2023-05-03 | 2023-05-03 | 1% | 2023-05-03
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091919 | RADIOGRAPHIC BUILDING |  |  |  | 2021-06-03 | 2024-02-05 | 2024-02-05 | 1% | 2024-02-05
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091920 | WARHEAD CASING OPERATIONS
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091921 | MOTOR ASSEMBLY COMPOUND
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091922 | SKYTOP FIRING BAYS |  |  |  | 2021-06-24 | 2024-01-23 | 2024-01-23 | 1% | 2024-01-23
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091924 | ACADEMIC TRAINING BUILDING |  |  |  | 2021-02-05 | 2023-02-06 | 2023-02-06 | 1% | 2023-02-06
2022-08-15 | 2020 | Navy Active | Major Military Construction | California | United States | N47609810 | RUNWAY & TAXIWAY EXTENSION |  |  |  | 2020-07-10 | 2022-04-10 | 2022-08-20 | 92% | 2022-12-16
2022-08-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N50092176 | ACU-4 ELECTRICAL UPGRADES |  |  |  | 2018-05-03 | 2019-07-08 | 2019-08-05 | 100% | 2019-05-02
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N60042117 | MISSLE MOTOR MAGAZINES AND U&SI
2022-08-15 | 2020 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N601911026 | AIR INTELLIGENCE SUPPORT FACILITY |  |  |  | 2020-12-25 | 2022-06-10 | 2022-12-06 | 1% | 2022-12-06
2022-08-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N60191160 | ISR OPERATIONS FACILITY EXPAN |  |  |  | 2020-02-28 | 2022-03-01 | 2022-08-24 | 1% | 2022-08-24
2022-08-15 | 2014 | Navy Active | Major Military Construction | Virginia | United States | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  |  |  | 2014-09-30 | 2016-10-25 | 2021-02-12 | 87% | 2021-02-05
2022-08-15 | 2017 | Navy Active | Major Military Construction | Florida | United States | N60201154 | TRITON FORWARD OPERATING BASE HANGAR |  |  |  | 2017-07-13 | 2019-09-26 | 2019-12-27 | 100% | 2019-12-05
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60201195 | HEAVY WEATHER MOORINGS AT BRAVO WHARF |  |  |  | 2019-08-30 | 2020-08-29 | 2021-03-31 | 100% | 2020-07-27
2022-08-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N60201421 | MISSILE MAGAZINES |  |  |  | 2018-08-17 | 2020-08-04 | 2022-06-25 | 34% | 2022-07-25
2022-08-15 | 2016 | Navy Active | Major Military Construction | Florida | United States | N60201424 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2016-07-28 | 2018-02-05 | 2019-02-05 | 100% | 2019-08-06
2022-08-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60201426 | LCS SUPPORT FACILITY |  |  |  | 2019-09-27 | 2021-04-02 | 2022-06-27 | 83% | 2022-06-27
2022-08-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60201427 | LCS OPERATIONAL TRAINING FACILITY ADDITION |  |  |  | 2019-03-08 | 2021-02-05 | 2021-06-04 | 100% | 2021-04-09
2022-08-15 | 2016 | Navy Active | Major Military Construction | Nevada | United States | N60495111 | NAVOPSPTCEN FALLON |  |  |  | 2017-08-31 | 2019-03-11 | 2020-07-18 | 100% | 2021-02-12
2022-08-15 | 2014 | Navy Active | Major Military Construction | Nevada | United States | N60495393 | WASTEWATER TREATMENT PLANT |  |  |  | 2018-05-03 | 2020-05-08 | 2020-11-30 | 100% | 2020-08-31
2022-08-15 | 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495420 | AIR WING TRAINING FACILITY |  |  |  | 2015-09-30 | 2017-11-24 | 2019-10-31 | 98% | 2020-05-19
2022-08-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Nevada | United States | N60495426 | SECURITY FENCE TO ENCLAVE AIRFIELD |  |  |  | 2019-01-11 | 2019-10-25 | 2019-10-25 | 100% | 2020-05-06
2022-08-15 | 2017 | Navy Active | Major Military Construction | Nevada | United States | N60495440 | AIR WING SIMULATOR FACILITY |  |  |  | 2018-08-20 | 2020-08-25 | 2020-10-17 | 100% | 2020-12-01
2022-08-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60508253 | AIR TRAFFIC CONTROL TOWER (NORTH FIELD) |  |  |  | 2021-05-26 | 2024-05-11 | 2024-05-11 | 8% | 2024-05-11
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60508288 | AHTS TEMPORARY MAINTENANCE HANGAR FOUNDATION |  |  |  | 2020-01-24 | 2021-01-11 | 2023-03-30 | 37% | 2022-03-15
2022-08-15 | 2019 | Navy Active | Major Military Construction |  | Cuba | N60514160 | SOLID WASTE MANAGEMENT FACILITY |  |  |  | 2019-10-03 | 2022-03-18 | 2022-05-26 | 54% | 2022-10-27
2022-08-15 | 2019 | Navy Active | Major Military Construction |  | Cuba | N60514343 | CONSOLIDATED FIRE STATION |  |  |  | 2019-10-04 | 2021-09-20 | 2022-10-01 | 68% | 2022-10-01
2022-08-15 | 2014 | Navy Active | Major Military Construction |  | Japan | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  |  |  | 2014-10-03 | 2020-01-23 | 2020-02-23 | 100% | 2020-02-23
2022-08-15 | 2021 | Navy Active | Military Family Housing Improvement |  | Japan | N610542101 | WHOLE HOUSE REVITALIZATION, IKEGO TOWNHOUSE PH2 |  |  |  | 2021-03-19 | 2024-05-01 | 2024-05-01 | 1% | 2024-05-01
2022-08-15 | 2019 | Navy Active | Major Military Construction |  | Japan | N61056512 | TACTICAL OPERATIONS CENTER |  |  |  | 2019-05-03 | 2020-12-31 | 2020-12-31 | 1% | 2021-01-29
2022-08-15 | 2017 | Navy Active | Major Military Construction | Hawaii | United States | N61064402 | UPGRADE POWER PLANT & ELECTRICAL DIST SYS |  |  |  | 2019-01-09 | 2021-07-13 | 2021-12-27 | 92% | 2021-12-22
2022-08-15 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | N61064416 | PMRF POWER GRID CONSOLIDATION |  |  |  | 2018-09-20 | 2020-05-28 | 2022-06-17 | 100% | 2022-04-05
2022-08-15 | 2014 | Navy Active | Major Military Construction | California | United States | N61065202 | NOSC MORENO VALLEY RESERVE TRAINING CENTER |  |  |  | 2016-09-12 | 2018-06-10 | 2019-12-11 | 100% | 2019-12-11
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N61065224 | CAUSEWAY, BOAT CHANNEL & TURNING BASIN |  |  |  | 2019-07-29 | 2022-10-27 | 2024-06-18 | 55% | 2024-03-18
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N61065241 | MISSILE MAGAZINES |  |  |  | 2019-09-02 | 2021-04-15 | 2021-04-26 | 100% | 2021-08-30
2022-08-15 | 2021 | Navy Active | Major Military Construction | California | United States | N61065243 | MISSILE MAGAZINES |  |  |  | 2021-08-26 | 2023-08-27 | 2023-08-27 | 1% | 2023-08-27
2022-08-15 | 2022 | Navy Active | Major Military Construction | California | United States | N61065243A | MISSILE MAGAZINES (INC)
2022-08-15 | 2018 | Navy Active | Major Military Construction | Washington | United States | N61066604 | MISSILE MAGAZINES
2022-08-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N61151163 | AGILE CHEMICAL FACILITY PHASE 3/GAP B |  |  |  | 2018-10-13 | 2021-08-14 | 2021-08-14 | 100% | 2021-08-09
2022-08-15 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX, PHASE 2 |  |  |  | 2017-05-11 | 2019-09-06 | 2023-04-09 | 33% | 2023-10-31
2022-08-15 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX PH 2 | N61151190A |  |  | 2017-05-11 | 2019-09-06 | 2023-04-09 | 9% | 2023-10-31
2022-08-15 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151287 | MISSILE SUPPORT FACILITY |  |  |  | 2015-09-16 | 2017-07-17 | 2019-10-31 | 100% | 2019-10-26
2022-08-15 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61152621 | CYBER SECURITY STUDIES BUILDING |  |  |  | 2016-04-14 | 2019-09-08 | 2020-05-22 | 100% | 2020-09-04
2022-08-15 | 2020 | Navy Active | Major Military Construction | Guam | Guam | N61755491 | EOD COMPOUND FACILITIES |  |  |  | 2020-08-21 | 2022-12-20 | 2022-12-20 | 1% | 2023-03-03
2022-08-15 | 2022 | Navy Active | Major Military Construction |  | Guam | N61755519 | X-RAY WHARF BERTH 2
2022-08-15 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N61755535 | SANITARY SEWER SYSTEM RECAPITALIZATION |  |  |  | 2017-09-04 | 2020-01-03 | 2020-09-10 | 100% | 2022-07-29
2022-08-15 | 2019 | Navy Active | Major Military Construction | Guam | Guam | N61755640 | UNACCOMPANIED ENLISTED HOUSING |  |  |  | 2019-07-09 | 2022-10-07 | 2022-11-04 | 53% | 2023-12-04
2022-08-15 | 2017 | Navy Active | Major Military Construction | Guam | Guam | N61755652 | HARDENING OF GUAM POL INFRASTRUCTURE |  |  |  | 2018-06-06 | 2020-04-03 | 2021-08-15 | 62% | 2022-07-21
2022-08-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Guam | Guam | N61755680 | HARDEN ELECTRICAL CIRCUIT |  |  |  | 2018-10-12 | 2019-09-27 | 2021-05-26 | 87% | 2021-01-07
2022-08-15 | 2018 | Navy Active | Major Military Construction |  | Guam | N61766661 | NAVY-COMMERCIAL TIE-IN HARDENING |  |  |  | 2022-05-05 | 2024-07-10 | 2024-07-10 | 1% | 2024-08-02
2022-08-15 | 2017 | Navy Active | Major Military Construction |  | Italy | N62588307 | ERI: P-8A HANGAR UPGRADE |  |  |  | 2019-01-03 | 2021-02-09 | 2022-02-18 | 82% | 2021-11-16
2022-08-15 | 2017 | Navy Active | Major Military Construction |  | Italy | N62588308 | ERI: P-8A AIRCRAFT RINSE RACK |  |  |  | 2019-01-03 | 2021-02-09 | 2022-02-18 | 96% | 2021-11-16
2022-08-15 | 2019 | Navy Active | Major Military Construction |  | Italy | N62588312 | EDI: P-8 BASE IMPROVEMENTS
2022-08-15 | 2019 | Navy Active | Major Military Construction | Mississippi | United States | N62604855 | EXPEDITIONARY COMBAT SKILLS STUDENT BERTHING |  |  |  | 2019-05-29 | 2022-06-30 | 2022-06-30 | 78% | 2022-06-29
2022-08-15 | 2022 | Navy Active | Major Military Construction | Virginia | United States | N62688095 | SUBMARINE PIER 3 INC.
2022-08-15 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N626881035 | MH60 CORROSION CONTROL AND PAINT FACILITY |  |  |  | 2021-09-03 | 2024-03-22 | 2024-03-22 | 1% | 2024-07-01
2022-08-15 | 2021 | Navy Active | Major Military Construction | Virginia | United States | N626881035A | MH60 & CMV-22B CORROSION CNTRL & PAINT FAC |  |  |  | 2021-09-03 | 2024-03-22 | 2024-03-22 | 1% | 2024-05-01
2022-08-15 | 2021 | Navy Active | Major Military Construction | Virginia | United States | N62688404 | E-2D TRAINING FACILITY |  |  |  | 2021-09-23 | 2019-11-30 | 2023-06-20 | 1% | 2023-09-01
2022-08-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N62688495 | CHAMBERS FIELD MAGAZINE RECAP PH 1 |  |  |  | 2018-10-12 | 2021-02-04 | 2023-05-26 | 47% | 2023-05-26
2022-08-15 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688610 | ELECTRICAL REPAIRS TO PIERS 2,6,7, AND 11 |  |  |  | 2017-09-14 | 2019-10-25 | 2020-12-30 | 100% | 2020-12-22
2022-08-15 | 2017 | Navy Active | Major Military Construction | Virginia | United States | N62688610 | ELECTRICAL REPAIRS TO PIERS 2,6,7, AND 11 | N62688610A |  |  | 2017-09-14 | 2019-10-25 | 2020-12-30 | 100% | 2020-12-22
2022-08-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N62688762 | SUBMARINE UMM ANTENNA MAINTENANCE TOWER |  |  |  | 2018-05-16 | 2019-07-17 | 2021-01-03 | 99% | 2021-01-26
2022-08-15 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688913 | COMMUNICATIONS CENTER |  |  |  | 2018-05-07 | 2020-11-01 | 2022-03-16 | 100% | 2022-09-23
2022-08-15 | 2018 | Navy Active | Major Military Construction | Hawaii | United States | N62813013 | COMMUNICATIONS/CRYPTO FAC (WAHIAWA) |  |  |  | 2019-08-09 | 2021-04-26 | 2021-09-25 | 100% | 2024-04-24
2022-08-15 | 2020 | Navy Active | Major Military Construction | Hawaii | United States | N62813033 | MAGAZINE CONSOLIDATION, PHASE 1 |  |  |  | 2020-08-24 | 2022-09-09 | 2022-09-09 | 1% | 2023-07-05
2022-08-15 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | N62813036 | WELDING SCHOOL SHOP CONSOLIDATION |  |  |  | 2016-02-09 | 2018-03-26 | 2021-07-06 | 99% | 2021-06-25
2022-08-15 | 2021 | Navy Active | Major Military Construction | Hawaii | United States | N62813044 | WATERFRONT IMPROVEMENTS WHARVES S8-S10 |  |  |  | 2021-05-14 | 2023-11-12 | 2023-11-12 | 1% | 2023-11-12
2022-08-15 | 2014 | Navy Active | Unspecified Minor Military Construction | Hawaii | United States | N62813058 | ROCKFALL PROTECTION AT RED HILL |  |  |  | 2014-12-08 | 2016-05-18 | 2019-12-31 | 100% | 2019-11-06
2022-08-15 | 2021 | Navy Active | Major Military Construction | Hawaii | United States | N628131006 | WATERFRONT WHARVES S1, S11-13, S20-21 |  |  |  | 2021-05-14 | 2023-11-12 | 2023-11-12 | 1% | 2023-11-12
2022-08-15 | 2019 | Navy Active | Major Military Construction | Hawaii | United States | N62813169 | WATER TRANSMISSION LINE |  |  |  | 2019-04-12 | 2022-01-24 | 2022-08-03 | 64% | 2023-08-31
2022-08-15 | 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  |  |  | 2014-07-14 | 2017-08-03 | 2020-10-06 | 100% | 2020-09-01
2022-08-15 | 2018 | Navy Active | Major Military Construction | Hawaii | United States | N62813704 | SEWER LIFT STATION & RELIEF SEWER LINE |  |  |  | 2019-03-26 | 2021-06-19 | 2021-07-21 | 100% | 2021-07-21
2022-08-15 | 2020 | Navy Active | Major Military Construction |  | Italy | N628632001 | W/H REVITALIZATION - LAS PALMERAS PH V
2022-08-15 | 2021 | Navy Active | Major Military Construction |  | Italy | N62863313 | MH-60R SQUADRON SUPPORT FACILITIES |  |  |  | 2021-12-30 | 2024-09-09 | 2024-09-09 | 1% | 2024-09-09
2022-08-15 | 2020 | Navy Active | Major Military Construction |  | Spain | N62863605 | SEAMANSHIP TRAINING FACILITY |  |  |  | 2021-04-06 | 2023-01-17 | 2023-01-17 | 89% | 2023-01-17
2022-08-15 | 2021 | Navy Active | Major Military Construction |  | Italy | N62863620 | EDI: EXPEDITIONARY MAINTENANCE FACILITY |  |  |  | 2022-01-04 | 2024-07-01 | 2024-07-01 | 1% | 2024-07-01
2022-08-15 | 2017 | Navy Active | Major Military Construction |  | Spain | N62863621 | COMMUNICATION STATION |  |  |  | 2017-09-14 | 2023-02-13 | 2023-01-08 | 96% | 2021-11-01
2022-08-15 | 2015 | Navy Active | Major Military Construction |  | Spain | N62863712 | SHIP BERTHING POWER UPGRADES |  |  |  | 2015-12-04 | 2018-05-23 | 2022-12-27 | 96% | 2023-02-16
2022-08-15 | 2020 | Navy Active | Major Military Construction |  | Italy | N62863785 | EDI: SMALL CRAFT BERTHING FACILITY |  |  |  | 2022-01-04 | 2023-12-31 | 2023-12-31 | 1% | 2023-12-31
2022-08-15 | 2019 | Navy Active | Major Military Construction |  | Italy | N62863811 | EDI: PORT OPERATION FACILITIES |  |  |  | 2021-09-13 | 2024-04-16 | 2024-04-16 | 1% | 2024-06-18
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction |  | Spain | N62863812 | PROVIDE SHIP TO SHORE ELECTRICAL SUBSTATIONS AT PIER #1 |  |  |  | 2020-10-07 | 2022-06-30 | 2022-06-30 | 1% | 2022-07-05
2022-08-15 | 2020 | Navy Active | Major Military Construction |  | Italy | N62995130 | COMMUNICATIONS STATION |  |  |  | 2020-10-13 | 2025-06-05 | 2026-02-06 | 1% | 2026-02-06
2022-08-15 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995407 | TRITON HANGAR AND OPERATION FACILITY |  | 4099000 | N32414547 | 2016-12-06 | 2018-06-28 | 2021-12-14 | 72% | 2022-06-30
2022-08-15 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995655 | P-8A HANGAR AND FLEET SUPPORT FACILITY |  |  |  | 2016-12-06 | 2019-04-23 | 2021-12-14 | 55% | 2022-06-30
2022-08-15 | 2017 | Navy Active | Major Military Construction |  | Italy | N62995737 | UPGRADE ENTRY CONTROL POINT |  |  |  | 2017-03-14 | 2018-08-22 | 2021-01-21 | 100% | 2021-12-22
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction |  | Bahrain | N63005955U | P8A CLEAR WATER RINSE FACILITY
2022-08-15 | 2021 | Navy Active | Major Military Construction |  | Bahrain | N63005964 | SHIP TO SHORE UTILITY SERVICES
2022-08-15 | 2020 | Navy Active | Major Military Construction |  | Bahrain | N63005974 | ELECTRICAL SYSTEM UPGRADE
2022-08-15 | 2016 | Navy Active | Major Military Construction |  | Bahrain | N63005976 | MINA SALMAN PIER REPLACEMENT
2022-08-15 | 2017 | Navy Active | Unspecified Minor Military Construction |  | Bahrain | N63005985 | FIRE WATER TANK |  |  |  | 2019-06-28 | 2021-03-25 | 2021-03-25 | 100% | 2022-07-31
2022-08-15 | 2016 | Navy Active | Major Military Construction | California | United States | N63042218 | RTO AND MISSION DEBRIEF FACILITY |  |  |  | 2016-05-24 | 2019-11-03 | 2020-09-17 | 98% | 2020-07-10
2022-08-15 | 2018 | Navy Active | Major Military Construction | California | United States | N63042282 | F/A 18 AVIONICS REPAIR FACILITY REPLACEMENT |  |  |  | 2018-10-03 | 2021-02-24 | 2022-02-25 | 100% | 2021-06-09
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N63042284 | F-35 MAINTENANCE HANGAR |  |  |  | 2019-09-30 | 2021-11-17 | 2022-08-12 | 98% | 2022-08-12
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N63042392 | COMMUNICATIONS LINE OPS TO ADMIN |  |  |  | 2019-08-13 | 2021-05-06 | 2021-05-06 | 100% | 2020-12-28
2022-08-15 | 2022 | Navy Active | Major Military Construction | California | United States | N63402391A | F-35C HANGAR 6 PHASE 2 (MOD 3/4)(INC)
2022-08-15 | 2021 | Navy Active | Major Military Construction |  | Greece | N66691131 | COMMUNICATIONS CENTER |  |  |  | 2022-02-18 | 2024-07-22 | 2024-10-20 | 1% | 2024-09-23
2022-08-15 | 2019 | Navy Active | Major Military Construction |  | Greece | N66691144 | EDI: MARATHI LOGISTICS SUPPORT CENTER
2022-08-15 | 2018 | Navy Active | Major Military Construction |  | Greece | N66691911 | STRATEGIC AIRCRAFT PARKING APRON EXPANSION |  |  |  | 2018-12-26 | 2021-02-14 | 2021-10-04 | 94% | 2021-12-16
2022-08-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436400 | SUBMARINE REFIT MAINT SUPPORT FACILITY |  |  |  | 2018-10-13 | 2021-06-30 | 2022-03-19 | 46% | 2023-07-28
2022-08-15 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436401 | REGIONAL SHIP MAINTENANCE SUPPORT FACILITY |  |  |  | 2017-10-10 | 2020-01-04 | 2021-07-06 | 100% | 2021-07-20
2022-08-15 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436431 | DRY DOCK 6 MODERNIZATION & UTILITY IMPROVE. |  |  |  | 2016-08-25 | 2017-11-14 | 2021-08-06 | 100% | 2022-05-19
2022-08-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436438 | NUCLEAR REPAIR FACILITY |  |  |  | 2018-05-07 | 2019-10-30 | 2020-08-14 | 100% | 2020-05-27
2022-08-15 | 2020 | Navy Active | Major Military Construction | Washington | United States | N68436447 | DRY DOCK 4 & PIER 3 MODERNIZATION |  |  |  | 2020-06-22 | 2023-08-02 | 2023-08-02 | 1% | 2023-08-02
2022-08-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436834 | SEAWOLF CLASS SERVICE PIER |  |  |  | 2020-02-17 | 2022-07-04 | 2022-08-24 | 95% | 2022-08-24
2022-08-15 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436983 | WRA LAND/WATER INTERFACE |  |  |  | 2016-10-05 | 2018-02-13 | 2019-04-21 | 90% | 2020-03-24
2022-08-15 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 - INC 4 | N68436990C | 2728000 | M67399222; N68436993 | 2015-01-22 | 2016-01-09 | 2017-09-30 | 100% | 2016-12-23
2022-08-15 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436993 | TPS PORT ANGELES FORWARD OPERATING LOCATION |  |  |  | 2016-09-13 | 2018-02-06 | 2019-08-07 | 100% | 2018-09-03
2022-08-15 | 2019 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469001 | MASTER TIME CLOCKS & OPERATIONS FACILITY - INC 1 |  |  |  | 2019-09-30 | 2024-09-15 | 2024-09-15 | 69% | 2025-10-10
2022-08-15 | 2015 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY |  |  |  | 2017-11-16 | 2021-06-16 | 2022-11-13 | 39% | 2023-03-18
2022-08-15 | 2018 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY | N68469275A |  |  | 2017-11-16 | 2021-06-16 | 2022-11-13 | 98% | 2023-03-18
2022-08-15 | 2017 | Navy Active | Unspecified Minor Military Construction | District Of Columbia | United States | N68469760 | DIRECT AIRCRAFT REFUELING SYSTEM
2022-08-15 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N69212169 | NMC ORDNANCE FACILITIES RECAP |  |  |  | 2021-04-08 | 2023-06-25 | 2024-07-17 | 1% | 2024-07-17
2022-08-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N69212995 | BACHELOR ENLISTED QUARTERS |  |  |  | 2019-02-14 | 2021-06-25 | 2021-12-08 | 100% | 2022-10-15
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N69232586 | MISSILE ASSEMBLY BUILDING AND HIGH EXPLOSIVE MAG |  |  |  | 2019-10-10 | 2021-02-15 | 2021-07-01 | 98% | 2022-09-30
2022-08-15 | 2019 | Navy Active | Major Military Construction | California | United States | N69232777 | DIRECTED ENERGY SYSTEMS INTEGRATION LAB |  |  |  | 2019-09-11 | 2021-01-11 | 2021-11-24 | 86% | 2022-11-01
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Texas | United States | N83447084 | CDC STORM SHELTER |  |  |  | 2019-10-01 | 2020-09-20 | 2021-02-25 | 100% | 2021-02-25
2022-08-15 | 2017 | Navy Reserve | Major Military Construction | Louisiana | United States | M68479777 | MARINE CORPS RESERVE CENTER |  |  |  | 2020-02-19 | 2021-08-30 | 2022-06-01 | 46% | 2023-05-12
2022-08-15 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Connecticut | United States | N00129664 | CORIVRON 8 RESERVE HVU DET SUPPORT FACILITIES |  |  |  | 2015-09-08 | 2016-09-08 | 2017-04-21 | 98% | 2017-07-14
2022-08-15 | 2020 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206475 | ENTRY CONTROL FACILITY UPGRADES |  |  |  | 2020-08-27 | 2023-03-06 | 2023-06-06 | 83% | 2023-06-06
2022-08-15 | 2019 | Navy Reserve | Unspecified Minor Military Construction | Louisiana | United States | N00206493 | FLIGHT LINE ACCESS CONTROL AND SECURITY |  |  |  | 2020-01-23 | 2021-01-08 | 2022-01-04 | 80% | 2022-01-06
2022-08-15 | 2017 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206500 | JOINT RESERVE INTELLIGENCE CENTER |  |  |  | 2017-07-13 | 2019-07-27 | 2020-10-01 | 100% | 2020-08-21
2022-08-15 | 2018 | Navy Reserve | Major Military Construction | Georgia | United States | N42237642 | NAVY OPERATIONAL SUPPORT CENTER FORT GORDON |  |  |  | 2018-09-26 | 2020-01-06 | 2021-10-16 | 100% | 2021-10-16
2022-08-15 | 2019 | Navy Reserve | Major Military Construction | Georgia | United States | N42237643 | RESERVE TRAINING CENTER |  |  |  | 2019-08-23 | 2021-10-03 | 2022-05-04 | 28% | 2022-05-04
2022-08-15 | 2019 | Navy Reserve | Major Military Construction | California | United States | N61065160 | RESERVE TRAINING CENTER |  |  |  | 2019-02-07 | 2021-02-07 | 2021-06-01 | 96% | 2021-05-26
2022-08-15 | 2018 | Navy Reserve | Major Military Construction | California | United States | N63042366 | NAVAL OPERATIONAL SUPPORT CENTER LEMOORE |  |  |  | 2019-04-25 | 2021-03-26 | 2022-03-02 | 100% | 2021-02-24
2022-08-15 | 2018 | Navy Reserve | Major Military Construction | Texas | United States | N83447077 | K-C130J EACTS FACILITY |  |  |  | 2018-10-10 | 2019-12-31 | 2020-12-31 | 100% | 2021-03-02
2022-08-08 | 2015 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80011 | Redundant Chilled Water Loop |  | 1300000 | Reprogramming of expired funds received from project 80004 | 2020-04-01 | 2021-06-21 | 2022-05-16 | 89% | 2022-08-15
2022-08-08 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 87637 | Pentagon Corridor 8 Pedestrian Access Control Point |  | 55553 | Reprogramming to project 88963 | 2020-09-28 | 2022-06-21 | 2023-07-30 | 13% | 2023-01-28
2022-08-08 | 2019 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 87645 | North Village Secondary VACP and Fencing |  | 383475 | Reprogramming $383,475 to project 87744 | 2020-10-15 | 2021-04-23 | 2022-12-30 | 33% | 2022-07-23
2022-08-08 | 2019 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 88790 | Exterior Infrastructure and Security Improvements |  | 244262 | Reprogramming to project 88963 | 2020-04-24 | 2022-08-17 | 2022-11-10 | 76% | 2022-10-17
2022-08-08 | 2018 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 88963 | Security Upgrades |  | 299816 | Reprogramming received from projects 87637 & 88790 | 2020-02-12 | 2022-01-20 | 2022-08-12 | 99% | 2022-08-30
2022-08-08 | 2022 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 90570 | Consolidated Maintenance Complex
2022-08-08 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91474 | Southest Safety Traffic and Parking Improvements |  | 4170000 | Reprogramming of UMC funds to project | 2020-02-01 | 2021-01-22 | 2023-12-29 | 13% | 2023-04-23
2022-08-08 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91474A | Southest Safety Traffic and Parking Improvements |  |  |  | 2019-03-18 | 2019-06-18 | 2019-06-18 | 100% | 2021-09-22
2022-08-08 | 2020 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91531 | Backup Generator
2022-08-08 | 2020 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 92232 | Control Tower and Fire Day Station |  |  |  | 2021-09-30 | 2023-04-30 | 2023-12-27 | 15%
2022-08-08 | 2022 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 95677 | Force Protection Perimeter Enhancements
2022-08-08 | 2022 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 95696 | Public Works Support Facility

## CONTRACTS
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Prime Contract Number | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date
2022-07-31 | 2021 | Air Force Active | ACJP183018 |  | 2021-03-31 | 2021-09-21 | J.I. Garcia Construction, Inc. | N6247318D5817 | 4749000 | 4749000 | 2022-11-13 | 2022-11-13
2022-07-31 | 2018 | Air Force Active | AEWV171012 |  | 2018-08-01 | 2019-03-01 | Black & Veatch Special Project | W912ER18D0005 | 3705150 | 3769955 | 2023-10-02 | 2025-05-24
2022-07-31 | 2018 | Air Force Active | AGGN053009 |  | 2020-02-22 | 2020-03-24 | Source Selection Sensitive | W912BV20C0005 | 20353334 | 20537195 | 2022-05-07 | 2023-03-30
2022-07-31 | 2016 | Air Force Active | AGGN123003 |  | 2019-08-28 | 2019-09-27 | CNS Sheffield-Korte Team | W912BV19C0024 | 23141087 | 23141087 | 2021-10-26 | 2022-06-15
2022-07-31 | 2017 | Air Force Active | AGGN173001 |  | 2017-01-06 | 2017-07-06 | SGS, LLC | W912BV17C0010 | 10428748 | 10774827 | 2023-08-23 | 2024-07-06
2022-07-31 | 2019 | Air Force Active | AGGN213001 |  | 2018-10-29 | 2019-06-17 | SGS, LLC; Yukon OK | W912BV19C0011 | 12250972 | 12250972 | 2023-07-30 | 2023-07-30
2022-07-31 | 2017 | Air Force Active | AJJY073105P2 |  | 2021-07-12 | 2021-12-16 | Relyant Global LLC / Maryville / Tennessee | N6274222C1320 | 30905912 | 30905912 | 2025-02-07 | 2025-02-07
2022-07-31 | 2020 | Air Force Active | AJJY073105P3 |  | 2020-01-17 | 2020-09-16 | Core Tech-Hawaiian Dredging | N6274220R1324 | 52969474 | 52969474 | 2023-07-16 | 2023-06-16
2022-07-31 | 2022 | Air Force Active | AJJY073105P4 |  | 2021-10-13 | 2022-05-04 | Reliable Builders, Inc | N6274222C1325 | 43444038 | 43444038 | 2025-08-15 | 2025-08-15
2022-07-31 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 91150297 | 91150297 | 2017-04-16 | 2025-12-19
2022-07-31 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 98038253 | 104322589 | 2017-03-08 | 2022-11-30
2022-07-31 | 2015 | Air Force Active | AJJY133028 |  | 2016-06-01 | 2016-09-30 | Pernix Guam, LLC | N6274216C1309 | 27010495 | 29858250 | 2018-11-08 | 2023-03-03
2022-07-31 | 2022 | Air Force Active | AJJY163000 |  | 2021-10-06 | 2022-05-09 | Cadell-Nan | N6274222C1308 | 29671766 | 29671766 | 2023-11-30 | 2023-11-30
2022-07-31 | 2019 | Air Force Active | AJJY183003 |  | 2021-10-06 | 2022-05-26 | Granite-Obayashi | N6274222C1327 | 10760166 | 10760166 | 2024-01-29 | 2024-01-29
2022-07-31 | 2020 | Air Force Active | AJJY183017 |  | 2020-06-15 | 2020-09-30 | Serrano Construction | N4019218D2804 | 4160672 | 4220039 | 2022-06-29 | 2022-08-30
2022-07-31 | 2021 | Air Force Active | AJJY203001 |  | 2020-09-16 | 2021-02-25 | Granite-Obayashi, a Joint Venture | N6274221C1338 | 43545116 | 47011767 | 2023-03-25 | 2023-11-24
2022-07-31 | 2017 | Air Force Active | AJXF093000 |  | 2017-08-02 | 2018-05-24 | EDIFICE, LLC | N4008017D0009 | 11179388 | 11179388 | 2020-02-25 | 2022-07-12
2022-07-31 | 2018 | Air Force Active | AJXF173021 |  | 2018-06-05 | 2018-07-05 | Clark Construction Group, LLC | N4008019C0008 | 220000000 | 220000000 | 2019-01-26 | 2022-08-30
2022-07-31 | 2018 | Air Force Active | AJXF173030 |  | 2019-02-17 | 2020-09-23 | Clark Construction LLC | N4008020C0024 | 20335697 | 20335697 | 2022-01-24 | 2022-08-30
2022-07-31 | 2018 | Air Force Active | ALUA113023 |  | 2019-05-29 | 2019-09-26 | MVL USA, Inc. / Houston / TX | W912ER19C0016 | 13890460 | 13734951 | 2021-01-20 | 2022-01-27
2022-07-31 | 2018 | Air Force Active | ASHE143008 |  | 2018-01-04 | 2018-09-28 | CMC | N6247018C4004 | 16003726 | 16003726 | 2021-01-25 | 2022-08-23
2022-07-31 | 2020 | Air Force Active | ASPR150126 |  | 2020-10-05 | 2020-11-04 | Source Selection Sensitive | W9127821C0005 | 3795142 | 3795142 | 2020-12-18 | 2022-01-20
2022-07-31 | 2017 | Air Force Active | ASVF164000 |  | 2017-09-16 | 2018-09-11 | RED HORSE | FA571018P0325 | 2200000 | 2348000 | 2024-01-23 | 2025-08-11
2022-07-31 | 2018 | Air Force Active | ASVF183100A |  | 2019-01-11 | 2020-04-10 | American International Contractors, (Pkg 2, Aprons) | W912ER20C0009 | 32474636 | 32474636 | 2023-03-28 | 2023-07-12
2022-07-31 | 2018 | Air Force Active | ASVF183100B |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER20C0009 | 9862845 | 9856753 | 2023-03-28 | 2023-07-12
2022-07-31 | 2018 | Air Force Active | ASVF183100C |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc, (Pkg 2, Aprons) | W912ER20C0009 | 8267668 | 8267668 | 2023-03-28 | 2023-07-12
2022-07-31 | 2018 | Air Force Active | ASVF183100D |  | 2018-06-28 | 2019-04-05 | The Morganti Group, Inc / Danbury, CT (Pkg 3, Dorm) | W912ER19C0008 | 10434344 | 10393609 | 2020-08-29 | 2021-10-09
2022-07-31 | 2018 | Air Force Active | ASVF183100E |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER20C0009 | 804821 | 806055 | 2023-03-28 | 2023-07-12
2022-07-31 | 2018 | Air Force Active | ASVF183100F |  | 2020-03-11 | 2020-04-10 | American International Contractors, Inc (Pkg 2, Aprons) | W912ER20C0009 | 28401350 | 28167704 | 2023-03-21 | 2022-07-12
2022-07-31 | 2017 | Air Force Active | AWUB095000 |  | 2016-12-02 | 2019-07-17 | CNS Bristol General Contractors, LLC | N6945013D1771 | 24961520 | 25022647 | 2022-01-02 | 2022-10-07
2022-07-31 | 2017 | Air Force Active | AWUB105003 |  | 2017-07-10 | 2018-06-21 | CNS Source Selection Sensitive | N6945018C2105 | 3396587 | 3570241 | 2020-10-08 | 2021-02-23
2022-07-31 | 2018 | Air Force Active | BIKF180001 |  | 2018-05-02 | 2018-12-06 | Iceland Prime Contractor, LTD | N6247018R4005 | 14146220 | 14146220 | 2021-10-20 | 2021-02-13
2022-07-31 | 2020 | Air Force Active | BIKF190001 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 19776676 | 19776676 | 2023-07-14 | 2023-07-14
2022-07-31 | 2020 | Air Force Active | BIKF190002 |  | 2019-11-15 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 4671392 | 4671392 | 2023-07-14 | 2023-07-14
2022-07-31 | 2020 | Air Force Active | BIKF190003 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 14404448 | 14404448 | 2023-07-14 | 2023-07-14
2022-07-31 | 2017 | Air Force Active | CADJ170001 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 3194454 | 3410296 | 2020-02-06 | 2022-01-27
2022-07-31 | 2017 | Air Force Active | CADJ170002 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 4911856 | 5442283 | 2020-02-06 | 2022-04-11
2022-07-31 | 2018 | Air Force Active | CRWU093002 |  | 2018-04-15 | 2018-12-18 | Mortenson | W9128F19C0006 | 37107984 | 37107984 | 2019-02-12 | 2022-08-16
2022-07-31 | 2019 | Air Force Active | CRWU173001 |  | 2020-07-15 | 2020-09-25 | Iron Mike Construction | W9128F20C0048 | 4763991 | 4849127 | 2021-12-12 | 2022-03-01
2022-07-31 | 2017 | Air Force Active | DHAF152900 |  | 2018-04-01 | 2019-09-06 | Amana Contracting & Steel Building Co. WLL, Abu Dhabi UAE | W912ER19C0015 | 25152460 | 25528019 | 2024-09-11 | 2025-04-21
2022-07-31 | 2017 | Air Force Active | DXEB053005 |  | 2017-04-26 | 2018-04-30 | Bethel-Unit JV | W911KB18C0006 | 19278001 | 20209919 | 2020-04-11 | 2021-10-11
2022-07-31 | 2017 | Air Force Active | EEEI150006 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB15D0029 | 1451631 | 1451631 | 2024-04-10 | 2024-04-10
2022-07-31 | 2018 | Air Force Active | EEEI180001 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB15D0029 | 1210326 | 1210326 | 2024-04-10 | 2024-04-10
2022-07-31 | 2020 | Air Force Active | EEPZ1073283 |  | 2021-04-21 | 2021-07-21 | ESA South, Inc | W9127821C0022 | 4798123 | 4798123 | 2022-12-08 | 2022-12-08
2022-07-31 | 2017 | Air Force Active | EPPW170003 |  | 2017-07-14 | 2017-09-21 | Wolff & Mueller & Erbud JV | W912GB15D0060 | 2463632 | 2463632 | 2020-03-26 | 2021-01-27
2022-07-31 | 2020 | Air Force Active | EPPW190001 |  | 2020-12-30 | 2021-09-29 | HATCON INSAAT TAAHHUT ITHALAT IHRACAT LI | W912GB21C0031 | 17039500 | 17039500 | 2027-11-20 | 2027-11-20
2022-07-31 | 2017 | Air Force Active | EVKP174535 |  | 2020-06-12 | 2021-06-25 | Nishimatsu Construction Co. | W912HV21C0001 | 79714176 | 79714176 | 2024-08-31 | 2024-08-31
2022-07-31 | 2019 | Air Force Active | FBNV033002 |  | 2019-08-22 | 2019-09-28 | Inc BFL Construction CO | W912PL19C0035 | 11502142 | 11502142 | 2021-06-02 | 2022-08-24
2022-07-31 | 2017 | Air Force Active | FBNV163001 |  | 2019-04-12 | 2020-01-17 | LLC Chase, Carson & White | W912PL20C0008 | 3387810 | 3387810 | 2021-04-09 | 2021-07-12
2022-07-31 | 2017 | Air Force Active | FJXT133000 |  | 2020-03-01 | 2020-03-31 | CNS Archer Western Federal JV | W912BU20C0015 | 44643899 | 44643899 | 2021-12-31 | 2023-04-30
2022-07-31 | 2016 | Air Force Active | FNWZ100071A |  | 2018-07-11 | 2018-08-08 | Basecom Construction Services | W9126G18C0049 | 4400848 | 4400848 | 2019-09-09 | 2022-09-30
2022-07-31 | 2017 | Air Force Active | FSPM053503C |  | 2017-05-12 | 2018-05-22 | I.E. Pacific, INC | W912PL8C0024 | 22414000 | 22537509 | 2020-06-18 | 2020-07-31
2022-07-31 | 2021 | Air Force Active | FSPM1075894 |  | 2021-05-17 | 2021-09-28 | KORTE CONSTRUCTION COMPANY | W912PL21C0028 | 41217348 | 41217348 | 2023-08-27 | 2024-01-27
2022-07-31 | 2019 | Air Force Active | FSPM173504 |  | 2020-01-31 | 2020-08-06 | Korte Company | W912PL20C0030 | 38397321 | 38397321 | 2022-08-09 | 2022-09-09
2022-07-31 | 2017 | Air Force Active | FTFA033003 |  | 2017-08-28 | 2018-01-11 | The Green-Simmons Company, Inc | W9127816D0016 | 12034000 | 12208303 | 2018-05-26 | 2021-02-26
2022-07-31 | 2017 | Air Force Active | FTFA043000 |  | 2018-06-07 | 2019-03-15 | Hensel Phelps | W9127819C00006 | 59456363 | 61865044 | 2020-03-16 | 2022-09-30
2022-07-31 | 2017 | Air Force Active | FTFA053017 |  | 2019-05-20 | 2019-09-30 | CNS Source Selection Sensitive | W9127819C0034 | 43336911 | 43336911 | 2021-11-05 | 2022-08-29
2022-07-31 | 2019 | Air Force Active | FTFA093965 |  | 2018-11-12 | 2019-03-21 | Whitesell-Green | W9127819C0012 | 26376465 | 26387419 | 2021-04-21 | 2021-12-19
2022-07-31 | 2017 | Air Force Active | FTFA133002 |  | 2020-11-12 | 2021-04-21 | CNS EMR, Inc | W9127816D0035 | 3941080 | 3941080 | 2022-02-15 | 2022-10-30
2022-07-31 | 2019 | Air Force Active | FTFA143913 |  | 2019-03-26 | 2019-04-25 | Korte Construction | W9127819C0013 | 31295038 | 31286284 | 2020-04-24 | 2021-09-08
2022-07-31 | 2018 | Air Force Active | FTFA163003 |  | 2018-06-28 | 2018-09-28 | Speegle Constrcution, Inc | W9127818C0026 | 8007902 | 8052184 | 2020-08-22 | 2021-07-14
2022-07-31 | 2019 | Air Force Active | FTFA163007 |  | 2020-07-07 | 2020-09-29 | Hensel Phelps Construction Co | W9127820C0033 | 30147298 | 30147298 | 2022-05-12 | 2022-10-31
2022-07-31 | 2019 | Air Force Active | FTQW1053834 |  | 2019-01-03 | 2019-07-18 | CNS Ames 1/Conam JV | W911KB19R0008 | 7608922 | 8989456 | 2021-03-10 | 2022-12-31
2022-07-31 | 2019 | Air Force Active | FTQW1054329 |  | 2019-06-07 | 2019-09-30 | CNS ASRC Builders, LLC | W911KB19C0030 | 13310756 | 14780249 | 2021-07-31 | 2022-11-30
2022-07-31 | 2020 | Air Force Active | FTQW1055646 |  | 2020-08-11 | 2021-09-02 | Bristol Site Constructors LLC | W911KB21C0031 | 15504182 | 15504182 | 2024-04-16 | 2024-07-13
2022-07-31 | 2017 | Air Force Active | FTQW170100 |  | 2021-05-31 | 2021-06-30 | Bethel Environmental Solutions LLC | W911KB21F0085 | 15588 | 15588 | 2021-08-14 | 2021-08-14
2022-07-31 | 2018 | Air Force Active | FTQW180107 |  | 2017-09-29 | 2018-03-23 | Bethel Environmental Solutions LLC | W911KB21F0085 | 20024777 | 25141378 | 2020-08-14 | 2022-12-31
2022-07-31 | 2019 | Air Force Active | FTQW180109 |  | 2018-09-27 | 2019-02-28 | GHEMM Company, Inc | W911KB19C0013 | 19794920 | 20495551 | 2020-07-30 | 2020-09-25
2022-07-31 | 2019 | Air Force Active | FTQW180110 |  | 2021-05-27 | 2021-09-08 | CNS Callahan-Watterson JV (CWJV) | W911KB21C0031 | 9446802 | 9640665 | 2023-01-09 | 2023-02-26
2022-07-31 | 2017 | Air Force Active | FTQW183001 |  | 2021-05-31 | 2021-06-30 | Bethel Environmental Solutions LLC | W911KB21F0085 | 31412 | 31412 | 2021-08-14 | 2023-02-26
2022-07-31 | 2021 | Air Force Active | FXBM1081508 |  | 2021-07-12 | 2021-09-17 | LLC Walsh Federal | W9128F21C0045 | 143007394 | 143007394 | 2024-10-21 | 2024-11-01
2022-07-31 | 2017 | Air Force Active | FXSB982839 |  | 2016-10-20 | 2020-04-01 | CNS Unit Company | W911KB20C008 | 45648623 | 48481426 | 2022-03-17 | 2022-08-30
2022-07-31 | 2017 | Air Force Active | GHLN083004 |  | 2017-05-16 | 2017-06-15 | W9128F16R0011 | W9128F16D00550001 | 5129267 | 5129267 | 2019-01-06 | 2020-08-06
2022-07-31 | 2016 | Air Force Active | GHLN153001 |  | 2017-09-19 | 2018-12-07 | CNS Source Selection Sensitive | W9128F19C0005 | 154269651 | 154671056 | 2022-06-04 | 2023-03-05
2022-07-31 | 2017 | Air Force Active | GJKZ040009 |  | 2018-08-10 | 2018-12-28 | GARCO Construction | W912DW19C0002 | 23481000 | 23481000 | 2024-12-21 | 2024-12-21
2022-07-31 | 2019 | Air Force Active | GJLK1053425 |  | 2020-08-25 | 2020-09-24 | TSS-Garco JV | W912DW20C0015 | 11491000 | 11491000 | 2021-11-08 | 2022-10-20
2022-07-31 | 2020 | Air Force Active | GLEN203001 |  | 2019-11-30 | 2021-09-01 | Hensel Phelps | W9128F21C0041 | 130688368 | 130688368 | 2025-01-31 | 2025-05-31
2022-07-31 | 2020 | Air Force Active | JFSD201120 |  | 2021-03-20 | 2021-07-29 | Pro-Mark Services | W9128F21C0042 | 4807447 | 4807447 | 2021-08-28 | 2023-01-14
2022-07-31 | 2016 | Air Force Active | KNMD043004 |  | 2018-02-01 | 2018-09-29 | Nordic PCL Construction | W9128A18C0009 | 41476374 | 44043580 | 2020-10-22 | 2021-10-29
2022-07-31 | 2020 | Air Force Active | KRSM1065068 |  | 2020-06-27 | 2020-07-27 | Hensel Phelps Construction Co | W9123820C0012 | 92101014 | 95471587 | 2023-04-13 | 2023-06-03
2022-07-31 | 2017 | Air Force Active | KRSM113031 |  | 2020-06-16 | 2020-12-30 | The Povolny Group Inc | W9123821C0007 | 3892900 | 3892900 | 2022-01-19 | 2022-08-21
2022-07-31 | 2018 | Air Force Active | KRSM123009 |  | 2020-09-24 | 2021-03-09 | CNS HHI Corporation | W9123821C0013 | 89447135 | 89447135 | 2021-04-08 | 2023-01-14
2022-07-31 | 2017 | Air Force Active | KRSM143003 |  | 2018-06-30 | 2018-09-28 | Northern Construction, LLC | W9123818C0049 | 8958380 | 9367284 | 2021-11-01 | 2022-08-30
2022-07-31 | 2020 | Air Force Active | KRSM183001 |  | 2021-06-28 | 2021-07-28 | NVE-HHI JV | W9123821C0019 | 6319659 | 6319659 | 2021-08-27 | 2023-06-02
2022-07-31 | 2020 | Air Force Active | KWRD1055707 |  | 2021-04-10 | 2021-07-09 | W912PP21C0012 | W912PP21C0012 | 12949000 | 12949000 | 2023-06-08 | 2023-07-08
2022-07-31 | 2018 | Air Force Active | KWRD143000 |  | 2018-08-22 | 2019-10-31 | RPA Fixed Ground Control Station | W912PP19C0019 | 4963246 | 4963246 | 2020-11-29 | 2021-10-25
2022-07-31 | 2017 | Air Force Active | LBPG150008 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB17F0444 | 1611283 | 1611283 | 2021-01-21 | 2024-03-19
2022-07-31 | 2017 | Air Force Active | LBPG150009 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB17F0461 | 1978602 | 1978602 | 2022-02-11 | 2024-05-17
2022-07-31 | 2017 | Air Force Active | LJYC133003 |  | 2017-11-08 | 2018-05-01 | Aytekin Serol Insaat Taan | W912GB18C0013 | 10199660 | 10199660 | 2021-05-22 | 2023-04-12
2022-07-31 | 2018 | Air Force Active | LJYC183004 |  | 2018-08-29 | 2019-05-13 | EMTA INSAAT TAAHHUT VE TICARET ANONIUM SI | W912GB19F0076 | 3795142 | 3795142 | 2021-09-28 | 2023-06-07
2022-07-31 | 2019 | Air Force Active | LKTC203101 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL19C0028 | 25007200 | 25716568 | 2021-10-02 | 2022-05-23
2022-07-31 | 2019 | Air Force Active | LKTC203102 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL19C0028 | 24652900 | 25087883 | 2021-11-02 | 2022-05-23
2022-07-31 | 2017 | Air Force Active | LRCT150007 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2575083 | 2575083 | 2020-03-12 | 2022-09-15
2022-07-31 | 2017 | Air Force Active | LRCT150008 |  | 2017-07-28 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0021 | 1711902 | 1711902 | 2020-02-01 | 2021-12-14
2022-07-31 | 2017 | Air Force Active | LRCT150009 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2356785 | 2356785 | 2020-03-12 | 2022-09-15
2022-07-31 | 2017 | Air Force Active | LRCT150010 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2021357 | 2021357 | 2022-06-15 | 2022-11-20
2022-07-31 | 2021 | Air Force Active | LRCT190001 |  | 2021-03-08 | 2021-06-04 | Eiffage Infraestructura SA | W912GB21D0019 | 10852364 | 10852364 | 2023-11-06 | 2023-08-16
2022-07-31 | 2021 | Air Force Active | LRCT190002 |  | 2021-06-23 | 2021-09-16 | Relyant Global LLC | W912GB21F0202 | 27388762 | 27388762 | 2024-11-04 | 2024-11-04
2022-07-31 | 2021 | Air Force Active | LRCT210001 |  | 2021-03-17 | 2021-08-09 | Tepe Bozdemir Joint Venture | W912GB21C0022 | 44485900 | 44485900 | 2024-03-09 | 2024-03-09
2022-07-31 | 2021 | Air Force Active | LRCT210002 |  | 2020-11-26 | 2021-09-21 | Sociedad Espanola De Montajes Industrial (SEMI) | W912GB21F0202 | 12163401 | 12163401 | 2023-12-13 | 2023-12-13
2022-07-31 | 2016 | Air Force Active | LXEZ154288 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV16D0009 | 34988795 | 34988795 | 2021-01-14 | 2023-01-30
2022-07-31 | 2016 | Air Force Active | LXEZ164289 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV16D0009 | 27745871 | 27745871 | 2021-01-14 | 2023-01-30
2022-07-31 | 2018 | Air Force Active | LXEZ183486 |  | 2021-01-05 | 2021-07-13 | CNS Maeda-Onaka Joint Venture | FA527021F0092 | 2082263 | 2082263 | 2022-12-07 | 2022-12-10
2022-07-31 | 2018 | Air Force Active | LXEZ184546 |  | 2019-11-27 | 2020-05-18 | Kyowa Exeo Corporation | W912HV20B00010004 | 55457702 | 55457702 | 2022-12-30 | 2023-02-28
2022-07-31 | 2017 | Air Force Active | MAHG173002 |  | 2019-05-22 | 2020-05-28 | U-SMC/DeMaria JV, LLC | N6945019D0921 | 3591891 | 3591891 | 2023-03-26 | 2023-03-26
2022-07-31 | 2017 | Air Force Active | MAHG173003 |  | 2019-06-12 | 2020-05-28 | TU-SMC/DeMaria JV, LLC | N6945019D0921 | 4007591 | 4007591 | 2023-03-26 | 2023-03-26
2022-07-31 | 2017 | Air Force Active | MHMV053107 |  | 2020-10-30 | 2021-04-06 | QA Engineering, LLC | W912PP19D0035 | 2855784 | 2855784 | 2022-07-11 | 2022-11-05
2022-07-31 | 2018 | Air Force Active | MHMV083126A |  | 2020-08-14 | 2020-11-10 | Encanto Facillity Services 2 | W912PP19D0037 | 8427275 | 8427275 | 2022-04-11 | 2023-04-25
2022-07-31 | 2016 | Air Force Active | MPLS083737R5 |  | 2019-05-27 | 2019-06-26 | CNS Source Selection Sensitive | W9126G19C0035 | 5546178 | 5546178 | 2021-08-03 | 2022-09-30
2022-07-31 | 2017 | Air Force Active | MPLS083737R6 |  | 2019-01-22 | 2019-09-26 | DA-CA USACE | W9126G19C0023 | 103001487 | 103001487 | 2022-04-13 | 2022-12-15
2022-07-31 | 2016 | Air Force Active | MPLS083737S3 |  | 2017-11-29 | 2019-01-16 | CNS Source Selection Sensitive | W9126G19C0001 | 55663720 | 55663720 | 2021-09-05 | 2022-09-30
2022-07-31 | 2016 | Air Force Active | MPLS113003A |  | 2018-11-30 | 2019-03-01 | Express Contracting | W9126G19C0019 | 2872000 | 2872000 | 2020-06-30 | 2021-06-03
2022-07-31 | 2015 | Air Force Active | MPLS3274JB |  | 2015-02-17 | 2015-06-03 | Solis Constructors, Inc. | W9126G14D00500002 | 6077000 | 6133616 | 2016-08-31 | 2021-06-03
2022-07-31 | 2020 | Air Force Active | MPYJ043895A |  | 2021-03-27 | 2021-06-25 | Clark/Byrne Aquatics, JV | W9126G21C0012 | 58950000 | 58965582 | 2023-09-07 | 2023-06-26
2022-07-31 | 2019 | Air Force Active | MSBL103000 |  | 2021-02-19 | 2021-09-29 | Ranco Construction | W912DS21C0021 | 9138000 | 9138000 | 2023-05-13 | 2023-05-16
2022-07-31 | 2018 | Air Force Active | MSET143006 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 55113676 | 55113676 | 2023-03-29 | 2024-02-05
2022-07-31 | 2018 | Air Force Active | MSET153501 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 23292923 | 23292923 | 2021-10-05 | 2022-08-19
2022-07-31 | 2019 | Air Force Active | MSET153503 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 22219318 | 22219318 | 2024-01-21 | 2024-01-21
2022-07-31 | 2019 | Air Force Active | MSET153504 |  | 2018-05-14 | 2018-11-14 | KVF35 | DIOCB2076 | 33031258 | 33031258 | 2022-02-28 | 2022-02-28
2022-07-31 | 2019 | Air Force Active | MSET153505 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 11543865 | 11543865 | 2022-07-04 | 2022-07-04
2022-07-31 | 2018 | Air Force Active | MSET153506 |  | 2018-06-04 | 2020-09-14 | KVF 35 | DIOCB2076 | 16724478 | 16724478 | 2022-12-21 | 2023-04-24
2022-07-31 | 2019 | Air Force Active | MSET153508 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 36198139 | 36198139 | 2024-01-21 | 2024-01-21
2022-07-31 | 2018 | Air Force Active | MSET153509 |  | 2018-06-08 | 2019-04-10 | KVF 35 | DIOCB2076 | 6211718 | 6211718 | 2027-06-17 | 2027-06-17
2022-07-31 | 2018 | Air Force Active | MSET153513 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 22251003 | 22251003 | 2023-09-30 | 2023-09-30
2022-07-31 | 2018 | Air Force Active | MSET153514 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 39101561 | 39101561 | 2025-07-23 | 2025-07-23
2022-07-31 | 2017 | Air Force Active | MUHJ133000 |  | 2021-04-16 | 2021-05-11 | Source Selection Sensitive | W9123621C2005 | 46832875 | 46832875 | 2023-07-10 | 2023-10-04
2022-07-31 | 2017 | Air Force Active | MXRD083000 |  | 2022-01-12 | 2022-02-11 | J & J | W912WJ22C0005 | 16107000 | 16107000 | 2023-09-12 | 2024-04-20
2022-07-31 | 2019 | Air Force Active | MXRD153006 |  | 2021-03-23 | 2021-12-31 | Gilbane-Exyte JV | W912WJ22C0002 | 276858421 | 276858421 | 2020-05-17 | 2024-11-22
2022-07-31 | 2020 | Air Force Active | NKAK123007 |  | 2020-05-15 | 2020-08-31 | CNS RCO Ross Group JV | W9127S20C6006 | 35396600 | 35396600 | 2020-10-15 | 2022-10-15
2022-07-31 | 2018 | Air Force Active | NKAK153001 |  | 2021-06-02 | 2021-08-31 | LS Black Loeffel Construction, JV | W9127S21C6004 | 28147259 | 28147259 | 2023-04-13 | 2023-12-04
2022-07-31 | 2021 | Air Force Active | NKAK193001 |  | 2021-09-21 | 2021-10-21 | CNS Source Selection Sensitive | FA446017D0005 | 1491000 | 1491000 | 2022-11-20 | 2022-11-20
2022-07-31 | 2016 | Air Force Active | NUEX093016 |  | 2017-10-05 | 2018-02-01 | Okland Construction, Co. Inc. | W912PL18C0013 | 16223496 | 16246162 | 2020-02-26 | 2020-06-10
2022-07-31 | 2019 | Air Force Active | NVZR153710 |  | 2019-08-09 | 2020-02-26 | HCR | W9127820C0010 | 3351127 | 3351127 | 2021-06-18 | 2021-12-30
2022-07-31 | 2018 | Air Force Active | NVZR153711 |  | 2019-07-19 | 2019-09-26 | Southeast Cherokee Constr. Inc | W9127816D0015 | 8163765 | 8163765 | 2021-06-17 | 2021-10-29
2022-07-31 | 2016 | Air Force Active | NZAS043002 |  | 2019-05-06 | 2019-06-05 | DA-CA USACE | W912DW19C008 | 19868428 | 19868428 | 2020-12-26 | 2020-08-31
2022-07-31 | 2017 | Air Force Active | NZAS173001 |  | 2019-05-20 | 2019-06-05 | CNS Source Selection Sensitive | W912DW19C0008 | 19868428 | 19868428 | 2021-03-25 | 2021-10-12
2022-07-31 | 2017 | Air Force Active | PAF150400 |  | 2017-11-21 | 2018-05-18 | AECOM | N6274218C1314 | 24132780 | 33953429 | 2019-11-15 | 2021-10-29
2022-07-31 | 2018 | Air Force Active | PAF160600 |  | 2019-05-07 | 2019-09-26 | Nova Nacap JV | N6274219C1316 | 66955722 | 66955722 | 2022-10-25 | 2023-06-01
2022-07-31 | 2020 | Air Force Active | PAF180200 |  | 2020-11-24 | 2022-05-05 | Nova Nacap | N6274222C1314 | 86116647 | 86116647 | 2025-02-13 | 2025-06-20
2022-07-31 | 2020 | Air Force Active | PAF180300 |  | 2019-12-05 | 2020-05-28 | ICON SI (Aust) Pty Ltd | N6274220C1303 | 10310997 | 11463922 | 2022-02-03 | 2022-05-24
2022-07-31 | 2020 | Air Force Active | PAF189021 |  | 2020-06-12 | 2021-11-30 | Black Micro Corporation / Tamuning / Guam | N6274222C1318 | 90331063 | 90331063 | 2025-11-15 | 2025-11-15
2022-07-31 | 2020 | Air Force Active | PAF189022 |  | 2020-06-12 | 2021-11-30 | Black Micro Corporation / Tamuning / Guam | N6274222C1318 | 84957202 | 84957202 | 2025-11-15 | 2025-11-15
2022-07-31 | 2015 | Air Force Active | PAYZ15001B |  | 2016-06-18 | 2016-11-29 | Vilmanto Statybos | W912GB15D00560002 | 1515821 | 1515821 | 2018-07-07 | 2021-08-03
2022-07-31 | 2015 | Air Force Active | PAYZ15001C |  | 2016-08-01 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00410003 | 4479631 | 4479631 | 2018-07-06 | 2021-05-04
2022-07-31 | 2015 | Air Force Active | PAYZ15001H |  | 2017-03-08 | 2017-09-22 | Cimolai S.p.A | N6247017C5002 | 27192353 | 37466344 | 2020-08-30 | 2023-08-18
2022-07-31 | 2016 | Air Force Active | PAYZ16000B |  | 2020-03-31 | 2020-08-19 | Onaka Gumi Co., Ltd. | W912HV20C0006 | 2413198 | 2428538 | 2021-09-07 | 2021-12-22
2022-07-31 | 2017 | Air Force Active | PNQS072140 |  | 2018-01-01 | 2019-05-08 | Southeast Cherokee | W9127819C0017 | 13341000 | 13341000 | 2021-04-20 | 2021-09-15
2022-07-31 | 2019 | Air Force Active | PNQS103165 |  | 2019-07-17 | 2019-09-30 | Bear Brothers, INC | W9127819C0037 | 12768107 | 12768107 | 2021-05-26 | 2021-12-10
2022-07-31 | 2018 | Air Force Active | PRQE055155 |  | 2018-05-25 | 2018-09-28 | McConnell COMBAT ARMS FACILITY | W912DQ18C4051 | 16222360 | 16222360 | 2020-07-09 | 2021-06-30
2022-07-31 | 2015 | Air Force Active | PTFL106002 |  | 2019-04-20 | 2019-07-19 | Sun Construction Services, Inc. | W912DS19C0012 | 1910502 | 1910502 | 2020-12-20 | 2021-02-19
2022-07-31 | 2018 | Air Force Active | PTFL163001 |  | 2018-08-24 | 2019-02-27 | RANCO CONSTRUCTION INC | W912DS18B00210013 | 4427200 | 4557949 | 2021-03-08 | 2021-12-03
2022-07-31 | 2018 | Air Force Active | PTFL163006 |  | 2018-08-24 | 2018-09-28 | Sun Construction Services Inc. | W912DS18C0027 | 3159200 | 3307588 | 2019-11-09 | 2019-12-30
2022-07-31 | 2018 | Air Force Active | PTFL163010 |  | 2019-06-12 | 2019-09-25 | TDX Quality | W912DS19B007 | 7994996 | 8323132 | 2024-02-22 | 2024-04-18
2022-07-31 | 2018 | Air Force Active | PTFL163019 |  | 2018-10-29 | 2019-07-11 | Walsh Federal LLC | W912DS19C0011 | 52324000 | 52799674 | 2021-07-23 | 2022-11-30
2022-07-31 | 2018 | Air Force Active | QJVF012005 |  | 2019-01-25 | 2019-05-29 | CNS Source Selection Sensitive | W9128F18C0026 | 24993526 | 24993526 | 2021-02-15 | 2021-12-17
2022-07-31 | 2020 | Air Force Active | QJVF1058361 |  | 2021-09-30 | 2021-12-28 | Razor Consulting Solutions, INC. | W9128F22C0007 | 5022459 | 5022459 | 2023-08-25 | 2023-08-25
2022-07-31 | 2017 | Air Force Active | QSEU083023 |  | 2020-06-23 | 2020-09-03 | McKnight Construction | W912HN20C3007 | 23471929 | 23471929 | 2023-05-03 | 2023-05-03
2022-07-31 | 2017 | Air Force Active | QUUG064001 |  | 2019-04-17 | 2021-09-28 | Sociedad Espanola de Montajes | FA557521C0007 | 1336116 | 1336116 | 2022-12-19 | 2023-04-30
2022-07-31 | 2018 | Air Force Active | RKMF063004 |  | 2018-08-16 | 2019-07-03 | Record Steel and Construction, Inc., dba RSCI | W912PL19C0023 | 21623000 | 22289225 | 2024-04-16 | 2024-09-03
2022-07-31 | 2016 | Air Force Active | RKMF103011 |  | 2019-03-13 | 2019-12-17 | BRISTOL | W912PL20C0007 | 2667515 | 5075675 | 2020-11-25 | 2022-09-30
2022-07-31 | 2019 | Air Force Active | RKMF123009 |  | 2019-04-17 | 2019-08-27 | GUARDIAN/EC JV LLC | W912PL19C0024 | 5555674 | 5822833 | 2021-06-02 | 2022-10-31
2022-07-31 | 2020 | Air Force Active | RKMF163007 |  | 2020-07-23 | 2020-09-30 | KORTE | W912PL20C0021 | 40917285 | 40917285 | 2022-12-28 | 2023-05-07
2022-07-31 | 2018 | Air Force Active | RKMF173010 |  | 2019-03-04 | 2019-10-02 | Bristol Prime Contractors, LLC | W912PL20C0001 | 3698666 | 4146204 | 2020-11-11 | 2022-09-30
2022-07-31 | 2020 | Air Force Active | RKMF203001 |  | 2020-06-15 | 2020-09-16 | GUARDIAN | W912PL20C0035 | 5659450 | 5659450 | 2023-08-17 | 2022-08-30
2022-07-31 | 2019 | Air Force Active | RKMF203007 |  | 2020-03-13 | 2020-06-19 | Record Steel and Construction, Inc., dba RsCI | W912PL20C0018 | 27554000 | 27554000 | 2022-07-24 | 2022-08-23
2022-07-31 | 2019 | Air Force Active | SGBP1047602 |  | 2019-03-18 | 2019-05-20 | CNS Sapper Construction | W9128F19C0023 | 8623365 | 8671865 | 2019-06-19 | 2020-08-21
2022-07-31 | 2020 | Air Force Active | SGBP212904 |  | 2021-07-01 | 2021-09-29 | Medvolt-Komada JV | W9128F21C0066 | 17521500 | 17521500 | 2023-07-20 | 2023-07-20
2022-07-31 | 2020 | Air Force Active | SGBP212907 |  | 2021-06-29 | 2021-12-15 | FSA Construction LLC | W9128F22C0006 | 12851627 | 12851627 | 2022-01-14 | 2023-09-20
2022-07-31 | 2020 | Air Force Active | SGBP212908 |  | 2021-06-24 | 2021-09-22 | Covenant Russell LLC | W9128F21C0056 | 3736863 | 3736863 | 2023-07-27 | 2023-07-27
2022-07-31 | 2019 | Air Force Active | SMYU073011 |  | 2019-06-27 | 2019-09-27 | Kumsung Construction Co., Ltd | W912UM19C0017 | 1227670 | 1227670 | 2021-02-21 | 2021-08-30
2022-07-31 | 2017 | Air Force Active | SXHT013001 |  | 2017-02-16 | 2017-06-01 | LEEBC O R SER VIC ES, LLC | W9127816D0033 | 12383350 | 12447196 | 2019-03-12 | 2021-06-01
2022-07-31 | 2019 | Air Force Active | SXHT023007 |  | 2021-03-08 | 2022-04-26 | EMR Inc | W9127822C0016 | 12265000 | 12265000 | 2023-11-25 | 2024-03-05
2022-07-31 | 2018 | Air Force Active | TDKA063002D |  | 2018-11-07 | 2019-08-16 | JE Hurley Inc | W9128F19R0006 | 3888005 | 3934966 | 2020-12-02 | 2020-12-28
2022-07-31 | 2020 | Air Force Active | TDKA143002 |  | 2020-10-06 | 2021-04-27 | JE Dunn | W9128F21C0019 | 43789430 | 43789430 | 2023-09-11 | 2023-09-11
2022-07-31 | 2012 | Air Force Active | TYFR063017 |  | 2012-03-01 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541693 | 29662433 | 2017-01-18 | 2026-06-18
2022-07-31 | 2020 | Air Force Active | TYMX103001 |  | 2021-04-23 | 2021-07-22 | Joeris General Contractors, Ltd | W9126G21C0016 | 27589000 | 27589000 | 2023-07-30 | 2023-03-07
2022-07-31 | 2018 | Air Force Active | UHHZ163000 |  | 2018-12-12 | 2020-05-20 | Hensel Phelps, Orlando, FL | W912HN20F4009 | 10827560 | 10827560 | 2021-12-10 | 2021-12-10
2022-07-31 | 2019 | Air Force Active | ULDF123001 |  | 2019-07-18 | 2020-01-17 | FOUR TRIBES ENTERPRISES, LLC | W912DS20C0005 | 13147968 | 13620457 | 2021-08-03 | 2022-08-15
2022-07-31 | 2017 | Air Force Active | VDYD101053 |  | 2020-02-24 | 2020-07-29 | River City Construction, LLC/East Peoria IL | W912QR20C0028 | 30100000 | 30100000 | 2023-03-08 | 2024-01-10
2022-07-31 | 2020 | Air Force Active | VDYD1055428 |  | 2021-04-19 | 2021-07-08 | Zodiac-Poettker HBZ Construction JV | W912QR21C0021 | 72713000 | 72713000 | 2021-08-07 | 2023-06-30
2022-07-31 | 2020 | Air Force Active | VDYD1074289 |  | 2019-08-05 | 2021-04-08 | Litteken Construction Compancy | W912QR21C0005 | 3433700 | 3433700 | 2021-05-08 | 2023-06-26
2022-07-31 | 2016 | Air Force Active | VKAG013004R5 |  | 2017-08-21 | 2019-06-28 | Source Selection Sensitive | W912HN19C3006 | 23716745 | 23716745 | 2019-07-28 | 2021-11-15
2022-07-31 | 2020 | Air Force Active | VKAG193002 |  | 2021-06-30 | 2021-09-28 | Group III Mgt, Inc. | W912HN21C3008 | 4883000 | 4883000 | 2023-02-06 | 2023-02-06
2022-07-31 | 2019 | Air Force Active | VLSB193001 |  | 2020-08-11 | 2020-12-30 | MQ9 MCE Group | N6945021C004 | 49312181 | 49312181 | 2022-12-16 | 2023-03-01
2022-07-31 | 2022 | Air Force Active | VNVP063002 |  | 2021-11-15 | 2022-05-06 | CNS Southwind Construction Services LLC | W912BV22C0012 | 21716833 | 21716833 | 2023-08-04 | 2024-03-01
2022-07-31 | 2016 | Air Force Active | WWYK093003 |  | 2016-09-09 | 2017-03-13 | Walsh Federal JV (Chicago/IL) | W912BV17C0005 | 12472000 | 12809463 | 2018-11-08 | 2021-04-14
2022-07-31 | 2015 | Air Force Active | WWYK153005 |  | 2015-03-05 | 2017-03-30 | Walsh Federal Alberici JV | W912BV17C0004 | 97939000 | 98825383 | 2019-04-30 | 2021-11-19
2022-07-31 | 2018 | Air Force Active | WWYK173005 |  | 2020-06-25 | 2020-09-23 | Southwind Construction | W912BV18D0019 | 3899405 | 4667304 | 2021-12-03 | 2022-09-30
2022-07-31 | 2019 | Air Force Active | WWYK193001 |  | 2018-08-31 | 2019-08-29 | Korte | W912BV19C0015 | 69771792 | 69771792 | 2022-03-19 | 2023-02-07
2022-07-31 | 2017 | Air Force Active | WWYK193003 |  | 2017-12-22 | 2019-02-07 | Record Steel and Construction | W912BV19C0002 | 24873819 | 24873819 | 2020-11-24 | 2022-06-17
2022-07-31 | 2019 | Air Force Active | WWYK193014 |  | 2018-10-01 | 2019-09-27 | Korte Const Co | W912BV19C0017 | 71921672 | 71921672 | 2022-03-20 | 2023-02-22
2022-07-31 | 2020 | Air Force Active | XDAT1026962 |  | 2020-06-20 | 2020-07-16 | J.I. Garcia Construction Inc. Travis AFB KC-46A Alter B881, B885 & B887 Squadron Ops/AMU | N6247318D5817 | 5158710 | 5158710 | 2021-10-09 | 2022-04-30
2022-07-31 | 2020 | Air Force Active | XDAT1030576 |  | 2020-10-13 | 2021-05-06 | COFFMAN SPECIALTIES, INC | N6247913D2439 | 4045000 | 4045000 | 2021-11-12 | 2021-11-12
2022-07-31 | 2020 | Air Force Active | XDAT1046451 |  | 2020-03-27 | 2021-03-15 | Company SOLTEK | N6247321F4392 | 21960000 | 21960000 | 2021-04-14 | 2023-03-10
2022-07-31 | 2018 | Air Force Active | XDAT1051930 |  | 2018-10-26 | 2019-12-30 | LLC Walsh Federal | N6247320C0613 | 129264610 | 129264610 | 2022-06-17 | 2023-02-26
2022-07-31 | 2020 | Air Force Active | XDAT1074510 |  | 2020-08-31 | 2021-09-02 | RA Burch Company | N6246321F5351 | 17000000 | 17000000 | 2021-10-02 | 2023-12-11
2022-07-31 | 2021 | Air Force Active | XDAT173002 |  | 2019-05-12 | 2021-06-30 | Gideon Contracting | N6247319D1222 | 4339865 | 4339865 | 2021-07-30 | 2022-10-22
2022-07-31 | 2020 | Air Force Active | XLWU193004 |  | 2022-03-14 | 2022-04-13 | Howard W Pence Inc | W9127822C0014 | 17373320 | 17373320 | 2024-02-17 | 2024-04-24
2022-07-31 | 2019 | Air Force Active | XLWU193005 |  | 2019-08-12 | 2019-09-23 | Green Simmons Company INC | W9127819F0486 | 12369134 | 12369134 | 2021-11-09 | 2022-12-14
2022-07-31 | 2019 | Air Force Active | XLWU193006 |  | 2019-08-26 | 2019-09-26 | Southeast Cherokee Const INC | W9127810518 | 16624000 | 16614000 | 2021-11-02 | 2022-08-30
2022-07-31 | 2020 | Air Force Active | XLWU203002 |  | 2022-01-30 | 2022-03-31 | EMR, Inc. | W9127822C0010 | 100323520 | 100323520 | 2025-09-27 | 2026-02-06
2022-07-31 | 2020 | Air Force Active | XLWU203004 |  | 2021-07-23 | 2021-11-05 | Hensel Phelps Construction Co | W912HN21D3002 | 145433512 | 145433512 | 2024-08-26 | 2024-12-24
2022-07-31 | 2019 | Air Force Active | XLWU203006 |  | 2020-07-24 | 2020-09-25 | Inc Caddell | W912HN20D3003 | 31587290 | 31587290 | 2022-09-16 | 2022-12-15
2022-07-31 | 2020 | Air Force Active | XLWU203010 |  | 2021-07-29 | 2022-02-17 | CNS B.L. Harbert International, LLC | W9127822C0004 | 80656597 | 80656597 | 2024-09-26 | 2024-12-29
2022-07-31 | 2020 | Air Force Active | XLWU203011 |  | 2021-05-06 | 2022-02-01 | CNS EMR, Inc | W9127822C007 | 32539053 | 32539053 | 2024-05-03 | 2024-08-01
2022-07-31 | 2020 | Air Force Active | XLWU203012 |  | 2022-03-26 | 2022-05-25 | The Haskell Company | W9127822C0011 | 33325503 | 33325503 | 2024-05-15 | 2024-10-02
2022-07-31 | 2019 | Air Force Active | XLWU203013 |  | 2022-03-11 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 106810853 | 106810853 | 2024-12-16 | 2025-08-14
2022-07-31 | 2020 | Air Force Active | XLWU203014 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 86610671 | 86610671 | 2025-04-15 | 2025-12-12
2022-07-31 | 2020 | Air Force Active | XLWU203015 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 83476966 | 83476966 | 2025-08-13 | 2026-04-11
2022-07-31 | 2019 | Air Force Active | XLWU203016 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 69247953 | 69247953 | 2025-06-14 | 2026-02-10
2022-07-31 | 2020 | Air Force Active | XLWU203017 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 42273259 | 42273259 | 2025-05-15 | 2026-01-11
2022-07-31 | 2020 | Air Force Active | XLWU203018 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 44529014 | 44529014 | 2025-08-11 | 2025-12-12
2022-07-31 | 2020 | Air Force Active | XLWU203019 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 43521212 | 43521212 | 2025-03-16 | 2025-11-12
2022-07-31 | 2020 | Air Force Active | XLWU203025 |  | 2021-03-31 | 2021-07-12 | CNS Southeastern Industrial Barlovento JV-2, LLC | W9127821C0027 | 8039675 | 8039675 | 2023-03-27 | 2023-06-25
2022-07-31 | 2020 | Air Force Active | XLWU203026 |  | 2022-03-12 | 2022-05-11 | BL Harbert International, LLC | W9127822F0121 | 95169558 | 95169558 | 2024-08-23 | 2025-01-03
2022-07-31 | 2020 | Air Force Active | XLWU203028 |  | 2020-12-11 | 2021-06-25 | BL Harbert International, LLC | W912HN21D3000 | 104192393 | 104192393 | 2024-04-20 | 2024-08-27
2022-07-31 | 2020 | Air Force Active | XLWU203030 |  | 2021-05-06 | 2021-07-28 | Dawson Enterprises, LLC | W9127820R0047 | 35659204 | 35659204 | 2024-04-03 | 2024-04-02
2022-07-31 | 2020 | Air Force Active | XLWU203033 |  | 2021-03-19 | 2021-08-30 | Roundhouse PBN, LLC | W9127821C0028 | 15921736 | 15921736 | 2023-08-23 | 2023-11-21
2022-07-31 | 2020 | Air Force Active | XLWU203034 |  | 2021-07-26 | 2021-09-24 | CNS B.L. Harbert International, LLC | W912HN21D3000 | 25593168 | 25593168 | 2023-09-28 | 2023-12-27
2022-07-31 | 2020 | Air Force Active | XLWU203038 |  | 2022-03-11 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 32493777 | 32493777 | 2025-10-12 | 2026-06-10
2022-07-31 | 2020 | Air Force Active | XLWU203040 |  | 2021-02-09 | 2021-08-13 | CNS 4K Global-ACC JV, LLC | W9127821C0029 | 9703525 | 9703525 | 2023-06-26 | 2024-10-02
2022-07-31 | 2019 | Air Force Active | XLWU203041 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 51509161 | 51509161 | 2024-12-16 | 2025-08-14
2022-07-31 | 2020 | Air Force Active | XLWU203044 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 42950855 | 42950855 | 2024-12-16 | 2025-07-14
2022-07-31 | 2019 | Air Force Active | XLWU203045 |  | 2022-03-14 | 2022-05-13 | The Lane Construction Corporation | W9127822C0017 | 317731861 | 317731861 | 2026-05-06 | 2026-10-23
2022-07-31 | 2020 | Air Force Active | XLWU203046 |  | 2021-04-28 | 2021-09-08 | CNS EMR, Inc | W9127822C007 | 22097308 | 22097308 | 2023-10-13 | 2024-11-13
2022-07-31 | 2020 | Air Force Active | XLWU203047 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 40551031 | 40551031 | 2025-02-14 | 2025-10-13
2022-07-31 | 2020 | Air Force Active | XLWU203050 |  | 2022-03-07 | 2022-05-06 | The Lane Construction Corporation | W9127822C0017 | 402216042 | 402216042 | 2026-04-26 | 2026-10-23
2022-07-31 | 2018 | Air Force Active | XQPZ164001 |  | 2020-04-16 | 2020-08-21 | Bryan Construction | W9128F20C0038 | 26744525 | 26827768 | 2023-08-13 | 2024-01-08
2022-07-31 | 2020 | Air Force Active | XQPZ174006 |  | 2020-09-23 | 2021-01-29 | JBI Inc | W9128F21C0013 | 5040100 | 5040100 | 2023-02-27 | 2023-05-28
2022-07-31 | 2016 | Air Force Active | YANB144533 |  | 2019-12-19 | 2020-03-18 | LBB Kaiserslautern | W912GB16C0017 | 7128197 | 7128197 | 2021-04-01 | 2024-05-23
2022-07-31 | 2016 | Air Force Active | YWHG031002R2 |  | 2018-07-02 | 2019-01-31 | YWHG031002R2, Consolidated Stealth Operations & Nuclear Alert Facility | W912DQ19C4001 | 26957316 | 26957316 | 2020-08-15 | 2021-09-15
2022-07-31 | 2020 | Air Force Active | YWHG1030692 |  | 2021-03-04 | 2021-07-29 | L. S. Black | W912DQ21C4002 | 26470911 | 26470911 | 2023-09-01 | 2023-09-01
2022-07-31 | 2018 | Air Force Active | YWHG163100 |  | 2021-09-09 | 2021-11-12 | CNS Vazquez Reasbeck Construction LLC | FA462522F0009 | 5269467 | 5269467 | 2023-04-29 | 2023-09-04
2022-07-31 | 2021 | Air Force Active | YWHG193001 |  | 2020-12-21 | 2021-08-16 | Howard W Pence Inc | W912DQ21C4003 | 5505523 | 5505523 | 2021-09-15 | 2022-11-04
2022-07-31 | 2019 | Air Force Active | ZHTV093301 |  | 2019-07-17 | 2019-11-19 | DSG Source Selection Sensitive | W912QR19C0027 | 2060830 | 2060830 | 2020-10-14 | 2023-01-22
2022-07-31 | 2018 | Air Force Active | ZHTV153201 |  | 2020-02-06 | 2020-04-14 | Butt Construction | W912QR20C0011 | 7105735 | 7105735 | 2021-09-03 | 2022-08-30
2022-07-31 | 2020 | Air Force Active | ZNRE2031002 |  | 2021-04-16 | 2022-02-17 | Tokyu Construction Co., Ltd. | W912HV22C0003 | 16117926 | 16117926 | 2024-01-11 | 2024-04-12
2022-07-31 | 2020 | Air Force Active | ZNRE204308 |  | 2020-02-05 | 2020-08-18 | Nippo Corporation | W912HV17D001520F004 | 9480795 | 9480795 | 2022-09-06 | 2023-01-05
2022-07-31 | 2022 | Air Force Active | ZNRE254300 |  | 2021-10-06 | 2022-04-29 | Gilbane Japan GK | W912HV22C0002 | 43296723 | 43296723 | 2022-05-29 | 2024-10-30
2022-07-31 | 2020 | Air Force Reserve | AJXF223744 |  | 2020-06-01 | 2020-09-23 | Kinsley Construction, Inc. | W912QR20C0049 | 9992147 | 9992147 | 2022-05-26 | 2022-06-23
2022-07-31 | 2018 | Air Force Reserve | AWUB105005 |  | 2018-07-12 | 2019-03-30 | Justin J. Reeves, L.L.C. | N6945019C2105 | 2907892 | 2907892 | 2020-03-31 | 2021-08-27
2022-07-31 | 2019 | Air Force Reserve | CTGB169002 |  | 2019-04-23 | 2019-08-01 | NISOU LGC JV, LLC | W912QR19C0026 | 9928185 | 9928185 | 2020-10-27 | 2022-05-13
2022-07-31 | 2019 | Air Force Reserve | CTGB989003 |  | 2020-06-01 | 2020-09-16 | Messer Construction Co. | W912QR20C0039 | 11471000 | 11471000 | 2022-05-04 | 2022-10-31
2022-07-31 | 2018 | Air Force Reserve | DDPM130007 |  | 2018-06-29 | 2018-12-12 | Unified Sevices of Texas, Inc. | N6945019F1275 | 2179491 | 2179491 | 2020-09-14 | 2021-01-31
2022-07-31 | 2021 | Air Force Reserve | DDPM414396 |  | 2021-06-01 | 2021-09-29 | Conti Federal Services, Inc. | N6945021C0038 | 11259595 | 11259595 | 2024-09-30 | 2024-09-30
2022-07-31 | 2021 | Air Force Reserve | DDPM414415 |  | 2021-06-01 | 2021-09-29 | Conti Federal Services, Inc. | N6945021C0038 | 16788096 | 16788096 | 2024-09-30 | 2024-09-30
2022-07-31 | 2016 | Air Force Reserve | FGWB009002 |  | 2017-01-06 | 2017-09-21 | DRACE CONSTRUCTION COMPANY | W912QR17C0038 | 9397411 | 10249989 | 2019-06-06 | 2022-03-09
2022-07-31 | 2018 | Air Force Reserve | KNMD624007 |  | 2020-09-01 | 2020-12-17 | Hensel Phelps Construction Co. | N6247820D4003 | 8552000 | 8552000 | 2022-07-11 | 2022-11-30
2022-07-31 | 2019 | Air Force Reserve | MAHG063004 |  | 2019-10-01 | 2019-12-11 | EMR, Inc. | N6945020F0870 | 5057057 | 5057057 | 2020-10-31 | 2021-08-30
2022-07-31 | 2016 | Air Force Reserve | PDPG120514 |  | 2018-08-20 | 2018-09-14 | Lead Builders Inc | W912QR18C0031 | 4968200 | 5056600 | 2019-11-08 | 2021-05-31
2022-07-31 | 2021 | Air Force Reserve | QJKL100004 |  | 2021-06-01 | 2021-09-22 | L.S.Black Construction, LLC | W912QR21C0043 | 10511086 | 10511086 | 2023-09-22 | 2023-09-22
2022-07-31 | 2019 | Air Force Reserve | RVKQ079104 |  | 2019-04-29 | 2019-07-03 | LGC Global, Inc. | W912QR19C0021 | 11311046 | 11333785 | 2021-07-23 | 2021-12-08
2022-07-31 | 2018 | Air Force Reserve | SXHT103001 |  | 2018-03-01 | 2018-05-25 | Ashford Leebcor Enterpises, LLC | W912QR18C0018 | 25242688 | 22626925 | 2020-07-19 | 2022-05-31
2022-07-31 | 2019 | Air Force Reserve | SXHT171217 |  | 2019-06-24 | 2019-09-28 | Roundhouse PBN | W912QR17C0049 | 2863596 | 2863596 | 2021-03-15 | 2021-08-12
2022-07-31 | 2019 | Air Force Reserve | SXHT203000 |  | 2020-06-01 | 2022-03-22 | Patriot Construction | W912QR20C0050 | 20438870 | 20438870 | 2024-03-21 | 2024-04-01
2022-07-31 | 2018 | Air Force Reserve | UHHZ073003 |  | 2019-06-28 | 2019-09-24 | ACC Construction Company, Inc. | W912QR19C0042 | 32093710 | 28917160 | 2021-11-26 | 2022-09-20
2022-07-31 | 2020 | Air Force Reserve | UHHZ073005 |  | 2020-11-15 | 2021-01-29 | ACC Construction Company, Inc. | W912QR19C0009 | 31229066 | 31229066 | 2023-04-11 | 2023-06-24
2022-07-31 | 2017 | Air Force Reserve | VKAG159021 |  | 2017-05-19 | 2017-09-27 | Walbridge Aldinger LLC | W912QR17C0031 | 52493799 | 58903514 | 2020-09-09 | 2021-08-31
2022-07-31 | 2018 | Air Force Reserve | VKAG159026 |  | 2020-06-01 | 2020-09-29 | Ocean Construction Services, Inc. | W912QR20C0056 | 4628152 | 4628152 | 2022-07-08 | 2022-10-06
2022-07-31 | 2018 | Air Force Reserve | YTPM059004 |  | 2019-04-08 | 2019-08-01 | P & S Construction, Inc. | W912QR19C0020 | 10383981 | 9832232 | 2020-12-12 | 2021-08-12
2022-07-31 | 2019 | Air Force Reserve | YTPM099001B |  | 2019-07-26 | 2021-06-17 | Ciambro AZ JV | W912QR21C0025 | 46421000 | 46421000 | 2023-09-29 | 2023-09-29
2022-07-31 | 2021 | Air National Guard | AJXF189013 |  | 2022-01-24 | 2022-06-14 | Corenic Construction Group, LLC | W50S8W22C0003 | 15948509 | 14064852 | 2024-01-11 | 2024-01-11
2022-07-31 | 2018 | Air National Guard | CEKT149052 |  | 2018-06-30 | 2018-12-18 | LAROSA BUILDING GROUP, LLC | W91ZRS18R50010002 | 4979466 | 4990118 | 2024-12-26 | 2024-12-26
2022-07-31 | 2021 | Air National Guard | DPEZ029038 |  | 2021-04-23 | 2021-11-15 | Razor Cosulting | W50S8W22C0001 | 5527675 | 5375875 | 2023-02-28 | 2023-02-28
2022-07-31 | 2021 | Air National Guard | DPEZ189031 |  | 2021-07-22 | 2022-04-15 | Cora Jane | W50S8W22C0003 | 4588267 | 4470000 | 2023-08-08 | 2023-08-08
2022-07-31 | 2021 | Air National Guard | FAKZ189019 |  | 2021-10-28 | 2022-07-26 | Bear Brothers, INC | W50S6N22C0001 | 18205428 | 17736650 | 2024-06-29 | 2024-06-29
2022-07-31 | 2021 | Air National Guard | FAKZ999088 |  | 2021-10-28 | 2022-07-26 | BEAR BROTHERS, INC | W50S6N22C0001 | 19564393 | 19021500 | 2024-06-20 | 2024-06-20
2022-07-31 | 2020 | Air National Guard | FJRP189050 |  | 2021-05-14 | 2021-09-24 | Showalter Construction Company | W50S8721C5001 | 3279911 | 3216900 | 2022-08-20 | 2022-08-20
2022-07-31 | 2021 | Air National Guard | FJRP199040 |  | 2021-05-19 | 2021-09-30 | Brantley Construction Services LLC | W50S8721C5002 | 4690132 | 4598700 | 2023-03-10 | 2023-03-10
2022-07-31 | 2018 | Air National Guard | FMKM119035 |  | 2020-09-28 | 2021-04-19 | Max Gray Construction | W912LM21C0002 | 2439785 | 2466453 | 2022-10-11 | 2022-10-11
2022-07-31 | 2019 | Air National Guard | FMKM179063 |  | 2021-06-01 | 2021-10-06 | Max Gray Construction | W912LM21R10010002 | 6397054 | 6232840 | 2022-10-31 | 2022-10-31
2022-07-31 | 2018 | Air National Guard | HAAW179035 |  | 2020-04-30 | 2020-07-14 | SJ Thomas Co Inc | W50S8N20C0001 | 3428805 | 3568344 | 2021-08-08 | 2021-08-08
2022-07-31 | 2019 | Air National Guard | JLQN049119 |  | 2019-02-18 | 2019-06-01 | A. WBE-CCI Joint Venture One, LLC | W91SMC19C6001 | 8184676 | 7905803 | 2023-10-18 | 2023-10-18
2022-07-31 | 2018 | Air National Guard | KJAQ159096 |  | 2020-09-23 | 2021-02-19 | Ahtna Environmental Inc | W50S8Z21C0001 | 7873129 | 7694265 | 2022-05-05 | 2022-05-05
2022-07-31 | 2020 | Air National Guard | KJAQ179127 |  | 2021-08-28 | 2022-02-23 | Diversified Contractors, Inc | W50S8Z22F0001 | 3154571 | 3154571 | 2023-03-15 | 2023-03-15
2022-07-31 | 2021 | Air National Guard | KKGA169022 |  | 2021-03-16 | 2021-07-20 | Gast Construction | W901UZ21C0001 | 13557321 | 13302869 | 2022-07-20 | 2022-07-20
2022-07-31 | 2018 | Air National Guard | KNMD179040 |  | 2018-06-15 | 2019-05-07 | HI Technology Devel. Corp. | W912J61822021 | 3126987 | 2868023 | 2021-05-23 | 2021-05-23
2022-07-31 | 2019 | Air National Guard | KNMD189008 |  | 2019-06-24 | 2020-08-07 | Pacific Federal Contractors, LLC | W912J620C0001 | 20236741 | 18467656 | 2023-03-05 | 2023-03-05
2022-07-31 | 2019 | Air National Guard | LKLW099101 |  | 2019-06-24 | 2019-08-12 | State of PA per MCCA | 42190131 | 6923749 | 6767841 | 2021-11-07 | 2021-11-07
2022-07-31 | 2018 | Air National Guard | LRXQ159097 |  | 2021-06-24 | 2021-09-29 | Codaray Construction | W9127Q21C0015 | 7233035 | 7277117 | 2022-12-28 | 2022-12-28
2022-07-31 | 2018 | Air National Guard | LUXC099042 |  | 2021-12-09 | 2022-04-25 | Peska Construction, Inc | W50S9622C0001 | 15713360 | 15109000 | 2024-03-05 | 2024-03-05
2022-07-31 | 2019 | Air National Guard | MUHJ179000 |  | 2020-11-03 | 2020-12-23 | Ocean Construction Services | W9123621C2013 | 7644604 | 6748367 | 2023-01-31 | 2023-01-31
2022-07-31 | 2020 | Air National Guard | PBXP169102 |  | 2020-10-28 | 2021-04-02 | Massillon Construction & Supply, LLC | W50S8R21C0002 | 2279117 | 2160653 | 2022-02-26 | 2022-02-26
2022-07-31 | 2019 | Air National Guard | PBXP929798 |  | 2019-10-25 | 2020-02-18 | CANCO, LLC | W50S8R20C0003 | 10316495 | 10365100 | 2022-05-25 | 2022-05-25
2022-07-31 | 2021 | Air National Guard | PJVY199001 |  | 2021-07-01 | 2022-01-28 | MCW-TMG1, LLC | W50S8V22C0001 | 5806562 | 5655736 | 2025-05-12 | 2025-05-12
2022-07-31 | 2019 | Air National Guard | PSTE089064 |  | 2020-08-13 | 2021-09-30 | CCCS International LLC | W912QG21C0004 | 4748809 | 4571407 | 2023-10-30 | 2023-10-30
2022-07-31 | 2018 | Air National Guard | PSTE139022 |  | 2019-04-04 | 2019-09-30 | Expert Maintenance & Construction Services | W912QG19C0006 | 3123581 | 3086615 | 2021-04-22 | 2021-04-22
2022-07-31 | 2018 | Air National Guard | PSXE999132 |  | 2018-06-08 | 2019-08-05 | Messer Construction Company | W912L719C7001 | 29613217 | 31614446 | 2021-08-22 | 2021-08-22
2022-07-31 | 2020 | Air National Guard | QMSN199056 |  | 2020-07-24 | 2021-03-24 | Thompson Builders Corporation | W50S8X21C0001 | 55702065 | 54219500 | 2022-10-17 | 2022-10-17
2022-07-31 | 2019 | Air National Guard | RQLH059034 |  | 2020-08-20 | 2021-03-11 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945021C0005 | 7261649 | 6401000 | 2024-10-01 | 2024-10-01
2022-07-31 | 2019 | Air National Guard | RQLH189009 |  | 2020-08-20 | 2021-03-11 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945021C0005 | 21831459 | 19244906 | 2024-10-01 | 2024-10-01
2022-07-31 | 2022 | Air National Guard | SZCQ169264 |  | 2021-12-20 | 2022-04-12 | P&S Construction INC | W912WJ22F0052 | 3124366 | 2675744 | 2023-11-03 | 2023-11-03
2022-07-31 | 2018 | Air National Guard | TDKA169004 |  | 2020-07-17 | 2021-03-01 | Qayaq Gov. Solutions | W50S6V21C0001 | 8176132 | 7891745 | 2022-03-26 | 2022-03-26
2022-07-31 | 2020 | Air National Guard | TUMR189003 |  | 2020-12-17 | 2021-08-19 | QB GROUP LLC | N6945021C0031 | 9201235 | 7791000 | 2024-01-29 | 2024-01-29
2022-07-31 | 2020 | Air National Guard | TUMR189004 |  | 2020-12-17 | 2021-08-19 | QB GROUP LLC | N6945021C0031 | 31741307 | 27230000 | 2024-01-29 | 2024-01-29
2022-07-31 | 2018 | Air National Guard | ULYB049040 |  | 2019-07-02 | 2019-08-21 | Lee Grover Construction | W912NS19C6003 | 6052456 | 6157565 | 2021-03-23 | 2021-03-23
2022-07-31 | 2018 | Air National Guard | ULYB049040 |  | 2019-04-28 | 2019-09-25 | MCON, LLC | 413180 | 3025568 | 3022957 | 2020-05-01 | 2020-08-09
2022-07-31 | 2020 | Air National Guard | ULYB169010 |  | 2020-06-09 | 2020-09-02 | Lee Grover | W50S7G20C0001 | 5962100 | 6214088 | 2022-03-31 | 2022-03-31
2022-07-31 | 2020 | Air National Guard | XDQU109057 |  | 2020-06-23 | 2020-09-25 | Ashford Leebcor Enterprises IV LLC | W50S7020C0002 | 20213955 | 22055630 | 2022-01-23 | 2022-06-07
2022-07-31 | 2020 | Air National Guard | XGFG189001 |  | 2020-08-20 | 2021-04-15 | J. H. FINDORFF & SON, INC. | W50S9F21C0001 | 10552313 | 9319884 | 2023-01-07 | 2023-01-07
2022-07-31 | 2020 | Air National Guard | XGFG189004 |  | 2020-11-04 | 2021-07-19 | CONTI FEDERAL SERVICES, INC | W9128F21C0039 | 21978910 | 19703059 | 2022-11-11 | 2022-11-11
2022-07-31 | 2021 | Air National Guard | XHEA189054 |  | 2021-03-29 | 2021-08-30 | Granite Construction Compnay | F9K3CE1084MW01 | 4329586 | 3350722 | 2022-08-30 | 2022-08-30
2022-07-31 | 2019 | Army Active | 33584 |  | 2020-10-13 | 2021-03-26 | SGS, LLC | W9126G21C0005 | 44927000 | 45652000 | 2023-12-11 | 2024-11-22
2022-07-31 | 2019 | Army Active | 35782 |  | 2019-08-09 | 2019-09-26 | P & R JV | W912QR19C0039 | 45794000 | 47921000 | 2022-02-05 | 2023-03-30
2022-07-31 | 2019 | Army Active | 52203 |  | 2020-02-27 | 2020-09-29 | Kiewit Infrastructure West Co. | W9128A20C0006 | 44925000 | 46159000 | 2022-08-03 | 2022-06-17
2022-07-31 | 2018 | Army Active | 55112 |  | 2018-08-14 | 2019-02-22 | ACC Construction Co. | W912HN19C3003 | 21437000 | 22411000 | 2020-10-08 | 2022-07-07
2022-07-31 | 2018 | Army Active | 55199 |  | 2018-07-11 | 2019-10-15 | WHH Nisqually-Garco JV | W912DW20C0001 | 21087000 | 22111000 | 2021-11-29 | 2022-05-22
2022-07-31 | 2021 | Army Active | 55516 |  | 2021-02-12 | 2021-05-28 | ACC | W912HN21C3004 | 62212000 | 62809000 | 2023-07-05 | 2023-07-05
2022-07-31 | 2020 | Army Active | 59766 |  | 2020-08-05 | 2021-09-15 | Structural Associates, Inc. | W912DS21C0015 | 27331000 | 27331000 | 2023-10-18 | 2023-10-18
2022-07-31 | 2014 | Army Active | 59779 |  | 2016-02-24 | 2016-07-28 | San Juan Construction, Inc. | W9128A-16-C-0006 | 54844000 | 57844000 | 2020-06-10 | 2024-12-12
2022-07-31 | 2020 | Army Active | 60276 |  | 2020-02-13 | 2021-04-30 | M. A. Mortenson Company | W9123621C2024 | 63845000 | 64004000 | 2024-05-31 | 2024-05-31
2022-07-31 | 2018 | Army Active | 61147 |  | 2018-06-20 | 2019-11-15 | Walsh Federal JV | W912DW20C0002 | 77308000 | 79436000 | 2022-08-22 | 2022-10-23
2022-07-31 | 2019 | Army Active | 61388 |  | 2019-03-15 | 2019-06-14 | ETERNA SA | W9127819C0019 | 18881000 | 18977000 | 2022-07-14 | 2022-02-16
2022-07-31 | 2017 | Army Active | 62380 |  | 2018-08-13 | 2018-09-22 | Staatliches Hochbauamt Amberg | W912GB-16-C-0007 | 20950000 | 23458000 | 2022-05-11 | 2023-07-15
2022-07-31 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan | W912HV-14-C-0007 | 84367000 | 86472000 | 2021-06-09 | 2022-10-22
2022-07-31 | 2020 | Army Active | 62856 |  | 2020-04-14 | 2020-07-21 | Walsh Motor City JV | W912QR20C0027 | 22344000 | 23010000 | 2022-10-28 | 2022-10-28
2022-07-31 | 2019 | Army Active | 62866 |  | 2019-07-12 | 2019-09-30 | MVL USA Inc | W912ER19C0018 | 25397000 | 25452000 | 2021-05-02 | 2022-06-30
2022-07-31 | 2019 | Army Active | 63054 |  | 2019-07-26 | 2019-09-27 | Benard Associates, Inc | W912DS19C0033 | 25164000 | 30449000 | 2021-11-03 | 2022-11-30
2022-07-31 | 2019 | Army Active | 64296 |  | 2021-04-16 | 2022-02-24 | Walsh Federal LLC | W912QR22C0004 | 30521000 | 30521000 | 2024-02-21 | 2024-02-21
2022-07-31 | 2018 | Army Active | 65699 |  | 2018-08-16 | 2018-09-30 | Leebcor Services, LLC | W91278-16-D-0033 | 16707000 | 18188000 | 2020-10-28 | 2021-11-30
2022-07-31 | 2013 | Army Active | 68530 |  | 2015-05-02 | 2015-09-23 | Solis Constructors, Inc. | W9126G-14-D-0050 | 37657000 | 58068000 | 2018-12-17 | 2022-12-15
2022-07-31 | 2020 | Army Active | 69347 |  | 2020-02-06 | 2020-05-20 | B.L. Harbert Internationl | W912QR20C0022 | 37142000 | 40610000 | 2022-07-11 | 2022-11-16
2022-07-31 | 2015 | Army Active | 70668 |  | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 343799000 | 2021-11-07 | 2022-11-25
2022-07-31 | 2018 | Army Active | 70668 | 58857 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 343799000 | 2021-11-07 | 2022-11-25
2022-07-31 | 2017 | Army Active | 70668 | 76593 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 343799000 | 2021-11-07 | 2022-11-25
2022-07-31 | 2019 | Army Active | 70668 | 76595 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 343799000 | 2021-11-07 | 2022-11-25
2022-07-31 | 2020 | Army Active | 70668 | 92340 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 343799000 | 2021-11-07 | 2022-11-25
2022-07-31 | 2017 | Army Active | 70935 |  | 2021-07-28 | 2021-09-30 | John C. Grimberg Co., Inc. | W912DR21C0057 | 20150000 | 20150000 | 2024-04-24 | 2024-04-24
2022-07-31 | 2020 | Army Active | 73391 |  | 2020-06-12 | 2020-09-29 | Purcell Construction | W9123620C2027 | 47269000 | 47364000 | 2022-11-03 | 2022-11-03
2022-07-31 | 2017 | Army Active | 74877 |  | 2020-10-28 | 2021-08-19 | Walsh Federal LLC | W9123821C0011 | 13438000 | 13438000 | 2022-11-26 | 2023-02-24
2022-07-31 | 2019 | Army Active | 75157 |  | 2020-05-22 | 2020-08-13 | NASCO | W9126G20C0005 | 8315000 | 8403000 | 2022-02-25 | 2022-07-11
2022-07-31 | 2016 | Army Active | 75661 |  | 2017-11-30 | 2018-12-14 | Harper Construction | W912BV19C0003 | 59467000 | 59467000 | 2020-12-26 | 2022-04-22
2022-07-31 | 2018 | Army Active | 75718 |  | 2018-07-02 | 2019-05-09 | Tocci Building Corporation | W912WJ19C0011 | 20612000 | 26382000 | 2021-07-02 | 2022-02-18
2022-07-31 | 2015 | Army Active | 76093 |  | 2018-06-29 | 2019-05-31 | ARS Aleut Construction, LLC | W9123819C0015 | 8916000 | 10893000 | 2020-06-02 | 2022-05-27
2022-07-31 | 2020 | Army Active | 76673 |  | 2020-06-29 | 2020-11-10 | Turner Construction Co, Inc | W9127821C0006 | 34050000 | 35410000 | 2022-12-25 | 2022-12-25
2022-07-31 | 2021 | Army Active | 76897 |  | 2021-02-10 | 2021-09-21 | Hensel Phelps Construction Co. | W9128A21C0007 | 76594000 | 78583000 | 2024-10-12 | 2024-10-12
2022-07-31 | 2018 | Army Active | 77102 |  | 2018-03-15 | 2018-09-21 | Creative Times Dayschool, Inc | W912PL-18-C-0036 | 20265000 | 23382000 | 2020-06-05 | 2022-01-25
2022-07-31 | 2019 | Army Active | 77301 |  | 2019-04-03 | 2019-08-09 | Federal/Bryan | W9128F19C0029 | 69147000 | 71029000 | 2021-05-04 | 2021-10-15
2022-07-31 | 2020 | Army Active | 77303 |  | 2020-02-28 | 2020-06-19 | TEPA EC | W9128F20C0029 | 46209000 | 46916000 | 2022-06-12 | 2022-09-08
2022-07-31 | 2017 | Army Active | 77538 |  | 2018-02-12 | 2018-07-09 | GEC-HHI Joint Venture | W9123818C0020 | 7970000 | 10413000 | 2020-02-22 | 2022-02-16
2022-07-31 | 2020 | Army Active | 77728 |  | 2020-02-07 | 2020-06-26 | Walsh Federal, LLC | W912DW20C0007 | 38027000 | 40845000 | 2022-12-31 | 2023-05-26
2022-07-31 | 2018 | Army Active | 77779 |  | 2018-06-22 | 2019-06-06 | S.B. Ballard Construction Company | W9123619C0014 | 40458000 | 41200000 | 2021-02-15 | 2022-03-31
2022-07-31 | 2018 | Army Active | 78713 |  | 2021-07-21 | 2022-07-18 | Staatliches Hochbauamt Amberg | W912GB18C0002 | 0 | 0 | 2023-09-18 | 2023-09-18
2022-07-31 | 2019 | Army Active | 78804 |  | 2020-06-03 | 2020-12-04 | DOBCO GROUP, INC. | W912DS21C0002 | 186676000 | 189575000 | 2025-01-04 | 2025-04-02
2022-07-31 | 2015 | Army Active | 81234 |  | 2017-02-15 | 2018-09-14 | Aegis Security Insurance Company | W9126G-17-C-0046 | 2580000 | 2708000 | 2019-09-27 | 2022-08-31
2022-07-31 | 2019 | Army Active | 81316 |  | 2020-03-10 | 2020-06-23 | Anna Lisa Luna Construction, Inc. | W912PL20C0019 | 5481000 | 5800000 | 2021-08-18 | 2022-01-31
2022-07-31 | 2021 | Army Active | 81352 |  | 2021-08-26 | 2021-11-04 | KLK Electric, Inc | W912DS22C0002 | 4620000 | 4620000 | 2023-02-02 | 2023-01-25
2022-07-31 | 2017 | Army Active | 81428 |  | 2019-03-21 | 2019-06-03 | Daebo E & C | W912UM19C0015 | 43171000 | 50527000 | 2021-07-14 | 2021-12-30
2022-07-31 | 2019 | Army Active | 81429 |  | 2019-07-22 | 2019-10-30 | Daebo Engineering & Construction Co., Ltd. | W912UM20C0001 | 54939000 | 55721000 | 2022-09-05 | 2022-10-27
2022-07-31 | 2019 | Army Active | 82254 |  | 2019-06-18 | 2019-09-30 | ACC Construction Company, Inc. | W912PM19C0043 | 9649000 | 9776000 | 2021-06-30 | 2022-05-04
2022-07-31 | 2015 | Army Active | 85711 |  | 2017-05-09 | 2017-09-28 | BRYAN 77 CONSTRUCTION JV | W912GB17C0019 | 15238000 | 19096000 | 2020-12-09 | 2022-08-01
2022-07-31 | 2017 | Army Active | 85794 |  | 2018-05-25 | 2019-01-18 | Odyssey International | W912HN19C3000 | 14000000 | 14777000 | 2020-06-14 | 2022-04-29
2022-07-31 | 2019 | Army Active | 86019 |  | 2021-10-21 | 2021-11-10 | German Government (EBC) | W912GB18C0075 | 0 | 0 | 2022-09-27 | 2022-12-26
2022-07-31 | 2015 | Army Active | 86094 |  | 2019-02-11 | 2020-04-01 | Staatliches Hochbauamt Amberg | W912GB-16-C-0006 | 2418000 | 3017000 | 2021-09-05 | 2022-07-29
2022-07-31 | 2020 | Army Active | 86215 |  | 2021-07-28 | 2021-11-09 | Tactical Defense Solutions, Inc. | W9123622C2040 | 2700000 | 2725000 | 2022-12-20 | 2022-12-20
2022-07-31 | 2015 | Army Active | 86404 |  | 2017-05-09 | 2017-09-26 | MICHAEL M.TSONTOS S.A. | W912GB17D0015 | 6121000 | 4788000 | 2019-12-13 | 2022-02-11
2022-07-31 | 2016 | Army Active | 86409 |  | 2020-01-17 | 2020-09-03 | Tuckman Barbee Construction Co., Inc. | W912DR20C0042 | 24482000 | 25215000 | 2022-10-27 | 2022-11-09
2022-07-31 | 2018 | Army Active | 86518 |  | 2019-04-24 | 2019-07-17 | Doyon Management Services, LLC | W912DW19C0012 | 5076000 | 5254000 | 2020-08-14 | 2022-05-06
2022-07-31 | 2017 | Army Active | 86689 |  | 2017-06-13 | 2017-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM17C0044 | 382205000 | 391248000 | 2020-11-12 | 2021-12-30
2022-07-31 | 2017 | Army Active | 86689 |  | 2017-06-13 | 2019-02-26 | Yojin Construction & Engineering CO., LTD. | W912UM19C0007 | 382205000 | 391248000 | 2022-07-25 | 2023-02-17
2022-07-31 | 2019 | Army Active | 86689 | 86877 | 2018-10-10 | 2019-02-26 | Yojin | W912UM19C0007 | 382205000 | 391248000 | 2022-07-25 | 2023-02-17
2022-07-31 | 2020 | Army Active | 86689 | 91327 | 2021-01-13 | 2021-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM17C0044 | 382205000 | 391248000 | 2020-11-12 | 2021-12-30
2022-07-31 | 2018 | Army Active | 86689 | 91380 | 2018-07-27 | 2019-02-26 | Daewoo Engineering & Construction. Co., Ltd. | W912UM17C0044 | 382205000 | 391248000 | 2020-11-12 | 2021-12-30
2022-07-31 | 2018 | Army Active | 86689 | 91380 | 2018-07-27 | 2019-02-26 | Yojin Construction & Engineering CO., LTD. | W912UM19C0007 | 382205000 | 391248000 | 2022-07-25 | 2023-02-17
2022-07-31 | 2018 | Army Active | 86816 |  | 2019-03-21 | 2019-09-10 | The Robins & Morton Group | W9127819C0024 | 32995000 | 35432000 | 2021-10-10 | 2022-09-17
2022-07-31 | 2016 | Army Active | 86824 |  | 2019-04-08 | 2019-04-18 | Staatliches Hochbauamt Amberg | W912GB-15-C-0007 | 42195000 | 44325000 | 2023-06-03 | 2023-06-03
2022-07-31 | 2018 | Army Active | 86832 |  | 2018-04-24 | 2018-08-15 | Aytekin-Serol Eng Cons Trade Co. LTD. | W912GB-15-D-0084 | 4004000 | 9904000 | 2022-03-25 | 2024-04-30
2022-07-31 | 2016 | Army Active | 86914 |  | 2017-07-03 | 2017-08-30 | Nan, Inc., dba Ocean House Builders | W9128A-12-D-0012 | 2523000 | 2603000 | 2018-12-12 | 2022-02-15
2022-07-31 | 2018 | Army Active | 86991 |  | 2019-03-28 | 2020-01-27 | Landesbetrieb Bau und Immobilien Hessen Zentrale | W912GB-17-C-0002 | 43508000 | 46007000 | 2022-06-22 | 2023-03-19
2022-07-31 | 2018 | Army Active | 87205 |  | 2020-02-25 | 2020-04-30 | Allen-Batchelor Construction Co., Inc. | W912HN20C3004 | 6187000 | 11023000 | 2022-10-01 | 2022-10-01
2022-07-31 | 2020 | Army Active | 87807 |  | 2020-04-10 | 2021-07-02 | M.W. Builders | W9126G21C0014 | 36514000 | 36507000 | 2023-07-20 | 2023-08-03
2022-07-31 | 2020 | Army Active | 87933 |  | 2020-03-06 | 2020-09-25 | Structural Associate | W912DS20C0025 | 21732000 | 21783000 | 2022-10-11 | 2022-10-11
2022-07-31 | 2016 | Army Active | 87980 |  | 2019-02-12 | 2019-11-12 | C&C Contractors | W912HN20C3001 | 5155000 | 5230000 | 2021-01-09 | 2021-11-30
2022-07-31 | 2020 | Army Active | 88077 |  | 2019-11-20 | 2020-03-09 | Manhattan Construction Company | W912DR20C0007 | 76399000 | 82103000 | 2023-04-01 | 2023-07-19
2022-07-31 | 2021 | Army Active | 88077 | 96217 | 2019-11-20 | 2020-03-09 | Manhattan Construction Company | W912DR20C0007 | 76399000 | 82103000 | 2023-04-29 | 2023-04-29
2022-07-31 | 2018 | Army Active | 88380 |  | 2019-06-18 | 2019-09-05 | M.W. Builders | W9126G19C0119 | 30477000 | 36025000 | 2021-08-15 | 2022-03-04
2022-07-31 | 2020 | Army Active | 88410 |  | 2020-10-29 | 2021-06-15 | Zodiac-Poettker | W912HN21C3005 | 56295000 | 56311000 | 2023-08-01 | 2023-08-01
2022-07-31 | 2019 | Army Active | 88542 |  | 2019-06-24 | 2019-09-25 | EIFFAGE INFRAESTRUCTURAS SA | W912GB19D0039 | 11399000 | 11800000 | 2022-04-17 | 2022-06-01
2022-07-31 | 2019 | Army Active | 88724 |  | 2019-05-31 | 2020-06-19 | Gilbane Federal | W912HN20C3006 | 193807000 | 195936000 | 2022-07-07 | 2023-02-27
2022-07-31 | 2020 | Army Active | 88725 |  | 2020-12-02 | 2021-04-02 | J. KOKOLAKIS CONTRACTING | W912HN21C3003 | 112377000 | 113801000 | 2024-04-25 | 2024-05-11
2022-07-31 | 2020 | Army Active | 89057 |  | 2020-01-16 | 2020-05-29 | Sauer | W912PM20C0014 | 10480000 | 10750000 | 2022-03-10 | 2023-01-24
2022-07-31 | 2017 | Army Active | 89215 |  | 2019-02-12 | 2019-11-13 | C&C Contractors | W912HN20C3002 | 4996000 | 5081000 | 2021-01-09 | 2021-11-30
2022-07-31 | 2018 | Army Active | 89946 |  | 2019-10-29 | 2020-01-31 | CCI Utility and Construction Services, LLC | W9127820C0008 | 5292000 | 5551000 | 2021-05-22 | 2021-12-10
2022-07-31 | 2018 | Army Active | 90351 |  | 2020-09-18 | 2021-03-19 | AMG | W912PL21C0007 | 26473000 | 26998000 | 2023-02-10 | 2023-02-10
2022-07-31 | 2018 | Army Active | 90722 |  | 2019-07-11 | 2019-08-30 | Intercontinental Construction Contracting, INC. | W912DS19C0018 | 14893000 | 18214000 | 2021-09-01 | 2022-08-05
2022-07-31 | 2018 | Army Active | 91252 |  | 2019-05-10 | 2019-08-14 | Crowder Construction Company | W912PM19C0027 | 3864000 | 4297000 | 2021-05-15 | 2022-05-09
2022-07-31 | 2019 | Army Active | 91311 |  | 2019-07-02 | 2019-08-26 | TDX Quality, LLC | W912HN19C3010 | 6927000 | 6943000 | 2020-12-10 | 2021-10-14
2022-07-31 | 2020 | Army Active | 91328 |  | 2020-06-25 | 2020-09-15 | Weldin Construction, LLC | W912BV17D0017 | 4623000 | 4623000 | 2021-11-09 | 2023-02-26
2022-07-31 | 2020 | Army Active | 91397 |  | 2020-08-13 | 2020-09-24 | A.R. CHESSON CONSTRUCTION COMPANY | W912HN20C3011 | 7034000 | 7199000 | 2021-11-15 | 2022-09-02
2022-07-31 | 2018 | Army Active | 91528 |  | 2019-01-15 | 2019-06-18 | Ral Investment Corporation dba Silverstrand Construction | W912PL19C0017 | 5099000 | 5443000 | 2020-09-11 | 2022-06-28
2022-07-31 | 2018 | Army Active | 91732 |  | 2018-07-30 | 2018-09-28 | MICHAEL M.TSONTOS S.A. | W912GB17D0015 | 844000 | 1038000 | 2020-10-24 | 2022-05-13
2022-07-31 | 2018 | Army Active | 91742 |  | 2019-05-17 | 2019-09-05 | Nakasato Contracting, LLC | W9128A19C0006 | 14200000 | 15300000 | 2021-09-23 | 2022-05-13
2022-07-31 | 2020 | Army Active | 91996 |  | 2020-06-30 | 2020-09-22 | James Construction Group | W9126G20C0038 | 13350000 | 13242000 | 2022-07-12 | 2022-09-13
2022-07-31 | 2018 | Army Active | 92022 |  | 2019-06-07 | 2019-07-25 | Siler Excavating LLC | W912HN19C3008 | 4635000 | 4775000 | 2020-06-17 | 2022-03-01
2022-07-31 | 2020 | Army Active | 92422 |  | 2021-04-01 | 2021-08-18 | EMR, Inc | W91278-16-D-0035 | 3929000 | 3942000 | 2022-11-01 | 2023-02-10
2022-07-31 | 2019 | Army Active | 92518 |  | 2018-12-17 | 2020-02-27 | Bates Engineers/Contractors, Inc | W9127816D0018 | 21993000 | 23730000 | 2022-03-11 | 2022-07-31
2022-07-31 | 2019 | Army Active | 93021 |  | 2019-10-24 | 2020-04-07 | Anderson Burton Construction, Inc. | W9128A-16-D-0005 | 5827000 | 6033000 | 2022-01-08 | 2022-08-21
2022-07-31 | 2019 | Army Active | 93209 |  | 2020-11-16 | 2022-03-07 | German Government (EBC) | W912GB18C0024 | 4574000 | 4574000 | 2023-03-29 | 2023-06-27
2022-07-31 | 2021 | Army Active | 93322 |  | 2021-07-09 | 2021-09-30 | Manhattan Constr. | W912DR21C0056 | 29928000 | 29928000 | 2024-01-28 | 2024-01-28
2022-07-31 | 2021 | Army Active | 94363 |  | 2021-04-27 | 2021-10-22 | FOS Development Corp. | W912DS22C0001 | 5677000 | 5847000 | 2023-05-21 | 2023-05-21
2022-07-31 | 2019 | Army Active | 94606 |  | 2019-09-27 | 2019-11-06 | BFBC, LLC | W912PL20C0002 | 15233000 | 14906000 | 2021-06-08 | 2021-11-05
2022-07-31 | 2019 | Army Active | 94607 |  | 2019-09-27 | 2019-11-06 | BFBC, LLC | W912PL20C0002 | 245241000 | 404677000 | 2021-06-08 | 2021-11-05
2022-07-31 | 2019 | Army Active | 94608 |  | 2019-10-22 | 2019-12-02 | Fisher Sand & Gravel CO. | W912PL20C0004 | 268073000 | 419850000 | 2021-01-08 | 2021-10-18
2022-07-31 | 2019 | Army Active | 94609 |  | 2019-10-11 | 2019-11-19 | CJW Joint Venture | W9126G19D0024 | 55842000 | 121858000 | 2021-03-03 | 2022-04-22
2022-07-31 | 2019 | Army Active | 94610 |  | 2019-11-07 | 2020-01-10 | SLSCO, Ltd | W9126G19D0021 | 37106000 | 47319000 | 2021-07-20 | 2022-09-30
2022-07-31 | 2019 | Army Active | 94611 |  | 2019-11-16 | 2020-01-17 | SLSCO, Ltd | W9126G19D0021 | 130750000 | 178637000 | 2021-01-25 | 2022-09-30
2022-07-31 | 2019 | Army Active | 94612 |  | 2019-11-16 | 2020-01-17 | SLSCO, Ltd | W9126G19D0021 | 43620000 | 66268000 | 2021-01-24 | 2022-09-30
2022-07-31 | 2015 | Army Reserve | 67567 |  | 2018-02-01 | 2018-08-09 | RELYANT GLOBAL LLC | W912QR18C0026 | 7030000 | 7358000 | 2019-12-22 | 2022-05-18
2022-07-31 | 2018 | Army Reserve | 77074 |  | 2019-08-05 | 2019-09-27 | RBC Construction | W912QR19C0046 | 18838000 | 19103000 | 2021-04-22 | 2022-12-30
2022-07-31 | 2016 | Army Reserve | 77163 |  | 2019-08-02 | 2019-09-29 | Trans4Fed, LLC | W912QR19C0045 | 10304000 | 10556000 | 2021-06-23 | 2022-09-20
2022-07-31 | 2019 | Army Reserve | 77268 |  | 2018-11-20 | 2019-02-28 | Straub Construction, Inc. | W912QR19C0012 | 28937000 | 31041000 | 2020-11-21 | 2022-07-27
2022-07-31 | 2019 | Army Reserve | 80690 |  | 2019-06-10 | 2019-09-27 | LS Black Constructors | W912QR19C0051 | 20684000 | 22034000 | 2021-08-22 | 2022-04-01
2022-07-31 | 2021 | Army Reserve | 81564 |  | 2021-08-02 | 2021-09-28 | Range & Civil Const | W912QR21C0046 | 9972000 | 9972000 | 2024-02-16 | 2024-02-16
2022-07-31 | 2020 | Army Reserve | 81802 |  | 2020-07-30 | 2020-09-29 | LS Black Constructors | W912QR20C0052 | 18824000 | 19254000 | 2022-12-17 | 2022-12-17
2022-07-31 | 2021 | Army Reserve | 82197 |  | 2021-08-04 | 2021-09-30 | Sauer Construction, LLC | W912QR21C0049 | 33126000 | 33783000 | 2024-01-31 | 2024-01-31
2022-07-31 | 2016 | Army Reserve | 85813 |  | 2017-06-28 | 2017-09-28 | Hensel Phelps Construction Co. | W912QR-17-C-0043 | 49643000 | 52926000 | 2019-10-04 | 2022-06-01
2022-07-31 | 2020 | Army Reserve | 86823 |  | 2019-11-01 | 2020-03-26 | Harkins Builders | W912QR20C0012 | 19751000 | 20351000 | 2022-03-28 | 2021-11-29
2022-07-31 | 2022 | Army Reserve | 88554 |  | 2022-03-04 | 2022-06-09 | LS Black Constructors, LLC | W912QR22C0025 | 0 | 0 | 2023-12-16 | 2023-12-16
2022-07-31 | 2018 | Army Reserve | 88731 |  | 2018-06-29 | 2019-06-05 | Caribe General Constructors | W912QR19C0018 | 17399000 | 18645000 | 2020-12-19 | 2022-05-06
2022-07-31 | 2021 | Army Reserve | 88752 |  | 2021-08-23 | 2021-09-29 | R. ZOPPO CORPORATION | W912QR21C0054 | 7933000 | 7933000 | 2024-02-28 | 2024-02-28
2022-07-31 | 2019 | Army Reserve | 90202 |  | 2020-02-18 | 2020-09-04 | WHH Nisqually-Garco JV 2 | W912QR20C0035 | 20217000 | 20353000 | 2022-06-22 | 2022-06-22
2022-07-31 | 2021 | Army Reserve | 90896 |  | 2021-03-17 | 2021-07-16 | LRG Construction JV, LLC | W912QR21C0031 | 3962000 | 3962000 | 2022-09-15 | 2022-09-15
2022-07-31 | 2022 | Army Reserve | 92098 |  | 2021-08-17 | 2021-11-12 | G.M. HILL ENGINEERING, INC. | W912QR20D0024 | 4924000 | 4924000 | 2023-05-19 | 2023-05-19
2022-08-12 | 2017 | Defense Health Agency | 14019 |  | 2017-06-23 | 2018-06-29 | RQ-DPRI | N40085-18-C-0637 | 30188000 | 32491000 | 2020-07-13 | 2021-10-07
2022-08-12 | 2018 | Defense Health Agency | 14021 |  | 2018-06-12 | 2019-12-18 | Soltek Pacific Construction Co. | N6247318D5855 | 27799000 | 28065000 | 2022-05-10 | 2022-08-15
2022-08-12 | 2017 | Defense Health Agency | 14022 |  | 2017-04-28 | 2017-09-13 | Mirait T-Acty JV | W912-HV-17-D-0014 | 14781000 | 15015000 | 2019-10-26 | 2020-11-30
2022-08-12 | 2018 | Defense Health Agency | 14041 |  | 2018-06-13 | 2019-09-28 | Whiting Turner Contracting Co | N6247016D6006 | 22911000 | 23158000 | 2021-10-30 | 2022-08-15
2022-08-12 | 2018 | Defense Health Agency | 14042 |  | 2018-06-06 | 2019-09-28 | Whiting Turner Contracting Co | N4008519C9266 | 21875000 | 22412000 | 2021-10-30 | 2022-09-30
2022-08-12 | 2008 | Defense Health Agency | 52332 |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929000 | 28027000 | 2012-05-15 | 2012-07-16
2022-08-12 | 2007 | Defense Health Agency | 58395 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657000 | 2657000 | 2008-06-13 | 2008-06-08
2022-08-12 | 2007 | Defense Health Agency | 58395 | 58395-01 | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472000 | 1472000 | 2009-02-15 | 2009-02-13
2022-08-12 | 2007 | Defense Health Agency | 58395 | 58395-02 | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706000 | 706000 | 2010-04-13 | 2010-04-13
2022-08-12 | 2007 | Defense Health Agency | 58395 | 58395-03 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465000 | 2465000 | 2009-07-24 | 2009-07-24
2022-08-12 | 2007 | Defense Health Agency | 58395 | 58395-04 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 604000 | 2013-10-31 | 2013-12-06
2022-08-12 | 2007 | Defense Health Agency | 58395 | 58395-05 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 3949000 | 2014-05-31 | 2023-05-25
2022-08-12 | 2007 | Defense Health Agency | 58395 | 71101-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 7750000 | 7335000 | 2017-03-31 | 2017-05-04
2022-08-12 | 2013 | Defense Health Agency | 58395 | 78210-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 0 | 141000 | 2017-03-31 | 2017-05-04
2022-08-12 | 2013 | Defense Health Agency | 58395 | 78210-02 | 2017-08-18 | 2017-09-27 | Doyon Project Services, LLC | W912DR-17-D-0012 | 1607000 | 1580000 | 2018-10-26 | 2019-05-11
2022-08-12 | 2014 | Defense Health Agency | 58395 | 78211 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 3200000 | 3200000 | 2014-05-31 | 2023-05-25
2022-08-12 | 2009 | Defense Health Agency | 64156 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398000 | 17919000 | 2013-06-01 | 2015-06-10
2022-08-12 | 2009 | Defense Health Agency | 65731 |  | 2009-01-07 | 2009-04-08 | Total Engineering INC | W912DR-09-C-0030 | 436000 | 436000 | 2010-08-08 | 2010-08-31
2022-08-12 | 2009 | Defense Health Agency | 65731 | 65731-01 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 37771000 | 2013-06-01 | 2015-06-10
2022-08-12 | 2009 | Defense Health Agency | 65731 | 67180-01 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30
2022-08-12 | 2011 | Defense Health Agency | 66588 |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 30080000 | 31830000 | 2016-05-30 | 2017-05-03
2022-08-12 | 2018 | Defense Health Agency | 67402 |  | 2019-07-29 | 2020-01-30 | SGS, LLC | W9126G-20-C-0009 | 8996000 | 10090000 | 2022-04-03 | 2022-04-03
2022-08-12 | 2013 | Defense Health Agency | 71317 |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744000 | 46104000 | 2016-12-30 | 2019-02-15
2022-08-12 | 2013 | Defense Health Agency | 71325 |  | 2012-11-30 | 2013-09-13 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536000 | 47478000 | 2016-10-23 | 2018-06-01
2022-08-12 | 2012 | Defense Health Agency | 71408 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688000 | 21664000 | 2016-12-06 | 2019-02-15
2022-08-12 | 2012 | Defense Health Agency | 71503 |  | 2012-03-22 | 2016-08-25 | Surety Company | N69450 12 C 0754 | 9548000 | 2026000 | 2017-12-25 | 2019-05-10
2022-08-12 | 2017 | Defense Health Agency | 71509 |  | 2017-06-30 | 2018-12-26 | KBE BLDG CORP | N4008519C9070 | 30188000 | 31721000 | 2021-01-24 | 2021-07-14
2022-08-12 | 2010 | Defense Health Agency | 72481 |  | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 56858000 | 254981000 | 2016-11-26 | 2020-02-29
2022-08-12 | 2010 | Defense Health Agency | 72481 | 72481-01 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-10-12
2022-08-12 | 2010 | Defense Health Agency | 72481 | 72481-02 | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488000 | 10634000 | 2012-07-05 | 2012-12-31
2022-08-12 | 2010 | Defense Health Agency | 72481 | 72481-03 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-10-17
2022-08-12 | 2010 | Defense Health Agency | 72481 | 72481-04 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2015-08-27 | 2015-11-30
2022-08-12 | 2010 | Defense Health Agency | 72481 | 72481-05 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2015-09-16
2022-08-12 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G-11-P-0208 | 46000 | 46000 | 2011-11-01 | 2011-11-01
2022-08-12 | 2010 | Defense Health Agency | 72481 | 76558-01 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540000 | 623000 | 2014-10-24 | 2014-10-24
2022-08-12 | 2010 | Defense Health Agency | 72481 | 77293-01 | 2014-10-20 | 2019-07-10 | Ross Group | W9126G-19-C-0031, W9126G-19-C-0032 | 34029000 | 34126000 | 2020-10-18 | 2021-12-28
2022-08-12 | 2010 | Defense Health Agency | 72481 | 81407-01 | 2015-03-30 | 2019-10-28 | Justin J Reeves, LLC | W9126G-20-C-0003 | 2842000 | 2854402 | 2021-05-04 | 2021-05-04
2022-08-12 | 2018 | Defense Health Agency | 72481 | 91301 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 251330000 | 206136000 | 2016-11-26 | 2020-02-29
2022-08-12 | 2017 | Defense Health Agency | 72738 |  | 2017-01-19 | 2017-09-13 | JE Dunn Construction Company | W912-BV-17-C-0014 | 67487000 | 67762000 | 2020-10-31 | 2022-04-01
2022-08-12 | 2020 | Defense Health Agency | 72742 |  | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005a | 212000 | 212000 | 2021-09-26 | 2022-06-30
2022-08-12 | 2020 | Defense Health Agency | 72742 | 72742-01 | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005b | 305000 | 305000 | 2022-06-10 | 2022-08-31
2022-08-12 | 2020 | Defense Health Agency | 72742 | 72742-02 | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005c | 978000 | 978000 | 2023-03-24 | 2023-03-24
2022-08-12 | 2012 | Defense Health Agency | 72754 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22835000 | 2014-07-29 | 2016-09-02
2022-08-12 | 2013 | Defense Health Agency | 72808 |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703000 | 19971000 | 2015-03-16 | 2017-04-28
2022-08-12 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, ABG4 P00058 | 2359000 | 3563000 | 2016-04-30 | 2017-04-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 72661, 72662-02 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00102 | 56039000 | 56985000 | 2021-01-30 | 2022-09-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00085 | 33888000 | 34523000 | 2021-03-31 | 2021-12-07
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-01 | 2012-02-01 | 2012-03-15 | Joint Venture Bautra Baugesellschaft mbH / SRS Service GmbH | W912GB-10-C-0031, ABG4 P00023 | 261000 | 261000 | 2014-04-04 | 2014-04-04
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-02 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00030 | 681000 | 1747000 | 2014-10-29 | 2015-01-21
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-03 | 2012-02-01 | 2012-03-15 | Depenbrock Bau GmbH & Co. KG | W912GB-10-C-0031, ABG4 P00043 | 5321000 | 6586000 | 2016-04-30 | 2017-07-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-04 | 2012-02-01 | 2012-03-15 | Hermanns RTE Rohrleitungs- undd Tiefbau Erfurt GmbH | W912GB-10-C-0031, ABG4 P00062 | 5444000 | 6199000 | 2016-12-15 | 2017-12-15
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-05 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH (ABG4 P00033) | W912GB-10-C-0031, ABG4 P00033 | 141234 | 142000 | 2015-03-30 | 2015-05-01
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-06 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH | W912GB-10-C-0031, ABG4 P00031 | 17713 | 17713 | 2014-12-31 | 2014-12-31
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-07 | 2012-02-01 | 2012-03-15 | FRG/CREOS GmbH | W912GB-10-C-0031, ABG4 P00032 | 473000 | 492000 | 2014-10-16 | 2014-10-16
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-08 | 2012-02-01 | 2012-03-15 | FRG/Omexom GA Sud GmbH | W912GB-10-C-0031, ABG4 P00066 | 62000 | 68000 | 2016-10-30 | 2016-12-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB-10-C-0031, P00071 | 419000 | 419000 | 2020-03-30 | 2020-03-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-10 | 2012-02-01 | 2012-03-15 | FRG/Zeppelin STREIF Baulogistik GmbH | W912GB-10-C-0031, ABG4 P00039 | 5235000 | 7121000 | 2025-12-30 | 2027-10-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-13 | 2012-02-01 | 2012-03-15 | FRG/Deutsche Telekom Technik GmbH | W912GB-10-C-0031, ABG4 P00037 | 1000 | 1000 | 2014-12-31 | 2014-12-31
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-14 | 2015-08-19 | 2015-08-31 | FRG: Ed. Zublin AG / Gilbane Germany GmbH | W912GB-10-C-0031 | 913702000 | 913702000 | 2027-12-30 | 2027-12-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 76007-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 21988000 | 24175000 | 2018-07-30 | 2018-12-30
2022-08-12 | 2012 | Defense Health Agency | 76007 | 81412 | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 14187000 | 2025-12-30 | 2027-10-30
2022-08-12 | 2018 | Defense Health Agency | 76934 |  | 2018-05-24 | 2019-02-08 | Gilbane Federal JV | W912HN-19-C-3002 | 10042000 | 2562000 | 2021-03-14 | 2021-07-12
2022-08-12 | 2014 | Defense Health Agency | 77000 |  | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR-15-C-0015 | 206445000 | 218443000 | 2019-02-19 | 2023-02-01
2022-08-12 | 2014 | Defense Health Agency | 77000 | 77000-01 | 2021-07-31 | 2021-09-26 | BeltBuilt LLC | W912DR-21-C-0052 | 3052000 | 3052000 | 2022-12-06 | 2022-12-06
2022-08-12 | 2018 | Defense Health Agency | 77140 |  | 2018-06-22 | 2019-01-24 | Walga Ross Group JV | W912DQ-19-F-4003 | 10585000 | 10530000 | 2020-09-16 | 2021-10-29
2022-08-12 | 2012 | Defense Health Agency | 77154 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 66430000 | 72888000 | 2016-12-06 | 2022-09-30
2022-08-12 | 2016 | Defense Health Agency | 77986 |  | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005a | 23667000 | 28352000 | 2019-06-04 | 2022-08-26
2022-08-12 | 2016 | Defense Health Agency | 77986 | 77986-01 | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005b | 794000 | 794000 | 2023-07-30 | 2023-07-30
2022-08-12 | 2016 | Defense Health Agency | 77986 | 77986-02 | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005c | 889000 | 889000 | 2023-10-01 | 2023-10-01
2022-08-12 | 2018 | Defense Health Agency | 77987 |  | 2018-03-22 | 2018-09-21 | JJ Brun JV LLC | W9128F-18-0281 | 11396000 | 13579000 | 2021-06-17 | 2023-01-30
2022-08-12 | 2016 | Defense Health Agency | 78150 |  | 2015-11-05 | 2016-08-08 | Caddell-Nan joint Venture | N62742 16 C 1312 | 79722000 | 83356000 | 2018-12-21 | 2020-08-31
2022-08-12 | 2013 | Defense Health Agency | 80306 |  | 2013-07-25 | 2013-09-12 | G-W Management Services Inc. | N40080 10 D 0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25
2022-08-12 | 2013 | Defense Health Agency | 80306 | 80306-01 | 2014-03-15 | 2016-09-01 | Whiting Turner Contracting Co | N40080 16 C 0172 | 29435000 | 30582000 | 2017-12-10 | 2018-08-31
2022-08-12 | 2016 | Defense Health Agency | 80412 |  | 2016-01-27 | 2016-05-17 | Swinerton Builders | W9128A-16-C-0004 | 26084000 | 27183000 | 2017-12-08 | 2019-03-29
2022-08-12 | 2016 | Defense Health Agency | 80412 | 80412-01 | 2016-10-21 | 2018-02-08 | Hensel-Phelps Const. Co. | W9128A-18-C-0001 | 74987000 | 73999000 | 2020-05-21 | 2020-11-20
2022-08-12 | 2016 | Defense Health Agency | 80412 | 80412-02 | 2020-07-31 | 2020-09-21 | Su-Mo Builders Inc. | W9128A-16-D-0011 TO W9128A20F0067 | 1484000 | 1484000 | 2023-02-06 | 2023-02-06
2022-08-12 | 2017 | Defense Health Agency | 80906 |  | 2017-05-23 | 2017-09-28 | Whiting Turner Contracting Co | N40080-17-C-0039 | 26338000 | 31518000 | 2019-05-10 | 2021-08-31
2022-08-12 | 2018 | Defense Health Agency | 80906 | 81420 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080-20-C0001 | 570000000 | 214302000 | 2026-03-01 | 2027-05-13
2022-08-12 | 2020 | Defense Health Agency | 80906 | 85667 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080-20-C0001 | 570000000 | 214302000 | 2026-03-01 | 2027-05-13
2022-08-12 | 2016 | Defense Health Agency | 81422 |  | 2017-11-27 | 2018-09-24 | United Excel Corportation (now StructSure Projects) | W9126G-18-C-0077 | 40138000 | 48418000 | 2021-04-01 | 2023-06-19
2022-08-12 | 2015 | Defense Health Agency | 81430 |  | 2016-06-20 | 2018-01-18 | JE Dunn Construction Company | W9127S-13-D-6001 TO W91236-18-F-0014 | 52181000 | 56349000 | 2021-03-18 | 2023-01-12
2022-08-12 | 2014 | Defense Health Agency | 81436 |  | 2015-08-25 | 2016-03-17 | Contrack Watts Inc. | W912ER-11-D-0009-0012 | 24784000 | 26972000 | 2019-04-20 | 2020-01-20
2022-08-12 | 2018 | Defense Health Agency | 86204 |  | 2020-04-21 | 2020-07-08 | Kimball Construction Company, Inc | W912BU20C0033 | 3408000 | 3922000 | 2022-02-03 | 2022-05-15
2022-08-12 | 2019 | Defense Health Agency | 86943 |  | 2019-09-10 | 2019-12-15 | NVE-HHI JV | W9128F-20-C-0006 | 3384000 | 3384000 | 2021-06-15 | 2021-07-15
2022-08-12 | 2016 | Defense Health Agency | 86953 |  | 2016-07-25 | 2017-03-23 | M.A. Mortenson Company | W912QR-17-C-0009 | 54817000 | 66624000 | 2021-06-23 | 2023-01-04
2022-08-12 | 2018 | Defense Health Agency | 87208 |  | 2018-10-12 | 2019-04-10 | Shinsampeikensetsu-Unite Corporation JV | W912HV-19-C-0005 | 4111000 | 4265000 | 2020-08-21 | 2021-01-30
2022-08-12 | 2019 | Defense Health Agency | 89838 |  | 2019-07-09 | 2019-09-30 | DeMaria Building Co | N4008519C9124 | 28729000 | 28370000 | 2021-10-30 | 2023-01-31
2022-08-12 | 2019 | Defense Health Agency | 89839 |  | 2021-06-14 | 2021-08-25 | RQ-AECOM JV | N6945018D1317 | 5634000 | 5642000 | 2023-06-02 | 2023-09-07
2022-08-12 | 2019 | Defense Health Agency | 89902 |  | 2020-02-25 | 2020-08-18 | Korte Construction Company | N6945019D0910 | 21894000 | 22699000 | 2022-09-03 | 2022-11-15
2022-08-12 | 2020 | Defense Health Agency | 89906 |  | 2020-08-04 | 2020-09-30 | Soltek Pacific Construction Co. | N6247318D5855 | 15767000 | 15917000 | 2022-10-30 | 2022-10-30
2022-08-12 | 2018 | Defense Health Agency | 91884 |  | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-25
2022-08-12 | 2021 | Defense Health Agency | 91884 | 77168 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-25
2022-08-12 | 2020 | Defense Health Agency | 91884 | 94335 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-25
2022-08-12 | 2022 | Defense Health Agency | 91884 | 97762 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-25
2022-08-12 | 2019 | Defense Health Agency | 93298 |  | 2020-02-17 | 2020-08-25 | GCBJV1, Pensacola, FL | N6945019D0920 | 3859000 | 3921000 | 2021-09-10 | 2022-08-15
2022-08-11 | 2021 | Defense Information Systems Agency | 01DISA21 |  | 2021-04-16 | 2021-09-13 | The Korte Company | W912PL21C0013 | 27737733 | 27737733 | 2023-10-23 | 2024-01-31
2022-08-11 | 2013 | Defense Information Systems Agency | 13DISA01 |  | 2015-08-05 | 2015-08-19 | Bauamt Reutlingen | W912GB-15-C-011 | 2219820 | 2219820 | 2015-08-19 | 2022-12-31
2022-08-11 | 2014 | Defense Information Systems Agency | 14DISA01 |  | 2017-04-12 | 2017-07-13 | Heartwood Pacific, LLC | N6274217F0307 | 1781248 | 1781248 | 2018-12-31 | 2022-08-30
2022-08-11 | 2015 | Defense Information Systems Agency | 15DISA02 |  | 2018-05-02 | 2018-08-09 | Cockram Construction Australia Pty Ltd. 675 Victoria Street, Abbotsford Victoria 3067, Austrialia | N6274218C1306 | 8794967 | 12189000 | 2019-03-31 | 2020-03-31
2022-08-11 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11
2022-08-25 | 2017 | DLA Defense Distribution Center | DDCX1701A |  | 2017-12-08 | 2018-04-12 | Carouthers Construction | W9126G-18-C-0018 | 36159560 | 36510784 | 2020-06-25 | 2021-05-24
2022-08-25 | 2017 | DLA Defense Distribution Center | DDCX1701B |  | 2018-04-03 | 2018-08-30 | Bristol Construction Services | W9126G-18-C-0066 | 3881804 | 3881804 | 2020-09-30 | 2020-09-30
2022-08-25 | 2019 | DLA Defense Distribution Center | DDCX1901 |  | 2019-03-26 | 2019-06-19 | B. L. Harbert International, LLC | W9126-G19-C-0029 | 67142000 | 67909992 | 2023-01-30 | 2022-10-31
2022-08-25 | 2020 | DLA Defense Energy Support Center | DECS1913 |  | 2020-05-28 | 2020-09-15 | Nova Group, Inc. | W9128F20C0039 / 59008927 | 22124000 | 22201000 | 2022-11-30 | 2023-01-30
2022-08-25 | 2013 | DLA Defense Energy Support Center | DESC1301 |  | 2014-11-13 | 2015-08-28 | Rockford Corporation | W912QR-15-C-0026 | 36448000 | 37081000 | 2017-03-30 | 2022-11-30
2022-08-25 | 2017 | DLA Defense Energy Support Center | DESC1513 |  | 2019-03-08 | 2019-04-30 | Structural Associates, Inc | W9127821C0012 | 14758000 | 14809000 | 2022-10-17 | 2021-04-25
2022-08-25 | 2017 | DLA Defense Energy Support Center | DESC1513 |  | 2018-04-30 | 2018-09-20 | Bhate Zapata | W912EP-16-D-0008 | 1300000 | 4390000 | 2019-07-06 | 2023-01-03
2022-08-25 | 2016 | DLA Defense Energy Support Center | DESC1603 |  | 2017-12-12 | 2018-08-10 | Bietergemeinschaft UVB | W912GB-14-C-0005 | 6125000 | 6125000 | 2019-06-02 | 2019-10-02
2022-08-25 | 2016 | DLA Defense Energy Support Center | DESC1605 |  | 2016-06-23 | 2017-06-02 | STRUCTURAL ASSOCIATES | W912BU16R00370006 | 23170900 | 23170900 | 2019-06-16 | 2020-05-03
2022-08-25 | 2018 | DLA Defense Energy Support Center | DESC1608 |  | 2018-10-21 | 2019-03-20 | MEB | N69450-19-c-1304 | 20334000 | 20334000 | 2021-08-31 | 2021-03-01
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC1609 |  | 2018-08-01 | 2019-06-28 | SES Energy Services, LLC | W9128F19C0032 &#x2f; 42718510 | 7499541 | 7716000 | 2019-07-06 | 2021-11-30
2022-08-25 | 2017 | DLA Defense Energy Support Center | DESC1611 |  | 2017-11-29 | 2017-11-30 | NOVA Group, Inc | N62473-18-C-2202 | 26868000 | 26926198 | 2020-03-10 | 2021-07-15
2022-08-25 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | w | 20577000 | 20577000 | 2019-01-07 | 2021-09-24
2022-08-25 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | N62470-17-C-5003 | 20577000 | 21577000 | 2020-11-30 | 2019-08-03
2022-08-25 | 2016 | DLA Defense Energy Support Center | DESC1702 |  | 2017-02-09 | 2017-09-30 | MEB General Contractors, Inc. | W91299-17-C-0011 | 20973000 | 21083000 | 2019-06-25 | 2021-10-24
2022-08-25 | 2017 | DLA Defense Energy Support Center | DESC1705 |  | 2017-05-29 | 2017-05-30 | Black Construction/Mace Internation | N62742-17-C-1313 | 26978100 | 28361127 | 2019-06-29 | 2019-09-23
2022-08-25 | 2017 | DLA Defense Energy Support Center | DESC1707 |  | 2017-01-30 | 2017-08-07 | ASRC Builders | W911KB-17-C-0030 | 4088355 | 4129621 | 2018-12-15 | 2021-12-15
2022-08-25 | 2018 | DLA Defense Energy Support Center | DESC1709 |  | 2018-09-20 | 2018-09-21 | Tfs-Aptim JV | N40192-18-C-1300 | 21445996 | 21445996 | 2019-12-15 | 2022-01-30
2022-08-25 | 2018 | DLA Defense Energy Support Center | DESC1714 |  | 2018-08-09 | 2019-06-07 | Creative Times Inc | W9123819C0010 | 19480000 | 20000032 | 2021-07-07 | 2021-09-15
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC17U3 |  | 2019-07-02 | 2019-09-12 | The Ross Group | N6247319F5135 | 4384341 | 4883963 | 2021-01-15 | 2022-04-30
2022-08-25 | 2018 | DLA Defense Energy Support Center | DESC1805 |  | 2018-05-21 | 2018-12-27 | TOA CORPORATION | W912HV19C0003 / 51379145 | 33455000 | 33455000 | 2021-04-01 | 2022-02-05
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC18S2 |  | 2019-07-16 | 2019-09-20 | Diversified Constr. | W912BV19C0022 / 56986550 | 6186000 | 6717000 | 2020-12-31 | 2022-02-28
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC1905 |  | 2019-05-01 | 2019-08-01 | WHH Nisqually-Garco JV 2 | W912DW19C0017 / 56848368 | 22312000 | 23258000 | 2022-05-31 | 2021-11-16
2022-08-25 | 2021 | DLA Defense Energy Support Center | DESC1907 |  | 2022-02-01 | 2022-04-05 | Garco Construction, Inc. | W912QR21C0019 | 19652000 | 19883000 | 2022-05-03 | 2024-04-20
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC1909 |  | 2019-08-01 | 2019-09-30 | Rockford | W9123619C0044 / 56765125 | 8330000 | 8453000 | 2020-12-04 | 2022-05-05
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC1914 |  | 2019-07-16 | 2019-09-30 | UST General Contracting, LLC | W9123619C0043 / 56747799 | 4917000 | 5048000 | 2020-12-04 | 2023-01-31
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC19I1 |  | 2019-03-29 | 2019-06-10 | Diversified Construction of Oklahoma | W9126G19C0026 / 56924533 | 8330000 | 8453000 | 2020-09-30 | 2021-09-30
2022-08-25 | 2019 | DLA Defense Energy Support Center | DESC19S2 |  | 2019-05-31 | 2019-06-28 | Dawson Pond | PLACE HOLDER | 6193389 | 7190107 | 2022-10-03 | 2022-02-28
2022-08-25 | 2020 | DLA Defense Energy Support Center | DESC19S4 |  | 2020-04-28 | 2020-09-11 | SGJV, LLC | W9127820C0027 &#x2f; 68228349 | 13051000 | 13051000 | 2021-10-16 | 2023-03-03
2022-08-25 | 2021 | DLA Defense Energy Support Center | DESC2002 |  | 2021-01-04 | 2021-05-21 | Garco | N4425521R20000014 | 54249000 | 54387326 | 2024-01-20 | 2022-02-22
2022-08-25 | 2020 | DLA Defense Energy Support Center | DESC20S1 |  | 2020-08-10 | 2021-04-14 | Rockford Corporation | W912WJ21C0009 | 1162500000 | 1162500000 | 2022-08-15 | 2024-01-21
2022-08-25 | 2021 | DLA Defense Energy Support Center | DESC2104A |  | 2021-01-01 | 2021-09-30 | WHH Nisqually-Garco JV 2 | W912DW21C0021 | 9845000 | 9845000 | 2023-05-23 | 2023-05-25
2022-08-25 | 2021 | DLA Defense Energy Support Center | DESC2104B |  | 2021-01-01 | 2021-02-04 | WHH Nisqually-Garco JV 2 | W912DW21C0022 | 10279000 | 10279000 | 2023-05-23 | 2024-04-20
2022-08-25 | 2015 | DLA Defense National Stockpile Center | DESC1507 |  | 2015-02-02 | 2015-09-30 | Structural Associates Inc | W9128F-15-C-0032 | 17178089 | 17906802 | 2017-03-23 | 2023-05-16
2022-08-25 | 2015 | DLA Defense Supply Center Richmond | DSCR1501 |  | 2016-11-08 | 2017-12-14 | SAW Contracting | W91236-18-C-0008 | 6253160 | 7509000 | 2019-08-12 | 2019-11-13
2022-08-25 | 2020 | DLA Defense Supply Center Richmond | DSCR1901 |  | 2020-05-28 | 2020-12-11 | Manhattan Construction Company | W9123621C2019 | 87092000 | 87454000 | 2023-11-14 | 2024-03-05
2022-08-01 | 2014 | DoD Education Activity | AM00021 |  | 2016-11-07 | 2017-11-20 | John C. Grimberg CO., Inc. | N4008018C0006 | 52553000 | 52182000 | 2020-01-09 | 2020-10-13
2022-08-01 | 2019 | DoD Education Activity | AM00029 |  | 2020-06-29 | 2020-09-30 | A&K Construction Inc | W912QR-20-C-0054/33717697 | 56070000 | 57640656 | 2023-09-09 | 2024-01-07
2022-08-01 | 2016 | DoD Education Activity | AM00033 |  | 2016-07-25 | 2017-03-01 | DOBCO, Inc. | W912DS-17-C-0005/44966911 | 48535000 | 50878598 | 2020-03-05 | 2020-01-06
2022-08-01 | 2014 | DoD Education Activity | AM00046 | 246 | 2013-02-06 | 2016-03-16 | J&J Contractors & Engineers, Inc. | W912WJ-17-C-0004/57439943 | 35970000 | 37442688 | 2019-09-09 | 2019-08-20
2022-08-01 | 2017 | DoD Education Activity | AM00047 |  | 2018-01-03 | 2019-02-27 | Dobco, Inc. | W912BU-19-C-0017/53356011 | 47962590 | 49803671 | 2021-10-15 | 2025-01-31
2022-08-01 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/39179628 | 25629526 | 27304618 | 2020-06-10 | 2021-10-15
2022-08-01 | 2016 | DoD Education Activity | AM00048 | 8 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/54560299 | 4286000 | 4286000 | 2020-06-10 | 2021-10-15
2022-08-01 | 2016 | DoD Education Activity | AM00048 | 9 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/54560300 | 15500000 | 15500000 | 2020-06-10 | 2021-10-15
2022-08-01 | 2015 | DoD Education Activity | AM00051 |  | 2016-02-26 | 2017-03-29 | Walsh Federal, LLC | N40085 17 C 8322 | 47374000 | 43457000 | 2020-03-28 | 2021-04-09
2022-08-01 | 2015 | DoD Education Activity | AM00103 |  | 2015-09-15 | 2016-07-01 | Munilla Construction Management, LLC | N6945016C1612 | 21000000 | 127527000 | 2018-11-26 | 2021-10-09
2022-08-01 | 2016 | DoD Education Activity | AM00110 |  | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278-12-D-0037/41084584 | 27895686 | 37518689 | 2020-05-28 | 2022-09-01
2022-08-01 | 2016 | DoD Education Activity | AM00110 | 27 | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278-12-D-0037/57076763 | 11115000 | 11115000 | 2020-05-28 | 2022-09-01
2022-08-01 | 2016 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N6247016C6003 | 9233000 | 16021000 | 2019-03-27 | 2021-04-21
2022-08-01 | 2021 | DoD Education Activity | AM00182 |  | 2021-04-29 | 2021-08-11 | Messer Construction | W912QR-21-C-0033/59023911 | 58989000 | 59007698 | 2025-09-28 | 2024-10-09
2022-08-01 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029/27243529 | 77816984 | 90349050 | 2019-05-08 | 2019-10-31
2022-08-01 | 2012 | DoD Education Activity | EU00031 | 89 | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029/59013541 | 0 | 202458 | 2019-05-08 | 2019-10-31
2022-08-01 | 2013 | DoD Education Activity | EU00034 |  | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006/44599966 | 41569129 | 44097700 | 2018-12-24 | 2019-06-13
2022-08-01 | 2013 | DoD Education Activity | EU00034 | 45 | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006/50005397 | 0 | 388829 | 2018-12-24 | 2019-06-13
2022-08-01 | 2014 | DoD Education Activity | EU00037 | 1 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/52029300 | 89535967 | 98359412 | 2021-03-29 | 2021-06-28
2022-08-01 | 2017 | DoD Education Activity | EU00039 |  | 2019-03-19 | 2019-09-16 | LBB Kaiserslautern | W912GB-15-C-0013/47316927 | 48012330 | 48606240 | 2024-10-22 | 2025-04-18
2022-08-01 | 2014 | DoD Education Activity | EU00040 |  | 2016-10-21 | 2017-05-09 | LBB Kaiserslautern | W912GB-12-C-0025/52029339 | 43000974 | 49725985 | 2020-01-12 | 2021-03-26
2022-08-01 | 2014 | DoD Education Activity | EU00049 |  | 2015-11-24 | 2016-06-03 | Federal Republic of Germany | W912GB-12-C-0041/50728702 | 56573871 | 57572069 | 2021-07-23 | 2021-08-23
2022-08-01 | 2016 | DoD Education Activity | EU00051 | 51 | 2017-04-30 | 2017-07-20 | Staatliches Hochbauamt Reutlingen | W912GB-12-C-0030/54892650 | 46915286 | 54755811 | 2021-01-23 | 2022-05-30
2022-08-01 | 2015 | DoD Education Activity | EU00064 |  | 2017-06-29 | 2017-09-21 | Joint Venture WMV Brussels American School | W912GB-17-C-0018/44739768 | 28765482 | 29191607 | 2020-10-24 | 2023-03-31
2022-08-01 | 2016 | DoD Education Activity | EU00068 |  | 2017-09-05 | 2018-04-20 | Staatliches Hochbauamt Amberg | W912GB-12-C-0036/57200363 | 33667431 | 37509002 | 2021-03-16 | 2022-10-31
2022-08-01 | 2018 | DoD Education Activity | EU00117 |  | 2019-05-01 | 2019-09-27 | ICM SPA | N6247019C5007 | 36391000 | 39912000 | 2022-01-27 | 2022-12-16
2022-08-01 | 2017 | DoD Education Activity | EU00183 |  | 2020-02-12 | 2020-07-22 | Staatliches Hochbauamt Amberg | W912GB-17-C-0023/ 58997935 | 1304645 | 1430758 | 2021-04-29 | 2022-04-29
2022-08-01 | 2015 | DoD Education Activity | PA00017 |  | 2016-07-15 | 2016-12-23 | Nippo Corporation | W912HV-17-C-0004/37880445 | 61521811 | 88612824 | 2020-11-17 | 2023-01-22
2022-08-01 | 2015 | DoD Education Activity | PA00022 |  | 2018-09-21 | 2019-07-29 | Nippo Corporation | W912HV19C0007/36943919 | 52447552 | 50682194 | 2022-08-05 | 2022-08-05
2022-08-01 | 2015 | DoD Education Activity | PA00023 |  | 2016-06-13 | 2016-11-22 | NES PACIFIC LIMITED LIABILITY CO. | W912HV-17-C-0002/37064811 | 27722277 | 30649314 | 2019-05-28 | 2022-12-31
2022-08-01 | 2017 | DoD Education Activity | PA00032 |  | 2017-06-22 | 2017-12-22 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV18C0002/37880684 | 72844929 | 80243244 | 2021-02-15 | 2021-03-10
2022-08-15 | 2019 | Marine Corps Active | M00146130F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 33831000 | 35690000 | 2025-08-12 | 2025-08-12
2022-08-15 | 2019 | Marine Corps Active | M00146142F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 40771000 | 43289000 | 2025-08-12 | 2025-08-12
2022-08-15 | 2019 | Marine Corps Active | M00146162F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 41270000 | 45098000 | 2025-08-12 | 2025-08-12
2022-08-15 | 2015 | Marine Corps Active | M00146193 |  | 2015-06-17 | 2016-12-22 | GARNEY COMPANIES, INC. | N4008517C8315 AWD | 55798000 | 59250000 | 2021-11-23 | 2022-03-23
2022-08-15 | 2016 | Marine Corps Active | M00146194 |  | 2016-03-29 | 2016-08-31 | M A MORTENSON COMPANY | N4008516C5506 AWD | 28561000 | 29280000 | 2019-01-29 | 2019-01-29
2022-08-15 | 2022 | Marine Corps Active | M00146197 |  | 2021-09-13 | 2022-04-26 | WALSH FEDERAL, LLC | N4008522C0016 AWD | 0 | 16055000 | 2025-06-24 | 2025-06-24
2022-08-15 | 2019 | Marine Corps Active | M00146199 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N4008520C8501 AWD | 5813000 | 133928000 | 2022-07-14 | 2023-03-20
2022-08-15 | 2016 | Marine Corps Active | M00146222 |  | 2019-01-23 | 2019-04-18 | SAUER, INC. | N4008519C9021 | 21793000 | 22197000 | 2021-06-10 | 2021-06-10
2022-08-15 | 2019 | Marine Corps Active | M00146235 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N4008520C8501 AWD | 53073000 | 62549000 | 2022-07-14 | 2023-03-20
2022-08-15 | 2020 | Marine Corps Active | M00146246F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 17747042 | 19405000 | 2025-08-12 | 2025-08-12
2022-08-15 | 2020 | Marine Corps Active | M00146249 |  | 2020-10-26 | 2021-02-18 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008516D6303 N4008521F4682 | 1368000 | 1437000 | 2022-03-05 | 2022-08-11
2022-08-15 | 2019 | Marine Corps Active | M00146254F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 30990000 | 32513000 | 2025-08-12 | 2025-08-12
2022-08-15 | 2018 | Marine Corps Active | M00146766 |  | 2018-09-04 | 2018-09-29 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008516D6303 N4008518F7217 | 2468000 | 2444000 | 2020-01-08 | 2021-04-12
2022-08-15 | 2018 | Marine Corps Active | M00146990 |  | 2019-04-30 | 2021-05-27 | WHITING-TURNER CONTRACTING CO | N4008521C0035 AWD | 22677000 | 43001000 | 2023-05-01 | 2023-05-10
2022-08-15 | 2020 | Marine Corps Active | M00243312 |  | 2020-03-02 | 2020-05-29 | BRISTOL DESIGN BUILD SERVICES, LLC | N6247317D4627 N6247320F4683 | 9525039 | 10662000 | 2022-02-03 | 2022-08-22
2022-08-15 | 2017 | Marine Corps Active | M00263403 |  | 2017-01-27 | 2018-07-31 | KORTE CONSTRUCTION COMPANY | N4008518C0640 AWD | 30382000 | 31626000 | 2021-02-28 | 2022-03-18
2022-08-15 | 2019 | Marine Corps Active | M00263404 |  | 2019-02-14 | 2019-07-10 | R. C. CONSTRUCTION | N4008519C9017 AWD | 36938000 | 38095000 | 2021-08-17 | 2022-03-23
2022-08-15 | 2018 | Marine Corps Active | M00264542 |  | 2018-08-08 | 2019-05-30 | ARCHER WESTERN FEDERAL JV | N4008019C0023 AWD | 21419000 | 21978000 | 2020-10-30 | 2022-08-30
2022-08-15 | 2014 | Marine Corps Active | M00264588 |  | 2017-02-10 | 2018-09-29 | WHITING-TURNER CONTRACTING CO | N4008018C0034 AWD | 23040000 | 38549000 | 2020-06-06 | 2021-04-09
2022-08-15 | 2015 | Marine Corps Active | M00264635 |  | 2016-05-16 | 2016-11-16 | G-W MANAGEMENT SERVICES, LLC | N4008017C0014 AWD | 10883000 | 12141000 | 2018-03-25 | 2021-07-29
2022-08-15 | 2014 | Marine Corps Active | M00264677 |  | 2015-10-28 | 2016-03-31 | HARKINS BUILDERS INC. | N4008016C0151 AWD | 27064000 | 29429000 | 2018-01-05 | 2018-10-23
2022-08-15 | 2020 | Marine Corps Active | M00264719 |  | 2020-10-26 | 2021-03-22 | CLARK CONSTRUCTION GROUP, LLC. | N4008021C0005 AWD | 586000 | 70319000 | 2023-07-05 | 2023-07-05
2022-08-15 | 2019 | Marine Corps Active | M00264724 |  | 2019-06-05 | 2019-08-15 | G-W MANAGEMENT SERVICES, LLC | N4008019D0015 N4008019F4870 | 14142000 | 14683000 | 2021-01-30 | 2021-07-01
2022-08-15 | 2020 | Marine Corps Active | M00264733 |  | 2020-07-23 | 2020-09-29 | TUCKMAN-BARBEE CONSTRUCTION | N4008019D0018 N4008020F5390 | 3040000 | 3138000 | 2021-11-10 | 2022-04-12
2022-08-15 | 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274215C1305 AWD | 51071000 | 52768000 | 2018-08-11 | 2021-02-03
2022-08-15 | 2014 | Marine Corps Active | M00318863 |  | 2015-07-14 | 2016-09-19 | CONTRACK WATTS, INC | N6274216C1325 AWD | 50583000 | 87128000 | 2019-04-17 | 2020-03-07
2022-08-15 | 2018 | Marine Corps Active | M00318877 |  | 2020-05-20 | 2020-09-23 | NIKING CORP. | N6274220C1304 AWD | 34513000 | 18250000 | 2022-01-07 | 2022-02-11
2022-08-15 | 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720000 | 16255000 | 2016-12-18 | 2019-10-24
2022-08-15 | 2018 | Marine Corps Active | M00318887 |  | 2018-04-04 | 2018-12-28 | KIEWIT INFRASTRUCTURE WEST CO. | N6274219C1321 AWD | 18697000 | 37923000 | 2020-08-19 | 2021-01-25
2022-08-15 | 2016 | Marine Corps Active | M00318902 |  | 2016-05-27 | 2016-11-18 | NOVA GROUP INC | N6274217C1320 AWD | 24797000 | 29747000 | 2019-06-06 | 2021-08-13
2022-08-15 | 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 47645000 | 40956000 | 2020-09-18 | 2021-12-20
2022-08-15 | 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 53999000 | 50559000 | 2020-09-18 | 2021-12-20
2022-08-15 | 2017 | Marine Corps Active | M00318923 |  | 2017-04-07 | 2017-08-21 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6274217C1307 AWD | 72494000 | 82835000 | 2020-03-08 | 2022-05-21
2022-08-15 | 2019 | Marine Corps Active | M00318946 |  | 2018-11-20 | 2019-05-31 | HENSEL PHELPS CONSTRUCTION CO. | N6274219C1303 AWD | 62559000 | 123903000 | 2021-09-07 | 2022-08-27
2022-08-15 | 2021 | Marine Corps Active | M00318947 |  | 2021-12-08 | 2022-03-25 | HAKO PLUMBING, INC. | N6247820D4036 N6247822F4095 | 0 | 9621000 | 2023-04-24 | 2023-04-24
2022-08-15 | 2021 | Marine Corps Active | M00318964 |  | 2021-11-04 | 2022-01-18 | HAKO PLUMBING, INC. | N6247820D4036 N6247822F4051 | 0 | 8908000 | 2023-04-19 | 2023-04-19
2022-08-15 | 2019 | Marine Corps Active | M00681079 |  | 2019-07-24 | 2019-12-12 | ORION CONSTRUCTION CORPORATION | N6247320C0612 AWD | 35918000 | 67491000 | 2022-05-30 | 2022-05-30
2022-08-15 | 2020 | Marine Corps Active | M006811090 |  | 2020-04-16 | 2020-09-24 | DPR-RQ CONSTRUCTION, LLC | N6247320C0055 AWD | 53546419 | 82446000 | 2024-01-07 | 2024-01-07
2022-08-15 | 2021 | Marine Corps Active | M006811090A |  | 2020-05-15 | 2021-03-23 | DPR-RQ CONSTRUCTION, LLC | N6247320C0055 PC000009 | 0 | 0 | 2024-01-07 | 2024-01-07
2022-08-15 | 2021 | Marine Corps Active | M006811130 |  | 2020-07-23 | 2021-02-18 | HARPER CONSTRUCTION COMPANY, INC | N6247321D1206 N6247321F4378 | 42661879 | 48145000 | 2023-05-13 | 2023-05-22
2022-08-15 | 2018 | Marine Corps Active | M006811310 |  | 2018-04-12 | 2018-09-27 | HARPER CONSTRUCTION COMPANY, INC | N6247317D0817 | 62328000 | 46121000 | 2020-10-10 | 2022-01-15
2022-08-15 | 2018 | Marine Corps Active | M006811599 |  | 2019-01-15 | 2019-02-27 | ORION CONSTRUCTION CORPORATION | N6247318D5860 N6247319F4359 | 1876000 | 2333000 | 2020-02-26 | 2020-04-16
2022-08-15 | 2019 | Marine Corps Active | M006811901 |  | 2018-11-27 | 2019-05-02 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F4561 | 46146000 | 47707000 | 2022-06-09 | 2022-12-09
2022-08-15 | 2020 | Marine Corps Active | M006812000 |  | 2020-05-28 | 2020-12-17 | WHITING-TURNER CONTRACTING CO | N6247318D5858 N6247321F4212 | 3056000 | 62002000 | 2025-02-14 | 2025-02-14
2022-08-15 | 2019 | Marine Corps Active | M00681334 |  | 2019-06-21 | 2019-08-22 | I E PACIFIC INC | N6247317D4628 N6247319F5136 | 14684000 | 15716000 | 2021-08-06 | 2021-10-13
2022-08-15 | 2019 | Marine Corps Active | M006815001 |  | 2019-01-30 | 2019-04-09 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 | 9032000 | 8940000 | 2020-10-15 | 2022-01-12
2022-08-15 | 2019 | Marine Corps Active | M006815002 |  | 2019-02-05 | 2019-03-25 | SYNERGY ELECTRIC COMPANY INC | N6247319D2430 | 3326000 | 3443000 | 2020-03-30 | 2020-03-20
2022-08-15 | 2019 | Marine Corps Active | M00681574 |  | 2019-07-09 | 2019-08-22 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 N6247319F5115 | 12715000 | 12828000 | 2021-06-07 | 2021-12-10
2022-08-15 | 2014 | Marine Corps Active | M00681970 |  | 2014-07-01 | 2015-12-30 | SOLPAC CONSTRUCTION INC | N6247310D5411 0012 | 19459000 | 26563000 | 2018-04-27 | 2020-11-27
2022-08-15 | 2017 | Marine Corps Active | M60169464 |  | 2017-02-23 | 2017-06-29 | THE HASKELL COMPANY | N4008517C8327 AWD | 78310000 | 79928000 | 2020-07-13 | 2022-07-08
2022-08-15 | 2022 | Marine Corps Active | M60169492
2022-08-15 | 2018 | Marine Corps Active | M62204930 |  | 2017-03-07 | 2018-04-18 | M A MORTENSON COMPANY | N6247318D5850 N6247318F4497 | 23592000 | 24354000 | 2020-05-02 | 2020-05-17
2022-08-15 | 2020 | Marine Corps Active | M626131005
2022-08-15 | 2018 | Marine Corps Active | M626131006
2022-08-15 | 2021 | Marine Corps Active | M626131010U |  | 2021-06-01 | 2021-09-09 | MECCS MITOMO JV | N4008420D0071 N4008421F4605 | 0 | 986000 | 2022-07-06 | 2022-07-06
2022-08-15 | 2017 | Marine Corps Active | M626131701
2022-08-15 | 2020 | Marine Corps Active | M626132001 |  | 2020-11-13 | 2021-02-11 | SANKYO REINETSU CO., LTD. | N4008420D0073 N4008421F4127 | 18797000 | 18057000 | 2023-07-02 | 2023-07-02
2022-08-15 | 2016 | Marine Corps Active | M62613604
2022-08-15 | 2018 | Marine Corps Active | M62974539 |  | 2018-05-02 | 2018-07-03 | WHITING-TURNER CONTRACTING CO | N6247317D0822 N6247318F4783 | 37962000 | 38037000 | 2020-06-28 | 2022-04-04
2022-08-15 | 2016 | Marine Corps Active | M62974602 |  | 2017-03-31 | 2017-07-27 | STRAUB CONSTRUCTION, INC. | N6247316D1887 N6247317F4044 | 43119000 | 40940000 | 2019-06-30 | 2020-06-22
2022-08-15 | 2017 | Marine Corps Active | M62974612 |  | 2017-07-12 | 2019-06-13 | HARPER CONSTRUCTION COMPANY, INC | N6247316D1881 N6247319F4705 | 62293000 | 73989000 | 2022-06-06 | 2023-05-17
2022-08-15 | 2018 | Marine Corps Active | M670011043
2022-08-15 | 2019 | Marine Corps Active | M670011199F |  | 2019-10-15 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 19142000 | 20668000 | 2024-10-12 | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | M670011203F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 27688000 | 28944000 | 2024-09-30 | 2025-09-27
2022-08-15 | 2016 | Marine Corps Active | M670011280 |  | 2016-12-16 | 2017-05-30 | CADDELL CONSTRUCTION CO. (DE), LLC | N4008517C8325 AWD | 47882000 | 52784000 | 2019-06-24 | 2022-12-06
2022-08-15 | 2019 | Marine Corps Active | M670011300F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 17826000 | 20584000 | 2024-10-12 | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | M670011312F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 55017000 | 59555000 | 2024-09-30 | 2025-09-27
2022-08-15 | 2018 | Marine Corps Active | M670011320 |  | 2018-08-09 | 2018-09-28 | SAUER, INC. | N4008518C0610 AWD | 37174000 | 36007000 | 2020-10-23 | 2021-11-05
2022-08-15 | 2020 | Marine Corps Active | M670011338F |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N4008520C0145 AWD | 51246000 | 52967000 | 2025-05-27 | 2025-11-27
2022-08-15 | 2019 | Marine Corps Active | M670011387F |  | 2019-10-09 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N4008520C8505 AWD | 64921000 | 66954000 | 2025-03-06 | 2025-03-06
2022-08-15 | 2018 | Marine Corps Active | M670011479 |  | 2018-11-06 | 2019-06-14 | SAUER, INC. | N4008519C9053 AWD | 3247000 | 3600000 | 2020-10-26 | 2021-09-30
2022-08-15 | 2020 | Marine Corps Active | M670011483 |  | 2020-07-17 | 2020-09-25 | SAUER, INC. | N4008520D0035 N4008520F6732 | 11460484 | 12243000 | 2021-09-28 | 2022-06-22
2022-08-15 | 2020 | Marine Corps Active | M670011495 |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N4008520C0145 AWD | 35517314 | 37435000 | 2023-03-05 | 2023-03-19
2022-08-15 | 2018 | Marine Corps Active | M670011498 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N4008514D7742 N4008519F4172 | 3135000 | 3498000 | 2019-11-09 | 2022-07-29
2022-08-15 | 2018 | Marine Corps Active | M670011503 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N4008514D7742 N4008519F4172 | 3833000 | 4259000 | 2019-11-09 | 2022-07-29
2022-08-15 | 2019 | Marine Corps Active | M670011505F |  | 2020-01-23 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N4008520C8505 AWD | 66036000 | 64622000 | 2019-10-25 | 2025-03-06
2022-08-15 | 2020 | Marine Corps Active | M670011506F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 28045000 | 30887000 | 2024-09-30 | 2025-09-27
2022-08-15 | 2020 | Marine Corps Active | M670011507F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 17318680 | 21454000 | 2024-05-27 | 2025-01-07
2022-08-15 | 2019 | Marine Corps Active | M670011509F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 33391000 | 42099000 | 2017-05-30 | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | M670011512F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 135347000 | 142235000 | 2025-05-27 | 2025-11-27
2022-08-15 | 2020 | Marine Corps Active | M670011518F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 29242000 | 30508000 | 2024-09-30 | 2025-09-27
2022-08-15 | 2020 | Marine Corps Active | M670011519F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 36463000 | 37918000 | 2024-09-30 | 2025-09-27
2022-08-15 | 2019 | Marine Corps Active | M670011520F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 15383000 | 16905000 | 2019-10-25 | 2025-01-27
2022-08-15 | 2019 | Marine Corps Active | M670011522F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 26607000 | 28245000 | 2019-10-25 | 2025-01-27
2022-08-15 | 2019 | Marine Corps Active | M670011524F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 14143000 | 15581000 | 2021-06-16 | 2025-01-27
2022-08-15 | 2019 | Marine Corps Active | M670011525F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 7375000 | 9309000 | 2020-12-29 | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | M670011527F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 48103000 | 48878000 | 2025-05-27 | 2025-11-27
2022-08-15 | 2020 | Marine Corps Active | M670011529F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 22970805 | 27209000 | 2024-10-12 | 2025-01-27
2022-08-15 | 2020 | Marine Corps Active | M670011533F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 43802000 | 45332000 | 2024-09-30 | 2025-09-27
2022-08-15 | 2019 | Marine Corps Active | M670011604F |  | 2021-10-06 | 2022-05-31 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008518D1128 N6247022F4060 | 0 | 0 | 2023-11-22 | 2023-11-22
2022-08-15 | 2020 | Marine Corps Active | M670011800 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N4008521C0017 AWD | 5850000 | 76898000 | 2026-07-23 | 2027-05-09
2022-08-15 | 2021 | Marine Corps Active | M670011800A |  | 2020-07-10 | 2021-03-02 | ARCHER WESTERN FEDERAL JV | N4008521C0017 P00002 | 102629610 | 0 | 2026-07-23 | 2027-05-09
2022-08-15 | 2022 | Marine Corps Active | M670011800B
2022-08-15 | 2020 | Marine Corps Active | M670011801 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N4008521C0017 AWD | 5850000 | 56831000 | 2026-07-23 | 2027-05-09
2022-08-15 | 2020 | Marine Corps Active | M67001378F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 223502000 | 248966000 | 2024-10-12 | 2026-09-30
2022-08-15 | 2016 | Marine Corps Active | M67001686 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 3640000 | 3742000 | 2018-04-06 | 2021-04-22
2022-08-15 | 2020 | Marine Corps Active | M67001695F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 67658000 | 72155000 | 2024-10-12 | 2026-09-30
2022-08-15 | 2020 | Marine Corps Active | M67001707F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 79978000 | 85865000 | 2024-10-12 | 2026-09-30
2022-08-15 | 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159000 | 20079000 | 2019-02-01 | 2019-02-01
2022-08-15 | 2020 | Marine Corps Active | M67001728F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 48575000 | 54123000 | 2024-10-12 | 2026-09-30
2022-08-15 | 2016 | Marine Corps Active | M67001729 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 1885000 | 4896000 | 2018-04-06 | 2021-04-22
2022-08-15 | 2020 | Marine Corps Active | M67001883F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 54587000 | 58333000 | 2024-09-30 | 2025-09-27
2022-08-15 | 2019 | Marine Corps Active | M67004947 |  | 2019-08-07 | 2020-01-31 | THE HASKELL COMPANY | N4008520C8504 AWD | 29418000 | 29929000 | 2022-05-04 | 2022-07-27
2022-08-15 | 2018 | Marine Corps Active | M67004971 |  | 2017-12-12 | 2018-03-15 | DRACE CONSTRUCTION CORP. | N4008516D5524 N4008518F5082 | 1982000 | 3730000 | 2019-07-05 | 2019-07-05
2022-08-15 | 2016 | Marine Corps Active | M67004972 |  | 2016-12-14 | 2017-03-22 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N6945016D1112 WE01 | 8625000 | 8389000 | 2019-01-28 | 2019-02-23
2022-08-15 | 2021 | Marine Corps Active | M67004976 |  | 2021-10-25 | 2022-03-22 | U-SMC/DEMARIA JV1, LLC | N6945019D0921 N6945022F0122 | 0 | 4686000 | 2023-07-15 | 2023-07-15
2022-08-15 | 2018 | Marine Corps Active | M67004977 |  | 2018-07-18 | 2019-03-07 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008519C9126 | 23298000 | 23943000 | 2021-04-29 | 2021-05-27
2022-08-15 | 2016 | Marine Corps Active | M67029007 |  | 2016-10-25 | 2017-04-19 | TIDEWATER, INC | N4008017C0024 AWD | 1257000 | 2471000 | 2018-04-19 | 2020-07-30
2022-08-15 | 2016 | Marine Corps Active | M673991232 |  | 2017-06-27 | 2017-09-26 | PROCAL ELECTRIC INC | N6247316D1861 N6247317F4699 | 9329000 | 11735000 | 2019-04-19 | 2021-04-23
2022-08-15 | 2018 | Marine Corps Active | M67399192 |  | 2017-10-17 | 2018-09-29 | CDM CONSTRUCTORS INC | N6247318C4602 AWD | 55390000 | 104331000 | 2021-09-28 | 2023-02-15
2022-08-15 | 2015 | Marine Corps Active | M67399222 |  | 2016-02-22 | 2016-08-31 | AT&T GOVERNMENT SOLUTIONS, INC | N6247316C0601 AWD | 12948000 | 15099000 | 2019-03-04 | 2020-02-14
2022-08-15 | 2015 | Marine Corps Active | M67400213
2022-08-15 | 2016 | Marine Corps Active | M67400606 |  | 2016-07-20 | 2016-09-15 | NAVY STANDARD DOCUMENT | N4008516C5505 AWD | 8792000 | 8792000 | 2019-08-03 | 2018-03-26
2022-08-15 | 2017 | Marine Corps Active | M67400807
2022-08-15 | 2021 | Marine Corps Active | M67400901U |  | 2021-05-18 | 2021-07-01 | ACTY CO.,LTD. | N4008421C8000 AWD | 3417000 | 6518000 | 2022-03-14 | 2022-03-14
2022-08-15 | 2016 | Marine Corps Active | M67604132 |  | 2016-07-08 | 2016-08-31 | REYES CONSTRUCTION INC | N6247314D0068 0008 | 2887000 | 2712000 | 2017-10-30 | 2017-10-30
2022-08-15 | 2020 | Marine Corps Active | M67695009 |  | 2020-06-26 | 2020-09-16 | THE CLEMENT GROUP LLC | N6945019D0918 N6945020F0894 | 10933245 | 12689000 | 2022-03-25 | 2022-09-21
2022-08-15 | 2017 | Marine Corps Active | M67865198 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 35632000 | 39702000 | 2020-01-14 | 2020-06-26
2022-08-15 | 2018 | Marine Corps Active | M67865198 | M67865198A | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 79399000 | 83086000 | 2020-01-14 | 2020-06-26
2022-08-15 | 2017 | Marine Corps Active | M67865203 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 38707000 | 44546000 | 2020-01-14 | 2020-06-26
2022-08-15 | 2018 | Marine Corps Active | M67865210 |  | 2018-05-16 | 2018-08-30 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247318F4873 | 34513000 | 41722000 | 2020-05-20 | 2021-02-26
2022-08-15 | 2019 | Marine Corps Active | M67865222 |  | 2018-11-16 | 2019-03-14 | Granite Construction, Inc | N62473-19-C-5826 | 11358000 | 23767000 | 2020-09-27 | 2021-02-06
2022-08-15 | 2019 | Marine Corps Active | M67865238 |  | 2019-01-03 | 2019-03-08 | Teehee Engineering Inc. | N6247319C2425 | 4828000 | 7015000 | 2020-04-06 | 2020-04-06
2022-08-15 | 2017 | Marine Corps Active | M67865249 |  | 2017-09-19 | 2017-12-18 | R A BURCH CONSTRUCTION CO INC | N6247316D1884 N6247318F4138 | 32536000 | 34614000 | 2019-09-24 | 2020-10-01
2022-08-15 | 2021 | Marine Corps Active | M67865280 |  | 2021-04-26 | 2021-06-30 | DE LA FUENTE CONSTRUCTION, INC. | N6247321D1220 N6247321F4960 | 0 | 10560000 | 2023-03-07 | 2023-07-14
2022-08-15 | 2019 | Marine Corps Active | N41557270 |  | 2019-01-25 | 2019-09-12 | GILBANE SMCC ECC LLC | N6274219D1331 N6274219F9926 | 27191000 | 27162000 | 2022-03-25 | 2022-07-18
2022-08-15 | 2022 | Marine Corps Active | N41557280 |  | 2021-05-24 | 2022-05-04 | BLACK CONSTRUCTION-TUTOR PERINI JV | N6274219D1328 N6274222F9926 | 0 | 55794000 | 2024-08-22 | 2024-08-22
2022-08-15 | 2019 | Marine Corps Active | N41557290 |  | 2021-06-21 | 2022-01-11 | HENSEL PHELPS CONSTRUCTION CO. | N6274219D1332 N6274222F9921 | 0 | 194000 |  | 2025-01-10
2022-08-15 | 2019 | Marine Corps Active | N41557295 |  | 2019-04-15 | 2019-09-16 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274219C1301 AWD | 18002000 | 17676000 | 2021-12-04 | 2021-12-04
2022-08-15 | 2021 | Marine Corps Active | N41557296 |  | 2020-08-18 | 2021-03-17 | CORE TECH-HDCC-KAJIMA LLC | N6274219D1330 N6274221F9928 | 17683000 | 18451000 | 2023-03-28 | 2023-08-06
2022-08-15 | 2018 | Marine Corps Active | N41557601 |  | 2017-06-30 | 2018-05-16 | HENSEL PHELPS CONSTRUCTION CO. | N6274218C1316 AWD | 75233000 | 76221000 | 2020-10-02 | 2021-10-22
2022-08-15 | 2016 | Marine Corps Active | N41557715 |  | 2016-04-06 | 2017-08-24 | BLACK CONSTRUCTION CORP. | N6274217C1319 AWD | 123661000 | 196155000 | 2020-11-26 | 2023-01-08
2022-08-15 | 2019 | Marine Corps Active | N41557735 |  | 2019-06-11 | 2021-09-28 | BLACK CONSTRUCTION CORP. | N6274221C1346 AWD | 0 | 53084000 | 2024-10-25 | 2024-10-25
2022-08-15 | 2022 | Marine Corps Active | N61159305 |  | 2021-03-23 | 2022-05-04 | BLACK CONSTRUCTION-TUTOR PERINI JV | N6274219D1328 N6274222F9930 | 0 | 82075000 | 2024-08-22 | 2024-08-22
2022-08-15 | 2022 | Marine Corps Active | N61159306 |  | 2021-10-15 | 2022-05-04 | GILBANE SMCC ECC LLC | N6274219D1331 N6274222F9927 | 0 | 84521000 | 2024-09-06 | 2024-09-06
2022-08-15 | 2022 | Marine Corps Active | N61159307 |  | 2021-04-20 | 2022-04-14 | GILBANE SMCC ECC LLC | N6274219D1331 N6274222F9920 | 0 | 39507000 | 2024-08-02 | 2024-08-02
2022-08-15 | 2022 | Marine Corps Active | N61159310 |  | 2021-04-30 | 2022-04-27 | GILBANE SMCC ECC LLC | N6274219D1331 N6274222F9929 | 0 | 45364000 | 2024-08-18 | 2024-08-18
2022-08-15 | 2021 | Marine Corps Active | N61159311 |  | 2020-09-14 | 2021-03-15 | HENSEL PHELPS CONSTRUCTION CO. | N6274219D1332 N6274221F9927 | 27795000 | 28047000 | 2023-08-23 | 2023-08-23
2022-08-15 | 2021 | Marine Corps Active | N61159312
2022-08-15 | 2022 | Marine Corps Active | N61159326 |  | 2021-08-17 | 2022-04-01 | HENSEL PHELPS CONSTRUCTION CO. | N6274219D1332 N6274222F9925 | 0 | 40899000 | 2024-07-25 | 2024-07-25
2022-08-15 | 2021 | Marine Corps Active | N61159802 |  | 2021-04-08 | 2021-08-16 | CADDELL-NAN A JOINT VENTURE | N6274219D1329 N6274221F9933 | 0 | 41369000 | 2023-12-07 | 2023-12-07
2022-08-15 | 2021 | Marine Corps Active | N61159803 |  | 2021-04-08 | 2021-08-13 | CHUGACH CONSOLIDATED SOLUTIONS, LLC | N6274221C1315 AWD | 0 | 9390000 | 2022-08-27 | 2022-09-04
2022-08-15 | 2021 | Marine Corps Active | N61159804 |  | 2020-02-24 | 2021-03-22 | CORE TECH-HDCC-KAJIMA LLC | N6274221C1335 AWD | 36105000 | 36209000 | 2024-03-12 | 2024-03-12
2022-08-15 | 2019 | Marine Corps Active | N62813216 |  | 2019-09-06 | 2020-02-03 | RORE, INC. | N6247818D4024 N6274220F4001 | 17897000 | 20611000 | 2020-12-29 | 2022-09-30
2022-08-15 | 2018 | Marine Corps Reserve | M67861650 |  | 2018-12-13 | 2019-03-19 | NAVY STANDARD DOCUMENT | USACE | 11741000 | 11065000 | 2020-11-20 | 2020-11-20
2022-08-15 | 2020 | Marine Corps Reserve | M68479102
2022-08-15 | 2017 | Marine Corps Reserve | M68479135 |  | 2018-08-16 | 2019-01-22 | OAK GROUP, INC., THE | N4008517D5038 N4008519F4510 | 2109000 | 2291000 | 2020-01-28 | 2020-10-31
2022-08-15 | 2021 | Marine Corps Reserve | M68479303 |  | 2021-09-14 | 2022-02-02 | HESS CONSTRUCTION COMPANY, INC. | N4008022C0005 AWD | 0 | 44000 | 2024-09-17 | 2024-09-17
2022-08-15 | 2020 | Marine Corps Reserve | M68479811
2022-08-15 | 2016 | Marine Corps Reserve | N50092152 |  | 2019-05-02 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N4008519C9061 AWD | 18501000 | 18774000 | 2021-09-14 | 2022-02-04
2022-08-15 | 2020 | Marine Corps Reserve | N83447091
2022-08-15 | 2020 | Marine Corps Reserve | N83447181 |  | 2020-06-25 | 2020-09-25 | ENCANTO FACILITY SERVICES 2, LLC | N6945020D0036 N6945020F1278 | 0 | 1209000 | 2021-09-26 | 2021-09-26
2022-08-15 | 2020 | Marine Corps Reserve | N83447222 |  | 2020-05-08 | 2020-09-24 | N6945020C2575 AWD | N6945020C2575 AWD | 1763000 | 1921000 | 2021-09-20 | 2021-09-20
2022-07-31 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 114390000 | 2015-08-30 | 2016-05-12
2022-07-31 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 66900000 | 2015-08-30 | 2016-05-12
2022-07-31 | 2014 | Missile Defense Agency | 634 |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300000 | 15604000 | 2016-01-06 | 2016-05-02
2022-07-31 | 2016 | Missile Defense Agency | 640 |  | 2015-06-10 | 2016-02-10 | AMEC PROGRAMS, INC. | W912GB-16-C-0005 | 141906057 | 171152000 | 2018-05-30 | 2023-01-26
2022-07-31 | 2017 | Missile Defense Agency | 653 |  | 2017-02-01 | 2017-07-25 | AMES 1/Conam JV | W911KB-17-C-0029 | 6954581 | 8207372 | 2019-08-14 | 2021-09-29
2022-07-31 | 2017 | Missile Defense Agency | 657 |  | 2016-12-14 | 2017-04-28 | UNIT-ASRC Construction, LLC | W911KB-17-C-0002 | 112949720 | 119078184 | 2019-08-23 | 2020-06-01
2022-07-31 | 2017 | Missile Defense Agency | 657 |  | 2017-11-14 | 2018-02-15 | STG Pacific, LLC | W911KB-18-C-0015 | 24399601 | 24558572 | 2019-08-30 | 2019-06-27
2022-07-31 | 2017 | Missile Defense Agency | 657 |  | 2018-04-05 | 2018-09-07 | White Mountain Construction Company LLC | W911KB-18-R-0006 | 13335000 | 14660442 | 2020-09-30 | 2020-09-29
2022-07-31 | 2019 | Missile Defense Agency | 659 |  | 2018-10-10 | 2019-03-08 | CP03-UNIT-ASRC Construction LLC | W911KB-19-C-0001 | 128657500 | 136771860 | 2021-06-30 | 2022-07-28
2022-07-31 | 2019 | Missile Defense Agency | 659 |  | 2019-09-23 | 2019-12-18 | CP04-RED POINT CONSTRUCTION, LLC | W911KB-20-C-0002 | 13820000 | 15307457 | 2021-06-14 | 2021-08-16
2022-07-31 | 2017 | Missile Defense Agency | 673 |  | 2017-04-15 | 2017-08-03 | Indyne, Inc. | W912DY-11-D-0002 | 877752 | 1098939 | 2019-06-27 | 2022-08-15
2022-07-31 | 2018 | Missile Defense Agency | 674 |  | 2018-02-05 | 2018-04-10 | CP01-Alaska Aggregate Products, LLC | W911KB-18-C-0023 | 2600710 | 2549000 | 2018-06-30 | 2018-06-30
2022-07-31 | 2018 | Missile Defense Agency | 674 |  | 2018-01-05 | 2018-05-07 | CP02-Brice Civil Constructors | W911KB-18-C-0028 | 18965310 | 19525000 | 2018-10-30 | 2018-10-11
2022-07-31 | 2018 | Missile Defense Agency | 674 |  | 2018-02-16 | 2018-06-07 | CP02TP-Construction Services SATOC | W912DY-14-D-0042 | 2432439 | 2432439 | 2018-10-31 | 2018-10-11
2022-07-31 | 2018 | Missile Defense Agency | 674 |  | 2018-04-17 | 2018-07-20 | CP03-Watterson Construction Company | W911KB-18-C-0030 | 28807000 | 32124438 | 2020-11-01 | 2021-03-29
2022-07-31 | 2018 | Missile Defense Agency | 674 |  | 2018-09-23 | 2018-12-20 | CP04-NEESER CONSTRUCTION, INC | W911KB-19-C-0006 | 83991000 | 100560673 | 2021-09-30 | 2022-11-30
2022-07-31 | 2019 | Missile Defense Agency | 679 |  | 2022-02-15 | 2022-05-02 | ASRC Builders, LLC | W911KB-22-C-0009 | 8508953 | 9126931 | 2023-10-21 | 2023-10-21
2022-07-31 | 2021 | Missile Defense Agency | 680 |  | 2020-09-28 | 2021-03-17 | Davis Constructors & Engineers, Inc | W911KB-21-C-0012 | 45487063 | 46340792 | 2023-01-31 | 2023-01-31
2022-07-31 | 2021 | Missile Defense Agency | 689 |  | 2020-06-01 | 2021-09-30 | AYTEKIN SEROL INSAAT TAAHHUT MUHENDISLIK | W912GB-18-F-0186 | 3260896 | 0 | 2023-10-01 | 2023-12-22
2022-07-06 | 2021 | National Geospatial-Intelligence Agency | ARN13-0020 |  | 2021-05-18 | 2021-09-30 | SES Civil and Environmental LLC | W912DQ-21-C-7000 | 3749520 | 3914453 | 2023-11-17 | 2023-11-17
2022-07-31 | 2018 | National Geospatial-Intelligence Agency | NGA-016A |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ-17-R-7000 | 319965869 | 339161532 | 2023-10-19 | 2024-06-28
2022-07-31 | 2018 | National Geospatial-Intelligence Agency | NGA-016A-IPO |  | 2019-04-07 | 2019-07-10 | Modular Management Group (MMG) | W912DQ-17-C-7002 | 3146064 | 3152224 | 2024-07-08 | 2024-07-08
2022-07-31 | 2019 | National Geospatial-Intelligence Agency | NGA-016B |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ-17-R-7000 | 315507977 | 350248347 | 2023-10-19 | 2024-06-28
2022-07-31 | 2016 | National Security Agency | 30583 |  | 2015-09-30 | 2016-06-17 | Clark Construction | W912DR-16-C-0013 | 616311000 | 711458239 | 2020-09-10 | 2022-02-23
2022-07-31 | 2019 | National Security Agency | 32100 |  | 2019-03-18 | 2020-01-30 | Hensel-Phelps | W912DR-20-C-0004 | 34227105 | 36404760 | 2022-11-17 | 2022-11-17
2022-07-31 | 2022 | National Security Agency | 34490 |  | 2021-07-28 | 2022-04-11 | Henry Brothers Ltd | Z9D7393Y18 | 13704230 | 13704230 | 2023-06-14 | 2023-06-14
2022-07-31 | 2017 | National Security Agency | 35161 |  | 2021-08-09 | 2021-08-24 | Grunley Construction | W912DR-21-C-0016 | 21386000 | 21645166 | 2024-03-28 | 2024-03-28
2022-07-31 | 2019 | National Security Agency | 35168 |  | 2018-10-04 | 2019-03-28 | Hensel-Phelps | W912DR-19-C-0013 | 650261000 | 675763813 | 2023-04-30 | 2023-05-09
2022-07-31 | 2022 | National Security Agency | 38440/38441 |  | 2020-10-15 | 2022-05-26 | Hensel-Phelps | W912DR-22-C-0018 | 301612000 | 79134209 | 2026-06-15 | 2026-06-15
2022-07-31 | 2022 | National Security Agency | 38608 |  | 2020-09-30 | 2022-04-13 | Balfour Beatty Construction, LLC | W912DR-22-C-0012 | 692844325 | 85279976 | 2026-05-10 | 2026-05-10
2022-08-15 | 2016 | Navy Active | M006811220 |  | 2016-06-24 | 2016-11-30 | J. R. FILANC CONSTRUCTION COMPANY,INC | N6247317C3403 AWD | 39860000 | 75510000 | 2019-03-30 | 2019-03-30
2022-08-15 | 2016 | Navy Active | M62613603 |  | 2016-03-01 | 2018-12-18 | Awarded by Other Agency | N40084USACE02 AWD | 8904000 | 8904000 | 2020-07-08 | 2021-03-12
2022-08-15 | 2014 | Navy Active | N00128714 |  | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N4008518C8707 AWD | 32940000 | 98152000 | 2020-08-14 | 2020-10-23
2022-08-15 | 2017 | Navy Active | N00128714 | N00128714A | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N4008518C8707 AWD | 37695000 | 36245000 | 2020-08-14 | 2020-10-23
2022-08-15 | 2020 | Navy Active | N00129898 |  | 2020-04-07 | 2020-09-29 | WEEKS MARINE, INC | N4008520C0074 AWD | 2468000 | 4602000 | 2022-10-26 | 2023-01-31
2022-08-15 | 2016 | Navy Active | N00204723 |  | 2016-11-23 | 2017-06-28 | EMR, INC. | N6945017D0507 N6945017F1003 | 20056000 | 20173000 | 2019-10-16 | 2020-09-20
2022-08-15 | 2019 | Navy Active | N00207674 |  | 2019-02-08 | 2019-05-17 | DESBUILD INCORPORATEDDBA DES BUILD | N6945016D1111 N6945019F0712 | 3036000 | 3084000 | 2020-10-13 | 2021-05-20
2022-08-15 | 2019 | Navy Active | N00207711 |  | 2019-07-18 | 2019-09-13 | UP-SIDE MANAGEMENT COMPANY | N6945019C5648 AWD | 2323000 | 4425000 | 2020-09-14 | 2020-09-14
2022-08-15 | 2018 | Navy Active | N00213211 |  | 2019-05-03 | 2021-05-13 | KORTE CONSTRUCTION COMPANY | N6945021C0019 AWD | 52266000 | 101717000 | 2023-12-29 | 2023-12-29
2022-08-15 | 2021 | Navy Active | N00213211A
2022-08-15 | 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151000 | 14261000 | 2018-01-08 | 2018-01-08
2022-08-15 | 2019 | Navy Active | N00213720 |  | 2019-04-17 | 2019-09-26 | THE HASKELL COMPANY | N6945019D0909 N6945019F0874 | 30995000 | 31203000 | 2021-12-13 | 2023-06-29
2022-08-15 | 2018 | Navy Active | N00213731 |  | 2019-06-25 | 2019-09-19 | BURNS & MCDONNELL ENGINEERINGCOMPANY, INC. | N6945016D0100 N6945019F0105 | 9097000 | 9246000 | 2020-11-30 | 2021-12-23
2022-08-15 | 2018 | Navy Active | N00213741 |  | 2019-05-15 | 2019-09-27 | KORTE CONSTRUCTION COMPANY | N6945019C0903 AWD | 63582000 | 122481000 | 2022-01-17 | 2022-10-28
2022-08-15 | 2018 | Navy Active | N00216450 |  | 2018-05-25 | 2018-09-05 | URS GROUP, INC. | N6247013D6022 N6247018F4121 | 50430000 | 49912000 | 2021-09-04 | 2022-07-08
2022-08-15 | 2018 | Navy Active | N00216485 |  | 2018-06-28 | 2018-08-22 | GFP GROUP, L.L.C. | N6945016D0615 N6945018F2384 | 4213000 | 4859000 | 2020-03-14 | 2021-01-30
2022-08-15 | 2019 | Navy Active | N002450888 |  | 2019-01-02 | 2019-03-28 | HELIX ELECTRIC, INC. | N6247316D3201 0010 | 36336000 | 48661000 | 2021-08-18 | 2022-10-06
2022-08-15 | 2019 | Navy Active | N00245110 |  | 2019-04-19 | 2019-08-12 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247319F5055 | 14817000 | 13919000 | 2021-03-23 | 2021-03-23
2022-08-15 | 2017 | Navy Active | N00245312 |  | 2017-04-25 | 2017-06-29 | SYNERGY ELECTRIC COMPANY INC | N6247316D1862 N6247317F4054 | 2527000 | 2463000 | 2018-12-15 | 2018-12-15
2022-08-15 | 2019 | Navy Active | N00245440 |  | 2019-05-01 | 2019-06-14 | MANSON CONSTRUCTION CO | N6247319C1208 AWD | 47724000 | 102541000 | 2021-10-27 | 2021-10-31
2022-08-15 | 2021 | Navy Active | N00245443 |  | 2021-03-05 | 2021-04-30 | MANSON CONSTRUCTION CO | N6247321D1406 N6247321F4668 | 3164000 | 111553000 | 2023-09-17 | 2023-09-17
2022-08-15 | 2015 | Navy Active | N00245800 |  | 2015-06-15 | 2015-09-17 | S & R CONSTRUCTIONA JOINT VENTURE | N6247315C1604 AWD | 41838000 | 85837000 | 2019-04-10 | 2019-04-10
2022-08-15 | 2017 | Navy Active | N002461017 |  | 2017-03-22 | 2017-09-28 | WEST POINT CONTRACTORS, INC. | N6247317C0815 AWD | 2943000 | 5324000 | 2018-12-12 | 2018-12-12
2022-08-15 | 2019 | Navy Active | N002461018 |  | 2019-04-03 | 2019-07-25 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247319C1211 AWD | 53283000 | 94294000 | 2021-05-28 | 2022-07-25
2022-08-15 | 2020 | Navy Active | N002461024 |  | 2019-10-16 | 2020-06-11 | HARPER CONSTRUCTION COMPANY, INC | N6247320C0553 AWD | 69801056 | 77984000 | 2023-01-01 | 2023-03-03
2022-08-15 | 2021 | Navy Active | N00246762 |  | 2021-01-05 | 2021-11-04 | REYES CONSTRUCTION INC | N6247318D5862 N6247322F4006 | 0 | 9000000 | 2022-11-03 | 2022-11-03
2022-08-15 | 2017 | Navy Active | N00246947 |  | 2017-01-30 | 2017-03-30 | REYES CONSTRUCTION INC | N6247314D0068 0009 | 11659000 | 29830000 | 2018-10-06 | 2020-03-31
2022-08-15 | 2018 | Navy Active | N00246988 |  | 2018-06-06 | 2018-08-30 | RQ CONSTRUCTION, LLC | N6247317D0820 N6247318F5040 | 32923000 | 35325000 | 2021-03-22 | 2022-03-12
2022-08-15 | 2017 | Navy Active | N00246991 |  | 2016-11-23 | 2017-03-30 | RQ-DPR JV | N6247317C0808 AWD | 61541000 | 76610000 | 2019-04-23 | 2021-04-30
2022-08-15 | 2017 | Navy Active | N00620240 |  | 2016-06-14 | 2017-08-09 | BETHEL-WEBCOR JV-1 | N4425517D4032 N4425517F4132 | 28966000 | 56315000 | 2020-03-26 | 2021-01-19
2022-08-15 | 2019 | Navy Active | N00620253 |  | 2018-10-12 | 2019-03-11 | BETHEL-WEBCOR JV-1 | N4425517D4032 XN4425519F4123 | 12949000 | 13813000 | 2020-11-28 | 2021-07-06
2022-08-15 | 2017 | Navy Active | N00620256 |  | 2018-04-05 | 2019-01-30 | RQ CONSTRUCTION, LLC | N4425519C0003 AWD | 45981000 | 47623000 | 2021-07-19 | 2021-10-29
2022-08-15 | 2019 | Navy Active | N00620258 |  | 2018-11-14 | 2019-02-26 | TOMPCO, INC | N4425517D4014 N4425519F4091 | 7114000 | 7433000 | 2021-03-08 | 2021-01-29
2022-08-15 | 2019 | Navy Active | N32414106 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N4008519C9057 AWD | 66625000 | 66760000 | 2022-02-13 | 2022-11-25
2022-08-15 | 2019 | Navy Active | N324141098 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N4008519C9057 AWD | 3142000 | 3331000 | 2022-02-13 | 2022-11-25
2022-08-15 | 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 AWD | 34317000 | 59721000 | 2016-11-23 | 2021-11-19
2022-08-15 | 2019 | Navy Active | N32443256 |  | 2021-09-02 | 2021-11-29 | W.M. JORDAN COMPANY INC. | N4008519D9089 N4008522F4169 | 0 | 25344000 | 2024-01-28 | 2024-01-28
2022-08-15 | 2018 | Navy Active | N32443257 |  | 2017-11-03 | 2018-09-17 | RQ CONSTRUCTION, LLC | N4008518C1107 AWD | 73055000 | 138564000 | 2021-06-18 | 2022-03-30
2022-08-15 | 2016 | Navy Active | N32443614 |  | 2017-06-01 | 2017-12-15 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 45614000 | 46609000 | 2021-04-15 | 2021-06-30
2022-08-15 | 2017 | Navy Active | N32443614 | N32443614A | 2017-06-01 | 2017-12-14 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 2624000 | 2584000 | 2021-04-15 | 2021-06-30
2022-08-15 | 2020 | Navy Active | N32443653 |  | 2020-04-16 | 2020-09-04 | MEB GENERAL CONTRACTORS, INC. | N4008520C0063 AWD | 46986935 | 49658000 | 2023-06-17 | 2023-07-13
2022-08-15 | 2019 | Navy Active | N324461074 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N4008520C8500 AWD | 43523000 | 46027000 | 2021-01-27 | 2022-04-15
2022-08-15 | 2019 | Navy Active | N324461088 |  | 2019-05-23 | 2019-08-05 | TANTARA ASSOCIATES CORPORATION | N4008517D5049 N4008519F6032 | 3458000 | 6915000 | 2020-10-31 | 2021-07-30
2022-08-15 | 2017 | Navy Active | N32446285 |  | 2017-01-17 | 2017-06-29 | L.S. BLACK CONSTRUCTORS-LOEFFELCONSTRUCTION | N4008517C5056 AWD | 18927000 | 20332000 | 2019-05-10 | 2021-01-21
2022-08-15 | 2018 | Navy Active | N32446293 |  | 2018-08-31 | 2019-09-25 | METHUEN CONSTRUCTION CO., INC | N4008519C9261 AWD | 62457000 | 63927000 | 2022-08-09 | 2022-08-09
2022-08-15 | 2014 | Navy Active | N32446308 |  | 2015-09-29 | 2016-04-21 | TRITON MARINE CONSTRUCTION CORP. | N4008516C3013 AWD | 34722000 | 35093000 | 2018-10-25 | 2018-10-25
2022-08-15 | 2019 | Navy Active | N32446310 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N4008520C8500 AWD | 177914000 | 138799000 | 2021-01-27 | 2022-04-15
2022-08-15 | 2017 | Navy Active | N32446371 |  | 2017-09-19 | 2018-03-30 | ENGINEERED CONSTRUCTION SERVICES,INC | N4008518C8719 AWD | 30414000 | 43854000 | 2021-09-14 | 2021-09-14
2022-08-15 | 2021 | Navy Active | N32446381 |  | 2020-11-13 | 2021-08-13 | CAISSON PROCUREMENT | N4008521C0077 AWD | 0 | 82397000 | 2028-06-01 | 2028-06-01
2022-08-15 | 2018 | Navy Active | N32446385 |  | 2018-07-05 | 2018-09-20 | STRUCTURAL ASSOCIATES, INC | N4008517D5048 N4008518F6907 | 975000 | 1638000 | 2019-10-08 | 2019-10-08
2022-08-15 | 2017 | Navy Active | N3379A223 |  | 2017-10-13 | 2018-06-28 | J/V P. & C. DEVELOPMENT S.A. -ERGOTEM S.A. | N6247018C4015 AWD | 25219000 | 44936000 | 2020-10-05 | 2022-07-31
2022-08-15 | 2018 | Navy Active | N3379A505 |  | 2018-06-12 | 2018-10-26 | ECC MEZZ LLC | N6247019D5002 N6247019F9001 | 11315000 | 23450000 | 2020-06-18 | 2021-11-30
2022-08-15 | 2021 | Navy Active | N360423271 |  | 2020-10-30 | 2021-03-25 | SYNERGY ELECTRIC COMPANY INC | N6247319D2430 N6247321F4370 | 1000 | 49502000 | 2023-05-03 | 2023-10-16
2022-08-15 | 2015 | Navy Active | N41557230 |  | 2015-04-02 | 2015-11-17 | RELYANT GLOBAL LLC | N6274216C1317 AWD | 20799000 | 32731000 | 2019-01-29 | 2019-01-29
2022-08-15 | 2018 | Navy Active | N41557250 |  | 2018-01-24 | 2018-09-24 | BLACK CONSTRUCTION CORP. | N6274218C1300 AWD | 43203000 | 43735000 | 2021-01-21 | 2021-07-27
2022-08-15 | 2018 | Navy Active | N41557260 |  | 2018-01-24 | 2018-09-21 | BLACK CONSTRUCTION CORP. | N6274218C1300 AWD | 53554000 | 53270000 | 2020-12-28 | 2021-07-27
2022-08-15 | 2016 | Navy Active | N41557635 |  | 2016-06-24 | 2017-08-01 | TIKIGAQ CONSTRUCTION, LLC | N4019217C1305 AWD | 8715000 | 18199000 | 2019-02-22 | 2022-01-09
2022-08-15 | 2020 | Navy Active | N41557735A |  | 2019-06-11 | 2021-09-28 | BLACK CONSTRUCTION CORP. | N6274221C1346 AWD | 0 | 85262000 | 2024-10-25 | 2024-10-25
2022-08-15 | 2017 | Navy Active | N41557H279 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 78787000 | 79925000 | 2022-07-05 | 2023-03-13
2022-08-15 | 2018 | Navy Active | N41557H280 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 40850000 | 39042000 | 2022-07-05 | 2023-03-13
2022-08-15 | 2019 | Navy Active | N41557H282 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 83378000 | 84153000 | 2022-07-05 | 2023-03-13
2022-08-15 | 2015 | Navy Active | N42237099 |  | 2014-02-24 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 39730000 | 41478000 | 2018-06-20 | 2019-03-27
2022-08-15 | 2017 | Navy Active | N42237671 |  | 2017-08-10 | 2018-01-16 | DESIGN BUILD INCORPORATED | N6945016D1111 | 2979000 | 3018000 | 2019-08-23 | 2019-11-22
2022-08-15 | 2017 | Navy Active | N47608265 |  | 2018-04-10 | 2019-01-30 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008019C2015 AWD | 46919000 | 54397000 | 2020-09-28 | 2022-05-22
2022-08-15 | 2017 | Navy Active | N47608421 |  | 2017-08-03 | 2017-09-27 | REILLY CONSTRUCTION, INC | N4008017D0012 N4008017F4480 | 2627000 | 4467000 | 2018-10-24 | 2020-06-16
2022-08-15 | 2016 | Navy Active | N47608975 |  | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N4008018C0311 AWD | 38795000 | 41331000 | 2020-02-02 | 2020-07-23
2022-08-15 | 2017 | Navy Active | N47608975 | N47608975A | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N4008018C0311 AWD | 2145000 | 2043000 | 2020-02-02 | 2020-12-29
2022-08-15 | 2020 | Navy Active | N476091900 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 437309406 | 493641000 | 2023-11-30 | 2023-11-30
2022-08-15 | 2020 | Navy Active | N476091901 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 166423000 | 2023-11-30 | 2023-11-30
2022-08-15 | 2020 | Navy Active | N476091902 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 107093000 | 2023-11-30 | 2023-11-30
2022-08-15 | 2020 | Navy Active | N476091903 |  | 2020-05-22 | 2020-09-17 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247320F5462 | 111944000 | 135363000 | 2022-11-04 | 2022-11-04
2022-08-15 | 2020 | Navy Active | N476091904 |  | 2021-02-11 | 2021-06-25 | RQ CONSTRUCTION, LLC | N6247321D1211 N6247321F4921 | 0 | 257260000 | 2025-08-29 | 2025-08-29
2022-08-15 | 2020 | Navy Active | N476091907 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 78280000 | 2023-11-30 | 2023-11-30
2022-08-15 | 2020 | Navy Active | N476091908
2022-08-15 | 2020 | Navy Active | N476091911 |  | 2021-01-19 | 2021-06-24 | WEBCOR CONSTRUCTION LP | N6247321D1214 N6247321F4923 | 0 | 150899000 | 2024-01-22 | 2024-01-22
2022-08-15 | 2020 | Navy Active | N476091914 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 84684000 | 2023-11-30 | 2023-11-30
2022-08-15 | 2020 | Navy Active | N476091916 |  | 2020-05-15 | 2020-09-03 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247320F5296 | 53426000 | 62621000 | 2022-09-19 | 2022-09-19
2022-08-15 | 2020 | Navy Active | N476091917
2022-08-15 | 2020 | Navy Active | N476091918 |  | 2020-11-23 | 2021-03-03 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247321F4428 | 50924000 | 63339000 | 2023-05-03 | 2023-05-03
2022-08-15 | 2020 | Navy Active | N476091919 |  | 2021-02-03 | 2021-05-20 | HARPER CONSTRUCTION COMPANY, INC | N6247321D1206 N6247321F4741 | 3397000 | 48523000 | 2024-02-05 | 2024-02-05
2022-08-15 | 2020 | Navy Active | N476091920
2022-08-15 | 2020 | Navy Active | N476091921
2022-08-15 | 2020 | Navy Active | N476091922 |  | 2021-02-03 | 2021-06-10 | HARPER CONSTRUCTION COMPANY, INC | N6247321D1206 N6247321F4825 | 0 | 80613000 | 2024-01-23 | 2024-01-23
2022-08-15 | 2020 | Navy Active | N476091924 |  | 2020-10-16 | 2021-01-22 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 N6247321F4264 | 1660000 | 6851000 | 2023-02-06 | 2023-02-06
2022-08-15 | 2020 | Navy Active | N47609810 |  | 2020-04-15 | 2020-06-26 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247319D2438 N6247320F4817 | 53866451 | 57405000 | 2022-04-10 | 2022-08-20
2022-08-15 | 2018 | Navy Active | N50092176 |  | 2017-09-14 | 2018-04-19 | CIVIL WORKS CONTRACTING LLC | N4008517D0358 N4008518F5423 | 2670000 | 2747000 | 2019-08-05 | 2019-08-05
2022-08-15 | 2019 | Navy Active | N60042117
2022-08-15 | 2020 | Navy Active | N601911026 |  | 2020-07-23 | 2020-12-11 | TAZEWELL-BGI JV, LLC | N4008518D1144 N4008521F4343 | 4218000 | 5074000 | 2022-06-10 | 2022-12-06
2022-08-15 | 2018 | Navy Active | N60191160 |  | 2019-08-28 | 2020-02-14 | SYNCON, LLC | N4008520C8503 AWD | 25795000 | 24567000 | 2022-03-01 | 2022-08-24
2022-08-15 | 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446000 | 19724000 | 2016-10-25 | 2021-02-12
2022-08-15 | 2017 | Navy Active | N60201154 |  | 2017-02-23 | 2017-06-29 | HENSEL PHELPS CONSTRUCTION CO | N6945014D1269 N6945017F0700 | 40518000 | 42718000 | 2019-09-26 | 2019-12-27
2022-08-15 | 2019 | Navy Active | N60201195 |  | 2019-06-18 | 2019-08-16 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N6945016D1112 N6945019F0716 | 3600000 | 3750000 | 2020-08-29 | 2021-03-31
2022-08-15 | 2018 | Navy Active | N60201421 |  | 2017-10-16 | 2018-08-03 | DESBUILD INCORPORATEDDBA DES BUILD | N6945016D1111 N6945018F0723 | 11062000 | 12076000 | 2020-08-04 | 2022-06-25
2022-08-15 | 2016 | Navy Active | N60201424 |  | 2016-01-26 | 2016-07-14 | ARTEC GROUP (THE) INC | N6945016D1110 0001 | 14616000 | 16220000 | 2019-02-05 | 2019-02-05
2022-08-15 | 2019 | Navy Active | N60201426 |  | 2019-05-31 | 2019-09-13 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014D1267 N6945019F0708 | 76123000 | 73251000 | 2021-04-02 | 2022-11-23
2022-08-15 | 2019 | Navy Active | N60201427 |  | 2018-07-30 | 2019-02-22 | Archer Western Federal JV | N6945019F0855 | 27496000 | 26593000 | 2021-02-05 | 2021-06-04
2022-08-15 | 2016 | Navy Active | N60495111 |  | 2016-05-31 | 2017-08-17 | BRISTOL GENERAL CONTRACTORS, LLC | N6247315D2404 N6247317F4334 | 11253000 | 19074000 | 2019-02-25 | 2020-07-18
2022-08-15 | 2014 | Navy Active | N60495393 |  | 2017-02-28 | 2018-04-19 | WALTERS, K. G. CONSTRUCTION CO., IN | N6247318C2205 AWD | 15675000 | 30040000 | 2020-05-08 | 2020-11-30
2022-08-15 | 2015 | Navy Active | N60495420 |  | 2015-07-17 | 2015-09-16 | STRAUB CONSTRUCTION, INC. | N6247315D2427 0002 | 25541000 | 28487000 | 2017-11-24 | 2019-10-31
2022-08-15 | 2018 | Navy Active | N60495426 |  | 2018-11-07 | 2018-12-28 | J I GARCIA CONSTRUCTION INC | N6247318D5817 N6247319F4162 | 3295000 | 3234000 | 2019-10-25 | 2019-10-25
2022-08-15 | 2017 | Navy Active | N60495440 |  | 2017-07-20 | 2018-08-06 | STRAUB CONSTRUCTION, INC. | N6247316D1887 N6247318F4874 | 18936000 | 19001000 | 2020-08-25 | 2020-10-17
2022-08-15 | 2019 | Navy Active | N60508253 |  | 2019-05-13 | 2021-05-12 | WEBCO L.L.C. | N6945019D1085 N6945021F0280 | 10500000 | 16343000 | 2024-05-11 | 2024-05-11
2022-08-15 | 2019 | Navy Active | N60508288 |  | 2019-07-26 | 2020-01-10 | EMR, INC. | N6945018D1318 N6945020F0875 | 2466000 | 7156000 | 2021-01-11 | 2023-03-30
2022-08-15 | 2019 | Navy Active | N60514160 |  | 2018-12-10 | 2019-09-19 | RQ CONSTRUCTION, LLC | N6945019C0501 AWD | 66357000 | 66434000 | 2022-03-18 | 2022-05-26
2022-08-15 | 2019 | Navy Active | N60514343 |  | 2019-06-04 | 2019-09-20 | ISLANDS MECHANICAL CONTRACTOR | N6945018D1313 N6945019F1007 | 12440000 | 12470000 | 2021-09-20 | 2022-10-01
2022-08-15 | 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458000 | 8792000 | 2017-01-17 | 2017-01-17
2022-08-15 | 2021 | Navy Active | N610542101 |  | 2020-10-23 | 2021-03-05 | NIPPO CORPORATION | N4008419D0075 N4008421F4145 | 1382000 | 2107000 | 2024-05-01 | 2024-05-01
2022-08-15 | 2019 | Navy Active | N61056512 |  | 2018-10-31 | 2019-04-19 | Awarded by Other Agency | N40084USACE01 AWD | 9050000 | 9050000 | 2020-12-31 | 2020-12-31
2022-08-15 | 2017 | Navy Active | N61064402 |  | 2018-04-20 | 2018-12-26 | NOVA GROUP INC | N6274219C1320 AWD | 25137000 | 26498000 | 2021-07-13 | 2021-12-27
2022-08-15 | 2016 | Navy Active | N61064416 |  | 2018-04-19 | 2018-09-06 | HELIX ELECTRIC, INC. | N6247818C1516 AWD | 23932000 | 52933000 | 2020-05-28 | 2022-06-17
2022-08-15 | 2014 | Navy Active | N61065202 |  | 2014-12-11 | 2016-08-29 | VANDER WERFF, PETER CONSTRUCTION | N6247314D0039 0011 | 15972000 | 15287000 | 2018-06-10 | 2019-12-11
2022-08-15 | 2019 | Navy Active | N61065224 |  | 2018-12-10 | 2019-07-15 | MANSON/CONNOLLY SEAL BEACH JV | N6247319C2450 AWD | 111089000 | 118595000 | 2022-06-30 | 2024-06-18
2022-08-15 | 2019 | Navy Active | N61065241 |  | 2019-06-17 | 2019-08-19 | REYES CONSTRUCTION INC | N6247318D5862 N6247319F4995 | 23001000 | 24216000 | 2021-04-15 | 2021-04-26
2022-08-15 | 2021 | Navy Active | N61065243 |  | 2021-05-05 | 2021-08-12 | REYES CONSTRUCTION INC | N6247318D5862 N6247321F5105 | 0 | 22091000 | 2023-08-27 | 2023-08-27
2022-08-15 | 2022 | Navy Active | N61065243A
2022-08-15 | 2018 | Navy Active | N61066604
2022-08-15 | 2018 | Navy Active | N61151163 |  | 2018-02-12 | 2018-09-29 | JOHN C. GRIMBERG CO., INC. | N4008018C0008 AWD | 37296000 | 70272000 | 2021-08-14 | 2021-08-14
2022-08-15 | 2015 | Navy Active | N61151190 |  | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 15316000 | 15910000 | 2019-09-06 | 2023-04-09
2022-08-15 | 2017 | Navy Active | N61151190 | N61151190A | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 6546000 | 4583000 | 2020-01-13 | 2023-04-09
2022-08-15 | 2015 | Navy Active | N61151287 |  | 2015-03-04 | 2015-09-02 | M A MORTENSON COMPANY | N4008015C0167 AWD | 25679000 | 29774000 | 2017-07-17 | 2019-10-31
2022-08-15 | 2015 | Navy Active | N61152621 |  | 2015-07-15 | 2016-03-31 | TURNER CONSTRUCTION COMPANY | N4008016C0156 AWD | 120181000 | 141620000 | 2019-09-08 | 2020-05-22
2022-08-15 | 2020 | Navy Active | N61755491 |  | 2020-03-02 | 2020-08-07 | BLACK CONSTRUCTION-TUTOR PERINI JV | N6274219D1328 N6274220F9924 | 50514009 | 54490000 | 2022-12-20 | 2022-12-20
2022-08-15 | 2022 | Navy Active | N61755519
2022-08-15 | 2016 | Navy Active | N61755535 |  | 2016-11-10 | 2017-08-21 | CONTRACK WATTS, INC | N6274217C1325 AWD | 47314000 | 89164000 | 2020-01-03 | 2020-09-10
2022-08-15 | 2019 | Navy Active | N61755640 |  | 2019-02-20 | 2019-06-25 | GILBANE FEDERAL | N6274219C1310 AWD | 36419000 | 71356000 | 2022-10-07 | 2022-11-04
2022-08-15 | 2017 | Navy Active | N61755652 |  | 2017-06-12 | 2018-05-23 | APTIM FEDERAL SERVICES, LLC | N6274218C1318 AWD | 28975000 | 30191000 | 2020-04-03 | 2021-08-15
2022-08-15 | 2018 | Navy Active | N61755680 |  | 2018-08-03 | 2018-09-28 | RELIABLE BUILDERS, INC. | N4019216D2704 N4019218F4410 | 2804000 | 2536000 | 2019-09-27 | 2021-05-26
2022-08-15 | 2018 | Navy Active | N61766661 |  | 2021-07-28 | 2022-04-21 | GRANITE CONSTRUCTION COMPANY GUAM | N6274222C1329 AWD | 0 | 83000 | 2024-07-10 | 2024-07-10
2022-08-15 | 2017 | Navy Active | N62588307 |  | 2018-04-03 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N6247019C5009 AWD | 10833000 | 11394000 | 2021-02-09 | 2022-02-18
2022-08-15 | 2017 | Navy Active | N62588308 |  | 2018-08-09 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N6247019C5009 AWD | 4894000 | 5050000 | 2021-02-09 | 2022-02-18
2022-08-15 | 2019 | Navy Active | N62588312
2022-08-15 | 2019 | Navy Active | N62604855 |  | 2019-02-22 | 2019-05-15 | EMR, INC. | N6945017D0507 N6945019F0710 | 21022000 | 22424000 | 2022-06-30 | 2022-06-30
2022-08-15 | 2022 | Navy Active | N62688095
2022-08-15 | 2020 | Navy Active | N626881035 |  | 2020-11-12 | 2021-08-20 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008521D0083 N4008521F6191 | 0 | 2908000 | 2024-03-22 | 2024-03-22
2022-08-15 | 2021 | Navy Active | N626881035A |  | 2020-11-12 | 2021-08-20 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008521D0083 N4008521F6191 | 0 | 2907000 | 2024-03-22 | 2024-03-22
2022-08-15 | 2021 | Navy Active | N62688404 |  | 2021-03-29 | 2021-09-30 | BAMFORTH ENGINEERS + SURVEYORS,INC. | N4008519D9164 N4008520F4014-New Mod | 0 | 1547000 | 2019-11-30 | 2023-06-20
2022-08-15 | 2018 | Navy Active | N62688495 |  | 2017-07-10 | 2018-09-28 | WHITING-TURNER CONTRACTING CO | N4008518C1148 AWD | 35158000 | 67819000 | 2021-02-04 | 2023-05-26
2022-08-15 | 2016 | Navy Active | N62688610 |  | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N4008517C0307 AWD | 34675000 | 50207000 | 2019-10-25 | 2020-12-30
2022-08-15 | 2017 | Navy Active | N62688610 | N62688610A | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N4008517C0307 AWD | 12166000 | 12166000 | 2019-10-25 | 2020-12-30
2022-08-15 | 2018 | Navy Active | N62688762 |  | 2018-01-25 | 2018-05-02 | TAZEWELL HOMELAND JV, LLC | N4008518R1123 | 2573000 | 3096000 | 2019-07-02 | 2021-01-03
2022-08-15 | 2016 | Navy Active | N62688913 |  | 2017-03-23 | 2018-04-23 | WHITING-TURNER CONTRACTING CO | N4008518C1134 AWD | 114000000 | 151000000 | 2020-11-01 | 2022-03-16
2022-08-15 | 2018 | Navy Active | N62813013 |  | 2018-12-14 | 2019-07-26 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274219C1317 AWD | 59383000 | 120284000 | 2021-04-26 | 2021-09-25
2022-08-15 | 2020 | Navy Active | N62813033 |  | 2020-04-22 | 2020-08-10 | HDR ENGINEERING, INC.DBA HONOLULU HDR HAWAII PACIFIC | N6247820C4016 AWD | 50430000 | 38345000 | 2022-09-09 | 2022-09-09
2022-08-15 | 2016 | Navy Active | N62813036 |  | 2015-10-28 | 2016-01-26 | BETHEL-WEBCOR JV-1 | N6247814D4001 KB01 | 8520000 | 9589000 | 2018-03-26 | 2021-07-06
2022-08-15 | 2021 | Navy Active | N62813044 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N6247820D4015 N6247821F4087 | 2072000 | 39107000 | 2023-11-12 | 2023-11-12
2022-08-15 | 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810000 | 5336000 | 2016-05-18 | 2019-12-31
2022-08-15 | 2021 | Navy Active | N628131006 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N6247820D4015 N6247821F4087 | 2072000 | 30342000 | 2023-11-12 | 2023-11-12
2022-08-15 | 2019 | Navy Active | N62813169 |  | 2018-10-15 | 2019-03-29 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N62742-19-C-1319 | 64705000 | 69777000 | 2022-01-24 | 2022-08-03
2022-08-15 | 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970000 | 42072000 | 2017-08-03 | 2020-10-06
2022-08-15 | 2018 | Navy Active | N62813704 |  | 2018-09-21 | 2019-03-12 | KIEWIT INFRASTRUCTURE WEST CO. | N62478-19-C-1515 | 73199000 | 137497000 | 2021-06-19 | 2021-07-21
2022-08-15 | 2020 | Navy Active | N628632001
2022-08-15 | 2021 | Navy Active | N62863313 |  | 2021-07-22 | 2021-12-16 | ACCIONA CMS JV, LLC | N6247021D0011 N6247022F9000 | 0 | 58227000 | 2024-09-09 | 2024-09-09
2022-08-15 | 2020 | Navy Active | N62863605 |  | 2020-09-03 | 2021-04-12 | UTE CASTELLANO COBRA MACC | N3319119D0801 N3319121F4133 | 7127000 | 9151000 | 2023-01-17 | 2023-01-17
2022-08-15 | 2021 | Navy Active | N62863620 |  | 2021-09-01 | 2021-12-21 | ACCIONA CMS JV, LLC | N6247021D0011 N6247022F9001 | 0 | 25766000 | 2024-07-01 | 2024-07-01
2022-08-15 | 2017 | Navy Active | N62863621 |  | 2017-03-07 | 2017-08-31 | CONSTRUCCIONES FELIPE CASTELLANOCOBRA INSTALACIONES Y SERVICIOS | N6247017C5006 AWD | 21868000 | 23524000 | 2023-06-09 | 2023-01-08
2022-08-15 | 2015 | Navy Active | N62863712 |  | 2015-04-11 | 2015-11-20 | COBRA INSTALCIONES Y SERVICIOS SA | N6247016C6001 AWD | 19252000 | 22559000 | 2018-05-23 | 2022-12-27
2022-08-15 | 2020 | Navy Active | N62863785 |  | 2021-10-07 | 2021-12-21 | FERROVIAL AGROMAN SA | N6247021D0016 N6247022F9002 | 0 | 138000 | 2023-12-31 | 2023-12-31
2022-08-15 | 2019 | Navy Active | N62863811 |  | 2020-12-28 | 2021-08-30 | ACCIONA CMS JV, LLC | N6247021D0011 N6247021F9009 | 0 | 18208000 | 2024-04-16 | 2024-04-16
2022-08-15 | 2019 | Navy Active | N62863812 |  | 2020-05-14 | 2020-09-23 | CONSTRUCTORA SAN JOSE SA | N6247020C0009 AWD | 137000 | 5526000 | 2022-06-30 | 2022-06-30
2022-08-15 | 2020 | Navy Active | N62995130 |  | 2020-07-06 | 2020-09-29 | WOLFF & MULLER GOVERNMENT SERVICES | N6247020C0013 AWD | 39712368 | 47088000 | 2025-06-05 | 2026-02-06
2022-08-15 | 2016 | Navy Active | N62995407 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 23632000 | 23970000 | 2019-04-23 | 2021-12-14
2022-08-15 | 2016 | Navy Active | N62995655 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 28340000 | 69127000 | 2019-04-23 | 2021-12-14
2022-08-15 | 2017 | Navy Active | N62995737 |  | 2016-09-09 | 2017-02-28 | ENVIRONMENTAL CHEMICAL CORPORATION | N3319116D1010 JN01 | 6096000 | 16391000 | 2018-08-22 | 2021-01-21
2022-08-15 | 2019 | Navy Active | N63005955U
2022-08-15 | 2021 | Navy Active | N63005964
2022-08-15 | 2020 | Navy Active | N63005974
2022-08-15 | 2016 | Navy Active | N63005976
2022-08-15 | 2017 | Navy Active | N63005985 |  | 2018-02-13 | 2019-06-14 | JUDE & L CONSTRUCTION, LLC | N3319119C0805 AWD | 3407000 | 6453000 | 2021-03-25 | 2021-03-25
2022-08-15 | 2016 | Navy Active | N63042218 |  | 2015-12-10 | 2016-05-10 | A&D GC INC | N6247315D2403 0003 | 7386000 | 7509000 | 2017-11-16 | 2020-09-17
2022-08-15 | 2018 | Navy Active | N63042282 |  | 2018-01-23 | 2018-09-19 | R A BURCH CONSTRUCTION CO INC | N6247318C2201 AWD | 52594000 | 98657000 | 2021-02-24 | 2022-02-25
2022-08-15 | 2019 | Navy Active | N63042284 |  | 2018-11-09 | 2019-09-16 | HARPER CONSTRUCTION COMPANY, INC | N6247319C2455 AWD | 107641000 | 103233000 | 2021-11-17 | 2022-08-12
2022-08-15 | 2019 | Navy Active | N63042392 |  | 2019-05-09 | 2019-07-30 | POWER PRO PLUS INC. | N6247319D2428 N6247319F4769 | 13545000 | 14238000 | 2021-05-06 | 2021-05-06
2022-08-15 | 2022 | Navy Active | N63402391A
2022-08-15 | 2021 | Navy Active | N66691131 |  | 2021-09-01 | 2022-02-04 | Macro Vantage Levant DMCC | N6247022C0002 AWD | 0 | 39135000 | 2024-10-20 | 2024-10-20
2022-08-15 | 2019 | Navy Active | N66691144
2022-08-15 | 2018 | Navy Active | N66691911 |  | 2018-06-18 | 2018-12-12 | AKTOR S.A. - TSONTOS S.A. J/V | N6247019C5006 AWD | 10141000 | 3548000 | 2021-02-14 | 2021-10-04
2022-08-15 | 2017 | Navy Active | N68436400 |  | 2017-08-10 | 2018-09-29 | CUSTOM MECHANICAL SYSTEMS CORP(CMS) | N4425517D4034 N4425518F4438 | 38496000 | 41615000 | 2021-06-30 | 2022-03-19
2022-08-15 | 2016 | Navy Active | N68436401 |  | 2016-03-29 | 2017-09-26 | TOMPCO, INC | N4425517C8002 AWD | 17270000 | 30362000 | 2020-01-04 | 2021-07-06
2022-08-15 | 2016 | Navy Active | N68436431 |  | 2016-03-31 | 2016-08-11 | NOVA GROUP INC | N4425516C7002 AWD | 19943000 | 23523000 | 2017-11-14 | 2018-05-18
2022-08-15 | 2017 | Navy Active | N68436438 |  | 2017-01-20 | 2018-04-23 | VET INDUSTRIAL INC | N4425517D4007 N4425518F4134 | 10040000 | 20803000 | 2019-10-30 | 2020-08-14
2022-08-15 | 2020 | Navy Active | N68436447 |  | 2020-01-10 | 2020-06-08 | N4425520C1002 AWD | N4425520C1002 AWD | 1876000 | 53581000 | 2023-08-02 | 2023-08-02
2022-08-15 | 2017 | Navy Active | N68436834 |  | 2019-03-18 | 2020-02-03 | MANSON CONSTRUCTION CO | N4425520C2002 AWD | 73000000 | 102028000 | 2022-07-04 | 2022-08-24
2022-08-15 | 2016 | Navy Active | N68436983 |  | 2016-04-15 | 2016-09-21 | NOVA GROUP INC | N4425516C7005 AWD | 31744000 | 37407000 | 2018-02-13 | 2019-04-21
2022-08-15 | 2015 | Navy Active | N68436990 | N68436990C | 2010-07-07 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00004 | 80735000 | 82357000 | 2017-09-30 | 2017-09-30
2022-08-15 | 2015 | Navy Active | N68436993 |  | 2015-09-30 | 2016-08-30 | WATTS-ORION JV | N4425516C7004 AWD | 32047000 | 34667000 | 2019-08-07 | 2019-08-07
2022-08-15 | 2019 | Navy Active | N68469001 |  | 2019-06-07 | 2019-09-16 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247019F9101 | 40000000 | 103921000 | 2024-09-15 | 2024-09-15
2022-08-15 | 2015 | Navy Active | N68469275 |  | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 31151000 | 85724000 | 2019-11-15 | 2022-11-13
2022-08-15 | 2018 | Navy Active | N68469275 | N68469275A | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 39776000 | 37882000 | 2019-11-15 | 2022-11-13
2022-08-15 | 2017 | Navy Active | N68469760
2022-08-15 | 2020 | Navy Active | N69212169 |  | 2020-11-09 | 2021-03-25 | SAUER, INC. | N4008521C0028 AWD | 52191740 | 58183000 | 2023-06-25 | 2024-07-17
2022-08-15 | 2018 | Navy Active | N69212995 |  | 2018-12-19 | 2019-01-31 | AECOM CONSTRUCTION, INC. | N4008519D9066 N4008519F4710 | 31074000 | 59242000 | 2021-06-25 | 2021-12-08
2022-08-15 | 2019 | Navy Active | N69232586 |  | 2019-02-08 | 2019-09-26 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247319F5449 | 27152000 | 27173000 | 2020-02-15 | 2021-07-01
2022-08-15 | 2019 | Navy Active | N69232777 |  | 2019-05-30 | 2019-08-28 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F5130 | 19686000 | 21707000 | 2021-01-11 | 2021-11-24
2022-08-15 | 2019 | Navy Active | N83447084 |  | 2019-07-31 | 2019-09-17 | UNIFIED SERVICES OF TEXAS | N6945015D1618 N6945019F2598 | 2500000 | 4798000 | 2020-09-20 | 2021-02-25
2022-08-15 | 2017 | Navy Reserve | M68479777 |  | 2017-07-25 | 2020-02-05 | OAK GROUP, INC., THE | N4008517D5038 N4008520F4527 | 17729000 | 49963000 | 2021-08-30 | 2022-06-01
2022-08-15 | 2015 | Navy Reserve | N00129664 |  | 2015-08-24 | 2015-08-25 | VETERANS CONSTRUCTION, LLC | N4008515C9610 AWD | 1989000 | 1959000 | 2017-04-21 | 2017-04-21
2022-08-15 | 2020 | Navy Reserve | N00206475 |  | 2020-01-30 | 2020-08-13 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945019D0908 N6945020F0891 | 6796000 | 27380000 | 2023-03-06 | 2023-06-06
2022-08-15 | 2019 | Navy Reserve | N00206493 |  | 2019-10-03 | 2020-01-09 | DAWSON FEDERAL, INC. | N6945018D1320 N6945020F0873 | 4632000 | 4480000 | 2021-01-28 | 2022-01-04
2022-08-15 | 2017 | Navy Reserve | N00206500 |  | 2016-11-04 | 2017-06-29 | SAUER, INC. | N6945017C1613 AWD | 11589000 | 14281000 | 2019-07-27 | 2020-10-01
2022-08-15 | 2018 | Navy Reserve | N42237642 |  | 2018-05-04 | 2018-09-12 | LEEBCOR SERVICES LLC | N6945016D1113 N6945018F0731 | 14240000 | 19710000 | 2020-01-06 | 2021-10-16
2022-08-15 | 2019 | Navy Reserve | N42237643 |  | 2018-12-03 | 2019-08-09 | WINDAMIR DEVELOPMENT INC | N6945019D0922 N6945019F0864 | 11207000 | 11589000 | 2021-10-03 | 2022-05-04
2022-08-15 | 2019 | Navy Reserve | N61065160 |  | 2018-11-01 | 2019-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F4183 | 19180000 | 20204000 | 2021-02-07 | 2021-06-01
2022-08-15 | 2018 | Navy Reserve | N63042366 |  | 2018-06-04 | 2019-04-11 | SOLPAC CONSTRUCTION INC | N6247318D5855 | 16347000 | 17468000 | 2021-03-26 | 2022-03-02
2022-08-15 | 2018 | Navy Reserve | N83447077 |  | 2018-05-14 | 2018-09-26 | EMR, INC. | N6945018D1318 N6945018F0894 | 11343000 | 22027000 | 2019-12-31 | 2020-12-31
2022-08-08 | 2015 | Washington Headquarters Services | 80011 |  | 2018-08-20 | 2019-05-09 | Cherokee Nations Environmental Solutions | HQ0034-19-C-0043 | 15100000 |  | 2021-06-21 | 2022-05-16
2022-08-08 | 2018 | Washington Headquarters Services | 87637 |  | 2018-07-05 | 2020-03-27 | Sauer Incorporated | W912DR-20-C-0014 | 9711000 | 9711000 | 2022-06-21 | 2023-07-30
2022-08-08 | 2019 | Washington Headquarters Services | 87645 |  | 2019-07-22 | 2019-09-30 | John C. Grimberg Co, Inc. | W912DR19C0057 | 9255000 | 9255000 | 2021-04-23 | 2022-12-30
2022-08-08 | 2019 | Washington Headquarters Services | 88790 |  | 2019-10-25 | 2020-03-27 | Grunley Construction Company, Inc. | W912DR-20-C-0015 | 20553000 | 20553000 | 2022-07-05 | 2022-11-10
2022-08-08 | 2018 | Washington Headquarters Services | 88963 |  | 2019-05-22 | 2020-01-07 | HSU Development, Inc | W912DR-17-D-0015 | 11774418 |  | 2022-01-20 | 2022-08-12
2022-08-08 | 2022 | Washington Headquarters Services | 90570
2022-08-08 | 2018 | Washington Headquarters Services | 91474 |  | 2019-03-08 | 2019-06-28 | Grunley Construction Company, Inc. | W912DR-17-D-0002 | 24006000 |  | 2021-01-22 | 2023-12-29
2022-08-08 | 2018 | Washington Headquarters Services | 91474A |  | 2018-03-06 | 2018-09-25 | MC DEAN | HQ0034-17-D-0006 | 1186116 | 1186116 | 2019-06-18 | 2019-06-18
2022-08-08 | 2020 | Washington Headquarters Services | 91531
2022-08-08 | 2020 | Washington Headquarters Services | 92232 |  | 2020-03-12 | 2021-03-25 | Grunley Construction Company, Inc. | W912DR-21-C-0009 | 16690000 | 16690000 | 2023-04-30 | 2023-12-27
2022-08-08 | 2022 | Washington Headquarters Services | 95677
2022-08-08 | 2022 | Washington Headquarters Services | 95696

## EXPENDITURES
Expenditure Data as of Date | Appropriation Fiscal Year | Project Sponsor Component Name | Appropriation Fund Type Name | Use of Funds | Aggregated Appropriated Amount | Aggregated Current Obligated Amount | Aggregated Current Expenditure Amount
2022-06-30 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73937000 | 60586000 | 61380000
2022-06-30 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093000 | 3217000 | 18347000
2022-06-30 | 2016 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 94590000 | 35507000 | 71855000
2022-06-30 | 2017 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 56984000 | 56984000 | 19237000
2022-06-30 | 2018 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 80617000 | 57546000 | 7414000
2022-06-30 | 2019 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 75247000 | 0 | 0
2022-06-30 | 2020 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 75312000 | 25620000 | 591000
2022-06-30 | 2015 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 0 | 0 | 0
2022-06-30 | 2022 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 105258000 | 35061000 | 0
2022-06-30 | 2021 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 94245000 | 0 | 0
2022-06-30 | 2021 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 161809000 | 161626000 | 76843000
2022-06-30 | 2022 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 140942000 | 71285000 | 9003000
2022-06-30 | 2017 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 124813000 | 120714000 | 108263000
2022-06-30 | 2018 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 138783000 | 137385000 | 111603000
2022-06-30 | 2019 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 158232000 | 159354000 | 97548000
2022-06-30 | 2020 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 122590000 | 121347000 | 72960000
2022-06-30 | 2013 | Air Force Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 379000 | 325000 | 325000
2022-06-30 | 2014 | Air Force Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 23291000 | 23291000 | 23291000
2022-06-30 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 10738000 | 10705000 | 9733000
2022-06-30 | 2016 | Air Force Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 87809000 | 87061000 | 81273000
2022-06-30 | 2017 | Air Force Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 199393000 | 191641000 | 190089000
2022-06-30 | 2018 | Air Force Active | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 217485000 | 208483000 | 191688000
2022-06-30 | 2019 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 450277000 | 413436000 | 372002000
2022-06-30 | 2020 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 332636000 | 218139000 | 160094000
2022-06-30 | 2021 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 271356000 | 171132000 | 83986000
2022-06-30 | 2022 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 332575000 | 228129000 | 168755000
2022-06-30 | 2022 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 10458000 | 0 | 0
2022-06-30 | 2021 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 2969000 | 942000 | 688000
2022-06-30 | 2015 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 0 | 0 | 0
2022-06-30 | 2013 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY14 MILCON; design of FY13 non-PB projects if any; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3952000 | 293000 | 735000
2022-06-30 | 2014 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267000 | 0 | 0
2022-06-30 | 2016 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY17 MILCON; design of FY16 non-PB projects if any; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 9849000 | 2489000 | 2695000
2022-06-30 | 2017 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY18 MILCON; design of FY17 non-PB projects if any; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4368000 | 3027000 | 4307000
2022-06-30 | 2018 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY19 MILCON; design of FY18 non-PB projects if any; start design of F20 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4445000 | 1875000 | 4009000
2022-06-30 | 2019 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY20 MILCON; design of FY19 non-PB projects if any; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3199000 | 2061000 | 954000
2022-06-30 | 2020 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3409000 | 2822000 | 2812000
2022-06-30 | 2013 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 19006000 | 18972000 | 18772000
2022-06-30 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448000 | 20230000 | 19804000
2022-06-30 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5548000 | 5548000 | 5548000
2022-06-30 | 2016 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22900000 | 21810000 | 21053000
2022-06-30 | 2017 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 41237000 | 40450000 | 34081000
2022-06-30 | 2018 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 41400000 | 34949000 | 25631000
2022-06-30 | 2019 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 32967000 | 12128000 | 12025000
2022-06-30 | 2020 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 87082000 | 37125000 | 12343000
2022-06-30 | 2021 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 85000000 | 15168000 | 5574000
2022-06-30 | 2022 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 79244000 | 4074000 | 4074000
2022-07-31 | 2011 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1650000 | 1521000 | 1521000
2022-07-31 | 2012 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200000 | 1285000 | 1287000
2022-07-31 | 2013 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 2875000 | 426000 | 426000
2022-07-31 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229000 | 66000 | 66000
2022-07-31 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892000 | 81000 | 300000
2022-07-31 | 2016 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 13400000 | 999000 | 661000
2022-07-31 | 2017 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs. | 13500000 | 6466000 | 6637000
2022-07-31 | 2018 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs. | 24725000 | 13171000 | 18336000
2022-07-31 | 2019 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs. | 4055000 | 3011000 | 282000
2022-07-31 | 2020 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 4604000 | 697000 | 11000
2022-07-31 | 2021 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 3270000 | 0 | 0
2022-07-31 | 2011 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 2753000 | 2646000 | 2646000
2022-07-31 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5434000 | 2260000 | 2258000
2022-07-31 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997000 | 0 | 0
2022-07-31 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530000 | 44000 | 59000
2022-07-31 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400000 | 608000 | 665000
2022-07-31 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6121000 | 1125000 | 2946000
2022-07-31 | 2017 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1500000 | 0 | 0
2022-07-31 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13610000 | 3424000 | 1573000
2022-07-31 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3358000 | 0 | 0
2022-07-31 | 2020 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 12146000 | 0 | 0
2022-07-31 | 2021 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5647000 | 0 | 0
2022-07-31 | 2013 | Air National Guard | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 4000000 | 1594000 | 1594000
2022-07-31 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400000 | 626000 | 517000
2022-07-31 | 2022 | Air National Guard | Planning and Design - Military Construction | Complete design of FY23 MILCON; start design of FY24 MILCON; fund Congressionally directed designs. | 39682000 | 0 | 0
2022-07-31 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700000 | 885000 | 884000
2022-07-31 | 2016 | Air National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 5104000 | 982000 | 971000
2022-07-31 | 2017 | Air National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs. | 10462000 | 11152000 | 9776000
2022-07-31 | 2018 | Air National Guard | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs. | 54597000 | 34980000 | 30011000
2022-07-31 | 2019 | Air National Guard | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs. | 33114000 | 13762000 | 10664000
2022-07-31 | 2020 | Air National Guard | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 15431000 | 4700000 | 2090000
2022-07-31 | 2021 | Air National Guard | Planning and Design - Military Construction | Complete design of FY22 MILCON; start design of FY23 MILCON; fund Congressionally directed designs. | 3414000 | 0 | 0
2022-07-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000000 | 4810000 | 220000
2022-07-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 29454000 | 18744000 | 2397000
2022-07-31 | 2019 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 46145000 | 20833000 | 6403000
2022-07-31 | 2018 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44382000 | 25941000 | 19094000
2022-07-31 | 2017 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17495000 | 14996000 | 14958000
2022-07-31 | 2016 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7734000 | 404000 | 404000
2022-07-31 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6100000 | 0 | 0
2022-07-31 | 2022 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 29068000 | 0 | 0
2022-07-31 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000000 | 1611000 | 1611000
2022-07-31 | 2013 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5900000 | 91000 | 82000
2022-07-31 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000000 | 33873062 | 33873062
2022-07-31 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000000 | 22999621 | 22999621
2022-07-31 | 2015 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28000000 | 27985359 | 27985359
2022-07-31 | 2016 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36000000 | 35998550 | 35818311
2022-07-31 | 2017 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 18000000 | 17998791 | 17998791
2022-07-31 | 2018 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28700000 | 28699745 | 27936166
2022-07-31 | 2019 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000000 | 15892849 | 15847689
2022-07-31 | 2020 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 31000000 | 30492044 | 30240258
2022-07-31 | 2021 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 39000000 | 36626106 | 34645970
2022-07-31 | 2022 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 27000000 | 610224 | 547941
2022-07-31 | 2013 | Army Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46173000 | 46090698 | 46090691
2022-07-31 | 2014 | Army Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575000 | 41552298 | 41539587
2022-07-31 | 2015 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 18127000 | 23126879 | 23112218
2022-07-31 | 2016 | Army Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 73245000 | 73137394 | 72262529
2022-07-31 | 2017 | Army Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 138159000 | 111918475 | 109964536
2022-07-31 | 2018 | Army Active | Planning and Design - Military Construction | Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 122470000 | 113392055 | 109889581
2022-07-31 | 2019 | Army Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 115067000 | 96932736 | 90816814
2022-07-31 | 2020 | Army Active | Planning and Design - Military Construction | Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 105099000 | 102551574 | 95079561
2022-07-31 | 2021 | Army Active | Planning and Design - Military Construction | Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 108000000 | 95650182 | 72169392
2022-07-31 | 2022 | Army Active | Planning and Design - Military Construction | Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 149649000 | 5454604 | 1761608
2022-07-31 | 2013 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4641000 | 4605750 | 4605750
2022-07-31 | 2014 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4408000 | 4370513 | 4350513
2022-07-31 | 2015 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 1309000 | 1305379 | 1275379
2022-07-31 | 2016 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7195000 | 7180054 | 7075842
2022-07-31 | 2017 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2618000 | 2617410 | 2585337
2022-07-31 | 2018 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 29271000 | 29252595 | 27958331
2022-07-31 | 2019 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 18326000 | 18068227 | 8757010
2022-07-31 | 2020 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 9222000 | 16530567 | 6413018
2022-07-31 | 2021 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 11300000 | 2734976 | 509084
2022-07-31 | 2022 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7545000 | 3979339 | 1329844
2022-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24952712 | 24952530
2022-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24980592 | 24778829
2022-07-31 | 2015 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24890149 | 24663787
2022-07-31 | 2016 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 22975569 | 22337753
2022-07-31 | 2017 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 35000000 | 29827985 | 26864746
2022-07-31 | 2018 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 41500000 | 28669407 | 27956065
2022-07-31 | 2019 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 82000000 | 79954750 | 76879676
2022-07-31 | 2020 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 70600000 | 67325030 | 55105306
2022-07-31 | 2021 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 50900000 | 28614652 | 9129449
2022-07-31 | 2010 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2022-07-31 | 2011 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2022-07-31 | 2012 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2022-07-31 | 2013 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 67943000 | 46505000 | 42677000
2022-07-31 | 2014 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 3897000 | 3871000 | 3767000
2022-07-31 | 2015 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 4855000 | 4730000 | 4730000
2022-07-31 | 2016 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 94000 | 0 | 0
2022-07-31 | 2017 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2022-07-31 | 2018 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 40255000 | 39409000 | 38445000
2022-07-31 | 2019 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 55729000 | 55840000 | 49795000
2022-07-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2022-07-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2022-07-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2022-07-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4608000 | 4550000 | 4550000
2022-07-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4952000 | 3819000 | 3819000
2022-07-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4100000 | 2200000 | 2200000
2022-07-31 | 2016 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5000000 | 4927000 | 4892000
2022-07-31 | 2017 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 8433000 | 7907000 | 4200000
2022-07-31 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 7700000 | 6967000 | 3519000
2022-07-31 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2022-08-11 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 79430000 | 68213820 | 68213820
2022-08-11 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 2615000 | 2810000 | 2810000
2022-08-11 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 9600000 | 12189000 | 12189000
2022-08-11 | 2021 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 33728000 | 33728000 | 0
2022-05-11 | 2017 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2018 to 2021 | 27660000 | 27660000 | 24910066
2022-05-11 | 2018 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2019 to 2022 | 23012000 | 23012000 | 23012000
2022-05-11 | 2019 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2020 to 2023 | 49805000 | 44805000 | 38504924
2022-05-11 | 2020 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2021 to 2024 | 27000000 | 27000000 | 3864479
2022-05-11 | 2022 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2023 to 2025 | 20862000 | 20862000 | 0
2022-05-11 | 2021 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2021 to 2022 | 9726000 | 9726000 | 0
2022-05-11 | 2022 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2022 to 2023 | 6668000 | 6668000 | 0
2022-05-11 | 2020 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2021 to 2022 | 16736000 | 16736000 | 2935443
2022-05-11 | 2019 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2019 to 2020 | 17366000 | 17366000 | 17366000
2022-05-11 | 2018 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2018 to 2019 | 2039000 | 2039000 | 2039000
2022-05-11 | 2015 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2015 to 2017 | 5932000 | 5932000 | 5932000
2022-08-01 | 2008 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI andFY 08/09/ 10/11/12 MILCON projects | 5161000 | 5159000 | 5159000
2022-08-01 | 2009 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13593000 | 13496000 | 13496000
2022-08-01 | 2010 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 10/11/ 12/13 MILCON projects | 8755000 | 8755000 | 8755000
2022-08-01 | 2011 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 11/12/ 13 MILCON projects | 75242000 | 75050000 | 75050000
2022-08-01 | 2012 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 12/13 MILCON projects | 64551000 | 63922443 | 63922443
2022-08-01 | 2013 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 13/14/15/16 MILCON projects | 97290000 | 96885659 | 96885659
2022-08-01 | 2014 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 14/15/16/17 MILCON projects | 75905000 | 74563100 | 74563100
2022-08-01 | 2015 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42387000 | 38305666 | 38305666
2022-08-01 | 2016 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42183000 | 38574364 | 38574364
2022-08-01 | 2017 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 23585000 | 18945414 | 18945414
2022-08-01 | 2009 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5000000 | 4000000 | 4000000
2022-08-01 | 2013 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3771000 | 3771000 | 3771000
2022-08-01 | 2014 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5409000 | 5409000 | 5409000
2022-08-01 | 2015 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 6846000 | 6846000 | 6846000
2022-08-01 | 2017 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3000000 | 2999834 | 2999834
2022-07-31 | 2017 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY18-19 MILCON Projects | 15000000 | 14996448 | 14882427
2022-07-31 | 2019 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY20-21 MILCON Projects | 6184000 | 5842214 | 5842214
2022-07-31 | 2020 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY21-22 MILCON Projects | 35472000 | 18454123 | 14009617
2022-07-31 | 2022 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY23-24 MILCON Projects | 19000000 | 2982554 | 0
2022-07-31 | 2018 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY18/19 | 344000 | 334742 | 258615
2022-07-31 | 2019 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY19/20 | 10000000 | 3410197 | 0
2022-07-31 | 2020 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY19/20 | 10000000 | 0 | 0
2022-07-31 | 2021 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY21/22 | 4922000 | 0 | 0
2022-07-31 | 2022 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY22/23 | 4435000 | 0 | 0
2022-07-31 | 2018 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 1, Incr. 1); Small Business Project for IPO temporary facility | 200000000 | 200000000 | 198669944
2022-07-31 | 2019 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 1, Incr. 2 & Ph. 2, Incr. 1) | 291000000 | 291000000 | 136958805
2022-07-31 | 2020 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 2, Incr. 2) | 218800000 | 218800000 | 104294515
2022-07-31 | 2021 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 2, Incr. 3) | 119000000 | 99000000 | 472
2022-08-15 | 2021 | National Geospatial-Intelligence Agency | Unspecified Minor Military Construction | Renovation Project - NGA Arnold Rear Access Control Point | 4950000 | 4950000 | 941753
2022-07-01 | 2012 | National Security Agency | Construction - Major Military Construction | Mountainview, Whitelaw Wedge, HPCC2, ICECUBE, ECB1, HPCC1, MHS Generator Plant | 333439089 | 331999386 | 331999386
2022-07-01 | 2013 | National Security Agency | Construction - Major Military Construction | MOD II, VCP1, Mountainview, HPCC2, ICECUBE, ECB1, HPCC1 | 510067383 | 506627864 | 506524892
2022-07-01 | 2014 | National Security Agency | Construction - Major Military Construction | HPCC2, ECB1 | 511998526 | 511997906 | 511349960
2022-07-01 | 2015 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - North, VCP1, NSAW Feeders - Central, ECB1, Access Control Facility | 99728000 | 97083366 | 96812325
2022-07-01 | 2016 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - Central, ECB2 | 67764547 | 67429084 | 67399306
2022-07-01 | 2020 | National Security Agency | Construction - Major Military Construction | ECB3, Mission Support Compound | 478000000 | 422255929 | 344438962
2022-07-01 | 2021 | National Security Agency | Construction - Major Military Construction | ECB3, Mission Support Compound | 250336721 | 241089739 | 246869
2022-07-01 | 2017 | National Security Agency | Construction - Major Military Construction | Feeders Ph. 3, ECB2, Access Control Facility | 247239714 | 246939479 | 218595356
2022-07-01 | 2018 | National Security Agency | Construction - Major Military Construction | ECB2, EE Infra Construction | 318424461 | 317616473 | 317472184
2022-07-01 | 2019 | National Security Agency | Construction - Major Military Construction | ECB2, ECB3 | 407000000 | 405347926 | 315189764
2022-07-01 | 2022 | National Security Agency | Construction - Major Military Construction | ECB3, MORC | 244100000 | 6602074 | 173368537
2022-07-01 | 2020 | National Security Agency | Planning and Design - Military Construction | General P&D | 14000000 | 13872137 | 12527680
2022-07-01 | 2018 | National Security Agency | Planning and Design - Military Construction | General P&D | 20000000 | 19900000 | 15309838
2022-07-01 | 2022 | National Security Agency | Planning and Design - Military Construction | General P&D | 83840000 | 42768 | 61907231
2022-07-01 | 2021 | National Security Agency | Planning and Design - Military Construction | General P&D | 10303000 | 3002410 | 1747328
2022-07-01 | 2017 | National Security Agency | Planning and Design - Military Construction | General P&D | 15442000 | 15438485 | 14243666
2022-07-01 | 2012 | National Security Agency | Planning and Design - Military Construction | General P&D | 23800910 | 23297538 | 23297538
2022-07-01 | 2013 | National Security Agency | Planning and Design - Military Construction | General P&D | 3823616 | 3255628 | 3255628
2022-07-01 | 2014 | National Security Agency | Planning and Design - Military Construction | General P&D | 13161473 | 12666068 | 12159345
2022-07-01 | 2015 | National Security Agency | Planning and Design - Military Construction | General P&D | 599000 | 591520 | 591520
2022-07-01 | 2016 | National Security Agency | Planning and Design - Military Construction | General P&D | 1078000 | 1077928 | 1077928
2022-07-01 | 2013 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3530000 | 3353911 | 3353911
2022-07-01 | 2014 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 1500000 | 1493362 | 1493362
2022-07-01 | 2015 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 4229000 | 3873686 | 3873686
2022-07-01 | 2017 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 26085 | 26085 | 26085
2022-07-01 | 2021 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 0 | 0 | 0
2022-07-01 | 2022 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 12000000 | 0 | 0
2022-07-01 | 2018 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 2254000 | 2202264 | 2202264
2022-07-01 | 2020 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3228000 | 0 | 0
2022-08-15 | 2018 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 36251000 | 35345000 | 8739000
2022-08-15 | 2019 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 16638000 | 5870000 | 343000
2022-08-15 | 2020 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 41798000 | 24771000 | 2711000
2022-08-15 | 2021 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 37043000 | 30482000 | 4574000
2022-08-15 | 2022 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 84884000 | 0 | 0
2022-08-15 | 2018 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 276981000 | 236683000 | 228164000
2022-08-15 | 2019 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 234359000 | 200226000 | 187120000
2022-08-15 | 2020 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 283977000 | 214890000 | 180365000
2022-08-15 | 2021 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 279500000 | 215584000 | 174296000
2022-08-15 | 2022 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed designs | 679652000 | 205314000 | 113391000
2022-08-15 | 2018 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 4126000 | 738000 | 504000
2022-08-15 | 2019 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine CorpsFamily Housing Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 4502000 | 383000 | 324000
2022-08-15 | 2020 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 5863000 | 1681000 | 883000
2022-08-15 | 2021 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 5854000 | 911000 | 393000
2022-08-15 | 2022 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed designs | 5732000 | 689000 | 283000
2022-08-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 33842000 | 31744000 | 27723000
2022-08-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 28579000 | 26136000 | 15223000
2022-08-15 | 2020 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 81237000 | 62370000 | 20346000
2022-08-15 | 2021 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 38983000 | 24079000 | 3972000
2022-08-15 | 2022 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 131435000 | 9094000 | 67000
2022-08-15 | 2018 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 24430000 | 21907000 | 18010000
2022-08-15 | 2019 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 4695000 | 4360000 | 3522000
2022-08-15 | 2020 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 4780000 | 1624000 | 180000
2022-08-15 | 2021 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 3485000 | 363000 | 0
2022-08-15 | 2022 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed designs | 6005000 | 0 | 0
2022-08-15 | 2018 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 11504000 | 11389000 | 6412000
2022-08-15 | 2019 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 3000000 | 2612000 | 845000
2022-08-15 | 2020 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 24915000 | 4616000 | 3473000
2022-08-15 | 2021 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 3000000 | 0 | 0
2022-08-15 | 2022 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 2359000 | 0 | 0
2022-08-08 | 2018 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 1942000 | 1942000 | 1760079
2022-08-08 | 2019 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 2036000 | 2036000 | 1440081
2022-08-08 | 2020 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4890000 | 2316530 | 191047
2022-08-08 | 2021 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 0 | 0 | 0
2022-08-08 | 2022 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 5275000 | 0 | 0