## PROJECTS
Data as of Date | Fiscal Year | Component | Construction Project Type | State | Country | Project Number | Project Title | Parent Project Number [Initial Appropriation] | Solicitation Date | Award Date | Prime Contract Recipient (Company Name) | Prime Contract Number | Original Contract Amount ($000) | Current Contract Obligation ($000) | Start Date | Placed-In-Service Date | Original Completion Date | Current Completion Date | Percent Complete | Diverted Funds Amount ($000) | Diverted Funds Recipient Project | Remarks
2014-12-31 | 2006 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR064009 | Improve Family Housing, Ph C |  | 2007-08-01 | 2007-12-06 | Bilfinger Berger | C 04-1006BB | 1801.8135 | 1893.4955 | 2007-12-17 |  | 2008-07-13 | 2013-02-22 | 99%
2014-12-31 | [8 empty] | 2007-08-01 | 2007-12-06 | OBG | C 04-1006OBG | 1118.3451 | 1171.5011 | 2007-12-17 |  | 2007-12-06 | 2013-02-22
2014-12-31 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALDA053001B | Multi-Aircraft Maintenance Hanger |  | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 15238.069 | 16847.5048 | 2011-03-01 |  | 2011-10-11 | 2015-07-31 | 99%
2014-12-31 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALUA073008A | Facility Replacements |  | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244.838 | 28675.3487 | 2011-03-01 |  | 2011-10-11 | 2015-01-15 | 99%
2014-12-31 | 2008 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR084014 | Improve Family Housing, Ph E |  | 2012-08-21 | 2013-05-17 | MICKAN | C07-1003 | 4638.8202 | 5011.6997 | 2013-07-08 |  | 2014-05-02 | 2015-03-31 | 99%
2014-12-31 | 2008 | Air Force Active | Military Family Housing Improvement |  | TURKEY | LJYC084001 | Improve Family Housing 515 Units |  | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970.0225 | 42315.6545 | 2012-03-08 |  | 2012-08-15 | 2015-07-19 | 37%
2014-12-31 | 2009 | Air Force Active | Unspecified Minor Military Construction |  | TURKEY | AKNR041053 | CNS Replace Asf Admin Bldg 2621 |  | 2011-02-22 | 2011-09-23 | MATOC Contractor | W912GB09D00690007 | 1367.06 | 1367.06 | 2012-02-15 |  | 2012-09-17 | 2015-02-01 | 13%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 28616.5445 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT033003 | Consol Communications Facility |  | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248.94 | 11773.483 | 2011-01-03 | 2014-09-12 | 2013-09-20 | 2015-09-01 | 95%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD063003 | Ground Control Tower |  | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | N6274209D1186HC08 | 7379.329 | 7423.376 | 2013-02-20 |  | 2014-01-30 | 2015-02-20 | 85%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF063009 | Replace Munitions Storage Area |  | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464.83 | 10753.2604 | 2011-06-23 |  | 2013-03-05 | 2015-03-09 | 92%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG081001 | Land Acquisition North & South Boundaries |  | 2012-05-09 | 2012-09-12 | In-House Work Force-NWK | PN-329217-LAWAFB | 3474.5 | 3474.5 | 2012-09-12 |  | 2014-03-06 | 2015-01-21 | 90%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | MONTANA | UNITED STATES | NZAS003000A | Upgrade Weapons Storage Area |  | 2012-04-23 | 2012-11-28 | RSCI | W912DW13C0013 | 9474.72 | 9462.564 | 2013-12-09 |  | 2014-10-19 | 2015-05-15 | 69%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | XTLF033303 | Control Tower |  | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849.633 | 9518.0403 | 2010-10-05 |  | 2012-01-11 | 2015-06-04 | 89%
2014-12-31 | 2010 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility |  | 2009-11-19 | 2010-02-11 | Lyda Swinerton Builders, Inc. | W9126G10C0017 | 23483.61 | 25785.2822 | 2010-02-11 | 2012-10-31 | 2011-12-26 | 2015-09-30 | 99%
2014-12-31 | [8 empty] | 2010-05-14 | 2010-06-11 | Federal Pogram Integrators, LLC - JSR Inc. | W9126G10C0072 | 1409.452 | 1601.6059 | 2010-06-11 |  | 2011-06-03 | 2015-09-30
2014-12-31 | [8 empty] | 2014-09-29 | 2014-09-29 | Gideon Contracting, LLC | W9126G14D00570016 | 60.931 | 60.931 | 2014-09-30 |  | 2014-09-29 | 2015-09-30
2014-12-31 | 2010 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | MUHJ053008 | West & Lasalle Gates Force Protection/Access |  | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185.824 | 8498.0821 | 2010-07-07 | 2013-07-19 | 2011-12-17 | 2015-09-03 | 99%
2014-12-31 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006A | Blatchford-Preston Complex Ph II |  | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | W912ER11C0001 | 35758.85 | 37149.4231 | 2011-01-21 |  | 2013-02-03 | 2014-12-15 | 95%
2014-12-31 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA103001 | Construct Network Control Center |  | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | W912ER12C0028 | 2579.93 | 3160.1562 | 2012-08-19 |  | 2013-09-08 | 2014-12-15 | 76%
2014-12-31 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA107000 | Coalition Compound Billeting |  | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272.835 | 44968.0368 | 2012-06-05 |  | 2014-03-17 | 2015-03-16 | 76%
2014-12-31 | 2010 | Air Force Active | Major Military Construction |  | TURKEY | LJYC003006 | Consolidated Community Center |  | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | W912GB09D00690003 | 7880.644 | 8179.6972 | 2013-01-15 |  | 2011-09-22 | 2015-01-04 | 46%
2014-12-31 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100031 | Construct Maintenance Operations Center And Command Post |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671.642 | 1986.1406 | 2011-09-19 |  | 2012-01-31 | 2015-07-19 | 93%
2014-12-31 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100120 | Construct SatCom Facility |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136.701 | 1184.0301 | 2011-09-19 |  | 2011-01-31 | 2015-07-19 | 93%
2014-12-31 | 2010 | Air Force Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | XDAT073008 | Construct Military Working Dog & Supporting Facility |  | 2011-07-25 | 2011-09-28 | IE PACIFIC INC | N62473-07-D-2008 | 1620 | 1620 | 2012-02-27 | 2013-02-21 | 2012-09-27 | 2013-02-22 | 99%
2014-12-31 | [8 empty] | 2014-07-18 | 2014-07-18 | CREW MW | FA442710D01022058 | 71.771 | 71.771 | 2014-07-18 |  | 2014-09-16 | 2013-02-22
2014-12-31 | 2010 | Air National Guard | Major Military Construction | MAINE | UNITED STATES | FKNN089019 | Replace Aircraft Maintenance Hangar and Shops |  | 2009-09-29 | 2010-05-12 | Sheridan Corp | W912JD10C0001 | 15.064 | 17.786 | 2010-11-05 | 2012-08-01 | 2012-11-24 | 2013-03-28 | 98% | 2200 | KNMD109501;
2014-12-31 | 2010 | Air National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | SPBN019136 | Replace Ops and Training /ADAL DGS |  | 2010-07-16 | 2010-09-27 | P&S Construction | W912SV10R0040 | 2.487 | 3.12 | 2010-11-01 | 2013-06-17 | 2011-10-27 | 2013-07-31 | 50%
2014-12-31 | 2010 | Air National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | JTVE099057 | Force Protection Measures - Relocate Base Entrance |  | 2012-08-15 | 2012-09-27 | Gottfried Contracting | W9127Q09D00090005 | 3.823 | 4.11 | 2012-10-10 | 2014-06-30 | 2013-06-24 | 2014-06-30 | 56%
2014-12-31 | 2010 | Air National Guard | Major Military Construction | NEBRASKA | UNITED STATES | NGCB079069 | Joint Forces Operations Center - ANG Share |  | 2009-11-13 | 2010-02-17 | Hausmann Construction, Inc. | W912430422013 | 1.306 | 1.5 | 2010-02-18 | 2012-09-17 | 2011-09-16 | 2012-09-17 | 98% |  |  | This projects uses a state contract executed through a Military Construction Cooperative Agreement (MCCA).
2014-12-31 | 2010 | Air National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | SZCQ089023 | Replace Squadron Operations Facilities |  | 2011-03-09 | 2011-09-19 | NUTMEG Companies, Inc. | W912TF11C0503 | 10.752 | 11.906 | 2011-10-24 | 2013-11-13 | 2013-02-15 | 2014-03-14 | 98%
2014-12-31 | 2010 | Air National Guard | Major Military Construction | TENNESSEE | UNITED STATES | PYKL009136 | Base Civil Engineer Maintenance and Training Facilities |  | 2010-07-14 | 2010-09-21 | Chris Wood Construction Co, Inc. | W912L710C0017 | 6.069 | 7.366 | 2010-10-19 | 2012-10-31 | 2012-10-18 | 2014-06-30 | 98%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | XDQU109096 | CRTC Squadron Operation Addition |  | 2012-11-13 | 2012-12-27 | Holland and Holland, Inc. | W912JM10D00010005 | 1.209 | 1.363 | 2013-01-17 | 2014-01-31 | 2014-01-17 | 2014-07-31 | 98%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | PJMS119034 | A10 Flight Simulator Facility |  | 2012-11-01 | 2013-01-08 | SAF, Inc. | W912K612R2016 | 1.818 | 1.994 | 2013-01-24 | 2014-06-04 | 2014-03-26 | 2014-06-30 | 94%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | TWLR099087 | C-130 Parking Apron |  | 2013-04-08 | 2013-11-01 | TRAC Builders | W912LD11D00250004 | 1.6 | 1.688 | 2013-12-12 | 2014-09-11 | 2013-12-12 | 2014-09-11 | 42%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | DDPM109901 | Add to Civil Engineering Facility |  | 2012-08-19 | 2012-11-21 | Triune-Beck JV | W912L111d00120200 | 1.479 | 1.544 | 2013-02-12 | 2014-06-13 | 2014-06-03 | 2014-06-13 | 90%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | DDPM119026 | Multi Use Training Facility |  | 2012-08-19 | 2012-11-21 | Tribune-Beck JV | W912L111d00120043 | 1.697 | 1.785 | 2013-02-12 | 2014-06-13 | 2013-11-30 | 2014-06-13 | 90%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | FPBD109001 | Add to Vehicle Maintenance Facility |  | 2013-06-05 | 2013-12-26 | Mirador Enterprise, Inc | W912L111D00090008 | 1.4 | 1.45 | 2014-01-06 |  | 2015-01-06 | 2015-01-25 | 22%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | LYBH079028 | BCE Pavements and Grounds Facility |  | 2013-02-19 | 2013-06-14 | Wycliffe Enterprises, Inc | W912L812D00080002 | 0.899 | 0.93 | 2013-07-09 | 2014-05-30 | 2014-04-05 | 2014-05-30 | 43%
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | LYBH119145 | Convert Hangar 107 for Aeromedical Relocation |  | 2013-07-02 | 2013-09-03 | Wycliffe Inc | W912L812D00080003 | 1.743 | 1.826 | 2013-09-16 | 2014-07-31 | 2014-10-03 | 2014-08-15 | 46%
2014-12-31 | 2011 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083008 | Repair Central Heat And Power Plant Boiler |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 30243.0655 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
2014-12-31 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV063501 | AMARG Hangar |  | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282.136 | 23098.357 | 2011-09-12 | 2014-08-22 | 2013-07-17 | 2015-01-30 | 95%
2014-12-31 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV113002 | HC-130J Aerial Cargo Facility |  | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223 | 7526.036 | 2011-11-09 | 2014-08-12 | 2013-03-14 | 2015-01-23 | 96% | 2000 | YWHG111005;
2014-12-31 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093000 | F-35 Academic Training Center |  | 2012-04-18 | 2012-08-30 | Archer Western Contractors | W912PL12C0017 | 43347.122 | 46730.2939 | 2012-11-05 |  | 2014-01-31 | 2014-12-31 | 99% | 575 | PRQE145121;
2014-12-31 | [8 empty] | 2012-04-18 | 2014-09-27 | KWR Construction, Inc | W912PL14D00300002 | 587.608 | 587.608 |  |  | 2014-12-26 | 2014-12-31
2014-12-31 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093001 | F-35 Squadron Ops Facility |  | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | W912PL12C0027 | 9108.814 | 9246.9817 | 2012-10-09 | 2014-01-06 | 2013-09-10 | 2015-01-30 | 99%
2014-12-31 | 2011 | Air Force Active | Major Military Construction | COLORADO | UNITED STATES | XQPZ084017 | Const Center For Character & Leadership Development |  | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995.5 | 25002.256 | 2013-01-15 |  | 2014-06-12 | 2015-04-30 | 65%
2014-12-31 | 2011 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | SXHT053001 | Air Force Technical Applications Center |  | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231.0449 | 146030.7225 | 2011-07-06 | 2014-03-03 | 2015-12-02 | 2015-12-02 | 98%
2014-12-31 | [8 empty] | 2013-09-27 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99.768 | 99.768 | 2014-02-13 |  | 2014-08-02 | 2015-12-02
2014-12-31 | 2011 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB025502 | Weapons Load Crew Training Facility |  | 2010-10-22 | 2011-08-03 | Pacific - Tech - Sauer JV | N6945011C1754 | 14996 | 16332.5158 | 2011-08-03 | 2014-08-28 | 2013-01-24 | 2015-01-30 | 99%
2014-12-31 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R3 | Recruit Dormitories Phase 3 |  | 2010-12-06 | 2011-09-20 | Satterfield & Pontikes Const Inc. | W9126G11C0024 | 45885.001 | 46354.6403 | 2011-09-20 |  | 2013-10-31 | 2015-01-15 | 98% | 4894 | KRSM103011;
2014-12-31 | [8 empty] | 2011-09-02 | 2011-11-08 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 95.464 | 95.464 | 2011-11-08 |  | 2011-12-08 | 2015-01-15
2014-12-31 | [8 empty] | 2012-05-09 | 2012-05-29 | Raba-Kistner Consultants | PNASA1205700 | 1.8889 | 1.8889 | 2012-05-29 |  | 2012-06-09 | 2015-01-15
2014-12-31 | [8 empty] | 2012-05-09 | 2012-08-09 | Federal Pogram Integrators, LLC - JSR Inc. | W912BV11C0038 | 6886.921 | 7267.8431 | 2012-08-09 |  | 2014-04-04 | 2015-01-15
2014-12-31 | [8 empty] | 2012-09-06 | 2012-10-19 | Federal Program Integrators, LLC with JSR Inc. | W9126G11C0009 | 175.3584 | 175.3584 | 2012-10-19 |  | 2013-06-01 | 2015-01-15
2014-12-31 | [8 empty] | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06 | 2015-01-15
2014-12-31 | [8 empty] | 2012-02-15 | 2014-06-25 | American Eagle Protective Services Corp. | W9126G12C0017P0002 | 97.8954 | 97.8954 | 2014-06-25 |  | 2015-01-31 | 2015-01-15
2014-12-31 | [8 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00190007 | 1792.428 | 1792.428 | 2014-10-10 |  | 2015-09-05 | 2015-01-15
2014-12-31 | [8 empty] | 2010-12-06 | 2014-11-10 | AE Merrick & Company-Tittle 2 Svs $59,036x3 | W9126G08D00060053 | 177.1085 | 177.1085 |  |  | 2014-11-10 | 2015-01-15
2014-12-31 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 |  | 2011-02-25 | 2011-06-30 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 25985.138 | 27504.8574 | 2011-09-05 |  | 2013-04-20 | 2015-01-15 | 97%
2014-12-31 | [8 empty] | 2011-03-07 | 2011-07-08 | LB-KBR General Contract | 1234567890 | 25985.138 | 25985.138 |  |  | 2013-06-27 | 2015-01-15
2014-12-31 | [8 empty] | 2011-03-07 | 2012-10-31 | Merrick & Company (Tittle II Services) $59,036.40 | W9126G08D00060054 | 0 | 0 |  |  | 2012-10-31 | 2015-01-15
2014-12-31 | [8 empty] | 2012-12-12 | 2013-06-03 | Federal Pogram Integrators, LLC - JSR Inc. | W9126G13C0098 | 334.244 | 152.927 | 2013-06-03 |  | 2014-01-18 | 2015-01-15
2014-12-31 | [8 empty] | 2012-02-15 | 2014-01-16 | American Eagle Protective Services Corporation | W9126G12C00170001 | 97.8954 | 202.0082 | 2014-01-16 |  | 2015-01-31 | 2015-01-15
2014-12-31 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS093737V | BMT Visitors Reception Center |  | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | F48903-06-R-9991-R | 21500.479 | 21500.479 |  |  | 2013-09-22 | 2015-06-28 | 97%
2014-12-31 | [8 empty] | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | FA890306D85110085 | 21500.479 | 21664.63 | 2012-09-19 |  | 2013-09-22 | 2015-06-28
2014-12-31 | [8 empty] | 2011-05-09 | 2014-05-01 | Merrick's & Company-Redesign Parking $31,364.14+$19,435.86 | F48 | 50.8 | 50.8 |  |  | 2014-05-31 | 2015-06-28
2014-12-31 | [8 empty] | 2014-08-14 | 2014-11-10 | Red Cedar Enterprises, Inc. | W9126G14D00190007 | 498.711 | 498.711 | 2014-12-10 |  | 2015-02-10 | 2015-06-28
2014-12-31 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR083001 | Deicing Fluid Storage & Dispensing Facility |  | 2012-05-10 | 2011-09-02 | LBB | W912GB10C0001 | 2671 | 2783.6637 | 2012-11-13 |  | 2012-12-25 | 2015-08-31 | 96% | 155 | KRSM103011; | Removed for contract correction
2014-12-31 | [8 empty] | 2012-05-10 | 2012-09-26 | Peter Gross GmbH | W912GB-10-C-0001A | -530.298 | -530.298 | 2012-11-13 |  | 2013-04-14 | 2015-08-31
2014-12-31 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR123063 | C-130J Flight Simulator Facility |  | 2013-08-12 | 2011-09-02 | LBB (EBC AWD) | W912GB-10-C-002EB | 7112.8996 | 7280.7879 | 2014-01-06 |  | 2011-09-02 | 2015-01-29 | 94% |  |  | Removed for contract correction
2014-12-31 | [8 empty] | 2013-08-12 | 2013-11-13 | OBG Hochbau GmbH & Co. KG | W912GB10C0002 | -949.3042 | -949.3042 | 2014-01-06 |  | 2014-10-23 | 2015-01-29
2014-12-31 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFU083507R2 | Dormitory (128 Rm) |  | 2013-08-30 | 2011-09-16 | LBB (EBC AWD) | W | 17945 | 17945 | 2014-06-16 |  | 2013-09-05 | 2015-11-12 | 11% |  |  | Removed for contract correction
2014-12-31 | [8 empty] | 2013-08-30 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | -1693.1044 | -1693.1044 | 2014-06-16 |  | 2015-05-29 | 2015-11-12
2014-12-31 | 2011 | Air Force Active | Major Military Construction |  | ITALY | ASHE083011 | Air Support Operations Squadron (ASOS) Facility |  | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N33191-07-D-0211 | 7174.1698 | 7895.7036 | 2011-12-16 |  | 2013-06-20 | 2015-07-31 | 80% | 1453 | KRSM103011;
2014-12-31 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006B | Blatchford-Preston Complex, Phase III |  | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177.236 | 34649.116 | 2012-09-27 |  | 2014-05-15 | 2015-09-30 | 39%
2014-12-31 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility |  | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | W912ER11D00010007 | 40848 | 40848 | 2013-08-07 |  | 2015-08-30 | 2015-09-16 | 92%
2014-12-31 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA113001 | Theater Communications Facility |  | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912.5671 | 10408.1954 | 2012-06-01 |  | 2014-04-02 | 2015-09-30 | 57%
2014-12-31 | 2011 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ114127 | Improve Family Housing, Ph 11 |  | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621.7601 | 65174.5107 | 2012-10-24 |  | 2015-08-27 | 2015-11-08 | 77%
2014-12-31 | [8 empty] | 2011-05-09 | 2012-03-19 | OTIE Milwauke, WI; *Title 2 Contract support* | FA890308D878200014 | 1896.559 | 1896.559 |  |  | 2012-03-19 | 2015-11-08
2014-12-31 | [8 empty] | 2011-05-09 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan) *ArchTestDigs* | FA5270-12-P-0058 | 50.1855 | 50.1855 | 2012-10-24 |  | 2012-07-01 | 2015-11-08
2014-12-31 | [8 empty] | 2011-05-09 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT* | FA5270-12-P-0080 | 72.2669 | 72.2669 | 2012-10-24 |  | 2012-07-31 | 2015-11-08
2014-12-31 | [8 empty] | 2011-05-09 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | FA5270-12-FA-045 | 319.4136 | 319.4136 | 2012-10-24 |  | 2012-09-12 | 2015-11-08
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR106261 | PL-1 Security Measures For Communications Compound |  | 2013-09-17 | 2013-11-13 | Mikan | C11-4014 | 1840.2888 | 1840.2888 | 2014-01-22 |  | 2014-08-10 | 2015-01-30 | 21%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA110032 | Fuel Truck Parking |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730.623 | 1730.623 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113002 | Fuels Laboratory |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557.438 | 1557.438 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113005 | C-17 Spare Parts Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572.399 | 1572.399 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113006 | High Mast Lighting |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573.056 | 1573.056 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113009 | Entry Control Point |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615.612 | 615.612 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113010 | Cryogenics Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216.4 | 1216.4 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113012 | ELRS Storage Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615.533 | 1615.533 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120037 | Clinic |  | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhab,i UAE) | W912BU13C0060 | 1514.583 | 1514.583 | 2014-09-29 |  | 2015-01-20 | 2015-06-02 | 5%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120057 | Fire Protection Water Storage |  | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120.38 | 1120.38 | 2014-09-15 |  | 2014-11-24 | 2015-03-25 | 25%
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF124001 | EOD Facility |  | 2013-07-18 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1044.893 | 1044.893 | 2014-08-08 |  | 2015-08-14 | 2015-12-03 | 2% |  |  | Original contract terminated for default
2014-12-31 | 2011 | Air National Guard | Major Military Construction | ARIZONA | UNITED STATES | HFHA069130 | TFI - Predator LRE Beddown |  | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | W912L213C0001 | 9.434 | 10.25 | 2013-04-08 | 2014-07-02 | 2014-06-02 | 2014-06-02 | 62%
2014-12-31 | 2011 | Air National Guard | Major Military Construction | DELAWARE | UNITED STATES | JLWS079103 | Joint Forces Operations Center - ANG Share |  | 2011-06-29 | 2011-09-16 | Vigil Contracting, Inc. | W912L511B0001 | 1.134 | 1.164 | 2011-12-12 | 2014-01-31 | 2013-06-09 | 2014-01-31 | 98%
2014-12-31 | 2011 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069209 | TFI - F-22 Hangar, Squadron Operations and AMU |  | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | W912J611C0002 | 37.11 | 43.051 | 2011-07-15 | 2014-01-10 | 2013-07-14 | 2014-04-08 | 98% | 2001 | KNMD069215;
2014-12-31 | 2011 | Air National Guard | Major Military Construction | NEW YORK | UNITED STATES | WHAY089079 | Base Defense Group Beddown |  | 2011-07-30 | 2011-09-23 | APS Contractors Inc | W912PQ11B00040004 | 13.401 | 14.451 | 2011-10-13 | 2014-05-15 | 2013-05-05 | 2014-06-30 | 95%
2014-12-31 | 2011 | Air National Guard | Major Military Construction | TENNESSEE | UNITED STATES | BKTZ069078 | TFI- Renovate Intel Squadron Facilities |  | 2013-09-20 | 2013-11-21 | Codell Construction Company | W912L710D00060037 | 6.074 | 6.592 | 2013-12-02 | 2014-09-29 | 2014-10-17 | 2014-10-17 | 0%
2014-12-31 | 2011 | Air National Guard | Major Military Construction | TEXAS | UNITED STATES | FWJH069194 | TFI - Alter UAV Maintenance Hangar (Bldg 1382) |  | 2012-01-06 | 2012-06-14 | LeeTex Construction | W912L112C0012 | 5.038 | 5.938 | 2012-07-23 | 2014-07-01 | 2013-07-23 | 2014-07-01 | 93%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083005 | Dormitory (168 RM) |  | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061.944 | 33061.944 | 2014-08-26 |  | 2016-08-02 | 2016-08-15 | 2%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) |  | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805.3 | 56108.943 | 2012-06-19 |  | 2014-06-19 | 2015-03-16 | 69% | 19165 | ALUA073006B; YWHG111005; WWYK143004A; ZHTV053302;
2014-12-31 | [8 empty] | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230.2925 | 3230.2925 | 2012-06-26 |  | 2013-09-27 | 2015-03-16
2014-12-31 | [8 empty] | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978.8077 | 4978.8077 | 2012-06-26 |  | 2013-08-28 | 2015-03-16
2014-12-31 | [8 empty] | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874.106 | 2191.91 | 2012-07-02 |  | 2012-11-20 | 2015-03-16
2014-12-31 | [8 empty] | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799.2288 | 1799.2288 | 2012-07-27 |  | 2013-01-23 | 2015-03-16
2014-12-31 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV103006P1 | EC-130H Simulator/Training Operations |  | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | W912PL12C0011 | 14347.6 | 14438.88 | 2013-02-10 | 2014-08-28 | 2014-03-07 | 2015-01-23 | 99% | 4333 | WWYK143004A; LKTC093101;
2014-12-31 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV123002 | HC-130J Joint Use Fuel Cell |  | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | W912PL12C0018 | 12361 | 12415.286 | 2013-01-10 |  | 2014-03-14 | 2015-01-30 | 86%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120010 | F-35 ADAL Aircraft Maintenance Unit |  | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | W912PL12C0027 | 4781.113 | 4980.026 | 2012-10-09 | 2014-01-06 | 2013-09-10 | 2014-12-31 | 99%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120011 | F-35 Squad Ops/AMU 2 |  | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | W912PL13C0006 | 12358.5 | 12799.937 | 2013-10-08 |  | 2014-08-29 | 2014-12-16 | 94%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY983202 | Air Freight Terminal Complex |  | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | N6274210D1308JQ01 | 30047.253 | 32363.6898 | 2012-07-18 |  | 2014-05-14 | 2015-03-02 | 87%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility |  | 2011-12-30 | 2012-04-28 | Pacific West Builders | N4019210D28100003 | 9490.73 | 9433.61 | 2012-05-14 | 2014-08-15 | 2013-10-07 | 2015-01-31 | 99% | 2100 | ZHTV053302;
2014-12-31 | 2012 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB105002 | Mission Support Group Complex |  | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998 | 18551.6272 | 2012-03-26 |  | 2013-09-17 | 2015-01-16 | 99%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG071005 | WSA Security Control Facility |  | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172.6 | 4300.1692 | 2012-03-16 | 2014-08-15 | 2013-08-20 | 2015-08-15 | 98%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | NEBRASKA | UNITED STATES | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 102754.426 | 102442.3087 | 2012-10-15 |  | 2016-08-15 | 2016-09-12 | 31%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103003 | Communications Network Control Center |  | 2011-11-17 | 2012-04-24 | A4 Construction | W912PL12C0008 | 9326.701 | 9525.511 | 2012-12-01 | 2014-05-01 | 2014-04-24 | 2015-04-30 | 95% | 800 | ZHTV053302;
2014-12-31 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV093108 | AFNWC Sustainment Center |  | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | W912PP12C0016 | 21110 | 21507.2863 | 2012-07-09 |  | 2014-04-03 | 2014-12-15 | 98% | 1100 | ZHTV053302;
2014-12-31 | 2012 | Air Force Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH083003 | C-130 Flight Simulator |  | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | W912HN10D00630003 | 4630 | 4712.131 | 2013-04-30 |  | 2013-12-12 | 2015-01-08 | 93%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock |  | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | W9128F12C0013 | 32123.257 | 33407.635 | 2012-05-22 |  | 2014-09-06 | 2015-01-15 | 97%
2014-12-31 | 2012 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R4 | BMT Recruit Dormitory, Phase IV |  | 2011-12-16 | 2012-10-31 | AE-Merrick&Company ($400,140 shown under DDC) | W9126G08D00060055 | 0 | 0 |  |  | 2012-10-31 | 2015-04-11 | 78%
2014-12-31 | [8 empty] | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06 | 2015-04-11
2014-12-31 | [8 empty] | 2011-12-16 | 2013-07-17 | Spawglass Contractors Inc. | W9126G12C0023 | 50528.593 | 52100.097 | 2013-07-17 |  | 2014-11-26 | 2015-04-11
2014-12-31 | [8 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00J190007 | 6732.163 | 7301.64 | 2014-10-10 |  | 2016-01-03 | 2015-04-11
2014-12-31 | 2012 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | WACC120007 | AIT Barracks Complex, Ph 2 |  | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | W9123608D00140003 | 33915.149 | 34107.6364 | 2012-10-15 |  | 2014-09-19 | 2015-01-14 | 98% | 10112 | WWYK143004A; LKTC093101; ZHTV053302;
2014-12-31 | 2012 | Air Force Active | Major Military Construction | WASHINGTON | UNITED STATES | GJKZ860009 | Wing Headquarters |  | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | W912DW12C0030 | 11957.25 | 12236.213 | 2013-03-18 | 2014-03-07 | 2013-12-26 | 2014-11-10 | 96%
2014-12-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17001 | Aircraft Apron/Taxiway And Maintenance Shelters |  | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | N3319109D01200011 | 6740.135 | 6640.535 | 2012-05-15 | 2014-02-02 | 2013-01-27 | 2015-01-30 | 99%
2014-12-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17002 | Combat Aircraft Loading Area |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421 | 43728.4594 | 2012-12-24 |  | 2013-12-26 | 2015-03-12 | 49%
2014-12-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17003 | Parallel Taxiway Extension |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521.53 | 10521.53 | 2012-12-24 |  | 2014-05-03 | 2015-04-23 | 31%
2014-12-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17004 | Expeditionary Lodging |  | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587.915 | 27299.359 | 2013-03-15 |  | 2014-03-20 | 2015-01-09 | 86%
2014-12-31 | 2012 | Air Force Active | Major Military Construction |  | GERMANY | TYFR063017 | Dormitory (192 RM) |  | 2012-03-29 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541.6935 | 29541.6935 | 2014-07-01 |  | 2013-11-15 | 2015-09-15 | 1% | 1624 | WWYK143004A; ZHTV053302;
2014-12-31 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 |  | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706.6686 | 17706.6686 | 2013-06-04 |  | 2015-10-13 | 2015-11-20 | 68%
2014-12-31 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA124002 | Improve MFH Infrastructure, Phase 1 |  | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | W912HV12C0003 | 19550.171 | 20009.1332 | 2012-07-31 |  | 2014-10-21 | 2015-03-31 | 98%
2014-12-31 | 2012 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | AGGN123002P | Communications Network Control Center Consolidation |  | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619.1715 | 1619.1715 | 2014-03-10 |  | 2014-10-03 | 2015-02-26 | 60%
2014-12-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113026 | C-130 Aircraft Maintenance Unit |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511.518 | 1511.518 | 2013-09-12 |  | 2014-11-08 | 2016-02-29 | 23%
2014-12-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113027 | Air Defense Artillery Maintenance Facility |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265.194 | 1265.194 | 2013-08-28 |  | 2014-08-19 | 2015-06-19 | 21%
2014-12-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113032 | Precision Measurement Equipment Laboratory |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403.744 | 1409.0421 | 2013-08-28 |  | 2014-12-02 | 2015-07-24 | 21%
2014-12-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113034 | AFOSI Regional And Local Facility |  | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214.606 | 1214.606 | 2013-08-28 |  | 2015-01-14 | 2015-02-19 | 21%
2014-12-31 | 2012 | Air Force Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | PDPG020143 | Construct New Airfield Control Tower, B1295 & Base Op'S B395 |  | 2012-03-16 | 2012-07-26 | Flintco, LLC. | W912QR12C0048 | 16915 | 17335.163 | 2012-08-22 | 2014-06-23 | 2014-12-16 | 2015-01-22 | 98%
2014-12-31 | 2012 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ120572 | Vehicle Maintenance Facility |  | 2013-01-04 | 2014-08-22 | Oddo Construction Services | FA667014C0002 | 2087.131 | 2087.131 | 2014-09-22 |  | 2016-02-13 | 2015-07-31 | 2%
2014-12-31 | 2012 | Air Force Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX079003 | Red Horse Readiness And Training Facility |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149 | 9004.77 | 2012-07-13 |  | 2013-07-13 | 2014-12-15 | 92%
2014-12-31 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | UTAH | UNITED STATES | KRSM099001 | Fire Station #4 Annex |  | 2013-06-11 | 2013-09-25 | Grand Enterprises, LLC | FA820112D00250004 | 1322.061 | 1392.139 | 2013-10-11 | 2014-08-22 | 2014-05-28 | 2014-11-01 | 98%
2014-12-31 | 2012 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY029154 | Wing Operations and Training Facility |  | 2012-07-27 | 2012-09-26 | SM Construction | W912LA12C0008 | 4.96 | 5.48 | 2012-12-03 | 2014-06-16 | 2013-12-03 | 2014-06-13 | 95%
2014-12-31 | 2012 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | QMSN019029 | Replace Pararescue Training Facility |  | 2012-08-05 | 2012-09-26 | Flintco Construction | W912LA12C7025 | 25.161 | 27.749 | 2013-01-10 | 2014-08-15 | 2014-04-10 | 2014-08-14 | 74%
2014-12-31 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069212 | TFI - F-22 Flight Simulator Facility |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C0003 | 18.842 | 21.659 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 81%
2014-12-31 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069213 | TFI - F-22 Weapons Load Crew Training Facility |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | W912J612C0003 | 6.473 | 7.944 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 75%
2014-12-31 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron |  | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | W9128A12C0007 | 9.682 | 10.875 | 2012-08-08 | 2013-11-18 | 2013-08-08 | 2015-03-29 | 70%
2014-12-31 | [8 empty] | 2013-03-04 | 2013-09-12 | Nan, Inc | W912J613C0006 | 2 | 2 | 2013-09-30 |  | 2015-03-29 | 2015-03-29
2014-12-31 | 2012 | Air National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities |  | 2013-05-08 | 2013-08-29 | Maron Construction Co. | W912SV13C0003 | 7.919 | 8.226 | 2013-09-24 |  | 2013-09-28 | 2015-02-11 | 26%
2014-12-31 | 2012 | Air National Guard | Unspecified Minor Military Construction | ALASKA | UNITED STATES | FXSB121354 | Construct Aerospace Support Equipment Storage Facility |  | 2013-07-31 | 2013-09-27 | H. Watt & Scott | W91ZRU10D00060011 | 1.088 | 1.088 | 2013-10-02 | 2014-08-24 | 2014-03-01 | 2014-08-24 | 20%
2014-12-31 | 2012 | Air National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | AXQD119004 | Add to and Alter Survival Equipment Shop |  | 2013-04-10 | 2013-07-12 | Cornerstone Construction Svs | W912SV10D00080004 | 1.19 | 1.241 | 2013-07-16 | 2014-05-23 | 2014-02-07 | 2014-05-30 | 95%
2014-12-31 | 2012 | Air National Guard | Unspecified Minor Military Construction | OHIO | UNITED STATES | WAAR129078 | Relocate Main Gate |  | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | W9136413D00050002 | 1.713 | 1.884 | 2013-08-27 | 2014-05-22 | 2014-03-12 | 2014-05-22 | 84%
2014-12-31 | 2012 | Air National Guard | Unspecified Minor Military Construction | OREGON | UNITED STATES | KJAQ119031 | Addition Squadron Operations Facility |  | 2013-10-08 | 2014-01-29 | Anthem Builders, Inc | W912JV14C0002 | 1.678 | 1.76 | 2014-03-12 |  | 2014-11-10 | 2014-12-19 | 12%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK103006 | C-130J Fuel Systems Maintenance Hangar |  | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869 | 20869 | 2013-07-23 |  | 2015-06-25 | 2015-10-13 | 65%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK113005 | C-130J Flight Simulator Addition |  | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218.503 | 4218.503 | 2014-10-24 |  | 2015-09-24 | 2015-10-21 | 1%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY133001 | Civil Engineer Administration/Operations Facility |  | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947.269 | 15947.269 | 2014-07-09 |  | 2016-03-01 | 2016-03-30 | 2%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair |  | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 13298.609 | 13356.965 | 2013-08-21 |  | 2015-05-21 | 2015-05-29 | 78%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | QSEU103008 | HC-130J Simulator Facility |  | 2012-12-07 | 2013-06-28 | IBKI, Inc. Choctaw, MS | W912HN13C0011 | 7692.387 | 7805.965 | 2013-08-12 |  | 2014-11-20 | 2015-04-15 | 99%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | ACC123184 | Air Support Operations Center |  | 2013-03-14 | 2013-09-24 | Better Built Construction Serv | W912HN10D00530003 | 6458 | 6458 | 2013-11-07 |  | 2015-03-18 | 2015-05-01 | 17%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC133101 | RPA Mission Complex Physical Protection System |  | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643.42 | 10643.42 | 2014-08-19 |  | 2015-07-24 | 2015-09-01 | 2%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD123004 | MQ-9 Maintenance Hangar |  | 2013-03-01 | 2013-06-17 | HEW-Phelps | W912PP13C0019 | 20620 | 20726.768 | 2013-08-30 |  | 2015-03-09 | 2015-01-30 | 92%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083008 | Dormitory (96 Rm) |  | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170.185 | 17170.185 | 2014-03-15 |  | 2015-03-07 | 2015-03-25 | 18%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103012 | F-35 Adal Hangar 45W/AMU |  | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781 | 6934.456 | 2014-01-27 |  | 2015-06-13 | 2015-08-15 | 29%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103030 | F-35A Modular Storage Magazines |  | 2012-08-08 | 2013-12-17 | Zumwalt Construction, Inc. | W9123811D00260006 | 2028.458 | 2033.5187 | 2014-01-27 |  | 2015-06-10 | 2015-10-25 | 9%
2014-12-31 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM113028 | F-35 Adal Building 118 For Flight Simulator |  | 2012-08-08 | 2013-12-17 | Creative Times, Inc. (CTI) | W9123811D00240002 | 3878.926 | 3888.2676 | 2014-01-29 |  | 2015-02-15 | 2015-04-30 | 43%
2014-12-31 | 2013 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103032 | Dormitory (48 Pn) |  | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031.649 | 23031.649 | 2013-08-15 |  | 2015-05-21 | 2015-07-29 | 43%
2014-12-31 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 |  | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698.0727 | 14787.5107 | 2013-08-29 |  | 2015-10-16 | 2016-01-04 | 21%
2014-12-31 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA133001P2 | Improve Family Housing, Ph 2 |  | 2013-05-16 | 2013-09-30 | Nishimatsu Construction Co., Ltd | FZ520513C0005 | 13989.4156 | 13746.0243 | 2013-10-29 |  | 2015-05-23 | 2015-05-22 | 81%
2014-12-31 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA134001 | Improve Mfh Infrastructure, Phase 2 |  | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336.739 | 14803.5238 | 2013-10-23 |  | 2015-08-29 | 2015-08-31 | 50%
2014-12-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | FBNV133500 | T-10 Engine Test Cell (AMARG) |  | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D0110 | 1795 | 1795 | 2014-08-12 |  | 2015-05-04 | 2015-08-04 | 10%
2014-12-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | NKAK113003 | C130J Propeller Repair Training Facility |  | 2013-11-19 | 2014-02-21 | HGL Construction | FA446011D00075014 | 727 | 727 | 2014-06-20 |  | 2015-02-21 | 2015-02-20 | 1%
2014-12-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 |  | 2013-03-06 | 2013-05-23 | Southwind Construction | W912BV12D00180003 | 1525.212 | 1525.212 | 2013-06-07 |  | 2015-07-19 | 2015-08-03 | 66%
2014-12-31 | 2013 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ099095 | Flight Simulator Facility |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242.986 | 5242.986 | 2014-08-05 |  | 2015-09-18 | 2016-01-15 | 2%
2014-12-31 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | KYJM129022 | Add Simulator Bay, Building 191 |  | 2013-06-07 | 2013-09-23 | CCI | W9127810D001180020 | 1552.029 | 1591.6019 | 2013-12-16 |  | 2014-07-07 | 2015-02-12 | 82%
2014-12-31 | 2013 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | HAYW109006 | F-15 Conversion |  | 2013-08-23 | 2013-09-27 | RS Morris Construction | W912LA11D00180010 | 3.747 | 4.055 | 2013-11-01 |  | 2015-01-25 | 2015-06-23 | 0%
2014-12-31 | [8 empty] | 2013-08-23 | 2013-09-30 | RS Morris Cosntruction | W912LA11D00180011 | 2.402 | 2.575 | 2013-11-01 |  | 2015-01-25 | 2015-06-23
2014-12-31 | 2013 | Air National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV119001 | Alter Target Intelligence Facility |  | 2013-05-22 | 2013-10-10 | K.L. HOUSE CONSTRUCTION CO. | W912J314C1001 | 4.569 | 5.026 | 2014-01-27 |  | 2015-01-27 | 2015-02-23 | 13%
2014-12-31 | 2013 | Air National Guard | Major Military Construction | WYOMING | UNITED STATES | DPEZ089017 | C-130 Flight Simulator Training Facility |  | 2013-08-28 | 2013-09-27 | Faith Enterprises | W912L313D0003 | 5.062 | 5.294 | 2013-09-27 |  | 2015-03-21 | 2015-03-21 | 5%
2014-12-31 | 2013 | Air National Guard | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | FJRP079016 | BCE pavements and Grounds Facility |  | 2013-12-23 | 2014-04-07 | Showalter Construction | W9124209D0013N908 | 1.22 | 1.258 | 2014-06-01 |  | 2015-03-03 | 2015-03-28 | 1%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093007 | Construct Addition, Field Training Facility, B936 |  | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699.907 | 4699.907 | 2014-04-23 |  | 2015-06-11 | 2015-07-07 | 12%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) |  | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513.636 | 15513.636 | 2014-06-24 |  | 2016-01-11 | 2016-02-14 | 7%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699.643 | 53699.643 | 2014-08-27 |  | 2016-10-15 | 2017-02-21 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY143760 | Hardened Structures For POL Fuel Systems |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907.7 | 17907.7 | 2014-12-01 |  | 2016-03-30 | 2017-04-15 | 5%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility |  | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177.269 | 6177.269 | 2014-10-24 |  | 2016-07-20 | 2016-07-20 | 5%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  | 2013-11-18 | 2014-06-17 | SRB International LLC | N6274214C1312 | 2699 | 2699 | 2014-08-21 |  | 2015-05-08 | 2015-06-07 | 5%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar |  | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924.5 | 63924.5 | 2014-06-24 |  | 2015-12-03 | 2017-03-10 | 7% | 10500 | SGBP100904C;
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems |  | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100.5 | 8100.5 | 2014-09-02 |  | 2015-11-19 | 2015-12-19 | 25% | 2500 | SGBP100904C;
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145137 | KC-46A Alter Miscellaneous Facilities |  | 2014-03-10 | 2014-06-27 | Red Cedar Enterprises, Inc | W912DQ13D40010002 | 838.705 | 838.705 | 2014-07-12 |  | 2015-02-22 | 2015-03-11 | 85%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145138 | KC-46A Alter Aircraft Parking Apron |  | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976 | 976 | 2014-08-18 |  | 2017-02-06 | 2017-03-10 | 2% | 600 | PRQE145121;
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145142 | KC-46A 1-Bay Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200 | 25200 | 2014-09-19 |  | 2016-12-18 | 2017-03-10 | 4% | 3000 | SGBP100904C;
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959 | 53959 | 2014-06-24 |  | 2015-11-24 | 2017-03-10 | 2% | 19000 | SGBP100904C;
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) |  | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306.162 | 7306.162 | 2014-10-30 |  | 2015-09-23 | 2015-10-15 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | KENTUCKY | UNITED STATES | ACC123183 | Air Support Operations Center |  | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143.462 | 7143.462 | 2014-09-29 |  | 2016-02-13 | 2015-12-13 | 1%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 57000 | 57000 | 2014-07-07 |  | 2016-03-26 | 2017-04-13 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111010 | WSA: Construct Two New MOP Igloos |  | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817.7 | 3817.7 | 2014-08-11 |  | 2015-09-06 | 2015-11-13 | 23%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC073101 | Land Acquisition |  | 2014-07-18 | 2014-09-02 | USACE | W81EYN42417577 | 11.45 | 11.45 | 2014-09-02 |  | 2014-12-01 | 2016-03-15 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF083002 | Dormitory |  | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381 | 30381 | 2014-08-05 |  | 2016-08-22 | 2016-09-27 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103005 | F-35A ADAL AME Storage Facility |  | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D0113 | 4829.984 | 4829.984 | 2014-08-27 |  | 2016-01-15 | 2015-08-15 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103006 | F-35A Parts Store |  | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974.014 | 6974.014 | 2014-08-15 |  | 2015-12-01 | 2016-01-15 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar |  | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066 | 8066 | 2014-06-24 |  | 2015-11-12 | 2015-09-01 | 5%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF113005 | RPA Weapons School |  | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922.7 | 14922.7 | 2014-08-12 |  | 2016-05-31 | 2016-06-01 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073050 | Dormitory (144 Rm) |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19224.874 | 19224.874 | 2014-07-10 |  | 2016-07-07 | 2016-11-01 | 4%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 |  | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285.5 | 21285.5 | 2014-08-25 |  | 2016-09-30 | 2016-02-08 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092013 | B-52 Munitions Storage Igloos |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540.27 | 9540.27 | 2014-07-15 |  | 2015-12-01 | 2015-09-21 | 10%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164.308 | 1164.308 | 2014-07-30 |  | 2015-12-08 | 2015-03-12 | 29%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111.892 | 7111.892 | 2014-07-02 |  | 2015-12-08 | 2015-12-17 | 2%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645.2 | 5645.2 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 24%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143004 | KC-46A FTU Ftc Simulator Facility Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000 | 11000 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 24%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 |  | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265.367 | 3265.367 | 2014-05-15 |  | 2015-05-17 | 2015-06-09 | 41%
2014-12-31 | 2014 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103011 | F-35 ADAL Hangar 45E/AMU |  | 2013-07-22 | 2014-04-10 | CTI | W912PL14C0005 | 6587 | 8797.06 | 2014-05-20 |  | 2015-10-02 | 2015-10-15 | 29%
2014-12-31 | 2014 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817.6089 | 39817.6089 | 2014-08-19 |  | 2016-07-10 | 2016-06-17 | 2%
2014-12-31 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ144287 | Improve MFH Infrastructure, Phase 3 |  | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288.6807 | 6288.6807 | 2014-08-15 |  | 2016-01-07 | 2016-01-07 | 3%
2014-12-31 | [8 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202.136 | 4202.136 | 2014-07-23 |  | 2014-06-30 | 2016-01-07
2014-12-31 | [8 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473.4496 | 2473.4496 | 2014-08-06 |  | 2015-09-10 | 2016-01-07
2014-12-31 | [8 empty] | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302.11 | 25302.11 | 2014-10-30 |  | 2016-12-05 | 2016-12-24
2014-12-31 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility |  | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547.47 | 1547.47 | 2014-11-24 |  | 2015-07-29 | 2015-11-23 | 1%
2014-12-31 | 2014 | Air National Guard | Unspecified Minor Military Construction | SOUTH CAROLINA | UNITED STATES | PSTE129092 | Construct North Overrun |  | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W912420930003S401 | 1.702 | 1.78 | 2014-03-11 |  | 2014-12-24 | 2014-12-31 | 2%
2014-12-31 | 2008 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 50950 | Barracks Complex |  | 2009-01-30 | 2010-03-25 | Kiewit Building Group Inc. | W9128A-10-C-0005 | 44500 | 45992.851 | 2010-04-25 | 2012-11-06 | 2012-03-10 | 2012-10-14 | 98.95%
2014-12-31 | 2008 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 50950 | Barracks Complex |  |  | 2010-03-25 | Kiewit Building Group Inc. |  | 421.263 | 421.263 | 2010-04-25 | 2012-10-14 | 2012-03-10 | 2012-10-14 | 53.41%
2014-12-31 | 2008 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 54785 | Child Development Center |  | 2010-12-13 | 2011-08-04 | ASSET Group, Inc. | W9127S-11-C-6011 | 7835.188 | 7946.4612 | 2011-09-22 | 2014-12-27 | 2013-01-25 | 2015-02-12 | 92.2% | 2750 | 68772
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68786 | Brigade Complex |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 24779 | 28783.563 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68786 | Brigade Complex |  |  | 2011-03-27 | dck-ecc pacific, LLC |  | 1877 | 1894.683 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68821 | Battalion Complex |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 29140 | 33969.83 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68821 | Battalion Complex |  |  | 2011-03-27 | dck-ecc pacific, LLC |  | 1944 | 1975.872 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68822 | Battalion Complex |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 9103 | 10861.394 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68822 | Battalion Complex |  |  | 2011-03-27 | dck-ecc pacific, LLC |  | 737 | 754.683 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69308 | Infrastructure Expansion |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 58240 | 63818.854 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69308 | Infrastructure Expansion |  |  | 2011-03-27 | dck-ecc pacific, LLC |  | 2145 | 2504.842 | 2011-04-14 |  | 2014-03-13 | 2015-02-19 | 99%
2014-12-31 | 2009 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67579 | Add/Alt Army Reserve Center |  | 2009-02-19 | 2009-06-17 | E. W. Howell Company, LLC | W912QR-09-C-0040 | 15041.2 | 16141.3502 | 2009-07-20 |  | 2011-07-10 | 2015-01-30 | 99%
2014-12-31 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 72477 | USFOR-A Headquarters & Housing |  | 2011-03-27 | 2011-08-04 | Contrack International Inc. | W912ER-11-C-0049 | 47160.85 | 32307.8094 | 2011-09-08 | 2014-12-15 | 2013-12-07 | 2014-08-24 | 99%
2014-12-31 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses |  | 2013-06-20 | 2013-09-26 | Contrack International, Inc. | W912ER-13-C-0032 | 49412.74 | 54675.778 | 2013-10-24 |  | 2015-03-24 | 2015-03-24 | 18.15%
2014-12-31 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses |  | 2013-11-06 | 2014-04-02 | Contrack International, Inc. |  | 6749.291 | 6749.291 | 2014-05-07 |  | 2015-10-29 | 2015-10-29 | 7.99%
2014-12-31 | 2010 | Army Reserve | Major Military Construction | PUERTO RICO | PUERTO RICO | 69568 | Army Reserve Center/Land |  | 2011-06-15 | 2011-09-21 | RBC Construction Coporation | W912QR-11-C-0046 | 12356.39 | 12620.58 | 2011-11-15 |  | 2013-08-05 | 2014-12-31 | 98.23%
2014-12-31 | 2010 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 69471 | Army Reserve Center/Land |  | 2011-07-04 | 2012-04-01 | Blackhawk-Jamco, A SDVOB Joint Venture | W912QR-12-C-0022 | 16009 | 16319.55 | 2012-05-21 |  | 2013-09-23 | 2015-04-13 | 77.99%
2014-12-31 | 2010 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 58625 | Satellite Communications Facility |  | 2009-10-08 | 2010-02-05 | Harkins Builders, Inc. | W912DR-10-C-0068 | 11717.005 | 19327.8645 | 2010-03-06 | 2014-12-12 | 2012-08-31 | 2014-11-11 | 99%
2014-12-31 | 2010 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66726 | Ballistic Evaluation Facility, Ph 2 |  | 2012-05-10 | 2012-09-27 | APS Contracting Inc. | W912DS-12-C-0030 | 8757.272 | 8954.263 | 2012-12-04 |  | 2014-06-03 | 2015-05-14 | 63.22%
2014-12-31 | 2010 | Army Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | 69430 | Army Reserve Center/Land |  | 2011-07-27 | 2011-09-28 | Lobar Inc. | W912QR-11-C-0062 | 18272 | 18791.879 | 2012-01-18 |  | 2013-11-08 | 2015-04-06 | 82.38%
2014-12-31 | 2010 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 64209 | Access Control Point and Road Improvements |  | 2010-01-15 | 2010-07-14 | Liberty A / Vertex | W9128F-10-C-0056 | 9839.658 | 11751.452 | 2010-08-02 | 2012-10-30 | 2012-01-25 | 2014-09-29 | 98.17%
2014-12-31 | 2010 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 75110 | Tactical Equipment Maintenance Facility |  | 2011-10-03 | 2012-01-26 | Leetex Construction LLC | W912QR-12-C-0010 | 9433.577 | 10333.577 | 2012-04-04 |  | 2013-09-11 | 2015-01-15 | 95.96%
2014-12-31 | 2010 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 74885 | Fire Station |  | 2011-08-24 | 2012-07-16 | ARGO SYSTEMS, LLC | W912DR-12-C-0010 | 1636.889 | 1647.659 | 2012-08-02 | 2014-07-28 | 2014-01-25 | 2014-04-24 | 99%
2014-12-31 | 2010 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 74408 | Ft Lewis-McChord AFB Joint Access |  | 2013-02-12 | 2013-08-28 | TSS-Garco Joint Venture | W912DW-13-C-0040 | 7327 | 7645.264 | 2013-09-24 |  | 2015-01-28 | 2015-01-28 | 76.45%
2014-12-31 | 2011 | Army Active | Major Military Construction |  | AFGHANISTAN | 71604 | Eastside Utilities Infrastructure |  | 2012-05-29 | 2012-09-03 | ANHAM-ICSS Joint Venture | W912ER-11-D-0003 | 26826.989 | 24722.776 | 2012-10-17 |  | 2014-06-04 | 2015-01-31 | 76.59%
2014-12-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 60555 | Information Processing Center |  | 2012-09-30 | 2012-05-13 | Hessisches Baumanagement Wiesbaden | W912GB-08-C-0005 | 27799.1141 | 31824.6652 | 2012-06-17 |  | 2014-05-31 | 2014-12-19 | 97.11%
2014-12-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66465 | Confinement Facility |  | 2012-03-06 | 2013-03-07 | LBB Kaiserslautern | W912GB-09-C-0039 | 9459.8812 | 9968.7737 | 2013-04-28 | 2014-12-03 | 2014-12-15 | 2014-12-19 | 97.22%
2014-12-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66465 | Confinement Facility |  | 2012-11-21 | 2012-06-18 | LBB Kaiserslautern |  | 472.7664 | 470.1863 | 2013-04-28 | 2014-12-19 | 2014-12-15 | 2014-12-19 | 94.52%
2014-12-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66834 | Vehicle Maintenance Shop |  | 2010-12-01 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 15984.7877 | 17308.6172 | 2011-12-12 |  | 2013-12-18 | 2015-07-30 | 90.35%
2014-12-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68074 | Construct New ACP |  | 2013-11-15 | 2013-06-05 | Hessisches Baumanagement Wiesbaden |  | 6303.8821 | 7213.2685 | 2014-03-05 |  | 2014-12-12 | 2015-01-20 | 89.98%
2014-12-31 | 2011 | Army Active | Military Family Housing |  | GERMANY | 71422 | Family Housing Replacement Construction |  | 2014-10-14 | 2011-09-13 | LBB Niederlassung Idar-Oberstein |  | 33110.8094 | 33110.8094 |  |  | 2012-02-23 | 2017-09-28 | 4.998%
2014-12-31 | 2011 | Army Active | Major Military Construction |  | HONDURAS | 61383 | Barracks |  | 2011-05-17 | 2011-08-24 | Contracting, Consulting, Engineering, LLC | W91278-11-C-0028 | 15146.5804 | 15633.3629 | 2012-01-10 |  | 2014-01-09 | 2014-09-23 | 98.53%
2014-12-31 | 2011 | Army Active | Major Military Construction | ALABAMA | UNITED STATES | 60463 | Aviation Component Maintenance Shop |  | 2010-12-14 | 2011-05-17 | Carothers Construction, Inc | W91278-07-D-0033 | 19712.66 | 21525.314 | 2011-09-19 | 2013-07-29 | 2013-09-08 | 2015-01-05 | 99%
2014-12-31 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60285 | General Instruction Building |  | 2010-10-06 | 2011-05-17 | RQ Construction, LLC | W91238-11-C-0005 | 29886 | 32716.93 | 2011-06-06 | 2014-09-07 | 2013-05-23 | 2014-12-31 | 97.98%
2014-12-31 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility |  | 2011-01-07 | 2014-09-02 | Watts Constructors, LLC | W912PP-08-C-0019 | 38914.5 | 38914.5 | 2014-09-18 |  | 2016-06-29 | 2016-06-29 | 0.815% | 12900 | 73686
2014-12-31 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility |  |  | 2011-08-29 | Watts/Webcor A JV |  | 34801.408 | 35283.472 | 2011-09-20 |  | 2013-06-11 | 2014-06-29 | 4.326%
2014-12-31 | 2011 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 13852 | Simulations Center |  | 2011-07-14 | 2011-09-13 | Native American Services Corp. | W9128F-11-C-0061 | 27829.194 | 34671.3993 | 2011-11-03 | 2014-09-01 | 2013-04-26 | 2014-10-30 | 99%
2014-12-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 52269 | Barracks |  | 2011-04-27 | 2011-09-19 | Nan, Inc. dba Ocean House Builders | W9128A-11-C-0016 | 23984.24 | 25032.858 | 2011-10-16 | 2014-11-18 | 2014-07-15 | 2015-02-11 | 93.65%
2014-12-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 52269 | Barracks |  |  | 2011-09-19 | Nan, Inc. dba Ocean House Builders |  | 1329.054 | 16526.087 | 2011-10-16 |  | 2014-07-15 | 2015-02-11 | 94.02%
2014-12-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 56024 | Flood Mitigation |  | 2012-06-28 | 2012-09-24 | Nan, Inc | W9128A-12-C-0019 | 21105.273 | 21678.013 | 2012-10-16 |  | 2014-10-13 | 2015-06-29 | 69.86%
2014-12-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64760 | Training Aids Center |  | 2012-06-28 | 2012-09-18 | SRB International LLC | W9128A-12-C-0013 | 13310.008 | 13309.7969 | 2012-10-30 |  | 2014-08-16 | 2015-02-09 | 87.49%
2014-12-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 65650 | Command and Control Facility, Ph 1 |  | 2011-11-03 | 2012-02-28 | Niking Corporation | W9128A-12-C-0003 | 46780 | 48950.577 | 2012-04-02 |  | 2014-04-22 | 2015-06-29 | 86.89%
2014-12-31 | 2011 | Army Reserve | Major Military Construction | IOWA | UNITED STATES | 70654 | Army Reserve Center |  | 2011-11-15 | 2012-03-13 | The Vertex Companies | W912QR-12-C-0014 | 8931.622 | 8999.53 | 2012-04-08 |  | 2013-08-11 | 2015-02-15 | 95.51%
2014-12-31 | 2011 | Army Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | 74943 | Igloo Storage, Installation |  | 2012-03-12 | 2012-07-17 | Senate Builders & Construction Managers Inc. | W912DS-12-C-0017 | 1756.106 | 1851.3294 | 2012-08-09 | 2013-10-14 | 2013-07-06 | 2014-05-14 | 99%
2014-12-31 | 2011 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 59044 | Science Facility, Ph 2 |  | 2011-06-22 | 2011-09-29 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270 | 113142.487 | 2011-11-17 |  | 2015-11-14 | 2016-01-29 | 82.29%
2014-12-31 | 2011 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69599 | Army Reserve Center/Land |  | 2012-07-24 | 2012-09-24 | J. Kokolakis Contracting, Inc. | W912QR-12-C-0057 | 12353.9 | 12881.4 | 2012-10-24 |  | 2014-04-02 | 2015-01-14 | 99%
2014-12-31 | 2011 | Army Active | Unspecified Minor Military Construction | OHIO | UNITED STATES | 74757 | Fire Alarm System |  | 2012-01-19 | 2012-08-05 | Custom Mechanical Systems, Corp | W912QR-12-C-0050 | 1763.338 | 1782.2016 | 2012-09-04 |  | 2013-07-31 | 2015-03-19 | 78.89%
2014-12-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 57434 | Indoor Swimming Pool |  | 2011-08-07 | 2011-09-13 | Megen Construction Company, Inc. | W912DY-11-D-0039 | 13606.4 | 13808.217 | 2011-10-17 | 2013-05-08 | 2013-01-08 | 2013-05-08 | 99%
2014-12-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 67194 | Simulations Center |  | 2010-11-18 | 2011-05-30 | Blackhawk Ventrues, LLC | W9126G-09-D-0093 | 14554.1 | 15176.5831 | 2012-04-09 | 2014-09-14 | 2013-08-08 | 2014-07-30 | 98.65%
2014-12-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex |  | 2011-01-24 | 2011-09-30 | JAMA Constructors | W912HN-11-D-0035 | 6572.777 | 8565 | 2012-07-30 |  | 2014-01-21 | 2015-01-13 | 98%
2014-12-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71465 | Company Operations Facilities |  | 2011-03-21 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 3048.91 | 3461.2134 | 2012-06-19 | 2014-04-14 | 2013-11-11 | 2015-08-09 | 99%
2014-12-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex |  | 2012-12-19 | 2011-09-29 | MW Builders | W9126G-13-C-0061 | 11652.378 | 12094.0635 | 2012-06-19 | 2014-05-05 | 2013-11-11 | 2014-09-11 | 98.99% | 3289 | 65745
2014-12-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex |  | 2012-12-19 | 2013-09-30 | Bristol General Contractors, LLC |  | 15175 | 15261 | 2013-11-06 |  | 2015-01-30 | 2015-04-28 | 27%
2014-12-31 | 2011 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 69421 | Army Reserve Center/Land |  | 2012-01-10 | 2012-07-23 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4454 | 4454 | 2012-08-20 |  | 2014-03-20 | 2015-12-31 | 6.893%
2014-12-31 | 2011 | Army Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 66717 | Military Working Dog Kennel |  |  | 2013-08-05 | Sunlight Enterprises Co., Inc | W9126G-13-C-2005 | 1780.487 | 1817.94 | 2013-08-27 |  | 2014-07-22 | 2014-09-30 | 98.31%
2014-12-31 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 61453 | Replace Fire Station |  | 2012-08-05 | 2013-05-22 | TMG SERVICES, INC. Linda Frazier | W912DR-13-C-0030 | 6189 | 6378.06 | 2013-06-04 |  | 2014-11-27 | 2015-05-14 | 64.12% | 2580 | 68961
2014-12-31 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 65789 | Indoor Firing Range |  | 2011-11-14 | 2012-01-03 | Jordan-Versar, LLC | W91236-08-D-0056 | 6520 | 6749.174 | 2012-01-20 | 2013-10-23 | 2013-10-20 | 2013-10-23 | 99%
2014-12-31 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex |  | 2011-05-02 | 2013-01-22 | Garco Construction, Inc. | W912DW-13-C-0020 | 36247 | 39196.116 | 2013-02-13 |  | 2014-05-23 | 2014-12-15 | 99%
2014-12-31 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex |  | 2014-08-15 | 2014-09-26 | Wm. Dickson Company |  | 1628 | 39196.116 | 2014-10-24 |  | 2015-05-21 | 2015-05-31 | 19%
2014-12-31 | 2011 | Army Reserve | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 79128 | DEPMEDS |  | 2013-03-25 | 2013-09-29 | Imperial Construction | W912QR-13-C-0046 | 1560.895 | 1652.152 | 2013-10-10 | 2014-12-01 | 2014-09-25 | 2014-12-15 | 86.32%
2014-12-31 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74067 | Construct Drainage System, Ph 3 |  | 2012-04-26 | 2012-08-14 | ANHAM-ICSS JV | W912ER-11-D-0003 | 19902.989 | 22733.6248 | 2012-10-08 |  | 2014-05-31 | 2014-10-30 | 96.54%
2014-12-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 55985 | Chapel |  | 2013-07-11 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15915.6532 | 16181.8519 | 2013-11-21 |  | 2016-03-22 | 2016-03-22 | 24.59%
2014-12-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 57594 | Satellite Communications Center |  | 2012-03-11 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565.3511 | 27788.0021 | 2014-03-13 |  | 2015-12-14 | 2016-02-27 | 21.32%
2014-12-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 57594 | Satellite Communications Center |  | 2013-01-22 | 2012-03-27 | JV PGWM SATCOM |  | 262.9753 | 262.9753 | 2014-03-13 |  | 2015-12-14 | 2016-02-27 | 50%
2014-12-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 58925 | Satellite Communications Center |  | 2012-03-11 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0037 | 29010.1333 | 29010.1333 | 2014-10-15 |  | 2015-12-14 | 2016-07-06 | 0% | 6000 | 71485
2014-12-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 69614 | Barracks |  | 2012-03-02 | 2013-03-26 | Staatliches Hochbauamt Amberg | W912GB-10-C-0043 | 17523.1242 | 18638.6582 | 2013-03-26 |  | 2014-12-31 | 2015-01-30 | 83.04%
2014-12-31 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78505 | Family Housing New Construction |  | 2012-04-05 | 2013-08-06 | Staatliches Hochbauamt Amberg |  | 13548.8862 | 13641.2361 | 2013-08-06 |  | 2015-09-13 | 2015-11-05 | 47.36%
2014-12-31 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78506 | Family Housing New Construction |  | 2012-04-09 | 2013-09-29 | Bauamt Amberg-Sulzbach |  | 12815.485 | 12884.7251 | 2013-09-29 |  | 2015-08-10 | 2015-08-10 | 65.24%
2014-12-31 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78475 | Family Housing Improvements |  | 2013-05-21 | 2014-11-24 | Klebl GmbH | W912GB-15-C-0003 | 14631.5966 | 14631.5966 | 2015-01-16 |  | 2016-06-08 | 2016-06-08 | 0%
2014-12-31 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76235 | Barracks Complex |  | 2012-02-02 | 2012-04-05 | Fine Construction Co., Ltd. | W912UM-12-C-0022 | 28609.5284 | 29390.2948 | 2012-04-05 |  | 2014-06-21 | 2014-11-23 | 99%
2014-12-31 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76235 | Barracks Complex |  |  | 2012-02-09 | Hanmi C&E Co., LTD. |  | 18.1909 | 90.3946 | 2012-02-09 | 2014-12-05 | 2014-07-01 | 2014-12-03 | 58.48%
2014-12-31 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 61515 | Physical Fitness Facility |  | 2011-10-18 | 2012-11-07 | Bristol General Contractors, LLC | W911KB-13-C-0002 | 21813.389 | 22240.075 | 2013-03-15 |  | 2014-12-06 | 2015-06-30 | 53.59%
2014-12-31 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67113 | Aviation Complex, Ph 3A |  | 2011-07-14 | 2012-06-06 | Watterson Construction Company | W911KB-12-C-0008 | 70591 | 71467.009 | 2012-06-13 | 2014-11-10 | 2014-08-02 | 2014-12-16 | 98.01% | 27000 | 68962, 71539
2014-12-31 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 56425 | General Instruction Building |  | 2012-08-19 | 2012-09-28 | Souza Construction, Inc. | W91238-10-D-0010 | 2996 | 3163.422 | 2012-11-06 |  | 2013-11-06 | 2015-01-01 | 95.79%
2014-12-31 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 62657 | Water Treatment Plant |  | 2012-05-20 | 2012-09-11 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100112.66 | 99541.018 | 2012-10-18 |  | 2015-10-18 | 2016-01-05 | 63.3%
2014-12-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77264 | Barracks |  | 2012-08-21 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction |  | 51106 | 54384.8228 | 2013-05-31 |  | 2016-08-09 | 2016-08-09 | 3%
2014-12-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77265 | Barracks |  | 2012-08-23 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction |  | 35282 | 37640.8892 | 2013-05-31 |  | 2016-02-12 | 2016-02-12 | 1%
2014-12-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar |  | 2012-08-27 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction |  | 2669 | 2920.134 | 2013-05-31 |  | 2015-08-17 | 2015-09-18 | 18%
2014-12-31 | 2012 | Army Reserve | Major Military Construction | COLORADO | UNITED STATES | 67658 | Army Reserve Center |  | 2011-11-29 | 2012-04-15 | Liberty Mutual Insurance Company | W912QR-12-C-0028 | 10450.922 | 10580.378 | 2012-05-10 |  | 2013-10-17 | 2015-03-01 | 86.97%
2014-12-31 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 59581 | Centralized Wash Facility |  | 2011-10-12 | 2012-01-27 | Watts Constructors, LLC | W9128A-12-C-0001 | 28300 | 29982.274 | 2012-02-08 |  | 2013-12-14 | 2015-02-09 | 98.09%
2014-12-31 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64967 | Child Development Center |  | 2011-10-05 | 2012-02-27 | 57 Builders, Ltd. | W9128A-12-C-0002 | 9573.118 | 10253.638 | 2012-03-22 |  | 2013-12-13 | 2015-02-27 | 87.84%
2014-12-31 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69489 | Combat Aviation Brigade Complex, Ph 1 |  | 2012-01-24 | 2012-06-28 | David Boland, Inc. | W9128A-12-C-0009 | 54772 | 55761.886 | 2012-07-29 |  | 2015-05-26 | 2015-06-10 | 56.21%
2014-12-31 | 2012 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67713 | Army Reserve Center |  | 2012-07-30 | 2012-09-26 | Accel/Pacific J.V. | W912QR-12-C-0068 | 13312 | 14632.1012 | 2012-10-17 |  | 2014-07-09 | 2015-05-17 | 73.17%
2014-12-31 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-08-25 | 2014-01-07 | Law Company, Inc. | W912DQ-14-C-4003 | 20078.9 | 20094.624 | 2014-02-06 |  | 2015-07-30 | 2015-08-03 | 30.38%
2014-12-31 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-08-26 | 2012-10-31 | Arch Insurance Company |  | 5932.641 | 6058.041 | 2012-12-11 |  | 2014-03-15 | 2015-01-02 | 91.78%
2014-12-31 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 17220 | Fire Station |  | 2012-04-02 | 2013-09-24 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12622.8 | 12644.8 | 2013-11-06 |  | 2015-11-11 | 2015-11-11 | 18.57% | 5000 | 65745
2014-12-31 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex |  | 2011-12-16 | 2012-08-16 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 11856.9 | 12236.1292 | 2012-10-08 | 2014-11-12 | 2014-04-01 | 2015-01-30 | 94.82%
2014-12-31 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex |  | 2012-02-21 | 2012-03-22 | Blackhawk Ventures, LLC |  | 10283 | 10964.2248 | 2012-05-14 | 2014-12-20 | 2013-11-06 | 2015-02-12 | 96.2%
2014-12-31 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 64939 | Applied Instruction Facility |  | 2012-06-19 | 2012-09-23 | Grimberg/Amatea JV | W912DR-12-C-0023 | 30554 | 30975.465 | 2012-11-20 |  | 2014-11-20 | 2015-06-30 | 84.55%
2014-12-31 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65755 | Brigade Complex |  | 2012-04-30 | 2012-10-29 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30761.85 | 33584.753 | 2012-12-12 |  | 2015-12-12 | 2017-01-18 | 60.29% | 3500 | 34129, 52856, 64797, 65138, 69167, 69999, 71539
2014-12-31 | 2012 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 64365 | Vehicle Maintenance Facility |  | 2012-02-04 | 2012-11-14 | Robinson Mechanical Contractors, Inc. |  | 2493 | 11146.388 | 2013-01-04 |  | 2015-01-13 | 2015-03-16 | 92%
2014-12-31 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67691 | Army Reserve Center |  | 2011-11-16 | 2012-05-02 | SCMC, LLC | W912QR-12-C-0025 | 17931 | 18716.0068 | 2012-05-31 | 2014-05-20 | 2014-02-21 | 2015-04-29 | 94.91%
2014-12-31 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69432 | Army Reserve Center |  | 2012-12-21 | 2013-03-06 | MACNAK-Korte Design Build LLC | W912QR-13-C-0009 | 14115.817 | 13770.0623 | 2013-04-14 | 2014-11-12 | 2014-07-28 | 2014-11-06 | 97.25%
2014-12-31 | 2012 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 67466 | Army Reserve Center/Land |  | 2012-05-15 | 2012-09-17 | IKHANA, LL | W912QR-12-C-0055 | 15942 | 15977.219 | 2012-10-09 |  | 2014-03-18 | 2015-07-30 | 66.71%
2014-12-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 1235 | Physical Fitness Facility |  | 2012-01-05 | 2012-06-18 | Grahams Construction Inc. | W912DY-11-D-0040 | 23138.91 | 23149.051 | 2012-07-11 |  | 2014-04-09 | 2015-03-06 | 73.07%
2014-12-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 20697 | Chapel |  | 2012-01-27 | 2012-08-29 | Liberty Mutual Insurance Company | W912BV-12-C-0018 | 12999.823 | 13082.662 | 2012-09-19 |  | 2014-01-28 | 2015-04-29 | 52.86%
2014-12-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58207 | Railroad Tracks |  | 2011-11-29 | 2012-03-25 | McAlester Contract | W44XGQ80956921 | 6323.7745 | 6323.7745 | 2012-05-08 |  | 2013-10-05 | 2015-09-14 | 0%
2014-12-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58537 | Reception Station, Ph 1 |  | 2011-11-21 | 2012-05-23 | Zachry Federal Construction Corporation | W912BV-12-C-0010 | 32234.496 | 33035.398 | 2012-06-15 | 2014-12-02 | 2014-03-26 | 2014-12-02 | 97%
2014-12-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 64753 | Vehicle Maintenance Facility |  | 2012-01-17 | 2012-06-29 | Harper Construction Company, Inc. | W912BV-12-C-0012 | 37867.635 | 38313 | 2012-07-19 | 2014-08-29 | 2014-04-11 | 2014-08-29 | 91%
2014-12-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 74690 | THAAD Instruction Facility |  | 2012-01-09 | 2012-03-29 | Roy Anderson Corp. | W912BV-12-C-0002 | 25942 | 26669.2433 | 2012-07-26 | 2014-09-02 | 2014-04-16 | 2014-12-01 | 97.15%
2014-12-31 | 2012 | Army Reserve | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 79315 | Heated Storage Building |  | 2012-11-28 | 2013-02-25 | Q.B.S., Inc. | W912QR-09-D-0018 | 1560.1607 | 1698.0767 | 2013-04-15 | 2014-05-29 | 2014-04-15 | 2015-01-30 | 97.95%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility |  | 2012-10-21 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603 | 9101.83 | 2013-01-24 |  | 2014-07-17 | 2015-04-13 | 55.25% | 3900 | 65745
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility |  |  | 2013-09-26 | Anthony & Gordon Construction Co. Inc. |  | 4150 | 4150 | 2013-01-24 |  | 2014-07-17 | 2015-04-13 | 32.61%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex |  | 2012-01-05 | 2012-07-19 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503 | 39644.6778 | 2012-09-04 |  | 2014-07-27 | 2015-06-29 | 71.74%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex |  | 2012-07-18 | 2013-01-07 | Turner Strategic Technologies, LLC |  | 8195.202 | 8267.659 | 2013-03-08 |  | 2014-11-28 | 2015-02-25 | 85.26%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 |  | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | W9126G-12-C-0015 | 40532.114 | 40884 | 2012-04-24 |  | 2014-04-24 | 2015-09-08 | 72%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 68993 | Electronics Maintenance Facility |  | 2011-12-17 | 2013-09-20 | Venegas Engineering & Management Construction Company |  | 5117.965 | 5117.965 | 2012-08-20 |  | 2013-09-13 | 2015-09-24 | 97.76%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69286 | Infrastructure |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008.411 | 8732.566 | 2012-08-20 |  | 2013-09-13 | 2015-09-24 | 97.56%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69828 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-07-15 | 2014-05-28 | JAM-MAP JV | W9126G-14-C-0016 | 8829.807 | 8829.807 | 2014-08-26 |  | 2016-01-04 | 2016-01-18 | 0%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 70514 | Vehicle Maintenance Facility |  | 2011-12-15 | 2012-03-30 | Urban Associates, Inc. | W912BV-12-C-0005 | 9815.87 | 10561.552 | 2012-05-30 | 2014-04-30 | 2013-09-13 | 2014-01-10 | 99%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 9669.4345 | 10168 | 2012-06-22 |  | 2013-12-14 | 2014-09-11 | 90%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility |  | 2011-12-19 | 2013-12-04 | Soulis Constructors, Inc |  | 5786.309 | 5786.309 | 2014-01-15 |  | 2015-07-09 | 2015-07-29 | 56%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7472.9455 | 7866 | 2012-06-22 |  | 2013-12-14 | 2014-08-31 | 90%
2014-12-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility |  | 2011-12-19 | 2013-12-04 | Soulis Constructors, Inc |  | 5378.708 | 4709 | 2014-01-15 |  | 2015-07-09 | 2015-07-29 | 56%
2014-12-31 | 2012 | Army Active | Major Military Construction | UTAH | UNITED STATES | 55823 | Life Sciences Test Facility Addition |  | 2012-04-11 | 2012-07-25 | Big-D Construction Corp | W91238-12-C-0024 | 22608.566 | 29440.871 | 2012-08-28 |  | 2015-02-15 | 2015-12-03 | 81.73%
2014-12-31 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 57508 | Information Dominance Center, Ph 1 |  | 2013-03-14 | 2013-07-21 | Hensel Phelps Construction Co. | W912DR-13-C-0035 | 39700.01 | 40793.7765 | 2013-08-18 |  | 2015-03-11 | 2015-04-23 | 75.81%
2014-12-31 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 59005 | Aviation Training Facility |  | 2012-03-19 | 2012-05-15 | Oyster Point Construction Company | W91236-12-C-0035 | 13849 | 14321.249 | 2012-06-13 | 2014-09-24 | 2013-12-06 | 2014-06-13 | 99%
2014-12-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 53637 | Brigade Complex, Ph 2 |  |  | 2012-11-09 | Megen Construction Co., INC. |  | 14398 | 36690.9008 | 2012-12-18 |  | 2015-01-28 | 2015-01-28 | 76%
2014-12-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 58046 | Operational Readiness Training Cplx, Ph 1 |  | 2012-06-28 | 2013-03-31 | TSS-Garco Joint Venture | W912DW-12-C-0043 | 16416 | 16268.76 | 2013-05-20 |  | 2014-11-12 | 2015-03-24 | 61.04%
2014-12-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex |  | 2013-07-30 | 2012-09-21 | 3D Contracting Inc. | W9126G-08-D-0045 | 14649 | 32113.5974 | 2012-11-30 |  | 2015-01-13 | 2015-03-16 | 92%
2014-12-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 |  | 2012-08-18 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775 | 46375.6977 | 2013-03-04 |  | 2014-05-24 | 2014-10-31 | 99%
2014-12-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 |  | 2014-03-13 | 2012-08-29 | Alutiiq Diversified Services, LLC |  | 10525 | 46375.6977 | 2012-09-17 |  | 2015-08-21 | 2015-09-10 | 19%
2014-12-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B |  | 2012-08-19 | 2012-09-27 | CJW Construction, Inc. | W912DW-12-C-0051 | 12950.4 | 13974.8006 | 2012-11-29 | 2014-10-13 | 2014-05-22 | 2014-12-15 | 99%
2014-12-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B |  | 2013-12-04 | 2014-04-07 | Glen/Mar Construction, Inc. |  | 4771.02 | 4810.946 | 2014-05-20 |  | 2015-05-20 | 2015-05-30 | 19.32%
2014-12-31 | 2013 | Army Active | Major Military Construction |  | JAPAN | 62783 | Satellite Communications Facility |  | 2013-03-25 | 2014-09-17 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 6488.2629 | 6488.2629 | 2014-11-21 |  | 2021-06-08 | 2021-06-08 | 0% | 24810 | 36113, 61562, 64474, 66441, 69999, 71472, 71485, 72242
2014-12-31 | 2013 | Army Active | Major Military Construction |  | JAPAN | 62783 | Satellite Communications Facility |  |  | 2014-09-17 | Prime Projects International Japan Co., Ltd. |  | 61071.4985 | 61071.4985 | 2014-11-21 |  | 2021-06-08 | 2021-06-08 | 0%
2014-12-31 | 2013 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76196 | Battalion Headquarters Complex |  | 2013-02-01 | 2013-05-13 | Hyosung Corporation | W912UM-13-C-0021 | 25852.7608 | 28686.0028 | 2013-05-13 |  | 2015-06-08 | 2016-04-30 | 24.78%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  | 2014-08-20 | 2014-09-29 | Nan Inc | W9128A-12-D-0012 | 1555.718 | 1555.718 | 2014-10-27 |  | 2015-10-22 | 2015-10-22 | 0%
2014-12-31 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76086 | Lightning Protection System |  | 2014-01-23 | 2014-09-03 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072 | 3072 | 2014-09-15 |  | 2015-12-30 | 2015-12-30 | 0%
2014-12-31 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76091 | Engineering/Housing Maintenance Shop |  | 2014-05-14 | 2014-09-17 | Federal Solutions Group | W91238-14-C-0051 | 3211.6056 | 3211.6056 | 2014-10-07 |  | 2015-11-12 | 2015-11-12 | 0%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 71482 | ORTC |  | 2012-09-24 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56000.64 | 61736.64 | 2014-03-18 |  | 2016-05-16 | 2016-05-16 | 9.678%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72160 | UPH Barracks |  | 2013-03-27 | 2013-08-26 | Pre Con Industries, Inc. | W912QR-13-C-0027 | 4384.284 | 4381.945 | 2013-11-18 |  | 2014-11-03 | 2015-01-30 | 69.85%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 81367 | EXPLOSIVES RECEIVING/SERVICE BUILDING, DEP |  | 2013-12-18 | 2014-04-15 | Cyber Professional Solution Corp | W912PL-14-C-0006 | 1783.729 | 1783.729 | 2014-05-07 |  | 2015-05-07 | 2015-05-07 | 68.67%
2014-12-31 | 2013 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 59626 | Digital Multipurpose Training Range |  | 2013-05-30 | 2013-08-22 | NEU Security Services, LLC | W9128F-13-C-0016 | 14080 | 15393.603 | 2013-09-17 |  | 2015-03-11 | 2015-04-30 | 62.1%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE |  | 2013-08-14 | 2014-06-16 | PORTICO SERVICES, LLC | W912DR-14-C-0028 | 1793.105 | 1841.0157 | 2014-07-14 |  | 2015-03-11 | 2015-03-11 | 31.69%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE |  | 2013-08-15 | 2014-09-29 | Portico Services |  | 219.795 | 219.795 | 2014-10-29 |  | 2015-04-27 | 2015-09-24 | 5.547%
2014-12-31 | 2013 | Army Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 81597 | AMSA Addition/Alteration |  | 2013-08-26 | 2013-09-29 | FutureNet Group, Inc. | W912QR-13-D-0023 | 1379.863 | 1398.495 | 2013-10-08 |  | 2014-09-23 | 2015-03-24 | 50.24%
2014-12-31 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 57794 | Digital Multipurpose Training Range |  | 2012-12-26 | 2013-05-09 | Caddell Construction Co. (DE), LLC | W912HN-10-D-0044 | 19523 | 19679.251 | 2014-02-04 |  | 2015-04-29 | 2015-04-29 | 48.74%
2014-12-31 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 73008 | Unmanned Aerial Vehicle Complex |  | 2013-03-21 | 2013-08-14 | Caddell Construction CO. (DE), LLC | W912HN-10-D-0044 | 20726 | 21007.716 | 2013-11-06 |  | 2015-03-01 | 2015-03-08 | 55.87%
2014-12-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 66023 | Automated Infantry Platoon Battle Course |  | 2014-02-11 | 2014-06-22 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345 | 27345 | 2014-07-07 |  | 2016-09-08 | 2016-09-08 | 0%
2014-12-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76586 | Barracks |  | 2013-02-06 | 2013-07-10 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717.476 | 31271.715 | 2013-07-22 |  | 2015-08-31 | 2015-11-21 | 54.3%
2014-12-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76587 | Barracks |  | 2013-02-06 | 2013-07-10 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410.03 | 38345.079 | 2013-07-22 |  | 2015-08-31 | 2015-11-21 | 55.19%
2014-12-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76903 | Combat Aviation Brigade Barracks |  | 2012-11-26 | 2014-05-12 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749.203 | 69749.203 | 2014-06-25 |  | 2017-01-13 | 2017-01-13 | 3.14%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67659 | Army Reserve Center |  | 2013-04-28 | 2013-08-21 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21575 | 22597.2326 | 2014-01-13 |  | 2015-11-04 | 2015-12-31 | 33.22%
2014-12-31 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex |  | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | W912QR-14-C-0007 | 25750 | 25780.25 | 2014-03-04 |  | 2015-08-25 | 2015-08-25 | 30.8%
2014-12-31 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex |  |  | 2013-05-28 | Orocon-Carothers JV1 |  | 23450.6124 | 23804.1364 | 2013-07-14 |  | 2014-12-07 | 2015-01-09 | 92.86%
2014-12-31 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 76239 | Unmanned Aerial Vehicle Complex |  | 2012-11-13 | 2013-05-30 | Archer Western Federal JV | W912QR-13-C-0012 | 16983 | 17403.585 | 2013-06-24 |  | 2015-04-25 | 2015-04-25 | 92.43%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 81515 | CIDC FIELD OPERATIONS BUILDING |  | 2013-05-20 | 2013-09-28 | Guyco, Inc. | W9126G-09-D-0095 | 1784.466 | 1779.289 | 2013-12-04 |  | 2014-12-04 | 2015-01-03 | 88.32%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | MARYLAND | UNITED STATES | 68077 | Add/Alt Army Reserve Center |  | 2013-12-20 | 2014-06-25 | Arriba Corporation | W912QR-14-C-0023 | 7890.05 | 7890.05 | 2014-07-29 |  | 2016-05-29 | 2016-05-29 | 0.9725%
2014-12-31 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 |  | 2013-04-10 | 2013-08-14 | Caddell Construction Co. (DE), LLC | W912DQ-13-C-4024 | 33360 | 34118.1866 | 2013-09-11 |  | 2015-09-11 | 2015-10-15 | 71%
2014-12-31 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 |  | 2013-01-18 | 2013-05-30 | Donald Maggi, Inc. |  | 11711 | 12144.9042 | 2013-06-24 |  | 2014-12-17 | 2015-01-26 | 93.26%
2014-12-31 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 65679 | Vehicle Maintenance Shop |  | 2013-01-30 | 2013-06-02 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18726.852 | 19105.258 | 2013-06-26 |  | 2015-04-07 | 2015-04-17 | 75.2%
2014-12-31 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 66099 | Battalion Complex Facilities |  | 2012-12-19 | 2013-06-02 | MW Builders, Inc. | W912HN-11-D-0035 | 13687 | 14542.797 | 2013-06-30 |  | 2014-12-23 | 2015-01-11 | 95.17%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE |  | 2013-05-16 | 2013-07-16 | Huffman Construction, LLC |  | 1437.6 | 1550.114 | 2013-09-22 |  | 2014-06-19 | 2015-03-30 | 84.91%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE |  | 2013-02-08 | 2012-09-29 | Zieson Construction Company, LLC |  | 11.171 | 11.171 | 2012-12-10 |  | 2013-12-10 | 2015-05-20 | 99%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | NEVADA | UNITED STATES | 67660 | Army Reserve Center/AMSA |  | 2012-12-28 | 2013-06-11 | MACNAK Korte Team LLC | W912QR-13-C-0014 | 16436.543 | 16859.8067 | 2013-07-09 |  | 2015-04-30 | 2015-04-30 | 76.1%
2014-12-31 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center |  | 2013-05-15 | 2013-09-24 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959 | 6325.204 | 2013-10-22 |  | 2015-02-15 | 2015-08-02 | 73.59%
2014-12-31 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center |  | 2013-05-16 | 2012-09-27 | APS Contracting Inc. |  | 2019.198 | 2019.198 | 2012-12-04 |  | 2014-06-03 | 2015-05-14 | 78.37%
2014-12-31 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 71675 | Flight Equipment Complex |  | 2013-05-01 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751 | 42843.301 | 2014-01-15 |  | 2016-01-15 | 2016-03-10 | 30.06%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71720 | Automated Infantry Squad Battle Course |  | 2012-12-13 | 2013-06-27 | Eastern Construction & Electric, Inc. | W912QR-13-C-0015 | 3093.8904 | 3311.1024 | 2013-07-16 |  | 2014-07-16 | 2015-01-06 | 92.89%
2014-12-31 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 79933 | Cadet Barracks |  | 2012-11-06 | 2013-08-07 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 72000 | 72211.556 | 2013-08-25 |  | 2016-08-29 | 2016-10-27 | 53.56%
2014-12-31 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar |  | 2012-12-12 | 2013-06-16 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 26825.868 | 27139.258 | 2013-06-26 |  | 2015-06-16 | 2015-06-16 | 35.71%
2014-12-31 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar |  | 2012-12-13 | 2013-11-25 | VETCO Contracting Services, LLC |  | 21577.777 | 21390.014 | 2013-12-12 |  | 2015-12-02 | 2015-12-02 | 43.53%
2014-12-31 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80066 | Controlled Humidity Warehouse, Installatio |  | 2012-11-16 | 2013-09-19 | Tyler Construction Co., INC | W912HN-10-D-0060 | 6726.987 | 6769.3467 | 2013-11-06 |  | 2015-03-01 | 2015-04-07 | 60.08% | 8600 | 62955
2014-12-31 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80087 | Storage Building, General Purpose |  | 2012-07-15 | 2013-03-21 | Tyler Construction Group, Inc. | W912HN-10-D-0060 | 9037.592 | 9003.526 | 2013-04-17 |  | 2014-08-10 | 2015-02-27 | 83.25% | 12600 | 76235
2014-12-31 | 2013 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 67037 | Modified Record Fire Range |  | 2012-12-07 | 2013-06-13 | Diversified Construction of Oklahoma, Inc. | W912BV-13-D-0005 | 4160.3398 | 4174 | 2013-09-16 | 2014-09-30 | 2014-08-10 | 2014-09-30 | 99%
2014-12-31 | 2013 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 58970 | Trainee Barracks Complex 2, Ph 2 |  | 2013-04-28 | 2013-10-29 | ACC Construction Co., Inc | W912HP-14-C-0003 | 21786.027 | 21850.968 | 2013-12-04 |  | 2015-05-27 | 2015-06-06 | 51.43%
2014-12-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66911 | Multipurpose Machine Gun Range |  | 2012-12-21 | 2013-05-12 | Blackhawk Ventures, LLC | W9126G-09-D-0093 | 6397 | 6434.605 | 2013-06-09 | 2014-06-26 | 2014-07-04 | 2014-07-09 | 99%
2014-12-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 67020 | Modified Record Fire Range |  | 2012-11-30 | 2013-05-31 | Better Built Construction Services, Inc | W912DY-12-D-0026 | 4094.684 | 4099.3545 | 2013-08-02 | 2014-09-16 | 2014-09-05 | 2014-09-05 | 99%
2014-12-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71120 | Training Aids Center |  | 2013-03-08 | 2013-09-03 | PENTACON, LLC | W912DY-12-D-0030 | 21912 | 22001.757 | 2013-10-16 |  | 2015-04-09 | 2015-05-24 | 39.4%
2014-12-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex |  | 2013-04-24 | 2013-08-14 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491.27 | 11423.509 | 2013-10-06 |  | 2015-05-29 | 2015-05-29 | 60.91%
2014-12-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex |  | 2013-03-11 | 2014-05-28 | JAM-MAP JV |  | 5994.434 | 5994.434 | 2014-08-26 |  | 2016-01-04 | 2016-01-04 | 84.02%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | UTAH | UNITED STATES | 81106 | POLICE/MP STATION |  | 2013-06-10 | 2013-09-26 | Zumwalt Construction, Inc. | W91238-11-D-0026 | 1768.28 | 1768.28 | 2013-10-17 |  | 2014-12-17 | 2015-03-22 | 45.77%
2014-12-31 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  | 2013-07-16 | 2013-09-29 | Purcell Construction Corporation | W91236-13-C-0064 | 46650 | 46659.0739 | 2013-10-14 |  | 2015-10-14 | 2015-10-14 | 58.66%
2014-12-31 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  | 2013-07-17 | 2014-09-02 | VISTA Construction LLC |  | 4055.4 | 4055.4 | 2014-09-15 |  | 2015-09-15 | 2015-12-08 | 0.8077%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80317 | WATER DISTRIBUTION LINES, POTABLE |  | 2013-08-13 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1790.839 | 1790.839 | 2014-01-13 |  | 2014-09-09 | 2015-04-29 | 6.234%
2014-12-31 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 75165 | Waste Water Treatment Plant |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77476.628 | 77926.828 | 2014-03-03 |  | 2016-03-02 | 2016-03-02 | 21.87%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | WASHINGTON | UNITED STATES | 67715 | Army Reserve Center |  | 2013-02-25 | 2013-06-12 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31219 | 31538.544 | 2013-07-10 |  | 2015-08-29 | 2015-08-29 | 62.69%
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81320 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL |  | 2013-08-07 | 2013-09-25 | Northcon, Inc. | W912DW-13-C-0047 | 1380.171 | 1380.171 | 2013-10-27 |  | 2014-10-27 | 2014-10-27 | 84%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 67689 | Central Issue Facility |  | 2013-01-28 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0016 | 9302.203 | 9774.1395 | 2013-07-07 |  | 2014-11-10 | 2015-05-03 | 61.92%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71997 | Dining Facility |  | 2013-01-22 | 2013-08-22 | TCI Architects Engineers Contractor Inc. | W912QR-13-C-0026 | 7738.253 | 7801.4736 | 2013-10-01 |  | 2015-02-04 | 2015-03-24 | 36.59%
2014-12-31 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 72088 | ECS TEMF |  | 2013-01-24 | 2013-06-12 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19021.6 | 19209.031 | 2013-07-07 |  | 2015-06-07 | 2015-06-07 | 44.12%
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 82371 | Power Plant Facility 994 |  | 2014-11-28 | 2014-09-29 | San Juan Construction, Inc. | W9128A-12-D-0010 | 1596.834 | 1596.834 | 2014-10-27 |  | 2015-09-06 | 2015-09-06 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex |  | 2013-08-27 | 2014-05-06 | Silver Mountain Construction, LLC | W911KB-14-C-0008 | 14180.4971 | 14206.8744 | 2014-05-14 |  | 2016-02-04 | 2016-04-18 | 17.18% | 3850 | 63799
2014-12-31 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex |  |  | 2014-12-31 | Arctic-American JV |  | 16180.297 | 16131.008 | 2014-04-22 |  | 2015-10-14 | 2015-12-16 | 40.68%
2014-12-31 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar |  | 2013-08-29 | 2014-06-17 | UNIT COMPANY | W911KB-14-C-0021 | 25546.7 | 25546.7 | 2014-06-29 |  | 2016-03-20 | 2016-09-01 | 6.016%
2014-12-31 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar |  |  | 2014-04-09 | Tunista Construction, LLC |  | 9525 | 9486.903 | 2014-04-24 |  | 2015-10-15 | 2015-12-18 | 38.41%
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 79679 | Materials Analysis Lab |  | 2014-02-03 | 2014-06-09 | Au' Authum Ki, Inc | W912PL-10-D-0109 | 2983.983 | 2983.983 | 2014-07-27 |  | 2015-02-23 | 2015-02-23 | 22.25%
2014-12-31 | 2014 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72284 | TASS Training Center (TTC) |  | 2014-08-12 | 2014-09-29 | Bara Infoware Inc. | W912QR-14-C-0053 | 16186.7042 | 16186.7042 | 2014-10-19 |  | 2016-05-21 | 2016-05-21 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 71221 | Fire Station |  | 2014-03-27 | 2014-07-23 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542.275 | 12011.525 | 2014-08-26 |  | 2016-02-18 | 2016-02-18 | 2.218%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building |  | 2014-02-28 | 2014-07-14 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165.0006 | 17192.5006 | 2014-08-20 |  | 2016-02-12 | 2016-02-12 | 1.294%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building |  | 2014-03-01 | 2014-08-27 | Medvolt, LLC |  | 13195.378 | 13195.378 | 2014-10-07 |  | 2016-03-30 | 2016-03-30 | 5.206%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar |  | 2014-05-21 | 2014-08-06 | Swinerton Builders | W9128F-14-C-0031 | 56720.967 | 56730.945 | 2014-09-01 |  | 2016-08-21 | 2016-08-21 | 4.984%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar |  | 2012-08-26 | 2014-09-04 | John Bowman, Inc. |  | 2288 | 65707.7422 | 2014-10-07 |  | 2015-02-14 | 2015-04-10 | 33%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar |  | 2014-07-08 | 2014-09-11 | David Boland, Inc. | W9128F-14-C-0068 | 50585 | 50585 | 2014-10-05 |  | 2016-05-27 | 2016-05-27 | 0.6472%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar |  | 2014-07-09 | 2014-06-18 | Swinerton Builders |  | 4214.264 | 4321.837 | 2014-07-21 |  | 2015-08-16 | 2015-09-17 | 18.2%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77885 | Runway |  | 2014-03-09 | 2014-06-11 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9832.807 | 10161.124 | 2014-06-30 |  | 2015-06-30 | 2015-08-21 | 17.92%
2014-12-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 79618 | Simulator Building |  | 2014-04-10 | 2014-07-20 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440 | 8440 | 2014-08-19 |  | 2016-02-11 | 2016-02-11 | 0.6844%
2014-12-31 | 2014 | Army Active | Major Military Construction | FLORIDA | UNITED STATES | 77539 | Automated Sniper Field Fire Range |  | 2014-07-16 | 2014-09-25 | Barlovento LLC. | W91278-10-D-0072 | 4201.077 | 4201.077 | 2014-12-17 |  | 2015-12-17 | 2015-12-17 | 0%
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | 85260 | Secure Operations Center |  | 2014-07-08 | 2014-09-29 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1724.858 | 1724.858 | 2014-11-05 |  | 2015-11-05 | 2015-11-05 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 76024 | Simulations Center |  | 2014-02-28 | 2014-07-01 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630 | 15630 | 2014-09-01 |  | 2016-02-24 | 2016-02-24 | 2.221%
2014-12-31 | 2014 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 78778 | Battlefield Weather Support Facility |  | 2013-12-24 | 2014-06-17 | TJC Engineering | W912QR-14-C-0018 | 4275.114 | 4283.952 | 2014-06-26 |  | 2015-08-20 | 2015-08-20 | 16.06%
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 77980 | Cantonment Area, Roads, Paved |  | 2014-08-11 | 2014-09-15 | FutureNet Group, Inc. | W912QR-09-D-0050 | 1635.599 | 1635.599 | 2014-09-23 |  | 2015-08-19 | 2015-08-19 | 2%
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 82268 | Illinois Ave (PREPO) Yd |  | 2014-07-21 | 2014-09-29 | Tarver Land Development, LLC | W9126G-14-C-0059 | 1748.75 | 1748.75 | 2014-12-03 |  | 2015-04-01 | 2015-04-01 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 81875 | Operations and Maintenance Facilities |  | 2013-12-02 | 2014-05-11 | Edifice-Schlosser JV, LLC | W912DR-14-C-0017 | 17891 | 20186.3752 | 2014-05-22 |  | 2015-03-18 | 2015-04-28 | 51.55%
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 80477 | Fragmentation Simulation Lab |  | 2013-04-21 | 2013-12-13 | The Clement Group, L.L.C. | W91278-11-D-0029 | 2341.157 | 2345.214 | 2014-01-23 |  | 2015-07-16 | 2015-07-16 | 34.96%
2014-12-31 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  | 2014-03-06 | 2014-07-09 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777 | 48652.193 | 2014-08-04 |  | 2016-08-03 | 2016-09-10 | 5.779%
2014-12-31 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  | 2014-10-16 | 2014-12-19 | Zieson Construction Co. |  | 14313.443 | 14313.443 |  |  | 2016-07-09 | 2016-07-09 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 75019 | Simulator Building |  | 2014-08-27 | 2014-11-06 | Zieson Construction Co. | W912DQ-15-C-4000 | 3496.695 | 3496.695 | 2014-12-01 |  | 2015-12-01 | 2015-12-01 | 0%
2014-12-31 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 65277 | Consolidated Dining Facility |  | 2014-01-09 | 2014-03-30 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 10798.9 | 10798.9 | 2014-04-22 |  | 2015-09-29 | 2015-09-29 | 10.35%
2014-12-31 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 69669 | Central Issue Facility |  | 2014-01-31 | 2014-06-04 | Ranco Construction, Inc. | W912QR-14-C-0021 | 8783.22 | 8783.22 | 2014-07-06 |  | 2015-12-14 | 2015-12-14 | 1.058%
2014-12-31 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71769 | Modified Record Fire Range |  | 2014-08-05 | 2014-09-29 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653 | 4653 | 2014-10-16 |  | 2016-04-08 | 2016-04-08 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81186 | Cadet Barracks, Incr 2 | 79933 | 2012-11-06 | 2013-08-07 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 40000 | 40119.542 | 2013-08-25 |  | 2016-07-07 | 2016-07-07 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69624 | Command and Control Facility |  | 2014-06-09 | 2014-07-20 | Brantley Construction Services, LLC | W912HN-10-D-0056 | 4720.25 | 4726.269 | 2014-08-26 |  | 2015-08-26 | 2015-08-26 | 20.89%
2014-12-31 | 2014 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71900 | Army Reserve Center |  | 2014-07-28 | 2014-09-29 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129.201 | 22129.201 | 2014-12-02 |  | 2016-10-31 | 2016-10-31 | 0.9194%
2014-12-31 | 2014 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 81155 | Unmanned Aerial Vehicle Complex |  | 2014-05-01 | 2014-07-23 | SGS, LLC | W9126G-15-C-0005 | 32968.419 | 32968.419 | 2014-12-18 |  | 2016-04-10 | 2016-04-10 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  | 2014-05-12 | 2014-09-17 | Purcell Construction Corporation | W91236-14-C-0046 | 40036.48 | 40036.48 | 2014-10-08 |  | 2017-07-04 | 2018-06-14 | 0%
2014-12-31 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 54106 | Automated Multipurpose Machine Gun Range |  | 2013-12-24 | 2014-05-27 | TSS-Garco Joint Venture | W912DW-14-C-0012 | 7716 | 7716 | 2014-08-17 |  | 2016-02-09 | 2016-02-09 | 0.6%
2014-12-31 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar |  | 2014-06-24 | 2014-08-25 | Archer Western Federal JV | W912DW-14-C-0023 | 36998 | 36998 | 2014-09-22 |  | 2016-03-15 | 2016-03-15 | 0.5662%
2014-12-31 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar |  | 2014-05-18 | 2014-09-02 | The Renew Group, Inc. |  | 1106.039 | 1106.039 | 2014-10-23 |  | 2015-04-21 | 2015-04-21 | 0%
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80919 | Underground Electric Lines |  | 2014-08-11 | 2014-09-28 | Glen/Mar Construction, Inc. | W912DW-14-C-0029 | 1544.779 | 1544.779 |  |  | 2015-10-28 | 2015-10-28 | 0%
2014-12-31 | 2014 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71999 | NCO Academy Dining Facility |  | 2013-12-12 | 2014-03-30 | Wilson Brigadier Joint Venture | W912QR-14-C-0013 | 5900 | 5900 | 2014-04-21 |  | 2015-08-24 | 2015-08-24 | 23.74%
2014-12-31 | 2014 | Army Active | Military Family Housing | WISCONSIN | UNITED STATES | 74861 | Family Housing New Construction |  | 2014-03-04 | 2014-07-30 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862.0909 | 21862.0909 | 2014-08-19 |  | 2016-08-08 | 2016-08-08 | 2.743%
2014-12-31 | 2009 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010154 | Multipurpose Machine Gun Range |  | 2009-04-28 | 2009-05-05 | HDH General Contractors, Inc. | AC-09-C-0014-S | 2671 | 1636 | 2009-05-11 | 2011-11-21 | 2011-11-16 | 2011-11-16 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130109 | Armed Forces Reserve Center |  | 2009-09-09 | 2009-09-09 | New South Construction Company, Inc. | 41100-044-0000070579 | 36015 | 27900 | 2009-09-21 | 2011-11-01 | 2011-04-11 | 2013-09-24 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230070 | Regional Training Institute, PH 1 |  | 2009-04-08 | 2009-04-16 | Nickerson & O'Day, Inc. | 230070-D | 18713 | 14314 | 2009-05-18 | 2011-06-13 | 2011-06-13 | 2011-06-13 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240189 | Army Aviation Support Facility, Add/Alt |  | 2009-05-05 | 2009-09-28 | Tetra-Tech Facilities Construction, LLC | W912K6-09-C-0002 | 27603 | 27193 | 2010-03-01 | 2012-06-01 | 2010-09-27 | 2012-06-30 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Project has claim with ASBC and claim has not been finalized, schedule to go to trial in Oct 15
2014-12-31 | 2009 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260212 | Infantry Squad Battle Course |  | 2009-08-19 | 2009-09-02 | The Garrison Company | Y09127 | 2000 | 2167 | 2009-09-07 | 2010-06-30 | 2010-05-18 | 2010-05-18 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270260 | Readiness Center |  | 2009-08-04 | 2009-08-07 | Holte/Graham, JV | W912LM-09-C-0005 | 13390 | 12529 | 2009-08-10 | 2011-12-01 | 2010-12-14 | 2013-05-31 | 99% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320069 | Readiness Center |  | 2011-10-27 | 2012-06-01 | Nevada State Public Works | W9124X-11-2-2001 | 11246 | 7762 | 2012-06-11 | 2013-04-30 | 2013-07-12 | 2013-03-27 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2014-12-31 | 2009 | Army National Guard | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 320152 | Paint Booth |  | 2009-06-04 | 2009-09-01 | Nevada State Public Works | W9124X-09-2-2003 | 1500 | 1075 | 2009-09-16 | 2012-05-24 | 2012-05-21 | 2012-05-21 | 100% | 0 |  | Congressionally Directed
2014-12-31 | 2009 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360191 | Maneauver Area Training and Equipment Site, PH 3 |  | 2009-09-04 | 2009-09-30 | Beardsley Design Associates | DAHA30-00-0009 | 10879 | 9544 | 2010-03-10 | 2012-09-30 | 2011-03-09 | 2013-04-11 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Unspecified Minor Military Construction | OHIO | UNITED STATES | 390270 | Ravenna TTB Utilities |  | 2009-12-15 | 2010-01-28 | Portage County Water Resources Department |  | 1600 | 1600 | 2011-11-01 | 2012-02-22 | 2012-01-30 | 2012-12-06 | 100% | 0
2014-12-31 | 2009 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420511 | Readiness Center, Add/Alt |  | 2011-08-31 | 2011-09-15 | Lobar Incorporated | DGS 961-20.1 | 6117 | 5738 | 2011-09-26 | 2013-08-15 | 2012-10-30 | 2014-12-31 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440039 | Army Aviation Support Facility, Add/Alt (additional funds for FY08 project) |  | 2008-07-09 | 2008-09-25 | Bacon Construction Co., Inc. | W912LD-08-C-0036 | 4848 | 4150 | 2009-01-09 | 2012-01-06 | 2011-01-09 | 2012-09-30 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460077 | Armed Forces Reserve Center |  | 2009-03-31 | 2009-04-17 | J Scull Construction | W912MM-04-2-2001 | 28762 | 27822 | 2010-04-05 | 2011-06-24 | 2011-11-14 | 2011-11-14 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460132 | Barracks/Dining/Admin & Parking Complex, PH1 |  | 2009-06-11 | 2009-06-24 | J Scull Construction | W912-MM-09-2-2001 | 12765 | 11645 | 2009-08-10 | 2011-03-02 | 2010-12-15 | 2010-12-15 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | TENNESSEE | UNITED STATES | 470043 | Readiness Center |  | 2009-09-16 | 2009-09-25 | Sain Construction Co. | W912L7-09-C-0008 | 8787 | 7706 | 2009-10-01 | 2011-09-15 | 2011-01-21 | 2011-09-15 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490101 | Ammunition Supply Point |  | 2009-09-17 | 2009-09-18 | Creative Times Inc. |  | 13843 | 12045 | 2009-09-21 | 2011-07-30 | 2010-10-01 | 2010-10-01 | 100% | 2358 | 540205 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530012 | Readiness Center |  | 2009-09-11 | 2009-09-11 | Wade Perrow Construction, LLC | W912K3-09-C-0001 | 30265 | 24954 | 2009-09-12 | 2011-07-28 | 2011-01-31 | 2011-01-31 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540105 | Joint Interagency Training Education Center, PH 1 |  | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | DEFK10003 | 77500 | 72200 | 2009-10-01 | 2011-09-30 | 2011-09-28 | 2014-09-30 | 99% | 0 |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Generator work being completed
2014-12-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540205 | Access Control Point |  | 2009-09-25 | 2009-09-25 | DanHill Construction | DEFK13007 | 3945 | 3694 | 2013-05-01 | 2013-12-16 | 2013-12-11 | 2014-10-30 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Formal Reprogramming $2,358 funds from FY09 project savings {PN: 490101}, PM Assigned
2014-12-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540206 | Multi-Purpose Building, PH II |  | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | DEFK10004 | 4755 | 4624 | 2010-02-01 | 2010-08-30 | 2010-08-26 | 2013-03-31 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2014-12-31 | 2009 | Army National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | 540208 | Tri-State Armory Addition |  | 2009-04-24 | 2009-09-23 | Neighborgall Construction Company |  | 2000 | 2000 | 2009-10-01 | 2010-08-11 | 2010-07-16 | 2010-08-31 | 100% | 0 |  | Congressionally Directed, PM Assigned
2014-12-31 | 2010 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010279 | Urban Assault Course |  | 2010-09-06 | 2010-09-10 | Baggette Construction, Inc. | AC-10-C-0045-S | 2980 | 2396 | 2010-12-01 | 2011-10-11 | 2011-08-08 | 2011-08-08 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040227 | Combat Pistol Qualification Course |  | 2010-06-14 | 2010-06-15 | Norquay Construction | M10-0015 | 2964 | 1867 | 2010-06-28 | 2011-07-15 | 2010-12-31 | 2010-12-31 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060115 | Readiness Center, PH 1 |  | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | W912LA-10-C-0009 | 30711 | 23127 | 2010-11-15 | 2013-10-07 | 2012-02-06 | 2014-10-31 | 97% | 2900 | 390263 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | GUAM | GUAM | 140300 | Readiness Center |  | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | N40192-10-C-1335 | 20766 | 20797 | 2010-05-03 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 95% | 3000 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170611 | Readiness Center, Add/Alt |  | 2010-09-17 | 2010-09-22 | Capital Development Board | W91SMC-10-2-2001-100 | 5560 | 4319 | 2010-10-18 | 2012-03-31 | 2011-09-14 | 2011-09-14 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230114 | Regional Training Institute, PH II |  | 2010-08-11 | 2010-09-21 | Nickerson & O'Day, Inc. | 230070-D | 15464 | 14399 | 2010-09-21 | 2012-08-17 | 2012-07-21 | 2014-01-31 | 100% | 0 |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250087 | Armed Forces Reserve Center (JFHQ) |  | 2010-06-07 | 2010-06-25 | CTA Construction |  | 27595 | 26247 | 2010-07-12 | 2012-01-15 | 2011-10-19 | 2014-04-30 | 100% | 2000 | 060413 | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260213 | Organizational Maintenance Shop (ADRS) |  | 2010-08-04 | 2010-09-22 | LD Dosca Associates, Inc. | W912JB-09-D-2014 | 7722 | 7419 | 2010-10-01 | 2012-03-01 | 2011-10-18 | 2011-10-18 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Unspecified Minor Military Construction | MICHIGAN | UNITED STATES | 260232 | Dining Facility |  | 2010-07-09 | 2010-09-23 | Ripman Construction Co., Inc. | Y10342 | 1998 | 1991 | 2010-10-01 | 2011-06-27 | 2011-09-30 | 2011-12-01 | 100% | 0
2014-12-31 | 2010 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270252 | Urban Assault Course |  | 2011-07-11 | 2011-08-18 | Saginaw Contracting, Inc. | W912LM-10-D-0016 | 1693 | 1192 | 2011-08-22 | 2012-07-18 | 2013-03-18 | 2014-07-18 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270261 | Readiness Center, PH 2 |  | 2010-08-30 | 2010-09-07 | MAVCON | W912LM-10-C-0003 | 3184 | 2855 | 2010-09-27 | 2012-05-01 | 2011-07-18 | 2013-05-31 | 100% | 3500 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($3,184)
2014-12-31 | 2010 | Army National Guard | Unspecified Minor Military Construction | MINNESOTA | UNITED STATES | 270263 | CST, Add/Alt |  | 2011-08-09 | 2011-08-19 | LS Black Constructors | W912LM-10-D-0004 | 1954 | 1897 | 2011-09-12 | 2012-11-20 | 2012-08-24 | 2013-12-20 | 100% | 0
2014-12-31 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320143 | Readiness Center |  | 2010-09-27 | 2010-09-27 | The Penta Building Company |  | 25807 | 19910 | 2010-10-25 | 2013-05-01 | 2012-01-23 | 2013-04-19 | 99% | 3112 | 060413 | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320197 | Renewable Energy Sustainable Projects |  | 2010-09-21 | 2010-09-24 | Ray Heating Products Inc. | W9124X-10-2-2001 | 1997 | 1899 | 2010-10-04 | 2011-10-26 | 2011-04-04 | 2011-04-04 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350043 | Army Aviation Support Facility |  | 2010-06-29 | 2010-07-02 | PCL Construction Services Inc. | W912PP-10-C-0022 | 35577 | 31835 | 2010-09-13 | 2012-03-20 | 2011-09-14 | 2011-09-14 | 100% | 3300 | 080067 | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370896 | Readiness Center, Add/Alt |  | 2010-09-07 | 2010-09-10 | Architectural Design Studio |  | 2501 | 2033 | 2010-09-27 | 2011-10-13 | 2011-09-30 | 2011-10-17 | 99% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380120 | Dike Construction |  | 2010-06-01 | 2010-07-26 | Ames Construction | SER-3-020-(082)098 | 1675 | 1818 | 2010-11-01 | 2014-08-14 | 2012-08-20 | 2014-12-18 | 100% | 0 |  | (NGB 593)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410120 | Readiness Center |  | 2010-09-14 | 2010-09-21 | Lease Crutcher Lewis | 410120D002 | 12093 | 11893 | 2010-10-08 | 2012-09-01 | 2012-12-01 | 2012-12-01 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410820 | Water Supply Company |  | 2010-09-10 | 2010-09-21 | Hoffman Construction Company | 410820D002 | 3369 | 3368 | 2010-10-01 | 2011-08-01 | 2011-10-02 | 2011-10-02 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | UNITED STATES | 436019 | Urban Assault Course |  | 2009-12-01 | 2010-09-29 | Remex Co. | W912LR-10-B-0001 | 1669 | 1846 | 2010-10-01 | 2011-10-03 | 2011-09-23 | 2011-09-23 | 100% | 0 |  | Congressionally Directed
2014-12-31 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450252 | Army Aviation Support Facility, Add/Alt |  | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. |  | 14759 | 14078 | 2011-02-07 | 2013-04-15 | 2011-12-14 | 2013-05-01 | 99% | 11000 | 090115, 220241 and 220243 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450353 | Army Aviation Support Facility |  | 2010-09-23 | 2010-09-24 | Hendrick Construction | 460114576 | 27936 | 27304 | 2010-11-17 | 2013-06-21 | 2012-08-10 | 2013-06-21 | 75% | 12100 | 220241, 220243, and 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936)
2014-12-31 | 2010 | Air National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460141 | Joint Force HQ Readiness Center, Supplemental |  | 2010-08-26 | 2010-09-03 | J. Scull Construction Services, Inc. | W912MM-09-2-2003 | 5705 | 5257 | 2010-09-27 | 2012-04-14 | 2012-04-14 | 2012-04-14 | 100% | 2500 | 530035 | Congressional Add, PL 112-25 (Budget Control Act, 2011)/2853 Notification ($5,705), Delays in getting LEED Certification, State holding funds from A-E for this. Tentative submission date is May 2015
2014-12-31 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480175 | Armed Forces Reserve Center |  | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 16441 | 14196 | 2011-01-01 | 2012-07-17 | 2012-06-15 | 2013-11-04 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480176 | Field Maintenance Shop, Joint |  | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 5700 | 7021 | 2011-01-01 | 2012-07-17 | 2013-06-15 | 2013-11-04 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520014 | Regional Training Institute, PH 1 |  | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. | W9127P-10-C-0001 | 19978 | 19493 | 2010-07-01 | 2013-02-15 | 2012-02-20 | 2013-04-23 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540217 | Readiness Center Addition/Life Safety Upgrades |  | 2010-09-24 | 2010-09-26 | Hayslett Construction Company | DEFK11013 | 1073 | 1135 | 2010-10-01 | 2011-10-21 | 2011-09-18 | 2011-09-18 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050043 | Combined Support Maintenance Shop |  | 2011-06-24 | 2011-07-01 | CDI Contractor, LLC | 970816 | 29887 | 28574 | 2011-11-01 | 2013-08-15 | 2013-07-01 | 2013-10-01 | 95% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050163 | Combined Arms Collective Training Facility |  | 2010-12-21 | 2011-05-23 | Crossland Construction Company, Inc. | 9751022 | 18609 | 7413 | 2011-09-19 | 2013-06-13 | 2012-03-23 | 2013-10-15 | 99% | 6500 | 530035 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($8,858)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050173 | Live Fire Shoot House |  | 2011-05-26 | 2011-06-14 | Ross Sparks Builders, Inc. | 9751028 | 2488 | 2267 | 2011-07-01 | 2012-09-18 | 2012-06-07 | 2013-10-15 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060429 | Combined Arms Collective Training Facility |  | 2011-05-12 | 2011-09-20 | Cox Construction Company | W912LA-11-R-0005 | 12379 | 11525 | 2011-12-05 | 2013-06-15 | 2012-06-29 | 2013-09-27 | 99% | 6700 | 361103 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080062 | HAATS/AASF |  | 2011-05-19 | 2011-07-13 | Hensel Phelps Construction Company |  | 38862 | 37413 | 2011-11-01 | 2013-04-01 | 2013-03-31 | 2013-10-31 | 95% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080067 | Regional Training Institute |  | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC |  | 50886 | 50926 | 2011-10-01 | 2013-10-01 | 2014-10-18 | 2014-10-03 | 95% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2,000 Formal Reprogramming $9,300 funds from FY10 project savings {PNs: 160120 ($6,000) & 350043 ($3,300)}
2014-12-31 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080201 | Readiness Center |  | 2011-08-12 | 2011-09-16 | Smith Construction Management, LLC |  | 19934 | 18999 | 2011-12-01 | 2013-10-01 | 2013-09-30 | 2014-09-10 | 98% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080202 | Readiness Center |  | 2011-08-05 | 2011-08-16 | AP Mountain States |  | 7485 | 7469 | 2011-12-01 | 2012-11-01 | 2012-10-19 | 2012-10-19 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-12-31 | 2011 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090010 | Readiness Center (Aviation) |  | 2011-05-27 | 2011-09-22 | Walsh Construction Co. | W912RS-11-C-0017 | 40616 | 32004 | 2011-10-01 | 2013-11-05 | 2013-10-19 | 2013-10-19 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100037 | Armed Forces Reserve Center (JFHQ) |  | 2011-08-03 | 2011-08-18 | Vigil Contracting, Inc. | W912L5-09-2-2001 | 26879 | 25717 | 2011-12-01 | 2014-04-01 | 2013-07-10 | 2014-05-08 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130123 | Readiness Center, Add/Alt |  | 2011-05-17 | 2012-04-17 | TEPA | W912JM-10-D-0018 | 10363 | 10349 | 2012-06-04 | 2013-09-30 | 2013-09-30 | 2014-04-30 | 10% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130127 | Readiness Center |  | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 41100-033-0000078159 | 16941 | 16726 | 2011-12-01 | 2013-05-15 | 2012-11-16 | 2012-11-16 | 85% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | GUAM | GUAM | 140001 | Combined Support Maintenance Shop, Ph 1 |  | 2011-05-31 | 2011-09-01 | NAVFAC Pacific | N40192-10-D-2801-0004 | 18961 | 19300 | 2011-09-12 | 2013-04-19 | 2012-04-20 | 2012-04-20 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-12-31 | 2011 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160093 | Barracks (ORTC), Ph 1 |  | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | W912J7-11-C-0002 | 17333 | 13811 | 2011-08-27 | 2013-10-03 | 2013-02-28 | 2014-04-15 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 179237 | Combined Support Maintenance Shop, Add/Alt |  | 2011-09-15 | 2011-09-20 | CORE Construction | W91SMC-09-2-2002 | 14954 | 14464 | 2011-10-24 | 2013-07-17 | 2012-10-05 | 2014-07-31 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200063 | Readiness Center |  | 2011-07-15 | 2011-08-11 | Straub Construction Co., Inc. |  | 26283 | 23235 | 2011-09-23 | 2013-07-01 | 2012-12-07 | 2013-07-15 | 99% | 12461 | 150023 and 490444 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($26,283)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200090 | Field Maintenance Shop |  | 2011-09-01 | 2011-09-26 | The Law Company, Inc. |  | 13243 | 12402 | 2011-11-18 | 2014-04-15 | 2012-10-19 | 2014-04-15 | 99% | 9000 | 150023 and 400066 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($13,244)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220114 | Readiness Center |  | 2011-06-23 | 2011-08-08 | Walton Construction Co., LLC. | LA11-C-125 | 27676 | 22524 | 2011-08-29 | 2013-09-03 | 2013-01-14 | 2013-08-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($19,308), Closeout procedures pending
2014-12-31 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220222 | Tactical Unmanned Aircraft System Facility |  | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company | LA11-C-139 | 5470 | 5018 | 2011-09-12 | 2012-12-11 | 2012-07-30 | 2013-06-18 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240186 | Tactical Unmanned Aircraft System Facility |  | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | N40080-10-D-0498 | 5480 | 5583 | 2011-09-23 | 2013-09-27 | 2013-06-15 | 2014-04-15 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250136 | Armed Forces Reserve Center (JFHQ), Ph 2 |  | 2011-09-15 | 2011-09-22 | Nauset Construction Corp. | W912SV-11-C-0004 | 22927 | 21885 | 2011-10-17 | 2012-11-17 | 2012-10-27 | 2014-04-04 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270202 | Field Maintenance Shop |  | 2011-07-19 | 2011-08-08 | Stahl Construction Company | STA006002 | 28894 | 26314 | 2011-10-26 | 2013-05-03 | 2013-01-18 | 2014-04-18 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270267 | Tactical Unmanned Aircraft System Facility |  | 2011-07-21 | 2011-08-08 | Donlar Construction Company | DON050003 | 4413 | 3544 | 2012-04-03 | 2012-12-13 | 2012-10-27 | 2012-12-13 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310107 | Readiness Center |  | 2011-06-15 | 2011-07-12 | The Weltz Company, LLC |  | 11368 | 11339 | 2012-05-07 | 2013-05-06 | 2012-08-08 | 2013-04-01 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310110 | Readiness Center, Add/Alt |  | 2011-08-16 | 2011-08-19 | Kingery Construction Company |  | 3293 | 3339 | 2011-10-01 | 2013-05-06 | 2012-11-06 | 2013-04-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330034 | Classroom Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-25 | Eckman Construction Company, Inc. | 80342R-G | 20742 | 19649 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-03 | 15% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330035 | Barracks Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-26 | Eckman Construction Company, Inc. | 80342R-G | 14880 | 13736 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-30 | 15% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350075 | Readiness Center, Add/Alt |  | 2011-04-19 | 2011-09-29 | Jaynes Corporation | 12-705-0000-1213 | 8481 | 10306 | 2011-12-05 | 2012-12-25 | 2012-10-31 | 2012-10-31 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370898 | Readiness Center, Add/Alt |  | 2011-09-08 | 2011-09-15 | Holden Building Company, Inc. | W912421022003 | 1547 | 1590 | 2011-11-05 | 2012-08-01 | 2012-10-26 | 2012-10-26 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | UNITED STATES | 436021 | Multi Purpose Machine Gun Range |  | 2012-08-27 | 2012-08-29 | Eastern Construction and Electrical Inc. | W912LR-14-B-2004 | 9200 | 9567 | 2014-09-15 | 2015-01-26 | 2015-01-26 | 2015-01-26 | 0% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | UNITED STATES | 436023 | Live Fire Shoot House |  | 2011-07-21 | 2011-09-22 | Remex Co. | W912LR-11-B-0001 | 3077 | 2562 | 2011-11-07 | 2012-09-18 | 2012-12-14 | 2012-12-14 | 65% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440009 | United States Property and Fiscal Office |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 26713 | 21433 | 2012-08-20 | 2014-07-04 | 2014-04-17 | 2014-08-31 | 96% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460085 | Readiness Center |  | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. | W912MM-06-2-20002 | 18255 | 17797 | 2011-11-07 | 2013-03-01 | 2013-01-14 | 2014-11-01 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($18,225)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520034 | Readiness Center (JFHQ) |  | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | W9127P-11-C-0005 | 24850 | 22324 | 2011-11-01 | 2013-11-25 | 2012-08-20 | 2013-08-01 | 62% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530022 | Combined Support Maintenance Shop |  | 2011-06-07 | 2011-06-23 | Pease & Sons, Inc. |  | 24880 | 24115 | 2011-08-22 | 2013-12-12 | 2012-11-03 | 2014-09-23 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), State waiting on demolition of the old CSMS
2014-12-31 | 2011 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540068 | Readiness Center |  | 2011-09-21 | 2011-09-22 | Massaro Corporation |  | 20895 | 19502 | 2011-11-14 | 2013-04-09 | 2013-03-26 | 2013-03-26 | 75% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540084 | Readiness Center |  | 2011-06-01 | 2011-09-21 | Langan General Contracting Corp | DEFK1200 | 14145 | 13573 | 2011-10-08 | 2013-04-22 | 2013-03-24 | 2014-06-23 | 90% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550139 | Aircraft Parking |  | 2011-08-16 | 2011-09-15 | Buteyn Peterson Construction Co. | NGB-47-11-C-0014 | 5689 | 5960 | 2011-11-01 | 2012-10-09 | 2012-10-29 | 2012-10-17 | 94% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 011006 | Readiness Center, Add/Alt |  | 2012-09-13 | 2012-09-23 | Metro D. Constructions, LLC | AC-12-C-0036-S | 2000 | 1999 | 2012-11-18 | 2013-10-01 | 2013-09-16 | 2014-01-28 | 10% | 0
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 010263 | Readiness Center, Ph2 |  | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. | W912JA-12-C-0001 | 16413 | 14492 | 2012-09-14 | 2013-12-24 | 2013-12-10 | 2013-12-10 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040294 | Readiness Center |  | 2012-02-15 | 2012-08-16 | Haydon Building Corporation-Tem | M11-0045 | 17771 | 17655 | 2012-09-12 | 2013-11-04 | 2013-10-16 | 2014-01-31 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050172 | Convoy Live Fire/Entry Control Point Range |  | 2012-02-14 | 2012-08-16 | USPFO - AK | 9751104 | 3500 | 3604 | 2012-11-07 | 2013-12-20 | 2013-10-28 | 2014-07-15 | 97% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | 050190 | Wash Platform, Installation |  | 2013-09-12 | 2013-09-18 | Wilkins Construction, Inc. |  | 1195 | 1759 | 2014-03-10 | 2014-06-23 | 2014-06-23 | 2014-12-22 | 33% | 0
2014-12-31 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060009 | Utilities Replacement Ph1 |  | 2012-07-09 | 2012-08-01 | Cox Construction Co. | W912LA-12-C-0007 | 31073 | 25066 | 2012-12-01 | 2014-09-26 | 2015-03-01 | 2015-04-30 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060170 | Field Maintenance Shop |  | 2012-06-19 | 2012-06-26 | Goshawk LLC | W912LA-12-C-0003 | 7985 | 7482 | 2012-11-08 | 2013-10-20 | 2013-10-14 | 2014-06-06 | 30% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 060432 | Barracks |  | 2012-06-27 | 2012-09-28 | WEP Enterprises | W912LA-11-D-0024 | 1400 | 1131 | 2012-10-15 | 2013-10-07 | 2013-09-20 | 2014-10-30 | 99% | 0 |  | FY07 Congressionally Directed, Used FY10 funds
2014-12-31 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060438 | Tactical Unmanned Aircraft System Facility |  | 2012-06-04 | 2012-07-20 | Red Mountain LLC | W912LA-12-C-0002 | 6114 | 5236 | 2012-08-06 | 2013-11-11 | 2013-10-28 | 2014-11-15 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080093 | Barracks Complex (ORTC) |  | 2012-08-30 | 2012-09-04 | FSA & JKC Joint Venture One, LLC. |  | 42228 | 43796 | 2012-09-24 | 2013-12-03 | 2013-10-28 | 2015-01-23 | 97% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080126 | Readiness Center |  | 2012-06-12 | 2012-06-22 | FCI Constructors, Inc. |  | 6397 | 6254 | 2012-09-10 | 2013-12-02 | 2013-10-14 | 2013-10-14 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080206 | Tactical Unmanned Aircraft System Facility |  | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. |  | 3592 | 3892 | 2012-11-05 | 2013-12-03 | 2013-10-28 | 2014-08-15 | 83% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120188 | Convoy Live Fire/Entry Control Point Range |  | 2012-07-31 | 2012-08-16 | Breaking Ground Contracting Co. |  | 2400 | 3000 | 2013-02-13 | 2013-12-16 | 2013-12-02 | 2013-12-02 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120277 | Unit Storage Building (TUAS) |  | 2012-08-30 | 2012-09-14 | C. Young Construction |  | 821 | 821 | 2013-04-13 | 2013-10-19 | 2013-09-12 | 2013-09-12 | 20% | 0
2014-12-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130063 | Maneauver Area Training and Equipment Site, Ph 1 |  | 2012-01-12 | 2012-09-11 | J&S Construction Company, Inc. | W912JM-12-R-0011 | 19255 | 19288 | 2012-10-19 | 2013-11-18 | 2013-10-28 | 2015-02-02 | 22% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2014-12-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130068 | Readiness Center Ph 1 |  | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC |  | 14457 | 14123 | 2012-09-14 | 2013-04-12 | 2014-03-14 | 2014-10-14 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130120 | Readiness Center |  | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. |  | 10991 | 11239 | 2012-09-10 | 2013-11-18 | 2013-10-28 | 2014-11-24 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150043 | Readiness Center Ph 1 |  | 2012-02-15 | 2012-07-11 | Dawson Technical, LLC | W912J6-12-R-0002 | 31992 | 32580 | 2012-07-23 | 2014-08-11 | 2014-07-23 | 2014-07-23 | 12% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170801 | Readiness Center |  | 2012-09-13 | 2012-09-13 | River City Construction | W91SMC-10-2-2005 | 10871 | 10557 | 2012-11-05 | 2013-05-31 | 2014-10-28 | 2014-09-30 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($10,871)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ILLINOIS | UNITED STATES | 171005 | Battalion Maintenance Shelter |  | 2012-09-24 | 2012-09-24 | H&N Construction | W91SMC-10-2-2005 | 1210 | 999 | 2012-10-01 | 2013-06-30 | 2013-10-31 | 2014-09-30 | 99% | 0 |  | (Completed - State working on NGB 593)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180012 | JFHQ Add/Alt |  | 2012-09-19 | 2012-09-19 | F.A. WILHELM Construction, Inc. | MDI-SAB-13-C-0012 | 34971 | 34626 | 2012-11-15 | 2014-05-04 | 2013-10-28 | 2014-11-30 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2.000 FY09 {PN: 040026} & Formal Reprogramming $7,271 funds from FY09 project savings {PNs: 040226 ($2,540), 180116 ($3,805), 180137 ($510) and 260211 ($416)}
2014-12-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180142 | Railhead Expansion & Container Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 20908 | 19069 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180156 | Deployment Processing Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 8878 | 8255 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 96% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180160 | Operations Readiness Training Complex 1 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 24991 | 26136 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180161 | Operations Readiness Training Complx 2 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 27000 | 27520 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 220233 | Waste Water Treatment Facility |  | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. | LA12-C-117 | 2972 | 2881 | 2012-06-15 | 2013-07-15 | 2013-06-17 | 2014-12-02 | 99% | 0
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230046 | Readiness Center |  | 2012-04-05 | 2012-09-26 | ITSI Gibane |  | 15584 | 14878 | 2012-09-26 | 2014-07-30 | 2014-07-11 | 2015-05-01 | 72% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230071 | Armed Forces Reserve Center |  | 2012-11-10 | 2012-09-26 | J.C.N. Construction Co, Inc. |  | 22997 | 24162 | 2012-09-26 | 2012-10-26 | 2014-10-12 | 2015-01-26 | 94% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240017 | Readiness Center Add/Alt |  | 2012-08-29 | 2012-09-11 | The Whiting-Turner Contracting Company | 001B3400152 | 15771 | 12055 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2014-12-10 | 48% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240187 | Readiness Center Add/Alt |  | 2012-07-23 | 2012-09-11 | Harkins Builders | 001B3400154 | 10296 | 8075 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2015-01-16 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240193 | Readiness Center |  | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 001B3400155 | 9000 | 9998 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2015-06-22 | 25% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250135 | Readiness Center |  | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc. | MIL1001-DC1 | 8986 | 9630 | 2012-12-01 | 2013-11-18 | 2013-10-28 | 2014-10-28 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250178 | J-1 Range North Pump and Treat Facility |  | 2012-10-25 | 2012-11-15 | Tetra Tech/Mead & Hunt JV | DACW33-03-D-0006 | 2504 | 2394 | 2013-03-04 | 2013-10-21 | 2013-10-21 | 2014-10-21 | 12% | 0 |  | Used FY13 funds
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270266 | Multipurpose Machine Gun Range |  | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. | WGO010008 | 4718 | 4477 | 2012-09-17 | 2014-01-18 | 2013-12-15 | 2014-06-01 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,718)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280315 | Troop Housing (ORTC) Ph1 |  | 2012-01-12 | 2012-06-22 | DCD-YATES | W9127Q-12-C-0004 | 20710 | 20041 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,710)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280387 | Deployment Processing Facility |  | 2012-05-31 | 2012-07-11 | Hanco Corporation |  | 9222 | 8803 | 2012-12-01 | 2014-03-19 | 2013-10-16 | 2014-03-19 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($9,222) (NGB 593)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280389 | Operations Readiness Training Complx Ph1 |  | 2012-01-12 | 2012-06-22 | DCD-YATES | W9127Q-12-C-0004 | 24411 | 23621 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($24,411)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310085 | Readiness Center |  | 2012-05-29 | 2012-06-05 | Sampson Construction Company, Inc. |  | 21913 | 18727 | 2012-07-01 | 2013-12-13 | 2013-11-22 | 2014-03-25 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310086 | Readiness Center |  | 2012-04-09 | 2012-04-27 | Boyd Jones Construction |  | 9099 | 10002 | 2012-05-01 | 2013-11-01 | 2013-06-27 | 2014-05-23 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEBRASKA | UNITED STATES | 310142 | CATS Waste Water Treatment Facility |  | 28 Jun1 2 | 2012-08-10 | All Purpose Construction |  | 1536 | 1661 | 2012-09-01 | 2013-10-11 | 2013-09-19 | 2014-04-30 | 98% | 0
2014-12-31 | 2012 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320070 | Field Maintenance Shop |  | 2012-01-12 | 2012-04-17 | CORE Construction |  | 22932 | 21352 | 2012-12-01 | 2013-11-08 | 2013-10-25 | 2014-10-31 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEW HAMPSHIRE | UNITED STATES | 330052 | Readiness Center, Add/Alt |  | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 330052-GC | 1947 | 1943 | 2012-10-07 | 2013-07-29 | 2013-08-13 | 2013-08-13 | 100% | 0 |  | (Closeout procedures are in progress)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340115 | Army Aviation Support Facility |  | 2012-02-15 | 2012-09-19 | Senate Builders & Const Manager | W912KN-12-C-0006 | 48795 | 46170 | 2012-09-19 | 2015-01-31 | 2014-10-18 | 2015-01-31 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350115 | Readiness Center, Add/Alt |  | 2012-01-03 | 2012-04-10 | Jaynes Corporation | 12-08-0000-1219 | 5172 | 4440 | 2012-12-01 | 2013-07-13 | 2013-06-01 | 2013-06-01 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370899 | Readiness Center, Add/Alt |  | 2012-09-04 | 2012-09-04 | Holden Building Company, Inc. | W9123210220004 | 3680 | 3457 | 2012-12-01 | 2013-12-02 | 2013-10-28 | 2013-12-02 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400605 | Upgrade: Combined Arms Collective Training Facility |  | 2012-01-12 | 2012-08-16 | Benham Companies, LLC | W90FYQ-09-D-0006-9J01 | 10343 | 9308 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2015-01-16 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400606 | Live Fire Shoot House |  | 2012-01-24 | 2012-08-15 | Benham Companies, LLC | W90FYQ-09-D-0006-9J02 | 2995 | 3149 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-06-28 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410026 | Readiness Center |  | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 410026D002 | 13800 | 13190 | 2012-12-01 | 2014-02-21 | 2013-12-28 | 2014-03-20 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | PUERTO RICO | UNITED STATES | 430010 | Readiness Center |  | 2012-09-10 | 2012-09-18 | RB Construction Group Inc. | W912LR-12-C-0005 | 40565 | 38259 | 2012-12-01 | 2014-12-05 | 2013-10-28 | 2014-11-19 | 17% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($40,565)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450403 | Readiness Center, Add/Alt |  | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. |  | 4290 | 4255 | 2012-10-01 | 2013-09-01 | 2013-10-28 | 2013-10-28 | 10% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490618 | Multi-Purpose Machine Gun Range |  | 2012-09-06 | 2012-09-27 | Cracar Construction | W911YP-12-C-0007 | 6498 | 6577 | 2012-12-01 | 2014-01-06 | 2013-10-28 | 2013-10-28 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | VIRGINIA | UNITED STATES | 510307 | Combined Arms Collective Training Facility |  | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | W912LQ-13-C-0001 | 10912 | 8799 | 2013-04-01 | 2014-10-09 | 2014-10-09 | 2015-01-30 | 77% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540085 | Readiness Center Ph1 |  | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | DEK 13002 | 9991 | 11545 | 2012-11-01 | 2014-08-25 | 2014-11-12 | 2014-11-12 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550245 | Tactical Unmanned Aircraft System Facility |  | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. | NGB-47-12-C-0002 | 4250 | 3986 | 2012-07-01 | 2013-10-20 | 2013-05-20 | 2014-05-30 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 011007 | National Guard Readiness Center, Add/Alt |  | 2013-09-24 | 2013-09-26 | Butler Construction Company, LLC. | AC-13-B-0051-S | 1920 | 1904 | 2014-02-03 | 2015-04-24 | 2015-04-24 | 2014-10-01 | 0% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010278 | Live Fire Shoot House |  | 2013-08-01 | 2013-08-23 | Hurst Construction, LLC | AC-13-C-0052-S | 5223 | 5382 | 2013-09-23 | 2014-08-15 | 2014-08-15 | 2014-08-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 040669 | Underground Electrical Lines |  | 2013-09-23 | 2014-04-04 | Ludvik Electric | M13-0037 | 2000 | 1833 | 2014-05-05 | 2014-10-31 | 2014-10-31 | 2014-10-31 | 0% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050139 | Field Maintenance Shop |  | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC | 9751312 | 6577 | 5231 | 2013-08-30 | 2014-10-27 | 2014-10-01 | 2014-10-01 | 94% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060413 | Maneuver Area Training & Equipment Site Ph 3 |  | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793 | 30449 | 2013-10-21 | 2014-10-01 | 2014-10-01 | 2015-09-30 | 67% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 (1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090043 | Combined Support Maintenance Shop |  | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951 | 29441 | 2014-04-26 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 35% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090115 | RIP RAP |  | 2014-08-28 | 2014-09-11 | Nutmeg Companies, Inc. | W91ZRS-12-D-0026-0005 | 3600 | 1292 | 2014-09-22 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 20% | 0 |  | 11 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 450252)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100010 | Regional Training Institute Ph1 |  | 2013-06-28 | 2013-07-05 | EDIS Company | 40452 | 5319 | 5265 | 2013-09-23 | 2014-10-20 | 2014-10-01 | 2014-12-23 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120102 | Readiness Center |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) |  | 19345 | 21104 | 2014-03-03 | 2015-02-20 | 2015-02-20 | 2015-09-13 | 60% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120192 | Upgrade: Combined Arms Collective Training Facility |  | 2013-06-07 | 2013-06-25 | Thomas May Construction Company |  | 8705 | 6452 | 2013-10-04 | 2014-10-20 | 2014-10-01 | 2014-10-01 | 2% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120228 | Ready Building |  | 2013-09-05 | 2013-09-10 | Halfacre Construction Company |  | 1939 | 1920 | 2013-10-14 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 0% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | GUAM | GUAM | 140040 | JFHQ Ph 4 |  | 2013-08-22 | 2013-09-24 | NAVFAC Pacific | N40192-10-D-2800 | 8221 | 8089 | 2013-10-21 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150023 | Army Aviation Support Facility Ph1 |  | 2013-11-13 | 2014-09-11 | USPFO - HI | W912J6-14-R-00001 | 35078 | 33472 | 2014-09-22 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2014-12-31 | 2013 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160100 | ORTC (Barracks) Ph2 |  | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692 | 37607 | 2013-10-07 | 2014-08-01 | 2014-08-01 | 2015-12-10 | 34% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180106 | Field Maintenance Shop |  | 2013-09-24 | 2013-09-24 | Gamong Construction | MDI-SAB-14-C-0002 | 8705 | 8481 | 2014-07-21 | 2014-12-25 | 2014-12-25 | 2015-05-30 | 40% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180144 | Armed Forces Reserve Center Add/Alt |  | 2013-09-20 | 2013-09-20 | Ziolkowski Construction | MDI-SAB-14-C-0001 | 20311 | 22016 | 2014-04-21 | 2015-05-29 | 2015-08-23 | 2015-05-29 | 21% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | IOWA | UNITED STATES | 190142 | Urban Assault Course |  | 2013-05-29 | 2013-06-07 | Rochon Corporation of Iowa | C751SI088 | 2902 | 2545 | 2013-08-09 | 2014-05-30 | 2014-04-30 | 2014-05-30 | 100% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200102 | Taxiway, Ramp & Hangar Alterations |  | 2013-05-21 | 2013-06-14 | Senne & Co |  | 9188 | 8555 | 2013-07-22 | 2014-05-02 | 2014-10-01 | 2014-07-04 | 70% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | KANSAS | UNITED STATES | 200127 | Water Distribution Lines, Portable |  | 2013-09-16 | 2013-09-24 | Harbin Construction | W912JC-12-D-5308 | 1440 | 1445 | 2014-04-07 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 75% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210001 | Army Aviation Support Facility |  | 2013-05-17 | 2013-06-04 | DW Wilburn | CT2 1300000269 | 30953 | 26217 | 2013-07-08 | 2014-11-10 | 2014-10-01 | 2014-10-01 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220241 | National Guard Readiness Center |  | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300 | 8937 | 2014-09-22 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 1% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353 )
2014-12-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220243 | Jackson Barracks Billeting Replacement |  | 2013-07-25 | 2014-07-25 | Gibbs Construction | LA06-C-081 | 5700 | 3817 | 2014-07-25 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 99% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $3,000 - PN: 450252, $2,700 - PN: 450353)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 240194 | Combat Pistol/MP Firearms Qualification Course |  | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 1920 | 1740 | 2014-04-21 | 2014-09-22 | 2014-09-22 | 2014-09-22 | 1% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250065 | Unit Training Equipment Site |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279 | 21219 | 2014-04-07 | 2015-07-30 | 2015-07-30 | 2015-10-15 | 23% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250196 | Water Well, Non-Potable |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District |  | 2000 | 1838 | 2013-06-03 | 2013-12-02 | 2013-12-01 | 2013-12-01 | 0% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270236 | Scout Reconnaissance Range |  | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. | 67879 | 12783 | 13274 | 2013-09-23 | 2015-08-01 | 2015-10-01 | 2016-01-01 | 62% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270238 | Readiness Center |  | 2013-08-08 | 2013-08-14 | LS Black Constructors | W912LM-13-C-0007 | 16443 | 17496 | 2013-09-30 | 2015-10-15 | 2015-10-15 | 2015-10-28 | 44% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290176 | Regional Training Institute |  | 2013-07-26 | 2013-08-01 | KCI Construction Company | T1203-01B | 17410 | 15810 | 2013-12-09 | 2015-02-28 | 2015-02-28 | 2015-07-21 | 69% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290215 | Readiness Center Add/Alt |  | 2013-09-10 | 2013-09-17 | Larrison Construction Inc. | T1206-01 | 1837 | 1857 | 2013-09-30 | 2014-07-18 | 2014-06-30 | 2014-11-20 | 100% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | MONTANA | UNITED STATES | 300032 | Readiness Center |  | 2013-04-21 | 2013-06-24 | Jackson Contractor Group, Inc. | W9124V-06-2-2001 | 11606 | 12421 | 2013-07-08 | 2014-12-15 | 2015-01-09 | 2015-01-21 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340110 | Regional Training Institute |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885 | 31977 | 2014-10-15 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 10% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340130 | Communication Lines and Ductbank, Underground |  | 2014-09-19 | 2014-09-26 | Rome Management Associates, LLC | W912KN-13-D-0029 | 2228 | 1457 | 2014-10-03 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 1% | 0 |  | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition |  | 2014-08-18 | 2014-09-24 | Smithco Inc. | AGND14-52 | 1194 | 2000 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 1% | 0
2014-12-31 | [10 empty] | Peterson Mechanical, Inc. | AGND14-53 | 468
2014-12-31 | [10 empty] | Grotberg Electrical, Inc. | AGND14-54 | 311
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380123 | RIP RAP |  | 2013-09-02 | 2013-12-02 | Close Construction Company | AGND14-01 | 1688 | 1889 | 2013-12-09 | 2014-08-30 | 2014-08-30 | 2015-06-30 | 77% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390230 | Readiness Center |  | 2013-04-01 | 2013-05-03 | Barton Marlow Company | Construction ADJ-090001 | 11607 | 8736 | 2013-08-01 | 2014-01-10 | 2013-12-01 | 2014-11-18 | 99% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Air National Guard | Major Military Construction | OHIO | UNITED STATES | 390256 | Field Maintenance Shop Add/Alt |  | 2013-06-07 | 2013-09-19 | Henderson Contractors, Inc. | W91364-13-Q-0003 | 1998 | 2943 | 2013-11-04 | 2014-10-28 | 2014-07-02 | 2014-12-01 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390263 | Hutments |  | 2014-05-12 | 2014-07-09 | USPFO - OH | USPFO - OH | 2900 | 2662 | 2014-07-16 | 2015-06-15 | 2015-06-15 | 2015-06-15 | 35% | 0 |  | 11 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400066 | Operations Readiness Training Complex |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29197 | 27536 | 2013-10-25 | 2014-10-01 | 2014-10-01 | 2016-02-22 | 19% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 420542 | Controlled Access Secure Facility |  | 2014-07-09 | 2014-10-24 | Miller Bros. Construction, Inc. | W912KC-14-R-0005 | 1825 | 1896 | 2014-10-30 | 2015-11-13 | 2015-11-13 | 2015-11-13 | 0% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430081 | Readiness Center (JFHQ) |  | 2013-06-27 | 2013-09-26 | R B Construction Group Inc. | W912LR-13-C-0001 | 18294 | 17609 | 2014-03-03 | 2015-09-18 | 2015-09-18 | 2015-09-25 | 23% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | PUERTO RICO | 430622 | Sanitary Sewer |  | 2014-04-04 | 2014-08-27 | Integrated Construction Services, Inc. | W912LR-14-B-2005 | 1535 | 1897 | 2014-09-15 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430804 | Refill Station Building |  | 2013-06-25 | 2013-09-20 | Design Build S E |  | 2128 | 2577 | 2013-10-28 | 2015-05-08 | 2015-05-08 | 2015-05-08 | 0% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430806 | Readiness Center |  | 2013-06-06 | 2013-09-26 | Design Build S E |  | 3675 | 3643 | 2014-02-10 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 0% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490076 | BEQ Facility (Regional Training Institute) |  | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 137861 | 14508 | 15765 | 2013-08-12 | 2014-11-10 | 2014-10-01 | 2014-11-30 | 75% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490444 | Regional Training Institute Ph2 |  | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 137862 | 28772 | 28259 | 2013-08-26 | 2014-09-30 | 2014-09-30 | 2015-03-30 | 72% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | UTAH | UNITED STATES | 490803 | Unheated Aircraft Storage Hangar |  | 2013-11-06 | 2014-07-18 | Keller Construction Inc. | 147589 | 2000 | 1889 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 0% | 0
2014-12-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530015 | Readiness Center |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | USACE Construction Contract | 33853 | 30300 | 2013-09-23 | 2015-10-26 | 2015-08-20 | 2015-08-27 | 19% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530035 | National Guard Readiness Center |  | 2014-08-15 | 2014-08-20 | Absher Construction | Absher Construction | 26000 | 23820 | 2014-10-06 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 0% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540075 | Readiness Center |  | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734 | 14988 | 2014-04-07 | 2015-09-11 | 2015-09-11 | 2015-09-11 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550142 | Field Maintenance Shop |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673 | 9180 | 2013-10-28 | 2014-10-01 | 2014-10-01 | 2015-04-15 | 25% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | WISCONSIN | UNITED STATES | 550161 | National Guard Readiness Center Addition |  | 2013-09-24 | 2013-09-25 | Miron Construction | NGB-47-13-C-0009 | 1920 | 909 | 2013-12-12 | 2014-09-01 | 2015-07-01 | 2014-08-01 | 80% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 011014 | National Guard Readiness Center Add/Alt |  | 2014-08-14 | 2014-08-19 | Carmon Construction, Inc. | AC-14-C-0045-S | 4000 | 3756 | 2014-10-06 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050182 | Scout REECE Gunnery Complex |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-B-0001 | 21000 | 16758 | 2014-10-20 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120195 | Ready Building |  | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | 120195 D-B Kokolakis | 5700 | 5300 | 2014-04-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170033 | National Guard Readiness Center |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2004-100 | 14000 | 16000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170127 | Aircraft Maintenance Hangar |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2003-100 | 28000 | 30000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250095 | Enlisted Barracks, Transient Training Addition |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000 | 20559 | 2014-09-15 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260051 | Enlisted Barracks, Transient Training |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000 | 17398 | 2014-08-11 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270014 | National Guard Readiness Center |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000 | 17943 | 2014-10-22 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 281305 | Raw Sewage Lagoon and Oxidation Pond |  | 2014-09-24 | 2014-09-26 | Miller Enterprises |  | 1950 | 1039 | 2014-09-30 | 2005-04-30 | 2015-04-30 | 2015-04-30 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280272 | National Guard Readiness Center |  | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB-22-14-C-0003-S | 4500 | 4718 | 2014-07-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280423 | Water Supply/Treatment Building, Potable |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000 | 2581 | 2014-08-15 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290191 | National Guard Vehicle Maintenance Shop |  | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01C | 9100 | 7355 | 2015-05-12 | 2012-04-30 | 2015-07-31 | 2015-06-26 | 30% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290221 | Aircraft Maintenance Hangar |  | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 5000 | 4399 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360161 | National Guard Readiness Center Alteration |  | 2014-09-17 | 2014-09-30 | Design Resources Group Architects, A.I.A, Inc. |  | 31000 | 29608 | 2014-10-20 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390292 | Sanitary Sewer |  | 2014-04-04 | 2014-09-04 | USPFO - OH | W91364-13-D-0003 | 5200 | 4974 | 2014-09-08 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 30% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420051 | Aircraft Maintenance Instructional Building |  | 2014-08-29 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 40000 | 31940 | 2014-10-20 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430070 | Maneuver Area Training & Equipment Site Addition |  | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600 | 4418 | 2014-09-15 | 2015-05-30 | 2015-05-30 | 2015-05-30 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450131 | National Guard Vehicle Maintenance Shop |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | 460003 | 13000 | 12400 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450283 | National Guard Readiness Center |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | 460003 | 13000 | 12401 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-12-31 | 2014 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560081 | National Guard Readiness Center |  | 2013-12-16 | 2014-03-11 | Layton Construction Company, Inc. | 13002900601 | 10200 | 9748 | 2013-10-10 | 2015-03-31 | 2015-03-31 | 2015-08-31 | 25% | 0
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146136 | BACHELOR ENLISTED QUARTERS |  | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | N4008511C4026 AWD | 42882 | 42014 | 2011-06-16 | 2015-03-31 | 2013-07-07 |  | 82%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146148 | MISSILE MAGAZINE |  | 2010-10-21 | 2011-06-02 | SAUER, INC. | N4008511C4010 P00003 | 4779 | 4779 | 2011-06-16 | 2014-01-23 | 2012-07-10 |  | 97%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND |  | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091 | 27567 | 2013-09-19 | 2016-02-24 | 2016-01-18 | 2016-02-24 | 28%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146164 | MARINER'S BAY LAND ACQUISITION BOGUE |  |  | 2011-07-01 | NAVY STANDARD DOCUMENT | N4008509RP00103 | 4002 | 3706 | 2011-07-15 |  |  |  | 93%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146176 | STATION INFRASTRUCTURE UPGRADES |  | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | N4008510D0261 0003 | 5850 | 7300 | 2011-06-15 | 2013-10-10 | 2012-11-25 | 2013-10-10 | 100%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146601 | ARMORY |  | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0006 | 11782 | 11291 | 2013-09-19 | 2015-04-20 | 2015-04-08 | 2015-04-20 | 60%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY |  | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0003 | 14067 | 17408 | 2012-03-29 | 2014-04-29 | 2013-08-14 |  | 94%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243313 | ENTRY CONTROL POINT (GATE 5) |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974 | 10298 | 2014-01-03 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 11%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | N6247310D5480 0012 | 9928 | 9373 | 2011-06-17 | 2012-06-15 | 2012-06-17 |  | 98%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M00263382 | FRONT GATE AT/FP IMPROVMENTS |  | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513 | 10893 | 2013-10-30 | 2015-10-11 | 2015-04-12 | 2015-10-11 | 21%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264541 | ADDITION, MCU RESEARCH CENTER |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 31343 | 29407 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2015-01-02 | 97% | -3531 | Sequestration Reprogramming
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR |  | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0020 | 11118 | 11221 | 2012-09-25 | 2014-10-10 | 2014-03-28 |  | 99%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462 | 28694 | 2013-10-07 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 13%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 |  | 2011-06-20 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 45465 | 34560 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 30% | -8039 | Sequestration Reprogramming
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 |  | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222 | 23827 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 37%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION |  | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | N4008010D0497 0011 | 6555 | 7003 | 2012-08-10 | 2014-09-26 | 2013-09-05 | 2014-12-30 | 76%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL |  | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | N6274209D1174 JU01 | 34087 | 31012 | 2011-10-14 | 2013-09-26 | 2013-08-09 | 2014-04-30 | 100%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264611 | BACHELOR ENLISTED QUARTERS |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 32910 | 31667 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-03-18 | 71%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264612 | ENLISTED DINING FACILITY |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 5028 | 5137 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-03-18 | 91%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264615 | SNCO ACADEMIC FACILITY ADDITION |  | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | N4008010D0493 0002 | 6836 | 6730 | 2011-07-04 | 2013-07-22 | 2012-12-21 |  | 96%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264621 | EMBASSY SECURITY GROUP FACILITIES |  | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081 | 25378 | 2013-03-14 | 2015-08-15 | 2015-03-15 | 2015-03-25 | 45%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264632 | ACADEMIC INSTRUCTION FACILITY |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 60736 | 60203 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2015-01-02 | 95% | -2502 | N47608561
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264644 | WEAPONS TRAINING BATALLION MESS HALL |  | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168 | 12604 | 2013-09-18 | 2015-06-30 | 2015-04-22 | 2015-04-22 | 26%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318006 | PHYSICAL FITNESS CENTER, CAMP SMITH |  | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | N6274209D1171 HC01 | 28891 | 28105 | 2011-06-30 | 2014-04-03 | 2013-03-07 |  | 96%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318816 | WATERFRONT OPERATIONS FACILITY |  | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 0006 | 16634 | 15083 | 2011-07-14 | 2015-01-30 | 2013-11-16 |  | 79%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318822 | MCAS OPERATIONS COMPLEX |  | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 HC01 | 52970 | 51415 | 2012-05-02 | 2014-12-29 | 2014-03-17 | 2014-12-29 | 83%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318852 | 3RD BATTALION COMPLEX |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407 | 17348 | 2014-09-19 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 0%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318858 | BACHELOR ENLISTED QUARTERS |  | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6247811C1492 AWD | 62691 | 60611 | 2011-09-14 | 2015-03-31 | 2014-08-21 | 2014-12-11 | 92% | -17925 | N60191527, N60191582, Sequestration Reprogramming
2014-12-31 | 2014 | Marine Corps Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | M0031886167 | TEMPOARY MEDICAL FACILITY SITE PREPARATION |  |  | 2014-12-22 | CT JV | N6247814D4004 KB01 | 1667 | 1426 | 2015-01-05 |  |  |  | 0%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318864 | AIRCRAFT MAINTENANCE EXPANSION |  | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | N6274214C1315 AWD | 16968 | 15196 | 2014-04-30 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 9%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  | 2014-02-17 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720 | 15145 | 2014-10-14 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 0%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318904 | MV-22 HANGAR AND INFRASTRUCTURE |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 63056 | 55982 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 24%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318905 | AIRCRAFT STAGING AREA |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 11118 | 7008 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 30%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811014 | TRUCK COMPANY OPERATIONS COMPLEX |  | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | N6247311C0405 AWD | 52425 | 50438 | 2011-10-06 | 2015-06-03 | 2013-09-21 | 2015-06-03 | 89%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE |  | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0002-PC000002 | 11746 | 9512 | 2012-04-06 | 2013-08-05 | 2013-01-21 |  | 88% | -760 | N00246909
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811040 | INTERSECTION BRIDGE AND IMPROVEMENTS |  | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | N6247309D1606 0009 | 11432 | 13971 | 2012-09-07 | 2014-05-23 | 2013-09-27 |  | 97%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811043A | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | M006811043 | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | N6247310C5011 PC000001 | 29295 | 25314 | 2010-11-12 | 2015-02-17 | 2012-10-12 | 2015-08-21 | 52%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811044 | CONVEYANCE/WATER TREATMENT |  | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | N6247312C5033 AWD | 98236 | 83152 | 2012-10-13 | 2016-12-06 | 2016-01-13 | 2016-01-13 | 31%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811045 | NEW POTABLE WATER CONVEYANCE |  | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242 | 62016 | 2012-10-12 | 2016-12-21 | 2016-03-31 | 2016-03-31 | 33% | -16682 | N684691400
2014-12-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811046 | NORTH AREA WASTE WATER CONVEYANCE |  | 2014-08-28 | 2014-11-25 | ORION CONSTRUCTION CORPORATION | N6247310D5419 0012 | 75135 | 42482 | 2014-12-09 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 0%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811109 | BACHELOR ENLISTED QUARTERS, LAS FLORES |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 36173 | 33961 | 2011-10-13 | 2014-06-05 | 2013-10-13 |  | 99%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811113 | BACHELOR ENLISTED QUARTERS, 24 AREA |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 41889 | 39164 | 2011-10-13 | 2014-06-05 | 2013-10-13 |  | 99%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811176 | SAN JACINTO ROAD EXTENSION |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428 | 4269 | 2014-10-08 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 1%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811200 | MARINE CORPS ENERGY INITIATIVE |  | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | N6247310D5483 0003 | 9779 | 9567 | 2011-08-09 | 2013-06-21 | 2012-08-04 | 2014-01-16 | 100%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681310 | SMALL ARMS MAGAZINE, EDSON RANGE |  | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | N6247309D1618 0004 | 3760 | 3188 | 2011-06-21 | 2014-10-27 | 2012-07-06 | 2015-01-21 | 85%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681532 | ARMORY, 1ST MARINE DIVISION |  | 2012-04-23 | 2012-08-31 | A&D GC INC | N6247309D1658 0006 | 11201 | 10463 | 2012-09-14 | 2014-04-23 | 2013-12-24 |  | 99%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169420 | PHYSICAL FITNESS CENTER, BEAUFORT |  | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | N6945011C1760 AWD | 14780 | 14868 | 2011-09-21 | 2013-05-24 | 2013-06-08 | 2013-07-16 | 100%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169427 | GROUND SUPPORT EQUIPMENT SHOP |  | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | N6945013D1761 0001 | 10936 | 10661 | 2013-08-22 | 2015-01-16 | 2014-08-07 | 2014-12-12 | 57%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169442 | VERTICAL LANDING PADS FOR F-35B |  | 2011-12-06 | 2012-03-30 | HEAD, INC. | N6945012C1758 AWD | 18987 | 18046 | 2012-04-13 | 2013-10-21 | 2013-08-07 |  | 95%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169444 | TRAINING AND SIMULATOR FACILITY |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 40940 | 38701 | 2011-06-20 | 2014-06-17 | 2014-03-11 |  | 99%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169454 | F-35B AIRCRAFT HANGAR FOR FRS-2 |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 45398 | 45872 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 100%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169456 | SIMULATED LHD FLIGHT DECK |  | 2012-08-27 | 2013-06-26 | HEAD, INC. | N6945013C1773 AWD | 12302 | 11951 | 2013-07-10 | 2014-11-28 | 2014-07-11 |  | 93%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  | 2014-08-06 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643 | 36401 | 2014-08-29 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 1%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169472 | AIRFIELD SECURITY UPGRADES |  | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | N6945013C1772 AWD | 11043 | 12576 | 2013-07-15 | 2014-10-28 | 2014-03-28 |  | 89%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204925 | DIP TANK CLEANING FACILITY |  | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | N6247309D1616 0009 | 7970 | 7879 | 2012-04-04 | 2014-09-18 | 2013-09-27 |  | 92%
2014-12-31 | 2011 | Marine Corps Reserve | Military Family Housing Improvement |  | JAPAN | M626130501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 |  | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | N4008411C5504 AWD | 11626 | 11102 | 2011-10-06 | 2013-02-28 | 2013-01-14 | 2013-02-28 | 100%
2014-12-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 |  | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | N4008412D6501 0002 | 13357 | 12685 | 2012-08-13 | 2013-12-13 | 2013-11-23 | 2013-12-14 | 100%
2014-12-31 | 2013 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 |  | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | N4008414C5500 AWD | 17551 | 16715 | 2014-06-22 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 0%
2014-12-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626131001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 |  | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | N4008412D6501 0004 | 11335 | 10876 | 2012-08-14 | 2015-02-02 | 2014-12-20 | 2015-02-02 | 74.79%
2014-12-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 |  | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545 | 15632 | 2014-10-13 | 2016-02-02 | 2016-02-02 | 2016-02-02 | 0%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613995 | MAINTENANCE HANGAR IMPROVEMENTS |  | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT | N6274214MP00027 | 4947 | 4926 | 2014-06-06 | 2015-06-14 | 2015-06-14 | 2015-06-14 | 0%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH |  | 2014-04-07 | 2014-07-25 | NAVY STANDARD DOCUMENT | N6274214MP00039 | 6304 | 6304 | 2014-08-08 | 2015-09-24 | 2015-09-24 | 2015-09-24 | 0%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974378 | SECURITY OPERATIONS COMPLEX |  | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316 | 13478 | 2013-11-14 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 6%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974447A | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 30492 | 29300 | 2011-06-23 | 2013-12-05 | 2012-10-08 |  | 98%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 47715 | 46237 | 2011-06-23 | 2013-12-05 | 2012-10-08 |  | 99%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974533 | SIMULATOR FACILITY (JSF) |  | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0002 | 26438 | 23252 | 2011-06-17 | 2013-03-05 | 2012-06-02 |  | 99%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974535 | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | N6247308D8617 0004 | 32048 | 31780 | 2012-09-20 | 2014-08-06 | 2014-07-07 | 2015-01-01 | 99% | -5983 | N684691400
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0003 | 79917 | 78061 | 2012-04-03 | 2014-06-24 | 2014-05-20 |  | 98%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974546 | UTILITY UPGRADES (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 40106 | 36761 | 2011-06-21 | 2013-06-14 | 2012-07-08 |  | 99%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974566 | COMBAT AIRCRAFT LOADING APRON |  | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247309D1603 0013 | 12671 | 11791 | 2013-10-11 | 2015-03-02 | 2014-09-22 | 2015-03-02 | 31%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) |  | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0002 | 19793 | 16188 | 2011-08-10 | 2012-12-14 | 2012-07-25 |  | 99%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974575 | AUXILIARY LANDING FIELD (JSF) |  | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | N6247312C1802 AWD | 29475 | 28521 | 2012-07-09 | 2014-02-21 | 2013-06-25 |  | 94% | -5128 | N42237636
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974578 | VAN PAD RELOCATION (JSF) |  | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | N6247309D1653 0003 | 15045 | 14670 | 2011-09-26 | 2013-01-22 | 2012-09-11 | 2012-09-11 | 100%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 54843 | 54497 | 2011-06-21 | 2013-06-14 | 2012-07-08 |  | 93%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001003 | STAFF NCO ACADEMY FACILITIES |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260 | 27824 | 2013-09-19 | 2015-11-08 | 2015-09-01 | 2015-11-08 | 34%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC |  | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | N4008510D5329 0002 | 12906 | 12849 | 2011-06-16 | 2015-02-06 | 2012-12-01 |  | 94%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001030 | SQUAD BATTLE COURSE |  | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0003 | 16292 | 14381 | 2012-07-05 | 2014-12-01 | 2014-05-17 |  | 83%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011034 | 2ND INTEL BN OPERATIONS COMPLEX |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 79767 | 80482 | 2011-07-13 | 2015-04-30 | 2014-02-28 | 2014-12-15 | 94%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 32625 | 30659 | 2011-07-13 | 2015-04-30 | 2014-02-28 | 2014-12-15 | 93%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP |  | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | N4008510D0259 0007 | 6613 | 6017 | 2011-07-11 | 2013-05-13 | 2012-08-20 |  | 92%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 43950 | 40294 | 2011-07-13 | 2015-04-11 | 2013-07-13 | 2013-07-13 | 100%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 40236 | 38214 | 2011-09-14 | 2015-02-15 | 2013-10-08 | 2014-06-24 | 100%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER |  | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | N4008512C7719 AWD | 74707 | 72332 | 2012-05-14 | 2015-03-12 | 2014-07-24 | 2015-02-19 | 90%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 39788 | 37917 | 2011-09-14 | 2015-02-15 | 2013-10-08 |  | 99%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011256 | MESS HALL ADDITION, COURTHOUSE BAY |  | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0006 | 1499 | 1379 | 2011-06-16 | 2012-11-25 | 2012-11-25 |  | 98%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011264 | UTILITY EXPANSION, HADNOT POINT |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 55206 | 55212 | 2011-10-10 | 2014-09-16 | 2013-10-22 |  | 92%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011265 | UTILITY EXPANSION, FRENCH CREEK |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 54795 | 46483 | 2011-10-10 | 2014-09-16 | 2013-10-22 |  | 97%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011267 | MESS HALL, FRENCH CREEK |  | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | N4008511C4022 AWD | 24316 | 17444 | 2011-06-16 | 2014-03-07 | 2013-02-06 |  | 65%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE |  | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | N4008511C4008 AWD | 54720 | 55088 | 2011-09-13 | 2015-03-31 | 2013-09-07 |  | 95%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4021 AWD | 43568 | 40944 | 2011-06-16 | 2015-01-04 | 2013-08-30 | 2015-01-04 | 99%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4020 AWD | 46005 | 42198 | 2011-06-16 | 2014-08-29 | 2013-08-13 | 2014-04-14 | 100%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 49005 | 44550 | 2011-07-13 | 2015-03-02 | 2013-07-13 | 2015-04-11 | 97%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011323 | ARMORY II MEF, WALLACE CREEK |  | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | N4008511C4001 P00004 | 5941 | 5402 | 2011-12-20 | 2015-04-11 | 2013-07-13 | 2015-04-11 | 99% | -4148 | M00681159
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011353 | LANDFILL, PHASE 4 |  | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529 | 13776 | 2014-09-08 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 10%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK |  | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101 | 26020 | 2012-07-13 | 2014-12-15 | 2014-07-29 |  | 96%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011383 | BASE ENTRY POINT AND ROAD |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235 | 62533 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 69%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011384 | BASE ACCESS AND ROAD, PHASE 3 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666 | 28713 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 52%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-10-08 | 2011-05-31 | URS-IAP LLC | N6247006D6009 0016-02 | 8868 | 8147 | 2011-06-14 | 2012-12-06 | 2012-09-27 |  | 98%
2014-12-31 | 2012 | Marine Corps Active | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | M670011425 | OVERHEAD RANGE BAFFLE SYSTEM |  | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008511D8026 0008 | 2297 | 2215 | 2013-03-06 | 2014-12-30 | 2014-04-17 |  | 96%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312 | 13160 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 4%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001683 | HANGAR |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62154 | 59440 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 93%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001687 | MV-22 MAINTENANCE HANGAR (HMLA) |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62617 | 59662 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 92%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001705 | AIRCRAFT MAINTENANCE HANGAR AND APRON |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 57582 | 64265 | 2012-06-12 | 2015-02-19 | 2014-07-07 | 2015-02-19 | 98%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001710 | ORDNANCE LOADING AREA ADDITION |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 7768 | 7376 | 2012-06-12 | 2015-02-19 | 2014-07-07 | 2015-02-19 | 90%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001711 | PERSONNEL ADMINISTRATION CENTER |  | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0018 | 6449 | 5394 | 2013-09-20 | 2015-07-06 | 2015-07-06 | 2015-07-06 | 54%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001726 | REGIONAL COMMUNICATION STATION |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159 | 10019 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 3%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  | 2013-12-06 | 2014-09-10 | BLUEFORGE, LLC | N6945014D1271 0001 | 14685 | 14300 | 2014-09-24 | 2016-01-25 | 2016-01-25 | 2016-01-25 | 0%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004954 | CERS DISPATCH FACILITY |  | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | N6945012D1769 0005 | 1248 | 1157 | 2014-06-16 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 23%
2014-12-31 | 2011 | Marine Corps Active | Military Family Housing Improvement | DISTRICT OF COLUMBIA | UNITED STATES | M670291101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 |  | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0001-07 | 41 | 39 | 2011-01-28 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 100%
2014-12-31 | 2014 | Marine Corps Reserve | Major Military Construction | MISSOURI | UNITED STATES | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019 | 15845 | 2014-09-05 | 2016-02-23 | 2016-02-23 | 2016-02-23 | 0.7617%
2014-12-31 | 2011 | Marine Corps Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | M67399092 | TANK VEHICLE MAINTENANCE FACILITY |  | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | N6247309D1615 0041 | 6458 | 6168 | 2011-10-06 | 2013-03-11 | 2012-09-21 | 2013-03-28 | 99.9%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE |  | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | N6247310C5007 PC000001 | 51987 | 51426 | 2011-06-17 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 100%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA |  | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819 | 20055 | 2012-08-27 | 2016-02-15 | 2014-09-02 | 2016-05-03 | 19%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399212 | CHILD DEVELOPMENT CENTER |  | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | N6247310D5412 0006 | 21313 | 20429 | 2012-06-19 | 2015-05-19 | 2013-12-12 | 2015-05-19 | 38%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399541 | MULTI-PURPOSE BUILDING ADDITION |  | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | N6247309D1655 0003 | 15610 | 13793 | 2012-10-11 | 2014-04-20 | 2014-04-20 |  | 47%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction |  | JAPAN | M67400201 | AIRFIELD SECURITY UPGRADES |  | 2013-11-08 | 2014-04-18 | NAVY STANDARD DOCUMENT | N6274214MP00024 | 2881 | 2861 | 2014-05-02 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 4%
2014-12-31 | 2013 | Marine Corps Active | Unspecified Minor Military Construction |  | JAPAN | M67400305 | DEMOLISH 45 HOUSING UNITS, KISHABA HOUSING |  | 2013-07-10 | 2014-09-25 | NAVY STANDARD DOCUMENT | N6274214MP00043 | 1729 | 1719 | 2014-10-09 | 2015-06-29 | 2015-06-29 | 2015-06-29 | 0%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604109 | CNAT/FRS AVIATION TRAINING AND BEQ |  | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0434 AWD | 51999 | 45733 | 2011-09-26 | 2014-06-23 | 2014-01-08 |  | 98% | -11300 | N61151162, Sequestration Reprogramming
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604111 | MALS-39 MAINTENANCE HANGAR EXPANSION |  | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | N6247310D5409 0003 | 47061 | 33366 | 2011-07-06 | 2013-10-29 | 2013-03-13 |  | 86%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604113 | MV-22 AVIATION SIMULATOR BUILDING |  | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | N6247309D1619 0008 | 4380 | 4083 | 2013-06-27 | 2014-09-18 | 2014-09-21 |  | 98%
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604114 | MV-22 DOUBLE HANGAR REPLACEMENT |  | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0004 | 40539 | 38834 | 2012-08-03 | 2015-12-14 | 2015-08-10 | 2015-08-10 | 44% | -6761 | N684691400
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604116 | MV-22 AVIATION PAVEMENT |  | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | N6247309D1605 0012 | 14938 | 9645 | 2012-07-26 | 2015-03-30 | 2014-01-03 |  | 72% | -856 | N684691400
2014-12-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604117 | MV-22 AVIATION FUEL STORAGE |  | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | N6247007D7000 FZN7 | 7437 | 7216 | 2013-11-21 |  | 2013-10-07 | 2015-10-07 | 29%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695005 | PAINT AND BLAST FACILITY |  | 2011-04-29 | 2011-09-16 | SAUER, INC. | N6945009D1277 0005 | 20345 | 19808 | 2011-09-30 | 2014-03-10 | 2013-05-16 |  | 97%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695012 | CONTAINER STAGING AND LOADING LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3380 | 2529 | 2011-06-17 | 2013-12-05 | 2013-12-05 |  | 73%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695017 | HARDSTAND EXTENSION |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 12623 | 7904 | 2011-06-17 | 2013-12-05 | 2013-12-05 |  | 94%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695022 | CONSOLIDATED WAREHOUSE FACILITY |  | 2010-11-22 | 2011-06-03 | SAUER, INC. | N6945009D1277 0003 | 13295 | 11139 | 2011-06-17 | 2013-12-20 | 2012-07-27 | 2013-12-20 | 100%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695023 | WASHRACK EXPANSION |  | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | N6945011D1259 0002 | 8877 | 8449 | 2011-06-15 | 2013-06-10 | 2012-11-19 |  | 96%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695024 | CONTAINER STORAGE LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3702 | 3369 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 100%
2014-12-31 | 2012 | Marine Corps Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  |  | 2012-01-04 |  |  | 0 | 45 | 2012-01-18 |  | 2012-01-31 | 2012-01-31 | 100% |  |  | Awarded by Other Agency
2014-12-31 | 2014 | Navy Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611407 | SITE IMPROVEMENTS - GENERAL OFFICERS QUARTERS A |  |  | 2014-09-30 | QUALITY SUPPORT SERVICES, INC. | N4008314D1014 0003 | 75 | 64 | 2014-10-14 |  | 2014-11-30 | 2015-03-31 | 0%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865152 | PARKING APRON/TAXIWAY EXPANSION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 32816 | 35427 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | -28591 | N50092499, N60191527, Design, N47608561
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865181 | HANGAR 5 RENOVATIONS & ADDITION |  | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0002 | 13634 | 12826 | 2013-09-27 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 8%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865185 | HANGAR 4 ADDITION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 27121 | 27749 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | -4000 | M00681159, Design
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865192 | GTF-HANGAR MODIFICATION (HMT-302) |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 56417 | 54528 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | -30605 | N50092499, Design
2014-12-31 | 2012 | Marine Corps Reserve | Major Military Construction | TENNESSEE | UNITED STATES | M68479030 | RESERVE CENTER TRAINING CENTER - MEMPHIS |  | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | N4008313C0019 AWD | 9006 | 8500 | 2013-04-19 | 2015-01-26 | 2014-10-11 | 2015-01-15 | 68.75%
2014-12-31 | 2011 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | M68479060 | MARINE CORPS RESERVE CENTER |  | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0005 | 14630 | 14194 | 2011-10-11 | 2014-04-15 | 2013-02-08 | 2014-03-01 | 100%
2014-12-31 | 2013 | Marine Corps Reserve | Major Military Construction | NEW YORK | UNITED STATES | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY |  | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911 | 4764 | 2013-09-19 | 2015-11-04 | 2014-12-04 | 2014-12-04 | 14.38%
2014-12-31 | 2012 | Navy Active | Major Military Construction | ILLINOIS | UNITED STATES | N00128816 | DECENTRALIZE STEAM SYSTEM |  | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491 | 62556 | 2012-06-27 | 2015-11-06 | 2015-11-06 | 2015-11-06 | 60%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N00204791 | HVAC JOINT AVIATION SURVIVAL TRAINING |  | 2012-07-25 | 2012-09-29 | R L BURNS INC. | N6945012C6343 AWD | 2038 | 1975 | 2012-10-13 | 2013-12-19 | 2013-08-08 | 2013-08-08 | 100%
2014-12-31 | 2011 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | N00206477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY |  | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | N6945011C0756 AWD | 13604 | 14491 | 2011-06-17 | 2014-05-07 | 2013-06-07 | 2014-02-12 | 100%
2014-12-31 | 2012 | Marine Corps Reserve | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | N00206501 | MILITARY WORKING DOG FACILITY |  | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | N6945013C5571 AWD | 1286 | 1237 | 2013-08-29 | 2014-06-20 | 2014-05-22 | 2014-06-20 | 100%
2014-12-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207153 | BAMS UAS OPERATOR TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 2851 | 2936 | 2012-07-09 | 2014-03-24 | 2013-12-17 |  | 96% | -1321 | N42237100
2014-12-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207624 | P-8A TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 14194 | 13885 | 2012-07-09 | 2014-03-24 | 2013-12-17 |  | 96% | -11437 | N42237636, N42237100
2014-12-31 | 2013 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207655 | BAMS MISSION CONTROL COMPLEX |  | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | N6945013C1257 AWD | 18180 | 17997 | 2013-08-28 | 2014-12-27 | 2014-12-27 | 2015-02-15 | 36%
2014-12-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION |  | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573 | 5992 | 2014-10-10 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 0%
2014-12-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151 | 13396 | 2014-08-29 | 2016-01-07 | 2016-01-07 | 2016-01-07 | 0%
2014-12-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245327 | BERTHING PIER 12 REPL & DREDGING |  | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | N6247311C2850 AWD | 99132 | 90215 | 2011-10-13 | 2013-10-22 | 2013-10-22 |  | 88% | -1813 | N61151162
2014-12-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245405 | BACHELOR QUARTERS HOMEPORT ASHORE |  | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247311C2804 AWD | 72294 | 69777 | 2011-10-14 | 2013-12-03 | 2013-10-23 |  | 99% | -3179 | N42237100
2014-12-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245500 | LCS TRAINING FACILITY |  | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553 | 40296 | 2013-10-14 | 2015-10-24 | 2015-10-24 | 2016-01-09 | 26% | -10760 | N42237100
2014-12-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246705 | FITNESS CENTER, NORTH ISLAND |  | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | N6247310D5409 0013 | 46630 | 42554 | 2012-08-21 | 2015-07-27 | 2015-03-16 | 2015-07-27 | 72%
2014-12-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246750 | ROTARY HANGAR |  | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | N6247312C1406 P00001 | 64063 | 63857 | 2012-02-14 | 2013-12-10 | 2012-04-16 | 2014-03-11 | 100% | -1557 | N42237100
2014-12-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND |  | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977 | 55669 | 2012-07-17 | 2015-07-09 | 2015-03-30 | 2015-07-09 | 77%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY |  | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | N6247311D0067 0004 | 1816 | 1714 | 2013-02-21 | 2014-10-17 | 2014-01-31 |  | 98%
2014-12-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246909 | H-60S SIMULATOR TRAINING FACILITY |  | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088 | 2830 | 2014-03-14 | 2015-03-15 | 2015-03-15 | 2015-03-15 | 9%
2014-12-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND |  | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904 | 8407 | 2014-08-18 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 0%
2014-12-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620239 | EA-18G FACILITY IMPROVEMENTS |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5004 AWD | 29692 | 25168 | 2014-09-08 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 0%
2014-12-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620245 | EA-18G FLIGHT SIMULATOR FACILITY |  | 2012-08-16 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0009 | 5679 | 5916 | 2013-06-27 | 2014-12-25 | 2014-11-25 | 2015-01-27 | 87%
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction | OREGON | UNITED STATES | N00620246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY |  | 2013-07-26 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | N4425513C7005 AWD | 1120 | 1072 | 2013-10-14 | 2014-09-30 | 2014-09-30 | 2014-12-19 | 75%
2014-12-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620251 | P-8A HANGAR AND TRAINING FACILITIES |  | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5002 AWD | 84889 | 78957 | 2014-08-04 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 1%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N00620257 | HANGAR 11 MODIFICATIONS FOR SEARCH AND RESCUE |  | 2014-06-20 | 2014-09-02 | RORE, INC. | N4425514C8012 | 1424 | 1376 | 2014-09-16 |  |  |  | 28%
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | N32411056 | VPT TEST FACILITY |  | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | N4008510D9450 0006 | 2332 | 2328 | 2013-03-28 | 2013-11-21 | 2013-10-31 |  | 99%
2014-12-31 | 2011 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411068 | ELECTROMAGNETIC SENSOR FACILITY |  | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | N4008511C7231 AWD | 24394 | 26541 | 2011-08-23 | 2014-03-24 | 2013-08-22 |  | 97%
2014-12-31 | 2014 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411103 | HEWITT HALL RESEARCH CENTER |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319 | 12780 | 2014-08-14 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 1%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | N32414203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES |  | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | N4008512C5002 AWD | 1951 | 1838 | 2012-03-16 | 2012-08-28 | 2012-09-13 | 2012-09-13 | 100%
2014-12-31 | 2012 | Navy Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414860 | ARMED FORCES RESERVE CENTER, PITTSBURGH |  | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | N4008312C0005 AWD | 12033 | 12339 | 2012-08-14 | 2014-05-31 | 2014-02-06 | 2014-05-31 | 100%
2014-12-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443383 | CONTROLLED INDUSTRIAL FACILITY |  | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576 | 32343 | 2012-06-14 | 2015-07-31 | 2014-09-28 | 2015-03-23 | 34% | -7621 | N684691400
2014-12-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443516A | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | N32443516 | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | N4008510C3006 P00003 | 68459 | 66000 | 2011-04-14 | 2015-10-02 | 2014-11-22 | 2015-10-02 | 72%
2014-12-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE |  | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374 | 26278 | 2013-12-11 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 16%
2014-12-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A219 | GENERAL WAREHOUSE |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 7716 | 7755 | 2012-04-16 | 2014-10-31 | 2013-12-26 |  | 82%
2014-12-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A227 | ARMORY |  | 2014-03-17 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492 | 4178 | 2014-08-08 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 0%
2014-12-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A912 | PAVE EXTERNAL ROADS |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 3107 | 2761 | 2012-04-16 | 2014-10-31 | 2013-12-26 |  | 82%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A917 | CRITICAL POWER FOR BULDING 200 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1120 | 1120 | 2014-06-05 |  |  |  | 100%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A918 | CRITICAL POWER FOR BUILDING T-130 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1175 | 1175 | 2014-06-05 |  |  |  | 100%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A919 | CRITICAL POWER FOR BLDGS 111, 113 AND 115 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1064 | 1065 | 2014-06-05 |  |  |  | 100%
2014-12-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A921 | UNACCOMPANIED HOUSING |  | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714 | 19531 | 2014-10-15 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 1%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557101A | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 | N41557101 | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | N6274210D1309 JQ01 | 24305 | 19184 | 2013-08-21 | 2015-12-15 | 2015-07-12 | 2015-12-15 | 33%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820 | 57162 | 2014-05-21 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 1%
2014-12-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710 | 48381 | 2014-04-10 | 2016-04-25 | 2016-04-25 | 2016-05-27 | 6%
2014-12-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557J200 | NORTH RAMP UTILITIES II |  | 2014-04-11 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 AWD | 53014 | 47725 | 2014-10-31 | 2016-11-04 | 2016-09-02 | 2016-09-02 | 0%
2014-12-31 | 2014 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249 | 119854 | 2014-09-03 | 2018-06-20 | 2018-06-20 | 2018-04-08 | 3%
2014-12-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237601 | SECURITY ENCLAVE AND VEHICLE BARRIER |  | 2011-12-13 | 2012-03-16 | SAUER, INC. | N6945009D1277 0007 | 37278 | 39684 | 2012-03-30 | 2013-09-07 | 2013-09-07 |  | 92% | -5445 | Sequestration Reprogramming
2014-12-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237620 | WATERFRONT EMERGENCY GENERATORS |  | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | N6945010D1271 0003 | 15010 | 16822 | 2011-09-02 | 2013-05-13 | 2013-05-13 | 2015-02-20 | 97%
2014-12-31 | 2012 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE |  | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167 | 36608 | 2014-05-01 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 4%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  | 2014-08-11 | 2014-09-30 | REILLY CONSTRUCTION, INC | N4008014D3014 AWD | 1453 | 1358 | 2014-10-14 | 2015-04-14 | 2015-05-26 |  | 0%
2014-12-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC |  | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | N4008011C0154 AWD | 33033 | 34715 | 2011-06-16 | 2013-07-31 | 2012-07-30 |  | 99%
2014-12-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 |  | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49890 | 47015 | 2014-07-14 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 6%
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N47609003 | EOD/TEU RANGE SUPPORT FACILITY |  | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | N6247313D4608 0007 | 1896 | 1764 | 2014-06-27 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 7%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092199 | MSRON FOUR BOAT STORAGE BUILDING |  | 2012-10-31 | 2012-12-14 | JESSICO, INC | N4008511D3021 0008 | 970 | 938 | 2012-12-28 | 2013-11-15 | 2013-11-08 | 2013-11-15 | 100%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY |  | 2011-05-26 | 2011-08-03 | JESSICO, INC | N4008511C3026 AWD | 2085 | 1989 | 2011-08-17 | 2012-11-13 | 2012-09-30 |  | 98%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG |  | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008512C7000 AWD | 1725 | 1616 | 2011-11-18 | 2013-05-08 | 2012-07-21 | 2013-05-31 | 100%
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 |  | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008513C7711 AWD | 1925 | 1900 | 2013-03-14 | 2013-09-12 | 2013-08-30 |  | 99%
2014-12-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N50092499 | POWER DISTRIBUTION UPGRADES |  | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | N4008512C1704 AWD | 29520 | 28098 | 2012-10-08 | 2014-11-21 | 2014-10-09 |  | 93%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092662 | EOD ESU TWO EXPEDITIONARY LOGISTICS OVERHAUL WAREHOUSE |  | 2014-05-09 | 2014-08-06 | DOYON MANAGEMENT SERVICES, LLC | N4008514D2102 0001 | 1020 | 231 | 2014-08-20 | 2014-11-21 | 2014-11-21 |  | 6%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N57095101 | ROAD IMPROVEMENTS CAMP ALLEN AREA |  | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | N4008509D5027 0003-PC000002 | 1381 | 1326 | 2011-02-28 | 2012-01-27 | 2011-09-21 | 2012-01-27 | 100%
2014-12-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N57095197 | DECENTRALIZE STEAM SYSTEM |  | 2012-04-17 | 2012-09-20 | SAUER, INC. | N4008509D5026 0004 | 27161 | 26583 | 2012-10-04 | 2015-03-09 | 2015-05-08 | 2015-05-08 | 79%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | N60042116 | D5 MISSILE MOTOR MAGS MODS (NAVOBSSTA FLAGSTAFF AZ) |  |  | 2014-12-11 | NAVY STANDARD DOCUMENT | N6247315MPRM001 | 1725 | 1560 | 2014-12-25 |  |  |  | 0%
2014-12-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N60042260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  |  | 2011-09-29 | NAVY STANDARD DOCUMENT | N6247311RP00189 | 1421 | 1658 | 2011-10-13 |  |  |  | 100%
2014-12-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191513 | A SCHOOL BARRACKS |  | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430 | 29157 | 2013-11-14 | 2015-12-30 | 2015-12-16 | 2015-12-30 | 17% | -5604 | N42237100
2014-12-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS |  | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599 | 17914 | 2012-10-11 | 2015-04-01 | 2014-10-12 | 2015-01-01 | 63%
2014-12-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191582 | UNDERSEA SURVEILLANCE SCIF FACILITY |  | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0003 | 4129 | 4836 | 2012-12-03 | 2014-06-25 | 2013-11-29 |  | 99%
2014-12-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446 | 10677 | 2014-09-30 | 2016-10-25 | 2016-10-25 | 2016-10-25 | 0%
2014-12-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201425 | LCS LOGISTICS SUPPORT FACILITY |  | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | N6945013D1765 0002 | 15842 | 14932 | 2014-06-13 | 2015-11-26 | 2015-11-26 | 2015-11-28 | 12%
2014-12-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS |  | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | N6945012C0757 AWD | 7518 | 9913 | 2012-08-29 | 2014-02-21 | 2014-02-21 |  | 25%
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241288 | WASTEWATER SYSTEM |  | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | N6945014C0763 AWD | 1790 | 1645 | 2014-04-11 | 2015-03-27 | 2015-03-27 | 2015-03-27 | 47%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241294 | CONNECT TO KINGSVILLE WATER SYSTEM |  | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | N6945010D0776 0002 | 1658 | 1549 | 2012-10-08 | 2014-03-21 | 2014-03-21 |  | 96%
2014-12-31 | 2011 | Navy Active | Major Military Construction | ALABAMA | UNITED STATES | N60508266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD |  | 2012-07-05 | 2012-09-28 | HEAD, INC. | N6945012C0760 AWD | 29901 | 26546 | 2012-10-12 | 2014-09-28 | 2014-09-28 | 2014-12-24 | 81%
2014-12-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE |  | 2012-02-17 | 2012-06-07 | NAVY STANDARD DOCUMENT | N6247012MPS0048 | 18810 | 20581 | 2012-06-21 | 2015-04-14 | 2014-12-30 | 2015-04-14 | 73%
2014-12-31 | 2011 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N61007015 | CALIBRATION FACILITY LAND ACQUISITION |  |  | 2011-12-31 | NAVY STANDARD DOCUMENT | N6945011RP00148 | 3149 | 3080 | 2012-01-14 |  |  |  | 100%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61014851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION |  | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | N6247314C2801 AWD | 1916 | 1871 | 2014-01-02 | 2014-12-31 | 2014-10-17 | 2014-12-31 | 47%
2014-12-31 | 2014 | Navy Active | Major Military Construction |  | JAPAN | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458 | 9458 | 2014-10-03 | 2016-08-16 | 2016-08-16 | 2016-08-16 | 0%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054012 | CONSTRUCT NACCC ADDITION |  | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | N4008410D0014 0003 | 1380 | 1256 | 2011-06-24 | 2012-04-20 | 2012-04-13 |  | 96%
2014-12-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER |  | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | N4008411C0129 AWD | 17378 | 16915 | 2011-07-15 | 2013-01-17 | 2012-12-03 | 2013-01-20 | 100%
2014-12-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) |  | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | N4008412C0108 AWD | 19730 | 18773 | 2012-08-01 | 2014-01-13 | 2014-01-13 | 2014-01-13 | 100%
2014-12-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 |  | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | N4008412C0109 AWD | 9033 | 9094 | 2012-08-22 | 2015-01-11 | 2014-10-07 | 2015-01-11 | 77.1%
2014-12-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 |  | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791 | 7305 | 2014-07-29 | 2016-02-21 | 2016-02-21 | 2016-02-21 | 0%
2014-12-31 | 2013 | Navy Active | Major Military Construction |  | JAPAN | N61056353 | BACHELOR QUARTERS |  | 2013-01-24 | 2013-09-27 | NAVY STANDARD DOCUMENT | N6274213MP00015 | 5627 | 5521 | 2013-10-11 | 2015-02-02 | 2015-01-05 | 2015-02-02 | 25%
2014-12-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR |  | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | N4008412C8325 AWD | 5990 | 5654 | 2012-10-10 | 2013-11-22 | 2013-08-26 | 2013-11-22 | 100%
2014-12-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) |  | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | N4008412C0004 AWD | 17540 | 14942 | 2012-08-29 | 2014-07-01 | 2013-12-09 | 2014-07-01 | 100%
2014-12-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES |  | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | N4008414C8401 AWD | 12958 | 12065 | 2013-12-15 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 14.9%
2014-12-31 | 2011 | Navy Active | Major Military Construction |  | JAPAN | N61057203 | AVIATION SIMULATOR TRAINING FACILITY |  | 2010-12-09 | 2011-07-29 | NAVY STANDARD DOCUMENT | N6274211MP00014 | 6764 | 6442 | 2011-08-12 | 2013-11-13 | 2013-11-13 |  | 95%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61057221 | HELO ALFS TEST ROOM, BUILDING 194 |  | 2014-06-12 | 2014-08-06 | NIHON MECCS CO., LTD. | N4008414C8302 AWD | 890 | 812 | 2014-08-20 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 0%
2014-12-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) |  | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799 | 21589 | 2014-10-14 |  | 2016-01-01 | 2016-01-01 | 0%
2014-12-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N61064400 | NORTH LOOP ELECTRICAL REPLACEMENT |  | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | N6247811D4046 0005 | 6498 | 5905 | 2012-03-29 | 2013-12-24 | 2014-01-02 | 2014-12-31 | 88% | -2776 | N42237100
2014-12-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB |  | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447 | 27601 | 2013-10-14 | 2016-04-17 | 2016-04-17 | 2016-06-16 | 22%
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction |  | SINGAPORE | N61077123 | TEMPORARY LCS SUSTAINMENT FACILITY |  | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | N4008413C9001 AWD | 755 | 768 | 2012-12-20 | 2014-01-15 | 2013-03-10 |  | 93%
2014-12-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151162 | AGILE CHEMICAL FACILITY PHASE 2 |  | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | N4008012C2001 AWD | 34869 | 36120 | 2012-08-24 | 2015-06-26 | 2014-06-16 | 2015-06-26 | 67%
2014-12-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151222 | DECENTRALIZE STEAM SYSTEM |  | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984 | 68674 | 2012-10-12 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 81%
2014-12-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY |  | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0007 | 14130 | 13483 | 2013-09-02 | 2015-03-12 | 2015-03-12 | 2015-05-01 | 56%
2014-12-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151372 | PHYSICAL FITNESS CENTER |  | 2012-12-12 | 2013-09-27 | C.E.R. INC. | N4008010D0302 0021 | 11409 | 10677 | 2013-10-11 | 2015-05-02 | 2015-05-02 | 2015-05-02 | 25%
2014-12-31 | 2013 | Navy Active | Military Family Housing Improvement | GUAM | GUAM | N617551301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE |  | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 JQ02 | 26805 | 25377 | 2013-09-26 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 40.77%
2014-12-31 | 2011 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N61755204A | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | N61755204 | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | N4019210D2803 0006 | 21579 | 16525 | 2012-12-12 | 2014-09-29 | 2014-06-19 |  | 77%
2014-12-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755425 | MODULAR STORAGE MAGAZINE |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865 | 45199 | 2014-05-26 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 3%
2014-12-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755518 | X-RAY WHARF IMPROVEMENTS |  | 2014-01-10 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085 | 42581 | 2014-06-17 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 3%
2014-12-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755566 | EMERGENT REPAIR FACILITY EXPANSION |  | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860 | 27568 | 2014-04-24 | 2016-05-12 | 2016-05-12 | 2016-05-12 | 5%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction | GUAM | GUAM | N61755630 | HARDEN ELECTRICAL DISTRIBUTION LINE (POLARIS PT ROAD) |  | 2014-07-01 | 2014-09-30 | P&S CONSTRUCTION, INC. | N4019210D2804 0019 | 2000 | 1912 | 2014-10-14 | 2015-05-19 |  |  | 0%
2014-12-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY |  | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170 | 14318 | 2014-04-03 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 26%
2014-12-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755638 | SIERRA WHARF IMPROVEMENTS |  | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | N4019210D2808 0009 | 1462 | 1209 | 2014-06-13 | 2015-03-26 | 2015-03-26 | 2015-03-26 | 0%
2014-12-31 | 2013 | Navy Active | Major Military Construction |  | ROMANIA | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | N6247014MPE0025 | 40018 | 36389 | 2014-05-14 |  |  |  | 7%
2014-12-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688123 | BACHELOR QUARTERS, HOMEPORT ASHORE |  | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | N4008512C4572 AWD | 74854 | 72209 | 2012-09-14 | 2015-05-31 | 2014-09-13 | 2015-03-26 | 84% | -3084 | N684691400
2014-12-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365 | 1113 | 2014-07-14 | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2%
2014-12-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE |  | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008511D6585 0001 | 1395 | 1273 | 2011-06-28 | 2012-11-07 | 2012-06-18 | 2012-11-07 | 100%
2014-12-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688862 | PIER 1 UPGRADES TO BERTH USNS COMFORT |  | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | N4008511C0020 AWD | 3659 | 2953 | 2011-08-09 | 2012-09-18 | 2012-08-09 |  | 79% | -6185 | M00681159, N42237100
2014-12-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N627351102 | WHOLEHOUSE IMPROVEMENT |  | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | N4008411C0006 AWD | 8127 | 6990 | 2011-07-10 | 2013-01-18 | 2012-10-17 | 2013-02-14 | 100%
2014-12-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813005 | JOINT POW/MIA ACCOUNTING, USPACOM |  | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274211C1300 AWD | 95540 | 83528 | 2011-06-20 | 2014-11-24 | 2013-07-05 |  | 87%
2014-12-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY |  | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | N6247810D4022 0019 | 7708 | 7642 | 2012-04-19 | 2014-11-09 | 2013-11-16 |  | 98%
2014-12-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE |  | 2011-02-04 | 2011-06-24 | FOPCO, INC | N6247810D4019 0006 | 7856 | 9024 | 2011-07-08 | 2013-06-03 | 2012-08-15 |  | 99%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813058 | ROCKFALL PROTECTION AT RED HILL |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810 | 2615 | 2014-12-08 | 2016-05-18 | 2016-05-18 |  | 0%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) |  | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | N6247810D4020 0014 | 1559 | 1446 | 2011-10-03 | 2013-03-01 | 2012-12-24 | 2013-03-01 | 100%
2014-12-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813270 | DRYDOCK WATERFRONT FACILITY |  | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355 | 20180 | 2014-03-03 | 2015-12-11 | 2015-12-11 | 2015-12-11 | 4%
2014-12-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970 | 29387 | 2014-07-14 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 1%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863708 | CONSTRUCT LCAC BEACH ACCESS RAMP |  | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | N3319110D0219 0009 | 1751 | 1411 | 2013-10-13 | 2014-06-20 | 2014-05-28 |  | 97%
2014-12-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863709 | GENERAL PURPOSE WAREHOUSE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 2446 | 1908 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 42%
2014-12-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863710 | HIGH EXPLOSIVE MAGAZINE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 5849 | 5109 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 38%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863733 | PROVIDE ELECTROMAGNETIC CALIBRATION COMPLEX |  | 2014-08-29 | 2014-09-19 | NEWIMAR SA | N3319110D1801 0283 | 1144 | 711 | 2014-10-03 | 2015-08-21 |  |  | 5%
2014-12-31 | 2011 | Navy Active | Major Military Construction |  | SPAIN | N62863897 | AIR TRAFFIC CONTROL TOWER |  | 2012-01-13 | 2012-06-15 | SACYR SA | N3319112C0603 AWD | 19080 | 15666 | 2012-06-29 | 2015-04-15 | 2014-09-03 | 2015-01-04 | 67% | -2052 | N42237100
2014-12-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY |  | 2012-04-12 | 2012-08-17 | NAVY STANDARD DOCUMENT | N6247012MPE0064 | 41151 | 38523 | 2012-08-31 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 47% | -15471 | Sequestration Reprogramming
2014-12-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005954 | WATERFRONT DEVELOPMENT, PHASE 3 |  | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT | N6247012MPE0005 | 40713 | 40237 | 2012-03-14 | 2014-11-26 | 2014-11-26 |  | 84% | -19865 | Sequestration Reprogramming
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042331 | WATER WELL |  | 2011-01-11 | 2011-09-30 | EPC CORPORATION | N6247310D5415 0012 | 2713 | 2887 | 2011-10-14 | 2013-11-22 | 2012-10-01 | 2013-05-21 | 100%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 |  | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | N6247312C3410 AWD | 1980 | 1878 | 2012-09-12 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 100%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT |  | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | N6247312C3413 AWD | 2000 | 1896 | 2012-10-12 | 2014-03-05 | 2013-09-26 |  | 96%
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042376 | VFA-94 HANGAR ALTERATIONS |  | 2014-08-27 | 2014-09-27 | COPPERTOP LEDCOR JV | N6247313D4608 0014 | 1839 | 1650 | 2014-10-11 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 0%
2014-12-31 | 2013 | Navy Active | Major Military Construction | MISSISSIPPI | UNITED STATES | N63043317 | DINING FACILITY |  | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851 | 9278 | 2013-12-31 | 2015-10-09 | 2015-10-09 | 2015-10-09 | 17%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63406563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 |  | 2012-06-20 | 2012-09-28 | NOVA R M F | N6247312D0245 0003 | 1939 | 1875 | 2012-10-12 | 2014-06-23 | 2013-09-27 | 2014-07-01 | 100%
2014-12-31 | 2013 | Navy Active | Major Military Construction |  | GREECE | N66691907 | AIRCRAFT PARKING APRON EXPANSION |  | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPAQOLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663 | 11219 | 2014-07-25 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 4%
2014-12-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 |  | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | N4425510D5019 0002 | 13341 | 10555 | 2012-06-08 | 2013-06-27 | 2013-12-24 |  | 88%
2014-12-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179 | 10307 | 2014-08-01 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 1%
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436839 | RENOVATE LOWER BASE FIRE STATION |  | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | N4425509D4007 0017 | 1389 | 1327 | 2012-09-14 | 2013-11-13 | 2013-08-31 |  | 99%
2014-12-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436843 | CSDS-5 LABORATORY EXPANSION PHASE ! |  | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | N4425510D5006 0005 | 16042 | 16448 | 2011-06-17 | 2013-09-24 | 2012-10-15 |  | 88%
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436857 | FLOATING LABORATORY, MOORING DOLPHINS |  | 2013-01-16 | 2013-05-17 | NOVA GROUP INC | N4425510D5019 0003 | 3406 | 3115 | 2013-05-31 |  |  |  | 100%
2014-12-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 14315 | 14812 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-05-15 | 100%
2014-12-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436913 | EHW SECURITY FORCE FACILITY |  | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | N4425512C3007 AWD | 13485 | 13667 | 2012-02-14 | 2014-06-11 | 2013-08-08 |  | 75% | -7933 | N684691400
2014-12-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436973F | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | N63402973 | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | N4425508C6003 PC000094 | 20026 | 19450 | 2010-11-24 | 2012-06-01 | 2011-11-08 |  | 92%
2014-12-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436985 | WRA VEHICLE BARRIERS |  | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | N4425510D5008 0012 | 9338 | 8948 | 2012-02-24 | 2013-12-11 | 2013-12-10 |  | 85% | -7587 | N42237636
2014-12-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436987 | EMERGENCY GENERATOR, LIMITED AREA |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 11275 | 10432 | 2011-06-17 | 2013-07-10 | 2013-06-26 |  | 97%
2014-12-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 |  | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714 | 78002 | 2012-05-23 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 92%
2014-12-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990A | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | N68436990 | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 280041 | 238238 | 2012-11-15 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 63%
2014-12-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990B | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990 | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 24880 | 13754 | 2014-01-14 |  |  |  | 0%
2014-12-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N68469110 | REPLACE CONDEMNED COATINGS LABORATORY |  | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0019 | 3805 | 3998 | 2012-09-11 | 2014-04-24 | 2013-08-28 |  | 99%
2014-12-31 | 2014 | Navy Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | N684691400 | NAVSEA HQ RESTORATION |  | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | N6247013D6019 JU01 | 48905 | 48129 | 2014-02-14 | 2015-01-31 |  | 2015-01-31 | 78%
2014-12-31 | 2012 | Navy Active | Major Military Construction |  | DIEGO GARCIA | N68539184 | POTABLE WATER PLANT MODERNIZATION |  | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101 | 28232 | 2013-01-04 | 2015-08-26 | 2015-07-30 | 2015-08-26 | 74%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING |  | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | N4008506D6009 0008 | 928 | 950 | 2011-07-04 | 2012-04-16 | 2012-01-26 | 2012-04-30 | 100%
2014-12-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212543 | NAVELSG RESERVE FORCES MARSHALLING YARDS |  | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | N4008511D6588 0006 | 738 | 747 | 2013-01-30 | 2013-10-23 | 2014-01-21 |  | 95%
2014-12-31 | 2011 | Navy Reserve | Major Military Construction | VIRGINIA | UNITED STATES | N69212743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX |  | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008509D5019 0003 | 15431 | 17554 | 2011-06-17 | 2013-10-18 | 2013-04-27 | 2014-10-18 | 100%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212984 | REGIMENTAL HEADQUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028 | 10655 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-08-14 | 37%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212985 | BACHELOR ENLISTED QUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418 | 17605 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-08-14 | 30%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212986 | MOTOR TRANSPORTATION FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 5841 | 5659 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 52%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212987 | SUPPLY WAREHOUSE FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 6987 | 6635 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 53%
2014-12-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212989 | ARMORY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 3653 | 3453 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 78%
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | N69213206 | CONSTRUCT DISPATCH CENTER |  | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | N4008510D9451 0005 | 1630 | 1633 | 2011-12-01 | 2013-03-26 | 2013-01-25 | 2013-03-29 | 100%
2014-12-31 | 2013 | Navy Active | Major Military Construction | NEW JERSEY | UNITED STATES | N69213237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION |  | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | N4008513C3513 AWD | 34005 | 33534 | 2013-09-17 | 2014-11-27 | 2014-11-27 | 2015-01-24 | 88%
2014-12-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232281 | AIRCRAFT ENGINE TEST PADS |  | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | N6247309D1657 0016 | 6106 | 5718 | 2014-06-26 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 6%
2014-12-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232559 | E-2D AIRCREW TRAINING FACILITY |  | 2012-03-21 | 2012-06-29 | ALLEN ENGINEERING CONTRACTOR, INC | N6247309D1658 0012 | 13210 | 15680 | 2012-07-13 | 2014-06-25 | 2013-10-07 |  | 94%
2014-12-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232599 | UNACCOMPANIED HOUSING CONVERSION (PORT HUENEME) |  |  | 2014-11-24 | NAVY STANDARD DOCUMENT | N6247314RP00165 | 33594 | 25645 | 2014-12-08 |  |  |  | 100%
2014-12-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232900 | BAMS MAINTENANCE TRAINING FACILITY |  | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301 | 8719 | 2013-09-10 | 2014-11-21 | 2014-11-21 | 2015-05-01 | 8%
2014-12-31 | 2013 | Navy Reserve | Major Military Construction | TEXAS | UNITED STATES | N83447047 | COMMERCIAL VEHICLE INSPECTION SITE |  | 2013-01-22 | 2013-09-12 | KOMADA, LLC | N6945013D1767 0001 | 6894 | 6601 | 2013-09-26 | 2015-03-02 | 2014-11-06 | 2014-12-17 | 35.39%
2014-12-31 | 2014 | Navy Active | Major Military Construction | OKLAHOMA | UNITED STATES | N83447136 | TACAMO E-6B HANGAR |  | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19401 | 18478 | 2014-10-14 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 0%
2014-12-31 | 2013 | Defense Finance and Accounting Service | Major Military Construction | TEXAS | UNITED STATES | 80230 | DFAS Administration Building | 80230 | 2013-04-24 | 2013-07-30 | US Army COE Guyco, INC | Contract No. W9127S-09-D-6006 | 12903 | 12903 | 2013-09-11 | 2015-09-05 | 2015-03-05 | 2015-05-10 | 27%
2014-12-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 75132 | Joint Navy-VA Project |  |  | 2013-09-27 | Billy W. Jarrett Const Co Inc | N62470 13 MPS 0046 | 1797 | 1899 |  |  | 2014-10-15 | 2014-10-15 |  |  |  | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2014-12-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81004 | Site Development, NiCOE |  | 2012-05-16 | 2012-06-05 | Sunland Builders, Inc | N40085 09 D 9027 DO 0026 | 1363 | 1452 | 2012-08-01 | 2013-08-12 | 2013-08-29 | 2013-08-29 | 100% |  |  | Project is not financially closed.
2014-12-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | GUANTANAMO BAY NAVAL BASE | GUANTANAMO BAY NAVAL BASE | 82095 | Veterinary Treatment Facility Alterations
2014-12-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction |  | GERMANY | 68974 | Computer Operations Center |  | 2011-02-01 | 2011-04-22 | Federal Republic of Germany |  | 1950 | 1950 | 2011-05-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100%
2014-12-31 | [8 empty] | 2011-01-08 | 2011-03-14 | Wayss & Freytag |  | 1572 | 1548 | 2013-04-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100%
2014-12-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 77342 | Bldg 509 Alteration of Medical Laboratory |  | 2010-12-17 | 2011-01-28 | Odyssey International, Inc |  | 3294 | 3690 | 2011-02-16 | 2011-09-15 | 2011-09-15 | 2011-08-15 | 100% |  |  | Preparation for fiscal closeout.
2014-12-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 80093 | Medical Ed. & Training Facility |  | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc |  | 1698 | 1982 | 2012-08-14 | 2014-09-10 | 2013-11-14 | 2014-08-24 | 100% |  |  | Preconstruction Meeting held 31 JAN 2014. Physical Construction (mobilization) started FEB 2014. BOD 11 AUG 2014. Project Complete. The field office is currently working with the contractor on punch list items. Some of punch list items might require the shut down at least 10 hours to the Mike O'Callaghan Federal Medical Center so the contractor can repair a shutter in the switch gear. Coordination for the shutdown between the affected departments is in progress. The field office is trying to see if it can happen before the 31 December to minimize the impact to the patients.
2014-12-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 81247 | Site Dev in Support of NiCOE |  | 2012-08-15 | 2012-09-28 | GKK | W91278-10-D-0047 | 1589 | 1638 | 2012-10-28 | 2014-07-30 | 2014-01-03 | 2014-07-15 | 100% |  |  | Project is Closed Out.
2014-12-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80792 | Site Development, NiCOE |  | 2012-06-18 | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service | W81W3G22363343 / 22443665 / 22443666 / 30793685 | 1600 | 1690 | 2012-09-10 | 2013-06-30 | 2013-05-31 | 2013-08-29 | 100% |  |  | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Work executed via FBVA contract. 100% complete. BOD achieved 30 June 2013. Received invoice from DLA rep who manages American Water (water & wastewater) showing that they were paid in full, don't have a separate document from American Water that is a Release of Claims. Received from DPW a copy of a "Project Completion Form" sent by Dominion Virginia Power (electricity). PM was told this is what DPW requires from DVP when a project is complete. Received the last "Release of Claims" from NEC/ITA/Verizon with the statement, "All, I attached the MIPR Acceptance Form for the NICOE Building 1259. NEC was provided $68,141.25 to install the Outside Plant Copper and Fiber Cables. NEC/ITA/Verizon Federal completed the installation July 2013. No further funding required." Project Fiscal Closeout Ongoing.
2014-12-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80094 | Veterinary Clinic |  | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc | W912BV-12-C-0030 | 16643 | 1692 | 2013-01-04 | 2014-12-05 | 2014-07-05 | 2014-12-12 | 90% |  |  | Punch-list completed 31 Dec 14. Will revisit asphalt concerns with BCE and the contractor in the Spring of 2015 for possible snow plow damage. Contractor still needs to submit LEED and CAD as-builts. Current obligation w/all mods $2,046,905.00 which breaks down into $1,691,830.00 MILCON and $355,075.00 I/O funds. We just settled an REA in the amount of $18,577 so that will be added to the obligations.
2014-12-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 82358 | Veterinary Clinic Replacement |  | 2015-05-26 | 2015-08-30 | [6 empty] | 2016-05-30 |  |  |  |  | PA is $1.5M and CWE was $1.98M. PDT identified cost reduction measures. Once a confidence level is established that the requirements of the RFP have been adjusted to achieve the target CWE, a revised solicitation will be issued. USACE thinks the AF 1300 page iDBIO RFP Template will cause the bids to be about $$775/sqft a second time. Need DHA to concur or or increase the PA on this project.
2014-12-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81631 | NiCOE Satellite, Infrastructure Support |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc | W912HN-11-D-0043-0044 | 1436303 | 1436303 | 2014-06-30 | 2015-11-25 | 2015-04-24 | 2015-04-24 | 35% |  |  | The Site Support Contractor has promised unfettered access to the building pad by completing the two parking lots 4-inch stone base course. The Site Support Contractor will still be working on the communication duct bank (directional bore & MHs) and gas line after 19 Dec 14. ONUS will be completing their work (Fire Main, Domestic Water, SS, Lift Station) after 19 Dec 14. With the Building Contractor mobilizing personnel one week after rebar delivery on 29 Dec 14, the Site Support Contractor should be able to complete the remaining utilities so that their work will not interfere with the Building Contractor. Contingencies in district: $26,813.38
2014-12-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 81706 | NiCOE Satellite, Infrastructure Support |  | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 2166 | 1795 | 2014-09-15 | 2015-10-28 | 2016-08-19 | 2016-08-19 | 46% |  |  | Parking lot grading continues; installation of water and gas lines lines coninue; Sanitary sewer installation continues.
2014-12-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 1 |  | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 | 757737 | 774314 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100%
2014-12-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005A | Medical Center Add/Alt, Inc 2 | 005V | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100% |  |  | Not financially closed. Final invoicing for equipment.
2014-12-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005B | Medical Center Add/Alt, Inc 3 | 005V | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100%
2014-12-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MISSISSIPPI | UNITED STATES | 478V | Community Hospital |  | 2009-04-01 | 2009-11-10 | W.G. Yates & Sons Construction Co. | N69450 10 C 0763 | 38252 | 42256 | 2010-01-01 | 2012-02-25 | 2011-09-11 | 2012-10-11 | 100% |  |  | Not financially closed. Final invoicing for equipment - working with DLA.
2014-12-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69427 | Hopsital Replacement, Inc 1 |  | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV |  | 649025 | 9428 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | Project ready for closeout
2014-12-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69865 | Hopsital Replacement, Inc 4 | 69427 | 2007-06-12 | 2010-01-23 | Turner/Gilbane JV |  |  | 119266 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | Final Payment and final release received and processed. Target contract closeout by 30 January 2015. MEDCOM has deobligated $245K and returned . Target contract closeout 30 Jan 2015. Project Closeout in P2 by 15 Feb 2015. Unobligated funds $245K will be returned by 30 Jan 2015.
2014-12-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 77071 | Hopsital Replacement, Inc 5 | 69427 | 2007-06-12 | 2010-10-20 | Turner/Gilbane JV |  |  | 211800 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | See above.
2014-12-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 1 |  | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 107589 | 135926 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | There are still actions on-going that will prevent close-out: 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Resolution period to be determined. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments have been suspended. They provided the telephones for the project. Throughout USACE invoices from EYAK Technology, Inc continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. USACE does not expect this matter to be resolved by the Department of Justice during FY 2014. The status is unchanged. The SWF invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. I do not expect this matter to be resolved by the Department of Justice during FY 2014. - Per USACE CT Office 3. TEAM Integrated Services Task Orders. Last DCAA audit is estimated to be completed 31 Dec 2015.
2014-12-31 | 2009 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64180 | San Antonio Regional MEDCEN, Inc 2 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 265100 | 279273 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | See above.
2014-12-31 | 2010 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 69840 | San Antonio Regional MEDCEN, Inc 3 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 13748 | 243943 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | See above.
2014-12-31 | 2011 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 70990 | San Antonio Regional MEDCEN, Inc 4 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 37554 | 85520 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | See above.
2014-12-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64188 | Health Clinic |  | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | W9126G-08-C-0024 | 33382 | 37382 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 100% |  |  | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2014-12-31 | 2010 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64241 | Dental Clinic |  | 2009-09-16 | 2010-05-04 | Forrester Construction Company |  | 7541 | 8818 | 2010-05-18 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | NAB received 0516 BRAC Consolidated funding, executed the Global Settlement Modification, paid Final Invoice, and received Release of Claims from Contractor. Construction Contract and Project in Close Out Phase. Fiscal Closeout is scheduled, and tracking for 13 Jan 2015.
2014-12-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 64156 | USAMRICD Replacement, Inc 1 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398 | 17027 | 2010-03-15 | 2015-01-15 | 2013-06-01 | 2015-01-15 | 99% |  |  | Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 15 Jan 2015 for remainder of spaces.
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | GUAM GU | GUAM | 65270 | Hospital Replacement, Inc 1 |  | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133 | 165418 | 2010-11-01 | 2014-03-18 | 2014-10-15 | 2015-03-27 | 99% | 19460 |  | 93% complete is 100% of the hospital completion. The remaining 7% is the demo of the existing facility. Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77154 | Ambulatory Care Center, Inc 1 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 197804 | 137828 | 2013-03-01 | 2016-12-06 | 2016-12-06 | 2017-11-08 | 49% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 81291 | Ambulatory Care Center, Inc 2 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV |  |  | 66430 | [7 empty] | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 |  | 39820 | 39911 | Total Engineering for Site Package | W912DR-09-C-0030 | 1918-11-08 20:53 | 1919-05-10 04:45 | 2009-08-19 | 2010-08-31 | 4039800% | 40421 | 100% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC
[9 empty] | 39869 | 40039 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 1932-11-07 | 1934-08-27 | 2010-03-15 | 2014-11-01 | 4142600% | 41995 | 100% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC. $9,000 recinded as a result of Sequestration (04/29/13).
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67180 | USAMRICD Replacement, Inc 2 |  | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100%
[9 empty] | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 100%
[9 empty] | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 100375 | 103745.3283 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 100% |  |  | Main Building $142,857,143 FY10 Increment Awarded at $100,375,000 on 5 Mar 10 ($109,567,007 funded per D. Pritchett 17 Mar 10 email)
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67181 | USAMRICD Replacement, Inc 3 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 94608 | 96044.5065 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2015-01-15 | 99% |  |  | Full FY11 MILCON increment placed against contract.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67182 | USAMRICD Replacement, Inc 4 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 7915.345 | 27114 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2015-01-15 | 99% |  |  | Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 15 Jan 2015 for remainder of spaces.
2014-12-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 |  | 2007-06-30 | 2007-09-29 | Cont #1 - Offiste San Sewer & Storm (James Construction) | W912DR-07-C-0070 | 2657 | 2657 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 100% |  |  | Work complete. Contracts closed.
[9 empty] | 2008-01-10 | 2008-08-01 | Cont #2 - Storm Lat 1&3A (James Construction) | W912DR-08-C-0038 | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 100% |  |  | Work complete. Contracts closed.
[9 empty] | 2008-05-01 | 2009-09-28 | Cont #3 - IMP Pond (James Corporation) | W912DR-08-C-0078 | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 100% |  |  | Work complete. Contracts closed.
[9 empty] | 2008-01-10 | 2008-09-25 | Cont #4 - Early Site/Utility (Grunley/Goel JVA LLC) | W912DR-08-C-0053 | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 100% |  |  | Work complete. Contracts closed.
[10 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 2866 | 2866 | 2008-07-15 | 2013-12-06 | 2011-05-06 | 2013-10-31 | 100% | 2289 |  | Work being accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project. *** Need to add Contract #7 line items for FY 10/11 funding. FY 10: original contract amount ($496,221) and current contract/total obligation ($524,505.60). FY 11: original contract amount ($603,803) and current contract/total obligation ($638,219.77).
[9 empty] | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 15736 | 16161 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 94% |  |  | FY07. See FY2012 remarks. Contract active, but all funds on this increment obligated. Building to be operational NOV 2017.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63418 | USAMRIID Replacement, Incr 2 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 131264 | 138491 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | Phase I - FY 08 (note corrected PN)
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63419 | USAMRIID Replacement, Incr 3 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 185526 | 185630 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | FY09. See FY2012 remarks. Contract active, but all funds on this increment obligated.
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63420 | USAMRIID Replacement, Incr 4 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 94000 | 100180 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | FY10. See FY2012 remarks. Contract active, but all funds on this increment obligated.
[10 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 496 | 525 | 2008-07-15 | 2013-12-06 | 2013-10-31 | 2013-10-31 | 99% |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65324 | USAMRIID Replacement, Incr 5 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 13497 | 12893 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | FY11. See FY2012 remarks. Contract active, but all funds on this increment obligated.
[10 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 603 | 638 | 2008-07-15 | 2013-12-06 | 2013-10-31 | 2013-10-31 | 99% |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71101 | USAMRIID Replacement, Incr 6 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 66955 | 84557 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | FY12. Scheduled 100%, Actual 94%. Liquidated damages being assessed as a result of delays caused by a fire. Contractor's insurance covering repairs and delay costs. T&E change under negotiation with contractor. Contractor is re-installing BSL4 lab coatings, cleaning smoke-damaged BSL3 area equipment, and commissioning remainder of facility. Plan is to accept admin, BSL2 and BSL3 labs Jun 2016 to start CDC certification and accept BSL4 labs Jul 2017.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78210 | USAMRIID Replacement, Incr 7 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 0 | 0 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 0% |  |  | Utilities, DDC, North Parking and related costs.
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78211 | USAMRIID Replacement, Incr 8 | 58395 | 2015-01-22 | 2015-05-29 | Cont # 6 (North Parking) (TBD) |  |  | 0 | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | CENAB in-house resources completing design. RTA date for North Parking adjusted to 30 Jan 15 and schedule readjusted to allow additional time for Maryland Dept of Environment approvals. Contract solicitation will include NIBC Fence - Ph II (FY 11 DODM) and Entry Control Point.
[9 empty] | 2017-04-01 | 2017-08-01 | Cont # 8 (South Parking/Demolition) (TBD) |  |  | 0 | 2019-08-22 | 2020-10-21 | 2020-08-22 | 2020-10-31 | 0% |  |  | Notional schedule shown; dependent on CDC/DA Safety certification of USAMRIID primary facility and vacation/decommissioning of existing buildings 1408/1412/1414/1415. Due to delay in main contract, projections for award are moved out 2 years.
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 |  | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 7782 | 11366 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 24% |  |  | Note 1: The Hospital Contractor is tracking with the late finish + 90 days of delay due to pier and structural steel delays for a projected completion of May of 2017. Due to these delays and anticipated challenges in the areas of sub-contractor management and limited labor pools the BOD has been revised from 3 Apr 2017 to 3 Oct 2017 in order to provide a better planning date to coordinate IO&T activities and to provide a more realistic expectation to project stakeholders. •Placement to date: $144M as of 5 Dec 14. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Contractor has begun concrete floor placement of 60000sf on the first floor of the Hospital. •CUP slab on grade & CMU wall erection is ongoing. •Lift Station excavation is ongoing.
2014-12-31 | [8 empty] | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. - Infrastructure | W912G-09-D-0004-0008 | 39345 | 47508 | 2011-11-02 | 2013-10-12 | 2013-08-13 | 2013-08-29 | 100% |  |  | Construction 100% Complete
2014-12-31 | [8 empty] | 2011-03-25 | 2011-06-17 | Janco - Water Tower | W9126G-09-D-0096-0002 | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 100% |  |  | Construction 100% Complete
2014-12-31 | [8 empty] | 2012-03-16 | 2012-07-19 | VEMAC - Parking Pkg A | W9126G-12-C-0038 | 3848 | 3879 | 2012-08-28 | 2013-10-17 | 2013-06-19 | 2013-06-11 | 100% |  |  | Construction 100% Complete
2014-12-31 | [8 empty] | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960 | 2800 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-08-10 | 8% |  |  | 8% Construction Complete. The contractor began construction 3 Nov 14. He began at the southernmost end (Stockmeyer) and will work towards Pebble Hills. He reached Pebble Hills on 11/21/14. Contractor is constructing this line in 1,000 LF sections. Contracting also awarded the modification to EPWU for the revised bid amount of: $4,338,247.84 on 14 Nov 14.
2014-12-31 | [8 empty] | 2012-02-08 | 2012-09-04 | El Paso Electrical Substation | W9126G-12-P-0014 | 4047 | 4047 | 2012-09-04 | 2015-09-16 | 2014-01-04 | 2014-01-04 | 100% |  |  | Construction 100% Complete
2014-12-31 | [10 empty] | Temp Electric Contract |  | 46 | 46 |  |  |  |  | 100% |  |  | Temp power costs.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77251 | Fort Bliss Hospital Repl, Incr 2 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 68076 | 68076 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 24% |  |  | See Note 1 above.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72786 | Fort Bliss Hospital Repl, Incr 3 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 69851 | 72931 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 24% |  |  | See Note 1 above.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 76558 | Fort Bliss Hospital Repl, Incr 4 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 79914 | 160491 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 24% |  |  | See Note 1 above.
2014-12-31 | [8 empty] | 2013-08-08 | 2013-09-13 | Helipad | W9126G-13-C-0046 | 1540 | 657 | 2013-10-21 | 2014-11-24 | 2014-10-24 | 2014-10-24 | 100% |  |  | •Final Inspection was held on 6 Nov 2014. •BOD was 24 Nov 2014. •Contractor is currently working to complete punch list items.
2014-12-31 | [9 empty] | 2014-07-25 | El Paso Water Utility Pmt 2 / Sewer Contract | W9126G-14-P-0150 | 479 | 1538 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-08-10 | 8% |  |  | The contractor began construction 3 Nov 14. The tie-in manhole at the intersection of Stockmeyer and Pebble Hills was found to be in a deteriorated condition. A new manhole will need to be installed to perform the tie-in. The number of employees varies between 8 and 10 on any given day. The contractor plans on adding a second crew within the next couple of weeks, so this number may double. Contracting also awarded the modification to EPWU for the revised bid amount of: $4,338,247.84 on 14 Nov 14.
2014-12-31 | [9 empty] | 2015-02-15 | Parking Pkg B |  | 5562 |  | TBD (NOTES) | TBD (NOTES) | TBD (NOTES) | TBD (NOTES) | 0% |  |  | Parking Package “B”:(small business- LPTA) Est. Award: $5.5M •Solicitation Package is complete. •Proposed Award Date: 15 Feb 15
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77293 | Fort Bliss Hospital Repl, Incr 5 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 198148 | 77700 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 24% |  |  | See Note 1 above.
2014-12-31 | [8 empty] | 2014-10-20 | 2014-12-10 | ACPs |  | 24755 |  | 2014-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 0% |  |  | ACP Package: (small business-Best Value) Est. Award: $24.7M •Solicitation package is complete. •Proposed Award Date: 15 Feb 15
2014-12-31 | [9 empty] | 2015-03-30 | CAT E Equipment |  | 33125 | [5 empty] | 0% |  |  | No update this reporting period.
2014-12-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81047 | Fort Bliss Hospital Repl, Incr 6 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 225199 | 0 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 24% |  |  | See Note 1 above.
2014-12-31 | [8 empty] | 2015-03-30 | 2016-03-28 | Landscaping |  | 22616 |  | 2015-07-30 | 2016-07-30 | 2016-07-30 | 2016-07-30 | 0% |  |  | Landscaping Package: (small business-LPTA) Est. Award: $22.7M •Solicitation package is complete. •Proposed Award Date: 28 Mar 16 with a potential early award in May of 2016.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc | W9126G-12-C-0051 | 76038 | 75808 | 2012-11-01 | 2015-06-30 | 2014-07-29 | 2015-04-17 | 85% |  |  | Note 2: Construction Progress: Sch. 85% Act. 85% with BOD of 30 Jun 2015. Includes Buildings G, H, J, K, L & M. Contractor has begun MEP punch-out, and some finish work is ongoing in various buildings. Exterior work is complete or in the final stages. Site work: dining plaza footings underway, concrete placement continues and bollard installation ongoing. Parking Lot C has been turned over pending approval of interim DD 1354.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 80793 | Ambulatory Care Center Phase 3, Inc 2 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc | W9126G-12-C-0051 | 16319 | 21250 | 2012-11-01 | 2015-06-30 | 2014-07-29 | 2015-04-17 | 85% |  |  | See Note 2 above.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 |  |  |  | Environmental Compensation |  | 15042 | 1731 | 2014-01-13 |  | 2021-07-20 |  | 5% |  |  | German government solicitation and award dates to German industry are estimated. ['Constr Oblig to FRG 3/15/2012]
2014-12-31 | [10 empty] | Lot 1 Temporary Construction Fence |  | 260 | 260 | 2014-01-20 |  | 2014-04-04 | 2014-04-04 | 99% |  |  | Construction essentially completed April 2014; however, access from the east is still open. Once the security contract is awarded, the FRG govt will close the roadway access from the east in the construction fence. [Constr Oblig to FRG 3/15/2012]
2014-12-31 | [10 empty] | Lot 2.1 Demolition, Site Clearing |  | 1099 | 1099 | 2014-06-16 | 2014-08-29 | 2014-10-29 | 2015-01-14 | 90% |  |  | Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Before or on 14 Jan 2015, the FRG will evaluate next steps if contractor still not complete. [Constr Oblig to FRG 3/15/2012]
2014-12-31 | [10 empty] | Lot 2.2 Mass Grading |  | 20158 |  | 2015-03-15 | 2016-04-15 | 2016-04-15 |  | 0% |  |  | 100% P&S received 28 July 14 and approved 7 Aug 14. German govt released solicitation on 15Dec 2014. [Constr Oblig to FRG 3/15/2012]
2014-12-31 | [10 empty] | Transformers/Substation |  | 19557 |  | 2015-03-15 | 2017-01-15 | 2017-01-15 |  | 0% |  |  | FRG to solicit in est. 2QFY15. FRG solicitation and award dates to German industry are estimated. [Constr Oblig to FRG 3/15/2012]
2014-12-31 | [10 empty] | Lot 3.9 Site Security |  | 6215 | 6215 | 2015-01-05 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 0% |  |  | Contract for overall site security. Contract will run through the end of construction. [Constr Oblig to FRG 3/15/2012]
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction |  | GERMANY | 72661 | Medical Center Replacement, Incr 2 | 76007 |  |  | Lot 3.1 Construction Preparatory Measures |  | 26097 |  | 2015-04-15 | 2016-04-15 | 2016-04-15 | 2015-12-30 | 0% |  |  | ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines. Change coordinated with DHA-Europe; 25% water supply will no longer come from Ramstein Air Base. Change will also reduce risk in meeting German hygiene requirements for water supply. Awaiting new schedule from the FRG. Dates provided herein are estimated. [Constr Oblig to FRG 8/27/2013]
2014-12-31 | [10 empty] | Lot 4 Access Control Point, Bridge, External Roadways |  | 54539 |  | 2016-02-15 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Currently at 35% design. German government solicitation and award dates to German industry are estimated. [Constr Oblig to FRG 8/27/2013]
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 72662 | Medical Center Replacement, Incr 3 | 76007 |  |  | Lot 5.1 Parking Structures, Campus Roadways |  | 59043 |  | 2016-06-17 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Included in MedCen 20% design. EUD provided letter authorizing the design kickoff, currently targeted for Spring 2015. FRG solicitation and award dates to German industry are estimated. [Constr Obligation to FRG est. Mar 2015]
2014-12-31 | 2015 | Defense Health Agency | Major Military Construction |  | GERMANY | 76872 | Medical Center Replacement, Incr 4/5 | 76007 |  |  | Medical Center (Bed Tower, D&T, Clinics, Admin) |  | 635222 |  | 2019-02-12 | 2022-11-08 | 2021-12-08 |  | 0% |  |  | US led 20% MedCen final design submitted 2 Aug 2013. USACE is transitioning design to FRG. FRG AE target selection date is Spring 2015 for follow-on 20-100% design. FRG solicitation and award dates to German industry are estimated. Admin now apart of Med Ctr. [Constr Oblig Est. Mar 16]
2014-12-31 | 2007 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 52330 | Clinic Replacement, Inc 1 |  | 2007-02-16 | 2007-07-19 | Caddell Construction Co, Inc | W91278-07-C-0037 | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100% |  |  | Water intrusion problem update - AE and Contractor being contacted - expect AE response Jan 2015.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 67647 | Clinic Replacement, Inc 2 | 52330 | 2007-02-16 | 2007-07-19 | Caddell Construction Co, Inc | W91278-07-C-0037 | 32890 | 42183 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100% |  |  | Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. SAM has initiated discussions with Construction Contractor and is in process of developing a letter of inquiry to the designer of record requesting an assessment.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71857 | Hospital Addition |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 31112 | 32852 | 2010-12-03 | 2013-07-15 | 2013-01-12 | 2013-07-15 | 100% | 3486 |  | Funds used for FY00 Settlement, Ft. Wainwright. Residual activity on project funding items.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 64809 | Pharacare Addition/Alteration |  | 2007-09-27 | 2008-02-29 | J2 Engineering, Inc | W91278-07-D-0073-0002 | 3381 | 3489 | 2008-03-24 | 2009-03-24 | 2009-03-24 | 2009-03-24 | 100%
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) |  | 2009-04-08 | 2009-09-28 | Turner Construction Company | W912HN-09-C-0045 | 230018 | 274954 | 2009-10-22 | 2014-05-19 | 2013-02-03 | 2014-05-19 | 100% |  |  | Inspections, Punch-Outs and commissioning of systems continues. Contingencies at District: $850,131. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 1 Jul 15.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | KANSAS | UNITED STATES | 47298 | Hospital Replacement |  | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110 | 282778 | 2010-05-03 | 2015-07-01 | 2013-07-23 | 2015-01-30 | 97% |  |  | a.Contract CCD: 13 May 2014 b. Placement: 97% actual vs. 100% scheduled. c. Construction in progress: air handler and TAB/commissioning has restarted ; site work in the healing garden area has started; atrium curtain walls testing strated; expansion joint work continues on both sides of the building; Pre-final Inspections have restarted as of 3 Nov and are going fairly well. The basement, level one, level two, and level three have been completed, level four started. IBA is back on site to test windows including the outside chamber test to verify head conditions of the window system. d. Contractor's Schedule: not accepted as of November 2012 update. Schedule updates are being analyzed by NIBS and rejected. e. USACE estimated completion is 30 Jan 2015, but the Contractor will not finish by this date. There will be an overlap of the Hospital IO&T and IMF contractors and final Integrated Systems Commissioning and Final Inspections. The first furniture arrives on 12 January 2015. The contractor exceeded the required completion date of 13 May 2014. Liquidated damages are being withheld at $16,500 per calendar day. Corporate/senior manager engagement continues. A claim/request for Contracting Officer's Final Decision in the amount of $3,135,000.00 has been received and is under review. HFPA update and Council of Colonels meeting held on 16 December 2014.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 63864 | Health Clinic Add/Alt |  | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | W91DS-08-C-0019 | 27483 | 35963 | 2008-11-07 | 2012-12-01 | 2011-02-18 | 2013-12-12 | 100% |  |  | Financial closeout pending A-E Damages Resolution
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69626 | Burn Rehabilitation Center |  | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | W9126G-08-C-0036 | 18512 | 19120 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100% |  |  | Contract closeout ongoing.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 64473 | Medical/Dental Clinic |  | 2008-07-29 | 2008-09-18 | The Korte Company |  | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 100% | 1885 |  | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2014-12-31 | 2008 | Defense Health Agency | Major Military Construction |  | GERMANY | 52332 | Medical Clinic Replacement |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 100% |  |  | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. NAU will provide details on the claim.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 71653 | Hospital Replacement (ARRA) |  | 2010-06-11 | 2010-09-01 | Clark/McCarthy, JV | N62473 10 C 0001 | 418039 | 425895 | 2010-12-03 | 2013-10-17 | 2014-01-07 | 2014-01-07 | 100% |  |  | Multiple residual closeout issues.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 73599 | Hospital Renovation & MRI Addition (Cong Add) |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178 | 28389 | 2010-12-03 | 2015-03-04 | 2015-01-02 | 2015-03-04 | 89% |  |  | Active Project.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 55918 | Central Utility Plant |  | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034 | 13672 | 2009-10-01 | 2011-06-22 | 2011-02-07 | 2011-06-22 | 100% |  |  | Residual closeout issues.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 70350 | Hospital Alteration (ARRA) |  | 2011-07-26 | 2011-09-15 | Federal Contracting DBA Bryan Construction |  | 15929 | 20393 | 2011-11-08 | 2014-03-23 | 2013-11-27 | 2014-01-21 | 100%
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 70354 | Hospital Replacement (Supplemental) |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 159834 | 163146 | 2012-05-30 | 2017-07-16 | 2015-03-16 | 2017-05-15 | 30% |  |  | Structural steel set for completion on 19 JAN 2015 with the building shell to begin install early February 2015. PDT conintues to work toward intgerating the master schedule in order to better facilitate transition and outfitting processes. Additional $34M required in March 2015.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 79845 | Eglin Hospital Alteration (ARRA) |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction | W9126G-08-D-0057 | 51133 | 59385 | 2011-10-31 | 2015-03-12 | 2014-11-06 | 2015-01-26 | 95% |  |  | Current total obligations shown in column S are for ARRA MILCON only. Obligated ARRA MILCON amount $63,939,823.18/Disbursed Amount $62,269,851.84. Required completion date 21-Dec-14/Scheduled completion 26-Jan-15. Contractor is 36 days behind schedule. Contract including all currently identified modifications is at 99.58% of PA. Unknown extent of mold, rust and unforseen site conditions of areas to be renovated present a moderate to high risk that mandatory modifications will exceed PA. CT/PET RFP reissued and and received 17-Sep-14. Parts of scope still under discussion with AF medical comands. Contractor proposal of cost for CT/PET RFP is being reviewed by the Government. This date may be extended, area under partial suspension of work due to CT/PET equipment hold by AF. Surgery Suite Phase 3, Lab phase 2, B2794 Command Office scheduled for completion and move in. ENT and Plastics under construction. $560K REA is being discussed.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 59220 | Hospital Add/Alt (Supplemental) |  | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500 | 29108 | 2011-10-26 | 2015-06-01 | 2014-03-03 | 2015-05-26 | 71% |  |  | Curtain wall is being installed. Contractor provided schedule that work will be complete by the BOD.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) |  | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 76944 | 83404 | 2011-10-25 | 2015-03-18 | 2014-09-09 | 2015-03-18 | 96% |  |  | BOD will also be 18 March 2015. Ortho, ENT, Logistics and a small part of dining are all that remains. Project will finish well within the $4.88M funds.
2014-12-31 | [8 empty] | 2011-03-07 | 2011-03-20 | A1 Tree Service (Tree Cutting) | UNK | 9.6 | 9.6 | 2011-03-20 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 100% |  |  | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2014-12-31 | [8 empty] | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp (Swing Space) | W912QR-11-C-0027 | 5395 | 5395 | 2011-07-01 | 2015-03-18 | 2014-09-27 | 2015-03-18 | 99% |  |  | Leased Swing Space awarded for risk mitigation.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 62189 | Medical / Dental Clinic Replacement |  | 2008-10-27 | 2009-04-03 | Hensel Phelps |  | 47615 | 51375 | 2009-06-01 | 2012-06-04 | 2011-10-26 | 2012-02-09 | 100% |  |  | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) |  | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989 | 559532 | 2010-11-08 | 2015-07-17 | 2014-05-31 | 2015-06-30 | 90% |  |  | The government met with the contractor on 8 Dec 14 to discuss his revised schedule. The government now expects the contractor to be complete NLT 22 Jun 15, and has established the Hospital's BOD at 17 Jul 15. Intermediate dates have been established to facilitate furniture move-in in support of IO&T as well as help gauge the contractor's progress towards meeting his completion date. Contract CCD remains unchanged(23 Nov 14). Liquidated damages currently being assessed
2014-12-31 | [8 empty] | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc, Sanitary Sewer |  | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 100% |  |  | Construction 100% Complete
2014-12-31 | [8 empty] | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities | W9126G-10-C-0032 | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 100% |  |  | Construction 100% Complete
2014-12-31 | [8 empty] | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc., Demolition of Hood Stadium | W912DY-05-D-0011 | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 100% |  |  | Construction 100% Complete
2014-12-31 | [8 empty] | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. New Stadium | W9126G-09-D-0100 | 17290 | 15383 | 2011-01-06 | 2013-12-15 | 2012-06-29 | 2015-06-30 | 99% |  |  | Contractor working on additional punchlist items and close out documentation.
2014-12-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74728 | Hospital Replacement, Electrical Funding (100% ARRA) | 74650 | 2010-05-21 | 2010-06-11 | RMA Land Construction, Inc., Infrastructure, Electrical Distribution & Telecomm | W9126G-09-D-0100 | 9698 | 10156 | 2010-07-20 | 2012-09-20 | 2012-07-26 | 2012-09-20 | 100% |  |  | Construction 100% Complete
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement |  | 2010-06-16 | 2010-12-14 | Vinci Construction UK |  | 13098 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 100% |  |  | Estimated financial closure: 31 Dec 2014
2014-12-31 | [8 empty] | 2013-04-05 | 2013-06-15 | VolterFitzpatrick (Sidewalk) |  | 68 | 68 | 2013-07-01 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 100%
2014-12-31 | [8 empty] | 2014-08-20 | 2014-08-25 | Vinci Facilities (Entrance door amendments) |  | 69 | 69 | 2015-01-06 |  | 2015-01-30 | 2015-01-30 | 0% |  |  | Contractor has queried the original steelwork design, DIO currently investigating the query. No progress on site until resolved. DIO cannot close main project until this local order is complete.
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61401 | Boundary Gate at Nallin Pond |  | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075 | 10119 | 2011-01-12 | 2014-12-31 | 2013-01-10 | 2014-12-30 | 100% | 785 |  | 1354 was signed on 30 Dec 14 and included several punchlist items the the contractor is currently finishing. One item includes the final intersection top coat that will be installed once the temperature rises above 40 degrees. All pending modifications/REAs are settled. Remaining contg is $33k. Project is current within Congressional authority (NTE $12.692M).
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61536 | Emergency Service Center |  | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | W912DR-10-C-0087 | 13478 | 13858 | 2010-07-19 | 2013-05-23 | 2012-09-16 | 2013-05-23 | 100% |  |  | Expected to closeout March 2015.
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) |  | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | W912HN-11-C-0002 | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 100% | -458 |  | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14.
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 71318 | Dental Clinic Replacement |  | 2009-10-28 | 2010-02-26 | J E Dunn Construction Company | W9126G-08-D-0057 | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 100% | -3144.239 |  | Retainage on the project recently paid, processing close out. The project funds have been returned.
2014-12-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center, Phase 1 |  | 2010-06-11 | 2010-08-19 | J E Dunn Construction Company (Bldg 1 & CEP) | W9126G-08-D-0057 (TO 0005) | 41566 | 45105 | 2010-10-04 | 2013-11-19 | 2013-02-20 | 2013-08-30 | 100% |  |  | Building 1 is complete and turned over to the Air Force. BOD is 19 Nov 13. Interim DD 1354 has been signed by BCE 5 Dec 13. Closeout Correction and verification of punchlist deficiencies continues. Contractor working stone issue.
2014-12-31 | [8 empty] | 2010-06-11 | 2010-08-31 | J E Dunn Construction Company (Parking Structure & Temp Parking) | W9126G-08-D-0057 (TO 0006) | 23216 | 24153 | 2010-10-04 | 2012-12-13 | 2012-02-26 | 2012-11-30 | 100% |  |  | Phase 1A consisting of a multi-story parking garage and a Central Energy Plant is complete and turned over to the Air Force. BOD 13 Dec 2012. Fifteen remaining signs will be installed by Skanska once they remove the temporary partitions. SWF Structural Section has issued reports reviewing the stone block installation on Phase 1A and 1B. The Area Office is waiting on JE Dunn’s corrective action plan and schedule.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77116 | NNMC Parking Expansion |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 14030 | 14392 | 2012-06-18 | 2013-12-02 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77115 | Transient Wounded Warrior Lodging |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133 | 48829 | 2012-06-18 | 2014-05-27 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70482 | Health Clinic Addition/Alteration |  | 2010-11-19 | 2011-06-03 | McCarthy Building Companies | W912HN-11-C-0006 | 23050 | 26519 | 2011-06-21 | 2013-11-29 | 2013-06-20 | 2014-05-06 | 100% |  |  | Contingencies at District: $18,120. Final payment scheduled for 2 Mar 15.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MASSACHUSETTS | UNITED STATES | 71634 | Mental Health Clinic Addition |  | 2011-11-04 | 2011-12-23 | Watermark Environmental, Inc. | W912WJ-12-C-0002 | 2790 | 2790 | 2012-05-18 | 2013-02-16 | 2013-01-16 | 2013-03-01 | 100% |  |  | Final payment to Contractor in process.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 73360 | Consolidated Logistics Facility |  | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869 | 19957 | 2011-07-21 | 2014-12-05 | 2014-01-06 | 2014-11-14 | 100% |  |  | Punchlist item completion by mid Jan 15. Furniture funding for both CONLOG buildings was received; anticipating install Feb 2015.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 62886 | Information Services Facility Expansion |  | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | W912DR-12-C-0004 | 4270 | 4626 | 2012-03-19 | 2015-02-10 | 2013-11-09 | 2015-02-28 | 92% | 232 |  | Commissioning underway. Furniture contract awarded for installation 20 Jan 15. BTR of $232K from Health and Dental Clinics, White Sands to Information Services Facility, Ft. Detrick, MD executed on May 6, 2014.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67949 | NIBC Security Fending and Equipment |  | 2011-08-19 | 2012-02-14 | Cont #1 (Segment 1) (Rich Moe Enterprises, LLC) | W912DR-12-C-0001 | 1701 | 1701 | 2012-04-02 | 2013-04-01 | 2013-04-02 | 2013-04-01 | 100% |  |  | Project Closed.
2014-12-31 | [8 empty] | 2015-02-13 | 2015-05-29 | Cont #2 (Segment 2) (TBD) |  |  |  | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | 95% design under review. RTA date for Fence Segment 2 is 30 Jan 15. Contract solicitation will include USAMRIID Replacement North Parking which establishes overall site contours for fence construction. Combine with RID.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67953 | Supplemental Water Storage |  | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468 | 3944 | 2011-07-20 | 2015-04-30 | 2012-11-01 | 2014-05-30 | 97% | 263 |  | % Complete (Scheduled/Actual): 100/97 Contractor having difficulty completing pump facility. LD's being assessed. BOD slipped to 30 Apr 15 due to contractor performance and need to secure final MDE water system connection permit.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67951 | Water Treatment Plant Repair |  | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308 | 15540 | 2013-01-14 | 2015-04-30 | 2014-07-08 | 2014-11-17 | 87% | 5000 |  | % Complete (Scheduled/Actual): 99/87 BOD slipped due to city sewer connection and contractor performance. Commissioning underway. Potential CWE is showing 105% above PA.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 70472 | Health and Dental Clinic |  | 2010-11-02 | 2011-07-22 | Charpie-Korte Dsn-Bld JV S.B. L.L. |  | 14837 | 15067 | 2011-08-18 | 2013-04-26 | 2013-03-30 | 2013-08-02 | 100% | -1095 |  | CT final Payment made 25 NOV 14.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72752 | Ambulatory Care Center Phase 2 | 72430 | 2011-05-20 | 2011-09-28 | SKANSKA USA Building Inc. | W9126G-11-C-0053 | 80558 | 92460 | 2011-12-02 | 2015-03-15 | 2013-10-01 | 2015-02-03 | 96% |  |  | BOD of 15 Mar 2015. Phase 2 includes Buildings A, B & C. Different levels of MEP work are underway or finishing. Casework installation is ongoing. Punch list continues on exterior elevations. Central Energy plant equipment startup, testing, and commissioning is ongoing. Pending modifications will add additional time to the current contract completion date of 3 Feb 2015. The Area Office is working with Skanska to finalize this impact and definitize the delay. The pending modifications are mandatory to address RFIs or design errors. The construction completion date is expected to shift to mid-March, and the BOD to April or later.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 71251 | Dental Clinic Replacement |  | 2009-09-16 | 2011-05-17 | Forrester Construction Company |  | 2832 | 3185 | 2011-05-17 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | Fiscal Closeout is scheduled, and tracking for 13 Jan 2015, along with Project # 64241.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66693 | Health/Dental Clinic Replacement |  | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | W912GB-09-C-0029-NA | 34294 | 34376 | 2014-02-03 | 2016-06-11 | 2015-08-22 | 2016-04-12 | 28% |  |  | Concrete roof slab and bituminous membrane is substantially complete; roof installation is ongoing. Exterior window and heating line installation is ongoing. Interior plaster work is ongoing. Steel framing for the mechanical enclosure is ongoing. Parking lot curbstone and gutter installation.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66588 | Health Clinic Add/Alt |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany |  | 32103 | 32103 | 2013-04-08 | 2017-01-07 | 2016-04-12 | 04 Sep '16 | 60% |  |  | Interior mechanical & electrical work continues along with plumbing, ductwork and communications on the 1st and 2nd floor. Erecting walls and door frames on 1st and 2nd floors. Interior finish work continuing including painting, tiling, walls, and flooring. Construction of new lobby between existing and new clinic ongoing. Work on the building perimeter fire lane, new entry, and site grading is continuing. Final inspection and acceptabce of new Tennis Court on 17 Dec 14.
2014-12-31 | 2011 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 51740 | Health/Dental Clinic Replacement |  | 2011-05-13 | 2011-08-26 | Ilsung Construction Co., Ltd. | W912UM-11-C-0024 | 9821 | 10169 | 2011-08-26 | 2014-04-23 | 2013-05-13 | 2014-04-23 | 100% |  |  | The Carroll Dental Clinic OIC and NCOIC were in the lead for a ribbon cutting ceremony, however, per HFPO, a ceremony does not appear to be occurring. Awaiting return of excess funds from Huntsville Center for LOGCAT F procurement. Awaiting final billing from DLA for LOGCAT F equipment training.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 72727 | Medical/Dental Clinic Replacement |  | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd |  | 11958 | 11958 | 2014-05-06 | 2015-07-31 | 2015-10-30 | 2015-11-17 | 36% | 13060 |  | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65030 | Naval Hospital Great Lakes Health Clinic Demolition |  | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co | N40083 12 C 0001 | 5835 | 6195 | 2012-09-12 | 2014-04-21 | 2013-09-13 | 2014-08-08 | 100% | -3994
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 79554 | Child Development Center |  | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200 | 14457 | 2013-03-01 | 2014-04-07 | 2014-02-22 | 2014-06-02 | 100%
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71408 | Dental Clinic Replacement |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688 | 18688 | 2013-03-01 | 2016-12-06 | 2016-09-29 | 2017-01-28 | 0% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | MISSISSIPPI | UNITED STATES | 71503 | Branch Health Clinic |  | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Constr, Inc | N69450 12 C 0754 | 19096 | 19830 | 2012-09-01 | 2015-08-31 | 2014-09-09 | 2015-05-22 | 80%
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 70597 | Medical Clinic |  | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | W91278-12-C-0028 | 8897 | 9123 | 2012-10-17 | 2015-01-05 | 2014-10-07 | 2014-10-07 | 100% |  |  | Contingencies at District available for obligation $106,701. Project on schedule no issues.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 72292 | Hospital Addition/Alteration Phase 2 |  | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778 | 43913 | 2012-10-15 | 2017-06-14 | 2016-10-14 | 2017-02-17 | 66% |  |  | Design error (for exterior precast panels) required work stoppage to remove, redesign, & replace the panels. 145 days were added to the emergency dept interim milestone & 83 days to overall project completion. Contingencies at district: $572,510 of which $287,232 is for temp. swing space SAS investigating potential AE Liabilities.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70438 | Hospital Addition/Alteration |  | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company (DBA: Mortenson Construction) | W912QR-12-C-0036 | 43466 | 46171 | 2012-08-22 | 2015-05-23 | 2015-02-21 | 2015-03-25 | 84% |  |  | Curtain Wall - Flood Event Issue: Work continues to move forward with the KTR's Alternate Design. The exterior enclosure work has commenced at all locations with the framing and sheathing finishing up in all locations and air barrier to begin shortly. Still waiting to see a claim/REA from the Contractor that shows the cost impact due to the Curtain Wall issue. 21 2 day delay. Claim could cause an ATR if KO approves current amount of about $5M.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 70351 | Hospital Alteration |  | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400 | 23219 | 2012-09-13 | 2014-09-30 | 2014-06-23 | 2015-12-04 | 58% |  |  | Contractor behind schedule (Scheduled Progress is 95%). Contingencies at District: $154,325. Contractor has been issued an Interim Marginal CCASS. Contractor has had issues since June with resources and rework. Contractor has also experienced issues with properly managing and scheduling work on site. Quality Control has slipped as well causing undue rework thus additional schedule slip. Several face to face and telephone meetings have been held between SAS and upper level at R&M. Contractor has made some improvements between mid Aug and Sept with resources.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70580 | Dental Clinic Addition /Alteration |  | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | W91DS-13-C-0002 | 4370 | 4370 | 2013-01-09 | 2014-12-19 | 2015-01-09 | 2014-12-19 | 100% |  |  | BOD 19 DEC 14.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70579 | Medical Clinic (SFCC) |  | 2012-10-05 | 2013-02-13 | Structural Associates. Inc. | W912DS-13-C-0022 | 8934 | 8934 | 2013-03-15 | 2015-06-11 | 2015-03-11 | 2015-03-11 | 93% |  |  | Interior finishes being installed. Commisssioning to began 5 JAN 15.
2014-12-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 51969 | Hospital Nutrition Care Department Add/Alt |  | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | W9126G-12-C-0050 | 28291 | 26993 | 2012-10-02 | 2015-02-26 | 2014-10-30 | 2015-04-13 | 87% |  |  | Project RFP included a detailed equipment list which included the statement “For Information Only,” permitting the contractor to deviate from the equipment list, resulting in a design which changed the meal preparation and distribution operations and increased staffing. Health Facilities Planning Agency (HFPA) requested a redesign to eliminate these problems. The re-design resulted in a 283 day delay. The contractor's estimate was $1.5M greater than the government's. Negotiations concluded on 4 April without the contractor and government in agreement. The government issued a unilateral contract modification 9 April 14. *The contractor subsequently filed seven claims regarding this issue on 31 Sep 14, totaling $1,370,385. Total available contingency is6 currently $2,667,364. - KO reviewing claims for merit - OC extended response date to 15 Jan 2015.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 72808 | Medical Clinic Replacement |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc | N62473 10 D 5412 DO 0007 | 18703 | 18703 | 2014-02-28 | 2015-04-16 | 2015-03-16 | 2015-03-16 | 18%
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 78143 | Navy Drug Lab Replacement |  | 2013-01-14 | 2013-08-22 | Blinderman Constr Co | N40083 13 C 0003 | 14864 | 14785 | 2013-11-08 | 2015-02-15 | 2015-01-15 | 2015-04-18 | 89%
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71507 | Branch Health Clinic Replacement |  | 2013-02-28 | 2013-12-18 | Turner Construction Co | N40080 14 C 0154 | 41408 | 41451 | 2014-04-30 | 2015-11-18 | 2015-10-15 | 2015-11-18 | 20% |  |  | Groundbreaking is the 18 April 2014.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80307 | Implement Base Installation Appearance Plan |  | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898 | 4608 | 2014-04-01 | 2015-04-08 | 2015-03-31 | 2015-06-15 | 3%
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities |  | 2013-07-25 | 2012-09-12 | G-W Management Servicxes Inc (Dosimetry Award) | N40080 10 D 0498 DO 0025 | 5286 | 5217 | 2013-10-15 | 2014-04-04 | 2013-12-13 | 2014-03-25 | 100%
2014-12-31 | [8 empty] | 2014-03-15 | [12 empty] | On hold per DHA
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80308 | Electrical Utility Upgrades |  | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947 | 26947 |  | 2016-02-12 | 2016-02-12 | 2016-02-12 | 1% | 19460 |  | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 78144 | Medical Clinic Addition |  | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354 | 14586 | 2013-10-08 | 2015-03-31 | 2015-03-17 | 2015-07-08 | 73%
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71317 | Medical Clinic Replacement |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744 | 39996 | 2013-12-06 | 2016-03-18 | 2016-12-30 | 2017-08-16 | 27%
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 78146 | Veterinarian Facility |  | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254 | 7450 | 2014-02-28 | 2015-05-15 | 2014-12-06 | 2015-06-22 | 34%
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 51639 | USARIEM Replacement High Altitude Research Lab |  | 2015-07-30 | 2015-12-31 | [11 empty] | Received Code 7 Directive on 26 Jun 14. PM met with stakeholders the week of 28 Jul 14 to discuss the way forward and develop the revised design schedule. The most significant action impacting project completion will likely be the preparation of NEPA documents by the City of Colorado Springs. Will need Funds authorization extension. EXPECT CODE A request by 15 March 2015.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 72718 | Medical Logistics Warehouse Replacement |  | 2012-10-18 | 2013-06-18 | R&W Builders | W912QR-13-C-0021 | 2215.9 | 2215.9 | 2013-07-01 | 2014-07-30 | 2014-04-27 | 2014-07-23 | 100% |  |  | Contingency balance is zero. Closeout is in progress.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 71679 | Dental Clinic |  | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture |  | 10687 | 10505 | 2013-12-02 | 2015-04-29 | 2015-02-19 | 2015-02-19 | 85% |  |  | Commissioniong and Test and Balance begin 3 Secember 2014. Schedule: RMS shows 12% behind schedule. This is due primarily to high dollar placements pending (Dental Casework, Full BLDG Commissioning, as well as a large credit modification pending). LEED: Silver required (solar panels for domestic hot water and solar light tubing). Time Growth: None to date
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71325 | Medical Clinic Replacement |  | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536 | 47116 | 2013-10-24 | 2017-07-21 | 2016-04-30 | 2016-10-23 | 18% |  |  | Contractor continues with site work and site demo. Contingencies at District: $697,507.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77979 | Medical/Dental Clinic Replacement |  | 2013-09-03 | 2014-03-27 | JE DUNN + HWA | W9127S-13-D-6001 | 47044 | 47044 | 2014-04-28 | 2018-01-08 | 2017-10-25 | 2017-10-25 | 3% |  |  | REA adjustment for Gov't delay after award submitted by Contractor on 21 AUG 14. IGE for REA completed. Follow-up interviews with Med Group staff held 12 & 13 Nov. Submittal #1 (35%bldgd/ 60%site design)received and comments due 16 Jan. Review conference to be held week of 26 Jan.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 73776 | Soldier Specality Care Clinic |  | 2012-11-15 | 2013-12-18 | Structural Associates | W91DS-14-C-0003 | 11163 | 11163 | 2014-01-06 | 2016-04-05 | 2016-01-06 | 2016-01-06 | 22% |  |  | All "For Construction Documents" accepted and distributed. Contractor continues underground utility installation and construction of building foundation.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72420 | Medical/Dental Clinic Addition |  | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. | W912UM-13-C-0018 | 8544 | 8745 | 2013-06-05 | 2015-05-16 | 2015-02-25 | 2015-03-29 | 80% |  |  | Contingency Amounts: District $35,884; HQ Mgmt $166,412. 32 days have been added to the CCD, however, BOD has not been changed. User requested change (DIPC sterilizer purchase) approved by DHA. Contractor working on gypsum wall board, electrical conduit/wiring, and exterior civil work.
2014-12-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72419 | Hospital Addition/Alteration |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co., Ltd. | W912UM-13-C-0025 | 22361 | 22306 | 2013-09-26 | 2017-10-23 | 2017-08-08 | 2017-08-08 | 26% |  |  | Contingency Amounts: District $331,815; HQ Mgmt $847.596. Second level walls and roof formed. Structural steel work to start in Jan 2015. Temporary power ongoing. Phase 0 work began in Area 5.
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80904 | Mechanical & Electrical Improvements |  | 2014-01-30 | 2015-02-27
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80913 | Parking Garage |  | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835 | 15835 |  | 2016-04-16 | 2016-04-16 | 2016-04-16 | 0%
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77000 | Public Health Command Laboratory Replacement |  | 2014-03-24 | 2015-04-30 | [8 empty] | 0% |  |  | Project currently unawardable and undergoing Source Selection coordination (Procurement Sensitive). ATR package sumbmitted to DHA on 24 Dec 2014. Projected contract award and bids good to 30 Apr 2015.
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77922 | Medical Clinic Replacement |  | 2014-02-25 | 2014-08-20 | Gilbane | W9127S-13-D-6000 | 45629 | 45629 | 2014-10-27 | 2018-08-16 | 2018-01-30 | 2018-01-30 | 1% | 23279 |  | DB team working toward Submittal #1 scheduled for 7 Feb 2015.
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81340 | SAMMC Hyperbaric Facility Addition |  | 2014-03-17 | 2014-06-30 | Gilbane |  | 11289 | 11289 | 2015-07-10 | 2016-12-28 | 2016-09-30 | 2016-09-30 | 0% | 1900
2014-12-31 | 2014 | Defense Health Agency | Major Military Construction |  | BAHRAIN | 81436 | Medical/Dental Clinic Replacement |  | 2015-04-15 | 2015-08-15 | [11 empty] | On track for Aug 2015 award of a Design-Build contract with a one-year design period. This award schedule is being driven by site availability, pending completion of an on-going MCN project, the P908 Operations and Support Facilities, scheduled for completion in July 2016; expecting no additional schedule slippage. AE conducting a code update which will be complete by 31 Jan 2015; CWE will be re-validated upon completion of the code update and BCOE review. Expect to request Code A NLT 31 March 2015.
2014-12-31 | 2015 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 72414 | Dental Clinic Replacement |  | 2015-02-12 | 2015-04-25 | [11 empty] | Final draft RFP submittal review complete. Revising RFP to follow the last template.
2014-12-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81423 | Medical Clinic Replacement (Reid Clinic) |  | 2015-02-27 | 2015-06-15 | [5 empty] | 2017-12-31 |  | 2017-08-31 | 0% |  |  | 35% RFP review conference held 24 Nov 14. VE study delayed. RTA slipped to 27 Feb 15. No impact to 10 Jun 15 Award expected.
2014-12-31 | 2015 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 81430 | Hospital Add/CUP Replacement |  | 2015-07-09 | 2015-12-15 | [11 empty] | Received Code 7 on 16 Oct 13. Orginal scheduled AE1 contract award date was 30-APR-14. Actual award on 02-SEP-14. Primary cause for delay in award of the AE1 was conflicting scope requirements and level of design for the D-B RFP between DHA and the MX. The AE1 PoP to RTA provides an Advertise date of 01 June 2015. The construction contract will also include turnkey FFE and medical equipment. Thus increasing the procurement to > $50M. FY15 award is considered high risk due to the potential for an extended period (multiple rounds of discussion) for review of D-B contract proposals
2014-12-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 86944 | NiCOE Satellite, Infrastructure Support
2014-12-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 86943 | NiCOE Satellite, Infrastructure Support | [14 empty] | HNC conducted a Planning Charrette. District is validating 1391 and developing ENG3086 for approval.
2014-12-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81627 | NiCOE Satellite, Infrastructure Support | [14 empty] | HNC conducted a Planning Charrette. District is validating 1391 and developing ENG3086 for approval.
2014-12-31 | 2010 | Defense Intelligence Agency | Major Military Construction | ALABAMA | UNITED STATES | DIA10-002 | Replace MSIC Explosive Ordinance Exploitation (EOE) Complex |  | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company |  | 12000 | 12003 | 2012-07-20 |  | 2014-01-20 | 2014-05-21 | 100% |  |  | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved.
2014-12-31 | 2008 | Defense Intelligence Agency | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 154207 | Emergency Backup Water System |  | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC |  | 1012 | 1012 | 2009-10-03 | 2012-01-20 | 2011-09-16 |  | 100% |  |  | Approp. - $1,012
2014-12-31 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA11-002 | JBAB Paving of Gravel Parking Lot |  | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture |  | 2984 | 2819 | 2011-07-20 | 2012-07-25 | 2012-07-18 | 2012-07-25 | 99% | 700 |  | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2014-12-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000001 | DIAC Parking Garage Replacement |  | 2014-06-16 | 2014-09-23 | Arriba |  |  | 739156 | 2014-10-23 |  | 2016-03-02 | 2016-03-02 | 0% |  |  | Approp. - $13,645 - $793,156 CAT I obligated. NAVFAC Gold Team awarded the A/E contract in June 2013. Conducted the Design Charette on 18 July 2013. First NCPC, CFO and SHPO review conducted on 2 August 2013. Contract awarded on 23 September 2014. Concept Design Workshop was conducted on 20 November 2014.
2014-12-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center | [6 empty] | 1200 | [7 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-12-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000003 | DIAC Chilled Water Project for Data Center | [14 empty] | Approp. - $1,121 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-12-31 | [6 empty] | DIAC Cooling Tower for Data Center | [14 empty] | Approp. - $941 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-12-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | ECIP 120001 | Chiller Plant Operation |  |  | 2013-08-08 | Honeywell |  | 997 | 1071 | 2013-08-21 |  | 2014-08-08 | 2015-03-31 | 80% |  |  | Approp. - $1,200 - Project awarded August 2013. Kickoff meeting held 5 September 2013. All VFDs and field component sensors (flows, temperatures) have been installed. Optimization controls programming and graphics updates to be completed by January 2015. Commissioning (40 hours) will take place starting late February 2015. Training will be video-recorded per contract modification.
2014-12-31 | 2012 | Defense Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | DIA12000005 | Construction of Remote Delivery Facility (RDF) Meeting SCIF Standards |  | 2013-08-21 | 2013-09-25 | Heard Construction |  | 10758 | 6058 | 2013-10-10 |  | 2014-09-30 | 2015-03-11 | 46% |  |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Major construction activities last month were the floor slab placement, installation of roofing system, and exterior metal panels, and layout for interior partitions and MEP trim out. Once roof system is completed and exterior doors are installed (expected in mid-December), the facility will move to a "weathered in" condition and interior construction can move forward at a more rapid pace. Majority of final non-MILCON fitout work is now under contract; only about $160K of IT related work is not under contract as yet. Majority of increase in contract amount is due to unforeseen site conditions and extreme weather at key points in the construction schedule.
2014-12-31 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction |  | KOREA, SOUTH | DIA10-001 | FOB-K Renovation of Two Buildings to Include Administrative and SCIF Spaces |  | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd. |  | 4360 | 5050 | 2012-04-09 |  | 2013-10-09 | 2013-10-17 | 100% |  |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project in process of closeout.
2014-12-31 | 2013 | Defense Information Systems Agency | Major Military Construction |  | GERMANY | 13DISA01 | DISA Europe Facility Upgrade | [14 empty] | PA: $2.224M. Awaiting USACE to schedule Design Kick Off Meeting.
2014-12-31 | 2013 | Defense Information Systems Agency | Major Military Construction | ILLINOIS | UNITED STATES | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2014-03-01 |  | 2014-12-30 | 2016-03-01 |  |  |  | PA: $77.515M. Three (3) separate contracts: Soil Remediation $1.34M completed Feb 14; Construction $66M and Demolition of Bldg 3189 - TBD. Construction 45% completed.
2014-12-31 | 2014 | Defense Information Systems Agency | Major Military Construction | HAWAII | UNITED STATES | 14DISA01 | DISA Pacific Facility Upgrade | [14 empty] | PA: $2.615M. NAVFAC preparing RFP for Design.
2014-12-31 | 2008 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INC #1 - NAV SUP Fleet Logistics Center, Point Loma San Diego | DESC0704 | 2008-02-20 | 2008-09-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-12-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) - NAV SUP Fleet Logistics Center, Point Loma San Diego | DESC0704 | 2008-02-20 | 2011-03-22 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-12-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC0908 | Replace Jet Fuel Storage Complex - Jacksonville ANG | DESC0908 | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | W912EP-10-C-0023 | 7909 | 9988 | 2010-04-27 | 2014-04-10 | 2011-09-20 | 2014-09-30 | 99%
2014-12-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | KOREA, SOUTH | DESC0907 | Hydrant Fuel System - Osan AB | DESC0907 | 2010-01-12 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844 | 19441 | 2010-08-27 | 2015-02-02 | 2013-11-18 | 2014-11-15 | 97%
2014-12-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) - Pt. Loma | DESC0704 | 2008-02-20 | 2011-03-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-12-31 | 2011 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX0802 | Replace Headquarters Facility - New Cumberland | DDCX0802 | 2011-11-23 | 2012-08-17 | Walsh Construction | W912DR-12-C-011 | 80775 | 82555 | 2012-08-30 | 2016-02-29 | 2015-09-18 | 2016-01-20 | 73%
2014-12-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC0909 | Replace Fuel Pier - Craney Island | DESC0909 | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | N40085-11-C-0001 | 28815 | 32208 | 2012-11-26 | 2015-06-20 | 2014-07-03 | 2015-03-31 | 85% | -9428 |  | Rescinded by OSD 23 Mar 12
2014-12-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC0503 | Hydrant Fuel System - Misawa AB | DESC0503 | 2012-05-12 | 2012-09-22 | Tokyo Construction Co., Ltd. | W912HV-12-C-0013 | 25204 | 25425 | 2013-02-01 | 2015-06-20 | 2015-02-01 | 2015-03-01 | 95%
2014-12-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | UNITED KINGDOM | DESC0905 | Replace Hydrant Fuel System - RAF Mildenhall | DESC0905 | 2011-04-19 | 2011-12-06 | Spiecapag | DEUSFMIL/13232 | 12535.429 | 12535 | 2011-12-09 | 2014-04-25 | 2013-03-14 | 2014-05-02 | 99%
2014-12-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC1103 | Replace Hydrant Fuel System - Davis Montham AFB | DESC1103 | 2012-05-04 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 18252 | 19125 | 2012-11-13 | 2015-02-02 | 2014-11-03 | 2014-12-03 | 99%
2014-12-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1205 | Replace Fuel Facilities - San Clemente Is. | DESC1205 | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453 | 27610 | 2013-02-28 | 2015-03-11 | 2015-03-24 | 2015-07-01 | 69% | 10000 | FY09 Germersheim | 2853 Reprogramming
2014-12-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma | DESC0704 | 2008-02-20 | 2012-03-29 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08C-7501 | 15512 | 164864 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-12-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1102 | Public Safety Facility - Tracy | DDCX1102 | 2012-03-06 | 2012-07-16 | MASCON, INC | W91238-12-C-0021 | 14615 | 15091 | 2012-08-29 | 2014-12-05 | 2014-03-24 | 2014-12-07 | 100%
2014-12-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESI1101 | Alter Warehouse Space - JB PH Hickam | DESI1101 | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | N62478-11-D-4042/0004 | 5500 | 6430 | 2012-08-13 | 2014-09-30 | 2013-06-14 | 2014-04-29 | 99%
2014-12-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | MASSACHUSETTS | UNITED STATES | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB | DESC1102 | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 24480 | 25378 | 2013-06-18 | 2016-02-08 | 2016-02-02 | 2016-02-08 | 63% | 4500 | FY09 Hill, Hunter & Germersheim | 2853 Reprogramming
2014-12-31 | 2012 | DLA Defense Supply Center Columbus | Major Military Construction | OHIO | UNITED STATES | DSCC1201 | Security Enhancements - Columbus | DSCC1201 | 2012-02-19 | 2012-05-04 | Pinnacle Construction Development Group | W912QR-12-C-0031 | 8550 | 10318 | 2012-06-07 | 2014-09-15 | 2013-09-23 | 2014-12-24 | 99%
2014-12-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1203 | Upgrade Access Control Points - New Cumberland | DDCX1203 | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 16327 | 16327 | 2014-02-04 | 2016-03-21 | 2016-03-21 | 2016-03-21 | 8%
2014-12-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1202 | Replace General Purpose Warehouse - New Cumberland | DDCX1202 | 2012-09-17 | 2013-11-20 | Corothers Construction Inc. | W912DR-14-C-0005 | 24622 | 24622 | 2014-01-14 | 2015-10-23 | 2015-07-29 | 2015-07-29 | 60% | 3802 | FY 10 Duluth, FY11 Osan | 2853 Reprogramming
2014-12-31 | 2012 | DLA Defense Supply Center Philadelphia | Major Military Construction | PENNSYLVANIA | UNITED STATES | DSCP1201 | Upgrade HVAC System - Philadelphia | DSCP1201 | 2012-03-28 | 2012-06-01 | WU & Associates, Inc. | N40085-10-D-9451 | 4775 | 7240 | 2012-06-14 | 2014-04-29 | 2013-07-17 | 2014-06-06 | 99%
2014-12-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DESC1101 | Replace Fuel Storage Facility - Charleston AFB | DESC1101 | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | N694501-12-C-1757 | 26700 | 26485 | 2012-11-30 | 2014-12-30 | 2014-07-21 | 2014-11-26 | 98% | 5132 | FY10 Pt Loma, FY12 JB PH-Hickam & Barksdale | 2853 Reprogramming
2014-12-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WEST VIRGINIA | UNITED STATES | DESC12S1 | Replace Hydrant Fuel System - Camp Dawson | DESC12S1 | 2012-04-26 | 2012-07-05 | Kinley Construction Company | W9128F-10D-0052 | 1930 | 1945 | 2012-07-03 | 2015-04-13 | 2013-12-05 | 2015-04-14 | 99%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC13S4 | Replace Truck Unload Facility - Yuma | DESC13S4 | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322 | 1322 | 2013-09-30 | 2015-08-04 | 2014-08-03 | 2015-08-03 | 6% | 400 | FY12 Eielson | 2853 Reprogramming
2014-12-31 | 2013 | DLA Defense Reutilization and Marketing Service | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | DRMS12U2 | Warehouse 6 Distribution - Tracy | DRMS12U2 | 2013-05-01 | 2013-05-15 | Kinley Construction Company | W91238-10-D0036 | 925 | 925 | 2013-06-01 | 2014-10-18 | 2013-12-05 | 2013-12-25 | 100%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1304 | Replace Fuel Storage - Edwards AFB | DESC1304 | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513 | 19661 | 2013-11-20 | 2017-03-17 | 2016-10-18 | 2017-12-07 | 46%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC 1306 | Replace Fuel Pier - Pt Loma | DESC 1306 | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378 | 66378 | 2014-01-15 | 2017-10-14 | 2017-10-14 | 2017-10-15 | 27%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | DELAWARE | UNITED STATES | DESC1305 | Replace Truck Off-Load Facility - Dover AFB | DESC1305 | 2013-07-31 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800 | 1800 | 2013-12-06 | 2015-04-28 | 2015-02-27 | 2015-04-28 | 41%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1391 | Construct Fuel Storage Facility - Hurlburt AFB | DESC1391 | 2013-01-13 | 2013-08-01 | Nova Group Inc. | W91278-13-C1001 | 15952 | 15952 | 2013-10-31 | 2015-12-15 | 2015-09-14 | 2015-12-15 | 64%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC1203 | Replace Fuel Pier - GTMO | DESC1203 | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366 | 36366 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-09-28 | 32%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC13S3 | Replace Truck Loading Facility - GTMO | DESC13S3 | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961 | 1961 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 20%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | GUAM GU | GUAM | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB | DESC1303 | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364 | 52364 | 2014-06-30 | 2016-05-11 | 2016-02-06 | 2016-05-11 | 0%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | LOUISIANA | UNITED STATES | DESC1390 | Upgrade Pumphouse - Barksdale AFB | DESC1390 | 2012-10-30 | 2013-08-13 | Environmental Management Resources | N69450-10-D-0787 | 4311 | 4311 | 2013-09-09 | 2015-02-26 | 2015-02-26 | 2015-02-26 | 71%
2014-12-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | NORTH CAROLINA | UNITED STATES | DESC13S1 | Replace Transfer Fuel Line to Pump House #2 - Seymour Johnson | DESC13S1 | 2013-02-27 | 2013-07-09 | Shaw Environmental & Infrastructure, Inc. | W9128F-10-D-0073 | 1494 | 1542 | 2013-07-25 | 2014-10-13 | 2014-04-18 | 2014-10-21 | 99%
2014-12-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1301 | Replace Communications Building - New Cumberland | DDCX1301 | 2014-04-16 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 6800 | 6800 | 2014-10-10 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 1%
2014-12-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland | DDCX1303 | 2013-08-01 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9600 | 9600 | 2014-07-28 | 2016-03-06 | 2016-01-21 | 2016-01-04 | 7% | 5000 | FY10 Pt Loma, GTMO & Souda Bay; FY11 Pt Loma | 2853 Reprogramming
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC14U1 | Upgrades to Fuel Pier for Fire Protection - Pt Loma | DESC14U1 | 2014-06-01 | 2014-07-01 | CB&I Federal Services LLC | N62583-09-D-0130 TO-027 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0%
2014-12-31 | 2014 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1404 | General Purpose Warehouse - Tracy | DDCX1404 | 2014-06-23 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 1994 | 1994 | 2014-06-30 | 2016-04-04 | 2015-11-15 | 2016-06-03 | 0%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City | DESC11U2 | 2014-03-28 | 2014-04-24 | Gilbane Federal | N62583-09-D-0129 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 8%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1402 | Replace Fuel Pipeline - Jacksonville | DESC1402 | 2014-01-16 | 2014-04-17 | Industrial Power Systems | N69450-14-C-1255 | 5438 | 5438 | 2014-06-30 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 22%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC1504 | Upgrade Fuel Island - Hunter AAF | DESC1504 | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0001 | 13407 | 13407 | 2014-09-19 | 2016-03-12 | 2016-03-12 | 2016-03-11 | 1%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC14S2 | Replace Ground Vehicle Fueling Facility - Moody AFB | DESC14S2 | 2014-03-18 | 2014-04-14 | Pond Constructors Inc. | W9128F-14-D-0051 | 3780 | 3780 | 2014-05-15 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 9% |  |  | Additional Funds from FY12 Eielson
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC11U2 | Replace Ground Vehicle Fueling Facility - Atsugi | DESC11U2 | 2014-05-02 | 2014-07-29 | Ichibo Co. Ltd | W912HV-14-C-0002 | 1994 | 1994 | 2014-09-12 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW JERSEY | UNITED STATES | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst | DESC1501 | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637 | 8637 | 2014-10-30 | 2016-06-15 | 2016-06-15 | 2016-06-16 | 0%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NORTH DAKOTA | UNITED STATES | DESC1107 | Replace Fuel Pipeline - Minot AFB | DESC1107 | 2014-02-28 | 2014-06-13 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4092 | 4092 | 2014-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 1%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1561 | Replace Refueler Parking, Altus AFB | DESC1561 | 2014-03-10 | 2014-06-12 | Rockford Corporation | W9128F-10-D-0050 | 1917 | 1917 | 2014-07-11 | 2015-09-17 | 2015-09-17 | 2015-09-17 | 0%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | DESC1502 | 2014-06-09 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0070 | 32060 | 32060 | 2014-12-01 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 0%
2014-12-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island | DESC1405 | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749 | 8749 | 2014-11-30 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0%
2014-12-31 | 2007 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | DSO701 | Replace Ft Knox High School |  | 2007-04-03 | 2007-08-31 | BartonMarlow Company | W912QR-07-C-0059 / 2593359 | 16050 | 16149.241 | 2007-09-17 | 2009-10-08 | 2009-03-10 | 2009-12-04 | 100%
2014-12-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  | 2012-03-02 |  | Federal Republic of Germany | W912GB-12-C-0008 / 17387653 | 70600.7618 | 70600.7618 |  |  |  |  | 0%
2014-12-31 | 2010 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM 856 07 | New Elementary School |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764 | 20538.226 | 2012-08-01 | 2014-08-01 | 2013-12-14 | 2014-08-08 | 98%
2014-12-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) |  | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | W912GB-08-C-0046 / 14328568 | 15509.459 | 17705.0096 | 2011-05-09 | 2013-09-13 | 2013-01-19 | 2013-09-25 | 99%
2014-12-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46694.9233 | 48395 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 63%
2014-12-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513.9133 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 63%
2014-12-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 63%
2014-12-31 | 2010 | DoD Education Activity | Major Military Construction |  | BELGIUM | EUR 8318 09 | Replace School (SHAPE ES) |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414.6336 | 32998 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 99%
2014-12-31 | [8 empty] | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652.1853 | 1719.1947 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
2014-12-31 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School ( Boblingen HS) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869.3221 | 43600 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 64%
2014-12-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 64%
2014-12-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292.8744 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 64%
2014-12-31 | 2011 | DoD Education Activity | Major Military Construction | NEW YORK | UNITED STATES | AM2455205 | Construct Addition and Renovate West Point MS |  | 2011-07-18 | 2011-10-20 | Bernard Associates | W912DS-12-C-0001 / 25312318 | 23974 | 26098 | 2011-11-28 | 2014-03-17 | 2014-09-28 | 2014-03-17 | 99%
2014-12-31 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) |  | 2012-04-18 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260 | 27064 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 99%
2014-12-31 | [8 empty] | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843 | 6002 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
2014-12-31 | [8 empty] | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28674 | 29089 | 2012-08-01 |  | 2015-01-13 | 2015-01-30 | 87%
2014-12-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM8193 01 | Replace Elementary School (Antilles ES) |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968 | 51394 | 2012-07-18 |  | 2014-04-19 | 2015-04-30 | 56%
2014-12-31 | 2011 | DoD Education Activity | Major Military Construction | VIRGINIA | UNITED STATES | AM2455206 | Replace/Consolidate Elementary Schools |  | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297 | 43491 | 2012-09-29 |  | 2014-09-30 | 2015-06-01 | 85%
2014-12-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM100801 | Replace Elementary School (Murray ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121826 | 14851 | 16356 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 99%
2014-12-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AMD02051 | Replace Elementary School ( McNair ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121890 | 16413 | 17049 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 99%
2014-12-31 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB |  | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | W912HV-13-C-0002 / 29312081 | 9644 | 9750 | 2013-03-26 |  | 2015-07-25 | 2015-10-18 | 90%
2014-12-31 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00053 | Replace Elementary/Middle School (Ansbach EMS) |  | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 575 | 575 | 2013-10-28 |  | 2015-03-12 | 2015-05-29 | 42%
2014-12-31 | [8 empty] | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11783.7717 | 11873 | 2013-10-28 |  | 2015-03-12 | 2015-05-29 | 42%
2014-12-31 | 2012 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00020 | Replace Elementary School (Osan ES) |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187 | 29847 | 2013-09-30 |  | 2015-12-09 | 2016-03-01 | 23%
2014-12-31 | 2013 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00023 | Replace McBride Elementary School |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987 | 32987 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 23%
2014-12-31 | [8 empty] | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 23%
2014-12-31 | 2013 | DoD Education Activity | Major Military Construction | MASSACHUSETTS | UNITED STATES | AM00027 | Replace Hanscom Middle School |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 32260 | 32835 | 2014-02-11 |  | 2016-04-21 | 2016-08-19 | 24%
2014-12-31 | 2013 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00028 | Replace Barkley Elementary School |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39362 | 39373 | 2014-03-27 |  | 2015-12-17 | 2016-03-15 | 14%
2014-12-31 | 2012 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00026 | Replace Kingsolver/Pierce School |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685 | 32827 | 2014-03-11 |  | 2015-11-11 | 2016-01-30 | 11%
2014-12-31 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School |  | 2014-10-21 | 2014-03-07 | Federal Republic of Germany | W912GB-12-C-0007 / 33867035 | 0 | 0 | 2014-03-24 | 2014-08-11 | 2014-08-21 | 2014-08-30 | 13%
2014-12-31 | [8 empty] | 2014-10-21 | 2014-06-20 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 662 | 662 | 2014-09-30 |  | 2014-12-02 | 2015-04-29 | 13%
2014-12-31 | [8 empty] | 2014-10-21 |  | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 48926.0169 | 48954.4549 |  |  | 2017-04-22 | 2017-05-22 | 0%
2014-12-31 | 2012 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00025 | Replace Delalio Elementary School |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339 | 23372 | 2014-02-24 | 2016-06-01 | 2016-06-01 | 2017-05-20 | 26% |  |  | The occupancy date 1 Jun 16 is for the BOD of the school. This is the completion of Phase 1 of the project. The school can be occupied at this time. The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework itemsin the footprint of the school. The entire contract will be completed in May 17.
2014-12-31 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475 | 1475 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-12-31 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469 | 2469 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-12-31 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612 | 4612 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-12-31 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418 | 62418 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-12-31 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00062 | Netzaberg Middle School Addition |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 283 | 283 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 14%
2014-12-31 | [8 empty] | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366 | 5417 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 14%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00024 | Faith Middle School Addition |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4897 | 4897 | 2014-10-28 |  | 2016-01-21 | 2016-04-20 | 0%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00040 | Replace Marshall Elementary School |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 34748 | 34824 | 2014-08-06 |  | 2016-03-28 | 2016-05-27 | 9%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00038 | Diamond Elementary School Replacement |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40073 | 40073 | 2014-10-15 |  | 2016-09-14 | 2016-12-13 | 1%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00018 | Daegu Middle/High School Replacement |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28954 | 28954 | 2014-09-29 |  | 2016-10-03 | 2016-12-10 | 0%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00030 | Replace Zukeran Elementary School |  | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476 | 95476 | 2014-10-31 |  | 2016-11-30 | 2017-06-28 | 0%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00050 | White Elementary School Replacement |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791 | 31791 |  |  | 2016-10-18 | 2017-01-16 | 0%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00034 | Replace Fort Campbell High School |  | 2014-06-20 | 2014-10-31 | Walsh Group Ventures | W912QR-15-C-0001 | 55931 | 55931 |  |  | 2017-04-29 | 2017-04-29 | 0%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00031 | Pope Holbrook Elementary School |  | 2014-09-09 | 2014-11-26 | SAUER Incorporated | W91278-12-D-0039 | 32124 | 32124 |  |  | 2016-11-15 | 2016-11-15 | 0%
2014-12-31 | 2014 | DoD Education Activity | Major Military Construction | SOUTH CAROLINA | UNITED STATES | AM00037 | Replace Bolden-Galer Elementary School |  | 2014-07-25 | 2014-12-19 | Elkins Constructors, Inc. | N69450-15-C-1606 | 35705 | 35705 |  |  | 2016-12-27 | 2016-12-27 | 0%
2014-12-31 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00027 | Replace Yokota High School |  | 2014-07-25 | 2014-12-24 | Daiwa Odakyu Construction - JDC JV | W912HV-15-C-0002 | 40547 | 40547 |  |  | 2019-03-23 | 2019-03-23 | 0%
2015-12-11 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P646 | DSS Headquarters Addition |  | 2012-09-21 | 2013-03-29 | Hensel Phelps Construction Co. |  | 25149 | 28406 | 2013-04-30 | 2014-09-26 | 2014-07-22 | 2014-09-25 | 99% |  |  | [Solicitation/Advertise Date: Phase I - 21-Sep-2012 Phase II - 20-Dec-2012]
2014-12-12 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P659 | Defense Access Road Improvements-Telegraph Rd |  | 2013-01-22 | 2013-07-15 | Shirley Contracting Company, LLC |  | 2967 | 2967 | 2013-08-01 |  | 2014-08-01 | 2014-12-19 | 75% |  |  | This project is being managed and funded via FHWA. [Solicitation/Advertise Date: Phase I - 22-Jan-2013 Phase II - 04-Apr-2013] - UPDATE: The discovery of two underground storage tanks delayed the completion of the new storm drain system. Final paving activities may need to be delayed until Spring 2015 for a winter shutdown period.
2014-12-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 655 | Missile Test Vehicle Storage Facility |  | 2014-03-24 | 2014-05-09 | Arctic Slope Regional Corporation (ASRC) | W912DY-14-D-0042-0001 | 1832 | 1832 | 2014-06-17 | 2014-12-19 | 2014-12-11 | 2014-12-19 | 100% |  |  | Awaiting Interim 1354
2014-12-31 | 2010 | Missile Defense Agency | Major Military Construction | HAWAII | UNITED STATES | 627 | Aegis Ashore Missile Defense Test Complex |  | 2011-06-30 | 2011-08-03 | TOMCO CORP. | N62478-10-D-4024 | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 100% |  |  | Clearing and Grubbing Only
2014-12-31 | [8 empty] | 2012-01-19 | 2012-06-04 | URS GROUP, INC | N62742-09-D-1174 | 59616 | 69657 | 2012-07-04 | 2013-08-29 | 2013-09-12 | 2013-11-07 | 100% |  |  | GMAC Construction - awaiting Interim 1354
2014-12-31 | 2012 | Missile Defense Agency | Major Military Construction | ALABAMA | UNITED STATES | 633 | Von Braun Complex Phase IV |  | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | W91278-12-C-0017 | 51330 | 59842 | 2012-07-10 | 2014-06-26 | 2014-07-10 | 2014-10-15 | 100% |  |  | Awaiting Final 1354
2014-12-31 | 2013 | Missile Defense Agency | Major Military Construction | NEW YORK | UNITED STATES | 639 | In-Flight Interceptor Data Terminal Complex |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584 | 15270 | 2013-08-10 |  | 2014-11-28 | 2014-12-26 | 98% |  |  | Awaiting Interim 1354
2014-12-31 | 2013 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 81785 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 52% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2014-12-31 | 2014 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 646 | Aegis Ashore Missile Defense System Complex, Incr #2 | 630 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 28946 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 52% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2014-12-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300 | 13300 | 2014-07-07 |  | 2016-01-06 | 2016-01-06 | 30% |  |  | Awaiting Interim 1354
2014-12-31 | 2014 | Missile Defense Agency | Major Military Construction |  | JAPAN | 648 | AN/TPY-2 Radar Site |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991 | 12991 | 2014-05-27 |  | 2015-01-09 | 2015-01-09 | 88% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2014-12-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838 | 42838 | 2014-05-27 |  | 2016-05-31 | 2016-05-31 | 5% |  |  | Construction suspended for Winter; Awaiting Interim 1354
2014-12-31 | 2009 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060 | 13760 | 2010-09-21 | 2013-01-17 | 2013-01-17 | 2014-04-18 | 99%
2014-12-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223 | 124671 | 2010-09-21 | 2014-05-13 | 2014-04-18 |  | 93% | 37500 |  | Contract Completion date has not been negotiated yet
2014-12-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443 | 4544 | 2010-09-09 | 2012-06-29 | 2011-09-26 | 2012-06-29 | 100%
2014-12-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253 | 5702 | 2013-03-07 | 2014-09-30 | 2014-03-07 | 2014-12-09 | 98%
2014-12-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17781 | Tordella Chilled Water Backup Storage |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700 | 11700 | 2010-06-30 | 2012-05-30 | 2011-08-20 | 2012-05-30 | 100%
2014-12-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17782 | R&E Chilled Water Backup Storage |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200 | 3200 | 2011-11-07 | 2014-10-31 | 2013-07-13 | 2015-02-27 | 78% |  |  | Due to problems with Commissioning of chiller plant the tank has been pushed out to Aug 2015
2014-12-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18052 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566 | 8257 | 2011-03-31 | 2014-05-14 | 2013-02-01 | 2014-05-14 | 100%
2014-12-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18053 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095 | 16448 | 2012-01-31 | 2014-05-31 | 2013-02-01 | 2014-05-31 | 100%
2014-12-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18054 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085 | 7316 | 2012-11-30 | 2014-08-31 | 2013-02-01 | 2014-08-31 | 92% |  |  | Commissioning of system completed November 26, 2014.
2014-12-31 | 2011 | National Security Agency | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 22573 | Classified location |  | 2012-08-15 | 2012-09-30 | Kaseman |  | 12000 | 21500 | 2012-12-01 | 2013-10-01 | 2013-09-30 | 2014-03-15 | 100%
2014-12-31 | [8 empty] | 2012-08-01 | 2012-09-21 | Hardline |  | 12000 | 12000 | 2012-09-25 | 2012-09-15 | 2013-04-04 | 2013-04-04 | 100% |  |  | Placed in service 01-Oct-2013
2014-12-31 | [8 empty] | 2012-07-01 | 2012-07-30 | PAE |  | 200 | 200 | 2012-08-15 | 2012-09-15 | 2012-08-30 | 2012-08-30 | 100% |  |  | Placed in service 01-Oct-2013
2014-12-31 | 2011 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900 | 132488 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-01-16 | 98% | 50100 | Mountainview
2014-12-31 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 | MOD II |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657 | 8867 | 2012-05-30 | 2014-03-03 | 2014-01-30 | 2015-01-16 | 100%
2014-12-31 | [6 empty] | MOD II (Phase 2) |  | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620 | 2657 | 2013-11-26 | 2014-09-30 | 2014-02-28 | 2014-04-28 | 98%
2014-12-31 | [6 empty] | Whitelaw Wedge |  | 2012-04-26 | 2012-06-18 | JAAT | W912HN-10-D-0063 | 15315 | 16526 | 2012-07-18 | 2014-07-09 | 30-Ja n-14 | 2014-10-23 | 95%
2014-12-31 | 2012 | National Security Agency | Major Military Construction | COLORADO | UNITED STATES | 23051 | Mountainview |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975 | 125410 | 2012-11-02 | 2015-07-22 | 2015-05-03 | 2015-05-28 | 85%
2014-12-31 | [6 empty] | Mountainview |  | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621 | 5621 | 2013-10-13 |  | 2014-02-14 | 2015-09-30 | 100%
2014-12-31 | 2012 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 24649 | High Performance Computing Center 2 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589 | 591568 | 2013-03-12 | 2015-09-30 | 2015-09-16 | 2015-09-30 | 76%
2014-12-31 | 2013 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 26170 | East Campus Building 1 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91866 | 92192 | 2013-10-24 | 2016-01-05 | 2015-10-16 | 2015-10-16 | 15% |  |  | Corrected error in contract complete Date
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | ARIZONA | UNITED STATES | 53542 | Parachute Training Facility |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546.92 | 6546.92 | 2014-11-09 |  | 2016-05-09 | 2016-05-14 | 2%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60272 | Communications Training Complex (SWCS) |  | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN-10-D-0049 / 29371639 | 8290.317 | 8469.8948 |  |  | 2014-03-06 | 2015-02-02 | 96%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60821 | Squadron Headquarters Addition |  | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN-10-D-0060 / 29389201 | 10605 | 10918.0428 |  |  | 2014-06-06 | 2015-02-15 | 96%
2014-12-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 61064 | SOF Upgrade Training Facility |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951 | 13951 | 2014-11-17 |  | 2016-08-18 | 2016-08-18 | 1%
2014-12-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | 61772 | Operations Complex |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30155148 | 16751 | 17554.9517 | 2012-01-31 |  | 2013-04-25 | 2015-02-01 | 97%
2014-12-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64484 | Operations Additions |  | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | W912HN-11-C-0010 / 29379991 | 13388 | 15184.2497 | 2011-08-25 |  | 2014-06-10 | 2015-05-08 | 91%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 65052 | Medical Support Addition |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199.999 | 3283.4702 | 2013-10-16 |  | 2015-08-25 | 2015-04-17 | 69%
2014-12-31 | 2011 | Special Operations Command | Major Military Construction | GEORGIA | UNITED STATES | 65395 | Company Support Facility |  | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391.578 | 15637.173 | 2011-12-27 | 2014-05-30 | 2013-06-19 | 2014-07-31 | 99%
2014-12-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 66362 | C4 Facility - JSOC |  | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | W912HN-12-C-0009 / 29381338 | 41446 | 44322.4218 | 2012-06-14 |  | 2014-01-31 | 2015-06-16 | 99%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66597 | Landgraf Hangar Extension |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384.894 | 3384.894 | 2014-04-29 |  | 2015-10-21 | 2015-11-20 | 10%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66598 | Rotary Wing Hangar |  | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350 | 35208.168 |  |  | 2014-02-15 | 2015-04-15 | 93%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69382 | Civil Affairs Battalion Complex |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816 | 25816 | 2013-10-16 |  | 2015-08-14 | 2014-12-15 | 28%
2014-12-31 | 2014 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 69446 | Group Support Battalion Detachment |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083.965 | 15083.965 |  |  | 2016-02-18 | 2016-02-08 | 1%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 69447 | Group Support Battalion Detachment |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123.1802 | 22183.1802 | 2014-04-14 |  | 2016-02-13 | 2016-02-13 | 7%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69458 | Battalion Operations Complex |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772.305 | 16772.305 |  |  | 2014-06-03 | 2015-03-15 | 64%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69493 | Sustainment Bde Headquarters |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085 | 23085 | 2014-06-18 |  | 2016-05-02 | 2016-05-02 | 3%
2014-12-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69573 | Admin/Company Operations |  | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN-10-D-0058 / 29381912 | 8487 | 9166 | 2011-10-27 | 2013-11-21 | 2013-04-18 | 2014-01-23 | 99%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69758 | Brigade Headquarters |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 15649.974 | 16280.6264 |  |  | 2014-05-08 | 2015-05-09 | 47%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525.847 | 18617.616 |  |  | 2014-05-01 | 2015-03-01 | 87%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41071297 | 4506.8515 | 4506.8515 |  | 2014-05-01 | 2015-03-01 | 2015-03-01 | 87%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 76363 | Company Operations Facility |  | 2012-04-18 | 2012-08-30 | Adept-Absher 1 Joint Venture | W912DW-12-C-0037 / 27917342 | 18751 | 18626.363 | 2014-06-20 | 2014-06-20 | 2014-04-01 | 2014-06-21 | 99%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76364 | Battalion Operations Facility |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201.3031 | 33435.0071 |  |  | 2014-08-26 | 2015-06-01 | 75%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76366 | Company Operations Facility (GSTB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673.727 | 15674.302 |  |  | 2015-09-12 | 2016-04-26 | 79%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 76367 | SOF Battalion Operations Complex |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441 | 36461 |  |  | 2016-06-16 | 2016-07-20 | 1%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76371 | Company Operations Facility (GSB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092.801 | 17142.71 |  |  | 2015-09-12 | 2016-04-26 | 79%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 76374 | MH-47 Hangar |  | 2011-11-28 | 2012-05-07 | Hensel Phelps Construction Co. | W912QR-12-C-0035 / 28427841 | 32450 | 33728.627 | 2014-08-27 | 2014-08-27 | 2014-03-23 | 2014-08-29 | 99%
2014-12-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76375 | Civil Affairs Battalion Annexes |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358 | 27358 | 2014-11-14 |  | 2016-07-12 | 2016-07-12 | 0%
2014-12-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76376 | Language and Cultural Center |  |  | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696.6683 | 51696.6683 |  |  |  |  | 0%
2014-12-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 79438 | Combat Medic Skills Sustainment Course Bldg |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193.631 | 7193.631 |  |  | 2016-08-01 | 2016-08-01 | 0%
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 79655 | SOF Training Facility (4UMC) |  | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | W912PM-13-C-0003 | 1592 | 1592 | 2013-06-18 |  | 2014-10-15 | 2014-10-16 | 37%
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 80233 | SOF Live-Fire Training Tower (6UMC) |  | 2013-06-16 | 2014-01-22 | Trend Construction, Inc. | W912HN-12-D-0030-DQ04 | 1531.7653 | 1531.7653 | 2014-02-12 |  | 2015-05-15 | 2015-07-17 | 17%
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81483 | Mtn Climb/Rappel Tower (5UMC) |  | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F-13-C-0006 | 1513 | 1628 | 2013-09-20 |  | 2014-10-15 | 2014-09-15 | 99%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287a | Battalion Operations Complex |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907.435 | 30907.435 | 2013-10-09 |  | 2015-05-13 | 2015-10-24 | 30%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287b | Battalion Operations Complex |  |  | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404 | 21201 |  |  |  |  | 0%
2014-12-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033003 | Vehicle Maintenance Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30136034 | 4575 | 5123.2845 | 2012-01-31 |  | 2013-04-25 | 2015-03-15 | 97%
2014-12-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033005 | Storage Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154837 | 3603 | 3766.2116 | 2012-01-31 |  | 2013-04-25 | 2015-02-01 | 97%
2014-12-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033019 | Air Operations Center |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154494 | 2931 | 3078.5666 | 2012-01-31 | 2014-11-12 | 2013-04-25 | 2015-02-01 | 97%
2014-12-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063049 | Hangar / AMU (MC-130J) |  | 2011-05-13 | 2011-09-09 | Speegle Construction | W912PP-11-C-0029 / 30594756 | 19432 | 20310.9637 | 2011-10-11 | 2014-05-02 | 2013-12-01 | 2014-05-02 | 99%
2014-12-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13613.73 | 13829.0421 | 2012-09-06 | 2014-06-03 | 2013-07-17 | 2014-06-03 | 99% | 7132 | 66362
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073014 | SOF C-130 Sq Ops Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 25127091 | 7413 | 7874.8241 | 2014-07-11 | 2014-07-11 | 2014-02-22 | 2014-07-11 | 99%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073018 | SOF C-130 Wash Rack Hangar |  | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | W912PP-12-C-0025 / 30667913 | 9329 | 9703.7394 | 2014-09-09 | 2014-09-09 | 2014-04-10 | 2014-08-29 | 99%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073021 | SOF AMXS Facility |  | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | W912PP-12-C-0033 / 25138433 | 14700 | 14966.2684 | 2013-01-10 | 2014-09-22 | 2014-12-22 | 2014-09-19 | 99%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083012A | SOF Hangar/AMU |  | 2012-04-20 | 2012-08-31 | Hensel Phelps | W912PP-12-C-0027 / 30858121 | 28160 | 29105.547 | 2012-10-24 |  | 2014-12-23 | 2014-09-07 | 98%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083013 | Combat Parking Apron |  | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP-14-C-0014 / 32077093 | 19481.9877 | 19481 | 2014-06-13 |  | 2015-08-13 | 2015-11-22 | 77%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083016 | SOF Squadron Operations Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 28791332 | 10615 | 11040 | 2012-11-09 | 2014-05-30 | 2015-01-06 | 2014-05-30 | 99% | 2293 | CZQZ063035
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NEW MEXICO | UNITED STATES | CZQZ100221 | Parachute Drying Tower (3 UMC) |  | 2014-03-06 | 2014-07-01 | Speegle Construction | W912PP-14-C-0017 / 39136021 | 1547 | 1547 | 2014-07-28 |  | 2015-05-24 | 2015-05-24 | 12%
2014-12-31 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV083002 | Add/Alter Operations Facility |  | 2014-05-26 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048.867 | 7048.867 |  |  | 2016-08-03 | 2016-05-24 | 0%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV103011 | SOF Simulator Facility |  | 2012-05-01 | 2012-08-09 | Barlovento LLC. | W91278-10-D-0072 | 5551 | 5543 | 2012-09-13 | 2014-07-18 | 2013-12-24 | 2014-07-18 | 99%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTFA113004 | SOF AvFID Ops and MX Facilities |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942.3 | 29974.109 | 2013-11-05 |  | 2016-12-01 | 2016-12-25 | 21%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | NVZR083702 | Joint Special Operations University Facility |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753.0246 | 24836.9926 | 2013-11-04 |  | 2015-09-15 | 2015-06-28 | 17%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1049 | Range 130 Support Projects |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129 | 8130 | 2013-06-03 |  | 2014-11-13 | 2014-11-13 | 11%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1174 | MWD Facility |  | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | N6247311D0068 #0003 | 3075 | 3302 | 2012-10-03 | 2014-11-14 | 2014-03-23 | 2014-11-14 | 99%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1218 | Marine Battalion Company/Team Facilities |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46370 | 2014-02-20 |  | 2016-03-01 | 2016-01-18 | 39%
2014-12-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1391 | SOF Sustainment Training Complex |  | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333 #0004 | 27546.924 | 27546.924 |  |  | 2016-09-02 | 2016-09-02 | 2%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1393 | Survival Evasion Resistance Escape Trng Fac |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46370 | 2014-02-20 |  | 2016-01-18 | 2016-01-18 | 39%
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1410 | SOF EOD Expansion (1UMC) |  | 2013-09-04 | 2013-09-26 | Quadrant Construction, Inc | N4008510D0261 #0017 | 1566 | 1566 | 2013-10-15 |  | 2014-09-22 | 2014-09-22 | 83%
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1450 | Fires Platoon Storage Facility (7UMC) |  | 2013-12-20 | 2014-02-13 | Quadrant Construction, Inc | N4008510D0261 #0019 | 1459.25 | 1469 | 2014-03-13 |  | 2014-12-13 | 2014-12-10 | 87%
2014-12-31 | 2014 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1469 | MSOB Support Facilities |  | 2014-08-20 | 2014-09-30 | Quadrant Construction, Inc | N4008510D0261/0022 | 1751.362 | 1751.362 |  |  | 2015-09-25 | 2015-09-25 | 0%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-164 | Logistics Support Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727 | 11727 | 2012-12-09 |  | 2014-07-24 | 2015-06-16 | 77%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-165 | CS/CSS Support Facility |  | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351 | 9845 | 2014-10-06 |  | 2015-09-09 | 2015-11-26 | 41%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-473 | SEAL Team Operations Facility |  | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366 | 23866 | 2014-08-13 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 29%
2014-12-31 | 2012 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-504 | SOF Operational Vehicle Storage Facility (6UMC) |  | 2013-03-12 | 2013-05-23 | Richard Brady & Associates, Inc. | N4008511D6591 #0010 | 1660 | 1730 | 2013-12-03 | 2014-10-20 | 2014-10-20 | 2015-01-15 | 85%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | ALASKA | UNITED STATES | P-531 | Cold Weather Maritime Training Facility |  | 2012-04-30 | 2012-09-27 | Alutiiq Diversified Service, LLC | N4425512C3011 | 17449 | 17449 | 2014-03-04 |  | 2015-04-15 | 2015-04-15 | 95%
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-564 | NSWG-4 Paraloft Addition (2UMC) |  | 2013-06-14 | 2013-09-27 | Royce Homeland JV, LLC | N4008512D6305 #0005 | 1308 | 1319 | 2013-10-15 |  | 2014-12-31 | 2014-12-31 | 72%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-769 | Building Renovation |  | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022 | 3968 | 2013-01-02 | 2014-08-27 | 2014-06-27 | 2014-10-26 | 93%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-826 | Military Working Dog Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139 | 4139 | 2012-12-09 |  | 2014-07-24 | 2014-07-24 | 99%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-876 | Indoor Dynamic Shooting Facility |  |  | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290 | 24290 |  |  | 2016-10-01 | 2016-10-01 | 0%
2014-12-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-888 | Close Quarters Combat Range, Phase II |  |  | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489 | 12489 |  |  | 2016-09-30 | 2016-09-30 | 0%
2014-12-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH043055 | SOF Training Facility |  | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN-10-D-0063 / 25189640 | 4773.799 | 4752.7374 | 2012-05-31 | 2014-10-29 | 2013-11-22 | 2014-10-19 | 99%
2014-12-31 | 2010 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Upgrade Electrical System |  | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power |  | 23269 | 23269 | 2013-11-07 | 2015-02-05 | 2015-02-05 | 2015-02-05 | 2% | 4719 | PERC-$437, Fuel Storage Fac-$200, Secondary UPS-$300, FY11 P&D-$3,782 | Design/Build - 100% design in progress
2014-12-31 | 2010 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Secondary UPS |  | 2010-06-16 | 2010-09-27 | Iron Bridge Construction |  | 5192 | 7515 | 2010-09-27 | 2013-07-31 | 2012-02-29 | 2014-07-30 | 99% | 0 |  | Closeout in progress
2014-12-31 | 2011 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Power Plant Modernization Phase 3 (WPP) |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. |  | 43594 | 43741453 | 2013-04-22 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 18% | -4001 |  | Project at 100% design, funds absconded by sequester
2014-12-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Metro Entrance Facility/Visitor Screening Facility |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. |  | 5609 | 5609 | 2013-11-01 | 2015-06-01 | 2015-06-01 | 2015-06-01 | 13% | 0 |  | Design/Build - Not affected by sequester
2014-12-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Secure Access Lane (SAL) |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC |  | 5454 | 5454 | 2013-11-01 | 2015-05-01 | 2015-05-01 | 2015-05-01 | 4% | 0 |  | Award Contract Base Bid Items 28 Sep 2013; All options, for DIACAP $31,093, Perimeter Fence and 3 Vehicle Gates $138,693 and Public Rest Room (OPA funded) $447,766 awarded; NTP estimated by 1 Feb 2013. 510 cds contract duration.
2014-12-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Heliport Control Tower/Fire Station | [12 empty] | 0 |  | In 35% design.
2014-12-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Memorial Plaza | [12 empty] | 0 |  | Design contract award 26SEP13. NTP 1 Nov13. Design 8 mos/Construct 12mos. Contract duration 540 cds
2014-12-31 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | MISSOURI | UNITED STATES | NGA021 | Data Ctr West #1 Power & Cooling Upgrade |  | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors |  | 8202 | 11198 | 2012-08-06 | 2014-01-21 | 2013-08-06 | 2015-01-31 | 99% | N/A |  | Technology Center Third Floor Fit-out - project period of performance extended to 31 January 2015
2014-12-31 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | NGA013 | Technology Center Third Floor Fit-out |  | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 32387 | 39495 | 2012-11-02 | 2014-05-30 | 2014-01-02 | 2015-01-31 | 99% | 1975 | NGA021 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 31 January 2015
2014-12-31 | 2007 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES |  | Infrastructure Increments 1-3; NGA HQ's | [8 empty] | 2011-09-15 | 2013-06-15 | 2/31/2015 | 99% |  |  | ["Various" for Solicitation Date, Award Date, Start Date, Prime Contract Recipient (Company Name); "N/A" for Original Contract Amount, Current Contract Obligation, Diverted Funds Amount]
2014-12-31 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 65416 | NGA Headquarters, SCIF, All Phases |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 1181439 | 1398710 | 2007-09-06 | 2011-04-19 | 2011-12-22 | 02/31/2015 | 99% |  |  | ["N/A" for Diverted Funds Amount]

## DETAILED EXPENDITURES
Data as of Date | Fiscal Year | Component | Appropriation Fund Type | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Current Expenditure Amount ($000) | Remarks
2014-12-31 | 2006 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773.86 | 281956.1925 | 281662.7882
2014-12-31 | 2007 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232 | 329307.8469 | 329274.3414
2014-12-31 | 2008 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 259262 | 238598.4841 | 227987.9171
2014-12-31 | 2009 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513.728 | 207293.8625 | 164694.1449
2014-12-31 | 2010 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558 | 59490.8566 | 59488.5618
2014-12-31 | 2011 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192.95 | 53397.0155 | 37535.1029
2014-12-31 | 2012 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407 | 21828.5443 | 20987.6876
2014-12-31 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936.577 | 2534.3422 | 1029.8791
2014-12-31 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093 | 40753.6909 | 66.3957
2014-12-31 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 592614 | 592503 | 592503
2014-12-31 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - P.L. 111-5) | 16455 | 16455 | 16455
2014-12-31 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 529950 | 510499 | 508553
2014-12-31 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 544423 | 514109 | 512405
2014-12-31 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 448450 | 434123 | 428246
2014-12-31 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 468480 | 445103 | 400140
2014-12-31 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 417568 | 316002 | 189253
2014-12-31 | 2006 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782.96 | 26780.9748 | 26317.8729
2014-12-31 | 2006 | Air Force Active | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 63753.948 | 58353.2036 | 57487.5165
2014-12-31 | 2006 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 1530 | 0 | 0
2014-12-31 | 2007 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12896.1514 | 12677.2917
2014-12-31 | 2007 | Air Force Active | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 74021 | 72956.5581 | 72112.0236
2014-12-31 | 2007 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 2225 | 2206.9737 | 2206.9737
2014-12-31 | 2008 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12161.823 | 12161.823
2014-12-31 | 2008 | Air Force Active | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 30148 | 29576.7563 | 29188.6112
2014-12-31 | 2008 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 21054 | 13130.6247 | 13130.6247
2014-12-31 | 2009 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703 | 7593.62 | 7524.9478
2014-12-31 | 2009 | Air Force Active | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105196.1872 | 103703.1322 | 102193.183
2014-12-31 | 2010 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302 | 1440.5783 | 1396.5783
2014-12-31 | 2010 | Air Force Active | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 87562 | 87229.5766 | 84550.5745
2014-12-31 | 2010 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 25223 | 21494.5143 | 21441.8299
2014-12-31 | 2011 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153 | 3921.568 | 3915.9807
2014-12-31 | 2011 | Air Force Active | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 63903.328 | 61212.4568 | 56611.4374
2014-12-31 | 2011 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 2622 | 1854.0467 | 1854.0467
2014-12-31 | 2012 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056 | 4019.4525 | 4000.4976
2014-12-31 | 2012 | Air Force Active | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 78413 | 71137.6402 | 63526.2866
2014-12-31 | 2013 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3111.514 | 0 | 0
2014-12-31 | 2013 | Air Force Active | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 410.408 | 367.934 | 119.7052
2014-12-31 | 2014 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267 | 0 | 0
2014-12-31 | 2014 | Air Force Active | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314 | 9781.3495 | 7463.3155
2014-12-31 | 2006 | Air Force Reserve | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289.57 | 5289.1201 | 5289.1201
2014-12-31 | 2007 | Air Force Reserve | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109 | 5072.4629 | 5072.4629
2014-12-31 | 2008 | Air Force Reserve | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300 | 5270.7978 | 5270.7978
2014-12-31 | 2009 | Air Force Reserve | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165 | 6133.5834 | 6123.2565
2014-12-31 | 2010 | Air Force Reserve | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139 | 8001.7193 | 2824.1754
2014-12-31 | 2011 | Air Force Reserve | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649.694 | 1521.061 | 1521.061
2014-12-31 | 2012 | Air Force Reserve | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200 | 2037.9502 | 1322.0536
2014-12-31 | 2013 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875.201 | 1453.0932 | 485.3755
2014-12-31 | 2014 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229 | 0 | 0
2014-12-31 | 2006 | Air National Guard | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006 | 28020.5334 | 28018.597
2014-12-31 | 2007 | Air National Guard | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050 | 19043.34 | 19043.3394
2014-12-31 | 2008 | Air National Guard | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721 | 10619.0353 | 10619.0353
2014-12-31 | 2009 | Air National Guard | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056 | 19056 | 18961.6956
2014-12-31 | 2010 | Air National Guard | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670.441 | 19574.2109 | 19346.0434
2014-12-31 | 2011 | Air National Guard | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195.572 | 8638.9962 | 8568.8521
2014-12-31 | 2012 | Air National Guard | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225 | 12010.566 | 11046.6758
2014-12-31 | 2013 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994.721 | 3425.0242 | 2475.8628
2014-12-31 | 2014 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400 | 5076.2151 | 689.743
2014-12-31 | 2006 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15769.71 | 15283.0716 | 15073.8774
2014-12-31 | 2007 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14163.2777 | 14163.2777
2014-12-31 | 2008 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14081.4775 | 13525.7208
2014-12-31 | 2009 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14860.6296 | 14295.169
2014-12-31 | 2010 | Air Force Active | Unspecified Minor Military Construction [UMMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 12073.1657 | 11595.7213
2014-12-31 | 2010 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000 | 19867.8576 | 19836.9435
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction [UMMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 49584 | 39101.5746 | 24915.3188
2014-12-31 | 2011 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17964 | 17502.4646 | 16932.6922
2014-12-31 | 2012 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000 | 19483.0646 | 14302.0189
2014-12-31 | 2013 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 11130.1387 | 3991.1429 | 1523.4505
2014-12-31 | 2014 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448 | 0 | 0
2014-12-31 | 2006 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960 | 3959.9996 | 3959.9996
2014-12-31 | 2007 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477 | 4476.9716 | 4476.9716
2014-12-31 | 2008 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909 | 4909 | 4909
2014-12-31 | 2009 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443 | 5442.927 | 5442.927
2014-12-31 | 2010 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 752.8898 | 752.8898 | 752.8898
2014-12-31 | 2011 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2745.819 | 2728.9494 | 2651.5972
2014-12-31 | 2012 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4594.3732 | 4216.3096 | 2843.2031
2014-12-31 | 2013 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997.361 | 355.6 | 0
2014-12-31 | 2014 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530 | 0 | 0
2014-12-31 | 2006 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882 | 6882 | 6882
2014-12-31 | 2007 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000 | 5999.9999 | 5999.9999
2014-12-31 | 2008 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184 | 14183.984 | 14168.9847
2014-12-31 | 2009 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243 | 34163.725 | 33881.6744
2014-12-31 | 2010 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913.559 | 44875.1933 | 36878.3513
2014-12-31 | 2011 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984 | 7710.1992 | 5655.1967
2014-12-31 | 2012 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000 | 8665.1272 | 4701.7083
2014-12-31 | 2013 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892.214 | 3162.1387 | 769.9911
2014-12-31 | 2014 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000 | 687.6255 | 0
2014-12-31 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000 | 24000
2014-12-31 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000 | 25000
2014-12-31 | 2011 | Army Active | Host Nation Support | $29,944 Appropriated + $13,000 ATR | 42944 | 42932 | 42904
2014-12-31 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR + $9,000 ATR | 36000 | 35152 | 33961
2014-12-31 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954 | 33764 | 32641
2014-12-31 | 2014 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000 | 22729 | 21310
2014-12-31 | 2015 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33000 | 2757 | 2155
2014-12-31 | 2009 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 21855 | 21855 | 21855
2014-12-31 | 2010 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 28393 | 28392 | 28387
2014-12-31 | 2011 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 37328 | 37328 | 37311
2014-12-31 | 2012 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 34342 | 34265 | 34263
2014-12-31 | 2013 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 28124 | 27971 | 27860
2014-12-31 | 2014 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 21949 | 20926 | 15599
2014-12-31 | 2015 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 3000 | 2485 | 1170
2014-12-31 | 2010 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 60100 | 14055 | 14043
2014-12-31 | 2011 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 78330 | 1274 | 1274
2014-12-31 | 2009 | Army Active | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 218974 | 216654
2014-12-31 | 2009 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 576 | 576 | 524
2014-12-31 | 2010 | Army Active | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250415 | 246803
2014-12-31 | 2010 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 3936 | 3935 | 2503
2014-12-31 | 2011 | Army Active | Planning and Design | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 308676 | 262996 | 256125
2014-12-31 | 2011 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 2036 | 1990 | 1367
2014-12-31 | 2012 | Army Active | Planning and Design | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 191927 | 178559
2014-12-31 | 2012 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 7897 | 6908 | 6845
2014-12-31 | 2013 | Army Active | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46112 | 45188 | 40072
2014-12-31 | 2013 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 4635 | 149 | 147
2014-12-31 | 2014 | Army Active | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575 | 33865 | 22730
2014-12-31 | 2014 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 4408 | 0 | 0
2014-12-31 | 2009 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28750 | 28278 | 25954
2014-12-31 | 2010 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 31250 | 31149 | 29775
2014-12-31 | 2011 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28704 | 26450 | 26382
2014-12-31 | 2012 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 20000 | 19043 | 18601
2014-12-31 | 2013 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 23868 | 15579
2014-12-31 | 2014 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 22007 | 2240
2014-12-31 | 2009 | Army National Guard | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 60944 | 60943 | 60943 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2009 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 21880 | 21880 | 21880 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 47210 | 47210 | 47210 | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2010 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 36905 | 36905 | 36905 | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Planning and Design | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25604 | 24287 | 24287 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2011 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14215 | 11220 | 11220 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Planning and Design | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191 | 17250 | 17250 | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2012 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14149 | 13841 | 13841 | PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Planning and Design | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17 | 2407 | 1771 | 1771 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2014-12-31 | 2013 | Army National Guard | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25748 | 2971 | 2971 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2013 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14562 | 14254 | 14254 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-12-31 | 2014 | Army National Guard | Planning and Design | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930 | 2558 | 2558 | PL 113-76 P&D Recission
2014-12-31 | 2014 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 12240 | 2576 | 2576
2014-12-31 | 2015 | Army National Guard | Planning and Design | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 17600 | 0 | 0
2014-12-31 | 2015 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 13720 | 0 | 0
2014-12-31 | 2011 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 853 | 744 | 741
2014-12-31 | 2012 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719 | 566 | 566
2014-12-31 | 2013 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455 | 419 | 398
2014-12-31 | 2014 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463 | 0 | 0
2014-12-31 | 2015 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2014-12-31 | 2011 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 11087 | 10771 | 10771
2014-12-31 | 2012 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 25327 | 23561 | 20842
2014-12-31 | 2013 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 17441 | 16715 | 265
2014-12-31 | 2014 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 24253 | 15632 | 0
2014-12-31 | 2015 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2014-12-31 | 2011 | Navy Active | Planning and Design | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 2340 | 2229 | 2229
2014-12-31 | 2012 | Navy Active | Planning and Design | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2447 | 2377 | 2367
2014-12-31 | 2013 | Navy Active | Planning and Design | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609 | 684 | 660
2014-12-31 | 2014 | Navy Active | Planning and Design | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975 | 0 | 0
2014-12-31 | 2015 | Navy Active | Planning and Design | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2014-12-31 | 2011 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 27773 | 24966 | 24900
2014-12-31 | 2012 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 68661 | 48120 | 45071
2014-12-31 | 2013 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 42739 | 24278 | 2976
2014-12-31 | 2014 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 44716 | 28894 | 0
2014-12-31 | 2015 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2014-12-31 | 2011 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 136314 | 136312 | 126756 | [Component: Navy-MC Active]
2014-12-31 | 2012 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 83943 | 83694 | 79652 | [Component: Navy-MC Active]
2014-12-31 | 2013 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 96888 | 88620 | 58790 | [Component: Navy-MC Active]
2014-12-31 | 2014 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638 | 44854 | 34104 | [Component: Navy-MC Active]
2014-12-31 | 2015 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 16684 | 6988 | 6882 | Appropriated Amount reflects funds allocated to date only. [Component: Navy-MC Active]
2014-12-31 | 2011 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20757 | 20064 | 18679 | [Component: Navy-MC Active]
2014-12-31 | 2012 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20919 | 19792 | 18028 | [Component: Navy-MC Active]
2014-12-31 | 2013 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 15612 | 13300 | 6146 | [Component: Navy-MC Active]
2014-12-31 | 2014 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 19740 | 11490 | 415 | [Component: Navy-MC Active]
2014-12-31 | 2015 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 3582 | 0 | 0 | Appropriated Amount reflects funds allocated to date only. [Component: Navy-MC Active]
2014-12-31 | 2011 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1854 | 1854 | 1854 | [Component: Navy-MC Reserve]
2014-12-31 | 2012 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478 | 2148 | 2148 | [Component: Navy-MC Reserve]
2014-12-31 | 2013 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995 | 1994 | 1991 | [Component: Navy-MC Reserve]
2014-12-31 | 2014 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2540 | 864 | 853 | [Component: Navy-MC Reserve]
2014-12-31 | 2015 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15 [Component: Navy-MC Reserve]
2014-12-31 | 2011 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 2194 | 1632 | 1548 | [Component: Navy-MC Reserve]
2014-12-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 1947 | 1237 | 1171 | [Component: Navy-MC Reserve]
2014-12-31 | 2013 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2014-12-31 | 2014 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2014-12-31 | 2015 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | No funds yet allocated for FY15 [Component: Navy-MC Reserve]
2014-12-31 | 2012 | Defense Finance and Accounting Service | Planning and Design | Investigation and Design | 1992 | 748 | 709
2014-12-31 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction [UMMC] | Construction | 15404 | 12903 | 3059
2014-12-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 3979 | 3979 | 3979
2014-12-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 5547 | 3984 | 3944
2014-12-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4673 | 2733 | 2477
2014-12-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 5930 | 4755 | 4714
2014-12-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4608 | 2981 | 1317
2014-12-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 9578 | 554 | 24
2014-12-31 | 2009 | Defense Health Agency | Planning and Design | P&D Funding of MILCON Projects | 171255 | 170626 | 166035
2014-12-31 | 2010 | Defense Health Agency | Planning and Design | P&D Funding of MILCON Projects | 72679 | 72577 | 68480
2014-12-31 | 2011 | Defense Health Agency | Planning and Design | P&D Funding of MILCON Projects | 193126 | 132260 | 99883
2014-12-31 | 2012 | Defense Health Agency | Planning and Design | P&D Funding of MILCON Projects | 209957 | 3660 | 3520
2014-12-31 | 2013 | Defense Health Agency | Planning and Design | P&D Funding of MILCON Projects | 97411 | 0 | 0
2014-12-31 | 2014 | Defense Health Agency | Planning and Design | P&D Funding of MILCON Projects | 244 | 0 | 0
2014-12-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Parking Garage Replacement | 1498 | 461 |  | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $416K (CORRECTED AMOUNT) obligated as CAT I. Contract awarded on 23 September 2014.
2014-12-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Chilled Water Project for Data Center | 125 |  |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.
2014-12-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Cooling Tower for Data Center | 105 |  |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.
2014-12-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for UPS for Data Center Installation | 120 | 120 |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 100% design completed.
2014-12-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for Construction of JUIAF RDF | 1195 | 1195 |  | $1,195 obligated as CAT I acceptance. Design complete.
2014-12-31 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2224000 |  |  | DISA Europe Facility Upgrades
2014-12-31 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 77515000 | 62283147 | 19486000 | Construct New DISA Facility Scott AFB
2014-12-31 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2616000 |  |  | DISA Pacific Facility Upgrade
2014-12-31 | 2009 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2009 to 2013 | 4338 | 4334 | 4334
2014-12-31 | 2009 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2009 to 2010 | 4093 | 4027 | 4027
2014-12-31 | 2010 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2010 to 2015 | 12548 | 12446 | 12446
2014-12-31 | 2010 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2010 to 2014 | 4078 | 4078 | 4078
2014-12-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2012 to 2016 | 36093 | 35951 | 35951
2014-12-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2011 to 2014 | 4968 | 3996 | 3996
2014-12-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of project from 2012 to 2016 | 34331 | 34330 | 34330
2014-12-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2012 to 2014 | 6312 | 5431 | 5431
2014-12-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of project from 2014 to 2017 | 18308 | 10301 | 10301
2014-12-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] |  | 6686 | 0 | 0
2014-12-31 | 2008 | DoD Education Activity | Planning and Design | Design Efforts FY09 RCI MILCON projects | 3298 | 3348 | 3295 | RCI-Residential Communities Initiative
2014-12-31 | 2008 | DoD Education Activity | Planning and Design | Design efforts for FY 08/09/ 10/11/12 MILCON projects | 1863 | 1863 | 1863
2014-12-31 | 2009 | DoD Education Activity | Planning and Design | Design Efforts FY09 RCI MILCON projects | 1830 | 1830 | 1830
2014-12-31 | 2009 | DoD Education Activity | Planning and Design | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 5000 | 5000 | 5000
2014-12-31 | 2009 | DoD Education Activity | Planning and Design | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 6793 | 6793 | 5622
2014-12-31 | 2010 | DoD Education Activity | Planning and Design | Design efforts for FY 10/11/ 12/13 MILCON projects | 8829 | 8829 | 8717 | Reflects Sequestration Reduction
2014-12-31 | 2011 | DoD Education Activity | Planning and Design | Design efforts for FY 11/12/ 13 MILCON projects | 7840 | 7840 | 7840
2014-12-31 | 2011 | DoD Education Activity | Planning and Design | Design efforts for FY 11/12/13 MILCON projects | 70826 | 70826 | 53991 | Reflects Sequestration Reduction
2014-12-31 | 2012 | DoD Education Activity | Planning and Design | Design efforts for FY 12/13 MILCON projects | 64551 | 64465 | 45360 | Reflects Sequestration Reduction
2014-12-31 | 2013 | DoD Education Activity | Planning and Design | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 76472 | 24171 | Reflects Sequestration Reduction
2014-12-31 | 2014 | DoD Education Activity | Planning and Design | Design efforts for FY 14/15/16/17 MILCON projects | 75905 | 0
2014-12-31 | 2009 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5 | 4 | 4 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2014-12-31 | 2013 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 3771 | 0 |  | Reflects Sequestration Reduction
2014-12-31 | 2014 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5409 | 0
2014-12-31 | 2011 | Missile Defense Agency | Planning and Design | Design MDA FY15-16 MILCON Projects | 1186 | 1186 | 0 | Funds tranferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2014-12-31 | 2012 | Missile Defense Agency | Planning and Design | Design MDA FY13-14 MILCON Projects | 8368 | 8368 | 8124 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2014-12-31 | 2013 | Missile Defense Agency | Planning and Design | Design MDA FY13-14 MILCON Projects | 4191 | 4191 | 3835 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-12-31 | 2014 | Missile Defense Agency | Planning and Design | Design MDA FY14-16 MILCON Projects | 10891 | 7816 | 5198 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-12-31 | 2015 | Missile Defense Agency | Planning and Design | Design MDA FY16-17 MILCON Projects | 58704 | 3024 | 0 | Supports design of the Aegis Ashore Poland site.
2014-12-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY13/14 | 2243 | 2038 | 422 | Supports the R&C Piping project at Fort Greely, AK and the Storage Facility, Meck Island. $1.186M transferred to DHA in April 2014 for swap of FY11 P&D funds. $205K returned to OSD in Sep 2014.
2014-12-31 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000 | 155 | 2 | Supports the Storage Facility, Meck Island project.
2014-12-31 | 2010 | National Security Agency | Planning and Design | Generators 10 & 11 | 440 | 440 |  | MIPR 12-045 from MHS to AFCEC, $240K moved from Power & Cooling
2014-12-31 | 2010 | Special Operations Command | Planning and Design | MILCON Design Work | 4344 | 4331
2014-12-31 | 2011 | Special Operations Command | Planning and Design | MILCON Design Work | 26469 | 24860
2014-12-31 | 2012 | Special Operations Command | Planning and Design | MILCON Design Work | 30308 | 27617
2014-12-31 | 2013 | Special Operations Command | Planning and Design | MILCON Design Work | 25454 | 13697
2014-12-31 | 2014 | Special Operations Command | Planning and Design | MILCON Design Work | 36866 | 8048
2014-12-31 | 2010 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 6011 | 6010
2014-12-31 | 2011 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 7531 | 7526
2014-12-31 | 2012 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 8487 | 8039
2014-12-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 9216 | 8695
2014-12-31 | 2014 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 5170 | 982
2014-12-31 | 2012 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Data Center West #1 Power & Cooling Upgrade | 9253 | 8202 | 11198 | $1.975M MIPR'd from NGA013. Period of performance exteneded to 31 Janurary 2015.
2014-12-31 | 2012 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | NCE Tech Center 3rd Floor Fit-out | 54625 | 32387 | 39495 | Period of performance exteneded to 31 Janurary 2015.