## PROJECTS
Data as of Date | Fiscal Year | Component | Construction Project Type | State | Country | Project Number | Project Title | Parent Project Number [Initial Appropriation] | Solicitation Date | Award Date | Prime Contract Recipient (Company Name) | Prime Contract Number | Original Contract Amount ($000) | Current Contract Obligation ($000) | Start Date | Placed-In-Service Date | Original Completion Date | Current Completion Date | Percent Complete | Diverted Funds Amount ($000) | Diverted Funds Recipient Project | Remarks
2015-02-28 | 2006 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR064009 | Improve Family Housing, Ph C |  | 2007-08-01 | 2007-12-06 | Bilfinger Berger | C 04-1006BB | 1801.8135 | 1893.4955 | 2007-12-17 |  | 2008-07-13 | 2013-02-22 | 99%
[9 empty] | 2007-08-01 | 2007-12-06 | OBG | C 04-1006OBG | 1118.3451 | 1171.5011 | 2007-12-17 |  | 2007-12-06
2015-02-28 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALDA053001B | Multi-Aircraft Maintenance Hanger |  | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 15238.069 | 17873.5099 | 2011-03-01 |  | 2011-10-11 | 2015-10-31 | 99%
2015-02-28 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALUA073008A | Facility Replacements |  | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244.838 | 31385.3491 | 2011-03-01 |  | 2011-10-11 | 2015-10-31 | 99%
2015-02-28 | 2008 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR084014 | Improve Family Housing, Ph E |  | 2012-08-21 | 2013-05-17 | MICKAN | C07-1003 | 4638.8202 | 5011.6997 | 2013-07-08 |  | 2014-05-02 | 2015-03-31 | 99%
2015-02-28 | 2008 | Air Force Active | Military Family Housing Improvement |  | TURKEY | LJYC084001 | Improve Family Housing 515 Units |  | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970.0225 | 42315.6545 | 2012-03-08 |  | 2012-08-15 | 2015-07-19 | 37%
2015-02-28 | 2009 | Air Force Active | Unspecified Minor Military Construction |  | TURKEY | AKNR041053 | CNS Replace Asf Admin Bldg 2621 |  | 2011-02-22 | 2011-09-23 | MATOC Contractor | W912GB09D00690007 | 1367.06 | 1367.06 | 2012-02-15 |  | 2012-09-17 | 2015-02-01 | 13%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 28766.5445 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT033003 | Consol Communications Facility |  | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248.94 | 11773.483 | 2011-01-03 | 2014-09-12 | 2013-09-20 | 2015-09-01 | 95%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD063003 | Ground Control Tower |  | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | N6274209D1186HC08 | 7379.329 | 7423.376 | 2013-02-20 |  | 2014-01-30 | 2015-06-05 | 85%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF063009 | Replace Munitions Storage Area |  | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464.83 | 10753.2604 | 2011-06-23 |  | 2013-03-05 | 2015-08-09 | 92%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG081001 | Land Acquisition North & South Boundaries |  | 2012-05-09 | 2012-09-12 | In-House Work Force-NWK | PN-329217-LAWAFB | 3474.5 | 3474.5 | 2012-09-12 |  | 2014-03-06 | 2015-03-27 | 95%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | MONTANA | UNITED STATES | NZAS003000A | Upgrade Weapons Storage Area |  | 2012-04-23 | 2012-11-28 | RSCI | W912DW13C0013 | 9474.72 | 9462.564 | 2013-12-09 |  | 2014-10-19 | 2015-05-15 | 76%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | XTLF033303 | Control Tower |  | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849.633 | 9592.0332 | 2010-10-05 |  | 2012-01-11 | 2015-06-04 | 97%
2015-02-28 | 2010 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | MUHJ053008 | West & Lasalle Gates Force Protection/Access |  | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185.824 | 8498.0821 | 2010-07-07 | 2013-07-19 | 2011-12-17 | 2015-09-03 | 99%
2015-02-28 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA103001 | Construct Network Control Center |  | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | W912ER12C0028 | 2579.93 | 3160.1562 | 2012-08-19 |  | 2013-09-08 | 2015-06-01 | 76%
2015-02-28 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA107000 | Coalition Compound Billeting |  | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272.835 | 44795.7978 | 2012-06-05 |  | 2014-03-17 | 2015-03-16 | 85%
2015-02-28 | 2010 | Air Force Active | Major Military Construction |  | TURKEY | LJYC003006 | Consolidated Community Center |  | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | W912GB09D00690003 | 7880.644 | 8179.6972 | 2013-01-15 |  | 2011-09-22 | 2015-01-04 | 46%
2015-02-28 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100031 | Construct Maintenance Operations Center And Command Post |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671.642 | 1986.1406 | 2011-09-19 |  | 2012-01-31 | 2015-07-19 | 93%
2015-02-28 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100120 | Construct SatCom Facility |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136.701 | 1184.0301 | 2011-09-19 |  | 2011-01-31 | 2015-07-19 | 93%
2015-02-28 | 2010 | Air Force Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | XDAT073008 | Construct Military Working Dog & Supporting Facility |  | 2011-07-25 | 2011-09-28 | IE PACIFIC INC | N62473-07-D-2008 | 1620 | 1620 | 2012-02-27 | 2013-02-21 | 2012-09-27 | 2013-02-22 | 99%
[9 empty] | 2014-07-18 | 2014-07-18 | CREW MW | FA442710D01022058 | 71.771 | 71.771 | 2014-07-18 |  | 2014-09-16
2015-02-28 | 2011 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083008 | Repair Central Heat And Power Plant Boiler |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 30243.0655 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
2015-02-28 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV063501 | AMARG Hangar |  | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282.136 | 23098.357 | 2011-09-12 | 2014-08-22 | 2013-07-17 | 2015-03-30 | 95%
2015-02-28 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093000 | F-35 Academic Training Center |  | 2012-04-18 | 2012-08-30 | Archer Western Contractors | W912PL12C0017 | 43347.122 | 48110.6819 | 2012-11-05 |  | 2014-01-31 | 2015-03-31 | 99% | 575 | PRQE145121;
[9 empty] | 2012-04-18 | 2014-09-27 | KWR Construction, Inc | W912PL14D00300002 | 587.608 | 587.608 |  |  | 2014-12-26
2015-02-28 | 2011 | Air Force Active | Major Military Construction | COLORADO | UNITED STATES | XQPZ084017 | Const Center For Character & Leadership Development |  | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995.5 | 25002.256 | 2013-01-15 |  | 2014-06-12 | 2015-04-30 | 65%
2015-02-28 | 2011 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | SXHT053001 | Air Force Technical Applications Center |  | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231.0449 | 146271.6009 | 2011-07-06 | 2014-03-03 | 2015-12-02 | 2015-12-02 | 98%
[9 empty] | 2013-09-27 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99.768 | 99.768 | 2014-02-13 |  | 2014-08-02
2015-02-28 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R3 | Recruit Dormitories Phase 3 |  | 2010-12-06 | 2011-09-20 | Satterfield & Pontikes Const Inc. | W9126G11C0024 | 45885.001 | 46354.6403 | 2011-09-20 |  | 2013-10-31 | 2016-06-15 | 98% | 4894 | KRSM103011;
[9 empty] | 2011-09-02 | 2011-11-08 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 95.464 | 95.464 | 2011-11-08 |  | 2011-12-08
[9 empty] | 2012-05-09 | 2012-05-29 | Raba-Kistner Consultants | PNASA1205700 | 1.8889 | 1.8889 | 2012-05-29 |  | 2012-06-09
[9 empty] | 2012-05-09 | 2012-08-09 | Federal Pogram Integrators, LLC - JSR Inc. | W912BV11C0038 | 6886.921 | 7267.8431 | 2012-08-09 |  | 2014-04-04
[9 empty] | 2012-09-06 | 2012-10-19 | Federal Program Integrators, LLC with JSR Inc. | W9126G11C0009 | 175.3584 | 175.3584 | 2012-10-19 |  | 2013-06-01
[9 empty] | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06
[9 empty] | 2012-02-15 | 2014-06-25 | American Eagle Protective Services Corp. | W9126G12C0017P0002 | 97.8954 | 97.8954 | 2014-06-25 |  | 2015-01-31
[9 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00190007 | 1792.428 | 1792.428 | 2014-10-10 |  | 2015-09-05
[9 empty] | 2010-12-06 | 2014-11-10 | AE Merrick & Company-Tittle 2 Svs $59,036x3 | W9126G08D00060053 | 177.1085 | 177.1085 |  |  | 2014-11-10
2015-02-28 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 |  | 2011-02-25 | 2011-06-30 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 25985.138 | 27567.6015 | 2011-09-05 |  | 2013-04-20 | 2015-06-15 | 98%
[9 empty] | 2011-03-07 | 2011-07-08 | LB-KBR Gen Cntr (duplicate entry w/correct contract#) | W9126G11C00270000 | 0 | 0 |  |  | 2011-07-08
[9 empty] | 2011-03-07 | 2012-10-31 | Merrick & Company (Tittle II Services) $59,036.40 | W9126G08D00060054 | 118.073 | 118.073 | 2012-10-31 |  | 2012-10-31
[9 empty] | 2012-12-12 | 2013-06-03 | Federal Pogram Integrators, LLC - JSR Inc. | W9126G13C0098 | 334.244 | 152.927 | 2013-06-03 |  | 2014-01-18
[9 empty] | 2012-02-15 | 2014-01-16 | American Eagle Protective Services Corporation | W9126G12C00170001 | 97.8954 | 202.009 | 2014-01-16 |  | 2015-01-31
2015-02-28 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR083001 | Deicing Fluid Storage & Dispensing Facility |  | 2012-05-10 | 2011-09-02 | LBB | W912GB10C0001 | 2671 | 2783.6637 | 2012-11-13 |  | 2012-12-25 | 2015-08-31 | 96% | 155 | KRSM103011; | Removed for contract correction
[9 empty] | 2012-05-10 | 2012-09-26 | Peter Gross GmbH | W912GB-10-C-0001A | -530.298 | -530.298 | 2012-11-13 |  | 2013-04-14
2015-02-28 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR123063 | C-130J Flight Simulator Facility |  | 2013-08-12 | 2011-09-02 | LBB (EBC AWD) | W912GB-10-C-002EB | 7112.8996 | 7366.6972 | 2014-01-06 |  | 2011-09-02 | 2015-03-23 | 95% |  |  | Removed for contract correction
[9 empty] | 2013-08-12 | 2013-11-13 | OBG Hochbau GmbH & Co. KG | W912GB10C0002 | -949.3042 | -949.3042 | 2014-01-06 |  | 2014-10-23
2015-02-28 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFU083507R2 | Dormitory (128 Rm) |  | 2013-08-30 | 2011-09-16 | LBB (EBC AWD) | W | 17945 | 17945 | 2014-06-16 |  | 2013-09-05 | 2015-11-12 | 20% |  |  | Removed for contract correction
[9 empty] | 2013-08-30 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | -1693.1044 | -1693.1044 | 2014-06-16 |  | 2015-05-29
2015-02-28 | 2011 | Air Force Active | Major Military Construction |  | ITALY | ASHE083011 | Air Support Operations Squadron (ASOS) Facility |  | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N33191-07-D-0211 | 7174.1698 | 8164.7297 | 2011-12-16 |  | 2013-06-20 | 2015-07-31 | 80% | 1453 | KRSM103011;
2015-02-28 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006B | Blatchford-Preston Complex, Phase III |  | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177.236 | 34672.9582 | 2012-09-27 |  | 2014-05-15 | 2015-09-30 | 39%
2015-02-28 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility |  | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | W912ER11D00010007 | 40848 | 41335.1979 | 2013-08-07 |  | 2015-08-30 | 2015-09-16 | 92%
2015-02-28 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA113001 | Theater Communications Facility |  | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912.5671 | 10408.1954 | 2012-06-01 |  | 2014-04-02 | 2015-07-31 | 57%
2015-02-28 | 2011 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ114127 | Improve Family Housing, Ph 11 |  | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621.7601 | 65174.5107 | 2012-10-24 |  | 2015-08-27 | 2015-11-07 | 83%
[9 empty] | 2011-05-09 | 2012-03-19 | OTIE Milwauke, WI; *Title 2 Contract support* | FA890308D878200014 | 1896.559 | 1896.559 |  |  | 2012-03-19
[9 empty] | 2011-05-09 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan) *ArchTestDigs* | FA5270-12-P-0058 | 50.1855 | 50.1855 | 2012-10-24 |  | 2012-07-01
[9 empty] | 2011-05-09 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT* | FA5270-12-P-0080 | 72.2669 | 72.2669 | 2012-10-24 |  | 2012-07-31
[9 empty] | 2011-05-09 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | FA5270-12-FA-045 | 319.4136 | 319.4136 | 2012-10-24 |  | 2012-09-12
[9 empty] | 2011-05-09 | 2014-06-11 | OSC Solutions, Inc. (West Palm Beach, FL) **Appliances** | FA5270-14-P-0055 | 401.3565 | 401.3565 |  |  | 2014-06-11
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR106261 | PL-1 Security Measures For Communications Compound |  | 2013-09-17 | 2013-11-13 | Mikan | C11-4014 | 1840.2888 | 1840.2888 | 2014-01-22 |  | 2014-08-10 | 2015-04-30 | 97%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA110032 | Fuel Truck Parking |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730.623 | 1730.623 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113002 | Fuels Laboratory |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557.438 | 1557.438 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113005 | C-17 Spare Parts Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572.399 | 1572.399 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113006 | High Mast Lighting |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573.056 | 1573.056 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113009 | Entry Control Point |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615.612 | 615.612 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113010 | Cryogenics Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216.4 | 1216.4 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113012 | ELRS Storage Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615.533 | 1615.533 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120037 | Clinic |  | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhab,i UAE) | W912BU13C0060 | 1514.583 | 1553.273 | 2014-09-29 |  | 2015-01-20 | 2015-06-05 | 6%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120057 | Fire Protection Water Storage |  | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120.38 | 1120.38 | 2014-09-15 |  | 2014-11-24 | 2015-07-03 | 30%
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF124001 | EOD Facility |  | 2013-07-18 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1044.893 | 1044.893 | 2014-08-08 |  | 2015-08-14 | 2015-12-03 | 2% |  |  | Original contract terminated for default
2015-02-28 | 2011 | Air National Guard | Major Military Construction | TENNESSEE | UNITED STATES | BKTZ069078 | TFI- Renovate Intel Squadron Facilities |  | 2013-09-20 | 2013-11-21 | Codell Construction Company | W912L710D00060037 | 6.074 | 6.592 | 2013-12-02 | 2014-09-29 | 2014-10-17 | 2014-10-17 | 0%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083005 | Dormitory (168 RM) |  | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061.944 | 33061.944 | 2014-08-26 |  | 2016-08-02 | 2016-08-15 | 2%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) |  | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805.3 | 56312.187 | 2012-06-19 |  | 2014-06-19 | 2015-11-11 | 70% | 19165 | ALUA073006B; YWHG111005; WWYK143004A; ZHTV053302;
[9 empty] | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230.2925 | 3230.2925 | 2012-06-26 |  | 2013-09-27
[9 empty] | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978.8077 | 4978.8077 | 2012-06-26 |  | 2013-08-28
[9 empty] | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874.106 | 2191.91 | 2012-07-02 |  | 2012-11-20
[9 empty] | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799.2288 | 1799.2288 | 2012-07-27 |  | 2013-01-23
2015-02-28 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY983202 | Air Freight Terminal Complex |  | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | N6274210D1308JQ01 | 30047.253 | 32396.9728 | 2012-07-18 |  | 2014-05-14 | 2015-06-05 | 90%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility |  | 2011-12-30 | 2012-04-28 | Pacific West Builders | N4019210D28100003 | 9490.73 | 9433.61 | 2012-05-14 | 2014-08-15 | 2013-10-07 | 2015-03-31 | 99% | 2100 | ZHTV053302;
2015-02-28 | 2012 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB105002 | Mission Support Group Complex |  | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998 | 18717.5021 | 2012-03-26 |  | 2013-09-17 | 2015-01-16 | 99%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG071005 | WSA Security Control Facility |  | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172.6 | 4300.1692 | 2012-03-16 | 2014-08-15 | 2013-08-20 | 2015-08-15 | 98%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | NEBRASKA | UNITED STATES | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 102754.426 | 103646.2323 | 2012-10-15 |  | 2016-08-15 | 2016-09-12 | 39%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103003 | Communications Network Control Center |  | 2011-11-17 | 2012-04-24 | A4 Construction | W912PL12C0008 | 9326.701 | 9655.444 | 2012-12-01 | 2014-05-01 | 2014-04-24 | 2015-05-15 | 95% | 800 | ZHTV053302;
2015-02-28 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV093108 | AFNWC Sustainment Center |  | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | W912PP12C0016 | 21110 | 21590.3553 | 2012-07-09 |  | 2014-04-03 | 2015-03-31 | 99% | 1100 | ZHTV053302;
2015-02-28 | 2012 | Air Force Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH083003 | C-130 Flight Simulator |  | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | W912HN10D00630003 | 4630 | 4712.131 | 2013-04-30 |  | 2013-12-12 | 2015-01-08 | 99%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock |  | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | W9128F12C0013 | 32123.257 | 33445.233 | 2012-05-22 |  | 2014-09-06 | 2015-03-16 | 97%
2015-02-28 | 2012 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R4 | BMT Recruit Dormitory, Phase IV |  | 2011-12-16 | 2012-10-31 | AE-Merrick&Company ($400,140 shown under DDC) | W9126G08D00060055 | 0 | 0 |  |  | 2012-10-31 | 2016-12-11 | 81%
[9 empty] | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06
[9 empty] | 2011-12-16 | 2013-07-17 | Spawglass Contractors Inc. | W9126G12C0023 | 50528.593 | 52155.899 | 2013-07-17 |  | 2014-11-26
[9 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00J190007 | 6732.163 | 7301.64 | 2014-10-10 |  | 2016-01-03
2015-02-28 | 2012 | Air Force Active | Major Military Construction | WASHINGTON | UNITED STATES | GJKZ860009 | Wing Headquarters |  | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | W912DW12C0030 | 11957.25 | 12620.017 | 2013-03-18 | 2014-03-07 | 2013-12-26 | 2014-11-10 | 96%
2015-02-28 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17002 | Combat Aircraft Loading Area |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421 | 43728.4594 | 2012-12-24 |  | 2013-12-26 | 2015-03-12 | 49%
2015-02-28 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17003 | Parallel Taxiway Extension |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521.53 | 10521.53 | 2012-12-24 |  | 2014-05-03 | 2015-04-23 | 31%
2015-02-28 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17004 | Expeditionary Lodging |  | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587.915 | 27299.359 | 2013-03-15 |  | 2014-03-20 | 2015-01-09 | 86%
2015-02-28 | 2012 | Air Force Active | Major Military Construction |  | GERMANY | TYFR063017 | Dormitory (192 RM) |  | 2012-03-29 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541.6935 | 29541.6935 | 2014-07-01 |  | 2013-11-15 | 2015-09-15 | 1% | 1624 | WWYK143004A; ZHTV053302;
2015-02-28 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 |  | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706.6686 | 17706.6686 | 2013-06-04 |  | 2015-10-13 | 2015-11-20 | 80%
2015-02-28 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA124002 | Improve MFH Infrastructure, Phase 1 |  | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | W912HV12C0003 | 19550.171 | 20065.0231 | 2012-07-31 |  | 2014-10-21 | 2015-05-29 | 98%
2015-02-28 | 2012 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | AGGN123002P | Communications Network Control Center Consolidation |  | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619.1715 | 1619.1715 | 2014-03-10 |  | 2014-10-03 | 2015-02-26 | 62%
2015-02-28 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113026 | C-130 Aircraft Maintenance Unit |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511.518 | 1511.518 | 2013-09-12 |  | 2014-11-08 | 2016-02-29 | 23%
2015-02-28 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113027 | Air Defense Artillery Maintenance Facility |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265.194 | 1265.194 | 2013-08-28 |  | 2014-08-19 | 2015-06-19 | 92%
2015-02-28 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113032 | Precision Measurement Equipment Laboratory |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403.744 | 1409.0421 | 2013-08-28 |  | 2014-12-02 | 2015-07-24 | 87%
2015-02-28 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113034 | AFOSI Regional And Local Facility |  | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214.606 | 1214.606 | 2013-08-28 |  | 2015-01-14 | 2015-02-19 | 90%
2015-02-28 | 2012 | Air Force Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | PDPG020143 | Construct New Airfield Control Tower, B1295 & Base Op'S B395 |  | 2012-03-16 | 2012-07-26 | Flintco, LLC. | W912QR12C0048 | 16915 | 17335.163 | 2012-08-22 | 2014-06-23 | 2014-12-16 | 2015-01-22 | 98%
2015-02-28 | 2012 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ120572 | Vehicle Maintenance Facility |  | 2013-01-04 | 2014-08-22 | Oddo Construction Services | FA667014C0002 | 2087.131 | 2087.131 | 2014-09-22 |  | 2016-02-13 | 2015-07-31 | 2%
2015-02-28 | 2012 | Air Force Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX079003 | Red Horse Readiness And Training Facility |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149 | 9004.77 | 2012-07-13 |  | 2013-07-13 | 2014-12-15 | 92%
2015-02-28 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | UTAH | UNITED STATES | KRSM099001 | Fire Station #4 Annex |  | 2013-06-11 | 2013-09-25 | Grand Enterprises, LLC | FA820112D00250004 | 1322.061 | 1392.139 | 2013-10-11 | 2014-08-22 | 2014-05-28 | 2014-11-01 | 98%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK103006 | C-130J Fuel Systems Maintenance Hangar |  | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869 | 20869 | 2013-07-23 |  | 2015-06-25 | 2015-10-13 | 74%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK113005 | C-130J Flight Simulator Addition |  | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218.503 | 4218.503 | 2014-10-24 |  | 2015-09-24 | 2015-10-21 | 4%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY133001 | Civil Engineer Administration/Operations Facility |  | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947.269 | 15947.269 | 2014-07-09 |  | 2016-03-01 | 2016-03-30 | 2%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair |  | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 13298.609 | 13117.064 | 2013-08-21 |  | 2015-05-21 | 2015-05-29 | 88%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | QSEU103008 | HC-130J Simulator Facility |  | 2012-12-07 | 2013-06-28 | IBKI, Inc. Choctaw, MS | W912HN13C0011 | 7692.387 | 7808.669 | 2013-08-12 |  | 2014-11-20 | 2015-04-15 | 99%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | ACC123184 | Air Support Operations Center |  | 2013-03-14 | 2013-09-24 | Better Built Construction Serv | W912HN10D00530003 | 6458 | 6568.043 | 2013-11-07 |  | 2015-03-18 | 2015-06-10 | 48%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC133101 | RPA Mission Complex Physical Protection System |  | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643.42 | 10643.42 | 2014-08-19 |  | 2015-07-24 | 2015-09-01 | 21%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083008 | Dormitory (96 Rm) |  | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170.185 | 17241.765 | 2014-03-15 |  | 2015-03-07 | 2015-12-30 | 18%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103012 | F-35 Adal Hangar 45W/AMU |  | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781 | 6970.281 | 2014-01-27 |  | 2015-06-13 | 2015-08-15 | 42%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103030 | F-35A Modular Storage Magazines |  | 2012-08-08 | 2013-12-17 | Zumwalt Construction, Inc. | W9123811D00260006 | 2028.458 | 2033.5187 | 2014-01-27 |  | 2015-06-10 | 2015-10-25 | 26%
2015-02-28 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM113028 | F-35 Adal Building 118 For Flight Simulator |  | 2012-08-08 | 2013-12-17 | Creative Times, Inc. (CTI) | W9123811D00240002 | 3878.926 | 3888.2676 | 2014-01-29 |  | 2015-02-15 | 2015-04-30 | 65%
2015-02-28 | 2013 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103032 | Dormitory (48 Pn) |  | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031.649 | 23031.649 | 2013-08-15 |  | 2015-05-21 | 2015-07-29 | 43%
2015-02-28 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 |  | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698.0727 | 14787.5107 | 2013-08-29 |  | 2015-10-16 | 2016-01-04 | 35%
2015-02-28 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA133001P2 | Improve Family Housing, Ph 2 |  | 2013-05-16 | 2013-09-30 | Nishimatsu Construction Co., Ltd | FZ520513C0005 | 13989.4156 | 13835.0761 | 2013-10-29 |  | 2015-05-23 | 2015-05-22 | 90%
2015-02-28 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA134001 | Improve Mfh Infrastructure, Phase 2 |  | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336.739 | 14557.321 | 2013-10-23 |  | 2015-08-29 | 2015-08-31 | 57%
2015-02-28 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | FBNV133500 | T-10 Engine Test Cell (AMARG) |  | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D0110 | 1795 | 1795 | 2014-08-12 |  | 2015-05-04 | 2015-12-04 | 10%
2015-02-28 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | NKAK113003 | C130J Propeller Repair Training Facility |  | 2013-11-19 | 2014-02-21 | HGL Construction | FA446011D00075014 | 727 | 727 | 2014-06-20 |  | 2015-02-21 | 2015-02-20 | 1%
2015-02-28 | 2013 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 |  | 2013-03-06 | 2013-05-23 | Southwind Construction | W912BV12D00180003 | 1525.212 | 1573.679 | 2013-06-07 |  | 2015-07-19 | 2015-08-03 | 90%
2015-02-28 | 2013 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ099095 | Flight Simulator Facility |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242.986 | 5242.986 | 2014-08-05 |  | 2015-09-18 | 2016-01-15 | 2%
2015-02-28 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | KYJM129022 | Add Simulator Bay, Building 191 |  | 2013-06-07 | 2013-09-23 | CCI | W9127810D001180020 | 1552.029 | 1591.6019 | 2013-12-16 |  | 2014-07-07 | 2015-02-12 | 82%
2015-02-28 | 2013 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | HAYW109006 | F-15 Conversion |  | 2013-08-23 | 2013-09-27 | RS Morris Construction | W912LA11D00180010 | 3.747 | 4.055 | 2013-11-01 |  | 2015-01-25 | 2015-06-23 | 0%
[9 empty] | 2013-08-23 | 2013-09-30 | RS Morris Cosntruction | W912LA11D00180011 | 2.402 | 2.575 | 2013-11-01 |  | 2015-01-25
2015-02-28 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093007 | Construct Addition, Field Training Facility, B936 |  | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699.907 | 4699.907 | 2014-04-23 |  | 2015-06-11 | 2015-07-07 | 18%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) |  | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513.636 | 15620.812 | 2014-06-24 |  | 2016-01-11 | 2016-02-14 | 7%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699.643 | 53699.643 | 2014-08-27 |  | 2016-10-15 | 2017-02-21 | 2%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY143760 | Hardened Structures For POL Fuel Systems |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907.7 | 17907.7 | 2014-12-01 |  | 2016-03-30 | 2016-06-15 | 5%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility |  | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177.269 | 6177.269 | 2014-10-24 |  | 2016-07-20 | 2016-07-20 | 5%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  | 2013-11-18 | 2014-06-17 | SRB International LLC | N6274214C1312 | 2699 | 2699 | 2014-08-21 |  | 2015-05-08 | 2015-12-07 | 5%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar |  | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924.5 | 63996.803 | 2014-06-24 |  | 2015-12-03 | 2017-03-10 | 11% | 10500 | SGBP100904C;
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems |  | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100.5 | 8268.701 | 2014-09-02 |  | 2015-11-19 | 2015-12-19 | 25% | 2500 | SGBP100904C;
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145137 | KC-46A Alter Miscellaneous Facilities |  | 2014-03-10 | 2014-06-27 | Red Cedar Enterprises, Inc | W912DQ13D40010002 | 838.705 | 915.164 | 2014-07-12 |  | 2015-02-22 | 2015-03-11 | 85%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145138 | KC-46A Alter Aircraft Parking Apron |  | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976 | 976 | 2014-08-18 |  | 2017-02-06 | 2017-03-10 | 2% | 600 | PRQE145121;
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145142 | KC-46A 1-Bay Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200 | 25281.083 | 2014-09-19 |  | 2016-12-18 | 2017-03-10 | 4% | 3000 | SGBP100904C;
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959 | 53806.382 | 2014-06-24 |  | 2015-11-24 | 2017-03-10 | 2% | 19000 | SGBP100904C;
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) |  | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306.162 | 7311.706 | 2014-10-30 |  | 2015-09-23 | 2015-10-15 | 5%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | KENTUCKY | UNITED STATES | ACC123183 | Air Support Operations Center |  | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143.462 | 7143.462 | 2014-09-29 |  | 2016-02-13 | 2015-12-13 | 2%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 57000 | 57000 | 2014-07-07 |  | 2016-03-26 | 2017-04-13 | 2%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111010 | WSA: Construct Two New MOP Igloos |  | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817.7 | 3817.7 | 2014-08-11 |  | 2015-09-06 | 2015-12-13 | 28%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC073101 | Land Acquisition |  | 2014-07-18 | 2014-09-02 | USACE | W81EYN42417577 | 11.45 | 11.45 | 2014-09-02 |  | 2014-12-01 | 2016-03-15 | 2%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF083002 | Dormitory |  | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381 | 30381 | 2014-08-05 |  | 2016-08-22 | 2016-09-27 | 4%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103005 | F-35A ADAL AME Storage Facility |  | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D0113 | 4829.984 | 4829.984 | 2014-08-27 |  | 2016-01-15 | 2015-08-15 | 10%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103006 | F-35A Parts Store |  | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974.014 | 6974.014 | 2014-08-15 |  | 2015-12-01 | 2016-04-12 | 7%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar |  | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066 | 8066 | 2014-06-24 |  | 2015-11-12 | 2015-09-01 | 10%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF113005 | RPA Weapons School |  | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922.7 | 14922.7 | 2014-08-12 |  | 2016-05-31 | 2016-06-01 | 8%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073050 | Dormitory (144 Rm) |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19224.874 | 19678.9999 | 2014-07-10 |  | 2016-07-07 | 2016-11-01 | 6%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 |  | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285.5 | 21285.5 | 2014-08-25 |  | 2016-09-30 | 2016-02-08 | 10%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092013 | B-52 Munitions Storage Igloos |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540.27 | 9510.291 | 2014-07-15 |  | 2015-12-01 | 2016-01-06 | 10%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164.308 | 1164.308 | 2014-07-30 |  | 2015-12-08 | 2015-03-30 | 50%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111.892 | 7111.892 | 2014-07-02 |  | 2015-12-08 | 2015-12-24 | 2%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645.2 | 5645.2 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 24%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143004 | KC-46A FTU Ftc Simulator Facility Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000 | 11014.305 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 24%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 |  | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265.367 | 3265.367 | 2014-05-15 |  | 2015-05-17 | 2015-06-09 | 41%
2015-02-28 | 2014 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103011 | F-35 ADAL Hangar 45E/AMU |  | 2013-07-22 | 2014-04-10 | CTI | W912PL14C0005 | 6587 | 8832.885 | 2014-05-20 |  | 2015-10-02 | 2015-10-15 | 42%
2015-02-28 | 2014 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817.6089 | 39817.6089 | 2014-08-19 |  | 2016-07-10 | 2016-06-17 | 2%
2015-02-28 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ144287 | Improve MFH Infrastructure, Phase 3 |  | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288.6807 | 6288.6807 | 2014-08-15 |  | 2016-01-07 | 2016-01-07 | 3%
[9 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202.136 | 4202.136 | 2014-07-23 |  | 2014-06-30
[9 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473.4496 | 2473.4496 | 2014-08-06 |  | 2015-09-10
[9 empty] | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302.11 | 25302.11 | 2014-10-30 |  | 2016-12-05
2015-02-28 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility |  | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547.47 | 1547.47 | 2014-11-24 |  | 2015-07-29 | 2015-11-23 | 1%
2015-02-28 | 2015 | Air Force Active | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | VKAG133001 | OPERATIONS SUPPORT SQUADRON/WAR ROOM FACILITY |  | 2014-07-18 | 2015-01-28 | Crew MW, LLC | FA480915CC001 | 1864.7664 | 1864.7664 |  |  | 2016-01-03 | 2015-11-02
2015-02-28 | 2008 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 50950 | Barracks Complex |  | 2009-01-30 | 2010-03-25 | Kiewit Building Group Inc. | W9128A-10-C-0005 | 44500 | 45992.851 | 2010-04-25 | 2012-11-06 | 2012-03-10 | 2012-10-14 | 99%
2015-02-28 | 2008 | [7 empty] | 2009-01-31 | 2010-03-25 | Kiewit Building Group Inc. |  | 421.263 | 421.263 | 2010-04-25 | 2012-10-14 | 2012-03-10 | 2012-10-14 | 99%
2015-02-28 | 2008 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 54785 | Child Development Center |  | 2010-12-13 | 2011-08-04 | ASSET Group, Inc. | W9127S-11-C-6011 | 7835.188 | 7946.4612 | 2011-09-23 |  | 2013-01-25 | 2015-03-20 | 95% | 2750 | 68772
2015-02-28 | 2009 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67579 | Add/Alt Army Reserve Center |  | 2009-02-19 | 2009-06-18 | E. W. Howell Company, LLC | W912QR-09-C-0040 | 15041.2 | 16141.3502 | 2009-07-21 |  | 2011-07-11 | 2015-01-30 | 99%
2015-02-28 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68786 | Brigade Complex |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 24779 | 28823.563 | 2011-04-14 | 2015-02-25 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2009 | [7 empty] | 2010-06-23 | 2011-03-27 | dck-ecc pacific, LLC |  | 1877 | 1894.683 | 2011-04-14 | 2015-02-19 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68821 | Battalion Complex |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 29140 | 34049.766 | 2011-04-14 | 2015-02-25 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2009 | [7 empty] | 2010-06-23 | 2011-03-27 | dck-ecc pacific, LLC |  | 1944 | 1975.872 | 2011-04-14 | 2015-02-19 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68822 | Battalion Complex |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 9103 | 10871.394 | 2011-04-14 | 2015-02-25 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2009 | [7 empty] | 2010-06-23 | 2011-03-27 | dck-ecc pacific, LLC |  | 737 | 754.683 | 2011-04-14 | 2015-02-19 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69308 | Infrastructure Expansion |  | 2010-06-22 | 2011-03-27 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 58240 | 63818.854 | 2011-04-14 | 2015-02-25 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2009 | [7 empty] | 2010-06-23 | 2011-03-27 | dck-ecc pacific, LLC |  | 2145 | 2504.842 | 2011-04-14 | 2015-02-19 | 2014-03-13 | 2015-02-19 | 99%
2015-02-28 | 2010 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 64209 | Access Control Point and Road Improvements |  | 2010-01-15 | 2010-07-14 | Liberty A / Vertex | W9128F-10-C-0056 | 9839.658 | 11751.452 | 2010-08-03 | 2012-10-30 | 2012-01-25 | 2015-07-31 | 98%
2015-02-28 | 2010 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66726 | Ballistic Evaluation Facility, Ph 2 |  | 2012-05-10 | 2012-09-27 | APS Contracting Inc. | W912DS-12-C-0030 | 8757.272 | 8954.263 | 2012-12-04 |  | 2014-06-03 | 2015-05-14 | 63.04%
2015-02-28 | 2010 | Army Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | 69430 | Army Reserve Center/Land |  | 2011-07-28 | 2011-09-29 | Lobar Inc. | W912QR-11-C-0062 | 18272 | 18872.014 | 2012-01-18 |  | 2013-11-08 | 2015-05-07 | 88.93%
2015-02-28 | 2010 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 69471 | Army Reserve Center/Land |  | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | W912QR-12-C-0022 | 16009 | 16319.55 | 2012-05-22 |  | 2013-09-24 | 2015-08-31 | 81.81%
2015-02-28 | 2010 | Army Reserve | Major Military Construction | PUERTO RICO | PUERTO RICO | 69568 | Army Reserve Center/Land |  | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | W912QR-11-C-0046 | 12356.39 | 12620.58 | 2011-11-15 |  | 2013-08-06 | 2015-03-31 | 99%
2015-02-28 | 2010 | Army Active | Military Family Housing |  | GERMANY | 71421 | Family Housing Replacement Construction |  | 2014-10-14 | 2010-09-29 | LBB Niederlassung Idar-Oberstein | W912GB-07-D-0026 | 19120.2952 | 19120.2952 |  |  |  | 2017-10-01 | 3.496%
2015-02-28 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses |  | 2013-11-06 | 2014-04-03 | Contrack International, Inc. | W912ER-13-C-0032 | 49412.74 | 54675.778 | 2013-10-25 |  | 2015-03-25 | 2015-03-25 | 30.75%
2015-02-28 | 2010 | [7 empty] | 2013-11-06 | 2014-04-03 | Contrack International, Inc. |  | 6749.291 | 6749.291 | 2014-05-08 |  | 2015-10-30 | 2015-10-30 | 12.71%
2015-02-28 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 72477 | USFOR-A Headquarters & Housing |  | 2011-03-28 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 47160.85 | 32355.5764 | 2011-09-09 | 2015-02-28 | 2013-12-07 | 2014-08-25 | 99%
2015-02-28 | 2010 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 74408 | Ft Lewis-McChord AFB Joint Access |  | 2013-02-12 | 2013-08-29 | TSS-Garco Joint Venture | W912DW-13-C-0040 | 7327 | 7895.264 | 2013-09-25 |  | 2015-01-28 | 2015-03-30 | 87.37%
2015-02-28 | 2010 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 74885 | Fire Station |  | 2011-08-24 | 2012-07-16 | ARGO SYSTEMS, LLC | W912DR-12-C-0010 | 1636.889 | 1647.659 | 2012-08-02 | 2014-07-28 | 2014-01-25 | 2014-04-24 | 99%
2015-02-28 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 52269 | Barracks |  | 2011-04-27 | 2011-09-19 | Nan, Inc. dba Ocean House Builders | W9128A-11-C-0016 | 23984.24 | 25251.551 | 2011-10-16 | 2014-12-01 | 2014-07-15 | 2015-05-21 | 98.15%
2015-02-28 | 2011 | [7 empty] | 2011-04-28 | 2011-09-19 | Nan, Inc. dba Ocean House Builders |  | 1329.054 | 16744.75 | 2011-10-16 |  | 2014-07-15 | 2015-05-21 | 97.52%
2015-02-28 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 56024 | Flood Mitigation |  | 2012-06-28 | 2012-09-24 | Nan, Inc. | W9128A-12-C-0019 | 21105.273 | 21946.89 | 2012-10-16 |  | 2014-10-13 | 2015-06-29 | 74.45%
2015-02-28 | 2011 | [7 empty] | 2012-06-29 | 2012-09-24 | Nan, Inc. |  | 354.383 | 354.383 | 2012-10-16 |  | 2014-10-13 | 2015-06-29 | 24.76%
2015-02-28 | 2011 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 59044 | Science Facility, Ph 2 |  | 2011-06-22 | 2011-09-29 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270 | 113843.683 | 2011-11-17 |  | 2015-11-14 | 2016-01-29 | 83.66%
2015-02-28 | 2011 | Army Active | Major Military Construction | ALABAMA | UNITED STATES | 60463 | Aviation Component Maintenance Shop |  | 2010-12-14 | 2011-05-18 | Carothers Construction, Inc | W91278-07-D-0033 | 19712.66 | 21553.754 | 2011-09-20 | 2013-07-30 | 2013-09-09 | 2015-01-05 | 99%
2015-02-28 | 2011 | Army Active | Major Military Construction |  | GERMANY | 60555 | Information Processing Center |  | 2013-11-04 | 2014-03-18 | Hessisches Baumanagement Wiesbaden | W912GB-08-C-0005 | 27799.1141 | 32000.7428 | 2012-06-17 |  | 2014-05-31 | 2015-04-14 | 96.64%
2015-02-28 | 2011 | Army Active | Major Military Construction |  | HONDURAS | 61383 | Barracks |  | 2011-05-18 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | W91278-11-C-0028 | 15146.5804 | 15633.3629 | 2012-01-10 | 2015-01-15 | 2014-01-09 | 2014-09-24 | 99%
2015-02-28 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 61453 | Replace Fire Station |  | 2012-08-05 | 2013-05-22 | TMG SERVICES, INC. Linda Frazier | W912DR-13-C-0030 | 6189 | 6412.383 | 2013-06-04 |  | 2014-11-27 | 2015-05-14 | 78.62% | 2580 | 68961
2015-02-28 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W912PP-08-C-0019 | 38914.5 | 38914.5 | 2014-09-19 |  | 2016-06-30 | 2016-06-30 | 1.63% | 12900 | 73686
2015-02-28 | 2011 | [7 empty] | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV |  | 34801.408 | 35283.472 | 2011-09-21 | 2014-06-30 | 2013-06-12 | 2014-06-30 | 4.326%
2015-02-28 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64760 | Training Aids Center |  | 2012-06-28 | 2012-09-18 | SRB International LLC | W9128A-12-C-0013 | 13310.008 | 13325.4669 | 2012-10-30 | 2015-02-09 | 2014-08-16 | 2015-02-09 | 87.39%
2015-02-28 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 65650 | Command and Control Facility, Ph 1 |  | 2011-11-03 | 2012-02-28 | Niking Corporation | W9128A-12-C-0003 | 46780 | 49139.456 | 2012-04-02 |  | 2014-04-22 | 2015-07-30 | 93.7%
2015-02-28 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 65789 | Indoor Firing Range |  | 2011-11-14 | 2012-01-03 | Jordan-Versar, LLC | W91236-08-D-0056 | 6520 | 6749.174 | 2012-01-20 | 2013-10-23 | 2013-10-20 | 2013-10-23 | 99%
2015-02-28 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66595 | Barracks Complex |  | 2014-06-30 | 2015-01-19 | Federal Republic of Germany | W912GB-09-C-0014 | 29896.0912 | 29896.0912 |  |  | 2017-04-18 | 2017-04-18 | 1.121%
2015-02-28 | 2011 | Army Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 66717 | Military Working Dog Kennel |  | 2013-05-29 | 2014-04-30 | Sunlight Enterprises Co., Inc | W9126G-13-C-2005 | 1780.487 | 1847.173 | 2013-08-27 |  | 2014-07-22 | 2015-02-28 | 98.04%
2015-02-28 | 2011 | [7 empty] | 2013-05-30 | 2013-08-04 | Sunlight Enterprises Co., Inc |  | 78.2 | 78.2 | 2013-08-27 |  | 2014-07-22 | 2015-02-28 | 98%
2015-02-28 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66834 | Vehicle Maintenance Shop |  | 2011-05-25 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 15984.7877 | 19038.8451 | 2011-12-12 |  | 2013-12-18 | 2015-07-30 | 88.56%
2015-02-28 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68074 | Construct New ACP |  | 2013-11-15 | 2013-08-11 | Hessisches Baumanagement Wiesbaden | W912GB-09-C-0059 | 188.0818 | 225.0331 | 2014-03-05 | 2015-01-09 | 2014-12-12 | 2015-03-19 | 97.33%
2015-02-28 | 2011 | [7 empty] | 2013-11-15 | 2013-08-11 | Hessisches Baumanagement Wiesbaden |  | 6115.8003 | 7020.715 | 2014-03-05 |  | 2014-12-12 | 2015-03-19 | 93.6%
2015-02-28 | 2011 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 69421 | Army Reserve Center/Land |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4454 | 4454 | 2012-08-21 |  | 2014-03-21 | 2015-12-31 | 6.893%
2015-02-28 | 2011 | Army Reserve | Major Military Construction | IOWA | UNITED STATES | 70654 | Army Reserve Center |  | 2011-11-15 | 2012-03-14 | The Vertex Companies | W912QR-12-C-0014 | 8931.622 | 9043.596 | 2012-04-09 |  | 2013-08-12 | 2015-02-15 | 95.04%
2015-02-28 | 2011 | Army Active | Military Family Housing |  | GERMANY | 71422 | Family Housing Replacement Construction |  | 2014-10-14 | 2011-09-13 | LBB Niederlassung Idar-Oberstein |  | 32960.5419 | 32960.5419 |  |  | 2012-02-23 | 2017-09-28 | 5.021%
2015-02-28 | 2011 | Army Active | Major Military Construction |  | AFGHANISTAN | 71604 | Eastside Utilities Infrastructure |  | 2012-05-30 | 2012-09-04 | ANHAM-ICSS Joint Venture | W912ER-11-D-0003 | 26826.989 | 25202.776 | 2012-10-18 |  | 2014-06-05 | 2015-02-28 | 75.13%
2015-02-28 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex |  | 2012-12-19 | 2013-09-30 | Bristol General Contractors, LLC |  | 15175 | 15283 | 2013-11-06 |  | 2015-01-30 | 2015-07-04 | 41%
2015-02-28 | 2011 | Army Active | Unspecified Minor Military Construction | OHIO | UNITED STATES | 74757 | Fire Alarm System |  | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | W912QR-12-C-0050 | 1763.338 | 1782.2016 | 2012-09-05 |  | 2013-08-01 | 2015-03-30 | 85.78%
2015-02-28 | 2011 | Army Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | 74943 | Igloo Storage, Installation |  | 2012-03-12 | 2012-07-17 | Senate Builders & Construction Managers Inc. | W912DS-12-C-0017 | 1756.106 | 1851.3294 | 2012-08-09 | 2013-10-14 | 2013-07-06 | 2014-05-14 | 99%
2015-02-28 | 2011 | Army Reserve | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 79128 | DEPMEDS |  | 2013-03-26 | 2013-09-30 | Imperial Construction | W912QR-13-C-0046 | 1560.895 | 1652.152 | 2013-10-11 | 2014-12-01 | 2014-09-26 | 2014-12-15 | 86.32%
2015-02-28 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 1235 | Physical Fitness Facility |  | 2012-01-05 | 2012-06-18 | Grahams Construction Inc. | W912DY-11-D-0040 | 23138.91 | 23149.051 | 2012-07-12 |  | 2014-04-10 | 2015-08-17 | 81%
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility |  | 2012-10-21 | 2013-09-26 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603 | 9106.89 | 2013-01-24 |  | 2014-07-18 | 2015-04-14 | 55% | 3900 | 65745
2015-02-28 | 2012 | [7 empty] | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. |  | 4150 | 4150 | 2013-01-24 |  | 2014-07-18 | 2015-04-14 | 55%
2015-02-28 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 17220 | Fire Station |  | 2012-04-02 | 2013-09-24 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12622.8 | 12651.55 | 2013-11-06 |  | 2015-11-11 | 2016-03-30 | 24% | 5000 | 65745
2015-02-28 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 20697 | Chapel |  | 2012-01-27 | 2012-08-29 | Liberty Mutual Insurance Company | W912BV-12-C-0018 | 12999.823 | 13082.662 | 2012-09-20 |  | 2014-01-28 | 2015-04-30 | 58%
2015-02-28 | 2012 | Army Active | Major Military Construction | UTAH | UNITED STATES | 55823 | Life Sciences Test Facility Addition |  | 2012-04-12 | 2012-07-26 | Big-D Construction Corp | W91238-12-C-0024 | 22608.566 | 29443.93 | 2012-08-29 |  | 2015-02-15 | 2015-08-05 | 87.56%
2015-02-28 | 2012 | Army Active | Major Military Construction |  | GERMANY | 55985 | Chapel |  | 2013-07-11 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15915.6532 | 16181.8519 | 2013-11-21 |  | 2016-03-22 | 2016-03-22 | 29.19%
2015-02-28 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 56425 | General Instruction Building |  | 2012-08-20 | 2012-09-29 | Souza Construction, Inc. | W91238-10-D-0010 | 2996 | 3163.422 | 2012-11-06 | 2015-01-02 | 2013-11-06 | 2015-01-01 | 95.79%
2015-02-28 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 57508 | Information Dominance Center, Ph 1 |  | 2013-03-14 | 2013-07-21 | Hensel Phelps Construction Co. | W912DR-13-C-0035 | 39700.01 | 41282.9475 | 2013-08-18 |  | 2015-03-11 | 2015-05-11 | 88.56%
2015-02-28 | 2012 | Army Active | Major Military Construction |  | GERMANY | 57594 | Satellite Communications Center |  | 2013-01-22 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565.3511 | 27788.0021 | 2014-03-13 |  | 2015-12-14 | 2016-02-27 | 28.29%
2015-02-28 | 2012 | [7 empty] | 2013-01-22 | 2014-02-07 | JV PGWM SATCOM |  | 262.9753 | 262.9753 | 2014-03-13 |  | 2015-12-14 | 2016-02-27 | 99%
2015-02-28 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 58046 | Operational Readiness Training Cplx, Ph 1 |  | 2012-06-29 | 2013-04-01 | TSS-Garco Joint Venture | W912DW-12-C-0043 | 16416 | 16329.875 | 2013-05-21 |  | 2014-11-12 | 2015-05-15 | 88.37%
2015-02-28 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58207 | Railroad Tracks |  | 2011-11-29 | 2012-03-25 | McAlester Contract | W44XGQ80956921 | 6323.7745 | 6323.7745 | 2012-05-09 |  | 2013-10-06 | 2015-09-15 | 89%
2015-02-28 | 2012 | Army Active | Major Military Construction |  | GERMANY | 58925 | Satellite Communications Center |  | 2012-03-11 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0037 | 29010.1333 | 29010.1333 | 2014-10-15 |  | 2015-12-14 | 2016-07-06 | 0% | 6000 | 71485
2015-02-28 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 59005 | Aviation Training Facility |  | 2012-03-19 | 2012-05-15 | Oyster Point Construction Company | W91236-12-C-0035 | 13849 | 14386.418 | 2012-06-13 | 2014-09-24 | 2013-12-06 | 2014-06-13 | 99%
2015-02-28 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 59581 | Centralized Wash Facility |  | 2011-10-12 | 2012-01-27 | Watts Constructors, LLC | W9128A-12-C-0001 | 28300 | 29982.274 | 2012-02-08 | 2015-02-27 | 2013-12-14 | 2015-02-27 | 98.35%
2015-02-28 | 2012 | [7 empty] | 2011-10-13 | 2012-01-27 | Watts Constructors, LLC |  | 300 | 300 | 2012-02-08 | 2015-02-27 | 2013-12-14 | 2015-02-27 | 98%
2015-02-28 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 61515 | Physical Fitness Facility |  | 2011-10-18 | 2012-11-07 | Bristol General Contractors, LLC | W911KB-13-C-0002 | 21813.389 | 22240.075 | 2013-03-15 |  | 2014-12-06 | 2015-06-30 | 78.58%
2015-02-28 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 62657 | Water Treatment Plant |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100112.66 | 99576.518 | 2012-10-19 |  | 2015-10-19 | 2016-01-05 | 67.2%
2015-02-28 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex |  | 2012-02-21 | 2012-08-16 | Blackhawk Ventures, LLC | W9126G-09-D-0101 | 10283 | 10964.2248 | 2012-05-15 |  | 2013-11-06 | 2015-04-10 | 97.45%
2015-02-28 | 2012 | [7 empty] | 2012-02-22 | 2012-08-16 | The Ross Group Construction Corporation |  | 11856.9 | 12236.1292 | 2012-10-09 | 2014-11-19 | 2014-04-02 | 2015-02-27 | 98%
2015-02-28 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 64939 | Applied Instruction Facility |  | 2012-06-19 | 2012-09-23 | Grimberg/Amatea JV | W912DR-12-C-0023 | 30554 | 32735.065 | 2012-11-20 |  | 2014-11-20 | 2015-12-07 | 83.72%
2015-02-28 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64967 | Child Development Center |  | 2011-10-05 | 2012-02-27 | 57 Builders, Ltd. | W9128A-12-C-0002 | 9573.118 | 10256.824 | 2012-03-22 | 2015-02-27 | 2013-12-13 | 2015-02-27 | 93.35%
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex |  | 2012-07-18 | 2013-01-07 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503 | 39644.6778 | 2012-09-05 |  | 2014-07-28 | 2015-06-30 | 77%
2015-02-28 | 2012 | [7 empty] | 2012-07-19 | 2013-01-07 | Turner Strategic Technologies, LLC |  | 8195.202 | 8267.659 | 2013-03-08 |  | 2014-11-28 | 2015-02-25 | 94.61%
2015-02-28 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65755 | Brigade Complex |  | 2012-04-30 | 2012-10-29 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30761.85 | 34119.569 | 2012-12-12 |  | 2015-12-12 | 2017-01-18 | 67.28% | 3500 | 34129, 52856, 64797, 65138, 69167, 69999, 71539
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 |  | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | W9126G-12-C-0015 | 40532.114 | 40883.745 | 2012-04-24 |  | 2014-04-24 | 2015-11-05 | 77%
2015-02-28 | 2012 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 67466 | Army Reserve Center/Land |  | 2012-05-16 | 2012-09-18 | IKHANA, LL | W912QR-12-C-0055 | 15942 | 15977.219 | 2012-10-10 |  | 2014-03-19 | 2015-07-31 | 66.71%
2015-02-28 | 2012 | Army Reserve | Major Military Construction | COLORADO | UNITED STATES | 67658 | Army Reserve Center |  | 2011-11-29 | 2012-04-16 | Liberty Mutual Insurance Company | W912QR-12-C-0028 | 10450.922 | 10593.552 | 2012-05-11 |  | 2013-10-18 | 2015-04-01 | 86.86%
2015-02-28 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67691 | Army Reserve Center |  | 2011-11-16 | 2012-05-03 | SCMC, LLC | W912QR-12-C-0025 | 17931 | 18716.0068 | 2012-06-01 | 2014-05-21 | 2014-02-21 | 2015-05-31 | 96.04%
2015-02-28 | 2012 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67713 | Army Reserve Center |  | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | W912QR-12-C-0068 | 13312 | 14653.3582 | 2012-10-18 |  | 2014-07-10 | 2015-06-15 | 82.37%
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 68993 | Electronics Maintenance Facility |  | 2011-12-17 | 2013-09-20 | Venegas Engineering & Management Construction Company |  | 5117.965 | 5117.965 | 2012-08-20 |  | 2013-09-13 | 2016-01-31 | 97.76%
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69286 | Infrastructure |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008.411 | 8732.566 | 2012-08-20 |  | 2013-09-13 | 2016-01-31 | 97.56%
2015-02-28 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69489 | Combat Aviation Brigade Complex, Ph 1 |  | 2012-01-24 | 2012-06-28 | David Boland, Inc. | W9128A-12-C-0009 | 54772 | 55818.257 | 2012-07-29 |  | 2015-05-26 | 2015-06-10 | 56.15%
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69828 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-07-15 | 2014-05-28 | JAM-MAP JV | W9126G-14-C-0016 | 8829.807 | 8829.807 | 2014-08-27 |  | 2016-01-04 | 2016-01-18 | 6%
2015-02-28 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-08-26 | 2014-01-07 | Law Company, Inc. | W912DQ-14-C-4003 | 20078.9 | 20209.973 | 2014-02-06 |  | 2015-07-31 | 2015-08-04 | 36.25%
2015-02-28 | 2012 | [7 empty] | 2013-08-26 | 2012-11-01 | Arch Insurance Company |  | 5932.641 | 6058.041 | 2012-12-11 | 2015-02-27 | 2014-03-16 | 2015-02-27 | 97.88%
2015-02-28 | 2012 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69835 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2014-08-25 | 2014-12-05 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 30589 | 30589 | 2015-01-05 |  | 2016-02-29 | 2016-02-29 | 0.8431%
2015-02-28 | 2012 | [7 empty] | 2014-08-25 | 2014-12-05 | Caddell Construction Co. (DE) LLC |  | 0 | 0 | 2015-01-05 |  | 2016-02-29 | 2016-02-29 | 0%
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 9669.4345 | 10168 | 2012-06-22 |  | 2013-12-14 | 2015-04-24 | 93%
2015-02-28 | 2012 | [7 empty] | 2011-12-19 | 2013-12-04 | Soulis Constructors, Inc |  | 5786.309 | 5786.309 | 2014-01-15 |  | 2015-07-09 | 2015-07-29 | 73%
2015-02-28 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74067 | Construct Drainage System, Ph 3 |  | 2012-04-27 | 2012-08-15 | ANHAM-ICSS JV | W912ER-11-D-0003 | 19902.989 | 22733.6248 | 2012-10-09 | 2015-02-17 | 2014-06-01 | 2015-04-30 | 96.54%
2015-02-28 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B |  | 2013-12-04 | 2014-04-08 | CJW Construction, Inc. | W912DW-12-C-0051 | 12950.4 | 13974.8006 | 2012-11-29 | 2014-10-14 | 2014-05-23 | 41988 | 0.99
2015-02-28 | 2012 | [7 empty] | 2013-12-04 | 2014-04-08 | Glen/Mar Construction, Inc. |  | 4771.02 | 4810.946 | 2014-05-21 |  | 2015-05-21 | 42155 | 0.30431
2015-02-28 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7472.9455 | 7866 | 2012-06-22 |  | 2013-12-14 | 2015-04-24 | 93%
2015-02-28 | 2012 | [7 empty] | 2011-12-19 | 2013-12-04 | Soulis Constructors, Inc |  | 5378.708 | 4709 | 2014-01-15 |  | 2015-07-09 | 2015-07-29 | 73%
2015-02-28 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78475 | Family Housing Improvements |  | 2013-05-21 | 2014-11-18 | Klebl GmbH |  | 14631.5966 | 14631.5966 | 2015-01-16 |  | 2016-06-08 | 2016-06-08 | 0.7381%
2015-02-28 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78505 | Family Housing New Construction |  | 2013-04-18 | 2013-08-06 | Staatliches Hochbauamt Amberg |  | 13548.8862 | 13641.2361 | 2013-08-06 |  | 2015-09-13 | 2015-11-05 | 49.35%
2015-02-28 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78506 | Family Housing New Construction |  | 2013-07-07 | 2013-09-29 | Bauamt Amberg-Sulzbach |  | 12815.485 | 12891.5842 | 2013-09-29 |  | 2015-08-10 | 2015-08-10 | 68.43%
2015-02-28 | 2012 | Army Reserve | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 79315 | Heated Storage Building |  | 2012-11-28 | 2013-02-25 | Q.B.S., Inc. | W912QR-09-D-0018 | 1560.1607 | 1698.0767 | 2013-04-16 | 2014-05-30 | 2014-04-16 | 2015-05-01 | 98.31%
2015-02-28 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  | 2013-07-16 | 2014-09-02 | Purcell Construction Corporation | W91236-13-C-0064 | 46650 | 46659.0739 | 2013-10-14 |  | 2015-10-14 | 2015-10-14 | 69.85%
2015-02-28 | 2013 | [7 empty] | 2013-07-16 | 2014-09-02 | VISTA Construction LLC |  | 4055.4 | 4055.4 | 2014-09-15 |  | 2015-09-15 | 2015-12-08 | 0.8077%
2015-02-28 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center |  | 2013-05-15 | 2013-09-24 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959 | 7120.204 | 2013-10-22 |  | 2015-02-15 | 2015-08-02 | 78.94%
2015-02-28 | 2013 | [7 empty] | 2013-05-15 | 2012-09-27 | APS Contracting Inc. |  | 2019.198 | 2019.198 | 2012-12-04 |  | 2014-06-03 | 2015-05-14 | 81.86%
2015-02-28 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 |  | 2013-04-11 | 2013-08-15 | Caddell Construction Co. (DE), LLC | W912DQ-13-C-4024 | 33360 | 34313.4666 | 2013-09-12 |  | 2015-09-12 | 2015-10-16 | 82.3%
2015-02-28 | 2013 | [7 empty] | 2013-04-11 | 2013-05-31 | Donald Maggi, Inc. |  | 11711 | 12157.9971 | 2013-06-25 |  | 2014-12-17 | 2015-03-23 | 95.79%
2015-02-28 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 57794 | Digital Multipurpose Training Range |  | 2012-12-26 | 2013-05-10 | Caddell Construction Co. (DE), LLC | W912HN-10-D-0044 | 19523 | 19680.862 | 2014-02-04 |  | 2015-04-30 | 2015-05-13 | 69.57%
2015-02-28 | 2013 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 58970 | Trainee Barracks Complex 2, Ph 2 |  | 2013-04-29 | 2013-10-30 | ACC Construction Co., Inc | W912HP-14-C-0003 | 21786.027 | 21850.968 | 2013-12-04 |  | 2015-05-28 | 2015-06-07 | 62.46%
2015-02-28 | 2013 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 59626 | Digital Multipurpose Training Range |  | 2013-05-31 | 2013-08-23 | NEU Security Services, LLC | W9128F-13-C-0016 | 14080 | 15393.603 | 2013-09-18 |  | 2015-03-12 | 2015-05-01 | 72.85%
2015-02-28 | 2013 | Army Active | Major Military Construction |  | JAPAN | 62783 | Satellite Communications Facility |  | 2013-03-25 | 2014-09-17 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 6488.2629 | 6488.2629 | 2014-11-21 |  | 2021-06-08 | 2021-06-08 | 0% | 24810 | 36113, 61562, 64474, 66441, 69999, 71472, 71485, 72242
2015-02-28 | 2013 | [7 empty] | 2013-03-26 | 2014-09-17 | Prime Projects International Japan Co., Ltd. |  | 61071.4985 | 61071.4985 | 2014-11-21 |  | 2021-06-08 | 2021-06-08 | 0%
2015-02-28 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 65679 | Vehicle Maintenance Shop |  | 2014-08-12 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18726.852 | 19235.376 | 2013-06-27 |  | 2015-04-08 | 2015-04-18 | 81.45%
2015-02-28 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 66023 | Automated Infantry Platoon Battle Course |  | 2014-02-11 | 2014-06-22 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345 | 27345 | 2014-07-07 |  | 2016-09-08 | 2016-09-08 | 22.4%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67659 | Army Reserve Center |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21575 | 22597.2326 | 2014-01-13 |  | 2015-11-04 | 2015-12-31 | 37.09%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | NEVADA | UNITED STATES | 67660 | Army Reserve Center/AMSA |  | 2012-12-28 | 2013-06-12 | MACNAK Korte Team LLC | W912QR-13-C-0014 | 16436.543 | 16926.0638 | 2013-07-10 |  | 2015-05-01 | 2015-05-01 | 83.39%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 67689 | Central Issue Facility |  | 2013-01-28 | 2013-06-14 | KEPA-TCI JV LLC | W912QR-13-C-0016 | 9302.203 | 9774.1395 | 2013-07-08 |  | 2014-11-10 | 2015-06-10 | 76.74%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | WASHINGTON | UNITED STATES | 67715 | Army Reserve Center |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31219 | 31518.227 | 2013-07-11 |  | 2015-08-30 | 2015-08-30 | 70.01%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | MARYLAND | UNITED STATES | 68077 | Add/Alt Army Reserve Center |  | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890.05 | 7890.05 | 2014-07-30 |  | 2016-05-30 | 2016-05-30 | 0.9725%
2015-02-28 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71120 | Training Aids Center |  | 2013-03-08 | 2013-09-03 | PENTACON, LLC | W912DY-12-D-0030 | 21912 | 22001.757 | 2013-10-17 |  | 2015-04-10 | 2015-05-25 | 47%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 71482 | ORTC |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56000.64 | 61866.182 | 2014-03-19 |  | 2016-05-17 | 2016-05-17 | 12.38%
2015-02-28 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 71675 | Flight Equipment Complex |  | 2013-05-01 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751 | 42843.301 | 2014-01-15 |  | 2016-01-15 | 2016-03-10 | 32.04%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71997 | Dining Facility |  | 2013-01-22 | 2013-08-23 | TCI Architects Engineers Contractor Inc. | W912QR-13-C-0026 | 7738.253 | 7801.4736 | 2013-10-02 |  | 2015-02-04 | 2015-05-28 | 53.41%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 72088 | ECS TEMF |  | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19021.6 | 19262.17 | 2013-07-08 |  | 2015-06-08 | 2015-06-08 | 55.89%
2015-02-28 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72160 | UPH Barracks |  | 2013-03-28 | 2013-08-27 | Pre Con Industries, Inc. | W912QR-13-C-0027 | 4384.284 | 4399.535 | 2013-11-18 |  | 2014-11-03 | 2015-03-18 | 92.8%
2015-02-28 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 73008 | Unmanned Aerial Vehicle Complex |  | 2013-03-22 | 2013-08-15 | Caddell Construction CO. (DE), LLC | W912HN-10-D-0044 | 20726 | 21010.825 | 2013-11-06 |  | 2015-03-01 | 2015-04-27 | 65.81%
2015-02-28 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 75165 | Waste Water Treatment Plant |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77476.628 | 78018.153 | 2014-03-03 |  | 2016-03-02 | 2016-03-02 | 27.89%
2015-02-28 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76086 | Lightning Protection System |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072 | 3072 | 2014-09-16 |  | 2015-12-30 | 2015-12-30 | 1.488%
2015-02-28 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76091 | Engineering/Housing Maintenance Shop |  | 2014-05-15 | 2014-09-18 | Federal Solutions Group | W91238-14-C-0051 | 3211.6056 | 3211.6056 | 2014-10-08 |  | 2015-11-12 | 2015-11-12 | 0%
2015-02-28 | 2013 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76196 | Battalion Headquarters Complex |  | 2013-02-01 | 2013-05-13 | Hyosung Corporation | W912UM-13-C-0021 | 25852.7608 | 28682.4302 | 2013-05-13 |  | 2015-06-08 | 2016-05-07 | 27.34%
2015-02-28 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 76239 | Unmanned Aerial Vehicle Complex |  | 2012-11-13 | 2013-05-31 | Archer Western Federal JV | W912QR-13-C-0012 | 16983 | 17448.726 | 2013-06-25 |  | 2015-04-26 | 2015-04-26 | 96.61%
2015-02-28 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76586 | Barracks |  | 2013-02-06 | 2013-07-10 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717.476 | 31468.661 | 2013-07-22 |  | 2015-08-31 | 2015-11-21 | 57.24%
2015-02-28 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76587 | Barracks |  | 2013-02-06 | 2013-07-10 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410.03 | 39112.251 | 2013-07-22 |  | 2015-08-31 | 2015-11-21 | 56.15%
2015-02-28 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76903 | Combat Aviation Brigade Barracks |  | 2012-11-26 | 2014-05-12 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749.203 | 69749.203 | 2014-06-25 |  | 2017-01-13 | 2017-01-13 | 3.14%
2015-02-28 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 77419 | Ground Source Heat Transfer System |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 10400 | 10400 | 2015-01-06 |  | 2016-12-26 | 2016-12-26 | 0%
2015-02-28 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 79933 | Cadet Barracks |  | 2012-11-06 | 2013-08-07 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 72000 | 73411.622 | 2013-08-25 |  | 2016-08-29 | 2016-10-27 | 61.34%
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE |  | 2013-05-17 | 2013-07-17 | Huffman Construction, LLC | W912DQ-13-C-4018 | 1437.6 | 1550.114 | 2013-09-23 |  | 2014-06-20 | 2015-03-31 | 87.75%
2015-02-28 | 2013 | [7 empty] | 2013-05-17 | 2012-09-30 | Zieson Construction Company, LLC |  | 11.211 | 11.211 | 2012-12-10 |  | 2013-12-10 | 2015-05-21 | 99%
2015-02-28 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80066 | Controlled Humidity Warehouse, Installatio |  | 2012-11-16 | 2013-09-20 | Tyler Construction Co., INC | W912HN-10-D-0060 | 6726.987 | 6769.3467 | 2013-11-06 |  | 2015-03-01 | 2015-04-08 | 73.76% | 8600 | 62955
2015-02-28 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80087 | Storage Building, General Purpose |  | 2012-07-16 | 2013-03-22 | Tyler Construction Group, Inc. | W912HN-10-D-0060 | 9037.592 | 9003.526 | 2013-04-18 |  | 2014-08-11 | 2015-04-27 | 92.24% | 12600 | 76235
2015-02-28 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex |  | 2013-04-24 | 2013-08-14 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491.27 | 11426.577 | 2013-10-07 |  | 2015-05-30 | 2015-06-18 | 67%
2015-02-28 | 2013 | [7 empty] | 2013-03-11 | 2014-05-29 | JAM-MAP JV |  | 591 | 591 | 2014-08-27 |  | 2016-01-04 | 2016-01-04 | 6%
2015-02-28 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar |  | 2012-12-12 | 2013-11-25 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 26825.868 | 27139.258 | 2013-06-26 |  | 2015-06-16 | 2015-06-16 | 42.49%
2015-02-28 | 2013 | [7 empty] | 2012-12-12 | 2013-11-25 | VETCO Contracting Services, LLC |  | 21577.777 | 22625.014 | 2013-12-12 |  | 2015-12-02 | 2016-03-17 | 55.46%
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80317 | WATER DISTRIBUTION LINES, POTABLE |  | 2013-08-13 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1790.839 | 1464.69 | 2014-01-13 |  | 2014-09-09 | 2015-04-29 | 9.961%
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction | UTAH | UNITED STATES | 81106 | POLICE/MP STATION |  | 2013-06-11 | 2013-09-27 | Zumwalt Construction, Inc. | W91238-11-D-0026 | 1768.28 | 1768.28 | 2013-10-18 |  | 2014-12-17 | 2015-03-23 | 61.57%
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81320 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL |  | 2013-08-08 | 2013-09-26 | Northcon, Inc. | W912DW-13-C-0047 | 1380.171 | 1380.171 | 2013-10-28 | 2015-01-26 | 2014-10-28 | 2014-10-28 | 96%
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 81367 | EXPLOSIVES RECEIVING/SERVICE BUILDING, DEP |  | 2013-12-18 | 2014-04-16 | Cyber Professional Solution Corp | W912PL-14-C-0006 | 1783.729 | 1783.729 | 2014-05-08 |  | 2015-05-08 | 2015-05-08 | 70.44%
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE |  | 2013-08-14 | 2014-09-29 | PORTICO SERVICES, LLC | W912DR-14-C-0028 | 1793.105 | 1839.9466 | 2014-10-29 |  | 2015-04-27 | 2015-09-24 | 51.91%
2015-02-28 | 2013 | [7 empty] | 2013-08-14 | 2014-09-29 | Portico Services |  | 219.795 | 225.892 | 2014-10-29 |  | 2015-04-27 | 2015-09-24 | 12.21%
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  | 2014-08-20 | 2014-09-29 | Nan Inc | W9128A-12-D-0012 | 1555.718 | 1555.718 | 2014-10-27 |  | 2015-10-22 | 2015-10-22 | 6.67%
2015-02-28 | 2013 | Army Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 81597 | AMSA Addition/Alteration |  | 2013-08-27 | 2013-09-30 | FutureNet Group, Inc. | W912QR-13-D-0023 | 1379.863 | 1398.495 | 2013-10-09 |  | 2014-09-24 | 2015-03-25 | 60.25%
2015-02-28 | 2014 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 51868 | Adv Individual Training Barracks Cplx, Ph2 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 0 | 0 | 2015-01-06 |  | 2016-12-26 | 2016-12-26 | 0%
2015-02-28 | 2014 | [7 empty] | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC |  | 55619 | 55619 | 2015-01-06 |  | 2016-12-26 | 2016-12-26 | 1.181%
2015-02-28 | 2014 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  | 2014-05-12 | 2014-09-17 | Purcell Construction Corporation | W91236-14-C-0046 | 40036.48 | 40036.48 | 2014-10-08 |  | 2017-07-04 | 2017-07-04 | 0.6081%
2015-02-28 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 54106 | Automated Multipurpose Machine Gun Range |  | 2013-12-24 | 2014-05-28 | TSS-Garco Joint Venture | W912DW-14-C-0012 | 7716 | 7716 | 2014-08-18 |  | 2016-02-09 | 2016-02-09 | 8.911%
2015-02-28 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 65277 | Consolidated Dining Facility |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 10798.9 | 10798.9 | 2014-04-23 |  | 2015-09-30 | 2015-12-02 | 15.12%
2015-02-28 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex |  | 2013-08-27 | 2015-01-15 | Silver Mountain Construction, LLC | W911KB-14-C-0008 | 14180.4971 | 14220.9794 | 2014-05-15 |  | 2016-02-04 | 2016-02-04 | 25% | 3850 | 63799
2015-02-28 | 2014 | [7 empty] | 2013-08-27 | 2014-12-31 | Alcan Builders Inc. |  | 12374 | 12374 | 2015-01-15 |  | 2016-09-06 | 2016-09-06 | 1%
2015-02-28 | 2014 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69624 | Command and Control Facility |  | 2014-06-10 | 2014-07-21 | Brantley Construction Services, LLC | W912HN-10-D-0056 | 4720.25 | 4733.844 | 2014-08-27 |  | 2015-08-27 | 2015-08-27 | 33.73%
2015-02-28 | 2014 | [7 empty] | 2014-06-10 | 2014-07-21 | Brantley Construction Services, LLC |  | 153.1 | 153.1 | 2014-08-27 |  | 2015-08-27 | 2015-08-27 | 0%
2015-02-28 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 69669 | Central Issue Facility |  | 2014-01-31 | 2014-06-05 | Ranco Construction, Inc. | W912QR-14-C-0021 | 8783.22 | 8783.22 | 2014-07-07 |  | 2015-12-14 | 2016-01-27 | 4.71%
2015-02-28 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 71221 | Fire Station |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542.275 | 12317.912 | 2014-08-27 |  | 2016-02-18 | 2016-02-18 | 13.29%
2015-02-28 | 2014 | [7 empty] | 2014-03-28 |  | Mountain West Precast Concrete |  | 8.388 | 8.388 |  |  |  | 2016-02-18 | 0%
2015-02-28 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  | 2014-10-17 | 2014-12-19 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777 | 49054.856 | 2014-08-05 |  | 2016-08-04 | 2016-10-24 | 6.511%
2015-02-28 | 2014 | [7 empty] | 2014-10-17 | 2014-12-19 | Zieson Construction Co. |  | 14313.443 | 14313.443 | 2015-01-29 |  | 2016-07-22 | 2016-07-22 | 0%
2015-02-28 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71769 | Modified Record Fire Range |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653 | 4653 | 2014-10-17 |  | 2016-04-09 | 2016-04-09 | 0%
2015-02-28 | 2014 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71900 | Army Reserve Center |  | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129.201 | 22129.201 | 2014-12-02 |  | 2016-11-01 | 2016-11-01 | 2.806%
2015-02-28 | 2014 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71999 | NCO Academy Dining Facility |  | 2013-12-12 | 2014-03-31 | Wilson Brigadier Joint Venture | W912QR-14-C-0013 | 5900 | 5902.885 | 2014-04-22 |  | 2015-08-25 | 2015-08-25 | 31.3%
2015-02-28 | 2014 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72284 | TASS Training Center (TTC) |  | 2014-08-13 | 2014-09-30 | Bara Infoware Inc. | W912QR-14-C-0053 | 16186.7042 | 16186.7042 | 2014-10-20 |  | 2016-05-22 | 2016-05-22 | 0%
2015-02-28 | 2014 | Army Active | Military Family Housing | WISCONSIN | UNITED STATES | 74861 | Family Housing New Construction |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862.0909 | 21862.0909 | 2014-08-20 |  | 2016-08-09 | 2016-08-09 | 2.743%
2015-02-28 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 75019 | Simulator Building |  | 2014-08-28 | 2014-11-06 | Zieson Construction Co. | W912DQ-15-C-4000 | 3496.695 | 3496.695 | 2014-12-01 |  | 2015-12-01 | 2015-12-01 | 8.525%
2015-02-28 | 2014 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 76024 | Simulations Center |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630 | 15711.7565 | 2014-09-02 |  | 2016-02-24 | 2016-05-04 | 3.861%
2015-02-28 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar |  | 2013-08-29 | 2014-06-17 | UNIT COMPANY | W911KB-14-C-0021 | 25546.7 | 25546.7 | 2014-06-29 |  | 2016-03-20 | 2016-09-01 | 14.83%
2015-02-28 | 2014 | [7 empty] | 2013-08-30 | 2014-04-09 | Tunista Construction, LLC |  | 9525 | 9497.903 | 2014-04-24 |  | 2015-10-15 | 2015-12-18 | 20%
2015-02-28 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar |  | 2014-06-25 | 2014-09-03 | Archer Western Federal JV | W912DW-14-C-0023 | 36998 | 37065.375 | 2014-09-23 |  | 2016-03-16 | 2016-03-16 | 0.5652%
2015-02-28 | 2014 | [7 empty] | 2014-06-25 | 2014-09-03 | The Renew Group, Inc. |  | 1106.039 | 1106.039 | 2014-10-24 |  | 2015-04-22 | 2015-04-22 | 1.109%
2015-02-28 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building |  | 2014-02-28 | 2014-08-28 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165.0006 | 17196.7506 | 2014-08-21 |  | 2016-02-12 | 2016-02-12 | 1.575%
2015-02-28 | 2014 | [7 empty] | 2014-02-28 | 2014-08-28 | Medvolt, LLC |  | 13195.378 | 13195.378 | 2014-10-08 |  | 2016-03-31 | 2016-03-31 | 17.35%
2015-02-28 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56720.967 | 57055.471 | 2014-09-02 |  | 2016-08-22 | 2016-08-22 | 8.772%
2015-02-28 | 2014 | [7 empty] | 2014-05-22 | 2014-09-04 | SEK JV |  | 3339.182 | 3395.4962 | 2014-10-20 |  | 2015-10-20 | 2015-10-24 | 54.17%
2015-02-28 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar |  | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585 | 50585 | 2014-10-06 |  | 2016-05-28 | 2016-05-28 | 0.6472%
2015-02-28 | 2014 | [7 empty] | 2014-07-09 | 2015-01-16 | Swinerton Builders |  | 4214.264 | 4321.837 | 2015-02-11 |  | 2016-08-22 | 2016-08-22 | 21.69%
2015-02-28 | 2014 | Army Active | Major Military Construction | FLORIDA | UNITED STATES | 77539 | Automated Sniper Field Fire Range |  | 2014-07-17 | 2014-09-26 | Barlovento LLC. | W91278-10-D-0072 | 4201.077 | 4201.077 | 2014-12-17 |  | 2015-12-17 | 2015-12-17 | 0%
2015-02-28 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77885 | Runway |  | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9832.807 | 10816.316 | 2014-07-01 |  | 2015-07-01 | 2015-10-15 | 29.31%
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 77980 | Cantonment Area, Roads, Paved |  | 2014-08-12 | 2014-09-16 | FutureNet Group, Inc. | W912QR-09-D-0050 | 1635.599 | 1635.599 | 2014-09-24 |  | 2015-08-20 | 2015-08-20 | 2%
2015-02-28 | 2014 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 78778 | Battlefield Weather Support Facility |  | 2013-12-24 | 2014-06-18 | TJC Engineering | W912QR-14-C-0018 | 4275.114 | 4283.952 | 2014-06-27 |  | 2015-08-21 | 2015-09-20 | 22.57%
2015-02-28 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 79618 | Simulator Building |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440 | 8440 | 2014-08-20 |  | 2016-02-11 | 2016-02-11 | 0.6844%
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 79679 | Materials Analysis Lab |  | 2014-02-03 | 2014-06-10 | Au' Authum Ki, Inc | W912PL-10-D-0109 | 2983.983 | 2983.983 | 2014-07-28 |  | 2015-02-23 | 2015-08-17 | 14.08%
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 80477 | Fragmentation Simulation Lab |  | 2013-04-22 | 2013-12-13 | The Clement Group, L.L.C. | W91278-11-D-0029 | 2341.157 | 2345.214 | 2014-01-23 |  | 2015-07-17 | 2015-07-17 | 47.6%
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80919 | Underground Electric Lines |  | 2014-08-12 | 2014-09-29 | Glen/Mar Construction, Inc. | W912DW-14-C-0029 | 1544.779 | 1544.779 | 2015-02-13 |  | 2016-02-13 | 2016-02-13 | 1.055%
2015-02-28 | 2014 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 81155 | Unmanned Aerial Vehicle Complex |  | 2014-05-01 | 2014-12-05 | SGS, LLC | W9126G-15-C-0005 | 32968.419 | 32968.419 | 2014-12-18 |  | 2016-04-11 | 2016-04-11 | 10%
2015-02-28 | 2014 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81186 | Cadet Barracks, Incr 2 | 79933 | 2012-11-06 | 2013-08-07 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 40000 | 40119.542 | 2013-08-25 |  | 2016-07-07 | 2016-07-07 | 0.03877%
2015-02-28 | 2014 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 81875 | Operations and Maintenance Facilities |  | 2013-12-02 | 2014-05-11 | Edifice-Schlosser JV, LLC | W912DR-14-C-0017 | 17891 | 20302.405 | 2014-05-22 |  | 2015-03-18 | 2015-05-29 | 60.58%
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 82268 | Illinois Ave (PREPO) Yd |  | 2014-07-21 | 2014-09-30 | Tarver Land Development, LLC | W9126G-14-C-0059 | 1748.75 | 1748.75 | 2014-12-03 |  | 2015-04-02 | 2015-04-02 | 2%
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 82371 | Power Plant Facility 994 |  | 2014-11-28 | 2014-09-29 | San Juan Construction, Inc. | W9128A-12-D-0010 | 1596.834 | 1596.834 | 2014-10-27 |  | 2015-09-06 | 2015-09-06 | 0.6609%
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | 85260 | Secure Operations Center |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1724.858 | 1724.858 | 2014-11-05 |  | 2015-11-05 | 2015-11-05 | 0%
2015-02-28 | 2015 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81187 | Cadet Barracks, Incr 3 | 79933 | 2012-11-06 | 2013-08-07 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 51540 | 51540 | 2013-08-25 |  | 2016-07-07 | 2016-07-07 | 0%
2015-02-28 | 2009 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420511 | Readiness Center, Add/Alt |  | 2011-08-31 | 2011-09-15 | Lobar Incorporated | DGS 961-20.1 | 6117 | 5738 | 2011-09-26 | 2013-08-15 | 2012-10-30 | 2014-12-31 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Keep $300K per FME)
2015-02-28 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540105 | Joint Interagency Training Education Center, PH 1 |  | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | DEFK10003 | 77500 | 72200 | 2009-10-01 | 2011-09-30 | 2011-09-28 | 2014-09-30 | 99% | 0 |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Keep $300K per FME)
2015-02-28 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540206 | Multi-Purpose Building, PH II |  | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | DEFK10004 | 4755 | 4624 | 2010-02-01 | 2010-08-30 | 2010-08-26 | 2013-03-31 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2015-02-28 | 2010 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010279 | Urban Assault Course |  | 2010-09-06 | 2010-09-10 | Baggette Construction, Inc. | AC-10-C-0045-S | 2980 | 2396 | 2010-12-01 | 2011-10-11 | 2011-08-08 | 2011-08-08 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060115 | Readiness Center, PH 1 |  | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | W912LA-10-C-0009 | 30711 | 23378 | 2010-11-15 | 2013-10-07 | 2012-02-06 | 2015-01-30 | 95% | 2900 | 390263 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | GUAM | GUAM | 140300 | Readiness Center |  | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | N40192-10-C-1335 | 20766 | 20797 | 2010-05-03 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 95% | 3000 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170611 | Readiness Center, Add/Alt |  | 2010-09-17 | 2010-09-22 | Capital Development Board | W91SMC-10-2-2001-100 | 5560 | 4319 | 2010-10-18 | 2012-03-31 | 2011-09-14 | 2011-09-14 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2015-02-28 | 2010 | Army National Guard | Unspecified Minor Military Construction | MINNESOTA | UNITED STATES | 270263 | CST, Add/Alt |  | 2011-08-09 | 2011-08-19 | LS Black Constructors | W912LM-10-D-0004 | 1954 | 1897 | 2011-09-12 | 2012-11-20 | 2012-08-24 | 2013-12-20 | 100% | 0
2015-02-28 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320143 | Readiness Center |  | 2010-09-27 | 2010-09-27 | The Penta Building Company |  | 25807 | 19910 | 2010-10-25 | 2013-05-01 | 2012-01-23 | 2013-04-19 | 99% | 3112 | 060413 | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370896 | Readiness Center, Add/Alt |  | 2010-09-07 | 2010-09-10 | Architectural Design Studio | W91242-10-2-2002 | 2501 | 2033 | 2010-09-27 | 2011-10-13 | 2011-09-30 | 2011-10-17 | 99% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450252 | Army Aviation Support Facility, Add/Alt |  | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. | W912QG-10-C-0005 | 14759 | 14078 | 2011-02-07 | 2013-04-15 | 2011-12-14 | 2013-05-01 | 99% | 11000 | 090115, 220241 and 220243 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450353 | Army Aviation Support Facility |  | 2010-09-23 | 2010-09-24 | Hendrick Construction | 460114576 | 27936 | 27304 | 2010-11-17 | 2013-06-21 | 2012-08-10 | 2013-06-21 | 75% | 12100 | 220241, 220243, and 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480175 | Armed Forces Reserve Center |  | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 16441 | 14196 | 2011-01-01 | 2012-07-17 | 2012-06-15 | 2013-11-04 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (No more funds needed per FME)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480176 | Field Maintenance Shop, Joint |  | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 5700 | 7021 | 2011-01-01 | 2012-07-17 | 2013-06-15 | 2013-11-04 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (No more funds needed per FME)
2015-02-28 | 2010 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520014 | Regional Training Institute, PH 1 |  | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. | W9127P-10-C-0001 | 19978 | 19493 | 2010-07-01 | 2013-02-15 | 2012-02-20 | 2013-04-23 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050043 | Combined Support Maintenance Shop |  | 2011-06-24 | 2011-07-01 | CDI Contractor, LLC | 970816 | 29887 | 28574 | 2011-11-01 | 2013-08-15 | 2013-07-01 | 2013-10-01 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050163 | Combined Arms Collective Training Facility |  | 2010-12-21 | 2011-05-23 | Crossland Construction Company, Inc. | 9751022 | 18609 | 7413 | 2011-09-19 | 2013-06-13 | 2012-03-23 | 2013-10-15 | 100% | 6500 | 530035 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($8,858)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050173 | Live Fire Shoot House |  | 2011-05-26 | 2011-06-14 | Ross Sparks Builders, Inc. | 9751028 | 2488 | 2267 | 2011-07-01 | 2012-09-18 | 2012-06-07 | 2013-10-15 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060429 | Combined Arms Collective Training Facility |  | 2011-05-12 | 2011-09-20 | Cox Construction Company | W912LA-11-R-0005 | 12379 | 11525 | 2011-12-05 | 2013-06-15 | 2012-06-29 | 2013-09-27 | 99% | 6700 | 361103 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080062 | HAATS/AASF |  | 2011-05-19 | 2011-07-13 | Hensel Phelps Construction Company |  | 38862 | 37413 | 2011-11-01 | 2013-04-01 | 2013-03-31 | 2013-10-31 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080067 | Regional Training Institute |  | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC |  | 50886 | 50926 | 2011-10-01 | 2013-10-01 | 2014-10-18 | 2014-10-03 | 95% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2,000 Formal Reprogramming $9,300 funds from FY10 project savings {PNs: 160120 ($6,000) & 350043 ($3,300)}
2015-02-28 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080201 | Readiness Center |  | 2011-08-12 | 2011-09-16 | Smith Construction Management, LLC |  | 19934 | 18999 | 2011-12-01 | 2013-10-01 | 2013-09-30 | 2014-09-10 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080202 | Readiness Center |  | 2011-08-05 | 2011-08-16 | AP Mountain States |  | 7485 | 7469 | 2011-12-01 | 2012-11-01 | 2012-10-19 | 2012-10-19 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2015-02-28 | 2011 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090010 | Readiness Center (Aviation) |  | 2011-05-27 | 2011-09-22 | Walsh Construction Co. | W912RS-11-C-0017 | 40616 | 32004 | 2011-10-01 | 2013-11-05 | 2013-10-19 | 2013-10-19 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100037 | Armed Forces Reserve Center (JFHQ) |  | 2011-08-03 | 2011-08-18 | Vigil Contracting, Inc. | W912L5-09-2-2001 | 26879 | 25717 | 2011-12-01 | 2014-04-01 | 2013-07-10 | 2014-05-08 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130123 | Readiness Center, Add/Alt |  | 2011-05-17 | 2012-04-17 | TEPA | W912JM-10-D-0018 | 10363 | 10349 | 2012-06-04 | 2013-09-30 | 2013-09-30 | 2014-04-30 | 90% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130127 | Readiness Center |  | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 41100-033-0000078159 | 16941 | 16726 | 2011-12-01 | 2013-05-15 | 2012-11-16 | 2012-11-16 | 85% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | GUAM | GUAM | 140001 | Combined Support Maintenance Shop, Ph 1 |  | 2011-05-31 | 2011-09-01 | NAVFAC Pacific | N40192-10-D-2801-0004 | 18961 | 19300 | 2011-09-12 | 2013-04-19 | 2012-04-20 | 2012-04-20 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2015-02-28 | 2011 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160093 | Barracks (ORTC), Ph 1 |  | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | W912J7-11-C-0002 | 17333 | 13811 | 2011-08-27 | 2013-10-03 | 2013-02-28 | 2014-04-15 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 179237 | Combined Support Maintenance Shop, Add/Alt |  | 2011-09-15 | 2011-09-20 | CORE Construction | W91SMC-09-2-2002 | 14954 | 14464 | 2011-10-24 | 2013-07-17 | 2012-10-05 | 2014-07-31 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200063 | Readiness Center |  | 2011-07-15 | 2011-08-11 | Straub Construction Co., Inc. |  | 26283 | 23235 | 2011-09-23 | 2013-07-01 | 2012-12-07 | 2013-07-15 | 100% | 12461 | 150023 and 490444 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($26,283)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200090 | Field Maintenance Shop |  | 2011-09-01 | 2011-09-26 | The Law Company, Inc. |  | 13243 | 12402 | 2011-11-18 | 2014-04-15 | 2012-10-19 | 2014-04-15 | 100% | 9000 | 150023 and 400066 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($13,244)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220222 | Tactical Unmanned Aircraft System Facility |  | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company | LA11-C-139 | 5470 | 5018 | 2011-09-12 | 2012-12-11 | 2012-07-30 | 2013-06-18 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240186 | Tactical Unmanned Aircraft System Facility |  | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | N40080-10-D-0498 | 5480 | 5583 | 2012-06-01 | 2014-12-06 | 2013-06-15 | 2014-11-21 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250136 | Armed Forces Reserve Center (JFHQ), Ph 2 |  | 2011-09-15 | 2011-09-22 | Nauset Construction Corp. | W912SV-11-C-0004 | 22927 | 21885 | 2011-10-17 | 2012-11-17 | 2012-10-27 | 2014-04-04 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270202 | Field Maintenance Shop |  | 2011-07-19 | 2011-08-08 | Stahl Construction Company | STA006002 | 28894 | 26314 | 2011-10-26 | 2013-05-03 | 2013-01-18 | 2014-04-18 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270267 | Tactical Unmanned Aircraft System Facility |  | 2011-07-21 | 2011-08-08 | Donlar Construction Company | DON050003 | 4413 | 3544 | 2012-04-03 | 2012-12-13 | 2012-10-27 | 2012-12-13 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310107 | Readiness Center |  | 2011-06-15 | 2011-07-12 | The Weltz Company, LLC |  | 11368 | 11339 | 2012-05-07 | 2013-05-06 | 2012-08-08 | 2013-04-01 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310110 | Readiness Center, Add/Alt |  | 2011-08-16 | 2011-08-19 | Kingery Construction Company |  | 3293 | 3339 | 2011-10-01 | 2013-05-06 | 2012-11-06 | 2013-04-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330034 | Classroom Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-25 | Eckman Construction Company, Inc. | 80342R-G | 20742 | 19649 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-03 | 15% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330035 | Barracks Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-26 | Eckman Construction Company, Inc. | 80342R-G | 14880 | 13736 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-30 | 15% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350075 | Readiness Center, Add/Alt |  | 2011-04-19 | 2011-09-29 | Jaynes Corporation | 12-705-0000-1213 | 8481 | 10306 | 2011-12-05 | 2012-12-25 | 2012-10-31 | 2012-10-31 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370898 | Readiness Center, Add/Alt |  | 2011-09-08 | 2011-09-15 | Holden Building Company, Inc. | W912421022003 | 1547 | 1590 | 2011-11-05 | 2012-08-01 | 2012-10-26 | 2012-10-26 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 436021 | Multi Purpose Machine Gun Range |  | 2012-08-27 | 2012-08-29 | Eastern Construction and Electrical Inc. | W912LR-14-B-2004 | 9200 | 9567 | 2014-09-15 | 2015-01-26 | 2015-01-26 | 2015-01-26 | 0% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 436023 | Live Fire Shoot House |  | 2011-07-21 | 2011-09-22 | Remex Co. | W912LR-11-B-0001 | 3077 | 2562 | 2011-11-07 | 2012-09-18 | 2012-12-14 | 2012-12-14 | 65% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440009 | United States Property and Fiscal Office |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 26713 | 21433 | 2012-08-20 | 2015-01-31 | 2014-04-17 | 2015-01-31 | 98% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460085 | Readiness Center |  | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. | W912MM-06-2-20002 | 18255 | 17797 | 2011-11-07 | 2013-03-01 | 2013-01-14 | 2014-11-01 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($18,225)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520034 | Readiness Center (JFHQ) |  | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | W9127P-11-C-0005 | 24850 | 22324 | 2011-11-01 | 2013-11-25 | 2012-08-20 | 2013-08-01 | 62% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530022 | Combined Support Maintenance Shop |  | 2011-06-07 | 2011-06-23 | Pease & Sons, Inc. |  | 24880 | 24115 | 2011-08-22 | 2013-12-12 | 2012-11-03 | 2014-09-23 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), State waiting on demolition of the old CSMS
2015-02-28 | 2011 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540068 | Readiness Center |  | 2011-09-21 | 2011-09-22 | Massaro Corporation |  | 20895 | 19502 | 2011-11-14 | 2013-04-09 | 2013-03-26 | 2013-03-26 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540084 | Readiness Center |  | 2011-06-01 | 2011-09-21 | Langan General Contracting Corp | DEFK1200 | 14145 | 13573 | 2011-10-08 | 2013-04-22 | 2013-03-24 | 2014-06-23 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550139 | Aircraft Parking |  | 2011-08-16 | 2011-09-15 | Buteyn Peterson Construction Co. | NGB-47-11-C-0014 | 5689 | 5960 | 2011-11-01 | 2012-10-09 | 2012-10-29 | 2012-10-17 | 94% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 011006 | Readiness Center, Add/Alt |  | 2012-09-13 | 2012-09-23 | Metro D. Constructions, LLC | AC-12-C-0036-S | 2000 | 1999 | 2012-11-18 | 2013-10-01 | 2013-09-16 | 2014-01-28 | 10% | 0
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 010263 | Readiness Center, Ph2 |  | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. | W912JA-12-C-0001 | 16413 | 14492 | 2012-09-14 | 2013-12-24 | 2013-12-10 | 2013-12-10 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040294 | Readiness Center |  | 2012-02-15 | 2012-08-16 | Haydon Building Corporation-Tem | M11-0045 | 17771 | 17655 | 2012-09-12 | 2013-11-04 | 2013-10-16 | 2014-01-31 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050172 | Convoy Live Fire/Entry Control Point Range |  | 2012-02-14 | 2012-08-16 | USPFO - AK | 9751104 | 3500 | 3604 | 2012-11-07 | 2013-12-20 | 2013-10-28 | 2014-07-15 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | 050190 | Wash Platform, Installation |  | 2013-09-12 | 2013-09-18 | Wilkins Construction, Inc. |  | 1195 | 1759 | 2014-03-10 | 2014-06-23 | 2014-06-23 | 2014-12-22 | 63% | 0
2015-02-28 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060009 | Utilities Replacement Ph1 |  | 2012-07-09 | 2012-08-01 | Cox Construction Co. | W912LA-12-C-0007 | 31073 | 25066 | 2012-12-01 | 2014-09-26 | 2015-03-01 | 2015-04-30 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060170 | Field Maintenance Shop |  | 2012-06-19 | 2012-06-26 | Goshawk LLC | W912LA-12-C-0003 | 7985 | 7482 | 2012-11-08 | 2013-10-20 | 2013-10-14 | 2014-06-06 | 35% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 060432 | Barracks |  | 2012-06-27 | 2012-09-28 | WEP Enterprises | W912LA-11-D-0024 | 1400 | 1131 | 2012-10-15 | 2013-10-07 | 2013-09-20 | 2014-10-30 | 99% | 0 |  | FY07 Congressionally Directed, Used FY10 funds
2015-02-28 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060438 | Tactical Unmanned Aircraft System Facility |  | 2012-06-04 | 2012-07-20 | Red Mountain LLC | W912LA-12-C-0002 | 6114 | 5252 | 2012-08-06 | 2013-11-11 | 2013-10-28 | 2015-02-27 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080093 | Barracks Complex (ORTC) |  | 2012-08-30 | 2012-09-04 | FSA & JKC Joint Venture One, LLC. |  | 42228 | 43807 | 2012-09-24 | 2013-12-03 | 2013-10-28 | 2015-02-28 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080126 | Readiness Center |  | 2012-06-12 | 2012-06-22 | FCI Constructors, Inc. |  | 6397 | 6254 | 2012-09-10 | 2013-12-02 | 2013-10-14 | 2013-10-14 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080206 | Tactical Unmanned Aircraft System Facility |  | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. |  | 3592 | 3892 | 2012-11-05 | 2013-12-03 | 2013-10-28 | 2014-08-15 | 85% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120188 | Convoy Live Fire/Entry Control Point Range |  | 2012-07-31 | 2012-08-16 | Breaking Ground Contracting Co. |  | 2400 | 3000 | 2013-02-13 | 2013-12-16 | 2013-12-02 | 2013-12-02 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120277 | Unit Storage Building (TUAS) |  | 2012-08-30 | 2012-09-14 | C. Young Construction |  | 821 | 821 | 2013-04-13 | 2013-10-19 | 2013-09-12 | 2013-09-12 | 20% | 0
2015-02-28 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130063 | Maneauver Area Training and Equipment Site, Ph 1 |  | 2012-01-12 | 2012-09-11 | J&S Construction Company, Inc. | W912JM-12-R-0011 | 19255 | 19288 | 2012-10-19 | 2013-11-18 | 2013-10-28 | 2015-02-02 | 22% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2015-02-28 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130068 | Readiness Center Ph 1 |  | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC |  | 14457 | 14123 | 2012-09-14 | 2013-04-12 | 2014-03-14 | 2014-10-14 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130120 | Readiness Center |  | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. |  | 10991 | 11239 | 2012-09-10 | 2013-11-18 | 2013-10-28 | 2014-11-24 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150043 | Readiness Center Ph 1 |  | 2012-02-15 | 2012-07-11 | Dawson Technical, LLC | W912J6-12-R-0002 | 31992 | 32580 | 2012-07-23 | 2014-08-11 | 2014-07-23 | 2014-07-23 | 15% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170801 | Readiness Center |  | 2012-09-13 | 2012-09-13 | River City Construction | W91SMC-10-2-2005 | 10871 | 10557 | 2012-11-05 | 2013-05-31 | 2014-10-28 | 2014-09-30 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($10,871)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | ILLINOIS | UNITED STATES | 171005 | Battalion Maintenance Shelter |  | 2012-09-24 | 2012-09-24 | H&N Construction | W91SMC-10-2-2005 | 1210 | 999 | 2012-10-01 | 2013-06-30 | 2013-10-31 | 2014-09-30 | 100% | 0 |  | (Completed - State working on NGB 593)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180012 | JFHQ Add/Alt |  | 2012-09-19 | 2012-09-19 | F.A. WILHELM Construction, Inc. | MDI-SAB-13-C-0012 | 34971 | 34721 | 2012-11-15 | 2014-05-04 | 2013-10-28 | 2015-03-31 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2.000 FY09 {PN: 040026} & Formal Reprogramming $7,271 funds from FY09 project savings {PNs: 040226 ($2,540), 180116 ($3,805), 180137 ($510) and 260211 ($416)}
2015-02-28 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180142 | Railhead Expansion & Container Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 20908 | 19069 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180156 | Deployment Processing Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 8878 | 8255 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 96% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180160 | Operations Readiness Training Complex 1 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 24991 | 26136 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180161 | Operations Readiness Training Complx 2 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 27000 | 27520 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 220233 | Waste Water Treatment Facility |  | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. | LA12-C-117 | 2972 | 2881 | 2012-06-15 | 2013-07-15 | 2013-06-17 | 2014-12-02 | 100% | 0
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230046 | Readiness Center |  | 2012-04-05 | 2012-09-26 | ITSI Gibane |  | 15584 | 14878 | 2012-09-26 | 2015-06-29 | 2014-07-11 | 2015-05-01 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230071 | Armed Forces Reserve Center |  | 2012-11-10 | 2012-09-26 | J.C.N. Construction Co, Inc. |  | 22997 | 24262 | 2012-09-26 | 2015-03-23 | 2014-10-12 | 2015-01-26 | 96% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240017 | Readiness Center Add/Alt |  | 2012-08-29 | 2012-09-11 | The Whiting-Turner Contracting Company | 001B3400152 | 15771 | 12055 | 2012-10-01 | 2015-06-20 | 2014-09-22 | 2015-06-12 | 65% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240187 | Readiness Center Add/Alt |  | 2012-07-23 | 2012-09-11 | Harkins Builders | 001B3400154 | 10296 | 8201 | 2012-10-01 | 2015-03-01 | 2014-09-22 | 2015-03-20 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240193 | Readiness Center |  | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 001B3400155 | 9000 | 9998 | 2012-10-01 | 2015-07-11 | 2014-09-22 | 2015-07-01 | 68% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250135 | Readiness Center |  | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc. | MIL1001-DC1 | 8986 | 9630 | 2012-12-01 | 2013-11-18 | 2013-10-28 | 2014-10-28 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250178 | J-1 Range North Pump and Treat Facility |  | 2012-10-25 | 2012-11-15 | Tetra Tech/Mead & Hunt JV | DACW33-03-D-0006 | 2504 | 2394 | 2013-03-04 | 2013-10-21 | 2013-10-21 | 2014-10-21 | 12% | 0 |  | Used FY13 funds
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270266 | Multipurpose Machine Gun Range |  | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. | WGO010008 | 4718 | 4477 | 2012-09-17 | 2014-01-18 | 2013-12-15 | 2014-06-01 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,718)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280315 | Troop Housing (ORTC) Ph1 |  | 2012-01-12 | 2012-06-22 | DCD-YATES | W9127Q-12-C-0004 | 20710 | 20041 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,710)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280389 | Operations Readiness Training Complx Ph1 |  | 2012-01-12 | 2012-06-22 | DCD-YATES | W9127Q-12-C-0004 | 24411 | 23621 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($24,411)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310085 | Readiness Center |  | 2012-05-29 | 2012-06-05 | Sampson Construction Company, Inc. |  | 21913 | 18727 | 2012-07-01 | 2013-12-13 | 2013-11-22 | 2014-03-25 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310086 | Readiness Center |  | 2012-04-09 | 2012-04-27 | Boyd Jones Construction |  | 9099 | 10002 | 2012-05-01 | 2013-11-01 | 2013-06-27 | 2014-05-23 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEBRASKA | UNITED STATES | 310142 | CATS Waste Water Treatment Facility |  | 2012-06-28 | 2012-08-10 | All Purpose Construction |  | 1536 | 1661 | 2012-09-01 | 2013-10-11 | 2013-09-19 | 2014-04-30 | 100% | 0
2015-02-28 | 2012 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320070 | Field Maintenance Shop |  | 2012-01-12 | 2012-04-17 | CORE Construction |  | 22932 | 21352 | 2012-12-01 | 2013-11-08 | 2013-10-25 | 2014-10-31 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEW HAMPSHIRE | UNITED STATES | 330052 | Readiness Center, Add/Alt |  | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 330052-GC | 1947 | 1943 | 2012-10-07 | 2013-07-29 | 2013-08-13 | 2013-08-13 | 100% | 0 |  | (Closeout procedures are in progress)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340115 | Army Aviation Support Facility |  | 2012-02-15 | 2012-09-19 | Senate Builders & Const Manager | W912KN-12-C-0006 | 48795 | 46170 | 2012-09-19 | 2015-01-31 | 2014-10-18 | 2015-01-31 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350115 | Readiness Center, Add/Alt |  | 2012-01-03 | 2012-04-10 | Jaynes Corporation | 12-08-0000-1219 | 5172 | 4440 | 2012-12-01 | 2013-07-13 | 2013-06-01 | 2013-06-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400605 | Upgrade: Combined Arms Collective Training Facility |  | 2012-01-12 | 2012-08-16 | Benham Companies, LLC | W90FYQ-09-D-0006-9J01 | 10343 | 9308 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2015-01-16 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400606 | Live Fire Shoot House |  | 2012-01-24 | 2012-08-15 | Benham Companies, LLC | W90FYQ-09-D-0006-9J02 | 2995 | 3161 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-06-28 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410026 | Readiness Center |  | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 410026D002 | 13800 | 13190 | 2012-12-01 | 2014-02-21 | 2013-12-28 | 2014-03-20 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430010 | Readiness Center |  | 2012-09-10 | 2012-09-18 | RB Construction Group Inc. | W912LR-12-C-0005 | 40565 | 38365 | 2012-12-01 | 2014-12-05 | 2013-10-28 | 2015-02-28 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($40,565)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450403 | Readiness Center, Add/Alt |  | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. |  | 4290 | 4255 | 2012-10-01 | 2013-09-01 | 2013-10-28 | 2013-10-28 | 10% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490618 | Multi-Purpose Machine Gun Range |  | 2012-09-06 | 2012-09-27 | Cracar Construction | W911YP-12-C-0007 | 6498 | 6577 | 2012-12-01 | 2014-01-06 | 2013-10-28 | 2013-10-28 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | VIRGINIA | UNITED STATES | 510307 | Combined Arms Collective Training Facility |  | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | W912LQ-13-C-0001 | 8316 | 8874 | 2013-04-10 | 2015-04-10 | 2014-10-09 | 2015-02-27 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540085 | Readiness Center Ph1 |  | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | DEK 13002 | 9991 | 11545 | 2012-11-01 | 2014-08-25 | 2014-11-12 | 2014-11-12 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550245 | Tactical Unmanned Aircraft System Facility |  | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. | NGB-47-12-C-0002 | 4250 | 3986 | 2012-07-01 | 2013-10-20 | 2013-05-20 | 2014-05-30 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 011007 | National Guard Readiness Center, Add/Alt |  | 2013-09-24 | 2013-09-26 | Butler Construction Company, LLC. | AC-13-B-0051-S | 1920 | 1904 | 2014-02-03 | 2015-04-24 | 2015-04-24 | 2014-10-01 | 0% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010278 | Live Fire Shoot House |  | 2013-08-01 | 2013-08-23 | Hurst Construction, LLC | AC-13-C-0052-S | 5223 | 5382 | 2013-09-23 | 2014-08-15 | 2014-08-15 | 2014-08-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 040669 | Underground Electrical Lines |  | 2013-09-23 | 2014-04-04 | Ludvik Electric | M13-0037 | 2000 | 1833 | 2014-05-05 | 2014-10-31 | 2014-10-31 | 2014-10-31 | 0% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050139 | Field Maintenance Shop |  | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC | 9751312 | 6577 | 5231 | 2013-08-30 | 2014-10-27 | 2014-10-01 | 2014-10-01 | 99% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060413 | Maneuver Area Training & Equipment Site Ph 3 |  | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793 | 30449 | 2013-10-21 | 2014-10-01 | 2014-10-01 | 2015-09-30 | 67% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 (1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090043 | Combined Support Maintenance Shop |  | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951 | 29988 | 2014-04-26 | 2015-10-01 | 2015-10-01 | 2015-10-09 | 50% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090115 | RIP RAP |  | 2014-08-28 | 2014-09-11 | Nutmeg Companies, Inc. | W91ZRS-12-D-0026-0005 | 3600 | 1292 | 2014-09-22 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 40% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 450252)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100010 | Regional Training Institute Ph1 |  | 2013-06-28 | 2013-07-05 | EDIS Company | 40452 | 5319 | 5265 | 2013-09-23 | 2014-10-20 | 2014-10-01 | 2014-12-23 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120102 | Readiness Center |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) |  | 19345 | 21104 | 2014-03-03 | 2015-02-20 | 2015-02-20 | 2015-09-13 | 60% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120192 | Upgrade: Combined Arms Collective Training Facility |  | 2013-06-07 | 2013-06-25 | Thomas May Construction Company |  | 8705 | 6452 | 2013-10-04 | 2014-10-20 | 2014-10-01 | 2014-10-01 | 2% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120228 | Ready Building |  | 2013-09-05 | 2013-09-10 | Halfacre Construction Company |  | 1939 | 1920 | 2013-10-14 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 0% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | GUAM | GUAM | 140040 | JFHQ Ph 4 |  | 2013-08-22 | 2013-09-24 | NAVFAC Pacific | N40192-10-D-2800 | 8221 | 8089 | 2013-10-21 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150023 | Army Aviation Support Facility Ph1 |  | 2013-11-13 | 2014-09-11 | USPFO - HI | W912J6-14-R-00001 | 35078 | 33472 | 2014-09-22 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2015-02-28 | 2013 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160100 | ORTC (Barracks) Ph2 |  | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692 | 37726 | 2013-10-07 | 2014-08-01 | 2014-08-01 | 2016-01-07 | 58% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180106 | Field Maintenance Shop |  | 2013-09-24 | 2013-09-24 | Gamong Construction | MDI-SAB-14-C-0002 | 8705 | 8491 | 2014-07-21 | 2014-12-25 | 2014-12-25 | 2015-07-01 | 75% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180144 | Armed Forces Reserve Center Add/Alt |  | 2013-09-20 | 2013-09-20 | Ziolkowski Construction | MDI-SAB-14-C-0001 | 20311 | 22016 | 2014-04-21 | 2015-05-29 | 2015-08-23 | 2015-05-29 | 21% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200102 | Taxiway, Ramp & Hangar Alterations |  | 2013-05-21 | 2013-06-14 | Senne & Co |  | 9188 | 8555 | 2013-07-22 | 2014-05-02 | 2014-10-01 | 2014-07-04 | 70% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | KANSAS | UNITED STATES | 200127 | Water Distribution Lines, Portable |  | 2013-09-16 | 2013-09-24 | Harbin Construction | W912JC-12-D-5308 | 1440 | 1627 | 2014-04-07 | 2014-06-13 | 2014-06-13 | 2015-04-02 | 95% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210001 | Army Aviation Support Facility |  | 2013-05-17 | 2013-06-04 | DW Wilburn | CT2 1300000269 | 30953 | 26333 | 2013-07-08 | 2014-11-10 | 2014-10-01 | 2015-04-08 | 80% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220241 | National Guard Readiness Center |  | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300 | 8937 | 2014-09-22 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 5% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353 )
2015-02-28 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220243 | Jackson Barracks Billeting Replacement |  | 2013-07-25 | 2014-07-25 | Gibbs Construction | LA06-C-081 | 5700 | 3817 | 2014-07-25 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 100% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $3,000 - PN: 450252, $2,700 - PN: 450353)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 240194 | Combat Pistol/MP Firearms Qualification Course |  | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 1920 | 1740 | 2014-01-06 | 2015-09-18 | 2014-09-22 | 2015-09-18 | 20% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250065 | Unit Training Equipment Site |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279 | 21234 | 2014-04-07 | 2015-07-30 | 2015-07-30 | 2015-10-15 | 28% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250196 | Water Well, Non-Potable |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District |  | 2000 | 1838 | 2013-06-03 | 2013-12-02 | 2013-12-01 | 2013-12-01 | 0% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270236 | Scout Reconnaissance Range |  | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. | 67879 | 12783 | 13274 | 2013-09-23 | 2015-08-01 | 2015-10-01 | 2016-01-01 | 62% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270238 | Readiness Center |  | 2013-08-08 | 2013-08-14 | LS Black Constructors | W912LM-13-C-0007 | 16443 | 17505 | 2013-09-30 | 2015-10-15 | 2015-10-15 | 2015-10-28 | 62% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290176 | Regional Training Institute |  | 2013-07-26 | 2013-08-01 | KCI Construction Company | T1203-01B | 17410 | 15846 | 2013-12-09 | 2015-02-28 | 2015-02-28 | 2015-07-21 | 84% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | MONTANA | UNITED STATES | 300032 | Readiness Center |  | 2013-04-21 | 2013-06-24 | Jackson Contractor Group, Inc. | W9124V-06-2-2001 | 11606 | 12497 | 2013-07-08 | 2014-12-15 | 2015-01-09 | 2015-01-21 | 100% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340110 | Regional Training Institute |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885 | 31977 | 2014-10-15 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 16% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340130 | Communication Lines and Ductbank, Underground |  | 2014-09-19 | 2014-09-26 | Rome Management Associates, LLC | W912KN-13-D-0029 | 2228 | 1457 | 2014-10-03 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 5% | 0 |  | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition |  | 2014-08-18 | 2014-09-24 | Smithco Inc. | AGND14-52 | 1194 | 2000 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 1% | 0
[11 empty] | Peterson Mechanical, Inc. | AGND14-53 | 468
[11 empty] | Grotberg Electrical, Inc. | AGND14-54 | 311
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380123 | RIP RAP |  | 2013-09-02 | 2013-12-02 | Close Construction Company | AGND14-01 | 1688 | 1889 | 2013-12-09 | 2014-08-30 | 2014-08-30 | 2015-06-30 | 91% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390230 | Readiness Center |  | 2013-04-01 | 2013-05-03 | Barton Marlow Company | Construction ADJ-090001 | 11607 | 8758 | 2013-08-01 | 2014-01-10 | 2013-12-01 | 2015-02-21 | 99% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Air National Guard | Major Military Construction | OHIO | UNITED STATES | 390256 | Field Maintenance Shop Add/Alt |  | 2013-06-07 | 2013-09-19 | Henderson Contractors, Inc. | W91364-13-Q-0003 | 2998 | 2971 | 2013-11-04 | 2014-10-28 | 2014-07-02 | 2015-04-30 | 99% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390263 | Hutments |  | 2014-05-12 | 2014-07-09 | USPFO - OH | USPFO - OH | 2900 | 2662 | 2014-07-16 | 2015-06-15 | 2015-06-15 | 2015-06-15 | 71% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400066 | Operations Readiness Training Complex |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29197 | 27557 | 2013-10-25 | 2014-10-01 | 2014-10-01 | 2016-02-22 | 27% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 420542 | Controlled Access Secure Facility |  | 2014-07-09 | 2014-10-24 | Miller Bros. Construction, Inc. | W912KC-14-R-0005 | 1825 | 1896 | 2014-10-30 | 2015-11-13 | 2015-11-13 | 2015-11-13 | 0% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430081 | Readiness Center (JFHQ) |  | 2013-06-27 | 2013-09-26 | R B Construction Group Inc. | W912LR-13-C-0001 | 18294 | 17628 | 2014-03-03 | 2015-09-18 | 2015-09-18 | 2015-09-25 | 40% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | PUERTO RICO | 430622 | Sanitary Sewer |  | 2014-04-04 | 2014-08-27 | Integrated Construction Services, Inc. | W912LR-14-B-2005 | 1535 | 1897 | 2014-09-15 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430804 | Refill Station Building |  | 2013-06-25 | 2013-09-20 | Design Build S E |  | 2128 | 510 | 2013-10-28 | 2015-05-08 | 2015-05-08 | 2015-05-08 | 6% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430806 | Readiness Center |  | 2013-06-06 | 2013-09-26 | Design Build S E | W912LR-13-C-0002 | 3675 | 3667 | 2014-02-10 | 2015-05-15 | 2015-05-15 | 2015-06-19 | 0% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490076 | BEQ Facility (Regional Training Institute) |  | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 137861 | 14508 | 15859 | 2013-08-12 | 2014-11-10 | 2014-10-01 | 2014-11-30 | 99% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490444 | Regional Training Institute Ph2 |  | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 137862 | 28772 | 28280 | 2013-08-26 | 2014-09-30 | 2014-09-30 | 2015-03-30 | 86% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | UTAH | UNITED STATES | 490803 | Unheated Aircraft Storage Hangar |  | 2013-11-06 | 2014-07-18 | Keller Construction Inc. | 147589 | 2000 | 1925 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 30% | 0
2015-02-28 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530015 | Readiness Center |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | USACE Construction Contract | 33853 | 30542 | 2013-09-23 | 2015-10-26 | 2015-08-20 | 2015-08-27 | 58% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530035 | National Guard Readiness Center |  | 2014-08-15 | 2014-08-20 | Absher Construction | Absher Construction | 26000 | 23821 | 2014-10-06 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 30% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540075 | Readiness Center |  | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734 | 14988 | 2014-04-07 | 2015-09-11 | 2015-09-11 | 2015-09-11 | 70% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550142 | Field Maintenance Shop |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673 | 9180 | 2013-10-28 | 2014-10-01 | 2014-10-01 | 2015-04-15 | 25% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction | WISCONSIN | UNITED STATES | 550161 | National Guard Readiness Center Addition |  | 2013-09-24 | 2013-09-25 | Miron Construction | NGB-47-13-C-0009 | 1920 | 909 | 2013-12-12 | 2014-09-01 | 2015-07-01 | 2014-08-01 | 80% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 011014 | National Guard Readiness Center Add/Alt |  | 2014-08-14 | 2014-08-19 | Carmon Construction, Inc. | AC-14-C-0045-S | 4000 | 3756 | 2014-10-06 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050182 | Scout REECE Gunnery Complex |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-B-0001 | 21000 | 16758 | 2014-10-20 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120195 | Ready Building |  | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | 120195 D-B Kokolakis | 5700 | 5300 | 2014-04-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170033 | National Guard Readiness Center |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2004-100 | 14000 | 16000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170127 | Aircraft Maintenance Hangar |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2003-100 | 28000 | 30000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250095 | Enlisted Barracks, Transient Training Addition |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000 | 20559 | 2014-09-15 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260051 | Enlisted Barracks, Transient Training |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000 | 17398 | 2014-08-11 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270014 | National Guard Readiness Center |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000 | 17943 | 2014-10-22 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 5% | 0
2015-02-28 | 2014 | Army National Guard | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 281305 | Raw Sewage Lagoon and Oxidation Pond |  | 2014-09-24 | 2014-09-26 | Miller Enterprises | NGB22-14-C-0007-S | 1950 | 1039 | 2014-09-30 | 2005-04-30 | 2015-04-30 | 2015-04-30 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280272 | National Guard Readiness Center |  | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB22-14-C-0003-S | 4500 | 4718 | 2014-07-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280423 | Water Supply/Treatment Building, Potable |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000 | 4581 | 2014-08-15 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290191 | National Guard Vehicle Maintenance Shop |  | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01C | 9100 | 7355 | 2015-05-12 | 2012-04-30 | 2015-07-31 | 2015-06-26 | 30% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290221 | Aircraft Maintenance Hangar |  | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 5000 | 4399 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360161 | National Guard Readiness Center Alteration |  | 2014-09-17 | 2014-09-30 | Design Resources Group Architects, A.I.A, Inc. | 44573 | 31000 | 29614 | 2014-10-20 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390292 | Sanitary Sewer |  | 2014-04-04 | 2014-09-04 | USPFO - OH | W91364-13-D-0003 | 5200 | 4974 | 2014-09-08 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 30% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420051 | Aircraft Maintenance Instructional Building |  | 2014-08-29 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 40000 | 31940 | 2014-10-20 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430070 | Maneuver Area Training & Equipment Site Addition |  | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600 | 4418 | 2014-09-15 | 2015-05-30 | 2015-05-30 | 2015-05-30 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450131 | National Guard Vehicle Maintenance Shop |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | 460003 | 13000 | 12400 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450283 | National Guard Readiness Center |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | 460003 | 13000 | 12401 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2015-02-28 | 2014 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560081 | National Guard Readiness Center |  | 2013-12-16 | 2014-03-11 | Layton Construction Company, Inc. | 13002900601 | 10200 | 9748 | 2013-10-10 | 2015-03-31 | 2015-03-31 | 2015-08-31 | 25% | 0
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146136 | BACHELOR ENLISTED QUARTERS |  | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | N4008511C4026 AWD | 42882 | 42019 | 2011-06-16 | 2015-03-31 | 2013-07-07 |  | 86%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146148 | MISSILE MAGAZINE |  | 2010-10-21 | 2011-06-02 | SAUER, INC. | N4008511C4010 P00003 | 4779 | 4779 | 2011-06-16 | 2014-01-23 | 2012-07-10 |  | 97%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND |  | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091 | 27629 | 2013-09-19 | 2016-02-24 | 2016-01-18 | 2016-02-24 | 35%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146164 | MARINER'S BAY LAND ACQUISITION BOGUE |  |  | 2011-07-01 | NAVY STANDARD DOCUMENT | N4008509RP00103 | 4002 | 3706 | 2011-07-15 |  |  |  | 93%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146176 | STATION INFRASTRUCTURE UPGRADES |  | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | N4008510D0261 0003 | 5850 | 7300 | 2011-06-15 | 2013-10-10 | 2012-11-25 | 2013-10-10 | 100%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146601 | ARMORY |  | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0006 | 11782 | 11439 | 2013-09-19 | 2015-04-20 | 2015-04-08 | 2015-05-13 | 85%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY |  | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0003 | 14067 | 17432 | 2012-03-29 | 2014-04-29 | 2013-08-14 |  | 95%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243313 | ENTRY CONTROL POINT (GATE 5) |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974 | 10345 | 2014-01-03 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 17%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | N6247310D5480 0012 | 9928 | 9373 | 2011-06-17 | 2012-06-15 | 2012-06-17 |  | 98%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M00263382 | FRONT GATE AT/FP IMPROVMENTS |  | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513 | 11024 | 2013-10-30 | 2015-10-11 | 2015-04-12 | 2015-10-11 | 41%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264541 | ADDITION, MCU RESEARCH CENTER |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 31343 | 29440 | 2012-10-09 | 2015-02-17 | 2014-08-16 |  | 97% | 3531 | Sequestration Reprogramming
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR |  | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0020 | 11118 | 11221 | 2012-09-25 | 2015-05-29 | 2014-03-28 |  | 99%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462 | 28703 | 2013-10-07 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 13%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 |  | 2011-06-20 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 45465 | 34568 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 33% | 8039 | Sequestration Reprogramming
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 |  | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222 | 23835 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 47%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION |  | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | N4008010D0497 0011 | 6555 | 7004 | 2012-08-10 | 2014-09-26 | 2013-09-05 |  | 76%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL |  | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | N6274209D1174 JU01 | 34087 | 31012 | 2011-10-14 | 2013-09-26 | 2013-08-09 | 2014-04-30 | 100%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264611 | BACHELOR ENLISTED QUARTERS |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 32910 | 31700 | 2012-10-13 | 2015-05-11 | 2014-10-16 | 2015-03-18 | 89%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264612 | ENLISTED DINING FACILITY |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 5028 | 5150 | 2012-10-13 | 2015-05-11 | 2014-10-16 | 2015-03-18 | 95%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264615 | SNCO ACADEMIC FACILITY ADDITION |  | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | N4008010D0493 0002 | 6836 | 6730 | 2011-07-04 | 2013-07-22 | 2012-12-21 |  | 96%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264621 | EMBASSY SECURITY GROUP FACILITIES |  | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081 | 25418 | 2013-03-14 | 2015-08-15 | 2015-03-15 | 2015-03-25 | 58%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264632 | ACADEMIC INSTRUCTION FACILITY |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 60736 | 60277 | 2012-10-09 | 2015-02-17 | 2014-08-16 |  | 95% | 2502 | N47608561
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264644 | WEAPONS TRAINING BATALLION MESS HALL |  | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168 | 12678 | 2013-09-18 | 2015-12-29 | 2015-04-22 | 2015-04-22 | 30%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318006 | PHYSICAL FITNESS CENTER, CAMP SMITH |  | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | N6274209D1171 HC01 | 28891 | 27853 | 2011-06-30 | 2014-04-03 | 2013-03-07 |  | 97%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318816 | WATERFRONT OPERATIONS FACILITY |  | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 0006 | 16634 | 15092 | 2011-07-14 | 2015-09-30 | 2013-11-16 |  | 79%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318822 | MCAS OPERATIONS COMPLEX |  | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 HC01 | 52970 | 51564 | 2012-05-02 | 2014-12-29 | 2014-03-17 |  | 90%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318852 | 3RD RADIO BATTALION COMPLEX |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407 | 17477 | 2014-09-19 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 0%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318858 | BACHELOR ENLISTED QUARTERS |  | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6247811C1492 AWD | 62691 | 61087 | 2011-09-14 | 2015-05-30 | 2014-08-21 |  | 98% | 17925 | N60191527, N60191582, Sequestration Reprogramming
2015-02-28 | 2014 | Marine Corps Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | M0031886167 | TEMPOARY MEDICAL FACILITY SITE PREPARATION |  |  | 2014-12-22 | CT JV | N6247814D4004 KB01 | 1667 | 1529 | 2015-01-05 |  |  |  | 9%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318864 | AIRCRAFT MAINTENANCE EXPANSION |  | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | N6274214C1315 AWD | 16968 | 15209 | 2014-04-30 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 23%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720 | 15150 | 2014-10-14 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 1%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318904 | MV-22 HANGAR AND INFRASTRUCTURE |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 63056 | 56060 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 45%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318905 | AIRCRAFT STAGING AREA |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 11118 | 7014 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 31%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811014 | TRUCK COMPANY OPERATIONS COMPLEX |  | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | N6247311C0405 AWD | 52425 | 50602 | 2011-10-06 | 2015-06-03 | 2013-09-21 | 2015-06-03 | 93%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE |  | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0002-PC000002 | 11746 | 9659 | 2012-04-06 | 2013-08-05 | 2013-01-21 |  | 89% | 760 | N00246909
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811040 | INTERSECTION BRIDGE AND IMPROVEMENTS |  | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | N6247309D1606 0009 | 11432 | 13971 | 2012-09-07 | 2014-05-23 | 2013-09-27 |  | 96%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811043A | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | M006811043 | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | N6247310C5011 PC000001 | 29295 | 25324 | 2010-11-12 | 2015-05-13 | 2012-10-12 | 2015-08-21 | 61%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811044 | CONVEYANCE/WATER TREATMENT |  | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | N6247312C5033 AWD | 98236 | 83466 | 2012-10-13 | 2016-12-06 | 2016-01-13 | 2016-01-13 | 36%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811045 | NEW POTABLE WATER CONVEYANCE |  | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242 | 62687 | 2012-10-12 | 2016-12-21 | 2016-03-31 | 2016-03-31 | 44% | 16682 | N684691400
2015-02-28 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811046 | NORTH AREA WASTE WATER CONVEYANCE |  | 2014-08-28 | 2014-11-25 | ORION CONSTRUCTION CORPORATION | N6247310D5419 0012 | 75135 | 43741 | 2014-12-09 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 0%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811109 | BACHELOR ENLISTED QUARTERS, LAS FLORES |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 36173 | 33977 | 2011-10-13 | 2014-06-05 | 2013-10-13 |  | 99%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811113 | BACHELOR ENLISTED QUARTERS, 24 AREA |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 41889 | 39187 | 2011-10-13 | 2014-06-05 | 2013-10-13 |  | 99%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811176 | SAN JACINTO ROAD EXTENSION |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428 | 4476 | 2014-10-08 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 1%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811200 | MARINE CORPS ENERGY INITIATIVE |  | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | N6247310D5483 0003 | 9779 | 9567 | 2011-08-09 | 2013-06-21 | 2012-08-04 | 2014-01-16 | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681310 | SMALL ARMS MAGAZINE, EDSON RANGE |  | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | N6247309D1618 0004 | 3760 | 3191 | 2011-06-21 | 2015-01-29 | 2012-07-06 |  | 87%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681532 | ARMORY, 1ST MARINE DIVISION |  | 2012-04-23 | 2012-08-31 | A&D GC INC | N6247309D1658 0006 | 11201 | 10470 | 2012-09-14 | 2014-04-23 | 2013-12-24 |  | 99%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169420 | PHYSICAL FITNESS CENTER, BEAUFORT |  | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | N6945011C1760 AWD | 14780 | 14868 | 2011-09-21 | 2013-05-24 | 2013-06-08 | 2013-07-16 | 100%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169427 | GROUND SUPPORT EQUIPMENT SHOP |  | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | N6945013D1761 0001 | 10936 | 10759 | 2013-08-22 | 2015-04-08 | 2014-08-07 |  | 85%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169442 | VERTICAL LANDING PADS FOR F-35B |  | 2011-12-06 | 2012-03-30 | HEAD, INC. | N6945012C1758 AWD | 18987 | 18046 | 2012-04-13 | 2013-10-21 | 2013-08-07 | 2013-09-27 | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169444 | TRAINING AND SIMULATOR FACILITY |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 40940 | 38703 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169454 | F-35B AIRCRAFT HANGAR FOR FRS-2 |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 45398 | 45874 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 100%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169456 | SIMULATED LHD FLIGHT DECK |  | 2012-08-27 | 2013-06-26 | HEAD, INC. | N6945013C1773 AWD | 12302 | 12013 | 2013-07-10 | 2015-05-29 | 2014-07-11 |  | 94%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  | 2012-11-15 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643 | 36591 | 2014-08-29 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 8%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169472 | AIRFIELD SECURITY UPGRADES |  | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | N6945013C1772 AWD | 11043 | 12738 | 2013-07-15 | 2014-10-28 | 2014-03-28 |  | 89%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204925 | DIP TANK CLEANING FACILITY |  | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | N6247309D1616 0009 | 7970 | 7893 | 2012-04-04 | 2014-09-18 | 2013-09-27 |  | 92%
2015-02-28 | 2011 | Marine Corps Reserve | Military Family Housing Improvement |  | JAPAN | M626130501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 |  | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | N4008411C5504 AWD | 11626 | 11102 | 2011-10-06 | 2013-02-28 | 2013-01-14 | 2013-02-28 | 100%
2015-02-28 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 |  | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | N4008412D6501 0002 | 13357 | 12685 | 2012-08-13 | 2013-12-13 | 2013-11-23 |  | 100%
2015-02-28 | 2013 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 |  | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | N4008414C5500 AWD | 17551 | 16715 | 2014-06-22 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 11%
2015-02-28 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626131001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 |  | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | N4008412D6501 0004 | 11335 | 10949 | 2012-08-14 | 2015-02-20 | 2014-12-20 | 2015-02-02 | 100%
2015-02-28 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 |  | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545 | 15632 | 2014-10-13 | 2016-02-02 | 2016-02-02 |  | 0%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613995 | MAINTENANCE HANGAR IMPROVEMENTS |  | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT | N6274214MP00027 | 4947 | 4926 | 2014-06-06 | 2015-06-14 | 2015-06-14 | 2015-06-14 | 20%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH |  | 2014-04-07 | 2014-07-25 | NAVY STANDARD DOCUMENT | N6274214MP00039 | 6304 | 6304 | 2014-08-08 | 2015-09-24 | 2015-09-24 | 2015-09-24 | 0%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974378 | SECURITY OPERATIONS COMPLEX |  | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316 | 13697 | 2013-11-14 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 6%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974447A | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 30492 | 29300 | 2011-06-23 | 2013-12-05 | 2012-10-08 |  | 98%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 47715 | 46237 | 2011-06-23 | 2013-12-05 | 2012-10-08 |  | 99%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974533 | SIMULATOR FACILITY (JSF) |  | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0002 | 26438 | 23252 | 2011-06-17 | 2013-04-19 | 2012-06-02 |  | 99% | 1897 | M67925001
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974535 | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | N6247308D8617 0004 | 32048 | 32283 | 2012-09-20 | 2015-03-12 | 2014-07-07 | 2015-03-12 | 97% | 5983 | N684691400
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0003 | 79917 | 78598 | 2012-04-03 | 2014-12-17 | 2014-05-20 |  | 96%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974546 | UTILITY UPGRADES (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 40106 | 36761 | 2011-06-21 | 2013-06-14 | 2012-07-08 |  | 99% | 2879 | M67925001
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974566 | COMBAT AIRCRAFT LOADING APRON |  | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247309D1603 0013 | 12671 | 11823 | 2013-10-11 | 2015-03-02 | 2014-09-22 | 2015-03-02 | 41%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) |  | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0002 | 19793 | 16195 | 2011-08-10 | 2012-12-14 | 2012-07-25 |  | 99% | 525 | M67925001
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974575 | AUXILIARY LANDING FIELD (JSF) |  | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | N6247312C1802 AWD | 29475 | 28571 | 2012-07-09 | 2014-02-21 | 2013-06-25 |  | 95% | 5128 | N42237636
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974578 | VAN PAD RELOCATION (JSF) |  | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | N6247309D1653 0003 | 15045 | 14670 | 2011-09-26 | 2013-01-22 | 2012-09-11 | 2012-09-11 | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 54843 | 54497 | 2011-06-21 | 2013-06-14 | 2012-07-08 |  | 99%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001003 | STAFF NCO ACADEMY FACILITIES |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260 | 28029 | 2013-09-19 | 2015-11-08 | 2015-09-01 | 2015-11-08 | 40%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC |  | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | N4008510D5329 0002 | 12906 | 12861 | 2011-06-16 | 2015-02-06 | 2012-12-01 |  | 94%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001030 | SQUAD BATTLE COURSE |  | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0003 | 16292 | 12445 | 2012-07-05 | 2015-01-24 | 2014-05-17 |  | 97%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011034 | 2ND INTEL BN OPERATIONS COMPLEX |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 79767 | 81151 | 2011-07-13 | 2015-09-20 | 2014-02-28 |  | 95% | 1292 | M67925001
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 32625 | 30995 | 2011-07-13 | 2015-09-20 | 2014-02-28 |  | 92%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP |  | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | N4008510D0259 0007 | 6613 | 6019 | 2011-07-11 | 2013-05-13 | 2012-08-20 |  | 92%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 43950 | 40300 | 2011-07-13 | 2015-04-11 | 2013-07-13 |  | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 40236 | 38214 | 2011-09-14 | 2015-05-15 | 2013-10-08 | 2014-06-24 | 100% | 689 | M67925001
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER |  | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | N4008512C7719 AWD | 74707 | 72177 | 2012-05-14 | 2015-05-30 | 2014-07-24 | 2015-03-12 | 94%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 39788 | 37923 | 2011-09-14 | 2015-05-15 | 2013-10-08 |  | 99% | 1421 | M67925001
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011256 | MESS HALL ADDITION, COURTHOUSE BAY |  | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0006 | 1499 | 1379 | 2011-06-16 | 2012-11-25 | 2012-11-25 |  | 98%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011264 | UTILITY EXPANSION, HADNOT POINT |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 55206 | 55215 | 2011-10-10 | 2015-09-30 | 2013-10-22 |  | 95%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011265 | UTILITY EXPANSION, FRENCH CREEK |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 54795 | 46667 | 2011-10-10 | 2015-09-30 | 2013-10-22 |  | 97%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011267 | MESS HALL, FRENCH CREEK |  | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | N4008511C4022 AWD | 24316 | 21546 | 2011-06-16 | 2014-03-07 | 2013-02-06 |  | 81%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE |  | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | N4008511C4008 AWD | 54720 | 55106 | 2011-09-13 | 2015-03-31 | 2013-09-07 |  | 98%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4021 AWD | 43568 | 40987 | 2011-06-16 | 2015-06-01 | 2013-08-30 |  | 99%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4020 AWD | 46005 | 42200 | 2011-06-16 | 2014-08-29 | 2013-08-13 | 2014-08-29 | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 49005 | 44606 | 2011-07-13 | 2015-04-11 | 2013-07-13 | 2015-04-11 | 96%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011323 | ARMORY II MEF, WALLACE CREEK |  | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | N4008511C4001 P00004 | 5941 | 5414 | 2011-12-20 | 2015-04-11 | 2013-07-13 | 2015-04-11 | 99% | 4148 | M00681159
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011353 | LANDFILL, PHASE 4 |  | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529 | 13843 | 2014-09-08 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 35%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK |  | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101 | 26432 | 2012-07-13 | 2015-06-15 | 2014-07-29 |  | 98%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011383 | BASE ENTRY POINT AND ROAD |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235 | 62992 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 77%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011384 | BASE ACCESS AND ROAD, PHASE 3 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666 | 28757 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 59%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-10-08 | 2011-05-31 | URS-IAP LLC | N6247006D6009 0016-02 | 8868 | 8147 | 2011-06-14 | 2012-12-06 | 2012-09-27 |  | 98%
2015-02-28 | 2012 | Marine Corps Active | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | M670011425 | OVERHEAD RANGE BAFFLE SYSTEM |  | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008511D8026 0008 | 2297 | 2215 | 2013-03-06 | 2014-12-30 | 2014-04-17 |  | 97%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011445 | STEAM DECENTRALIZATION (CAMP JOHNSON) |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 2123 | 1917 | 2015-02-06 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 1%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011447 | STEAM DECENTRALIZATION (HADNOT POINT) |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 9605 | 9028 | 2015-02-06 |  |  |  | 1%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011448 | STEAM DECENTRALIZATION, BEQ NODES (HADNOT POINT) |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 15756 | 14886 | 2015-02-06 |  |  |  | 1%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312 | 13231 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 9%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001683 | HANGAR |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62154 | 59489 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 96%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001687 | MV-22 MAINTENANCE HANGAR (HMLA) |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62617 | 59684 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 95%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001705 | AIRCRAFT MAINTENANCE HANGAR AND APRON |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 57582 | 64469 | 2012-06-12 | 2015-02-19 | 2014-07-07 |  | 99%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001710 | ORDNANCE LOADING AREA ADDITION |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 7768 | 7380 | 2012-06-12 | 2015-02-19 | 2014-07-07 |  | 94%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001711 | PERSONNEL ADMINISTRATION CENTER |  | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0018 | 6449 | 5495 | 2013-09-20 | 2015-07-06 | 2015-07-06 | 2015-07-06 | 70%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001726 | REGIONAL COMMUNICATION STATION |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159 | 10031 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 10%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  | 2013-12-06 | 2014-09-10 | BLUEFORGE, LLC | N6945014D1271 0001 | 14685 | 14300 | 2014-09-24 | 2016-01-25 | 2016-01-25 | 2016-01-25 | 1%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004954 | CERS DISPATCH FACILITY |  | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | N6945012D1769 0005 | 1248 | 1171 | 2014-06-16 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 42%
2015-02-28 | 2011 | Marine Corps Active | Military Family Housing Improvement | DISTRICT OF COLUMBIA | UNITED STATES | M670291101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 |  | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0001-07 | 41 | 39 | 2011-01-28 | 2011-05-12 | 2011-05-13 | 2011-05-08 | 100%
2015-02-28 | 2014 | Marine Corps Reserve | Major Military Construction | MISSOURI | UNITED STATES | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019 | 15845 | 2014-09-05 | 2016-02-23 | 2016-02-23 | 2016-02-23 | 2%
2015-02-28 | 2011 | Marine Corps Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | M67399092 | TANK VEHICLE MAINTENANCE FACILITY |  | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | N6247309D1615 0041 | 6458 | 6168 | 2011-10-06 | 2013-03-11 | 2012-09-21 | 2013-03-11 | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE |  | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | N6247310C5007 PC000001 | 51987 | 51426 | 2011-06-17 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 100%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA |  | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819 | 20083 | 2012-08-27 | 2016-05-03 | 2014-09-02 | 2016-05-03 | 19%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399212 | CHILD DEVELOPMENT CENTER |  | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | N6247310D5412 0006 | 21313 | 20506 | 2012-06-19 | 2015-05-19 | 2013-12-12 | 2015-05-19 | 58%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399541 | MULTI-PURPOSE BUILDING ADDITION |  | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | N6247309D1655 0003 | 15610 | 13844 | 2012-10-11 | 2014-04-20 | 2014-04-20 |  | 71%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399991 | LAND EXPANSION |  |  | 2015-01-15 | NAVY STANDARD DOCUMENT | N6247314MPRM002 | 2249 | 1174 | 2015-01-29 |  |  |  | 10%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction |  | JAPAN | M67400201 | AIRFIELD SECURITY UPGRADES |  | 2013-11-08 | 2014-04-18 | NAVY STANDARD DOCUMENT | N6274214MP00024 | 2881 | 2861 | 2014-05-02 | 2015-10-26 | 2016-02-10 | 2015-10-26 | 9%
2015-02-28 | 2013 | Marine Corps Active | Unspecified Minor Military Construction |  | JAPAN | M67400305 | DEMOLISH 45 HOUSING UNITS, KISHABA HOUSING |  | 2013-07-10 | 2014-09-25 | NAVY STANDARD DOCUMENT | N6274214MP00043 | 1729 | 1719 | 2014-10-09 | 2015-06-29 | 2015-06-29 | 2015-06-29 | 0%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604109 | CNAT/FRS AVIATION TRAINING AND BEQ |  | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0434 AWD | 51999 | 46315 | 2011-09-26 | 2014-06-23 | 2014-01-08 |  | 99% | 15930 | M67925001, N61151162, Sequestration Reprogramming
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604111 | MALS-39 MAINTENANCE HANGAR EXPANSION |  | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | N6247310D5409 0003 | 47061 | 33412 | 2011-07-06 | 2013-10-29 | 2013-03-13 |  | 86% | 12329 | M67925001
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604113 | MV-22 AVIATION SIMULATOR BUILDING |  | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | N6247309D1619 0008 | 4380 | 4092 | 2013-06-27 | 2014-09-18 | 2014-09-21 |  | 98%
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604114 | MV-22 DOUBLE HANGAR REPLACEMENT |  | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0004 | 40539 | 38863 | 2012-08-03 | 2015-12-02 | 2015-08-10 | 2015-08-10 | 59% | 6761 | N684691400
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604116 | MV-22 AVIATION PAVEMENT |  | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | N6247309D1605 0012 | 14938 | 11071 | 2012-07-26 | 2015-07-08 | 2014-01-03 |  | 75% | 856 | N684691400
2015-02-28 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604117 | MV-22 AVIATION FUEL STORAGE |  | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | N6247007D7000 FZN7 | 7437 | 7221 | 2013-11-21 |  | 2013-10-07 | 2015-10-07 | 30%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695005 | PAINT AND BLAST FACILITY |  | 2011-04-29 | 2011-09-16 | SAUER, INC. | N6945009D1277 0005 | 20345 | 19809 | 2011-09-30 | 2014-03-10 | 2013-05-16 |  | 97%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695012 | CONTAINER STAGING AND LOADING LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3380 | 2529 | 2011-06-17 | 2013-12-05 | 2013-12-05 |  | 73%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695017 | HARDSTAND EXTENSION |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 12623 | 7904 | 2011-06-17 | 2013-12-05 | 2013-12-05 |  | 94%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695022 | CONSOLIDATED WAREHOUSE FACILITY |  | 2010-11-22 | 2011-06-03 | SAUER, INC. | N6945009D1277 0003 | 13295 | 11139 | 2011-06-17 | 2013-12-20 | 2012-07-27 | 2013-12-20 | 100%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695023 | WASHRACK EXPANSION |  | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | N6945011D1259 0002 | 8877 | 8449 | 2011-06-15 | 2013-06-10 | 2012-11-19 |  | 96%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695024 | CONTAINER STORAGE LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3702 | 3370 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 100%
2015-02-28 | 2012 | Marine Corps Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  |  | 2012-01-04 |  |  | 0 | 45 | 2012-01-18 |  | 2012-01-31 |  | 100%
2015-02-28 | 2014 | Navy Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611407 | SITE IMPROVEMENTS - GENERAL OFFICERS QUARTERS A |  |  | 2014-09-30 | QUALITY SUPPORT SERVICES, INC. | N4008314D1014 0003 | 75 | 64 | 2014-10-14 |  | 2014-11-30 | 2015-02-17 | 0%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865152 | PARKING APRON/TAXIWAY EXPANSION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 32816 | 35500 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 100% | 28591 | N50092499, N60191527, Design, N47608561
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865181 | HANGAR 5 RENOVATIONS & ADDITION |  | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0002 | 13634 | 12826 | 2013-09-27 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 8%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865185 | HANGAR 4 ADDITION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 27121 | 27820 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | 4000 | M00681159, Design
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865192 | GTF-HANGAR MODIFICATION (HMT-302) |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 56417 | 54605 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | 30605 | N50092499, Design
2015-02-28 | 2012 | Marine Corps Reserve | Major Military Construction | TENNESSEE | UNITED STATES | M68479030 | RESERVE CENTER TRAINING CENTER - MEMPHIS |  | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | N4008313C0019 AWD | 9006 | 8536 | 2013-04-19 | 2015-03-20 | 2015-02-17 | 2015-02-13 | 96%
2015-02-28 | 2011 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | M68479060 | MARINE CORPS RESERVE CENTER |  | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0005 | 14630 | 14196 | 2011-10-11 | 2014-04-15 | 2013-02-08 | 2013-12-31 | 100%
2015-02-28 | 2013 | Marine Corps Reserve | Major Military Construction | NEW YORK | UNITED STATES | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY |  | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911 | 4776 | 2013-09-19 | 2015-11-04 | 2014-12-04 | 2015-11-04 | 15%
2015-02-28 | 2012 | Navy Active | Major Military Construction | ILLINOIS | UNITED STATES | N00128816 | DECENTRALIZE STEAM SYSTEM |  | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491 | 63065 | 2012-06-27 | 2015-11-06 | 2015-11-06 | 2015-11-06 | 64%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N00204791 | HVAC JOINT AVIATION SURVIVAL TRAINING |  | 2012-07-25 | 2012-09-29 | R L BURNS INC. | N6945012C6343 AWD | 2038 | 1975 | 2012-10-13 | 2013-12-19 | 2013-08-08 | 2013-08-08 | 100%
2015-02-28 | 2011 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | N00206477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY |  | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | N6945011C0756 AWD | 13604 | 14494 | 2011-06-17 | 2014-05-07 | 2013-06-07 | 2014-05-07 | 95%
2015-02-28 | 2012 | Marine Corps Reserve | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | N00206501 | MILITARY WORKING DOG FACILITY |  | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | N6945013C5571 AWD | 1286 | 1237 | 2013-08-29 | 2014-06-20 | 2014-05-22 | 2014-06-20 | 100%
2015-02-28 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207153 | BAMS UAS OPERATOR TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 2851 | 2936 | 2012-07-09 | 2014-03-24 | 2013-12-17 |  | 96% | 1321 | N42237100
2015-02-28 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207624 | P-8A TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 14194 | 13887 | 2012-07-09 | 2014-03-24 | 2013-12-17 |  | 96% | 11437 | N42237636, N42237100
2015-02-28 | 2015 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207631 | P-8A RUNWAY THRESHOLDS AND TAXIWAYS |  | 2014-04-01 | 2015-02-27 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 | 11078 | 10042 | 2015-03-13 | 2016-06-26 | 2016-04-19 | 2016-06-26 | 0%
2015-02-28 | 2013 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207655 | BAMS MISSION CONTROL COMPLEX |  | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | N6945013C1257 AWD | 18180 | 18636 | 2013-08-28 | 2015-05-17 | 2014-12-27 | 2015-05-17 | 65%
2015-02-28 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION |  | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573 | 5992 | 2014-10-10 | 2016-06-26 | 2016-04-19 | 2016-06-26 | 0%
2015-02-28 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151 | 13436 | 2014-08-29 | 2016-01-07 | 2016-01-07 | 2016-01-07 | 0%
2015-02-28 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245327 | BERTHING PIER 12 REPL & DREDGING |  | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | N6247311C2850 AWD | 99132 | 110817 | 2011-10-13 | 2013-10-22 | 2013-10-22 |  | 72% | 1813 | N61151162
2015-02-28 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245405 | BACHELOR QUARTERS HOMEPORT ASHORE |  | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247311C2804 AWD | 72294 | 69919 | 2011-10-14 | 2013-12-03 | 2013-10-23 | 2013-12-03 | 100% | 3179 | N42237100
2015-02-28 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245500 | LCS TRAINING FACILITY |  | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553 | 40554 | 2013-10-14 | 2015-10-24 | 2015-10-24 | 2016-01-09 | 43% | 10760 | N42237100
2015-02-28 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246705 | FITNESS CENTER, NORTH ISLAND |  | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | N6247310D5409 0013 | 46630 | 43271 | 2012-08-21 | 2015-07-27 | 2015-03-16 | 2015-07-27 | 85%
2015-02-28 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246750 | ROTARY HANGAR |  | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | N6247312C1406 P00001 | 64063 | 63861 | 2012-02-14 | 2013-12-10 | 2012-04-16 | 2014-03-11 | 100% | 1557 | N42237100
2015-02-28 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND |  | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977 | 55971 | 2012-07-17 | 2015-07-09 | 2015-03-30 | 2015-07-09 | 87%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY |  | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | N6247311D0067 0004 | 1816 | 1716 | 2013-02-21 | 2015-01-28 | 2014-01-31 |  | 98%
2015-02-28 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246909 | H-60S SIMULATOR TRAINING FACILITY |  | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088 | 2941 | 2014-03-14 | 2015-05-15 | 2015-03-15 | 2015-03-15 | 24%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246943 | POWER DISTRIBUTION TO OP-3 TO SUPPORT ELMR |  | 2014-05-06 | 2014-09-16 | NAVY STANDARD DOCUMENT | N6247014POR0018 | 1652 | 1425 | 2014-09-30 |  |  |  | 4%
2015-02-28 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND |  | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904 | 8436 | 2014-08-18 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 7%
2015-02-28 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620239 | EA-18G FACILITY IMPROVEMENTS |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5004 AWD | 29692 | 25322 | 2014-09-08 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 0%
2015-02-28 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620245 | EA-18G FLIGHT SIMULATOR FACILITY |  | 2012-08-16 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0009 | 5679 | 5916 | 2013-06-27 | 2015-01-26 | 2014-11-25 |  | 96%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction | OREGON | UNITED STATES | N00620246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY |  | 2013-07-26 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | N4425513C7005 AWD | 1120 | 1073 | 2013-10-14 | 2015-01-21 | 2014-09-30 |  | 98%
2015-02-28 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620251 | P-8A HANGAR AND TRAINING FACILITIES |  | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5002 AWD | 84889 | 79251 | 2014-08-04 | 2016-01-12 | 2016-01-12 | 2016-01-26 | 7%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N00620257 | HANGAR 11 MODIFICATIONS FOR SEARCH AND RESCUE |  | 2014-06-20 | 2014-09-02 | RORE, INC. | N4425514C8012 | 1424 | 1378 | 2014-09-16 |  |  |  | 71%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | N32411056 | VPT TEST FACILITY |  | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | N4008510D9450 0006 | 2332 | 2331 | 2013-03-28 | 2013-11-21 | 2013-10-31 |  | 99%
2015-02-28 | 2011 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411068 | ELECTROMAGNETIC SENSOR FACILITY |  | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | N4008511C7231 AWD | 24394 | 26541 | 2011-08-23 | 2014-03-24 | 2013-08-22 |  | 98%
2015-02-28 | 2014 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411103 | HEWITT HALL RESEARCH CENTER |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319 | 12795 | 2014-08-14 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 9%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | N32414203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES |  | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | N4008512C5002 AWD | 1951 | 1838 | 2012-03-16 | 2012-08-28 | 2012-09-13 | 2012-09-13 | 100%
2015-02-28 | 2012 | Navy Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414860 | ARMED FORCES RESERVE CENTER, PITTSBURGH |  | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | N4008312C0005 AWD | 12033 | 12347 | 2012-08-14 | 2014-05-31 | 2014-02-06 | 2014-05-31 | 99%
2015-02-28 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443383 | CONTROLLED INDUSTRIAL FACILITY |  | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576 | 32450 | 2012-06-14 | 2015-11-27 | 2014-09-28 | 2015-03-23 | 38% | 7621 | N684691400
2015-02-28 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443516A | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | N32443516 | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | N4008510C3006 P00003 | 68459 | 68145 | 2011-04-14 | 2015-12-31 | 2014-11-22 | 2015-10-02 | 73%
2015-02-28 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE |  | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374 | 26312 | 2013-12-11 | 2016-02-12 | 2015-12-27 | 2015-12-27 | 38%
2015-02-28 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A219 | GENERAL WAREHOUSE |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 7716 | 7761 | 2012-04-16 | 2015-05-15 | 2013-12-26 |  | 83%
2015-02-28 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A227 | ARMORY |  | 2014-02-26 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492 | 4216 | 2014-08-08 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 10%
2015-02-28 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A912 | PAVE EXTERNAL ROADS |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 3107 | 2615 | 2012-04-16 | 2015-05-15 | 2013-12-26 |  | 87%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A917 | CRITICAL POWER FOR BULDING 200 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1120 | 1120 | 2014-06-05 |  |  |  | 100%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A918 | CRITICAL POWER FOR BUILDING T-130 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1175 | 1175 | 2014-06-05 |  |  |  | 100%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A919 | CRITICAL POWER FOR BLDGS 111, 113 AND 115 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1064 | 1064 | 2014-06-05 |  |  |  | 100%
2015-02-28 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A921 | UNACCOMPANIED HOUSING |  | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714 | 19555 | 2014-10-15 | 2016-05-30 | 2016-05-30 | 2016-06-28 | 7%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557101A | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 | N41557101 | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | N6274210D1309 JQ01 | 24305 | 19365 | 2013-08-21 | 2015-12-15 | 2015-07-12 | 2015-12-15 | 40%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820 | 57200 | 2014-05-21 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 6%
2015-02-28 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710 | 49621 | 2014-04-10 | 2016-04-25 | 2016-04-25 | 2016-09-23 | 8%
2015-02-28 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557J200 | NORTH RAMP UTILITIES II |  | 2014-04-11 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 AWD | 53014 | 47762 | 2014-10-31 | 2016-11-04 | 2016-09-02 | 2016-09-02 | 94%
2015-02-28 | 2014 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249 | 119886 | 2014-09-03 | 2018-06-20 | 2018-06-20 | 2018-04-08 | 3%
2015-02-28 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237601 | SECURITY ENCLAVE AND VEHICLE BARRIER |  | 2011-12-13 | 2012-03-16 | SAUER, INC. | N6945009D1277 0007 | 37278 | 39686 | 2012-03-30 | 2013-09-07 | 2013-09-07 |  | 93% | 5445 | Sequestration Reprogramming
2015-02-28 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237620 | WATERFRONT EMERGENCY GENERATORS |  | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | N6945010D1271 0003 | 15010 | 16827 | 2011-09-02 | 2013-05-13 | 2013-05-13 |  | 97%
2015-02-28 | 2012 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE |  | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167 | 36608 | 2014-05-01 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 15%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  | 2014-08-11 | 2014-09-30 | REILLY CONSTRUCTION, INC | N4008014D3014 AWD | 1453 | 1358 | 2014-10-14 | 2015-04-14 | 2015-05-26 |  | 1%
2015-02-28 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC |  | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | N4008011C0154 AWD | 33033 | 34718 | 2011-06-16 | 2013-07-31 | 2012-07-30 |  | 99%
2015-02-28 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 |  | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49890 | 47216 | 2014-07-14 | 2016-06-20 | 2016-04-01 | 2016-04-01 | 14%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N47609003 | EOD/TEU RANGE SUPPORT FACILITY |  | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | N6247313D4608 0007 | 1896 | 1764 | 2014-06-27 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 13%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092199 | MSRON FOUR BOAT STORAGE BUILDING |  | 2012-10-31 | 2012-12-14 | JESSICO, INC | N4008511D3021 0008 | 970 | 938 | 2012-12-28 | 2013-11-15 | 2013-11-08 | 2013-11-15 | 100%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY |  | 2011-05-26 | 2011-08-03 | JESSICO, INC | N4008511C3026 AWD | 2085 | 1989 | 2011-08-17 | 2012-11-13 | 2012-09-30 |  | 98%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG |  | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008512C7000 AWD | 1725 | 1616 | 2011-11-18 | 2013-05-08 | 2012-07-21 | 2013-05-31 | 100%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 |  | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008513C7711 AWD | 1925 | 1925 | 2013-03-14 | 2013-09-12 | 2013-08-30 |  | 86%
2015-02-28 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N50092499 | POWER DISTRIBUTION UPGRADES |  | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | N4008512C1704 AWD | 29520 | 28110 | 2012-10-08 | 2015-04-03 | 2014-10-09 |  | 94%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092662 | EOD ESU TWO EXPEDITIONARY LOGISTICS OVERHAUL WAREHOUSE |  | 2014-05-09 | 2014-08-06 | DOYON MANAGEMENT SERVICES, LLC | N4008514D2102 0001 | 1020 | 239 | 2014-08-20 | 2015-01-21 | 2014-11-21 |  | 24%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N57095101 | ROAD IMPROVEMENTS CAMP ALLEN AREA |  | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | N4008509D5027 0003-PC000002 | 1381 | 1326 | 2011-02-28 | 2012-01-27 | 2011-09-21 | 2012-01-27 | 100%
2015-02-28 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N57095197 | DECENTRALIZE STEAM SYSTEM |  | 2012-04-17 | 2012-09-20 | SAUER, INC. | N4008509D5026 0004 | 27161 | 26946 | 2012-10-04 | 2015-03-09 | 2015-05-08 | 2015-05-08 | 84%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | N60042116 | D5 MISSILE MOTOR MAGS MODS (NAVOBSSTA FLAGSTAFF AZ) |  |  | 2014-12-11 | NAVY STANDARD DOCUMENT | N6247315MPRM001 | 1725 | 1560 | 2014-12-25 |  |  |  | 0%
2015-02-28 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N60042260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  |  | 2011-09-29 | NAVY STANDARD DOCUMENT | N6247311RP00189 | 1421 | 1658 | 2011-10-13 |  |  |  | 100%
2015-02-28 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191513 | A SCHOOL BARRACKS |  | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430 | 29166 | 2013-11-14 | 2015-12-30 | 2015-12-16 | 2015-12-30 | 25% | 5604 | N42237100
2015-02-28 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS |  | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599 | 19040 | 2012-10-11 | 2015-04-30 | 2014-10-12 | 2015-05-07 | 63%
2015-02-28 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191582 | UNDERSEA SURVEILLANCE SCIF FACILITY |  | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0003 | 4129 | 4852 | 2012-12-03 | 2014-06-25 | 2013-11-29 |  | 99%
2015-02-28 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446 | 10707 | 2014-09-30 | 2016-10-25 | 2016-10-25 | 2016-10-25 | 1%
2015-02-28 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201425 | LCS LOGISTICS SUPPORT FACILITY |  | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | N6945013D1765 0002 | 15842 | 15000 | 2014-06-13 | 2015-11-26 | 2015-11-26 | 2015-12-01 | 31%
2015-02-28 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS |  | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | N6945012C0757 AWD | 7518 | 10061 | 2012-08-29 | 2014-02-21 | 2014-02-21 |  | 31%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241288 | WASTEWATER SYSTEM |  | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | N6945014C0763 AWD | 1790 | 1653 | 2014-04-11 | 2015-03-27 | 2015-03-27 | 2015-03-27 | 58%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241294 | CONNECT TO KINGSVILLE WATER SYSTEM |  | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | N6945010D0776 0002 | 1658 | 1549 | 2012-10-08 | 2014-08-25 | 2014-03-21 |  | 97%
2015-02-28 | 2011 | Navy Active | Major Military Construction | ALABAMA | UNITED STATES | N60508266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD |  | 2012-07-05 | 2012-09-28 | HEAD, INC. | N6945012C0760 AWD | 29901 | 28287 | 2012-10-12 | 2014-09-28 | 2014-09-28 | 2015-05-19 | 80%
2015-02-28 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE |  | 2012-02-17 | 2012-06-07 | NAVY STANDARD DOCUMENT | N6247012MPS0048 | 18810 | 20581 | 2012-06-21 | 2015-04-14 | 2014-12-30 | 2015-04-14 | 81%
2015-02-28 | 2011 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N61007015 | CALIBRATION FACILITY LAND ACQUISITION |  |  | 2011-12-31 | NAVY STANDARD DOCUMENT | N6945011RP00148 | 3149 | 3080 | 2012-01-14 |  |  |  | 100%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61014851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION |  | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | N6247314C2801 AWD | 1916 | 1895 | 2014-01-02 | 2014-12-31 | 2014-10-17 |  | 73%
2015-02-28 | 2014 | Navy Active | Major Military Construction |  | JAPAN | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458 | 9458 | 2014-10-03 | 2017-01-17 | 2016-08-16 | 2017-01-17 | 0%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054012 | CONSTRUCT NACCC ADDITION |  | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | N4008410D0014 0003 | 1380 | 1256 | 2011-06-24 | 2012-04-20 | 2012-04-13 |  | 96%
2015-02-28 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER |  | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | N4008411C0129 AWD | 17378 | 16915 | 2011-07-15 | 2013-01-17 | 2012-12-03 | 2013-01-17 | 100%
2015-02-28 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) |  | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | N4008412C0108 AWD | 19730 | 18773 | 2012-08-01 | 2014-01-13 | 2014-01-13 |  | 100%
2015-02-28 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 |  | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | N4008412C0109 AWD | 9033 | 9298 | 2012-08-22 | 2015-01-11 | 2014-10-07 | 2014-12-12 | 89%
2015-02-28 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 |  | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791 | 7305 | 2014-07-29 | 2016-02-21 | 2016-02-21 | 2016-02-21 | 28%
2015-02-28 | 2013 | Navy Active | Major Military Construction |  | JAPAN | N61056353 | BACHELOR QUARTERS |  | 2013-01-24 | 2013-09-27 | NAVY STANDARD DOCUMENT | N6274213MP00015 | 5627 | 5521 | 2013-10-11 | 2015-01-12 | 2015-01-05 |  | 93%
2015-02-28 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR |  | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | N4008412C8325 AWD | 5990 | 5654 | 2012-10-10 | 2013-11-22 | 2013-08-26 | 2013-11-22 | 100%
2015-02-28 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) |  | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | N4008412C0004 AWD | 17540 | 14942 | 2012-08-29 | 2014-07-01 | 2013-12-09 | 2014-07-01 | 95%
2015-02-28 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES |  | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | N4008414C8401 AWD | 12958 | 12065 | 2013-12-15 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 64%
2015-02-28 | 2011 | Navy Active | Major Military Construction |  | JAPAN | N61057203 | AVIATION SIMULATOR TRAINING FACILITY |  | 2010-12-09 | 2011-07-29 | NAVY STANDARD DOCUMENT | N6274211MP00014 | 6764 | 6442 | 2011-08-12 | 2013-11-13 | 2013-11-13 |  | 97%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61057221 | HELO ALFS TEST ROOM, BUILDING 194 |  | 2014-06-12 | 2014-08-06 | NIHON MECCS CO., LTD. | N4008414C8302 AWD | 890 | 812 | 2014-08-20 | 2015-02-03 | 2015-02-03 |  | 86%
2015-02-28 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) |  | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799 | 21589 | 2014-10-14 |  |  | 2016-01-01 | 5%
2015-02-28 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N61064400 | NORTH LOOP ELECTRICAL REPLACEMENT |  | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | N6247811D4046 0005 | 6498 | 5905 | 2012-03-29 | 2013-12-24 | 2014-01-02 |  | 88% | 2776 | N42237100
2015-02-28 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB |  | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447 | 27917 | 2013-10-14 | 2016-04-17 | 2016-04-17 | 2016-06-16 | 47%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction |  | SINGAPORE | N61077123 | TEMPORARY LCS SUSTAINMENT FACILITY |  | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | N4008413C9001 AWD | 755 | 768 | 2012-12-20 | 2014-01-15 | 2013-03-10 |  | 93%
2015-02-28 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151162 | AGILE CHEMICAL FACILITY PHASE 2 |  | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | N4008012C2001 AWD | 34869 | 37836 | 2012-08-24 | 2015-06-26 | 2014-06-16 | 2015-06-26 | 73%
2015-02-28 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151222 | DECENTRALIZE STEAM SYSTEM |  | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984 | 68760 | 2012-10-12 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 89%
2015-02-28 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY |  | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0007 | 14130 | 13701 | 2013-09-02 | 2015-03-12 | 2015-03-12 | 2015-05-01 | 67%
2015-02-28 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151372 | PHYSICAL FITNESS CENTER |  | 2012-12-12 | 2013-09-27 | C.E.R. INC. | N4008010D0302 0021 | 11409 | 10810 | 2013-10-11 | 2015-05-02 | 2015-05-02 | 2015-05-02 | 61%
2015-02-28 | 2013 | Navy Active | Military Family Housing Improvement | GUAM | GUAM | N617551301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE |  | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 JQ02 | 26805 | 25385 | 2013-09-26 | 2015-09-09 | 2015-09-09 | 2015-12-23 | 66%
2015-02-28 | 2011 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N61755204A | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | N61755204 | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | N4019210D2803 0006 | 21579 | 16528 | 2012-12-12 | 2014-09-29 | 2014-06-19 |  | 99%
2015-02-28 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755425 | MODULAR STORAGE MAGAZINE |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865 | 45201 | 2014-05-26 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 5%
2015-02-28 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755518 | X-RAY WHARF IMPROVEMENTS |  | 2014-01-10 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085 | 42603 | 2014-06-17 | 2016-09-20 | 2016-10-20 | 2016-10-20 | 9%
2015-02-28 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755566 | EMERGENT REPAIR FACILITY EXPANSION |  | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860 | 27694 | 2014-04-24 | 2016-05-12 | 2016-05-12 | 2016-05-12 | 15%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction | GUAM | GUAM | N61755630 | HARDEN ELECTRICAL DISTRIBUTION LINE (POLARIS PT ROAD) |  | 2014-07-01 | 2014-09-30 | P&S CONSTRUCTION, INC. | N4019210D2804 0019 | 2000 | 1917 | 2014-10-14 | 2015-05-19 |  |  | 10%
2015-02-28 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY |  | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170 | 14382 | 2014-04-03 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 41%
2015-02-28 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755638 | SIERRA WHARF IMPROVEMENTS |  | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | N4019210D2808 0009 | 1462 | 1211 | 2014-06-13 | 2015-04-27 | 2015-03-26 | 2015-03-26 | 45%
2015-02-28 | 2013 | Navy Active | Major Military Construction |  | ROMANIA | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | N6247014MPE0025 | 40018 | 36389 | 2014-05-14 |  |  |  | 21%
2015-02-28 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688123 | BACHELOR QUARTERS, HOMEPORT ASHORE |  | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | N4008512C4572 AWD | 74854 | 72235 | 2012-09-14 | 2015-05-31 | 2014-09-13 | 2015-05-31 | 94% | 3084 | N684691400
2015-02-28 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365 | 1146 | 2014-07-14 | 2016-01-01 | 2016-01-01 | 2016-01-01 | 5%
2015-02-28 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE |  | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008511D6585 0001 | 1395 | 1273 | 2011-06-28 | 2012-11-07 | 2012-06-18 | 2012-11-07 | 100%
2015-02-28 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688862 | PIER 1 UPGRADES TO BERTH USNS COMFORT |  | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | N4008511C0020 AWD | 3659 | 2953 | 2011-08-09 | 2012-09-18 | 2012-08-09 |  | 79% | 6185 | M00681159, N42237100
2015-02-28 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N627351102 | WHOLEHOUSE IMPROVEMENT |  | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | N4008411C0006 AWD | 8127 | 6990 | 2011-07-10 | 2013-01-18 | 2012-10-17 | 2013-01-18 | 100%
2015-02-28 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813005 | JOINT POW/MIA ACCOUNTING, USPACOM |  | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274211C1300 AWD | 95540 | 83765 | 2011-06-20 | 2015-03-31 | 2013-07-05 |  | 88%
2015-02-28 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY |  | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | N6247810D4022 0019 | 7708 | 7642 | 2012-04-19 | 2014-11-09 | 2013-11-16 |  | 98%
2015-02-28 | 2015 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813048 | SUBMARINE MANEUVERING ROOM TRAINER FACILITY |  | 2014-10-20 | 2015-02-27 | JSR ECC, LLC | N6247814D4003 | 8667 | 8054 | 2015-03-13 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 0%
2015-02-28 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE |  | 2011-02-04 | 2011-06-24 | FOPCO, INC | N6247810D4019 0006 | 7856 | 9024 | 2011-07-08 | 2013-06-03 | 2012-08-15 |  | 99%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813058 | ROCKFALL PROTECTION AT RED HILL |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810 | 2615 | 2014-12-08 | 2016-05-18 | 2016-05-18 |  | 0%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) |  | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | N6247810D4020 0014 | 1559 | 1446 | 2011-10-03 | 2013-03-01 | 2012-12-24 | 2013-03-01 | 100%
2015-02-28 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813270 | DRYDOCK WATERFRONT FACILITY |  | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355 | 20239 | 2014-03-03 | 2016-05-11 | 2015-12-11 | 2015-12-11 | 10%
2015-02-28 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970 | 29590 | 2014-07-14 | 2017-08-03 | 2017-08-03 | 2017-08-23 | 9%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863708 | CONSTRUCT LCAC BEACH ACCESS RAMP |  | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | N3319110D0219 0009 | 1751 | 1411 | 2013-10-13 | 2014-06-20 | 2014-05-28 |  | 97%
2015-02-28 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863709 | GENERAL PURPOSE WAREHOUSE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 2446 | 1916 | 2013-09-06 | 2015-06-11 | 2015-03-20 | 2015-03-20 | 54%
2015-02-28 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863710 | HIGH EXPLOSIVE MAGAZINE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 5849 | 5358 | 2013-09-06 | 2015-06-11 | 2015-03-20 | 2015-03-20 | 43%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863733 | PROVIDE ELECTROMAGNETIC CALIBRATION COMPLEX |  | 2014-08-29 | 2014-09-19 | NEWIMAR SA | N3319110D1801 0283 | 1144 | 712 | 2014-10-03 | 2015-08-21 |  |  | 7%
2015-02-28 | 2011 | Navy Active | Major Military Construction |  | SPAIN | N62863897 | AIR TRAFFIC CONTROL TOWER |  | 2012-01-13 | 2012-06-15 | SACYR SA | N3319112C0603 AWD | 19080 | 16195 | 2012-06-29 | 2015-04-15 | 2014-09-03 | 2015-04-04 | 73% | 2052 | N42237100
2015-02-28 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY |  | 2012-04-12 | 2012-08-17 | NAVY STANDARD DOCUMENT | N6247012MPE0064 | 41151 | 38946 | 2012-08-31 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 51% | 15471 | Sequestration Reprogramming
2015-02-28 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005954 | WATERFRONT DEVELOPMENT, PHASE 3 |  | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT | N6247012MPE0005 | 40713 | 40237 | 2012-03-14 | 2015-09-22 | 2014-11-26 | 2015-09-22 | 84% | 19865 | Sequestration Reprogramming
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042331 | WATER WELL |  | 2011-01-11 | 2011-09-30 | EPC CORPORATION | N6247310D5415 0012 | 2713 | 2887 | 2011-10-14 | 2013-11-22 | 2012-10-01 | 2013-05-21 | 100%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 |  | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | N6247312C3410 AWD | 1980 | 1878 | 2012-09-12 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 100%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT |  | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | N6247312C3413 AWD | 2000 | 1896 | 2012-10-12 | 2014-03-05 | 2013-09-26 | 2014-03-05 | 100%
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042376 | VFA-94 HANGAR ALTERATIONS |  | 2014-08-27 | 2014-09-27 | COPPERTOP LEDCOR JV | N6247313D4608 0014 | 1839 | 1653 | 2014-10-11 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 0%
2015-02-28 | 2013 | Navy Active | Major Military Construction | MISSISSIPPI | UNITED STATES | N63043317 | DINING FACILITY |  | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851 | 9286 | 2013-12-31 | 2015-10-09 | 2015-10-09 | 2015-10-09 | 28%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63406563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 |  | 2012-06-20 | 2012-09-28 | NOVA R M F | N6247312D0245 0003 | 1939 | 1875 | 2012-10-12 | 2014-06-23 | 2013-09-27 | 2014-07-01 | 100%
2015-02-28 | 2013 | Navy Active | Major Military Construction |  | GREECE | N66691907 | AIRCRAFT PARKING APRON EXPANSION |  | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPAQOLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663 | 13288 | 2014-07-25 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 8%
2015-02-28 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 |  | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | N4425510D5019 0002 | 13341 | 10693 | 2012-06-08 | 2013-06-27 | 2013-12-24 |  | 88%
2015-02-28 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179 | 10309 | 2014-08-01 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 1%
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436839 | RENOVATE LOWER BASE FIRE STATION |  | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | N4425509D4007 0017 | 1389 | 1329 | 2012-09-14 | 2013-08-31 | 2013-08-31 | 2013-11-22 | 100%
2015-02-28 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436843 | CSDS-5 LABORATORY EXPANSION PHASE ! |  | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | N4425510D5006 0005 | 16042 | 16525 | 2011-06-17 | 2013-09-24 | 2012-10-15 |  | 94%
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436857 | FLOATING LABORATORY, MOORING DOLPHINS |  | 2013-01-16 | 2013-05-17 | NOVA GROUP INC | N4425510D5019 0003 | 3406 | 3117 | 2013-05-31 |  |  |  | 100%
2015-02-28 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 14315 | 14812 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-08-28 | 100%
2015-02-28 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436913 | EHW SECURITY FORCE FACILITY |  | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | N4425512C3007 AWD | 13485 | 13642 | 2012-02-14 | 2014-06-11 | 2013-08-08 |  | 76% | 7933 | N684691400
2015-02-28 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436973F | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | N63402973 | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | N4425508C6003 PC000094 | 20026 | 19443 | 2010-11-24 | 2012-06-01 | 2011-11-08 |  | 93%
2015-02-28 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436985 | WRA VEHICLE BARRIERS |  | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | N4425510D5008 0012 | 9338 | 8948 | 2012-02-24 | 2013-12-11 | 2013-12-10 |  | 86% | 7587 | N42237636
2015-02-28 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436987 | EMERGENCY GENERATOR, LIMITED AREA |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 11275 | 10418 | 2011-06-17 | 2013-07-10 | 2013-06-26 |  | 97%
2015-02-28 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 |  | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714 | 78002 | 2012-05-23 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 93%
2015-02-28 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990A | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 2 OF 4 | N68436990 | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 280041 | 254445 | 2012-11-15 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 68%
2015-02-28 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990B | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990 | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 24880 | 13774 | 2014-01-14 |  |  |  | 0%
2015-02-28 | 2015 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990C | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 4 OF 4 | N68436990 | 2011-12-13 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 80735 | 70251 | 2015-01-22 |  |  |  | 0%
2015-02-28 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N68469110 | REPLACE CONDEMNED COATINGS LABORATORY |  | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0019 | 3805 | 3998 | 2012-09-11 | 2014-04-24 | 2013-08-28 |  | 99%
2015-02-28 | 2014 | Navy Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | N684691400 | NAVSEA HQ RESTORATION |  | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | N6247013D6019 JU01 | 48905 | 48797 | 2014-02-14 | 2015-01-31 |  |  | 99%
2015-02-28 | 2012 | Navy Active | Major Military Construction |  | DIEGO GARCIA | N68539184 | POTABLE WATER PLANT MODERNIZATION |  | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101 | 28307 | 2013-01-04 | 2015-08-26 | 2015-07-30 | 2015-08-26 | 70%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING |  | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | N4008506D6009 0008 | 928 | 950 | 2011-07-04 | 2012-04-16 | 2012-01-26 | 2012-04-30 | 100%
2015-02-28 | 2012 | Navy Reserve | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212543 | NAVELSG RESERVE FORCES MARSHALLING YARDS |  | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | N4008511D6588 0006 | 738 | 747 | 2013-01-30 | 2013-10-23 | 2014-01-21 |  | 95%
2015-02-28 | 2011 | Navy Reserve | Major Military Construction | VIRGINIA | UNITED STATES | N69212743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX |  | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008509D5019 0003 | 15431 | 17554 | 2011-06-17 | 2013-10-18 | 2013-04-27 | 2013-10-18 | 99%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212984 | REGIMENTAL HEADQUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028 | 10767 | 2013-09-13 | 2015-08-15 | 2015-06-26 | 2015-08-14 | 40%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212985 | BACHELOR ENLISTED QUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418 | 17631 | 2013-09-13 | 2015-08-15 | 2015-06-26 | 2015-08-14 | 31%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212986 | MOTOR TRANSPORTATION FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 5841 | 5674 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 65%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212987 | SUPPLY WAREHOUSE FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 6987 | 6674 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 72%
2015-02-28 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212989 | ARMORY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 3653 | 3507 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 78%
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | N69213206 | CONSTRUCT DISPATCH CENTER |  | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | N4008510D9451 0005 | 1630 | 1633 | 2011-12-01 | 2013-03-26 | 2013-01-25 | 2013-03-29 | 100%
2015-02-28 | 2013 | Navy Active | Major Military Construction | NEW JERSEY | UNITED STATES | N69213237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION |  | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | N4008513C3513 AWD | 34005 | 34271 | 2013-09-17 | 2014-11-27 | 2014-11-27 |  | 99%
2015-02-28 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232281 | AIRCRAFT ENGINE TEST PADS |  | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | N6247309D1657 0016 | 6106 | 5719 | 2014-06-26 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 11%
2015-02-28 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232559 | E-2D AIRCREW TRAINING FACILITY |  | 2012-03-21 | 2012-06-29 | A&D GC INC | N6247309D1658 0012 | 13210 | 15796 | 2012-07-13 | 2014-06-25 | 2013-10-07 | 2015-03-20 | 95%
2015-02-28 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232593 | BAMS CONSOLIDATED MAINTENANCE HANGAR |  | 2014-04-30 | 2015-01-16 | I E PACIFIC INC | N6247309D1657 0019 | 18400 | 17305 | 2015-01-30 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 1%
2015-02-28 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232599 | UNACCOMPANIED HOUSING CONVERSION (PORT HUENEME) |  |  | 2014-11-24 | NAVY STANDARD DOCUMENT | N6247314RP00165 | 33594 | 30033 | 2014-12-08 |  |  |  | 85%
2015-02-28 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232900 | BAMS MAINTENANCE TRAINING FACILITY |  | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301 | 8749 | 2013-09-10 | 2014-11-21 | 2014-11-21 | 2015-05-01 | 16%
2015-02-28 | 2013 | Navy Reserve | Major Military Construction | TEXAS | UNITED STATES | N83447047 | COMMERCIAL VEHICLE INSPECTION SITE |  | 2013-01-22 | 2013-09-12 | KOMADA, LLC | N6945013D1767 0001 | 6894 | 6607 | 2013-09-26 | 2015-05-01 | 2014-11-06 | 2014-11-06 | 45%
2015-02-28 | 2014 | Navy Active | Major Military Construction | OKLAHOMA | UNITED STATES | N83447136 | TACAMO E-6B HANGAR |  | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19401 | 18519 | 2014-10-14 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 0%
2015-02-28 | 2013 | Defense Finance and Accounting Service | Major Military Construction | TEXAS | UNITED STATES | 80230 | DFAS Administration Building | 80230 | 2013-04-24 | 2013-07-30 | US Army COE Guyco, INC | Contract No. W9127S-09-D-6006 | 12903 | 12903 | 2013-09-11 | 2015-12-01 | 2015-03-05 | 2015-09-01 | 33% |  |  | Site work continues to be behind schedule with wet and muddy conditions. The site conditions are affecting every sub-contractor on site. This will push the scheduled completion to 1 September with a 100 days of negative float.
2015-02-28 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 75132 | Joint Navy-VA Project |  |  | 2013-09-27 | Billy W. Jarrett Const Co Inc | N62470 13 MPS 0046 | 1797 | 1899 |  |  | 2014-10-15 | 2014-10-15 |  |  |  | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2015-02-28 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81004 | Site Development, NiCOE |  | 2012-05-16 | 2012-06-05 | Sunland Builders, Inc | N40085 09 D 9027 DO 0026 | 1363 | 1452 | 2012-08-01 | 2013-08-12 | 2013-08-29 | 2013-08-29 | 100% |  |  | Project is not financially closed.
2015-02-28 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | GUANTANAMO BAY NAVAL BASE | GUANTANAMO BAY NAVAL BASE | 82095 | Veterinary Treatment Facility Alterations
2015-02-28 | 2009 | Defense Health Agency | Unspecified Minor Military Construction |  | GERMANY | 68974 | Computer Operations Center |  | 2011-02-01 | 2011-04-22 | Federal Republic of Germany |  | 1950 | 1950 | 2011-05-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100%
2015-02-28 | [8 empty] | 2011-01-08 | 2011-03-14 | Wayss & Freytag |  | 1572 | 1548 | 2013-04-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100%
2015-02-28 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 77342 | Bldg 509 Alteration of Medical Laboratory |  | 2010-12-17 | 2011-01-28 | Odyssey International, Inc |  | 3294 | 3690 | 2011-02-16 | 2011-09-15 | 2011-09-15 | 2011-08-15 | 100% |  |  | Preparation for fiscal closeout.
2015-02-28 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 80093 | Medical Ed. & Training Facility |  | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc | W9126G-09-D-0105 | 1698 | 1982 | 2012-08-14 | 2014-09-10 | 2013-11-14 | 2014-08-24 | 100% |  |  | Switch gear was changed on 18 FEB 2015. Project complete. No punch list itmes.
2015-02-28 | 2011 | Defense Health Agency | Unspecified Minor Military Construction |  | JAPAN | 78853 | New Clinic Addition | [14 empty] | DHA issued DA memo dated 22 Dec 2014 cancelled the FY11 project. Corps has estimated $3k to close out the project's design contract; previously provided funds are available for this effort.
2015-02-28 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80792 | Site Development, NiCOE |  | 2012-06-18 | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service | W81W3G22363343 / 22443665 / 22443666 / 30793685 | 1600 | 1690 | 2012-09-10 | 2013-06-30 | 2013-05-31 | 2013-08-29 | 100% |  |  | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Project financial closeout is ongoing.
2015-02-28 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80094 | Veterinary Clinic |  | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc | W912BV-12-C-0030 | 1692 | 1710 | 2013-01-04 | 2014-12-12 | 2014-07-05 | 2015-04-12 | 98% |  |  | BOD Issued 12 Dec 14. Several items on punch-list remained incomplete after 31 Dec 14. Will revisit asphalt concerns with BCE and KTR in Spring 15 for possible snow plow damage. KTR is working on the close out documents. Current obligation w/all mods $2,046,905.00 which breaks down into $1,691,830.00 MILCON and $355,075.00 I/O funds. We just settled an REA in the amount of $18,577 so that will be added to the obligations.
2015-02-28 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 82358 | Veterinary Clinic Replacement |  | 2015-05-26 | 2015-08-30 | [11 empty] | Cost reduction measures incorporated new HQCWE is $1.8M. Need DHA to concur on increase to the PA as KO will not advertise above PA.
2015-02-28 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | DELAWARE | UNITED STATES | 86204 | Medical Warehouse Add/Alt | [14 empty] | DHA provided authorization to rework design and raised PA to $2M on 13 Feb 2015. Request PA be increased to $3M.
2015-02-28 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81631 | NiCOE Satellite, Infrastructure Support |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc | W912HN-11-D-0043-0044 | 1436 | 1436 | 2014-06-30 | 2015-11-25 | 2016-02-01 | 2016-02-01 | 63% |  |  | The NiCOE Contractor has started work on new clinic. The Site Support Contractor is completing installation of communication manholes and ductbank. Contingencies in district: $26,813.38
2015-02-28 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 81706 | NiCOE Satellite, Infrastructure Support |  | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 2166 | 1795 | 2014-09-15 | 2015-10-28 | 2015-10-28 | 2015-10-28 | 68% |  |  | Demolition is 100% complete; Underground electrical and communications complete; bldg contractor has tied into the comm. line to run into the bldg. Sewer line complete with the exception of the Mandrel test. Waterline complete minus concrete around valve boxes. Work that still needs to be complete: Pad mounted transformer (bldg contractor needs to lay foundation), south entry to fire lane, and recycle pad. Construction % complete delay is due to weather and inspections that will be required for the sewer line that will occur after the completion of Phase II work. The delay does not impact the current schedule.
2015-02-28 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 1 |  | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 | 757737 | 774314 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100%
2015-02-28 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005A | Medical Center Add/Alt, Inc 2 | 005V | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100% |  |  | Not financially closed. Final invoicing for equipment.
2015-02-28 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005B | Medical Center Add/Alt, Inc 3 | 005V | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100%
2015-02-28 | 2009 | Defense Health Agency | Base Realignment and Closures | MISSISSIPPI | UNITED STATES | 478V | Community Hospital |  | 2009-04-01 | 2009-11-10 | W.G. Yates & Sons Construction Co. | N69450 10 C 0763 | 38252 | 42256 | 2010-01-01 | 2012-02-25 | 2011-09-11 | 2012-10-11 | 100% |  |  | Not financially closed. Final invoicing for equipment - working with DLA.
2015-02-28 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69427 | Hopsital Replacement, Inc 1 |  | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV | W91236-07-C-0053 | 649025 | 9428 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | Project ready for closeout
2015-02-28 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69865 | Hopsital Replacement, Inc 4 | 69427 | 2007-06-12 | 2010-01-23 | Turner/Gilbane JV | W91236-07-C-0053 |  | 119266 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | All Unobligated funds $245K were returned. 1354 is being prepared.
2015-02-28 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 77071 | Hopsital Replacement, Inc 5 | 69427 | 2007-06-12 | 2010-10-20 | Turner/Gilbane JV | W91236-07-C-0053 |  | 211800 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | See above.
2015-02-28 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 1 |  | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 107589 | 135926 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | There are still actions on-going that will prevent close-out: 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Resolution period to be determined. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments have been suspended. They provided the telephones for the project. Throughout USACE invoices from EYAK Technology, Inc continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. USACE does not expect this matter to be resolved by the Department of Justice during FY 2014. The status is unchanged. The SWF invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. I do not expect this matter to be resolved by the Department of Justice during FY 2014. - Per USACE CT Office 3. TEAM Integrated Services Task Orders. Last DCAA audit is estimated to be completed 31 Dec 2015.
2015-02-28 | 2009 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64180 | San Antonio Regional MEDCEN, Inc 2 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 265100 | 279273 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | See above.
2015-02-28 | 2010 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 69840 | San Antonio Regional MEDCEN, Inc 3 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 13748 | 243943 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | See above.
2015-02-28 | 2011 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 70990 | San Antonio Regional MEDCEN, Inc 4 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 37554 | 85520 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | See above.
2015-02-28 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64188 | Health Clinic |  | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | W9126G-08-C-0024 | 33382 | 37382 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 100% |  |  | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2015-02-28 | 2010 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64241 | Dental Clinic |  | 2009-09-16 | 2010-05-04 | Forrester Construction Company | W912DR-10-C-0067 | 7541 | 8818 | 2010-05-18 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | NAB received 0516 BRAC Consolidated funding, executed the Global Settlement Modification, paid Final Invoice, and received Release of Claims from Contractor. Construction Contract and Project in Close Out Phase. Fiscal Closeout is scheduled, and tracking for 10 Apr 2015.
2015-02-28 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 64156 | USAMRICD Replacement, Inc 1 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398 | 17027 | 2010-03-15 | 2015-04-30 | 2013-06-01 | 2015-03-13 | 99% |  |  | Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 30 Apr 2015 for remainder of spaces.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 65270 | Hospital Replacement, Inc 1 |  | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133 | 165885 | 2010-11-01 | 2014-03-18 | 2014-10-15 | 2015-06-12 | 99% | 19460 |  | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77154 | Ambulatory Care Center, Inc 1 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 197804 | 137317 | 2013-03-01 | 2016-12-06 | 2016-12-06 | 2017-11-08 | 55% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 81291 | Ambulatory Care Center, Inc 2 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV |  |  | 66430 | [7 empty] | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 |  | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 6887.87 | 7070.1979 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC
2015-02-28 | [8 empty] | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 12000 | 12658 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 100% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC. $9,000 recinded as a result of Sequestration (04/29/13).
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67180 | USAMRICD Replacement, Inc 2 |  | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100%
2015-02-28 | [8 empty] | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 100%
2015-02-28 | [8 empty] | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 100375 | 103745.3283 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 100% |  |  | Main Building $142,857,143 FY10 Increment Awarded at $100,375,000 on 5 Mar 10 ($109,567,007 funded per D. Pritchett 17 Mar 10 email)
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67181 | USAMRICD Replacement, Inc 3 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 94608 | 96044.5065 | 2010-03-15 | 2015-04-30 | 2013-06-01 | 2015-03-13 | 99% |  |  | Full FY11 MILCON increment placed against contract.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67182 | USAMRICD Replacement, Inc 4 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 7915.345 | 27166.399 | 2010-03-15 | 2015-04-30 | 2013-06-01 | 2015-03-13 | 99% |  |  | Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 30 Apr 2015 for remainder of spaces.
2015-02-28 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 |  | 2007-06-30 | 2007-09-29 | Cont #1 - Offiste San Sewer & Storm (James Construction) | W912DR-07-C-0070 | 2657 | 2657 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 100% |  |  | Work complete. Contracts closed.
2015-02-28 | [8 empty] | 2008-01-10 | 2008-08-01 | Cont #2 - Storm Lat 1&3A (James Construction) | W912DR-08-C-0038 | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 100% |  |  | Work complete. Contracts closed.
2015-02-28 | [8 empty] | 2008-05-01 | 2009-09-28 | Cont #3 - IMP Pond (James Corporation) | W912DR-08-C-0078 | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 100% |  |  | Work complete. Contracts closed.
2015-02-28 | [8 empty] | 2008-01-10 | 2008-09-25 | Cont #4 - Early Site/Utility (Grunley/Goel JVA LLC) | W912DR-08-C-0053 | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 100% |  |  | Work complete. Contracts closed.
2015-02-28 | [9 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 2866 | 2866 | 2008-07-15 | 2013-12-06 | 2011-05-06 | 2013-10-31 | 100% | 2289 |  | Work being accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project. *** Need to add Contract #7 line items for FY 10/11 funding. FY 10: original contract amount ($496,221) and current contract/total obligation ($524,505.60). FY 11: original contract amount ($603,803) and current contract/total obligation ($638,219.77).
2015-02-28 | [8 empty] | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 15736 | 16161 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 94% |  |  | FY07. See FY2012 remarks. Contract active, but all funds on this increment obligated. Building to be operational NOV 2017.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63418 | USAMRIID Replacement, Incr 2 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 131264 | 138491 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | Phase I - FY 08 (note corrected PN)
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63419 | USAMRIID Replacement, Incr 3 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 185526 | 185630 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | FY09. See FY2012 remarks. Contract active, but all funds on this increment obligated.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63420 | USAMRIID Replacement, Incr 4 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 94000 | 100180 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | FY10. See FY2012 remarks. Contract active, but all funds on this increment obligated.
2015-02-28 | [9 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 496 | 525 | 2008-07-15 | 2013-12-06 | 2013-10-31 | 2013-10-31 | 99% |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65324 | USAMRIID Replacement, Incr 5 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 13497 | 12893 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-12-16 | 94% |  |  | FY11. See FY2012 remarks. Contract active, but all funds on this increment obligated.
2015-02-28 | [9 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 603 | 638 | 2008-07-15 | 2013-12-06 | 2013-10-31 | 2013-10-31 | 99% |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71101 | USAMRIID Replacement, Incr 6 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 66955 | 84624 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 94% |  |  | FY12. Scheduled 100%, Actual 94%. Liquidated damages from 16 Dec 2014 being assessed as a result of delays caused by a fire. Contractor's insurance covering repairs and delay costs. T&E change under negotiation with contractor. Contractor is re-installing BSL4 lab coatings, cleaning smoke-damaged BSL3 area equipment, and commissioning remainder of facility. Plan is to accept admin, BSL2 and BSL3 labs Jun 2016 to start CDC certification and accept BSL4 labs Jul 2017. North Parking funding shifted to this FY.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78210 | USAMRIID Replacement, Incr 7 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 0 | 0 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 0% |  |  | Utilities, DDC, Certification and related costs.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78211 | USAMRIID Replacement, Incr 8 | 58395 | 2015-01-22 | 2015-05-29 |  |  |  | 0 | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | CENAB in-house resources completed design. RTA date for North Parking adjusted to 30 Jan 15 and schedule readjusted to allow additional time for Maryland Dept of Environment approvals. Contract solicitation will include NIBC Fence - Ph II (FY 11 DODM) and Entry Control Point.
2015-02-28 | [8 empty] | 2017-04-01 | 2017-08-01 |  |  |  | 0 | 2019-08-22 | 2020-10-21 | 2020-08-22 | 2020-10-31 | 0% |  |  | Notional schedule shown; dependent on CDC/DA Safety certification of USAMRIID primary facility and vacation/decommissioning of existing buildings 1408/1412/1414/1415. Due to delay in main contract, projections for award are moved out 2 years.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 |  | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 7782 | 11366 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 25% |  |  | NOTE 1 : The Hospital Contractor is tracking with the late finish + 90 days of delay due to pier and structural steel delays with a projected completion of May of 2017. Due to these delays, anticipated challenges in the areas of sub-contractor management, and limited labor pools the BOD has been revised from 3 Apr 2017 to 3 Oct 2017. Placement to date: $154M as of 5 Feb 15. Slab on metal deck (SOMD) placements proceeding on floors 1 through 3. Contractor continues to make progress on concrete placements in basement connector spine. Heavy structural steel in the Hospital has completed and both cranes have relocated to the clinic footprints. Steel erection has begun on rotunda. Backfill of Admin footprint remains at approximately 80%. Surface foundations of the clinical investigation buildings (CIB) are proceeding. Review of laboratory performance mock up held. Lift Station installation is ongoing.
2015-02-28 | [8 empty] | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. - Infrastructure | W912G-09-D-0004-0008 | 39345 | 47508 | 2011-11-02 | 2013-10-12 | 2013-08-13 | 2013-08-29 | 100% |  |  | Construction 100% Complete
2015-02-28 | [8 empty] | 2011-03-25 | 2011-06-17 | Janco - Water Tower | W9126G-09-D-0096-0002 | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 100% |  |  | Construction 100% Complete
2015-02-28 | [8 empty] | 2012-03-16 | 2012-07-19 | VEMAC - Parking Pkg A | W9126G-12-C-0038 | 3848 | 3879 | 2012-08-28 | 2013-10-17 | 2013-06-19 | 2013-06-11 | 100% |  |  | Construction 100% Complete
2015-02-28 | [8 empty] | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960 | 2800 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-08-10 | 37% |  |  | The contractor began construction 3 Nov 14. DPW is researching the performance criteria / requirements for the lift station pumps due to their depth. Progress is on schedule for the Contract Required Completion of 10 Aug 2015.
2015-02-28 | [8 empty] | 2012-02-08 | 2012-09-04 | El Paso Electrical Substation | W9126G-12-P-0014 | 4047 | 4047 | 2012-09-04 | 2015-09-16 | 2014-01-04 | 2014-01-04 | 100% |  |  | Construction 100% Complete
2015-02-28 | [10 empty] | Temp Electric Contract |  | 46 | 46 |  |  |  |  | 100% |  |  | Temp power costs.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77251 | Fort Bliss Hospital Repl, Incr 2 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 68076 | 68076 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 25% |  |  | See Note 1 above.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72786 | Fort Bliss Hospital Repl, Incr 3 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 69851 | 72931 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 25% |  |  | See Note 1 above.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 76558 | Fort Bliss Hospital Repl, Incr 4 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 79914 | 160491 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 25% |  |  | See Note 1 above.
2015-02-28 | [8 empty] | 2013-08-08 | 2013-09-13 | Helipad | W9126G-13-C-0046 | 1540 | 657 | 2013-10-21 | 2014-11-24 | 2014-10-24 | 2014-10-24 | 100% |  |  | •Final Inspection was held on 6 Nov 2014. •BOD was 24 Nov 2014. •Contractor is currently working to complete punch list items.
2015-02-28 | [9 empty] | 2014-07-25 | El Paso Water Utility Pmt 2 / Sewer Contract | W9126G-14-P-0150 | 479 | 1538 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-08-10 | 37% |  |  | The contractor began construction 3 Nov 14. DPW is researching the performance criteria / requirements for the lift station pumps due to their depth. Progress is on schedule for the Contract Required Completion of 10 Aug 2015.
2015-02-28 | [9 empty] | 2015-02-15 | Parking Pkg B |  | 5562 | [5 empty] | 0% |  |  | Parking Package “B”:(small business- LPTA) Est. Award: $5.5M •Solicitation Package is complete. •Proposed Award Date: FY16
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77293 | Fort Bliss Hospital Repl, Incr 5 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 198148 | 77700 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 25% |  |  | See Note 1 above.
2015-02-28 | [8 empty] | 2014-10-20 | 2014-12-10 | ACPs |  | 24755 |  | 2014-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 0% |  |  | ACP Package: (small business-Best Value) Est. Award: $24.7M •Solicitation package is complete. •Proposed Award Date: FY16
2015-02-28 | [9 empty] | 2015-03-30 |  |  | 33125 | [5 empty] | 0% |  |  | No update this reporting period.
2015-02-28 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81047 | Fort Bliss Hospital Repl, Incr 6 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 225199 | 0 | 2013-05-29 | 2017-10-03 | 2016-11-26 | 2017-05-01 | 25% |  |  | See Note 1 above.
2015-02-28 | [8 empty] | 2015-03-30 | 2016-03-28 |  |  | 22616 |  | 2015-07-30 | 2016-07-30 | 2016-07-30 | 2016-07-30 | 0% |  |  | Landscaping Package: (small business-LPTA) Est. Award: $22.7M •Solicitation package is complete. •Proposed Award Date: FY16.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc | W9126G-12-C-0051 | 76038 | 76108 | 2012-11-01 | 2016-04-06 | 2014-07-29 | 2015-04-17 | 90% |  |  | NOTE 2: Construction Progress: Sch. 90%, Act. 90%. Pending modifications will add time and delay CCD from 17 Apr 15 by +/138 days to approximately 2 Sep 2015. Phase 3 includes Buildings G, H, J, K, L & M. Contractor has begun MEP punch-out, and finish work is ongoing in various buildings. Exterior work is complete or in the final stages. Site work: dining plaza footings underway, concrete placement continues and bollard installation ongoing.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 80793 | Ambulatory Care Center Phase 3, Inc 2 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc | W9126G-12-C-0051 | 16319 | 21362 | 2012-11-01 | 2016-04-06 | 2014-07-29 | 2015-04-17 | 90% |  |  | See Note 2 above.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  | 2012-03-15 | Environmental Compensation Also includes: Lots 7.2 & 7.3 Initial Compensation Measures | W912GB-10-C-0031 | 19836 | 19836 | 2014-01-13 |  | 2021-07-20 |  | 5% |  |  | German government solicitation and award dates to German industry are estimated.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 1 Temporary Construction Fence | W912GB-10-C-0031 | 462 | 260 | 2014-01-20 |  | 2014-04-04 | 2014-04-04 | 99% |  |  | Construction essentially completed April 2014; however, access from the east is still open. FRG Security Contractor will be on site in March 2015; at that time the construction fence will be closed off from the east, and construction access will be from the L369 construction gate.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 2.1 Demolition, Site Clearing | W912GB-10-C-0031 | 1588 | 1099 | 2014-06-16 | 2014-08-29 | 2014-10-29 | 2015-01-21 | 95.3% |  |  | Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Final inspection held on 21 Jan 2015, and final contract document provided by FRG (ABG7).
2015-02-28 | [9 empty] | 2012-03-15 | Lot 2.2 Mass Grading | W912GB-10-C-0031 | 24307 | 24307 | 2015-04-01 | 2016-04-15 | 2016-04-15 |  | 0% |  |  | Contract solicitation went out on 11 December 2014. FRG informed that contractor interest in this contract is high, and many questions were received. Bid opening was 10 February 2015. Bids are favorable, FRG to award late March 2015. Contaminated landfill remediation will not be part of this contract; FRG will issue a separate soliciatation for remediation work.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 3.1 Utilties to site | W912GB-10-C-0031 | 11183 | 11183 | 2015-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 0% |  |  | ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines. Change coordinated with DHA-Europe; 100% water supply will now come from civilian lines with redundancy. Change will also reduce risk in meeting German hygiene requirements for water supply. Awaiting new schedule from the FRG. Dates provided herein are estimated.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 3.2 Traffic Light System | W912GB-10-C-0031 | 155 | 155 | 2014-08-22 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 98% |  |  | The Traffic Light System will be in place upon start of construction for Lot 2.2.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 3.3 Construction Sign | W912GB-10-C-0031 | 19 | 19 | 2014-10-08 | 2014-12-31 | 2014-12-31 | 2014-12-31 | 100% |  |  | ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines. Change coordinated with DHA-Europe; 100% water supply will now come from civilian lines with redundancy. Change will also reduce risk in meeting German hygiene requirements for water supply. Awaiting new schedule from the FRG. Dates provided herein are estimated.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 3.4 Gas Line Relocation | W912GB-10-C-0031 | 560 | 560 | 2014-08-11 | 2014-10-16 | 2014-10-16 | 2014-10-16 | 100% |  |  | Construction complete.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 3.5 Transformers/Substation | W912GB-10-C-0031 | 19335 | 19335 | 2015-05-15 | 2017-01-15 | 2017-01-15 |  | 0% |  |  | This portion of the ROBMCR project may be accomplished as a direct project through NAU due to FRG issues with sole-source contract to the German power provider. NAU currently coordinating with FRG and power provider to prepare the SOW for this effort.
2015-02-28 | [9 empty] | 2012-03-15 | Lot 3.6 Water Connection to WZV-Weilerback system | W912GB-10-C-0031 | 2000 | 2000 | 2015-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 0% |  |  | The proposed route is currently under review by LBB/USACE/and Water Utility Company. A confirmation meeting for the proposed route is scheduled for 3 Mar 14
2015-02-28 | [9 empty] | 2012-03-15 | Lot 3.9 Site Security | W912GB-10-C-0031 | 6215 | 5966 | 2014-12-10 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 0% |  |  | FRG solicitation and award dates to German industry are TBD. Awaiting design schedule from FRG.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 76006 | Medical Center Replacement, Incr 1 |  |  | 2012-03-15 | 3.10 Site Logistics | W912GB-10-C-0031 | 2796 | 27996 | 2014-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 50%
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 76006 | Medical Center Replacement, Incr 1 |  |  | 2012-03-15 | Removal of X- Area Fencing | W912GB-10-C-0031 | 82 | 82 | 2015-06-01 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 0% |  |  | Coordination of the fence removal is underway.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 76006 | Medical Center Replacement, Incr 1 |  |  | 2012-03-15 | Communications Cable relocation | W912GB-10-C-0031 | 1 | 1 | 2014-10-23 | 2014-12-31 | 2014-12-31 | 2014-12-31 | 100% |  |  | Action 100% complete
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 76006 | Medical Center Replacement, Incr 1 |  |  | 2012-03-15 | Construction Additional Services | W912GB-10-C-0031 | 586 | 586 | 2015-03-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 0%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction |  | GERMANY | 72661 | Medical Center Replacement, Incr 2 | 76007 |  | 2013-08-27 | Construction Measures, Roadways, & Site Utilities | W912GB-10-C-0031 | 44950 | 44950 | 2015-06-15 | 2016-12-30 | 2016-12-30 | 2016-12-30 | 0% |  |  | FRG revising and coordinating lot requirements for campus roadways, utilities, and additional construction measures not included in current lot packages.
2015-02-28 | [9 empty] | 2013-08-27 | Lot 4 Access Control Point, Bridge, External Roadways | W912GB-10-C-0031 | 39286 | 39286 | 2016-04-15 | 2018-04-15 | 2016-04-15 | 2016-04-15 | 0% |  |  | 65% OTS design review scheduled for June 2015. German government solicitation and award dates to German industry are estimated.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 72662 | Medical Center Replacement, Incr 3 | 76007 |  | 2015-03-31 |  |  | 60551 | 60551 | 2016-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 0% |  |  | Included in MedCen 20% design. FRG kicked off post 20% design on 9 Dec 2014. Awaiting new schedule from FRG.
2015-02-28 | 2015 | Defense Health Agency | Major Military Construction |  | GERMANY | 76872 | Medical Center Replacement, Incr 4/5 | 76007 |  | 2016-03-31 |  |  | 593454 | 593454 | 2019-02-12 | 2022-11-08 | 2021-12-08 | 2021-12-08 | 0% |  |  | US led 20% MedCen final design submitted 2 Aug 2013. USACE is transitioning design to FRG. FRG AE target selection date is now September 2015 for follow-on 20-100% design. FRG solicitation and award dates to German industry are estimated
2015-02-28 | 2007 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 52330 | Clinic Replacement, Inc 1 |  | 2007-02-16 | 2007-07-19 | Caddell Construction Co, Inc | W91278-07-C-0037 | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100% |  |  | Water intrusion problem update - AE and Contractor being contacted - construction Contractor reviewing their records and will provide response to AF reports NLT 10 Feb 2015. Letter issued to Designer of Record 12 Jan 2015 requesting their response NLT 2 Feb 2015.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 67647 | Clinic Replacement, Inc 2 | 52330 | 2007-02-16 | 2007-07-19 | Caddell Construction Co, Inc | W91278-07-C-0037 | 32890 | 42183 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100% |  |  | Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. Construction Contractor reviewed their records and provided a response to AF reports 30 Jan 2015. A-E provided response on 2 Feb 2015. CESAM reviewed responses and is initiating acquisition of building envelope specialist to prepare independent determination addressing the responsibilities of each party and estimate of damages by each party.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71857 | Hospital Addition |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 31112 | 32852 | 2010-12-03 | 2013-07-15 | 2013-01-12 | 2013-07-15 | 100% | 3486 |  | Funds used for FY00 Settlement, Ft. Wainwright. Residual activity on project funding items.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) |  | 2009-04-08 | 2009-09-28 | Turner Construction Company | W912HN-09-C-0045 | 230018 | 275075 | 2009-10-22 | 2014-05-19 | 2013-02-03 | 2014-05-19 | 100% |  |  | Commissioning of systems continues. Contingencies at District: $426,402. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 1 Jul 15.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | KANSAS | UNITED STATES | 47298 | Hospital Replacement |  | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110 | 282778 | 2010-05-03 | 2015-07-01 | 2013-07-23 | 2015-04-01 | 98% |  |  | 2/19/2015 Fort Riley Replacement Hospital. a. Current CCD: 13 May 2014 b. Placement: 98% actual vs. 100% scheduled (as of December's pay estimate). c. Construction in progress: TAB/commissioning is ongoing. Testing of the atrium curtain walls revealed multiple leaks. Testing restarted 16 February and will continue as weather permits. Pre-final inspections continue. Final inspections have started in a few areas. d. Contractor's Schedule: Schedule not accepted as of November 2012 update. Schedule updates are being analyzed by NIBS and rejected. e. Estimated Completion: USACE estimated completion is 1 April 2015, but the Contractor is already missing milestones he gave us on his last update. Huntsville has postponed the delivery and installation of equipment and furnishings until further notice. The contractor exceeded the required completion date of 13 May 2014. Liquidated damages are being withheld at $16,500 per calendar day. Corporate/senior manager engagement continues. Contracting Officer's Final Decision issued 15 Dec 2014 denying $14 million steel claim. A claim/request for Contracting Officer's Final Decision associated with the expansion joint in the amount of $3,135,000.00 has been received and is under review. Contracting Officer's Final Decision is scheduled for July 2015. The Council of Colonels is conducting weekly conference calls to discuss progress on 11 specific items that need to be completed before BOD. BG Kem, BG Wesley, and Dr Hearn attended a briefing and tour of the hospital on 11 Feb 2015 and concurred with our course of action to delay joint occupancy until BOD.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 63864 | Health Clinic Add/Alt |  | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | W91DS-08-C-0019 | 27483 | 35963 | 2008-11-07 | 2012-12-01 | 2011-02-18 | 2013-12-12 | 100% |  |  | Financial closeout pending A-E Damages Resolution
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69626 | Burn Rehabilitation Center |  | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | W9126G-08-C-0036 | 18512 | 19120 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100% |  |  | Contract closeout ongoing.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 64473 | Medical/Dental Clinic |  | 2008-07-29 | 2008-09-18 | The Korte Company | 912DW-08-C-0018 | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 100% | 1885 |  | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2015-02-28 | 2008 | Defense Health Agency | Major Military Construction |  | GERMANY | 52332 | Medical Clinic Replacement |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 100% |  |  | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. NAU will provide details on the claim.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 71653 | Hospital Replacement (ARRA) |  | 2010-06-11 | 2010-09-01 | Clark/McCarthy, JV | N62473 10 C 0001 | 418039 | 425895 | 2010-12-03 | 2013-10-17 | 2014-01-07 | 2014-01-07 | 100% |  |  | Multiple residual closeout issues.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 73599 | Hospital Renovation & MRI Addition (Cong Add) |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178 | 28612 | 2010-12-03 | 2015-03-04 | 2015-01-02 | 2015-07-03 | 92% |  |  | Active Project.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 55918 | Central Utility Plant |  | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034 | 13672 | 2009-10-01 | 2011-06-22 | 2011-02-07 | 2011-06-22 | 100% |  |  | Residual closeout issues.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 70350 | Hospital Alteration (ARRA) |  | 2011-07-26 | 2011-09-15 | Federal Contracting DBA Bryan Construction | W9128F-06-D-0019 | 15929 | 20393 | 2011-11-08 | 2014-03-23 | 2013-11-27 | 2014-01-21 | 100% |  |  | Chiller Plant- Need warmer weather to fully test chillers and finish commissioning.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 70354 | Hospital Replacement (Supplemental) |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 159834 | 163146 | 2012-05-30 | 2017-07-16 | 2015-03-16 | 2017-05-15 | 33% |  |  | Significant changes in processes impacting water storage and the central utility plant are being resolved. Full impact of the changes on the project are unknown and continue to be addressed by the delivery team. Senior leadership continues to engage regularly to assist in resolution of project issues.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 79845 | Eglin Hospital Alteration (ARRA) |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction | W9126G-08-D-0057 | 51133 | 59456 | 2011-10-31 | 2015-03-12 | 2014-11-06 | 2015-07-28 | 98% |  |  | Contract including all currently identified modifications is at 99.58% of PA. Hospital Command moved into new building Dec 19. Urology, ENT, Lab II, Surgery Phase III move in also completed mid December. Contractor is 44 days behind schedule on base contract requirements. Current contract completion date Dec 21, 2014. CT/PET modification to meet Air Force certification requirements in process. Proposal received Jan 29, 2015 which will extend the project completion date to July 28, 2015. Estimated equipment arrival date May 1, 2015 with a scheduled move in date of July 28, 2015.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 59220 | Hospital Add/Alt (Supplemental) |  | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500 | 29431 | 2011-10-26 | 2015-06-01 | 2014-03-03 | 2015-05-26 | 82% |  |  | Curtain wall panels continue to be delivered and installed. Work continued towards completion to meet BOD date. Air Vapor Barrier 99% complete. Metal panel installation on-going. Main Roof 95% complete. Drywall installation and painting continues on 2nd floor and 1st floor.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) |  | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 76944 | 84365 | 2011-10-25 | 2015-03-18 | 2014-09-09 | 2015-03-18 | 98.1% |  |  | Substantial completion and BOD date of 18 Mar 15 will be reached. ENT Department turned over early February. Orthopedics Department turnover scheduled for 13 March. All Departments will be possessed and in use by 13 March. Waiting on DHA decision on user requested exterior plenum work. Punch list work continues. No additional funding is anticipated to execute remaining work including the plenum.
2015-02-28 | [8 empty] | 2011-03-07 | 2011-03-20 | A1 Tree Service (Tree Cutting) |  | 9.6 | 9.6 | 2011-03-20 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 100% |  |  | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2015-02-28 | [8 empty] | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp (Swing Space) | W912QR-11-C-0027 | 5395 | 5395 | 2011-07-01 | 2015-03-18 | 2014-09-27 | 2015-03-18 | 99% |  |  | Leased Swing Space awarded for risk mitigation.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 62189 | Medical / Dental Clinic Replacement |  | 2008-10-27 | 2009-04-03 | Hensel Phelps | W912BV-09-D-2016 | 47615 | 51375 | 2009-06-01 | 2012-06-04 | 2011-10-26 | 2012-02-09 | 100% |  |  | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub.
2015-02-28 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) |  | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989 | 560053 | 2010-11-08 | 2015-07-17 | 2014-05-31 | 2015-06-30 | 92% |  |  | The government now expects the contractor to be complete with construction NLT 22 Jun 15, and has established the Hospital's BOD at 17 Jul 15. Intermediate dates have been established to facilitate furniture move-in in support of IO&T as well as help gauge the contractor's progress towards meeting his completion date. CCD remains unchanged (23 Nov 14). Liquidated damages currently being assessed.
2015-02-28 | [8 empty] | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc, Sanitary Sewer |  | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 100% |  |  | Construction 100% Complete
2015-02-28 | [8 empty] | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities | W9126G-10-C-0032 | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 100% |  |  | Construction 100% Complete
2015-02-28 | [8 empty] | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc., Demolition of Hood Stadium | W912DY-05-D-0011 | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 100% |  |  | Construction 100% Complete
2015-02-28 | [8 empty] | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. New Stadium | W9126G-09-D-0100 | 17290 | 15383 | 2011-01-06 | 2013-12-15 | 2012-06-29 | 2015-06-30 | 99% |  |  | Contractor working on additional punchlist items and close out documentation.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement |  | 2010-06-16 | 2010-12-14 | Vinci Construction UK |  | 13098 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 100% |  |  | Estimated financial closure: 31 Dec 2014
2015-02-28 | [8 empty] | 2013-04-05 | 2013-06-15 | VolterFitzpatrick (Sidewalk) |  | 68 | 68 | 2013-07-01 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 100%
2015-02-28 | [8 empty] | 2014-08-20 | 2014-08-25 | Vinci Facilities (Entrance door amendments) |  | 69 | 69 | 2015-03-03 |  | 2015-01-30 | 2015-06-30 | 0% |  |  | Contractor has queried the original steelwork design, DIO currently investigating the query. No progress on site until resolved. DIO cannot close main project until this local order is complete. Awaiting contractor to provide detail to support claim that original steelwork design is not to standard.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61401 | Boundary Gate at Nallin Pond |  | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075 | 10119 | 2011-01-12 | 2014-12-31 | 2013-01-10 | 2015-01-08 | 100% | 785 |  | 1354 was signed on 8 Jan 15. One punchlist item remains; the final intersection top coat that will be installed once the temperature rises above 40 degrees (Mar 15). All pending modifications/REAs are settled. Project is current within Congressional authority (NTE $12.692M).
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61536 | Emergency Service Center |  | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | W912DR-10-C-0087 | 13478 | 13858 | 2010-07-19 | 2013-05-23 | 2012-09-16 | 2013-05-23 | 100% |  |  | Expected to closeout March 2015.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) |  | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | W912HN-11-C-0002 | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 100% | 458 |  | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14. Financial close-out underway.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 71318 | Dental Clinic Replacement |  | 2009-10-28 | 2010-02-26 | J E Dunn Construction Company | W9126G-08-D-0057 | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 100% | 3144.239 |  | Retainage on the project recently paid, processing close out. The project funds have been returned.
2015-02-28 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center, Phase 1 |  | 2010-06-11 | 2010-08-19 | J E Dunn Construction Company (Bldg 1 & CEP) | W9126G-08-D-0057 (TO 0005) | 41566 | 45105 | 2010-10-04 | 2013-11-19 | 2013-02-20 | 2013-08-30 | 100% |  |  | Building 1B is complete and turned over to the Air Force. BOD is 19 Nov 13. Interim DD 1354 has been signed by BCE 5 Dec 13. Contractor working stone issue.
2015-02-28 | [8 empty] | 2010-06-11 | 2010-08-31 | J E Dunn Construction Company (Parking Structure & Temp Parking) | W9126G-08-D-0057 (TO 0006) | 23216 | 24153 | 2010-10-04 | 2012-12-13 | 2012-02-26 | 2012-11-30 | 100% |  |  | Phase 1A consisting of a multi-story parking garage and a Central Energy Plant is complete and turned over to the Air Force. BOD 13 Dec 2012. The Area Office is waiting on JE Dunn’s corrective action plan to correct the stone block installation (remaining warranty work).
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77116 | NNMC Parking Expansion |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 14030 | 14392 | 2012-06-18 | 2013-12-02 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77115 | Transient Wounded Warrior Lodging |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133 | 48829 | 2012-06-18 | 2014-05-27 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70482 | Health Clinic Addition/Alteration |  | 2010-11-19 | 2011-06-03 | McCarthy Building Companies | W912HN-11-C-0006 | 23050 | 25062 | 2011-06-21 | 2013-11-29 | 2013-06-20 | 2014-05-19 | 100% |  |  | Contingencies at District: $18,120. CAT E&F remaining at Distirct: $825,711.12. Final payment scheduled for 30 Mar 15. Financial close-out underway.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MASSACHUSETTS | UNITED STATES | 71634 | Mental Health Clinic Addition |  | 2011-11-04 | 2011-12-23 | Watermark Environmental, Inc. | W912WJ-12-C-0002 | 2790 | 2790 | 2012-05-18 | 2013-02-16 | 2013-01-16 | 2013-03-01 | 100% |  |  | Final payment to Contractor in process. Awaiting singed 1354 from Hanscom AFB. No issues that USACE is aware of in terms of Hanscom signing the 1354.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 73360 | Consolidated Logistics Facility |  | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869 | 19957 | 2011-07-21 | 2014-12-05 | 2014-01-06 | 2014-11-14 | 100% |  |  | Punchlist item completion by Mar 15. Furniture funding for both CONLOG buildings was received; anticipating install May 2015.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 62886 | Information Services Facility Expansion |  | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | W912DR-12-C-0004 | 4270 | 4624 | 2012-03-19 | 2015-02-10 | 2013-11-09 | 2015-02-28 | 99% | 232 |  | Commissioning underway. Furniture being installed. BTR of $232K from Health and Dental Clinics, White Sands to Information Services Facility, Ft. Detrick, MD executed on May 6, 2014. Contract amount corrected to reflect contract obligation only.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67949 | NIBC Security Fending and Equipment |  | 2011-08-19 | 2012-02-14 | Cont #1 (Segment 1) (Rich Moe Enterprises, LLC) | W912DR-12-C-0001 | 1701 | 1701 | 2012-04-02 | 2013-04-01 | 2013-04-02 | 2013-04-01 | 100% |  |  | Segment 1 - Project Closed. Segment 2 will be awarded on 29 May 15.
2015-02-28 | [8 empty] | 2015-02-13 | 2015-05-29 |  |  |  |  | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | RTA date for Fence Segment 2 was 30 Jan 15. Contract solicitation will include USAMRIID Replacement North Parking which establishes overall site contours for fence construction. Combine with RID. Authority to advertised provided 12 Feb 2015.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67953 | Supplemental Water Storage |  | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468 | 3944 | 2011-07-20 | 2015-04-30 | 2012-11-01 | 2015-04-30 | 97% | 263 |  | % Complete (Scheduled/Actual): 100/97 Contractor having difficulty completing pump facility. LD's being assessed from 30 May 2014. BOD slipped to 30 Apr 15 due to contractor performance and need to secure final MDE water system connection permit.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67951 | Water Treatment Plant Repair |  | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308 | 15540 | 2013-01-14 | 2015-04-30 | 2014-07-08 | 2015-04-30 | 91% | 5000 |  | % Complete (Scheduled/Actual): 99/91 BOD slipped due to city sewer connection and contractor performance. Commissioning underway. Potential CWE is showing 105% above PA.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 70472 | Health and Dental Clinic |  | 2010-11-02 | 2011-07-22 | Charpie-Korte Dsn-Bld JV S.B. L.L. | W9126G-11-C-0031 | 14837 | 15067 | 2011-08-18 | 2013-04-26 | 2013-03-30 | 2013-08-02 | 100% | 1095 |  | CT final Payment made 25 NOV 14.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72752 | Ambulatory Care Center Phase 2 | 72430 | 2011-05-20 | 2011-09-28 | SKANSKA USA Building Inc. | W9126G-11-C-0053 | 80558 | 92317 | 2011-12-02 | 2015-10-01 | 2013-10-01 | 2015-04-04 | 97% |  |  | Current CCD (4 Apr 2015) is expected to slip right +/120 days as a result of pending modifications. Phase 2 includes Buildings A, B, C and Concourse. Punch list ongoing in most areas. Testing and Balancing is underway. Central Energy plant equipment startup, testing, and commissioning are ongoing. Completion of generator startup pending repair of generator, and resolution of generator room ventilation issue. Based on preliminary information and feedback from DHA the adjusted CWE for Phase 2 of $110,265,000 is within Congressional Authorization and will not require an Above Threshold Reprogramming (ATR). It was noted that additional funds above this amount would require reprogramming. Phase 2 Pending Modification (Electrical Design Issue): HDR submitted design solution on 17 Feb 2015 and the Area Office issued on RFP for the long-lead time material on 20 Feb.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 71251 | Dental Clinic Replacement |  | 2009-09-16 | 2011-05-17 | Forrester Construction Company | W912DR-10-C-0067 | 2832 | 3185 | 2011-05-17 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | Fiscal Closeout is scheduled, and tracking for 10 Apr 2015, along with Project # 64241.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66693 | Health/Dental Clinic Replacement |  | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | W912GB-09-C-0029-NA | 34294 | 34376 | 2014-02-03 | 2016-06-11 | 2015-08-22 | 2016-04-12 | 38% |  |  | Roof parapets and roof insulation substantially complete. Exterior window and curtain wall install is substantially complete. Interior masonry wall plaster work is substantially complete. Construction of interior drywalls is ongoing. Steel framing for the mechanical enclosure is ongoing. Parking lot curbstone and gutter install is ongoing.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66588 | Health Clinic Add/Alt |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 32103 | 32103 | 2013-04-08 | 2017-01-07 | 2016-04-12 | 2016-09-04 | 63% |  |  | Interior Mech/Elect work continues.plumbing,ductwork, and comms on 1st & 2nd floors. - Door and window installation ongoing, 1st & 2nd floors. - Interior finish work ongoing; painting, tiling walls/floors, rubber flooring. - Construction of new lobby between existing and new Health Clinics ongoing. - Photovoltaic panels installed on roof. - Final inspection and acceptance of new Tennis Court on 17DEC14. Ongoing discussions to resolve carpet change request, to finalize letter of guarentee from Germany supplier.
2015-02-28 | 2011 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 51740 | Health/Dental Clinic Replacement |  | 2011-05-13 | 2011-08-26 | Ilsung Construction Co., Ltd. | W912UM-11-C-0024 | 9821 | 10169 | 2011-08-26 | 2014-04-23 | 2013-05-13 | 2014-04-23 | 100% |  |  | The Carroll Dental Clinic OIC and NCOIC were in the lead for a ribbon cutting ceremony, however, per HFPO, a ceremony does not appear to be occurring. Awaiting final billing ($19,954.70) from DLA for LOGCAT F equipment training.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 72727 | Medical/Dental Clinic Replacement |  | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd |  | 11958 | 11958 | 2014-05-06 | 2015-07-31 | 2015-10-30 | 2015-12-25 | 55% | 13060 |  | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14. Contracting Officer has granted a nil cost extension of time to 25 Dec 2015 based on delays resulting from the original groundwork subcontractor withdrawing from the contract and from a national shortage of labour delaying the brickwork trade.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65030 | Naval Hospital Great Lakes Health Clinic Demolition |  | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co | N40083 12 C 0001 | 5835 | 6195 | 2012-09-12 | 2014-04-21 | 2013-09-13 | 2014-08-08 | 100% | 3994
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 79554 | Child Development Center |  | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200 | 14457 | 2013-03-01 | 2014-04-07 | 2014-02-22 | 2014-06-02 | 100%
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71408 | Dental Clinic Replacement |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688 | 18688 | 2013-03-01 | 2016-12-06 | 2016-09-29 | 2017-01-28 | 0% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | MISSISSIPPI | UNITED STATES | 71503 | Branch Health Clinic |  | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Constr, Inc | N69450 12 C 0754 | 19096 | 20597 | 2012-09-01 | 2015-08-31 | 2014-09-09 | 2015-05-22 | 80%
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 70597 | Medical Clinic |  | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | W91278-12-C-0028 | 8897 | 9137 | 2012-10-17 | 2015-01-05 | 2014-10-07 | 2014-10-07 | 100% |  |  | Final document turnover in process. Performing post BOD changes at user request, PT room flooring, walk off matts, rear gate padlocks and door hardware. Final Pay anticipated April, 2015.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 72292 | Hospital Addition/Alteration Phase 2 |  | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778 | 44031 | 2012-10-15 | 2017-06-14 | 2016-10-14 | 2017-03-17 | 67% |  |  | PA $58,845,000. Design error (for exterior precast panels) required work stoppage to remove, redesign, & replace the panels. 145 days were added to the emergency dept interim milestone & 83 days to overall project completion. Demand Letter dated 30 Jan 15 issued to A-E for $1.8M incurred costs as a result of this design error. A-E response to Demand Letter was received 6 Mar 2015. Project is over 11% contingencies which are being funded by bid savings and excess CAT E&F funds. SAS submitted to HQUSACE a cost control plan for implementation. A revised phasing plan is under review to aid in cost savings. Contingencies at district: $684,235 of which $287,232 is for temp. swing space.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70438 | Hospital Addition/Alteration |  | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company (DBA: Mortenson Construction) | W912QR-12-C-0036 | 43466 | 46198 | 2012-08-22 | 2015-05-23 | 2015-02-21 | 2015-03-25 | 86% |  |  | Pending $5.342M REA. Update on Claim resolution: We are reviewing resumes of senior schedule analyzers and will select one from the company under contract. The selected person should be on site by NLT 6 March. The a Time Impact Analysis is the first deliverable we'll get. LRL will keep everyone informed on what delivery date is reached for that initial product.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 70351 | Hospital Alteration |  | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400 | 23750 | 2012-09-13 | 2015-12-31 | 2014-06-23 | 2015-04-05 | 60% |  |  | Contractor is 38% behind schedule. Contingencies at District: $211,187. Contractor has been issued an Interim Marginal CCASS. Emergency Dept construction is on schedule. Tile re-work on 4th Floor is underway. Several face to face and telephone meetings have been held between SAS and upper level at R&M. Negotiations underway on DHA approved User Change to delete work on 2 floors from the contract. SAS returned $17,720.40 of P&D by Revocation FAD 021 2010 2050 32002000000 dated 9 Feb 15.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70580 | Dental Clinic Addition /Alteration |  | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | W91DS-13-C-0002 | 4370 | 4370 | 2013-01-09 | 2014-12-19 | 2015-01-09 | 2014-12-19 | 100% |  |  | BOD 19 DEC 14.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70579 | Medical Clinic (SFCC) |  | 2012-10-05 | 2013-02-13 | Structural Associates. Inc. | W912DS-13-C-0022 | 8934 | 8934 | 2013-03-15 | 2015-06-11 | 2015-03-06 | 2015-03-06 | 99% |  |  | Commisssioning was completed on 27 JAN 15. Contractor resolving two issues. Awaiting commissioning report. Prefinal Inspection was conducted on 23 Jan 2015. Contractor correcting punchlist items.
2015-02-28 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 51969 | Hospital Nutrition Care Department Add/Alt |  | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | W9126G-12-C-0050 | 28291 | 26993 | 2012-10-02 | 2015-05-02 | 2014-10-30 | 2015-05-31 | 92% |  |  | Contractor filed seven claims in Nov 14 totaling $1.4M. OC denied the claims in February and the contractor filed an appeal. PDT confidence in contractor delivery is low; contractor insists BOD will be 18 Mar; PDT believes it to be early to mid April. HFPA has organized a weekly status update to the hospital DCA to better track the contractors delivery and reinforce the need for timely delivery. New Issue: Contract provides sealed concrete floors in certain areas of the kitchen and storage; end user demands quarry tile throughout; change would delay contract by several months and cost over $500K; PDT developing solution.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 72808 | Medical Clinic Replacement |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc | N62473 10 D 5412 DO 0007 | 18703 | 18853 | 2014-02-28 | 2015-04-16 | 2015-03-16 | 2015-03-16 | 21%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 78143 | Navy Drug Lab Replacement |  | 2013-01-14 | 2013-08-22 | Blinderman Constr Co | N40083 13 C 0003 | 14864 | 14798 | 2013-11-08 | 2015-04-15 | 2015-01-15 | 2015-04-18 | 95%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71507 | Branch Health Clinic Replacement |  | 2013-02-28 | 2013-12-18 | Turner Construction Co | N40080 14 C 0154 | 41408 | 41451 | 2014-04-30 | 2015-12-31 | 2015-10-15 | 2016-01-12 | 25%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80307 | Implement Base Installation Appearance Plan |  | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898 | 4608 | 2014-04-01 | 2015-04-08 | 2015-03-31 | 2015-09-15 | 3%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities |  | 2013-07-25 | 2012-09-12 | G-W Management Servicxes Inc (Dosimetry Award) | N40080 10 D 0498 DO 0025 | 5286 | 5217 | 2013-10-15 | 2014-04-04 | 2013-12-13 | 2014-03-25 | 100%
2015-02-28 | [8 empty] | 2014-03-15 | [12 empty] | On hold per DHA
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80308 | Electrical Utility Upgrades |  | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947 | 26947 |  | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2% | 19460 |  | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 78144 | Medical Clinic Addition |  | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354 | 14614 | 2013-10-08 | 2015-03-31 | 2015-03-17 | 2015-07-08 | 80%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71317 | Medical Clinic Replacement |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744 | 40398 | 2013-12-06 | 2016-03-18 | 2016-12-30 | 2017-10-07 | 42%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 78146 | Veterinarian Facility |  | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254 | 7450 | 2014-02-28 | 2015-05-15 | 2014-12-06 | 2015-06-22 | 54%
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 51639 | USARIEM Replacement High Altitude Research Lab |  | 2015-04-17 | 2015-12-10 | [11 empty] | Received Code 7 Directive on 26 Jun 14. PM met with stakeholders the week of 28 Jul 14 to discuss the way forward and develop the revised design schedule. The most significant action impacting project completion will likely be the preparation of NEPA documents by the City of Colorado Springs. Will need Funds authorization extension. EXPECT CODE A request by 15 March 2015.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 72718 | Medical Logistics Warehouse Replacement |  | 2012-10-18 | 2013-06-18 | R&W Builders | W912QR-13-C-0021 | 2215.9 | 2215.9 | 2013-07-01 | 2014-07-30 | 2014-04-27 | 2014-07-23 | 100% |  |  | Contingency balance is zero. Closeout is in progress.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 71679 | Dental Clinic |  | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture | W912DQ-13-C-4017 | 10687 | 10505 | 2013-12-02 | 2015-04-29 | 2015-02-19 | 2015-04-29 | 97% |  |  | Complete 19 Feb. Facility transfered with some pending items awaiting replacement parts/materials. Schedule: On schedule. LEED: Silver required (solar panels for domestic hot water and solar light tubing). Pending certification review by USGBC. Time Growth: None FISD: To be performed by HFPA after turnover.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71325 | Medical Clinic Replacement |  | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536 | 47116 | 2013-10-24 | 2017-07-21 | 2016-10-23 | 2016-12-11 | 18% |  |  | Contractor continues with site work and site demo. Placement of foundations are underway. Contingencies at District: $465,125.19. Cat E&F Equip funds at District: $1,723,000
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77979 | Medical/Dental Clinic Replacement |  | 2013-09-03 | 2014-03-27 | JE DUNN + HWA | W9127S-13-D-6001 | 47044 | 47044 | 2014-04-28 | 2018-01-08 | 2017-10-25 | 2017-10-25 | 4% |  |  | Contractor is working toward Submittal #2 (65% bldg/ 95% site design) due to be received 3 April.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 73776 | Soldier Specality Care Clinic |  | 2012-11-15 | 2013-12-18 | Structural Associates | W91DS-14-C-0003 | 11163 | 11163 | 2014-01-06 | 2016-04-05 | 2016-01-06 | 2016-01-06 | 31% |  |  | Contractor continues placement of the structural steel. Roof decking installation started 11 FEB 2105
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72420 | Medical/Dental Clinic Addition |  | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. | W912UM-13-C-0018 | 8544 | 8932 | 2013-06-05 | 2015-05-16 | 2015-02-25 | 2015-03-29 | 94% |  |  | Contingency Amounts: District $8,991; HQ Mgmt $0. 32 days have been added to the CCD, including 15 days for K0002, Differing Site Conditions for Sewer Line, 10 days for K0008, User Requested Change - DIPC/Clean Room, and 7 days for K0010, User Request Change-Rev B. Revised CCD is 29 Mar 2015. A separate CCD for sterilizer equipment installation in room 135 is 22 May 2015.
2015-02-28 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72419 | Hospital Addition/Alteration |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co., Ltd. | W912UM-13-C-0025 | 22361 | 22383 | 2013-09-26 | 2017-11-17 | 2017-08-08 | 2017-09-02 | 29% |  |  | Contingency Amounts: District $319,464; HQ Mgmt $782,422. Steel structure work in Area 1 of Steel Structure Work Plan is at 90% complete. Temporary power ongoing.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80904 | Mechanical & Electrical Improvements |  | 2014-01-30 | 2015-03-31
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80913 | Parking Garage |  | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835 | 15835 |  | 2016-04-16 | 2016-04-16 | 2016-04-16 | 0%
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77000 | Public Health Command Laboratory Replacement |  | 2014-03-24 | 2015-06-30 | [11 empty] | OSD requested bid date extended to 30 Jun 2015 to support reprogramming effort.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77922 | Medical Clinic Replacement |  | 2014-02-25 | 2014-08-20 | Gilbane | W9127S-13-D-6000 | 45629 | 47382 | 2014-10-27 | 2018-08-16 | 2018-01-30 | 2018-01-30 | 4% | 23279 |  | Submittal #1 (35% Arch/MEP/Fire, 65% Foundation/Structural, 100% Civil/Site) was received 7 Feb 2015. Design review closes 27 February. Review conference scheduled for 2-6 March at Holloman AFB.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81340 | SAMMC Hyperbaric Facility Addition |  | 2014-03-17 | 2014-06-30 | Gilbane | W9127S-13-D-6000 DY01 | 11289 | 11289 | 2015-07-10 | 2016-12-28 | 2016-09-30 | 2016-09-30 | 0% | 1900 |  | 65% submittal slipped four weeks. Slip may impact construction start date. Contractor has stated it will not delay completion.
2015-02-28 | 2014 | Defense Health Agency | Major Military Construction |  | BAHRAIN | 81436 | Medical/Dental Clinic Replacement |  | 2015-04-15 | 2015-08-15 | [11 empty] | On track for Aug 2015 award of a Design-Build contract with a one-year design period. This award schedule is being driven by site availability, pending completion of an on-going MCN project, the P908 Operations and Support Facilities, scheduled for completion in July 2016; expecting no additional schedule slippage. AE code update completed on 30 January 2015 and design/specs received on 3 February 2015 to begin review; CWE will be re-validated upon completion of the BCOE review. Expect to request Code A NLT 31 March 2015.
2015-02-28 | 2015 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 72414 | Dental Clinic Replacement |  | 2015-03-30 | 2015-07-30 | [11 empty] | Final RFP Review Conference held on 29 Jan 15 Resolving comments related to new medical template for DB, which delayed advertisement.
2015-02-28 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81423 | Medical Clinic Replacement (Reid Clinic) |  | 2015-03-13 | 2015-06-10 | [11 empty] | RFP final review ongoing. BCOES on schedule for completion by 20 Mar 15. Project on schedule for 10 Jun 15 award.
2015-02-28 | 2015 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 81430 | Hospital Add/CUP Replacement |  | 2015-07-09 | 2015-12-18 | [11 empty] | Received Code 7 on 16 Oct 13. Orginal scheduled AE1 contract award date was 30-APR-14. Actual award on 02-SEP-14. Primary cause for delay in award of the AE1 was conflicting scope requirements and level of design for the D-B RFP between DHA and the MX. The AE1 PoP to RTA provides an Advertise date of 01 June 2015. The construction contract will also include turnkey FFE and medical equipment. Thus increasing the procurement to > $50M. FY15 award is considered high risk due to the potential for an extended period (multiple rounds of discussion) for review of D-B contract proposals
2015-02-28 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 86944 | NiCOE Satellite, Infrastructure Support | [14 empty] | Conducted kickoff meeting on 29 Jan 15; in the process of developing the P&D budget and coordinating in-house resources for RFP development.
2015-02-28 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 86943 | NiCOE Satellite, Infrastructure Support | [14 empty] | HNC conducted a Planning Charrette. District is validating 1391 and developing ENG3086 for approval. DHA indicates this project will very likely not be awarded until CY16.
2015-02-28 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81627 | NiCOE Satellite, Infrastructure Support |  | 2015-06-02 | 2015-08-03 | [11 empty] | DD1391 has been approved and NWS is proceeding with development of RFP. Need DHA to issue DA to develop RFP (Code 7). Site approval impacted by lack of coordination with current tenants. Schedule impacts may occur. JBLM, ACSIM, and DHA working to reslove.
2015-02-28 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 86899 | Structural Repairs Pharmacy Floor Building 02 |  |  | 2014-11-01 | Air Services Inc |  |  |  | 2014-12-01 |  | 2015-03-31 | 2015-08-01
2015-02-28 | 2008 | Defense Intelligence Agency | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 154207 | Emergency Backup Water System |  | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC |  | 1012 | 1012 | 2009-10-03 | 2012-01-20 | 2011-09-16 |  | 100% |  |  | Approp. - $1,012
2015-02-28 | 2010 | Defense Intelligence Agency | Major Military Construction | ALABAMA | UNITED STATES | DIA10-002 | Replace MSIC Explosive Ordinance Exploitation (EOE) Complex |  | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company |  | 12000 | 12003 | 2012-07-20 |  | 2014-01-20 | 2014-05-21 | 100% |  |  | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved. Contingency funds will be used in FY15 for within scope modifications.
2015-02-28 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction |  | KOREA, SOUTH | DIA10-001 | FOB-K Renovation of Two Buildings to Include Administrative and SCIF Spaces |  | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd. |  | 4608 | 5224 | 2012-04-09 |  | 2013-10-09 | 2013-10-17 | 100% |  |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project in process of closeout.
2015-02-28 | 2011 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA11-002 | JBAB Paving of Gravel Parking Lot |  | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture |  | 2984 | 2294 | 2011-07-20 | 2012-07-25 | 2012-07-18 | 2012-07-25 | 99% | 690 | DIA10-001 | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2015-02-28 | 2012 | Defense Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | DIA12000005 | Construction of Remote Delivery Facility (RDF) Meeting SCIF Standards |  | 2013-08-21 | 2013-09-25 | Heard Construction |  | 10758 | 6058 | 2013-10-10 |  | 2014-09-30 | 2015-03-11 | 60% |  |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Major construction activities last month were installation of roofing system (up to final layer - after all HVAC work is completed final layer to be installed), exterior metal panels completed, interior electrical and mechanical nearing completion (estimated for mid-February 2015), and installation of setting utilities meters. Final Trim-out and Punch phase expected to begin on or around 1 March 2015. Majority of final non-MILCON fitout work is now under contract; only about $160K of IT related work is not under contract as yet. Majority of increase in contract amount is due to unforeseen site conditions and extreme weather at key points in the construction schedule (additional minor mods are expected).
2015-02-28 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000001 | DIAC Parking Garage Replacement |  | 2014-06-16 | 2014-09-23 | Arriba |  | 13586 | 13358 | 2014-10-23 |  | 2016-03-02 | 2016-03-02 | 0% |  |  | Approp. - $13,645 - $793,156 CAT I obligated. Concept Design Workshop was conducted on 20 November 2014. 50% design review condected on 11 February 2015. NAVFAC PM has requested an additional $2M for the prject; DIA is still awaiting official request.
2015-02-28 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000003 | DIAC Chilled Water Project for Data Center | [14 empty] | Estimates indicate project costs exceed programmed amounts. DIA initiating reprogramming action to move funds to UPS for Data Center
2015-02-28 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center | [14 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions to add funds from the DIAC Chiller project.
2015-02-28 | 2013 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES |  | Parking Garage Demolition | [14 empty] | This line was reduced due to sequestration. The remaining funds are insufficient to complete demolition of the existing parking garage. DIA is currently exploring options
2015-02-28 | 2013 | Defense Information Systems Agency | Major Military Construction |  | GERMANY | 13DISA01 | DISA Europe Facility Upgrade | [14 empty] | PA: $2.224M. Awaiting USACE to schedule Design Kick Off Meeting. USCE determined this will be a "Direct" Contract.
2015-03-01 | 2013 | Defense Information Systems Agency | Major Military Construction | ILLINOIS | UNITED STATES | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994 | 65994 | 2014-03-01 |  | 2014-12-30 | 2016-03-09 | 52% |  |  | PA: $77.515M. Three (3) separate contracts: Soil Remediation $1.34M completed Feb 14; Construction $66M and Demolition of Bldg 3189 - TBD. Construction completion date slipped due to weather.. Original date 1 Mar 2016.
2015-03-02 | 2014 | Defense Information Systems Agency | Major Military Construction | HAWAII | UNITED STATES | 14DISA01 | DISA Pacific Facility Upgrade | [14 empty] | PA: $2.615M. NAVFAC preparing RFP for Design. RFP will take into consideration the Navy's Energy Project to replace the 2 existing chillers.
2015-03-03 | 2015 | Defense Information Systems Agency | Major Military Construction |  | AUSTRALIA | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) | [5 empty] | 9600 | 9600 | [7 empty] | PA: $9.6M. Combined Communications Gateway Geraldton. NAVFAC will prepare RFP for Design to construct Electronic Equipment Building, Antenna Foundations for the AN/GSB 52B Medium Satellite Earth Terminals and supporting infrastructure.
2015-02-28 | 2008 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INC #1 - NAV SUP Fleet Logistics Center, Point Loma San Diego | DESC0704 | 2008-02-20 | 2008-09-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99% |  |  | wo# 861477
2015-02-28 | 2010 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) - NAV SUP Fleet Logistics Center, Point Loma San Diego | DESC0704 | 2008-02-20 | 2011-03-22 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99% |  |  | wo#861477
2015-02-28 | 2010 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC0908 | Replace Jet Fuel Storage Complex - Jacksonville ANG | DESC0908 | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | W912EP-10-C-0023 | 7909 | 9988 | 2010-04-27 | 2014-04-10 | 2011-09-20 | 2014-09-30 | 100%
2015-02-28 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | KOREA, SOUTH | DESC0907 | Hydrant Fuel System - Osan AB | DESC0907 | 2010-01-12 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844 | 19638 | 2010-08-27 | 2015-04-20 | 2013-11-18 | 2015-04-30 | 99%
2015-02-28 | 2011 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) - Pt. Loma | DESC0704 | 2008-02-20 | 2011-03-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99% |  |  | wo#974938
2015-02-28 | 2011 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX0802 | Replace Headquarters Facility - New Cumberland | DDCX0802 | 2011-11-23 | 2012-08-17 | Walsh Construction | W912DR-12-C-011 | 80775 | 82555 | 2012-08-30 | 2016-02-29 | 2015-09-18 | 2016-01-20 | 73%
2015-02-28 | 2011 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC0909 | Replace Fuel Pier - Craney Island | DESC0909 | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | N40085-11-C-0001 | 28815 | 34079 | 2012-11-26 | 2015-04-30 | 2014-07-03 | 2015-04-30 | 90% | 9428 |  | Rescinded by OSD 23 Mar 12 wo# 799865
2015-02-28 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC0503 | Hydrant Fuel System - Misawa AB | DESC0503 | 2012-05-12 | 2012-09-22 | Tokyo Construction Co., Ltd. | W912HV-12-C-0013 | 25204 | 25567 | 2013-02-01 | 2015-03-13 | 2015-02-01 | 2015-03-01 | 98%
2015-02-28 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | UNITED KINGDOM | DESC0905 | Replace Hydrant Fuel System - RAF Mildenhall | DESC0905 | 2011-04-19 | 2011-12-06 | Spiecapag | DEUSFMIL/13232 | 12535.429 | 12535 | 2011-12-09 | 2014-04-25 | 2013-03-14 | 2014-05-02 | 99%
2015-02-28 | 2012 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC1103 | Replace Hydrant Fuel System - Davis Montham AFB | DESC1103 | 2012-05-04 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 18252 | 18534 | 2012-11-13 | 2014-07-23 | 2014-11-03 | 2015-04-01 | 96%
2015-02-28 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1205 | Replace Fuel Facilities - San Clemente Is. | DESC1205 | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453 | 27768 | 2013-02-28 | 2015-03-11 | 2015-03-24 | 2015-07-01 | 69% | 10000 | FY09 Germersheim | 2853 Reprogramming wo# 973902
2015-02-28 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma | DESC0704 | 2008-02-20 | 2012-03-29 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08C-7501 | 15512 | 164864 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2015-02-28 | 2012 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1102 | Public Safety Facility - Tracy | DDCX1102 | 2012-03-06 | 2012-07-16 | MASCON, INC | W91238-12-C-0021 | 14615 | 15091 | 2012-08-29 | 2014-12-05 | 2014-03-24 | 2014-12-07 | 100%
2015-02-28 | 2012 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESI1101 | Alter Warehouse Space - JB PH Hickam | DESI1101 | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | N62478-11-D-4042/0004 | 5500 | 6430 | 2012-08-13 | 2014-09-30 | 2013-06-14 | 2014-04-29 | 99%
2015-02-28 | 2012 | DLA Defense Energy Support Center | Major Military Construction | MASSACHUSETTS | UNITED STATES | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB | DESC1102 | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 24480 | 25378 | 2013-06-18 | 2016-02-08 | 2016-02-02 | 2015-12-10 | 66% | 4500 | FY09 Hill, Hunter & Germersheim | 2853 Reprogramming
2015-02-28 | 2012 | DLA Defense Supply Center Columbus | Major Military Construction | OHIO | UNITED STATES | DSCC1201 | Security Enhancements - Columbus | DSCC1201 | 2012-02-19 | 2012-05-04 | Pinnacle Construction Development Group | W912QR-12-C-0031 | 8550 | 10318 | 2012-06-07 | 2014-09-26 | 2013-09-23 | 2014-09-25 | 99%
2015-02-28 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1203 | Upgrade Access Control Points - New Cumberland | DDCX1203 | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 16327 | 16327 | 2014-02-04 | 2016-09-18 | 2016-03-21 | 2016-03-21 | 8%
2015-02-28 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1202 | Replace General Purpose Warehouse - New Cumberland | DDCX1202 | 2012-09-17 | 2013-11-20 | Corothers Construction Inc. | W912DR-14-C-0005 | 24622 | 24707 | 2014-01-14 | 2015-07-20 | 2015-07-29 | 2015-07-29 | 78% | 3802 | FY 10 Duluth, FY11 Osan | 2853 Reprogramming
2015-02-28 | 2012 | DLA Defense Supply Center Philadelphia | Major Military Construction | PENNSYLVANIA | UNITED STATES | DSCP1201 | Upgrade HVAC System - Philadelphia | DSCP1201 | 2012-03-28 | 2012-06-01 | WU & Associates, Inc. | N40085-10-D-9451 | 4775 | 7240 | 2012-06-14 | 2014-04-29 | 2013-07-17 | 2014-06-06 | 99% |  |  | wo# 971006
2015-02-28 | 2012 | DLA Defense Energy Support Center | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DESC1101 | Replace Fuel Storage Facility - Charleston AFB | DESC1101 | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | N694501-12-C-1757 | 26700 | 26485 | 2012-11-30 | 2014-12-30 | 2014-07-21 | 2014-11-26 | 99% | 5132 | FY10 Pt Loma, FY12 JB PH-Hickam & Barksdale | 2853 Reprogramming wo# 972228
2015-02-28 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WEST VIRGINIA | UNITED STATES | DESC12S1 | Replace Hydrant Fuel System - Camp Dawson | DESC12S1 | 2012-04-26 | 2012-07-05 | Kinley Construction Company | W9128F-10D-0052 | 1930 | 1945 | 2012-07-03 | 2015-09-22 | 2013-12-05 | 2015-07-24 | 99%
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC13S4 | Replace Truck Unload Facility - Yuma | DESC13S4 | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322 | 1454 | 2013-09-30 | 2015-10-11 | 2014-08-03 | 2015-08-03 | 6% | 400 | FY12 Eielson | 2853 Reprogramming wo# 1133398
2015-02-28 | 2013 | DLA Defense Reutilization and Marketing Service | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | DRMS12U2 | Warehouse 6 Distribution - Tracy | DRMS12U2 | 2013-05-01 | 2013-05-15 | Kinley Construction Company | W91238-10-D0036 | 925 | 925 | 2013-06-01 | 2014-09-02 | 2013-12-05 | 2014-09-02 | 100%
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1304 | Replace Fuel Storage - Edwards AFB | DESC1304 | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513 | 19661 | 2013-11-20 | 2017-03-07 | 2016-10-18 | 2016-12-07 | 48%
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC 1306 | Replace Fuel Pier - Pt Loma | DESC 1306 | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378 | 66907 | 2014-01-15 | 2017-10-14 | 2017-10-14 | 2017-10-15 | 34% |  |  | wo# 1124159
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | DELAWARE | UNITED STATES | DESC1305 | Replace Truck Off-Load Facility - Dover AFB | DESC1305 | 2013-07-31 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800 | 1800 | 2013-12-06 | 2015-04-28 | 2015-02-27 | 2015-04-28 | 43%
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1391 | Construct Fuel Storage Facility - Hurlburt AFB | DESC1391 | 2013-01-13 | 2013-08-01 | Nova Group Inc. | W91278-13-C1001 | 15952 | 15952 | 2013-10-31 | 2015-12-18 | 2015-09-14 | 2015-10-04 | 70%
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC1203 | Replace Fuel Pier - GTMO | DESC1203 | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366 | 36366 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-09-28 | 35% |  |  | wo# 1124257
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC13S3 | Replace Truck Loading Facility - GTMO | DESC13S3 | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961 | 1961 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 32% |  |  | wo# 1303226
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | GUAM | GUAM | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB | DESC1303 | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364 | 53367 | 2014-06-30 | 2016-05-11 | 2016-02-06 | 2016-05-11 | 2% |  |  | wo# 1125022
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | LOUISIANA | UNITED STATES | DESC1390 | Upgrade Pumphouse - Barksdale AFB | DESC1390 | 2012-10-30 | 2013-08-13 | Environmental Management Resources | N69450-10-D-0787 | 4311 | 4455 | 2013-09-09 | 2015-02-26 | 2015-02-26 | 2015-02-26 | 88% |  |  | wo# 1123107
2015-02-28 | 2013 | DLA Defense Energy Support Center | Major Military Construction | NORTH CAROLINA | UNITED STATES | DESC13S1 | Replace Transfer Fuel Line to Pump House #2 - Seymour Johnson | DESC13S1 | 2013-02-27 | 2013-07-09 | Shaw Environmental & Infrastructure, Inc. | W9128F-10-D-0073 | 1494 | 1542 | 2013-07-25 | 2014-10-13 | 2014-04-18 | 2014-10-21 | 100%
2015-02-28 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1301 | Replace Communications Building - New Cumberland | DDCX1301 | 2014-04-16 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 6800 | 6800 | 2014-10-10 | 2016-07-27 | 2016-12-02 | 2016-04-28 | 1%
2015-02-28 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland | DDCX1303 | 2013-08-01 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9600 | 9600 | 2014-07-28 | 2016-03-06 | 2016-01-21 | 2016-01-04 | 7% | 5000 | FY10 Pt Loma, GTMO & Souda Bay; FY11 Pt Loma | 2853 Reprogramming
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC14U1 | Upgrades to Fuel Pier for Fire Protection - Pt Loma | DESC14U1 | 2014-06-01 | 2014-07-01 | CB&I Federal Services LLC | N62583-09-D-0130 TO-027 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0% |  |  | wo#1360039
2015-02-28 | 2014 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1404 | General Purpose Warehouse - Tracy | DDCX1404 | 2014-06-23 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 1994 | 1994 | 2014-06-30 | 2016-04-04 | 2015-11-15 | 2016-02-28 | 1%
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City | DESC11U2 | 2014-03-28 | 2014-04-24 | Gilbane Federal | N62583-09-D-0129 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 16% |  |  | wo# 1302082
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1402 | Replace Fuel Pipeline - Jacksonville | DESC1402 | 2014-01-16 | 2014-04-17 | Industrial Power Systems | N69450-14-C-1255 | 5438 | 5438 | 2014-06-30 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 45% |  |  | wo# 1163305
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC1504 | Upgrade Fuel Island - Hunter AAF | DESC1504 | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0001 | 13407 | 13407 | 2014-09-19 | 2016-07-07 | 2016-03-12 | 2016-04-08 | 1%
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC14S2 | Replace Ground Vehicle Fueling Facility - Moody AFB | DESC14S2 | 2014-03-18 | 2014-04-14 | Pond Constructors Inc. | W9128F-14-D-0051 | 3780 | 3780 | 2014-05-15 | 2015-08-05 | 2015-05-15 | 2015-07-06 | 17% |  |  | Additional Funds from FY12 Eielson
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC11U2 | Replace Ground Vehicle Fueling Facility - Atsugi | DESC11U2 | 2014-05-02 | 2014-07-29 | Ichibo Co. Ltd | W912HV-14-C-0002 | 1994 | 1994 | 2014-09-12 | 2015-10-23 | 2015-11-15 | 2015-08-28 | 30%
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW JERSEY | UNITED STATES | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst | DESC1501 | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637 | 8637 | 2014-10-30 | 2016-08-09 | 2016-06-15 | 11 msy 16 | 0%
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NORTH DAKOTA | UNITED STATES | DESC1107 | Replace Fuel Pipeline - Minot AFB | DESC1107 | 2014-02-28 | 2014-06-13 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4092 | 4092 | 2014-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-11 | 1%
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1561 | Replace Refueler Parking, Altus AFB | DESC1561 | 2014-03-10 | 2014-06-12 | Rockford Corporation | W9128F-10-D-0050 | 1917 | 1917 | 2014-07-11 | 2015-09-17 | 2015-09-17 | 2015-08-07 | 24%
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | DESC1502 | 2014-06-09 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0070 | 32060 | 32060 | 2014-12-01 | 2017-09-11 | 2016-06-02 | 2017-05-23 | 0%
2015-02-28 | 2014 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island | DESC1405 | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749 | 8749 | 2014-11-30 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0% |  |  | wo#1140322
2015-03-04 | 2007 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | DS0701 | Replace Ft Knox High School |  | 2007-04-03 | 2007-08-31 | BartonMarlow Company | W912QR-07-C-0059 / 2593359 | 16050 | 16149.241 | 2007-09-17 | 2009-10-08 | 2009-03-10 | 2009-12-04 | 100%
2015-03-04 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  | 2014-12-06 |  | Federal Republic of Germany | W912GB-12-C-0008 / 17387653 | 70600.7618 | 70600.7618 |  |  |  |  | 0%
2015-03-04 | 2010 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM 856 07 | New Elementary School |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764 | 20538.226 | 2012-08-01 | 2014-08-01 | 2013-12-14 | 2014-07-09 | 99%
2015-03-04 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) |  | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | W912GB-08-C-0046 / 14328568 | 15509.459 | 17800 | 2011-05-09 | 2013-09-13 | 2013-01-19 | 2013-09-25 | 99%
2015-03-04 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46694.9233 | 48551 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 68%
[9 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513.9133 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 68%
[9 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 68%
2015-03-04 | 2010 | DoD Education Activity | Major Military Construction |  | BELGIUM | EUR 8318 09 | Replace School (SHAPE ES) |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414.6336 | 33033 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 99%
[9 empty] | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652.1853 | 1719.1947 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
2015-03-04 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School (Boblingen HS) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869.3221 | 44746 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 68%
[9 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 68%
[9 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292.8744 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 68%
2015-03-04 | 2011 | DoD Education Activity | Major Military Construction | NEW YORK | UNITED STATES | AM2455205 | Construct Addition and Renovate West Point MS |  | 2011-07-18 | 2011-10-20 | Bernard Associates | W912DS-12-C-0001 / 25312318 | 23974 | 26115 | 2011-11-28 | 2014-03-17 | 2014-09-28 | 2014-03-17 | 99%
2015-03-04 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) |  | 2012-04-18 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260 | 27072 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 99%
[9 empty] | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843 | 6002 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
[9 empty] | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28674 | 29089 | 2012-08-01 | 2015-02-12 | 2015-01-13 | 2015-02-12 | 96%
2015-03-04 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM8193 01 | Replace Elementary School (Antilles ES) |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968 | 51394 | 2012-07-18 |  | 2014-04-19 | 2015-09-30 | 66%
2015-03-02 | 2011 | DoD Education Activity | Major Military Construction | VIRGINIA | UNITED STATES | AM2455206 | Replace/Consolidate Elementary Schools |  | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297 | 43453 | 2012-09-29 |  | 2014-09-30 | 2015-06-01 | 98%
2015-03-04 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM100801 | Replace Elementary School (Murray ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121826 | 14851 | 16469 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 99%
2015-03-04 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AMD02051 | Replace Elementary School ( McNair ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121890 | 16413 | 17205 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 99%
2015-03-04 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB |  | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | W912HV-13-C-0002 / 29312081 | 9644 | 9773 | 2013-03-26 |  | 2015-07-25 | 2015-10-18 | 74%
2015-03-04 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00053 | Replace Elementary/Middle School (Ansbach EMS) |  | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 575 | 575 | 2013-10-28 |  | 2015-03-12 | 2015-06-15 | 46%
[9 empty] | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11783.7717 | 11873 | 2013-10-28 |  | 2015-03-12 | 2015-06-15 | 46%
2015-03-04 | 2012 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00020 | Replace Elementary School (Osan ES) |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187 | 29897 | 2013-09-30 |  | 2015-12-09 | 2016-03-01 | 29%
2015-03-04 | 2013 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00023 | Replace McBride Elementary School |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987 | 32987 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 33%
[9 empty] | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 33%
2015-03-04 | 2013 | DoD Education Activity | Major Military Construction | MASSACHUSETTS | UNITED STATES | AM00027 | Replace Hanscom Middle School |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 32260 | 33084 | 2014-02-11 |  | 2016-04-21 | 2016-08-19 | 29%
2015-03-04 | 2013 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00028 | Replace Barkley Elementary School |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39362 | 39666 | 2014-03-27 |  | 2015-12-17 | 2016-03-15 | 20%
2015-03-04 | 2012 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00026 | Replace Kingsolver/Pierce School |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685 | 32932 | 2014-03-11 |  | 2015-11-11 | 2016-01-30 | 11%
2015-03-04 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School |  | 2014-10-21 | 2014-03-07 | Federal Republic of Germany | W912GB-12-C-0007 / 33867035 | 0 | 0 | 2014-03-24 | 2014-08-11 | 2014-08-21 | 2014-08-30 | 13%
[9 empty] | 2014-10-21 | 2014-06-20 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 662 | 954 | 2014-10-06 |  | 2014-12-08 | 2015-04-29 | 13%
[9 empty] | 2014-10-21 |  | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 48983 | 49115 |  |  | 2017-06-20 | 2017-07-20 | 0%
2015-03-02 | 2012 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00025 | Replace Delalio Elementary School |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339 | 23918 | 2014-02-24 | 2016-06-01 | 2016-06-01 | 2017-05-20 | 31% |  |  | The occupancy date 1 Jun 16 is for the BOD of the school. This is the completion of Phase 1 of the project. The school can be occupied at this time. The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2015-03-04 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475 | 1475 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 4%
[9 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469 | 2469 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 4%
[9 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612 | 4612 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 4%
[9 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418 | 62521 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 4%
2015-03-04 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00062 | Netzaberg Middle School Addition |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 283 | 283 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 28%
[9 empty] | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366 | 5427 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 28%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00024 | Faith Middle School Addition |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4897 | 4897 | 2014-10-28 |  | 2016-01-21 | 2016-04-20 | 4%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00040 | Replace Marshall Elementary School |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 34748 | 34851 | 2014-08-06 |  | 2016-03-28 | 2016-05-27 | 14%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00038 | Diamond Elementary School Replacement |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40073 | 39854 | 2014-10-15 |  | 2016-09-14 | 2016-12-13 | 1%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00018 | Daegu Middle/High School Replacement |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28954 | 28954 | 2014-09-29 |  | 2016-10-03 | 2016-12-10 | 3%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00030 | Replace Zukeran Elementary School |  | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476 | 95476 | 2014-10-23 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 1%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00050 | White Elementary School Replacement |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791 | 31791 | 2014-12-16 |  | 2016-10-31 | 2017-01-29 | 0%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00034 | Replace Fort Campbell High School |  | 2014-06-20 | 2014-10-31 | Walsh Group Ventures | W912QR-15-C-0001 | 55931 | 55931 |  |  | 2017-04-29 | 2017-04-29 | 0%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00031 | Pope Holbrook Elementary School |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278-12-D-0039 | 32124 | 32124 | 2015-02-11 |  | 2017-02-10 | 2017-05-11 | 0%
2015-03-02 | 2014 | DoD Education Activity | Major Military Construction | SOUTH CAROLINA | UNITED STATES | AM00037 | Replace Bolden-Galer Elementary School |  | 2014-07-25 | 2014-12-19 | Elkins Constructors, Inc. | N6945015C1606 | 35705 | 35705 |  |  | 2017-01-11 | 2017-10-31 | 1%
2015-03-04 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00027 | Replace Yokota High School |  | 2014-07-25 | 2014-12-24 | Daiwa Odakyu Construction - JDC JV | W912HV-15-C-0002 | 40547 | 40547 |  |  | 2019-03-23 | 2019-03-23 | 0%
2015-03-04 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00035 | Kadena Middle School Addition/Renovation |  | 2014-09-23 | 2015-02-18 | Nippo Corporation | W912HV-15-C-0003 / 34596540 | 31459 | 31459 |  |  | 2016-10-16 | 2016-10-16 | 0%
2015-02-28 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P646 | DSS Headquarters Addition |  | 2012-09-21 | 2013-03-29 | Hensel Phelps Construction Co. |  | 25149 | 28544 | 2013-04-30 | 2014-09-26 | 2014-07-22 | 2015-01-09 | 99% |  |  | [Solicitation/Advertise Date: Phase I - 21-Sep-2012 Phase II - 20-Dec-2012]
2015-02-28 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P659 | Defense Access Road Improvements-Telegraph Rd |  | 2013-01-22 | 2013-07-15 | Shirley Contracting Company, LLC |  | 2967 | 2967 | 2013-08-01 |  | 2014-08-01 | 2015-05-15 | 81% |  |  | This project is being managed and funded via FHWA. [Solicitation/Advertise Date: Phase I - 22-Jan-2013 Phase II - 04-Apr-2013] - UPDATE: The discovery of two underground storage tanks delayed the completion of the new storm drain system. Final paving activities may need to be delayed until Spring 2015 for a winter shutdown period.
2015-02-28 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 655 | Missile Test Vehicle Storage Facility |  | 2014-03-24 | 2014-05-09 | Arctic Slope Regional Corporation (ASRC) | W912DY-14-D-0042-0001 | 1832 | 1832 | 2014-06-17 | 2014-12-19 | 2014-12-11 | 2014-12-28 | 100% |  |  | Awaiting Interim 1354
2015-02-28 | 2010 | Missile Defense Agency | Major Military Construction | HAWAII | UNITED STATES | 627 | Aegis Ashore Missile Defense Test Complex |  | 2011-06-30 | 2011-08-03 | TOMCO CORP. | N62478-10-D-4024 | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 100% |  |  | Clearing and Grubbing Only
[9 empty] | 2012-01-19 | 2012-06-04 | URS GROUP, INC | N62742-09-D-1174 | 59616 | 69657 | 2012-07-04 | 2013-08-29 | 2013-09-12 | 2013-11-07 | 100% |  |  | GMAC Construction - awaiting Interim 1354
2015-02-28 | 2012 | Missile Defense Agency | Major Military Construction | ALABAMA | UNITED STATES | 633 | Von Braun Complex Phase IV |  | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | W91278-12-C-0017 | 51330 | 59842 | 2012-07-10 | 2014-06-26 | 2014-07-10 | 2014-10-15 | 100% |  |  | Awaiting Final 1354
2015-02-28 | 2013 | Missile Defense Agency | Major Military Construction | NEW YORK | UNITED STATES | 639 | In-Flight Interceptor Data Terminal Complex |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584 | 15270 | 2013-08-10 | 2015-02-04 | 2014-11-28 | 2015-03-28 | 98% |  |  | Awaiting Final 1354
2015-02-28 | 2013 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 109373 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 53% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2015-02-28 | 2014 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 646 | Aegis Ashore Missile Defense System Complex, Incr #2 | 1901-09-21 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 33569 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 53% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2015-02-28 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300 | 13300 | 2014-07-07 |  | 2016-01-06 | 2016-01-06 | 46% |  |  | Awaiting Interim 1354
2015-02-28 | 2014 | Missile Defense Agency | Major Military Construction |  | JAPAN | 648 | AN/TPY-2 Radar Site |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991 | 12991 | 2014-05-27 | 2015-02-03 | 2015-01-09 | 2015-02-20 | 100% |  |  | Site Identifier is pending as this is a new Installation.
2015-02-28 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838 | 42838 | 2014-05-27 |  | 2016-05-31 | 2016-05-31 | 17% |  |  | Construction suspended for Winter; Awaiting Interim 1354
2015-02-28 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | MISSOURI | UNITED STATES | NGA021 | Data Ctr West #1 Power & Cooling Upgrade |  | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors |  | 8202 | 11198 | 2012-08-06 | 2014-01-21 | 2013-08-06 | 2015-01-31 | 99% |  |  | Technology Center Third Floor Fit-out - project period of performance extended to 31 May 2015 ["N/A" for Diverted Funds Amount]
2015-02-28 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | NGA013 | Technology Center Third Floor Fit-out |  | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 32387 | 39495 | 2012-11-02 | 2014-05-30 | 2014-01-02 | 2015-01-31 | 99% | 1975 | NGA021 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 30 September 2015
2015-02-28 | 2007 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES |  | Infrastructure Increments 1-3; NGA HQ's | [8 empty] | 2011-09-15 | 2013-06-15 | 31-Apr-2015 | 99% |  |  | ["Various" for Solicitation Date, Award Date, Start Date, Prime Contract Recipient (Company Name); "N/A" for Original Contract Amount, Current Contract Obligation, Diverted Funds Amount]
2015-02-28 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 65416 | NGA Headquarters, SCIF, All Phases |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 1181439 | 1398710 | 2007-09-06 | 2011-04-19 | 2011-12-22 | 31-Apr-2015 | 99% |  |  | ["N/A" for Diverted Funds Amount]
2015-02-28 | 2009 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060 | 13760 | 2010-09-21 | 2013-01-17 | 2013-01-17 | 2014-04-18 | 99%
2015-02-28 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223 | 126372 | 2010-09-21 | 2015-10-12 | 2014-04-18 | 2015-10-12 | 96% | 37500
2015-02-28 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443 | 4544 | 2010-09-09 | 2012-06-29 | 2011-09-26 | 2012-06-29 | 100%
2015-02-28 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253 | 5787 | 1915-11-09 | 2014-11-30 | 2014-03-07 | 2014-12-09 | 98%
2015-02-28 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17781 | Tordella Chilled Water Backup Storage |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700 | 11700 | 2010-06-30 | 2012-05-30 | 2011-08-20 | 2012-05-30 | 100%
2015-02-28 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17782 | R&E Chilled Water Backup Storage |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200 | 3200 | 2011-11-07 | 2014-10-31 | 2013-07-13 | 2015-07-31 | 78% |  |  | Due to problems with Commissioning of chiller plant the tank has been pushed out to Aug 2015
2015-02-28 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18052 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566 | 8257 | 2011-03-31 | 2014-05-14 | 2013-02-01 | 2014-05-14 | 100%
2015-02-28 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18053 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095 | 16448 | 2012-01-31 | 2014-05-31 | 2013-02-01 | 2014-05-31 | 100%
2015-02-28 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18054 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085 | 7316 | 2012-11-30 | 2014-08-31 | 2013-02-01 | 2014-08-31 | 92% |  |  | Commissioning of system completed November 26, 2014.
2015-02-28 | 2011 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900 | 130106 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-10-31 | 99.1% | 54500 | Mountainview, South Campus Electrical Utility Plant
2015-02-28 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 | MOD II |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657 | 8867 | 2012-05-30 | 2014-03-03 | 2014-01-30 | 2015-01-16 | 100%
[7 empty] | MOD II (Phase 2) |  | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620 | 2657 | 2013-11-26 | 2014-09-30 | 2014-02-28 | 2014-04-28 | 98%
[7 empty] | Whitelaw Wedge |  | 2012-04-26 | 2012-06-18 | JAAT | W912HN-10-D-0063 | 15315 | 16526 | 2012-07-18 | 2014-07-09 | 30-Ja n-14 | 2014-10-23 | 95%
2015-02-28 | 2012 | National Security Agency | Major Military Construction | COLORADO | UNITED STATES | 23051 | Mountainview |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975 | 127132 | 2012-11-02 | 2015-08-30 | 2015-05-03 | 2015-05-28 | 93%
[7 empty] | Mountainview |  | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621 | 5627 | 2013-10-13 | 2014-04-30 | 2014-02-14 | 2015-09-30 | 100%
2015-02-28 | 2012 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 24649 | High Performance Computing Center 2 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589 | 589524 | 2013-03-12 | 2015-09-30 | 2015-09-15 | 2015-10-20 | 83% |  |  | Implementation of a client-related change extended contract completion date.
2015-02-28 | 2013 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 26170 | East Campus Building 1 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91866 | 94216 | 2013-10-24 | 2016-01-05 | 2015-10-11 | 2015-10-11 | 21% |  |  | February totals reflect auto accurals
2015-02-28 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | 61772 | Operations Complex |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30155148 | 16751 | 17554.9517 | 2012-01-31 | 2014-12-03 | 2013-04-25 | 2014-12-31 | 98%
2015-02-28 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033003 | Vehicle Maintenance Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30136034 | 4575 | 5123.2845 | 2012-01-31 |  | 2013-04-25 | 2015-03-15 | 98%
2015-02-28 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033005 | Storage Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154837 | 3603 | 3766.2116 | 2012-01-31 |  | 2013-04-25 | 2014-12-31 | 98%
2015-02-28 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033019 | Air Operations Center |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154494 | 2931 | 3078.5666 | 2012-01-31 | 2014-12-03 | 2013-04-25 | 2014-12-31 | 98%
2015-02-28 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64484 | Operations Additions |  | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | W912HN-11-C-0010 / 29379991 | 13388 | 15582 | 2011-08-25 |  | 2014-06-10 | 2015-09-06 | 93%
2015-02-28 | 2011 | Special Operations Command | Major Military Construction | GEORGIA | UNITED STATES | 65395 | Company Support Facility |  | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391.578 | 15637.173 | 2011-12-27 | 2014-05-30 | 2013-06-19 | 2014-07-31 | 99%
2015-02-28 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 66362 | C4 Facility - JSOC |  | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | W912HN-12-C-0009 / 29381338 | 41446 | 44329 | 2012-06-14 |  | 2014-01-31 | 2015-06-16 | 100%
2015-02-28 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69573 | Admin/Company Operations |  | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN-10-D-0058 / 29381912 | 8487 | 9166 | 2011-10-27 | 2013-11-21 | 2013-04-18 | 2013-11-21 | 99%
2015-02-28 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063049 | Hangar / AMU (MC-130J) |  | 2011-05-13 | 2011-09-09 | Speegle Construction | W912PP-11-C-0029 / 30594756 | 19432 | 20310.9637 | 2011-10-11 | 2014-05-02 | 2013-12-01 | 2014-05-02 | 99%
2015-02-28 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13613.73 | 13829.0421 | 2012-09-06 | 2014-06-03 | 2013-07-17 | 2014-06-03 | 99% | 7132 | 66362
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60272 | Communications Training Complex (SWCS) |  | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN-10-D-0049 / 29371639 | 8290.317 | 41066 | 2012-09-12 |  | 2014-03-06 | 2015-02-15 | 97%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60821 | Squadron Headquarters Addition |  | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN-10-D-0060 / 29389201 | 10605 | 10926 | 2012-06-06 |  | 2014-06-06 | 2015-07-04 | 97%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66598 | Rotary Wing Hangar |  | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350 | 35208.168 | 2012-04-16 |  | 2014-02-15 | 2015-04-15 | 95%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69458 | Battalion Operations Complex |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772.305 | 16772.305 | 2012-12-10 |  | 2014-06-03 | 2015-05-14 | 71%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69758 | Brigade Headquarters |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 15649.974 | 16280.6264 |  |  | 2014-05-08 | 2015-10-31 | 56%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525.847 | 18786 | 2012-11-07 |  | 2014-05-01 | 2015-05-16 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41071297 | 4506.8515 | 4506.8515 | 2012-11-07 |  | 2015-03-01 | 2015-05-16 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 76363 | Company Operations Facility |  | 2012-04-18 | 2012-08-30 | Adept-Absher 1 Joint Venture | W912DW-12-C-0037 / 27917342 | 18751 | 19630 | 2014-06-20 | 2014-06-20 | 2014-04-01 | 2014-06-21 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76364 | Battalion Operations Facility |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201.3031 | 33435.0071 | 2012-12-04 |  | 2014-08-26 | 2015-06-01 | 76%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76366 | Company Operations Facility (GSTB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673.727 | 15674.302 | 2012-09-12 |  | 2015-09-12 | 2016-04-26 | 83%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76371 | Company Operations Facility (GSB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092.801 | 17144 | 2012-09-12 |  | 2015-09-12 | 2016-04-26 | 83%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 76374 | MH-47 Hangar |  | 2011-11-28 | 2012-05-07 | Hensel Phelps Construction Co. | W912QR-12-C-0035 / 28427841 | 32450 | 34200 | 2014-08-27 | 2014-08-27 | 2014-03-23 | 2014-08-29 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073014 | SOF C-130 Sq Ops Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 25127091 | 7413 | 7874.8241 | 2014-07-11 | 2014-07-11 | 2014-02-22 | 2014-07-11 | 100%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073018 | SOF C-130 Wash Rack Hangar |  | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | W912PP-12-C-0025 / 30667913 | 9329 | 9703.7394 | 2014-09-09 | 2014-09-09 | 2014-04-10 | 2014-08-29 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073021 | SOF AMXS Facility |  | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | W912PP-12-C-0033 / 25138433 | 14700 | 14966.2684 | 2013-01-10 | 2014-09-22 | 2014-12-22 | 2014-09-19 | 100%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083012A | SOF Hangar/AMU |  | 2012-04-20 | 2012-08-31 | Hensel Phelps | W912PP-12-C-0027 / 30858121 | 28160 | 29105.547 | 2012-10-24 | 2014-10-02 | 2014-12-23 | 2014-09-07 | 100%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083016 | SOF Squadron Operations Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 28791332 | 10615 | 11040 | 2012-11-09 | 2014-05-30 | 2015-01-06 | 2014-05-30 | 100% | 2293 | CZQZ063035
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV103011 | SOF Simulator Facility |  | 2012-05-01 | 2012-08-09 | Barlovento LLC. | W91278-10-D-0072 | 5551 | 5543 | 2012-09-13 | 2014-07-18 | 2013-12-24 | 2014-07-18 | 100%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1049 | Range 130 Support Projects |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129 | 8587 | 2013-06-03 |  | 2014-11-13 | 2015-11-20 | 16%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1174 | MWD Facility |  | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | N6247311D0068 #0003 | 3075 | 3304 | 2012-10-03 | 2014-11-14 | 2014-03-23 | 2014-11-14 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-164 | Logistics Support Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727 | 11727 | 2012-12-09 |  | 2014-07-24 | 2015-06-16 | 85%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-473 | SEAL Team Operations Facility |  | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366 | 27062 | 2014-08-13 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 31%
2015-02-28 | 2012 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-504 | SOF Operational Vehicle Storage Facility (6UMC) |  | 2013-03-12 | 2013-05-23 | Richard Brady & Associates, Inc. | N4008511D6591 #0010 | 1660 | 1730 | 2013-12-03 | 2015-04-18 | 2014-10-20 | 2015-01-15 | 86%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | ALASKA | UNITED STATES | P-531 | Cold Weather Maritime Training Facility |  | 2012-04-30 | 2012-09-27 | Alutiiq Diversified Service, LLC | N4425512C3011 | 17449 | 17449 | 2014-03-04 |  | 2015-04-15 | 2015-04-15 | 95%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-769 | Building Renovation |  | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022 | 3968 | 2013-01-02 | 2014-08-27 | 2014-06-27 | 2014-10-26 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-826 | Military Working Dog Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139 | 4139 | 2012-12-09 |  | 2014-07-24 | 2014-07-24 | 99%
2015-02-28 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH043055 | SOF Training Facility |  | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN-10-D-0063 / 25189640 | 4773.799 | 4752.7374 | 2012-05-31 | 2014-10-29 | 2013-11-22 | 2014-11-12 | 100%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | ARIZONA | UNITED STATES | 53542 | Parachute Training Facility |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546.92 | 6546.92 | 2014-11-09 |  | 2016-05-09 | 2016-05-07 | 2%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 65052 | Medical Support Addition |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199.999 | 3272 | 2013-10-16 | 2015-01-23 | 2015-08-25 | 2015-04-17 | 92%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66597 | Landgraf Hangar Extension |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384.894 | 3384.894 | 2014-04-29 |  | 2015-10-21 | 2015-11-20 | 13%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287a | Battalion Operations Complex |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907.435 | 30907.435 | 2013-10-09 |  | 2015-05-13 | 2015-12-23 | 39%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287b | Battalion Operations Complex |  |  | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404 | 23709 | 2014-11-20 |  |  | 2016-11-01 | 3%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69382 | Civil Affairs Battalion Complex |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816 | 25808 | 2013-10-16 |  | 2015-08-14 | 2015-11-12 | 46%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 69447 | Group Support Battalion Detachment |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123.1802 | 22427 | 2014-04-14 |  | 2016-02-13 | 2016-02-13 | 24%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69493 | Sustainment Bde Headquarters |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085 | 23085 | 2014-06-18 |  | 2016-05-02 | 2016-10-14 | 14%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 76367 | SOF Battalion Operations Complex |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441 | 36544 | 2014-09-04 |  | 2016-06-16 | 2016-10-01 | 1%
2015-02-28 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 79655 | SOF Training Facility (4UMC) |  | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | W912PM-13-C-0003 | 1592 | 1608 | 2013-06-18 | 2014-10-01 | 2014-10-15 | 2014-08-21 | 100%
2015-02-28 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 80233 | SOF Live-Fire Training Tower (6UMC) |  | 2013-06-16 | 2014-01-22 | Trend Construction, Inc. | W912HN-12-D-0030-DQ04 | 1531.7653 | 1570 | 2014-02-12 | 2015-03-04 | 2015-05-15 | 2015-03-04 | 95%
2015-02-28 | 2013 | Special Operations Command | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81483 | Mtn Climb/Rappel Tower (5UMC) |  | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F-13-C-0006 | 1513 | 1628 | 2013-09-20 | 2014-11-26 | 2014-10-15 | 2014-11-26 | 99%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083013 | Combat Parking Apron |  | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP-14-C-0014 / 32077093 | 19481.9877 | 19500 | 2014-06-13 |  | 2015-08-13 | 2016-02-20 | 79%
2015-02-28 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NEW MEXICO | UNITED STATES | CZQZ100221 | Parachute Drying Tower (3 UMC) |  | 2014-03-06 | 2014-07-01 | Speegle Construction | W912PP-14-C-0017 / 39136021 | 1547 | 1572 | 2014-07-28 |  | 2015-05-24 | 2015-05-24 | 44%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTFA113004 | SOF AvFID Ops and MX Facilities |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942.3 | 30051 | 2013-11-05 |  | 2016-12-01 | 2017-04-14 | 44%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | NVZR083702 | Joint Special Operations University Facility |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753.0246 | 25246 | 2013-11-04 |  | 2015-09-15 | 2016-01-07 | 35%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1218 | Marine Battalion Company/Team Facilities |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46370 | 2014-02-20 |  | 2016-03-01 | 2016-01-18 | 49%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1393 | Survival Evasion Resistance Escape Trng Fac |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46389 | 2014-02-20 |  | 2016-01-18 | 2016-01-18 | 49%
2015-02-28 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1410 | SOF EOD Expansion (1UMC) |  | 2013-09-04 | 2013-09-26 | Quadrant Construction, Inc | N4008510D0261 #0017 | 1566 | 1566 | 2013-10-15 | 2015-01-31 | 2014-09-22 | 2014-09-22 | 93%
2015-02-28 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1450 | Fires Platoon Storage Facility (7UMC) |  | 2013-12-20 | 2014-02-13 | Quadrant Construction, Inc | N4008510D0261 #0019 | 1459.25 | 1469 | 2014-03-13 |  | 2014-12-13 | 2015-03-04 | 54%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-165 | CS/CSS Support Facility |  | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351 | 9915 | 2014-10-06 |  | 2015-09-09 | 2015-11-26 | 56%
2015-02-28 | 2013 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-564 | NSWG-4 Paraloft Addition (2UMC) |  | 2013-06-14 | 2013-09-27 | Royce Homeland JV, LLC | N4008512D6305 #0005 | 1308 | 1319 | 2013-10-15 |  | 2014-12-31 | 2014-12-31 | 72%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-876 | Indoor Dynamic Shooting Facility |  |  | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290 | 24440 |  |  | 2016-10-01 | 2016-10-07 | 4%
2015-02-28 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-888 | Close Quarters Combat Range, Phase II |  |  | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489 | 12489 |  |  | 2016-09-30 | 2016-09-30 | 3%
2015-02-28 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 61064 | SOF Upgrade Training Facility |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951 | 13951 | 2014-11-17 |  | 2016-08-18 | 2016-10-13 | 1%
2015-02-28 | 2014 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 69446 | Group Support Battalion Detachment |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083.965 | 15083.965 | 2014-08-27 |  | 2016-02-18 | 2016-04-20 | 5%
2015-02-28 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76375 | Civil Affairs Battalion Annexes |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358 | 27358 | 2014-11-14 |  | 2016-07-12 | 2017-01-19 | 3%
2015-02-28 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76376 | Language and Cultural Center |  |  | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696.6683 | 51696.6683 | 2015-01-09 |  |  | 2018-01-15 | 0%
2015-02-28 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 79438 | Combat Medic Skills Sustainment Course Bldg |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193.631 | 7193.631 | 2014-10-27 |  | 2016-08-01 | 2016-10-13 | 1%
2015-02-28 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV083002 | Add/Alter Operations Facility |  | 2014-05-26 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048.867 | 7048.867 | 2014-09-02 |  | 2016-08-03 | 2016-08-22 | 3%
2015-02-28 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1391 | SOF Sustainment Training Complex |  | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333 #0004 | 27546.924 | 27546.924 |  |  | 2016-09-02 | 2016-09-02 | 8%
2015-02-28 | 2014 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1469 | MSOB Support Facilities |  | 2014-08-20 | 2014-09-30 | Quadrant Construction, Inc | N4008510D0261/0022 | 1751.362 | 1751.362 |  |  | 2015-09-25 | 2015-09-25 | 0%
2015-03-04 | 2010 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Upgrade Electrical System |  | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power |  | 23269 | 23912 | 2013-11-07 | 2015-06-01 | 2015-02-05 | 2015-06-01 | 12% | 0 |  | Design/Build - 100% design in progress
2015-03-04 | 2011 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Power Plant Modernization Phase 3 (WPP) |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. |  | 43594 | 44791 | 2013-04-22 | 2016-06-30 | 2016-05-11 | 2016-06-30 | 31% | 4001 | Budget Sequester | Project at 100% design, funds reduced by sequester
2015-03-04 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Metro Entrance Facility/Visitor Screening Facility |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. |  | 5609 | 5804 | 2013-11-01 | 2015-06-01 | 2015-06-01 | 2015-06-01 | 20% | 0 |  | Design/Build - Not affected by sequester
2015-03-04 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Secure Access Lane (SAL) |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC |  | 5454 | 5454 | 2013-11-01 | 2015-10-01 | 2015-05-01 | 2015-10-01 | 5% | 0 |  | Award Contract Base Bid Items 28 Sep 2013; All options, for DIACAP $31,093, Perimeter Fence and 3 Vehicle Gates $138,693 and Public Rest Room (OPA funded) $447,766 awarded; NTP estimated by 1 Feb 2013. 510 cds contract duration.
2015-03-04 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Heliport Control Tower/Fire Station | [12 empty] | 798 | Budget Sequester | In 35% design.
2015-03-04 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Memorial Plaza | [12 empty] | 176 | Budget Sequester | Design contract award 26SEP13. NTP 1 Nov13. Design 8 mos/Construct 12mos. Contract duration 540 cds

## DETAILED EXPENDITURES
Data as of Date | Fiscal Year | Component | Appropriation Fund Type | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Current Expenditure Amount ($000) | Remarks
2015-02-28 | 2006 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773.86 | 281843.8046 | 281662.8729
2015-02-28 | 2006 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782.96 | 26642.0458 | 26416.375
2015-02-28 | 2006 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 65283.948 | 58292.3489 | 57489.3337
2015-02-28 | 2006 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15769.71 | 15283.0716 | 15073.8774
2015-02-28 | 2006 | Air Force Reserve | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289.57 | 5289.1201 | 5289.1201
2015-02-28 | 2006 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960 | 3959.9996 | 3959.9996
2015-02-28 | 2006 | Air National Guard | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006 | 28018.597 | 28018.597
2015-02-28 | 2006 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882 | 6882 | 6882
2015-02-28 | 2007 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232 | 329306.4785 | 329274.3414
2015-02-28 | 2007 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12896.1514 | 12677.2917
2015-02-28 | 2007 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 76246 | 75165.3921 | 74320.8576
2015-02-28 | 2007 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14163.2777 | 14163.2777
2015-02-28 | 2007 | Air Force Reserve | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109 | 5072.4629 | 5072.4629
2015-02-28 | 2007 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477 | 4476.9716 | 4476.9716
2015-02-28 | 2007 | Air National Guard | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050 | 19043.34 | 19043.3394
2015-02-28 | 2007 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000 | 5999.9999 | 5999.9999
2015-02-28 | 2008 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 259262 | 238592.895 | 229116.7517
2015-02-28 | 2008 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12161.823 | 12161.823
2015-02-28 | 2008 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 51202 | 42706.692 | 42319.2358
2015-02-28 | 2008 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14081.4775 | 13525.7208
2015-02-28 | 2008 | Air Force Reserve | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300 | 5270.7978 | 5270.7978
2015-02-28 | 2008 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909 | 4909 | 4909
2015-02-28 | 2008 | Air National Guard | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721 | 10619.0353 | 10619.0353
2015-02-28 | 2008 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184 | 14183.984 | 14173.9844
2015-02-28 | 2009 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513.728 | 207279.1631 | 171416.5029
2015-02-28 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing; Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - P.L. 111-5) | 609075 | 608958 | 608958
2015-02-28 | 2009 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703 | 7559.9996 | 7524.9478
2015-02-28 | 2009 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105196.1872 | 103703.1322 | 102223.7475
2015-02-28 | 2009 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14858.0376 | 14375.3953
2015-02-28 | 2009 | Air Force Reserve | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165 | 6133.5834 | 6123.2565
2015-02-28 | 2009 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443 | 5442.927 | 5442.927
2015-02-28 | 2009 | Air National Guard | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056 | 19056 | 18961.6956
2015-02-28 | 2009 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243 | 34163.725 | 34044.0379
2015-02-28 | 2010 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558 | 59491.5566 | 59488.5618
2015-02-28 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 529950 | 510499 | 508572
2015-02-28 | 2010 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302 | 1440.5783 | 1396.5783
2015-02-28 | 2010 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations ; Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 112785 | 108730.5242 | 106164.9873
2015-02-28 | 2010 | Air Force Active | Unspecified Minor Military Construction [UMMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a).; Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 35000 | 31961.0229 | 31452.6645
2015-02-28 | 2010 | Air Force Reserve | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139 | 8001.7193 | 3147.4819
2015-02-28 | 2010 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 752.8898 | 752.8898 | 752.8898
2015-02-28 | 2010 | Air National Guard | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670.441 | 19574.2109 | 19393.8035
2015-02-28 | 2010 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913.559 | 44875.1933 | 38526.4579
2015-02-28 | 2011 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192.95 | 53621.2454 | 41997.1119
2015-02-28 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 544424 | 514017 | 512601
2015-02-28 | 2011 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153 | 3921.568 | 3915.9807
2015-02-28 | 2011 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations; Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 66525.328 | 63186.8771 | 59165.6918
2015-02-28 | 2011 | Air Force Active | Unspecified Minor Military Construction [UMMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a).; Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 67548 | 56811.4706 | 42323.7713
2015-02-28 | 2011 | Air Force Reserve | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649.694 | 1521.061 | 1521.061
2015-02-28 | 2011 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2745.819 | 2728.9494 | 2651.5972
2015-02-28 | 2011 | Air National Guard | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195.572 | 8638.9962 | 8568.8521
2015-02-28 | 2011 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984 | 7751.361 | 5923.9799
2015-02-28 | 2012 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407 | 21868.2641 | 21038.5249
2015-02-28 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 448450 | 434099 | 428829
2015-02-28 | 2012 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056 | 4025.1857 | 4025.1857
2015-02-28 | 2012 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 78413 | 71834.5008 | 64936.6779
2015-02-28 | 2012 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 19844.5595 | 19492.0296 | 14665.318
2015-02-28 | 2012 | Air Force Reserve | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200 | 2059.7994 | 1523.6497
2015-02-28 | 2012 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4594.3732 | 4216.3096 | 3318.0142
2015-02-28 | 2012 | Air National Guard | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225 | 12010.566 | 11418.4182
2015-02-28 | 2012 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000 | 8703.5979 | 4798.5198
2015-02-28 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936.577 | 2584.4897 | 1188.7813
2015-02-28 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 468478 | 444703 | 410246
2015-02-28 | 2013 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 493.638 | 0 | 0
2015-02-28 | 2013 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 410.408 | 367.934 | 156.4243
2015-02-28 | 2013 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5037.9988 | 3990.2267 | 1523.4505
2015-02-28 | 2013 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875.201 | 1555.8376 | 500.798
2015-02-28 | 2013 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997.361 | 355.6 | 6.531
2015-02-28 | 2013 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994.721 | 3616.4187 | 2842.705
2015-02-28 | 2013 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892.214 | 4099.1316 | 971.7574
2015-02-28 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093 | 40753.6909 | 219.9159
2015-02-28 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 399595 | 313955 | 208277
2015-02-28 | 2014 | Air Force Active | Planning and Design - Military Family Housing [MFH P&D] | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267 | 0 | 0
2015-02-28 | 2014 | Air Force Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314 | 9896.9773 | 8038.3543
2015-02-28 | 2014 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448 | 0 | 0
2015-02-28 | 2014 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229 | 0 | 0
2015-02-28 | 2014 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530 | 0 | 0
2015-02-28 | 2014 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400 | 5212.7589 | 1117.1279
2015-02-28 | 2014 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000 | 2186.0607 | 29.1652
2015-02-28 | 2015 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 352062 | 59.493 | 1.182
2015-02-28 | 2015 | Air Force Active | Planning and Design | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 10738 | 0 | 0
2015-02-28 | 2015 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22613 | 0 | 0
2015-02-28 | 2015 | Air Force Reserve | Planning and Design | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892 | 0 | 0
2015-02-28 | 2015 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400 | 0 | 0
2015-02-28 | 2015 | Air National Guard | Planning and Design | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700 | 0 | 0
2015-02-28 | 2015 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6100 | 0 | 0
2015-02-28 | 2009 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000 | 24000
2015-02-28 | 2009 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 21855 | 21855 | 21855
2015-02-28 | 2009 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 219462 | 217314
2015-02-28 | 2009 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 576 | 576 | 524
2015-02-28 | 2009 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28750 | 28278 | 26010
2015-02-28 | 2010 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000 | 25000
2015-02-28 | 2010 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 28393 | 28392 | 28387
2015-02-28 | 2010 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 60100 | 15687 | 15686
2015-02-28 | 2010 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250437 | 247549
2015-02-28 | 2010 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 3936 | 3935 | 2503
2015-02-28 | 2010 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 31250 | 31149 | 29907
2015-02-28 | 2011 | Army Active | Host Nation Support [HNS] | $29,944 Appropriated + $13,000 ATR Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 42944 | 42933 | 42905
2015-02-28 | 2011 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 37328 | 37328 | 37311
2015-02-28 | 2011 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 78330 | 1274 | 1274
2015-02-28 | 2011 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 308676 | 263029 | 256374
2015-02-28 | 2011 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 2036 | 1990 | 1367
2015-02-28 | 2011 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28704 | 26460 | 26424
2015-02-28 | 2012 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR + $9,000 ATR | 36000 | 35238 | 34592
2015-02-28 | 2012 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 34342 | 34265 | 34263
2015-02-28 | 2012 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 192299 | 182022
2015-02-28 | 2012 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 7897 | 7551 | 7165
2015-02-28 | 2012 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 20000 | 19043 | 17019
2015-02-28 | 2013 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954 | 33856 | 32751
2015-02-28 | 2013 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 28124 | 27932 | 27857
2015-02-28 | 2013 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46112 | 45358 | 42184
2015-02-28 | 2013 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 4635 | 778 | 776
2015-02-28 | 2013 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 23595 | 16334
2015-02-28 | 2014 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000 | 22808 | 21573
2015-02-28 | 2014 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 21949 | 20180 | 17052
2015-02-28 | 2014 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575 | 37105 | 29987
2015-02-28 | 2014 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 4408 | 0 | 0
2015-02-28 | 2014 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 22168 | 2956
2015-02-28 | 2015 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33000 | 5933 | 5062
2015-02-28 | 2015 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 6000 | 4006 | 2322
2015-02-28 | 2015 | Army Active | Planning & Design | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 18127 | 2936 | 2458
2015-02-28 | 2011 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25604 | 24287 | 24287 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2011 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14215 | 11207 | 11207 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191 | 19163 | 19163 | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2012 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14149 | 11520 | 11520 | PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17; Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 28155 | 6226 | 6226 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013); PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2013 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14562 | 14562 | 14562 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-02-28 | 2014 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930 | 2558 | 2558 | PL 113-76 P&D Recission
2015-02-28 | 2014 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 12240 | 2120 | 2120
2015-02-28 | 2015 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 17600 | 0 | 0
2015-02-28 | 2015 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $3M | 13720 | 0 | 0
2015-02-28 | 2012 | Defense Finance and Accounting Service | Planning and Design - Military Construction [MILCON P&D] | Investigation and Design | 1992 | 748 | 709
2015-02-28 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction [UMMC] | Construction | 15404 | 12903 | 3059
2015-02-28 | 2009 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 3979 | 3979 | 3979
2015-02-28 | 2010 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 5547 | 3984 | 3984
2015-02-28 | 2011 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4673 | 2734 | 2643
2015-02-28 | 2012 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 5930 | 4756 | 4715
2015-02-28 | 2013 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4608 | 3063 | 2063
2015-02-28 | 2014 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 9578 | 554 | 29
2015-02-28 | 2015 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4100 | 4100 | 4100
2015-02-28 | 2009 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 171255 | 170636 | 166045
2015-02-28 | 2010 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 72679 | 72543 | 68599
2015-02-28 | 2011 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 193126 | 138830 | 102075
2015-02-28 | 2012 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 209957 | 3962 | 3807
2015-02-28 | 2013 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 97411 | 0 | 0
2015-02-28 | 2014 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 244 | 0 | 0
2015-02-28 | 2015 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 0 | 0 | 0
2015-02-28 | 2010 | Defense Intelligence Agency | Planning and Design - Military Construction [MILCON P&D] | P&D for K-16 FOB-K renovation of two buildings to include Administrative and SCIF Spaces | 442 | 0 | 442 | Planning and Design MIPR sent to U.S. Army Engineer District, Far East for K-16 Design. MIPR has been fully executed.
2015-02-28 | 2012 | Defense Intelligence Agency | Planning and Design - Military Construction [MILCON P&D] | P&D for DIAC Parking Garage Replacement; P&D for DIAC Chilled Water Project for Data Center ($125K) and P&D for DIAC Cooling Tower for Data Center ($105K); P&D for UPS for Data Center Installation; P&D for Construction of JUIAF RDF | 3260 | 472 | 2772 | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $416K (CORRECTED AMOUNT) obligated as CAT I. Contract awarded on 23 September 2014.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 100% design completed.; Design complete.
2014-12-31 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 79739 | 62283 | 19486 | DISA Europe Facility Upgrades; Construct New DISA Facility Scott AFB
2014-12-31 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2616 |  |  | DISA Pacific Facility Upgrade
2015-03-03 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction |  | 9600 |  |  | Combined Communications Gateway Geraldton (DoD Teleport Geraldton)
2015-02-28 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] | For design of projects from 2012 to 2016 | 36093 | 36093 | 36093
2015-02-28 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2011 to 2014 | 4968 | 4569 | 4569
2015-02-28 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] | For design of project from 2012 to 2016 | 34331 | 34331 | 34331
2015-02-28 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2012 to 2014 | 6312 | 5391 | 5391
2015-02-28 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] | For design of project from 2014 to 2017 | 30636 | 17148 | 17148
2015-02-28 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] |  | 6686 | 0 | 0
2015-02-28 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] |  | 6978 | 0 | 0
2015-02-28 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] |  | 7430 | 0 | 0
2015-02-28 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] |  | 0 | 0 | 0
2015-02-28 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] |  | 5932 | 0 | 0
2015-03-04 | 2008 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design Efforts FY09 RCI MILCON projects/Design efforts for FY 08/09/ 10/11/12 MILCON projects | 5161 | 5211 | 5158 | RCI-Residential Communities Initiative
2015-03-04 | 2009 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design Efforts FY09 RCI MILCON projects/Design efforts for FY 09/10/ 11/12/13 MILCON projects | 13623 | 13623 | 12452
2015-03-04 | 2010 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 10/11/ 12/13 MILCON projects | 8829 | 8764 | 8717 | Reflects Sequestration Reduction
2015-03-04 | 2011 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 11/12/ 13 MILCON projects | 78666 | 78666 | 62044 | Reflects Sequestration Reduction
2015-03-04 | 2012 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 12/13 MILCON projects | 64551 | 64533 | 46094 | Reflects Sequestration Reduction
2015-03-04 | 2013 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 94115 | 31722 | Reflects Sequestration Reduction
2015-03-04 | 2014 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 14/15/16/17 MILCON projects | 75905 | 0
2015-03-04 | 2015 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY15/16/17/18 MILCON projects | 42387 | 0
2015-03-04 | 2009 | DoD Education Activity | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5 | 4 | 4 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2015-03-04 | 2013 | DoD Education Activity | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 3771 | 0 |  | Reflects Sequestration Reduction
2015-03-04 | 2014 | DoD Education Activity | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5409 | 0
2015-03-04 | 2015 | DoD Education Activity | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 6846 | 0
2015-02-28 | 2011 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY15-16 MILCON Projects | 1186 | 1186 | 1186 | Funds tranferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2015-02-28 | 2012 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY13-14 MILCON Projects | 8368 | 8368 | 8124 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2015-02-28 | 2013 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY13-14 MILCON Projects | 4191 | 4191 | 3985 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2015-02-28 | 2014 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY14-16 MILCON Projects | 10891 | 10891 | 7655 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2015-02-28 | 2015 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY16-17 MILCON Projects | 58704 | 4516 | 201 | Supports design of the Aegis Ashore Poland site and Long Range Discrimination Radar, Pacific Region.
2015-02-28 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY13/14 | 2243 | 2038 | 1095 | Supports the R&C Piping project at Fort Greely, AK and the Storage Facility, Meck Island. $1.186M transferred to DHA in April 2014 for swap of FY11 P&D funds. $205K returned to OSD in Sep 2014.
2015-02-28 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000 | 155 | 13 | Supports the Storage Facility, Meck Island project.
2015-02-28 | 2015 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY15/16 | 2000 | 0 | 0
2015-02-28 | 2011 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 11087 | 10771 | 10771
2015-02-28 | 2011 | Marine Corps Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 853 | 744 | 741
2015-02-28 | 2011 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 27773 | 24966 | 24900
2015-02-28 | 2011 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 136314 | 136312 | 126756 | [Component: Navy-MC Active]
2015-02-28 | 2011 | Navy Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 2340 | 2229 | 2229
2015-02-28 | 2011 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20757 | 20065 | 18704 | [Component: Navy-MC Active]
2015-02-28 | 2011 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1854 | 1854 | 1854 | [Component: Navy-MC Reserve]
2015-02-28 | 2011 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 2194 | 1632 | 1548 | [Component: Navy-MC Reserve]
2015-02-28 | 2012 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 25327 | 23561 | 22824
2015-02-28 | 2012 | Marine Corps Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719 | 566 | 566
2015-02-28 | 2012 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 68661 | 48120 | 45071
2015-02-28 | 2012 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 83943 | 83696 | 79924 | [Component: Navy-MC Active]
2015-02-28 | 2012 | Navy Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2447 | 2377 | 2367
2015-02-28 | 2012 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20919 | 19802 | 18187 | [Component: Navy-MC Active]
2015-02-28 | 2012 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478 | 2148 | 2148 | [Component: Navy-MC Reserve]
2015-02-28 | 2012 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 1947 | 1237 | 1171 | [Component: Navy-MC Reserve]
2015-02-28 | 2013 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 17441 | 16715 | 265
2015-02-28 | 2013 | Marine Corps Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455 | 419 | 378
2015-02-28 | 2013 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 42739 | 24278 | 2976
2015-02-28 | 2013 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 96888 | 90634 | 61878 | [Component: Navy-MC Active]
2015-02-28 | 2013 | Navy Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609 | 684 | 643
2015-02-28 | 2013 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 15612 | 13309 | 6831 | [Component: Navy-MC Active]
2015-02-28 | 2013 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995 | 1994 | 1991 | [Component: Navy-MC Reserve]
2015-02-28 | 2013 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2015-02-28 | 2014 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 24253 | 15632 | 0
2015-02-28 | 2014 | Marine Corps Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463 | 0 | 0
2015-02-28 | 2014 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 44716 | 28894 | 0
2015-02-28 | 2014 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638 | 45515 | 34285 | [Component: Navy-MC Active]
2015-02-28 | 2014 | Navy Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975 | 0 | 0
2015-02-28 | 2014 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 19740 | 11495 | 584 | [Component: Navy-MC Active]
2015-02-28 | 2014 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2556 | 1154 | 1136 | [Component: Navy-MC Reserve]
2015-02-28 | 2014 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2015-02-28 | 2015 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2015-02-28 | 2015 | Marine Corps Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2015-02-28 | 2015 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2015-02-28 | 2015 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 16684 | 10921 | 10252 | Appropriated Amount reflects funds allocated to date only. [Component: Navy-MC Active]
2015-02-28 | 2015 | Navy Active | Planning and Design - Military Family Housing [MFH P&D] | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2015-02-28 | 2015 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 3582 | 0 | 0 | Appropriated Amount reflects funds allocated to date only. [Component: Navy-MC Active]
2015-02-28 | 2015 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15 [Component: Navy-MC Reserve]
2015-02-28 | 2015 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | No funds yet allocated for FY15 [Component: Navy-MC Reserve]
2015-02-28 | 2010 | National Security Agency | Planning and Design - Military Construction [MILCON P&D] | Generators 10 & 11 | 440 | 440 |  | MIPR 12-045 from MHS to AFCEC, $240K moved from Power & Cooling
2015-02-15 | 2010 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 4344 | 4331 |  | As of 15Feb2015
2015-02-15 | 2011 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 26469 | 25109 |  | As of 15Feb2015; Includes funds given to UK DIO
2015-02-15 | 2012 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 30308 | 28055 |  | As of 15Feb2015; Includes funds given to UK DIO
2015-02-15 | 2013 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 25454 | 14580 |  | As of 15Feb2015; Includes funds given to UK DIO
2015-02-15 | 2014 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 36866 | 0 |  | As of 15Feb2015
2015-02-15 | 2015 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 24197 | 0 |  | As of 15Feb2015
2015-02-15 | 2010 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 6011 | 6010 |  | As of 15Feb2015
2015-02-15 | 2011 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 7531 | 7526 |  | As of 15Feb2015
2015-02-15 | 2012 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 8487 | 8045 |  | As of 15Feb2015
2015-02-15 | 2013 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 9216 | 8735 |  | As of 15Feb2015
2015-02-15 | 2014 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 5170 | 2833 |  | As of 15Feb2015
2015-02-15 | 2015 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 10334 | 0 |  | As of 15Feb2015