## PROJECTS
Project Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Construction Project Type Name | State Name | Country Name | Project Number | Project Title | Sub-Project Number | Diverted Funds Total Amount | Diverted Funds Recipient Text | Construction Start Date | Original Construction Completion Date | Current Construction Completion Date | Construction Percent Complete | Current RPA Placed-In-Service Date
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Tennessee | United States | ACC123183 | Air Support Operations Center |  |  |  | 2014-09-29 | 2016-02-20 | 2016-03-21 | 100% | 2016-03-21
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Texas | United States | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 |  |  |  | 2014-05-15 | 2015-06-09 | 2017-01-25 | 99% | 2015-06-30
2017-02-15 | 2016 | Air Force Active | Major Military Construction |  | Germany | AFAF140005 | Construct Airfield and Base Camp |  |  |  | 2016-03-31 | 2017-12-29 | 2017-12-29 | 33% | 2017-07-07
2016-11-15 | 2012 | Air Force Active | Unspecified Minor Military Construction | Oklahoma | United States | AGGN123002P | Communications Network Control Center Consolidation |  |  |  | 2014-03-10 | 2014-12-19 | 2016-01-28 | 100% | 2016-01-28
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS |  |  |  | 2014-07-30 | 2015-12-24 | 2016-10-03 | 98% | 2016-07-18
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu |  |  |  | 2015-01-14 | 2015-12-24 | 2016-10-03 | 90% | 2016-10-03
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 |  |  |  | 2014-06-19 | 2015-10-12 | 2016-09-23 | 98% | 2016-09-23
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143004 | KC-46A FTU FTC Simulator Facility Phase 1 |  |  |  | 2014-06-19 | 2015-10-12 | 2016-09-23 | 98% | 2016-09-23
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143005A | KC-46A FTU ADAL FUEL CELL MAINTENANCE HANGAR |  |  |  | 2016-05-30 | 2017-07-17 | 2017-07-03 | 6% | 2017-09-29
2017-02-15 | 2013 | Air Force Active | Major Military Construction | Guam | Guam | AJJY123010 | Guam Strike Fuel Systems Maintenance Hangar |  |  |  | 2015-03-25 | 2017-04-16 | 2017-10-26 | 12% | 2017-10-26
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | AJJY133027 | Guam Strike Tanker Gp Maint Hangar/Amu/Sqd Ops (Incr 1) |  |  |  | 2015-02-01 | 2017-03-08 | 2018-01-15 | 14% | 2018-01-15
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Guam | Guam | AJJY133028 | PAR Low Observable/Corrosion Control/Composite Repair Shop |  |  |  | 2016-09-30 | 2018-10-20 | 2018-09-20 | 5% | 2018-09-20
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Guam | Guam | AJJY143030 | APR SOUTH RAMP UTILITIES PHASE 2 |  |  |  | 2016-09-02 | 2017-01-10 | 2018-02-24 | 5% | 2018-02-24
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | AJJY143760 | Hardened Structures For POL Fuel Systems |  |  |  | 2017-03-15 | 2016-05-29 | 2018-04-27 | 6% | 2018-04-27
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility |  |  |  | 2014-10-24 | 2016-08-17 | 2016-07-20 | 100% | 2016-07-20
2016-11-15 | 2010 | Air Force Active | Major Military Construction | Maryland | United States | AJXF063009 | Replace Munitions Storage Area |  |  |  | 2011-06-23 | 2013-05-13 | 2016-05-03 | 100% | 2016-05-03
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Maryland | United States | AJXF103010 | Construct Helicopter Operations Facility |  |  |  | 2016-05-02 | 2017-04-05 | 2017-05-04 | 45% | 2017-05-04
2016-11-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Maryland | United States | AJXF106000 | Construct Taxiway To North Of ACA Facility Bldg 2489 |  |  |  | 2015-05-08 | 2016-04-08 | 2016-09-30 | 99% | 2016-09-01
2017-02-15 | 2011 | Air Force Active | Major Military Construction |  | Qatar | ALUA073006B | Blatchford-Preston Complex, Phase III |  |  |  | 2012-09-27 | 2016-10-16 | 2017-01-31 | 90% | 2017-01-31
2016-11-15 | 2008 | Air Force Active | Major Military Construction |  | Qatar | ALUA073008A | Facility Replacements |  |  |  | 2011-03-01 | 2012-08-22 | 2015-10-06 | 100% | 2015-10-13
2016-11-15 | 2010 | Air Force Active | Major Military Construction |  | Qatar | ALUA107000 | Coalition Compound Billeting |  |  |  | 2012-06-05 | 2014-04-06 | 2016-06-28 | 100% | 2016-08-15
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA110032 | Fuel Truck Parking |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2017-02-15 | 2011 | Air Force Active | Major Military Construction |  | Qatar | ALUA113001 | Theater Communications Facility |  |  |  | 2012-06-01 | 2014-04-02 | 2017-01-21 | 75% | 2017-01-31
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113002 | Fuels Laboratory |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113005 | C-17 Spare Parts Facility |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113006 | High Mast Lighting |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113009 | Entry Control Point |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113010 | Cryogenics Facility |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113012 | ELRS Storage Facility |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2017-02-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113026 | C-130 Aircraft Maintenance Unit |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 45% | 2018-10-26
2016-11-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113027 | Air Defense Artillery Maintenance Facility |  |  |  | 2013-08-28 | 2014-11-06 | 2015-11-27 | 100% | 2015-12-10
2016-11-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113032 | Precision Measurement Equipment Laboratory |  |  |  | 2013-07-08 | 2015-02-19 | 2015-11-27 | 100% | 2016-01-06
2016-11-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113034 | AFOSI Regional And Local Facility |  |  |  | 2013-08-28 | 2015-02-19 | 2015-11-27 | 100% | 2015-12-10
2017-02-15 | 2016 | Air Force Active | Major Military Construction |  | Oman | AMAB120001 | AIRLIFT APRON |  |  |  | 2016-07-22 | 2018-05-15 | 2018-05-13 | 2% | 2018-05-13
2016-11-15 | 2011 | Air Force Active | Major Military Construction |  | Italy | ASHE083011 | Air Support Operations Squadron (ASOS) Facility |  | 1453000 | KRSM103011; | 2011-12-16 | 2013-09-05 | 2016-03-28 | 100% | 2016-02-03
2017-02-15 | 2013 | Air Force Active | Major Military Construction |  | Italy | ASHE103001 | F-16 Mission Training Center |  |  |  | 2015-05-04 | 2016-12-02 | 2018-02-23 | 82% | 2017-02-24
2017-02-15 | 2012 | Air Force Active | Major Military Construction | Louisiana | United States | AWUB105002 | Mission Support Group Complex |  |  |  | 2012-03-26 | 2013-11-24 | 2015-09-16 | 99% | 2014-12-23
2017-02-15 | 2013 | Air Force Active | Major Military Construction | California | United States | BAEY133001 | Civil Engineer Administration/Operations Facility |  |  |  | 2014-07-09 | 2016-03-30 | 2017-01-27 | 53% | 2017-01-27
2017-02-15 | 2014 | Air Force Active | Major Military Construction | California | United States | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 3000000 | CADJ140004; | 2014-08-27 | 2016-11-04 | 2016-12-14 | 53% | 2017-02-02
2017-02-15 | 2015 | Air Force Active | Major Military Construction |  | Djibouti | CADJ140004 | Construct Perimeter Boundary - Chabelley Airfield, Djibouti |  |  |  | 2015-10-09 | 2017-02-02 | 2017-05-12 | 2% | 2017-05-31
2016-11-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ013004 | Airman And Family Readiness Center |  |  |  | 2015-07-08 | 2016-06-10 | 2016-07-28 | 100% | 2016-07-28
2016-11-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ073023A | Satellite Dining Facility |  |  |  | 2015-03-09 | 2016-11-19 | 2016-05-26 | 99% | 2016-07-20
2017-02-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ073050 | Dormitory (144 Rm) |  |  |  | 2014-08-14 | 2016-08-21 | 2017-04-07 | 99% | 2016-05-17
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Florida | United States | DBEH063000 | Range Communications Facility |  |  |  | 2016-08-29 | 2018-06-20 | 2018-07-01 | 5% | 2018-09-29
2016-11-15 | 2010 | Air Force Active | Major Military Construction |  | United Arab Emirates | DHAF100031 | Construct Maintenance Operations Center And Command Post |  |  |  | 2011-09-19 | 2012-02-28 | 2016-03-01 | 100% | 2016-03-01
2016-11-15 | 2010 | Air Force Active | Major Military Construction |  | United Arab Emirates | DHAF100120 | Construct SatCom Facility |  |  |  | 2011-09-19 | 2012-02-28 | 2016-03-01 | 100% | 2016-03-01
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF120037 | Clinic |  |  |  | 2014-09-29 | 2015-01-20 | 2017-03-15 | 88% | 2017-03-15
2016-11-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF120057 | Fire Protection Water Storage |  |  |  | 2014-09-15 | 2014-11-24 | 2016-05-24 | 100% | 2016-05-24
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF124001 | EOD Facility |  |  |  | 2014-12-01 | 2016-11-25 | 2017-05-31 | 85% | 2017-05-31
2016-11-15 | 2011 | Air Force Active | Major Military Construction | Arizona | United States | FBNV063501 | AMARG Hangar |  |  |  | 2011-09-12 | 2013-08-27 | 2016-01-15 | 100% | 2016-01-15
2017-02-15 | 2011 | Air Force Active | Major Military Construction | Arizona | United States | FBNV113002 | HC-130J Aerial Cargo Facility |  | 2000000 | YWHG111005; | 2011-11-09 | 2013-05-02 | 2017-03-20 | 95% | 2013-09-13
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | FBNV113005 | HC-130J Wash Rack |  |  |  | 2016-11-15 | 2018-03-20 | 2018-03-20 | 1% | 2018-04-20
2016-11-15 | 2012 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | FBNV133500 | T-10 Engine Test Cell (AMARG) |  |  |  | 2014-11-22 | 2015-06-08 | 2016-03-06 | 100% | 2016-03-10
2017-02-15 | 2010 | Air Force Active | Major Military Construction | Delaware | United States | FJXT033003 | Consol Communications Facility |  |  |  | 2011-01-03 | 2013-10-12 | 2017-08-01 | 95% | 2014-09-12
2016-11-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | FTFA073007 | CNST Modular Storage Magazines |  |  |  | 2015-02-05 | 2016-02-05 | 2016-05-13 | 100% | 2016-06-23
2016-11-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | FTFA123000 | Advanced Energetics Development Office Facility |  |  |  | 2014-12-05 | 2015-12-05 | 2016-04-02 | 100% | 2016-03-08
2017-02-15 | 2012 | Air Force Active | Major Military Construction | Alaska | United States | FTQW083005 | Dormitory (168 RM) |  |  |  | 2014-08-26 | 2016-08-15 | 2016-12-16 | 100% | 2016-12-20
2017-02-15 | 2010 | Air Force Active | Major Military Construction | Alaska | United States | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 |  |  |  | 2011-06-17 | 2015-01-27 | 2016-12-22 | 99% | 2015-06-28
2017-02-15 | 2011 | Air Force Active | Major Military Construction | Alaska | United States | FTQW083008 | Repair Central Heat And Power Plant Boiler |  |  |  | 2011-06-17 | 2015-01-27 | 2016-12-22 | 99% | 2016-12-22
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Alaska | United States | FTQW163011 | F-35A Flight Sim /ADAL Sqd Ops/AMU |  |  |  | 2016-12-23 | 2018-06-18 | 2018-06-18 | 2% | 2018-06-19
2017-02-15 | 2016 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM063002 | DORMITORY (168 RM) |  |  |  | 2017-01-10 | 2018-04-13 | 2018-04-13 | 1% | 2018-05-31
2016-11-15 | 2012 | Air Force Active | Major Military Construction | Alaska | United States | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) |  | 19165000 | ALUA073006B;WWYK143004A;YWHG111005;ZHTV053302; | 2012-06-26 | 2018-03-28 | 2016-09-30 | 99% | 2016-03-01
2017-02-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Washington | United States | GJKZ130025 | ADAL, Physiological Tng Fac, Convert To PMEL; B2145 |  |  |  | 2015-05-24 | 2015-12-17 | 2016-08-01 | 40% | 2016-08-01
2017-02-15 | 2012 | Air Force Active | Major Military Construction |  | Italy | HACC123204 | UAS SATCOM Relay Pads and Facility |  |  |  | 2016-07-18 | 2017-02-21 | 2017-10-31 | 2% | 2017-10-31
2017-02-15 | 2015 | Air Force Active | Major Military Construction | New Jersey | United States | HEKP103001 | FIRE STATION |  |  |  | 2016-04-15 | 2017-10-28 | 2017-10-30 | 1% | 2017-10-22
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Hawaii | United States | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  |  |  | 2015-11-10 | 2016-04-17 | 2017-01-20 | 2% | 2017-01-20
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Utah | United States | KRSM003009 | Fire Crash Rescue Station |  |  |  | 2015-04-28 | 2017-04-27 | 2017-04-16 | 32% | 2017-04-16
2016-12-07 | 2013 | Air Force Active | Major Military Construction | Utah | United States | KRSM103012 | F-35 Adal Hangar 45W/AMU |  |  |  | 2014-01-27 | 2015-10-29 | 2016-11-18 | 100% | 2016-08-30
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Utah | United States | KRSM103013 | F-35A HANGAR 40/42 ADAL AND AMU |  |  |  | 2016-10-07 | 2017-05-30 | 2018-10-07 | 3% | 2018-10-07
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Utah | United States | KRSM133002 | HAYMAN IGLOOS |  |  |  | 2016-09-13 | 2017-05-30 | 2017-05-30 | 3% | 2017-05-30
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Utah | United States | KRSM153001 | F-35A FLIGHT SIMULATOR ADDITION, PHASE 2 |  |  |  | 2016-09-23 | 2017-06-15 | 2017-06-15 | 3% | 2017-06-15
2016-11-15 | 2012 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD013003 | Child Development Center |  |  |  | 2012-11-08 | 2014-05-17 | 2014-07-31 | 100% | 2014-06-14
2017-02-15 | 2016 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD133001 | MARSHALING AREA, ARM/DE-ARM PAD D |  |  |  | 2016-10-25 | 2017-07-15 | 2017-07-15 | 1% | 2017-07-15
2016-11-15 | 2008 | Air Force Active | Military Family Housing Improvement |  | Turkey | LJYC084001 | Improve Family Housing 515 Units |  |  |  | 2012-03-08 | 2012-10-19 | 2016-08-22 | 100% | 2016-03-18
2017-02-15 | 2014 | Air Force Active | Unspecified Minor Military Construction |  | Turkey | LJYC106001 | EOD Facility |  |  |  | 2016-09-30 | 2016-09-28 | 2017-09-29 | 2% | 2017-08-31
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | LKTC073101 | Land Acquisition |  |  |  | 2016-04-05 | 2015-08-15 | 2016-12-30 | 63% | 2016-12-30
2016-11-15 | 2013 | Air Force Active | Major Military Construction | Nevada | United States | LKTC133101 | RPA Mission Complex Physical Protection System |  |  |  | 2014-09-01 | 2015-08-19 | 2015-10-12 | 100% | 2015-10-12
2016-11-15 | 2011 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ114127 | Improve Family Housing, Ph 11 |  |  |  | 2012-10-24 | 2015-11-08 | 2015-10-16 | 100% | 2015-10-16
2016-11-15 | 2012 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 |  |  |  | 2013-06-04 | 2016-05-10 | 2015-10-16 | 100% | 2015-10-15
2016-11-15 | 2013 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 |  |  |  | 2013-08-29 | 2015-11-27 | 2016-04-29 | 100% | 2016-03-03
2016-11-15 | 2014 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ144287 | Improve MFH Infrastructure, Phase 3 |  |  |  | 2014-08-04 | 2015-12-15 | 2016-09-02 | 100% | 2016-10-13
2017-02-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 |  |  |  | 2014-08-25 | 2016-11-01 | 2016-11-28 | 98% | 2017-03-28
2017-02-15 | 2013 | Air Force Active | Major Military Construction | Texas | United States | MPLS083008 | Dormitory (96 Rm) |  |  |  | 2014-03-15 | 2015-06-12 | 2016-06-20 | 99% | 2016-06-25
2016-11-15 | 2011 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R3 | Recruit Dormitories Phase 3 |  | 4894000 | KRSM103011; | 2011-11-11 | 2015-03-15 | 2014-08-31 | 100% | 2014-09-30
2016-11-15 | 2012 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R4 | BMT Recruit Dormitory, Phase IV |  |  |  | 2013-01-26 | 2016-10-10 | 2015-09-11 | 100% | 2015-09-11
2016-11-15 | 2011 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 |  |  |  | 2011-09-05 | 2015-04-25 | 2014-06-30 | 100% | 2015-03-15
2016-11-15 | 2010 | Air Force Active | Major Military Construction | Virginia | United States | MUHJ053008 | West & Lasalle Gates Force Protection/Access |  |  |  | 2010-07-07 | 2014-09-30 | 2014-03-14 | 100% | 2013-07-19
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD083002 | DORMITORY (72 RM) |  |  |  | 2016-09-21 | 2016-10-25 | 2018-06-22 | 1% | 2018-04-19
2016-11-15 | 2013 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK103006 | C-130J Fuel Systems Maintenance Hangar |  | 2000000 | KRSM103012; | 2013-07-23 | 2015-07-23 | 2015-12-18 | 100% | 2015-12-18
2016-11-15 | 2013 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK113005 | C-130J Flight Simulator Addition |  |  |  | 2014-10-21 | 2015-10-21 | 2016-04-08 | 100% | 2016-04-07
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093007 | Construct Addition, Field Training Facility, B936 |  |  |  | 2014-12-01 | 2015-07-07 | 2015-12-30 | 100% | 2015-11-09
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) |  | 1200000 | CADJ140004; | 2015-06-15 | 2016-02-14 | 2016-05-25 | 100% | 2016-05-25
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Arizona | United States | NUEX103005 | Construct Flightline Fillstands |  |  |  | 2016-01-01 | 2016-11-22 | 2017-05-19 | 83% | 2017-05-19
2017-02-15 | 2016 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | NUEX113001 | FLIGHT LINE SECURITY FENCE |  |  |  | 2017-01-25 | 2017-11-22 | 2017-11-23 | 1% | 2017-11-23
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123001 | F-35 Aircraft Maintenance Hangar (Squadron 2) |  |  |  | 2016-07-01 | 2017-05-16 | 2017-05-16 | 43% | 2017-07-15
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123004 | F-35A SQUADRON OPERATIONS/AMU/HANGAR (SQUADRON 4) |  |  |  | 2016-12-01 | 2018-05-18 | 2018-11-06 | 9% | 2018-11-06
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123005 | F-35A AIRCRAFT MAINTENANCE HANGAR (SQUADRON 3) |  |  |  | 2016-12-16 | 2018-04-04 | 2018-04-26 | 12% | 2018-05-26
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Maryland | United States | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  |  |  | 2014-07-07 | 2018-07-30 | 2017-04-13 | 23% | 2017-04-13
2017-02-15 | 2015 | Air Force Active | Major Military Construction |  | Estonia | PAYZ15001A | ERI: Improve Airfield Infrastructure |  |  |  | 2017-06-01 | 2018-07-30 | 2018-07-30 | 1% | 2018-06-30
2017-02-15 | 2015 | Air Force Active | Major Military Construction |  | Lithuania | PAYZ15001B | ERI: Improve Airfield Infrastructure |  |  |  | 2017-05-29 | 2018-06-29 | 2018-06-29 | 2% | 2018-05-25
2017-02-15 | 2015 | Air Force Active | Major Military Construction |  | Latvia | PAYZ15001C | ERI: Improve Airfield Infrastructure |  |  |  | 2017-05-01 | 2018-06-30 | 2018-06-30 | 2% | 2018-05-30
2017-02-15 | 2015 | Air Force Active | Major Military Construction |  | Bulgaria | PAYZ15001D | ERI: Improve Airfield Infrastructure |  |  |  | 2017-10-01 | 2018-09-01 | 2018-09-01 | 1% | 2018-06-01
2017-02-15 | 2015 | Air Force Active | Major Military Construction |  | Romania | PAYZ15001E | ERI: Improve Airfield Infrastructure |  |  |  | 2017-10-10 | 2018-09-30 | 2018-09-30 | 2% | 2018-07-28
2017-02-15 | 2015 | Air Force Active | Unspecified Minor Military Construction | California | United States | PDPG130118 | MULTI-CUBE AMMUNITION STORAGE FACILITY, B1714 |  |  |  | 2016-01-12 | 2017-01-11 | 2016-09-01 | 80% | 2016-08-25
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar |  | 10500000 | SGBP100904C; | 2014-08-10 | 2016-01-05 | 2017-01-06 | 100% | 2017-01-06
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145118 | KC-46A Fuselage Trainer |  |  |  | 2015-05-18 | 2016-05-04 | 2017-02-15 | 99% | 2017-02-15
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145121 | KC-46A ADAL Flight Simulator Buildings |  |  |  | 2015-03-30 | 2016-04-19 | 2016-06-24 | 100% | 2016-06-24
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems |  | 2500000 | SGBP100904C; | 2014-09-02 | 2015-12-17 | 2015-10-13 | 100% | 2015-10-13
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145138 | KC-46A Alter Aircraft Parking Apron |  | 600000 | PRQE145121; | 2014-08-18 | 2017-03-10 | 2017-04-10 | 98% | 2017-04-10
2016-12-07 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145142 | KC-46A 1-Bay Maintenance Hangar |  | 3000000 | SGBP100904C; | 2014-09-19 | 2017-01-19 | 2016-11-18 | 100% | 2016-11-18
2016-12-07 | 2015 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155118 | KC-46A Adal Mobility Bag Storage Expansion |  |  |  | 2015-05-18 | 2016-05-04 | 2016-11-04 | 100% | 2016-11-04
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar |  | 19000000 | SGBP100904C; | 2014-09-30 | 2015-12-26 | 2017-04-28 | 83% | 2017-04-28
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155121 | KC-46A COMPOSITE MAINTENANCE SHOP |  |  |  | 2016-09-28 | 2017-09-19 | 2017-09-19 | 2% | 2017-09-19
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) |  |  |  | 2014-10-30 | 2015-10-15 | 2016-03-07 | 100% | 2016-04-15
2016-11-15 | 2015 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155124 | KC-46A Alter Taxiway Foxtrot |  |  |  | 2015-05-12 | 2016-11-02 | 2016-06-17 | 100% | 2016-06-17
2016-12-07 | 2016 | Air Force Active | Major Military Construction | Kansas | United States | PRQE165114 | KC-46A ADAL DEICING PADS |  |  |  | 2016-05-06 | 2016-12-26 | 2016-11-17 | 100% | 2016-11-17
2017-02-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | New Jersey | United States | PTFL126001 | Addition To Maintenance Training Facility, Bldg 2324 |  |  |  | 2015-11-02 | 2016-06-29 | 2017-03-06 | 95% | 2017-03-06
2017-02-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | New Mexico | United States | PXLY110459 | CNS RANGE CONTROL OFFICER TOWER |  |  |  | 2016-06-07 | 2017-03-05 | 2017-04-17 | 31% | 2017-04-17
2017-02-15 | 2014 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF092009 | B-52 ADAL Aircraft Maintenance Unit (AMU) |  |  |  | 2016-03-23 | 2017-09-14 | 2017-09-28 | 40% | 2017-08-15
2017-02-15 | 2014 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF092013 | B-52 Munitions Storage Igloos |  |  |  | 2014-07-15 | 2016-01-06 | 2016-11-30 | 92% | 2016-11-30
2017-02-15 | 2014 | Air Force Active | Military Family Housing Improvement |  | Japan | QKKA133001P1 | Improve Family Housing, Ph 1 |  |  |  | 2015-10-29 | 2017-09-28 | 2017-09-01 | 45% | 2017-10-05
2016-11-15 | 2013 | Air Force Active | Military Family Housing Improvement |  | Japan | QKKA134001 | Improve Mfh Infrastructure, Phase 2 |  |  |  | 2013-10-29 | 2015-09-23 | 2015-11-18 | 100% | 2015-12-22
2017-02-15 | 2014 | Air Force Active | Military Family Housing Improvement |  | Japan | QKKA144002 | Improve MFH Infrastructure, Phase 3 |  |  |  | 2014-11-10 | 2017-01-14 | 2017-05-01 | 80% | 2017-05-08
2016-11-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Georgia | United States | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility |  |  |  | 2014-11-19 | 2015-11-19 | 2016-05-18 | 100% | 2016-05-18
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF083002 | Dormitory |  |  |  | 2016-02-11 | 2016-09-28 | 2017-01-17 | 89% | 2017-03-13
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103005 | F-35A ADAL AME Storage Facility |  |  |  | 2015-04-01 | 2016-02-18 | 2016-03-16 | 100% | 2016-05-24
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103006 | F-35A Parts Store |  | 1400000 | CADJ140004; | 2015-04-30 | 2016-01-06 | 2016-05-05 | 100% | 2016-05-05
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar |  |  |  | 2015-03-03 | 2015-12-16 | 2016-02-29 | 100% | 2016-02-29
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF113005 | RPA Weapons School |  | 2000000 | CADJ140004; | 2014-03-01 | 2016-08-01 | 2016-06-14 | 100% | 2016-06-14
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Nevada | United States | RKMF123007 | F-35A Weapons School Addition |  |  |  | 2015-12-16 | 2017-05-03 | 2017-04-01 | 50% | 2017-07-15
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Nevada | United States | RKMF133001 | F-22 Flight Simulator Facility |  |  |  | 2015-10-15 | 2017-01-19 | 2017-05-27 | 51% | 2017-05-18
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Nevada | United States | RKMF143001 | F-35A Maintenance Hangar/Amu |  |  |  | 2016-02-15 | 2017-09-11 | 2017-11-08 | 11% | 2017-11-10
2016-11-15 | 2015 | Air Force Active | Major Military Construction | Guam | Guam | SAKW059006 | PRTC - Red Horse Logistics Facility |  |  |  | 2015-03-07 | 2016-04-10 | 2016-07-08 | 100% | 2016-07-08
2016-11-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | SAKW113003 | PRTC - Red Horse Airfield Operations Facility (TFI) |  |  |  | 2015-03-06 | 2016-07-08 | 2016-09-01 | 100% | 2016-09-01
2016-11-15 | 2015 | Air Force Active | Major Military Construction | Guam | Guam | SAKW113008 | PRTC - Combat Communications Infrastructure Facility |  |  |  | 2015-08-15 | 2016-06-21 | 2016-09-22 | 100% | 2016-09-22
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | SAKW133005 | PRTC Silver Flag Fire Rescue & Emergency Management Training |  |  |  | 2015-03-30 | 2017-02-06 | 2017-01-20 | 87% | 2017-01-20
2016-11-15 | 2015 | Air Force Active | Major Military Construction | Guam | Guam | SAKW143031 | PRTC Satellite Fire Station |  |  |  | 2015-03-06 | 2016-07-30 | 2016-09-20 | 100% | 2016-09-20
2017-02-15 | 2012 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  |  |  | 2012-10-15 | 2016-09-10 | 2017-12-22 | 86% | 2017-01-17
2016-11-15 | 2011 | Air Force Active | Major Military Construction | Florida | United States | SXHT053001 | Air Force Technical Applications Center |  |  |  | 2012-01-23 | 2016-05-30 | 2016-04-01 | 100% | 2014-03-03
2017-02-15 | 2010 | Air Force Active | Major Military Construction |  | Germany | TYFR053037 | Aerospace Ground Equipment Maintenance Complex |  |  |  | 2012-08-06 | 2014-08-05 | 2017-07-03 | 99% | 2014-02-11
2016-12-07 | 2011 | Air Force Active | Major Military Construction |  | Germany | TYFR083001 | Deicing Fluid Storage & Dispensing Facility |  | 155000 | KRSM103011; | 2012-11-13 | 2014-09-11 | 2016-10-07 | 98% | 2016-10-10
2016-12-07 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR106261 | PL-1 Security Measures For Communications Compound |  |  |  | 2014-01-22 | 2014-12-12 | 2016-05-01 | 99% | 2015-02-04
2016-11-15 | 2013 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR126175 | Expand AOC Parking Structure |  |  |  | 2014-08-08 | 2015-02-24 | 2015-10-22 | 100% | 2015-10-22
2017-02-15 | 2011 | Air Force Active | Major Military Construction |  | Germany | TYFU083507R2 | Dormitory (128 Rm) |  |  |  | 2014-06-16 | 2017-07-04 | 2017-07-19 | 99% | 2017-03-31
2017-02-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Georgia | United States | UHHZ123001 | Convert Cooler Area B/660 To AFLCMC/WFM C-17 Program Office |  |  |  | 2015-02-11 | 2016-05-11 | 2016-09-16 | 98% | 2016-04-25
2016-11-15 | 2012 | Air Force Active | Major Military Construction |  | Djibouti | USAFE17002 | Combat Aircraft Loading Area |  |  |  | 2013-01-24 | 2014-01-16 | 2016-06-10 | 100% | 2015-10-01
2016-11-15 | 2012 | Air Force Active | Major Military Construction |  | Djibouti | USAFE17003 | Parallel Taxiway Extension |  |  |  | 2013-01-24 | 2014-05-24 | 2015-09-25 | 100% | 2015-10-01
2016-11-15 | 2012 | Air Force Active | Major Military Construction |  | Djibouti | USAFE17004 | Expeditionary Lodging |  |  |  | 2013-03-15 | 2014-04-13 | 2014-09-26 | 100% | 2014-10-20
2017-02-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | North Carolina | United States | VKAG133001 | Operations Support Squadron/War Room Facility |  |  |  | 2015-05-27 | 2016-06-05 | 2016-01-25 | 36% | 2016-01-25
2017-02-15 | 2008 | Air Force Active | Major Military Construction | South Carolina | United States | VLSB083007 | Base Infrastructure |  |  |  | 2008-10-27 | 2016-02-26 | 2016-06-02 | 99% | 2010-03-08
2017-02-15 | 2014 | Air Force Active | Unspecified Minor Military Construction |  | Germany | VYHK143301 | Catch Basin For Storm Water Discharge, Location 2, Welscherw |  |  |  | 2015-10-30 | 2017-09-14 | 2017-10-30 | 2% | 2017-10-30
2017-02-15 | 2016 | Air Force Active | Major Military Construction |  | Greenland | WWCX103027 | Thule Consolidation, Phase 1 |  |  |  | 2016-07-09 | 2018-07-28 | 2018-07-28 | 2% | 2018-07-28
2017-02-15 | 2014 | Air Force Active | Major Military Construction |  | Greenland | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  |  |  | 2014-08-19 | 2016-08-08 | 2017-09-01 | 79% | 2016-11-30
2017-02-15 | 2013 | Air Force Active | Major Military Construction |  | Greenland | WWCX103032 | Dormitory (48 Pn) |  |  |  | 2013-08-15 | 2015-07-29 | 2016-10-14 | 99% | 2015-10-27
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK129000 | AIR CONTROL GROUP SQUADRON OPERATIONS |  |  |  | 2016-04-14 | 2017-09-06 | 2017-09-21 | 2% | 2017-09-21
2017-02-15 | 2015 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK143004 | KC-46A DEPOT MAINT COMPLEX SUPPORT INFRASTRUCTURE |  |  |  | 2016-08-31 | 2018-02-08 | 2017-09-25 | 2% | 2017-06-26
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK163002 | KC-46A Depot Maintenance Dock |  |  |  | 2016-11-01 | 2018-05-31 | 2018-05-31 | 1% | 2018-08-15
2016-11-15 | 2013 | Air Force Active | Major Military Construction | Florida | United States | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair |  |  |  | 2013-08-21 | 2015-08-11 | 2016-01-21 | 100% | 2015-06-10
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Florida | United States | XLWU103007 | F-22 Muntions Storage Complex |  |  |  | 2015-06-26 | 2016-11-11 | 2017-01-28 | 86% | 2017-02-15
2016-11-15 | 2011 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ084017 | Const Center For Character & Leadership Development |  |  |  | 2013-01-15 | 2014-09-29 | 2016-07-13 | 100% | 2016-04-08
2017-02-15 | 2016 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ094013 | Front Gates Force Protection Enhancements |  |  |  | 2017-03-30 | 2017-10-17 | 2017-10-17 | 2% | 2017-10-17
2016-11-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | XQPZ124003 | Const Perm ECP-Pine Drive |  |  |  | 2015-05-13 | 2015-12-09 | 2016-01-18 | 100% | 2016-01-18
2016-11-15 | 2010 | Air Force Active | Major Military Construction | Oklahoma | United States | XTLF033303 | Control Tower |  |  |  | 2010-10-05 | 2012-02-12 | 2015-12-10 | 100% | 2015-09-18
2016-11-15 | 2012 | Air Force Active | Major Military Construction | Missouri | United States | YWHG071005 | WSA Security Control Facility |  |  |  | 2012-03-16 | 2013-09-07 | 2016-01-06 | 100% | 2014-08-15
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Missouri | United States | YWHG111010 | WSA: Construct Two New MOP Igloos |  |  |  | 2014-08-11 | 2015-12-04 | 2017-05-31 | 99% | 2016-01-07
2017-02-15 | 2014 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV053302 | Add/Alter Foreign Materiel Exploitation Laboratory |  |  |  | 2015-09-09 | 2017-06-02 | 2017-06-02 | 61% | 2017-08-10
2017-02-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Ohio | United States | ZHTV126003 | Add Standby Generator (NASIC) (P-341) |  |  |  | 2015-09-15 | 2016-04-14 | 2016-11-30 | 99% | 2016-11-30
2016-12-01 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Indiana | United States | CTGB109003 | Reserve Fire Station Annex |  |  |  | 2014-11-04 | 2015-11-04 | 2016-09-18 | 100% | 2016-10-31
2016-12-01 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Texas | United States | DDPM120009 | Add Simulator Bay, Bulding 1792 |  |  |  | 2015-09-30 | 2016-10-28 | 2016-07-27 | 100% | 2016-07-27
2017-02-07 | 2015 | Air Force Reserve | Major Military Construction | Texas | United States | DDPM130008 | Explosive Ordnance Disposal Facility |  |  |  | 2017-07-01 | 2016-07-27 | 2019-01-15 | 0%
2017-02-07 | 2012 | Air Force Reserve | Major Military Construction | South Carolina | United States | DKFX079003 | Red Horse Readiness And Training Facility |  |  |  | 2012-07-13 | 2013-03-01 | 2017-03-31 | 93% | 2016-10-11
2017-02-07 | 2014 | Air Force Reserve | Major Military Construction | California | United States | PDPG030130P1 | Joint Regional Deployment And Passenger Terminal Facility |  |  |  | 2015-05-05 | 2017-03-20 | 2017-03-31 | 95%
2017-02-07 | 2013 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ099095 | Flight Simulator Facility |  |  |  | 2014-08-05 | 2015-07-31 | 2017-02-28 | 98% | 2016-07-13
2016-12-01 | 2012 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ120572 | Vehicle Maintenance Facility |  |  |  | 2014-09-22 | 2015-03-21 | 2016-05-26 | 100% | 2015-10-25
2017-02-07 | 2014 | Air Force Reserve | Major Military Construction | Oklahoma | United States | WWYK129000 | AIR CONTROL TOWER SQUADRON OPERATIONS |  |  |  | 2016-02-26 | 2017-09-21 | 2017-09-21 | 2%
2017-02-15 | 2013 | Air National Guard | Unspecified Minor Military Construction | Indiana | United States | ATQZ099073 | MCCA: A-10 Conversion-Expand Arm/Disarm Apron-T/W Bravo |  |  |  | 2014-12-08 | 2016-04-21 | 2016-05-27 | 99% | 2015-08-15
2016-09-14 | 2012 | Air National Guard | Major Military Construction | Indiana | United States | ATQZ099080 | A-10 Facility Conversion - Munitions Complex |  |  |  | 2014-08-27 | 2015-11-20 | 2016-05-27 | 92% | 2016-03-18
2016-09-14 | 2012 | Air National Guard | Unspecified Minor Military Construction | Massachusetts | United States | AXQD129074 | F 15 Shop Addition |  |  |  | 2015-01-13 | 2016-07-16 | 2017-07-16 | 38% | 2016-07-16
2017-02-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Tennessee | United States | BKTZ129083 | Construct Cyber SCIF |  |  |  | 2015-10-28 | 2016-10-20 | 2017-01-20 | 96% | 2016-12-13
2017-02-15 | 2014 | Air National Guard | Major Military Construction | Alabama | United States | BRKR999147 | Add to and Alter Distributed Ground Station Facility |  |  |  | 2014-10-31 | 2016-10-23 | 2017-05-31 | 54% | 2017-05-31
2017-02-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Connecticut | United States | CEKT129080 | Add to Fire Station |  |  |  | 2016-03-01 | 2018-08-18 | 2018-05-18 | 40% | 2018-05-18
2017-02-15 | 2015 | Air National Guard | Major Military Construction | Connecticut | United States | CEKT139004 | Construct C-130 Fuel Cell and Corrosion Control Facility |  |  |  | 2015-07-24 | 2018-01-09 | 2017-02-28 | 61% | 2017-02-28
2017-02-15 | 2016 | Air National Guard | Major Military Construction | Iowa | United States | FFAN139009 | NDAA: Remotely Piloted & Targeting Group Beddown |  |  |  | 2016-09-17 | 2017-09-14 | 2018-04-27 | 15% | 2017-09-16
2017-02-15 | 2015 | Air National Guard | Major Military Construction | Iowa | United States | FFAN139010 | NDAA: Remotely Piloted & Targeting Group Beddown |  |  |  | 2015-07-23 | 2016-08-07 | 2017-03-31 | 97% | 2016-09-09
2017-02-15 | 2016 | Air National Guard | Major Military Construction | Maine | United States | FKNN059220 | Add to and Alter Fire Crash/Rescue Station |  |  |  | 2016-10-03 | 2017-10-15 | 2018-03-27 | 10% | 2018-03-27
2017-02-15 | 2014 | Air National Guard | Major Military Construction | New York | United States | FPBB129050 | MQ-9 Flight Training Unit Hangar |  |  |  | 2014-09-25 | 2015-08-04 | 2016-08-31 | 99% | 2015-11-04
2017-02-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Colorado | United States | FTAE129002 | Construct Range Control Facility & Fitness Center |  |  |  | 2016-04-26 | 2016-06-22 | 2017-03-24 | 70% | 2017-02-24
2017-02-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Washington | United States | GJKZ129093 | Construct 2 Set DRBS Storage Facility |  |  |  | 2014-09-18 | 2015-03-17 | 2016-10-31 | 99% | 2016-10-31
2016-10-12 | 2013 | Air National Guard | Major Military Construction | California | United States | HAYW109006 | F-15 Conversion |  |  |  | 2014-12-02 | 2016-02-25 | 2016-04-26 | 93% | 2016-02-15
2017-02-15 | 2014 | Air National Guard | Major Military Construction | Montana | United States | JKSE129321 | Intra-Theater Airlift Conversion |  |  |  | 2014-10-20 | 2016-10-15 | 2017-02-28 | 91% | 2017-02-15
2017-02-15 | 2013 | Air National Guard | Major Military Construction | Hawaii | United States | KNMD119001 | TFI - F-22 Combat Apron Addition |  |  |  | 2013-10-31 | 2015-04-24 | 2017-05-31 | 98% | 2017-04-28
2017-02-15 | 2014 | Air National Guard | Major Military Construction | Indiana | United States | LDXF099060 | Add/Alter Bldg 37 for Distributed Common Grnd Stn |  |  |  | 2014-10-16 | 2016-02-28 | 2016-09-22 | 98% | 2016-12-16
2016-10-12 | 2014 | Air National Guard | Major Military Construction | Pennsylvania | United States | LKLW109037 | Communications Operations and Training Facility |  |  |  | 2014-10-16 | 2015-10-25 | 2016-05-31 | 98% | 2016-01-15
2016-10-12 | 2014 | Air National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | LKLW959716 | Consolidate Vehicle Maintenance Function |  |  |  | 2015-10-16 | 2016-07-12 | 2016-07-12 | 77% | 2016-07-12
2017-02-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | South Dakota | United States | LUXC139026 | Construct Addition, B16 Crash/Fire Rescue |  |  |  | 2016-04-01 | 2016-11-27 | 2016-12-07 | 93% | 2016-12-07
2017-02-15 | 2016 | Air National Guard | Major Military Construction | West Virginia | United States | LYBH049066 | Force Protection- Relocate Coonskin Road |  |  |  | 2016-07-20 | 2016-07-20 | 2017-04-15 | 55% | 2017-04-15
2017-02-15 | 2015 | Air National Guard | Major Military Construction | Michigan | United States | MBMV129060 | RPA Beddown |  |  |  | 2016-06-12 | 2017-06-12 | 2017-06-12 | 37% | 2017-06-12
2017-02-15 | 2016 | Air National Guard | Unspecified Minor Military Construction | Arkansas | United States | NKAK139133 | Construct Small Air Terminal Coverd Storage |  |  |  | 2015-07-10 | 2016-10-18 | 2017-03-15 | 92% | 2017-03-15
2016-11-16 | 2014 | Air National Guard | Unspecified Minor Military Construction | South Carolina | United States | PSTE129092 | Construct North Overrun |  |  |  | 2014-03-11 | 2014-12-24 | 2016-01-29 | 99% | 2014-12-08
2016-11-16 | 2014 | Air National Guard | Major Military Construction | Tennessee | United States | PSXE109034 | TEC Expansion - Dormitory and Classroom Training Facility |  |  |  | 2014-07-22 | 2016-07-21 | 2016-09-23 | 83% | 2016-09-23
2017-02-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Tennessee | United States | PSXE139000 | Taxiway B Extension |  |  |  | 2016-11-07 | 2018-01-01 | 2018-02-07 | 12% | 2018-01-17
2016-09-14 | 2012 | Air National Guard | Major Military Construction | Massachusetts | United States | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities |  |  |  | 2013-09-24 | 2014-09-24 | 2016-06-29 | 99% | 2016-01-28
2016-09-14 | 2012 | Air National Guard | Unspecified Minor Military Construction | Massachusetts | United States | SPBN089050 | Relocate Main Gate |  |  |  | 2015-09-28 | 2016-09-08 | 2016-09-28 | 85% | 2016-09-28
2017-02-15 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139901 | KC-46A ADAL Fuel Cell Building 253 |  |  |  | 2015-08-18 | 2016-11-19 | 2017-07-05 | 50% | 2017-07-05
2017-02-15 | 2016 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139903 | KC-46A Add/Alter Flight Simulator Bldg 156 |  |  |  | 2016-05-06 | 2017-01-01 | 2017-01-31 | 52% | 2017-01-31
2017-02-15 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139904 | KC-46A ADAL Maint Hangar Building 254 |  |  |  | 2015-08-18 | 2016-11-18 | 2018-08-13 | 3% | 2018-08-13
2016-09-14 | 2012 | Air National Guard | Unspecified Minor Military Construction | Oregon | United States | TQKD129072 | Construct Alert Hangar Bay |  |  |  | 2014-09-03 | 2015-03-19 | 2016-06-30 | 97% | 2015-07-30
2017-02-15 | 2013 | Air National Guard | Unspecified Minor Military Construction | Oregon | United States | TQKD139018 | Relocate Base Boundary Fence |  |  |  | 2015-02-02 | 2015-08-01 | 2016-02-28 | 79% | 2016-01-01
2016-09-14 | 2012 | Air National Guard | Unspecified Minor Military Construction | Puerto Rico | Puerto Rico | TUMR109004 | Joint Force HQ - ANG Share Fort Buchanan |  |  |  | 2013-11-25 | 2015-10-06 | 2017-03-31 | 98% | 2016-03-18
2017-02-15 | 2014 | Air National Guard | Major Military Construction | Rhode Island | United States | TWLR129077 | C-130J Flight Simulator Training Facility |  |  |  | 2015-03-15 | 2015-12-14 | 2017-01-31 | 95% | 2016-10-31
2017-02-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Missouri | United States | ULYB112022 | Security Forces Admin and Storage Facility |  |  |  | 2014-10-29 | 2015-10-12 | 2017-09-30 | 99% | 2016-03-04
2017-02-15 | 2014 | Air National Guard | Major Military Construction | Ohio | United States | WAAR109002 | Alter Intelligence Operations Facility |  |  |  | 2014-12-01 | 2015-12-01 | 2016-12-31 | 99% | 2016-02-10
2016-09-14 | 2012 | Air National Guard | Unspecified Minor Military Construction | Ohio | United States | WAAR129078 | Relocate Main Gate |  |  |  | 2013-08-27 | 2014-02-23 | 2016-06-30 | 95% | 2014-10-31
2016-09-14 | 2012 | Air National Guard | Unspecified Minor Military Construction | New York | United States | WKVB099052 | Add to Fire Station |  |  |  | 2015-06-26 | 2016-04-23 | 2016-10-14 | 18% | 2016-10-14
2017-02-15 | 2016 | Air National Guard | Major Military Construction | Georgia | United States | XDQU949500 | C-130 Squadron Operations Facility |  |  |  | 2016-11-14 | 2017-11-08 | 2018-01-31 | 3% | 2017-12-01
2017-02-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Oklahoma | United States | XHZG129946 | Add to Fire Crash and Rescue Station, Building 403 |  |  |  | 2014-08-20 | 2015-08-15 | 2016-12-30 | 99% | 2015-10-08
2016-10-12 | 2015 | Air National Guard | Major Military Construction | Pennsylvania | United States | ZAWA159061 | RPA Operations Center |  |  |  | 2015-07-20 | 2016-02-15 | 2016-07-22 | 80% | 2016-07-22
2017-01-31 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 1235 | Physical Fitness Facility |  |  |  | 2012-07-12 | 2014-04-10 | 2016-03-31 | 95%
2017-01-31 | 2011 | Army Active | Major Military Construction | Colorado | United States | 13852 | Simulations Center |  |  |  | 2011-11-04 | 2016-07-23 | 2016-09-30 | 99% | 2016-12-12
2017-01-31 | 2012 | Army Active | Major Military Construction | Louisiana | United States | 17220 | Fire Station |  |  |  | 2013-11-06 | 2015-11-11 | 2017-01-19 | 96% | 2017-01-19
2017-01-31 | 2012 | Army Active | Major Military Construction | Kansas | United States | 2728 | Physical Fitness Facility |  |  |  | 2012-03-29 | 2017-02-08 | 2017-03-03 | 99%
2017-01-31 | 2013 | Army Active | Major Military Construction | Virginia | United States | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2013-10-15 | 2017-05-03 | 2017-05-23 | 80%
2017-01-31 | 2015 | Army Active | Major Military Construction | Virginia | United States | 41449 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  | 2016-10-17 | 2018-10-07 | 2018-12-18 | 0%
2017-01-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 45116 | Aircraft Component Maintenance Shop |  |  |  | 2013-08-08 | 2016-12-30 | 2016-12-30 | 92%
2017-01-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 5034 | Vehicle Maintenance Facility |  |  |  | 2013-01-24 | 2014-07-18 | 2017-01-31 | 95% | 2017-01-31
2017-01-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 51519 | Ballistic Evaluation Center |  |  |  | 2012-12-04 | 2015-02-15 | 2017-03-31 | 98%
2017-01-31 | 2014 | Army Active | Major Military Construction | Georgia | United States | 51868 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2015-01-06 | 2016-12-26 | 2017-05-04 | 79%
2017-01-31 | 2015 | Army Active | Major Military Construction | South Carolina | United States | 51937 | Trainee Barracks Complex 3, Ph1 |  |  |  | 2016-03-17 | 2018-03-17 | 2018-05-01 | 26%
2017-01-31 | 2014 | Army Active | Major Military Construction | Virginia | United States | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  | 2014-10-09 | 2017-12-09 | 2017-12-09 | 88%
2017-01-31 | 2011 | Army Active | Major Military Construction | California | United States | 53789 | Advanced Individual Training Barracks |  |  |  | 2013-10-22 | 2015-01-05 | 2017-02-02 | 32%
2017-01-31 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 55121 | Aerial Gunnery Range |  |  |  | 2015-12-31 | 2017-12-30 | 2018-08-13 | 45%
2017-01-31 | 2012 | Army Active | Major Military Construction |  | Germany | 55985 | Chapel |  |  |  | 2013-11-21 | 2016-03-23 | 2017-04-25 | 97%
2017-01-31 | 2011 | Army Active | Major Military Construction | Hawaii | United States | 56024 | Flood Mitigation |  |  |  | 2012-10-17 | 2014-10-14 | 2016-11-17 | 99%
2017-01-31 | 2012 | Army Active | Major Military Construction |  | Germany | 57594 | Satellite Communications Center |  |  |  | 2014-03-14 | 2017-10-13 | 2017-10-13 | 99% | 2016-12-27
2016-12-31 | 2010 | Army Active | Major Military Construction | Maryland | United States | 58625 | Satellite Communications Facility |  |  |  | 2010-03-06 | 2012-09-01 | 2016-07-03 | 100% | 2016-11-04
2017-01-31 | 2011 | Army Active | Major Military Construction | Kentucky | United States | 58675 | Mout Collective Training Facility |  |  |  | 2011-07-06 | 2016-10-15 | 2016-09-09 | 99% | 2016-11-22
2017-01-31 | 2008 | Army Active | Major Military Construction |  | Korea, South | 58784 | Barracks Complex |  |  |  | 2008-04-22 | 2014-09-07 | 2017-04-30 | 96%
2017-01-31 | 2013 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility |  |  |  | 2016-04-15 | 2019-10-12 | 2019-12-01 | 16%
2017-01-31 | 2017 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility, Incr 2 | 86285 |  |  | 2016-04-15 | 2019-10-12 | 2019-12-01 | 16%
2017-01-31 | 2012 | Army Active | Major Military Construction |  | Germany | 58925 | Satellite Communications Center |  |  |  | 2014-03-14 | 2017-10-13 | 2017-10-13 | 94%
2017-01-31 | 2011 | Army Active | Major Military Construction | New York | United States | 59044 | Science Facility, Ph 2 |  |  |  | 2011-11-17 | 2015-11-14 | 2017-08-31 | 99%
2017-01-31 | 2014 | Army Active | Major Military Construction |  | Marshall Islands | 59779 | Pier |  |  |  | 2016-08-17 | 2020-06-10 | 2020-06-10 | 0%
2017-01-31 | 2011 | Army Active | Major Military Construction |  | Germany | 60555 | Information Processing Center |  |  |  | 2012-06-18 | 2014-06-01 | 2017-01-31 | 99% | 2016-11-08
2017-01-31 | 2012 | Army Active | Major Military Construction |  | Germany | 61842 | Access Control Point |  |  |  | 2015-05-11 | 2016-12-01 | 2017-02-15 | 90%
2017-01-31 | 2014 | Army Active | Major Military Construction | Maryland | United States | 62204 | Hazardous Material Storage Building |  |  |  | 2016-02-23 | 2017-08-16 | 2017-08-16 | 14%
2017-01-31 | 2012 | Army Active | Major Military Construction | California | United States | 62657 | Water Treatment and Distro System |  |  |  | 2012-10-19 | 2015-10-19 | 2016-10-25 | 98% | 2017-01-23
2017-01-31 | 2013 | Army Active | Major Military Construction |  | Japan | 62783 | Satellite Communications Facility |  |  |  | 2014-11-21 | 2021-06-09 | 2021-12-06 | 21%
2017-01-31 | 2011 | Army Active | Major Military Construction | California | United States | 63015 | Satellite Communications Facility |  |  |  | 2011-09-21 | 2016-06-30 | 2016-10-22 | 52% | 2017-01-20
2017-01-31 | 2010 | Army Active | Major Military Construction | Virginia | United States | 63571 | Road and Access Control Point |  |  |  | 2016-04-28 | 2017-08-01 | 2017-10-29 | 11%
2017-01-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 64014 | Battalion Complex |  | 600000 | 78196 | 2012-07-25 | 2015-04-08 | 2016-10-24 | 99% | 2016-10-24
2017-01-31 | 2012 | Army Active | Major Military Construction | Missouri | United States | 64365 | Vehicle Maintenance Facility |  |  |  | 2012-09-18 | 2014-08-25 | 2017-02-17 | 98% | 2016-05-12
2017-01-31 | 2013 | Army Active | Major Military Construction | Washington | United States | 64456 | Battalion Complex |  |  |  | 2013-06-26 | 2018-07-05 | 2018-07-05 | 46%
2017-01-31 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 64753 | Vehicle Maintenance Facility |  |  |  | 2012-07-19 | 2014-04-11 | 2016-04-14 | 98%
2017-01-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 65374 | Operational Readiness Training Complex |  |  |  | 2012-09-05 | 2017-07-10 | 2017-07-10 | 98%
2017-01-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 65679 | Vehicle Maintenance Shop |  |  |  | 2013-06-27 | 2016-08-06 | 2016-10-13 | 98% | 2016-10-13
2017-01-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 65755 | Brigade Complex |  |  |  | 2012-12-12 | 2018-01-06 | 2017-12-01 | 71%
2017-01-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 66023 | Automated Infantry Platoon Battle Course |  |  |  | 2014-07-08 | 2016-09-09 | 2017-01-20 | 97% | 2016-10-22
2017-01-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 66099 | Battalion Complex Facilities |  |  |  | 2013-07-01 | 2016-05-05 | 2017-02-28 | 98% | 2016-11-04
2017-01-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 66206 | Infrastructure, Ph 1 |  |  |  | 2012-09-17 | 2017-06-10 | 2017-05-27 | 96%
2017-01-31 | 2011 | Army Active | Major Military Construction |  | Germany | 66595 | Barracks Complex |  |  |  | 2015-03-23 | 2017-09-28 | 2017-09-28 | 81%
2017-01-31 | 2009 | Army Active | Major Military Construction | New Jersey | United States | 66725 | Ballistic Evaluation Facility Ph 1 |  |  |  | 2012-12-04 | 2014-06-04 | 2017-03-31 | 91%
2017-01-31 | 2010 | Army Active | Major Military Construction | New Jersey | United States | 66726 | Ballistic Evaluation Facility, Ph 2 |  |  |  | 2012-12-04 | 2014-06-04 | 2017-03-31 | 96%
2017-01-31 | 2011 | Army Active | Major Military Construction |  | Germany | 66834 | Vehicle Maintenance Shop |  |  |  | 2011-12-12 | 2013-12-18 | 2016-01-15 | 97% | 2016-11-18
2017-01-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 67116 | Aviation Battalion Complex |  |  |  | 2014-04-23 | 2016-09-06 | 2016-09-26 | 99% | 2016-10-03
2017-01-31 | 2014 | Army Active | Major Military Construction | Hawaii | United States | 67157 | Command and Control Facility - Admin |  |  |  | 2015-09-25 | 2017-12-13 | 2018-01-13 | 27%
2017-01-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 68050 | Command and Control Facility |  |  |  | 2016-02-24 | 2018-06-13 | 2018-09-25 | 11%
2016-11-30 | 2011 | Army Active | Major Military Construction |  | Germany | 68074 | Construct New ACP |  |  |  | 2014-03-05 | 2014-12-12 | 2015-01-09 | 99%
2017-01-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 68530 | Barracks |  |  |  | 2015-11-18 | 2017-05-11 | 2017-05-11 | 9%
2016-11-30 | 2011 | Army Active | Major Military Construction |  | Germany | 68606 | Barracks |  |  |  | 2012-10-12 | 2014-05-25 | 2014-06-16 | 98%
2017-01-31 | 2011 | Army Active | Major Military Construction |  | Germany | 68866 | Sensitive Compartmented Information Fac |  |  |  | 2013-02-13 | 2015-09-19 | 2017-07-31 | 85%
2017-01-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 68993 | Electronics Maintenance Facility |  |  |  | 2012-08-08 | 2013-12-16 | 2016-11-12 | 99% | 2014-06-27
2017-01-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 69286 | Infrastructure |  |  |  | 2012-08-20 | 2013-09-13 | 2016-11-12 | 72% | 2012-10-22
2017-01-31 | 2012 | Army Active | Major Military Construction | Hawaii | United States | 69489 | Combat Aviation Brigade Complex, Ph 1 |  |  |  | 2012-07-30 | 2015-05-27 | 2017-06-01 | 90%
2017-01-31 | 2015 | Army Active | Major Military Construction | Pennsylvania | United States | 69649 | Rebuild Shop |  |  |  | 2015-11-12 | 2017-07-24 | 2017-07-18 | 39%
2017-01-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 69828 | Unmanned Aerial Vehicle Maintenance Hangar |  |  |  | 2014-08-27 | 2016-01-19 | 2016-11-07 | 98% | 2016-06-29
2017-01-31 | 2012 | Army Active | Major Military Construction | North Carolina | United States | 70751 | Brigade Complex Facilities |  | 1500000 | 77405 | 2012-02-29 | 2017-01-08 | 2017-01-05 | 100%
2017-01-31 | 2012 | Army Active | Major Military Construction | Virginia | United States | 71149 | Road and Infrastucture Improvements |  |  |  | 2016-08-17 | 2017-09-15 | 2018-07-31 | 1%
2017-01-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 71221 | Fire Station |  |  |  | 2014-08-27 | 2016-02-18 | 2016-09-28 | 99% | 2016-10-24
2017-01-31 | 2010 | Army Active | Military Family Housing |  | Germany | 71421 | Family Housing Replacement Construction |  |  |  | 2015-04-07 | 2017-04-23 | 2018-09-29 | 10%
2017-01-31 | 2011 | Army Active | Military Family Housing |  | Germany | 71422 | Family Housing Replacement Construction |  |  |  | 2015-04-07 | 2018-07-27 | 2018-09-29 | 19%
2016-11-30 | 2011 | Army Active | Major Military Construction | New York | United States | 71472 | Brigade Complex Ph 1 |  | 9250000 | 62783 | 2011-08-05 | 2013-03-07 | 2014-07-23 | 99% | 2016-10-31
2017-01-31 | 2010 | Army Active | Major Military Construction |  | Kuwait | 71485 | APS Warehouses |  | 11339000 | 58925, 62783 | 2013-10-25 | 2015-10-30 | 2016-11-07 | 99% | 2016-11-07
2017-01-31 | 2014 | Army Active | Major Military Construction | Missouri | United States | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  |  |  | 2014-08-05 | 2016-08-04 | 2017-02-05 | 93%
2017-01-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 71675 | Flight Equipment Complex |  |  |  | 2014-01-15 | 2016-01-15 | 2017-08-31 | 99%
2017-01-31 | 2015 | Army Active | Major Military Construction | Virginia | United States | 73272 | Tactical Vehicle Hardstand |  |  |  | 2015-10-21 | 2016-10-20 | 2017-08-18 | 23%
2017-01-31 | 2014 | Army Active | Major Military Construction | Maryland | United States | 73384 | Entry Control Point |  |  |  | 2016-03-31 | 2017-03-31 | 2017-03-31 | 76%
2017-01-31 | 2015 | Army Active | Major Military Construction | Kentucky | United States | 73542 | Unmanned Aerial Vehicle Hangar |  | 3225000 | 85811 | 2015-09-04 | 2017-04-26 | 2017-06-01 | 81%
2017-01-31 | 2014 | Army Active | Major Military Construction | Texas | United States | 74638 | Control Tower |  |  |  | 2015-04-28 | 2017-01-02 | 2017-04-21 | 85%
2017-01-31 | 2014 | Army Active | Military Family Housing | Wisconsin | United States | 74861 | Family Housing New Construction |  |  |  | 2014-08-20 | 2016-08-09 | 2017-06-30 | 75% | 2016-10-03
2017-01-31 | 2013 | Army Active | Major Military Construction | Washington | United States | 75165 | Waste Water Treatment Plant |  |  |  | 2014-03-03 | 2016-03-02 | 2016-10-19 | 98% | 2016-10-19
2017-01-31 | 2015 | Army Active | Military Family Housing | Illinois | United States | 75536 | Family Housing New Construction |  |  |  | 2016-09-13 | 2018-03-07 | 2018-03-07 | 0%
2017-01-31 | 2016 | Army Active | Military Family Housing | Illinois | United States | 75538 | Family Housing Replacement Construction |  |  |  | 2016-10-17 | 2018-04-10 | 2018-04-27 | 0%
2017-01-31 | 2016 | Army Active | Major Military Construction | Alaska | United States | 75966 | Physical Readiness Training Facility |  |  |  | 2016-07-28 | 2017-12-10 | 2017-12-08 | 0%
2017-01-31 | 2014 | Army Active | Major Military Construction | Kansas | United States | 76024 | Simulations Center |  |  |  | 2014-09-02 | 2016-02-24 | 2017-03-30 | 90%
2017-01-31 | 2013 | Army Active | Major Military Construction | California | United States | 76086 | Lightning Protection System |  |  |  | 2014-09-16 | 2018-05-30 | 2018-05-30 | 55%
2017-01-31 | 2015 | Army Active | Major Military Construction | California | United States | 76087 | General Purpose Maintenance Shop |  |  |  | 2015-11-30 | 2017-03-31 | 2017-05-20 | 18%
2017-01-31 | 2013 | Army Active | Major Military Construction |  | Korea, South | 76196 | Battalion Headquarters Complex |  |  |  | 2013-05-14 | 2015-06-09 | 2017-04-28 | 95%
2017-01-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76586 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2017-01-13 | 94%
2017-01-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76587 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2017-01-13 | 93%
2016-10-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 76601 | Aviation Storage Hangar |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 91%
2017-01-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76767 | Aviation Unit Complex, Ph 1A |  |  |  | 2012-07-09 | 2017-01-18 | 2017-01-23 | 99% | 2017-01-23
2017-01-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76768 | Aviation Complex, Ph 1B |  | 25700000 | 49472, 68050, 71149 | 2012-11-29 | 2017-05-06 | 2017-05-06 | 98%
2017-01-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 76776 | Airfield Operations Complex |  |  |  | 2015-05-18 | 2018-05-11 | 2018-05-11 | 60%
2017-01-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 76777 | Aircraft Maintenance Hangar |  |  |  | 2014-09-23 | 2017-07-06 | 2017-11-06 | 68%
2017-01-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76903 | Combat Aviation Brigade Barracks |  |  |  | 2014-06-26 | 2017-01-13 | 2017-04-13 | 78%
2017-01-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 77187 | Vehicle Maintenance Facility |  |  |  | 2012-06-22 | 2016-12-07 | 2017-01-06 | 91% | 2016-12-08
2017-01-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77262 | Headquarters Building |  |  |  | 2014-08-21 | 2016-03-31 | 2017-06-01 | 92%
2017-01-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77304 | Aircraft Maintenance Hangar |  |  |  | 2014-08-18 | 2016-08-22 | 2017-04-30 | 95% | 2017-01-04
2017-01-31 | 2015 | Army Active | Major Military Construction | Colorado | United States | 77305 | Aircraft Maintenance Hangar |  |  |  | 2015-06-16 | 2016-06-15 | 2016-09-12 | 97% | 2017-01-27
2017-01-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77405 | Aircraft Maintenance Hangar |  |  |  | 2014-07-22 | 2016-08-22 | 2017-08-31 | 73%
2017-01-31 | 2013 | Army Active | Major Military Construction | Georgia | United States | 77419 | Ground Source Heat Transfer System |  |  |  | 2015-01-06 | 2016-12-26 | 2017-05-04 | 93%
2017-01-31 | 2013 | Army Active | Major Military Construction | District Of Columbia | United States | 78054 | Vehicle Storage Building, Installation |  |  |  | 2015-04-03 | 2016-09-24 | 2017-02-21 | 50%
2017-01-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 78196 | Aviation Battalion Complex |  |  |  | 2016-01-13 | 2018-04-05 | 2018-04-05 | 29%
2017-01-31 | 2016 | Army Active | Military Family Housing Improvement |  | Germany | 78366 | Family Housing Improvements |  |  |  | 2016-10-25 | 2017-12-09 | 2018-02-07 | 0%
2017-01-31 | 2012 | Army Active | Military Family Housing Improvement |  | Germany | 78475 | Family Housing Improvements |  |  |  | 2015-01-16 | 2016-09-27 | 2017-02-24 | 91%
2017-01-31 | 2012 | Army Active | Military Family Housing |  | Germany | 78505 | Family Housing New Construction |  |  |  | 2013-08-07 | 2015-09-14 | 2016-02-17 | 93%
2017-01-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 79618 | Simulator Building |  |  |  | 2014-08-20 | 2016-02-11 | 2017-03-06 | 89%
2017-01-31 | 2012 | Army Active | Major Military Construction |  | Unspecified World Wide | 79749 | Forward Operating Site |  |  |  | 2012-07-25 | 2014-11-30 | 2017-02-15 | 91%
2017-01-31 | 2013 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks |  |  |  | 2013-08-26 | 2016-08-30 | 2017-03-03 | 97%
2017-01-31 | 2014 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 2 | 81186 |  |  | 2013-08-26 | 2016-08-30 | 2017-03-03 | 97%
2017-01-31 | 2015 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 3 | 81187 |  |  | 2013-08-26 | 2016-08-30 | 2017-03-03 | 97%
2017-01-31 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 80112 | Unmanned Aerial Vehicle Complex |  |  |  | 2015-05-26 | 2016-07-19 | 2016-11-01 | 98% | 2016-11-01
2017-01-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 80113 | Unmanned Aerial Vehicle Complex |  |  |  | 2013-10-07 | 2016-01-04 | 2016-11-07 | 100% | 2016-06-29
2017-01-31 | 2012 | Army Active | Unspecified Minor Military Construction | Maryland | United States | 80231 | Replace Oil Water Separators |  |  |  | 2014-11-03 | 2015-11-03 | 2017-07-12 | 18%
2017-01-31 | 2013 | Army Active | Major Military Construction | New York | United States | 80246 | Aircraft Maintenance Hangar |  |  |  | 2013-06-27 | 2015-12-02 | 2017-03-01 | 94%
2017-01-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 80433 | Central Energy Plant |  |  |  | 2015-10-27 | 2016-10-26 | 2017-03-01 | 87%
2017-01-31 | 2015 | Army Active | Unspecified Minor Military Construction | Mississippi | United States | 80666 | Precision Machine Shop |  |  |  | 2016-10-26 | 2018-04-19 | 2018-04-19 | 0%
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Hawaii | United States | 80992 | Upgrade Power Distribution |  |  |  | 2015-04-29 | 2016-10-20 | 2016-11-19 | 89%
2017-01-31 | 2014 | Army Active | Major Military Construction | Texas | United States | 81155 | Unmanned Aerial Vehicle Complex |  |  |  | 2014-12-18 | 2016-04-11 | 2016-11-04 | 99% | 2016-11-03
2017-01-31 | 2015 | Army Active | Military Family Housing |  | Korea, South | 81230 | Family Housing New Construction |  |  |  | 2015-08-19 | 2018-04-28 | 2018-07-08 | 11%
2017-01-31 | 2015 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81242 | General Purpose Maintenance Shop |  |  |  | 2015-10-28 | 2016-10-27 | 2017-07-14 | 10%
2017-01-31 | 2015 | Army Active | Major Military Construction | New York | United States | 81349 | Unmanned Aerial Vehicle Hangar |  | 4275000 | 85811 | 2015-06-22 | 2016-12-18 | 2017-04-15 | 81%
2017-01-31 | 2015 | Army Active | Major Military Construction | Colorado | United States | 81357 | Unmanned Aerial Vehicle Hangar |  |  |  | 2014-07-01 | 2017-01-18 | 2017-05-31 | 68%
2017-01-31 | 2015 | Army Active | Major Military Construction | California | United States | 81372 | Unmanned Aerial Vehicle Hangar |  |  |  | 2015-11-18 | 2017-12-16 | 2017-12-16 | 34%
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81424 | Tracking Equipment Support Fac |  |  |  | 2015-11-10 | 2017-02-02 | 2017-03-03 | 82%
2017-01-31 | 2016 | Army Active | Military Family Housing |  | Korea, South | 81427 | Family Housing New Construction |  |  |  | 2016-09-29 | 2019-02-24 | 2019-02-24 | 0%
2017-01-31 | 2015 | Army Active | Unspecified Minor Military Construction | New Mexico | United States | 81658 | Organizational Storage Building |  |  |  | 2017-01-31 | 2017-10-28 | 2017-10-28 | 1%
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Oklahoma | United States | 82394 | Decontamination Facility |  |  |  | 2016-02-18 | 2017-02-12 | 2017-05-03 | 51%
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 85260 | Secure Operations Center |  |  |  | 2014-11-05 | 2015-11-05 | 2016-01-13 | 99% | 2017-01-20
2017-01-31 | 2016 | Army Active | Major Military Construction | Georgia | United States | 85811 | Command and Control Facility |  |  |  | 2016-11-02 | 2018-07-25 | 2018-07-25 | 1%
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction |  | Germany | 85817 | CANTONMENT AREA ROADS, PAVED |  |  |  | 2016-04-07 | 2016-08-25 | 2016-12-22 | 66%
2017-01-31 | 2014 | Army Active | Major Military Construction | California | United States | 86033 | Water Well, Potable |  |  |  | 2015-11-13 | 2016-09-08 | 2016-12-14 | 97% | 2016-12-15
2017-01-31 | 2015 | Army Active | Unspecified Minor Military Construction | Colorado | United States | 86573 | Wash Platform |  |  |  | 2016-08-03 | 2018-01-25 | 2018-01-25 | 7%
2017-01-31 | 2015 | Army Active | Unspecified Minor Military Construction |  | Honduras | 86859 | Continuing Education Facility |  |  |  | 2016-11-22 | 2018-04-26 | 2018-04-26 | 0%
2017-01-31 | 2016 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 89734 | Administrative Building, General Purpose |  |  |  | 2016-10-18 | 2017-05-16 | 2017-05-16 | 28%
2017-01-31 | 2015 | Army Active | Major Military Construction | Kentucky | United States | 8984 | Shipping and Receiving Building |  |  |  | 2016-10-18 | 2018-04-11 | 2018-04-11 | 0%
2016-12-06 | 2013 | Army National Guard | Major Military Construction | Alabama | United States | 010278 | Live Fire Shoot House |  |  |  | 2013-11-12 | 2014-11-11 | 2015-06-15 | 100% | 2016-06-13
2017-02-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | Alabama | United States | 011007 | National Guard Readiness Center, Add/Alt |  |  |  | 2013-12-31 | 2014-10-01 | 2017-03-01 | 98% | 2017-03-01
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Alabama | United States | 011014 | National Guard Readiness Center Add/Alt |  |  |  | 2014-10-07 | 2015-12-10 | 2016-04-01 | 100% | 2016-09-01
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Alabama | United States | 011317 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-11-07 | 2017-09-15 | 2017-09-15 | 1% | 2017-09-15
2017-02-06 | 2015 | Army National Guard | Unspecified Minor Military Construction | Arizona | United States | 040730 | Water/Supply Treatment Building |  |  |  | 2016-11-07 | 2017-06-30 | 2017-06-30 | 1% | 2017-06-30
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Arkansas | United States | 050182 | Scout REECE Gunnery Complex |  |  |  | 2014-12-01 | 2016-12-01 | 2017-06-30 | 80% | 2016-12-01
2017-02-06 | 2013 | Army National Guard | Major Military Construction | California | United States | 060413 | Maneuver Area Training & Equipment Site Ph 3 |  |  |  | 2013-10-21 | 2014-10-01 | 2016-02-29 | 99% | 2016-02-29
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Connecticut | United States | 090043 | Combined Support Maintenance Shop |  |  |  | 2014-04-26 | 2015-10-01 | 2016-08-16 | 100% | 2015-10-01
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Connecticut | United States | 090071 | Ready Building (CST-WMD) |  |  |  | 2016-11-26 | 2018-04-06 | 2018-04-06 | 1% | 2018-04-06
2017-02-06 | 2014 | Army National Guard | Unspecified Minor Military Construction | Connecticut | United States | 090088 | Storage Building General Purpose, Installation |  |  |  | 2015-12-01 | 2016-11-30 | 2016-12-31 | 95% | 2016-12-31
2016-12-06 | 2013 | Army National Guard | Major Military Construction | Delaware | United States | 100010 | Regional Training Institute Ph1 |  |  |  | 2013-09-23 | 2014-09-23 | 2014-12-04 | 100% | 2014-12-15
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Delaware | United States | 100082 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-10-01 | 2017-08-25 | 2018-02-28 | 10% | 2017-08-25
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Florida | United States | 120102 | Readiness Center |  |  |  | 2014-01-21 | 2015-07-26 | 2017-02-02 | 99% | 2016-10-04
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Florida | United States | 120173 | National Guard Readiness Center |  |  |  | 2016-11-01 | 2018-07-30 | 2018-03-31 | 1% | 2018-07-30
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Florida | United States | 120195 | Ready Building |  |  |  | 2015-05-11 | 2016-04-05 | 2016-08-24 | 100% | 2016-08-24
2017-02-06 | 2015 | Army National Guard | Unspecified Minor Military Construction | Florida | United States | 120212 | Organizational Vehicle Parking, Paved |  |  |  | 2016-10-17 | 2017-10-13 | 2017-10-13 | 1% | 2017-10-13
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Georgia | United States | 130130 | Tactical Aerial Unmanned Systems |  |  |  | 2017-04-30 | 2017-11-03 | 2017-11-03 | 1% | 2017-11-03
2017-02-06 | 2014 | Army National Guard | Unspecified Minor Military Construction | Guam | Guam | 140055 | Aircraft Maintenance Bay |  |  |  | 2016-10-24 | 2017-09-29 | 2017-09-29 | 98% | 2017-09-29
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Hawaii | United States | 150023 | Army Aviation Support Facility Ph1 |  |  |  | 2014-11-12 | 2016-11-01 | 2017-01-31 | 99% | 2017-01-31
2017-01-06 | 2013 | Army National Guard | Major Military Construction | Idaho | United States | 160100 | ORTC (Barracks) Ph2 |  |  |  | 2013-10-07 | 2014-08-01 | 2016-06-24 | 100% | 2014-08-01
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Illinois | United States | 170033 | National Guard Readiness Center |  |  |  | 2014-08-14 | 2016-10-01 | 2017-10-01 | 94% | 2017-10-01
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Illinois | United States | 170127 | Aircraft Maintenance Hangar |  |  |  | 2014-08-14 | 2017-10-01 | 2017-03-12 | 80% | 2017-10-01
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Illinois | United States | 171001 | Basic 10M-25M Firing Range (Zero) |  |  |  | 2016-11-01 | 2018-05-11 | 2018-05-11 | 25% | 2018-05-11
2017-02-06 | 2016 | Army National Guard | Unspecified Minor Military Construction | Iowa | United States | 190192 | Combined Support Maintenance Shop Add/Alt |  |  |  | 2016-10-24 | 2017-07-31 | 2017-07-31 | 1% | 2017-07-31
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Kansas | United States | 200112 | Automated Combat Pistol/Military Police Firearms Qualification Course |  |  |  | 2016-11-01 | 2017-03-01 | 2017-03-15 | 45% | 2017-03-15
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Kansas | United States | 200113 | Modified Record Fire Range |  |  |  | 2016-11-01 | 2017-03-01 | 2017-03-15 | 45% | 2017-03-15
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Kentucky | United States | 210001 | Army Aviation Support Facility |  |  |  | 2013-07-08 | 2014-10-01 | 2015-08-16 | 99% | 2015-10-21
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Louisiana | United States | 220241 | National Guard Readiness Center |  |  |  | 2014-09-22 | 2016-11-30 | 2016-11-30 | 99% | 2016-11-30
2017-02-06 | 2012 | Army National Guard | Major Military Construction | Maine | United States | 230046 | Readiness Center |  |  |  | 2012-09-26 | 2014-07-11 | 2016-12-30 | 99% | 2015-08-28
2017-02-06 | 2015 | Army National Guard | Major Military Construction | Maine | United States | 230113 | National Guard Reserve Center |  |  |  | 2015-08-20 | 2017-08-03 | 2017-08-03 | 55% | 2017-08-03
2017-02-06 | 2012 | Army National Guard | Major Military Construction | Maryland | United States | 240017 | Readiness Center Add/Alt |  | 3160000 | 170127 | 2012-10-01 | 2014-09-22 | 2016-11-25 | 99% | 2016-02-06
2017-02-06 | 2015 | Army National Guard | Major Military Construction | Maryland | United States | 240165 | National Guard Readiness Center |  |  |  | 2015-10-19 | 2017-10-29 | 2017-12-30 | 10% | 2017-10-29
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Maryland | United States | 240173 | National Guard Readiness Center |  |  |  | 2017-03-27 | 2018-04-06 | 2018-04-06 | 1% | 2018-04-06
2017-02-06 | 2011 | Army National Guard | Major Military Construction | Maryland | United States | 240186 | Tactical Unmanned Aircraft System Facility |  |  |  | 2012-06-01 | 2013-06-15 | 2014-11-21 | 99% | 2014-12-06
2017-02-06 | 2012 | Army National Guard | Major Military Construction | Maryland | United States | 240187 | Readiness Center Add/Alt |  | 1030000 | 120102 | 2012-10-01 | 2014-09-22 | 2015-03-20 | 100% | 2015-03-01
2017-02-06 | 2012 | Army National Guard | Major Military Construction | Maryland | United States | 240193 | Readiness Center |  |  |  | 2012-10-01 | 2014-09-22 | 2016-06-01 | 99% | 2016-06-01
2017-02-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | Maryland | United States | 240194 | Combat Pistol/MP Firearms Qualification Course |  |  |  | 2015-06-01 | 2014-09-22 | 2016-03-29 | 100% | 2016-03-29
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Massachusetts | United States | 250065 | Unit Training Equipment Site |  |  |  | 2014-04-07 | 2015-07-30 | 2017-05-17 | 84% | 2015-07-30
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Massachusetts | United States | 250095 | Enlisted Barracks, Transient Training Addition |  |  |  | 2014-09-15 | 2016-11-01 | 2017-01-16 | 99% | 2016-11-01
2017-02-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | Massachusetts | United States | 250196 | Water Well, Non-Potable |  |  |  | 2013-06-03 | 2013-12-01 | 2013-12-01 | 95% | 2013-12-02
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Michigan | United States | 260051 | Enlisted Barracks, Transient Training |  |  |  | 2014-08-11 | 2016-10-01 | 2016-10-01 | 97% | 2016-10-01
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Minnesota | United States | 270014 | National Guard Readiness Center |  |  |  | 2014-10-22 | 2016-04-15 | 2016-12-31 | 99% | 2016-12-31
2016-12-06 | 2013 | Army National Guard | Major Military Construction | Minnesota | United States | 270236 | Scout Reconnaissance Range |  |  |  | 2013-09-23 | 2015-10-01 | 2016-06-30 | 100% | 2015-08-01
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Mississippi | United States | 280272 | National Guard Readiness Center |  |  |  | 2014-09-03 | 2016-04-30 | 2016-12-01 | 88% | 2016-04-30
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Mississippi | United States | 280327 | Aviation Classification and Repair Activity Depot |  |  |  | 2016-11-28 | 2019-06-28 | 2019-06-28 | 1% | 2019-06-28
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Mississippi | United States | 280423 | Water Supply/Treatment Building, Potable |  |  |  | 2014-08-27 | 2016-11-30 | 2016-11-30 | 10% | 2016-11-30
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Mississippi | United States | 281501 | National Guard Readiness Center |  |  |  | 2017-03-10 | 2018-02-09 | 2018-02-09 | 1% | 2018-02-09
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Missouri | United States | 290191 | National Guard Vehicle Maintenance Shop |  |  |  | 2015-06-26 | 2015-06-26 | 2015-12-31 | 99% | 2015-10-27
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Missouri | United States | 290221 | Aircraft Maintenance Hangar |  |  |  | 2015-10-06 | 2015-10-06 | 2015-10-06 | 99% | 2015-10-05
2017-02-06 | 2015 | Army National Guard | Major Military Construction | Montana | United States | 300128 | National Guard Readiness Center Add/Alt |  |  |  | 2015-05-13 | 2017-05-13 | 2017-05-30 | 76% | 2017-06-03
2017-02-06 | 2015 | Army National Guard | Major Military Construction | Montana | United States | 300216 | Dining Facility Transient Training |  |  |  | 2015-10-19 | 2017-06-24 | 2017-01-31 | 99% | 2017-01-31
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Nevada | United States | 320075 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-10-24 | 2017-06-23 | 2017-07-22 | 1% | 2017-07-22
2017-02-06 | 2012 | Army National Guard | Unspecified Minor Military Construction | Nevada | United States | 320141 | Clark County Armory, Add/Alt |  |  |  | 2016-04-04 | 2017-06-23 | 2017-06-23 | 48% | 2016-07-23
2017-02-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | New Hampshire | United States | 330053 | National Guard Readiness Center, Add/Alt |  |  |  | 2016-02-16 | 2017-02-15 | 2017-02-15 | 95% | 2018-04-02
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340110 | Regional Training Institute |  |  |  | 2014-10-15 | 2016-02-12 | 2017-02-10 | 98% | 2017-02-10
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340124 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-10-21 | 2017-09-23 | 2018-01-17 | 1% | 2018-01-17
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340126 | Troop Dispensary/Health Clinic |  |  |  | 2016-08-01 | 2017-07-06 | 2017-07-06 | 8% | 2017-07-06
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340127 | Engineering/Housing Maintenance Shop |  |  |  | 2016-10-21 | 2017-09-23 | 2017-09-23 | 1% | 2017-09-23
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340128 | General Instruction Building |  |  |  | 2016-08-01 | 2017-07-06 | 2017-07-06 | 8% | 2017-07-06
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340129 | Power Plant Building |  |  |  | 2016-10-14 | 2017-03-03 | 2017-03-03 | 3% | 2017-03-13
2017-02-06 | 2015 | Army National Guard | Major Military Construction | New Mexico | United States | 350029 | National Guard Readiness Center Add/Alt |  |  |  | 2016-06-20 | 2018-01-01 | 2018-01-01 | 1% | 2018-01-01
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New York | United States | 360139 | Combined Support Maintenance Shop |  |  |  | 2016-04-04 | 2017-12-30 | 2017-06-30 | 76% | 2018-08-01
2017-02-06 | 2014 | Army National Guard | Major Military Construction | New York | United States | 360161 | National Guard Readiness Center Alteration |  |  |  | 2014-10-20 | 2016-09-29 | 2017-05-03 | 74% | 2017-06-15
2017-02-06 | 2013 | Army National Guard | Major Military Construction | New York | United States | 361103 | Access Control Point |  |  |  | 2016-03-07 | 2016-11-05 | 2017-01-31 | 98% | 2017-01-31
2016-12-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | North Dakota | United States | 380053 | National Guard Vehicle Maintenance Shop Addition |  |  |  | 2014-10-06 | 2015-10-30 | 2015-12-11 | 100% | 2015-10-21
2016-12-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | North Dakota | United States | 380053 | National Guard Vehicle Maintenance Shop Addition | 87 |  |  | 2014-10-06 | 2015-10-30 | 2015-12-11 | 100% | 2015-10-21
2016-12-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | North Dakota | United States | 380053 | National Guard Vehicle Maintenance Shop Addition | 88 |  |  | 2014-10-06 | 2015-10-30 | 2015-12-11 | 100% | 2015-10-21
2017-02-06 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop |  |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 65% | 2017-07-18
2017-02-06 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 135 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 65% | 2017-07-18
2017-02-06 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 136 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 65% | 2017-07-18
2017-02-06 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 137 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 65% | 2017-07-18
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Ohio | United States | 390290 | Modified Record Fire Range |  |  |  | 2016-06-06 | 2018-05-18 | 2018-05-18 | 2% | 2018-05-18
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Ohio | United States | 390292 | Sanitary Sewer |  |  |  | 2014-09-08 | 2016-07-02 | 2016-10-15 | 98% | 2016-10-15
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Oklahoma | United States | 400066 | Operations Readiness Training Complex |  |  |  | 2013-10-25 | 2014-10-01 | 2017-09-30 | 72% | 2017-02-11
2017-02-06 | 2012 | Army National Guard | Major Military Construction | Oregon | United States | 410026 | Readiness Center |  |  |  | 2012-12-01 | 2013-12-28 | 2014-03-20 | 100% | 2014-02-21
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Oregon | United States | 410301 | National Guard/Reserve Center Building Add/Alt (JFHQ) |  |  |  | 2016-11-29 | 2018-01-10 | 2018-01-10 | 1% | 2018-01-10
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420051 | Aircraft Maintenance Instructional Building |  |  |  | 2014-10-20 | 2016-04-22 | 2017-07-06 | 91% | 2017-07-06
2017-02-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | 420533 | Sanitary Sewer |  |  |  | 2016-01-13 | 2016-06-17 | 2017-04-28 | 63% | 2017-04-28
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Puerto Rico | Puerto Rico | 430070 | Maneuver Area Training & Equipment Site Addition |  |  |  | 2014-09-15 | 2016-05-30 | 2016-11-01 | 98% | 2015-05-30
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Puerto Rico | Puerto Rico | 430081 | Readiness Center (JFHQ) |  |  |  | 2014-03-03 | 2015-09-18 | 2016-04-20 | 100% | 2017-04-30
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Puerto Rico | Puerto Rico | 430803 | Readiness Center |  |  |  | 2015-10-19 | 2017-12-01 | 2018-04-08 | 36% | 2018-04-08
2017-02-06 | 2011 | Army National Guard | Major Military Construction | Rhode Island | United States | 440009 | United States Property and Fiscal Office |  |  |  | 2012-10-08 | 2014-04-17 | 2015-03-31 | 99% | 2015-01-31
2017-02-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | Rhode Island | United States | 440053 | Access Control Point |  |  |  | 2015-10-01 | 2016-04-01 | 2016-12-15 | 98% | 2016-10-31
2017-02-06 | 2014 | Army National Guard | Major Military Construction | South Carolina | United States | 450131 | National Guard Vehicle Maintenance Shop |  |  |  | 2014-03-26 | 2017-04-06 | 2017-07-06 | 95% | 2017-04-06
2017-02-06 | 2014 | Army National Guard | Major Military Construction | South Carolina | United States | 450283 | National Guard Readiness Center |  |  |  | 2014-03-26 | 2017-04-06 | 2017-07-06 | 55% | 2017-05-06
2017-02-06 | 2010 | Army National Guard | Major Military Construction | South Carolina | United States | 450353 | Army Aviation Support Facility |  | 12100000 | 220241, 220243 and 530035 | 2010-11-23 | 2012-08-18 | 2016-06-30 | 100% | 2013-06-21
2017-02-06 | 2012 | Army National Guard | Major Military Construction | South Carolina | United States | 450403 | Readiness Center, Add/Alt |  |  |  | 2012-10-01 | 2014-01-08 | 2014-04-30 | 100% | 2014-06-27
2017-02-06 | 2014 | Army National Guard | Major Military Construction | Texas | United States | 480243 | Armed Forces Reserve Center |  |  |  | 2016-04-13 | 2017-06-09 | 2018-04-17 | 8% | 2017-07-08
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Vermont | United States | 500079 | National Guard Vehicle Maintenance Shop Addition |  |  |  | 2016-04-11 | 2017-03-31 | 2017-03-31 | 85% | 2017-03-31
2017-02-06 | 2016 | Army National Guard | Major Military Construction | Virginia | United States | 510065 | National Guard/Reserve Center Building (JFHQ) |  |  |  | 2016-08-15 | 2018-03-18 | 2018-03-26 | 6% | 2018-03-26
2017-02-06 | 2012 | Army National Guard | Major Military Construction | Virginia | United States | 510307 | Combined Arms Collective Training Facility |  |  |  | 2013-04-10 | 2014-10-09 | 2015-02-27 | 99% | 2015-04-10
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Washington | United States | 530015 | Readiness Center |  |  |  | 2013-09-23 | 2015-08-20 | 2016-03-10 | 99% | 2016-01-09
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Washington | United States | 530035 | National Guard Readiness Center |  |  |  | 2014-10-06 | 2016-06-30 | 2016-09-21 | 99% | 2016-11-30
2017-02-06 | 2013 | Army National Guard | Major Military Construction | West Virginia | United States | 540075 | Readiness Center |  |  |  | 2014-04-07 | 2015-09-11 | 2015-11-29 | 99% | 2015-09-11
2017-02-06 | 2013 | Army National Guard | Major Military Construction | Wisconsin | United States | 550142 | Field Maintenance Shop |  |  |  | 2013-10-28 | 2014-10-01 | 2015-06-15 | 99% | 2014-10-01
2017-02-06 | 2017 | Army National Guard | Major Military Construction | Wyoming | United States | 560084 | National Guard Readiness Center |  |  |  | 2017-04-17 | 2018-04-30 | 2018-04-30 | 1% | 2018-04-30
2017-01-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 65277 | Consolidated Dining Facility |  |  |  | 2014-04-23 | 2015-09-30 | 2017-02-13 | 91%
2017-01-31 | 2012 | Army Reserve | Major Military Construction | North Carolina | United States | 67466 | Army Reserve Center/Land |  |  |  | 2012-10-10 | 2014-03-19 | 2017-02-28 | 92%
2017-01-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 67652 | Army Reserve Center |  |  |  | 2015-04-24 | 2017-02-12 | 2017-04-03 | 90%
2017-01-31 | 2013 | Army Reserve | Major Military Construction | Illinois | United States | 67659 | Army Reserve Center |  |  |  | 2014-01-13 | 2015-11-04 | 2016-11-28 | 97% | 2017-01-05
2017-01-31 | 2015 | Army Reserve | Major Military Construction | New York | United States | 67661 | Army Reserve Center/AMSA |  |  |  | 2016-04-07 | 2018-03-08 | 2018-03-08 | 26%
2017-01-31 | 2014 | Army Reserve | Major Military Construction | Maryland | United States | 67663 | Army Reserve Center/Land |  |  |  | 2015-10-07 | 2017-09-06 | 2018-09-18 | 13%
2017-01-31 | 2012 | Army Reserve | Major Military Construction | Indiana | United States | 67673 | Army Reserve Center |  |  |  | 2012-05-30 | 2015-01-29 | 2015-07-27 | 99%
2017-01-31 | 2012 | Army Reserve | Major Military Construction | Kansas | United States | 67681 | Army Reserve Center/Land |  |  |  | 2016-10-12 | 2018-01-05 | 2018-01-05 | 2%
2017-01-31 | 2013 | Army Reserve | Major Military Construction | Maryland | United States | 67705 | Army Reserve Center |  |  |  | 2015-10-08 | 2017-09-07 | 2017-09-07 | 9%
2017-01-31 | 2012 | Army Reserve | Major Military Construction | Massachusetts | United States | 67709 | Army Reserve Center/Land |  |  |  | 2016-09-19 | 2018-03-23 | 2018-03-23 | 6%
2017-01-31 | 2013 | Army Reserve | Major Military Construction | Washington | United States | 67715 | Army Reserve Center |  |  |  | 2013-07-11 | 2016-01-15 | 2016-12-30 | 99% | 2016-12-30
2017-01-31 | 2013 | Army Reserve | Major Military Construction | Maryland | United States | 68077 | Add/Alt Army Reserve Center |  | 5455000 | 69562 | 2014-07-30 | 2016-05-30 | 2017-03-23 | 90%
2017-01-31 | 2011 | Army Reserve | Major Military Construction | Texas | United States | 69421 | Army Reserve Center/Land |  |  |  | 2012-08-21 | 2014-03-21 | 2017-08-30 | 80% | 2016-04-01
2017-01-31 | 2011 | Army Reserve | Major Military Construction | Virginia | United States | 69562 | Army Reserve Center |  |  |  | 2015-01-23 | 2017-05-10 | 2017-09-11 | 14%
2017-01-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 71482 | ORTC |  |  |  | 2014-03-19 | 2016-05-17 | 2017-02-28 | 91%
2017-01-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71768 | Automated Multipurpose Machine Gun (MPMG) |  |  |  | 2015-11-19 | 2017-05-12 | 2017-04-28 | 92%
2017-01-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71769 | Modified Record Fire Range |  |  |  | 2014-10-17 | 2016-04-09 | 2016-10-18 | 97% | 2016-10-18
2017-01-31 | 2014 | Army Reserve | Major Military Construction | North Carolina | United States | 71900 | Army Reserve Center |  | 1700000 | 71720 | 2014-12-02 | 2016-11-01 | 2017-03-17 | 96%
2017-01-31 | 2015 | Army Reserve | Major Military Construction | California | United States | 71901 | Army Reserve Center/AMSA |  |  |  | 2016-03-02 | 2018-02-20 | 2018-03-22 | 24%
2017-01-31 | 2014 | Army Reserve | Major Military Construction | California | United States | 71903 | Army Reserve Center |  |  |  | 2016-11-28 | 2018-07-01 | 2018-07-01 | 0%
2017-01-31 | 2013 | Army Reserve | Major Military Construction | Wisconsin | United States | 72088 | ECS TEMF |  | 5455000 | 69562 | 2013-07-08 | 2016-12-12 | 2016-12-12 | 96% | 2016-12-12
2017-01-31 | 2014 | Army Reserve | Major Military Construction | California | United States | 72284 | TASS Training Center (TTC) |  |  |  | 2014-10-20 | 2016-05-22 | 2017-06-14 | 42%
2017-01-31 | 2015 | Army Reserve | Major Military Construction | Virginia | United States | 72291 | TASS Training Center |  |  |  | 2015-10-19 | 2017-08-28 | 2017-08-28 | 43%
2017-01-31 | 2015 | Army Reserve | Major Military Construction | New Jersey | United States | 77151 | Army Reserve Center |  |  |  | 2016-10-13 | 2018-09-13 | 2018-09-13 | 0%
2017-01-31 | 2015 | Army Reserve | Major Military Construction | Illinois | United States | 77228 | Army Reserve Center |  |  |  | 2016-02-27 | 2018-02-16 | 2018-02-16 | 0%
2017-01-31 | 2015 | Army Reserve | Major Military Construction | Colorado | United States | 81959 | Training Building Addition |  |  |  | 2015-08-07 | 2016-12-09 | 2017-03-31 | 38%
2017-01-31 | 2015 | Army Reserve | Major Military Construction | California | United States | 85812 | Army Reserve Center |  |  |  | 2015-11-02 | 2017-10-02 | 2017-11-16 | 20%
2017-04-14 | 2016 | DLA Defense Automation and Production Service | Major Military Construction | Virginia | United States | DSFF1501 | DLA Visitor Control Center, Ft. Belvoir |  |  |  | 2017-03-01 | 2018-01-28 | 2018-01-28 | 2%
2017-04-14 | 2016 | DLA Defense Automation and Production Service | Major Military Construction | Virginia | United States | DESC1607 | Replace Fuel Pier and Distribution Facility, Langley AFB, VA |  |  |  | 2016-10-12 | 2019-10-12 | 2019-12-12 | 1%
2017-04-14 | 2012 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1203 | Upgrade Access Control Points - New Cumberland |  |  |  | 2013-11-01 | 2015-05-05 | 2017-05-31 | 93% | 2016-11-07
2017-04-14 | 2013 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1301 | Replace Communications Bldg - New Cumberland |  |  |  | 2014-10-31 | 2016-04-28 | 2017-03-24 | 88% | 2016-11-07
2017-04-14 | 2013 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland |  |  |  | 2014-07-11 | 2016-01-04 | 2016-12-27 | 97% | 2016-10-27
2017-04-14 | 2014 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1309 | Phase I DDC, Upgrade Public Safety Facility |  |  |  | 2016-11-18 | 2018-02-20 | 2018-02-20 | 2%
2017-04-14 | 2014 | DLA Defense Distribution Center | Major Military Construction | California | United States | DDCX1404 | (Tracy) General Purpose warehouse San Joaquin |  |  |  | 2014-10-02 | 2016-02-28 | 2017-06-09 | 55% | 2017-02-10
2017-04-14 | 2015 | DLA Defense Distribution Center | Major Military Construction | South Carolina | United States | DESC1606 | Replace Fuel Distribution Facilities - MCAS Beaufort |  |  |  | 2015-12-16 | 2017-11-16 | 2017-11-05 | 45% | 2017-11-06
2017-04-14 | 2014 | DLA Defense Distribution Center | Unspecified Minor Military Construction | Hawaii | United States | DSFH1401 | Upgrade Administrative Space - JB PH Hickam | DSFH14U2 |  |  | 2015-06-02 | 2016-10-14 | 2017-01-17 | 87% | 2016-10-14
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC 1306 | Replace Fuel Pier - Pt Loma |  |  |  | 2014-01-15 | 2017-10-14 | 2017-10-14 | 95% | 2017-10-14
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | South Dakota | United States | DESC 1463 | Construct Hydrant Fuel System - Ellsworth AFB |  |  |  | 2016-01-19 | 2016-10-31 | 2017-04-16 | 97%
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC 1509 | Replace Fuel Pipeline - MCAS Miramar |  |  |  | 2016-02-16 | 2016-12-30 | 2017-01-31 | 96%
2017-04-14 | 2012 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma |  | 7345000 | FY13 Grissom | 2012-03-29 | 2015-03-11 | 2017-10-17 | 95% | 2016-05-05
2017-04-14 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  |  | DESC0907 | Hydrant Fuel System - Osan AB |  | 2151000 | FY12 New Cumberland General Purpose Warehous | 2013-08-12 | 2014-08-14 | 2016-04-30 | 100% | 2016-04-30
2017-04-14 | 2012 | DLA Defense Energy Support Center | Major Military Construction | Massachusetts | United States | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB |  | 1761000 | FY14 Iwakuni | 2013-06-18 | 2015-12-10 | 2016-08-15 | 100% | 2016-08-14
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | North Dakota | United States | DESC1107 | Replace Fuel Pipeline - Minot AFB |  |  |  | 2014-08-11 | 2015-08-11 | 2015-10-29 | 100% | 2015-07-21
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City |  |  |  | 2014-06-30 | 2015-11-15 | 2016-04-08 | 100% | 2016-04-11
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | Cuba | DESC1203 | Replace Fuel Pier - GTMO |  |  |  | 2013-10-28 | 2015-09-28 | 2017-08-29 | 97% | 2016-07-15
2017-04-14 | 2012 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1205 | Replace Fuel Facilities - San Clemente Is. |  |  |  | 2013-02-28 | 2015-03-11 | 2016-10-11 | 97%
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Indiana | United States | DESC1301 | Replace Hydrant Fuel system - Grissom ARB |  |  |  | 2015-09-17 | 2017-04-09 | 2017-11-22 | 33% | 2017-11-22
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Guam | Guam | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB |  |  |  | 2014-06-30 | 2016-02-06 | 2017-12-29 | 89%
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1304 | Replace Fuel Storage - Edwards AFB |  | 3470000 | FY13 Grissom | 2013-12-04 | 2016-12-07 | 2016-12-07 | 100% | 2017-03-07
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Delaware | United States | DESC1305 | Replace Truck Off-Load Facility - Dover AFB |  |  |  | 2013-10-18 | 2015-04-11 | 2015-11-02 | 100% | 2015-11-02
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1353 | Replace Hydrant Fuel System - Robins AFB |  |  |  | 2016-06-16 | 2018-06-18 | 2018-09-21 | 27%
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC13S2 | Replace Fuel Pipeline - Tyndall AFB |  |  |  | 2015-01-27 | 2016-05-06 | 2016-12-30 | 100% | 2016-09-14
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | Cuba | DESC13S3 | Replace Truck Loading Facility - GTMO |  |  |  | 2013-10-28 | 2015-09-28 | 2016-12-30 | 99% | 2016-06-15
2017-04-14 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Arizona | United States | DESC13S4 | Replace Truck Unload Facility - Yuma |  |  |  | 2013-09-30 | 2014-08-03 | 2016-04-24 | 100% | 2016-04-25
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1401 | Construct Type III Hydrant Fueling system - Iwakuni MCAS |  |  |  | 2015-04-26 | 2017-08-23 | 2017-10-20 | 58% | 2017-10-20
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction |  | Cuba | DESC1404 | Replace Fuel Storage Tanks, Guantanamo Bay, Cuba |  |  |  | 2016-03-01 | 2017-11-13 | 2017-11-13 | 9%
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island |  |  |  | 2014-11-30 | 2016-04-22 | 2016-01-14 | 100% | 2016-01-14
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1407 | Replace Hydrant Fuel System, Holloman AFB |  |  |  | 2015-08-17 | 2017-01-10 | 2017-04-17 | 97% | 2017-04-17
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | North Carolina | United States | DESC1459 | Replace Hydrant Fuel System, Seymour Johnson AFB |  |  |  | 2015-09-10 | 2017-05-02 | 2017-08-25 | 56% | 2017-08-26
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Jersey | United States | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst |  |  |  | 2014-11-18 | 2016-05-11 | 2017-06-30 | 66% | 2017-01-12
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB |  |  |  | 2015-01-19 | 2017-05-23 | 2017-06-08 | 74% | 2017-09-08
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | 43 |  |  | 2015-08-10 | 2016-10-23 | 2017-04-29 | 74% | 2016-12-08
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1503 | Replace Diesel Fuel Pumps - Yokosuka |  |  |  | 2015-05-15 | 2016-11-05 | 2017-01-31 | 100% | 2017-01-07
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1504 | Upgrade Fuel Island - Hunter AAF |  |  |  | 2014-10-16 | 2016-04-08 | 2016-10-21 | 100% | 2016-10-16
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1508 | Replace Fuel Storage And Distribution Facilities NAS Lemoore CA |  |  |  | 2017-01-02 | 2020-03-30 | 2020-03-30 | 0%
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Michigan | United States | DESC1510 | Replace Fuel Distribution Facilities, Selfridge ANG |  |  |  | 2015-12-09 | 2018-04-07 | 2018-10-05 | 49% | 2018-10-05
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1515 | Replace and Alter Fuel Distribution Facilites, Craney Island DFSP |  |  |  | 2015-09-30 | 2017-06-26 | 2017-07-07 | 65% | 2017-06-26
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Hawaii | United States | DESC1551 | Upgrade fire Suppression and Ventilation System - Rd Hill; JB Pearl Harbor - Hickam |  |  |  | 2015-09-30 | 2017-09-25 | 2017-09-25 | 69% | 2017-09-25
2017-04-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Tennessee | United States | DESC1557 | Replace Ground Vehicle Fueling Facility - Arnold AFB |  |  |  | 2015-06-18 | 2016-10-11 | 2016-11-29 | 95% | 2017-01-09
2017-04-14 | 2015 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1606 | Replace Fuel Distribution Facilities - MCAS Beaufort |  |  |  | 2015-12-16 | 2017-11-16 | 2017-11-05 | 45% | 2017-11-06
2017-04-14 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1607 | Replace Fuel Pier and Distribution Facility, Langley AFB, VA |  |  |  | 2016-10-12 | 2019-10-12 | 2019-12-12 | 1%
2017-04-14 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Nevada | United States | DESC1613 | Replace Hydrant Fuels System Nellis AFB Nevada |  |  |  | 2017-03-01 | 2019-07-05 | 2019-10-04 | 1%
2017-04-14 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Djibouti | DESC1701 | Construct Fuel Storage Facilities, Camp Lemonnie, Djibouti, Horn-of-Africa |  |  |  | 2017-03-13 | 2019-01-07 | 2019-01-07 | 1%
2017-04-14 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1710 | Replace Truck Fill Stands, Moody AFB, Georgia |  |  |  | 2016-11-15 | 2018-07-31 | 2018-07-31 | 2%
2017-04-14 | 2015 | DLA Defense National Stockpile Center | Major Military Construction | Maryland | United States | DESC1507 | Construct Hydrant Fuel System Andrews AFB MD |  |  |  | 2016-10-31 | 2018-02-07 | 2018-02-07 | 7%
2017-04-14 | 2016 | DLA Defense Supply Center Philadelphia | Major Military Construction | Pennsylvania | United States | DSCP1501 | DLA Toop Suport Headquarters, NSA Philadelphia, PA |  |  |  | 2016-10-01 | 2019-03-30 | 2019-03-30 | 1%
2017-04-14 | 2014 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1401 | Operations Center Phase 1 |  |  |  | 2015-08-26 | 2018-08-25 | 2018-08-25 | 40% | 2018-08-25
2017-01-31 | 2008 | Defense Health Agency | Major Military Construction | Kansas | United States | 47298 | Hospital Replacement |  | 44000000 | PN 72754 | 2010-05-03 | 2013-07-23 | 2016-08-12 | 100% | 2016-03-15
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 51969 | Hospital Nutrition Care Department Add/Alt |  |  |  | 2012-10-02 | 2014-10-30 | 2016-10-27 | 100% | 2015-11-20
2017-01-31 | 2008 | Defense Health Agency | Major Military Construction |  | Germany | 52332 | Medical Clinic Replacement |  |  |  | 2008-08-29 | 2012-05-15 | 2012-07-16 | 100% | 2011-10-08
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Guam | Guam | 55918 | Central Utility Plant |  | 696000 | PN 78146 | 2009-10-01 | 2011-02-07 | 2011-06-22 | 100% | 2011-06-22
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 |  |  |  | 2007-10-12 | 2008-06-13 | 2008-06-08 | 100% | 2008-07-23
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-01 |  |  | 2008-08-19 | 2009-02-15 | 2009-02-13 | 100% | 2009-03-03
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-02 |  |  | 2009-10-15 | 2010-04-13 | 2010-04-13 | 100% | 2010-04-13
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-03 |  |  | 2008-12-05 | 2009-07-24 | 2009-07-24 | 100% | 2009-07-24
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-04 |  |  | 2008-07-15 | 2011-05-06 | 2013-10-31 | 100% | 2013-12-06
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-05 |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 97% | 2017-07-01
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 2 | 63418 |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 97% | 2017-07-01
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 3 | 63419 |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 97% | 2017-07-01
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 97% | 2017-07-01
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420-01 |  |  | 2008-07-15 | 2013-10-31 | 2016-12-06 | 100% | 2013-12-06
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324 | 186000 | PN 67949 | 2009-06-01 | 2014-05-31 | 2017-07-01 | 97% | 2017-07-01
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324-01 |  |  | 2008-07-15 | 2013-10-31 | 2013-12-06 | 100% | 2013-12-06
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101 |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 97% | 2017-07-01
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-03-31 | 87% | 2017-06-29
2017-01-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210 |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 97% | 2017-07-01
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | New York | United States | 59220 | Hospital Add/Alt (Supplemental) |  | 5537000 | PN 76558 | 2011-10-26 | 2015-08-03 | 2015-09-11 | 99% | 2015-07-15
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Maryland | United States | 61401 | Boundary Gate at Nallin Pond |  |  |  | 2011-01-12 | 2013-01-10 | 2015-01-08 | 100% | 2014-12-31
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Oklahoma | United States | 62189 | Medical / Dental Clinic Replacement |  | 7033000 | PN 00001 VCOE PN 76558 | 2009-06-01 | 2011-10-26 | 2012-02-09 | 100% | 2012-06-04
2017-01-31 | 2008 | Defense Health Agency | Major Military Construction | New York | United States | 63864 | Health Clinic Add/Alt |  | 1000000 | PN 67647 | 2008-11-07 | 2011-02-18 | 2013-12-12 | 100% | 2012-12-01
2017-01-31 | 2009 | Defense Health Agency | Base Realignment and Closures | Maryland | United States | 64156 | USAMRICD Replacement, Inc 1 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Illinois | United States | 65030 | Naval Hospital Great Lakes Health Clinic Demolition |  | 9210000 | PN 67951 PN 71325 PN 77154 | 2012-09-12 | 2013-09-13 | 2014-08-08 | 100% | 2014-04-21
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Guam | Guam | 65270 | Hospital Replacement, Inc 1 |  | 659000 | PN 61401 | 2010-11-01 | 2014-10-15 | 2016-09-06 | 100% | 2014-03-18
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 | 65731-01 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-01 |  |  | 2010-10-01 | 2011-09-30 | 2011-09-30 | 100% | 2011-10-01
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-02 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 3 | 67181 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 4 | 67182 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66588 | Health Clinic Add/Alt |  |  |  | 2013-04-08 | 2016-05-30 | 2017-05-03 | 94% | 2017-01-07
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66693 | Health/Dental Clinic Replacement |  |  |  | 2014-02-03 | 2016-04-12 | 2016-06-30 | 100% | 2016-06-30
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67949 | NIBC Security Fencing and Equipment |  |  |  | 2012-04-02 | 2013-04-02 | 2013-04-01 | 100% | 2013-04-01
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67949 | NIBC Security Fencing and Equipment | 67949-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-06-29 | 65% | 2017-06-29
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67951 | Water Treatment Plant Repair |  |  |  | 2013-01-14 | 2014-07-08 | 2016-06-01 | 100% | 2016-03-18
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67953 | Supplemental Water Storage |  |  |  | 2011-07-20 | 2012-11-01 | 2016-12-01 | 100% | 2016-11-04
2017-01-31 | 2008 | Defense Health Agency | Major Military Construction | Georgia | United States | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) |  |  |  | 2009-10-22 | 2013-02-03 | 2014-05-19 | 100% | 2014-05-19
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | North Carolina | United States | 70351 | Hospital Alteration |  | 23532000 | PN 67182 PN 71503 | 2012-09-13 | 2014-06-23 | 2016-07-13 | 99% | 2016-05-19
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) |  | 92680000 | PN 76558 | 2012-05-30 | 2015-03-16 | 2017-05-31 | 88% | 2017-07-16
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Kentucky | United States | 70438 | Hospital Addition/Alteration |  |  |  | 2012-08-22 | 2015-02-21 | 2015-10-27 | 100% | 2015-10-27
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Georgia | United States | 70482 | Health Clinic Addition/Alteration |  |  |  | 2011-06-21 | 2013-06-20 | 2014-05-19 | 100% | 2013-11-29
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Florida | United States | 70597 | Medical Clinic |  |  |  | 2012-10-17 | 2014-10-07 | 2014-10-07 | 100% | 2014-10-07
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | South Carolina | United States | 71317 | Medical Clinic Replacement |  | 4000000 | PN 80306 | 2013-12-06 | 2016-12-30 | 2018-05-03 | 93% | 2016-12-02
2016-10-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 71318 | Dental Clinic Replacement |  | 3144000 | FY14 - PN77922 | 2010-04-06 | 2012-01-06 | 2012-09-01 | 100% | 2012-04-30
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 71325 | Medical Clinic Replacement |  |  |  | 2013-10-24 | 2016-10-23 | 2017-03-27 | 67% | 2017-07-21
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 71408 | Dental Clinic Replacement |  |  |  | 2013-03-01 | 2016-12-06 | 2018-06-05 | 1% | 2017-10-25
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic |  | 8300000 | PN 72754 | 2012-09-01 | 2014-09-09 | 2016-01-31 | 50% | 2016-04-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic | 71503-01 |  |  | 2016-08-25 | 2017-12-25 | 2017-12-29 | 79% | 2017-09-30
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 71507 | Branch Health Clinic Replacement |  | 8100000 | PN 72722 PN 80306 | 2014-04-30 | 2015-10-15 | 2017-03-31 | 99% | 2017-01-09
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement |  | 205000 | PN 14010 | 2010-12-14 | 2012-08-10 | 2012-09-28 | 100% | 2012-09-28
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement | 71550-01 |  |  | 2013-07-01 | 2013-08-30 | 2013-08-30 | 100% | 2013-08-30
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement | 71550-02 |  |  | 2015-03-03 | 2015-06-30 | 2016-06-30 | 100% | 2016-06-30
2017-01-31 | 2016 | Defense Health Agency | Major Military Construction | Ohio | United States | 71642 | Satellite Pharmacy Replacement |  |  |  | 2016-10-14 | 2019-01-12 | 2019-01-12 | 1% | 2019-04-04
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Missouri | United States | 71679 | Dental Clinic |  | 234000 | PN 72718 | 2013-12-02 | 2015-02-19 | 2015-02-19 | 100% | 2015-10-01
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Georgia | United States | 72292 | Hospital Addition/Alteration Phase 2 |  | 11000000 | PN-72754 | 2012-10-15 | 2016-10-14 | 2017-03-15 | 97% | 2017-05-17
2017-01-31 | 2015 | Defense Health Agency | Major Military Construction | Colorado | United States | 72414 | Dental Clinic Replacement |  |  |  | 2015-11-03 | 2017-10-23 | 2017-11-22 | 31% | 2017-12-22
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction |  | Korea, South | 72419 | Hospital Addition/Alteration |  |  |  | 2013-09-26 | 2017-08-08 | 2018-08-07 | 76% | 2018-10-22
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72430 | Ambulatory Care Center, Phase 1 |  |  |  | 2010-10-04 | 2013-02-20 | 2013-11-19 | 100% | 2013-11-19
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72430 | Ambulatory Care Center, Phase 1 | 72430-01 |  |  | 2010-10-04 | 2012-02-26 | 2012-12-13 | 100% | 2012-12-13
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 |  |  |  | 2013-05-29 | 2016-11-26 | 2018-09-03 | 60% | 2018-09-03
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-01 |  |  | 2011-11-02 | 2013-08-13 | 2013-10-12 | 100% | 2013-10-12
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-02 |  |  | 2011-08-23 | 2012-07-05 | 2012-12-31 | 100% | 2012-12-31
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-03 |  |  | 2012-08-28 | 2013-06-19 | 2013-10-17 | 100% | 2013-10-17
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-04 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-05 |  |  | 2012-09-04 | 2014-01-04 | 2015-09-16 | 100% | 2015-09-16
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-06 |  |  | 2011-08-25 | 2011-11-01 | 2011-11-01 | 100% | 2011-11-01
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 3 | 72786 |  |  | 2013-05-29 | 2016-11-26 | 2018-09-03 | 60% | 2018-09-03
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 |  |  | 2013-05-29 | 2016-11-26 | 2018-09-03 | 60% | 2018-09-03
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-01 |  |  | 2013-10-21 | 2014-10-24 | 2014-10-24 | 99% | 2014-11-24
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-02 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 77251 |  |  | 2013-05-29 | 2016-11-26 | 2018-09-03 | 60% | 2018-09-03
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 |  |  | 2013-05-29 | 2016-11-26 | 2018-09-03 | 60% | 2018-09-03
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407 |  |  | 2013-05-29 | 2016-11-26 | 2018-09-03 | 60% | 2018-09-03
2017-01-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 7 | 81408 |  |  | 2013-05-29 | 2016-11-26 | 2018-09-03 | 60% | 2018-09-03
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) |  | 22793000 | PN 76558 | 2011-10-25 | 2014-09-09 | 2015-04-17 | 100% | 2015-09-23
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-01 |  |  | 2011-03-20 | 2011-04-01 | 2011-04-01 | 100% | 2011-04-01
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-02 |  |  | 2011-07-01 | 2014-09-27 | 2015-03-18 | 100% | 2015-03-18
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-03 |  |  | 2015-11-30 | 2016-06-01 | 2016-06-08 | 100% | 2016-06-08
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | United Kingdom | 72727 | Medical/Dental Clinic Replacement |  |  |  | 2014-05-06 | 2015-10-30 | 2016-01-06 | 100% | 2015-08-27
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Texas | United States | 72752 | Ambulatory Care Center Phase 2 |  | 75054000 | PN72727 PN62886 PN77000 | 2011-12-02 | 2013-10-01 | 2016-09-02 | 100% | 2016-09-02
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 2 | 80793-01 |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | California | United States | 72808 | Medical Clinic Replacement |  | 1500000 | PN 80309 | 2014-02-28 | 2015-03-16 | 2017-03-31 | 98% | 2016-06-23
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 73360 | Consolidated Logistics Facility |  |  |  | 2011-07-21 | 2014-01-06 | 2014-10-07 | 99% | 2014-10-07
2016-10-31 | 2009 | Defense Health Agency | Major Military Construction | North Carolina | United States | 73599 | Hospital Renovation & MRI Addition (Cong Add) |  | 5623000 | PN - 76558 | 2010-12-03 | 2015-01-02 | 2015-10-16 | 100% | 2015-09-18
2016-11-30 | 2013 | Defense Health Agency | Major Military Construction | New York | United States | 73776 | Soldier Specality Care Clinic |  |  |  | 2014-01-06 | 2016-01-06 | 2016-01-06 | 100% | 2016-01-06
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) |  | 3850000 | PN 100040 | 2010-11-08 | 2014-05-31 | 2016-02-15 | 99% | 2016-04-01
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-01 |  |  | 2010-06-15 | 2012-02-25 | 2012-06-02 | 100% | 2012-06-02
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-02 |  |  | 2010-04-05 | 2010-05-30 | 2010-06-30 | 100% | 2010-06-30
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-03 |  |  | 2010-06-18 | 2010-10-18 | 2010-10-05 | 100% | 2010-10-05
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-04 |  |  | 2010-07-20 | 2012-01-11 | 2012-09-20 | 100% | 2012-09-20
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-05 |  |  | 2011-01-06 | 2012-06-29 | 2013-12-15 | 99% | 2013-12-15
2017-01-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | Florida | United States | 75132 | Joint Navy-VA Project |  |  |  | 2014-06-01 | 2014-10-15 | 2016-12-07 | 100% | 2016-12-12
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 |  |  |  | 2014-01-13 | 2021-07-20 | 2022-12-30 | 5% | 2022-12-30
2016-12-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  | 2017-06-30 | 2020-12-30 | 2020-12-30 | 1% | 2020-12-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661-01 |  |  | 2017-07-30 | 2020-12-30 | 2020-12-30 | 1% | 2020-12-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 72662 |  |  | 2017-12-15 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-01 |  |  | 2014-01-20 | 2014-04-04 | 2014-04-04 | 100% | 2014-04-04
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-02 |  |  | 2014-06-16 | 2014-10-29 | 2015-01-21 | 100% | 2015-01-21
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-03 |  |  | 2015-04-20 | 2016-04-30 | 2017-04-30 | 99% | 2016-12-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-04 |  |  | 2016-06-15 | 2016-12-15 | 2017-12-15 | 62% | 2018-01-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-05 |  |  | 2014-08-22 | 2015-03-30 | 2015-05-01 | 100% | 2015-05-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-06 |  |  | 2014-10-08 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-07 |  |  | 2014-08-11 | 2014-10-16 | 2014-10-16 | 100% | 2014-10-16
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-08 |  |  | 2016-08-15 | 2016-10-30 | 2016-12-30 | 100% | 2016-12-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-09 |  |  | 2016-11-30 | 2016-12-15 | 2017-04-30 | 89% | 2017-06-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-10 |  |  | 2014-12-10 | 2022-12-30 | 2022-12-30 | 2% | 2022-12-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-11 |  |  | 2018-06-30 | 2022-12-30 | 2022-12-30 | 1% | 2018-06-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-12 |  |  | 2016-02-28 | 2016-04-30 | 2017-03-30 | 84% | 2017-02-28
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-13 |  |  | 2014-10-23 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-14 |  |  | 2015-03-30 | 2022-12-30 | 2022-12-30 | 1% | 2022-12-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-10-30 | 5% | 2018-11-30
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 4 | 76872 |  |  | 2018-03-30 | 2021-12-08 | 2022-12-30 | 1% | 2022-12-30
2017-01-31 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement |  |  |  | 2015-09-08 | 2019-02-19 | 2019-03-09 | 9% | 2019-10-18
2017-01-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 77115 | Transient Wounded Warrior Lodging |  | 9730000 | NATO HQ PN 77116 PN 72414 | 2012-06-18 | 2014-02-02 | 2014-07-18 | 100% | 2014-05-27
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 1 |  |  |  | 2013-03-01 | 2016-12-06 | 2018-06-05 | 80% | 2017-08-04
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 2 | 81291 |  |  | 2013-03-01 | 2016-12-06 | 2018-06-05 | 80% | 2017-08-04
2017-01-31 | 2014 | Defense Health Agency | Major Military Construction | New Mexico | United States | 77922 | Medical Clinic Replacement |  | 1900000 | PN 81340 | 2014-10-28 | 2018-01-23 | 2018-01-23 | 69% | 2018-04-23
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | New Mexico | United States | 77979 | Medical/Dental Clinic Replacement |  |  |  | 2014-08-12 | 2018-02-10 | 2018-06-08 | 66% | 2018-01-08
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Illinois | United States | 78143 | Navy Drug Lab Replacement |  | 644000 | PN 78146 | 2013-11-08 | 2015-01-15 | 2017-07-28 | 99% | 2015-04-20
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 78144 | Medical Clinic Addition |  | 1800000 | PN 71507 | 2013-10-08 | 2015-03-17 | 2015-12-21 | 100% | 2015-09-11
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Virginia | United States | 78146 | Veterinarian Facility |  |  |  | 2014-02-28 | 2014-12-06 | 2015-11-23 | 100% | 2015-09-21
2017-01-31 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 78150 | Medical Clinic Replacement |  |  |  | 2016-11-14 | 2018-12-21 | 2019-01-15 | 2% | 2018-12-21
2017-01-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 79554 | Child Development Center |  | 2000000 | PN 67182 | 2013-03-01 | 2014-02-22 | 2014-06-02 | 100% | 2014-04-07
2017-01-31 | 2009 | Defense Health Agency | Major Military Construction | Florida | United States | 79845 | Eglin Hospital Alteration (ARRA) |  |  |  | 2011-10-31 | 2014-11-06 | 2015-07-29 | 99% | 2015-03-12
2016-10-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | Nevada | United States | 80093 | Medical Ed. & Training Facility |  |  |  | 2012-08-14 | 2013-11-14 | 2014-08-24 | 100% | 2014-09-10
2016-12-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | Washington | United States | 80094 | Veterinary Clinic |  |  |  | 2013-01-04 | 2014-07-05 | 2014-12-12 | 100% | 2014-12-12
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities |  |  |  | 2013-10-15 | 2013-12-13 | 2014-03-25 | 100% | 2014-04-04
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities | 80306-01 |  |  | 2016-10-04 | 2017-12-10 | 2017-12-10 | 2% | 2017-12-10
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80307 | Implement Base Installation Appearance Plan |  |  |  | 2014-04-01 | 2015-04-08 | 2017-07-28 | 66% | 2017-07-28
2017-01-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80308 | Electrical Utility Upgrades |  | 4500000 | PN 65270 PN 65270 | 2014-10-23 | 2016-02-12 | 2016-10-31 | 100% | 2016-10-31
2017-01-31 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 |  |  |  | 2016-06-16 | 2017-12-08 | 2017-12-08 | 2% | 2018-01-22
2017-01-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | Virginia | United States | 80792 | Site Development, NiCOE |  |  |  | 2012-09-10 | 2013-05-31 | 2013-08-29 | 100% | 2013-06-30
2017-01-31 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 80904 | Mechanical & Electrical Improvements |  |  |  | 2015-05-31 | 2017-02-07 | 2017-11-09 | 56% | 2017-11-09
2017-01-31 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 80913 | Parking Garage |  |  |  | 2014-11-30 | 2016-04-16 | 2017-04-16 | 60% | 2017-04-16
2017-01-31 | 2014 | Defense Health Agency | Major Military Construction | Texas | United States | 81340 | SAMMC Hyperbaric Facility Addition |  |  |  | 2014-07-29 | 2016-07-28 | 2017-03-30 | 85% | 2017-05-05
2017-01-31 | 2015 | Defense Health Agency | Major Military Construction | Texas | United States | 81423 | Medical Clinic Replacement (Reid Clinic) |  |  |  | 2015-09-28 | 2018-09-27 | 2018-10-18 | 22% | 2018-06-10
2017-01-31 | 2014 | Defense Health Agency | Major Military Construction |  | Bahrain | 81436 | Medical/Dental Clinic Replacement |  |  |  | 2016-04-20 | 2019-04-20 | 2019-04-20 | 7% | 2019-07-19
2017-01-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | Washington | United States | 81627 | NiCOE Satellite, Infrastructure Support |  |  |  | 2016-03-28 | 2017-11-14 | 2017-09-14 | 82% | 2017-11-14
2017-01-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | North Carolina | United States | 81631 | NiCOE Satellite, Infrastructure Support |  |  |  | 2014-06-30 | 2016-02-01 | 2016-06-23 | 98% | 2016-03-31
2017-01-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | Texas | United States | 81706 | NiCOE Satellite, Infrastructure Support |  |  |  | 2014-09-15 | 2015-10-28 | 2015-12-11 | 99% | 2015-11-20
2015-10-30 | 2013 | Defense Information Systems Agency | Major Military Construction |  | Germany | 13DISA01 | DISA Europe Facility Upgrade |  |  |  | 2015-08-19 | 2016-12-31 | 2016-12-31
2015-10-30 | 2014 | Defense Information Systems Agency | Major Military Construction | Hawaii | United States | 14DISA01 | DISA Pacific Facility Upgrade
2015-10-30 | 2015 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 15DISA01 | Design/Renovate Bldg 52120 for JITC
2015-10-30 | 2015 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 15DISA01 | Design of Bldgs 52101, 52110, 52111 for JITC | 1
2015-10-30 | 2015 | Defense Information Systems Agency | Major Military Construction |  | Australia | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton)
2015-10-30 | 2013 | Defense Information Systems Agency | Major Military Construction | Illinois | United States | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  |  |  | 2014-03-01 | 2015-12-30 | 2016-03-11 | 85%
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA12000001 | DIAC Parking Garage Replacement |  |  |  | 2014-09-23 | 2015-10-09 | 2016-10-20 | 30%
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA12000003 | DIAC Chilled Water Project for Data Center |  | 2070000 | $2,070K diverted to DIA (UPS) Data Center, project DIA12000002, approved MILCON Reprogramming.
2015-08-31 | 2013 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA13000001 | Parking Garage Demolition
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction | Georgia | United States | AM 856 07 | New Elementary School |  |  |  | 2012-08-01 | 2013-12-14 | 2014-07-21 | 99% | 2014-08-01
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00023 | Replace McBride Elementary School |  |  |  | 2013-12-11 | 2015-12-11 | 2016-08-03 | 99% | 2016-08-02
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00023 | Replace McBride Elementary School | 28 |  |  | 2013-12-11 | 2015-12-11 | 2016-08-03 | 99% | 2016-08-02
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00024 | Faith Middle School Addition |  |  |  | 2014-10-28 | 2016-01-21 | 2016-05-24 | 99% | 2016-08-02
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00025 | Replace Delalio Elementary School |  |  |  | 2014-02-24 | 2016-06-01 | 2018-04-16 | 70%
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00026 | Replace Kingsolver/Pierce School |  |  |  | 2014-03-11 | 2015-11-11 | 2016-05-31 | 98%
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00026 | Replace Consolidate Kingsolver/Pierce Elem Schools | 43 |  |  | 2015-12-01 | 2016-11-30 | 2016-12-01 | 99% | 2016-11-30
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00027 | Replace Hanscom Middle School |  |  |  | 2014-02-11 | 2016-04-21 | 2016-04-27 | 99% | 2016-04-22
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00027 | Replace Hanscom Middle School | 88 |  |  | 2014-02-11 | 2016-04-21 | 2016-04-27 | 99% | 2016-04-22
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School |  | 800000 | PA00033 | 2014-03-27 | 2015-12-17 | 2016-08-26 | 100%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School | 44 |  |  | 2014-03-27 | 2015-12-17 | 2016-08-26 | 100%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00031 | Pope Holbrook Elementary School |  |  |  | 2015-02-11 | 2017-02-10 | 2017-04-17 | 74%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | Tennessee | United States | AM00034 | Replace Fort Campbell High School |  |  |  | 2015-01-27 | 2017-02-25 | 2017-06-28 | 85%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | South Carolina | United States | AM00037 | Replace Bolden-Galer Elementary School |  |  |  | 2015-08-18 | 2018-06-28 | 2018-07-08 | 45%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00038 | Diamond Elementary School Replacement |  |  |  | 2014-10-15 | 2016-09-14 | 2017-03-19 | 81%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00038 | Diamond Elementary School Replacement | 29 |  |  | 2016-06-15 | 2017-01-11 | 2017-01-11 | 0%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00040 | Replace Marshall Elementary School |  |  |  | 2014-08-06 | 2016-03-28 | 2016-06-10 | 99% | 2016-06-10
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | United States | AM00046 | Design and Construct new Primary School at Hanscom |  |  |  | 2014-02-11 | 2016-04-21 | 2016-04-27 | 99% | 2016-04-22
2017-02-07 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School |  | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2020-06-10 | 4%
2017-02-07 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 8 | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2020-06-10 | 4%
2017-02-07 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 9 | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2020-06-10 | 4%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00050 | White Elementary School Replacement |  |  |  | 2014-12-16 | 2016-10-31 | 2017-04-11 | 68%
2017-02-07 | 2015 | DoD Education Activity | Major Military Construction |  | United States | AM00103 | Consolidate/Replace W.T. Sampson Elementary School |  |  |  | 2016-07-01 | 2018-11-26 | 2018-11-26 | 11%
2017-02-07 | 2015 | DoD Education Activity | Major Military Construction |  | Spain | AM00115 | Rota Elementary and High School Additions |  |  |  | 2016-07-20 | 2019-03-27 | 2019-03-27 | 7%
2017-02-07 | 2016 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00123 | AM00123 Ft Knox High School Addition |  |  |  | 2016-08-16 | 2018-05-08 | 2018-05-08 | 6%
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction | Virginia | United States | AM2455206 | Replace/Consolidate Elementary Schools |  |  |  | 2012-09-29 | 2014-09-30 | 2016-01-21 | 100% | 2015-04-13
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction | Puerto Rico | Puerto Rico | AM8193 01 | Replace Elementary School (Antilles ES) |  |  |  | 2012-07-18 | 2014-04-19 | 2014-05-10 | 95% | 2016-08-10
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction |  | Belgium | D9124-1 | Replace Schools (SHAPE MS/HS) |  |  |  | 2012-01-18 | 2014-04-17 | 2015-05-31 | 100% | 2014-07-04
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction |  | Belgium | D9124-1 | Replace Schools (SHAPE MS/HS) | 17 |  |  | 2012-07-05 | 2015-07-23 | 2016-09-29 | 100% | 2012-12-05
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction |  | Belgium | D9124-1 | Replace Schools (SHAPE MS/HS) | 18 |  |  | 2012-08-01 | 2015-01-13 | 2015-09-19 | 100% | 2015-02-12
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School |  |  |  | 2016-08-19 | 2017-02-15 | 2017-02-15 | 85%
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School | 29 |  |  | 2017-01-08 | 2019-05-08 | 2019-05-08 | 0%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School |  |  |  | 2016-09-02 | 2019-01-02 | 2019-01-02 | 4%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School | 45 |  |  | 2016-09-02 | 2019-01-02 | 2019-01-02 | 4%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement |  |  |  | 2016-03-14 | 2016-06-22 | 2016-09-23 | 100% | 2016-10-21
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement | 60 |  |  | 2017-05-12 | 2017-05-09 | 2017-05-09 | 90%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement | 61 |  |  | 2017-05-12 | 2019-06-18 | 2019-06-18 | 0%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement | 62 |  |  | 2017-05-12 | 2019-06-18 | 2019-06-18 | 0%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School |  |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 66%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 33 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 66%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 34 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 66%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 35 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 66%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 36 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 66%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00049 | Replace Hainerberg Elementary School |  |  |  | 2022-06-25 | 2022-06-25 | 2022-06-25 | 0%
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00053 | Replace Elementary/Middle School (Ansbach EMS) |  |  |  | 2013-10-28 | 2015-03-10 | 2015-08-20 | 100% | 2015-09-23
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00053 | Replace Elementary/Middle School (Ansbach EMS) | 25 |  |  | 2013-10-28 | 2015-03-10 | 2015-08-20 | 100% | 2015-09-23
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00062 | Netzaberg Middle School Addition |  |  |  | 2014-06-05 | 2015-09-20 | 2015-11-24 | 100% | 2015-12-21
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00062 | Netzaberg Middle School Addition | 42 |  |  | 2014-06-05 | 2015-09-20 | 2015-11-24 | 100% | 2015-12-21
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00072 | Replace Wiesbaden Middle School |  |  |  | 2016-04-21 | 2018-04-11 | 2018-04-11 | 11%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00072 | Replace Wiesbaden Middle School | 7 |  |  | 2016-04-21 | 2018-04-11 | 2018-04-11 | 11%
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8268 02 | Replace School (Boblingen HS) |  | 3999000 | PA00033 | 2013-07-29 | 2015-04-30 | 2015-06-23 | 100% | 2015-08-25
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8268 02 | Replace School (Boblingen HS) | 13 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 100% | 2015-08-25
2017-02-07 | 2011 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8268 02 | Replace School (Boblingen HS) | 14 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 100% | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Belgium | EUR 8318 09 | Replace School (SHAPE ES) |  |  |  | 2012-01-18 | 2014-04-17 | 2015-05-31 | 100% | 2014-07-04
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Belgium | EUR 8318 09 | Replace School (SHAPE ES) | 11 |  |  | 2012-07-05 | 2015-07-23 | 2016-09-29 | 100% | 2012-12-05
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8320 03 | Replace School (Boblingen ES) |  | 1475000 | PA00033 | 2013-07-29 | 2015-04-30 | 2015-06-23 | 100% | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8320 03 | Replace School (Boblingen ES) | 8 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 100% | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8320 03 | Replace School (Boblingen ES) | 9 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 100% | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 45%
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 3 |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 45%
2017-02-07 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 4 |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 45%
2017-02-07 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00017 | Killin Elementary School Replacement/Renovation |  |  |  | 2017-01-11 | 2020-11-17 | 2020-11-17 | 0%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Korea, South | PA00018 | Daegu Middle/High School Replacement |  |  |  | 2014-09-29 | 2016-10-03 | 2016-12-08 | 96%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Korea, South | PA00020 | Replace Elementary School (Osan ES) |  | 6444000 | PA00033 | 2013-09-30 | 2015-12-09 | 2016-06-14 | 100% | 2016-07-12
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00021 | Replace Sasebo Elementary School |  |  |  | 2016-04-04 | 2018-11-03 | 2018-11-03 | 7%
2017-02-07 | 2012 | DoD Education Activity | Major Military Construction |  | Japan | PA00027 | Replace Yokota High School |  |  |  | 2015-02-19 | 2018-12-21 | 2019-01-18 | 65%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00030 | Replace Zukeran Elementary School |  |  |  | 2014-10-23 | 2017-04-01 | 2017-07-06 | 37%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  |  |  | 2014-07-07 | 2016-10-24 | 2017-04-30 | 76%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 38 |  |  | 2014-07-07 | 2016-10-24 | 2017-04-30 | 76%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 39 |  |  | 2014-07-07 | 2016-10-24 | 2017-04-30 | 76%
2017-02-07 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 40 |  |  | 2014-07-07 | 2016-10-24 | 2017-04-30 | 76%
2017-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Japan | PA00035 | Kadena Middle School Addition/Renovation |  |  |  | 2015-03-06 | 2016-10-02 | 2016-10-31 | 80%
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND |  | 1743000 | M00318863 | 2013-09-19 | 2016-01-18 | 2016-07-15 | 99% | 2016-07-15
| 2015 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146193 | WATER TREATMENT PLANT REPLACEMENT |  |  |  | 2017-01-05 | 2020-02-28 | 2020-02-28 | 1% | 2020-02-28
| 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146194 | UNMANNED AIRCRAFT SYSTEM FACILITIES |  |  |  | 2016-09-14 | 2018-10-04 | 2018-10-04 | 1% | 2018-10-04
| 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146229 | KC-130J ENLISTED AIR CREW TRAINER FACILITY |  |  |  | 2016-09-20 | 2017-10-02 | 2017-10-02 | 6% | 2017-10-02
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M00243313 | ENTRY CONTROL POINT (GATE 5) |  |  |  | 2014-01-03 | 2015-04-29 | 2016-11-30 | 99% | 2016-11-01
| 2014 | Marine Corps Active | Major Military Construction | California | United States | M00243520 | STEAM PLANT DECENTRALIZATION |  |  |  | 2015-10-13 | 2018-01-11 | 2018-01-11 | 31% | 2018-01-11
| 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263382 | FRONT GATE AT/FP IMPROVMENTS |  |  |  | 2013-10-30 | 2015-04-12 | 2016-01-31 | 97% | 2015-12-09
| 2016 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263398 | RANGE SAFETY IMPROVEMENTS & MODERNIZATION |  |  |  | 2016-10-11 | 2018-04-20 | 2018-04-20 | 1% | 2018-04-20
| 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M002641406 | ATC TX/RX RELOCATION |  |  |  | 2015-05-15 | 2016-11-21 | 2016-11-21 | 5% | 2017-11-21
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  |  |  | 2013-10-07 | 2016-11-06 | 2018-01-22 | 18% | 2018-01-22
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 |  | 3390000 | N32446308; M00318863 | 2012-12-14 | 2016-11-06 | 2018-01-22 | 96% | 2018-01-22
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264572 | INFRASTRUCTURE WIDEN RUSSELL ROAD |  |  |  | 2015-10-15 | 2017-05-28 | 2017-05-28 | 23% | 2017-03-26
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264621 | EMBASSY SECURITY GROUP FACILITIES |  |  |  | 2013-03-14 | 2015-03-15 | 2016-07-21 | 91% | 2015-08-15
| 2015 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264635 | AMMUNITION SUPPLY POINT EXPANSION |  |  |  | 2016-12-16 | 2018-03-25 | 2018-03-25 | 2% | 2018-05-04
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264644 | WEAPONS TRAINING BATALLION MESS HALL |  |  |  | 2013-09-18 | 2015-04-22 | 2016-04-30 | 98% | 2016-08-31
| 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264677 | TECOM SCHOOLS ACADEMIC INSTRUCTION FACILITY |  |  |  | 2016-04-14 | 2018-01-05 | 2018-01-05 | 7% | 2018-01-05
| 2016 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318116 | P-8A DETACHMENT SUPPORT FACILITIES |  |  |  | 2016-08-22 | 2018-06-09 | 2018-06-09 | 2% | 2018-06-14
| 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318778 | ARMORY ADDITION AND RENOVATION |  |  |  | 2015-03-27 | 2017-08-09 | 2018-01-27 | 23% | 2018-01-02
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318852 | 3RD RADIO BATTALION COMPLEX |  |  |  | 2014-09-19 | 2016-10-04 | 2016-10-04 | 24% | 2017-09-15
| 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318861 | FACILITY MODIFICATIONS FOR VMU, MWSD AND CH53E |  |  |  | 2015-09-15 | 2017-09-28 | 2017-09-28 | 6% | 2017-09-28
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318863 | AIRCRAFT MAINTENANCE HANGAR UPGRADES |  |  |  | 2016-10-03 | 2019-04-17 | 2019-04-17 | 1% | 2019-04-17
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  |  |  | 2014-10-14 | 2016-12-18 | 2016-12-18 | 24% | 2018-02-28
| 2016 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318902 | AIRFIELD LIGHTING MODERNIZATION |  |  |  | 2016-12-02 | 2019-06-06 | 2019-06-06 | 1% | 2019-06-06
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  |  |  | 2015-04-28 | 2017-01-03 | 2017-03-24 | 15% | 2018-02-23
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318908 | MV-22 HANGAR |  |  |  | 2015-04-28 | 2017-01-03 | 2017-03-24 | 33% | 2018-02-23
| 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318924 | ROAD & INFRASTRUCTURE IMPROVEMENTS |  |  |  | 2015-10-12 | 2016-11-24 | 2016-11-24 | 13% | 2016-12-27
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M006811045 | NEW POTABLE WATER CONVEYANCE |  | 17000000 | N684691400; M00318863 | 2012-10-12 | 2016-03-31 | 2016-03-31 | 87% | 2018-07-01
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M006811132 | COMMUNICATION INFORMATION SYSTEMS OPS COMPLEX |  |  |  | 2016-04-07 | 2020-01-23 | 2020-01-23 | 7% | 2020-01-23
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M006811176 | SAN JACINTO ROAD EXTENSION |  |  |  | 2014-10-08 | 2016-04-21 | 2016-06-17 | 100% | 2017-09-28
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M00681637 | INFANTRY SQUAD DEFENSE RANGE |  |  |  | 2016-07-14 | 2018-09-23 | 2018-09-23 | 1% | 2018-09-23
| 2014 | Marine Corps Active | Major Military Construction | California | United States | M00681970 | AMMUNITION SUPPLY POINT FACILITIES PULGAS |  |  |  | 2016-01-13 | 2018-04-27 | 2018-04-27 | 8% | 2018-04-27
| 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2014-08-29 | 2016-09-08 | 2017-03-29 | 89% | 2017-02-20
| 2015 | Marine Corps Active | Major Military Construction | California | United States | M62204939 | ENGINE DYNAMOMETER FACILITY |  |  |  | 2015-04-14 | 2016-10-06 | 2016-12-02 | 97% | 2017-01-31
| 2016 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626130702 | WHOLEHOUSE REVITALIZATION MONZEN TOWNHOUSES PHASE 3 |  |  |  | 2016-10-06 | 2017-10-09 | 2017-10-09 | 1% | 2016-06-22
| 2014 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131402 | WHOLEHOUSE REVITALIZATION SOQs |  |  |  | 2016-10-11 | 2018-03-04 | 2018-03-04 | 1% | 2018-03-04
| 2015 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131502 | WHOLEHOUSE REVITALIZATION MIDRISE 656 |  |  |  | 2015-10-11 | 2017-01-30 | 2017-03-07 | 98% | 2017-01-30
| 2013 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974378 | SECURITY OPERATIONS COMPLEX |  |  |  | 2013-11-14 | 2015-07-31 | 2017-01-20 | 92% | 2016-04-28
| 2015 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974617 | AVIATION MAINTENANCE AND SUPPORT COMPLEX |  |  |  | 2016-06-02 | 2017-11-29 | 2017-11-29 | 13% | 2017-11-29
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001003 | STAFF NCO ACADEMY FACILITIES |  |  |  | 2013-09-19 | 2015-09-01 | 2017-03-31 | 99% | 2017-03-31
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011349 | SPECIAL OPERATIONS TRAINING COMPLEX |  |  |  | 2015-09-14 | 2017-03-21 | 2017-10-24 | 44% | 2017-10-24
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011353 | LANDFILL, PHASE 4 |  | 3527000 | N68436993 | 2014-09-08 | 2016-03-01 | 2016-09-01 | 96% | 2016-08-19
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK |  | 297000 | M00318863 | 2012-07-13 | 2014-07-29 | 2016-08-31 | 97% | 2016-10-27
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011383 | BASE ENTRY POINT AND ROAD |  |  |  | 2012-04-17 | 2015-04-18 | 2017-04-23 | 100% | 2017-03-31
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011384 | BASE ACCESS AND ROAD, PHASE 3 |  |  |  | 2012-04-17 | 2015-04-18 | 2017-04-23 | 100% | 2017-03-31
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011445 | STEAM DECENTRALIZATION (CAMP JOHNSON) |  |  |  | 2015-02-06 | 2017-02-06 | 2017-06-17 | 85% | 2017-07-18
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011447 | STEAM DECENTRALIZATION - HADNOT POINT |  |  |  | 2015-02-06 | 2017-02-06 | 2017-06-17 | 91% | 2017-07-18
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011448 | STEAM DECENTRALIZATION (BEQ NODES) |  |  |  | 2015-02-06 | 2016-02-19 | 2016-02-19 | 30% | 2016-03-23
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001674 | CORROSION CONTROL HANGAR |  |  |  | 2015-09-02 | 2017-03-11 | 2017-09-29 | 21% | 2017-09-29
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY |  |  |  | 2014-06-13 | 2015-12-20 | 2016-07-20 | 100% | 2017-03-31
| 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001686 | RADAR AIR TRAFFIC CONTROL FACILITY ADDITION |  |  |  | 2016-10-12 | 2018-04-06 | 2018-04-06 | 1% | 2018-04-06
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001726 | REGIONAL COMMUNICATION STATION |  |  |  | 2014-06-13 | 2015-12-20 | 2016-07-20 | 100% | 2017-03-31
| 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001729 | OPERATIONAL TRAINER FACILITY |  |  |  | 2016-10-12 | 2018-04-06 | 2018-04-06 | 2% | 2018-04-06
| 2014 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  |  |  | 2014-09-24 | 2016-03-17 | 2017-01-06 | 49% | 2016-03-17
| 2015 | Marine Corps Active | Major Military Construction | California | United States | M67399159 | CAMP WILSON INFRASTRUCTURE UPGRADES |  |  |  | 2015-04-29 | 2017-05-01 | 2017-05-01 | 96% | 2017-05-01
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA |  |  |  | 2012-08-27 | 2014-09-02 | 2016-09-20 | 99% | 2016-09-20
| 2015 | Marine Corps Active | Major Military Construction | California | United States | M67399222 | E-LMR SLICE COMMUNICATION TOWERS |  |  |  | 2016-09-14 | 2019-03-04 | 2019-03-04 | 1% | 2019-03-04
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67399991 | LAND EXPANSION |  | 5103000 | N32446308; M00318863 | 2016-01-30 | 2016-01-19 | 2016-01-19 | 54% | 2016-01-19
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M67399992 | LAND EXPANSION - PHASE 2 |  |  |  | 2016-01-30 | 2016-01-19 | 2016-01-19 | 40% | 2016-01-19
| 2014 | Marine Corps Active | Major Military Construction |  | Japan | M67400201 | AIRFIELD SECURITY UPGRADES |  |  |  | 2014-05-02 | 2015-11-18 | 2015-11-18 | 91% | 2015-11-18
| 2016 | Marine Corps Active | Major Military Construction |  | Japan | M67400606 | MILITARY WORKING DOG FACILITIES (CAMP HANSEN) |  |  |  | 2016-09-29 | 2018-03-26 | 2018-03-26 | 2% | 2018-03-26
| 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400801 | LHD PRACTICE SITE IMPROVEMENTS |  |  |  | 2016-05-05 | 2017-07-29 | 2017-07-29 | 8% | 2017-07-29
| 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400803 | AIRCRAFT MAINT HANGAR ALTERATIONS AND SAP-F |  |  |  | 2016-01-05 | 2017-09-12 | 2017-09-12 | 11% | 2017-09-12
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67604117 | MV-22 AVIATION FUEL STORAGE |  |  |  | 2013-11-21 | 2014-12-12 | 2015-05-26 | 76% | 2016-06-24
| 2016 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M67604132 | ORDNANCE BULD-UP FACILITY |  |  |  | 2016-09-14 | 2017-10-30 | 2017-10-30 | 4% | 2017-10-30
| 2014 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  |  |  | 2014-05-21 | 2016-12-03 | 2017-03-08 | 80% | 2017-10-31
| 2014 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557J200 | NORTH RAMP UTILITIES II |  |  |  | 2014-10-31 | 2016-09-02 | 2016-09-02 | 1% | 2016-10-03
| 2014 | Marine Corps Active | Military Family Housing Improvement | Guam | Guam | N61755H106 | WHOLE HOUSE REVITALIZATION PHASE II AT LOCKWOOD TERRACE |  |  |  | 2015-05-14 | 2017-08-13 | 2018-06-22 | 30% | 2018-06-09
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | N69212984 | REGIMENTAL HEADQUARTERS |  |  |  | 2013-09-13 | 2015-06-26 | 2016-09-04 | 100% | 2017-03-30
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | N69212985 | BACHELOR ENLISTED QUARTERS |  |  |  | 2013-09-13 | 2015-06-26 | 2016-09-04 | 100% | 2017-03-30
| 2014 | Marine Corps Reserve | Major Military Construction | Missouri | United States | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  |  |  | 2014-09-05 | 2016-03-25 | 2016-06-16 | 100% | 2017-06-16
| 2013 | Marine Corps Reserve | Major Military Construction | New York | United States | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY |  |  |  | 2013-09-19 | 2014-12-04 | 2015-10-13 | 100% | 2017-01-31
| 2015 | Marine Corps Reserve | Major Military Construction | Washington | United States | N00620234 | C-40 RESERVE MAINTENANCE HANGAR |  |  |  | 2015-08-12 | 2016-12-15 | 2017-03-06 | 72% | 2017-03-01
2017-01-31 | 2013 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  |  |  | 2013-07-31 | 2015-08-30 | 2016-11-30 | 99%
2017-01-31 | 2014 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #2 | 646 |  |  | 2013-07-31 | 2015-08-30 | 2016-11-30 | 99%
2017-01-31 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  |  |  | 2014-07-07 | 2016-01-06 | 2016-01-06 | 100% | 2016-01-06
2017-01-31 | 2013 | Missile Defense Agency | Major Military Construction | New York | United States | 639 | In-Flight Interceptor Data Terminal Complex |  | 1801000 | 630 | 2013-08-10 | 2014-11-28 | 2015-09-12 | 100% | 2015-02-04
2017-01-31 | 2016 | Missile Defense Agency | Major Military Construction |  | Poland | 640 | Aegis Ashore Missile Defense System Complex |  |  |  | 2016-03-14 | 2018-03-30 | 2018-03-30 | 7%
2017-01-31 | 2014 | Missile Defense Agency | Major Military Construction |  | Japan | 648 | AN/TPY-2 Radar Site |  |  |  | 2014-05-27 | 2015-01-09 | 2015-02-20 | 100% | 2015-02-03
2017-01-31 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 22900000 | 646 | 2014-05-27 | 2016-05-31 | 2016-05-31 | 100% | 2016-05-04
2017-01-31 | 2016 | Missile Defense Agency | Unspecified Minor Military Construction |  | Wake Island | 661 | Flight Test Communication Facility |  |  |  | 2016-05-25 | 2016-08-31 | 2016-11-04 | 99%
2017-03-15 | 2015 | National Geospatial-Intelligence Agency | Major Military Construction | Virginia | United States | 030 | Parking Lot |  |  |  | 2016-08-10 | 2016-09-16 | 2017-02-01 | 100%
2017-03-15 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | Virginia | United States | 65416 | NGA Headquarters, SCIF, All Phases |  |  |  | 2007-09-06 | 2011-12-22 | 2018-09-03 | 99% | 2011-04-19
2017-01-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17781 | Tordella Chilled Water Backup Storage |  |  |  | 2010-06-30 | 2011-08-20 | 2012-05-30 | 100% | 2012-05-30
2017-01-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17782 | R&E Chilled Water Backup Storage |  |  |  | 2011-11-07 | 2013-07-13 | 2016-02-05 | 100% | 2016-02-05
2017-01-31 | 2011 | National Security Agency | Major Military Construction | Maryland | United States | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 54500000 | Mountainview, South Campus Electrical Utility Plant | 2011-10-04 | 2014-11-30 | 2015-10-31 | 99% | 2014-11-30
2017-01-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 37500000 | Due to a Congressional rescission of funds | 2010-09-21 | 2014-04-18 | 2015-11-30 | 99% | 2015-10-12
2017-01-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18052 | Power & Cooling Infrastructure Upgrade |  |  |  | 2011-03-31 | 2013-02-01 | 2014-05-14 | 100% | 2014-05-14
2017-01-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18053 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-01-31 | 2013-02-01 | 2014-05-31 | 100% | 2014-05-31
2017-01-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18054 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-11-30 | 2013-02-01 | 2014-08-31 | 100% | 2014-08-31
2017-01-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II |  |  |  | 2012-05-30 | 2014-01-30 | 2015-01-16 | 100% | 2014-03-03
2017-01-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II (Phase 2) | 2 |  |  | 2013-11-26 | 2014-02-28 | 2014-04-28 | 100% | 2014-09-30
2017-01-31 | 2009 | National Security Agency | Major Military Construction | Maryland | United States | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  |  |  | 2010-09-21 | 2013-01-17 | 2014-04-18 | 99% | 2013-01-17
2017-01-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  |  |  | 2010-09-09 | 2011-09-26 | 2012-06-29 | 99% | 2012-06-29
2017-01-31 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview |  |  |  | 2012-11-02 | 2015-05-03 | 2015-07-28 | 99% | 2015-08-30
2017-01-31 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview | 2 |  |  | 2013-10-13 | 2014-02-14 | 2015-09-30 | 100% | 2014-04-30
2017-01-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 23994 | Whitelaw Wedge |  |  |  | 2012-07-18 | 2014-01-30 | 2014-12-23 | 100% | 2015-08-28
2017-01-31 | 2012 | National Security Agency | Major Military Construction | Maryland | United States | 24649 | High Performance Computing Center 2 |  |  |  | 2013-03-13 | 2015-09-15 | 2016-02-08 | 99% | 2016-02-08
2017-01-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  |  |  | 1915-11-09 | 2014-03-07 | 2015-05-04 | 99% | 2014-11-30
2017-01-31 | 2013 | National Security Agency | Major Military Construction | Maryland | United States | 26170 | East Campus Building 1 (ECB1) |  |  |  | 2013-10-24 | 2015-10-11 | 2016-11-30 | 86% | 2017-02-24
2017-01-31 | 2015 | National Security Agency | Major Military Construction | Maryland | United States | 27532 | North Campus Buildings Feeders - Phase 1 |  |  |  | 2016-09-01 | 2018-03-01 | 2018-04-26 | 10% | 2018-10-25
2017-01-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 30583 | East Campus Building 2 (ECB2) |  |  |  | 2016-07-18 | 2020-09-09 | 2020-09-09 | 1%
2017-01-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 31066 | North Campus Buildings Feeders - Phase 2 |  |  |  | 2016-11-14 | 2018-08-08 | 2018-08-08 | 1% | 2018-08-08
2017-01-31 | 2016 | National Security Agency | Major Military Construction | Georgia | United States | 31934 | ICECUBE |  |  |  | 2015-11-19 | 2016-12-31 | 2016-12-31 | 90%
2017-01-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 32122 | VCP-1 |  |  |  | 2016-06-23 | 2018-06-08 | 2018-06-08 | 0%
| 2015 | Navy Active | Unspecified Minor Military Construction | North Carolina | United States | M00146996 | UTILITY SERVICE UPGRADES, BUILDING 245 |  |  |  | 2015-09-16 | 2017-03-31 | 2017-04-29 | 76% | 2017-02-18
| 2016 | Navy Active | Major Military Construction | Virginia | United States | M00264714 | ELECTRICAL DISTRIBUTION UPGRADE |  |  |  | 2016-07-28 | 2017-07-29 | 2017-07-29 | 10% | 2017-07-29
| 2016 | Navy Active | Major Military Construction | Hawaii | United States | M00318910 | BACHELOR ENLISTED QUARTERS |  |  |  | 2016-07-26 | 2018-10-31 | 2018-10-31 | 4% | 2018-10-31
| 2012 | Navy Active | Major Military Construction | California | United States | M006811046 | NORTH AREA WASTE WATER CONVEYANCE |  |  |  | 2014-12-09 | 2016-12-08 | 2016-12-08 | 15% | 2017-11-01
| 2016 | Navy Active | Major Military Construction | California | United States | M006811220 | RAW WATER PIPELINE PENDLETON TO FALLBROOK |  |  |  | 2016-12-14 | 2019-03-30 | 2019-03-30 | 1% | 2019-03-30
| 2014 | Navy Active | Military Family Housing Improvement |  | Japan | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 |  |  |  | 2014-10-13 | 2016-02-02 | 2016-02-02 | 98% | 2016-02-19
| 2015 | Navy Active | Major Military Construction |  | Japan | M62613602 | SECURITY MODS DPRI MC167-T (CVW-5 E2D EA-18G) |  |  |  | 2015-05-11 | 2016-06-24 | 2016-06-24 | 95% | 2016-06-24
| 2016 | Navy Active | Major Military Construction | North Carolina | United States | M670011346 | SIMULATOR INTEGRATION/RANGE CONTROL FACILITY |  |  |  | 2016-08-12 | 2018-08-13 | 2018-08-13 | 8% | 2018-08-13
| 2012 | Navy Active | Major Military Construction | Illinois | United States | N00128816 | DECENTRALIZE STEAM SYSTEM |  | 2068000 | Design; N61151222 | 2012-06-27 | 2016-06-30 | 2016-06-30 | 83% | 2015-08-26
| 2016 | Navy Active | Major Military Construction | Florida | United States | N00207334 | FLEET SUPPORT FACILITY ADDITION |  |  |  | 2016-04-01 | 2017-06-11 | 2017-06-11 | 25% | 2017-06-11
| 2015 | Navy Active | Major Military Construction | Florida | United States | N00207631 | P-8A RUNWAY THRESHOLDS AND TAXIWAYS |  | 5357000 | Design | 2015-03-13 | 2016-04-19 | 2016-08-16 | 99% | 2016-08-16
| 2014 | Navy Active | Major Military Construction | Florida | United States | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION |  | 6752000 | Design | 2014-10-10 | 2016-04-19 | 2016-08-16 | 88% | 2016-08-16
| 2016 | Navy Active | Major Military Construction | Florida | United States | N00207662 | TRITON MISSION CONTROL FACILITY |  |  |  | 2016-10-11 | 2017-07-07 | 2017-11-13 | 1% | 2017-07-07
| 2015 | Navy Active | Major Military Construction | Florida | United States | N00207664 | MH-60 PARKING APRON |  |  |  | 2015-05-14 | 2016-04-30 | 2016-11-14 | 81% | 2017-03-31
| 2014 | Navy Active | Major Military Construction | Florida | United States | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  |  |  | 2014-08-29 | 2016-01-07 | 2016-11-15 | 84% | 2016-11-15
| 2016 | Navy Active | Major Military Construction | California | United States | N00245499 | LCS SUPPORT FACILITY |  |  |  | 2016-09-12 | 2018-08-29 | 2018-08-29 | 1% | 2018-08-29
| 2013 | Navy Active | Major Military Construction | California | United States | N00245500 | LCS TRAINING FACILITY |  | 10760000 | N42237100 | 2013-10-14 | 2015-10-24 | 2017-01-10 | 98% | 2017-01-10
| 2015 | Navy Active | Major Military Construction | California | United States | N00245800 | STEAM DISTRIBUTION SYSTEM DECENTRALIZATION |  |  |  | 2015-10-01 | 2017-10-01 | 2017-10-01 | 46% | 2017-12-27
| 2013 | Navy Active | Major Military Construction | California | United States | N00246730 | BACHELOR QUARTERS |  |  |  | 2015-08-13 | 2017-07-29 | 2017-09-14 | 79% | 2017-07-14
| 2012 | Navy Active | Major Military Construction | California | United States | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND |  | 2604000 | Design; N61151222 | 2012-07-17 | 2015-03-30 | 2015-10-18 | 99% | 2016-01-20
| 2014 | Navy Active | Major Military Construction | California | United States | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND |  | 238000 | N68436993 | 2014-08-18 | 2016-02-10 | 2016-09-08 | 98% | 2016-09-08
| 2015 | Navy Active | Unspecified Minor Military Construction | California | United States | N00246987 | PIER 21 UPGRADES FOR MARK VI PATROL BOAT |  |  |  | 2015-09-30 | 2016-09-19 | 2016-09-19 | 99% | 2016-05-26
| 2016 | Navy Active | Major Military Construction | California | United States | N00246998 | COASTAL CAMPUS UTILITIES |  |  |  | 2016-02-02 | 2018-04-02 | 2018-09-30 | 44% | 2017-09-29
| 2014 | Navy Active | Major Military Construction | Washington | United States | N00620239 | EA-18G FACILITY IMPROVEMENTS |  | 620000 | Design | 2014-09-08 | 2017-05-26 | 2017-05-26 | 76% | 2017-02-15
| 2014 | Navy Active | Major Military Construction | Washington | United States | N00620251 | P-8A HANGAR AND TRAINING FACILITIES |  |  |  | 2014-08-04 | 2016-01-12 | 2016-04-29 | 92% | 2016-05-02
| 2015 | Navy Active | Major Military Construction | Washington | United States | N00620259 | P-8A AIRCRAFT APRON AND SUPPORTING FACILITIES |  |  |  | 2017-01-04 | 2018-06-19 | 2018-06-19 | 8% | 2018-06-19
| 2014 | Navy Active | Major Military Construction | Rhode Island | United States | N32411103 | HEWITT HALL RESEARCH CENTER |  |  |  | 2014-08-14 | 2015-12-16 | 2016-01-01 | 99% | 2016-07-25
| 2015 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  |  |  | 2015-06-01 | 2016-11-23 | 2017-03-09 | 60% | 2017-06-04
| 2012 | Navy Active | Major Military Construction | Virginia | United States | N32443383 | CONTROLLED INDUSTRIAL FACILITY |  | 7621000 | N684691400 | 2012-06-14 | 2014-09-28 | 2015-06-15 | 100% | 2017-01-31
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N32443527 | SUBMARINE MAINTENANCE FACILITY |  |  |  | 2015-09-17 | 2017-04-20 | 2017-07-19 | 25% | 2017-07-19
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE |  |  |  | 2013-12-11 | 2015-12-27 | 2016-08-30 | 98% | 2016-08-30
| 2014 | Navy Active | Major Military Construction | Maine | United States | N32446266 | STRUCTURAL SHOPS CONSOLIDATION |  |  |  | 2015-08-31 | 2018-01-23 | 2018-01-23 | 45% | 2018-06-15
| 2014 | Navy Active | Major Military Construction | Maine | United States | N32446308 | NCTAMS VLF COMMERCIAL POWER CONNECTION |  | 1104000 | N68436993 | 2016-05-05 | 2018-10-25 | 2018-10-25 | 51% | 2017-10-25
| 2015 | Navy Active | Unspecified Minor Military Construction |  | Djibouti | N3379A064 | POST OFFICE FACILITY |  |  |  | 2015-09-25 | 2017-01-23 | 2017-01-23 | 82% | 2017-01-09
| 2014 | Navy Active | Major Military Construction |  | Djibouti | N3379A227 | ARMORY |  | 1910000 | Design | 2014-08-08 | 2015-09-28 | 2016-06-29 | 99% | 2016-10-31
| 2015 | Navy Active | Major Military Construction |  | Djibouti | N3379A330 | ENTRY CONTROL POINT |  | 1819000 | N68436993; Design | 2015-09-25 | 2017-01-18 | 2017-01-18 | 97% | 2017-01-18
| 2014 | Navy Active | Major Military Construction |  | Djibouti | N3379A921 | UNACCOMPANIED HOUSING |  | 2146000 | N68436993; Design | 2014-10-15 | 2016-05-30 | 2016-09-30 | 99% | 2016-09-30
| 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557230 | DPRI-GSE SHOPS AT NORTH RAMP |  |  |  | 2015-12-01 | 2018-06-19 | 2018-06-19 | 14% | 2018-10-17
| 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557240 | DPRI-MWSS FACILITIES AT NORTH RAMP |  |  |  | 2015-10-13 | 2018-05-02 | 2018-05-02 | 15% | 2018-05-11
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  |  |  | 2014-04-10 | 2016-04-25 | 2017-09-28 | 79% | 2017-01-16
| 2015 | Navy Active | Major Military Construction | South Carolina | United States | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  |  |  | 2015-08-05 | 2018-06-20 | 2018-04-22 | 20% | 2018-04-22
| 2014 | Navy Active | Major Military Construction | South Carolina | United States | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  |  |  | 2014-09-03 | 2018-06-20 | 2018-04-22 | 68% | 2018-04-22
| 2012 | Navy Active | Major Military Construction | South Carolina | United States | N42237611 | CRAB ISLAND SECURITY ENCLAVE |  |  |  | 2016-07-12 | 2018-11-30 | 2018-11-30 | 1% | 2018-11-30
| 2012 | Navy Active | Major Military Construction | Georgia | United States | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE |  |  |  | 2014-05-01 | 2017-04-16 | 2017-04-16 | 86% | 2017-04-16
| 2015 | Navy Active | Major Military Construction | Maryland | United States | N47608155 | ATLANTIC TEST RANGE FACILITY |  |  |  | 2015-10-14 | 2017-08-20 | 2017-08-20 | 32% | 2017-08-20
| 2014 | Navy Active | Unspecified Minor Military Construction | Maryland | United States | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  |  |  | 2014-10-14 | 2016-09-29 | 2017-06-06 | 100% | 2016-06-06
| 2012 | Navy Active | Major Military Construction | Maryland | United States | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 |  |  |  | 2014-07-14 | 2016-04-01 | 2017-02-23 | 82% | 2017-08-24
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N50092354 | EOD CONSOLIDATED OPS AND LOGISTICS FACILITIES |  |  |  | 2015-10-12 | 2018-10-07 | 2018-10-07 | 31% | 2018-10-07
| 2016 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N50092726 | ExMCM UUV OPERATIONS AND MAINTENANCE FACILITY |  |  |  | 2016-10-13 | 2018-04-07 | 2018-04-07 | 1% | 2018-04-07
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N60191513 | A SCHOOL BARRACKS |  | 5604000 | N42237100 | 2013-11-14 | 2015-12-16 | 2016-11-22 | 100% | 2017-01-05
| 2012 | Navy Active | Major Military Construction | Virginia | United States | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS |  |  |  | 2012-10-11 | 2014-10-12 | 2015-09-06 | 100% | 2017-03-01
| 2016 | Navy Active | Major Military Construction | Virginia | United States | N60191603 | MARITIME SURVEILLANCE SYSTEM FACILITY |  |  |  | 2016-06-29 | 2017-06-30 | 2017-11-12 | 10% | 2017-06-30
| 2014 | Navy Active | Major Military Construction | Virginia | United States | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  |  |  | 2014-09-30 | 2016-10-25 | 2018-02-20 | 30% | 2018-11-02
| 2015 | Navy Active | Major Military Construction | Florida | United States | N60201423 | LCS OPERATIONAL TRAINING FACILITY |  |  |  | 2016-11-29 | 2018-04-09 | 2018-04-09 | 1% | 2018-04-09
| 2016 | Navy Active | Major Military Construction | Florida | United States | N60201424 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2016-07-28 | 2018-02-05 | 2018-02-05 | 13% | 2018-02-05
| 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495420 | AIR WING TRAINING FACILITY |  |  |  | 2015-09-30 | 2017-11-24 | 2018-11-24 | 8% | 2017-11-24
| 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495430 | FACILITY ALTERATION FOR F-35 TRAINING MISSION |  |  |  | 2016-10-13 | 2017-11-23 | 2017-11-23 | 1% | 2017-11-23
| 2016 | Navy Active | Major Military Construction | Florida | United States | N60508274 | T-6B JPATS TRAINING OPERATIONS FACILITY |  |  |  | 2016-07-04 | 2018-03-24 | 2018-03-24 | 6% | 2018-03-24
| 2015 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60508278 | PAVEMENT LANDING SYSTEMS |  |  |  | 2015-08-05 | 2016-04-28 | 2016-04-28 | 89% | 2016-04-28
| 2012 | Navy Active | Major Military Construction | Florida | United States | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE |  |  |  | 2012-06-21 | 2015-11-24 | 2015-11-24 | 96% | 2015-11-24
| 2014 | Navy Active | Major Military Construction |  | Japan | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  |  |  | 2014-10-03 | 2017-01-17 | 2017-01-17 | 4% | 2017-01-17
| 2016 | Navy Active | Major Military Construction |  | Japan | N61054023 | CHILD DEVELOPMENT CENTER |  |  |  | 2017-01-02 | 2018-09-30 | 2018-09-30 | 1% | 2018-12-31
| 2013 | Navy Active | Military Family Housing Improvement |  | Japan | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 |  |  |  | 2014-07-29 | 2016-02-21 | 2016-02-21 | 98% | 2016-05-02
| 2014 | Navy Active | Military Family Housing Improvement |  | Japan | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) |  |  |  | 2014-10-14 | 2016-01-01 | 2016-01-01 | 91% | 2016-01-01
| 2014 | Navy Active | Major Military Construction | California | United States | N61065202 | NOSC MORENO VALLEY RESERVE TRAINING CENTER |  |  |  | 2016-09-12 | 2018-06-10 | 2018-06-10 | 1% | 2018-06-10
| 2013 | Navy Active | Major Military Construction | California | United States | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB |  | 659000 | N68436993 | 2013-10-14 | 2016-04-17 | 2016-06-16 | 99% | 2016-06-06
| 2014 | Navy Active | Unspecified Minor Military Construction | California | United States | N61065240 | STANDARD MISSILE-6 ALL UP ROUND TEST FACILITY |  |  |  | 2015-04-30 | 2016-10-21 | 2016-10-21 | 92% | 2016-10-12
| 2016 | Navy Active | Major Military Construction | Washington | United States | N61066603 | SHORE POWER TO AMMUNITION PIER |  |  |  | 2016-02-19 | 2017-03-06 | 2017-03-06 | 61% | 2017-05-31
| 2012 | Navy Active | Major Military Construction | Maryland | United States | N61151222 | DECENTRALIZE STEAM SYSTEM |  |  |  | 2012-10-12 | 2016-07-14 | 2016-07-14 | 99% | 2016-07-14
| 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151287 | MISSILE SUPPORT FACILITY |  |  |  | 2015-09-16 | 2017-07-17 | 2018-05-14 | 42% | 2018-05-01
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N61151372 | PHYSICAL FITNESS CENTER |  |  |  | 2013-10-11 | 2015-05-02 | 2016-01-04 | 99% | 2016-01-05
| 2014 | Navy Active | Major Military Construction | Maryland | United States | N61152001 | MARFORCYBERCOM HQ-OPS BUILDING |  |  |  | 2015-04-21 | 2017-05-05 | 2017-05-05 | 42% | 2017-05-05
| 2015 | Navy Active | Major Military Construction | Maryland | United States | N61152621 | CYBER SECURITY STUDIES BUILDING |  |  |  | 2016-04-14 | 2019-03-22 | 2019-09-08 | 17% | 2019-09-08
| 2014 | Navy Active | Military Family Housing Improvement | Guam | Guam | N617551403 | WHOLE HOUSE REVITALIZATION PHASE II AT LOCKWOOD TERRACE |  |  |  | 2015-05-14 | 2017-08-13 | 2017-12-02 | 68% | 2017-09-29
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755425 | MODULAR STORAGE MAGAZINE |  |  |  | 2014-05-26 | 2016-06-11 | 2017-04-20 | 65% | 2017-05-19
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755518 | X-RAY WHARF IMPROVEMENTS |  |  |  | 2014-06-17 | 2016-10-20 | 2017-03-15 | 68% | 2017-05-04
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755566 | EMERGENT REPAIR FACILITY EXPANSION |  |  |  | 2014-04-24 | 2016-05-12 | 2016-08-28 | 100% | 2017-01-20
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY |  | 271000 | Design | 2014-04-03 | 2016-04-11 | 2016-05-09 | 86% | 2016-05-03
| 2016 | Navy Active | Unspecified Minor Military Construction | Guam | Guam | N61755656 | HEAVY WEATHER MOORING SIERRA WHARF, GUAM |  |  |  | 2016-09-29 | 2017-07-13 | 2017-07-13 | 1% | 2017-07-13
| 2013 | Navy Active | Major Military Construction |  | Romania | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  |  |  | 2014-05-14 | 2016-03-04 | 2016-03-04 | 93% | 2016-03-04
| 2016 | Navy Active | Major Military Construction |  | Poland | N62592401 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  |  |  | 2016-05-20 | 2017-11-09 | 2017-11-09 | 21% | 2017-11-09
| 2014 | Navy Active | Major Military Construction | Virginia | United States | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  |  |  | 2014-07-14 | 2016-01-01 | 2016-11-11 | 98% | 2017-02-03
| 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688518 | MH-60 HELICOPTER TRAINING FACILITY |  |  |  | 2016-03-17 | 2017-09-29 | 2017-09-29 | 19% | 2018-01-07
| 2016 | Navy Active | Major Military Construction | Hawaii | United States | N62813036 | WELDING SCHOOL SHOP CONSOLIDATION |  |  |  | 2016-02-09 | 2018-03-26 | 2018-04-29 | 15% | 2018-03-26
| 2015 | Navy Active | Major Military Construction | Hawaii | United States | N62813048 | SUBMARINE MANEUVERING ROOM TRAINER FACILITY |  |  |  | 2015-03-13 | 2016-10-04 | 2017-02-10 | 85% | 2017-02-02
| 2014 | Navy Active | Unspecified Minor Military Construction | Hawaii | United States | N62813058 | ROCKFALL PROTECTION AT RED HILL |  |  |  | 2014-12-08 | 2016-05-18 | 2016-05-18 | 100% | 2016-12-30
| 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813270 | DRYDOCK WATERFRONT FACILITY |  |  |  | 2014-03-03 | 2015-12-11 | 2015-12-11 | 22% | 2018-12-30
| 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  |  |  | 2014-07-14 | 2017-08-03 | 2018-02-24 | 88% | 2018-02-24
| 2012 | Navy Active | Military Family Housing Improvement |  | Spain | N628631201 | WHOLEHOUSE REVITALIZATION, LAS PALMERAS, PHASE 3 |  |  |  | 2015-03-27 | 2017-07-13 | 2017-07-13 | 28% | 2017-07-13
| 2015 | Navy Active | Major Military Construction |  | Spain | N62863712 | SHIP BERTHING POWER UPGRADES |  |  |  | 2015-12-04 | 2018-05-23 | 2018-05-23 | 37% | 2018-05-23
| 2016 | Navy Active | Major Military Construction |  | Italy | N62995407 | TRITON HANGAR AND OPERATION FACILITY |  |  |  | 2016-12-06 | 2019-01-08 | 2019-01-08 | 1% | 2019-02-05
| 2016 | Navy Active | Major Military Construction |  | Italy | N62995655 | P-8A HANGAR AND FLEET SUPPORT FACILITY |  |  |  | 2016-12-06 | 2019-01-08 | 2019-01-08 | 9% | 2019-02-05
| 2015 | Navy Active | Major Military Construction |  | Bahrain | N63005955 | P-8A HANGAR |  | 4857000 | N68436993; Design | 2015-09-30 | 2018-11-09 | 2018-11-09 | 18% | 2018-11-09
| 2016 | Navy Active | Major Military Construction |  | Bahrain | N63005970 | SHIP MAINTENANCE SUPPORT FACILITY(MINA SULMAN PIER |  |  |  | 2016-06-05 | 2018-11-06 | 2018-11-06 | 12% | 2018-07-06
| 2016 | Navy Active | Major Military Construction | California | United States | N63042218 | RTO AND MISSION DEBRIEF FACILITY |  |  |  | 2016-05-20 | 2017-11-16 | 2018-01-15 | 3% | 2017-11-16
| 2015 | Navy Active | Major Military Construction | California | United States | N63042327 | F-35C OPERATIONAL TRAINING FACILITY |  |  |  | 2015-07-10 | 2016-10-17 | 2017-02-10 | 92% | 2017-02-10
| 2015 | Navy Active | Major Military Construction | California | United States | N63042328 | F-35C FACILITY ADDITION AND MODIFICATION |  |  |  | 2015-06-25 | 2016-11-03 | 2016-12-06 | 95% | 2016-12-14
| 2015 | Navy Active | Unspecified Minor Military Construction | California | United States | N63042377 | CARRIER AIR WING FOURTEEN (CVW-14) FACILITY |  |  |  | 2016-03-11 | 2016-05-26 | 2020-05-21 | 11% | 2017-04-30
| 2016 | Navy Active | Major Military Construction | California | United States | N63042378 | F-35C HANGAR MODERNIZATION AND ADDITION |  |  |  | 2016-06-14 | 2017-12-07 | 2017-12-07 | 4% | 2017-12-07
| 2016 | Navy Active | Major Military Construction | California | United States | N63042379 | F-35C TRAINING FACILITIES |  |  |  | 2016-03-31 | 2017-03-31 | 2017-05-23 | 44% | 2017-05-23
| 2013 | Navy Active | Major Military Construction | Mississippi | United States | N63043317 | DINING FACILITY |  | 465000 | N68436993 | 2013-12-31 | 2015-10-09 | 2016-09-11 | 84% | 2016-06-03
| 2013 | Navy Active | Major Military Construction |  | Greece | N66691907 | AIRCRAFT PARKING APRON EXPANSION |  | 3574000 | FY Prior Year Rescission; Design | 2014-07-25 | 2016-05-15 | 2016-07-10 | 98% | 2016-08-14
| 2013 | Navy Active | Major Military Construction |  | Greece | N66691908 | INTERMODAL ACCESS ROAD |  |  |  | 2016-08-25 | 2017-11-24 | 2017-11-24 | 3% | 2017-11-24
| 2014 | Navy Active | Major Military Construction | Washington | United States | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  | 5484000 | Design | 2014-08-01 | 2016-02-16 | 2016-02-16 | 100% | 2017-06-09
| 2015 | Navy Active | Major Military Construction | Washington | United States | N68436422 | INTEGRATED WATER TREATMENT SYSTEM DD 1, 2 & 5 |  | 3264000 | Design; P993 | 2015-05-18 | 2016-10-25 | 2016-10-25 | 66% | 2017-05-31
| 2016 | Navy Active | Major Military Construction | Washington | United States | N68436431 | DRY DOCK 6 MODERNIZATION & UTILITY IMPROVE. |  |  |  | 2016-08-25 | 2017-11-14 | 2017-11-14 | 2% | 2017-11-14
| 2014 | Navy Active | Unspecified Minor Military Construction | Washington | United States | N68436855 | SUBMARINE BRIDGE TEAM SIMULATOR |  |  |  | 2015-07-14 | 2016-05-15 | 2016-05-30 | 100% | 2017-02-03
| 2016 | Navy Active | Major Military Construction | Washington | United States | N68436983 | WRA LAND/WATER INTERFACE |  |  |  | 2016-10-05 | 2018-02-13 | 2018-02-13 | 1% | 2018-02-13
| 2012 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 |  |  |  | 2012-05-23 | 2016-01-09 | 2017-04-07 | 100% | 2016-12-23
| 2013 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | N68436990A |  |  | 2012-11-15 | 2016-01-09 | 2017-04-07 | 97% | 2016-12-23
| 2014 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990B |  |  | 2014-01-14 | 2016-01-09 | 2017-04-07 | 68% | 2016-12-23
| 2015 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 - INC 4 | N68436990C | 2728000 | P222; P993 | 2015-01-22 | 2016-01-09 | 2017-04-07 | 86% | 2016-12-23
| 2015 | Navy Active | Major Military Construction | Washington | United States | N68436993 | TPS PORT ANGELES FORWARD OPERATING LOCATION |  |  |  | 2016-09-13 | 2018-02-06 | 2018-02-06 | 9% | 2018-02-06
| 2012 | Navy Active | Major Military Construction |  | Diego Garcia | N68539184 | POTABLE WATER PLANT MODERNIZATION |  |  |  | 2013-01-04 | 2015-07-30 | 2016-04-30 | 100% | 2016-12-30
| 2014 | Navy Active | Major Military Construction | Virginia | United States | N69212461 | SMALL ARMS RANGES |  |  |  | 2015-10-13 | 2017-02-25 | 2017-06-16 | 52% | 2017-06-16
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N69212991 | BACHELOR ENLISTED QUARTERS |  |  |  | 2016-03-22 | 2018-03-23 | 2018-03-23 | 8% | 2018-03-23
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N69212992 | FAST COMPANY TRAINING FACILITY |  |  |  | 2015-10-13 | 2016-09-28 | 2017-09-28 | 6% | 2016-09-28
| 2016 | Navy Active | Major Military Construction | California | United States | N69232565 | E-2C/D HANGAR ADDITIONS AND RENOVATIONS |  |  |  | 2016-04-13 | 2017-04-14 | 2017-04-14 | 56% | 2017-04-30
| 2014 | Navy Active | Major Military Construction | California | United States | N69232593 | BAMS CONSOLIDATED MAINTENANCE HANGAR |  |  |  | 2015-01-30 | 2016-09-17 | 2017-03-28 | 76% | 2017-05-31
| 2014 | Navy Active | Major Military Construction | California | United States | N69232599 | UNACCOMPANIED HOUSING CONVERSION (PORT HUENEME) |  | 1256000 | Design | 2014-12-08 | 2016-03-12 | 2016-03-12 | 1% | 2016-03-12
| 2016 | Navy Active | Major Military Construction | California | United States | N69232607 | TRITON AVIONICS AND FUEL SYSTEMS TRAINER |  |  |  | 2016-09-08 | 2017-11-08 | 2017-11-08 | 6% | 2017-11-08
| 2013 | Navy Active | Major Military Construction | California | United States | N69232900 | BAMS MAINTENANCE TRAINING FACILITY |  | 1678000 | Design | 2013-09-10 | 2014-11-21 | 2015-10-31 | 95% | 2015-10-29
| 2014 | Navy Active | Major Military Construction | Texas | United States | N83447136 | TACAMO E-6B HANGAR |  |  |  | 2014-10-14 | 2016-02-12 | 2016-06-19 | 100% | 2016-12-20
| 2015 | Navy Reserve | Unspecified Minor Military Construction | Connecticut | United States | N00129664 | CORIVRON 8 RESERVE HVU DET SUPPORT FACILITIES |  |  |  | 2015-09-08 | 2016-09-08 | 2016-09-08 | 100% | 2017-02-15
| 2013 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206470 | TRANSIENT QUARTERS |  |  |  | 2015-09-15 | 2017-03-09 | 2017-04-30 | 54% | 2017-03-09
| 2016 | Navy Reserve | Unspecified Minor Military Construction | Louisiana | United States | N00206509 | POLICE STATION ADDITION |  |  |  | 2016-10-14 | 2017-09-29 | 2017-09-29 | 14% | 2017-09-29
| 2015 | Navy Reserve | Unspecified Minor Military Construction | Florida | United States | N00207278 | CRS 10 BOAT MAINTENANCE FACILITY |  |  |  | 2015-10-14 | 2016-10-14 | 2017-05-17 | 81% | 2016-11-13
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | Kentucky | United States | 36977 | System Integration Maintenance Office Facility |  |  |  | 2015-09-10 | 2017-03-03 | 2017-08-04 | 67%
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | Colorado | United States | 47942 | Language Training Facility |  |  |  | 2016-07-08 | 2017-03-01 | 2018-01-04 | 1%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Arizona | United States | 53542 | Parachute Training Facility |  |  |  | 2014-11-09 | 2016-02-07 | 2016-02-20 | 100%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 61064 | SOF Upgrade Training Facility |  |  |  | 2014-11-17 | 2016-05-10 | 2016-10-20 | 99%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 65052 | Medical Support Addition |  |  |  | 2013-10-16 | 2015-08-25 | 2014-12-18 | 98% | 2014-12-18
2017-02-15 | 2011 | Special Operations Command | Major Military Construction | Georgia | United States | 65395 | Company Support Facility |  |  |  | 2011-12-27 | 2013-06-19 | 2014-07-31 | 99% | 2014-05-30
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Kentucky | United States | 66597 | Landgraf Hangar Extension |  |  |  | 2014-04-29 | 2015-10-21 | 2015-11-06 | 99% | 2015-11-06
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | Kentucky | United States | 66598 | Rotary Wing Hangar |  |  |  | 2012-04-16 | 2014-02-15 | 2015-02-15 | 99% | 2015-05-05
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 68526 | SOF Engineer Training Facility |  |  |  | 2015-05-27 | 2016-11-17 | 2017-01-21 | 74%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Washington | United States | 69257 | SOF Military Working Dog Kennel |  |  |  | 2015-05-04 | 2016-09-15 | 2016-12-23 | 95%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69287a | Battalion Operations Complex |  |  |  | 2013-10-09 | 2015-05-13 | 2015-10-30 | 99%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69287b | Battalion Operations Complex |  |  |  | 2014-11-20 | 2016-12-02 | 2016-12-15 | 97%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69382 | Civil Affairs Battalion Complex |  |  |  | 2013-10-16 | 2015-08-14 | 2015-09-21 | 100% | 2015-11-04
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Washington | United States | 69445 | SOF Battalion Operations Facility |  |  |  | 2015-06-30 | 2017-05-25 | 2017-06-08 | 56%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | Colorado | United States | 69446 | Group Support Battalion |  |  |  | 2014-08-27 | 2016-02-08 | 2016-06-09 | 99%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Kentucky | United States | 69447 | Group Support Battalion Detachment |  |  |  | 2014-04-14 | 2016-02-13 | 2016-02-15 | 100% | 2016-02-15
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69458 | Battalion Operations Complex |  | 1738000 | 69445 | 2012-12-10 | 2014-06-03 | 2015-01-03 | 99% | 2015-01-03
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69493 | Sustainment Bde Headquarters |  |  |  | 2014-06-18 | 2016-07-18 | 2016-08-16 | 99%
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69758 | Brigade Headquarters |  |  |  | 2012-11-14 | 2014-05-08 | 2014-10-11 | 97%
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 71224 | Group Headquarters |  | 2896000 | 68526 | 2012-11-07 | 2014-05-01 | 2015-02-06 | 99% | 2015-04-27
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 76364 | Battalion Operations Facility |  | 5000000 | 69445 | 2012-12-04 | 2014-08-26 | 2015-04-17 | 100%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | Kentucky | United States | 76365 | Group Special Troops Battalion |  |  |  | 2015-12-02 | 2017-10-02 | 2017-11-07 | 50%
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76366 | Company Operations Facility (GSTB) |  |  |  | 2012-09-12 | 2015-09-12 | 2016-03-02 | 100% | 2016-03-02
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Colorado | United States | 76367 | SOF Battalion Operations Complex |  |  |  | 2014-09-04 | 2016-07-20 | 2017-04-15 | 70%
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76371 | Company Operations Facility (GSB) |  |  |  | 2012-09-12 | 2015-09-12 | 2016-03-02 | 100% | 2016-03-02
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76375 | Civil Affairs Battalion Annexes |  |  |  | 2014-12-01 | 2016-07-23 | 2016-08-15 | 60%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76376 | Language and Cultural Center |  |  |  | 2015-01-09 | 2017-06-27 | 2017-10-20 | 65%
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 76518 | SOF Indoor Range |  |  |  | 2016-05-17 | 2016-05-17 | 2017-05-17 | 20%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction |  | Japan | 78024 | Facility Augmentation |  |  |  | 2015-07-01 | 2017-12-12 | 2017-12-12 | 33%
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79437 | SOF Training Command Building |  |  |  | 2016-10-28 | 2018-10-18 | 2018-10-18 | 1%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 79438 | Combat Medic Skills Sustainment Course Bldg |  |  |  | 2014-10-27 | 2016-04-19 | 2016-10-07 | 99%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | 79440 | SOF BOAT DOCKS |  |  |  | 2015-05-14 | 2016-08-22 | 2016-11-11 | 43% | 2017-12-22
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79456 | SOF Tactical Equipment Maintenance Facility (TEMF) |  |  |  | 2015-05-21 | 2017-09-27 | 2016-11-11 | 95%
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 80773 | SOF Battalion Operations Facility |  |  |  | 2017-01-31 | 2019-01-31 | 2019-01-31 | 0%
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | Kentucky | United States | 81897 | Company Operations Headquarters |  |  |  | 2017-01-03 | 2018-08-26 | 2018-08-26 | 0%
2017-02-15 | 2011 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 7132000 | 66362 | 2012-09-06 | 2013-07-17 | 2014-06-03 | 100% | 2014-06-03
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | Florida | United States | FTEV073010 | SOF Fuel Cell Maintenance Facility |  |  |  | 2016-09-15 | 2018-09-15 | 2018-09-15 | 1%
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | FTEV083002 | Add/Alter Operations Facility |  |  |  | 2014-09-02 | 2016-05-24 | 2016-10-20 | 2%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | FTFA113004 | SOF AvFID Ops and MX Facilities |  |  |  | 2013-11-05 | 2016-12-25 | 2017-04-06 | 82%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | NVZR083702 | Joint Special Operations University Facility |  |  |  | 2013-11-04 | 2015-06-28 | 2016-09-30 | 100% | 2016-09-30
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | Florida | United States | NVZR143703 | SOF Operations Support Facility |  |  |  | 2016-10-18 | 2019-01-26 | 2019-01-26 | 1%
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | California | United States | P-1049 | Range 130 Support Projects |  |  |  | 2013-06-03 | 2014-11-13 | 2016-03-06 | 2%
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-1119 | SOF COMMUNICATION / ELECTRONICS MAINTENANCE FACILITY |  |  |  | 2015-10-13 | 2016-04-06 | 2017-04-06 | 76% | 2017-04-06
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | California | United States | P-1126 | SOF COMBAT SERVICE SUPPORT FACILITY |  |  |  | 2016-08-22 | 2018-02-14 | 2018-02-14 | 3% | 2018-02-14
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1218 | SOF MARINE BATTALION COMPANY/TEAM FACILITIES |  |  |  | 2013-10-03 | 2016-01-18 | 2016-12-02 | 93% | 2017-02-01
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1391 | SOF SUSTAINMENT TRAINING COMPLEX |  |  |  | 2014-09-11 | 2016-09-02 | 2017-02-25 | 99% | 2017-02-25
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1393 | SOF SURVIVAL EVASION RESISTANCE ESCAPE TRAINING FACILITY |  |  |  | 2013-10-03 | 2016-01-18 | 2016-12-02 | 94% | 2017-02-01
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1396 | SOF INTEL OPS EXPANSION |  |  |  | 2015-08-31 | 2017-03-09 | 2017-04-15 | 47% | 2017-04-06
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P-157 | SOF HUMAN PERFORMANCE CENTER |  |  |  | 2016-03-11 | 2017-09-03 | 2017-09-03 | 12% | 2018-01-05
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-164 | Logistics Support Facility |  |  |  | 2012-12-09 | 2014-07-24 | 2015-06-16 | 97%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Virginia | United States | P-165 | CS/CSS Support Facility |  |  |  | 2014-10-06 | 2015-09-09 | 2015-11-26 | 98%
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | P-166 | QDR SOF MOBILE COMMUNICATIONS DET SUPPORT FACILITY |  |  |  | 2015-10-05 | 2017-07-17 | 2017-08-31 | 22% | 2017-07-17
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | Mississippi | United States | P-170 | SOF NAVSCIATTS APPLIED INSTRUCTION FACILITY |  |  |  | 2016-02-09 | 2017-10-17 | 2017-11-28 | 18% | 2017-10-17
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | P-183 | SOF INDOOR DYNAMIC RANGE |  |  |  | 2014-05-01 | 2017-07-24 | 2017-07-24 | 28% | 2018-01-04
2017-02-15 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P-334 | SOF LOGSU TWO OPERATIONS FACILITY |  |  |  | 2016-02-24 | 2018-07-29 | 2018-07-29 | 15% | 2018-07-29
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | Nevada | United States | P-418 | SOF TACTICAL GROUND MOBILITY VEHICLE MAINTENANCE FACILITY |  |  |  | 2015-09-01 | 2017-02-23 | 2017-04-06 | 40% | 2017-06-07
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-473 | SEAL Team Operations Facility |  |  |  | 2014-08-13 | 2015-12-27 | 2015-12-27 | 68%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | Hawaii | United States | P-475 | SOF-SDVT-1 WATERFRONT OPERATIONS FACILITY |  |  |  | 2016-02-08 | 2018-02-13 | 2018-04-03 | 8% | 2018-04-03
2017-02-15 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P-576 | SOF KNOWN DISTANCE RANGE TOWER |  |  |  | 2016-07-29 | 2016-08-14 | 2017-08-14 | 10% | 2017-08-14
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-769 | Building Renovation |  |  |  | 2013-01-02 | 2014-06-27 | 2015-02-20 | 99% | 2015-02-20
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-776 | SOF LOGSU ONE OPERATIONS FACILITY #1 |  |  |  | 2015-10-14 | 2017-10-23 | 2017-10-23 | 14% | 2018-05-07
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | California | United States | P-797 | SOF SUPPORT ACTIVITY OPERATIONS FACILITY |  |  |  | 2015-10-14 | 2018-04-02 | 2018-04-02 | 15% | 2018-04-02
2017-02-15 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-826 | Military Working Dog Facility |  |  |  | 2012-12-09 | 2014-07-24 | 2015-06-16 | 97%
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-876 | SOF INDOOR DYNAMIC SHOOTING FACILITY |  |  |  | 2014-10-10 | 2016-10-07 | 2016-10-07 | 99% | 2017-03-24
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-888 | SOF CLOSE QUARTERS COMBAT AND DYNAMIC SHOOTING FACILITY (LA POSTA) |  |  |  | 2014-10-14 | 2016-09-29 | 2016-12-20 | 15% | 2017-12-29
2017-02-15 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-893 | SOF SUPPORT ACTIVITY OPERATIONS FACILITY #2 |  |  |  | 2015-10-14 | 2018-04-02 | 2018-04-02 | 13% | 2018-04-02
2017-02-15 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-915 | SOF MOBILE COMMUNICATIONS DETACHMENT SUPPORT FACILITY |  |  |  | 2015-09-24 | 2017-03-18 | 2017-03-18 | 30% | 2017-07-28
2017-02-15 | 2016 | Special Operations Command | Major Military Construction | California | United States | P-920 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #2 |  |  |  | 2016-10-04 | 2018-10-13 | 2018-10-13 | 1% | 2018-10-13
2017-01-19 | 2010 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80001 | Pentagon Electrical Upgrade |  |  |  | 2013-11-07 | 2015-02-05 | 2016-12-31 | 48% | 2016-12-31
2017-01-19 | 2011 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80002 | Power Plant Modernization Phase 3 (WPP) |  | 4331051 | Budget Sequester: $4,001,00 Reprogramming: $330,051 to project 80003 | 2013-04-22 | 2016-05-11 | 2017-12-14 | 56% | 2017-12-14
2017-01-19 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80003 | Metro Entrance Facility/Visitor Screening Facility |  |  |  | 2013-11-01 | 2015-05-03 | 2016-08-30 | 99% | 2016-04-01
2017-01-19 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80004 | Secure Access Lane (SAL) |  |  |  | 2016-10-25 | 2018-05-18 | 2018-05-18 | 13% | 2018-05-18
2016-12-15 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80005 | Pentagon Heliport Control Tower/Fire Station |  | 798000 | Budget Sequester
2016-12-15 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80006 | Pentagon Memorial Pedestrian Plaza |  | 2285000 | $176,000 Budget Sequester $409,000 to 80003 $1.7M to 80004
2017-01-19 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80007 | PFPA Support Operations Center
2017-01-19 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80008 | Boundary Channel Access Control Point |  |  |  | 2016-06-01 | 2017-12-01 | 2017-12-01 | 0%
2017-01-19 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80009 | Raven Rock Admin Facility Upgrade |  | 500000 | Reprogramming: $500,000 to project 80002
2017-01-19 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80010 | Raven Rock Exterior Cooling Towers |  | 3929000 | Reprogramming: to project 80001
2017-01-19 | 2015 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80011 | Redundant Chilled Water Loop

## CONTRACTS
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Prime Contract Number | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date
2016-11-15 | 2014 | Air Force Active | ACC123183 |  | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143462 | 7200020 | 2016-02-20 | 2016-04-11
2017-02-15 | 2014 | Air Force Active | AETC176870 |  | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265367 | 3306340 | 2015-06-09 | 2015-06-09
2017-02-15 | 2016 | Air Force Active | AFAF140005 |  | 2016-02-11 | 2016-03-01 | RED HORSE | REDHORSE1640005 | 24606000 | 24606000 | 2017-12-21 | 2017-12-21
2017-02-15 | 2016 | Air Force Active | AFAF140005 |  | 2016-05-18 | 2016-06-17 | AFCAP - FLUOR | FA805115D00020003 | 2922353 | 2922353 | 2018-01-16 | 2018-01-16
2017-02-15 | 2016 | Air Force Active | AFAF140005 |  | 2016-02-29 | 2016-03-30 | LOGCAP - FLUOR | W52P1J07D00080013 | 9071647 | 9071647 | 2016-10-12 | 2016-10-12
2016-11-15 | 2012 | Air Force Active | AGGN123002P |  | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619171 | 1662571 | 2014-12-19 | 2014-12-19
2016-11-15 | 2014 | Air Force Active | AGGN143001 |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164308 | 1178891 | 2015-12-24 | 2016-01-01
2016-11-15 | 2014 | Air Force Active | AGGN143002 |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111892 | 7219701 | 2015-12-24 | 2016-01-12
2016-11-15 | 2014 | Air Force Active | AGGN143003 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645200 | 5645200 | 2015-10-12 | 2015-10-12
2016-11-15 | 2014 | Air Force Active | AGGN143004 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000000 | 11112754 | 2015-10-12 | 2015-11-14
2017-02-15 | 2016 | Air Force Active | AGGN143005A |  | 2015-09-18 | 2016-03-24 | The Ross Group Construct Org | W912BV16C0016 | 9290840 | 9290840 | 2017-07-17 | 2017-07-16
2017-02-15 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 89918305 | 92040285 | 2017-04-16 | 2017-11-21
2017-02-15 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 96616619 | 100631064 | 2017-03-08 | 2018-01-15
2017-02-15 | 2015 | Air Force Active | AJJY133028 |  | 2016-06-01 | 2016-09-30 | Pernix Guam, LLC | N6274216C1309 | 26463336 | 26463336 | 2018-10-20 | 2018-09-20
2017-02-15 | 2016 | Air Force Active | AJJY143030 |  | 2016-06-03 | 2016-09-02 | Reliable Builders, Inc. | N4019216D2704 | 5790000 | 5790000 | 2018-03-26 | 2018-02-24
2017-02-15 | 2014 | Air Force Active | AJJY143760 |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907700 | 17907700 | 2016-05-12 | 2018-04-10
2017-02-15 | 2014 | Air Force Active | AJJY143760 |  | 2014-12-23 | 2015-01-22 | Environet Inc. | N4019210D00040012 | 101676 | 101676 | 2015-03-10 | 2015-03-10
2016-11-15 | 2014 | Air Force Active | AJJY153011 |  | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177269 | 6168044 | 2016-08-17 | 2016-08-17
2016-11-15 | 2010 | Air Force Active | AJXF063009 |  | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464830 | 10464830 | 2013-05-13 | 2013-05-25
2017-02-15 | 2014 | Air Force Active | AJXF103010 |  | 2014-08-15 | 2014-12-30 | The Haskell Company | N4008010D04910002 | 21754670 | 22161611 | 2017-04-05 | 2017-04-05
2016-11-15 | 2013 | Air Force Active | AJXF106000 |  | 2014-08-07 | 2015-03-04 | Heard Contracting | W912DR15C0010 | 2132837 | 2151817 | 2016-04-08 | 2016-04-08
2017-02-15 | 2011 | Air Force Active | ALUA073006B |  | 2016-02-15 | 2016-03-16 | Federal Contracting, Inc. | W912ER16C0002 | 5668000 | 5735247 | 2017-03-26 | 2017-03-26
2017-02-15 | 2011 | Air Force Active | ALUA073006B |  | 2015-08-18 | 2015-09-17 | American International Contractors, Inc. | W912ER15C0008 | 9848000 | 9964674 | 2017-04-09 | 2017-04-09
2017-02-15 | 2011 | Air Force Active | ALUA073006B |  | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177236 | 34717491 | 2014-05-15 | 2015-03-06
2016-11-15 | 2008 | Air Force Active | ALUA073008A |  | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244838 | 31385349 | 2012-08-22 | 2015-10-15
2016-11-15 | 2010 | Air Force Active | ALUA107000 |  | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272835 | 48548502 | 2014-04-06 | 2016-06-28
2017-02-15 | 2011 | Air Force Active | ALUA110032 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730623 | 1735160 | 2014-12-06 | 2018-08-14
2017-02-15 | 2011 | Air Force Active | ALUA113001 |  | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912567 | 11564308 | 2014-04-02 | 2016-12-27
2017-02-15 | 2011 | Air Force Active | ALUA113002 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557438 | 1562649 | 2014-12-06 | 2018-08-14
2017-02-15 | 2011 | Air Force Active | ALUA113005 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572399 | 1572399 | 2014-12-06 | 2018-08-14
2017-02-15 | 2011 | Air Force Active | ALUA113006 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573056 | 1594559 | 2014-12-06 | 2018-08-14
2017-02-15 | 2011 | Air Force Active | ALUA113009 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615612 | 615612 | 2014-12-06 | 2018-08-14
2017-02-15 | 2011 | Air Force Active | ALUA113010 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216400 | 1222633 | 2014-12-06 | 2018-08-14
2017-02-15 | 2011 | Air Force Active | ALUA113012 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615533 | 1615533 | 2014-12-06 | 2018-08-14
2017-02-15 | 2012 | Air Force Active | ALUA113026 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511518 | 1511518 | 2014-12-06 | 2018-08-14
2016-11-15 | 2012 | Air Force Active | ALUA113027 |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265194 | 1278425 | 2014-11-06 | 2015-11-27
2016-11-15 | 2012 | Air Force Active | ALUA113032 |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403744 | 1473063 | 2015-02-19 | 2015-11-27
2016-11-15 | 2012 | Air Force Active | ALUA113034 |  | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214606 | 1160276 | 2015-02-19 | 2015-11-27
2017-02-15 | 2016 | Air Force Active | AMAB120001 |  | 2015-10-02 | 2016-06-15 | American International Contractors Inc. | W192ER11D00010008 | 24448000 | 24448000 | 2018-06-05 | 2018-05-13
2016-11-15 | 2011 | Air Force Active | ASHE083011 |  | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N3319107D02110002 | 7174169 | 8608122 | 2013-09-05 | 2015-03-15
2017-02-15 | 2013 | Air Force Active | ASHE103001 |  | 2014-03-06 | 2015-02-26 | Coop Muratori & Cementisti CMC Di Ravenn | N6247015C5005 | 1780234 | 1780234 | 2016-12-02 | 2016-12-06
2017-02-15 | 2012 | Air Force Active | AWUB105002 |  | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998000 | 18717502 | 2013-11-24 | 2014-03-16
2017-02-15 | 2013 | Air Force Active | BAEY133001 |  | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947269 | 16363873 | 2016-03-30 | 2016-09-09
2017-02-15 | 2014 | Air Force Active | BAEY143000 |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699643 | 54701186 | 2016-11-04 | 2016-12-04
2017-02-15 | 2015 | Air Force Active | CADJ140004 |  | 2015-08-30 | 2015-09-29 | AICI, Burlingame, CA | N3319113D0839 | 6960000 | 6960000 | 2017-02-02 | 2017-05-12
2016-11-15 | 2014 | Air Force Active | CZQZ013004 |  | 2015-01-29 | 2015-05-18 | Speegle Construction Inc. | W912PP15C0006 | 5102200 | 5155066 | 2016-06-10 | 2016-07-07
2016-11-15 | 2014 | Air Force Active | CZQZ073023A |  | 2014-08-04 | 2014-12-05 | Speegle Construction Inc. | W912PP15C0001 | 7001000 | 7127038 | 2016-11-19 | 2016-11-24
2017-02-15 | 2014 | Air Force Active | CZQZ073050 |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19716709 | 19812313 | 2016-08-21 | 2016-08-21
2017-02-15 | 2016 | Air Force Active | DBEH063000 |  | 2016-02-23 | 2016-07-29 | SAUER | W9127812D0039 | 18658000 | 18658000 | 2018-06-29 | 2018-06-30
2016-11-15 | 2010 | Air Force Active | DHAF100031 |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671642 | 1995737 | 2012-02-28 | 2016-03-01
2016-11-15 | 2010 | Air Force Active | DHAF100120 |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136701 | 1188828 | 2012-02-28 | 2016-03-01
2017-02-15 | 2011 | Air Force Active | DHAF120037 |  | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhabi UAE) | W912BU13C0060 | 1514583 | 1639782 | 2015-01-20 | 2017-03-15
2016-11-15 | 2011 | Air Force Active | DHAF120057 |  | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120380 | 1192114 | 2014-11-24 | 2016-05-24
2017-02-15 | 2011 | Air Force Active | DHAF124001 |  | 2014-05-21 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1176823 | 1159452 | 2015-09-13 | 2017-05-12
2016-11-15 | 2011 | Air Force Active | FBNV063501 |  | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282136 | 23526207 | 2013-08-27 | 2016-01-15
2017-02-15 | 2011 | Air Force Active | FBNV113002 |  | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223000 | 7534524 | 2013-05-02 | 2013-09-13
2017-02-15 | 2016 | Air Force Active | FBNV113005 |  | 2016-06-08 | 2016-09-14 | Creative Times, Inc. | W912PL16C0025 | 9300000 | 9300000 | 2017-11-18 | 2017-11-18
2016-11-15 | 2012 | Air Force Active | FBNV133500 |  | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D01100001 | 1795000 | 1867865 | 2015-06-08 | 2016-03-06
2017-02-15 | 2010 | Air Force Active | FJXT033003 |  | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248940 | 11773483 | 2013-10-12 | 2014-10-21
2016-11-15 | 2014 | Air Force Active | FTFA073007 |  | 2014-07-24 | 2014-12-30 | Southeast Cherokee Constructio | W9127810D00780008 | 1457737 | 1457737 | 2016-02-05 | 2016-02-05
2016-11-15 | 2013 | Air Force Active | FTFA123000 |  | 2014-07-28 | 2014-10-30 | Barlovento LLC | W9127810D00720015 | 1756830 | 1756830 | 2015-12-05 | 2015-12-05
2017-02-15 | 2012 | Air Force Active | FTQW083005 |  | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061944 | 34791725 | 2016-08-15 | 2016-12-16
2017-02-15 | 2010 | Air Force Active | FTQW083007 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981132 | 36819520 | 2015-01-27 | 2016-12-22
2017-02-15 | 2011 | Air Force Active | FTQW083008 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981132 | 30891694 | 2015-01-27 | 2016-12-22
2017-02-15 | 2016 | Air Force Active | FTQW163011 |  | 2016-06-22 | 2016-12-08 | Watterson Construction Company | W911KB17C0004 | 19754000 | 19754000 | 2018-09-19 | 2018-09-19
2017-02-15 | 2016 | Air Force Active | FXBM063002 |  | 2016-09-08 | 2016-12-19 | Dean Kurtz Construction | W9128F17C0008 | 20456953 | 20456953 | 2019-01-18 | 2019-01-18
2016-11-15 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805300 | 57337337 | 2014-06-19 | 2015-04-19
2016-11-15 | 2012 | Air Force Active | FXSB061561 |  | 2012-05-13 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230292 | 3230292 | 2013-10-27 | 2014-08-11
2016-11-15 | 2012 | Air Force Active | FXSB061561 |  | 2012-05-20 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978807 | 4654908 | 2013-09-27 | 2014-08-12
2016-11-15 | 2012 | Air Force Active | FXSB061561 |  | 2012-06-27 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799228 | 1799228 | 2013-02-22 | 2013-02-22
2016-11-15 | 2012 | Air Force Active | FXSB061561 |  | 2012-05-23 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874106 | 2191910 | 2012-12-20 | 2012-12-20
2017-02-15 | 2013 | Air Force Active | GJKZ130025 |  | 2014-08-01 | 2014-12-31 | Ahtna Engineering | FA462013DB0040003 | 1698195 | 1742635 | 2015-12-17 | 2015-12-17
2017-02-15 | 2012 | Air Force Active | HACC123204 |  | 2015-01-13 | 2015-08-21 | JV SKE Italy 2012 | N3319115C0802 | 9793080 | 7723700 | 2017-02-21 | 2017-02-21
2017-02-15 | 2015 | Air Force Active | HEKP103001 |  | 2016-03-02 | 2016-04-01 | RANCO Construction Inc | W912DS16C0009 | 5218000 | 5218000 | 2017-10-28 | 2017-10-28
2017-02-15 | 2014 | Air Force Active | KNMD142222 |  | 2015-10-06 | 2015-11-05 | Jacobsen Construction Company, Inc | N6247816C1506 | 2699000 | 2699000 | 2016-10-15 | 2016-10-15
2017-02-15 | 2014 | Air Force Active | KRSM003009 |  | 2014-05-06 | 2015-03-27 | Northern Construction LLC | W9123815C0001 | 12777054 | 13644931 | 2017-04-27 | 2017-10-18
2016-12-07 | 2013 | Air Force Active | KRSM103012 |  | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781000 | 9758075 | 2015-07-21 | 2016-06-19
2016-12-07 | 2013 | Air Force Active | KRSM103012 |  | 2015-07-28 | 2015-08-27 | BRINKERHOFF EXCAVATING AND CONSTRUCTION, | FA820112D0013 | 536389 | 536389 | 2016-01-04 | 2016-01-04
2017-02-15 | 2016 | Air Force Active | KRSM103013 |  | 2016-04-05 | 2016-09-02 | Mountain West Construction Group | W9123816C0023 | 19453853 | 19453853 | 2018-10-02 | 2018-10-07
2017-02-15 | 2016 | Air Force Active | KRSM133002 |  | 2016-02-11 | 2016-08-02 | KW-HHI JV | W9123816C0015 | 8099863 | 8099863 | 2018-09-01 | 2018-09-13
2017-02-15 | 2016 | Air Force Active | KRSM153001 |  | 2016-03-10 | 2016-08-25 | Provo Wasatch JV, LLC | W9123815D00110001 | 5671521 | 5671521 | 2017-12-18 | 2017-12-17
2016-11-15 | 2012 | Air Force Active | KWRD013003 |  | 2012-05-18 | 2012-08-17 | Turner Atlantic Construction | W912PP12C0026 | 9843654 | 10288429 | 2014-05-17 | 2014-11-24
2017-02-15 | 2016 | Air Force Active | KWRD133001 |  | 2016-06-14 | 2016-09-13 | LC Structural, Inc. | W912PP16C0009 | 2509194 | 2509194 | 2017-07-20 | 2017-07-20
2016-11-15 | 2008 | Air Force Active | LJYC084001 |  | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970022 | 42315654 | 2012-10-19 | 2016-09-30
2017-02-15 | 2014 | Air Force Active | LJYC106001 |  | 2015-06-02 | 2015-09-30 | KIRNAK Ins.San. Ve Tic. Ltd. | FA568515C0009 | 1530537 | 1530537 | 2016-09-28 | 2016-09-28
2016-11-15 | 2014 | Air Force Active | LKTC073101 |  | 2014-07-18 | 2014-09-02 | Indian Springs Holdings,LLC | DACA099140900 | 11450000 | 11450000 | 2014-12-01 | 2014-12-01
2016-11-15 | 2014 | Air Force Active | LKTC073101 |  | 2015-07-15 | 2015-08-14 | Penick-Nordic JV | W912PL10D00720003 | 3100312 | 3586905 | 2016-05-10 | 2016-07-14
2016-11-15 | 2013 | Air Force Active | LKTC133101 |  | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643420 | 10801343 | 2015-08-19 | 2015-10-24
2016-11-15 | 2011 | Air Force Active | LXEZ114127 |  | 2012-02-18 | 2012-03-19 | OTIE Milwauke, WI; *Title 2 Contract support* | FA890308D87820014 | 1896559 | 1896559 | 2012-04-18 | 2012-04-18
2016-11-15 | 2011 | Air Force Active | LXEZ114127 |  | 2014-05-12 | 2014-06-11 | OSC Solutions, Inc. (West Palm Beach, FL) **Appliances** | FA527014P0055 | 401356 | 401356 | 2014-07-11 | 2014-07-11
2016-11-15 | 2011 | Air Force Active | LXEZ114127 |  | 2012-08-13 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) ** Appliances** | FA527012FA045 | 319431 | 319431 | 2012-10-12 | 2012-10-12
2016-11-15 | 2011 | Air Force Active | LXEZ114127 |  | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621760 | 67931188 | 2015-11-08 | 2015-12-03
2016-11-15 | 2011 | Air Force Active | LXEZ114127 |  | 2012-06-01 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan)*Arch TestDigs* | FA527012P0058 | 50185 | 50185 | 2012-07-31 | 2012-07-31
2016-11-15 | 2011 | Air Force Active | LXEZ114127 |  | 2012-07-01 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT" | FA527012P0080 | 72005 | 72005 | 2012-08-30 | 2012-08-30
2016-11-15 | 2012 | Air Force Active | LXEZ124285 |  | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706668 | 17706668 | 2016-05-10 | 2016-05-10
2016-11-15 | 2013 | Air Force Active | LXEZ134286 |  | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698072 | 15307318 | 2015-11-27 | 2016-04-29
2016-11-15 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202135 | 4367984 | 2014-07-23 | 2015-01-01
2016-11-15 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288680 | 6392439 | 2015-12-15 | 2016-08-08
2016-11-15 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473449 | 2543417 | 2014-07-23 | 2014-09-30
2017-02-15 | 2014 | Air Force Active | MHMV103105B |  | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285500 | 21740961 | 2016-11-01 | 2016-11-28
2017-02-15 | 2013 | Air Force Active | MPLS083008 |  | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170185 | 17241355 | 2015-06-12 | 2015-07-07
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-09-19 | 2012-10-19 | SB FPI, LLC/JSR Inc-Refencing | W9126G11C0009 | 175358 | 175358 | 2012-11-18 | 2012-11-18
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2014-10-11 | 2014-11-10 | AE Merrick & Company-Tittle 2 Svs $59,036x3 | W9126G08D00060053 | 177108 | 177108 | 2014-12-10 | 2014-12-10
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2011-10-09 | 2011-11-08 | LB Koonz Brown & Root (DCF2 Ktr)-Free Zone Fence | W9126G11C0027 | 95464 | 95464 | 2011-12-08 | 2011-12-08
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2014-05-26 | 2014-06-25 | SVS-Am Eagle Protective Svs Corp-Gate Monitor, OY2 | W9126G12C0017P0002 | 100466 | 100466 | 2014-07-25 | 2014-07-25
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2014-09-10 | 2014-10-10 | SB Red Cedar Enterprises Inc-Quadrangle Main 3/4 | W9126G14D00190007 | 3102034 | 3102034 | 2014-11-09 | 2014-11-09
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-07-10 | 2012-08-09 | SB JSR Inc-Exterior Facilties & Grounds | W912BV11C0038 | 6886921 | 7284529 | 2014-01-21 | 2014-01-21
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2013-05-04 | 2013-06-03 | SB FPI, LLC/JSR Inc-DCF2s Gary Rd portion 2/3 | W9126G13C0098 | 91850 | 91850 | 2013-07-03 | 2013-07-03
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-04-29 | 2012-05-29 | AE RabaKistner Consultants-Sidewalk Survey $1865.12 | PNASA1205700 | 1889 | 1889 | 2012-06-28 | 2012-06-28
2016-11-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2010-12-06 | 2011-09-20 | LB SutherfielfPontikes, LLC-Main Facility Construction | W9126G11C0024 | 45885000 | 46365642 | 2013-10-31 | 2014-02-25
2016-11-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2014-09-10 | 2014-10-10 | SB Red Cedar Enterprise Inc-Ext Facs/Kneewall/Quad | W9126G14D00190007 | 7301694 | 7301694 | 2016-01-13 | 2016-03-01
2016-11-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2013-06-17 | 2013-07-17 | LB-SpawGlass Contractors, Inc. | W9126G12C0023 | 50528593 | 52398956 | 2015-08-16 | 2016-07-16
2016-11-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2012-10-01 | 2012-10-31 | AE-Merrick&Company (E&D) | W9126G08D00060055 | 400152 | 400152 | 2013-01-29 | 2013-01-29
2016-11-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2011-12-16 | 2012-07-08 | SB FPI/JSR Inc/DCF2 Ktr - Gary Rd 3/3 | W9126G13C0098 | 91850 | 91850 | 2013-06-08 | 2013-06-08
2016-11-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2012-10-01 | 2012-10-31 | Merrick & Company (Tittle II Services) $59,036.40 | W9126G08D00060054 | 118073 | 118073 | 2012-11-30 | 2012-11-30
2016-11-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2011-03-07 | 2011-07-08 | LB-KBR General Contract | W9126G11C0027 | 25985137 | 27613959 | 2013-08-18 | 2014-10-28
2016-11-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2012-01-30 | 2012-02-29 | AEP Services Corp (Gate Monitor Svs 100K x 2 yrs | W9126G12C00170001 | 202008 | 202008 | 2012-03-30 | 2012-03-30
2016-11-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2012-06-08 | 2012-07-08 | SB JSR Inc (Gary Rd Realign Pt 2of3) | W9126G13C0098 | 152927 | 155310 | 2012-08-07 | 2012-08-07
2016-11-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2015-03-25 | 2015-04-24 | SB Gideon Contracting | W9126G14D00570019 | 54574 | 54574 | 2015-10-09 | 2015-10-09
2016-11-15 | 2010 | Air Force Active | MUHJ053008 |  | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185824 | 8498082 | 2012-01-26 | 2013-07-19
2016-11-15 | 2010 | Air Force Active | MUHJ053008 |  | 2014-08-30 | 2014-09-29 | Homeland Contracting Corporation | F4A0012D00040013 | 231490 | 231490 | 2015-08-25 | 2015-08-25
2017-02-15 | 2015 | Air Force Active | MXRD083002 |  | 2015-06-04 | 2016-08-08 | BBIX, LLC | W912WJ16C0011 | 12595000 | 12595000 | 2018-09-07 | 2018-09-07
2016-11-15 | 2013 | Air Force Active | NKAK103006 |  | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869000 | 21631199 | 2015-07-23 | 2015-12-19
2016-11-15 | 2013 | Air Force Active | NKAK113005 |  | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218502 | 4595603 | 2015-10-21 | 2016-04-08
2016-11-15 | 2014 | Air Force Active | NUEX093007 |  | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699907 | 4716796 | 2015-07-07 | 2016-03-20
2016-11-15 | 2014 | Air Force Active | NUEX093011 |  | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513636 | 15807972 | 2016-02-14 | 2016-04-21
2017-02-15 | 2015 | Air Force Active | NUEX103005 |  | 2014-12-16 | 2015-04-30 | SAI-TALON JV | W912PL15C0005 | 13097800 | 13095777 | 2016-11-22 | 2016-11-22
2017-02-15 | 2016 | Air Force Active | NUEX113001 |  | 2016-09-10 | 2016-12-15 | Marsh Development, Inc. | W912PL16D0009 | 1307252 | 1307252 | 2017-10-11 | 2017-10-11
2017-02-15 | 2015 | Air Force Active | NUEX123001 |  | 2015-02-06 | 2015-08-19 | KORTE Construction Company | W912PL15C0015 | 10318700 | 10318700 | 2017-05-16 | 2017-05-16
2017-02-15 | 2016 | Air Force Active | NUEX123004 |  | 2016-01-05 | 2016-08-25 | Okland Construction Company, Inc | W912PL16C0015 | 23915372 | 23915372 | 2018-05-17 | 2018-04-30
2017-02-15 | 2016 | Air Force Active | NUEX123005 |  | 2016-02-15 | 2016-06-30 | OKLAND CONSTRUCTION COMPANY | W912PL16C0013 | 10687842 | 10687842 | 2018-03-22 | 2018-03-27
2017-02-15 | 2014 | Air Force Active | PAYZ130011 |  | 2015-03-11 | 2015-04-10 | Clark Construction Group, LLC | W912DR15C0008 | 20623200 | 20623200 | 2017-08-25 | 2017-08-25
2017-02-15 | 2014 | Air Force Active | PAYZ130011 |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 57000000 | 57000000 | 2016-04-13 | 2016-04-13
2017-02-15 | 2015 | Air Force Active | PAYZ15001A |  | 2016-10-22 | 2016-11-21 | Bauschmidt OU | W912GB15D00310005 | 2834042 | 2834042 | 2018-06-14 | 2018-06-14
2017-02-15 | 2015 | Air Force Active | PAYZ15001A |  | 2016-10-10 | 2016-11-09 | Astlanda Ehitus OU | W912GB15D00290002 | 3205839 | 3205839 | 2018-06-02 | 2018-06-02
2017-02-15 | 2015 | Air Force Active | PAYZ15001A |  | 2016-06-07 | 2016-11-04 | SKE | W912GB15D00360003 | 5926719 | 5926719 | 2018-05-28 | 2018-05-28
2017-02-15 | 2015 | Air Force Active | PAYZ15001B |  | 2016-10-30 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00500002 | 7097718 | 7097718 | 2018-06-22 | 2018-06-22
2017-02-15 | 2015 | Air Force Active | PAYZ15001B |  | 2016-06-18 | 2016-11-21 | Vilmanto Statybos | W912GB15D00560002 | 1515821 | 1515821 | 2018-06-05 | 2018-06-05
2017-02-15 | 2015 | Air Force Active | PAYZ15001C |  | 2016-06-10 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00410003 | 4479631 | 4479631 | 2018-06-05 | 2018-06-05
2017-02-15 | 2015 | Air Force Active | PAYZ15001C |  | 2016-06-10 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00410002 | 1221288 | 1221288 | 2018-06-05 | 2018-06-05
2017-02-15 | 2015 | Air Force Active | PAYZ15001D |  | 2016-07-15 | 2016-11-05 | Ahntech-Badzak Bulgaria JV | W912GB16D00400003 | 1528908 | 1528908 | 2018-04-29 | 2018-04-29
2017-02-15 | 2015 | Air Force Active | PAYZ15001E |  | 2016-07-15 | 2016-10-20 | SKE SRL | W912GB13D00380006 | 2923496 | 2923496 | 2018-06-27 | 2018-06-27
2017-02-15 | 2015 | Air Force Active | PDPG130118 |  | 2015-10-21 | 2016-01-12 | MTM Builders & Erickson-Hall | N6247311D00210044 | 1788249 | 1841682 | 2017-01-11 | 2017-01-11
2017-02-15 | 2014 | Air Force Active | PRQE145117 |  | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924500 | 65048402 | 2016-01-05 | 2016-04-19
2017-02-15 | 2015 | Air Force Active | PRQE145118 |  | 2015-01-26 | 2015-04-03 | Hanke Constructors | W912DQ14D40030001 | 6389509 | 6397810 | 2016-05-04 | 2016-05-04
2016-11-15 | 2014 | Air Force Active | PRQE145121 |  | 2014-03-14 | 2015-03-02 | Aerostar SES, Inc | W912DQ15C4005 | 3061137 | 3120734 | 2016-04-19 | 2016-06-02
2016-11-15 | 2014 | Air Force Active | PRQE145136 |  | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100500 | 8268701 | 2015-12-17 | 2015-12-19
2017-02-15 | 2014 | Air Force Active | PRQE145138 |  | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976000 | 976000 | 2017-03-10 | 2017-03-10
2016-12-07 | 2014 | Air Force Active | PRQE145142 |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200000 | 26138166 | 2017-01-19 | 2017-02-18
2016-12-07 | 2015 | Air Force Active | PRQE155118 |  | 2015-01-12 | 2015-04-03 | Hanke Constructors | W912DQ14D40030001 | 2286153 | 2300381 | 2016-05-04 | 2016-05-04
2017-02-15 | 2014 | Air Force Active | PRQE155119 |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959000 | 54644437 | 2015-12-26 | 2016-01-25
2017-02-15 | 2015 | Air Force Active | PRQE155121 |  | 2016-02-29 | 2016-09-19 | Archer Western Aviation Partne | W912DQ16C40060072 | 4000000 | 4000000 | 2017-09-20 | 2017-09-20
2016-11-15 | 2014 | Air Force Active | PRQE155122 |  | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306162 | 7387873 | 2015-10-15 | 2015-11-17
2016-11-15 | 2015 | Air Force Active | PRQE155124 |  | 2014-11-13 | 2015-04-17 | K&K Industries, Inc | W912DQ14D40090002 | 5679326 | 5775143 | 2016-11-02 | 2016-11-16
2016-12-07 | 2016 | Air Force Active | PRQE165114 |  | 2016-01-07 | 2016-03-31 | LGC Global INC. | W912DQ16C4007 | 4368472 | 4429036 | 2016-12-26 | 2016-12-27
2017-02-15 | 2013 | Air Force Active | PTFL126001 |  | 2015-08-04 | 2015-09-03 | Ranco Construction, INC | W912DS15C0009 | 1383300 | 1429350 | 2016-06-29 | 2016-09-19
2017-02-15 | 2014 | Air Force Active | PXLY110459 |  | 2015-05-07 | 2016-02-04 | Barlovento L.L.C. | FA300208D0015 | 2490003 | 2490003 | 2017-03-05 | 2017-08-19
2017-02-15 | 2014 | Air Force Active | QJVF092009 |  | 2015-02-11 | 2016-01-28 | Fluor Federal Solutions | W9128F16C0011 | 17648238 | 17653265 | 2017-09-14 | 2017-09-28
2017-02-15 | 2014 | Air Force Active | QJVF092013 |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540270 | 9501991 | 2016-01-06 | 2016-07-17
2017-02-15 | 2014 | Air Force Active | QKKA133001P1 |  | 2015-04-10 | 2015-09-29 | Nishimatsu Construction Corp | FA520515C0005 | 21841808 | 21490923 | 2017-09-28 | 2017-09-28
2016-11-15 | 2013 | Air Force Active | QKKA134001 |  | 2016-06-28 | 2016-07-28 | Tanaka GUMI Tanaka Construction Konno | FA520513D0002 | 218303 | 218303 | 2017-06-03 | 2017-06-03
2016-11-15 | 2013 | Air Force Active | QKKA134001 |  | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336739 | 14948824 | 2015-09-23 | 2016-01-11
2017-02-15 | 2014 | Air Force Active | QKKA144002 |  | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302110 | 25302110 | 2017-01-14 | 2017-04-30
2017-02-15 | 2014 | Air Force Active | QKKA144002 |  | 2016-06-28 | 2016-07-28 | Tanaka GUMI Tanaka Construction Konno | FA520513D00025092 | 218303 | 218303 | 2017-06-03 | 2017-06-03
2016-11-15 | 2014 | Air Force Active | QSEU123003 |  | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547470 | 1547470 | 2015-11-19 | 2015-11-19
2017-02-15 | 2014 | Air Force Active | RKMF083002 |  | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381000 | 30657276 | 2016-09-28 | 2016-12-07
2016-11-15 | 2014 | Air Force Active | RKMF103005 |  | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D01130012 | 4829984 | 5023531 | 2016-02-18 | 2016-04-19
2016-11-15 | 2014 | Air Force Active | RKMF103006 |  | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974014 | 7183903 | 2016-01-06 | 2016-03-03
2016-11-15 | 2014 | Air Force Active | RKMF103009 |  | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066000 | 8447429 | 2015-12-16 | 2016-03-14
2016-11-15 | 2014 | Air Force Active | RKMF113005 |  | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922700 | 14950148 | 2016-08-01 | 2016-08-01
2017-02-15 | 2015 | Air Force Active | RKMF123007 |  | 2015-03-05 | 2015-07-21 | CTI, OGDEN, UT | W912PL15C0013 | 7733000 | 7828404 | 2017-05-03 | 2017-05-08
2017-02-15 | 2015 | Air Force Active | RKMF133001 |  | 2015-01-22 | 2015-06-12 | CTI | W912PL15C0010 | 11361000 | 11408859 | 2017-01-19 | 2017-03-20
2017-02-15 | 2015 | Air Force Active | RKMF143001 |  | 2015-03-26 | 2015-09-16 | Harper Construction Co. | W912PL15C0017 | 22397265 | 22397265 | 2017-09-11 | 2017-09-11
2016-11-15 | 2015 | Air Force Active | SAKW059006 |  | 2014-11-07 | 2015-03-07 | P&S Construction Inc | N4019210D28040025 | 2841600 | 2857284 | 2016-04-10 | 2016-07-08
2016-11-15 | 2014 | Air Force Active | SAKW113003 |  | 2014-01-23 | 2015-03-06 | P&S Construction Inc | N4019210D28040023 | 7050506 | 6944532 | 2016-07-08 | 2016-09-02
2016-11-15 | 2015 | Air Force Active | SAKW113008 |  | 2015-03-20 | 2015-06-30 | GSI-EA JV, LLC | N4019210D28090004 | 3586194 | 3581569 | 2016-06-21 | 2016-09-17
2017-02-15 | 2014 | Air Force Active | SAKW133005 |  | 2014-03-04 | 2015-03-05 | P & S Construction | N4019210D2804KB01 | 3587000 | 3608946 | 2017-02-06 | 2017-03-04
2016-11-15 | 2015 | Air Force Active | SAKW143031 |  | 2014-12-05 | 2015-03-06 | P&S Construction Inc | N4019210D28040024 | 6205000 | 6205000 | 2016-07-30 | 2016-09-19
2017-02-15 | 2012 | Air Force Active | SGBP100904C |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 524445324 | 553123326 | 2016-09-10 | 2017-12-22
2016-11-15 | 2011 | Air Force Active | SXHT053001 |  | 2014-01-04 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99768 | 99768 | 2014-09-01 | 2014-09-01
2016-11-15 | 2011 | Air Force Active | SXHT053001 |  | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231044 | 148820919 | 2015-12-02 | 2016-04-02
2017-02-15 | 2010 | Air Force Active | TYFR053037 |  | 2011-08-31 | 2011-09-30 | D & b Bau GmbH, Neustadt | W912GB09C0022 | 10500000 | 10500000 | 2013-07-15 | 2013-08-16
2016-12-07 | 2011 | Air Force Active | TYFR083001 |  | 2012-08-27 | 2012-09-26 | Peter Gross GmbH | W912GB10C001A | 2140702 | 2253366 | 2013-05-14 | 2013-05-14
2016-12-07 | 2011 | Air Force Active | TYFR106261 |  | 2013-09-13 | 2013-11-13 | MICKAN | C0114014 | 1697911 | 1794880 | 2014-12-12 | 2015-01-22
2016-11-15 | 2013 | Air Force Active | TYFR126175 |  | 2014-01-21 | 2014-07-23 | MICKAN Generalbau | C124019 | 1664151 | 1737129 | 2015-02-24 | 2015-06-04
2017-02-15 | 2011 | Air Force Active | TYFU083507R2 |  | 2014-03-25 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | 17945000 | 16558194 | 2015-06-28 | 2015-06-28
2017-02-15 | 2014 | Air Force Active | UHHZ123001 |  | 2014-08-01 | 2015-01-15 | Garbutt Construction Company | W912HN10D00340002 | 1779360 | 1827879 | 2016-05-11 | 2016-05-11
2016-11-15 | 2012 | Air Force Active | USAFE17002 |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421000 | 43939851 | 2014-01-16 | 2016-06-10
2016-11-15 | 2012 | Air Force Active | USAFE17003 |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521530 | 10521530 | 2014-05-24 | 2015-10-01
2016-11-15 | 2012 | Air Force Active | USAFE17004 |  | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587915 | 29806790 | 2014-04-13 | 2015-01-27
2017-02-15 | 2014 | Air Force Active | VKAG133001 |  | 2014-07-18 | 2015-01-28 | Crew MW, LLC | FA480915CC001 | 1864766 | 1864766 | 2016-06-05 | 2016-07-25
2017-02-15 | 2008 | Air Force Active | VLSB083007 |  | 2008-07-31 | 2008-09-29 | Prime Ktr Golf Course CNS (Phase 1) | N6945008C2846 | 2771874 | 2827760 | 2009-09-29 | 2009-09-29
2017-02-15 | 2008 | Air Force Active | VLSB083007 |  | 2015-06-23 | 2015-07-23 | Bell & Carrington | W912HN15P0034 | 7320 | 7320 | 2017-08-21 | 2017-08-21
2017-02-15 | 2008 | Air Force Active | VLSB083007 |  | 2016-01-26 | 2016-02-25 | Robert K Carter (Tract 1001) | DACA216166023 | 87500 | 87500 | 2016-03-27 | 2016-03-27
2017-02-15 | 2008 | Air Force Active | VLSB083007 |  | 2011-05-11 | 2011-06-10 | J2 Engineering (Phase 2) | N6945008D17820005 | 3446432 | 5339270 | 2012-11-09 | 2014-03-01
2017-02-15 | 2008 | Air Force Active | VLSB083007 |  | 2015-06-28 | 2015-07-28 | Property Solutions, LLC | W912HN15P0036 | 14350 | 14350 | 2017-02-17 | 2017-02-17
2016-12-07 | 2014 | Air Force Active | VYHK143301 |  | 2014-12-15 | 2015-09-03 | UVB, Bitburg | C147392 | 1911000 | 1911000 | 2017-09-14 | 2017-09-14
2017-02-15 | 2014 | Air Force Active | VYHK143301 |  | 2014-12-15 | 2015-09-03 | UVB, Bitburg | CON1473920000 | 1911000 | 1911000 | 2017-09-14 | 2017-09-14
2017-02-15 | 2016 | Air Force Active | WWCX103027 |  | 2016-03-08 | 2016-06-13 | MT Hojgaard | W912DS16C0010 | 24343934 | 24343934 | 2018-10-24 | 2018-10-24
2017-02-15 | 2014 | Air Force Active | WWCX103028 |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817608 | 39817608 | 2016-08-08 | 2016-08-08
2017-02-15 | 2013 | Air Force Active | WWCX103032 |  | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031649 | 24018115 | 2015-07-29 | 2015-07-29
2017-02-15 | 2014 | Air Force Active | WWYK129000 |  | 2015-10-08 | 2016-02-26 | Fortiss SBJV,LLC | W912BV16C0004 | 10958132 | 10958132 | 2017-09-06 | 2017-09-06
2017-02-15 | 2015 | Air Force Active | WWYK143004 |  | 2015-03-23 | 2016-05-05 | CWG-JV | W912BV16C0029 | 36114652 | 36114652 | 2018-02-08 | 2018-03-17
2017-02-15 | 2016 | Air Force Active | WWYK163002 |  | 2016-03-08 | 2016-09-28 | Harper Construction | W912BV16C0045 | 33800153 | 33800153 | 2018-06-20 | 2018-06-20
2016-11-15 | 2013 | Air Force Active | XLWU103002 |  | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 12555018 | 13564863 | 2015-08-11 | 2016-08-26
2017-02-15 | 2014 | Air Force Active | XLWU103007 |  | 2015-03-10 | 2015-04-14 | Southeast Cherokee Construction | W9127810D00780009 | 9094468 | 9183905 | 2016-11-11 | 2017-01-15
2016-11-15 | 2011 | Air Force Active | XQPZ084017 |  | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995500 | 25607151 | 2014-09-29 | 2015-09-23
2017-02-15 | 2016 | Air Force Active | XQPZ094013 |  | 2016-07-08 | 2016-11-08 | Federal/Bryan Construction | W9128F17C0004 | 5989953 | 5989953 | 2017-11-03 | 2017-11-03
2016-11-15 | 2014 | Air Force Active | XQPZ124003 |  | 2014-12-03 | 2015-03-25 | John Bowman Incorporated (JBI) | W9128F12D00370011 | 1581000 | 1588581 | 2015-12-09 | 2016-01-20
2016-11-15 | 2010 | Air Force Active | XTLF033303 |  | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849633 | 9592033 | 2012-02-12 | 2012-06-29
2016-11-15 | 2012 | Air Force Active | YWHG071005 |  | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172600 | 4308791 | 2013-09-07 | 2014-08-15
2017-02-15 | 2014 | Air Force Active | YWHG111010 |  | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817700 | 3892833 | 2015-12-04 | 2016-12-02
2017-02-15 | 2014 | Air Force Active | ZHTV053302 |  | 2015-03-11 | 2015-06-23 | Messer Construction | W912QR15C0012 | 24166000 | 24395669 | 2017-06-02 | 2017-07-03
2017-02-15 | 2014 | Air Force Active | ZHTV126003 |  | 2014-11-13 | 2015-04-02 | Ma Chis Kawv | W912QR14D0013 | 1989978 | 2005599 | 2016-04-14 | 2016-08-31
2016-12-01 | 2013 | Air Force Reserve | CTGB109003 |  | 2014-07-30 | 2014-09-30 | Ma-Chis KAWV V, LLC | W912QR14D00130004 | 1078904 | 1110040 | 2015-11-04 | 2016-08-31
2016-12-01 | 2013 | Air Force Reserve | DDPM120009 |  | 2015-02-22 | 2015-09-16 | IICON CONSTRUCTION GROUP | FA667515C0002 | 1697850 | 1697850 | 2016-09-29 | 2016-07-27
2017-02-07 | 2015 | Air Force Reserve | DDPM130008 |  | 2015-06-22 | 2015-08-27 | K-W Construction | N6945013D17690003 | 2814000 | 2814000 | 2016-07-27 | 2019-01-15
2017-02-07 | 2012 | Air Force Reserve | DKFX079003 |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149000 | 9004770 | 2013-03-01 | 2016-08-18
2017-02-07 | 2014 | Air Force Reserve | PDPG030130P1 |  | 2014-12-02 | 2015-04-24 | Macro-Z Technology | W912QR15C0009 | 17092932 | 17092932 | 2017-03-20 | 2017-03-20
2017-02-07 | 2013 | Air Force Reserve | RVKQ099095 |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242986 | 5242986 | 2016-01-15 | 2016-07-13
2016-12-01 | 2012 | Air Force Reserve | RVKQ120572 |  | 2013-01-04 | 2014-08-21 | Oddo Construction Services | FA667014R00040001 | 2087131 | 2137512 | 2015-03-21 | 2016-05-26
2017-02-07 | 2014 | Air Force Reserve | WWYK129000 |  | 2015-10-08 | 2016-02-26 | Fortiss SBJV,LLC | W912BV16C0004 | 10958133 | 10958133 | 2018-02-18 | 2018-02-18
2017-02-15 | 2013 | Air National Guard | ATQZ099073 |  | 2014-10-01 | 2014-12-08 | E & B Paving, Inc | W912L91322101 | 1498405 | 1498405 | 2016-04-21 | 2016-05-27
2016-09-14 | 2012 | Air National Guard | ATQZ099080 |  | 2014-05-10 | 2014-08-27 | Patterson Horth, Inc. | W912L910D00090055 | 4241000 | 4241000 | 2015-11-20 | 2016-05-27
2016-09-14 | 2012 | Air National Guard | AXQD129074 |  | 2014-09-12 | 2014-12-15 | Cutter Enterprises LLC | W912SV15C0001 | 1680218 | 1680218 | 2016-07-16 | 2017-07-16
2017-02-15 | 2015 | Air National Guard | BKTZ129083 |  | 2015-07-29 | 2015-09-21 | RL Alvarez Constction, LLC | W912L715C0009 | 2358247 | 2358247 | 2016-10-20 | 2017-01-20
2017-02-15 | 2014 | Air National Guard | BRKR999147 |  | 2014-04-02 | 2014-08-13 | Southeast Cherokee Construction, Inc | W912JA14C0001 | 8201275 | 8201275 | 2016-10-23 | 2017-05-31
2017-02-15 | 2015 | Air National Guard | CEKT129080 |  | 2015-08-19 | 2015-12-29 | NUTMEG COMPANIES, INC. | W91ZRS12D00260006 | 1968645 | 1968645 | 2018-08-18 | 2018-05-18
2017-02-15 | 2015 | Air National Guard | CEKT139004 |  | 2015-02-17 | 2015-06-03 | Cutter Enterprises, LLC | W91ZRS15C0002 | 14859726 | 14859726 | 2018-01-09 | 2017-02-28
2017-02-15 | 2016 | Air National Guard | FFAN139009 |  | 2016-05-26 | 2016-08-16 | Lang Construction Group, Inc | W912LP16C0008 | 6042876 | 6042876 | 2017-09-14 | 2018-04-27
2017-02-15 | 2015 | Air National Guard | FFAN139010 |  | 2015-03-01 | 2015-07-09 | Lang Construction | W912LP15C00010005 | 8154789 | 8154789 | 2016-08-07 | 2017-03-31
2017-02-15 | 2016 | Air National Guard | FKNN059220 |  | 2016-06-16 | 2016-09-15 | Lang Construction Group, Inc | W912LP16C0008 | 4552775 | 4552775 | 2017-10-15 | 2018-03-27
2017-02-15 | 2014 | Air National Guard | FPBB129050 |  | 2014-07-17 | 2014-09-08 | R.J. Ortlieb | W912PQ12D00100008 | 4895886 | 4895886 | 2015-08-04 | 2016-08-31
2017-02-15 | 2015 | Air National Guard | FTAE129002 |  | 2015-04-24 | 2015-08-07 | Aztec General Contractors, LLC | W912LC15R5002 | 1789838 | 1789838 | 2016-06-22 | 2017-03-24
2017-02-15 | 2014 | Air National Guard | GJKZ129093 |  | 2014-04-22 | 2014-08-12 | Pacific Tech Construction | W912K311D00030005 | 1758438 | 1758438 | 2015-03-17 | 2016-10-31
2016-10-12 | 2013 | Air National Guard | HAYW109006 |  | 2014-08-15 | 2014-10-26 | Cooper Chase | W912LA11D00040002 | 1261072 | 1261072 | 2016-02-25 | 2016-04-26
2017-02-15 | 2014 | Air National Guard | JKSE129321 |  | 2014-09-24 | 2014-11-07 | Guy Tabacco Construction Co.. | W9124V12D00110003 | 1261466 | 1261466 | 2015-10-03 | 2016-08-24
2017-02-15 | 2013 | Air National Guard | KNMD119001 |  | 2013-03-04 | 2013-09-12 | Nan Inc. | W912J613C0006 | 5593905 | 5593905 | 2015-04-24 | 2017-05-31
2017-02-15 | 2014 | Air National Guard | LDXF099060 |  | 2014-07-30 | 2014-09-22 | Patterson-Horth | W912L914D00110002 | 7071641 | 7071641 | 2016-02-28 | 2016-09-22
2016-10-12 | 2014 | Air National Guard | LKLW109037 |  | 2014-08-06 | 2014-09-25 | Lobar Associates | W912KC14C0008 | 7039937 | 7039937 | 2015-10-25 | 2016-05-31
2016-10-12 | 2014 | Air National Guard | LKLW959716 |  | 2015-07-29 | 2015-09-29 | Miller Bros CNS Inc | W912KC15C00270000 | 1904075 | 1904075 | 2016-07-12 | 2016-07-12
2017-02-15 | 2015 | Air National Guard | LUXC139026 |  | 2015-07-11 | 2016-02-22 | Golden Rule Construction Co., Inc. | W912MM12D00050009 | 1567590 | 1567590 | 2016-11-27 | 2016-12-07
2017-02-15 | 2016 | Air National Guard | LYBH049066 |  | 2016-04-20 | 2016-06-22 | Danhill Construction | W912L812D0014 | 2809109 | 2809109 | 2016-07-20 | 2017-04-15
2017-02-15 | 2015 | Air National Guard | MBMV129060 |  | 2016-02-22 | 2016-05-17 | Beckering Construction | W912JB15C2007 | 1328194 | 1328194 | 2017-06-12 | 2017-06-12
2017-02-15 | 2016 | Air National Guard | NKAK139133 |  | 2015-03-29 | 2015-07-20 | HGL | W912JF14D00130002 | 1349711 | 1349711 | 2016-10-18 | 2017-03-15
2016-11-16 | 2014 | Air National Guard | PSTE129092 |  | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W9124209D0003S401 | 1813699 | 1813699 | 2014-12-24 | 2016-01-29
2016-11-16 | 2014 | Air National Guard | PSXE109034 |  | 2014-04-15 | 2014-07-01 | Howard Pence, Inc | W912L714C0004 | 17303286 | 17303286 | 2016-07-21 | 2016-09-23
2017-02-15 | 2015 | Air National Guard | PSXE139000 |  | 2016-05-02 | 2016-09-01 | Eutaw Construction | W912L71322101 | 6550688 | 6550688 | 2018-01-01 | 2018-02-07
2016-09-14 | 2012 | Air National Guard | SPBN079047 |  | 2013-05-08 | 2013-08-29 | Maron Construction Co. | W912SV13C0003 | 8178006 | 8178006 | 2014-09-24 | 2016-06-29
2016-09-14 | 2012 | Air National Guard | SPBN089050 |  | 2015-07-09 | 2015-08-10 | Maron Construction Company | W912SV10D00170007 | 1922000 | 1922000 | 2016-09-08 | 2016-09-28
2017-02-15 | 2015 | Air National Guard | SZCQ139901 |  | 2015-01-28 | 2015-07-28 | Cutter Enterprises, LLC | W912TF15C05000008 | 16527517 | 16527517 | 2016-11-19 | 2017-07-05
2017-02-15 | 2016 | Air National Guard | SZCQ139903 |  | 2015-12-29 | 2016-04-07 | Cutter Enterprises, LLC | W912TF14D05130501 | 2022617 | 2022617 | 2017-01-01 | 2017-01-31
2017-02-15 | 2015 | Air National Guard | SZCQ139904 |  | 2015-01-28 | 2015-07-27 | Cutter Enterprises, LLC | W912TF15C0500 | 16353767 | 16353767 | 2016-11-18 | 2018-08-13
2016-09-14 | 2012 | Air National Guard | TQKD129072 |  | 2014-03-25 | 2014-07-22 | Total Site Services | W912JV14C0006 | 1802993 | 1802993 | 2015-03-19 | 2016-06-30
2016-10-12 | 2013 | Air National Guard | TQKD139018 |  | 2014-11-03 | 2015-01-20 | Andrews Contracting Services | W912JV15C0001 | 912772 | 912772 | 2015-07-09 | 2016-02-28
2017-02-15 | 2013 | Air National Guard | TQKD139018 |  | 2014-11-03 | 2015-01-20 | Port of Portland | W912JV1422150 | 912772 | 912772 | 2015-07-09 | 2016-02-28
2016-09-14 | 2012 | Air National Guard | TUMR109004 |  | 2013-04-30 | 2013-09-26 | R.B. Construction Group, Inc. | W912LR13C0001 | 1500000 | 1500000 | 2015-10-06 | 2017-03-31
2017-02-15 | 2014 | Air National Guard | TWLR129077 |  | 2014-07-25 | 2014-11-14 | MARON CONSTRUCTION CO., INC. | W912LD15C0001 | 6315747 | 6315747 | 2015-12-14 | 2017-01-31
2017-02-15 | 2014 | Air National Guard | ULYB112022 |  | 2014-07-30 | 2014-09-12 | E.L.Crawford Construction | W912NS14D00160002 | 1954163 | 1954163 | 2015-10-12 | 2017-09-30
2017-02-15 | 2014 | Air National Guard | WAAR109002 |  | 2014-07-02 | 2014-08-20 | AWA/Megen Joint Venture LLC | W9136414C0011 | 5944120 | 5944120 | 2015-12-01 | 2016-12-31
2016-09-14 | 2012 | Air National Guard | WAAR129078 |  | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | W9136413D00050002 | 1793652 | 1793652 | 2014-02-23 | 2016-06-30
2016-09-14 | 2012 | Air National Guard | WKVB099052 |  | 2014-12-04 | 2015-03-25 | Regiment | W912PQ15C0003 | 2021340 | 2021340 | 2016-04-23 | 2016-10-14
2017-02-15 | 2016 | Air National Guard | XDQU949500 |  | 2016-04-29 | 2016-09-22 | BSL Galbreath, Inc. | W912JM16C0013 | 8811106 | 8811106 | 2017-11-08 | 2018-01-31
2017-02-15 | 2014 | Air National Guard | XHZG129946 |  | 2014-06-25 | 2014-08-20 | Magnum Constrution | W912L611D00010029 | 1979359 | 1979359 | 2015-08-15 | 2016-12-30
2016-10-12 | 2015 | Air National Guard | ZAWA159061 |  | 2015-05-20 | 2015-09-30 | Marteen Inc | W912KC15R00160000 | 1500000 | 1500000 | 2016-01-18 | 2016-07-08
2017-01-31 | 2012 | Army Active | 1235 |  | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23139000 | 23189000 | 2014-04-10 | 2016-03-31
2017-01-31 | 2011 | Army Active | 13852 |  | 2011-07-15 | 2015-09-28 | Dawson Technical, LLC | W9128F-15-C-0044 | 1996000 | 2003000 | 2016-07-23 | 2016-09-30
2016-12-31 | 2012 | Army Active | 17220 |  | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12623000 | 12866000 | 2015-11-11 | 2016-11-15
2017-01-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2014-07-02 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 727000 | 749000 | 2017-02-08 | 2016-10-12
2016-10-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 23320000 | 23379000 | 2013-09-20 | 2014-11-24
2017-01-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2016-06-10 | Zieson Construction Company, LLC | W912DQ-15-D-4001 | 44000 | 47000 | 2016-12-21 | 2017-03-03
2017-01-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2014-09-03 | VISTA Construction LLC | W91236-14-C-0043 | 4055000 | 4805000 | 2015-09-16 | 2017-05-23
2016-10-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650000 | 46658000 | 2015-10-15 | 2015-10-16
2017-01-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2015-01-14 | Doyon Management Services, LLC | W91236-15-C-0017 | 14297000 | 14313000 | 2017-05-03 | 2017-05-03
2016-10-31 | 2015 | Army Active | 41449 |  | 2016-05-09 | 2016-09-15 | Purcell Construction Corporation | W91236-16-C-0018 | 58913000 | 58913000 | 2018-10-07 | 2018-12-18
2017-01-31 | 2013 | Army Active | 45116 |  | 2013-02-23 | 2013-07-25 | ANTHONY AND GORDON CONSTRUCTION COMPANY | N69450-13-C-0754 | 0 | 0 | 2016-12-30 | 2016-12-30
2017-01-31 | 2012 | Army Active | 5034 |  | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603000 | 13966000 | 2014-07-18 | 2017-01-31
2017-01-31 | 2013 | Army Active | 51519 |  | 2012-05-16 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 2033000 | 2033000 | 2014-06-04 | 2017-03-31
2017-01-31 | 2013 | Army Active | 51519 |  | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959000 | 7327000 | 2015-02-15 | 2017-01-31
2017-01-31 | 2014 | Army Active | 51868 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 55619000 | 57328000 | 2016-12-26 | 2017-05-04
2017-01-31 | 2015 | Army Active | 51937 |  | 2015-07-28 | 2016-01-28 | ACC Construction Co., Inc | W912HP-16-C-0001 | 45035000 | 56063000 | 2018-03-17 | 2018-05-01
2017-01-31 | 2014 | Army Active | 53584 |  | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036000 | 40965000 | 2017-12-09 | 2017-12-09
2017-01-31 | 2011 | Army Active | 53789 |  | 2012-12-18 | 2013-09-30 | Halbert Construction Company, Inc. | W91238-13-C-0012 | 18519000 | 28093000 | 2015-01-05 | 2017-02-02
2017-01-31 | 2013 | Army Active | 55121 |  | 2014-10-21 | 2015-07-31 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 40866000 | 43384000 | 2017-12-30 | 2018-08-13
2016-12-31 | 2012 | Army Active | 55985 |  | 2012-01-10 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15916000 | 18090000 | 2016-03-23 | 2017-01-25
2017-01-31 | 2011 | Army Active | 56024 |  | 2012-06-29 | 2012-09-25 | Nan, Inc. | W9128A-12-C-0019 | 21105000 | 23910000 | 2014-10-14 | 2016-11-17
2016-11-30 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2016-09-27 | JV PGWM SATCOM | W912GB-11-D-0021 | 0 | 0 | 2017-10-13 | 2017-10-13
2016-12-31 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565000 | 29775000 | 2015-10-05 | 2016-03-15
2016-12-31 | 2010 | Army Active | 58625 |  | 2009-10-09 | 2010-02-05 | Harkins Builders, Inc. | W912DR-10-C-0068 | 11717000 | 19424000 | 2012-09-01 | 2014-11-11
2017-01-31 | 2011 | Army Active | 58675 |  | 2011-02-22 | 2015-09-30 | Semper Tek, Inc. | W912QR-14-D-0023 | 354000 | 387000 | 2016-10-15 | 2016-09-09
2017-01-31 | 2008 | Army Active | 58784 |  | 2012-02-02 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | W912UM-12-C-0057 | 5458000 | 6988000 | 2014-03-16 | 2017-01-31
2016-10-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2008-03-31 | Shinsung Engr. & Const. Co., Ltd. | W912UM-08-C-0011 | 15961000 | 559000 | 2010-06-13 | 2008-10-22
2017-01-31 | 2008 | Army Active | 58784 |  | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32469000 | 36193000 | 2014-09-07 | 2017-04-30
2016-10-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2009-01-29 | Hanwha Engr. & Corporation Co., Ltd. | W912UM-09-C-0009 | 17815000 | 18941000 | 2011-01-01 | 2011-05-18
2017-01-31 | 2013 | Army Active | 58849 |  | 2015-06-02 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 88666000 | 125515000 | 2019-10-12 | 2019-12-01
2017-01-31 | 2017 | Army Active | 58849 | 86285 | 2015-12-12 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 88666000 | 125515000 | 2019-10-12 | 2019-12-01
2017-01-31 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2014-09-05 | DBA ARGE JV PGWM NETCOM | W912GB-14-C-0037 | 29010000 | 31521000 | 2016-07-07 | 2017-03-03
2017-01-31 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 0 | 0 | 2015-10-05 | 2016-03-15
2017-01-31 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2016-09-27 | JV PGWM SATCOM | W912GB-11-D-0021 | 396000 | 396000 | 2017-10-13 | 2017-10-13
2017-01-31 | 2011 | Army Active | 59044 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270000 | 117542000 | 2015-11-14 | 2017-08-31
2017-01-31 | 2014 | Army Active | 59779 |  | 2016-02-24 | 2016-07-28 | San Juan Construction, Inc. | W9128A-16-C-0006 | 54844000 | 53559000 | 2020-06-10 | 2020-06-10
2017-01-31 | 2011 | Army Active | 60555 |  | 2010-12-16 | 2012-05-14 | Landesbetrieb Bau und Immobilien Hessen Zentrale | W912GB-08-C-0005 | 28704000 | 33623000 | 2014-06-01 | 2017-01-31
2017-01-31 | 2012 | Army Active | 61842 |  | 2012-03-13 | 2015-04-20 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0004 | 12172000 | 10425000 | 2016-12-01 | 2017-02-15
2017-01-31 | 2014 | Army Active | 62204 |  | 2015-03-19 | 2016-02-08 | Meltech Corp., Inc. | W912DR-14-D-0021 | 6840000 | 6840000 | 2017-08-16 | 2017-08-16
2017-01-31 | 2012 | Army Active | 62657 |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100113000 | 102060000 | 2015-10-19 | 2016-10-25
2017-01-31 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 84367000 | 85780000 | 2021-06-09 | 2021-12-06
2016-10-31 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV | W91238-11-C-0010 | 34801000 | 3567000 | 2013-06-12 | 2014-06-30
2017-01-31 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W91238-14-C-0040 | 38915000 | 44104000 | 2016-06-30 | 2016-10-22
2017-01-31 | 2010 | Army Active | 63571 |  | 2016-01-16 | 2016-04-12 | Akima Construction Services, LLC | W912DY-14-D-0001 | 16769000 | 16769000 | 2017-08-01 | 2017-10-29
2017-01-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-09-26 | MEGEN Construction Company, Inc. | W912HN-11-D-0047 | 7295000 | 9869000 | 2015-04-08 | 2016-10-24
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-06-28 | M.A. Mortenson Company | W9126G-08-D-0045 | 19332000 | 19731000 | 2013-11-17 | 2013-11-14
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-01-03 | TSS-Garco Joint Venture | W912DW-13-C-0019 | 8912000 | 9318000 | 2014-08-06 | 2015-04-30
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-09-21 | 3D Contracting Inc. | W912DW-12-C-0046 | 14649000 | 15311000 | 2014-05-24 | 2014-12-09
2016-10-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-08-23 | KCI Construction Company | W912DQ-12-C-4009 | 30970000 | 32856000 | 2014-03-12 | 2014-10-27
2016-10-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | W912DQ-12-D-4006 | 2493000 | 3965000 | 2014-01-04 | 2015-12-08
2017-01-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-07 | Arch Insurance Company | W912DQ-11-D-4011 | 8541000 | 9243000 | 2014-08-25 | 2017-02-17
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-06-18 | Megen Construction Company, Inc. | W912HN-11-D-0047 | 14849000 | 16091000 | 2015-01-02 | 2016-08-19
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-09-12 | Environet, Inc. | W912DW-13-C-0042 | 5662000 | 11648000 | 2015-02-12 | 2016-07-28
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-05-17 | Tunista Construction, LLC | W912DW-13-C-0035 | 9433000 | 11453000 | 2014-12-18 | 2015-12-31
2017-01-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2016-09-22 | TSS-Garco Joint Venture | W912DW-16-C-0015 | 42468000 | 42468000 | 2018-07-05 | 2018-07-05
2017-01-31 | 2012 | Army Active | 64753 |  | 2012-01-09 | 2012-07-13 | Liberty Mutual Insurance Company | W9126G-11-D-0061 | 6095000 | 6160000 | 2014-02-03 | 2016-04-14
2017-01-31 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503000 | 42808000 | 2014-07-28 | 2017-02-24
2016-10-31 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2013-01-07 | Turner Strategic Technologies, LLC | W91236-13-C-0017 | 8195000 | 8575000 | 2014-11-28 | 2015-05-28
2017-01-31 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2016-09-30 | ASJ Construction LLC | W9126G-16-C-0117 | 623000 | 623000 | 2017-07-10 | 2017-07-10
2016-10-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18727000 | 19913000 | 2015-04-08 | 2015-10-14
2017-01-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2015-09-30 | Fortis Networks, Inc. | W912DQ-14-D-4011 | 1828000 | 2406000 | 2016-08-06 | 2016-10-13
2017-01-31 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30762000 | 38895000 | 2015-12-12 | 2017-12-01
2017-01-31 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2016-05-27 | ARGO Systems LLC | W912DR-16-C-0016 | 6900000 | 6900000 | 2018-01-06 | 2018-01-06
2017-01-31 | 2013 | Army Active | 66023 |  | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345000 | 27484000 | 2016-09-09 | 2017-01-20
2016-10-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687000 | 14606000 | 2014-12-23 | 2014-12-31
2017-01-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2015-01-20 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 6228000 | 6524000 | 2016-05-05 | 2017-02-28
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-08-29 | Alutiiq Diversified Services, LLC | W912DW-12-C-0040 | 10525000 | 13116000 | 2014-03-11 | 2015-07-28
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-06-20 | Bristol General Contractors, LLC | W912DW-14-C-0015 | 5288000 | 6122000 | 2015-09-10 | 2016-04-15
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6814000 | 7400000 | 2015-08-21 | 2015-10-09
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-12-24 | Burr-MZT Joint Venture | W912DW-14-C-0001 | 919000 | 983000 | 2014-08-04 | 2014-08-01
2017-01-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2016-09-28 | National Native American Construction, Inc. | W912DQ-16-C-4017 | 1325000 | 1325000 | 2017-05-27 | 2017-05-27
2017-01-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2016-09-08 | Centennial Contractors Enterprises Inc. | W912DW-11-D-1002 | 460000 | 460000 | 2017-06-10 | 2017-01-23
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-08-02 | James Talcott Construction, Inc. | W912DW-10-D-1015 | 5769000 | 6297000 | 2014-11-17 | 2015-02-06
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Vet Industrial, Inc. | W912DW-10-D-1021 | 4980000 | 5253000 | 2013-11-01 | 2013-11-25
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Bristol General Contractors, LLC | W912DW-12-D-1018 | 1979000 | 2354000 | 2013-05-30 | 2013-11-22
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775000 | 14633000 | 2014-08-26 | 2015-03-02
2017-01-31 | 2011 | Army Active | 66595 |  | 2011-09-08 | 2015-01-19 | LBB Kaiserslautern | W912GB-09-C-0014 | 30046000 | 30614000 | 2017-09-28 | 2017-09-28
2017-01-31 | 2009 | Army Active | 66725 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7202000 | 7957000 | 2014-06-04 | 2017-03-31
2017-01-31 | 2010 | Army Active | 66726 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757000 | 9230000 | 2014-06-04 | 2017-03-31
2017-01-31 | 2011 | Army Active | 66834 |  | 2010-12-01 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 16173000 | 20463000 | 2013-12-18 | 2016-01-15
2016-10-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-04-14 | Arctic-American JV | W911KB-14-C-0008 | 16180000 | 16156000 | 2015-10-15 | 2015-10-15
2017-01-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-12-31 | ALCAN BUILDERS INC. | W911KB-15-C-0001 | 12375000 | 12770000 | 2016-09-06 | 2016-09-26
2016-10-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0019 | 14180000 | 14599000 | 2016-02-04 | 2016-05-10
2017-01-31 | 2014 | Army Active | 67157 |  | 2015-05-13 | 2015-08-18 | Watts Constructors, LLC | W9128A-15-C-0003 | 63500000 | 64292000 | 2017-12-13 | 2018-01-13
2017-01-31 | 2012 | Army Active | 68050 |  | 2012-10-19 | 2016-01-15 | Whiting-Turner Contracting Company | W912DR-16-C-0002 | 30470000 | 60487000 | 2018-06-13 | 2018-09-25
2016-11-30 | 2011 | Army Active | 68074 |  | 2013-05-30 | 2013-08-12 | Hessisches Baumanagement Wiesbaden | W912GB-09-C-0059 | 6765000 | 7983000 | 2014-12-12 | 2015-01-09
2017-01-31 | 2013 | Army Active | 68530 |  | 2015-05-02 | 2015-09-23 | Solis Constructors, Inc. | W9126G-14-D-0050 | 18828000 | 20186000 | 2017-05-11 | 2017-05-11
2016-11-30 | 2011 | Army Active | 68606 |  | 2011-09-02 | 2012-10-12 | Bauamt Amberg-Sulzbach | W912GB-09-C-0017 | 18121000 | 18366000 | 2014-05-25 | 2014-06-16
2017-01-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | W912GB-11-D-0036 | 7198000 | 8645000 | 2014-06-25 | 2014-12-04
2017-01-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2014-06-24 | OBG Engineering GmbH & Co. KG | W912GB-14-D-0019 | 90000 | 90000 | 2014-10-07 | 2014-11-20
2017-01-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-23 | ECC International LLC | W912GB-13-C-0003 | 87011000 | 91198000 | 2015-09-19 | 2017-07-31
2016-10-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | W912BV-12-C-0003 | 9573000 | 9590000 | 2013-12-16 | 2014-06-27
2017-01-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 5118000 | 5118000 | 2013-09-13 | 2016-11-12
2017-01-31 | 2012 | Army Active | 69286 |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008000 | 8868000 | 2013-09-13 | 2016-11-12
2017-01-31 | 2012 | Army Active | 69489 |  | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772000 | 58548000 | 2015-05-27 | 2017-06-01
2017-01-31 | 2015 | Army Active | 69649 |  | 2015-08-13 | 2015-09-28 | Odyssey International, Inc | W912DR-15-C-0038 | 14675000 | 19766000 | 2017-07-24 | 2017-07-18
2017-01-31 | 2012 | Army Active | 69828 |  | 2013-07-16 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 8830000 | 8852000 | 2016-01-19 | 2016-11-07
2016-10-31 | 2012 | Army Active | 70751 |  | 2011-11-21 | 2012-06-29 | Brantley Construction Services, LLC | W912HN-10-D-0056 | 11682000 | 12285000 | 2014-07-21 | 2014-07-23
2016-10-31 | 2012 | Army Active | 70751 |  | 2011-11-21 | 2012-01-26 | Balfour Beatty Construction, LLC | W912HN-09-D-0022 | 10447000 | 10437000 | 2014-02-18 | 2013-10-10
2017-01-31 | 2012 | Army Active | 70751 |  | 2011-11-21 | 2016-07-18 | Trend Construction, Inc. | W912HN-15-D-0001 | 301000 | 301000 | 2017-01-08 | 2017-01-05
2017-01-31 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Design and Production Incorporated | W912WJ-11-D-0008 | 55000 | 55000 | 2017-09-15 | 2018-07-31
2017-01-31 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Design and Production Incorporated | W912WJ-16-D-0014 | 2206000 | 2206000 | 2017-09-15 | 2018-07-31
2017-01-31 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Eisterhold Associates Inc | W912WJ-16-D-0012 | 1749000 | 1749000 | 2017-09-15 | 2018-07-31
2017-01-31 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | The McGraw-Hill Companies Inc | W912WJ-08-M-0034 | 9000 | 9000 | 2017-09-15 | 2018-07-31
2017-01-31 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Eisterhold Associates Inc | W912WJ-08-D-0006 | 12451000 | 12451000 | 2017-09-15 | 2018-07-31
2017-01-31 | 2014 | Army Active | 71221 |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542000 | 14301000 | 2016-02-18 | 2016-09-28
2017-01-31 | 2010 | Army Active | 71421 |  | 2010-08-01 | 2015-01-06 | LBB Niederlassung Idar-Oberstein | W912GB-10-C-0042 | 18945000 | 17343000 | 2017-04-23 | 2018-09-29
2017-01-31 | 2011 | Army Active | 71422 |  | 2011-07-18 | 2011-09-14 | LBB Niederlassung Idar-Oberstein | W912GB-09-C-0007 | 34935000 | 31862000 | 2018-07-27 | 2018-09-29
2016-11-30 | 2011 | Army Active | 71472 |  | 2011-03-04 | 2011-08-15 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 18280000 | 19603000 | 2013-03-07 | 2014-07-23
2017-01-31 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2013-09-27 | Contrack Watts, Inc. | W912ER-13-C-0032 | 49413000 | 60476000 | 2015-03-25 | 2016-11-07
2016-10-31 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2014-04-03 | Contrack Watts, Inc. | W912ER-14-C-0011 | 6749000 | 6749000 | 2015-10-30 | 2015-12-08
2017-01-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-19 | Zieson Construction Co. | W912DQ-14-D-4000 | 4796000 | 5011000 | 2016-01-29 | 2016-11-22
2017-01-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777000 | 53703000 | 2016-08-04 | 2017-02-05
2017-01-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-18 | Zieson Construction Company, LLC | W912DQ-15-C-4004 | 14313000 | 15205000 | 2016-07-22 | 2017-02-01
2017-01-31 | 2013 | Army Active | 71675 |  | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751000 | 45753000 | 2016-01-15 | 2017-08-31
2017-01-31 | 2015 | Army Active | 73272 |  | 2015-07-23 | 2015-09-28 | Joint forces Construction, LLC | W91236-15-C-0054 | 6350000 | 7134000 | 2016-10-20 | 2017-08-18
2017-01-31 | 2014 | Army Active | 73384 |  | 2015-03-10 | 2016-03-31 | Edifice-Schlosser JV, LLC | W912DR-15-C-0025 | 0 | 3044000 | 2017-03-31 | 2017-03-31
2017-01-31 | 2015 | Army Active | 73542 |  | 2015-01-23 | 2015-08-27 | Walsh Federal JV | W912QR-15-C-0024 | 17724000 | 17956000 | 2017-04-26 | 2017-06-01
2017-01-31 | 2014 | Army Active | 74638 |  | 2013-11-07 | 2015-04-02 | SGS, LLC | W9126G-15-C-0091 | 13978000 | 14028000 | 2017-01-02 | 2017-04-21
2017-01-31 | 2014 | Army Active | 74861 |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862000 | 27692000 | 2016-08-09 | 2017-06-30
2017-01-31 | 2013 | Army Active | 75165 |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77477000 | 80592000 | 2016-03-02 | 2016-10-19
2017-01-31 | 2015 | Army Active | 75536 |  | 2015-06-15 | 2015-09-30 | Atherton Construction, LLC | W912QR-16-C-0018 | 41545000 | 22837000 | 2018-03-07 | 2018-03-07
2017-01-31 | 2016 | Army Active | 75538 |  | 2016-08-02 | 2016-09-29 | Atherton Construction, LLC | W912QR-16-C-0026 | 23347000 | 23480000 | 2018-04-10 | 2018-04-27
2017-01-31 | 2016 | Army Active | 75966 |  | 2016-04-26 | 2016-07-21 | Weldin Construction, Inc | W911KB-16-C-0017 | 5490000 | 5490000 | 2017-12-10 | 2017-12-08
2017-01-31 | 2014 | Army Active | 76024 |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630000 | 16703000 | 2016-02-24 | 2017-03-30
2017-01-31 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2016-09-28 | Herman Construction Group, Inc. | W91238-15-D-0015 | 2623000 | 2623000 | 2018-05-30 | 2018-05-30
2016-10-31 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072000 | 3140000 | 2015-11-10 | 2016-06-03
2017-01-31 | 2015 | Army Active | 76087 |  | 2015-06-01 | 2015-09-30 | GEMS Environmental Management Services | W91238-15-D-0014 | 4860000 | 4937000 | 2017-03-31 | 2017-05-20
2017-01-31 | 2013 | Army Active | 76196 |  | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25853000 | 29398000 | 2015-06-09 | 2017-04-28
2017-01-31 | 2013 | Army Active | 76586 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717000 | 33082000 | 2015-09-01 | 2017-01-13
2017-01-31 | 2013 | Army Active | 76587 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410000 | 41942000 | 2015-09-01 | 2017-01-13
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-08 | C.I. Contractors INC. | W911KB-14-C-0010 | 5007000 | 6855000 | 2015-04-17 | 2016-07-25
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC | W911KB-14-C-0005 | 9525000 | 10101000 | 2015-10-16 | 2016-08-29
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25547000 | 26284000 | 2016-03-21 | 2016-09-29
2016-10-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6360000 | 7003000 | 2015-08-21 | 2015-10-09
2016-10-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | W9126G-08-D-0044 | 24162000 | 24502000 | 2013-12-31 | 2014-02-18
2017-01-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2016-09-09 | Centennial Contractors Enterprises Inc. | W912DW-11-D-1002 | 36000 | 36000 | 2017-01-18 | 2017-01-23
2016-10-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | W912DW-12-C-0051 | 25901000 | 27950000 | 2014-05-23 | 2014-10-14
2017-01-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2014-04-08 | Glen/Mar Construction, Inc. | W912DW-14-C-0009 | 4771000 | 5945000 | 2015-05-21 | 2017-02-15
2017-01-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2016-09-13 | Glen/Mar Construction, Inc. | W912DW-11-D-1002 | 146000 | 146000 | 2017-05-06 | 2017-05-06
2017-01-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-07-09 | Vet Industrial, Inc. | W912DW-15-C-0007 | 11893000 | 13165000 | 2016-08-24 | 2017-03-13
2017-01-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-04-09 | Walsh Group Ventures | W912DW-15-C-0002 | 11319000 | 11936000 | 2017-07-06 | 2017-07-06
2017-01-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2016-09-20 | WHH Nisqually-Garco Joint Venture | W912DW-16-C-0020 | 12390000 | 12390000 | 2018-05-11 | 2018-05-11
2017-01-31 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2014-08-26 | Archer Western Federal JV | W912DW-14-C-0023 | 36998000 | 39741000 | 2016-03-16 | 2016-11-30
2017-01-31 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 23706000 | 24405000 | 2017-07-06 | 2017-11-06
2016-10-31 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2014-09-03 | The Renew Group, Inc. | W912DW-14-C-0017 | 1106000 | 1124000 | 2015-04-22 | 2015-09-04
2017-01-31 | 2013 | Army Active | 76903 |  | 2012-11-26 | 2014-05-13 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749000 | 69749000 | 2017-01-13 | 2017-04-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3750000 | 1013000 | 2014-02-15 | 2013-08-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7473000 | 8035000 | 2013-12-14 | 2016-06-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2013-12-04 | Solis Constructors, Inc | W9126G-14-C-0006 | 0 | 0 | 2015-01-25 | 2016-03-31
2017-01-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2016-04-12 | AMIDON, INC. | W9126G-16-C-0030 | 3163000 | 3163000 | 2016-12-07 | 2017-01-06
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 | 5379000 | 4709000 | 2013-06-21 | 2014-05-13
2017-01-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-08-28 | Medvolt, LLC | W9128F-14-C-0054 | 13195000 | 13994000 | 2016-03-31 | 2016-06-03
2017-01-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165000 | 17807000 | 2016-02-12 | 2017-06-01
2017-01-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | John Bowman, Inc. | W9128F-13-D-0013 | 2288000 | 2329000 | 2015-10-07 | 2015-12-17
2017-01-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-07-16 | SEK JV | W9128F-13-D-0015 | 3133000 | 3596000 | 2015-02-14 | 2015-07-07
2017-01-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56721000 | 59536000 | 2016-08-22 | 2017-04-30
2016-10-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | Hartland/Mass JV LLC | W9128F-13-D-0014 | 3339000 | 3566000 | 2015-10-20 | 2016-01-05
2017-01-31 | 2015 | Army Active | 77305 |  | 2015-05-23 | 2015-05-28 | Francisco Semsch, Architect, Inc. | W9128F-15-C-0010 | 3848000 | 3848000 | 2016-06-15 | 2016-09-12
2017-01-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 891000 | 891000 | 2016-08-22 | 2017-04-30
2017-01-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585000 | 52540000 | 2016-05-28 | 2017-08-31
2016-10-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2015-01-16 | Agile Infrastructure Services, L.L.C. | W9128F-15-C-0002 | 2843000 | 2902000 | 2016-02-11 | 2016-07-14
2017-01-31 | 2013 | Army Active | 77419 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 10400000 | 10915000 | 2016-12-26 | 2017-05-04
2017-01-31 | 2013 | Army Active | 78054 |  | 2014-07-08 | 2015-03-17 | Akima Construction Services, LLC | W912DR-15-C-0013 | 3358000 | 10413000 | 2016-09-24 | 2017-02-21
2017-01-31 | 2014 | Army Active | 78196 |  | 2015-08-07 | 2016-09-21 | Veterans Northwest Construction LLC | W912DW-16-C-0016 | 11120000 | 11120000 | 2018-04-05 | 2018-04-05
2017-01-31 | 2014 | Army Active | 78196 |  | 2015-08-07 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 20099000 | 20197000 | 2017-07-06 | 2017-11-06
2017-01-31 | 2016 | Army Active | 78366 |  | 2016-08-24 | 2016-09-27 | Mickan Generalbaugesellschaft Amberg | W912GB-15-D-0072 | 2694000 | 2694000 | 2017-12-09 | 2018-02-07
2017-01-31 | 2012 | Army Active | 78475 |  | 2013-05-22 | 2014-11-18 | Klebl GmbH | W912GB-15-C-0003 | 14632000 | 15340000 | 2016-09-27 | 2017-02-24
2017-01-31 | 2012 | Army Active | 78505 |  | 2012-04-06 | 2013-08-07 | Staatliches Hochbauamt Amberg | W912GB-11-C-0027 | 13548000 | 13863000 | 2015-09-14 | 2016-02-17
2017-01-31 | 2014 | Army Active | 79618 |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440000 | 9498000 | 2016-02-11 | 2017-03-06
2017-01-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-08-30 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129000 | 12355000 | 2014-11-30 | 2017-02-15
2016-10-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-07-05 | EMTA CONSTRUCTION CO. INC. | W912GB-10-D-0020 | 320000 | 320000 | 2012-11-22 | 2012-11-22
2016-10-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2013-03-19 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. | W912GB-12-D-0035 | 199000 | 199000 | 2013-10-16 | 2013-10-17
2017-01-31 | 2013 | Army Active | 79933 |  | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 168026000 | 2016-08-30 | 2017-03-03
2017-01-31 | 2014 | Army Active | 79933 | 81186 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 168026000 | 2016-08-30 | 2017-03-03
2017-01-31 | 2015 | Army Active | 79933 | 81187 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 168026000 | 2016-08-30 | 2017-03-03
2017-01-31 | 2013 | Army Active | 80112 |  | 2014-12-02 | 2015-04-23 | Sauer Inc. | W91278-12-D-0039 | 10965000 | 11567000 | 2016-07-19 | 2016-11-01
2017-01-31 | 2013 | Army Active | 80113 |  | 2013-03-12 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 591000 | 717000 | 2016-01-04 | 2016-11-07
2016-10-31 | 2013 | Army Active | 80113 |  | 2013-03-12 | 2013-08-30 | Carntribe-Clement 8aJV #1, LLC | W912HN-11-D-0028 | 5994000 | 5981000 | 2014-11-27 | 2015-02-05
2016-10-31 | 2013 | Army Active | 80113 |  | 2013-03-12 | 2013-08-15 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491000 | 11454000 | 2015-05-30 | 2015-07-20
2017-01-31 | 2012 | Army Active | 80231 |  | 2013-06-03 | 2014-09-28 | East Coast Utility Contractors | W912DR-14-C-0041 | 1484000 | 2146000 | 2015-11-03 | 2017-07-12
2017-01-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-11-25 | Upstate Construction Services, Inc. | W912DS-09-D-0005 | 17287000 | 17827000 | 2015-12-02 | 2016-05-30
2017-01-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 39587000 | 42451000 | 2015-06-17 | 2016-01-25
2017-01-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | Black Horse Group LLC | W912DS-09-D-0004 | 21578000 | 24664000 | 2015-06-22 | 2017-03-01
2017-01-31 | 2014 | Army Active | 80433 |  | 2015-06-11 | 2015-09-22 | K.L. House Construction Co. | W9128F-15-C-0028 | 3423000 | 3435000 | 2016-10-26 | 2017-03-01
2017-01-31 | 2015 | Army Active | 80666 |  | 2016-06-15 | 2016-08-23 | CORE Engineering & Construction, Inc. | W91278-16-D-0014 | 3213000 | 3460000 | 2018-04-19 | 2018-04-19
2017-01-31 | 2014 | Army Active | 80992 |  | 2015-02-06 | 2015-03-24 | Red One Construction, LLC | W9128A-15-C-0002 | 1696000 | 1696000 | 2016-10-20 | 2016-11-19
2017-01-31 | 2014 | Army Active | 81155 |  | 2014-05-02 | 2014-12-05 | SGS, LLC | W9126G-15-C-0005 | 32968000 | 33945000 | 2016-04-11 | 2016-11-04
2017-01-31 | 2015 | Army Active | 81230 |  | 2015-05-08 | 2015-07-27 | Yojin Construction & Engineering Co., Ltd. | W912UM-15-C-0015 | 43753000 | 44722000 | 2018-04-28 | 2018-07-08
2017-01-31 | 2015 | Army Active | 81242 |  | 2015-08-19 | 2015-09-27 | BIC-SCC JV, LLC | W91278-13-D-0003 | 1740000 | 1659000 | 2016-10-27 | 2017-07-14
2017-01-31 | 2015 | Army Active | 81349 |  | 2015-02-20 | 2015-06-04 | Upstate Construction Services, Inc. | W912DS-15-C-0008 | 19408000 | 20173000 | 2016-12-18 | 2017-04-15
2017-01-31 | 2015 | Army Active | 81357 |  | 2015-04-13 | 2015-07-07 | David Boland, Inc. | W9128F-15-C-0017 | 26149000 | 26281000 | 2017-01-18 | 2017-05-31
2017-01-31 | 2015 | Army Active | 81372 |  | 2015-03-31 | 2015-10-29 | Cox Construction Co. | W912PL-16-C-0002 | 26117000 | 29445000 | 2017-12-16 | 2017-12-16
2017-01-31 | 2014 | Army Active | 81424 |  | 2015-07-21 | 2015-09-30 | Southeast Cherokee Construction,Inc. | W91278-10-D-0064 | 3562000 | 3616000 | 2017-02-02 | 2017-03-03
2017-01-31 | 2016 | Army Active | 81427 |  | 2016-07-14 | 2016-09-08 | Daebo Engr. & Const. Co., Ltd | W912UM-16-C-0034 | 44367000 | 44367000 | 2019-02-24 | 2019-02-24
2017-01-31 | 2015 | Army Active | 81658 |  | 2016-09-12 | 2016-12-13 | G2i, LLC | W912PP-17-C-0001 | 2511000 | 2511000 | 2017-10-28 | 2017-10-28
2017-01-31 | 2014 | Army Active | 82394 |  | 2015-03-04 | 2015-12-31 | Red Cedar Enterprises, Inc. | W912BV-13-D-0011 | 2690000 | 2646000 | 2017-02-12 | 2017-05-03
2017-01-31 | 2014 | Army Active | 85260 |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1725000 | 1771000 | 2015-11-05 | 2016-01-13
2017-01-31 | 2016 | Army Active | 85811 |  | 2016-02-12 | 2016-08-29 | B.L. Harbert International, LLC | W912HN-16-C-0014 | 85100000 | 85100000 | 2018-07-25 | 2018-07-25
2017-01-31 | 2014 | Army Active | 85817 |  | 2015-09-22 | 2016-04-07 | LBB Kaiserslautern | W912GB-14-C-0020 | 1685000 | 1924000 | 2016-08-25 | 2016-12-22
2017-01-31 | 2014 | Army Active | 86033 |  | 2015-05-13 | 2015-09-24 | Engineering Design Technologies, Inc. | W9126G-15-D-0003 | 2965000 | 3093000 | 2016-09-08 | 2016-12-14
2017-01-31 | 2015 | Army Active | 86573 |  | 2016-03-29 | 2016-06-30 | Hartland/Mass Joint Venture, LLC | W9128F-15-D-0034 | 2345000 | 2345000 | 2018-01-25 | 2018-01-25
2017-01-31 | 2015 | Army Active | 86859 |  | 2016-07-15 | 2016-09-15 | ETERNA S.A. | W91278-13-D-0020 | 1400000 | 1400000 | 2018-04-26 | 2018-04-26
2017-01-31 | 2016 | Army Active | 89734 |  | 2016-08-15 | 2016-09-29 | TEYA SERVICES LLC | W912HN-16-C-0026 | 1874000 | 1874000 | 2017-05-16 | 2017-05-16
2017-01-31 | 2015 | Army Active | 8984 |  | 2016-03-17 | 2016-09-19 | Orocon - Carothers JV3 | W912QR-16-C-0017 | 13304000 | 13304000 | 2018-04-11 | 2018-04-11
2016-12-06 | 2013 | Army National Guard | 010278 |  | 2013-08-01 | 2013-08-27 | Hurst Construction, LLC | AC-13-C-0052-S | 5223000 | 5437000 | 2014-11-11 | 2015-06-15
2017-02-06 | 2013 | Army National Guard | 011007 |  | 2013-09-24 | 2013-09-30 | Butler Construction Company, LLC. | AC-13-C-0051-S | 1920000 | 1904000 | 2014-10-01 | 2017-03-01
2017-02-06 | 2014 | Army National Guard | 011014 |  | 2014-08-14 | 2014-08-22 | Carmon Construction, Inc. | AC-14-C-0005-S | 4000000 | 3785000 | 2015-12-10 | 2016-04-01
2017-02-06 | 2016 | Army National Guard | 011317 |  | 2016-08-25 | 2016-09-13 | M W Rogers Construction Company, LLC | AC-16-C-0023-S | 4500000 | 4815000 | 2017-09-15 | 2017-09-15
2017-02-06 | 2015 | Army National Guard | 040730 |  | 2016-07-28 | 2016-09-19 | SJ Anderson Company | M16-0068 | 2000000 | 1988000 | 2017-06-30 | 2017-06-30
2017-01-06 | 2014 | Army National Guard | 050182 |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-C -0003 | 12270000 | 16758000 | 2016-12-01 | 2017-06-30
2017-02-06 | 2014 | Army National Guard | 050182 |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-C-0003 | 12270000 | 16758000 | 2016-12-01 | 2017-06-30
2017-02-06 | 2013 | Army National Guard | 060413 |  | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793000 | 30766000 | 2014-10-01 | 2016-02-29
2017-02-06 | 2013 | Army National Guard | 090043 |  | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951000 | 31486000 | 2015-10-01 | 2016-08-16
2017-02-06 | 2016 | Army National Guard | 090071 |  | 2016-08-09 | 2016-09-16 | Sealaska Constructors | W91ZRS-16-C-0001 | 11000000 | 10404000 | 2018-04-06 | 2018-04-06
2017-02-06 | 2014 | Army National Guard | 090088 |  | 2015-08-27 | 2015-09-19 | K-Con, Inc | BI-Q-670-DB | 1363000 | 1318000 | 2016-09-26 | 2016-12-31
2016-12-06 | 2013 | Army National Guard | 100010 |  | 2013-06-21 | 2013-07-25 | EDIS Company | 40325 | 5319000 | 5322000 | 2014-09-23 | 2014-12-04
2017-02-06 | 2016 | Army National Guard | 100082 |  | 2016-06-17 | 2016-09-02 | Wohlsen Construction | 07-2014 | 10800000 | 11467000 | 2017-08-25 | 2018-02-28
2017-02-06 | 2013 | Army National Guard | 120102 |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) | W911YN-11-2-2002 | 19950000 | 24109000 | 2015-07-26 | 2017-02-02
2017-02-06 | 2016 | Army National Guard | 120173 |  | 2016-08-04 | 2016-08-17 | West Construction, Inc. | W911YN-06-2-2001 | 18000000 | 17232000 | 2018-07-30 | 2018-07-30
2017-02-06 | 2014 | Army National Guard | 120195 |  | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | W911YN-13-2-2004 | 5700000 | 5276000 | 2016-04-05 | 2016-04-05
2017-02-06 | 2015 | Army National Guard | 120212 |  | 2016-05-16 | 2016-05-26 | Hendrick Brothers Construction | WI11YN-15-2-2001 | 2000000 | 1911000 | 2017-10-13 | 2017-10-13
2017-02-06 | 2016 | Army National Guard | 130130 |  | 2016-09-16 | 2016-09-22 | Burns & McDonnell Engineering Company, Inc. | W9133L-15-D-0003-C003 | 6800000 | 6446000 | 2017-11-03 | 2017-11-03
2017-02-06 | 2014 | Army National Guard | 140055 |  | 2016-08-02 | 2016-09-30 | NAVFAC Pacific | N40192-16-D-2701 | 2000000 | 1930000 | 2017-09-29 | 2017-09-29
2017-02-06 | 2013 | Army National Guard | 150023 |  | 2013-10-25 | 2014-09-26 | Watts Constructors, LLC | W912J6-14-C-0003 | 32625000 | 33735000 | 2016-11-01 | 2017-01-31
2017-01-06 | 2013 | Army National Guard | 160100 |  | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692000 | 38546000 | 2014-08-01 | 2016-06-24
2017-02-06 | 2014 | Army National Guard | 170033 |  | 2014-06-11 | 2014-06-27 | George Sollitt Construction Co. | W91SMC-14-2-2004-10001 | 17100000 | 16068000 | 2016-10-01 | 2017-10-01
2017-02-06 | 2014 | Army National Guard | 170127 |  | 2014-06-11 | 2014-06-27 | George Sollitt Construction Co. | W91SMC-14-2-2003-10001 | 38000000 | 37862000 | 2016-10-01 | 2017-10-01
2017-02-06 | 2016 | Army National Guard | 171001 |  | 2016-08-08 | 2016-09-30 | Fager-McGee | W91SMC-15-2-2001 | 1900000 | 2343000 | 2017-08-01 | 2017-08-01
2017-02-06 | 2016 | Army National Guard | 190192 |  | 2016-09-23 | 2016-09-29 | Jensen Builders, LTD | W912LP-16-2-2001 | 1900000 | 1658000 | 2017-07-31 | 2017-07-31
2017-02-06 | 2016 | Army National Guard | 200112 |  | 2016-05-06 | 2016-08-26 | Harbin Construction | W912JC-12-D-5308 | 2400000 | 2103000 | 2018-03-09 | 2017-03-01
2017-02-06 | 2016 | Army National Guard | 200113 |  | 2016-05-06 | 2016-09-26 | Harbin Construction | W912JC-12-D-5308 | 4300000 | 3582000 | 2018-03-09 | 2017-03-01
2017-02-06 | 2013 | Army National Guard | 210001 |  | 2013-05-17 | 2013-06-04 | DW Wilburn, Inc. | CT2 1300000269 | 24778000 | 27054000 | 2014-10-01 | 2015-08-16
2017-02-06 | 2013 | Army National Guard | 220241 |  | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300000 | 8872000 | 2016-11-30 | 2016-11-30
2017-02-06 | 2012 | Army National Guard | 230046 |  | 2012-04-05 | 2012-09-26 | ITSI Gibane | W912JD-12-C-0003 | 14390000 | 14894000 | 2014-07-11 | 2016-12-30
2017-02-06 | 2015 | Army National Guard | 230113 |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113-D | 30616000 | 31394000 | 2017-08-03 | 2017-08-03
2017-02-06 | 2012 | Army National Guard | 240017 |  | 2012-08-29 | 2012-09-11 | The Whiting-Turner Contracting Company | 001B3400152 | 12611000 | 11938000 | 2014-09-22 | 2016-11-25
2017-02-06 | 2015 | Army National Guard | 240165 |  | 2015-08-17 | 2015-09-23 | Harkins Builders | 001B6400136 | 16496000 | 12488000 | 2017-10-29 | 2017-12-30
2017-02-06 | 2016 | Army National Guard | 240173 |  | 2016-08-10 | 2016-09-28 | Harkins Builders | 1521010362 | 13800000 | 13763000 | 2018-04-06 | 2018-04-06
2017-02-06 | 2011 | Army National Guard | 240186 |  | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | N40080-10-D-0498 | 5480000 | 5592000 | 2013-06-15 | 2014-11-21
2017-02-06 | 2012 | Army National Guard | 240187 |  | 2012-07-23 | 2012-09-11 | Harkins Builders | 001B3400154 | 10296000 | 8277000 | 2014-09-22 | 2015-03-20
2017-02-06 | 2012 | Army National Guard | 240193 |  | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 001B3400155 | 9280000 | 10770000 | 2014-09-22 | 2016-06-01
2017-02-06 | 2013 | Army National Guard | 240194 |  | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 3000000 | 1922000 | 2014-09-22 | 2016-03-29
2017-02-06 | 2013 | Army National Guard | 250065 |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279000 | 21257000 | 2015-07-30 | 2017-05-17
2017-02-06 | 2014 | Army National Guard | 250095 |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000000 | 20747000 | 2016-11-01 | 2017-01-16
2017-02-06 | 2013 | Army National Guard | 250196 |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District | W912W3-11-D-0069 | 2000000 | 1881000 | 2013-12-01 | 2013-12-01
2017-02-06 | 2014 | Army National Guard | 260051 |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000000 | 17710000 | 2016-10-01 | 2016-10-01
2017-02-06 | 2014 | Army National Guard | 270014 |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000000 | 18423000 | 2016-04-15 | 2016-11-01
2016-12-06 | 2013 | Army National Guard | 270236 |  | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. | 67879 | 12783000 | 13807000 | 2015-10-01 | 2016-06-30
2017-02-06 | 2014 | Army National Guard | 280272 |  | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB22-14-C-0003-S | 4500000 | 4798000 | 2016-04-30 | 2016-12-01
2017-02-06 | 2016 | Army National Guard | 280327 |  | 2016-09-08 | 2016-09-21 | Orocon Construction LLC | NGB22-16-C-0005-S | 40000000 | 33927000 | 2019-06-28 | 2019-06-28
2017-02-06 | 2014 | Army National Guard | 280423 |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000000 | 2829000 | 2016-11-30 | 2016-11-30
2017-02-06 | 2016 | Army National Guard | 281501 |  | 2016-09-14 | 2016-09-26 | HANCO General Contractors | NGB22-16-C-0008-S | 12800000 | 11910000 | 2018-02-09 | 2018-02-09
2017-02-06 | 2014 | Army National Guard | 290191 |  | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01 | 6834000 | 7852000 | 2015-06-26 | 2016-05-09
2017-02-06 | 2014 | Army National Guard | 290221 |  | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 4399000 | 4494000 | 2015-10-06 | 2015-10-06
2017-02-06 | 2015 | Army National Guard | 300128 |  | 2015-04-14 | 2015-04-20 | Swank Enterprises - Valier | W9124V-08-2-2001 | 38000000 | 28271000 | 2017-05-13 | 2017-05-30
2017-02-06 | 2015 | Army National Guard | 300216 |  | 2015-09-03 | 2015-09-19 | Golden Eagle Construction INC | W9124V-15-2-2001 | 2600000 | 2694000 | 2017-06-24 | 2017-01-31
2017-02-06 | 2016 | Army National Guard | 320075 |  | 2016-09-01 | 2016-09-08 | State Public Works Board | W9124X-15-2-2001 | 8000000 | 6406000 | 2017-06-23 | 2017-07-22
2017-02-06 | 2012 | Army National Guard | 320141 |  | 2015-10-01 | 2015-10-19 | Senate Builders & Const Manager | SPWB-09-C-14-109740 | 2000000 | 702000 | 2017-06-23 | 2017-07-15
2017-02-06 | 2013 | Army National Guard | 330053 |  | 2015-12-07 | 2016-01-19 | JCN Construction Co., Inc. | W912TF-14-D-0502 | 1900000 | 1847000 | 2017-02-15 | 2017-02-15
2017-02-06 | 2013 | Army National Guard | 340110 |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885000 | 33138000 | 2016-02-12 | 2017-02-10
2017-02-06 | 2013 | Army National Guard | 340124 |  | 2016-09-23 | 2016-09-28 | USPFO - NJ | W912KN-13-2-2001 | 3390000 | 2870000 | 2017-09-23 | 2018-01-17
2017-02-06 | 2013 | Army National Guard | 340126 |  | 2016-03-17 | 2016-07-06 | Ranco Construction, Inc. | W912KN-16-C-0002 | 4842000 | 4801000 | 2017-07-06 | 2017-07-06
2017-02-06 | 2013 | Army National Guard | 340127 |  | 2016-09-23 | 2016-09-30 | USPFO - NJ | W912KN-13-2-2004 | 3632000 | 4118000 | 2017-09-23 | 2017-09-23
2017-02-06 | 2013 | Army National Guard | 340128 |  | 2016-03-17 | 2016-07-06 | Ranco Construction, Inc. | W912KN-16-C-0002 | 5036000 | 4986000 | 2017-07-06 | 2017-07-06
2016-10-07 | 2013 | Army National Guard | 340129 |  | 2016-09-23 | 2016-09-29 | USPFO - NJ | W912KN-13-2-2006 | 1937000 | 2028000 | 2017-03-13 | 2017-03-13
2017-02-06 | 2013 | Army National Guard | 340129 |  | 2016-09-23 | 2016-10-11 | Ranco Construction, Inc. | W912KN-13-D-0008 0009 | 1937000 | 2039000 | 2017-03-13 | 2017-03-13
2017-02-06 | 2015 | Army National Guard | 350029 |  | 2016-02-19 | 2016-05-26 | White Sands Construction Inc. | W912J3-13-2-2001 | 5000000 | 5962000 | 2018-01-01 | 2018-01-01
2017-02-06 | 2013 | Army National Guard | 360139 |  | 2015-09-02 | 2015-10-27 | Darland Construction Inc. (GC) Global Electrical Contracting of Westchester, Inc. (EC) S & O Construction Services, Inc (HC) S & L Plumbing & Heating Corp (PC) | 45011 (GC)45011(EC) 45011 (PC) 45011 (HC) | 23213000 | 21704000 | 2017-12-30 | 2017-06-30
2017-02-06 | 2014 | Army National Guard | 360161 |  | 2014-09-17 | 2014-09-30 | Rockmore Contracting Corp (GC) Global Electrical Contracting of Westchester, Inc (EC) AWL Industries, Inc (HC) Eastern Plumbing & Mechanical Contracting, Inc. (PC) | 44573 (GC) 44573 (EC) 44573 (HC) 44573 (PC) | 34814000 | 35059000 | 2016-09-29 | 2017-05-03
2017-02-06 | 2013 | Army National Guard | 361103 |  | 2015-09-03 | 2015-09-15 | Arold Construction Co., Inc (GC) Global Electrical Contracting of Westchester, Inc (EC) S & O Construction Services, Inc. (HC) S & O Construction Services, Inc. (PC) | 44897 (GC) 44897 (EC) 44897 (HC) 44897 (PC) | 6700000 | 6611000 | 2016-11-05 | 2017-01-31
2016-12-06 | 2013 | Army National Guard | 380053 |  | 2014-08-18 | 2014-09-24 | Smithco Inc. | AGND14-52 | 1194000 | 2000000 | 2015-10-30 | 2015-12-11
2016-12-06 | 2013 | Army National Guard | 380053 | 87 | 2014-08-18 | 2014-09-24 | Peterson Mechanical, Inc. | AGND14-53 | 468000 |  | 2015-10-30 | 2015-12-11
2016-12-06 | 2013 | Army National Guard | 380053 | 88 | 2014-08-18 | 2014-09-24 | Grotberg Electrical, Inc. | AGND14-54 | 311000 |  | 2015-10-30 | 2015-12-11
2017-02-06 | 2015 | Army National Guard | 380073 |  | 2015-03-31 | 2015-06-15 | Strata Corp. | AGND15-18 | 3811000 | 12765000 | 2017-06-30 | 2017-07-18
2017-02-06 | 2015 | Army National Guard | 380073 | 135 | 2015-03-31 | 2015-06-15 | T.F. Powers Construction Co. | AGND15-19 | 6048000 |  | 2017-06-30 | 2017-07-18
2017-02-06 | 2015 | Army National Guard | 380073 | 136 | 2015-03-31 | 2015-06-15 | Manning Mechanical Inc. | AGND15-20 | 1421000 |  | 2017-06-30 | 2017-07-18
2017-02-06 | 2015 | Army National Guard | 380073 | 137 | 2015-03-31 | 2015-06-15 | Scott's Electric Inc. | AGND15-21 | 844000 |  | 2017-06-30 | 2017-07-18
2017-02-06 | 2016 | Army National Guard | 390290 |  | 2016-04-07 | 2016-04-28 | Leidos Engineering, LLC | W90FYQ-09-D-0006 | 3300000 | 3791403 | 2018-05-18 | 2018-05-18
2017-02-06 | 2014 | Army National Guard | 390292 |  | 2014-04-04 | 2014-09-04 | Rock Industries, Inc. | W91364-13-D-0003 | 5200000 | 5127000 | 2016-07-02 | 2016-10-15
2017-02-06 | 2013 | Army National Guard | 400066 |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29197000 | 28897000 | 2014-10-01 | 2017-09-30
2017-02-06 | 2012 | Army National Guard | 410026 |  | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 410026D002 | 13800000 | 13466000 | 2013-12-28 | 2014-03-20
2017-02-06 | 2016 | Army National Guard | 410301 |  | 2016-06-14 | 2016-07-13 | Fortis Construction Inc. | 410301D002 | 16500000 | 15769000 | 2018-01-10 | 2018-01-10
2017-02-06 | 2014 | Army National Guard | 420051 |  | 2014-07-09 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 33932000 | 35749000 | 2016-04-22 | 2017-07-06
2017-02-06 | 2013 | Army National Guard | 420533 |  | 2015-07-17 | 2015-09-17 | ImbuTec | W912KC-11-D-0004 | 2400000 | 2637000 | 2016-06-17 | 2017-04-28
2017-02-06 | 2014 | Army National Guard | 430070 |  | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600000 | 45820000 | 2015-05-30 | 2016-11-01
2017-02-06 | 2013 | Army National Guard | 430081 |  | 2013-06-27 | 2013-09-26 | RB Construction Group Inc. | W912LR-13-C-0001 | 18294000 | 17879000 | 2015-09-18 | 2016-02-05
2017-02-06 | 2013 | Army National Guard | 430803 |  | 2015-08-06 | 2015-09-15 | OSSAM Construction, Inc. | NGB70-15-C-0021 | 14218000 | 12866000 | 2017-03-25 | 2018-04-08
2017-02-06 | 2011 | Army National Guard | 440009 |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 19316000 | 21433000 | 2014-04-17 | 2015-03-31
2017-02-06 | 2013 | Army National Guard | 440053 |  | 2014-08-15 | 2015-01-06 | J J Cardosi, Inc | W912LD-11-D-0016 | 1032000 | 1203000 | 2015-11-01 | 2016-10-31
2017-02-06 | 2014 | Army National Guard | 450131 |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | State Contract # 4600406465 | 13000000 | 12997000 | 2017-04-06 | 2017-07-06
2016-09-07 | 2014 | Army National Guard | 450131 |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | State Contract # 46000406465 | 13000000 | 12632000 | 2017-04-06 | 2017-07-06
2016-09-07 | 2014 | Army National Guard | 450283 |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | State Contract # 46000406370 | 13000000 | 12552000 | 2017-04-06 | 2017-05-06
2017-02-06 | 2014 | Army National Guard | 450283 |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | State Contract # 4600406370 | 13000000 | 12552000 | 2017-04-06 | 2017-07-06
2017-02-06 | 2010 | Army National Guard | 450353 |  | 2010-09-23 | 2010-09-24 | Hendrick Construction, Inc. | State Contract # 4600114576 | 26781000 | 27304000 | 2012-08-18 | 2016-06-30
2016-09-07 | 2010 | Army National Guard | 450353 |  | 2010-09-23 | 2010-09-24 | Hendrick Construction | State Contract # 460114576 | 26781000 | 27304000 | 2012-08-18 | 2016-06-30
2017-02-06 | 2012 | Army National Guard | 450403 |  | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. | State Contract # 4600277403 | 4096000 | 4255000 | 2014-01-08 | 2014-04-30
2017-02-06 | 2014 | Army National Guard | 480243 |  | 2014-02-25 | 2015-09-28 | USPFO - TX | W912L1-15-0023 | 14270000 | 14697000 | 2017-06-09 | 2017-07-08
2016-09-07 | 2016 | Army National Guard | 500079 |  | 2016-02-22 | 2016-03-22 | Spates Construction, Inc. | 00000 | 7900000 | 8353000 | 2017-03-31 | 2017-03-31
2017-02-06 | 2016 | Army National Guard | 500079 |  | 2016-02-22 | 2016-03-22 | Spates Construction, Inc. | State Contract # 30971 | 8030000 | 8353000 | 2017-03-31 | 2017-03-31
2017-02-06 | 2016 | Army National Guard | 510065 |  | 2016-06-01 | 2016-06-24 | S. B. Ballard Construction Company | PC#123-18108-000 | 29000000 | 27591000 | 2018-03-18 | 2018-03-26
2017-02-06 | 2012 | Army National Guard | 510307 |  | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | W912LQ-13-C-0001 | 8316000 | 8937000 | 2014-10-09 | 2015-02-27
2017-02-06 | 2013 | Army National Guard | 530015 |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | W912DW-13-C-0044 | 33853000 | 31449000 | 2015-08-20 | 2016-03-10
2017-02-06 | 2013 | Army National Guard | 530035 |  | 2014-08-15 | 2014-08-20 | Absher Construction | 2013-295 G(2-1) | 26000000 | 23942000 | 2016-06-30 | 2016-09-21
2017-02-06 | 2013 | Army National Guard | 540075 |  | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734000 | 15603000 | 2015-09-11 | 2015-11-29
2017-02-06 | 2013 | Army National Guard | 550142 |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673000 | 9634000 | 2014-10-01 | 2015-06-15
2017-02-06 | 2017 | Army National Guard | 560084 |  | 2016-10-31 | 2017-02-03 | Layton Construction Company, Inc. | 17042027901 | 21000000 | 19388000 | 2018-04-30 | 2018-04-30
2017-01-31 | 2014 | Army Reserve | 65277 |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 11895000 | 13499000 | 2015-09-30 | 2017-02-13
2017-01-31 | 2012 | Army Reserve | 67466 |  | 2012-05-16 | 2012-09-18 | Continental Casualty Company | W912QR-12-C-0055 | 16212000 | 16472000 | 2014-03-19 | 2017-02-28
2017-01-31 | 2013 | Army Reserve | 67652 |  | 2014-05-06 | 2015-03-31 | Cox Construction Co. | W912QR-15-C-0007 | 24044000 | 24557000 | 2017-02-12 | 2017-04-03
2017-01-31 | 2013 | Army Reserve | 67659 |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21779000 | 24339000 | 2015-11-04 | 2016-11-28
2017-01-31 | 2015 | Army Reserve | 67661 |  | 2015-12-01 | 2016-03-01 | Structural Associates, Inc. | W912QR-16-C-0009 | 20118000 | 20197000 | 2018-03-08 | 2018-03-08
2017-01-31 | 2014 | Army Reserve | 67663 |  | 2014-08-01 | 2015-08-28 | Sheffield Korte Joint Venture | W912QR-15-C-0027 | 21428000 | 21428000 | 2017-09-06 | 2018-09-18
2017-01-31 | 2012 | Army Reserve | 67673 |  | 2012-02-14 | 2012-05-15 | Hunt Construction Group | W912QR-12-C-0029 | 44568000 | 48560000 | 2015-01-29 | 2015-07-27
2017-01-31 | 2012 | Army Reserve | 67681 |  | 2016-04-14 | 2016-08-25 | S&S - EXCEL CONSTRUCTORS JV | W912QR-16-C-0019 | 12078000 | 12078000 | 2018-01-05 | 2018-01-05
2017-01-31 | 2013 | Army Reserve | 67705 |  | 2015-02-13 | 2015-09-24 | Korte Construction Company | W912QR-15-C-0035 | 18104000 | 20653000 | 2017-09-07 | 2017-09-07
2017-01-31 | 2012 | Army Reserve | 67709 |  | 2016-04-11 | 2016-08-04 | J&J Contractors, Inc. | W912QR-16-C-0015 | 18542000 | 18542000 | 2018-03-23 | 2018-03-23
2017-01-31 | 2013 | Army Reserve | 67715 |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31523000 | 32775000 | 2016-01-15 | 2016-12-30
2017-01-31 | 2013 | Army Reserve | 68077 |  | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890000 | 8263000 | 2016-05-30 | 2017-03-23
2017-01-31 | 2011 | Army Reserve | 69421 |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4504000 | 4564000 | 2014-03-21 | 2017-08-30
2017-01-31 | 2011 | Army Reserve | 69562 |  | 2014-12-17 | 2015-09-10 | Blueridge General Inc | W912QR-15-C-0030 | 25135000 | 26003000 | 2017-05-10 | 2017-09-11
2017-01-31 | 2011 | Army Reserve | 69562 |  | 2014-10-17 | 2014-11-14 | Crossroads-Sergent Construction JV | W912QR-13-D-0026 | 1720000 | 1920000 | 2015-10-20 | 2017-02-15
2017-01-31 | 2013 | Army Reserve | 71482 |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56039000 | 61973000 | 2016-05-17 | 2017-02-28
2017-01-31 | 2014 | Army Reserve | 71768 |  | 2015-08-20 | 2015-11-04 | Eastern Construction & Electric, Inc. | W912QR-16-C-0003 | 6433000 | 6815000 | 2017-05-12 | 2017-04-28
2017-01-31 | 2014 | Army Reserve | 71769 |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653000 | 4682000 | 2016-04-09 | 2016-10-18
2017-01-31 | 2014 | Army Reserve | 71900 |  | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129000 | 22862000 | 2016-11-01 | 2017-03-17
2017-01-31 | 2015 | Army Reserve | 71901 |  | 2015-05-26 | 2016-01-21 | Hal Hays Construction, Inc. | W912QR-16-C-0006 | 18508000 | 25459000 | 2018-02-20 | 2018-03-22
2017-01-31 | 2014 | Army Reserve | 71903 |  | 2014-07-28 | 2016-07-06 | David Boland, Inc. | W912QR-16-C-0013 | 17277000 | 17277000 | 2018-07-01 | 2018-07-01
2017-01-31 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2016-06-30 | AAECON General Contracting LLC | W912QR-14-D-0025 | 2520000 | 2573000 | 2016-12-12 | 2016-12-12
2016-10-31 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19101000 | 19893000 | 2015-06-08 | 2016-03-02
2017-01-31 | 2014 | Army Reserve | 72284 |  | 2014-08-13 | 2014-09-30 | Bara Infoware Inc. | W912QR-14-C-0053 | 16187000 | 16351000 | 2016-05-22 | 2017-06-14
2017-01-31 | 2015 | Army Reserve | 72291 |  | 2015-05-01 | 2015-09-30 | Korte Construction Company | W912QR-15-C-0042 | 13283000 | 13627000 | 2017-08-28 | 2017-08-28
2017-01-31 | 2015 | Army Reserve | 77151 |  | 2016-04-05 | 2016-09-29 | Boro Developers, Inc. d.b.a Boro Construction | W912QR-16-C-0024 | 19988000 | 19988000 | 2018-09-13 | 2018-09-13
2017-01-31 | 2015 | Army Reserve | 77228 |  | 2015-08-11 | 2016-01-28 | Blinderman Construction | W912QR-16-C-0007 | 21311000 | 21311000 | 2018-02-16 | 2018-02-16
2017-01-31 | 2015 | Army Reserve | 81959 |  | 2015-03-06 | 2015-07-17 | ETD-TCG, LLC with RSP Architects | W912QR-15-C-0018 | 5215000 | 5332000 | 2016-12-09 | 2017-03-31
2017-01-31 | 2015 | Army Reserve | 85812 |  | 2015-08-11 | 2015-09-30 | Cox Construction Co. | W912QR-15-C-0044 | 21672000 | 21747000 | 2017-10-02 | 2017-11-16
2016-12-14 | 2016 | DLA Defense Automation and Production Service | DSFF1501 |  | 2016-08-01 | 2016-09-30 | PER IMETER SECURITY PARTNERS LLC | W912DY-14-D-0006 | 4249000 |  | 2017-10-17
2017-04-14 | 2016 | DLA Defense Automation and Production Service | DESC1607 |  | 2016-06-24 | 2016-09-16 | W.F. Magann Corporation | W91236-16-R-0008-0005 | 20646000 | 20646000 | 2019-10-12 | 2019-12-12
2016-09-14 | 2012 | DLA Defense Distribution Center | DDCX1203 |  | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 15198000 | 174423737 | 2016-05-05 | 2017-05-31
2016-09-14 | 2013 | DLA Defense Distribution Center | DDCX1301 |  | 2014-05-15 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 12049430 | 12394223 | 2016-04-28 | 2017-03-24
2016-09-14 | 2013 | DLA Defense Distribution Center | DDCX1303 |  | 2013-06-13 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9658000 | 10721858 | 2016-01-02 | 2016-10-27
2017-03-30 | 2014 | DLA Defense Distribution Center | DDCX1309 |  | 2016-06-30 | 2016-09-27 | Belt Built CFM Construction Services JV, LLC | W912DR-16-C-0049 / 35958356 | 2597000 | 2597000 | 2016-11-18 | 2018-02-20
2017-04-14 | 2014 | DLA Defense Distribution Center | DDCX1404 |  | 2014-02-11 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 32930000 | 33000000 | 2016-02-29 | 2017-06-09
2017-03-20 | 2015 | DLA Defense Distribution Center | DESC1606 |  | 2015-09-01 | 2015-11-16 | MEB General Contractors Inc | 1234 | 36443425 | 37147206 | 2018-07-01 | 2018-07-01
2016-06-07 | 2014 | DLA Defense Distribution Center | DSFH1401 | DSFH14U2 | 2015-01-28 | 2015-06-02 | Hako Plumbing, Inc. | N62742-15-C-1310B | 3000000 | 3000000 | 2016-10-14 | 2017-01-17
2017-04-14 | 2013 | DLA Defense Energy Support Center | DESC 1306 |  | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378000 | 68006493 | 2017-10-14 | 2017-10-14
2017-04-14 | 2015 | DLA Defense Energy Support Center | DESC 1463 |  | 2015-07-15 | 2015-09-30 | Structural Asspcoates Omc. | W9128F-15-C-0032 | 8518820 | 8518820 | 2017-02-17 | 2017-02-01
2017-04-14 | 2014 | DLA Defense Energy Support Center | DESC 1509 |  | 2015-07-27 | 2015-09-23 | CB&I Federal Contractors | N39430-15-D-1632 | 4882257 | 4882257 | 2016-12-30 | 2017-01-31
2016-06-08 | 2012 | DLA Defense Energy Support Center | DESC0704 |  | 2012-03-06 | 2012-03-29 | Structural Associates | N62473-13C-4213 | 15512000 | 16393973 | 2015-03-11 | 2015-07-01
2016-05-09 | 2010 | DLA Defense Energy Support Center | DESC0907 |  | 2009-12-17 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844000 | 19618992 | 2012-12-16 | 2015-12-30
2016-05-09 | 2012 | DLA Defense Energy Support Center | DESC1102 |  | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 25181000 | 26338000 | 2015-12-10 | 2016-06-15
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1107 |  | 2014-02-28 | 2014-06-12 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4056000 | 4470000 | 2015-08-11 | 2015-10-29
2016-05-09 | 2014 | DLA Defense Energy Support Center | DESC11U2 |  | 2014-03-28 | 2014-04-24 | Gilbane Federal | N62583-09-D-0129 | 1994000 | 2042165 | 2015-11-15 | 2016-04-08
2016-05-09 | 2013 | DLA Defense Energy Support Center | DESC1203 |  | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366000 | 31974716 | 2015-09-28 | 2016-04-16
2017-03-20 | 2012 | DLA Defense Energy Support Center | DESC1205 |  | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453000 | 28613000 | 2015-03-24 | 2015-08-30
2017-03-20 | 2013 | DLA Defense Energy Support Center | DESC1301 |  | 2014-11-13 | 2015-08-28 | Rockford Corporation | W912QR-15-C-0026 | 33997000 | 35316109 | 2017-03-30 | 2017-04-10
2017-03-20 | 2013 | DLA Defense Energy Support Center | DESC1303 |  | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364400 | 65306000 | 2016-02-06 | 2017-12-29
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1304 |  | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513000 | 20077000 | 2016-12-07 | 2017-03-07
2016-05-09 | 2013 | DLA Defense Energy Support Center | DESC1305 |  | 2013-07-07 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800000 | 1800139 | 2015-04-11 | 2015-06-23
2017-04-14 | 2015 | DLA Defense Energy Support Center | DESC1353 |  | 2015-03-13 | 2015-08-09 | Middle Eastern Builders | W912HN-12C-0016 | 15685100 | 15685100 | 2018-05-23 | 2018-09-21
2016-12-14 | 2014 | DLA Defense Energy Support Center | DESC13S2 |  | 2014-08-20 | 2015-01-27 | Reliable Contracting Group, LLC | W91278-15-C-0005 | 8456000 | 9357755 | 2016-05-06 | 2016-11-22
2017-04-14 | 2013 | DLA Defense Energy Support Center | DESC13S3 |  | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961000 | 2290000 | 2015-10-28 | 2015-10-28
2016-05-09 | 2013 | DLA Defense Energy Support Center | DESC13S4 |  | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322000 | 1538906 | 2014-08-03 | 2016-04-24
2016-09-15 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2015-02-27 | 2015-04-07 | Nippo Corporation | W912HV-15-C-005 | 32623000 | 32838656 | 2017-08-23 | 2017-10-30
2016-05-09 | 2015 | DLA Defense Energy Support Center | DESC1404 |  | 2015-04-23 | 2016-01-21 | Gilbane Federal | N39430-15-D-1634-JM01 | 9960000 | 9960000 | 2017-11-13 | 2017-11-13
2016-12-14 | 2014 | DLA Defense Energy Support Center | DESC1405 |  | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749000 | 7715765 | 2016-04-22 | 2016-04-22
2017-03-20 | 2014 | DLA Defense Energy Support Center | DESC1407 |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP-15-C-003 | 21288300 | 21724000 | 2017-02-01 | 2017-04-16
2017-04-14 | 2015 | DLA Defense Energy Support Center | DESC1459 |  | 2015-02-26 | 2015-08-12 | CB&I Federal Services LLC | W912HN-15-C-0017 | 5949000 | 5949000 | 2017-05-02 | 2017-08-26
2017-03-20 | 2014 | DLA Defense Energy Support Center | DESC1501 |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637000 | 9148898 | 2016-05-23 | 2017-06-30
2017-04-14 | 2014 | DLA Defense Energy Support Center | DESC1502 |  | 2014-06-17 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0001 | 32060100 | 32188673 | 2017-05-23 | 2017-07-05
2017-04-14 | 2014 | DLA Defense Energy Support Center | DESC1502 | 43 | 2014-06-17 | 2015-05-04 | Rockford Corporation | W912BV-15-C-0017 | 4556371 | 4645254 | 2016-10-23 | 2017-04-29
2016-12-15 | 2014 | DLA Defense Energy Support Center | DESC1503 |  | 2014-10-03 | 2015-04-23 | Tokyo Construction Co., Ltd. | W912HV-15-C-0007 | 6244000 | 6463000 | 2016-11-05 | 2017-01-31
2016-12-14 | 2014 | DLA Defense Energy Support Center | DESC1504 |  | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0011 | 13407000 | 13503915 | 2016-04-08 | 2016-10-07
2017-04-14 | 2015 | DLA Defense Energy Support Center | DESC1508 |  | 2016-03-31 | 2017-03-30 | CB&I Federal Services, LLC | N62473-15-R-0001-0008 | 54095271 | 54095271 | 2020-03-30 | 2020-03-30
2017-04-14 | 2015 | DLA Defense Energy Support Center | DESC1510 |  | 2015-02-02 | 2015-08-20 | Graco Construction Inc. | W912QR-15-C-0025 | 32592465 | 33070092 | 2018-04-07 | 2018-10-05
2016-10-14 | 2015 | DLA Defense Energy Support Center | DESC1515 |  | 2015-02-12 | 2015-08-31 | MEB General Contractors Inc. | N40085-15-C-0022 | 22944000 | 22944000 | 2017-06-26 | 2017-06-26
2017-04-14 | 2015 | DLA Defense Energy Support Center | DESC1551 |  | 2014-10-29 | 2015-08-25 | Hensel Phelps Constuction co | N62742-15-C-1308 | 42823800 | 44417331 | 2017-09-25 | 2017-12-30
2017-04-14 | 2014 | DLA Defense Energy Support Center | DESC1557 |  | 2014-07-28 | 2015-05-14 | Cape Env. Mgmt. | W9128F-10-D-0075 | 3471000 | 3578000 | 2016-10-10 | 2016-11-16
2016-05-09 | 2015 | DLA Defense Energy Support Center | DESC1606 |  | 2014-12-23 | 2015-11-16 | MEB General Contractors | N69450-16-C-1604 | 36565000 | 337193000 | 2017-11-06 | 2017-11-06
2017-03-23 | 2016 | DLA Defense Energy Support Center | DESC1613 |  | 2016-03-28 | 2016-09-28 | NOVA Group Inc | W912PL-16-C-0026 | 32813000 | 32813000 | 2019-10-04 | 2019-10-04
2017-04-14 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | w | 20577000 | 20577000 | 2019-01-07 | 2019-01-07
2017-04-14 | 2016 | DLA Defense Energy Support Center | DESC1710 |  | 2016-06-15 | 2016-09-20 | RELIABLE CONTRACTING GROUP, LLC | W912HN-16-C-0017 / 43104748 | 9568000.28 | 9568000.28 | 2018-04-26 | 2018-07-25
2017-03-20 | 2015 | DLA Defense National Stockpile Center | DESC1507 |  | 2015-02-02 | 2015-09-30 | Structural Associates Inc | W9128F-15-C-0032 | 17178089 | 17178089 | 2017-03-23
2017-03-30 | 2016 | DLA Defense Supply Center Philadelphia | DSCP1501 |  | 2016-03-11 | 2016-09-16 | Daniel J. keating Company | N40085-16-C-3037 | 46845550 | 47048123 | 2019-03-30 | 2019-03-30
2016-12-14 | 2014 | DLA Defense Supply Center Richmond | DSCR1401 |  | 2015-02-13 | 2015-06-12 | Hensel Phelps Constuction Co | W91236-15-C-0045 | 71969000 | 74955000 | 2018-08-25 | 2018-08-25
2017-01-31 | 2008 | Defense Health Agency | 47298 |  | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110000 | 282778000 | 2013-07-23 | 2016-03-15
2017-01-31 | 2012 | Defense Health Agency | 51969 |  | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | W9126G-12-C-0050 | 28291000 | 31949000 | 2014-10-30 | 2016-08-25
2017-01-31 | 2008 | Defense Health Agency | 52332 |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929000 | 26866000 | 2012-05-15 | 2012-08-06
2017-01-31 | 2009 | Defense Health Agency | 55918 |  | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034000 | 13672000 | 2011-02-07 | 2011-06-22
2017-01-31 | 2007 | Defense Health Agency | 58395 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657000 | 2657000 | 2008-06-13 | 2008-06-08
2017-01-31 | 2007 | Defense Health Agency | 58395 | 58395-01 | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472000 | 1472000 | 2009-02-15 | 2009-02-13
2017-01-31 | 2007 | Defense Health Agency | 58395 | 58395-02 | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706000 | 706000 | 2010-04-13 | 2010-04-13
2017-01-31 | 2007 | Defense Health Agency | 58395 | 58395-03 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465000 | 2465000 | 2009-07-24 | 2009-07-24
2017-01-31 | 2007 | Defense Health Agency | 58395 | 58395-04 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 2866000 | 2866000 | 2011-05-06 | 2013-10-31
2017-01-31 | 2007 | Defense Health Agency | 58395 | 58395-05 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 15736000 | 16161000 | 2014-05-31 | 2017-09-01
2017-01-31 | 2007 | Defense Health Agency | 58395 | 63418 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 131264000 | 138491000 | 2014-05-31 | 2017-09-01
2017-01-31 | 2007 | Defense Health Agency | 58395 | 63419 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 185526000 | 185630000 | 2014-05-31 | 2017-09-01
2017-01-31 | 2007 | Defense Health Agency | 58395 | 63420 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 94000000 | 100180000 | 2014-05-31 | 2017-09-01
2017-01-31 | 2007 | Defense Health Agency | 58395 | 63420-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 496000 | 525000 | 2013-10-31 | 2014-01-02
2017-01-31 | 2007 | Defense Health Agency | 58395 | 65324 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 13497000 | 12893000 | 2014-05-31 | 2017-09-01
2017-01-31 | 2007 | Defense Health Agency | 58395 | 65324-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 638000 | 2013-10-31 | 2013-12-06
2017-01-31 | 2007 | Defense Health Agency | 58395 | 71101 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 66955000 | 90542000 | 2014-05-31 | 2017-09-01
2017-01-31 | 2007 | Defense Health Agency | 58395 | 71101-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 7750000 | 7676000 | 2017-03-31 | 2017-03-31
2017-01-31 | 2007 | Defense Health Agency | 58395 | 78210 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 601000 | 2014-05-31 | 2017-09-01
2017-01-31 | 2009 | Defense Health Agency | 59220 |  | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500000 | 29404000 | 2015-08-03 | 2015-09-11
2017-01-31 | 2010 | Defense Health Agency | 61401 |  | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075000 | 10119000 | 2013-01-10 | 2015-01-08
2017-01-31 | 2009 | Defense Health Agency | 62189 |  | 2008-10-27 | 2009-04-03 | Hensel-Phelps Const. Co. | W912BV-09-D-2016 | 47615000 | 51375000 | 2011-10-26
2017-01-31 | 2008 | Defense Health Agency | 63864 |  | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | W91DS-08-C-0019 | 27483000 | 35963000 | 2011-02-18 | 2012-12-01
2017-01-31 | 2009 | Defense Health Agency | 64156 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398000 | 17763000 | 2013-06-01 | 2015-06-10
2017-01-31 | 2012 | Defense Health Agency | 65030 |  | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co. | N40083 12 C 0001 | 5835000 | 6195000 | 2013-09-13 | 2014-08-08
2017-01-31 | 2010 | Defense Health Agency | 65270 |  | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133000 | 168571000 | 2014-10-15 | 2016-09-05
2017-01-31 | 2009 | Defense Health Agency | 65731 |  | 2009-01-07 | 2009-04-08 | Clark Construction Group, LLC | W912DR-09-C-0030 | 6887870 | 6758000 | 2010-08-08 | 2010-08-31
2017-01-31 | 2009 | Defense Health Agency | 65731 | 65731-01 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 12000000 | 12658000 | 2013-06-01 | 2015-06-10
2017-01-31 | 2009 | Defense Health Agency | 65731 | 67180 | 2009-01-07 | 2009-04-08 | Clark Construction Group, LLC | W912DR-09-C-0030 | 461470 | 436000 | 2010-08-08 | 2010-08-31
2017-01-31 | 2009 | Defense Health Agency | 65731 | 67180-01 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30
2017-01-31 | 2009 | Defense Health Agency | 65731 | 67180-02 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 100375000 | 103750000 | 2013-06-01 | 2015-06-10
2017-01-31 | 2009 | Defense Health Agency | 65731 | 67181 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 94608000 | 106045000 | 2013-06-01 | 2015-06-10
2017-01-31 | 2009 | Defense Health Agency | 65731 | 67182 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 37745000 | 2013-06-01 | 2015-06-10
2017-01-31 | 2011 | Defense Health Agency | 66588 |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 32103000 | 32103000 | 2016-05-30 | 2016-09-04
2017-01-31 | 2011 | Defense Health Agency | 66693 |  | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | W912GB-09-C-0029-NA | 34294000 | 34376000 | 2016-04-12 | 2016-05-23
2017-01-31 | 2011 | Defense Health Agency | 67949 |  | 2011-08-19 | 2012-02-14 | Rich Moe Enterprises, LLC | W912DR-12-C-0001 | 1701000 | 1701000 | 2013-04-02 | 2013-04-01
2017-01-31 | 2011 | Defense Health Agency | 67949 | 67949-01 | 2015-03-09 | 2015-09-18 | Edifice- Schlosser JV (Phase II) | W912DR-15-C-0025 | 660000 | 660000 | 2017-03-31 | 2017-03-31
2017-01-31 | 2011 | Defense Health Agency | 67951 |  | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308000 | 15641000 | 2014-07-08 | 2015-08-03
2017-01-31 | 2011 | Defense Health Agency | 67953 |  | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468000 | 3944000 | 2012-11-01 | 2014-05-30
2017-01-31 | 2008 | Defense Health Agency | 70235 |  | 2009-04-08 | 2009-09-28 | Turner Construction Company | W912HN-09-C-0045 | 230018000 | 275275000 | 2013-02-03 | 2014-05-19
2017-01-31 | 2012 | Defense Health Agency | 70351 |  | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400000 | 23770000 | 2014-06-23 | 2015-06-15
2017-01-31 | 2009 | Defense Health Agency | 70354 |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 159834000 | 204246000 | 2015-03-16 | 2017-06-29
2017-01-31 | 2012 | Defense Health Agency | 70438 |  | 2011-10-18 | 2012-05-14 | M.A. Mortenson Company | W912QR-12-C-0036 | 43466000 | 51711000 | 2015-02-21 | 2015-10-27
2017-01-31 | 2011 | Defense Health Agency | 70482 |  | 2010-11-19 | 2011-06-03 | McCarthy Building Companies, Inc. | W912HN-11-C-0007 | 23050000 | 25062000 | 2013-06-20 | 2013-12-04
2017-01-31 | 2012 | Defense Health Agency | 70597 |  | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | W91278-12-C-0028 | 8897000 | 9137000 | 2014-10-07 | 2014-10-07
2017-01-31 | 2013 | Defense Health Agency | 71317 |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744000 | 42643000 | 2016-12-30 | 2018-05-03
2016-10-31 | 2010 | Defense Health Agency | 71318 |  | 2009-10-28 | 2010-02-26 | JE Dunn Construction Company | W9126G-08-D-0057 | 22680000 | 23591000 | 2012-01-06
2017-01-31 | 2013 | Defense Health Agency | 71325 |  | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536000 | 47116000 | 2016-10-23 | 2017-03-27
2017-01-31 | 2012 | Defense Health Agency | 71408 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688000 | 18731000 | 2016-12-06 | 2018-03-05
2017-01-31 | 2012 | Defense Health Agency | 71503 |  | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Construction | N69450 12 C 0754 | 19096000 | 21083000 | 2014-09-09 | 2016-01-31
2017-01-31 | 2012 | Defense Health Agency | 71503 | 71503-01 | 2012-03-22 | 2016-08-25 | Surety Company | N69450 12 C 0754 | 1000 | 1000 | 2017-12-25 | 2017-12-29
2017-01-31 | 2013 | Defense Health Agency | 71507 |  | 2013-02-28 | 2013-12-18 | Turner Construction Company | N40080 14 C 0154 | 41408000 | 43375000 | 2015-10-15 | 2016-11-27
2017-01-31 | 2010 | Defense Health Agency | 71550 |  | 2010-06-16 | 2010-12-14 | Vinci Construction UK Ltd. | CT/INT21/13625 | 13425000 | 12421000 | 2012-08-10 | 2012-09-28
2017-01-31 | 2010 | Defense Health Agency | 71550 | 71550-01 | 2013-04-05 | 2013-06-15 | VolterFitzpatrick | DEUSF/13214 | 68000 | 68000 | 2013-08-30 | 2013-08-30
2017-01-31 | 2010 | Defense Health Agency | 71550 | 71550-02 | 2014-08-20 | 2014-08-25 | Vinci Facilities | CT/INT21/13625 | 69000 | 149000 | 2015-06-30 | 2016-06-30
2017-01-31 | 2016 | Defense Health Agency | 71642 |  | 2016-07-08 | 2016-09-30 | Butt Construction Co. | W912QR-15-D-0002-0014 | 6301000 | 6301000 | 2019-01-12 | 2019-01-12
2017-01-31 | 2013 | Defense Health Agency | 71679 |  | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture | W912DQ-13-C-4017 | 10687000 | 10505000 | 2015-02-19 | 2015-02-19
2017-01-31 | 2012 | Defense Health Agency | 72292 |  | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778000 | 44615000 | 2016-10-14 | 2017-03-15
2017-01-31 | 2015 | Defense Health Agency | 72414 |  | 2015-04-21 | 2015-09-25 | Gilbane Federal JV | W9127S-13-D-6000 | 14598000 | 14598000 | 2017-10-23 | 2017-10-23
2017-01-31 | 2013 | Defense Health Agency | 72419 |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co. Ltd. | W912UM-13-C-0025 | 22361000 | 22816000 | 2017-08-08 | 2018-08-07
2017-01-31 | 2010 | Defense Health Agency | 72430 |  | 2010-06-11 | 2010-08-19 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0005) | 41566000 | 45105000 | 2013-02-20 | 2013-11-19
2017-01-31 | 2010 | Defense Health Agency | 72430 | 72430-01 | 2010-06-11 | 2010-08-31 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0006) | 23216000 | 24153000 | 2012-02-26 | 2012-12-13
2017-01-31 | 2010 | Defense Health Agency | 72481 |  | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 7782000 | 11366000 | 2016-11-26 | 2017-11-13
2017-01-31 | 2010 | Defense Health Agency | 72481 | 72481-01 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-10-12
2017-01-31 | 2010 | Defense Health Agency | 72481 | 72481-02 | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488000 | 10635000 | 2012-07-05 | 2012-12-31
2017-01-31 | 2010 | Defense Health Agency | 72481 | 72481-03 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-10-17
2017-01-31 | 2010 | Defense Health Agency | 72481 | 72481-04 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960000 | 2800000 | 2015-08-27 | 2015-11-30
2017-01-31 | 2010 | Defense Health Agency | 72481 | 72481-05 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2015-09-16
2017-01-31 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G-11-P | 46000 | 46000 | 2011-11-01 | 2011-11-01
2017-01-31 | 2010 | Defense Health Agency | 72481 | 72786 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 69851000 | 72931000 | 2016-11-26 | 2017-11-13
2017-01-31 | 2010 | Defense Health Agency | 72481 | 76558 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 79914000 | 165839000 | 2016-11-26 | 2017-11-13
2017-01-31 | 2010 | Defense Health Agency | 72481 | 76558-01 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540000 | 657000 | 2014-10-24 | 2014-10-24
2017-01-31 | 2010 | Defense Health Agency | 72481 | 76558-02 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2015-08-27 | 2015-11-30
2017-01-31 | 2010 | Defense Health Agency | 72481 | 77251 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 68076000 | 68076000 | 2016-11-26 | 2017-11-13
2017-01-31 | 2010 | Defense Health Agency | 72481 | 77293 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 198148000 | 93144000 | 2016-11-26 | 2017-11-13
2017-01-31 | 2010 | Defense Health Agency | 72481 | 81407 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 225199000 | 85171000 | 2016-11-26 | 2017-11-13
2017-01-31 | 2010 | Defense Health Agency | 72481 | 81408 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 56858000 | 161072000 | 2016-11-26 | 2017-11-13
2017-01-31 | 2009 | Defense Health Agency | 72722 |  | 2011-07-01 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 71357000 | 95091000 | 2014-09-09 | 2015-04-17
2017-01-31 | 2009 | Defense Health Agency | 72722 | 72722-01 | 2011-03-07 | 2011-03-20 | A1 Tree Service | W912QR-11-C-0040-1 | 9600 | 9600 | 2011-04-01 | 2011-04-01
2017-01-31 | 2009 | Defense Health Agency | 72722 | 72722-02 | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp | W912QR-11-C-0027 | 5395000 | 5395000 | 2014-09-27 | 2015-03-18
2017-01-31 | 2009 | Defense Health Agency | 72722 | 72722-03 | 2015-07-10 | 2015-08-30 | Northview Enterprises | W912QR-14-D-0022-1 | 260000 | 260000 | 2016-06-01 | 2016-06-08
2017-01-31 | 2012 | Defense Health Agency | 72727 |  | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd. | CT/INT21/13487 | 11958000 | 11958000 | 2015-10-30 | 2016-01-06
2017-01-31 | 2011 | Defense Health Agency | 72752 |  | 2011-05-20 | 2011-09-28 | Skanska USA Building Inc. | W9126G-11-C-0053 | 80558000 | 102303000 | 2013-10-01 | 2016-09-02
2017-01-31 | 2012 | Defense Health Agency | 72754 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 76038000 | 82975000 | 2014-07-29 | 2016-09-02
2017-01-31 | 2012 | Defense Health Agency | 72754 | 80793-01 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22835000 | 2014-07-29 | 2016-09-02
2017-01-31 | 2013 | Defense Health Agency | 72808 |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703000 | 19873000 | 2015-03-16 | 2017-01-08
2017-01-31 | 2011 | Defense Health Agency | 73360 |  | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869000 | 19957000 | 2014-01-06 | 2014-10-07
2016-10-31 | 2009 | Defense Health Agency | 73599 |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178000 | 29302000 | 2015-01-02 | 2015-10-16
2016-11-30 | 2013 | Defense Health Agency | 73776 |  | 2012-11-15 | 2013-12-18 | Structural Associates Inc. | W91DS-14-C-0003 | 11163000 | 10901000 | 2016-01-06 | 2016-01-06
2017-01-31 | 2009 | Defense Health Agency | 74650 |  | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989000 | 550747000 | 2014-05-31 | 2015-11-04
2017-01-31 | 2009 | Defense Health Agency | 74650 | 74650-01 | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc | SP0600-08-C-8250 | 10225000 | 11445000 | 2012-02-25 | 2012-06-02
2017-01-31 | 2009 | Defense Health Agency | 74650 | 74650-02 | 2010-02-12 | 2010-03-08 | TTG Utilities, LP | W9126G-10-C-0032 | 301000 | 301000 | 2010-05-30 | 2010-06-30
2017-01-31 | 2009 | Defense Health Agency | 74650 | 74650-03 | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc. | W912DY-05-D-0011 | 1018000 | 1040000 | 2010-10-18 | 2010-10-05
2017-01-31 | 2009 | Defense Health Agency | 74650 | 74650-04 | 2010-04-11 | 2010-06-11 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0002 | 6304000 | 10156000 | 2012-01-11 | 2012-09-20
2017-01-31 | 2009 | Defense Health Agency | 74650 | 74650-05 | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0003 | 17290000 | 15383000 | 2012-06-29 | 2013-12-15
2017-01-31 | 2011 | Defense Health Agency | 75132 |  | 2013-06-14 | 2013-09-27 | Billy W. Jarrett Const Co. Inc. | N62470 13 MPS 0046 | 1797000 | 1834000 | 2014-10-15 | 2016-07-08
2017-01-31 | 2012 | Defense Health Agency | 76007 |  | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 16910000 | 2021-07-20 | 2022-12-30
2016-12-31 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 39993000 | 39993000 | 2020-12-30 | 2020-12-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 39993000 | 39993000 | 2020-12-30 | 2020-12-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 72662 | 2015-08-19 | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 120950000 | 120950000 | 2019-04-30 | 2020-09-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-01 | 2012-02-01 | 2012-03-15 | Joint Venture Bautra Baugesellschaft mbH / SRS Service GmbH | W912GB-10-C-0031, ABG4 P00023 | 265000 | 297000 | 2014-04-04 | 2014-04-04
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-02 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00030 | 694489 | 1653000 | 2014-10-29 | 2015-01-21
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-03 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00043 | 5321000 | 6545000 | 2016-04-30 | 2016-08-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-04 | 2012-02-01 | 2012-03-15 | Hermanns RTE Rohrleitungs- undd Tiefbau Erfurt GmbH | W912GB-10-C-0031, ABG4 P00062 | 5444000 | 5494000 | 2016-12-15 | 2017-12-15
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-05 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH (ABG4 P00033) | W912GB-10-C-0031, ABG4 P00033 | 141234 | 141238 | 2015-03-30 | 2015-05-01
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-06 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH | W912GB-10-C-0031, ABG4 P00031 | 17713 | 17713 | 2014-12-31 | 2014-12-31
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-07 | 2012-02-01 | 2012-03-15 | FRG/CREOS GmbH | W912GB-10-C-0031, ABG4 P00032 | 482902 | 482902 | 2014-10-16 | 2014-10-16
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-08 | 2012-02-01 | 2012-03-15 | FRG/Omexom GA Sud GmbH | W912GB-10-C-0031, ABG4 P00066 | 89440 | 89440 | 2016-10-30 | 2016-12-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB-10-C-0031 | 419000 | 419000 | 2016-12-15 | 2017-05-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-10 | 2012-02-01 | 2012-03-15 | FRG/Zeppelin STREIF Baulogistik GmbH | W912GB-10-C-0031, ABG4 P00039 | 5339748 | 5394000 | 2022-12-30 | 2022-12-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-11 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5339000 | 5339000 | 2022-12-30 | 2021-12-17
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-12 | 2012-02-01 | 2012-03-15 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, ABG4 P00058 | 2539000 | 2988000 | 2016-04-30 | 2017-01-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-13 | 2012-02-01 | 2012-03-15 | FRG/Deutsche Telekom Technik GmbH | W912GB-10-C-0031, ABG4 P00037 | 1000 | 1000 | 2014-12-31 | 2014-12-31
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-14 | 2012-02-01 | 2012-03-15 | FRG/ABG3 | W912GB-10-C-0031 | 5226000 | 5226000 | 2022-12-30 | 2022-12-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76007-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 22234000 | 22234000 | 2018-07-30 | 2018-10-30
2017-01-31 | 2012 | Defense Health Agency | 76007 | 76872 | 2015-08-19 | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 563112000 | 563112000 | 2021-12-08
2017-01-31 | 2014 | Defense Health Agency | 77000 |  | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR-15-C-0015 | 206445000 | 206802000 | 2019-02-19 | 2019-03-08
2017-01-31 | 2011 | Defense Health Agency | 77115 |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133000 | 48899000 | 2014-02-02 | 2014-07-18
2017-01-31 | 2012 | Defense Health Agency | 77154 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 131374000 | 139511000 | 2016-12-06 | 2018-03-05
2017-01-31 | 2012 | Defense Health Agency | 77154 | 81291 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 66430000 | 66479000 | 2016-12-06 | 2018-03-05
2017-01-31 | 2014 | Defense Health Agency | 77922 |  | 2014-02-25 | 2014-08-19 | Gilbane | W9127S-13-D-6000 DM01 | 45629000 | 46718000 | 2018-01-23 | 2018-01-23
2017-01-31 | 2013 | Defense Health Agency | 77979 |  | 2013-09-03 | 2014-03-27 | JE Dunn + HWA | W9127S-13-D-6001 DM01 | 45938000 | 47470000 | 2018-02-10 | 2018-05-08
2017-01-31 | 2013 | Defense Health Agency | 78143 |  | 2013-01-14 | 2013-08-22 | Blinderman Constr Co. | N40083 13 C 0003 | 14864000 | 14901000 | 2015-01-15 | 2017-07-28
2017-01-31 | 2013 | Defense Health Agency | 78144 |  | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354000 | 14791000 | 2015-03-17 | 2015-12-21
2017-01-31 | 2013 | Defense Health Agency | 78146 |  | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254000 | 7413000 | 2014-12-06 | 2015-11-23
2017-01-31 | 2016 | Defense Health Agency | 78150 |  | 2015-11-05 | 2016-08-08 | Caddell-Nan joint Venture | N62742 16 C 1312 | 79722000 | 79935000 | 2018-12-21 | 2019-01-15
2017-01-31 | 2012 | Defense Health Agency | 79554 |  | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200000 | 14457000 | 2014-02-22 | 2014-06-02
2017-01-31 | 2009 | Defense Health Agency | 79845 |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction Company | W9126G-08-D-0057 | 51133000 | 59456000 | 2014-11-06
2016-10-31 | 2011 | Defense Health Agency | 80093 |  | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc. | W9126G-09-D-0105 | 1698000 | 1982000 | 2013-11-14 | 2014-08-24
2016-12-31 | 2012 | Defense Health Agency | 80094 |  | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc. | W912BV-12-C-0030 | 1692000 | 1710000 | 2014-07-05 | 2014-12-12
2017-01-31 | 2013 | Defense Health Agency | 80306 |  | 2013-07-25 | 2013-09-12 | G-W Management Servicxes Inc. | N40080 10 D 0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25
2017-01-31 | 2013 | Defense Health Agency | 80306 | 80306-01 | 2014-03-15 | 2016-09-01 | Whiting Turner Contracting Co | N40080 16 C 0172 | 29435000 | 29435000 | 2017-12-10 | 2017-12-10
2017-01-31 | 2013 | Defense Health Agency | 80307 |  | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898000 | 4930000 | 2015-04-08 | 2017-03-28
2017-01-31 | 2013 | Defense Health Agency | 80308 |  | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947000 | 29019000 | 2016-02-12 | 2016-09-18
2017-01-31 | 2016 | Defense Health Agency | 80412 |  | 2016-01-27 | 2016-05-17 | Swinerton Builders | W9128A-16-C-0004 | 26084000 | 26179000 | 2017-12-08 | 2017-12-08
2017-01-31 | 2012 | Defense Health Agency | 80792 |  | 2012-06-18 | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service | W81W3G22363343 / 22443665 / 22443666 / 30793685 | 1600000 | 1690000 | 2013-05-31 | 2013-08-29
2017-01-31 | 2014 | Defense Health Agency | 80904 |  | 2014-01-30 | 2015-03-30 | Whiting Turner Contracting Co | N40080 15 C 0156 | 38490000 | 40120000 | 2017-02-07 | 2017-08-03
2017-01-31 | 2014 | Defense Health Agency | 80913 |  | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835000 | 15835000 | 2016-04-16 | 2017-03-10
2017-01-31 | 2014 | Defense Health Agency | 81340 |  | 2014-03-17 | 2014-06-30 | Gilbane | W9127S-13-D-6000 DY01 | 11289000 | 11568000 | 2016-07-28 | 2016-10-30
2017-01-31 | 2015 | Defense Health Agency | 81423 |  | 2015-03-20 | 2015-09-03 | JE Dunn Construction Company | W9127S-13-D-6001 | 33473000 | 33853000 | 2018-09-27 | 2018-10-18
2017-01-31 | 2014 | Defense Health Agency | 81436 |  | 2015-08-25 | 2016-03-17 | Contrack Watts Inc. | W912ER-11-D-0009-0012 | 24784000 | 24784000 | 2019-04-20 | 2019-04-20
2017-01-31 | 2015 | Defense Health Agency | 81627 |  | 2015-10-30 | 2016-03-11 | Orion Construction, Inc. | W912DW-16-C-0006 | 2062000 | 2183000 | 2017-11-14 | 2017-09-14
2017-01-31 | 2014 | Defense Health Agency | 81631 |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc. | W912HN-11-D-0043-0044 | 1436000 | 1438000 | 2016-02-01 | 2016-02-01
2017-01-31 | 2014 | Defense Health Agency | 81706 |  | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 1795000 | 1760000 | 2015-10-28 | 2015-12-11
2015-10-30 | 2013 | Defense Information Systems Agency | 13DISA01 |  | 2015-08-05 | 2015-08-19 | Bauamt Reutlingen | W912GB-15-C-011 | 2219820 | 2219820 | 2015-08-19 | 2016-12-31
2015-10-30 | 2014 | Defense Information Systems Agency | 14DISA01 | [5 empty] | 2615000 | 2615000
2015-10-30 | 2015 | Defense Information Systems Agency | 15DISA01 | [5 empty] | 1871000 | 1871000
2015-10-30 | 2015 | Defense Information Systems Agency | 15DISA01 | 1 |  |  |  |  | 745000 | 745000
2015-10-30 | 2015 | Defense Information Systems Agency | 15DISA02 | [5 empty] | 9600000 | 9600000
2015-10-30 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000001 |  | 2014-06-16 | 2014-09-23 | Arriba | N4008-11-D-0496-0050/N0080-11-D-0495-0016 | 15186000 | 13358000 | 2016-03-02 | 2016-06-30
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000002
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000003
2015-08-31 | 2013 | Defense Intelligence Agency | DIA13000001
2017-02-07 | 2010 | DoD Education Activity | AM 856 07 |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764000 | 20571550 | 2013-12-14 | 2014-07-09
2017-02-07 | 2012 | DoD Education Activity | AM00023 |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987000 | 34674432 | 2015-12-11 | 2016-05-30
2017-02-07 | 2012 | DoD Education Activity | AM00023 | 28 | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2015-12-11 | 2016-05-30
2017-02-07 | 2014 | DoD Education Activity | AM00024 |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4896600 | 5020614 | 2016-01-21 | 2016-05-22
2017-02-07 | 2012 | DoD Education Activity | AM00025 |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339200 | 25739051 | 2016-06-01 | 2017-08-11
2017-02-07 | 2012 | DoD Education Activity | AM00026 |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685000 | 34607581 | 2015-11-11 | 2017-02-03
2017-02-07 | 2012 | DoD Education Activity | AM00026 | 43 | 2013-03-04 | 2015-11-05 | Northview Enterprises, Incorporated | W912QR-14-D-0022/36144721 | 1169000 | 1239078 | 2016-11-30 | 2016-11-30
2017-01-08 | 2012 | DoD Education Activity | AM00027 |  | 2012-10-31 | 2013-12-20 | J&J Contractors, Inc. | W912WJ-14-C-0007 / 53881843 | 45000 | 45000 | 2016-04-21 | 2016-06-30
2017-02-07 | 2012 | DoD Education Activity | AM00027 |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 32260396 | 34308579 | 2016-04-21 | 2016-06-30
2017-02-07 | 2012 | DoD Education Activity | AM00027 | 88 | 2012-10-31 | 2013-12-20 | J&J Contractors, Inc. | W912WJ-14-C-0007 / 53881843 | 45000 | 45000 | 2016-04-21 | 2016-06-30
2017-02-07 | 2013 | DoD Education Activity | AM00028 |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39361936 | 41381347 | 2015-12-17 | 2017-02-15
2017-02-07 | 2013 | DoD Education Activity | AM00028 | 44 | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001/51839544 | 145726 | 145726 | 2015-12-17 | 2017-02-15
2017-02-07 | 2014 | DoD Education Activity | AM00031 |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278-12-D-0039/30132665 | 32124000 | 32940189 | 2017-02-10 | 2017-06-30
2017-02-07 | 2014 | DoD Education Activity | AM00034 |  | 2014-06-20 | 2014-11-10 | Walsh Group Ventures | W912QR-15-C-0001/34496304 | 50930542 | 51661644 | 2017-02-25 | 2017-08-01
2017-02-07 | 2014 | DoD Education Activity | AM00037 |  | 2014-07-25 | 2015-08-18 | Roy Anderson Corp | N6945014R17600005 | 38343900 | 41501694 | 2018-06-28 | 2018-06-30
2017-02-07 | 2014 | DoD Education Activity | AM00038 |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40092900 | 40544226 | 2016-09-14 | 2017-06-30
2017-02-07 | 2014 | DoD Education Activity | AM00038 | 29 | 2014-07-22 | 2016-05-09 | Canoochee EMC | DACA87-01-D-0014 / 53303340 | 467157 | 467157 | 2017-01-11 | 2017-03-23
2017-02-07 | 2014 | DoD Education Activity | AM00040 |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 35264000 | 36161861 | 2016-03-28 | 2016-06-10
2017-02-07 | 2014 | DoD Education Activity | AM00046 |  | 2013-02-06 | 2013-12-20 | J&J Contractors, Inc. | W912WJ-14-C-0007 / 34504372 | 0 | 1240550 | 2016-04-21 | 2016-06-30
2017-02-07 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037 / 39179628 | 25624589 | 25624589 | 2020-06-10 | 2020-09-08
2016-11-03 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc. | W91278-12--D-0037-CV03 | 45411000 | 45411000 | 2020-06-02 | 2020-06-02
2017-02-07 | 2016 | DoD Education Activity | AM00048 | 8 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037 / 54560299 | 4286000 | 4286000 | 2020-06-10 | 2020-09-08
2017-02-07 | 2016 | DoD Education Activity | AM00048 | 9 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037 / 54560300 | 15500000 | 15500000 | 2020-06-10 | 2020-09-08
2017-02-07 | 2014 | DoD Education Activity | AM00050 |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791250 | 32210822 | 2016-10-31 | 2017-07-15
2017-02-07 | 2015 | DoD Education Activity | AM00103 |  | 2015-09-15 | 2016-07-01 | Munilla Construction Management, LLC | N69450 16 C 1612 | 65190000 | 67301358 | 2018-11-26 | 2018-11-26
2017-02-07 | 2015 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N62470 16 c 6003 | 6498338 | 7088580 | 2019-03-27 | 2019-03-27
2017-02-07 | 2016 | DoD Education Activity | AM00123 |  | 2016-02-22 | 2016-07-21 | Walsh Construction Company II. LLC | W912QR-16-C-0012 / 44615921 | 20483300 | 20483300 | 2018-05-08 | 2018-08-31
2017-02-07 | 2011 | DoD Education Activity | AM2455206 |  | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297000 | 44111956 | 2014-09-30 | 2016-01-21
2017-02-07 | 2011 | DoD Education Activity | AM8193 01 |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968494 | 50464225 | 2014-04-19 | 2016-08-15
2017-02-07 | 2011 | DoD Education Activity | D9124-1 |  | 2012-04-18 | 2012-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260170 | 28559921 | 2014-04-17 | 2014-07-04
2017-02-07 | 2011 | DoD Education Activity | D9124-1 | 17 | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843004 | 5600711 | 2015-07-23 | 2013-01-04
2017-02-07 | 2011 | DoD Education Activity | D9124-1 | 18 | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28673973 | 30365039 | 2015-01-13 | 2015-02-12
2017-02-07 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029 / 27243529 | 77816984 | 77816984 | 2019-05-08 | 2019-09-05
2017-02-07 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-08-19 | SKE Support Services GmbH | W912GB-15-D-0013 / 53705899 | 133430 | 133430 | 2017-02-15 | 2017-04-16
2017-02-07 | 2013 | DoD Education Activity | EU00034 |  | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006 / 44599966 | 41569129 | 41654078 | 2019-01-02 | 2019-04-02
2017-02-07 | 2013 | DoD Education Activity | EU00034 | 45 | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006 / 50005397 | 0 | 0 | 2019-01-02 | 2019-04-02
2016-11-03 | 2014 | DoD Education Activity | EU00040 |  | 2016-03-14 | 2016-07-20 | LBB Kaiserslautern | W912GB-12-C-0025 / 52029339 | 2898099 | 2898099
2017-02-07 | 2014 | DoD Education Activity | EU00040 |  | 2015-10-21 | 2016-03-14 | SKE Support Services GmbH | W912GB-15-D-0013 / 51896424 | 133763 | 135866 | 2016-06-22 | 2016-10-21
2017-02-07 | 2014 | DoD Education Activity | EU00040 | 60 | 2015-10-21 | 2016-09-06 | LBB Kaiserslautern | W912GB-12-C-0025 / 52029339 | 47851843 | 47881681 | 2017-05-09 | 2020-03-31
2017-02-07 | 2014 | DoD Education Activity | EU00040 | 61 | 2015-10-21 | 2016-09-06 | LBB Kaiserslautern | W912GB-12-C-0025 / 51896465 | 0 | 0 | 2019-06-18 | 2020-03-16
2017-02-07 | 2014 | DoD Education Activity | EU00040 | 62 | 2015-10-21 | 2016-09-06 | LBB Kaiserslautern | W912GB-12-C-0025 / 54333375 | 0 | 0
2017-02-07 | 2013 | DoD Education Activity | EU00043 |  | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817336 | 0 | 0 | 2017-06-21 | 2017-04-28
2017-02-07 | 2013 | DoD Education Activity | EU00043 | 33 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817338 | 3587070 | 3586824 | 2017-06-21 | 2017-04-28
2017-02-07 | 2013 | DoD Education Activity | EU00043 | 34 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 42246282 | 43203885 | 2017-06-21 | 2017-04-28
2017-02-07 | 2013 | DoD Education Activity | EU00043 | 35 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 635478 | 797141 | 2017-06-21 | 2017-04-28
2017-02-07 | 2013 | DoD Education Activity | EU00043 | 36 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 46876264 | 1444538 | 1444538 | 2017-06-21 | 2017-04-28
2017-02-07 | 2014 | DoD Education Activity | EU00049 |  | 2015-11-24 | 2016-06-03 | Federal Republic of Germany | W912GB-12-C-0041 / 50728702 | 56357984 | 56357984 | 2022-06-25 | 2022-06-25
2017-02-07 | 2012 | DoD Education Activity | EU00053 |  | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 574911 | 574911 | 2015-03-10 | 2015-08-28
2017-02-07 | 2012 | DoD Education Activity | EU00053 | 25 | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11795473 | 12346565 | 2015-03-10 | 2015-08-28
2017-02-07 | 2012 | DoD Education Activity | EU00062 |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 282692 | 282692 | 2015-09-20 | 2016-01-01
2017-02-07 | 2012 | DoD Education Activity | EU00062 | 42 | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366274 | 5728662 | 2015-09-20 | 2016-01-01
2017-02-07 | 2014 | DoD Education Activity | EU00072 |  | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB-12-C-0022 / 50815967 | 16940 | 92905 | 2018-04-11 | 2018-07-10
2017-02-07 | 2014 | DoD Education Activity | EU00072 |  | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB-12-C-0022 / 48719947 | 49290298 | 49364713 | 2018-04-11 | 2018-07-10
2017-02-07 | 2011 | DoD Education Activity | EUR 8268 02 |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869322 | 47502295 | 2015-04-30 | 2015-08-25
2017-02-07 | 2011 | DoD Education Activity | EUR 8268 02 | 13 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2015-04-30 | 2015-08-25
2017-02-07 | 2011 | DoD Education Activity | EUR 8268 02 | 14 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292874 | 2015-04-30 | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | EUR 8318 09 |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414633 | 33177784 | 2014-04-17 | 2014-07-04
2017-02-07 | 2010 | DoD Education Activity | EUR 8318 09 | 11 | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652185 | 1716 | 2015-07-23 | 2013-01-04
2017-02-07 | 2010 | DoD Education Activity | EUR 8320 03 |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46101110 | 50515218 | 2015-04-30 | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | EUR 8320 03 | 8 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513913 | 2015-04-30 | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | EUR 8320 03 | 9 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2015-04-30 | 2015-08-25
2017-02-07 | 2010 | DoD Education Activity | EUR826708 |  | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 17387653 | 58128307 | 57932958 | 2018-03-01 | 2018-06-04
2017-02-07 | 2010 | DoD Education Activity | EUR826708 | 3 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 39972656 | 3327125 | 3332638 | 2018-03-01 | 2018-06-04
2017-02-07 | 2010 | DoD Education Activity | EUR826708 | 4 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 45239562 | 0 | 0 | 2018-03-01 | 2018-06-04
2017-02-07 | 2015 | DoD Education Activity | PA00017 |  | 2016-07-15 | 2016-12-23 | Nippo Corporation | W912HV-17-C-0004 / 37880445 | 61521811 | 61521811 | 2020-11-17 | 2019-06-06
2017-02-07 | 2014 | DoD Education Activity | PA00018 |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28953797 | 31218893 | 2016-10-03 | 2017-04-28
2017-02-07 | 2013 | DoD Education Activity | PA00020 |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187221 | 32377858 | 2015-12-09 | 2016-05-22
2017-02-07 | 2013 | DoD Education Activity | PA00021 |  | 2015-06-12 | 2016-02-19 | Nippo Corporation | W912HV-16-C-0004 / 32602254 | 47987000 | 47987000 | 2018-11-03 | 2019-01-02
2017-02-07 | 2012 | DoD Education Activity | PA00027 |  | 2014-07-25 | 2014-12-24 | Daiwa Odakyu Construction - JDC JV | W912HV-15-C-0002/ 29312181 | 40546769 | 41565105 | 2018-12-21 | 2019-04-09
2017-02-07 | 2013 | DoD Education Activity | PA00030 |  | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476284 | 97887483 | 2017-04-01 | 2017-06-20
2017-02-07 | 2013 | DoD Education Activity | PA00033 |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475000 | 1475000 | 2016-10-24 | 2017-05-31
2017-02-07 | 2013 | DoD Education Activity | PA00033 | 38 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469000 | 2469000 | 2016-10-24 | 2017-05-31
2017-02-07 | 2013 | DoD Education Activity | PA00033 | 39 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612000 | 4612000 | 2016-10-24 | 2017-05-31
2017-02-07 | 2013 | DoD Education Activity | PA00033 | 40 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418175 | 63930482 | 2016-10-24 | 2017-05-31
2017-02-07 | 2014 | DoD Education Activity | PA00035 |  | 2014-09-23 | 2015-02-18 | Nippo Corporation | W912HV-15-C-0003 / 34596540 | 31459277 | 32188127 | 2016-10-02 | 2016-12-02
| 2013 | Marine Corps Active | M00146163 |  | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091000 | 28242000 | 2016-01-18 | 2016-07-15
| 2015 | Marine Corps Active | M00146193 |  | 2015-06-17 | 2016-12-22 | GARNEY COMPANIES, INC. | N4008517C8315 | 54905000 | 52291000 | 2020-02-28 | 2020-02-28
| 2016 | Marine Corps Active | M00146194 |  | 2016-03-29 | 2016-08-31 | M A MORTENSON COMPANY | N4008516C5506 AWD | 28561000 | 26903000 | 2018-10-04 | 2018-10-04
| 2016 | Marine Corps Active | M00146229 |  | 2016-07-18 | 2016-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008516D6301 0002 | 4160000 | 3752000 | 2017-10-02 | 2017-10-02
| 2013 | Marine Corps Active | M00243313 |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974000 | 11993000 | 2015-04-29 | 2016-11-30
| 2014 | Marine Corps Active | M00243520 |  | 2015-01-29 | 2015-09-29 | MESA ENERGY SYSTEMS, INC. | N6247315C3602 AWD | 43778000 | 29667000 | 2018-01-11 | 2018-01-11
| 2013 | Marine Corps Active | M00263382 |  | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513000 | 11215000 | 2015-04-12 | 2016-01-31
| 2016 | Marine Corps Active | M00263398 |  | 2016-08-05 | 2016-09-27 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 25643000 | 24150000 | 2018-04-06 | 2018-04-20
| 2014 | Marine Corps Active | M002641406 |  | 2014-12-18 | 2015-05-01 | BISCAYNE CONTRACTORS, INC. | N4008015C2007 AWD | 4439000 | 4335000 | 2016-11-21 | 2016-11-21
| 2013 | Marine Corps Active | M00264562 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462000 | 29575000 | 2016-11-06 | 2018-01-22
| 2012 | Marine Corps Active | M00264567 |  | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222000 | 24969000 | 2016-11-06 | 2018-01-22
| 2013 | Marine Corps Active | M00264572 |  | 2015-04-24 | 2015-09-30 | CORINTHIAN CONTRACTORS, INC | N4008015C0169 | 14182000 | 13562000 | 2017-05-28 | 2017-05-28
| 2012 | Marine Corps Active | M00264621 |  | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081000 | 28544000 | 2015-03-15 | 2016-07-21
| 2015 | Marine Corps Active | M00264635 |  | 2016-05-16 | 2016-11-16 | G-W MANAGEMENT SERVICES, LLC | N4008017C0014 | 10730000 | 10219000 | 2018-03-25 | 2018-03-25
| 2013 | Marine Corps Active | M00264644 |  | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168000 | 12097000 | 2015-04-22 | 2016-04-30
| 2014 | Marine Corps Active | M00264677 |  | 2015-10-28 | 2016-03-31 | HARKINS BUILDERS INC. | N4008016C0151 AWD | 27064000 | 26183000 | 2018-01-05 | 2018-01-05
| 2016 | Marine Corps Active | M00318116 |  | 2016-03-16 | 2016-08-08 | 1GBR7 - PAVE-TECH INC | N6274216C1307 | 12857000 | 11981000 | 2018-06-09 | 2018-06-09
| 2015 | Marine Corps Active | M00318778 |  | 2014-01-10 | 2015-03-13 | DAWSON-HAWAIIAN BUILDERS I | N6274215C1316 AWD | 14825000 | 12999000 | 2017-08-09 | 2018-01-27
| 2014 | Marine Corps Active | M00318852 |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407000 | 17761000 | 2016-10-04 | 2016-10-04
| 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | HORIKAWA, NORINE E | N62742 15 C 1305 | 51071000 | 47489000 | 2018-03-31 | 2017-09-28
| 2014 | Marine Corps Active | M00318863 |  | 2016-07-13 | 2016-09-19 | NIPPO CORPORATION | N4008414D0010 0013 | 49620000 | 47110000 | 2018-03-04 | 2019-04-17
| 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720000 | 15296000 | 2016-12-18 | 2016-12-18
| 2016 | Marine Corps Active | M00318902 |  | 2016-05-27 | 2016-11-18 | NOVA GROUP INC | N6274217C1320 | 24797000 | 20361000 | 2019-06-06 | 2019-06-06
| 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 47645000 | 25271000 | 2017-01-03 | 2017-03-24
| 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 53999000 | 45204000 | 2017-01-03 | 2017-03-24
| 2015 | Marine Corps Active | M00318924 |  | 2014-12-01 | 2015-09-28 | DAWSON TECHNICAL LLC | N62742 15 C 1306 | 2197000 | 2199000 | 2016-09-26 | 2016-11-24
| 2012 | Marine Corps Active | M006811045 |  | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242000 | 71461000 | 2016-03-31 | 2016-03-31
| 2013 | Marine Corps Active | M006811132 |  | 2014-11-18 | 2016-03-24 | BETHEL-WEBCOR JV-1 | N6247316C0606 AWD | 78418000 | 74319000 | 2020-01-23 | 2020-01-23
| 2013 | Marine Corps Active | M006811176 |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428000 | 4427000 | 2016-04-21 | 2016-06-17
| 2012 | Marine Corps Active | M00681637 |  | 2016-03-29 | 2016-06-30 | GRANITE CONSTRUCTION COMPANY | N6247314D0066 0004 | 29164000 | 26583000 | 2018-09-23 | 2018-09-23
| 2014 | Marine Corps Active | M00681970 |  | 2014-07-01 | 2015-12-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0012 | 37184000 | 18102000 | 2018-04-27 | 2018-04-27
| 2013 | Marine Corps Active | M60169465 |  | 2012-11-15 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643000 | 38729000 | 2016-09-08 | 2017-02-20
| 2015 | Marine Corps Active | M62204939 |  | 2015-01-14 | 2015-03-31 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0003 | 15300000 | 14160000 | 2016-10-06 | 2016-12-02
| 2016 | Marine Corps Active | M626130702 |  | 2016-09-21 | 2016-09-22 | Nippo Corporation | N40084-14-D-0010-TO 0012 | 6941000 | 6794000 | 2017-10-09 | 2017-10-09
| 2014 | Marine Corps Active | M626131402 |  | 2016-07-20 | 2016-09-27 | NIPPO CORPORATION | N4008414D0010 | 3357000 | 3312000 | 2018-03-26 | 2018-03-04
| 2015 | Marine Corps Active | M626131502 |  | 2015-07-15 | 2015-09-27 | NIPPO CORPORATION | N4008415C0009 AWD | 14308000 | 13587000 | 2017-01-30 | 2017-03-07
| 2013 | Marine Corps Active | M62974378 |  | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316000 | 13696000 | 2015-07-31 | 2017-01-20
| 2015 | Marine Corps Active | M62974617 |  | 2016-02-29 | 2016-05-23 | HARPER CONSTRUCTION COMPANY, INC | N6247315D2432 0004 | 16694000 | 16376000 | 2017-11-29 | 2017-11-29
| 2013 | Marine Corps Active | M67001003 |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260000 | 29180000 | 2015-09-01 | 2017-03-31
| 2014 | Marine Corps Active | M670011349 |  | 2014-02-27 | 2015-08-31 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0014 | 25742000 | 24958000 | 2017-03-21 | 2017-05-10
| 2014 | Marine Corps Active | M670011353 |  | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529000 | 14035000 | 2016-03-01 | 2016-09-01
| 2012 | Marine Corps Active | M67001138 |  | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101000 | 26924000 | 2014-07-29 | 2016-08-31
| 2012 | Marine Corps Active | M670011383 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235000 | 68076000 | 2015-04-18 | 2016-11-29
| 2013 | Marine Corps Active | M670011384 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666000 | 39794000 | 2015-04-18 | 2016-11-29
| 2014 | Marine Corps Active | M670011445 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 2123000 | 2273000 | 2017-02-06 | 2017-06-17
| 2014 | Marine Corps Active | M670011447 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 9605000 | 10359000 | 2017-02-06 | 2017-06-17
| 2014 | Marine Corps Active | M670011448 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 15756000 | 15192000
| 2014 | Marine Corps Active | M67001674 |  | 2014-02-03 | 2015-08-19 | BRISTOL GENERAL CONTRACTORS, LLC | N4008515C0320 AWD | 17032000 | 16382000 | 2017-03-11 | 2017-09-29
| 2014 | Marine Corps Active | M67001676 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312000 | 13854000 | 2015-12-20 | 2016-07-20
| 2016 | Marine Corps Active | M67001686 |  | 2016-06-30 | 2016-09-28 | GP ABSHER ONE, LLC | N4008515D0094 0003 | 3640000 | 3239000 | 2018-04-07 | 2018-04-06
| 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159000 | 10836000 | 2015-12-20 | 2016-07-20
| 2016 | Marine Corps Active | M67001729 |  | 2015-10-08 | 2016-09-28 | VANDER WERFF, PETER CONSTRUCTION | N6247314D0039 0012 | 1885000 | 1656000 | 2017-11-23 | 2018-04-06
| 2014 | Marine Corps Active | M67004934 |  | 2013-12-06 | 2014-09-10 | GULF BUILDING CORP & HERNANDEZCONSULTANTS | N6945014D1274 0002 | 14685000 | 14384000 | 2016-03-17 | 2017-01-06
| 2015 | Marine Corps Active | M67399159 |  | 2015-01-30 | 2015-04-15 | RQ-BERG JV | N6247310D5482 0009 | 28644000 | 27233000 | 2017-05-01 | 2017-05-01
| 2012 | Marine Corps Active | M67399177 |  | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819000 | 20270000 | 2014-09-02 | 2016-09-20
| 2015 | Marine Corps Active | M67399222 |  | 2016-02-22 | 2016-08-31 | AT&T GOVERNMENT SOLUTIONS, INC | N6247316C0601 AWD | 12948000 | 12001000 | 2019-03-04 | 2019-03-04
| 2012 | Marine Corps Active | M67399991 |  | 2015-01-14 | 2015-01-15 | NAVY STANDARD DOCUMENT | N6247314MPRM002 | 2249000 | 1220000
| 2013 | Marine Corps Active | M67399992 |  | 2015-01-14 | 2015-01-15 | NAVY STANDARD DOCUMENT | N6247314MPRM002 | 24750000 | 9868000
| 2014 | Marine Corps Active | M67400201 |  | 2013-11-08 | 2014-04-18 | NAVY STANDARD DOCUMENT | N6274214MP00024 | 2881000 | 2721000 | 2015-11-18 | 2015-11-18
| 2016 | Marine Corps Active | M67400606 |  | 2016-07-22 | 2016-09-15 | R. C. CONSTRUCTION | N4008516C5505 AWD | 8853000 | 8600000 | 2018-04-20 | 2018-03-26
| 2015 | Marine Corps Active | M67400801 |  | 2015-08-27 | 2016-04-21 | NAVY STANDARD DOCUMENT | USACE | 29352000 | 31610000 | 2017-07-29 | 2017-07-29
| 2015 | Marine Corps Active | M67400803 |  | 2015-08-21 | 2015-12-22 | NAVY STANDARD DOCUMENT | USACE | 20221000 | 19643000 | 2017-09-12 | 2017-09-12
| 2012 | Marine Corps Active | M67604117 |  | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | N6258309D0131 FZ01 | 7437000 | 7112000 | 2014-12-12 | 2015-05-26
| 2016 | Marine Corps Active | M67604132 |  | 2016-07-08 | 2016-08-31 | REYES CONSTRUCTION INC | N6247314D0068 0008 | 2887000 | 2714000 | 2017-10-30 | 2017-10-30
| 2014 | Marine Corps Active | N41557109 |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820000 | 57555000 | 2016-12-03 | 2017-03-08
| 2014 | Marine Corps Active | N41557J200 |  | 2014-10-16 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 | 53014000 | 47830000 | 2016-09-02 | 2016-09-02
| 2014 | Marine Corps Active | N61755H106 |  | 2013-11-14 | 2015-04-30 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 0002 | 24771000 | 38813000 | 2017-08-13 | 2017-08-13
| 2013 | Marine Corps Active | N69212984 |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028000 | 11036000 | 2015-06-26 | 2016-09-04
| 2013 | Marine Corps Active | N69212985 |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418000 | 18007000 | 2015-06-26 | 2016-09-04
| 2014 | Marine Corps Reserve | M67386139 |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019000 | 16478000 | 2016-03-25 | 2016-06-16
| 2013 | Marine Corps Reserve | M68479130 |  | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911000 | 4949000 | 2014-12-04 | 2015-10-13
| 2015 | Marine Corps Reserve | N00620234 |  | 2014-12-30 | 2015-07-29 | SWINERTON BUILDERS | N4425515C6001 AWD | 29746000 | 29061000 | 2016-12-15 | 2017-02-19
2017-01-31 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 114390000 | 2015-08-30 | 2016-11-30
2016-12-31 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 66900000 | 2015-08-30 | 2016-11-30
2017-01-31 | 2014 | Missile Defense Agency | 634 |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300000 | 14468818 | 2016-01-06 | 2016-01-06
2017-01-31 | 2013 | Missile Defense Agency | 639 |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584000 | 16093814 | 2014-11-28 | 2015-09-12
2017-01-31 | 2016 | Missile Defense Agency | 640 |  | 2015-06-10 | 2016-02-10 | AMEC PROGRAMS, INC. | W912GB-16-C-0005 | 141906057 | 162103599 | 2018-03-30 | 2018-03-30
2017-01-31 | 2014 | Missile Defense Agency | 648 |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991000 | 15673220 | 2015-01-09 | 2015-02-20
2017-01-31 | 2014 | Missile Defense Agency | 649 |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838000 | 50712661 | 2016-05-31 | 2016-05-31
2017-01-31 | 2016 | Missile Defense Agency | 661 |  | 2015-07-16 | 2016-02-05 | BRICE ENVIRONMENTAL SERVICES CORPORATION | FA8903-16-C-0001 | 1637189 | 1890163 | 2016-08-31 | 2016-11-04
2016-09-30 | 2015 | National Geospatial-Intelligence Agency | 030 |  | 2015-09-14 | 2015-11-23 | Greenway Enterprises, Inc. | W912DR-13-D-0023 | 6098135.18 | 6900000 | 2016-09-25 | 2017-01-10
2015-06-01 | 2008 | National Geospatial-Intelligence Agency | 65416 |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture | W912DR-07-C-0027 | 1409901000 | 1467244000 | 2011-12-22 | 2015-11-21
2017-01-31 | 2010 | National Security Agency | 17781 |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700000 | 11700000 | 2011-08-20 | 2012-05-30
2017-01-31 | 2010 | National Security Agency | 17782 |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200000 | 3200000 | 2013-07-13 | 2015-11-30
2017-01-31 | 2011 | National Security Agency | 17866 |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900000 | 131089216 | 2014-11-30 | 2015-10-31
2017-01-31 | 2010 | National Security Agency | 17872 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223000 | 129078000 | 2014-04-18 | 2015-10-12
2017-01-31 | 2010 | National Security Agency | 18052 |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566000 | 8257000 | 2013-02-01 | 2014-05-14
2017-01-31 | 2010 | National Security Agency | 18053 |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095000 | 16448000 | 2013-02-01 | 2014-05-31
2017-01-31 | 2010 | National Security Agency | 18054 |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085000 | 7316000 | 2013-02-01 | 2014-08-31
2017-01-31 | 2011 | National Security Agency | 20489 |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657000 | 8867000 | 2014-01-30 | 2015-01-16
2017-01-31 | 2011 | National Security Agency | 20489 | 2 | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620000 | 2657000 | 2014-02-28 | 2014-04-28
2017-01-31 | 2009 | National Security Agency | 21120 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060000 | 13760000 | 2013-01-17 | 2014-04-18
2017-01-31 | 2010 | National Security Agency | 21372 |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443000 | 4201000 | 2011-09-26 | 2012-06-29
2017-01-31 | 2012 | National Security Agency | 23051 |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975000 | 132008057 | 2015-05-03 | 2016-01-01
2017-01-31 | 2012 | National Security Agency | 23051 | 2 | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621000 | 5621000 | 2014-02-14 | 2015-09-30
2017-01-31 | 2011 | National Security Agency | 23994 |  | 2012-04-26 | 2012-06-18 | JAAAT | W912HN-10-D-0063 | 15315000 | 16526000 | 2014-01-30 | 2014-12-23
2017-01-31 | 2012 | National Security Agency | 24649 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589000 | 608357051 | 2015-09-15 | 2016-02-08
2017-01-31 | 2010 | National Security Agency | 25047 |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253000 | 5792000 | 2014-03-07 | 2015-05-04
2017-01-31 | 2013 | National Security Agency | 26170 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91777000 | 100657014 | 2015-10-11 | 2016-11-30
2017-01-31 | 2015 | National Security Agency | 27532 |  | 2015-06-30 | 2016-04-05 | Hensel-Phelps | W912DR-15-D-0032 | 40081050 | 40081050 | 2018-10-25 | 2018-10-25
2017-01-31 | 2016 | National Security Agency | 30583 |  | 2015-12-18 | 2016-06-17 | Clark Construction | W912DR-15-R-0024 | 616311000 | 636971000 | 2020-09-09 | 2020-09-09
2017-01-31 | 2016 | National Security Agency | 31066 |  | 2015-06-30 | 2016-04-05 | Hensel-Phelps | W912DR-15-D-0032 DO 0002 | 30538350 | 30538350 | 2018-08-08 | 2018-08-08
2017-01-31 | 2016 | National Security Agency | 31934 |  | 2015-07-08 | 2015-09-15 | Whiting-Turner | W912DR-15-C-0026 | 24554985 | 26225082 | 2016-12-31 | 2016-12-31
2017-01-31 | 2016 | National Security Agency | 32122 |  | 2016-04-01 | 2016-05-23 | Argo | WH12DR-14-D-0019 | 22375000 | 22375000 | 2018-06-08 | 2018-06-08
| 2015 | Navy Active | M00146996 |  | 2015-06-04 | 2015-09-02 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0015 | 1350000 | 1315000 | 2017-03-31 | 2017-04-29
| 2016 | Navy Active | M00264714 |  | 2016-05-02 | 2016-07-14 | CHEROKEE NATION CONSTRUCTIONSERVICES, LLC | N4008016C0162 AWD | 7003000 | 6620000 | 2017-07-29 | 2017-07-29
| 2016 | Navy Active | M00318910 |  | 2015-11-24 | 2016-07-12 | ABSHER CONSTRUCTION CO | N6274216C1322 AWD | 67105000 | 60275000 | 2018-10-31 | 2018-10-31
| 2012 | Navy Active | M006811046 |  | 2014-08-28 | 2014-11-25 | ORION CONSTRUCTION CORPORATION | N6247310D5419 0012 | 75135000 | 45955000 | 2016-12-08 | 2016-12-08
| 2016 | Navy Active | M006811220 |  | 2016-06-24 | 2016-11-30 | J. R. FILANC CONSTRUCTION COMPANY,INC | N6247317C3403 AWD | 44351000 | 33562000 | 2019-03-30 | 2019-03-30
| 2014 | Navy Active | M626131403 |  | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545000 | 15906000 | 2016-02-02 | 2016-02-02
| 2015 | Navy Active | M62613602 |  | 2014-11-21 | 2015-04-30 | NAVY STANDARD DOCUMENT | N6274215MP00014 | 4913000 | 5073000 | 2016-06-24 | 2016-06-24
| 2016 | Navy Active | M670011346 |  | 2016-02-26 | 2016-07-29 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008516C5500 AWD | 45118000 | 40590000 | 2018-08-13 | 2018-08-13
| 2012 | Navy Active | N00128816 |  | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491000 | 83172000 | 2016-06-30 | 2016-06-30
| 2016 | Navy Active | N00207334 |  | 2015-11-06 | 2016-03-18 | HICAPS, INC. | N69450 14 D 1275 | 5881000 | 5693000 | 2017-06-11 | 2017-06-11
| 2015 | Navy Active | N00207631 |  | 2014-04-01 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 11078000 | 13617000 | 2016-04-19
| 2014 | Navy Active | N00207659 |  | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573000 | 12686000 | 2016-04-19
| 2016 | Navy Active | N00207662 |  | 2016-06-17 | 2016-09-27 | WHITESELL-GREEN, INC. | N6945016C1103 AWD | 9719000 | 9215000 | 2017-07-07 | 2017-11-13
| 2015 | Navy Active | N00207664 |  | 2015-01-26 | 2015-04-30 | PHOENIX CONSTRUCTION SERVICES, INC. | N6945015C1104 AWD | 7293000 | 7255000 | 2016-04-30 | 2016-11-14
| 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151000 | 14254000 | 2016-01-07 | 2016-11-15
| 2016 | Navy Active | N00245499 |  | 2016-04-07 | 2016-08-29 | RQ CONSTRUCTION, LLC | N6247316D1885 0001 | 32629000 | 30611000 | 2018-08-29 | 2018-08-29
| 2013 | Navy Active | N00245500 |  | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553000 | 47810000 | 2015-10-24 | 2017-01-10
| 2015 | Navy Active | N00245800 |  | 2015-06-15 | 2015-09-17 | S & R CONSTRUCTIONA JOINT VENTURE | N6247315C1604 AWD | 41838000 | 42604000 | 2017-10-01 | 2017-10-01
| 2013 | Navy Active | N00246730 |  | 2013-05-29 | 2015-07-30 | HENSEL PHELPS CONSTRUCTION CO | N6247315C1614 AWD | 72648000 | 71376000 | 2017-07-29 | 2017-09-14
| 2012 | Navy Active | N00246880 |  | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977000 | 57877000 | 2015-03-30 | 2015-10-18
| 2014 | Navy Active | N00246957 |  | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904000 | 8586000 | 2016-02-10 | 2016-09-08
| 2015 | Navy Active | N00246987 |  | 2015-07-14 | 2015-09-16 | BUENA VISTA CONTRACTING INC | N6247315C1613 AWD | 906000 | 865000 | 2016-09-19 | 2016-09-19
| 2016 | Navy Active | N00246998 |  | 2015-07-29 | 2016-01-19 | RQ-DPR JV | N6247315C1609 | 3443000 | 3650000 | 2018-04-02 | 2018-09-30
| 2014 | Navy Active | N00620239 |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY | N4425514C5004 AWD | 29692000 | 27958000 | 2017-05-26 | 2017-05-26
| 2014 | Navy Active | N00620251 |  | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY | N4425514C5002 AWD | 84997000 | 82187000 | 2016-01-12 | 2016-04-29
| 2015 | Navy Active | N00620259 |  | 2015-02-27 | 2016-12-21 | WATTS CONTRACK A JV | N4425517C8001 AWD | 2298000 | 30391000 | 2018-06-19 | 2018-06-19
| 2014 | Navy Active | N32411103 |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319000 | 13549000 | 2015-12-16 | 2016-01-01
| 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 AWD | 34317000 | 34578000 | 2016-11-23 | 2017-03-09
| 2012 | Navy Active | N32443383 |  | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576000 | 60532000 | 2014-09-28 | 2015-06-15
| 2015 | Navy Active | N32443527 |  | 2014-12-19 | 2015-09-03 | WHITESELL-GREEN, INC. | N4008513D7776 0007 | 11256000 | 10653000 | 2017-04-20 | 2017-07-19
| 2013 | Navy Active | N32443998 |  | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374000 | 30358000 | 2015-12-27
| 2014 | Navy Active | N32446266 |  | 2013-12-30 | 2015-08-17 | METHUEN CONSTRUCTION CO., INC | N4008515C8746 AWD | 31542000 | 35524000 | 2018-01-23 | 2018-01-23
| 2014 | Navy Active | N32446308 |  | 2015-09-29 | 2016-04-21 | TRITON MARINE CONSTRUCTION CORP. | N4008516C3013 AWD | 34722000 | 31794000 | 2018-10-25 | 2018-10-25
| 2015 | Navy Active | N3379A064 |  | 2015-03-12 | 2015-09-11 | ZAFER TAAJJIT OMSAAT VE TOCARET A S | N62470 15 C 5006 | 1407000 | 1367000 | 2017-01-16 | 2017-01-23
| 2014 | Navy Active | N3379A227 |  | 2014-02-26 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492000 | 4306000 | 2015-09-28 | 2016-06-29
| 2015 | Navy Active | N3379A330 |  | 2015-03-12 | 2015-09-11 | ZAFER TAAJJIT OMSAAT VE TOCARET A S | N6247015C5006 AWD | 8104000 | 8003000 | 2017-01-18 | 2017-01-18
| 2014 | Navy Active | N3379A921 |  | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714000 | 19746000 | 2016-05-30
| 2015 | Navy Active | N41557230 |  | 2015-04-02 | 2015-11-17 | RELYANT GLOBAL LLC | N6274216C1317 AWD | 20799000 | 15627000 | 2018-06-19 | 2018-06-19
| 2015 | Navy Active | N41557240 |  | 2015-06-16 | 2015-09-29 | WATTS CONSTRUCTORS, LLC | N6274215C1303 | 27345000 | 17011000 | 2018-05-02 | 2018-05-02
| 2014 | Navy Active | N41557625 |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710000 | 50782000 | 2016-04-25 | 2017-09-28
| 2015 | Navy Active | N42237099 |  | 2014-02-24 | 2015-07-22 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 39730000 | 39743000 | 2018-06-20 | 2018-04-22
| 2014 | Navy Active | N42237100 |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249000 | 128220000 | 2018-06-20 | 2018-04-22
| 2012 | Navy Active | N42237611 |  | 2015-11-13 | 2016-06-28 | M A MORTENSON COMPANY | N6945014D1270 0003 | 54619000 | 53906000 | 2018-11-30 | 2018-11-30
| 2012 | Navy Active | N42237636 |  | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167000 | 54754000 | 2017-04-16 | 2017-04-16
| 2015 | Navy Active | N47608155 |  | 2015-04-30 | 2015-09-29 | G-W MANAGEMENT SERVICES, LLC | N4008015C0168 AWD | 11273000 | 10909000 | 2017-08-20 | 2017-08-20
| 2014 | Navy Active | N47608262 |  | 2014-08-11 | 2014-09-29 | REILLY CONSTRUCTION, INC | N4008014D3014 0001 | 1426000 | 1686000 | 2016-09-29 | 2017-06-06
| 2012 | Navy Active | N47608561 |  | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49900000 | 49567000 | 2016-04-01 | 2017-01-24
| 2015 | Navy Active | N50092354 |  | 2015-07-31 | 2015-09-28 | HOURIGAN-SUNDT, A JOINT VENTURE | N4008515C0011 AWD | 40638000 | 38540000 | 2018-10-07 | 2018-10-07
| 2016 | Navy Active | N50092726 |  | 2016-08-02 | 2016-09-29 | AIC INTERNATIONAL, INC. | N4019216D2700 0005 | 2880000 | 2646000 | 2017-07-13 | 2018-04-07
| 2013 | Navy Active | N60191513 |  | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430000 | 29588000 | 2015-12-16 | 2016-11-22
| 2012 | Navy Active | N60191527 |  | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599000 | 21044000 | 2014-10-12 | 2015-09-06
| 2016 | Navy Active | N60191603 |  | 2016-02-18 | 2016-06-15 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008516C6119 AWD | 21334000 | 20873000 | 2017-06-30 | 2017-11-12
| 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446000 | 13549000 | 2016-10-25 | 2018-02-20
| 2015 | Navy Active | N60201423 |  | 2015-08-28 | 2016-11-15 | SAUER, INC. | N6945017C0902 | 27930000 | 26558000 | 2018-04-09 | 2018-04-09
| 2016 | Navy Active | N60201424 |  | 2016-01-26 | 2016-07-14 | ARTEC GROUP (THE) INC | N6945016D1110 0001 | 13608000 | 12970000 | 2018-02-05 | 2018-02-05
| 2015 | Navy Active | N60495420 |  | 2015-07-17 | 2015-09-16 | STRAUB CONSTRUCTION, INC. | N6247315D2427 0002 | 25541000 | 24696000 | 2017-11-24 | 2018-11-24
| 2015 | Navy Active | N60495430 |  | 2016-04-15 | 2016-09-29 | NOVA GROUP INC | N4425516C7005 AWD | 7713000 | 6923000 | 2018-02-13 | 2017-11-23
| 2016 | Navy Active | N60508274 |  | 2016-01-15 | 2016-06-20 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0008 | 11628000 | 11242000 | 2018-03-24 | 2018-03-24
| 2015 | Navy Active | N60508278 |  | 2015-04-08 | 2015-08-19 | NAVY STANDARD DOCUMENT | N6247015MPS0050 | 1407000 | 1364000 | 2016-04-28 | 2016-04-28
| 2012 | Navy Active | N60508927 |  | 2012-02-17 | 2012-06-07 | NAVY STANDARD DOCUMENT | N6247012MPS0048 | 18810000 | 20652000 | 2015-11-24 | 2015-11-24
| 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458000 | 9458000 | 2017-01-17 | 2017-01-17
| 2016 | Navy Active | N61054023 |  | 2016-08-03 | 2016-12-19 | NAVY STANDARD DOCUMENT | N6274217MD0P023 | 14479000 | 14479000 | 2018-09-30 | 2018-09-30
| 2016 | Navy Active | N61054023 |  | 2016-08-03 | 2016-12-19 | NAVY STANDARD DOCUMENT | USACE | 14479000 | 14479000 | 2018-09-30 | 2018-09-30
| 2013 | Navy Active | N610541305 |  | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791000 | 7305000 | 2016-02-21 | 2016-02-21
| 2014 | Navy Active | N610581401 |  | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799000 | 21637000
| 2014 | Navy Active | N61065202 |  | 2014-12-11 | 2016-08-29 | VANDER WERFF, PETER CONSTRUCTION | N6247314D0039 0011 | 15972000 | 14021000 | 2018-06-10 | 2018-06-10
| 2013 | Navy Active | N61065229 |  | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447000 | 28023000 | 2016-04-17 | 2016-06-16
| 2014 | Navy Active | N61065240 |  | 2015-02-23 | 2015-04-16 | TEEHEE ENGINEERING, INC. | N6247315C4204 AWD | 1949000 | 1893000 | 2016-10-21 | 2016-10-21
| 2016 | Navy Active | N61066603 |  | 2015-08-19 | 2016-02-05 | NORTH STAR CONSTRUCTION &ENGINEERING, INC | N4425515D0018 0004 | 5585000 | 5294000 | 2017-03-06 | 2017-03-06
| 2012 | Navy Active | N61151222 |  | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984000 | 69633000 | 2016-07-14 | 2016-07-14
| 2015 | Navy Active | N61151287 |  | 2015-03-04 | 2015-09-02 | M A MORTENSON COMPANY | N4008015C0167 AWD | 25679000 | 24720000 | 2017-07-17 | 2018-05-14
| 2013 | Navy Active | N61151372 |  | 2012-12-12 | 2013-09-27 | NAVY STANDARD DOCUMENT | N4008010D0302 0021 | 11409000 | 11143000 | 2015-05-02 | 2016-01-04
| 2014 | Navy Active | N61152001 |  | 2014-01-10 | 2015-04-13 | NAVY STANDARD DOCUMENT | N6247015MPC0032 | 109808000 | 106597000 | 2017-05-05 | 2017-05-05
| 2015 | Navy Active | N61152621 |  | 2015-07-15 | 2016-03-31 | TURNER CONSTRUCTION COMPANY | N40080 16 C 0156 | 120181000 | 115641000 | 2019-03-22 | 2019-09-08
| 2014 | Navy Active | N617551403 |  | 2013-11-14 | 2015-04-30 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 0002 | 24771000 | 24569000 | 2017-08-13 | 2017-12-02
| 2014 | Navy Active | N61755425 |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865000 | 53585000 | 2016-06-11 | 2017-04-20
| 2014 | Navy Active | N61755518 |  | 2014-06-02 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085000 | 47374000 | 2016-10-20 | 2017-03-15
| 2014 | Navy Active | N61755566 |  | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860000 | 28909000 | 2016-05-12 | 2016-08-28
| 2014 | Navy Active | N61755637 |  | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170000 | 14536000 | 2016-04-11 | 2016-05-09
| 2016 | Navy Active | N61755656 |  | 2015-07-14 | 2016-09-20 | CONTRACK WATTS, INC | N6274216C1325 AWD | 1760000 | 1638000 | 2019-04-17 | 2017-07-13
| 2013 | Navy Active | N62590400 |  | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | N6247014MPE0025 | 40018000 | 39839000
| 2016 | Navy Active | N62592401 |  | 2015-11-09 | 2016-05-05 | NAVY STANDARD DOCUMENT | USACE | 41851000 | 41720000 | 2017-11-09 | 2017-11-09
| 2014 | Navy Active | N62688500 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365000 | 1644000 | 2016-01-01 | 2016-11-11
| 2016 | Navy Active | N62688518 |  | 2015-11-23 | 2016-03-03 | SYNCON, LLC | N4008514D8152 0007 | 4575000 | 4504000 | 2017-09-29 | 2017-09-29
| 2016 | Navy Active | N62813036 |  | 2015-10-28 | 2016-01-26 | BETHEL-WEBCOR JV-1 | N6247814D4001 KB01 | 8520000 | 7899000 | 2018-03-26 | 2018-04-29
| 2015 | Navy Active | N62813048 |  | 2014-10-20 | 2015-02-27 | JSR ECC, LLC | N6247814D4003 KB01 | 8667000 | 10116000 | 2016-10-04 | 2017-02-10
| 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810000 | 2661000 | 2016-05-18 | 2016-05-18
| 2014 | Navy Active | N62813270 |  | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355000 | 20703000 | 2015-12-11 | 2015-12-11
| 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970000 | 32642000 | 2017-08-03 | 2017-12-18
| 2012 | Navy Active | N628631201 |  | 2014-04-29 | 2015-03-13 | SOCIEDAD ESPNOLA DE MONTAJES INDUSTRIALES SA DBA SEMI | 0DUMMY3295023 AWD | 13940000 | 13602000 | 2017-07-13 | 2017-07-13
| 2015 | Navy Active | N62863712 |  | 2015-04-11 | 2015-11-20 | COBRA INSTALCIONES Y SERVICIOS SA | N6247016C6001 AWD | 19252000 | 18021000 | 2018-05-23 | 2018-05-23
| 2016 | Navy Active | N62995407 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 | 20668000 | 19684000 | 2019-01-08 | 2019-01-08
| 2016 | Navy Active | N62995655 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 | 27894000 | 26565000 | 2019-01-08 | 2019-01-08
| 2015 | Navy Active | N63005955 |  | 2015-04-15 | 2015-09-16 | KOOHEJI CONTRACTORS | N3319113D0832 *New TO | 21897000 | 21826000 | 2018-11-09 | 2018-11-09
| 2016 | Navy Active | N63005970 |  | 2016-03-07 | 2016-05-26 | NAVY STANDARD DOCUMENT | USACE | 41115000 | 39039000 | 2018-11-06 | 2018-11-06
| 2016 | Navy Active | N63042218 |  | 2015-12-10 | 2016-05-10 | A&D GC INC | N6247315D2403 0003 | 7260000 | 6790000 | 2017-11-16 | 2018-01-15
| 2015 | Navy Active | N63042327 |  | 2015-03-02 | 2015-06-26 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0007 | 22497000 | 23661000 | 2016-10-17 | 2017-02-10
| 2015 | Navy Active | N63042328 |  | 2015-02-24 | 2015-06-11 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0006 | 17016000 | 16991000 | 2016-11-03 | 2016-11-06
| 2015 | Navy Active | N63042377 |  | 2015-10-27 | 2016-02-26 | NORTH STAR CONSTRUCTION & ENGINEERING, INC | N6247309D1643 X087 | 5041000 | 2412000 | 2016-05-26 | 2020-05-21
| 2016 | Navy Active | N63042378 |  | 2016-02-12 | 2016-05-31 | STRAUB CONSTRUCTION, INC. | N6247316C4602 AWD | 52939000 | 49914000 | 2017-12-07 | 2017-12-07
| 2016 | Navy Active | N63042379 |  | 2016-01-28 | 2016-03-17 | A&D GC INC | N6247315D2403 0002 | 7489000 | 7154000 | 2017-03-31 | 2017-03-31
| 2013 | Navy Active | N63043317 |  | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851000 | 9375000 | 2015-10-09 | 2016-09-11
| 2013 | Navy Active | N66691907 |  | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPA?OLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663000 | 13991000 | 2016-05-15
| 2013 | Navy Active | N66691908 |  | 2016-03-17 | 2016-08-11 | TSONTOS MICHAEL M. S.A. | N6247016C6008 AWD | 1383000 | 941000 | 2017-11-24 | 2017-11-24
| 2014 | Navy Active | N68436420 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179000 | 11071000 | 2016-02-16 | 2016-02-16
| 2015 | Navy Active | N68436422 |  | 2014-12-01 | 2015-05-04 | TRITON MARINE CONSTRUCTION CORP. | N4425514D9007 0003 | 12592000 | 11462000 | 2016-10-25 | 2016-10-25
| 2016 | Navy Active | N68436431 |  | 2016-03-31 | 2016-08-11 | NOVA GROUP INC | N4425516C7002 AWD | 19943000 | 18713000 | 2017-11-14 | 2017-11-14
| 2014 | Navy Active | N68436855 |  | 2015-01-30 | 2015-06-30 | DOYON MANAGEMENT SERVICES, LLC | N4425515C8000 AWD | 1951000 | 1887000 | 2016-05-15 | 2016-05-30
| 2016 | Navy Active | N68436983 |  | 2016-08-05 | 2016-09-22 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 31744000 | 23193000 | 2018-04-06 | 2018-02-13
| 2012 | Navy Active | N68436990 |  | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714000 | 78030000 | 2016-01-09 | 2016-12-12
| 2013 | Navy Active | N68436990 | N68436990A | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 266304000 | 262595000 | 2016-01-09 | 2016-12-12
| 2014 | Navy Active | N68436990 | N68436990B | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00002 | 24880000 | 16663000 | 2016-01-09 | 2016-12-12
| 2015 | Navy Active | N68436990 | N68436990C | 2010-07-07 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00004 | 80735000 | 78762000 | 2016-01-09 | 2016-12-12
| 2015 | Navy Active | N68436993 |  | 2015-09-30 | 2016-08-30 | WATTS-ORION JV | N4425516C7004 AWD | 32047000 | 28077000 | 2018-02-06 | 2018-02-06
| 2012 | Navy Active | N68539184 |  | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101000 | 29985000 | 2015-07-30 | 2016-04-30
| 2014 | Navy Active | N69212461 |  | 2015-07-24 | 2015-09-29 | VIRTEXCO CORPORATION | N4008515C0043 AWD | 14051000 | 13462000 | 2017-02-25 | 2017-05-03
| 2015 | Navy Active | N69212991 |  | 2015-08-05 | 2016-03-08 | PURCELL CONSTRUCTION CORP. | N4008516C6145 AWD | 20817000 | 19797000 | 2018-03-23 | 2018-03-23
| 2015 | Navy Active | N69212992 |  | 2015-03-13 | 2015-09-29 | OCEAN CONSTRUCTION SERVICES | N4008515D0095 AWD | 5272000 | 5047000 | 2016-09-28 | 2017-09-28
| 2016 | Navy Active | N69232565 |  | 2016-01-25 | 2016-03-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247315D2426 0003 | 20557000 | 19948000 | 2017-04-14 | 2017-04-14
| 2014 | Navy Active | N69232593 |  | 2014-04-30 | 2015-01-16 | I E PACIFIC INC | N6247309D1657 0019 | 18400000 | 17650000 | 2016-09-17 | 2017-03-28
| 2014 | Navy Active | N69232599 |  | 2014-11-23 | 2014-11-24 | NAVY STANDARD DOCUMENT | N6247314RP00165 | 33594000 | 30093000 | 2016-03-12 | 2016-03-12
| 2016 | Navy Active | N69232607 |  | 2016-03-24 | 2016-08-25 | I E PACIFIC INC | N6247311D0066 0008 | 3892000 | 3562000 | 2017-11-08 | 2017-11-08
| 2013 | Navy Active | N69232900 |  | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301000 | 9198000 | 2014-11-21 | 2015-10-31
| 2014 | Navy Active | N83447136 |  | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19616000 | 19557000 | 2016-02-12 | 2016-06-19
| 2015 | Navy Reserve | N00129664 |  | 2015-08-24 | 2015-08-25 | VETERANS CONSTRUCTION, LLC | N4008515C9610 AWD | 1989000 | 1906000 | 2016-09-08 | 2016-09-08
| 2013 | Navy Reserve | N00206470 |  | 2013-04-23 | 2015-09-01 | WEBCO L.L.C. | N6945015D0612 0002 | 9648000 | 10058000 | 2017-03-09 | 2017-04-30
| 2016 | Navy Reserve | N00206509 |  | 2016-08-01 | 2016-09-30 | AMES 1 , LLC | N6945016C6534 | 1372000 | 1290000 | 2017-09-29 | 2017-09-29
| 2015 | Navy Reserve | N00207278 |  | 2015-07-30 | 2015-09-30 | SWEAT LLC | N6945015C1113 AWD | 1699000 | 1732000 | 2016-10-14 | 2016-11-13
2017-02-15 | 2015 | Special Operations Command | 36977 |  | 2015-04-15 | 2015-08-20 | Walsh Group Ventures | W912QR-15-C-0021 / 43320000 | 14851000 | 15300000 | 2017-03-03 | 2017-10-17
2016-11-30 | 2016 | Special Operations Command | 47942 |  | 2015-12-22 | 2016-06-24 | Medvolt LLC | W9128F-16-C-0033 | 9065868 | 9065868 | 2017-03-01 | 2017-03-01
2017-02-15 | 2016 | Special Operations Command | 47942 |  | 2015-12-22 | 2016-06-24 | Medvolt LLC | W9128F-16-C-0033 / 38804715 | 9066000 | 9066000 | 2018-01-04 | 2018-03-05
2017-02-15 | 2013 | Special Operations Command | 53542 |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546920 | 6654000 | 2016-02-07 | 2016-05-20
2017-02-15 | 2014 | Special Operations Command | 61064 |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951000 | 14335000 | 2016-05-10 | 2017-02-17
2017-02-15 | 2013 | Special Operations Command | 65052 |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199999 | 3272000 | 2015-08-25 | 2015-04-17
2017-02-15 | 2011 | Special Operations Command | 65395 |  | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391578 | 15637173 | 2013-06-19 | 2014-07-31
2017-02-15 | 2013 | Special Operations Command | 66597 |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384894 | 3376000 | 2015-10-21 | 2016-04-29
2017-02-15 | 2012 | Special Operations Command | 66598 |  | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350000 | 35586000 | 2014-02-15 | 2015-05-05
2017-02-15 | 2014 | Special Operations Command | 68526 |  | 2014-03-26 | 2015-04-09 | Barlovento, LLC | W91278-10-D-0058-DQ01 | 10815034 | 12125000 | 2017-04-07 | 2017-04-17
2017-02-15 | 2013 | Special Operations Command | 69257 |  | 2014-03-11 | 2015-04-01 | Pease Construction, Inc. | W912DW-15-C-0003 | 4484160 | 4895000 | 2016-09-15 | 2017-01-22
2017-02-15 | 2013 | Special Operations Command | 69287a |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907435 | 31157000 | 2015-05-13 | 2016-06-15
2017-02-15 | 2013 | Special Operations Command | 69287b |  | 2014-05-14 | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404000 | 25361000 | 2016-11-01 | 2017-05-14
2017-02-15 | 2013 | Special Operations Command | 69382 |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816000 | 26046000 | 2015-08-14 | 2015-11-04
2017-02-15 | 2013 | Special Operations Command | 69445 |  | 2013-02-01 | 2015-05-07 | RQ Construction LLC | W912DW-15-C-0006 | 45104000 | 46386000 | 2017-05-25 | 2017-08-01
2017-02-15 | 2014 | Special Operations Command | 69446 |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083965 | 15665000 | 2016-02-08 | 2016-06-15
2017-02-15 | 2013 | Special Operations Command | 69447 |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123180 | 22826000 | 2016-02-13 | 2016-04-29
2017-02-15 | 2012 | Special Operations Command | 69458 |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772305 | 16854000 | 2014-06-03 | 2016-02-15
2017-02-15 | 2013 | Special Operations Command | 69493 |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085000 | 23066000 | 2016-07-18 | 2016-12-12
2017-02-15 | 2012 | Special Operations Command | 69758 |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 16429000 | 16005000 | 2014-05-08 | 2016-12-06
2017-02-15 | 2012 | Special Operations Command | 71224 |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525847 | 18831000 | 2014-05-01 | 2015-04-27
2017-02-15 | 2012 | Special Operations Command | 76364 |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201303 | 33465000 | 2014-08-26 | 2016-04-01
2017-02-15 | 2014 | Special Operations Command | 76365 |  | 2015-07-15 | 2015-11-12 | B.L. Harbert International, LLC | W912QR-16-C-0002/38708732 | 22740000 | 23147000 | 2017-10-02 | 2017-12-31
2017-02-15 | 2012 | Special Operations Command | 76366 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673727 | 15674302 | 2015-09-12 | 2016-04-26
2017-02-15 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-10 | Raass Brothers, Inc | W9128F-14-C-0018/43307123 | 8983000 | 9568000 | 2017-03-01 | 2017-06-15
2017-02-15 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441000 | 37500000 | 2016-07-20 | 2016-12-30
2017-02-15 | 2012 | Special Operations Command | 76371 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092801 | 17224000 | 2015-09-12 | 2016-01-27
2017-02-15 | 2014 | Special Operations Command | 76375 |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358000 | 27527000 | 2016-07-23 | 2017-01-19
2017-02-15 | 2014 | Special Operations Command | 76376 |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696668 | 53678000 | 2017-06-27 | 2018-01-15
2017-02-15 | 2016 | Special Operations Command | 76518 |  | 2015-11-23 | 2016-03-17 | Bristol Environmental Remediation Servic | W912DY-12-D-0053 | 8465006 | 8465006 | 2017-06-01 | 2017-08-15
2017-02-15 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | Nishimatsu Construction Co., Ltd. | W912HV-15-004 / 35808936 | 54777000 | 54821000 | 2017-12-12 | 2018-04-05
2017-02-15 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | Nishimatsu Construction Co., Ltd. | W912HV-15-C-0004 / 35808936 | 46555863 | 61266000 | 2017-12-12 | 2018-04-05
2017-02-15 | 2015 | Special Operations Command | 79437 |  | 2016-06-27 | 2016-09-28 | SAUER Incorporated, d/b/a Sauer Southeast | W91278-12-D-0039 / 43665546 | 38618000 | 38618000 | 2018-10-18 | 2019-06-25
2017-02-15 | 2014 | Special Operations Command | 79438 |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7194000 | 7402000 | 2016-04-19 | 2016-12-05
2017-02-15 | 2014 | Special Operations Command | 79440 |  | 2014-12-15 | 2015-04-30 | ARGO SYSTEMS, LLC | N6945014D1271 0003 | 4140000 | 3990000 | 2016-08-22 | 2016-11-11
2017-02-15 | 2015 | Special Operations Command | 79456 |  | 2015-05-21 | 2015-08-31 | Lifecycle Construction Services, LLC | W912HN-13-D-0002-DQ01 | 5798000 | 5817000 | 2016-11-11 | 2017-02-13
2017-02-15 | 2016 | Special Operations Command | 80773 |  | 2016-07-27 | 2016-11-21 | ACC Construction Co., Inc. | W912PM-17-C-0001 / 46240484 | 32661 | 32661 | 2019-01-31 | 2019-07-29
2017-02-15 | 2016 | Special Operations Command | 81897 |  | 2015-12-18 | 2016-11-18 | BUTT CONSTRUCTION COMPANY, INC | W912QR-17-C-0002 / 46150444 | 11975 | 11988 | 2018-08-26 | 2018-10-25
2017-02-15 | 2011 | Special Operations Command | CZQZ063052A |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13829000 | 13829042 | 2013-07-17 | 2014-06-03
2017-02-15 | 2016 | Special Operations Command | FTEV073010 |  | 2016-03-19 | 2016-08-02 | Cutter Enterprises, LLC | W91278-16-C-0021 / 53891665 | 14173 | 14173 | 2018-09-15 | 2018-12-14
2017-02-15 | 2014 | Special Operations Command | FTEV083002 |  | 2014-05-01 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 48908883 | 1573300 | 1603464 | 2016-05-24 | 2016-10-20
2017-02-15 | 2014 | Special Operations Command | FTEV083002 |  | 2014-05-01 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048867 | 7230868 | 2016-05-24 | 2016-10-20
2017-02-15 | 2013 | Special Operations Command | FTFA113004 |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942300 | 30416000 | 2016-12-25 | 2017-04-06
2017-02-15 | 2013 | Special Operations Command | NVZR083702 |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753024 | 27764000 | 2015-06-28 | 2016-09-30
2017-02-15 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co. | W91278-12-D-0038 / 44336728 | 20933 | 20933 | 2019-01-26 | 2019-04-26
2017-02-15 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co. | W91278-12-D-0038 / 54346656 | 13223 | 13223 | 2019-01-26 | 2019-04-26
2017-02-15 | 2012 | Special Operations Command | P-1049 |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648#0003 | 8129000 | 8774782 | 2014-11-13 | 2016-03-16
2017-02-15 | 2012 | Special Operations Command | P-1049 |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129000 | 8767000 | 2014-11-13 | 2015-11-13
2017-02-15 | 2015 | Special Operations Command | P-1119 |  | 2015-08-14 | 2015-09-29 | Cox Construction Company | N62473-15-D-2405-0003 | 11080000 | 11080000 | 2017-04-06 | 2017-04-06
2017-02-15 | 2015 | Special Operations Command | P-1119 |  | 2015-08-05 | 2015-09-29 | COX CONSTRUCTION CO | N6247315D2405 0003 | 12428000 | 11835000 | 2016-04-06 | 2017-04-06
2017-02-15 | 2016 | Special Operations Command | P-1126 |  | 2016-05-10 | 2016-08-08 | A&D GC INC | N6247315D2403 0005 | 10911000 | 10226000 | 2018-02-14 | 2018-02-14
2017-02-15 | 2013 | Special Operations Command | P-1218 |  | 2013-06-11 | 2013-09-19 | RQ-DPR JV | N4008513C6000 AWD | 47295000 | 49463000 | 2016-01-18 | 2016-12-02
2017-02-15 | 2013 | Special Operations Command | P-1218 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370000 | 48044000 | 2016-03-01 | 2016-05-31
2017-02-15 | 2014 | Special Operations Command | P-1391 |  | 2014-05-29 | 2014-08-28 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0004 | 30963000 | 30625000 | 2016-09-02 | 2017-02-25
2017-02-15 | 2014 | Special Operations Command | P-1391 |  | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333#0004 | 27547000 | 27858000 | 2016-09-02 | 2016-09-02
2017-02-15 | 2013 | Special Operations Command | P-1393 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370000 | 48044000 | 2016-01-18 | 2016-05-31
2017-02-15 | 2013 | Special Operations Command | P-1393 |  | 2013-06-11 | 2013-09-19 | RQ-DPR JV | N4008513C6000 AWD | 4903000 | 4781000 | 2016-01-18 | 2016-12-02
2017-02-15 | 2015 | Special Operations Command | P-1396 |  | 2015-05-29 | 2015-08-17 | The Whiting-Turner Contracting Co | N40085-10-D-5330-0012 | 9128684 | 9128684
2017-02-15 | 2015 | Special Operations Command | P-1396 |  | 2015-05-29 | 2015-08-17 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0012 | 10331000 | 10164000 | 2017-03-09 | 2017-04-15
2017-02-15 | 2014 | Special Operations Command | P-157 |  | 2014-11-13 | 2016-02-26 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0008 | 19230000 | 18464000 | 2017-09-03 | 2017-09-03
2017-02-15 | 2014 | Special Operations Command | P-157 |  | 2014-10-24 | 2016-02-26 | DPR Hardin Construction-WGI JV | N40085-10-D-5333 #0008 | 17300000 | 17300000 | 2017-09-03 | 2017-09-03
2017-02-15 | 2012 | Special Operations Command | P-164 |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727000 | 18855000 | 2014-07-24 | 2015-06-16
2017-02-15 | 2013 | Special Operations Command | P-165 |  | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351000 | 10272000 | 2015-09-09 | 2015-11-26
2017-02-15 | 2015 | Special Operations Command | P-166 |  | 2015-05-05 | 2015-09-21 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0011 | 13588000 | 12536000 | 2017-07-17 | 2017-08-31
2017-02-15 | 2015 | Special Operations Command | P-170 |  | 2015-03-10 | 2016-01-26 | PENTACON, LLC | N6945014D0757 0002 | 10593000 | 10268000 | 2017-10-17 | 2017-11-28
2017-02-15 | 2015 | Special Operations Command | P-183 |  | 2014-04-17 | 2015-08-12 | CLARK NEXSEN - CH2M HILL - NORFOLK | N6247011D1010 WE11 | 15050000 | 15178000 | 2017-07-24 | 2017-07-24
2017-02-15 | 2014 | Special Operations Command | P-334 |  | 2015-07-21 | 2016-02-10 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0007 | 29668000 | 28655000 | 2018-07-29 | 2018-07-29
2017-02-15 | 2014 | Special Operations Command | P-334 |  | 2015-07-21 | 2016-02-10 | DPR Hardin Construction-WGI JV | N40085-10_D-5333 | 26731230 | 26731230 | 2018-07-01 | 2018-07-01
2017-02-15 | 2015 | Special Operations Command | P-418 |  | 2015-06-12 | 2015-08-18 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0006 | 20585000 | 21104000 | 2017-02-23 | 2017-04-06
2017-02-15 | 2012 | Special Operations Command | P-473 |  | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366000 | 27585000 | 2015-12-27 | 2015-12-27
2017-02-15 | 2013 | Special Operations Command | P-475 |  | 2014-07-31 | 2016-01-25 | BETHEL-WEBCOR JV-1 | N6247814D4001 0006 | 22462000 | 21311000 | 2018-02-13 | 2018-04-03
2017-02-15 | 2013 | Special Operations Command | P-576 |  | 2016-03-17 | 2016-07-15 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N4008515D0096 0003 | 2519000 | 2457000 | 2016-08-14 | 2017-08-14
2017-02-15 | 2012 | Special Operations Command | P-769 |  | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022000 | 4067000 | 2014-06-27 | 2015-02-20
2017-02-15 | 2015 | Special Operations Command | P-776 |  | 2015-08-26 | 2015-09-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247315D2426 0002 | 30528000 | 31024000 | 2017-10-23 | 2017-10-23
2017-02-15 | 2012 | Special Operations Command | P-797 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N6247315C1609 AWD | 36213000 | 33958000 | 2018-04-02 | 2018-04-02
2017-02-15 | 2012 | Special Operations Command | P-826 |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139000 | 18855000 | 2014-07-24 | 2015-06-16
2017-02-15 | 2013 | Special Operations Command | P-876 |  | 2014-05-05 | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290000 | 24440000 | 2016-10-01 | 2016-10-07
2017-02-15 | 2013 | Special Operations Command | P-876 |  | 2014-05-05 | 2014-09-26 | RQ CONSTRUCTION, LLC | N6247310D5409 0015 | 27636000 | 27279000 | 2016-10-07 | 2016-10-07
2017-02-15 | 2013 | Special Operations Command | P-888 |  | 2014-04-01 | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489000 | 15440000 | 2016-09-30 | 2016-09-29
2017-02-15 | 2013 | Special Operations Command | P-888 |  | 2014-04-01 | 2014-09-30 | KOO CONSTRUCTION INC | N6247309D1655 0005 | 14869000 | 13694000 | 2016-09-29 | 2017-11-08
2017-02-15 | 2015 | Special Operations Command | P-893 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N6247315C1609 AWD | 24873000 | 23643000 | 2018-04-02 | 2018-04-02
2017-02-15 | 2013 | Special Operations Command | P-915 |  | 2015-02-12 | 2015-09-10 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0011 | 10605000 | 10038000 | 2017-03-18 | 2017-03-18
2017-02-15 | 2016 | Special Operations Command | P-920 |  | 2016-05-12 | 2016-09-20 | RQ CONSTRUCTION, LLC | N6247315D2428 0003 | 47022000 | 43643000 | 2018-10-13 | 2018-10-13
2017-01-19 | 2010 | Washington Headquarters Services | 80001 |  | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power | HQ0034-13-C-0133 | 9669575 | 10923401 | 2015-02-05 | 2015-09-14
2017-01-19 | 2010 | Washington Headquarters Services | 80001 |  | 2013-09-01 | 2013-09-30 | Virginia Electric and Power Company | HQ0034-13-F-0027 | 13679273 | 13679273 | 2015-01-31 | 2015-01-31
2017-01-19 | 2011 | Washington Headquarters Services | 80002 |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. | HQ0034-13-C-0062 | 43594000 | 47760814 | 2016-05-11 | 2017-03-19
2017-01-19 | 2011 | Washington Headquarters Services | 80003 |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. | W912DR-11-R-0060 | 5609000 | 6357500 | 2015-05-03 | 2016-07-01
2017-01-19 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2016-09-30 | Turtle Associates | W912DR-16-C-0039 | 6814002 | 6814002 | 2018-04-30 | 2018-04-30
2016-09-15 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC | W912DR-11-R-0062 | 5454000 | 5492659 | 2015-05-01 | 2015-10-01
2016-12-15 | 2012 | Washington Headquarters Services | 80005
2016-12-15 | 2012 | Washington Headquarters Services | 80006
2017-01-19 | 2014 | Washington Headquarters Services | 80007
2017-01-19 | 2014 | Washington Headquarters Services | 80008 |  | 2016-02-11 | 2016-04-29 | ACS | W912DR-16-C-0009 | 5797373 | 5797373 | 2017-12-01 | 2017-12-01
2017-01-19 | 2014 | Washington Headquarters Services | 80009 |  | 2016-08-12
2017-01-19 | 2014 | Washington Headquarters Services | 80010
2017-01-19 | 2015 | Washington Headquarters Services | 80011

## EXPENDITURES
Expenditure Data as of Date | Appropriation Fiscal Year | Project Sponsor Component Name | Appropriation Fund Type Name | Use of Funds | Aggregated Appropriated Amount | Aggregated Current Obligated Amount | Aggregated Current Expenditure Amount
2017-02-15 | 2007 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232000 | 329292795 | 329291135
2017-02-15 | 2016 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 150649000 | 0 | 0
2017-02-15 | 2008 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 238674552 | 238683341 | 238071215
2017-02-15 | 2010 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558000 | 59491476 | 59491476
2017-02-15 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093000 | 52269934 | 42470383
2017-02-15 | 2012 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407000 | 22904340 | 22503913
2017-02-15 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936577 | 3294004 | 3284180
2017-02-15 | 2009 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513728 | 205771643 | 205498285
2017-02-15 | 2011 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192950 | 70280847 | 66639665
2017-02-15 | 2006 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773860 | 281664955 | 281661594
2017-02-15 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-02-15 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-02-15 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-02-15 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-02-15 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-02-15 | 2015 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-02-15 | 2016 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-02-15 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing. Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - | 0 | 0 | 0
2017-02-15 | 2008 | Air Force Active | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 30148000 | 29576067 | 29329943
2017-02-15 | 2016 | Air Force Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 89164000 | 76774184 | 52293759
2017-02-15 | 2012 | Air Force Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 78413000 | 78298278 | 76143532
2017-02-15 | 2013 | Air Force Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 410408 | 374528 | 266569
2017-02-15 | 2010 | Air Force Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 87562000 | 86869706 | 85968503
2017-02-15 | 2007 | Air Force Active | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 74021000 | 72589483 | 72587358
2017-02-15 | 2009 | Air Force Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105506000 | 103418809 | 103007142
2017-02-15 | 2011 | Air Force Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 63903328 | 62904715 | 62654263
2017-02-15 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 22238000 | 10617815 | 8940026
2017-02-15 | 2014 | Air Force Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314000 | 11306975 | 11093023
2017-02-15 | 2006 | Air Force Active | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 63753948 | 60476986 | 59548924
2017-02-15 | 2012 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056000 | 4055206 | 4055206
2017-02-15 | 2010 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302000 | 1396578 | 1396578
2017-02-15 | 2009 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703000 | 7524947 | 7524947
2017-02-15 | 2016 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 9849000 | 3085996 | 2048032
2017-02-15 | 2007 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064000 | 12735924 | 12735924
2017-02-15 | 2006 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782960 | 27379308 | 26595117
2017-02-15 | 2013 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3951846 | 3933368 | 3840654
2017-02-15 | 2014 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267000 | 3888540 | 3646160
2017-02-15 | 2008 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210000 | 12161823 | 12161823
2017-02-15 | 2011 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153000 | 3921567 | 3921567
2017-02-15 | 2006 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 19369988 | 16716208 | 15244277
2017-02-15 | 2009 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15927089 | 15778887 | 15778887
2017-02-15 | 2008 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20741321 | 16952139 | 16952139
2017-02-15 | 2007 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 24108245 | 17277124 | 17217001
2017-02-15 | 2016 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22900000 | 3151131 | 0
2017-02-15 | 2011 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 67607214 | 42233959 | 38356736
2017-02-15 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22612999 | 3197657 | 662349
2017-02-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20447998 | 13598607 | 7784316
2017-02-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 18175975 | 17753599 | 17207617
2017-02-15 | 2012 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 19999992 | 19868001 | 18550914
2017-02-15 | 2010 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 34999994 | 31661200 | 31183756
2017-02-07 | 2011 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649694 | 1521061 | 1521061
2017-02-07 | 2016 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 13400000 | 0 | 0
2017-02-07 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892000 | 741524 | 218201
2017-02-07 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229000 | 1805573 | 701099
2017-02-07 | 2013 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875201 | 2362653 | 2155523
2017-02-07 | 2012 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200000 | 2117881 | 2082312
2017-02-07 | 2010 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139000 | 8001719 | 6000916
2017-02-07 | 2009 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165000 | 6133583 | 6123256
2017-02-07 | 2008 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300000 | 5270797 | 5270797
2017-02-07 | 2007 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109000 | 5072462 | 5072462
2017-02-07 | 2006 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289570 | 5289120 | 5289120
2017-02-07 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5434000 | 4216309 | 3745090
2017-02-07 | 2011 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2753482 | 2728949 | 2651597
2017-02-07 | 2010 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 800000 | 752889 | 752889
2017-02-07 | 2009 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443000 | 5442927 | 5442927
2017-02-07 | 2008 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909000 | 4909000 | 4909000
2017-02-07 | 2007 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477000 | 4476971 | 4476971
2017-02-07 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6121000 | 0 | 0
2017-02-07 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400000 | 0 | 0
2017-02-07 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530000 | 0 | 0
2017-02-07 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997361 | 355600 | 38552
2017-02-07 | 2006 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960000 | 3959698 | 3959698
2017-02-15 | 2007 | Air National Guard | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050000 | 19043340 | 19043339
2017-02-15 | 2016 | Air National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 5104000 | 2604806 | 37369
2017-02-15 | 2017 | Air National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY98 MILCON; fund Congressionally directed designs. | 10462000 | 119010 | 0
2017-02-15 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700000 | 5877156 | 2950813
2017-02-15 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400000 | 12873919 | 9986134
2017-02-15 | 2013 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994721 | 3980871 | 3967377
2017-02-15 | 2012 | Air National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225000 | 12194974 | 12158471
2017-02-15 | 2011 | Air National Guard | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195572 | 9150973 | 9045613
2017-02-15 | 2010 | Air National Guard | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670441 | 19601297 | 19514664
2017-02-15 | 2009 | Air National Guard | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056000 | 19040836 | 19005487
2017-02-15 | 2008 | Air National Guard | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721000 | 10619035 | 10619035
2017-02-15 | 2006 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006000 | 28018596 | 28018596
2017-02-15 | 2007 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000000 | 5999999 | 5999999
2017-02-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000000 | 9000000 | 8717175
2017-02-15 | 2013 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892214 | 5883163 | 5868450
2017-02-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000000 | 12516762 | 8576919
2017-02-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6100000 | 5833305 | 4342094
2017-02-15 | 2016 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7734000 | 6936044 | 2294721
2017-02-15 | 2006 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882000 | 6882000 | 6882000
2017-02-15 | 2010 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913559 | 44874037 | 44638026
2017-02-15 | 2009 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243000 | 34243000 | 34235708
2017-02-15 | 2008 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184000 | 14184000 | 14184000
2017-02-15 | 2011 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984000 | 7975387 | 7975387
2017-01-31 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000000 | 33872908 | 33872908
2017-01-31 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36500000 | 35998001 | 35856668
2017-01-31 | 2011 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 42944000 | 42931330 | 42931330
2017-01-31 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000000 | 24984362 | 24984362
2017-01-31 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000000 | 22942800 | 22897830
2017-01-31 | 2015 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28000000 | 27767035 | 27320845
2017-01-31 | 2016 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36000000 | 19877886 | 17091597
2017-01-31 | 2017 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 18000000 | 0 | 0
2017-01-31 | 2013 | Army Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46173000 | 45974633 | 44300653
2017-01-31 | 2010 | Army Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 305903000 | 266114891 | 265311277
2017-01-31 | 2011 | Army Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 379238000 | 263299302 | 261598505
2017-01-31 | 2012 | Army Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 265741000 | 253719770 | 248985322
2017-01-31 | 2014 | Army Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575000 | 40061821 | 39695297
2017-01-31 | 2015 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 23127000 | 22746479 | 22265690
2017-01-31 | 2016 | Army Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 73245000 | 42480371 | 28998763
2017-01-31 | 2017 | Army Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 80159000 | 0 | 0
2017-01-31 | 2010 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 3936000 | 3224336 | 2745401
2017-01-31 | 2011 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2036000 | 2029690 | 1578746
2017-01-31 | 2012 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7897000 | 7863796 | 7600996
2017-01-31 | 2016 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7195000 | 5974012 | 5382086
2017-01-31 | 2013 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4641000 | 4604683 | 4459767
2017-01-31 | 2015 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 1309000 | 1031133 | 508577
2017-01-31 | 2014 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4408000 | 2428499 | 2352704
2016-12-31 | 2017 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 35000000 | 0 | 0
2017-01-31 | 2012 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 20000000 | 19965201 | 19679235
2017-01-31 | 2011 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 28704000 | 28694262 | 28693975
2017-01-31 | 2010 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 31250000 | 31240730 | 30517798
2017-01-31 | 2016 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 4642581 | 603927
2017-01-31 | 2015 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 21662151 | 8550528
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 23068581 | 18291862
2017-01-31 | 2013 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 24618245 | 23895435
2017-02-06 | 2016 | Army National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20337000 | 240000 | 240000
2017-02-06 | 2014 | Army National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930000 | 8059000 | 8059000
2017-02-06 | 2013 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17; Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 28155000 | 27486000 | 27486000
2016-12-06 | 2012 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191000 | 20125000 | 20125000
2017-02-06 | 2017 | Army National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20337000 | 240000 | 240000
2017-02-06 | 2015 | Army National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 17600000 | 7241000 | 7241000
2016-12-06 | 2012 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14149000 | 14227000 | 14227000
2017-02-06 | 2013 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14562000 | 14562000 | 14562000
2017-02-06 | 2014 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 12240000 | 12088000 | 12088000
2017-02-06 | 2015 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 13720000 | 5656000 | 5656000
2017-02-06 | 2017 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 12001000 | 0 | 0
2017-02-06 | 2016 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 15000000 | 167000 | 167000
2016-02-22 | 2012 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34331000 | 34331000
2016-02-24 | 2013 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 30636000 | 30636000
2016-02-26 | 2016 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For Design of projects from 2014 to 2019 | 31772000 | 363952 | 363952
2015-11-05 | 2013 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2265551 | 2265551
2015-11-05 | 2011 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 5247000 | 3801453 | 3801453
2015-02-28 | 2012 | Defense Finance and Accounting Service | Planning and Design - Military Construction | Investigation and Design | 1992 | 712 | 711
2015-02-28 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction | Construction | 15404 | 13902 | 13713
2017-01-31 | 2015 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 4855000 | 0 | 0
2017-01-31 | 2016 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 94000 | 0 | 0
2017-01-31 | 2013 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 97411000 | 10746000 | 4642000
2017-01-31 | 2012 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 66449000 | 59142000 | 19528000
2017-01-31 | 2011 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 181781000 | 172111000 | 146197000
2017-01-31 | 2010 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 72679000 | 72449000 | 69641000
2017-01-31 | 2009 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 171255000 | 170779000 | 166457000
2017-01-31 | 2014 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 244000 | 0 | 0
2017-01-31 | 2017 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2017-01-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4100000 | 0 | 0
2017-01-31 | 2017 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 8500000 | 0 | 0
2017-01-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4608000 | 4603000 | 3660000
2017-01-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5930000 | 5522000 | 5233000
2017-01-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 3373000 | 2758000 | 2758000
2017-01-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5547000 | 3984000 | 3984000
2017-01-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 3979000 | 3979000 | 3979000
2017-01-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 9578000 | 4649000 | 3083000
2017-01-31 | 2016 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5000000 | 0 | 0
2015-10-30 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction |  | 12216000 | 11471000 | 146000
2015-10-30 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2615000 | 46800 | 5000
2015-10-30 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 79739000 | 69643972 | 57967778
2015-08-31 | 2012 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for DIAC Parking Garage Replacement; P&D for DIAC Chilled Water Project for Data Center ($125K) and P&D for DIAC Cooling Tower for Data Center ($105K); P&D for UPS for Data Center Installation; P&D for Construction of JUIAF RDF | 2914673 | 73272 | 2841401
2015-08-31 | 2010 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for K-16 FOB-K renovation of two buildings to include Administrative and SCIF Spaces | 442000 | 0 | 442000
2015-08-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 27241500 | 27415000
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2015 to 2018 | 6978000 | 0 | 0
2015-08-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction |  | 0 | 0 | 0
2015-08-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of projects from 2012 to 2016 | 36093000 | 35966000 | 35966000
2015-08-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34239000 | 34239000
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2013 to 2016 | 7430000 | 0 | 0
2015-08-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2015 to 2019 | 5932000 | 0 | 0
2015-08-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 4864000 | 4501000 | 4501000
2015-08-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2014 | 6312000 | 6312000 | 6312000
2015-08-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2266000 | 2266000
2017-01-06 | 2008 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI andFY 08/09/ 10/11/12 MILCON projects | 5159000 | 5159000 | 5159000
2017-01-06 | 2016 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42183000 | 0 | 0
2017-01-06 | 2014 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 14/15/16/17 MILCON projects | 75905000 | 59764000 | 56192000
2017-01-06 | 2015 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42387000 | 0 | 0
2017-01-06 | 2013 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 13/14/15/16 MILCON projects | 97290000 | 97272000 | 97272000
2017-01-06 | 2010 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 10/11/ 12/13 MILCON projects | 8755000 | 8755000 | 8755000
2017-01-06 | 2011 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 11/12/ 13 MILCON projects | 75242000 | 75240000 | 75240000
2017-01-06 | 2012 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 12/13 MILCON projects | 64551000 | 64229000 | 64229000
2017-01-06 | 2009 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13593000 | 13592000 | 13592000
2017-01-06 | 2014 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5409000 | 0 | 0
2017-01-06 | 2015 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 6846000 | 0 | 0
2017-01-06 | 2013 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3771000 | 1312000 | 1312000
2017-01-06 | 2009 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5000 | 4000 | 4025
| 2014 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 24253000 | 23614000 | 20148000
| 2015 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 15940000 | 13309000 | 13026000
| 2016 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 7857000 | 6457000 | 0
| 2017 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 11047000 | 0 | 0
| 2013 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 17441000 | 17270000 | 16699000
2016-01-31 | 2012 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 25327000 | 23639000 | 23639000
2016-01-31 | 2012 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719000 | 719000 | 719000
| 2017 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 693000 | 0 | 0
| 2013 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455000 | 445000 | 445000
| 2014 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463000 | 462000 | 462000
| 2015 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 472000 | 75000 | 75000
| 2016 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 613000 | 0 | 0
2017-01-31 | 2016 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY17-18 MILCON Projects | 12664000 | 0 | 0
2017-01-31 | 2014 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY14-16 MILCON Projects | 10891000 | 10882225 | 10875051
2017-01-31 | 2015 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY16-17 MILCON Projects | 26290000 | 26272164 | 22604374
2017-01-31 | 2013 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY13-14 MILCON Projects | 4191000 | 4167420 | 4138660
2017-01-31 | 2015 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY15/16 | 2000000 | 252974 | 146456
2017-01-31 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000000 | 1694187 | 1359853
2017-01-31 | 2013 | National Security Agency | Construction - Major Military Construction | MOD II, VCP1, Mountainview, HPCC2, ICECUBE, ECB1, HPCC1 | 511067383 | 504667652 | 436398782
2017-01-31 | 2014 | National Security Agency | Construction - Major Military Construction | HPCC2, ECB1 | 507598526 | 506998526 | 480112246
2017-01-31 | 2012 | National Security Agency | Construction - Major Military Construction | Mountainview, Whitelaw Wedge, HPCC2, ICECUBE, ECB1, HPCC1, MHS Generator Plant | 333439089 | 333430420 | 306348133
2017-01-31 | 2015 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - North, VCP1, NSAW Feeders - Central, ECB1 | 99728000 | 98193067 | 48781741
2017-01-31 | 2016 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - Central, ECB2 | 68642000 | 67880919 | 21772058
2017-01-31 | 2017 | National Security Agency | Construction - Major Military Construction | ECB2, NSAW Feeders - South, Access Control Facility | 233000000 | 195000000 | 0
2017-01-31 | 2012 | National Security Agency | Planning and Design - Military Construction | General P&D | 23800910 | 23594029 | 22838423
2017-01-31 | 2013 | National Security Agency | Planning and Design - Military Construction | General P&D | 4123616 | 4123616 | 3946026
2017-01-31 | 2017 | National Security Agency | Planning and Design - Military Construction | General P&D | 24000000 | 0 | 0
2017-01-31 | 2016 | National Security Agency | Planning and Design - Military Construction | General P&D | 1078000 | 0 | 0
2017-01-31 | 2015 | National Security Agency | Planning and Design - Military Construction | General P&D | 599000 | 0 | 0
2017-01-31 | 2014 | National Security Agency | Planning and Design - Military Construction | General P&D | 17561473 | 8008347 | 4803686
2017-01-31 | 2013 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 2765000 | 387942 | 0
2017-01-31 | 2017 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3913000 | 0 | 0
2017-01-31 | 2015 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 2994000 | 229414 | 0
2017-01-31 | 2014 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 1500000 | 1415000 | 55792
| 2015 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
| 2013 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 42740000 | 37672000 | 34269000
| 2014 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 44716000 | 32545000 | 29260000
2016-01-31 | 2012 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 68660000 | 66164000 | 50480000
| 2016 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 3658000 | 0 | 0
| 2017 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
| 2016 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 91649000 | 86773000 | 62721000
2016-01-31 | 2012 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 95021000 | 94986000 | 83923000
| 2017 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 88230000 | 10896000 | 10067000
| 2013 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 120717000 | 120659000 | 107008000
| 2014 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 99774000 | 97296000 | 77372000
| 2015 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 44724000 | 40754000 | 31594000
| 2013 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609000 | 3563000 | 3366000
| 2014 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975000 | 2007000 | 1045000
| 2015 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0
| 2016 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 3975000 | 0 | 0
| 2017 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 3456000 | 0 | 0
2016-01-31 | 2012 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2446000 | 2440000 | 2401000
| 2013 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 15612000 | 15084000 | 13488000
2016-01-31 | 2012 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 20919000 | 20672000 | 18816000
| 2014 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 19740000 | 18804000 | 14044000
| 2015 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 7163000 | 6495000 | 2806000
| 2016 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 22590000 | 5406000 | 55000
| 2017 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 29790000 | 0 | 0
2016-01-31 | 2012 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478000 | 2478000 | 2466000
| 2017 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 3783000 | 150000 | 10000
| 2016 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 2208000 | 1399000 | 898000
| 2015 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 2123000 | 2106000 | 2096000
| 2014 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2540000 | 2538000 | 2531000
| 2013 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995000 | 1995000 | 1992000
| 2017 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0
| 2016 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 1468000 | 0 | 0
| 2015 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 4000000 | 2662000 | 1545000
| 2014 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0
| 2013 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0
2016-01-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 2447000 | 2059000 | 1595000
2017-02-15 | 2014 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 36866000 | 33687000 | 33687000
2017-02-15 | 2015 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 24197000 | 20629000 | 20629000
2017-02-15 | 2016 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 31628000 | 14427000 | 14427000
2017-02-15 | 2017 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 27653000 | 0 | 0
2016-12-15 | 2011 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 26469000 | 26468000 | 26468000
2016-12-15 | 2012 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 30308000 | 30303000 | 30303000
2017-02-15 | 2013 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 25454000 | 23434000 | 23434000
2017-02-15 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 9216000 | 9116000 | 9116000
2017-02-15 | 2014 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5170000 | 5003000 | 5003000
2017-02-15 | 2016 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 15676000 | 0 | 0
2017-02-15 | 2017 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5994000 | 0 | 0
2016-12-15 | 2012 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 8487000 | 8447000 | 8447000
2016-12-15 | 2011 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 7531000 | 7526000 | 7526000
2017-02-15 | 2015 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 10334000 | 1847000 | 1847000
2016-09-15 | 2012 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4870000 | 4870000 | 3922831
2017-01-19 | 2016 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 3041000 | 0 | 0
2017-01-19 | 2013 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 7508000 | 4131832 | 1642524
2017-01-19 | 2014 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 6931000 | 0 | 0
2017-01-19 | 2015 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 1183000 | 0 | 0