## PROJECTS
Project Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Construction Project Type Name | State Name | Country Name | Project Number | Project Title | Sub-Project Number | Diverted Funds Total Amount | Diverted Funds Recipient Text | Construction Start Date | Original Construction Completion Date | Current Construction Completion Date | Construction Percent Complete | Current RPA Placed-In-Service Date
2023-01-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | California | United States | ACJP183018 | RELOCATE MAIN GATE ENTRY CONTROL POINT |  |  |  | 2021-08-30 | 2022-11-13 | 2023-01-26 | 57% | 2023-01-26
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Kuwait | AEWV171012 | Dining Facility Addition |  |  |  | 2019-03-27 | 2022-05-20 | 2022-05-27 | 100% | 2022-05-26
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN053009 | FIRE RESCUE CENTER |  |  |  | 2020-04-30 | 2022-04-30 | 2023-06-08 | 79% | 2023-03-14
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN123003 | DORMITORY (120 RM) |  |  |  | 2019-11-06 | 2021-10-26 | 2022-06-10 | 100% | 2022-06-14
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN173001 | KC-46A FTU FTC SIMULATOR FACILITY PHASE 2 |  |  |  | 2017-09-07 | 2018-12-01 | 2019-09-09 | 100% | 2019-09-09
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN213001 | KC-46A FTU Fuselage Trainer Phase 3 |  |  |  | 2019-08-14 | 2021-11-21 | 2022-02-24 | 100% | 2022-03-07
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Guam | AJJY073105P2 | APR - Munitions Storage Igloos, Phase 2 |  |  |  | 2022-01-06 | 2024-02-15 | 2023-11-22 | 6% | 2023-11-22
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Guam | AJJY073105P3 | APSI - MUNITIONS STORAGE IGLOOS PHASE 3 |  |  |  | 2020-10-16 | 2023-06-16 | 2023-06-16 | 83% | 2023-06-16
2023-01-31 | 2022 | Air Force Active | Major Military Construction |  | Guam | AJJY073105P4 | PDI: MUNITIONS STORAGE IGLOOS IV |  |  |  | 2022-06-21 | 2024-04-15 | 2024-04-30 | 14% | 2024-04-30
2023-01-31 | 2013 | Air Force Active | Major Military Construction |  | Guam | AJJY123010 | GUAM STRIKE FUEL SYSTEMS MAINTENANCE HANGAR |  |  |  | 2015-03-18 | 2017-11-21 | 2022-05-09 | 99% | 2022-05-09
2023-01-31 | 2014 | Air Force Active | Major Military Construction |  | Guam | AJJY133027 | PAR - TANKER GP MAINT HANGAR/AMU/SQD OPS |  |  |  | 2015-01-08 | 2017-01-30 | 2021-12-30 | 99% | 2021-12-30
2023-01-31 | 2015 | Air Force Active | Major Military Construction |  | Guam | AJJY133028 | PAR Low Observable/Corrosion Control/Composite Repair Shop |  |  |  | 2016-11-18 | 2018-09-20 | 2023-04-14 | 91% | 2023-04-14
2023-01-31 | 2022 | Air Force Active | Major Military Construction |  | Guam | AJJY163000 | PDI: AIRFIELD DAMAGE REPAIR WAREHOUSE |  |  |  | 2022-05-30 | 2023-11-06 | 2023-11-06 | 6% | 2023-11-06
2023-01-31 | 2019 | Air Force Active | Major Military Construction |  | Guam | AJJY183003 | 3 HAYMAN MUNITIONS STORAGE IGLOOS, MSA 2 |  |  |  | 2022-06-16 | 2024-01-29 | 2024-01-29 | 16% | 2024-01-29
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction |  | Guam | AJJY183017 | CONSOLIDATED CONTINGENCY CENTER |  |  |  | 2020-10-07 | 2022-06-25 | 2022-07-21 | 99% | 2022-07-21
2023-01-31 | 2021 | Air Force Active | Major Military Construction |  | Guam | AJJY203001 | STAND OFF WEAPONS COMPLEX, MSA 2 |  |  |  | 2021-04-04 | 2023-10-23 | 2023-11-17 | 53% | 2023-11-17
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Maryland | United States | AJXF093000 | CONSTRUCT 21 POINT ENCLOSED FIRING RANGE |  |  |  | 2018-05-24 | 2021-05-31 | 2021-05-31 | 100% | 2021-05-31
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Maryland | United States | AJXF133003 | CONSOLIDATED COMMUNICATIONS CENTER AJXF133003 |  |  |  | 2021-06-01 | 2026-02-23 | 2026-02-22 | 9% | 2026-02-22
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Maryland | United States | AJXF156000 | Vehicle Operations Facility |  |  |  | 2019-03-18 | 2023-07-11 | 2020-06-30 | 100% | 2020-06-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Maryland | United States | AJXF173021 | PRESIDENTIAL AIRCRAFT RECAPITALIZATION COMPLEX |  |  |  | 2018-08-19 | 2022-05-30 | 2022-12-30 | 96% | 2022-12-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Maryland | United States | AJXF173030 | SECOND TAXIWAY ACCESS HANGAR 20 - WHISKEY 6 |  |  |  | 2020-09-23 | 2022-02-27 | 2022-12-30 | 98% | 2022-12-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Qatar | ALUA113023 | Consolidated Squadron Operations Facility |  |  |  | 2019-10-28 | 2021-01-20 | 2021-12-28 | 100% | 2022-02-01
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Italy | ASHE143008 | GUARDIAN ANGEL OPERATIONS FACILITY |  |  |  | 2018-11-30 | 2021-07-26 | 2023-03-30 | 40% | 2023-03-30
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | ASPR150126 | ADD AIRFIELD SECURITY FENCE, FACILITY 779 |  |  |  | 2020-12-18 | 2022-01-20 | 2022-01-20 | 100% | 2022-01-20
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF164000 | DINING FACILITY |  |  |  | 2018-09-11 | 2020-03-04 | 2022-11-30 | 100% | 2022-11-30
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100A | OIR: MSAB - AIRFIELD PAVEMENTS |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100B | OIR: MSAB - ISR SHELTERS |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100C | OIR: MSAB - CAS REVETMENTS/SUNSHADES |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Jordan | ASVF183100D | OIR: MSAB - DORMITORY |  |  |  | 2019-04-05 | 2021-10-09 | 2021-10-09 | 100% | 2021-10-09
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100E | OIR: MSAB - CARGO MARSHALLING YARD FACILITY |  |  |  | 2020-06-01 | 2023-07-12 | 2023-07-12 | 52% | 2023-07-12
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Jordan | ASVF183100F | OIR: MSAB - SUPPORTING FACILITIES/UTILITIES |  |  |  | 2018-08-22 | 2021-07-14 | 2022-07-12 | 100% | 2022-07-12
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Jordan | ASVF203110 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2022-07-14 | 2024-08-02 | 2024-08-02 | 9% | 2025-08-01
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Jordan | ASVF203130 | MUNITIONS STORAGE AREA |  |  |  | 2022-09-01 | 2024-11-20 | 2024-11-20 | 2% | 2024-11-20
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Louisiana | United States | AWUB095000 | Consolidated Communication Facility |  |  |  | 2019-07-17 | 2022-01-03 | 2023-01-02 | 69% | 2023-01-02
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Louisiana | United States | AWUB105003 | FIRE STATION NO. 2 |  |  |  | 2018-06-21 | 2020-10-08 | 2021-02-23 | 100% | 2021-02-23
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Iceland | BIKF180001 | ERI: AIRFIELD REPAIRS AND UPGRADES |  |  |  | 2019-08-12 | 2020-04-15 | 2021-02-13 | 100% | 2021-02-13
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190001 | EDI: AIRFIELD UPGRADES - APRON EXPANSION |  |  |  | 2020-09-21 | 2023-03-05 | 2023-04-05 | 99% | 2023-04-05
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190002 | EDI: BEDDOWN SITE PREPARATION |  |  |  | 2020-09-21 | 2023-03-05 | 2024-11-01 | 98% | 2024-11-01
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190003 | EDI: AIRFIELD UPGRADES - DANGEROUS CARGO PAD |  |  |  | 2020-09-09 | 2023-03-05 | 2023-03-01 | 99% | 2023-03-01
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170001 | Construct Chabelley Access Road |  |  |  | 2018-08-05 | 2019-11-01 | 2022-01-27 | 100% | 2022-01-27
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170002 | Construct Parking Apron and Taxiway |  |  |  | 2018-08-05 | 2019-11-01 | 2022-02-22 | 100% | 2022-02-22
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Colorado | United States | CRWU093002 | SBIRS Operations Facility |  |  |  | 2019-02-12 | 2021-04-22 | 2021-12-17 | 99% | 2021-08-16
2023-01-31 | 2019 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | CRWU173001 | Large Vehicle Inspection Point (LVIP) |  |  |  | 2020-10-13 | 2021-12-12 | 2022-03-01 | 100% | 2022-03-01
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Texas | United States | CYRB205940 | JBSA Camp Bullis Dining Facility |  |  |  | 2022-11-15 | 2025-08-31 | 2025-08-31 | 2% | 2025-08-31
2023-01-31 | 2018 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ143001 | Dangerous Cargo Pa Relocate CATM |  |  |  | 2022-10-03 | 2024-06-24 | 2024-06-24 | 3% | 2024-11-22
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | United Arab Emirates | DHAF152900 | LARGE AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2019-09-26 | 2021-10-15 | 2022-10-15 | 100% | 2022-10-15
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | DXEB053005 | FIRE STATION |  |  |  | 2018-05-04 | 2020-07-06 | 2021-10-01 | 100% | 2020-07-31
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Estonia | EEEI150006 | ERI: Construct Bulk Fuel Storage |  |  |  | 2021-08-02 | 2023-04-28 | 2023-04-28 | 79% | 2023-01-01
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Estonia | EEEI180001 | ERI: POL CAPACITY PHASE 2 |  |  |  | 2021-08-02 | 2023-04-28 | 2023-04-28 | 2% | 2023-06-28
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | EEPZ1073283 | MODULAR FIRING RANGE |  |  |  | 2021-09-09 | 2022-12-08 | 2022-12-30 | 81% | 2022-12-08
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Poland | EPPW170003 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2017-11-27 | 2020-03-26 | 2021-01-27 | 100% | 2021-01-27
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Poland | EPPW190001 | EDI: MUNITIONS STORAGE AREA |  |  |  | 2022-05-19 | 2024-11-05 | 2025-01-31 | 7% | 2025-02-03
2023-01-31 | 2017 | Air Force Active | Military Family Housing Improvement |  | Japan | EVKP174535 | IMPROVE FAMILY HOUSING (NORTH FOSTER TOWERS) |  |  |  | 2021-09-01 | 2024-08-31 | 2024-08-31 | 32% | 2024-08-31
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Arizona | United States | FBNV033002 | UPL-Aerospace Ground Equipment (AGE) Complex |  |  |  | 2019-12-10 | 2021-06-02 | 2022-11-10 | 78% | 2023-03-31
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | FBNV163001 | Add/Alter MXG Engine Maintenance Facility |  |  |  | 2020-04-09 | 2021-06-25 | 2021-07-12 | 100% | 2021-07-12
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Delaware | United States | FJXT133000 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2020-04-24 | 2021-12-25 | 2023-09-19 | 60% | 2023-06-11
2023-01-31 | 2016 | Air Force Active | Unspecified Minor Military Construction | Texas | United States | FNWZ100071A | Military Working Dogs Facs - Multi |  |  |  | 2018-10-22 | 2019-10-22 | 2022-12-30 | 99% | 2022-11-04
2023-01-31 | 2017 | Air Force Active | Major Military Construction | California | United States | FSPM053503C | FLIGHT LINE FIRE STATION |  |  |  | 2018-06-19 | 2020-06-18 | 2021-07-15 | 100% | 2020-07-31
2023-01-31 | 2021 | Air Force Active | Major Military Construction | California | United States | FSPM1075894 | FLIGHT TEST ENGINEERING LABORATORY COMPLEX |  |  |  | 2022-03-30 | 2024-05-26 | 2024-05-26 | 4% | 2024-05-26
2023-01-31 | 2019 | Air Force Active | Major Military Construction | California | United States | FSPM173504 | Joint Simulation Environment Facility - Edwards |  |  |  | 2020-09-09 | 2022-08-09 | 2022-12-16 | 83% | 2022-12-02
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA033003 | Flightline Fire Station |  |  |  | 2018-01-29 | 2019-07-23 | 2021-02-11 | 100% | 2021-02-11
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA043000 | Advanced Munitions Technology Complex |  |  |  | 2019-04-24 | 2022-05-12 | 2023-01-18 | 99% | 2023-05-01
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA053017 | Dormitories Replace Dorm 19 |  |  |  | 2019-11-06 | 2021-11-05 | 2023-03-17 | 77% | 2022-11-27
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA093965 | F-35A Student Dormitory II |  |  |  | 2019-05-02 | 2021-05-01 | 2022-01-18 | 100% | 2022-01-18
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | FTFA133002 | CNST AT Entry Control Point North Gate |  |  |  | 2021-06-09 | 2022-06-09 | 2022-12-30 | 95% | 2022-10-30
2023-01-31 | 2019 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | FTFA133003 | New Munitions North Gate Holding Area |  |  |  | 2020-08-12 | 2021-07-12 | 2021-07-12 | 100% | 2021-07-12
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA143913 | F-35A Integrated Trng Center Academics Bldg |  |  |  | 2019-06-11 | 2021-06-10 | 2021-07-30 | 100% | 2021-08-12
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Florida | United States | FTFA163003 | F-35A Armament Research Facility Addition (B614) |  |  |  | 2018-11-01 | 2020-08-22 | 2021-07-15 | 100% | 2021-07-15
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Florida | United States | FTFA163004 | LONG-RANGE STAND-OFF ACQUISITION FACILITY |  |  |  | 2019-10-15 | 2021-10-14 | 2023-04-28 | 77% | 2023-05-26
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA163007 | Cyberspace Test Facility |  |  |  | 2020-11-10 | 2022-10-31 | 2023-04-18 | 87% | 2022-12-08
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1053834 | F-35 Aircraft Maintenance Unit Admin Facility |  |  |  | 2019-08-05 | 2021-08-05 | 2023-10-23 | 98% | 2021-08-05
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1054329 | F-35 Conventional Munitions Maintenance Fac |  |  |  | 2019-10-18 | 2021-08-02 | 2022-08-15 | 93% | 2022-08-15
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1055646 | F-35 AME Storage Facility |  |  |  | 2021-09-09 | 2024-04-16 | 2024-04-16 | 25% | 2024-07-13
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170100 | F-35A ADAL FIELD TRAINING DETACHMENT (FTD) FACILITY |  |  |  | 2017-06-20 | 2019-04-27 | 2019-04-27 | 100% | 2019-04-26
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180107 | F-35A Consolidated Munitions Admin Facility |  |  |  | 2018-04-05 | 2020-02-14 | 2020-06-12 | 99% | 2020-07-02
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180109 | F-35A School Age Facility |  |  |  | 2019-03-12 | 2020-08-01 | 2020-09-24 | 100% | 2021-10-21
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180110 | F-35 CATM Range |  |  |  | 2021-09-16 | 2023-01-09 | 2023-01-09 | 20% | 2023-02-26
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW183001 | F-35A Aircraft Weather Shelter SQD #2 |  |  |  | 2018-06-15 | 2020-05-06 | 2021-03-19 | 100% | 2021-03-19
2023-01-31 | 2021 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM1081508 | B-21 2-Bay LO Restoration Facility |  |  |  | 2021-10-28 | 2024-11-01 | 2024-11-01 | 19% | 2024-11-01
2023-01-31 | 2022 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM1088018 | B-21 Field Training Detachment Facility |  |  |  | 2022-08-12 | 2024-10-20 | 2024-10-20 | 5% | 2024-09-22
2023-01-31 | 2022 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM1088037 | B-21 Mission Operations Planning Facility |  |  |  | 2022-08-12 | 2024-10-20 | 2024-10-20 | 5% | 2024-03-20
2023-01-31 | 2022 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM1093477 | B-21 Formal Training Unit/AMU |  |  |  | 2022-07-27 | 2024-10-04 | 2024-10-04 | 3% | 2024-10-16
2023-01-31 | 2022 | Air Force Active | Major Military Construction | Alaska | United States | FXSB143004 | PDI: EXTEND RUNWAY 16/34 |  |  |  | 2022-08-04 | 2026-01-11 | 2026-01-11 | 2% | 2026-01-11
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FXSB982839 | ADD/ALTER AWACS ALERT HANGAR |  |  |  | 2020-04-20 | 2022-03-11 | 2022-07-15 | 99% | 2022-07-15
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN083004 | MISSILE TRANSFER FACILITY |  |  |  | 2017-06-15 | 2020-07-31 | 2020-08-06 | 100% | 2020-08-06
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN153001 | FE WARREN--WEAPON STORAGE FACILITY |  |  |  | 2019-02-20 | 2022-06-04 | 2023-01-06 | 67% | 2023-03-05
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN983001A | CONSOLIDATED HELO/TRF OPS/AMU AND ALERT FACILITY |  |  |  | 2022-10-24 | 2025-05-19 | 2025-05-19 | 2% | 2025-05-19
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Washington | United States | GJKZ040009 | SERE PIPELINE DORMITORY (150 RM) |  |  |  | 2019-02-22 | 2021-01-22 | 2022-04-08 | 100% | 2022-03-21
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Washington | United States | GJLK1053425 | ADD/ALTER Joint Personnel Recovery Agency Command & Control, Mission Support Facility |  |  |  | 2020-10-20 | 2022-10-10 | 2022-12-29 | 90% | 2022-12-29
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Colorado | United States | GLEN203001 | Consolidated Space Operations Facility |  |  |  | 2021-10-19 | 2025-01-31 | 2025-03-15 | 24% | 2025-05-31
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | North Dakota | United States | JFSD201120 | MUNITIONS MAINTENANCE AND INSPECTION FACILITY |  |  |  | 2021-08-18 | 2023-08-18 | 2023-08-18 | 51% | 2023-08-18
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Texas | United States | KELL123018 | Air Traffic Control Tower |  |  |  | 2022-11-15 | 2025-09-12 | 2025-09-12 | 2% | 2025-09-12
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Hawaii | United States | KNMD043004 | F-22 FIGHTER ALERT FACILITY |  |  |  | 2018-11-01 | 2020-10-22 | 2021-10-29 | 100% | 2021-11-01
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Utah | United States | KRSM1065068 | GBSD Mission Integration Facility |  |  |  | 2020-08-17 | 2023-04-04 | 2023-04-04 | 14% | 2023-06-03
2023-01-31 | 2021 | Air Force Active | Major Military Construction | Utah | United States | KRSM1071882 | GBSD Organic Software Sustainment Center |  |  |  | 2022-05-31 | 2024-02-22 | 2024-02-22 | 2% | 2024-02-22
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Utah | United States | KRSM113031 | Construct East Gate Canopy and Inspection Facility |  |  |  | 2021-01-19 | 2022-01-19 | 2022-12-30 | 96% | 2022-12-31
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Utah | United States | KRSM123009 | UTTR CONSOLIDATED MISSION CONTROL CENTER |  |  |  | 2021-03-24 | 2023-07-24 | 2022-12-26 | 92% | 2023-01-14
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Utah | United States | KRSM143003 | F-35A MUNITIONS MAINTENANCE COMPLEX |  |  |  | 2018-10-18 | 2020-10-17 | 2021-11-15 | 99% | 2021-11-24
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Utah | United States | KRSM183001 | Missile Storage Facility |  |  |  | 2021-08-25 | 2023-08-15 | 2023-08-15 | 17% | 2023-06-02
2023-01-31 | 2020 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD1055707 | NC3 SUPPORT WRM STORAGE/SHIPPING FACILITY |  |  |  | 2021-08-17 | 2023-04-09 | 2023-10-06 | 69% | 2023-07-08
2023-01-31 | 2018 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD143000 | RPA FIXED GROUND CONTROL STATION FACILITY |  |  |  | 2019-09-28 | 2021-09-25 | 2021-10-25 | 100% | 2021-10-25
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Bulgaria | LBPG150008 | ERI: FIGHTER RAMP EXTENSION |  |  |  | 2019-02-11 | 2021-01-21 | 2021-10-07 | 100% | 2021-10-07
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Bulgaria | LBPG150009 | ERI: CONSTRUCT SQUADRON OPERATIONS/OPERATION ALERT FACILITY |  |  |  | 2019-02-11 | 2022-02-11 | 2021-10-07 | 100% | 2021-10-07
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Turkey | LJYC133003 | AIRFIELD FIRE / CRASH RESCUE STATION |  |  |  | 2018-08-30 | 2021-05-16 | 2023-11-20 | 54% | 2024-01-02
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Turkey | LJYC183004 | REPLACE PERIMETER FENCE |  |  |  | 2019-06-11 | 2023-06-07 | 2022-05-12 | 100% | 2022-05-13
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | LKTC203101 | MQ-9 CPIP GCS Operations Facility |  |  |  | 2019-10-13 | 2022-05-23 | 2022-05-23 | 100% | 2022-05-23
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | LKTC203102 | MQ-9 CPIP Ops & Command Center Facility |  |  |  | 2019-11-13 | 2021-11-02 | 2022-10-04 | 98% | 2022-05-23
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150007 | ERI: EXTEND PARKING APRONS |  |  |  | 2018-01-17 | 2020-03-12 | 2023-02-01 | 90% | 2023-03-01
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150008 | ERI: CONSTRUCT MUNITIONS STORAGE AREA |  |  |  | 2016-02-19 | 2020-03-12 | 2021-12-14 | 100% | 2022-02-17
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150009 | ERI: CONSTRUCT ONE-BAY HANGAR |  |  |  | 2018-01-17 | 2020-03-12 | 2023-02-01 | 90% | 2023-03-01
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150010 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2018-01-17 | 2020-03-12 | 2023-02-01 | 90% | 2023-03-01
2023-01-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT190001 | EDI: DANGEROUS CARGO PAD |  |  |  | 2021-07-29 | 2023-08-16 | 2023-08-16 | 24% | 2024-09-10
2023-01-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT190002 | EDI: POL INCREASE CAPACITY |  |  |  | 2018-01-17 | 2024-11-04 | 2025-03-14 | 84% | 2025-03-14
2023-01-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT210001 | EDI-DABS-FEV STORAGE |  |  |  | 2021-09-28 | 2023-05-24 | 2023-05-24 | 12% | 2024-02-08
2023-01-31 | 2021 | Air Force Active | Major Military Construction |  | Romania | LRCT210002 | EDI-AIRCRAFT PARKING APRON |  |  |  | 2021-11-23 | 2023-11-23 | 2024-04-30 | 11% | 2024-04-30
2023-01-31 | 2022 | Air Force Active | Major Military Construction |  | Japan | LXEZ1069456 | PDI: AIRFIELD DAMAGE REPAIR STORAGE FACILITIES |  |  |  | 2022-06-24 | 2024-08-22 | 2024-08-22 | 7% | 2024-08-30
2023-01-31 | 2016 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ154288 | IMPROVE FAMILY HSG INFRASTRUCTURE, PH 4 |  |  |  | 2018-11-26 | 2021-01-14 | 2023-01-30 | 98% | 2021-11-17
2023-01-31 | 2016 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ164289 | IMPROVE FAMILY HSG INFRASTRUCTURE, PH 5 |  |  |  | 2018-11-26 | 2021-01-14 | 2023-01-30 | 98% | 2021-11-17
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Japan | LXEZ183486 | AIRFIELD SECURITY BARRIERS |  |  |  | 2021-08-02 | 2022-12-07 | 2022-12-10 | 29% | 2022-12-10
2023-01-31 | 2018 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ184546 | IMPROVE FAMILY HOUSING, KAB SEBILLE MANOR (100 UN) |  |  |  | 2020-10-01 | 2022-12-30 | 2023-03-30 | 51% | 2023-03-30
2023-01-31 | 2019 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ194643 | IMPROVE MFH, KAB STEARLY HEIGHTS (130UN) |  |  |  | 2022-10-18 | 2025-10-22 | 2025-10-22 | 2% | 2025-10-22
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Japan | LXFB123876 | APR - REPLACE MUNITIONS STRUCTURES |  |  |  | 2022-08-22 | 2024-08-11 | 2024-08-01 | 2% | 2024-08-01
2023-01-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173001 | VISITOR'S CENTER |  |  |  | 2021-06-04 | 2022-07-31 | 2022-08-12 | 100% | 2022-08-12
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173002 | ENTRY GATE INSPECTION AREA |  |  |  | 2020-06-15 | 2022-03-16 | 2022-03-16 | 100% | 2022-03-16
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173003 | COMMERCIAL VEHICLE INSPECTION |  |  |  | 2020-06-15 | 2022-03-16 | 2022-03-16 | 100% | 2022-03-16
2023-01-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | New Mexico | United States | MHMV053107 | LIGHTING FOR AIRCRAFT MAINTENANCE AND PARKING |  |  |  | 2021-05-04 | 2022-05-29 | 2022-12-30 | 88% | 2022-11-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | New Mexico | United States | MHMV083126A | Replace Fire Station 3 |  |  |  | 2020-12-31 | 2022-03-01 | 2023-02-24 | 66% | 2023-02-24
2023-01-31 | 2022 | Air Force Active | Unspecified Minor Military Construction | New Mexico | United States | MHMV180068 | Apparatus Bay, Fire Station #5 |  |  |  | 2022-08-01 | 2023-11-23 | 2023-11-23 | 2% | 2023-11-23
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R5 | BMT RECRUIT DORMITORY 5 |  |  |  | 2019-03-19 | 2021-09-04 | 2023-08-25 | 100% | 2023-08-31
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R6 | BMT RECRUIT DORMITORY 6 |  |  |  | 2020-05-10 | 2022-10-27 | 2023-04-27 | 76% | 2023-04-27
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737S3 | BMT CLASSROOMS/DINING FACILITY PHASE 3 |  |  |  | 2019-03-19 | 2021-09-04 | 2023-08-25 | 65% | 2023-08-31
2023-01-31 | 2016 | Air Force Active | Unspecified Minor Military Construction | Texas | United States | MPLS113003A | Telephone Maintenance Facility |  |  |  | 2019-05-02 | 2020-06-30 | 2021-06-03 | 100% | 2021-07-21
2023-01-31 | 2015 | Air Force Active | Major Military Construction | Texas | United States | MPLS3274JB | FIRE STATION |  |  |  | 2015-07-08 | 2020-06-03 | 2021-06-03 | 100% | 2021-06-18
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Texas | United States | MPYJ043895A | Aquatics tank |  |  |  | 2021-09-01 | 2023-04-24 | 2023-09-21 | 55% | 2023-09-21
2023-01-31 | 2019 | Air Force Active | Major Military Construction | New Jersey | United States | MSBL103000 | COMMERCIAL VEHICLE SECURITY ENTRY CONTROL POINT (ECP) |  |  |  | 2021-11-22 | 2023-05-16 | 2023-09-19 | 28% | 2023-05-16
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET143006 | CONSOLIDATED CORROSION CONTROL FACILITY |  |  |  | 2021-03-01 | 2024-02-05 | 2024-03-05 | 60% | 2024-03-05
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153501 | F-35A FLIGHT SIMULATOR FACILITY |  |  |  | 2019-07-18 | 2020-11-01 | 2022-08-24 | 100% | 2022-08-24
2023-01-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153503 | F-35A FUEL SYSTEM MAINTENANCE DOCK 2 BAY |  |  |  | 2020-08-03 | 2022-04-20 | 2023-07-10 | 84% | 2023-07-10
2023-01-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153504 | F-35A PARKING APRON |  |  |  | 2020-09-04 | 2022-02-28 | 2022-02-28 | 100% | 2022-02-28
2023-01-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153505 | F-35A AGE FACILITY |  |  |  | 2020-01-17 | 2021-04-01 | 2022-02-28 | 100% | 2022-02-28
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153506 | F-35A FIELD TRAINING DETACHMENT FACILITY |  |  |  | 2020-09-02 | 2022-02-19 | 2022-08-03 | 87% | 2022-08-03
2023-01-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153508 | F-35A 6-BAY HANGAR |  |  |  | 2020-11-09 | 2023-02-15 | 2023-07-10 | 76% | 2023-07-10
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153509 | F-35A INFRASTRUCTURE |  |  |  | 2020-04-09 | 2022-08-31 | 2023-09-30 | 75% | 2023-09-30
2023-01-31 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153511 | F-35A DORM |  |  |  | 2021-07-31 | 2023-06-23 | 2024-05-17 | 2% | 2024-05-17
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153513 | F-35A 6-BAY HANGAR |  |  |  | 2021-01-22 | 2023-03-10 | 2022-04-04 | 77% | 2022-04-04
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153514 | F-35A SQUADRON OPERATIONS AND AMU |  |  |  | 2019-07-18 | 2021-02-01 | 2023-09-29 | 96% | 2023-09-29
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Virginia | United States | MUHJ133000 | Air Force Targeting Center Facility |  |  |  | 2021-06-09 | 2023-06-09 | 2023-09-07 | 14% | 2023-06-09
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Virginia | United States | MUHJ193002 | Consolidated OPS/Maintenance Hangar |  |  |  | 2022-11-17 | 2024-10-17 | 2024-10-17 | 2% | 2025-01-20
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Virginia | United States | MUHJ193004 | Low Observable Component Repair Facility |  |  |  | 2022-08-16 | 2024-08-15 | 2024-08-15 | 9% | 2024-12-13
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD083000 | Vandenberg Gate Complex |  |  |  | 2022-04-29 | 2023-09-29 | 2023-09-29 | 5% | 2023-09-29
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD153006 | MIT-Lincoln Laboratory (West Lab CSL/MIF) |  |  |  | 2019-11-18 | 2024-11-22 | 2024-11-22 | 5% | 2024-11-22
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK123007 | C-130H/J FUSELAGE TRAINER FACILITY |  |  |  | 2020-10-15 | 2022-10-15 | 2023-06-01 | 70% | 2023-06-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK153001 | DORMITORY (168 PN) |  |  |  | 2021-10-20 | 2023-04-13 | 2023-11-13 | 23% | 2023-12-04
2023-01-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | Arkansas | United States | NKAK193001 | Vandenberg Visitor Control Center |  |  |  | 2021-11-20 | 2022-11-20 | 2022-12-30 | 68% | 2022-11-30
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093016 | COMMUNICATIONS FACILITY |  |  |  | 2018-02-26 | 2020-02-26 | 2021-07-27 | 100% | 2020-06-10
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | NUEX1009271 | CONSTRUCT POTABLE WATER WELL |  |  |  | 2022-11-22 | 2023-08-15 | 2023-08-15 | 2% | 2023-08-15
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | NVZR153710 | KC135 Beddown Add Flt Simltr Training |  |  |  | 2020-03-20 | 2021-03-25 | 2021-12-30 | 100% | 2021-12-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Florida | United States | NVZR153711 | KC135 Beddown OG/MXG HQ |  |  |  | 2019-11-18 | 2021-05-11 | 2021-08-27 | 100% | 2021-08-27
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Montana | United States | NZAS043002 | TACTICAL RESPONSE FORCE ALERT FACILITY |  |  |  | 2018-08-22 | 2020-05-13 | 2020-08-31 | 100% | 2020-08-31
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Montana | United States | NZAS173001 | Relocate Missile Maintenance Dispatch Facility (MMDF) |  |  |  | 2019-06-25 | 2021-05-15 | 2021-09-17 | 98% | 2021-09-17
2023-01-31 | 2017 | Air Force Active | Major Military Construction |  | Australia | PAF150400 | APR EXPAND AIRCRAFT PARKING APRON |  |  |  | 2018-08-01 | 2019-10-15 | 2021-10-29 | 100% | 2020-12-17
2023-01-31 | 2018 | Air Force Active | Major Military Construction |  | Australia | PAF160600 | APR - BULK FUEL STORAGE TANKS |  |  |  | 2019-10-26 | 2022-09-01 | 2023-06-17 | 90% | 2023-06-01
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Australia | PAF180200 | APSI - JET FUEL STORAGE TANKS |  |  |  | 2022-05-20 | 2025-06-20 | 2025-06-20 | 2% | 2025-06-20
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Australia | PAF180300 | APSI - EARTH COVERED MAGAZINES |  |  |  | 2020-11-02 | 2022-04-20 | 2022-05-24 | 100% | 2022-05-24
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Northern Mariana Islands | PAF189021 | APSI - AIRFIELD DEVELOPMENT PHASE 1 |  |  |  | 2022-01-27 | 2025-10-09 | 2025-10-09 | 13% | 2025-10-09
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Northern Mariana Islands | PAF189022 | APSI - PARKING APRON |  |  |  | 2022-01-27 | 2025-10-09 | 2025-10-09 | 13% | 2025-10-09
2023-01-31 | 2015 | Air Force Active | Major Military Construction |  | Lithuania | PAYZ15001B | ERI: Improve Airfield Infrastructure |  |  |  | 2017-01-12 | 2018-07-06 | 2020-09-11 | 100% | 2020-09-11
2023-01-31 | 2015 | Air Force Active | Major Military Construction |  | Latvia | PAYZ15001C | ERI: Improve Airfield Infrastructure |  |  |  | 2017-01-12 | 2018-07-06 | 2020-04-01 | 100% | 2021-05-31
2023-01-31 | 2015 | Air Force Active | Major Military Construction |  | Italy | PAYZ15001H | ERI: Improve Weapons Storage Facility |  |  |  | 2017-11-24 | 2020-08-28 | 2021-05-04 | 100% | 2021-05-03
2023-01-31 | 2016 | Air Force Active | Major Military Construction |  | Japan | PAYZ16000B | Munitions Storage Igloos |  |  |  | 2020-10-07 | 2021-09-07 | 2021-12-22 | 100% | 2022-02-04
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Alabama | United States | PNQS072140 | JAG School Expansion |  |  |  | 2019-07-10 | 2020-12-31 | 2021-09-13 | 100% | 2021-09-15
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Alabama | United States | PNQS103165 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2019-12-03 | 2021-05-26 | 2021-12-10 | 100% | 2021-10-18
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Kansas | United States | PRQE055155 | Combat Arms Facility |  |  |  | 2018-10-24 | 2023-04-20 | 2023-07-19 | 100% | 2021-06-30
2023-01-31 | 2021 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL023003 | MUNITIONS STORAGE AREA |  |  |  | 2022-11-10 | 2024-10-30 | 2024-10-30 | 2% | 2024-09-19
2023-01-31 | 2015 | Air Force Active | Unspecified Minor Military Construction | New Jersey | United States | PTFL106002 | ATFP-AIRFIELD FLIGHTLINE SECURITY ENHANCEMENT |  |  |  | 2019-10-01 | 2020-09-30 | 2021-02-19 | 100% | 2021-01-20
2023-01-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163001 | KC-46A ADAL B2319 FOR BOOM OPERATOR TRAINER |  |  |  | 2019-03-19 | 2021-11-03 | 2021-08-17 | 100% | 2021-08-17
2023-01-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163006 | KC-46A ADAL B3209 FOR FUSELAGE TRAINER |  |  |  | 2018-11-09 | 2019-11-09 | 2019-12-30 | 100% | 2019-12-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163010 | KC-46A Alter BLDGS FOR OPS AND TFI AMU-AMXS |  |  |  | 2019-11-14 | 2021-05-07 | 2023-02-17 | 95% | 2023-12-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163019 | KC-46A TWO BAY GENERAL PURPOSE MX HANGAR |  |  |  | 2019-08-23 | 2021-07-23 | 2023-03-31 | 96% | 2023-02-28
2023-01-31 | 2018 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF012005 | Indoor Firing Range |  |  |  | 2019-06-26 | 2021-02-15 | 2021-12-17 | 100% | 2021-12-17
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | North Dakota | United States | QJVF1058361 | Special Purpose Maintenance Facility |  |  |  | 2022-03-03 | 2023-04-27 | 2023-04-27 | 2% | 2023-04-27
2023-01-31 | 2022 | Air Force Active | Major Military Construction |  | Japan | QKKA1074664 | PDI: Airfield Damage Repair Facility |  |  |  | 2022-07-15 | 2024-07-03 | 2024-04-19 | 2% | 2024-07-15
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Georgia | United States | QSEU083023 | PERSONNEL RECOVERY 4-BAY HANGAR/HMU |  |  |  | 2020-10-29 | 2022-10-29 | 2022-12-17 | 99% | 2022-12-17
2023-01-31 | 2017 | Air Force Active | Military Family Housing Improvement |  | Spain | QUUG064001 | RENOVATE MFH UNITS 650 AND 658 |  |  |  | 2021-09-28 | 2022-12-08 | 2023-05-30 | 3% | 2023-05-30
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Nevada | United States | RKMF063004 | RED FLAG 5th GEN FACILITY ADDITION |  |  |  | 2019-08-13 | 2021-08-02 | 2022-04-22 | 99% | 2022-04-27
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103011 | F-35A MUNITIONS MAINTENANCE FACILITIES |  |  |  | 2020-01-30 | 2021-08-22 | 2021-10-16 | 83% | 2022-09-30
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | RKMF123009 | CRH Simulator |  |  |  | 2019-11-20 | 2021-07-02 | 2022-12-31 | 99% | 2022-12-31
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Nevada | United States | RKMF163007 | 365 ISR Group Consolidated Facility |  |  |  | 2020-12-08 | 2022-12-28 | 2023-08-31 | 72% | 2022-12-31
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Nevada | United States | RKMF173010 | HYDRAZINE FUEL STORAGE & SERVICING FACILITY |  |  |  | 2019-10-30 | 2020-09-30 | 2022-12-31 | 100% | 2022-12-31
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Nevada | United States | RKMF203001 | F-35A MUNITIONS ASSEMBLY CONVEYOR (MAC) FACILITY |  |  |  | 2020-12-01 | 2021-12-01 | 2022-07-03 | 72% | 2023-05-07
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | RKMF203007 | Joint Simulation Environment (JSE) - Nellis |  |  |  | 2020-08-03 | 2022-07-24 | 2022-12-30 | 90% | 2022-11-30
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP1047602 | PARKING LOT, USSTRATCOM |  |  |  | 2019-05-30 | 2020-08-21 | 2020-08-21 | 100% | 2020-08-21
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212902 | NC3 ALERT CAMPUS |  |  |  | 2023-02-22 | 2025-08-22 | 2025-08-22 | 2% | 2025-08-22
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212903 | NON-KINETIC OPERATIONS CAMPUS |  |  |  | 2023-04-03 | 2027-10-08 | 2027-10-08 | 2% | 2027-10-08
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212904 | LOGISTICS READINESS SQUADRON CAMPUS |  |  |  | 2021-10-18 | 2023-03-22 | 2023-03-22 | 21% | 2023-07-20
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212905 | SECURITY CAMPUS |  |  |  | 2021-10-14 | 2024-11-19 | 2024-11-19 | 67% | 2025-01-09
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212907 | FLIGHTLINE HANGARS CAMPUS |  |  |  | 2022-01-26 | 2023-10-28 | 2023-12-10 | 12% | 2023-09-20
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP212908 | LAKE CAMPUS |  |  |  | 2021-10-05 | 2023-03-29 | 2023-04-28 | 49% | 2023-03-22
2023-01-31 | 2019 | Air Force Active | Unspecified Minor Military Construction |  | Korea, South | SMYU073011 | MILITARY WORKING DOG KENNEL SUPPORTING FACILITY |  |  |  | 2019-09-30 | 2021-02-21 | 2021-08-30 | 100% | 2021-08-30
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Florida | United States | SXHT013001 | FIRE/CRASH RESCUE STATION |  |  |  | 2017-07-26 | 2019-03-12 | 2021-01-15 | 100% | 2021-01-15
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | SXHT023007 | MAIN GATE |  |  |  | 2022-06-22 | 2023-12-22 | 2023-12-22 | 2% | 2024-03-05
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | TDKA063002D | MWD Kennel Facility |  |  |  | 2019-09-09 | 2020-12-02 | 2020-12-28 | 100% | 2020-12-28
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Colorado | United States | TDKA143002 | SOCNORTH THEATER OPERATIONAL SUPPORT FACILITY |  |  |  | 2021-05-24 | 2023-09-11 | 2023-10-04 | 37% | 2023-12-10
2023-01-31 | 2012 | Air Force Active | Major Military Construction |  | Germany | TYFR063017 | DORMITORY (192 RM) |  |  |  | 2015-08-10 | 2017-06-27 | 2021-08-15 | 100% | 2021-08-15
2023-01-31 | 2021 | Air Force Active | Major Military Construction |  | Germany | TYFR203027 | RAPID AIRFIELD DAMAGE REPAIR COMPOUND |  |  |  | 2024-10-28 | 2026-06-30 | 2026-06-30 | 2% | 2026-06-30
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Texas | United States | TYMX103001 | REPAIR WING B OF AFPC FACILITY B499 |  |  |  | 2021-09-17 | 2023-03-11 | 2023-03-30 | 21% | 2023-10-04
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Georgia | United States | UHHZ163000 | COMMERCIAL VEHICLE VISITOR CONTROL FACILITY |  |  |  | 2020-06-18 | 2021-12-10 | 2021-12-10 | 100% | 2021-12-28
2023-01-31 | 2019 | Air Force Active | Major Military Construction | New York | United States | ULDF123001 | Anti-terrorism Perimeter Security/Entry Control Point |  |  |  | 2020-02-10 | 2021-08-03 | 2022-11-12 | 100% | 2022-08-30
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Illinois | United States | VDYD101053 | Consolidated Communications Facility Add/Alt |  |  |  | 2020-09-25 | 2023-10-12 | 2024-01-10 | 76% | 2023-12-27
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Illinois | United States | VDYD1055428 | Joint Operations & Mission Planning Center |  |  |  | 2021-08-02 | 2023-08-21 | 2023-10-06 | 44% | 2023-06-30
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Illinois | United States | VDYD1074289 | ADAL MAF Distributed Mission Operations; B5028 |  |  |  | 2021-04-27 | 2023-06-26 | 2023-06-26 | 70% | 2023-06-26
2023-01-31 | 2016 | Air Force Active | Major Military Construction | North Carolina | United States | VKAG013004R5 | AIR TRAFFIC CONTROL TOWER/BASE OPERATIONS FACILITY |  |  |  | 2019-08-14 | 2021-02-04 | 2021-10-12 | 100% | 2021-10-12
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | North Carolina | United States | VKAG193002 | Berkeley Gate Entry Control Point |  |  |  | 2021-04-11 | 2023-01-13 | 2023-01-03 | 53% | 2023-01-03
2023-01-31 | 2019 | Air Force Active | Major Military Construction | South Carolina | United States | VLSB193001 | CPIP MQ-9 MCE GROUP (MILCON) |  |  |  | 2020-12-30 | 2023-03-01 | 2023-06-18 | 75% | 2023-06-18
2023-01-31 | 2022 | Air Force Active | Major Military Construction | Texas | United States | VNVP063002 | Construct Child Development Center, B195 |  |  |  | 2022-06-16 | 2024-06-15 | 2024-06-15 | 2% | 2024-06-17
2023-01-31 | 2021 | Air Force Active | Major Military Construction |  | Germany | VYHK213002 | EDI - RAPID AIRFIELD DAMAGE REPAIR STORAGE |  |  |  | 2024-10-29 | 2026-02-11 | 2026-02-11 | 2% | 2026-02-11
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK093003 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2017-05-17 | 2018-11-08 | 2021-04-12 | 100% | 2021-04-12
2023-01-31 | 2015 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK153005 | KC-46A TWO-BAY DEPOT MAINTENANCE HANGAR |  |  |  | 2017-05-11 | 2019-04-30 | 2021-01-07 | 100% | 2021-01-07
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK153007 | COMMERCIAL VEHICLE INSPECTION FACILITY |  |  |  | 2022-11-15 | 2024-01-30 | 2024-01-30 | 2% | 2024-01-30
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Oklahoma | United States | WWYK173005 | IMPROVE LIBERATOR GATE |  |  |  | 2020-02-03 | 2022-09-30 | 2022-12-30 | 97% | 2022-11-30
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193001 | KC-46A Depot Maintenance Hangar |  |  |  | 2019-10-10 | 2022-07-16 | 2023-05-22 | 94% | 2023-02-07
2023-01-31 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193003 | E-3G MISSION AND FLIGHT SIMULATOR TRAINING FACILITY |  |  |  | 2019-03-05 | 2021-03-04 | 2022-06-15 | 100% | 2022-06-17
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193014 | KC-46A Depot Fuel Maintenance Hangar |  |  |  | 2019-10-23 | 2022-03-20 | 2023-04-18 | 93% | 2023-02-22
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Oklahoma | United States | WWYK913019 | NATURAL GAS MAIN EXTENSION |  |  |  | 2022-07-07 | 2023-09-30 | 2023-09-30 | 3% | 2023-09-30
2023-01-31 | 2020 | Air Force Active | Major Military Construction | California | United States | XDAT1026962 | KC-46A ALTER B181/B185/B187 SQUAD OPS/AMU |  |  |  | 2022-03-15 | 2021-12-16 | 2022-04-21 | 100% | 2022-04-21
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | California | United States | XDAT1030576 | Construct and Expand Taxiway ALPHA and BRAVO |  |  |  | -1 | 2021-08-21 | 2021-08-21 | 100% | 2021-08-21
2023-01-31 | 2020 | Air Force Active | Major Military Construction | California | United States | XDAT1046451 | KC-46A Regional Maintenance Training Facility |  |  |  | 2021-06-15 | 2023-03-10 | 2023-03-10 | 70% | 2023-03-10
2023-01-31 | 2018 | Air Force Active | Major Military Construction | California | United States | XDAT1051930 | KC-46A Aircraft 3-Bay Maintenance Hangar |  |  |  | 2020-12-30 | 2023-02-26 | 2023-02-24 | 96% | 2023-02-24
2023-01-31 | 2020 | Air Force Active | Major Military Construction | California | United States | XDAT1074510 | ADAL Aerial Port Squadron Materiel Warehouse |  |  |  | 2021-09-02 | 2023-12-11 | 2023-12-11 | 39% | 2023-12-11
2023-01-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | California | United States | XDAT173002 | KC-46A B564, AGE Covered Storage |  |  |  | 2021-08-15 | 2022-10-22 | 2023-07-31 | 33% | 2023-07-31
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU193004 | CONSTRUCT INDOOR CATM RANGE |  |  |  | 2022-05-05 | 2024-01-25 | 2024-01-25 | 9% | 2024-04-24
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU193005 | FIRE STATION #2 |  |  |  | 2019-12-10 | 2022-08-30 | 2022-12-14 | 77% | 2022-12-14
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU193006 | ACS Flight Simulator |  |  |  | 2019-12-03 | 2022-03-21 | 2023-01-31 | 99% | 2023-01-31
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203002 | CE/Contracting/USACE Complex |  |  |  | 2022-04-26 | 2025-09-27 | 2026-02-06 | 12% | 2026-02-06
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203004 | Dorm Complex |  |  |  | 2021-11-30 | 2024-08-26 | 2024-08-26 | 16% | 2024-08-26
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203005 | Chapel |  |  |  | 2022-09-14 | 2024-11-22 | 2024-11-22 | 2% | 2025-02-20
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203006 | Child Development Center |  |  |  | 2020-10-16 | 2022-09-16 | 2023-03-01 | 82% | 2023-03-01
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203008 | 53 WEG HQ Facility |  |  |  | 2022-08-04 | 2025-06-09 | 2025-06-09 | 2% | 2025-10-07
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203009 | 53 WEG Hangar |  |  |  | 2022-08-04 | 2025-06-09 | 2025-06-09 | 2% | 2025-10-07
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203010 | 53 WEG Subscale Drone Facility |  |  |  | 2022-03-15 | 2024-09-30 | 2024-09-30 | 3% | 2024-12-29
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203011 | Flightline-MUNS Storage, 7000 Area |  |  |  | 2022-02-23 | 2024-05-03 | 2024-05-03 | 8% | 2024-05-03
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203012 | OSS/RADAR Approach Control Facility |  |  |  | 2022-06-27 | 2024-07-16 | 2024-07-16 | 3% | 2024-10-02
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203013 | Ops/Aircraft Maintenance Unit Hangar #1 |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2026-02-10
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203014 | Ops/Aircraft Maintenance Unit Hangar #2 |  |  |  | 2022-06-01 | 2025-08-14 | 2025-08-14 | 5% | 2025-12-12
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203015 | Ops/Aircraft Maintenance Unit Hangar #3 |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2026-04-11
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203016 | Maintenance Squadron Complex |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2025-09-12
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203017 | Operations Group/Maintenance Group HQ |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2026-01-11
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203018 | Aircraft Wash Rack |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2025-12-12
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203019 | AIRCRAFT MX FUEL CELL HANGAR |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2025-11-12
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203021 | Logistics Readiness Squadron Complex |  |  |  | 2022-08-17 | 2025-10-10 | 2025-10-10 | 3% | 2026-02-07
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203025 | Security Forces Mobility Storage Facility |  |  |  | 2021-08-04 | 2023-03-27 | 2023-05-17 | 37% | 2023-05-17
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203026 | MWR Facilities |  |  |  | 2022-06-08 | 2024-10-05 | 2024-10-05 | 12% | 2025-01-03
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203028 | Lodging Facilities |  |  |  | 2021-07-21 | 2024-04-16 | 2024-08-27 | 23% | 2024-08-27
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203029 | Community Commons Facility |  |  |  | 2022-09-14 | 2025-02-20 | 2025-02-20 | 2% | 2025-02-20
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203030 | 325th Fighter Wing HQ Facility |  |  |  | 2021-08-26 | 2024-04-02 | 2024-04-02 | 56% | 2024-04-02
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203033 | Emergency Mgmt, Ops Center, Alt CP |  |  |  | 2021-09-22 | 2023-08-23 | 2023-08-23 | 52% | 2023-08-23
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203034 | Silver Flag Facilities |  |  |  | 2021-10-28 | 2023-09-28 | 2023-09-28 | 45% | 2023-09-28
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203036 | Fire Station Silver Flag #4 |  |  |  | 2022-08-04 | 2024-07-04 | 2024-07-04 | 4% | 2024-10-02
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203038 | Weapons Load Training Hangar |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2026-06-10
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203040 | Special Purpose Vehicle Maintenance |  |  |  | 2021-09-14 | 2023-06-26 | 2023-06-26 | 22% | 2023-06-26
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203041 | Aircraft Parking Apron |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2025-08-14
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203043 | 53 WEG Parking Apron |  |  |  | 2022-08-04 | 2025-06-09 | 2025-06-09 | 2% | 2025-10-07
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203044 | Simulator Facility |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2025-08-14
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203045 | Site Development, Utilities, & Demo Phase 1 |  |  |  | 2022-05-17 | 2026-06-25 | 2026-06-25 | 2% | 2026-10-23
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203046 | Tyndall AFB Gate Complexes |  |  |  | 2021-09-23 | 2024-08-15 | 2024-08-15 | 40% | 2024-08-15
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203047 | Auxiliary Ground Equipment Facility |  |  |  | 2022-06-01 | 2026-02-10 | 2026-02-10 | 4% | 2025-10-13
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203049 | MU-2 Hangar |  |  |  | 2022-08-30 | 2025-10-07 | 2025-10-07 | 2% | 2025-10-07
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Florida | United States | XLWU203050 | SITE DEVELOPMENT, UTILITIES, & DEMO PHASE 2 |  |  |  | 2022-05-17 | 2026-06-25 | 2026-06-25 | 2% | 2026-10-23
2023-01-31 | 2022 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ124008 | High Bay-Vehicle Maintenance |  |  |  | 2022-06-22 | 2023-11-16 | 2023-11-16 | 2% | 2023-11-16
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ164001 | Air Force CyberWorx |  |  |  | 2020-10-13 | 2023-08-13 | 2024-01-08 | 16% | 2024-03-28
2023-01-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | XQPZ174006 | Expand Midfield Facility |  |  |  | 2021-03-29 | 2023-02-27 | 2023-06-20 | 39% | 2023-06-20
2023-01-31 | 2022 | Air Force Active | Major Military Construction | California | United States | XUMU193000 | GBSD STAGE PROCESSING FACILITY |  |  |  | 2022-06-15 | 2024-01-02 | 2023-12-30 | 4% | 2024-01-01
2023-01-31 | 2016 | Air Force Active | Military Family Housing Improvement |  | Germany | YANB144533 | FAMILY HOUSING MANAGEMENT FACILITY |  |  |  | 2020-04-04 | 2024-05-03 | 2024-05-03 | 29% | 2024-05-03
2023-01-31 | 2016 | Air Force Active | Major Military Construction | Missouri | United States | YWHG031002R2 | YWHG031002R2, Consolidated Stealth Operations & Nuclear Alert Facility |  |  |  | 2019-03-19 | 2021-09-15 | 2021-09-15 | 100% | 2021-09-15
2023-01-31 | 2020 | Air Force Active | Major Military Construction | Missouri | United States | YWHG1030692 | CONSOLIDATED VEHICLE MAINTENANCE FACILITY |  |  |  | 2021-09-01 | 2023-09-01 | 2024-01-14 | 36% | 2023-01-08
2023-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Missouri | United States | YWHG163100 | Force Support Squadron Annex |  |  |  | 2022-04-08 | 2023-07-28 | 2023-09-04 | 49% | 2023-06-01
2023-01-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | Missouri | United States | YWHG193001 | New ECP at LeMay Gate |  |  |  | 2021-09-21 | 2022-11-04 | 2022-12-30 | 52% | 2022-11-30
2023-01-31 | 2019 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV093301 | ADAL Intelligence Production Facility |  |  |  | 2019-08-16 | 2023-12-13 | 2024-06-13 | 100% | 2023-01-22
2023-01-31 | 2018 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV153201 | FIRE/CRASH RESCUE STATION |  |  |  | 2020-05-06 | 2021-09-03 | 2023-02-28 | 98% | 2022-11-22
2023-01-31 | 2020 | Air Force Active | Major Military Construction |  | Japan | ZNRE2031002 | APSI - FUEL RECEIPT AND DISTRIBUTION UPGRADES |  |  |  | 2022-03-04 | 2024-01-12 | 2024-04-12 | 10% | 2024-04-12
2023-01-31 | 2020 | Air Force Active | Military Family Housing Improvement |  | Japan | ZNRE204308 | Improve Family Housing Phase 8a |  |  |  | 2020-09-16 | 2023-01-05 | 2023-01-05 | 98% | 2023-01-05
2023-01-31 | 2022 | Air Force Active | Military Family Housing Improvement |  | Japan | ZNRE254300 | IMPROVE FAMILY HOUSING, YOKOTA AB PHASE 8 (45 UN) |  |  |  | 2022-05-18 | 2025-03-03 | 2025-03-03 | 2% | 2024-10-30
2023-01-31 | 2020 | Air Force Reserve | Major Military Construction | Maryland | United States | AJXF223744 | Aeromedical Evacuation Squadron Training/Admin. Facility |  |  |  | 2020-09-23 | 2022-05-26 | 2023-03-20 | 86%
2023-01-31 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Louisiana | United States | AWUB105005 | Missile Maintenance Facility |  |  |  | 2019-03-30 | 2020-03-31 | 2021-08-27 | 100%
2023-01-31 | 2022 | Air Force Reserve | Major Military Construction | California | United States | BAEY105675 | 940 ARW Squad Ops & AMU |  |  |  | 2022-10-27 | 2024-10-26 | 2024-10-26 | 2%
2023-01-31 | 2019 | Air Force Reserve | Major Military Construction | Indiana | United States | CTGB169002 | Aerial Port Facility |  |  |  | 2019-08-26 | 2020-10-27 | 2022-05-13 | 100%
2023-01-31 | 2019 | Air Force Reserve | Major Military Construction | Indiana | United States | CTGB989003 | Aircraft Maintenance Hanger, Bldg. 437 |  |  |  | 2020-09-16 | 2022-05-04 | 2023-02-18 | 91%
2023-01-31 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Texas | United States | DDPM130007 | Munitions Training/Admin Facility |  |  |  | 2018-12-12 | 2020-09-14 | 2021-01-31 | 100%
2023-01-31 | 2021 | Air Force Reserve | Major Military Construction | Texas | United States | DDPM414396 | F-35A Flight Simulator |  |  |  | 2021-09-29 | 2024-09-30 | 2024-09-30 | 35%
2023-01-31 | 2021 | Air Force Reserve | Major Military Construction | Texas | United States | DDPM414415 | F-35A Squadron Ops/AMU |  |  |  | 2021-09-29 | 2024-09-30 | 2024-09-30 | 35%
2023-01-31 | 2022 | Air Force Reserve | Unspecified Minor Military Construction | Arizona | United States | FBNV170602 | Renovation Bldg. 5247 47th Fighter Squadron |  |  |  | 2022-07-08 | 2024-02-28 | 2024-02-28 | 2%
2023-01-31 | 2016 | Air Force Reserve | Major Military Construction | Georgia | United States | FGWB009002 | Fire Station |  |  |  | 2017-12-13 | 2019-06-06 | 2022-03-09 | 100%
2023-01-31 | 2018 | Air Force Reserve | Major Military Construction | Hawaii | United States | KNMD624007 | Consolidated Training Facility |  |  |  | 2021-01-29 | 2022-07-11 | 2023-02-15 | 97%
2023-01-31 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Mississippi | United States | MAHG063004 | Aeromedical Staging Squadron Facility |  |  |  | 2019-12-11 | 2020-10-31 | 2021-08-30 | 100%
2023-01-31 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | California | United States | PDPG120514 | Satellite Fire Station |  |  |  | 2018-09-14 | 2019-11-08 | 2021-05-31 | 100%
2023-01-31 | 2022 | Air Force Reserve | Unspecified Minor Military Construction | Washington | United States | PQWY149006 | 446th SFS Training Annex |  |  |  | 2022-09-28 | 2024-06-08 | 2024-06-08 | 5%
2023-01-31 | 2022 | Air Force Reserve | Unspecified Minor Military Construction | Washington | United States | PQWY149007 | 446th CES Training Annex |  |  |  | 2022-09-28 | 2024-06-08 | 2024-06-08 | 5%
2023-01-31 | 2022 | Air Force Reserve | Major Military Construction | Minnesota | United States | QJKL090004 | Mission Support Group Facility |  |  |  | 2022-05-16 | 2023-09-29 | 2023-09-29 | 20%
2023-01-31 | 2021 | Air Force Reserve | Major Military Construction | Minnesota | United States | QJKL100004 | Aerial Port Facility |  |  |  | 2021-09-22 | 2023-09-22 | 2023-09-22 | 20%
2023-01-31 | 2019 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ079104 | Physical Fitness Center |  |  |  | 2019-09-02 | 2021-07-23 | 2021-12-08 | 100%
2023-01-31 | 2022 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ219742 | Construct a New Entrance Gate |  |  |  | 2022-05-16 | 2024-03-14 | 2024-03-14 | 20%
2023-01-31 | 2018 | Air Force Reserve | Major Military Construction | Florida | United States | SXHT103001 | Guardian Angel Facility |  |  |  | 2018-08-29 | 2020-07-19 | 2022-05-31 | 100%
2023-01-31 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Florida | United States | SXHT171217 | Addition To 39 RQS B 673 |  |  |  | 2020-03-01 | 2021-03-15 | 2021-08-12 | 100%
2023-01-31 | 2019 | Air Force Reserve | Major Military Construction | Florida | United States | SXHT203000 | HC-130J General Maintenance Hanger |  |  |  | 2022-06-05 | 2024-03-21 | 2024-04-01 | 5%
2023-01-31 | 2022 | Air Force Reserve | Major Military Construction | Florida | United States | SXHT219201 | Personnel Recovery HC-130J Flight Simulator |  |  |  | 2022-06-11 | 2024-06-07 | 2024-06-07 | 11%
2023-01-31 | 2018 | Air Force Reserve | Major Military Construction | Georgia | United States | UHHZ073003 | Consolidated Mission Complex, Phase 2 |  |  |  | 2019-11-07 | 2021-11-26 | 2023-01-31 | 100%
2023-01-31 | 2020 | Air Force Reserve | Major Military Construction | Georgia | United States | UHHZ073005 | Consolidated Mission Complex, Phase 3 |  |  |  | 2021-03-18 | 2023-04-11 | 2023-08-05 | 67%
2023-01-31 | 2017 | Air Force Reserve | Major Military Construction | North Carolina | United States | VKAG159021 | KC-46A Construct Two Bay Corrosion/Fuel Cell Hangar |  |  |  | 2017-09-27 | 2020-09-09 | 2021-08-31 | 100%
2023-01-31 | 2018 | Air Force Reserve | Major Military Construction | North Carolina | United States | VKAG159026 | KC-46A ADAL Bldg. for Alternate Mission Equipment Storage |  |  |  | 2020-09-29 | 2022-07-08 | 2023-07-31 | 95%
2023-01-31 | 2018 | Air Force Reserve | Major Military Construction | Massachusetts | United States | YTPM059004 | Indoor Small Arms Range |  |  |  | 2019-11-04 | 2020-12-12 | 2021-08-12 | 100%
2023-01-31 | 2019 | Air Force Reserve | Major Military Construction | Massachusetts | United States | YTPM099001B | Regional ISO Maintenance Hanger |  |  |  | 2021-09-29 | 2023-09-29 | 2023-09-29 | 45%
2023-01-31 | 2021 | Air National Guard | Major Military Construction | Maryland | United States | AJXF189013 | F-16 Mission Training Center |  |  |  | 2022-07-15 | 2024-01-11 | 2024-01-11 | 21%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | California | United States | DJCF149001 | Construct C-130J Flight Simulator Facility |  |  |  | 2022-11-03 | 2023-12-08 | 2023-11-26 | 5%
2023-01-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Wyoming | United States | DPEZ029038 | Security Forces Facility |  |  |  | 2021-12-03 | 2023-02-28 | 2023-03-27 | 60%
2023-01-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Wyoming | United States | DPEZ189031 | Combat Arms Training & Emergency Management |  |  |  | 2022-05-19 | 2023-08-08 | 2023-04-14 | 14%
2023-01-31 | 2021 | Air National Guard | Major Military Construction | Alabama | United States | FAKZ189019 | F-35 Simulator Facility |  |  |  | 2022-09-19 | 2024-08-19 | 2025-01-16 | 7%
2023-01-31 | 2021 | Air National Guard | Major Military Construction | Alabama | United States | FAKZ999088 | Base Supply Complex |  |  |  | 2022-09-19 | 2025-01-06 | 2024-07-31 | 4%
2023-01-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | North Carolina | United States | FJRP189030 | MCCA: ADD ALTER B5740 Fire Station |  |  |  | 2021-11-01 | 2022-11-01 | 2022-12-05 | 99%
2023-01-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | North Carolina | United States | FJRP189050 | C-17 Munitions Storage Area Expansion |  |  |  | 2021-12-23 | 2022-08-20 | 2023-01-27 | 99%
2023-01-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | North Carolina | United States | FJRP199040 | C-17 Conv: Air Drop Facility |  |  |  | 2021-12-15 | 2023-03-10 | 2023-03-10 | 60%
2023-01-31 | 2019 | Air National Guard | Unspecified Minor Military Construction | North Carolina | United States | FJRP199080 | C-17 Simulator Facility |  |  |  | 2019-08-27 | 2020-08-26 | 2022-07-01 | 99%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | Minnesota | United States | FMKM179063 | Construct Small Arms Range |  |  |  | 2022-05-31 | 2022-10-31 | 2023-06-16 | 56%
2023-01-31 | 2022 | Air National Guard | Unspecified Minor Military Construction | New York | United States | HAAW139030 | Entry Control Facility |  |  |  | 2022-03-01 | 2023-03-01 | 2023-07-06 | 24%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | Illinois | United States | JLQN049119 | Construct New Fire Crash Rescue Station |  |  |  | 2019-06-01 | 2023-10-18 | 2022-10-31 | 98%
2023-01-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | Oregon | United States | KJAQ179127 | Construct Multi-Use Addition B127 |  |  |  | 2022-03-15 | 2023-03-15 | 2023-07-01 | 14%
2023-01-31 | 2021 | Air National Guard | Major Military Construction | North Dakota | United States | KKGA169022 | Consolidated RPA Operations Facility |  |  |  | 2021-07-20 | 2022-07-20 | 2023-07-31 | 75%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | Hawaii | United States | KNMD189008 | 3rd Bay F-22 LO CRF B3408 |  |  |  | 2021-02-18 | 2023-03-05 | 2023-04-07 | 74%
2023-01-31 | 2022 | Air National Guard | Major Military Construction | South Dakota | United States | LUXC189012 | F-16 Mission Training Center |  |  |  | 2022-11-22 | 2024-06-24 | 2024-05-25 | 1%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | Virginia | United States | MUHJ179000 | Construct Cyber Ops Facility |  |  |  | 2021-02-20 | 2023-01-31 | 2023-04-23 | 65%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | Ohio | United States | PBXP929798 | Replace Fire Station |  |  |  | 2020-08-03 | 2022-05-25 | 2023-05-25 | 64%
2023-01-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | West Virginia | United States | PJVY199001 | Correct MILCON Fuel Cell Hangar Deficiencies, B305 |  |  |  | 2022-01-28 | 2025-05-12 | 2023-05-01 | 20%
2023-01-31 | 2019 | Air National Guard | Unspecified Minor Military Construction | South Carolina | United States | PSTE089064 | Add to and Alter Security Forces Building 979 |  |  |  | 2021-12-20 | 2023-10-30 | 2023-06-18 | 37%
2023-01-31 | 2020 | Air National Guard | Major Military Construction | California | United States | QMSN199056 | Fuels Corrosion Control Hangar and Shops |  |  |  | 2021-05-03 | 2022-10-17 | 2023-05-26 | 77%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH059034 | NORTHCOM - Construct Alert Apron |  |  |  | 2021-03-11 | 2024-10-01 | 2023-06-30 | 92%
2023-01-31 | 2019 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH189009 | NORTHCOM - Construct Alert Facilities |  |  |  | 2021-03-11 | 2024-10-01 | 2023-06-30 | 92%
2023-01-31 | 2022 | Air National Guard | Major Military Construction | Maine | United States | SCRV359001 | Vehicle Maintenance Facility |  |  |  | 2022-08-26 | 2024-11-30 | 2024-11-30 | 13%
2023-01-31 | 2022 | Air National Guard | Unspecified Minor Military Construction | New Hampshire | United States | SZCQ169264 | ADD to Bldg 264, Squadron Operations |  |  |  | 2022-05-04 | 2023-11-03 | 2023-12-07 | 23%
2023-01-31 | 2020 | Air National Guard | Major Military Construction | Puerto Rico | Puerto Rico | TUMR189003 | Hurricane Maria - Comm Facility |  |  |  | 2021-08-19 | 2024-01-29 | 2024-02-19 | 5%
2023-01-31 | 2020 | Air National Guard | Major Military Construction | Puerto Rico | Puerto Rico | TUMR189004 | Contingency Response Facility |  |  |  | 2021-08-19 | 2024-01-29 | 2024-02-19 | 5%
2023-01-31 | 2020 | Air National Guard | Major Military Construction | Missouri | United States | ULYB169010 | C-130 Flight Simulator Facility |  |  |  | 2020-10-06 | 2022-03-31 | 2023-02-28 | 73%
2023-01-31 | 2022 | Air National Guard | Major Military Construction | New York | United States | VBDZ179043 | C-130 Flight Simulator Facility |  |  |  | 2022-12-23 | 2024-01-22 | 2023-12-23 | 0%
2023-01-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Kentucky | United States | WEAS189001 | Joint Forces Headquarters - ANG Share |  |  |  | 2021-09-27 | 2023-09-27 | 2023-09-27 | 73%
2023-01-31 | 2022 | Air National Guard | Unspecified Minor Military Construction | New York | United States | WKVB139002 | Add to Maintenance Complex Building 358 |  |  |  | 2023-03-10 | 2023-10-26 | 2023-10-26 | 1%
2023-01-31 | 2020 | Air National Guard | Major Military Construction | Georgia | United States | XDQU109057 | Consolidated Joint Air Dominance Hangar Shops |  |  |  | 2020-10-27 | 2022-01-23 | 2023-04-14 | 94%
2023-01-31 | 2022 | Air National Guard | Major Military Construction | Wisconsin | United States | XGFG139001 | Medical Readiness Facility |  |  |  | 2022-10-12 | 2024-01-22 | 2024-02-05 | 6%
2023-01-31 | 2020 | Air National Guard | Major Military Construction | Wisconsin | United States | XGFG189001 | F-35 Simulator Facility-B424 |  |  |  | 2021-06-21 | 2023-01-07 | 2023-03-31 | 99%
2023-01-31 | 2022 | Air National Guard | Major Military Construction | Wisconsin | United States | XGFG189002 | F-35: 3-Bay Specialized Hangar |  |  |  | 2022-10-06 | 2024-04-03 | 2024-05-11 | 1%
2023-01-31 | 2020 | Air National Guard | Major Military Construction | Wisconsin | United States | XGFG189004 | Fighter Alert Shelters (F-35 bedown) |  |  |  | 2021-08-06 | 2022-11-11 | 2023-04-23 | 48%
2023-01-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Arizona | United States | XHEA189054 | MCCA: Construct AAS Runway 3-21 |  |  |  | 2021-08-30 | 2022-08-30 | 2022-11-27 | 97%
2023-01-31 | 2022 | Air National Guard | Unspecified Minor Military Construction | Oklahoma | United States | XHZG159052 | Commercial Inspection Facility |  |  |  | 2022-12-15 | 2024-01-14 | 2023-12-15 | 1%
2023-01-31 | 2019 | Army Active | Major Military Construction | New Mexico | United States | 33584 | Information Systems Facility |  |  |  | 2021-05-25 | 2023-12-11 | 2025-04-27 | 18%
2023-01-31 | 2019 | Army Active | Major Military Construction | Kentucky | United States | 35782 | Digital Air/Ground Integration Range |  |  |  | 2020-02-06 | 2022-02-05 | 2023-03-31 | 89%
2023-01-31 | 2018 | Army Active | Major Military Construction | Washington | United States | 55199 | Fire Station |  |  |  | 2019-12-10 | 2021-11-29 | 2023-03-17 | 97% | 2022-11-14
2023-01-31 | 2021 | Army Active | Major Military Construction | Georgia | United States | 55516 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  | 2021-07-15 | 2023-07-05 | 2023-11-15 | 43%
2023-01-31 | 2021 | Army Active | Major Military Construction | Colorado | United States | 58139 | Physical Fitness Facility |  |  |  | 2021-07-15 | 2023-01-06 | 2023-04-29 | 52%
2023-01-31 | 2020 | Army Active | Major Military Construction | New York | United States | 59766 | Railhead |  |  |  | 2021-10-18 | 2023-10-18 | 2023-10-18 | 8%
2023-01-31 | 2014 | Army Active | Major Military Construction |  | Marshall Islands | 59779 | Pier |  | 2125000 | 92764 | 2016-08-17 | 2020-06-10 | 2025-09-07 | 85%
2023-01-31 | 2020 | Army Active | Major Military Construction | Virginia | United States | 60276 | Secure Operations and Admin Facility |  |  |  | 2021-06-01 | 2024-05-31 | 2024-05-31 | 24%
2023-01-31 | 2018 | Army Active | Major Military Construction | Washington | United States | 61147 | Confinement Facility |  |  |  | 2019-12-06 | 2022-08-22 | 2022-11-14 | 99% | 2022-11-14
2023-01-31 | 2017 | Army Active | Major Military Construction |  | Germany | 62380 | Training Support Center |  |  |  | 2018-02-22 | 2022-05-11 | 2022-11-22 | 81% | 2022-11-22
2023-01-31 | 2013 | Army Active | Major Military Construction |  | Japan | 62783 | Satellite Communications Facility |  |  |  | 2014-11-21 | 2021-06-09 | 2026-10-10 | 74%
2023-01-31 | 2020 | Army Active | Major Military Construction | Michigan | United States | 62856 | Substation |  |  |  | 2020-08-21 | 2022-10-28 | 2023-01-04 | 80% | 2023-01-04
2023-01-31 | 2019 | Army Active | Major Military Construction | New Jersey | United States | 63054 | Munitions Disassembly Complex |  | 4300000 | 64026 | 2019-11-04 | 2021-11-03 | 2022-11-16 | 98% | 2022-11-16
2023-01-31 | 2019 | Army Active | Major Military Construction | Kentucky | United States | 64296 | Vehicle Maintenance Shop |  |  |  | 2022-05-02 | 2024-02-21 | 2024-04-17 | 6%
2023-01-31 | 2008 | Army Active | Military Family Housing |  | Germany | 66253 | Family Housing Replacement Construction |  |  |  | 2008-11-18 | 2010-10-09 | 2023-07-28 | 100%
2023-01-31 | 2018 | Army Active | Major Military Construction | Texas | United States | 67554 | Vehicle Maintenance Shop |  |  |  | 2022-11-30 | 2024-08-21 | 2024-08-21 | 0%
2023-01-31 | 2020 | Army Active | Major Military Construction |  | Honduras | 68253 | Aircraft Maintenance Hangar |  |  |  | 2021-12-15 | 2025-01-08 | 2025-01-08 | 38%
2023-01-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 68530 | Barracks |  |  |  | 2015-11-18 | 2018-12-17 | 2023-02-28 | 99%
2023-01-31 | 2020 | Army Active | Major Military Construction | Kentucky | United States | 69347 | General Purpose Maintenance Shop |  | 6892000 | 62783, 68253, 77538 | 2020-06-11 | 2022-07-11 | 2022-12-15 | 96% | 2023-01-12
2023-01-31 | 2021 | Army Active | Major Military Construction | Hawaii | United States | 70551 | Child Development Center |  |  |  | 2022-10-20 | 2026-03-09 | 2026-03-09 | 0%
2023-01-31 | 2015 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility Complex |  |  |  | 2017-11-02 | 2021-11-07 | 2023-02-20 | 97% | 2022-05-18
2023-01-31 | 2018 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 3 | 58857 |  |  | 2017-11-02 | 2021-11-07 | 2023-02-20 | 97% | 2022-05-18
2023-01-31 | 2017 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 2 | 76593 |  |  | 2017-11-02 | 2021-11-07 | 2023-02-20 | 97% | 2022-05-18
2023-01-31 | 2019 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 4 | 76595 |  |  | 2017-11-02 | 2021-11-07 | 2023-02-20 | 97% | 2022-05-18
2023-01-31 | 2020 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 5 | 92340 |  |  | 2017-11-02 | 2021-11-07 | 2023-02-20 | 97% | 2022-05-18
2023-01-31 | 2017 | Army Active | Major Military Construction | Virginia | United States | 70935 | Vehicle Maintenance Shop |  |  |  | 2021-10-27 | 2024-04-24 | 2024-04-24 | 5%
2023-01-31 | 2018 | Army Active | Military Family Housing Improvement |  | Germany | 71425 | Family Housing Improvements |  |  |  | 2022-02-15 | 2027-02-14 | 2027-02-14 | 0%
2023-01-31 | 2020 | Army Active | Major Military Construction | Virginia | United States | 73391 | Adv Individual Training Barracks Cplx, Ph4 |  |  |  | 2020-11-03 | 2022-11-03 | 2023-03-31 | 95%
2023-01-31 | 2019 | Army Active | Military Family Housing Improvement |  | Germany | 74339 | Family Housing Improvements |  |  |  | 2022-02-15 | 2027-02-14 | 2027-02-14 | 0%
2023-01-31 | 2017 | Army Active | Major Military Construction | California | United States | 74877 | Access Control Point |  |  |  | 2021-09-02 | 2022-11-26 | 2023-09-29 | 40%
2023-01-31 | 2020 | Army Active | Major Military Construction | Alabama | United States | 76673 | Aircraft and Flight Equipment Building |  |  |  | 2021-01-04 | 2022-12-25 | 2022-12-25 | 99%
2023-01-31 | 2021 | Army Active | Major Military Construction | Hawaii | United States | 76897 | Aircraft Maintenance Hangar |  |  |  | 2021-10-13 | 2024-10-12 | 2024-10-12 | 38%
2023-01-31 | 2020 | Army Active | Major Military Construction | Colorado | United States | 77303 | Company Operations Facility |  | 6345000 | 62783 | 2020-09-10 | 2022-06-12 | 2023-01-31 | 95%
2023-01-31 | 2020 | Army Active | Major Military Construction | Washington | United States | 77728 | Information Systems Facility |  |  |  | 2020-07-14 | 2022-12-31 | 2023-05-26 | 90%
2023-01-31 | 2018 | Army Active | Major Military Construction | Virginia | United States | 77779 | Aircraft Maintenance Instructional Bldg |  |  |  | 2019-06-26 | 2021-02-15 | 2023-01-31 | 98% | 2022-12-16
2023-01-31 | 2021 | Army Active | Military Family Housing |  | Marshall Islands | 77881 | Family Housing Replacement Construction |  |  |  | 2022-08-23 | 2024-08-22 | 2024-08-22 | 1%
2023-01-31 | 2018 | Army Active | Military Family Housing |  | Germany | 78713 | Family Housing New Construction |  |  |  | 2022-10-11 | 2025-02-05 | 2025-02-05 | 0%
2023-01-31 | 2019 | Army Active | Major Military Construction | New York | United States | 78804 | Engineering Center |  |  |  | 2021-01-04 | 2025-01-04 | 2025-05-29 | 42% | 2022-10-28
2023-01-31 | 2015 | Army Active | Unspecified Minor Military Construction | Louisiana | United States | 81234 | Fire Station Addition |  |  |  | 2018-09-27 | 2019-09-27 | 2023-03-31 | 83%
2023-01-31 | 2021 | Army Active | Unspecified Minor Military Construction | New Jersey | United States | 81352 | Igloo Storage Installation |  |  |  | 2021-12-01 | 2023-02-02 | 2023-01-25 | 81%
2023-01-31 | 2019 | Army Active | Military Family Housing |  | Korea, South | 81429 | Family Housing Replacement Construction |  |  |  | 2019-10-31 | 2022-09-05 | 2023-09-19 | 86%
2023-01-31 | 2019 | Army Active | Unspecified Minor Military Construction |  | Germany | 86019 | Animal Building |  |  |  | 2020-10-10 | 2022-09-27 | 2022-12-26 | 100% | 2022-12-26
2023-01-31 | 2015 | Army Active | Unspecified Minor Military Construction |  | Germany | 86094 | Child Development Center Addition |  |  |  | 2020-05-18 | 2021-09-05 | 2022-12-08 | 96% | 2022-12-08
2023-01-31 | 2020 | Army Active | Unspecified Minor Military Construction | Virginia | United States | 86215 | Ship Loading and Unloading Mockup |  |  |  | 2021-12-20 | 2022-12-20 | 2022-11-28 | 96% | 2022-12-28
2023-01-31 | 2019 | Army Active | Major Military Construction | Kentucky | United States | 86351 | Microgrid |  |  |  | 2022-11-14 | 2024-10-14 | 2024-10-14 | 0%
2023-01-31 | 2016 | Army Active | Major Military Construction | Maryland | United States | 86409 | Access Control Point |  |  |  | 2020-10-27 | 2022-10-27 | 2023-09-07 | 61%
2023-01-31 | 2017 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction |  |  |  | 2017-10-31 | 2022-07-25 | 2023-04-18 | 98%
2023-01-31 | 2019 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 3 | 86877 |  |  | 2019-02-26 | 2022-07-25 | 2023-04-18 | 98%
2023-01-31 | 2020 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 4 | 91327 | 20800000 | 65981, 71425, 87092 | 2017-10-31 | 2022-07-25 | 2023-04-18 | 98%
2023-01-31 | 2018 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 2 | 91380 |  |  | 2017-10-31 | 2022-07-25 | 2023-04-18 | 98%
2023-01-31 | 2018 | Army Active | Major Military Construction | Alabama | United States | 86816 | Training Support Facility |  |  |  | 2019-10-21 | 2021-10-10 | 2023-12-14 | 89%
2023-01-31 | 2016 | Army Active | Major Military Construction |  | Germany | 86824 | Vehicle Maintenance Shop |  | 4000000 | 55199 | 2019-06-17 | 2023-06-03 | 2023-06-03 | 42%
2023-01-31 | 2018 | Army Active | Major Military Construction |  | Turkey | 86832 | Forward Operating Site |  |  |  | 2018-10-02 | 2022-03-25 | 2024-10-31 | 94%
2023-01-31 | 2018 | Army Active | Major Military Construction |  | Germany | 86991 | Administrative Building |  |  |  | 2020-04-03 | 2022-06-22 | 2024-03-16 | 88%
2023-01-31 | 2018 | Army Active | Military Family Housing | Georgia | United States | 87205 | Family Housing New Construction |  |  |  | 2021-02-26 | 2022-10-01 | 2022-11-04 | 99% | 2022-11-03
2023-01-31 | 2020 | Army Active | Major Military Construction | Texas | United States | 87807 | Barracks |  |  |  | 2021-08-19 | 2023-07-20 | 2023-08-03 | 32%
2023-01-31 | 2020 | Army Active | Major Military Construction | New York | United States | 87933 | Unmanned Aerial Vehicle Hangar |  |  |  | 2020-10-21 | 2022-10-11 | 2023-01-23 | 98%
2023-01-31 | 2020 | Army Active | Major Military Construction | Pennsylvania | United States | 88077 | General Instruction Building INC 1 |  |  |  | 2020-04-01 | 2023-04-01 | 2023-08-03 | 83%
2023-01-31 | 2021 | Army Active | Major Military Construction | Pennsylvania | United States | 88077 | General Instruction Building, Incr 2 | 96217 |  |  | 2021-06-07 | 2023-04-29 | 2023-04-29 | 83%
2023-01-31 | 2020 | Army Active | Major Military Construction | Georgia | United States | 88410 | Aircraft Maintenance Hangar |  |  |  | 2021-08-11 | 2023-08-01 | 2023-09-25 | 29%
2023-01-31 | 2019 | Army Active | Major Military Construction | Georgia | United States | 88724 | Cyber Instructional Fac and Network Ctr |  |  |  | 2020-07-17 | 2022-07-07 | 2023-11-30 | 63%
2023-01-31 | 2020 | Army Active | Major Military Construction | Georgia | United States | 88725 | Cyber Instructional Fac (Admin/Command)INC |  |  |  | 2021-05-11 | 2024-04-25 | 2024-05-17 | 54%
2023-01-31 | 2020 | Army Active | Major Military Construction | North Carolina | United States | 89057 | Dining Facility |  |  |  | 2020-09-16 | 2022-04-09 | 2023-04-28 | 55%
2023-01-31 | 2018 | Army Active | Major Military Construction | Arizona | United States | 90351 | Ground Transport Equipment Building |  |  |  | 2021-04-21 | 2023-02-10 | 2023-02-10 | 43%
2023-01-31 | 2020 | Army Active | Military Family Housing Improvement |  | Germany | 90430 | Family Housing Improvements |  |  |  | 2022-02-15 | 2027-02-14 | 2027-02-14 | 0%
2023-01-31 | 2020 | Army Active | Unspecified Minor Military Construction | Texas | United States | 91328 | Ready Building-Tactical Operations Center |  |  |  | 2020-11-09 | 2021-11-09 | 2023-09-23 | 15%
2023-01-31 | 2020 | Army Active | Unspecified Minor Military Construction | Mississippi | United States | 92422 | Target Assembly Facility Expansion |  |  |  | 2021-11-01 | 2022-11-01 | 2023-04-24 | 81%
2023-01-31 | 2019 | Army Active | Unspecified Minor Military Construction | Hawaii | United States | 93021 | Aviation Parts Storage |  |  |  | 2020-05-18 | 2022-01-08 | 2022-11-29 | 100% | 2022-10-03
2023-01-31 | 2019 | Army Active | Unspecified Minor Military Construction |  | Germany | 93209 | Aircraft Parts Storage |  |  |  | 2022-03-28 | 2023-03-29 | 2024-03-29 | 12%
2023-01-31 | 2021 | Army Active | Major Military Construction | Virginia | United States | 93322 | Training Support Facility |  | 9300000 | 86991 | 2021-12-09 | 2024-01-28 | 2024-01-28 | 38%
2023-01-31 | 2022 | Army Active | Major Military Construction | Hawaii | United States | 93672 | Rotary Wing Parking Apron |  |  |  | 2022-10-26 | 2024-10-25 | 2024-10-25 | 0%
2023-01-31 | 2021 | Army Active | Unspecified Minor Military Construction | New York | United States | 94363 | General Instruction Building, Thayer Swing |  |  |  | 2021-11-19 | 2023-05-21 | 2023-05-21 | 47%
2023-01-31 | 2021 | Army Active | Major Military Construction | Hawaii | United States | 96540 | Child Development Center |  |  |  | 2022-10-14 | 2025-08-26 | 2025-08-26 | 0%
2023-01-31 | 2022 | Army Active | Unspecified Minor Military Construction | California | United States | 99325 | Substation |  |  |  | 2022-10-21 | 2024-04-21 | 2024-04-21 | 1%
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Alabama | United States | 010908 | National Guard Readiness Center |  |  |  | 2020-09-01 | 2021-09-30 | 2022-02-25 | 49% | 2022-02-25
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Alabama | United States | 011801 | Enlisted Barracks, Transient Training |  |  |  | 2021-05-17 | 2022-10-21 | 2022-10-21 | 1% | 2022-10-21
2021-12-15 | 2019 | Army National Guard | Major Military Construction | Alaska | United States | 020143 | United States Property and Fiscal Office Building |  |  |  | 2019-08-12 | 2021-04-23 | 2021-10-30 | 89% | 2021-10-30
2021-12-15 | 2021 | Army National Guard | Major Military Construction | Arizona | United States | 040037 | National Guard Readiness Center |  |  |  | 2021-06-14 | 2022-08-26 | 2022-08-26 | 1% | 2022-08-26
2021-12-15 | 2019 | Army National Guard | Unspecified Minor Military Construction | Arkansas | United States | 050220 | Access Control Building |  |  |  | 2020-10-19 | 2021-10-15 | 2021-10-15 | 15% | 2021-10-15
2021-05-20 | 2017 | Army National Guard | Major Military Construction | Colorado | United States | 080115 | National Guard Readiness Center |  |  |  | 2019-05-20 | 2021-07-23 | 2020-09-30 | 99% | 2020-09-30
2021-05-20 | 2016 | Army National Guard | Unspecified Minor Military Construction | Colorado | United States | 080213 | Airborne Equip/Parachute Repair Shop |  |  |  | 2018-05-14 | 2018-12-31 | 2020-05-30 | 99% | 2018-12-31
2021-12-15 | 2018 | Army National Guard | Unspecified Minor Military Construction | Colorado | United States | 080220 | Unheated Aircraft Storage Hangar |  |  |  | 2020-08-01 | 2021-05-01 | 2021-09-30 | 80% | 2021-10-31
2022-06-30 | 2021 | Army National Guard | Unspecified Minor Military Construction | Colorado | United States | 080303 | National Guard Readiness Center Add/Alt |  |  |  | 2022-04-20 | 2024-04-24 | 2024-04-24 | 1% | 2024-04-24
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Delaware | United States | 100040 | Combined Support Maintenance Shop |  |  |  | 2019-04-08 | 2020-12-31 | 2020-11-20 | 99% | 2020-12-31
2022-06-30 | 2020 | Army National Guard | Unspecified Minor Military Construction | Delaware | United States | 100097 | Physical Fitness Center |  |  |  | 2022-03-21 | 2023-08-25 | 2023-08-25 | 1% | 2023-08-25
2021-12-15 | 2020 | Army National Guard | Unspecified Minor Military Construction | Florida | United States | 120330 | Ready Building Add/Alt |  |  |  | 2021-08-19 | 2022-11-18 | 2022-11-18 | 1% | 2022-11-18
2021-12-15 | 2017 | Army National Guard | Major Military Construction | Hawaii | United States | 150035 | Combined Support Maintenance Shop |  |  |  | 2018-02-26 | 2019-06-30 | 2021-10-18 | 94% | 2021-08-20
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Idaho | United States | 160024 | Railroad Tracks |  |  |  | 2020-09-22 | 2022-09-02 | 2022-03-16 | 55% | 2022-03-16
2021-12-15 | 2018 | Army National Guard | Unspecified Minor Military Construction | Idaho | United States | 160174 | Water Storage Tank, Potable |  |  |  | 2020-01-13 | 2021-01-23 | 2021-12-14 | 95% | 2021-12-14
2021-12-15 | 2019 | Army National Guard | Unspecified Minor Military Construction | Idaho | United States | 160193 | Fire Station Addition |  |  |  | 2020-09-25 | 2021-08-20 | 2021-10-02 | 65% | 2021-10-02
2021-12-15 | 2019 | Army National Guard | Major Military Construction | Illinois | United States | 171510 | Automated Record Fire Range |  |  |  | 2020-04-06 | 2020-10-16 | 2021-09-09 | 95% | 2021-09-09
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Indiana | United States | 180202 | National Guard Readiness Center Add/Alt |  |  |  | 2021-10-15 | 2023-04-27 | 2023-04-27 | 6% | 2023-04-27
2021-03-16 | 2014 | Army National Guard | Unspecified Minor Military Construction | Indiana | United States | 180234 | National Guard Readiness Center Add/Alt |  |  |  | 2018-11-15 | 2019-12-31 | 2020-11-13 | 93% | 2020-09-08
2021-12-15 | 2020 | Army National Guard | Unspecified Minor Military Construction | Iowa | United States | 190005 | Enlisted Barracks, Transient Training Addition |  |  |  | 2020-09-21 | 2021-04-15 | 2021-04-15 | 1% | 2021-04-15
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Iowa | United States | 190130 | Vehicle Maintenance Instructional Building Addition |  |  |  | 2018-10-15 | 2019-12-31 | 2021-04-30 | 95% | 2021-04-30
2021-12-15 | 2017 | Army National Guard | Major Military Construction | Kansas | United States | 200101 | National Guard Readiness Center |  |  |  | 2018-12-04 | 2020-12-23 | 2022-02-12 | 99% | 2022-02-12
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Kansas | United States | 200129 | Solar PV & Water Conservation |  |  |  | 2021-04-26 | 2022-06-24 | 2022-06-24 | 5% | 2021-06-22
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Kansas | United States | 200151 | Enlisted Barracks, Transient Training |  |  |  | 2018-10-10 | 2020-05-14 | 2021-10-15 | 99% | 2021-10-15
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Kentucky | United States | 210054 | National Guard/Reserve Center Building |  |  |  | 2021-10-20 | 2023-09-27 | 2023-09-27 | 10% | 2023-09-27
2022-06-30 | 2022 | Army National Guard | Major Military Construction | Louisiana | United States | 220141 | National Guard Readiness Center |  |  |  | 2022-07-11 | 2024-04-19 | 2024-04-19 | 1% | 2024-04-19
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Louisiana | United States | 220304 | National Guard Readiness Center |  |  |  | 2021-11-15 | 2023-02-24 | 2023-02-24 | 1% | 2023-02-24
2021-12-15 | 2015 | Army National Guard | Major Military Construction | Maine | United States | 230113 | National Guard Reserve Center |  |  |  | 2015-08-20 | 2017-08-03 | 2021-03-31 | 99% | 2018-04-02
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Maine | United States | 230135 | National Guard Readiness Center |  |  |  | 2018-09-17 | 2020-09-01 | 2021-12-31 | 99% | 2021-06-02
2022-06-30 | 2021 | Army National Guard | Unspecified Minor Military Construction | Maine | United States | 230139 | National Guard Vehicle Maintenance Shop Addition/Alteration |  |  |  | 2021-12-20 | 2023-05-23 | 2023-05-23 | 1% | 2023-05-23
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Maryland | United States | 240149 | National Guard Readiness Center |  |  |  | 2018-11-01 | 2020-10-30 | 2021-06-30 | 98% | 2021-07-01
2021-12-15 | 2013 | Army National Guard | Major Military Construction | Massachusetts | United States | 250065 | Unit Training Equipment Site |  |  |  | 2014-04-07 | 2015-07-30 | 2017-05-17 | 84% | 2015-07-30
2021-12-15 | 2015 | Army National Guard | Unspecified Minor Military Construction | Michigan | United States | 260222 | Ammunition Hut, Installation |  |  |  | 2019-05-01 | 2019-10-04 | 2020-12-31 | 78% | 2020-01-26
2021-12-15 | 2020 | Army National Guard | Unspecified Minor Military Construction | Michigan | United States | 260269 | Aircraft Maintenance Bay |  |  |  | 2020-10-05 | 2021-11-05 | 2021-11-05 | 5% | 2021-11-05
2021-12-15 | 2019 | Army National Guard | Unspecified Minor Military Construction | Michigan | United States | 260274 | Waste Water Treatment Plant Add/Alt |  |  |  | 2020-05-27 | 2020-10-02 | 2021-04-20 | 80% | 2020-05-31
2021-12-15 | 2017 | Army National Guard | Unspecified Minor Military Construction | Minnesota | United States | 270127 | Vehicle Storage Building, Installation Alteration |  |  |  | 2019-03-04 | 2020-04-10 | 2020-04-17 | 100% | 2020-04-10
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Minnesota | United States | 270132 | National Guard Readiness Center |  |  |  | 2018-10-05 | 2020-08-24 | 2020-07-01 | 99% | 2020-07-01
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Minnesota | United States | 270203 | National Guard Vehicle Maintenance Shop |  |  |  | 2021-04-19 | 2022-08-20 | 2022-08-20 | 15% | 2022-08-20
2022-06-30 | 2019 | Army National Guard | Unspecified Minor Military Construction | Minnesota | United States | 270220 | National Guard Readiness Center |  |  |  | 2021-10-25 | 2023-03-15 | 2023-03-15 | 1% | 2023-03-15
2022-04-14 | 2018 | Army National Guard | Unspecified Minor Military Construction | Minnesota | United States | 270233 | BN Headquarters Transient Training |  |  |  | 2021-05-03 | 2023-07-20 | 2023-07-20 | 99% | 2023-07-20
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Mississippi | United States | 280381 | National Guard Vehicle Maintenance Shop |  |  |  | 2022-05-23 | 2024-04-14 | 2024-04-14 | 1% | 2024-04-14
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Mississippi | United States | 280408 | Automated Multipurpose Machine Gun Range |  |  |  | 2020-09-15 | 2021-09-30 | 2022-05-14 | 26% | 2022-05-14
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Missouri | United States | 290109 | Aircraft Maintenance Hangar Addition (AVCRAD) |  |  |  | 2018-11-19 | 2020-11-18 | 2021-06-30 | 96% | 2020-11-18
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Missouri | United States | 290186 | National Guard Readiness Center |  |  |  | 2020-08-01 | 2021-08-18 | 2021-12-15 | 12% | 2021-12-15
2021-12-15 | 2019 | Army National Guard | Major Military Construction | Montana | United States | 300031 | National Guard Readiness Center |  |  |  | 2019-06-03 | 2021-04-09 | 2020-12-04 | 99% | 2020-12-04
2022-06-30 | 2022 | Army National Guard | Major Military Construction | Montana | United States | 300049 | National Guard Readiness Center |  |  |  | 2022-06-06 | 2024-07-26 | 2024-07-16 | 1% | 2024-07-16
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Nebraska | United States | 310103 | Training Site Rebuild |  |  |  | 2020-09-01 | 2022-10-28 | 2022-10-28 | 30% | 2022-10-28
2021-12-15 | 2021 | Army National Guard | Major Military Construction | Nebraska | United States | 310140 | National Guard Vehicle Maintenance Shop |  |  |  | 2021-04-01 | 2022-09-20 | 2022-09-20 | 15% | 2022-09-20
2021-06-24 | 2020 | Army National Guard | Major Military Construction | Nebraska | United States | 310168 | Flood Control Levee/Floodwall |  |  |  | 2020-10-05 | 2021-04-30 | 2021-06-18 | 98% | 2021-06-18
2021-04-20 | 2019 | Army National Guard | Major Military Construction | Nevada | United States | 320157 | National Guard Readiness Center |  |  |  | 2019-02-05 | 2020-05-28 | 2020-06-30 | 99% | 2020-06-30
2021-12-15 | 2020 | Army National Guard | Major Military Construction | New Hampshire | United States | 330050 | National Guard Readiness Center |  |  |  | 2020-10-05 | 2022-09-02 | 2022-09-02 | 15% | 2022-09-02
2022-06-30 | 2021 | Army National Guard | Major Military Construction | New Jersey | United States | 340132 | National Guard Readiness Center |  |  |  | 2021-10-18 | 2023-06-15 | 2023-06-15 | 5% | 2023-06-15
2021-12-15 | 2018 | Army National Guard | Major Military Construction | New Mexico | United States | 350200 | National Guard Readiness Center Addition |  |  |  | 2019-04-08 | 2020-10-01 | 2021-02-26 | 80% | 2021-02-26
2021-12-15 | 2020 | Army National Guard | Major Military Construction | New York | United States | 361811 | National Guard Readiness Center Alteration |  |  |  | 2020-10-19 | 2023-12-08 | 2024-04-12 | 21% | 2022-09-16
2021-11-16 | 2017 | Army National Guard | Major Military Construction | North Carolina | United States | 371301 | National Guard Readiness Center |  |  |  | 2017-11-15 | 2019-08-17 | 2020-05-01 | 96% | 2020-03-15
2022-06-30 | 2017 | Army National Guard | Unspecified Minor Military Construction | North Carolina | United States | 371402 | Unheated Vehicle Storage (Aircraft) |  |  |  | 2022-02-07 | 2023-08-05 | 2023-08-05 | 1% | 2023-08-05
2021-12-15 | 2019 | Army National Guard | Major Military Construction | North Dakota | United States | 380116 | National Guard Readiness Center |  |  |  | 2019-06-10 | 2021-06-30 | 2021-06-30 | 97% | 2021-06-30
2021-12-15 | 2019 | Army National Guard | Major Military Construction | Ohio | United States | 390285 | Automated Multipurpose Machine Gun (MPMG) Range |  |  |  | 2020-09-28 | 2022-09-30 | 2022-09-30 | 5% | 2022-09-30
2021-12-15 | 2021 | Army National Guard | Major Military Construction | Oklahoma | United States | 400602 | National Guard Vehilce Maintenance Shop |  |  |  | 2021-08-23 | 2023-02-25 | 2023-02-25 | 1% | 2023-02-25
2021-03-16 | 2016 | Army National Guard | Unspecified Minor Military Construction | Oklahoma | United States | 401221 | Fire Station |  |  |  | 2019-05-06 | 2020-09-25 | 2020-09-25 | 1% | 2020-09-25
2021-03-16 | 2019 | Army National Guard | Major Military Construction | Oklahoma | United States | 401301 | Aircraft Maintenance Bay (Aircraft Storage) |  |  |  | 2019-11-18 | 2020-10-30 | 2020-10-30 | 1% | 2020-10-30
2021-12-15 | 2019 | Army National Guard | Major Military Construction | Oregon | United States | 410818 | Tactical Unmanned Aerial Vehicle Hangar |  |  |  | 2019-10-04 | 2021-10-22 | 2021-11-22 | 65% | 2021-12-15
2021-12-15 | 2019 | Army National Guard | Unspecified Minor Military Construction | Oregon | United States | 411104 | Water Supply/Treatment Building, Potable |  |  |  | 2020-06-22 | 2020-12-31 | 2021-09-30 | 87% | 2021-10-15
2021-12-15 | 2015 | Army National Guard | Major Military Construction | Oregon | United States | 411300 | BIOMASS Heating |  |  |  | 2020-04-13 | 2020-09-30 | 2021-01-19 | 100% | 2020-09-30
2021-12-15 | 2015 | Army National Guard | Major Military Construction | Oregon | United States | 411301 | Exterior/Interior Lighting Retrofit, Multiple Sites |  |  |  | 2017-10-12 | 2018-12-29 | 2021-08-30 | 95% | 2021-09-15
2021-12-15 | 2016 | Army National Guard | Unspecified Minor Military Construction | Oregon | United States | 411503 | Waste Water Treatment Facility |  |  |  | 2020-07-08 | 2021-01-31 | 2021-08-30 | 90% | 2021-09-30
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Oregon | United States | 411508 | Enlisted Barracks, Transient Training |  |  |  | 2021-10-15 | 2023-10-30 | 2023-10-30 | 12% | 2023-10-30
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Oregon | United States | 411510 | Enlisted Barracks, Transient Training |  |  |  | 2021-10-15 | 2023-10-30 | 2023-10-30 | 15% | 2023-10-30
2022-06-30 | 2017 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420502 | Access Control Building |  |  |  | 2021-10-30 | 2023-08-10 | 2023-08-10 | 20% | 2023-08-10
2021-05-20 | 2016 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420522 | Training Aids Center |  |  |  | 2017-11-20 | 2018-08-24 | 2019-12-30 | 99% | 2020-07-06
2022-06-30 | 2017 | Army National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | 420595 | Police / MP Station |  |  |  | 2021-11-02 | 2023-11-20 | 2023-11-20 | 9% | 2023-11-20
2021-12-15 | 2018 | Army National Guard | Unspecified Minor Military Construction | Rhode Island | United States | 440061 | National Guard Readiness Center Add/Alt |  |  |  | 2021-09-27 | 2022-10-29 | 2022-10-29 | 1% | 2022-10-29
2021-12-15 | 2017 | Army National Guard | Major Military Construction | Rhode Island | United States | 440064 | National Guard/Reserve Center Building (JFHQ) |  |  |  | 2017-10-02 | 2020-02-28 | 2021-09-30 | 98% | 2020-02-28
2021-12-15 | 2019 | Army National Guard | Major Military Construction | South Dakota | United States | 460115 | National Guard Readiness Center |  |  |  | 2019-05-01 | 2020-11-01 | 2020-11-15 | 27% | 2020-11-15
2021-12-15 | 2020 | Army National Guard | Unspecified Minor Military Construction | South Dakota | United States | 465001 | Access Control Building |  |  |  | 2020-08-24 | 2021-08-27 | 2021-08-27 | 1% | 2021-08-27
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Tennessee | United States | 470030 | National Guard Readiness Center |  |  |  | 2021-12-15 | 2023-11-16 | 2023-11-16 | 1% | 2023-11-16
2021-12-15 | 2015 | Army National Guard | Unspecified Minor Military Construction | Tennessee | United States | 470035 | Sanitary Sewer |  |  |  | 2020-05-01 | 2021-01-20 | 2021-06-15 | 80% | 2021-06-15
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Texas | United States | 481315 | National Guard Vehicle Maintenance Shop |  |  |  | 2021-10-15 | 2023-03-15 | 2023-03-15 | 1% | 2023-03-15
2021-12-15 | 2017 | Army National Guard | Major Military Construction | Utah | United States | 490601 | National Guard Readiness Center |  |  |  | 2017-10-19 | 2019-04-03 | 2021-05-27 | 99% | 2021-05-27
2022-06-30 | 2021 | Army National Guard | Major Military Construction | Utah | United States | 491201 | National Guard Readiness Center |  |  |  | 2022-04-07 | 2023-10-31 | 2023-10-31 | 1% | 2023-10-31
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Vermont | United States | 500110 | General Instruction Building |  |  |  | 2020-10-12 | 2022-09-02 | 2022-04-30 | 43% | 2022-04-30
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Virginia | United States | 511503 | National Guard Readiness Center |  |  |  | 2018-11-05 | 2020-08-31 | 2021-09-16 | 99% | 2021-09-16
2020-11-12 | 2020 | Army National Guard | Unspecified Minor Military Construction | Virginia | United States | 511863 | Access Control Building |  |  |  | 2020-10-05 | 2021-09-10 | 2021-09-10 | 1% | 2021-09-10
2021-12-15 | 2016 | Army National Guard | Major Military Construction | Washington | United States | 530041 | Enlisted Barracks, Transient Training |  |  |  | 2018-09-17 | 2020-04-17 | 2021-10-29 | 87% | 2021-12-30
2021-12-15 | 2018 | Army National Guard | Major Military Construction | Washington | United States | 530129 | National Guard Readiness Center |  |  |  | 2018-10-15 | 2020-09-01 | 2021-08-31 | 98% | 2021-09-20
2021-12-15 | 2020 | Army National Guard | Major Military Construction | Washington | United States | 531201 | National Guard Readiness Center |  |  |  | 2020-10-01 | 2022-03-21 | 2022-03-21 | 52% | 2022-03-21
2021-12-15 | 2021 | Army National Guard | Major Military Construction | Wisconsin | United States | 550148 | National Guard Readiness Center Add/Alt |  |  |  | 2021-10-25 | 2023-05-19 | 2023-05-19 | 1% | 2023-05-19
2021-06-24 | 2017 | Army National Guard | Unspecified Minor Military Construction | Wisconsin | United States | 550280 | National Guard/Reserve Center Building Alteration |  |  |  | 2019-05-20 | 2021-04-09 | 2021-04-09 | 1% | 2021-04-09
2021-12-15 | 2020 | Army National Guard | Unspecified Minor Military Construction | Virginia | United States | 571863 | Access Control Building |  |  |  | 2021-06-01 | 2022-07-30 | 2022-07-30 | 1% | 2022-07-30
2023-01-31 | 2018 | Army Reserve | Major Military Construction |  | Puerto Rico | 77074 | Army Reserve Center |  |  |  | 2019-10-30 | 2021-04-22 | 2023-03-28 | 92% | 2023-01-27
2023-01-31 | 2016 | Army Reserve | Major Military Construction | Mississippi | United States | 77163 | Army Reserve Center |  |  |  | 2019-11-01 | 2021-06-23 | 2023-06-12 | 88%
2023-01-31 | 2021 | Army Reserve | Major Military Construction | Wisconsin | United States | 81564 | Scout Reconnaissance Range |  |  |  | 2022-02-16 | 2024-02-16 | 2024-02-16 | 13%
2023-01-31 | 2020 | Army Reserve | Major Military Construction | Wisconsin | United States | 81802 | Transient Training Barracks |  |  |  | 2020-10-28 | 2022-12-17 | 2023-04-01 | 99%
2023-01-31 | 2021 | Army Reserve | Major Military Construction | Florida | United States | 82197 | ECS TEMF / Warehouse |  |  |  | 2022-02-10 | 2024-01-31 | 2024-01-31 | 36%
2023-01-31 | 2022 | Army Reserve | Major Military Construction | Wisconsin | United States | 88554 | Collective Training BDE HQ |  |  |  | 2022-06-24 | 2023-12-16 | 2023-12-16 | 13%
2023-01-31 | 2021 | Army Reserve | Major Military Construction | Massachusetts | United States | 88752 | Automated Multipurpose Machine Gun Range |  |  |  | 2022-02-18 | 2024-02-28 | 2024-02-28 | 1%
2023-01-31 | 2019 | Army Reserve | Major Military Construction | Washington | United States | 90202 | ECS Modified TEMF |  |  |  | 2020-09-22 | 2022-06-22 | 2023-04-04 | 96%
2023-01-31 | 2021 | Army Reserve | Unspecified Minor Military Construction | Texas | United States | 90896 | Rotary-Wing Landing Pad |  |  |  | 2021-09-15 | 2022-09-15 | 2023-03-10 | 10%
2023-01-31 | 2022 | Army Reserve | Unspecified Minor Military Construction | Virginia | United States | 92098 | Army Reserve Vehicle Maintenance Shop |  |  |  | 2022-01-26 | 2023-05-19 | 2024-04-19 | 6%
2023-02-14 | 2017 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14019 | Dental Clinic Replacement |  |  |  | 2018-07-20 | 2020-07-13 | 2021-10-07 | 100% | 2021-08-26
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | California | United States | 14021 | Ambulatory Care Center Replacement (Area 13) |  |  |  | 2020-01-02 | 2022-05-10 | 2022-12-31 | 99% | 2021-10-26
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14040 | Ambulatory Care Center Addition/Alteration (French Creek) |  | 1500000 | PN 99800 | 2022-01-18 | 2023-10-12 | 2024-01-18 | 39% | 2024-01-18
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14041 | Ambulatory Care Center/Dental Clinic Replacement (Hadnot Point) |  |  |  | 2019-10-12 | 2021-10-30 | 2022-07-18 | 100% | 2022-07-18
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14042 | Ambulatory Care Center/Dental Clinic Wallace Creek) |  |  |  | 2019-10-12 | 2021-10-30 | 2022-10-31 | 100% | 2022-10-23
2023-02-14 | 2008 | Defense Health Agency | Major Military Construction |  | Germany | 52332 | Medical Clinic Replacement |  |  |  | 2008-08-29 | 2012-05-15 | 2012-07-16 | 100% | 2011-10-08
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 |  |  |  | 2007-10-12 | 2008-06-13 | 2008-06-08 | 100% | 2008-07-23
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-01 |  |  | 2008-08-19 | 2009-02-15 | 2009-02-13 | 100% | 2009-03-03
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-02 |  |  | 2009-10-15 | 2010-04-13 | 2010-04-13 | 100% | 2010-04-13
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-03 |  |  | 2008-12-05 | 2009-07-24 | 2009-07-24 | 100% | 2009-07-24
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-04 |  |  | 2008-07-15 | 2011-05-06 | 2013-10-31 | 100% | 2013-12-06
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-05 |  |  | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 2 | 63418 |  |  | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 3 | 63419 |  |  | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420-01 |  |  | 2008-07-15 | 2013-10-31 | 2016-12-06 | 100% | 2013-12-06
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324 |  |  | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324-01 |  |  | 2008-07-15 | 2013-10-31 | 2013-12-06 | 100% | 2013-12-06
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101 |  |  | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 100% | 2017-05-04
2023-02-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210 |  |  | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 100% | 2017-05-04
2023-02-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-02 |  |  | 2017-10-26 | 2018-10-26 | 2019-05-11 | 98% | 2019-07-03
2023-02-14 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 8 | 78211 | 5800000 | PN 99800 | 2009-06-01 | 2014-05-31 | 2023-06-01 | 98% | 2023-06-15
2023-02-14 | 2009 | Defense Health Agency | Base Realignment and Closures | Maryland | United States | 64156 | USAMRICD Replacement, Inc 1 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2023-02-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2023-02-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 | 65731-01 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2023-02-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2023-02-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-01 |  |  | 2010-10-01 | 2011-09-30 | 2011-09-30 | 100% | 2011-10-01
2023-02-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-02 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2023-02-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 3 | 67181 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2023-02-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 4 | 67182 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2023-02-14 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66588 | Health Clinic Add/Alt |  |  |  | 2013-04-08 | 2016-05-30 | 2017-05-03 | 100% | 2017-05-10
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | Texas | United States | 67402 | Blood Processing Center |  |  |  | 2020-07-02 | 2022-04-03 | 2022-04-03 | 100% | 2022-04-03
2023-02-14 | 2013 | Defense Health Agency | Major Military Construction | South Carolina | United States | 71317 | Medical Clinic Replacement |  | 4898450 | PN 80306 | 2013-12-06 | 2016-12-30 | 2019-02-15 | 100% | 2016-12-02
2023-02-14 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 71325 | Medical Clinic Replacement |  |  |  | 2013-10-24 | 2016-10-23 | 2018-06-01 | 99% | 2018-06-08
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 71408 | Dental Clinic Replacement |  | 312000 | PN 71503 | 2013-03-01 | 2016-12-06 | 2019-02-15 | 100% | 2019-01-03
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic |  | 8300000 | PN 72754 | 2012-09-01 | 2014-09-09 | 2016-01-31 | 100% | 2016-04-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic | 71503-01 |  |  | 2016-08-25 | 2017-12-25 | 2019-05-10 | 100% | 2018-07-31
2023-02-14 | 2017 | Defense Health Agency | Major Military Construction | Maine | United States | 71509 | Medical/Dental Clinic Replacement |  |  |  | 2019-02-01 | 2021-01-24 | 2021-07-14 | 100% | 2021-08-31
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 |  |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 100% | 2020-02-29
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 72251 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 100% | 2020-02-29
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-01 |  |  | 2011-11-02 | 2013-08-13 | 2013-10-12 | 100% | 2013-10-12
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-02 |  |  | 2011-08-23 | 2012-07-05 | 2012-12-31 | 100% | 2012-12-31
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-03 |  |  | 2012-08-28 | 2013-06-19 | 2013-10-17 | 100% | 2013-10-17
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-04 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-05 |  |  | 2012-09-04 | 2014-01-04 | 2015-09-16 | 100% | 2015-09-16
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-06 |  |  | 2011-08-25 | 2011-11-01 | 2011-11-01 | 100% | 2011-11-01
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 3 | 72786 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 100% | 2020-02-29
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 100% | 2020-02-01
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-01 |  |  | 2013-10-21 | 2014-10-24 | 2014-10-24 | 100% | 2014-11-24
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-02 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 100% | 2020-02-29
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293-01 |  |  | 2019-07-26 | 2020-10-18 | 2021-12-28 | 100% | 2021-12-28
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407-01 |  |  | 2019-12-04 | 2021-05-04 | 2021-05-04 | 100% | 2021-06-03
2023-02-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 7 | 81408 | 2500000 | PN 77000 PN 14040 | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Hospital Replacement, Increment 8 | 91301 | 2000000 | PN 77000 PN 80412 | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2023-02-14 | 2017 | Defense Health Agency | Major Military Construction | Texas | United States | 72738 | Medical/Dental Clinic Replacement |  | 741000 | PN 14040 PN 80412 | 2017-10-26 | 2020-10-31 | 2022-04-01 | 99% | 2022-04-01
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center |  |  |  | 2021-06-10 | 2021-09-26 | 2022-06-30 | 99% | 2022-06-30
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center | 72742-01 |  |  | 2022-01-10 | 2022-06-10 | 2022-09-12 | 100% | 2022-09-12
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center | 72742-02 |  |  | 2022-11-07 | 2023-03-24 | 2023-03-24 | 1% | 2023-04-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 2 | 80793 |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2023-02-14 | 2013 | Defense Health Agency | Major Military Construction | California | United States | 72808 | Medical Clinic Replacement |  | 1765000 | PN 80309 PN 72292 | 2014-02-28 | 2015-03-16 | 2017-04-28 | 100% | 2016-06-23
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  | 2016-02-28 | 2016-04-30 | 2017-04-30 | 100% | 2017-02-28
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 72661-01 |  |  | 2017-07-30 | 2021-03-31 | 2021-12-07 | 99% | 2021-07-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 72662-01 |  |  | 2023-06-30 | 2025-12-30 | 2025-12-30 | 1% | 2025-12-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72662-02 |  |  | 2018-09-07 | 2021-01-30 | 2022-12-09 | 99% | 2021-12-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-01 |  |  | 2014-01-20 | 2014-04-04 | 2014-04-04 | 100% | 2014-04-04
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-02 |  |  | 2014-06-16 | 2014-10-29 | 2015-01-21 | 100% | 2015-01-21
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-03 |  |  | 2015-04-20 | 2016-04-30 | 2017-07-30 | 100% | 2016-12-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-04 |  |  | 2016-06-15 | 2016-12-15 | 2017-12-15 | 100% | 2018-01-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-05 |  |  | 2014-08-22 | 2015-03-30 | 2015-05-01 | 100% | 2015-05-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-06 |  |  | 2014-10-08 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-07 |  |  | 2014-08-11 | 2014-10-16 | 2014-10-16 | 100% | 2014-10-16
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-08 |  |  | 2016-08-15 | 2016-10-30 | 2016-12-30 | 100% | 2016-12-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-09 |  |  | 2016-11-30 | 2020-03-30 | 2020-03-30 | 100% | 2020-03-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1, Incr 6 | 76007-10 |  |  | 2014-12-10 | 2025-12-30 | 2027-10-30 | 20% | 2025-12-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-13 |  |  | 2014-10-23 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 through Incr 8 | 76007-14 |  |  | 2015-03-30 | 2025-12-30 | 2027-10-30 | 2% | 2027-09-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 76007-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-12-30 | 100% | 2018-12-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 6 | 81412 |  |  | 2014-01-13 | 2025-12-30 | 2027-10-30 | 55% | 2025-12-30
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement Incr 2-9 | 95984 |  |  | 2021-12-30 | 2027-12-30 | 2027-12-30 | 7% | 2027-12-30
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | Georgia | United States | 76934 | Blood Donor Center Replacement |  |  |  | 2019-03-12 | 2021-03-14 | 2021-07-12 | 98% | 2021-09-13
2023-02-14 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement |  | 539000 | PN 81436 PN 14022 | 2015-09-08 | 2019-02-19 | 2023-02-01 | 99% | 2022-12-16
2023-02-14 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement Water Storage Tank | 77000-10 |  |  | 2021-12-07 | 2022-12-06 | 2022-12-06 | 1% | 2022-12-06
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 77140 | Blood Processing Center Replacement |  |  |  | 2019-03-26 | 2020-09-16 | 2021-10-29 | 99% | 2021-05-07
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 1 |  | 150000 | PN 71408 | 2013-03-01 | 2016-12-06 | 2023-03-31 | 99% | 2017-06-20
2023-02-14 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 2 | 81291 |  |  | 2013-03-01 | 2016-12-06 | 2023-03-31 | 99% | 2017-06-20
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition |  | 536000 | PN 67402 | 2016-12-14 | 2019-06-04 | 2023-02-10 | 99% | 2023-02-28
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition | 77986-01 |  |  | 2022-08-30 | 2023-04-13 | 2023-04-13 | 30% | 2023-07-30
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition | 77986-02 |  |  | 2023-04-01 | 2023-10-01 | 2023-10-01 | 1% | 2023-10-01
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | Colorado | United States | 77987 | Medical/Dental Clinic Addition/Alteration |  | 2110000 | PN 77140 PN 76934 | 2018-10-23 | 2021-06-17 | 2023-08-26 | 75% | 2021-08-16
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 78150 | Medical Clinic Replacement |  | 41463000 | PN 81430 PN 67402 PN 86557 | 2016-11-14 | 2018-12-21 | 2020-08-31 | 100% | 2020-07-31
2023-02-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities |  |  |  | 2013-10-15 | 2013-12-13 | 2014-03-25 | 100% | 2014-04-04
2023-02-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities | 80306-01 |  |  | 2018-11-07 | 2017-12-10 | 2018-08-31 | 100% | 2018-11-07
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 |  |  |  | 2016-06-16 | 2017-12-08 | 2019-03-29 | 100% | 2019-04-19
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 | 80412-01 | 2000000 | PN 86953 | 2018-02-28 | 2020-05-21 | 2020-11-20 | 99% | 2021-02-21
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 | 80412-02 |  |  | 2020-10-19 | 2023-02-06 | 2023-02-06 | 97% | 2022-06-01
2023-02-14 | 2017 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 1 |  |  |  | 2017-12-22 | 2019-05-10 | 2021-08-31 | 100% | 2021-03-17
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 2 | 81420 |  |  | 2020-07-01 | 2026-03-01 | 2027-05-13 | 48% | 2027-05-01
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 3 | 85667 |  |  | 2020-07-01 | 2026-03-01 | 2027-05-13 | 48% | 2027-05-01
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 4 | 90417 |  |  | 2020-07-01 | 2026-03-01 | 2027-05-13 | 48% | 2027-05-01
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction | Texas | United States | 81422 | Lackland Ambulatory Care Center Phase 4 |  | 2000000 | PN 78210 | 2018-10-24 | 2021-04-01 | 2023-06-19 | 74% | 2023-08-18
2023-02-14 | 2015 | Defense Health Agency | Major Military Construction | Virginia | United States | 81430 | Hospital Add/CUP Replacement |  |  |  | 2019-06-01 | 2021-03-18 | 2023-01-12 | 94% | 2022-09-12
2023-02-14 | 2014 | Defense Health Agency | Major Military Construction |  | Bahrain | 81436 | Medical/Dental Clinic Replacement |  | 4000000 | PN 80904 PN 78211 | 2016-04-20 | 2019-04-20 | 2020-01-20 | 99% | 2019-12-30
2023-02-14 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | Delaware | United States | 86204 | Armed Forces Medical Examiner Medical Warehouse Addition/Alteration |  |  |  | 2021-01-07 | 2022-02-03 | 2022-05-15 | 100% | 2022-06-14
2023-02-14 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | Colorado | United States | 86943 | NiCOE Satellite, Infrastructure Support |  |  |  | 2019-12-03 | 2021-06-15 | 2021-07-15 | 100% | 2022-02-25
2023-02-14 | 2016 | Defense Health Agency | Major Military Construction | Kentucky | United States | 86953 | Medical Clinic |  | 2000000 | PN 78211 | 2017-04-13 | 2021-06-23 | 2023-01-04 | 99% | 2021-11-16
2023-02-14 | 2019 | Defense Health Agency | Major Military Construction | North Carolina | United States | 89838 | Ambulatory Care CTR/Dental Clinic Replacement |  |  |  | 2019-09-30 | 2021-10-30 | 2023-07-31 | 92% | 2023-05-15
2023-02-14 | 2019 | Defense Health Agency | Major Military Construction |  | Cuba | 89839 | Working Dog Treatment Facility Replacement |  |  |  | 2022-01-11 | 2023-06-02 | 2023-12-15 | 39% | 2023-10-23
2023-02-14 | 2019 | Defense Health Agency | Major Military Construction | South Carolina | United States | 89902 | Consolidated Storage and Distribution Center |  |  |  | 2020-08-18 | 2022-09-03 | 2023-09-28 | 56% | 2023-05-10
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction | California | United States | 89906 | Ambulatory Care Center Replacement (Area 21) |  |  |  | 2020-11-30 | 2022-10-30 | 2022-11-21 | 97% | 2022-11-21
2023-02-14 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 |  |  |  | 2019-10-14 | 2023-10-13 | 2023-11-08 | 78% | 2024-05-07
2023-02-14 | 2021 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 | 77168 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-25 | 78% | 2024-05-07
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 | 94335 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-25 | 78% | 2024-05-07
2023-02-14 | 2022 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Incre 1 & Incre 2 | 97762 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-25 | 78% | 2024-05-07
2023-02-14 | 2020 | Defense Health Agency | Major Military Construction | Hawaii | United States | 92005 | Working Dog Treatment Facility Replacement |  |  |  | 2022-11-01 | 2024-02-18 | 2024-02-18 | 10% | 2024-02-18
2023-02-14 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | South Carolina | United States | 93298 | High Altitude Airdrop Mission Support (HAAMS) |  |  |  | 2020-11-30 | 2021-09-10 | 2023-01-13 | 99% | 2022-11-21
2023-02-28 | 2021 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 01DISA21 | FTH - JITC LAB Building |  |  |  | 2021-09-10 | 2023-09-13 | 2024-01-18 | 54%
2023-02-28 | 2013 | Defense Information Systems Agency | Major Military Construction |  | Germany | 13DISA01 | DISA Europe Facility Upgrade |  |  |  | 2015-08-19 | 2016-12-31 | 2023-03-31 | 99%
2023-02-28 | 2014 | Defense Information Systems Agency | Major Military Construction | Hawaii | United States | 14DISA01 | DISA Pacific Facility Upgrade |  |  |  | 2018-01-11 | 2018-12-31 | 2022-11-30 | 100%
2023-02-28 | 2015 | Defense Information Systems Agency | Major Military Construction |  | Australia | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) |  |  |  | 2018-10-01 | 2019-03-31 | 2022-08-30 | 100%
2023-02-28 | 2013 | Defense Information Systems Agency | Major Military Construction | Illinois | United States | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  |  |  | 2014-03-01 | 2015-12-30 | 2016-03-11 | 100%
2022-09-30 | 2021 | Defense Intelligence Agency | Major Military Construction | District Of Columbia | United States | 2019030003 | ICS Modernization |  |  |  | 2022-03-23 | 2025-05-20 | 2025-05-20 | 15%
2022-09-30 | 2022 | Defense Intelligence Agency | Major Military Construction | District Of Columbia | United States | 2019040007 | DIA HQ Photovoltaic Carports
2022-09-30 | 2022 | Defense Intelligence Agency | Major Military Construction | Alabama | United States | 94369 | MSIC Material Exploitation Center (MEC)
2022-09-30 | 2022 | Defense Intelligence Agency | Major Military Construction | District Of Columbia | United States | PRJ0238132 | Replace Cooling Towers & Condenser Water Pumps (Bldg. 6000)
2023-02-15 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701A | CONSTRUCT WAREHOUSE OPEN STORAGE |  |  |  | 2018-06-26 | 2020-06-18 | 2021-05-24 | 99% | 2021-10-01
2023-02-15 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701B | CONSTRUCT WAREHOUSE |  |  |  | 2018-09-30 | 2020-09-30 | 2020-09-30 | 99% | 2021-10-01
2023-02-15 | 2019 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1901 | General Purpose Warehouse |  |  |  | 2019-07-31 | 2023-01-04 | 2022-11-18 | 100% | 2022-11-18
2023-02-15 | 2020 | DLA Defense Energy Support Center | Major Military Construction | South Dakota | United States | DECS1913 | Ellsworth Air Force Base Hydrgant Fuel System at Ellsworth AFB |  |  |  | 2020-09-28 | 2022-11-18 | 2023-07-30 | 90%
2023-02-15 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Indiana | United States | DESC1301 | Replace Hydrant Fuel system - Grissom ARB |  |  |  | 2015-09-17 | 2017-04-09 | 2021-04-25 | 100% | 2018-09-25
2023-02-15 | 2017 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC1513 | Replace JP-8 Fuel Storage Tanks, Patrick AFB, FL-Demolition New Construction |  |  |  | 2019-07-15 | 2020-09-15 | 2023-03-31 | 50% | 2021-06-30
2023-02-15 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Germany | DESC1603 | CONSTRUCT FUEL LINE NORTH TO SOUTH SIDE, SPANGDAHLEM AB |  |  |  | 2019-08-10 | 2020-08-10 | 2024-03-02 | 100% | 2020-12-07
2023-02-15 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Delaware | United States | DESC1605 | Construct Hydrant Fuel System, Dover AFB, DE |  |  |  | 2019-07-06 | 2020-01-06 | 2020-05-03 | 100% | 2020-05-23
2023-02-15 | 2018 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1608 | Consolidate Fuel Facilities at Shaw AFB, SC |  |  |  | 2019-06-13 | 2021-03-19 | 2021-03-01 | 99% | 2021-05-01
2023-02-15 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1609 | Ft Belvoir, Replace Ground Fueling Facility |  |  |  | 2019-07-15 | 2021-07-15 | 2021-11-30 | 100% | 2021-12-01
2023-02-15 | 2017 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1611 | REPLACE HYDRANT SYSTEM , Travis AFB |  |  |  | 2017-12-30 | 2020-03-10 | 2021-07-15 | 100% | 2020-07-24
2023-02-15 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Djibouti | DESC1701 | Construct Fuel Storage Facilities, Camp Lemonnie, Djibouti, Horn-of-Africa |  |  |  | 2017-03-13 | 2020-11-30 | 2026-01-24 | 70%
2023-02-15 | 2016 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1702 | CONSTRUCT DISTIBUTION PT. SE RAMP, CANNON AFB |  |  |  | 2017-12-07 | 2019-06-25 | 2019-08-03 | 100% | 2019-07-19
2023-02-15 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Marshall Islands | DESC1704 | Replace Fuel Tanks, Kwajalein Atoll |  |  |  | 2017-11-08 | 2020-11-07 | 2026-10-31 | 53%
2023-02-15 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Diego Garcia | DESC1705 | IMPROVE WHARF REFUELING CAPABILITY Diego Garcia |  |  |  | 2017-06-30 | 2019-06-29 | 2021-10-24 | 100% | 2020-04-28
2023-02-15 | 2017 | DLA Defense Energy Support Center | Major Military Construction | Alaska | United States | DESC1707 | CONSTRUCT TRUCK OFFLOAD FACILITY |  |  |  | 2017-08-24 | 2018-12-15 | 2019-09-23 | 100% | 2018-12-06
2023-02-15 | 2018 | DLA Defense Energy Support Center | Major Military Construction |  | Guam | DESC1709 | Construct Fuel Truck Offload, Andersen AB |  |  |  | 2018-09-21 | 2019-12-15 | 2021-12-15 | 99% | 2021-07-15
2023-02-15 | 2018 | DLA Defense Energy Support Center | Major Military Construction | Utah | United States | DESC1714 | DESC 1714 Replace POL Pumphouse, Hill AFB |  |  |  | 2019-06-07 | 2021-07-12 | 2022-01-30 | 99% | 2022-01-31
2023-02-15 | 2019 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | California | United States | DESC17U3 | New Fuels lab-Point Loma |  |  |  | 2020-01-20 | 2021-01-15 | 2022-12-31 | 99% | 2022-02-15
2023-02-15 | 2018 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1805 | FY18 DLA DESC1805 Upgrade Fuel Wharf, Yokose Fuel Terminal, Japan SABO JAPAN |  |  |  | 2019-03-13 | 2021-04-21 | 2022-04-30 | 99% | 2022-09-01
2023-02-15 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC18S2 | Replace Bulk Diesel System,McAlester Army Ammo Plant |  |  |  | 2019-09-19 | 2021-02-26 | 2022-02-05 | 100% | 2021-09-30
2023-02-15 | 2018 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | Virginia | United States | DESC18U1 | Pier A Rebiuld, Craney Island, VA |  |  |  | 2019-03-13 | 2020-03-13 | 2022-02-28 | 100% | 2020-05-11
2023-02-15 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Arkansas | United States | DESC1902 | Add/Alter to the existing hydrant fuel system and the associated bulk fuel farm that services LRAFB |  |  |  | 2021-09-22 | 2023-03-01 | 2023-10-31 | 66%
2023-02-15 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC1905 | Hot Refuel ReplacementJoint Base Lewis-McChord |  |  |  | 2019-08-19 | 2021-03-31 | 2021-11-16 | 99% | 2021-11-16
2023-02-15 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Ohio | United States | DESC1907 | Replace Hydrant Fueling System, Wright Patterson Air Force Base |  |  |  | 2021-05-06 | 2023-10-23 | 2024-04-20 | 55%
2023-02-15 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1909 | Replace Flight Line Aviation POL Yard, Joint Base Langley-Eustis |  |  |  | 2019-09-30 | 2020-12-31 | 2022-05-05 | 99% | 2022-05-10
2023-02-15 | 2020 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1912 | Construct Fuels Storage Complex for Air National Guard at Tulsa Airport |  |  |  | 2021-08-04 | 2023-01-31 | 2023-05-31 | 67%
2023-02-15 | 2019 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | Virginia | United States | DESC1914 | Replace Ground Vehicle Fuel Facility, Joint Base Langley-Eustis |  |  |  | 2019-06-17 | 2020-12-31 | 2022-09-30 | 99% | 2022-09-30
2023-02-15 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Texas | United States | DESC19I1 | Construct Aerospace Facility Joint Base San Antonio |  |  |  | 2019-08-07 | 2020-11-20 | 2022-02-28 | 99% | 2022-03-09
2023-02-15 | 2019 | DLA Defense Energy Support Center | Major Military Construction |  | Guam | DESC19S2 | Convert Bulk Tanks at Sasa Valley, Guam |  |  |  | 2019-11-04 | 2022-10-10 | 2023-03-03 | 95%
2023-02-15 | 2020 | DLA Defense Energy Support Center | Major Military Construction | Ohio | United States | DESC19S4 | Replace Fuel Facilities, Columbus Air Force Base |  |  |  | 2020-10-16 | 2021-10-15 | 2022-02-22 | 99% | 2022-08-31
2023-02-15 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC2002 | Bulk Fuel Storage Tanks Phase 1, Manchester, WA. |  |  |  | 2022-01-03 | 2024-01-20 | 2024-05-21 | 50%
2023-02-15 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Texas | United States | DESC2003 | Replace Fuel FacilityReplace Fuel Facility, Ft Hood, Texas |  |  |  | 2021-08-28 | 2023-11-12 | 2024-05-08 | 53%
2023-02-15 | 2020 | DLA Defense Energy Support Center | Major Military Construction | Rhode Island | United States | DESC20S1 | Replace Fuels Storage Complex, Warwick, Ri |  |  |  | 2021-05-25 | 2023-08-23 | 2025-05-25 | 5%
2023-02-15 | 2021 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC2101 | Construct Fuels Receipt Area Storage Tank, Beale BARF, CA |  |  |  | 2021-10-28 | 2023-10-09 | 2024-01-19 | 33%
2023-02-15 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC2104A | Construct Retail Fuel Facilities &#x28;Lewis North&#x29;,Joint Base Lewis-McChord |  |  |  | 2022-03-01 | 2023-10-23 | 2024-04-20 | 32%
2023-02-15 | 2021 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC2104B | Joint Base Lewis-McChord, Construct Retail Fuel Facilities |  |  |  | 2022-02-01 | 2023-05-16 | 2023-05-16 | 37%
2023-02-15 | 2022 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC21E1 | Admin Facilities, Chibana Compound, OkinawaAdmin Facilities, Chibana Compound, Okinawa |  |  |  | 2022-10-31 | 2025-06-29 | 2025-06-29 | 2%
2023-02-15 | 2015 | DLA Defense National Stockpile Center | Major Military Construction | Maryland | United States | DESC1507 | Construct Hydrant Fuel System Andrews AFB MD |  |  |  | 2016-10-31 | 2018-02-07 | 2019-11-13 | 100% | 2019-11-13
2023-02-15 | 2015 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1501 | Replace Access Control Point, Richmond |  |  |  | 2018-02-23 | 2019-08-12 | 2021-05-31 | 100% | 2021-06-01
2023-02-15 | 2020 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1901 | Replace DLA Avation Phase II Richmond,VA |  |  |  | 2021-01-28 | 2020-12-11 | 2024-03-05 | 35%
2023-02-06 | 2014 | DoD Education Activity | Major Military Construction | Virginia | United States | AM00021 | REPLACE QUANTICO MIDDLE/HIGH SCHOOL |  |  |  | 2017-12-04 | 2020-01-09 | 2020-10-13 | 51%
2023-02-06 | 2019 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00029 | Fort Campbell Middle School |  |  |  | 2021-02-01 | 2023-09-09 | 2024-01-02 | 34%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction | New York | United States | AM00033 | USMA - REPLACE WEST POINT ELEMENTARY SCHOOL (PN AM00033) |  |  |  | 2017-03-21 | 2020-03-05 | 2021-04-23 | 99% | 2020-01-06
2023-02-06 | 2014 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00046 | Design and Construct new Primary School at Hanscom | 246 |  |  | 2017-03-23 | 2019-09-09 | 2019-10-16 | 100% | 2019-08-16
2023-02-06 | 2017 | DoD Education Activity | Major Military Construction | Delaware | United States | AM00047 | AM00047 FY17 WELCH ES - DOVER AIR BASE MS AT DOVER AFB |  |  |  | 2019-03-30 | 2021-12-24 | 2022-07-08 | 51%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School |  | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2021-02-09 | 100%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 8 | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2021-02-09 | 100%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 9 |  |  | 2016-10-20 | 2020-06-10 | 2021-02-09 | 100%
2023-02-06 | 2015 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00051 | Lejeune High School Addition/Renovation |  |  |  | 2017-04-12 | 2020-03-28 | 2021-04-09 | 100%
2023-02-06 | 2015 | DoD Education Activity | Major Military Construction |  | United States | AM00103 | Consolidate/Replace W.T. Sampson Elementary School |  |  |  | 2016-07-01 | 2018-11-26 | 2021-10-09 | 100%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00110 | Replace/Renovate Maxwell ES/MS |  |  |  | 2017-04-12 | 2020-05-28 | 2022-09-01 | 94%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00110 | Replace/Renovate Maxwell ES/MS | 27 |  |  | 2017-04-12 | 2020-05-28 | 2022-09-01 | 94%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction |  | Spain | AM00115 | Rota Elementary and High School Additions |  |  |  | 2016-07-20 | 2019-03-27 | 2021-04-21 | 96%
2023-02-06 | 2021 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00182 | Replace Van Voorhis Elementary School |  |  |  | 2021-08-30 | 2025-09-28 | 2025-10-26 | 31%
2023-02-06 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School |  |  |  | 2017-01-09 | 2019-05-08 | 2019-07-01 | 98% | 2019-10-31
2023-02-06 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School | 89 |  |  | 2017-01-09 | 2019-05-08 | 2019-07-01 | 98% | 2019-10-31
2023-02-06 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School |  |  |  | 2016-09-12 | 2018-12-24 | 2019-03-15 | 99% | 2019-08-22
2023-02-06 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School | 45 |  |  | 2016-09-12 | 2018-12-24 | 2019-03-15 | 100% | 2019-08-22
2023-02-06 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 1 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 98% | 2021-05-12
2023-02-06 | 2017 | DoD Education Activity | Major Military Construction |  | Germany | EU00039 | Replace Sembach Middle/High School |  |  |  | 2019-07-08 | 2019-12-15 | 2019-12-15 | 13% | 2020-04-29
2023-02-06 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement |  |  |  | 2017-06-30 | 2020-01-12 | 2020-06-28 | 100% | 2021-03-26
2023-02-06 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00049 | Replace Hainerberg Elementary School |  |  |  | 2018-07-09 | 2021-07-23 | 2021-07-23 | 97% | 2021-04-23
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00051 | FY16 DoDEA-E EU00051 Replace Patch Elementary School | 51 |  |  | 2019-01-23 | 2021-01-23 | 2021-03-25 | 87% | 2022-08-16
2023-02-06 | 2015 | DoD Education Activity | Major Military Construction |  | Belgium | EU00064 | Replace Brussels Elementary/ High School |  |  |  | 2017-10-25 | 2020-10-24 | 2020-10-24 | 46%
2023-02-06 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00068 | Replace Grafenwoehr |  |  |  | 2018-09-12 | 2021-03-16 | 2021-06-08 | 90%
2023-02-06 | 2018 | DoD Education Activity | Major Military Construction |  | Italy | EU00117 | Vicenza High School Replacement |  |  |  | 2019-09-27 | 2022-01-27 | 2023-05-08 | 48%
2023-02-06 | 2017 | DoD Education Activity | Major Military Construction |  | Germany | EU00183 | Vilseck High School Field House |  |  |  | 2020-08-03 | 2021-04-29 | 2021-07-17 | 75% | 2022-03-24
2023-02-06 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00017 | Killin Elementary School Replacement/Renovation |  |  |  | 2017-01-11 | 2020-11-17 | 2022-11-23 | 90%
2023-02-06 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00022 | E.J King HS Addition/ Renovate |  |  |  | 2019-08-21 | 2022-08-05 | 2021-12-31 | 100% | 2021-09-10
2023-02-06 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00023 | FY15 DODS PA00023 Renovate Edgren High School, Misawa Air Base, Japan |  |  |  | 2017-02-07 | 2019-05-28 | 2020-01-24 | 99%
2023-02-06 | 2017 | DoD Education Activity | Major Military Construction |  | Japan | PA00032 | Replace Kadena ES |  |  |  | 2018-04-02 | 2021-02-15 | 2022-04-13 | 99%
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146130F | MOTOR TRANSPORTATION/COMM SHOP REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 17% | 2025-12-10
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146142F | FIRE STATIONS REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 16% | 2025-12-10
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146162F | PMO/H&HS & MWHS-2 HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 24% | 2025-12-10
2023-02-15 | 2015 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146193 | WATER TREATMENT PLANT REPLACEMENT |  |  |  | 2017-01-05 | 2020-02-28 | 2022-03-23 | 100% | 2022-02-08
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146194 | UNMANNED AIRCRAFT SYSTEM FACILITIES |  |  |  | 2016-09-14 | 2018-10-04 | 2019-01-29 | 100% | 2020-01-30
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146197 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2022-05-10 | 2025-06-24 | 2025-06-24 | 1% | 2025-06-25
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146199 | AIRCRAFT MAINTENANCE HANGAR - INC 1 |  |  |  | 2020-01-06 | 2022-07-14 | 2023-04-02 | 87% | 2023-04-02
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146222 | AIRFIELD SECURITY IMPROVEMENTS |  |  |  | 2019-05-02 | 2021-06-10 | 2021-06-10 | 95% | 2021-10-08
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146235 | FLIGHTLINE UTILITY MODERNIZATION - INC 1 |  |  |  | 2020-01-06 | 2022-07-14 | 2023-03-20 | 86% | 2023-04-02
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146246F | BT-11 RANGE OPERATIONS CENTER REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 1% | 2025-12-10
2023-02-15 | 2020 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M00146249 | MCAS CHERRY POINT PERIMETER SECURITY: SLOCUM/NUGENT |  |  |  | 2021-03-04 | 2022-03-05 | 2022-08-11 | 47% | 2022-08-09
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146254F | STATION ACADEMIC FACILITY/AUDITORIUM REPLACE |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 17% | 2025-12-10
2023-02-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M00146766 | F-35B LIFT SYSTEM REPAIR FACILITY |  |  |  | 2018-10-13 | 2020-01-08 | 2021-04-12 | 100% | 2021-04-01
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146990 | F-35B VERTICAL LIFT FAN TEST FACILITY |  |  |  | 2021-06-10 | 2023-05-01 | 2023-05-10 | 98% | 2023-08-09
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M00243312 | PMO FACILITY REPLACEMENT |  |  |  | 2022-02-03 | 2022-02-03 | 2022-08-22 | 1% | 2022-08-22
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263403 | RECRUIT RECONDITIONING CENTER & BARRACKS |  |  |  | 2018-08-14 | 2021-02-28 | 2022-03-18 | 100% | 2022-02-18
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263404 | RANGE IMPROVEMENTS & MODERNIZATION, PHASE 2 |  |  |  | 2019-07-24 | 2021-08-17 | 2022-03-23 | 82% | 2022-05-26
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264542 | TBS FIRE STATION BUILDING 533 REPLACEMENT |  |  |  | 2019-06-13 | 2020-10-30 | 2022-08-30 | 58% | 2022-12-30
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264588 | FULLER ROAD IMPROVEMENTS |  |  |  | 2018-10-13 | 2020-06-06 | 2021-04-09 | 100% | 2021-05-12
2023-02-15 | 2015 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264635 | AMMUNITION SUPPLY POINT EXPANSION |  |  |  | 2016-11-30 | 2018-03-25 | 2021-07-29 | 100% | 2021-07-27
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264677 | TECOM SCHOOLS ACADEMIC INSTRUCTION FACILITY |  |  |  | 2016-04-14 | 2018-01-05 | 2018-10-23 | 100% | 2019-12-02
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264719 | WARGAMING CENTER |  |  |  | 2021-04-05 | 2023-07-05 | 2023-07-05 | 1% | 2023-07-05
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264724 | AMMUNITION SUPPLY POINT UPGRADE, PHASE 2 |  |  |  | 2019-08-29 | 2021-01-30 | 2021-07-01 | 100% | 2021-07-01
2023-02-15 | 2020 | Marine Corps Active | Unspecified Minor Military Construction | Virginia | United States | M00264733 | RUNWAY 02 INSTRUMENT LANDING SYSTEM (ILS) |  |  |  | 2020-10-13 | 2021-11-10 | 2022-12-30 | 51% | 2022-08-09
2023-02-15 | 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318861 | FACILITY MODIFICATIONS FOR VMU, MWSD AND CH53E |  |  |  | 2015-09-15 | 2018-08-11 | 2021-02-03 | 100% | 2021-02-03
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318863 | AIRCRAFT MAINTENANCE HANGAR UPGRADES |  |  |  | 2016-10-03 | 2019-04-17 | 2020-07-07 | 99% | 2022-12-16
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318877 | MOKAPU GATE ENTRY CONTROL AT/FP COMPLIANCE |  |  |  | 2020-10-07 | 2022-01-07 | 2022-02-11 | 100% | 2022-07-01
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  |  |  | 2014-10-14 | 2016-12-18 | 2019-10-24 | 100% | 2019-10-28
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318887 | LHD PAD CONVERSIONS MV-22 LANDING PADS |  |  |  | 2019-01-11 | 2020-08-19 | 2021-01-25 | 100% | 2021-03-17
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318902 | AIRFIELD LIGHTING MODERNIZATION |  |  |  | 2016-12-02 | 2019-06-06 | 2021-08-13 | 100% | 2021-07-16
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  |  |  | 2015-04-28 | 2017-01-03 | 2021-12-20 | 100% | 2018-06-20
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318908 | MV-22 HANGAR |  |  |  | 2015-04-28 | 2017-01-03 | 2021-12-20 | 100% | 2018-06-20
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318923 | REGIMENTAL CONSOLIDATED COMM/ELEC FACILITY |  |  |  | 2017-09-04 | 2020-03-08 | 2022-05-21 | 100% | 2021-05-21
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318946 | CORROSION CONTROL HANGAR |  |  |  | 2019-06-14 | 2021-09-07 | 2022-08-27 | 100% | 2022-11-30
2023-02-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | M00318947 | MARINE CORPS TRAINING AREA BELLOWS PERIMETER SECURITY FENCE |  |  |  | 2022-04-08 | 2023-04-24 | 2023-04-24 | 1% | 2024-01-31
2023-02-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | M00318964 | RAPPEL TOWER TRAINING FACILITY |  |  |  | 2022-02-01 | 2023-04-19 | 2023-04-19 | 1% | 2023-08-19
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681079 | POTABLE WATER DISTRIBUTION IMPROVEMENTS |  |  |  | 2019-12-26 | 2022-05-30 | 2022-11-20 | 72% | 2023-10-26
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M006811090 | 1 MEF CONSOLIDATED INFORMATION CENTER |  |  |  | 2020-10-08 | 2024-01-07 | 2024-01-07 | 1% | 2024-01-07
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction | California | United States | M006811090A | 1 MEF CONSOLIDATED INFORMATION CENTER (INC) |  |  |  | 2021-04-06 | 2024-01-07 | 2024-01-07 | 1% | 2024-01-07
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction | California | United States | M006811130 | 1ST MARDIV OPERATIONS COMPLEX |  |  |  | 2021-03-04 | 2023-05-13 | 2023-10-20 | 1% | 2023-10-10
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M006811310 | AMMUNITION SUPPLY POINT UPGRADE |  |  |  | 2018-10-11 | 2020-10-10 | 2023-03-26 | 55% | 2024-02-23
2023-02-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M006811599 | STUART MESA ROAD SAFETY IMPROVEMENT |  |  |  | 2019-03-13 | 2020-02-26 | 2020-04-16 | 100% | 2020-04-16
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006811901 | AAV-ACV MAINTENANCE & WAREHOUSE FACILITY |  |  |  | 2019-05-16 | 2022-06-09 | 2022-12-09 | 70% | 2023-01-30
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M006812000 | 62 AREA MESS HALL AND CONSOLIDATED WAREHOUSE |  |  |  | 2020-12-31 | 2025-02-14 | 2025-02-14 | 1% | 2025-06-13
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681334 | SUPPLY WAREHOUSE SOI - WEST |  |  |  | 2019-09-05 | 2021-08-06 | 2021-10-13 | 100% | 2022-01-26
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006815001 | FULL MOTION TRAINER FACILITY |  |  |  | 2019-04-23 | 2020-10-15 | 2022-01-12 | 97% | 2022-01-12
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006815002 | ELECTRICAL UPGRADES |  |  |  | 2019-04-08 | 2020-03-30 | 2020-03-20 | 100% | 2020-03-19
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681574 | FIRE EMERGENCY RESPONSE STATION |  |  |  | 2019-09-05 | 2021-06-07 | 2021-12-10 | 91% | 2021-12-10
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | California | United States | M00681970 | AMMUNITION SUPPLY POINT FACILITIES PULGAS |  |  |  | 2016-01-13 | 2018-04-27 | 2020-11-27 | 100% | 2022-12-30
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169464 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2017-07-13 | 2020-07-13 | 2022-07-08 | 100% | 2022-06-29
2023-02-15 | 2022 | Marine Corps Active | Unspecified Minor Military Construction | South Carolina | United States | M60169492 | INSTRUMENT LANDING SYSTEM |  |  |  | 2022-07-28 | 2023-06-08 | 2023-06-08 | 1% | 2023-06-08
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M62204930 | COMBAT VEHICLE REPAIR FACILITY |  |  |  | 2018-05-02 | 2020-05-02 | 2020-05-17 | 100% | 2020-09-22
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction |  | Japan | M626131005 | VTOL PAD - SOUTH
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction |  | Japan | M626131006 | KC130J ENLISTED AIRCREW TRAINER FACILITY
2023-02-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction |  | Japan | M626131010U | SEAWALL ACCESS |  |  |  | 2021-09-23 | 2022-07-06 | 2023-04-20 | 1% | 2023-04-20
2023-02-15 | 2017 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131701 | WHOLEHOUSE REVITALIZATION NORTH SIDE TOWNHOUSES PHASE 2
2023-02-15 | 2019 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131901 | WHOLEHOUSE REVITALIZATION MIDRISE 657 |  |  |  | 2022-10-14 | 2024-07-26 | 2024-07-26 | 1% | 2024-07-26
2023-02-15 | 2020 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626132001 | WHOLEHOUSE REVITALIZATION MIDRISE 1209 |  |  |  | 2021-02-25 | 2023-07-02 | 2023-07-02 | 12% | 2023-07-02
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M62613604 | SECURITY MODIFICATIONS - CVW5/MAG12 HQ
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974539 | ENLISTED DINING FACILITY & COMMUNITY BLDGS |  |  |  | 2018-07-17 | 2021-07-02 | 2022-04-04 | 99% | 2022-06-17
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974602 | AIRCRAFT MAINT. FACILITIES & APRON (SO. CALA) |  |  |  | 2017-08-10 | 2019-06-30 | 2020-06-22 | 100% | 2020-06-18
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974612 | VMX-22 MAINTENANCE HANGAR |  |  |  | 2019-06-27 | 2022-06-06 | 2023-05-17 | 73% | 2023-05-17
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011043 | WATER TREATMENT PLANT REPLACEMENT HADNOT PT |  |  |  | 2022-07-22 | 2025-08-01 | 2025-08-01 | 1% | 2025-08-01
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011199F | CLB HEADQUARTERS FACILITIES REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 17% | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011203F | COURTHOUSE BAY FIRE STATION REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011280 | 2ND RADIO BN COMPLEX PHASE 1 |  |  |  | 2017-06-13 | 2019-06-24 | 2023-08-10 | 95% | 2023-08-10
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011300F | 2D TANK BN/CO HQ AND ARMORY REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 11% | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011312F | MCES APPLIED INSTRUCTION FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011320 | BACHELOR ENLISTED QUARTERS |  |  |  | 2018-10-12 | 2020-10-23 | 2022-10-23 | 77% | 2023-03-31
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011338F | II MEF SIMULATION/TRAINING CENTER REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-11-27 | 1% | 2026-01-22
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011387F | ONSLOW BEACH BRIDGE REPLACEMENT |  |  |  | 2020-08-07 | 2025-03-06 | 2025-03-06 | 32% | 2025-03-06
2023-02-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011479 | OUTDOOR INFANTRY IMMERSION TRAINER SITE PREP |  |  |  | 2019-06-28 | 2020-10-26 | 2021-09-30 | 100% | 2021-09-30
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011483 | ACV-AAV MAINTENANCE FACILITY UPGRADES |  |  |  | 2020-10-09 | 2021-09-28 | 2022-06-22 | 1% | 2022-06-22
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011495 | 10TH MARINES HIMARS COMPLEX |  |  |  | 2020-08-27 | 2023-03-05 | 2023-04-07 | 1% | 2023-04-07
2023-02-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011498 | WC504 MECHANICAL SYSTEM REPLACEMENT |  |  |  | 2018-11-28 | 2019-11-09 | 2023-02-25 | 100% | 2023-02-25
2023-02-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011503 | WC500 MECHANICAL SYSTEM REPLACEMENT |  |  |  | 2018-11-28 | 2019-11-09 | 2022-05-31 | 100% | 2022-07-29
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011505F | RAILROAD TRESTLE REPLACEMENT |  |  |  | 2020-08-07 | 2025-03-06 | 2025-03-06 | 20% | 2025-03-06
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011506F | NCIS FACILITIES REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011507F | WTBN HEADQUARTERS REPLACEMENT |  |  |  | 2020-09-29 | 2024-05-27 | 2025-02-07 | 1% | 2025-02-07
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011509F | 2D MARDIV REGIMENTAL HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 20% | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011512F | MCCSSS LOG OPS SCHOOL REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-12-27 | 1% | 2026-01-22
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011518F | HADNOT POINT FIRE STATION REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011519F | LSSS FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011520F | 1ST BN, 8TH MARINES BN HQ REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 17% | 2027-07-20
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011522F | 22D, 24TH, AND 26TH MEU HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 25% | 2027-07-20
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011524F | 2D TRANSPORTATION SUPPORT BN HQS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 17% | 2027-07-20
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011525F | ENVIRONMENTAL MANAGEMENT DIVISION REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 12% | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011527F | LOGCOM CSP WAREHOUSE REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-12-27 | 1% | 2026-01-22
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011529F | MC ADVISOR BATTALION HQS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2027-07-20 | 1% | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011533F | PMO FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011603F | BACHELOR ENLISTED QUARTERS REPAIR
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011604F | OPEN MESS HALL REPAIR |  |  |  | 2022-06-14 | 2023-11-22 | 2023-11-22 | 1% | 2023-12-05
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800 | II MEF OPERATIONS CENTER REPLACEMENT |  |  |  | 2021-01-05 | 2026-07-23 | 2027-05-09 | 1% | 2026-03-20
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800A | II MEF OPERATIONS CENTER REPLACEMENT (INC) |  |  |  | 2021-03-16 | 2026-07-23 | 2027-05-09 | 1% | 2026-03-20
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800B | II MEF OPERATIONS CENTER REPLACEMENT (INC) |  |  |  | 2022-06-09 | 2026-07-23 | 2027-05-09 | 1% | 2026-03-20
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011801 | 2ND MARDIV/2ND MLG OPS CENTER REPLACEMENT |  |  |  | 2021-01-05 | 2026-07-23 | 2027-05-09 | 1% | 2026-03-20
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001378F | CH-53K MAINTENANCE HANGAR REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001686 | RADAR AIR TRAFFIC CONTROL FACILITY ADDITION |  |  |  | 2016-10-12 | 2018-04-06 | 2021-04-22 | 100% | 2021-03-30
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001695F | CNATT CLASSROOM BUILDING REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001707F | BACHELOR ENLISTED QUARTERS REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2023-02-15 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001726 | REGIONAL COMMUNICATION STATION |  |  |  | 2014-06-13 | 2015-12-20 | 2019-02-01 | 100% | 2018-05-31
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001728F | C-12W AIRCRAFT MAINTENANCE HANGAR REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001729 | OPERATIONAL TRAINER FACILITY |  |  |  | 2016-10-12 | 2018-04-06 | 2021-04-22 | 100% | 2021-03-30
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001883F | HADNOT POINT MESS HALL REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004947 | WELDING AND BODY REPAIR SHOP FACILITY |  |  |  | 2020-02-14 | 2022-05-04 | 2022-09-12 | 45% | 2023-01-31
2023-02-15 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | Georgia | United States | M67004971 | CONSTRUCT LOGCOM OPEN STORAGE LOT |  |  |  | 2018-03-29 | 2018-11-06 | 2019-07-05 | 100% | 2019-07-10
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004972 | GROUND SOURCE HEAT PUMPS |  |  |  | 2017-04-05 | 2019-01-28 | 2019-02-23 | 100% | 2022-06-30
2023-02-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | Georgia | United States | M67004976 | GATE 15 MOCK ROAD ENTRY CONTROL POINT |  |  |  | 2022-04-05 | 2023-07-15 | 2023-07-15 | 1% | 2023-07-15
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004977 | COMBAT VEHICLE WAREHOUSE |  |  |  | 2019-03-21 | 2021-04-29 | 2021-05-27 | 100% | 2021-03-02
2023-02-15 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | District Of Columbia | United States | M67029007 | Communications Center for Marine Barracks, Washington, DC |  |  |  | 2017-05-03 | 2018-04-19 | 2020-07-30 | 100% | 2019-12-23
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | California | United States | M673991232 | MICROGRID EXPANSION |  |  |  | 2017-10-10 | 2019-04-19 | 2021-04-23 | 100% | 2021-04-23
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67399192 | POTABLE WATER TREATMENT/BLENDING FACILITY |  |  |  | 2018-10-13 | 2021-09-28 | 2023-02-15 | 89% | 2022-10-31
2023-02-15 | 2015 | Marine Corps Active | Major Military Construction | California | United States | M67399222 | E-LMR SLICE COMMUNICATION TOWERS |  |  |  | 2016-09-14 | 2019-03-04 | 2020-02-14 | 100% | 2020-02-06
2023-02-15 | 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400213 | HANGAR & RINSE FACILITY MODERNIZATIONS
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M67400606 | MILITARY WORKING DOG FACILITIES (CAMP HANSEN) |  |  |  | 2016-09-29 | 2018-03-26 | 2021-11-19 | 100% | 2019-09-03
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction |  | Japan | M67400807 | AIRCRAFT MAINTENANCE COMPLEX
2023-02-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction |  | Japan | M67400901U | FORCE PROTECTION UPGRADES CVI GATE 4 CAMP FUJI |  |  |  | 2021-07-15 | 2022-03-14 | 2022-03-14 | 12% | 2022-10-26
2023-02-15 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M67604132 | ORDNANCE BULD-UP FACILITY |  |  |  | 2016-09-14 | 2017-10-30 | 2017-10-30 | 100% | 2017-12-18
2023-02-15 | 2020 | Marine Corps Active | Major Military Construction | Florida | United States | M67695009 | POLICE STATION AND EOC FACILITY REPLACEMENT |  |  |  | 2020-09-30 | 2022-03-25 | 2023-01-27 | 1% | 2023-01-27
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR - INC 1 |  |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 100% | 2020-06-26
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR - INC 2 | M67865198A |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 100% | 2020-06-26
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865203 | F-35 F-35 Aircraft Parking Apron |  |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 100% | 2020-06-26
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67865210 | F-35 SIMULATOR FACILITY |  |  |  | 2018-09-13 | 2020-05-20 | 2021-02-26 | 100% | 2021-01-20
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M67865222 | F-35 VERTICAL LANDING PADS AND TAXIWAY |  |  |  | 2019-03-28 | 2020-09-27 | 2021-02-06 | 100% | 2020-07-28
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M67865238 | AIRFIELD SECURITY IMPROVEMENTS |  |  |  | 2019-03-22 | 2020-04-06 | 2020-04-06 | 51% | 2019-11-25
2023-02-15 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865249 | COMMUNICATIONS COMPLEX & INFRASTRUCTURE UPGRADE |  |  |  | 2018-01-01 | 2019-09-24 | 2020-10-01 | 100% | 2020-08-19
2023-02-15 | 2021 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M67865280 | ENTRY CONTROL POINT IMPROVEMENTS |  |  |  | 2021-07-14 | 2023-03-07 | 2023-07-14 | 35% | 2023-07-14
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557270 | ACE GYM & DINING |  |  |  | 2019-09-26 | 2022-03-25 | 2022-07-18 | 100% | 2022-10-07
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N41557280 | AVIATION ADMIN BUILDING |  |  |  | 2022-05-18 | 2024-08-22 | 2024-08-22 | 1% | 2024-08-22
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction |  | Guam | N41557290 | EARTH COVERED MAGAZINES |  |  |  | 2022-01-25 | 2025-01-10 | 2025-01-10 | 35% | 2025-01-28
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557295 | ORDNANCE OPS |  |  |  | 2019-09-30 | 2021-12-04 | 2021-12-04 | 100% | 2022-01-31
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557296 | ORDNANCE OPERATIONS ADMIN |  |  |  | 2021-03-31 | 2023-03-28 | 2023-08-13 | 1% | 2023-08-13
2023-02-15 | 2018 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557601 | AIRCRAFT MAINTENANCE HANGAR #2 |  |  |  | 2018-05-30 | 2020-10-02 | 2021-10-22 | 100% | 2022-03-15
2023-02-15 | 2016 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557715 | LIVE-FIRE TRAINING RANGE COMPLEX (NW FIELD) |  |  |  | 2017-09-07 | 2020-11-26 | 2023-01-08 | 81% | 2022-07-29
2023-02-15 | 2019 | Marine Corps Active | Major Military Construction |  | Guam | N41557735 | MACHINE GUN RANGE - INC 1 |  |  |  | 2021-10-12 | 2024-10-25 | 2024-10-25 | 8% | 2024-10-25
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159305 | 4TH MARINES REGIMENT FACILITIES |  |  |  | 2022-05-18 | 2024-08-22 | 2024-08-22 | 1% | 2024-08-22
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159306 | COMBAT LOGISTICS BATALLION-4 FACILITY |  |  |  | 2022-05-18 | 2024-09-06 | 2024-09-06 | 1% | 2024-09-06
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159307 | CONSOLIDATED ARMORY |  |  |  | 2022-04-28 | 2024-08-02 | 2024-08-02 | 1% | 2024-08-02
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159310 | INFANTRY BATTALION COMPANY HQ |  |  |  | 2022-05-11 | 2024-08-18 | 2024-08-18 | 1% | 2024-08-18
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159311 | CENTRAL FUEL STATION |  |  |  | 2021-03-29 | 2023-08-23 | 2023-08-23 | 1% | 2023-08-23
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159312 | DISTRIBUTION WAREHOUSE |  |  |  | 2021-04-05 | 2024-03-12 | 2024-03-12 | 1% | 2024-03-12
2023-02-15 | 2022 | Marine Corps Active | Major Military Construction |  | Guam | N61159326 | PRINCIPAL END ITEM (PEI) WAREHOUSE |  |  |  | 2022-04-15 | 2024-07-25 | 2024-07-25 | 1% | 2024-07-25
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction |  | Guam | N61159802 | BASE WAREHOUSE |  |  |  | 2021-08-30 | 2023-12-07 | 2023-12-07 | 1% | 2023-12-07
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction |  | Guam | N61159803 | INDIVIDUAL COMBAT SKILLS TRAINING |  |  |  | 2021-08-27 | 2022-08-27 | 2022-09-04 | 1% | 2023-05-31
2023-02-15 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159804 | CENTRAL ISSUE FACILITY |  |  |  | 2021-04-05 | 2024-03-12 | 2024-03-12 | 1% | 2024-03-12
2023-02-15 | 2019 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | N62813216 | ELECTRICAL DISTRIBUTION INTERCONNECT |  |  |  | 2020-02-17 | 2020-12-29 | 2022-09-30 | 64% | 2023-03-27
2023-02-15 | 2018 | Marine Corps Reserve | Major Military Construction | Louisiana | United States | M67861650 | AIRCRAFT APRON, TAXIWAY & SUPPORT FACILITIES |  |  |  | 2019-04-02 | 2020-11-20 | 2020-11-20 | 100% | 2020-11-20
2023-02-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Louisiana | United States | M68479102 | MARINE CORPS RESERVE CENTER, BROOKLYN NY POV PARKING
2023-02-15 | 2017 | Marine Corps Reserve | Major Military Construction | Louisiana | United States | M68479135 | ELECTRIC FEEDER DUCTBANK |  |  |  | 2019-02-05 | 2020-01-28 | 2020-10-31 | 96% | 2020-11-04
2023-02-15 | 2021 | Marine Corps Reserve | Major Military Construction | Maryland | United States | M68479303 | RESERVE TRAINING CENTER, CAMP FRETTERD, MD |  |  |  | 2022-02-16 | 2024-09-17 | 2024-12-13 | 1% | 2025-01-09
2023-02-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Louisiana | United States | M68479811 | MCRC BROOKLYN FIRE PROTECTION SYSTEM AND ACCESS GATES
2023-02-15 | 2016 | Marine Corps Reserve | Major Military Construction | Virginia | United States | N50092152 | RESERVE TRAINING CENTER COMPLEX |  |  |  | 2019-10-14 | 2021-09-14 | 2022-02-04 | 87% | 2022-02-04
2023-02-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447091 | HANGAR 1050 ADDITION VMGR-234 PROP SHOP |  |  |  | 2020-09-11 | 2021-08-27 | 2022-01-02 | 48% | 2023-06-30
2023-02-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447181 | HEADQUARTERS BUILDING ADDITION |  |  |  | 2020-10-09 | 2021-09-26 | 2022-08-10 | 1% | 2023-08-16
2023-02-15 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447222 | OVERHEAD COVER AT MARINE CORPS RESERVE CENTER, EL PASO |  |  |  | 2020-10-08 | 2021-09-21 | 2020-09-21 | 1% | 2022-01-12
2023-01-31 | 2013 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  |  |  | 2013-07-31 | 2015-08-30 | 2016-05-12 | 99% | 2017-04-13
2023-01-31 | 2014 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #2 | 646 |  |  | 2013-07-31 | 2015-08-30 | 2016-05-12 | 99% | 2017-04-13
2023-01-31 | 2016 | Missile Defense Agency | Major Military Construction |  | Poland | 640 | Aegis Ashore Missile Defense System Complex |  |  |  | 2016-03-14 | 2018-05-30 | 2023-04-27 | 96%
2023-01-31 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 653 | MDC Switchgear Facility |  | 379000 | 657 | 2017-08-31 | 2019-08-14 | 2021-09-29 | 98% | 2021-09-29
2023-01-31 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 657 | Long Range Discrimination Radar Complex, Phase 1 |  |  |  | 2017-06-05 | 2020-11-27 | 2020-09-29 | 100% | 2020-09-29
2023-01-31 | 2019 | Missile Defense Agency | Major Military Construction | Alaska | United States | 659 | Long Range Discrimination Radar Complex, Phase 2 |  |  |  | 2019-04-29 | 2021-06-30 | 2022-07-28 | 100% | 2022-04-18
2023-01-31 | 2017 | Missile Defense Agency | Unspecified Minor Military Construction |  | Israel | 673 | Integrated Electronic Security System (IESS) Installation & Security Infrastructure Upgrades |  |  |  | 2018-08-15 | 2019-05-31 | 2023-01-31 | 99%
2023-01-31 | 2018 | Missile Defense Agency | Major Military Construction | Alaska | United States | 674 | Missile Field #4 |  |  |  | 2018-04-25 | 2021-09-30 | 2023-03-10 | 98%
2023-01-31 | 2019 | Missile Defense Agency | Major Military Construction | Alaska | United States | 679 | Missile Field #1 Expansion |  |  |  | 2022-05-06 | 2023-10-21 | 2023-10-21 | 32%
2023-01-31 | 2021 | Missile Defense Agency | Major Military Construction | Alaska | United States | 680 | Communications Center |  |  |  | 2021-06-01 | 2023-01-31 | 2024-06-14 | 61%
2023-01-31 | 2021 | Missile Defense Agency | Unspecified Minor Military Construction |  | Turkey | 689 | Integrated Electronic Security System Installation and Security Infrastructure Upgrades |  |  |  | 2022-09-25 | 2023-10-01 | 2023-12-22 | 0%
2023-02-03 | 2021 | National Geospatial-Intelligence Agency | Unspecified Minor Military Construction | Missouri | United States | ARN13-0020 | NGA Arnold Rear ACP |  |  |  | 2021-11-17 | 2023-11-17 | 2023-11-17 | 55%
2023-01-31 | 2018 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016A | Next NGA West (N2W) Complex, Ph. 1 |  |  |  | 2019-04-23 | 2023-10-19 | 2024-06-28 | 71%
2023-01-31 | 2018 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016A-IPO | IPO Temporary Facility associated with Next NGA West (N2W) Complex, Ph. 1 |  |  |  | 2019-07-10 | 2024-07-08 | 2024-07-08 | 76%
2023-01-31 | 2019 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016B | Next NGA West (N2W) Complex, Ph. 2 |  |  |  | 2019-04-23 | 2023-10-19 | 2024-06-28 | 63%
2022-12-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 30583 | East Campus Building 2 (ECB2) |  |  |  | 2016-07-18 | 2020-09-10 | 2022-02-23 | 99% | 2022-08-15
2022-12-31 | 2019 | National Security Agency | Major Military Construction | Maryland | United States | 32100 | Mission Support Operations Warehouse Facility |  |  |  | 2020-02-27 | 2022-11-17 | 2022-11-17 | 91% | 2022-11-17
2022-12-31 | 2022 | National Security Agency | Major Military Construction |  | United Kingdom | 34490 | RAF Menwith Hill Main Gate Rehabilitation |  |  |  | 2022-06-06 | 2023-05-24 | 2023-05-24 | 40% | 2022-05-24
2022-12-31 | 2017 | National Security Agency | Major Military Construction | Maryland | United States | 35161 | Access Control Facility/Vistor Control 1 |  |  |  | 2021-09-20 | 2024-03-28 | 2024-03-28 | 7% | 2024-03-28
2022-12-31 | 2019 | National Security Agency | Major Military Construction | Maryland | United States | 35168 | NSAW Recapitalization Building 3 |  |  |  | 2019-05-01 | 2023-04-30 | 2023-05-09 | 76% | 2023-05-09
2022-12-31 | 2022 | National Security Agency | Major Military Construction | Maryland | United States | 38440/38441 | Mission Operations and Records Center |  |  |  | 2022-06-23 | 2026-06-15 | 2026-06-15 | 0%
2022-12-31 | 2022 | National Security Agency | Major Military Construction | Maryland | United States | 38608 | NSAW Recapitalization Building 4 |  |  |  | 2022-05-11 | 2026-05-10 | 2026-05-10 | 5% | 2026-05-10
2023-02-15 | 2016 | Navy Active | Major Military Construction | California | United States | M006811220 | RAW WATER PIPELINE PENDLETON TO FALLBROOK |  |  |  | 2016-12-14 | 2019-03-30 | 2019-03-30 | 100% | 2019-10-02
2023-02-15 | 2016 | Navy Active | Major Military Construction |  | Japan | M62613603 | E-2D OPERATIONAL TRAINER COMPLEX |  |  |  | 2019-01-01 | 2020-07-08 | 2021-03-12 | 1% | 2021-03-12
2023-02-15 | 2014 | Navy Active | Major Military Construction | Illinois | United States | N00128714 | UNACCOMPANIED HOUSING |  |  |  | 2018-08-13 | 2020-08-14 | 2020-10-23 | 100% | 2020-10-23
2023-02-15 | 2017 | Navy Active | Major Military Construction | Illinois | United States | N00128714 | UNACCOMPANIED HOUSING | N00128714A |  |  | 2018-08-13 | 2020-08-14 | 2020-10-23 | 100% | 2020-10-23
2023-02-15 | 2020 | Navy Active | Major Military Construction | Connecticut | United States | N00129898 | SSN BERTHING PIER 32 |  |  |  | 2020-10-13 | 2022-10-26 | 2023-01-31 | 1% | 2022-12-16
2023-02-15 | 2016 | Navy Active | Major Military Construction | Florida | United States | N00204723 | A-SCHOOL UNACCOMPANIED HOUSING (CORRY STATION) |  |  |  | 2017-07-12 | 2019-10-16 | 2020-09-20 | 100% | 2021-02-10
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N00207674 | AIRCRAFT COMPONENT FACILITY |  |  |  | 2019-05-31 | 2020-10-13 | 2021-05-20 | 100% | 2021-04-30
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N00207711 | SECURITY FENCE - AGUADA BOUNDARY |  |  |  | 2019-09-27 | 2020-09-14 | 2020-09-14 | 100% | 2020-09-14
2023-02-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213211 | REPLACE AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2021-05-27 | 2023-12-29 | 2023-12-29 | 43% | 2023-12-29
2023-02-15 | 2021 | Navy Active | Major Military Construction | Florida | United States | N00213211A | REPLACE AIRCRAFT MAINTENANCE HANGAR (CTC)
2023-02-15 | 2014 | Navy Active | Major Military Construction | Florida | United States | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  |  |  | 2014-08-29 | 2016-02-08 | 2018-01-08 | 100% | 2017-07-28
2023-02-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N00213720 | AUTEC AUSTERE QUARTERS |  |  |  | 2019-10-10 | 2021-12-13 | 2023-06-29 | 20% | 2023-10-19
2023-02-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213731 | FIRE STATION |  |  |  | 2019-10-03 | 2020-11-30 | 2022-10-31 | 64% | 2023-02-15
2023-02-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213741 | NAVY GATEWAY INN & SUITES (NGIS) FACILITY |  |  |  | 2019-10-11 | 2022-01-17 | 2022-10-28 | 60% | 2023-03-11
2023-02-15 | 2018 | Navy Active | Major Military Construction | Texas | United States | N00216450 | CONSOLIDATED SQUADRON OPERATIONS & FLIGHT TRAINING BUILDING |  |  |  | 2018-09-19 | 2021-09-04 | 2023-01-31 | 47% | 2023-06-15
2023-02-15 | 2018 | Navy Active | Major Military Construction | Texas | United States | N00216485 | HAZARDOUS WASTE STORAGE AND TRANSFER FACILITY |  |  |  | 2018-09-05 | 2020-03-14 | 2021-01-30 | 100% | 2021-02-26
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N002450888 | HARBOR DRIVE SWITCHING STATION |  |  |  | 2019-04-11 | 2021-08-18 | 2022-11-05 | 80% | 2023-01-29
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N00245110 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2019-08-26 | 2021-03-23 | 2021-03-23 | 100% | 2021-05-31
2023-02-15 | 2017 | Navy Active | Major Military Construction | California | United States | N00245312 | UPGRADE PIER 10 TO 4160 VOLT |  |  |  | 2017-07-13 | 2018-09-30 | 2018-12-15 | 100% | 2018-12-12
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N00245440 | PIER 8 REPLACEMENT - INC 1 |  |  |  | 2019-06-28 | 2021-10-27 | 2021-10-31 | 100% | 2021-06-17
2023-02-15 | 2021 | Navy Active | Major Military Construction | California | United States | N00245443 | PIER 6 REPLACEMENT |  |  |  | 2021-05-14 | 2023-09-17 | 2023-09-17 | 1% | 2023-07-31
2023-02-15 | 2015 | Navy Active | Major Military Construction | California | United States | N00245800 | STEAM DISTRIBUTION SYSTEM DECENTRALIZATION |  |  |  | 2015-10-01 | 2017-10-01 | 2019-04-10 | 100% | 2019-04-10
2023-02-15 | 2017 | Navy Active | Unspecified Minor Military Construction | California | United States | N002461017 | Upgrades for MV-22 Depot Maintenance Program |  |  |  | 2017-10-12 | 2018-12-12 | 2018-12-12 | 100% | 2018-12-06
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N002461018 | CMV-22B AIRFIELD IMPROVEMENTS |  |  |  | 2019-08-08 | 2022-07-25 | 2022-07-25 | 100% | 2023-04-28
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N002461024 | NAVY V-22 HANGAR |  |  |  | 2020-06-25 | 2023-01-01 | 2023-03-03 | 1% | 2023-08-30
2023-02-15 | 2021 | Navy Active | Unspecified Minor Military Construction | California | United States | N00246762 | COMBAT AIRCRAFT LOADING AREA |  |  |  | 2021-11-18 | 2022-11-03 | 2022-11-03 | 1% | 2023-02-28
2023-02-15 | 2017 | Navy Active | Major Military Construction | California | United States | N00246947 | COASTAL CAMPUS ENTRY CONTROL POINT |  |  |  | 2017-04-13 | 2018-10-06 | 2020-03-31 | 100% | 2021-08-27
2023-02-15 | 2018 | Navy Active | Major Military Construction | California | United States | N00246988 | UNDERSEA RESCUE COMMAND OPERATIONS BUILDING |  |  |  | 2018-09-13 | 2021-03-22 | 2022-10-05 | 93% | 2022-11-02
2023-02-15 | 2017 | Navy Active | Major Military Construction | California | United States | N00246991 | COASTAL CAMPUS UTILITIES INFRASTRUCTURE |  | 4715000 | N32414547, M62613604 | 2017-04-13 | 2019-04-23 | 2021-04-30 | 100% | 2021-06-09
2023-02-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N00620240 | TRITON MISSION CONTROL FACILITY |  |  |  | 2017-08-23 | 2020-03-26 | 2021-01-19 | 100% | 2020-07-16
2023-02-15 | 2019 | Navy Active | Major Military Construction | Washington | United States | N00620253 | FLEET SUPPORT FACILITY |  |  |  | 2019-03-25 | 2020-11-28 | 2021-07-06 | 100% | 2021-06-01
2023-02-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N00620256 | E/A-18G MAINTENANCE HANGAR |  |  |  | 2019-02-13 | 2021-07-19 | 2021-10-29 | 100% | 2021-08-18
2023-02-15 | 2019 | Navy Active | Major Military Construction | Washington | United States | N00620258 | NEXT GENERATION JAMMER FACILITY |  |  |  | 2019-03-12 | 2021-03-08 | 2021-01-29 | 100% | 2021-01-29
2023-02-15 | 2019 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414106 | SUBMARINE PROPULSOR MANUFACTURING SUPPORT FAC |  |  |  | 2019-06-26 | 2022-02-13 | 2023-02-17 | 88% | 2023-02-17
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Pennsylvania | United States | N324141098 | SUBMARINE PROPULSOR MACHINE SHOP STAGING FACILITY |  |  |  | 2019-06-26 | 2022-02-13 | 2023-02-01 | 100% | 2023-02-01
2023-02-15 | 2015 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  |  |  | 2015-06-01 | 2017-01-12 | 2021-11-19 | 100% | 2022-07-27
2023-02-15 | 2019 | Navy Active | Major Military Construction | Virginia | United States | N32443256 | SHIPS MAINTENANCE FACILITY |  |  |  | 2021-12-13 | 2024-01-28 | 2024-01-28 | 1% | 2024-01-28
2023-02-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N32443257 | SHIP REPAIR TRAINING FACILITY |  |  |  | 2018-10-01 | 2021-06-18 | 2022-08-31 | 87% | 2022-08-31
2023-02-15 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATERFRONT UTILITIES |  |  |  | 2017-12-29 | 2021-04-15 | 2021-06-30 | 100% | 2021-06-30
2023-02-15 | 2017 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATER FRONT UTILITIES | N32443614A |  |  | 2017-12-29 | 2021-04-15 | 2021-06-30 | 100% | 2021-06-30
2023-02-15 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N32443653 | DRY DOCK FLOOD PROTECTION IMPROVEMENTS |  |  |  | 2020-09-18 | 2023-06-17 | 2023-08-22 | 1% | 2022-11-15
2023-02-15 | 2022 | Navy Active | Major Military Construction | Virginia | United States | N32443678 | DRY DOCK SALTWATER SYSTEM FOR CVN-78 |  |  |  | 2022-10-07 | 2026-09-08 | 2026-09-08 | 1% | 2026-09-08
2023-02-15 | 2019 | Navy Active | Major Military Construction | Maine | United States | N324461074 | EXTEND PORTAL CRANE RAIL |  |  |  | 2019-12-05 | 2021-01-27 | 2022-04-15 | 74% | 2022-05-06
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Maine | United States | N324461088 | ENTRY CONTROL POINT MODERNIZATION |  |  |  | 2019-08-19 | 2020-10-31 | 2021-07-30 | 100% | 2021-07-30
2023-02-15 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446285 | UNACCOMPANIED HOUSING |  |  |  | 2017-07-13 | 2019-05-10 | 2021-01-21 | 100% | 2020-03-31
2023-02-15 | 2018 | Navy Active | Major Military Construction | Maine | United States | N32446293 | PAINT, BLAST AND RUBBER FACILITY |  |  |  | 2019-10-09 | 2022-08-09 | 2022-08-09 | 53% | 2023-06-15
2023-02-15 | 2014 | Navy Active | Major Military Construction | Maine | United States | N32446308 | NCTAMS VLF COMMERCIAL POWER CONNECTION |  | 1104000 | N68436993 | 2016-05-05 | 2018-10-25 | 2018-10-25 | 100% | 2018-10-25
2023-02-15 | 2019 | Navy Active | Major Military Construction | Maine | United States | N32446310 | DRY DOCK #1 SUPERFLOOD BASIN |  |  |  | 2019-12-05 | 2021-01-27 | 2022-04-15 | 88% | 2022-05-06
2023-02-15 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446371 | UTILITY IMPROVEMENTS FOR NUCLEAR PLATFORMS |  |  |  | 2018-04-13 | 2021-09-14 | 2021-09-14 | 100% | 2021-07-12
2023-02-15 | 2021 | Navy Active | Major Military Construction | Virginia | United States | N32446381 | MULTI-MISSION DRY DOCK #1 EXTENSION (INC) |  |  |  | 2021-08-27 | 2028-06-01 | 2028-08-17 | 1% | 2028-08-17
2023-02-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Maine | United States | N32446385 | COMMUNICATIONS ANTENNA |  |  |  | 2018-10-04 | 2019-10-08 | 2019-10-08 | 100% | 2019-10-15
2023-02-15 | 2023 | Navy Active | Major Military Construction | Virginia | United States | N32466381 | MULTI-MISSION DRY DOCK #1 EXTENSION (INC)
2023-02-15 | 2017 | Navy Active | Major Military Construction |  | Djibouti | N3379A223 | OCO: MEDICAL/DENTAL FACILITY |  |  |  | 2018-07-12 | 2020-10-05 | 2022-07-31 | 95% | 2024-02-07
2023-02-15 | 2018 | Navy Active | Major Military Construction |  | Djibouti | N3379A505 | AIRCRAFT PARKING APRON EXPANSION |  |  |  | 2018-11-09 | 2020-06-18 | 2021-11-30 | 100% | 2022-12-31
2023-02-15 | 2021 | Navy Active | Major Military Construction | California | United States | N360423271 | F-35C SIMULATOR FACILITY & ELECTRICAL UPGRADES |  |  |  | 2021-04-08 | 2023-05-03 | 2023-10-16 | 61% | 2023-10-16
2023-02-15 | 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557230 | GSE SHOPS AT NORTH RAMP |  |  |  | 2015-12-01 | 2018-06-19 | 2019-01-29 | 100% | 2019-01-28
2023-02-15 | 2018 | Navy Active | Major Military Construction |  | Japan | N41557250 | MALS FACILITIES |  |  |  | 2018-10-08 | 2021-01-21 | 2022-10-06 | 98% | 2022-10-30
2023-02-15 | 2018 | Navy Active | Major Military Construction | Guam | Guam | N41557260 | CORROSION CONTROL HANGAR |  |  |  | 2018-10-05 | 2020-12-28 | 2022-10-06 | 87% | 2022-10-30
2023-02-15 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N41557635 | MUNICIPAL SOLID WASTE LANDFILL CLOSURE |  |  |  | 2017-08-15 | 2019-02-22 | 2022-01-09 | 100% | 2022-11-30
2023-02-15 | 2020 | Navy Active | Major Military Construction |  | Guam | N41557735A | MACHINE GUN RANGE (INC) |  |  |  | 2021-10-12 | 2024-10-25 | 2024-10-25 | 1% | 2024-10-25
2023-02-15 | 2017 | Navy Active | Major Military Construction | Guam | Guam | N41557H279 | REPLACE ANDERSEN HOUSING PH I |  |  |  | 2019-10-03 | 2022-07-05 | 2023-03-13 | 100% | 2023-03-13
2023-02-15 | 2018 | Navy Active | Major Military Construction | Guam | Guam | N41557H280 | REPLACE ANDERSEN HOUSING PH II |  |  |  | 2019-10-03 | 2022-07-05 | 2023-03-13 | 40% | 2023-05-31
2023-02-15 | 2019 | Navy Active | Major Military Construction | Guam | Guam | N41557H282 | REPLACE ANDERSEN HOUSING PH III |  |  |  | 2019-10-03 | 2022-07-05 | 2023-03-13 | 29% | 2023-05-31
2023-02-15 | 2015 | Navy Active | Major Military Construction | South Carolina | United States | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  |  |  | 2014-09-03 | 2018-06-20 | 2019-03-27 | 100% | 2020-05-13
2023-02-15 | 2017 | Navy Active | Unspecified Minor Military Construction | Georgia | United States | N42237671 | SUBMARINE BRIDGE TRAINER |  |  |  | 2018-01-30 | 2019-08-23 | 2019-11-22 | 100% | 2020-02-12
2023-02-15 | 2023 | Navy Active | Major Military Construction | Georgia | United States | N42237676 | TRIDENT TRAINING FACILITY COLUMBIA TRAINER EXP |  |  |  | 2023-01-13 | 2025-03-03 | 2025-03-03 | 1% | 2025-03-05
2023-02-15 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N47608265 | UCLASS RDT&E HANGAR |  |  |  | 2019-02-13 | 2020-09-28 | 2022-05-22 | 100% | 2022-11-30
2023-02-15 | 2017 | Navy Active | Unspecified Minor Military Construction | Maryland | United States | N47608421 | Inert Storage Building Replacement |  |  |  | 2017-10-11 | 2018-10-24 | 2020-06-16 | 100% | 2020-08-14
2023-02-15 | 2016 | Navy Active | Major Military Construction | Maryland | United States | N47608975 | UNACCOMPANIED HOUSING |  |  |  | 2018-04-27 | 2020-02-02 | 2020-07-23 | 100% | 2020-07-23
2023-02-15 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N47608975 | UNACCOMPANIED HOUSING | N47608975A |  |  | 2018-04-27 | 2020-02-02 | 2020-12-29 | 100% | 2020-12-29
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091900 | HANGAR 3 REPLACEMENT, APRON, TAXIWAY & UTILITIES FOR RDT&E |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091901 | INTEGRATION LABORATORY |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091902 | AIR OPERATIONS FACILITY & AIR TRAFFIC CONTROL TOWER |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091903 | MICHELSON MISSION SYSTEMS INTEGRATION LABORATORY |  |  |  | 2020-10-01 | 2022-11-04 | 2022-11-04 | 1% | 2022-11-04
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091904 | MICHELSON LABORATORY COMPLEX |  |  |  | 2021-07-09 | 2025-08-29 | 2025-10-14 | 1% | 2025-10-14
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091907 | AIRCRAFT PARKING APRON IN SUPPORT OF HANGAR 2 REPLACEMENT |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091908 | ADVANCED WARFARE HANGAR |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091911 | RANGE CONTROL COMPLEX |  |  |  | 2021-07-08 | 2024-01-22 | 2024-01-22 | 1% | 2024-01-22
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091914 | STRUCTUAL/AIRCRAFT FIRE AND RESCUE STATION |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091916 | COMMUNITY SUPPORT FACILITIES |  |  |  | 2020-09-17 | 2022-09-19 | 2023-01-13 | 1% | 2023-01-13
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091917 | CAST PROPELLANT MIX BUILDING |  |  |  | 2021-09-30 | 2024-02-20 | 2024-02-20 | 1% | 2024-02-20
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091918 | ORDANCE TEST SUPPORT AND TECHNICAL SERVICES LABORATORY |  |  |  | 2021-03-17 | 2023-05-03 | 2023-05-03 | 1% | 2023-05-03
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091919 | RADIOGRAPHIC BUILDING |  |  |  | 2021-06-03 | 2024-02-05 | 2024-02-05 | 1% | 2024-02-05
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091920 | WARHEAD CASING OPERATIONS |  |  |  | 2021-09-30 | 2024-02-20 | 2024-02-20 | 1% | 2024-02-20
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091921 | MOTOR ASSEMBLY COMPOUND |  |  |  | 2021-09-30 | 2024-02-20 | 2024-02-20 | 1% | 2024-02-20
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091922 | SKYTOP FIRING BAYS |  |  |  | 2021-06-24 | 2024-01-23 | 2024-01-23 | 1% | 2024-01-23
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N476091924 | ACADEMIC TRAINING BUILDING |  |  |  | 2021-02-05 | 2023-02-06 | 2023-02-06 | 1% | 2023-02-06
2023-02-15 | 2020 | Navy Active | Major Military Construction | California | United States | N47609810 | RUNWAY & TAXIWAY EXTENSION |  |  |  | 2020-07-10 | 2022-04-10 | 2022-08-20 | 100% | 2022-12-16
2023-02-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N50092176 | ACU-4 ELECTRICAL UPGRADES |  |  |  | 2018-05-03 | 2019-07-08 | 2019-08-05 | 100% | 2019-05-02
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N60042117 | MISSLE MOTOR MAGAZINES AND U&SI
2023-02-15 | 2020 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N601911026 | AIR INTELLIGENCE SUPPORT FACILITY |  |  |  | 2020-12-25 | 2022-06-10 | 2022-12-06 | 1% | 2023-12-31
2023-02-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N60191160 | ISR OPERATIONS FACILITY EXPAN |  |  |  | 2020-02-28 | 2022-03-01 | 2023-01-14 | 1% | 2022-11-18
2023-02-15 | 2014 | Navy Active | Major Military Construction | Virginia | United States | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  |  |  | 2014-09-30 | 2016-10-25 | 2021-02-12 | 100% | 2021-02-05
2023-02-15 | 2017 | Navy Active | Major Military Construction | Florida | United States | N60201154 | TRITON FORWARD OPERATING BASE HANGAR |  |  |  | 2017-07-13 | 2019-09-26 | 2019-12-27 | 100% | 2019-12-05
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60201195 | HEAVY WEATHER MOORINGS AT BRAVO WHARF |  |  |  | 2019-08-30 | 2020-08-29 | 2021-03-31 | 100% | 2020-07-27
2023-02-15 | 2018 | Navy Active | Major Military Construction | Florida | United States | N60201421 | MISSILE MAGAZINES |  |  |  | 2018-08-17 | 2020-08-04 | 2022-06-25 | 37% | 2022-07-25
2023-02-15 | 2016 | Navy Active | Major Military Construction | Florida | United States | N60201424 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2016-07-28 | 2018-02-05 | 2019-02-05 | 100% | 2019-08-06
2023-02-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60201426 | LCS SUPPORT FACILITY |  |  |  | 2019-09-27 | 2021-04-02 | 2022-06-27 | 100% | 2022-08-19
2023-02-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60201427 | LCS OPERATIONAL TRAINING FACILITY ADDITION |  |  |  | 2019-03-08 | 2021-02-05 | 2021-06-04 | 100% | 2021-04-09
2023-02-15 | 2016 | Navy Active | Major Military Construction | Nevada | United States | N60495111 | NAVOPSPTCEN FALLON |  |  |  | 2017-08-31 | 2019-03-11 | 2020-07-18 | 100% | 2021-02-12
2023-02-15 | 2014 | Navy Active | Major Military Construction | Nevada | United States | N60495393 | WASTEWATER TREATMENT PLANT |  |  |  | 2018-05-03 | 2020-05-08 | 2020-11-30 | 100% | 2020-08-31
2023-02-15 | 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495420 | AIR WING TRAINING FACILITY |  |  |  | 2015-09-30 | 2017-11-24 | 2019-10-31 | 100% | 2020-05-19
2023-02-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Nevada | United States | N60495426 | SECURITY FENCE TO ENCLAVE AIRFIELD |  |  |  | 2019-01-11 | 2019-10-25 | 2019-10-25 | 100% | 2020-05-06
2023-02-15 | 2017 | Navy Active | Major Military Construction | Nevada | United States | N60495440 | AIR WING SIMULATOR FACILITY |  |  |  | 2018-08-20 | 2020-08-25 | 2020-10-17 | 100% | 2020-12-01
2023-02-15 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60508253 | AIR TRAFFIC CONTROL TOWER (NORTH FIELD) |  |  |  | 2021-05-26 | 2024-05-11 | 2024-05-11 | 16% | 2024-05-11
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60508288 | AHTS TEMPORARY MAINTENANCE HANGAR FOUNDATION |  |  |  | 2020-01-24 | 2021-01-11 | 2023-03-30 | 37% | 2022-03-15
2023-02-15 | 2019 | Navy Active | Major Military Construction |  | Cuba | N60514160 | SOLID WASTE MANAGEMENT FACILITY |  |  |  | 2019-10-03 | 2022-03-18 | 2022-05-26 | 54% | 2023-02-17
2023-02-15 | 2019 | Navy Active | Major Military Construction |  | Cuba | N60514343 | CONSOLIDATED FIRE STATION |  |  |  | 2019-10-04 | 2021-09-20 | 2022-10-12 | 100% | 2022-12-12
2023-02-15 | 2014 | Navy Active | Major Military Construction |  | Japan | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  |  |  | 2014-10-03 | 2020-01-23 | 2020-02-23 | 100% | 2020-02-23
2023-02-15 | 2021 | Navy Active | Military Family Housing Improvement |  | Japan | N610542101 | WHOLE HOUSE REVITALIZATION, IKEGO TOWNHOUSE PH2 |  |  |  | 2021-03-19 | 2024-05-01 | 2024-05-01 | 1% | 2024-05-01
2023-02-15 | 2022 | Navy Active | Military Family Housing Improvement |  | Japan | N610542202 | WHOLE HOUSE REVITALIZATION, IKEGO TOWNHOUSE, PH3
2023-02-15 | 2019 | Navy Active | Major Military Construction |  | Japan | N61056512 | TACTICAL OPERATIONS CENTER |  |  |  | 2019-05-03 | 2020-12-31 | 2020-12-31 | 1% | 2021-01-29
2023-02-15 | 2017 | Navy Active | Major Military Construction | Hawaii | United States | N61064402 | UPGRADE POWER PLANT & ELECTRICAL DIST SYS |  |  |  | 2019-01-09 | 2021-07-13 | 2021-12-27 | 100% | 2021-12-22
2023-02-15 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | N61064416 | PMRF POWER GRID CONSOLIDATION |  |  |  | 2018-09-20 | 2020-05-28 | 2022-06-17 | 100% | 2022-04-05
2023-02-15 | 2014 | Navy Active | Major Military Construction | California | United States | N61065202 | NOSC MORENO VALLEY RESERVE TRAINING CENTER |  |  |  | 2016-09-12 | 2018-06-10 | 2019-12-11 | 100% | 2019-12-11
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N61065224 | CAUSEWAY, BOAT CHANNEL & TURNING BASIN |  |  |  | 2019-07-29 | 2022-10-27 | 2024-06-18 | 55% | 2024-03-18
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N61065241 | MISSILE MAGAZINES |  |  |  | 2019-09-02 | 2021-04-15 | 2021-04-26 | 100% | 2021-08-30
2023-02-15 | 2021 | Navy Active | Major Military Construction | California | United States | N61065243 | MISSILE MAGAZINES |  |  |  | 2021-08-26 | 2023-08-27 | 2023-08-27 | 1% | 2023-08-27
2023-02-15 | 2022 | Navy Active | Major Military Construction | California | United States | N61065243A | MISSILE MAGAZINES (INC)
2023-02-15 | 2018 | Navy Active | Major Military Construction | Washington | United States | N61066604 | MISSILE MAGAZINES
2023-02-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N61151163 | AGILE CHEMICAL FACILITY PHASE 3/GAP B |  |  |  | 2018-10-13 | 2021-08-14 | 2021-08-14 | 100% | 2021-08-09
2023-02-15 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX, PHASE 2 |  |  |  | 2017-05-11 | 2019-09-06 | 2023-04-09 | 36% | 2023-10-31
2023-02-15 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX PH 2 | N61151190A |  |  | 2017-05-11 | 2019-09-06 | 2023-04-09 | 9% | 2023-10-31
2023-02-15 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151287 | MISSILE SUPPORT FACILITY |  |  |  | 2015-09-16 | 2017-07-17 | 2019-10-31 | 100% | 2019-10-26
2023-02-15 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61152621 | CYBER SECURITY STUDIES BUILDING |  |  |  | 2016-04-14 | 2019-09-08 | 2020-05-22 | 100% | 2020-09-04
2023-02-15 | 2020 | Navy Active | Major Military Construction | Guam | Guam | N61755491 | EOD COMPOUND FACILITIES |  |  |  | 2020-08-21 | 2022-12-20 | 2022-12-20 | 1% | 2023-03-03
2023-02-15 | 2022 | Navy Active | Major Military Construction |  | Guam | N61755519 | X-RAY WHARF BERTH 2 |  |  |  | 2022-05-27 | 2024-09-10 | 2024-09-10 | 1% | 2024-09-10
2023-02-15 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N61755535 | SANITARY SEWER SYSTEM RECAPITALIZATION |  |  |  | 2017-09-04 | 2020-01-03 | 2020-09-10 | 100% | 2022-07-29
2023-02-15 | 2019 | Navy Active | Major Military Construction | Guam | Guam | N61755640 | UNACCOMPANIED ENLISTED HOUSING |  |  |  | 2019-07-09 | 2022-10-07 | 2022-11-04 | 53% | 2023-09-30
2023-02-15 | 2017 | Navy Active | Major Military Construction | Guam | Guam | N61755652 | HARDENING OF GUAM POL INFRASTRUCTURE |  |  |  | 2018-06-06 | 2020-04-03 | 2021-08-15 | 90% | 2022-07-21
2023-02-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Guam | Guam | N61755680 | HARDEN ELECTRICAL CIRCUIT |  |  |  | 2018-10-12 | 2019-09-27 | 2021-05-26 | 100% | 2021-01-07
2023-02-15 | 2018 | Navy Active | Major Military Construction |  | Guam | N61766661 | NAVY-COMMERCIAL TIE-IN HARDENING |  |  |  | 2022-05-05 | 2024-07-10 | 2024-07-10 | 1% | 2024-08-02
2023-02-15 | 2017 | Navy Active | Major Military Construction |  | Italy | N62588307 | ERI: P-8A HANGAR UPGRADE |  |  |  | 2019-01-03 | 2021-02-09 | 2022-02-18 | 89% | 2021-11-16
2023-02-15 | 2017 | Navy Active | Major Military Construction |  | Italy | N62588308 | ERI: P-8A AIRCRAFT RINSE RACK |  |  |  | 2019-01-03 | 2021-02-09 | 2022-02-18 | 97% | 2021-11-16
2023-02-15 | 2019 | Navy Active | Major Military Construction |  | Italy | N62588312 | EDI: P-8 BASE IMPROVEMENTS
2023-02-15 | 2019 | Navy Active | Major Military Construction | Mississippi | United States | N62604855 | EXPEDITIONARY COMBAT SKILLS STUDENT BERTHING |  |  |  | 2019-05-29 | 2022-06-30 | 2022-06-30 | 79% | 2022-06-29
2023-02-15 | 2022 | Navy Active | Major Military Construction | Virginia | United States | N62688095 | SUBMARINE PIER 3 INC. |  |  |  | 2022-05-07 | 2027-02-27 | 2027-02-27 | 1% | 2027-02-27
2023-02-15 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N626881035 | MH60 CORROSION CONTROL AND PAINT FACILITY |  |  |  | 2021-09-03 | 2024-03-22 | 2024-03-22 | 1% | 2024-09-01
2023-02-15 | 2021 | Navy Active | Major Military Construction | Virginia | United States | N626881035A | MH60 & CMV-22B CORROSION CNTRL & PAINT FAC |  |  |  | 2021-09-03 | 2024-03-22 | 2024-03-22 | 1% | 2024-09-01
2023-02-15 | 2021 | Navy Active | Major Military Construction | Virginia | United States | N62688404 | E-2D TRAINING FACILITY |  |  |  | 2021-09-23 | 2019-11-30 | 2023-08-20 | 1% | 2025-07-01
2023-02-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N62688495 | CHAMBERS FIELD MAGAZINE RECAP PH 1 |  |  |  | 2018-10-12 | 2021-02-04 | 2023-05-26 | 93% | 2023-05-26
2023-02-15 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688610 | ELECTRICAL REPAIRS TO PIERS 2,6,7, AND 11 |  |  |  | 2017-09-14 | 2019-10-25 | 2020-12-30 | 100% | 2020-12-22
2023-02-15 | 2017 | Navy Active | Major Military Construction | Virginia | United States | N62688610 | ELECTRICAL REPAIRS TO PIERS 2,6,7, AND 11 | N62688610A |  |  | 2017-09-14 | 2019-10-25 | 2020-12-30 | 100% | 2020-12-22
2023-02-15 | 2018 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N62688762 | SUBMARINE UMM ANTENNA MAINTENANCE TOWER |  |  |  | 2018-05-16 | 2019-07-17 | 2021-01-03 | 100% | 2021-01-26
2023-02-15 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688913 | COMMUNICATIONS CENTER |  |  |  | 2018-05-07 | 2020-11-01 | 2022-03-16 | 100% | 2023-03-31
2023-02-15 | 2018 | Navy Active | Major Military Construction | Hawaii | United States | N62813013 | COMMUNICATIONS/CRYPTO FAC (WAHIAWA) |  |  |  | 2019-08-09 | 2021-04-26 | 2024-04-24 | 98% | 2024-04-24
2023-02-15 | 2020 | Navy Active | Major Military Construction | Hawaii | United States | N62813033 | MAGAZINE CONSOLIDATION, PHASE 1 |  |  |  | 2020-08-24 | 2022-09-09 | 2022-09-09 | 1% | 2023-07-05
2023-02-15 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | N62813036 | WELDING SCHOOL SHOP CONSOLIDATION |  |  |  | 2016-02-09 | 2018-03-26 | 2021-07-06 | 99% | 2021-06-25
2023-02-15 | 2021 | Navy Active | Major Military Construction | Hawaii | United States | N62813044 | WATERFRONT IMPROVEMENTS WHARVES S8-S10 |  |  |  | 2021-05-14 | 2023-11-12 | 2023-11-12 | 1% | 2023-11-12
2023-02-15 | 2014 | Navy Active | Unspecified Minor Military Construction | Hawaii | United States | N62813058 | ROCKFALL PROTECTION AT RED HILL |  |  |  | 2014-12-08 | 2016-05-18 | 2019-12-31 | 100% | 2019-11-06
2023-02-15 | 2021 | Navy Active | Major Military Construction | Hawaii | United States | N628131006 | WATERFRONT WHARVES S1, S11-13, S20-21 |  |  |  | 2021-05-14 | 2023-11-12 | 2023-11-12 | 1% | 2023-11-12
2023-02-15 | 2019 | Navy Active | Major Military Construction | Hawaii | United States | N62813169 | WATER TRANSMISSION LINE |  |  |  | 2019-04-12 | 2022-01-24 | 2022-08-03 | 73% | 2023-08-31
2023-02-15 | 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  |  |  | 2014-07-14 | 2017-08-03 | 2020-10-06 | 100% | 2020-09-01
2023-02-15 | 2018 | Navy Active | Major Military Construction | Hawaii | United States | N62813704 | SEWER LIFT STATION & RELIEF SEWER LINE |  |  |  | 2019-03-26 | 2021-06-19 | 2021-07-21 | 100% | 2021-07-21
2023-02-15 | 2020 | Navy Active | Major Military Construction |  | Italy | N628632001 | W/H REVITALIZATION - LAS PALMERAS PH V |  |  |  | 2021-10-11 | 2023-04-05 | 2023-10-04 | 1% | 2023-10-04
2023-02-15 | 2021 | Navy Active | Major Military Construction |  | Italy | N62863313 | MH-60R SQUADRON SUPPORT FACILITIES |  |  |  | 2021-12-30 | 2024-09-09 | 2024-09-09 | 1% | 2024-09-09
2023-02-15 | 2020 | Navy Active | Major Military Construction |  | Spain | N62863605 | SEAMANSHIP TRAINING FACILITY |  |  |  | 2021-04-06 | 2023-01-17 | 2023-01-17 | 89% | 2023-04-11
2023-02-15 | 2021 | Navy Active | Major Military Construction |  | Italy | N62863620 | EDI: EXPEDITIONARY MAINTENANCE FACILITY |  |  |  | 2022-01-04 | 2024-07-01 | 2025-01-06 | 1% | 2025-01-06
2023-02-15 | 2017 | Navy Active | Major Military Construction |  | Spain | N62863621 | COMMUNICATION STATION |  |  |  | 2017-09-14 | 2023-02-13 | 2023-01-08 | 100% | 2021-11-01
2023-02-15 | 2015 | Navy Active | Major Military Construction |  | Spain | N62863712 | SHIP BERTHING POWER UPGRADES |  |  |  | 2015-12-04 | 2018-05-23 | 2022-12-27 | 96% | 2024-01-20
2023-02-15 | 2020 | Navy Active | Major Military Construction |  | Spain | N62863716 | EDI: IN-TRANSIT MUNITIONS FACILITY
2023-02-15 | 2020 | Navy Active | Major Military Construction |  | Italy | N62863785 | EDI: SMALL CRAFT BERTHING FACILITY |  |  |  | 2022-01-04 | 2023-12-31 | 2023-12-31 | 1% | 2023-12-31
2023-02-15 | 2021 | Navy Active | Major Military Construction |  | Spain | N62863810 | EDI: EOD BOAT SHOP |  |  |  | 2023-01-20 | 2024-10-25 | 2024-10-25 | 1% | 2024-11-04
2023-02-15 | 2019 | Navy Active | Major Military Construction |  | Italy | N62863811 | EDI: PORT OPERATION FACILITIES |  |  |  | 2021-09-13 | 2024-04-16 | 2024-04-16 | 24% | 2024-06-18
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction |  | Spain | N62863812 | PROVIDE SHIP TO SHORE ELECTRICAL SUBSTATIONS AT PIER #1 |  |  |  | 2020-10-07 | 2022-06-30 | 2022-06-30 | 1% | 2022-06-30
2023-02-15 | 2020 | Navy Active | Major Military Construction |  | Italy | N62995130 | COMMUNICATIONS STATION |  |  |  | 2020-10-13 | 2025-06-05 | 2026-12-24 | 1% | 2026-12-24
2023-02-15 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995407 | TRITON HANGAR AND OPERATION FACILITY |  | 4099000 | N32414547 | 2016-12-06 | 2018-06-28 | 2021-12-14 | 75% | 2023-03-31
2023-02-15 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995655 | P-8A HANGAR AND FLEET SUPPORT FACILITY |  |  |  | 2016-12-06 | 2019-04-23 | 2021-12-14 | 64% | 2023-03-31
2023-02-15 | 2017 | Navy Active | Major Military Construction |  | Italy | N62995737 | UPGRADE ENTRY CONTROL POINT |  |  |  | 2017-03-14 | 2018-08-22 | 2021-01-21 | 100% | 2021-12-22
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction |  | Bahrain | N63005955U | P8A CLEAR WATER RINSE FACILITY
2023-02-15 | 2021 | Navy Active | Major Military Construction |  | Bahrain | N63005964 | SHIP TO SHORE UTILITY SERVICES
2023-02-15 | 2020 | Navy Active | Major Military Construction |  | Bahrain | N63005974 | ELECTRICAL SYSTEM UPGRADE
2023-02-15 | 2016 | Navy Active | Major Military Construction |  | Bahrain | N63005976 | MINA SALMAN PIER REPLACEMENT
2023-02-15 | 2017 | Navy Active | Unspecified Minor Military Construction |  | Bahrain | N63005985 | FIRE WATER TANK |  |  |  | 2019-06-28 | 2021-03-25 | 2021-03-25 | 100% | 2022-07-31
2023-02-15 | 2016 | Navy Active | Major Military Construction | California | United States | N63042218 | RTO AND MISSION DEBRIEF FACILITY |  |  |  | 2016-05-24 | 2019-11-03 | 2020-09-17 | 100% | 2020-07-10
2023-02-15 | 2018 | Navy Active | Major Military Construction | California | United States | N63042282 | F/A 18 AVIONICS REPAIR FACILITY REPLACEMENT |  |  |  | 2018-10-03 | 2021-02-24 | 2022-02-25 | 100% | 2021-06-09
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N63042284 | F-35 MAINTENANCE HANGAR |  |  |  | 2019-09-30 | 2021-11-17 | 2022-08-12 | 100% | 2022-08-12
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N63042392 | COMMUNICATIONS LINE OPS TO ADMIN |  |  |  | 2019-08-13 | 2021-05-06 | 2021-05-06 | 100% | 2020-12-28
2023-02-15 | 2022 | Navy Active | Major Military Construction | California | United States | N63402391A | F-35C HANGAR 6 PHASE 2 (MOD 3/4)(INC)
2023-02-15 | 2021 | Navy Active | Major Military Construction |  | Greece | N66691131 | COMMUNICATIONS CENTER |  |  |  | 2022-02-18 | 2024-07-22 | 2024-10-20 | 1% | 2024-09-23
2023-02-15 | 2019 | Navy Active | Major Military Construction |  | Greece | N66691144 | EDI: MARATHI LOGISTICS SUPPORT CENTER
2023-02-15 | 2018 | Navy Active | Major Military Construction |  | Greece | N66691911 | STRATEGIC AIRCRAFT PARKING APRON EXPANSION |  |  |  | 2018-12-26 | 2021-02-14 | 2021-10-04 | 100% | 2021-12-16
2023-02-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436400 | SUBMARINE REFIT MAINT SUPPORT FACILITY |  |  |  | 2018-10-13 | 2021-06-30 | 2022-03-19 | 83% | 2023-10-28
2023-02-15 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436401 | REGIONAL SHIP MAINTENANCE SUPPORT FACILITY |  |  |  | 2017-10-10 | 2020-01-04 | 2021-07-06 | 100% | 2021-07-20
2023-02-15 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436431 | DRY DOCK 6 MODERNIZATION & UTILITY IMPROVE. |  |  |  | 2016-08-25 | 2017-11-14 | 2021-08-06 | 100% | 2022-05-19
2023-02-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436438 | NUCLEAR REPAIR FACILITY |  |  |  | 2018-05-07 | 2019-10-30 | 2020-08-14 | 100% | 2020-05-27
2023-02-15 | 2020 | Navy Active | Major Military Construction | Washington | United States | N68436447 | DRY DOCK 4 & PIER 3 MODERNIZATION |  |  |  | 2020-06-22 | 2023-08-02 | 2023-08-02 | 1% | 2023-08-02
2023-02-15 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436834 | SEAWOLF CLASS SERVICE PIER |  |  |  | 2020-02-17 | 2022-07-04 | 2022-08-24 | 100% | 2022-11-07
2023-02-15 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436983 | WRA LAND/WATER INTERFACE |  |  |  | 2016-10-05 | 2018-02-13 | 2019-04-21 | 100% | 2020-03-24
2023-02-15 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 - INC 4 | N68436990C | 2728000 | M67399222; N68436993 | 2015-01-22 | 2016-01-09 | 2017-09-30 | 100% | 2016-12-23
2023-02-15 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436993 | TPS PORT ANGELES FORWARD OPERATING LOCATION |  |  |  | 2016-09-13 | 2018-02-06 | 2019-08-07 | 100% | 2018-09-03
2023-02-15 | 2019 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469001 | MASTER TIME CLOCKS & OPERATIONS FACILITY - INC 1 |  |  |  | 2019-09-30 | 2024-09-15 | 2024-09-15 | 70% | 2025-10-10
2023-02-15 | 2015 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY |  |  |  | 2017-11-16 | 2021-06-16 | 2023-03-03 | 39% | 2023-04-07
2023-02-15 | 2018 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY | N68469275A |  |  | 2017-11-16 | 2021-06-16 | 2023-03-03 | 98% | 2023-04-07
2023-02-15 | 2017 | Navy Active | Unspecified Minor Military Construction | District Of Columbia | United States | N68469760 | DIRECT AIRCRAFT REFUELING SYSTEM
2023-02-15 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N69212169 | NMC ORDNANCE FACILITIES RECAP |  |  |  | 2021-04-08 | 2023-06-25 | 2024-07-17 | 1% | 2024-07-17
2023-02-15 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N69212995 | BACHELOR ENLISTED QUARTERS |  |  |  | 2019-02-14 | 2021-06-25 | 2021-12-08 | 71% | 2023-02-24
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N69232586 | MISSILE ASSEMBLY BUILDING AND HIGH EXPLOSIVE MAG |  |  |  | 2019-10-10 | 2021-02-15 | 2022-10-31 | 98% | 2022-08-11
2023-02-15 | 2019 | Navy Active | Major Military Construction | California | United States | N69232777 | DIRECTED ENERGY SYSTEMS INTEGRATION LAB |  |  |  | 2019-09-11 | 2021-01-11 | 2021-11-24 | 92% | 2022-10-17
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Texas | United States | N83447084 | CDC STORM SHELTER |  |  |  | 2019-10-01 | 2020-09-20 | 2021-02-25 | 100% | 2021-02-25
2023-02-15 | 2017 | Navy Reserve | Major Military Construction | Louisiana | United States | M68479777 | MARINE CORPS RESERVE CENTER |  |  |  | 2020-02-19 | 2021-08-30 | 2024-09-27 | 46% | 2024-09-27
2023-02-15 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Connecticut | United States | N00129664 | CORIVRON 8 RESERVE HVU DET SUPPORT FACILITIES |  |  |  | 2015-09-08 | 2016-09-08 | 2017-04-21 | 100% | 2017-07-14
2023-02-15 | 2020 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206475 | ENTRY CONTROL FACILITY UPGRADES |  |  |  | 2020-08-27 | 2023-03-06 | 2023-06-06 | 83% | 2023-06-06
2023-02-15 | 2019 | Navy Reserve | Unspecified Minor Military Construction | Louisiana | United States | N00206493 | FLIGHT LINE ACCESS CONTROL AND SECURITY |  |  |  | 2020-01-23 | 2021-01-08 | 2022-01-04 | 85% | 2022-01-06
2023-02-15 | 2017 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206500 | JOINT RESERVE INTELLIGENCE CENTER |  |  |  | 2017-07-13 | 2019-07-27 | 2020-10-01 | 100% | 2020-08-21
2023-02-15 | 2018 | Navy Reserve | Major Military Construction | Georgia | United States | N42237642 | NAVY OPERATIONAL SUPPORT CENTER FORT GORDON |  |  |  | 2018-09-26 | 2020-01-06 | 2021-10-16 | 100% | 2021-10-16
2023-02-15 | 2019 | Navy Reserve | Major Military Construction | Georgia | United States | N42237643 | RESERVE TRAINING CENTER |  |  |  | 2019-08-23 | 2021-10-03 | 2022-05-04 | 38% | 2022-05-04
2023-02-15 | 2019 | Navy Reserve | Major Military Construction | California | United States | N61065160 | RESERVE TRAINING CENTER |  |  |  | 2019-02-07 | 2021-02-07 | 2021-06-01 | 100% | 2021-05-26
2023-02-15 | 2018 | Navy Reserve | Major Military Construction | California | United States | N63042366 | NAVAL OPERATIONAL SUPPORT CENTER LEMOORE |  |  |  | 2019-04-25 | 2021-03-26 | 2022-03-02 | 100% | 2021-02-24
2023-02-15 | 2018 | Navy Reserve | Major Military Construction | Texas | United States | N83447077 | K-C130J EACTS FACILITY |  |  |  | 2018-10-10 | 2019-12-31 | 2020-12-31 | 100% | 2021-03-02
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | New Mexico | United States | 063054x | CAFB SOF C-130 PARK APR RCP PH I |  |  |  | 2010-05-11 | 2012-02-26 | 2013-03-15 | 100% | 2013-03-15
2022-12-14 | 2008 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 0P-926 | *OTH P-926 SOF Operations Fac |  |  |  | 2010-04-14 | 2011-12-13 | 2014-03-02 | 100% | 2014-03-02
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | 1362 | SOF HUMAN PERFORMANCE TRAINING CENTER |  |  |  | 2020-08-05 | 2022-02-07 | 2023-11-18 | 14% | 2022-02-07
2022-12-20 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 1391 | SOF SUSTAINMENT TRAINING COMPLEX |  |  |  | 2014-09-11 | 2016-09-02 | 2019-01-31 | 100% | 2018-06-06
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | North Carolina | United States | 26542 | SOF 26542 Expand Trng Cmpnd |  |  |  | 2009-10-15 | 2011-07-02 | 2012-09-24 | 100% | 2012-03-13
2022-12-14 | 2008 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 33003 | *SOF Vehicle Maintenance Facility |  |  |  | 2012-01-31 | 2013-04-25 | 2015-03-05 | 100% | 2015-03-05
2022-12-14 | 2008 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 33005 | *SOF Storage Facility |  |  |  | 2012-01-31 | 2013-04-25 | 2015-01-21 | 100% | 2015-01-21
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | Florida | United States | 33017 | OTH 033017 SOF SPECIAL TACTICS |  |  |  | 2009-04-06 | 2010-09-28 | 2011-06-08 | 100% | 2011-06-08
2022-12-14 | 2008 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 33019 | *SOF Air Operations Center Facility |  |  |  | 2012-01-31 | 2013-04-25 | 2015-01-21 | 100% | 2015-01-21
2022-12-14 | 2015 | Special Operations Command | Major Military Construction | Kentucky | United States | 36977 | OTH 036977 SOF System Integration Maintenance Facility |  |  |  | 2015-09-10 | 2017-03-03 | 2017-10-17 | 100% | 2017-10-17
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | New Mexico | United States | 43010 | CAFB SOF MAINT HANGAR/AMU 2009 |  |  |  | 2009-11-10 | 2011-05-09 | 2012-02-02 | 100% | 2012-02-06
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 43055 | CLOSED POPE 43055 SOF Training Facilit |  |  |  | 2012-05-31 | 2013-11-22 | 2014-11-12 | 100% | 2014-11-12
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | Colorado | United States | 47942 | CAP 047942 SOF Lang Sustnmt Trng Fac |  |  |  | 2016-12-06 | 2018-05-30 | 2018-10-10 | 100% | 2018-10-10
2022-12-14 | 2008 | Special Operations Command | Major Military Construction | Kentucky | United States | 53530 | OTH 053530 SOF Battalion & Com |  |  |  | 2008-04-08 | 2009-12-09 | 2010-01-29 | 100% | 2010-01-29
2022-12-14 | 2013 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 53542 | CAP 053542 SPC OPS PARACHUTE |  |  |  | 2014-11-14 | 2016-02-07 | 2016-02-20 | 100% | 2016-06-23
2022-12-14 | 2008 | Special Operations Command | Major Military Construction | Florida | United States | 53712A | OTH 53712A SOF 501-D BLDG ADD |  |  |  | 2009-01-21 | 2013-05-02 | 2013-08-31 | 100% | 2013-08-31
2022-12-14 | 2015 | Special Operations Command | Major Military Construction | Georgia | United States | 57442 | CLOSED STEW 057442 SOF Company Ops Facility |  |  |  | 2017-04-27 | 2018-10-19 | 2019-02-07 | 100% | 2019-04-16
2022-12-14 | 2009 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 59990 | *OTH 059990 SOF TRAINING RANGE |  |  |  | 2009-11-02 | 2011-01-26 | 2012-08-15 | 100% | 2010-11-09
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 60272 | CLOSED - SOF Commo Trng Complex 60272 |  |  |  | 2012-09-12 | 2014-03-06 | 2015-02-18 | 100% | 2015-05-29
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | North Carolina | United States | 60636 | Closed SOF 60636 Security/ Force Prot |  |  |  | 2009-10-15 | 2010-06-12 | 2010-11-15 | 100% | 2010-07-01
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | North Carolina | United States | 60743 | SOF 60743 BN HQs 112th Sig Fac |  |  |  | 2009-09-30 | 2011-03-24 | 2012-03-05 | 100% | 2012-05-04
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | North Carolina | United States | 60815 | SOF 60815 Training Facility |  |  |  | 2009-06-02 | 2010-11-24 | 2011-04-12 | 100% | 2011-04-12
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 60821 | CLOSED - SOF Squadron HQ Addition 60821 |  |  |  | 2012-06-06 | 2014-06-06 | 2015-03-06 | 100% | 2015-03-16
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 60833 | SOF 060833 Prep Cond Cmplx |  |  |  | 2010-11-30 | 2012-08-31 | 2012-12-20 | 100% | 2012-12-20
2022-12-14 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 61064 | CLOSED - SOF Upgrade Training Facility - 61064 |  |  |  | 2014-11-17 | 2016-11-27 | 2017-05-23 | 100% | 2017-06-23
2022-12-14 | 2017 | Special Operations Command | Major Military Construction | Georgia | United States | 61065 | CLOSED BE 061065 SOF TUAV Maintenance Facility |  |  |  | 2017-10-02 | 2018-12-01 | 2019-07-18 | 100% | 2019-08-05
2022-12-14 | 2008 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 61772 | *SOF Operations Complex |  |  |  | 2012-01-31 | 2013-04-25 | 2015-01-21 | 100% | 2015-01-21
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 61874 | Closed SOF 061874 BN & CO HQs |  |  |  | 2010-11-02 | 2012-03-16 | 2013-06-04 | 100% | 2013-10-14
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | New Mexico | United States | 63019 | CAFB C-130 FUEL CELL & CORR CONT |  |  |  | 2010-05-11 | 2012-12-24 | 2013-03-15 | 100% | 2013-03-15
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | New Mexico | United States | 63027 | CAFB - SOF CV-22 SIM FAC FY11 |  |  |  | 2009-04-28 | 2010-09-10 | 2011-06-02 | 100% | 2011-06-02
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | New Mexico | United States | 63035 | CAFB CV-22 AMU ADD HANGAR 208 |  |  |  | 2010-12-16 | 2012-08-07 | 2013-09-10 | 100% | 2013-09-10
2022-12-14 | 2011 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 63049 | CAFB SOF HANGAR AMU 63049 |  |  |  | 2011-10-13 | 2013-12-01 | 2014-04-11 | 100% | 2014-05-02
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | New Mexico | United States | 63051 | CAFB-SOF AIRCRAFT PARKING APRON |  |  |  | 2011-10-05 | 2012-10-04 | 2012-10-10 | 100% | 2012-10-10
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | New Mexico | United States | 63052 | CAFB-SOF OPS & TRNG COMPLX |  |  |  | 2012-01-10 | 2014-03-12 | 2014-06-04 | 100% | 2014-06-04
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | Florida | United States | 63711 | OTH 063711 SOF ADD/ALTER 501B |  |  |  | 2011-06-01 | 2012-10-13 | 2013-10-10 | 100% | 2013-08-29
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | Colorado | United States | 63831 | SOF 063831 BN Facililty |  |  |  | 2010-08-26 | 2012-05-01 | 2012-08-03 | 100% | 2012-08-03
2022-12-14 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | 63850 | SOF Support Battalion Admin Facility - 63850 |  |  |  | 2018-10-02 | 2020-06-24 | 2021-05-11 | 100% | 2021-05-11
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | North Carolina | United States | 64484 | CLOSED - SOF Operations Additions 64484 |  |  |  | 2011-08-25 | 2014-06-10 | 2015-04-16 | 100% | 2015-04-17
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 64669 | SOF 64669 Ops Spprt Addn Blg N |  |  |  | 2010-10-22 | 2012-04-14 | 2013-03-01 | 100% | 2013-03-01
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 65052 | CLOSED - SOF Support Addition 65052 |  |  |  | 2013-12-03 | 2014-12-03 | 2014-12-18 | 100% | 2014-12-18
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 65266 | SOF 65266 Milit Work Dog Fac |  |  |  | 2010-07-22 | 2011-07-22 | 2011-09-29 | 100% | 2011-10-04
2022-12-14 | 2008 | Special Operations Command | Major Military Construction | Georgia | United States | 65272 | SOF 65272 Support Company Fac |  |  |  | 2008-04-23 | 2011-11-27 | 2012-02-10 | 100% | 2012-02-10
2022-12-14 | 2008 | Special Operations Command | Major Military Construction | Kentucky | United States | 65392 | OTH 065392 SOF Group Support B |  |  |  | 2008-04-18 | 2009-08-11 | 2010-03-11 | 100% | 2010-03-11
2022-12-14 | 2008 | Special Operations Command | Major Military Construction | Georgia | United States | 65394 | Closed SOF 65394 Battalion HQ Complex |  |  |  | 2008-04-18 | 2010-04-21 | 2010-07-31 | 100% | 2010-06-18
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | Georgia | United States | 65395 | SOF 65395 SOF Company Support |  |  |  | 2011-12-27 | 2013-06-19 | 2014-05-30 | 100% | 2014-05-30
2022-12-14 | 2008 | Special Operations Command | Major Military Construction | Georgia | United States | 65396 | Closed SOF 65396 Regimental HQ Addtn |  |  |  | 2008-03-11 | 2009-04-05 | 2009-06-16 | 100% | 2009-06-16
2022-12-14 | 2008 | Special Operations Command | Major Military Construction | North Carolina | United States | 65397 | Closed SOF 65397 Tactical Equip Shop |  |  |  | 2008-04-18 | 2010-04-21 | 2010-07-31 | 100% | 2010-06-18
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | Kentucky | United States | 65678 | OTH 065678 TAC Equip Shop Band |  |  |  | 2009-04-16 | 2010-08-09 | 2010-08-21 | 100% | 2010-08-21
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 66227 | SOF 066227 BN HQ Facility |  |  |  | 2010-11-09 | 2012-05-02 | 2013-06-07 | 100% | 2013-04-08
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 66315 | SOF 66315 Operations Addition North |  |  |  | 2010-08-25 | 2013-02-11 | 2014-07-22 | 100% | 2014-07-22
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | North Carolina | United States | 66362 | CLOSED - SOF C4 Facility 66362 |  |  |  | 2012-06-14 | 2014-01-31 | 2014-12-30 | 100% | 2015-01-05
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | North Carolina | United States | 66443 | CLOSED - SOF Operations Sppt Fac 66443 |  |  |  | 2011-07-19 | 2013-01-09 | 2013-05-31 | 100% | 2013-07-01
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | North Carolina | United States | 66444 | CLOSED - SOF Operational Com Fac 66444 |  |  |  | 2011-09-14 | 2013-01-16 | 2013-05-31 | 100% | 2013-07-16
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | Kentucky | United States | 66597 | OTH 066597 Hangar Addition, 160th SOAR |  |  |  | 2014-04-29 | 2015-10-21 | 2016-04-15 | 100% | 2016-04-28
2022-12-14 | 2019 | Special Operations Command | Major Military Construction | Kentucky | United States | 66813 | FTC SOF Logistics Support Operations Facility |  |  |  | 2019-06-12 | 2020-12-03 | 2021-06-17 | 100% | 2021-07-08
2022-12-14 | 2019 | Special Operations Command | Major Military Construction | Kentucky | United States | 67039 | OTH 067039 MOUT/Aerial Gunnery Range |  |  |  | 2019-06-12 | 2020-12-03 | 2021-02-16 | 100% | 2021-02-16
2022-12-14 | 2009 | Special Operations Command | Major Military Construction | Florida | United States | 67428 | PN:67428 SOF Cmplx Ph 4 |  |  |  | 2009-02-12 | 2011-07-29 | 2011-07-29 | 100% | 2011-07-29
2022-12-14 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 68526 | CLOSED - SOF Engineer Training Facility - 68526 |  |  |  | 2015-05-27 | 2016-11-17 | 2017-04-20 | 100% | 2017-04-17
2022-12-14 | 2019 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 69251 | SOF Replace Maze and Tower - 69251 |  |  |  | 2019-05-21 | 2020-05-20 | 2020-10-28 | 100% | 2020-10-28
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | Georgia | United States | 69261 | SOF 69261 Mil Wk Dog Ken Cplx |  |  |  | 2012-01-09 | 2014-08-06 | 2014-08-27 | 100% | 2014-08-27
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 69275 | Closed SOF 069275 TUAV Hanger |  |  |  | 2010-06-22 | 2011-12-14 | 2012-02-13 | 100% | 2012-03-07
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69277 | CLOSED - SOF Entry Control Point 69277 |  |  |  | 2012-08-22 | 2013-08-22 | 2013-12-18 | 100% | 2014-01-01
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | Colorado | United States | 69278 | SOF TUAV Hanger |  |  |  | 2012-05-16 | 2013-08-09 | 2014-01-27 | 100% | 2014-01-27
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69287 | SOF Battalion Operations Facility - 69287 |  |  |  | 2013-11-05 | 2016-12-02 | 2018-03-15 | 100% | 2018-05-01
2022-12-14 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 69302 | SOF Battalion Operations Facility - 69302 |  |  |  | 2017-05-17 | 2019-05-07 | 2020-12-11 | 100% | 2020-12-11
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 69366 | SOF 069366 Expand BN HQS |  |  |  | 2010-09-21 | 2011-09-21 | 2012-04-12 | 100% | 2012-04-12
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69382 | CLOSED - SOF Civil Affairs Battalion Complex - 69382 |  |  |  | 2013-11-19 | 2015-05-13 | 2015-09-21 | 100% | 2015-11-04
2022-12-14 | 2014 | Special Operations Command | Major Military Construction | Colorado | United States | 69446 | PN 69446 SOF Group Support Battalion Expansion |  |  |  | 2014-08-27 | 2016-03-31 | 2016-06-08 | 100% | 2016-06-17
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | Kentucky | United States | 69447 | OTH 069447 SOF Admin Annex |  |  |  | 2014-04-14 | 2016-02-13 | 2016-02-15 | 100% | 2016-03-04
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | Florida | United States | 69449 | OTH 69449, 7th SFG Spt Det |  |  |  | 2011-06-29 | 2012-09-26 | 2012-12-18 | 100% | 2013-01-28
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69458 | CLOSED - SOF Bn Ops Complex 4 MIS/O 69458 |  |  |  | 2012-12-10 | 2014-06-03 | 2016-03-04 | 100% | 2016-03-24
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69493 | CLOSED - SOF Sustainment Brigade 69493 |  |  |  | 2014-06-18 | 2016-05-17 | 2016-12-16 | 100% | 2016-12-16
2022-12-14 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 69552 | SOF Tactical Equipment Maint Facility - 69552 |  |  |  | 2019-03-19 | 2020-11-08 | 2022-04-12 | 99% | 2022-04-12
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | Kentucky | United States | 69558 | OTH 069558 SOF MWD Kennel |  |  |  | 2010-05-11 | 2011-04-11 | 2011-06-24 | 100% | 2011-07-19
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | North Carolina | United States | 69559 | SOF 069559 Mil Wrk Dog Kennel |  |  |  | 2010-05-18 | 2011-05-18 | 2011-11-02 | 100% | 2012-01-02
2022-12-14 | 2010 | Special Operations Command | Major Military Construction | Florida | United States | 69560 | PN: 69560, 7SFG Canine Tng Fac |  |  |  | 2010-04-08 | 2011-08-01 | 2012-05-31 | 100% | 2011-09-14
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | North Carolina | United States | 69573 | CLOSED - SOF Admin/Co Ops 69573 USASOC |  |  |  | 2011-10-27 | 2013-03-29 | 2014-01-23 | 100% | 2013-11-21
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69758 | CLOSED - SOF Brigade HQs 69758 |  |  |  | 2012-11-14 | 2014-04-08 | 2016-12-06 | 100% | 2016-12-06
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | Georgia | United States | 69759 | SOF 069759 TEMF Expansion |  |  |  | 2011-08-17 | 2012-08-16 | 2012-10-18 | 100% | 2012-10-18
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 71224 | CLOSED - SOF Admin/Com Ops Ph2 71224 |  |  |  | 2012-11-07 | 2014-07-30 | 2015-04-27 | 100% | 2015-04-28
2022-12-14 | 2021 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 72426 | SOF Military Working Dog Facility - 72426 |  |  |  | 2021-07-06 | 2022-12-28 | 2023-12-05 | 57% | 2023-12-05
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | New Mexico | United States | 73018 | CAFB 73018 C130 WASH RACK HANG |  |  |  | 2012-11-16 | 2014-04-10 | 2014-08-26 | 100% | 2014-09-09
2022-12-14 | 2012 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 73021 | CAFB 73021 AMXS FACILITY |  |  |  | 2013-02-25 | 2014-08-09 | 2014-11-24 | 100% | 2014-11-24
2022-12-14 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 74813 | SOF Parachute Rigging Facility - 74813 |  |  |  | 2018-07-17 | 2020-09-04 | 2021-11-01 | 99% | 2021-11-01
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 76364 | CLOSED - SOF BN Ops Complex 76364 |  |  |  | 2012-12-04 | 2014-08-26 | 2016-04-21 | 100% | 2016-04-21
2022-12-14 | 2014 | Special Operations Command | Major Military Construction | Kentucky | United States | 76365 | 076365 Trps Btln Facil |  |  |  | 2015-12-02 | 2017-10-02 | 2018-01-24 | 100% | 2018-01-24
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76366 | OTH 76366, 7th SFG GSTB (FY12) |  |  |  | 2012-09-12 | 2015-09-12 | 2016-01-27 | 100% | 2016-03-02
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | Colorado | United States | 76367 | 076367 SOF Battalion Operations Complex |  |  |  | 2014-08-28 | 2020-03-18 | 2020-03-18 | 100% | 2020-03-18
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76371 | OTH 76371 7th SFG GSB Detachment |  |  |  | 2012-09-12 | 2015-09-12 | 2016-01-27 | 100% | 2016-03-02
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 76373 | CLOSED - SOF Administrative Annex 76373 |  |  |  | 2012-08-15 | 2014-04-17 | 2014-10-03 | 100% | 2014-11-04
2022-12-14 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76375 | SOF Civil Affairs Battalion Complex - 76375 |  |  |  | 2014-12-01 | 2016-07-23 | 2017-08-28 | 100% | 2017-08-29
2022-12-14 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76376 | CLOSED - SOF Language & Cultural Center - 76376 |  |  |  | 2015-01-09 | 2017-05-14 | 2018-01-19 | 100% | 2018-01-19
2022-12-14 | 2011 | Special Operations Command | Major Military Construction | North Carolina | United States | 76511 | CLOSED - SOF JIB AND AVTEG ANNEX 76511 |  |  |  | 2011-11-09 | 2013-05-11 | 2013-10-31 | 100% | 2013-10-31
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 76513 | SOF Special Tactics Facility, Ph2 76513 |  |  |  | 2017-09-19 | 2019-12-18 | 2021-04-22 | 100% | 2021-04-22
2022-12-14 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 76514 | SOF Special Tactics Facility, Ph 3 - 76514 |  |  |  | 2018-07-02 | 2020-03-23 | 2021-12-17 | 99% | 2021-12-17
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 76518 | CLOSED - SOF Indoor Firing Range (ATF) - 76518 |  |  |  | 2016-05-17 | 2017-05-17 | 2018-01-12 | 100% | 2018-01-31
2022-12-14 | 2014 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 78024 | OKI-Torii FY14 SOCOM 78024 SOF Fac Augmentation |  |  |  | 2015-07-01 | 2017-12-12 | 2018-06-18 | 100% | 2018-06-18
2022-12-14 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79437 | SOF Training Command Building - 79437 |  |  |  | 2017-02-21 | 2019-02-11 | 2022-07-29 | 96% | 2022-07-29
2022-12-14 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 79438 | CLOSED - SOF Combat Medic Skills Sustainment Course Bldg - 79438 |  |  |  | 2014-10-27 | 2016-04-19 | 2016-10-26 | 100% | 2016-12-14
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 79439 | SOF Intelligence Training - 79439 |  |  |  | 2018-11-14 | 2020-05-07 | 2021-11-15 | 99% | 2023-02-20
2022-12-14 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | 79443 | SOF Human Performance Training Center- 79443 |  |  |  | 2019-02-26 | 2020-12-27 | 2021-08-18 | 100% | 2021-08-18
2022-12-14 | 2019 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 79447 | SOF Human Performance Training Facility PN79447 |  |  |  | 2019-06-11 | 2021-05-31 | 2023-05-17 | 82% | 2023-05-17
2022-12-14 | 2018 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 79453 | SOF TEMF - 79453 |  |  |  | 2019-03-19 | 2022-06-16 | 2023-03-04 | 96% | 2023-03-04
2022-12-14 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79456 | CLOSED - SOF Tactical Equipment Maint Facility - 79456 |  |  |  | 2015-11-12 | 2016-11-11 | 2017-02-13 | 100% | 2017-02-13
2022-12-14 | 2013 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 80233 | CLOSED - SOF Live-Fire Training Tower (UMC) - 80233 |  |  |  | 2014-02-27 | 2015-02-27 | 2015-03-04 | 100% | 2015-03-05
2022-12-14 | 2018 | Special Operations Command | Major Military Construction | Virginia | United States | 80771 | FY18 Battalion Complex, Phase 1 |  |  |  | 2019-02-25 | 2020-12-26 | 2022-12-15 | 99% | 2022-12-15
2022-12-14 | 2019 | Special Operations Command | Major Military Construction | Florida | United States | 80772 | SOF Human Performance Training Center |  |  |  | 2021-06-10 | 2023-06-10 | 2023-09-08 | 17% | 2023-09-08
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 80773 | CLOSED - SOF Battalion Operations Facility - PN80773 |  |  |  | 2017-01-31 | 2019-01-31 | 2019-06-06 | 100% | 2019-07-17
2022-12-14 | 2019 | Special Operations Command | Major Military Construction | North Carolina | United States | 80774 | SOF SERE Resistance Training Complex - 80774 |  |  |  | 2020-01-07 | 2022-01-06 | 2023-02-13 | 99% | 2023-02-13
2022-12-14 | 2019 | Special Operations Command | Major Military Construction | Virginia | United States | 80775 | Battalion Complex, Phase 2 |  |  |  | 2021-01-11 | 2023-02-22 | 2024-08-30 | 51% | 2024-08-30
2022-12-14 | 2020 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 81165 | SOF Human Platform Force Gen Fac - 81165 |  |  |  | 2020-12-08 | 2023-03-08 | 2023-12-15 | 67% | 2023-12-15
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | Colorado | United States | 81483 | PN 81483 SOF Mountaineering Climbing Rappel Tower |  |  |  | 2013-09-20 | 2014-09-15 | 2014-11-26 | 100% | 2014-11-26
2022-12-14 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | 81894 | CLOSED - SOF Telecom Reliability Facility - 81894 |  |  |  | 2018-11-27 | 2019-11-27 | 2020-10-30 | 100% | 2020-12-01
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | Kentucky | United States | 81897 | FTC SOF 81897 Company Headquarters/Classrooms |  |  |  | 2017-01-03 | 2018-08-26 | 2019-01-30 | 100% | 2019-01-30
2022-12-14 | 2019 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 81899 | SOF Mountaineering Facility , PN81899 |  |  |  | 2019-06-11 | 2021-05-31 | 2023-01-28 | 66% | 2023-01-28
2022-12-14 | 2018 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 81903 | FY18 PN81903 1-1 SFG Torii Sta |  |  |  | 2019-04-19 | 2021-04-18 | 2022-10-04 | 99% | 2022-05-26
2022-12-14 | 2012 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 83011 | CAFB 83011 AC-RECAP APR & TAXI |  |  |  | 2012-10-30 | 2014-05-01 | 2014-03-05 | 100% | 2014-03-05
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | 83702 | Joint Special Operations University |  |  |  | 2013-11-05 | 2015-06-28 | 2016-09-30 | 100% | 2016-09-30
2022-12-14 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 85958 | SOF Combat Medic Training Facility - 85958 |  |  |  | 2019-06-18 | 2021-04-28 | 2023-01-04 | 92% | 2023-01-04
2022-12-14 | 2020 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 86021 | SOF Assessment and Selection Training Complex - 86021 |  |  |  | 2020-09-09 | 2022-09-09 | 2023-02-06 | 74% | 2023-02-06
2022-12-14 | 2021 | Special Operations Command | Major Military Construction | Arizona | United States | 86022 | OTH 86022 SOF HANGAR YUMA PROVING GROUND, ARIZONA |  |  |  | 2021-11-17 | 2023-11-07 | 2023-11-07 | 44% | 2023-11-07
2022-12-14 | 2019 | Special Operations Command | Major Military Construction | Virginia | United States | 86025 | SOCOM Maintenance and Supply Facility_86025 |  |  |  | 2022-04-01 | 2024-06-19 | 2024-06-19 | 21% | 2024-06-19
2022-12-14 | 2021 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 87437 | SOF Group Headquarters - 87437 |  |  |  | 2022-04-19 | 2025-01-03 | 2025-01-03 | 10% | 2025-01-03
2022-12-14 | 2019 | Special Operations Command | Major Military Construction | Kentucky | United States | 87438 | OTH 087438 SOF Multi-Use Helicopter Training Facility |  |  |  | 2021-01-06 | 2022-05-01 | 2022-06-29 | 100% | 2022-07-12
2022-12-14 | 2021 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 88658 | SOF Operations Facility - 88658 |  |  |  | 2021-09-16 | 2023-03-10 | 2024-03-21 | 20% | 2024-03-21
2022-12-14 | 2022 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 91018 | OTH 91018 SOF Battalion Operations Facility / ECSA |  |  |  | 2022-10-26 | 2024-10-15 | 2024-10-15 | 1% | 2024-10-15
2022-12-14 | 2020 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | 92594 | SOF Operations Support Facility - 92594 |  |  |  | 2020-09-09 | 2022-03-03 | 2022-09-06 | 65% | 2022-09-06
2022-12-14 | 2008 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | A73010 | OTHA73010 Logistics Storage Wa |  |  |  | 2009-11-12 | 2011-02-05 | 2012-11-15 | 100% | 2012-11-15
2022-12-14 | 2016 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | AFSOC103002 | FY16 ACE AFSOC103002 Airfield Pavements |  |  |  | 2018-11-01 | 2020-10-21 | 2021-02-17 | 100% | 2021-02-26
2022-12-14 | 2017 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | AFSOC103010 | ACE AFSOC103010 Simulator Facility |  |  |  | 2021-06-04 | 2023-06-04 | 2023-06-04 | 29%
2022-12-14 | 2017 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | AFSOC103022 | ACE AFSOC103022 Airfield Apron & Site Infrastructure |  |  |  | 2018-03-20 | 2021-12-26 | 2022-04-27 | 100% | 2022-09-16
2022-12-14 | 2016 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | ANZY163001 | ANZY163001 - Aircraft Test Support Facility |  |  |  | 2018-04-11 | 2019-10-03 | 2022-09-06 | 100% | 2022-03-08
2022-12-14 | 2015 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ063029 | CZQZ63029 CAFB FY15 STS SOF |  |  |  | 2019-01-17 | 2021-05-16 | 2022-08-17 | 99% | 2022-08-31
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ083012 | CAFB FY12 SOF HANGAR/AMU (2-BAY) |  |  |  | 2012-10-24 | 2014-09-04 | 2014-10-02 | 100% | 2014-10-02
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ083013 | CAFB FY13 SOF AC-RECAP COMBAT PARKING APRON |  |  |  | 2014-06-20 | 2015-11-22 | 2015-10-15 | 100% | 2015-10-15
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ083021 | CAFB FY16 SOF 551 SOS SQ OPS Facility |  |  |  | 2017-03-23 | 2018-11-13 | 2018-11-09 | 100% | 2018-12-26
2022-12-14 | 2018 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ103006 | SOF C-130 AGE FACILITY; CANNON AFB, NM |  |  |  | 2018-11-14 | 2020-01-13 | 2020-05-27 | 100% | 2020-05-27
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ133003 | CZQZ133003 CAFB FY16 SOF ST SQ OPS Facility |  |  |  | 2019-01-17 | 2021-05-16 | 2022-08-17 | 99% | 2022-08-31
2022-12-14 | 2016 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | FTEV073010 | SOF Fuel Cell Maint Hangar, Hurlburt Field, FL |  |  |  | 2016-09-15 | 2018-09-15 | 2022-05-31 | 99% | 2021-11-01
2022-12-14 | 2021 | Special Operations Command | Major Military Construction | Florida | United States | FTEV103005 | FTEV103005 SOF Special Tactics Ops Facility |  |  |  | 2022-09-12 | 2025-02-28 | 2025-02-28 | 3% | 2025-02-28
2022-12-14 | 2018 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153003 | (FTEV153003) SOF SIMULATOR & FUT FACILITY |  |  |  | 2018-10-31 | 2020-04-23 | 2022-11-30 | 99% | 2021-01-21
2022-12-14 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153007 | OTH FTEV153007 MAINTENANCE TRAINING FACILITY HURLBURT FIELD |  |  |  | 2020-12-02 | 2022-11-22 | 2023-01-07 | 84% | 2023-01-07
2022-12-14 | 2018 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153008 | (FTEV153008) SOF COMBAT PARKING APRON (AC-130J) (CAPA) |  |  |  | 2020-04-02 | 2023-03-18 | 2023-03-18 | 76% | 2023-03-18
2022-12-14 | 2020 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | FTEV153009 | SOF AMU & WEAPONS HANGAR, HURLBURT FIELD, FL (FTEV153009) |  |  |  | 2021-04-19 | 2024-05-18 | 2024-07-19 | 37% | 2024-07-19
2022-12-14 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153010 | OTH FTEV153010 Combined Squadron Operations Facility, Hurlb |  |  |  | 2020-10-20 | 2022-10-10 | 2022-12-20 | 86% | 2022-12-20
2022-12-14 | 2021 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153011 | OTH FTEV153011 SOF Combat Parking Apron North (AC-130), Hur |  |  |  | 2021-11-09 | 2024-10-24 | 2024-10-24 | 26% | 2024-10-24
2022-12-14 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | FTFA113004 | SOF AvFID Operations & Maint Facilities, Duke Field, FL |  |  |  | 2013-12-26 | 2016-12-25 | 2017-05-26 | 100% | 2017-05-26
2022-12-14 | 2018 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | FTFA163001 | (FTFA163001) SOF Simulator Facility (C-146), Duke Field |  |  |  | 2020-10-06 | 2022-03-30 | 2022-09-29 | 99% | 2022-09-29
2022-12-14 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | FTFA163002 | FTFA163002 - SOF Combined Squad Ops |  |  |  | 2021-09-20 | 2023-09-10 | 2023-09-10 | 54% | 2023-09-10
2022-12-14 | 2017 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | LXEZ123484 | FY17 LXEZ123484 Simulator Fac Kadena |  |  |  | 2020-01-27 | 2021-09-27 | 2021-09-29 | 99% | 2021-09-29
2022-12-14 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | NVZR123709 | SOF Acquisition Ctr PHII |  |  |  | 2012-09-06 | 2014-01-19 | 2015-01-07 | 100% | 2014-02-07
2022-12-14 | 2016 | Special Operations Command | Major Military Construction |  | Unspecified World Wide | NVZR143703 | SOCOM-Operations Support Facility, MacDill AFB, FL |  |  |  | 2016-10-18 | 2019-01-26 | 2019-11-19 | 100% | 2019-11-19
2022-12-14 | 2020 | Special Operations Command | Major Military Construction | Washington | United States | PQWY083008 | SOF 22 STS Operations Facility PN PQWY083008 |  |  |  | 2020-06-16 | 2022-06-16 | 2022-12-23 | 99% | 2022-10-07
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | California | United States | Q1119 | SOF COMMUNICATION / ELECTRONICS MAINTENANCE FACILITY |  |  |  | 2015-10-13 | 2016-04-06 | 2016-04-06 | 100% | 2017-06-01
2022-12-20 | 2016 | Special Operations Command | Major Military Construction | California | United States | Q1126 | SOF COMBAT SERVICE SUPPORT FACILITY |  |  |  | 2016-08-22 | 2018-02-14 | 2019-02-28 | 100% | 2019-03-15
2022-12-20 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1219 | SOF MARINE BATTALION COMPANY/TEAM FACILITIES |  |  |  | 2018-01-11 | 2020-01-12 | 2022-03-31 | 98% | 2022-03-31
2022-12-20 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1288 | SOF COMBAT SERVICE SUPPORT FACILITY |  |  |  | 2018-01-11 | 2020-01-12 | 2022-03-31 | 100% | 2022-02-15
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1394 | SOF MOTOR TRANSPORT MAINTENANCE EXPANSION |  |  |  | 2020-04-10 | 2021-10-04 | 2022-06-30 | 100% | 2022-05-31
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1394B | SOF MOTOR TRANSPORT MAINTENANCE EXAPANSION PHASE B |  |  |  | 2022-09-27 | 2024-09-27 | 2024-09-27 | 89% | 2024-09-12
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1395 | SOF MARINE RAIDER REGIMENT HQ |  |  |  | 2020-04-10 | 2022-12-17 | 2023-02-17 | 74% | 2023-02-17
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1396 | SOF INTEL OPS EXPANSION |  |  |  | 2015-08-31 | 2017-03-09 | 2017-10-27 | 100% | 2017-10-25
2022-12-20 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1469 | SOF MSOB SUPPORT FACILITIES |  |  |  | 2014-10-14 | 2015-11-24 | 2016-08-25 | 99% | 2016-08-25
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1475 | MARSOC CULTURAL ASSIMILATION FACILITY |  |  |  | 2018-07-03 | 2019-09-13 | 2021-01-14 | 94% | 2021-01-13
2022-12-20 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1481 | INDIVIDUAL TRAINING COURSE TEAM TRAINING FACILITY |  |  |  | 2018-09-14 | 2019-11-11 | 2020-07-06 | 100% | 2020-07-06
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1482 | MARINE SPECIAL OPERATIONS SCHOOL 120 MAN CLASSROOMS |  |  |  | 2020-10-06 | 2021-09-18 | 2023-07-15 | 100% | 2022-07-15
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | Q1534 | REPLACE MARSOC ITC TEAM FACILITY |  |  |  | 2020-09-29 | 2024-05-27 | 2025-02-07 | 52% | 2025-02-07
2022-12-20 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | Q157 | SOF HUMAN PERFORMANCE CENTER |  |  |  | 2016-03-11 | 2017-09-03 | 2020-09-16 | 100% | 2021-01-20
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | Q166 | QDR SOF MOBILE COMMUNICATIONS DET SUPPORT FACILITY |  |  |  | 2015-10-05 | 2017-07-17 | 2019-03-04 | 100% | 2019-03-04
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | Mississippi | United States | Q170 | SOF NAVSCIATTS APPLIED INSTRUCTION FACILITY |  |  |  | 2016-02-09 | 2017-10-17 | 2018-06-16 | 100% | 2018-06-27
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | Q183 | SOF INDOOR DYNAMIC RANGE |  |  |  | 2014-05-01 | 2017-10-01 | 2018-05-18 | 100% | 2017-11-23
2022-12-20 | 2019 | Special Operations Command | Major Military Construction | California | United States | Q200 | SOF NSWG-1 OPERATIONS SUPPORT FACILITY |  |  |  | 2020-07-14 | 2023-01-20 | 2023-01-20 | 60% | 2023-01-20
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | Virginia | United States | Q224 | SOF NSWG-10 OPERATIONS SUPPORT FACILITY |  |  |  | 2021-02-12 | 2023-08-05 | 2023-10-04 | 45% | 2023-10-04
2022-12-20 | 2016 | Special Operations Command | Major Military Construction | Virginia | United States | Q225 | SOF NSWG-10 UAS SUPPORT FACILITY |  |  |  | 2018-08-17 | 2019-10-22 | 2020-01-07 | 100% | 2020-01-07
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | Mississippi | United States | Q240 | SOF LAND ACQUISITION WESTERN MANEUVER AREA |  |  |  | 2019-07-29 | 2020-01-25 | 2020-01-25 | 100% | 2019-12-31
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | Q241 | SOF NSWG4 BOAT SUPPORT FACILITY |  |  |  | 2019-10-10 | 2020-11-13 | 2021-04-16 | 100% | 2021-04-15
2022-12-20 | 2021 | Special Operations Command | Major Military Construction | Mississippi | United States | Q246U | SOF STENNIS RANGE SUPPORT FACILITY |  |  |  | 2021-10-12 | 2022-10-03 | 2024-01-02 | 54% | 2022-10-05
2022-12-20 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | Q334 | SOF LOGSU TWO OPERATIONS FACILITY |  |  |  | 2016-02-24 | 2018-07-29 | 2020-05-01 | 100% | 2020-05-01
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | Nevada | United States | Q418 | SOF TACTICAL GROUND MOBILITY VEHICLE MAINTENANCE FACILITY |  |  |  | 2015-09-01 | 2017-02-23 | 2018-02-12 | 100% | 2018-02-02
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | Hawaii | United States | Q463 | SOF UNDERSEA OPERATIONAL TRAINING FACILITY |  |  |  | 2020-04-29 | 2022-04-15 | 2022-04-15 | 100% | 2022-04-15
2022-12-20 | 2021 | Special Operations Command | Major Military Construction | California | United States | Q651U | SOF SBT-12 COMBATANT CRAFT OPERATIONS FACILITY |  |  |  | 2022-01-21 | 2023-07-18 | 2023-07-18 | 1% | 2023-10-09
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | Virginia | United States | Q698 | SOF PHYSICAL SECURITY BUILDING ADDITION (DAM NECK) |  |  |  | 2021-04-07 | 2022-08-08 | 2022-08-08 | 39% | 2022-08-08
2022-12-20 | 2014 | Special Operations Command | Major Military Construction | Arizona | United States | Q771 | SOF DESERT WARFARE TRAINING CENTER |  |  |  | 2018-10-03 | 2020-02-02 | 2022-07-25 | 98% | 2021-08-13
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | California | United States | Q776 | SOF LOGSU ONE OPERATIONS FACILITY #1 |  |  |  | 2015-10-14 | 2017-10-23 | 2019-07-23 | 100% | 2019-07-23
2022-12-20 | 2016 | Special Operations Command | Major Military Construction | Virginia | United States | Q777 | SOF APPLIED INSTRUCTION FACILITY |  |  |  | 2018-07-30 | 2020-10-09 | 2022-08-16 | 98% | 2021-08-12
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | Virginia | United States | Q791 | SOF SATEC RANGE EXPANSION |  |  |  | 2018-09-27 | 2021-03-17 | 2021-11-17 | 99% | 2024-07-18
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | Virginia | United States | Q824 | SOF DTC COMPLEX EXPANSION |  |  |  | 2020-10-14 | 2022-08-16 | 2022-08-16 | 35% | 2023-07-28
2022-12-20 | 2019 | Special Operations Command | Major Military Construction | Virginia | United States | Q834 | SOF MAGAZINES |  |  |  | 2019-11-26 | 2021-05-20 | 2021-11-17 | 80% | 2023-05-05
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | California | United States | Q855 | SOF BASIC TRAINING COMMAND |  |  |  | 2019-10-14 | 2022-08-30 | 2023-02-10 | 41% | 2020-05-08
2022-12-20 | 2017 | Special Operations Command | Major Military Construction | California | United States | Q889 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2017-10-12 | 2020-03-31 | 2021-01-31 | 100% | 2020-03-31
2022-12-20 | 2017 | Special Operations Command | Major Military Construction | California | United States | Q890 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2017-10-12 | 2020-03-31 | 2021-01-31 | 100% | 2021-07-30
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | California | United States | Q892 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2018-09-27 | 2021-03-31 | 2021-06-13 | 100% | 2017-08-28
2022-12-20 | 2015 | Special Operations Command | Major Military Construction | California | United States | Q893 | SOF SUPPORT ACTIVITY OPERATIONS FACILITY #2 |  |  |  | 2015-10-14 | 2018-04-02 | 2019-03-11 | 99% | 2020-08-20
2022-12-20 | 2017 | Special Operations Command | Major Military Construction | Virginia | United States | Q900 | SOF MULTI-PURPOSE CANINE OPERATIONS FACILITY |  |  |  | 2018-06-28 | 2020-06-30 | 2021-04-30 | 99% | 2021-04-30
2022-12-20 | 2021 | Special Operations Command | Major Military Construction | Virginia | United States | Q907 | SOF DRY COMBAT SUBMERSIBLE OPERATIONS FACILITY AND COMMAND CENTER |  |  |  | 2020-10-04 | 2023-07-26 | 2024-02-21 | 22% | 2023-12-21
2022-12-20 | 2022 | Special Operations Command | Major Military Construction | California | United States | Q912 | SOF NSWG11 OPERATIONS SUPPORT FACILITY |  |  |  | 2022-05-26 | 2024-06-11 | 2024-06-11 | 79% | 2024-06-14
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | Virginia | United States | Q914U | SOF NSWG2 TRAINING FACILITY |  |  |  | 2020-10-21 | 2022-04-23 | 2022-11-30 | 100% | 2022-10-31
2022-12-20 | 2019 | Special Operations Command | Major Military Construction | California | United States | Q918 | SOF CLOSE QUARTERS COMBAT FACILITY |  |  |  | 2019-10-10 | 2021-10-09 | 2022-02-24 | 99% | 2022-02-24
2022-12-20 | 2017 | Special Operations Command | Major Military Construction | California | United States | Q919 | SOF SPECIAL RECON TEAM ONE OPERATIONS FACILITY |  |  |  | 2017-04-13 | 2018-10-22 | 2020-03-06 | 100% | 2020-03-06
2022-12-20 | 2016 | Special Operations Command | Major Military Construction | California | United States | Q920 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #2 |  |  |  | 2016-10-04 | 2018-10-13 | 2019-12-27 | 100% | 2019-04-12
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | California | United States | Q921 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #3 |  |  |  | 2018-08-09 | 2021-02-15 | 2021-06-18 | 100% | 2021-10-14
2022-12-20 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | Q9440 | SOF BOAT DOCKS |  |  |  | 2015-05-14 | 2016-08-22 | 2019-07-17 | 100% | 2019-07-17
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | Q945 | SOF WATERCRAFT MAINTENANCE FACILITY |  |  |  | 2021-01-29 | 2022-10-31 | 2023-08-03 | 44% | 2023-01-17
2022-12-20 | 2019 | Special Operations Command | Major Military Construction | California | United States | Q949 | SOF ATC APPLIED INSTRUCTION FACILITY |  |  |  | 2019-11-11 | 2022-05-19 | 2022-12-23 | 51% | 2022-12-23
2022-12-20 | 2019 | Special Operations Command | Major Military Construction | California | United States | Q950 | SOF ATC TRAINING FACILITY |  |  |  | 2019-11-11 | 2022-05-19 | 2022-12-23 | 50% | 2022-12-23
2022-12-20 | 2022 | Special Operations Command | Major Military Construction | California | United States | Q951 | SOF ATC OPERATIONS SUPPORT FACILITY |  |  |  | 2024-11-02 | 2025-01-02 | 2025-04-03 | 22% | 2025-01-02
2022-12-20 | 2017 | Special Operations Command | Major Military Construction | California | United States | Q952 | SOF HUMAN PERFORMANCE TRAINING CENTER |  |  |  | 2017-08-24 | 2019-11-22 | 2020-03-02 | 100% | 2021-04-16
2022-12-20 | 2018 | Special Operations Command | Major Military Construction | California | United States | Q964 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2018-09-27 | 2021-03-31 | 2021-06-13 | 100% | 2021-07-30
2022-12-20 | 2017 | Special Operations Command | Major Military Construction | California | United States | Q966 | SOF TRADET ONE OPERATIONS FACILITY |  |  |  | 2017-10-12 | 2020-04-19 | 2020-11-20 | 100% | 2020-11-20
2022-12-20 | 2021 | Special Operations Command | Major Military Construction | Virginia | United States | Q997 | SOF NSWTG2 COMBAT SERVICE SUPPORT FACILITIES |  |  |  | 2021-05-21 | 2024-03-16 | 2024-03-16 | 32% | 2024-03-11
2022-12-20 | 2020 | Special Operations Command | Major Military Construction | Virginia | United States | Q999 | SOF NSWG2 JSOTF OPERATIONS TRAINING FACILITY |  |  |  | 2021-02-12 | 2023-08-05 | 2023-10-04 | 45% | 2023-10-04
2022-12-14 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | TMKH003003 | SOF 21 STS Ops Facility - PN TMKH003003 |  |  |  | 2018-07-31 | 2020-01-22 | 2020-09-22 | 80% | 2025-09-22
2023-01-31 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 102299 | CNST Pilot EV Charge Stations |  |  |  | 2022-10-06 | 2023-08-26 | 2023-09-08 | 10%
2023-01-31 | 2015 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80011 | Redundant Chilled Water Loop |  | 1300000 | Reprogramming of expired funds received from project 80004 | 2020-04-01 | 2021-06-21 | 2023-02-28 | 92% | 2022-08-15
2023-01-31 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 87637 | Pentagon Corridor 8 Pedestrian Access Control Point |  | 55553 | Reprogramming to project 88963 | 2022-04-14 | 2022-06-21 | 2024-01-01 | 13% | 2023-01-28
2023-01-31 | 2019 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 87645 | North Village Secondary VACP and Fencing |  | 383475 | Reprogramming $383,475 to project 87744 | 2021-04-01 | 2021-04-23 | 2023-07-31 | 33% | 2022-07-23
2023-01-31 | 2019 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 88790 | Exterior Infrastructure and Security Improvements |  | 244262 | Reprogramming to project 88963 | 2020-04-24 | 2022-08-17 | 2022-11-10 | 100% | 2022-10-17
2023-01-31 | 2018 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 88963 | Security Upgrades |  | 299816 | Reprogramming received from projects 87637 & 88790 | 2020-02-12 | 2022-01-20 | 2022-10-14 | 100% | 2022-08-30
2023-01-31 | 2022 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 90570 | Consolidated Maintenance Complex
2023-01-31 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91474 | Southeast Safety Traffic and Parking Improvements |  | 4170000 | Reprogramming of UMC funds to project | 2020-02-01 | 2021-01-20 | 2024-02-12 | 13% | 2023-04-23
2023-01-31 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91474A | Southeast Safety Traffic and Parking Improvements |  |  |  | 2019-03-18 | 2019-06-18 | 2019-06-18 | 100% | 2021-09-22
2023-01-31 | 2020 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91531 | Backup Generator
2023-01-31 | 2020 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 92232 | Control Tower and Fire Day Station |  |  |  | 2022-05-02 | 2023-04-27 | 2024-02-27 | 24%
2023-01-31 | 2022 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 95677 | Force Protection Perimeter Enhancements |  |  |  |  | 2024-10-03
2023-01-31 | 2022 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 95696 | Public Works Support Facility
2023-01-31 | 2023 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 97665 | Commercial Vehicle Inpsection Facility

## CONTRACTS
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Prime Contract Number | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date
2023-01-31 | 2021 | Air Force Active | ACJP183018 |  | 2021-03-31 | 2021-09-21 | J.I. Garcia Construction, Inc. | N6247318D5817 | 4749000 | 4749000 | 2022-11-13 | 2022-11-13
2023-01-31 | 2018 | Air Force Active | AEWV171012 |  | 2018-08-01 | 2019-03-01 | Black & Veatch Special Project | W912ER18D0005 | 3705150 | 3769955 | 2023-10-02 | 2025-05-24
2023-01-31 | 2018 | Air Force Active | AGGN053009 |  | 2019-03-20 | 2020-03-24 | Source Selection Sensitive | W912BV20C0005 | 18933323 | 19941747 | 2022-04-30 | 2023-06-08
2023-01-31 | 2016 | Air Force Active | AGGN123003 |  | 2018-06-14 | 2019-09-27 | CNS Sheffield-Korte Team | W912BV19C0024 | 22471409 | 22546864 | 2021-10-26 | 2022-06-10
2023-01-31 | 2017 | Air Force Active | AGGN173001 |  | 2017-01-06 | 2017-07-06 | SGS, LLC | W912BV17C0010 | 10817113 | 11163192 | 2018-12-01 | 2019-09-09
2023-01-31 | 2019 | Air Force Active | AGGN213001 |  | 2018-10-31 | 2019-06-17 | SGS, LLC; Yukon OK | W912BV19C0011 | 12273387 | 13016024 | 2021-11-21 | 2022-02-24
2023-01-31 | 2017 | Air Force Active | AJJY073105P2 |  | 2021-07-12 | 2021-12-16 | Relyant Global LLC / Maryville / Tennessee | N6274222C1320 | 30905912 | 30905912 | 2025-02-07 | 2025-02-07
2023-01-31 | 2020 | Air Force Active | AJJY073105P3 |  | 2020-01-17 | 2020-09-16 | Core Tech-Hawaiian Dredging | N6274220R1324 | 52969474 | 52969474 | 2023-07-16 | 2023-06-16
2023-01-31 | 2022 | Air Force Active | AJJY073105P4 |  | 2021-10-13 | 2022-05-04 | Reliable Builders, Inc | N6274222C1325 | 43444038 | 43444038 | 2025-08-15 | 2025-08-15
2023-01-31 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 91150297 | 91150297 | 2017-04-16 | 2025-12-19
2023-01-31 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 98038253 | 104322589 | 2017-03-08 | 2022-11-30
2023-01-31 | 2015 | Air Force Active | AJJY133028 |  | 2016-06-01 | 2016-09-30 | Pernix Guam, LLC | N6274216C1309 | 27010495 | 29858250 | 2018-11-08 | 2023-03-03
2023-01-31 | 2022 | Air Force Active | AJJY163000 |  | 2021-10-06 | 2022-05-09 | Cadell-Nan | N6274222C1308 | 29671766 | 29671766 | 2023-11-30 | 2023-11-30
2023-01-31 | 2019 | Air Force Active | AJJY183003 |  | 2021-10-06 | 2022-05-26 | Granite-Obayashi | N6274222C1327 | 10760166 | 10760166 | 2024-01-29 | 2024-01-29
2023-01-31 | 2020 | Air Force Active | AJJY183017 |  | 2020-06-15 | 2020-09-30 | Serrano Construction | N4019218D2804 | 4160672 | 4220039 | 2022-06-29 | 2022-07-28
2023-01-31 | 2021 | Air Force Active | AJJY203001 |  | 2020-09-16 | 2021-02-25 | Granite-Obayashi, a Joint Venture | N6274221C1338 | 43545116 | 47011767 | 2023-03-25 | 2023-11-24
2023-01-31 | 2017 | Air Force Active | AJXF093000 |  | 2017-08-02 | 2018-05-24 | EDIFICE, LLC | N4008017D0009 | 11179388 | 11179388 | 2020-02-25 | 2022-07-12
2023-01-31 | 2018 | Air Force Active | AJXF173021 |  | 2018-06-05 | 2018-07-05 | Clark Construction Group, LLC | N4008019C0008 | 220000000 | 220000000 | 2019-01-26 | 2022-08-30
2023-01-31 | 2018 | Air Force Active | AJXF173030 |  | 2019-02-17 | 2020-09-23 | Clark Construction LLC | N4008020C0024 | 20335697 | 20335697 | 2022-01-24 | 2022-12-30
2023-01-31 | 2018 | Air Force Active | ALUA113023 |  | 2019-05-29 | 2019-09-26 | MVL USA, Inc. / Houston / TX | W912ER19C0016 | 13890460 | 13651445 | 2021-01-20 | 2021-12-28
2023-01-31 | 2018 | Air Force Active | ASHE143008 |  | 2018-01-04 | 2018-09-28 | CMC | N6247018C4004 | 16003726 | 16003726 | 2021-01-25 | 2023-03-10
2023-01-31 | 2020 | Air Force Active | ASPR150126 |  | 2020-10-05 | 2020-11-04 | Source Selection Sensitive | W9127821C0005 | 3795142 | 3795142 | 2020-12-18 | 2022-01-20
2023-01-31 | 2017 | Air Force Active | ASVF164000 |  | 2017-09-16 | 2018-09-11 | RED HORSE | FA571018P0325 | 2200000 | 2348000 | 2024-01-23 | 2025-08-11
2023-01-31 | 2018 | Air Force Active | ASVF183100A |  | 2019-01-11 | 2020-04-10 | American International Contractors, (Pkg 2, Aprons) | W912ER20C0009 | 32474636 | 32474636 | 2023-03-28 | 2023-07-12
2023-01-31 | 2018 | Air Force Active | ASVF183100B |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER20C0009 | 9862845 | 9856753 | 2023-03-28 | 2023-07-12
2023-01-31 | 2018 | Air Force Active | ASVF183100C |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc, (Pkg 2, Aprons) | W912ER20C0009 | 8267668 | 8267668 | 2023-03-28 | 2023-07-12
2023-01-31 | 2018 | Air Force Active | ASVF183100D |  | 2018-06-28 | 2019-04-05 | The Morganti Group, Inc / Danbury, CT (Pkg 3, Dorm) | W912ER19C0008 | 10434344 | 10393609 | 2020-08-29 | 2021-10-09
2023-01-31 | 2018 | Air Force Active | ASVF183100E |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER20C0009 | 804821 | 806055 | 2023-03-28 | 2023-07-12
2023-01-31 | 2018 | Air Force Active | ASVF183100F |  | 2020-03-11 | 2020-04-10 | American International Contractors, Inc (Pkg 2, Aprons) | W912ER20C0009 | 28401350 | 28167704 | 2023-03-21 | 2022-07-12
2023-01-31 | 2020 | Air Force Active | ASVF203110 |  | 2021-10-22 | 2022-05-10 | Morganti Group, Inc. | W912ER22C0016 | 14696614 | 14712663 | 2024-08-02 | 2024-08-02
2023-01-31 | 2020 | Air Force Active | ASVF203130 |  | 2021-10-22 | 2022-05-06 | American Int'l Contractors Inc | W912ER22C0015 | 37010368 | 39416041 | 2025-01-18 | 2025-01-18
2023-01-31 | 2017 | Air Force Active | AWUB095000 |  | 2016-12-02 | 2019-07-17 | CNS Bristol General Contractors, LLC | N6945013D1771 | 24961520 | 25022647 | 2022-01-03 | 2023-04-24
2023-01-31 | 2017 | Air Force Active | AWUB105003 |  | 2017-07-10 | 2018-06-21 | CNS Source Selection Sensitive | N6945018C2105 | 3396587 | 3570241 | 2020-10-08 | 2021-02-23
2023-01-31 | 2018 | Air Force Active | BIKF180001 |  | 2018-05-02 | 2018-12-06 | Iceland Prime Contractor, LTD | N6247018R4005 | 14146220 | 14146220 | 2021-10-20 | 2021-02-13
2023-01-31 | 2020 | Air Force Active | BIKF190001 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 19776676 | 19776676 | 2023-07-14 | 2023-07-14
2023-01-31 | 2020 | Air Force Active | BIKF190002 |  | 2019-11-15 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 4671392 | 4671392 | 2023-07-14 | 2023-07-14
2023-01-31 | 2020 | Air Force Active | BIKF190003 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 14404448 | 14404448 | 2023-07-14 | 2023-07-14
2023-01-31 | 2017 | Air Force Active | CADJ170001 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 3194454 | 3410296 | 2020-02-06 | 2022-01-27
2023-01-31 | 2017 | Air Force Active | CADJ170002 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 4911856 | 5442283 | 2020-02-06 | 2022-04-11
2023-01-31 | 2018 | Air Force Active | CRWU093002 |  | 2018-01-26 | 2018-12-18 | Mortenson | W9128F19C0006 | 34249000 | 35540531 | 2021-04-22 | 2021-12-17
2023-01-31 | 2019 | Air Force Active | CRWU173001 |  | 2020-07-15 | 2020-09-25 | Iron Mike Construction | W9128F20C0048 | 4763991 | 4849127 | 2021-12-12 | 2022-03-01
2023-01-31 | 2018 | Air Force Active | CZQZ143001 |  | 2021-07-27 | 2022-07-01 | Hensel Phelps Construction Co | W912PP22C0008 | 47905000 | 47905000 | 2024-06-24 | 2024-06-24
2023-01-31 | 2017 | Air Force Active | DHAF152900 |  | 2019-04-01 | 2019-09-06 | Amana Contracting & Steel Building Co. WLL, Abu Dhabi UAE | W912ER19C0015 | 25152460 | 25711559 | 2021-10-15 | 2022-10-15
2023-01-31 | 2017 | Air Force Active | DXEB053005 |  | 2018-01-17 | 2018-04-30 | Bethel-Unit JV | W911KB18C0006 | 19278001 | 20209919 | 2020-07-06 | 2021-10-01
2023-01-31 | 2017 | Air Force Active | EEEI150006 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB15D0029 | 1451631 | 1451631 | 2024-04-10 | 2024-04-10
2023-01-31 | 2018 | Air Force Active | EEEI180001 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB15D0029 | 1210326 | 1210326 | 2024-04-10 | 2024-04-10
2023-01-31 | 2020 | Air Force Active | EEPZ1073283 |  | 2021-04-21 | 2021-07-21 | ESA South, Inc | W9127821C0022 | 4798123 | 4798123 | 2022-12-08 | 2022-12-08
2023-01-31 | 2017 | Air Force Active | EPPW170003 |  | 2017-07-14 | 2017-09-21 | Wolff & Mueller & Erbud JV | W912GB15D0060 | 2463632 | 2463632 | 2020-03-26 | 2021-01-27
2023-01-31 | 2020 | Air Force Active | EPPW190001 |  | 2020-12-30 | 2021-09-29 | HATCON INSAAT TAAHHUT ITHALAT IHRACAT LI | W912GB21C0031 | 17039500 | 17039500 | 2027-11-20 | 2027-11-20
2023-01-31 | 2017 | Air Force Active | EVKP174535 |  | 2020-06-12 | 2021-06-25 | Nishimatsu Construction Co. | W912HV21C0001 | 79714176 | 79714176 | 2024-08-31 | 2024-08-31
2023-01-31 | 2019 | Air Force Active | FBNV033002 |  | 2019-07-17 | 2019-09-28 | Inc BFL Construction CO | W912PL19C0035 | 10792977 | 11253033 | 2021-06-02 | 2022-11-10
2023-01-31 | 2017 | Air Force Active | FBNV163001 |  | 2019-04-12 | 2020-01-17 | LLC Chase, Carson & White | W912PL20C0008 | 3387810 | 3387810 | 2021-04-09 | 2021-07-12
2023-01-31 | 2017 | Air Force Active | FJXT133000 |  | 2019-02-19 | 2020-03-31 | CNS Archer Western Federal JV | W912BU20C0015 | 41247000 | 42969988 | 2021-12-25 | 2023-09-19
2023-01-31 | 2016 | Air Force Active | FNWZ100071A |  | 2018-07-11 | 2018-08-08 | Basecom Construction Services | W9126G18C0049 | 4400848 | 4400848 | 2019-09-09 | 2099-12-31
2023-01-31 | 2017 | Air Force Active | FSPM053503C |  | 2017-06-17 | 2018-05-22 | I.E. Pacific, INC | W912PL18C0024 | 22414000 | 22641924 | 2020-06-18 | 2021-07-15
2023-01-31 | 2021 | Air Force Active | FSPM1075894 |  | 2021-05-04 | 2021-09-28 | KORTE CONSTRUCTION COMPANY | W912PL21C0028 | 36405855 | 39663987 | 2024-05-26 | 2024-05-26
2023-01-31 | 2019 | Air Force Active | FSPM173504 |  | 2020-01-31 | 2020-08-06 | Korte Company | W912PL20C0030 | 38397321 | 38397321 | 2022-08-09 | 2022-09-09
2023-01-31 | 2017 | Air Force Active | FTFA033003 |  | 2017-07-25 | 2017-09-30 | The Green-Simmons Company, Inc | W9127816D0016 | 12034000 | 12372639 | 2019-07-23 | 2021-02-11
2023-01-31 | 2017 | Air Force Active | FTFA043000 |  | 2018-09-12 | 2019-03-15 | Hensel Phelps | W9127819C0006 | 59456363 | 62466927 | 2021-09-20 | 2022-04-22
2023-01-31 | 2017 | Air Force Active | FTFA053017 |  | 2019-05-20 | 2019-09-30 | CNS Source Selection Sensitive | W9127819C0034 | 43336911 | 43336911 | 2021-11-05 | 2022-08-29
2023-01-31 | 2019 | Air Force Active | FTFA093965 |  | 2018-11-19 | 2019-03-21 | Whitesell-Green | W9127819C0012 | 26376465 | 27720472 | 2021-05-01 | 2022-01-18
2023-01-31 | 2017 | Air Force Active | FTFA133002 |  | 2020-11-12 | 2021-04-21 | CNS EMR, Inc | W9127816D0035 | 3941080 | 3941080 | 2022-02-15 | 2022-10-30
2023-01-31 | 2019 | Air Force Active | FTFA133003 |  | 2019-08-01 | 2020-06-25 | Leebcor Services, LLC | W9127820F0227 | 1833698 | 1941189 | 2021-04-13 | 2021-04-13
2023-01-31 | 2019 | Air Force Active | FTFA143913 |  | 2018-12-10 | 2019-04-25 | Korte Construction | W9127819C0013 | 31295038 | 32396355 | 2021-06-10 | 2021-07-30
2023-01-31 | 2018 | Air Force Active | FTFA163003 |  | 2018-06-28 | 2018-09-28 | Speegle Constrcution, Inc | W9127818C0026 | 8007902 | 8063384 | 2020-08-22 | 2021-07-15
2023-01-31 | 2018 | Air Force Active | FTFA163004 |  | 2019-05-21 | 2019-08-15 | Lord & Son Construction, Inc | W9127819C0023 | 32128489 | 37010381 | 2021-10-14 | 2023-04-28
2023-01-31 | 2019 | Air Force Active | FTFA163007 |  | 2020-05-31 | 2020-09-29 | Hensel Phelps Construction Co | W9127820C0033 | 28587000 | 32362061 | 2022-10-31 | 2023-04-18
2023-01-31 | 2019 | Air Force Active | FTQW1053834 |  | 2019-01-03 | 2019-07-18 | CNS Ames 1/Conam JV | W911KB19R0008 | 7608922 | 8989456 | 2021-03-10 | 2022-12-31
2023-01-31 | 2019 | Air Force Active | FTQW1054329 |  | 2019-06-07 | 2019-09-30 | CNS ASRC Builders, LLC | W911KB19C0030 | 12795968 | 14546469 | 2021-08-02 | 2022-08-15
2023-01-31 | 2020 | Air Force Active | FTQW1055646 |  | 2020-08-11 | 2021-09-02 | Bristol Site Constructors LLC | W911KB21C0031 | 15504182 | 15504182 | 2024-04-16 | 2024-07-13
2023-01-31 | 2017 | Air Force Active | FTQW170100 |  | 2021-05-31 | 2021-06-30 | Bethel Environmental Solutions LLC | W911KB21F0085 | 15588 | 15588 | 2021-08-14 | 2021-08-14
2023-01-31 | 2018 | Air Force Active | FTQW180107 |  | 2017-09-29 | 2018-03-23 | Bethel Environmental Solutions LLC | W911KB21F0085 | 20024777 | 25141378 | 2020-08-14 | 2022-12-31
2023-01-31 | 2019 | Air Force Active | FTQW180109 |  | 2018-09-27 | 2019-02-28 | GHEMM Company, Inc | W911KB19C0013 | 19794920 | 20495551 | 2020-08-01 | 2020-09-24
2023-01-31 | 2019 | Air Force Active | FTQW180110 |  | 2021-05-27 | 2021-09-08 | CNS Callahan-Watterson JV (CWJV) | W911KB21C0031 | 9446802 | 9640665 | 2023-01-09 | 2023-02-26
2023-01-31 | 2017 | Air Force Active | FTQW183001 |  | 2021-05-31 | 2021-06-30 | Bethel Environmental Solutions LLC | W911KB21F0085 | 31412 | 31412 | 2021-08-14 | 2023-02-26
2023-01-31 | 2021 | Air Force Active | FXBM1081508 |  | 2021-03-24 | 2021-09-17 | LLC Walsh Federal | W9128F21C0045 | 8642600 | 89578019 | 2024-11-01 | 2024-11-01
2023-01-31 | 2022 | Air Force Active | FXBM1088018 |  | 2021-10-22 | 2022-06-30 | Federal Contracting, Inc. | W9128F22C0025 | 92367302 | 92336520 | 2024-10-20 | 2024-10-20
2023-01-31 | 2022 | Air Force Active | FXBM1088037 |  | 2021-10-22 | 2022-06-30 | Federal Contracting, Inc. | W9128F22C0025 | 44298142 | 92336520 | 2024-10-20 | 2024-10-20
2023-01-31 | 2022 | Air Force Active | FXSB143004 |  | 2021-11-10 | 2022-07-22 | Not Listed | W911KB22C0012 | 73621226 | 73621226 | 2099-12-31 | 2099-12-31
2023-01-31 | 2017 | Air Force Active | FXSB982839 |  | 2016-10-20 | 2020-04-01 | CNS Unit Company | W911KB20C008 | 45648623 | 48481426 | 2022-03-17 | 2024-10-30
2023-01-31 | 2017 | Air Force Active | GHLN083004 |  | 2017-05-16 | 2017-06-15 | W9128F16R0011 | W9128F16D00550001 | 5129267 | 5129267 | 2019-01-06 | 2020-08-06
2023-01-31 | 2016 | Air Force Active | GHLN153001 |  | 2017-05-11 | 2018-12-07 | CNS Source Selection Sensitive | W9128F19C0005 | 145720840 | 158751165 | 2022-06-04 | 2023-01-06
2023-01-31 | 2018 | Air Force Active | GHLN983001A |  | 2021-07-30 | 2022-09-16 | Conti Federal Services, LLC | W9128F22C0029 | 124733987 | 124733987 | 2025-04-21 | 2025-04-21
2023-01-31 | 2017 | Air Force Active | GJKZ040009 |  | 2018-08-10 | 2018-12-28 | GARCO Construction | W912DW19C0002 | 23481000 | 29745710 | 2021-01-22 | 2022-04-08
2023-01-31 | 2019 | Air Force Active | GJLK1053425 |  | 2020-05-29 | 2020-09-24 | TSS-Garco JV | W912DW20C0015 | 12230000 | 12323030 | 2022-10-10 | 2022-12-29
2023-01-31 | 2020 | Air Force Active | GLEN203001 |  | 2021-03-23 | 2021-09-01 | Hensel Phelps | W9128F21C0041 | 121968000 | 127486482 | 2025-01-31 | 2025-03-15
2023-01-31 | 2020 | Air Force Active | JFSD201120 |  | 2021-03-20 | 2021-07-29 | Pro-Mark Services | W9128F21C0042 | 4807447 | 4807447 | 2021-08-28 | 2023-01-14
2023-01-31 | 2018 | Air Force Active | KELL123018 |  | 2020-07-31 | 2022-09-26 | Not Listed | W9999999999999 | 20303238 | 20303238 | 2099-12-31 | 2099-12-31
2023-01-31 | 2016 | Air Force Active | KNMD043004 |  | 2018-02-01 | 2018-09-29 | Nordic PCL Construction | W9128A18C0009 | 41476374 | 44495875 | 2020-10-22 | 2021-10-29
2023-01-31 | 2020 | Air Force Active | KRSM1065068 |  | 2020-06-27 | 2020-07-27 | Hensel Phelps Construction Co | W9123820C0012 | 92101014 | 95471587 | 2023-04-13 | 2023-06-03
2023-01-31 | 2021 | Air Force Active | KRSM1071882 |  | 2021-10-08 | 2022-06-28 | Not Listed | W9999999999999 | 40011650 | 40011650 | 2099-12-31 | 2099-12-31
2023-01-31 | 2017 | Air Force Active | KRSM113031 |  | 2020-06-16 | 2020-12-30 | The Povolny Group Inc | W9123821C0007 | 3892900 | 3892900 | 2022-01-19 | 2022-08-21
2023-01-31 | 2018 | Air Force Active | KRSM123009 |  | 2020-09-24 | 2021-03-09 | CNS HHI Corporation | W9123821C0013 | 22229812 | 23004315 | 2023-07-24 | 2022-12-26
2023-01-31 | 2017 | Air Force Active | KRSM143003 |  | 2018-02-09 | 2018-09-28 | Northern Construction, LLC | W9123818C0049 | 8958380 | 9367284 | 2020-10-17 | 2021-11-15
2023-01-31 | 2020 | Air Force Active | KRSM183001 |  | 2021-03-23 | 2021-07-28 | NVE-HHI JV | W9123821C0019 | 6319659 | 6310611 | 2023-08-15 | 2023-08-15
2023-01-31 | 2020 | Air Force Active | KWRD1055707 |  | 2021-03-01 | 2021-07-09 | W912PP21C0012 | W912PP21C0012 | 12949000 | 12959957 | 2023-04-09 | 2023-10-06
2023-01-31 | 2018 | Air Force Active | KWRD143000 |  | 2018-08-22 | 2019-10-31 | RPA Fixed Ground Control Station | W912PP19C0019 | 4963246 | 4963246 | 2020-11-29 | 2021-10-25
2023-01-31 | 2017 | Air Force Active | LBPG150008 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB17F0444 | 1611283 | 1611283 | 2021-01-21 | 2024-03-19
2023-01-31 | 2017 | Air Force Active | LBPG150009 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB17F0461 | 1978602 | 1978602 | 2022-02-11 | 2024-05-17
2023-01-31 | 2017 | Air Force Active | LJYC133003 |  | 2017-11-08 | 2018-05-01 | Aytekin Serol Insaat Taan | W912GB18C0013 | 10199660 | 10762014 | 2021-05-16 | 2023-11-20
2023-01-31 | 2018 | Air Force Active | LJYC183004 |  | 2018-08-29 | 2019-05-13 | EMTA INSAAT TAAHHUT VE TICARET ANONIUM SI | W912GB19F0076 | 3795142 | 3795142 | 2021-09-28 | 2023-06-07
2023-01-31 | 2019 | Air Force Active | LKTC203101 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL19C0028 | 25007200 | 52482897 | 2021-10-02 | 2022-05-23
2023-01-31 | 2019 | Air Force Active | LKTC203102 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL19C0028 | 49660100 | 52482897 | 2021-11-02 | 2022-05-23
2023-01-31 | 2017 | Air Force Active | LRCT150007 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2575083 | 2575083 | 2020-03-12 | 2023-02-01
2023-01-31 | 2017 | Air Force Active | LRCT150008 |  | 2017-07-28 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0021 | 1711902 | 1711902 | 2020-02-01 | 2021-12-14
2023-01-31 | 2017 | Air Force Active | LRCT150009 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2356785 | 2356785 | 2020-03-12 | 2022-09-15
2023-01-31 | 2017 | Air Force Active | LRCT150010 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2021357 | 2021357 | 2022-06-15 | 2023-02-01
2023-01-31 | 2021 | Air Force Active | LRCT190001 |  | 2021-03-08 | 2021-06-04 | Eiffage Infraestructura SA | W912GB21D0019 | 10852364 | 10852364 | 2023-11-06 | 2023-08-16
2023-01-31 | 2021 | Air Force Active | LRCT190002 |  | 2021-06-23 | 2021-09-16 | Relyant Global LLC | W912GB21F0202 | 27388762 | 27388762 | 2024-11-04 | 2024-11-04
2023-01-31 | 2021 | Air Force Active | LRCT210001 |  | 2021-03-17 | 2021-08-09 | Tepe Bozdemir Joint Venture | W912GB21C0022 | 44485900 | 44485900 | 2024-03-09 | 2024-03-09
2023-01-31 | 2021 | Air Force Active | LRCT210002 |  | 2020-10-26 | 2021-09-21 | Sociedad Espanola De Montajes Industrial (SEMI) | W912GB21D0021 | 12163399 | 12344791 | 2023-11-23 | 2024-04-30
2023-01-31 | 2016 | Air Force Active | LXEZ154288 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV16D0009 | 34988795 | 34988795 | 2021-01-14 | 2023-01-30
2023-01-31 | 2016 | Air Force Active | LXEZ164289 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV16D0009 | 27745871 | 27745871 | 2021-01-14 | 2023-01-30
2023-01-31 | 2018 | Air Force Active | LXEZ183486 |  | 2021-01-05 | 2021-07-13 | CNS Maeda-Onaka Joint Venture | FA527021F0092 | 2082263 | 2082263 | 2022-12-07 | 2022-12-10
2023-01-31 | 2018 | Air Force Active | LXEZ184546 |  | 2019-11-27 | 2020-05-18 | Kyowa Exeo Corporation | W912HV20B00010004 | 55457702 | 55457702 | 2022-12-30 | 2023-02-28
2023-01-31 | 2019 | Air Force Active | LXEZ194643 |  | 2021-05-03 | 2022-09-23 | NIPPO CORPORATION | W912HV22C0014 | 99652251 | 99652251 | 2025-10-22 | 2025-10-22
2023-01-31 | 2017 | Air Force Active | LXFB123876 |  | 2021-11-01 | 2022-07-13 | TODA-AEC JV | W912HV22C0008 | 23860272 | 23860272 | 2024-08-11 | 2024-08-11
2023-01-31 | 2017 | Air Force Active | MAHG173002 |  | 2019-05-22 | 2020-05-28 | U-SMC/DeMaria JV, LLC | N6945019D0921 | 3591891 | 3591891 | 2023-03-26 | 2023-03-26
2023-01-31 | 2017 | Air Force Active | MAHG173003 |  | 2019-06-12 | 2020-05-28 | TU-SMC/DeMaria JV, LLC | N6945019D0921 | 4007591 | 4007591 | 2023-03-26 | 2023-03-26
2023-01-31 | 2017 | Air Force Active | MHMV053107 |  | 2020-10-30 | 2021-04-06 | QA Engineering, LLC | W912PP19D0035 | 2855784 | 2855784 | 2022-07-11 | 2022-11-05
2023-01-31 | 2018 | Air Force Active | MHMV083126A |  | 2020-08-14 | 2020-11-10 | Encanto Facillity Services 2 | W912PP19D0037 | 8427275 | 8427275 | 2022-03-01 | 2023-02-24
2023-01-31 | 2022 | Air Force Active | MHMV180068 |  | 2022-02-25 | 2022-07-07 | Not Listed | W9999999999999 | 4212029 | 4212029 | 2099-12-31 | 2099-12-31
2023-01-31 | 2016 | Air Force Active | MPLS083737R5 |  | 2017-12-01 | 2019-06-26 | CNS Source Selection Sensitive | W9126G19C0035 | 5546178 | 5667402 | 2020-05-23 | 2020-07-29
2023-01-31 | 2017 | Air Force Active | MPLS083737R6 |  | 2019-01-22 | 2019-09-26 | DA-CA USACE | W9126G19C0023 | 96449882 | 98361617 | 2022-10-27 | 2023-04-27
2023-01-31 | 2016 | Air Force Active | MPLS083737S3 |  | 2017-12-01 | 2019-01-16 | CNS Source Selection Sensitive | W9126G19C0001 | 52357846 | 94728610 | 2021-09-04 | 2023-08-25
2023-01-31 | 2016 | Air Force Active | MPLS113003A |  | 2018-11-30 | 2019-03-01 | Express Contracting | W9126G19C0019 | 2872000 | 2872000 | 2020-06-30 | 2021-06-03
2023-01-31 | 2015 | Air Force Active | MPLS3274JB |  | 2015-02-17 | 2015-06-03 | Solis Constructors, Inc. | W9126G14D00500002 | 6077000 | 6133616 | 2016-08-31 | 2021-06-03
2023-01-31 | 2020 | Air Force Active | MPYJ043895A |  | 2021-03-23 | 2021-06-25 | Clark/Byrne Aquatics, JV | W9126G21C0012 | 58950000 | 59820789 | 2023-04-24 | 2023-09-21
2023-01-31 | 2019 | Air Force Active | MSBL103000 |  | 2021-02-19 | 2021-09-29 | Ranco Construction | W912DS21C0021 | 9138000 | 9138000 | 2023-05-16 | 2023-09-19
2023-01-31 | 2018 | Air Force Active | MSET143006 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 55113676 | 55113676 | 2023-03-29 | 2024-02-05
2023-01-31 | 2018 | Air Force Active | MSET153501 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 23292923 | 23292923 | 2021-10-05 | 2022-08-24
2023-01-31 | 2019 | Air Force Active | MSET153503 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 22219318 | 22219318 | 2024-01-21 | 2024-01-21
2023-01-31 | 2019 | Air Force Active | MSET153504 |  | 2018-05-14 | 2018-11-14 | KVF35 | DIOCB2076 | 33031258 | 33031258 | 2022-02-28 | 2022-02-28
2023-01-31 | 2019 | Air Force Active | MSET153505 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 11543865 | 11543865 | 2022-07-04 | 2022-07-04
2023-01-31 | 2018 | Air Force Active | MSET153506 |  | 2018-06-04 | 2020-09-14 | KVF 35 | DIOCB2076 | 16724478 | 16724478 | 2022-12-21 | 2023-04-24
2023-01-31 | 2019 | Air Force Active | MSET153508 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 36198139 | 36198139 | 2024-01-21 | 2024-01-21
2023-01-31 | 2018 | Air Force Active | MSET153509 |  | 2018-06-08 | 2019-04-10 | KVF 35 | DIOCB2076 | 6211718 | 6211718 | 2027-06-17 | 2027-06-17
2023-01-31 | 2018 | Air Force Active | MSET153513 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 22251003 | 22251003 | 2023-09-30 | 2023-09-30
2023-01-31 | 2018 | Air Force Active | MSET153514 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 39101561 | 39101561 | 2025-07-23 | 2025-07-23
2023-01-31 | 2017 | Air Force Active | MUHJ133000 |  | 2020-11-03 | 2021-05-11 | Source Selection Sensitive | W9123621C2005 | 46375000 | 45813748 | 2023-06-09 | 2023-09-07
2023-01-31 | 2019 | Air Force Active | MUHJ193002 |  | 2022-05-27 | 2022-07-28 | WALSH FEDERAL, LLC | W9123622C2003 | 55423000 | 55423000 | 2024-10-17 | 2024-10-17
2023-01-31 | 2019 | Air Force Active | MUHJ193004 |  | 2021-12-23 | 2022-06-10 | Balfour Beatty Construction, LLC | W9123622C2023 | 75056068 | 75985814 | 2024-08-15 | 2024-08-15
2023-01-31 | 2017 | Air Force Active | MXRD083000 |  | 2022-01-12 | 2022-02-11 | J & J | W912WJ22C0005 | 16107000 | 16107000 | 2023-09-12 | 2024-04-20
2023-01-31 | 2019 | Air Force Active | MXRD153006 |  | 2021-03-23 | 2021-12-31 | Gilbane-Exyte JV | W912WJ22C0002 | 276858421 | 276858421 | 2020-05-17 | 2024-11-22
2023-01-31 | 2020 | Air Force Active | NKAK123007 |  | 2020-05-15 | 2020-08-31 | CNS RCO Ross Group JV | W9127S20C6006 | 35396600 | 35982182 | 2022-10-15 | 2023-06-01
2023-01-31 | 2018 | Air Force Active | NKAK153001 |  | 2020-04-09 | 2021-08-31 | LS Black Loeffel Construction, JV | W9127S21C6004 | 28147259 | 28471862 | 2023-04-13 | 2023-11-13
2023-01-31 | 2021 | Air Force Active | NKAK193001 |  | 2021-09-21 | 2021-10-21 | CNS Source Selection Sensitive | FA446017D0005 | 1491000 | 1491000 | 2022-11-20 | 2022-11-20
2023-01-31 | 2016 | Air Force Active | NUEX093016 |  | 2017-10-04 | 2018-02-01 | Okland Construction, Co. Inc. | W912PL18C0013 | 16223496 | 16566800 | 2020-02-26 | 2021-07-27
2023-01-31 | 2020 | Air Force Active | NUEX1009271 |  | 2022-06-10 | 2022-09-30 | KWR Construction, Inc. | W912PL22C0040 | 4485163 | 4740817 | 2023-08-11 | 2023-08-11
2023-01-31 | 2019 | Air Force Active | NVZR153710 |  | 2019-08-09 | 2020-02-26 | HCR | W9127820C0010 | 3351127 | 3351127 | 2021-06-18 | 2021-12-30
2023-01-31 | 2018 | Air Force Active | NVZR153711 |  | 2019-07-17 | 2019-09-26 | Southeast Cherokee Constr. Inc | W9127816D0015 | 8163765 | 8323242 | 2021-05-11 | 2021-08-27
2023-01-31 | 2016 | Air Force Active | NZAS043002 |  | 2019-05-06 | 2019-06-05 | DA-CA USACE | W912DW19C008 | 19868428 | 19868428 | 2020-12-26 | 2020-08-31
2023-01-31 | 2017 | Air Force Active | NZAS173001 |  | 2018-06-01 | 2019-06-05 | CNS Source Selection Sensitive | W912DW19C0008 | 18688440 | 18981055 | 2021-05-15 | 2021-09-17
2023-01-31 | 2017 | Air Force Active | PAF150400 |  | 2017-11-21 | 2018-05-18 | AECOM | N6274218C1314 | 24132780 | 33953429 | 2019-11-15 | 2021-10-29
2023-01-31 | 2018 | Air Force Active | PAF160600 |  | 2019-05-07 | 2019-09-26 | Nova Nacap JV | N6274219C1316 | 66955722 | 66955722 | 2022-10-25 | 2023-06-01
2023-01-31 | 2020 | Air Force Active | PAF180200 |  | 2020-11-24 | 2022-05-05 | Nova Nacap | N6274222C1314 | 86116647 | 86116647 | 2025-02-13 | 2025-06-20
2023-01-31 | 2020 | Air Force Active | PAF180300 |  | 2019-12-05 | 2020-05-28 | ICON SI (Aust) Pty Ltd | N6274220C1303 | 10310997 | 11463922 | 2022-02-03 | 2022-05-24
2023-01-31 | 2020 | Air Force Active | PAF189021 |  | 2020-06-12 | 2021-11-30 | Black Micro Corporation / Tamuning / Guam | N6274222C1318 | 90331063 | 90331063 | 2025-11-15 | 2025-11-15
2023-01-31 | 2020 | Air Force Active | PAF189022 |  | 2020-06-12 | 2021-11-30 | Black Micro Corporation / Tamuning / Guam | N6274222C1318 | 84957202 | 84957202 | 2025-11-15 | 2025-11-15
2023-01-31 | 2015 | Air Force Active | PAYZ15001B |  | 2016-06-18 | 2016-11-29 | Vilmanto Statybos | W912GB15D00560002 | 1515821 | 1515821 | 2018-07-07 | 2021-08-03
2023-01-31 | 2015 | Air Force Active | PAYZ15001C |  | 2016-08-01 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00410003 | 4479631 | 4479631 | 2018-07-06 | 2021-05-04
2023-01-31 | 2015 | Air Force Active | PAYZ15001H |  | 2017-03-08 | 2017-09-22 | Cimolai S.p.A | N6247017C5002 | 27192353 | 37466344 | 2020-08-30 | 2023-08-18
2023-01-31 | 2016 | Air Force Active | PAYZ16000B |  | 2020-03-31 | 2020-08-19 | Onaka Gumi Co., Ltd. | W912HV20C0006 | 2413198 | 2428538 | 2021-09-07 | 2021-12-22
2023-01-31 | 2017 | Air Force Active | PNQS072140 |  | 2018-12-14 | 2019-05-08 | Southeast Cherokee | W9127819C0017 | 13341000 | 17161802 | 2020-12-31 | 2021-09-13
2023-01-31 | 2019 | Air Force Active | PNQS103165 |  | 2019-07-16 | 2019-09-30 | Bear Brothers, INC | W9127819C0037 | 12768107 | 13046214 | 2021-05-26 | 2021-12-10
2023-01-31 | 2018 | Air Force Active | PRQE055155 |  | 2018-05-25 | 2018-09-28 | McConnell COMBAT ARMS FACILITY | W912DQ18C4051 | 14796430 | 15284242 | 2020-07-05 | 2020-10-15
2023-01-31 | 2021 | Air Force Active | PTFL023003 |  | 2021-11-05 | 2022-08-02 | Benaska, Inc | W912DS22C0004 | 25517551 | 23992000 | 2099-12-31 | 2024-10-30
2023-01-31 | 2015 | Air Force Active | PTFL106002 |  | 2019-04-20 | 2019-07-19 | Sun Construction Services, Inc. | W912DS19C0012 | 1910502 | 1910502 | 2020-12-20 | 2021-02-19
2023-01-31 | 2018 | Air Force Active | PTFL163001 |  | 2018-08-17 | 2019-02-27 | RANCO CONSTRUCTION INC | W912DS19C0005 | 4427200 | 4587349 | 2021-11-03 | 2021-08-17
2023-01-31 | 2018 | Air Force Active | PTFL163006 |  | 2018-08-24 | 2018-09-28 | Sun Construction Services Inc. | W912DS18C0027 | 3159200 | 3307588 | 2019-11-09 | 2019-12-30
2023-01-31 | 2018 | Air Force Active | PTFL163010 |  | 2019-06-12 | 2019-09-25 | TDX Quality | W912DS19C0022 | 8602603 | 11479491 | 2021-05-07 | 2023-02-17
2023-01-31 | 2018 | Air Force Active | PTFL163019 |  | 2018-11-02 | 2019-07-11 | Walsh Federal LLC | W912DS19C0011 | 52324000 | 53764450 | 2021-07-23 | 2023-03-31
2023-01-31 | 2018 | Air Force Active | QJVF012005 |  | 2019-01-25 | 2019-05-29 | CNS Source Selection Sensitive | W9128F18C0026 | 24993526 | 24993526 | 2021-02-15 | 2021-12-17
2023-01-31 | 2020 | Air Force Active | QJVF1058361 |  | 2021-09-30 | 2021-12-28 | Razor Consulting Solutions, INC. | W9128F22C0007 | 5022459 | 5022459 | 2023-08-25 | 2023-08-25
2023-01-31 | 2022 | Air Force Active | QKKA1074664 |  | 2021-10-14 | 2022-06-30 | ITOGUMI CONSTRUCTION CO., LTD. | W912HV22C0007 | 14419495 | 14419495 | 2024-07-03 | 2024-04-19
2023-01-31 | 2017 | Air Force Active | QSEU083023 |  | 2020-06-23 | 2020-09-03 | McKnight Construction | W912HN20C3007 | 23471929 | 23471929 | 2023-05-03 | 2023-05-03
2023-01-31 | 2017 | Air Force Active | QUUG064001 |  | 2019-04-17 | 2021-09-28 | Sociedad Espanola de Montajes | FA557521C0007 | 1336116 | 1336116 | 2022-12-19 | 2023-04-30
2023-01-31 | 2018 | Air Force Active | RKMF063004 |  | 2018-08-16 | 2019-07-03 | Record Steel and Construction, Inc., dba RSCI | W912PL19C0023 | 21623000 | 22329968 | 2021-08-02 | 2022-04-22
2023-01-31 | 2016 | Air Force Active | RKMF103011 |  | 2018-01-18 | 2019-12-17 | BRISTOL | W912PL20C0007 | 4938791 | 5243992 | 2021-08-22 | 2021-10-16
2023-01-31 | 2019 | Air Force Active | RKMF123009 |  | 2019-04-17 | 2019-08-27 | GUARDIAN/EC JV LLC | W912PL19C0024 | 5555674 | 5822833 | 2021-06-02 | 2022-10-31
2023-01-31 | 2020 | Air Force Active | RKMF163007 |  | 2020-07-23 | 2020-09-30 | KORTE | W912PL20C0021 | 36685652 | 37627322 | 2022-12-28 | 2023-08-31
2023-01-31 | 2018 | Air Force Active | RKMF173010 |  | 2019-03-04 | 2019-10-02 | Bristol Prime Contractors, LLC | W912PL20C0001 | 3698666 | 4146204 | 2020-11-11 | 2022-09-30
2023-01-31 | 2020 | Air Force Active | RKMF203001 |  | 2020-06-15 | 2020-09-16 | GUARDIAN | W912PL20C0035 | 5659450 | 5741472 | 2021-12-01 | 2022-07-03
2023-01-31 | 2019 | Air Force Active | RKMF203007 |  | 2020-03-13 | 2020-06-19 | Record Steel and Construction, Inc., dba RsCI | W912PL20C0018 | 27554000 | 27554000 | 2022-07-24 | 2022-11-16
2023-01-31 | 2019 | Air Force Active | SGBP1047602 |  | 2019-03-18 | 2019-05-20 | CNS Sapper Construction | W9128F19C0023 | 8623365 | 8671865 | 2019-06-19 | 2020-08-21
2023-01-31 | 2019 | Air Force Active | SGBP212902 |  | 2021-08-24 | 2021-09-24 | Medvolt Construction Services, LLC | W9128F21C0059 | 13893550 | 13893550 | 2023-04-07 | 2023-04-07
2023-01-31 | 2019 | Air Force Active | SGBP212903 |  | 2021-08-24 | 2021-09-24 | Medvolt Construction Services, LLC | W9128F21C0059 | 54480535 | 31998474 | 2023-04-07 | 2023-04-07
2023-01-31 | 2020 | Air Force Active | SGBP212904 |  | 2021-08-02 | 2021-09-29 | Medvolt-Komada JV | W9128F21C0066 | 17521500 | 17857100 | 2023-03-22 | 2023-03-22
2023-01-31 | 2020 | Air Force Active | SGBP212905 |  | 2021-12-27 | 2022-06-30 | M. A. Mortenson Company | W9128F22C0027 | 68459000 | 68515752 | 2024-11-19 | 2024-11-19
2023-01-31 | 2020 | Air Force Active | SGBP212907 |  | 2021-06-29 | 2021-12-15 | FSA Construction LLC | W9128F22C0006 | 12851627 | 13637749 | 2023-10-28 | 2023-12-10
2023-01-31 | 2020 | Air Force Active | SGBP212908 |  | 2021-03-18 | 2021-09-15 | Covenant Russell LLC | W9128F21C0056 | 3736863 | 3751924 | 2023-03-29 | 2023-04-28
2023-01-31 | 2019 | Air Force Active | SMYU073011 |  | 2019-06-27 | 2019-09-27 | Kumsung Construction Co., Ltd | W912UM19C0017 | 1227670 | 1227670 | 2021-02-21 | 2021-08-30
2023-01-31 | 2017 | Air Force Active | SXHT013001 |  | 2017-02-17 | 2017-06-02 | LEEBC O R SER VIC ES, LLC | W9127816D0033 | 12383350 | 12509795 | 2019-03-12 | 2021-01-15
2023-01-31 | 2019 | Air Force Active | SXHT023007 |  | 2021-02-15 | 2022-04-26 | EMR Inc | W9127822C0016 | 12265000 | 12967000 | 2023-12-22 | 2023-12-22
2023-01-31 | 2018 | Air Force Active | TDKA063002D |  | 2018-11-07 | 2019-08-16 | JE Hurley Inc | W9128F19R0006 | 3888005 | 3934966 | 2020-12-02 | 2020-12-28
2023-01-31 | 2020 | Air Force Active | TDKA143002 |  | 2020-10-06 | 2021-04-27 | JE Dunn | W9128F21C0019 | 43789430 | 50909204 | 2023-09-11 | 2023-10-04
2023-01-31 | 2012 | Air Force Active | TYFR063017 |  | 2012-03-01 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541693 | 29662433 | 2017-01-18 | 2026-06-18
2023-01-31 | 2021 | Air Force Active | TYFR203027 |  | 2021-07-13 | 2021-09-16 | Not Listed | W9999999999999 | 33320586 | 33320586 | 2099-12-31 | 2099-12-31
2023-01-31 | 2020 | Air Force Active | TYMX103001 |  | 2021-02-23 | 2021-07-22 | Joeris General Contractors, Ltd | W9126G21C0016 | 27589000 | 28049731 | 2023-03-11 | 2023-03-30
2023-01-31 | 2018 | Air Force Active | UHHZ163000 |  | 2018-12-12 | 2020-05-20 | Hensel Phelps, Orlando, FL | W912HN20F4009 | 10827560 | 10827560 | 2021-12-10 | 2021-12-10
2023-01-31 | 2019 | Air Force Active | ULDF123001 |  | 2019-11-15 | 2020-01-17 | FOUR TRIBES ENTERPRISES, LLC | W912DS20C0005 | 13147968 | 15394125 | 2021-08-03 | 2022-11-12
2023-01-31 | 2017 | Air Force Active | VDYD101053 |  | 2020-02-24 | 2020-07-29 | River City Construction, LLC/East Peoria IL | W912QR20C0028 | 30100000 | 30100000 | 2023-03-08 | 2024-01-10
2023-01-31 | 2020 | Air Force Active | VDYD1055428 |  | 2021-03-09 | 2021-07-08 | Zodiac-Poettker HBZ Construction JV | W912QR21C0021 | 72713000 | 79137090 | 2023-08-21 | 2023-10-06
2023-01-31 | 2020 | Air Force Active | VDYD1074289 |  | 2019-08-05 | 2021-04-08 | Litteken Construction Compancy | W912QR21C0005 | 3433700 | 3433700 | 2021-05-08 | 2023-06-26
2023-01-31 | 2016 | Air Force Active | VKAG013004R5 |  | 2017-08-21 | 2019-06-28 | Source Selection Sensitive | W912HN19C3006 | 21823320 | 22433882 | 2021-02-04 | 2021-10-12
2023-01-31 | 2020 | Air Force Active | VKAG193002 |  | 2021-06-30 | 2021-09-28 | Group III Mgt, Inc. | W912HN21C3008 | 4883000 | 4883000 | 2023-02-06 | 2023-02-06
2023-01-31 | 2019 | Air Force Active | VLSB193001 |  | 2020-08-11 | 2020-12-30 | MQ9 MCE Group | N6945021C004 | 49312181 | 49312181 | 2022-12-16 | 2023-03-01
2023-01-31 | 2022 | Air Force Active | VNVP063002 |  | 2021-11-15 | 2022-05-06 | CNS Southwind Construction Services LLC | W912BV22C0012 | 21716833 | 21716833 | 2023-08-04 | 2024-03-01
2023-01-31 | 2021 | Air Force Active | VYHK213002 |  | 2022-09-19 | 2022-09-25 | Not Listed | W9999999999999 | 24020438 | 24020438 | 2099-12-31 | 2099-12-31
2023-01-31 | 2016 | Air Force Active | WWYK093003 |  | 2016-08-31 | 2017-03-13 | Walsh Federal JV (Chicago/IL) | W912BV17C0005 | 12472000 | 13510350 | 2018-11-08 | 2021-04-12
2023-01-31 | 2015 | Air Force Active | WWYK153005 |  | 2016-02-11 | 2017-03-30 | Walsh Federal Alberici JV | W912BV17C0004 | 97939000 | 124484087 | 2019-04-30 | 2021-01-07
2023-01-31 | 2019 | Air Force Active | WWYK153007 |  | 2021-03-31 | 2022-09-29 | Not Listed | W9999999999999 | 21307723 | 21307723 | 2099-12-31 | 2099-12-31
2023-01-31 | 2018 | Air Force Active | WWYK173005 |  | 2020-06-25 | 2020-09-23 | Southwind Construction | W912BV18D0019 | 3899405 | 4667304 | 2021-12-03 | 2022-09-30
2023-01-31 | 2019 | Air Force Active | WWYK193001 |  | 2019-01-29 | 2019-08-29 | Korte | W912BV19C0015 | 63921812 | 65296480 | 2022-03-19 | 2023-04-14
2023-01-31 | 2017 | Air Force Active | WWYK193003 |  | 2018-05-21 | 2019-02-07 | Record Steel and Construction | W912BV19C0002 | 24633000 | 25822548 | 2021-03-04 | 2022-06-15
2023-01-31 | 2019 | Air Force Active | WWYK193014 |  | 2019-01-21 | 2019-09-27 | Korte Const Co | W912BV19C0017 | 72827332 | 73247149 | 2022-03-20 | 2023-03-12
2023-01-31 | 2020 | Air Force Active | WWYK913019 |  | 2022-01-05 | 2022-06-16 | Not Listed | W9999999999999 | 4510463 | 4510463 | 2099-12-31 | 2099-12-31
2023-01-31 | 2020 | Air Force Active | XDAT1026962 |  | 2020-06-20 | 2020-07-16 | J.I. Garcia Construction Inc. Travis AFB KC-46A Alter B881, B885 & B887 Squadron Ops/AMU | N6247318D5817 | 5158710 | 5158710 | 2021-10-09 | 2022-04-30
2023-01-31 | 2020 | Air Force Active | XDAT1030576 |  | 2020-10-13 | 2021-05-06 | COFFMAN SPECIALTIES, INC | N6247913D2439 | 4045000 | 4045000 | 2021-11-12 | 2021-11-12
2023-01-31 | 2020 | Air Force Active | XDAT1046451 |  | 2020-03-27 | 2021-03-15 | Company SOLTEK | N6247321F4392 | 21960000 | 21960000 | 2021-04-14 | 2023-03-10
2023-01-31 | 2018 | Air Force Active | XDAT1051930 |  | 2018-10-26 | 2019-12-30 | LLC Walsh Federal | N6247320C0613 | 129264610 | 129264610 | 2022-06-17 | 2023-02-26
2023-01-31 | 2020 | Air Force Active | XDAT1074510 |  | 2020-08-31 | 2021-09-02 | RA Burch Company | N6246321F5351 | 17000000 | 17000000 | 2021-10-02 | 2023-12-11
2023-01-31 | 2021 | Air Force Active | XDAT173002 |  | 2019-05-12 | 2021-06-30 | Gideon Contracting | N6247319D1222 | 4339865 | 4339865 | 2021-07-30 | 2022-12-19
2023-01-31 | 2020 | Air Force Active | XLWU193004 |  | 2022-03-14 | 2022-04-13 | Howard W Pence Inc | W9127822C0014 | 17373320 | 17373320 | 2024-02-17 | 2024-04-24
2023-01-31 | 2019 | Air Force Active | XLWU193005 |  | 2019-08-12 | 2019-09-23 | Green Simmons Company INC | W9127819F0486 | 12369134 | 12369134 | 2021-11-09 | 2022-12-14
2023-01-31 | 2019 | Air Force Active | XLWU193006 |  | 2019-08-26 | 2019-09-26 | Southeast Cherokee Const INC | W9127810518 | 16624000 | 16614000 | 2021-11-02 | 2022-08-30
2023-01-31 | 2020 | Air Force Active | XLWU203002 |  | 2022-01-30 | 2022-03-31 | EMR, Inc. | W9127822C0010 | 100323520 | 100323520 | 2025-09-27 | 2026-02-06
2023-01-31 | 2020 | Air Force Active | XLWU203004 |  | 2021-07-23 | 2021-11-05 | Hensel Phelps Construction Co | W912HN21D3002 | 129253000 | 129253000 | 2024-08-26 | 2024-08-26
2023-01-31 | 2020 | Air Force Active | XLWU203005 |  | 2022-04-14 | 2022-08-18 | BL Harbert International, LLC | W912HN21D3000 | 87623359 | 47319236 | 2024-11-22 | 2024-10-05
2023-01-31 | 2019 | Air Force Active | XLWU203006 |  | 2020-07-24 | 2020-09-25 | Inc Caddell | W912HN20D3003 | 25994000 | 26255947 | 2022-09-16 | 2023-03-01
2023-01-31 | 2020 | Air Force Active | XLWU203008 |  | 2021-11-19 | 2022-07-12 | BL Harbert International, LLC | W9127822C0012 | 63919543 | 63919543 | 2025-06-09 | 2025-06-09
2023-01-31 | 2020 | Air Force Active | XLWU203009 |  | 2021-11-19 | 2022-07-12 | BL Harbert International, LLC | W9127822C0012 | 100587412 | 63919543 | 2025-06-09 | 2025-06-09
2023-01-31 | 2020 | Air Force Active | XLWU203010 |  | 2021-07-29 | 2022-02-17 | CNS B.L. Harbert International, LLC | W9127822C0004 | 71282998 | 71282998 | 2024-09-30 | 2024-09-30
2023-01-31 | 2020 | Air Force Active | XLWU203011 |  | 2021-05-07 | 2022-02-01 | CNS EMR, Inc | W9127822C0007 | 27568000 | 27561775 | 2024-05-03 | 2024-05-03
2023-01-31 | 2020 | Air Force Active | XLWU203012 |  | 2021-10-25 | 2022-05-25 | The Haskell Company | W9127822C0011 | 43045122 | 43045122 | 2024-07-16 | 2024-07-16
2023-01-31 | 2019 | Air Force Active | XLWU203013 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 78000000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203014 |  | 2022-03-12 | 2022-05-11 | Hensel Phelps | W9127822C0008 | 86610671 | 78000000 | 2025-04-15 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203015 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 70660000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2019 | Air Force Active | XLWU203016 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 47000000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203017 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 34603000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203018 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 36345000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203019 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 35779000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203021 |  | 2021-10-20 | 2022-07-21 | BL Harbert International, LLC | W9127822C0023 | 163143366 | 163143366 | 2025-10-10 | 2025-10-10
2023-01-31 | 2020 | Air Force Active | XLWU203025 |  | 2021-03-31 | 2021-07-12 | CNS Southeastern Industrial Barlovento JV-2, LLC | W9127821C0027 | 6265450 | 6950094 | 2023-03-27 | 2023-05-17
2023-01-31 | 2020 | Air Force Active | XLWU203026 |  | 2022-03-12 | 2022-05-11 | BL Harbert International, LLC | W9127822F0121 | 95169558 | 95169558 | 2024-08-23 | 2025-01-03
2023-01-31 | 2020 | Air Force Active | XLWU203028 |  | 2020-12-11 | 2021-06-25 | BL Harbert International, LLC | W912HN21D3000 | 91500000 | 47319236 | 2024-04-16 | 2024-10-05
2023-01-31 | 2020 | Air Force Active | XLWU203029 |  | 2022-04-14 | 2022-08-18 | Burns & McDonell | W912HN21D3000 | 64825728 | 47319236 | 2099-12-31 | 2024-10-05
2023-01-31 | 2020 | Air Force Active | XLWU203030 |  | 2021-05-06 | 2021-07-28 | Dawson Enterprises, LLC | W9127820R0047 | 35659204 | 35659204 | 2024-04-03 | 2024-04-02
2023-01-31 | 2020 | Air Force Active | XLWU203033 |  | 2021-03-19 | 2021-08-30 | Roundhouse PBN, LLC | W9127821C0028 | 13862809 | 13796239 | 2023-08-23 | 2023-08-23
2023-01-31 | 2020 | Air Force Active | XLWU203034 |  | 2021-07-26 | 2021-09-24 | CNS B.L. Harbert International, LLC | W912HN21D3000 | 22056565 | 47319236 | 2023-09-28 | 2024-10-05
2023-01-31 | 2020 | Air Force Active | XLWU203036 |  | 2021-09-10 | 2022-07-08 | HEALTHEON, INC | W9127822D0047 | 9488700 | 9488700 | 2024-07-04 | 2024-07-04
2023-01-31 | 2020 | Air Force Active | XLWU203038 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 119330000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203040 |  | 2021-02-09 | 2021-08-13 | CNS 4K Global-ACC JV, LLC | W9127821C0029 | 8031188 | 8738524 | 2023-06-26 | 2023-06-26
2023-01-31 | 2019 | Air Force Active | XLWU203041 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 41055000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203043 |  | 2021-11-19 | 2022-07-12 | BL Harbert International, LLC | W9127822C0012 | 16854220 | 63919543 | 2025-06-09 | 2025-06-09
2023-01-31 | 2020 | Air Force Active | XLWU203044 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 35396000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2019 | Air Force Active | XLWU203045 |  | 2021-06-25 | 2022-04-29 | The Lane Construction Corporation | W9127822C0017 | 182766415 | 184052336 | 2026-06-25 | 2026-06-25
2023-01-31 | 2020 | Air Force Active | XLWU203046 |  | 2021-04-28 | 2021-09-08 | CNS EMR, Inc | W9127822C007 | 22097308 | 22097308 | 2023-10-13 | 2024-11-13
2023-01-31 | 2020 | Air Force Active | XLWU203047 |  | 2021-04-30 | 2022-05-10 | Hensel Phelps | W9127822C0008 | 33569000 | 78000000 | 2026-02-10 | 2026-02-10
2023-01-31 | 2020 | Air Force Active | XLWU203049 |  | 2021-11-19 | 2022-07-12 | BL Harbert International, LLC | W9127822C0012 | 7714614 | 63919543 | 2025-06-09 | 2025-06-09
2023-01-31 | 2020 | Air Force Active | XLWU203050 |  | 2021-06-25 | 2022-04-29 | The Lane Construction Corporation | W9127822C0017 | 175216738 | 184052336 | 2026-04-26 | 2026-06-25
2023-01-31 | 2022 | Air Force Active | XQPZ124008 |  | 2021-12-22 | 2022-06-01 | John Bowman, Inc. | W9128F22C0019 | 4640852 | 4917444 | 2023-12-14 | 2023-12-14
2023-01-31 | 2018 | Air Force Active | XQPZ164001 |  | 2020-04-16 | 2020-08-21 | Bryan Construction | W9128F20C0038 | 26744525 | 26827768 | 2023-08-13 | 2024-01-08
2023-01-31 | 2020 | Air Force Active | XQPZ174006 |  | 2020-09-23 | 2021-01-29 | JBI Inc | W9128F21C0013 | 5040100 | 5040100 | 2023-02-27 | 2023-05-28
2023-01-31 | 2022 | Air Force Active | XUMU193000 |  | 2021-12-01 | 2022-05-10 | Peter Vander Werff Construction, Inc | W912PL22C0014 | 13397000 | 13397000 | 2024-01-02 | 2023-12-30
2023-01-31 | 2016 | Air Force Active | YANB144533 |  | 2019-12-19 | 2020-03-18 | LBB Kaiserslautern | W912GB16C0017 | 7128197 | 7128197 | 2021-04-01 | 2024-05-23
2023-01-31 | 2016 | Air Force Active | YWHG031002R2 |  | 2018-07-02 | 2019-01-31 | YWHG031002R2, Consolidated Stealth Operations & Nuclear Alert Facility | W912DQ19C4001 | 26957316 | 26957316 | 2020-08-15 | 2021-09-15
2023-01-31 | 2020 | Air Force Active | YWHG1030692 |  | 2021-03-03 | 2021-07-29 | L. S. Black | W912DQ21C4002 | 25045996 | 26790450 | 2023-09-01 | 2024-01-14
2023-01-31 | 2018 | Air Force Active | YWHG163100 |  | 2021-09-09 | 2021-11-12 | CNS Vazquez Reasbeck Construction LLC | FA462522F0009 | 5269467 | 5269467 | 2023-04-29 | 2023-09-04
2023-01-31 | 2021 | Air Force Active | YWHG193001 |  | 2020-12-21 | 2021-08-16 | Howard W Pence Inc | W912DQ21C4003 | 5505523 | 5505523 | 2021-09-15 | 2022-11-04
2023-01-31 | 2019 | Air Force Active | ZHTV093301 |  | 2019-05-31 | 2019-08-09 | National Contracting Service, LLC | W912QR19C0027 | 1936614 | 1969863 | 2020-05-12 | 2020-09-10
2023-01-31 | 2018 | Air Force Active | ZHTV153201 |  | 2020-01-27 | 2020-04-14 | Butt Construction | W912QR20C0011 | 0 | 0 | 2021-09-03 | 2023-02-28
2023-01-31 | 2020 | Air Force Active | ZNRE2031002 |  | 2021-04-19 | 2022-02-17 | Tokyu Construction Co., Ltd. | W912HV22C0003 | 15384034 | 15384034 | 2024-01-12 | 2024-04-12
2023-01-31 | 2020 | Air Force Active | ZNRE204308 |  | 2020-02-05 | 2020-08-18 | Nippo Corporation | W912HV17D001520F004 | 9480795 | 9480795 | 2022-09-06 | 2023-01-05
2023-01-31 | 2022 | Air Force Active | ZNRE254300 |  | 2021-10-06 | 2022-04-29 | Gilbane Japan GK | W912HV22C0002 | 43296723 | 43296723 | 2022-05-29 | 2024-10-30
2023-01-31 | 2020 | Air Force Reserve | AJXF223744 |  | 2020-06-01 | 2020-09-23 | Kinsley Construction, Inc. | W912QR20C0049 | 9992147 | 9992147 | 2022-05-26 | 2023-01-09
2023-01-31 | 2018 | Air Force Reserve | AWUB105005 |  | 2018-07-12 | 2019-03-30 | Justin J. Reeves, L.L.C. | N6945019C2105 | 2907892 | 2907892 | 2020-03-31 | 2021-08-27
2023-01-31 | 2022 | Air Force Reserve | BAEY105675 |  | 2022-07-22 | 2022-09-30 | Cox Construction Co. | W912QR22C0036 | 32879000 | 32879000 | 2024-09-30 | 2024-09-30
2023-01-31 | 2019 | Air Force Reserve | CTGB169002 |  | 2019-04-23 | 2019-08-01 | NISOU LGC JV, LLC | W912QR19C0026 | 9928185 | 9928185 | 2020-10-27 | 2022-05-13
2023-01-31 | 2019 | Air Force Reserve | CTGB989003 |  | 2020-06-01 | 2020-09-16 | Messer Construction Co. | W912QR20C0039 | 11471000 | 11471000 | 2022-05-04 | 2023-02-18
2023-01-31 | 2018 | Air Force Reserve | DDPM130007 |  | 2018-06-29 | 2018-12-12 | Unified Sevices of Texas, Inc. | N6945019F1275 | 2179491 | 2179491 | 2020-09-14 | 2021-01-31
2023-01-31 | 2021 | Air Force Reserve | DDPM414396 |  | 2021-06-01 | 2021-09-29 | Conti Federal Services, Inc. | N6945021C0038 | 11259595 | 11259595 | 2024-09-30 | 2024-09-30
2023-01-31 | 2021 | Air Force Reserve | DDPM414415 |  | 2021-06-01 | 2021-09-29 | Conti Federal Services, Inc. | N6945021C0038 | 16788096 | 16788096 | 2024-09-30 | 2024-09-30
2023-01-31 | 2022 | Air Force Reserve | FBNV170602 |  | 2021-07-09 | 2022-07-08 | Richard Group, LLC | W912QR22F0199 | 5194235 | 5194235 | 2024-02-28 | 2024-02-28
2023-01-31 | 2016 | Air Force Reserve | FGWB009002 |  | 2017-01-06 | 2017-09-21 | DRACE CONSTRUCTION COMPANY | W912QR17C0038 | 9397411 | 10249989 | 2019-06-06 | 2022-03-09
2023-01-31 | 2018 | Air Force Reserve | KNMD624007 |  | 2020-09-01 | 2020-09-30 | Hensel Phelps Construction Co. | N6247820D4003 | 8552000 | 8552000 | 2022-07-11 | 2022-11-30
2023-01-31 | 2019 | Air Force Reserve | MAHG063004 |  | 2019-10-01 | 2019-12-11 | EMR, Inc. | N6945020F0870 | 5057057 | 5057057 | 2020-10-31 | 2021-08-30
2023-01-31 | 2016 | Air Force Reserve | PDPG120514 |  | 2018-08-20 | 2018-09-14 | Lead Builders Inc | W912QR18C0031 | 4968200 | 5056600 | 2019-11-08 | 2021-05-31
2023-01-31 | 2022 | Air Force Reserve | PQWY149006 |  | 2021-07-09 | 2022-07-08 | Gideon Contracting, LLC | W912QR22F0315 | 3774459 | 3774714 | 2024-06-08 | 2024-06-08
2023-01-31 | 2022 | Air Force Reserve | PQWY149007 |  | 2022-07-20 | 2022-09-28 | Gideon Contracting, LLC | W912QR22F0315 | 3268363 | 3268363 | 2024-06-08 | 2024-06-08
2023-01-31 | 2022 | Air Force Reserve | QJKL090004 |  | 2021-09-24 | 2022-05-12 | L.S.Black Construction, LLC | W912QR22C0024 | 11661640 | 11661640 | 2023-12-28 | 2023-12-28
2023-01-31 | 2021 | Air Force Reserve | QJKL100004 |  | 2021-06-01 | 2021-09-22 | L.S.Black Construction, LLC | W912QR21C0043 | 10511086 | 10511086 | 2023-09-22 | 2023-09-22
2023-01-31 | 2019 | Air Force Reserve | RVKQ079104 |  | 2019-04-29 | 2019-07-03 | LGC Global, Inc. | W912QR19C0021 | 11311046 | 11333785 | 2021-07-23 | 2021-12-08
2023-01-31 | 2022 | Air Force Reserve | RVKQ219742 |  | 2022-01-21 | 2022-05-16 | Butt Construction | W912QR21D0057 | 11948000 | 11948000 | 2024-03-14 | 2024-03-14
2023-01-31 | 2018 | Air Force Reserve | SXHT103001 |  | 2018-03-01 | 2018-05-25 | Ashford Leebcor Enterpises, LLC | W912QR18C0018 | 25242688 | 22626925 | 2020-07-19 | 2022-05-31
2023-01-31 | 2019 | Air Force Reserve | SXHT171217 |  | 2019-06-24 | 2019-09-28 | Roundhouse PBN | W912QR17C0049 | 2863596 | 2863596 | 2021-03-15 | 2021-08-12
2023-01-31 | 2019 | Air Force Reserve | SXHT203000 |  | 2020-06-01 | 2022-03-22 | Patriot Construction | W912QR20C0050 | 20438870 | 20438870 | 2024-03-21 | 2024-04-01
2023-01-31 | 2022 | Air Force Reserve | SXHT219201 |  | 2021-10-08 | 2022-06-11 | Roundhouse-MV JV | W912QR22C0023 | 18921899 | 18921899 | 2024-09-05 | 2024-09-05
2023-01-31 | 2018 | Air Force Reserve | UHHZ073003 |  | 2019-06-28 | 2019-09-24 | ACC Construction Company, Inc. | W912QR19C0042 | 32093710 | 28917160 | 2021-11-26 | 2022-11-30
2023-01-31 | 2020 | Air Force Reserve | UHHZ073005 |  | 2020-11-15 | 2021-01-29 | ACC Construction Company, Inc. | W912QR19C0009 | 31229066 | 31229066 | 2023-04-11 | 2023-08-03
2023-01-31 | 2017 | Air Force Reserve | VKAG159021 |  | 2017-05-19 | 2017-09-27 | Walbridge Aldinger LLC | W912QR17C0031 | 52493799 | 58903514 | 2020-09-09 | 2021-08-31
2023-01-31 | 2018 | Air Force Reserve | VKAG159026 |  | 2020-06-01 | 2020-09-29 | Ocean Construction Services, Inc. | W912QR20C0056 | 4628152 | 4628152 | 2022-07-08 | 2023-02-07
2023-01-31 | 2018 | Air Force Reserve | YTPM059004 |  | 2019-04-08 | 2019-08-01 | P & S Construction, Inc. | W912QR19C0020 | 10383981 | 9832232 | 2020-12-12 | 2021-08-12
2023-01-31 | 2019 | Air Force Reserve | YTPM099001B |  | 2019-07-26 | 2021-06-17 | Ciambro AZ JV | W912QR21C0025 | 46421000 | 46421000 | 2023-09-29 | 2023-09-29
2023-01-31 | 2021 | Air National Guard | AJXF189013 |  | 2022-01-24 | 2022-06-14 | Corenic Construction Group, LLC | W912DR22C0015 | 15948509 | 14064852 | 2024-01-11 | 2024-01-11
2023-01-31 | 2019 | Air National Guard | DJCF149001 |  | 2022-07-18 | 2022-09-22 | Macro Z Technologies | W50S7522C0002 | 14400000 | 13684000 | 2023-12-08 | 2023-12-08
2023-01-31 | 2021 | Air National Guard | DPEZ029038 |  | 2021-04-23 | 2021-11-15 | Razor Cosulting | W50S8W22C0001 | 5527675 | 5439010 | 2023-02-28 | 2023-06-06
2023-01-31 | 2021 | Air National Guard | DPEZ189031 |  | 2021-07-22 | 2022-04-15 | Cora Jane | W50S8W22C0003 | 4588267 | 4470000 | 2023-08-08 | 2023-08-08
2023-01-31 | 2021 | Air National Guard | FAKZ189019 |  | 2021-10-28 | 2022-06-27 | Bear Brothers, INC | W50S6N22C0001 | 18205428 | 17736650 | 2024-08-19 | 2024-08-19
2023-01-31 | 2021 | Air National Guard | FAKZ999088 |  | 2021-10-28 | 2022-06-27 | BEAR BROTHERS, INC | W50S6N22C0001 | 19564393 | 19021500 | 2025-01-06 | 2025-01-06
2023-01-31 | 2020 | Air National Guard | FJRP189030 |  | 2021-05-14 | 2021-11-01 | Edison Foard, Inc | 2022000158 | 1659272 | 1593860 | 2022-11-01 | 2022-11-01
2023-01-31 | 2020 | Air National Guard | FJRP189050 |  | 2021-05-14 | 2021-09-24 | Showalter Construction Company | W50S8721C5001 | 3279911 | 3216900 | 2022-08-20 | 2022-08-20
2023-01-31 | 2021 | Air National Guard | FJRP199040 |  | 2021-05-19 | 2021-10-01 | Brantley Construction Services LLC | W50S8721C5002 | 4690132 | 4598700 | 2023-03-10 | 2023-03-10
2023-01-31 | 2019 | Air National Guard | FJRP199080 |  | 2019-03-28 | 2019-07-12 | GVA-AVM Joint Venture | W9124219C5007 | 5224985 | 5722538 | 2020-08-26 | 2020-08-26
2023-01-31 | 2019 | Air National Guard | FMKM179063 |  | 2021-06-01 | 2021-10-06 | Max Gray Construction | W912LM21R10010002 | 6397054 | 6265424 | 2022-10-31 | 2022-10-31
2023-01-31 | 2022 | Air National Guard | HAAW139030 |  | 2021-09-28 | 2022-02-15 | JJ Contracting | W50S8N22C0001 | 4585649 | 4395136 | 2023-03-01 | 2023-03-01
2023-01-31 | 2019 | Air National Guard | JLQN049119 |  | 2019-02-18 | 2019-06-01 | A. WBE-CCI Joint Venture One, LLC | W91SMC19C6001 | 8184676 | 7905803 | 2023-10-18 | 2023-10-18
2023-01-31 | 2020 | Air National Guard | KJAQ179127 |  | 2021-08-28 | 2022-02-23 | Diversified Contractors, Inc | W50S8Z22F0001 | 3154571 | 3154571 | 2023-03-15 | 2023-03-15
2023-01-31 | 2021 | Air National Guard | KKGA169022 |  | 2021-03-16 | 2021-07-20 | Gast Construction | W901UZ21C0001 | 13557321 | 13484790 | 2022-07-20 | 2022-07-20
2023-01-31 | 2019 | Air National Guard | KNMD189008 |  | 2019-06-24 | 2020-08-07 | Pacific Federal Contractors, LLC | W912J620C0001 | 20236741 | 18675556 | 2023-03-05 | 2023-03-05
2023-01-31 | 2022 | Air National Guard | LUXC189012 |  | 2022-08-19 | 2022-11-22 | Peska | W50S9623C0001 | 11437382 | 10967000 | 2024-06-24 | 2024-06-24
2023-01-31 | 2019 | Air National Guard | MUHJ179000 |  | 2020-11-03 | 2020-12-23 | Ocean Construction Services | W9123621C2013 | 7644604 | 6748367 | 2023-01-31 | 2023-01-31
2023-01-31 | 2019 | Air National Guard | PBXP929798 |  | 2019-10-25 | 2020-02-18 | CANCO, LLC | W50S8R20C0003 | 10316495 | 10365100 | 2022-05-25 | 2022-05-25
2023-01-31 | 2021 | Air National Guard | PJVY199001 |  | 2021-07-01 | 2022-01-28 | MCW-TMG1, LLC | W50S8V22C0001 | 5806562 | 5655736 | 2025-05-12 | 2025-05-12
2023-01-31 | 2019 | Air National Guard | PSTE089064 |  | 2020-08-13 | 2021-09-30 | CCCS International LLC | W912QG21C0004 | 4748809 | 4571407 | 2023-10-30 | 2023-10-30
2023-01-31 | 2020 | Air National Guard | QMSN199056 |  | 2020-07-24 | 2021-03-24 | Thompson Builders Corporation | W50S8X21C0001 | 55702065 | 54219500 | 2022-10-17 | 2022-10-17
2023-01-31 | 2019 | Air National Guard | RQLH059034 |  | 2020-08-20 | 2021-03-11 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945021C0005 | 7261649 | 6401000 | 2024-10-01 | 2024-10-01
2023-01-31 | 2019 | Air National Guard | RQLH189009 |  | 2020-08-20 | 2021-03-11 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945021C0005 | 21831459 | 19244906 | 2024-10-01 | 2024-10-01
2023-01-31 | 2022 | Air National Guard | SCRV359001 |  | 2022-06-04 | 2022-08-26 | Sheridan Corporation | 15A20220825*0601 | 5200000 | 4665000 | 2024-11-30 | 2024-11-30
2023-01-31 | 2022 | Air National Guard | SZCQ169264 |  | 2021-12-20 | 2022-04-12 | P&S Construction INC | W912WJ22F0052 | 3124366 | 2675744 | 2023-11-03 | 2023-11-03
2023-01-31 | 2020 | Air National Guard | TUMR189003 |  | 2020-12-17 | 2021-08-19 | QB GROUP LLC | N6945021C0031 | 9201235 | 7791000 | 2024-01-29 | 2024-01-29
2023-01-31 | 2020 | Air National Guard | TUMR189004 |  | 2020-12-17 | 2021-08-19 | QB GROUP LLC | N6945021C0031 | 31741307 | 27230000 | 2024-01-29 | 2024-01-29
2023-01-31 | 2020 | Air National Guard | ULYB169010 |  | 2020-06-09 | 2020-09-02 | Lee Grover | W50S7G20C0001 | 5962100 | 6229998 | 2022-03-31 | 2022-03-31
2023-01-31 | 2022 | Air National Guard | VBDZ179043 |  | 2022-06-29 | 2022-12-23 | Riverview Construction | W50S8J23C0001 | 10826967 | 10552800 | 2024-01-22 | 2024-01-22
2023-01-31 | 2021 | Air National Guard | WEAS189001 |  | 2021-08-11 | 2021-09-27 | Monarch Construction | 2200000107 | 1500000 | 1500000 | 2023-09-27 | 2023-09-27
2023-01-31 | 2022 | Air National Guard | WKVB139002 |  | 2022-05-03 | 2022-09-26 | VRD Contracting | W50S8E22C0004 | 3017115 | 2935000 | 2023-10-26 | 2023-10-26
2023-01-31 | 2020 | Air National Guard | XDQU109057 |  | 2020-06-23 | 2020-09-25 | Ashford Leebcor Enterprises IV LLC | W50S7020C0002 | 20213955 | 22115430 | 2022-01-23 | 2022-07-02
2023-01-31 | 2022 | Air National Guard | XGFG139001 |  | 2022-04-25 | 2022-09-29 | KPH Construction Corp | W50S9F22C0005 | 11091902 | 10693887 | 2024-01-22 | 2024-01-22
2023-01-31 | 2020 | Air National Guard | XGFG189001 |  | 2020-08-20 | 2021-04-15 | J. H. FINDORFF & SON, INC. | W50S9F21C0001 | 10552313 | 9338142 | 2023-01-07 | 2023-01-07
2023-01-31 | 2022 | Air National Guard | XGFG189002 |  | 2022-05-18 | 2022-09-29 | J.H. Findorff and Son Inc. | W50S9F22C0004 | 26864399 | 26129682 | 2024-04-03 | 2024-04-03
2023-01-31 | 2020 | Air National Guard | XGFG189004 |  | 2020-11-04 | 2021-07-19 | CONTI FEDERAL SERVICES, INC | W9128F21C0039 | 21978910 | 19703059 | 2022-11-11 | 2022-11-11
2023-01-31 | 2021 | Air National Guard | XHEA189054 |  | 2021-03-29 | 2021-08-30 | Granite Construction Compnay | F9K3CE1084MW01 | 4329586 | 3350722 | 2022-08-30 | 2022-08-30
2023-01-31 | 2022 | Air National Guard | XHZG159052 |  | 2022-06-13 | 2022-12-15 | Magnum Construction | W50S8U23C0001 | 5962459 | 5634800 | 2024-01-14 | 2024-01-14
2023-01-31 | 2019 | Army Active | 33584 |  | 2020-10-13 | 2021-03-26 | SGS, LLC | W9126G21C0005 | 44927000 | 46765000 | 2023-12-11 | 2025-04-27
2023-01-31 | 2019 | Army Active | 35782 |  | 2019-08-09 | 2019-09-26 | P & R JV | W912QR19C0039 | 45794000 | 48170000 | 2022-02-05 | 2023-03-31
2023-01-31 | 2018 | Army Active | 55199 |  | 2018-07-11 | 2019-10-15 | WHH Nisqually-Garco JV | W912DW20C0001 | 21087000 | 22111000 | 2021-11-29 | 2023-03-17
2023-01-31 | 2021 | Army Active | 55516 |  | 2021-02-12 | 2021-05-28 | ACC | W912HN21C3004 | 62212000 | 63257000 | 2023-07-05 | 2023-11-15
2023-01-31 | 2021 | Army Active | 58139 |  | 2021-03-04 | 2021-06-17 | TEPA EC | W9128F21C0038 | 41730000 | 43062000 | 2023-01-06 | 2023-04-29
2023-01-31 | 2020 | Army Active | 59766 |  | 2020-08-05 | 2021-09-15 | Structural Associates, Inc. | W912DS21C0015 | 27331000 | 27269000 | 2023-10-18 | 2023-10-18
2023-01-31 | 2014 | Army Active | 59779 |  | 2016-02-24 | 2016-07-28 | San Juan | W9128A-16-C-0006 | 54844000 | 57844000 | 2020-06-10 | 2025-09-07
2023-01-31 | 2020 | Army Active | 60276 |  | 2020-02-13 | 2021-04-30 | M. A. Mortenson Company | W9123621C2024 | 66749000 | 67330000 | 2024-05-31 | 2024-05-31
2023-01-31 | 2018 | Army Active | 61147 |  | 2018-06-20 | 2019-11-15 | Walsh Federal JV | W912DW20C0002 | 77308000 | 79440000 | 2022-08-22 | 2022-11-14
2023-01-31 | 2017 | Army Active | 62380 |  | 2018-08-13 | 2018-09-22 | Staatliches Hochbauamt Amberg | W912GB-16-C-0007 | 20950000 | 23997000 | 2022-05-11 | 2022-11-22
2023-01-31 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan | W912HV-14-C-0007 | 84367000 | 90117000 | 2021-06-09 | 2026-10-10
2023-01-31 | 2020 | Army Active | 62856 |  | 2020-04-14 | 2020-07-21 | Walsh Motor City JV | W912QR20C0027 | 22344000 | 23320000 | 2022-10-28 | 2023-01-04
2023-01-31 | 2019 | Army Active | 63054 |  | 2019-07-26 | 2019-09-27 | Benard Associates, Inc | W912DS19C0033 | 25164000 | 30706000 | 2021-11-03 | 2022-11-16
2023-01-31 | 2019 | Army Active | 64296 |  | 2021-04-16 | 2022-02-24 | Walsh Federal LLC | W912QR22C0004 | 30521000 | 30544000 | 2024-02-21 | 2024-04-17
2023-01-31 | 2008 | Army Active | 66253 |  | 2008-02-15 | 2008-03-31 | Staatliches Hochbauamt Nurnberg II | W912GB-06-C-0038 | 53186000 | 55564000 | 2010-10-09 | 2023-07-28
2023-01-31 | 2018 | Army Active | 67554 |  | 2022-06-02 | 2022-09-21 | Direct Steel and Construction | W9126G22C0029 | 25544000 | 25544000 | 2024-08-21 | 2024-08-21
2023-01-31 | 2020 | Army Active | 68253 |  | 2020-05-07 | 2021-09-29 | ETERNA SA | W9127821C0039 | 39318000 | 39318000 | 2025-01-08 | 2025-01-08
2023-01-31 | 2013 | Army Active | 68530 |  | 2015-05-02 | 2015-09-23 | D Wilson Contruction, Inc | W9126G-14-D-0050 | 37657000 | 58068000 | 2018-12-17 | 2023-02-28
2023-01-31 | 2020 | Army Active | 69347 |  | 2020-02-06 | 2020-05-20 | B.L. Harbert Internationl | W912QR20C0022 | 37142000 | 40747000 | 2022-07-11 | 2022-12-15
2023-01-31 | 2021 | Army Active | 70551 |  | 2022-06-08 | 2022-10-04 | Nan, Inc. | W9128A23C0001 | 44698000 | 44698000 | 2026-03-09 | 2026-03-09
2023-01-31 | 2015 | Army Active | 70668 |  | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 347866000 | 2021-11-07 | 2023-02-20
2023-01-31 | 2018 | Army Active | 70668 | 58857 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 347866000 | 2021-11-07 | 2023-02-20
2023-01-31 | 2017 | Army Active | 70668 | 76593 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 347866000 | 2021-11-07 | 2023-02-20
2023-01-31 | 2019 | Army Active | 70668 | 76595 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 347866000 | 2021-11-07 | 2023-02-20
2023-01-31 | 2020 | Army Active | 70668 | 92340 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 347866000 | 2021-11-07 | 2023-02-20
2023-01-31 | 2017 | Army Active | 70935 |  | 2021-07-28 | 2021-09-30 | John C. Grimberg Co., Inc. | W912DR21C0057 | 20150000 | 20185000 | 2024-04-24 | 2024-04-24
2023-01-31 | 2018 | Army Active | 71425 |  | 2021-06-11 | 2022-01-14 | JV AFH Baumholder | W912GB22C0008 | 72136000 | 83826000 | 2027-02-14 | 2027-02-14
2023-01-31 | 2020 | Army Active | 73391 |  | 2020-06-12 | 2020-09-29 | Purcell Construction | W9123620C2027 | 47269000 | 47895000 | 2022-11-03 | 2023-03-31
2023-01-31 | 2019 | Army Active | 74339 |  | 2021-06-11 | 2022-01-14 | JV AFH Baumholder | W912GB22C0008 | 0 | 0 | 2027-02-14 | 2027-02-14
2023-01-31 | 2017 | Army Active | 74877 |  | 2020-10-28 | 2021-08-19 | Walsh Federal LLC | W9123821C0011 | 13438000 | 14016000 | 2022-11-26 | 2023-09-29
2023-01-31 | 2020 | Army Active | 76673 |  | 2020-06-29 | 2020-11-10 | Turner Construction Co, Inc | W9127821C0006 | 34050000 | 35559000 | 2022-12-25 | 2022-12-25
2023-01-31 | 2021 | Army Active | 76897 |  | 2021-02-10 | 2021-09-21 | Hensel Phelps Construction Co. | W9128A21C0007 | 76594000 | 78994000 | 2024-10-12 | 2024-10-12
2023-01-31 | 2020 | Army Active | 77303 |  | 2020-02-28 | 2020-06-19 | TEPA EC | W9128F20C0029 | 46209000 | 47097000 | 2022-06-12 | 2023-01-31
2023-01-31 | 2020 | Army Active | 77728 |  | 2020-02-07 | 2020-06-26 | Walsh Federal, LLC | W912DW20C0007 | 38027000 | 41588000 | 2022-12-31 | 2023-05-26
2023-01-31 | 2018 | Army Active | 77779 |  | 2018-06-22 | 2019-06-06 | S.B. Ballard Construction Company | W9123619C0014 | 40458000 | 41308000 | 2021-02-15 | 2023-01-31
2023-01-31 | 2021 | Army Active | 77881 |  | 2021-06-21 | 2022-08-04 | Nan Inc. DBA Ocean House Builders | W9128A22C0007 | 59085000 | 57792000 | 2024-08-22 | 2024-08-22
2023-01-31 | 2018 | Army Active | 78713 |  | 2021-07-21 | 2022-08-12 | Staatliches Hochbauamt Amberg | W912GB18C0002 | 21306000 | 21352000 | 2025-02-05 | 2025-02-05
2023-01-31 | 2019 | Army Active | 78804 |  | 2020-06-03 | 2020-12-04 | DOBCO GROUP, INC. | W912DS21C0002 | 186676000 | 198989000 | 2025-01-04 | 2025-05-29
2023-01-31 | 2015 | Army Active | 81234 |  | 2017-02-15 | 2018-09-14 | Aegis Security Insurance Company | W9126G-17-C-0046 | 2580000 | 2707000 | 2019-09-27 | 2023-03-31
2023-01-31 | 2021 | Army Active | 81352 |  | 2021-08-26 | 2021-11-04 | KLK Electric, Inc | W912DS22C0002 | 4620000 | 4707000 | 2023-02-02 | 2023-01-25
2023-01-31 | 2019 | Army Active | 81429 |  | 2019-07-22 | 2019-10-30 | Daebo Engr. & Const. Co., Ltd. | W912UM20C0001 | 54939000 | 56890000 | 2022-09-05 | 2023-09-19
2023-01-31 | 2019 | Army Active | 86019 |  | 2021-10-21 | 2021-11-10 | Staatliches Hochbauamt Amberg | W912GB18C0075 | 0 | 0 | 2022-09-27 | 2022-12-26
2023-01-31 | 2015 | Army Active | 86094 |  | 2019-02-11 | 2020-04-01 | Staatliches Hochbauamt Amberg | W912GB-16-C-0006 | 2418000 | 3024000 | 2021-09-05 | 2022-12-08
2023-01-31 | 2020 | Army Active | 86215 |  | 2021-07-28 | 2021-11-09 | Tactical Defense Solutions, Inc. | W9123622C2040 | 2700000 | 2728000 | 2022-12-20 | 2022-11-28
2023-01-31 | 2019 | Army Active | 86351 |  | 2022-02-25 | 2022-09-29 | Ameresco Inc. | W912QR22C0042 | 11265000 | 11265000 | 2024-10-14 | 2024-10-14
2023-01-31 | 2016 | Army Active | 86409 |  | 2020-01-17 | 2020-09-03 | Tuckman Barbee Construction Co., Inc. | W912DR20C0042 | 24482000 | 25306000 | 2022-10-27 | 2023-09-07
2023-01-31 | 2017 | Army Active | 86689 |  | 2017-06-13 | 2019-02-26 | Yojin Construction & Engineering Co., Ltd. | W912UM19C0007 | 382205000 | 448537000 | 2022-07-25 | 2023-04-18
2023-01-31 | 2019 | Army Active | 86689 | 86877 | 2018-10-10 | 2019-02-26 | Yojin | W912UM19C0007 | 382205000 | 448537000 | 2022-07-25 | 2023-04-18
2023-01-31 | 2020 | Army Active | 86689 | 91327 | 2018-10-10 | 2019-02-26 | Yojin Construction & Engineering Co., Ltd. | W912UM19C0007 | 382205000 | 448537000 | 2022-07-25 | 2023-04-18
2023-01-31 | 2018 | Army Active | 86689 | 91380 | 2018-07-27 | 2019-02-26 | Yojin Construction & Engineering Co., Ltd. | W912UM19C0007 | 382205000 | 448537000 | 2022-07-25 | 2023-04-18
2023-01-31 | 2018 | Army Active | 86816 |  | 2019-03-21 | 2019-09-10 | The Robins & Morton Group | W9127819C0024 | 32995000 | 36654000 | 2021-10-10 | 2023-12-14
2023-01-31 | 2016 | Army Active | 86824 |  | 2019-04-08 | 2019-04-18 | Staatliches Hochbauamt Amberg | W912GB-15-C-0007 | 42195000 | 44325000 | 2023-06-03 | 2023-06-03
2023-01-31 | 2018 | Army Active | 86832 |  | 2018-04-24 | 2018-08-15 | Aytekin-Serol Eng Cons Trade Co. LTD. | W912GB-15-D-0084 | 4004000 | 9904000 | 2022-03-25 | 2024-10-31
2023-01-31 | 2018 | Army Active | 86991 |  | 2019-03-28 | 2020-01-27 | Landesbetrieb Bau und Immobilien Hessen Zentrale | W912GB-17-C-0002 | 43508000 | 46808000 | 2022-06-22 | 2024-03-16
2023-01-31 | 2018 | Army Active | 87205 |  | 2020-02-25 | 2020-04-30 | Allen-Batchelor Construction Co., Inc. | W912HN20C3004 | 6187000 | 11229000 | 2022-10-01 | 2022-11-04
2023-01-31 | 2020 | Army Active | 87807 |  | 2020-04-10 | 2021-07-02 | M.W. Builders | W9126G21C0014 | 36514000 | 36707000 | 2023-07-20 | 2023-08-03
2023-01-31 | 2020 | Army Active | 87933 |  | 2020-03-06 | 2020-09-25 | Structural Associate | W912DS20C0025 | 21732000 | 21798000 | 2022-10-11 | 2023-01-23
2023-01-31 | 2020 | Army Active | 88077 |  | 2019-11-20 | 2020-03-09 | Manhattan Construction Company | W912DR20C0007 | 76399000 | 84201000 | 2023-04-01 | 2023-08-03
2023-01-31 | 2021 | Army Active | 88077 | 96217 | 2019-11-20 | 2020-03-09 | Manhattan Construction Company | W912DR20C0007 | 76399000 | 84201000 | 2023-04-29 | 2023-04-29
2023-01-31 | 2020 | Army Active | 88410 |  | 2020-10-29 | 2021-06-15 | Zodiac-Poettker | W912HN21C3005 | 56295000 | 56322000 | 2023-08-01 | 2023-09-25
2023-01-31 | 2019 | Army Active | 88724 |  | 2019-05-31 | 2020-06-19 | Gilbane Federal | W912HN20C3006 | 193807000 | 196046000 | 2022-07-07 | 2023-11-30
2023-01-31 | 2020 | Army Active | 88725 |  | 2020-12-02 | 2021-04-02 | J. KOKOLAKIS CONTRACTING | W912HN21C3003 | 112377000 | 112918000 | 2024-04-25 | 2024-05-17
2023-01-31 | 2020 | Army Active | 89057 |  | 2020-01-16 | 2020-05-29 | Sauer | W912PM20C0014 | 10480000 | 10972000 | 2022-04-09 | 2023-04-28
2023-01-31 | 2018 | Army Active | 90351 |  | 2020-09-18 | 2021-03-19 | AMG | W912PL21C0007 | 26473000 | 27087000 | 2023-02-10 | 2023-02-10
2023-01-31 | 2020 | Army Active | 90430 |  | 2021-06-11 | 2022-01-14 | JV AFH Baumholder | W912GB22C0008 | 0 | 0 | 2027-02-14 | 2027-02-14
2023-01-31 | 2020 | Army Active | 91328 |  | 2020-06-25 | 2020-09-15 | Weldin Construction, LLC | W912BV17D0017 | 4623000 | 4623000 | 2021-11-09 | 2023-09-23
2023-01-31 | 2020 | Army Active | 92422 |  | 2021-04-01 | 2021-08-18 | EMR, Inc | W91278-16-D-0035 | 3929000 | 3956000 | 2022-11-01 | 2023-04-24
2023-01-31 | 2019 | Army Active | 93021 |  | 2019-10-24 | 2020-04-07 | Anderson Burton Construction, Inc. | W9128A-16-D-0005 | 5827000 | 6047000 | 2022-01-08 | 2022-11-29
2023-01-31 | 2019 | Army Active | 93209 |  | 2020-11-16 | 2022-03-07 | Staatliches Bauamt Nurnberg | W912GB18C0024 | 4574000 | 4591000 | 2023-03-29 | 2024-03-29
2023-01-31 | 2021 | Army Active | 93322 |  | 2021-07-09 | 2021-09-30 | Manhattan Constr. | W912DR21C0056 | 29928000 | 33647000 | 2024-01-28 | 2024-01-28
2023-01-31 | 2022 | Army Active | 93672 |  | 2022-06-08 | 2022-10-06 | Kiewit Infrastructure West Co. | W9128A23C0002 | 53148000 | 53148000 | 2024-10-25 | 2024-10-25
2023-01-31 | 2021 | Army Active | 94363 |  | 2021-04-27 | 2021-10-22 | FOS Development Corp. | W912DS22C0001 | 5677000 | 5847000 | 2023-05-21 | 2023-05-21
2023-01-31 | 2021 | Army Active | 96540 |  | 2022-06-22 | 2022-10-06 | Nan, Inc. | W9128A23C0003 | 53165000 | 53165000 | 2025-08-26 | 2025-08-26
2023-01-31 | 2022 | Army Active | 99325 |  | 2022-05-02 | 2022-09-27 | Creative Build Stronghold Electric Joint Venture | W9123822C0019 | 4587000 | 4587000 | 2024-04-21 | 2024-04-21
2021-12-15 | 2020 | Army National Guard | 010908 |  | 2020-07-10 | 2020-07-19 | Nearen Construction Company | AC-20-C-0014-S | 12000000 | 11826000 | 2021-09-30 | 2022-02-25
2021-12-15 | 2020 | Army National Guard | 011801 |  | 2021-04-22 | 2021-06-10 | Carmon Construction, Inc. | AC-21-C-0004-S | 34000000 | 34789000 | 2022-10-21 | 2022-10-21
2021-12-15 | 2019 | Army National Guard | 020143 |  | 2018-10-02 | 2019-07-19 | TDX Quality, LLC | W91ZRU-16-2-2001 | 27000000 | 22489000 | 2021-04-23 | 2021-10-30
2021-12-15 | 2021 | Army National Guard | 040037 |  | 2021-05-02 | 2021-05-24 | Lloyd Construction Company | CTR054747 | 18100000 | 17120000 | 2022-08-26 | 2022-08-26
2021-12-15 | 2019 | Army National Guard | 050220 |  | 2020-09-17 | 2020-09-23 | Ross Sparks Builders, Inc. | 9752002 | 2150000 | 1618000 | 2021-10-15 | 2021-10-15
2021-12-15 | 2018 | Army National Guard | 080220 |  | 2020-04-07 | 2020-04-13 | Iron Mike Construction, LLC | W912LC-18-2-2001 | 5519955 | 5860202 | 2021-05-01 | 2021-09-30
2022-06-30 | 2021 | Army National Guard | 080303 |  | 2022-02-11 | 2022-02-17 | Howell Construction | W912LC-20-2-2001 | 6000000 | 5722000 | 2024-04-24 | 2024-04-24
2021-12-15 | 2018 | Army National Guard | 100040 |  | 2018-09-07 | 2018-09-13 | Harkins Builders, Inc. | 09-2016 | 36000000 | 36000000 | 2020-12-31 | 2020-12-31
2022-06-30 | 2020 | Army National Guard | 100097 |  | 2021-11-16 | 2022-01-26 | Delmarva Veteran Builders | W912L5-20-2-2001 | 3250000 | 3421000 | 2023-08-25 | 2023-08-25
2021-12-15 | 2020 | Army National Guard | 120330 |  | 2021-04-20 | 2021-06-03 | STG Contracting Group | W911YN-20-2-2003 | 3000000 | 3000000 | 2022-11-18 | 2022-11-18
2021-12-15 | 2017 | Army National Guard | 150035 |  | 2017-02-02 | 2017-09-28 | Alutiiq General Contractors LLC | W912J6-17-C-0001 | 31000000 | 28808000 | 2019-06-30 | 2021-10-18
2021-12-15 | 2020 | Army National Guard | 160024 |  | 2020-08-25 | 2020-08-31 | IMCO Construction | W912J7-19-2-2001 | 29000000 | 29809000 | 2022-09-02 | 2022-03-16
2021-12-15 | 2018 | Army National Guard | 160174 |  | 2019-12-03 | 2019-12-12 | C-2 Construction Inc. | NGBID-20-B-0009 | 3000000 | 2413413 | 2021-01-23 | 2021-12-14
2021-12-15 | 2019 | Army National Guard | 160193 |  | 2020-09-16 | 2020-09-18 | HC Company | W912J7-19-2-2002 | 6000000 | 5415000 | 2021-08-20 | 2021-10-02
2021-12-15 | 2019 | Army National Guard | 171510 |  | 2019-09-10 | 2019-09-13 | Vissering Construction Company | W91SMC-19-2-2001 | 5000000 | 4555000 | 2020-10-16 | 2021-09-09
2022-06-30 | 2021 | Army National Guard | 180202 |  | 2021-09-08 | 2021-09-21 | Messer Construction Co. | MDI-SAB-21-C-0012 | 12000000 | 13769000 | 2023-04-01 | 2023-04-27
2021-12-15 | 2020 | Army National Guard | 190005 |  | 2020-09-08 | 2020-09-11 | Happe Commercial | 8425A033 | 3000000 | 2984000 | 2021-04-15 | 2021-04-15
2021-12-15 | 2018 | Army National Guard | 190130 |  | 2018-08-27 | 2018-08-30 | Rochon Corp of Iowa | C85148014 | 8500000 | 6667000 | 2019-12-31 | 2021-04-30
2021-12-15 | 2017 | Army National Guard | 200101 |  | 2018-06-12 | 2018-11-27 | The Law Company Inc. | A-013650 | 29000000 | 28834954 | 2020-12-23 | 2022-02-12
2021-12-15 | 2018 | Army National Guard | 200129 |  | 2021-03-11 | 2021-04-01 | Cheney Construction | W912JC-19-2-2001 | 3700000 | 3408000 | 2021-06-22 | 2021-06-22
2021-12-15 | 2018 | Army National Guard | 200151 |  | 2018-09-12 | 2018-09-14 | Straub Construction Co., Inc. | W912JC-18-2-20001 | 19000000 | 18828000 | 2020-05-14 | 2021-10-15
2022-06-30 | 2021 | Army National Guard | 210054 |  | 2021-09-15 | 2021-09-27 | Monarch Construction | 785 22000000107 | 15000000 | 16536000 | 2023-09-27 | 2023-09-27
2022-06-30 | 2022 | Army National Guard | 220141 |  | 2022-04-12 | 2022-04-26 | USPFO - LA | LA22-C-017 | 23000000 | 22294000 | 2024-04-19 | 2024-04-19
2021-12-15 | 2020 | Army National Guard | 220304 |  | 2021-07-29 | 2021-09-07 | Mapp Construction | LA21-C-116 | 16500000 | 17340000 | 2023-02-24 | 2023-02-24
2021-12-15 | 2015 | Army National Guard | 230113 |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113-D | 30615000 | 32795000 | 2017-08-03 | 2021-03-31
2021-12-15 | 2018 | Army National Guard | 230135 |  | 2018-07-20 | 2018-08-14 | Devoe Construction | 230135-D | 17500000 | 18990000 | 2020-09-01 | 2021-12-31
2022-06-30 | 2021 | Army National Guard | 230139 |  | 2021-11-12 | 2021-11-19 | Sheridan Corporation | 230139-D | 3200000 | 3367000 | 2021-05-23 | 2023-05-23
2021-12-15 | 2018 | Army National Guard | 240149 |  | 2018-09-17 | 2018-09-18 | Towson Mechanical Inc. | M-900-160-0004 | 19000000 | 17704000 | 2021-04-23 | 2021-06-30
2021-12-15 | 2013 | Army National Guard | 250065 |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279000 | 21661000 | 2015-07-30 | 2017-05-17
2021-12-15 | 2015 | Army National Guard | 260222 |  | 2018-04-06 | 2018-06-29 | Ripman Construction Co Inc. | Y18228 | 1200000 | 1777000 | 2019-10-04 | 2020-12-31
2021-12-15 | 2020 | Army National Guard | 260269 |  | 2020-09-10 | 2020-09-25 | Ripman Construction Co Inc. | Y20410 | 4141000 | 4055000 | 2021-11-05 | 2021-11-05
2021-12-15 | 2019 | Army National Guard | 260274 |  | 2019-12-18 | 2020-01-03 | Ripman Construction Co Inc. | Y20003 | 3000000 | 2904000 | 2020-10-02 | 2021-04-20
2021-12-15 | 2017 | Army National Guard | 270127 |  | 2018-12-26 | 2019-01-18 | Eagle Construction Company, Inc. | 151541 | 2400000 | 2030000 | 2020-04-10 | 2020-04-17
2021-12-15 | 2018 | Army National Guard | 270132 |  | 2018-08-31 | 2018-09-06 | Stahl Construction Company | Swift #147206 | 39000000 | 40396000 | 2020-02-14 | 2020-07-01
2021-12-15 | 2020 | Army National Guard | 270203 |  | 2020-12-29 | 2021-01-08 | Donlar Construction Company | 187596 | 11200000 | 12435000 | 2022-08-20 | 2022-08-20
2022-06-30 | 2019 | Army National Guard | 270220 |  | 2021-09-21 | 2021-09-30 | Brennan Construction of MN, Inc. | 12345-Brennan | 2000000 | 4275000 | 2023-03-15 | 2023-03-15
2022-04-14 | 2018 | Army National Guard | 270233 |  | 2021-01-12 | 2021-01-13 | Project One Construction, Inc. | 188046 | 1730000 | 1331000 | 2023-07-20 | 2023-07-20
2022-06-30 | 2021 | Army National Guard | 280381 |  | 2022-04-14 | 2022-04-27 | Century Construction Group | NGB22-22-C-0003-S | 22400000 | 10400000 | 2024-04-14 | 2024-04-14
2021-12-15 | 2020 | Army National Guard | 280408 |  | 2020-07-20 | 2020-07-31 | Chris Albrition Construction | NGB22-20-C-0002 | 8100000 | 6069000 | 2021-09-30 | 2022-05-14
2021-12-15 | 2018 | Army National Guard | 290109 |  | 2018-09-19 | 2018-09-20 | KCI Construction Company | T1818-01 | 32000000 | 24564000 | 2020-11-18 | 2021-06-30
2021-12-15 | 2020 | Army National Guard | 290186 |  | 2020-05-28 | 2020-07-10 | Pro-Prost Joint Venture | T1809-01 | 12000000 | 9889000 | 2021-08-18 | 2021-12-15
2021-12-15 | 2019 | Army National Guard | 300031 |  | 2019-02-26 | 2019-02-27 | Swank Enterprises - Valier | W9124V-16-2-2001 | 12806888 | 16803433 | 2020-12-04 | 2020-12-04
2022-06-30 | 2022 | Army National Guard | 300049 |  | 2022-04-08 | 2022-04-28 | Swank Enterprises Kalispell | 2019-33-03 | 16000000 | 17501000 | 2024-07-16 | 2024-07-16
2021-12-15 | 2020 | Army National Guard | 310103 |  | 2020-08-26 | 2020-08-31 | Sampson Construction Company, Inc. | W91243-19-2-2001 | 35000000 | 27225000 | 2022-10-28 | 2022-10-28
2021-12-15 | 2021 | Army National Guard | 310140 |  | 2021-01-14 | 2021-02-06 | Perry Reid Construction | W91243-18-2-2001 | 9300000 | 8685000 | 2022-09-20 | 2022-09-20
2021-12-15 | 2020 | Army National Guard | 330050 |  | 2020-09-03 | 2020-09-21 | Turnstone Corporation | W912TF-18-2-2001 | 5950000 | 6539000 | 2022-09-02 | 2022-09-02
2022-06-30 | 2021 | Army National Guard | 340132 |  | 2021-09-05 | 2021-09-22 | DMD Contracting | W912KN-19-2-2001 | 15000000 | 14013000 | 2023-06-15 | 2023-06-15
2021-12-15 | 2018 | Army National Guard | 350200 |  | 2018-09-25 | 2018-09-27 | Jaynes Corporation | W912J3-16-2-2001 | 8600000 | 10566000 | 2020-10-01 | 2021-02-26
2021-12-15 | 2020 | Army National Guard | 361811 |  | 2020-09-17 | 2020-09-30 | Suffolk Construction Co., Inc. | 46086C | 91000000 | 67804000 | 2022-09-16 | 2024-04-12
2022-06-30 | 2017 | Army National Guard | 371402 |  | 2021-09-28 | 2021-09-29 | Garanco Inc | W91242-18-2-20019 | 1950000 | 4760000 | 2023-08-05 | 2023-08-05
2021-12-15 | 2019 | Army National Guard | 380116 |  | 2019-05-31 | 2019-06-05 | Gast Construction | AGND 19-17 | 32000000 | 28724000 | 2021-06-30 | 2021-06-30
2021-12-15 | 2019 | Army National Guard | 390285 |  | 2020-08-06 | 2020-09-02 | USPFO - OH | W91364-20-B-0001 | 7400000 | 6945000 | 2022-09-30 | 2022-09-30
2022-06-30 | 2019 | Army National Guard | 390285 |  | 2020-08-06 | 2020-09-30 | USPFO for Ohio | W9136420C0002 | 7400000 | 6944000 | 2022-09-30 | 2022-09-30
2021-12-15 | 2021 | Army National Guard | 400602 |  | 2019-06-26 | 2021-08-04 | Flintco, LLC | W912L6-19-2-2014 | 9800000 | 9323000 | 2023-02-23 | 2023-02-23
2021-12-15 | 2019 | Army National Guard | 410818 |  | 2019-09-24 | 2019-09-30 | Apollo INC. | 410818D002 | 11000000 | 10773000 | 2021-10-22 | 2021-11-22
2021-12-15 | 2019 | Army National Guard | 411104 |  | 2020-05-26 | 2020-07-10 | Silvercreek Contracting, LLC | 411104A0001 | 3000000 | 3000000 | 2020-12-31 | 2021-09-30
2021-12-15 | 2015 | Army National Guard | 411300 |  | 2019-06-13 | 2019-09-20 | Fortis Construction, Inc | 179997D002 | 6031000 | 5900000 | 2020-09-30 | 2021-01-19
2021-12-15 | 2015 | Army National Guard | 411301 |  | 2017-04-18 | 2017-09-28 | Abacus Resource Management Co. | 140033D002 | 2850000 | 2850000 | 2018-12-29 | 2021-08-30
2021-12-15 | 2016 | Army National Guard | 411503 |  | 2020-05-29 | 2020-07-22 | Rotschy, Inc. | 411305C001 | 3000000 | 2979000 | 2021-01-31 | 2021-08-30
2022-06-30 | 2021 | Army National Guard | 411508 |  | 2021-09-23 | 2021-09-27 | Fowler General Construction, Inc. | 219995C001 | 9300000 | 10576000 | 2023-10-30 | 2023-10-30
2022-06-30 | 2021 | Army National Guard | 411510 |  | 2021-09-23 | 2021-09-28 | Fowler General Construction, Inc. | 219995C003 | 15735000 | 8333000 | 2023-10-30 | 2023-10-30
2022-06-30 | 2017 | Army National Guard | 420502 |  | 2021-09-20 | 2021-09-29 | USPFO - PA | W912DR-17-D-0014 | 20000000 | 15725000 | 2023-08-10 | 2023-08-10
2022-06-30 | 2017 | Army National Guard | 420595 |  | 2021-09-18 | 2021-09-26 | Department of General Services - PA | W912KC-17-2-2001 | 2567000 | 3382000 | 2023-11-20 | 2023-11-20
2022-06-30 | 2018 | Army National Guard | 440061 |  | 2021-08-17 | 2021-09-02 | Tower Construction | 3744296 | 2900000 | 3572000 | 2022-10-30 | 2022-10-29
2021-12-15 | 2018 | Army National Guard | 440061 |  | 2021-08-17 | 2021-09-02 | USPFO - RI | W912LD-19-2-2001 | 2900000 | 3515000 | 2022-10-30 | 2022-10-30
2021-12-15 | 2017 | Army National Guard | 440064 |  | 2017-09-06 | 2017-09-13 | Marion Construction Co Inc | W912LD-15-2-2001 | 20000000 | 20595000 | 2020-02-28 | 2021-09-30
2021-12-15 | 2019 | Army National Guard | 460115 |  | 2019-02-07 | 2019-02-15 | RCS Construction, Inc. | W912MM-17-2-2001 | 15000000 | 13023000 | 2020-11-15 | 2020-11-15
2021-12-15 | 2020 | Army National Guard | 465001 |  | 2020-08-07 | 2020-08-20 | Ainsworth-Benning | W912MM-20-2-2001 | 3000000 | 3593000 | 2021-08-27 | 2021-08-27
2022-06-30 | 2021 | Army National Guard | 470030 |  | 2021-11-02 | 2021-11-16 | USPFO - TN | W912L7-19-2-2001 | 11200000 | 12806000 | 2023-11-16 | 2023-11-16
2021-12-15 | 2015 | Army National Guard | 470035 |  | 2020-02-20 | 2020-04-14 | Marbury Construction | W912l7-18-R-0005 | 1606000 | 1536000 | 2021-01-20 | 2021-06-15
2022-06-30 | 2021 | Army National Guard | 481315 |  | 2021-09-01 | 2021-09-20 | SMR Construction, Inc | W912l1-20-2-2002 | 7800000 | 9228000 | 2023-03-15 | 2023-03-15
2021-12-15 | 2017 | Army National Guard | 490601 |  | 2017-09-21 | 2017-09-26 | Jacobsen Construction Company | 1875077 | 37000000 | 37610000 | 2019-04-03 | 2021-05-27
2022-06-30 | 2021 | Army National Guard | 491201 |  | 2021-09-20 | 2021-09-29 | Hogan & Associated Construction Inc. | 2271555 | 23100000 | 13339000 | 2023-10-31 | 2023-10-31
2021-12-15 | 2020 | Army National Guard | 500110 |  | 2020-09-22 | 2020-09-29 | Dew Construction | 40766 | 30000000 | 28175479 | 2022-09-02 | 2022-09-02
2021-12-15 | 2018 | Army National Guard | 511503 |  | 2018-09-11 | 2018-09-12 | S. B. Ballard Construction Company | PC123-18312-000 | 15000000 | 16999000 | 2020-08-31 | 2021-09-16
2021-12-15 | 2016 | Army National Guard | 530041 |  | 2018-01-19 | 2018-06-28 | TDX Quality, LLC | W912DW-18-C-0015 | 19000000 | 20635000 | 2020-04-17 | 2021-12-30
2021-12-15 | 2018 | Army National Guard | 530129 |  | 2018-09-05 | 2018-09-11 | Pease Constructoin | 2016-0008 G (1-1) | 31000000 | 31823000 | 2020-09-01 | 2021-09-01
2021-12-15 | 2020 | Army National Guard | 531201 |  | 2020-06-02 | 2020-09-25 | Fowler General Construction, Inc. | 2018-586 G (1-1) | 11400000 | 10861000 | 2022-03-21 | 2022-03-21
2021-12-15 | 2021 | Army National Guard | 550148 |  | 2021-08-23 | 2021-09-14 | Miron Construction | W912J2-20-2-2001 | 11600000 | 9051000 | 2023-05-19 | 2023-05-19
2021-12-15 | 2020 | Army National Guard | 571863 |  | 2021-02-25 | 2021-03-08 | TBD | NGB-01 | 3000000 | 2895000 | 2022-07-30 | 2022-07-30
2022-06-30 | 2020 | Army National Guard | 571863 |  | 2021-02-25 | 2021-03-08 | Landivar & Associates LLC. | W9133L21C4000 | 3000000 | 2993000 | 2022-09-30 | 2022-09-30
2023-01-31 | 2018 | Army Reserve | 77074 |  | 2019-08-05 | 2019-09-27 | RBC Construction | W912QR19C0046 | 18838000 | 19273000 | 2021-04-22 | 2023-03-28
2023-01-31 | 2016 | Army Reserve | 77163 |  | 2019-08-02 | 2019-09-29 | Trans4Fed, LLC | W912QR19C0045 | 10304000 | 10574000 | 2021-06-23 | 2023-06-12
2023-01-31 | 2021 | Army Reserve | 81564 |  | 2021-08-02 | 2021-09-28 | Range & Civil Const | W912QR21C0046 | 9972000 | 9972000 | 2024-02-16 | 2024-02-16
2023-01-31 | 2020 | Army Reserve | 81802 |  | 2020-07-30 | 2020-09-29 | LS Black Constructors, LLC | W912QR20C0052 | 18824000 | 19254000 | 2022-12-17 | 2023-04-01
2023-01-31 | 2021 | Army Reserve | 82197 |  | 2021-08-04 | 2021-09-30 | Sauer Construction, LLC | W912QR21C0049 | 33126000 | 34298000 | 2024-01-31 | 2024-01-31
2023-01-31 | 2022 | Army Reserve | 88554 |  | 2022-03-04 | 2022-06-09 | LS Black Constructors, LLC | W912QR22C0025 | 11964000 | 12075000 | 2023-12-16 | 2023-12-16
2023-01-31 | 2021 | Army Reserve | 88752 |  | 2021-08-23 | 2021-09-29 | R. ZOPPO | W912QR21C0054 | 7933000 | 7933000 | 2024-02-28 | 2024-02-28
2023-01-31 | 2019 | Army Reserve | 90202 |  | 2020-02-18 | 2020-09-04 | WHH Nisqually-Garco JV 2 | W912QR20C0035 | 20217000 | 21145000 | 2022-06-22 | 2023-04-04
2023-01-31 | 2021 | Army Reserve | 90896 |  | 2021-03-17 | 2021-07-16 | LRG Construction JV, LLC | W912QR21C0031 | 3962000 | 4304000 | 2022-09-15 | 2023-03-10
2023-01-31 | 2022 | Army Reserve | 92098 |  | 2021-08-17 | 2021-11-12 | G.M. HILL ENGINEERING, INC. | W912QR20D0024 | 4924000 | 4924000 | 2023-05-19 | 2024-04-19
2023-02-14 | 2017 | Defense Health Agency | 14019 |  | 2017-06-23 | 2018-06-29 | RQ-DPRI | N40085-18-C-0637 | 30121000 | 31721000 | 2020-07-13 | 2021-10-07
2023-02-14 | 2018 | Defense Health Agency | 14021 |  | 2018-06-12 | 2019-12-18 | Soltek Pacific Construction Co. | N6247318D5855 | 27799000 | 28297000 | 2022-05-10 | 2022-12-31
2023-02-14 | 2018 | Defense Health Agency | 14040 |  | 2021-04-30 | 2021-09-27 | Whiting Turner Contracting Co | N4008521C0064 | 20355000 | 20161000 | 2023-10-12 | 2024-01-18
2023-02-14 | 2018 | Defense Health Agency | 14041 |  | 2018-06-13 | 2019-09-28 | Whiting Turner Contracting Co | N6247016D6006 | 22911000 | 23186000 | 2021-10-30 | 2022-07-18
2023-02-14 | 2018 | Defense Health Agency | 14042 |  | 2018-06-06 | 2019-09-28 | Whiting Turner Contracting Co | N4008519C9266 | 21875000 | 22500000 | 2021-10-30 | 2022-10-31
2023-02-14 | 2008 | Defense Health Agency | 52332 |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929000 | 28027000 | 2012-05-15 | 2012-07-16
2023-02-14 | 2007 | Defense Health Agency | 58395 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657000 | 2657000 | 2008-06-13 | 2008-06-08
2023-02-14 | 2007 | Defense Health Agency | 58395 | 58395-01 | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472000 | 1472000 | 2009-02-15 | 2009-02-13
2023-02-14 | 2007 | Defense Health Agency | 58395 | 58395-02 | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706000 | 706000 | 2010-04-13 | 2010-04-13
2023-02-14 | 2007 | Defense Health Agency | 58395 | 58395-03 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465000 | 2465000 | 2009-07-24 | 2009-07-24
2023-02-14 | 2007 | Defense Health Agency | 58395 | 58395-04 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 604000 | 2013-10-31 | 2013-12-06
2023-02-14 | 2007 | Defense Health Agency | 58395 | 58395-05 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 3949000 | 2014-05-31 | 2023-06-01
2023-02-14 | 2007 | Defense Health Agency | 58395 | 71101-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 7750000 | 7335000 | 2017-03-31 | 2017-05-04
2023-02-14 | 2013 | Defense Health Agency | 58395 | 78210-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 0 | 141000 | 2017-03-31 | 2017-05-04
2023-02-14 | 2013 | Defense Health Agency | 58395 | 78210-02 | 2017-08-18 | 2017-09-27 | Doyon Project Services, LLC | W912DR-17-D-0012 | 1607000 | 1580000 | 2018-10-26 | 2019-05-11
2023-02-14 | 2014 | Defense Health Agency | 58395 | 78211 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 3200000 | 3200000 | 2014-05-31 | 2023-06-01
2023-02-14 | 2009 | Defense Health Agency | 64156 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398000 | 17919000 | 2013-06-01 | 2015-06-10
2023-02-14 | 2009 | Defense Health Agency | 65731 |  | 2009-01-07 | 2009-04-08 | Total Engineering INC | W912DR-09-C-0030 | 436000 | 436000 | 2010-08-08 | 2010-08-31
2023-02-14 | 2009 | Defense Health Agency | 65731 | 65731-01 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 37771000 | 2013-06-01 | 2015-06-10
2023-02-14 | 2009 | Defense Health Agency | 65731 | 67180-01 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30
2023-02-14 | 2011 | Defense Health Agency | 66588 |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 30080000 | 31830000 | 2016-05-30 | 2017-05-03
2023-02-14 | 2018 | Defense Health Agency | 67402 |  | 2019-07-29 | 2020-01-30 | SGS, LLC | W9126G-20-C-0009 | 8996000 | 9327000 | 2022-04-03 | 2022-04-03
2023-02-14 | 2013 | Defense Health Agency | 71317 |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744000 | 46104000 | 2016-12-30 | 2019-02-15
2023-02-14 | 2013 | Defense Health Agency | 71325 |  | 2012-11-30 | 2013-09-13 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536000 | 47478000 | 2016-10-23 | 2018-06-01
2023-02-14 | 2012 | Defense Health Agency | 71408 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688000 | 21664000 | 2016-12-06 | 2019-02-15
2023-02-14 | 2012 | Defense Health Agency | 71503 |  | 2012-03-22 | 2016-08-25 | Surety Company | N69450 12 C 0754 | 9548000 | 2026000 | 2017-12-25 | 2019-05-10
2023-02-14 | 2017 | Defense Health Agency | 71509 |  | 2017-06-30 | 2018-12-26 | KBE BLDG CORP | N4008519C9070 | 30188000 | 31774000 | 2021-01-24 | 2021-07-14
2023-02-14 | 2010 | Defense Health Agency | 72481 |  | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 56858000 | 254981000 | 2016-11-26 | 2020-02-29
2023-02-14 | 2010 | Defense Health Agency | 72481 | 72481-01 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-10-12
2023-02-14 | 2010 | Defense Health Agency | 72481 | 72481-02 | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488000 | 10634000 | 2012-07-05 | 2012-12-31
2023-02-14 | 2010 | Defense Health Agency | 72481 | 72481-03 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-10-17
2023-02-14 | 2010 | Defense Health Agency | 72481 | 72481-04 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2015-08-27 | 2015-11-30
2023-02-14 | 2010 | Defense Health Agency | 72481 | 72481-05 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2015-09-16
2023-02-14 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G-11-P-0208 | 46000 | 46000 | 2011-11-01 | 2011-11-01
2023-02-14 | 2010 | Defense Health Agency | 72481 | 76558-01 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540000 | 623000 | 2014-10-24 | 2014-10-24
2023-02-14 | 2010 | Defense Health Agency | 72481 | 77293-01 | 2014-10-20 | 2019-07-10 | Ross Group | W9126G-19-C-0031, W9126G-19-C-0032 | 34029000 | 34126000 | 2020-10-18 | 2021-12-28
2023-02-14 | 2010 | Defense Health Agency | 72481 | 81407-01 | 2015-03-30 | 2019-10-28 | Justin J Reeves, LLC | W9126G-20-C-0003 | 2842000 | 2854402 | 2021-05-04 | 2021-05-04
2023-02-14 | 2018 | Defense Health Agency | 72481 | 91301 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 251330000 | 206136000 | 2016-11-26 | 2020-02-29
2023-02-14 | 2017 | Defense Health Agency | 72738 |  | 2017-01-19 | 2017-09-13 | JE Dunn Construction Company | W912-BV-17-C-0014 | 67487000 | 67762000 | 2020-10-31 | 2022-04-01
2023-02-14 | 2020 | Defense Health Agency | 72742 |  | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005a | 212000 | 212000 | 2021-09-26 | 2022-06-30
2023-02-14 | 2020 | Defense Health Agency | 72742 | 72742-01 | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005b | 305000 | 305000 | 2022-06-10 | 2022-09-12
2023-02-14 | 2020 | Defense Health Agency | 72742 | 72742-02 | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005c | 978000 | 978000 | 2023-03-24 | 2023-03-24
2023-02-14 | 2012 | Defense Health Agency | 72754 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22835000 | 2014-07-29 | 2016-09-02
2023-02-14 | 2013 | Defense Health Agency | 72808 |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703000 | 19971000 | 2015-03-16 | 2017-04-28
2023-02-14 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, ABG4 P00058 | 2359000 | 3563000 | 2016-04-30 | 2017-04-30
2023-02-14 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00085 | 33888000 | 34523000 | 2021-03-31 | 2021-12-07
2023-02-14 | 2012 | Defense Health Agency | 76007 | 72662-02 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00102 | 56039000 | 56985000 | 2021-01-30 | 2022-12-09
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-01 | 2012-02-01 | 2012-03-15 | Joint Venture Bautra Baugesellschaft mbH / SRS Service GmbH | W912GB-10-C-0031, ABG4 P00023 | 261000 | 261000 | 2014-04-04 | 2014-04-04
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-02 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00030 | 681000 | 1747000 | 2014-10-29 | 2015-01-21
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-03 | 2012-02-01 | 2012-03-15 | Depenbrock Bau GmbH & Co. KG | W912GB-10-C-0031, ABG4 P00043 | 5321000 | 6586000 | 2016-04-30 | 2017-07-30
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-04 | 2012-02-01 | 2012-03-15 | Hermanns RTE Rohrleitungs- undd Tiefbau Erfurt GmbH | W912GB-10-C-0031, ABG4 P00062 | 5444000 | 6199000 | 2016-12-15 | 2017-12-15
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-05 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH (ABG4 P00033) | W912GB-10-C-0031, ABG4 P00033 | 141234 | 142000 | 2015-03-30 | 2015-05-01
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-06 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH | W912GB-10-C-0031, ABG4 P00031 | 17713 | 17713 | 2014-12-31 | 2014-12-31
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-07 | 2012-02-01 | 2012-03-15 | FRG/CREOS GmbH | W912GB-10-C-0031, ABG4 P00032 | 473000 | 492000 | 2014-10-16 | 2014-10-16
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-08 | 2012-02-01 | 2012-03-15 | FRG/Omexom GA Sud GmbH | W912GB-10-C-0031, ABG4 P00066 | 62000 | 68000 | 2016-10-30 | 2016-12-30
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB-10-C-0031, P00071 | 419000 | 419000 | 2020-03-30 | 2020-03-30
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-10 | 2012-02-01 | 2012-03-15 | FRG/Zeppelin STREIF Baulogistik GmbH | W912GB-10-C-0031, ABG4 P00039 | 5235000 | 7121000 | 2025-12-30 | 2027-10-30
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-13 | 2012-02-01 | 2012-03-15 | FRG/Deutsche Telekom Technik GmbH | W912GB-10-C-0031, ABG4 P00037 | 1000 | 1000 | 2014-12-31 | 2014-12-31
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-14 | 2015-08-19 | 2015-08-31 | FRG: Ed. Zublin AG / Gilbane Germany GmbH | W912GB-10-C-0031 | 913702000 | 913702000 | 2027-12-30 | 2027-12-30
2023-02-14 | 2012 | Defense Health Agency | 76007 | 76007-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 21988000 | 24175000 | 2018-07-30 | 2018-12-30
2023-02-14 | 2012 | Defense Health Agency | 76007 | 81412 | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 14187000 | 2025-12-30 | 2027-10-30
2023-02-14 | 2018 | Defense Health Agency | 76934 |  | 2018-05-24 | 2019-02-08 | Gilbane Federal JV | W912HN-19-C-3002 | 10042000 | 2562000 | 2021-03-14 | 2021-07-12
2023-02-14 | 2014 | Defense Health Agency | 77000 |  | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR-15-C-0015 | 206445000 | 218443000 | 2019-02-19 | 2023-02-01
2023-02-14 | 2014 | Defense Health Agency | 77000 | 77000-10 | 2021-07-31 | 2021-09-26 | BeltBuilt LLC | W912DR-21-C-0052 | 3052000 | 3052000 | 2022-12-06 | 2022-12-06
2023-02-14 | 2018 | Defense Health Agency | 77140 |  | 2018-06-22 | 2019-01-24 | Walga Ross Group JV | W912DQ-19-F-4003 | 10585000 | 10530000 | 2020-09-16 | 2021-10-29
2023-02-14 | 2012 | Defense Health Agency | 77154 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 66430000 | 78005000 | 2016-12-06 | 2023-03-31
2023-02-14 | 2016 | Defense Health Agency | 77986 |  | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005a | 23667000 | 28704000 | 2019-06-04 | 2023-02-10
2023-02-14 | 2016 | Defense Health Agency | 77986 | 77986-01 | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005b | 662000 | 662000 | 2023-04-13 | 2023-04-13
2023-02-14 | 2016 | Defense Health Agency | 77986 | 77986-02 | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005c | 889000 | 889000 | 2023-10-01 | 2023-10-01
2023-02-14 | 2018 | Defense Health Agency | 77987 |  | 2018-03-22 | 2018-09-21 | JJ Brun JV LLC | W9128F-18-0281 | 11396000 | 13579000 | 2021-06-17 | 2023-08-26
2023-02-14 | 2016 | Defense Health Agency | 78150 |  | 2015-11-05 | 2016-08-08 | Caddell-Nan joint Venture | N62742 16 C 1312 | 79722000 | 83356000 | 2018-12-21 | 2020-08-31
2023-02-14 | 2013 | Defense Health Agency | 80306 |  | 2013-07-25 | 2013-09-12 | G-W Management Services Inc. | N40080 10 D 0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25
2023-02-14 | 2013 | Defense Health Agency | 80306 | 80306-01 | 2014-03-15 | 2016-09-01 | Whiting Turner Contracting Co | N40080 16 C 0172 | 29435000 | 30582000 | 2017-12-10 | 2018-08-31
2023-02-14 | 2016 | Defense Health Agency | 80412 |  | 2016-01-27 | 2016-05-17 | Swinerton Builders | W9128A-16-C-0004 | 26084000 | 27183000 | 2017-12-08 | 2019-03-29
2023-02-14 | 2016 | Defense Health Agency | 80412 | 80412-01 | 2016-10-21 | 2018-02-08 | Hensel-Phelps Const. Co. | W9128A-18-C-0001 | 74987000 | 73999000 | 2020-05-21 | 2020-11-20
2023-02-14 | 2016 | Defense Health Agency | 80412 | 80412-02 | 2020-07-31 | 2020-09-21 | Su-Mo Builders Inc. | W9128A-16-D-0011 TO W9128A20F0067 | 1484000 | 1484000 | 2023-02-06 | 2023-02-06
2023-02-14 | 2017 | Defense Health Agency | 80906 |  | 2017-05-23 | 2017-09-28 | Whiting Turner Contracting Co | N40080-17-C-0039 | 26338000 | 31518000 | 2019-05-10 | 2021-08-31
2023-02-14 | 2018 | Defense Health Agency | 80906 | 81420 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080-20-C0001 | 570000000 | 329948000 | 2026-03-01 | 2027-05-13
2023-02-14 | 2020 | Defense Health Agency | 80906 | 85667 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080-20-C0001 | 570000000 | 329948000 | 2026-03-01 | 2027-05-13
2023-02-14 | 2016 | Defense Health Agency | 81422 |  | 2017-11-27 | 2018-09-24 | United Excel Corportation (now StructSure Projects) | W9126G-18-C-0077 | 40138000 | 70215000 | 2021-04-01 | 2023-06-19
2023-02-14 | 2015 | Defense Health Agency | 81430 |  | 2016-06-20 | 2018-01-18 | JE Dunn Construction Company | W9127S-13-D-6001 TO W91236-18-F-0014 | 52181000 | 56349000 | 2021-03-18 | 2023-01-12
2023-02-14 | 2014 | Defense Health Agency | 81436 |  | 2015-08-25 | 2016-03-17 | Contrack Watts Inc. | W912ER-11-D-0009-0012 | 24784000 | 26972000 | 2019-04-20 | 2020-01-20
2023-02-14 | 2018 | Defense Health Agency | 86204 |  | 2020-04-21 | 2020-07-08 | Kimball Construction Company, Inc | W912BU20C0033 | 3408000 | 3922000 | 2022-02-03 | 2022-05-15
2023-02-14 | 2019 | Defense Health Agency | 86943 |  | 2019-09-10 | 2019-12-15 | NVE-HHI JV | W9128F-20-C-0006 | 3384000 | 3384000 | 2021-06-15 | 2021-07-15
2023-02-14 | 2016 | Defense Health Agency | 86953 |  | 2016-07-25 | 2017-03-23 | M.A. Mortenson Company | W912QR-17-C-0009 | 54817000 | 66624000 | 2021-06-23 | 2023-01-04
2023-02-14 | 2019 | Defense Health Agency | 89838 |  | 2019-07-09 | 2019-09-30 | DeMaria Building Co | N4008519C9124 | 28729000 | 28563000 | 2021-10-30 | 2023-07-31
2023-02-14 | 2019 | Defense Health Agency | 89839 |  | 2021-06-14 | 2021-08-25 | RQ-AECOM JV | N6945018D1317 | 5634000 | 5642000 | 2023-06-02 | 2023-12-15
2023-02-14 | 2019 | Defense Health Agency | 89902 |  | 2020-02-25 | 2020-08-18 | Korte Construction Company | N6945019D0910 | 21894000 | 22699000 | 2022-09-03 | 2023-09-28
2023-02-14 | 2020 | Defense Health Agency | 89906 |  | 2020-08-04 | 2020-09-30 | Soltek Pacific Construction Co. | N6247318D5855 | 15767000 | 16012000 | 2022-10-30 | 2022-11-21
2023-02-14 | 2018 | Defense Health Agency | 91884 |  | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 303714000 | 2023-10-13 | 2023-11-08
2023-02-14 | 2021 | Defense Health Agency | 91884 | 77168 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 303714000 | 2023-10-13 | 2023-10-25
2023-02-14 | 2020 | Defense Health Agency | 91884 | 94335 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 303714000 | 2023-10-13 | 2023-10-25
2023-02-14 | 2022 | Defense Health Agency | 91884 | 97762 | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 303714000 | 2023-10-13 | 2023-10-25
2023-02-14 | 2020 | Defense Health Agency | 92005 |  | 2021-11-30 | 2022-06-07 | Nan, INC | N62742-22-C-1328 | 20925000 | 23211000 | 2024-02-18 | 2024-02-18
2023-02-14 | 2019 | Defense Health Agency | 93298 |  | 2020-02-17 | 2020-08-25 | GCBJV1, Pensacola, FL | N6945019D0920 | 3859000 | 3921000 | 2021-09-10 | 2023-01-13
2023-02-28 | 2021 | Defense Information Systems Agency | 01DISA21 |  | 2021-04-16 | 2021-09-13 | The Korte Company | W912PL21C0013 | 27737733 | 27737733 | 2023-09-13 | 2024-01-18
2023-02-28 | 2013 | Defense Information Systems Agency | 13DISA01 |  | 2015-08-05 | 2015-08-19 | Bauamt Reutlingen | W912GB-15-C-011 | 2219820 | 2219820 | 2015-08-19 | 2023-03-31
2023-02-28 | 2014 | Defense Information Systems Agency | 14DISA01 |  | 2017-04-12 | 2017-07-13 | Heartwood Pacific, LLC | N6274217F0307 | 1781248 | 1781248 | 2018-12-31 | 2022-11-30
2023-02-28 | 2015 | Defense Information Systems Agency | 15DISA02 |  | 2018-05-02 | 2018-08-09 | Cockram Construction Australia Pty Ltd. 675 Victoria Street, Abbotsford Victoria 3067, Austrialia | N6274218C1306 | 8794967 | 12189000 | 2019-03-31 | 2020-03-31
2023-02-28 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11
2022-09-30 | 2021 | Defense Intelligence Agency | 2019030003 |  | 2021-02-22 | 2022-03-23 | Dewberry | W912DY20D0029 | 21325000 | 18564000 | 2025-06-30 | 2025-06-30
2023-02-15 | 2017 | DLA Defense Distribution Center | DDCX1701A |  | 2017-12-08 | 2018-04-12 | Carouthers Construction | W9126G-18-C-0018 | 36159560 | 36510784 | 2020-06-25 | 2021-05-24
2023-02-15 | 2017 | DLA Defense Distribution Center | DDCX1701B |  | 2018-04-03 | 2018-08-30 | Bristol Construction Services | W9126G-18-C-0066 | 3881804 | 3881804 | 2020-09-30 | 2020-09-30
2023-02-15 | 2019 | DLA Defense Distribution Center | DDCX1901 |  | 2019-03-26 | 2019-06-19 | B. L. Harbert International, LLC | W9126-G19-C-0029 | 67142000 | 67909992 | 2023-01-30 | 2022-11-18
2023-02-15 | 2020 | DLA Defense Energy Support Center | DECS1913 |  | 2020-05-28 | 2020-09-15 | Nova Group, Inc. | W9128F20C0039 / 59008927 | 22124000 | 22201000 | 2022-11-30 | 2023-07-30
2023-02-15 | 2013 | DLA Defense Energy Support Center | DESC1301 |  | 2014-11-13 | 2015-08-28 | Rockford Corporation | W912QR-15-C-0026 | 36448000 | 37081000 | 2017-03-30 | 2022-11-30
2023-02-15 | 2017 | DLA Defense Energy Support Center | DESC1513 |  | 2019-03-08 | 2019-04-30 | Structural Associates, Inc | W9127821C0012 | 14758000 | 14809000 | 2022-10-17 | 2023-03-31
2023-02-15 | 2017 | DLA Defense Energy Support Center | DESC1513 |  | 2018-04-30 | 2018-09-20 | Bhate Zapata | W912EP-16-D-0008 | 1300000 | 4390000 | 2019-07-06 | 2023-01-03
2023-02-15 | 2016 | DLA Defense Energy Support Center | DESC1603 |  | 2017-12-12 | 2018-08-10 | Bietergemeinschaft UVB | W912GB-14-C-0005 | 6125000 | 6125000 | 2019-06-02 | 2019-10-02
2023-02-15 | 2016 | DLA Defense Energy Support Center | DESC1605 |  | 2016-06-23 | 2017-06-02 | STRUCTURAL ASSOCIATES | W912BU16R00370006 | 23170900 | 23170900 | 2019-06-16 | 2020-05-03
2023-02-15 | 2018 | DLA Defense Energy Support Center | DESC1608 |  | 2018-10-21 | 2019-03-20 | MEB | N69450-19-c-1304 | 20334000 | 20334000 | 2021-08-31 | 2021-03-01
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC1609 |  | 2018-08-01 | 2019-06-28 | SES Energy Services, LLC | W9128F19C0032 &#x2f; 42718510 | 7499541 | 7716000 | 2019-07-06 | 2021-11-30
2023-02-15 | 2017 | DLA Defense Energy Support Center | DESC1611 |  | 2017-11-29 | 2017-11-30 | NOVA Group, Inc | N62473-18-C-2202 | 26868000 | 26926198 | 2020-03-10 | 2021-07-15
2023-02-15 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | w | 20577000 | 20577000 | 2019-01-07 | 2025-01-24
2023-02-15 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | N62470-17-C-5003 | 20577000 | 21577000 | 2020-11-30 | 2025-01-24
2023-02-15 | 2016 | DLA Defense Energy Support Center | DESC1702 |  | 2017-02-09 | 2017-09-30 | MEB General Contractors, Inc. | W91299-17-C-0011 | 20973000 | 21083000 | 2019-06-25 | 2021-10-24
2023-02-15 | 2017 | DLA Defense Energy Support Center | DESC1704 |  | 2017-07-25 | 2017-09-29 | San Juan Construction, Inc. | W9128A17C0008 | 63298000 | 66345000 | 2020-11-07 | 2026-10-31
2023-02-15 | 2017 | DLA Defense Energy Support Center | DESC1705 |  | 2017-05-29 | 2017-05-30 | Black Construction/Mace Internation | N62742-17-C-1313 | 26978100 | 28361127 | 2019-06-29 | 2019-09-23
2023-02-15 | 2017 | DLA Defense Energy Support Center | DESC1707 |  | 2017-01-30 | 2017-08-07 | ASRC Builders | W911KB-17-C-0030 | 4088355 | 4129621 | 2018-12-15 | 2021-12-15
2023-02-15 | 2018 | DLA Defense Energy Support Center | DESC1709 |  | 2018-09-20 | 2018-09-21 | Tfs-Aptim JV | N40192-18-C-1300 | 21445996 | 21445996 | 2019-12-15 | 2022-01-30
2023-02-15 | 2018 | DLA Defense Energy Support Center | DESC1714 |  | 2018-08-09 | 2019-06-07 | Creative Times Inc | W9123819C0010 | 19480000 | 20000032 | 2021-07-07 | 2021-09-15
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC17U3 |  | 2019-07-02 | 2019-09-12 | The Ross Group | N6247319F5135 | 4384341 | 4883963 | 2021-01-15 | 2022-12-31
2023-02-15 | 2018 | DLA Defense Energy Support Center | DESC1805 |  | 2018-05-21 | 2018-12-27 | TOA CORPORATION | W912HV19C0003 / 51379145 | 33455000 | 35455000 | 2021-04-01 | 2022-02-05
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC18S2 |  | 2019-07-16 | 2019-09-20 | Diversified Constr. | W912BV19C0022 / 56986550 | 6186000 | 6717000 | 2020-12-31 | 2022-02-28
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC1902 |  | 2020-08-12 | 2021-07-29 | Reliable Contracting Group, LLC | W9127S21C6002 | 15406000 | 15974000 | 2023-03-01 | 2023-10-18
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC1905 |  | 2019-05-01 | 2019-08-01 | WHH Nisqually-Garco JV 2 | W912DW19C0017 / 56848368 | 22312000 | 23258000 | 2022-05-31 | 2021-11-16
2023-02-15 | 2021 | DLA Defense Energy Support Center | DESC1907 |  | 2022-02-01 | 2022-04-05 | Garco Construction, Inc. | W912QR21C0019 | 19652000 | 19883000 | 2022-05-03 | 2024-04-20
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC1909 |  | 2019-08-01 | 2019-09-30 | Rockford | W9123619C0044 / 56765125 | 8330000 | 8453000 | 2020-12-04 | 2022-05-05
2023-02-15 | 2020 | DLA Defense Energy Support Center | DESC1912 |  | 2020-08-25 | 2021-06-29 | Bodell Construction Company | W912BV21C0012 | 19796000 | 19820000 | 2023-11-12 | 2024-05-31
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC1914 |  | 2019-07-16 | 2019-09-30 | UST General Contracting, LLC | W9123619C0043 / 56747799 | 4917000 | 5048000 | 2020-12-04 | 2023-01-31
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC19I1 |  | 2019-03-29 | 2019-06-10 | Diversified Construction of Oklahoma | W9126G19C0026 / 56924533 | 8330000 | 8453000 | 2020-09-30 | 2021-09-30
2023-02-15 | 2019 | DLA Defense Energy Support Center | DESC19S2 |  | 2019-05-31 | 2019-06-28 | Dawson Pond | PLACE HOLDER | 6193389 | 7190107 | 2022-10-03 | 2022-02-28
2023-02-15 | 2020 | DLA Defense Energy Support Center | DESC19S4 |  | 2020-04-28 | 2020-09-11 | SGJV, LLC | W9127820C0027 &#x2f; 68228349 | 13051000 | 13051000 | 2021-10-16 | 2023-03-03
2023-02-15 | 2021 | DLA Defense Energy Support Center | DESC2002 |  | 2021-01-04 | 2021-05-21 | Garco | N4425521R20000014 | 54249000 | 54387326 | 2024-01-20 | 2024-05-22
2023-02-15 | 2021 | DLA Defense Energy Support Center | DESC2003 |  | 2021-06-25 | 2021-09-22 | MEB General Contractors | W9126G22C0003 | 28013000 | 28057000 | 2023-01-12 | 2023-05-31
2023-02-15 | 2020 | DLA Defense Energy Support Center | DESC20S1 |  | 2020-08-10 | 2021-04-14 | Rockford Corporation | W912WJ21C0009 | 1162500000 | 1162500000 | 2022-08-15 | 2025-01-21
2023-02-15 | 2021 | DLA Defense Energy Support Center | DESC2101 |  | 2021-06-25 | 2021-09-22 | Nova Group Inc | W9123821C0026 | 14320000 | 14554000 | 2023-10-09 | 2024-01-19
2023-02-15 | 2021 | DLA Defense Energy Support Center | DESC2104A |  | 2021-01-01 | 2021-09-30 | WHH Nisqually-Garco JV 2 | W912DW21C0021 | 9845000 | 9845000 | 2023-05-23 | 2023-05-25
2023-02-15 | 2021 | DLA Defense Energy Support Center | DESC2104B |  | 2021-01-01 | 2021-02-04 | WHH Nisqually-Garco JV 2 | W912DW21C0022 | 10279000 | 10279000 | 2023-05-23 | 2024-04-20
2023-02-15 | 2022 | DLA Defense Energy Support Center | DESC21E1 |  | 2017-07-25 | 2017-09-29 | MAEDA ONAKA JOINT VENTURE | W912HV22C0015 | 14634000 | 14634000 | 2022-04-29 | 2022-09-22
2023-02-15 | 2015 | DLA Defense National Stockpile Center | DESC1507 |  | 2015-02-02 | 2015-09-30 | Structural Associates Inc | W9128F-15-C-0032 | 17178089 | 17906802 | 2017-03-23 | 2023-05-16
2023-02-15 | 2015 | DLA Defense Supply Center Richmond | DSCR1501 |  | 2016-11-08 | 2017-12-14 | SAW Contracting | W91236-18-C-0008 | 6253160 | 7509000 | 2019-08-12 | 2019-11-13
2023-02-15 | 2020 | DLA Defense Supply Center Richmond | DSCR1901 |  | 2020-05-28 | 2020-12-11 | Manhattan Construction Company | W9123621C2019 | 87092000 | 87454000 | 2023-11-14 | 2024-03-05
2023-02-06 | 2014 | DoD Education Activity | AM00021 |  | 2016-11-07 | 2017-11-20 | John C. Grimberg CO., Inc. | N4008018C0006 | 52553000 | 48781252 | 2020-01-09 | 2020-10-13
2023-02-06 | 2019 | DoD Education Activity | AM00029 |  | 2020-06-29 | 2020-09-30 | A&K Construction Inc | W912QR-20-C-0054/33717697 | 56070000 | 57888635 | 2023-09-09 | 2024-04-30
2023-02-06 | 2016 | DoD Education Activity | AM00033 |  | 2016-07-25 | 2017-03-01 | DOBCO, Inc. | W912DS-17-C-0005/44966911 | 48535000 | 50878598 | 2020-03-05 | 2020-01-06
2023-02-06 | 2014 | DoD Education Activity | AM00046 | 246 | 2013-02-06 | 2016-03-16 | J&J Contractors & Engineers, Inc. | W912WJ-17-C-0004/57439943 | 35970000 | 37442688 | 2019-09-09 | 2019-08-20
2023-02-06 | 2017 | DoD Education Activity | AM00047 |  | 2018-01-03 | 2019-02-27 | Dobco, Inc. | W912BU-19-C-0017/53356011 | 47962590 | 49803671 | 2021-12-24 | 2025-01-31
2023-02-06 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/39179628 | 25629526 | 27304618 | 2020-06-10 | 2021-10-15
2023-02-06 | 2016 | DoD Education Activity | AM00048 | 8 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/54560299 | 4286000 | 4286000 | 2020-06-10 | 2021-10-15
2023-02-06 | 2016 | DoD Education Activity | AM00048 | 9 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/54560300 | 15500000 | 15500000 | 2020-06-10 | 2021-10-15
2023-02-06 | 2015 | DoD Education Activity | AM00051 |  | 2016-02-26 | 2017-03-29 | Walsh Federal, LLC | N40085 17 C 8322 | 47374000 | 86916000 | 2020-03-28 | 2021-04-09
2023-02-06 | 2015 | DoD Education Activity | AM00103 |  | 2015-09-15 | 2016-07-01 | Munilla Construction Management, LLC | N6945016C1612 | 21000000 | 127527000 | 2018-11-26 | 2021-10-09
2023-02-06 | 2016 | DoD Education Activity | AM00110 |  | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278-12-D-0037/41084584 | 27895686 | 37550921 | 2020-05-28 | 2022-11-04
2023-02-06 | 2016 | DoD Education Activity | AM00110 | 27 | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278-12-D-0037/57076763 | 11115000 | 11115000 | 2020-05-28 | 2022-11-04
2023-02-06 | 2016 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N6247016C6003 | 9233000 | 16044000 | 2019-03-27 | 2021-04-21
2023-02-06 | 2021 | DoD Education Activity | AM00182 |  | 2021-04-29 | 2021-08-11 | Messer Construction | W912QR-21-C-0033/59023911 | 58989000 | 59180617 | 2025-09-28 | 2024-10-09
2023-02-06 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029/27243529 | 77816984 | 90402371 | 2019-05-08 | 2019-10-31
2023-02-06 | 2012 | DoD Education Activity | EU00031 | 89 | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029/59013541 | 0 | 202458 | 2019-05-08 | 2019-10-31
2023-02-06 | 2013 | DoD Education Activity | EU00034 |  | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006/44599966 | 41569129 | 44097700 | 2018-12-24 | 2019-06-13
2023-02-06 | 2013 | DoD Education Activity | EU00034 | 45 | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006/50005397 | 0 | 388829 | 2018-12-24 | 2019-06-13
2023-02-06 | 2014 | DoD Education Activity | EU00037 | 1 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/52029300 | 89535967 | 98418110 | 2021-03-29 | 2021-06-28
2023-02-06 | 2017 | DoD Education Activity | EU00039 |  | 2019-03-19 | 2019-09-16 | LBB Kaiserslautern | W912GB-15-C-0013/47316927 | 48012330 | 48792920 | 2024-10-22 | 2025-04-18
2023-02-06 | 2014 | DoD Education Activity | EU00040 |  | 2016-10-21 | 2017-05-09 | LBB Kaiserslautern | W912GB-12-C-0025/52029339 | 43000974 | 49725985 | 2020-01-12 | 2021-03-26
2023-02-06 | 2014 | DoD Education Activity | EU00049 |  | 2015-11-24 | 2016-06-03 | Federal Republic of Germany | W912GB-12-C-0041/50728702 | 56573871 | 57755552 | 2021-07-23 | 2021-08-23
2023-02-06 | 2016 | DoD Education Activity | EU00051 | 51 | 2017-04-30 | 2017-07-20 | Staatliches Hochbauamt Reutlingen | W912GB-12-C-0030/54892650 | 46915286 | 55168577 | 2021-01-23 | 2022-05-30
2023-02-06 | 2015 | DoD Education Activity | EU00064 |  | 2017-06-29 | 2017-09-21 | Joint Venture WMV Brussels American School | W912GB-17-C-0018/44739768 | 28765482 | 29313101 | 2020-10-24 | 2023-10-23
2023-02-06 | 2016 | DoD Education Activity | EU00068 |  | 2017-09-05 | 2018-04-20 | Staatliches Hochbauamt Amberg | W912GB-12-C-0036/57200363 | 33667431 | 37420732 | 2021-03-16 | 2022-10-31
2023-02-06 | 2018 | DoD Education Activity | EU00117 |  | 2019-05-01 | 2019-09-27 | ICM SPA | N6247019C5007 | 36391000 | 39919000 | 2022-01-27 | 2023-05-08
2023-02-06 | 2017 | DoD Education Activity | EU00183 |  | 2020-02-12 | 2020-07-22 | Staatliches Hochbauamt Amberg | W912GB-17-C-0023/ 58997935 | 1304645 | 1430758 | 2021-04-29 | 2022-04-29
2023-02-06 | 2015 | DoD Education Activity | PA00017 |  | 2016-07-15 | 2016-12-23 | Nippo Corporation | W912HV-17-C-0004/37880445 | 61521811 | 88612824 | 2020-11-17 | 2023-08-01
2023-02-06 | 2015 | DoD Education Activity | PA00022 |  | 2018-09-21 | 2019-07-29 | Nippo Corporation | W912HV19C0007/36943919 | 52447552 | 50682194 | 2022-08-05 | 2022-08-05
2023-02-06 | 2015 | DoD Education Activity | PA00023 |  | 2016-06-13 | 2016-11-22 | NES PACIFIC LIMITED LIABILITY CO. | W912HV-17-C-0002/37064811 | 27722277 | 30649314 | 2019-05-28 | 2022-12-31
2023-02-06 | 2017 | DoD Education Activity | PA00032 |  | 2017-06-22 | 2017-12-22 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV18C0002/37880684 | 72844929 | 80278415 | 2021-02-15 | 2023-08-15
2023-02-15 | 2019 | Marine Corps Active | M00146130F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 33831000 | 35827000 | 2025-08-12 | 2025-08-12
2023-02-15 | 2019 | Marine Corps Active | M00146142F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 40771000 | 43410000 | 2025-08-12 | 2025-08-12
2023-02-15 | 2019 | Marine Corps Active | M00146162F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 41270000 | 47404000 | 2025-08-12 | 2025-08-12
2023-02-15 | 2015 | Marine Corps Active | M00146193 |  | 2015-06-17 | 2016-12-22 | GARNEY COMPANIES, INC. | N4008517C8315 AWD | 55798000 | 96297000 | 2021-11-23 | 2022-06-21
2023-02-15 | 2016 | Marine Corps Active | M00146194 |  | 2016-03-29 | 2016-08-31 | M A MORTENSON COMPANY | N4008516C5506 AWD | 28561000 | 29444000 | 2019-01-29 | 2019-01-29
2023-02-15 | 2022 | Marine Corps Active | M00146197 |  | 2021-09-13 | 2022-04-26 | WALSH FEDERAL, LLC | N4008522C0016 AWD | 0 | 80467000 | 2025-06-24 | 2025-06-24
2023-02-15 | 2019 | Marine Corps Active | M00146199 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N4008520C8501 AWD | 5813000 | 147821000 | 2022-07-14 | 2023-04-02
2023-02-15 | 2016 | Marine Corps Active | M00146222 |  | 2019-01-23 | 2019-04-18 | SAUER, INC. | N4008519C9021 | 21793000 | 23426000 | 2021-06-10 | 2021-06-10
2023-02-15 | 2019 | Marine Corps Active | M00146235 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N4008520C8501 AWD | 53073000 | 116807000 | 2022-07-14 | 2023-04-02
2023-02-15 | 2020 | Marine Corps Active | M00146246F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 17747042 | 19613000 | 2025-08-12 | 2025-08-12
2023-02-15 | 2020 | Marine Corps Active | M00146249 |  | 2020-10-26 | 2021-02-18 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008516D6303 N4008521F4682 | 1368000 | 2680000 | 2022-03-05 | 2022-08-11
2023-02-15 | 2019 | Marine Corps Active | M00146254F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 30990000 | 32645000 | 2025-08-12 | 2025-08-12
2023-02-15 | 2018 | Marine Corps Active | M00146766 |  | 2018-09-04 | 2018-09-29 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008516D6303 N4008518F7217 | 2468000 | 2579000 | 2020-01-08 | 2021-04-12
2023-02-15 | 2018 | Marine Corps Active | M00146990 |  | 2019-04-30 | 2021-05-27 | WHITING-TURNER CONTRACTING CO | N4008521C0035 AWD | 22677000 | 44026000 | 2023-05-01 | 2023-05-10
2023-02-15 | 2020 | Marine Corps Active | M00243312 |  | 2020-03-02 | 2020-05-29 | BRISTOL DESIGN BUILD SERVICES, LLC | N6247317D4627 N6247320F4683 | 9525039 | 10662000 | 2022-02-03 | 2022-08-22
2023-02-15 | 2017 | Marine Corps Active | M00263403 |  | 2017-01-27 | 2018-07-31 | KORTE CONSTRUCTION COMPANY | N4008518C0640 AWD | 30382000 | 48434000 | 2021-02-28 | 2022-03-18
2023-02-15 | 2019 | Marine Corps Active | M00263404 |  | 2019-02-14 | 2019-07-10 | R. C. CONSTRUCTION | N4008519C9017 AWD | 36938000 | 38189000 | 2021-08-17 | 2022-03-23
2023-02-15 | 2018 | Marine Corps Active | M00264542 |  | 2018-08-08 | 2019-05-30 | ARCHER WESTERN FEDERAL JV | N4008019C0023 AWD | 21419000 | 22114000 | 2020-10-30 | 2022-08-30
2023-02-15 | 2014 | Marine Corps Active | M00264588 |  | 2017-02-10 | 2018-09-29 | WHITING-TURNER CONTRACTING CO | N4008018C0034 AWD | 23040000 | 56386000 | 2020-06-06 | 2021-04-09
2023-02-15 | 2015 | Marine Corps Active | M00264635 |  | 2016-05-16 | 2016-11-16 | G-W MANAGEMENT SERVICES, LLC | N4008017C0014 AWD | 10883000 | 12785000 | 2018-03-25 | 2021-07-29
2023-02-15 | 2014 | Marine Corps Active | M00264677 |  | 2015-10-28 | 2016-03-31 | HARKINS BUILDERS INC. | N4008016C0151 AWD | 27064000 | 54513000 | 2018-01-05 | 2018-10-23
2023-02-15 | 2020 | Marine Corps Active | M00264719 |  | 2020-10-26 | 2021-03-22 | CLARK CONSTRUCTION GROUP, LLC. | N4008021C0005 AWD | 586000 | 97866000 | 2023-07-05 | 2023-07-05
2023-02-15 | 2019 | Marine Corps Active | M00264724 |  | 2019-06-05 | 2019-08-15 | G-W MANAGEMENT SERVICES, LLC | N4008019D0015 N4008019F4870 | 14142000 | 16268000 | 2021-01-30 | 2021-07-01
2023-02-15 | 2020 | Marine Corps Active | M00264733 |  | 2020-07-23 | 2020-09-29 | TUCKMAN-BARBEE CONSTRUCTION | N4008019D0018 N4008020F5390 | 3040000 | 6328000 | 2021-11-10 | 2022-12-30
2023-02-15 | 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274215C1305 AWD | 51071000 | 92632000 | 2018-08-11 | 2021-02-03
2023-02-15 | 2014 | Marine Corps Active | M00318863 |  | 2015-07-14 | 2016-09-19 | CONTRACK WATTS, INC | N6274216C1325 AWD | 50583000 | 92941000 | 2019-04-17 | 2020-07-07
2023-02-15 | 2018 | Marine Corps Active | M00318877 |  | 2020-05-20 | 2020-09-23 | NIKING CORP. | N6274220C1304 AWD | 34513000 | 38767000 | 2022-01-07 | 2022-08-15
2023-02-15 | 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720000 | 17403000 | 2016-12-18 | 2019-10-24
2023-02-15 | 2018 | Marine Corps Active | M00318887 |  | 2018-04-04 | 2018-12-28 | KIEWIT INFRASTRUCTURE WEST CO. | N6274219C1321 AWD | 18697000 | 38454000 | 2020-08-19 | 2021-01-25
2023-02-15 | 2016 | Marine Corps Active | M00318902 |  | 2016-05-27 | 2016-11-18 | NOVA GROUP INC | N6274217C1320 AWD | 24797000 | 58379000 | 2019-06-06 | 2021-08-13
2023-02-15 | 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 47645000 | 71621000 | 2020-09-18 | 2021-12-20
2023-02-15 | 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 53999000 | 103519000 | 2020-09-18 | 2021-12-20
2023-02-15 | 2017 | Marine Corps Active | M00318923 |  | 2017-04-07 | 2017-08-21 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6274217C1307 AWD | 72494000 | 141846000 | 2020-03-08 | 2022-05-21
2023-02-15 | 2019 | Marine Corps Active | M00318946 |  | 2018-11-20 | 2019-05-31 | HENSEL PHELPS CONSTRUCTION CO. | N6274219C1303 AWD | 62559000 | 124330000 | 2021-09-07 | 2022-08-27
2023-02-15 | 2021 | Marine Corps Active | M00318947 |  | 2021-12-08 | 2022-03-25 | HAKO PLUMBING, INC. | N6247820D4036 N6247822F4095 | 0 | 9621000 | 2023-04-24 | 2023-04-24
2023-02-15 | 2021 | Marine Corps Active | M00318964 |  | 2021-11-04 | 2022-01-18 | HAKO PLUMBING, INC. | N6247820D4036 N6247822F4051 | 0 | 8985000 | 2023-04-19 | 2023-04-19
2023-02-15 | 2019 | Marine Corps Active | M00681079 |  | 2019-07-24 | 2019-12-12 | ORION CONSTRUCTION CORPORATION | N6247320C0612 AWD | 35918000 | 68056000 | 2022-05-30 | 2022-11-20
2023-02-15 | 2020 | Marine Corps Active | M006811090 |  | 2020-04-16 | 2020-09-24 | DPR-RQ CONSTRUCTION, LLC | N6247320C0055 AWD | 53546419 | 83228000 | 2024-01-07 | 2024-01-07
2023-02-15 | 2021 | Marine Corps Active | M006811090A |  | 2020-05-15 | 2021-03-23 | DPR-RQ CONSTRUCTION, LLC | N6247320C0055 PC000009 | 0 | 0 | 2024-01-07 | 2024-01-07
2023-02-15 | 2021 | Marine Corps Active | M006811130 |  | 2020-07-23 | 2021-02-18 | HARPER CONSTRUCTION COMPANY, INC | N6247321D1206 N6247321F4378 | 42661879 | 51318000 | 2023-05-13 | 2023-10-20
2023-02-15 | 2018 | Marine Corps Active | M006811310 |  | 2018-04-12 | 2018-09-27 | HARPER CONSTRUCTION COMPANY, INC | N6247317D0817 | 62328000 | 91424000 | 2020-10-10 | 2023-03-26
2023-02-15 | 2018 | Marine Corps Active | M006811599 |  | 2019-01-15 | 2019-02-27 | ORION CONSTRUCTION CORPORATION | N6247318D5860 N6247319F4359 | 1876000 | 2451000 | 2020-02-26 | 2020-04-16
2023-02-15 | 2019 | Marine Corps Active | M006811901 |  | 2018-11-27 | 2019-05-02 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F4561 | 46146000 | 50285000 | 2022-06-09 | 2022-12-09
2023-02-15 | 2020 | Marine Corps Active | M006812000 |  | 2020-05-28 | 2020-12-17 | WHITING-TURNER CONTRACTING CO | N6247318D5858 N6247321F4212 | 3056000 | 63952000 | 2025-02-14 | 2025-02-14
2023-02-15 | 2019 | Marine Corps Active | M00681334 |  | 2019-06-21 | 2019-08-22 | I E PACIFIC INC | N6247317D4628 N6247319F5136 | 14684000 | 15818000 | 2021-08-06 | 2022-03-18
2023-02-15 | 2019 | Marine Corps Active | M006815001 |  | 2019-01-30 | 2019-04-09 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 | 9032000 | 9460000 | 2020-10-15 | 2022-01-12
2023-02-15 | 2019 | Marine Corps Active | M006815002 |  | 2019-02-05 | 2019-03-25 | SYNERGY ELECTRIC COMPANY INC | N6247319D2430 | 3326000 | 6886000 | 2020-03-30 | 2020-03-20
2023-02-15 | 2019 | Marine Corps Active | M00681574 |  | 2019-07-09 | 2019-08-22 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 N6247319F5115 | 12715000 | 13522000 | 2021-06-07 | 2021-12-10
2023-02-15 | 2014 | Marine Corps Active | M00681970 |  | 2014-07-01 | 2015-12-30 | SOLPAC CONSTRUCTION INC | N6247310D5411 0012 | 19459000 | 27790000 | 2018-04-27 | 2021-09-14
2023-02-15 | 2017 | Marine Corps Active | M60169464 |  | 2017-02-23 | 2017-06-29 | THE HASKELL COMPANY | N4008517C8327 AWD | 78310000 | 160976000 | 2020-07-13 | 2022-07-08
2023-02-15 | 2022 | Marine Corps Active | M60169492 |  | 2022-02-17 | 2022-07-14 | BLAKELAND, LLC | N4008518D0629 N4008522F5350 | 0 | 2731000 | 2023-06-08 | 2023-06-08
2023-02-15 | 2018 | Marine Corps Active | M62204930 |  | 2017-03-07 | 2018-04-18 | M A MORTENSON COMPANY | N6247318D5850 N6247318F4497 | 23592000 | 46390000 | 2020-05-02 | 2020-05-17
2023-02-15 | 2020 | Marine Corps Active | M626131005
2023-02-15 | 2018 | Marine Corps Active | M626131006
2023-02-15 | 2021 | Marine Corps Active | M626131010U |  | 2021-06-01 | 2021-09-09 | MECCS MITOMO JV | N4008420D0071 N4008421F4605 | 0 | 986000 | 2022-07-06 | 2023-04-20
2023-02-15 | 2017 | Marine Corps Active | M626131701
2023-02-15 | 2019 | Marine Corps Active | M626131901 |  | 2022-04-06 | 2022-09-30 | NIPPO CORPORATION | N4008420D0072 N4008422F4724 | 0 | 15914000 | 2024-07-26 | 2024-07-26
2023-02-15 | 2020 | Marine Corps Active | M626132001 |  | 2020-11-13 | 2021-02-11 | SANKYO REINETSU CO., LTD. | N4008420D0073 N4008421F4127 | 18797000 | 18947000 | 2023-07-02 | 2023-07-02
2023-02-15 | 2016 | Marine Corps Active | M62613604
2023-02-15 | 2018 | Marine Corps Active | M62974539 |  | 2018-05-02 | 2018-07-03 | WHITING-TURNER CONTRACTING CO | N6247317D0822 N6247318F4783 | 37962000 | 40267000 | 2020-06-28 | 2022-04-04
2023-02-15 | 2016 | Marine Corps Active | M62974602 |  | 2017-03-31 | 2017-07-27 | STRAUB CONSTRUCTION, INC. | N6247316D1887 N6247317F4044 | 43119000 | 43933000 | 2019-06-30 | 2020-06-22
2023-02-15 | 2017 | Marine Corps Active | M62974612 |  | 2017-07-12 | 2019-06-13 | HARPER CONSTRUCTION COMPANY, INC | N6247316D1881 N6247319F4705 | 62293000 | 124495000 | 2022-06-06 | 2023-05-17
2023-02-15 | 2018 | Marine Corps Active | M670011043 |  | 2021-05-10 | 2022-07-08 | ENVIRONMENTAL CHEMICAL CORPORATION | N4008522C0026 AWD | 0 | 71742000 | 2025-08-01 | 2025-08-01
2023-02-15 | 2019 | Marine Corps Active | M670011199F |  | 2019-10-15 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 19142000 | 21733000 | 2024-10-12 | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | M670011203F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 27688000 | 29033000 | 2024-09-30 | 2025-09-27
2023-02-15 | 2016 | Marine Corps Active | M670011280 |  | 2016-12-16 | 2017-05-30 | CADDELL CONSTRUCTION CO. (DE), LLC | N4008517C8325 AWD | 47882000 | 67195000 | 2019-06-24 | 2023-08-10
2023-02-15 | 2019 | Marine Corps Active | M670011300F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 17826000 | 20596000 | 2024-10-12 | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | M670011312F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 55017000 | 59603000 | 2024-09-30 | 2025-09-27
2023-02-15 | 2018 | Marine Corps Active | M670011320 |  | 2018-08-09 | 2018-09-28 | SAUER, INC. | N4008518C0610 AWD | 37174000 | 71715000 | 2020-10-23 | 2022-10-23
2023-02-15 | 2020 | Marine Corps Active | M670011338F |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N4008520C0145 AWD | 51246000 | 55461000 | 2025-05-27 | 2025-12-27
2023-02-15 | 2019 | Marine Corps Active | M670011387F |  | 2019-10-09 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N4008520C8505 AWD | 64921000 | 70305000 | 2025-03-06 | 2025-03-06
2023-02-15 | 2018 | Marine Corps Active | M670011479 |  | 2018-11-06 | 2019-06-14 | SAUER, INC. | N4008519C9053 AWD | 3247000 | 3677000 | 2020-10-26 | 2021-09-30
2023-02-15 | 2020 | Marine Corps Active | M670011483 |  | 2020-07-17 | 2020-09-25 | SAUER, INC. | N4008520D0035 N4008520F6732 | 11460484 | 12503000 | 2021-09-28 | 2022-06-22
2023-02-15 | 2020 | Marine Corps Active | M670011495 |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N4008520C0145 AWD | 35517314 | 37825000 | 2023-03-05 | 2023-04-07
2023-02-15 | 2018 | Marine Corps Active | M670011498 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N4008514D7742 N4008519F4172 | 3135000 | 3498000 | 2019-11-09 | 2023-02-25
2023-02-15 | 2018 | Marine Corps Active | M670011503 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N4008514D7742 N4008519F4172 | 3833000 | 4259000 | 2019-11-09 | 2023-02-25
2023-02-15 | 2019 | Marine Corps Active | M670011505F |  | 2020-01-23 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N4008520C8505 AWD | 66036000 | 68006000 | 2019-10-25 | 2025-03-06
2023-02-15 | 2020 | Marine Corps Active | M670011506F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 28045000 | 31059000 | 2024-09-30 | 2025-09-27
2023-02-15 | 2020 | Marine Corps Active | M670011507F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 17318680 | 21647000 | 2024-05-27 | 2025-02-07
2023-02-15 | 2019 | Marine Corps Active | M670011509F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 33391000 | 44156000 | 2017-05-30 | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | M670011512F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 135347000 | 164668000 | 2025-05-27 | 2025-12-27
2023-02-15 | 2020 | Marine Corps Active | M670011518F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 29242000 | 30483000 | 2024-09-30 | 2025-09-27
2023-02-15 | 2020 | Marine Corps Active | M670011519F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 36463000 | 37910000 | 2024-09-30 | 2025-09-27
2023-02-15 | 2019 | Marine Corps Active | M670011520F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 15383000 | 17724000 | 2019-10-25 | 2027-07-20
2023-02-15 | 2019 | Marine Corps Active | M670011522F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 26607000 | 29586000 | 2019-10-25 | 2027-07-20
2023-02-15 | 2019 | Marine Corps Active | M670011524F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 14143000 | 16383000 | 2021-06-16 | 2027-07-20
2023-02-15 | 2019 | Marine Corps Active | M670011525F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 7375000 | 9319000 | 2020-12-29 | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | M670011527F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 48103000 | 50324000 | 2025-05-27 | 2025-12-27
2023-02-15 | 2020 | Marine Corps Active | M670011529F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 22970805 | 27209000 | 2024-10-12 | 2027-07-20
2023-02-15 | 2020 | Marine Corps Active | M670011533F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 43802000 | 45419000 | 2024-09-30 | 2025-09-27
2023-02-15 | 2019 | Marine Corps Active | M670011603F
2023-02-15 | 2019 | Marine Corps Active | M670011604F |  | 2021-10-06 | 2022-05-31 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008518D1128 N6247022F4060 | 0 | 0 | 2023-11-22 | 2023-11-22
2023-02-15 | 2020 | Marine Corps Active | M670011800 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N4008521C0017 AWD | 5850000 | 128028000 | 2026-07-23 | 2027-05-09
2023-02-15 | 2021 | Marine Corps Active | M670011800A |  | 2020-07-10 | 2021-03-02 | ARCHER WESTERN FEDERAL JV | N4008521C0017 P00002 | 102629610 | 0 | 2026-07-23 | 2027-05-09
2023-02-15 | 2022 | Marine Corps Active | M670011800B |  | 2020-07-10 | 2022-05-26 | ARCHER WESTERN FEDERAL JV | N4008521C0017 P00021 | 0 | 0 | 2026-07-23 | 2027-05-09
2023-02-15 | 2020 | Marine Corps Active | M670011801 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N4008521C0017 AWD | 5850000 | 62323000 | 2026-07-23 | 2027-05-09
2023-02-15 | 2020 | Marine Corps Active | M67001378F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 223502000 | 267580000 | 2024-10-12 | 2025-02-18
2023-02-15 | 2016 | Marine Corps Active | M67001686 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 3640000 | 7418000 | 2018-04-06 | 2021-04-22
2023-02-15 | 2020 | Marine Corps Active | M67001695F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 67658000 | 74328000 | 2024-10-12 | 2025-02-18
2023-02-15 | 2020 | Marine Corps Active | M67001707F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 79978000 | 86697000 | 2024-10-12 | 2025-02-18
2023-02-15 | 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159000 | 21211000 | 2019-02-01 | 2019-02-01
2023-02-15 | 2020 | Marine Corps Active | M67001728F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 48575000 | 56608000 | 2024-10-12 | 2025-02-18
2023-02-15 | 2016 | Marine Corps Active | M67001729 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 1885000 | 4910000 | 2018-04-06 | 2021-04-22
2023-02-15 | 2020 | Marine Corps Active | M67001883F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 54587000 | 58867000 | 2024-09-30 | 2025-09-27
2023-02-15 | 2019 | Marine Corps Active | M67004947 |  | 2019-08-07 | 2020-01-31 | THE HASKELL COMPANY | N4008520C8504 AWD | 29418000 | 31081000 | 2022-05-04 | 2022-09-12
2023-02-15 | 2018 | Marine Corps Active | M67004971 |  | 2017-12-12 | 2018-03-15 | DRACE CONSTRUCTION CORP. | N4008516D5524 N4008518F5082 | 1982000 | 3836000 | 2019-07-05 | 2019-07-05
2023-02-15 | 2016 | Marine Corps Active | M67004972 |  | 2016-12-14 | 2017-03-22 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N6945016D1112 WE01 | 8625000 | 9065000 | 2019-01-28 | 2019-02-23
2023-02-15 | 2021 | Marine Corps Active | M67004976 |  | 2021-10-25 | 2022-03-22 | U-SMC/DEMARIA JV1, LLC | N6945019D0921 N6945022F0122 | 0 | 5220000 | 2023-07-15 | 2023-07-15
2023-02-15 | 2018 | Marine Corps Active | M67004977 |  | 2018-07-18 | 2019-03-07 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008519C9126 | 23298000 | 47977000 | 2021-04-29 | 2021-05-27
2023-02-15 | 2016 | Marine Corps Active | M67029007 |  | 2016-10-25 | 2017-04-19 | TIDEWATER, INC | N4008017C0024 AWD | 1257000 | 2635000 | 2018-04-19 | 2020-07-30
2023-02-15 | 2016 | Marine Corps Active | M673991232 |  | 2017-06-27 | 2017-09-26 | PROCAL ELECTRIC INC | N6247316D1861 N6247317F4699 | 9329000 | 12127000 | 2019-04-19 | 2021-04-23
2023-02-15 | 2018 | Marine Corps Active | M67399192 |  | 2017-10-17 | 2018-09-29 | CDM CONSTRUCTORS INC | N6247318C4602 AWD | 55390000 | 104994000 | 2021-09-28 | 2023-02-15
2023-02-15 | 2015 | Marine Corps Active | M67399222 |  | 2016-02-22 | 2016-08-31 | AT&T GOVERNMENT SOLUTIONS, INC | N6247316C0601 AWD | 12948000 | 25107000 | 2019-03-04 | 2020-02-14
2023-02-15 | 2015 | Marine Corps Active | M67400213
2023-02-15 | 2016 | Marine Corps Active | M67400606 |  | 2016-07-20 | 2016-09-15 | NAVY STANDARD DOCUMENT | N4008516C5505 AWD | 8792000 | 8792000 | 2019-08-03 | 2018-03-26
2023-02-15 | 2017 | Marine Corps Active | M67400807
2023-02-15 | 2021 | Marine Corps Active | M67400901U |  | 2021-05-18 | 2021-07-01 | ACTY CO.,LTD. | N4008421C8000 AWD | 3417000 | 6519000 | 2022-03-14 | 2022-03-14
2023-02-15 | 2016 | Marine Corps Active | M67604132 |  | 2016-07-08 | 2016-08-31 | REYES CONSTRUCTION INC | N6247314D0068 0008 | 2887000 | 4598000 | 2017-10-30 | 2017-10-30
2023-02-15 | 2020 | Marine Corps Active | M67695009 |  | 2020-06-26 | 2020-09-16 | THE CLEMENT GROUP LLC | N6945019D0918 N6945020F0894 | 10933245 | 12764000 | 2022-03-25 | 2023-01-27
2023-02-15 | 2017 | Marine Corps Active | M67865198 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 35632000 | 41726000 | 2020-01-14 | 2020-06-26
2023-02-15 | 2018 | Marine Corps Active | M67865198 | M67865198A | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 79399000 | 87647000 | 2020-01-14 | 2020-06-26
2023-02-15 | 2017 | Marine Corps Active | M67865203 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 38707000 | 46833000 | 2020-01-14 | 2020-06-26
2023-02-15 | 2018 | Marine Corps Active | M67865210 |  | 2018-05-16 | 2018-08-30 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247318F4873 | 34513000 | 78490000 | 2020-05-20 | 2021-02-26
2023-02-15 | 2019 | Marine Corps Active | M67865222 |  | 2018-11-16 | 2019-03-14 | Granite Construction, Inc | N62473-19-C-5826 | 11358000 | 23942000 | 2020-09-27 | 2021-02-06
2023-02-15 | 2019 | Marine Corps Active | M67865238 |  | 2019-01-03 | 2019-03-08 | Teehee Engineering Inc. | N6247319C2425 | 4828000 | 7218000 | 2020-04-06 | 2020-04-06
2023-02-15 | 2017 | Marine Corps Active | M67865249 |  | 2017-09-19 | 2017-12-18 | R A BURCH CONSTRUCTION CO INC | N6247316D1884 N6247318F4138 | 32536000 | 37041000 | 2019-09-24 | 2020-10-01
2023-02-15 | 2021 | Marine Corps Active | M67865280 |  | 2021-04-26 | 2021-06-30 | DE LA FUENTE CONSTRUCTION, INC. | N6247321D1220 N6247321F4960 | 0 | 10803000 | 2023-03-07 | 2023-07-14
2023-02-15 | 2019 | Marine Corps Active | N41557270 |  | 2019-01-25 | 2019-09-12 | GILBANE SMCC ECC LLC | N6274219D1331 N6274219F9926 | 27191000 | 50578000 | 2022-03-25 | 2022-09-09
2023-02-15 | 2022 | Marine Corps Active | N41557280 |  | 2021-05-24 | 2022-05-04 | BLACK CONSTRUCTION-TUTOR PERINI JV | N6274219D1328 N6274222F9926 | 0 | 55817000 | 2024-08-22 | 2024-08-22
2023-02-15 | 2019 | Marine Corps Active | N41557290 |  | 2021-06-21 | 2022-01-11 | HENSEL PHELPS CONSTRUCTION CO. | N6274219D1332 N6274222F9921 | 0 | 45140000 | 2025-01-10 | 2025-01-10
2023-02-15 | 2019 | Marine Corps Active | N41557295 |  | 2019-04-15 | 2019-09-16 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274219C1301 AWD | 18002000 | 33042000 | 2021-12-04 | 2021-12-04
2023-02-15 | 2021 | Marine Corps Active | N41557296 |  | 2020-08-18 | 2021-03-17 | CORE TECH-HDCC-KAJIMA LLC | N6274219D1330 N6274221F9928 | 17683000 | 19129000 | 2023-03-28 | 2023-08-13
2023-02-15 | 2018 | Marine Corps Active | N41557601 |  | 2017-06-30 | 2018-05-16 | HENSEL PHELPS CONSTRUCTION CO. | N6274218C1316 AWD | 75233000 | 145395000 | 2020-10-02 | 2021-10-22
2023-02-15 | 2016 | Marine Corps Active | N41557715 |  | 2016-04-06 | 2017-08-24 | BLACK CONSTRUCTION CORP. | N6274217C1319 AWD | 123661000 | 204681000 | 2020-11-26 | 2023-01-08
2023-02-15 | 2019 | Marine Corps Active | N41557735 |  | 2019-06-11 | 2021-09-28 | BLACK CONSTRUCTION CORP. | N6274221C1346 AWD | 0 | 6214000 | 2024-10-25 | 2024-10-25
2023-02-15 | 2022 | Marine Corps Active | N61159305 |  | 2021-03-23 | 2022-05-04 | BLACK CONSTRUCTION-TUTOR PERINI JV | N6274219D1328 N6274222F9930 | 0 | 83156000 | 2024-08-22 | 2024-08-22
2023-02-15 | 2022 | Marine Corps Active | N61159306 |  | 2021-10-15 | 2022-05-04 | GILBANE SMCC ECC LLC | N6274219D1331 N6274222F9927 | 0 | 85734000 | 2024-09-06 | 2024-09-06
2023-02-15 | 2022 | Marine Corps Active | N61159307 |  | 2021-04-20 | 2022-04-14 | GILBANE SMCC ECC LLC | N6274219D1331 N6274222F9920 | 0 | 39958000 | 2024-08-02 | 2024-08-02
2023-02-15 | 2022 | Marine Corps Active | N61159310 |  | 2021-04-30 | 2022-04-27 | GILBANE SMCC ECC LLC | N6274219D1331 N6274222F9929 | 0 | 45959000 | 2024-08-18 | 2024-08-18
2023-02-15 | 2021 | Marine Corps Active | N61159311 |  | 2020-09-14 | 2021-03-15 | HENSEL PHELPS CONSTRUCTION CO. | N6274219D1332 N6274221F9927 | 27795000 | 28402000 | 2023-08-23 | 2023-08-23
2023-02-15 | 2021 | Marine Corps Active | N61159312 |  | 2020-06-22 | 2021-03-22 | CORE TECH-HDCC-KAJIMA LLC | N6274221C1335 AWD | 0 | 54804000 | 2024-03-12 | 2024-03-12
2023-02-15 | 2022 | Marine Corps Active | N61159326 |  | 2021-08-17 | 2022-04-01 | HENSEL PHELPS CONSTRUCTION CO. | N6274219D1332 N6274222F9925 | 0 | 40909000 | 2024-07-25 | 2024-07-25
2023-02-15 | 2021 | Marine Corps Active | N61159802 |  | 2021-04-08 | 2021-08-16 | CADDELL-NAN A JOINT VENTURE | N6274219D1329 N6274221F9933 | 0 | 41459000 | 2023-12-07 | 2023-12-07
2023-02-15 | 2021 | Marine Corps Active | N61159803 |  | 2021-04-08 | 2021-08-13 | CHUGACH CONSOLIDATED SOLUTIONS, LLC | N6274221C1315 AWD | 0 | 9649000 | 2022-08-27 | 2022-09-04
2023-02-15 | 2021 | Marine Corps Active | N61159804 |  | 2020-02-24 | 2021-03-22 | CORE TECH-HDCC-KAJIMA LLC | N6274221C1335 AWD | 36105000 | 36494000 | 2024-03-12 | 2024-03-12
2023-02-15 | 2019 | Marine Corps Active | N62813216 |  | 2019-09-06 | 2020-02-03 | RORE, INC. | N6247818D4024 N6274220F4001 | 17897000 | 31465000 | 2020-12-29 | 2022-09-30
2023-02-15 | 2018 | Marine Corps Reserve | M67861650 |  | 2018-12-13 | 2019-03-19 | NAVY STANDARD DOCUMENT | USACE | 11741000 | 11065000 | 2020-11-20 | 2020-11-20
2023-02-15 | 2020 | Marine Corps Reserve | M68479102
2023-02-15 | 2017 | Marine Corps Reserve | M68479135 |  | 2018-08-16 | 2019-01-22 | OAK GROUP, INC., THE | N4008517D5038 N4008519F4510 | 2109000 | 2306000 | 2020-01-28 | 2020-10-31
2023-02-15 | 2021 | Marine Corps Reserve | M68479303 |  | 2021-09-14 | 2022-02-02 | HESS CONSTRUCTION COMPANY, INC. | N4008022C0005 AWD | 0 | 36137000 | 2024-09-17 | 2024-12-13
2023-02-15 | 2020 | Marine Corps Reserve | M68479811
2023-02-15 | 2016 | Marine Corps Reserve | N50092152 |  | 2019-05-02 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N4008519C9061 AWD | 18501000 | 18948000 | 2021-09-14 | 2022-02-04
2023-02-15 | 2020 | Marine Corps Reserve | N83447091 |  | 2020-06-25 | 2020-08-28 | ENCANTO FACILITY SERVICES 2, LLC | N6945020D0036 N6945020F1277 | 2614000 | 3278000 | 2021-08-27 | 2022-01-02
2023-02-15 | 2020 | Marine Corps Reserve | N83447181 |  | 2020-06-25 | 2020-09-25 | ENCANTO FACILITY SERVICES 2, LLC | N6945020D0036 N6945020F1278 | 0 | 1209000 | 2021-09-26 | 2022-08-10
2023-02-15 | 2020 | Marine Corps Reserve | N83447222 |  | 2020-05-08 | 2020-09-24 | N6945020C2575 AWD | N6945020C2575 AWD | 1763000 | 1921000 | 2021-09-20 | 2021-09-20
2023-01-31 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 114390000 | 2015-08-30 | 2016-05-12
2023-01-31 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 66900000 | 2015-08-30 | 2016-05-12
2023-01-31 | 2016 | Missile Defense Agency | 640 |  | 2015-06-10 | 2016-02-10 | AMEC PROGRAMS, INC. | W912GB-16-C-0005 | 141906057 | 171152000 | 2018-05-30 | 2023-04-27
2023-01-31 | 2017 | Missile Defense Agency | 653 |  | 2017-02-01 | 2017-07-25 | AMES 1/Conam JV | W911KB-17-C-0029 | 6954581 | 8207372 | 2019-08-14 | 2021-09-29
2023-01-31 | 2017 | Missile Defense Agency | 657 |  | 2016-12-14 | 2017-04-28 | UNIT-ASRC Construction, LLC | W911KB-17-C-0002 | 112949720 | 119078184 | 2019-08-23 | 2020-06-01
2023-01-31 | 2017 | Missile Defense Agency | 657 |  | 2017-11-14 | 2018-02-15 | STG Pacific, LLC | W911KB-18-C-0015 | 24399601 | 24558572 | 2019-08-30 | 2019-06-27
2023-01-31 | 2017 | Missile Defense Agency | 657 |  | 2018-04-05 | 2018-09-07 | White Mountain Construction Company LLC | W911KB-18-R-0006 | 13335000 | 14660442 | 2020-09-30 | 2020-09-29
2023-01-31 | 2019 | Missile Defense Agency | 659 |  | 2018-10-10 | 2019-03-08 | CP03-UNIT-ASRC Construction LLC | W911KB-19-C-0001 | 128657500 | 136771860 | 2021-06-30 | 2022-07-28
2023-01-31 | 2019 | Missile Defense Agency | 659 |  | 2019-09-23 | 2019-12-18 | CP04-RED POINT CONSTRUCTION, LLC | W911KB-20-C-0002 | 13820000 | 15307457 | 2021-06-14 | 2021-08-16
2023-01-31 | 2017 | Missile Defense Agency | 673 |  | 2017-04-15 | 2017-08-03 | Indyne, Inc. | W912DY-11-D-0002 | 877752 | 1098939 | 2019-06-27 | 2023-01-31
2023-01-31 | 2018 | Missile Defense Agency | 674 |  | 2018-02-05 | 2018-04-10 | CP01-Alaska Aggregate Products, LLC | W911KB-18-C-0023 | 2600710 | 2549000 | 2018-06-30 | 2018-06-30
2023-01-31 | 2018 | Missile Defense Agency | 674 |  | 2018-01-05 | 2018-05-07 | CP02-Brice Civil Constructors | W911KB-18-C-0028 | 18965310 | 19525000 | 2018-10-30 | 2018-10-11
2023-01-31 | 2018 | Missile Defense Agency | 674 |  | 2018-02-16 | 2018-06-07 | CP02TP-Construction Services SATOC | W912DY-14-D-0042 | 2432439 | 2432439 | 2018-10-31 | 2018-10-11
2023-01-31 | 2018 | Missile Defense Agency | 674 |  | 2018-04-17 | 2018-07-20 | CP03-Watterson Construction Company | W911KB-18-C-0030 | 28807000 | 32705772 | 2020-11-01 | 2021-03-29
2023-01-31 | 2018 | Missile Defense Agency | 674 |  | 2018-09-23 | 2018-12-20 | CP04-NEESER CONSTRUCTION, INC | W911KB-19-C-0006 | 83991000 | 102021058 | 2021-09-30 | 2023-03-10
2023-01-31 | 2019 | Missile Defense Agency | 679 |  | 2022-02-15 | 2022-05-02 | ASRC Builders, LLC | W911KB-22-C-0009 | 8508953 | 12289761 | 2023-10-21 | 2023-10-21
2023-01-31 | 2021 | Missile Defense Agency | 680 |  | 2020-09-28 | 2021-03-17 | Davis Constructors & Engineers, Inc | W911KB-21-C-0012 | 45487063 | 47343682 | 2023-01-31 | 2024-06-14
2023-01-31 | 2021 | Missile Defense Agency | 689 |  | 2020-06-01 | 2021-09-30 | AYTEKIN SEROL INSAAT TAAHHUT MUHENDISLIK | W912GB-18-F-0186 | 3260896 | 0 | 2023-10-01 | 2023-12-22
2023-02-03 | 2021 | National Geospatial-Intelligence Agency | ARN13-0020 |  | 2021-05-18 | 2021-09-30 | SES Civil and Environmental LLC | W912DQ-21-C-7000 | 3749520 | 4114040 | 2023-11-17 | 2023-11-17
2023-01-31 | 2018 | National Geospatial-Intelligence Agency | NGA-016A |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ-17-R-7000 | 319965869 | 340192808 | 2023-10-19 | 2024-06-28
2023-01-31 | 2018 | National Geospatial-Intelligence Agency | NGA-016A-IPO |  | 2019-04-07 | 2019-07-10 | Modular Management Group (MMG) | W912DQ-17-C-7002 | 3146064 | 3152224 | 2024-07-08 | 2024-07-08
2023-01-31 | 2019 | National Geospatial-Intelligence Agency | NGA-016B |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ-17-R-7000 | 315507977 | 352073304 | 2023-10-19 | 2024-06-28
2022-12-31 | 2016 | National Security Agency | 30583 |  | 2015-09-30 | 2016-06-17 | Clark Construction | W912DR-16-C-0013 | 616311000 | 717944264 | 2020-09-10 | 2022-02-23
2022-12-31 | 2019 | National Security Agency | 32100 |  | 2019-03-18 | 2020-01-30 | Hensel-Phelps | W912DR-20-C-0004 | 34227105 | 36443740 | 2022-11-17 | 2022-11-17
2022-12-31 | 2022 | National Security Agency | 34490 |  | 2021-07-28 | 2022-04-11 | Henry Brothers Ltd | Z9D7393Y18 | 13704230 | 13704230 | 2023-06-14 | 2023-06-14
2022-12-31 | 2017 | National Security Agency | 35161 |  | 2021-08-09 | 2021-08-24 | Grunley Construction | W912DR-21-C-0016 | 21386000 | 21686971 | 2024-03-28 | 2024-03-28
2022-12-31 | 2019 | National Security Agency | 35168 |  | 2018-10-04 | 2019-03-28 | Hensel-Phelps | W912DR-19-C-0013 | 650261000 | 676013342 | 2023-04-30 | 2023-05-09
2022-12-31 | 2022 | National Security Agency | 38440/38441 |  | 2020-10-15 | 2022-05-26 | Hensel-Phelps | W912DR-22-C-0018 | 301612000 | 301612000 | 2026-06-15 | 2026-06-15
2022-12-31 | 2022 | National Security Agency | 38608 |  | 2020-09-30 | 2022-04-13 | Balfour Beatty Construction, LLC | W912DR-22-C-0012 | 692844325 | 85279976 | 2026-05-10 | 2026-05-10
2023-02-15 | 2016 | Navy Active | M006811220 |  | 2016-06-24 | 2016-11-30 | J. R. FILANC CONSTRUCTION COMPANY,INC | N6247317C3403 AWD | 39860000 | 85107000 | 2019-03-30 | 2019-03-30
2023-02-15 | 2016 | Navy Active | M62613603 |  | 2016-03-01 | 2018-12-18 | Awarded by Other Agency | N40084USACE02 AWD | 8904000 | 8904000 | 2020-07-08 | 2021-03-12
2023-02-15 | 2014 | Navy Active | N00128714 |  | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N4008518C8707 AWD | 32940000 | 98302000 | 2020-08-14 | 2020-10-23
2023-02-15 | 2017 | Navy Active | N00128714 | N00128714A | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N4008518C8707 AWD | 37695000 | 36045000 | 2020-08-14 | 2020-10-23
2023-02-15 | 2020 | Navy Active | N00129898 |  | 2020-04-07 | 2020-09-29 | WEEKS MARINE, INC | N4008520C0074 AWD | 2468000 | 76994000 | 2022-10-26 | 2023-01-31
2023-02-15 | 2016 | Navy Active | N00204723 |  | 2016-11-23 | 2017-06-28 | EMR, INC. | N6945017D0507 N6945017F1003 | 20056000 | 38540000 | 2019-10-16 | 2020-09-20
2023-02-15 | 2019 | Navy Active | N00207674 |  | 2019-02-08 | 2019-05-17 | DESBUILD INCORPORATEDDBA DES BUILD | N6945016D1111 N6945019F0712 | 3036000 | 6168000 | 2020-10-13 | 2021-05-20
2023-02-15 | 2019 | Navy Active | N00207711 |  | 2019-07-18 | 2019-09-13 | UP-SIDE MANAGEMENT COMPANY | N6945019C5648 AWD | 2323000 | 4425000 | 2020-09-14 | 2020-09-14
2023-02-15 | 2018 | Navy Active | N00213211 |  | 2019-05-03 | 2021-05-13 | KORTE CONSTRUCTION COMPANY | N6945021C0019 AWD | 52266000 | 124153000 | 2023-12-29 | 2023-12-29
2023-02-15 | 2021 | Navy Active | N00213211A
2023-02-15 | 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151000 | 15765000 | 2018-01-08 | 2018-01-08
2023-02-15 | 2019 | Navy Active | N00213720 |  | 2019-04-17 | 2019-09-26 | THE HASKELL COMPANY | N6945019D0909 N6945019F0874 | 30995000 | 32797000 | 2021-12-13 | 2023-06-29
2023-02-15 | 2018 | Navy Active | N00213731 |  | 2019-06-25 | 2019-09-19 | BURNS & MCDONNELL ENGINEERINGCOMPANY, INC. | N6945016D0100 N6945019F0105 | 9097000 | 17147000 | 2020-11-30 | 2022-11-30
2023-02-15 | 2018 | Navy Active | N00213741 |  | 2019-05-15 | 2019-09-27 | KORTE CONSTRUCTION COMPANY | N6945019C0903 AWD | 63582000 | 122831000 | 2022-01-17 | 2022-10-28
2023-02-15 | 2018 | Navy Active | N00216450 |  | 2018-05-25 | 2018-09-05 | URS GROUP, INC. | N6247013D6022 N6247018F4121 | 50430000 | 54135000 | 2021-09-04 | 2023-01-31
2023-02-15 | 2018 | Navy Active | N00216485 |  | 2018-06-28 | 2018-08-22 | GFP GROUP, L.L.C. | N6945016D0615 N6945018F2384 | 4213000 | 8897000 | 2020-03-14 | 2023-02-28
2023-02-15 | 2019 | Navy Active | N002450888 |  | 2019-01-02 | 2019-03-28 | HELIX ELECTRIC, INC. | N6247316D3201 0010 | 36336000 | 91338000 | 2021-08-18 | 2023-01-29
2023-02-15 | 2019 | Navy Active | N00245110 |  | 2019-04-19 | 2019-08-12 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247319F5055 | 14817000 | 14712000 | 2021-03-23 | 2021-03-23
2023-02-15 | 2017 | Navy Active | N00245312 |  | 2017-04-25 | 2017-06-29 | SYNERGY ELECTRIC COMPANY INC | N6247316D1862 N6247317F4054 | 2527000 | 4925000 | 2018-12-15 | 2018-12-15
2023-02-15 | 2019 | Navy Active | N00245440 |  | 2019-05-01 | 2019-06-14 | MANSON CONSTRUCTION CO | N6247319C1208 AWD | 47724000 | 105282000 | 2021-10-27 | 2021-10-31
2023-02-15 | 2021 | Navy Active | N00245443 |  | 2021-03-05 | 2021-04-30 | MANSON CONSTRUCTION CO | N6247321D1406 N6247321F4668 | 3164000 | 114501000 | 2023-09-17 | 2023-09-17
2023-02-15 | 2015 | Navy Active | N00245800 |  | 2015-06-15 | 2015-09-17 | S & R CONSTRUCTIONA JOINT VENTURE | N6247315C1604 AWD | 41838000 | 120929000 | 2019-04-10 | 2019-04-10
2023-02-15 | 2017 | Navy Active | N002461017 |  | 2017-03-22 | 2017-09-28 | WEST POINT CONTRACTORS, INC. | N6247317C0815 AWD | 2943000 | 5564000 | 2018-12-12 | 2018-12-12
2023-02-15 | 2019 | Navy Active | N002461018 |  | 2019-04-03 | 2019-07-25 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247319C1211 AWD | 53283000 | 97717000 | 2021-05-28 | 2022-07-25
2023-02-15 | 2020 | Navy Active | N002461024 |  | 2019-10-16 | 2020-06-11 | HARPER CONSTRUCTION COMPANY, INC | N6247320C0553 AWD | 69801056 | 78202000 | 2023-01-01 | 2023-03-03
2023-02-15 | 2021 | Navy Active | N00246762 |  | 2021-01-05 | 2021-11-04 | REYES CONSTRUCTION INC | N6247318D5862 N6247322F4006 | 0 | 9209000 | 2022-11-03 | 2022-11-03
2023-02-15 | 2017 | Navy Active | N00246947 |  | 2017-01-30 | 2017-03-30 | REYES CONSTRUCTION INC | N6247314D0068 0009 | 11659000 | 41787000 | 2018-10-06 | 2020-03-31
2023-02-15 | 2018 | Navy Active | N00246988 |  | 2018-06-06 | 2018-08-30 | RQ CONSTRUCTION, LLC | N6247317D0820 N6247318F5040 | 32923000 | 66419000 | 2021-03-22 | 2022-10-05
2023-02-15 | 2017 | Navy Active | N00246991 |  | 2016-11-23 | 2017-03-30 | RQ-DPR JV | N6247317C0808 AWD | 61541000 | 150028000 | 2019-04-23 | 2021-04-30
2023-02-15 | 2017 | Navy Active | N00620240 |  | 2016-06-14 | 2017-08-09 | BETHEL-WEBCOR JV-1 | N4425517D4032 N4425517F4132 | 28966000 | 59514000 | 2020-03-26 | 2021-01-19
2023-02-15 | 2019 | Navy Active | N00620253 |  | 2018-10-12 | 2019-03-11 | BETHEL-WEBCOR JV-1 | N4425517D4032 XN4425519F4123 | 12949000 | 14945000 | 2020-11-28 | 2021-07-06
2023-02-15 | 2017 | Navy Active | N00620256 |  | 2018-04-05 | 2019-01-30 | RQ CONSTRUCTION, LLC | N4425519C0003 AWD | 45981000 | 95303000 | 2021-07-19 | 2021-10-29
2023-02-15 | 2019 | Navy Active | N00620258 |  | 2018-11-14 | 2019-02-26 | TOMPCO, INC | N4425517D4014 N4425519F4091 | 7114000 | 7561000 | 2021-03-08 | 2021-01-29
2023-02-15 | 2019 | Navy Active | N32414106 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N4008519C9057 AWD | 66625000 | 133091000 | 2022-02-13 | 2023-02-17
2023-02-15 | 2019 | Navy Active | N324141098 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N4008519C9057 AWD | 3142000 | 3520000 | 2022-02-13 | 2023-02-17
2023-02-15 | 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 AWD | 34317000 | 85167000 | 2016-11-23 | 2021-11-19
2023-02-15 | 2019 | Navy Active | N32443256 |  | 2021-09-02 | 2021-11-29 | W.M. JORDAN COMPANY INC. | N4008519D9089 N4008522F4169 | 0 | 26330000 | 2024-01-28 | 2024-01-28
2023-02-15 | 2018 | Navy Active | N32443257 |  | 2017-11-03 | 2018-09-17 | RQ CONSTRUCTION, LLC | N4008518C1107 AWD | 73055000 | 142148000 | 2021-06-18 | 2022-08-31
2023-02-15 | 2016 | Navy Active | N32443614 |  | 2017-06-01 | 2017-12-15 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 45614000 | 49379000 | 2021-04-15 | 2021-06-30
2023-02-15 | 2017 | Navy Active | N32443614 | N32443614A | 2017-06-01 | 2017-12-14 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 2624000 | 2584000 | 2021-04-15 | 2021-06-30
2023-02-15 | 2020 | Navy Active | N32443653 |  | 2020-04-16 | 2020-09-04 | MEB GENERAL CONTRACTORS, INC. | N4008520C0063 AWD | 46986935 | 52019000 | 2023-06-17 | 2023-08-22
2023-02-15 | 2022 | Navy Active | N32443678 |  | 2022-03-29 | 2022-09-23 | MEB GENERAL CONTRACTORS, INC. | N4008522C0047 AWD | 0 | 82034000 | 2026-09-08 | 2026-09-08
2023-02-15 | 2019 | Navy Active | N324461074 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N4008520C8500 AWD | 43523000 | 49932000 | 2021-01-27 | 2022-04-15
2023-02-15 | 2019 | Navy Active | N324461088 |  | 2019-05-23 | 2019-08-05 | TANTARA ASSOCIATES CORPORATION | N4008517D5049 N4008519F6032 | 3458000 | 6917000 | 2020-10-31 | 2021-07-30
2023-02-15 | 2017 | Navy Active | N32446285 |  | 2017-01-17 | 2017-06-29 | L.S. BLACK CONSTRUCTORS-LOEFFELCONSTRUCTION | N4008517C5056 AWD | 18927000 | 37670000 | 2019-05-10 | 2021-01-21
2023-02-15 | 2018 | Navy Active | N32446293 |  | 2018-08-31 | 2019-09-25 | METHUEN CONSTRUCTION CO., INC | N4008519C9261 AWD | 62457000 | 67275000 | 2022-08-09 | 2022-08-09
2023-02-15 | 2014 | Navy Active | N32446308 |  | 2015-09-29 | 2016-04-21 | TRITON MARINE CONSTRUCTION CORP. | N4008516C3013 AWD | 34722000 | 42833000 | 2018-10-25 | 2018-10-25
2023-02-15 | 2019 | Navy Active | N32446310 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N4008520C8500 AWD | 177914000 | 146787000 | 2021-01-27 | 2022-04-15
2023-02-15 | 2017 | Navy Active | N32446371 |  | 2017-09-19 | 2018-03-30 | ENGINEERED CONSTRUCTION SERVICES,INC | N4008518C8719 AWD | 30414000 | 61515000 | 2021-09-14 | 2021-09-14
2023-02-15 | 2021 | Navy Active | N32446381 |  | 2020-11-13 | 2021-08-13 | CAISSON PROCUREMENT | N4008521C0077 AWD | 0 | 454908000 | 2028-06-01 | 2028-08-17
2023-02-15 | 2018 | Navy Active | N32446385 |  | 2018-07-05 | 2018-09-20 | STRUCTURAL ASSOCIATES, INC | N4008517D5048 N4008518F6907 | 975000 | 1638000 | 2019-10-08 | 2019-10-08
2023-02-15 | 2023 | Navy Active | N32466381
2023-02-15 | 2017 | Navy Active | N3379A223 |  | 2017-10-13 | 2018-06-28 | J/V P. & C. DEVELOPMENT S.A. -ERGOTEM S.A. | N6247018C4015 AWD | 25219000 | 46100000 | 2020-10-05 | 2022-07-31
2023-02-15 | 2018 | Navy Active | N3379A505 |  | 2018-06-12 | 2018-10-26 | ECC MEZZ LLC | N6247019D5002 N6247019F9001 | 11315000 | 12609000 | 2020-06-18 | 2022-12-31
2023-02-15 | 2021 | Navy Active | N360423271 |  | 2020-10-30 | 2021-03-25 | SYNERGY ELECTRIC COMPANY INC | N6247319D2430 N6247321F4370 | 1000 | 44130000 | 2023-05-03 | 2023-10-16
2023-02-15 | 2015 | Navy Active | N41557230 |  | 2015-04-02 | 2015-11-17 | RELYANT GLOBAL LLC | N6274216C1317 AWD | 20799000 | 32908000 | 2019-01-29 | 2019-01-29
2023-02-15 | 2018 | Navy Active | N41557250 |  | 2018-01-24 | 2018-09-24 | BLACK CONSTRUCTION CORP. | N6274218C1300 AWD | 43203000 | 44012000 | 2021-01-21 | 2022-10-06
2023-02-15 | 2018 | Navy Active | N41557260 |  | 2018-01-24 | 2018-09-21 | BLACK CONSTRUCTION CORP. | N6274218C1300 AWD | 53554000 | 53780000 | 2020-12-28 | 2022-10-06
2023-02-15 | 2016 | Navy Active | N41557635 |  | 2016-06-24 | 2017-08-01 | TIKIGAQ CONSTRUCTION, LLC | N4019217C1305 AWD | 8715000 | 18724000 | 2019-02-22 | 2022-01-09
2023-02-15 | 2020 | Navy Active | N41557735A |  | 2019-06-11 | 2021-09-28 | BLACK CONSTRUCTION CORP. | N6274221C1346 AWD | 0 | 87141000 | 2024-10-25 | 2024-10-25
2023-02-15 | 2017 | Navy Active | N41557H279 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 78787000 | 148828000 | 2022-07-05 | 2023-03-13
2023-02-15 | 2018 | Navy Active | N41557H280 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 40850000 | 41182000 | 2022-07-05 | 2023-03-13
2023-02-15 | 2019 | Navy Active | N41557H282 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 83378000 | 84705000 | 2022-07-05 | 2023-03-13
2023-02-15 | 2015 | Navy Active | N42237099 |  | 2014-02-24 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 39730000 | 44524000 | 2018-06-20 | 2019-03-27
2023-02-15 | 2017 | Navy Active | N42237671 |  | 2017-08-10 | 2018-01-16 | DESIGN BUILD INCORPORATED | N6945016D1111 | 2979000 | 3178000 | 2019-08-23 | 2019-11-22
2023-02-15 | 2023 | Navy Active | N42237676 |  | 2022-07-29 | 2022-12-30 | SAUER, INC. | N6945021D0061 N6945023F0148 | 0 | 43778000 | 2025-03-03 | 2025-03-03
2023-02-15 | 2017 | Navy Active | N47608265 |  | 2018-04-10 | 2019-01-30 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008019C2015 AWD | 46919000 | 101140000 | 2020-09-28 | 2023-02-20
2023-02-15 | 2017 | Navy Active | N47608421 |  | 2017-08-03 | 2017-09-27 | REILLY CONSTRUCTION, INC | N4008017D0012 N4008017F4480 | 2627000 | 4330000 | 2018-10-24 | 2020-06-16
2023-02-15 | 2016 | Navy Active | N47608975 |  | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N4008018C0311 AWD | 38795000 | 62801000 | 2020-02-02 | 2020-07-23
2023-02-15 | 2017 | Navy Active | N47608975 | N47608975A | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N4008018C0311 AWD | 2145000 | 2043000 | 2020-02-02 | 2020-12-29
2023-02-15 | 2020 | Navy Active | N476091900 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 437309406 | 498062000 | 2023-11-30 | 2023-11-30
2023-02-15 | 2020 | Navy Active | N476091901 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 167657000 | 2023-11-30 | 2023-11-30
2023-02-15 | 2020 | Navy Active | N476091902 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 109027000 | 2023-11-30 | 2023-11-30
2023-02-15 | 2020 | Navy Active | N476091903 |  | 2020-05-22 | 2020-09-17 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247320F5462 | 111944000 | 137989000 | 2022-11-04 | 2022-11-04
2023-02-15 | 2020 | Navy Active | N476091904 |  | 2021-02-11 | 2021-06-25 | RQ CONSTRUCTION, LLC | N6247321D1211 N6247321F4921 | 0 | 269130000 | 2025-08-29 | 2025-10-14
2023-02-15 | 2020 | Navy Active | N476091907 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 78947000 | 2023-11-30 | 2023-11-30
2023-02-15 | 2020 | Navy Active | N476091908 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 157314000 | 2023-11-30 | 2023-11-30
2023-02-15 | 2020 | Navy Active | N476091911 |  | 2021-01-19 | 2021-06-24 | WEBCOR CONSTRUCTION LP | N6247321D1214 N6247321F4923 | 0 | 153144000 | 2024-01-22 | 2024-01-22
2023-02-15 | 2020 | Navy Active | N476091914 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 0 | 85411000 | 2023-11-30 | 2023-11-30
2023-02-15 | 2020 | Navy Active | N476091916 |  | 2020-05-15 | 2020-09-03 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247320F5296 | 53426000 | 63290000 | 2022-09-19 | 2023-01-13
2023-02-15 | 2020 | Navy Active | N476091917 |  | 2021-02-10 | 2021-09-16 | WHITING-TURNER CONTRACTING COMPANY,THE | N6247321D1215 N6247321F4727 | 0 | 75791000 | 2024-02-20 | 2024-02-20
2023-02-15 | 2020 | Navy Active | N476091918 |  | 2020-11-23 | 2021-03-03 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247321F4428 | 50924000 | 63870000 | 2023-05-03 | 2023-05-03
2023-02-15 | 2020 | Navy Active | N476091919 |  | 2021-02-03 | 2021-05-20 | HARPER CONSTRUCTION COMPANY, INC | N6247321D1206 N6247321F4741 | 3397000 | 54046000 | 2024-02-05 | 2024-02-05
2023-02-15 | 2020 | Navy Active | N476091920 |  | 2021-02-10 | 2021-09-16 | WHITING-TURNER CONTRACTING COMPANY,THE | N6247321D1215 N6247321F4727 | 0 | 40770000 | 2024-02-20 | 2024-02-20
2023-02-15 | 2020 | Navy Active | N476091921 |  | 2021-02-10 | 2021-09-16 | WHITING-TURNER CONTRACTING COMPANY,THE | N6247321D1215 N6247321F4727 | 0 | 85433000 | 2024-02-20 | 2024-02-20
2023-02-15 | 2020 | Navy Active | N476091922 |  | 2021-02-03 | 2021-06-10 | HARPER CONSTRUCTION COMPANY, INC | N6247321D1206 N6247321F4825 | 0 | 82649000 | 2024-01-23 | 2024-01-23
2023-02-15 | 2020 | Navy Active | N476091924 |  | 2020-10-16 | 2021-01-22 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 N6247321F4264 | 1660000 | 27545000 | 2023-02-06 | 2023-02-06
2023-02-15 | 2020 | Navy Active | N47609810 |  | 2020-04-15 | 2020-06-26 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247319D2438 N6247320F4817 | 53866451 | 57673000 | 2022-04-10 | 2022-08-20
2023-02-15 | 2018 | Navy Active | N50092176 |  | 2017-09-14 | 2018-04-19 | CIVIL WORKS CONTRACTING LLC | N4008517D0358 N4008518F5423 | 2670000 | 5204000 | 2019-08-05 | 2019-08-05
2023-02-15 | 2019 | Navy Active | N60042117
2023-02-15 | 2020 | Navy Active | N601911026 |  | 2020-07-23 | 2020-12-11 | TAZEWELL-BGI JV, LLC | N4008518D1144 N4008521F4343 | 4218000 | 5755000 | 2022-06-10 | 2022-12-06
2023-02-15 | 2018 | Navy Active | N60191160 |  | 2019-08-28 | 2020-02-14 | SYNCON, LLC | N4008520C8503 AWD | 25795000 | 24567000 | 2022-03-01 | 2023-01-14
2023-02-15 | 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446000 | 32711000 | 2016-10-25 | 2021-02-12
2023-02-15 | 2017 | Navy Active | N60201154 |  | 2017-02-23 | 2017-06-29 | HENSEL PHELPS CONSTRUCTION CO | N6945014D1269 N6945017F0700 | 40518000 | 42718000 | 2019-09-26 | 2019-12-27
2023-02-15 | 2019 | Navy Active | N60201195 |  | 2019-06-18 | 2019-08-16 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N6945016D1112 N6945019F0716 | 3600000 | 7416000 | 2020-08-29 | 2021-03-31
2023-02-15 | 2018 | Navy Active | N60201421 |  | 2017-10-16 | 2018-08-03 | DESBUILD INCORPORATEDDBA DES BUILD | N6945016D1111 N6945018F0723 | 11062000 | 12364000 | 2020-08-04 | 2022-06-25
2023-02-15 | 2016 | Navy Active | N60201424 |  | 2016-01-26 | 2016-07-14 | ARTEC GROUP (THE) INC | N6945016D1110 0001 | 14616000 | 17111000 | 2019-02-05 | 2019-02-05
2023-02-15 | 2019 | Navy Active | N60201426 |  | 2019-05-31 | 2019-09-13 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014D1267 N6945019F0708 | 76123000 | 95224000 | 2021-04-02 | 2022-11-23
2023-02-15 | 2019 | Navy Active | N60201427 |  | 2018-07-30 | 2019-02-22 | Archer Western Federal JV | N6945019F0855 | 27496000 | 28125000 | 2021-02-05 | 2021-06-04
2023-02-15 | 2016 | Navy Active | N60495111 |  | 2016-05-31 | 2017-08-17 | BRISTOL GENERAL CONTRACTORS, LLC | N6247315D2404 N6247317F4334 | 11253000 | 23867000 | 2019-02-25 | 2020-07-18
2023-02-15 | 2014 | Navy Active | N60495393 |  | 2017-02-28 | 2018-04-19 | WALTERS, K. G. CONSTRUCTION CO., IN | N6247318C2205 AWD | 15675000 | 30076000 | 2020-05-08 | 2020-11-30
2023-02-15 | 2015 | Navy Active | N60495420 |  | 2015-07-17 | 2015-09-16 | STRAUB CONSTRUCTION, INC. | N6247315D2427 0002 | 25541000 | 41944000 | 2017-11-24 | 2019-10-31
2023-02-15 | 2018 | Navy Active | N60495426 |  | 2018-11-07 | 2018-12-28 | J I GARCIA CONSTRUCTION INC | N6247318D5817 N6247319F4162 | 3295000 | 3234000 | 2019-10-25 | 2019-10-25
2023-02-15 | 2017 | Navy Active | N60495440 |  | 2017-07-20 | 2018-08-06 | STRAUB CONSTRUCTION, INC. | N6247316D1887 N6247318F4874 | 18936000 | 37956000 | 2020-08-25 | 2020-10-17
2023-02-15 | 2019 | Navy Active | N60508253 |  | 2019-05-13 | 2021-05-12 | WEBCO L.L.C. | N6945019D1085 N6945021F0280 | 10500000 | 17625000 | 2024-05-11 | 2024-05-11
2023-02-15 | 2019 | Navy Active | N60508288 |  | 2019-07-26 | 2020-01-10 | EMR, INC. | N6945018D1318 N6945020F0875 | 2466000 | 7140000 | 2021-01-11 | 2023-03-30
2023-02-15 | 2019 | Navy Active | N60514160 |  | 2018-12-10 | 2019-09-19 | RQ CONSTRUCTION, LLC | N6945019C0501 AWD | 66357000 | 124001000 | 2022-03-18 | 2023-02-17
2023-02-15 | 2019 | Navy Active | N60514343 |  | 2019-06-04 | 2019-09-20 | ISLANDS MECHANICAL CONTRACTOR | N6945018D1313 N6945019F1007 | 12440000 | 24050000 | 2021-09-20 | 2022-12-12
2023-02-15 | 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458000 | 8792000 | 2017-01-17 | 2017-01-17
2023-02-15 | 2021 | Navy Active | N610542101 |  | 2020-10-23 | 2021-03-05 | NIPPO CORPORATION | N4008419D0075 N4008421F4145 | 1382000 | 38283000 | 2024-05-01 | 2024-05-01
2023-02-15 | 2022 | Navy Active | N610542202
2023-02-15 | 2019 | Navy Active | N61056512 |  | 2018-10-31 | 2019-04-19 | Awarded by Other Agency | N40084USACE01 AWD | 9050000 | 9050000 | 2020-12-31 | 2020-12-31
2023-02-15 | 2017 | Navy Active | N61064402 |  | 2018-04-20 | 2018-12-26 | NOVA GROUP INC | N6274219C1320 AWD | 25137000 | 53356000 | 2021-07-13 | 2021-12-27
2023-02-15 | 2016 | Navy Active | N61064416 |  | 2018-04-19 | 2018-09-06 | HELIX ELECTRIC, INC. | N6247818C1516 AWD | 23932000 | 53750000 | 2020-05-28 | 2022-06-17
2023-02-15 | 2014 | Navy Active | N61065202 |  | 2014-12-11 | 2016-08-29 | VANDER WERFF, PETER CONSTRUCTION | N6247314D0039 0011 | 15972000 | 20297000 | 2018-06-10 | 2019-12-11
2023-02-15 | 2019 | Navy Active | N61065224 |  | 2018-12-10 | 2019-07-15 | MANSON/CONNOLLY SEAL BEACH JV | N6247319C2450 AWD | 111089000 | 207963000 | 2022-06-30 | 2024-06-18
2023-02-15 | 2019 | Navy Active | N61065241 |  | 2019-06-17 | 2019-08-19 | REYES CONSTRUCTION INC | N6247318D5862 N6247319F4995 | 23001000 | 24205000 | 2021-04-15 | 2021-04-26
2023-02-15 | 2021 | Navy Active | N61065243 |  | 2021-05-05 | 2021-08-12 | REYES CONSTRUCTION INC | N6247318D5862 N6247321F5105 | 0 | 30399000 | 2023-08-27 | 2023-08-27
2023-02-15 | 2022 | Navy Active | N61065243A
2023-02-15 | 2018 | Navy Active | N61066604
2023-02-15 | 2018 | Navy Active | N61151163 |  | 2018-02-12 | 2018-09-29 | JOHN C. GRIMBERG CO., INC. | N4008018C0008 AWD | 37296000 | 70115000 | 2021-08-14 | 2021-08-14
2023-02-15 | 2015 | Navy Active | N61151190 |  | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 15316000 | 16202000 | 2019-09-06 | 2023-04-09
2023-02-15 | 2017 | Navy Active | N61151190 | N61151190A | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 6546000 | 4583000 | 2020-01-13 | 2023-04-09
2023-02-15 | 2015 | Navy Active | N61151287 |  | 2015-03-04 | 2015-09-02 | M A MORTENSON COMPANY | N4008015C0167 AWD | 25679000 | 30935000 | 2017-07-17 | 2019-10-31
2023-02-15 | 2015 | Navy Active | N61152621 |  | 2015-07-15 | 2016-03-31 | TURNER CONSTRUCTION COMPANY | N4008016C0156 AWD | 120181000 | 166881000 | 2019-09-08 | 2020-05-22
2023-02-15 | 2020 | Navy Active | N61755491 |  | 2020-03-02 | 2020-08-07 | BLACK CONSTRUCTION-TUTOR PERINI JV | N6274219D1328 N6274220F9924 | 50514009 | 56534000 | 2022-12-20 | 2022-12-20
2023-02-15 | 2022 | Navy Active | N61755519 |  | 2021-11-12 | 2022-05-13 | BLACK CONSTRUCTION CORP. | N6274222C1326 AWD | 0 | 95319000 | 2024-09-10 | 2024-09-10
2023-02-15 | 2016 | Navy Active | N61755535 |  | 2016-11-10 | 2017-08-21 | CONTRACK WATTS, INC | N6274217C1325 AWD | 47314000 | 90910000 | 2020-01-03 | 2020-09-10
2023-02-15 | 2019 | Navy Active | N61755640 |  | 2019-02-20 | 2019-06-25 | GILBANE FEDERAL | N6274219C1310 AWD | 36419000 | 67407000 | 2022-10-07 | 2022-11-04
2023-02-15 | 2017 | Navy Active | N61755652 |  | 2017-06-12 | 2018-05-23 | APTIM FEDERAL SERVICES, LLC | N6274218C1318 AWD | 28975000 | 43526000 | 2020-04-03 | 2021-08-15
2023-02-15 | 2018 | Navy Active | N61755680 |  | 2018-08-03 | 2018-09-28 | RELIABLE BUILDERS, INC. | N4019216D2704 N4019218F4410 | 2804000 | 4771000 | 2019-09-27 | 2021-05-26
2023-02-15 | 2018 | Navy Active | N61766661 |  | 2021-07-28 | 2022-04-21 | GRANITE CONSTRUCTION COMPANY GUAM | N6274222C1329 AWD | 0 | 130000 | 2024-07-10 | 2024-07-10
2023-02-15 | 2017 | Navy Active | N62588307 |  | 2018-04-03 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N6247019C5009 AWD | 10833000 | 12403000 | 2021-02-09 | 2022-02-18
2023-02-15 | 2017 | Navy Active | N62588308 |  | 2018-08-09 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N6247019C5009 AWD | 4894000 | 5101000 | 2021-02-09 | 2022-02-18
2023-02-15 | 2019 | Navy Active | N62588312
2023-02-15 | 2019 | Navy Active | N62604855 |  | 2019-02-22 | 2019-05-15 | EMR, INC. | N6945017D0507 N6945019F0710 | 21022000 | 22709000 | 2022-06-30 | 2022-06-30
2023-02-15 | 2022 | Navy Active | N62688095 |  | 2021-09-17 | 2022-05-13 | RQ-MAGANN JV | N4008522C0017 AWD | 0 | 86932000 | 2027-02-27 | 2027-02-27
2023-02-15 | 2020 | Navy Active | N626881035 |  | 2020-11-12 | 2021-08-20 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008521D0083 N4008521F6191 | 0 | 57759000 | 2024-03-22 | 2024-03-22
2023-02-15 | 2021 | Navy Active | N626881035A |  | 2020-11-12 | 2021-08-20 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008521D0083 N4008521F6191 | 0 | 2923000 | 2024-03-22 | 2024-03-22
2023-02-15 | 2021 | Navy Active | N62688404 |  | 2021-03-29 | 2021-09-30 | BAMFORTH ENGINEERS + SURVEYORS,INC. | N4008519D9164 N4008520F4014-New Mod | 0 | 30907000 | 2019-11-30 | 2023-08-20
2023-02-15 | 2018 | Navy Active | N62688495 |  | 2017-07-10 | 2018-09-28 | WHITING-TURNER CONTRACTING CO | N4008518C1148 AWD | 35158000 | 68038000 | 2021-02-04 | 2023-05-26
2023-02-15 | 2016 | Navy Active | N62688610 |  | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N4008517C0307 AWD | 34675000 | 71205000 | 2019-10-25 | 2020-12-30
2023-02-15 | 2017 | Navy Active | N62688610 | N62688610A | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N4008517C0307 AWD | 12166000 | 12166000 | 2019-10-25 | 2020-12-30
2023-02-15 | 2018 | Navy Active | N62688762 |  | 2018-01-25 | 2018-05-02 | TAZEWELL HOMELAND JV, LLC | N4008518R1123 | 2573000 | 3565000 | 2019-07-02 | 2021-01-03
2023-02-15 | 2016 | Navy Active | N62688913 |  | 2017-03-23 | 2018-04-23 | WHITING-TURNER CONTRACTING CO | N4008518C1134 AWD | 114000000 | 216635000 | 2020-11-01 | 2022-03-16
2023-02-15 | 2018 | Navy Active | N62813013 |  | 2018-12-14 | 2019-07-26 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274219C1317 AWD | 59383000 | 137761000 | 2021-04-26 | 2024-04-24
2023-02-15 | 2020 | Navy Active | N62813033 |  | 2020-04-22 | 2020-08-10 | HDR ENGINEERING, INC.DBA HONOLULU HDR HAWAII PACIFIC | N6247820C4016 AWD | 50430000 | 38450000 | 2022-09-09 | 2022-09-09
2023-02-15 | 2016 | Navy Active | N62813036 |  | 2015-10-28 | 2016-01-26 | BETHEL-WEBCOR JV-1 | N6247814D4001 KB01 | 8520000 | 9633000 | 2018-03-26 | 2021-07-06
2023-02-15 | 2021 | Navy Active | N62813044 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N6247820D4015 N6247821F4087 | 2072000 | 39617000 | 2023-11-12 | 2023-11-12
2023-02-15 | 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810000 | 5346000 | 2016-05-18 | 2019-12-31
2023-02-15 | 2021 | Navy Active | N628131006 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N6247820D4015 N6247821F4087 | 2072000 | 30726000 | 2023-11-12 | 2023-11-12
2023-02-15 | 2019 | Navy Active | N62813169 |  | 2018-10-15 | 2019-03-29 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N62742-19-C-1319 | 64705000 | 139861000 | 2022-01-24 | 2022-08-03
2023-02-15 | 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970000 | 68457000 | 2017-08-03 | 2020-10-06
2023-02-15 | 2018 | Navy Active | N62813704 |  | 2018-09-21 | 2019-03-12 | KIEWIT INFRASTRUCTURE WEST CO. | N62478-19-C-1515 | 73199000 | 142566000 | 2021-06-19 | 2021-07-21
2023-02-15 | 2020 | Navy Active | N628632001 |  | 2021-07-29 | 2021-09-27 | UTE CASTELLANO COBRA MACC | N6247021D0012 N6247021F9010 | 0 | 14618000 | 2023-10-04 | 2023-10-04
2023-02-15 | 2021 | Navy Active | N62863313 |  | 2021-07-22 | 2021-12-16 | ACCIONA CMS JV, LLC | N6247021D0011 N6247022F9000 | 0 | 58840000 | 2024-09-09 | 2024-09-09
2023-02-15 | 2020 | Navy Active | N62863605 |  | 2020-09-03 | 2021-04-12 | UTE CASTELLANO COBRA MACC | N3319119D0801 N3319121F4133 | 7127000 | 9395000 | 2023-01-17 | 2023-04-11
2023-02-15 | 2021 | Navy Active | N62863620 |  | 2021-09-01 | 2021-12-21 | ACCIONA CMS JV, LLC | N6247021D0011 N6247022F9001 | 0 | 26439000 | 2024-07-01 | 2025-01-06
2023-02-15 | 2017 | Navy Active | N62863621 |  | 2017-03-07 | 2017-08-31 | CONSTRUCCIONES FELIPE CASTELLANOCOBRA INSTALACIONES Y SERVICIOS | N6247017C5006 AWD | 21868000 | 25424000 | 2023-06-09 | 2023-01-08
2023-02-15 | 2015 | Navy Active | N62863712 |  | 2015-04-11 | 2015-11-20 | COBRA INSTALCIONES Y SERVICIOS SA | N6247016C6001 AWD | 19252000 | 26502000 | 2018-05-23 | 2022-12-27
2023-02-15 | 2020 | Navy Active | N62863716
2023-02-15 | 2020 | Navy Active | N62863785 |  | 2021-10-07 | 2021-12-21 | FERROVIAL AGROMAN SA | N6247021D0016 N6247022F9002 | 0 | 16000 | 2023-12-31 | 2023-12-31
2023-02-15 | 2021 | Navy Active | N62863810 |  | 2021-12-07 | 2023-01-06 | SOCIEDAD ESPANOLA DE MONTAJESINDUSTRIALES S.A. S.E.M.I. | N6247021D0017 N6247023F9000 | 0 | 27698000 | 2024-10-25 | 2024-10-25
2023-02-15 | 2019 | Navy Active | N62863811 |  | 2020-12-28 | 2021-08-30 | ACCIONA CMS JV, LLC | N6247021D0011 N6247021F9009 | 0 | 32063000 | 2024-04-16 | 2024-04-16
2023-02-15 | 2019 | Navy Active | N62863812 |  | 2020-05-14 | 2020-09-23 | CONSTRUCTORA SAN JOSE SA | N6247020C0009 AWD | 137000 | 5526000 | 2022-06-30 | 2022-06-30
2023-02-15 | 2020 | Navy Active | N62995130 |  | 2020-07-06 | 2020-09-29 | WOLFF & MULLER GOVERNMENT SERVICES | N6247020C0013 AWD | 39712368 | 48341000 | 2025-06-05 | 2026-12-24
2023-02-15 | 2016 | Navy Active | N62995407 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 23632000 | 24594000 | 2019-04-23 | 2021-12-14
2023-02-15 | 2016 | Navy Active | N62995655 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 28340000 | 72726000 | 2019-04-23 | 2021-12-14
2023-02-15 | 2017 | Navy Active | N62995737 |  | 2016-09-09 | 2017-02-28 | ENVIRONMENTAL CHEMICAL CORPORATION | N3319116D1010 JN01 | 6096000 | 24708000 | 2018-08-22 | 2021-01-21
2023-02-15 | 2019 | Navy Active | N63005955U
2023-02-15 | 2021 | Navy Active | N63005964
2023-02-15 | 2020 | Navy Active | N63005974
2023-02-15 | 2016 | Navy Active | N63005976
2023-02-15 | 2017 | Navy Active | N63005985 |  | 2018-02-13 | 2019-06-14 | JUDE & L CONSTRUCTION, LLC | N3319119C0805 AWD | 3407000 | 6536000 | 2021-03-25 | 2021-03-25
2023-02-15 | 2016 | Navy Active | N63042218 |  | 2015-12-10 | 2016-05-10 | A&D GC INC | N6247315D2403 0003 | 7386000 | 8200000 | 2017-11-16 | 2020-09-17
2023-02-15 | 2018 | Navy Active | N63042282 |  | 2018-01-23 | 2018-09-19 | R A BURCH CONSTRUCTION CO INC | N6247318C2201 AWD | 52594000 | 99258000 | 2021-02-24 | 2022-02-25
2023-02-15 | 2019 | Navy Active | N63042284 |  | 2018-11-09 | 2019-09-16 | HARPER CONSTRUCTION COMPANY, INC | N6247319C2455 AWD | 107641000 | 201356000 | 2021-11-17 | 2022-08-12
2023-02-15 | 2019 | Navy Active | N63042392 |  | 2019-05-09 | 2019-07-30 | POWER PRO PLUS INC. | N6247319D2428 N6247319F4769 | 13545000 | 27216000 | 2021-05-06 | 2021-05-06
2023-02-15 | 2022 | Navy Active | N63402391A
2023-02-15 | 2021 | Navy Active | N66691131 |  | 2021-09-01 | 2022-02-04 | Macro Vantage Levant DMCC | N6247022C0002 AWD | 0 | 39814000 | 2024-10-20 | 2024-10-20
2023-02-15 | 2019 | Navy Active | N66691144
2023-02-15 | 2018 | Navy Active | N66691911 |  | 2018-06-18 | 2018-12-12 | AKTOR S.A. - TSONTOS S.A. J/V | N6247019C5006 AWD | 10141000 | 4115000 | 2021-02-14 | 2021-10-04
2023-02-15 | 2017 | Navy Active | N68436400 |  | 2017-08-10 | 2018-09-29 | CUSTOM MECHANICAL SYSTEMS CORP(CMS) | N4425517D4034 N4425518F4438 | 38496000 | 65552000 | 2021-06-30 | 2022-03-19
2023-02-15 | 2016 | Navy Active | N68436401 |  | 2016-03-29 | 2017-09-26 | TOMPCO, INC | N4425517C8002 AWD | 17270000 | 34946000 | 2020-01-04 | 2021-07-06
2023-02-15 | 2016 | Navy Active | N68436431 |  | 2016-03-31 | 2016-08-11 | NOVA GROUP INC | N4425516C7002 AWD | 19943000 | 23943000 | 2017-11-14 | 2018-05-18
2023-02-15 | 2017 | Navy Active | N68436438 |  | 2017-01-20 | 2018-04-23 | VET INDUSTRIAL INC | N4425517D4007 N4425518F4134 | 10040000 | 20811000 | 2019-10-30 | 2020-08-14
2023-02-15 | 2020 | Navy Active | N68436447 |  | 2020-01-10 | 2020-06-08 | N4425520C1002 AWD | N4425520C1002 AWD | 1876000 | 53668000 | 2023-08-02 | 2023-08-02
2023-02-15 | 2017 | Navy Active | N68436834 |  | 2019-03-18 | 2020-02-03 | MANSON CONSTRUCTION CO | N4425520C2002 AWD | 73000000 | 107271000 | 2022-07-04 | 2023-01-14
2023-02-15 | 2016 | Navy Active | N68436983 |  | 2016-04-15 | 2016-09-21 | NOVA GROUP INC | N4425516C7005 AWD | 31744000 | 69018000 | 2018-02-13 | 2019-04-21
2023-02-15 | 2015 | Navy Active | N68436990 | N68436990C | 2010-07-07 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00004 | 80735000 | 82357000 | 2017-09-30 | 2017-09-30
2023-02-15 | 2015 | Navy Active | N68436993 |  | 2015-09-30 | 2016-08-30 | WATTS-ORION JV | N4425516C7004 AWD | 32047000 | 59705000 | 2019-08-07 | 2019-08-07
2023-02-15 | 2019 | Navy Active | N68469001 |  | 2019-06-07 | 2019-09-16 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247019F9101 | 40000000 | 105574000 | 2024-09-15 | 2024-09-15
2023-02-15 | 2015 | Navy Active | N68469275 |  | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 31151000 | 87655000 | 2019-11-15 | 2023-03-03
2023-02-15 | 2018 | Navy Active | N68469275 | N68469275A | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 39776000 | 37882000 | 2019-11-15 | 2023-03-03
2023-02-15 | 2017 | Navy Active | N68469760
2023-02-15 | 2020 | Navy Active | N69212169 |  | 2020-11-09 | 2021-03-25 | SAUER, INC. | N4008521C0028 AWD | 52191740 | 61047000 | 2023-06-25 | 2024-07-17
2023-02-15 | 2018 | Navy Active | N69212995 |  | 2018-12-19 | 2019-01-31 | AECOM CONSTRUCTION, INC. | N4008519D9066 N4008519F4710 | 31074000 | 49257000 | 2021-06-25 | 2021-12-08
2023-02-15 | 2019 | Navy Active | N69232586 |  | 2019-02-08 | 2019-09-26 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247319F5449 | 27152000 | 28819000 | 2020-02-15 | 2022-10-31
2023-02-15 | 2019 | Navy Active | N69232777 |  | 2019-05-30 | 2019-08-28 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F5130 | 19686000 | 22952000 | 2021-01-11 | 2021-11-24
2023-02-15 | 2019 | Navy Active | N83447084 |  | 2019-07-31 | 2019-09-17 | UNIFIED SERVICES OF TEXAS | N6945015D1618 N6945019F2598 | 2500000 | 4804000 | 2020-09-20 | 2021-02-25
2023-02-15 | 2017 | Navy Reserve | M68479777 |  | 2017-07-25 | 2020-02-05 | OAK GROUP, INC., THE | N4008517D5038 N4008520F4527 | 17729000 | 50923000 | 2021-08-30 | 2024-09-27
2023-02-15 | 2015 | Navy Reserve | N00129664 |  | 2015-08-24 | 2015-08-25 | VETERANS CONSTRUCTION, LLC | N4008515C9610 AWD | 1989000 | 3049000 | 2017-04-21 | 2017-04-21
2023-02-15 | 2020 | Navy Reserve | N00206475 |  | 2020-01-30 | 2020-08-13 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945019D0908 N6945020F0891 | 6796000 | 27380000 | 2023-03-06 | 2023-06-06
2023-02-15 | 2019 | Navy Reserve | N00206493 |  | 2019-10-03 | 2020-01-09 | DAWSON FEDERAL, INC. | N6945018D1320 N6945020F0873 | 4632000 | 4753000 | 2021-01-28 | 2022-01-04
2023-02-15 | 2017 | Navy Reserve | N00206500 |  | 2016-11-04 | 2017-06-29 | SAUER, INC. | N6945017C1613 AWD | 11589000 | 14281000 | 2019-07-27 | 2020-10-01
2023-02-15 | 2018 | Navy Reserve | N42237642 |  | 2018-05-04 | 2018-09-12 | LEEBCOR SERVICES LLC | N6945016D1113 N6945018F0731 | 14240000 | 23015000 | 2020-01-06 | 2021-10-16
2023-02-15 | 2019 | Navy Reserve | N42237643 |  | 2018-12-03 | 2019-08-09 | WINDAMIR DEVELOPMENT INC | N6945019D0922 N6945019F0864 | 11207000 | 12688000 | 2021-10-03 | 2022-05-04
2023-02-15 | 2019 | Navy Reserve | N61065160 |  | 2018-11-01 | 2019-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F4183 | 19180000 | 21533000 | 2021-02-07 | 2021-06-01
2023-02-15 | 2018 | Navy Reserve | N63042366 |  | 2018-06-04 | 2019-04-11 | SOLPAC CONSTRUCTION INC | N6247318D5855 | 16347000 | 17542000 | 2021-03-26 | 2022-03-02
2023-02-15 | 2018 | Navy Reserve | N83447077 |  | 2018-05-14 | 2018-09-26 | EMR, INC. | N6945018D1318 N6945018F0894 | 11343000 | 22067000 | 2019-12-31 | 2020-12-31
2022-12-14 | 2011 | Special Operations Command | 063054x |  | 2011-02-23 | 2011-04-09 | Hensel Phelps Construction Co. | W912PP-10-C-0015 | 0 | 4616078 | 2012-02-26 | 2013-03-15
2022-12-14 | 2008 | Special Operations Command | 0P-926 |  | 2008-05-27 | 2009-09-25 | Contrack Watts, Inc | W912ER-09-C-0051 | 0 | 15889227 | 2011-12-13 | 2012-12-27
2022-12-20 | 2018 | Special Operations Command | 1362 |  | 2020-01-27 | 2020-07-22 | PATRIOT CONSTRUCTION, LLC | N4008520C0142 AWD | 7962 | 7705 | 2022-02-07 | 2023-11-18
2022-12-20 | 2014 | Special Operations Command | 1391 |  | 2014-05-29 | 2014-08-28 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0004 | 30963 | 30840 | 2016-09-02 | 2019-01-31
2022-12-14 | 2009 | Special Operations Command | 26542 |  | 2009-04-09 | 2009-09-10 | Heery International, Inc. | W912HN-09-C-0050 | 11777057 | 12749904 | 2011-07-02 | 2012-09-24
2022-12-14 | 2008 | Special Operations Command | 33003 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 | 4574738 | 5123284 | 2013-04-25 | 2015-03-05
2022-12-14 | 2008 | Special Operations Command | 33005 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 | 3603251 | 3763908 | 2013-04-25 | 2015-01-21
2022-12-14 | 2009 | Special Operations Command | 33017 |  | 2008-10-15 | 2009-03-03 | CCSI/Barlovento, LLC, JV | W91278-09-C-0010 | 5240500 | 6602985 | 2010-09-28 | 2011-06-08
2022-12-14 | 2008 | Special Operations Command | 33019 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 | 2930589 | 3076695 | 2013-04-25 | 2015-01-21
2022-12-14 | 2015 | Special Operations Command | 36977 |  | 2015-04-15 | 2015-08-20 | Walsh Group Ventures | W912QR-15-C-0021 | 14851238 | 15516050 | 2017-03-03 | 2017-10-17
2022-12-14 | 2009 | Special Operations Command | 43010 |  | 2009-06-15 | 2009-09-28 | Big D Construction Corp | W912PP-09-C-0034 | 10882320 | 16423555 | 2011-05-09 | 2012-02-02
2022-12-14 | 2012 | Special Operations Command | 43055 |  | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN-10-D-0063 | 4773799 | 5344212 | 2013-11-22 | 2014-11-12
2022-12-14 | 2016 | Special Operations Command | 47942 |  | 2015-12-22 | 2016-06-24 | Medvolt, LLC | W9128F-16-C-0033 | 9065868 | 9433554 | 2018-05-30 | 2018-10-10
2022-12-14 | 2008 | Special Operations Command | 53530 |  | 2007-10-31 | 2008-03-20 | B.L. Harbert International, LLC | W912QR-08-C-0009 | 25906995 | 26435895 | 2009-12-09 | 2010-01-29
2022-12-14 | 2013 | Special Operations Command | 53542 |  | 2014-05-22 | 2014-09-25 | AU AUTHUM KI, INC | W912PL-14-C-0020 | 6546920 | 6674183 | 2016-02-07 | 2016-02-20
2022-12-14 | 2008 | Special Operations Command | 53712A |  | 2008-05-16 | 2008-10-16 | Rush-PEAK Three, JV | W91278-09-C-0003 | 9243000 | 9544521 | 2010-06-05 | 2010-06-07
2022-12-14 | 2015 | Special Operations Command | 57442 |  | 2016-03-23 | 2017-03-17 | Brantley Construction Services, LLC | W912HN-17-C-0006 | 8456354 | 8826862 | 2018-10-19 | 2019-02-07
2022-12-14 | 2009 | Special Operations Command | 59990 |  | 2009-03-25 | 2009-09-28 | American International Contractors, Inc. | W912ER-09-C-0055 | 9978000 | 10839492 | 2011-01-26 | 2012-08-15
2022-12-14 | 2012 | Special Operations Command | 60272 |  | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN-10-D-0049 | 8290317 | 8465679 | 2014-03-06 | 2015-02-18
2022-12-14 | 2009 | Special Operations Command | 60636 |  | 2009-06-15 | 2009-08-31 | Team Construction LLC A JV of Mil Fed/WT Humphrey | W912HN-09-C-0054 | 0 | 0 | 2010-06-12 | 2010-11-15
2022-12-14 | 2009 | Special Operations Command | 60743 |  | 2009-04-15 | 2009-09-14 | IronBridge Construction | W912HN-09-C-0046 | 12273879 | 13140227 | 2011-03-24 | 2012-03-05
2022-12-14 | 2009 | Special Operations Command | 60815 |  | 2008-12-12 | 2009-04-30 | Porter-Metcon | W912HN-09-C-0022 | 4847000 | 5753585 | 2010-11-24 | 2011-04-12
2022-12-14 | 2012 | Special Operations Command | 60821 |  | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN-10-D-0060 | 10605000 | 10926290 | 2014-06-06 | 2015-03-06
2022-12-14 | 2010 | Special Operations Command | 60833 |  | 2010-05-17 | 2010-10-29 | Caddell Construction CO., INC | W91278-07-D-0036 | 15072000 | 15260312 | 2012-08-31 | 2012-12-20
2022-12-14 | 2014 | Special Operations Command | 61064 |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029 | 13951000 | 14300613 | 2016-05-10 | 2017-02-15
2022-12-14 | 2017 | Special Operations Command | 61065 |  | 2017-03-24 | 2017-07-21 | R. C. Construction Co., Inc. | W912HN17C0008 | 4609000 | 5099620 | 2018-12-01 | 2019-07-18
2022-12-14 | 2008 | Special Operations Command | 61772 |  | 2007-12-21 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 | 16750710 | 17544730 | 2013-04-25 | 2015-01-21
2022-12-14 | 2010 | Special Operations Command | 61874 |  | 2010-06-16 | 2010-09-30 | Windamir Development, Inc | W912HN-10-D-0059 | 9327304 | 12372455 | 2012-03-16 | 2013-06-04
2022-12-14 | 2010 | Special Operations Command | 63019 |  | 2009-09-24 | 2010-04-09 | Hensel Phelps Construction Co. | W912PP-10-C-0015 | 32766000 | 35162304 | 2012-12-24 | 2013-03-15
2022-12-14 | 2009 | Special Operations Command | 63027 |  | 2008-11-24 | 2009-03-27 | Phil Howry Company | W912PP-09-C-0006 | 5885533 | 6043246 | 2010-09-10 | 2011-06-02
2022-12-14 | 2010 | Special Operations Command | 63035 |  | 2010-08-10 | 2010-10-25 | A4 Construction Company, Inc. | W912PP-11-C-0002 | 9529882 | 14296126 | 2012-08-07 | 2013-09-10
2022-12-14 | 2011 | Special Operations Command | 63049 |  | 2011-06-14 | 2011-09-09 | Speegle Construction, Inc. | W912PP-11-C-0029 | 19432000 | 20310963 | 2013-12-01 | 2014-04-11
2022-12-14 | 2011 | Special Operations Command | 63051 |  | 2011-02-23 | 2011-08-03 | Sundt Construction, Inc. | W912PP-11-C-0016 | 23743780 | 24785051 | 2012-10-04 | 2012-10-10
2022-12-14 | 2011 | Special Operations Command | 63052 |  | 2011-05-24 | 2011-07-24 | KL House Construction Co. | W912PP-12-C-0002 | 13260000 | 16851420 | 2013-03-25 | 2013-05-31
2022-12-14 | 2009 | Special Operations Command | 63711 |  | 2010-10-28 | 2011-03-30 | Carothers Construction, Inc. | W91278-07-D-0026 | 7175815 | 9584934 | 2012-10-13 | 2013-10-10
2022-12-14 | 2010 | Special Operations Command | 63831 |  | 2010-01-06 | 2010-08-03 | Federal Contracting dba Bryan Construction | W9128F-10-C-0061 | 28586634 | 33108929 | 2012-05-01 | 2012-08-03
2022-12-14 | 2018 | Special Operations Command | 63850 |  | 2018-04-18 | 2018-08-27 | 4K Global-ACC JV LLC | W912PM18C0015 | 12187034 | 14813125 | 2020-06-24 | 2021-05-11
2022-12-14 | 2011 | Special Operations Command | 64484 |  | 2011-05-21 | 2011-07-21 | Sauer Incoporated | W912HN-11-C-0010 | 13388000 | 15616478 | 2014-06-10 | 2015-04-16
2022-12-14 | 2010 | Special Operations Command | 64669 |  | 2010-03-29 | 2010-09-30 | Sauer, Inc. | W912HN-10-C-0063 | 6661700 | 7560146 | 2012-04-14 | 2013-03-01
2022-12-14 | 2013 | Special Operations Command | 65052 |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 | 3199999 | 3271762 | 2014-12-03 | 2014-12-18
2022-12-14 | 2010 | Special Operations Command | 65266 |  | 2009-12-18 | 2010-06-30 | Lifecycle Construction Service, LLC | W912HN-10-D-0033 | 1007935 | 1024285 | 2011-07-22 | 2011-09-29
2022-12-14 | 2008 | Special Operations Command | 65272 |  | 2007-10-23 | 2008-03-28 | Walbridge Aldinger Company | W912HN-07-D-0054 | 13354750 | 13733299 | 2010-04-23 | 2010-06-11
2022-12-14 | 2008 | Special Operations Command | 65392 |  | 2007-10-18 | 2008-03-21 | TJC Engineering Inc | W912QR-08-C-0012 | 15161429 | 15519395 | 2009-08-11 | 2010-03-11
2022-12-14 | 2008 | Special Operations Command | 65394 |  | 2007-11-26 | 2008-03-28 | ACC Construction Co. | W912HN-07-D-0042 | 16571575 | 16883761 | 2010-04-21 | 2010-07-31
2022-12-14 | 2011 | Special Operations Command | 65395 |  | 2011-06-27 | 2011-09-19 | JAAAT Technical. Services, LLC | W912HN-10-D-0057 | 15391578 | 15637173 | 2013-06-19 | 2014-05-30
2022-12-14 | 2008 | Special Operations Command | 65396 |  | 2007-10-09 | 2008-02-14 | Walbridge Aldinger Company | W912HN-07-D-0054 | 5143000 | 5507227 | 2009-04-05 | 2009-06-16
2022-12-14 | 2008 | Special Operations Command | 65397 |  | 2007-11-26 | 2008-03-28 | ACC Construction Co. | W912HN-07-D-0042 | 7184356 | 7193709 | 2010-04-21 | 2010-07-31
2022-12-14 | 2009 | Special Operations Command | 65678 |  | 2008-11-13 | 2009-03-31 | J&S Construction Co., Inc. | W912QR-09-C-0023 | 12824050 | 13455100 | 2010-08-09 | 2010-08-21
2022-12-14 | 2010 | Special Operations Command | 66227 |  | 2010-07-01 | 2010-09-25 | Caddell Construction CO., INC | W912HN-07-D-0056 | 11713000 | 12285692 | 2012-05-02 | 2013-06-07
2022-12-14 | 2010 | Special Operations Command | 66315 |  | 2010-04-27 | 2010-08-05 | Sauer Inc | W912HN-10-C-0054 | 18649100 | 22880316 | 2013-02-11 | 2014-07-22
2022-12-14 | 2011 | Special Operations Command | 66362 |  | 2011-04-08 | 2012-05-30 | Archer Western Contractors, LLC | W912HN-12-C-0009 | 41446000 | 44338384 | 2014-01-31 | 2014-12-30
2022-12-14 | 2011 | Special Operations Command | 66443 |  | 2010-12-23 | 2011-06-20 | SFL+A Architects, PA | W912HN-11-D-0003 | 9591000 | 10179482 | 2013-01-09 | 2013-05-31
2022-12-14 | 2011 | Special Operations Command | 66444 |  | 2011-06-10 | 2011-08-10 | Pacific Tech Sauer JV V | W912HN-11-C-0009 | 9674000 | 9864411 | 2013-01-16 | 2013-05-31
2022-12-14 | 2013 | Special Operations Command | 66597 |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 | 3384894 | 3480791 | 2015-10-21 | 2016-04-15
2022-12-14 | 2019 | Special Operations Command | 66813 |  | 2018-09-17 | 2019-05-23 | Howard W. Pence, Inc | W912QR-15-D-0001 | 5405390 | 5682502 | 2020-12-03 | 2021-06-17
2022-12-14 | 2019 | Special Operations Command | 67039 |  | 2018-11-27 | 2019-05-23 | Howard W. Pence, Inc | W912QR19C0017 | 8825159 | 9122816 | 2020-12-03 | 2021-02-16
2022-12-14 | 2009 | Special Operations Command | 67428 |  | 2008-07-21 | 2009-01-23 | Hensel Phelps Construction Company | W91278-09-C-0017 | 0 | 39068176 | 2011-07-29 | 2011-07-29
2022-12-14 | 2014 | Special Operations Command | 68526 |  | 2014-03-26 | 2015-04-09 | Barlovento, LLC | W91278-10-D-0058 | 10815034 | 12431294 | 2016-11-17 | 2017-04-20
2022-12-14 | 2019 | Special Operations Command | 69251 |  | 2018-12-20 | 2019-04-05 | Sauer | W912PM19C0016 | 9776000 | 9899334 | 2020-05-20 | 2020-10-28
2022-12-14 | 2011 | Special Operations Command | 69261 |  | 2010-12-17 | 2011-09-30 | Komada, LLC | W912HN-11-C-0016 | 3103928 | 3227443 | 2013-01-08 | 2013-03-07
2022-12-14 | 2010 | Special Operations Command | 69275 |  | 2009-11-05 | 2010-03-31 | WECC Incorporated | W912HN-10-C-0024 | 2954015 | 3091827 | 2011-12-14 | 2012-02-13
2022-12-14 | 2012 | Special Operations Command | 69277 |  | 2012-04-24 | 2012-07-30 | Lifecyle Construction Services, LLC | W912HP-11-D-0016 | 2196113 | 2270078 | 2013-08-22 | 2013-12-18
2022-12-14 | 2011 | Special Operations Command | 69278 |  | 2011-07-07 | 2011-09-25 | Iron Mike Construction, LLC | W9128F-12-C-0011 | 3505997 | 3578435 | 2013-08-09 | 2014-01-27
2022-12-14 | 2013 | Special Operations Command | 69287 |  | 2013-06-03 | 2013-09-20 | Archer Western Contractors, LLC | W91278-11-D-0073 | 30907435 | 33877211 | 2015-07-26 | 2016-05-25
2022-12-14 | 2015 | Special Operations Command | 69302 |  | 2015-11-12 | 2017-04-03 | Sauer Incorporated | W91278-12-D-0039 | 36061000 | 39828403 | 2019-05-07 | 2020-12-11
2022-12-14 | 2010 | Special Operations Command | 69366 |  | 2010-03-22 | 2010-08-31 | Atlantic Marine Construction Company, Inc | W912HN-07-D-0024 | 3292508 | 4036729 | 2011-09-21 | 2012-04-12
2022-12-14 | 2013 | Special Operations Command | 69382 |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 | 25816000 | 28305680 | 2015-05-13 | 2015-09-21
2022-12-14 | 2014 | Special Operations Command | 69446 |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 | 15083965 | 16145285 | 2016-02-08 | 2016-06-08
2022-12-14 | 2013 | Special Operations Command | 69447 |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 | 22123180 | 22825995 | 2016-02-13 | 2016-02-15
2022-12-14 | 2011 | Special Operations Command | 69449 |  | 2011-01-07 | 2011-05-23 | Barlovento, LLC | W91278-10-D-0072 | 4110280 | 4984696 | 2012-09-26 | 2012-12-18
2022-12-14 | 2012 | Special Operations Command | 69458 |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 | 16772305 | 19445395 | 2014-06-03 | 2016-03-04
2022-12-14 | 2013 | Special Operations Command | 69493 |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 | 23085000 | 26553696 | 2016-05-17 | 2016-12-16
2022-12-14 | 2017 | Special Operations Command | 69552 |  | 2017-03-02 | 2019-01-15 | ACC Construction Co., Inc. | W912PM19C0008 | 30006388 | 31202082 | 2020-11-08 | 2022-04-12
2022-12-14 | 2010 | Special Operations Command | 69558 |  | 2009-11-02 | 2010-04-16 | Better Built Construction Inc. | W912QR-10-C-0048 | 2885585 | 3257458 | 2011-04-11 | 2011-06-24
2022-12-14 | 2010 | Special Operations Command | 69559 |  | 2009-12-11 | 2010-04-22 | Johnson Roofing & Construction Faith Construction-JV | W912HN-10-C-0028 | 2717800 | 3068801 | 2011-05-18 | 2011-11-02
2022-12-14 | 2010 | Special Operations Command | 69560 |  | 2009-11-04 | 2010-03-16 | CCI Group, LLC | W91278-10-C-0041 | 2643455 | 3157424 | 2011-08-01 | 2012-05-31
2022-12-14 | 2011 | Special Operations Command | 69573 |  | 2011-07-26 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN-10-D-0058 | 8487000 | 9279066 | 2013-03-29 | 2014-01-23
2022-12-14 | 2012 | Special Operations Command | 69758 |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 | 15649974 | 19104823 | 2014-04-08 | 2016-12-06
2022-12-14 | 2011 | Special Operations Command | 69759 |  | 2010-12-16 | 2011-07-26 | Holland and Holland, Inc. | W912HN-11-C-0011 | 2818574 | 2836413 | 2012-08-16 | 2012-10-18
2022-12-14 | 2012 | Special Operations Command | 71224 |  | 2012-06-06 | 2012-09-26 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 | 18525847 | 23524962 | 2014-07-30 | 2015-04-27
2022-12-14 | 2021 | Special Operations Command | 72426 |  | 2021-01-22 | 2021-05-12 | ACC Construction Co., Inc. | W912PM21C0010 | 15525964 | 16785343 | 2022-12-28 | 2023-12-05
2022-12-14 | 2012 | Special Operations Command | 73018 |  | 2012-06-06 | 2012-08-27 | Solis Constructors, Inc. | W912PP-12-C-0025 | 9329356 | 9703739 | 2014-04-10 | 2014-08-26
2022-12-14 | 2012 | Special Operations Command | 73021 |  | 2012-06-06 | 2012-09-12 | K. L. HOUSE CONSTRUCTION COMPANY | W912PP-12-C-0033 | 14700000 | 15132847 | 2014-08-09 | 2014-11-24
2022-12-14 | 2017 | Special Operations Command | 74813 |  | 2017-11-16 | 2018-06-15 | ACC Construction Co., Inc. | W912PM18C0014 | 17972005 | 24309082 | 2020-09-04 | 2021-11-01
2022-12-14 | 2012 | Special Operations Command | 76364 |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 | 29232386 | 33465310 | 2014-08-26 | 2016-04-21
2022-12-14 | 2014 | Special Operations Command | 76365 |  | 2015-07-15 | 2015-11-12 | B. L. Harbert International, LLC | W912QR-16-C-0002 | 22740000 | 23868765 | 2017-10-02 | 2018-01-24
2022-12-14 | 2012 | Special Operations Command | 76366 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 | 16664200 | 19188822 | 2015-09-12 | 2016-01-27
2022-12-14 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-03-08 | Watts Constructors, LLC | W9128F-14-C-0024 | 36441000 | 35801649 | 2016-07-20 | 2018-01-30
2022-12-14 | 2012 | Special Operations Command | 76371 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 | 19092800 | 20598546 | 2015-09-12 | 2016-01-27
2022-12-14 | 2012 | Special Operations Command | 76373 |  | 2012-03-01 | 2012-06-21 | GSC Construction, Inc. | W912HN-10-D-0049 | 9771161 | 11158105 | 2014-04-17 | 2014-10-03
2022-12-14 | 2014 | Special Operations Command | 76375 |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062 | 27358000 | 29794432 | 2016-07-23 | 2017-08-28
2022-12-14 | 2014 | Special Operations Command | 76376 |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073 | 51696668 | 61769562 | 2017-05-14 | 2018-01-19
2022-12-14 | 2011 | Special Operations Command | 76511 |  | 2011-07-30 | 2011-09-30 | Archer Western Contractors, LLC | W912HN-11-C-0014 | 28900000 | 30484390 | 2013-05-11 | 2013-10-31
2022-12-14 | 2016 | Special Operations Command | 76513 |  | 2016-11-07 | 2017-08-02 | Caddell Construction CO. | W912PM17C0004 | 42661500 | 45640993 | 2019-12-18 | 2021-04-22
2022-12-14 | 2017 | Special Operations Command | 76514 |  | 2017-03-02 | 2018-04-05 | RQ Construction, LLC | W912PM18C0011 | 34937000 | 36782800 | 2020-03-23 | 2021-12-17
2022-12-14 | 2016 | Special Operations Command | 76518 |  | 2015-11-23 | 2016-03-17 | Bristol Environmental Remediation Servic | W912DY-12-D-0053 | 8465006 | 9128867 | 2017-05-17 | 2018-01-12
2022-12-14 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV-15-C-0004 | 46555863 | 63212524 | 2017-12-12 | 2018-06-18
2022-12-14 | 2015 | Special Operations Command | 79437 |  | 2016-06-27 | 2016-09-28 | SAUER Incorporated, d/b/a Sauer Southeast | W91278-12-D-0039 | 38659000 | 54260853 | 2019-02-11 | 2022-07-29
2022-12-14 | 2014 | Special Operations Command | 79438 |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 | 7193631 | 7896819 | 2016-04-19 | 2016-10-26
2022-12-14 | 2016 | Special Operations Command | 79439 |  | 2018-04-06 | 2018-08-14 | Archer Western Contractors, LLC | W912PM18C0016 | 24955000 | 36737863 | 2020-05-07 | 2021-11-15
2022-12-14 | 2018 | Special Operations Command | 79443 |  | 2018-09-07 | 2018-12-19 | ACC | W912PM19C0007 | 16474525 | 17729047 | 2020-12-27 | 2021-08-18
2022-12-14 | 2019 | Special Operations Command | 79447 |  | 2019-01-09 | 2019-05-03 | Guarantee Co of North America | W9128F19C0018 | 12309817 | 13924035 | 2021-05-31 | 2023-05-17
2022-12-14 | 2018 | Special Operations Command | 79453 |  | 2018-01-12 | 2019-01-23 | ACC Construction Co., Inc. | W912PM19C0011 | 21039018 | 22836971 | 2022-06-16 | 2023-03-04
2022-12-14 | 2015 | Special Operations Command | 79456 |  | 2015-05-21 | 2015-08-31 | Lifecycle Construction Services | W912HN-13-D-0002 | 5997470 | 6178195 | 2016-11-11 | 2017-02-13
2022-12-14 | 2013 | Special Operations Command | 80233 |  | 2013-09-16 | 2014-01-22 | Trend Construction Inc | W912HN-12-D-0030 | 1531765 | 1570203 | 2015-02-27 | 2015-03-04
2022-12-14 | 2018 | Special Operations Command | 80771 |  | 2017-11-16 | 2018-09-27 | MEB General Contractors, Inc | W9123618C0025 | 50257000 | 54764292 | 2020-12-26 | 2022-12-15
2022-12-14 | 2019 | Special Operations Command | 80772 |  | 2020-07-10 | 2021-05-10 | HSU Development, Inc | W912DR-17-D-0015 | 7745692 | 8786667 | 2023-06-10 | 2023-09-08
2022-12-14 | 2016 | Special Operations Command | 80773 |  | 2016-07-27 | 2016-11-21 | ACC Construction Co., Inc. | W912PM-17-C-0001 | 32661077 | 33207816 | 2019-01-31 | 2019-06-06
2022-12-14 | 2019 | Special Operations Command | 80774 |  | 2019-06-10 | 2019-09-30 | ACC | W912PM19C0042 | 17061326 | 17347588 | 2022-01-06 | 2023-02-13
2022-12-14 | 2019 | Special Operations Command | 80775 |  | 2020-03-05 | 2020-09-29 | Balfour Beatty Construction, LLC | W9123620C2025 | 104543631 | 114020057 | 2023-02-22 | 2024-08-30
2022-12-14 | 2020 | Special Operations Command | 81165 |  | 2020-07-24 | 2020-09-18 | ACC CONSTRUCTION CO., INC. | W912PM20C0031 | 24885638 | 26637401 | 2023-03-08 | 2023-12-15
2022-12-14 | 2013 | Special Operations Command | 81483 |  | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F-13-C-0006 | 1513371 | 1642769 | 2014-09-15 | 2014-11-26
2022-12-14 | 2018 | Special Operations Command | 81894 |  | 2018-06-19 | 2018-09-17 | Attaway Construction | W912PM18C0019 | 4123177 | 4581868 | 2019-11-27 | 2020-10-30
2022-12-14 | 2016 | Special Operations Command | 81897 |  | 2015-12-18 | 2016-11-18 | BUTT CONSTRUCTION COMPANY, INC | W912QR-17-C-0002 | 11975000 | 12544449 | 2018-08-26 | 2019-01-30
2022-12-14 | 2019 | Special Operations Command | 81899 |  | 2019-01-10 | 2019-04-19 | Guarantee Co of North America | W9128F19C0016 | 8794325 | 9276699 | 2021-05-31 | 2023-01-28
2022-12-14 | 2018 | Special Operations Command | 81903 |  | 2018-10-30 | 2019-03-25 | KYUDENKO CORPORATION | W912HV19C0004 | 17057035 | 17938694 | 2021-04-18 | 2022-10-04
2022-12-14 | 2012 | Special Operations Command | 83011 |  | 2012-05-15 | 2012-08-31 | Okland Geneva Joint Venture | W912PP-12-C-0023 | 22227916 | 24626857 | 2014-05-01 | 2014-03-05
2022-12-14 | 2013 | Special Operations Command | 83702 |  | 2013-07-01 | 2013-09-18 | WG Yates & Sons Construction Co | W91278-12-D-0040 | 25870100 | 29269603 | 2015-06-28 | 2016-09-30
2022-12-14 | 2017 | Special Operations Command | 85958 |  | 2017-12-01 | 2019-04-11 | Windamir Development, Inc. | W912PM19C0020 | 11507959 | 12698129 | 2021-04-28 | 2023-01-04
2022-12-14 | 2020 | Special Operations Command | 86021 |  | 2020-02-28 | 2020-07-20 | Russell Construction Co | W912PM20C0018 | 10284300 | 10698922 | 2022-09-09 | 2023-02-06
2022-12-14 | 2021 | Special Operations Command | 86022 |  | 2021-03-10 | 2021-08-10 | Harper Construction Company, Inc. | W912PL21C0017 | 45167317 | 45556630 | 2023-11-07 | 2023-11-07
2022-12-14 | 2019 | Special Operations Command | 86025 |  | 2021-07-12 | 2022-02-04 | Coakley & Williams | W912DR22C0009 | 19009300 | 19580749 | 2024-06-19 | 2024-06-19
2022-12-14 | 2021 | Special Operations Command | 87437 |  | 2020-10-08 | 2021-06-09 | Messer Construction Co. | W912PM21C0006 | 30661544 | 31129741 | 2025-01-03 | 2025-01-03
2022-12-14 | 2019 | Special Operations Command | 87438 |  | 2019-05-28 | 2020-11-30 | Archer Western Federal JV | W912QR21C0003 | 4970375 | 5439796 | 2022-05-01 | 2022-06-29
2022-12-14 | 2021 | Special Operations Command | 88658 |  | 2020-11-20 | 2021-05-20 | Walsh Federal LLC | W912PM21C0008 | 27957700 | 32000425 | 2023-03-10 | 2024-03-21
2022-12-14 | 2022 | Special Operations Command | 91018 |  | 2022-05-13 | 2022-09-02 | John C. Grimberg Co., Inc. | W912DR22C0036 | 26435000 | 26435000 | 2024-10-15 | 2024-10-15
2022-12-14 | 2020 | Special Operations Command | 92594 |  | 2020-02-12 | 2020-06-19 | Sauer Incorporated | W912PM20C0016 | 20768000 | 22357834 | 2022-03-03 | 2022-09-06
2022-12-14 | 2008 | Special Operations Command | A73010 |  | 2009-02-13 | 2009-09-01 | IAP Worldwide Services, Inc. | W912ER-09-C-0035 | 6639338 | 6799124 | 2011-02-05 | 2012-11-15
2022-12-14 | 2016 | Special Operations Command | AFSOC103002 |  | 2018-04-09 | 2018-09-28 | NIPPO CORPORATION | W912HV-16-D-0008 | 33751828 | 34992358 | 2020-10-21 | 2021-02-17
2022-12-14 | 2017 | Special Operations Command | AFSOC103010 |  | 2020-07-24 | 2021-04-14 | NIPPO CORPORATION | W912HV21C0002 | 10759517 | 11021003 | 2023-06-04 | 2023-06-04
2022-12-14 | 2017 | Special Operations Command | AFSOC103022 |  | 2018-03-23 | 2019-08-02 | NIPPO CORPORATION | W912HV-17-D-0015 | 63052343 | 67428172 | 2021-12-26 | 2022-04-27
2022-12-14 | 2016 | Special Operations Command | ANZY163001 |  | 2017-09-15 | 2018-02-22 | Southeast Cherokee Construction, Inc | W91278-16-D-0015 | 19344000 | 20218608 | 2019-10-03 | 2022-09-06
2022-12-14 | 2015 | Special Operations Command | CZQZ063029 |  | 2016-12-13 | 2018-10-05 | Federal Contracting, Inc. | W912PP19C0001 | 36206044 | 38469776 | 2021-05-16 | 2022-08-17
2022-12-14 | 2012 | Special Operations Command | CZQZ083012 |  | 2012-05-07 | 2012-08-31 | Hensel Phelps Construction Co | W912PP-12-C-0027 | 28160000 | 29398390 | 2014-09-04 | 2014-10-02
2022-12-14 | 2013 | Special Operations Command | CZQZ083013 |  | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP-14-C-0014 | 19481987 | 19876398 | 2015-11-22 | 2015-10-15
2022-12-14 | 2016 | Special Operations Command | CZQZ083021 |  | 2016-06-16 | 2017-02-08 | SHEFFIELD KORTE JOINT VENTURE | W912PP-14-D-0025 | 11900000 | 11940630 | 2018-11-13 | 2018-11-09
2022-12-14 | 2018 | Special Operations Command | CZQZ103006 |  | 2018-04-26 | 2018-09-28 | Walga Ross Group JV | W912PP18C0022 | 5732950 | 5868773 | 2020-01-13 | 2020-05-27
2022-12-14 | 2016 | Special Operations Command | CZQZ133003 |  | 2016-12-13 | 2018-10-05 | Federal Contracting, Inc. | W912PP19C0001 | 16606634 | 17302482 | 2021-05-16 | 2022-08-17
2022-12-14 | 2016 | Special Operations Command | FTEV073010 |  | 2016-03-19 | 2016-08-02 | Delta Mechanical Contractors, LLC | W91278-16-C-0021 | 16065430 | 16492443 | 2018-09-15 | 2022-05-31
2022-12-14 | 2021 | Special Operations Command | FTEV103005 |  | 2021-07-09 | 2022-07-22 | Conti Federal Services, LLC | W9127822C0026 | 49686478 | 49686478 | 2025-02-28 | 2025-02-28
2022-12-14 | 2018 | Special Operations Command | FTEV153003 |  | 2018-07-27 | 2018-09-27 | Leebcor Services, LLC | W91278-16-D-0033 | 10689719 | 11276299 | 2020-04-23 | 2022-11-30
2022-12-14 | 2020 | Special Operations Command | FTEV153007 |  | 2020-06-03 | 2020-09-30 | Speegle Construction, Inc | W9127820C0026 | 11836700 | 12516053 | 2022-11-22 | 2023-01-07
2022-12-14 | 2018 | Special Operations Command | FTEV153008 |  | 2019-06-27 | 2020-02-27 | RC Construction Co, Inc | W9127820C0009 | 30127950 | 29988818 | 2023-03-18 | 2023-03-18
2022-12-14 | 2020 | Special Operations Command | FTEV153009 |  | 2020-11-06 | 2021-02-26 | Hensel Phelps Construction Co | W9127821C0008 | 66581000 | 67627705 | 2024-05-18 | 2024-07-19
2022-12-14 | 2020 | Special Operations Command | FTEV153010 |  | 2020-04-15 | 2020-09-09 | Speegle Construction, Inc | W9127820C0028 | 13214700 | 15715649 | 2022-10-10 | 2022-12-20
2022-12-14 | 2021 | Special Operations Command | FTEV153011 |  | 2021-05-26 | 2021-09-21 | RC Construction Co, Inc | W9127821C0038 | 27592000 | 27592000 | 2024-10-24 | 2024-10-24
2022-12-14 | 2013 | Special Operations Command | FTFA113004 |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 | 29942300 | 32051388 | 2016-12-25 | 2017-05-26
2022-12-14 | 2018 | Special Operations Command | FTFA163001 |  | 2019-07-12 | 2020-09-03 | EMR, Inc | W91278-16-D-0035 | 7234190 | 7268236 | 2022-03-30 | 2022-09-29
2022-12-14 | 2020 | Special Operations Command | FTFA163002 |  | 2021-04-14 | 2021-07-26 | David Boland, Inc | W9127821C0030 | 15629263 | 15660564 | 2023-09-10 | 2023-09-10
2022-12-14 | 2017 | Special Operations Command | LXEZ123484 |  | 2018-04-12 | 2019-05-30 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV-16-D-0009 | 16739026 | 17214008 | 2021-09-27 | 2021-09-29
2022-12-14 | 2012 | Special Operations Command | NVZR123709 |  | 2012-05-15 | 2012-07-31 | The Clement Group, LLC | W91278-11-D-0028 | 9981550 | 10581450 | 2014-01-19 | 2015-01-07
2022-12-14 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co | W91278-12-D-0038 | 34157000 | 38234191 | 2019-01-26 | 2019-11-19
2022-12-14 | 2020 | Special Operations Command | PQWY083008 |  | 2019-12-13 | 2020-05-28 | Jabez-Absher Small Business Joint Venture | W912DW20C0005 | 42743158 | 47919763 | 2022-06-16 | 2022-12-23
2022-12-20 | 2015 | Special Operations Command | Q1119 |  | 2015-08-05 | 2015-09-29 | COX CONSTRUCTION CO | N6247315D2405 0003 | 12428 | 12167 | 2016-04-06 | 2016-04-06
2022-12-20 | 2016 | Special Operations Command | Q1126 |  | 2016-05-10 | 2016-08-08 | A&D GC INC | N6247315D2403 0005 | 10911 | 11674 | 2018-02-14 | 2019-02-28
2022-12-20 | 2016 | Special Operations Command | Q1219 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 64004 | 65569 | 2020-01-12 | 2022-03-31
2022-12-20 | 2016 | Special Operations Command | Q1288 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 14741 | 15421 | 2020-01-12 | 2022-03-31
2022-12-20 | 2018 | Special Operations Command | Q1394 |  | 2019-09-17 | 2020-03-27 | WHITING-TURNER CONTRACTING CO | N4008520D0036 | 11658 | 13415 | 2021-10-04 | 2022-06-30
2022-12-20 | 2018 | Special Operations Command | Q1394B |  | 2022-04-26 | 2022-09-13 | WHITING-TURNER CONTRACTING CO | N4008520D0036 | 0 | 11879 | 2023-05-04 | 2023-05-04
2022-12-20 | 2020 | Special Operations Command | Q1395 |  | 2020-07-14 | 2020-12-18 | WHITING-TURNER CONTRACTING CO | N4008521C0018 AWD | 15417 | 20659 | 2022-12-17 | 2023-02-17
2022-12-20 | 2015 | Special Operations Command | Q1396 |  | 2015-05-29 | 2015-08-17 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0012 | 10331 | 13052 | 2017-03-09 | 2017-10-27
2022-12-20 | 2014 | Special Operations Command | Q1469 |  | 2014-08-20 | 2014-09-30 | Awarded by Other Agency | N4008510D0261 | 1944 | 1938 | 2015-11-24 | 2016-08-25
2022-12-20 | 2015 | Special Operations Command | Q1475 |  | 2018-02-07 | 2018-06-19 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008518C6101 | 3136 | 3130 | 2019-09-13 | 2021-01-14
2022-12-20 | 2016 | Special Operations Command | Q1481 |  | 2018-03-05 | 2018-08-31 | LARION HUMPHREY CONSTRUCTION LLC | N4008518C6118 | 3716 | 3594 | 2019-11-11 | 2020-07-06
2022-12-20 | 2020 | Special Operations Command | Q1482 |  | 2020-06-30 | 2020-09-22 | QUADRANT CONSTRUCTION, INC | N4008515D0851 N4008520F6725 | 5152 | 5191 | 2021-09-18 | 2023-07-15
2022-12-20 | 2020 | Special Operations Command | Q1534 |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 26080 | 31044 | 2024-05-27 | 2025-02-07
2022-12-20 | 2014 | Special Operations Command | Q157 |  | 2014-11-13 | 2016-02-26 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0008 | 19230 | 24016 | 2017-09-03 | 2020-09-16
2022-12-20 | 2015 | Special Operations Command | Q166 |  | 2015-05-05 | 2015-09-21 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0011 | 13588 | 13362 | 2017-07-17 | 2019-03-04
2022-12-20 | 2015 | Special Operations Command | Q170 |  | 2015-03-10 | 2016-01-26 | PENTACON, LLC | N6945014D0757 0002 | 10593 | 10462 | 2017-10-17 | 2018-06-16
2022-12-20 | 2015 | Special Operations Command | Q183 |  | 2013-08-12 | 2014-04-17 | CLARK NEXSEN - CH2M HILL - NORFOLK | N6247011D1010 WE11 | 15050 | 16162 | 2017-10-01 | 2018-05-18
2022-12-20 | 2019 | Special Operations Command | Q200 |  | 2019-01-30 | 2020-06-30 | RQ CONSTRUCTION, LLC | N6247317D0820 N6247320F4839 | 26431 | 31850 | 2023-01-20 | 2023-01-20
2022-12-20 | 2020 | Special Operations Command | Q224 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N4008519D9070 N4008521F4540 | 26797 | 26220 | 2023-08-05 | 2023-10-04
2022-12-20 | 2016 | Special Operations Command | Q225 |  | 2017-09-05 | 2018-08-03 | TIKIGAQ CONSTRUCTION, LLC | N4008517D0362 | 3455 | 3450 | 2019-10-22 | 2020-01-07
2022-12-20 | 2015 | Special Operations Command | Q240 |  | 2019-04-22 | 2019-07-29 | TIKIGAQ CONSTRUCTION, LLC | N6945019C5214 | 18436 | 16982 | 2020-01-25 | 2020-01-25
2022-12-20 | 2018 | Special Operations Command | Q241 |  | 2019-08-08 | 2019-09-26 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008514D1322 | 4921 | 9087 | 2020-11-13 | 2021-04-16
2022-12-20 | 2021 | Special Operations Command | Q246U |  | 2021-06-24 | 2021-09-28 | DRACE ANDERSON JOINT VENTURE | N6945018D1323 N6945021F0743 | 0 | 3448 | 2022-10-03 | 2024-01-02
2022-12-20 | 2014 | Special Operations Command | Q334 |  | 2015-07-21 | 2016-02-10 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0007 | 29668 | 31359 | 2018-07-29 | 2020-05-01
2022-12-20 | 2015 | Special Operations Command | Q418 |  | 2015-06-12 | 2015-08-18 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0006 | 20585 | 37452 | 2017-02-23 | 2018-02-12
2022-12-20 | 2020 | Special Operations Command | Q463 |  | 2019-08-29 | 2020-04-15 | HENSEL PHELPS CONSTRUCTION CO. | N6247819D5029 | 0 | 65022 | 2022-04-15 | 2022-04-15
2022-12-20 | 2021 | Special Operations Command | Q651U |  | 2021-08-26 | 2022-01-07 | AHTNA-CDM JV | N6247319D1220 N6247322F4212 | 0 | 4532 | 2023-07-18 | 2023-07-18
2022-12-20 | 2018 | Special Operations Command | Q698 |  | 2020-12-21 | 2021-03-24 | SYNCON, LLC | N4008518D1143 N4008521F4963 | 2846 | 4494 | 2022-08-08 | 2022-08-08
2022-12-20 | 2014 | Special Operations Command | Q771 |  | 2018-07-13 | 2018-09-19 | SOLPAC CONSTRUCTION INC | N6247317D0821 | 32018 | 34180 | 2020-02-02 | 2022-07-25
2022-12-20 | 2015 | Special Operations Command | Q776 |  | 2015-08-26 | 2015-09-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247315D2426 0002 | 30528 | 37009 | 2017-10-23 | 2019-07-23
2022-12-20 | 2016 | Special Operations Command | Q777 |  | 2016-10-31 | 2018-07-16 | WHITING-TURNER CONTRACTING CO | N4008518C1137 | 24780 | 25675 | 2020-10-09 | 2022-08-16
2022-12-20 | 2018 | Special Operations Command | Q791 |  | 2018-01-19 | 2018-09-13 | HOURIGAN CONSTRUCTION CORPORATION | N4008518C1103 | 24701 | 29132 | 2021-03-17 | 2021-11-17
2022-12-20 | 2020 | Special Operations Command | Q824 |  | 2020-08-05 | 2020-09-30 | ASTURIAN-CONSIGLI JV, LLC | N4008518D1124 N4008520F6689 | 12500 | 12604 | 2022-08-16 | 2022-08-16
2022-12-20 | 2019 | Special Operations Command | Q834 |  | 2019-03-22 | 2019-11-12 | Awarded by Other Agency | N4008518D1125 N4008520F4066 | 10586 | 10308 | 2021-05-20 | 2021-11-17
2022-12-20 | 2018 | Special Operations Command | Q855 |  | 2017-11-08 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N6247319C1238 | 96932 | 98458 | 2022-08-30 | 2023-02-10
2022-12-20 | 2017 | Special Operations Command | Q889 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N6247314D0061 | 36321 | 65067 | 2020-03-31 | 2021-01-31
2022-12-20 | 2017 | Special Operations Command | Q890 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N6247317C0830 | 37097 | 35530 | 2020-03-31 | 2021-01-31
2022-12-20 | 2018 | Special Operations Command | Q892 |  | 2017-11-07 | 2018-09-13 | RQ CONSTRUCTION, LLC | N6247318C1017 | 49562 | 48325 | 2021-03-31 | 2021-06-13
2022-12-20 | 2015 | Special Operations Command | Q893 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N6247315C1609 AWD | 24873 | 24400 | 2018-04-02 | 2019-03-11
2022-12-20 | 2017 | Special Operations Command | Q900 |  | 2018-06-28 | 2019-02-22 | SYNCON, LLC | N4008518D1143 | 3422 | 3323 | 2020-02-10 | 2021-04-30
2022-12-20 | 2021 | Special Operations Command | Q907 |  | 2021-03-07 | 2021-05-07 | TBD | N4008520D0036 #N4008521F5235 | 44471 | 47849 | 2023-07-26 | 2024-02-21
2022-12-20 | 2022 | Special Operations Command | Q912 |  | 2021-11-29 | 2022-05-12 | VANDER WERFF, PETER CONSTRUCTION | N6247320D1125 N6247322F4459 | 12442 | 12436 | 2024-06-11 | 2024-06-11
2022-12-20 | 2020 | Special Operations Command | Q914U |  | 2020-07-09 | 2020-10-07 | ASTURIAN-CONSIGLI JV, LLC | N4008518D1124 N4008521F4027 | 5098 | 5269 | 2022-04-23 | 2022-11-30
2022-12-20 | 2019 | Special Operations Command | Q918 |  | 2019-05-01 | 2019-09-26 | THE HASKELL COMPANY | N6247317D0818 | 15182 | 14862 | 2021-10-09 | 2022-02-24
2022-12-20 | 2017 | Special Operations Command | Q919 |  | 2016-09-20 | 2017-03-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 18210 | 18051 | 2018-10-22 | 2020-03-06
2022-12-20 | 2016 | Special Operations Command | Q920 |  | 2016-05-12 | 2016-09-20 | RQ CONSTRUCTION, LLC | N6247315D2428 0003 | 47022 | 45942 | 2018-10-13 | 2019-12-27
2022-12-20 | 2018 | Special Operations Command | Q921 |  | 2018-02-14 | 2018-07-26 | RQ CONSTRUCTION, LLC | N6247318D0820 | 47550 | 46909 | 2021-02-15 | 2021-06-18
2022-12-20 | 2014 | Special Operations Command | Q9440 |  | 2014-12-15 | 2015-04-30 | ARGO SYSTEMS, LLC | N6945014D1271 0003 | 4140 | 4085 | 2016-08-22 | 2019-07-17
2022-12-20 | 2020 | Special Operations Command | Q945 |  | 2020-01-23 | 2021-01-15 | EG DESIGNBUILD, L.L.C | N6945019D0919 N6945021F0872 | 18408 | 18219 | 2022-10-31 | 2023-08-03
2022-12-20 | 2019 | Special Operations Command | Q949 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N6247317D0822 N6247320F4023 | 15467 | 16370 | 2022-05-19 | 2022-12-23
2022-12-20 | 2019 | Special Operations Command | Q950 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N6247317D0822 N6247320F4023 | 18434 | 20366 | 2022-05-19 | 2022-12-23
2022-12-20 | 2022 | Special Operations Command | Q951 |  | 2021-12-16 | 2022-06-16 | TBD | TBD | 13142 | 20215 | 2025-01-02 | 2025-04-03
2022-12-20 | 2017 | Special Operations Command | Q952 |  | 2017-04-28 | 2017-08-10 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 16668 | 16762 | 2019-11-22 | 2020-03-02
2022-12-20 | 2018 | Special Operations Command | Q964 |  | 2018-02-22 | 2018-09-13 | RQ CONSTRUCTION, LLC | N6247318C1017 | 39378 | 38089 | 2021-03-31 | 2021-06-13
2022-12-20 | 2017 | Special Operations Command | Q966 |  | 2017-04-28 | 2017-09-28 | M A MORTENSON COMPANY | N6247317D0819 | 46106 | 44895 | 2020-04-19 | 2020-11-20
2022-12-20 | 2021 | Special Operations Command | Q997 |  | 2020-10-14 | 2021-05-07 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008521F5236 | 48939 | 4397 | 2024-03-16 | 2024-03-16
2022-12-20 | 2020 | Special Operations Command | Q999 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N4008519D9070 N4008521F4540 | 10850 | 11538 | 2023-08-05 | 2023-10-04
2022-12-14 | 2016 | Special Operations Command | TMKH003003 |  | 2017-04-07 | 2018-06-07 | Leebcor Services, LLC. | W912PM18C0013 | 15241121 | 15194631 | 2020-01-22 | 2020-09-22
2023-01-31 | 2018 | Washington Headquarters Services | 102299 |  | 2022-08-26 | 2022-08-30 | Signature Renovations LLC | HQ0034-19-D-0018 | 1165538 | 1165538 | 2023-08-26 | 2023-09-08
2023-01-31 | 2015 | Washington Headquarters Services | 80011 |  | 2018-08-20 | 2019-05-09 | Cherokee Nations Environmental Solutions | HQ0034-19-C-0043 | 15100000 |  | 2021-06-21 | 2023-02-28
2023-01-31 | 2018 | Washington Headquarters Services | 87637 |  | 2018-07-05 | 2020-03-27 | Sauer Incorporated | W912DR-20-C-0014 | 9711000 | 9711000 | 2022-06-21 | 2024-01-01
2023-01-31 | 2019 | Washington Headquarters Services | 87645 |  | 2019-07-22 | 2019-09-30 | John C. Grimberg Co, Inc. | W912DR19C0057 | 9255000 | 9255000 | 2021-04-23 | 2023-07-31
2023-01-31 | 2019 | Washington Headquarters Services | 88790 |  | 2019-10-25 | 2020-03-27 | Grunley Construction Company, Inc. | W912DR-20-C-0015 | 20553000 | 20553000 | 2022-07-05 | 2022-11-10
2023-01-31 | 2018 | Washington Headquarters Services | 88963 |  | 2019-05-22 | 2020-01-07 | HSU Development, Inc | W912DR-17-D-0015 | 11774418 |  | 2022-01-20 | 2022-10-14
2023-01-31 | 2022 | Washington Headquarters Services | 90570
2023-01-31 | 2018 | Washington Headquarters Services | 91474 |  | 2019-03-08 | 2019-06-28 | Grunley Construction Company, Inc. | W912DR-17-D-0002 | 24006000 |  | 2021-01-20 | 2024-02-12
2023-01-31 | 2018 | Washington Headquarters Services | 91474A |  | 2018-03-06 | 2018-09-25 | MC DEAN | HQ0034-17-D-0006 | 1186116 | 1186116 | 2019-06-18 | 2019-06-18
2023-01-31 | 2020 | Washington Headquarters Services | 91531
2023-01-31 | 2020 | Washington Headquarters Services | 92232 |  | 2020-03-12 | 2021-03-25 | Grunley Construction Company, Inc. | W912DR-21-C-0009 | 16690000 | 16690000 | 2023-04-27 | 2024-02-27
2023-01-31 | 2022 | Washington Headquarters Services | 95677 |  | 2022-01-21 | 2022-08-17 | Grunley Construction Company, Inc. | W912DR-22-D-0007 | 6272000 | 6272000 | 2023-10-03
2023-01-31 | 2022 | Washington Headquarters Services | 95696
2023-01-31 | 2023 | Washington Headquarters Services | 97665

## EXPENDITURES
Expenditure Data as of Date | Appropriation Fiscal Year | Project Sponsor Component Name | Appropriation Fund Type Name | Use of Funds | Aggregated Appropriated Amount | Aggregated Current Obligated Amount | Aggregated Current Expenditure Amount
2022-12-01 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73646000 | 60586000 | 61380000
2022-12-01 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093000 | 3156000 | 18347000
2022-12-01 | 2016 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 94590000 | 35178000 | 77975000
2022-12-01 | 2017 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 56984000 | 56954000 | 38697000
2022-12-01 | 2018 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 80617000 | 74561000 | 24940000
2022-12-01 | 2019 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 75247000 | 72129000 | 0
2022-12-01 | 2020 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 100222000 | 87192000 | 1986000
2022-12-01 | 2022 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 105258000 | 35082000 | 145000
2022-12-01 | 2015 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 0 | 0 | 0
2022-12-01 | 2021 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 94245000 | 48111000 | 8000
2022-12-01 | 2023 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 251588000 | 0 | 0
2022-12-01 | 2021 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 161809000 | 161753000 | 110367000
2022-12-01 | 2022 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 122394000 | 121696000 | 32911000
2022-12-01 | 2023 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 9383000 | 1371000
2022-12-01 | 2018 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 138783000 | 136816000 | 121139000
2022-12-01 | 2019 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 158232000 | 159073000 | 104307000
2022-12-01 | 2020 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 122590000 | 120954000 | 78025000
2022-12-01 | 2013 | Air Force Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 326000 | 326000 | 326000
2022-12-01 | 2014 | Air Force Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 23291000 | 23291000 | 23291000
2022-12-01 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 10738000 | 10705000 | 9733000
2022-12-01 | 2016 | Air Force Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 87809000 | 87061000 | 81345000
2022-12-01 | 2017 | Air Force Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 199393000 | 191635000 | 190111000
2022-12-01 | 2018 | Air Force Active | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 217485000 | 208144000 | 193968000
2022-12-01 | 2019 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 450277000 | 416730000 | 382715000
2022-12-01 | 2020 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 332636000 | 258916000 | 185451000
2022-12-01 | 2022 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 332575000 | 84669000 | 17842000
2022-12-01 | 2021 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 271356000 | 184173000 | 121374000
2022-12-01 | 2023 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 332575000 | 84669000 | 17842000
2022-12-01 | 2021 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 2969000 | 1010000 | 963000
2022-12-01 | 2015 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 0 | 0 | 0
2022-12-01 | 2022 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 10458000 | 975000 | 0
2022-09-30 | 2013 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY14 MILCON; design of FY13 non-PB projects if any; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 2329000 | 293000 | 735000
2022-12-01 | 2014 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267000 | 0 | 0
2022-09-30 | 2016 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY17 MILCON; design of FY16 non-PB projects if any; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 9849000 | 2528000 | 2695000
2022-09-30 | 2017 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY18 MILCON; design of FY17 non-PB projects if any; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4368000 | 3027000 | 4307000
2022-09-30 | 2018 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY19 MILCON; design of FY18 non-PB projects if any; start design of F20 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4445000 | 2087000 | 4242000
2022-09-30 | 2019 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY20 MILCON; design of FY19 non-PB projects if any; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3199000 | 2319000 | 1687000
2022-09-30 | 2020 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3409000 | 2845000 | 2845000
2022-12-01 | 2013 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 18773000 | 18773000 | 18773000
2022-12-01 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448000 | 20230000 | 20028000
2022-12-01 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5548000 | 5548000 | 5548000
2022-12-01 | 2016 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22900000 | 21810000 | 21606000
2022-12-01 | 2017 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 41237000 | 40409000 | 36377000
2022-12-01 | 2018 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 41400000 | 40439000 | 31198000
2022-12-01 | 2019 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 32967000 | 14540000 | 12138000
2022-12-01 | 2020 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 87082000 | 57523000 | 24900000
2022-12-01 | 2022 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 109244000 | 13588000 | 210000
2022-12-01 | 2021 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 94778000 | 14879000 | 5881000
2022-12-01 | 2023 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 109244000 | 13588000 | 210000
2023-01-31 | 2022 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 20830000 | 5297000 | 733000
2023-01-31 | 2011 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1650000 | 1521000 | 1521000
2023-01-31 | 2012 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200000 | 1285000 | 1287000
2023-01-31 | 2013 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 2875000 | 426000 | 426000
2023-01-31 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229000 | 66000 | 66000
2023-01-31 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892000 | 72000 | 477000
2023-01-31 | 2016 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 13400000 | 957000 | 1083000
2023-01-31 | 2017 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs. | 13500000 | 6595000 | 7488000
2023-01-31 | 2018 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs. | 24725000 | 16070000 | 23700000
2023-01-31 | 2019 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs. | 4055000 | 3871000 | 3541000
2023-01-31 | 2020 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 4604000 | 3566000 | 2489000
2023-01-31 | 2021 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 11270000 | 9616000 | 3348000
2023-01-31 | 2011 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 2753000 | 2646000 | 2646000
2023-01-31 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5434000 | 2260000 | 2258000
2023-01-31 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997000 | 0 | 0
2023-01-31 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530000 | 44000 | 59000
2023-01-31 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400000 | 607000 | 666000
2023-01-31 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6121000 | 1320000 | 3399000
2023-01-31 | 2017 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1500000 | 0 | 0
2023-01-31 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13610000 | 9561000 | 5726000
2023-01-31 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3358000 | 3358000 | 0
2023-01-31 | 2020 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 12146000 | 3131000 | 13000
2023-01-31 | 2021 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5647000 | 0 | 0
2023-01-31 | 2022 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15444000 | 0 | 0
2022-11-30 | 2013 | Air National Guard | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 4000000 | 1594000 | 1594000
2022-12-31 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400000 | 626000 | 518000
2022-12-31 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700000 | 885000 | 884000
2022-12-31 | 2016 | Air National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 5104000 | 982000 | 971000
2022-12-31 | 2017 | Air National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs. | 10462000 | 111152000 | 9853000
2022-12-31 | 2018 | Air National Guard | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs. | 18000000 | 35116000 | 30939000
2022-12-31 | 2019 | Air National Guard | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs. | 33114000 | 13772000 | 11645000
2022-12-31 | 2022 | Air National Guard | Planning and Design - Military Construction | Complete design of FY23 MILCON; start design of FY24 MILCON; fund Congressionally directed designs. | 45553000 | 0 | 0
2022-12-31 | 2020 | Air National Guard | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 12421000 | 7998000 | 3423000
2022-12-31 | 2021 | Air National Guard | Planning and Design - Military Construction | Complete design of FY22 MILCON; start design of FY23 MILCON; fund Congressionally directed designs. | 2600000 | 0 | 0
2022-12-31 | 2021 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000000 | 8925000 | 1270000
2022-12-31 | 2020 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 29454000 | 19303000 | 6738000
2022-12-31 | 2022 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 29068000 | 6022000 | 0
2022-12-31 | 2019 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 46145000 | 20874000 | 9954000
2022-12-31 | 2018 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17191000 | 26686000 | 20168000
2022-12-31 | 2017 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17495000 | 14996000 | 14971000
2022-12-31 | 2016 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7734000 | 404000 | 404000
2022-12-31 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6100000 | 4000 | 0
2022-12-31 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000000 | 1677000 | 1611000
2022-11-30 | 2013 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5900000 | 82000 | 82000
2023-01-31 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000000 | 33873062 | 33873062
2023-01-31 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000000 | 22999621 | 22999621
2023-01-31 | 2015 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28000000 | 27985359 | 27985359
2023-01-31 | 2016 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36000000 | 35998550 | 35818311
2023-01-31 | 2017 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 18000000 | 17998791 | 17998791
2023-01-31 | 2018 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28700000 | 28699745 | 27938474
2023-01-31 | 2019 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 16000000 | 15887109 | 15848031
2023-01-31 | 2020 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 31000000 | 30884019 | 30732809
2023-01-31 | 2021 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 39000000 | 38336803 | 36725297
2023-01-31 | 2022 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 27000000 | 14068795 | 12105735
2023-01-31 | 2013 | Army Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46173000 | 46090691 | 46090691
2023-01-31 | 2014 | Army Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575000 | 41552298 | 41539587
2023-01-31 | 2015 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 18127000 | 23112352 | 23112218
2023-01-31 | 2016 | Army Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 73245000 | 73137388 | 72301641
2023-01-31 | 2017 | Army Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 138559000 | 111866087 | 110061786
2023-01-31 | 2018 | Army Active | Planning and Design - Military Construction | Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 122470000 | 113401008 | 110019738
2023-01-31 | 2019 | Army Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 115067000 | 96822764 | 91099274
2023-01-31 | 2020 | Army Active | Planning and Design - Military Construction | Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 155847000 | 107344954 | 98671198
2023-01-31 | 2021 | Army Active | Planning and Design - Military Construction | Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 108000000 | 102762984 | 84041881
2023-01-31 | 2022 | Army Active | Planning and Design - Military Construction | Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 149649000 | 79096189 | 31211151
2023-01-31 | 2013 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4641000 | 4605750 | 4605750
2023-01-31 | 2014 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4408000 | 4370513 | 4350513
2023-01-31 | 2015 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 1309000 | 1305379 | 1275379
2023-01-31 | 2016 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7195000 | 7180054 | 7075842
2023-01-31 | 2017 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2618000 | 2617410 | 2585337
2023-01-31 | 2018 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 29271000 | 29270493 | 27991043
2023-01-31 | 2019 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 18326000 | 18276916 | 8821311
2023-01-31 | 2020 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 9222000 | 17048047 | 7713875
2023-01-31 | 2021 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 11300000 | 2825511 | 619426
2023-01-31 | 2022 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7545000 | 14016294 | 6878223
2023-01-31 | 2013 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24952530 | 24952530
2023-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24980592 | 24778829
2023-01-31 | 2015 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24890149 | 24663787
2023-01-31 | 2016 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 22975180 | 22488459
2023-01-31 | 2017 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 35000000 | 29827985 | 27997773
2023-01-31 | 2018 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 41500000 | 28671711 | 28212052
2023-01-31 | 2019 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 82000000 | 80418768 | 78105198
2023-01-31 | 2020 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 70600000 | 67866166 | 59899963
2023-01-31 | 2021 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 50900000 | 42885438 | 15417987
2023-01-31 | 2022 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 45543000 | 14716417 | 744006
2021-12-15 | 2017 | Army National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20729000 | 19783009 | 19783009
2021-12-15 | 2018 | Army National Guard | Planning and Design - Military Construction | Complete design of FY19 MILCON; design of FY18 Congressional Inserts & Recovery from Hurricanes; start design of FY20 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 74741000 | 68522570 | 68522570
2021-12-15 | 2019 | Army National Guard | Planning and Design - Military Construction | Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 16622000 | 16246754 | 16246754
2021-12-15 | 2020 | Army National Guard | Planning and Design - Military Construction | Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 26469000 | 3918620 | 3918620
2021-12-15 | 2021 | Army National Guard | Planning and Design - Military Construction | Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 44593000 | 98937 | 98937
2022-06-30 | 2022 | Army National Guard | Planning and Design - Military Construction | Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 57725000 | 0 | 0
2022-06-30 | 2022 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 52136000 | 0 | 0
2021-12-15 | 2017 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 12001000 | 11997485 | 11997485
2021-12-15 | 2018 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 26731000 | 26942010 | 26942010
2021-12-15 | 2019 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 28100000 | 16728955 | 14377502
2021-12-15 | 2020 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 15000000 | 6299049 | 6299049
2021-12-15 | 2021 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 45744000 | 2999906 | 2999906
2023-01-31 | 2010 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2023-01-31 | 2011 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2023-01-31 | 2012 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2023-01-31 | 2013 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2023-01-31 | 2014 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 3897000 | -1169000 | -1238000
2023-01-31 | 2015 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 4855000 | 5659000 | 5659000
2023-01-31 | 2016 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 94000 | 0 | 0
2023-01-31 | 2017 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2023-01-31 | 2018 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 40255000 | 16974000 | 16332000
2023-01-31 | 2019 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 55729000 | 25107000 | 21457000
2023-01-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2023-01-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2023-01-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2023-01-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2023-01-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4952000 | -1307000 | -1307000
2023-01-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4100000 | 2200000 | 2200000
2023-01-31 | 2016 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5000000 | 4927000 | 4913000
2023-01-31 | 2017 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 8433000 | 2598000 | 2583000
2023-01-31 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 7700000 | 3616000 | 3616000
2023-01-31 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2023-02-28 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 79430000 | 68213820 | 68213820
2023-02-28 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 2615000 | 2810000 | 2810000
2023-02-28 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 9600000 | 12189000 | 12189000
2023-02-28 | 2021 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 33728000 | 33728000 | 3466836
2022-09-30 | 2021 | Defense Intelligence Agency | Construction - Major Military Construction | Construction | 18454000 | 18454000 | 0
2022-09-30 | 2022 | Defense Intelligence Agency | Construction - Major Military Construction | Construction | 182950000 | 182950000 | 0
2022-05-11 | 2017 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2018 to 2021 | 27660000 | 27660000 | 24910066
2022-05-11 | 2022 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2023 to 2025 | 20862000 | 20862000 | 0
2022-05-11 | 2018 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2019 to 2022 | 23012000 | 23012000 | 23012000
2022-05-11 | 2019 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2020 to 2023 | 49805000 | 44805000 | 38504924
2022-05-11 | 2020 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2021 to 2024 | 27000000 | 27000000 | 3864479
2022-05-11 | 2021 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2021 to 2022 | 9726000 | 9726000 | 0
2022-05-11 | 2022 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2022 to 2023 | 6668000 | 6668000 | 0
2022-05-11 | 2020 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2021 to 2022 | 16736000 | 16736000 | 2935443
2022-05-11 | 2019 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2019 to 2020 | 17366000 | 17366000 | 17366000
2022-05-11 | 2018 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2018 to 2019 | 2039000 | 2039000 | 2039000
2022-05-11 | 2015 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2015 to 2017 | 5932000 | 5932000 | 5932000
2023-02-06 | 2008 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI andFY 08/09/ 10/11/12 MILCON projects | 5161000 | 5159000 | 5159000
2023-02-06 | 2009 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13593000 | 13496000 | 13496000
2023-02-06 | 2010 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 10/11/ 12/13 MILCON projects | 8755000 | 8755000 | 8755000
2023-02-06 | 2011 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 11/12/ 13 MILCON projects | 75242000 | 75050000 | 75050000
2023-02-06 | 2012 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 12/13 MILCON projects | 64551000 | 63922443 | 63922443
2023-02-06 | 2013 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 13/14/15/16 MILCON projects | 97290000 | 95268921 | 95268921
2023-02-06 | 2014 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 14/15/16/17 MILCON projects | 75905000 | 74561100 | 74561100
2023-02-06 | 2015 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42387000 | 38303282 | 38303282
2023-02-06 | 2016 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42183000 | 38574364 | 38574364
2023-02-06 | 2017 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 23585000 | 19062095 | 19062095
2023-02-06 | 2009 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5000000 | 4000000 | 4000000
2023-02-06 | 2013 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3771000 | 3771000 | 3771000
2023-02-06 | 2014 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5409000 | 5409000 | 5409000
2023-02-06 | 2015 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 6846000 | 6846000 | 6846000
2023-02-06 | 2017 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3000000 | 2999834 | 2999834
2023-01-31 | 2019 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY20-21 MILCON Projects | 6184000 | 6176630 | 6165491
2023-01-31 | 2020 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY21-22 MILCON Projects | 35472000 | 24831285 | 24566810
2023-01-31 | 2022 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY23-24 MILCON Projects | 19000000 | 5478118 | 5354625
2023-01-31 | 2018 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY18/19 | 344000 | 343970 | 343970
2023-01-31 | 2019 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY19/20 | 10000000 | 3410197 | 0
2023-01-31 | 2020 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY19/20 | 10000000 | 0 | 0
2023-01-31 | 2021 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY21/22 | 4922000 | 0 | 0
2023-01-31 | 2022 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY22/23 | 4435000 | 0 | 0
2023-01-31 | 2018 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 1, Incr. 1); Small Business Project for IPO temporary facility | 200000000 | 200000000 | 199174266
2023-01-31 | 2019 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 1, Incr. 2 & Ph. 2, Incr. 1) | 291000000 | 291000000 | 197783987
2023-01-31 | 2020 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 2, Incr. 2) | 218800000 | 218800000 | 162403744
2023-01-31 | 2021 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 2, Incr. 3) | 119000000 | 119000000 | 472
2023-02-03 | 2021 | National Geospatial-Intelligence Agency | Unspecified Minor Military Construction | Renovation Project - NGA Arnold Rear Access Control Point | 4950000 | 4950000 | 2473209
2023-01-01 | 2012 | National Security Agency | Construction - Major Military Construction | Mountainview, Whitelaw Wedge, HPCC2, ICECUBE, ECB1, HPCC1, MHS Generator Plant | 333439089 | 331999386 | 331999386
2023-01-01 | 2013 | National Security Agency | Construction - Major Military Construction | MOD II, VCP1, Mountainview, HPCC2, ICECUBE, ECB1, HPCC1 | 510067383 | 506627864 | 506524892
2023-01-01 | 2014 | National Security Agency | Construction - Major Military Construction | HPCC2, ECB1 | 511998526 | 511997906 | 511349960
2023-01-01 | 2015 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - North, VCP1, NSAW Feeders - Central, ECB1, Access Control Facility | 99728000 | 97083366 | 96812325
2023-01-01 | 2016 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - Central, ECB2 | 67764547 | 67429084 | 67429084
2023-01-01 | 2017 | National Security Agency | Construction - Major Military Construction | Feeders Ph. 3, ECB2, Access Control Facility | 247239714 | 246939479 | 219450434
2023-01-01 | 2018 | National Security Agency | Construction - Major Military Construction | ECB2, EE Infra Construction | 318424461 | 317616473 | 317566334
2023-01-01 | 2019 | National Security Agency | Construction - Major Military Construction | ECB2, ECB3 | 407000000 | 399402559 | 340974077
2023-01-01 | 2020 | National Security Agency | Construction - Major Military Construction | ECB3, Mission Support Compound | 477000000 | 422532338 | 400093954
2023-01-01 | 2021 | National Security Agency | Construction - Major Military Construction | ECB3, Mission Support Compound | 250336721 | 180922640 | 60413968
2023-01-01 | 2022 | National Security Agency | Construction - Major Military Construction | ECB3, MORC | 244100000 | 45118043 | 134872638
2023-01-01 | 2022 | National Security Agency | Planning and Design - Military Construction | General P&D | 83840000 | 10390092 | 51559907
2023-01-01 | 2021 | National Security Agency | Planning and Design - Military Construction | General P&D | 10303000 | 2449944 | 3672152
2023-01-01 | 2020 | National Security Agency | Planning and Design - Military Construction | General P&D | 14000000 | 13995566 | 13329105
2023-01-01 | 2018 | National Security Agency | Planning and Design - Military Construction | General P&D | 20000000 | 19898575 | 16614195
2023-01-01 | 2017 | National Security Agency | Planning and Design - Military Construction | General P&D | 15442000 | 15352115 | 15145152
2023-01-01 | 2012 | National Security Agency | Planning and Design - Military Construction | General P&D | 23800910 | 23297538 | 23297538
2023-01-01 | 2013 | National Security Agency | Planning and Design - Military Construction | General P&D | 3823616 | 3255628 | 3255628
2023-01-01 | 2014 | National Security Agency | Planning and Design - Military Construction | General P&D | 13161473 | 12666068 | 12159345
2023-01-01 | 2015 | National Security Agency | Planning and Design - Military Construction | General P&D | 599000 | 591520 | 591520
2023-01-01 | 2016 | National Security Agency | Planning and Design - Military Construction | General P&D | 1078000 | 1077928 | 1077928
2023-01-01 | 2013 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3530000 | 3353911 | 3353911
2023-01-01 | 2014 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 1500000 | 1493362 | 1493362
2023-01-01 | 2015 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 4229000 | 3873686 | 3873686
2023-01-01 | 2017 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 26085 | 26085 | 26085
2023-01-01 | 2018 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 2254000 | 2202264 | 2202264
2023-01-01 | 2020 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3228000 | 0 | 0
2023-01-01 | 2021 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 0 | 0 | 0
2023-01-01 | 2022 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 12000000 | 0 | 0
2023-02-15 | 2019 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 16638000 | 5870000 | 15800000
2023-02-15 | 2020 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 41798000 | 39875000 | 7879000
2023-02-15 | 2021 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 37043000 | 32254000 | 10735000
2023-02-15 | 2022 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 84884000 | 0 | 0
2023-02-15 | 2023 | Navy Active | Improvements - Military Family Housing | Navy and Marine Corps Military Family Housing Improvement | 74540000 | 0 | 0
2023-02-15 | 2019 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 234359000 | 115898000 | 114660000
2023-02-15 | 2020 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 283977000 | 214715000 | 189169000
2023-02-15 | 2021 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 279500000 | 250857000 | 191287000
2023-02-15 | 2022 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed designs | 679652000 | 374084000 | 202426000
2023-02-15 | 2023 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY24 MILCON; design of FY23 Congressional Inserts; start design of FY25 MILCON; fund Congressionally directed designs | 397124000 | 40897000 | 26415000
2023-02-15 | 2019 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine CorpsFamily Housing Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 4502000 | 369000 | 324000
2023-02-15 | 2020 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 5863000 | 2021000 | 1085000
2023-02-15 | 2021 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 5854000 | 1160000 | 624000
2023-02-15 | 2022 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed designs | 5732000 | 1483000 | 398000
2023-02-15 | 2023 | Navy Active | Planning and Design - Military Family Housing | Navy and Marine Corps Family Housing Complete design of FY24 MILCON; design of FY23 Congressional Inserts; start design of FY25 MILCON; fund Congressionally directed designs | 14123000 | 561000 | 23000
2023-02-15 | 2019 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 28579000 | 25087000 | 18448000
2023-02-15 | 2020 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 81237000 | 68505000 | 28781000
2023-02-15 | 2021 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 38983000 | 28163000 | 9764000
2023-02-15 | 2022 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 131435000 | 15661000 | 4847000
2023-02-15 | 2023 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 109994000 | 0 | 0
2023-02-15 | 2019 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 4695000 | 1447000 | 1350000
2023-02-15 | 2020 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 4780000 | 1629000 | 623000
2023-02-15 | 2021 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 3485000 | 733000 | 0
2023-02-15 | 2022 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY23 MILCON; design of FY22 Congressional Inserts; start design of FY24 MILCON; fund Congressionally directed designs | 6005000 | 0 | 0
2023-02-15 | 2023 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY24 MILCON; design of FY23 Congressional Inserts; start design of FY25 MILCON; fund Congressionally directed designs | 2590000 | 0 | 0
2023-02-15 | 2019 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 3000000 | 800000 | 845000
2023-02-15 | 2020 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 24915000 | 4852000 | 3693000
2023-02-15 | 2021 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 3000000 | 0 | 0
2023-02-15 | 2022 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 2359000 | 0 | 0
2023-02-15 | 2023 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 27747000 | 0 | 0
2022-09-30 | 2013 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 25454000 | 25448053 | 25448053
2022-09-30 | 2014 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 36866000 | 36673438 | 36673438
2022-09-30 | 2015 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 24197000 | 24101632 | 24101632
2022-09-30 | 2016 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 31628000 | 31408469 | 31408469
2022-09-30 | 2017 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 27653000 | 27510934 | 27510934
2022-09-30 | 2022 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 20576000 | 12679644 | 12679644
2022-09-30 | 2018 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 39746000 | 39734726 | 39734726
2022-09-30 | 2019 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 55925000 | 50668753 | 50668753
2022-09-30 | 2020 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 52532000 | 48231815 | 48231815
2022-09-30 | 2021 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 32624000 | 17876824 | 17876824
2022-09-30 | 2021 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 17698000 | 15240536 | 15240536
2022-09-30 | 2020 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 31464000 | 26939429 | 26939429
2022-09-30 | 2019 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 13642000 | 13223314 | 13223314
2022-09-30 | 2018 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 7384000 | 7382955 | 7382955
2022-09-30 | 2022 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 21746000 | 21746000 | 21746000
2022-09-30 | 2017 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5994000 | 5889808 | 5889808
2022-09-30 | 2016 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 15676000 | 15664908 | 15664908
2022-09-30 | 2015 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 10334000 | 10188771 | 10188771
2022-09-30 | 2014 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5170000 | 5170001 | 5170001
2022-09-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 9216000 | 9215996 | 9215996
2023-01-31 | 2018 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 1942000 | 1942000 | 1835048
2023-01-31 | 2019 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 2036000 | 2036000 | 1818060
2023-01-31 | 2020 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4890000 | 2910306 | 491201
2023-01-31 | 2021 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 0 | 0 | 0
2023-01-31 | 2022 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 5275000 | 0 | 0