## Projects
Data as of Date | Submission Date | Fiscal Year | Component | Project type | State (2-Alpha)/ Country (3-Alpha) | State or Country Title | Installation | Project number | Project title | Solicitation/ Advertise Date | Award Date | Contract Recipient | Original Contract Amount ($000) | Current Contract Obligation ($000) | Start Date | Occupancy Date | Original Completion Date | Current Completion Date | Percent Complete | Funds Diverted ($000) (if applicable) | Recipient Project (if applicable) | Recipient Installation (if applicable) | Notes/Remarks
2013-07-31 | 2013-08-01 | 2012 | NGA | Military Construction | MO | MISSOURI | ARNOLD | NGA021 | Data Ctr West #1 Power & Cooling Upgrade | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors | 8202 | 9465 | 2012-08-06 | 2013-08-20 | 2013-08-06 | 2013-08-20 | 87 | 1525 |  |  | from NGA013
2013-07-31 | 2013-08-01 | 2012 | NGA | Military Construction | VA | VIRGINIA | FORT BELVOIR | NGA013 | Technology Center Third Floor Fit-out | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty - NCE, A Joint Venture | 32387 | 33013 | 2012-11-02 | 2013-11-02 | 2014-01-02 | 2014-01-02 | 60 | 1525 |  |  | to NGA021
2013-07-31 | 2013-08-01 | 2007 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR |  | Infrastructure Increments 1-3; NGA HQ's | Various | Various | Various |  |  | Various | 2011-09-15 | 2013-06-15 | 2013-09-30 | 99 |  |  |  | Const - Water Tank & CDC Infrastructure contract continues
2013-07-31 | 2013-08-01 | 2007 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR
2013-07-31 | 2013-08-01 | 2008 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR
2013-07-31 | 2013-08-01 | 2008 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR | 65416 | NGA Headquarters,SCIF, ALL PHASES | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty - NCE, A Joint Venture | 1181439 | 1398710 | 2007-09-06 | 2011-04-19 | 2011-12-22 | 2013-12-31 | 93 |  |  |  | Closeout efforts ongoing
2013-07-31 | 2013-08-01 | 2009 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR | 68472
2013-07-31 | 2013-08-01 | 2010 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR | 68474
2013-07-31 | 2013-08-01 | 2011 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR | 68475
2013-07-31 | 2013-08-02 | 2009 | NSA | Major Construction | MD | MARYLAND | NSAW | 21120 | South Campus Electrical Utility Plant-SCEUP (Phase 1) | 2010-05-03 | 2010-08-30 | Clark/ MC Dean | 18550 | 18550 | 2010-09-21 | 2013-01-17 | 2014-04-18 | 2013-01-17 | 99 |  |  |  | AFCEE returned Additional Funds rom PAII back to Building 1045 Extension.
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17872 | South Campus Electrical Utility Plant -SCEUP (Phase 2) | 2010-05-03 | 2010-08-30 | Clark/ MC Dean | 138400 | 138091 | 2010-09-21 | 2014-05-13 | 2014-04-18 | 2014-05-13 | 62 | 37500 |  |  | The funds diverted in this project have not been assigned to other project at the present time.
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) | 2009-05-04 | 2010-08-26 | Goels/Grunley | 4443 | 4544 | 2010-09-09 | 2012-06-29 | 2011-09-26 | 2012-06-29 | 100 |  |  |  | The construction cost is $4,443,532.86, which $4,393,532.86 is for construction and $50,000 is for escorts.
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) | 2012-10-17 | 2013-02-19 | District Veterans Contracting | 5253 | 6206 | 2013-05-15 | 2014-01-21 | 2014-02-19 | 2014-02-19 | 8
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17781 | Tordella Chilled Water Backup Storage | 2009-08-24 | 2010-06-24 | Nothern Tiaga Venture,LLC Inc. (NTVI) | 11700 | 11700 | 2010-06-30 | 2012-05-30 | 2011-08-20 | 2012-05-30 | 100
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17782 | R&E Chilled Water Backup Storage | 2011-05-31 | 2011-08-30 | Walsh Construction Company | 3200 | 3200 | 2011-11-07 | 2014-05-30 | 2013-07-13 | 2014-06-30 | 40 |  |  |  | The projects have different Projects Number but one MILCON funding line.
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | GBR | UNITED KINGDOM | MHS | 18052 (MWHL10-3001) | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2011-03-15 | NPGL | 7566 | 8257 | 2011-03-31 | 2014-04-01 | 2013-02-01 | 2014-04-01 | 80
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | GBR | UNITED KINGDOM | MHS | 18053 (MWHL10-3001) | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2012-02-15 | IUS | 16095 | 16448 | 2012-01-31 | 2014-05-31 | 2013-02-01 | 2014-05-31 | 41
2013-07-31 | 2013-08-02 | 2010 | NSA | Major Construction | GBR | UNITED KINGDOM | MHS | 18054 (MWHL10-3001) | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | 7085 | 7316 | 2012-11-30 | 2014-08-31 | 2013-02-01 | 2014-08-31 | 25 |  |  |  | NEDL - Offsite work. IUS - Onsite. Power and Cooling Infrastructure Upgrade includes the Power Upgrade OFF Base, Power Upgrade On Base, Power DSS AA&BB, Power Water Borehole and Power UPS and Cooling
2013-07-31 | 2013-08-02 | 2011 | NSA | Major Construction | CL | CLASSIFIED LOCATION | Classified Location | 22573 | Classified Project | 2012-08-15 | 2012-09-30 | Kaseman | 12000 | 21500 | 2012-12-01 | 2012-09-15 | 2012-09-30 | 2012-09-30 | 30
2013-07-31 | 2013-08-02 | 2011 | NSA | Major Construction | CL | CLASSIFIED LOCATION | Classified Location | 22573 | Classified Project | 2012-08-01 | 2012-09-21 | Hardline | 12000 | 12000 | 2012-09-25 | 2012-09-15 | 2013-04-04 | 2013-04-04 | 100
2013-07-31 | 2013-08-02 | 2011 | NSA | Major Construction | CL | CLASSIFIED LOCATION | Classified Location | 22573 | Classified Project | 2012-07-01 | 2012-07-30 | PAE | 200 | 200 | 2012-08-15 | 2012-09-15 | 2012-08-30 | 2012-08-30 | 100
2013-07-31 | 2013-08-02 | 2011 | NSA | Major Construction | MD | MARYLAND | NSAW | 17866 | North Campus Electrical Utility Plant (NCEUP) | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | 125900 | 125900 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-01-16 | 65 | 50100 | Mountainview | NSA/Colorado | The project was recently awarded. Pending for the Notice to Proceed (NTP).
2013-07-31 | 2013-08-02 | 2011 | NSA | Major Construction | GA | GEORGIA | BackHall Campus/Sweet Tea Annex | 20489 | MOD II | 2011-12-23 | 2012-04-13 | Brantley Co. | 9636 | 10206 | 2012-05-30 | 2013-09-30 | 2014-01-30 | 2013-09-27 | 80
2013-07-31 | 2013-08-02 | 2012 | NSA | Major Construction | GA | GEORGIA | Whitelaw | 23994 | Whitelaw Wedge | 2012-04-26 | 2012-06-18 | JAAAT | 17117 | 17705 | 2012-07-18 | 2014-07-09 | 2014-01-30 | 2014-07-07 | 31
2013-07-31 | 2013-08-02 | 2012 | NSA | Major Construction | CO | COLORADO | ADFC | 23051 | Mountainview | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | 116975 | 120792 | 2012-11-02 | 2015-05-28 | 2015-05-03 | 2015-05-03 | 12
2013-07-31 | 2013-08-02 | 2012 | NSA | Major Construction | MD | MARYLAND | NSAW | 24649 | High Performance Computing Center 2 | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | 564689000 | 565196818 | 2013-03-12 | 2015-09-16 | 2015-09-16 | 2015-09-16 | 3
2013-07-31 | 2013-08-02 | 2013 | NSA | Major Construction | UT | UTAH | Camp Williams | 21078 | Bumblehive / IC CNCI Data Center 1 | 2009-12-18 | 2010-09-24 | Balfour Beatty/DPR/Big-D, A Joint Venture (BDB) | 1201370 | 1090919 | 2010-11-08 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 93 |  |  |  | The Utah Data Center Project is a fully authorized project in the amount of $1,529,500,000.00 which is incrementally funded over the following FY's: FY09- $109,500,000 FY10-$600,000,000 FY11-$397.562,000 FY12-$246,401,000 FY13-$176,037,000 The United States Army Corps of Engineers (USACE) is the construction agent for the NSA. The major contract for the project which is to design and construct the data center was awarded to Balfour Beatty/DPR/Big-D, A Joint Venture (BDB) in the amount of $1,198,950,000. There have been several contracts that have supplemented and supported the main construction effort for the UDC project which include, but are not limited to, the following: - Early Earthwork - $49,422,999 - Substation - $23,269,749 - Military Installation Development Authority (MIDA) - $70,000,000 - USACE Supervision & Administration/Supervision, Inspection & Overhead (S&A/SIOH) - $77,037,086 Note: The exact current obligation amount is $837,927,788 Original Contract Amount: $1,201,369,992
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010154 | Multi Purpose Machine Gun Range | 2009-04-28 | 2009-05-05 | HDH General Contractors, Inc. | 2659015.24 | 1636116.62 | 2009-05-11 | 2011-11-21 | 2011-11-16 | 2011-11-16 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | AK | ALASKA | Bethel | 020123 | Readiness Center | 2009-08-17 | 2009-09-01 | USPFO - AK | 15608000 | 13754358 | 2009-09-18 | 2011-10-20 | 2011-03-18 | 2011-03-18 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closed)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | AZ | ARIZONA | Camp Navajo | 040014 | Readiness Center | 2009-09-01 | 2009-09-18 | Smith Construction Management, LLC | 11658000 | 7992484.42 | 2009-09-25 | 2011-09-19 | 2011-02-21 | 2011-02-21 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | AZ | ARIZONA | Florence | 040170 | Readiness Center | 2009-08-18 | 2009-08-21 | The Benham Companies, LLC | 12231000 | 7534991.58 | 2009-08-28 | 2012-12-10 | 2011-02-07 | 2011-02-07 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closed)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | AZ | ARIZONA | Papago Park | 040226 | Readiness Center | 2009-09-01 | 2009-09-02 | SDVO Constructors, LP | 11603500 | 14115026.93 | 2009-11-02 | 2011-07-01 | 2011-04-01 | 2011-04-01 | 100 | 4540000 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | AR | ARKANSAS | Cabot | 050167 | Readiness Center | 2009-09-14 | 2009-09-14 | Nabholz Construction | 10863000 | 10139505.37 | 2009-11-01 | 2011-04-05 | 2011-04-01 | 2011-04-11 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | CO | COLORADO | Fort Lupton | 080203 | Readiness Center | 2009-08-31 | 2009-09-10 | GH Phipps Construction Companies | 8901000 | 8330742.03 | 2009-09-21 | 2011-05-20 | 2011-03-20 | 2011-03-20 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | CO | COLORADO | Grand Junction | 080204 | Readiness Center | 2010-09-21 | 2010-09-22 | FCI Constructors | 8963000 | 8159279.48 | 2010-10-04 | 2011-09-23 | 2011-09-20 | 2011-09-20 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593 Sent)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | CO | COLORADO | Centennial | 080560 | Mailroom and Plaza Reconfiguration | 2010-06-29 | 2010-09-10 | A&P Contracting | 1277000 | 1307577.85 | 2010-09-20 | 2011-06-13 | 2011-06-01 | 2011-06-01 | 100 | 0 |  |  | Used FY10 funds
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | CT | CONNECTICUT | East Haven | 090044 | KD Range, Add/Alt | 2009-05-25 | 2009-06-08 | Enfield Builders, Inc. | 12673000 | 9837295.07 | 2009-06-15 | 2011-08-01 | 2010-04-05 | 2010-04-05 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | CT | CONNECTICUT | Camp Rell | 090047 | Regional Training Institute | 2009-02-19 | 2009-02-19 | The Fusco Corporation | 27984000 | 27526508 | 2009-05-04 | 2011-11-01 | 2011-09-06 | 2011-09-06 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | DE | DELAWARE | New Castle | 100046 | Army Aviation Support Facility, Add/Alt | 2009-07-06 | 2009-07-15 | Wohlsen Construction Company | 26923000 | 23288221.04 | 2009-08-11 | 2011-06-01 | 2010-12-27 | 2010-12-27 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120164 | Ammunition Supply Point | 2009-09-01 | 2009-09-02 | McCorkle Construction Company | 11472000 | 8344966.26 | 2009-09-16 | 2012-02-24 | 2010-09-20 | 2012-02-24 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120191 | Regional Training Institute, PH 4 | 2009-06-25 | 2009-07-07 | The Tower Group | 20478000 | 18060266.8 | 2009-07-13 | 2011-01-31 | 2010-07-23 | 2011-01-31 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | GA | GEORGIA | Marietta | 130109 | Armed Forces Reserve Center | 2009-09-09 | 2009-09-09 | New South Construction Company, Inc. | 28815000 | 27900485.75 | 2009-09-21 | 2011-11-01 | 2011-04-11 | 2011-04-11 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | ID | IDAHO | Orchard Training Area | 160115 | Live Fire Shoot House | 2009-02-19 | 2009-02-23 | TRS Range Services | 1850000 | 1849611.13 | 2009-05-01 | 2010-04-29 | 2010-02-22 | 2010-02-22 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593 Sent)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | ID | IDAHO | Boise | 160119 | RCOE Operations and Maintenance Building | 2008-11-18 | 2009-03-03 | PSI | 1710000 | 1635000 | 2009-10-26 | 2010-12-13 | 2010-12-06 | 2010-12-06 | 100 | 0
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | IL | ILLINOIS | Urbana | 170614 | Readiness Center | 2009-09-02 | 2009-09-18 | Capital Development Board | 15588000.67 | 13930566.66 | 2010-09-01 | 2012-12-31 | 2011-03-07 | 2013-05-31 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180114 | Multipurpose Machine Gun Range | 2011-09-16 | 2011-09-21 | Bruns-Gutzwiller Inc. | 5786000 | 5357427.6 | 2011-10-03 | 2013-05-01 | 2012-09-21 | 2012-09-21 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Need more funds)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | IN | INDIANA | Lawrence | 180116 | Readiness Center | 2009-05-11 | 2009-05-19 | Shiel Sexton Company, Inc. | 15199999.33 | 15325453.33 | 2009-06-08 | 2011-04-18 | 2010-09-01 | 2010-09-01 | 100 | 3805000 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closed)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | IN | INDIANA | Muscatatuck | 180137 | Combined Arms Collective Training Facility, PH I | 2009-09-22 | 2009-09-23 | DV Contracting, LLC | 5416969.39 | 5416969.39 | 2009-10-05 | 2011-06-07 | 2010-10-25 | 2010-10-25 | 100 | 510000 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | IA | IOWA | Davenport | 190136 | Readiness Center, Add/Alt | 2009-08-04 | 2009-08-06 | Russell Construction Co., Inc. | 1550000 | 1498050.66 | 2009-08-24 | 2010-10-18 | 2010-04-20 | 2010-04-20 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | IA | IOWA | Mount Pleasant | 190146 | Readiness Center, Add/Alt | 2009-09-10 | 2009-09-11 | Woodruff Construction Co. | 1500000 | 1870716 | 2009-09-21 | 2010-11-08 | 2010-12-01 | 2010-12-01 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | IA | IOWA | Camp Dodge | 190150 | MOUT Site, Add/Alt | 2009-09-24 | 2009-09-25 | Pinnacle Construction Group | 1351000 | 820644.01 | 2009-10-03 | 2011-01-18 | 2010-01-18 | 2010-01-18 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | KY | KENTUCKY | London | 210290 | Aviation Operations Facility, PH 3 | 2009-09-18 | 2009-09-18 | D.W. Wilburn | 6844000 | 6822902.03 | 2009-09-26 | 2011-04-27 | 2010-08-14 | 2010-08-14 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | LA | LOUISIANA | Camp Minden | 220154 | Regional Training Institute, PH I | 2009-09-01 | 2009-09-02 | McInnis Brothers Construction, Inc. | 23875000 | 24722216.63 | 2009-09-14 | 2011-05-30 | 2010-05-27 | 2010-05-27 | 100 | 0 |  |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230070 | Regional Training Institute, PH 1 | 2009-04-08 | 2009-04-16 | Nickerson & O'Day, Inc. | 18713000 | 14313529.52 | 2009-04-27 | 2011-06-13 | 2011-06-13 | 2011-06-13 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MD | MARYLAND | Salisbury | 240031 | Readiness Center, Add/Alt | 2010-05-17 | 2010-05-21 | Nason Construction Company, Inc. | 8748000 | 7200870.98 | 2010-06-01 | 2012-09-12 | 2012-03-07 | 2013-05-11 | 98 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MD | MARYLAND | Edgewood | 240189 | Army Aviation Support Facility, Add/Alt | 2009-05-05 | 2009-09-28 | Tetra-Tech Facilities Construction, LLC | 27603000 | 27188439.57 | 2010-03-01 | 2012-06-01 | 2010-09-27 | 2012-06-01 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Methuen | 250106 | Readiness Center, Add/Alt (ADRS) | 2009-06-03 | 2009-06-05 | JK Scanlan Company, Inc. | 14990000 | 11505953 | 2009-08-10 | 2011-04-01 | 2011-11-16 | 2011-11-16 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260180 | Barracks Replacement, PH 1 | 2009-07-31 | 2009-08-06 | Hallmark Construction, Inc. | 16943000 | 17125496.12 | 2009-08-19 | 2011-03-31 | 2011-10-07 | 2011-10-07 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Need more funds)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260210 | Live Fire Shoot House | 2009-08-19 | 2009-09-01 | Graham Construction, Inc. | 1959000 | 1784914.04 | 2009-09-07 | 2010-07-01 | 2010-07-21 | 2010-07-21 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260211 | Urban Assault Course | 2009-08-19 | 2009-09-01 | Beckering Advisor, Inc. | 1437840.8 | 1451840.8 | 2009-09-07 | 2010-09-15 | 2010-06-18 | 2010-06-18 | 100 | 416000 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260212 | Infantry Squad Battle Course | 2009-08-19 | 2009-09-02 | The Garrison Company | 2000000 | 2116999.7 | 2009-09-07 | 2010-06-30 | 2010-05-18 | 2010-05-18 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Need more funds)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270260 | Readiness Center | 2009-08-04 | 2009-08-07 | Holte/Graham, JV | 13390000 | 12528763.58 | 2009-08-10 | 2011-12-01 | 2010-12-14 | 2013-05-31 | 99 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | MO | MISSOURI | Springfield | 290107 | AVCRAD, PH 2 | 2009-08-26 | 2009-09-01 | Walton Construction Company, LLC | 45113000 | 36184365.77 | 2009-09-07 | 2011-07-13 | 2011-05-23 | 2011-05-23 | 99 | 0 |  |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | NV | NEVADA | Elko | 320069 | Readiness Center | 2011-10-27 | 2012-06-01 | Nevada State Public Works | 11246000 | 7749811.72 | 2012-06-11 | 2013-04-30 | 2013-07-12 | 2013-03-27 | 99 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | NV | NEVADA | North NV Military Depot (Carson City) | 320152 | Paint Booth | 2009-06-04 | 2009-09-01 | Nevada State Public Works | 1500000 | 1074962.56 | 2009-09-16 | 2012-05-24 | 2012-05-21 | 2012-05-21 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | NJ | NEW JERSEY | Sea Girt | 340701 | Water System Replacement | 2010-08-16 | 2010-02-18 | Mark Woszcak Mechanical Contractors, Inc. | 1116000 | 1330412 | 2011-01-24 | 2013-06-26 | 2011-05-28 | 2011-05-28 | 100 | 0 |  |  | (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | NY | NEW YORK | Fort Drum | 360191 | Maneuver Area Training and Equipment Site, PH 3 | 2009-09-04 | 2009-09-30 | Beardsley Design Associates | 10876000 | 9544482.83 | 2009-12-01 | 2011-06-15 | 2010-07-26 | 2010-07-26 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | NY | NEW YORK | Queensbury | 360193 | Field Maintenance Shop | 2009-03-19 | 2009-03-23 | BCI Construction Corporation | 5565000 | 4816601.09 | 2009-03-16 | 2010-11-15 | 2010-10-15 | 2010-10-15 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Fargo | 380095 | Readiness Center Unit Storage Building | 2009-01-05 | 2009-09-01 | Roers' Construction Inc. | 1943000 | 1018898.95 | 2009-11-05 | 2010-09-27 | 2010-10-30 | 2010-10-30 | 100 | 0 |  |  | (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | OH | OHIO | Camp Perry | 390257 | Barracks | 2009-07-29 | 2009-08-06 | Studer-Obringer, Inc. | 1907000 | 1645633.64 | 2009-11-02 | 2010-12-27 | 2010-06-01 | 2010-06-01 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | OH | OHIO | Ravenna | 390264 | Barracks | 2009-09-11 | 2009-09-11 | QBS Inc. | 1980000 | 1838000 | 2009-11-01 | 2011-03-03 | 2010-09-01 | 2010-09-01 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | OH | OHIO | Newton Falls | 390270 | Ravenna TTB Utilities | 2009-12-15 | 2010-01-28 | Portage County Water Resources Department | 1600000 | 1600000 | 2011-11-01 | 2012-02-22 | 2012-01-30 | 2012-12-06 | 100 | 0
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | PA | PENNSYLVANIA | Honesdale | 420511 | Readiness Center, Add/Alt | 2011-08-31 | 2011-09-15 | Lobar Incorporated | 6096000 | 5462543.21 | 2011-09-26 | 2013-05-15 | 2012-10-30 | 2013-05-15 | 99 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Need more funds)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | RI | RHODE ISLAND | North Kingstown | 440039 | Army Aviation Support Facility (additional funds for FY08 project) | 2008-12-01 | 2008-12-09 | Bacon Construction Co., Inc. | 4848000 | 4150000 | 2009-02-09 | 2010-06-25 | 2010-02-12 | 2010-02-12 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Eastover | 450115 | Joint Forces Headquarters | 2009-09-24 | 2009-09-24 | Ikhana-Choate | 26398000 | 28331540.06 | 2010-06-01 | 2012-10-23 | 2011-09-28 | 2012-10-23 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Florence | 450185 | Field Maintenance Shop, PH I | 2010-11-01 | 2010-12-09 | FBI Construction, Inc. | 4588000 | 3716588.75 | 2011-05-01 | 2012-03-19 | 2011-12-21 | 2012-03-19 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Anderson | 450218 | Readiness Center | 2009-08-27 | 2009-09-09 | C. Marshall Carithers | 10997000 | 9867298.85 | 2009-09-14 | 2009-09-02 | 2011-04-18 | 2013-09-25 | 90 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Beaufort | 450367 | Readiness Center, Add/Alt | 2009-08-25 | 2009-09-01 | Summerfield Associates, Inc. | 3152000 | 2308193.47 | 2009-11-02 | 2010-05-06 | 2010-09-20 | 2010-09-28 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Rapid City | 460077 | Armed Forces Reserve Center | 2009-03-31 | 2009-04-17 | J Scull Construction | 28762000 | 27821891.07 | 2010-04-05 | 2011-06-24 | 2011-11-14 | 2011-11-14 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 460132 | Barracks/Dining/Admin & Parking Complex, PH I | 2009-06-11 | 2009-06-24 | J Scull Construction | 11645594.24 | 11645594.24 | 2009-08-10 | 2011-03-02 | 2010-12-15 | 2010-12-15 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | TN | TENNESSEE | Tullahoma | 470043 | Readiness Center | 2009-09-16 | 2009-09-25 | Sain Construction Co. | 8787000 | 7706138.13 | 2009-10-01 | 2011-09-15 | 2011-01-21 | 2011-07-05 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Need more funds)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | TX | TEXAS | Laredo | 480195 | Readiness Center, Add/Alt | 2009-11-10 | 2010-04-22 | CG Construction, Inc. | 1165000 | 809473.45 | 2010-06-01 | 2011-12-17 | 2011-07-12 | 2011-07-12 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | UT | UTAH | Camp HG Williams | 490101 | Ammunition Supply Point | 2009-09-17 | 2009-09-18 | Creative Times Inc. | 13843000 | 12044859.22 | 2009-09-21 | 2011-07-30 | 2010-10-01 | 2010-10-01 | 100 | 2358000 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | UT | UTAH | American Fork | 490903 | Readiness Center Structural Upgrade | 2009-08-26 | 2009-09-18 | Interwest Construction Company, Inc. | 1424000 | 676976.64 | 2009-10-05 | 2010-07-30 | 2010-07-30 | 2010-12-26 | 100 | 0
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | UT | UTAH | Price | 490904 | Readiness Center Structural Upgrade | 2009-08-26 | 2009-10-14 | Bud Mahas Construction, Inc. | 2156000 | 757942.09 | 2010-07-15 | 2011-02-01 | 2010-08-31 | 2012-02-09 | 100 | 0 |  |  | (NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | VT | VERMONT | Ethan Allen Firing Range Jericho | 500052 | Readiness Center | 2009-05-12 | 2009-05-15 | E.F. Wall & Associates, Inc. | 9837000 | 8580167 | 2009-06-01 | 2010-09-01 | 2010-09-01 | 2010-09-01 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | VT | VERMONT | Westminister Training Site | 500066 | Westminister Zero Range | 2009-04-17 | 2009-09-24 | Clemons Construction | 1789000 | 1367920 | 2009-09-28 | 2010-08-02 | 2010-08-01 | 2010-08-01 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | VT | VERMONT | Colchester | 500072 | Readiness Center, Add/Alt | 2011-08-09 | 2011-08-11 | Stewart Construction | 1909000 | 1862349 | 2011-09-12 | 2012-04-16 | 2012-06-18 | 2012-06-18 | 100 | 0
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510148 | Multipurpose Machine Gun Range | 2009-09-24 | 2009-09-25 | US Army Corps Engineers, Norfolk District | 2950000 | 3203496.75 | 2009-09-28 | 2011-04-20 | 2010-06-21 | 2010-06-21 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)(NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | VI | VIRGIN ISLANDS | Bethlehem Military Compound Christiansted | 520035 | Construct Main Gate | 2009-02-17 | 2009-09-23 | Barlovento, LLC | 1946000 | 2032865 | 2009-12-01 | 2011-08-28 | 2011-09-15 | 2012-04-23 | 100 | 0 |  |  | (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | VI | VIRGIN ISLANDS | Bethlehem Military Compound Christiansted | 520036 | Restoration LTC Jackson Armory | 2009-04-14 | 2009-09-23 | K-CON Inc. | 2990000 | 2997901.82 | 2009-11-01 | 2011-05-16 | 2010-10-31 | 2011-07-15 | 100 | 0 |  |  | (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | WA | WASHINGTON | Fort Lewis (Gray Field) | 530012 | Readiness Center | 2009-09-11 | 2009-09-11 | Wade Perrow Construction, LLC | 28265000 | 24954481.35 | 2009-09-12 | 2011-07-28 | 2011-01-31 | 2011-01-31 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540006 | Shoot House | 2009-09-23 | 2009-09-23 | Renew Resources, Inc. | 2620000 | 2619564.68 | 2009-10-05 | 2010-09-13 | 2010-08-23 | 2010-08-23 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Formal Reprogramming funds from FY07 project savings ($936,000.00) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Kingwood | 540105 | Joint Interagency Training Education Center, PH I | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | 77180000 | 69339089.15 | 2009-10-01 | 2011-09-30 | 2011-09-28 | 2011-09-28 | 95 | 0 |  |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540205 | Access Control Point | 2009-09-25 | 2009-09-25 | DanHill Construction | 3945000 | 3693718.77 | 2013-05-01 | 2013-12-16 | 2013-12-11 | 2013-12-11 | 5 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Formal Reprogramming $2.358M funds from FY09 project savings {PN: 490101}
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540206 | Multi-Purpose Building, PH II | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | 4755000 | 4308624.78 | 2010-02-01 | 2010-08-30 | 2010-08-26 | 2010-08-26 | 99 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Minor Construction (UMMC) | WV | WEST VIRGINIA | Kenova | 540208 | Tri-State Armory Addition | 2009-04-24 | 2009-09-23 | Neighborgall Construction Company | 2000000 | 2000000 | 2009-10-01 | 2010-08-11 | 2010-07-16 | 2011-05-02 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Major Construction | VA | VIRGINIA | Arlington | 570402 | ARNG Addition, PH II | 2008-09-23 | 2008-11-18 | Tompkins Builders, Inc. | 14513000 | 16459974.37 | 2008-12-01 | 2011-06-30 | 2010-03-15 | 2010-03-15 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010279 | Urban Assault Course | 2010-09-06 | 2010-09-10 | Baggette Construction, Inc. | 2980000 | 2351754 | 2009-12-01 | 2011-10-11 | 2011-08-08 | 2011-08-08 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | AK | ALASKA | Fort Richardson | 020903 | Regional Training Institute, Add/Alt | 2010-05-14 | 2010-09-03 | H. Watt & Scott, Inc. | 1992000 | 1785276 | 2010-09-20 | 2011-10-03 | 2011-09-30 | 2011-09-30 | 100 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | AZ | ARIZONA | Camp Navajo | 040227 | Combat Pistol Qualification Course | 2010-06-14 | 2010-06-15 | Norquay Construction | 2964000 | 1867492.4 | 2010-06-28 | 2011-07-15 | 2010-12-31 | 2010-12-31 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | CA | CALIFORNIA | Los Alamitos | 060115 | Readiness Center, PH 1 | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | 20505000 | 21935468.01 | 2010-11-15 | 2013-10-07 | 2012-02-06 | 2014-04-18 | 37 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | GA | GEORGIA | Fort Benning | 130077 | Readiness Center | 2010-01-28 | 2010-02-04 | USACOE Louisville District | 8400000 | 8622378.6 | 2010-02-22 | 2011-11-15 | 2011-09-14 | 2011-09-14 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | GA | GEORGIA | Hunter AAF | 130112 | Readiness Center | 2010-09-29 | 2010-09-29 | Choice Concrete Construction | 8927000 | 7696026.5 | 2010-10-06 | 2012-05-07 | 2012-03-20 | 2012-03-20 | 95 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | GU | GUAM | Barrigada | 140300 | Readiness Center | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | 20537000 | 20797256 | 2010-05-03 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | ID | IDAHO | Gowen Field | 160120 | Combined Arms Collective Training Facility | 2010-04-27 | 2010-05-25 | Performance Systems Inc. | 7824080 | 7773072.34 | 2010-06-21 | 2012-01-31 | 2011-10-04 | 2011-10-04 | 100 | 6000000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | ID | IDAHO | Orchard Range TS, Boise | 160127 | Fixed Tactical Internet Infrastructure | 2011-07-20 | 2011-09-15 | USPFO - Idaho | 1369000 | 1426280.59 | 2011-10-26 | 2012-08-27 | 2012-08-17 | 2012-08-17 | 100 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | IL | ILLINOIS | Milan | 170611 | Readiness Center, Add/Alt | 2010-09-17 | 2010-09-22 | Capital Development Board | 5560000 | 4319159.15 | 2010-10-18 | 2012-03-31 | 2011-09-14 | 2011-09-14 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | IN | INDIANA | Muscatatuck | 180145 | Combined Arms Collective Training Facility, PH Ib | 2010-04-20 | 2010-04-22 | McKellar Corporation | 10018000 | 7507610.33 | 2010-08-12 | 2011-06-15 | 2010-09-20 | 2010-09-20 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Iowa Falls | 190139 | Readiness Center, Add/Alt | 2010-02-18 | 2010-07-20 | Larson Construction company | 2000000 | 1794105.78 | 2010-08-02 | 2011-10-10 | 2011-08-30 | 2011-08-30 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Davenport | 190151 | Army Aviation Support Facility, Add/Alt | 2010-02-18 | 2010-09-20 | Russell Construction Co., Inc. | 2000000 | 1937949.47 | 2010-09-27 | 2012-01-17 | 2011-11-30 | 2011-11-30 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | IA | IOWA | Johnston (Camp Dodge) | 190154 | FEH Associates, Inc. (USPFO) | 2010-08-10 | 2010-08-16 | SKE International, Inc. | 3999000 | 3981146.73 | 2010-09-06 | 2011-11-08 | 2011-08-15 | 2011-08-15 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Fairfield | 190155 | Field Maintenance Shop, Add/Alt | 2010-02-18 | 2010-09-20 | Jean C. Wiley & Sons, Inc. | 2000000 | 1948912.25 | 2010-10-04 | 2011-10-26 | 2011-09-06 | 2011-09-06 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Camp Dodge | 190157 | Motor Vehicle Storage Buildings, Freedom Center | 2010-02-18 | 2010-07-20 | Septagon Construction Co. | 1963000 | 1267240.25 | 2010-07-29 | 2011-08-04 | 2011-05-01 | 2011-05-01 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | KS | KANSAS | Salina | 200103 | Taxiway Alterations, ARNG AASF | 2010-08-24 | 2010-08-25 | Pavers Inc. | 2219000 | 1988414.86 | 2010-09-01 | 2011-04-29 | 2011-07-18 | 2011-07-18 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | KY | KENTUCKY | Owensboro | 210291 | Readiness Center | 2010-06-07 | 2010-08-16 | A & K Construction Company, Inc. | 10483000 | 9957000 | 2010-06-01 | 2012-04-14 | 2011-08-28 | 2011-08-28 | 100 | 0 |  |  | Programmatic Plus Up PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | KY | KENTUCKY | London | 210292 | Aviation Operations Facility, Add/Alt, PH IV | 2010-09-07 | 2010-09-24 | Septagon Construction Co. | 1805000 | 1682396.41 | 2010-11-08 | 2011-07-05 | 2011-11-25 | 2011-11-25 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | ME | MAINE | Waterville | 230806 | CST Ready Bay Addition | 2011-07-01 | 2011-09-07 | USPFO - Maine | 1927000 | 1121253.73 | 2011-09-25 | 2012-08-20 | 2012-08-13 | 2012-08-13 | 100 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230114 | Regional Training Institute, PH II | 2010-08-11 | 2010-08-16 | Nickerson & O'Day, Inc. | 15464000 | 14434438.6 | 2010-08-23 | 2012-07-01 | 2011-07-01 | 2011-07-01 | 100 | 0 |  |  | Programmatic Plus Up PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Hanscom AFB | 250087 | Armed Forces Reserve Center (JFHQ) | 2010-06-07 | 2010-06-25 | CTA Construction | 27595000 | 25446356.51 | 2010-07-12 | 2012-01-15 | 2011-10-19 | 2011-10-19 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | MI | MICHIGAN | Fort Custer (Augusta) | 260213 | Organizational Maintenance Shop (ADRS) | 2010-08-04 | 2010-09-22 | LD Dosca Associates, Inc. | 7722000 | 7420434.81 | 2010-10-01 | 2012-03-01 | 2011-10-18 | 2011-10-18 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | MI | MICHIGAN | Camp Grayling | 260232 | Dining Facility | 2010-07-09 | 2010-09-24 | Ripman Construction Co., Inc. | 1998000 | 1991296.11 | 2010-10-01 | 2011-06-27 | 2011-09-30 | 2011-12-01 | 100 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270252 | Urban Assault Course | 2011-07-11 | 2011-08-18 | Saginaw Contracting, Inc. | 1693000 | 1193323.74 | 2011-08-22 | 2012-07-18 | 2013-03-18 | 2013-07-18 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270261 | Readiness Center, PH 2 | 2010-08-30 | 2010-09-07 | MAVCON | 3183584 | 2855434.49 | 2010-09-27 | 2012-05-01 | 2011-07-18 | 2013-05-31 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | MN | MINNESOTA | St. Paul | 270263 | CST, Add/Alt | 2011-08-09 | 2011-08-19 | LS Black Constructors | 1954000 | 1888550.04 | 2011-09-12 | 2012-11-20 | 2012-08-24 | 2013-12-20 | 99 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | MS | MISSISSIPPI | Monticello | 280308 | Readiness Center | 2010-09-22 | 2010-09-23 | Mac's Construction Co., Inc. | 8383350 | 8008358 | 2010-11-03 | 2012-06-26 | 2012-01-06 | 2012-01-06 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)/2853 Notification (NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280352 | Combined Arms Collective Training Facility, Add/Alt | 2010-04-09 | 2010-04-22 | B. W. Sullivan Building Contractor, Inc. | 7260000 | 7020324 | 2010-05-17 | 2011-11-20 | 2010-08-23 | 2010-08-23 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification (NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | MO | MISSOURI | Boonville | 290213 | Readiness Center, PH 2 | 2010-04-16 | 2010-04-22 | SIRCAL Contracting | 1775000 | 1011411.5 | 2010-05-01 | 2011-02-17 | 2010-10-18 | 2010-10-18 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | MT | MONTANA | Fort Harrison | 300202 | Troop Medical Clinic, Add/Alt | 2010-04-23 | 2010-09-13 | R&R Taylor Construction | 1750000 | 1657794.99 | 2010-10-13 | 2011-09-01 | 2011-06-30 | 2011-06-30 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | NE | NEBRASKA | Lincoln | 310076 | Armed Forces Reserve Center (JFHQ) | 2010-01-26 | 2010-02-16 | Hausman Construction, Inc. | 22962000 | 21804833.39 | 2010-04-01 | 2012-07-17 | 2011-09-30 | 2011-09-30 | 98 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | NE | NEBRASKA | Mead Training Site | 310122 | Water Supply & Distribution System | 2010-08-23 | 2010-08-25 | Rutjens Construction, Inc. | 1995000 | 1842956.65 | 2010-08-25 | 2011-07-15 | 2011-07-25 | 2011-07-25 | 100 | 0 |  |  | Programmatic Plus Up PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | NV | NEVADA | North Las Vegas | 320143 | Readiness Center | 2010-09-27 | 2010-09-27 | The Penta Building Group | 25807000 | 19910357.28 | 2010-10-25 | 2013-05-01 | 2012-01-23 | 2013-04-19 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | NV | NEVADA | Carson City | 320197 | Renewable Energy Sustainable Projects | 2010-09-21 | 2010-09-24 | RHP Mechanical Systems (Contractor) | 1997000 | 1917039 | 2010-10-04 | 2011-10-26 | 2011-04-04 | 2011-04-04 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | NM | NEW MEXICO | Santa Fe | 350043 | Army Aviation Support Facility | 2010-06-29 | 2010-07-02 | US Army Corps of Engineers | 35577000 | 31834806.4 | 2010-09-13 | 2012-03-20 | 2011-09-14 | 2011-09-14 | 100 | 3300000 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | NC | NORTH CAROLINA | East Flat Rock | 370896 | Readiness Center, Add/Alt | 2010-09-07 | 2010-09-10 | Architectural Design Studio | 2501000 | 2033369.25 | 2010-09-27 | 2011-10-13 | 2011-09-30 | 2011-10-17 | 99 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 370897 | Tactical UAS Support Facility | 2010-09-10 | 2010-09-27 | J.M. Thompson Co | 2459000 | 2736112.8 | 2010-10-09 | 2012-03-02 | 2012-06-08 | 2011-08-15 | 95 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)/2853 Notification ($2,589,623.00)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Bismarck | 380118 | Raymond J. Bohn Readiness Center, Addition | 2010-04-01 | 2010-09-28 | Associated Builders, Inc. | 2000000 | 1198567.21 | 2010-10-20 | 2012-01-23 | 2011-12-31 | 2011-12-31 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | ND | NORTH DAKOTA | Camp Grafton | 380119 | Shoreline Stabilization | 2010-02-12 | 2010-03-01 | Ames Construction | 1992000 | 1747147.76 | 2010-03-15 | 2010-08-17 | 2011-08-30 | 2011-08-30 | 100 | 0 |  |  | Programmatic Plus Up PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Camp Grafton, Devils Lake | 380120 | Dike Construction | 2010-07-26 | 2010-09-03 | Ames Construction | 1569000 | 1943779.7 | 2010-11-01 | 2012-08-13 | 2012-08-20 | 2012-08-20 | 100 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | OH | OHIO | Beightler | 390261 | Joint Forces Headquarters (JOC), Addition | 2010-02-03 | 2010-08-05 | Elford, Inc. | 2000000 | 1839130.8 | 2010-09-01 | 2011-08-01 | 2011-07-18 | 2011-07-18 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | OH | OHIO | Ravenna | 390267 | Shoot House | 2009-12-14 | 2010-09-20 | USPFO - Ohio | 2000000 | 1946920.12 | 2010-10-01 | 2011-11-16 | 2011-10-25 | 2011-10-25 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | OR | OREGON | Polk County | 410120 | Readiness Center | 2010-09-14 | 2010-09-21 | Lease Crutcher Lewis | 12093000 | 11892715.57 | 2010-10-08 | 2012-09-01 | 2012-12-01 | 2012-12-01 | 95 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | OR | OREGON | Clastop County (Warrenton) (Camp Rilea) | 410820 | Water Supply Company | 2010-09-10 | 2010-09-21 | Hoffman Construction Company | 3369000 | 3367999.48 | 2010-10-01 | 2011-08-01 | 2011-10-02 | 2011-10-02 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | PA | PENNSYLVANIA | Fort Indiantown Gap | 420507 | CSMS Paint Stripping & Prep Shop | 2010-06-01 | 2010-08-27 | Arthur Funk & Sons, Inc. | 1998000 | 1587766.47 | 2010-10-01 | 2011-07-27 | 2011-06-22 | 2011-10-31 | 100 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | PRI | PUERTO RICO | Camp Santiago | 436019 | Urban Assault Course | 2009-12-01 | 2010-09-29 | Remex Co. | 1669000 | 1845996.46 | 2010-10-01 | 2011-10-03 | 2011-09-23 | 2011-09-23 | 100 | 0 |  |  | Congressionally Directed
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Eastover | 450252 | Army Aviation Support Facility, Add/Alt | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. | 14758680 | 14078418 | 2011-02-07 | 2013-04-15 | 2011-12-14 | 2013-05-01 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Greenville | 450353 | Army Aviation Support Facility | 2010-09-23 | 2010-09-24 | Hendrick Construction | 27935984 | 27303538 | 2010-11-17 | 2013-06-21 | 2012-08-10 | 2013-06-21 | 75 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 460141 | Joint Force HQ Readiness Center Supplemental | 2010-08-26 | 2010-09-03 | J. Scull Construction Services, Inc. | 5705000 | 5270893.64 | 2010-09-27 | 2012-04-14 | 2012-04-14 | 2012-04-14 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 461536 | Troop Medical Clinic, Add/Alt | 2010-09-01 | 2010-09-07 | J. Scull Construction Services, Inc. | 1949000 | 1723490.87 | 2010-09-20 | 2011-05-23 | 2011-05-01 | 2011-05-01 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | TX | TEXAS | Austin-Bergstrom Airport | 480175 | Armed Forces Reserve Center | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | 16441000 | 13991459.3 | 2011-01-01 | 2012-07-17 | 2012-06-15 | 2012-06-15 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | TX | TEXAS | Austin-Bergstrom Airport | 480176 | Field Maintenance Shop, Joint | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | 5700000 | 6931779.58 | 2011-01-01 | 2012-07-17 | 2012-06-15 | 2012-06-15 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | VT | VERMONT | Ethan Allen Firing Range | 500071 | Bachelor Officer Quarters additions and improvement | 2010-09-14 | 2010-09-20 | Summit/Catamount Construction | 1996000 | 2163343.29 | 2010-09-27 | 2011-06-30 | 2011-08-15 | 2011-08-15 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510302 | Regional Training Institute, PH 2 | 2010-01-27 | 2010-02-26 | Barton Marlow Company | 31946000 | 30249051.23 | 2010-07-01 | 2012-01-06 | 2012-09-10 | 2012-09-10 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (Completed - no NGB 593)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | VI | VIRGIN ISLANDS | St. Croix | 520014 | Regional Training Institute, PH 1 | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. | 19978000 | 19493319.3 | 2010-07-01 | 2013-02-15 | 2012-02-20 | 2013-04-23 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Minor Construction (UMMC) | WA | WASHINGTON | Camp Murray | 530033 | Entrance Gate w/Access Control Buildings | 2011-09-15 | 2011-09-19 | Berschauer Construction | 2994000 | 2994000 | 2011-10-03 | 2012-10-02 | 2012-09-17 | 2012-09-17 | 100 | 0
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Major Construction | WV | WEST VIRGINIA | St. Albans | 540217 | Readiness Center Addition/Life Safety Upgrades | 2010-09-24 | 2010-09-26 | Hayslett Construction Company | 1973000 | 1135206.62 | 2010-10-01 | 2011-10-21 | 2011-09-18 | 2011-09-18 | 100 | 0 |  |  | Congressional Add PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | AZ | ARIZONA | Florence | 040023 | Readiness Center | 2011-08-01 | 2011-09-01 | Haydon Building Corporation-Tem | 16467000 | 16296966.98 | 2011-09-19 | 2012-12-10 | 2012-12-14 | 2012-12-14 | 90 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | AR | ARKANSAS | Camp Robinson | 050043 | Combined Support Maintenance Shop | 2011-06-24 | 2011-07-01 | CDI Contractors, LLC | 29940000 | 28273500 | 2011-11-01 | 2013-08-01 | 2013-07-01 | 2013-07-01 | 80 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | AR | ARKANSAS | Fort Chaffee | 050163 | Combined Arms Collective Training Facility | 2010-12-21 | 2011-05-23 | Crossland Construction Company, Inc. | 8857560 | 7412601 | 2011-09-19 | 2013-01-22 | 2012-03-23 | 2013-06-01 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | AR | ARKANSAS | Fort Chaffee | 050173 | Live Fire Shoot House | 2011-05-26 | 2011-06-14 | Ross Sparks Builders, Inc. | 2495000 | 2266871.38 | 2011-07-01 | 2012-09-18 | 2012-06-07 | 2013-06-01 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060429 | Combined Arms Collective Training Facility | 2011-05-12 | 2011-09-20 | Cox Construction Company | 12379000 | 11525157.7 | 2011-12-05 | 2013-06-15 | 2012-06-29 | 2013-09-27 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Gypsum/Eagle | 080062 | HAATS/AASF | 2011-05-19 | 2011-07-13 | Hensel Phelps Construction Company | 38922000 | 37424862.05 | 2011-11-01 | 2013-04-01 | 2013-03-31 | 2013-03-31 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Fort Carson | 080067 | Regional Training Institute | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC | 49220000 | 42646881 | 2011-10-01 | 2013-10-01 | 2013-10-18 | 2013-10-18 | 90 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011). Informal Reprogramming $2.293M Formal Reprogramming $9.3M funds from FY10 project savings {PNs: 160120, ($6M) & 350043 ($3.3M)}
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Colorado Springs | 080201 | Readiness Center | 2011-08-12 | 2011-09-16 | Pahl Architecture | 19960000 | 18555455.87 | 2011-12-01 | 2013-10-01 | 2013-09-30 | 2013-09-30 | 22 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Windsor | 080202 | Readiness Center | 2011-08-05 | 2011-08-16 | AP Mountain States | 7485000 | 7468555.7 | 2011-12-01 | 2012-11-01 | 2012-10-19 | 2012-10-19 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) Final closeout in progress
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | CT | CONNECTICUT | Windsor Locks | 090010 | Readiness Center (Aviation) | 2011-05-27 | 2011-09-22 | USPFO - CT | 40918000 | 31679225 | 2011-10-01 | 2013-11-05 | 2013-10-19 | 2013-10-19 | 77 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | DE | DELAWARE | New Castle | 100037 | Armed Forces Reserve Center (JFHQ) | 2011-08-03 | 2011-08-18 | Vigil Contracting, Inc. | 26946000 | 25288071.37 | 2011-12-01 | 2013-08-12 | 2013-07-10 | 2013-07-10 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | GA | GEORGIA | Dobbins | 130123 | Readiness Center, Add/Alt | 2011-05-17 | 2012-04-17 | TEPA | 10379000 | 9927343.13 | 2012-01-01 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 10 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | GA | GEORGIA | Cumming | 130127 | Readiness Center | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 16966000 | 16395970.11 | 2011-12-01 | 2013-05-15 | 2012-11-16 | 2012-11-16 | 85 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | GU | GUAM | Barrigada | 140001 | Combined Support Maintenance Shop, Ph 1 | 2011-05-31 | 2011-09-01 | NAVFAC Pacific | 18962000 | 19150383.04 | 2011-09-12 | 2013-04-19 | 2012-04-20 | 2012-04-20 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | HI | HAWAII | Kalaeloa | 150077 | Combined Support Maintenance Shop, Ph 2A | 2011-08-11 | 2011-12-29 | BCP Construction of Hawaii, Inc. | 37924000 | 36867811.2 | 2012-02-01 | 2013-09-02 | 2013-08-18 | 2013-08-18 | 56 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | ID | IDAHO | Gowen Field | 160093 | Barracks (ORTC), Ph 1 | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | 12969000 | 13681983.19 | 2011-08-27 | 2013-03-16 | 2013-02-28 | 2013-02-28 | 45 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | ID | IDAHO | Mountain Home | 160122 | Tactical Unmanned Aircraft System Facility | 2011-05-23 | 2011-08-02 | Construction Inc, Moutain Home | 6287000 | 5501880.29 | 2011-09-13 | 2013-07-10 | 2013-10-22 | 2013-10-22 | 75 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | IL | ILLINOIS | Springfield | 179237 | Combined Support Maintenance Shop, Add/Alt | 2011-09-15 | 2011-09-20 | CORE Construction | 14970000 | 14447600 | 2011-10-24 | 2013-07-17 | 2012-10-05 | 2013-10-05 | 60 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | KS | KANSAS | Wichita East | 200063 | Readiness Center | 2011-07-15 | 2011-08-11 | Straub Construction Co., Inc. | 26283000 | 24235376.19 | 2011-09-23 | 2013-07-01 | 2012-12-07 | 2013-07-15 | 90 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | KS | KANSAS | Wichita | 200090 | Field Maintenance Shop | 2011-09-01 | 2011-09-28 | The Law Company, Inc. | 13243800 | 12144967.58 | 2011-11-18 | 2014-04-15 | 2012-10-19 | 2014-04-15 | 28 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | KY | KENTUCKY | Burlington | 210034 | Readiness Center | 2011-08-31 | 2011-09-16 | D.W. Wilburn | 19461000 | 18743440.2 | 2011-11-09 | 2013-01-30 | 2013-03-01 | 2013-01-30 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | LA | LOUISIANA | Minden | 220114 | Readiness Center | 2011-06-23 | 2011-08-08 | Walton Construction Co., LLC. | 19307752 | 22351050.43 | 2011-08-29 | 2013-09-03 | 2013-01-14 | 2013-08-29 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | LA | LOUISIANA | Fort Polk | 220222 | Tactical Unmanned Aircraft System Facility | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company | 5489000 | 5010566.27 | 2011-09-12 | 2012-12-11 | 2012-07-30 | 2013-06-18 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | MD | MARYLAND | Webster Field, St Inigoes | 240186 | Tactical Unmanned Aircraft System Facility | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | 5489000 | 5219755 | 2011-09-23 | 2013-09-16 | 2013-06-15 | 2013-08-15 | 65 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Hanscom AFB | 250136 | Armed Forces Reserve Center (JFHQ), Ph 2 | 2011-09-15 | 2011-09-22 | Nauset Construction Corp | 22954000 | 21486083.07 | 2011-10-17 | 2012-11-17 | 2012-10-27 | 2012-10-27 | 85 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260207 | Combined Arms Collective Training Facility | 2011-06-22 | 2011-08-18 | Saylor Construction LLC | 18962000 | 13822986.89 | 2011-09-20 | 2012-03-09 | 2012-03-09 | 2012-04-15 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270096 | Infantry Squad Battle Course | 2011-06-28 | 2011-07-01 | Eagle Construction Company, Inc. | 4291000 | 2231974.6 | 2011-11-01 | 2013-02-15 | 2012-07-06 | 2013-02-15 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (Closed)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270202 | Field Maintenance Shop | 2011-07-19 | 2011-08-08 | Stahl Construction Company | 28942000 | 26312226.88 | 2012-05-08 | 2013-05-03 | 2013-01-18 | 2014-04-18 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 1121-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270267 | Tactical Unmanned Aircraft System Facility | 2011-07-21 | 2011-08-08 | Donlar Construction Company | 4441000 | 3548418 | 2012-04-03 | 2012-12-13 | 2012-10-27 | 2013-07-30 | 90 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | NE | NEBRASKA | Mead | 310107 | Readiness Center | 2011-06-15 | 2011-07-12 | The Weitz Company, LLC | 11377000 | 11147590 | 2012-05-07 | 2013-05-06 | 2012-08-08 | 2013-04-01 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | NE | NEBRASKA | Lincoln | 310110 | Readiness Center, Add/Alt | 2011-08-16 | 2011-08-19 | Kingery Construction Company | 3293000 | 3306605.59 | 2011-10-01 | 2013-05-06 | 2012-11-06 | 2013-04-02 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | NH | NEW HAMPSHIRE | Pembroke | 330034 | Classroom Facility (Regional Training Institute) | 2011-05-09 | 2011-08-25 | TLT Construction Corp. | 20958000 | 14113265.69 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2013-09-20 | 15 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | NH | NEW HAMPSHIRE | Pembroke | 330035 | Barracks Facility (Regional Training Institute) | 2011-05-09 | 2011-08-26 | TLT Construction Corp | 14970000 | 12098806.21 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2013-09-20 | 15 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | NM | NEW MEXICO | Farmington | 350075 | Readiness Center, Add/Alt | 2011-04-19 | 2011-09-29 | Jaynes Corporation | 8483000 | 10306121.78 | 2011-12-05 | 2012-12-25 | 2012-10-31 | 2012-10-31 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | NC | NORTH CAROLINA | High Point | 370898 | Readiness Center, Add/Alt | 2011-09-08 | 2011-09-15 | Holden Building Company, Inc. | 1548672 | 1590022.94 | 2011-11-05 | 2012-08-01 | 2012-10-26 | 2012-10-26 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | ND | NORTH DAKOTA | Camp Grafton | 380014 | Readiness Center, Add/Alt | 2011-06-15 | 2011-07-19 | Comstock Construction, Inc. | 11178000 | 11742926.68 | 2011-08-08 | 2012-08-04 | 2012-07-15 | 2012-07-15 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Camp Grafton, Devils Lake | 380121 | Levee Pump Station | 2011-09-22 | 2011-10-11 | Swanberg Construction, Inc. | 1695000 | 1928576.85 | 2011-10-24 | 2013-01-12 | 2012-12-15 | 2012-12-15 | 60 | 0 |  |  | Used FY11 funds
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | PRI | PUERTO RICO | Camp Santiago | 436023 | Live Fire Shoot House | 2011-07-21 | 2011-09-22 | Remex Co. | 3094000 | 2562384.37 | 2011-11-07 | 2012-09-18 | 2012-12-14 | 2012-12-14 | 65 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | RI | RHODE ISLAND | East Greenwich | 440009 | United States Property and Fiscal Office | 2011-08-25 | 2011-09-30 | USPFO - RI, Purchasing & Contracting | 26946000 | 21152997 | 2011-10-21 | 2012-10-29 | 2012-10-24 | 2012-10-24 | 85 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Watertown | 460085 | Readiness Center | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. | 18225100 | 17608092.27 | 2011-11-07 | 2013-03-01 | 2013-01-14 | 2013-01-14 | 55 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | TX | TEXAS | Camp Maxey | 480267 | Combat Pistol/Military Pistol Qualification Course | 2011-04-06 | 2011-09-12 | Unified Services of Texas, Inc. | 2495000 | 1962098.14 | 2011-09-26 | 2012-09-28 | 2012-03-31 | 2012-03-31 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | TX | TEXAS | Camp Swift | 480290 | Urban Assault Course | 2011-08-25 | 2011-09-12 | Gaeke Construction Co., Inc. | 2595000 | 2172467.8 | 2011-11-01 | 2012-09-27 | 2012-08-20 | 2012-08-20 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | VI | VIRGIN ISLANDS | St. Croix | 520034 | Readiness Center (JFHQ) | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | 24950000 | 21792220.75 | 2011-11-01 | 2013-11-25 | 2013-11-01 | 2013-11-20 | 62 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | WA | WASHINGTON | Tacoma | 530022 | Combined Support Maintenance Shop | 2011-06-07 | 2011-06-23 | Walsh Construction Co, II, LLC | 24950000 | 22951981.14 | 2011-08-22 | 2013-12-12 | 2012-11-03 | 2012-11-03 | 75 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Morgantown | 540068 | Readiness Center | 2011-09-21 | 2011-09-22 | Massaro Corporation | 20958000 | 18998651.85 | 2011-11-14 | 2013-04-09 | 2013-03-26 | 2013-03-26 | 75 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Moorefield | 540084 | Readiness Center | 2011-06-01 | 2011-09-21 | Langan General Contracting Corp | 14172000 | 13565717.86 | 2011-10-08 | 2013-04-22 | 2013-03-24 | 2013-03-24 | 75 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | WI | WISCONSIN | Madison | 550139 | Aircraft Parking | 2011-08-16 | 2011-09-15 | Buteyn Peterson Construction Co. | 5689000 | 5781635 | 2011-11-01 | 2012-10-09 | 2012-10-29 | 2012-10-17 | 94 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Major Construction | WY | WYOMING | Laramie | 560116 | Field Maintenance Shop | 2011-07-28 | 2011-08-16 | Health Construction | 14371000 | 11195625.88 | 2011-09-12 | 2013-05-25 | 2013-06-30 | 2013-06-30 | 66 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | AL | ALABAMA | Talladega | 011006 | Readiness Center, Add/Alt | 2012-09-13 | 2012-09-21 | Metro D. Constructions, LLC. | 2000000 | 1905143.78 | 2012-11-18 | 2013-10-01 | 2013-09-16 | 2013-09-16 | 10 | 0 |  |  | Used FY12 funds
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010263 | Readiness Center Ph2 | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. | 16444000 | 14296735 | 2012-09-14 | 2013-12-24 | 2013-12-10 | 2013-12-10 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | AZ | ARIZONA | Papago Military Reservation | 040294 | Readiness Center | 2012-02-15 | 2012-08-16 | Haydon Building Corporation - Tem | 17771000 | 17251101.63 | 2012-09-12 | 2013-11-04 | 2013-10-16 | 2013-10-16 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | AR | ARKANSAS | Fort Chafee | 050172 | Convoy Live Fire/Entry Control Point Range | 2012-02-14 | 2012-08-16 | SAIC | 3500000 | 3559384.39 | 2012-11-07 | 2013-12-02 | 2013-10-28 | 2013-10-28 | 15 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060009 | Utilities Replacement Ph1 | 2012-07-09 | 2012-08-01 | Cox Construction Co. | 31300000 | 22595510.2 | 2012-12-01 | 2015-03-01 | 2015-03-01 | 2015-03-01 | 41 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp San Luis Obispo | 060170 | Field Maintenance Shop | 2012-06-19 | 2012-06-26 | Goshawk LLC | 7985000 | 7392265.69 | 2012-11-08 | 2013-10-20 | 2013-10-14 | 2013-09-22 | 30 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | CA | CALIFORNIA | Los Alamitos | 060432 | Barracks | 2012-06-27 | 2012-09-28 | WEP Enterprises | 1400000 | 867723.5 | 2012-10-15 | 2003-10-07 | 2013-09-20 | 2013-09-20 | 10 | 0 |  |  | FY07 Congressionally Directed, Used FY10 funds
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060438 | Tactical Unmanned Aircraft System Facility | 2012-06-04 | 2012-07-20 | USPFO Contracting California | 4834795.71 | 4873634.94 | 2012-08-06 | 2013-11-11 | 2013-10-28 | 2013-10-28 | 50 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Fort Carson | 080093 | Barracks Complex (ORTC) | 2012-08-30 | 2012-09-04 | Jacob's | 42228000 | 42922514.45 | 2012-09-24 | 2013-12-02 | 2013-10-28 | 2013-10-28 | 18 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Alamosa | 080126 | Readiness Center | 2012-06-12 | 2012-06-22 | FCI Constructors, Inc. | 6397000 | 6276185.07 | 2012-09-10 | 2013-12-02 | 2013-10-14 | 2013-10-14 | 85 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Aurora | 080206 | Tactical Unmanned Aircraft System Facility | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. | 3592000 | 3858949.17 | 2012-11-05 | 2013-12-02 | 2013-10-28 | 2013-10-28 | 38 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | DC | DISTRICT OF COLUMBIA | Anacostia | 110007 | US Property & Fiscal Office Add/Alt | 2012-08-21 | 2012-08-28 | Allen & Shariff Corporation | 5300000 | 4722825 | 2013-03-01 | 2013-12-30 | 2013-12-13 | 2013-12-13 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120188 | Convoy Live Fire/Entry Control Point Range | 2012-07-31 | 2012-08-16 | Breaking Ground Constracting Co. | 2400000 | 2918900 | 2013-02-13 | 2013-12-16 | 2013-12-02 | 2013-12-02 | 11 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120193 | Live Fire Shoot House | 2012-04-10 | 2012-04-27 | STG Contracting Group | 3099000 | 2556008.99 | 2012-05-21 | 2013-03-01 | 2013-10-28 | 2013-10-28 | 98 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | FL | FLORIDA | Camp Blanding, Starke | 120277 | Unit Storage Building (TUAS) | 2012-08-30 | 2012-09-14 | C. Young Construction | 821000 | 821000 | 2013-04-13 | 2013-10-19 | 2013-09-12 | 2013-09-12 | 20 | 0
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Hinesville | 130063 | Maneuver Area Training & Equipment Site Ph1 | 2012-01-12 | 2012-09-11 | USPFO - GA | 16924000 | 19461776.76 | 2012-10-19 | 2013-11-18 | 2013-10-28 | 2013-10-28 | 22 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Macon | 130068 | Readiness Center Ph 1 | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC | 14471000 | 13867572.9 | 2012-09-14 | 2014-04-12 | 2014-03-15 | 2014-03-15 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Atlanta | 130120 | Readiness Center | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. | 10991000 | 11164225.91 | 2012-09-10 | 2013-11-18 | 2013-10-28 | 2013-10-28 | 20 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | HI | HAWAII | Kalaeloa | 150043 | Readiness Center Ph 1 | 2012-02-15 | 2012-07-11 | Dawson Technical, LLC | 32024000 | 32208735.52 | 2012-07-23 | 2014-08-11 | 2014-07-23 | 2014-07-23 | 12 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | IL | ILLINOIS | Normal | 170801 | Readiness Center | 2012-09-13 | 2012-09-13 | River City Construction | 10000000 | 10445180.89 | 2012-11-05 | 2014-05-31 | 2014-10-28 | 2014-10-28 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | IL | ILLINOIS | Sparta | 171005 | Battalion Maintenance Shelter | 2012-09-24 | 2012-09-24 | H&N Construction | 1210000 | 996756.79 | 2012-10-01 | 2013-06-30 | 2013-10-31 | 2013-10-31 | 20 | 0
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Indianapolis | 180012 | JFHQ Add/Alt | 2012-09-19 | 2012-09-19 | F.A. WILHELM Construction., Inc. | 34971000 | 33179910 | 2012-11-15 | 2014-05-04 | 2013-10-28 | 2013-10-28 | 30 | 0 |  |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2M FY09 project {PN: 040226} & Formal Reprogramming $7.271M funds from FY09 project savings {PNs: 040226 ($2.540M), 180116 (3.805M), 180137 (510K) & 260211 (416K)}
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180142 | Railhead Expansion & Container Facility | 2012-09-11 | 2012-09-12 | Milestone Contractors, L.P. | 20939000 | 19068700 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 4 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180156 | Deployment Processing Facility | 2012-09-11 | 2012-09-12 | Milestone Contractors, L.P. | 8878000 | 8214000 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180160 | Operations Readiness Training Complex 1 | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | 24991000 | 26136137 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 19 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180161 | Operations Readiness Training Cmplx 2 | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | 27000000 | 27520300 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 15 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | LA | LOUISIANA | Camp Minden | 220233 | Waste Water Treatment Facility | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. | 2972000 | 2847329 | 2012-06-01 | 2013-07-15 | 2013-06-17 | 2013-06-17 | 46 | 0
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230046 | Readiness Center | 2012-08-28 | 2012-08-28 | ITSI Gibane | 15584000 | 14690109 | 2012-09-17 | 2013-11-15 | 2013-10-21 | 2013-10-21 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | ME | MAINE | Brunswick | 230071 | Armed Forces Reserve Center | 2012-06-06 | 2012-06-14 | Nickerson & O'Day, Inc. | 23866635.14 | 23867079.14 | 2012-08-06 | 2013-11-15 | 2013-10-21 | 2013-10-21 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | Dundalk | 240017 | Readiness Center Add/Alt | 2012-08-29 | 2012-09-11 | The Whiting Turner Contracting Company | 15834000 | 10855825.5 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2014-10-22 | 12 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | Westminster | 240187 | Readiness Center Add/Alt | 2012-07-23 | 2012-09-11 | Harkins Builders | 10296000 | 7179656.32 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2014-10-22 | 12 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | La Plata | 240193 | Readiness Center | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 9000000 | 9364656.32 | 2012-10-01 | 2013-10-06 | 2014-09-22 | 2014-10-22 | 12 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Natick | 250135 | Readiness Center | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc | 9324695 | 8564265 | 2012-12-01 | 2013-11-18 | 2013-10-28 | 2013-10-28 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | MA | MASSACHUSETTS | Camp Edwards | 250178 | J-1 Range North Pump and Treat Facility | 2012-10-25 | 2012-11-15 | Tetra Tech/Mead & Hunt JV | 2972000 | 2394000 | 2013-03-04 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 12 | 0 |  |  | Used FY13 funds
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270266 | Multipurpose Machine Gun Range | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. | 4718468 | 4467178.97 | 2012-09-17 | 2014-01-18 | 2013-12-15 | 2013-12-15 | 50 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280315 | Troop Housing (ORTC) Ph1 | 2012-01-12 | 2012-06-22 | DCD-YATES | 20709500 | 20003954.24 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2013-10-21 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280387 | Deployment Processing Facility | 2012-05-31 | 2012-07-11 | Hanco Corporation | 9222260 | 8803310 | 2012-12-01 | 2013-11-15 | 2013-10-16 | 2013-10-16 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280389 | Operations Readiness Training Cmplx Ph1 | 2012-01-12 | 2012-06-22 | DCD-YATES | 24411040 | 23526448.76 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2013-10-21 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | NE | NEBRASKA | Grand Island | 310085 | Readiness Center | 2012-05-29 | 2012-06-05 | Sampson Construction Company, Inc. | 21913000 | 18612852 | 2012-07-01 | 2013-12-13 | 2013-11-22 | 2013-12-13 | 60 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | NE | NEBRASKA | Mead | 310086 | Readiness Center | 2012-04-09 | 2012-04-27 | Boyd Jones Construction | 9099000 | 9814471.09 | 2012-05-01 | 2013-09-09 | 2013-06-27 | 2013-08-26 | 40 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | NE | NEBRASKA | Ashland | 310142 | CATS Waste Water Treatment Facility | 2012-06-28 | 2012-08-10 | All Purpose Construction | 1536000 | 1597486 | 2012-09-01 | 2013-10-11 | 2013-09-19 | 2013-09-26 | 41 | 0
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | NV | NEVADA | Las Vegas | 320070 | Field Maintenance Shop | 2012-01-12 | 2012-04-17 | CORE Construction | 22932000 | 21144971.94 | 2012-12-01 | 2013-11-08 | 2013-10-25 | 2013-10-25 | 80 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Minor Construction (UMMC) | NH | NEW HAMPSHIRE | Milford | 330052 | Readiness Center, Add/Alt | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 1947000 | 1926060.5 | 2013-10-07 | 2013-07-29 | 2013-08-13 | 2013-08-13 | 95 | 0
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | NJ | NEW JERSEY | Lakehurst | 340115 | Army Aviation Support Facility | 2012-06-07 | 2012-08-15 | Senate Builders & Construction Managers | 48858000 | 44606211.99 | 2012-12-01 | 2014-10-06 | 2014-09-30 | 2014-09-30 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | NM | NEW MEXICO | Santa Fe | 350115 | Readiness Center Add/Alt | 2012-01-03 | 2012-04-10 | Jaynes Corporation | 5172000 | 4439818.96 | 2012-12-01 | 2013-07-13 | 2013-06-01 | 2013-06-01 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | NC | NORTH CAROLINA | Greensboro | 370899 | Readiness Center Add/Alt | 2012-09-04 | 2012-09-04 | Holden Building Company, Inc. | 3689000 | 3370848.51 | 2012-12-01 | 2013-11-04 | 2013-10-28 | 2013-10-28 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | OK | OKLAHOMA | Camp Gruber | 400605 | Upgrade-Combined Arms Collective Training Fac | 2012-01-12 | 2012-08-16 | PentaCon, LLC | 10343000 | 9024107.16 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-02-19 | 22 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | OK | OKLAHOMA | Camp Gruber | 400606 | Live Fire Shoot House | 2012-01-24 | 2012-08-15 | PentaCon, LLC | 2995000 | 3073646.94 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-02-19 | 2 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | OR | OREGON | The Dalles | 410026 | Readiness Center | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 13800000 | 13189960 | 2012-12-01 | 2014-02-07 | 2013-12-28 | 2013-12-28 | 4 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | PRI | PUERTO RICO | Fort Buchanan | 430010 | Readiness Center | 2012-09-10 | 2012-09-18 | RB Construction Group Inc | 40565271.7 | 37822839.46 | 2012-12-01 | 2014-12-05 | 2013-10-28 | 2013-11-05 | 17 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Allendale | 450403 | Readiness Center Add/Alt | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. | 4290000 | 4096864 | 2012-10-01 | 2013-09-01 | 2013-10-28 | 2013-10-28 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | UT | UTAH | Camp Williams | 490618 | Multi Purpose Machine Gun Range | 2012-09-06 | 2012-09-27 | USPFO - UT | 6498000 | 6576914.72 | 2012-12-01 | 2014-01-06 | 2013-10-28 | 2013-10-28 | 66 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510307 | Combined Arms Collective Training Facility | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | 10364000 | 8780509.99 | 2013-04-01 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 4 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Buckhannon | 540085 | Readiness Center Ph1 | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | 9991000 | 11442216.32 | 2012-11-01 | 2014-08-25 | 2014-11-12 | 2014-08-06 | 6 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | WI | WISCONSIN | Camp Williams | 550245 | Tactical Unmanned Aircraft System Facility | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. | 4149560 | 4014697.6 | 2012-07-01 | 2013-10-20 | 2013-05-20 | 2013-07-20 | 40 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Major Construction | WY | WYOMING | Cheyenne | 560702 | Readiness Center | 2012-04-27 | 2012-04-18 | Hensel Phelps | 8898000 | 10341796 | 2012-12-01 | 2013-11-18 | 2013-10-28 | 2013-10-28 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | AR | ARKANSAS | Searcy | 050139 | Field Maintenance Shop | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC I | 6577000 | 4966584 | 2013-08-30 | 2014-10-27 | 2014-10-01 | 2014-10-01 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) Used FY09 funds
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | DE | DELAWARE | Bethany Beach | 100010 | Regional Training Institute Ph 1 | 2013-06-28 | 2013-07-05 | EDIS Company | 5319000 | 4614000 | 2013-09-23 | 2014-10-20 | 2014-10-01 | 2014-10-01 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) Used FY09 funds
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120192 | Upgrade: Combined Arms Collective Training Facility | 2013-06-07 | 2013-06-25 | Thomas May Construction Company | 8705000 | 6452001.28 | 2013-10-04 | 2014-10-20 | 2014-10-01 | 2014-10-01 | 2 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | IA | IOWA | Camp Dodge | 190142 | Urban Assault Course | 2013-05-29 | 2013-06-07 | Rochon Corporation of Iowa | 2902000 | 2483503 | 2013-08-09 | 2014-05-12 | 2014-04-30 | 2014-04-30 | 2 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | KS | KANSAS | Topeka | 200102 | Taxiway, Ramp & Hangar Alterations | 2013-05-21 | 2013-06-14 | Senne & Co | 9188000 | 8172893.64 | 2013-07-22 | 2014-11-03 | 2014-10-01 | 2014-10-01 | 8 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) Used FY09 funds
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | KY | KENTUCKY | Frankfort | 210001 | Army Aviation Support Facility | 2013-05-17 | 2013-06-04 | DW Wilburn | 30953000 | 25649183 | 2013-07-08 | 2014-11-10 | 2014-10-01 | 2014-10-01 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Minor Construction (UMMC) | MA | MASSACHUSETTS | Bourne (Camp Edwards) | 250196 | Water Well, Non-Potable | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District | 2000000 | 1838000 | 2013-06-03 | 2013-12-02 | 2013-12-01 | 2013-12-01 | 0 | 0
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | MO | MISSOURI | Fort Leonard Wood | 290176 | Regional Training Institute | 2013-07-26 | 2013-08-01 | KCI Construction Company | 17410000 | 14906000 | 2013-12-09 | 2015-02-28 | 2015-02-28 | 2015-02-28 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | MO | MISSOURI | Perryville | 290217 | Readiness Center Add/Alt | 2013-07-31 | 2013-08-01 | Zoellner Construction Co, Inc. | 677000 | 494000 | 2013-10-21 | 2014-02-14 | 2014-02-14 | 2014-02-14 | 0 | 0 |  |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) Used FY09 funds
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | MT | MONTANA | Miles City | 300032 | Readiness Center | 2013-05-29 | 2013-06-07 | Jackson Contractor Group, Inc. | 10639000 | 12041429.5 | 2013-06-17 | 2014-01-27 | 2014-01-01 | 2014-01-01 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | OH | OHIO | Delaware | 390230 | Readiness Center | 2013-05-29 | 2013-06-05 | Barton Marlow Company | 11607000 | 8572022.24 | 2013-06-21 | 2014-01-10 | 2013-12-01 | 2013-12-01 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | UT | UTAH | Camp Williams | 490076 | BEQ Facility (Regional Training Institute) | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 14508000 | 15552165 | 2013-08-12 | 2014-11-10 | 2014-10-01 | 2014-10-01 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) Used FY09 funds
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Major Construction | UT | UTAH | Camp Williams | 490444 | Regional Training Institute Ph 2 | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 20311000 | 14177684 | 2013-08-26 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-05 | 2009 | MDA | UMC | TUR | TURKEY | EUCOM Site | 638 | European Phased Adaptive Approach, Phase I Radar Site | 2011-09-15 | 2011-10-19 | EMTA INSAAT TAAHUT VE TICARET A.S. | 1885 | 1810 | 2011-10-26 | 2011-12-31 | 2011-12-31 | 2013-09-30 | 95 | 0 |  |  | None
2013-07-31 | 2013-08-05 | 2009 | MDA | UMC | AK | ALASKA | Fort Greely | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | 1564 | 1207 | 2013-03-22 | 2013-06-30 | 2013-06-30 | 2013-07-03 | 99 | 0
2013-07-31 | 2013-08-05 | 2010 | MDA | UMC | AK | ALASKA | Fort Greely | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | 1564 | 267 | 2013-03-22 | 2013-06-30 | 2013-06-30 | 2013-07-03 | 99 | 0
2013-07-31 | 2013-08-05 | 2010 | MDA | Major Construction | VA | VIRGINIA | NSWC Dahlgren | 609 | Aegis BMD Facility Expansion | 2010-03-23 | 2010-06-30 | Sauer Incorporated | 18813 | 18681 | 2010-07-15 | 2012-07-31 | 2012-10-31 | 2012-10-31 | 99 | 5700 |  |  | (Reprogrammed to P&D)
2013-07-31 | 2013-08-05 | 2010 | MDA | Major Construction | HI | HAWAII | PMRF | 627 | Aegis Ashore Missile Defense Test Complex - Clearing and Grubbing Only | 2011-06-30 | 2011-08-03 | TOMCO CORP. | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 100 | 0
2013-07-31 | 2013-08-05 | 2010 | MDA | Major Construction | HI | HAWAII | PMRF | 627 | Aegis Ashore Missile Defense Test Complex - Construction | 2012-01-19 | 2012-06-04 | URS GROUP, INC | 59616 | 59616 | 2012-07-04 | 2013-08-29 | 2013-09-12 | 2013-09-12 | 97 | 0
2013-07-31 | 2013-08-05 | 2012 | MDA | Major Construction | AL | ALABAMA | Redstone Arsenal | 633 | Von Braun Complex Phase IV | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | 51330 | 51330 | 2012-07-10 | 2014-07-31 | 2014-10-31 | 2014-10-31 | 50 | 0
2013-07-31 | 2013-08-05 | 2013 | MDA | Major Construction | NY | NEW YORK | Ft Drum | 639 | In-Flight Interceptor Data Terminal Complex | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | 12584 | 13301 | 2013-08-10 | 2014-11-30 | 2014-11-30 | 2014-11-30 | 0 | 0
2013-07-31 | 2013-08-06 | 2006 | Air Force active | MFH construction | NC | NORTH CAROLINA | SEYMOUR JOHNSON AIR FORCE BASE | VKAG056002R1 | Replace Family Housing (Ph 9) | 2007-10-19 | 2009-01-09 | R&O Construction Ogden, Utah | 53054 | 53230 | 2009-03-24 | 2013-04-02 | 2010-09-20 | 2013-04-02 | 98 | 8185
2013-07-31 | 2013-08-06 | 2006 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR064009 | Improve Family Housing, Ph C | 2007-08-01 | 2007-12-06 | Bilfinger Berger | 1802 | 1893 | 2007-12-06 | 2013-04-15 | 2008-07-15 | 2013-02-22 | 99 | -389
2013-07-31 | 2013-08-06 | 2006 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR064009 | Improve Family Housing, Ph C | 2007-08-01 | 2007-12-06 | OBG | 1118 | 1172 | 2007-12-06 | 2013-04-15 | 2008-07-15 | 2013-02-22 | 99 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT053012 | C-17 Alter Hangars (Bldgs 715, 945) | 2007-06-15 | 2007-09-28 | Odyssey | 11816 | 10875 | 2007-11-08 | 2010-11-30 | 2010-10-27 | 2012-10-05 | 100 | 1712
2013-07-31 | 2013-08-06 | 2007 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT053012 | C-17 Alter Hangars (Bldgs 715, 945) | 2007-06-15 | 2010-05-07 | Pride | 3397 | 3397 | 2007-11-08 | 2010-11-30 | 2010-10-27 | 2012-10-05 | 100 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT053012 | C-17 Alter Hangars (Bldgs 715, 945) | 2007-06-15 | 2010-11-19 | Pride | 58 | 58 | 2007-11-08 | 2010-11-30 | 2010-10-27 | 2012-10-05 | 100 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ033011 | Advanced Metal Finishing Facility (DMRT) | 2007-05-07 | 2008-06-25 | Benham Constructors | 27454 | 27763 | 2008-07-11 | 2013-03-14 | 2010-07-12 | 2013-02-27 | 100 | 1489
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2008-05-30 | Joseph H. Henderson, Gurnee, IL | 16203 | 16230 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 1139
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2008-08-07 | Garco Construction, Inc | 45487 | 46502 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2008-09-21 | Oswood Construction Company | 3711 | 3807 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2009-08-25 | Joseph H. Henderson, Gurnee, IL | 21279 | 21718 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2010-05-11 | Talcott | 12893 | 12959 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2010-09-28 | Affilated Constr | 738 | 732 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2011-07-14 | Garco Constr | 14612 | 15102 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | Replace Family Housing | 2009-06-05 | 2011-08-31 | Performance Sys | 10264 | 10197 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR074035 | Improve Family Housing, Ph D | 2010-04-21 | 2010-08-26 | BilfingerBerger Government Service | 2310 | 1776 | 2010-10-14 | 2012-12-21 | 2008-08-01 | 2013-08-16 | 99 | 380
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR074035 | Improve Family Housing, Ph D | 2010-04-21 | 2011-09-07 | OBG Bau GMBH&CoKG | 1402 | 1402 | 2010-10-14 | 2012-12-21 | 2008-08-01 | 2013-08-16 | 99 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR074035 | Improve Family Housing, Ph D | 2010-04-21 | 2013-06-18 | MULTI | 1528 | 1528 | 2010-10-14 | 2012-12-21 | 2008-08-01 | 2013-08-16 | 99 | 0
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ074215 | Improve Family Housing, Ph 7 | 2008-08-01 | 2008-09-29 | OBAYASHI CORPORATION | 99294 | 105399 | 2008-11-18 | 2013-03-12 | 2012-09-01 | 2013-04-15 | 100 | -6532
2013-07-31 | 2013-08-06 | 2007 | Air Force active | MFH improvement | JPN | JAPAN | YOKOTA AIR BASE | ZNRE074306 | Improve MFH (Phase 5) | 2009-05-26 | 2009-09-22 | Nishimatsu Corporation | 38062 | 40339 | 2009-10-22 | 2012-11-09 | 2009-07-01 | 2012-11-09 | 100 | 5840
2013-07-31 | 2013-08-06 | 2007 | Air Force active | Minor construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU073005 | Military Working Dog Kennel | 2006-09-01 | 2007-08-17 | Toltest.Inc | 240 | 240 | 2010-06-29 | 2011-10-27 | 2008-08-17 | 2012-06-26 | 98 | 1753
2013-07-31 | 2013-08-06 | 2007 | Air Force active | Minor construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU073005 | Military Working Dog Kennel | 2006-09-01 | 2010-06-03 | D-Squared and AAK (Joint Ventures) | 1312 | 1312 | 2010-06-29 | 2011-10-27 | 2008-08-17 | 2012-06-26 | 98 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT073002 | C-17 Southwest Landing Zone | 2008-07-12 | 2009-02-18 | Baldi Bros Constructors | 12270 | 15319 | 2010-03-01 | 2013-03-26 | 2009-10-15 | 2013-04-09 | 100 | -3081
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR053714B | Replace Uscentcom Headquarters | 2009-05-05 | 2007-08-15 | temp fac foundation | 896 | 896 | 2009-08-10 | 2012-10-31 | 2012-01-12 | 2012-10-30 | 100 | -34265
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR053714B | Replace Uscentcom Headquarters | 2009-05-05 | 2008-11-21 | Peak Contracting Inc-Early Site | 2476 | 2538 | 2009-08-10 | 2012-10-31 | 2012-01-12 | 2012-10-30 | 100 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR053714B | Replace Uscentcom Headquarters | 2009-05-05 | 2009-06-30 | Clark Construction Group | 61068 | 71895 | 2009-08-10 | 2012-10-31 | 2012-01-12 | 2012-10-30 | 100 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU063009 | 1 AF AFFOR Center, Ph 3 | 2008-07-02 | 2008-09-05 | Speegle Construction, Inc. | 7529 | 7696 | 2008-10-20 | 2010-06-08 | 2010-12-15 | 2013-06-13 | 100 | 355
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU063009 | 1 AF AFFOR Center, Ph 3 | 2008-07-02 | 2012-09-25 | SB Ktr for Parking Lot | 306 | 306 | 2008-10-20 | 2010-06-08 | 2010-12-15 | 2013-06-13 | 100 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ053002 | Command Post Facility | 2008-07-03 | 2008-09-30 | J2 Engineering, Inc. | 4333 | 4451 | 2008-11-12 | 2011-09-12 | 2010-05-06 | 2011-07-29 | 99 | -41
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALDA053001B | Multi-Aircraft Maintenance Hanger | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | 15238 | 15238 | 2010-08-23 | 2013-07-30 | 2009-10-30 | 2013-05-31 | 76 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA073004 | CAS Parking Apron | 2009-05-22 | 2010-04-14 | American International Contractors, Inc | 55884 | 57367 | 2010-05-20 | 2013-06-30 | 2009-10-31 | 2013-06-30 | 99 | 2000
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA073008A | Facility Replacements | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | 26245 | 27676 | 2010-08-23 | 2013-07-30 | 2010-06-30 | 2013-05-31 | 76 | 782
2013-07-31 | 2013-08-06 | 2008 | Air Force active | Major construction | TX | TEXAS | LAUGHLIN AIR FORCE BASE | MXDP073000 | Consolidated Student Activity Center/Library | 2009-07-06 | 2009-09-01 | Cooley Constructors, Oklahoma City, OK | 4407 | 5001 | 2009-11-05 | 2011-10-31 | 2010-03-31 | 2013-06-28 | 99 | 749
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR084014 | Improve Family Housing, Ph E | 2012-11-02 | 2013-05-17 | MICKAN | 4639 | 4639 | 2013-07-08 | 2014-10-31 | 2009-06-15 | 2014-09-26 | 3 | 1025
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2009-10-29 | Nishimatsu Construction Corporation | 140248 | 144122 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 80 | 28229
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2010-07-23 | PASCO Corporation (Meguro-KU) *Arch Test Digs* | 30 | 30 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 80 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-06-22 | Okinawa Elevator Maintenance Union (Naha) *CCT4506 leak rpr* | 43 | 43 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 80 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 405 | 405 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 80 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | MISAWA AIR BASE | QKKA084025 | Improve Family Housing, Ph. 3 | 2008-11-21 | 2009-03-31 | Nishimatsu Construction Co. Lt | 35226 | 36790 | 2011-08-31 | 2013-12-14 | 2010-09-01 | 2013-12-14 | 63 | 15873
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | YOKOTA AIR BASE | ZNRE084303 | Improve MFH (Phase 6) | 2010-02-12 | 2010-07-08 | Nishimatsu | 31373 | 33885 | 2010-08-02 | 2012-12-21 | 2011-01-01 | 2012-12-25 | 100 | -3587
2013-07-31 | 2013-08-06 | 2008 | Air Force active | MFH improvement | TUR | TURKEY | INCIRLIK AIR BASE ADANA | LJYC084001 | Improve Family Housing 515 Units | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | 41970 | 41673 | 2009-12-04 | 2014-08-15 | 2011-06-30 | 2014-06-15 | 19 | 14622
2013-07-31 | 2013-08-06 | 2008 | Air Force NG | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU059006 | Squadron Operations Facility | 2008-07-11 | 2008-09-19 | Aleut Facilities Support Services, LLC | 6676 | 7904 | 2008-10-24 | 2010-01-27 | 2009-10-19 | 2013-02-18 | 100 | 604
2013-07-31 | 2013-08-06 | 2008 | Air Force NG | Major construction | FL | FLORIDA | JACKSONVILLE INTERNATIONAL AIRPORT | LSGA029009 | Communications Training Facility | 2008-08-25 | 2008-09-26 | Cooley Constructors, Inc. | 4809 | 5661 | 2008-10-15 | 2010-12-12 | 2010-01-18 | 2011-10-25 | 100 | -339
2013-07-31 | 2013-08-06 | 2008 | Air Force NG | Major construction | IN | INDIANA | HULMAN REGIONAL AIRPORT | LDXF069062 | TFI - Distributed Ground Station (DGS) Beddown | 2008-07-16 | 2008-09-26 | Hannig Construction Incorporated | 2901 | 5074 | 2008-10-15 | 2010-10-01 | 2009-10-15 | 2012-06-01 | 100 | 251
2013-07-31 | 2013-08-06 | 2008 | Air Force NG | Major construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB019121 | Add/Alter Security Forces and Communications Facility | 2010-10-29 | 2011-01-14 | Kingery Construction | 1181 | 1567 | 2011-02-01 | 2011-11-07 | 2011-02-13 | 2012-02-01 | 100 | -108
2013-07-31 | 2013-08-06 | 2008 | Air Force NG | Major construction | VT | VERMONT | BURLINGTON INTERNATIONAL AIRPORT | CURZ049023 | Security Improvements- Relocate Poor Farm Road | 2011-01-03 | 2011-09-24 | Stewart Construction INC | 4730 | 6102 | 2011-10-14 | 2012-11-15 | 2012-09-18 | 2013-05-15 | 99 | -641
2013-07-31 | 2013-08-06 | 2008 | Air Force NG | Minor construction | MA | MASSACHUSETTS | BARNES MUNICIPAL AIRPORT | AXQD109075 | Snow Removal Equipment Storage Facility | 2011-05-23 | 2012-03-09 | Classic Site Solutions, Inc | 1494 | 1694 | 2012-04-20 | 2013-05-31 | 2012-10-17 | 2013-05-31 | 70 | 0
2013-07-31 | 2013-08-06 | 2008 | Air Force NG | Minor construction | OR | OREGON | KLAMATH FALLS AIRPORT-KINGSLEY FIELD | KJAQ109022 | Expand North Arm Disarm Apron | 2012-06-02 | 2012-08-01 | J.I. Garcia | 1931 | 1966 | 2012-08-14 | 2013-05-31 | 2012-12-14 | 2013-07-31 | 78 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH093150 | CAS Apron | 2010-05-06 | 2010-09-07 | CH2MHILL | 14119 | 20209 | 2010-10-15 | 2012-07-31 | 2011-07-15 | 2012-10-10 | 100 | -10026
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | Construct Child Development Center | 2009-07-31 | 2009-09-29 | MaxFour, Englewood, Co | 8114 | 8150 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | -490
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | Construct Child Development Center | 2009-07-31 | 2012-03-05 | M&SS | 31 | 31 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | Construct Child Development Center | 2009-07-31 | 2012-08-28 | American Demolition Inc | 59 | 59 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | Construct Child Development Center | 2009-07-31 | 2012-11-15 | M&SS | 89 | 89 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT993002 | ADAL Physical Fitness Center | 2009-05-11 | 2009-09-03 | Richard Y. Johnson & Son Inc | 11414 | 12457 | 2009-09-17 | 2011-11-18 | 2010-10-06 | 2013-01-31 | 100 | -5654
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU063004 | 325 Acs Ops Training Complex | 2009-05-28 | 2009-09-08 | Speegle Construction, Inc. | 7136 | 8401 | 2009-10-14 | 2011-11-29 | 2011-09-08 | 2013-02-07 | 100 | -2284
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK093005 | Construct Child Development Center | 2012-01-07 | 2011-09-02 | LBB (EBC AWD) | 9924 | 10171 | 2012-07-09 | 2014-03-30 | 2011-03-09 | 2014-01-30 | 56 | 1307
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK093005 | Construct Child Development Center | 2012-01-07 | 2012-05-15 | Peter Gross GmbH | 1263 | 1263 | 2012-07-09 | 2014-03-30 | 2011-03-09 | 2014-01-30 | 56 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | MS | MISSISSIPPI | KEESLER AIR FORCE BASE | MAHG033002 | Indoor Firing Range | 2009-07-15 | 2010-06-23 | North Wind, Inc. | 5329 | 5451 | 2010-07-19 | 2012-03-28 | 2011-11-21 | 2012-10-23 | 100 | -570
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | MS | MISSISSIPPI | KEESLER AIR FORCE BASE | MAHG043000 | Dormitory (144 Pn) | 2009-07-08 | 2009-08-28 | Anderson Drace JV | 14453 | 15527 | 2009-10-28 | 2011-05-10 | 2011-07-04 | 2013-04-05 | 100 | -3677
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000 | Upgrade Weapons Storage Area, Phase I | 2009-08-06 | 2009-09-26 | Doyon Project Services, Federal Way, WA | 10481 | 12002 | 2009-11-11 | 2012-12-10 | 2009-08-07 | 2014-07-30 | 99 | 4995
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000 | Upgrade Weapons Storage Area, Phase I | 2009-08-06 | 2013-07-17 | Affiliated Construction Group | 38 | 38 | 2009-11-11 | 2012-12-10 | 2009-08-07 | 2014-07-30 | 99 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | NV | NEVADA | CREECH AIR FORCE BASE | LKTC093101 | UAS Ops Facility | 2008-12-12 | 2009-04-28 | USACE | 9388 | 13931 | 2009-07-23 | 2013-07-10 | 2010-08-03 | 2013-07-10 | 100 | -333
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF083011 | F-16 Aggressor Squadron Ops/Infrastructure | 2008-12-29 | 2009-03-24 | HARDY CONSTRUCTION, LAS VEGAS, NV | 5344 | 6197 | 2009-04-23 | 2013-01-10 | 2010-07-05 | 2013-03-15 | 100 | -3012
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF083011 | F-16 Aggressor Squadron Ops/Infrastructure | 2008-12-29 | 2010-04-21 | CJW-MZT Project II | 5188 | 5188 | 2009-04-23 | 2013-01-10 | 2010-07-05 | 2013-03-15 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | NJ | NEW JERSEY | MCGUIRE AIR FORCE BASE | PTFL073003P1 | Security Forces Operations Facility Ph 1 | 2009-06-02 | 2009-08-10 | Eastern Const & Electric Wrightstown NJ | 6610 | 7222 | 2009-08-27 | 2012-08-29 | 2011-08-17 | 2013-01-31 | 100 | 561
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF072003 | Dormitory (168 Rm) | 2009-06-27 | 2009-08-25 | Graham Construction Services | 18860 | 19749 | 2009-09-24 | 2011-09-17 | 2011-09-14 | 2013-09-30 | 99 | -7268
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | OH | OHIO | WRIGHT PATTERSON AIR FORCE BASE | ZHTV063202 | Security Forces Operations Facility | 2009-04-02 | 2009-06-04 | WIL CON Corporation | 12152 | 13870 | 2009-06-24 | 2011-03-01 | 2010-12-13 | 2013-03-01 | 100 | 884
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA080126 | Temporary West Munitions Storage Area | 2010-02-19 | 2010-06-03 | American International Contractors, Inc. | 18079 | 15944 | 2010-08-05 | 2013-02-27 | 2010-12-15 | 2013-02-09 | 100 | 2000
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS093002 | Cns Addition To Child Development Center (Cdc) B8210 | 2009-07-14 | 2009-08-31 | MAPCO, Inc. | 5913 | 6605 | 2009-10-15 | 2012-08-20 | 2011-02-22 | 2012-11-27 | 99 | 1420
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Major construction | GBR | UNITED KINGDOM | RAF LAKENHEATH | MSET023002 | Large Vehicle Inspection Station | 2009-09-16 | 2010-11-23 | MANSELL PLC | 12684 | 12684 | 2011-01-10 | 2012-11-15 | 2010-08-07 | 2012-11-15 | 100 | 5710
2013-07-31 | 2013-08-06 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2009-09-24 | Nishimatsu Construction Co Ltd | 104812 | 107709 | 2010-02-04 | 2014-06-01 | 2015-10-20 | 2014-06-30 | 83 | -16062
2013-07-31 | 2013-08-06 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 140 | 140 | 2010-02-04 | 2014-06-01 | 2015-10-20 | 2014-06-30 | 83 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Minor construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY086000 | Interim Horizontal Landfill Expansion | 2009-07-31 | 2010-03-11 | RMA Land Construction | 910 | 910 | 2010-03-29 | 2013-04-30 | 2010-12-15 | 2013-04-30 | 99 | 883
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Minor construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS086006 | Replace MWD Kennel Facility | 2011-02-02 | 2011-07-26 | Oswood Construction, GF, MT | 1904 | 1904 | 2011-08-15 | 2012-11-30 | 2012-11-02 | 2012-12-20 | 92 | 1989
2013-07-31 | 2013-08-06 | 2009 | Air Force active | Minor construction | TUR | TURKEY | ANKARA ADMINISTRATION OFFICE | AKNR041053 | Cns Replace Asf Admin Bldg 2621 | 2011-02-22 | 2011-09-23 | MATOC Contractor | 1367 | 1367 | 2012-02-15 | 2014-12-31 | 2011-05-12 | 2014-11-01 | 3 | 1505
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | ARRA | IN | INDIANA | ATTERBURY RESERVE FORCES TRAINING AREA | AQXG029005 | Range Support Facility Complex | 2010-06-02 | 2010-07-28 | Dunlap & Co. Inc. | 1052 | 1157 | 2010-09-21 | 2012-06-30 | 2011-07-18 | 2012-06-30 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | ARRA | IA | IOWA | DES MOINES INTERNATIONAL AIRPORT | FFAN049054 | Replace Communications Facility | 2009-05-05 | 2009-06-23 | Breiholz Construction | 5761 | 6428 | 2009-07-16 | 2010-12-15 | 2010-07-16 | 2012-07-20 | 100 | 431
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | ARRA | PA | PENNSYLVANIA | FT INDIANTOWN GAP ANG STATION | LKLW959714 | Replace Troop Training Quarters | 2009-08-05 | 2009-09-30 | Miller Bros Construction | 4986 | 5834 | 2009-10-15 | 2010-11-15 | 2010-10-15 | 2012-01-31 | 100 | -1166
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | ARRA | UT | UTAH | SALT LAKE CITY INTERNATIONAL AIRPORT | USEB889585B | Construct Mobility Processing and EOD Facility | 2009-05-27 | 2009-08-31 | Zwick Construction Company | 2167 | 2450 | 2009-09-08 | 2012-02-05 | 2011-05-01 | 2012-06-14 | 100 | -2600
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | ARRA | WV | WEST VIRGINIA | EWVRA-SHEPHERD FIELD | PJVY049072 | C-5 Avionics Shop | 2009-07-31 | 2009-09-28 | LDH Electrical Co | 2274 | 2660 | 2009-10-23 | 2010-12-20 | 2010-10-23 | 2011-10-31 | 100 | -1617
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU029003 | Alert Crew Headquarters | 2009-04-17 | 2009-09-09 | Tower One Construction Company | 2451 | 2877 | 2009-10-30 | 2011-02-11 | 2010-10-30 | 2013-10-22 | 99 | -1323
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | CT | CONNECTICUT | BRADLEY INTERNATIONAL AIRPORT | CEKT069119 | TFI - Upgrade Engine Shop | 2009-06-18 | 2010-01-08 | Cutter Enterprises | 4360 | 5403 | 2010-02-01 | 2012-12-24 | 2010-12-04 | 2013-02-28 | 100 | -2095
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | DE | DELAWARE | NEW CASTLE COUNTY AIRPORT | JLWS019057 | Replace C-130 Aircraft Maintenance Shops | 2009-02-03 | 2009-06-12 | DJ's Mechanical Inc. | 9323 | 9987 | 2009-06-30 | 2011-01-20 | 2010-06-30 | 2011-12-15 | 99 | -1705
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | MD | MARYLAND | MARTIN STATE AIRPORT | PJMS959554 | Replace Fire Station | 2009-07-20 | 2009-09-24 | Milestone Construction Services | 6321 | 7178 | 2009-09-24 | 2011-09-01 | 2011-03-23 | 2012-10-31 | 100 | -760
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN079049 | TFI-Digital Ground Station- IOC | 2009-09-18 | 2009-09-30 | Endicott Construction | 11792 | 14036 | 2009-10-20 | 2013-03-22 | 2011-04-13 | 2013-04-15 | 93 | -264
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | MN | MINNESOTA | MINNEAPOLIS ST PAUL INTL AIRPORT | QJKL079050 | Aircraft De-icing Drainage System | 2010-09-08 | 2010-09-08 | Hamline Construction | 1161 | 1260 | 2010-10-07 | 2011-06-30 | 2010-10-08 | 2012-02-29 | 100 | -240
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB039126 | Replace Fire Station/Training Facility | 2008-06-20 | 2009-11-19 | CITY of St Joseph | 999 | 1063 | 2009-12-19 | 2012-05-20 | 2010-12-14 | 2012-05-20 | 100 | -942
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB039126 | Replace Fire Station/Training Facility | 2009-09-01 | 2009-09-28 | Wolfe Construction 836 Osage Ave | 2730 | 2995 | 2009-09-30 | 2011-09-23 | 2010-10-28 | 2011-10-28 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | NY | NEW YORK | FRANCIS S. GABRESKI AIRPORT | WKVB079038 | Replace Pararescue Ops Facility, PH2 | 2009-06-20 | 2009-03-20 | Racanelli Constrution Company, Inc (631)-454-1010 | 5554 | 5838 | 2009-04-14 | 2012-07-27 | 2010-07-13 | 2012-08-30 | 100 | -1662
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP049130 | Replace Fire Crash Rescue Station | 2009-06-22 | 2009-07-29 | Edison Foard, Inc; | 3629 | 5875 | 2009-08-04 | 2010-07-16 | 2010-05-31 | 2012-04-30 | 100 | -1125
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | ND | NORTH DAKOTA | HECTOR INTERNATIONAL AIRPORT | KKGA029115 | Fire Crash and Rescue Station | 2009-06-20 | 2010-01-27 | TF Powers | 4775 | 5203 | 2010-01-27 | 2011-07-28 | 2011-01-27 | 2012-01-31 | 99 | -2310
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | OH | OHIO | SPRINGFIELD-BECKLEY MUNICIPAL AIRPORT | WAAR009098 | Combat Communications Training Facility | 2011-04-13 | 2011-08-01 | Tamsah Marker JV | 10601 | 11554 | 2011-08-19 | 2013-06-30 | 2012-08-18 | 2013-06-30 | 99 | -1246
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | RI | RHODE ISLAND | QUONSET STATE AIRPORT | TWLR039186 | Construct Air Traffic Control Tower | 2010-01-08 | 2010-07-23 | Cutter Enterprises, LLC | 6290 | 7708 | 2010-10-26 | 2012-08-10 | 2011-06-01 | 2013-04-30 | 100 | 9
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC079089 | Aircraft Ready Shelters/AMU | 2010-10-05 | 2011-02-02 | Golden Rule Constuction Co., Inc. | 3506 | 3622 | 2011-04-24 | 2012-01-10 | 2011-12-28 | 2012-04-19 | 100 | -878
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | TN | TENNESSEE | MCGHEE TYSON AIRPORT | PSXE999134 | Replace Squadron Operations | 2009-08-03 | 2009-09-23 | Hickory Construction, Inc. | 5890 | 6262 | 2009-10-05 | 2011-09-14 | 2011-05-28 | 2011-10-14 | 100 | -1738
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | UT | UTAH | SALT LAKE CITY INTERNATIONAL AIRPORT | USEB889585 | Replace Fire Station | 2009-05-27 | 2009-08-31 | Zwick Construction Company | 5072 | 5973 | 2009-09-08 | 2012-02-10 | 2011-05-01 | 2012-10-31 | 100 | -2527
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | VT | VERMONT | BURLINGTON INTERNATIONAL AIRPORT | CURZ069220 | Security Forces and Communications Facility | 2011-08-23 | 2011-09-26 | Stewart Construction | 5347 | 6130 | 2011-11-18 | 2013-02-16 | 2013-01-03 | 2013-04-30 | 99 | -470
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | WA | WASHINGTON | MCCHORD AIR FORCE BASE | PQWY059045 | 262d Info Warfare Aggressor Squadron Facility | 2009-08-10 | 2009-09-29 | Pine Island/Takisaki | 5659 | 6792 | 2009-10-02 | 2011-07-25 | 2010-09-27 | 2012-08-01 | 100 | -1808
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Major construction | WV | WEST VIRGINIA | YEAGER AIRPORT | LYBH009134 | Fuel System/Corrosion Control Hangar | 2009-07-29 | 2009-09-30 | BBL Carlton LLC | 20068 | 21860 | 2009-11-05 | 2011-11-30 | 2011-04-29 | 2012-12-05 | 100 | -1193
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | AL | ALABAMA | BIRMINGHAM INTERNATIONAL AIRPORT | BRKR029059 | aKC-135 Alert Crew Quarters | 2009-08-21 | 2009-09-29 | North American Specialty Insurance Company | 1232 | 1590 | 2009-10-29 | 2012-12-27 | 2010-12-23 | 2012-12-27 | 99 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG099009 | DRBS Storage Facility | 2012-07-26 | 2012-09-27 | Marsh Creek Construction | 1412 | 1451 | 2012-10-31 | 2014-01-12 | 2012-10-31 | 2014-01-12 | 10 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | CA | CALIFORNIA | SOUTHERN CALIFORNIA LOGISTICS APT | SCLT109080 | Predator LRE Storage Facility | 2012-07-26 | 2012-09-27 | Marsh Creek Construction | 1597 | 1687 | 2012-10-31 | 2014-01-14 | 2012-10-31 | 2014-01-14 | 20 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU109069 | Replace CRTC AGE Facility | 2012-06-05 | 2012-07-19 | HCR Construction Inc | 927 | 1011 | 2012-09-17 | 2013-05-13 | 2013-04-28 | 2013-08-14 | 99 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | IN | INDIANA | FORT WAYNE INTERNATIONAL AIRPORT | ATQZ109537 | A10 Conversion Add and Alter Aircraft Shops | 2011-03-22 | 2011-09-25 | Patterson Horth | 1406 | 1432 | 2011-09-28 | 2012-10-01 | 2012-08-20 | 2012-10-01 | 70 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | KS | KANSAS | SMOKY HILL ANG RANGE | VUBV119025 | Construct Vehicle Maintenance Facility | 2012-11-15 | 2012-12-19 | SBA Construction Company | 1861 | 1926 | 2013-01-18 | 2014-02-02 | 2014-01-18 | 2014-02-02 | 28 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | NY | NEW YORK | EASTERN AIR DEFENSE SECTOR (EADS) ANG | GRCL109071 | Add to and Alter NEADS Operations Building | 2012-06-15 | 2012-08-20 | VETCO Contracting Services LLC. | 1331 | 1382 | 2012-08-21 | 2013-06-17 | 2013-06-17 | 2013-06-17 | 97 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP099064 | aANG Share- Joint Ops Center | 2009-04-01 | 2009-06-05 | Shelco, Inc | 823 | 823 | 2009-07-13 | 2011-09-30 | 2011-07-13 | 2012-02-15 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | OH | OHIO | RICKENBACKER INTERNATIONAL AIRPORT (ANG) | NLZG069111 | Aircraft Support Equipment (ASE) Facility | 2012-02-29 | 2012-05-14 | Puente/CCE - JV | 785 | 931 | 2012-05-23 | 2013-05-31 | 2013-02-17 | 2013-06-28 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | OH | OHIO | RICKENBACKER INTERNATIONAL AIRPORT (ANG) | NLZG082014 | Security Gate | 2011-08-24 | 2011-09-22 | SherrickWoolpert Co | 1917 | 1959 | 2011-11-10 | 2012-08-31 | 2012-08-06 | 2013-01-25 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD109045 | Add to and Alter Crash/Fire Station | 2010-10-13 | 2011-01-20 | McTech Industries | 1205 | 1542 | 2011-02-03 | 2011-12-29 | 2012-02-03 | 2012-02-29 | 100 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | SC | SOUTH CAROLINA | MCENTIRE JOINT NATIONAL GUARD BASE | PSTE119018 | Pavements and Grounds Facility | 2012-11-30 | 2013-01-10 | Lyn-Rich Contracting Company | 1560 | 1607 | 2013-02-25 | 2013-08-26 | 2013-08-08 | 2013-08-26 | 20 | 0
2013-07-31 | 2013-08-06 | 2009 | Air Force NG | Minor construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC079133 | Conventional Munitions Storage Complex | 2009-08-18 | 2009-09-30 | Golden Rule Construction Co | 1559 | 1792 | 2009-10-16 | 2010-08-19 | 2010-07-13 | 2011-11-30 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH103400 | Aviation Operations & Maintenance Facilities | 2010-05-06 | 2010-09-07 | CH2MHILL | 3085 | 4661 | 2010-10-15 | 2012-11-20 | 2011-07-15 | 2012-11-20 | 100 | -3700
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH103500 | Expeditionary Fighter Shelter | 2010-05-06 | 2010-09-07 | CH2MHILL | 2959 | 3868 | 2010-10-15 | 2013-08-30 | 2011-07-15 | 2013-08-30 | 99 | -2072
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | CAMP BASTION | CMBA113100 | Parallel Taxiway | 2011-01-03 | 2011-05-10 | Enterprise Chemical Corporation/Burlingame/CA | 29770 | 30973 | 2011-05-10 | 2012-05-17 | 2012-02-14 | 2012-10-13 | 100 | -51000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | CAMP BASTION | CMBA113200 | Refueler Apron | 2011-01-03 | 2011-05-10 | Environmental Chemical Corporation/Burlingame/CA | 13298 | 13408 | 2011-05-10 | 2012-10-04 | 2012-01-02 | 2012-10-13 | 100 | -39000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | FOB DWYER | ACC103910 | Cargo Handling Area | 2010-05-10 | 2010-06-25 | ACI-SCC (JV) | 4154 | 4154 | 2010-07-28 | 2013-12-31 | 2011-01-25 | 2013-12-31 | 84 | 106
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | KANDAHAR AB | KARD113100 | Expand Cargo Handling Area | 2010-11-23 | 2011-02-14 | Yenigun Insaat Sanayi ve Ticaret A.S. | 5337 | 6121 | 2011-03-30 | 2013-02-01 | 2011-11-21 | 2013-08-05 | 99 | 7100
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | KANDAHAR AB | KARD113200 | Expeditionary Airlift Shelter | 2010-11-23 | 2011-02-14 | Yenigun Insaat Sanayi ve Ticaret A.S. | 6743 | 6777 | 2011-03-30 | 2013-08-21 | 2011-11-21 | 2013-08-21 | 99 | 7659
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | KANDAHAR AB | LYAV103500 | ISR Apron Expansion | 2010-06-08 | 2010-09-30 | CH2MHill | 21235 | 21668 | 2010-11-02 | 2012-03-23 | 2011-04-29 | 2013-04-12 | 100 | -14877
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | KANDAHAR AB | LYAV103900 | Relocate North Airfield Road | 2011-03-08 | 2011-07-29 | Contrack International Inc. | 4012 | 5587 | 2011-09-03 | 2012-07-13 | 2011-05-04 | 2012-11-09 | 100 | -8000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 | 2010-07-12 | 2011-06-02 | Haskell Corporation | 26981 | 28332 | 2011-06-17 | 2015-02-26 | 2014-11-23 | 2015-02-26 | 40 | 31702
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV103001 | CSAR HC-130J Simulator Facility | 2010-04-16 | 2010-08-20 | KISAQ-RQ LLC | 4852 | 5081 | 2010-09-22 | 2013-02-17 | 2012-12-17 | 2013-05-31 | 97 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV103002 | CSAR HC-130J Rescue Squadron Operations Facility | 2010-04-16 | 2010-08-20 | KISAQ-RQ LLC | 4868 | 5035 | 2010-09-22 | 2013-02-17 | 2012-12-17 | 2013-05-31 | 97 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV103003 | CSAR HC-130J Infrastructure | 2010-04-16 | 2010-08-20 | KISAQ-RQ LLC | 4150 | 4347 | 2010-09-22 | 2013-02-17 | 2011-05-20 | 2013-05-31 | 98 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT063010 | Taxiway Mike Bypass Road | 2011-06-14 | 2012-01-06 | Hal Hays Construction, Inc | 4899 | 4946 | 2012-01-06 | 2012-12-20 | 2013-01-31 | 2013-01-28 | 99 | 562
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | CA | CALIFORNIA | VANDENBERG AIR FORCE BASE | XUMU003000 | Child Development Center | 2009-12-04 | 2010-03-18 | The Korte Company | 9777 | 10061 | 2010-04-06 | 2012-05-11 | 2011-01-14 | 2013-01-11 | 100 | -265
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA093004 | East Gate Realignment | 2011-08-26 | 2011-12-29 | Komada | 5290 | 5630 | 2012-01-26 | 2013-05-06 | 2011-09-30 | 2013-05-06 | 100 | -606
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT033003 | Consol Communications Facility | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | 10187 | 11663 | 2010-10-13 | 2013-08-30 | 2011-11-09 | 2015-05-20 | 93 | 1005
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT093000A | Chapel Center | 2010-06-07 | 2010-11-24 | Gardiner and Gardiner Contracting, LLC | 7719 | 7748 | 2011-01-03 | 2012-11-16 | 2012-05-08 | 2013-02-13 | 100 | 1275
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA053025 | Construct Dormitory (96 Rm) | 2009-10-16 | 2010-02-11 | Whitesell-Green, Inc/Yates & Sons, JV | 7635 | 8472 | 2010-09-03 | 2013-03-29 | 2011-08-01 | 2013-03-29 | 100 | 503
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA061726 | F-35 POL Ops Facility | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | 4309 | 4384 | 2010-10-27 | 2013-12-30 | 2010-12-30 | 2013-12-31 | 98 | 72
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073902 | F-35 Hydrant Refueling System Phase 1 | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | 9452 | 9944 | 2010-07-15 | 2013-10-30 | 2011-02-28 | 2013-12-30 | 99 | -85
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073904 | F-35 JP-8 Flightline Fillstands | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | 3217 | 3264 | 2010-10-07 | 2013-10-30 | 2010-12-30 | 2013-12-31 | 97 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073905 | F-35 JP-8 West Side Bulk Fuel Tank Upgrades | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | 1464 | 1494 | 2010-06-15 | 2013-10-30 | 2010-12-30 | 2013-12-31 | 99 | 85
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073911 | F-35 Live Ordnance Load Facility | 2010-03-25 | 2010-06-04 | R.C. Construction Co., Inc. | 14320 | 14551 | 2010-06-28 | 2011-11-01 | 2011-06-30 | 2013-03-11 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR033702 | Consolidated Communications Facility | 2010-05-19 | 2010-07-07 | Carothers Construction | 16518 | 16938 | 2010-08-11 | 2013-10-23 | 2013-08-10 | 2013-10-23 | 86 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR063708 | Dormitory (120 Room) | 2009-08-21 | 2010-02-19 | David Boland | 10095 | 12251 | 2010-06-09 | 2012-08-13 | 2012-02-04 | 2012-11-05 | 100 | 1724
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT013025 | Combat Weapons Training Facility | 2010-07-09 | 2010-09-22 | Harkins Development Corp | 8381 | 8519 | 2010-12-03 | 2012-06-22 | 2011-09-30 | 2013-10-31 | 99 | 1544
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR053037 | Aerospace Ground Equipment Maintenance Complex | 2012-01-27 | 2011-09-30 | LBB (EBC AWD) | 10500 | 10500 | 2012-06-15 | 2014-01-15 | 2012-09-26 | 2013-12-23 | 18 | -2987
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR0530402 | Contingency Response Group Command | 2011-06-26 | 2011-08-26 | Bodo Freimuth GmbH (Demo AWD) | 235 | 299 | 2012-01-01 | 2014-02-28 | 2012-09-26 | 2014-01-31 | 46 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR0530402 | Contingency Response Group Command | 2011-06-26 | 2011-09-24 | LBB (EBC AWD) | 19788 | 19788 | 2012-01-01 | 2014-02-28 | 2012-09-26 | 2014-01-31 | 46 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK043100 | Fitness Center | 2011-01-22 | 2011-05-30 | Peter Gross Bau | 17881 | 18317 | 2011-06-07 | 2013-10-28 | 2006-04-15 | 2013-09-19 | 92 | 1127
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | HI | HAWAII | HICKAM AIR FORCE BASE | KNMD063003 | Ground Control Tower | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | 7379 | 7393 | 2012-09-07 | 2014-02-14 | 2011-10-28 | 2014-02-28 | 27 | 4435
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | IL | ILLINOIS | SCOTT AIR FORCE BASE | VDYD040181 | Aeromedical Evacuation Faciuty | 2010-03-01 | 2010-05-10 | Charpie-Korte Joint Venture | 5851 | 6460 | 2010-05-25 | 2012-01-31 | 2011-11-09 | 2012-09-04 | 99 | -164
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | ITA | ITALY | NAVAL AIR STATION SIGONELLA | USAFE073006 | Global Hawk Aircraft Maint And Ops Complex | 2010-03-20 | 2010-09-24 | C.M.C. di Ravenna | 16487 | 16487 | 2010-09-30 | 2012-10-04 | 2009-01-31 | 2012-10-04 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | MD | MARYLAND | ANDREWS AIR FORCE BASE | AJXF063009 | Replace Munitions Storage Area | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | 10465 | 10753 | 2011-06-23 | 2013-12-02 | 2011-12-16 | 2013-12-02 | 79 | 1994
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG081001 | Land Acquisition North & South Boundaries | 2012-05-09 | 2012-09-12 | In-House Work Force-NWK | 3475 | 3475 | 2012-09-12 | 2013-10-18 | 2013-02-28 | 2013-10-18 | 51 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000A | Upgrade Weapons Storage Area | 2012-04-23 | 2012-11-28 | RSCI | 9475 | 9429 | 2013-01-07 | 2015-03-28 | 2012-02-29 | 2015-01-27 | 9 | 99
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | NE | NEBRASKA | OFFUTT AIR FORCE BASE | SGBP120902 | Stratcom Gate | 2010-07-08 | 2010-09-24 | JE Dunn Construction Company, Kansas City MO | 10842 | 11328 | 2010-10-14 | 2013-05-28 | 2012-07-15 | 2013-03-29 | 51 | 1910
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063002 | Consolidated Communication Facility | 2010-01-14 | 2010-03-24 | San Juan Construction, Inc. | 12305 | 13622 | 2010-04-21 | 2014-02-24 | 2008-06-15 | 2014-01-24 | 41 | 11992
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063002 | Consolidated Communication Facility | 2010-01-14 | 2012-01-26 | Spiral Solutions | 1930 | 1930 | 2010-04-21 | 2014-02-24 | 2008-06-15 | 2014-01-24 | 41 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD103003 | UAS Ftu Complex | 2010-05-18 | 2010-09-02 | Mesa Verde Enterprises | 9947 | 12830 | 2010-11-15 | 2012-07-17 | 2012-08-03 | 2013-11-30 | 99 | 5000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD103003 | UAS Ftu Complex | 2010-05-18 | 2010-09-07 | Creative Times | 16695 | 16695 | 2010-11-15 | 2012-07-17 | 2012-08-03 | 2013-11-30 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | NC | NORTH CAROLINA | POPE AIR FORCE BASE | TMKH063006CT | Air Traffic Control Tower | 2010-05-25 | 2010-08-11 | LIFECYCLE CONSTRUCTION SERVICE | 7462 | 7789 | 2010-09-10 | 2013-02-18 | 2011-03-03 | 2014-05-30 | 99 | 108
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | NC | NORTH CAROLINA | SEYMOUR JOHNSON AIR FORCE BASE | VKAG013004A | Radar Approach Control Complex, Ph 1 | 2010-06-28 | 2010-09-21 | Sanford Group | 5655 | 6168 | 2010-09-29 | 2013-09-20 | 2012-02-06 | 2013-09-13 | 80 | 432
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | ND | NORTH DAKOTA | GRAND FORKS AIR FORCE BASE | JFSD200113 | Consolidated Security Forces Facility | 2010-07-19 | 2010-09-17 | CONSTRUCTION ENGINEERS, INC, Grand Forks ND | 9180 | 9640 | 2010-10-26 | 2012-09-18 | 2012-09-15 | 2013-08-01 | 100 | -1275
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF082003 | Dormitory (168 Rm) | 2010-05-21 | 2010-08-20 | RAASS Brothers Inc. | 16590 | 17063 | 2010-10-05 | 2012-05-09 | 2012-05-09 | 2013-11-01 | 93 | 18373
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | OH | OHIO | WRIGHT PATTERSON AIR FORCE BASE | ZHTV063301 | Conversion For Advanced Power Research Lab | 2009-12-10 | 2010-06-16 | Messer Construction Company, Dayton, OH | 17884 | 19090 | 2010-07-07 | 2013-02-15 | 2012-04-24 | 2013-08-14 | 99 | 245
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | Child Development Center | 2010-03-17 | 2010-05-27 | Nationview/BhateJV | 8649 | 9382 | 2010-05-27 | 2013-07-31 | 2011-12-15 | 2013-07-31 | 98 | 10408
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | Child Development Center | 2010-03-17 | 2010-09-27 | MA-CHIS KAWV TWO, LLC | 231 | 231 | 2010-05-27 | 2013-07-31 | 2011-12-15 | 2013-07-31 | 98 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | Child Development Center | 2010-03-17 | 2010-09-30 | Nationview Bhate - Kitchen Equip - B. Opt 6 | 167 | 167 | 2010-05-27 | 2013-07-31 | 2011-12-15 | 2013-07-31 | 98 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK103019 | T-9 Noise Suppressor | 2010-07-23 | 2010-09-24 | Downey Construction LLC, Oklahoma City, OK | 5598 | 5676 | 2010-11-02 | 2012-12-19 | 2011-07-31 | 2012-12-20 | 100 | 834
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | VANCE AIR FORCE BASE | XTLF033303 | Control Tower | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | 8850 | 9511 | 2010-10-05 | 2014-02-14 | 2012-05-31 | 2014-05-14 | 53 | 673
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA073006A | Blatchford-Preston Complex Ph II | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | 35759 | 35574 | 2010-12-16 | 2013-08-02 | 2012-02-15 | 2013-07-02 | 56 | 1993
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA103001 | Construct Network Control Center | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | 2580 | 2580 | 2012-07-05 | 2013-09-08 | 2011-08-15 | 2013-09-08 | 19 | 2911
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA107000 | Coalition Compound Billeting | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | 45273 | 45273 | 2012-04-16 | 2014-03-06 | 2013-11-30 | 2014-03-06 | 27 | 52000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | SC | SOUTH CAROLINA | SHAW AIR FORCE BASE | VLSB073002 | Add/Alt USAFCENT Headquarters | 2010-06-22 | 2010-09-21 | Roy Anderson Corp | 14431 | 16353 | 2010-09-21 | 2012-12-11 | 2012-10-01 | 2013-05-17 | 99 | 1852
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104200 | Strategic Airlift Apron (Mazar-E-Sharif) | 2010-08-23 | 2011-04-08 | Yuksel Insaat A.S./Bestepelar-Ankara/Turkey | 6934 | 7461 | 2011-04-26 | 2013-04-04 | 2011-12-23 | 2013-04-04 | 100 | -18000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104210 | Helicopter Apron (Mazar-E-Sharif) | 2010-08-23 | 2011-04-08 | Yuksel Insaat A.S./Bestepelar-Ankara/Turkey | 22607 | 22876 | 2011-04-26 | 2013-04-04 | 2011-12-23 | 2013-04-04 | 100 | -24000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104600 | SOF Helicopter Apron (Shindand) | 2010-11-19 | 2011-04-29 | Contrack International Inc/McLean/VA | 6834 | 7121 | 2011-04-29 | 2012-11-30 | 2012-01-31 | 2012-11-30 | 100 | -11000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104601 | SOF ISR Apron & Support Complex (Shindand) | 2010-11-19 | 2011-04-29 | Contrack International Inc/McLean/VA | 6083 | 6382 | 2011-04-29 | 2012-11-30 | 2012-01-31 | 2012-11-30 | 100 | -3700
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104650 | Munitions Storage Area (Shindand) | 2010-07-27 | 2010-09-29 | Road and Roof Construction Company (RRCC) | 9812 | 9601 | 2010-11-02 | 2012-11-30 | 2011-07-28 | 2012-11-30 | 100 | -8000
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104660 | ISR Apron (Shindand) | 2010-11-19 | 2011-04-29 | Contrack International Inc/McLean/VA | 21192 | 22252 | 2011-04-29 | 2012-11-30 | 2012-01-31 | 2012-11-30 | 100 | -26504
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU043002 | Consolidated Learning Center | 2010-07-06 | 2010-09-10 | The Ross Group | 10657 | 10918 | 2010-09-17 | 2012-10-09 | 2011-09-30 | 2013-06-21 | 100 | 19
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU053000 | Joint Intel Technical Training Facility, Ph 1 (TFI) | 2010-04-12 | 2010-08-16 | PBS&J Constructors, Inc. | 11390 | 12550 | 2010-10-13 | 2013-05-15 | 2011-06-01 | 2013-08-01 | 98 | 1611
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU053000 | Joint Intel Technical Training Facility, Ph 1 (TFI) | 2010-04-12 | 2013-04-19 | SDIC Constructors | 774 | 774 | 2010-10-13 | 2013-05-15 | 2011-06-01 | 2013-08-01 | 98 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU083001 | Student Dormitory (100 Room) | 2010-02-02 | 2010-06-18 | Triune Beck Joint Venture | 12721 | 13981 | 2010-08-24 | 2013-01-18 | 2011-07-01 | 2013-01-18 | 100 | 916
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083005 | Evasion, Conduct After Capture Training | 2009-12-04 | 2010-03-12 | Gideon Marshall Joint Venture | 5160 | 5131 | 2010-04-15 | 2011-08-24 | 2010-12-31 | 2013-04-09 | 100 | 1010
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083005 | Evasion, Conduct After Capture Training | 2009-12-04 | 2012-08-12 | JSR Incorporated | 234 | 234 | 2010-04-15 | 2011-08-24 | 2010-12-31 | 2013-04-09 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | Recruit Dormitory 2, Phase 2 | 2009-10-15 | 2010-04-20 | Martin Harris (M&H) Enterprises | 41573 | 42478 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2014-09-30 | 99 | -1467
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | Recruit Dormitory 2, Phase 2 | 2009-10-15 | 2011-05-31 | SB-Federal Program Integrators, NA Corp. | 6663 | 7250 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2014-09-30 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility | 2009-12-10 | 2010-02-11 | Lyda Swinerton | 23484 | 25544 | 2010-05-05 | 2012-10-31 | 2011-09-01 | 2013-08-28 | 99 | 650
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility | 2009-12-10 | 2010-06-11 | Telecomm Ductbank Contractor | 1409 | 1602 | 2010-05-05 | 2012-10-31 | 2011-09-01 | 2013-08-28 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | TUR | TURKEY | INCIRLIK AIR BASE ADANA | LJYC003006 | Consolidated Community Center | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | 7881 | 8180 | 2010-04-26 | 2014-09-06 | 2008-04-15 | 2014-07-08 | 13 | 930
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF100031 | Construct Maintenance Operations Center And Command Post | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | 1672 | 1710 | 2011-06-03 | 2013-09-30 | 2011-06-15 | 2013-09-30 | 84 | 2149
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF100120 | Construct SatCom Facility | 2010-10-28 | 2010-05-06 | Lakeshore Engineering Services, Inc. | 1137 | 1184 | 2011-06-03 | 2013-09-30 | 2011-09-15 | 2013-09-30 | 84 | 1690
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM043003 | F-22A Radar Cross Section Testing Facility | 2010-01-06 | 2010-05-27 | Okland Construction | 18401 | 18974 | 2010-06-29 | 2013-08-31 | 2011-12-22 | 2013-08-31 | 98 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | VA | VIRGINIA | AIR COMBAT COMMAND | WACC113220 | Runway (Sharana) | 2010-06-21 | 2010-09-10 | METAG Insaat Ticaret A.S. | 18251 | 17597 | 2010-10-16 | 2011-10-30 | 2011-10-30 | 2011-10-30 | 29 | 21677
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | MUHJ053008 | West & Lasalle Gates Force Protection/Access | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | 7186 | 7690 | 2010-08-04 | 2013-07-19 | 2011-04-28 | 2013-08-09 | 80 | 1303
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ060074 | Refueling Vehicle Maintenance Facility | 2010-07-15 | 2010-09-08 | Doyon Project Services LLC, Washington | 3428 | 3533 | 2010-10-14 | 2012-07-17 | 2012-02-28 | 2012-10-19 | 100 | -5
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ920012P1 | Sere Force Support Complex, Phase 1 | 2010-07-19 | 2010-09-24 | Yost-Moody-Pugh, Spokane, WA | 7857 | 8473 | 2010-10-18 | 2012-06-28 | 2012-02-28 | 2013-05-06 | 100 | -931
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | WY | WYOMING | FRANCIS E WARREN AIR FORCE BASE | GHLN053010 | ADAL Missile Service Complex | 2009-10-16 | 2010-03-11 | Lindgren RF Enclosures | 329 | 351 | 2010-04-07 | 2011-11-10 | 2011-09-19 | 2013-08-30 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Major construction | WY | WYOMING | FRANCIS E WARREN AIR FORCE BASE | GHLN053010 | ADAL Missile Service Complex | 2009-10-16 | 2010-03-11 | RSCI | 4944 | 5324 | 2010-04-07 | 2011-11-10 | 2011-09-19 | 2013-08-30 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ104126 | Improve Family Housing, Ph 10 | 2010-04-21 | 2010-08-10 | Obayashi Corporation | 54864 | 56203 | 2010-10-01 | 2014-02-15 | 2012-10-01 | 2014-04-01 | 78 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ104126 | Improve Family Housing, Ph 10 | 2010-04-21 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 270 | 270 | 2010-10-01 | 2014-02-15 | 2012-10-01 | 2014-04-01 | 78 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH103046 | Construct Network Control Center | 2012-01-31 | 2012-05-18 | CH2M Hill | 1274 | 1274 | 2012-06-07 | 2013-07-08 | 2012-07-27 | 2013-07-08 | 46 | 1539
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH103051 | Install Area Lighting On Bravo Apron | 2012-01-31 | 2012-05-18 | CH2MHill | 1704 | 1704 | 2012-06-07 | 2013-06-27 | 2012-07-27 | 2013-06-27 | 91 | 1932
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | AFG | AFGHANISTAN | KANDAHAR AB | LYAV100053 | MQ 1/9 Operations And Maintenance Admin Facility | 2012-01-02 | 2012-03-15 | Entire-Ashna-Vertex JV | 1026 | 1026 | 2012-04-14 | 2013-04-29 | 2012-07-13 | 2013-04-29 | 100 | 1180
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT073008 | Construct Military Working Dog & Supporting Facility | 2011-07-25 | 2011-09-28 | IE PACIFIC INC | 1620 | 1620 | 2011-10-20 | 2012-09-28 | 2012-09-10 | 2013-02-22 | 87 | 1884
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA093001 | Military Working Dog Kennels | 2010-08-19 | 2010-11-01 | Barlovento, LLC; Dothan AL | 1772 | 1806 | 2010-12-09 | 2012-05-04 | 2011-12-02 | 2012-12-10 | 100 | 1920
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | BRVN060310 | Operations Town Dining Facility | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 936 | 936 | 2011-12-19 | 2013-10-31 | 2012-12-31 | 2013-10-31 | 68 | 1098
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | BRVN100460 | Construct Flightline Fire Station | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 1243 | 1243 | 2011-12-19 | 2013-10-31 | 2012-12-31 | 2013-10-31 | 67 | 1397
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG101003 | Cnst MLA & MHU Trailer Storage Facility | 2011-06-17 | 2011-09-23 | Carlson Constructors Corp | 1750 | 1812 | 2011-10-26 | 2013-01-23 | 2012-08-17 | 2013-01-23 | 100 | 1922
2013-07-31 | 2013-08-06 | 2010 | Air Force active | Minor construction | WA | WASHINGTON | MCCHORD AIR FORCE BASE | PQWY093000 | Satellite Fire Station | 2010-05-07 | 2010-08-19 | Garco Construction | 1824 | 1824 | 2010-09-02 | 2011-09-22 | 2011-04-22 | 2011-09-29 | 99 | 1899
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | CA | CALIFORNIA | FRESNO YOSEMITE INTERNATIONAL ANG | HAYW049133 | Replace Squadron Operations Facility | 2010-12-10 | 2011-02-22 | J.I. Garcia | 8437 | 10421 | 2011-04-14 | 2013-09-30 | 2012-07-12 | 2013-09-30 | 73 | 410
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | CA | CALIFORNIA | SOUTH CALIFORNIA LOGISTICS AIRPORT | SCLA069165 | TFI - Predator Beddown - FTU/LRE Site | 2010-01-22 | 2010-08-02 | PAC West Builders | 4628 | 6404 | 2010-08-30 | 2012-03-13 | 2011-08-30 | 2012-04-30 | 99 | -2012
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU019119 | ADAL Weapon Release Facility | 2010-05-28 | 2010-09-23 | Tower One Construction Company | 3025 | 3646 | 2010-10-27 | 2012-02-09 | 2011-08-23 | 2013-08-14 | 99 | -441
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | CT | CONNECTICUT | BRADLEY INTERNATIONAL AIRPORT | CEKT079036 | TFI - cNAF Beddown - Upgrade Facilities | 2012-02-21 | 2010-05-26 | LUPACHINO & SALVATORE, INC. | 6107 | 6764 | 2010-06-21 | 2013-09-27 | 2011-06-25 | 2013-09-27 | 100 | -2236
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069208 | TFI - F-22 LO/Composite Repair Facility | 2009-12-02 | 2010-04-20 | SU MO-NAN, LLC | 23250 | 27109 | 2010-05-24 | 2012-04-19 | 2011-12-25 | 2012-05-15 | 99 | 426
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109501 | TFI - F-22 Parking Apron and Taxiways | 2012-01-04 | 2012-07-16 | Cutting Edge | 2032 | 2182 | 2012-08-08 | 2013-07-30 | 2013-08-08 | 2013-08-31 | 75 | 3945
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | IL | ILLINOIS | ABRAHAM LINCOLN CAPITAL AIRPORT | DCFT039115 | Security Improvements - Relocate Base Entrance | 2010-05-13 | 2010-09-17 | Perry Broughton Trucking and Excavating | 3391 | 3668 | 2010-10-26 | 2012-07-30 | 2010-10-26 | 2012-07-30 | 100 | 668
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | IL | ILLINOIS | GENERAL WAYNE A. DOWNING PEORIA IAP(ANG) | JLQN069160 | Squadron Operations Facility | 2010-02-18 | 2010-06-21 | JM Industrial Supply, Inc./River City Construction | 9132 | 10262 | 2010-08-17 | 2012-07-02 | 2012-02-13 | 2012-06-30 | 100 | 1122
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | IA | IOWA | DES MOINES INTERNATIONAL AIRPORT | FFAN029023 | Add to and Alter Security Forces Facility | 2010-08-06 | 2010-09-24 | Neuman Brothers | 4014 | 4247 | 2010-10-01 | 2011-09-11 | 2011-06-28 | 2012-07-27 | 100 | -353
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE089032 | TFI - Upgrade DCGS Facilities | 2010-05-11 | 2010-08-04 | Key Construction Company | 8223 | 9068 | 2010-08-16 | 2011-11-21 | 2011-08-16 | 2013-08-31 | 99 | 66
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | ME | MAINE | BANGOR INTERNATIONAL AIRPORT | FKNN089019 | Replace Aircraft Maintenance Hangar and Shops | 2009-09-29 | 2010-05-12 | Sheridan Corp | 15064 | 17786 | 2010-11-05 | 2012-08-01 | 2012-11-24 | 2013-03-28 | 98 | -9592
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MD | MARYLAND | JOINT BASE ANDREWS | AJXF049104 | Replace Munitions Maintenance and Storage Complex | 2010-02-03 | 2011-04-15 | Charter Environmental, Inc. | 14521 | 15179 | 2010-09-13 | 2013-02-26 | 2010-11-12 | 2013-07-28 | 78 | 1662
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MA | MASSACHUSETTS | BARNES MUNICIPAL AIRPORT | AXQD089070 | Aircraft Ready Shelters | 2010-08-02 | 2010-09-30 | Maron Construction | 5428 | 6534 | 2010-10-26 | 2012-12-31 | 2011-10-26 | 2013-01-31 | 100 | -1314
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN019136 | Replace Ops and Training /ADAL DGS | 2010-07-16 | 2010-09-27 | P&S Construction | 2487 | 3113 | 2010-11-01 | 2013-06-17 | 2011-10-27 | 2013-07-31 | 31 | -1000
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN019136 | Replace Ops and Training /ADAL DGS | 2010-07-22 | 2010-09-30 | K-CON | 6752 | 8938 | 2010-11-01 | 2013-09-30 | 2011-12-29 | 2013-10-11 | 31 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MI | MICHIGAN | ALPENA COUNTY REGIONAL AIRPORT | TDVG029066 | Replace Troop Training Quarters | 2010-06-18 | 2010-08-24 | B&B General Contracting Inc. | 6793 | 7378 | 2010-08-30 | 2012-01-23 | 2011-08-15 | 2013-05-31 | 100 | -1272
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MI | MICHIGAN | SELFRIDGE AIR NATIONAL GUARD BASE | VGLZ059023 | Add to and Alter Squadron Operations Facility | 2010-08-20 | 2010-09-28 | Rock Industries, Inc. | 5698 | 6709 | 2010-11-15 | 2012-11-20 | 2012-01-10 | 2013-04-12 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MI | MICHIGAN | W. K. KELLOGG AIRPORT | MBMV079055 | TFI - cNAF Beddown - Upgrade Bulding 6923 | 2010-08-26 | 2010-09-30 | Beckering Advisors, Inc. | 8851 | 10730 | 2010-10-17 | 2012-04-06 | 2012-04-17 | 2012-10-30 | 99 | -1561
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MN | MINNESOTA | MINNEAPOLIS ST PAUL INTL AIRPORT | QJKL089207 | Alter STARBASE Facility | 2010-09-01 | 2010-09-29 | L.S. Black Constructors, Inc. | 1775 | 2177 | 2010-11-08 | 2011-10-17 | 2011-08-08 | 2012-03-01 | 100 | 277
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MS | MISSISSIPPI | GULFPORT - BILOXI REGIONAL AIRPORT | JTVE099057 | Force Protection Measures - Relocate Base Entrance | 2012-08-15 | 2012-09-27 | Gottfried Contracting | 3823 | 3925 | 2012-10-10 | 2013-09-01 | 2013-06-24 | 2013-09-01 | 1 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB099003 | Add to Fire Station | 2010-03-01 | 2010-07-25 | Lee Grover Constrution | 5709 | 6547 | 2010-08-04 | 2013-07-02 | 2011-07-30 | 2013-07-31 | 75 | -2629
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB079069 | Joint Forces Operations Center - ANG Share | 2009-11-13 | 2010-02-17 | Hausmann Construction, Inc. | 1306 | 1500 | 2010-02-18 | 2012-09-17 | 2011-09-16 | 2012-09-17 | 95 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | NV | NEVADA | RENO-TAHOE INTERNATIONAL AIRPORT | UCTL919637 | Replace Fire Station | 2010-07-27 | 2010-09-07 | Gilbane Building Company | 9263 | 10246 | 2010-09-23 | 2011-12-25 | 2012-03-21 | 2012-09-30 | 99 | -40
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | NH | NEW HAMPSHIRE | PEASE INTERNATIONAL TRADEPORT ANG | SZCQ089023 | Replace Squadron Operations Facilities | 2011-03-09 | 2011-09-19 | NUTMEG Companies, Inc. | 10752 | 11802 | 2011-10-24 | 2013-08-15 | 2013-02-15 | 2013-09-13 | 87 | 2000
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | NJ | NEW JERSEY | JOINT BASE MCGUIRE-DIX-LAKEHURST | PTFL029107 | Replace Base Civil Engineer Complex | 2010-07-14 | 2010-09-28 | Puente Construction Enterprises Inc | 6573 | 8308 | 2010-10-21 | 2012-05-07 | 2012-04-20 | 2013-07-05 | 99 | -950
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATION | FPBB069168 | Reaper LRE Beddown | 2012-07-27 | 2012-10-17 | Black Horse Group | 3155 | 3205 | 2012-10-17 | 2013-07-31 | 2013-11-11 | 2013-07-31 | 82 | 555
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | OH | OHIO | MANSFIELD LAHM AIRPORT | PBXP069219 | TFI - RED HORSE Squadron Beddown | 2009-10-15 | 2010-04-12 | Butcher and Baeker Construction | 6368 | 6862 | 2010-05-17 | 2011-09-30 | 2011-06-21 | 2012-02-03 | 100 | -4737
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD929753 | Replace Munitions Storage Complex (ASA) | 2010-07-24 | 2011-04-08 | Penick-Nordic | 10533 | 11857 | 2011-05-24 | 2012-06-15 | 2012-05-07 | 2012-12-31 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | OK | OKLAHOMA | WILL ROGERS WORLD AIRPORT | YZEU069106 | TFI - ASOS Beddown | 2010-02-05 | 2010-05-06 | Magnum Construction | 4808 | 5206 | 2010-05-05 | 2012-04-18 | 2011-04-30 | 2012-12-04 | 100 | -1894
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | OR | OREGON | KLAMATH FALLS AIRPORT-KINGSLEY FIELD | KJAQ029041 | Replace Security Forces Facilities | 2010-05-28 | 2010-09-29 | S&B James | 5599 | 5842 | 2010-11-03 | 2012-06-05 | 2012-05-04 | 2012-10-12 | 100 | -158
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | SC | SOUTH CAROLINA | MCENTIRE JOINT NATIONAL GUARD BASE | PSTE089005 | Joint Forces Headquarters - ANG Portion | 2010-05-28 | 2010-08-31 | IKAHANA/CHOATE | 1300 | 1300 | 2010-08-31 | 2012-09-24 | 2011-08-26 | 2013-03-02 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC059827 | Add to Munitions Maintenance Complex, | 2010-08-17 | 2010-09-30 | Sunkota Construction, Inc. | 1054 | 1113 | 2010-10-21 | 2011-08-05 | 2011-07-23 | 2012-01-06 | 100 | -15
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC069080 | Addition to Above Ground Multi-Cube Magazine Storage | 2010-08-17 | 2010-09-30 | Sunkota Construction, Inc. | 964 | 1011 | 2010-10-21 | 2011-08-05 | 2011-07-23 | 2012-01-06 | 100 | -262
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | TN | TENNESSEE | MEMPHIS INTERNATIONAL AIRPORT | PYKL009136 | Base Civil Engineer Maintenance and Training Facilities | 2010-07-14 | 2010-09-21 | Chris Wood Construction Co, Inc. | 6069 | 7351 | 2010-10-19 | 2012-10-31 | 2012-10-18 | 2013-02-28 | 97 | -2180
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM972002 | Add to and Alter Avionics/ECM Shop | 2010-07-15 | 2010-09-20 | Triune-Beck JV | 1890 | 1986 | 2011-09-01 | 2012-09-20 | 2011-10-28 | 2012-10-15 | 100 | -14
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | TX | TEXAS | KELLY FIELD ANNEX | KELL089001 | Add/Alt Aircraft Maintenance Shops | 2011-07-18 | 2010-09-30 | FA Nunnelly | 4546 | 4957 | 2010-12-17 | 2013-01-23 | 2011-10-30 | 2013-04-01 | 99 | -1010
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | VT | VERMONT | BURLINGTON INTERNATIONAL AIRPORT | CURZ029000 | Add to and Alter Fire Crash/Rescue Station | 2010-06-12 | 2010-09-27 | EF Wall & Associates, Inc; | 4741 | 5044 | 2010-10-15 | 2012-01-10 | 2011-08-11 | 2012-01-10 | 100 | -956
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | WV | WEST VIRGINIA | EWVRA-SHEPHERD FIELD | PJVY069225 | C-5 Aircraft Upgrade Taxiways | 2010-06-09 | 2010-09-24 | Atlantic Contracting & Material Co., INC | 8080 | 9469 | 2010-10-05 | 2012-08-17 | 2011-11-25 | 2012-09-28 | 100 | -7802
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | WI | WISCONSIN | GENERAL MITCHELL INTERNATIONAL AIRPORT | HTUV039088 | Add to and Alter KC-135 Corrosion Control Hangar | 2009-11-25 | 2010-08-17 | KPH | 3805 | 4215 | 2010-09-13 | 2012-01-31 | 2011-06-10 | 2012-10-22 | 100 | -782
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Major construction | WY | WYOMING | CHEYENNE REGIONAL AIRPORT | DPEZ019148A | Add to Squadron Operations | 2011-02-04 | 2011-06-02 | Various Contractors | 975 | 1303 | 2011-06-01 | 2011-12-01 | 2011-11-28 | 2012-11-30 | 89 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW009192 | Add to Communications Training Facility | 2012-11-07 | 2012-12-27 | G2 Construction | 1448 | 1530 | 2013-01-24 | 2013-10-15 | 2014-01-24 | 2013-10-31 | 16 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | FL | FLORIDA | CAMP BLANDING MILITARY RESERVATION | CYQL099005 | DRBS Storage Facility | 2012-10-01 | 2013-02-11 | Sweat, LLC | 1143 | 1143 | 2013-02-11 | 2014-02-10 | 2013-11-08 | 2014-02-10 | 5 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU109096 | CRTC Squadron Operation Addition | 2012-11-13 | 2012-12-27 | Holland and Holland, Inc. | 1209 | 1327 | 2013-01-17 | 2014-01-31 | 2014-01-17 | 2014-02-28 | 40 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY099016 | DRBS Storage Facility | 2011-07-15 | 2011-09-29 | Serrano Construction and Development | 1643 | 1777 | 2011-09-29 | 2013-04-30 | 2012-08-23 | 2013-04-30 | 96 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | IN | INDIANA | FORT WAYNE INTERNATIONAL AIRPORT | ATQZ099062 | A-10 Flight Simulator Addition | 2011-09-15 | 2011-04-19 | Patterson Horth | 1028 | 1146 | 2011-05-20 | 2012-02-15 | 2012-03-15 | 2012-02-15 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | MD | MARYLAND | MARTIN STATE AIRPORT | PJMS119034 | A10 Flight Simulator Facility | 2012-11-01 | 2013-01-08 | SAF, Inc. | 1818 | 1898 | 2013-01-24 | 2014-01-31 | 2014-03-26 | 2014-01-31 | 33 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | MA | MASSACHUSETTS | HANSCOM AFB | MXRD089075 | Joint Forces Operations Center- ANG Share | 2010-02-10 | 2010-05-27 | CTA Constr | 1500 | 1500 | 2010-05-27 | 2012-10-01 | 2010-05-27 | 2011-11-29 | 100 | 1500
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | MI | MICHIGAN | ALPENA COUNTY REGIONAL AIRPORT | TDVG072909A | Replace Classroom Training Facilities | 2012-11-15 | 2012-12-27 | Meridan Contracting Services, LLC | 1437 | 1531 | 2013-03-25 | 2013-11-16 | 2013-08-24 | 2013-11-16 | 32 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB109082 | Alter Base Entry Complex | 2012-10-30 | 2012-12-27 | American Contracting, LLC | 1297 | 1337 | 2013-01-23 | 2013-11-20 | 2014-01-23 | 2013-11-20 | 11 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | NH | NEW HAMPSHIRE | PEASE INTERNATIONAL TRADEPORT ANG | SZCQ119041 | Construct DRBS Storage Facility | 2012-09-28 | 2012-12-27 | Cornerstone Construction Service LLC | 1604 | 1604 | 2013-03-01 | 2013-10-27 | 2013-10-23 | 2013-10-27 | 13 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | NJ | NEW JERSEY | ATLANTIC CITY INTERNATIONAL AIRPORT | AQRC059017 | Munitions Administrative Facility | 2010-07-16 | 2010-09-29 | Ranco Construction Inc | 1510 | 1607 | 2010-10-25 | 2011-11-25 | 2011-10-25 | 2011-11-25 | 98 | 1607
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP089051 | PRIME BEEF "S Teams" Beddown | 2010-06-01 | 2010-09-28 | D.E. Walker Constructing Inc | 1778 | 1970 | 2010-11-22 | 2012-07-12 | 2011-11-22 | 2012-07-12 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | OH | OHIO | MANSFIELD LAHM AIRPORT | PBXP099056 | DRBS Storage Facility | 2010-09-01 | 2010-09-30 | Blue Scope Construction | 650 | 760 | 2010-09-30 | 2011-08-02 | 2011-04-28 | 2012-01-17 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD009206 | Multi-Use Instructional Facility | 2010-08-30 | 2010-09-21 | Rock Industries | 1614 | 1730 | 2010-10-07 | 2011-12-29 | 2011-10-07 | 2012-03-01 | 100 | 1730
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | OH | OHIO | ZANESVILLE AIR GUARD STATION | ZRVL099068 | Supply Warehouse | 2010-09-17 | 2010-10-27 | Henderson Contractors Corporation | 938 | 1233 | 2010-11-04 | 2012-08-31 | 2011-08-01 | 2013-03-29 | 100 | 1225
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | TN | TENNESSEE | NASHVILLE INTERNATIONAL AIRPORT | BKTZ139025 | Convert RPA Interim SCIF, B720 | 2013-05-08 | 2013-06-20 | Codell Construction Company | 1651 | 1705 | 2013-07-01 | 2014-03-22 | 2014-04-16 | 2014-03-22 | 0 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM109901 | Add to Civil Engineering Facility | 2012-08-19 | 2012-11-21 | Triune-Beck JV | 1479 | 1529 | 2013-02-12 | 2014-02-14 | 2014-06-03 | 2014-02-14 | 10 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM119026 | Multi Use Training Facility | 2012-08-19 | 2012-11-21 | Tribune-Beck JV | 1697 | 1747 | 2013-02-12 | 2014-02-14 | 2013-11-30 | 2014-02-14 | 10 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | TX | TEXAS | ELLINGTON FIELD | FWJH079112 | Munitions Maintenance Shop | 2010-04-30 | 2010-09-28 | All American Brothers | 1762 | 1890 | 2010-10-06 | 2012-01-30 | 2011-04-04 | 2012-01-05 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | TX | TEXAS | KELLY FIELD ANNEX | KELL099067 | F-16 Mission Training Center (Flight Sim) Facility | 2010-05-13 | 2011-09-28 | HJD Capital Electric, Inc | 1578 | 1685 | 2011-09-30 | 2013-02-28 | 2012-09-29 | 2013-02-28 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | VA | VIRGINIA | CAMP PENDLETON MILITARY RESERVATION | ERVD099006 | DRBS Storage Facility | 2011-07-15 | 2011-09-23 | Vanguard Contractors | 854 | 865 | 2012-03-12 | 2012-04-30 | 2012-09-08 | 2012-05-31 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force NG | Minor construction | WV | WEST VIRGINIA | YEAGER AIRPORT | LYBH079028 | BCE Pavements and Grounds Facility | 2013-02-19 | 2013-06-14 | Wycliffe Enterprises, Inc | 899 | 899 | 2013-07-09 | 2014-04-05 | 2014-04-05 | 2014-03-11 | 0 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG050237 | Small Arms Firing Range | 2010-07-21 | 2010-09-13 | P&S Construction, Inc. | 8578 | 9092 | 2010-10-14 | 2013-06-07 | 2012-02-16 | 2013-06-07 | 98 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT089021 | C-5 Squadron Operations And Aircraft Maintenance Facility | 2010-07-21 | 2010-09-20 | Solpac | 6402 | 7049 | 2010-09-20 | 2012-07-19 | 2011-09-19 | 2012-05-15 | 99 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | FL | FLORIDA | HOMESTEAD AIR RESERVE BASE | KYJM049010 | Troop Feeding/Community Activity Center | 2010-07-26 | 2010-09-21 | JCI | 5117 | 5647 | 2010-12-29 | 2013-11-01 | 2012-05-22 | 2014-02-01 | 98 | -539
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT033002 | Iso Dock Extension Hangar 630 | 2010-07-23 | 2010-09-27 | Sea Tech of the Florida Keys | 2471 | 3346 | 2011-01-04 | 2013-10-31 | 2011-09-15 | 2013-10-31 | 88 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ023012 | Deployment Readiness And Training Center | 2010-06-17 | 2010-08-31 | EDT Constructors | 5431 | 5669 | 2010-11-02 | 2012-12-06 | 2012-03-06 | 2012-12-06 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | MS | MISSISSIPPI | KEESLER AIR FORCE BASE | MAHG063003 | Aerial Port Squadron Facility | 2010-03-30 | 2010-08-09 | W. G. Yates & Sons Const. Co. | 6827 | 8077 | 2010-08-26 | 2012-08-16 | 2012-03-01 | 2013-01-08 | 100 | 0
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | NY | NEW YORK | NIAGARA FALLS IAP-AIR RESERVE STATION | RVKQ109091 | Indoor Small Arms Range | 2010-07-16 | 2010-09-22 | R.B. Mac Construction, Inc. | 6236 | 6617 | 2010-11-05 | 2012-10-10 | 2011-11-04 | 2012-10-10 | 99 | 1323
2013-07-31 | 2013-08-06 | 2010 | Air Force res | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | KELL043010A | Wing Training And Readiness Facility | 2010-07-26 | 2010-09-30 | EDT Construction | 5627 | 5601 | 2010-11-02 | 2012-10-17 | 2011-09-30 | 2012-10-15 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH110101 | Consolidated Rigging Facility | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest, JV, LLC | 8364 | 9839 | 2011-08-10 | 2013-11-25 | 2012-03-14 | 2013-11-25 | 39 | 1313
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH110103 | Medevac Ramp Expansion/ Fire Station | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest JV, LLC | 9537 | 10755 | 2011-08-10 | 2013-12-31 | 2012-03-14 | 2013-12-31 | 25 | 994
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH110104 | Fighter Hangar | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest IV, LLC | 8305 | 10417 | 2011-08-10 | 2013-12-01 | 2012-03-14 | 2013-12-01 | 61 | 3837
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | HERAT | KLZT103000 | SOF Helicopter Apron | 2012-01-02 | 2012-03-05 | State Corps Limited/Kabul/Afghanistan | 6920 | 305 | 2013-02-13 | 2013-09-30 | 2012-12-21 | 2013-09-30 | 2 | 8200
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AL | ALABAMA | MAXWELL AIR FORCE BASE | PNQS983126 | ADAL Air University Library | 2010-12-07 | 2011-06-14 | Southeast Cherokee Construction | 10211 | 11012 | 2011-07-18 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 92 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW083008 | Repair Central Heat And Power Plant Boiler | 2010-07-12 | 2011-06-02 | Haskell Corporation | 26981 | 26984 | 2011-06-17 | 2015-02-26 | 2014-11-24 | 2015-02-26 | 40 | 2000
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB073012 | F-22 Add/Alter Weapons Release Systems Shop & Ame (TFI) | 2010-09-29 | 2011-09-29 | Bristol Design Build Services, LLC | 5608 | 6213 | 2011-10-12 | 2013-08-13 | 2012-07-23 | 2013-08-13 | 96 | 458
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB123201 | Add/Alter Air Support Operations Squadron Training Facility | 2010-08-10 | 2011-07-19 | Tunista | 4237 | 4202 | 2011-07-29 | 2012-10-11 | 2012-01-20 | 2012-10-11 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV063501 | AMARG Hangar | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | 22282 | 22262 | 2011-09-07 | 2014-01-14 | 2013-03-11 | 2014-01-14 | 18 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV103005 | HC-130J Parts Store | 2011-05-06 | 2011-09-28 | Benchmark INC, DBA Cobblestone/ Las Vegas/ NV | 5195 | 5258 | 2011-11-17 | 2013-10-17 | 2012-07-30 | 2013-10-17 | 41 | 423
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV113002 | HC-130J Aerial Cargo Facility | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | 7223 | 7223 | 2011-11-09 | 2013-10-16 | 2012-09-21 | 2013-10-16 | 72 | -2491
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV113007 | HC-130 AGE Maintenance Facility | 2010-12-03 | 2011-06-06 | Benchmark Contr DBA Cobblestone Constr Las Vegas NV | 4078 | 4256 | 2011-07-05 | 2013-06-21 | 2012-03-12 | 2013-06-21 | 92 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093000 | F-35 Academic Training Center | 2012-04-18 | 2012-08-30 | Archer Western Contractors | 43347 | 44182 | 2012-11-05 | 2014-06-07 | 2013-06-28 | 2014-07-08 | 16 | -2434
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093001 | F-35 Squadron Ops Facility | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | 9109 | 9225 | 2012-10-09 | 2013-12-10 | 2013-06-28 | 2014-01-26 | 57 | 273
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU073004 | Security Forces Operations Facility | 2010-09-14 | 2011-06-01 | Roche Constructors, Inc. | 8274 | 8472 | 2011-07-05 | 2013-02-01 | 2011-06-24 | 2013-02-01 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA093005 | Raidrs Space Control Facility | 2010-11-12 | 2011-06-08 | Bryan Construction | 14284 | 14473 | 2011-06-08 | 2013-05-06 | 2012-08-17 | 2013-05-06 | 100 | -2269
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | CO | COLORADO | USAF ACADEMY | XQPZ084017 | Const Center For Character & Leadership Development | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | 24996 | 25164 | 2013-01-14 | 2014-10-10 | 2014-05-15 | 2014-10-10 | 11 | 1205
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT113001 | C-5M/C-17 Maintenance Training Facility, Ph 2 | 2011-03-09 | 2011-08-02 | Asset Group, Incorporated, Oklahoma City, Oklahoma | 2952 | 2950 | 2011-08-11 | 2013-09-27 | 2012-05-30 | 2013-10-09 | 78 | 127
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | DC | DISTRICT OF COLUMBIA | BOLLING AIR FORCE BASE | BXUR105000 | Joint Air Defense Operations Center | 2011-03-02 | 2011-08-05 | Sauer Inc. | 11978 | 12622 | 2011-08-05 | 2013-07-30 | 2012-02-29 | 2013-07-30 | 90 | 1783
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073908 | F-35 Fuel Cell Maintenance Hangar | 2010-10-06 | 2011-06-23 | Sauer Inc. | 6957 | 7164 | 2011-08-17 | 2013-08-30 | 2013-01-05 | 2013-08-30 | 90 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV023010 | Add to Visiting Quarters (24 Rm) | 2010-09-24 | 2011-06-15 | DWG & Associates, Inc. | 3516 | 3572 | 2011-08-11 | 2013-06-21 | 2012-01-10 | 2013-07-31 | 99 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV023013 | ADAL Special Operations School Facility | 2010-09-23 | 2011-06-20 | Barlovento, LLC | 4536 | 4868 | 2011-07-28 | 2013-03-01 | 2012-05-15 | 2013-07-02 | 100 | 121
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | Base Logistics Facility | 2010-09-22 | 2011-06-06 | Sauer Incorporated | 16031 | 16658 | 2011-07-19 | 2013-09-24 | 2011-07-25 | 2014-03-14 | 76 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | Base Logistics Facility | 2010-09-22 | 2011-08-29 | AEROSTAR ENVIRONMENTAL SERVICES, INC. | 192 | 192 | 2011-07-19 | 2013-09-24 | 2011-07-25 | 2014-03-14 | 76 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | Base Logistics Facility | 2010-09-22 | 2012-10-03 | STOA Architects | 163 | 163 | 2011-07-19 | 2013-09-24 | 2011-07-25 | 2014-03-14 | 76 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT053001 | Air Force Technical Applications Center | 2010-11-04 | 2011-06-03 | Hensel Phelps | 70619 | 73970 | 2011-07-06 | 2014-01-31 | 2015-06-30 | 2015-12-02 | 70 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | DEU | GERMANY | KAPAUN ADMINISTRATION ANX | TYFU083507R2 | Dormitory (128 Rm) | 2013-04-26 | 2011-09-16 | LBB (EBC AWD) | 17945 | 17945 | 2013-06-24 | 2015-07-15 | 2013-03-06 | 2015-02-09 | 1 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR073143 | UAS Satcom Relay Pads And Facility | 2011-08-12 | 2011-09-26 | Bidder C | 8352 | 8656 | 2011-12-15 | 2013-07-15 | 2012-12-30 | 2013-07-05 | 97 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR083001 | Deicing Fluid Storage & Dispensing Facility | 2012-05-10 | 2011-09-02 | LBB | 2671 | 2671 | 2012-10-31 | 2013-09-30 | 2011-08-17 | 2013-09-06 | 43 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR123063 | C-130J Flight Simulator Facility | 2013-08-02 | 2011-09-02 | LBB (EBC AWD) | 7024 | 7024 | 2013-11-20 | 2015-01-28 | 2012-04-29 | 2014-12-26 | 1 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | DEU | GERMANY | VILSECK | VILS093001 | Air Support Operations Squadron (ASOS) Complex | 2011-07-01 | 2011-09-23 | Mickan Amber | 10734 | 10940 | 2011-10-05 | 2013-05-04 | 2013-01-13 | 2013-04-04 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY113007 | Guam Strike Ops Group & Tanker Task Force Renovation (TFI) | 2010-09-17 | 2011-09-12 | P & S Construction | 8627 | 9013 | 2011-09-27 | 2013-12-04 | 2012-08-13 | 2013-12-04 | 93 | 629
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY336509 | Guam Strike South Ramp Utilities Phase 1 (TFI) | 2010-09-17 | 2011-07-28 | P & S Construction | 9582 | 9547 | 2011-08-18 | 2013-09-09 | 2013-01-30 | 2013-09-09 | 95 | -1369
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW091006 | PRTC - Red Horse Headquarters/Engineering Facility | 2010-08-18 | 2011-06-07 | Overland Corporation | 6538 | 7220 | 2011-06-30 | 2013-02-27 | 2012-10-09 | 2013-04-25 | 100 | 372
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW123002 | PRTC - Combat Communications Operations Facility | 2010-08-13 | 2011-06-06 | Guam Pacific International, LLC | 7548 | 7530 | 2011-06-30 | 2012-11-23 | 2012-11-23 | 2012-12-21 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | ITA | ITALY | AVIANO AIR BASE | ASHE083011 | Air Support Operations Squadron (ASOS) Facility | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | 7174 | 7201 | 2011-12-15 | 2014-03-31 | 2013-06-06 | 2014-03-01 | 35 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | ITA | ITALY | AVIANO AIR BASE | ASHE123000 | Dormitory (144 Rm) | 2011-02-14 | 2011-07-28 | A.T.I. TACOSE S.c.a.r.l. | 13672 | 13768 | 2011-10-11 | 2013-09-30 | 2013-01-13 | 2013-08-30 | 80 | -247
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | KOR | KOREA | KUNSAN AIR BASE | MLWR093183 | Construct Dmt Flight Simulator Facility | 2010-08-18 | 2011-07-07 | Kum Sung Construction Co., Ltd | 6568 | 6816 | 2011-07-07 | 2013-03-06 | 2012-06-29 | 2014-01-31 | 98 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | LA | LOUISIANA | BARKSDALE AIR FORCE BASE | AWUB025502 | Weapons Load Crew Training Facility | 2010-10-22 | 2011-08-03 | Pacific - Tech - Sauer JV | 15903 | 17146 | 2011-08-03 | 2013-11-14 | 2013-01-28 | 2013-11-14 | 40 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NV | NEVADA | CREECH AIR FORCE BASE | LKTC113102 | UAS Airfield Fire/Crash Rescue Station | 2010-12-10 | 2011-06-29 | Jaynes Corporation | 7345 | 7423 | 2011-09-02 | 2013-11-15 | 2013-03-01 | 2013-11-15 | 49 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF093004 | F-35A Maintenance Hangar/AMU | 2011-03-23 | 2011-09-15 | Straub Construction, Inc | 20049 | 20517 | 2011-11-09 | 2014-01-15 | 2013-02-06 | 2014-01-15 | 79 | -3071
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103002 | F-35 Add/Alter 422 Test Evaluation Squadron Facility | 2010-01-07 | 2011-07-25 | Teehee-Straub JV | 5912 | 6773 | 2011-09-14 | 2013-05-01 | 2012-08-01 | 2013-05-29 | 100 | 747
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103007 | F-35 Flight Simulator Facility | 2010-11-18 | 2011-07-27 | Swinerton Builders | 8725 | 9089 | 2011-09-19 | 2013-05-20 | 2012-08-01 | 2013-05-20 | 100 | -2887
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103008 | F-35A Add/Alter Flight Test Instrumentation Facility | 2011-01-07 | 2011-08-02 | Power Services Inc. | 1508 | 1538 | 2011-09-09 | 2012-09-17 | 2012-02-02 | 2012-11-30 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NJ | NEW JERSEY | MCGUIRE AIR FORCE BASE | PTFL063000 | Base Ops/Command Post Facility (TFI) | 2010-12-08 | 2011-06-30 | Marco Builders, Inc | 6714 | 6845 | 2011-07-30 | 2013-05-17 | 2012-01-30 | 2013-06-14 | 99 | -127
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NJ | NEW JERSEY | MCGUIRE AIR FORCE BASE | PTFL083003 | Dormitory (120 Room) | 2010-12-08 | 2011-08-04 | Ranco Construction Inc | 13772 | 13893 | 2011-10-19 | 2013-09-16 | 2012-05-30 | 2013-08-09 | 80 | -2921
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073005 | Dormitory (96 Rm) | 2011-10-07 | 2012-02-15 | Charpie Korte Builders, LLC | 12413 | 12413 | 2012-04-19 | 2013-10-11 | 2012-07-02 | 2013-10-11 | 84 | -121
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ093004 | UAS Squadron Ops Facility | 2011-04-27 | 2011-10-11 | Speegle Construction Inc | 13126 | 13126 | 2012-01-10 | 2014-03-28 | 2013-01-18 | 2014-03-28 | 60 | -4806
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD093013 | UAS Add/Alter Maintenance Hangar | 2011-06-22 | 2011-09-13 | Candelaria Corporation | 10254 | 10254 | 2011-10-12 | 2013-12-12 | 2012-07-02 | 2013-12-12 | 73 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD093016 | UAS Maintenance Hangar | 2011-07-29 | 2011-09-29 | Hensel Phelps Construction Company | 19498 | 19711 | 2011-11-03 | 2013-11-22 | 2013-01-18 | 2013-11-22 | 90 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV053114A | Armament Shop | 2011-07-13 | 2011-09-23 | K.L. House | 3548 | 3548 | 2011-11-09 | 2013-09-09 | 2012-01-26 | 2013-07-31 | 95 | -1178
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV083114 | H/MC-130 Fuel System Maintenance Facility | 2011-02-11 | 2011-09-23 | K.L House | 11178 | 11596 | 2011-11-09 | 2013-09-09 | 2012-05-01 | 2013-07-31 | 92 | -737
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV083118 | Aerial Delivery Addition | 2011-07-21 | 2011-09-16 | TLW | 3036 | 3180 | 2011-10-11 | 2012-11-26 | 2011-05-26 | 2012-11-09 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATON | WACC073020 | 20th Air Support Operations Squadron Complex | 2010-10-21 | 2011-07-29 | Vetco Contracting Services, LLC | 15197 | 15223 | 2011-08-09 | 2013-02-15 | 2012-07-13 | 2013-02-15 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF012002 | Control Tower/Base Operations Facility | 2010-11-23 | 2011-06-06 | Mason & Hanger, Inc. | 14560 | 14886 | 2011-08-15 | 2013-06-18 | 2012-05-01 | 2013-07-31 | 92 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK083003B | Upgrade Building 3001 Infrastructure, Ph III | 2010-10-07 | 2011-07-22 | Korte Construction Company, St Louis, MO | 12687 | 13230 | 2011-07-22 | 2013-01-19 | 2012-06-01 | 2013-01-17 | 100 | 269
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | OMN | OMAN | AL MUSANAH AB | AMAB110001 | Airlift Ramp And Fuel Facilities | 2011-11-03 | 2012-05-10 | American Int'l Contractors, Inc. (AICI) | 36782 | 37020 | 2012-06-04 | 2014-04-15 | 2011-12-31 | 2014-04-29 | 62 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | OMN | OMAN | AL MUSANAH AB | AMAB110002 | Parallel Taxiway Extension | 2012-01-19 | 2012-07-05 | American Int'l Contractors, Inc. | 19348 | 19415 | 2012-08-06 | 2014-05-01 | 2013-11-01 | 2014-05-05 | 67 | 44245
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA073006B | Blatchford-Preston Complex, Phase III | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | 34177 | 34177 | 2012-03-26 | 2014-05-15 | 2013-03-31 | 2014-05-15 | 5 | 1390
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | 40848 | 40848 | 2013-08-07 | 2015-10-16 | 2013-08-15 | 2015-09-16 | 1 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA113001 | Theater Communications Facility | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | 9913 | 9913 | 2012-05-02 | 2014-02-12 | 2012-12-21 | 2014-02-12 | 4 | 12000
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA113031 | Munitions Storage Area Complex | 2011-12-21 | 2012-05-24 | American International Contractors, Inc | 42778 | 42778 | 2012-05-24 | 2014-01-14 | 2012-12-21 | 2014-01-14 | 71 | 48675
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | SC | SOUTH CAROLINA | CHARLESTON AIR FORCE BASE | DKFX913001P1 | Civil Engineer Complex (TFI) - Phase 1 | 2011-01-20 | 2011-06-03 | Sauer, Inc. | 11649 | 12334 | 2011-06-03 | 2013-05-17 | 2013-03-08 | 2013-06-18 | 95 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | TX | TEXAS | DYESS AIR FORCE BASE | FNWZ103010 | C-130J Add/Alter Flight Simulator Facility | 2011-02-28 | 2012-01-24 | Federal Program Integrators, L | 4464 | 4489 | 2012-03-06 | 2013-07-01 | 2012-09-28 | 2013-07-24 | 100 | 777
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | TX | TEXAS | FORT SAM HOUSTON | MPLS116414JB | One Company Fire Station | 2011-01-21 | 2011-06-17 | Blackhawk Ventures, LLC | 4845 | 4923 | 2011-07-08 | 2013-06-05 | 2012-01-31 | 2013-06-05 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R3 | Recruit Dormitories Phase 3 | 2010-12-06 | 2011-09-20 | Satterfield and Pontikes Construction (S&P) | 45885 | 46468 | 2011-11-01 | 2014-02-28 | 2012-12-28 | 2014-03-27 | 65 | 2000
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R3 | Recruit Dormitories Phase 3 | 2010-12-06 | 2012-08-09 | PSI | 6887 | 6900 | 2011-11-01 | 2014-02-28 | 2012-12-28 | 2014-03-27 | 65 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 | 2011-03-07 | 2011-07-08 | Kellogg Brown Root | 26018 | 26779 | 2011-08-29 | 2014-02-01 | 2013-06-30 | 2014-03-01 | 50 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS093737V | BMT Visitors Reception Center | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | 21500 | 21696 | 2011-09-30 | 2013-09-23 | 2011-07-01 | 2013-09-02 | 75 | 1369
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | GBR | UNITED KINGDOM | RAF MILDENHALL | QFQE063007 | Extend Taxiway Alpha | 2011-03-14 | 2011-09-29 | BALFOUR BEATTY | 9900 | 10211 | 2012-01-30 | 2013-05-17 | 2013-02-28 | 2013-05-17 | 100 | -1559
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | MUHJ063017 | F-22 Add/Alter Hangar Bay LO/CR Facility - TFI | 2010-10-15 | 2011-06-16 | Leebcor Services, LLC | 6595 | 6656 | 2011-11-18 | 2013-02-11 | 2012-07-16 | 2013-02-11 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Major construction | WY | WYOMING | CAMP GUERNSEY | AFSPC053012 | Nuclear/Space Security Tactics Training Center (Nssttc) | 2010-10-13 | 2011-06-02 | R.C. Heath Construction Co. | 3854 | 4061 | 2011-06-29 | 2012-12-13 | 2012-09-21 | 2013-08-30 | 99 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | 64622 | 64622 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 14 | 14598
2013-07-31 | 2013-08-06 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan) *ArchTestDigs* | 50 | 50 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 14 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT* | 72 | 72 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 14 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 319 | 319 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 14 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH085082 | EMSG Headquarters And Town Hall | 2012-01-31 | 2012-05-18 | CH2MHill | 998 | 998 | 2012-06-07 | 2013-06-27 | 2013-01-18 | 2013-06-27 | 70 | 1134
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | BAGR113008 | Operations Group Command And Control (C2) Facility | 2012-01-31 | 2012-05-18 | CH2MHill | 1618 | 1618 | 2012-06-07 | 2013-06-30 | 2013-01-18 | 2013-06-30 | 54 | 1838
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | BAGR113010 | Tactical Fighter AMU | 2012-01-31 | 2012-05-18 | CH2MHill | 1306 | 1306 | 2012-06-07 | 2013-08-14 | 2013-01-18 | 2013-08-14 | 48 | 1650
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | BAGR113011 | Tactical Fighter Squad Ops | 2012-01-31 | 2012-05-18 | CH2MHill | 1578 | 1578 | 2012-06-07 | 2013-07-07 | 2013-01-18 | 2013-07-07 | 67 | 1792
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | BAGR113022 | Flight Line Fire Station | 2012-01-31 | 2012-05-18 | CH2M Hill | 1519 | 1519 | 2012-06-07 | 2013-07-11 | 2013-01-18 | 2013-07-11 | 42 | 1798
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | KANDAHAR AB | LYAV100026 | 451 AEW SCIF | 2012-01-02 | 2012-03-15 | Entire-Ashna-Vertex JV | 871 | 871 | 2012-04-14 | 2013-06-30 | 2012-07-13 | 2013-06-30 | 95 | 1645
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | FL | FLORIDA | HURLBURT FIELD | FTEV083015 | Relocate Family Camping Facility | 2012-02-16 | 2012-06-15 | Green Simmons | 1870 | 1961 | 2012-07-09 | 2013-05-17 | 2013-03-29 | 2013-07-08 | 100 | 1975
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | GA | GEORGIA | MOODY AIR FORCE BASE | QSEU090402 | ADAL Hc-130J Aerial Delivery/Logistics Facility | 2012-04-26 | 2012-07-05 | USCS | 1716 | 1716 | 2012-07-19 | 2013-06-13 | 2012-12-21 | 2013-06-20 | 100 | 1968
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ113001R1 | Convert Bldg 660 To C-17 Combined Program Office | 2011-09-29 | 2011-12-08 | MAPCO, INC. | 938 | 978 | 2011-12-20 | 2012-06-15 | 2012-06-20 | 2012-10-25 | 100 | 1700
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK113003 | Catch Basin For Waste Water Treatment | 2012-03-30 | 2012-07-31 | UVB BITBURG | 1762 | 1762 | 2012-08-15 | 2013-09-30 | 2013-09-15 | 2013-09-15 | 65 | 1762
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | ID | IDAHO | MOUNTAIN HOME AIR FORCE BASE | QYZH090057 | Relocate Arresting Systems, Runways 12 & 30 | 2013-04-12 | 2012-05-25 | North Wind Services | 2145 | 2145 | 2012-06-05 | 2012-12-10 | 2012-08-31 | 2012-08-31 | 85 | 2284
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | KWT | KUWAIT | ALI AL SALEM AB | AEWV111136 | Sewage Treatment System | 2012-08-29 | 2013-01-09 | ARABI CO. W.L.L. | 1592 | 1592 | 2013-04-10 | 2014-01-31 | 2013-08-15 | 2014-01-31 | 20 | 1788
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | NZYY110190 | Air Freight Facility | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 926 | 926 | 2011-12-19 | 2013-09-30 | 2013-02-28 | 2013-09-30 | 64 | 1041
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | NZYY110200 | Aerial Port C2 Facility | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 1282 | 1282 | 2011-12-19 | 2013-09-30 | 2013-02-28 | 2013-09-30 | 68 | 1440
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF113020 | Medical Education & Training Facility Replacement | 2012-03-01 | 2012-05-31 | Synergy Systems Inc | 1698 | 1622 | 2012-08-14 | 2014-08-11 | 2013-04-17 | 2014-08-18 | 13 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD110006A | Construct CDC Addition, B650 | 2011-06-20 | 2011-08-11 | MODULAR MANAGEMENT GROUP, INC | 600 | 600 | 2011-08-30 | 2013-07-26 | 2012-09-12 | 2013-07-26 | 60 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113004 | F-16 Hydrazine Facility | 2011-10-21 | 2012-02-08 | ITSI | 1689 | 1689 | 2012-02-27 | 2013-08-02 | 2013-05-17 | 2013-08-02 | 98 | 1810
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV113101 | P-341 Add Composites Repair Shop to Corrosion Control Facility | 2011-08-12 | 2011-09-23 | K.L. House | 1351 | 1375 | 2011-11-09 | 2013-09-09 | 2012-10-31 | 2013-07-31 | 99 | 1699
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF080145 | Information Transfer Node | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 1074 | 1074 | 2012-10-03 | 2014-02-01 | 2012-10-30 | 2014-02-01 | 11 | 1318
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF105000 | Dining Facility | 2012-04-06 | 2012-07-31 | C Davis and Associates | 1004 | 1004 | 2012-10-03 | 2014-02-01 | 2012-09-01 | 2014-02-01 | 11 | 1233
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF110018 | EMSG Hq | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 1007 | 1007 | 2012-10-03 | 2014-02-01 | 2012-09-10 | 2014-02-01 | 11 | 1236
2013-07-31 | 2013-08-06 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF110019 | Kennel | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 583 | 583 | 2012-10-03 | 2014-02-01 | 2012-09-10 | 2014-02-01 | 11 | 716
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | AL | ALABAMA | MONTGOMERY REGIONAL AIRPORT (ANG) BASE | FAKZ959574 | Fuel Cell and Corrosion Control Hangar | 2011-03-15 | 2011-07-22 | Lord and Son Constrution, Inc | 7249 | 7477 | 2011-10-12 | 2013-09-01 | 2013-01-22 | 2013-10-01 | 92 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV089069 | TFI - Predator FOC – Increased Mission Orbit Tasking | 2011-05-13 | 2011-07-29 | Komada, LLC | 3761 | 4037 | 2011-09-08 | 2012-12-17 | 2012-09-07 | 2013-03-15 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | AZ | ARIZONA | FORT HUACHUCA | HFHA069130 | TFI - Predator LRE Beddown | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | 9434 | 10056 | 2013-04-08 | 2014-07-02 | 2014-06-02 | 2014-06-02 | 11 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | DE | DELAWARE | NEW CASTLE COUNTY AIRPORT | JLWS079103 | Joint Forces Operations Center - ANG Share | 2011-06-29 | 2011-09-16 | Vigil Contracting, Inc. | 1134 | 1164 | 2011-12-12 | 2013-03-22 | 2013-06-09 | 2013-07-22 | 70 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | FL | FLORIDA | JACKSONVILLE INTERNATIONAL AIRPORT | LSGA029009A | Security Forces Training Facility | 2010-11-12 | 2011-06-06 | Americaan Patriot Construction -IMC, LLC | 3909 | 4153 | 2011-08-05 | 2013-04-30 | 2012-12-03 | 2013-05-31 | 99 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU069150 | Relocate ASOS Facilities | 2011-04-20 | 2011-06-29 | Choice Concrete Construction LLC | 5962 | 6687 | 2011-08-01 | 2012-08-20 | 2012-07-28 | 2013-08-20 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069209 | TFI - F-22 Hangar, Squadron Operations and AMU | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | 37110 | 42160 | 2011-07-15 | 2013-07-05 | 2013-07-14 | 2013-07-05 | 91 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069215 | TFI - F-22 Upgrade Munitions Complex | 2012-01-11 | 2012-05-24 | Nan Inc. | 17142 | 19842 | 2012-06-14 | 2013-12-11 | 2013-12-11 | 2013-12-11 | 72 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109500 | TFI - F-22 Beddown Infrastructure Support | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | 5155 | 6634 | 2011-08-15 | 2013-08-14 | 2013-07-14 | 2013-08-14 | 94 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | IL | ILLINOIS | ABRAHAM LINCOLN CAPITAL AIRPORT | DCFT069059 | TFI - cNAF Beddown - Upgrade Facilities | 2010-12-15 | 2012-04-26 | JM Industrial Supply, Inc. | 13733 | 15347 | 2012-06-01 | 2013-12-31 | 2013-03-20 | 2014-01-08 | 80 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | IN | INDIANA | HULMAN REGIONAL AIRPORT | LDXF069123 | TFI - ASOS Beddown - Upgrade Facilities | 2011-03-08 | 2011-06-13 | Hannig Construction | 3571 | 3674 | 2011-07-07 | 2012-09-04 | 2012-07-06 | 2012-10-31 | 95 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | MD | MARYLAND | MARTIN STATE AIRPORT | PJMS909928 | Replace Operations and Medical Training Facility | 2011-08-17 | 2011-09-28 | Costello Construction of MD, Inc. | 11802 | 12716 | 2012-07-20 | 2014-02-03 | 2013-10-18 | 2014-02-03 | 75 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATION | FPBB109013 | TFI - Reaper Infrastructure Support | 2012-07-27 | 2012-10-17 | Black Horse Group | 2040 | 2157 | 2012-10-17 | 2013-07-31 | 2013-10-12 | 2013-07-31 | 73 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | NY | NEW YORK | STEWART INTERNATIONAL AIRPORT | WHAY089079 | Base Defense Group Beddown | 2011-07-30 | 2011-09-23 | APS Contractors Inc | 13401 | 14300 | 2011-10-13 | 2013-12-31 | 2013-05-05 | 2013-12-31 | 72 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | NC | NORTH CAROLINA | STANLY COUNTY AIRPORT | WEFM089029 | Upgrade ASOS Facilities | 2011-04-19 | 2011-08-26 | DOT Construction | 1660 | 1873 | 2011-10-24 | 2013-03-25 | 2012-07-21 | 2013-06-07 | 99 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | PA | PENNSYLVANIA | STATE COLLEGE ANG STATION | WFGE089076 | Add to and Alter AOS Facility | 2010-04-16 | 2011-08-25 | HSCC | 3903 | 4222 | 2011-08-25 | 2012-11-27 | 2012-08-24 | 2013-11-29 | 100 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Major construction | TX | TEXAS | ELLINGTON FIELD | FWJH069194 | TFI - Alter UAV Maintenance Hangar (Bldg 1382) | 2012-01-06 | 2012-06-14 | LeeTex Construction | 5038 | 5796 | 2012-07-23 | 2014-01-22 | 2013-07-23 | 2013-09-01 | 67 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Minor construction | CA | CALIFORNIA | MOFFETT FIELD (NASA), SAN JOSE, (ANG) | QMSN099051 | Force Protection Measures - Relocate Main Gate | 2011-11-04 | 2012-02-09 | Herrera Corporation | 1875 | 1952 | 2011-03-02 | 2013-01-07 | 2011-08-29 | 2013-02-04 | 99 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Minor construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU119021 | Relocate Taxiway Juliet | 2012-06-22 | 2012-08-23 | JE Hurley Construction, Inc. | 1824 | 1917 | 2012-09-12 | 2013-05-06 | 2013-03-01 | 2013-07-26 | 99 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Minor construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109032 | TFI- F-22 Beddown- Add to Communication Facility | 2012-01-04 | 2012-06-12 | HAKO PLUMBING, INC. | 1695 | 1858 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 23 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force NG | Minor construction | WY | WYOMING | CHEYENNE REGIONAL AIRPORT | DPEZ089083 | Relocate ROSC | 2011-07-18 | 2012-04-11 | Recco, Inc. | 1636 | 1975 | 2012-04-25 | 2013-06-28 | 2012-10-22 | 2013-06-28 | 95 | 0
2013-07-31 | 2013-08-06 | 2011 | Air Force res | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT043000 | Weapons Maintenance Facility | 2011-05-20 | 2011-07-22 | S&M and Associates, Inc./Pascagoula MS | 2937 | 3006 | 2011-10-03 | 2013-01-25 | 2012-05-25 | 2013-01-25 | 100 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | 53805 | 54672 | 2012-06-19 | 2014-10-08 | 2013-11-20 | 2014-10-08 | 17 | -11200
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | 3230 | 3230 | 2012-06-19 | 2014-10-08 | 2013-11-20 | 2014-10-08 | 17 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | 4979 | 4979 | 2012-06-19 | 2014-10-08 | 2013-11-20 | 2014-10-08 | 17 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | 1874 | 2192 | 2012-06-19 | 2014-10-08 | 2013-11-20 | 2014-10-08 | 17 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | 1799 | 1799 | 2012-06-19 | 2014-10-08 | 2013-11-20 | 2014-10-08 | 17 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV103006P1 | EC-130H Simulator/Training Operations | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | 14348 | 14348 | 2013-02-05 | 2014-12-27 | 2013-10-07 | 2014-12-27 | 2 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV123002 | HC-130J Joint Use Fuel Cell | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | 12361 | 12361 | 2012-10-31 | 2014-03-07 | 2014-04-28 | 2014-04-28 | 3 | 1256
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | AETC120010 | F-35 ADAL Aircraft Maintenance Unit | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | 4781 | 4923 | 2012-10-09 | 2013-12-10 | 2012-11-30 | 2014-01-26 | 57 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | AETC120011 | F-35 Squad Ops/AMU 2 | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | 12359 | 12359 | 2013-10-08 | 2014-09-19 | 2012-11-30 | 2014-12-06 | 1 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK111089A | Emergency Permanent Repair Hangar 245 | 2012-04-06 | 2012-07-11 | Blackhawk Ventures, LLC | 2404 | 2404 | 2012-08-28 | 2013-12-27 | 2014-04-25 | 2013-10-28 | 45 | 2727
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK133004 | Emergency Pest Management Facility | 2012-04-30 | 2012-08-14 | Guyco, Inc. | 1452 | 1462 | 2012-09-25 | 2013-11-24 | 2014-06-16 | 2013-11-07 | 21 | 1839
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT083003 | Dormitory (144 RM) | 2011-12-22 | 2012-05-11 | Barnhart-Balfour-Beatty, Inc; San Diego CA | 18492 | 18608 | 2012-06-11 | 2013-12-04 | 2013-11-11 | 2013-12-23 | 31 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | CA | CALIFORNIA | VANDENBERG AIR FORCE BASE | XUMU033002 | Education Center | 2011-12-13 | 2012-02-28 | TEEHEE-STRAUB JV | 13185 | 13407 | 2012-03-29 | 2013-12-03 | 2013-08-23 | 2013-12-10 | 65 | 693
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | CO | COLORADO | USAF ACADEMY | XQPZ044003 | Const Vehicle Search Facility | 2011-11-18 | 2012-03-30 | Komada LLC | 5941 | 5878 | 2012-05-01 | 2014-01-13 | 2013-12-15 | 2013-11-11 | 52 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT123000 | C-5M Formal Training Unit Facility | 2011-11-14 | 2012-05-07 | Eastern Sun Enterprises, Incorporated | 2085 | 2085 | 2012-06-12 | 2013-11-08 | 2013-11-04 | 2013-11-04 | 5 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT053001A | Air Force Technical Applications Center | 2011-09-30 | 2012-02-24 | Hensel Phelps | 70613 | 71623 | 2012-02-24 | 2014-01-31 | 2015-12-02 | 2015-12-02 | 70 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR063017 | Dormitory (192 RM) | 2013-10-12 | 2012-05-24 | LBB (EBC AWD) | 29542 | 29542 | 2014-03-31 | 2015-11-16 | 2015-03-02 | 2015-09-15 | 1 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17001 | Aircraft Apron/Taxiway And Maintenance Shelters | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | 6740 | 6671 | 2012-05-02 | 2013-09-02 | 2013-02-03 | 2013-09-02 | 89 | 8177
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17002 | Combat Aircraft Loading Area | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | 43421 | 43421 | 2012-10-01 | 2014-01-16 | 2014-01-16 | 2014-01-16 | 12 | 154000
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17003 | Parallel Taxiway Extension | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | 10522 | 10522 | 2012-10-01 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 4 | 24000
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17004 | Expeditionary Lodging | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | 26588 | 26588 | 2012-10-20 | 2014-03-15 | 2013-09-30 | 2014-03-21 | 10 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GRL | GREENLAND | THULE AIR BASE | WWCX103033 | Dormitory (72 PN) | 2011-12-05 | 2012-05-11 | MTHojgaard | 27936 | 27555 | 2012-06-06 | 2014-11-26 | 2014-12-26 | 2014-12-26 | 23 | 2000
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY123009 | Guam Strike - Clear Water Rinse Facility | 2011-11-15 | 2012-04-21 | Niking Corporation | 6739 | 6739 | 2012-06-11 | 2013-12-12 | 2013-12-30 | 2013-12-12 | 29 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY123011 | Guam Strike Coventional Munition Maintenance Facility | 2011-11-22 | 2012-04-27 | P & S Construction | 9527 | 9527 | 2012-05-11 | 2014-07-19 | 2014-07-19 | 2014-07-19 | 32 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY123011 | Guam Strike Coventional Munition Maintenance Facility | 2011-11-22 | 2012-05-29 | Navy Crane Center | 59 | 59 | 2012-05-11 | 2014-07-19 | 2014-07-19 | 2014-07-19 | 32 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY983202 | Air Freight Terminal Complex | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | 30047 | 31863 | 2012-07-18 | 2014-10-16 | 2014-03-31 | 2014-10-16 | 16 | 674
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility | 2011-12-30 | 2012-04-27 | Pacific West Builders | 9491 | 9434 | 2012-05-14 | 2013-11-06 | 2013-10-07 | 2013-11-06 | 59 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW091002 | PRTC - Combat Communications Transmission Systems Facility | 2011-11-28 | 2012-04-27 | Guam Pacific International | 3960 | 3960 | 2012-05-14 | 2013-11-02 | 2013-11-02 | 2013-11-02 | 41 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW101001 | PRTC - Combat Communications Combat Support Facility | 2011-11-28 | 2012-04-27 | Guam Pacific International | 6212 | 6212 | 2012-05-14 | 2013-11-02 | 2013-11-02 | 2013-11-02 | 40 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | ITA | ITALY | AVIANO AIR BASE | ASHE163000 | Child Development Center Addition | 2012-06-06 | 2012-09-30 | Collodetto Angelo Costruzioni | 890 | 890 | 2012-09-30 | 2014-01-31 | 2013-12-29 | 2013-12-29 | 14 | 1900
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | KS | KANSAS | FT RILEY | HACC123302 | Air Support Operations Center | 2011-12-05 | 2012-05-01 | Vengas Engineering Management & Const, Inc. | 5475 | 5572 | 2012-05-14 | 2013-09-03 | 2013-06-28 | 2013-08-09 | 91 | -1483
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | KOR | KOREA | OSAN AIR BASE | SMYU123002 | Dormitory (156 RM) | 2011-09-05 | 2012-03-13 | Seohee Construction Co., Ltd. | 14839 | 15129 | 2012-03-14 | 2014-07-08 | 2014-04-30 | 2014-07-08 | 24 | -2674
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | LA | LOUISIANA | BARKSDALE AIR FORCE BASE | AWUB105002 | Mission Support Group Complex | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | 17998 | 18056 | 2012-03-26 | 2013-12-17 | 2013-06-17 | 2013-12-17 | 47 | -3184
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG071005 | WSA Security Control Facility | 2011-11-23 | 2012-02-27 | Carlson Constructors | 4173 | 4173 | 2012-03-16 | 2013-10-14 | 2012-10-16 | 2013-10-14 | 25 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG111005 | Force Support Squadron Facility | 2012-06-01 | 2012-08-23 | Titan Construction Organizatio | 5388 | 5388 | 2012-09-07 | 2013-09-17 | 2013-09-09 | 2013-09-17 | 38 | 5997
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NE | NEBRASKA | OFFUTT AIR FORCE BASE | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | 102754 | 101945 | 2012-09-11 | 2016-01-15 | 2016-02-15 | 2016-09-09 | 6 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103001 | F-35A AGE Facility | 2011-11-17 | 2012-06-01 | R.L. Reed, Inc. | 11097 | 11215 | 2012-06-19 | 2013-12-15 | 2013-07-15 | 2013-12-15 | 52 | -6390
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103003 | Communications Network Control Center | 2011-11-17 | 2012-04-24 | A4 Construction | 9327 | 9508 | 2012-05-22 | 2014-01-15 | 2013-03-15 | 2014-05-15 | 65 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103010 | F-35 Add/Alter Engine Shop | 2011-11-17 | 2012-05-24 | Au Authum KI, Inc | 1867 | 1867 | 2012-08-03 | 2014-09-15 | 2013-06-15 | 2014-09-15 | 2 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ123001 | Dormitory (96 RM) | 2012-06-13 | 2012-08-31 | USACE | 12463 | 12537 | 2012-09-26 | 2014-03-07 | 2013-07-31 | 2014-02-10 | 54 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ133001 | ADAL Wastewater Treatment Plant | 2012-04-26 | 2012-07-11 | KEAR Civil Corporation | 7787 | 7787 | 2012-09-11 | 2014-02-03 | 2013-12-31 | 2013-11-04 | 82 | 1083
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD013003 | Child Development Center | 2012-05-18 | 2012-08-17 | Turner Atlantic Construction | 9844 | 9844 | 2012-11-08 | 2014-08-15 | 2012-06-15 | 2014-08-15 | 6 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD083007 | Parallel Taxiway, Rwy 07/25 | 2012-03-15 | 2012-06-08 | Mesa Verde Enterprises, Inc. | 6349 | 6349 | 2012-07-02 | 2014-04-29 | 2013-04-05 | 2014-04-29 | 28 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113005 | F-16 Academic Training Facility | 2012-02-03 | 2012-06-13 | White Sands Construction | 4990 | 4990 | 2012-07-09 | 2014-03-21 | 2013-07-12 | 2014-03-21 | 42 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113010 | F-16 Sead Training Facility | 2012-02-03 | 2012-06-13 | White Sands Construction | 3614 | 3614 | 2012-07-09 | 2014-03-21 | 2013-02-04 | 2014-03-21 | 42 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV093108 | AFNWC Sustainment Center | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | 21110 | 21117 | 2012-07-09 | 2014-08-08 | 2014-08-08 | 2014-08-08 | 22 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | NC | NORTH CAROLINA | POPE AIR FORCE BASE | TMKH083003 | C-130 Flight Simulator | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | 4630 | 4630 | 2012-07-24 | 2013-12-04 | 2013-12-31 | 2013-12-31 | 19 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092001 | Dormitory (168 RM) | 2011-11-15 | 2012-02-14 | Graham Construction | 17775 | 17849 | 2012-03-21 | 2013-09-12 | 2013-08-08 | 2014-03-11 | 79 | -2049
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092010 | B-52 3-Bay Conventional Munitions Mtc Facility | 2012-01-24 | 2012-05-03 | Creative Times, Inc. | 10490 | 10776 | 2012-05-31 | 2014-04-21 | 2013-08-01 | 2014-04-21 | 17 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | 32123 | 32300 | 2012-05-22 | 2014-11-10 | 2014-02-11 | 2014-11-10 | 21 | 1813
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | TX | TEXAS | JOINT BASE FT SAM HOUSTON | MPLS11473JB | Advance Individual Trainee (AIT) Barracks (300 RM) | 2011-12-15 | 2012-03-30 | Hensel-Phelps Constr. Co. | 34889 | 34988 | 2012-07-20 | 2014-03-14 | 2014-08-05 | 2014-03-14 | 83 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R4 | BMT Recruit Dormitory, Phase IV | 2011-12-16 | 2012-07-17 | SpawGlass Contractors, Inc. | 50530 | 50911 | 2012-11-26 | 2015-03-26 | 2013-10-01 | 2015-04-02 | 9 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM123011R | F-22 System Support Facility | 2011-12-09 | 2012-06-05 | Creative Times Inc | 9598 | 9579 | 2012-07-24 | 2014-02-20 | 2013-12-05 | 2014-06-05 | 29 | -4155
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | WACC120007 | AIT Barracks Complex, Ph 2 | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | 33915 | 33915 | 2012-10-12 | 2014-04-30 | 2014-04-01 | 2014-05-30 | 7 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ860009 | Wing Headquarters | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | 11957 | 12244 | 2012-05-21 | 2014-06-24 | 2014-01-15 | 2014-09-25 | 34 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ920012P2 | SERE Force Support Complex, Phase 2 | 2011-11-21 | 2012-07-05 | Total Site Services/Garco | 11724 | 11855 | 2012-07-20 | 2014-01-19 | 2014-05-20 | 2014-06-15 | 17 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | 17707 | 17707 | 2013-06-04 | 2015-11-11 | 2014-03-01 | 2015-11-20 | 3 | 15000
2013-07-31 | 2013-08-06 | 2012 | Air Force active | MFH improvement | JPN | JAPAN | MISAWA AIR BASE | QKKA124002 | Improve MFH Infrastructure, Phase 1 | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | 19550 | 19911 | 2012-06-11 | 2014-11-13 | 2014-11-13 | 2014-11-13 | 25 | -78
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU123005 | PL-1 Entry Control Facility | 2013-01-31 | 2013-04-04 | Hartland/Mass JV | 1125 | 1125 | 2013-04-22 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 5 | 1800
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU121019 | F-22 ADAL Deployment Processing Center | 2012-06-13 | 2012-09-20 | MTNT Properties, Inc | 1890 | 1890 | 2012-10-04 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 62 | 1985
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ110047 | ADAL Corrosion Control Hangar (Bldg 89) | 2012-06-25 | 2012-11-06 | GSC Construction, Inc. | 1831 | 1831 | 2012-11-19 | 2013-12-10 | 2013-10-20 | 2013-12-17 | 14 | 3989
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ110048 | ADAL Corrosion Control Hangar (Bldg 54) | 2012-06-25 | 2012-11-06 | GSC Construction, Inc. | 1819 | 1819 | 2012-11-19 | 2014-02-25 | 2013-12-22 | 2014-02-25 | 14 | 1923
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | IN | INDIANA | GRISSOM AIR RESERVE BASE | CTGB102040 | Addition to BOWST Simulator | 2012-04-23 | 2012-08-03 | ITSI | 1031 | 1031 | 2012-08-06 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 35 | 1031
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | NJ | NEW JERSEY | MCGUIRE AIR FORCE BASE | PTFL106001 | Construct Covered Storage | 2012-06-22 | 2012-09-10 | Complete Technical Inc | 1295 | 1295 | 2012-06-26 | 2013-12-30 | 2013-12-30 | 2013-12-30 | 74 | 1295
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF123101 | Addition to High Fidelity Trainer | 2012-07-16 | 2012-09-11 | Ainsworth-Benning of Wyoming, | 1639 | 1639 | 2013-05-20 | 2013-10-18 | 2013-10-20 | 2013-10-20 | 1 | 1639
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113027 | Air Defense Artillery Maintenance Facility | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | 1265 | 1265 | 2013-07-08 | 2014-06-10 | 2014-04-09 | 2014-06-10 | 1 | 1421
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113032 | Precision Measurement Equipment Laboratory | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | 1404 | 1404 | 2013-07-08 | 2014-06-10 | 2014-04-09 | 2014-06-10 | 1 | 1577
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113034 | AFOSI Regional And Local Facility | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | 1215 | 1215 | 2013-11-18 | 2014-06-10 | 2014-04-09 | 2014-06-10 | 1 | 1364
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | TX | TEXAS | SHEPPARD AIR FORCE BASE | VNVP113003 | Upgrade Metals Training Facility | 2012-06-29 | 2012-09-19 | Koht'aene Enterprises Co (KEC) | 1722 | 1722 | 2012-10-03 | 2013-02-04 | 2013-05-17 | 2013-05-03 | 100 | 1722
2013-07-31 | 2013-08-06 | 2012 | Air Force active | Minor construction | UT | UTAH | HILL AIR FORCE BASE | KRSM123015 | Construct Hayman Type Igloo | 2012-10-15 | 2013-01-15 | Hal Hays Construction, Inc. | 1055 | 1055 | 2013-02-04 | 2014-04-30 | 2014-04-28 | 2014-04-30 | 2 | 1190
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Major construction | CA | CALIFORNIA | BEALE AIR FORCE BASE | BAEY029154 | Wing Operations and Training Facility | 2012-07-27 | 2012-09-26 | SM Construction | 4960 | 5269 | 2012-12-03 | 2014-05-01 | 2013-12-03 | 2014-05-01 | 25 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Major construction | CA | CALIFORNIA | MOFFETT FIELD (NASA), SAN JOSE, (ANG) | QMSN019029 | Replace Pararescue Training Facility | 2012-08-05 | 2012-09-26 | Flintco Construction | 25535 | 26361 | 2013-01-10 | 2014-04-15 | 2014-04-10 | 2014-05-15 | 16 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069212 | TFI - F-22 Flight Simulator Facility | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | 18842 | 21381 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 36 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069213 | TFI - F-22 Weapons Load Crew Training Facility | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | 6473 | 7218 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 23 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | 9682 | 10506 | 2012-08-08 | 2013-08-08 | 2013-08-08 | 2013-08-08 | 32 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Major construction | OH | OHIO | SPRINGFIELD-BECKLEY MUNICIPAL AIRPORT | WAAR109001 | Alter Predator Operations Center Facility | 2012-08-17 | 2012-09-26 | UTS-DAG Construction Co., LLC | 5296 | 6376 | 2012-12-05 | 2013-12-31 | 2013-11-01 | 2013-12-13 | 70 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Minor construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU129062 | Vehicle Maintenance Addition | 2012-05-24 | 2012-08-17 | Tyler Construction Group, Inc. | 1500 | 1500 | 2012-08-17 | 2013-08-16 | 2013-02-13 | 2013-08-30 | 70 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Minor construction | ME | MAINE | BANGOR INTERNATIONAL AIRPORT | FKNN049094 | Pavements and Grounds Facility | 2012-05-16 | 2012-09-12 | Cornerstone Construction | 1277 | 1523 | 2012-09-19 | 2013-10-19 | 2013-03-18 | 2013-09-19 | 5 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force NG | Minor construction | MN | MINNESOTA | DULUTH INTERNATIONAL AIRPORT | FMKM099063 | Munitions Storage Igloos | 2012-08-29 | 2012-09-26 | Max Gray Construction, INC. | 1798 | 1874 | 2012-11-13 | 2013-09-12 | 2013-03-13 | 2013-09-12 | 45 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force res | Major construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG020143 | Construct New Airfield Control Tower, B1295 & Base Op'S B395 | 2012-03-16 | 2012-07-26 | Flintco, LLC. | 16915 | 16966 | 2012-08-22 | 2014-07-24 | 2013-04-23 | 2015-01-22 | 56 | 1928
2013-07-31 | 2013-08-06 | 2012 | Air Force res | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG111420 | 442: Construct LRS Facility | 2012-08-09 | 2012-09-26 | J & S Construction Co, Inc., Cookeville, TN | 3507 | 3507 | 2012-12-19 | 2013-12-05 | 2013-12-20 | 2014-01-01 | 23 | 3840
2013-07-31 | 2013-08-06 | 2012 | Air Force res | Major construction | SC | SOUTH CAROLINA | JOINT BASE CHARLESTON ISSOT NORTH CHARLESTON | DKFX079003 | Red Horse Readiness And Training Facility | 2012-02-08 | 2012-07-13 | IKHANA | 8149 | 8663 | 2012-07-13 | 2014-01-10 | 2013-03-01 | 2014-01-10 | 43 | 0
2013-07-31 | 2013-08-06 | 2012 | Air Force res | Minor construction | FL | FLORIDA | HURLBURT FIELD | FTEV111226B | Alter Building 90131 For 2 SOS | 2012-06-05 | 2012-09-13 | HCG, LLC | 926 | 994 | 2012-10-22 | 2013-08-19 | 2013-04-16 | 2013-08-19 | 85 | 1000
2013-07-31 | 2013-08-06 | 2013 | Air Force active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK103006 | C-130J Fuel Systems Maintenance Hangar | 2012-11-15 | 2013-06-25 | The Ross Group | 20869 | 20869 | 2013-07-23 | 2015-10-01 | 2014-11-19 | 2015-08-02 | 2 | 0
2013-07-31 | 2013-08-06 | 2013 | Air Force active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair | 2013-01-09 | 2013-05-31 | Barlovento | 13299 | 13299 | 2013-06-25 | 2014-06-20 | 2014-07-20 | 2014-07-20 | 1 | 339
2013-07-31 | 2013-08-06 | 2013 | Air Force active | Major construction | GRL | GREENLAND | THULE AIR BASE | WWCX103032 | Dormitory (48 Pn) | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | 23032 | 23032 | 2013-07-31 | 2015-08-25 | 2015-08-25 | 2015-08-25 | 1 | 1485
2013-07-31 | 2013-08-06 | 2013 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD123004 | MQ-9 Maintenance Hangar | 2013-03-01 | 2013-06-17 | HEW-Phelps | 20620 | 20620 | 2013-07-15 | 2015-06-15 | 2014-11-28 | 2015-06-15 | 2 | 0
2013-07-31 | 2013-08-06 | 2013 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092011 | B-52 Add/Alter Munitions Age Facility | 2012-11-19 | 2013-05-31 | Rolac Contracting, Inc. | 4377 | 4377 | 2013-06-19 | 2014-12-11 | 2014-08-21 | 2014-12-11 | 2 | 289
2013-07-31 | 2013-08-06 | 2013 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | 14698 | 14698 | 2013-10-01 | 2015-12-01 | 2015-03-01 | 2015-12-01 | 1 | 20489
2013-07-31 | 2013-08-06 | 2013 | Air Force active | Minor construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 | 2013-03-06 | 2013-05-23 | Southwind Construction | 1525 | 1525 | 2013-06-07 | 2015-10-17 | 2015-08-06 | 2015-08-06 | 2 | 1713
2013-07-31 | 2013-08-02 | 2013 | DFAS | Military Construction | TX | TEXAS | Red River Army Depot | 80230 | DFAS Facility
2013-07-31 | 2013-08-02 | 2008 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 1 | 2007-10-11 | 2008-02-29 | Hensel Phelps Construction Company | 369605 | 176436 | 2008-04-16 | 2011-01-08 | 2011-04-15 | 2010-10-13 | 100 |  |  |  | Incrementally Funded for FY08
2013-07-31 | 2013-08-02 | 2009 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 2 | 2007-10-11 | 2008-02-29 | Hensel Phelps Contruction Company | 369605 | 130128 | 2008-04-16 | 2011-01-29 | 2011-04-15 | 2010-11-30 | 100 |  |  |  | Incrementally Funded for FY09
2013-07-31 | 2013-08-02 | 2010 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 3 | 2007-10-11 | 2008-02-29 | Hensel Phelps Construction Company | 369605 | 131662 | 2008-04-16 | 2011-02-19 | 2011-04-15 | 2011-01-24 | 100 |  |  |  | Incrementally Funded for FY10
2013-07-31 | 2013-08-02 | 2010 | DISA | Military Construction | HI | HAWAII | Ford Island | DISA10-02 | DISA PAC Facility Upgrades | 2010-08-30 | 2010-12-16 | Bulltrack-Watts (Joint Venture) | 12625 | 17212.464 | 2010-12-16 | 2013-04-22 | 2010-12-16 | 2013-04-22 | 100 | 300 |  |  | As of 27 June 2013, awaiting final invoice to be submitted from the Contractor before project can be financially closed out and remaining funds returned to DISA.
2013-07-31 | 2013-08-02 | 2011 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | DISA10-01 | Field Command Facility Upgrade (Wing Enclosure) | 2011-08-11 | 2011-09-30 | DWG & Associates | 1194 | 924.1 | 2011-10-26 | 2012-12-21 | 2012-09-19 | 2012-11-30 | 100 | -300
2013-07-31 | 2013-08-02 | 2012 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | 68120 | Construct New Facility Scott AFB - Design |  | 2012-05-01 | Burns & McDonnell | 5036.15 | 5183.48 | 2012-05-01 |  | 2013-05-31 | 2013-05-31 | 99
2013-07-31 | 2013-08-02 | 2010 | DISA | Military Construction | HI | HAWAII | Ford Island | DISA10-02 | Pacific Operations Facility Upgrade
2013-07-31 | 2013-08-02 | 2011 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | DISA10-01 | Field Command Facility Upgrade
2013-07-31 | 2013-08-02 | 2012 | DISA | Military Construction | DEU | GERMANY | Stuttgart-Patch Barracks | DISA10-03 | DISA Europe Facility Upgrades |  | 2012-04-10 | Buchart-Horn GMBH (Design) | 205.3 | 205.3 | 2013-04-17 |  | 2012-09-07 | 2012-09-11 | 100 |  |  |  | Design cost $205,,337.62 US
2013-07-31 | 2013-08-02 | 2012 | DISA | Military Construction | DEU | GERMANY | Stuttgart-Patch Barracks | DISA10-03 | DISA Europe Facility Upgrades | 2013-01-22 | 1 May 13 (construction) | Way SS & Freytag Ingenieurbau AG | 1387.3 | 1387.3 | 2013-05-16 | 2014-01-11 | 2013-12-11 | 2013-12-11 | 2 | 500 |  |  | Project descoped .25%. Sprinkler System. Unforeseen requirement to add double sprinkler heads due to false ceiling and additional water tank.
2013-07-31 | 2013-08-02 | 2013 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | VDYDS97032 | Construct New Facility Scott AFB - Soil Remediation | 2013-04-05 | 2013-06-27 | Plexus Scientific Corp. | 1339.17 |  |  |  |  | 41638 | 0.1 | 0 |  |  | Soil Remediation Contract Award Amount: $1.339,170.73 + USACE fees $161,333.27 = $1,500,504
2013-07-31 | 2013-08-02 | 2013 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | VDYDS97032 | Construct New Facility Scott AFB - Facility Construction | 2013-05-24 |  | TBD | [5 empty] | TBD | 0 | 0
2013-07-31 | 2013-08-02 | 2013 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | VDYDS97032 | Construct New Facility Scott AFB - Demo of Bldg 3189 |  |  | TBD | [5 empty] | TBD | 0 | 0
2013-07-31 | 2013-08-02 | 2013 | DISA | Military Construction | DEU | GERMANY | Stuttgart-Patch Barracks | DISA13-01 | DISA Europe Facility- Replace/Upgrade UPS and Paralleling Gear |  |  | TBD | [5 empty] | TBD | 0 |  |  |  | Revised PA=$2.224 M based on Sequestration Budget Cut. Intial PA: $2.413M
2013-07-31 | 2013-08-02 | 2008 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 1
2013-07-31 | 2013-08-02 | 2009 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 2
2013-07-31 | 2013-08-02 | 2010 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 3
2013-07-31 | 2013-08-13 | 2008 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities INCR#1 (of 4 Increments) | 2008-02-20 | 2008-09-30 | Nova Group Inc - Underground Construction Company - AJV | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | 0 | Increments 1-3 awarded
2013-07-31 | 2013-08-13 | 2008 | DLA | MC | PA | PENNSYLVANIA | DLA Distribution New Cumberland | DDCX0702 | Replace Central Heat Plant | 2008-07-14 | 2008-09-28 | John C. Grimberg Company | 19757 | 20611 | 2008-11-03 | 2011-10-21 | 2011-07-21 | 2012-10-21 | 100 | 0
2013-07-31 | 2013-08-13 | 2009 | DLA | MC | CA | CALIFORNIA | DLA Distribution Depot San Joaquin at Tracy | DDCX1002 | Replace General Purpose Warehouse | 2008-11-11 | 2009-03-11 | Whiting Turner Contracting Co. | 29345 | 30469 | 2009-04-02 | 2012-01-05 | 2012-03-17 | 2013-03-20 | 100 | -6,600 | Rescinded per PL 111-117
2013-07-31 | 2013-08-13 | 2009 | DLA | MC | FL | FLORIDA | NAV SUP Fleet Logistics Center Jacksonville | DESC0801 | Replace Fuel Storage Tanks | 2009-03-11 | 2009-09-22 | Mid Eastern Builders INC | 22226 | 22640 | 2009-10-30 | 2012-12-31 | 2012-09-22 | 2012-12-15 | 100 | -9,000 | Rescinded per PL 111-117
2013-07-31 | 2013-08-13 | 2009 | DLA | MC | DEU | GERMANY | DLA Distribution Europe at Germersheim | DDCX0904 | Logistics Distribution Center | 2010-02-12 | 2010-05-18 | Wolfe & Muller Regionalbau GmbH & Co. / Peter Gross GmbH & Co. | 34991 | 36800 | 2010-06-16 | 2012-01-25 | 2012-01-04 | 2012-01-04 | 100 | -10,400 | Rescinded by 0SD 24 May 11A, PROJECT COMPLETE
2013-07-31 | 2013-08-13 | 2009 | DLA | MC | HI | HAWAII | NAV SUP Fleet Logistics Center Pearl Harbor | DESC0808 | Replace Fuel Pipeline | 2009-05-01 | 2009-06-12 | Watts Construction LLC | 17336 | 24416 | 2009-07-12 | 2012-12-30 | 2011-07-12 | 2013-08-31 | 99 | -5,300 | Rescinded per PL 111-117
2013-07-31 | 2013-08-13 | 2009 | DLA | MC | NM | NEW MEXICO | Kirtland Air Force Base | DESC0802 | Replace Fuel Storage Tanks | 2009-04-06 | 2009-08-20 | Kinley Construction | 7355 | 7762 | 2009-10-14 | 2011-03-18 | 2011-06-11 | 2011-06-11 | 100 | -5,900 | Rescinded per PL 111-117, PROJECT COMPLETE
2013-07-31 | 2013-08-13 | 2009 | DLA | MC | UT | UTAH | Hill Air Force Base | DESC0608 | Hydrant Fuel System | 2009-01-29 | 2009-05-22 | Rockford Corp | 14636 | 15416 | 2009-06-18 | 2011-04-21 | 2011-05-13 | 2011-05-13 | 100 | -3000 | Rescinded by 0SD 24 May 11A, PROJECT COMPLETE
2013-07-31 | 2013-08-13 | 2009 | DLA | MC | VA | VIRGINIA | Defense Fuel Support Point Craney Island | DESC0703 | Replace Fuel Storage Tanks | 2009-04-01 | 2009-07-31 | Mid Eastern Builders INC | 36371 | 38046 | 2009-09-03 | 2012-12-29 | 2012-08-29 | 2013-08-31 | 99 | 0
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) | 2008-02-20 | 2011-03-22 | Nova Group Inc - Underground Construction Company - AJV | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | 0 | Increments 1-3 awarded
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | CA | CALIFORNIA | Travis Air Force Base | DESC0803 | Replace Fuel Distribution System | 2010-11-10 | 2011-02-18 | Kinley Construction | 13621 | 14208 | 2011-05-10 | 2013-03-20 | 2012-08-26 | 2013-08-31 | 99 | 0
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | FL | FLORIDA | Jacksonville International Airport | DESC0908 | Replace Jet Fuel Storage Complex | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | 7909 | 9756 | 2010-04-27 | 2012-08-09 | 2011-09-20 | 2013-08-30 | 93 | -1900 | Rescinded by 0SD 18 May 11A
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | MN | MINNESOTA | Duluth Air National Guard | DESC1002 | Replace Jet Fuel Storage Complex | 2010-03-10 | 2010-07-16 | Talon Industries Inc. | 11195 | 11195 | 2010-08-30 | 2012-01-12 | 2011-11-01 | 2012-01-09 | 100 | -2000 | Rescinded by 0SD 18 May 11A, PROJECT COMPLETE
2013-07-31 | 2013-08-13 | 2010 | DLA | UMMC | NC | NORTH CAROLINA | Marine Corps Air Station New River | DESC11S3 | Replace Pump Station | 2010-02-20 | 2010-09-29 | North State Mechanical Inc. | 947 | 1047 | 2011-01-15 | 2012-11-16 | 2011-12-08 | 2012-08-10 | 100 | 0
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | AX2 | GUANTANAMO BAY NAVAL BASE | Naval Station Guantanamo Bay | DESC0904 | Replace Fuel Storage Tank | 2010-01-19 | 2010-05-27 | Toltest, Inc | 8594 | 8658 | 2010-05-27 | 2011-11-28 | 2012-11-28 | 2012-11-28 | 100 | -2200 | Rescinded by 0SD 18 May 11A, PROJECT COMPLETE
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | GRC | GREECE | Naval Support Activity Souda Bay, Crete | DESC0707A | Fuel Tanks and Pipeline Replacement | 2010-01-29 | 2010-09-30 | AKTORS, S.A. | 19667 | 21060 | 2010-01-12 | 2013-01-11 | 2012-07-09 | 2013-08-31 | 99 | -8,250 | Rescinded by 0SD 18 May 11A
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | KOR | KOREA | Osan Air Base | DESC0907 | Hydrant Fuel System | 2010-01-12 | 2010-04-16 | Namwha Construction Co. | 17844 | 19014 | 2010-08-27 | 2014-08-22 | 2013-11-18 | 2014-08-22 | 74 | -7,000 | Rescinded by 0SD 18 May 11A
2013-07-31 | 2013-08-13 | 2010 | DLA | MC | GBR | UNITED KINGDOM | Royal Air Force Base Mildenhall | DESC0910 | Connect Fuel Tank to Distribution Pipeline | 2010-04-23 | 2010-09-16 | Entrepose Industrial Services | 3300 | 3300 | 2011-03-07 | 2013-03-04 | 2011-08-18 | 2011-12-16 | 100 | 0 | PROJECT COMPLETE
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) | 2008-02-20 | 2011-03-30 | Nova Group Inc - Underground Construction Company - AJV | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | 0 | Increments 1-3 awarded
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | CA | CALIFORNIA | Naval Base Ventura County, Point Mugu | DESC10S4 | Aircraft Direct Fueling Station | 2011-04-29 | 2011-06-30 | RORE, INC. | 2553 | 2733 | 2011-07-30 | 2014-04-24 | 2012-08-13 | 2014-04-24 | 98 | 0 | Design/Build 35% 11/01/11
2013-07-31 | 2013-08-13 | 2011 | DLA | UMMC | CA | CALIFORNIA | Edwards Air Force Base | DESC11U1 | Truck Offload Facility | 2012-03-16 | 2012-07-12 | Kinley Construction Company | 1019 | 1019 | 2012-07-26 | 2013-09-30 | 2013-05-31 | 2013-08-31 | 25 | 0
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | GA | GEORGIA | Hunter Army Arifield | DESC11S4 | Fuel Unload Facility | 2011-06-03 | 2011-09-15 | Ponds Constructors, Inc | 1199 | 1398 | 2011-10-26 | 2013-12-30 | 2012-10-31 | 2013-10-30 | 27 | -980 | Rescinded by OSD 23 Mar 12A, Design-Build Effort
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | HI | HAWAII | Hickam Air Force Base | DESC1190 | Alter Fuel Storage Tanks | 2011-01-03 | 2011-05-26 | Reliable Contracting Group, LLC | 7584 | 8071 | 2011-06-22 | 2012-12-17 | 2012-12-13 | 2013-08-30 | 99 | 0
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | ID | IDAHO | Mountain Home Air Force Base | DESC1113 | Replace Fuel Storage Tanks | 2011-03-30 | 2011-09-02 | Garco Construction, Inc. | 16480 | 16699 | 2011-10-12 | 2014-07-11 | 2012-04-12 | 2014-05-26 | 79 | -8380 | Rescinded by OSD 23 Mar 12A
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | MD | MARYLAND | Andrews Air Force Base | DESC1003 | Replace Fuel Storage and Distribution Facilities | 2011-05-15 | 2011-10-31 | MEB General Contractors | 7971 | 8312 | 2011-11-21 | 2013-05-18 | 2013-05-18 | 2013-08-01 | 93 | -4872 | Rescinded by OSD 23 Mar 12A
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | PA | PENNSYLVANIA | DLA Distribution New Cumberland | DDCX0802 | Replace Headquarters Facility | 2011-11-23 | 2012-08-17 | Walsh Construction | 80775 | 80775 | 2012-08-30 | 2016-01-18 | 2015-09-18 | 2015-10-30 | 14 | 0
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | OH | OHIO | DLA Land and Maritime Columbus | DSCC0802 | Replace Public Safety Facility | 2011-04-04 | 2011-10-21 | Industria Paschen Group JV | 5883 | 6196 | 2011-11-10 | 2013-03-01 | 2013-03-21 | 2013-05-29 | 98 | 0
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | VA | VIRGINIA | Defense Fuel Support Point Craney Island | DESC0909 | Replace Fuel Pier | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | 28815 | 29805 | 2012-10-26 | 2014-06-30 | 2014-07-03 | 2014-08-29 | 57 | -9428 | Rescinded by OSD 23 Mar 12A
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | JPN | JAPAN | Kadena Air Base Okinawa | DESC11S1 | Install Fuel Filter/Separators | 2010-10-07 | 2011-06-27 | Nippo Corporation | 1175 | 1175 | 2011-07-13 | 2012-11-09 | 2012-10-27 | 2012-10-27 | 100 | 0 | PROJECT COMPLETE
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | JPN | JAPAN | Misawa Air Base | DESC0503 | Hydrant Fuel System | 2012-05-12 | 2012-09-22 | Tokyo Construction Co., Ltd. | 25204 | 25238 | 2013-02-01 | 2015-06-06 | 2015-02-01 | 2015-02-01 | 4 | 0
2013-07-31 | 2013-08-13 | 2011 | DLA | MC | GBR | UNITED KINGDOM | Royal Air Force Base Mildenhall | DESC0905 | Replace Hydrant Fuel System | 2011-04-19 | 2011-12-06 | Spiecapag | 12535.429 | 12535 | 2011-12-09 | 2013-03-14 | 2013-03-14 | 2013-05-30 | 75 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | AK | ARKANSAS | Eielson Air Force Base | DESC1108 | Upgrade Rail Line | 2012-02-29 | 2012-07-06 | G2 Construction, Inc. | 12210 | 12332 | 2012-07-16 | 2014-04-03 | 2013-12-05 | 2014-04-03 | 60 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | AZ | ARIZONA | Davis Monthan Air Force Base | DESC1103 | Replace Hydrant Fuel System | 2012-05-04 | 2012-09-25 | Nova Group Inc. | 18252 | 18291 | 2012-11-13 | 2015-03-29 | 2014-11-03 | 2015-01-02 | 38 | -1322 | Diverted to Altus
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | CA | CALIFORNIA | NAVBASE Coronado, San Clemente Island | DESC1205 | Replace Fuel Facilities | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | 27453 | 27453 | 2013-02-28 | 2015-03-24 | 2015-03-24 | 2015-03-24 | 0 | 9000 | Additional funds Formal Reprogramming FY09 Germersheim
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) | 2008-02-20 | 2012-03-29 | Nova Group Inc - Underground Construction Company - AJV | 15512 | 15512 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | -7000 | 10 USC 2853 submitted 23 Apr 12. Increments 1-4 awarded
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | CA | CALIFORNIA | DLA Distribution Tracy | DDCX1102 | Public Safety Facility | 2012-04-13 | 2012-07-16 | MASCON, INC | 14615 | 14735 | 2012-08-29 | 2014-10-09 | 2014-03-24 | 2014-09-30 | 20 | 900 | Additional funds from FY 09 Bid Savings
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | FL | FLORIDA | Naval Air Station Whiting Field | DESC12S3 | Truck Load/Unload Facility | 2012-01-13 | 2012-03-21 | Weston Solutions Inc. | 2500 | 3009 | 2012-03-21 | 2013-03-15 | 2013-03-24 | 2013-03-24 | 62 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | HI | HAWAII | Joint Base Pearl Harbor-Hickam | DESC12S5 | Upgrade Refueler Parking Area | 2011-10-21 | 2012-03-13 | RAASS Brothers INC | 5079 | 5605 | 2012-08-05 | 2013-04-30 | 2013-04-09 | 2013-09-26 | 82 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | HI | HAWAII | Joint Base Pearl Harbor-Hickam | DESC1101 | Alter Warehouse Space | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | 5500 | 5529 | 2012-08-13 | 2013-06-22 | 2013-06-14 | 2013-09-30 | 76 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | LA | LOUISIANA | Barksdale Air Force Base | DESC1106 | Hydrant Fuel System | 2011-10-04 | 2012-01-30 | Thrash Commercial Contractors INC | 4687 | 4953 | 2012-02-28 | 2013-08-02 | 2013-03-14 | 2013-03-11 | 74 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | MA | MASSACHUSETTS | Westover Air Reserve Base | DESC1102 | Upgrade Hydrant Fuel System | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | 24480 | 24480 | 2013-06-28 | 2016-01-28 | 2015-12-28 | 2015-12-28 | 0 | 963 | Reprogrammed fund OSD withholds
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | MS | MISSISSIPPI | Columbus Air Force Base | DESC11S2 | Replace Refueler Parking Facility | 2012-02-14 | 2012-04-30 | Reliable Contracting Group, LLC | 2360 | 2424 | 2012-06-07 | 2013-06-18 | 2013-03-15 | 2013-06-18 | 99 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | OH | OHIO | DLA Land & Maritime Columbus | DSCC1201 | Security Enhancements | 2012-02-19 | 2012-05-03 | Pinnacle Construction Development Group | 8550 | 9041 | 2012-06-03 | 2014-01-06 | 2013-10-16 | 2013-10-16 | 30 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | OK | OKLAHOMA | Altus Air Force Base | DESC1201 | Replace Fuel Transfer Pipeline | 2012-03-26 | 2012-09-17 | Reliable Contracting Group, LLC | 8856 | 8856 | 2012-11-01 | 2014-05-27 | 2014-03-01 | 2014-03-01 | 73 | 1322 | Additional funds from Davis Monthan
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | PA | PENNSYLVANIA | DLA Troop Support Philadelphia | DSCP1201 | Upgrade HVAC System | 2012-03-28 | 2012-06-01 | WU & Associates, Inc | 4775 | 6635 | 2012-06-14 | 2013-09-19 | 2013-07-17 | 2013-09-15 | 96 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | SC | SOUTH CAROLINA | Charleston Air Force Base | DESC1101 | Replace Fuel Storage Facility | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | 26085 | 26134 | 2012-11-30 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 33 | 5132 | Additional funds from Formal Reprogramming
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | WA | WASHINGTON | McChord Air Force Base | DESC1004 | Replace Hydrant Fuel System | 2011-10-28 | 2012-02-02 | Garco Construction, Inc. | 10217 | 10507 | 2012-02-27 | 2013-09-15 | 2013-05-17 | 2013-05-17 | 90 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | WA | WASHINGTON | NAS Whidbey Island | DESC1104 | Replace Fuel Pipeline | 2012-03-20 | 2013-02-28 | Talon Industries Inc. | 16984 | 16984 |  | 2014-08-30 | 2014-08-30 | 2014-08-30 | 5 | 0
2013-07-31 | 2013-08-13 | 2012 | DLA | MC | WV | WEST VIRGINIA | Camp Dawson | DESC12S1 | Replace Hydrant Fuel System | 2012-04-26 | 2012-07-05 | Kinley Construction Company | 1930 | 1930 | 2012-07-03 | 2013-12-01 | 2013-12-05 | 2013-12-05 | 5 | 0
2013-07-31 | 2013-08-13 | 2013 | DLA | UMMC | CA | CALIFORNIA | DLA Distribution Tracy | DRMS12U2 | Warehouse 6 Distribution | 2013-05-01 | 2013-05-15 | Kinley Construction Company | 925 | 925 | 2013-06-01 | 2014-10-04 | 2013-12-05 | 2013-08-29 | 0 | 0
2013-07-31 | 2013-08-13 | 2013 | DLA | MC | NC | NORTH CAROLINA | Seymour Johnson AFB | DESC13S1 | Replace Transfer Fuel Line to Pump House #2 | 2013-02-27 | 2013-07-09 | Shaw Environmental & Infrastructure, Inc | 1494 | 1494 | 2013-08-07 | 2014-04-18 | 2014-04-18 | 2014-04-18 | 0 | 0
2013-08-05 | 2013-08-05 | 2012 | DSS | Military Construction | VA | VIRGINIA | QUANTICO | P646 | DSS Headquarters Addition | Phase I - 21-Sep-2012 Phase II - 20-Dec-2012 | 2013-03-29 | Hensel Phelps Construction Co. | 25149100 | 27587740 | 2013-04-30 | 2014-07-22 | 2014-07-22 | 2014-07-22 | 15 |  |  |  | None
2013-08-05 | 2013-08-05 | 2012 | DSS | Military Construction | VA | VIRGINIA | QUANTICO | P659 | Defense Access Road Improvements-Telegraph Rd | Phase I - 22-Jan-2013 Phase II - 04-Apr-2013 | 2013-07-15 | Shirley Contracting Company, LLC | 2967875 | 2967875 | 2013-08-01 | NA | 2014-08-01 | 2014-09-05 | 0 |  |  |  | This project is being managed and funded via FHWA
2013-07-31 | 2013-08-13 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | 61772 | Operations Complex | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 16751 | 16751 | 2013-04-24 | 2012-01-31 | 2013-12-12 | 2013-10-13 | 51 | 3966
2013-07-31 | 2013-08-13 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | AFSOC033003 | Vehicle Maintenance Facility | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 4575 | 4575 | 2013-04-24 | 2012-01-31 | 2013-04-24 | 2013-10-13 | 51 | 2043
2013-07-31 | 2013-08-13 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | AFSOC033005 | Storage Facility | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 3603 | 3603 | 2013-04-24 | 2012-01-31 | 2013-04-24 | 2013-10-13 | 51 | 1368
2013-07-31 | 2013-08-13 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | AFSOC033019 | Air Operations Center | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 2931 | 2931 | 2013-04-24 | 2012-01-31 | 2013-04-24 | 2013-10-13 | 51 | -2042
2013-07-31 | 2013-08-13 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | ALUA073010 | Logistics Storage Warehouse | 2009-02-13 | 2009-09-01 01:00 | IAP Worldwide Services, Inc | 6639 | 6804 | 2011-02-05 | 2009-11-12 | 2012-11-15 | 2012-11-12 | 85 | 666
2013-07-31 | 2013-08-13 | 2008 | SOCOM | Major Construction | FL | FLORIDA | MacDill AFB | NVZR53712A | SOF 501D Building Addition Phase II (Parking Garage), MacDill AFB, FL | 2008-05-16 | 2012-09-27 | RUSH RORE, Joint Venture | 1015 | 1178 | 2013-03-11 | 2012-12-03 | 2013-08-31 | 2013-08-31 | 93
2013-07-31 | 2013-08-13 | 2009 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 26542 | Expand Training Compound | 2009-01-09 | 2009-09-10 01:00 | Heery International, Inc. | 11823 | 12745 | 2011-07-02 | 2009-10-15 | 2012-04-01 | 2012-09-24 | 99 | 638
2013-07-31 | 2013-08-13 | 2009 | SOCOM | Major Construction | WA | WASHINGTON | Ft Lewis | 50347 | Ranger Battalion Complex | 2009-04-20 | 2009-08-13 01:00 | Korte Construction Company | 24176 | 25423 | 2011-05-16 | 2009-09-23 | 2011-03-17 | 2011-03-24 | 99 | -11240
2013-07-31 | 2013-08-13 | 2009 | SOCOM | Major Construction | FL | FLORIDA | MacDill AFB | NVZR063711 | Add / Alter 501B (HQ SOCOM) | 2010-10-28 | 2011-03-30 | Carothers Construction, Inc. | 7186 | 7128 | 2012-09-20 | 2011-05-09 | 2013-11-11 | 2013-10-10 | 94 | -262
2013-07-31 | 2013-08-13 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 61874 | Battalion & Company Headquarters | 2009-11-13 | 2010-09-30 01:00 | Windamir Development, Inc | 9327 | 11049 | 2012-03-16 | 2010-11-02 | 2014-01-11 | 2014-01-11 | 99 | -3379
2013-07-31 | 2013-08-13 | 2010 | SOCOM | Major Construction | WA | WASHINGTON | Ft Lewis | 65446 | Support Company Facility | 2010-04-09 | 2010-09-22 01:00 | Vet Industrial, Inc. | 10947 | 11474 | 2012-10-04 | 2011-01-05 | 2012-12-03 | 2012-10-04 | 99 | -509
2013-07-31 | 2013-08-13 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 66315 | Operations Addition North | 2010-04-27 | 2010-08-05 01:00 | Sauer, Inc. | 18649 | 19420 | 2013-02-10 | 2010-08-25 | 2014-01-30 | 2013-11-01 | 87 | -3756
2013-07-31 | 2013-08-13 | 2010 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063019 | Fuel Cell Hangar (MC-130) | 2009-09-24 | 2010-04-09 01:00 | Hensel Phelps Construction Co. | 32766 | 34369 | 2012-02-26 | 2010-05-11 | 2012-12-24 | 2013-03-15 | 99 | 1159
2013-07-31 | 2013-08-13 | 2010 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063035 | AMU Addition (CV-22) | 2010-08-10 | 2010-10-25 01:00 | A4 Construction Company, Inc. | 9530 | 13961 | 2012-08-07 | 2010-12-16 | 2013-09-10 | 2013-09-10 | 98 | 4274
2013-07-31 | 2013-08-13 | 2010 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073015 | AC-130 Munitions Loadout Apr Ph 1 (Insert) | 2010-08-20 | 2010-09-30 01:00 | Nick Griego & Son's Construction, Inc. | 6196 | 10918 | 2011-10-29 | 2010-11-03 | 2012-10-10 | 2012-10-08 | 99 | 861
2013-07-31 | 2013-08-13 | 2010 | SOCOM | Major Construction | CA | CALIFORNIA | NAB Coronado | P-781 | Close Quarters Combat Facility | 2010-08-17 | 2011-09-30 | Barnhart Balfour Beatty Inc. | 13684 | 13684 | 2013-04-22 | 2011-10-15 | 2013-05-30 | 2013-08-30 | 75 | 28
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | AZ | COLORADO | Yuma | 62070 | Military Free Fall Simulator | 2011-04-11 | 2012-06-21 | Pilkington Commercial Co., Inc. | 10030 | 10030 | 2013-12-30 | 2012-07-02 | 2014-03-06 | 2014-01-05 | 78 | 1954
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 64484 | Operations Additions | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | 13388 | 13815 | 2014-06-10 | 2011-08-25 | 2014-11-07 | 2014-06-10 | 49 | -12352
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | KY | KENTUCKY | Ft Campbell | 64989 | Battalion Operations Complex | 2010-11-16 | 2011-07-06 | Korte Construction Company | 21572 | 23665 | 2013-06-05 | 2011-08-05 | 2013-07-24 | 2013-07-17 | 99 | -12144
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | GA | GEORGIA | Ft Benning | 65395 | Company Support Facility | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | 15392 | 15551 | 2013-06-12 | 2011-12-27 | 2013-10-29 | 2013-08-17 | 85 | -1431
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 66362 | C4 Facility - JSOC | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | 41446 | 42914 | 2014-06-26 | 2012-06-14 | 2014-06-30 | 2014-06-26 | 35 | 8466
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 66443 | Operations Support Facility | 2010-12-23 | 2011-06-20 | SFL+A Architects, AP | 9591 | 10145 | 2012-09-18 | 2011-07-19 | 2013-10-02 | 2013-05-31 | 99 | -266
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 66444 | Operational Communications Facility - JCU | 2011-02-18 | 2011-08-10 | Pacific Tech Sauer J.V. | 9674 | 9864 | 2012-12-26 | 2011-09-14 | 2013-11-27 | 2013-05-31 | 94 | 677
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | GA | GEORGIA | Ft Benning | 69261 | MWD Kennel Complex | 2010-12-17 | 2011-09-30 | Komada, LLC | 3103.928 | 3227 | 2013-02-09 | 2012-01-09 | 2013-05-09 | 2013-03-07 | 99 | -16
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | CO | COLORADO | Ft Carson | 69278 | TUAV Hangar | 2011-07-07 | 2012-04-06 | Iron Mike Construction LLC | 3506 | 3526 | 2013-08-09 | 2012-05-16 | 2013-10-22 | 2013-08-23 | 79 | 459
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69573 | Admin/Company Operations | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | 8487 | 9166 | 2013-04-18 | 2011-10-27 | 2013-11-21 | 2013-10-10 | 87 | 19
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 76511 | Joint Intelligence Brigade | 2011-05-12 | 2011-09-30 | Archer Western Contractors | 28900 | 30114 | 2013-05-11 |  | 2014-02-18 | 2013-08-22 | 95 | 1200
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Ft Bragg | 78253 | Electronic Equipment Lab | 2011-09-19 | 2011-09-30 | Kiewit Federal Services | 1411 | 1785 | 2012-09-29 | 2011-09-30 | 2012-11-02 | 2012-12-27 | 94
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063049 | Hangar / AMU (MC-130J) | 2011-05-13 | 2011-09-09 | Speegle Construction | 19432 | 20063 | 2013-10-30 | 2011-10-11 | 2014-02-05 | 2014-01-22 | 77 | -309
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063051 | Aircraft Parking Apron | 2011-02-23 | 2011-08-03 | Sundt Corporation | 23744 | 24810 | 2012-11-03 | 2011-10-05 | 2012-10-12 | 2012-10-10 | 99 | -1139
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063052A | Operations & Training Complex (3rd UAS) | 2011-04-15 | 2011-10-26 | Speegle Construction | 13614 | 13280 | 2013-07-17 | 2012-09-06 | 2014-05-12 | 2014-03-28 | 68 | -7389
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063052B | Operations & Training Complex (130 SOS Sq Ops) | 2011-04-15 | 2011-10-26 | KL House | 13260 | 16851 | 2013-01-13 | 2012-01-10 | 2013-06-15 | 2013-05-16 | 99
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063054A | C-130 Parking Apron (RECAP), Phase 1 | 2011-02-23 | 2011-08-03 | Sundt Corporation | 16206.9 | 16206.9 | 2012-11-03 | 2011-10-05 | 2012-11-03 | 2012-12-24 | 99 | -2261
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063054B | C-130 Parking Apron (RECAP), Phase 1 | 2011-02-23 | 2011-08-03 | Hensel Phelps Construction Co. | 3213 | 4616 | 2012-10-04 | 2011-10-05 | 2013-03-04 | 2013-03-15 | 99
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073012 | ADAL Simulator Facility for MC-130 (RECAP) | 2011-05-26 | 2011-08-25 | PACE Pacific Corporation | 8868 | 9421 | 2013-05-27 | 2011-11-03 | 2013-05-27 | 2013-05-27 | 98 | -291
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Minor Construction | FL | FLORIDA | Hurlburt Field | FTEV063000 | Squad Ops Annex 4 SOS (1UMC) | 2011-03-28 | 2011-06-23 | DWG & Associates, Inc. | 1629 | 1629 | 2012-11-17 | 2011-09-22 | 2012-11-20 | 2013-02-18 | 97
2013-07-31 | 2013-08-13 | 2011 | SOCOM | Major Construction | HI | HAWAII | Pearl Harbor | P-462 | NSWG3 Command & Ops Facility | 2011-01-19 | 2011-06-16 | dkc/TtEC, LLC | 17886 | 17886 | 2013-01-07 | 2011-07-01 | 2013-02-28 | 2013-03-08 | 99 | -6266
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 60272 | Communications Training Complex (SWCS) | 2012-04-11 | 2012-07-24 | GSC Construction Inc. |  | 8354 | 2013-08-23 |  | 2014-07-04 | 2014-03-06 | 23 | -72
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 60821 | Squadron Headquarters Addition | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | 10605 | 10671 | 2013-12-09 | 2012-06-06 | 2014-08-18 | 2013-12-09 | 36 | 1352
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | KY | KENTUCKY | Ft Campbell | 66598 | Rotary Wing Hangar | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | 34350 | 34611 | 2014-02-28 | 2012-04-16 | 2014-04-16 | 2014-04-04 | 31 | -170
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69277 | Entry Control Point | 2012-04-24 | 2012-07-30 | Lifecyle Construction Services, LLC | 2196 | 2229 | 2014-02-27 |  | 2013-11-23 | 2013-08-29 | 74 | 391
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69458 | Battalion Operations Complex | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors |  | 16772 |  |  | 2014-10-01 | 2014-06-03 | 9 | -389
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69758 | Brigade Headquarters | 2012-05-09 | 2012-09-17 | JAAAT Technical Services |  | 16429 |  |  | 2014-05-08 | 2014-05-08 | 5 | 800
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 71224 | Group Headquarters | 2012-06-06 | 2012-09-25 | Engineering Design Technologies |  | 18341 | 2014-06-20 |  | 2014-08-29 | 2014-07-05 | 17 | -892
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | WA | WASHINGTON | Ft Lewis | 76363 | Company Operations Facility | 2012-04-18 | 2012-08-30 | Adept - Absher 1 Joint Venture | 18751 | 18957 |  |  | 2014-06-21 | 2014-04-22 | 28 | 59
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 76364 | Battalion Operations Facility | 2012-06-20 | 2012-10-25 | Engineering Design Technologies | 29232 | 29247 | 2014-07-28 |  | 2014-10-27 | 2014-07-28 | 7 | -690
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | FL | FLORIDA | Eglin AFB | 76366 | Company Operations Facility (GSTB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | 16664 | 14746 | 2014-06-27 |  | 2016-04-26 | 2016-01-27 | 21 | 1736
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | FL | FLORIDA | Eglin AFB | 76371 | Company Operations Facility (GSB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | 19093 | 17143 | 2013-09-30 |  | 2016-04-26 | 2016-01-27 | 21 | -10
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 76373 | Administrative Annex | 2012-03-01 | 2012-06-21 | GSC Construction Inc |  | 10034 | 2013-12-10 |  | 2014-06-27 | 2014-03-17 | 32 | -48
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | KY | KENTUCKY | Ft Campbell | 76374 | MH-47 Hangar | 2011-11-28 | 2012-05-07 | Hensel Phelps | 32450 | 33260 |  |  | 2014-07-08 | 2014-06-07 | 42 | -623
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Minor Construction | CO | COLORADO | Ft Carson | 80234 | SOF Classified Operations Facility (4UMC) | 2012-03-21 | 2012-05-25 | Facilities Contracting, Inc. | 1822 | 1822 | 2012-12-16 | 2012-06-19 | 2012-12-16 | 2013-02-04 | 96
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073014 | SOF C-130 Sq Ops Facility | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | 18028 | 7432 | 2015-01-06 | 2012-11-09 | 2014-05-30 | 2014-02-22 | 28 | -1727
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073018 | SOF C-130 Wash Rack Hangar | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | 9329 | 9485 | 2014-07-18 |  | 2014-06-18 | 2014-04-10 | 33 | -72
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073021 | SOF AMXS Facility | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | 14700 | 14777 | 2014-12-22 | 2013-01-10 | 2014-09-22 | 2014-08-09 | 13 | 1537
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083011 | SOF Apron and Taxiway | 2012-04-23 | 2012-08-31 | Okland/Geneva Joint Venture | 26836 | 22391 | 2014-01-26 | 2012-10-03 | 2014-05-22 | 2014-02-22 | 41 | -342
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083012A | SOF Hangar/AMU | 2012-04-20 | 2012-08-31 | Hensel Phelps | 28160 | 28443 | 2014-12-23 | 2012-10-24 | 2015-01-05 | 2014-09-04 | 31 | -499
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083012B | SOF Hangar/AMU | 2012-04-20 |  | Oakland/Geneva Joint Venture | 4608 | 4626 | 2014-02-22 | 2012-10-30 | 2014-05-22 | 2014-02-22 | 4
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083014 | SOF ADAL Simulator Facility | 2012-04-17 | 2012-09-07 | PACE Pacific Corporation | 7349 | 7415 | 2014-01-26 | 2012-10-03 | 2014-03-25 | 2014-01-26 | 76 | -141
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083016 | SOF Squadron Operations Facility | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | 18028 | 10632 | 2015-01-06 | 2012-11-09 | 2014-05-30 | 2014-05-30 | 28 | -4292
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | FL | FLORIDA | Hurlburt Field | FTEV103011 | SOF Simulator Facility | 2012-05-01 | 2012-08-09 | Barlovento LLC. | 5551 | 5444 | 2013-12-24 | 2012-09-13 | 2014-05-06 | 2014-02-07 | 34 | -34
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | FL | FLORIDA | MacDill AFB | NVZR123709 | Acquistions Center Phase II (Prkg Garage) | 2012-05-15 | 2012-07-31 | The Clement Group, L.L.C. | 8504 | 8486 | 2014-01-19 | 2012-09-06 | 2014-04-19 | 2014-02-07 | 66 | 1007
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | CA | CALIFORNIA | Camp Pendleton | P-1049 | Range 130 Support Projects | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | 8129 | 8129 | 2014-11-13 | 2013-06-03 | 2014-11-13 | 2014-11-13 | 5 | 675
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | CA | CALIFORNIA | Camp Pendleton | P-1174 | MWD Facility | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | 3075 | 3075 | 2014-03-23 | 2012-10-03 | 2014-03-23 | 2014-03-23 | 5
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1285 | Armory Facility Expansion | 2012-01-26 | 2012-05-07 | Team Construction, LLC. | 4004 | 4004 | 2013-08-30 | 2012-07-16 | 2013-09-30 | 2013-09-30 | 65 | -861
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1419 | Milam Aid Station Expansion (1UMC) | 2012-02-29 | 2012-04-19 | Graham Construction | 1465 | 1465 | 2013-04-19 | 2012-08-01 | 2013-08-02 | 2013-08-02 | 75
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1440 | SOF G3-X Training Facilities (5UMC) | 2012-08-20 | 2012-09-27 | Alderman Building Company, Inc. | 1541 | 1541 | 2013-09-22 | 2013-01-15 | 2013-11-14 | 2013-11-14 | 35
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | Dam Neck | P-164 | Logistics Support Facility | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | 11727 | 11727 | 2014-07-24 | 2012-12-09 | 2014-07-24 | 2014-07-24 | 5 | -151
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Minor Construction | VA | VIRGINIA | Dam Neck | P-504 | SOF Operational Vehicle Storage Facility (6UMC) |  | 2013-05-23 | Richard Brady & Associates, Inc. |  | 1660 |  |  |  |  | 5
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | AK | ARKANSAS | Kodiak | P-531 | Cold Weather Maritime Training Facility |  | 2012-09-27 | Alutiiq Diversified Service, LLC | 17449 | 17449 | 2015-04-15 |  | 2015-04-15 | 2015-04-15 | 5 | 1387
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | Dam Neck | P-769 | Building Renovation | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | 3022 | 3022 | 2014-06-27 | 2013-01-02 | 2014-06-27 | 2014-06-27 | 5 | -47
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | Dam Neck | P-826 | Military Working Dog Facility | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | 4139 | 4139 | 2014-07-24 | 2012-12-09 | 2014-07-24 | 2014-07-24 | 5 | -58
2013-07-31 | 2013-08-13 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Pope AFB | TMKH043055 | SOF Training Facility | 2012-01-31 | 2012-04-24 | JAAAT Technical Services, LLC | 4774 | 4783 | 2013-11-22 | 2012-05-31 | 2014-02-20 | 2013-11-22 | 33 | 100
2013-07-31 | 2013-08-13 | 2013 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Ft Bragg | 79655 | SOF Training Facility (2UMC) | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | 1592 | 1592 | 2014-10-15 | 2013-06-18 | 2014-10-29 | 2014-10-15 | 0
2013-06-28 | 2013-07-03 | 2009 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2009-1 | Pentagon Athletic Club (PAC) Phase II | 2009-10-08 | 2009-12-10 | HSU | 4765 | 5748 | 2009-12-17 | 2011-08-14 | 2010-12-16 | 2011-09-14 | 100 | -401 |  |  | $.400.83K to SAL ($99K remaining)
2013-06-28 | 2013-07-03 | 2009 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2009-3 | Pentagon Emergency Response Center (PERC) | 2009-02-05 | 2009-09-21 | THE CHRISTMAN COMPANY | 12469 | 14967 | 2009-09-28 | 2011-12-12 | 2011-07-20 | 2012-05-11 | 99.5 | -683 |  |  | $683.49K to SAL
2013-06-28 | 2013-07-03 | 2010 | WHS | Major construction | VA | VIRGINIA | Pentagon | N/A | Upgrade Electrical System | 2012-06-04 | TBD | TBD | [6 empty] | 0 | TBD |  |  | PERC-$437, Fuel Storage Fac-$200, Secondary UPS-$300, FY11 P&D-$3,782
2013-06-28 | 2013-07-03 | 2010 | WHS | Major construction | PA | PENNSYLVANIA | RRMC | N/A | Secondary UPS System | 2010-06-16 | 2010-09-27 | IRON BRIDGE CONSTRUCTION | 5192 | 7515 | 2010-09-27 | 2013-07-31 | 2012-02-29 | 2013-07-31 | 97
2013-06-28 | 2013-07-03 | 2011 | WHS | Major construction | PA | PENNSYLVANIA | RRMC | N/A | Power Plant Modernization Phase 3 West Power Plant | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc | 43594 | 43594 | 2013-04-22 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 0
2013-06-28 | 2013-07-03 | 2011 | WHS | Major construction | VA | VIRGINIA | Pentagon | N/A | Metro Entrance & Corridor 8 | 2012-01-10 | TBD | TBD | [6 empty] | 0
2013-06-28 | 2013-07-03 | 2011 | WHS | Major construction | VA | VIRGINIA | Pentagon | N/A | Secure Access Lane (SAL) | 2011-08-08 | TBD | TBD | [6 empty] | 0
2013-06-28 | 2013-07-03 | 2012 | WHS | Major construction | VA | VIRGINIA | Pentagon | N/A | Pentagon Heliport Control Tower and Fire Station | TBD | TBD | TBD | [6 empty] | 0
2013-06-28 | 2013-07-03 | 2012 | WHS | Major construction | VA | VIRGINIA | Pentagon | N/A | Pentagon West-End Safety Upgrade | TBD | TBD | TBD | [6 empty] | 0
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const BRAC | MD | MARYLAND | Bethesda | 401V | Traffic Mitigation Increment 1 | 2010-03-05 | 2010-05-10 | Clark/Balfour Beatty, Joint Venture, Gates N&S Wood Dr | 9512 | 10848 |  |  | 2010-03-10 | 2012-07-12 | 100
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const BRAC | MD | MARYLAND | Bethesda | 401V | Traffic Mitigation Increment 1 | 2010-03-16 | 2010-06-21 | Whiting-Turner, University Road & Perimeter Road/Palmer Road | 6800 | 10291 | 2010-07-01 |  | 2011-08-31 | 2011-08-31 | 100
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const BRAC | MD | MARYLAND | Bethesda | 401A | Traffic Mitigation Increment 2 | 2010-11-14 | 2011-04-21 | RMA Land Construction Inc, Gates Gunnell & Grier | 5132 | 5982 |  |  | 2012-12-06 | 2012-12-06 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 64238 | Hospital Replacement, Increment 1 | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV | 649025 | 9428 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const BRAC | MD | MARYLAND | Bethesda Naval Hospital | 005V | Medical Center Addition/Alteration, Inc 1 | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | 109025.544 | 774314 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2011-09-11 | 100 |  |  |  | 100% ADD 100% ALT
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 64241 | Dental Clinic | 2009-09-16 | 2010-05-04 | Forrester Construction Company | 7541 | 8818 | 2010-05-18 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const BRAC | MS | MISSISSIPPI | Keesler AFB | 478V | Community Hospital | 2009-04-09 | 2009-11-10 | W.G. Yates & Sons Constuction Co | 37258 | 42256 | 2010-01-01 | 2012-12-11 | 2011-09-11 | 2012-10-11 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const BRAC | MD | MARYLAND | Bethesda | 020V | Site Utility Infra Upgrade for NICoE | 2008-07-08 | 2008-12-22 | Turner Construction Company | 7294.531 | 7371 | 2009-01-01 | 2010-03-29 | 2010-03-06 | 2010-04-30 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 64188 | Health Clinic | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | 33382 | 37429 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const BRAC | MD | MARYLAND | Bethesda | 796V | Supt Fac for WTC Admin Ctr (BQ/Dining) | PH II Apr 09 | 2009-08-26 | Whiting-Turner | 117555 | 126445 | 2010-02-01 | 2011-08-01 | 2011-08-31 | 2011-09-11 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const BRAC | MD | MARYLAND | Bethesda | 701V | Consolidation of Administration Spaces (WTU Admin) | PH II Apr 09 | 2009-08-26 | Whiting-Turner | 63440 | 78196 | 2010-02-01 | 2011-08-01 | 2011-08-31 | 2011-09-11 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 65731 | USAMRICD Replacement, Inc 1 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | 6887.87 | 7070.1979 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67180 | USAMRICD Replacement, Inc 2 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67180 | USAMRICD Replacement, Inc 2 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2007-06-30 | 2007-09-29 | Cont # 1 - Offiste San Sewer & Storm (James Construction) | 2657 | 2657 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2008-01-10 | 2008-08-01 | Con # 2 - Storm Lat 1&3A (James Construction) | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2008-05-01 | 2009-09-28 | Con# 3 - IMP Pond (James Corporation) | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2008-01-10 | 2008-09-25 | Cont # 4 - Early Site/Utility (Grunley/Goel JVA LLC) | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2011-03-25 | 2011-06-17 | Janco - Water Tower | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const Incremental | FL | FLORIDA | MacDill AFB | 52330 | Clinic Replacement | 2007-02-16 | 2007-07-19 | Caddell Construction Co., Inc | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const Incremental | FL | FLORIDA | MacDill AFB | 67647 | Clinic Replacement, Inc II | 2007-02-16 | 2007-07-19 | Caddell Construction Co., Inc | 32890 | 42183 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const | AK | ARKANSAS | Fort Richardson | 64773 | Health Clinic | 2007-03-02 | 2007-05-16 | Bristol Design Build Services LLC | 26317 | 29824 | 2007-03-01 | 2009-01-01 | 2009-09-15 | 2009-01-21 | 100 | 4000
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const | CA | CALIFORNIA | Fort Irwin | 47627 | Dental Clinic Addition/Alteration | 2006-11-24 | 2007-03-30 | Hal Hays Construction, Inc. | 4736 | 4864 | 2007-05-16 | 2008-08-12 | 2008-09-07 | 2008-09-21 | 100 | 751
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const | IL | ILLINOIS | NH Great Lakes | 55924 | Fed Health Care, (Parking Structure) (Total Auth = $133M) | 2006-08-28 | 2007-05-25 | Joseph J Henderson & Son, Inc | 16061.8 | 17588 | 2007-07-02 | 2008-12-30 | 2008-06-30 | 2008-12-30 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const | HI | HAWAII | NS Pearl Harbor | 59178 | EPMU 6 Replacement Facility | 2006-10-30 | 2007-07-05 | Primatech Construction, Inc | 6763 | 6950 | 2007-09-01 | 2009-03-26 | 2008-11-26 | 2009-03-26 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const | NY | NEW YORK | Fort Drum | 57724 | Dental Clinic | 2007-03-28 | 2007-07-16 | SLR Contracting & Service Co., Inc | 8121 | 8468 | 2007-08-13 | 2009-05-20 | 2009-02-03 | 2009-04-20 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const | TX | TEXAS | Fort Hood | 59210 | Women's Health Add/Alt | 2006-11-06 | 2008-03-07 | Akima Construction Services | 17545 | 17820 | 2008-04-08 | 2010-12-17 | 2010-04-08 | 2010-11-17 | 100
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const | ITA | ITALY | Vicenza | 62455 | Enhanced Health Service Center**Foreign Currency | 2007-02-12 | 2007-08-16 | Consorzio Bilfinger Berger Pizzarotti | 34790.371 | 37828 |  |  | 2010-04-27 | 2010-09-15 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | FL | FLORIDA | MacDill AFB | 64809 | Pharmacare Addition/Alteration | 2007-09-27 | 2008-02-29 | J2 Engineering, Inc | 3381 | 3489 | 2008-03-24 | 2009-03-24 | 2009-03-24 | 2009-03-24 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | IL | ILLINOIS | NH Great Lakes | 65028 | Federal Healthcare Facility | 2007-10-01 | 2008-02-27 | Flannery Fire Protection | 6782 | 7382 | 2008-04-01 | 2009-09-02 | 2009-09-02 | 2009-09-02 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | IL | ILLINOIS | NH Great Lakes | 65028 | Federal Healthcare Facility | 2008-02-22 | 2008-06-17 | Walsh Construction Company of Illinois | 71567 | 75921 | 2008-08-01 | 2010-10-01 | 2010-07-31 | 2010-09-27 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | NC | NORTH CAROLINA | Camp Lejeune | 71857 | Hospital Addition | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | 31112 | 32617 | 2010-12-03 | 2013-06-03 | 2013-01-12 | 2013-09-27 | 99.9 | 3486
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | TX | TEXAS | Camp Bullis | 17153 | Health Clinic Replacement | 2008-02-15 | 2008-05-08 | Guyco, Inc. | 5214 | 5430 | 2008-05-08 | 2009-11-18 | 2009-11-16 | 2010-03-17 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | VA | VIRGINIA | NS Norfolk | 53577 | Environ. Prev. Med Unit 2 Replacement | 2008-10-31 | 2009-03-31 | Virtexco Corporation | 5951 | 6558 | 2009-05-01 | 2010-10-15 | 2010-05-04 | 2010-09-08 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | WA | WASHINGTON | Fort Lewis | 64473 | Medical/Dental Clinic | 2008-07-29 | 2008-09-18 | The Korte Company | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 100 | 1885
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | DEU | GERMANY | Spangdahlem AB | 52332 | Medical Clinic Replacement | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | CO | COLORADO | Buckley AFB | 64709 | Satellite Pharmacy | 2009-03-04 | 2009-05-21 | Liberty-Mass II | 1963 | 2014 | 2009-02-13 | 2010-09-03 | 2010-09-09 | 2010-09-09 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | FL | FLORIDA | NAS Jacksonville | 971B | Hospital Alteration (ARRA) | 2009-09-09 | 2009-12-18 | Brasfield & Gorrie, LLC | 8000 | 13282 | 2010-01-20 | 2011-12-11 | 2011-12-11 | 2011-12-11 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | GA | GEORGIA | Fort Benning | 65080 | Consolidated Troop Medical Clinic | 2008-11-12 | 2009-02-25 | Mathis and Sons, Inc. | 2983 | 3084 | 2009-03-16 | 2010-05-07 | 2010-03-16 | 2010-05-07 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | KY | KENTUCKY | Fort Campbell | 64573 | Medical/Dental Clinic | 2008-12-10 | 2009-05-26 | The Korte Company | 14342 | 14700 | 2009-05-22 | 2011-03-30 | 2011-05-15 | 2011-03-30 | 100 | 3867
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | MD | MARYLAND | Bethesda | 75585 | Vision Center of Excellence | 2010-02-17 | 2010-06-25 | Clark/Balfour Beatty, Joint Venture | 3473 | 3900 | 2011-03-01 | 2011-08-01 | 2011-07-31 | 2011-07-31 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | MO | MISSOURI | Fort Leonard Wood | 59987 | Primary Care Clinic Addition/Alteration | 2009-04-15 | 2009-07-15 | MAXFour Weitz JV | 13627 | 14503 | 2009-08-24 | 2011-07-28 | 2011-05-30 | 2011-07-28 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | OH | OHIO | Wright-Patterson AFB | 72722 | Tree Cutting | 2011-03-07 | 2011-03-20 | A1 Tree Service | 10 | 10 | 2011-03-20 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | TX | TEXAS | Fort Hood | 74650 | Sanitary Sewer | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc, Sanitary Sewer | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | TX | TEXAS | Fort Hood | 74650 | Relocation of Gas & Electric Utilities | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | TX | TEXAS | Fort Hood | 74650 | Demolition of Hood Stadium | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc., Demolition of Hood Stadium | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 100
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | TX | TEXAS | Fort Sam Houston | 53341 | Medical Instructional Facility | 2008-11-13 | 2009-02-20 | Innovative Technology Solutions, Inc | 10432 | 15334 | 2010-01-27 | 2012-08-14 | 2010-06-02 | 2010-11-12 | 100 | -1539
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | GUM | GUAM | NH Guam | 55918 | Central Utility Plant | 2009-03-15 | 2009-09-15 | PDI - HSW Joint Venture | 13034 | 13672 | 2009-10-01 | 2011-06-01 | 2011-02-07 | 2011-02-07 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | AK | ALASKA | Elmendorf AFB | 71310 | Aeromedical Services/Mental Health Clinic | 2009-09-18 | 2010-02-25 | Davis Constructors & Engineers, Inc. | 19839 | 20258 | 2010-03-11 | 2011-11-29 | 2011-10-15 | 2011-11-29 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | AK | ALASKA | Fort Richardson | 69805 | Health Clinic Add/Alt | 2009-11-30 | 2010-02-10 | Bristol Design Build Services LLC | 3087 | 3140 | 2010-02-22 | 2011-03-18 | 2011-05-23 | 2011-03-18 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | CO | COLORADO | Fort Carson | 69295 | Health and Dental Clinics | 2010-04-26 | 2010-09-23 | Korte Construction Company | 17616 | 18171 | 2010-10-20 | 2012-02-27 | 2012-02-13 | 2012-02-27 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | GA | GEORGIA | Fort Benning | 64481 | Blood Donor Center Replacement | 2009-11-05 | 2010-09-24 | IAP-Leopardo | 7792 | 7904 | 2010-11-12 | 2012-08-05 | 2012-05-05 | 2012-05-05 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | GA | GEORGIA | Fort Benning | 71620 | Dental Clinic | 2009-12-23 | 2010-03-31 | EJS Contracting, Inc. | 2549 | 2619 | 2010-04-28 | 2011-03-11 | 2011-04-28 | 2011-03-11 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | GA | GEORGIA | Fort Stewart | 70481 | Health and Dental Clinics | 2009-11-25 | 2010-09-30 | Brafield & Gorrie, LLC | 9742 | 10101 | 2010-10-21 | 2012-06-04 | 2012-03-22 | 2012-03-22 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | KY | KENTUCKY | Fort Campbell | 70557 | Health Clinic Addition/Alteration | 2010-04-12 | 2010-09-27 | Charpie-Korte Joint Venture | 4018 | 4034 | 2010-09-30 | 2011-06-30 | 2012-02-05 | 2011-06-30 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 67948 | NIBC Truck Inspection Station & Road | 2010-09-02 | 2010-10-29 | CFM Engineering | 2880 | 3132 | 2010-12-15 | 2012-07-05 | 2011-12-15 | 2012-07-05 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | MO | MISSOURI | Fort Leonard Wood | 64153 | Dental Clinic Addition/Alteration | 2009-10-20 | 2010-07-02 | TMG Services | 3890 | 4319 | 2010-07-22 | 2012-03-19 | 2012-01-13 | 2012-03-15 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | NC | NORTH CAROLINA | Fort Bragg | 64244 | Consolidated Health Clinic | 2009-10-28 | 2010-09-30 | Korte Construction Company | 15313 | 15501 | 2010-10-21 | 2012-10-26 | 2012-05-18 | 2012-10-26 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | NC | NORTH CAROLINA | Fort Bragg | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | OK | OKLAHOMA | Fort Sill | 69711 | Dental Clinic | 2009-11-03 | 2010-06-16 | The Korte Company | 8199 | 8199 | 2010-07-30 | 2012-03-04 | 2012-01-04 | 2012-01-04 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | TX | TEXAS | Fort Bliss | 69294 | Health and Dental Clinics | 2010-02-17 | 2010-11-17 | LEC-CMS, LP | 12743 | 13226 | 2011-02-07 | 2012-08-20 | 2012-05-22 | 2012-12-31 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | TX | TEXAS | Lackland AFB | 71318 | Dental Clinic Replacement | 2009-10-28 | 2010-02-26 | J E Dunn Construction Company | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 100 | 439
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | WA | WASHINGTON | Fort Lewis | 70343 | Health and Dental Clinic Additions | 2009-12-04 | 2010-03-24 | Vet Industrial of Bremerton, WA | 7219 | 7583 | 2010-04-19 | 2011-05-13 | 2011-05-07 | 2011-05-02 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | TX | TEXAS | Lackland AFB | 72430 | Ambulatory Care Center, Phase 1 A | 2010-06-11 | 2010-08-31 | J E Dunn Construction Company (Parking Structure & Temp Parking)) | 23216 | 24085 | 2010-10-04 | 2012-12-13 | 2012-02-26 | 2013-08-01 | 100
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | GBR | UNITED KINGDOM | RAF Alconbury | 71550 | Medical/Dental Clinic Replacement | 2010-06-16 | 2010-12-14 | Vinci Construction UK | 13098 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 100
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | VA | VIRGINIA | Fort Belvoir | 71251 | Dental Clinic Replacement | 2009-09-16 | 2011-05-17 | Forrester Construction Company | 2832 | 3021 | 2011-05-17 | 2013-01-31 | 2012-07-11 | 2013-01-31 | 100
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 64179 | San Antonio Regional Medical Center, Inc 1 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 107589 | 135926 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 64180 | Brooke Army MEDCEN Increment 2 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 265100 | 279273 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 69840 | Brooke Army MEDCEN Increment 3 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 13748 | 243943 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 70990 | Brooke Army MEDCEN Increment 4 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 37554 | 85444 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const BRAC | MD | MARYLAND | Aberdeen Proving Ground | 64156 | USAMRICD Replacement, Inc 1 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contractor for main building) | 14398 | 15291.5103 | 2010-03-15 | 2013-09-24 | 2013-06-01 | 2014-05-30 | 91
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 65731 | USAMRICD Replacement, Inc 1 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 12000 | 12562.6925 | 2010-03-15 | 2013-09-24 | 2013-06-01 | 2014-05-30 | 92
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67180 | USAMRICD Replacement, Inc 2 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 100375 | 103745.3283 | 2010-03-15 | 2013-09-24 | 2013-06-01 | 2014-05-30 | 92
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67181 | USAMRICD Replacement, Inc 3 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 94608 | 96044.5065 | 2010-03-15 | 2013-09-24 | 2013-06-01 | 2014-05-30 | 92
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67182 | USAMRICD Replacement, Inc 4 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 7915.345 | 15814.2788 | 2010-03-15 | 2013-09-24 | 2013-06-01 | 2014-05-30 | 92
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | SSP Mod | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | 2866 | 2866 | 2008-07-15 | 2013-07-31 | 2011-05-06 | 2013-05-25 | 99 | 1489
2013-07-31 | 2013-08-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 63418 | USAMRIID Replacement, Incr 2 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 15736 | 16159 | 2009-06-01 | 2014-11-30 | 2014-05-31 | 2014-10-21 | 86
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 63419 | USAMRIID Replacement, Incr 3 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 131264 | 137966 | 2009-06-01 | 2014-11-30 | 2014-05-31 | 2014-10-21 | 86
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 63419 | USAMRIID Replacement, Incr 3 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 185526 | 185526 | 2009-06-01 | 2014-11-30 | 2014-05-31 | 2014-10-21 | 86
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 63420 | USAMRIID Replacement, Incr 4 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 94000 | 100558 | 2009-06-01 | 2014-11-30 | 2014-05-31 | 2014-10-21 | 86
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 65324 | USAMRIID Replacement, Incr 5 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 13497 | 13497 | 2009-06-01 | 2014-11-30 | 2014-05-31 | 2014-10-21 | 86
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 71101 | USAMRIID Replacement, Incr 6 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 66955 | 84152 | 2009-06-01 | 2014-11-30 | 2014-05-31 | 2014-10-21 | 86
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const Incremental | MD | MARYLAND | Joint Base Andrews | 77154 | Ambulatory Care Center | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | 196430 | 131540 | 2013-03-01 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 4
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | 7782 | 7782 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-26 | 1
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. - Infrastructure | 39345 | 47508 | 2011-11-02 | 2013-10-12 | 2013-08-13 | 2013-08-29 | 99
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2012-03-16 | 2012-07-19 | VEMAC - Parking Pkg A | 3848 | 3879 | 2012-08-28 | 2013-10-17 | 2013-06-19 | 2013-06-11 | 99
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2013-02-19 | 2013-05-17 | El Paso Water Utility | 3960 |  | 2013-07-30 | 2014-12-15 | 2014-09-28 | 2014-09-28 | 0
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2012-02-08 | 2012-09-04 | El Paso Electrical Substation | 4047 | 4047 | 2012-09-04 | 2015-09-16 | 2014-01-04 | 2014-01-04 | 99
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 77251 | Fort Bliss Hospital Repl, Incr 2 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | 68076 | 68076 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-26 | 1
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72786 | Fort Bliss Hospital Repl, Incr 3 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | 69851 | 69851 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-26 | 1
2013-07-31 | 2013-08-15 | 2013 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 76558 | Fort Bliss Hospital Repl, Incr 4 | 2012-08-07 | 2013-01-29 | Hospital Contract (1st increment) | 79914 | 87985 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-26 | 1
2013-07-31 | 2013-08-15 | 2013 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 76558 | Fort Bliss Hospital Repl, Incr 4 | 2013-06-01 | 2013-09-02 | Helipad | 1540 | [5 empty] | 0
2013-07-31 | 2013-08-15 | 2013 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 76558 | Fort Bliss Hospital Repl, Incr 4 | 2013-10-01 | 2013-12-13 | Parking Pkg B | 5562 | [5 empty] | 0
2013-07-31 | 2013-08-15 | 2014 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 77293 | Fort Bliss Hospital Repl, Incr 5 | 2012-08-07 | 2013-01-29 | Hospital Contract (2nd increment) | 198148 |  | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-26 | 1
2013-07-31 | 2013-08-15 | 2014 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 77293 | Fort Bliss Hospital Repl, Incr 5 | 2013-12-16 | 2014-12-20 | ACPs | 24755 | [5 empty] | 0
2013-07-31 | 2013-08-15 | 2015 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 81047 | Fort Bliss Hospital Repl, Incr 6 | 2012-08-07 | 2013-01-29 | Hospital Contract (3rd increment) | 225199 |  | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-26 | 1
2013-07-31 | 2013-08-15 | 2015 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 81047 | Fort Bliss Hospital Repl, Incr 6 | 2013-12-16 | 2015-06-30 | Landscaping | 22616 |  | 2015-07-30 |  |  |  | 0
2013-07-31 | 2013-08-15 | 2016 | TMA | Major Const Incremental | TX | TEXAS | Fort Bliss | 81408 | Fort Bliss Hospital Repl, Incr 7 | 2012-08-07 | 2013-01-29 | Hospital Contract (4th increment) | 56858 |  | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-26 | 1
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const Incremental | GUM | GUAM | NAVHOSP Guam | 65270 | Hospital Replacement Increment 1 | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | 158132.5 | 163302 | 2010-11-01 | 2014-05-01 | 2014-10-15 | 2015-01-01 | 81
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const Incremental | TX | TEXAS | Joint Base San Antonio | 72754 | Ambulatory Care Center Phase 3, Inc 1 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | 76038 | 72267 | 2012-11-01 | 2015-01-30 | 2014-07-29 | 2014-10-03 | 36
2013-07-31 | 2013-08-15 | 2013 | TMA | Major Const Incremental | TX | TEXAS | Joint Base San Antonio | 80793 | Ambulatory Care Center Phase 3, Increment 2 | 2012-05-09 | 2013-06-03 |  | 16319 | 16319 | 2012-11-01 | 2015-01-30 | 2014-07-29 | 2014-10-03 | 36
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | GA | GEORGIA | Fort Benning | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) | 2009-04-08 | 2009-09-28 | Turner Construction Co., Inc | 230018 | 267547 | 2009-10-22 | 2014-05-19 | 2013-02-03 | 2014-05-19 | 70
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | KS | KANSAS | Fort Riley | 47298 | Hospital Replacement | 2009-02-06 | 2009-09-30 | Balfour Beatty/Walton JV | 324110 | 282778 | 2010-05-03 | 2014-06-01 | 2013-07-23 | 2013-12-31 | 75
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | NY | NEW YORK | Fort Drum | 63864 | Health Clinic Add/Alt | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | 27483 | 35946 | 2008-11-07 | 2012-12-01 | 2011-02-18 | 2012-12-14 | 99
2013-07-31 | 2013-08-15 | 2008 | TMA | Major Const | TX | TEXAS | Fort Sam Houston | 69626 | Burn Rehabilitation Center | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | 18512 | 19120 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | CA | CALIFORNIA | Camp Pendleton | 71653 | Hospital Replacement, (ARRA) | 2010-06-11 | 2010-09-01 | Clark/McCarthy, A joint Venture | 393883 | 427274 | 2010-12-03 | 2014-01-07 | 2014-01-07 | 2014-01-07 | 95
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | CO | COLORADO | Fort Carson | 70350 | Hospital Alteration (ARRA) | 2011-07-26 | 2011-09-15 | Federal Contracting dba Bryan Construction | 15929 | 20393 | 2011-10-11 | 2014-03-13 | 2013-11-27 | 2014-01-12 | 80
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | CA | CALIFORNIA | Fort Irwin | 70354 | Hospital Replacement (SUPPLEMENTAL) | 2011-12-19 | 2012-05-09 | Turner Construction Company | 159834 | 162257 | 2012-05-30 | 2016-02-16 | 2015-03-16 | 2015-03-16 | 1
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | FL | FLORIDA | Eglin AFB (ARRA) | 79845 | Eglin Hospital Alteration | 2011-07-01 | 2011-09-23 | JE Dunn Construction | 51133 | 58067 | 2011-10-31 | 2015-04-10 | 2015-01-10 | 2015-02-09 | 65
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | NC | NORTH CAROLINA | Camp Lejeune | 73559 | Hospital Renovation & MRI Addition (Cong Add) | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | 26178 | 26466 | 2010-12-03 | 2014-04-01 | 2015-01-02 | 2015-01-02 | 32
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | NY | NEW YORK | UMA West Point | 59220 | Hospital Addition/Alteration (Supplemental) | 2011-06-10 | 2011-09-28 | Morgan Construction Enterprises,Inc | 28500 | 30230 | 2011-10-26 | 2014-01-24 | 2014-03-03 | 2013-10-25 | 46
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | OH | OHIO | Wright-Patterson AFB | 72722 | Hospital Renovation (Supplemental) | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | 71356 | 75714 | 2011-10-25 | 2014-12-09 | 2014-09-09 | 2014-09-09 | 40
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | OH | OHIO | Wright-Patterson AFB | 72722 | Swing Space | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp | 5578 | 5578 | 2011-07-01 | 2011-12-05 | 2014-09-27 | 2014-09-27 | 86
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | OK | OKLAHOMA | Tinker AFB | 62189 | Medical/Dental Clinic Replacement | 2008-10-27 | 2009-04-03 | Hensel Phelps | 47615 | 51375 | 2009-06-01 | 2012-06-04 | 2011-10-26 | 2012-02-09 | 98
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | TX | TEXAS | Fort Hood | 74650 | Hospital Replacement, Phase 1 (100% ARRA) | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | 529989 | 544572 | 2010-11-08 | 2014-08-29 | 2014-05-31 | 2014-07-20 | 49
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | TX | TEXAS | Fort Hood | 74728 | Hospital Replacement, Phase 2 (100% ARRA) | 2010-05-21 | 2010-06-11 | RMA Land Construction, Inc., Infrastructure, Electrical Distribution & Telecomm | 9698 | 10156 | 2010-07-20 | 2014-08-29 | 2012-01-11 | 2014-07-20 | 49
2013-07-31 | 2013-08-15 | 2009 | TMA | Major Const | TX | TEXAS | Fort Hood | 74650 | New Stadium | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. New Stadium | 17290 | 15383 | 2011-01-06 | 2013-06-13 | 2012-06-29 | 2013-08-31 | 89
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 61401 | Boundary Gate at Nallin Pond | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | 9075 | 9160 | 2011-01-11 | 2014-05-30 | 2013-01-10 | 2014-02-27 | 78
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 61536 | Emergency Service Center | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | 13478 | 13635 | 2010-07-19 | 2013-05-25 | 2012-09-16 | 2013-05-22 | 99
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | TX | TEXAS | Lackland AFB | 72430 | Ambulatory Care Center, Phase 1 B | 2010-06-11 | 2010-08-19 | J E Dunn Construction Company (Bldg 1 & CEP) | 41566 | 44895 | 2010-10-04 | 2013-08-31 | 2013-02-20 | 2013-07-04 | 98
2013-07-31 | 2013-08-15 | 2010 | TMA | Major Const | GBR | UNITED KINGDOM | RAF Alconbury | 71550 | Medical/Dental Clinic Replacement - Sidewalk | 2013-04-05 |  | VolterFitzpatrick | 68 | 68 | 2013-07-01 |  | 2013-07-25 |  | 99
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | GA | GEORGIA | Fort Stewart | 70482 | Health Clinic Addition/Alteration | 2010-11-19 | 2011-06-03 | McCarthy Building Companies | 23050 | 26015 | 2011-06-21 | 2013-11-29 | 2013-06-20 | 2013-10-11 | 79
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MA | MASSACHUSETTS | Hanscom AFB | 71634 | Mental Health Clinic Addition | 2011-11-04 | 2011-12-23 | Watermark Environmental, Inc. | 2790 | 2790 | 2012-05-18 | 2013-02-16 | 2013-01-16 | 2013-03-01 | 99
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MD | MARYLAND | Bethesda Naval Hospital | 77116 | NNMC Parking Expansion | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | 14030 | 14284 | 2012-06-18 | 2014-02-01 | 2014-02-01 | 2014-02-01 | 57
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MD | MARYLAND | Bethesda Naval Hospital | 77115 | Transient Wounded Warrior Lodging | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | 48133 | 48487 | 2012-06-18 | 2014-02-01 | 2014-02-01 | 2014-02-01 | 48
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 73360 | Consolidated Logistics Facility | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | 19869 | 19869 | 2011-07-21 | 2014-04-06 | 2014-01-06 | 2014-01-06 | 10
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 62886 | Information Services Facility Expansion | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | 4270 | 4309 | 2012-03-19 | 2014-01-08 | 2013-11-09 | 2013-11-09 | 8
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 67949 | NIBC Security Fencing and Equipment | 2011-08-19 | 2012-02-14 | Rich Moe Enterprises, LLC | 1701 | 1701 | 2012-04-02 | 2013-06-01 | 2013-04-02 | 2013-04-01 | 75
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 67953 | Supplemental Water Storage | 2011-02-18 | 2011-06-30 | FutureNet Group | 3468 | 3674 | 2011-07-20 | 2013-12-02 | 2012-11-11 | 2013-04-01 | 59
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | MD | MARYLAND | Fort Detrick | 67951 | Water Treatment Plant Repair | 2011-08-12 | 2012-12-17 | Grimberg/Amatea GC JV | 14308 | 14308 | 2013-01-14 | 2014-10-06 | 2014-07-08 | 2014-07-08 | 12 | 4400
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | NM | NEW MEXICO | White Sands Missile Range | 70472 | Health and Dental Clinic | 2010-11-02 | 2011-07-22 | Charpie-Korte Dsn-Bld JV S.B. L.L. | 14837 | 15032 | 2011-08-18 | 2013-04-26 | 2013-03-30 | 2013-04-26 | 99
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | WA | WASHINGTON | Fort Lewis | 47344 | Preventive Medicine Facility | 2011-05-03 | 2011-09-13 | Charpie-Korte Group LLC | 7230 | 7676 | 2011-10-14 | 2013-02-28 | 2013-02-28 | 2013-02-28 | 97
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | DEU | GERMANY | Katterbach | 66693 | Health/Dental Clinic Replacement | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | 34294 | 34376 | 2013-10-29 | 2015-10-22 | 2015-08-22 | 2015-08-22 | 1
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | DEU | GERMANY | Vilseck | 66588 | Health Clinic Add/Alt | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | 32103 | 32103 | 2013-03-29 | 2016-10-13 | 2016-04-12 | 2016-04-12 | 0
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | KOR | KOREA | Camp Carroll | 51740 | Health/Dental Clinic Replacement | 2011-05-13 | 2011-08-26 | Ilsung Construction Co., Ltd. | 9821 | 10136 | 2011-08-26 | 2013-10-28 | 2013-05-13 | 2013-10-28 | 99
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | TX | TEXAS | Lackland AFB | 72752 | Ambulatory Care Center Phase 2 | 2011-05-20 | 2011-09-28 | SKANSKA USA Building Inc. | 80558 | 84040 | 2011-12-02 | 2014-07-07 | 2013-10-01 | 2014-03-21 | 71
2013-07-31 | 2013-08-15 | 2011 | TMA | Major Const | GBR | UNITED KINGDOM | RAF Croughton | 72727 | Medical/Dental Clinic Replacement | 2013-02-21 | 2013-09-30 |  |  |  | 2014-03-01 | 2015-12-30 | 2015-10-30 | 2015-08-31 | 0
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | FL | FLORIDA | Eglin AFB | 70597 | Medical Clinic | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | 8897 | 8949 | 2012-10-17 | 2015-01-05 | 2014-10-07 | 2014-10-07 | 25
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | GA | GEORGIA | Ft Stewart | 72292 | Hospital Addition/Alteration Phase 2 | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | 37778 | 38029 | 2012-10-15 | 2017-03-23 | 2016-10-14 | 2016-11-23 | 11
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | IL | ILLINOIS | NAVHOSP Great Lakes | 65030 | Naval Hospital Great Lakes Health Clinic Demolition | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co | 5835 | 6299 | 2012-09-12 | 2014-04-01 | 2013-09-13 | 2014-04-21 | 67
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | KY | KENTUCKY | Ft Campbell | 70438 | Hospital Addition/Alteration | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company (DBA: Mortenson Construction) | 43466 | 44757 | 2012-08-22 | 2015-05-23 | 2015-03-12 | 2015-03-12 | 19
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | MD | MARYLAND | NSA Bethesda (WRNMMC) | 79554 | Child Development Center | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | 14200 | 14200 | 2013-03-01 | 2014-01-08 | 2014-02-22 | 2014-02-22 | 40
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | MD | MARYLAND | Joint Base Andrews | 71408 | Dental Clinic Replacement | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | 18371 | 18688 | 2013-03-01 | 2016-12-06 | 2016-09-29 | 2016-12-07 | 0
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | MS | MISSISSIPPI | NCBC Gulfport | 72754 | Branch Health Clinic | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Constr, Inc | 19096 | 19345 | 2012-09-01 | 2014-08-09 | 2014-08-09 | 2014-09-27 | 27
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | NC | NORTH CAROLINA | Ft Bragg | 70351 | Hospital Alteration | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | 22400 | 22379 | 2012-09-13 | 2014-09-30 | 2014-06-23 | 2014-06-23 | 12
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | NY | NEW YORK | Ft Drum | 70580 | Dental Clinic Addition /Alteration | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | 4370 | 4370 | 2013-01-09 | 2015-04-09 | 2015-01-09 | 2015-01-09 | 7
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | NY | NEW YORK | Ft Drum | 70579 | Medical Clinic (SFCC) | 2012-10-05 | 2013-02-13 | Structural Associates. Inc. | 8934 | 8934 | 2013-03-15 | 2015-05-30 | 2015-03-11 | 2015-03-11 | 3
2013-07-31 | 2013-08-15 | 2012 | TMA | Major Const | TX | TEXAS | JB San Antonio | 51969 | Hospital Nutrition Care Department Add/Alt | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | 28291 | 27689 | 2012-10-02 | 2014-10-27 | 2014-10-30 | 2014-07-04 | 32
2013-07-31 | 2013-08-15 | 2013 | TMA | Major Const | IL | ILLINOIS | Scott AFB, IL | 72718 | Medical Logistics Warehouse Replacement | 2012-10-18 | 2013-06-18 | R&W Builders | 2216 | 2216 | 2013-07-01 | 2014-07-08 | 2014-04-27 | 2014-04-27 | 0
2013-07-31 | 2013-08-15 | 2013 | TMA | Major Const | MO | MISSOURI | Ft. Leonard Wood | 71679 | Dental Clinic | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture | 10687 | 10687 | 2013-08-27 | 2015-06-18 | 2015-02-18 | 2015-02-18 | 0
2013-07-31 | 2013-08-15 | 2013 | TMA | Major Const | KOR | KOREA | Kunsan AB | 72420 | Medical/Dental Clinic Addition | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. | 8544 | 8544 | 2013-06-05 | 2015-05-16 | 2015-02-25 | 2015-02-25 | 0
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | KY | KENTUCKY | Fort Knox | 080656 | HEADQUARTERS BUILDING, WARRIOR IN TRANSITI | 2012-07-19 08:00 | 2012-09-28 | Intersteel, Inc. | 2614.888 | 2614.888 | 2012-10-31 | 2014-03-10 | 2014-01-24 | 2014-01-24 | 7
2013-07-31 | 2013-08-15 | 2009 | Army Reserve | Major Construction | MD | MARYLAND | Curtis Bay, Md | 069422 | Army Reserve Center | 2009-04-30 | 2010-02-11 | James W. Ancel, Inc. | 9850.314 | 13037.3345 | 2010-04-12 | 2013-11-04 | 2011-10-04 | 2013-10-14 | 92
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | FL | FLORIDA | GEORGE P WENTWORTH USARC | 069470 | Army Reserve Center/Land | 2012-01-05 | 2012-08-29 | Leebcor Services, LLC | 6353.27 | 6353.27 | 2012-10-15 | 2014-04-30 | 2014-02-17 | 2014-02-17 | 26
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | James W Reese USARC, PA | 069430 | Army Reserve Center/Land | 2011-07-28 | 2011-09-29 | Lobar Inc. | 18538 | 18607.752 | 2012-01-18 | 2014-10-27 | 2013-11-08 | 2013-11-08 | 20
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | FL | FLORIDA | ELLIOTT BABCOCK MEMORIAL AFRC | 069471 | Army Reserve Center/Land | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | 16207 | 16011.518 | 2012-05-22 | 2014-02-28 | 2013-09-24 | 2013-09-24 | 23
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | CHAPLAIN L J SABALIS MEMORIAL USARC | 069561 | Army Reserve Center | 2010-04-12 08:00 | 2010-06-24 | P&S Construction, Inc. | 9147 | 11280.352 | 2010-08-10 | 2013-11-03 | 2011-12-13 | 2013-10-09 | 88
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | PRI | PUERTO RICO | JUAN PONCE DE LEON ARMORY | 069568 | Army Reserve Center/Land | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | 12506.39 | 12732.3993 | 2011-11-15 | 2014-02-03 | 2013-08-06 | 2013-08-06 | 50
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | UNIONTOWN USARC/AMSA 104 SS 2 (G) | 069652 | Army Reserve Center/Land | 2011-06-23 08:00 | 2011-09-23 | Charpie Korte Enterprise LLC | 11807.704 | 11807.704 | 2012-04-03 | 2013-12-04 | 2014-02-12 | 2013-09-06 | 78
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | HARRISBURG USARC | 070511 | Army Reserve Center | 2010-07-13 08:00 | 2011-03-31 | Eagle ACN Joint Venture | 7740.007 | 10324.5915 | 2011-04-18 | 2014-03-05 | 2012-08-20 | 2013-12-06 | 66
2013-07-31 | 2013-08-15 | 2010 | Army Reserve | Major Construction | TX | TEXAS | Comstock, Us Border Patrol Station | 075110 | Tactical Equipment Maintenance Facility | 2011-10-04 08:00 | 2012-01-26 | Leetex Construction LLC | 9487.777 | 9487.777 | 2012-04-05 | 2014-03-26 | 2013-09-12 | 2013-09-22 | 30
2013-07-31 | 2013-08-15 | 2011 | Active Army | Minor Construction - UMMCA | OH | OHIO | Lima Army Tank Center | 074757 | Fire Alarm System | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | 1763.338 | 1763.338 | 2012-09-05 | 2013-10-24 | 2013-08-01 | 2013-08-01 | 75
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | FL | FLORIDA | Orlando, FL | 069608 | Army Reserve Center/Land | 2011-06-17 | 2011-09-16 | Harkins Development LLC | 7914.55 | 8043.8915 | 2011-11-01 | 2013-09-18 | 2013-03-05 | 2013-12-02 | 97
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | IA | IOWA | Fort Sheridan | 070654 | Army Reserve Center | 2011-11-15 | 2012-03-14 | Greenleaf Construction Co., Inc. | 9055.727 | 9064.361 | 2012-04-09 | 2014-01-08 | 2013-08-12 | 2013-10-01 | 47
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | CA | CALIFORNIA | Fort Hunter Liggett | 072097 | ECS Tactical Equipment Maint Facility | 2010-12-02 08:00 | 2011-06-09 | Kisaq-RQ 8A 2 JV | 20251.66 | 20408.399 | 2011-08-03 | 2013-09-20 | 2013-05-24 | 2013-12-19 | 90
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | CA | CALIFORNIA | Fort Hunter Liggett | 072098 | Tactical Vehicle Wash Rack | 2011-07-29 08:00 | 2011-09-30 | P&S Construction | 8481.2 | 8533.8001 | 2011-10-11 | 2013-08-14 | 2013-02-12 | 2013-11-14 | 99
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | TX | TEXAS | Rio Grand, TX | 069421 | Army Reserve Center/Land | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | 4564 | 4564 | 2012-08-21 | 2015-05-18 | 2014-03-21 | 2014-04-25 | 4
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | NM | NEW MEXICO | Las Cruces, NM | 069582 | Army Reserve Center/Land | 2012-06-13 08:00 | 2012-09-21 | Old Veteran Construction, Inc. | 10535 | 10584.602 | 2012-11-07 | 2014-06-24 | 2014-05-01 | 2014-05-01 | 18
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | NY | NEW YORK | Binghamton, NY (Utica) | 069599 | Army Reserve Center/Land | 2012-07-25 | 2012-09-25 | J. Kokolakis Contracting, Inc. | 12974.5 | 12974.5 | 2012-10-25 | 2014-05-28 | 2014-04-03 | 2014-04-03 | 18
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | VA | VIRGINIA | Roanoke, VA | 070641 | Army Reserve Center/Land | 2011-08-18 | 2011-11-23 | Anthony & Gordon Construction Co, Inc. | 13817 | 13883.305 | 2012-01-12 | 2013-10-16 | 2013-05-06 | 2013-12-29 | 69
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | FL | FLORIDA | Cape Coral, FL / Ft. Meyers | 071303 | Army Reserve Center/Land | 2011-05-03 | 2011-12-13 | FSA + JKC Joint Venture One, LLC | 11088.5 | 11181.377 | 2012-03-06 | 2013-12-10 | 2013-07-23 | 2013-11-06 | 56
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | FL | FLORIDA | Tallahassee, FL | 074220 | Army Reserve Center/Land | 2011-05-19 | 2011-09-23 | Greenleaf Construction Co., Inc. | 8969.571 | 8825.227 | 2011-10-21 | 2013-10-31 | 2013-03-24 | 2014-03-06 | 76
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | TN | TENNESSEE | Millington, TN | 078256 | TEMF/AMSA | 2011-09-14 | 2011-12-23 | Orocon-Carothers JV1 | 9478.98 | 9742.1176 | 2012-02-01 | 2013-08-12 | 2013-06-05 | 2013-08-13 | 95
2013-07-31 | 2013-08-15 | 2011 | Army Reserve | Major Construction | PRI | PUERTO RICO | Fort Buchanan | 077807 | ENGINEERING/HOUSING MAINTENANCE SHOP | 2011-07-14 | 2011-09-28 | Consigli Construction Company, Inc. | 16861.765 | 17061.3659 | 2011-11-08 | 2013-10-01 | 2013-07-30 | 2013-07-30 | 91
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 018646 | Vehicle Maintenance Facility | 2011-12-09 | 2012-05-08 | J & S Construction Company, Inc. | 12240.9707 | 12150.5757 | 2012-05-30 | 2013-10-22 | 2013-08-23 | 2013-08-31 | 91
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 065147 | Physical Fitness Facility | 2011-11-10 | 2012-03-15 | Paladin-Hoar Construction, LLC | 16199.3 | 16412.977 | 2012-03-28 | 2013-11-19 | 2013-07-21 | 2013-09-12 | 89
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 064297 | Vehicle Maintenance Facility | 2011-12-05 08:00 | 2012-05-18 | TJC Engineering, Inc | 23597.2131 | 32607.7451 | 2012-05-31 | 2014-05-31 | 2014-03-12 | 2014-04-08 | 63
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 064297 | Vehicle Maintenance Facility | 2011-12-05 08:00 | 2012-05-01 | J&S Construction Company, Inc. | 8483.139 | 32607.7451 | 2012-05-17 | 2013-10-05 | 2013-09-09 | 2013-09-16 | 92
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 071703 | Scout/Recce Gunnery Range | 2012-02-17 08:00 | 2012-05-10 | The Ross Group Construction Corp | 9236.2 | 9405.997 | 2012-06-04 | 2013-10-19 | 2013-08-20 | 2013-09-16 | 90
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Knox | 065293 | Battalion Complex | 2012-02-10 | 2012-06-29 | B>L> Harbert International, LLC | 40887 | 40918.671 | 2012-07-18 | 2014-07-08 | 2014-03-18 | 2014-04-05 | 62
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 069501 | Unmanned Aerial Vehicle Maintenance Hangar | 2011-12-16 08:00 | 2012-09-27 | Archer Western Federal JV | 40397 | 40699.021 | 2012-11-05 | 2014-11-05 | 2014-09-06 | 2014-10-21 | 26
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 073541 | Barracks | 2011-11-30 08:00 | 2012-05-18 | Sundt Construction, Inc. | 21465.283 | 21475.95 | 2012-06-07 | 2014-01-28 | 2013-11-29 | 2013-12-14 | 65
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 072684 | Barracks Complex | 2011-11-17 | 2012-05-16 | Balfour Beatty Construction, LLC | 50995.657 | 51094.655 | 2012-06-11 | 2014-04-30 | 2014-03-23 | 2014-03-23 | 43
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | NAVAL STATION STATEN ISLAND USARC | 069432 | Army Reserve Center | 2012-12-21 | 2013-03-06 | MACNAK-Korte Design Build LLC | 14338.486 | 14338.486 | 2013-04-15 | 2014-09-27 | 2014-07-29 | 2014-07-29 | 3
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | NAVAL STATION STATEN ISLAND USARC | 069432 | Army Reserve Center | 2012-12-21 | 2012-04-13 | L.S.black Constructors, Inc | 0 | 14338.486 | 2012-06-27 | 2014-02-28 | 2013-12-04 | 2014-02-05 | 19
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | CA | CALIFORNIA | Fort Hunter Liggett | 071702 | Automated Multipurpose Machine Gun (MPMG) | 2012-03-05 08:00 | 2012-05-31 | Cooper Chase Construction | 4838.776 | 4781.5969 | 2012-06-26 | 2013-09-30 | 2013-12-03 | 2013-12-03 | 93
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 067720 | Modified Record Fire Known Distance Range | 2011-12-27 08:00 | 2012-03-27 | Range and Civil Construction , LLC | 5053 | 5131.615 | 2012-04-18 | 2013-09-30 | 2013-08-06 | 2013-08-13 | 97
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | MO | MISSOURI | Weldon Springs, Mo | 067581 | Army Reserve Center | 2012-04-20 08:00 | 2012-07-13 | K&S Associates, Inc. | 16864 | 17122.031 | 2012-08-14 | 2014-04-15 | 2014-01-21 | 2014-03-15 | 40
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | IN | INDIANA | Fort Benjamin Harrison | 067673 | Army Reserve Center | 2012-02-14 | 2012-05-15 | Hunt Construction Group | 44568.206 | 46237.4532 | 2012-05-30 | 2014-07-09 | 2015-01-29 | 2015-04-16 | 40
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | IL | ILLINOIS | Homewood, IL - P2#331461 | 067713 | Army Reserve Center | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | 13454 | 13635.5909 | 2012-10-18 | 2014-10-19 | 2014-07-10 | 2014-07-10 | 18
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 067684 | Container Loading Facility | 2011-11-17 | 2012-03-30 | Carntribe-Clement 3, A Joint Venture, LLC | 5061.521 | 5276.303 | 2012-06-27 | 2013-12-19 | 2013-10-30 | 2013-10-30 | 27
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | NC | NORTH CAROLINA | Greensboro, NC - P2#333014 | 067466 | Army Reserve Center/Land | 2012-05-16 | 2012-09-18 | IKHANA, LL | 16212 | 16212 | 2012-10-10 | 2014-06-19 | 2014-03-19 | 2014-03-19 | 9
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | IL | ILLINOIS | Rockford, IL - P2#333015 | 067664 | Army Reserve Center/Land | 2012-01-18 | 2012-05-02 | Charpie Korte Industries | 10690.067 | 10756.6119 | 2012-06-29 | 2014-01-15 | 2013-12-06 | 2013-12-06 | 45
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | SC | SOUTH CAROLINA | Orangeburg, SC - P2#333016 | 067672 | Army Reserve Center/Land | 2011-11-16 | 2012-03-29 | Group III Mgt. Inc | 10539.52 | 10539.52 | 2012-05-21 | 2014-01-28 | 2013-09-23 | 2013-12-17 | 29
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | MN | MINNESOTA | St. Joseph, MN - P2#333017 | 067674 | Army Reserve Center | 2011-11-30 | 2012-04-13 | L.S.black Constructors, Inc | 10501.332 | 10671.232 | 2012-06-27 | 2014-02-28 | 2013-12-04 | 2014-02-05 | 19
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | Schenectady, NY - P2#333019 | 067691 | Army Reserve Center | 2011-11-16 | 2012-05-03 | SENECA - SCMC, LLC | 18367 | 18367 | 2012-06-01 | 2014-04-25 | 2014-02-21 | 2014-02-21 | 40
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | CO | COLORADO | Fort Collins | 067658 | Army Reserve Center | 2011-11-29 | 2012-04-16 | Greenleaf Construction Co., Inc. | 10608.481 | 10708.063 | 2012-05-11 | 2014-06-30 | 2013-10-18 | 2013-10-18 | 16
2013-07-31 | 2013-08-15 | 2012 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 074310 | NCOA Phase III - Billeting | 2012-06-04 08:00 | 2012-08-14 | Carlson Constructors Corp | 11958.9 | 11958.9 | 2012-09-20 | 2014-04-22 | 2014-02-27 | 2014-02-27 | 36
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 061810 | Battalion Headquarters Complex | 2012-12-06 08:00 | 2013-05-29 | Orocon-Carothers JV1 | 23450.6124 | 23450.6124 | 2013-07-15 | 2015-02-06 | 2014-12-07 | 2014-12-07 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Knox | 005924 | Automated Infantry Squad Battle Course | 2013-01-22 08:00 | 2013-06-17 | Howard W. Pence, Inc. | 3918 | 3918 | TBD | 2014-10-18 | 2014-08-21 | 2014-08-21 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 071712 | Live Fire Exercise Shoothouse | 2012-11-20 08:00 | 2013-06-07 | C3, LLC | 2581.3 | 2581.3 | 2013-06-19 | 2014-07-14 | 2014-05-15 | 2014-05-15 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 076239 | Unmanned Aerial Vehicle Complex | 2012-11-13 08:00 | 2013-05-31 | Archer Western Federal JV | 16983 | 16983 | 2013-06-25 | 2015-06-25 | 2015-04-26 | 2015-04-26 | 3
2013-07-31 | 2013-08-15 | 2013 | Army Reserve | Major Construction | MA | MASSACHUSETTS | Devens Reserve Forces Training Area, Ayer, MA | 067725 | Automatic Record Fire Range | 2013-02-28 | 2013-06-14 | Security Construction Services, Inc. | 4264.1247 | 4264.1247 | 2013-07-31 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 0
2013-07-31 | 2013-08-15 | 2013 | Army Reserve | Major Construction | NJ | NEW JERSEY | Fort Dix | 071720 | Automated Infantry Squad Battle Course | 2012-12-13 | 2013-06-28 | Eastern Construction & Electric, Inc. | 3093.8904 | 3093.8904 | 2013-07-17 | 2014-10-03 | 2014-07-17 | 2014-07-17 | 0
2013-07-31 | 2013-08-15 | 2013 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 067689 | Central Issue Facility | 2013-01-28 | 2013-06-14 | KEPA-TCI JV LLC | 9302.203 | 9302.203 | TBD | 2015-01-05 | 2014-11-16 | 2014-11-16 | 0
2013-07-31 | 2013-08-15 | 2013 | Army Reserve | Major Construction | NV | NEVADA | Las Vegas | 067660 | Army Reserve Center/AMSA | 2012-12-28 | 2013-06-12 | MACNAK Korte Team LLC | 16649.361 | 16649.361 | 2013-07-10 | 2015-08-30 | 2015-05-01 | 2015-05-01 | 0
2013-07-31 | 2013-08-15 | 2013 | Army Reserve | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 067715 | Army Reserve Center | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | 31523 | 31523 | 2013-07-11 | 2015-09-13 | 2015-08-30 | 2015-08-30 | 0
2013-07-31 | 2013-08-15 | 2013 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 072088 | ECS TEMF | 2013-01-24 08:00 | 2013-06-13 | KEPA-TCI JV LLC | 19101.1 | 19101.1 | 2013-07-08 | 2015-08-27 | 2015-06-08 | 2015-06-08 | 1
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction | DEU | GERMANY | Grafenwoehr Germany | 055978 | Brigade Complex-Maintenance/Operations | 2008-02-13 08:00 | 2008-07-23 | Staatliches Hochbauamt Amberg | 16031.1154 | 24637.6044 | 2008-07-28 | 2013-08-30 | 2013-07-15 | 2013-07-15 | 97
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction | EU | EUROPE | Europe Various | 063714 | Base Camp | 2008-06-20 | 2012-07-30 | Planex ltd. | 2190.5335 | 42961.0312 | 2012-09-13 | 2014-11-02 | 2014-09-03 | 2014-09-03 | 18
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction - AFH | DEU | GERMANY | Ansbach, Germany | 066253 | Family Housing Replacement Construction | 2012-10-05 08:00 | 2013-02-14 | Staatliches Hochbauamt Nurnberg II | 0 | 45718.6513 | 2013-03-13 | 2014-04-12 | 2014-03-13 | 2014-03-13 | 97
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | PA | PENNSYLVANIA | Carlisle Barracks | 057142 | Museum Support Facility | 2009-05-08 17:00 | 2012-07-13 | HCR Construction Inc. | 196.9332 | 10724.27 | 2012-08-27 | 2013-07-29 | 2013-05-24 | 2013-10-09 | 92
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | DEU | GERMANY | Vilseck Germany | 069416 | Aircraft/Vehicle Maintenance Complex | 2008-12-05 08:00 | 2011-03-17 | Federal Republic of Germany | 11251.6674 | 8862.4178 | 2011-06-29 | 2013-08-16 | 2013-04-01 | 2013-09-30 | 99
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | NJ | NEW JERSEY | Picatinny Arsenal | 066725 | Ballistic Evaluation Facility Ph 1 | 2012-05-11 08:00 | 2012-09-28 | APS Contracting Inc. | 7201.728 | 7201.728 | 2012-12-04 | 2014-09-02 | 2014-06-04 | 2014-06-04 | 19
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | DEU | GERMANY | Ansbach, Germany | 060238 | Child Development Center | 2011-07-08 | 2011-09-29 | Staatliches Hochbauamt Nurnberg II | 8392.9995 | 6677.5458 | 2011-10-07 | 2013-07-15 | 2013-04-14 | 2013-05-14 | 83
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | DEU | GERMANY | Ansbach, Germany | 062511 | Child Development Center | 2011-07-08 | 2011-09-22 | Staatliches Hochbauamt Nurnberg II | 11350.716 | 9130.4982 | 2011-10-13 | 2013-09-13 | 2013-06-10 | 2013-08-05 | 91
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction - AFH | DEU | GERMANY | Wiesbaden Germany | 062486 | Family Housing Improvements | 2009-02-20 | 2011-12-22 | Noelke GmbH Malerbetrieb | 14394.7135 | 14260.1676 | 2012-01-06 | 2013-10-05 | 2013-07-07 | 2013-09-05 | 63
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | MD | MARYLAND | Fort Detrick | 058625 | Satellite Communications Facility | 2009-10-09 08:00 | 2010-02-05 | Harkins Builders, Inc. | 11717.005 | 19252.4315 | 2010-03-06 | 2015-09-16 | 2012-09-01 | 2015-08-11 | 98
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | VA | VIRGINIA | Fort A P Hill | 067011 | Automated Infantry Platoon Battle Course | 2010-01-27 10:00 | 2011-07-06 | Rand Enterprises, Inc. | 4598.4944 | 5066.3114 | 2011-08-11 | 2013-08-30 | 2012-08-10 | 2013-06-01 | 99
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | DEU | GERMANY | Katterbach Germany | 063394 | Barracks | 2010-03-15 08:00 | 2011-12-13 | Staatliches Hochbauamt Nurnberg II | 16797.4108 | 13163.9821 | 2012-01-09 | 2013-11-06 | 2013-09-06 | 2013-09-06 | 59
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | DEU | GERMANY | Kaiserslautern Germany | 066596 | Barracks | 2011-11-14 | 2012-06-20 | Federal Republic of Germany | 16925.5868 | 13136.7379 | 2012-09-05 | 2014-07-19 | 2014-05-20 | 2014-05-20 | 35
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | DEU | GERMANY | Illesheim Germany | 069616 | Barracks | 2012-03-16 | 2012-07-11 | Staatliches Hochbauamt Nurnberg II | 13907.2139 | 10840.5684 | 2012-08-06 | 2014-04-18 | 2014-01-10 | 2014-02-11 | 17
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | MD | MARYLAND | Aberdeen Proving Ground, Md | 059978 | Analytical Chem Wing-Advanced Chem Lab | 2010-11-22 | 2011-04-27 | JOHN C GRIMBERG CO., INC. | 14904 | 15384.6426 | 2011-06-02 | 2013-08-30 | 2012-12-31 | 2013-08-30 | 94
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | MD | MARYLAND | Fort Detrick | 060027 | Auditorium and Training Center Expansion | 2011-02-23 | 2011-07-08 | Grunley/Goel JV D LLC | 7530 | 7902.125 | 2011-08-18 | 2013-11-15 | 2013-08-17 | 2013-11-12 | 71
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | NJ | NEW JERSEY | Picatinny Arsenal | 066726 | Ballistic Evaluation Facility, Ph 2 | 2012-05-11 08:00 | 2012-09-28 | APS Contracting Inc. | 8757.272 | 8757.272 | 2012-12-04 | 2014-09-02 | 2014-06-04 | 2014-06-04 | 19
2013-07-31 | 2013-08-15 | 2010 | Active Army | Minor Construction - UMMCA | VA | VIRGINIA | Fort Belvoir | 074885 | Fire Station | 2011-08-25 | 2012-07-17 | ARGO SYSTEMS, LLC | 1636.889 | 1636.889 | 2012-08-03 | 2014-03-25 | 2014-01-25 | 2014-01-25 | 15
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NY | NEW YORK | West Point Military Academy | 059044 | Science Facility, Ph 2 | 2011-06-23 08:00 | 2011-09-30 | Walsh Construction Company II L.L.C. | 105270 | 106303.92 | 2011-11-17 | 2016-04-29 | 2015-11-14 | 2015-11-14 | 32
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | VA | VIRGINIA | Fort A P Hill | 065726 | MOUT Collective Training Fac | 2011-11-14 08:00 | 2012-01-03 | Jordan-Versar, LLC | 55547 | 56600.25 | 2012-01-20 | 2013-10-29 | 2013-10-21 | 2013-10-29 | 75
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | VA | VIRGINIA | Fort A P Hill | 065789 | Indoor Firing Range | 2011-11-14 08:00 | 2012-01-03 | Jordan-Versar, LLC | 6520 | 6593.911 | 2012-01-20 | 2013-10-24 | 2013-10-21 | 2013-10-24 | 75
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | MD | MARYLAND | Fort Meade | 065793 | Indoor Firing Range | 2011-06-17 | 2011-09-21 | John C. Grimberg Company, Inc. | 7241 | 8616.8942 | 2011-10-13 | 2013-12-20 | 2013-04-05 | 2013-11-05 | 82
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Wiesbaden Germany | 060555 | Information Processing Center | 2012-10-01 | 2012-05-14 | Hessisches Baumanagement Wiesbaden | 28563.3498 | 20756.8818 | 2012-06-18 | 2014-01-20 | 2013-10-23 | 2013-10-23 | 43
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 062580 | Aircraft Fuel Storage Complex | 2011-08-17 08:00 | 2011-09-29 | Green Jacket- DC Building Systems Joint Venture | 13411.4 | 13660.803 | 2011-10-24 | 2013-09-07 | 2013-04-21 | 2013-09-07 | 85
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Wiesbaden Germany | 068866 | Sensitive Compartmented Information Fac | 2012-05-22 | 2013-01-23 | ECC International LLC | 87011.483 | 69523.811 | 2013-02-22 | 2015-11-30 | 2015-08-17 | 2015-08-17 | 3
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Wiesbaden Germany | 068866 | Sensitive Compartmented Information Fac | 2012-05-22 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | 7198.2416 | 69523.811 | 2013-02-13 | 2014-04-14 | 2014-02-13 | 2014-02-13 | 11
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | VA | VIRGINIA | Fort Belvoir | 061453 | Replace Fire Station | 2012-08-06 | 2013-05-23 | TMG SERVICES, INC. Linda Frazier | 6189 | 6189 | 2013-06-05 | 2015-01-27 | 2014-11-27 | 2014-11-27 | 0
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 057735 | Infantry Squad Battle Course | 2011-12-21 | 2012-04-25 | Dynamic Construction of Northern New York, LLC | 6675 | 6675 | 2012-08-26 | 2014-05-23 | 2014-02-22 | 2014-02-22 | 67
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Katterbach Germany | 059434 | Physical Fitness Center | 2012-06-15 17:00 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II | 14482.3279 | 10553.0803 | 2012-11-30 | 2014-08-31 | 2014-06-08 | 2014-06-08 | 6
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 067532 | Aircraft Maintenance Hangar | 2010-11-23 | 2012-09-27 | Black Horse Group | 2966.8 | 14140.205 | 2012-10-19 | 2014-07-16 | 2014-04-17 | 2014-04-17 | 4
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Grafenwoehr Germany | 067968 | Barracks | 2011-07-17 | 2011-11-23 | Federal Republic of Germany | 16357.4626 | 11947.6319 | 2011-12-12 | 2014-01-29 | 2013-04-09 | 2014-02-28 | 85
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | East Camp Grafenwoehr | 068606 | Barracks | 2012-05-04 08:00 | 2012-10-12 | Bundeskasse Trier | 18121.4668 | 13083.14 | 2012-10-12 | 2014-04-09 | 2014-05-09 | 2014-05-09 | 30
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Vilseck Germany | 069612 | Barracks | 2011-10-21 | 2012-02-15 | Federal Republic of Germany | 18034.1312 | 13122.2554 | 2012-02-29 | 2013-12-15 | 2013-11-08 | 2013-11-08 | 76
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Grafenwoehr Germany | 069613 | Barracks | 2011-10-21 | 2012-02-15 | Federal Republic of Germany | 18352.1994 | 13357.5073 | 2012-02-29 | 2013-12-15 | 2013-11-08 | 2013-11-08 | 74
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | MD | MARYLAND | Fort Meade | 057595 | Wideband SATCOM Operations Center | 2010-11-23 17:00 | 2011-08-08 | Lebolo-Watts Constructors 01 JV LLC | 18392 | 19553.741 | 2011-09-06 | 2013-09-30 | 2013-04-28 | 2013-09-15 | 91
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 067045 | Battalion Complex | 2011-03-04 17:00 | 2011-09-01 | Upstate Construction Services, Inc. | 18658.7 | 41100.449 | 2011-09-26 | 2013-10-31 | 2013-03-19 | 2013-08-02 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 071472 | Brigade Complex Ph 1 | 2011-03-04 17:00 | 2011-08-15 | VETCO Contracting Services, LLC | 18279.51 | 32634.222 | 2011-09-14 | 2013-11-29 | 2013-03-07 | 2013-08-31 | 78
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Katterbach Germany | 066834 | Vehicle Maintenance Shop | 2011-05-26 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | 16289.8057 | 12272.8148 | 2011-12-12 | 2014-01-18 | 2013-12-18 | 2013-12-18 | 90
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | VA | VIRGINIA | Fort Lee | 071114 | Training Aids Center | 2010-09-30 17:00 | 2011-07-14 | TRS Range Services, LLC | 4699.764 | 4769.544 | 2011-09-22 | 2013-10-23 | 2013-01-06 | 2013-07-03 | 98
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NY | NEW YORK | West Point Military Academy | 065166 | Urban Assault Course | 2011-08-09 17:00 | 2012-05-17 | Doyle Contracting Inc | 4465 | 4665.897 | 2012-06-19 | 2014-03-14 | 2013-12-17 | 2013-12-17 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | DEU | GERMANY | Sembach Germany | 066465 | Confinement Facility Sembach | 2012-11-21 | 2013-03-07 | LBB Kaiserslautern | 9437.3488 | 6843.5999 | 2013-04-29 | 2014-08-01 | 2014-06-21 | 2014-06-21 | 11
2013-07-31 | 2013-08-15 | 2011 | Active Army | Minor Construction - UMMCA | NJ | NEW YORK | Picatinny Arsenal | 074943 | Igloo Storage, Installation | 2012-03-13 | 2012-07-18 | Senate Builders & Construction Managers Inc. | 1756.106 | 1786.7037 | 2012-08-10 | 2013-10-31 | 2013-07-07 | 2013-08-26 | 70
2013-07-31 | 2013-08-15 | 2011 | Active Army | Minor Construction - UMMCA | MD | MARYLAND | Fort Meade | 070788 | Mapes Road and Cooper Ave Improvements | 2011-08-22 | 2011-12-16 | Chugach World Services, Inc. | 1612.5431 | 1612.5431 | 2012-01-11 | 2014-02-25 | 2013-12-27 | 2013-12-27 | 14
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | MD | MARYLAND | Fort Meade | 065755 | Brigade Complex | 2012-05-01 08:00 | 2012-10-30 | Skanska USA Building Inc. | 30816.734 | 30897.569 | 2012-12-12 | 2016-04-10 | 2015-12-12 | 2015-12-12 | 2
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 061235 | Chapel | 2012-05-16 | 2012-08-03 | Structural Associates Inc. | 7601.3 | 7601.3 | 2012-09-06 | 2014-06-03 | 2014-03-05 | 2014-03-05 | 32
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | DEU | GERMANY | Landstuhl Germany | 057594 | Satellite Communications Center | 2013-01-22 | 2013-07-30 | LBB Kaiserslautern | 22708.5465 | 17048.8816 | 2013-10-01 | 2015-05-01 | 2016-03-08 | 2016-03-08 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | DEU | GERMANY | East Camp Grafenwoehr | 069614 | Ease Camp Grafenwoehr Barracks | 2012-10-19 | 2013-03-27 | Staatliches Hochbauamt Amberg | 17523.1242 | 13188.3501 | 2013-03-27 | 2015-01-03 | 2014-12-31 | 2014-12-31 | 3
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | DEU | GERMANY | Vilseck Germany | 069615 | Barracks | 2012-06-01 | 2012-09-27 | Bundeskasse Trier | 17668.7874 | 13254.9687 | 2012-10-10 | 2014-09-25 | 2014-08-27 | 2014-08-27 | 25
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 058005 | Ammunition Supply Point | 2011-12-22 | 2012-04-17 | Black Horse Group | 4680.9 | 4668.928 | 2012-05-18 | 2013-11-13 | 2013-08-15 | 2013-08-15 | 61
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | MD | MARYLAND | Fort Meade | 064939 | Applied Instruction Facility | 2012-06-20 | 2012-09-24 | Grimberg/Amatea JV | 30554 | 30572.017 | 2012-11-20 | 2015-01-22 | 2014-11-20 | 2014-11-20 | 17
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | DEU | GERMANY | Grafenwoehr Germany | 065129 | Convoy Live Fire Range | 2012-08-17 08:00 | 2012-10-29 | Bundeskasse Trier | 3406.8394 | 2662.5937 | 2012-10-29 | 2013-10-31 | 2014-05-15 | 2014-05-15 | 89
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | MD | MARYLAND | Aberdeen Proving Ground, Md | 066750 | Auto Technology Evaluation Fac, Ph 3 | 2012-07-12 | 2012-09-28 | Meltech/W.M.Schlosser, LLC B, Joint Venture | 12988 | 13263.481 | 2012-10-17 | 2014-07-31 | 2014-04-15 | 2014-04-25 | 39
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | DEU | GERMANY | Oberdachstatten Germany | 071906 | Automated Record Fire Range | 2012-11-16 | 2013-01-22 | Staatliches Hochbauamt Nurnberg II | 9782.4347 | 7353.9774 | 2013-02-06 | 2014-06-30 | 2014-05-16 | 2014-05-16 | 25
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | VA | VIRGINIA | Joint Base Langley-Eustis | 059005 | Aviation Training Facility | 2012-03-20 08:00 | 2012-05-16 | Oyster Point Construction | 13849 | 14127.217 | 2012-06-14 | 2014-05-14 | 2013-12-06 | 2014-02-13 | 52
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TUR | TURKEY | Turkey Various | 079749 | Forward Operating Site | 2012-06-15 17:00 | 2012-08-30 | EMTA INSAAT A.S | 12129.1464 | 12449.0483 | 2012-09-13 | 2014-03-07 | 2014-02-05 | 2014-02-05 | 6
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Vilseck Germany | 078506 | Family Housing New Construction | 2012-04-10 | 2012-05-04 | LBB Amberg | 11999 | 10748 | 2013-10-30 | 2014-09-13 | 2014-10-12 | 2014-10-12 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Grafenwoehr Germany | 078505 | Family Housing New Construction | 2013-04-19 08:00 | 2012-05-04 | LBB Amberg | 12999 | 11581 | 2013-09-01 | 2014-09-25 | 2014-10-25 | 2014-10-25 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Ansbach, Germany | 079097 | Family Housing Improvements | 2013-02-04 17:00 | 2012-09-13 | Klebl GmbH | 17917.1392 | 13526.5119 | 2012-10-15 | 2018-05-11 | 2018-04-02 | 2018-04-13 | 8
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Ansbach, Germany | 079097 | Family Housing Improvements | 2013-02-04 17:00 | 2013-05-09 | WAYSS & FREYTAG INGENIEURBAU AG | 0 | 13526.5119 | 2013-05-23 | 2014-11-04 | 2014-09-05 | 2014-09-05 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Ansbach, Germany | 078841 | Family Housing Improvements | 2013-02-04 17:00 | 2012-09-13 | Klebl GmbH | 20428.5583 | 16337.7008 | 2012-10-15 | 2018-12-30 | 2018-10-29 | 2018-12-17 | 8
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Ansbach, Germany | 078841 | Family Housing Improvements | 2013-02-04 17:00 | 2013-05-09 | WAYSS & FREYTAG INGENIEURBAU AG | 1168.1153 | 16337.7008 | 2013-05-23 | 2014-11-04 | 2014-09-05 | 2014-09-05 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | NJ | NEW JERSEY | Picatinny Arsenal | 051519 | Ballistic Evaluation Center | 2013-05-16 08:00 | 2012-09-28 | APS Contracting Inc. | 0 | 0 | 2012-12-04 | 2014-09-02 | 2014-06-04 | 2014-06-04 | 19
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 080246 | Aircraft Maintenance Hangar | 2012-12-12 08:00 | 2013-06-17 | VETCO Contracting Services, LLC | 26825.868 | 61164.298 | 2013-06-27 | 2015-09-25 | 2015-06-27 | 2015-06-27 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 080246 | Aircraft Maintenance Hangar | 2012-12-12 08:00 | 2013-06-17 | VETCO | 12760.653 | 61164.298 | 2013-06-27 | 2015-09-15 | 2015-06-17 | 2015-06-17 | 0
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 065133 | Brigade Complex | 2011-05-16 | 2011-07-15 | Better Built Construction Services Inc. | 13542 | 41944.1086 | 2011-08-15 | 2014-02-04 | 2012-10-28 | 2013-12-06 | 91
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 065935 | Brigade Complex, Inc 4 | 2009-04-13 08:00 | 2011-09-22 | Bristol Engineering Services Corporation | 27004 | 29476 | 2012-01-15 | 2014-02-05 | 2013-08-25 | 2014-02-05 | 83
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 071543 | Warrior in Transition Complex | 2013-04-20 | 2013-05-31 | Oke-Thomas & Associates, Inc. | 67.365 | 14702.529 | TBD | 2013-09-25 | 2013-09-25 | 2013-09-25 | 0
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 057194 | Barracks | 2010-12-15 | 2011-12-23 | Hunt Building Company, LTD | 19471.9 | 20053.619 | 2012-01-26 | 2013-09-30 | 2013-06-19 | 2013-09-21 | 88
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 055198 | Barracks Complex | 2011-01-27 08:00 | 2011-09-26 | MEGEN Construction Co., INC. | 11816 | 30844.401 | 2012-02-15 | 2013-10-03 | 2013-07-05 | 2013-09-10 | 96
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 065460 | Automated Qualification/Training Range | 2011-05-10 17:00 | 2011-08-04 | Zieson Construction Company, LLC | 4696.958 | 5315.11 | 2011-09-08 | 2013-08-27 | 2012-11-21 | 2013-08-27 | 97
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 065714 | Battalion Complex, Ph 1 | 2011-04-27 | 2011-05-13 | Alutiiq International Solutions, LLC | 7138.55 | 23008.959 | 2011-06-01 | 2013-09-05 | 2012-08-24 | 2013-07-07 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 064457 | Barracks | 2011-07-11 08:00 | 2011-09-26 | Archer Western Contractors, LTD | 31747 | 62063.8199 | 2011-11-07 | 2013-07-15 | 2013-05-20 | 2013-09-05 | 96
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 064457 | Barracks | 2011-07-11 08:00 | 2011-09-22 | Bristol Engineering Services Corporation | 26919.634 | 62063.8199 | 2012-01-15 | 2014-02-05 | 2013-08-25 | 2013-12-07 | 83
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 013852 | Simulations Center | 2011-07-15 | 2011-09-14 | Native American Services Corp. | 27829.194 | 29147.4287 | 2011-11-04 | 2013-10-25 | 2013-04-27 | 2013-09-25 | 69
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 065171 | Known Distance Range | 2011-05-10 17:00 | 2011-08-04 | Zieson Construction Company, LLC | 4653.926 | 5031.474 | 2011-09-08 | 2013-08-27 | 2012-11-21 | 2013-08-27 | 97
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 072055 | Brigade Headquarters | 2010-10-19 17:00 | 2011-05-18 | McTech Corp | 10563 | 11191.719 | 2011-06-16 | 2013-08-06 | 2012-10-28 | 2014-01-27 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 072838 | Regional Logistic Spt Complex Warehouse | 2011-08-16 | 2011-09-28 | Innovative Technical Solutions, Inc. | 23442.954 | 26037.538 | 2011-10-12 | 2013-09-15 | 2013-04-04 | 2013-12-20 | 82
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 072854 | Regional Logistic Support Complex | 2012-11-09 08:00 | 2013-01-22 | Garco Construction, Inc. | 36247 | 36323.841 | 2013-02-13 | 2014-08-07 | 2014-08-07 | 2014-08-07 | 1
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 075078 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL | 2010-06-16 | 2011-05-19 | ASSET Group Inc. | 5873.409 | 5894.7434 | 2011-07-20 | 2013-08-07 | 2012-10-12 | 2014-01-28 | 94
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 058046 | Operational Readiness Training Cplx, Ph 1 | 2012-06-29 17:00 | 2013-04-01 | TSS-Garco Joint Venture | 16416 | 16416 | 2013-05-21 | 2015-01-11 | 2014-11-12 | 2014-11-12 | 1
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 053637 | Brigade Complex, Ph 2 | 2012-03-30 | 2012-11-09 | MEGEN Construction Co., INC. | 14398 | 48781.219 | 2012-12-18 | 2014-07-17 | 2014-06-11 | 2014-06-11 | 5
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 053637 | Brigade Complex, Ph 2 | 2012-03-30 | 2012-06-07 | Bristol General Contractors, LLC | 19374.564 | 48781.219 | 2012-07-03 | 2013-10-20 | 2013-07-03 | 2013-08-21 | 35
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 053637 | Brigade Complex, Ph 2 | 2012-03-30 | 2012-06-14 | Archer Western Contractors, Ltd | 14691 | 48781.219 | 2012-06-29 | 2013-12-21 | 2013-10-22 | 2013-10-22 | 64
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 061211 | Chapel | 2011-11-22 | 2012-05-31 | TMG Services, Inc. | 7104.944 | 7245.108 | 2012-06-29 | 2013-12-05 | 2013-08-25 | 2013-10-06 | 66
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 064365 | Vehicle Maintenance Facility | 2012-02-03 | 2012-08-23 | KCI Construction Company | 30970 | 42547.909 | 2012-09-18 | 2014-05-11 | 2014-03-12 | 2014-04-09 | 26
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 064365 | Vehicle Maintenance Facility | 2012-02-03 | 2012-11-07 | Greenleaf Construction Co., Inc | 8541.461 | 42547.909 | 2013-07-01 | 2014-10-24 | 2014-08-25 | 2014-08-25 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 064365 | Vehicle Maintenance Facility | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | 2493.149 | 42547.909 | 2013-01-04 | 2014-03-12 | 2014-01-04 | 2014-02-03 | 50
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 060344 | Air Support Operations Facilities | 2012-01-06 | 2012-03-09 | Performance Systems, Inc. | 7511.891 | 7660.049 | 2012-04-17 | 2013-09-29 | 2013-07-31 | 2013-11-07 | 43
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 064014 | Battalion Complex | 2013-07-29 | 2012-06-28 | M.A. Mortenson Company | 19332 | 43253.23 | 2012-07-25 | 2014-01-16 | 2013-11-17 | 2013-11-17 | 82
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 064014 | Battalion Complex | 2013-07-29 | 2013-01-03 | TSS-Garco Joint Venture | 8912 | 43253.23 | 2013-02-12 | 2014-10-05 | 2014-08-06 | 2014-08-06 | 5
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 064014 | Battalion Complex | 2013-07-29 | 2012-09-21 | 3D Contracting Inc. | 14649 | 43253.23 | 2012-11-30 | 2014-07-26 | 2014-05-24 | 2014-05-27 | 20
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 066206 | Infrastructure, Ph 1 | 2013-06-06 | 2013-01-25 | CeSight Joint Venture | 13775.4 | 32418.968 | 2013-03-01 | 2014-10-22 | 2014-08-23 | 2014-08-23 | 8
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 066206 | Infrastructure, Ph 1 | 2013-06-06 | 2012-08-29 | Alutiiq Diversified Services, LLC | 10665 | 32418.968 | 2012-09-17 | 2014-05-10 | 2014-03-11 | 2014-03-11 | 46
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 066206 | Infrastructure, Ph 1 | 2013-06-06 | 2012-09-28 | Vet Industrial, Inc. | 4980.322 | 32418.968 | 2012-11-05 | 2014-02-09 | 2013-10-31 | 2013-12-11 | 65
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 002728 | Physical Fitness Facility | 2011-12-09 17:00 | 2012-03-16 | Better Built Construction Services Inc. | 11660 | 11706.996 | 2012-03-29 | 2013-11-19 | 2013-09-20 | 2013-09-20 | 34
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 076767 | Aviation Unit Complex, Ph 1A | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | 24162 | 24356.151 | 2012-07-09 | 2014-03-01 | 2013-12-31 | 2014-02-18 | 41
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 076768 | Aviation Complex, Ph 1B | 2012-08-20 08:00 | 2012-09-28 | CJW Construction, Inc. | 12950.4 | 12955.609 | 2012-11-29 | 2014-07-22 | 2014-05-23 | 2014-05-23 | 23
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 065602 | Brigade Headquarters | 2012-02-07 08:00 | 2012-03-30 | Komada, LLC | 9947 | 11168.908 | 2012-04-18 | 2013-11-06 | 2013-07-12 | 2013-10-07 | 74
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 065602 | Brigade Headquarters | 2012-02-07 08:00 | 2013-05-02 | M.A. Mortenson Company | 610.065 | 11168.908 | 2013-05-31 | 2015-03-14 | 2015-01-13 | 2015-01-13 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077265 | Barracks | 2012-06-01 | 2013-05-02 | M.A. Mortenson Company | 37228.729 | 37262.2122 | 2013-05-31 | 2015-03-14 | 2015-01-13 | 2015-01-13 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077264 | Barracks | 2012-06-01 | 2013-05-02 | M.A. Mortenson Company | 53766.583 | 53816.8078 | 2013-05-31 | 2015-03-14 | 2015-01-13 | 2015-01-13 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077306 | Aircraft Maintenance Hangar | 2012-01-17 08:00 | 2012-08-09 | Hensel Phelps Construction Company | 44801 | 51689.344 | 2012-08-23 | 2014-05-06 | 2014-02-14 | 2014-03-07 | 19
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077306 | Aircraft Maintenance Hangar | 2012-01-17 08:00 | 2013-05-02 | M.A. Mortenson Company | 2669.032 | 51689.344 | 2013-05-31 | 2015-03-14 | 2015-01-13 | 2015-01-13 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077302 | Control Tower | 2012-02-22 17:00 | 2012-08-02 | Hensel Phelps Construction Co. | 10891 | 11830.8061 | 2012-08-27 | 2014-03-30 | 2014-01-05 | 2014-01-29 | 44
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077302 | Control Tower | 2012-02-22 17:00 | 2013-05-02 | M.A. Mortenson Company | 601.591 | 11830.8061 | 2013-05-31 | 2015-03-14 | 2015-01-13 | 2015-01-13 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077319 | Aircraft Loading Area | 2012-04-06 17:00 | 2012-09-19 | Komada, LLC | 6524.909 | 32724.003 | 2012-10-10 | 2013-11-19 | 2013-10-10 | 2013-10-10 | 44
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077319 | Aircraft Loading Area | 2012-04-06 17:00 | 2012-08-10 | Loyd Contracting Co., Inc. | 18222 | 32724.003 | 2012-09-07 | 2014-02-02 | 2013-09-07 | 2013-12-04 | 50
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077319 | Aircraft Loading Area | 2012-04-06 17:00 | 2012-08-09 | Hartland/Mass JV, LLC | 3212.3 | 32724.003 | 2012-09-06 | 2013-11-24 | 2013-09-06 | 2013-09-25 | 33
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077319 | Aircraft Loading Area | 2012-04-06 17:00 | 2012-08-13 | Komada, LLC | 3832.74 | 32724.003 | 2012-09-05 | 2014-01-01 | 2013-09-05 | 2013-11-02 | 75
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 064456 | Battalion Complex | 2013-02-20 | 2013-06-18 | MEGEN Construction Co., INC. | 14849 | 24281.86 | 2013-07-11 | 2015-03-03 | 2015-01-02 | 2015-01-02 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 064456 | Battalion Complex | 2013-02-20 | 2013-05-17 | Tunista Construction, LLC | 9432.86 | 24281.86 | 2013-06-26 | 2015-02-16 | 2014-12-18 | 2014-12-18 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 054489 | Trainee Barracks Complex 3, Ph 2 | 2013-04-11 | 2013-05-31 | Donald Maggi, Inc. | 11711 | 11711 | 2013-06-25 | 2014-12-17 | 2014-12-17 | 2014-12-17 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 065679 | Vehicle Maintenance Shop | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | 18726.852 | 18726.852 | 2013-06-27 | 2015-07-07 | 2015-04-08 | 2015-04-08 | 1
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 066099 | Battalion Complex Facilities | 2012-12-19 | 2013-06-03 | MW Builders of Texas, Inc. | 13687 | 13687 | 2013-07-01 | 2015-04-22 | 2014-12-23 | 2014-12-23 | 1
2013-07-31 | 2013-08-15 | 2013 | Active Army | Minor Construction - UMMCA | MO | MISSOURI | Fort Leonard Wood | 081377 | LIMITED USE INSTRUCTIONAL BUILDING | 2013-02-08 | 2013-05-03 | Zieson Construction Company, LLC | 1675.747 | 1675.747 | 2013-06-19 | 2014-03-16 | 2014-03-16 | 2014-03-16 | 0
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction | KOR | KOREA | Humphreys, Korea | 058784 | Barracks Complex | 2012-02-02 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | 5457.7516 | 6426100.1046 | 2012-09-17 | 2014-10-06 | 2014-03-16 | 2014-08-17 | 8
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction | KOR | KOREA | Humphreys, Korea | 058784 | Barracks Complex | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | 32468.604 | 6426100.1046 | 2012-09-17 | 2014-11-06 | 2014-09-07 | 2014-09-07 | 16
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068786 | Brigade Complex | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 26656 | 26777.518 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-03-14 | 68
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068821 | Battalion Complex | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 31084 | 31695.576 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-03-14 | 68
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068822 | Battalion Complex | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 9840 | 9961.518 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-03-14 | 68
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069308 | Infrastructure Expansion | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 60385 | 61360.844 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-03-14 | 68
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | KOR | KOREA | Humphreys, Korea | 060783 | Fire Stations | 2009-11-20 | 2012-07-26 | Il Kwang Engr. & Cons. Co., Ltd. | 7385.2095 | 14356904.687 | 2012-07-26 | 2013-11-30 | 2013-04-22 | 2013-09-19 | 77
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069521 | Warrior in Transition (WT) Barracks | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 32745.37 | 33082.823 | 2011-07-27 | 2014-07-10 | 2013-10-12 | 2013-10-24 | 32
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 071553 | Warrior in Transition Complex | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 26339.63 | 26367.073 | 2011-07-27 | 2014-07-10 | 2013-10-12 | 2013-10-24 | 32
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 052267 | Barracks | 2010-11-30 | 2011-06-30 | Absher Construction Company | 35275.888 | 64360.119 | 2011-08-29 | 2013-11-28 | 2013-08-29 | 2013-10-10 | 88
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 052267 | Barracks | 2010-11-30 | 2011-09-01 | SUMO-NAN LLC | 28024.553 | 64360.119 | 2011-10-28 | 2013-11-18 | 2013-10-17 | 2013-10-17 | 75
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 052269 | Barracks | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | 41466.255 | 41542.942 | 2011-10-17 | 2014-09-04 | 2013-10-14 | 2014-07-16 | 26
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AK | ALASKA | Fort Richardson | 057369 | Simulations Center | 2010-10-04 17:00 | 2011-05-11 | UNIT COMPANY | 20025.555 | 22057.576 | 2011-05-18 | 2013-08-20 | 2013-05-17 | 2013-08-20 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HI | HAWAII | Fort Shafter | 056024 | Flood Mitigation | 2012-06-29 | 2012-09-25 | Nan, Inc | 21105.273 | 21185.273 | 2012-10-17 | 2015-02-05 | 2014-10-14 | 2014-10-14 | 13
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HI | HAWAII | Tripler Army Medical Center | 067258 | Barracks | 2010-12-20 17:00 | 2011-05-25 | SUMO-NAN LLC | 15996.619 | 16553.712 | 2011-06-15 | 2014-03-28 | 2013-09-12 | 2013-12-12 | 57
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AK | ALASKA | Fort Wainwright | 067112 | Aviation Task Force Complex, Ph 2A (Hngar) | 2010-07-19 17:00 | 2011-05-10 | Watterson Construction Company | 67814 | 67899.304 | 2011-05-17 | 2013-08-14 | 2013-08-14 | 2013-08-14 | 97
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AK | ALASKA | Fort Richardson | 055695 | Brigade Complex, Ph 1 | 2011-03-01 17:00 | 2011-05-11 | Korte-Purcell JV | 23898.777 | 48011.1975 | 2011-05-25 | 2013-09-20 | 2013-03-24 | 2013-09-20 | 97
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HI | HAWAII | Fort Shafter | 065650 | Command and Control Facility, Ph 1 | 2011-11-04 | 2012-02-28 | Niking Corporation | 46780 | 48136.544 | 2012-04-03 | 2015-01-31 | 2014-04-23 | 2014-10-22 | 28
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 064760 | Training Aids Center | 2012-06-29 | 2012-09-19 | SRB International LLC | 13310.008 | 13310.008 | 2012-10-31 | 2014-10-21 | 2014-08-17 | 2014-08-17 | 1
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | KOR | KOREA | Camp Walker Korea | 061551 | Electrical Sys Upgrade & Natural Gas Sys | 2010-11-04 08:00 | 2011-05-13 | Lim kwang Engr. & Const. Co., Ltd. | 15608.2713 | 20550026.308 | 2011-05-13 | 2013-10-10 | 2013-02-01 | 2013-09-10 | 98
2013-07-31 | 2013-08-15 | 2011 | Active Army | Minor Construction - UMMCA | HI | HAWAII | Schofield Barracks | 065454 | Police/MP Station | 2011-08-26 | 2011-11-10 | Polu Kai Services, LLC | 1404.5127 | 1600.2683 | 2012-01-04 | 2013-10-15 | 2013-01-03 | 2013-10-15 | 75
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | AK | ALASKA | Fort Richardson | 061515 | Physical Fitness Facility | 2011-10-19 17:00 | 2012-11-07 | Bristol General Contractors, LLC | 21813.389 | 23027.771 | 2013-03-16 | 2015-03-05 | 2014-12-06 | 2015-02-04 | 3
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | HI | HAWAII | Fort Shafter | 064967 | Child Development Center | 2011-10-06 | 2012-02-27 | 57 Builders, Ltd. | 9573.118 | 9862.415 | 2012-03-23 | 2014-08-11 | 2013-12-13 | 2014-06-12 | 14
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069489 | Combat Aviation Brigade Complex, Ph 1 | 2012-01-24 | 2012-06-29 | David Boland, Inc. | 54772 | 54915.588 | 2012-07-30 | 2015-09-30 | 2015-05-27 | 2015-05-27 | 20
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | AK | ALASKA | Fort Wainwright | 067113 | Aviation Complex, Ph 3A | 2011-07-15 17:00 | 2012-06-07 | Watterson Construction Company | 70591 | 71276.881 | 2012-06-14 | 2014-10-15 | 2014-08-03 | 2014-10-05 | 22
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 059581 | Centralized Wash Facility | 2011-10-13 08:00 | 2012-01-27 | Watts Constructors, LLC | 28300 | 28218.23 | 2012-02-08 | 2014-02-11 | 2013-12-14 | 2013-12-14 | 54
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | AK | ALASKA | Joint Base Elmendorf-Richardson | 072270 | Brigade Complex, Ph 2 | 2011-12-22 08:00 | 2012-05-03 | KICC - Alcan General JV | 23170.1 | 54081.702 | 2012-05-16 | 2014-05-08 | 2013-12-27 | 2014-01-30 | 75
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | AK | ALASKA | Joint Base Elmendorf-Richardson | 072270 | Brigade Complex, Ph 2 | 2011-12-22 08:00 | 2012-02-02 | UNIT COMPANY | 24839.9 | 54081.702 | 2012-02-10 | 2014-04-10 | 2014-02-09 | 2014-02-09 | 76
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Henry/George, Korea | 076235 | Barracks Complex | 2012-02-02 | 2012-04-06 | Fine Construction Co., Ltd. | 28609.5284 | 31669512.34 | 2012-04-06 | 2014-09-13 | 2014-06-22 | 2014-08-14 | 16
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Henry/George, Korea | 076235 | Barracks Complex | 2012-02-02 | 2012-02-09 | Hanmi C&E Co., LTD. | 72.2037 | 31669512.34 | 2012-02-09 | 2014-08-02 | 2014-07-02 | 2014-07-02 | 27
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Carroll, Korea | 072650 | Barracks | 2011-11-10 | 2012-02-24 | Samsung C&T Corporation | 27592.9923 | 30526721.496 | 2012-02-24 | 2016-01-05 | 2015-12-05 | 2015-10-07 | 19
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Carroll, Korea | 072650 | Barracks | 2011-11-10 | 2012-02-27 | Hanmi C&E Co., LTD. | 63.7852 | 30526721.496 | 2012-02-27 | 2015-11-30 | 2015-10-31 | 2015-10-31 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Minor Construction - UMMCA | MHL | MARSHALL ISLANDS | Kwajalein Atoll | 080026 | Secondary Waste Water Treatment | 2012-09-06 | 2012-09-28 | San Juan Construction, Inc. | 1399.217 | 1561.366 | 2012-10-25 | 2014-03-31 | 2014-01-29 | 2014-05-02 | 1
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | KOR | KOREA | Humphreys, Korea | 076196 | Battalion Headquarters Complex | 2013-02-01 | 2013-05-14 | Hyosung Corporation | 25852.7608 | 28313000 | 2013-05-14 | 2015-06-09 | 2015-06-09 | 2015-06-09 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | AK | ALASKA | Fort Wainwright | 061681 | Modified Record Fire Range | 2012-11-30 08:00 | 2013-05-14 | Arctic-American JV | 5094.09 | 5095.09 | 2013-05-24 | 2014-09-01 | 2014-08-01 | 2014-08-01 | 1
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | AK | ALASKA | Joint Base Elmendorf-Richardson | 061731 | Modified Record Fire Range | 2012-11-30 17:00 | 2013-05-16 | G2 Construction, Inc | 4807.087 | 4807.087 | 2013-05-22 | 2014-06-28 | 2014-06-28 | 2014-06-28 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 076586 | Barracks | 2013-02-06 | 2013-07-11 | Nan, Inc. | 30717.476 | 30717.476 | 2013-07-23 | 2015-12-10 | 2015-08-18 | 2015-08-18 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 076587 | Barracks | 2013-02-06 | 2013-07-11 | Nan, Inc. | 37410.03 | 37410.03 | 2013-07-23 | 2015-12-10 | 2015-08-18 | 2015-08-18 | 0
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 068818 | Ammunition Supply Point/Veh Main Fac | 2008-05-22 | 2012-05-10 | Barnhill Contracting Company | 551.67 | 84920.8716 | 2012-06-08 | 2013-08-28 | 2013-02-03 | 2013-02-03 | 90
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 069742 | Training Area Infrastructure-Northern Area | 2009-11-23 | 2012-12-03 | Komada, LLC | 3199.854 | 17126.623 | 2012-12-19 | 2014-01-18 | 2013-12-19 | 2013-12-19 | 82
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction - OCO | MS | MISSISSIPPI | Mississippi Army Ammo Plant | 075436 | Major Caliber Loading Plant | 2010-06-30 08:00 | 2010-07-01 | Speegle Construction, Inc. | 9182 | 41019.7671 | 2010-11-29 | 2013-09-23 | 2011-11-29 | 2013-09-23 | 85
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction - OCO | MS | MISSISSIPPI | Mississippi Army Ammo Plant | 075436 | Major Caliber Loading Plant | 2010-06-30 08:00 | 2010-11-30 | Sauer, Incorporated | 27349.7 | 41019.7671 | 2011-01-12 | 2013-10-31 | 2012-07-05 | 2013-11-01 | 95
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 065557 | Training Area Tank Trails | 2010-05-28 08:00 | 2012-12-03 | Komada, LLC | 0 | 9448.3986 | 2012-12-19 | 2014-01-18 | 2013-12-19 | 2013-12-19 | 82
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 068759 | Automated Multipurpose Machine Gun | 2010-11-29 08:00 | 2011-06-30 | Trend Construction, Inc. | 5975.7354 | 6070.185 | 2011-08-31 | 2013-08-21 | 2013-02-21 | 2013-02-21 | 96
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 069150 | Training Battalion Complex | 2009-11-24 | 2012-08-23 | Brasfield & Gorrie LLC | 21400 | 35350.5276 | 2012-09-20 | 2014-10-26 | 2014-08-21 | 2014-08-21 | 24
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 069417 | Training Battalion Complex | 2009-11-03 | 2010-06-24 | Balfour Beatty Construction, LLC | 43613.85 | 49980.0567 | 2010-07-27 | 2014-05-31 | 2013-06-03 | 2014-01-17 | 86
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brigade Complex | 2011-05-24 | 2011-09-19 | Polote Corp. | 10869 | 38871.6159 | 2012-03-15 | 2013-10-08 | 2013-05-09 | 2013-08-09 | 70
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brigade Complex | 2011-05-24 | 2011-09-16 | Atlantic Marine Construction Company, Inc | 1209.6245 | 38871.6159 | 2011-11-29 | 2014-07-31 | 2012-11-28 | 2014-05-02 | 44
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brigade Complex | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | 15752.3734 | 38871.6159 | 2011-11-21 | 2014-05-05 | 2014-01-29 | 2014-03-06 | 87
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brigade Complex | 2011-05-24 | 2011-12-09 | H-S Joint Venture, LLC | 10469.241 | 38871.6159 | 2012-01-05 | 2013-09-28 | 2013-06-28 | 2013-07-14 | 79
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brigade Complex | 2011-05-24 | 2013-04-15 | Barnhill Contracting Company | 68.429 | 38871.6159 | 2013-04-29 | 2014-02-23 | 2013-11-25 | 2013-11-25 | 60
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 057317 | Battalion Complex | 2011-05-24 | 2011-09-19 | Polote Corp. | 3908 | 18093.2062 | 2012-03-15 | 2013-10-08 | 2013-05-09 | 2013-08-09 | 70
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 057317 | Battalion Complex | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | 13850.4196 | 18093.2062 | 2011-11-21 | 2014-05-05 | 2014-01-29 | 2014-03-06 | 87
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 065204 | Company Operations Facilities | 2011-03-07 | 2011-08-08 | Tyler Construction Group, Inc. | 8526 | 9878.5589 | 2011-09-08 | 2013-09-19 | 2013-03-01 | 2014-02-26 | 93
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 065204 | Company Operations Facilities | 2011-03-07 | 2011-09-15 | Atlantic Marine Construction Company, Inc | 1352.2359 | 9878.5589 | 2011-11-29 | 2014-01-27 | 2013-01-22 | 2013-12-28 | 52
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 072188 | Automated Multipurpose Machine Gun Range | 2010-12-03 | 2011-05-12 | Trend Construction, Inc. | 6457.6011 | 8492.2391 | 2011-05-25 | 2013-08-16 | 2012-05-24 | 2013-04-06 | 93
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 072456 | Training Battalion Complex, Ph 2 | 2011-07-20 08:00 | 2011-09-29 | IAP-Leopardo Construction, Inc. | 22100.1 | 22100.1 | 2011-10-13 | 2014-04-10 | 2013-04-05 | 2013-12-11 | 72
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 072457 | Training Battalion Complex, Ph 2 | 2011-07-20 08:00 | 2011-09-29 | IAP-Leopardo Construction, Inc. | 22157.9 | 22157.9 | 2011-10-13 | 2014-03-22 | 2013-04-05 | 2013-12-11 | 68
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 044968 | Command and Control Facility | 2011-01-12 | 2011-06-13 | Sauer Inc. | 33708 | 35742.3897 | 2011-07-11 | 2013-12-19 | 2013-06-10 | 2013-09-20 | 95
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 053794 | Trainee Barracks Complex, Ph 1 | 2011-07-15 08:00 | 2011-08-30 | W. G. YATES & SONS CONSTRUCTION COMPANY | 20249.7 | 36066.3933 | 2012-01-04 | 2013-11-25 | 2013-06-27 | 2013-11-20 | 89
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 053794 | Trainee Barracks Complex, Ph 1 | 2011-07-15 08:00 | 2012-04-16 | H-S JOINT VENTURE, LLC | 10186.85 | 36066.3933 | 2012-07-13 | 2013-12-31 | 2013-07-08 | 2013-07-15 | 55
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 053794 | Trainee Barracks Complex, Ph 1 | 2011-07-15 08:00 | 2012-07-03 | LIFECYCLE CONSTRUCTION SERVICES, LLC | 2731.143 | 36066.3933 | 2012-08-09 | 2013-10-10 | 2013-08-04 | 2013-08-16 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 064340 | Brigade Complex | 2011-08-03 08:00 | 2011-09-23 | GSC Construction, Inc. | 4282.55 | 23774.4564 | 2011-11-17 | 2013-09-10 | 2013-02-09 | 2015-01-26 | 96
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 064340 | Brigade Complex | 2011-08-03 08:00 | 2011-09-29 | The Polote Corporation | 19315.777 | 23774.4564 | 2011-12-05 | 2013-11-30 | 2013-05-28 | 2013-09-12 | 71
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 064342 | Brigade Complex | 2011-04-06 | 2011-06-02 | Walbridge Aldinger Company | 15158.7 | 30254.761 | 2011-06-16 | 2013-08-24 | 2012-10-27 | 2013-12-16 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 064342 | Brigade Complex | 2011-04-06 | 2011-08-29 | Better Built Construction Services, Inc. | 13311 | 30254.761 | 2011-09-28 | 2013-09-21 | 2013-03-21 | 2013-10-17 | 87
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 071583 | Battalion Complex | 2011-04-28 | 2011-06-23 | Q.B.S.Incorporated | 12552.888 | 17272.085 | 2011-09-28 | 2013-10-03 | 2013-05-20 | 2013-07-05 | 94
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 072324 | Trainee Barracks Ph 2 | 2010-10-26 08:00 | 2011-09-29 | Anthony and Gordon Construction Company, Inc | 7936 | 16751.5628 | 2011-11-07 | 2013-08-20 | 2013-04-30 | 2015-02-20 | 89
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | FL | FLORIDA | Homestead Air Force Base | 061533 | Command and Control Facility | 2011-05-10 | 2011-07-29 | Carothers Construction, Inc. | 39233.28 | 41203.505 | 2011-09-20 | 2015-01-04 | 2014-10-06 | 2014-10-06 | 66
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | HND | HONDURAS | Honduras Various | 061383 | Barracks | 2011-05-18 17:00 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | 15146.5804 | 15283.8037 | 2012-01-10 | 2014-04-09 | 2014-01-09 | 2014-06-07 | 50
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 073299 | Trainee Barracks | 2011-01-14 08:00 | 2011-07-29 | CLARK CONSTRUCTION GROUP LLC | 16984 | 17425.984 | 2011-12-06 | 2013-07-20 | 2013-04-21 | 2013-09-20 | 98
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 039614 | Simulations Center | 2011-07-26 08:00 | 2011-09-12 | IAP-Leopardo Construction, Inc. | 17954.066 | 18069.098 | 2011-10-12 | 2013-08-16 | 2013-04-04 | 2013-10-25 | 99
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 073930 | Student Barracks | 2011-03-07 | 2011-08-08 | Tyler Construction Group, Inc. | 12754 | 12760.349 | 2011-09-08 | 2013-11-30 | 2013-03-01 | 2014-01-21 | 93
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AL | ALABAMA | Fort Rucker | 060463 | Aviation Component Maintenance Shop | 2010-12-14 17:00 | 2011-05-18 | Carothers Construction, Inc | 19712.66 | 20380.052 | 2011-09-20 | 2013-08-15 | 2013-09-09 | 2013-09-25 | 98
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 071119 | Training Aids Center | 2011-06-03 17:00 | 2011-08-03 | PENTACON, LLC | 14999.9 | 15830.902 | 2011-09-08 | 2014-09-28 | 2013-03-01 | 2014-09-09 | 15
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 069745 | Trainee Barracks Complex, Ph 3 | 2011-12-16 | 2012-05-08 | Compton Construction Company, Inc. | 7898 | 18917.608 | 2012-05-18 | 2014-01-08 | 2013-11-09 | 2013-11-09 | 80
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 069745 | Trainee Barracks Complex, Ph 3 | 2011-12-16 | 2013-02-21 | SOCO Contracting Company, INC. | 11019.608 | 18917.608 | 2013-05-30 | 2014-10-22 | 2014-08-23 | 2014-08-23 | 0
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 062955 | Trainee Barracks Complex, Ph 2 | 2012-02-16 | 2012-03-28 | CLARK CONSTRUCTION GROUP LLC | 44267 | 44934.024 | 2012-07-23 | 2014-06-14 | 2014-01-14 | 2014-05-23 | 42
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 062953 | Rail Loading Facility | 2012-06-04 | 2012-08-14 | R. C. Construction Co., Inc. | 7409 | 7409.18 | 2012-09-05 | 2014-05-11 | 2014-02-27 | 2014-02-27 | 61
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 067022 | Modified Record Fire Range | 2011-09-23 08:00 | 2012-06-29 | TREND CONSTRUCTION INC | 4375.259 | 4510.036 | 2012-09-06 | 2014-03-14 | 2013-12-30 | 2014-04-15 | 20
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | GA | GEORGIA | Fort Gordon, GA | 071705 | Hand Grenade Familiarization Range | 2011-12-16 | 2012-03-30 | Atkinson Incorporated | 1450 | 1490.6288 | 2012-04-19 | 2013-10-18 | 2013-04-19 | 2013-08-14 | 99
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 043335 | NCO Academy | 2012-05-08 | 2012-07-30 | Caddell Construction CO., INC | 34647 | 34750.1045 | 2012-10-03 | 2014-10-16 | 2014-07-15 | 2014-07-15 | 55
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | AL | ALABAMA | Fort Rucker | 065429 | Combat Readiness Center | 2011-10-28 08:00 | 2012-01-25 | Bates Engineers/Contractors, Inc. | 8698 | 9178.886 | 2012-03-21 | 2014-04-10 | 2014-01-10 | 2014-02-03 | 81
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 070751 | Brigade Complex Facilities | 2012-04-19 | 2012-01-26 | Balfour Beatty Construction, LLC | 10447 | 22496.89 | 2012-02-29 | 2013-11-22 | 2014-02-18 | 2014-02-18 | 91
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 070751 | Brigade Complex Facilities | 2012-04-19 | 2012-06-29 | Brantley Construction Services, LLC | 11681.588 | 22496.89 | 2012-07-31 | 2014-08-22 | 2014-07-21 | 2014-07-23 | 38
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 076958 | Battle Command Training Center | 2011-12-06 | 2012-02-01 | SFL+A Architects, PA | 17927.666 | 17891.0576 | 2012-03-01 | 2013-12-21 | 2013-08-23 | 2013-08-23 | 63
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 062728 | Dog Kennel | 2012-06-04 08:00 | 2012-09-27 | SEPI Engineering & Construction, Inc. | 2881.959 | 2881.959 | 2012-10-23 | 2014-01-05 | 2013-10-23 | 2013-10-23 | 14
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 057794 | Digital Multipurpose Training Range | 2012-12-26 | 2013-05-10 | Caddell Construction CO., INC | 19523 | 19523 | TBD | 2015-03-30 | 2015-03-30 | 2015-03-30 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 077416 | Ground Source Heat Transfer System | 2013-04-04 08:00 | 2013-05-29 | R. C. Construction Co., Inc. | 8295 | 8295 | 2013-07-12 | 2015-03-04 | 2015-01-03 | 2015-01-03 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 067019 | Automated Combat Pistol Qual Crse | 2012-11-16 08:00 | 2013-05-10 | Komada, LLC | 2515 | 2515 | 2013-06-06 | 2014-09-24 | 2014-07-01 | 2014-07-01 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Gordon, GA | 061498 | Modified Record Fire Range | 2012-11-19 | 2013-05-10 | BRISTOL ENVIRONMENTAL REMEDIATION SERVIC | 3163.794 | 3163.794 | 2013-07-03 | 2014-12-30 | 2014-07-19 | 2014-07-19 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Gordon, GA | 067017 | Multipurpose Machine Gun Range | 2012-11-19 08:00 | 2013-05-16 | BRISTOL ENVIRONMENTAL REMEDIATION SERVIC | 6483.273 | 6483.273 | 2013-07-11 | 2014-11-21 | 2014-08-05 | 2014-08-05 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 080087 | Storage Building, General Purpose | 2012-07-16 08:00 | 2013-03-22 | Tyler Construction Group, Inc. | 9037.592 | 9037.592 | 2013-04-18 | 2014-11-09 | 2014-08-11 | 2014-08-11 | 2
2013-07-31 | 2013-08-15 | 2013 | Active Army | Minor Construction - UMMCA | GA | GEORGIA | Fort Benning | 081043 | CANTONMENT AREA TANK TRAILS | 2013-04-15 08:00 | 2013-06-14 | R. C. Construction Co., Inc. | 1607 | 1607 | 2013-07-17 | 2014-09-15 | 2014-07-17 | 2014-07-17 | 1
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | AZ | ARIZONA | Fort Huachuca | 062363 | UAV ER/MPEr/Mp | 2010-04-16 17:00 | 2013-05-22 | Marsh Development, Inc. | 78.987 | 9149.036 | 2013-06-11 | 2013-08-30 | 2013-08-10 | 2013-08-10 | 96
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | CA | CALIFORNIA | Presidio Of Monterey | 060285 | General Instruction Building | 2010-10-07 17:00 | 2011-05-18 | RQ Construction, Inc. | 29886 | 32274.658 | 2011-06-07 | 2014-04-11 | 2013-05-24 | 2013-11-18 | 79
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | CA | CALIFORNIA | Camp Roberts | 063015 | Satellite Communications Facility | 2011-01-07 17:00 | 2011-08-30 | Watts/Webcor A JV | 34801.408 | 35283.472 | 2011-09-21 | 2015-05-15 | 2013-06-12 | 2013-10-22 | 4
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | UT | UTAH | Dugway Proving Ground | 055823 | Life Sciences Test Facility Addition | 2012-04-12 17:00 | 2012-07-26 | Big-D Construction | 22608.566 | 22824.707 | 2012-08-29 | 2015-06-23 | 2015-02-15 | 2015-02-23 | 9
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CA | CALIFORNIA | Presidio Of Monterey | 056425 | General Instruction Building | 2012-08-20 17:00 | 2012-09-29 | Souza Construction, Inc. | 2996 | 3017.438 | 2012-11-06 | 2014-03-12 | 2013-11-06 | 2013-11-06 | 9
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CA | CALIFORNIA | Fort Irwin | 071707 | Infantry Squad Battle Course | 2011-11-01 08:00 | 2012-03-15 | SHANKS ELECTRIC CORPORATION | 3387.6 | 3565.597 | 2012-04-16 | 2013-12-24 | 2013-04-11 | 2013-12-23 | 96
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | CA | CALIFORNIA | Fort Irwin | 062657 | Water Treatment Plant | 2012-05-21 17:00 | 2012-09-12 | CDM CONSTRUCTORS INC. | 100112.66 | 100039.229 | 2012-10-19 | 2016-03-28 | 2015-10-19 | 2015-10-19 | 8
2013-07-31 | 2013-08-15 | 2012 | Active Army | Minor Construction - UMMCA | AZ | ARIZONA | Fort Huachuca | 079959 | ANTENNA | 2012-04-23 17:00 | 2012-09-10 | KAYA Associates | 1670.866 | 1674.467 | 2012-10-17 | 2014-02-05 | 2013-07-14 | 2013-12-07 | 86
2013-07-31 | 2013-08-15 | 2013 | Active Army | Minor Construction - UMMCA | AZ | ARIZONA | Yuma Proving Ground | 062788 | Ammunition Demolition Facility | 2013-03-18 17:00 | 2013-07-03 | Sybrant Construction, LLC | 3587.91 | 3587.91 | 2013-08-19 | 2014-04-16 | 2014-02-15 | 2014-02-15 | 0
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 054785 | Child Development Center | 2010-12-13 | 2011-08-05 | ASSET Group, Inc. | 7835.188 | 7946.4612 | 2011-09-23 | 2014-04-30 | 2013-01-25 | 2014-06-29 | 39
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 069199 | Unit Operations Facilities | 2013-04-03 08:00 | 2011-07-06 | Q.B.S., Inc. | 7076 | 27916.3678 | 2011-08-24 | 2013-10-30 | 2013-04-05 | 2013-08-22 | 84
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | TX | TEXAS | Joint Base San Antonio | 047338 | AIT Barracks | 2009-05-22 08:00 | 2012-03-30 | Hensel Phelps Construction Company | 1655 | 42598.77 | 2012-04-25 | 2014-03-14 | 2014-01-15 | 2014-01-25 | 83
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 060130 | Barracks | 2011-01-28 | 2011-08-10 | Sundt Construction Inc | 24390.053 | 24403.952 | 2011-09-21 | 2013-10-14 | 2013-03-14 | 2013-08-23 | 95
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 065299 | General Purpose Storage Building | 2010-10-26 17:00 | 2011-09-15 | GSC Construction, Inc. | 11951.46 | 12033.798 | 2011-11-17 | 2013-08-26 | 2013-04-19 | 2013-10-14 | 80
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071465 | Company Operations Facilities | 2011-03-21 | 2011-09-29 | MW Builders | 3048.91 | 3453.4583 | 2012-06-19 | 2014-03-11 | 2013-11-11 | 2013-11-11 | 48
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071462 | Battalion Complex | 2011-08-02 08:00 | 2011-09-30 | JAMA Constructors | 6572.777 | 26909.3161 | 2012-07-30 | 2014-08-30 | 2014-01-21 | 2014-04-21 | 36
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071462 | Battalion Complex | 2011-08-02 08:00 | 2011-09-29 | MW Builders | 8779.712 | 26909.3161 | 2012-06-19 | 2014-03-11 | 2013-11-11 | 2013-11-11 | 48
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071639 | Brigade Complex | 2012-12-19 17:00 | 2011-09-29 | MW Builders | 11652.378 | 18574.0239 | 2012-06-19 | 2014-03-11 | 2013-11-11 | 2013-11-11 | 48
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | TX | TEXAS | Joint Base San Antonio | 067194 | Simulations Center | 2010-11-18 08:00 | 2012-03-13 | Blackhawk Ventrues, LLC | 14554.1 | 14837.012 | 2012-04-10 | 2013-12-30 | 2013-08-09 | 2013-11-30 | 68
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 072845 | Unmanned Aerial System (UAS) Hangar | 2010-12-23 17:00 | 2011-07-21 | Satterfield & Pontikes Construction Inc. | 37388.894 | 39847.4 | 2011-12-13 | 2014-04-11 | 2013-11-12 | 2014-02-15 | 73
2013-07-31 | 2013-08-15 | 2011 | Active Army | Minor Construction - UMMCA | NM | NEW MEXICO | White Sands Missile Range | 073641 | PHYSICS LAB | 2011-08-18 | 2012-01-20 | Denco | 1443.431 | 1521.257 | 2012-02-16 | 2013-07-01 | 2013-01-31 | 2013-05-01 | 97
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 061846 | Rail Deployment Facility | 2012-01-27 | 2012-04-25 | Terra Construction | 3497.82 | 3641.8557 | 2012-05-29 | 2013-08-12 | 2013-04-29 | 2013-08-12 | 74
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 062622 | Military Working Dog Facility | 2012-03-01 08:00 | 2012-06-30 | Jamco Ventures, LLC | 2437 | 2445.1074 | 2012-08-14 | 2014-01-08 | 2013-08-09 | 2013-09-16 | 24
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 064415 | Brigade Complex | 2012-02-21 | 2012-03-23 | Blackhawk Ventures, LLC | 10283 | 22196.3556 | 2012-05-15 | 2014-03-06 | 2013-11-06 | 2013-11-29 | 46
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 064415 | Brigade Complex | 2012-02-21 | 2012-08-17 | The Ross Group Construction Corporation | 11856.9 | 22196.3556 | 2012-10-09 | 2014-05-30 | 2014-04-02 | 2014-04-24 | 22
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 001235 | Physical Fitness Facility | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | 23138.91 | 23121.051 | 2012-07-12 | 2014-08-13 | 2014-04-10 | 2014-04-28 | 10
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 020697 | Chapel | 2012-01-27 | 2012-08-30 | Greenleaf Construction Co.,Inc | 12999.823 | 13015.239 | 2012-09-20 | 2014-05-28 | 2014-01-28 | 2014-01-28 | 21
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 058537 | Reception Station, Ph 1 | 2011-11-21 | 2012-05-23 | Zachry Federal Construction Corporation | 32234.496 | 32224.904 | 2012-06-15 | 2014-06-26 | 2014-03-26 | 2014-03-26 | 24
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | McAlester Army Ammo Plant | 058207 | Railroad Tracks | 2011-11-29 | 2012-03-26 | McAlester Contract | 6323.7745 | 6323.7745 | 2012-05-09 | 2014-01-04 | 2013-10-06 | 2013-10-06 | 55
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071682 | Vehicle Maintenance Facility | 2011-12-19 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | 3844.2 | 13514.8105 | 2012-08-24 | 2014-04-16 | 2014-02-15 | 2014-02-15 | 17
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071682 | Vehicle Maintenance Facility | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | 9669.4345 | 13514.8105 | 2012-06-22 | 2014-02-02 | 2013-12-14 | 2013-12-28 | 40
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Joint Base San Antonio | 005034 | Vehicle Maintenance Facility | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | 8603 | 8603 | 2013-01-24 | 2014-12-15 | 2014-07-18 | 2014-07-18 | 13
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 064753 | Vehicle Maintenance Facility | 2012-01-09 | 2012-06-29 | Harper Construction Company, Inc. | 37867.635 | 43962.357 | 2012-07-19 | 2014-07-03 | 2014-04-11 | 2014-04-11 | 40
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 064753 | Vehicle Maintenance Facility | 2012-01-09 | 2012-07-13 | GSC Construction, Inc. | 6094.722 | 43962.357 | 2012-09-26 | 2014-05-06 | 2014-02-03 | 2014-02-03 | 7
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 067033 | Multipurpose Machine Gun Range | 2012-03-13 | 2012-08-03 | Jamco Ventures, LLC. | 8493 | 8500.0767 | 2012-10-25 | 2014-02-24 | 2013-10-25 | 2013-11-13 | 38
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 068993 | Electronics Maintenance Facility | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | 9573 | 14690.965 | 2012-08-08 | 2014-02-14 | 2013-12-16 | 2013-12-16 | 30
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 068993 | Electronics Maintenance Facility | 2011-12-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | 5117.965 | 14690.965 | 2012-08-20 | 2014-07-31 | 2013-09-13 | 2013-09-13 | 72
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 069286 | Infrastructure | 2011-09-16 08:00 | 2012-07-26 | Venegas Engineering & Management Construction Company | 9008.411 | 8705.699 | 2012-08-20 | 2014-07-31 | 2013-09-13 | 2013-09-13 | 72
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 070514 | Vehicle Maintenance Facility | 2011-12-15 17:00 | 2012-03-30 | J&M Contractors | 3921.5 | 14246.804 | 2012-05-31 | 2013-12-06 | 2013-10-08 | 2013-10-08 | 68
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 070514 | Vehicle Maintenance Facility | 2011-12-15 17:00 | 2012-03-30 | Urban Associates, Inc. | 9815.87 | 14246.804 | 2012-05-30 | 2013-11-13 | 2013-09-13 | 2013-10-20 | 66
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Red River Army Depot | 066691 | Maneuver Systems Sustainment Ctr, Ph 3 | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | 40532.114 | 40779.149 | 2012-04-24 | 2014-08-28 | 2014-04-24 | 2014-06-26 | 16
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 064815 | Battle Command Training Center | 2011-12-22 | 2012-04-10 | Harper Construction Company, Inc. | 20720.265 | 20727.506 | 2012-07-09 | 2014-06-10 | 2014-03-19 | 2014-03-19 | 69
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 074845 | Water Well, Potable | 2012-01-04 | 2012-08-01 | Bailey CKY JV | 2248.08 | 2251.435 | 2012-08-28 | 2013-09-30 | 2013-05-25 | 2013-07-02 | 99
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 065374 | Operational Readiness Training Complex | 2012-07-19 08:00 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | 38503 | 45438.734 | 2012-09-05 | 2014-11-10 | 2014-07-28 | 2014-07-28 | 19
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 065374 | Operational Readiness Training Complex | 2012-07-19 08:00 | 2013-01-07 | Turner Strategic Technologies, LLC | 8195.202 | 45438.734 | 2013-03-08 | 2015-05-15 | 2014-11-28 | 2014-11-28 | 9
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 077187 | Vehicle Maintenance Facility | 2011-12-19 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | 3749.6 | 16592.2348 | 2012-08-24 | 2014-04-16 | 2014-02-15 | 2014-02-15 | 17
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 077187 | Vehicle Maintenance Facility | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | 7472.9455 | 16592.2348 | 2012-06-22 | 2014-02-02 | 2013-12-14 | 2013-12-28 | 40
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 077187 | Vehicle Maintenance Facility | 2011-12-19 | 2012-03-28 | RMA Land Construction, Inc. | 5378.708 | 16592.2348 | 2012-06-26 | 2013-12-18 | 2013-06-21 | 2013-11-18 | 33
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 074690 | THAAD Instruction Facility | 2012-01-09 | 2012-03-29 | Roy Anderson Corp. | 25942 | 25942 | 2012-07-26 | 2014-07-25 | 2014-04-16 | 2014-05-05 | 35
2013-07-31 | 2013-08-15 | 2012 | Active Army | Minor Construction - UMMCA | OK | OKLAHOMA | Fort Sill | 080407 | SIMULATOR BUILDING (NON-MOTION-BASED) | 2011-12-16 08:00 | 2012-06-22 | Comanche Nation Construction, LLC | 1700.971 | 1753.259 | 2012-06-22 | 2014-01-06 | 2013-09-15 | 2013-10-15 | 85
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 066911 | Multipurpose Machine Gun Range | 2012-12-21 17:00 | 2013-05-13 | Blackhawk Ventures, LLC | 6397 | 6397 | 2013-06-10 | 2014-08-13 | 2014-07-05 | 2014-07-05 | 2
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 067020 | Modified Record Fire Range | 2012-11-30 17:00 | 2013-05-31 | Better Built Conststruction Services, Inc | 4094.684 | 4094.684 | 2013-07-16 | 2014-09-16 | 2014-08-19 | 2014-08-19 | 0
2013-07-31 | 2013-08-15 | 2013 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 067037 | Modified Record Fire Range | 2012-12-06 | 2013-06-13 | Diversified Construction of Oklahoma, Inc. | 4160.3398 | 4160.3398 | 2013-07-23 | 2014-08-05 | 2014-06-06 | 2014-06-06 | 0
2013-07-31 | 2013-08-15 | 2008 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 064131 | New Roads | 2009-07-20 17:00 | 2009-09-23 | Global Operation & Trust Construction Ltd JV | 17780.3681 | 17426.0578 | 2009-10-27 | 2013-07-31 | 2012-01-17 | 2013-10-31 | 82
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 070037 | SOF HQ Complex | 2009-05-22 | 2010-02-12 | EMTA Insaat VE Ticaret A.S. | 11619.3495 | 17993.9026 | 2010-03-22 | 2013-09-30 | 2011-08-19 | 2013-09-23 | 87
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 072125 | SOF Alpha Ramp Facilities | 2012-04-04 | 2010-01-30 | ALMCO Limited | 9047.5 | 11522.8028 | 2010-03-17 | 2011-11-30 | 2011-06-10 | 2013-11-11 | 93
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 072125 | SOF Alpha Ramp Facilities | 2012-04-04 | 2012-08-23 | Prime Projects Int'l (Const) Limited | 7995.5256 | 11522.8028 | 2012-09-26 | 2013-11-11 | 2013-08-13 | 2013-08-13 | 78
2013-07-31 | 2013-08-15 | 2009 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 072605 | Troop Housing, Ph 3 | 2010-07-25 | 2010-09-06 | EMTA Insaat VE Ticaret A.S. | 10990.1872 | 11387.8558 | 2010-10-09 | 2014-01-14 | 2013-02-25 | 2013-12-09 | 88
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 071488 | Coalition Operation Center | 2011-10-11 08:00 | 2011-12-14 | Ch2m Hill-Yuksel Joint Venture | 39961.861 | 41400.9337 | 2012-03-16 | 2013-12-01 | 2013-07-09 | 2013-10-09 | 63
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 072126 | Command and Control Facility | 2010-06-16 08:00 | 2010-09-24 | Metag Insaat Ticaret A.S. | 16908.8471 | 25717.6166 | 2010-10-24 | 2013-10-17 | 2012-01-17 | 2013-11-16 | 95
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 069398 | Fuel System Ph 6 | 2009-12-18 08:00 | 2010-03-31 | EMTA Insaat VE Ticaret A.S. | 5001.829 | 5349.4628 | 2010-04-20 | 2013-08-15 | 2011-10-12 | 2013-06-01 | 97
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 071489 | Barracks | 2010-05-03 08:00 | 2010-09-25 | Zafer Construction Company | 11196.317 | 13654.6239 | 2010-10-25 | 2013-08-31 | 2012-05-17 | 2013-07-31 | 99
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 073124 | Drainage System, Ph 2 | 2011-06-01 | 2011-08-17 | Yuksel Insaat A.S. | 13900 | 16223.2602 | 2011-09-08 | 2014-01-09 | 2013-04-10 | 2013-11-10 | 88
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 072477 | USFOR-A Headquarters & Housing | 2011-03-28 | 2011-08-05 | Contrack International Inc. | 47160.85 | 47339.4736 | 2011-09-09 | 2014-01-27 | 2013-12-07 | 2014-01-27 | 21
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 074292 | Warehouse | 2010-06-29 08:00 | 2013-05-05 | Arkel International, LLC | 844.5623 | 14592.2813 | 2013-05-26 | 2013-11-13 | 2013-08-24 | 2013-09-14 | 0
2013-07-31 | 2013-08-15 | 2010 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 074195 | Water Distribution System | 2011-07-29 | 2012-01-26 | Technologists, Inc. | 17565.6438 | 16620.5978 | 2012-03-28 | 2013-12-01 | 2012-12-23 | 2013-11-01 | 24
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 068083 | Consolidated Community Support Area | 2011-02-15 08:00 | 2011-05-23 | Zafer Construction Company | 12944.211 | 15398.1341 | 2011-06-21 | 2013-12-31 | 2012-11-22 | 2013-10-09 | 70
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 071602 | Barracks | 2011-11-14 | 2012-02-07 | Bryan 77 Construction JV | 16732.683 | 17283.809 | 2012-03-06 | 2014-03-15 | 2013-11-26 | 2014-01-25 | 57
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 071604 | Eastside Utilities Infrastructure | 2012-05-30 | 2012-09-04 | ANHAM-ICSS Joint Venture | 26826.989 | 26826.989 | 2012-10-18 | 2014-08-04 | 2014-06-05 | 2014-06-05 | 7
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 071605 | Eastside Electrical Distribution | 2011-07-15 | 2012-07-26 | Fluor Intercontinental, Inc. | 10944.278 | 10970.778 | 2012-07-26 | 2013-10-30 | 2013-08-12 | 2013-08-31 | 73
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 072606 | Troop Housing, Ph 4 | 2010-12-07 17:00 | 2011-06-01 | Yuksel Insaat A.S. | 14226.7 | 14902.7385 | 2011-06-22 | 2013-06-03 | 2012-10-29 | 2013-07-24 | 65
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 074090 | Troop Housing, Ph 5 | 2011-01-07 | 2011-07-05 | Yuksel Insaat A.S. | 18499.9 | 19150.3584 | 2011-08-15 | 2013-12-01 | 2012-11-12 | 2013-07-11 | 97
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 074155 | Troop Housing, Ph 6 | 2010-12-22 | 2011-07-08 | Yuksel Insaat A.S. | 18499.9 | 19232.7109 | 2011-08-07 | 2013-09-02 | 2012-11-04 | 2013-07-04 | 98
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 074104 | Command & Control Facility | 2010-11-17 | 2012-01-11 | YUKSEL INSAAT A.S. | 7090.5 | 7239.8577 | 2012-04-05 | 2014-01-15 | 2013-07-09 | 2013-11-15 | 78
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 074925 | Dining Facility | 2011-07-05 08:00 | 2012-02-16 | Zafer Construction Company | 5217.732 | 5879.002 | 2012-04-18 | 2013-10-01 | 2013-05-03 | 2013-08-24 | 77
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 075202 | Command & Control Facility | 2012-03-16 | 2012-06-11 | Road & Roof Construction Company | 5027.586 | 4975.424 | 2012-07-16 | 2013-11-25 | 2013-07-26 | 2013-07-26 | 39
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan | 071606 | Entry Control Point | 2011-06-10 17:00 | 2011-11-09 | 77 Construction Contracting & Trading Company | 6490.6192 | 6920.3025 | 2012-02-06 | 2013-10-01 | 2013-02-05 | 2013-07-16 | 88
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 077119 | Roads and Utilities, Ph 1 | 2011-07-29 17:00 | 2012-01-26 | Technologists, Inc. | 14706 | 13761 | 2012-03-28 | 2013-12-01 | 2012-12-23 | 2012-12-23 | 24
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 077054 | Replace Temporary Guard Towers | 2011-01-08 | 2011-09-21 | Metag Insaat Ticaret A.S. | 5999 | 6981.5003 | 2011-11-15 | 2013-11-01 | 2013-01-18 | 2013-10-28 | 44
2013-07-31 | 2013-08-15 | 2011 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 077066 | MP HQ | 2011-01-08 | 2011-09-21 | Metag Insaat Ticaret A.S. | 3352 | 3849 | 2011-11-15 | 2013-11-01 | 2013-01-18 | 2013-10-28 | 44
2013-07-31 | 2013-08-15 | 2011 | Active Army | Minor Construction - UMMCA | AFG | AFGHANISTAN | Afghanistan Various | 079762 | PRIMARY WASTE WATER TREATMENT | 2011-05-04 | 2011-08-05 | Contrack International Inc. | 1387 | 1386.997 | 2011-09-09 | 2014-01-27 | 2013-12-07 | 2014-01-27 | 21
2013-07-31 | 2013-08-15 | 2011 | Active Army | Minor Construction - UMMCA | AFG | AFGHANISTAN | Afghanistan Various | 079770 | WATER WELL, POTABLE | 2011-05-13 08:00 | 2011-08-05 | Contrack International Inc. | 1331 | 1330.83 | 2011-09-09 | 2014-01-27 | 2013-12-07 | 2014-01-27 | 21
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan | 074084 | Barracks, Ph 5 | 2011-12-05 08:00 | 2012-04-12 | Bryan 77 Construction JV | 19331.277 | 20217.723 | 2012-06-08 | 2014-12-31 | 2014-04-19 | 2014-09-17 | 21
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 074067 | Drainage System, Ph 3 | 2012-04-27 | 2012-08-15 | ANHAM-ICSS Joint Venture | 19902.989 | 19902.989 | 2012-10-09 | 2014-07-31 | 2014-06-01 | 2014-06-01 | 25
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan | 071570 | Westside Electrical Distribution | 2012-07-03 | 2012-08-23 | Inglett & Stubbs, International LTD | 8117.7809 | 8117.7809 | 2012-08-23 | 2013-09-29 | 2013-07-29 | 2013-07-29 | 90
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan | 071568 | Eastside Electrical Distribution, Ph 2 | 2012-06-14 | 2012-08-03 | Fluor Intercontinental, Inc. | 6506.937 | 6506.937 | 2012-08-07 | 2013-08-02 | 2013-06-03 | 2013-08-09 | 90
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan | 071569 | Westside Utilities Infrastructure | 2012-08-24 | 2012-11-15 | Contrack International Inc. | 11924.059 | 11924.059 | 2012-12-12 | 2014-05-06 | 2014-03-07 | 2014-03-07 | 14
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction | WW | WORLD WIDE | Various Worldwide Locations | 079652 | Radar Security and Support Facilities | 2012-05-25 08:00 | 2012-08-20 | State Corps | 3800 | 3800 | 2012-09-27 | 2013-09-22 | 2013-07-24 | 2013-07-24 | 53
2013-07-31 | 2013-08-15 | 2012 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan | 080001 | Waste Management Complex (60 Tons) | 2012-05-25 08:00 | 2012-08-21 | Bryan 77 Construction JV | 24435.92 | 24708.77 | 2012-11-14 | 2014-01-13 | 2013-11-14 | 2014-01-08 | 18

## Planning and Design
Data As Of Date | Submission Date | Fiscal Year | Component | Type of funds | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Funds Diverted ($000) (if applicable) | Notes/remarks
2013-07-31 | 2013-07-31 | 2008 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 3400 | 3348 |  | RCI-Residential Communities Initiative
2013-07-31 | 2013-07-31 | 2008 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 08/09/ 10/11/12 MILCON projects | 1891 | 1891
2013-07-31 | 2013-07-31 | 2009 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 1830 | 1830
2013-07-31 | 2013-07-31 | 2009 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 5000 | 5000
2013-07-31 | 2013-07-31 | 2009 | DoDEA | P&D-FAD from OSD May 2010 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 7000 | 7000
2013-07-31 | 2013-07-31 | 2010 | DoDEA | P&D-FAD from OSD Jan 2010 | Design efforts for FY 10/11/ 12/13 MILCON projects | 8830 | 8698 |  | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2011 | DoDEA | P&D-FAD from OSD 24 Feb 2011 | Design efforts for FY 11/12/ 13 MILCON projects | 7840 | 7840
2013-07-31 | 2013-07-31 | 2011 | DoDEA | P&D-FAD from ODS 2 June 2011 | Design efforts for FY 11/12/13 MILCON projects | 70841 | 70395 |  | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2012 | DoDEA | P&D-FAD from OSD 6 Jan 2012 | Design efforts for FY 12/13 MILCON projects | 64551 | 64540 |  | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2013 | DoDEA | P&D-FAD from OSD 6 Jun 2013 | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 18339 |  | Reflects Sequestration Reduction
2013-07-31 | 2013-08-02 | 2009 | NSA | General P&D | Power & Cooling Infrastructure | 4000 | 4000 |  | P & D for High Voltage Power Upgrade
2013-07-31 | 2013-08-02 | 2010 | NSA | General P&D | Power & Cooling Infrastructure | 240 | 240 |  | Additional Funding, assume from MHS Backup Power Generation Facility Reprogramming
2013-07-31 | 2013-08-02 | 2010 | NSA | General P&D | Generators 10 & 11 | 200 | 200
2013-07-31 | 2013-08-02 | 2011 | NSA | General P&D | A&E Design for Colorado Powerhouse | 3000 | 3000
2013-07-31 | 2013-08-02 | 2012 | NSA | General P&D | East Campus Building 1 | 12000 | 12000
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Planning and Design (P&D) | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 60944 | 60941 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Planning and Design (P&D) | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 47210 | 46144 |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Planning and Design (P&D) | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25611 | 25556 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Planning and Design (P&D) | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191 | 8024 |  | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Planning and Design (P&D) | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25749 | 371 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-05 | 2007 | MDA | General P&D | Design MDA 609 - Aegis-BMD Facility Expansion, Dahlgren, VA. | 770 | 770 |  | Completed RFP for design-build (D-B) project.
2013-07-31 | 2013-08-05 | 2009 | MDA | General P&D | Design MDA FY10-FY13 MILCON Projects | 14889 | 14752 |  | Supports design of the Aegis Ashore Test Complex, East Coast Comm site, Aegis Ashore Romania site, UEWR Modifications at Clear AFS, AK and completes RFP for D-B Von Braun Complex, Phase IV.
2013-07-31 | 2013-08-05 | 2010 | MDA | General P&D | Design MDA FY12-13 MILCON Projects | 7700 | 7672 |  | Supports design of the Aegis Ashore Romania site, East Coast Comm site, UEWR Modifications at Clear AFS, AK, and EUCOM Radar site. Includes $5,700,000 reprogrammed from MILCON.
2013-07-31 | 2013-08-05 | 2012 | MDA | General P&D | Design MDA FY13-14 MILCON Projects | 8368 | 8368 |  | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2013-07-31 | 2013-08-05 | 2013 | MDA | General P&D | Design MDA FY13-14 MILCON Projects | 4548 | 2880 |  | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2013-07-31 | 2013-08-06 | 2006 | Air Force | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; GWOT Supplemental | 65284 | 56808
2013-07-31 | 2013-08-06 | 2006 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27783 | 27251
2013-07-31 | 2013-08-06 | 2006 | Air Force Reserve | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5290 | 5289
2013-07-31 | 2013-08-06 | 2006 | Air National Guard | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006 | 28047
2013-07-31 | 2013-08-06 | 2007 | Air Force | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements ; GWOT Supplemental | 76246 | 72310
2013-07-31 | 2013-08-06 | 2007 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12983
2013-07-31 | 2013-08-06 | 2007 | Air Force Reserve | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109 | 5087
2013-07-31 | 2013-08-06 | 2007 | Air National Guard | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050 | 19044
2013-07-31 | 2013-08-06 | 2008 | Air Force | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; GWOT Supplemental | 51202 | 46881
2013-07-31 | 2013-08-06 | 2008 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12162
2013-07-31 | 2013-08-06 | 2008 | Air Force Reserve | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300 | 5256
2013-07-31 | 2013-08-06 | 2008 | Air National Guard | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721 | 10619
2013-07-31 | 2013-08-06 | 2009 | Air Force | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105506 | 93896
2013-07-31 | 2013-08-06 | 2009 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7708 | 7633
2013-07-31 | 2013-08-06 | 2009 | Air Force Reserve | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165 | 5779
2013-07-31 | 2013-08-06 | 2009 | Air National Guard | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056 | 18613
2013-07-31 | 2013-08-06 | 2010 | Air Force | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 112785 | 91953
2013-07-31 | 2013-08-06 | 2010 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4314 | 1413
2013-07-31 | 2013-08-06 | 2010 | Air Force Reserve | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 3869 | 2318
2013-07-31 | 2013-08-06 | 2010 | Air National Guard | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 20021 | 19140
2013-07-31 | 2013-08-06 | 2011 | Air Force | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 68825 | 46496
2013-07-31 | 2013-08-06 | 2011 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4216 | 3425
2013-07-31 | 2013-08-06 | 2011 | Air Force Reserve | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1650 | 1369
2013-07-31 | 2013-08-06 | 2011 | Air National Guard | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9196 | 8368
2013-07-31 | 2013-08-06 | 2012 | Air Force | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 81913 | 28201
2013-07-31 | 2013-08-06 | 2012 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4208 | 3426
2013-07-31 | 2013-08-06 | 2012 | Air Force Reserve | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200 | 713
2013-07-31 | 2013-08-06 | 2012 | Air National Guard | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225 | 7782
2013-07-31 | 2013-08-06 | 2013 | Air Force | General P&D | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 18610 | 0
2013-07-31 | 2013-08-06 | 2013 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY14 MILCON; design of FY13 non-PB projects if any; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3952 | 0
2013-07-31 | 2013-08-06 | 2013 | Air Force Reserve | General P&D | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 2875 | 0
2013-07-31 | 2013-08-06 | 2013 | Air National Guard | General P&D | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 3995 | 0
2013-07-31 | 2013-07-31 | 2008 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 3400 | 3348 | RCI-Residential Communities Initiative
2013-07-31 | 2013-07-31 | 2008 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 08/09/ 10/11/12 MILCON projects | 1891 | 1891
2013-07-31 | 2013-07-31 | 2009 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 1830 | 1830
2013-07-31 | 2013-07-31 | 2009 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 5000 | 5000
2013-07-31 | 2013-07-31 | 2009 | DoDEA | P&D-FAD from OSD May 2010 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 7000 | 7000
2013-07-31 | 2013-07-31 | 2010 | DoDEA | P&D-FAD from OSD Jan 2010 | Design efforts for FY 10/11/ 12/13 MILCON projects | 8830 | 8698 | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2011 | DoDEA | P&D-FAD from OSD 24 Feb 2011 | Design efforts for FY 11/12/ 13 MILCON projects | 7840 | 7840
2013-07-31 | 2013-07-31 | 2011 | DoDEA | P&D-FAD from ODS 2 June 2011 | Design efforts for FY 11/12/13 MILCON projects | 70841 | 70395 | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2012 | DoDEA | P&D-FAD from OSD 6 Jan 2012 | Design efforts for FY 12/13 MILCON projects | 64551 | 64540 | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2013 | DoDEA | P&D-FAD from OSD 6 Jun 2013 | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 18339 | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2009 | DLA | General P&D | Design efforts for FY 10/11/12 MILCON projects | 4338 | 4338
2013-07-31 | 2013-07-31 | 2010 | DLA | General P&D | Design efforts for FY 11/12/13 MILCON projects | 12548 | 12548 | OSD provided additional P&D 15 Jun 11
2013-07-31 | 2013-07-31 | 2011 | DLA | General P&D | Design efforts for FY 11/12/13 MILCON projects | 36093 | 36093 | OSD provided additional P&D 23 May 13
2013-07-31 | 2013-07-31 | 2012 | DLA | General P&D | Design efforts for FY 12/13/14 MILCON projects | 34331 | 22470 | OSD provided additional P&D 23 May 13
2013-07-31 | 2013-07-31 | 2013 | DLA | General P&D | Design efforts for FY 13/14/15 MILCON projects | 4608 | 0 | Initial P&D load by OSD 7 Jun 13
2013-07-31 | 2013-07-31 | 2009 | SOCOM | General P&D | MILCON | 14533 | 14446 | From 15Jul13 Update
2013-07-31 | 2013-07-31 | 2010 | SOCOM | General P&D | MILCON | 4069 | 3695 | Awaiting July Update
2013-07-31 | 2013-07-31 | 2011 | SOCOM | General P&D | MILCON | 26782 | 23963 | Awaiting July Update
2013-07-31 | 2013-07-31 | 2012 | SOCOM | General P&D | MILCON | 31468 | 20850 | Awaiting July Update
2013-07-31 | 2013-07-31 | 2013 | SOCOM | General P&D | MILCON | 27620 | 3103 | Awaiting July Update
2013-05-31 | 2013-06-05 | 2010 | WHS | General P&D | Complete design or RFP development of FY11 MILCON projects | 3575 | 3575
2013-05-31 | 2013-06-05 | 2011 | WHS | General P&D | Complete design or RFP development of FY12 MILCON projects | 6257 | 0
2013-05-31 | 2013-06-05 | 2012 | WHS | General P&D | Complete design or RFP development of FY13 MILCON projects
2013-07-31 | 2013-08-15 | 2009 | Army Active | MCA-P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 221132
2013-07-31 | 2013-08-15 |  |  | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000
2013-07-31 | 2013-08-15 | 2010 | Army Active | MCA-P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250679
2013-07-31 | 2013-08-15 |  |  | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000
2013-07-31 | 2013-08-15 | 2011 | Army Active | MCA-P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 219636 | 263727
2013-07-31 | 2013-08-15 |  |  | Host Nation Support | $29,944 Appropriated + $13,000 ATR | 42944 | 42927
2013-07-31 | 2013-08-15 | 2012 | Army Active | MCA-P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 148310
2013-07-31 | 2013-08-15 |  |  | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25500 | 25481
2013-07-31 | 2013-08-15 | 2013 | Army Active | MCA-P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 65000 | 3072
2013-07-31 | 2013-08-15 |  |  | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954 | 22674
2013-07-31 | 2013-08-15 | 2007 | TMA | MCA - P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 80052 | 79993
2013-07-31 | 2013-08-15 | 2008 | TMA | MCA - P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 113065 | 112654
2013-07-31 | 2013-08-15 | 2009 | TMA | MCA - P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 171255 | 166869
2013-07-31 | 2013-08-15 | 2010 | TMA | MCA - P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 72679 | 68802
2013-07-31 | 2013-08-15 | 2011 | TMA | MCA - P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 208312 | 106223

## Minor Construction
Data As Of Date | Submission Date | Fiscal Year | Component | Type of funds | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Notes/remarks
2013-07-31 | 2013-07-31 | 2008 | DoDEA | UMC | Unspecified Minor Construction for projects < $2.M | 666 | 0
2013-07-31 | 2013-07-31 | 2009 | DoDEA | UMC | Unspecified Minor Construction for projects < $2.M | 382 | 4 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2013-07-31 | 2013-07-31 | 2010 | DoDEA | UMC | Unspecified Minor Construction for projects < $2.M | 6275 | 0 | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2011 | DoDEA | UMC | Unspecified Minor Construction for projects < $2.M | 3217 | 0 | Reflects Sequestration Reduction
2013-07-31 | 2013-07-31 | 2013 | DoDEA | UMC | Unspecified Minor Construction for projects < $2.M | 3771 | 0 | Reflects Sequestration Reduction
2013-07-31 | 2013-08-02 | 2009 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 23623 | 19061 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2010 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 36905 | 29543 | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2011 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 11377 | 11252 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2012 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 14149 | 8174 | PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-02 | 2013 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 14562 | 4232 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2013-07-31 | 2013-08-05 | 2009 | MDA | UMC | Used for accomplishing urgent unforeseen construction projects in FY12/13 | 3457 | 3017 | Obligated funds support the EUCOM Radar Site. EUCOM work which resumed on 6 May 2013. Additional obligation of funds supports the Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping project at Fort Greely, AK
2013-07-31 | 2013-08-05 | 2010 | MDA | UMC | Used for accomplishing urgent unforeseen construction projects in FY12-13 | 3717 | 267 | Supports the R&C Piping project at Fort Greely, AK.