## Projects
Data as of Date | Submission Date | Fiscal Year | Component | Project Type | State (2-Alpha)/ Country (3-Alpha) | State or Country Title | Installation | Project Number | Project Title | Solicitation/ Advertise Date | Award Date | Contract Recipient | Original Contract Amount ($000) | Current Contract Obligation ($000) | Start Date | Occupancy Date | Original Completion Date | Current Completion Date | % Complete | Funds Diverted ($000) if applicable | Recipient Project (if applicable) | Recipient Installation (if applicable) | Notes/Remarks
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 447 | AIRCRAFT MAINTENANCE HANGAR, PHASE 1 (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | 19374 | 19976 | 2011-06-23 | 2013-12-05 | 2012-10-08 | 2013-10-15 | 99.5933
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 556 | AIRFIELD ELECTRICAL DISTRIBUTION & CONTROL | 2010-03-15 | 2010-06-24 | MAC ELECTRIC INC | 1727 | 1598 | 2010-07-08 | 2011-11-30 | 2011-06-24 | 2011-12-15 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | BHR | BAHRAIN | NAVSUPPACT BAHRAIN | 928 | WATERFRONT DEVELOPMENT PHASE 2 | 2010-03-19 | 2010-09-28 | NAVY STANDARD DOCUMENT | 33904 | 29298 | 2010-10-12 | 2012-10-24 | 2012-10-24 | 2012-10-24 | 89.0925
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 296 | MESSHALL EXPANSION | 2010-01-15 | 2010-05-03 | R A BURCH CONSTRUCTION CO INC | 19100 | 17222 | 2010-05-17 | 2012-04-12 | 2011-11-09 | 2012-05-12 | 99.8008
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 101 | MAINTENANCE SHOP, WHEELED | 2010-07-28 | 2010-09-30 | I E PACIFIC INC | 15940 | 14707 | 2010-10-14 | 2013-09-12 | 2012-10-14 | 2013-09-30 | 99.6599
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 103 | MAINTENANCE SUNSHADES, WHEELED | 2010-07-02 | 2010-09-29 | ALLEN ENGINEERING CONTRACTOR, INC | 14455 | 12953 | 2010-10-13 | 2013-01-28 | 2012-10-13 | 2013-01-28 | 99.8225
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 107 | COMM/ELECT MAINTENANCE/STORAGE | 2010-07-22 | 2010-09-30 | ALLEN ENGINEERING CONTRACTOR, INC | 13564 | 12554 | 2010-10-14 | 2012-10-14 | 2012-10-14 | 2013-11-29 | 99.9913
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 114 | DINING FACILITY, NORTH MAINSIDE | 2010-07-02 | 2010-09-28 | STRAUB MARTIN A JOINT VENTURE | 17260 | 17988 | 2010-10-12 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 99.8591
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 116 | BACHELOR ENLISTED QUARTERS, 1ST TANKS | 2010-07-02 | 2010-09-28 | STRAUB MARTIN A JOINT VENTURE | 38546 | 36850 | 2010-10-12 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 99.6967
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 121 | MAINTENANCE SHOP, TRACKED | 2010-07-27 | 2010-09-24 | I E PACIFIC INC | 20672 | 18486 | 2010-10-08 | 2013-09-12 | 2012-10-13 | 2013-09-30 | 99.3669
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 126 | STATION COMM FACILITY & INFRASTRUCTURE | 2010-07-16 | 2010-09-27 | R A BURCH CONSTRUCTION CO INC | 40766 | 49539 | 2010-10-11 | 2015-04-30 | 2012-10-20 | 2014-05-10 | 95.7074
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 127 | SUB-STATION AND ELECTRICAL UPGRADES | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 16493 | 25922 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 99.9445
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 128 | ELEC INFRASTRUCTURE UPGRADE, 34.5KV TO 115KV | 2008-01-17 | 2011-06-02 | SOUTHERN CALIFORNIA EDISON | 41774 | 39673 | 2011-06-16 |  | 1996-10-08 | 2014-08-30 | 96.284
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 129 | ELEC POWER PLANT/CO-GEN/GAS TURBINE | 2010-07-16 | 2010-09-24 | T. B. PENICK & SONS, INC. | 54824 | 53717 | 2010-10-08 | 2014-06-17 | 2012-06-30 | 2014-01-27 | 98.2858
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 130 | WATER IMPROVEMENTS AND STORAGE TANK | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 16911 | 23812 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 99.513
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 131 | SEWAGE SYSTEM IMPROVEMENTS | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 4735 | 4832 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 132 | HTHW/CHILLED WATER SYSTEM | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 14341 | 16248 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 99.9954
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 133 | NATURAL GAS SYSTEM EXTENSION | 2009-10-22 | 2010-09-30 | SOUTHERN CALIFORNIA GAS CO | 20931 | 15025 | 2010-10-14 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 99.9868
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 143 | CONSTRUCT ROADS, NORTH MAINSIDE | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 22236 | 20802 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 99.9506
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 146 | INDUSTRIAL WASTE WATER IMPROVEMENTS | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 1994 | 3567 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 99.953
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 170 | BACHELOR ENLISTED QUARTERS, 1ST TANKS | 2010-07-02 | 2010-09-28 | STRAUB MARTIN A JOINT VENTURE | 38644 | 37002 | 2010-10-12 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 99.9259
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 171 | LAYDOWN SITE WORK, NORTH MAINSIDE | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 20560 | 23475 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 100.1657
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 172 | SECONDARY ELEC DISTRIBUTION, NORTH MAINSIDE | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 16654 | 22000 | 2010-06-17 | 2012-10-18 | 2012-03-28 | 2013-02-15 | 99.958
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 173 | ARMORY, 1ST TANKS | 2010-07-20 | 2010-09-29 | I E PACIFIC INC | 11038 | 10317 | 2010-10-13 | 2013-09-12 | 2012-10-22 | 2013-09-30 | 99.5534
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 202 | COMMISSARY, MWTC | 2010-11-29 | 2012-01-25 | KBR FEDERAL SERVICES,LLC | 8128 | 8442 | 2012-02-08 | 2013-12-09 | 2013-02-07 | 2013-12-09 | 96.6637
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 550 | FIRE STATION RENOVATION, MWTC | 2010-01-25 | 2010-03-25 | J I GARCIA CONSTRUCTION INC | 4631 | 4289 | 2010-04-08 | 2012-07-09 | 2011-07-19 | 2012-09-30 | 99.9816
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 086 | EXPAND COMBAT AIRCRAFT LOADING APRON | 2010-01-26 | 2010-03-23 | REYES CONSTRUCTION INC | 6795 | 6041 | 2010-04-06 | 2011-11-09 | 2011-09-12 | 2011-11-09 | 98.3464
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 107 | AVIATION TRANSMITTER/RECEIVER SITE | 2011-04-14 | 2011-07-29 | RQ-BERG JV | 10261 | 9541 | 2011-08-12 | 2014-03-14 | 2013-01-19 | 2014-03-14 | 95.5952
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS MIRAMAR | 178 | AIRCRAFT PARKING APRON MODIFICATION | 2010-07-28 | 2010-12-15 | BALDI BROS INC201 CALIFORNIA AVENUE | 9184 | 8655 | 2010-12-29 | 2013-08-06 | 2012-12-29 | 2013-12-23 | 99.455
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | CA | CALIFORNIA | MCAS MIRAMAR | 307 | BATTALION SQUADRON HEADQUARTERS | 2010-08-16 | 2010-12-16 | SOLTEK PACIFIC CONSTRUCTION CO | 8026 | 7811 | 2010-12-30 | 2012-04-25 | 2011-12-31 | 2012-04-25 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 610 | RECRUIT MARKSMANSHIP TRAINING FACILITY | 2010-04-26 | 2010-08-17 | A&D GC INC | 13594 | 11879 | 2010-08-31 | 2012-06-11 | 2012-02-23 | 2012-06-14 | 95.3567
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1012 | ANGLICO OPERATIONS COMPLEX | 2010-06-29 | 2010-09-28 | WEBCOR/ RA BURCH A JV | 26348 | 23478 | 2010-10-12 | 2013-10-30 | 2013-01-25 | 2013-10-31 | 95.4642
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1016 | RECONNAISANCE BN OPERATIONS COMPLEX | 2010-06-29 | 2010-09-28 | WEBCOR/ RA BURCH A JV | 81206 | 74278 | 2010-10-12 | 2013-10-30 | 2013-01-25 | 2013-10-31 | 97.9259
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1019 | COMM/ELEC MAINTENANCE FACILITIES | 2010-07-30 | 2010-09-23 | RQ CONSTRUCTION, LLC | 12911 | 12749 | 2010-10-07 | 2013-01-31 | 2012-04-02 | 2013-06-10 | 96.0234
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1029 | WFTBN SUPPORT FACILITIES, EDSON RANGE | 2010-05-17 | 2010-08-17 | BILBRO CONSTRUCTION COMPANY | 16282 | 14470 | 2010-08-31 | 2013-03-04 | 2012-03-09 | 2013-03-04 | 99.932
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1033 | ENLISTED DINING FACILITY, EDSON RANGE | 2010-05-28 | 2010-09-10 | WHITING-TURNER CONTRACTING CO | 38259 | 34934 | 2010-09-24 | 2013-07-23 | 2012-09-24 | 2013-04-30 | 99.7042
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1041 | EXPANSION OF SRTTP TO 7.5 MGD | 2010-07-29 | 2010-09-28 | CDM-FILANC JV | 51114 | 45846 | 2010-10-12 | 2015-02-17 | 2012-10-12 | 2015-08-21 | 90.2043
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1043 | NORTH REGION TERITARY TREATMENT PLANT INC 1 OF 2 | 2010-07-29 | 2010-09-28 | CDM-FILANC JV | 117679 | 97767 | 2010-10-12 | 2015-02-17 | 2012-10-12 | 2015-08-21 | 87.6209
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1048 | GAS/ELECTRICAL UPGRADES | 2011-07-14 | 2011-09-28 | RQ-BERG JV | 49713 | 41198 | 2011-10-12 | 2015-07-31 | 2014-01-15 | 2014-07-03 | 83.4534
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1067 | BACHELOR ENLISTED QUARTERS, LAS FLORES | 2010-06-29 | 2010-09-28 | WEBCOR/ RA BURCH A JV | 41375 | 37867 | 2010-10-12 | 2013-10-30 | 2013-01-25 | 2013-10-31 | 99.3938
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1069 | RECRUIT BARRACKS, EDSON RANGE | 2010-04-20 | 2010-09-21 | HARPER CONSTRUCTION COMPANY, INC | 48523 | 44718 | 2010-10-05 | 2013-02-28 | 2012-10-16 | 2013-03-04 | 98.957
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1084 | ENLISTED DINING FACILITY | 2010-05-28 | 2010-09-10 | WHITING-TURNER CONTRACTING CO | 32421 | 30118 | 2010-09-24 | 2013-07-23 | 2012-09-24 | 2013-04-30 | 99.8935
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1086 | RECRUIT BARRACKS, FIELD/K-SPAN | 2010-04-06 | 2010-09-07 | T. B. PENICK & SONS, INC. | 20164 | 19874 | 2010-09-21 | 2014-05-21 | 2012-09-30 | 2014-05-22 | 97.208
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1093 | COMMUNICATIONS UPGRADES | 2010-06-30 | 2010-09-28 | URS GROUP, INC. | 71427 | 71834 | 2010-10-12 | 2014-11-06 | 2012-10-21 | 2014-11-06 | 98.1671
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1094 | ELECTRICAL DISTRIBUTION SYSTEM | 2010-06-30 | 2010-09-28 | URS GROUP, INC. | 73986 | 74432 | 2010-10-12 | 2014-11-06 | 2012-10-21 | 2014-11-06 | 91.7061
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 159A | OPERATION ACCESS POINTS | 2011-07-29 | 2011-09-14 | REYES CONSTRUCTION INC | 13347 | 12264 | 2011-09-28 | 2014-09-29 | 2013-10-07 | 2014-09-29 | 88.9928
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCLB BARSTOW CA | 947V | INDUSTRIAL MACHINE SHOP FACILITY | 2009-09-21 | 2010-03-18 | HENSEL PHELPS CONSTRUCTION CO | 6718 | 6286 | 2010-04-01 | 2010-12-15 | 2010-12-27 | 2010-12-27 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | CA | CALIFORNIA | NAF EL CENTRO CA | 600 | RESERVE CENTER MOVE TO LUKE AFB, NOSC PHOENIX | 2010-01-21 | 2010-04-22 | A&D GC INC | 11667 | 10606 | 2010-05-06 | 2011-12-16 | 2011-09-19 | 2011-11-21 | 99.9979
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | CA | CALIFORNIA | NAS LEMOORE CA | 049 | RESERVE CENTER ADDITION, ALAMEDA | 2010-07-21 | 2010-09-24 | J I GARCIA CONSTRUCTION INC | 6236 | 7291 | 2010-10-08 | 2013-12-23 | 2012-04-01 | 2012-08-01 | 99.8509
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 129 | PUBLIC WORKS SHOPS CONSOLIDATION | 2009-11-17 | 2010-08-06 | HALBERT CONSTRUCTION | 8880 | 7373 | 2010-08-20 | 2012-06-12 | 2012-05-25 | 2012-05-25 | 99.9229
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 503 | ADD/ALTER MARINE MAMMAL SURGICAL CENTER | 2010-08-23 | 2010-09-30 | SYNERGY SYSTEMS INC | 2992 | 2771 | 2010-10-14 | 2012-09-21 | 2012-06-02 | 2012-08-28 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVSUPPACT MONTEREY CA | 174 | MARINE METEOROLOGY CENTER | 2010-08-11 | 2010-09-30 | SOLTEK PACIFIC CONSTRUCTION CO | 10961 | 9836 | 2010-10-14 | 2014-04-11 | 2012-04-21 | 2013-02-20 | 99.7145
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | CA | CALIFORNIA | NAVWPNSTA SEAL BEACH | 063 | MARINE CORPS RESERVE TRAINING CENTER | 2010-07-23 | 2010-09-30 | RMA LAND CONSTRUCTION, INC. | 12044 | 11445 | 2010-10-14 | 2012-05-23 | 2012-04-07 | 2013-04-20 | 99.9997
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 777V | WEAPONS DYNAMICS RDT&E CENTER | 2009-10-22 | 2010-02-08 | VANDER WERFF, PETER CONSTRUCTION | 4893 | 4723 | 2010-02-22 | 2010-12-15 | 2010-10-06 | 2010-12-15 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 908F | F-35 EDWARDS RAMP EXTENSION (EDWARDS AFB) | 2010-04-16 | 2010-02-23 | NAVY STANDARD DOCUMENT | 1983 | 1944 | 2010-03-09 | 2010-06-01 | 2010-06-01 | 2010-06-01 | 99.9318
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | CT | CONNECTICUT | NAVSUBASE NEW LONDON CT | 848 | MK-48 TORPEDO MAGAZINE | 2011-01-28 | 2011-03-03 | LAROSA BUILDING GROUP, LLC | 6137 | 4728 | 2011-03-17 | 2012-11-28 | 2013-01-28 | 2013-03-22 | 81.8225
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 001V | CRYSTAL PARK 5 MOVE TO ARLINGTON SERVICE CENT | 2010-04-16 | 2010-09-17 | HITT CONTRACTING, INC | 49600 | 70776 | 2010-10-01 | 2012-01-13 | 2011-08-01 | 2012-07-09 | 99.9377
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 003A | NAVY SYSTEMS MGMT ACTIVITY RELOCATION INC 2 | 2009-07-06 | 2009-09-30 | ATLANTIC CONTINGENCY CONSTRUCTION,LLC | 71699 | 72355 | 2009-10-14 | 2011-09-28 | 2011-06-30 | 2011-09-28 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 183V | WNY-A-12 BRAC Relocation to Bldg 183 | 2010-08-16 | 2010-11-29 | ALLEN AND SHARIFF CORP | 7517 | 8849 | 2010-12-13 | 2012-04-10 | 2011-08-30 | 2011-08-30 | 99.8319
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 220V | WNY-220, PEO-EIS PMW 200 & 240 BRAC TO BLDG 220 | 2010-08-18 | 2010-11-29 | ARRIBA CORPORATION | 7580 | 9626 | 2010-12-13 | 2013-01-09 | 2011-08-30 | 2012-10-24 | 99.7934
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NSA NORTH POTOMAC | 189 | RDT&E SUPPORT FACILITY | 2010-07-16 | 2010-09-28 | WHITING-TURNER CONTRACTING CO | 6177 | 6078 | 2010-10-12 | 2012-02-08 | 2012-06-28 | 2012-06-28 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NSA NORTH POTOMAC | 149V | CRYSTAL PARK 5 TO ARLINGTON SERVICE CENTER | 2010-04-16 | 2010-09-17 | HITT CONTRACTING, INC | 7275 | 10058 | 2010-10-01 | 2012-01-13 | 2011-08-01 | 2012-07-09 | 99.0522
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 220 | AMMUNITION SUPPLY POINT | 2012-04-30 | 2012-09-10 | CH2M HILL-METAG JOINT VENTURE | 13922 | 12260 | 2012-09-24 | 2015-04-29 | 2014-05-14 | 2014-05-19 | 22.9981
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 235 | SECURITY FENCING 1 | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 11850 | 10055 | 2012-04-16 | 2014-10-31 | 2013-12-26 | 2014-02-19 | 93.2221
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 237 | FIRE STATION | 2010-05-03 | 2010-07-21 | UNITED INFRASTRUCTURE PROJECTS FZCO | 4598 | 3863 | 2010-08-04 | 2013-09-28 | 2012-03-02 | 2012-11-06 | 95.8333
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 916 | INTERIOR PAVED ROADS | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 15666 | 13880 | 2012-04-16 | 2014-10-31 | 2013-12-26 | 2014-02-19 | 77.5443
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | ESP | SPAIN | NAVSTA ROTA SP | 898 | PROVIDE RECEPTION AIRFIELD FACILITIES | 2010-04-28 | 2010-09-28 | COPCISA SA ELECNOR SA U.T.E. | 12001 | 12045 | 2010-10-12 | 2013-09-06 | 2013-01-25 | 2014-04-14 | 97.9594
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | MCSF BLOUNT ISLAND | 006 | PORT OPERATIONS FACILITY | 2010-04-30 | 2011-02-16 | CMS CORP/TOLTEST JV IV | 3981 | 3659 | 2011-03-02 | 2013-01-08 | 2012-08-20 | 2013-01-08 | 98.9259
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 629 | ARMED FORCES RESERVE CENTER | 2014-04-03 | 2010-09-30 | Awarded by Other Agency | 7568 | 3394 | 2010-10-14 |  | 2016-01-12 | 2016-01-12 | 57.5596
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 630 | P-8A (MMA) FACILITIES MODIFICATION | 2010-04-29 | 2010-06-30 | SAUER, INC. | 3916 | 7376 | 2010-07-14 | 2011-11-08 | 2011-08-04 | 2011-10-30 | 99.8691
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS PENSACOLA FL | 724 | CORRY 'A' SCHOOL BACHELOR ENLISTED QUARTERS | 2010-04-23 | 2010-07-26 | ANDERSON DRACE JOINT VENTURE | 16929 | 19805 | 2010-08-09 | 2013-09-20 | 2012-08-18 | 2013-09-20 | 99.9013
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS PENSACOLA FL | 782 | SIMULATOR ADDITION FOR UMFO PROGRAM | 2009-12-18 | 2010-04-27 | KAISERKANE, INC. | 3605 | 3804 | 2010-05-11 | 2012-03-09 | 2011-05-02 | 2011-09-27 | 94.3258
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 273 | T-6B JPATS TRAINING OPS PARALOFT FACILITY | 2010-04-16 | 2011-01-05 | ARROW-IMC, JOINT VENTURE | 3168 | 3262 | 2011-01-19 | 2013-10-29 | 2013-10-29 | 2015-02-26 | 99.3674
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 925 | BEQ EOD SCHOOL, PHASE 2 | 2010-02-05 | 2010-07-30 | Awarded by Other Agency | 22769 | 22009 | 2010-08-13 |  |  |  | 99.6461
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 187 | CHANNEL DREDGING | 2010-06-14 | 2010-08-24 | Awarded by Other Agency | 29757 | 45298 | 2010-09-07 | 2012-08-03 | 2012-08-03 | 2012-08-03 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 760 | FITNESS CENTER ADDITION, MAYPORT | 2011-01-12 | 2011-05-06 | SAUER, INC. | 27356 | 26581 | 2011-05-20 | 2013-09-03 | 2013-05-14 | 2013-08-26 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 777 | WHARF CHARLIE REPLACEMENT | 2010-05-24 | 2010-08-25 | MISENER MARINE CONSTRUCTION, INC. | 26695 | 28122 | 2010-09-08 | 2013-12-20 | 2012-08-24 | 2013-06-06 | 99.2893
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GA | GEORGIA | MCLB ALBANY GA | 930 | MCA HARDSTAND, PHASE 1 | 2010-05-28 | 2010-08-18 | HCR/CAPE JV, LLC | 3102 | 3278 | 2010-09-01 | 2013-03-18 | 2011-08-18 | 2013-03-19 | 92.0486
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 204 | APRA HARBOR WHARF IMPROVEMENT, INC 1 OF 2 | 2010-05-14 | 2010-09-30 | GUAM MACC BUILDERS A JV | 133082 | 105966 | 2010-10-14 | 2014-01-28 | 2013-08-27 | 2014-03-15 | 90.5477
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 465 | CONSOLIDATED SLC TRAINING & CSS-15 HQ FAC | 2009-11-01 | 2010-05-10 | DCK-ECC PACIFIC GUAM, LLC | 30672 | 24963 | 2010-05-24 | 2013-02-27 | 2011-11-30 | 2014-04-28 | 85.4576
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 528 | TORPEDO EXERCISE SUPPORT BUILDING | 2009-11-01 | 2010-05-10 | DCK-ECC PACIFIC GUAM, LLC | 6399 | 8726 | 2010-05-24 | 2013-02-27 | 2011-11-30 | 2014-04-28 | 86.1044
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 1003 | MILITARY WORKING DOG RELOCATION, APRA HARBOR | 2010-06-10 | 2010-09-29 | PACIFIC WEST BUILDERS | 11792 | 10376 | 2010-10-13 | 2014-08-21 | 2012-09-28 | 2014-03-31 | 85.9765
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 1006 | DEFENSE ACCESS ROAD IMPROVEMENTS | 2010-04-02 | 2010-12-03 | DEPARTMENT OF TRANSPORTATION, FEDERAL HIGHWAY ADMINISTRATION | 8608 | 1078 | 2010-12-17 |  |  |  | 16.2415
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GU | GUAM | US NAVSUPACT ANDERSEN GUAM | 100 | NORTH RAMP UTILITIES, INC 1 OF 2 | 2010-06-30 | 2011-04-06 | GUAM PACIFIC INTERNATIONAL, LLCDBA CMS CORP TOLTEST JV | 22524 | 22457 | 2011-04-20 | 2014-10-29 | 2013-03-03 | 2014-10-29 | 80.3414
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | GU | GUAM | US NAVSUPACT ANDERSEN GUAM | 101 | NORTH RAMP PARKING, INC 1 OF 2 | 2010-06-30 | 2011-04-06 | PERINI/NORTON A JOINT VENTURE | 88797 | 84123 | 2011-04-20 | 2014-06-04 | 2014-01-15 | 2014-07-21 | 99.1328
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 004 | APCSS CONFERENCE & TECHNOLOGY LEARNING CENTER | 2010-05-25 | 2010-08-04 | Awarded by Other Agency | 11431 | 12775 | 2010-08-18 | 2012-06-12 | 2012-06-12 | 2012-06-12 | 93.5506
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 182 | MISSILE MAGAZINES, WEST LOCH | 2009-12-14 | 2010-01-28 | DCK PACIFIC CONSTRUCTION, LLC | 16223 | 14095 | 2010-02-11 | 2011-12-16 |  | 2011-12-20 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 307 | PRODUCTION SERVICES SUPPORT FACILITY | 2010-08-11 | 2010-09-29 | MANSON-NAN HAWAII JV | 19165 | 17370 | 2010-10-13 | 2012-11-21 | 2012-06-29 | 2013-07-29 | 99.9904
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 587B | SUB DRIVE-IN MSF, BECKONING POINT INC 3 OF 3 | 2008-01-10 | 2008-08-11 | WATTS-HEALY TIBBITTS A JV | 8155 | 8960 | 2008-08-25 | 2010-12-30 | 2010-10-10 | 2010-12-30 | 77.8797
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 839 | RANGE, 1000 YARDS, PUULOA | 2010-08-10 | 2010-09-30 | NIKING CORP. | 7464 | 6646 | 2010-10-14 | 2012-02-22 | 2011-08-26 | 2012-02-10 | 99.9147
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | IL | ILLINOIS | GREAT LAKES NAVAL STATION | 133 | NOSC CONSOLIDATION BATTLE CREEK MI | 2010-08-13 | 2011-01-26 | FACILITY DEFENSE CONSULTANTS INC.DBA HANKE CONSTRUCTORS | 8899 | 8476 | 2011-02-09 | 2012-09-06 | 2012-06-01 | 2012-09-06 | 97.1997
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | IL | ILLINOIS | GREAT LAKES NAVAL STATION | 630V | ARMED FORCES RESERVE CENTER | 2009-10-23 | 2010-02-26 | BETTER BUILT + CLARK LLC | 12660 | 12608 | 2010-03-12 | 2011-09-15 | 2011-06-08 | 2011-08-17 | 99.4578
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | IN | INDIANA | NAVAL SUPPORT ACTIVITY CRANE | 340 | STRATEGIC WEAPONS SYSTEM ENGINEERING | 2010-05-26 | 2010-08-25 | CANT BE BEAT FENCE ANDCONSTRUCTION, LLC | 14613 | 13160 | 2010-09-08 | 2012-05-28 | 2012-01-05 | 2012-05-28 | 99.4456
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | LA | LOUISIANA | HDQTRS 4TH MARDIV NEW ORLEANS | 048 | RESERVE CENTER, JOLIET IL | 2010-05-27 | 2010-09-30 | CHARPIE-KORTE JOINT VENTURE | 8794 | 8734 | 2010-10-14 | 2012-08-15 | 2011-12-15 | 2012-05-20 | 97.5271
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | LA | LOUISIANA | HDQTRS 4TH MAW NEW ORLEANS LA | 196 | RESERVE VEHICLE MAINTENANCE FACILITY | 2009-11-25 | 2010-03-11 | TEAM CONSTRUCTION, LLC J/V MILITARY& FEDERAL CONSTRUCTION CO.,INC/W.T | 3517 | 3028 | 2010-03-25 | 2011-11-30 | 2011-04-14 | 2011-09-06 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | LA | LOUISIANA | NSA NEW ORLEANS LA | 506V | FLAG HOUSING - QUARTERS A | 2010-11-29 | 2011-01-20 | AMERICAN CONTRACTOR AND TECHNOLOGY | 1814 | 1794 | 2011-02-03 | 2011-09-26 | 2011-08-18 | 2011-10-13 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | MD | MARYLAND | NAVAL AIR STATION PAX RIVER | 140 | SPECIAL COMMUNICATIONS REQUIREMENTS ENGINEERING FACILITY | 2011-05-12 | 2011-08-08 | G-W MANAGEMENT SERVICES, LLC | 11304 | 11674 | 2011-08-22 | 2013-10-31 | 2013-01-23 | 2013-12-10 | 99.2606
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | ME | MAINE | NAS BRUNSWICK ME | 028V | MARINE CORPS RESERVE CENTER | 2010-02-15 | 2010-07-23 | NUTMEG COMPANIES, INC., THE | 9314 | 9684 | 2010-08-06 | 2011-10-14 | 2011-07-28 | 2011-11-23 | 99.3361
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | ME | MAINE | NSS PORTSMOUTH NAVY SHIPYARD | 280 | GATE 2 IMPROVEMENTS | 2011-08-31 | 2012-02-21 | MCC CONSTRUCTION CORPORATION | 7403 | 7893 | 2012-03-06 | 2013-09-20 | 2013-03-21 | 2013-07-12 | 95.4998
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 141 | EMS/FIRE VEHICLE FACILITY | 2009-12-14 | 2010-03-31 | CHAVIS' INC. | 6459 | 6186 | 2010-04-14 | 2012-03-15 | 2011-10-22 | 2012-03-18 | 99.2015
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 146 | ORDNANCE MAGAZINES | 2010-10-21 | 2010-12-16 | SAUER, INC. | 3700 | 3397 | 2010-12-30 | 2014-01-23 | 2012-07-10 | 2013-11-04 | 99.3719
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 311 | PARALLEL TAXIWAY | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 9283 | 9911 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 88.894
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 619 | TACTICAL SUPPORT VAN PAD ADDITION | 2009-10-14 | 2010-01-26 | ALDERMAN BUILDING CO., INC. | 3469 | 3347 | 2010-02-09 | 2011-07-14 | 2011-01-26 | 2011-08-20 | 93.7335
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 652 | VMMT-204 MAINTENANCE HANGAR, PHASE 3 | 2010-07-14 | 2010-09-27 | F & S MECHANICAL AND PLUMBINGSERVICES, INC. | 26687 | 25589 | 2010-10-11 | 2014-10-01 | 2013-09-30 | 2014-01-14 | 91.8014
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 688 | APRON EXPANSION, PHASE 2 | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 32726 | 35773 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 97.8008
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 714 | GYMNASIUM/OUTDOOR POOL | 2009-07-24 | 2010-12-09 | WHITING-TURNER CONTRACTING CO | 17792 | 16202 | 2010-12-23 | 2012-08-23 | 2010-08-14 | 2013-06-14 | 79.6226
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1160 | PHYSICAL FITNESS CENTER | 2009-08-27 | 2010-03-23 | SUFFOLK CONSTRUCTION CO INC | 22908 | 21764 | 2010-04-06 | 2013-10-01 | 2012-01-27 | 2013-10-11 | 99.8437
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1194 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 24810 | 31207 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 98.2885
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1195 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 25300 | 32104 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 98.0995
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1196 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 25300 | 32174 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 98.0377 | -1009
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1197 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 24047 | 29118 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 93.5177
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1233 | MAINTENANCE/OPERATIONS COMPLEX | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 29621 | 25008 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 85.6448 | -20100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1247 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 22509 | 16453 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 96.5243
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1266 | UTILITY EXPANSION COURTHOUSE BAY | 2011-03-30 | 2011-05-19 | WALBRIDGE ALDINGER COMPANY, INC. | 30983 | 28921 | 2011-06-02 | 2015-04-01 | 2013-06-30 | 2014-01-26 | 85.4416
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1268 | SOI EAST FACILITIES, CAMP GEIGER | 2010-03-19 | 2010-08-16 | DCK NORTH AMERICA, LLC | 33644 | 43881 | 2010-08-30 | 2014-10-21 | 2013-04-10 | 2014-10-21 | 94.1893
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1269 | FIELD TRAINING FACILITY, DEVIL DOG SOI | 2010-04-02 | 2010-06-29 | ARCHER WESTERN CONTRACTORS, LTD | 35465 | 29351 | 2010-07-13 | 2013-12-03 | 2012-12-05 | 2013-12-16 | 99.4889
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1297 | 4TH INFANTRY BATTALION OPS COMPLEX | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 31109 | 26074 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 85.441 | -20878
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1298 | ROAD NETWORK, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 10943 | 16128 | 2010-03-11 | 2014-03-28 | 2012-10-27 | 2013-10-03 | 99.108
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1304 | MP WORKING DOG KENNEL RELOCATION | 2010-08-17 | 2010-09-01 | THR ENTERPRISES, INC. | 6073 | 5582 | 2010-09-15 | 2013-02-08 | 2012-03-09 | 2013-02-08 | 99.716
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1310 | PRE-TRIAL DETAINEE FACILITY | 2010-02-02 | 2010-08-26 | TEAM ENVIRO JOINT VENTURE II | 16332 | 15859 | 2010-09-09 | 2012-09-18 | 2012-03-18 | 2013-02-08 | 99.9276
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1311 | CONSOLIDATED INFOTECH/TELCOM COMPLEX | 2010-12-16 | 2011-03-04 | DANIELS & DANIELS GRUNLEYJOINT VENTURE | 35011 | 33710 | 2011-03-18 | 2014-09-25 | 2014-07-01 | 2014-09-25 | 98.2915 | -4617
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1382 | NEW BASE ENTRY POINT AND ROAD PHASE 1 | 2011-11-08 | 2010-07-12 | SKANSKA USA CIVIL SOUTHEAST INC | 64692 | 73033 | 2010-07-26 | 2014-08-15 | 2013-01-10 | 2014-05-06 | 96.0162
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | NV | NEVADA | NAS FALLON NV | 306 | WARRIOR PHYSICAL TRAINING FACILITY (FITNESS CENTER) | 2010-07-21 | 2010-09-28 | STRAUB CONSTRUCTION, INC. | 11177 | 10006 | 2010-10-12 | 2012-06-07 | 2012-04-05 | 2012-05-12 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 115 | MULTI-PURPOSE FLIGHT SIMULATOR | 2010-08-18 | 2010-09-29 |  | 6254 | 6768 | 2010-10-13 | 2011-10-20 | 2011-10-20 | 2011-10-20 | 88.3632
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 952 | INSTALL HVAC SYSTEM AT NOSC AVOCA PA | 2011-01-06 | 2011-02-25 | WU & ASSOCIATES INC | 3191 | 3153 | 2011-03-11 | 2012-08-06 | 2011-12-10 | 2012-10-01 | 96.6174
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 451 | OFFICER TRAINING COMMAND QUARTERS | 2010-02-12 | 2010-08-13 | ABSHER CONSTRUCTION CO | 44074 | 46503 | 2010-08-27 | 2013-05-22 | 2012-12-28 | 2014-07-22 | 97.9881
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 482 | RENOVATION OF SENIOR ENLISTED ACADEMY (BLDG 1269) | 2011-02-03 | 2011-04-14 | CUTTER ENTERPRISES, LLC | 6550 | 8678 | 2011-04-28 | 2013-05-01 | 2012-07-20 | 2013-11-06 | 98.6989
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 485 | RENOVATIONS TO PERRY HALL (NAPS TRAINING SUPPORT SPACE) | 2010-09-17 | 2010-11-05 | WATERMARK ENVIRONMENTAL, INC. | 8454 | 8489 | 2010-11-19 | 2012-12-17 | 2012-01-14 | 2013-06-30 | 91.0033
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 441 | WIDE BODY AIRCRAFT FUEL LANE | 2009-12-09 | 2010-01-25 | SMALL BUSINESS GROUP, INC | 1037 | 923 | 2010-02-08 | 2010-11-03 | 2011-01-28 | 2011-01-28 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCRD/BEAUFORT PI SC | 360 | ELECTRICAL SUBSTATION AND SYSTEM UPGRADE | 2010-04-30 | 2010-08-31 | TEAM CONSTRUCTION, LLC J/V MILITARY& FEDERAL CONSTRUCTION CO.,INC/W.T | 6455 | 5189 | 2010-09-14 | 2014-08-15 | 2012-03-08 | 2014-03-28 | 89.4467
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | NAVAL SUPPORT ACTY CHASN | 300V | CONSOLIDATED BRIG ADDITION | 2009-09-08 | 2009-12-18 | HUNT CONSTRUCTION GROUP, INC. | 8647 | 8445 | 2010-01-01 | 2011-05-04 | 2011-05-04 | 2011-05-04 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | NAVAL SUPPORT ACTY CHASN | 301V | SPAWAR DATA CENTER | 2009-11-25 | 2010-05-05 | SUFFOLK CONSTRUCTION CO INC | 10694 | 10333 | 2010-05-19 | 2011-07-28 | 2011-06-06 | 2011-07-28 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | TX | TEXAS | NAS CORPUS CHRISTI TX | 105 | RESERVE TRAINING CENTER | 2010-04-15 | 2010-06-30 | GIDEON MARSHALL JOINT VENTURE | 2666 | 2662 | 2010-07-14 | 2011-09-23 | 2011-07-13 | 2011-09-02 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | TX | TEXAS | NAS CORPUS CHRISTI TX | 437 | OPERATIONAL FACILITIES FOR T-6, GOLIAD OLF | 2011-01-11 | 2011-08-05 | THE ROSS GROUP CONSTRUCTION CORP.DBA THE ROSS GROUP | 21037 | 21051 | 2011-08-19 | 2012-09-26 | 2012-05-26 | 2012-09-26 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | TX | TEXAS | NAS FORT WORTH JRB TX | 039 | REPLACE JOINT BASE COMMUNICATIONS BLDG | 2010-05-21 | 2010-08-06 | I LEETEX/HILL & WILKINSON LLC | 5061 | 4625 | 2010-08-20 | 2012-04-20 | 2011-11-19 | 2012-04-20 | 99.9933
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | TX | TEXAS | NAS FORT WORTH JRB TX | 055 | JOINT RESERVE CENTER | 2010-06-18 | 2010-12-03 | Awarded by Other Agency | 6024 | 5507 | 2010-12-17 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 93.2089
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | TX | TEXAS | NAS KINGSVILLE TX | 287 | RENEWABLE ENERGY DEMO PROJECT - SOLAR PANEL ARRAY | 2010-07-16 | 2010-09-10 | CHEVRON U.S.A. INC. | 3694 | 3420 | 2010-09-24 | 2011-12-08 | 2011-09-05 | 2011-09-05 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 851 | NAVAL CONSTRUCTION DIV OPERATIONS CONTROL FAC | 2010-03-10 | 2010-06-22 | NOAH ENTERPRISES AND MID EASTERNBUILDERS INC JV1 | 13184 | 11354 | 2010-07-06 | 2013-04-15 | 2012-07-06 | 2013-04-15 | 88.4299
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 221V | BUILDING 1558 RENOVATIONS FOR SPAWAR | 2010-04-23 | 2010-07-26 | NOAH ENTERPRISES, INC. | 2081 | 1801 | 2010-08-09 | 2011-08-19 | 2011-07-18 | 2011-10-07 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 406 | OPERATIONAL FLIGHT SIMULATOR | 2010-03-17 | 2010-07-15 | GDI/ALLEN & SHARIFF JOINT VENTURE | 3370 | 3222 | 2010-07-29 | 2012-04-25 | 2011-08-15 | 2011-09-16 | 99.6562
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 548 | STUDENT DINING FACILITY, THE BASIC SCHOOL | 2010-06-11 | 2010-10-19 | HARKINS BUILDERS INC. | 15483 | 14519 | 2010-11-02 | 2013-06-14 | 2012-08-09 | 2013-04-21 | 95.9849
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 565 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 4 | 2010-06-11 | 2010-10-19 | HARKINS BUILDERS INC. | 33584 | 31393 | 2010-11-02 | 2013-06-14 | 2012-08-09 | 2013-04-21 | 97.6424
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 614 | SOUTH MAINSIDE ELECTRICAL SUBSTATION | 2010-07-22 | 2010-09-29 | WHITING-TURNER CONTRACTING CO | 11138 | 12736 | 2010-10-13 | 2014-09-26 | 2012-04-11 | 2014-11-06 | 93.0315
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 620 | BATTALION TRAINING FACILITY, MSGBN | 2010-05-28 | 2010-09-30 | SAUER, INC. | 10980 | 10485 | 2010-10-14 | 2012-02-24 | 2011-11-11 | 2011-11-11 | 99.005
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 625 | MC INFORMATION OPERATIONS CENTER | 2010-05-07 | 2010-09-28 | THE HASKELL COMPANY | 29630 | 25455 | 2010-10-12 | 2012-09-19 | 2012-05-13 | 2012-09-18 | 99.7664
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 132 | SOF CAFETERIA | 2011-05-10 | 2011-08-30 | SAUER, INC. | 11346 | 10564 | 2011-09-13 | 2013-06-11 | 2013-02-23 | 2013-03-12 | 99.2025
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 837 | C-40 HANGAR | 2009-11-24 | 2010-03-31 | HOURIGAN CONSTRUCTION CORPORATION | 18008 | 18565 | 2010-04-14 | 2012-05-03 | 2012-03-30 | 2012-10-31 | 99.8768
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL SUPPORT STATION NRFK NSY | 516 | SHIP REPAIR PIER REPLACEMENT INC 1 OF 2 | 2010-05-27 | 2010-09-29 | SKANSKA USA CIVIL SOUTHEAST INC | 133014 | 123339 | 2010-10-13 | 2015-10-02 | 2014-11-22 | 2015-10-02 | 95.2935
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 016 | E-2D AIRCREW TRAINER FACILITY | 2009-12-07 | 2010-05-07 | HOURIGAN CONSTRUCTION CORPORATION | 5737 | 5675 | 2010-05-21 | 2011-11-21 | 2011-07-23 | 2011-12-02 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 838 | E-2D FACILITIES UPGRADE | 2010-08-27 | 2010-11-10 | VIRTEXCO CORPORATION | 5434 | 5784 | 2010-11-24 | 2012-12-18 | 2012-01-02 | 2012-12-30 | 93.4796
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSUPPACT HAMPTON ROADS VA | 208A | JOINT REGIONAL CORRECTIONAL FAC INC 2 OF 2 | 2009-02-06 | 2009-08-21 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | 42521 | 42477 | 2009-09-04 | 2011-06-15 | 2011-05-01 | 2011-06-15 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 311 | ELECTROMAGNETIC RESEARCH & ENGINEERING FAC ADDITION PHASE 2 | 2010-06-16 | 2010-09-14 | G-W MANAGEMENT SERVICES, LLC | 3721 | 3690 | 2010-09-28 | 2013-04-26 | 2012-04-04 | 2013-04-14 | 97.8099
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 356A | CVN MAINTENANCE PIER REPLACEMENT INC 2 OF 2 | 2007-11-07 | 2010-01-25 | NOVA GROUP/TUTOR-SALIBAA JOINT VENTURE | 72353 | 62809 | 2010-02-08 | 2012-01-10 | 2012-01-05 | 2012-01-26 | 91.6469
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 973E | LIMITED AREA PRODUCTION/STRG CMPLX INC 6 OF 7 | 2006-11-20 | 2010-01-04 | KIEWIT-GENERAL, A JOINT VENTURE | 91449 | 87292 | 2010-01-18 | 2012-06-01 | 2011-11-08 | 2012-10-29 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 977A | ENCLAVE FENCING/PARKING | 2010-06-18 | 2010-09-30 | WATTS-GRANITE A JV | 69877 | 44118 | 2010-10-14 | 2013-08-08 | 2012-11-28 | 2013-09-02 | 60.2796
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVMAG INDIAN ISLAND WA | 605 | ORDNANCE STORAGE PADS WITH COVERS (2) | 2010-04-14 | 2010-08-17 | ADVANCED TECHNOLOGY CONSTRUCTION | 3803 | 5008 | 2010-08-31 | 2013-05-17 | 2012-02-23 | 2013-06-06 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVSTA EVERETT WA | 164 | SMALL CRAFT LAUNCH | 2011-05-05 | 2011-07-07 | MANSON CONSTRUCTION CO | 3120 | 3462 | 2011-07-21 | 2012-11-16 | 2012-05-02 | 2012-11-22 | 88.2542
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVSTA EVERETT WA | 702 | SPECIALIZED SERE TRAINING AREA | 2009-12-06 | 2010-03-31 | LCC-MZT TEAM II | 13266 | 12669 | 2010-04-14 | 2011-11-17 | 2011-09-02 | 2011-10-10 | 99.5942
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Major Construction | WV | WEST VIRGINIA | NIOC SUGAR GROVE WV | 205 | EMERGENCY SERVICES CENTER | 2010-05-24 | 2010-09-28 | ARCHER WESTERN CONTRACTORS, LTD | 9178 | 9525 | 2010-10-12 | 2014-03-31 | 2012-04-25 | 2013-09-30 | 98.1416
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | MFH Construction | GU | GUAM | COMNAVMARIANAS GUAM | H952 | REPLACEMENT, 30 UNITS AT NORTH TIPALAO, PH3 | 2010-02-15 | 2010-06-16 | FED-CON A JV | 16587 | 16279 | 2010-06-30 | 2013-12-05 | 2011-10-09 | 2012-01-05 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | MFH Construction | KOR | KOREA | COMFLEACT CHINHAE KS | H115 | CONSTRUCT FH WELCOME CENTER , WAREHOUSE, SELF-HELP | 2010-01-06 | 2010-08-12 | Awarded by Other Agency | 3576 | 3482 | 2010-08-26 | 2013-05-31 | 2012-10-30 | 2013-05-31 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | MFH Improvement | DC | DISTRICT OF COLUMBIA | MARBKS WASHINGTON DC | 1001 | WHOLE HOUSE REVITAL'N TO "HOME OF THE COMMANDANTS" | 2010-03-18 | 2010-06-17 | G-W MANAGEMENT SERVICES, LLC | 3599 | 4140 | 2010-07-01 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | MFH Improvement | ESP | SPAIN | NAVSTA ROTA SP | 0803 | DUPLEX CONVERSION PH II | 2010-07-08 | 2010-12-28 | UTE CASTELLANO COBRA MATOC | 8348 | 9056 | 2011-01-11 | 2013-06-22 | 2012-04-10 | 2013-06-22 | 99.824 | -2704
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | MFH Improvement | GU | GUAM | COMNAVMARIANAS GUAM | 1210 | INSTALL WINDOW SHUTTERS, 146 UNITS AT NEW APRA | 2010-04-15 | 2010-04-22 | SERRANO CONSTRUCTION ANDDEVELOPMENT CORPORATION | 1005 | 977 | 2010-05-06 | 2011-01-03 | 2010-11-19 | 2011-01-12 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | MFH Improvement | GU | GUAM | COMNAVMARIANAS GUAM | 1411 | INSTALL WINDOW SHUTTERS PH III AND IV , LOCKWOOD TERRACE | 2009-11-13 | 2010-03-17 | GPPC, INC. | 1810 | 1669 | 2010-03-31 | 2010-10-28 | 2010-08-24 | 2010-08-24 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | MFH Improvement | JPN | JAPAN | MCAS IWAKUNI JA | 0801 | WholeHouse Restoration, Family Housing Midrise # 1200 | 2010-01-14 | 2010-05-18 | NISHIMATSU CONSTRUCTION CO.,LTD | 10324 | 10125 | 2010-06-01 | 2011-10-11 | 2011-10-13 | 2011-10-13 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 521 | CONSTRUCT EOD FACILITY | 2010-09-03 | 2010-09-30 | RORE, INC. | 1984 | 1882 | 2010-10-14 | 2012-07-23 | 2011-10-15 | 2012-07-23 | 97.9188
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Minor Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 120 | CONSTRUCT ADDITIONAL BERTHING FOR SOCOM | 2010-04-23 | 2010-08-09 | PRIME PROJECTS INTERNATIONAL | 872 | 1589 | 2010-08-23 | 2011-02-01 | 2011-02-01 | 2011-02-01 | 86.0667
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Minor Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 678X | AIR TRAFFIC CONTROL TOWER EXTENSION | 2010-07-14 | 2010-09-27 | F & S MECHANICAL AND PLUMBINGSERVICES, INC. | 2013 | 2213 | 2010-10-11 | 2014-10-01 | 2013-09-30 | 2014-01-14 | 96.3265
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Res | Minor Construction | TX | TEXAS | NAS FORT WORTH JRB TX | 044 | HAZARDOUS MATERIAL STOREHOUSE | 2011-07-27 | 2011-09-26 | AFFILIATED WESTERN, INC | 2019 | 1996 | 2011-10-10 | 2012-10-19 | 2012-07-16 | 2013-07-12 | 99.6927
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Minor Construction | VA | VIRGINIA | NAVAL SUPPORT STATION NRFK NSY | 878 | AUTOMOTIVE ORGANIZATIONAL SHOP | 2010-01-26 | 2010-05-04 | CLARK ENTERPRISES, INC., J.W. | 1574 | 1511 | 2010-05-18 | 2012-01-30 | 2011-05-14 | 2012-03-12 | 100
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Minor Construction | VA | VIRGINIA | NAVAL SUPPORT STATION NRFK NSY | 992 | COMMISSARY UTILITIES | 2010-06-29 | 2010-08-27 | CLARK ENTERPRISES, INC., J.W. | 1117 | 1163 | 2010-09-10 | 2012-10-29 | 2011-05-09 | 2012-10-29 | 93.8621
2014-07-31 | 2014-08-04 | 2010 | Navy-MC Active | Minor Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 235 | RELOCATE SECURITY | 2009-08-19 | 2009-12-17 | TOMPCO-TRITON | 3001 | 2887 | 2009-12-31 | 2010-07-29 | 2010-04-24 | 2010-09-30 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | 47715 | 46237 | 2011-06-23 | 2013-12-05 | 2012-10-08 | 2013-10-15 | 98.7588
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 533 | SIMULATOR FACILITY (JSF) | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | 26438 | 23250 | 2011-06-17 | 2013-04-19 | 2012-06-02 | 2013-04-19 | 98.7793
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 546 | UTILITY UPGRADES (JSF) | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | 40106 | 36761 | 2011-06-21 | 2013-06-14 | 2012-07-08 | 2013-06-14 | 98.6399
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | 19793 | 16188 | 2011-08-10 | 2012-12-14 | 2012-07-25 | 2012-12-14 | 98.8986
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 578 | VAN PAD RELOCATION (JSF) | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | 15045 | 14670 | 2011-09-26 | 2013-01-22 | 2012-09-11 | 2013-03-20 | 99.8488
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | 54843 | 54497 | 2011-06-21 | 2013-06-14 | 2012-07-08 | 2013-06-14 | 82.7444
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 447A | AIRCRAFT MAINTENANCE HANGAR (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | 30492 | 29300 | 2011-06-23 | 2013-12-05 | 2012-10-08 | 2013-10-15 | 98.4701
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | BHR | BAHRAIN | NAVSUPPACT BAHRAIN | 908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY | 2012-04-12 | 2012-08-17 | NAVY STANDARD DOCUMENT | 41151 | 38043 | 2012-08-31 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 45.147 | -15471
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | BHR | BAHRAIN | NAVSUPPACT BAHRAIN | 954 | WATERFRONT DEVELOPMENT, PHASE 3 | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT | 40713 | 36788 | 2012-03-14 | 2014-11-26 | 2014-11-26 | 2014-11-26 | 89.4663 | -19865
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 400 | MARINE CORPS ENERGY INITIATIVE | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | 9928 | 9373 | 2011-06-17 | 2012-06-15 | 2012-06-17 | 2012-07-11 | 98.1464
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Res | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 092 | TANK VEHICLE MAINTENANCE FACILITY | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | 6458 | 6168 | 2011-10-06 | 2013-03-11 | 2012-09-21 | 2013-03-28 | 99.8017
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | 51987 | 51420 | 2011-06-17 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 99.9653
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 109 | CNAT/FRS AVIATION TRAINING AND BEQ | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | 51999 | 45623 | 2011-09-26 | 2014-06-23 | 2014-01-08 | 2014-06-23 | 95.5949 | -11300
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 111 | MALS-39 MAINTENANCE HANGAR EXPANSION | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | 47061 | 33348 | 2011-07-06 | 2013-10-29 | 2013-03-13 | 2013-10-29 | 85.6172
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS MIRAMAR | 152 | PARKING APRON/TAXIWAY EXPANSION | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | 32816 | 35427 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 97.3994 | -28591
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS MIRAMAR | 185 | HANGAR 4 ADDITION | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | 27121 | 27749 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 98.8499 | -4000
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS MIRAMAR | 192 | GTF-HANGAR MODIFICATION (HMT-302) | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | 56417 | 54528 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 98.6244 | -30605
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 310 | SMALL ARMS MAGAZINE, EDSON RANGE | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | 3760 | 3159 | 2011-06-21 | 2014-09-26 | 2012-07-06 | 2014-09-26 | 83.6903
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1014 | TRUCK COMPANY OPERATIONS COMPLEX | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | 52425 | 50518 | 2011-10-06 | 2015-06-03 | 2013-09-21 | 2013-10-06 | 73.0888
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1044 | CONVEYANCE/WATER TREATMENT | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | 98236 | 82611 | 2012-10-13 | 2016-07-15 | 2016-01-13 | 2016-01-13 | 15.8196
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1109 | BACHELOR ENLISTED QUARTERS, LAS FLORES | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | 36173 | 33931 | 2011-10-13 | 2014-06-05 | 2013-10-13 | 2014-05-26 | 98.3601
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1113 | BACHELOR ENLISTED QUARTERS, 24 AREA | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | 41889 | 39138 | 2011-10-13 | 2014-06-05 | 2013-10-13 | 2014-05-26 | 97.3525
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1200 | MARINE CORPS ENERGY INITIATIVE | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | 9779 | 9567 | 2011-08-09 | 2013-06-21 | 2012-08-04 | 2014-01-16 | 99.8959
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1043A | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | 29295 | 25269 | 2010-11-12 | 2015-02-17 | 2012-10-12 | 2015-08-21 | 32.4296
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAF EL CENTRO CA | 260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  | 2011-09-29 | Land Acquisition | 1421 | 1658 | 2011-10-13 |  |  |  | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO SAN DIEGO CA | 750 | ROTARY HANGAR | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | 64063 | 63848 | 2012-02-14 | 2013-12-10 | 2012-04-16 | 2014-03-11 | 99.9184
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE SAN DIEGO | 327 | BERTHING PIER 12 REPL & DREDGING | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | 99132 | 90113 | 2011-10-13 | 2013-10-22 | 2013-10-22 | 2014-03-11 | 88.2501 | -1813
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE SAN DIEGO | 405 | BACHELOR QUARTERS HOMEPORT ASHORE | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | 72294 | 69741 | 2011-10-14 | 2013-12-03 | 2013-10-23 | 2013-12-03 | 99.6897
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 219 | GENERAL WAREHOUSE | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 7716 | 7638 | 2012-04-16 | 2014-10-31 | 2013-12-26 | 2014-02-19 | 67.5807
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 912 | PAVE EXTERNAL ROADS | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 3107 | 2657 | 2012-04-16 | 2014-10-31 | 2013-12-26 | 2014-02-19 | 83.5523
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | ESP | SPAIN | NAVSTA ROTA SP | 897 | AIR TRAFFIC CONTROL TOWER | 2012-01-13 | 2012-06-15 | SACYR SA | 19080 | 15384 | 2012-06-29 | 2015-01-04 | 2014-09-03 | 2015-01-04 | 56.0628
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | MCSF BLOUNT ISLAND | 005 | PAINT AND BLAST FACILITY | 2011-04-29 | 2011-09-16 | SAUER, INC. | 20345 | 19807 | 2011-09-30 | 2014-03-10 | 2013-05-16 | 2014-01-24 | 97.1923
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | MCSF BLOUNT ISLAND | 012 | CONTAINER STAGING AND LOADING LOT | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | 3380 | 2529 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 72.97
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | MCSF BLOUNT ISLAND | 017 | HARDSTAND EXTENSION | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | 12623 | 7904 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 94.0745
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | MCSF BLOUNT ISLAND | 022 | CONSOLIDATED WAREHOUSE FACILITY | 2010-11-22 | 2011-06-03 | SAUER, INC. | 13295 | 11114 | 2011-06-17 | 2013-12-20 | 2012-07-27 | 2013-09-28 | 99.7657
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | MCSF BLOUNT ISLAND | 023 | WASHRACK EXPANSION | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | 8877 | 8449 | 2011-06-15 | 2013-06-10 | 2012-11-19 | 2013-06-30 | 96.2258
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | MCSF BLOUNT ISLAND | 024 | CONTAINER STORAGE LOT | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | 3702 | 3369 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 92.8139
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD | 2012-07-05 | 2012-09-28 | HEAD, INC. | 29901 | 25333 | 2012-10-12 | 2014-09-28 | 2014-09-28 | 2014-10-12 | 58.0245
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | FL | FLORIDA | NAVAL SUPPORT ACTIVITY ORLANDO | 015 | CALIBRATION FACILITY LAND ACQUISITION |  | 2011-12-31 | Land Acquisition | 3149 | 3080 | 2012-01-14 |  |  |  | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | GA | GEORGIA | SUBASE KINGS BAY GA | 601 | SECURITY ENCLAVE AND VEHICLE BARRIER | 2011-12-13 | 2012-03-16 | SAUER, INC. | 37278 | 37684 | 2012-03-30 | 2013-09-07 | 2013-09-07 | 2014-08-15 | 88.5965 | -5445
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | GA | GEORGIA | SUBASE KINGS BAY GA | 620 | WATERFRONT EMERGENCY GENERATORS | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | 15010 | 16576 | 2011-09-02 | 2013-05-13 | 2013-05-13 | 2014-07-28 | 94.061
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 204A | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | 21579 | 16280 | 2012-12-12 | 2014-09-17 | 2014-06-19 | 2014-07-19 | 64.6052
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 005 | JOINT POW/MIA ACCOUNTING, USPACOM | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | 95540 | 83049 | 2011-06-20 | 2014-11-24 | 2013-07-05 | 2014-10-02 | 80.6856
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE | 2011-02-04 | 2011-06-24 | FOPCO, INC | 7856 | 9024 | 2011-07-08 | 2013-06-03 | 2012-08-15 | 2013-04-30 | 98.8772
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 006 | PHYSICAL FITNESS CENTER, CAMP SMITH | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | 28891 | 28102 | 2011-06-30 | 2014-04-03 | 2013-03-07 | 2014-04-04 | 95.6936
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 816 | WATERFRONT OPERATIONS FACILITY | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | 16634 | 15092 | 2011-07-14 | 2014-11-16 | 2013-11-16 | 2014-04-14 | 78.5325
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 858 | BACHELOR ENLISTED QUARTERS | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | 62691 | 60423 | 2011-09-14 | 2014-12-11 | 2014-08-21 | 2014-12-11 | 76.5983 | -17925
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | JPN | JAPAN | NAF ATSUGI JA | 203 | AVIATION SIMULATOR TRAINING FACILITY | 2010-12-09 | 2011-07-29 | Awarded by Other Agency | 6764 | 6442 | 2011-08-12 | 2013-11-13 | 2013-11-13 | 2013-11-13 | 97.1245
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Res | Major Construction | LA | LOUISIANA | HDQTRS 4TH MARDIV NEW ORLEANS | 060 | MARINE CORPS RESERVE CENTER | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | 14630 | 14188 | 2011-10-11 | 2014-04-15 | 2013-02-08 | 2014-03-01 | 98.8025
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Res | Major Construction | LA | LOUISIANA | NAS JRB NEW ORLEANS LA | 477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | 13604 | 14455 | 2011-06-17 | 2014-05-07 | 2013-06-07 | 2014-02-12 | 93.3869
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | MD | MARYLAND | NAVAL AIR STATION PAX RIVER | 263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | 33033 | 34617 | 2011-06-16 | 2013-07-31 | 2012-07-30 | 2014-07-16 | 99.3517
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 136 | BACHELOR ENLISTED QUARTERS | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | 42882 | 42010 | 2011-06-16 | 2014-09-05 | 2013-07-07 | 2014-05-07 | 75.025
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 148 | MISSILE MAGAZINE | 2010-10-21 | 2011-06-02 | SAUER, INC. | 4779 | 4779 | 2011-06-16 | 2014-01-23 | 2012-07-10 | 2013-11-04 | 96.7755
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 164 | MARINER'S BAY LAND ACQUISITION BOGUE |  | 2011-07-01 | Land Acquisition | 4002 | 3706 | 2011-07-15 |  |  |  | 93.1665
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 176 | STATION INFRASTRUCTURE UPGRADES | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | 5850 | 7300 | 2011-06-15 | 2013-10-10 | 2012-11-25 | 2013-10-10 | 99.6306
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | 12906 | 12841 | 2011-06-16 | 2015-01-06 | 2012-12-01 | 2014-01-15 | 97.0168
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 683 | HANGAR | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 62154 | 56577 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 88.5347
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 687 | MV-22 MAINTENANCE HANGAR (HMLA) | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 62617 | 57993 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 79.6219
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1034 | 2ND INTEL BN OPERATIONS COMPLEX | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | 79767 | 80069 | 2011-07-13 | 2014-12-15 | 2014-02-28 | 2014-12-15 | 84.2678
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | 32625 | 30595 | 2011-07-13 | 2014-12-15 | 2014-02-28 | 2014-12-15 | 92.024
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | 6613 | 6000 | 2011-07-11 | 2013-05-13 | 2012-08-20 | 2013-07-31 | 92.2961
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | 43950 | 40082 | 2011-07-13 | 2014-12-31 | 2013-07-13 | 2014-06-30 | 99.827
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | 40236 | 38214 | 2011-09-14 | 2014-09-15 | 2013-10-08 | 2014-06-24 | 100.0499
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | 39788 | 37914 | 2011-09-14 | 2014-09-15 | 2013-10-08 | 2014-06-24 | 99.3272
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1256 | MESS HALL ADDITION, COURTHOUSE BAY | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | 1499 | 1379 | 2011-06-16 | 2012-11-25 | 2012-11-25 | 2012-11-25 | 98.4804
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1264 | UTILITY EXPANSION, HADNOT POINT | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | 55206 | 53553 | 2011-10-10 | 2014-09-16 | 2013-10-22 | 2013-12-26 | 87.309
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1265 | UTILITY EXPANSION, FRENCH CREEK | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | 54795 | 44815 | 2011-10-10 | 2014-09-16 | 2013-10-22 | 2013-12-26 | 89.0516
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1267 | MESS HALL, FRENCH CREEK | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | 24316 | 17442 | 2011-06-16 | 2014-03-07 | 2013-02-06 | 2013-10-25 | 76.2635
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | 54720 | 52787 | 2011-09-13 | 2014-12-01 | 2013-09-07 | 2013-09-12 | 90.2222
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | 43568 | 40884 | 2011-06-16 | 2014-09-30 | 2013-08-30 | 2014-06-02 | 98.5753
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | 46005 | 42146 | 2011-06-16 | 2014-08-18 | 2013-08-13 | 2014-04-14 | 99.4943
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | 49005 | 44297 | 2011-07-13 | 2014-12-31 | 2013-07-13 | 2014-06-30 | 96.5924
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1323 | ARMORY II MEF, WALLACE CREEK | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | 5941 | 5259 | 2011-12-20 | 2014-12-31 | 2013-07-13 | 2014-06-30 | 99.5896 | -4148
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1400 | MARINE CORPS ENERGY INITIATIVE | 2010-10-08 | 2011-05-31 | URS-IAP LLC | 8868 | 8147 | 2011-06-14 | 2012-12-06 | 2012-09-27 | 2012-12-31 | 97.5105
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 068 | ELECTROMAGNETIC SENSOR FACILITY | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | 24394 | 26106 | 2011-08-23 | 2014-03-24 | 2013-08-22 | 2014-09-08 | 95.3261
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 420 | PHYSICAL FITNESS CENTER, BEAUFORT | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | 14780 | 14867 | 2011-09-21 | 2013-05-24 | 2013-06-08 | 2013-07-16 | 99.5436
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 444 | TRAINING AND SIMULATOR FACILITY | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | 40940 | 38698 | 2011-06-20 | 2014-06-09 | 2014-03-11 | 2014-06-09 | 98.4986
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 454 | F-35B AIRCRAFT HANGAR FOR FRS-2 | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | 45398 | 45805 | 2011-06-20 | 2014-06-09 | 2014-03-11 | 2014-06-09 | 99.7897
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 541 | ADDITION, MCU RESEARCH CENTER | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | 31343 | 29285 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2014-08-20 | 75.8012 | -3531
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 | 2011-06-20 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | 45465 | 34314 | 2012-12-14 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 19.2152 | -8039
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | 34087 | 31012 | 2011-10-14 | 2013-09-26 | 2013-08-09 | 2014-04-30 | 99.6424
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 615 | SNCO ACADEMIC FACILITY ADDITION | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | 6836 | 6730 | 2011-07-04 | 2013-07-22 | 2012-12-21 | 2013-05-31 | 95.4945
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL SUPPORT STATION NRFK NSY | 516A | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | 68459 | 65094 | 2011-04-14 | 2015-10-02 | 2014-11-22 | 2015-10-02 | 67.4612
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Res | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | 15431 | 17554 | 2011-06-17 | 2013-10-18 | 2013-04-27 | 2014-10-18 | 98.1312
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | 1395 | 1273 | 2011-06-28 | 2012-11-07 | 2012-06-18 | 2012-11-07 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 862 | PIER 1 UPGRADES TO BERTH USNS COMFORT | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | 3659 | 2951 | 2011-08-09 | 2012-09-18 | 2012-08-09 | 2012-09-28 | 79.1286 | -3000
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 162 | AGILE CHEMICAL FACILITY PHASE 2 | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | 34869 | 34811 | 2012-08-24 | 2015-06-26 | 2014-06-16 | 2015-06-26 | 51.5225
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 843 | CSDS-5 LABORATORY EXPANSION PHASE ! | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | 16042 | 16447 | 2011-06-17 | 2013-09-24 | 2012-10-15 | 2014-04-04 | 87.5393
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | 14315 | 14811 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-05-15 | 99.6403
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 987 | EMERGENCY GENERATOR, LIMITED AREA | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | 11275 | 10418 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-05-15 | 96.9771
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 973F | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | 20026 | 19310 | 2010-11-24 | 2012-06-01 | 2011-11-08 | 2012-10-29 | 90.5202
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | MFH Improvement | DC | DISTRICT OF COLUMBIA | MARBKS WASHINGTON DC | 1101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | 41 | 39 | 2011-01-28 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | MFH Improvement | JPN | JAPAN | COMFLEACT YOKOSUKA JA | 1101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | 17378 | 16915 | 2011-07-15 | 2013-01-17 | 2012-12-03 | 2013-01-20 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | MFH Improvement | JPN | JAPAN | MCAS IWAKUNI JA | 0501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | 11626 | 11102 | 2011-10-06 | 2013-02-28 | 2013-01-14 | 2013-02-28 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | MFH Improvement | JPN | JAPAN | NMC EAST ASIA DIV DET SASEBO | 1102 | WHOLEHOUSE IMPROVEMENT | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | 8127 | 6990 | 2011-07-10 | 2013-01-18 | 2012-10-17 | 2013-02-14 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAS LEMOORE CA | 331 | WATER WELL | 2011-01-11 | 2011-09-30 | EPC CORPORATION | 2713 | 2887 | 2011-10-14 | 2013-11-22 | 2012-10-01 | 2013-05-21 | 99.6224
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | 1559 | 1446 | 2011-10-03 | 2013-03-01 | 2012-12-24 | 2013-03-01 | 99.6635
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | JPN | JAPAN | COMFLEACT YOKOSUKA JA | 012 | CONSTRUCT NACCC ADDITION | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | 1380 | 1256 | 2011-06-24 | 2012-04-20 | 2012-04-13 | 2012-04-20 | 95.5869
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | NJ | NEW JERSEY | NAVAL WEAPONS STATION EARLE NJ | 206 | CONSTRUCT DISPATCH CENTER | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | 1630 | 1633 | 2011-12-01 | 2013-03-26 | 2013-01-25 | 2013-03-29 | 98.4919
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | 1951 | 1838 | 2012-03-16 | 2012-08-28 | 2012-09-13 | 2012-09-13 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY | 2011-05-26 | 2011-08-03 | JESSICO, INC | 2085 | 1989 | 2011-08-17 | 2012-11-13 | 2012-09-30 | 2012-11-13 | 98.442
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | 1725 | 1616 | 2011-11-18 | 2013-05-08 | 2012-07-21 | 2013-05-31 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | 928 | 950 | 2011-07-04 | 2012-04-16 | 2012-01-26 | 2012-04-30 | 100
2014-07-31 | 2014-08-04 | 2011 | Navy-MC Active | Minor Construction | VA | VIRGINIA | NAVSUPPACT HAMPTON ROADS VA | 101 | ROAD IMPROVEMENTS CAMP ALLEN AREA | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | 1381 | 1326 | 2011-02-28 | 2012-01-27 | 2011-09-21 | 2012-01-27 | 100
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 535 | AIRCRAFT MAINTENANCE HANGAR (JSF) | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | 32048 | 31596 | 2012-09-20 | 2014-08-06 | 2014-07-07 | 2014-08-06 | 94.1997 | -5983
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | 79917 | 77481 | 2012-04-03 | 2014-06-24 | 2014-05-20 | 2014-09-11 | 94.6496
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 575 | AUXILIARY LANDING FIELD (JSF) | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | 29475 | 28474 | 2012-07-09 | 2014-02-21 | 2013-06-25 | 2014-01-31 | 92.2235 | -5128
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 177 | MULTI-USE OPERATIONAL FITNESS AREA | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | 18819 | 20038 | 2012-08-27 | 2014-09-02 | 2014-09-02 | 2016-02-15 | 16.6693
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 212 | CHILD DEVELOPMENT CENTER | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | 21313 | 20401 | 2012-06-19 | 2015-05-19 | 2013-12-12 | 2015-05-19 | 20.3184
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAGCC TWENTYNINE PALMS CA | 541 | MULTI-PURPOSE BUILDING ADDITION | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | 15610 | 13361 | 2012-10-11 | 2014-04-20 | 2014-04-20 | 2014-07-27 | 23.7501
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 114 | MV-22 DOUBLE HANGAR REPLACEMENT | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | 40539 | 38294 | 2012-08-03 | 2015-12-14 | 2015-08-10 | 2015-08-10 | 27.3079 | -6761
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 116 | MV-22 AVIATION PAVEMENT | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | 14938 | 9608 | 2012-07-26 | 2014-11-11 | 2014-01-03 | 2014-02-27 | 69.5977 | -856
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 117 | MV-22 AVIATION FUEL STORAGE | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | 7437 | 7179 | 2013-11-21 |  |  |  | 17.3078
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 532 | ARMORY, 1ST MARINE DIVISION | 2012-04-23 | 2012-08-31 | A&D GC INC | 11201 | 10425 | 2012-09-14 | 2014-04-23 | 2013-12-24 | 2014-03-01 | 99.1935
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | 11746 | 9496 | 2012-04-06 | 2013-08-05 | 2013-01-21 | 2013-08-05 | 87.5158 | -760
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1040 | INTERSECTION BRIDGE AND IMPROVEMENTS | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | 11432 | 13973 | 2012-09-07 | 2014-05-23 | 2013-09-27 | 2014-06-24 | 92.4299
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCB CAMP PENDLETON CA | 1045 | NEW POTABLE WATER CONVEYANCE | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | 85242 | 62019 | 2012-10-12 | 2016-09-06 | 2016-03-31 | 2016-03-31 | 14.1004 | -16682
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCLB BARSTOW CA | 925 | DIP TANK CLEANING FACILITY | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | 7970 | 7877 | 2012-04-04 | 2013-09-27 | 2013-09-27 | 2014-04-09 | 86.7853
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO SAN DIEGO CA | 705 | FITNESS CENTER, NORTH ISLAND | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | 46630 | 42556 | 2012-08-21 | 2015-03-16 | 2015-03-16 | 2015-07-27 | 47.3373
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO SAN DIEGO CA | 880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | 56977 | 55615 | 2012-07-17 | 2015-03-30 | 2015-03-30 | 2015-07-09 | 49.3884
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE VENTURA CTY PT MUGU CA | 559 | E-2D AIRCREW TRAINING FACILITY | 2012-03-21 | 2012-06-29 | ALLEN ENGINEERING CONTRACTOR, INC | 13210 | 15563 | 2012-07-13 | 2014-11-30 | 2013-10-07 | 2013-10-07 | 76.9822
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 110 | REPLACE CONDEMNED COATINGS LABORATORY | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | 3805 | 3998 | 2012-09-11 | 2014-04-24 | 2013-08-28 | 2014-05-30 | 99.4892
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | DGA | DIEGO GARCIA | NAVSUPPFAC DIEGO GARCIA | 184 | POTABLE WATER PLANT MODERNIZATION | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | 30101 | 28077 | 2013-01-04 | 2015-08-26 | 2015-07-30 | 2015-08-26 | 47.5131
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 153 | BAMS UAS OPERATOR TRAINING FACILITY | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | 2851 | 2936 | 2012-07-09 | 2014-03-24 | 2013-12-17 | 2014-04-09 | 95.9371
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 624 | P-8A TRAINING FACILITY | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | 14194 | 13885 | 2012-07-09 | 2014-03-24 | 2013-12-17 | 2014-04-09 | 95.8273 | -10000
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE | 2012-02-17 | 2012-06-07 | Awarded by Other Agency | 18810 | 20306 | 2012-06-21 | 2014-09-01 | 2014-09-01 | 2014-09-01 | 61.6893
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | 7518 | 9431 | 2012-08-29 | 2014-02-21 | 2014-02-21 | 2015-01-23 | 18.365
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | GA | GEORGIA | SUBASE KINGS BAY GA | 636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | 53167 | 36608 | 2014-05-01 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 0.58967
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | HI | HAWAII | CNI PMRF HAWREA BARKING SANDS | 400 | NORTH LOOP ELECTRICAL REPLACEMENT | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | 6498 | 5879 | 2012-03-29 | 2013-12-24 | 2014-01-02 | 2014-01-02 | 88.0006
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | 7708 | 7616 | 2012-04-19 | 2014-06-09 | 2013-11-16 | 2014-06-09 | 97.6373
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 822 | MCAS OPERATIONS COMPLEX | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | 52970 | 51186 | 2012-05-02 | 2014-10-20 | 2014-03-17 | 2014-10-20 | 84.573
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | IL | ILLINOIS | GREAT LAKES NAVAL STATION | 816 | DECENTRALIZE STEAM SYSTEM | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | 89491 | 62473 | 2012-06-27 | 2015-11-06 | 2015-11-06 | 2015-11-06 | 47.4586
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Res | Major Construction | LA | LOUISIANA | HDQTRS 4TH MARDIV NEW ORLEANS | 030 | RESERVE CENTER TRAINING CENTER - MEMPHIS | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | 9006 | 8443 | 2013-04-19 | 2014-12-24 | 2014-10-11 | 2014-10-11 | 43.2214
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | MD | MARYLAND | NAVAL AIR STATION PAX RIVER | 561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | 49890 | 46719 | 2014-07-14 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 0
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | 14067 | 17019 | 2012-03-29 | 2014-04-29 | 2013-08-14 | 2014-07-29 | 95.4051
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 030 | SQUAD BATTLE COURSE | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | 16292 | 14329 | 2012-07-05 | 2014-12-01 | 2014-05-17 | 2014-08-03 | 80.7747
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | 26101 | 26005 | 2012-07-13 | 2014-10-01 | 2014-07-29 | 2014-08-30 | 80.4502
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 705 | AIRCRAFT MAINTENANCE HANGAR AND APRON | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | 57582 | 63635 | 2012-06-12 | 2015-02-15 | 2014-07-07 | 2015-02-19 | 86.194
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 710 | ORDNANCE LOADING AREA ADDITION | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | 7768 | 7328 | 2012-06-12 | 2015-02-15 | 2014-07-07 | 2015-02-19 | 75.6141
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | 74707 | 72598 | 2012-05-14 | 2015-02-19 | 2014-07-24 | 2015-02-19 | 73.5846
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1383 | BASE ENTRY POINT AND ROAD | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | 64235 | 55443 | 2012-04-17 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 62.6523
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Res | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 860 | ARMED FORCES RESERVE CENTER, PITTSBURGH | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | 12033 | 12289 | 2012-08-14 | 2014-05-31 | 2014-02-06 | 2014-05-31 | 99.0623
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 442 | VERTICAL LANDING PADS FOR F-35B | 2011-12-06 | 2012-03-30 | HEAD, INC. | 18987 | 17996 | 2012-04-13 | 2013-10-21 | 2013-08-07 | 2013-09-27 | 93.9405
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 499 | POWER DISTRIBUTION UPGRADES | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | 29520 | 27975 | 2012-10-08 | 2014-10-09 | 2014-10-09 | 2014-11-23 | 70.7131
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | 11118 | 11202 | 2012-09-25 | 2014-10-10 | 2014-03-28 | 2014-10-10 | 98.1595
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | 27222 | 23702 | 2012-12-14 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 23.3434
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | 6555 | 6960 | 2012-08-10 | 2014-09-26 | 2013-09-05 | 2014-09-26 | 64.6578
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 611 | BACHELOR ENLISTED QUARTERS | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | 32910 | 31613 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-01-27 | 49.8079
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 612 | ENLISTED DINING FACILITY | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | 5028 | 4964 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-01-27 | 74.8961
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 621 | EMBASSY SECURITY GROUP FACILITIES | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | 26081 | 25107 | 2013-03-14 | 2015-08-15 | 2015-03-15 | 2015-03-15 | 23.2425
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 632 | ACADEMIC INSTRUCTION FACILITY | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | 60736 | 59990 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2014-08-20 | 72.3268 | -2502
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | 18599 | 17840 | 2012-10-11 | 2015-04-01 | 2014-10-12 | 2014-10-31 | 46.3599
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL SUPPORT STATION NRFK NSY | 383 | CONTROLLED INDUSTRIAL FACILITY | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | 60576 | 31447 | 2012-06-14 | 2015-06-05 | 2014-09-28 | 2015-03-23 | 23.8179 | -7621
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 123 | BACHELOR QUARTERS, HOMEPORT ASHORE | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | 74854 | 72168 | 2012-09-14 | 2015-04-30 | 2014-09-13 | 2015-02-17 | 69.3528 | -3084
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSUPPACT HAMPTON ROADS VA | 197 | DECENTRALIZE STEAM SYSTEM | 2012-04-17 | 2012-09-20 | SAUER, INC. | 27161 | 26377 | 2012-10-04 | 2015-03-09 | 2015-05-08 | 2015-05-08 | 77.0757
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 222 | DECENTRALIZE STEAM SYSTEM | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | 69984 | 67347 | 2012-10-12 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 58.1016
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | 13341 | 10554 | 2012-06-08 | 2013-06-27 | 2013-12-24 | 2014-11-10 | 88.1989
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 913 | EHW SECURITY FORCE FACILITY | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | 13485 | 13639 | 2012-02-14 | 2014-06-11 | 2013-08-08 | 2014-02-16 | 72.3358 | -7933
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 985 | WRA VEHICLE BARRIERS | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | 9338 | 8570 | 2012-02-24 | 2013-12-11 | 2013-12-10 | 2014-06-30 | 85.119 | -7587
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | 81714 | 77594 | 2012-05-23 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 91.0469
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | MFH Improvement | JPN | JAPAN | COMFLEACT YOKOSUKA JA | 1201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | 19730 | 18773 | 2012-08-01 | 2014-01-13 | 2014-01-13 | 2014-01-13 | 94.5531
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | MFH Improvement | JPN | JAPAN | COMFLEACT YOKOSUKA JA | 1202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | 9033 | 9094 | 2012-08-22 | 2015-01-11 | 2014-10-07 | 2015-01-11 | 18.3848
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | MFH Improvement | JPN | JAPAN | MCAS IWAKUNI JA | 0601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | 13357 | 12685 | 2012-08-13 | 2013-12-13 | 2013-11-23 | 2013-12-14 | 100
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | MFH Improvement | JPN | JAPAN | MCAS IWAKUNI JA | 1001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | 11335 | 10876 | 2012-08-14 | 2015-02-02 | 2014-12-20 | 2015-02-02 | 37.6796
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | MFH Improvement | JPN | JAPAN | NAF ATSUGI JA | 1201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | 5990 | 5654 | 2012-10-10 | 2013-11-22 | 2013-08-26 | 2013-11-22 | 99.9686
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | MFH Improvement | JPN | JAPAN | NAF ATSUGI JA | 1202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | 17540 | 14942 | 2012-08-29 | 2014-07-01 | 2013-12-09 | 2014-07-01 | 94.4301
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | MFH Improvement | LA | LOUISIANA | MARCORRESFOR NEW ORLEANS LA | 1201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  | 2012-01-04 | Awarded by Other Agency | 0 | 45 | 2012-01-18 |  |  |  | 100
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAS LEMOORE CA | 363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | 1980 | 1878 | 2012-09-12 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 100
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAS LEMOORE CA | 364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | 2000 | 1858 | 2012-10-12 | 2014-03-05 | 2013-09-26 | 2014-03-05 | 98.7166
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE CORONADO SAN DIEGO CA | 896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | 1816 | 1714 | 2013-02-21 | 2014-01-31 | 2014-01-31 | 2014-04-02 | 75.7331
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 | 2012-06-20 | 2012-09-28 | NOVA R M F | 1939 | 1875 | 2012-10-12 | 2014-06-23 | 2013-09-27 | 2014-07-01 | 100
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAVSUPPACT MONTEREY CA | 851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | 1916 | 1807 | 2014-01-02 | 2014-10-17 | 2014-10-17 | 2014-10-17 | 5.9327
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | ESP | SPAIN | NAVSTA ROTA SP | 708 | CONSTRUCT LCAC BEACH ACCESS RAMP | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | 1751 | 1411 | 2013-10-13 | 2014-06-20 | 2014-05-28 | 2014-06-20 | 94.1109
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | FL | FLORIDA | NAS PENSACOLA FL | 791 | HVAC JOINT AVIATION SURVIVAL TRAINING | 2012-07-25 | 2012-09-29 | R L BURNS INC. | 2038 | 1975 | 2012-10-13 | 2013-12-19 | 2013-08-08 | 2013-08-08 | 100
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Res | Minor Construction | LA | LOUISIANA | NAS JRB NEW ORLEANS LA | 501 | MILITARY WORKING DOG FACILITY | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | 1286 | 1223 | 2013-08-29 | 2014-05-22 | 2014-05-22 | 2014-06-20 | 96.7439
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1425 | OVERHEAD RANGE BAFFLE SYSTEM | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | 2297 | 2173 | 2013-03-06 | 2014-08-31 | 2014-04-17 | 2014-04-17 | 97.9345
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | TX | TEXAS | NAS KINGSVILLE TX | 294 | CONNECT TO KINGSVILLE WATER SYSTEM | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | 1658 | 1549 | 2012-10-08 | 2014-03-21 | 2014-03-21 | 2014-08-25 | 72.7844
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 199 | MSRON FOUR BOAT STORAGE BUILDING | 2012-10-31 | 2012-12-14 | JESSICO, INC | 970 | 938 | 2012-12-28 | 2013-11-15 | 2013-11-08 | 2013-11-15 | 99.9492
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Res | Minor Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 543 | NAVELSG RESERVE FORCES MARSHALLING YARDS | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | 738 | 747 | 2013-01-30 | 2013-10-23 | 2014-01-21 | 2014-01-21 | 95.2271
2014-07-31 | 2014-08-04 | 2012 | Navy-MC Active | Minor Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 839 | RENOVATE LOWER BASE FIRE STATION | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | 1389 | 1327 | 2012-09-14 | 2013-11-13 | 2013-08-31 | 2013-11-22 | 98.9365
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 378 | SECURITY OPERATIONS COMPLEX | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | 14316 | 13460 | 2013-11-14 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 4.8386
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | AZ | ARIZONA | MCAS YUMA AZ | 566 | COMBAT AIRCRAFT LOADING APRON | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | 12671 | 11787 | 2013-10-11 | 2014-09-22 | 2014-09-22 | 2014-09-22 | 21.7974
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 313 | ENTRY CONTROL POINT (GATE 5) | 2013-03-15 | 2013-12-20 | A&D GC INC | 10974 | 10282 | 2014-01-03 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 1.4864
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS CAMP PENDLETON CA | 113 | MV-22 AVIATION SIMULATOR BUILDING | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | 4380 | 4028 | 2013-06-27 | 2014-09-21 | 2014-09-21 | 2014-09-21 | 78.3238
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | CA | CALIFORNIA | MCAS MIRAMAR | 181 | HANGAR 5 RENOVATIONS & ADDITION | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | 13634 | 12778 | 2013-09-27 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 7.2546
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO SAN DIEGO CA | 909 | H-60S SIMULATOR TRAINING FACILITY | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | 3088 | 2822 | 2014-03-14 | 2015-03-15 | 2015-03-15 | 2015-03-15 | 2.3313
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE SAN DIEGO | 500 | LCS TRAINING FACILITY | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | 45553 | 40224 | 2013-10-14 | 2015-10-24 | 2015-10-24 | 2016-01-09 | 7.1852
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE VENTURA CTY PT MUGU CA | 900 | BAMS MAINTENANCE TRAINING FACILITY | 2013-05-28 | 2013-08-27 | A&D GC INC | 10301 | 8736 | 2013-09-10 | 2014-11-21 | 2014-11-21 | 2015-05-01 | 8.0316
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVWPNSTA SEAL BEACH | 229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | 29447 | 27514 | 2013-10-14 | 2016-04-17 | 2016-04-17 | 2016-06-16 | 11.5923
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | ESP | SPAIN | NAVSTA ROTA SP | 709 | GENERAL PURPOSE WAREHOUSE | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | 2446 | 1906 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 21.6697
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | ESP | SPAIN | NAVSTA ROTA SP | 710 | HIGH EXPLOSIVE MAGAZINE | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | 5849 | 5081 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 22.3882
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 655 | BAMS MISSION CONTROL COMPLEX | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | 18180 | 17487 | 2013-08-28 | 2014-12-27 | 2014-12-27 | 2014-12-27 | 20.7542
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | GRC | GREECE | NAVSUPPACT SOUDA BAY GR | 907 | AIRCRAFT PARKING APRON EXPANSION | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPAQOLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | 14663 | 11219 | 2014-07-25 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | GU | GUAM | US NAVSUPACT ANDERSEN GUAM | 101A | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | 24305 | 19104 | 2013-08-21 | 2015-12-15 | 2015-07-12 | 2015-12-15 | 22.372
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 904 | MV-22 HANGAR AND INFRASTRUCTURE | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | 63056 | 55524 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 14.6245
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 905 | AIRCRAFT STAGING AREA | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | 11118 | 6999 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 25.3067
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | JPN | JAPAN | COMFLEACT OKINAWA JA | 353 | BACHELOR QUARTERS | 2013-01-24 | 2013-09-27 | Awarded by Other Agency | 5627 | 5521 | 2013-10-11 | 2014-12-05 | 2014-12-05 | 2014-12-05 | 8.801
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | JPN | JAPAN | MCAS IWAKUNI JA | 995 | MAINTENANCE HANGAR IMPROVEMENTS | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT | 4947 | 4926 | 2014-06-06 | 2015-06-14 | 2015-06-14 | 2015-06-14 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | JPN | JAPAN | MCAS IWAKUNI JA | 996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH | 2014-04-07 | 2014-07-25 | Awarded by Other Agency | 6304 | 6304 | 2014-08-08 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Res | Major Construction | LA | LOUISIANA | HDQTRS 4TH MARDIV NEW ORLEANS | 130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | 4911 | 4752 | 2013-09-19 | 2015-04-27 | 2014-12-04 | 2014-12-04 | 14.3799
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | MS | MISSISSIPPI | NAS MERIDIAN MS | 317 | DINING FACILITY | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | 9851 | 9246 | 2013-12-31 | 2015-10-09 | 2015-10-09 | 2015-10-09 | 9.3861
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 163 | MARINE AIR SUPPORT SQUADRON COMPOUND | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | 29091 | 27445 | 2013-09-19 | 2016-02-24 | 2016-01-18 | 2016-02-24 | 9.3806
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCAS CHERRY POINT NC | 601 | ARMORY | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | 11782 | 11245 | 2013-09-19 | 2015-04-20 | 2015-04-08 | 2015-04-20 | 36.1438
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 003 | STAFF NCO ACADEMY FACILITIES | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | 29260 | 27742 | 2013-09-19 | 2015-11-08 | 2015-09-01 | 2015-11-08 | 21.0349
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 711 | PERSONNEL ADMINISTRATION CENTER | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | 6449 | 5257 | 2013-09-20 | 2015-07-06 | 2015-07-06 | 2015-07-06 | 31.8185
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 1384 | BASE ACCESS AND ROAD, PHASE 3 | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | 28666 | 24294 | 2012-04-17 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 32.4213
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | NJ | NEW JERSEY | NAVAL WEAPONS STATION EARLE NJ | 237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | 34005 | 33094 | 2013-09-17 | 2014-11-27 | 2014-11-27 | 2015-01-24 | 48.2279
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | ROU | ROMANIA | NAVSUPPFAC BUCHAREST ROMANIA | 400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | 40018 | 36205 | 2014-05-14 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 427 | GROUND SUPPORT EQUIPMENT SHOP | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | 10936 | 10664 | 2013-08-22 | 2014-10-09 | 2014-08-07 | 2014-09-21 | 42.2638
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 456 | SIMULATED LHD FLIGHT DECK | 2012-08-27 | 2013-06-26 | HEAD, INC. | 12302 | 11922 | 2013-07-10 | 2014-10-05 | 2014-07-11 | 2014-10-05 | 69.0929
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCAS BEAUFORT SC | 472 | AIRFIELD SECURITY UPGRADES | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | 11043 | 12254 | 2013-07-15 | 2014-09-12 | 2014-03-28 | 2014-09-12 | 79.5643
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | SC | SOUTH CAROLINA | MCRD/BEAUFORT PI SC | 382 | FRONT GATE AT/FP IMPROVMENTS | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | 11513 | 10135 | 2013-10-30 | 2015-10-11 | 2015-04-12 | 2015-05-28 | 2.8489
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Res | Major Construction | TX | TEXAS | NAS FORT WORTH JRB TX | 047 | COMMERCIAL VEHICLE INSPECTION SITE | 2013-01-22 | 2013-09-12 | KOMADA, LLC | 6894 | 6548 | 2013-09-26 | 2014-12-17 | 2014-11-06 | 2014-12-17 | 14.2709
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | 30462 | 28674 | 2013-10-07 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 4.6465
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 644 | WEAPONS TRAINING BATALLION MESS HALL | 2013-02-22 | 2013-09-04 | C.E.R. INC. | 13168 | 12590 | 2013-09-18 | 2015-04-22 | 2015-04-22 | 2015-04-22 | 16.1837
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 513 | A SCHOOL BARRACKS | 2012-08-20 | 2013-10-31 | SAUER, INC. | 31430 | 29137 | 2013-11-14 | 2015-12-30 | 2015-12-16 | 2015-12-30 | 11.6297
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 582 | UNDERSEA SURVEILLANCE SCIF FACILITY | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | 4129 | 4793 | 2012-12-03 | 2014-06-25 | 2013-11-29 | 2014-06-27 | 96.4604
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL SUPPORT STATION NRFK NSY | 998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | 28374 | 26237 | 2013-12-11 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2.4026
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 984 | REGIMENTAL HEADQUARTERS | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | 11028 | 10609 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 16.8246
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 985 | BACHELOR ENLISTED QUARTERS | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | 18418 | 17536 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 14.5249
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 986 | MOTOR TRANSPORTATION FACILITY | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | 5841 | 5597 | 2013-09-13 | 2014-04-19 | 2015-03-23 | 2015-04-19 | 31.5521
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 987 | SUPPLY WAREHOUSE FACILITY | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | 6987 | 6581 | 2013-09-13 | 2014-04-19 | 2015-03-23 | 2015-04-19 | 31.0188
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 989 | ARMORY | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | 3653 | 3407 | 2013-09-13 | 2014-04-19 | 2015-03-23 | 2015-04-19 | 50.7968
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | 14130 | 13400 | 2013-09-02 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 32.9324
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 372 | PHYSICAL FITNESS CENTER | 2012-12-12 | 2013-09-27 | C.E.R. INC. | 11409 | 10672 | 2013-10-11 | 2015-05-02 | 2015-05-02 | 2015-05-02 | 11.4587
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 245 | EA-18G FLIGHT SIMULATOR FACILITY | 2012-08-16 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | 5679 | 5911 | 2013-06-27 | 2014-12-25 | 2014-11-25 | 2015-01-27 | 73.2462
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 990A | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | 280041 | 226885 | 2012-11-15 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 53.1512
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | MFH Improvement | GU | GUAM | NAVBASE GUAM | 1301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | 26805 | 25136 | 2013-09-26 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 14.8374
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | MFH Improvement | JPN | JAPAN | COMFLEACT YOKOSUKA JA | 1305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | 7791 | 7305 | 2014-07-29 | 2016-02-21 | 2016-02-21 | 2016-02-21 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | MFH Improvement | JPN | JAPAN | MCAS IWAKUNI JA | 0901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | 17551 | 16715 | 2014-06-22 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | MFH Improvement | JPN | JAPAN | NAF ATSUGI JA | 1302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | 12958 | 12065 | 2013-12-15 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Minor Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 003 | EOD/TEU RANGE SUPPORT FACILITY | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | 1896 | 1764 | 2014-06-27 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Minor Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 056 | VPT TEST FACILITY | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | 2332 | 2323 | 2013-03-28 | 2013-11-21 | 2013-10-31 | 2013-12-13 | 99.0052
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Minor Construction | SGP | SINGAPORE | SINGAPORE AREA COORDINATOR | 123 | TEMPORARY LCS SUSTAINMENT FACILITY | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | 755 | 768 | 2012-12-20 | 2014-01-15 | 2013-03-10 | 2013-03-10 | 93.0919
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Minor Construction | TX | TEXAS | NAS KINGSVILLE TX | 288 | WASTEWATER SYSTEM | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | 1790 | 1639 | 2014-04-11 | 2015-03-27 | 2015-03-27 | 2015-03-27 | 1.629
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | 1925 | 1900 | 2013-03-14 | 2013-09-12 | 2013-08-30 | 2013-09-29 | 98.7445
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Minor Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY | 2013-07-26 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | 1120 | 1063 | 2013-10-14 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 38.721
2014-07-31 | 2014-08-04 | 2013 | Navy-MC Active | Minor Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 857 | FLOATING LABORATORY, MOORING DOLPHINS | 2013-01-16 | 2013-05-17 | NOVA GROUP INC | 3406 | 3112 | 2013-05-31 |  |  |  | 97.8413
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | CA | CALIFORNIA | NAVBASE VENTURA CTY PT MUGU CA | 281 | AIRCRAFT ENGINE TEST PADS | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | 6106 | 5710 | 2014-06-26 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 0.66599
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 1400 | NAVSEA HQ RESTORATION | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | 48905 | 47015 | 2014-02-14 |  |  |  | 11.8316
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 227 | ARMORY | 2014-03-17 | 2014-07-25 | JV SKE DJIBOUTI MACC | 4492 | 4178 | 2014-08-08 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 425 | LCS LOGISTICS SUPPORT FACILITY | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | 15842 | 14829 | 2014-06-13 | 2015-11-26 | 2015-11-26 | 2015-11-26 | 0.03423
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GA | GEORGIA | MCLB ALBANY GA | 954 | CERS DISPATCH FACILITY | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | 1248 | 1156 | 2014-06-16 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 425 | MODULAR STORAGE MAGAZINE | 2013-12-30 | 2014-05-14 | GUAM MACC BUILDERS A JV | 54865 | 45031 | 2014-05-28 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 0.010138
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 518 | X-RAY WHARF IMPROVEMENTS | 2014-01-10 | 2014-06-03 | GUAM MACC BUILDERS A JV | 53085 | 42552 | 2014-06-17 |  |  |  | 0.0032198
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 566 | EMERGENT REPAIR FACILITY EXPANSION | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | 35860 | 27539 | 2014-04-24 | 2016-05-12 | 2016-05-12 | 2016-05-12 | 0.81784
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | 17170 | 14300 | 2014-04-03 |  |  |  | 3.2363
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GU | GUAM | NAVBASE GUAM | 638 | SIERRA WHARF IMPROVEMENTS | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | 1462 | 1209 | 2014-06-13 | 2015-03-26 | 2015-03-26 | 2015-03-26 | 0.010338
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GU | GUAM | US NAVSUPACT ANDERSEN GUAM | 109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | 62820 | 57101 | 2014-05-21 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 1.089
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | GU | GUAM | US NAVSUPACT ANDERSEN GUAM | 625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | 57710 | 48457 | 2014-04-10 |  |  |  | 0.88029
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 270 | DRYDOCK WATERFRONT FACILITY | 2013-12-05 | 2014-03-17 | WATTS-HEALY TIBBITTS A JV | 22355 | 19953 | 2014-03-31 | 2015-12-11 | 2015-12-11 | 2015-12-11 | 0.77333
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY &IMF) | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | 33970 | 28265 | 2014-07-14 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | HI | HAWAII | MCB HAWAII KANEOHE | 864 | AIRCRAFT MAINTENANCE EXPANSION | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | 16968 | 15072 | 2014-04-30 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 3.1783
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | JPN | JAPAN | MCB CAMP S D BUTLER OKINAWA JA | 201 | AIRFIELD SECURITY UPGRADES | 2013-11-08 | 2014-04-18 | Awarded by Other Agency | 2881 | 2861 | 2014-05-02 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 0.012653
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 676 | CH-53K MAINTENANCE TRAINING FACILITY | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | 14312 | 12948 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 1.0466
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | NC | NORTH CAROLINA | MCB CAMP LEJEUNE NC | 726 | REGIONAL COMMUNICATION STATION | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | 20159 | 10013 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 0.50446
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 500 | PIER 11 POWER UPGRADES FOR CVN-78 | 2014-03-28 | 2014-06-30 | SYNCON, LLC | 1365 | 1100 | 2014-07-14 | 2019-06-29 | 2019-06-29 | 2019-06-29 | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 251 | P-8A HANGAR AND TRAINING FACILITIES | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | 84889 | 54533 | 2014-08-04 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | 12179 | 10302 | 2014-08-01 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP | 990B | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | 2011-12-13 | 2013-12-04 | EHW CONSTRUCTORS, A JOINT VENTURE | 24880 | 13750 | 2013-12-18 |  |  |  | 0.03572
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Minor Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 917 | CRITICAL POWER FOR BULDING 200 |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | 1120 | 1120 | 2014-06-05 |  |  |  | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Minor Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 918 | CRITICAL POWER FOR BUILDING T-130 |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | 1175 | 1175 | 2014-06-05 |  |  |  | 0
2014-07-31 | 2014-08-04 | 2014 | Navy-MC Active | Minor Construction | DJI | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 919 | CRITICAL POWER FOR BLDGS 111, 113 AND 115 |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | 1064 | 1064 | 2014-06-05 |  |  |  | 0
2014-07-31 | 2014-08-04 | 2006 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR064009 | Improve Family Housing, Ph C | 2007-08-01 | 2007-12-06 | Bilfinger Berger | 1802 | 1893 | 2007-12-06 | 2013-04-15 | 2008-07-15 | 2013-02-22 | 99 | -389
2014-07-31 | 2014-08-04 | 2006 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR064009 | Improve Family Housing, Ph C | 2007-08-01 | 2007-12-06 | OBG | 1118 | 1172 | 2007-12-06 | 2013-04-15 | 2008-07-15 | 2013-02-22 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ053002 | Command Post Facility | 2008-07-03 | 2008-09-30 | J2 Engineering, Inc. | 4333 | 4451 | 2008-11-12 | 2011-09-12 | 2010-05-06 | 2011-07-29 | 99 | -41
2014-07-31 | 2014-08-04 | 2008 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALDA053001B | Multi-Aircraft Maintenance Hanger | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | 15238 | 16848 | 2010-08-23 | 2015-01-31 | 2009-10-30 | 2015-01-15 | 98 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA073008A | Facility Replacements | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | 26245 | 28683 | 2010-08-23 | 2015-01-31 | 2010-06-30 | 2015-01-15 | 98 | 782
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR084014 | Improve Family Housing, Ph E | 2012-11-02 | 2013-05-17 | MICKAN | 4639 | 5012 | 2013-07-08 | 2014-12-10 | 2009-06-15 | 2014-09-26 | 79 | 1025
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2009-10-29 | Nishimatsu Construction Corporation | 140248 | 146740 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 27579
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2010-03-24 | Title II Contract through AFCEE/EX | 3452 | 3452 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2010-07-23 | PASCO Corporation (Meguro-KU) *Arch Test Digs* | 30 | 30 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2010-09-25 | FY10 US Civilian (GS-) Pay for 18CONS per AFCEE/CMP | 74 | 74 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2011-02-03 | GEITA contract through AFCEE/EX | 200 | 200 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2011-09-27 | FY11 US Civilian (GS-) Pay for 18CONS per AFCEE/CMP | 37 | 37 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-03-16 | A&AS contract through AFCEE/EX | 76 | 76 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-05-11 | Title II Contract extension for LXEZ074215 | 500 | 500 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-06-22 | Okinawa Elevator Maintenance Union (Naha) *CCT4506 leak rpr* | 43 | 43 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-08-28 | FY13 US Civilian (GS-) Pay for 18CONS per AFCEE/CMP | 4 | 4 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 696 | 696 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2012-11-19 | FY12 US Civilian (GS-) Pay for 18CONS per AFCEE/CMP | 66 | 66 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ084216 | Improve Family Housing, Ph 8 | 2009-06-23 | 2013-03-26 | A&AS contract through AFCEE/EX | 89 | 89 | 2010-02-04 | 2014-08-15 | 2010-12-30 | 2014-08-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | JPN | JAPAN | MISAWA AIR BASE | QKKA084025 | Improve Family Housing, Ph. 3 | 2008-11-21 | 2009-03-31 | Nishimatsu Construction Co. Lt | 35226 | 37550 | 2011-08-31 | 2013-11-19 | 2010-09-01 | 2013-11-19 | 100 | 15873
2014-07-31 | 2014-08-04 | 2008 | Air Force active | MFH improvement | TUR | TURKEY | INCIRLIK AIR BASE ADANA | LJYC084001 | Improve Family Housing 515 Units | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | 41970 | 42316 | 2009-12-04 | 2015-07-19 | 2011-06-30 | 2015-07-19 | 37 | 14622
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Major construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK093005 | Construct Child Development Center | 2012-01-07 | 2011-09-02 | LBB (EBC AWD) | 9924 | 10468 | 2012-07-09 | 2014-07-22 | 2011-03-09 | 2014-06-30 | 100 | 1307
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Major construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK093005 | Construct Child Development Center | 2012-01-07 | 2012-05-15 | Peter Gross GmbH | 1263 | 1263 | 2012-07-09 | 2014-07-22 | 2011-03-09 | 2014-06-30 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000 | Upgrade Weapons Storage Area, Phase I | 2009-08-06 | 2009-09-26 | Doyon Project Services, Federal Way, WA | 10481 | 12017 | 2009-11-11 | 2012-12-10 | 2009-08-07 | 2013-12-13 | 100 | 3873
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000 | Upgrade Weapons Storage Area, Phase I | 2009-08-06 | 2013-07-17 | Affiliated Construction Group | 38 | 38 | 2009-11-11 | 2012-12-10 | 2009-08-07 | 2013-12-13 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS093002 | CNS Addition To Child Development Center (Cdc) B8210 | 2009-07-14 | 2009-08-31 | MAPCO, Inc. | 5913 | 6605 | 2009-10-15 | 2012-08-20 | 2011-02-22 | 2014-10-07 | 95 | 1420
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS093002 | CNS Addition To Child Development Center (Cdc) B8210 | 2009-07-14 | 2013-06-15 | JSR | 367 | 367 | 2009-10-15 | 2012-08-20 | 2011-02-22 | 2014-10-07 | 95 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2009-09-24 | Nishimatsu Construction Co Ltd | 104518 | 108089 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | -25132
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2010-03-30 | Title II Contract through AFCEE/EX | 3773 | 3773 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2010-08-09 | Corps of Engineers D-B for project EVKP10-4218 | 26 | 26 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2011-03-31 | GEITA Contract through AFCEE/EX | 30 | 30 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2011-04-30 | GEITA Contract through AFCEE/EX | 140 | 140 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2011-06-30 | GEITA Contract through AFCEE/EX | 18 | 18 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2011-09-27 | FY11 US Civilain (GS-) Pay for 18CONS per AFCEE/CMP | 38 | 38 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2012-03-16 | GEITA (A&AS) through AFCEE/EX | 76 | 76 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 436 | 436 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2012-11-19 | FY12 US Civilain (GS-) Pay for 18CONS per AFCEE/CMP | 65 | 65 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2012-11-19 | FY13 US Civilian (GS-) Pay for 18CONS per AFCEE/CMP | 49 | 49 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2013-03-26 | GEITA (A&AS) through AFCEE/EX | 62 | 62 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ094217 | Improve Family Housing, Ph9 | 2009-06-23 | 2013-09-05 | FY14 US Civilian (GS-) Pay for 18CONS per AFCEC/CMP | 20 | 20 | 2010-02-04 | 2014-06-10 | 2015-10-20 | 2014-06-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Minor construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY086000 | Interim Horizontal Landfill Expansion | 2009-07-31 | 2010-03-11 | RMA Land Construction | 910 | 910 | 2010-03-29 | 2013-04-30 | 2010-12-15 | 2013-04-30 | 99 | 883
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Minor construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD110006A | Construct CDC Addition, B650 | 2011-06-20 | 2011-08-11 | MODULAR MANAGEMENT GROUP, INC | 600 | 629 | 2011-08-30 | 2013-08-08 | 2012-09-12 | 2014-04-30 | 100 | 132
2014-07-31 | 2014-08-04 | 2009 | Air Force active | Minor construction | TUR | TURKEY | ANKARA ADMINISTRATION OFFICE | AKNR041053 | CNS Replace Asf Admin Bldg 2621 | 2011-02-22 | 2011-09-23 | MATOC Contractor | 1367 | 1367 | 2012-02-15 | 2015-03-03 | 2011-05-12 | 2015-02-01 | 13 | 1549
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH103500 | Expeditionary Fighter Shelter | 2010-05-06 | 2010-09-07 | CH2MHILL | 2959 | 3868 | 2010-10-15 | 2014-03-24 | 2011-07-15 | 2014-04-30 | 100 | -2072
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | AFG | AFGHANISTAN | KANDAHAR AB | KARD113100 | Expand Cargo Handling Area | 2010-11-23 | 2011-02-14 | Yenigun Insaat Sanayi ve Ticaret A.S. | 5337 | 6121 | 2011-03-30 | 2013-02-01 | 2011-11-21 | 2013-10-03 | 100 | 7100
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 | 2010-07-12 | 2011-06-02 | Haskell Corporation | 26981 | 28617 | 2011-06-17 | 2015-10-11 | 2014-11-23 | 2015-10-11 | 75 | 31702
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT033003 | Consol Communications Facility | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | 10249 | 11773 | 2010-10-13 | 2014-08-15 | 2011-11-09 | 2015-09-01 | 95 | 1268
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA061726 | F-35 POL Ops Facility | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | 4309 | 4447 | 2010-10-27 | 2013-09-30 | 2010-12-30 | 2014-10-31 | 99 | 127
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073902 | F-35 Hydrant Refueling System Phase 1 | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | 9452 | 10287 | 2010-07-15 | 2013-10-30 | 2011-02-28 | 2014-10-31 | 99 | 76
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073904 | F-35 JP-8 Flightline Fillstands | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | 3217 | 3422 | 2010-10-07 | 2013-10-30 | 2010-12-30 | 2014-10-31 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073905 | F-35 JP-8 West Side Bulk Fuel Tank Upgrades | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | 1464 | 1494 | 2010-06-15 | 2013-10-30 | 2010-12-30 | 2014-05-30 | 99 | 85
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR033702 | Consolidated Communications Facility | 2010-05-19 | 2010-07-07 | Carothers Construction | 16518 | 16824 | 2010-08-11 | 2013-05-25 | 2013-08-10 | 2013-10-23 | 90 | 1104
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT013025 | Combat Weapons Training Facility | 2010-07-09 | 2010-09-22 | Harkins Development Corp | 8381 | 8519 | 2010-12-03 | 2012-06-22 | 2011-09-30 | 2014-08-29 | 99 | 1389
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR053037 | Aerospace Ground Equipment Maintenance Complex | 2012-01-27 | 2011-09-30 | LBB (EBC AWD) | 10500 | 10500 | 2012-06-15 | 2014-02-12 | 2012-09-26 | 2014-02-11 | 100 | -2987
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR053037 | Aerospace Ground Equipment Maintenance Complex | 2012-01-27 | 2012-06-15 | NATO | 3181 | 3181 | 2012-06-15 | 2014-02-12 | 2012-09-26 | 2014-02-11 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR0530402 | Contingency Response Group Command | 2011-06-26 | 2011-08-26 | Bodo Freimuth GmbH (Demo AWD) | 235 | 658 | 2012-01-01 | 2014-03-18 | 2012-09-26 | 2014-03-17 | 100 | -717
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR0530402 | Contingency Response Group Command | 2011-06-26 | 2011-09-24 | LBB (EBC AWD) | 19788 | 19788 | 2012-01-01 | 2014-03-18 | 2012-09-26 | 2014-03-17 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK043100 | Fitness Center | 2011-01-22 | 2011-05-30 | Peter Gross Bau | 17881 | 19025 | 2011-06-07 | 2013-11-27 | 2006-04-15 | 2013-11-26 | 100 | 1127
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | HI | HAWAII | HICKAM AIR FORCE BASE | KNMD063003 | Ground Control Tower | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | 7379 | 7423 | 2012-09-07 | 2014-12-04 | 2011-10-28 | 2014-12-16 | 70 | 4435
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | MD | MARYLAND | ANDREWS AIR FORCE BASE | AJXF063009 | Replace Munitions Storage Area | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | 10465 | 10753 | 2011-06-23 | 2015-02-15 | 2011-12-16 | 2015-02-15 | 88 | 3456
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG081001 | Land Acquisition North & South Boundaries | 2012-05-09 | 2012-09-12 | In-House Work Force-NWK | 3475 | 3475 | 2012-09-12 | 2014-09-30 | 2013-02-28 | 2014-09-30 | 60 | -195
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000A | Upgrade Weapons Storage Area | 2012-04-23 | 2012-11-28 | RSCI | 9475 | 9463 | 2013-01-07 | 2015-04-29 | 2012-02-29 | 2015-02-28 | 40 | 99
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063002 | Consolidated Communication Facility | 2010-01-14 | 2010-03-24 | San Juan Construction, Inc. | 12305 | 23141 | 2010-04-21 | 2014-01-10 | 2008-06-15 | 2014-06-24 | 99 | 11992
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063002 | Consolidated Communication Facility | 2010-01-14 | 2012-01-26 | Spiral Solutions | 1930 | 1930 | 2010-04-21 | 2014-01-10 | 2008-06-15 | 2014-06-24 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD103003 | UAS Ftu Complex | 2010-05-18 | 2010-09-02 | Mesa Verde Enterprises | 9947 | 15588 | 2010-11-15 | 2013-02-28 | 2012-08-03 | 2013-12-12 | 100 | 5000
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD103003 | UAS Ftu Complex | 2010-05-18 | 2010-09-07 | Creative Times | 16695 | 16695 | 2010-11-15 | 2013-02-28 | 2012-08-03 | 2013-12-12 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | NC | NORTH CAROLINA | SEYMOUR JOHNSON AIR FORCE BASE | VKAG013004A | Radar Approach Control Complex, Ph 1 | 2010-06-28 | 2010-09-21 | Sanford Group | 5655 | 6168 | 2010-09-29 | 2013-11-08 | 2012-02-06 | 2013-11-08 | 100 | 432
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF082003 | Dormitory (168 Rm) | 2010-05-21 | 2010-08-20 | RAASS Brothers Inc. | 16590 | 17063 | 2010-10-05 | 2012-05-09 | 2012-05-09 | 2013-11-20 | 100 | 18373
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | Child Development Center | 2010-03-17 | 2010-05-27 | Nationview/BhateJV | 8649 | 9522 | 2010-05-27 | 2013-08-21 | 2011-12-15 | 2014-01-10 | 100 | 10408
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | Child Development Center | 2010-03-17 | 2010-09-27 | MA-CHIS KAWV TWO, LLC | 231 | 231 | 2010-05-27 | 2013-08-21 | 2011-12-15 | 2014-01-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | Child Development Center | 2010-03-17 | 2013-09-02 | Southwind Construction - Task Order 006 | 27 | 27 | 2010-05-27 | 2013-08-21 | 2011-12-15 | 2014-01-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | OK | OKLAHOMA | VANCE AIR FORCE BASE | XTLF033303 | Control Tower | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | 8850 | 9518 | 2010-10-05 | 2014-10-02 | 2012-05-31 | 2014-10-02 | 76 | 673
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA073006A | Blatchford-Preston Complex Ph II | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | 35759 | 37149 | 2010-12-16 | 2014-12-15 | 2012-02-15 | 2014-12-15 | 93 | 1993
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA103001 | Construct Network Control Center | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | 2580 | 3160 | 2012-07-05 | 2014-11-28 | 2011-08-15 | 2014-10-28 | 69 | 3432
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA107000 | Coalition Compound Billeting | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | 45273 | 44968 | 2012-04-16 | 2015-04-16 | 2013-11-30 | 2015-03-16 | 65 | 52000
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU053000 | Joint Intel Technical Training Facility, Ph 1 (TFI) | 2010-04-12 | 2010-08-16 | PBS&J Constructors, Inc. | 11390 | 12899 | 2010-10-13 | 2013-05-15 | 2011-06-01 | 2013-10-31 | 100 | 1919
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU053000 | Joint Intel Technical Training Facility, Ph 1 (TFI) | 2010-04-12 | 2013-04-19 | SDIC Constructors | 774 | 774 | 2010-10-13 | 2013-05-15 | 2011-06-01 | 2013-10-31 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | Recruit Dormitory 2, Phase 2 | 2009-10-15 | 2010-04-20 | COE-LB Martin Harris/SATX | 41573 | 42572 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2014-09-30 | 98 | 3548
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | Recruit Dormitory 2, Phase 2 | 2009-10-15 | 2011-05-31 | COE-SB-JSR/FPI Native American Contractor | 6663 | 7418 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2014-09-30 | 98 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | Recruit Dormitory 2, Phase 2 | 2009-10-15 | 2013-09-30 | COE-SB/Admin Gate Monitor-$91,652 | 92 | 92 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2014-09-30 | 98 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | Recruit Dormitory 2, Phase 2 | 2009-10-15 | 2013-09-30 | COE-SB/JOC - Drill Pad Lighting-$114,305.12 NonSIOH | 114 | 114 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2014-09-30 | 98 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility | 2009-12-10 | 2010-02-11 | Lyda Swinerton | 23484 | 25711 | 2010-05-05 | 2012-10-31 | 2011-09-01 | 2014-12-30 | 98 | 650
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility | 2009-12-10 | 2010-06-11 | Telecomm Ductbank Contractor | 1409 | 1602 | 2010-05-05 | 2012-10-31 | 2011-09-01 | 2014-12-30 | 98 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | TUR | TURKEY | INCIRLIK AIR BASE ADANA | LJYC003006 | Consolidated Community Center | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | 7881 | 8180 | 2010-04-26 | 2015-02-03 | 2008-04-15 | 2015-01-04 | 39 | 930
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF100031 | Construct Maintenance Operations Center And Command Post | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | 1672 | 1986 | 2011-06-03 | 2014-11-01 | 2011-06-15 | 2014-11-01 | 93 | 2149
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF100120 | Construct SatCom Facility | 2010-10-28 | 2010-05-06 | Lakeshore Engineering Services, Inc. | 1137 | 1184 | 2011-06-03 | 2014-11-01 | 2011-09-15 | 2014-11-01 | 93 | 1690
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM043003 | F-22A Radar Cross Section Testing Facility | 2010-01-06 | 2010-05-27 | Okland Construction | 18401 | 18974 | 2010-06-29 | 2014-08-15 | 2011-12-22 | 2014-08-15 | 98 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | VA | VIRGINIA | AIR COMBAT COMMAND | WACC113220 | Runway (Sharana) | 2010-06-21 | 2010-09-10 | METAG Insaat Ticaret A.S. | 18251 | 10060 | 2010-10-16 | 2011-10-30 | 2011-10-30 | 2011-10-30 | 29 | 21677
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | MUHJ053008 | West & Lasalle Gates Force Protection/Access | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | 7186 | 8498 | 2010-08-04 | 2013-07-19 | 2011-04-28 | 2014-09-03 | 99 | 1562
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | WY | WYOMING | FRANCIS E WARREN AIR FORCE BASE | GHLN053010 | ADAL Missile Service Complex | 2009-10-16 | 2010-03-11 | Lindgren RF Enclosures | 329 | 351 | 2010-04-07 | 2011-11-10 | 2011-09-19 | 2013-10-21 | 100 | -29
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Major construction | WY | WYOMING | FRANCIS E WARREN AIR FORCE BASE | GHLN053010 | ADAL Missile Service Complex | 2009-10-16 | 2010-03-11 | RSCI | 4944 | 5324 | 2010-04-07 | 2011-11-10 | 2011-09-19 | 2013-10-21 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ104126 | Improve Family Housing, Ph 10 | 2010-04-21 | 2010-08-10 | Obayashi Corporation | 54864 | 57863 | 2010-10-01 | 2014-03-18 | 2012-10-01 | 2014-03-18 | 100 | 1120
2014-07-31 | 2014-08-04 | 2010 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ104126 | Improve Family Housing, Ph 10 | 2010-04-21 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 371 | 371 | 2010-10-01 | 2014-03-18 | 2012-10-01 | 2014-03-18 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH103046 | Construct Network Control Center | 2012-01-31 | 2012-05-18 | CH2MHill | 1274 | 1274 | 2012-06-07 | 2014-02-15 | 2012-07-27 | 2014-06-14 | 100 | 1749
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH103051 | Install Area Lighting On Bravo Apron | 2012-01-31 | 2012-05-18 | CH2MHill | 1704 | 1704 | 2012-06-07 | 2013-11-30 | 2012-07-27 | 2013-11-30 | 100 | 1932
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Minor construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT073008 | Construct Military Working Dog & Supporting Facility | 2011-07-25 | 2011-09-28 | IE PACIFIC INC | 1620 | 1620 | 2011-10-20 | 2013-02-21 | 2012-09-10 | 2013-02-22 | 99 | 1884
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | BRVN060310 | Operations Town Dining Facility | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 936 | 936 | 2011-12-19 | 2014-02-01 | 2012-12-31 | 2014-02-01 | 100 | 1098
2014-07-31 | 2014-08-04 | 2010 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | BRVN100460 | Construct Flightline Fire Station | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 1243 | 1243 | 2011-12-19 | 2014-02-01 | 2012-12-31 | 2014-02-01 | 100 | 1397
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | CA | CALIFORNIA | FRESNO YOSEMITE INTERNATIONAL ANG | HAYW049133 | Replace Squadron Operations Facility | 2010-12-10 | 2011-02-22 | J.I. Garcia | 7990 | 10705 | 2011-04-14 | 2013-11-22 | 2012-07-12 | 2014-05-09 | 99 | 920
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | CA | CALIFORNIA | SOUTH CALIFORNIA LOGISTICS AIRPORT | SCLA069165 | TFI - Predator Beddown - FTU/LRE Site | 2010-01-22 | 2010-08-02 | PAC West Builders | 4628 | 6372 | 2010-08-30 | 2012-03-13 | 2011-08-30 | 2012-04-30 | 100 | -2028
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU019119 | ADAL Weapon Release Facility | 2010-05-28 | 2010-09-23 | Tower One Construction Company | 3025 | 3649 | 2010-10-27 | 2012-02-09 | 2011-08-23 | 2014-08-20 | 99 | -501
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | CT | CONNECTICUT | BRADLEY INTERNATIONAL AIRPORT | CEKT079036 | TFI - cNAF Beddown - Upgrade Facilities | 2012-02-21 | 2010-05-26 | LUPACHINO & SALVATORE, INC. | 6107 | 6764 | 2010-06-21 | 2013-02-28 | 2011-06-25 | 2013-02-28 | 100 | -2236
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069208 | TFI - F-22 LO/Composite Repair Facility | 2009-12-02 | 2010-04-20 | SU MO-NAN, LLC | 23250 | 27119 | 2010-05-24 | 2012-04-19 | 2011-12-25 | 2012-05-15 | 100 | 1119
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109501 | TFI - F-22 Parking Apron and Taxiways | 2012-01-04 | 2012-07-16 | Cutting Edge | 2032 | 2187 | 2012-08-08 | 2013-09-07 | 2013-08-08 | 2013-09-07 | 100 | 3914
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | IL | ILLINOIS | ABRAHAM LINCOLN CAPITAL AIRPORT | DCFT039115 | Security Improvements - Relocate Base Entrance | 2010-05-13 | 2010-09-17 | Perry Broughton Trucking and Excavating | 3391 | 3668 | 2010-10-26 | 2012-07-30 | 2010-10-26 | 2012-07-30 | 100 | 668
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | IL | ILLINOIS | GENERAL WAYNE A. DOWNING PEORIA IAP(ANG) | JLQN069160 | Squadron Operations Facility | 2010-02-18 | 2010-06-21 | JM Industrial Supply, Inc./River City Construction | 9132 | 10260 | 2010-08-17 | 2012-07-02 | 2012-02-13 | 2012-06-30 | 100 | 260
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | IA | IOWA | DES MOINES INTERNATIONAL AIRPORT | FFAN029023 | Add to and Alter Security Forces Facility | 2010-08-06 | 2010-09-24 | Neuman Brothers | 4014 | 4247 | 2010-10-01 | 2011-09-11 | 2011-06-28 | 2012-07-27 | 100 | -353
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE089032 | TFI - Upgrade DCGS Facilities | 2010-05-11 | 2010-08-04 | Key Construction Company | 8223 | 9068 | 2010-08-16 | 2011-11-21 | 2011-08-16 | 2013-11-01 | 100 | 368
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | ME | MAINE | BANGOR INTERNATIONAL AIRPORT | FKNN089019 | Replace Aircraft Maintenance Hangar and Shops | 2009-09-29 | 2010-05-12 | Sheridan Corp | 15064 | 17786 | 2010-11-05 | 2012-08-01 | 2012-11-24 | 2013-03-28 | 98 | -10180
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MD | MARYLAND | JOINT BASE ANDREWS | AJXF049104 | Replace Munitions Maintenance and Storage Complex | 2010-02-03 | 2011-04-15 | Charter Environmental, Inc. | 13942 | 16733 | 2010-09-13 | 2014-11-01 | 2010-11-12 | 2014-12-30 | 88 | 2962
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MA | MASSACHUSETTS | BARNES MUNICIPAL AIRPORT | AXQD089070 | Aircraft Ready Shelters | 2010-08-02 | 2010-09-30 | Maron Construction | 5428 | 6525 | 2010-10-26 | 2012-12-31 | 2011-10-26 | 2013-01-31 | 100 | -1575
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN019136 | Replace Ops and Training /ADAL DGS | 2010-07-16 | 2010-09-27 | P&S Construction | 2487 | 3116 | 2010-11-01 | 2013-06-14 | 2011-10-27 | 2013-07-31 | 50 | -21
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MI | MICHIGAN | ALPENA COUNTY REGIONAL AIRPORT | TDVG029066 | Replace Troop Training Quarters | 2010-06-18 | 2010-08-24 | B&B General Contracting Inc. | 6793 | 7299 | 2010-08-30 | 2012-01-23 | 2011-08-15 | 2013-05-31 | 100 | -1601
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MI | MICHIGAN | SELFRIDGE AIR NATIONAL GUARD BASE | VGLZ059023 | Add to and Alter Squadron Operations Facility | 2010-08-20 | 2010-09-28 | Rock Industries, Inc. | 5698 | 6670 | 2010-11-15 | 2012-11-20 | 2012-01-10 | 2013-04-12 | 99 | -430
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MI | MICHIGAN | W. K. KELLOGG AIRPORT | MBMV079055 | TFI - cNAF Beddown - Upgrade Bulding 6923 | 2010-08-26 | 2010-09-30 | Beckering Advisors, Inc. | 8851 | 10730 | 2010-10-17 | 2012-04-06 | 2012-04-17 | 2012-10-30 | 100 | -2620
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MN | MINNESOTA | MINNEAPOLIS ST PAUL INTL AIRPORT | QJKL089207 | Alter STARBASE Facility | 2010-09-01 | 2010-09-29 | L.S. Black Constructors, Inc. | 1775 | 2177 | 2010-11-08 | 2011-10-17 | 2011-08-08 | 2012-03-01 | 100 | 277
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MS | MISSISSIPPI | GULFPORT - BILOXI REGIONAL AIRPORT | JTVE099057 | Force Protection Measures - Relocate Base Entrance | 2012-08-15 | 2012-09-27 | Gottfried Contracting | 3823 | 4111 | 2012-10-10 | 2014-08-25 | 2013-06-24 | 2014-08-25 | 56 | 220
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB099003 | Add to Fire Station | 2010-03-01 | 2009-09-23 | Lee Grover Construction | 293 | 358 | 2009-09-23 | 2014-04-30 | 2012-08-29 | 2014-04-30 | 99 | -2285
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB099003 | Add to Fire Station | 2010-03-01 | 2010-07-25 | Lee Grover Constrution | 5709 | 6678 | 2010-08-04 | 2013-08-05 | 2011-07-30 | 2014-05-30 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB079069 | Joint Forces Operations Center - ANG Share | 2009-11-13 | 2010-02-17 | Hausmann Construction, Inc. | 1306 | 1500 | 2010-02-18 | 2012-09-17 | 2011-09-16 | 2012-09-17 | 98 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | NV | NEVADA | RENO-TAHOE INTERNATIONAL AIRPORT | UCTL919637 | Replace Fire Station | 2010-07-27 | 2010-09-07 | Gilbane Building Company | 9263 | 10246 | 2010-09-23 | 2011-12-25 | 2012-03-21 | 2012-09-30 | 99 | -179
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | NH | NEW HAMPSHIRE | PEASE INTERNATIONAL TRADEPORT ANG | SZCQ089023 | Replace Squadron Operations Facilities | 2011-03-09 | 2011-09-19 | NUTMEG Companies, Inc. | 10752 | 11905 | 2011-10-24 | 2013-11-13 | 2013-02-15 | 2014-03-14 | 98 | 1906
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | NJ | NEW JERSEY | JOINT BASE MCGUIRE-DIX-LAKEHURST | PTFL029107 | Replace Base Civil Engineer Complex | 2010-07-14 | 2010-09-28 | Puente Construction Enterprises Inc | 6573 | 8308 | 2010-10-21 | 2012-05-07 | 2012-04-20 | 2013-07-05 | 100 | -1017
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATION | FPBB069168 | Reaper LRE Beddown | 2012-07-27 | 2012-10-17 | Black Horse Group | 3155 | 3252 | 2012-10-17 | 2013-11-01 | 2013-11-11 | 2014-06-16 | 100 | 552
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | OH | OHIO | MANSFIELD LAHM AIRPORT | PBXP069219 | TFI - RED HORSE Squadron Beddown | 2009-10-15 | 2010-04-12 | Butcher and Baeker Construction | 6368 | 6862 | 2010-05-17 | 2011-09-30 | 2011-06-21 | 2012-02-03 | 100 | -4538
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD929753 | Replace Munitions Storage Complex (ASA) | 2010-07-24 | 2011-04-08 | Penick-Nordic | 10533 | 11846 | 2011-05-24 | 2012-06-15 | 2012-05-07 | 2012-12-31 | 100 | -154
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | OK | OKLAHOMA | WILL ROGERS WORLD AIRPORT | YZEU069106 | TFI - ASOS Beddown | 2010-02-05 | 2010-05-06 | Magnum Construction | 4808 | 5206 | 2010-05-05 | 2012-04-18 | 2011-04-30 | 2012-12-04 | 100 | -2094
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | OR | OREGON | KLAMATH FALLS AIRPORT-KINGSLEY FIELD | KJAQ029041 | Replace Security Forces Facilities | 2010-05-28 | 2010-09-29 | S&B James | 5599 | 5842 | 2010-11-03 | 2012-06-05 | 2012-05-04 | 2012-10-12 | 100 | -158
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | SC | SOUTH CAROLINA | MCENTIRE JOINT NATIONAL GUARD BASE | PSTE089005 | Joint Forces Headquarters - ANG Portion | 2010-05-28 | 2010-08-31 | IKAHANA/CHOATE | 1300 | 1300 | 2010-08-31 | 2012-09-24 | 2011-08-26 | 2013-03-02 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC059827 | Add to Munitions Maintenance Complex, | 2010-08-17 | 2010-09-30 | Sunkota Construction, Inc. | 1054 | 1113 | 2010-10-21 | 2011-08-05 | 2011-07-23 | 2012-01-06 | 100 | -187
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC069080 | Addition to Above Ground Multi-Cube Magazine Storage | 2010-08-17 | 2010-09-30 | Sunkota Construction, Inc. | 964 | 1011 | 2010-10-21 | 2011-08-05 | 2011-07-23 | 2012-01-06 | 100 | -289
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | TN | TENNESSEE | MEMPHIS INTERNATIONAL AIRPORT | PYKL009136 | Base Civil Engineer Maintenance and Training Facilities | 2010-07-14 | 2010-09-21 | Chris Wood Construction Co, Inc. | 6069 | 7366 | 2010-10-19 | 2012-10-31 | 2012-10-18 | 2014-06-30 | 98 | -2434
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM972002 | Add to and Alter Avionics/ECM Shop | 2010-07-15 | 2010-09-20 | Triune-Beck JV | 1890 | 1986 | 2011-09-01 | 2012-09-20 | 2011-10-28 | 2012-10-15 | 100 | -14
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | TX | TEXAS | KELLY FIELD ANNEX | KELL089001 | Add/Alt Aircraft Maintenance Shops | 2011-07-18 | 2010-09-30 | FA Nunnelly | 4546 | 4965 | 2010-12-17 | 2013-01-23 | 2011-10-30 | 2014-03-27 | 100 | -2010
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | VT | VERMONT | BURLINGTON INTERNATIONAL AIRPORT | CURZ029000 | Add to and Alter Fire Crash/Rescue Station | 2010-06-12 | 2010-09-27 | EF Wall & Associates, Inc; | 4741 | 5044 | 2010-10-15 | 2012-01-10 | 2011-08-11 | 2012-01-10 | 100 | -956
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | WV | WEST VIRGINIA | EWVRA-SHEPHERD FIELD | PJVY069225 | C-5 Aircraft Upgrade Taxiways | 2010-06-09 | 2010-09-24 | Atlantic Contracting & Material Co., INC | 8080 | 9469 | 2010-10-05 | 2012-08-17 | 2011-11-25 | 2012-09-28 | 100 | -10031
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | WI | WISCONSIN | GENERAL MITCHELL INTERNATIONAL AIRPORT | HTUV039088 | Add to and Alter KC-135 Corrosion Control Hangar | 2009-11-25 | 2010-08-17 | KPH | 3805 | 4215 | 2010-09-13 | 2012-01-31 | 2011-06-10 | 2012-10-22 | 100 | -785
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Major construction | WY | WYOMING | CHEYENNE REGIONAL AIRPORT | DPEZ019148A | Add to Squadron Operations | 2011-02-04 | 2011-06-02 | Various Contractors | 975 | 1303 | 2011-06-01 | 2011-08-01 | 2011-11-28 | 2014-01-31 | 99 | -166
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW009192 | Add to Communications Training Facility | 2012-11-07 | 2012-12-27 | G2 Construction | 1448 | 1695 | 2013-01-24 | 2014-02-19 | 2014-01-24 | 2014-08-08 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | FL | FLORIDA | CAMP BLANDING MILITARY RESERVATION | CYQL099005 | DRBS Storage Facility | 2012-10-01 | 2013-02-11 | Sweat, LLC | 1143 | 1143 | 2013-02-11 | 2014-05-15 | 2013-11-08 | 2014-02-15 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU109096 | CRTC Squadron Operation Addition | 2012-11-13 | 2012-12-27 | Holland and Holland, Inc. | 1209 | 1363 | 2013-01-17 | 2014-01-31 | 2014-01-17 | 2014-07-31 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY099016 | DRBS Storage Facility | 2011-07-15 | 2011-09-29 | Serrano Construction and Development | 1643 | 1858 | 2011-09-29 | 2013-04-30 | 2012-08-23 | 2013-04-30 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | IN | INDIANA | FORT WAYNE INTERNATIONAL AIRPORT | ATQZ099062 | A-10 Flight Simulator Addition | 2011-09-15 | 2011-04-19 | Patterson Horth | 1028 | 1146 | 2011-05-20 | 2012-02-15 | 2012-03-15 | 2012-02-15 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | IA | IOWA | SIOUX GATEWAY AIRPORT/COL BUD DAY FIELD | VSSB069014 | Add To Security Forces Facility | 2013-06-19 | 2013-08-05 | H&R Construction | 1304 | 1377 | 2013-08-15 | 2014-02-19 | 2013-08-15 | 2014-06-04 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | MD | MARYLAND | MARTIN STATE AIRPORT | PJMS119034 | A10 Flight Simulator Facility | 2012-11-01 | 2013-01-08 | SAF, Inc. | 1818 | 1994 | 2013-01-24 | 2014-06-04 | 2014-03-26 | 2014-06-30 | 97 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | MA | MASSACHUSETTS | HANSCOM AFB | MXRD089075 | Joint Forces Operations Center- ANG Share | 2010-02-10 | 2010-05-27 | CTA Constr | 1500 | 1500 | 2010-05-27 | 2012-10-01 | 2010-05-27 | 2011-11-29 | 99 | 1500
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | MI | MICHIGAN | ALPENA COUNTY REGIONAL AIRPORT | TDVG072909A | Replace Classroom Training Facilities | 2012-11-15 | 2012-12-27 | Meridan Contracting Services, LLC | 1437 | 1608 | 2013-03-25 | 2014-01-10 | 2013-08-24 | 2014-06-03 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB109082 | Alter Base Entry Complex | 2012-10-30 | 2012-12-27 | American Contracting, LLC | 1297 | 1404 | 2013-01-23 | 2014-02-23 | 2014-01-23 | 2014-02-24 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | NH | NEW HAMPSHIRE | PEASE INTERNATIONAL TRADEPORT ANG | SZCQ119041 | Construct DRBS Storage Facility | 2012-09-28 | 2012-12-27 | Cornerstone Construction Service LLC | 1604 | 1615 | 2013-03-01 | 2014-02-24 | 2013-10-23 | 2014-03-07 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | NJ | NEW JERSEY | ATLANTIC CITY INTERNATIONAL AIRPORT | AQRC059017 | Munitions Administrative Facility | 2010-07-16 | 2010-09-29 | Ranco Construction Inc | 1510 | 1607 | 2010-10-25 | 2011-11-25 | 2011-10-25 | 2011-11-25 | 100 | 1607
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP089051 | PRIME BEEF "S Teams" Beddown | 2010-06-01 | 2010-09-28 | D.E. Walker Constructing Inc | 1778 | 1970 | 2010-11-22 | 2012-07-12 | 2011-11-22 | 2012-07-12 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | OH | OHIO | MANSFIELD LAHM AIRPORT | PBXP099056 | DRBS Storage Facility | 2010-09-01 | 2010-09-30 | Blue Scope Construction | 650 | 760 | 2010-09-30 | 2011-08-02 | 2011-04-28 | 2012-01-17 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD009206 | Multi-Use Instructional Facility | 2010-08-30 | 2010-09-21 | Rock Industries | 1614 | 1730 | 2010-10-07 | 2011-12-29 | 2011-10-07 | 2012-03-01 | 100 | 1730
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | OH | OHIO | ZANESVILLE AIR GUARD STATION | ZRVL099068 | Supply Warehouse | 2010-09-17 | 2010-10-27 | Henderson Contractors Corporation | 938 | 1232 | 2010-11-04 | 2012-08-31 | 2011-08-01 | 2013-03-29 | 100 | 1197
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | OR | OREGON | KLAMATH FALLS AIRPORT-KINGSLEY FIELD | KJAQ109023 | Expand South Arm/Disarm Apron | 2014-03-12 | 2014-05-14 | Alutiiq Manufacture | 1169 | 1238 | 2014-05-27 | 2014-10-07 | 2014-10-21 | 2014-10-07 | 0 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | RI | RHODE ISLAND | QUONSET STATE AIRPORT | TWLR099087 | C-130 Parking Apron | 2013-04-08 | 2013-11-01 | TRAC Builders | 1600 | 1732 | 2013-12-12 | 2014-09-11 | 2013-12-12 | 2014-09-11 | 65 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | TN | TENNESSEE | NASHVILLE INTERNATIONAL AIRPORT | BKTZ139025 | Convert RPA Interim SCIF, B720 | 2013-05-08 | 2013-06-20 | Codell Construction Company | 1651 | 1811 | 2013-07-01 | 2014-04-28 | 2014-04-16 | 2014-08-01 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM109901 | Add to Civil Engineering Facility | 2012-08-19 | 2012-11-21 | Triune-Beck JV | 1479 | 1545 | 2013-02-12 | 2014-05-30 | 2014-06-03 | 2014-06-13 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM119026 | Multi Use Training Facility | 2012-08-19 | 2012-11-21 | Tribune-Beck JV | 1697 | 1787 | 2013-02-12 | 2014-05-30 | 2013-11-30 | 2014-06-13 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | TX | TEXAS | ELLINGTON FIELD | FWJH079112 | Munitions Maintenance Shop | 2010-04-30 | 2010-09-28 | All American Brothers | 1762 | 1890 | 2010-10-06 | 2012-01-30 | 2011-04-04 | 2012-01-05 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | TX | TEXAS | FORT BLISS | FPBD109001 | Add to Vehicle Maintenance Facility | 2013-06-05 | 2013-12-26 | Mirador Enterprise, Inc | 1400 | 1539 | 2014-01-06 | 2015-01-25 | 2015-01-06 | 2015-01-25 | 25 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | TX | TEXAS | KELLY FIELD ANNEX | KELL099067 | F-16 Mission Training Center (Flight Sim) Facility | 2010-05-13 | 2011-09-28 | HJD Capital Electric, Inc | 1578 | 1685 | 2011-09-30 | 2013-02-28 | 2012-09-29 | 2013-02-28 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | VA | VIRGINIA | CAMP PENDLETON MILITARY RESERVATION | ERVD099006 | DRBS Storage Facility | 2011-06-24 | 2011-09-23 | Vanguard Contractors | 854 | 865 | 2012-03-12 | 2012-04-30 | 2012-09-08 | 2012-05-31 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | WV | WEST VIRGINIA | YEAGER AIRPORT | LYBH079028 | BCE Pavements and Grounds Facility | 2013-02-19 | 2013-06-14 | Wycliffe Enterprises, Inc | 899 | 930 | 2013-07-09 | 2014-05-30 | 2014-04-05 | 2014-05-30 | 43 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force NG | Minor construction | WV | WEST VIRGINIA | YEAGER AIRPORT | LYBH119145 | Convert Hangar 107 for Aeromedical Relocation | 2013-07-02 | 2013-09-03 | Wycliffe Inc | 1743 | 1826 | 2013-09-16 | 2014-07-31 | 2014-10-03 | 2014-08-15 | 46 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force res | Major construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG050237 | Small Arms Firing Range | 2010-07-21 | 2010-09-13 | P&S Construction, Inc. | 8578 | 9149 | 2010-10-14 | 2012-09-09 | 2012-02-16 | 2013-12-31 | 99 | 294
2014-07-31 | 2014-08-04 | 2010 | Air Force res | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT089021 | C-5 Squadron Operations And Aircraft Maintenance Facility | 2010-07-21 | 2010-09-20 | Solpac | 6402 | 7446 | 2010-09-20 | 2012-07-19 | 2011-09-19 | 2014-01-07 | 100 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force res | Major construction | FL | FLORIDA | HOMESTEAD AIR RESERVE BASE | KYJM049010 | Troop Feeding/Community Activity Center | 2010-07-26 | 2010-09-21 | JCI | 5117 | 5707 | 2010-12-29 | 2013-10-19 | 2012-05-22 | 2014-04-18 | 99 | -712
2014-07-31 | 2014-08-04 | 2010 | Air Force res | Major construction | FL | FLORIDA | HOMESTEAD AIR RESERVE BASE | KYJM049010 | Troop Feeding/Community Activity Center | 2010-07-26 | 2013-07-26 | CCI | 208 | 260 | 2010-12-29 | 2013-10-19 | 2012-05-22 | 2014-04-18 | 99 | 0
2014-07-31 | 2014-08-04 | 2010 | Air Force res | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT033002 | Iso Dock Extension Hangar 630 | 2010-07-23 | 2010-09-27 | Sea Tech of the Florida Keys | 2471 | 4294 | 2011-01-04 | 2014-08-29 | 2011-09-15 | 2014-08-29 | 94 | 710
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH110101 | Consolidated Rigging Facility | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest, JV, LLC | 8364 | 9839 | 2011-08-10 | 2015-01-31 | 2012-03-14 | 2015-01-31 | 87 | 1313
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH110103 | Medevac Ramp Expansion/ Fire Station | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest JV, LLC | 9537 | 10755 | 2011-08-10 | 2015-03-31 | 2012-03-14 | 2015-03-31 | 66 | 994
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH110104 | Fighter Hangar | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest IV, LLC | 8305 | 10417 | 2011-08-10 | 2015-02-28 | 2012-03-14 | 2015-02-28 | 76 | 3837
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AFG | AFGHANISTAN | HERAT | KLZT103000 | SOF Helicopter Apron | 2012-01-02 | 2012-03-05 | State Corps Limited/Kabul/Afghanistan | 6920 | 305 | 2013-02-13 | 2014-09-30 | 2012-12-21 | 2014-09-30 | 2 | 8200
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AL | ALABAMA | MAXWELL AIR FORCE BASE | PNQS983126 | ADAL Air University Library | 2010-12-07 | 2011-06-14 | Southeast Cherokee Construction | 10211 | 11043 | 2011-07-18 | 2013-10-18 | 2013-09-30 | 2014-02-12 | 100 | -38
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW083008 | Repair Central Heat And Power Plant Boiler | 2010-07-12 | 2011-06-02 | Haskell Corporation | 26981 | 30243 | 2011-06-17 | 2015-10-11 | 2014-11-24 | 2015-10-11 | 75 | 5187
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | FXSB073012 | F-22 Add/Alter Weapons Release Systems Shop & Ame (TFI) | 2010-09-29 | 2011-09-29 | Bristol Design Build Services, LLC | 5608 | 6317 | 2011-10-12 | 2013-10-08 | 2012-07-23 | 2013-10-08 | 100 | 481
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV063501 | AMARG Hangar | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | 22282 | 23098 | 2011-09-07 | 2015-01-30 | 2013-03-11 | 2015-01-30 | 93 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV103005 | HC-130J Parts Store | 2011-05-06 | 2011-09-28 | Benchmark INC, DBA Cobblestone/ Las Vegas/ NV | 5195 | 5517 | 2011-11-17 | 2014-02-14 | 2012-07-30 | 2014-02-21 | 100 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV113002 | HC-130J Aerial Cargo Facility | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | 7223 | 7526 | 2011-11-09 | 2013-09-08 | 2012-09-21 | 2014-12-31 | 91 | -2491
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV113007 | HC-130 AGE Maintenance Facility | 2010-12-03 | 2011-06-06 | Benchmark Contr DBA Cobblestone Constr Las Vegas NV | 4078 | 4127 | 2011-07-05 | 2013-10-22 | 2012-03-12 | 2014-02-10 | 100 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093000 | F-35 Academic Training Center | 2012-04-18 | 2012-08-30 | Archer Western Contractors | 43347 | 46499 | 2012-11-05 | 2014-09-30 | 2013-06-28 | 2014-09-11 | 82 | -2709
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093001 | F-35 Squadron Ops Facility | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | 9109 | 9247 | 2012-10-09 | 2014-01-06 | 2013-06-28 | 2014-05-30 | 99 | 273
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | CO | COLORADO | USAF ACADEMY | XQPZ084017 | Const Center For Character & Leadership Development | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | 24996 | 25002 | 2013-01-14 | 2015-04-30 | 2014-08-29 | 2015-04-30 | 45 | 1205
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT113001 | C-5M/C-17 Maintenance Training Facility, Ph 2 | 2011-03-09 | 2011-08-02 | Asset Group, Incorporated, Oklahoma City, Oklahoma | 2952 | 2950 | 2011-08-11 | 2014-05-12 | 2012-05-30 | 2014-08-29 | 96 | 166
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | DC | DISTRICT OF COLUMBIA | BOLLING AIR FORCE BASE | BXUR105000 | Joint Air Defense Operations Center | 2011-03-02 | 2011-08-05 | Sauer Inc. | 11978 | 14045 | 2011-08-05 | 2014-02-14 | 2012-02-29 | 2014-05-14 | 98 | 1997
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073908 | F-35 Fuel Cell Maintenance Hangar | 2010-10-06 | 2011-06-23 | Sauer Inc. | 6957 | 7196 | 2011-08-17 | 2013-08-06 | 2013-01-05 | 2014-02-10 | 100 | -299
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | Base Logistics Facility | 2010-09-22 | 2011-06-06 | Sauer Incorporated | 16031 | 16870 | 2011-07-19 | 2014-03-28 | 2011-07-25 | 2014-06-02 | 100 | 464
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | Base Logistics Facility | 2010-09-22 | 2011-08-29 | AEROSTAR ENVIRONMENTAL SERVICES, INC. | 192 | 192 | 2011-07-19 | 2014-03-28 | 2011-07-25 | 2014-06-02 | 100 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | Base Logistics Facility | 2010-09-22 | 2012-10-03 | STOA Architects | 163 | 163 | 2011-07-19 | 2014-03-28 | 2011-07-25 | 2014-06-02 | 100 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT053001 | Air Force Technical Applications Center | 2010-11-04 | 2011-06-03 | Hensel Phelps | 141231 | 146000 | 2011-07-06 | 2014-03-03 | 2015-06-30 | 2015-12-02 | 98 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT053001 | Air Force Technical Applications Center | 2010-11-04 | 2014-02-03 | CDA Solutions | 100 | 100 | 2011-07-06 | 2014-03-03 | 2015-06-30 | 2015-12-02 | 98 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | DEU | GERMANY | KAPAUN ADMINISTRATION ANX | TYFU083507R2 | Dormitory (128 Rm) | 2013-04-26 | 2011-09-16 | LBB (EBC AWD) | 17945 | 17945 | 2014-06-16 | 2015-10-30 | 2013-03-06 | 2015-09-21 | 1 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR073143 | UAS Satcom Relay Pads And Facility | 2011-08-12 | 2011-09-26 | Bidder C | 8352 | 9147 | 2011-12-15 | 2013-10-04 | 2012-12-30 | 2013-12-03 | 100 | -514
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR083001 | Deicing Fluid Storage & Dispensing Facility | 2012-05-10 | 2011-09-02 | LBB | 2671 | 2784 | 2012-10-31 | 2014-11-30 | 2011-08-17 | 2014-11-15 | 96 | -155
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR123063 | C-130J Flight Simulator Facility | 2013-08-12 | 2011-09-02 | LBB (EBC AWD) | 7113 | 7265 | 2013-11-27 | 2015-02-10 | 2012-04-29 | 2015-01-29 | 32 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY113007 | Guam Strike Ops Group & Tanker Task Force Renovation (TFI) | 2010-09-17 | 2011-09-12 | P & S Construction | 8627 | 9020 | 2011-09-27 | 2013-12-04 | 2012-08-13 | 2013-12-04 | 100 | 629
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY336509 | Guam Strike South Ramp Utilities Phase 1 (TFI) | 2010-09-17 | 2011-07-28 | P & S Construction | 9582 | 9617 | 2011-08-18 | 2014-07-31 | 2013-01-30 | 2014-07-31 | 100 | -1369
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | ITA | ITALY | AVIANO AIR BASE | ASHE083011 | Air Support Operations Squadron (ASOS) Facility | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | 7174 | 7896 | 2011-12-15 | 2015-01-01 | 2013-06-06 | 2014-09-15 | 65 | -755
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | ITA | ITALY | AVIANO AIR BASE | ASHE123000 | Dormitory (144 Rm) | 2011-02-14 | 2011-07-28 | A.T.I. TACOSE S.c.a.r.l. | 13672 | 13784 | 2011-10-11 | 2014-01-15 | 2013-01-13 | 2014-01-15 | 100 | -300
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | KOR | KOREA | KUNSAN AIR BASE | MLWR093183 | Construct Dmt Flight Simulator Facility | 2010-08-18 | 2011-07-07 | Kum Sung Construction Co., Ltd | 6568 | 6827 | 2011-07-07 | 2013-12-05 | 2012-06-29 | 2013-12-05 | 100 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | LA | LOUISIANA | BARKSDALE AIR FORCE BASE | AWUB025502 | Weapons Load Crew Training Facility | 2010-10-22 | 2011-08-03 | Pacific - Tech - Sauer JV | 14996 | 16172 | 2011-08-03 | 2014-08-15 | 2013-01-28 | 2014-08-15 | 94 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | NV | NEVADA | CREECH AIR FORCE BASE | LKTC113102 | UAS Airfield Fire/Crash Rescue Station | 2010-12-10 | 2011-06-29 | Jaynes Corporation | 7345 | 7423 | 2011-09-02 | 2014-07-31 | 2013-03-01 | 2014-07-31 | 97 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF093004 | F-35A Maintenance Hangar/AMU | 2011-03-23 | 2011-09-15 | Straub Construction, Inc | 20049 | 20684 | 2011-11-14 | 2013-11-14 | 2013-02-06 | 2013-11-15 | 100 | -3071
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | NJ | NEW JERSEY | MCGUIRE AIR FORCE BASE | PTFL083003 | Dormitory (120 Room) | 2010-12-08 | 2011-08-04 | Ranco Construction Inc | 13772 | 13905 | 2011-10-19 | 2013-11-20 | 2012-05-30 | 2013-11-20 | 100 | -2921
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ093004 | UAS Squadron Ops Facility | 2011-04-27 | 2011-10-11 | Speegle Construction Inc | 13126 | 13126 | 2012-01-10 | 2014-06-03 | 2013-01-18 | 2014-06-03 | 95 | -5260
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD093013 | UAS Add/Alter Maintenance Hangar | 2011-06-22 | 2011-09-13 | Candelaria Corporation | 10254 | 10674 | 2011-10-12 | 2013-11-22 | 2012-07-02 | 2014-02-21 | 100 | -3009
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV053114A | Armament Shop | 2011-07-13 | 2011-09-23 | K.L. House | 3548 | 3547 | 2011-11-09 | 2013-11-26 | 2012-01-26 | 2013-10-18 | 100 | -2178
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV083114 | H/MC-130 Fuel System Maintenance Facility | 2011-02-11 | 2011-09-23 | K.L House | 11178 | 11596 | 2011-11-09 | 2013-11-26 | 2012-05-01 | 2013-10-18 | 100 | -803
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | OMN | OMAN | AL MUSANAH AB | AMAB110001 | Airlift Ramp And Fuel Facilities | 2011-11-03 | 2012-05-10 | American Int'l Contractors, Inc. (AICI) | 36782 | 39132 | 2012-06-04 | 2014-09-20 | 2011-12-31 | 2014-09-20 | 97 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | OMN | OMAN | AL MUSANAH AB | AMAB110002 | Parallel Taxiway Extension | 2012-01-19 | 2012-07-05 | American Int'l Contractors, Inc. | 19348 | 19782 | 2012-08-06 | 2014-08-24 | 2013-11-01 | 2014-08-24 | 99 | 44245
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA073006B | Blatchford-Preston Complex, Phase III | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | 34177 | 34187 | 2012-03-26 | 2015-01-17 | 2013-03-31 | 2014-09-22 | 38 | 17607
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | 40848 | 40848 | 2013-08-07 | 2015-10-16 | 2013-08-15 | 2015-09-16 | 1 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA113001 | Theater Communications Facility | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | 9913 | 10408 | 2012-05-02 | 2015-01-02 | 2012-12-21 | 2014-11-29 | 49 | 12000
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | QAT | QATAR | AL UDEID AB | ALUA113031 | Munitions Storage Area Complex | 2011-12-21 | 2012-05-24 | American International Contractors, Inc | 42778 | 42672 | 2012-05-24 | 2014-01-31 | 2012-12-21 | 2013-11-21 | 100 | 48675
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | SC | SOUTH CAROLINA | CHARLESTON AIR FORCE BASE | DKFX913001P1 | Civil Engineer Complex (TFI) - Phase 1 | 2011-01-20 | 2011-06-03 | Sauer, Inc. | 11649 | 12334 | 2011-06-03 | 2014-03-13 | 2013-03-08 | 2014-03-13 | 95 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R3 | Recruit Dormitories Phase 3 | 2010-12-06 | 2011-09-20 | LB S&P-Facility Construction | 45885 | 46355 | 2011-11-01 | 2014-09-01 | 2012-12-28 | 2014-08-31 | 95 | -4894
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R3 | Recruit Dormitories Phase 3 | 2010-12-06 | 2012-08-09 | SB JSR-Exterior Facilties | 6887 | 6966 | 2011-11-01 | 2014-09-01 | 2012-12-28 | 2014-08-31 | 95 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R3 | Recruit Dormitories Phase 3 | 2010-12-06 | 2014-06-08 | JSR or equal | 1500 | 1500 | 2011-11-01 | 2014-09-01 | 2012-12-28 | 2014-08-31 | 95 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 | 2011-03-07 | 2011-07-08 | LB-KBR General Contract | 25985 | 27179 | 2011-08-29 | 2014-08-30 | 2013-06-30 | 2014-09-25 | 90 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 | 2011-03-07 | 2012-07-08 | SB JSR-Gary Rd Realign Pt 1of3 (see ATC3&4) | 153 | 242 | 2011-08-29 | 2014-08-30 | 2013-06-30 | 2014-09-25 | 90 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 | 2011-03-07 | 2013-10-08 | AEP-Gate Monitoring Services Option Year D | 202 | 261 | 2011-08-29 | 2014-08-30 | 2013-06-30 | 2014-09-25 | 90 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS093737V | BMT Visitors Reception Center | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | 21500 | 21895 | 2011-09-30 | 2014-04-09 | 2011-07-01 | 2014-11-28 | 97 | 1449
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Major construction | WY | WYOMING | CAMP GUERNSEY | AFSPC053012 | Nuclear/Space Security Tactics Training Center (Nssttc) | 2010-10-13 | 2011-06-02 | R.C. Heath Construction Co. | 3854 | 4061 | 2011-06-29 | 2012-12-13 | 2012-09-21 | 2014-05-15 | 99 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | 64622 | 65174 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 57 | 15198
2014-07-31 | 2014-08-04 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan) *ArchTestDigs* | 50 | 50 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 57 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT* | 72 | 72 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 57 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 319 | 319 | 2012-05-07 | 2015-10-31 | 2014-12-01 | 2015-11-08 | 57 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | ATUH085082 | EMSG Headquarters And Town Hall | 2012-01-31 | 2012-05-18 | CH2MHill | 998 | 998 | 2012-06-07 | 2013-12-22 | 2013-01-18 | 2013-12-22 | 100 | 1134
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | BAGR113008 | Operations Group Command And Control (C2) Facility | 2012-01-31 | 2012-05-18 | CH2MHill | 1618 | 1618 | 2012-06-07 | 2013-12-22 | 2013-01-18 | 2013-12-22 | 100 | 1838
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | BAGR113010 | Tactical Fighter AMU | 2012-01-31 | 2012-05-18 | CH2MHill | 1306 | 1306 | 2012-06-07 | 2013-10-15 | 2013-01-18 | 2013-10-15 | 100 | 1650
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | AFG | AFGHANISTAN | BAGRAM AB | BAGR113022 | Flight Line Fire Station | 2012-01-31 | 2012-05-18 | CH2M Hill | 1519 | 1519 | 2012-06-07 | 2014-02-15 | 2013-01-18 | 2014-05-01 | 100 | 1798
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR106261 | PL-1 Security Measures For Communications Compound | 2013-09-17 | 2013-11-13 | Mikan | 1840 | 1840 | 2014-03-17 | 2015-01-22 | 2015-01-30 | 2015-01-30 | 21 | 1840
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | DEU | GERMANY | SPANGDAHLEM AIR BASE | VYHK113003 | Catch Basin For Waste Water Treatment | 2012-04-16 | 2012-07-31 | UVB BITBURG | 1762 | 1762 | 2012-08-15 | 2014-08-01 | 2013-09-15 | 2014-09-30 | 90 | 1762
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | KWT | KUWAIT | ALI AL SALEM AB | AEWV111136 | Sewage Treatment System | 2012-08-29 | 2013-01-09 | ARABI CO. W.L.L. | 1592 | 1592 | 2013-04-10 | 2014-01-29 | 2013-08-15 | 2014-01-29 | 100 | 1788
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | NZYY110190 | Air Freight Facility | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 926 | 926 | 2011-12-19 | 2013-12-18 | 2013-02-28 | 2014-02-01 | 100 | 1041
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | KGZ | KYRGYZSTAN | MANAS TRANSIT CENTER | NZYY110200 | Aerial Port C2 Facility | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 1282 | 1282 | 2011-12-19 | 2013-12-31 | 2013-02-28 | 2014-02-01 | 100 | 1440
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF113020 | Medical Education & Training Facility Replacement | 2012-03-01 | 2012-05-31 | Synergy Systems Inc | 1698 | 1685 | 2012-08-14 | 2014-08-01 | 2013-04-17 | 2014-08-01 | 78 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA110032 | Fuel Truck Parking | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 1731 | 1731 | 2013-09-12 | 2015-04-07 | 2013-05-06 | 2014-12-08 | 2 | 1944
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113002 | Fuels Laboratory | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 1557 | 1557 | 2013-09-12 | 2015-04-07 | 2013-05-06 | 2014-12-08 | 2 | 1749
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113005 | C-17 Spare Parts Facility | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 1572 | 1572 | 2013-09-12 | 2015-04-07 | 2013-05-06 | 2014-12-08 | 2 | 1766
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113006 | High Mast Lighting | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 1573 | 1573 | 2013-09-12 | 2015-04-07 | 2013-05-06 | 2014-12-08 | 2 | 1767
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113009 | Entry Control Point | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 616 | 616 | 2013-09-12 | 2015-04-07 | 2013-05-06 | 2014-12-08 | 2 | 691
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113010 | Cryogenics Facility | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 1216 | 1216 | 2013-09-12 | 2015-04-07 | 2013-05-06 | 2014-12-08 | 2 | 1366
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113012 | ELRS Storage Facility | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 1616 | 1616 | 2013-09-12 | 2015-04-07 | 2014-04-17 | 2014-12-08 | 2 | 1815
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF080145 | Information Transfer Node | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 1074 | 4 | 2012-10-03 | 2014-12-01 | 2012-10-30 | 2014-12-01 | 15 | 1318
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF105000 | Dining Facility | 2012-04-06 | 2012-07-31 | C Davis and Associates | 1004 | 21 | 2012-10-03 | 2014-12-01 | 2012-09-01 | 2014-12-01 | 15 | 1233
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF110018 | EMSG Hq | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 1007 | 61 | 2012-10-03 | 2014-12-01 | 2012-09-10 | 2014-12-01 | 15 | 1236
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF110019 | Kennel | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 583 | 70 | 2012-10-03 | 2014-12-01 | 2012-09-10 | 2014-12-01 | 15 | 716
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF120037 | Clinic | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhab,i UAE) | 1515 | 1515 | 2013-09-27 | 2015-01-20 | 2014-10-05 | 2015-01-20 | 2 | 2000
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF120057 | Fire Protection Water Storage | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | 1120 | 1120 | 2013-09-30 | 2014-11-24 | 2014-10-05 | 2014-11-24 | 2 | 1256
2014-07-31 | 2014-08-04 | 2011 | Air Force active | Minor construction | ARE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF124001 | EOD Facility | 2013-07-18 | 2013-09-29 | ACF & BSC JV (Dubai, UAE) | 1144 | 1144 | 2013-09-29 | 2015-08-16 | 2014-10-05 | 2015-08-16 | 2 | 2000
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | AL | ALABAMA | MONTGOMERY REGIONAL AIRPORT (ANG) BASE | FAKZ959574 | Fuel Cell and Corrosion Control Hangar | 2011-03-15 | 2011-07-22 | Lord and Son Constrution, Inc | 7249 | 7783 | 2011-10-12 | 2013-11-01 | 2013-01-22 | 2014-07-31 | 99 | 326
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV089069 | TFI - Predator FOC – Increased Mission Orbit Tasking | 2011-05-13 | 2011-07-29 | Komada, LLC | 3761 | 4037 | 2011-09-08 | 2012-12-17 | 2012-09-07 | 2013-03-15 | 100 | -91
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | AZ | ARIZONA | FORT HUACHUCA | HFHA069130 | TFI - Predator LRE Beddown | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | 9434 | 10166 | 2013-04-08 | 2014-09-15 | 2014-06-02 | 2014-12-31 | 77 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | DE | DELAWARE | NEW CASTLE COUNTY AIRPORT | JLWS079103 | Joint Forces Operations Center - ANG Share | 2011-06-29 | 2011-09-16 | Vigil Contracting, Inc. | 1134 | 1164 | 2011-12-12 | 2014-01-31 | 2013-06-09 | 2014-01-31 | 98 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | FL | FLORIDA | JACKSONVILLE INTERNATIONAL AIRPORT | LSGA029009A | Security Forces Training Facility | 2010-11-12 | 2011-06-06 | Americaan Patriot Construction -IMC, LLC | 3909 | 4200 | 2011-08-05 | 2013-04-08 | 2012-12-03 | 2014-08-29 | 99 | -987
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU069150 | Relocate ASOS Facilities | 2011-04-20 | 2011-06-29 | Choice Concrete Construction LLC | 5962 | 6687 | 2011-08-01 | 2012-08-20 | 2012-07-28 | 2013-08-20 | 100 | -748
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069209 | TFI - F-22 Hangar, Squadron Operations and AMU | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | 37110 | 43059 | 2011-07-15 | 2014-01-10 | 2013-07-14 | 2014-06-30 | 98 | -3087
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069215 | TFI - F-22 Upgrade Munitions Complex | 2012-01-11 | 2012-05-24 | Nan Inc. | 17142 | 20850 | 2012-06-14 | 2014-03-14 | 2013-12-11 | 2014-03-31 | 99 | 3816
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109500 | TFI - F-22 Beddown Infrastructure Support | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | 5155 | 6794 | 2011-08-15 | 2014-01-10 | 2013-07-14 | 2013-11-23 | 99 | 856
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | IL | ILLINOIS | ABRAHAM LINCOLN CAPITAL AIRPORT | DCFT069059 | TFI - cNAF Beddown - Upgrade Facilities | 2010-12-15 | 2012-04-26 | JM Industrial Supply, Inc. | 13733 | 15077 | 2012-06-01 | 2014-02-21 | 2013-03-20 | 2014-02-21 | 99 | -730
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | IN | INDIANA | HULMAN REGIONAL AIRPORT | LDXF069123 | TFI - ASOS Beddown - Upgrade Facilities | 2011-03-08 | 2011-06-13 | Hannig Construction | 3571 | 3702 | 2011-07-07 | 2012-09-04 | 2012-07-06 | 2012-10-31 | 100 | -390
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | MD | MARYLAND | MARTIN STATE AIRPORT | PJMS909928 | Replace Operations and Medical Training Facility | 2011-08-17 | 2011-09-28 | Costello Construction of MD, Inc. | 11802 | 13426 | 2012-07-20 | 2014-02-28 | 2013-10-18 | 2014-08-29 | 99 | 1886
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATION | FPBB109013 | TFI - Reaper Infrastructure Support | 2012-07-27 | 2012-10-17 | Black Horse Group | 2040 | 2196 | 2012-10-17 | 2014-06-16 | 2013-10-12 | 2014-08-29 | 99 | -295
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | NY | NEW YORK | STEWART INTERNATIONAL AIRPORT | WHAY089079 | Base Defense Group Beddown | 2011-07-30 | 2011-09-23 | APS Contractors Inc | 13401 | 14451 | 2011-10-13 | 2014-07-01 | 2013-05-05 | 2014-08-15 | 97 | 172
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | NC | NORTH CAROLINA | STANLY COUNTY AIRPORT | WEFM089029 | Upgrade ASOS Facilities | 2011-04-19 | 2011-08-26 | DOT Construction | 1660 | 1873 | 2011-10-24 | 2013-03-25 | 2012-07-21 | 2014-06-07 | 99 | -123
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | PA | PENNSYLVANIA | STATE COLLEGE ANG STATION | WFGE089076 | Add to and Alter AOS Facility | 2010-04-16 | 2011-08-25 | HSCC | 3903 | 4222 | 2011-08-25 | 2012-11-27 | 2012-08-24 | 2013-11-29 | 100 | 130
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | TN | TENNESSEE | NASHVILLE INTERNATIONAL AIRPORT | BKTZ069078 | TFI- Renovate Intel Squadron Facilities | 2013-09-20 | 2013-11-21 | Codell Construction Company | 2765 | 3009 | 2013-12-02 | 2014-09-29 | 2014-10-17 | 2014-10-17 | 40 | 1350
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | TN | TENNESSEE | NASHVILLE INTERNATIONAL AIRPORT | BKTZ069078 | TFI- Renovate Intel Squadron Facilities | 2013-09-21 | 2013-11-21 | Codell Construction Co. | 3309 | 3690 | 2013-12-02 | 2014-10-31 | 2014-10-17 | 2014-10-31 | 40 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Major construction | TX | TEXAS | ELLINGTON FIELD | FWJH069194 | TFI - Alter UAV Maintenance Hangar (Bldg 1382) | 2012-01-06 | 2012-06-14 | LeeTex Construction | 5038 | 5971 | 2012-07-23 | 2014-07-03 | 2013-07-23 | 2014-07-03 | 100 | 93
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Minor construction | CA | CALIFORNIA | MOFFETT FIELD (NASA), SAN JOSE, (ANG) | QMSN099051 | Force Protection Measures - Relocate Main Gate | 2011-11-04 | 2012-02-09 | Herrera Corporation | 1875 | 1952 | 2011-03-02 | 2013-01-07 | 2011-08-29 | 2013-02-04 | 100 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Minor construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU119021 | Relocate Taxiway Juliet | 2012-06-22 | 2012-08-23 | JE Hurley Construction, Inc. | 1824 | 1916 | 2012-09-12 | 2013-05-06 | 2013-03-01 | 2013-08-26 | 100 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Minor construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109032 | TFI- F-22 Beddown- Add to Communication Facility | 2012-01-04 | 2012-06-12 | HAKO PLUMBING, INC. | 1695 | 1953 | 2012-06-17 | 2014-08-17 | 2014-06-07 | 2014-08-17 | 99 | 0
2014-07-31 | 2014-08-04 | 2011 | Air Force NG | Minor construction | WY | WYOMING | CHEYENNE REGIONAL AIRPORT | DPEZ089083 | Relocate ROSC | 2011-07-18 | 2012-04-11 | Recco, Inc. | 1636 | 1953 | 2012-04-25 | 2013-07-31 | 2012-10-22 | 2014-06-30 | 99 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | 53805 | 56240 | 2012-06-19 | 2015-01-22 | 2013-11-20 | 2015-01-22 | 66 | -19165
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | 3230 | 3230 | 2012-06-19 | 2015-01-22 | 2013-11-20 | 2015-01-22 | 66 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | 4979 | 4979 | 2012-06-19 | 2015-01-22 | 2013-11-20 | 2015-01-22 | 66 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | 1874 | 2192 | 2012-06-19 | 2015-01-22 | 2013-11-20 | 2015-01-22 | 66 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | 1799 | 1799 | 2012-06-19 | 2015-01-22 | 2013-11-20 | 2015-01-22 | 66 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV103006P1 | EC-130H Simulator/Training Operations | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | 14348 | 14439 | 2013-02-05 | 2015-02-23 | 2013-10-07 | 2014-12-23 | 81 | -4333
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV123002 | HC-130J Joint Use Fuel Cell | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | 12361 | 12415 | 2012-10-31 | 2014-11-03 | 2014-04-28 | 2014-09-02 | 88 | 1256
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | AETC120010 | F-35 ADAL Aircraft Maintenance Unit | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | 4781 | 4980 | 2012-10-09 | 2014-01-06 | 2012-11-30 | 2014-05-30 | 99 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | AETC120011 | F-35 Squad Ops/AMU 2 | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | 12359 | 12359 | 2013-04-04 | 2014-09-19 | 2012-11-30 | 2014-11-26 | 61 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK111089A | Emergency Permanent Repair Hangar 245 | 2012-04-06 | 2012-07-11 | Blackhawk Ventures, LLC | 2404 | 2757 | 2012-08-28 | 2014-06-27 | 2014-04-25 | 2014-06-27 | 93 | 2998
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK133004 | Emergency Pest Management Facility | 2012-04-30 | 2012-08-14 | Guyco, Inc. | 1452 | 1462 | 2012-09-25 | 2013-02-25 | 2014-06-16 | 2014-06-23 | 100 | 1833
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT083003 | Dormitory (144 RM) | 2011-12-22 | 2012-05-11 | Barnhart-Balfour-Beatty, Inc; San Diego CA | 18492 | 18780 | 2012-06-11 | 2014-04-18 | 2013-11-11 | 2014-04-29 | 99 | -800
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | CA | CALIFORNIA | VANDENBERG AIR FORCE BASE | XUMU033002 | Education Center | 2011-12-13 | 2012-02-28 | TEEHEE-STRAUB JV | 13185 | 13690 | 2012-03-29 | 2014-01-06 | 2013-09-20 | 2014-08-08 | 99 | 693
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | CO | COLORADO | USAF ACADEMY | XQPZ044003 | Const Vehicle Search Facility | 2011-11-18 | 2012-03-30 | Komada LLC | 5941 | 5888 | 2012-05-01 | 2013-11-18 | 2013-12-15 | 2013-11-18 | 100 | -6712
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT123000 | C-5M Formal Training Unit Facility | 2011-11-14 | 2012-05-07 | Eastern Sun Enterprises, Incorporated | 2085 | 2085 | 2012-06-12 | 2016-02-29 | 2013-11-04 | 2016-02-29 | 5 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR063017 | Dormitory (192 RM) | 2013-10-02 | 2012-05-24 | LBB (EBC AWD) | 29542 | 29542 | 2014-07-01 | 2015-11-16 | 2015-03-02 | 2015-09-15 | 1 | -1624
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17001 | Aircraft Apron/Taxiway And Maintenance Shelters | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | 6740 | 6641 | 2012-05-02 | 2014-02-02 | 2013-05-12 | 2014-08-28 | 99 | 8177
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17002 | Combat Aircraft Loading Area | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | 43421 | 43715 | 2012-10-01 | 2015-03-12 | 2014-01-16 | 2015-03-12 | 12 | 154000
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17003 | Parallel Taxiway Extension | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | 10522 | 10522 | 2012-10-01 | 2015-04-23 | 2014-05-24 | 2015-04-23 | 4 | 24000
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | DEU | GERMANY | US AIR FORCES, EUROPE | USAFE17004 | Expeditionary Lodging | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | 26588 | 27071 | 2012-10-20 | 2015-01-09 | 2013-09-30 | 2015-01-09 | 36 | 33000
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GRL | GREENLAND | THULE AIR BASE | WWCX103033 | Dormitory (72 PN) | 2011-12-05 | 2012-05-11 | MTHojgaard | 27936 | 27907 | 2012-06-06 | 2014-08-25 | 2014-05-27 | 2014-08-08 | 99 | 2000
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY123009 | Guam Strike - Clear Water Rinse Facility | 2011-11-15 | 2012-04-21 | Niking Corporation | 6739 | 6739 | 2012-06-11 | 2013-12-12 | 2013-12-30 | 2013-12-12 | 100 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY123011 | Guam Strike Coventional Munition Maintenance Facility | 2011-11-22 | 2012-04-27 | P & S Construction | 9527 | 9719 | 2012-05-11 | 2014-07-18 | 2014-07-19 | 2014-09-17 | 93 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY123011 | Guam Strike Coventional Munition Maintenance Facility | 2011-11-22 | 2012-05-29 | Navy Crane Center | 59 | 59 | 2012-05-11 | 2014-07-18 | 2014-07-19 | 2014-09-17 | 93 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | AJJY983202 | Air Freight Terminal Complex | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | 30047 | 32239 | 2012-07-18 | 2015-01-12 | 2014-03-31 | 2015-01-12 | 72 | 674
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility | 2011-12-30 | 2012-04-28 | Pacific West Builders | 9491 | 9434 | 2012-05-14 | 2014-08-15 | 2013-12-15 | 2014-09-30 | 93 | -2100
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW091002 | PRTC - Combat Communications Transmission Systems Facility | 2011-11-28 | 2012-04-27 | Guam Pacific International | 3960 | 3960 | 2012-05-14 | 2014-01-08 | 2013-11-02 | 2014-01-08 | 100 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | GU | GUAM | ANDERSEN AIR FORCE BASE | SAKW101001 | PRTC - Combat Communications Combat Support Facility | 2011-11-28 | 2012-04-27 | Guam Pacific International | 6212 | 6205 | 2012-05-14 | 2014-01-08 | 2013-11-02 | 2014-01-08 | 100 | -1900
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | ITA | ITALY | AVIANO AIR BASE | ASHE163000 | Child Development Center Addition | 2012-06-06 | 2012-09-30 | Collodetto Angelo Costruzioni | 890 | 910 | 2012-09-30 | 2014-08-08 | 2013-12-29 | 2014-07-17 | 80 | 1900
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | KOR | KOREA | OSAN AIR BASE | SMYU123002 | Dormitory (156 RM) | 2011-09-05 | 2012-03-13 | Seohee Construction Co., Ltd. | 14839 | 15501 | 2012-03-14 | 2014-10-07 | 2014-04-30 | 2014-08-08 | 97 | -5956
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | LA | LOUISIANA | BARKSDALE AIR FORCE BASE | AWUB105002 | Mission Support Group Complex | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | 17998 | 18552 | 2012-03-26 | 2014-08-15 | 2013-06-17 | 2014-08-15 | 94 | -3184
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG071005 | WSA Security Control Facility | 2011-11-23 | 2012-02-27 | Carlson Constructors | 4173 | 4300 | 2012-03-16 | 2014-08-15 | 2013-09-06 | 2014-08-15 | 96 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG111005 | Force Support Squadron Facility | 2012-06-01 | 2012-08-23 | Titan Construction Organizatio | 5388 | 7513 | 2012-09-07 | 2013-09-30 | 2013-09-09 | 2014-05-14 | 99 | 7966
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NE | NEBRASKA | OFFUTT AIR FORCE BASE | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | 102754 | 100246 | 2012-09-11 | 2017-01-17 | 2016-02-15 | 2016-09-12 | 22 | 37000
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103001 | F-35A AGE Facility | 2011-11-17 | 2012-06-01 | R.L. Reed, Inc. | 11097 | 11304 | 2012-06-19 | 2014-01-17 | 2013-07-15 | 2014-01-17 | 100 | -8490
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103003 | Communications Network Control Center | 2011-11-17 | 2012-04-24 | A4 Construction | 9327 | 9526 | 2012-05-22 | 2014-05-01 | 2013-03-15 | 2014-08-15 | 95 | -800
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103010 | F-35 Add/Alter Engine Shop | 2011-11-17 | 2012-05-24 | Au Authum KI, Inc | 1867 | 1867 | 2012-08-03 | 2014-11-21 | 2013-06-15 | 2014-11-21 | 73 | -572
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ123001 | Dormitory (96 RM) | 2012-06-13 | 2012-08-31 | MACNAK Korte | 12463 | 12589 | 2012-09-26 | 2014-03-07 | 2013-07-31 | 2014-01-10 | 99 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ133001 | ADAL Wastewater Treatment Plant | 2012-04-26 | 2012-07-11 | KEAR Civil Corporation | 7787 | 8142 | 2012-09-11 | 2014-02-10 | 2013-12-31 | 2014-02-10 | 100 | 1083
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD013003 | Child Development Center | 2012-05-18 | 2012-08-17 | Turner Atlantic Construction | 9844 | 9932 | 2012-11-08 | 2014-06-13 | 2012-06-15 | 2014-08-12 | 85 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD083007 | Parallel Taxiway, Rwy 07/25 | 2012-03-15 | 2012-06-08 | Mesa Verde Enterprises, Inc. | 6349 | 6611 | 2012-07-02 | 2014-03-07 | 2013-04-05 | 2014-03-07 | 100 | -700
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113005 | F-16 Academic Training Facility | 2012-02-03 | 2012-06-13 | White Sands Construction | 4990 | 5106 | 2012-07-09 | 2014-05-01 | 2013-07-12 | 2014-04-09 | 100 | 18
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113010 | F-16 Sead Training Facility | 2012-02-03 | 2012-06-13 | White Sands Construction | 3614 | 3695 | 2012-07-09 | 2014-03-01 | 2013-02-04 | 2014-04-09 | 100 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV093108 | AFNWC Sustainment Center | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | 21110 | 21507 | 2012-07-09 | 2014-12-06 | 2014-08-08 | 2014-10-07 | 85 | -1100
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | NC | NORTH CAROLINA | POPE AIR FORCE BASE | TMKH083003 | C-130 Flight Simulator | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | 4630 | 4712 | 2012-07-24 | 2014-12-29 | 2014-05-12 | 2014-12-29 | 75 | 186
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092001 | Dormitory (168 RM) | 2011-11-15 | 2012-02-14 | Graham Construction | 17775 | 17668 | 2012-03-21 | 2013-10-04 | 2013-08-08 | 2014-02-05 | 100 | -2049
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092010 | B-52 3-Bay Conventional Munitions Mtc Facility | 2012-01-24 | 2012-05-03 | Creative Times, Inc. | 10490 | 10839 | 2012-05-31 | 2014-03-31 | 2013-08-01 | 2014-06-30 | 100 | -18
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | 32123 | 33378 | 2012-05-22 | 2014-11-14 | 2014-02-11 | 2014-11-14 | 80 | 1813
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | TX | TEXAS | JOINT BASE FT SAM HOUSTON | MPLS11473JB | Advance Individual Trainee (AIT) Barracks (300 RM) | 2011-12-15 | 2012-03-30 | Hensel-Phelps Constr. Co. | 34889 | 34981 | 2012-07-20 | 2013-12-18 | 2014-08-05 | 2013-12-18 | 99 | -6900
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R4 | BMT Recruit Dormitory, Phase IV | 2011-12-16 | 2012-07-17 | LB-SpawGlass Contractors, Inc. | 50529 | 51562 | 2012-11-26 | 2015-03-26 | 2013-10-01 | 2015-01-11 | 44 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM123011R | F-22 System Support Facility | 2011-12-09 | 2012-06-05 | Creative Times Inc | 9598 | 9579 | 2012-07-24 | 2014-05-02 | 2013-12-05 | 2014-04-28 | 100 | -5555
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | WACC120007 | AIT Barracks Complex, Ph 2 | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | 33915 | 34106 | 2012-10-12 | 2014-10-07 | 2014-04-01 | 2014-10-07 | 90 | -10112
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ860009 | Wing Headquarters | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | 11957 | 12236 | 2012-05-21 | 2014-03-07 | 2014-01-15 | 2014-09-25 | 96 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ920012P2 | SERE Force Support Complex, Phase 2 | 2011-11-21 | 2012-07-05 | Total Site Services/Garco | 11724 | 12195 | 2012-07-20 | 2014-04-22 | 2014-05-20 | 2014-08-15 | 92 | -700
2014-07-31 | 2014-08-04 | 2012 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | 17707 | 17707 | 2013-06-04 | 2015-11-11 | 2014-03-01 | 2015-11-20 | 48 | 15000
2014-07-31 | 2014-08-04 | 2012 | Air Force active | MFH improvement | JPN | JAPAN | MISAWA AIR BASE | QKKA124002 | Improve MFH Infrastructure, Phase 1 | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | 19550 | 20009 | 2012-06-11 | 2014-11-13 | 2014-11-13 | 2014-11-13 | 89 | -78
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | AZ | ARIZONA | DAVIS-MONTHAN AIR FORCE BASE | FBNV133500 | T-10 Engine Test Cell (AMARG) | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | 1795 | 1795 | 2014-07-30 | 2015-05-04 | 2013-07-29 | 2015-05-04 | 1 | 1997
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU123005 | PL-1 Entry Control Facility | 2013-01-31 | 2013-04-04 | Hartland/Mass JV | 1125 | 1125 | 2013-04-22 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 65 | 1716
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ110047 | ADAL Corrosion Control Hangar (Bldg 89) | 2012-06-25 | 2012-11-06 | GSC Construction, Inc. | 1831 | 1946 | 2012-11-19 | 2014-02-28 | 2013-10-20 | 2014-02-28 | 100 | 2094
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ110048 | ADAL Corrosion Control Hangar (Bldg 54) | 2012-06-25 | 2012-11-06 | GSC Construction, Inc. | 1819 | 1819 | 2012-11-19 | 2014-03-23 | 2013-12-22 | 2014-03-23 | 100 | 1960
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | DEU | GERMANY | RAMSTEIN AIR BASE | TYFR126174 | Alter Air Operations Center | 2013-06-22 | 2013-09-25 | URS Group, Inc. | 1517 | 1517 | 2014-02-10 | 2014-07-03 | 2014-07-07 | 2014-07-03 | 100 | 1665
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | IN | INDIANA | GRISSOM AIR RESERVE BASE | CTGB102040 | Addition to BOWST Simulator | 2012-04-23 | 2012-08-03 | ITSI | 1031 | 1031 | 2012-08-06 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 35 | 1031
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | NJ | NEW JERSEY | MCGUIRE AIR FORCE BASE | PTFL106001 | Construct Covered Storage | 2012-06-22 | 2012-09-10 | Complete Technical Inc | 1295 | 1295 | 2012-06-26 | 2013-12-30 | 2013-12-30 | 2013-12-30 | 95 | 1295
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF123101 | Addition to High Fidelity Trainer | 2012-07-16 | 2012-09-11 | Ainsworth-Benning of Wyoming, | 1639 | 1639 | 2013-05-20 | 2013-10-18 | 2013-10-20 | 2013-10-20 | 1 | 1639
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | OK | OKLAHOMA | ALTUS AIR FORCE BASE | AGGN123002P | Communications Network Control Center Consolidation | 2013-03-22 | 2013-12-23 | Kothane Enterprises | 1619 | 1619 | 2014-03-10 | 2014-12-19 | 2014-03-31 | 2014-12-19 | 40 | 1663
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113026 | C-130 Aircraft Maintenance Unit | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | 1512 | 1512 | 2013-09-12 | 2015-04-07 | 2014-04-09 | 2015-04-07 | 23 | 1698
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113027 | Air Defense Artillery Maintenance Facility | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | 1265 | 1265 | 2013-08-28 | 2015-07-24 | 2014-04-09 | 2015-06-19 | 21 | 1421
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113032 | Precision Measurement Equipment Laboratory | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | 1404 | 1409 | 2013-08-28 | 2015-07-24 | 2014-04-09 | 2015-07-24 | 21 | 1577
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | QAT | QATAR | AL UDEID AB | ALUA113034 | AFOSI Regional And Local Facility | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | 1215 | 1215 | 2013-08-28 | 2015-07-24 | 2014-04-09 | 2015-02-19 | 21 | 1364
2014-07-31 | 2014-08-04 | 2012 | Air Force active | Minor construction | UT | UTAH | HILL AIR FORCE BASE | KRSM123015 | Construct Hayman Type Igloo | 2012-10-15 | 2013-01-15 | Hal Hays Construction, Inc. | 1055 | 1062 | 2013-02-04 | 2014-06-06 | 2014-04-28 | 2014-08-05 | 99 | 1190
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | CA | CALIFORNIA | BEALE AIR FORCE BASE | BAEY029154 | Wing Operations and Training Facility | 2012-07-27 | 2012-09-26 | SM Construction | 4960 | 5663 | 2012-12-03 | 2014-06-16 | 2013-12-03 | 2014-06-16 | 100 | 333
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | CA | CALIFORNIA | MOFFETT FIELD (NASA), SAN JOSE, (ANG) | QMSN019029 | Replace Pararescue Training Facility | 2012-08-05 | 2012-09-26 | Flintco Construction | 25161 | 27728 | 2013-01-10 | 2014-10-28 | 2014-04-10 | 2014-10-28 | 84 | 1418
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069212 | TFI - F-22 Flight Simulator Facility | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | 18842 | 21663 | 2012-06-17 | 2014-08-15 | 2014-06-07 | 2014-08-15 | 90 | 1863
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069213 | TFI - F-22 Weapons Load Crew Training Facility | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | 6473 | 7916 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 86 | 953
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | 9682 | 10875 | 2012-08-08 | 2013-11-18 | 2013-08-08 | 2013-11-18 | 70 | 1199
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron | 2013-03-04 | 2013-09-12 | Nan, Inc | 2000 | 2000 | 2013-09-30 | 2015-03-29 | 2015-03-29 | 2015-03-29 | 70 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities | 2013-05-08 | 2013-08-29 | Maron Construction Co. | 7919 | 8325 | 2013-09-24 | 2015-05-29 | 2013-09-28 | 2015-06-12 | 35 | 1061
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Major construction | OH | OHIO | SPRINGFIELD-BECKLEY MUNICIPAL AIRPORT | WAAR109001 | Alter Predator Operations Center Facility | 2012-08-17 | 2012-09-26 | UTS-DAG Construction Co., LLC | 5296 | 7090 | 2012-12-05 | 2013-10-31 | 2013-11-01 | 2014-06-15 | 99 | 25
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Minor construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB121354 | Construct Aerospace Support Equipment Storage Facility | 2013-07-31 | 2013-09-27 | H. Watt & Scott | 1088 | 1088 | 2013-10-02 | 2014-08-24 | 2014-03-01 | 2014-08-24 | 45 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Minor construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU129062 | Vehicle Maintenance Addition | 2012-05-24 | 2012-08-17 | Tyler Construction Group, Inc. | 1500 | 1500 | 2012-08-17 | 2013-09-30 | 2013-02-13 | 2014-07-31 | 99 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Minor construction | ME | MAINE | BANGOR INTERNATIONAL AIRPORT | FKNN049094 | Pavements and Grounds Facility | 2012-05-16 | 2012-09-12 | Cornerstone Construction | 1277 | 1329 | 2012-09-19 | 2013-11-25 | 2013-03-18 | 2014-07-31 | 99 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Minor construction | MA | MASSACHUSETTS | BARNES MUNICIPAL AIRPORT | AXQD119004 | Add to and Alter Survival Equipment Shop | 2013-04-10 | 2013-07-12 | Cornerstone Construction Svs | 1190 | 1246 | 2013-07-16 | 2014-05-23 | 2014-02-07 | 2014-05-30 | 95 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Minor construction | MN | MINNESOTA | DULUTH INTERNATIONAL AIRPORT | FMKM099063 | Munitions Storage Igloos | 2012-08-29 | 2012-09-26 | Max Gray Construction, INC. | 1798 | 1880 | 2012-11-13 | 2013-11-18 | 2013-03-13 | 2013-11-18 | 100 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Minor construction | OH | OHIO | SPRINGFIELD-BECKLEY MUNICIPAL AIRPORT | WAAR129078 | Relocate Main Gate | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | 1713 | 1884 | 2013-08-27 | 2014-05-22 | 2014-03-12 | 2014-05-22 | 84 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force NG | Minor construction | OR | OREGON | KLAMATH FALLS AIRPORT-KINGSLEY FIELD | KJAQ119031 | Addition Squadron Operations Facility | 2013-10-08 | 2014-01-29 | Anthem Builders, Inc | 1678 | 1765 | 2014-03-12 | 2014-12-12 | 2014-11-10 | 2014-12-19 | 14 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force res | Major construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG020143 | Construct New Airfield Control Tower, B1295 & Base Op'S B395 | 2012-03-16 | 2012-07-26 | Flintco, LLC. | 16915 | 17317 | 2012-08-22 | 2014-06-23 | 2013-04-23 | 2015-01-22 | 98 | 2000
2014-07-31 | 2014-08-04 | 2012 | Air Force res | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG111420 | 442: Construct LRS Facility | 2012-08-09 | 2012-09-26 | J & S Construction Co, Inc., Cookeville, TN | 3507 | 3526 | 2012-12-19 | 2014-07-18 | 2013-12-20 | 2014-07-18 | 100 | 3840
2014-07-31 | 2014-08-04 | 2012 | Air Force res | Major construction | SC | SOUTH CAROLINA | JOINT BASE CHARLESTON ISSOT NORTH CHARLESTON | DKFX079003 | Red Horse Readiness And Training Facility | 2012-02-08 | 2012-07-13 | IKHANA | 8149 | 9005 | 2012-07-13 | 2014-06-07 | 2013-03-01 | 2014-06-07 | 86 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force res | Minor construction | FL | FLORIDA | HURLBURT FIELD | FTEV111226B | Alter Building 90131 For 2 SOS | 2012-06-05 | 2012-09-13 | HCG, LLC | 926 | 1010 | 2012-10-22 | 2013-11-25 | 2013-04-16 | 2014-02-28 | 100 | 1016
2014-07-31 | 2014-08-04 | 2012 | Air Force res | Minor construction | FL | FLORIDA | HURLBURT FIELD | FTEV111226B | Alter Building 90131 For 2 SOS | 2012-06-05 | 2012-09-13 | HCG.LLC | 1 | 1 | 2012-10-22 | 2013-11-25 | 2013-04-16 | 2014-02-28 | 100 | 0
2014-07-31 | 2014-08-04 | 2012 | Air Force res | Minor construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE088144 | 931 ARG Medical Administration | 2013-04-29 | 2013-09-05 | Zieson Construction Co. | 1800 | 1870 | 2013-09-18 | 2014-07-25 | 2014-04-01 | 2014-07-25 | 80 | 2000
2014-07-31 | 2014-08-04 | 2012 | Air Force res | Minor construction | UT | UTAH | HILL AIR FORCE BASE | KRSM099001 | Fire Station #4 Annex | 2013-06-11 | 2013-09-25 | Grand Enterprises, LLC | 1322 | 1366 | 2013-10-11 | 2014-07-21 | 2014-07-19 | 2014-08-26 | 88 | 1388
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK103006 | C-130J Fuel Systems Maintenance Hangar | 2012-11-15 | 2013-06-25 | The Ross Group | 20869 | 20869 | 2013-07-23 | 2015-08-22 | 2014-11-19 | 2015-07-23 | 20 | 0
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | CA | CALIFORNIA | BEALE AIR FORCE BASE | BAEY133001 | Civil Engineer Administration/Operations Facility | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | 15947 | 15947 | 2014-07-09 | 2016-05-30 | 2016-08-26 | 2016-03-30 | 2 | 17500
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair | 2013-01-09 | 2013-05-31 | Barlovento | 13299 | 13357 | 2013-08-21 | 2015-02-11 | 2014-07-20 | 2015-02-11 | 44 | 339
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | GA | GEORGIA | FT STEWART | ACC123184 | Air Support Operations Center | 2013-03-14 | 2013-09-24 | Better Built Construction Serv | 6458 | 6458 | 2013-11-07 | 2015-07-30 | 2014-05-01 | 2015-05-01 | 12 | 0
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | GA | GEORGIA | MOODY AIR FORCE BASE | QSEU103008 | HC-130J Simulator Facility | 2012-12-07 | 2013-06-28 | IBKI, Inc. Choctaw, MS | 7692 | 7692 | 2013-08-12 | 2014-12-24 | 2014-10-15 | 2015-01-15 | 62 | 370
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | GRL | GREENLAND | THULE AIR BASE | WWCX103032 | Dormitory (48 Pn) | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | 23032 | 23032 | 2013-08-08 | 2015-10-27 | 2015-07-29 | 2015-07-29 | 13 | 1485
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | NV | NEVADA | CREECH AIR FORCE BASE | LKTC133101 | RPA Mission Complex Physical Protection System | 2014-02-25 | 2014-07-24 | Cobblestone Construction | 10643 | 10643 | 2014-09-01 | 2015-09-01 | 2014-11-01 | 2015-09-01 | 1 | 12279
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD123004 | MQ-9 Maintenance Hangar | 2013-03-01 | 2013-06-17 | HEW-Phelps | 20620 | 20620 | 2013-07-15 | 2015-01-20 | 2014-11-28 | 2014-12-30 | 63 | -437
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092011 | B-52 Add/Alter Munitions Age Facility | 2012-11-19 | 2013-05-31 | Rolac Contracting, Inc. | 4377 | 4256 | 2013-06-19 | 2014-12-11 | 2014-08-21 | 2014-12-11 | 20 | 289
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083008 | Dormitory (96 Rm) | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | 17170 | 17170 | 2013-06-11 | 2015-06-25 | 2014-12-25 | 2015-06-25 | 18 | 788
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM103012 | F-35 Adal Hangar 45W/AMU | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | 6781 | 6899 | 2014-01-27 | 2015-07-21 | 2012-10-29 | 2015-08-15 | 6 | 182
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM103030 | F-35A Modular Storage Magazines | 2012-08-08 | 2013-12-17 | Zumwalt Construction, Inc. | 2028 | 2028 | 2014-01-27 | 2015-10-25 | 2012-10-29 | 2015-10-25 | 6 | 0
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM113028 | F-35 Adal Building 118 For Flight Simulator | 2012-08-08 | 2013-12-17 | Creative Times, Inc. (CTI) | 3879 | 3871 | 2014-01-29 | 2015-03-30 | 2012-10-29 | 2015-04-30 | 4 | 255
2014-07-31 | 2014-08-04 | 2013 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | 14698 | 14788 | 2013-08-29 | 2015-12-01 | 2015-03-01 | 2015-12-01 | 5 | 20489
2014-07-31 | 2014-08-04 | 2013 | Air Force active | MFH improvement | JPN | JAPAN | MISAWA AIR BASE | QKKA133001P2 | Improve Family Housing, Ph 2 | 2013-05-16 | 2013-09-30 | Nishimatsu Construction Co., Ltd | 13989 | 13746 | 2013-10-29 | 2015-05-22 | 2015-08-31 | 2015-05-22 | 30 | 13989
2014-07-31 | 2014-08-04 | 2013 | Air Force active | MFH improvement | JPN | JAPAN | MISAWA AIR BASE | QKKA134001 | Improve Mfh Infrastructure, Phase 2 | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | 15337 | 15284 | 2013-10-23 | 2015-08-31 | 2015-04-15 | 2015-08-31 | 20 | 15337
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Minor construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK113003 | C130J Propeller Repair Training Facility | 2013-03-11 | 2014-02-21 | HGL Construction | 727 | 727 | 2014-06-20 | 2015-02-23 | 2015-02-20 | 2015-02-20 | 1 | 763
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Minor construction | CO | COLORADO | USAF ACADEMY | XQPZ124002 | Const Perm ECP-Stad Blvd | 2013-08-23 | 2013-11-19 | JBI Construction | 845 | 838 | 2013-12-17 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 72 | 987
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Minor construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 | 2013-03-06 | 2013-05-23 | Southwind Construction | 1525 | 1525 | 2013-06-07 | 2015-10-17 | 2015-08-06 | 2015-08-06 | 46 | 1800
2014-07-31 | 2014-08-04 | 2013 | Air Force active | Minor construction | WA | WASHINGTON | MCCHORD AIR FORCE BASE | PQWY133001 | ADAL 22 STS Squad Ops, Bldg 304 | 2013-06-07 | 2013-09-19 | Cherokee Gen'l Corp, Federal Way, WA | 1645 | 1645 | 2013-10-20 | 2014-08-09 | 2014-08-16 | 2014-08-09 | 70 | 1834
2014-07-31 | 2014-08-04 | 2013 | Air Force NG | Major construction | CA | CALIFORNIA | FRESNO YOSEMITE INTERNATIONAL ANG | HAYW109006 | F-15 Conversion | 2013-08-23 | 2013-09-27 | RS Morris Construction | 3747 | 4075 | 2013-11-01 | 2015-01-20 | 2015-01-25 | 2015-01-20 | 24 | 1069
2014-07-31 | 2014-08-04 | 2013 | Air Force NG | Major construction | CA | CALIFORNIA | FRESNO YOSEMITE INTERNATIONAL ANG | HAYW109006 | F-15 Conversion | 2013-08-23 | 2013-09-30 | RS Morris Cosntruction | 2402 | 2594 | 2013-11-01 | 2015-06-23 | 2015-01-25 | 2015-06-23 | 24 | 0
2014-07-31 | 2014-08-04 | 2013 | Air Force NG | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD119001 | TFI - F-22 Combat Apron Addition | 2013-03-04 | 2013-09-12 | Nan Inc. | 4993 | 5615 | 2013-10-31 | 2015-04-24 | 2015-04-24 | 2015-04-24 | 22 | 1000
2014-07-31 | 2014-08-04 | 2013 | Air Force NG | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV119001 | Alter Target Intelligence Facility | 2013-05-22 | 2013-10-10 | K.L. HOUSE CONSTRUCTION CO. | 4569 | 5074 | 2014-01-27 | 2015-02-23 | 2015-01-27 | 2015-02-23 | 23 | 0
2014-07-31 | 2014-08-04 | 2013 | Air Force NG | Major construction | WY | WYOMING | CHEYENNE REGIONAL AIRPORT | DPEZ089017 | C-130 Flight Simulator Training Facility | 2013-08-28 | 2013-09-27 | Faith Enterprises | 5062 | 5294 | 2013-09-27 | 2015-03-23 | 2015-03-21 | 2015-03-21 | 16 | 650
2014-07-31 | 2014-08-04 | 2013 | Air Force NG | Minor construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP079016 | BCE pavements and Grounds Facility | 2013-12-23 | 2014-04-07 | Showalter Construction | 1220 | 1258 | 2014-06-01 | 2015-06-01 | 2015-03-03 | 2015-06-01 | 5 | 0
2014-07-31 | 2014-08-04 | 2013 | Air Force res | Major construction | NY | NEW YORK | NIAGARA FALLS IAP-AIR RESERVE STATION | RVKQ099095 | Flight Simulator Facility | 2013-12-16 | 2014-03-27 | SCMS, LLC | 5243 | 5243 | 2014-08-01 | 2015-11-30 | 2015-07-31 | 2015-11-30 | 1 | 1276
2014-07-31 | 2014-08-04 | 2013 | Air Force res | Minor construction | FL | FLORIDA | HOMESTEAD AIR RESERVE BASE | KYJM129022 | Add Simulator Bay, Building 191 | 2013-06-07 | 2013-09-23 | CCI | 1552 | 1552 | 2013-12-13 | 2014-09-13 | 2014-12-12 | 2014-12-12 | 40 | 1763
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093007 | Construct Addition, Field Training Facility, B936 | 2013-11-15 | 2014-03-28 | Candelaria Corp | 4700 | 4700 | 2014-09-05 | 2015-04-30 | 2014-07-07 | 2015-09-28 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) | 2013-11-22 | 2014-05-21 | Okland Construction Company | 15514 | 15514 | 2014-07-31 | 2016-05-31 | 2015-09-30 | 2016-03-31 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | GRL | GREENLAND | THULE AIR BASE | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility | 2014-02-12 | 2014-07-21 | Per Aarsleff | 39818 | 39818 | 2014-08-06 | 2016-09-14 | 2016-06-17 | 2016-06-17 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | HI | HAWAII | HICKAM AIR FORCE BASE | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 | 2013-11-18 | 2014-06-17 | SRB International LLC | 2699 | 2699 | 2014-07-17 | 2015-06-07 | 2014-08-29 | 2015-06-07 | 2 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | 63925 | 63925 | 2014-06-24 | 2016-02-05 | 2017-01-21 | 2016-02-05 | 3 | -10500
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | 8101 | 8101 | 2014-09-01 | 2015-09-02 | 2016-06-24 | 2016-06-24 | 1 | -2500
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE145137 | KC-46A Alter Miscellaneous Facilities | 2014-03-10 | 2014-06-27 | Red Cedar Enterprises, Inc | 839 | 839 | 2014-08-15 | 2015-03-16 | 2015-06-24 | 2015-03-16 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE145138 | KC-46A Alter Aircraft Parking Apron | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | 976 | 976 | 2014-07-31 | 2017-03-02 | 2016-06-24 | 2016-06-24 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE145142 | KC-46A 1-Bay Maintenance Hangar | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | 25200 | 25200 | 2014-09-19 | 2015-12-18 | 2016-05-27 | 2016-05-27 | 1 | -3000
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | KS | KANSAS | MCCONNELL AIR FORCE BASE | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | 53959 | 53959 | 2014-09-30 | 2017-03-02 | 2017-05-27 | 2017-05-27 | 1 | -19000
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | MD | MARYLAND | FORT GEORGE MEADE | PAYZ130011 | U.S. Cyber Command Joint Operations Center | 2012-09-11 | 2014-03-27 | Hensel Phelps | 57000 | 57000 | 2014-07-07 | 2017-04-13 | 2016-09-30 | 2017-04-13 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG111010 | WSA: Construct Two New MOP Igloos | 2013-12-13 | 2014-05-14 | Record Steel And Construction | 3818 | 3818 | 2014-08-11 | 2015-11-13 | 2015-11-13 | 2015-11-13 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF083002 | Dormitory | 2014-01-27 | 2014-06-04 | Macnac-Korte | 30381 | 30381 | 2015-03-15 | 2016-07-15 | 2015-10-01 | 2016-07-15 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103005 | F-35A ADAL AME Storage Facility | 2013-12-13 | 2014-07-24 | RCDS Contractors | 4830 | 4830 | 2014-08-15 | 2015-08-15 | 2015-08-15 | 2015-08-15 | 1 | 283
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103006 | F-35A Parts Store | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | 6974 | 6974 | 2015-01-15 | 2015-09-01 | 2015-09-01 | 2015-09-01 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar | 2013-12-16 | 2014-05-21 | TeeHee Straub | 8066 | 8066 | 2014-11-01 | 2015-09-01 | 2014-09-01 | 2015-09-01 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF113005 | RPA Weapons School | 2013-12-20 | 2014-06-11 | RSCI | 14923 | 14923 | 2015-02-15 | 2016-07-15 | 2015-08-01 | 2016-07-15 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073050 | Dormitory (144 Rm) | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | 19225 | 19225 | 2014-07-10 | 2015-07-10 | 2015-07-15 | 2015-07-15 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 | 2013-10-24 | 2014-07-24 | K.L. House Construction | 21286 | 21286 | 2014-08-18 | 2016-02-08 | 2016-02-08 | 2016-02-08 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092013 | B-52 Munitions Storage Igloos | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | 9540 | 9540 | 2014-07-15 | 2015-09-21 | 2014-10-01 | 2015-09-21 | 2 | 2000
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | OK | OKLAHOMA | ALTUS AIR FORCE BASE | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | 1164 | 1164 | 2014-07-24 | 2015-07-30 | 2015-11-12 | 2015-11-12 | 1 | 73
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | OK | OKLAHOMA | ALTUS AIR FORCE BASE | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | 7112 | 7112 | 2015-03-30 | 2016-01-06 | 2016-01-06 | 2016-01-06 | 1 | 378
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | OK | OKLAHOMA | ALTUS AIR FORCE BASE | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | 5645 | 5645 | 2014-06-23 | 2015-07-31 | 2015-08-28 | 2015-08-28 | 1 | 16
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | OK | OKLAHOMA | ALTUS AIR FORCE BASE | AGGN143004 | KC-46A FTU Ftc Simulator Facility Phase 1 | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | 11000 | 11000 | 2014-07-23 | 2015-07-06 | 2015-07-31 | 2015-07-31 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | TX | TEXAS | FT BLISS | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | 3265 | 3265 | 2014-05-15 | 2015-08-07 | 2015-06-09 | 2015-06-09 | 6 | 258
2014-07-31 | 2014-08-04 | 2014 | Air Force active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM103011 | F-35 ADAL Hangar 45E/AMU | 2013-07-22 | 2014-04-10 | CTI | 6587 | 6592 | 2014-04-22 | 2015-09-19 | 2012-12-06 | 2015-09-19 | 6 | 15021
2014-07-31 | 2014-08-04 | 2014 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ144287 | Improve MFH Infrastructure, Phase 3 | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd | 2473 | 2473 | 2014-10-07 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ144287 | Improve MFH Infrastructure, Phase 3 | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd | 4202 | 4202 | 2014-10-07 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force active | MFH improvement | JPN | JAPAN | KADENA AIR BASE | LXEZ144287 | Improve MFH Infrastructure, Phase 3 | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd | 6289 | 6289 | 2014-10-07 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 1 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force NG | Minor construction | SC | SOUTH CAROLINA | MCENTIRE JOINT NATIONAL GUARD BASE | PSTE129092 | Construct North Overrun | 2013-10-22 | 2014-02-11 | Carolina Siteworks | 1702 | 1791 | 2014-03-11 | 2014-12-24 | 2014-12-24 | 2014-12-31 | 45 | 0
2014-07-31 | 2014-08-05 | 2009 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2009-1 | Pentagon Athletic Club (PAC) Phase II | 2009-10-08 | 2009-12-10 | HSU | 4765 | 5748 | 2009-12-17 | 2011-08-14 | 2010-12-16 | 2011-09-14 | 100 | -401 |  |  | $.400.83K to SAL ($99K remaining)
2014-07-31 | 2014-08-05 | 2009 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2009-3 | Pentagon Emergency Response Center (PERC) | 2009-02-05 | 2009-09-21 | THE CHRISTMAN COMPANY | 12469 | 14967 | 2009-09-28 | 2011-12-12 | 2011-07-20 | 2012-05-11 | 100 | -683 |  |  | $683.49K to SAL
2014-07-31 | 2014-08-05 | 2009 | WHS | Major construction | PA | PENNSYLVANIA | RRMC | 2009-2 | Power Plant Modernization - Phase Two | 2009-01-01 | 2009-11-12 | Kiewit Federal Group, Inc. | 12300 | 13218 | 2009-12-01 | 2013-04-01 | 2011-10-26 | 2013-04-01 | 100 |  |  |  | PROJECT COMPLETE / CLOSED OUT
2014-07-31 | 2014-08-05 | 2010 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2010-1 | Upgrade Electrical System | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power | 23269 | 23269 | 2013-11-07 | 2015-02-05 | 2015-02-05 | 2015-02-05 | 2 | 4719 |  |  | PERC-$437, Fuel Storage Fac-$200, Secondary UPS-$300, FY11 P&D-$3,782
2014-07-31 | 2014-08-05 | 2010 | WHS | Major construction | PA | PENNSYLVANIA | RRMC | 2010-2 | Secondary UPS System | 2010-06-16 | 2010-09-27 | IRON BRIDGE CONSTRUCTION | 5192 | 7515 | 2010-09-27 | 2013-07-31 | 2012-02-29 | 2014-07-30 | 100
2014-07-31 | 2014-08-05 | 2011 | WHS | Major construction | PA | PENNSYLVANIA | RRMC | 2011-1 | Power Plant Modernization Phase 3 West Power Plant | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. | 43594 | 43594 | 2013-04-22 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 9 | -4001 |  |  | Project at 35% design, funds absconded by sequester
2014-07-31 | 2014-08-05 | 2011 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2011-2 | Metro Entrance Facility Visitor Screening Facility (MEF VSF) | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. | 5609 | 5609 | 2013-11-01 | 2015-06-01 | 2015-06-01 | 2015-06-01 | 0 | 0 |  |  | Contract Award 26 Sep 2013. NTP 1 Nov 2013. Design 8 months followed by 12 months construction. Contract duration 540 cds
2014-07-31 | 2014-08-05 | 2011 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2011-3 | Secure Access Lane (SAL) | 2011-08-08 | 2013-09-30 | IKHANA,LLC | 5454 | 5454 | 2013-11-01 | 2015-05-01 | 2015-05-01 | 2015-05-01 | 0 | 0 |  |  | Award Contract Base Bid Items 28 Sep 2013; All options, for DIACAP $31,093, Perimeter Fence and 3 Vehicle Gates $138,693 and Public Rest Room (OPA funded) $447,766 awarded; NTP estimated by 1 Feb 2013. 510 cds contract duration.
2014-07-31 | 2014-08-05 | 2012 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2012-1 | Pentagon Heliport Control Tower and Fire Station |  |  | TBD | [10 empty] | 2nd site analysis underway. Required due to cancellation of new heliport.
2014-07-31 | 2014-08-05 | 2012 | WHS | Major construction | VA | VIRGINIA | Pentagon | 2012-2 | Pentagon Memorial Pedestrian Plaza |  |  | TBD | [10 empty] | Design contract award 26SEP13. NTP 1 Nov13. Design 8 mos/Construct 12mos. Contract duration 540 cds
2014-07-31 | 2014-08-05 | 2009 | MDA | UMC | TUR | TURKEY | EUCOM Site | 638 | European Phased Adaptive Approach, Phase I Radar Site | 2011-09-15 | 2011-10-19 | EMTA INSAAT TAAHUT VE TICARET A.S. | 1885 | 1900 | 2011-10-26 | 2011-12-31 | 2011-12-31 | 2013-11-15 | 100 | 0
2014-07-31 | 2014-08-05 | 2009 | MDA | UMC | AK | ALASKA | Fort Greely | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | 1564 | 1207 | 2013-03-22 | 2013-06-30 | 2013-06-30 | 2013-07-03 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | MDA | UMC | AK | ALASKA | Fort Greely | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | 1564 | 243 | 2013-03-22 | 2013-06-30 | 2013-06-30 | 2013-07-03 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | MDA | UMC | MH | MARSHALL ISLANDS | USAG-Kwajalein Atoll, Meck Island | 655 | Missile Test Vehicle Storage Facility | 2014-03-24 | 2014-05-09 | TBD | 1832 | 1832 | 2014-06-17 | 2014-12-02 | 2014-12-02 | 2014-12-02 | 10 | 0
2014-07-31 | 2014-08-05 | 2010 | MDA | Major Construction | VA | VIRGINIA | NSWC Dahlgren | 609 | Aegis BMD Facility Expansion | 2010-03-23 | 2010-06-30 | Sauer Incorporated | 18813 | 18748 | 2010-07-15 | 2012-07-31 | 2012-10-31 | 2012-10-31 | 99 | -5700 |  |  | Reprogrammed to P&D
2014-07-31 | 2014-08-05 | 2010 | MDA | Major Construction | HI | HAWAII | PMRF | 627 | Aegis Ashore Missile Defense Test Complex - Clearing and Grubbing Only | 2011-06-30 | 2011-08-03 | TOMCO CORP. | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | MDA | Major Construction | HI | HAWAII | PMRF | 627 | Aegis Ashore Missile Defense Test Complex - Construction | 2012-01-19 | 2012-06-04 | URS GROUP, INC | 59616 | 68447 | 2012-07-04 | 2013-08-29 | 2013-09-12 | 2013-09-12 | 99 | 1902 |  |  | BTR from Ft Drum
2014-07-31 | 2014-08-05 | 2012 | MDA | Major Construction | AL | ALABAMA | Redstone Arsenal | 633 | Von Braun Complex Phase IV | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | 51330 | 54395 | 2012-07-10 | 2014-07-31 | 2014-10-31 | 2014-10-31 | 99 | 1100 |  |  | BTR from Ft Drum
2014-07-31 | 2014-08-05 | 2013 | MDA | Major Construction | NY | NEW YORK | Ft Drum | 639 | In-Flight Interceptor Data Terminal Complex | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | 12584 | 14041 | 2013-08-10 | 2014-11-30 | 2014-11-30 | 2014-11-30 | 76 | -4442 |  |  | BTR reprogramming
2014-07-31 | 2014-08-05 | 2013 | MDA | Major Construction | ROU | ROMANIA | Deveselu Base | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | 118300 | 81785 | 2013-07-31 | 2014-12-09 | 2015-08-01 | 2015-08-01 | 30 | 0
2014-07-31 | 2014-08-05 | 2014 | MDA | Major Construction | ROU | ROMANIA | Deveselu Base | 646 | Aegis Ashore Missile Defense System Complex, Incr #2 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | 118300 | 28946 | 2013-07-31 | 2014-12-09 | 2015-08-01 | 2015-08-01 | 30 | 0
2014-07-31 | 2014-08-05 | 2014 | MDA | Major Construction | AK | ALASKA | Clear AFS | 634 | BMDS Upgrade Early Warning Radar (UEWR) | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | 13300 | 13300 | 2014-07-07 | 2015-02-13 | 2017-05-31 | 2017-05-31 | 5 | 0
2014-07-31 | 2014-08-05 | 2014 | MDA | Major Construction | JPN | JAPAN | Kyoga Misaki | 648 | AN/TPY-2 Radar Site | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | 12991 | 12991 | 2014-05-27 | 2014-10-11 | 2015-01-09 | 2015-01-09 | 10 | 1300 |  |  | BTR from MEB, MF1; BTR from Ft Drum $700
2014-07-31 | 2014-08-05 | 2014 | MDA | Major Construction | AK | ALASKA | Fort Greely | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) | 2014-01-23 | 2014-05-16 | Watterson Construction Company | 42838 | 42838 | 2014-05-27 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 15 | -1300 |  |  | BTR reprogramming
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010154 | Multi Purpose Machine Gun Range | 2009-04-28 | 2009-05-05 | HDH General Contractors, Inc. | 2671000 | 1636116.62 | 2009-05-11 | 2011-11-21 | 2011-11-16 | 2011-11-16 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | CT | CONNECTICUT | Camp Rell | 090047 | Regional Training Institute | 2009-02-19 | 2009-02-19 | The Fusco Corporation Contract #: BI-Q-588 | 27526508 | 27526508 | 2009-05-04 | 2011-10-03 | 2011-09-06 | 2011-09-30 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | GA | GEORGIA | Marietta | 130109 | Armed Forces Reserve Center | 2009-09-09 | 2009-09-09 | New South Construction Company, Inc. Contract #: 41100-044-0000070579 | 36015000 | 27900485.75 | 2009-09-21 | 2011-11-01 | 2011-04-11 | 2013-09-24 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230070 | Regional Training Institute, PH 1 | 2009-04-08 | 2009-04-16 | Nickerson & O'Day, Inc. Contract #: 230070-D | 14313529.52 | 14313529.52 | 2009-05-18 | 2011-06-13 | 2011-06-13 | 2011-06-13 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | MD | MARYLAND | Edgewood | 240189 | Army Aviation Support Facility, Add/Alt | 2009-05-05 | 2009-09-28 | Tetra-Tech Facilities Construction, LLC Contract #: W912K6-09-C-0002 | 27603000 | 27193439.57 | 2010-03-01 | 2012-06-01 | 2010-09-27 | 2012-06-30 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Project has claim with ASBC and claim has not been finalized, schedule to go to trial in Oct 14
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Methuen | 250106 | Readiness Center, Add/Alt (ADRS) | 2009-06-03 | 2009-06-05 | JK Scanlan Company, Inc. | 19004000 | 11505953 | 2009-08-10 | 2011-04-01 | 2011-11-16 | 2011-11-16 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260212 | Infantry Squad Battle Course | 2009-08-19 | 2009-09-02 | The Garrison Company | 2116999.7 | 2116999.7 | 2009-09-07 | 2010-06-30 | 2010-05-18 | 2010-05-18 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270260 | Readiness Center | 2009-08-04 | 2009-08-07 | Holte/Graham, JV Contract #: W912LM-09-C-0005 | 13390000 | 12528763.58 | 2009-08-10 | 2011-12-01 | 2010-12-14 | 2013-05-31 | 99 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | NV | NEVADA | Elko | 320069 | Readiness Center | 2011-10-27 | 2012-06-01 | Nevada State Public Works Contract #: W9124X-11-2-2001 | 11246000 | 7762379.44 | 2012-06-11 | 2013-04-30 | 2013-07-12 | 2013-03-27 | 99 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Minor Construction (UMMC) | NV | NEVADA | North NV Military Depot (Carson City) | 320152 | Paint Booth | 2009-06-04 | 2009-09-01 | Nevada State Public Works | 1500000 | 1074962.56 | 2009-09-16 | 2012-05-24 | 2012-05-21 | 2012-05-21 | 100 | 0 |  |  | Congressionally Directed
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | NY | NEW YORK | Fort Drum | 360191 | Maneuver Area Training and Equipment Site, PH 3 | 2009-09-04 | 2009-09-30 | Beardsley Design Associates Contract #: DAHA30-00-0009 | 10879000 | 9544482.83 | 2010-03-10 | 2012-09-30 | 2011-03-09 | 2013-04-11 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Minor Construction (UMMC) | OH | OHIO | Newton Falls | 390270 | Ravenna TTB Utilities | 2009-12-15 | 2010-01-28 | Portage County Water Resources Department | 1600000 | 1600000 | 2011-11-01 | 2012-02-22 | 2012-01-30 | 2012-12-06 | 100 | 0
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | PA | PENNSYLVANIA | Honesdale | 420511 | Readiness Center, Add/Alt | 2011-08-31 | 2011-09-15 | Lobar Incorporated Contract #: DGS 961-20.1 | 6117000 | 5737844.6 | 2011-09-26 | 2013-08-15 | 2012-10-30 | 2014-12-31 | 99 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | RI | RHODE ISLAND | North Kingstown | 440039 | Army Aviation Support Facility (additional funds for FY08 project) | 2008-07-09 | 2008-09-25 | Bacon Construction Co., Inc. Contract #: W912LD-08-C-0036 | 4848000 | 4150000 | 2009-01-09 | 2012-01-06 | 2011-01-09 | 2013-07-31 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Rapid City | 460077 | Armed Forces Reserve Center | 2009-03-31 | 2009-04-17 | J Scull Construction Contract #: W912MM-04-2-2001 | 28762000 | 27821891.07 | 2010-04-05 | 2011-06-24 | 2011-11-14 | 2011-11-14 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 460132 | Barracks/Dining/Admin & Parking Complex, PH I | 2009-06-11 | 2009-06-24 | J Scull Construction Contract #: W912-MM-09-2-2001 | 12765000 | 11645594.24 | 2009-08-10 | 2011-03-02 | 2010-12-15 | 2010-12-15 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | TN | TENNESSEE | Tullahoma | 470043 | Readiness Center | 2009-09-16 | 2009-09-25 | Sain Construction Co. Contract #: W912L7-09-C-0008 | 8787000 | 7706138.13 | 2009-10-01 | 2011-09-15 | 2011-01-21 | 2011-07-05 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | UT | UTAH | Camp HG Williams | 490101 | Ammunition Supply Point | 2009-09-17 | 2009-09-18 | Creative Times Inc. | 13843000 | 12044859.22 | 2009-09-21 | 2011-07-30 | 2010-10-01 | 2010-10-01 | 100 | 2358000 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Minor Construction (UMMC) | VT | VERMONT | Colchester | 500072 | Readiness Center, Add/Alt | 2011-08-09 | 2011-08-11 | Stewart Construction Contract #: W912LN-08-D-0004 | 1862349 | 1862349 | 2011-09-12 | 2012-05-02 | 2012-06-18 | 2012-07-18 | 100 | 0 |  |  | (NGB 593)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | WA | WASHINGTON | Fort Lewis (Gray Field) | 530012 | Readiness Center | 2009-09-11 | 2009-09-11 | Wade Perrow Construction, LLC Contract #: W912K3-09-C-0001 | 30265000 | 24954481.35 | 2009-09-12 | 2011-07-28 | 2011-01-31 | 2011-01-31 | 100 | 0 |  |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Kingwood | 540105 | Joint Interagency Training Education Center, PH I | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company Contract #: DEFK10003 | 77500000 | 72199929.15 | 2009-10-01 | 2011-09-30 | 2011-09-28 | 2014-09-30 | 99 | 0 |  |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Generator work being completed
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540205 | Access Control Point | 2009-09-25 | 2009-09-25 | DanHill Construction Contract #: DEFK13007 | 3945000 | 3693718.77 | 2013-05-01 | 2013-12-16 | 2013-12-11 | 2/29/2014 | 100 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Formal Reprogramming $2.358M funds from FY09 project savings {PN: 490101}, PM Assigned
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540206 | Multi-Purpose Building, PH II | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. Contract #: DEFK10004 | 4755000 | 4624095.62 | 2010-02-01 | 2010-08-30 | 2010-08-26 | 2013-03-31 | 99 | 0 |  |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Minor Construction (UMMC) | WV | WEST VIRGINIA | Kenova | 540208 | Tri-State Armory Addition | 2009-04-24 | 2009-09-23 | Neighborgall Construction Company | 2000000 | 2000000 | 2009-10-01 | 2010-08-11 | 2010-07-16 | 2010-08-31 | 100 | 0 |  |  | Congressionally Directed, PM Assigned
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010279 | Urban Assault Course | 2010-09-06 | 2010-09-10 | Baggette Construction, Inc. Contract #: AC-10-C-0045-S | 2980000 | 2395741 | 2010-12-01 | 2011-10-11 | 2011-08-08 | 2011-08-08 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | AK | ALASKA | Fort Richardson | 020903 | Regional Training Institute, Add/Alt | 2010-05-14 | 2010-09-03 | H. Watt & Scott, Inc. Contract #: W91ZRU-05-D-0002-0032 | 1754913 | 1754913 | 2010-09-20 | 2011-09-28 | 2011-09-30 | 2011-09-28 | 100 | 0 |  |  | (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | AZ | ARIZONA | Camp Navajo | 040227 | Combat Pistol Qualification Course | 2010-06-14 | 2010-06-15 | Norquay Construction Contract #: M10-0015 | 2964000 | 1867492.4 | 2010-06-28 | 2011-07-15 | 2010-12-31 | 2010-12-31 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | CA | CALIFORNIA | Los Alamitos | 060115 | Readiness Center, PH 1 | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. Contract #: W912LA-10-C-0009 | 22705602.11 | 22705602.11 | 2010-11-15 | 2013-10-07 | 2012-02-06 | 2014-08-31 | 37 | 2900000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505,000.00)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | GA | GEORGIA | Fort Benning | 130077 | Readiness Center | 2010-01-28 | 2010-02-04 | USACOE Louisville District Contract #: 130077A | 8622378.6 | 8622378.6 | 2010-02-22 | 2012-01-31 | 2011-09-14 | 2012-01-31 | 100 | 3631000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($8,400,000.00) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | GA | GEORGIA | Hunter AAF | 130112 | Readiness Center | 2010-09-29 | 2010-09-29 | Choice Concrete Construction Contract #: W912JM-10-D-00150002 | 7696026.5 | 7696026.5 | 2010-10-06 | 2012-08-01 | 2012-03-20 | 2012-07-31 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | GU | GUAM | Barrigada | 140300 | Readiness Center | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific Contract #: N40192-10-C-1335 | 20797256 | 20797256 | 2010-05-03 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 95 | 3000000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537,000.00)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | ID | IDAHO | Gowen Field | 160120 | Combined Arms Collective Training Facility | 2010-04-27 | 2010-05-25 | Performance Systems Inc. Contract #: W912J7-10-C-0001 | 7752891.63 | 7752891.63 | 2010-06-21 | 2012-04-13 | 2011-10-04 | 2013-09-11 | 100 | 7000000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($7,824,080.00) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | ID | IDAHO | Orchard Range TS, Boise | 160127 | Fixed Tactical Internet Infrastructure | 2011-07-20 | 2011-09-15 | USPFO - Idaho Contract #: W912J7-11-C-0004 | 1380231.13 | 1380231.13 | 2011-10-26 | 2012-10-02 | 2012-08-17 | 2012-10-02 | 100 | 0 |  |  | (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | IL | ILLINOIS | Milan | 170611 | Readiness Center, Add/Alt | 2010-09-17 | 2010-09-22 | Capital Development Board Contract #: W91SMC-10-2-2001-100 | 5560000 | 4319159.15 | 2010-10-18 | 2012-03-31 | 2011-09-14 | 2011-09-14 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | IN | INDIANA | Muscatatuck | 180145 | Combined Arms Collective Training Facility, PH Ib | 2010-04-20 | 2010-04-22 | McKellar Corporation Contract #: W912L9-10-C-0004 | 7507610.33 | 7507610.33 | 2010-08-12 | 2011-07-01 | 2010-09-20 | 2011-07-01 | 100 | 1500000 |  |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Iowa Falls | 190139 | Readiness Center, Add/Alt | 2010-02-18 | 2010-07-20 | Larson Construction company Contract #: C921I3023 | 1794105.78 | 1794105.78 | 2010-08-02 | 2011-10-10 | 2011-08-30 | 2011-10-10 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Davenport | 190151 | Army Aviation Support Facility, Add/Alt | 2010-02-18 | 2010-09-20 | Russell Construction Co., Inc. Contract #: C954Z3070 | 1937949.47 | 1937949.47 | 2010-09-27 | 2012-01-17 | 2011-11-30 | 2012-01-17 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | IA | IOWA | Johnston (Camp Dodge) | 190154 | FEH Associates, Inc. (USPFO) | 2010-08-10 | 2010-08-16 | SKE International, Inc. Contract #: C951SI093 | 3981146.73 | 3981146.73 | 2010-09-06 | 2011-11-15 | 2011-08-15 | 2011-11-15 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Fairfield | 190155 | Field Maintenance Shop, Add/Alt | 2010-02-18 | 2010-09-20 | Jean C. Wiley & Sons, Inc. Contract #: C954Y2071 | 1948912.25 | 1948912.25 | 2010-10-04 | 2011-10-26 | 2011-09-06 | 2011-10-26 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | IA | IOWA | Camp Dodge | 190157 | Motor Vehicle Storage Buildings, Freedom Center | 2010-02-18 | 2010-07-20 | Septagon Construction Co. Contract #: C95470065 | 1267240.25 | 1267240.25 | 2010-07-29 | 2011-08-04 | 2011-05-01 | 2012-02-08 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | KS | KANSAS | Salina | 200103 | Taxiway Alterations, ARNG AASF | 2010-08-24 | 2010-08-25 | Pavers Inc. Contract #: CONST | 1988414.86 | 1988414.86 | 2010-09-01 | 2012-02-10 | 2011-07-18 | 2012-02-10 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | KY | KENTUCKY | Owensboro | 210291 | Readiness Center | 2010-06-07 | 2010-08-16 | A & K Construction Company, Inc. Contract #: CT2 785 1000000319 1 | 10483000 | 10023655.5 | 2010-08-23 | 2012-04-14 | 2011-08-28 | 2011-08-28 | 100 | 0 |  |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | KY | KENTUCKY | London | 210292 | Aviation Operations Facility, Add/Alt, PH IV | 2010-09-07 | 2010-09-24 | Septagon Construction Co. Contract #: CTC 785 1 100000093 1 | 1682396.41 | 1682396.41 | 2010-11-08 | 2012-02-15 | 2011-11-25 | 2012-02-15 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | ME | MAINE | Waterville | 230806 | CST Ready Bay Addition | 2011-07-01 | 2011-09-07 | Blaine Casey Building Contractor, Inc. Contract #: 230806-D | 1121188.63 | 1121188.63 | 2011-09-25 | 2012-09-28 | 2012-08-10 | 2012-09-28 | 100 | 0 |  |  | (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230114 | Regional Training Institute, PH II | 2010-08-11 | 2010-09-21 | Nickerson & O'Day, Inc. Contract #: 230070-D | 15464000 | 14398817.6 | 2010-09-21 | 2012-08-17 | 2012-07-21 | 2014-01-31 | 100 | 0 |  |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Hanscom AFB | 250087 | Armed Forces Reserve Center (JFHQ) | 2010-06-07 | 2010-06-25 | CTA Construction Contract #: CTA Base Bid | 27595000 | 26247100.71 | 2010-07-12 | 2012-01-15 | 2011-10-19 | 2014-04-30 | 100 | 2000000 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | MI | MICHIGAN | Fort Custer (Augusta) | 260213 | Organizational Maintenance Shop (ADRS) | 2010-08-04 | 2010-09-22 | LD Dosca Associates, Inc. Contract #: W912JB-09-D-2014 | 7722000 | 7419375.18 | 2010-10-01 | 2012-03-01 | 2011-10-18 | 2011-10-18 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | MI | MICHIGAN | Camp Grayling | 260232 | Dining Facility | 2010-07-09 | 2010-09-24 | Ripman Construction Co., Inc. Contract #: Y10342 | 1998000 | 1991296.11 | 2010-10-01 | 2011-06-27 | 2011-09-30 | 2011-12-01 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270252 | Urban Assault Course | 2011-07-11 | 2011-08-18 | Saginaw Contracting, Inc. Contract #: W912LM-10-D-0016 | 1693000 | 1193323.74 | 2011-08-22 | 2012-07-18 | 2013-03-18 | 2013-07-18 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270261 | Readiness Center, PH 2 | 2010-08-30 | 2010-09-07 | MAVCON Contract #: W912LM-10-C-0003 | 3183584 | 2855434.49 | 2010-09-27 | 2012-05-01 | 2011-07-18 | 2013-05-31 | 100 | 3500000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($3,183,584.00)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | MN | MINNESOTA | St. Paul | 270263 | CST, Add/Alt | 2011-08-09 | 2011-08-19 | LS Black Constructors Contract #: W912LM-10-D-0004 | 1954000 | 1897458.9 | 2011-09-12 | 2012-11-20 | 2012-08-24 | 2013-12-20 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | MS | MISSISSIPPI | Monticello | 280308 | Readiness Center | 2010-09-22 | 2010-09-23 | Mac's Construction Co., Inc. Contract #: NGB22-10-C-0008-S | 8008358 | 8008358 | 2010-11-03 | 2013-01-08 | 2012-01-06 | 2013-01-08 | 100 | 6000000 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)/2853 Notification ($8,383,350.00) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280352 | Combined Arms Collective Training Facility, Add/Alt | 2010-04-09 | 2010-04-22 | B. W. Sullivan Building Contractor, Inc. Contract #: NGB22-10-C-0001-S | 7020324 | 7020324 | 2010-05-17 | 2012-02-29 | 2010-08-23 | 2012-02-29 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($7,260,000.00) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | MO | MISSOURI | Boonville | 290213 | Readiness Center, PH 2 | 2010-04-16 | 2010-04-22 | SIRCAL Contracting Contract #: NGB23-10-C00001 | 1011411.5 | 1011411.5 | 2010-05-01 | 2011-02-11 | 2010-10-18 | 2011-02-11 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)(NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | MT | MONTANA | Fort Harrison | 300202 | Troop Medical Clinic, Add/Alt | 2010-04-23 | 2010-09-13 | R&R Taylor Construction Contract #: 300202 | 1657794.99 | 1657794.99 | 2010-10-13 | 2011-09-01 | 2011-06-30 | 2010-10-26 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | NE | NEBRASKA | Lincoln | 310076 | Armed Forces Reserve Center (JFHQ) | 2010-01-26 | 2010-02-16 | Hausman Construction, Inc. Contract #: 310076 | 21804833.39 | 21804833.39 | 2010-04-01 | 2012-09-17 | 2011-09-30 | 2014-05-15 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | NE | NEBRASKA | Mead Training Site | 310122 | Water Supply & Distribution System | 2010-08-23 | 2010-08-25 | Rutjens Construction, Inc. Contract #: RUTJENS-Constr01 | 1842956.65 | 1842956.65 | 2010-09-13 | 2011-12-01 | 2011-07-25 | 2012-03-05 | 100 | 0 |  |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | NV | NEVADA | North Las Vegas | 320143 | Readiness Center | 2010-09-27 | 2010-09-27 | The Penta Building Group | 19910357.28 | 19910357.28 | 2010-10-25 | 2013-05-01 | 2012-01-23 | 2013-04-19 | 99 | 3112000 |  |  | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | NV | NEVADA | Carson City | 320197 | Renewable Energy Sustainable Projects | 2010-09-21 | 2010-09-24 | RHP Mechanical Systems (Contractor) | 1997000 | 1917039 | 2010-10-04 | 2011-10-26 | 2011-04-04 | 2011-04-04 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | NM | NEW MEXICO | Santa Fe | 350043 | Army Aviation Support Facility | 2010-06-29 | 2010-07-02 | PCL Construction Services Inc. Contract #: W912PP-10-C-0022 | 35577000 | 31834806.4 | 2010-09-13 | 2012-03-20 | 2011-09-14 | 2011-09-14 | 100 | 3300000 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | NC | NORTH CAROLINA | East Flat Rock | 370896 | Readiness Center, Add/Alt | 2010-09-07 | 2010-09-10 | Architectural Design Studio | 2501000 | 2033369.25 | 2010-09-27 | 2011-10-13 | 2011-09-30 | 2011-10-17 | 99 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 370897 | Tactical UAS Support Facility | 2010-09-10 | 2010-09-27 | J.M. Thompson Co | 2736644.8 | 2736644.8 | 2010-10-09 | 2012-03-02 | 2012-06-08 | 2011-08-15 | 95 | 2486000 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)/2853 Notification ($2,589,623.00)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Bismarck | 380118 | Raymond J. Bohn Readiness Center, Addition | 2010-04-01 | 2010-09-27 | Associated Builders, Inc. Contract #: AGND10-70 | 1198567.21 | 1198567.21 | 2010-10-20 | 2011-12-29 | 2011-12-31 | 2012-03-27 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | ND | NORTH DAKOTA | Camp Grafton | 380119 | Shoreline Stabilization | 2010-02-12 | 2010-02-10 | Ames Construction | 1747147.76 | 1747147.76 | 2010-03-15 | 2010-08-17 | 2011-08-30 | 2010-12-10 | 100 | 0 |  |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Camp Grafton, Devils Lake | 380120 | Dike Construction | 2010-07-26 | 2010-07-26 | Ames Construction Contract #: SER-3-020-(082)098 | 1943779.7 | 1943779.7 | 2010-11-01 | 2012-08-13 | 2012-08-20 | 2014-08-30 | 99 | 0 |  |  | NGB 593 will be completed once the Dept of Transportation asks for final payment
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | OH | OHIO | Beightler | 390261 | Joint Forces Headquarters (JOC), Addition | 2010-02-03 | 2010-08-05 | Elford, Inc. Contract #: ADJ100007-01-01 | 1839130.8 | 1839130.8 | 2010-09-01 | 2011-08-01 | 2011-08-01 | 2012-05-30 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | OH | OHIO | Ravenna | 390267 | Shoot House | 2009-12-14 | 2010-09-20 | USPFO - Ohio Contract #: W91364-10-C-0005 | 1946920.12 | 1946920.12 | 2010-10-01 | 2011-11-16 | 2011-10-25 | 2012-03-22 | 100 | 0 |  |  | Congressionally Directed (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | OR | OREGON | Polk County | 410120 | Readiness Center | 2010-09-14 | 2010-09-21 | Lease Crutcher Lewis Contract #: 410120D002 | 12093000 | 11892715.57 | 2010-10-08 | 2012-09-01 | 2012-12-01 | 2012-12-01 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | OR | OREGON | Clastop County (Warrenton) (Camp Rilea) | 410820 | Water Supply Company | 2010-09-10 | 2010-09-21 | Hoffman Construction Company Contract #: 410820D002 | 3369000 | 3367999.48 | 2010-10-01 | 2011-08-01 | 2011-10-02 | 2011-10-02 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | PA | PENNSYLVANIA | Fort Indiantown Gap | 420507 | CSMS Paint Stripping & Prep Shop | 2010-06-01 | 2010-08-27 | Arthur Funk & Sons, Inc. Contract #: W912KC-10-D-0009-0003 | 1587766.26 | 1587766.26 | 2010-10-01 | 2011-07-27 | 2011-06-22 | 2011-10-31 | 100 | 0 |  |  | (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | PR | PUERTO RICO | Camp Santiago | 436019 | Urban Assault Course | 2009-12-01 | 2010-09-29 | Remex Co. Contract #: W912LR-10-B-0001 | 1845996.46 | 1845996.46 | 2010-10-01 | 2011-10-03 | 2011-09-23 | 2011-09-23 | 100 | 0 |  |  | Congressionally Directed
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Eastover | 450252 | Army Aviation Support Facility, Add/Alt | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. | 14758680 | 14078418 | 2011-02-07 | 2013-04-15 | 2011-12-14 | 2013-05-01 | 99 | 11000000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,758,680.00)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Greenville | 450353 | Army Aviation Support Facility | 2010-09-23 | 2010-09-24 | Hendrick Construction Contract #: 4600114576 | 27935984 | 27303538 | 2010-11-17 | 2013-06-21 | 2012-08-10 | 2013-06-21 | 75 | 12100000 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,935,984.00)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 460141 | Joint Force HQ Readiness Center Supplemental | 2010-08-26 | 2010-09-03 | J. Scull Construction Services, Inc. Contract #: W912MM-09-2-2003 | 5705000 | 5257176.34 | 2010-09-27 | 2012-04-14 | 2012-04-14 | 2012-04-14 | 100 | 2500000 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)/2853 Notification ($5,705,000.00), Delays in getting LEED Certification, State holding funds from A-E for this. Tentative submission date is May 2014
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 461536 | Troop Medical Clinic, Add/Alt | 2010-09-01 | 2010-09-07 | J. Scull Construction Services, Inc. Contract #: W912MM-09-2-2002 | 1723490.87 | 1723490.87 | 2010-09-20 | 2011-05-23 | 2011-05-01 | 2012-05-14 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | TX | TEXAS | Austin-Bergstrom Airport | 480175 | Armed Forces Reserve Center | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. Contract #: TX10-ENG-25 | 16441000 | 14195598.92 | 2011-01-01 | 2012-07-17 | 2012-06-15 | 2013-11-04 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | TX | TEXAS | Austin-Bergstrom Airport | 480176 | Field Maintenance Shop, Joint | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. Contract #: TX10-ENG-25 | 7020718.76 | 7020718.76 | 2011-01-01 | 2012-07-17 | 2012-06-15 | 2013-11-04 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | VT | VERMONT | Ethan Allen Firing Range | 500071 | Bachelor Officer Quarters additions and improvement | 2010-09-14 | 2010-09-20 | Summit/Catamount Construction Contract #: W912LN-08-D-0003-0003 | 2163343.29 | 2163343.29 | 2010-09-27 | 2011-06-30 | 2011-08-15 | 2011-08-15 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510302 | Regional Training Institute, PH 2 | 2010-01-27 | 2010-02-26 | Barton Marlow Company Contract #: W91236-08-C-0079-P00001 | 30249051.23 | 30249051.23 | 2010-07-01 | 2011-07-06 | 2012-09-10 | 2012-08-01 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | VI | VIRGIN ISLANDS | St. Croix | 520014 | Regional Training Institute, PH 1 | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. Contract #: W9127P-10-C-0001 | 19978000 | 19493319.3 | 2010-07-01 | 2013-02-15 | 2012-02-20 | 2013-04-23 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Minor Construction (UMMC) | WA | WASHINGTON | Camp Murray | 530033 | Entrance Gate w/Access Control Buildings | 2011-09-15 | 2011-09-01 | Berschauer Construction Contract #: 2010-234G(2-1) | 2994000 | 2994000 | 2011-10-07 | 2013-03-05 | 2013-03-08 | 2013-03-05 | 100 | 0 |  |  | (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Major Construction | WV | WEST VIRGINIA | St. Albans | 540217 | Readiness Center Addition/Life Safety Upgrades | 2010-09-24 | 2010-09-26 | Hayslett Construction Company Contract #: DEFK11013 | 1973000 | 1135206.62 | 2010-10-01 | 2011-10-21 | 2011-09-18 | 2011-09-18 | 100 | 0 |  |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | AZ | ARIZONA | Florence | 040023 | Readiness Center | 2011-08-01 | 2011-09-01 | Haydon Building Corporation-Tem Contract #: M11-31 | 16446000 | 16319458.79 | 2011-09-19 | 2012-12-10 | 2012-12-14 | 2014-01-30 | 90 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | AR | ARKANSAS | Camp Robinson | 050043 | Combined Support Maintenance Shop | 2011-06-24 | 2011-07-01 | CDI Contractors, LLC Contract #: 9750816 CSMS Const | 29887000 | 28273500 | 2011-11-01 | 2013-08-15 | 2013-07-01 | 2013-10-01 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | AR | ARKANSAS | Fort Chaffee | 050163 | Combined Arms Collective Training Facility | 2010-12-21 | 2011-05-23 | Crossland Construction Company, Inc. Contract #: 9751022 | 8857560 | 7412601 | 2011-09-19 | 2013-06-13 | 2012-03-23 | 2013-10-15 | 99 | 6500000 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($8,857,560.00)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | AR | ARKANSAS | Fort Chaffee | 050173 | Live Fire Shoot House | 2011-05-26 | 2011-06-14 | Ross Sparks Builders, Inc. Contract #: 9751028 LFSH Const | 2488000 | 2266871.38 | 2011-07-01 | 2012-09-18 | 2012-06-07 | 2013-10-15 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060429 | Combined Arms Collective Training Facility | 2011-05-12 | 2011-09-20 | Cox Construction Company Contract #: W912LA-11-R-0005 | 12379000 | 11525157.7 | 2011-12-05 | 2013-06-15 | 2012-06-29 | 2013-09-27 | 99 | 6700000 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379,000.00)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Gypsum/Eagle | 080062 | HAATS/AASF | 2011-05-19 | 2011-07-13 | Hensel Phelps Construction Company Contract #: HAATS Construction - Federal Contracting | 38862000 | 37414650.85 | 2011-11-01 | 2013-04-01 | 2013-03-31 | 2013-10-31 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Fort Carson | 080067 | Regional Training Institute | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC Contract #: RTI Construction | 50886147 | 50819123 | 2011-10-01 | 2013-10-01 | 2014-10-18 | 2014-10-03 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011). Informal Reprogramming $2M Formal Reprogramming $9.3M funds from FY10 project savings {PNs: 160120, ($6M) & 350043 ($3.3M)}
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Colorado Springs | 080201 | Readiness Center | 2011-08-12 | 2011-09-16 | Smith Construction Management, LLC Contract #: North Colorado Springs (USAFA) Readiness Center Construction | 19934000 | 19013638.7 | 2011-12-01 | 2013-10-01 | 2013-09-30 | 2014-09-08 | 85 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Windsor | 080202 | Readiness Center | 2011-08-05 | 2011-08-16 | AP Mountain States Contract #: 080202 - Adolfson & Peterson Construction | 7468555.7 | 7468555.7 | 2011-12-01 | 2012-11-01 | 2012-10-19 | 2012-10-19 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | CT | CONNECTICUT | Windsor Locks | 090010 | Readiness Center (Aviation) | 2011-05-27 | 2011-09-22 | Walsh Construction Co. Contract #: W91ZRS-11-C-0017 | 40616000 | 32004159 | 2011-10-01 | 2013-11-05 | 2013-10-19 | 2013-10-19 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | DE | DELAWARE | New Castle | 100037 | Armed Forces Reserve Center (JFHQ) | 2011-08-03 | 2011-08-18 | Vigil Contracting, Inc. Contract #: W912L5-09-2-2001 | 26879000 | 25629474 | 2011-12-01 | 2014-04-01 | 2013-07-10 | 2014-05-08 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | GA | GEORGIA | Dobbins | 130123 | Readiness Center, Add/Alt | 2011-05-17 | 2012-04-17 | TEPA Contract #: W912JM-10-D-0018-002 | 10363000 | 10349028.69 | 2012-06-04 | 2013-09-30 | 2013-09-30 | 2014-04-30 | 10 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | GA | GEORGIA | Cumming | 130127 | Readiness Center | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. Contract #: W912JM-10-D-0018-002 | 16941000 | 16726443.32 | 2011-12-01 | 2013-05-15 | 2012-11-16 | 2012-11-16 | 85 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | GU | GUAM | Barrigada | 140001 | Combined Support Maintenance Shop, Ph 1 | 2011-05-31 | 2011-09-01 | NAVFAC Pacific Contract #: N40192-10-D-2801-0004 | 19300156.12 | 19300156.12 | 2011-09-12 | 2013-04-19 | 2012-04-20 | 2012-04-20 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | HI | HAWAII | Kalaeloa | 150077 | Combined Support Maintenance Shop, Ph 2A | 2011-08-11 | 2011-12-29 | BCP Construction of Hawaii, Inc. Contract #: W912J6-11-C-0002 | 37192930.2 | 37192930.2 | 2012-02-01 | 2014-03-20 | 2013-08-18 | 2014-03-20 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | ID | IDAHO | Gowen Field | 160093 | Barracks (ORTC), Ph 1 | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. Contract #: W912J7-11-C-0002 | 17333000 | 13808602.63 | 2011-08-27 | 2013-10-03 | 2013-02-28 | 2014-04-15 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969,000.00)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | ID | IDAHO | Mountain Home | 160122 | Tactical Unmanned Aircraft System Facility | 2011-05-23 | 2011-08-02 | Construction Inc, Moutain Home Contract #: W912J7-11-C-0001 | 5476880.29 | 5476880.29 | 2011-09-13 | 2013-11-14 | 2013-10-22 | 2013-11-14 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | IL | ILLINOIS | Springfield | 179237 | Combined Support Maintenance Shop, Add/Alt | 2011-09-15 | 2011-09-20 | CORE Construction Contract #: W91SMC-09-2-2002-200 | 14954000 | 14463788.25 | 2011-10-24 | 2013-07-17 | 2012-10-05 | 2014-07-31 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | KS | KANSAS | Wichita East | 200063 | Readiness Center | 2011-07-15 | 2011-08-11 | Straub Construction Co., Inc. Contract #: CONSTRUCTION | 26283000 | 24235376.19 | 2011-09-23 | 2013-07-01 | 2012-12-07 | 2013-07-15 | 99 | 8461000 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($26,283,000.00)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | KS | KANSAS | Wichita | 200090 | Field Maintenance Shop | 2011-09-01 | 2011-09-28 | The Law Company, Inc. | 13243800 | 12402000.58 | 2011-11-18 | 2014-04-15 | 2012-10-19 | 2014-04-15 | 95 | 5004000 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($13,243,800.00)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | KY | KENTUCKY | Burlington | 210034 | Readiness Center | 2011-08-31 | 2011-09-16 | D.W. Wilburn Contract #: CT2 785 1200000063 1 | 18776454.84 | 18776454.84 | 2011-11-09 | 2013-01-30 | 2013-03-01 | 2013-01-30 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | LA | LOUISIANA | Minden | 220114 | Readiness Center | 2011-06-23 | 2011-08-08 | Walton Construction Co., LLC. Contract #: LA11-C-125 | 27676000 | 22524304.8 | 2011-08-29 | 2013-09-03 | 2013-01-14 | 2013-08-29 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($19,307,752.00)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | LA | LOUISIANA | Fort Polk | 220222 | Tactical Unmanned Aircraft System Facility | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company Contract #: LA11-C-139 | 5470000 | 5010566.27 | 2011-09-12 | 2012-12-11 | 2012-07-30 | 2013-06-18 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | MD | MARYLAND | Webster Field, St Inigoes | 240186 | Tactical Unmanned Aircraft System Facility | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC Contract #: N40080-10-D-0498 | 5583154 | 5583154 | 2011-09-23 | 2013-09-27 | 2013-06-15 | 2014-04-15 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Hanscom AFB | 250136 | Armed Forces Reserve Center (JFHQ), Ph 2 | 2011-09-15 | 2011-09-22 | Nauset Construction Corp Contract #: W912SV-11-C-0004 | 22927000 | 21885221.26 | 2011-10-17 | 2012-11-17 | 2012-10-27 | 2014-04-04 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260207 | Combined Arms Collective Training Facility | 2011-06-22 | 2011-08-18 | Saylor Construction LLC Contract #: Y11261 | 13822986.89 | 13822986.89 | 2011-09-20 | 2013-04-05 | 2012-03-09 | 2013-11-18 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270096 | Infantry Squad Battle Course | 2011-06-28 | 2011-07-01 | Eagle Construction Company, Inc. Contract #: EAG010025 | 2231992.1 | 2231992.1 | 2011-11-01 | 2013-02-15 | 2012-07-06 | 2013-02-15 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270202 | Field Maintenance Shop | 2011-07-19 | 2011-08-08 | Stahl Construction Company Contract #: STA006002 | 28894000 | 26313740.88 | 2011-10-26 | 2013-05-03 | 2013-01-18 | 2014-04-18 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 1121-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270267 | Tactical Unmanned Aircraft System Facility | 2011-07-21 | 2011-08-08 | Donlar Construction Company Contract #: DON050003 | 4413000 | 3544198.7 | 2012-04-03 | 2012-12-13 | 2012-10-27 | 2012-12-13 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | NE | NEBRASKA | Mead | 310107 | Readiness Center | 2011-06-15 | 2011-07-12 | The Weitz Company, LLC Contract #: WEITZ-ATLAS01CONSTR | 11368000 | 11339271 | 2012-05-07 | 2013-05-06 | 2012-08-08 | 2013-04-01 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | NE | NEBRASKA | Lincoln | 310110 | Readiness Center, Add/Alt | 2011-08-16 | 2011-08-19 | Kingery Construction Company Contract #: EastCampus-CONSTR-KINGERY-01 | 3338605.59 | 3338605.59 | 2011-10-01 | 2013-05-06 | 2012-11-06 | 2013-04-29 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | NH | NEW HAMPSHIRE | Pembroke | 330034 | Classroom Facility (Regional Training Institute) | 2011-05-09 | 2011-08-25 | Eckman Construction Company, Inc. Contract #: 80342R-G | 20742000 | 19804677.51 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-03 | 15 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | NH | NEW HAMPSHIRE | Pembroke | 330035 | Barracks Facility (Regional Training Institute) | 2011-05-09 | 2011-08-26 | Eckman Construction Company, Inc. Contract #: 80342R-G | 14880000 | 14074443.67 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-30 | 15 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | NM | NEW MEXICO | Farmington | 350075 | Readiness Center, Add/Alt | 2011-04-19 | 2011-09-29 | Jaynes Corporation Contract #: 12-705-0000-1213 | 10306121.78 | 10306121.78 | 2011-12-05 | 2012-12-25 | 2012-10-31 | 2012-10-31 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | NC | NORTH CAROLINA | High Point | 370898 | Readiness Center, Add/Alt | 2011-09-08 | 2011-09-15 | Holden Building Company, Inc. Contract #: W912421022003 | 1590022.94 | 1590022.94 | 2011-11-05 | 2012-08-01 | 2012-10-26 | 2012-10-26 | 95 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | ND | NORTH DAKOTA | Camp Grafton | 380014 | Readiness Center, Add/Alt | 2011-06-15 | 2011-06-22 | Comstock Construction, Inc. Contract #: AGND11-30 | 11742926.68 | 11742926.68 | 2011-08-08 | 2012-09-11 | 2012-07-15 | 2013-02-26 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Camp Grafton, Devils Lake | 380121 | Levee Pump Station | 2011-09-22 | 2011-09-30 | Swanberg Construction, Inc. Contract #: AGND11-71 | 1927747.33 | 1927747.33 | 2011-10-24 | 2012-10-31 | 2012-12-15 | 2014-05-30 | 100 | 0 |  |  | (NGB 593)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | PR | PUERTO RICO | Camp Santiago | 436023 | Live Fire Shoot House | 2011-07-21 | 2011-09-22 | Remex Co. Contract #: W912LR-11-B-0001 | 3077000 | 2562384.37 | 2011-11-07 | 2012-09-18 | 2012-12-14 | 2012-12-14 | 65 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | RI | RHODE ISLAND | East Greenwich | 440009 | United States Property and Fiscal Office | 2011-07-26 | 2011-09-30 | Maron Construction Co, Inc. USPFO - RI, Purchasing & Contracting Contract #: W912LD-12-C-0001 | 26713000 | 21211178 | 2012-09-21 | 2014-07-05 | 2014-04-09 | 2014-07-05 | 67 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note: SB Size Protest delayed award and construction start of project)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Watertown | 460085 | Readiness Center | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. Contract #: W912MM-06-2-2002 | 18225100 | 17722658.2 | 2011-11-07 | 2013-03-01 | 2013-01-14 | 2013-05-24 | 99 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($18,225,100.00)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | TX | TEXAS | Camp Maxey | 480267 | Combat Pistol/Military Pistol Qualification Course | 2011-04-06 | 2011-09-12 | Unified Services of Texas, Inc. Contract #: TX11-ENG-10 | 1962098.14 | 1962098.14 | 2011-09-26 | 2012-10-31 | 2012-03-31 | 2012-10-31 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | TX | TEXAS | Camp Swift | 480290 | Urban Assault Course | 2011-08-25 | 2011-09-12 | Gaeke Construction Co., Inc. Contract #: TX11-ENG-06 | 2172467.8 | 2172467.8 | 2011-11-01 | 2013-01-21 | 2012-08-20 | 2013-08-01 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | VI | VIRGIN ISLANDS | St. Croix | 520034 | Readiness Center (JFHQ) | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. Contract #: W9127P-11-C-0005 | 24850000 | 22324012.96 | 2011-11-01 | 2013-11-25 | 2013-11-01 | 2014-04-17 | 62 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | WA | WASHINGTON | Tacoma | 530022 | Combined Support Maintenance Shop | 2011-06-07 | 2011-06-23 | Walsh Construction Co, II, LLC Contract #: 2009-205 G 1-1 | 24880000 | 23925480.33 | 2011-08-22 | 2013-12-12 | 2012-11-03 | 2013-05-07 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), State waiting on demolition of the old CSMS
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Morgantown | 540068 | Readiness Center | 2011-09-21 | 2011-09-22 | Massaro Corporation Contract #: 540068A | 20895000 | 18998651.85 | 2011-11-14 | 2013-04-09 | 2013-03-26 | 2013-03-26 | 75 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Moorefield | 540084 | Readiness Center | 2011-06-01 | 2011-09-21 | Langan General Contracting Corp Contract #: DEFK12000 | 14145000 | 13572590.86 | 2011-10-08 | 2013-04-22 | 2013-03-24 | 2014-06-23 | 90 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | WI | WISCONSIN | Madison | 550139 | Aircraft Parking | 2011-08-16 | 2011-09-15 | Buteyn Peterson Construction Co. Contract #: NGB-47-11-C-0014 (BP) | 5960235 | 5960235 | 2011-11-01 | 2012-10-09 | 2012-10-29 | 2012-10-17 | 94 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Major Construction | WY | WYOMING | Laramie | 560116 | Field Maintenance Shop | 2011-07-28 | 2011-08-16 | Health Construction Contract #: 11041922101 | 11195625.88 | 11195625.88 | 2011-09-12 | 2013-03-19 | 2013-06-30 | 2014-06-03 | 100 | 0 |  |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | AL | ALABAMA | Talladega | 011006 | Readiness Center, Add/Alt | 2012-09-13 | 2012-09-21 | Metro D. Constructions, LLC. Contract #: AC-12-C-0036-S | 2000000 | 1999490.51 | 2012-11-18 | 2013-10-01 | 2013-09-16 | 2014-01-28 | 10 | 0
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010263 | Readiness Center Ph2 | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. Contract #: W912JA-12-C-0001 | 16413000 | 14492476 | 2012-09-14 | 2013-12-24 | 2013-12-10 | 2013-12-10 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | AZ | ARIZONA | Papago Military Reservation | 040294 | Readiness Center | 2012-02-15 | 2012-08-16 | Haydon Building Corporation - Tem Contract #: M11-0045 | 17771000 | 17654637.63 | 2012-09-12 | 2013-11-04 | 2013-10-16 | 2014-01-31 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | AR | ARKANSAS | Fort Chafee | 050172 | Convoy Live Fire/Entry Control Point Range | 2012-02-14 | 2012-08-16 | USPFO - AK Contract #: 9751104 | 3604364.39 | 3604364.39 | 2012-11-07 | 2013-12-20 | 2013-10-28 | 2014-07-15 | 55 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | AR | ARKANSAS | Camp Robinson | 050190 | Wash Platform, Installation | 2013-09-12 | 2013-09-18 | Wilkins Construction, Inc. Contract #: CONST-1/RMTC Veh Wash Facility | 1195000 | 1758804.31 | 2014-03-10 | 2014-06-23 | 2014-06-23 | 2014-12-22 | 33 | 0
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060009 | Utilities Replacement Ph1 | 2012-07-09 | 2012-08-01 | Cox Construction Co. Contract #: W912LA-12-C-0007 | 31073000 | 25066372.2 | 2012-12-01 | 2014-09-26 | 2015-03-01 | 2015-04-30 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp San Luis Obispo | 060170 | Field Maintenance Shop | 2012-06-19 | 2012-06-26 | Goshawk LLC Contract #: W912LA-12-C-0003 | 7985000 | 7456031.69 | 2012-11-08 | 2013-10-20 | 2013-10-14 | 2014-06-06 | 30 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | CA | CALIFORNIA | Los Alamitos | 060432 | Barracks | 2012-06-27 | 2012-09-28 | WEP Enterprises Contract #: W912LA-11-D-0024-0002 | 1400000 | 1118519.03 | 2012-10-15 | 2003-10-07 | 2013-09-20 | 2013-09-20 | 98 | 0 |  |  | FY07 Congressionally Directed, Used FY10 funds
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060438 | Tactical Unmanned Aircraft System Facility | 2012-06-04 | 2012-07-20 | Red Mountain LLC Contract #: W912LA-12-C-0002-0001 | 5060050.36 | 5060050.36 | 2012-08-06 | 2013-11-11 | 2013-10-28 | 2014-05-15 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,834,795.71)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Fort Carson | 080093 | Barracks Complex (ORTC) | 2012-08-30 | 2012-09-04 | FSA & JKC Joint Venture One, LLC. | 43667656.88 | 43667656.88 | 2012-09-24 | 2013-12-02 | 2013-10-28 | 2014-12-03 | 81 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Alamosa | 080126 | Readiness Center | 2012-06-12 | 2012-06-22 | FCI Constructors, Inc. Contract #: 080126 - FCI Constructors - CM/GC Construction | 6397000 | 6276185.07 | 2012-09-10 | 2013-12-02 | 2013-10-14 | 2013-10-14 | 85 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Aurora | 080206 | Tactical Unmanned Aircraft System Facility | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. Contract #: 080206 - TUAS - McCauley Constructors - Constr | 3886550.17 | 3886550.17 | 2012-11-05 | 2013-12-02 | 2013-10-28 | 2014-08-15 | 83 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | DC | DISTRICT OF COLUMBIA | Anacostia | 110007 | US Property & Fiscal Office Add/Alt | 2012-08-21 | 2012-08-28 | Allen & Shariff Corporation Contract #: N40080-10-D-0496-0017 | 4774284.57 | 4774284.57 | 2013-03-01 | 2014-06-04 | 2013-12-13 | 2014-06-04 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120188 | Convoy Live Fire/Entry Control Point Range | 2012-07-31 | 2012-08-16 | Breaking Ground Contracting Co. Contract #: 120188 Construction | 2918900 | 2918900 | 2013-02-13 | 2013-12-16 | 2013-12-02 | 2013-12-02 | 11 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120193 | Live Fire Shoot House | 2012-04-10 | 2012-04-27 | STG Contracting Group Contract #: 120193 LFSH Construction | 2556008.99 | 2556008.99 | 2012-05-21 | 2013-03-04 | 2013-10-28 | 2013-04-19 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | FL | FLORIDA | Camp Blanding, Starke | 120277 | Unit Storage Building (TUAS) | 2012-08-30 | 2012-09-14 | C. Young Construction Contract #: 120277 TUAS D-B contract | 821000 | 821000 | 2013-04-13 | 2013-10-19 | 2013-09-12 | 2013-09-12 | 20 | 0
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Hinesville | 130063 | Maneuver Area Training & Equipment Site Ph1 | 2012-01-12 | 2012-09-11 | J&S Construction Company, Inc. Contract #: W912JM-12-R-0011 | 19255000 | 19241668.76 | 2012-10-19 | 2013-11-18 | 2013-10-28 | 2013-10-28 | 22 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2331M funds from FY10 project savings PN: 130077
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Macon | 130068 | Readiness Center Ph 1 | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC | 14457000 | 13968549.46 | 2012-09-14 | 2014-04-12 | 2014-03-14 | 2014-04-20 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Atlanta | 130120 | Readiness Center | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. | 11209719.39 | 11209719.39 | 2012-09-10 | 2013-11-18 | 2013-10-28 | 2014-08-14 | 90 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | HI | HAWAII | Kalaeloa | 150043 | Readiness Center Ph 1 | 2012-02-15 | 2012-07-11 | Dawson Technical, LLC Contract #: W912J6-12-R-0002 | 32556514.82 | 32556514.82 | 2012-07-23 | 2014-08-11 | 2014-07-23 | 2014-07-23 | 12 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | IL | ILLINOIS | Normal | 170801 | Readiness Center | 2012-09-13 | 2012-09-13 | River City Construction Contract #: W91SMC-10-2-2005-200 | 10870650 | 10544117.87 | 2012-11-05 | 2014-05-31 | 2014-10-28 | 2014-09-30 | 97 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($10,870,650.00)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | IL | ILLINOIS | Sparta | 171005 | Battalion Maintenance Shelter | 2012-09-24 | 2012-09-24 | H&N Construction Contract #: W91SMC-10-2-2002-200 | 1210000 | 998620.76 | 2012-10-01 | 2013-06-30 | 2013-10-31 | 2014-09-30 | 99 | 0 |  |  | (Completed - State working on NGB 593)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Indianapolis (Stout Field) | 180012 | JFHQ Add/Alt | 2012-09-19 | 2012-09-19 | F.A. WILHELM Construction., Inc. Contract #: MDI-SAB-13-C-0012 | 34971000 | 34456346.7 | 2012-11-15 | 2014-05-04 | 2013-10-28 | 2014-10-31 | 80 | 0 |  |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2M FY09 project {PN: 040226} & 2853 & Formal Reprogramming $7.271M funds from FY09 project savings {PNs: 040226 ($2.540M), 180116 (3.805M), 180137 (510K) & 260211 (416K)}
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180142 | Railhead Expansion & Container Facility | 2012-09-11 | 2012-09-12 | Milestone Contractors, L.P. Contract #: MDI-SAB-13-C-0011 | 20908000 | 19068700 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 4 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180156 | Deployment Processing Facility | 2012-09-11 | 2012-09-12 | Milestone Contractors, L.P. Contract #: MDI-SAB-13-C-0011 | 8878000 | 8254642 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180160 | Operations Readiness Training Complex 1 | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. Contract #: MDI-SAB-12-C-0031 | 26136137 | 26136137 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 19 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180161 | Operations Readiness Training Cmplx 2 | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. Contract #: MDI-SAB-12-C-0031 | 27520300 | 27520300 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 15 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | LA | LOUISIANA | Camp Minden | 220233 | Waste Water Treatment Facility | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. Contract #: LA12-C-117 | 2972000 | 2875138.5 | 2012-06-15 | 2013-07-15 | 2013-06-17 | 2014-09-01 | 95 | 0
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230046 | Readiness Center | 2012-04-05 | 2012-09-26 | ITSI Gibane Contract #: 230046-DB | 15584000 | 14795830.39 | 2012-09-26 | 2014-07-30 | 2014-07-11 | 2014-08-02 | 35 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | ME | MAINE | Brunswick | 230071 | Armed Forces Reserve Center | 2012-11-10 | 2012-09-26 | J.C.N. Construction Co, Inc. Contract #: 230071-D | 23977667.33 | 23977667.33 | 2012-09-26 | 2014-10-26 | 2014-10-12 | 2014-11-21 | 73 | 0 |  |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | Dundalk | 240017 | Readiness Center Add/Alt | 2012-08-29 | 2012-09-11 | The Whiting Turner Contracting Company Contract #: 001B3400152 | 15771000 | 11818635.74 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2014-10-22 | 79 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | Westminster | 240187 | Readiness Center Add/Alt | 2012-07-23 | 2012-09-11 | Harkins Builders Contract #: 001B3400154 | 10296000 | 7520414.32 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2015-01-15 | 26 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | La Plata | 240193 | Readiness Center | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. Contract #: 001B3400155 | 9997709.8 | 9997709.8 | 2012-10-01 | 2013-10-06 | 2014-09-22 | 2015-06-22 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Natick | 250135 | Readiness Center | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc Contract #: MIL1001-DC1 | 9530445.98 | 9530445.98 | 2012-12-01 | 2013-11-18 | 2013-10-28 | 2014-10-28 | 75 | 0 |  |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | MA | MASSACHUSETTS | Camp Edwards | 250178 | J-1 Range North Pump and Treat Facility | 2012-10-25 | 2012-11-15 | Tetra Tech/Mead & Hunt JV Contract #: DACW33-03-D-0006 | 2504000 | 2394000 | 2013-03-04 | 2013-10-21 | 2013-10-21 | 2014-10-21 | 12 | 0 |  |  | Used FY13 funds
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270266 | Multipurpose Machine Gun Range | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. Contract #: WGO010008 | 4718468 | 4477124.97 | 2012-09-17 | 2014-01-18 | 2013-12-15 | 2014-06-01 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,718,469.00)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280315 | Troop Housing (ORTC) Ph1 | 2012-01-12 | 2012-06-22 | DCD-YATES Contract #: W9127Q-12-C-0004 | 20709500 | 20041154.24 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,709,500.00)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280387 | Deployment Processing Facility | 2012-05-31 | 2012-07-11 | Hanco Corporation Contract #: Construction | 9222260 | 8803310 | 2012-12-01 | 2013-11-15 | 2013-10-16 | 2013-12-31 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($9,222,260.00)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280389 | Operations Readiness Training Cmplx Ph1 | 2012-01-12 | 2012-06-22 | DCD-YATES Contract #:W9127Q-12-C-0004 | 24411040 | 23620595.76 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($24,411,040.00)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | NE | NEBRASKA | Grand Island | 310085 | Readiness Center | 2012-05-29 | 2012-06-05 | Sampson Construction Company, Inc. Contract #: SAMPSON-GIRC-01 CONSTR | 21913000 | 18742184 | 2012-07-01 | 2013-12-13 | 2013-11-22 | 2014-03-25 | 99 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | NE | NEBRASKA | Mead | 310086 | Readiness Center | 2012-04-09 | 2012-04-27 | Boyd Jones Construction Contract #: BOYDJONES-TITAN-01CONSTR | 9954864.83 | 9954864.83 | 2012-05-01 | 2013-11-01 | 2013-06-27 | 2014-05-21 | 98 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | NE | NEBRASKA | Ashland | 310142 | CATS Waste Water Treatment Facility | 2012-06-28 | 2012-08-10 | All Purpose Construction Contract #: ALLPURPOSE-CATS-WWTF-01 CALLOT | 1661134.5 | 1661134.5 | 2012-09-01 | 2013-10-11 | 2013-09-19 | 2014-04-30 | 98 | 0
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | NV | NEVADA | Las Vegas | 320070 | Field Maintenance Shop | 2012-01-12 | 2012-04-17 | CORE Construction | 22932000 | 21295220.15 | 2012-12-01 | 2013-11-08 | 2013-10-25 | 2014-10-31 | 98 | 0 |  |  | PL 112-25 (Budget Control Act, 2011), State waiting on demolition of existing FMS and will submit draft NGB 593 in Oct 14
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Minor Construction (UMMC) | NH | NEW HAMPSHIRE | Milford | 330052 | Readiness Center, Add/Alt | 2012-08-27 | 2012-09-04 | Turnstone Corporation Contract #: 330052-GC | 1947000 | 1943047.44 | 2012-10-07 | 2013-07-29 | 2013-08-13 | 2013-08-13 | 100 | 0 |  |  | (Closeout procedures are in progress)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | NJ | NEW JERSEY | Lakehurst | 340115 | Army Aviation Support Facility | 2012-02-15 | 2012-09-19 | Senate Builders & Construction Managers Contract #: W912KN-12-C-0006 | 48795000 | 45244039.49 | 2012-09-19 | 2014-12-15 | 2014-10-18 | 2014-12-05 | 72 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | NM | NEW MEXICO | Santa Fe | 350115 | Readiness Center Add/Alt | 2012-01-03 | 2012-04-10 | Jaynes Corporation Contract #: 12-07-0000-1219 | 5172000 | 4439818.96 | 2012-12-01 | 2013-07-13 | 2013-06-01 | 2013-06-01 | 95 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | NC | NORTH CAROLINA | Greensboro | 370899 | Readiness Center Add/Alt | 2012-09-04 | 2012-09-04 | Holden Building Company, Inc. Contract #: W912421022004 CO1 | 3680000 | 3370848.51 | 2012-12-01 | 2013-11-04 | 2013-10-28 | 2013-10-28 | 5 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | OK | OKLAHOMA | Camp Gruber | 400605 | Upgrade-Combined Arms Collective Training Fac | 2012-01-12 | 2012-08-16 | Benham Companies, LLC Contract #: W90FYQ-09-D-0006-9J01 | 10343000 | 9245608.77 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-06-20 | 96 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | OK | OKLAHOMA | Camp Gruber | 400606 | Live Fire Shoot House | 2012-01-24 | 2012-08-15 | Benham Companies, LLC Contract #: W90FYQ-09-D-0006-9J02 | 3148780.73 | 3148780.73 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-06-28 | 2 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | OR | OREGON | The Dalles | 410026 | Readiness Center | 2012-03-02 | 2012-03-19 | Hoffman Construction Company Contract #: 410026D002 | 13800000 | 13189960 | 2012-12-01 | 2014-02-21 | 2013-12-28 | 2014-03-20 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | PR | PUERTO RICO | Fort Buchanan | 430010 | Readiness Center | 2012-09-10 | 2012-09-18 | RB Construction Group Inc Contract #: W912LR-12-C-0005-P00001 | 40565271.7 | 38119214.56 | 2012-12-01 | 2014-12-05 | 2013-10-28 | 2013-11-05 | 17 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($40,565,271.20)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Allendale | 450403 | Readiness Center Add/Alt | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. | 4290000 | 4254800.75 | 2012-10-01 | 2013-09-01 | 2013-10-28 | 2013-10-28 | 10 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | UT | UTAH | Camp Williams | 490618 | Multi Purpose Machine Gun Range | 2012-09-06 | 2012-09-27 | Cracar Construction Contract #: W911YP-12-C-0007 | 6576914.72 | 6576914.72 | 2012-12-01 | 2014-01-06 | 2013-10-28 | 2013-10-28 | 66 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510307 | Combined Arms Collective Training Facility | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC Contract #: W912LQ-13-C-0001 | 10912000 | 8757592.5 | 2013-04-01 | 2014-10-09 | 2014-10-09 | 2014-10-09 | 77 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Buckhannon | 540085 | Readiness Center Ph1 | 2012-09-20 | 2012-09-25 | Paramount Builders LLC Contract #: DEFK 13002 | 11545393.51 | 11545393.51 | 2012-11-01 | 2014-08-25 | 2014-11-12 | 2014-11-12 | 75 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | WI | WISCONSIN | Camp Williams | 550245 | Tactical Unmanned Aircraft System Facility | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. Contract #: NGB-47-12-C-0002 | 4249560 | 3985634.66 | 2012-07-01 | 2013-10-20 | 2013-05-20 | 2014-05-30 | 98 | 0 |  |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,249,560.00)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Major Construction | WY | WYOMING | Cheyenne | 560702 | Readiness Center | 2012-04-27 | 2012-04-18 | Hensel Phelps Contract #: 12014512201 | 10341796 | 10341796 | 2012-12-01 | 2013-06-17 | 2013-10-28 | 2013-06-17 | 100 | 0 |  |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | AL | ALABAMA | Athens | 011007 | National Guard Readiness Center | 2013-09-24 | 2013-09-26 | Butler Construction Company, LLC. Contract #: AC-13-B-0051-S | 1920000 | 1891325 | 2014-02-03 | 2015-04-24 | 2015-04-24 | 2014-10-01 | 0 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010278 | Live Fire Shoot House | 2013-08-01 | 2013-08-23 | Hurst Construction, LLC Contract #: AC-13-C-0052-S | 5382125.2 | 5382125.2 | 2013-09-23 | 2014-08-15 | 2014-08-15 | 2014-08-15 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | AZ | ARIZONA | Camp Navajo | 040669 | Underground Electrical Lines | 2013-09-23 | 2014-04-04 | Ludvik Electric Contract #: M13-0037 | 2000000 | 1832989.71 | 2014-05-05 | 2014-10-31 | 2014-10-31 | 2014-10-31 | 0 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | AR | ARKANSAS | Searcy | 050139 | Field Maintenance Shop | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC Contract #: 9751312 | 6577000 | 4966584 | 2013-08-30 | 2014-10-27 | 2014-10-01 | 2014-10-01 | 2 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) Used FY09 funds only
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | CA | CALIFORNIA | Fort Irwin | 060413 | Maneuver Area Training & Equipment Site Ph 3 | 2013-08-01 | 2013-09-20 | Cox Construction Co. Contract #: W912LA-13-C-0003 | 31793000 | 22901289.01 | 2013-10-21 | 2014-10-01 | 2014-10-01 | 2015-09-30 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funs from FY10 project savings {PNs: 180145 (1.5M), 320143 ($3,112M), 250087 ($2M) & 160120 ($1M)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | CT | CONNECTICUT | Camp Hartell | 090043 | Combined Support Maintenance Shop | 2013-06-25 | 2013-08-27 | Whiting Turner Contract #: W91ZRS-13-C-0002 | 30951000 | 29440589.76 | 2014-04-26 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 5 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | DE | DELAWARE | Bethany Beach | 100010 | Regional Training Institute Ph 1 | 2013-06-28 | 2013-07-05 | EDIS Company Contract #: 10-2010 | 5319000 | 5151591.72 | 2013-09-23 | 2014-10-20 | 2014-10-01 | 2014-10-28 | 43 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | FL | FLORIDA | Miramar | 120102 | Readiness Center | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) Contract #: 120102 Construction-MCM | 20758062 | 20758062 | 2014-03-03 | 2015-02-20 | 2015-02-20 | 2015-09-03 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120192 | Upgrade: Combined Arms Collective Training Facility | 2013-06-07 | 2013-06-25 | Thomas May Construction Company Contract #: 120192 Construction | 8705000 | 6452001.28 | 2013-10-04 | 2014-10-20 | 2014-10-01 | 2014-10-01 | 2 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | FL | FLORIDA | MacDill AFB, St Augustine | 120228 | Ready Building | 2013-09-05 | 2013-09-10 | Halfacre Construction Company Contract #: 120228 SOD-C Ready D-B Halfacre | 1939000 | 1920000 | 2013-10-14 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 0 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | GU | GUAM | Barrigada | 140040 | JFHQ Ph 4 | 2013-08-22 | 2013-09-24 | NAVFAC Pacific Contract #: N40192-10-D-2800/2801/2802/2803/2804/2810 | 8221000 | 8088654 | 2013-10-21 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | ID | IDAHO | Orchard (MATES) | 160100 | ORTC (Barracks) Ph 2 | 2013-06-27 | 2013-09-27 | Trainor Enterprises Contract #: W912J7-13-C-0001 | 38692000 | 37583239.48 | 2013-10-07 | 2014-08-01 | 2014-08-01 | 2015-12-10 | 17 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | IN | INDIANA | Terre Haute | 180106 | Field Maintenance Shop | 2013-09-24 | 2013-09-24 | Gamong Construction Contract #: MDI-SAB-14-C-0002 | 8705000 | 8463137 | 2014-07-21 | 2014-12-25 | 2014-12-25 | 2015-05-30 | 25 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | IN | INDIANA | South Bend | 180144 | Armed Forces Reserve Center Add/Alt | 2013-09-20 | 2013-09-20 | Ziolkowski Construction Contract #: MDI-SAB-14-C-0001 | 22015800 | 22015800 | 2014-04-21 | 2015-05-29 | 2015-08-23 | 2015-05-29 | 5 | 0 |  |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | IA | IOWA | Camp Dodge | 190142 | Urban Assault Course | 2013-05-29 | 2013-06-07 | Rochon Corporation of Iowa Contract #: C751SI088 | 2902000 | 2544576.88 | 2013-08-09 | 2014-05-30 | 2014-04-30 | 2014-09-30 | 94 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | KS | KANSAS | Topeka | 200102 | Taxiway, Ramp & Hangar Alterations | 2013-05-21 | 2013-06-14 | Senne & Co Contract #: CONSTRUCTION | 9188000 | 8389497.61 | 2013-07-22 | 2014-05-02 | 2014-10-01 | 2014-07-04 | 44 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | KS | KANSAS | Salina Smokey Hill MAJ Tng Area | 200127 | Water Distribution Lines, Potable | 2013-09-16 | 2013-09-24 | Harbin Construction Contract #: W912JC-12-D-5308 | 1444875 | 1444875 | 2014-04-07 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 75 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | KY | KENTUCKY | Frankfort | 210001 | Army Aviation Support Facility | 2013-05-17 | 2013-06-04 | DW Wilburn Contract #: CT2 1300000269 | 30953000 | 26194422.8 | 2013-07-08 | 2014-11-10 | 2014-10-01 | 2014-10-01 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | MD | MARYLAND | Glen Arm | 240194 | Combat Pistol/MP Firearms Qualification Course | 2013-09-26 | 2013-09-27 | W M Schlosser Contract #: 001B4400150 | 1920000 | 1740000 | 2014-04-21 | 2014-09-22 | 2014-09-22 | 2014-09-22 | 1 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Camp Edwards | 250065 | Unit Training Equipment Site | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. Contract#: W912SV-13-R-0001 | 21279000 | 21202345.7 | 2014-04-07 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | MA | MASSACHUSETTS | Bourne (Camp Edwards) | 250196 | Water Well, Non-Potable | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District Contract #: DESIGN-250196-USACES | 2000000 | 1838000 | 2013-06-03 | 2013-12-02 | 2013-12-01 | 2013-12-01 | 0 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270236 | Scout Reconnaissance Range | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. Contract #: EAGLE - SWIFT 67879 | 16695000 | 13193606 | 2013-09-23 | 2015-08-01 | 2015-10-01 | 2015-12-15 | 40 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270238 | Readiness Center | 2013-08-08 | 2013-08-14 | LS Black Constructors Contract #: W912LM-13-C-0007 | 17505139.48 | 17505139.48 | 2013-09-30 | 2015-10-15 | 2015-10-15 | 2015-10-23 | 16 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MO | MISSOURI | Fort Leonard Wood | 290176 | Regional Training Institute | 2013-07-26 | 2013-08-01 | KCI Construction Company Contract #: T1203-01B | 17410000 | 15405834.94 | 2013-12-09 | 2015-02-28 | 2015-02-28 | 2015-03-10 | 15 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MO | MISSOURI | Kansas City | 290215 | Readiness Center Add/Alt | 2013-09-10 | 2013-09-17 | Larrison Construction Inc. Contract #: T1206-01 | 1862633.66 | 1862633.66 | 2013-09-30 | 2014-05-27 | 2014-06-30 | 2014-06-30 | 60 | 0 |  |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MO | MISSOURI | Monett | 290216 | Readiness Center Add/Alt | 2013-06-02 | 2013-08-09 | Branco Enterprises Contract #: T1205-01B | 818676 | 818676 | 2014-09-23 | 2014-05-09 | 2014-05-09 | 2014-05-01 | 54 | 0 |  |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MO | MISSOURI | Perryville | 290217 | Readiness Center Add/Alt | 2013-07-31 | 2013-08-05 | Zoellner Construction Co, Inc. Contract #: T1204-04 | 524859 | 524859 | 2013-10-21 | 2014-05-19 | 2014-02-14 | 2014-05-19 | 100 | 0 |  |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | MT | MONTANA | Miles City | 300032 | Readiness Center | 2013-05-29 | 2013-06-07 | Jackson Contractor Group, Inc. Contract #: 300032_const | 12015991.03 | 12015991.03 | 2013-07-08 | 2014-12-15 | 2015-01-09 | 2015-01-21 | 78 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | NJ | NEW JERSEY | Sea Girt | 340110 | Regional Training Institute | 2013-06-17 | 2013-09-30 | Dobco, Inc. Contract #: SG301 | 32885000 | 31932912 | 2014-10-15 | 2016-08-01 | 2016-02-12 | 2016-07-12 | 5 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | ND | NORTH DAKOTA | Camp Grafton, Devils Lake | 380123 | RIP RAP | 2013-09-24 | 2013-12-02 | Close Construction Company Contract #: AGND14-01 | 1775000 | 1738859.4 | 2013-12-09 | 2014-08-30 | 2014-08-30 | 2014-08-30 | 0 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | OH | OHIO | Delaware | 390230 | Readiness Center | 2013-05-29 | 2013-06-05 | Barton Marlow Company Contract #: Construction ADJ-090001 | 11607000 | 8682345.78 | 2013-06-21 | 2014-01-10 | 2013-12-01 | 2014-10-25 | 53 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | OH | OHIO | Chillicothe | 390256 | Field Maintenance Shop Add/Alt | 2013-06-07 | 2013-09-19 | Henderson Contractors, Inc. Contract #: W91364-13-Q-0003 | 2998000 | 2912775.89 | 2013-11-04 | 2014-10-28 | 2014-07-02 | 2014-10-28 | 55 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | OH | OHIO | Port Clinton | 390263 | Hutments | 2014-05-12 | 2014-07-09 | USPFO - OH | 2900000 | 2615660 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 0 | 0 |  |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | OK | OKLAHOMA | Camp Gruber | 400066 | Operations Readiness Training Complex | 2013-08-20 | 2013-08-29 | Semi-USA Contract #: 13231 | 29196708.7 | 27262998.7 | 2013-10-25 | 2014-10-01 | 2014-10-01 | 2016-01-28 | 18 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004M funds from FY11 project savings (PN: 200090)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | PR | PUERTO RICO | Guaynabo | 430081 | Readiness Center (JFHQ) | 2013-06-27 | 2013-09-26 | R B Construction Group Inc. Contract #: W912LR-13-C-0001 | 18294000 | 17447929 | 2014-03-03 | 2015-09-18 | 2015-09-18 | 2015-09-25 | 23 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786M funds from FY10 project savings {PNs: 370897 ($2,856M) & 130077 ($1.3M)}
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | PR | PUERTO RICO | Ceiba | 430804 | Refill Station Building | 2013-06-25 | 2013-09-20 | Design Build S E Contract #: 430804 | 2577293 | 2577293 | 2013-10-28 | 2015-05-08 | 2015-05-08 | 2015-05-08 | 0 | 0 |  |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | PR | PUERTO RICO | Camp Santiago | 430806 | Readiness Center | 2013-06-06 | 2013-09-26 | Design Build S E Contract #: 430806 | 3675000 | 3643273 | 2014-02-10 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 0 | 0 |  |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | UT | UTAH | Camp Williams | 490076 | BEQ Facility (Regional Training Institute) | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. Contract #: 137861 | 15685957.99 | 15685957.99 | 2013-08-12 | 2014-11-10 | 2014-10-01 | 2014-10-31 | 52 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | UT | UTAH | Camp Williams | 490444 | Regional Training Institute Ph 2 | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company Contract #: 137862 | 28772000 | 27870532.52 | 2013-08-26 | 2014-09-30 | 2014-09-30 | 2015-12-30 | 57 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461M funds from FY11 project savings (PN: 200063)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | UT | UTAH | West Jordan | 490803 | Unheated Aircraft Storage Hangar | 2013-11-06 | 2014-07-18 | Keller Construction Inc. Contract #: 147589 | 2000000 | 1840000 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 0 | 0
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | WA | WASHINGTON | Fort Lewis | 530015 | Readiness Center | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) Contract #: USACE Construction Contract | 33853000 | 30034573.54 | 2013-09-23 | 2015-10-26 | 2015-08-20 | 2015-08-27 | 19 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Logan | 540075 | Readiness Center | 2013-09-13 | 2013-09-18 | Paramount Builders LLC Contract #: DEFK14000 | 14987502.28 | 14987502.28 | 2014-04-07 | 2015-09-11 | 2015-09-11 | 2015-09-11 | 0 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Major Construction | WI | WISCONSIN | Wausau | 550142 | Field Maintenance Shop | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company Contract #: NGB-47-13-C-0005 | 9673000 | 9181014.93 | 2013-10-28 | 2014-10-01 | 2014-10-01 | 2015-04-15 | 25 | 0 |  |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Minor Construction (UMMC) | WI | WISCONSIN | Portage | 550161 | National Guard Readiness Center Addition | 2013-09-24 | 2013-09-25 | Miron Construction Contract #: NGB-47-13-C-0009 | 1920000 | 907652.16 | 2013-12-12 | 2014-09-01 | 2015-07-01 | 2014-08-01 | 70 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | FL | FLORIDA | Pinellas Park | 120195 | Ready Building | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. Contract #: 120195 D-B Kokolakis | 5700000 | 5300000 | 2014-04-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0 | 0 |  |  | Used FY10 funds only
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | IL | ILLINOIS | Kankakee | 170033 | National Guard Readiness Center | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. Contract #: W91SMC-14-2-2004-100 | 16000000 | 16000000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | IL | ILLINOIS | Kankakee | 170127 | Aircraft Maintenance Hangar | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. Contract #: W91SMC-14-2-2003-100 | 30000000 | 30000000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260051 | Enlisted Barracks, Transient Training | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. Contract #: Y14290 | 17398000 | 17398000 | 2014-08-11 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | MS | MISSISSIPPI | Pascagoula | 280272 | National Guard Readiness Center | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated Contract #: NGB-22-14-C-0003-S | 4718338 | 4718338 | 2014-07-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280423 | Water Supply/Treatment Building, Potable | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors Contract #: NGB22-14-C-0005-S | 3000000 | 2581230 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | MO | MISSOURI | Macon | 290191 | National Guard Vehicle Maintenance Shop | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. Contract #: T1227-01C | 9100000 | 7087939.1 | 2015-05-12 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | MO | MISSOURI | Whiteman AFB | 290221 | Aircraft Maintenance Hangar | 2014-06-26 | 2014-07-10 | Blackhawk Joint Venture Contract #: W912NS-14-R-1000 | 5000000 | 4317000 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Major Construction | WY | WYOMING | Afton | 560081 | National Guard Readiness Center | 2013-12-16 | 2014-03-11 | Layton Construction Company, Inc. Contract #: 13002900601 | 10200000 | 9747750 | 2013-10-10 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 4 | 0
2014-07-31 | 2014-08-05 | 2010 | DoDEA | Major Construction | GA | GEORGIA | Fort Stewart | AM 856 07 | New Elementary School | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | 19764 | 20534 | 2012-08-01 | 2014-07-28 | 2013-12-14 | 2014-03-09 | 94 |  |  |  | As reported by the Construction Agent (USACE )
2014-07-31 | 2014-08-05 | 2010 | DoDEA | Major Construction | DEU | GERMANY | Ramstein AB | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | 15509 | 17636 | 2011-05-09 | 2013-09-13 | 2013-01-19 | 2013-01-19 | 99
2014-07-31 | 2014-08-05 | 2010 | DoDEA | Major Construction | DEU | GERMANY | USAG Stuttgart | EUR 8320 03 | Replace School (Boblingen ES) | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | 46695 | 48232 | 2013-07-29 | 2015-06-30 | 2015-04-30 | 2015-04-30 | 39
2014-07-31 | 2014-08-05 | 2010 | DoDEA | Major Construction | BEL | BELGIUM | USAG Benelux | EUR 8318 09 | Replace School (SHAPE ES) | 2011-07-07 | 2011-12-09 | Besix SA | 31415 | 32686 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-31 | 95
2014-07-31 | 2014-08-05 | 2010 | DoDEA | Major Construction | BEL | BELGIUM | USAG Benelux | EUR 8318 09 | Replace School (SHAPE ES) | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | 1652 | 1719 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2015-07-23 | 95
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | DEU | GERMANY | USAG Stuttgart | EUR 8268 02 | Replace School ( Boblingen HS) | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | 41869 | 43416 | 2013-07-29 | 2015-06-29 | 2015-04-30 | 2015-06-23 | 36
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | NY | NEW YORK | West Point MILRES | AM2455205 | Construct Addition and Renovate MS | 2011-07-18 | 2011-10-20 | Bernard Associates | 23974 | 25875 | 2011-11-28 | 2015-01-04 | 2014-09-28 | 2014-11-25 | 99
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | BEL | BELGIUM | USAG Benelux | D9124-1 | Replace Schools (SHAPE MS/HS) | 2012-04-18 | 2011-12-09 | Besix SA | 26260 | 26929 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-31 | 95
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | BEL | BELGIUM | USAG Benelux | D9124-1 | Replace Schools (SHAPE MS/HS) | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | 5843 | 6002 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2015-07-23 | 95
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | BEL | BELGIUM | USAG Benelux | D9124-1 | Replace Schools (SHAPE MS/HS) | 2012-04-18 | 2012-07-20 | association besix-cmc jv | 28674 | 28774 | 2012-08-01 | 2014-12-19 | 2015-01-13 | 2015-01-13 | 69
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | NC | NORTH CAROLINA | Fort Buchanan | AM8193 01 | Replace Elementary School (Antilles ES) | 2012-03-16 | 2012-06-12 | Gilbane Building Company | 50968 | 51394 | 2012-07-18 | 2015-04-30 | 2014-04-19 | 2014-05-03 | 40 |  |  |  | As reported by the Construction Agent (USACE )
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | VA | VIRGINIA | MCB Quantico | AM2455206 | Replace/Consolidate Elementary Schools | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | 43242 | 46188 | 2012-09-29 | 2015-04-16 | 2014-09-30 | 2015-06-01 | 75
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | NC | NORTH CAROLINA | Fort Bragg | AM100801 | Replace Elementary School (Murray ES) | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | 14851 | 16356 | 2012-09-12 | 2014-08-15 | 2014-04-03 | 2014-07-15 | 96
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Major Construction | NC | NORTH CAROLINA | Fort Bragg | AMD02051 | Replace Elementary School ( McNair ES) | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | 16413 | 17049 | 2012-09-12 | 2014-08-15 | 2014-04-03 | 2014-07-15 | 96
2014-07-31 | 2014-08-05 | 2012 | DODEA | Major Construction | JPN | JAPAN | Yokota Air Base, Japan | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | 9644 | 9719 | 2013-03-26 | 2015-10-18 | 2015-07-25 | 2015-07-25 | 60
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | NC | NORTH CAROLINA | Fort Bragg | AM00022 | Replace Facility (DSO) | 2012-04-11 | 2012-08-22 | Guerrero Builders, LLC | 3226 | 3235 | 2012-10-02 | 2014-06-10 | 2013-10-02 | 2014-02-16 | 99
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | DEU | GERMANY | USAG Ansbach | EU00053 | Replace Elementary/Middle School (Ansbach EMS) | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | 575 | 575 | 2013-10-28 | 2015-05-29 | 2015-03-12 | 2015-03-16 | 14
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | DEU | GERMANY | USAG Ansbach | EU00053 | Replace Elementary/Middle School (Ansbach EMS) | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | 11784 | 11799 | 2013-10-28 | 2015-05-29 | 2015-03-12 | 2015-03-16 | 14
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | KOR | KOREA | Osan Air Base | PA00020 | Replace Elementary School (Osan ES) | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | 29187 | 29764 | 2013-09-30 | 2016-03-01 | 2015-12-09 | 2015-12-09 | 13
2014-07-31 | 2014-08-05 | 2013 | DoDEA | Major Construction | GA | GEORGIA | Fort Benning | AM00023 | Replace McBride Elementary School | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | 32987 | 32987 | 2013-12-11 | 2016-01-16 | 2015-12-11 | 2015-12-11 | 13
2014-07-31 | 2014-08-05 | 2013 | DoDEA | Major Construction | MA | MASSACHUSETTS | Hanscom Air Force Base | AM00027 | Replace Hanscom Middle School | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | 31687 | 31687 | 2014-02-11 | 2016-08-19 | 2016-04-21 | 2016-04-21 | 9
2014-07-31 | 2014-08-05 | 2013 | DoDEA | Major Construction | KY | KENTUCKY | Fort Campbell | AM00028 | Replace Barkley Elementary School | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | 39362 | 39372 | 2014-03-27 | 2016-03-15 | 2015-12-17 | 2015-12-17 | 3
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | KY | KENTUCKY | Fort Knox | AM00026 | Replace Kingsolver/Pierce School | 2013-03-04 | 2014-02-21 | AWA Wilson JV | 32685 | 32685 | 2014-03-11 | 2016-01-30 | 2015-11-11 | 2015-11-11 | 1
2014-07-31 | 2014-08-05 | 2013 | DoDEA | Major Construction | DEU | GERMANY | USAG Wiesbaden | EU00043 | Replace Wiesbaden High School | 2015-01-30 | 2014-03-07 | Federal Republic of Germany | 0 | 0 | 2014-03-24 | 2014-08-30 | 2014-08-21 | 2014-08-21 | 3 |  |  |  | Contract awarded for temporary facilities only
2014-07-31 | 2014-08-05 | 2013 | DoDEA | Major Construction | DEU | GERMANY | USAG Wiesbaden | EU00043 | Replace Wiesbaden High School | 2015-01-30 | 2014-03-07 | Federal Republic of Germany | 387 | 387 |  | 2015-02-06 | 2014-12-08 | 2014-12-08 | 3 |  |  |  | Contract awarded for temporary facilities only
2014-07-31 | 2014-08-05 | 2013 | DoDEA | Major Construction | DEU | GERMANY | USAG Wiesbaden | EU00043 | Replace Wiesbaden High School | 2015-01-30 | 2014-03-07 | Federal Republic of Germany | 8044 | 8044 |  | 2017-05-22 | 2017-04-22 | 2017-04-22 | 0 |  |  |  | Contract awarded for temporary facilities only
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | NC | NORTH CAROLINA | MCAS New River | AM00025 | Replace Delalio Elementary School | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | 23339 | 23372 | 2014-02-24 | 2016-06-01 | 2016-06-01 | 2017-05-20 | 4
2014-07-31 | 2014-08-05 | 2013 | DODEA | Major Construction | JPN | JAPAN | Kadena Air Base Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | 1475 | 1475 | 2014-07-07 | 2017-01-01 | 2016-10-24 | 2016-10-24 | 0
2014-07-31 | 2014-08-05 | 2013 | DODEA | Major Construction | JPN | JAPAN | Kadena Air Base Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | 2469 | 2469 | 2014-07-07 | 2017-01-01 | 2016-10-24 | 2016-10-24 | 0
2014-07-31 | 2014-08-05 | 2013 | DODEA | Major Construction | JPN | JAPAN | Kadena Air Base Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | 4612 | 4612 | 2014-07-07 | 2017-01-01 | 2016-10-24 | 2016-10-24 | 0
2014-07-31 | 2014-08-05 | 2013 | DODEA | Major Construction | JPN | JAPAN | Kadena Air Base Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | 62418 | 62418 | 2014-07-07 | 2017-01-01 | 2016-10-24 | 2016-10-24 | 0
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | DEU | GERMANY | USAG Grafenwoehr | EU00062 | Netzaberg Middle School Addition | 2014-03-19 | 2014-05-28 | Mickan GmbH | 283 | 283 | 2014-06-05 | 2015-11-10 | 2015-09-26 | 2015-09-26 | 2
2014-07-31 | 2014-08-05 | 2012 | DoDEA | Major Construction | DEU | GERMANY | USAG Grafenwoehr | EU00062 | Netzaberg Middle School Addition | 2014-03-19 | 2014-05-28 | Mickan GmbH | 5366 | 5366 | 2014-06-05 | 2015-11-10 | 2015-09-26 | 2015-09-26 | 2
2014-07-31 | 2014-08-05 | 2013 | DFAS | Military Construction | TX | TEXAS | Red River Army Depot | 80230 | DFAS Facility | 2013-04-24 | 2013-07-30 | Guyco | 12903 |  | 2013-09-11 | 2015-09-15 | 2015-03-15 | 2115-03-15 04:48 | 13 |  |  |  | The site work sub-contractor has increased the man power on site and work has started to speed up. The building pad is now complete with only minor final grading taking place. The electrical sub is installing the building pad is now complete with only minor final grading taking place. The electrical sub is installing the primary underground.
2014-08-05 | 2014-08-05 | 2012 | DSS | Military Construction | VA | VIRGINIA | QUANTICO | P646 | DSS Headquarters Addition | 2012-09-21 | 2013-03-29 | Hensel Phelps Construction Co. | 25149100 | 27587740 | 2013-04-30 | 2014-08-08 | 2014-07-22 | 2014-08-08 | 83.24 |  |  |  | Phase I Solicitation/Advertise Date shown; Phase II - 20-Dec-2012
2014-08-05 | 2014-08-05 | 2012 | DSS | Military Construction | VA | VIRGINIA | QUANTICO | P659 | Defense Access Road Improvements-Telegraph Rd | 2013-01-22 | 2013-07-15 | Shirley Contracting Company, LLC | 2967875 | 2967875 | 2013-08-01 |  | 2014-08-01 | 2014-09-05 | 38.8 |  |  |  | Phase I Solicitation/Advertise Date shown; Phase II - 04-Apr-2013;This project is being managed and funded via FHWA
2014-07-31 | 2014-08-05 | 2008 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities INCR#1 (of 4 Increments) | 2008-02-20 | 2008-09-30 | Nova Group Inc - Underground Construction Company - AJV | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | 0 |  |  | Increments 1-4 awarded
2014-07-31 | 2014-08-05 | 2008 | DLA | MC | PA | PENNSYLVANIA | DLA Distribution New Cumberland | DDCX0702 | Replace Central Heat Plant | 2008-07-14 | 2008-09-28 | John C. Grimberg Company | 19757 | 20611 | 2008-11-03 | 2011-10-21 | 2011-07-21 | 2012-10-21 | 100 | 0
2014-07-31 | 2014-08-05 | 2009 | DLA | MC | CA | CALIFORNIA | DLA Distribution Depot San Joaquin at Tracy | DDCX1002 | Replace General Purpose Warehouse | 2008-11-11 | 2009-03-11 | Whiting Turner Contracting Co. | 29345 | 30469 | 2009-04-02 | 2012-01-05 | 2012-03-17 | 2013-03-20 | 100 | 6558 |  |  | Rescinded per PL 111-117, +$42K from FY12 Davis Monthan
2014-07-31 | 2014-08-05 | 2009 | DLA | MC | FL | FLORIDA | NAV SUP Fleet Logistics Center Jacksonville | DESC0801 | Replace Fuel Storage Tanks | 2009-03-11 | 2009-09-22 | Mid Eastern Builders INC | 22226 | 22640 | 2009-10-30 | 2012-12-31 | 2012-09-22 | 2012-12-15 | 100 | -9000 |  |  | Rescinded per PL 111-117
2014-07-31 | 2014-08-05 | 2009 | DLA | MC | DEU | GERMANY | DLA Distribution Europe at Germersheim | DDCX0904 | Logistics Distribution Center | 2010-02-12 | 2010-05-18 | Wolfe & Muller Regionalbau GmbH & Co. / Peter Gross GmbH & Co. | 34991 | 36800 | 2010-06-16 | 2012-01-25 | 2012-01-04 | 2012-01-04 | 100 | -10400 |  |  | Rescinded by 0SD 24 May 11A
2014-07-31 | 2014-08-05 | 2009 | DLA | MC | HI | HAWAII | NAV SUP Fleet Logistics Center Pearl Harbor | DESC0808 | Replace Fuel Pipeline | 2009-05-01 | 2009-06-12 | Watts Construction LLC | 17336 | 24695 | 2009-07-12 | 2012-12-30 | 2011-07-12 | 2013-09-30 | 99 | -5300 |  |  | Rescinded per PL 111-117
2014-07-31 | 2014-08-05 | 2009 | DLA | MC | NM | NEW MEXICO | Kirtland Air Force Base | DESC0802 | Replace Fuel Storage Tanks | 2009-04-06 | 2009-08-20 | Kinley Construction | 7355 | 7762 | 2009-10-14 | 2011-03-18 | 2011-06-11 | 2011-06-11 | 100 | -5900 |  |  | Rescinded per PL 111-117, PROJECT COMPLETE
2014-07-31 | 2014-08-05 | 2009 | DLA | MC | UT | UTAH | Hill Air Force Base | DESC0608 | Hydrant Fuel System | 2009-01-29 | 2009-05-22 | Rockford Corp | 14636 | 15416 | 2009-06-18 | 2011-04-21 | 2011-05-13 | 2011-05-13 | 100 | -3000 |  |  | Rescinded by 0SD 24 May 11A, PROJECT COMPLETE
2014-07-31 | 2014-08-05 | 2009 | DLA | MC | VA | VIRGINIA | Defense Fuel Support Point Craney Island | DESC0703 | Replace Fuel Storage Tanks | 2009-04-01 | 2009-07-31 | Mid Eastern Builders INC | 36371 | 38331 | 2009-09-03 | 2012-12-29 | 2012-08-29 | 2013-09-30 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) | 2008-02-20 | 2011-03-22 | Nova Group Inc - Underground Construction Company - AJV | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | 0 |  |  | Increments 1-4 awarded
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | CA | CALIFORNIA | Travis Air Force Base | DESC0803 | Replace Fuel Distribution System | 2010-11-10 | 2011-02-18 | Kinley Construction | 12637 | 14208 | 2011-05-10 | 2013-05-20 | 2012-08-26 | 2013-08-31 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | FL | FLORIDA | Jacksonville International Airport | DESC0908 | Replace Jet Fuel Storage Complex | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | 7909 | 9988 | 2010-04-27 | 2014-04-09 | 2011-09-20 | 2014-09-30 | 99 | -1900 |  |  | Rescinded by 0SD 18 May 11A
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | MN | MINNESOTA | Duluth Air National Guard | DESC1002 | Replace Jet Fuel Storage Complex | 2010-03-10 | 2010-07-16 | Talon Industries Inc. | 11195 | 11195 | 2010-08-30 | 2012-01-12 | 2011-11-01 | 2012-01-09 | 100 | -2000 |  |  | Rescinded by 0SD 18 May 11A, PROJECT COMPLETE
2014-07-31 | 2014-08-05 | 2010 | DLA | UMMC | NC | NORTH CAROLINA | Marine Corps Air Station New River | DESC11S3 | Replace Pump Station | 2010-02-20 | 2010-09-29 | North State Mechanical Inc. | 947 | 1047 | 2011-01-15 | 2012-11-16 | 2011-12-08 | 2012-08-10 | 100 | 0
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | CUB | CUBA | Naval Station Guantanamo Bay | DESC0904 | Replace Fuel Storage Tank | 2010-01-19 | 2010-05-27 | Toltest, Inc | 8594 | 8658 | 2010-05-27 | 2011-11-28 | 2012-11-28 | 2012-11-28 | 100 | -2200 |  |  | Rescinded by 0SD 18 May 11A, PROJECT COMPLETE
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | GRC | GREECE | Naval Support Activity Souda Bay, Crete | DESC0707A | Fuel Tanks and Pipeline Replacement | 2010-01-29 | 2010-09-30 | AKTORS, S.A. | 19667 | 21060 | 2010-01-12 | 2013-07-06 | 2012-07-09 | 2013-07-06 | 100 | -8250 |  |  | Rescinded by 0SD 18 May 11A
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | KOR | KOREA | Osan Air Base | DESC0907 | Hydrant Fuel System | 2010-01-12 | 2010-04-16 | Namwha Construction Co. | 17844 | 19441 | 2010-08-27 | 2014-12-26 | 2013-11-18 | 2014-10-27 | 93 | -2789 |  |  | Rescinded by 0SD 18 May 11A
2014-07-31 | 2014-08-05 | 2010 | DLA | MC | GBR | UNITED KINGDOM | Royal Air Force Base Mildenhall | DESC0910 | Connect Fuel Tank to Distribution Pipeline | 2010-04-23 | 2010-09-16 | Entrepose Industrial Services | 3300 | 3300 | 2011-03-07 | 2013-03-04 | 2011-08-18 | 2011-12-16 | 100 | 0 |  |  | PROJECT COMPLETE
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) | 2008-02-20 | 2011-03-30 | Nova Group Inc - Underground Construction Company - AJV | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | 0 |  |  | Increments 1-4 awarded
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | CA | CALIFORNIA | Naval Base Ventura County, Point Mugu | DESC10S4 | Aircraft Direct Fueling Station | 2011-04-29 | 2011-06-30 | RORE, INC. | 2553 | 2733 | 2011-07-30 | 2013-06-07 | 2012-07-15 | 2013-06-07 | 100 | 0 |  |  | PROJECT COMPLETE
2014-07-31 | 2014-08-05 | 2011 | DLA | UMMC | CA | CALIFORNIA | Edwards Air Force Base | DESC11U1 | Truck Offload Facility | 2012-03-16 | 2012-07-12 | Kinley Construction Company | 1019 | 1019 | 2012-07-26 | 2013-09-30 | 2013-09-30 | 2013-08-31 | 100 | 0
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | GA | GEORGIA | Hunter Army Arifield | DESC11S4 | Fuel Unload Facility | 2011-06-03 | 2011-09-15 | Ponds Constructors, Inc | 1199 | 1398 | 2011-10-26 | 2013-12-30 | 2012-10-31 | 2013-12-30 | 100 | -980 |  |  | Rescinded by OSD 23 Mar 12A, Design-Build Effort
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | HI | HAWAII | Hickam Air Force Base | DESC1190 | Alter Fuel Storage Tanks | 2011-01-03 | 2011-05-26 | Reliable Contracting Group, LLC | 7584 | 8078 | 2011-06-22 | 2012-12-17 | 2012-12-13 | 2013-08-30 | 100 | 0
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | ID | IDAHO | Mountain Home Air Force Base | DESC1113 | Replace Fuel Storage Tanks | 2011-03-30 | 2011-09-02 | Garco Construction, Inc. | 16480 | 17158 | 2011-10-12 | 2014-05-28 | 2012-04-12 | 2014-07-27 | 100 | -8380 |  |  | Rescinded by OSD 23 Mar 12A
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | MD | MARYLAND | Andrews Air Force Base | DESC1003 | Replace Fuel Storage and Distribution Facilities | 2011-05-15 | 2011-10-31 | MEB General Contractors | 7971 | 8470 | 2011-11-21 | 2013-10-16 | 2013-05-03 | 2013-10-16 | 100 | -4872 |  |  | Rescinded by OSD 23 Mar 12A
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | PA | PENNSYLVANIA | DLA Distribution New Cumberland | DDCX0802 | Replace Headquarters Facility | 2011-11-23 | 2012-08-17 | Walsh Construction | 80775 | 82555 | 2012-08-30 | 2016-02-29 | 2015-09-18 | 2015-12-27 | 52 | 0
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | OH | OHIO | DLA Land and Maritime Columbus | DSCC0802 | Replace Public Safety Facility | 2011-04-04 | 2011-10-21 | Industria Paschen Group JV | 5883 | 6197 | 2011-11-10 | 2013-03-01 | 2013-03-21 | 2013-07-09 | 99 | 0
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | VA | VIRGINIA | Defense Fuel Support Point Craney Island | DESC0909 | Replace Fuel Pier | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | 28815 | 32208 | 2012-11-26 | 2014-08-29 | 2014-07-03 | 2014-11-12 | 71 | -9428 |  |  | Rescinded by OSD 23 Mar 12A
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | JPN | JAPAN | Kadena Air Base Okinawa | DESC11S1 | Install Fuel Filter/Separators | 2010-10-07 | 2011-06-27 | Nippo Corporation | 1175 | 1175 | 2011-07-13 | 2012-11-09 | 2012-10-27 | 2012-10-27 | 100 | 0 |  |  | PROJECT COMPLETE
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | JPN | JAPAN | Misawa Air Base | DESC0503 | Hydrant Fuel System | 2012-05-12 | 2012-09-22 | Tokyo Construction Co., Ltd. | 25204 | 25425 | 2013-02-01 | 2015-07-01 | 2015-02-01 | 2015-03-01 | 66 | 0
2014-07-31 | 2014-08-05 | 2011 | DLA | MC | GBR | UNITED KINGDOM | Royal Air Force Base Mildenhall | DESC0905 | Replace Hydrant Fuel System | 2011-04-19 | 2011-12-06 | Spiecapag | 12535.429 | 12535 | 2011-12-09 | 2014-04-25 | 2013-03-14 | 2014-05-02 | 99 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | AK | ALASKA | Eielson Air Force Base | DESC1108 | Upgrade Rail Line | 2012-02-29 | 2012-07-06 | G2 Construction, Inc. | 12210 | 12407 | 2012-07-16 | 2013-12-08 | 2013-12-05 | 2014-06-15 | 100 | -1500 |  |  | Sequestration, Diverted to FY14 Moody, FY09 Tracy
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | AZ | ARIZONA | Davis Monthan Air Force Base | DESC1103 | Replace Hydrant Fuel System | 2012-05-04 | 2012-09-25 | Nova Group Inc. | 18252 | 19125 | 2012-11-13 | 2014-06-16 | 2014-11-03 | 2015-02-09 | 99 | -1474 |  |  | Diverted to FY12 Altus, FY12 JB PH-H Trck Prkng
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | CA | CALIFORNIA | NAVBASE Coronado, San Clemente Island | DESC1205 | Replace Fuel Facilities | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | 27453 | 27610 | 2013-02-28 | 2015-03-11 | 2015-03-24 | 2015-07-01 | 69 | 9000 |  |  | Additional funds Formal Reprogramming FY09 Germersheim
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | CA | CALIFORNIA | NAV SUP Fleet Logistics Center San Diego, Point Loma | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) | 2008-02-20 | 2012-03-29 | Nova Group Inc - Underground Construction Company - AJV | 15512 | 164864 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 99 | -7000 |  |  | 10 USC 2853 submitted 23 Apr 12. Increments 1-4 awarded
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | CA | CALIFORNIA | DLA Distribution Tracy | DDCX1102 | Public Safety Facility | 2012-03-06 | 2012-07-16 | MASCON, INC | 14615 | 15091 | 2012-08-29 | 2014-12-05 | 2014-03-24 | 2014-12-08 | 86 | 900 |  |  | Additional Funds from FY09 Bid Savings (Hunter, Hill)
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | FL | FLORIDA | Naval Air Station Whiting Field | DESC12S3 | Truck Load/Unload Facility | 2012-01-13 | 2012-03-21 | Weston Solutions Inc. | 2500 | 3167 | 2012-03-21 | 2014-02-21 | 2013-03-24 | 2014-04-24 | 99 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | HI | HAWAII | Joint Base Pearl Harbor-Hickam | DESC12S5 | Upgrade Refueler Parking Area | 2011-10-21 | 2012-03-13 | RAASS Brothers INC | 5079 | 5681 | 2012-08-05 | 2013-09-26 | 2013-04-09 | 2013-09-26 | 100 | 99 |  |  | From FY12 Daivs Monthan
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | HI | HAWAII | Joint Base Pearl Harbor-Hickam | DESI1101 | Alter Warehouse Space | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | 5500 | 6430 | 2012-08-13 | 2014-03-03 | 2013-06-14 | 2014-04-29 | 97 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | LA | LOUISIANA | Barksdale Air Force Base | DESC1106 | Hydrant Fuel System | 2011-10-04 | 2012-01-30 | Thrash Commercial Contractors INC | 4687 | 5470 | 2012-02-28 | 2013-08-02 | 2013-03-14 | 2013-08-16 | 100 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | MA | MASSACHUSETTS | Westover Air Reserve Base | DESC1102 | Upgrade Hydrant Fuel System | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | 24480 | 25378 | 2013-06-18 | 2016-02-08 | 2016-02-02 | 2016-02-08 | 37 | 4500 |  |  | Additional fund Formal Reprogramming (FY09 Hill, Hunter, Germersheim)
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | MS | MISSISSIPPI | Columbus Air Force Base | DESC11S2 | Replace Refueler Parking Facility | 2012-02-14 | 2012-04-30 | Reliable Contracting Group, LLC | 2360 | 2424 | 2012-06-07 | 2013-06-18 | 2013-06-18 | 2013-06-18 | 100 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | OH | OHIO | DLA Land & Maritime Columbus | DSCC1201 | Security Enhancements | 2012-02-19 | 2012-05-04 | Pinnacle Construction Development Group | 8550 | 10318 | 2012-06-07 | 2014-07-18 | 2013-09-23 | 2014-10-16 | 89 | 1568 |  |  | Additional funds form FY12 Pt. Loma, Eielson; FY10 Osan $1M
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | OK | OKLAHOMA | Altus Air Force Base | DESC1201 | Replace Fuel Transfer Pipeline | 2012-03-26 | 2012-09-17 | Reliable Contracting Group, LLC | 8856 | 8671 | 2012-10-17 | 2013-12-23 | 2014-03-01 | 2013-12-23 | 99 | 1407 |  |  | Additional funds from Davis Monthan
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | PA | PENNSYLVANIA | DLA Distribution New Cumberland | DDCX1203 | Upgrade Access Control Points | 2013-04-17 | 2013-09-30 | the Matthews Group | 16327 | 16327 | 2014-02-04 | 2016-03-21 | 2016-03-21 | 2016-03-21 | 6 | 154 |  |  | Additional funds from FY12 Pt. Loma
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | PA | PENNSYLVANIA | DLA Distribution New Cumberland | DDCX1202 | Replace General Purpose Warehouse | 2012-09-17 | 2013-11-20 | Corothers Constuction Inc | 24622 | 24622 | 2014-01-14 | 2015-07-20 | 2015-07-29 | 2015-09-05 | 24 | 3802 |  |  | Additional funds from Formal Reprogramming from FY10 Duluth $1.651M, Osan $2.151M
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | PA | PENNSYLVANIA | DLA Troop Support Philadelphia | DSCP1201 | Upgrade HVAC System | 2012-03-28 | 2012-06-01 | WU & Associates, Inc | 4775 | 7240 | 2012-06-14 | 2014-04-29 | 2013-07-17 | 2014-04-25 | 99 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | SC | SOUTH CAROLINA | Charleston Air Force Base | DESC1101 | Replace Fuel Storage Facility | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | 26085 | 26485 | 2012-11-30 | 2014-07-21 | 2014-07-21 | 2014-11-26 | 87 | 5132 |  |  | Additional funds from Formal Reprogramming (FY10 Duluth, FY11 Osan, FY12 Pt. Loma)
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | WA | WASHINGTON | McChord Air Force Base | DESC1004 | Replace Hydrant Fuel System | 2011-10-28 | 2012-02-02 | Garco Construction, Inc. | 10217 | 10660 | 2012-02-27 | 2013-09-24 | 2013-05-17 | 2013-09-30 | 100 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | WA | WASHINGTON | NAS Whidbey Island | DESC1104 | Replace Fuel Pipeline | 2012-03-20 | 2013-02-28 | Talon Industries Inc. | 16984 | 17506 | 2013-02-28 | 2014-09-15 | 2014-08-30 | 2014-09-20 | 98 | 0
2014-07-31 | 2014-08-05 | 2012 | DLA | MC | WV | WEST VIRGINIA | Camp Dawson | DESC12S1 | Replace Hydrant Fuel System | 2012-04-26 | 2012-07-05 | Kinley Construction Company | 1930 | 1945 | 2012-07-03 | 2014-05-30 | 2013-12-05 | 2014-04-30 | 98 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | AZ | ARIZONA | MCAS Yuma | DESC13S4 | Replace Truck Unload Facility | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | 1322 | 1322 | 2013-09-30 | 2014-08-03 | 2014-08-03 | 2014-08-03 | 6 | 400 |  |  | Additional funds from Formal Reprogramming from FY12 Eielson
2014-07-31 | 2014-08-05 | 2013 | DLA | UMMC | CA | CALIFORNIA | DLA Distribution Tracy | DRMS12U2 | Warehouse 6 Distribution | 2013-05-01 | 2013-05-15 | Kinley Construction Company | 925 | 925 | 2013-06-01 | 2014-10-18 | 2013-12-05 | 2013-12-25 | 100 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | CA | CALIFORNIA | Edwards AFB | DESC1304 | Replace Fuel Storage | 2013-05-23 | 2013-09-27 | Nova Group Inc. | 19513 | 19661 | 2013-11-20 | 2017-03-17 | 2016-10-18 | 2017-12-07 | 9 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | CA | CALIFORNIA | NAVBASE Point Loma | DESC 1306 | Replace Fuel Pier | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | 66378 | 66378 | 2014-01-15 | 2017-10-14 | 2017-10-14 | 2017-10-15 | 19 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | DE | DELAWARE | Dover AFB | DESC1305 | Replace Truck Off-Load Facility | 2013-07-31 | 2013-09-26 | Reliable Contracting Group, LLC | 1800 | 1800 | 2013-12-06 | 2015-02-27 | 2015-02-27 | 2015-02-27 | 0 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | FL | FLORIDA | Hurlburt AFB | DESCV1391 | Construct Fuel Storage Facility | 2013-01-13 | 2013-08-01 | Nova Group Inc | 15952 | 15952 | 2013-10-31 | 2015-12-15 | 2015-09-14 | 2015-10-04 | 22 | 1955 |  |  | Additional funds from FY09 Jax $1.536M, Osan $419K
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | CUB | CUBA | Naval Station Guantanamo Bay | DESC1203 | Replace Fuel Pier | 2013-08-23 | 2013-10-03 | URS Group | 36366 | 36366 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 3 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | CUB | CUBA | Naval Station Guantanamo Bay | DESC13S3 | Replace Truck Loading Facility | 2013-08-23 | 2013-10-03 | URS Group | 1961 | 1961 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 1 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | GU | GUAM | Anderson AFB | DESC1303 | Upgrade Fuel Pipeline | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | 52364 | 52364 | 2014-06-30 | 2016-05-11 | 2016-02-06 | 2016-02-06 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | LA | LOUISIANA | Barksdale Air Force Base | DESC1390 | Upgrade Pumphouse | 2012-10-30 | 2013-08-13 | Environmental Management Resources | 4311 | 4311 | 2013-09-09 | 2015-02-26 | 2015-02-26 | 2015-02-26 | 28 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | NC | NORTH CAROLINA | Seymour Johnson AFB | DESC13S1 | Replace Transfer Fuel Line to Pump House #2 | 2013-02-27 | 2013-07-09 | Shaw Environmental & Infrastructure, Inc | 1494 | 1542 | 2013-07-25 | 2014-10-22 | 2014-04-18 | 2014-09-22 | 44 | 0
2014-07-31 | 2014-08-05 | 2013 | DLA | MC | PA | PENNSYLVANIA | DLA Distribution New Cumberland | DDCX1303 | Replace Sewage Treatment Plant | 2013-08-01 | 2014-06-27 | Johnston Construction Company | 9600 | 9600 | 2014-07-28 | 2016-03-20 | 2016-01-21 | 2016-01-21 | 0 | 5000 |  |  | Additional funds from Formal Reprogramming from FY10 Pt Loma $2M, Guantanamo $1M, Souda Bay $1M; FY11 Pt Loma $1M
2014-07-31 | 2014-08-05 | 2014 | DLA | UMMC | CA | CALIFORNIA | NAVBASE Point Loma | DESC14U1 | Upgrades to Fuel Pier for Fire Protection | 2014-05-01 | 2014-07-17 | CB&I Federal Services | 1019 | 1019 | 2014-07-17 | 2015-01-15 | 2015-01-15 | 2015-01-15 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | DLA | MC | FL | FLORIDA | Naval Support Activity, Panama City | DESC11U2 | Replace Ground Vehicle Fueling Facility | 2014-03-28 | 2014-04-24 | Gelbane Federal | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | DLA | MC | FL | FLORIDA | Naval Station Mayport (Jacksonville) | DESC1402 | Replace Fuel Pipeline | 2014-01-16 | 2014-04-17 | Industrial Power Systems | 5438 | 5438 | 2014-06-30 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 0 | 0
2014-07-31 | 2014-08-05 | 2014 | DLA | MC | GA | GEORGIA | Moody AFB | DESC14S2 | Replace Ground Vehicle Fueling Facility | 2014-03-18 | 2014-04-14 | Pond Constructors Inc | 3780 | 3780 | 2014-05-15 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 0 | 440 |  |  | Additional Funds from FY12 Eielson
2014-07-31 | 2014-08-05 | 2014 | DLA | MC | JPN | JAPAN | Naval Air Station Atsugi | DESC15S1 | Repair Groung Vehicle Fueling Facility | 2014-05-02 | 2014-06-29 | Ichibo Company Limited | 1800 | 1800 | 2014-08-21 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 0
2014-07-31 | 2014-08-05 | 2014 | DLA | MC | ND | NORTH DAKOTA | Minot AFB | DESC1107 | Replace Fuel Pipeline | 2014-02-28 | 2014-06-13 | Reliabel Contracting Group, LLC | 4092 | 4092 | 2014-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 0 | 0
2014-07-31 | 2014-08-06 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | 61772 | Operations Complex | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 16751 | 17555 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 95 | 5495
2014-07-31 | 2014-08-06 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | AFSOC033003 | Vehicle Maintenance Facility | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 4575 | 4854.8575 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 95 | 2821
2014-07-31 | 2014-08-06 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | AFSOC033005 | Storage Facility | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 3603 | 3766.2116 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 95 | 1696
2014-07-31 | 2014-08-06 | 2008 | SOCOM | Major Construction | QAT | QATAR | Al Udeid | AFSOC033019 | Air Operations Center | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 2931 | 3078.5666 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 95 | -1747
2014-07-31 | 2014-08-06 | 2009 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ043010 | Maintenance Hangar/ AMU | 2009-07-15 | 2009-09-28 01:00 | Big D Construction Corp | 10882 | 11675.516 | 2009-11-10 | 2012-02-06 | 2011-05-09 | 2012-02-02 | 99 | -5417
2014-07-31 | 2014-08-06 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 66315 | Operations Addition North | 2010-04-27 | 2010-08-05 01:00 | Sauer, Inc. | 18649 | 20655 | 2010-08-25 | 2014-10-20 | 2013-02-10 | 2014-07-22 | 97 | -3756
2014-07-31 | 2014-08-06 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 64484 | Operations Additions | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | 13388 | 15047 | 2011-08-25 | 2015-05-08 | 2014-06-10 | 2014-12-09 | 80 | 1202
2014-07-31 | 2014-08-06 | 2011 | SOCOM | Major Construction | GA | GEORGIA | Ft Benning | 65395 | Company Support Facility | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | 15392 | 15637 | 2011-12-27 | 2014-07-31 | 2013-06-12 | 2014-07-31 | 97 | -1528
2014-07-31 | 2014-08-06 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 66362 | C4 Facility - JSOC | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | 41446 | 43744 | 2012-06-14 | 2015-02-01 | 2014-06-26 | 2014-07-21 | 92 | 8466
2014-07-31 | 2014-08-06 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69573 | Admin/Company Operations | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | 8487 | 9166 | 2011-10-27 | 2013-11-21 | 2013-04-18 | 2014-01-23 | 99 | 19
2014-07-31 | 2014-08-06 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063049 | Hangar / AMU (MC-130J) | 2011-05-13 | 2011-09-09 | Speegle Construction | 19432 | 20310.9637 | 2011-10-11 | 2014-05-09 | 2013-10-30 | 2014-05-15 | 99 | -309
2014-07-31 | 2014-08-06 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ063052A | Operations & Training Complex (3rd UAS) | 2011-04-15 | 2011-10-26 | Speegle Construction | 13614 | 13700.7721 | 2012-09-06 | 2014-06-03 | 2013-07-17 | 2014-06-03 | 99 | -7389
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 60272 | Communications Training Complex (SWCS) | 2012-04-11 | 2012-07-24 | GSC Construction Inc. | 8290 | 8464 | 2012-09-12 | 2014-11-13 | 2013-08-23 | 2014-05-27 | 68 | -72
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 60821 | Squadron Headquarters Addition | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | 10605 | 10839 | 2012-06-06 | 2014-11-25 | 2013-12-09 | 2014-09-26 | 77 | 1352
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | KY | KENTUCKY | Ft Campbell | 66598 | Rotary Wing Hangar | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | 34350 | 34948 | 2012-04-16 | 2014-05-07 | 2014-02-28 | 2014-04-07 | 73 | -170
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69458 | Battalion Operations Complex | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors | 16722 | 16772 | 2012-12-10 | 2014-10-01 | 2014-06-03 | 2014-06-03 | 30 | -389
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69758 | Brigade Headquarters | 2012-05-09 | 2012-09-17 | JAAAT Technical Services | 15650 | 16348 | 2012-11-14 | 2014-09-05 | 2014-05-08 | 2014-05-08 | 15 | 800
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 71224 | Group Headquarters | 2012-06-06 | 2012-09-25 | Engineering Design Technologies | 18526 | 18382 | 2012-11-07 | 2014-08-29 | 2014-06-20 | 2014-07-05 | 53 | -892
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | WA | WASHINGTON | Ft Lewis | 76363 | Company Operations Facility | 2012-04-18 | 2012-08-30 | Adept - Absher 1 Joint Venture | 18751 | 18995 | 2012-10-09 | 2014-06-21 | 2014-04-22 | 2014-08-19 | 98 | 59
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 76364 | Battalion Operations Facility | 2012-06-20 | 2012-10-25 | Engineering Design Technologies | 29232 | 28974 | 2012-10-25 | 2014-10-27 | 2014-07-28 | 2015-01-08 | 37 | -690
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | FL | FLORIDA | Eglin AFB | 76366 | Company Operations Facility (GSTB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | 16664 | 15558 | 2012-09-12 | 2016-04-26 | 2014-06-27 | 2016-01-27 | 54 | 1736
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | FL | FLORIDA | Eglin AFB | 76371 | Company Operations Facility (GSB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | 19093 | 17143 | 2012-09-12 | 2016-04-26 | 2013-09-30 | 2016-01-27 | 54 | 1791
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 76373 | Administrative Annex | 2012-03-01 | 2012-06-21 | GSC Construction Inc | 9771 | 11047 | 2012-08-15 | 2014-06-27 | 2013-12-10 | 2014-06-05 | 72 | -48
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | KY | KENTUCKY | Ft Campbell | 76374 | MH-47 Hangar | 2011-11-28 | 2012-05-07 | Hensel Phelps | 32450 | 33123 | 2012-05-22 | 2014-07-31 | 2014-03-23 | 2014-10-20 | 95 | -623
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073014 | SOF C-130 Sq Ops Facility | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | 7413 | 7874.8241 | 2012-11-09 | 2014-07-11 | 2015-01-06 | 2014-08-10 | 99 | -1727
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073018 | SOF C-130 Wash Rack Hangar | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | 9329 | 9714.6074 | 2012-11-16 | 2014-06-18 | 2014-07-18 | 2014-08-14 | 94 | -72
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ073021 | SOF AMXS Facility | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | 14700 | 14966.2684 | 2013-01-10 | 2014-09-22 | 2014-12-22 | 2014-08-25 | 92 | 1537
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083012A | SOF Hangar/AMU | 2012-04-20 | 2012-08-31 | Hensel Phelps | 28160 | 29105.547 | 2012-10-24 | 2015-01-05 | 2014-12-23 | 2014-09-07 | 93 | -499
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083014 | SOF ADAL Simulator Facility | 2012-04-17 | 2012-09-07 | PACE Pacific Corporation | 7349 | 7630 | 2012-10-03 | 2014-03-25 | 2014-01-26 | 2014-02-04 | 99 | -141
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083016 | SOF Squadron Operations Facility | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | 10615 | 11040 | 2012-11-09 | 2014-05-30 | 2015-01-06 | 2014-05-30 | 99 | -4292
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | FL | FLORIDA | Hurlburt Field | FTEV103011 | SOF Simulator Facility | 2012-05-01 | 2012-08-09 | Barlovento LLC. | 5551 | 5543 | 2012-09-13 | 2014-07-18 | 2013-12-24 | 2014-07-18 | 99 | -34
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | CA | CALIFORNIA | Camp Pendleton | P-1049 | Range 130 Support Projects | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | 8129 | 8130 | 2013-06-03 | 2015-03-24 | 2014-11-13 | 2014-11-13 | 11 | 675
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | CA | CALIFORNIA | Camp Pendleton | P-1174 | MWD Facility | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | 3075 | 3302 | 2012-10-03 | 2014-09-18 | 2014-03-23 | 2014-08-01 | 11
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1285 | Armory Facility Expansion | 2012-01-26 | 2012-05-07 | Team Construction, LLC. | 4004 | 5590 | 2012-07-16 | 2014-04-16 | 2013-08-30 | 2014-04-24 | 94 | -861
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1419 | Milam Aid Station Expansion (1UMC) | 2012-02-29 | 2012-04-19 | Graham Construction | 1465 | 1546 | 2012-08-01 | 2013-08-02 | 2013-04-19 | 2013-12-06 | 95
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1440 | SOF G3-X Training Facilities (5UMC) | 2012-08-20 | 2012-09-27 | Alderman Building Company, Inc. | 1541 | 1570 | 2013-01-15 | 2014-06-15 | 2013-09-22 | 2014-04-22 | 99
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | Dam Neck | P-164 | Logistics Support Facility | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | 11727 | 11727 | 2012-12-09 | 2015-03-02 | 2014-07-24 | 2014-07-24 | 43 | -475
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | JEB Little Creek Ft Story | P-473 | SEAL Team Operations Facility | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | 23366 | 23366 | 2014-08-13 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 8 | -2856
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Minor Construction | VA | VIRGINIA | Dam Neck | P-504 | SOF Operational Vehicle Storage Facility (6UMC) | 2013-03-12 | 2013-05-23 | Richard Brady & Associates, Inc. | 1660 | 1660 | 2013-12-03 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 47
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | AK | ALASKA | Kodiak | P-531 | Cold Weather Maritime Training Facility | 2012-04-30 | 2012-09-27 | Alutiiq Diversified Service, LLC | 17449 | 17449 | 2014-03-04 | 2015-05-06 | 2015-04-15 | 2015-04-15 | 56 | 1387
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | Dam Neck | P-769 | Building Renovation | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | 3022 | 3441 | 2013-01-02 | 2014-08-27 | 2014-06-27 | 2014-06-27 | 72 | -47
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | Dam Neck | P-826 | Military Working Dog Facility | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | 4139 | 4139 | 2012-12-09 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 61 | 292
2014-07-31 | 2014-08-06 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | Pope AFB | TMKH043055 | SOF Training Facility | 2012-01-31 | 2012-04-24 | JAAAT Technical Services, LLC | 4774 | 4737 | 2012-05-31 | 2014-08-29 | 2013-11-22 | 2014-07-26 | 95 | 92
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 65052 | Medical Support Addition | 2013-08-06 | 2013-09-23 | SFL+A Architects | 3200 | 3200 | 2013-10-16 | 2015-04-02 | 2015-08-25 | 2014-12-03 | 11 | -34
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | KY | KENTUCKY | Ft Campbell | 66597 | Landgraf Hangar Extension | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | 3385 | 3385 | 2014-04-29 | 2015-11-20 | 2015-10-21 | 2015-10-21 | 1 | 360
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69287 | Battalion Operations Complex | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | 30907 | 30907 | 2013-10-09 | 2015-08-11 | 2015-05-13 | 2015-05-13 | 4 | -5294
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69382 | Civil Affairs Battalion Complex | 2013-05-31 | 2013-09-27 | Caddell Construction | 25816 | 25816 | 2013-10-16 | 2015-11-12 | 2015-08-14 | 2015-08-14 | 3 | -1202
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | KY | KENTUCKY | Ft Campbell | 69447 | Group Support Battalion Detachment | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | 22123.1802 | 22123.1802 | 2014-04-14 | 2016-04-13 | 2016-02-13 | 2016-02-13 | 2 | -63
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | NC | NORTH CAROLINA | Ft Bragg | 69493 | Sustainment Bde Headquarters | 2013-06-27 | 2014-04-17 | Polote Corporation | 23085 | 23085 | 2014-06-18 | 2016-10-14 | 2016-05-02 | 2016-05-02 | 0 | 2368
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | CO | COLORADO | Ft Carson | 76367 | SOF Battalion Operations Complex | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | 36441 | 36441 |  | 2016-06-16 | 2016-06-16 | 2016-06-16 | 0 | -4444
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Ft Bragg | 79655 | SOF Training Facility (4UMC) | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | 1592 | 1592 | 2013-06-18 | 2014-10-29 | 2014-10-15 | 2014-10-16 | 37
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Ft Bragg | 80233 | SOF Live-Fire Training Tower (6UMC) | 2013-06-16 | 2014-01-22 | Trend Construction, Inc. | 1531.7653 | 1531.7653 | 2014-02-12 | 2015-05-18 | 2015-05-15 | 2015-05-18 | 1
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Minor Construction | CO | COLORADO | Ft Carson | 81483 | Mtn Climb/Rappel Tower (5UMC) | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | 1513 | 1513 | 2013-09-20 | 2014-11-14 | 2014-10-15 | 2014-09-15 | 15
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | NM | NEW MEXICO | Cannon AFB | CZQZ083013 | Combat Parking Apron | 2013-07-12 | 2014-05-22 | Okland/Geneva Joint Venture | 19481.988 | 19481.988 | 2014-06-13 | 2015-08-13 | 2015-08-13 | 2015-08-13 | 0 | -1701
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Minor Construction | NM | NEW MEXICO | Cannon AFB | CZQZ100221 | Parachute Drying Tower (3 UMC) | 2014-03-06 | 2014-07-01 | Speegle Construction | 1547 | 1547 | 2014-07-28 | 2015-05-24 | 2015-05-24 | 2015-05-24 | 0
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | FL | FLORIDA | Duke Field | FTFA113004 | SOF AvFID Ops and MX Facilities | 2013-05-07 | 2013-09-20 | Carothers Construction | 29942 | 29942 | 2013-11-05 | 2017-03-25 | 2016-12-01 | 2016-12-25 | 4 | -3270
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | FL | FLORIDA | MacDill AFB | NVZR083702 | Joint Special Operations University Facility | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | 24753 | 24916 | 2013-11-04 | 2015-09-26 | 2015-09-15 | 2015-06-28 | 8 | -1390
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1218 | Marine Battalion Company/Team Facilities | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | 46370 | 46370 | 2014-02-20 | 2016-01-18 | 2016-03-01 | 2016-01-18 | 13 | -4669
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1393 | Survival Evasion Resistance Escape Trng Fac | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | 46370 | 46370 | 2014-02-20 | 2016-02-25 | 2016-01-18 | 2016-01-18 | 12 | -428
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1410 | SOF EOD Expansion (1UMC) | 2013-09-04 | 2013-09-26 | Quadrant Construction | 1566 | 1566 | 2013-10-15 | 2014-09-22 | 2014-09-22 | 2014-09-22 | 33
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Minor Construction | NC | NORTH CAROLINA | Camp Lejeune | P-1450 | Fires Platoon Storage Facility (7UMC) | 2013-12-20 | 2014-02-13 | Quadrant Construction, Inc | 1459.25 | 1459.25 | 2014-03-13 | 2014-12-10 | 2014-12-13 | 2014-12-10 | 5
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Major Construction | VA | VIRGINIA | JEB Little Creek Ft Story | P-165 | CS/CSS Support Facility | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | 9351 | 9344 | 2014-10-06 | 2015-11-27 | 2015-09-09 | 2015-11-26 | 9 | -391
2014-07-31 | 2014-08-06 | 2013 | SOCOM | Minor Construction | VA | VIRGINIA | JEB Little Creek Ft Story | P-564 | NSWG-4 Paraloft Addition (2UMC) | 2013-06-14 | 2013-09-27 | Royce Homeland JV, LLC | 1308 | 1308 | 2013-10-15 | 2014-12-31 | 2014-12-31 | 2014-12-31 | 2
2014-07-31 | 2014-08-06 | 2014 | SOCOM | Major Construction | CO | COLORADO | Ft Carson | 69446 | Group Support Battalion Detachment | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | 15083.965 | 15083.965 |  | 2016-03-19 | 2016-02-18 | 2016-02-18 | 0
2014-07-31 | 2014-08-06 | 2014 | SOCOM | Major Construction | FL | FLORIDA | Hurlburt Field | FTEV083002 | Add/Alter Operations Facility | 2014-05-26 | 2014-07-30 | Barlovento, LLC | 7048.867 | 7048.867 |  | 2016-08-03 | 2016-08-03 | 2016-08-03 | 0 | 0
2014-07-31 | 2014-08-08 | 2008 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 1 | 2007-10-11 | 2008-02-29 | Hensel Phelps Construction Company | 369605 | 176436 | 2008-04-16 | 2011-01-08 | 2011-04-15 | 2010-10-13 | 100 |  |  |  | Incrementally Funded for FY08
2014-07-31 | 2014-08-08 | 2009 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 2 | 2007-10-11 | 2008-02-29 | Hensel Phelps Contruction Company | 369605 | 130128 | 2008-04-16 | 2011-01-29 | 2011-04-15 | 2010-11-30 | 100 |  |  |  | Incrementally Funded for FY09
2014-07-31 | 2014-08-08 | 2010 | DISA | Military Construction - BRAC | MD | MARYLAND | Fort Meade | DISA 853 | DISA Headquarters, Inc 3 | 2007-10-11 | 2008-02-29 | Hensel Phelps Construction Company | 369605 | 131662 | 2008-04-16 | 2011-02-19 | 2011-04-15 | 2011-01-24 | 100 |  |  |  | 12
2014-07-31 | 2014-08-08 | 2010 | DISA | Military Construction | HI | HAWAII | FORD ISLAND | DISA10-02 | DISA PAC Facility Upgrades | 2010-08-30 | 2010-12-16 | Bulltrack-Watts (Joint Venture) | 12624.5 | 17212.464 | 2010-12-16 | 2013-04-22 | 2010-12-16 | 2013-04-22 | 100 | 300 |  |  | Programmed Amount: $9.6M. Contract Award: $12,624,500 included MILCON ($8.478M) + options for O&M ($2.765M) and Procurement ($1.380M) funded items. Final Project Costs: MILCON: $9.932M; O&M: $6.845M; Procurement: $1.5M. Awaiting final invoice from the contractor. No change.
2014-07-31 | 2014-08-08 | 2011 | DISA | Military Construction | IL | ILLINOIS | SCOTT AFB | DISA10-01 | Field Command Facility Upgrade (Wing Enclosure) | 2011-08-11 | 2011-09-30 | DWG & Associates | 1194 | 924.1 | 2011-10-26 | 2012-12-21 | 2012-09-19 | 2012-11-30 | 100 | -300 |  |  | Programmed Amount $1.385M. Awaiting final invoice from contractor. USACE advised of S&A Leakage for $8.92.
2014-07-31 | 2014-08-08 | 2012 | DISA | Military Construction | IL | ILLINOIS | SCOTT AFB | 68120 | Construct New Facility Scott AFB - Design |  | 2012-05-01 | Burns & McDonnell | 5036.15 | 5183.48 | 2012-05-01 |  | 2013-05-31 | 2013-05-31 | 100 |  |  |  | Design completed May2013.
2014-07-31 | 2014-08-08 | 2010 | DISA | Military Construction | HI | HAWAII | Ford Island | DISA10-02 | Pacific Operations Facility Upgrade | [9 empty] | 0
2014-07-31 | 2014-08-08 | 2011 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | DISA10-01 | Field Command Facility Upgrade | [9 empty] | 0
2014-07-31 | 2014-08-08 | 2012 | DISA | Military Construction | DEU | GERMANY | STUTTGART-PATCH BARRACKS | DISA10-03 | DISA Europe Facility Upgrades - Design |  | 2012-04-10 | Buchart-Horn GMBH (Design) | 205.3 | 205.3 | 2013-04-17 |  | 2012-09-07 | 2012-09-11 | 100 |  |  |  | Design cost $205,337.62 US
2014-07-31 | 2014-08-08 | 2012 | DISA | Military Construction | DEU | GERMANY | STUTTGART-PATCH BARRACKS | DISA10-03 | DISA Europe Facility Upgrades | 2013-01-22 | 2013-05-01 | Way SS & Freytag Ingenieurbau AG | 1387.3 | 1387.3 | 2013-05-16 | 2014-01-11 | 2013-12-11 | 2014-03-01 | 100 |  |  |  | Project descoped .25%. Sprinkler System. Unforeseen requirement to add double sprinkler heads due to false ceiling and additional water tank. Modification for paralleling switchgearr and extending the canopy over building entrance. Available funds to be used. Site pre-work started 16 Sept 13. Testing of generator and paralleling gear conducted 10 Dec 13. Scheduled slipped due to modification to etrance/foyer. Project completed 28 Feb 14 pending punchlist items. DISA Europe has requested mod to contract for additional thermostat on lower level of building for a/c in utility room, realign fire alarm cabling and entrance signage. Funding available. Received proposals for thermostat, signage and realigning fire alarm cabling. Approved signage and cabling proposals. Cost for thermostat is extremely high and needed for the additional is a nice to have. Thermostat proposal cancelled.
2014-07-31 | 2014-08-08 | 2013 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | VDYDS97032 | Construct New Facility Scott AFB - Soil Remediation | 2013-04-05 | 2013-06-27 | Plexus Scientific Corp. | 1339.17 | 1339 | 2013-10-02 |  | 2013-11-23 | 2014-02-01 | 100 | 0 |  |  | Soil Remediation Contract Award Amount: $1.339,170.73 + USACE fees $161,333.27 = $1,500,504. Internal approvals from EPA, site Installation and State requirements coordinated. Phase IV & V excavation completed. Awaiting test results from Phase V excavation cells 4, 9, 11, 15A, 17, 26 & 29 then load out. If failures persit a Phase VI excavation will be required. Relocating hazardous soils from 16B to characterize harmat level. Soil remediaton complete 1 Feb 14, USACE reviewing Plexus (contractor) responses to Illinois EPA comments. Final modification to adjust quantities will result in approximately $500K credit to Government. Contractor has submitted a $435K Request for Equitable Adjustment. USACE reviewing for merit. Final decision to be made end of August 2014.
2014-07-31 | 2014-08-08 | 2013 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | VDYDS97032 | Construct New Facility Scott AFB - Facility Construction | 2013-05-24 | 2013-09-30 | River City | 66994 | 66994 | 2013-12-02 | 2016-05-30 | 2015-12-30 | 2015-12-30 | 24 | 0 |  |  | Revised PA: $77.515M Construction Contract Award: $66,994 on 30 Sept 13 to River City Construction (RCC). Construction Contract does not include the demo of Bldg 3189. This will be a separate contract. Contractor provided NTP letter issued on 9 Oct 13. Groundbreaking Ceremony: 13 Nov 13. Contruction Kickoff/Partnering Session: 14 Nov 13. As noted above Soil Remediation project impacted construction contractor having full access to site, 3 Dec 13 per contract, due to remediation delays (56 days). Construction contractor had full access to site 3 Feb 14, Rebar cage, Auger caset piles installed, Pile caps 100% complete. Placing of steel mesh for 2nd floor to start next week.
2014-07-31 | 2014-08-08 | 2013 | DISA | Military Construction | IL | ILLINOIS | Scott AFB | VDYDS97032 | Construct New Facility Scott AFB - Demo of Bldg 3189 |  |  | TBD | [6 empty] | 0 | 0 |  |  | Estimated Contract Award FY16
2014-07-31 | 2014-08-08 | 2013 | DISA | Military Construction | DEU | GERMANY | STUTTGART-PATCH BARRACKS | DISA13-01 | DISA Europe Facility- Replace/Upgrade UPS and Paralleling Gear |  |  | TBD | [6 empty] | 0 | 0 |  |  | Revised Programmed Amount: $2.224M based on Sequestration Budget Cut. Intial PA: $2.413M MIPR forwarded to USACE on 23 Sept 13. Telcon held with USACE regarding project on 19 Dec 2013. Coordinating SOW for final review due to mission change. Coordinating with legal counsel.
2014-07-31 | 2014-08-08 | 2014 | DISA | Military Construction | HI | HAWAII | FORD ISLAND | DISA14-01 | DISA Pacific Facility Upgrade |  |  | TBD | [6 empty] | 0 | 0 |  |  | Programmed Amount: $2.615M. Developing Statement of Work for redundant chiller which will work in conjunction with Navy's Energy Project (replacement of 2 existing chillers. A chiller load study conducted Apr 2014. Load study results being reviewed. Reviewing revised SOW which includes addressing JIE The Navy's FY14 MILCON Energy Project ($2.019M) will replace two existing DISA PAC chillers. Contract awarded 15 Jul 2014.
2014-07-31 | 2014-08-13 | 2008 | DIA | Major Construction | DC | DISTRICT OF COLUMBIA | DIAC | 154207 | Emergency Back Up Water System | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC | 1012 | 1012 | 2009-10-03 | 2012-01-20 | 2011-09-16 |  | 100 |  |  |  | Approp. - $1,012
2014-07-31 | 2014-08-13 | 2010 | DIA | Major Construction | AL | ALABAMA | MSIC, Redstone Arsenal | DIA10-002 | Design/build construction project to replace MSIC Explosive Ordnance Exploitation (EOE) complex | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company | 12000 | 12003 | 2012-07-20 |  | 2014-01-20 | 2014-05-21 | 98 |  |  |  | Approp. - $12,000; Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Original BOD of 21 May 2014 has passed. New BOD is being extended due to inclement weather delays and change orders pertaining to Life Safety issues. Contractor has asked for an extension to early September 2014 though this has not yet been approved. Project was shut down most of June for EOE operations. Construction activities resumed 30 June 2014.
2014-07-31 | 2014-08-13 | 2010 | DIA | Minor Construction | KOR | KOREA | K16 Air Field | DIA10-001 | FOB-K renovation of two building to include administrative and SCIF space | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd | 4360 | 5050 | 2012-04-09 |  | 2013-10-09 | 2013-10-17 | 100 |  |  |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project in process of closeout.
2014-07-31 | 2014-08-13 | 2010 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA11-002 | JBAB paving of gravel parking lot | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture | 2984 | 2819 | 2011-07-20 | 2012-07-25 | 2012-07-18 | 2012-07-25 | 99 | 700 |  |  | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2014-07-31 | 2014-08-13 | 2012 | DIA | Major Construction | VA | VIRGINIA | JUIAF | DIA12000005 | Construction of Remote Delivery Facility (RDF) meeting SCIF standards | 2013-08-21 | 2013-09-25 | Heard Construction | 10758 | 6058000 | 2013-10-10 |  |  | 2014-11-21 | 23 |  |  |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW title 10, USC 2853. $4.7M returned to DIA in May 2013. The user requested change to add approximately 2K SF of unclassified transit storage space will not be awarded because negotiations with the general contractor could not reach a fair and reasonable cost (the contractor proposal was 211% higher than the government estimate). The contractor this month should complete erecting the structural steel framing and begin erecting the precast panels.
2014-07-31 | 2014-08-13 | 2012 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000001 | DIAC parking garage replacement |  |  | Pennoni Associates, Inc. | 0 | 739156 |  |  |  |  | 0 |  |  |  | Approp. - $13,645 - $793,156 CAT I obligated. NAVFAC Gold Team awarded the A/E contract in June 2013. Conducted the Design Charette on 18 July 2013. First NCPC, CFO and SHPO review conducted on 2 August 2013. 65% design complete and review comments submitted. New site selected. Concept Charette held 29 Apr 14. RFP completed and issued for solicitation. Bids expected mid-August 2014.
2014-07-31 | 2014-08-13 | 2012 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000003 | DIAC chilled water project for data center |  |  | H & A Architects and Engineers | 0 | 0 |  |  |  |  | 0 |  |  |  | Approp. - $1,121 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-07-31 | 2014-08-13 | 2012 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000003 | DIAC cooling tower for data center |  |  | H & A Architects and Engineers | 0 | 0 |  |  |  |  | 0 |  |  |  | Approp. - $941 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-07-31 | 2014-08-13 | 2012 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000002 | Uninterrupted Power Supply (UPS) for data center |  |  | H & A Architects and Engineers | 0 | 1200 |  |  |  |  | 0 |  |  |  | Approp. - $1,076 - NAVFAC awarded the design contract on 30 January 2013. 100% design under review. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-07-31 | 2014-08-13 | 2012 | DIA | Minor Construction | AL | ALABAMA | DIAC | ECIP 120001 | Chiller Plant Optimization |  | 2013-08-08 | Honeywell | 997 |  | 2013-08-21 |  | 2014-08-08 | 2014-08-08 | 53 |  |  |  | Approp. $1,200 - Project awarded August 2013. Kickoff meeting held 5 September 2013. Field measuring devices (flows, temperatures) have been installed. Sensor installations complete. Wiring to field input devices in Bldg 6000A is underway; VFD drive installations in bldg 6000A began week of 03 March 2014. Two within-budget modifications have taken place: 1) to change the total of VFD drives from eight to nine, based on chiller efficiency improvement, and 2) to control the formerly Siemens' chiller plant with Honeywell.
2014-07-31 | 2014-08-14 | 2009 | Army Reserve | Major Construction | NY | NEW YORK | CW2 Kerry P. Hein USARC | 067579 | Shoreham AR Center Unheated Stg | 2009-02-19 | 2009-06-18 | E. W. Howell Company, Inc. | 15041.2 | 16141.3502 | 2009-07-21 | 2014-07-18 | 2011-07-11 | 2014-10-16 | 99.278
2014-07-31 | 2014-08-14 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | James W Reese USARC, PA | 069430 | GTA Chester/Newtown Square Army Reserve Center | 2011-07-28 | 2011-09-29 | Lobar Inc. | 18272 | 18539.236 | 2012-01-18 | 2015-06-20 | 2013-11-08 | 2015-05-21 | 57.7183
2014-07-31 | 2014-08-14 | 2010 | Army Reserve | Major Construction | FL | FLORIDA | ELLIOTT BABCOCK MEMORIAL AFRC | 069471 | GTA West Palm Beach FL Army Reserve Center/Land | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | 16009 | 16319.55 | 2012-05-22 | 2015-01-15 | 2013-09-24 | 2015-01-15 | 72.6458
2014-07-31 | 2014-08-14 | 2010 | Army Reserve | Major Construction | PR | PUERTO RICO | JUAN PONCE DE LEON ARMORY | 069568 | GTA Caguas/Puerto Nuevo ARC | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | 12356.39 | 12640.4564 | 2011-11-15 | 2014-07-31 | 2013-08-06 | 2014-07-21 | 96.4673
2014-07-31 | 2014-08-14 | 2010 | Army Reserve | Major Construction | TX | TEXAS | Comstock, Us Border Patrol Station | 075110 | Corpus Christi (Robstown) Tactical Equipment Maintenance Facility | 2011-10-04 | 2012-01-26 | Leetex Construction LLC | 9433.577 | 9433.577 | 2012-04-05 | 2014-12-18 | 2013-09-12 | 2014-11-20 | 85.8507
2014-07-31 | 2014-08-14 | 2011 | Active Army | Minor Construction - UMMCA | OH | OHIO | Lima Army Tank Center | 074757 | Fire Alarm System | 2012-02-01 | 2012-08-06 | Custom Mechanical Systems, Corp | 1763.338 | 1770.5529 | 2012-09-05 | 2014-04-18 | 2013-08-01 | 2014-03-19 | 76.9113
2014-07-31 | 2014-08-14 | 2011 | Army Reserve | Major Construction | TX | TEXAS | Rio Grand, TX | 069421 | GTA Rio Grande City, TX Army Reserve Center/Land | 2012-02-01 | 2012-07-24 | Highmark Construction Company, LLC | 4454 | 4454 | 2012-08-21 | 2015-06-30 | 2014-03-21 | 2015-08-30 | 5.7379
2014-07-31 | 2014-08-14 | 2011 | Army Reserve | Major Construction | NY | NEW YORK | Binghamton, NY (Utica) | 069599 | GTA Binghamton, NY (Utica) Army Reserve Center/Land | 2012-07-24 | 2012-09-25 | J. Kokolakis Contracting, Inc. | 12353.9 | 12863.5 | 2012-10-25 | 2014-10-03 | 2014-04-03 | 2014-10-03 | 97.0094
2014-07-31 | 2014-08-14 | 2011 | Army Reserve | Major Construction | VA | VIRGINIA | Roanoke, VA | 070641 | GTA Roanoke, VA Army Reserve Center/Land | 2011-08-18 | 2011-11-23 | Anthony & Gordon Construction Co, Inc. | 13345 | 13570.305 | 2012-01-12 | 2014-08-08 | 2013-05-06 | 2014-08-08 | 98.4855
2014-07-31 | 2014-08-14 | 2011 | Army Reserve | Major Construction | IA | IOWA | Fort Sheridan | 070654 | GTA Des Moines IA - Ft. Sheridan Army Reserve Center | 2011-11-15 | 2012-03-14 | The Vertex Companies | 8931.622 | 8952.812 | 2012-04-09 | 2014-10-30 | 2013-08-12 | 2014-10-24 | 84.8063
2014-07-31 | 2014-08-14 | 2011 | Army Reserve | Major Construction | FL | FLORIDA | Tallahassee, FL | 074220 | GTA Tallahassee, FL Army Reserve Center/Land | 2011-05-19 | 2011-09-23 | Liberty Mutual Insurance Company | 8807.148 | 8716.787 | 2011-10-21 | 2014-10-03 | 2013-03-24 | 2014-09-03 | 96.0896
2014-07-31 | 2014-08-14 | 2011 | Army Reserve | Minor Construction - UMMCAR | CA | CALIFORNIA | Fort Hunter Liggett | 074731 | FHL Training Exercise Warehouse | 2011-08-19 | 2012-07-13 | Total Team Construction Services Inc. | 1612.061 | 1612.773 | 2012-09-11 | 2014-09-08 | 2013-08-07 | 2014-08-15 | 60.224
2014-07-31 | 2014-08-14 | 2011 | Army Reserve | Minor Construction - UMMCAR | WA | WASHINGTON | Fairchild AFB, WA | 079128 | Fairchild, WA DEPMEDS | 2013-03-26 | 2013-09-30 | Imperial Construction | 1560.895 | 1560.895 | 2013-10-11 | 2014-11-23 | 2014-09-26 | 2014-09-26 | 41.4065
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 069501 | Unmanned Aerial Vehicle Maintenance Hangar | 2011-12-15 | 2012-09-27 | Archer Western Federal JV | 40397 | 40823.544 | 2012-11-05 | 2015-02-02 | 2014-09-06 | 2014-12-03 | 82.5842
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | NC | NORTH CAROLINA | Greensboro, NC - P2#333014 | 067466 | Greensboro NC Army Reserve Center/Land | 2012-05-15 | 2012-09-18 | IKHANA, LL | 15942 | 15977.219 | 2012-10-10 | 2015-04-14 | 2014-03-19 | 2015-04-14 | 50.2072
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | CO | COLORADO | Fort Collins | 067658 | Ft. Collins, CO Army Reserve Center | 2011-11-29 | 2012-04-16 | Liberty Mutual Insurance Company | 10450.922 | 10580.378 | 2012-05-11 | 2015-03-01 | 2013-10-18 | 2015-03-01 | 56.5668
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | IL | ILLINOIS | Rockford, IL - P2#333015 | 067664 | Rockford IL, Army Reserve Center/Land | 2012-01-17 | 2012-05-02 | Charpie Korte Industries | 10230.744 | 10314.9506 | 2012-06-29 | 2014-07-25 | 2013-12-06 | 2014-07-25 | 98.2976
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | SC | SOUTH CAROLINA | Orangeburg, SC - P2#333016 | 067672 | Orangeburg, SC Army Reserve Center/Land | 2011-11-17 | 2012-03-29 | Group III Mgt. Inc | 10122.796 | 10709.552 | 2012-05-21 | 2014-09-29 | 2013-09-23 | 2014-09-29 | 92.5635
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | IN | INDIANA | Fort Benjamin Harrison | 067673 | Fort Ben Harrison Army Reserve Center | 2012-03-13 | 2012-05-15 | Hunt Construction Group | 44046.206 | 46409.7042 | 2012-05-30 | 2014-08-07 | 2015-01-29 | 2015-03-19 | 98.0174
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 067684 | Ft. McCoy Container Loading Facility | 2011-11-17 | 2012-03-30 | Carntribe-Clement 3, A Joint Venture | 5049.662 | 5211.225 | 2012-06-27 | 2014-08-29 | 2013-10-30 | 2014-08-01 | 87.7925
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | Schenectady, NY - P2#333019 | 067691 | Schenectady, NY Army Reserve Center | 2011-11-17 | 2012-05-03 | SCMC, LLC | 17931 | 18225.1129 | 2012-06-01 | 2014-05-21 | 2014-02-21 | 2014-10-30 | 97.2033
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | IL | ILLINOIS | Homewood, IL - P2#331461 | 067713 | Homewood IL Add/Alt Army Reserve Center | 2012-08-01 | 2012-09-27 | Accel/Pacific J.V. | 13312 | 14211.8549 | 2012-10-18 | 2015-07-12 | 2014-07-10 | 2015-05-18 | 53.3254
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | NAVAL STATION STATEN ISLAND USARC | 069432 | GTA Staten Island Army Reserve Center | 2012-12-27 | 2013-03-06 | MACNAK-Korte Design Build LLC | 14115.817 | 13761.5623 | 2013-04-15 | 2014-09-27 | 2014-07-29 | 2014-08-07 | 86.0133
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | NAVAL STATION STATEN ISLAND USARC | 069432 | Army Reserve Center | 2012-12-27 | 2013-03-06 | MACNAK-Korte Design Build LLC | 14115.817 | 13311.088 | 2013-04-15 | 2014-09-27 | 2014-07-29 | 2014-08-07 | 57.4969
2014-07-31 | 2014-08-14 | 2012 | Army Reserve | Minor Construction - UMMCAR | PA | PENNSYLVANIA | Coraopolis Armory, PA | 079315 | Coraopolis, PA Heated Storage Building | 2012-12-07 | 2013-02-25 | Q.B.S., Inc. | 1560.1607 | 1698.0767 | 2013-04-16 | 2014-05-30 | 2014-04-16 | 2014-09-30 | 98.3903
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Knox | 005924 | Infantry Squad Battle Course | 2013-01-22 | 2013-06-14 | Howard W. Pence, Inc. | 3918.0746 | 3942.7188 | 2013-09-24 | 2014-10-06 | 2014-09-24 | 2014-11-28 | 80.5558
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 061810 | Battalion Headquarters Complex | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | 25750 | 25750 | 2014-03-04 | 2015-10-25 | 2015-08-26 | 2015-08-26 | 8.5894
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 061810 | Battalion Headquarters Complex | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | 25750 | 25750 | 2014-03-04 | 2015-10-25 | 2015-08-26 | 2015-08-26 | 3.0523
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 076239 | Unmanned Aerial Vehicle Complex | 2012-11-13 | 2013-05-31 | Archer Western Federal JV | 16983 | 17103.485 | 2013-06-25 | 2015-06-25 | 2015-04-26 | 2015-04-26 | 59.2706
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | IL | ILLINOIS | Fort Sheridan | 067659 | Sheridan, IL Army Reserve Center | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | 21575 | 22424.0926 | 2014-01-13 | 2015-07-06 | 2015-11-04 | 2015-12-31 | 7.9346
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | NV | NEVADA | RYLAND G TAYLOR AFRC | 067660 | Las Vegas, NV AR Center/OMS/AMSA/Unheated Storage | 2012-12-24 | 2013-06-12 | MACNAK Korte Team LLC | 16436.543 | 16583.3635 | 2013-07-10 | 2015-07-06 | 2015-05-01 | 2015-05-01 | 51.6038
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 067689 | Ft. McCoy, WI Central Issue Facility | 2013-01-14 | 2013-06-14 | KEPA-TCI JV LLC | 9302.203 | 9461.4485 | 2013-07-08 | 2014-12-30 | 2014-11-10 | 2014-11-10 | 27.5614
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 067715 | Ft. Lewis, WA Army Reserve Center | 2013-02-26 | 2013-06-13 | S.M. Wilson & Co. | 31219 | 31312.871 | 2013-07-11 | 2015-11-16 | 2015-08-30 | 2015-08-30 | 30.5215
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | CA | CALIFORNIA | Fort Hunter Liggett | 071482 | Fort Hunter Ligget ORTC | 2012-09-19 | 2014-02-06 | Sauer Incorporated | 56000.64 | 56000.64 | 2014-03-19 | 2016-08-04 | 2016-05-17 | 2016-05-17 | 3.9334
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | NJ | NEW JERSEY | Fort Dix | 071720 | Ft. Dix, NJ Automated Infantry Squad Battle Course | 2012-12-13 | 2013-06-28 | Eastern Construction & Electric, Inc. | 3093.8904 | 3287.0754 | 2013-07-17 | 2014-12-17 | 2014-07-17 | 2014-11-25 | 45.7749
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | MA | MASSACHUSETTS | Devens Reserve Forces Training Area, Ayer, MA | 071721 | Ft. Devens, MA COMBAT PISTOL/MP FIREARMS QUALIFICATION CO | 2013-03-04 | 2013-08-23 | Security Construction Services, Inc. | 3375.2884 | 3450.6204 | 2013-11-12 | 2014-09-26 | 2014-09-08 | 2014-09-26 | 85.9985
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 071997 | Ft. McCoy Dining Facility | 2013-01-18 | 2013-08-23 | TCI Architects Engineers Contractor Inc. | 7738.253 | 7738.253 | 2013-10-02 | 2015-03-16 | 2015-02-04 | 2015-02-04 | 6.2061
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 072088 | Fort McCoy - ECS TEMF | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | 19021.6 | 19110.122 | 2013-07-08 | 2015-08-27 | 2015-06-08 | 2015-06-08 | 22.8529
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Major Construction | CA | CALIFORNIA | Fort Hunter Liggett | 072160 | Fort Hunter Ligget CA UPH Barracks | 2013-03-28 | 2013-08-27 | Pre Con Industries, Inc. | 4384.284 | 4379.148 | 2013-11-18 | 2014-12-12 | 2014-11-03 | 2014-11-03 | 22.0185
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Minor Construction - UMMCAR | FL | FLORIDA | Tampa, Fl | 081597 | Tampa, FL AMSA Addition/Alteration | 2013-08-27 | 2013-09-30 | FutureNet Group, Inc. | 1379.863 | 1393.566 | 2013-10-09 | 2014-11-24 | 2014-09-24 | 2014-10-24 | 18.3644
2014-07-31 | 2014-08-14 | 2013 | Army Reserve | Minor Construction - UMMCAR | CO | COLORADO | Fort Carson | 082067 | Ft. Carson, CO - Unheated Storage Bldg | 2013-08-01 | 2013-12-05 | Komada, LLC | 1626.125 | 1626.125 | 2013-12-23 | 2015-02-23 | 2014-12-23 | 2014-12-23 | 41.1683
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | KY | KENTUCKY | Fort Campbell | 078778 | Battlefield Weather Facility | 2013-12-24 | 2014-06-18 | TJC Engineering | 4275.114 | 4275.114 | 2014-06-27 | 2015-10-20 | 2015-08-21 | 2015-05-23 | 0.87743
2014-07-31 | 2014-08-14 | 2014 | Army Reserve | Major Construction | NJ | NEW JERSEY | Joint Base McGuire-Dix-Lakehurst | 065277 | Ft. Dix Consolidated Dining Facility | 2014-01-07 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | 10798.9 | 10798.9 | 2014-04-23 | 2016-02-01 | 2015-09-30 | 2015-09-30 | 0
2014-07-31 | 2014-08-14 | 2014 | Army Reserve | Major Construction | NJ | NEW JERSEY | Joint Base McGuire-Dix-Lakehurst | 069669 | McGuire-Dix-Lakehurst, NJ Central Issue Facility | 2014-02-18 | 2014-06-05 | Ranco Construction, Inc. | 8783.22 | 8783.22 | 2014-07-07 | 2016-04-30 | 2015-12-14 | 2015-12-14 | 0
2014-07-31 | 2014-08-14 | 2014 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 071999 | Ft. McCoy, WI NCO Academy Dining Facility | 2013-12-23 | 2014-03-31 | Wilson Brigadier Joint Venture | 5900 | 5900 | 2014-04-22 | 2016-01-04 | 2015-08-25 | 2015-08-25 | 0.72683
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 069417 | Training Barracks Cnsldt Dining Facility 69417 FY 10 | 2009-11-03 | 2010-09-24 | BL Harbert International, LLC | 43613.85 | 49751.5567 | 2010-10-28 | 2012-11-26 | 2013-06-03 | 2014-12-31 | 88.2785
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brks Cplx/3rd BDE - PH III | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | 15752.3734 | 16515.7194 | 2011-11-21 | 2013-07-10 | 2014-01-29 | 2014-09-03 | 93.3355
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brks Cplx/3rd BDE - PH III | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | 15752.3734 | 16515.7194 | 2011-11-21 | 2013-07-10 | 2014-01-29 | 2014-09-03 | 90.8932
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 053555 | Brks Cplx/3rd BDE - PH III | 2011-05-24 | 2013-04-15 | Polote Corp. | 10869 | 11245.4628 | 2011-11-21 | 2014-04-30 | 2013-11-25 | 2015-04-18 | 96.1015
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | AL | ALABAMA | Fort Rucker | 060463 | LIC: 40540, Aviation Component Maintenance Shop | 2010-12-14 | 2011-05-18 | Carothers Construction, Inc | 19712.66 | 21442.7 | 2011-09-20 | 2013-07-30 | 2013-09-09 | 2014-08-11 | 99.497
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | HND | HONDURAS | Honduras Various | 061383 | Construction of new Barrack FY011 | 2011-05-18 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | 15146.5804 | 15633.3629 | 2012-01-10 | 2015-01-15 | 2014-01-09 | 2014-09-18 | 87.0626
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 071119 | 071119 Training Aids Center FY11 | 2011-06-03 | 2011-08-03 | PENTACON, LLC | 14999.9 | 15915.2921 | 2011-09-08 | 2014-11-03 | 2013-03-01 | 2014-10-07 | 81.933
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 072324 | Benning Barracks Ph 2 | 2010-10-26 | 2013-01-10 | Caddell Construction | 20847 | 21397.928 | 2013-02-12 | 2014-11-11 | 2014-05-08 | 2014-09-12 | 79.8033
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 072324 | Benning Barracks Ph 2 | 2010-10-26 | 2013-01-10 | Caddell Construction | 20847 | 20970.105 | 2013-02-12 | 2014-09-08 | 2014-05-08 | 2014-07-10 | 63.2172
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 043335 | NCO Academy | 2012-05-08 | 2012-07-30 | Caddell Construction CO., INC | 34647 | 34701.3095 | 2012-10-03 | 2014-10-31 | 2014-07-15 | 2014-07-30 | 99.9863
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 062955 | AIT Barracks Ph 2 FY12 | 2012-02-22 | 2012-03-28 | CLARK CONSTRUCTION GROUP LLC | 44267 | 46007.488 | 2012-07-23 | 2014-11-10 | 2014-01-14 | 2014-11-05 | 95.7687
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 070751 | TEMF, ACP, Infrastructure | 2012-04-19 | 2012-06-29 | Brantley Construction Services, LLC | 11681.588 | 12210.23 | 2012-07-31 | 2014-03-19 | 2014-07-21 | 2014-07-30 | 95.8138
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 057794 | Digital Multi-Purp Trng | 2012-12-26 | 2013-05-10 | Caddell Construction CO, LLC | 19523 | 19560.603 | 2014-02-04 | 2015-07-15 | 2015-04-30 | 2015-04-30 | 19.8256
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | SC | SOUTH CAROLINA | Fort Jackson | 058970 | BTC Complex II Phase 2 | 2012-12-21 | 2013-10-30 | ACC Construction Co., Inc | 21786.027 | 21826.317 | 2013-12-04 | 2015-09-05 | 2015-05-28 | 2015-06-07 | 19.1988
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Gordon, GA | 061498 | Automated Record Fire Range | 2012-11-19 | 2013-05-10 | BRISTOL ENVIRONMENTAL REMEDIATION SERVIC | 3163.794 | 3163.794 | 2013-07-03 | 2015-02-28 | 2014-07-19 | 2014-08-26 | 85.2388
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Gordon, GA | 067017 | Automated Multi-purpose Machine Gun Range | 2012-11-19 | 2013-05-16 | Bristol Environmental Remediation Service | 6483.273 | 6483.273 | 2013-07-11 | 2014-11-29 | 2014-08-05 | 2014-08-13 | 94.542
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Stewart | 073008 | UAS | 2013-03-22 | 2013-08-15 | Caddell Construction CO. (DE), LLC | 20726 | 21001.03 | 2013-11-06 | 2015-06-01 | 2015-03-01 | 2015-03-08 | 19.9855
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | GA | GEORGIA | Fort Benning | 077416 | Ground Source Heat Transfer System | 2013-04-04 | 2013-05-29 | R. C. Construction Co., Inc. | 8295 | 8398.886 | 2013-07-12 | 2015-04-04 | 2015-01-03 | 2015-01-03 | 80.8729
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 080066 | Whse Replacement J-1756 | 2012-11-16 | 2013-09-20 | Tyler Construction Co., INC | 6726.987 | 6769.3467 | 2013-11-06 | 2015-06-30 | 2015-03-01 | 2015-04-08 | 26.4169
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 080087 | Whse Replacement J-1952Tornado | 2012-07-16 | 2013-03-22 | Tyler Construction Group, Inc. | 9037.592 | 9003.526 | 2013-04-18 | 2014-12-15 | 2014-08-11 | 2014-09-16 | 34.313
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | GA | GEORGIA | Fort Stewart | 081273 | CIDC FIELD OPERATIONS BUILDING | 2013-07-17 | 2013-09-20 | Wolf Creek Federal Services, Inc. | 2841.632 | 2847.757 | 2013-10-29 | 2014-11-02 | 2014-08-25 | 2014-08-27 | 72.3211
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | GA | GEORGIA | Fort Stewart | 081299 | ORGANIZATIONAL STORAGE BUILDING | 2013-07-17 | 2013-09-20 | Wolf Creek Federal Services, Inc. | 0 | 0 | 2013-10-29 | 2014-11-02 | 2014-08-25 | 2014-08-27 | 0
2014-07-31 | 2014-08-14 | 2014 | Active Army | Minor Construction - UMMCA | MS | MISSISSIPPI | Waterways Experiment Station | 080477 | Fragmentation Simulation Laboratory Engineer Research & Development | 2013-04-30 | 2013-12-13 | The Clement Group, L.L.C. | 2341.157 | 2341.157 | 2014-01-23 | 2015-10-15 | 2015-07-17 | 2015-07-17 | 5.8195
2014-07-31 | 2014-08-14 | 2008 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 050950 | Barracks Cpx-Wheeler 205, SB | 2009-01-30 | 2010-03-26 | Kiewit Building Group Inc. | 44500 | 45992.851 | 2010-04-26 | 2012-11-06 | 2012-03-10 | 2012-10-15 | 98.9541
2014-07-31 | 2014-08-14 | 2008 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 050950 | Barracks Cpx-Wheeler 205, SB | 2009-01-30 | 2010-03-26 | Kiewit Building Group Inc. | 0 | 421.263 | 2010-04-26 | 2012-11-06 | 2012-03-10 | 2012-10-15 | 53.4108
2014-07-31 | 2014-08-14 | 2008 | Active Army | Major Construction | KOR | KOREA | Humphreys, Korea | 058784 | WHOLE BARRACKS RENEWAL PH 3, USAG HUMPHREYS | 2012-02-03 | 2012-09-17 | ECC International, LLC (ECC) | 32468.604 | 35283.2111 | 2012-09-17 | 2015-08-26 | 2014-09-07 | 2015-05-26 | 67.0823
2014-07-31 | 2014-08-14 | 2008 | Active Army | Major Construction | KOR | KOREA | Humphreys, Korea | 058784 | WHOLE BARRACKS RENEWAL PH 3, USAG HUMPHREYS | 2012-02-03 | 2012-09-17 | Shinsung Engr. & Const. Co., Ltd. | 17815.4345 | 18941.388 | 2012-09-17 | 2011-08-12 | 2014-03-16 | 2014-09-17 | 100
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068786 | Engr Unit Ops & Maint Complex, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 24779 | 28683.795 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 98.1631
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068786 | Engr Unit Ops & Maint Complex, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 1877 | 1893.723 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 100
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068821 | MP Unit Operations Facilities, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 29140 | 33821.435 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 98.3527
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068821 | MP Unit Operations Facilities, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 1944 | 1974.141 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 100
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068822 | Unit Operations Facilities, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 9103 | 10807.795 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 97.5974
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 068822 | Unit Operations Facilities, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 737 | 753.723 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 100
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069308 | Infrastructure Expansion, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 58240 | 63710.64 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 93.7544
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069308 | Infrastructure Expansion, South Range, SB | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 2145 | 2492.357 | 2011-04-15 | 2014-09-30 | 2014-03-14 | 2014-10-31 | 99.0992
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069521 | Warrior in Transition (WT) Barracks, SB | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 30812.375 | 31222.153 | 2011-07-27 | 2014-08-15 | 2013-10-12 | 2014-08-15 | 93.6382
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069521 | Warrior in Transition (WT) Barracks, SB | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 1932.995 | 1981.502 | 2011-07-27 | 2014-08-15 | 2013-10-12 | 2014-08-15 | 99.9999
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 071553 | Warrior in Transition (WT) Recovery, SB | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 24321.069 | 24674.494 | 2011-07-27 | 2014-08-15 | 2013-10-12 | 2014-08-15 | 99.9606
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 071553 | Warrior in Transition (WT) Recovery, SB | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 2018.561 | 2038.561 | 2011-07-27 | 2014-08-15 | 2013-10-12 | 2014-08-15 | 100
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 052269 | FY11 MCA PN52269 WBR Phase 3B2, Quad D, SB | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | 23984.24 | 24619.399 | 2011-10-17 | 2014-09-04 | 2014-07-16 | 2014-10-09 | 90.6901
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 052269 | FY11 MCA PN52269 WBR Phase 3B2, Quad D, SB | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | 1329.054 | 16259.078 | 2011-10-17 | 2014-09-04 | 2014-07-16 | 2014-10-09 | 89.5611
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | HI | HAWAII | Fort Shafter | 056024 | FY11 MCA PN56024 Flood Mitigation, FS | 2012-06-29 | 2012-09-25 | Nan, Inc | 21105.273 | 21711.224 | 2012-10-17 | 2015-04-28 | 2014-10-14 | 2015-04-28 | 52.0533
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | AK | ALASKA | Fort Richardson | 057369 | FTR159 Mission Training Complex | 2010-10-04 | 2011-05-11 | UNIT COMPANY | 20025.555 | 22497.391 | 2011-05-18 | 2013-10-23 | 2013-05-17 | 2013-10-24 | 99.9501
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 064760 | FY11 MCA PN64760 Training Support Center Upgrade, SB | 2012-06-29 | 2012-09-19 | SRB International LLC | 13310.008 | 13306.7969 | 2012-10-31 | 2014-10-21 | 2014-08-17 | 2014-09-26 | 61.7824
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | HI | HAWAII | Fort Shafter | 065650 | FY11 MCA PN65650 USARPAC Command & Control Facility, PH 1, Fort Shafter | 2011-11-04 | 2012-02-28 | Niking Corporation | 46780 | 48633.588 | 2012-04-03 | 2015-09-30 | 2014-04-23 | 2014-10-22 | 73.9235
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 059581 | Centralized Wash Facility, SB | 2011-10-13 | 2012-01-27 | Watts Constructors, LLC | 28300 | 29706.692 | 2012-02-08 | 2014-09-19 | 2013-12-14 | 2014-09-19 | 96.401
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | AK | ALASKA | Fort Richardson | 061515 | Expand Buckner Field House | 2011-10-19 | 2012-11-07 | Bristol General Contractors, LLC | 21813.389 | 22243.025 | 2013-03-16 | 2015-04-04 | 2014-12-06 | 2015-02-04 | 29.6739
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | HI | HAWAII | Fort Shafter | 064967 | Child Dev Ctr-School Age, FS | 2011-10-06 | 2012-02-27 | 57 Builders, Ltd. | 9573.118 | 10193.638 | 2012-03-23 | 2014-10-29 | 2013-12-13 | 2014-10-15 | 74.3125
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | AK | ALASKA | Fort Wainwright | 067113 | Aviation Task Force Complex, Ph 3 | 2011-07-15 | 2012-06-07 | Watterson Construction Company | 70591 | 71510.343 | 2012-06-14 | 2014-10-21 | 2014-08-03 | 2014-11-14 | 88.6814
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 069489 | Combat Aviation Brigade - PH 1, SB | 2012-01-24 | 2012-06-29 | David Boland, Inc. | 54772 | 55119.774 | 2012-07-30 | 2015-10-15 | 2015-05-27 | 2015-06-11 | 45.8133
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Carroll, Korea | 072650 | BARRACKS AND VMF, CP CARROLL | 2011-11-28 | 2012-02-24 | Samsung C&T Corporation | 27592.9923 | 28296.5491 | 2012-02-24 | 2015-11-23 | 2015-12-05 | 2015-10-07 | 38.3806
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Carroll, Korea | 072650 | BARRACKS AND VMF, CP CARROLL | 2011-11-28 | 2012-02-27 | Hanmi C&E Co., LTD. | 63.7852 | 4.2522 | 2014-02-21 | 2015-11-30 | 2015-10-31 | 2015-10-31 | 99.9965
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Henry/George, Korea | 076235 | BARRACKS W/DFAC, CP HENRY/GEORGE | 2012-02-02 | 2012-04-06 | Fine Construction Co., Ltd. | 28609.5284 | 29035.199 | 2012-04-06 | 2014-12-05 | 2014-06-22 | 2014-11-23 | 87.6586
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KOR | KOREA | Camp Henry/George, Korea | 076235 | BARRACKS W/DFAC, CP HENRY/GEORGE | 2012-02-02 | 2012-02-09 | Hanmi C&E Co., LTD. | 0 | 72.2037 | 2012-02-09 | 2014-08-02 | 2014-07-02 | 2014-07-02 | 25.194
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | AK | ALASKA | Fort Wainwright | 061681 | FTW370 Modified Record Fire Range | 2012-11-30 | 2013-05-14 | Arctic-American JV | 5094.09 | 5216.603 | 2013-05-24 | 2014-09-01 | 2014-08-01 | 2014-08-01 | 97.963
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | HI | HAWAII | Pohakuloa, Hi | 066023 | Infantry Platoon Battle Course, PTA | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | 27345 | 27345 | 2014-07-08 | 2017-01-23 | 2016-09-09 | 2016-09-09 | 0
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | KOR | KOREA | Humphreys, Korea | 076196 | Battalion Headquarters Complex, USAG Humphreys | 2012-10-04 | 2013-05-14 | Hyosung Corporation | 25852.7608 | 27865.2852 | 2013-05-14 | 2016-07-29 | 2015-06-09 | 2016-04-14 | 17.2675
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 076586 | WBR - Quad B, PH 2B (UPH), SB | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | 30717.476 | 30790.995 | 2013-07-23 | 2015-12-24 | 2015-09-01 | 2015-11-19 | 38.1798
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | HI | HAWAII | Schofield Barracks | 076587 | WBR - Quad B, PH 2C (OPS), SB | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | 37410.03 | 37592.924 | 2013-07-23 | 2015-12-24 | 2015-09-01 | 2015-11-19 | 38.2621
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | HI | HAWAII | Wheeler Army Air Field | 076903 | Combat Aviation Brigade Cpx - PH 2, WAAF | 2012-11-20 | 2014-05-13 | Nan-Samsung, LLC | 69749.203 | 69749.203 | 2014-06-26 | 2017-04-13 | 2017-01-13 | 2017-01-13 | 0
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | AK | ALASKA | Fort Wainwright | 067116 | FTW374 Aviation Task Force Complex, Ph 4 | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | 14180.4971 | 14180.4971 | 2014-05-15 | 2016-04-19 | 2016-02-04 | 2016-04-19 | 0.77861
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | AK | ALASKA | Fort Wainwright | 067116 | FTW374 Aviation Task Force Complex, Ph 4 | 2013-08-28 | 2014-04-14 | Arctic-American JV | 16180.297 | 16180.297 | 2014-04-23 | 2016-08-16 | 2015-10-15 | 2015-10-14 | 7.0097
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | NJ | NEW JERSEY | Picatinny Arsenal | 066725 | Picatinny - Ballistic Evaluation Facility Ph 1 (PN 066725) | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | 7201.728 | 7660.728 | 2012-12-04 | 2014-12-01 | 2014-06-04 | 2014-12-01 | 43.8442
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction - AFH | DEU | GERMANY | Baumholder, Germany | 071421 | Construct new Town Houses in Baumholder, Upper Wetzel | 2010-08-01 | 2010-09-30 | LBB Niederlassung Idar-Oberstein | 19295.714 | 19295.714 | 2014-12-16 | 2016-11-15 | 2016-10-14 | 2016-10-14 | 0
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | VA | VIRGINIA | Fort Eustis | 053663 | UPGRADE MARSHALLING AREA | 2010-07-28 | 2010-09-29 | Leebcor Services, LLC | 6330.28 | 7073.8299 | 2010-11-04 | 2012-11-27 | 2011-11-14 | 2014-09-05 | 99.1377
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | MD | MARYLAND | Fort Detrick | 058625 | DETRICK, Satellite Facility | 2009-10-09 | 2010-02-05 | Harkins Builders, Inc. | 11717.005 | 19327.8645 | 2010-03-06 | 2014-12-12 | 2012-09-01 | 2014-11-11 | 99.8318
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | MD | MARYLAND | Fort Detrick | 060027 | DETRICK, Community Support Center | 2011-02-18 | 2011-07-08 | Grunley/Goel JV D LLC | 7530 | 8165.482 | 2011-08-18 | 2014-07-31 | 2013-08-17 | 2014-07-30 | 100
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | DEU | GERMANY | Katterbach Germany | 063394 | Barracks Complex, Katterbach | 2010-03-22 | 2011-12-13 | Staatliches Hochbauamt Nurnberg II | 16797.4108 | 17215.8464 | 2010-09-27 | 2014-04-30 | 2013-09-06 | 2014-04-29 | 93
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | DEU | GERMANY | Kaiserslautern Germany | 066596 | Barracks Complex, Rhein | 2010-09-07 | 2010-09-30 | Federal Republic of Germany | 16925.5868 | 17633.9528 | 2012-09-05 | 2014-09-12 | 2014-05-20 | 2014-07-14 | 94.2161
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | NJ | NEW JERSEY | Picatinny Arsenal | 066726 | Picatinny - Ballistic Evaluation Facility Ph 2 (PN066726) | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | 8757.272 | 8911.254 | 2012-12-04 | 2014-12-01 | 2014-06-04 | 2014-12-01 | 55.0754
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | DEU | GERMANY | Illesheim Germany | 069616 | Barracks Complex, Storck | 2010-03-15 | 2010-03-31 | Staatliches Hochbauamt Nurnberg II | 648.1765 | 896.4629 | 2012-08-06 | 2014-05-31 | 2014-01-10 | 2014-06-30 | 84
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | DEU | GERMANY | Illesheim Germany | 069616 | Barracks Complex, Storck | 2012-03-16 | 2012-07-11 | Staatliches Hochbauamt Nurnberg II | 13259.0374 | 13569.4643 | 2012-08-06 | 2014-05-31 | 2014-02-10 | 2014-06-30 | 84
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction - AFH | DEU | GERMANY | Baumholder, Germany | 071422 | FY11 071422 Housing Construction | 2015-02-27 | 2015-06-15 | LBB Niederlassung Idar-Oberstein | 33106.2357 | 33106.2357 | 2015-07-15 | 2017-10-11 | 2017-07-17 | 2017-07-17 | 0
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | NY | NEW YORK | West Point Military Academy | 059044 | USMA - Multipurpose Academic Ph 2 (PN 059044) | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | 105270 | 112848.449 | 2011-11-17 | 2016-04-29 | 2015-11-14 | 2016-01-29 | 74.265
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Katterbach Germany | 059434 | FY11 059434 Physical Fitness Center, Katterbach | 2010-12-01 | 2011-08-12 | Staatliches Hochbauamt Nurnberg II | 13513.2866 | 13662.7329 | 2012-11-30 | 2014-11-28 | 2014-06-08 | 2014-11-17 | 61
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Katterbach Germany | 059434 | FY11 059434 Physical Fitness Center, Katterbach | 2012-06-15 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II | 969.0413 | 1087.6861 | 2012-11-30 | 2014-11-28 | 2014-06-08 | 2014-11-15 | 61
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Wiesbaden Germany | 060555 | Network Warfare Center, Wiesbaden | 2010-12-16 | 2011-06-21 | Hessisches Baumanagement Wiesbaden | 27781.5441 | 31146.9222 | 2012-06-18 | 2014-12-07 | 2014-03-25 | 2014-11-07 | 92
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | VA | VIRGINIA | Fort Belvoir | 061453 | BELVOIR, Replace Fire Station | 2012-07-05 | 2013-05-23 | TMG SERVICES, INC. Linda Frazier | 6189 | 6366.913 | 2013-06-05 | 2015-07-10 | 2014-11-27 | 2015-04-26 | 24.682
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | VA | VIRGINIA | Fort A P Hill | 065789 | FY11 AP HILL MCA PN 65789 100 METER INDOOR RGE | 2011-10-26 | 2012-01-03 | Jordan-Versar, LLC | 6520 | 6749.174 | 2012-01-20 | 2013-10-24 | 2013-10-21 | 2013-10-24 | 100
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | MD | MARYLAND | Fort Meade | 065793 | MEADE, 100 Meter Indoor Range | 2011-06-16 | 2011-09-21 | John C. Grimberg Co., Inc. | 7241 | 8127.413 | 2011-10-13 | 2014-08-30 | 2013-04-05 | 2014-08-30 | 99.9973
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Sembach Germany | 066465 | FY11 066465 Confinement Facility, Sembach | 2012-03-06 | 2012-06-19 | LBB Kaiserslautern | 472.7664 | 304.9657 | 2013-04-29 | 2014-08-21 | 2014-07-21 | 2014-07-25 | 98
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Sembach Germany | 066465 | FY11 066465 Confinement Facility, Sembach | 2012-11-21 | 2013-03-07 | LBB Kaiserslautern | 9459.8812 | 9441.6077 | 2013-04-29 | 2014-08-21 | 2014-07-21 | 2014-07-25 | 98
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Katterbach Germany | 066834 | FY11 066834 Transform Vehicle Maintenance Shop | 2010-12-01 | 2011-06-16 | Staatliches Hochbauamt Nurnberg II | 16289.8057 | 17843.8901 | 2011-12-12 | 2014-10-31 | 2013-12-18 | 2014-10-15 | 88.4088
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Grafenwoehr Germany | 067968 | FY11 067968 Barracks Grafenwoehr | 2010-12-03 | 2011-11-23 | Bauamt Amberg-Sulzbach | 16357.4626 | 16487.9829 | 2011-12-12 | 2014-03-17 | 2013-04-10 | 2014-02-28 | 100
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Wiesbaden Germany | 068074 | FY11 068074 Construct New Access Control Point, Wiesbaden | 2013-11-15 | 2014-03-04 | Hessisches Baumanagement Wiesbaden | 6303.2366 | 6892 | 2014-03-05 | 2015-01-26 | 2014-12-12 | 2014-12-12 | 43.8682
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | East Camp Grafenwoehr | 068606 | FY11 068606 Barracks, Grafenwoehr | 2011-09-02 | 2011-09-16 | Bauamt Amberg-Sulzbach | 18097.4785 | 18341.9328 | 2012-10-12 | 2014-06-30 | 2014-06-01 | 2015-07-10 | 100
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Wiesbaden Germany | 068866 | FY11 068866 Consolidated Intelligence Center, Wiesbaden | 2012-05-22 | 2013-02-04 | OBG Hochbau GmbH & Co. KG | 87011.483 | 89200.6517 | 2013-02-22 | 2016-05-31 | 2015-09-19 | 2016-05-31 | 16
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Vilseck Germany | 069612 | FY11 069612 Barracks, Vilseck | 2010-12-03 | 2012-02-15 | Bauamt Amberg-Sulzbach | 18034.1312 | 18174.7289 | 2012-02-29 | 2014-01-13 | 2013-11-14 | 2013-12-04 | 100
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | DEU | GERMANY | Grafenwoehr Germany | 069613 | FY11 069613 Barracks Grafenwoehr | 2010-12-03 | 2012-02-15 | Bauamt Amberg-Sulzbach | 18352.1994 | 18506.2087 | 2012-02-29 | 2014-02-03 | 2013-11-08 | 2014-01-13 | 100
2014-07-31 | 2014-08-14 | 2011 | Active Army | Minor Construction - UMMCA | NJ | NEW JERSEY | Picatinny Arsenal | 074943 | Picatinny - Igloo Storage Installation (PN 074943) | 2011-08-10 | 2012-07-18 | Senate Builders & Construction Managers Inc. | 1756.106 | 1851.3294 | 2012-08-10 | 2013-10-15 | 2013-07-07 | 2014-05-15 | 99.9999
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Grafenwoehr Germany | 078505 | Construct 26 Townhouses East Camp | 2013-04-19 | 2013-08-07 | Staatliches Hochbauamt Amberg | 13548.8862 | 13613.8072 | 2013-08-07 | 2016-07-18 | 2015-09-14 | 2015-11-05 | 14
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction - AFH | DEU | GERMANY | Vilseck Germany | 078506 | Construction of 22 townhouses | 2013-07-08 | 2013-09-30 | Bauamt Amberg-Sulzbach | 12815.485 | 12848.5891 | 2013-09-30 | 2015-09-24 | 2015-08-11 | 2015-08-11 | 32
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | DEU | GERMANY | East Camp Grafenwoehr | 055985 | Chapel, Grafenwoehr | 2012-01-10 | 2012-03-15 | Bauamt Amberg-Sulzbach | 15915.6532 | 16018.1318 | 2013-11-21 | 2016-04-22 | 2016-03-23 | 2016-03-23 | 12
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | VA | VIRGINIA | Fort Belvoir | 057508 | BELVOIR, SCIF Phase 1 | 2013-03-08 | 2013-07-22 | Hensel Phelps Construction Co. | 39700.01 | 40397.5895 | 2013-08-19 | 2015-07-03 | 2015-03-12 | 2015-04-24 | 38.4618
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | DEU | GERMANY | Landstuhl Germany | 057594 | Wideband SATCOM Operations Center, Landstuhl | 2012-03-12 | 2012-03-28 | JV PGWM SATCOM | 27565.3511 | 27565.3511 | 2014-03-14 | 2015-10-25 | 2015-10-25 | 2015-12-14 | 1.6541
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 058005 | AMMO SUPPLY POINT | 2011-12-23 | 2012-04-17 | Black Horse Group LLC | 4680.9 | 4784.437 | 2012-05-18 | 2014-07-31 | 2013-08-15 | 2014-06-30 | 99.6979
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | VA | VIRGINIA | Joint Base Langley-Eustis | 059005 | Aviation Training Facility | 2012-03-21 | 2012-05-16 | Oyster Point Construction Company | 13849 | 14328.533 | 2012-06-14 | 2014-08-25 | 2013-12-06 | 2014-06-14 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | MD | MARYLAND | Fort Meade | 064939 | Defense Information School (DINFOS) | 2012-06-22 | 2012-09-24 | Grimberg/Amatea JV | 30554 | 30773.141 | 2012-11-20 | 2015-01-22 | 2014-11-20 | 2014-11-20 | 74.7343
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | DEU | GERMANY | Grafenwoehr Germany | 065129 | Combat Trail, Grafenwoehr | 2012-03-02 | 2012-03-15 | Bauamt Amberg-Sulzbach | 2279.4471 | 2640.2701 | 2012-10-29 | 2013-10-18 | 2013-10-31 | 2013-10-18 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | MD | MARYLAND | Fort Meade | 065755 | MEADE, Asymmetric Warfare Group Complex | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | 30761.85 | 32091.873 | 2012-12-12 | 2016-08-09 | 2015-12-12 | 2016-08-09 | 59.5113
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | DEU | GERMANY | East Camp Grafenwoehr | 069614 | New Barracks, Graf | 2012-10-19 | 2013-03-28 | Staatliches Hochbauamt Amberg | 17523.1242 | 17752.2228 | 2013-03-27 | 2015-08-04 | 2014-12-31 | 2014-12-04 | 65
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | DEU | GERMANY | Vilseck Germany | 069615 | FY12 069615 New Barracks, Vilseck | 2012-01-03 | 2012-03-15 | Bauamt Amberg-Sulzbach | 17668.7874 | 17945.655 | 2012-10-10 | 2014-10-25 | 2014-09-25 | 2014-09-25 | 98
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | DEU | GERMANY | Oberdachstatten Germany | 071906 | Automated Record Fire (ARF) at Range 2, Oberdachstetten, USAG Ansbach | 2012-03-01 | 2012-03-15 | Staatliches Hochbauamt Nurnberg II | 9280.9785 | 9660.9996 | 2013-02-06 | 2014-06-03 | 2014-05-16 | 2014-05-20 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TUR | TURKEY | Turkey Various | 079749 | Forward Operating Site, Turkey 079749 | 2012-06-15 | 2012-08-17 | EMTA INSAAT A.S | 173.0245 | 173.025 | 2012-07-25 | 2012-11-23 | 2015-04-29 | 2014-11-30 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TUR | TURKEY | Turkey Various | 079749 | Forward Operating Site, Turkey 079749 | 2012-06-15 | 2012-08-17 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. | 12129.1464 | 12151.695 | 2013-12-05 | 2015-01-29 | 2015-04-29 | 2015-04-29 | 12
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | VA | VIRGINIA | Fort Lee | 033771 | AIT BARRACKS COMPLEX, PH2 | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | 46650 | 46659.0739 | 2013-10-15 | 2015-12-15 | 2015-10-15 | 2015-10-15 | 21.5212
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NJ | NEW JERSEY | Picatinny Arsenal | 051519 | Picatinny - Ballistic Evaluation Center | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | 5959 | 6219.178 | 2013-10-23 | 2015-05-31 | 2015-02-15 | 2014-12-01 | 34.1624
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NJ | NEW JERSEY | Picatinny Arsenal | 051519 | Picatinny - Ballistic Evaluation Center (PN 051519) | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | 5959 | 6009 | 2013-10-23 | 2015-05-31 | 2015-02-15 | 2014-06-04 | 24.9224
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NJ | NEW JERSEY | Lakehurst, NJ | 071675 | Lakehurst - CERDEC Flight Activity Facility | 2013-05-03 | 2013-11-21 | The Bedwell Company | 42751 | 42773.182 | 2014-01-15 | 2016-04-15 | 2016-01-15 | 2016-03-10 | 7.9182
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NY | NEW YORK | West Point Military Academy | 079933 | USMA - Cadet Barracks | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | 72000 | 72000 | 2013-08-26 | 2016-10-24 | 2016-08-30 | 2016-10-28 | 36.0665
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 080246 | Aircraft Maintenance Hangar | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | 26825.868 | 27174.02 | 2013-06-27 | 2015-09-15 | 2015-06-17 | 2015-06-17 | 14.5914
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | NY | NEW YORK | Fort Drum | 080246 | Ft Drum - Aircraft Maintenance Hangar (PN 080246) | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | 26825.868 | 27151.832 | 2013-06-27 | 2015-09-15 | 2015-06-17 | 2015-06-17 | 5.5259
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | VA | VIRGINIA | Joint Base Myer-Henderson Hall | 080317 | WATER DISTRIBUTION LINES, POTABLE | 2013-08-14 | 2013-11-26 | FLBE, INC. | 1790.839 | 1790.839 | 2014-01-13 | 2014-12-10 | 2014-09-10 | 2014-12-10 | 2.5194
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | DC | DISTRICT OF COLUMBIA | Fort McNair | 081431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE | 2013-08-15 | 2014-06-17 | PORTICO SERVICES, LLC | 1793.105 | 1793.105 | 2014-07-15 | 2015-07-10 | 2015-03-12 | 2015-03-12 | 0
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | VA | VIRGINIA | Fort Belvoir | 081629 | This additional chiller will increase Bldg 2000 capacity from 1200 tons to 1700 | 2013-07-15 | 2013-09-27 | Team Henry Enterprises, LLC | 1089.1834 | 1132.5334 | 2013-10-17 | 2014-10-10 | 2014-08-13 | 2014-08-13 | 99.9999
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | NY | NEW YORK | West Point Military Academy | 081186 | USMA - Cadet Barracks, Incr 2 (PN 081186) | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | 40000 | 40000 | 2013-08-26 | 2016-08-30 | 2016-07-08 | 2016-07-08 | 0
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | MD | MARYLAND | Aberdeen Proving Ground, Md | 081875 | Operations and Maintenance Facilities | 2013-11-27 | 2014-05-12 | Edifice Group, Inc. | 17891 | 18328 | 2014-05-23 | 2015-04-02 | 2015-03-19 | 2015-04-02 | 0
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction | CA | CALIFORNIA | Sierra Army Depot | 060859 | CONSTRUCT WATER TREATMENT PLANTS WITH EVAPORATION PONDS | 2008-12-04 | 2009-05-13 | Cushman Contracting Corporation | 4795 | 6424.5692 | 2009-06-17 | 2011-07-24 | 2010-12-09 | 2014-10-31 | 99.9719
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | CA | CALIFORNIA | Presidio Of Monterey | 060285 | Gen Ins Fac VII | 2010-10-07 | 2011-05-18 | RQ Construction, LLC | 29886 | 32382.623 | 2011-06-07 | 2014-09-01 | 2013-05-24 | 2014-09-01 | 98.1195
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | CA | CALIFORNIA | Camp Roberts | 063015 | Sat Comm Facility / Tree Mitigation | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV | 34801.408 | 35283.472 | 2011-09-21 | 2015-05-15 | 2013-06-12 | 2014-06-30 | 4.3259
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | UT | UTAH | Dugway Proving Ground | 055823 | LIFE SCIENCES TEST FAC ANX | 2012-04-17 | 2012-07-26 | Big-D Construction Corp | 22608.566 | 29431.975 | 2012-08-29 | 2015-12-03 | 2015-02-15 | 2015-12-03 | 60.3011
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | CA | CALIFORNIA | Presidio Of Monterey | 056425 | DLI-Gen Instruction Bldg (Weckerling Ctr) | 2012-08-16 | 2012-09-29 | Souza Construction, Inc. | 2996 | 3104.151 | 2012-11-06 | 2014-08-15 | 2013-11-06 | 2014-08-15 | 85.4581
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | CA | CALIFORNIA | Fort Irwin | 062657 | Water Treatment Plant | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | 100112.66 | 99853.018 | 2012-10-19 | 2016-03-28 | 2015-10-19 | 2016-01-05 | 39.2797
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | UT | UTAH | Dugway Proving Ground | 081106 | POLICE/MP STATION | 2013-06-11 | 2013-09-27 | Zumwalt Construction, Inc. | 1768.28 | 1768.28 | 2013-10-18 | 2015-01-16 | 2014-12-17 | 2014-12-17 | 11.6976
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | CA | CALIFORNIA | Fort Irwin | 081367 | EXPLOSIVES RECEIVING/SERVICE BUILDING, DEP | 2013-12-18 | 2014-04-16 | Cyber Professional Solution Corp | 1783.729 | 1783.729 | 2014-05-08 | 2015-08-06 | 2015-05-08 | 2015-05-08 | 1.8308
2014-07-31 | 2014-08-14 | 2014 | Active Army | Minor Construction - UMMCA | AZ | ARIZONA | Yuma | 79679 | Material Analysis Lab | 2014-02-03 | 2014-06-10 | AU AUTHUM KI, INC. | 2983 | 2983 | 2014-07-10 | 2015-04-06 | 2015-02-05 | 2015-02-05 | 0
2014-07-31 | 2014-08-14 | 2009 | Active Army | Major Construction - OCO | AFG | AFGHANISTAN | Afghanistan Various | 072125 | SOF Alpha Ramp Fac, BAF | 2012-04-04 | 2012-08-23 | Prime Projects Int'l (Const) Limited | 5739 | 8416 | 2012-09-26 | 2014-11-30 | 2013-08-13 | 2014-03-01 | 89
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | KWT | KUWAIT | Arifjan Kuwait, Arcent-Ku | 071485 | PM-F, KW - APS - 5 Warehouses / Power Plant | 2013-06-21 | 2013-09-27 | Contrack International, Inc. | 49412.74 | 54675.778 | 2013-10-25 | 2015-07-04 | 2015-03-25 | 2015-03-25 | 4.3158
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | KWT | KUWAIT | Arifjan Kuwait, Arcent-Ku | 071485 | PM-F, KW - APS - 5 Warehouses / Power Plant | 2013-11-06 | 2014-05-03 | Contrack International, Inc. | 6749.291 | 6749.291 | 2013-10-25 | 2015-12-29 | 2015-10-30 | 2015-10-25 | 0
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 072477 | USFOR-A HQ & Housing, Kabul | 2011-03-10 | 2011-08-05 | Contrack International Inc. | 47160.85 | 32296.3139 | 2011-09-09 | 2014-11-10 | 2013-12-07 | 2014-08-25 | 86.7884
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 071604 | PM-M, AFG, 071604, Eastside Utilities Infrastructure, BAF | 2012-05-31 | 2012-09-04 | ANHAM-ICSS Joint Venture | 26826.989 | 24726.989 | 2012-10-18 | 2014-11-30 | 2014-06-05 | 2014-11-30 | 42.6533
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan | 071569 | PM-M, AFG, 071569, Westside Utilities Infrastructure, BAF | 2012-08-23 | 2012-11-15 | Contrack International Inc. | 11924.059 | 10050.8594 | 2012-12-12 | 2014-09-30 | 2014-03-07 | 2014-08-02 | 91.0697
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan Various | 074067 | Drainage System, Ph 3, BAF | 2012-04-30 | 2012-08-15 | ANHAM-ICSS JV | 19902.989 | 20774.5888 | 2012-10-09 | 2014-10-31 | 2014-06-01 | 2014-10-31 | 70.1547
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan | 074084 | SOF Barracks, Ph 5, BAF | 2011-12-08 | 2012-04-12 | Bryan 77 Construction JV | 19331.277 | 14215.2052 | 2012-06-08 | 2014-09-17 | 2014-04-19 | 2014-09-17 | 80.3865
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | AFG | AFGHANISTAN | Various Worldwide Locations | 079652 | PM-M, RS&SF, ARCENT CAS South | 2012-05-25 | 2012-08-20 | American International Contractors, Inc | 3800 | 4171.3837 | 2012-09-27 | 2015-01-29 | 2013-07-24 | 2014-11-03 | 81.7487
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | AFG | AFGHANISTAN | Afghanistan | 080001 | PM-M, AFG, 080001, Waste Management Complex, BAF | 2012-05-25 | 2012-08-21 | Bryan 77 Construction JV | 24435.92 | 23956.722 | 2012-11-14 | 2014-08-31 | 2014-03-27 | 2014-08-31 | 97.8115
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 074408 | Ft Lewis-McChord AFB Joint Access | 2013-02-12 | 2013-08-29 | TSS-Garco Joint Venture | 7327 | 7440.125 | 2013-09-25 | 2015-03-29 | 2015-01-28 | 2015-01-28 | 20.7057
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 013852 | FY11 Battle Sims training Support Center | 2011-07-19 | 2011-09-14 | Native American Services Corp. | 27829.194 | 34334.6404 | 2011-11-04 | 2014-06-16 | 2013-04-27 | 2014-06-16 | 93.2484
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 072854 | Regional Logistic Support Complex | 2011-05-02 | 2011-09-26 | Garco Construction, Inc. | 36247 | 36817.542 | 2013-02-13 | 2014-12-27 | 2014-08-07 | 2014-08-07 | 77.782
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | WA | WASHINGTON | Fort Lewis | 072854 | Regional Logistic Support Complex | 2014-03-07 | 2014-04-30 | Maanilaq Services LLC | 8893.541 | 11287.2752 | 2013-02-13 | 2013-12-20 | 2014-10-17 | 2014-10-17 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 002728 | Physical Fitness Facility | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | 11660 | 11694.8087 | 2012-03-29 | 2014-08-05 | 2013-09-20 | 2014-07-02 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 002728 | Physical Fitness Facility (Parking Lot) | 2014-04-01 | 2014-07-02 | Zieson Construction Co. | 727.389 | 727.389 | 2015-03-13 | 2016-06-30 | 2015-07-16 | 2015-07-16 | 0
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 058046 | ROTC Facilities Phase I | 2012-06-29 | 2013-04-01 | TSS-Garco Joint Venture | 16416 | 16175.619 | 2013-05-21 | 2015-01-26 | 2014-11-12 | 2015-03-25 | 27.0171
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 064014 | 23rd Chemical Battalion Complex | 2012-08-14 | 2012-09-21 | 3D Contracting Inc. | 19332 | 19731.034 | 2012-11-30 | 2014-09-09 | 2014-05-24 | 2014-08-10 | 99.4678
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 064365 | TEMF COMPLEX w/Central Vehicle Wash Facility | 2012-02-03 | 2012-08-23 | KCI Construction Company | 30970 | 32715.163 | 2012-09-18 | 2014-08-15 | 2014-03-12 | 2014-08-15 | 98.4266
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 064365 | TEMF COMPLEX w/Central Vehicle Wash Facility | 2012-07-31 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | 8541.461 | 8570.425 | 2013-01-04 | 2014-06-24 | 2014-08-25 | 2015-07-15 | 29.7745
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 066206 | North Fort Infrastructure Expansion | 2012-08-18 | 2013-01-25 | CeSight Joint Venture | 13775.4 | 14292.0618 | 2013-03-04 | 2014-11-19 | 2014-08-26 | 2014-09-20 | 78.8093
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 066206 | North Fort Infrastructure Expansion | 2014-03-12 | 2014-06-20 | Vet Industrial, Inc. | 10525 | 12152.295 | 2012-11-06 | 2013-11-25 | 2015-09-10 | 2015-09-10 | 80.4793
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 069834 | Unmanned Aerial Vehicle Maintenance Hangar | 2013-08-26 | 2014-01-07 | Law Company, Inc., The | 20078.9 | 20078.9 | 2014-02-06 | 2015-11-08 | 2015-07-31 | 2015-07-31 | 8.0721
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | KS | KANSAS | Fort Riley | 069834 | Unmanned Aerial Vehicle Maintenance Hangar | 2012-05-01 | 2012-11-01 | Arch Insurance Company | 5932.641 | 6058.041 | 2012-12-11 | 2015-01-30 | 2014-03-16 | 2014-12-31 | 55.8434
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 076768 | Aviation Complex, Ph 1B | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | 12950.4 | 13736.6266 | 2012-11-29 | 2014-07-22 | 2014-05-23 | 2014-07-22 | 89.8589
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 076768 | Aviation Complex, Ph 1B | 2013-12-04 | 2014-04-08 | Glen/Mar Construction, Inc. | 4771.02 | 4771.02 | 2014-05-21 | 2016-11-03 | 2015-05-21 | 2015-05-21 | 0.84405
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077306 | Aircraft Maintenance Hangar | 2012-01-17 | 2012-08-09 | Hensel Phelps Construction Co. | 44801 | 54069.066 | 2012-08-23 | 2014-10-31 | 2014-02-14 | 2014-10-06 | 93.7515
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077306 | Aircraft Maintenance Hangar | 2012-01-04 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | 2669.032 | 2717.234 | 2012-08-23 | 2014-10-31 | 2015-02-08 | 2015-02-08 | 27.4956
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 054489 | Basic Training Complex Barracks 3 South Ph 2 | 2013-04-11 | 2013-08-15 | Caddell Construction Co. (DE), LLC | 33360 | 33964.0256 | 2013-09-12 | 2015-12-12 | 2015-09-12 | 2015-10-16 | 33.4636
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 054489 | Basic Training Complex Barracks 3 South Ph 2 | 2013-01-18 | 2013-05-31 | Donald Maggi, Inc. | 11711 | 12104.075 | 2013-06-25 | 2015-04-16 | 2014-12-17 | 2014-12-17 | 59.5342
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 059626 | PN 59626 Digital Multipurpose Training Range | 2013-05-31 | 2013-08-23 | NEU Security Services, LLC | 14080 | 15393.603 | 2013-09-18 | 2015-06-10 | 2015-03-12 | 2015-05-01 | 29.6294
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 064456 | Brigade Headquarters Building | 2012-11-19 | 2013-06-26 | Tunista Construction, LLC | 14849 | 15378.09 | 2013-06-26 | 2017-05-19 | 2014-12-18 | 2017-05-19 | 50.1665
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 065679 | Tactical Equipment Maintenance Facility | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | 18726.852 | 18978.188 | 2013-06-27 | 2015-07-17 | 2015-04-08 | 2015-04-18 | 49.9305
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 066099 | Battalion Headquarters Building | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | 13687 | 14116.247 | 2013-07-01 | 2015-05-11 | 2014-12-23 | 2015-01-11 | 69.2191
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | WA | WASHINGTON | Yakima Firing Center | 067545 | Automated Record Fire Range | 2013-05-16 | 2013-08-22 | Vet Industrial Inc. | 4990.675 | 5123.211 | 2013-09-10 | 2015-03-04 | 2015-01-03 | 2015-01-03 | 81.9604
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | WA | WASHINGTON | Joint Base Lewis-McChord | 075165 | Waste Water Treatment Plant, Phase 1 | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | 77476.628 | 77523.974 | 2014-03-03 | 2016-05-01 | 2016-03-02 | 2016-03-02 | 11.7058
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | MO | MISSOURI | Fort Leonard Wood | 079980 | Const potable wtr UV disinfection treatment fac to meet req of EPA long term 2 Enhanced Surface Wtr Disinfection Rule @ FLW MO | 2013-05-17 | 2013-07-17 | Huffman Construction, LLC | 1437.6 | 1423.518 | 2013-09-23 | 2014-08-22 | 2014-06-20 | 2014-08-22 | 69.7081
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | CO | COLORADO | Fort Carson | 081300 | Construct Aircraft Maintenance Apron for 2 Large Area Maintenance Shelter - Aviation (LAMS-A) | 2013-04-24 | 2013-09-12 | CMS of Colorado Springs, Inc. dba CMS | 1730.8978 | 1817.5218 | 2013-10-29 | 2014-10-24 | 2014-08-25 | 2014-10-24 | 69.5322
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | WA | WASHINGTON | Joint Base Lewis-McChord | 081320 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL | 2013-08-08 | 2013-09-26 | Northcon, Inc. | 1380.171 | 1380.171 | 2013-10-28 | 2014-12-27 | 2014-10-28 | 2014-10-28 | 59.9046
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | MO | MISSOURI | Fort Leonard Wood | 071502 | Advanced Individual Training Complex Barracks 2 Ph1 | 2014-03-06 | 2014-07-10 | MW Builders of Texas, Inc. | 47777 | 47777 | 2013-05-21 | 2016-12-02 | 2016-08-08 | 2016-08-08 | 0
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | KS | KANSAS | Fort Leavenworth | 076024 | Battle Command Training Center Upgrade | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | 15630 | 15630 | 2014-08-07 | 2016-04-26 | 2016-01-07 | 2016-01-07 | 0
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077262 | Headquarters Building | 2014-03-11 | 2014-07-15 | Mirador Enterprises, Inc. | 17165.0006 | 17165.0006 | 2014-07-29 | 2016-03-20 | 2016-01-20 | 2016-01-20 | 0
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 077885 | Runway, Fort Carson, CO | 2014-03-06 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | 9832.807 | 9832.807 | 2014-07-01 | 2015-08-30 | 2015-07-01 | 2015-07-01 | 0.60907
2014-07-31 | 2014-08-14 | 2014 | Active Army | Major Construction | CO | COLORADO | Fort Carson | 079618 | CAP 079618 Flight Simulator | 2014-07-28 | 2014-07-21 | Mirador Enterprises, Inc. | 8440 | 8440 | 2014-08-04 | 2016-03-26 | 2016-01-26 | 2016-01-26 | 0
2014-07-31 | 2014-08-14 | 2008 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 054785 | School Age Service Center (6-10 years) | 2010-12-13 | 2011-08-05 | ASSET Group, Inc. | 7835.188 | 7946.4612 | 2011-09-23 | 2014-12-27 | 2013-01-25 | 2014-10-27 | 76.8249
2014-07-31 | 2014-08-14 | 2010 | Active Army | Major Construction | TX | TEXAS | Joint Base San Antonio | 064209 | Access Control Point Road Improvements, FSH | 2010-01-15 | 2010-07-15 | Greenleaf Construction Company, Inc. | 9839.658 | 11751.452 | 2010-08-03 | 2012-10-31 | 2012-01-25 | 2014-09-30 | 99.2637
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 057434 | Indoor Aquatic Training Facility (EBA Community Area) | 2011-08-08 | 2011-09-14 | Megen Construction Company, Inc. | 13606.4 | 13808.217 | 2011-10-18 | 2013-05-09 | 2013-01-08 | 2013-05-09 | 99.7494
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Joint Base San Antonio | 067194 | Simulations Center | 2010-11-18 | 2011-05-31 | Blackhawk Ventrues, LLC | 14554.1 | 15161.3161 | 2012-04-10 | 2014-07-03 | 2013-08-09 | 2014-07-31 | 93.0336
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071462 | Battalion Complex | 2011-01-24 | 2011-09-30 | JAMA Constructors | 6572.777 | 7848.4512 | 2012-07-30 | 2014-08-30 | 2014-01-21 | 2014-12-31 | 94.4954
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071465 | Company Operations Facilities | 2011-03-21 | 2011-09-29 | MW Builders | 3048.91 | 3122.2434 | 2012-06-19 | 2015-05-07 | 2013-11-11 | 2015-03-08 | 99.8324
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071639 | Brigade Complex | 2012-12-19 | 2011-09-29 | MW Builders | 11652.378 | 11981.1625 | 2012-06-19 | 2014-11-10 | 2013-11-11 | 2014-09-11 | 99.9374
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 072149 | Explosive Ordnance Detachment COF | 2010-10-29 | 2011-05-31 | Alutiiq International Solution , LLC | 12509.698 | 13164.587 | 2011-07-12 | 2012-12-27 | 2012-11-13 | 2013-01-04 | 99.924
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 074635 | THAAD Battery II | 2010-10-29 | 2011-05-31 | Alutiiq International Solution , LLC | 4374.806 | 4463.188 | 2011-07-12 | 2012-12-27 | 2012-11-13 | 2013-01-04 | 99.7759
2014-07-31 | 2014-08-14 | 2011 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 074635 | THAAD Battery II | 2010-10-29 | 2011-05-31 | Hensel Phelps Construction Company | 9175 | 10820.229 | 2011-07-05 | 2012-11-05 | 2012-09-09 | 2014-09-30 | 99
2014-07-31 | 2014-08-14 | 2011 | Active Army | Minor Construction - UMMCA | TX | TEXAS | Fort Bliss | 066717 | Military Working Dog Facility | 2013-05-30 | 2013-08-05 | Sunlight Enterprises Co., Inc | 1780.487 | 1811.605 | 2013-08-27 | 2014-09-17 | 2014-07-22 | 2014-08-15 | 93.8042
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 001235 | Physical Fitness Facility (PFF - Large) - (PN 01235) | 2012-01-06 | 2012-06-19 | Grahams Construction Inc. | 23138.91 | 23149.051 | 2012-07-12 | 2015-03-16 | 2014-04-10 | 2015-01-01 | 51.3226
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Joint Base San Antonio | 005034 | Tactical Equipment Maintenance Facility, FSH | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | 8603 | 9101.83 | 2013-01-24 | 2015-05-29 | 2014-07-18 | 2015-04-14 | 51.6807
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Joint Base San Antonio | 005034 | Tactical Equipment Maintenance Facility, FSH | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | 0 | 4150 | 2013-01-24 | 2015-05-29 | 2014-07-18 | 2015-05-29 | 45
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 017220 | Fire Station/Emergency Dispatch | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | 12622.8 | 12622.8 | 2013-11-06 | 2016-01-12 | 2015-11-11 | 2015-11-11 | 9.898
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 020697 | Chapel Complex | 2012-01-30 | 2012-08-30 | Liberty Mutual Insurance Company | 12999.823 | 13041.417 | 2012-09-20 | 2015-06-30 | 2014-01-28 | 2015-04-30 | 37.4992
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | McAlester Army Ammo Plant | 058207 | MCAAP AP3 MainLine RR Tracks | 2011-11-28 | 2012-03-26 | McAlester Contract | 6323.7745 | 6323.7745 | 2012-05-09 | 2014-12-02 | 2013-10-06 | 2014-09-15 | 62.9255
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 058537 | Reception Station Ph 1 (PN 58537) | 2011-12-02 | 2012-05-23 | Zachry Federal Construction Corporation | 32234.496 | 33035.398 | 2012-06-15 | 2014-09-15 | 2014-03-26 | 2014-10-01 | 92.0706
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 064415 | BCT Complex (MEB HQ & MEB COF) | 2011-12-16 | 2012-08-17 | The Ross Group Construction Corporation | 11856.9 | 12224.6292 | 2012-10-09 | 2014-10-19 | 2014-04-02 | 2014-08-30 | 86.2416
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 064415 | BCT Complex (MEB HQ & MEB COF) | 2012-02-21 | 2012-03-23 | Blackhawk Ventures, LLC | 10283 | 10964.2248 | 2012-05-15 | 2014-09-20 | 2013-11-06 | 2014-09-08 | 89
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 064753 | TEMF Complex (aka-Fires Brigade Complex) Ph 1 - (PN 64753) | 2012-01-17 | 2012-06-29 | Harper Construction Company, Inc. | 37867.635 | 38167.363 | 2012-07-19 | 2014-07-03 | 2014-04-11 | 2014-07-03 | 83.7696
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 064753 | TEMF Complex (aka-Fires Brigade Complex) Ph 1 - (PN 64753) | 2012-01-09 | 2012-07-13 | GSC Construction, Inc. | 6094.722 | 6094.722 | 2012-09-26 | 2015-07-15 | 2014-02-03 | 2015-07-15 | 42.3506
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 065374 | Operational Readiness Training Complex | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | 38503 | 39398.127 | 2012-09-05 | 2015-03-09 | 2014-07-28 | 2014-11-24 | 58.9893
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 065374 | Operational Readiness Training Complex | 2012-07-19 | 2013-01-07 | Turner Strategic Technologies, LLC | 8195.202 | 8267.659 | 2013-03-08 | 2015-05-15 | 2014-11-28 | 2014-12-15 | 71.8764
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Red River Army Depot | 066691 | Maneuver Systems Sustainment Center, Phase 3 | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | 40532.114 | 40793.3202 | 2014-03-04 | 2015-02-28 | 2014-04-24 | 2015-04-07 | 60.9576
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | LA | LOUISIANA | Fort Polk | 067033 | Multipurpose Machine Gun Range (MPMG) | 2012-03-13 | 2012-08-03 | Jamco Ventures, LLC. | 8493 | 8536.2517 | 2012-10-25 | 2014-09-30 | 2013-10-25 | 2014-08-08 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 068993 | Electronics Maintenance Facility - Tier 2 | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | 9573 | 9573 | 2012-08-08 | 2014-07-14 | 2013-12-16 | 2014-07-14 | 99.8282
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 068993 | Electronics Maintenance Facility - Tier 2 | 2011-12-16 | 2013-09-20 | Venegas Engineering & Management Construction Company | 5117.965 | 5117.965 | 2012-08-20 | 2014-12-30 | 2014-05-05 | 2014-12-30 | 97.7618
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 069286 | Utility Feed for Industrial Complex | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | 9008.411 | 8732.566 | 2012-08-20 | 2014-12-30 | 2013-09-13 | 2014-12-30 | 97.5585
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 069828 | Unmanned Aerial Systems | 2013-07-16 | 2014-05-29 | JAM-MAP JV | 8829.807 | 8829.807 | 2014-08-04 | 2016-11-01 | 2016-07-27 | 2016-08-10 | 0
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 070514 | THAAD Battery III | 2011-12-15 | 2012-03-30 | Urban Associates, Inc. | 9815.87 | 10561.552 | 2012-05-30 | 2014-04-30 | 2013-09-13 | 2014-01-10 | 99.8827
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 070514 | THAAD Battery III | 2011-12-15 | 2013-09-20 | J&M Contractors | 3921.5 | 3931.5 | 2012-05-31 | 2014-03-07 | 2014-05-05 | 2014-06-14 | 100
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071682 | THAAD Battery (TEMF and COF) | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | 9669.4345 | 10104.662 | 2012-06-22 | 2014-09-30 | 2013-12-14 | 2014-08-31 | 83.5601
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071682 | THAAD Battery (TEMF and COF) | 2011-12-19 | 2013-12-04 | Soulis Constructors. Inc | 5786.309 | 5786.309 | 2012-08-24 | 2015-09-01 | 2015-07-09 | 2015-07-09 | 13
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 074690 | Terminal High Altitude Air Defense - THAAD | 2012-01-06 | 2012-03-29 | Roy Anderson Corp. | 25942 | 26663.384 | 2012-07-26 | 2014-08-29 | 2014-04-16 | 2014-08-22 | 92.498
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 074845 | Water Well, Non Potable | 2012-01-04 | 2012-08-01 | Bailey CKY JV | 2248.08 | 2251.435 | 2012-08-28 | 2013-10-30 | 2013-05-25 | 2013-07-02 | 99.2005
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 077187 | THAAD Battery (TEMF, COF, and ACP) | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | 7472.9455 | 7802.2463 | 2012-06-22 | 2017-04-24 | 2013-12-14 | 2014-08-31 | 82.2837
2014-07-31 | 2014-08-14 | 2012 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 077187 | THAAD Battery (TEMF, COF, and ACP) | 2011-12-19 | 2013-12-04 | Soulis Constructors. Inc | 5378.708 | 5838.2959 | 2014-01-15 | 2015-09-01 | 2015-07-09 | 2015-07-09 | 13
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | TX | TEXAS | Fort Bliss | 066911 | Multi-purpose Machine Gun Range (MPMG) | 2012-12-21 | 2013-05-13 | Blackhawk Ventures, LLC | 6397 | 6434.605 | 2013-06-10 | 2014-06-27 | 2014-07-05 | 2014-07-10 | 100
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 067020 | Modified Record Fire Range | 2012-11-30 | 2013-05-31 | Better Built Construction Services, Inc | 4094.684 | 4099.3545 | 2013-08-02 | 2014-09-16 | 2014-09-05 | 2014-09-05 | 80.7349
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | OK | OKLAHOMA | Fort Sill | 067037 | Modified Record Fire Range | 2012-12-07 | 2013-06-13 | Diversified Construction of Oklahoma, Inc. | 4160.3398 | 4160.3398 | 2013-09-16 | 2014-11-03 | 2014-08-10 | 2014-08-08 | 66.506
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 071120 | Training Support Center | 2013-03-08 | 2013-09-04 | PENTACON, LLC | 21912 | 21912 | 2013-10-17 | 2015-06-09 | 2015-04-10 | 2015-05-25 | 16.4026
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 080113 | Unmanned Aerial Vehicle Complex | 2013-04-25 | 2013-08-15 | J&S Construction Company, Inc | 11491.27 | 11345.483 | 2013-10-07 | 2015-10-01 | 2015-05-30 | 2015-06-01 | 35.4735
2014-07-31 | 2014-08-14 | 2013 | Active Army | Major Construction | TX | TEXAS | Fort Hood | 080113 | Unmanned Aerial Vehicle Complex | 2013-03-12 | 2014-05-29 | JAM-MAP JV | 590 | 590 | 2014-08-04 | 2016-11-01 | 2016-07-27 | 2016-07-27 | 0
2014-07-31 | 2014-08-14 | 2013 | Active Army | Minor Construction - UMMCA | LA | LOUISIANA | Fort Polk | 081515 | CIDC Field Operations Building | 2013-05-21 | 2013-09-29 | Guyco, Inc. | 1784.466 | 1779.289 | 2013-12-04 | 2015-02-02 | 2014-12-04 | 2014-12-04 | 48.4739
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const Incremental | FL | FLORIDA | MacDill AFB | 52330 | Clinic Replacement | 2007-02-16 | 2007-07-19 | Caddell Construction Co., Inc | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2007-06-30 | 2007-09-29 | Cont # 1 - Offiste San Sewer & Storm (James Construction) | 2657 | 2657 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 100
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2008-01-10 | 2008-08-01 | Con # 2 - Storm Lat 1&3A (James Construction) | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 100
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2008-05-01 | 2009-09-28 | Con# 3 - IMP Pond (James Corporation) | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 100
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2008-01-10 | 2008-09-25 | Cont # 4 - Early Site/Utility (Grunley/Goel JVA LLC) | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 100
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 1 |  | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | 2866 | 2866 | 2008-07-15 | 2013-12-06 | 2011-05-06 | 2013-10-31 | 100 | 2289 |  |  | Solicitation/Advertise Date is N/A - SSP Mod
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 64238 | Hospital Replacement, Increment 1 | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV | 649025 | 9428 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const Incremental | FL | FLORIDA | MacDill AFB | 67647 | Clinic Replacement, Inc II | 2007-02-16 | 2007-07-19 | Caddell Construction Co., Inc | 32890 | 42183 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | FL | FLORIDA | MacDill AFB | 64809 | Pharmacare Addition/Alteration | 2007-09-27 | 2008-02-29 | J2 Engineering, Inc | 3381 | 3489 | 2008-03-24 | 2009-03-24 | 2009-03-24 | 2009-03-24 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | IL | ILLINOIS | NH Great Lakes | 65028 | Federal Healthcare Facility | 2007-10-01 | 2008-02-27 | Flannery Fire Protection | 6781.5 | 7382 | 2008-04-01 | 2009-09-02 | 2009-09-02 | 2009-09-02 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | IL | ILLINOIS | NH Great Lakes | 65028 | Federal Healthcare Facility | 2008-02-22 | 2008-06-17 | Walsh Construction Company of Illinois | 71567 | 75921 | 2008-08-01 | 2010-10-01 | 2010-08-27 | 2010-09-27 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const BRAC | MD | MARYLAND | Bethesda Naval Hospital | 005V | Medical Center Addition/Alteration, Inc 1 | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | 757737 | 774314 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const BRAC | MD | MARYLAND | Bethesda | 701V | Consolidation of Administration Spaces (WTU Admin) | 2014-04-09 | 2009-08-26 | Whiting-Turner | 68529 | 78196 | 2010-02-01 | 2011-08-01 | 2011-08-01 | 2011-09-11 | 100 |  |  |  | Soliciation/Advertise Date is for PH II
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | NY | NEW YORK | Fort Drum | 63864 | Health Clinic Add/Alt | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | 27483 | 35963 | 2008-11-07 | 2012-12-01 | 2011-02-18 | 2013-12-12 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | TX | TEXAS | Camp Bullis | 17153 | Health Clinic Replacement | 2008-02-15 | 2008-05-08 | Guyco, Inc. | 5214 | 5430 | 2008-05-08 | 2009-11-18 | 2009-11-16 | 2010-03-17 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 64179 | San Antonio Regional Medical Center, Inc 1 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 107589 | 135926 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 64188 | Health Clinic | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | 33382 | 37382 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | TX | TEXAS | Fort Sam Houston | 69626 | Burn Rehabilitation Center | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | 18512 | 19120 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 64238 | Hospital Replacement, Increment 2 | 2007-06-12 | 2008-04-04 | Turner/Gilbane JV | 649025 | 376782 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | VA | VIRGINIA | NS Norfolk | 53577 | Environ. Prev. Med Unit 2 Replacement | 2008-10-31 | 2009-03-31 | Virtexco Corporation | 5951 | 6558 | 2009-05-01 | 2010-10-15 | 2010-05-04 | 2010-09-08 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | WA | WASHINGTON | Fort Lewis | 64473 | Medical/Dental Clinic | 2008-07-29 | 2008-09-18 | The Korte Company | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 100 | 1885
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | DEU | GERMANY | Spangdahlem AB | 52332 | Medical Clinic Replacement | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | CO | COLORADO | Buckley AFB | 64709 | Satellite Pharmacy | 2009-03-04 | 2009-05-21 | Liberty-Mass II | 1963 | 2014 | 2009-07-01 | 2010-09-03 | 2010-09-09 | 2010-09-09 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | GA | GEORGIA | Fort Benning | 65080 | Consolidated Troop Medical Clinic | 2008-11-12 | 2009-02-25 | Mathis and Sons, Inc. | 2983 | 3084 | 2009-03-16 | 2010-05-07 | 2010-03-16 | 2010-05-07 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | KY | KENTUCKY | Fort Campbell | 64573 | Medical/Dental Clinic | 2008-12-10 | 2009-05-26 | The Korte Company | 14342 | 14699.754 | 2009-05-22 | 2011-03-30 | 2011-05-15 | 2011-03-30 | 100 | 5367
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const BRAC | MD | MARYLAND | Bethesda | 020V | Site Utility Infra Upgrade for NICoE | 2008-07-08 | 2008-12-22 | Turner Construction Company | 7294.531 | 7371 | 2009-01-01 | 2010-03-29 | 2010-03-06 | 2010-04-30 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const BRAC | MD | MARYLAND | Bethesda | 796V | Supt Fac for WTC Admin Ctr (BQ/Dining) | 2014-04-09 | 2009-08-26 | Whiting-Turner | 117555 | 126445 | 2010-02-01 | 2011-07-13 | 2011-05-31 | 2011-09-11 | 100 |  |  |  | Soliciation/Advertise Date is for PH II
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | MD | MARYLAND | Bethesda | 75585 | Vision Center of Excellence | 2010-02-17 | 2010-06-25 | Clark/Balfour Beatty, Joint Venture | 3900 | 3900 | 2011-03-01 | 2011-07-21 | 2011-07-31 | 2011-07-31 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 65731 | USAMRICD Replacement, Inc 1 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | 6887.87 | 7070.1979 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | MO | MISSOURI | Fort Leonard Wood | 59987 | Primary Care Clinic Addition/Alteration | 2009-04-15 | 2009-07-15 | MAXFour Weitz JV | 13627 | 14503 | 2009-08-24 | 2011-07-28 | 2011-05-30 | 2011-07-28 | 100 | 1500
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const BRAC | MS | MISSISSIPPI | Keesler AFB | 478V | Community Hospital | 2009-04-09 | 2009-11-10 | W.G. Yates & Sons Constuction Co | 38252 | 42256 | 2010-01-01 | 2012-02-25 | 2011-09-11 | 2012-10-11 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Sam Houston | 53341 | Medical Instructional Facility | 2008-11-13 | 2009-02-20 | Innovative Technology Solutions, Inc | 10432 | 15334 | 2010-01-27 | 2012-08-14 | 2010-06-02 | 2010-11-12 | 100 | -1538.8993
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 64180 | Brooke Army MEDCEN Increment 2 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 265100 | 279273 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 65676 | Hospital Replacement, Increment 3 | 2007-06-12 | 2008-12-23 | Turner/Gilbane JV | 649025 | 241353 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | GU | GUAM | NH Guam | 55918 | Central Utility Plant | 2009-03-15 | 2009-09-15 | PDI - HSW Joint Venture | 13034 | 13672 | 2009-10-01 | 2011-06-22 | 2011-02-07 | 2011-06-22 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | AK | ALASKA | Elmendorf AFB | 71310 | Aeromedical Services/Mental Health Clinic | 2009-09-18 | 2010-02-25 | Davis Constructors & Engineers, Inc. | 19839 | 20258 | 2010-03-11 | 2011-11-29 | 2011-10-15 | 2011-11-29 | 100 | -577
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | AK | ALASKA | Fort Richardson | 69805 | Health Clinic Add/Alt | 2009-11-30 | 2010-02-10 | Bristol Design Build Services LLC | 3087 | 3140 | 2010-02-22 | 2011-03-18 | 2011-05-23 | 2011-03-18 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | CO | COLORADO | Fort Carson | 69295 | Health and Dental Clinics | 2010-04-26 | 2010-09-23 | Korte Construction Company | 17616 | 18171 | 2010-10-20 | 2012-02-27 | 2012-02-13 | 2012-02-27 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | GA | GEORGIA | Fort Benning | 64481 | Blood Donor Center Replacement | 2009-11-05 | 2010-09-24 | IAP-Leopardo | 7792 | 7904 | 2010-11-12 | 2012-08-05 | 2012-05-05 | 2012-05-05 | 100 | -3185
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | GA | GEORGIA | Fort Benning | 71620 | Dental Clinic | 2009-12-23 | 2010-03-31 | EJS Contracting, Inc. | 2549 | 2619 | 2010-04-28 | 2011-03-11 | 2011-04-28 | 2011-03-11 | 100 | -168
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | GA | GEORGIA | Fort Stewart | 70481 | Health and Dental Clinics | 2009-11-25 | 2010-09-30 | Brafield & Gorrie, LLC | 9742 | 10101 | 2010-10-21 | 2012-06-04 | 2012-03-22 | 2012-03-22 | 100 | -818
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | KY | KENTUCKY | Fort Campbell | 70557 | Health Clinic Addition/Alteration | 2010-04-12 | 2010-09-27 | Charpie-Korte Joint Venture | 4018 | 4034 | 2010-09-30 | 2011-06-30 | 2012-02-05 | 2011-06-30 | 100 | -2278
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const BRAC | MD | MARYLAND | Bethesda | 401V | Traffic Mitigation Increment 1 | 2010-03-05 | 2010-05-10 | Clark/Balfour Beatty, Joint Venture, Gates N&S Wood Dr | 9512 | 10848 |  | 2011-08-15 | 2011-07-31 | 2011-08-15 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67180 | USAMRICD Replacement, Inc 2 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67180 | USAMRICD Replacement, Inc 2 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 4 |  | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | 496 | 525 | 2008-07-15 | 2013-10-31 | 2011-05-06 | 2013-10-31 | 100 |  |  |  | Solicitation/Advertise Date is N/A - SSP Mod
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 61536 | Emergency Service Center | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | 13478 | 13858 | 2010-07-19 | 2013-05-23 | 2012-09-16 | 2013-05-23 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 67948 | NIBC Truck Inspection Station & Road | 2010-09-02 | 2010-10-29 | CFM Engineering | 2880 | 3132 | 2010-12-15 | 2012-07-05 | 2011-12-15 | 2012-07-05 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | MO | MISSOURI | Fort Leonard Wood | 64153 | Dental Clinic Addition/Alteration | 2009-10-20 | 2010-07-02 | TMG Services | 3890 | 4319 | 2010-07-22 | 2012-03-19 | 2012-01-13 | 2012-03-15 | 100 | -712
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | NC | NORTH CAROLINA | Fort Bragg | 64244 | Consolidated Health Clinic | 2009-10-28 | 2010-09-30 | Korte Construction Company | 15313 | 16186 | 2010-10-21 | 2012-10-26 | 2012-05-18 | 2012-10-26 | 100 | -6655
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | NC | NORTH CAROLINA | Fort Bragg | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 100 | -458
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | OK | OKLAHOMA | Fort Sill | 69711 | Dental Clinic | 2009-11-03 | 2010-06-16 | The Korte Company | 8199 | 8199 | 2010-07-30 | 2012-03-04 | 2012-01-04 | 2012-01-04 | 100 | -1016
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | TX | TEXAS | Lackland AFB | 72430 | Ambulatory Care Center, Phase 1 A | 2010-06-11 | 2010-08-31 | J E Dunn Construction Company (Parking Structure & Temp Parking)) | 23216 | 24153 | 2010-10-04 | 2012-12-13 | 2012-02-26 | 2012-11-30 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 69840 | Brooke Army MEDCEN Increment 3 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 13748 | 243943 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. - Infrastructure | 39345 | 47508 | 2011-11-02 | 2013-10-12 | 2013-08-13 | 2013-08-29 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2011-03-25 | 2011-06-17 | Janco - Water Tower | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2012-03-16 | 2012-07-19 | VEMAC - Parking Pkg A | 3848 | 3879 | 2012-08-28 | 2013-10-17 | 2013-06-19 | 2013-06-11 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2012-02-08 | 2012-09-04 | El Paso Electrical Substation | 4047 | 4047 | 2012-09-04 | 2015-09-16 | 2014-01-04 | 2014-01-04 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | TX | TEXAS | Fort Bliss | 69294 | Health and Dental Clinics | 2010-02-17 | 2010-11-17 | LEC-CMS, LP | 12743 | 13018 | 2011-02-07 | 2012-08-20 | 2012-05-22 | 2012-12-31 | 100 | -3280
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | TX | TEXAS | Lackland AFB | 71318 | Dental Clinic Replacement | 2009-10-28 | 2010-02-26 | J E Dunn Construction Company | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 100 | -3144.239
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | TX | TEXAS | Lackland AFB | 72430 | Ambulatory Care Center, Phase 1 B | 2010-06-11 | 2010-08-19 | J E Dunn Construction Company (Bldg 1 & CEP) | 41566 | 45105 | 2010-10-04 | 2013-11-19 | 2013-02-20 | 2013-08-30 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 69865 | Hospital Replacement, Increment 4 | 2007-06-12 | 2010-01-23 | Turner/Gilbane JV | 649025 | 119266 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 64241 | Dental Clinic | 2009-09-16 | 2010-05-04 | Forrester Construction Company | 7541 | 8818 | 2010-05-18 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | WA | WASHINGTON | Fort Lewis | 70343 | Health and Dental Clinic Additions | 2009-12-04 | 2010-03-24 | Vet Industrial of Bremerton, WA | 7219 | 7583 | 2010-04-19 | 2011-05-13 | 2011-05-07 | 2011-05-02 | 100 | -2109
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | GBR | UNITED KINGDOM | RAF Alconbury | 71550 | Medical/Dental Clinic Replacement | 2010-06-16 | 2010-12-14 | Vinci Construction UK | 13097.501 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | GBR | UNITED KINGDOM | RAF Alconbury | 71550 | Medical/Dental Clinic Replacement - Sidewalk | 2013-04-05 | 2013-06-15 | VolterFitzpatrick | 68 | 68 | 2013-07-01 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 100
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | GBR | UNITED KINGDOM | RAF Alconbury | 71550 | Medical/Dental Clinic Replacement | 2010-06-16 | 2010-12-14 | Vinci Construction UK | 13165.501 | 12489 |  | 2013-10-12 |  |  | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | GA | GEORGIA | Fort Stewart | 70482 | Health Clinic Addition/Alteration | 2010-11-19 | 2011-06-03 | McCarthy Building Companies | 23050 | 26510 | 2011-06-21 | 2013-11-29 | 2013-06-20 | 2014-05-06 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MA | MASSACHUSETTS | Hanscom AFB | 71634 | Mental Health Clinic Addition | 2011-11-04 | 2011-12-23 | Watermark Environmental, Inc. | 2790 | 2790 | 2012-05-18 | 2013-02-16 | 2013-01-16 | 2013-03-01 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const BRAC | MD | MARYLAND | Bethesda | 401V | Traffic Mitigation Increment 1 | 2010-03-16 | 2010-06-21 | Whiting-Turner, University Road & Perimeter Road/Palmer Road | 8800 | 10291 | 2010-07-01 |  | 2011-08-31 | 2011-08-23 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const BRAC | MD | MARYLAND | Bethesda | 401A | Traffic Mitigation Increment 2 | 2010-11-14 | 2011-04-21 | RMA Land Construction Inc, Gates Gunnell & Grier | 5572 | 5982 |  | 2012-09-02 | 2012-12-06 | 2012-11-26 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MD | MARYLAND | Bethesda Naval Hospital | 77116 | NNMC Parking Expansion | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | 14030 | 14392 | 2012-06-18 | 2013-12-02 | 2014-02-02 | 2014-07-18 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MD | MARYLAND | Bethesda Naval Hospital | 77115 | Transient Wounded Warrior Lodging | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | 48133 | 48829 | 2012-06-18 | 2014-05-27 | 2014-02-02 | 2014-07-18 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 67949 | NIBC Security Fencing and Equipment | 2011-08-19 | 2012-02-14 | Cont # 1 (Segment 1) (Rich Moe Enterprises, LLC) | 1701 | 1701 | 2012-04-02 | 2013-04-01 | 2013-04-02 | 2013-04-01 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement Stage I, Increment 5 |  | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | 603 | 638 | 2008-07-15 | 2013-10-31 | 2011-05-06 | 2013-10-31 | 100 |  |  |  | Solicitation/Advertise Date is N/A - SSP Mod
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | NM | NEW MEXICO | White Sands Missile Range | 70472 | Health and Dental Clinic | 2010-11-02 | 2011-07-22 | Charpie-Korte Dsn-Bld JV S.B. L.L. | 14837 | 15067 | 2011-08-18 | 2013-04-26 | 2013-03-30 | 2013-08-02 | 100 | -1095
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const BRAC | TX | TEXAS | Fort Sam Houston | 70990 | Brooke Army MEDCEN Increment 4 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | 37554 | 85520 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const BRAC | VA | VIRGINIA | Fort Belvoir | 77071 | Hospital Replacement, Increment 5 | 2007-06-12 | 2010-10-20 | Turner/Gilbane JV | 649025 | 211800 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | VA | VIRGINIA | Fort Belvoir | 71251 | Dental Clinic Replacement | 2009-09-16 | 2011-05-17 | Forrester Construction Company | 2832 | 3185 | 2011-05-17 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | WA | WASHINGTON | Fort Lewis | 47344 | Preventive Medicine Facility | 2011-05-03 | 2011-09-13 | Charpie-Korte Group LLC | 7230 | 7676 | 2011-10-14 | 2013-02-28 | 2013-02-28 | 2013-02-28 | 100
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | KOR | KOREA | Camp Carroll | 51740 | Health/Dental Clinic Replacement | 2011-05-13 | 2011-08-26 | Ilsung Construction Co., Ltd. | 9821 | 10169 | 2011-08-26 | 2014-04-23 | 2013-05-13 | 2014-04-23 | 100
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | MD | MARYLAND | NSA Bethesda (WRNMMC) | 79554 | Child Development Center | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | 14200 | 14457 | 2013-03-01 | 2014-04-07 | 2014-02-22 | 2014-06-02 | 100
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 76007 | Medical Center Replacement, Incr 1 |  | 2012-03-15 | Lot 1 Temporary Construction Fence | 290 | 290 | 2014-01-20 |  | 2014-04-04 | 2014-04-04 | 100
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | MD | MARYLAND | NSA Bethesda (WRNMMC) | 80306 | Temporary Facilities - Dosimetry Award | 2013-07-25 | 2012-09-12 | G-W Management Servicxes Inc | 5286 | 5217 | 2013-10-15 | 2014-04-04 | 2013-12-13 | 2014-03-25 | 100
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | NC | NORTH CAROLINA | Camp Lejeune | 71857 | Hospital Addition | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | 31112 | 32791 | 2010-12-03 | 2013-07-15 | 2013-01-12 | 2013-07-15 | 100 | 3486
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | CA | CALIFORNIA | Camp Pendleton | 71653 | Hospital Replacement, (ARRA) | 2010-06-11 | 2010-09-01 | Clark/McCarthy, A joint Venture | 418039 | 425895 | 2010-12-03 | 2013-10-17 | 2014-01-07 | 2014-01-07 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | CO | COLORADO | Fort Carson | 70350 | Hospital Alteration (ARRA) | 2011-07-26 | 2011-09-15 | Federal Contracting dba Bryan Construction | 15929 | 20393 | 2011-11-08 | 2014-03-23 | 2013-11-27 | 2014-01-21 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | FL | FLORIDA | NAS Jacksonville | 971B | Hospital Alteration (ARRA) | 2009-09-09 | 2009-12-18 | Brasfield & Gorrie, LLC | 8000 | 13282 | 2010-01-20 | 2011-12-11 | 2011-12-11 | 2011-12-11 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Hood | 74728 | Hospital Replacement, Electrical Funding (100% ARRA) | 2010-05-21 | 2010-06-11 | RMA Land Construction, Inc., Infrastructure, Electrical Distribution & Telecomm | 9698 | 10156 | 2010-07-20 | 2012-09-20 | 2012-07-26 | 2012-09-20 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Hood | 74650 | Sanitary Sewer | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc, Sanitary Sewer | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Hood | 74650 | Relocation of Gas & Electric Utilities | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Hood | 74650 | Demolition of Hood Stadium | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc., Demolition of Hood Stadium | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Hood | 74650 | Ambulatory Care Center, Phase 1 | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities | 1341 | 1341 |  | 2010-06-30 |  |  | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Hood | 74650 | New Stadium | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. New Stadium | 17290 | 15383 | 2011-01-06 | 2013-12-15 | 2012-06-29 | 2013-12-15 | 100
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | OH | OHIO | Wright-Patterson AFB | 72722 | Tree Cutting | 2011-03-07 | 2011-03-20 | A1 Tree Service | 9.6 | 9.6 | 2011-03-20 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 100
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | IL | ILLINOIS | NAVHOSP Great Lakes | 65030 | Naval Hospital Great Lakes Health Clinic Demolition | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co | 5835 | 6195 | 2012-09-12 | 2014-04-21 | 2013-09-13 | 2014-07-31 | 99 | -3994
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const BRAC | MD | MARYLAND | Aberdeen Proving Ground | 64156 | USAMRICD Replacement, Inc 1 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contractor for main building) | 14398 | 15704.9853 | 2010-03-15 | 2014-08-30 | 2013-06-01 | 2014-08-30 | 98
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 65731 | USAMRICD Replacement, Inc 1 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 12000 | 12562.6925 | 2010-03-15 | 2014-08-30 | 2013-06-01 | 2014-06-30 | 98
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | OK | OKLAHOMA | Tinker AFB | 62189 | Medical/Dental Clinic Replacement | 2008-10-27 | 2009-04-03 | Hensel Phelps | 47615 | 51375 | 2009-06-01 | 2012-06-04 | 2011-10-26 | 2012-02-09 | 98
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67180 | USAMRICD Replacement, Inc 2 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 100375 | 103745.3283 | 2010-03-15 | 2014-08-30 | 2013-06-01 | 2014-06-30 | 98
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67181 | USAMRICD Replacement, Inc 3 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 94608 | 96044.5065 | 2010-03-15 | 2014-08-30 | 2013-06-01 | 2014-06-30 | 98
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 67182 | USAMRICD Replacement, Inc 4 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 7915.345 | 24291.6859 | 2010-03-15 | 2014-08-30 | 2013-06-01 | 2014-06-30 | 98
2014-07-31 | 2014-08-14 |  | DHA | Major Const Incremental | MD | MARYLAND | Aberdeen Proving Ground | 65731 | USAMRICD Replacement | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | 282746.345 | 309919.1985 | 2010-03-15 | 2014-08-30 | 2013-06-01 | 2014-06-30 | 98
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | GA | GEORGIA | Fort Benning | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) | 2009-04-08 | 2009-09-28 | Turner Construction Co., Inc | 230018 | 273633 | 2009-10-22 | 2014-05-19 | 2013-02-03 | 2014-05-19 | 95
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const | KS | KANSAS | Fort Riley | 47298 | Hospital Replacement | 2009-02-06 | 2009-09-30 | Balfour Beatty/Walton JV | 324110 | 282778 | 2010-05-03 | 2015-07-01 | 2013-07-23 | 2015-01-30 | 95
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | GU | GUAM | NAVHOSP Guam | 65270 | Hospital Replacement Increment 1 | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | 158132.5 | 165395 | 2010-11-01 | 2014-03-18 | 2014-10-15 | 2015-03-27 | 95 | -19460
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | IL | ILLINOIS | Scott AFB, IL | 72718 | Medical Logistics Warehouse Replacement | 2012-10-18 | 2013-06-18 | R&W Builders | 2215.9 | 2215.9 | 2013-07-01 | 2014-07-30 | 2014-04-27 | 2014-07-23 | 95
2014-07-31 | 2014-08-14 | 2007 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 58395 | USAMRIID Replacement, Incr 1 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 15736 | 16161 | 2009-06-01 | 2015-07-01 | 2014-05-31 | 2014-10-21 | 93
2014-07-31 | 2014-08-14 | 2008 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 63418 | USAMRIID Replacement, Incr 2 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 131264 | 138491 | 2009-06-01 | 2015-07-01 | 2014-05-31 | 2014-10-21 | 93
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 63419 | USAMRIID Replacement, Incr 3 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 185526 | 185630 | 2009-06-01 | 2015-07-01 | 2014-05-31 | 2014-10-21 | 93
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 63420 | USAMRIID Replacement, Incr 4 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 94000 | 100180 | 2009-06-01 | 2015-07-01 | 2014-05-31 | 2014-10-21 | 93
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 65324 | USAMRIID Replacement, Incr 5 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 13497 | 12893 | 2009-06-01 | 2015-07-01 | 2014-05-31 | 2014-10-21 | 93
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | TX | TEXAS | Lackland AFB | 72752 | Ambulatory Care Center Phase 2 | 2011-05-20 | 2011-09-28 | SKANSKA USA Building Inc. | 80558 | 91375 | 2011-12-02 | 2015-01-29 | 2013-10-01 | 2014-12-31 | 93
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 71101 | USAMRIID Replacement, Incr 6 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 66955 | 82773 | 2009-06-01 | 2015-07-01 | 2014-05-31 | 2014-10-21 | 93
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | OH | OHIO | Wright-Patterson AFB | 72722 | Swing Space | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp | 5578.1 | 5578 | 2011-07-01 | 2011-12-05 | 2014-09-27 | 2014-09-27 | 93
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 67953 | Supplemental Water Storage | 2011-02-18 | 2011-06-30 | FutureNet Group | 3468 | 3944 | 2011-07-20 | 2014-09-28 | 2012-11-01 | 2014-05-30 | 91 | 263
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 61401 | Boundary Gate at Nallin Pond | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | 9075 | 10119 | 2011-01-12 | 2014-12-05 | 2013-01-10 | 2014-11-14 | 88 | 785
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | FL | FLORIDA | Eglin AFB | 79845 | Eglin Hospital Alteration | 2011-07-01 | 2011-09-23 | JE Dunn Construction | 51133 | 59375 | 2011-10-31 | 2015-03-08 | 2014-11-06 | 2014-12-08 | 88
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | FL | FLORIDA | Eglin AFB | 70597 | Medical Clinic | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | 8897 | 9103 | 2012-10-17 | 2015-01-05 | 2014-10-07 | 2014-10-07 | 84
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | TX | TEXAS | Fort Hood | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | 529989 | 554824 | 2010-11-08 | 2014-12-01 | 2014-05-31 | 2014-10-10 | 83
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | NC | NORTH CAROLINA | Camp Lejeune | 73599 | Hospital Renovation & MRI Addition (Cong Add) | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | 26178 | 27920 | 2010-12-03 | 2014-04-01 | 2015-01-02 | 2015-02-01 | 79
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 67951 | Water Treatment Plant Repair | 2011-08-12 | 2012-12-17 | Grimberg/Amatea GC JV | 14308 | 15378 | 2013-01-14 | 2014-11-28 | 2014-07-08 | 2014-11-17 | 74 | 5000
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | TX | TEXAS | Joint Base San Antonio | 72754 | Ambulatory Care Center Phase 3, Inc 1 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | 76038 | 73082 | 2012-11-01 | 2015-06-30 | 2014-07-29 | 2014-10-15 | 73
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const Incremental | TX | TEXAS | Joint Base San Antonio | 80793 | Ambulatory Care Center Phase 3, Increment 2 | 2012-05-09 | 2013-06-03 | Skanska USA Building Inc. | 16319 | 20131 | 2012-11-01 | 2015-06-30 | 2014-07-29 | 2014-10-15 | 73
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 73360 | Consolidated Logistics Facility | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | 19869 | 19957 | 2011-07-21 | 2014-09-05 | 2014-01-06 | 2014-08-31 | 70
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | MS | MISSISSIPPI | NCBC Gulfport | 71503 | Branch Health Clinic | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Constr, Inc | 19096 | 19604 | 2012-09-01 | 2014-09-09 | 2014-09-09 | 2014-11-21 | 70
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | NY | NEW YORK | Ft Drum | 70580 | Dental Clinic Addition /Alteration | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | 4370 | 4370 | 2013-01-09 | 2015-04-09 | 2015-01-09 | 2015-01-09 | 70
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | OH | OHIO | Wright-Patterson AFB | 72722 | Hospital Renovation (Supplemental) | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | 71356.39 | 79416 | 2011-10-25 | 2014-12-09 | 2014-09-09 | 2014-12-09 | 68
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | NY | NEW YORK | UMA West Point | 59220 | Hospital Addition/Alteration (Supplemental) | 2011-06-10 | 2011-09-28 | Morgan Construction Enterprises,Inc | 28500 | 29108 | 2011-10-26 | 2015-07-30 | 2014-03-03 | 2015-04-30 | 63
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | KY | KENTUCKY | Ft Campbell | 70438 | Hospital Addition/Alteration | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company (DBA: Mortenson Construction) | 43466 | 45624 | 2012-08-22 | 2015-05-23 | 2015-02-21 | 2015-03-19 | 61
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | GA | GEORGIA | Ft Stewart | 72292 | Hospital Addition/Alteration Phase 2 | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | 37778 | 42925 | 2012-10-15 | 2017-03-23 | 2016-10-14 | 2017-02-14 | 56
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | NC | NORTH CAROLINA | Ft Bragg | 70351 | Hospital Alteration | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | 22400 | 23219 | 2012-09-13 | 2014-09-30 | 2014-06-23 | 2014-10-27 | 54
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | MD | MARYLAND | Fort Detrick | 62886 | Information Services Facility Expansion | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | 4270 | 4626 | 2012-03-19 | 2015-02-10 | 2013-11-09 | 2014-12-12 | 53 | 232
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | TX | TEXAS | JB San Antonio | 51969 | Hospital Nutrition Care Department Add/Alt | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | 28291 | 26991 | 2012-10-02 | 2015-02-26 | 2014-10-30 | 2015-04-13 | 52
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | MO | MISSOURI | Ft. Leonard Wood | 71679 | Dental Clinic | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture | 10687 | 10687 | 2013-12-02 | 2015-06-19 | 2015-02-19 | 2015-02-19 | 51
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | NC | NORTH CAROLINA | Camp Lejeune | 78144 | Medical Clinic Addition | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | 14354 | 14370 | 2013-10-08 | 2015-03-31 | 2015-03-17 | 2015-07-08 | 47
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | NY | NEW YORK | Ft Drum | 70579 | Medical Clinic (SFCC) | 2012-10-05 | 2013-02-13 | Structural Associates. Inc. | 8934 | 8934 | 2013-03-15 | 2015-05-30 | 2015-03-11 | 2015-03-11 | 45
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 76558 | Fort Bliss Hospital Repl, Incr 4 | 2013-08-08 | 2013-09-13 | Helipad | 1540 | 655 | 2013-10-21 | 2014-11-24 | 2014-10-24 | 2014-10-24 | 43
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | DEU | GERMANY | Vilseck | 66588 | Health Clinic Add/Alt | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | 32103 | 32103 | 2013-04-08 | 2016-10-04 | 2016-04-12 | 2016-09-04 | 36
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | IL | ILLINOIS | Great Lakes Naval Tng Ctr | 78143 | Navy Drug Lab Replacement | 2013-01-14 | 2013-08-22 | Blinderman Constr Co | 14864 | 14864 | 2013-11-08 | 2015-02-15 | 2015-01-15 | 2015-01-15 | 35
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | KOR | KOREA | Kunsan AB | 72420 | Medical/Dental Clinic Addition | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. | 8544 | 8671 | 2013-06-05 | 2015-05-16 | 2015-02-25 | 2015-03-22 | 33
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | MD | MARYLAND | Joint Base Andrews | 77154 | Ambulatory Care Center | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | 196430 | 137051 | 2013-03-01 | 2016-12-06 | 2016-12-06 | 2017-11-08 | 25
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const Incremental | MD | MARYLAND | Joint Base Andrews | 81291 | Ambulatory Care Center, Incr 2 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | 196430 | 66430 | 2013-03-01 | 2016-12-06 | 2016-12-06 | 2017-11-08 | 25
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | 7782 | 11098 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 14
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 77251 | Fort Bliss Hospital Repl, Incr 2 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | 68076 | 68076 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 14
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72786 | Fort Bliss Hospital Repl, Incr 3 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | 69851 | 72931 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 14
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 76558 | Fort Bliss Hospital Repl, Incr 4 | 2012-08-07 | 2013-01-29 | Hospital Contract | 79914 | 160491 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 14
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 77293 | Fort Bliss Hospital Repl, Incr 5 | 2012-08-07 | 2013-01-29 | Hospital Contract | 198148 | 77700 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 14
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | SC | SOUTH CAROLINA | Shaw AFB, SC | 71317 | Medical Clinic Replacement | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | 38744 | 39890 | 2013-12-06 | 2017-10-08 | 2016-12-30 | 2017-08-16 | 13
2014-07-31 | 2014-08-14 | 2009 | DHA | Major Const | CA | CALIFORNIA | Fort Irwin | 70354 | Hospital Replacement (SUPPLEMENTAL) | 2011-12-19 | 2012-05-09 | Turner Construction Company | 159834.183 | 162387.283 | 2012-05-30 | 2017-07-25 | 2015-03-16 | 2016-08-22 | 11
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | VA | VIRGINIA | NOB Norfolk | 78146 | Veterinarian Facility | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | 7254 | 7274 | 2014-02-28 | 2015-05-15 | 2014-12-06 | 2015-05-05 | 10
2014-07-31 | 2014-08-14 | 2011 | DHA | Major Const | DEU | GERMANY | Katterbach | 66693 | Health/Dental Clinic Replacement | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | 34294 | 34376 | 2014-02-03 | 2016-06-11 | 2015-08-22 | 2016-04-12 | 9
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | CA | CALIFORNIA | MCB Twenty-Nine Palms | 72808 | Medical Clinic Replacement | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc | 18703 | 18703 | 2014-02-28 | 2015-04-16 | 2015-03-16 | 2015-03-16 | 9
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | NY | NEW YORK | Fort Drum | 73776 | Soldier Specality Care Clinic | 2012-11-15 | 2013-12-18 | Structural Associates | 11163 | 11163 | 2014-01-06 | 2016-04-05 | 2016-01-06 | 2016-01-06 | 8
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | KOR | KOREA | Osan AFB | 72419 | Hospital Addition/Alteration | 2013-07-26 | 2013-09-26 | Seohee Construction Co., Ltd. | 22361 | 22377 | 2013-09-26 | 2017-10-23 | 2017-08-08 | 2017-08-08 | 8
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | NC | NORTH CAROLINA | Seymour-Johnson AFB | 71325 | Medical Clinic Replacement | 2012-11-30 | 2013-09-16 | Heery International, Inc. | 45536 | 45672 | 2013-10-24 | 2017-07-21 | 2016-04-30 | 2016-10-23 | 7
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | GBR | UNITED KINGDOM | RAF Croughton | 72727 | Medical/Dental Clinic Replacement | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd | 11958 | 11958 | 2014-05-06 | 2015-07-31 | 2015-10-30 | 2015-10-30 | 6 | 13060
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | MD | MARYLAND | Annapolis | 71507 | Branch Health Clinic Replacement | 2013-02-28 | 2013-12-18 | Turner Construction Co | 41408 | 41433 | 2014-04-30 | 2016-04-04 | 2015-10-15 | 2015-11-18 | 6
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 76007 | Medical Center Replacement, Incr 1 |  | 2012-03-15 | Environmental Compensation | 16816 | 1731 | 2014-01-13 |  | 2021-07-20 |  | 5
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 76007 | Medical Center Replacement, Incr 1 |  | 2012-03-15 | Lot 2.1 Demolition, Site Clearing | 4806 | 681 | 2014-06-16 | 2014-08-29 | 2014-09-29 |  | 5
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | MD | MARYLAND | NSA Bethesda (WRNMMC) | 80307 | Implement Base Installation Appearance Plan | 2013-04-23 | 2013-09-27 | Allen & Shariff | 4898 | 4608 | 2014-04-01 | 2015-03-17 | 2015-03-31 | 2015-06-15 | 2
2014-07-31 | 2014-08-14 | 2010 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2013-02-19 | 2013-05-17 | El Paso Water Utility | 3960 | 2800 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-06-30 | 0
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const | MD | MARYLAND | Joint Base Andrews | 71408 | Dental Clinic Replacement | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | 18371 | 19488 | 2013-03-01 | 2016-12-06 | 2016-09-29 | 2017-01-28 | 0
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 76007 | Medical Center Replacement, Incr 1 |  | 2012-03-15 | Lot 2.2 Mass Grading | 14927 |  | 2014-09-15 | 2015-07-17 | 2015-08-17 |  | 0
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 76007 | Medical Center Replacement, Incr 1 |  | 2012-03-15 | Lot 3.2 Temp. Construction measures | 11730 |  | 2015-05-26 | 2016-04-29 | 2016-05-29 |  | 0
2014-07-31 | 2014-08-14 | 2012 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 76007 | Medical Center Replacement, Incr 1 |  | 2012-03-15 | Transformers/Substation | 21764 |  | 2015-01-21 | 2016-11-10 | 2016-12-10 |  | 0
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 78210 | USAMRIID Replacement, Incr 7 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | 0 | 0 | 2009-06-01 | 2015-07-01 | 2014-05-31 | 2014-10-21 | 0
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | MD | MARYLAND | NSA Bethesda (WRNMMC) | 80308 | Electrical Utility Upgrades | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | 26947 | 26947 |  |  | 2016-02-12 | 2016-02-12 | 0 | 19460
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const | NM | NEW MEXICO | Cannon AFB | 77979 | Medical/Dental Clinic Replacement | 2013-09-03 | 2014-03-27 | JE DUNN + HWA | 45938 | 45938 | 2014-04-28 | 2018-02-22 | 2017-10-25 | 2017-10-25 | 0
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 76558 | Fort Bliss Hospital Repl, Incr 4 |  |  | Parking Pkg B | 5562 | [5 empty] | 0
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 72661 | Medical Center Replacement, Incr 2 |  | 2013-08-27 | Lot 3.1 Construction Preparatory Measures | 56069 |  | 2014-11-03 | 2015-08-20 | 2015-09-29 |  | 0
2014-07-31 | 2014-08-14 | 2013 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 72661 | Medical Center Replacement, Incr 2 |  | 2013-08-27 | Lot 4 Access Control Point, Bridge, External Roadways | 60972 |  | 2015-09-21 | 2021-11-17 | 2021-12-17 |  | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 78210 | USAMRIID Replacement, Incr 8 | 2015-01-05 | 2015-06-01 | Cont # 6 (North Parking) (TBD) |  | 0 | 2015-07-15 | 2017-09-15 | 2016-07-15 | 2016-07-15 | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const Incremental | MD | MARYLAND | Fort Detrick | 78211 | USAMRIID Replacement, Incr 8 | 2017-04-01 | 2017-08-01 | Cont # 8 (South Parking/Demolition) (TBD) |  | 0 | 2019-08-22 | 2020-10-21 | 2020-08-22 | 2020-10-31 | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const | MD | MARYLAND | Aberdeen Proving Ground | 77000 | Public Health Command Laboratory Replacement | 2014-03-24 | 2014-09-26 |  |  |  | 2014-10-15 | 2018-04-08 | 2017-07-25 | 2018-01-09 | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const | MD | MARYLAND | NSA Bethesda (WRNMMC) | 80904 | Mechanical & Electrical Improvements | 2014-01-30 | 2014-11-24 | [7 empty] | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const | MD | MARYLAND | NSA Bethesda (WRNMMC) | 80913 | Parking Garage | 2014-05-30 | 2014-09-30 | [7 empty] | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const | NM | NEW MEXICO | Holloman AFB | 77922 | Medical Clinic Replacement | 2014-02-25 | 2014-08-20 |  |  |  | 2014-10-06 | 2018-06-12 | 2018-01-30 | 2018-01-30 | 0 | 23279
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 77293 | Fort Bliss Hospital Repl, Incr 5 | 2014-10-20 | 2014-12-20 | ACPs | 24755 |  | 2014-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const Incremental | TX | TEXAS | Fort Bliss | 77293 | Fort Bliss Hospital Repl, Incr 5 |  | 2014-09-01 | CAT E Equipment | 33125 | [5 empty] | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const | TX | TEXAS | Joint Base San Antonio | 81340 | SAMMC Hyperbaric Facility Addition | 2014-03-17 | 2014-06-30 | Gilbane | 11289 | 11289 |  | 2016-12-28 | 2016-09-30 | 2016-09-30 | 0 | 1900
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const | BHR | BAHRAIN | NBHC NSA Bahrain | 81436 | Medical/Dental Clinic Replacement | 2015-04-15 | 2015-08-15 | [7 empty] | 0
2014-07-31 | 2014-08-14 | 2014 | DHA | Major Const Incremental | DEU | GERMANY | Rhine Ordnance Barracks | 72662 | Medical Center Replacement, Incr 3 |  | 2014-08-14 | Lot 5.1 Parking Structures, Campus Roadways | 66545 |  | 2016-06-17 | 2021-11-17 | 2021-12-17 |  | 0
2014-07-31 | 2014-08-15 | 2009 | NSA | Major Construction | MD | MARYLAND | NSAW | 21120 | South Campus Electrical Utility Plant-SCEUP (Phase 1) | 2010-05-03 | 2010-08-30 | Clark/ MC Dean | 12060 | 13760 | 2010-09-21 | 2013-01-17 | 2014-04-18 | 2013-01-17 | 99 |  |  |  | AFCEE returned Additional Funds rom PAII back to Building 1045 Extension.
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17872 | South Campus Electrical Utility Plant -SCEUP (Phase 2) | 2010-05-03 | 2010-08-30 | Clark/ MC Dean | 113223 | 123688 | 2010-09-21 | 2014-05-13 | 2014-04-18 | 2014-08-28 | 90 | 37500 |  |  | The funds diverted in this project have not been assigned to other project at the present time.
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) | 2009-05-04 | 2010-08-26 | Goels/Grunley | 4443 | 4544 | 2010-09-09 | 2012-06-29 | 2011-09-26 | 2012-06-29 | 100 |  |  |  | The construction cost is $4,443,532.86, which $4,393,532.86 is for construction and $50,000 is for escorts.
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) | 2012-10-17 | 2013-02-19 | District Veterans Contracting | 5253 | 5423 | 2013-03-07 | 2014-09-30 | 2014-03-07 | 2014-09-30 | 86
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17781 | Tordella Chilled Water Backup Storage | 2009-08-24 | 2010-06-24 | Nothern Tiaga Venture,LLC Inc. (NTVI) | 11700 | 11700 | 2010-06-30 | 2012-05-30 | 2011-08-20 | 2012-05-30 | 100
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17782 | R&E Chilled Water Backup Storage | 2011-05-31 | 2011-08-30 | Walsh Construction Company | 3200 | 3200 | 2011-11-07 | 2014-10-31 | 2013-07-13 | 2015-02-27 | 78 |  |  |  | The projects have different Projects Number but one MILCON funding line.
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | GBR | UNITED KINGDOM | MHS | 18052 (MWHL10-3001) | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2011-03-15 | NPGL | 7566 | 8257 | 2011-03-31 | 2014-05-14 | 2013-02-01 | 2014-05-14 | 100
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | GBR | UNITED KINGDOM | MHS | 18053 (MWHL10-3001) | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2012-02-15 | IUS | 16095 | 16448 | 2012-01-31 | 2014-05-31 | 2013-02-01 | 2014-05-31 | 100
2014-07-31 | 2014-08-15 | 2010 | NSA | Major Construction | GBR | UNITED KINGDOM | MHS | 18054 (MWHL10-3001) | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | 7085 | 7316 | 2012-11-30 | 2014-08-31 | 2013-02-01 | 2014-08-31 | 84 |  |  |  | NEDL - Offsite work. IUS - Onsite. Power and Cooling Infrastructure Upgrade includes the Power Upgrade OFF Base, Power Upgrade On Base, Power DSS AA&BB, Power Water Borehole and Power UPS and Cooling
2014-07-31 | 2014-08-15 | 2011 | NSA | Major Construction | CL | CLASSIFIED LOCATION | Classified Location | 22573 | Classified Location | 2012-08-15 | 2012-09-30 | Kaseman | 12000 | 21500 | 2012-12-01 | 2013-10-01 | 2013-09-30 | 2014-03-15 | 99
2014-07-31 | 2014-08-15 | 2011 | NSA | Major Construction | CL | CLASSIFIED LOCATION | Classified Location | 22573 | Classified Location | 2012-08-01 | 2012-09-21 | Hardline | 12000 | 12000 | 2012-09-25 | 2012-09-15 | 2013-04-04 | 2013-04-04 | 100
2014-07-31 | 2014-08-15 | 2011 | NSA | Major Construction | CL | CLASSIFIED LOCATION | Classified Location | 22573 | Classified Location | 2012-07-01 | 2012-07-30 | PAE | 200 | 200 | 2012-08-15 | 2012-09-15 | 2012-08-30 | 2012-08-30 | 100
2014-07-31 | 2014-08-15 | 2011 | NSA | Major Construction | MD | MARYLAND | NSAW | 17866 | North Campus Electrical Utility Plant (NCEUP) | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | 125900 | 132128 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-01-16 | 98 | 50100 | Mountainview | NSA/Colorado | The project was recently awarded. Pending for the Notice to Proceed (NTP).
2014-07-31 | 2014-08-15 | 2011 | NSA | Major Construction | GA | GEORGIA | BackHall Campus/Sweet Tea Annex | 20489 | MOD II | 2011-12-23 | 2012-04-13 | Brantley Co. | 7657 | 8867 | 2012-05-30 | 2014-03-03 | 2014-01-30 | 2014-04-28 | 100
2014-07-31 | 2014-08-15 | 2011 | NSA | Major Construction | GA | GEORGIA | BackHall Campus/Sweet Tea Annex | 20489 | MOD II (Phase 2) | 2013-10-07 | 2013-11-20 | Brantley Co. | 2620 | 2657 | 2013-11-26 | 2014-09-30 | 2014-02-28 | 2014-08-31 | 98
2014-07-31 | 2014-08-15 | 2012 | NSA | Major Construction | GA | GEORGIA | Whitelaw | 23994 | Whitelaw Wedge | 2012-04-26 | 2012-06-18 | JAAAT | 15315 | 16526 | 2012-07-18 | 2014-07-09 | 2014-01-30 | 2014-10-23 | 90
2014-07-31 | 2014-08-15 | 2012 | NSAC | Major Construction | CO | COLORADO | ADFC | 23051 | Mountainview | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | 116975 | 123390 | 2012-11-02 | 2015-07-22 | 2015-05-03 | 2015-05-23 | 69
2014-07-31 | 2014-08-15 | 2012 | NSAC | Major Construction | CO | COLORADO | ADFC | 23051 | Mountainview | 2012-02-14 | 2013-09-29 | Xcel Power Feed | 5621 | 5621 | 2013-10-13 |  | 2014-02-14 | 2014-04-14 | 100
2014-07-31 | 2014-08-15 | 2012 | NSA | Major Construction | MD | MARYLAND | NSAW | 24649 | High Performance Computing Center 2 | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | 564689 | 587990 | 2013-03-12 | 2015-09-30 | 2015-09-16 | 2015-09-30 | 35
2014-07-31 | 2014-08-15 | 2013 | NSA | Major Construction | MD | MARYLAND | NSAW | 26170 | East Campus Building 1 | 2013-03-02 | 2013-09-23 | Walsh Federal, LLC | 91866 | 92192 | 2013-10-24 | 2016-01-05 | 2015-10-16 | 2015-10-16 | 6
2014-07-31 | 2014-08-15 | 2013 | NSA | Major Construction | UT | UTAH | Camp Williams | 21078 | Bumblehive / IC CNCI Data Center 1 | 2009-12-18 | 2010-09-24 | Balfour Beatty/DPR/Big-D, A Joint Venture (BDB) | 1201 | 1091 | 2010-11-08 | 2013-12-31 | 2013-12-31 | 2014-05-31 | 99 |  |  |  | The Utah Data Center Project is a fully authorized project in the amount of $1,529,500,000.00 which is incrementally funded over the following FY's: FY09- $109,500,000 FY10-$600,000,000 FY11-$397.562,000 FY12-$246,401,000 FY13-$176,037,000 The United States Army Corps of Engineers (USACE) is the construction agent for the NSA. The major contract for the project which is to design and construct the data center was awarded to Balfour Beatty/DPR/Big-D, A Joint Venture (BDB) in the amount of $1,198,950,000. There have been several contracts that have supplemented and supported the main construction effort for the UDC project which include, but are not limited to, the following: - Early Earthwork - $49,422,999 - Substation - $23,269,749 - Military Installation Development Authority (MIDA) - $70,000,000 - USACE Supervision & Administration/Supervision, Inspection & Overhead (S&A/SIOH) - $77,037,086 Note: The exact current obligation amount is $837,927,788 Original Contract Amount: $1,201,369,992
2014-07-31 | 2014-08-26 | 2012 | NGA | Military Construction | MO | MISSOURI | ARNOLD | NGA021 | Data Ctr West #1 Power & Cooling Upgrade | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors | 8202 | 10436 | 2012-08-06 | 2014-01-21 | 2013-08-06 | 2014-06-06 | 99 | 1975 |  |  | from NGA013
2014-07-31 | 2014-08-26 | 2012 | NGA | Military Construction | VA | VIRGINIA | FORT BELVOIR | NGA013 | Technology Center Third Floor Fit-out | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty - NCE, A Joint Venture | 32387 | 39495 | 2012-11-02 | 2014-05-30 | 2014-01-02 | 2014-12-30 | 94 | 1975 |  |  | to NGA021
2014-07-31 | 2014-08-26 | 2007 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR |  | Infrastructure Increments 1-3; NGA HQ's |  |  | Various |  |  |  | 2011-09-15 | 2013-06-15 | 2013-09-30 | 99 |  |  |  | Const - Water Tank & CDC Infrastructure contract continues
2014-07-31 | 2014-08-26 | 2008 | NGA | Military Construction - BRAC | VA | VIRGINIA | FORT BELVOIR | 65416 | NGA Headquarters,SCIF, ALL PHASES | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty - NCE, A Joint Venture | 1181439 | 1398710 | 2007-09-06 | 2011-04-19 | 2011-12-22 | 2013-12-31 | 93 |  |  |  | Closeout efforts ongoing
Formulas:
Occupancy Date = [Occupancy Date, row above]
Note on X870: E1COXRGX:
Note on T1738: WALDEN, DAVID R GB USAF AFCEC USAFE UK/CFEK: Ground work sub-contractor withdrew from contract; therefore, no futher progress to date: 6 Jun 14.

## Planning and Design
Data as of Date | Submission Date | Fiscal Year | Component | Type of funds | Use of funds | Appropriated Amount | Currently Obligated Amount | Notes/remarks
2014-07-31 | 2014-08-04 | 2010 | Navy-MC active | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs | 220194 | 220063 | Design funds in the amount of $4.0M withdrawn in April/August/December 2010, for transfer to the Federal Highway Administration to support one Camp Lejeune and two Guam Defense Access Road Improvement projects, factored into the Current Obligated Amount.
2014-07-31 | 2014-08-04 | 2011 | Navy-MC active | General P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 136314 | 135997
2014-07-31 | 2014-08-04 | 2012 | Navy-MC active | General P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 83944 | 83683
2014-07-31 | 2014-08-04 | 2013 | Navy-MC active | General P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 96890 | 69822
2014-07-31 | 2014-08-04 | 2014 | Navy-MC active | General P&D | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638 | 28445 | Allocation reduced January 2014 i/a/o $9,192k in accordance with P.L. 113-76
2014-07-31 | 2014-08-04 | 2010 | Navy-MC active | MFH P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs | 2720 | 2676
2014-07-31 | 2014-08-04 | 2011 | Navy-MC active | MFH P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 3193 | 2974
2014-07-31 | 2014-08-04 | 2012 | Navy-MC active | MFH P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 3166 | 2943
2014-07-31 | 2014-08-04 | 2013 | Navy-MC active | MFH P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 4065 | 1083
2014-07-31 | 2014-08-04 | 2014 | Navy-MC active | MFH P&D | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 4438 | 0
2014-07-31 | 2014-08-04 | 2010 | Navy-MC res | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs | 2951 | 2951
2014-07-31 | 2014-08-04 | 2011 | Navy-MC res | General P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1854 | 1854
2014-07-31 | 2014-08-04 | 2012 | Navy-MC res | General P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478 | 2149
2014-07-31 | 2014-08-04 | 2013 | Navy-MC res | General P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995 | 1724
2014-07-31 | 2014-08-04 | 2014 | Navy-MC res | General P&D | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2540 | 0
2014-07-31 | 2014-08-04 | 2006 | Air Force | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; GWOT Supplemental | 65284 | 29122
2014-07-31 | 2014-08-04 | 2006 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27783 | 25506
2014-07-31 | 2014-08-04 | 2006 | Air Force Reserve | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5290 | 4749
2014-07-31 | 2014-08-04 | 2006 | Air National Guard | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006 | 28021
2014-07-31 | 2014-08-04 | 2007 | Air Force | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements ; GWOT Supplemental | 76246 | 75120
2014-07-31 | 2014-08-04 | 2007 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12231
2014-07-31 | 2014-08-04 | 2007 | Air Force Reserve | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109 | 4707
2014-07-31 | 2014-08-04 | 2007 | Air National Guard | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050 | 19043
2014-07-31 | 2014-08-04 | 2008 | Air Force | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; GWOT Supplemental | 51202 | 49125
2014-07-31 | 2014-08-04 | 2008 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12162
2014-07-31 | 2014-08-04 | 2008 | Air Force Reserve | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300 | 4840
2014-07-31 | 2014-08-04 | 2008 | Air National Guard | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721 | 10619
2014-07-31 | 2014-08-04 | 2009 | Air Force | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105506 | 103286
2014-07-31 | 2014-08-04 | 2009 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703 | 7594
2014-07-31 | 2014-08-04 | 2009 | Air Force Reserve | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165 | 5766
2014-07-31 | 2014-08-04 | 2009 | Air National Guard | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056 | 19056
2014-07-31 | 2014-08-04 | 2010 | Air Force | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 112785 | 107360
2014-07-31 | 2014-08-04 | 2010 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302 | 1423
2014-07-31 | 2014-08-04 | 2010 | Air Force Reserve | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 3869 | 2572
2014-07-31 | 2014-08-04 | 2010 | Air National Guard | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670 | 19201
2014-07-31 | 2014-08-04 | 2011 | Air Force | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 66525 | 60201
2014-07-31 | 2014-08-04 | 2011 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153 | 3922
2014-07-31 | 2014-08-04 | 2011 | Air Force Reserve | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1650 | 1518
2014-07-31 | 2014-08-04 | 2011 | Air National Guard | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9196 | 8606
2014-07-31 | 2014-08-04 | 2012 | Air Force | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 78413 | 66509
2014-07-31 | 2014-08-04 | 2012 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056 | 4000
2014-07-31 | 2014-08-04 | 2012 | Air Force Reserve | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200 | 1846
2014-07-31 | 2014-08-04 | 2012 | Air National Guard | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225 | 11632
2014-07-31 | 2014-08-04 | 2013 | Air Force | General P&D | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 410 | 368
2014-07-31 | 2014-08-04 | 2013 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3952 | 0
2014-07-31 | 2014-08-04 | 2013 | Air Force Reserve | General P&D | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875 | 148
2014-07-31 | 2014-08-04 | 2013 | Air National Guard | General P&D | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3995 | 2926
2014-07-31 | 2014-08-04 | 2014 | Air Force | General P&D | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314 | 6610
2014-07-31 | 2014-08-04 | 2014 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267 | 0
2014-07-31 | 2014-08-04 | 2014 | Air Force Reserve | General P&D | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229 | 0
2014-07-31 | 2014-08-04 | 2014 | Air National Guard | General P&D | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400 | 149
2014-07-31 | 2014-08-05 | 2010 | WHS | General P&D | Complete design or RFP development of FY11 MILCON projects | 3575 | 3575
2014-07-31 | 2014-08-05 | 2011 | WHS | General P&D | Complete design or RFP development of FY12 MILCON projects | 6257 | 0
2014-07-31 | 2014-08-05 | 2012 | WHS | General P&D | Complete design or RFP development of FY13 MILCON projects
2014-07-31 | 2014-08-05 | 2007 | MDA | General P&D | Design MDA 609 - Aegis-BMD Facility Expansion, Dahlgren, VA. | 770 | 770 | Completed RFP for design-build (D-B) project.
2014-07-31 | 2014-08-05 | 2009 | MDA | General P&D | Design MDA FY10-FY13 MILCON Projects | 14848 | 14839 | Supports design of the Aegis Ashore Test Complex, East Coast Comm site, Aegis Ashore Romania site, UEWR Modifications at Clear AFS, AK and completes RFP for D-B Von Braun Complex, Phase IV.
2014-07-31 | 2014-08-05 | 2010 | MDA | General P&D | Design MDA FY12-13 MILCON Projects | 7698 | 7698 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, UEWR Modifications at Clear AFS, AK, and EUCOM Radar site. Includes $5,700,000 reprogrammed from MILCON.
2014-07-31 | 2014-08-05 | 2011 | MDA | General P&D | Design MDA FY15-16 MILCON Projects | 1186 | 0 | Funds tranferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2014-07-31 | 2014-08-05 | 2012 | MDA | General P&D | Design MDA FY13-14 MILCON Projects | 8368 | 8368 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2014-07-31 | 2014-08-05 | 2013 | MDA | General P&D | Design MDA FY13-14 MILCON Projects | 4191 | 4191 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-07-31 | 2014-08-05 | 2014 | MDA | General P&D | Design MDA FY14-16 MILCON Projects | 10891 | 7816 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Planning and Design (P&D) | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 60944 | 60943 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Planning and Design (P&D) | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 47210 | 47207 | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Planning and Design (P&D) | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25604 | 25602 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Planning and Design (P&D) | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191 | 15375 | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Planning and Design (P&D) | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17 | 2407 | 1747 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Planning and Design (P&D) | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25748 | 2064 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Planning and Design (P&D) | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930 | 2575 | PL 113-76 P&D Recission
2014-07-31 | 2014-08-05 | 2008 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 3400 | 3348 | RCI-Residential Communities Initiative
2014-07-31 | 2014-08-05 | 2008 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 08/09/ 10/11/12 MILCON projects | 1891 | 1891
2014-07-31 | 2014-08-05 | 2009 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 1830 | 1830
2014-07-31 | 2014-08-05 | 2009 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 5000 | 5000
2014-07-31 | 2014-08-05 | 2009 | DoDEA | P&D-FAD from OSD May 2010 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 7000 | 7000
2014-07-31 | 2014-08-05 | 2010 | DoDEA | P&D-FAD from OSD Jan 2010 | Design efforts for FY 10/11/ 12/13 MILCON projects | 8830 | 8830 | Reflects Sequestration Reduction
2014-07-31 | 2014-08-05 | 2011 | DoDEA | P&D-FAD from OSD 24 Feb 2011 | Design efforts for FY 11/12/ 13 MILCON projects | 7840 | 7840
2014-07-31 | 2014-08-05 | 2011 | DoDEA | P&D-FAD from ODS 2 June 2011 | Design efforts for FY 11/12/13 MILCON projects | 70841 | 70826 | Reflects Sequestration Reduction
2014-07-31 | 2014-08-05 | 2012 | DoDEA | P&D-FAD from OSD 6 Jan 2012 | Design efforts for FY 12/13 MILCON projects | 64551 | 64526 | Reflects Sequestration Reduction
2014-07-31 | 2014-08-05 | 2013 | DoDEA | P&D-FAD from OSD 6 Jun 2013 | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 56140 | Reflects Sequestration Reduction
2014-07-31 | 2014-08-05 | 2014 | DoDEA | P&D-FAD from OSD 19 Feb 2014 | Design efforts for FY 14/15/16/17 MILCON projects | 75905 | 0
2014-07-31 | 2014-08-05 | 2012 | DFAS | MILCON | Investigation & Design | 1992 | 748.4
2014-07-31 | 2014-08-05 | 2009 | DLA | General P&D | Design efforts for FY 10/11/12 MILCON projects | 4338 | 4338 | Expired
2014-07-31 | 2014-08-05 | 2010 | DLA | General P&D | Design efforts for FY 11/12/13 MILCON projects | 12548 | 12537 | OSD provided additional P&D 15 Jun 11
2014-07-31 | 2014-08-05 | 2011 | DLA | General P&D | Design efforts for FY 12/13/14 MILCON projects | 36093 | 36093 | OSD provided additional P&D 23 May 13
2014-07-31 | 2014-08-05 | 2012 | DLA | General P&D | Design efforts for FY 13/14/15 MILCON projects | 34331 | 34331 | OSD provided additional P&D 23 May 13
2014-07-31 | 2014-08-05 | 2013 | DLA | General P&D | Design efforts for FY 14/15/16 MILCON projects | 18308 | 10291 | OSD provided additional P&D 31 Jan 14
2014-07-31 | 2014-08-05 | 2014 | DLA | General P&D | Design efforts for FY 15/16/17 MILCON projects | 0 | 0 | Initial load by OSD 19 Feb 14
2014-07-31 | 2014-08-06 | 2010 | SOCOM | General P&D | MILCON | 4344 | 3937 | As of 15Jul2014
2014-07-31 | 2014-08-06 | 2011 | SOCOM | General P&D | MILCON | 26469 | 24759 | As of 15Jul2014
2014-07-31 | 2014-08-06 | 2012 | SOCOM | General P&D | MILCON | 30308 | 26604 | As of 15Jul2014
2014-07-31 | 2014-08-06 | 2013 | SOCOM | General P&D | MILCON | 25454 | 11061 | As of 15Jul2014
2014-07-31 | 2014-08-06 | 2014 | SOCOM | General P&D | MILCON | 36866 | 0 | As of 15Jul2014
2014-07-31 | 2014-08-13 | 2012 | DIA | General P&D | P&D for DIAC parking garage replacement | 1498 | 461 | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $461K (CORRECTED AMOUNT) obligated as CAT I. NAVFAC awarded A/E contract 7 June 2013. 65% design complete and review comments submitted.
2014-07-31 | 2014-08-13 | 2012 | DIA | General P&D | P&D for DIAC chilled water project for data center | 125 | 0 | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded 30 Jan 2013. 35% design completed.
2014-07-31 | 2014-08-13 | 2012 | DIA | General P&D | P&D for DIAC cooling tower for data center | 105 | 0 | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded 30 Jan 2013. 35% design completed.
2014-07-31 | 2014-08-13 | 2012 | DIA | General P&D | P&D for UPS for data center installation | 120 | 120 | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded 30 Jan 2013. 100% design completed.
2014-07-31 | 2014-08-13 | 2012 | DIA | General P&D | P&D for construction of JUIAF RDF | 1195 | 1195 | $1,195 obligated as CAT I acceptance. Design complete.
2014-07-31 | 2014-08-14 | 2009 | Army Active | MCA-P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 218284
2014-07-31 | 2014-08-14 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000
2014-07-31 | 2014-08-14 | 2010 | Army Active | MCA-P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250429
2014-07-31 | 2014-08-14 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000
2014-07-31 | 2014-08-14 | 2011 | Army Active | MCA-P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 308676 | 262614
2014-07-31 | 2014-08-14 | 2011 | Army Active | Host Nation Support | $29,944 Appropriated + $13,000 ATR | 42944 | 42932
2014-07-31 | 2014-08-14 | 2012 | Army Active | MCA-P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 179961
2014-07-31 | 2014-08-14 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR | 27000 | 27289
2014-07-31 | 2014-08-14 | 2013 | Army Active | MCA-P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46112 | 44293
2014-07-31 | 2014-08-14 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954 | 33627
2014-07-31 | 2014-08-14 | 2014 | Army Active | MCA-P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575 | 13056
2014-07-31 | 2014-08-14 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33000 | 20233
2014-07-31 | 2014-08-15 | 2010 | NSA | General P&D | Generators 10 & 11 | 440 | 440 | MIPR 12-045 from MHS to AFCEC, $240K moved from Power & Cooling

## Minor Const & Family Housing
Data As Of Date | Submission Date | Fiscal Year | Component | Type of funds | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Notes/remarks
2014-07-31 | 2014-08-05 | 2009 | MDA | UMC | Used for accomplishing urgent unforeseen construction projects in FY12/13 | 3317 | 3117 | Obligated funds support the EUCOM Radar Site. EUCOM work which resumed on 6 May 2013. Additional obligation of funds supports the Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping project at Fort Greely, AK
2014-07-31 | 2014-08-05 | 2010 | MDA | UMC | Used for accomplishing urgent unforeseen construction projects in FY13/14 | 2243 | 2009 | Supports the R&C Piping project at Fort Greely, AK and the Storage Facility, Meck Island. $1.186M transferred to DHA in April 2014 for swap of FY11 P&D funds.
2014-07-31 | 2014-08-05 | 2014 | MDA | UMC | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000 | 0
2014-07-31 | 2014-08-05 | 2009 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 21880 | 21880 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2010 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 36905 | 32124 | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2011 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 14215 | 11252 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2012 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 14149 | 10842 | PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2013 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 14562 | 9431 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-07-31 | 2014-08-05 | 2014 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 12240 | 0
2014-07-31 | 2014-08-05 | 2008 | DoDEA | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Construction for projects < $2.M | 666 | 0
2014-07-31 | 2014-08-05 | 2009 | DoDEA | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Construction for projects < $2.M | 382 | 4 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2014-07-31 | 2014-08-05 | 2010 | DoDEA | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Construction for projects < $2.M | 6275 | 6275 | Reflects Sequestration Reduction
2014-07-31 | 2014-08-05 | 2011 | DoDEA | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Construction for projects < $2.M | 3217 | 3217
2014-07-31 | 2014-08-05 | 2013 | DoDEA | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Construction for projects < $2.M | 3771 | 0 | Reflects Sequestration Reduction
2014-07-31 | 2014-08-05 | 2014 | DoDEA | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Construction for projects < $2.M | 5409 | 0
2014-07-31 | 2014-08-08 | 2010 | DISA | O&M | Replace raised floor and clean and seal, bldg 2340 |  | 903.6 | 97% complete
2014-07-31 | 2014-08-14 | 2009 | Active Army | UMMCA | Unspecified Minor Construction for Projects < $2.M | 28750 | 28232
2014-07-31 | 2014-08-14 | 2010 | Active Army | UMMCA | Unspecified Minor Construction for Projects < $2.M | 31250 | 30964
2014-07-31 | 2014-08-14 | 2010 | Active Army | Overseas Contingency Operations | Unspecified Minor Construction for Projects < $2.M | 60100 | 14055
2014-07-31 | 2014-08-14 | 2011 | Active Army | UMMCA | Unspecified Minor Construction for Projects < $2.M | 28704 | 26390
2014-07-31 | 2014-08-14 | 2011 | Active Army | Overseas Contingency Operations | Unspecified Minor Construction for Projects < $2.M | 78330 | 1274
2014-07-31 | 2014-08-14 | 2012 | Active Army | UMMCA | Unspecified Minor Construction for Projects < $2.M | 20000 | 19044
2014-07-31 | 2014-08-14 | 2013 | Active Army | UMMCA | Unspecified Minor Construction for Projects < $2.M | 24967 | 20490
2014-07-31 | 2014-08-14 | 2014 | Active Army | UMMCA | Unspecified Minor Construction for Projects < $2.M | 25000 | 9774
2014-07-31 | 2014-08-14 | 2009 | Active Army | AFHC | Army Family Housing Construction for Projects | 576 | 576
2014-07-31 | 2014-08-14 | 2010 | Active Army | AFHC | Army Family Housing Construction for Projects | 3936 | 3935
2014-07-31 | 2014-08-14 | 2011 | Active Army | AFHC | Army Family Housing Construction for Projects | 2036 | 1989
2014-07-31 | 2014-08-14 | 2012 | Active Army | AFHC | Army Family Housing Construction for Projects | 7897 | 5005
2014-07-31 | 2014-08-14 | 2013 | Active Army | AFHC | Army Family Housing Construction for Projects | 4635 | 58
2014-07-31 | 2014-08-14 | 2014 | Active Army | AFHC | Army Family Housing Construction for Projects | 4408