## PROJECTS
Data as of Date | Fiscal Year | Component | Construction Project Type | State | Country | Project Number | Project Title | Parent Project Number [Initial Appropriation] | Solicitation Date | Award Date | Prime Contract Recipient (Company Name) | Prime Contract Number | Original Contract Amount ($000) | Current Contract Obligation ($000) | Start Date | Placed-In-Service Date | Original Completion Date | Current Completion Date | Percent Complete | Diverted Funds Amount ($000) | Diverted Funds Recipient Project | Remarks
2015-07-31 | 2008 | Air Force Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | VLSB083007 | Base Infrastructure |  | 2008-07-31 | 2008-09-29 | Prime Ktr Golf Course CNS | N6945008C2846 | 2771.874 | 2827.76 | 2008-09-29 | 2010-03-08 | 2009-09-29 | 2016-06-02 | 0.99
[9 empty] | 2011-04-11 | 2011-06-10 | J2 Engineering | N6945008D1782 | 3446.432 | 5339.2705 | 2011-07-10 | 2010-03-08 | 2012-11-09
[9 empty] | 2015-05-24 | 2015-07-23 | Bell & Carrington | W912HN15P0034 | 7.32 | 7.32 | 2015-08-23 | 2010-03-08 | 2017-08-22
[9 empty] | 2015-05-29 | 2015-07-28 | Property Solutions, LLC | W912HN15P0036 | 14.35 | 14.35 | 2015-08-28 | 2010-03-08 | 2017-02-18
2015-07-31 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALDA053001B | Multi-Aircraft Maintenance Hanger |  | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 15238.069 | 17873.5099 | 2010-08-23 |  | 2012-08-22 | 2015-10-31 | 0.99
2015-07-31 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALUA073008A | Facility Replacements |  | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244.838 | 31385.3491 | 2010-08-23 |  | 2012-08-22 | 2015-10-31 | 0.99
2015-07-31 | 2008 | Air Force Active | Military Family Housing |  | GERMANY | TYFR084034 | Replace Family Housing, Ph E |  | 2008-08-04 | 2008-09-18 | LBB Kaiserslautern EBC | W912GB-08-C-0001 | 45686.7224 | 46119.8599 | 2009-08-28 | 2011-12-15 | 2010-12-01 | 2014-12-18 | 1
2015-07-31 | 2008 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR084014 | Improve Family Housing, Ph E |  | 2013-01-25 | 2013-05-17 | MICKAN | C07-1003 | 4638.8202 | 4458.1334 | 2013-07-08 | 2014-12-18 | 2014-06-23 | 2015-03-16 | 1
2015-07-31 | 2008 | Air Force Active | Military Family Housing Improvement |  | TURKEY | LJYC084001 | Improve Family Housing 515 Units |  | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970.0225 | 42315.6545 | 2009-12-04 |  | 2012-10-19 | 2015-07-19 | 0.37
2015-07-31 | 2009 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R1 | BMT Recruit Dormitory |  | 2009-07-09 | 2009-09-17 | COE-BalfourBeattySutterfieldPontikes JV (LB-Main Facilities) | W9126G-09-C-0054 | 46437.194 | 54453.5783 | 2009-10-06 | 2012-11-21 | 2011-10-06 | 2014-12-10 | 1
[9 empty] | 2010-08-01 | 2011-01-28 | COE-JSR Inc. (SB-Exterior Facilities) | W9126G-09-C-0000 | 6037.485 | 6396.8813 | 2011-02-28 | 2012-11-21 | 2012-02-13
[9 empty] | 2012-05-20 | 2012-11-16 | CE-DawsonAlamo JV, LLC (SABER-Comm Cabinets) Pop w/in LB | FA304710D00120046 | 17.2782 | 17.2782 | 2012-12-16 | 2012-11-21 | 2012-12-16
[9 empty] | 2013-02-13 | 2013-08-12 | CE-JSR Inc. (SABER-MTI Offices+mod $6,392.52) PoP w/in SB | FA304710D00130003 | 236.2072 | 236.2072 | 2013-09-12 | 2012-11-21 | 2013-09-12
[9 empty] | 2013-03-18 | 2013-09-14 | COE-JSR Inc. (JOC-Stair Tread-Landing Retrofit) | W9126G12D00180017 | 216.6837 | 216.6837 | 2013-10-14 | 2012-11-21 | 2014-06-21
[9 empty] | 2013-03-31 | 2013-09-27 | COE-JSR Inc. (SB-Gary Rd Finishes/FZ Fence Relocation) | W9126G13C00980004 | 86.693 | 86.693 | 2013-10-27 | 2012-11-21 | 2014-05-15
[9 empty] | 2013-04-18 | 2013-10-15 | COE-JSR Inc. (JOC-Running Track/Drill Pad Light) | W9126G12D00180019 | 98.6814 | 98.6814 | 2013-11-15 | 2012-11-21 | 2014-07-11
[9 empty] | 2013-06-18 | 2013-12-15 | COE-JSR Inc. (Stair Handrails Retrofit) PoP w/in SB | W9126G12D00180025 | 79.7535 | 79.7535 | 2014-01-15 | 2012-11-21 | 2014-01-15
2015-07-31 | 2009 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS093002 | CNS Addition To Child Development Center (Cdc) B8210 |  | 2009-07-14 | 2009-08-31 | MAPCO, Inc. | W9126G09D00340002 | 5913.251 | 6604.8908 | 2009-10-15 | 2012-08-20 | 2011-02-27 | 2014-12-11 | 1
[9 empty] | 2013-04-16 | 2013-06-15 | JSR Inc. | FA301612D00050008 | 366.5141 | 375.4125 | 2013-07-15 | 2012-08-20 | 2014-01-26
2015-07-31 | 2009 | Air Force Active | Unspecified Minor Military Construction |  | TURKEY | AKNR041053 | CNS Replace Asf Admin Bldg 2621 |  | 2011-02-22 | 2011-09-23 | MATOC Contractor | W912GB09D00690007 | 1367.06 | 1367.06 | 2012-02-15 | 2015-03-26 | 2013-02-09 | 2015-05-12 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 28919.5195 | 2011-06-17 |  | 2015-01-27 | 2016-12-22 | 0.77
2015-07-31 | 2010 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT033003 | Consol Communications Facility |  | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248.94 | 11773.483 | 2010-10-13 | 2014-09-12 | 2013-10-12 | 2015-09-01 | 0.95
2015-07-31 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA061726 | F-35 POL Ops Facility |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | W9127810C0074 | 4309 | 4446.688 | 2010-10-27 | 2013-09-30 | 2011-10-27 | 2014-10-31 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073902 | F-35 Hydrant Refueling System Phase 1 |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | W9127810C0074 | 9452 | 10701.3416 | 2010-07-15 | 2013-10-30 | 2011-07-15 | 2014-10-31 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073904 | F-35 JP-8 Flightline Fillstands |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | W9127810C0074 | 3217 | 3422.26 | 2010-10-07 | 2013-10-30 | 2011-10-07 | 2014-10-31 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073905 | F-35 JP-8 West Side Bulk Fuel Tank Upgrades |  | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | W9127810C0074 | 1464 | 1534.199 | 2010-06-15 | 2013-10-30 | 2011-06-15 | 2014-10-31 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | NVZR033702 | Consolidated Communications Facility |  | 2010-05-19 | 2010-07-07 | Carothers Construction | W9127807D00260003 | 16517.735 | 16824.4072 | 2010-08-11 | 2013-12-13 | 2013-07-26 | 2014-12-31 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD063003 | Ground Control Tower |  | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | N6274209D1186HC08 | 7379.329 | 7423.376 | 2012-09-07 |  | 2014-03-01 | 2015-08-14 | 0.85
2015-07-31 | 2010 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF063009 | Replace Munitions Storage Area |  | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464.83 | 10753.2604 | 2011-06-23 |  | 2013-05-13 | 2015-08-09 | 0.91
2015-07-31 | 2010 | Air Force Active | Major Military Construction | MONTANA | UNITED STATES | NZAS003000A | Upgrade Weapons Storage Area |  | 2012-04-23 | 2012-11-28 | RSCI | W912DW13C0013 | 9474.72 | 9462.564 | 2013-01-07 | 2015-07-31 | 2014-11-28 | 2015-08-28 | 0.94
2015-07-31 | 2010 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | XTLF033303 | Control Tower |  | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849.633 | 9592.0332 | 2010-10-05 |  | 2012-02-12 | 2015-08-24 | 0.97
2015-07-31 | 2010 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility |  | 2009-12-10 | 2010-02-11 | COE LB Lyda Swinerton (Whole Facility) | W9126G10C0017 | 23483.61 | 25785.2822 | 2010-05-05 | 2012-10-31 | 2011-12-26 | 2014-11-26 | 1
[9 empty] | 2010-04-12 | 2010-06-11 | COE SB JSR Inc. (Telecomm Ductbank) | W9126G10C0072 | 1409.452 | 1601.6059 | 2010-07-11 | 2012-10-31 | 2011-07-11
[9 empty] | 2014-07-31 | 2014-09-29 | COE JOC Gideon Cntrg (Handrails/Screening Retrofit) | W9126G14D00570016 | 60.931 | 60.931 | 2014-10-29 | 2012-10-31 | 2014-10-29
2015-07-31 | 2010 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | MUHJ053008 | West & Lasalle Gates Force Protection/Access |  | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185.824 | 8498.0821 | 2010-08-04 | 2013-07-19 | 2012-01-26 | 2015-09-03 | 0.99
[9 empty] | 2014-07-01 | 2014-09-29 | Homeland Contracting Corporation | FA480012D0004 | 231.491 | 231.491 | 2014-10-29 | 2013-07-19 | 2015-08-25
2015-07-31 | 2010 | Air Force Active | Major Military Construction |  | GERMANY | TYFR053037 | Aerospace Ground Equipment Maintenance Complex |  | 2012-01-27 | 2012-06-15 | D & b Bau GmbH, Neustadt | W912GB-09-C0022 | 5745.6986 | 5997.0712 | 2012-06-15 |  | 2013-07-06 | 2015-10-15 | 0.99
2015-07-31 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006A | Blatchford-Preston Complex Ph II |  | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | W912ER11C0001 | 35758.85 | 37334.8501 | 2010-12-16 | 2014-12-30 | 2013-02-03 | 2014-12-30 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA103001 | Construct Network Control Center |  | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | W912ER12C0028 | 2579.93 | 3160.1562 | 2012-07-05 |  | 2013-09-08 | 2015-09-23 | 0.76
2015-07-31 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA107000 | Coalition Compound Billeting |  | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272.835 | 44788.3605 | 2012-04-16 |  | 2014-04-06 | 2015-12-04 | 0.92
2015-07-31 | 2010 | Air Force Active | Major Military Construction |  | TURKEY | LJYC003006 | Consolidated Community Center |  | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | W912GB09D00690003 | 7880.644 | 8179.6972 | 2010-04-26 | 2015-07-27 | 2011-10-18 | 2015-07-27 | 1
2015-07-31 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100031 | Construct Maintenance Operations Center And Command Post |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671.642 | 1986.1406 | 2011-06-03 |  | 2012-02-28 | 2015-09-30 | 0.96
2015-07-31 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100120 | Construct SatCom Facility |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136.701 | 1184.0301 | 2011-06-03 |  | 2012-02-28 | 2015-09-30 | 0.96
2015-07-31 | 2011 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083008 | Repair Central Heat And Power Plant Boiler |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 30243.0655 | 2011-06-17 |  | 2015-01-27 | 2016-12-22 | 0.77
2015-07-31 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV063501 | AMARG Hangar |  | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282.136 | 23526.207 | 2011-09-07 |  | 2013-08-27 | 2015-08-07 | 0.95
2015-07-31 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV113002 | HC-130J Aerial Cargo Facility |  | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223 | 7534.524 | 2011-11-09 | 2013-09-13 | 2013-05-02 | 2015-10-31 | 0.95 | 2000 | YWHG111005;
2015-07-31 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093000 | F-35 Academic Training Center |  | 2012-04-18 | 2012-08-30 | Archer Western Contractors | W912PL12C0017 | 43347.122 | 48331.2719 | 2012-11-05 | 2014-12-22 | 2014-04-08 | 2015-05-29 | 1 | 2406.08 | PRQE145121;SGBP100904C;
[9 empty] | 2014-04-30 | 2014-09-27 | KWR Construction, Inc | W912PL14D00300002 | 587.608 | 587.608 | 2014-10-27 | 2014-12-22 | 2015-01-25
2015-07-31 | 2011 | Air Force Active | Major Military Construction | COLORADO | UNITED STATES | XQPZ084017 | Const Center For Character & Leadership Development |  | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995.5 | 25471.49 | 2013-01-14 |  | 2014-09-29 | 2015-09-30 | 0.94
2015-07-31 | 2011 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT113001 | C-5M/C-17 Maintenance Training Facility, Ph 2 |  | 2011-03-09 | 2011-08-02 | Asset Group, Incorporated, Oklahoma City, Oklahoma | W912BU11C0024 | 2951.817 | 2950.318 | 2011-08-11 | 2014-05-12 | 2012-08-10 | 2014-10-31 | 1
2015-07-31 | 2011 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | SXHT053001 | Air Force Technical Applications Center |  | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231.0449 | 147760.0719 | 2011-07-06 | 2014-03-03 | 2015-12-02 | 2016-03-01 | 0.98
[9 empty] | 2013-08-07 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99.768 | 99.768 | 2014-03-03 | 2014-03-03 | 2014-08-30
2015-07-31 | 2011 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC113102 | UAS Airfield Fire/Crash Rescue Station |  | 2010-12-10 | 2011-06-29 | Jaynes Corporation | W912PL11C0004 | 7345.225 | 7478.704 | 2011-09-02 | 2014-07-14 | 2013-02-28 | 2014-11-06 | 1
2015-07-31 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R3 | Recruit Dormitories Phase 3 |  | 2010-12-06 | 2011-09-20 | LB SutherfielfPontikes, LLC-Main Facility Construction | W9126G11C0024 | 45885 | 46365.6429 | 2011-11-01 | 2015-06-06 | 2013-10-31 | 2016-12-15 | 0.9 | 4894 | KRSM103011;
[9 empty] | 2011-05-12 | 2011-11-08 | LB Koonz Brown & Root (DCF2 Ktr)-Free Zone Fence | W9126G11C0027 | 95.464 | 95.464 | 2011-12-08 | 2015-06-06 | 2011-12-08
[9 empty] | 2011-12-01 | 2012-05-29 | AE RabaKistner Consultants-Sidewalk Survey $1865.12 | PNASA1205700 | 1.889 | 1.889 | 2012-06-29 | 2015-06-06 | 2012-06-29
[9 empty] | 2012-02-11 | 2012-08-09 | SB JSR Inc-Exterior Facilties & Grounds | W912BV11C0038 | 6886.921 | 7284.5293 | 2012-09-09 | 2015-06-06 | 2014-01-22
[9 empty] | 2012-04-22 | 2012-10-19 | SB FPI, LLC/JSR Inc-Refencing | W9126G11C0009 | 175.3584 | 175.3584 | 2012-11-19 | 2015-06-06 | 2012-11-19
[9 empty] | 2012-12-05 | 2013-06-03 | SB FPI, LLC/JSR Inc-DCF2s Gary Rd portion 2/3 | W9126G13C0098 | 91.85 | 91.85 | 2013-07-03 | 2015-06-06 | 2013-07-03
[9 empty] | 2013-12-27 | 2014-06-25 | SVS-Am Eagle Protective Svs Corp-Gate Monitor, OY2 | W9126G12C0017P0002 | 100.4666 | 100.4666 | 2014-07-25 | 2015-06-06 | 2014-07-25
[9 empty] | 2014-04-13 | 2014-10-10 | SB Red Cedar Enterprises Inc-Quadrangle Main 3/4 | W9126G14D00190007 | 3102.034 | 3102.034 | 2014-11-10 | 2015-06-06 | 2014-11-10
[9 empty] | 2014-05-14 | 2014-11-10 | AE Merrick & Company-Tittle 2 Svs $59,036x3 | W9126G08D00060053 | 177.1085 | 177.1085 | 2014-12-10 | 2015-06-06 | 2014-12-10
2015-07-31 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 |  | 2011-03-07 | 2011-07-08 | LB-KBR General Contract | W9126G11C0027 | 25985.138 | 27613.9869 | 2011-08-29 | 2015-03-15 | 2013-08-18 | 2015-08-30 | 0.98
[9 empty] | 2011-11-01 | 2012-02-29 | AEP Services Corp (Gate Monitor Svs 100K x 2 yrs | W9126G12C00170001 | 202.0082 | 202.0082 | 2012-03-29 | 2015-03-15 | 2012-03-29
[9 empty] | 2012-03-10 | 2012-07-08 | SB JSR Inc (Gary Rd Realign Pt 2of3) | W9126G13C0098 | 152.927 | 155.31 | 2012-08-08 | 2015-03-15 | 2012-08-08
[9 empty] | 2012-07-03 | 2012-10-31 | Merrick & Company (Tittle II Services) $59,036.40 | W9126G08D00060054 | 118.073 | 118.073 | 2012-11-30 | 2015-03-15 | 2012-11-30
[9 empty] | 2014-12-25 | 2015-04-24 | SB Gideon Contracting | W9126G14D00570019 | 54.5741 | 54.5741 | 2015-05-24 | 2015-03-15 | 2015-10-09
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | AFGHANISTAN | ATUH110101 | Consolidated Rigging Facility |  | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest, JV, LLC | W912ER11D00130002 | 8364.461 | 9345.0618 | 2011-08-10 | 2014-05-21 | 2012-09-08 | 2015-01-17 | 1
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | AFGHANISTAN | ATUH110103 | Medevac Ramp Expansion/ Fire Station |  | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest JV, LLC | W912ER11D00130002 | 9537.395 | 7863.428 | 2011-08-10 | 2014-05-21 | 2012-08-24 | 2015-01-17 | 1
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | AFGHANISTAN | ATUH110104 | Fighter Hangar |  | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest IV, LLC | W912ER11D00130002 | 8305.226 | 9188.2642 | 2011-08-10 | 2014-05-21 | 2012-08-24 | 2015-01-17 | 1
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR083001 | Deicing Fluid Storage & Dispensing Facility |  | 2012-05-10 | 2012-09-26 | Peter Gross GmbH | W912GB-10-C-0001A | 2140.702 | 2253.3657 | 2012-10-31 |  | 2013-05-19 | 2015-08-31 | 0.96 | 155 | KRSM103011;
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR123063 | C-130J Flight Simulator Facility |  | 2013-08-12 | 2013-11-13 | OBG Hochbau GmbH & Co. KG | W912GB10C0002 | 6163.5954 | 6561.8593 | 2013-11-27 | 2015-03-26 | 2014-11-06 | 2015-09-15 | 0.99
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFU083507R2 | Dormitory (128 Rm) |  | 2013-08-30 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | 16251.8956 | 16251.8956 | 2014-06-10 |  | 2015-07-15 | 2015-12-03 | 0.62
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | ITALY | ASHE083011 | Air Support Operations Squadron (ASOS) Facility |  | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N3319107D02110002 | 7174.1698 | 8608.1225 | 2011-12-15 |  | 2013-09-05 | 2015-07-31 | 0.84 | 1453 | KRSM103011;
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006B | Blatchford-Preston Complex, Phase III |  | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177.236 | 34672.9582 | 2012-03-26 |  | 2014-05-15 | 2016-01-29 | 0.45
[9 empty] | 2014-07-27 | 2015-01-23 | Federal Contracting, Inc. | W912ER15C0003 | 4899.425 | 4899.425 | 2015-02-18 |  | 2016-01-29
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility |  | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | W912ER11D00010007 | 40848 | 41717.6573 | 2013-07-25 |  | 2015-10-03 | 2015-09-16 | 0.99
2015-07-31 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA113001 | Theater Communications Facility |  | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912.5671 | 10499.2401 | 2012-05-02 |  | 2014-04-02 | 2016-03-31 | 0.75
2015-07-31 | 2011 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ114127 | Improve Family Housing, Ph 11 |  | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621.7601 | 66149.551 | 2012-05-07 |  | 2015-11-08 | 2015-09-14 | 0.97
[9 empty] | 2011-09-21 | 2012-03-19 | OTIE Milwauke, WI; *Title 2 Contract support* | FA890308D878200014 | 1896.559 | 1896.559 | 2012-05-07 |  | 2015-08-30
[9 empty] | 2012-01-03 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan)*Arch TestDigs* | FA527012P0058 | 50.1855 | 50.1855 | 2012-08-01 |  | 2012-09-03
[9 empty] | 2012-02-02 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT" | FA527012P0080 | 72.005 | 72.005 | 2012-08-31 |  | 2012-09-24
[9 empty] | 2012-03-16 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) ** Appliances** | FA527012FA045 | 319.4316 | 319.4316 | 2012-10-12 |  | 2012-12-11
[9 empty] | 2013-12-13 | 2014-06-11 | OSC Solutions, Inc. (West Palm Beach, FL) **Appliances** | FA527014P0055 | 401.3565 | 401.3565 | 2014-07-11 |  | 2014-09-09
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR106261 | PL-1 Security Measures For Communications Compound |  | 2013-09-13 | 2013-11-13 | MICKAN | C11-4014 | 1840.2888 | 1840.2888 | 2014-03-17 |  | 2014-12-12 | 2015-08-28 | 0.97
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | VYHK113003 | Catch Basin For Waste Water Treatment |  | 2012-04-16 | 2012-07-31 | UVB BITBURG | 113003 | 1762.2 | 1762.2 | 2012-08-15 | 2014-08-01 | 2013-04-12 | 2014-11-22 | 1
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA110032 | Fuel Truck Parking |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730.623 | 1730.623 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.42
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113002 | Fuels Laboratory |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557.438 | 1557.438 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.42
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113005 | C-17 Spare Parts Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572.399 | 1572.399 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.42
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113006 | High Mast Lighting |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573.056 | 1573.056 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.42
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113009 | Entry Control Point |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615.612 | 615.612 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.42
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113010 | Cryogenics Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216.4 | 1216.4 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.42
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113012 | ELRS Storage Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615.533 | 1615.533 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.42
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF080145 | Information Transfer Node |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 1073.822 | 146.94 | 2012-10-03 |  | 2013-10-03 | 2014-12-01 | 0.15
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF105000 | Dining Facility |  | 2012-04-06 | 2012-07-31 | C Davis and Associates | W912ER12C0038 | 1003.878 | 155.7336 | 2012-10-03 |  | 2013-10-03 | 2014-12-01 | 0.15
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF110018 | EMSG Hq |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 1006.756 | 191.812 | 2012-10-03 |  | 2013-10-03 | 2014-12-01 | 0.15
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF110019 | Kennel |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 582.994 | 128.7942 | 2012-10-03 |  | 2013-10-03 | 2014-12-01 | 0.15
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120037 | Clinic |  | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhabi UAE) | W912BU13C0060 | 1514.583 | 1625.7 | 2013-09-27 |  | 2015-01-20 | 2015-12-15 | 0.25
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120057 | Fire Protection Water Storage |  | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120.38 | 1179.614 | 2013-09-30 |  | 2014-11-24 | 2015-09-30 | 0.65
2015-07-31 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF124001 | EOD Facility |  | 2013-07-18 | 2013-09-29 | ACF & BSC JV (Dubai, UAE) | W912BU13C0061 | 0 | 0 | 2014-08-08 |  | 2015-10-02 | 2015-12-03 | 0.1
[9 empty] | 2014-04-21 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1044.893 | 1073.954 | 2014-08-08 |  | 2015-10-02
2015-07-31 | 2011 | Air National Guard | Major construction | ALABAMA | UNITED STATES | FAKZ959574 | Fuel Cell and Corrosion Control Hangar |  | 2011-03-15 | 2011-07-22 | Lord and Son Constrution, Inc | W912JA11C0005 | 7.249 | 7.783 | 2011-10-12 | 2013-11-01 | 2013-01-22 | 2015-08-31 | 1
2015-07-31 | 2011 | Air National Guard | Major construction | ARIZONA | UNITED STATES | HFHA069130 | TFI - Predator LRE Beddown |  | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | W912L213C0001 | 9.434 | 10.626 | 2013-04-08 | 2015-02-13 | 2014-06-02 | 2015-09-25 | 0.98
2015-07-31 | 2011 | Air National Guard | Major construction | FLORIDA | UNITED STATES | LSGA029009A | Security Forces Training Facility |  | 2010-11-12 | 2011-06-06 | Americaan Patriot Construction -IMC, LLC | W911YN11C0003 | 3.909 | 4.164 | 2011-08-05 | 2015-04-08 | 2012-12-03 | 2015-06-08 | 1
2015-07-31 | 2011 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069209 | TFI - F-22 Hangar, Squadron Operations and AMU |  | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | W912J611C0002 | 37.11 | 43.134 | 2011-07-15 | 2016-01-11 | 2013-07-14 | 2016-01-11 | 0.98 | 2001 | KNMD069215;
[9 empty] | 2015-06-04 | 2015-07-06 | Talion Construction | W912J613D00260002 | 0.301 | 0.301 |  | 2016-01-11 | 2016-02-01
2015-07-31 | 2011 | Air National Guard | Major construction | MARYLAND | UNITED STATES | PJMS909928 | Replace Operations and Medical Training Facility |  | 2011-08-17 | 2011-09-28 | Costello Construction of MD, Inc. | W912K611C0016 | 11.802 | 13.584 | 2012-07-20 | 2014-02-28 | 2013-10-18 | 2015-09-30 | 1
2015-07-31 | 2011 | Air National Guard | Major construction | NEW YORK | UNITED STATES | FPBB109013 | TFI - Reaper Infrastructure Support |  | 2012-07-27 | 2012-10-17 | Black Horse Group | W912PQ12D00130003 | 2.04 | 2.196 | 2012-10-17 | 2014-06-16 | 2013-10-12 | 2014-10-20 | 1
2015-07-31 | 2011 | Air National Guard | Major construction | NEW YORK | UNITED STATES | WHAY089079 | Base Defense Group Beddown |  | 2011-07-30 | 2011-09-23 | APS Contractors Inc. | W912PQ11C0048 | 13.401 | 14.451 | 2011-10-13 | 2014-09-05 | 2013-05-05 | 2015-09-25 | 0.98
2015-07-31 | 2011 | Air National Guard | Major construction | NORTH CAROLINA | UNITED STATES | WEFM089029 | Upgrade ASOS Facilities |  | 2011-04-19 | 2011-08-26 | DOT Construction | W9124209D00010904 | 1.66 | 1.873 | 2011-10-24 | 2013-03-25 | 2012-07-21 | 2015-07-01 | 1
2015-07-31 | 2011 | Air National Guard | Major construction | TENNESSEE | UNITED STATES | BKTZ069078 | TFI- Renovate Intel Squadron Facilities |  | 2013-09-20 | 2013-11-21 | Codell Construction Company | W912L710D00060037 | 6.074 | 6.837 | 2013-12-02 | 2015-03-31 | 2014-10-17 | 2015-06-15 | 1
2015-07-31 | 2011 | Air National Guard | Minor construction | HAWAII | UNITED STATES | KNMD109032 | TFI- F-22 Beddown- Add to Communication Facility |  | 2012-01-04 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C0003 | 1.695 | 1.96 | 2012-06-17 | 2014-11-25 | 2014-06-07 | 2014-11-25 | 1
2015-07-31 | 2011 | Air National Guard | Minor construction | WYOMING | UNITED STATES | DPEZ089083 | Relocate ROSC |  | 2011-07-18 | 2012-04-11 | Recco, Inc. | W912L312C0003 | 1.636 | 1.949 | 2012-04-25 | 2015-08-21 | 2012-10-22 | 2016-07-22 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083005 | Dormitory (168 RM) |  | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061.944 | 33061.944 | 2014-08-26 |  | 2016-08-15 | 2016-08-15 | 0.09
2015-07-31 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) |  | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805.3 | 56392.983 | 2012-06-19 |  | 2014-06-19 | 2015-11-11 | 0.82 | 19165 | ALUA073006B;WWYK143004A;YWHG111005;ZHTV053302;
[9 empty] | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230.2925 | 3230.2925 | 2012-06-19 |  | 2013-10-04
[9 empty] | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978.8077 | 4978.8077 | 2012-06-19 |  | 2013-08-28
[9 empty] | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874.106 | 2191.91 | 2012-07-22 |  | 2012-12-20
[9 empty] | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799.2288 | 1799.2288 | 2012-08-27 |  | 2013-02-23
2015-07-31 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120011 | F-35 Squad Ops/AMU 2 |  | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | W912PL13C0006 | 12358.5 | 12848.967 | 2013-04-04 | 2015-01-12 | 2014-09-26 | 2015-01-12 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV103006P1 | EC-130H Simulator/Training Operations |  | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | W912PL12C0011 | 14347.6 | 14990.801 | 2013-02-05 | 2014-10-17 | 2014-07-30 | 2015-08-15 | 0.99 | 4333 | LKTC093101;WWYK143004A;
2015-07-31 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV123002 | HC-130J Joint Use Fuel Cell |  | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | W912PL12C0018 | 12361 | 12645.529 | 2012-10-31 | 2015-05-21 | 2014-04-24 | 2015-07-20 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY983202 | Air Freight Terminal Complex |  | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | N6274210D1308JQ01 | 30047.253 | 33699.6997 | 2012-07-18 | 2015-06-12 | 2014-06-02 | 2015-06-26 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility |  | 2011-12-30 | 2012-04-28 | Pacific West Builders | N4019210D28100003 | 9490.73 | 9433.61 | 2012-05-14 | 2014-08-15 | 2013-10-23 | 2015-03-31 | 1 | 2100 | ZHTV053302;
2015-07-31 | 2012 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB105002 | Mission Support Group Complex |  | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998 | 18717.5021 | 2012-03-26 | 2014-12-23 | 2013-11-24 | 2015-08-31 | 0.99
2015-07-31 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG071005 | WSA Security Control Facility |  | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172.6 | 4308.7912 | 2012-03-16 | 2014-08-15 | 2013-09-07 | 2015-08-15 | 0.99
2015-07-31 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111005 | Force Support Squadron Facility |  | 2012-06-01 | 2012-08-23 | Titan Construction Organizatio | W912DQ11D40150001 | 5388.481 | 5625.923 | 2012-09-07 | 2013-09-30 | 2013-09-07 | 2014-11-07 | 1
[9 empty] | 2013-09-19 | 2013-12-18 | Mack Mechanical, Inc. | W912DQ14C4000 | 1814.472 | 1886.816 | 2014-01-18 | 2013-09-30 | 2014-09-15
2015-07-31 | 2012 | Air Force Active | Major Military Construction | NEBRASKA | UNITED STATES | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 102754.426 | 111911.1589 | 2012-09-11 |  | 2016-09-10 | 2016-09-12 | 0.53
2015-07-31 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103003 | Communications Network Control Center |  | 2011-11-17 | 2012-04-24 | A4 Construction | W912PL12C0008 | 9326.701 | 9655.444 | 2012-05-22 | 2014-05-01 | 2014-05-22 | 2015-07-31 | 0.99 | 800 | ZHTV053302;
2015-07-31 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103010 | F-35 Add/Alter Engine Shop |  | 2011-11-17 | 2012-05-24 | Au Authum KI, Inc | W912PL10D01090001 | 1866.78 | 1866.78 | 2012-08-03 | 2014-09-02 | 2014-11-21 | 2014-12-01 | 1 | 572 | WWYK143004A;
2015-07-31 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD113005 | F-16 Academic Training Facility |  | 2012-02-03 | 2012-06-13 | White Sands Construction | W912PP12C0017 | 4990.32 | 5270.4366 | 2012-07-09 | 2014-05-01 | 2013-11-12 | 2015-10-15 | 0.99
2015-07-31 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV093108 | AFNWC Sustainment Center |  | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | W912PP12C0016 | 21110 | 21590.3553 | 2012-07-09 | 2015-05-20 | 2014-04-30 | 2015-03-06 | 1 | 1100 | ZHTV053302;
2015-07-31 | 2012 | Air Force Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH083003 | C-130 Flight Simulator |  | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | W912HN10D00630003 | 4630 | 5033.2175 | 2012-07-24 | 2015-04-23 | 2014-01-15 | 2015-01-09 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock |  | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | W9128F12C0013 | 32123.257 | 33445.233 | 2012-05-22 | 2015-03-09 | 2014-10-09 | 2015-03-09 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R4 | BMT Recruit Dormitory, Phase IV |  | 2011-12-16 | 2012-07-08 | SB FPI/JSR Inc/DCF2 Ktr - Gary Rd 3/3 | W9126G13C0098 | 91.85 | 91.85 | 2012-11-26 |  | 2012-11-27 | 2015-12-30 | 0.8
[9 empty] | 2012-05-04 | 2012-10-31 | AE-Merrick&Company (E&D) | W9126G08D00060055 | 400.1528 | 400.1528 | 2012-11-26 |  | 2012-11-26
[9 empty] | 2013-01-18 | 2013-07-17 | LB-SpawGlass Contractors, Inc. | W9126G12C0023 | 50528.593 | 52394.893 | 2013-08-17 |  | 2015-08-17
[9 empty] | 2014-04-13 | 2014-10-10 | SB Red Cedar Enterprise Inc-Ext Facs/Kneewall/Quad | W9126G14D00190007 | 7301.694 | 7301.694 | 2014-11-10 |  | 2014-11-10
2015-07-31 | 2012 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | WACC120007 | AIT Barracks Complex, Ph 2 |  | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | W9123608D00140003 | 33915.149 | 34116.7784 | 2012-10-12 | 2014-10-29 | 2014-10-04 | 2014-11-19 | 1 | 10112 | LKTC093101;WWYK143004A;ZHTV053302;
2015-07-31 | 2012 | Air Force Active | Major Military Construction | WASHINGTON | UNITED STATES | GJKZ860009 | Wing Headquarters |  | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | W912DW12C0030 | 11957.25 | 12620.017 | 2012-05-21 | 2014-03-07 | 2014-01-21 | 2015-04-10 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17001 | Aircraft Apron/Taxiway And Maintenance Shelters |  | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | N3319109D01200011 | 6740.135 | 6640.535 | 2012-05-02 | 2015-01-07 | 2013-01-27 | 2015-01-07 | 1
2015-07-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17002 | Combat Aircraft Loading Area |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421 | 43761.8504 | 2012-10-01 |  | 2014-01-16 | 2015-08-31 | 0.88
2015-07-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17003 | Parallel Taxiway Extension |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521.53 | 10521.53 | 2012-10-01 |  | 2014-05-24 | 2015-08-31 | 0.98
2015-07-31 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17004 | Expeditionary Lodging |  | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587.915 | 27299.359 | 2012-10-20 | 2014-10-20 | 2014-04-13 | 2015-12-31 | 0.99
2015-07-31 | 2012 | Air Force Active | Major Military Construction |  | ITALY | ASHE163000 | Child Development Center Addition |  | 2012-06-06 | 2012-09-30 | Collodetto Angelo Costruzioni | N3319112R06220002 | 890.2326 | 988.1307 | 2012-09-30 | 2014-10-21 | 2013-12-29 | 2014-12-03 | 1
2015-07-31 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 |  | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706.6686 | 17706.6686 | 2013-06-04 |  | 2016-05-10 | 2015-11-20 | 0.94
2015-07-31 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA124002 | Improve MFH Infrastructure, Phase 1 |  | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | W912HV12C0003 | 19550.171 | 20354.9856 | 2012-06-11 | 2015-06-30 | 2014-11-28 | 2015-06-30 | 1
2015-07-31 | 2012 | Air Force Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | FBNV133500 | T-10 Engine Test Cell (AMARG) |  | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D0110 | 1795 | 1795 | 2014-08-12 |  | 2015-06-08 | 2015-11-22 | 0.15
2015-07-31 | 2012 | Air Force Active | Unspecified Minor Military Construction | INDIANA | UNITED STATES | CTGB102040 | Addition to BOWST Simulator |  | 2012-04-23 | 2012-08-03 | ITSI | FA6643-08-D-0005 | 1031.327 | 1031.327 | 2012-08-06 |  | 2013-04-08 | 2013-04-30 | 0.35
2015-07-31 | 2012 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | AGGN123002P | Communications Network Control Center Consolidation |  | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619.1715 | 1619.1715 | 2014-03-10 |  | 2014-12-19 | 2015-07-07 | 0.92
2015-07-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113026 | C-130 Aircraft Maintenance Unit |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511.518 | 1511.518 | 2013-09-12 |  | 2014-12-06 | 2016-06-30 | 0.23
2015-07-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113027 | Air Defense Artillery Maintenance Facility |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265.194 | 1277.795 | 2013-08-28 |  | 2014-11-06 | 2015-10-15 | 0.98
2015-07-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113032 | Precision Measurement Equipment Laboratory |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403.744 | 1423.5787 | 2013-08-28 |  | 2015-02-19 | 2015-10-15 | 0.98
2015-07-31 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113034 | AFOSI Regional And Local Facility |  | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214.606 | 1219.6319 | 2013-08-28 |  | 2015-02-19 | 2015-10-15 | 0.98
2015-07-31 | 2012 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ120572 | Vehicle Maintenance Facility |  | 2013-01-04 | 2014-08-22 | Oddo Construction Services | FA667014C0002 | 2087.131 | 2087.131 | 2014-09-22 |  | 2016-03-15 | 2015-07-31 | 0.82
2015-07-31 | 2012 | Air Force Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX079003 | Red Horse Readiness And Training Facility |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149 | 9004.77 | 2012-07-13 |  | 2013-07-13 | 2015-12-15 | 0.92
2015-07-31 | 2012 | Air National Guard | Major construction | CALIFORNIA | UNITED STATES | QMSN019029 | Replace Pararescue Training Facility |  | 2012-08-05 | 2012-09-26 | Flintco Construction | W912LA12C7025 | 25.066 | 27.717 | 2012-11-25 | 2015-02-13 | 2014-02-23 | 2015-03-13 | 1
2015-07-31 | 2012 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069212 | TFI - F-22 Flight Simulator Facility |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C0003 | 18.842 | 21.739 | 2012-06-17 | 2014-11-25 | 2014-06-07 | 2014-11-25 | 1
2015-07-31 | 2012 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069213 | TFI - F-22 Weapons Load Crew Training Facility |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | W912J612C0003 | 6.473 | 8.278 | 2012-06-17 | 2014-11-25 | 2014-06-07 | 2014-11-25 | 1
2015-07-31 | 2012 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron |  | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | W9128A12C0007 | 9.682 | 10.875 | 2012-08-08 | 2015-06-24 | 2013-08-08 | 2015-06-24 | 1
[9 empty] | 2013-03-04 | 2013-09-12 | Nan, Inc | W912J613C0006 | 2 | 2 | 2013-09-30 | 2015-06-24 | 2015-03-29
2015-07-31 | 2012 | Air National Guard | Major construction | INDIANA | UNITED STATES | ATQZ099080 | A-10 Facility Conversion - Munitions Complex |  | 2014-05-10 | 2014-08-27 | Patterson Horth, Inc. | W912L910D00090055 | 4.121 | 4.437 | 2014-08-27 | 2015-12-31 | 2015-11-20 | 2015-12-31 | 0.42
2015-07-31 | 2012 | Air National Guard | Major construction | MASSACHUSETTS | UNITED STATES | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities |  | 2013-05-08 | 2013-08-29 | Maron Construction Co. | W912SV13C0003 | 7.919 | 8.731 | 2013-09-24 | 2015-07-24 | 2013-09-28 | 2015-09-04 | 0.75
2015-07-31 | 2012 | Air National Guard | Minor construction | GEORGIA | UNITED STATES | XDQU129062 | Vehicle Maintenance Addition |  | 2012-05-24 | 2012-08-17 | Tyler Construction Group, Inc. | W912JM10D00040001 | 1.5 | 1.5 | 2012-08-17 | 2013-09-30 | 2013-02-13 | 2014-10-28 | 1
2015-07-31 | 2012 | Air National Guard | Minor construction | MAINE | UNITED STATES | FKNN049094 | Pavements and Grounds Facility |  | 2012-05-16 | 2012-09-12 | Cornerstone Construction | W912JD11D00070003 | 1.277 | 1.329 | 2012-09-19 | 2013-11-25 | 2013-03-18 | 2014-11-14 | 1
2015-07-31 | 2012 | Air National Guard | Minor construction | MASSACHUSETTS | UNITED STATES | AXQD119004 | Add to and Alter Survival Equipment Shop |  | 2013-04-10 | 2013-07-12 | Cornerstone Construction Svs | W912SV10D00080004 | 1.19 | 1.265 | 2013-07-16 | 2015-01-31 | 2014-02-07 | 2015-02-28 | 1
2015-07-31 | 2012 | Air National Guard | Minor construction | MASSACHUSETTS | UNITED STATES | AXQD129074 | F 15 Shop Addition |  | 2014-09-12 | 2014-12-15 | Cutter Enterprises LLC | W912SV15C0001 | 1.631 | 1.713 | 2015-01-13 | 2016-07-16 | 2016-07-16 | 2016-06-17 | 0.03
2015-07-31 | 2012 | Air National Guard | Minor construction | NEW YORK | UNITED STATES | WKVB099052 | Add to Fire Station |  | 2014-12-04 | 2015-03-25 | Regiment | W912PQ15C0003 | 1.972 | 2.021 | 2015-06-26 | 2016-06-28 | 2016-04-23 | 2016-06-28 | 0.03
2015-07-31 | 2012 | Air National Guard | Minor construction | OHIO | UNITED STATES | WAAR129078 | Relocate Main Gate |  | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | W9136413D00050002 | 1.713 | 1.818 | 2013-08-27 | 2014-10-31 | 2014-02-23 | 2015-12-31 | 0.95
2015-07-31 | 2012 | Air National Guard | Minor construction | OREGON | UNITED STATES | KJAQ119031 | Addition Squadron Operations Facility |  | 2013-10-08 | 2014-01-29 | Anthem Builders, Inc | W912JV14C0002 | 1.678 | 1.842 | 2014-03-12 | 2015-08-28 | 2014-11-10 | 2015-09-25 | 1
2015-07-31 | 2012 | Air National Guard | Minor construction | OREGON | UNITED STATES | TQKD129072 | Construct Alert Hangar Bay |  | 2014-03-25 | 2014-07-22 | Total Site Services | W912JV14C0006 | 1.737 | 1.907 | 2014-09-03 | 2015-08-21 | 2015-03-19 | 2015-09-11 | 0.94
2015-07-31 | 2012 | Air National Guard | Minor construction | PUERTO RICO | PUERTO RICO | TUMR109004 | Joint Force HQ - ANG Share Fort Buchanan |  | 2013-04-30 | 2013-09-26 | R.B. Construction Group, Inc. | W912LR13C0001 | 1.5 | 1.5 | 2013-11-25 |  | 2015-10-06 | 2015-10-14 | 0.7
2015-07-31 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK103006 | C-130J Fuel Systems Maintenance Hangar |  | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869 | 21464.974 | 2013-07-23 |  | 2015-07-23 | 2015-10-28 | 0.78 | 2000 | KRSM103012;
2015-07-31 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK113005 | C-130J Flight Simulator Addition |  | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218.503 | 4218.503 | 2014-10-21 |  | 2015-10-21 | 2015-10-21 | 0.34
2015-07-31 | 2013 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY133001 | Civil Engineer Administration/Operations Facility |  | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947.269 | 16020.4956 | 2014-07-09 |  | 2016-03-30 | 2016-03-30 | 0.13
2015-07-31 | 2013 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair |  | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 12555.018 | 13444.061 | 2013-08-21 | 2015-06-10 | 2015-08-11 | 2015-05-29 | 1
2015-07-31 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | ACC123184 | Air Support Operations Center |  | 2013-03-14 | 2013-09-24 | Better Built Construction Serv | W912HN10D00530003 | 6458 | 6575.957 | 2013-11-07 |  | 2015-05-01 | 2015-08-12 | 0.6
2015-07-31 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | QSEU103008 | HC-130J Simulator Facility |  | 2012-12-07 | 2013-06-28 | IBKI, Inc. Choctaw, MS | W912HN13C0011 | 7692.387 | 7808.669 | 2013-08-12 | 2014-12-19 | 2015-01-04 | 2015-04-29 | 1
2015-07-31 | 2013 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY123010 | Guam Strike Fuel Systems Maintenance Hangar |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 89918.305 | 89918.305 | 2015-03-18 |  | 2017-04-16 | 2017-03-21 | 0.07
2015-07-31 | 2013 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC133101 | RPA Mission Complex Physical Protection System |  | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643.42 | 10795.95 | 2014-08-19 |  | 2015-08-19 | 2015-10-15 | 0.82
2015-07-31 | 2013 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD123004 | MQ-9 Maintenance Hangar |  | 2013-03-01 | 2013-06-17 | HEW-Phelps | W912PP13C0019 | 20620 | 20726.768 | 2013-07-15 | 2014-09-22 | 2015-04-06 | 2015-02-23 | 1 | 1225 | KRSM103012;
2015-07-31 | 2013 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092011 | B-52 Add/Alter Munitions Age Facility |  | 2012-11-19 | 2013-05-31 | Rolac Contracting, Inc. | W9128F13C0008 | 4376.727 | 4260.351 | 2013-06-19 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 1
2015-07-31 | 2013 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083008 | Dormitory (96 Rm) |  | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170.185 | 17241.355 | 2014-01-10 |  | 2015-07-04 | 2015-12-20 | 0.52
2015-07-31 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103012 | F-35 Adal Hangar 45W/AMU |  | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781 | 9369.9451 | 2014-01-27 |  | 2015-07-21 | 2016-03-21 | 0.55
2015-07-31 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103030 | F-35A Modular Storage Magazines |  | 2012-08-08 | 2013-12-17 | Zumwalt Construction, Inc. | W9123811D00260006 | 2028.458 | 2033.5187 | 2014-01-27 |  | 2015-07-21 | 2015-10-25 | 0.99
2015-07-31 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM113028 | F-35 Adal Building 118 For Flight Simulator |  | 2012-08-08 | 2013-12-17 | Creative Times, Inc. (CTI) | W9123811D00240002 | 3878.926 | 3947.8686 | 2014-01-29 |  | 2015-03-30 | 2015-07-30 | 0.99
2015-07-31 | 2013 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103032 | Dormitory (48 Pn) |  | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031.649 | 23031.649 | 2013-08-08 |  | 2015-07-29 | 2015-07-29 | 0.99
2015-07-31 | 2013 | Air Force Active | Major Military Construction |  | ITALY | ASHE103001 | F-16 Mission Training Center |  | 2014-03-06 | 2015-02-26 | Coop Muratori & Cementisti CMC Di Ravenn | N6247015C5005 | 1780.2343 | 1780.2343 | 2015-03-13 |  | 2016-12-02 | 2016-06-01 | 0.02
2015-07-31 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 |  | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698.0727 | 14787.5107 | 2013-08-29 |  | 2015-11-27 | 2016-01-04 | 0.64
2015-07-31 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA133001P2 | Improve Family Housing, Ph 2 |  | 2013-05-16 | 2013-09-30 | Nishimatsu Construction Co., Ltd | FZ520513C0005 | 13989.4156 | 14084.1796 | 2013-10-29 | 2015-06-05 | 2015-06-21 | 2015-06-05 | 1
2015-07-31 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA134001 | Improve Mfh Infrastructure, Phase 2 |  | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336.739 | 14750.0427 | 2013-10-23 |  | 2015-09-23 | 2015-09-22 | 0.88
2015-07-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | FTFA123000 | Advanced Energetics Development Office Facility |  | 2014-07-28 | 2014-10-30 | Barlovento LLC | W9127810D00720015 | 1756.83 | 1756.83 | 2014-12-05 |  | 2015-12-05 | 2015-12-08 | 0.29
2015-07-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | AJXF106000 | Construct Taxiway To North Of ACA Facility Bldg 2489 |  | 2014-08-07 | 2015-03-04 | Heard Contracting | W912DR15C0010 | 2132.837 | 2132.837 | 2015-04-09 |  | 2016-04-08 | 2016-05-08 | 0.02
2015-07-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 |  | 2013-03-06 | 2013-05-23 | Southwind Construction | W912BV12D00180003 | 1525.212 | 1573.679 | 2013-06-07 | 2015-07-17 | 2015-08-03 | 2015-07-17 | 1
2015-07-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | GJKZ130025 | ADAL, Physiological Tng Fac, Convert To PMEL; B2145 |  | 2014-08-01 | 2014-12-31 | Ahtna Engineering | FA462013DB004003 | 1698.195 | 1698.195 | 2015-01-27 |  | 2015-12-17 | 2015-12-17 | 0.03
2015-07-31 | 2013 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR126175 | Expand AOC Parking Structure |  | 2014-01-21 | 2014-07-23 | MICKAN Generalbau | C124019 | 1664.1511 | 1664.1511 | 2014-08-08 |  | 2015-02-24 | 2015-08-14 | 0.97
2015-07-31 | 2013 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ099095 | Flight Simulator Facility |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242.986 | 5242.986 | 2014-07-24 |  | 2016-01-15 | 2016-01-15 | 0.02
2015-07-31 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | KYJM129022 | Add Simulator Bay, Building 191 |  | 2013-06-07 | 2013-09-23 | CCI | W9127810D01180020 | 1552.029 | 1591.6019 | 2013-12-13 | 2015-06-30 | 2014-09-26 | 2015-06-30 | 1
2015-07-31 | 2013 | Air National Guard | Major construction | CALIFORNIA | UNITED STATES | HAYW109006 | F-15 Conversion |  | 2013-08-23 | 2013-09-27 | RS Morris Construction | W912LA11D00180010 | 3.747 | 4.9 | 2013-11-01 | 2016-02-18 | 2015-01-25 | 2016-02-18 | 0.85
[9 empty] | 2013-08-23 | 2013-09-30 | RS Morris Cosntruction | W912LA11D00180011 | 2.402 | 2.636 | 2013-11-01 | 2016-02-18 | 2015-01-25
[9 empty] | 2014-08-15 | 2014-10-26 | Cooper Chase | W912LA11D00040002 | 1.09 | 1.387 | 2014-12-02 | 2016-02-18 | 2016-02-25
2015-07-31 | 2013 | Air National Guard | Major construction | HAWAII | UNITED STATES | KNMD119001 | TFI - F-22 Combat Apron Addition |  | 2013-03-04 | 2013-09-12 | Nan Inc. | W912J613C0006 | 4.993 | 6.185 | 2013-10-31 | 2015-07-24 | 2015-04-24 | 2015-07-24 | 1
2015-07-31 | 2013 | Air National Guard | Major construction | NEW MEXICO | UNITED STATES | MHMV119001 | Alter Target Intelligence Facility |  | 2013-05-22 | 2013-10-10 | K.L. HOUSE CONSTRUCTION CO. | W912J314C1001 | 4.569 | 5.174 | 2014-01-27 | 2015-07-21 | 2015-01-27 | 2015-08-21 | 0.98
2015-07-31 | 2013 | Air National Guard | Major construction | WYOMING | UNITED STATES | DPEZ089017 | C-130 Flight Simulator Training Facility |  | 2013-08-28 | 2013-09-27 | Faith Enterprises | W912L313D00030001 | 5.062 | 5.356 | 2013-09-27 | 2015-03-23 | 2015-03-21 | 2016-08-25 | 0.93
2015-07-31 | 2013 | Air National Guard | Minor construction | INDIANA | UNITED STATES | ATQZ099073 | MCCA: A-10 Conversion-Expand Arm/Disarm Apron-T/W Bravo |  | 2014-10-01 | 2014-12-08 | E & B Paving, Inc | W912L91322101 | 1.38 | 1.498 | 2014-11-12 | 2015-07-09 | 2016-05-21 | 2015-08-31 | 0.98
2015-07-31 | 2013 | Air National Guard | Minor construction | NORTH CAROLINA | UNITED STATES | FJRP079016 | BCE pavements and Grounds Facility |  | 2013-12-23 | 2014-04-07 | Showalter Construction | W9124209D0013N908 | 1.22 | 1.305 | 2014-06-01 | 2015-06-01 | 2015-03-03 | 2015-06-01 | 1
2015-07-31 | 2013 | Air National Guard | Minor construction | OHIO | UNITED STATES | WYTD139000 | Construct Security Forces |  | 2014-02-05 | 2014-06-12 | K & T Construction and Supply, Inc | W9136413D00220007 | 1.549 | 1.659 | 2014-07-08 | 2015-06-29 | 2015-04-04 | 2015-09-30 | 0.95
2015-07-31 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093007 | Construct Addition, Field Training Facility, B936 |  | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699.907 | 4699.907 | 2014-04-23 |  | 2015-07-07 | 2015-08-29 | 0.52
2015-07-31 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) |  | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513.636 | 15698.045 | 2014-06-24 |  | 2016-02-14 | 2016-02-14 | 0.23
2015-07-31 | 2014 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699.643 | 53699.643 | 2014-08-27 |  | 2016-11-04 | 2017-02-21 | 0.07
2015-07-31 | 2014 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103007 | F-22 Muntions Storage Complex |  | 2015-03-10 | 2015-04-14 | Southeast Cherokee Construction | W9127810D00780009 | 9094.468 | 9094.468 | 2015-05-21 |  | 2016-11-11 | 2016-10-25 | 0.02
2015-07-31 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY133027 | Guam Strike Tanker Gp Maint Hangar/Amu/Sqd Ops (Incr 1) |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 96616.6193 | 96616.6193 | 2015-01-08 |  | 2017-03-08 | 2017-03-08 | 0.08
2015-07-31 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY143760 | Hardened Structures For POL Fuel Systems |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907.7 | 17907.7 | 2014-10-20 |  | 2016-04-12 | 2016-06-15 | 0.06
2015-07-31 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility |  | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177.269 | 6177.269 | 2014-10-27 |  | 2016-08-17 | 2016-07-20 | 0.22
2015-07-31 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW113003 | PRTC - Red Horse Airfield Operations Facility (TFI) |  | 2014-01-23 | 2015-03-06 | P&S Construction Inc | N4019210D28040023 | 7050.5063 | 7050.5063 | 2015-03-06 |  | 2016-07-08 | 2016-07-08 | 0.13
2015-07-31 | 2014 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW133005 | PRTC Silver Flag Fire Rescue & Emergency Management Training |  | 2014-03-04 | 2015-03-05 | P & S Construction | N4019210D2804KB01 | 3587 | 3587 | 2015-03-27 |  | 2017-02-06 | 2017-01-01 | 0.07
2015-07-31 | 2014 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  | 2013-11-18 | 2014-06-17 | SRB International LLC | N6274214C1312 | 2699 | 2699 | 2014-07-17 |  | 2015-06-07 | 2015-12-07 | 0.05
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar |  | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924.5 | 64191.03 | 2014-06-24 |  | 2016-01-05 | 2017-03-10 | 0.38 | 10500 | SGBP100904C;
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145121 | KC-46A ADAL Flight Simulator Buildings |  | 2014-03-14 | 2015-03-02 | Aerostar SES, Inc | W912DQ15C4005 | 3061.137 | 3061.137 | 2015-04-20 |  | 2016-04-19 | 2016-03-30 | 0.03
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems |  | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100.5 | 8268.701 | 2014-06-25 |  | 2015-12-17 | 2015-12-19 | 0.81 | 2500 | SGBP100904C;
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145137 | KC-46A Alter Miscellaneous Facilities |  | 2014-03-10 | 2014-06-27 | Red Cedar Enterprises, Inc | W912DQ13D40010002 | 838.705 | 917.758 | 2014-07-03 |  | 2015-02-28 | 2015-04-30 | 0.89
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145138 | KC-46A Alter Aircraft Parking Apron |  | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976 | 976 | 2014-06-24 |  | 2017-03-10 | 2017-03-10 | 0.16 | 600 | PRQE145121;
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145142 | KC-46A 1-Bay Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200 | 25281.083 | 2014-06-24 |  | 2017-01-19 | 2017-03-10 | 0.41 | 3000 | SGBP100904C;
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959 | 53806.382 | 2014-06-24 |  | 2015-12-26 | 2017-03-10 | 0.12 | 19000 | SGBP100904C;
2015-07-31 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) |  | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306.162 | 7315.789 | 2014-10-15 |  | 2015-10-15 | 2015-10-15 | 0.33
2015-07-31 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF103010 | Construct Helicopter Operations Facility |  | 2014-08-15 | 2014-12-30 | The Haskell Company | N4008010D04910002 | 21754.67 | 21754.67 | 2015-01-26 |  | 2017-04-05 | 2017-03-09 | 0.02
2015-07-31 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 57000 | 57000 | 2014-04-14 |  | 2016-04-13 | 2017-04-13 | 0.02
2015-07-31 | 2014 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111010 | WSA: Construct Two New MOP Igloos |  | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817.7 | 3828.847 | 2014-08-11 |  | 2015-12-04 | 2015-12-13 | 0.58
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC073101 | Land Acquisition |  | 2014-07-18 | 2014-09-02 | USACE | W81EYN42417577 | 11450 | 11450 | 2014-09-02 |  | 2014-12-01 | 2016-03-15 | 0.02
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF083002 | Dormitory |  | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381 | 30381 | 2014-07-11 |  | 2016-09-28 | 2016-09-27 | 0.11
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103005 | F-35A ADAL AME Storage Facility |  | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D0113 | 4829.984 | 4829.984 | 2014-08-27 |  | 2016-02-18 | 2016-02-18 | 0.24
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103006 | F-35A Parts Store |  | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974.014 | 6974.014 | 2014-07-10 |  | 2016-01-06 | 2016-04-12 | 0.24
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar |  | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066 | 8130.086 | 2014-06-24 |  | 2015-12-16 | 2016-03-01 | 0.43
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF113005 | RPA Weapons School |  | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922.7 | 14938.36 | 2014-08-12 |  | 2016-08-01 | 2016-06-01 | 0.4
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ013004 | Airman And Family Readiness Center |  | 2015-01-29 | 2015-05-18 | Speegle Construction Inc. | W912PP15C0006 | 5102.2 | 5102.2 | 2015-06-11 |  | 2016-06-10 | 2016-06-10 | 0.02
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073023A | Satellite Dining Facility |  | 2014-08-04 | 2014-12-05 | Speegle Construction Inc. | W912PP15C0001 | 7001 | 7022.3761 | 2015-01-27 |  | 2016-11-19 | 2016-11-19 | 0.31
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073050 | Dormitory (144 Rm) |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19716.709 | 19678.9999 | 2014-08-14 |  | 2016-08-21 | 2016-08-21 | 0.43
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 |  | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285.5 | 21285.5 | 2014-08-25 |  | 2016-11-01 | 2016-02-08 | 0.25
2015-07-31 | 2014 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092013 | B-52 Munitions Storage Igloos |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540.27 | 9510.291 | 2014-07-15 |  | 2016-01-06 | 2016-01-06 | 0.38
2015-07-31 | 2014 | Air Force Active | Major Military Construction | OHIO | UNITED STATES | ZHTV053302 | Add/Alter Foreign Materiel Exploitation Laboratory |  | 2015-03-11 | 2015-06-23 | Messer Construction | W912QR15C0012 | 24166 | 24166 | 2015-07-13 |  | 2017-06-02 | 2017-01-06 | 0.02
2015-07-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164.308 | 1178.891 | 2014-07-02 | 2015-04-13 | 2015-12-24 | 2015-09-29 | 0.97
2015-07-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111.892 | 7184.142 | 2014-07-02 |  | 2015-12-24 | 2016-01-05 | 0.42
2015-07-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645.2 | 5645.2 | 2014-06-19 |  | 2015-09-22 | 2015-11-14 | 0.48
2015-07-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143004 | KC-46A FTU FTC Simulator Facility Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000 | 11112.7549 | 2014-06-19 |  | 2015-09-22 | 2015-11-14 | 0.61
2015-07-31 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | WWYK143004A | KC46A Land Acquisition |  | 2015-01-27 | 2015-03-13 | BNJ Builders of Oklahoma City | W912BV11D00130007 | 496.781 | 496.781 | 2015-03-23 | 2015-02-26 | 2015-07-05 | 2015-06-15 | 1
2015-07-31 | 2014 | Air Force Active | Major Military Construction | TENNESSEE | UNITED STATES | ACC123183 | Air Support Operations Center |  | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143.462 | 7200.0209 | 2014-08-28 |  | 2016-02-20 | 2015-12-13 | 0.44
2015-07-31 | 2014 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 |  | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265.367 | 3310.0714 | 2014-05-15 | 2015-06-30 | 2015-06-09 | 2015-08-15 | 0.95
2015-07-31 | 2014 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103011 | F-35 ADAL Hangar 45E/AMU |  | 2013-07-22 | 2014-04-10 | CTI | W912PL14C0005 | 6587 | 9002.326 | 2014-04-22 |  | 2015-10-14 | 2015-10-15 | 0.99
2015-07-31 | 2014 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817.6089 | 39817.6089 | 2014-08-19 |  | 2016-08-08 | 2016-06-17 | 0.16
2015-07-31 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ144287 | Improve MFH Infrastructure, Phase 3 |  | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288.6807 | 6312.8478 | 2014-07-23 |  | 2015-08-27 | 2016-04-06 | 0.31
[9 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202.136 | 4202.136 | 2014-07-23 |  | 2015-12-15
[9 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473.4496 | 2473.4496 | 2014-07-23 |  | 2014-07-23
[9 empty] | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302.11 | 25302.11 | 2014-11-06 |  | 2017-01-14
2015-07-31 | 2014 | Air Force Active | Unspecified Minor Military Construction | COLORADO | UNITED STATES | XQPZ124003 | Const Perm ECP-Pine Drive |  | 2014-12-03 | 2015-03-25 | John Bowman Incorporated (JBI) | W9128F12D0037 | 1581 | 1581 | 2015-04-13 |  | 2015-12-09 | 2015-12-09 | 0.15
2015-07-31 | 2014 | Air Force Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | FTFA073007 | CNST Modular Storage Magazines |  | 2014-07-24 | 2014-12-30 | Southeast Cherokee Constructio | W9127810D00780008 | 1457.737 | 1457.737 | 2015-02-05 |  | 2016-02-05 | 2016-02-09 | 0.02
2015-07-31 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility |  | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547.47 | 1547.47 | 2014-11-19 |  | 2015-11-19 | 2015-11-23 | 0.02
2015-07-31 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | UHHZ123001 | Convert Cooler Area B/660 To AFLCMC/WFM C-17 Program Office |  | 2014-08-01 | 2015-01-15 | Garbutt Construction Company | W912HN10D00340002 | 1779.3606 | 1779.3606 | 2015-02-11 |  | 2016-05-11 | 2016-05-11 | 0.02
2015-07-31 | 2014 | Air National Guard | Major construction | ALABAMA | UNITED STATES | BRKR999147 | Add to and Alter Distributed Ground Station Facility |  | 2014-04-02 | 2014-08-13 | Southeast Cherokee Conwstruction, Inc | W912JA14C0001 | 8.05 | 8.23 | 2014-10-31 | 2016-08-02 | 2016-10-23 | 2016-08-02 | 0.15
2015-07-31 | 2014 | Air National Guard | Major construction | INDIANA | UNITED STATES | LDXF099060 | Add/Alter Bldg 37 for Distributed Common Grnd Stn |  | 2014-07-30 | 2014-09-22 | Patterson-Horth | W912L914D00110002 | 6.848 | 7.423 | 2014-10-16 | 2016-06-30 | 2016-02-28 | 2016-06-30 | 0.29
2015-07-31 | 2014 | Air National Guard | Major construction | MONTANA | UNITED STATES | JKSE129321 | Intra-Theater Airlift Conversion |  | 2014-06-11 | 2014-09-16 | James Talcott Construction Inc | W9124V14C0004 | 20.253 | 21.104 | 2014-10-20 | 2015-08-31 | 2016-10-15 | 2016-09-15 | 0.54
[9 empty] | 2014-07-15 | 2014-10-28 | Guy Tabacco Construction Co.. | W9124V12D00110003 | 1.442 | 1.492 | 2014-11-17 | 2015-08-31 | 2015-09-13
[9 empty] | 2014-09-24 | 2014-11-07 | Wadsworth Builders Co., Inc. | W9124V12D00090008 | 1.261 | 1.261 |  | 2015-08-31 | 2015-10-03
2015-07-31 | 2014 | Air National Guard | Major construction | NEW YORK | UNITED STATES | FPBB129050 | MQ-9 Flight Training Unit Hangar |  | 2014-07-17 | 2014-09-08 | R.J. Ortlieb | W912PQ12D00100008 | 4.605 | 4.861 | 2014-09-25 | 2015-09-21 | 2015-08-04 | 2015-09-21 | 0.8
2015-07-31 | 2014 | Air National Guard | Major construction | OHIO | UNITED STATES | WAAR109002 | Alter Intelligence Operations Facility |  | 2014-07-02 | 2014-08-20 | AWA/Megen Joint Venture LLC | W9136414C0011 | 5.623 | 6.519 | 2014-12-01 | 2015-11-30 | 2015-12-01 | 2015-12-19 | 0.54
2015-07-31 | 2014 | Air National Guard | Major construction | PENNSYLVANIA | UNITED STATES | LKLW109037 | Communications Operations and Training Facility |  | 2014-08-06 | 2014-09-25 | Lobar Associates | W912KC14C0008 | 6.651 | 7.222 | 2014-10-16 | 2015-10-16 | 2015-10-25 | 2015-10-25 | 0.35
2015-07-31 | 2014 | Air National Guard | Major construction | RHODE ISLAND | UNITED STATES | TWLR129077 | C-130J Flight Simulator Training Facility |  | 2014-07-25 | 2014-11-14 | MARON CONSTRUCTION CO., INC. | W912LD15C0001 | 5.983 | 6.287 | 2015-03-15 |  | 2015-12-14 | 2015-11-14 | 0.17
2015-07-31 | 2014 | Air National Guard | Major construction | TENNESSEE | UNITED STATES | PSXE109034 | TEC Expansion - Dormitory and Classroom Training Facility |  | 2014-04-15 | 2014-07-01 | Howard Pence, Inc | W912L714C0004 | 16.301 | 17.005 | 2014-07-22 | 2016-07-20 | 2016-07-21 | 2016-07-20 | 0.35
2015-07-31 | 2014 | Air National Guard | Minor construction | MISSOURI | UNITED STATES | ULYB112022 | Security Forces Admin and Storage Facility |  | 2014-07-30 | 2014-09-12 | E.L.Crawford Construction | W912NS14D00160002 | 1.86 | 1.954 | 2014-10-29 | 2015-11-04 | 2015-10-12 | 2016-05-05 | 0.6
2015-07-31 | 2014 | Air National Guard | Minor construction | OKLAHOMA | UNITED STATES | XHZG129946 | Add to Fire Crash and Rescue Station, Building 403 |  | 2014-06-25 | 2014-08-20 | Magnum Constrution | W912L611D00010029 | 1.915 | 1.979 | 2014-08-20 | 2015-08-20 | 2015-08-15 | 2015-08-20 | 0.73
2015-07-31 | 2014 | Air National Guard | Minor construction | SOUTH CAROLINA | UNITED STATES | PSTE129092 | Construct North Overrun |  | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W9124209D0003S401 | 1.702 | 1.807 | 2014-03-11 | 2014-12-08 | 2014-12-24 | 2015-07-31 | 1
2015-07-31 | 2014 | Air National Guard | Minor construction | WASHINGTON | UNITED STATES | GJKZ129093 | Construct 2 Set DRBS Storage Facility |  | 2014-04-22 | 2014-08-12 | Pacific Tech Construction | W912K311D00030005 | 1.719 | 1.778 | 2014-09-18 | 2015-09-01 | 2015-03-17 | 2015-09-23 | 0.7
2015-07-31 | 2015 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX103005 | Construct Flightline Fillstands |  | 2014-12-16 | 2015-04-30 | SAI-TALON JV | W912PL15C0005 | 13097.8 | 13097.8 | 2015-06-01 |  | 2016-11-22 | 2016-11-23 | 0.03
2015-07-31 | 2015 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059006 | PRTC - Red Horse Logistics Facility |  | 2014-11-07 | 2015-03-07 | P&S Construction Inc | N4019210D28040025 | 2841.6 | 2841.6 | 2015-03-07 |  | 2016-04-10 | 2016-04-10 | 0.15
2015-07-31 | 2015 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW113008 | PRTC - Combat Communications Infrastructure Facility |  | 2015-03-20 | 2015-06-30 | GSI-EA JV, LLC | N4019210D2809004 | 3586.194 | 3586.194 | 2015-07-17 |  | 2016-06-21 | 2017-01-01 | 0.02
2015-07-31 | 2015 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW143031 | PRTC Satellite Fire Station |  | 2014-12-05 | 2015-03-06 | P&S Construction Inc | N4019210D28040024 | 6205 | 6205 | 2015-03-06 |  | 2016-07-30 | 2016-07-30 | 0.15
2015-07-31 | 2015 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145118 | KC-46A Fuselage Trainer |  | 2015-01-26 | 2015-04-03 | Hanke Constructors | W912DQ14D400300101 | 6389.509 | 6389.509 | 2015-05-05 |  | 2016-05-04 | 2016-11-07 | 0.02
2015-07-31 | 2015 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155118 | KC-46A Adal Mobility Bag Storage Expansion |  | 2015-01-26 | 2015-04-03 | Hanke Constructors | W912DQ14D400300101 | 2286.153 | 2286.153 | 2015-05-05 |  | 2016-05-04 | 2016-02-05 | 0.02
2015-07-31 | 2015 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155124 | KC-46A Alter Taxiway Foxtrot |  | 2015-01-26 | 2015-04-17 | K&K Industries, Inc | W912DQ14D40090002 | 5679.326 | 5679.326 | 2015-05-12 |  | 2016-11-02 | 2016-11-21 | 0.02
2015-07-31 | 2015 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF133001 | F-22 Flight Simulator Facility |  | 2015-01-22 | 2015-06-12 | CTI | W912PL15C0010 | 11361 | 11361 | 2015-07-09 |  | 2017-01-19 | 2017-02-15 | 0.02
2015-07-31 | 2015 | Air National Guard | Major construction | CONNECTICUT | UNITED STATES | CEKT139004 | Construct C-130 Fuel Cell and Corrosion Control Facility |  | 2015-02-17 | 2015-06-03 | Cutter Enterprises, LLC | W91ZRS15C0002 | 14.368 | 14.86 | 2015-07-24 | 2016-12-23 | 2016-12-05 | 2016-12-23 | 0.05
2015-07-31 | 2015 | Air National Guard | Major construction | MICHIGAN | UNITED STATES | MBMV129060 | RPA Beddown |  | 2015-03-01 | 2015-04-15 | Beckering Construction | W912JB15C2007 | 5.826 | 5.934 | 2015-05-07 | 2016-05-06 | 2016-05-14 | 2016-05-06 | 0.08
2015-07-31 | 2015 | Air National Guard | Major construction | PENNSYLVANIA | UNITED STATES | ZAWA159061 | RPA Operations Center |  | 2015-03-01 | 2015-06-30 | Senate Builders | W912KC10D00170029 | 4.1 | 4.185 |  |  | 2016-02-25 | 2016-01-26 | 0.05
2015-07-31 | 2008 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 54785 | Child Development Center |  | 2010-12-13 | 2011-08-05 | ASSET Group, Inc. | W9127S-11-C-6011 | 7835 | 7946 | 2011-09-23 | 2015-07-09 | 2013-01-25 | 2014-12-21 | 0.98
2015-07-31 | 2008 | Army Active | Major Military Construction |  | KOREA, SOUTH | 58784 | Barracks Complex |  | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32469 | 35334 | 2008-04-22 |  | 2014-09-07 | 2015-06-09 | 0.96
2015-07-31 | [8 empty] | 2012-02-02 | 2008-03-31 | Shinsung Engr. & Const. Co., Ltd. | W912UM-08-C-0011 | 15961 | 559
2015-07-31 | [8 empty] | 2012-02-02 | 2009-01-29 | Hanwha Engr. & Corporation Co., Ltd. | W912UM-09-C-0009 | 17815 | 18941
2015-07-31 | [8 empty] | 2012-02-02 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | W912UM-12-C-0057 | 5458 | 6193
2015-07-31 | 2008 | Army Active | Major Military Construction |  | BULGARIA | 63714 | Base Camp |  | 2008-06-20 | 2008-09-17 | Bilfinger Berger SE Sede Secondaria Italia | W912GB-08-C-0031 | 47980 | 47574 | 2008-11-03 | 2015-06-08 | 2014-09-03 | 2015-01-01 | 0.95
2015-07-31 | [8 empty] | 2008-06-20 | 2012-07-30 | PLANEX Ltd. | W912GB-12-D-0030 | 3904 | 5633
2015-07-31 | 2009 | Army Active | Major Military Construction |  | GERMANY | 53874 | Child Youth Services Center |  | 2009-07-31 | 2012-05-22 | LBB Kaiserslautern | W912GB-09-C-0036 | 5289 | 6145 | 2012-08-14 | 2014-12-01 | 2014-03-19 | 2014-04-11 | 0.98
2015-07-31 | 2009 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60859 | Water Treatment Plant |  | 2008-12-04 | 2009-05-13 | Cushman Contracting Corporation | W91238-09-C-0009 | 4795 | 6425 | 2009-06-17 | 2011-07-24 | 2010-12-09 | 2014-10-31 | 1
2015-07-31 | 2009 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66725 | Ballistic Evaluation Facility Ph 1 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7202 | 7661 | 2012-12-04 |  | 2014-06-04 | 2015-05-27 | 0.69
2015-07-31 | 2009 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67579 | Add/Alt Army Reserve Center |  | 2009-02-19 | 2009-06-18 | E. W. Howell Company, LLC | W912QR-09-C-0040 | 15494 | 16532 | 2009-07-21 | 2015-06-26 | 2011-07-11 | 2014-01-06 | 1
2015-07-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68786 | Brigade Complex |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 26656 | 30818 | 2011-04-15 | 2015-03-31 | 2014-03-14 | 2014-10-31 | 0.99
2015-07-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68821 | Battalion Complex |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 31084 | 36116 | 2011-04-15 | 2015-03-31 | 2014-03-14 | 2014-10-31 | 0.97
2015-07-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68822 | Battalion Complex |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 9840 | 11626 | 2011-04-15 | 2015-03-31 | 2014-03-14 | 2014-10-31 | 1 | 12682 | 68866
2015-07-31 | 2009 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 69199 | Unit Operations Facilities |  | 2010-07-15 | 2010-09-29 | Bristol Design Build Services, LLC | W912HN-08-D-0027 | 7687 | 7968 | 2010-11-03 | 2014-10-01 | 2014-08-22 | 2014-08-22 | 0.99
2015-07-31 | [8 empty] | 2010-07-15 | 2010-09-27 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 4321 | 4496
2015-07-31 | [8 empty] | 2010-07-15 | 2013-09-30 | Tunista Construction, LLC | W9126G-13-C-0080 | 605 | 622
2015-07-31 | [8 empty] | 2010-07-15 | 2010-09-24 | The Davis Group, Inc. | W912HN-08-D-0037 | 8333 | 8367
2015-07-31 | [8 empty] | 2010-07-15 | 2011-07-06 | Q.B.S., Inc. | W912HN-08-D-0038 | 6876 | 7112
2015-07-31 | 2009 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 69224 | Warrior in Transition (WT) Complex |  | 2009-07-21 | 2009-09-16 | M.A. Mortenson Company | W9126G-08-D-0048 | 51973 | 53657 | 2009-11-20 | 2015-07-01 | 2014-09-12 | 2015-04-30 | 1
2015-07-31 | [8 empty] | 2009-07-21 | 2011-03-24 | Doyon Project Services LLC | W9126G-11-C-0015 | 19863 | 17754
2015-07-31 | [8 empty] | 2009-07-21 | 2013-07-03 | Kevcon Inc. | W912DW-10-D-1016 | 3177 | 3387
2015-07-31 | [8 empty] | 2009-07-21 | 2013-09-03 | Doyon Management Services, LLC | W912DW-13-C-0043 | 2991 | 3227
2015-07-31 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69308 | Infrastructure Expansion |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 60385 | 66324 | 2011-04-15 | 2015-03-31 | 2014-03-14 | 2014-10-31 | 0.97
2015-07-31 | 2009 | Army Active | Major Military Construction |  | AFGHANISTAN | 72125 | SOF Alpha Ramp Facilities |  | 2009-11-05 | 2010-01-30 | ALMCO Limited | W912ER-10-C-0013 | 9048 | 3421 | 2010-03-17 | 2014-11-23 | 2013-08-13 | 2014-07-26 | 0.9
2015-07-31 | [8 empty] | 2009-11-05 | 2012-08-23 | Prime Projects Int'l (Const) Limited | W912ER-12-C-0040 | 5739 | 8416
2015-07-31 | 2010 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 58625 | Satellite Communications Facility |  | 2009-10-09 | 2010-02-05 | Harkins Builders, Inc. | W912DR-10-C-0068 | 11717 | 19350 | 2010-03-06 |  | 2012-09-01 | 2015-11-11 | 1
2015-07-31 | 2010 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 65133 | Brigade Complex |  | 2010-05-04 | 2010-06-17 | TEPA EC, LLC | W912HN-08-D-0022 | 9882 | 11570 | 2010-04-29 | 2015-04-17 | 2015-03-08 | 2015-04-20 | 0.99
2015-07-31 | [8 empty] | 2010-05-04 | 2010-03-16 | MW Builders Inc. | W9126G-08-D-0044 | 9389 | 9420
2015-07-31 | [8 empty] | 2010-05-04 | 2011-07-15 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 13542 | 15413
2015-07-31 | [8 empty] | 2010-05-04 | 2014-09-04 | Zieson Construction Company, LLC | W912DQ-13-D-4002 | 359 | 362
2015-07-31 | [8 empty] | 2010-05-04 | 2010-05-20 | McTech Corporation | W912HN-08-D-0026 | 6114 | 6030
2015-07-31 | 2010 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 66011 | Forensic Lab |  | 2010-04-28 | 2010-07-16 | Odyssey International, Inc. | W912HN-10-C-0044 | 7034 | 7653 | 2010-08-23 | 2015-05-27 | 2015-06-13 | 2015-06-13 | 1
2015-07-31 | [8 empty] | 2010-04-28 | 2014-09-28 | Trend Construction, Inc. | W912HN-12-D-0030 | 696 | 696
2015-07-31 | 2010 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 66545 | General Purpose Storage Building |  | 2010-05-17 | 2010-09-22 | Anderson Drace Joint Venture | W912BV-10-C-2007 | 11779 | 12311 | 2010-11-22 | 2012-06-01 | 2015-09-22 | 2015-09-22 | 0.96
2015-07-31 | [8 empty] | 2010-05-17 | 2012-05-16 | Easky Construction, LLC | W912BV-09-D-2019 | 757 | 757
2015-07-31 | [8 empty] | 2010-05-17 | 2014-06-16 | Red Cedar Enterprises, Inc. | W912BV-13-D-0011 | 1581 | 1495
2015-07-31 | 2010 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66726 | Ballistic Evaluation Facility, Ph 2 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757 | 8982 | 2012-12-04 |  | 2014-06-04 | 2015-05-27 | 0.77
2015-07-31 | 2010 | Army Active | Major Military Construction | ARKANSAS | UNITED STATES | 67106 | Fuse & Detonator Magazine, Depot Level |  | 2009-10-16 | 2010-01-22 | Carson & Associates, Inc. | W9127S-10-C-6008 | 18457 | 21432 | 2010-02-22 | 2013-01-31 | 2012-02-22 | 2015-01-20 | 1
2015-07-31 | 2010 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69150 | Training Battalion Complex |  | 2009-11-24 | 2010-02-19 | Walbridge Aldinger Company | W912HN-07-D-0054 | 12239 | 13951 | 2010-05-12 | 2011-12-21 | 2015-01-26 | 2015-07-15 | 0.99
2015-07-31 | [8 empty] | 2009-11-24 | 2012-08-23 | Brasfield & Gorrie LLC | W912HN-10-D-0046 | 21400 | 52595
2015-07-31 | 2010 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 69417 | Training Battalion Complex |  | 2009-11-03 | 2010-06-24 | Balfour Beatty Construction, LLC | W91236-10-C-0058 | 43614 | 50094 | 2010-07-27 | 2015-03-16 | 2013-06-03 | 2015-02-18 | 1
2015-07-31 | [8 empty] | 2009-11-03 | 2010-09-24 | BL Harbert International, LLC | W91278-07-D-0042 | 3800 | 3875
2015-07-31 | 2010 | Army Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | 69430 | Army Reserve Center/Land |  | 2011-07-28 | 2011-09-29 | Lobar Inc. | W912QR-11-C-0062 | 18388 | 20326 | 2012-01-18 |  | 2013-11-08 | 2015-06-12 | 0.96
2015-07-31 | 2010 | Army Reserve | Major Military Construction | CONNECTICUT | UNITED STATES | 69461 | Army Reserve Center/Land |  | 2014-02-11 | 2014-07-10 | Carothers Construction, Inc. | W912QR-14-C-0024 | 13543 | 17567 | 2011-11-29 |  | 2015-12-21 | 2016-01-29 | 0.45
2015-07-31 | [8 empty] | 2014-02-11 | 2011-08-31 | Korte-Fusco Joint Venture | W912QR-11-C-0037 | 0 | 0
2015-07-31 | 2010 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 69471 | Army Reserve Center/Land |  | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | W912QR-12-C-0022 | 16009 | 16320 | 2012-05-22 |  | 2013-09-24 | 2013-10-06 | 0.86
2015-07-31 | 2010 | Army Reserve | Major Military Construction | PUERTO RICO | PUERTO RICO | 69568 | Army Reserve Center/Land |  | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | W912QR-11-C-0046 | 12356 | 12771 | 2011-11-15 | 2015-03-11 | 2013-08-06 | 2013-11-16 | 0.94
2015-07-31 | 2010 | Army Active | Military Family Housing |  | GERMANY | 71421 | Family Housing Replacement Construction |  | 2010-08-01 | 2015-01-06 | LBB Niederlassung Idar-Oberstein | W912GB-10-C-0042 | 18945 | 18945 | 2015-04-07 |  | 2017-04-23 | 2017-04-23 | 0.03
2015-07-31 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses |  | 2013-06-21 | 2013-09-27 | Contrack International, Inc. | W912ER-13-C-0032 | 49413 | 55213 | 2013-10-25 |  | 2015-10-30 | 2015-10-30 | 0.54 | 11339 | 58925, 62783
2015-07-31 | [8 empty] | 2013-06-21 | 2014-04-03 | Contrack International, Inc. | W912ER-14-C-0011 | 6749 | 6749
2015-07-31 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 71488 | Coalition Operation Center |  | 2011-10-11 | 2011-12-14 | Ch2m Hill-Yuksel Joint Venture | W912ER-11-D-0008 | 39962 | 46679 | 2012-03-16 | 2015-06-29 | 2014-09-14 | 2015-10-07 | 0.98
2015-07-31 | [8 empty] | 2011-10-11 | 2014-08-30 | Inglett & Stubbs, International LTD | W5J9JE-14-P-0044 | 56 | 56
2015-07-31 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 72477 | USFOR-A Headquarters & Housing |  | 2011-03-28 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 47161 | 32389 | 2011-09-09 | 2015-03-18 | 2013-12-07 | 2014-11-10 | 0.97
2015-07-31 | 2010 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 74408 | Ft Lewis-McChord AFB Joint Access |  | 2013-02-12 | 2013-08-29 | TSS-Garco Joint Venture | W912DW-13-C-0040 | 7327 | 8538 | 2013-09-25 | 2015-05-04 | 2015-01-28 | 2015-05-15 | 0.99
2015-07-31 | 2010 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 75110 | Tactical Equipment Maintenance Facility |  | 2011-10-04 | 2012-01-26 | Leetex Construction LLC | W912QR-12-C-0010 | 9470 | 10447 | 2012-04-05 | 2015-01-30 | 2013-09-12 | 2014-01-10 | 0.96
2015-07-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 52269 | Barracks |  | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | W9128A-11-C-0016 | 25313 | 43715 | 2011-10-17 | 2014-12-01 | 2014-07-16 | 2015-05-22 | 0.97 | 5750 | 65374, 78054
2015-07-31 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex |  | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | W912HN-11-C-0013 | 15752 | 16699 | 2011-11-21 | 2015-05-18 | 2014-01-29 | 2015-04-18 | 0.99
2015-07-31 | [8 empty] | 2011-05-24 | 2011-12-09 | H-S Joint Venture, LLC | W91236-10-D-0011 | 10469 | 10491
2015-07-31 | [8 empty] | 2011-05-24 | 2011-09-16 | Atlantic Marine Construction Company, Inc | W912HN-07-D-0025 | 1158 | 1210
2015-07-31 | [8 empty] | 2011-05-24 | 2013-04-15 | Barnhill Contracting Company | W912HN-09-D-0045 | 68 | 68
2015-07-31 | [8 empty] | 2011-05-24 | 2011-09-19 | Polote Corp. | W912HN-10-D-0061 | 10869 | 11295
2015-07-31 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 53789 | Advanced Individual Training Barracks |  | 2013-07-23 | 2013-09-30 | Halbert Construction Company, Inc. | W91238-13-C-0012 | 18519 | 27700 | 2013-10-22 |  | 2015-01-05 | 2016-02-17 | 0.08
2015-07-31 | 2011 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 53794 | Trainee Barracks Complex, Ph 1 |  | 2011-07-15 | 2011-08-30 | W. G. YATES & SONS CONSTRUCTION COMPANY | W9126G-09-D-0018 | 20250 | 25608 | 2012-01-04 | 2014-11-25 | 2013-08-04 | 2014-12-18 | 1
2015-07-31 | [8 empty] | 2011-07-15 | 2012-04-16 | H-S JOINT VENTURE, LLC | W91236-10-D-0011 | 10187 | 11210
2015-07-31 | [8 empty] | 2011-07-15 | 2012-07-03 | LIFECYCLE CONSTRUCTION SERVICES | W912HP-11-D-0016 | 2731 | 2757
2015-07-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 56024 | Flood Mitigation |  | 2012-06-29 | 2012-09-25 | Nan, Inc. | W9128A-12-C-0019 | 21105 | 22708 | 2012-10-17 |  | 2014-10-14 | 2015-08-29 | 0.88
2015-07-31 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 57317 | Battalion Complex |  | 2011-05-24 | 2011-09-19 | Polote Corp. | W912HN-10-D-0061 | 3908 | 4025 | 2011-11-21 | 2014-04-30 | 2014-01-29 | 2015-01-09 | 0.99
2015-07-31 | [8 empty] | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | W912HN-11-C-0013 | 13850 | 14717
2015-07-31 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 57595 | Wideband SATCOM Operations Center |  | 2015-05-07 | 2011-08-08 | Lebolo-Watts Constructors 01 JV LLC | W912DR-11-C-0033 | 18392 | 21010 | 2011-09-06 | 2014-04-15 | 2015-12-22 | 2015-12-22 | 0.95
2015-07-31 | [8 empty] | 2015-05-07 | 2015-06-01 | Argo Systems LLC | W912DR-14-D-0019 | 734 | 734
2015-07-31 | 2011 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 57735 | Infantry Squad Battle Course |  | 2011-12-21 | 2012-04-25 | Dynamic Construction of Northern New York, LLC | W912DS-12-C-0008 | 6675 | 6946 | 2012-08-26 | 2014-10-21 | 2014-02-22 | 2014-10-21 | 1
2015-07-31 | 2011 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 59044 | Science Facility, Ph 2 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270 | 115589 | 2011-11-17 |  | 2015-11-14 | 2015-11-14 | 0.89
2015-07-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 59434 | Physical Fitness Center |  | 2010-12-01 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0040 | 14482 | 15200 | 2012-11-30 | 2014-12-18 | 2014-11-28 | 2014-11-28 | 0.96
2015-07-31 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60285 | General Instruction Building |  | 2010-10-07 | 2011-05-18 | RQ Construction, LLC | W91238-11-C-0005 | 29886 | 33123 | 2011-06-07 | 2014-09-08 | 2015-07-14 | 2015-07-14 | 0.99
2015-07-31 | [8 empty] | 2010-10-07 | 2014-12-09 | Romero General Construction Corp. | W91238-13-D-0009 | 441 | 441
2015-07-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 60555 | Information Processing Center |  | 2010-12-16 | 2012-05-14 | Hessisches Baumanagement Wiesbaden | W912GB-08-C-0005 | 28606 | 33015 | 2012-06-18 |  | 2014-06-01 | 2014-11-07 | 0.97
2015-07-31 | 2011 | Army Active | Major Military Construction |  | HONDURAS | 61383 | Barracks |  | 2011-05-18 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | W91278-11-C-0028 | 15147 | 15633 | 2012-01-10 | 2015-02-13 | 2014-01-09 | 2014-09-24 | 0.98
2015-07-31 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 61453 | Replace Fire Station |  | 2012-08-06 | 2013-05-23 | TMG SERVICES, INC. Linda Frazier | W912DR-13-C-0030 | 6189 | 6582 | 2013-06-05 | 2015-06-15 | 2014-11-27 | 2015-07-16 | 0.95
2015-07-31 | 2011 | Army Active | Major Military Construction | FLORIDA | UNITED STATES | 61533 | Command and Control Facility |  | 2011-05-10 | 2011-07-29 | Carothers Construction, Inc. | W91278-07-D-0026 | 34508 | 44851 | 2011-09-20 | 2014-03-07 | 2014-10-06 | 2014-10-06 | 1
2015-07-31 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W91238-14-C-0040 | 38915 | 38915 | 2011-09-21 |  | 2016-06-30 | 2016-06-30 | 0.11
2015-07-31 | [8 empty] | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV | W91238-11-C-0010 | 34801 | 3567
2015-07-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64760 | Training Aids Center |  | 2012-06-29 | 2012-09-19 | SRB International LLC | W9128A-12-C-0013 | 13310 | 13325 | 2012-10-31 | 2015-07-20 | 2014-08-17 | 2014-09-26 | 0.9
2015-07-31 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 65650 | Command and Control Facility, Ph 1 |  | 2011-11-04 | 2012-02-28 | Niking Corporation | W9128A-12-C-0003 | 46780 | 49535 | 2012-04-03 |  | 2014-04-23 | 2015-02-20 | 0.98
2015-07-31 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 65726 | MOUT Collective Training Fac |  | 2011-11-14 | 2012-01-03 | Jordan-Versar, LLC | W91236-08-D-0056 | 55547 | 57539 | 2012-01-20 | 2013-10-25 | 2013-10-21 | 2014-10-24 | 0.99 | 735 | 53789
2015-07-31 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65793 | Indoor Firing Range |  | 2011-06-17 | 2011-09-21 | John C. Grimberg Co., Inc. | W912DR-11-C-0018 | 7241 | 8409 | 2011-10-13 | 2014-10-15 | 2013-04-05 | 2014-08-11 | 1
2015-07-31 | [8 empty] | 2011-06-17 | 2011-09-29 | Aisow Technologies Corporation | W912DR-08-D-0036 | 306 | 316
2015-07-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66465 | Confinement Facility |  | 2012-03-06 | 2013-03-07 | LBB Kaiserslautern | W912GB-09-C-0039 | 9933 | 11010 | 2013-04-29 | 2014-11-20 | 2014-12-15 | 2014-12-19 | 0.99
2015-07-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66595 | Barracks Complex |  | 2011-09-08 | 2015-01-19 | LBB Kaiserslautern | W912GB-09-C-0014 | 30046 | 30051 | 2015-03-23 |  | 2017-09-28 | 2017-09-28 | 0.06
2015-07-31 | 2011 | Army Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 66717 | Military Working Dog Kennel |  | 2013-05-30 | 2013-08-05 | Sunlight Enterprises Co., Inc | W9126G-13-C-2005 | 1780 | 1925 | 2013-08-27 | 2015-03-26 | 2014-07-22 | 2014-08-29 | 0.99
2015-07-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66834 | Vehicle Maintenance Shop |  | 2010-12-01 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 16286 | 20380 | 2011-12-12 |  | 2013-12-18 | 2015-07-31 | 0.96
2015-07-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 67194 | Simulations Center |  | 2010-11-18 | 2012-03-13 | Blackhawk Ventrues, LLC | W9126G-09-D-0093 | 14554 | 15295 | 2012-04-10 | 2015-02-05 | 2013-08-09 | 2013-12-30 | 0.99
2015-07-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68074 | Construct New ACP |  | 2013-05-30 | 2013-08-12 | Hessisches Baumanagement Wiesbaden | W912GB-09-C-0059 | 6768 | 7869 | 2014-03-05 | 2015-01-09 | 2014-12-12 | 2014-12-12 | 1
2015-07-31 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68866 | Sensitive Compartmented Information Fac |  | 2012-05-22 | 2013-01-23 | ECC International LLC | W912GB-13-C-0003 | 87011 | 88580 | 2013-02-13 |  | 2015-09-19 | 2015-10-31 | 0.35
2015-07-31 | [8 empty] | 2012-05-22 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | W912GB-11-D-0036 | 7198 | 8645
2015-07-31 | [8 empty] | 2012-05-22 | 2014-06-24 | OBG Engineering GmbH & Co. KG | W912GB-14-D-0019 | 90 | 90
2015-07-31 | 2011 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 69421 | Army Reserve Center/Land |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4504 | 4564 | 2012-08-21 |  | 2014-03-21 | 2014-05-01 | 0.26
2015-07-31 | 2011 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69599 | Army Reserve Center/Land |  | 2012-07-25 | 2012-09-25 | J. Kokolakis Contracting, Inc. | W912QR-12-C-0057 | 12465 | 13303 | 2012-10-25 | 2015-02-20 | 2014-05-12 | 2014-05-12 | 0.98
2015-07-31 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69830 | Aviation Unit Operations Complex |  | 2010-12-23 | 2011-06-22 | Sauer Inc. d/b/a Sauer Southeast | W91278-07-D-0030 | 27688 | 29236 | 2011-07-27 | 2015-04-28 | 2015-08-01 | 2015-08-25 | 0.97
2015-07-31 | [8 empty] | 2010-12-23 | 2014-05-02 | Lunacon Engineering Group Corp | W912HN-13-D-0004 | 1073 | 1100
2015-07-31 | [8 empty] | 2010-12-23 | 2015-01-09 | SILER EXCAVATING LLC | W912HN-14-D-0010 | 54 | 54
2015-07-31 | 2011 | Army Reserve | Major Military Construction | VIRGINIA | UNITED STATES | 70641 | Army Reserve Center/Land |  | 2011-08-18 | 2011-11-23 | Anthony & Gordon Construction Co, Inc. | W912QR-12-C-0004 | 13345 | 13883 | 2012-01-12 | 2014-10-30 | 2013-05-06 | 2013-09-25 | 0.97
2015-07-31 | 2011 | Army Reserve | Major Military Construction | IOWA | UNITED STATES | 70654 | Army Reserve Center |  | 2011-11-15 | 2012-03-14 | The Vertex Companies | W912QR-12-C-0014 | 9013 | 9189 | 2012-04-09 | 2015-04-15 | 2013-08-12 | 2013-11-13 | 0.95
2015-07-31 | 2011 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71119 | Training Aids Center |  | 2011-06-03 | 2011-08-03 | PENTACON, LLC | W912HP-11-D-0007 | 15000 | 15992 | 2011-09-08 | 2014-10-14 | 2013-03-01 | 2014-12-11 | 1
2015-07-31 | 2011 | Army Active | Military Family Housing |  | GERMANY | 71422 | Family Housing Replacement Construction |  | 2011-07-18 | 2011-09-14 | LBB Niederlassung Idar-Oberstein | W912GB-09-C-0007 | 34935 | 34935 | 2012-01-12 |  | 2012-02-23 | 2012-02-23 | 0.02
2015-07-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex |  | 2011-01-24 | 2011-09-30 | JAMA Constructors | W912HN-11-D-0044 | 6573 | 8565 | 2011-07-13 | 2015-01-14 | 2014-01-21 | 2015-01-05 | 1
2015-07-31 | [8 empty] | 2011-01-24 | 2011-06-01 | Sundt Construction Inc | W9126G-09-D-0004 | 6819 | 6957
2015-07-31 | [8 empty] | 2011-01-24 | 2011-09-12 | McGoldrick Construction Services, Corp. | W9126G-09-D-0098 | 3097 | 3448
2015-07-31 | [8 empty] | 2011-01-24 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 8780 | 9297
2015-07-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71465 | Company Operations Facilities |  | 2011-03-21 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 3049 | 3463 | 2011-07-13 | 2014-04-14 | 2013-11-11 | 2014-12-12 | 1
2015-07-31 | [8 empty] | 2011-03-21 | 2011-06-01 | Sundt Construction Inc | W9126G-09-D-0004 | 289 | 363
2015-07-31 | 2011 | Army Active | Major Military Construction |  | AFGHANISTAN | 71604 | Eastside Utilities Infrastructure |  | 2012-05-30 | 2012-09-04 | ANHAM-ICSS Joint Venture | W912ER-11-D-0003 | 26827 | 25203 | 2012-10-18 | 2015-03-13 | 2014-06-05 | 2015-01-31 | 0.99
2015-07-31 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex |  | 2012-12-19 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 11652 | 12096 | 2011-07-13 | 2014-05-05 | 2015-01-30 | 2015-06-28 | 0.85
2015-07-31 | [8 empty] | 2012-12-19 | 2011-06-01 | Sundt Construction Inc | W9126G-09-D-0004 | 6608 | 6783
2015-07-31 | [8 empty] | 2012-12-19 | 2013-09-30 | Bristol General Contractors, LLC | W9126G-13-C-0061 | 15175 | 15233
2015-07-31 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72324 | Trainee Barracks Ph 2 |  | 2010-10-26 | 2013-01-10 | Caddell Construction | W912HN-10-D-0044 | 20847 | 21398 | 2011-08-18 | 2014-12-15 | 2014-05-08 | 2014-09-12 | 0.98
2015-07-31 | [8 empty] | 2010-10-26 | 2011-09-09 | Leebcor Services, LLC | W91236-10-D-0020 | 6994 | 7151
2015-07-31 | [8 empty] | 2010-10-26 | 2011-09-29 | Anthony and Gordon Construction Company, Inc | W9126G-11-D-0075 | 7936 | 7952
2015-07-31 | [8 empty] | 2010-10-26 | 2011-08-04 | Atlantic Marine Construction Company, Inc | W912HN-07-D-0024 | 1614 | 1649
2015-07-31 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72457 | Training Battalion Complex, Ph 2 |  | 2011-07-20 | 2011-09-29 | IAP Design-Build, LLC | W912HN-10-D-0054 | 11084 | 22116 | 2011-10-13 | 2015-04-24 | 2015-05-11 | 2015-05-11 | 0.99
2015-07-31 | [8 empty] | 2011-07-20 | 2014-10-24 | Turner Strategic Technologies, LLC | W912HN-13-D-0013 | 706 | 706
2015-07-31 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex |  | 2011-05-02 | 2013-01-22 | Garco Construction, Inc. | W912DW-13-C-0020 | 36247 | 38940 | 2011-10-12 |  | 2015-10-24 | 2015-10-24 | 0.96
2015-07-31 | [8 empty] | 2011-05-02 | 2011-09-28 | Innovative Technical Solutions, Inc. | W9126G-08-D-0085 | 8894 | 11287
2015-07-31 | [8 empty] | 2011-05-02 | 2014-04-30 | Maanilaq Services LLC | W912DW-14-C-0011 | 3373 | 3366
2015-07-31 | [8 empty] | 2011-05-02 | 2014-09-26 | Wm. Dickson Company | W912DW-14-C-0028 | 1628 | 2063
2015-07-31 | 2011 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 74220 | Army Reserve Center/Land |  | 2011-05-19 | 2011-09-23 | Liberty Mutual Insurance Company | W912QR-11-C-0048 | 8916 | 8956 | 2011-10-21 | 2014-11-13 | 2013-03-24 | 2013-09-17 | 1
2015-07-31 | 2011 | Army Active | Unspecified Minor Military Construction | OHIO | UNITED STATES | 74757 | Fire Alarm System |  | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | W912QR-12-C-0050 | 1763 | 3083 | 2012-09-05 | 2015-07-31 | 2013-08-01 | 2015-04-15 | 0.96
2015-07-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 1235 | Physical Fitness Facility |  | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23139 | 23149 | 2012-07-12 |  | 2014-04-10 | 2014-05-27 | 0.84
2015-07-31 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 2728 | Physical Fitness Facility |  | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 11660 | 11694 | 2012-03-29 | 2014-11-24 | 2016-09-09 | 2016-09-09 | 0.88
2015-07-31 | [8 empty] | 2011-12-09 | 2014-07-02 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 727 | 727
2015-07-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility |  | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603 | 13268 | 2013-01-24 |  | 2014-07-18 | 2015-08-09 | 0.68
2015-07-31 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 17220 | Fire Station |  | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12623 | 12866 | 2013-11-06 |  | 2015-11-11 | 2015-12-24 | 0.41
2015-07-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 20697 | Chapel |  | 2012-01-27 | 2012-08-30 | Liberty Mutual Insurance Company | W912BV-12-C-0018 | 13000 | 13099 | 2012-09-20 |  | 2014-01-28 | 2014-01-28 | 0.75
2015-07-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 53637 | Brigade Complex, Ph 2 |  | 2012-02-21 | 2012-06-14 | Archer Western Contractors, Ltd | W9126G-08-D-0046 | 14691 | 14795 | 2012-06-29 | 2015-03-15 | 2014-06-11 | 2015-03-12 | 0.99
2015-07-31 | [8 empty] | 2012-02-21 | 2012-06-07 | Bristol General Contractors, LLC | W912DW-12-C-0032 | 19375 | 21818
2015-07-31 | [8 empty] | 2012-02-21 | 2012-11-09 | Megen Construction Co., INC. | W912HN-11-D-0047 | 14398 | 14928
2015-07-31 | 2012 | Army Active | Major Military Construction | UTAH | UNITED STATES | 55823 | Life Sciences Test Facility Addition |  | 2012-04-12 | 2012-07-26 | Big-D Construction Corp | W91238-12-C-0024 | 22609 | 29924 | 2012-08-29 |  | 2015-02-15 | 2015-10-26 | 0.97
2015-07-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 55985 | Chapel |  | 2012-01-10 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15916 | 16198 | 2013-11-21 |  | 2016-03-23 | 2016-03-23 | 0.42
2015-07-31 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 56425 | General Instruction Building |  | 2012-08-20 | 2012-09-29 | Souza Construction, Inc. | W91238-10-D-0010 | 2996 | 3163 | 2012-11-06 | 2015-01-02 | 2013-11-06 | 2014-05-11 | 0.9
2015-07-31 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 57508 | Information Dominance Center, Ph 1 |  | 2013-03-15 | 2013-07-22 | Hensel Phelps Construction Co. | W912DR-13-C-0035 | 39700 | 44660 | 2013-08-19 | 2015-02-17 | 2015-03-12 | 2015-10-27 | 0.83
2015-07-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 57594 | Satellite Communications Center |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565 | 28245 | 2014-03-14 |  | 2015-10-05 | 2015-12-19 | 0.64
2015-07-31 | 2012 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 58005 | Ammunition Supply Point |  | 2011-12-22 | 2012-04-17 | Black Horse Group LLC | W912DS-09-D-0004 | 4681 | 4801 | 2012-05-18 | 2014-11-04 | 2013-08-15 | 2014-11-14 | 1
2015-07-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 58046 | Operational Readiness Training Cplx, Ph 1 |  | 2012-06-29 | 2013-04-01 | TSS-Garco Joint Venture | W912DW-12-C-0043 | 16416 | 16330 | 2013-05-21 |  | 2014-11-12 | 2015-02-08 | 0.95
2015-07-31 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58537 | Reception Station, Ph 1 |  | 2011-11-21 | 2012-05-23 | Zachry Federal Construction Corporation | W912BV-12-C-0010 | 32234 | 33040 | 2012-06-15 | 2014-12-02 | 2014-03-26 | 2014-05-25 | 0.97
2015-07-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 58925 | Satellite Communications Center |  | 2012-03-12 | 2014-09-05 | DBA ARGE JV PGWM NETCOM | W912GB-14-C-0037 | 29010 | 29233 | 2014-10-16 |  | 2016-07-07 | 2016-07-07 | 0.21
2015-07-31 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 59148 | Deployment Support Facility |  | 2012-02-01 | 2012-03-23 | Alexander-Weitz JV | W912DQ-11-D-4012 | 3901 | 3998 | 2012-04-10 | 2014-08-04 | 2014-10-10 | 2014-10-10 | 1
2015-07-31 | [8 empty] | 2012-02-01 | 2014-05-15 | Zieson Construction Company, LLC | W912DQ-13-D-4002 | 9 | 9
2015-07-31 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 59581 | Centralized Wash Facility |  | 2011-10-13 | 2012-01-27 | Watts Constructors, LLC | W9128A-12-C-0001 | 28300 | 30397 | 2012-02-08 | 2015-03-02 | 2013-12-14 | 2014-09-16 | 0.99
2015-07-31 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 61211 | Chapel |  | 2011-11-22 | 2012-05-31 | TMG Services, Inc. | W912DQ-12-C-4005 | 7090 | 7300 | 2012-06-29 | 2014-10-27 | 2014-10-28 | 2014-10-28 | 0.98 | 620 | 55121
2015-07-31 | [8 empty] | 2011-11-22 | 2014-08-29 | Zieson Construction Company, LLC | W912DQ-13-D-4002 | 20 | 20
2015-07-31 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 61515 | Physical Fitness Facility |  | 2011-10-19 | 2012-11-07 | Bristol General Contractors, LLC | W911KB-13-C-0002 | 21813 | 22240 | 2012-07-03 |  | 2014-12-06 | 2015-06-14 | 0.88
2015-07-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 61842 | Access Control Point |  | 2012-03-13 | 2015-04-20 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0004 | 11607 | 9720 | 2015-05-11 |  | 2016-12-01 | 2016-12-01 | 0.08
2015-07-31 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 62657 | Water Treatment Plant |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100113 | 100314 | 2012-10-19 |  | 2015-10-19 | 2016-01-12 | 0.85
2015-07-31 | 2012 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 62955 | Trainee Barracks Complex, Ph 2 |  | 2012-02-16 | 2012-03-28 | CLARK CONSTRUCTION GROUP LLC | W9126G-11-D-0049 | 44267 | 48090 | 2012-07-23 | 2014-10-27 | 2014-01-14 | 2014-11-06 | 0.99 | 8600 | 80066
2015-07-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex |  | 2012-08-14 | 2012-09-21 | 3D Contracting Inc. | W912DW-12-C-0046 | 14649 | 15247 | 2012-07-25 | 2015-04-30 | 2015-04-08 | 2015-09-30 | 0.93
2015-07-31 | [8 empty] | 2012-08-14 | 2012-06-28 | M.A. Mortenson Company | W9126G-08-D-0045 | 19332 | 19731
2015-07-31 | [8 empty] | 2012-08-14 | 2013-01-03 | TSS-Garco Joint Venture | W912DW-13-C-0019 | 8912 | 9125
2015-07-31 | [8 empty] | 2012-08-14 | 2013-09-26 | MEGEN Construction Company, Inc. | W912HN-11-D-0047 | 7295 | 8546
2015-07-31 | 2012 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 64365 | Vehicle Maintenance Facility |  | 2012-02-03 | 2012-08-23 | KCI Construction Company | W912DQ-12-C-4009 | 30970 | 32860 | 2012-09-18 | 2014-09-19 | 2014-08-25 | 2015-11-30 | 0.83
2015-07-31 | [8 empty] | 2012-02-03 | 2012-11-07 | Arch Insurance Company | W912DQ-11-D-4011 | 8541 | 8804
2015-07-31 | [8 empty] | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | W912DQ-12-D-4006 | 2493 | 4123
2015-07-31 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex |  | 2011-12-16 | 2012-03-23 | Blackhawk Ventures, LLC | W9126G-09-D-0093 | 10283 | 11234 | 2012-05-15 | 2014-11-19 | 2014-04-02 | 2015-07-02 | 0.98
2015-07-31 | [8 empty] | 2011-12-16 | 2012-08-17 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 11857 | 12236
2015-07-31 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 64939 | Applied Instruction Facility |  | 2012-06-20 | 2012-09-24 | Grimberg/Amatea JV | W912DR-12-C-0023 | 30554 | 35586 | 2012-11-20 |  | 2014-11-20 | 2016-01-04 | 0.89
2015-07-31 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64967 | Child Development Center |  | 2011-10-06 | 2012-02-27 | 57 Builders, Ltd. | W9128A-12-C-0002 | 9573 | 10828 | 2012-03-23 | 2015-07-31 | 2013-12-13 | 2015-09-30 | 0.94
2015-07-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex |  | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503 | 39961 | 2012-09-05 |  | 2014-11-28 | 2015-05-30 | 0.9
2015-07-31 | [8 empty] | 2012-01-05 | 2013-01-07 | Turner Strategic Technologies, LLC | W91236-13-C-0017 | 8195 | 8452
2015-07-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 65602 | Brigade Headquarters |  | 2012-02-07 | 2012-03-30 | Komada, LLC | W9128F-12-C-0008 | 9947 | 11356 | 2012-04-18 | 2014-08-15 | 2015-02-08 | 2015-03-16 | 1 | 1700 | 66745
2015-07-31 | [8 empty] | 2012-02-07 | 2014-05-08 | HHI Corporation | W9128F-11-D-0026 | 147 | 184
2015-07-31 | [8 empty] | 2012-02-07 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 610 | 667
2015-07-31 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65755 | Brigade Complex |  | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30762 | 36912 | 2012-12-12 |  | 2015-12-12 | 2017-04-25 | 0.66
2015-07-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 |  | 2012-08-18 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775 | 14595 | 2012-09-17 |  | 2015-09-10 | 2016-04-01 | 0.9
2015-07-31 | [8 empty] | 2012-08-18 | 2013-08-02 | James Talcott Construction, Inc. | W912DW-10-D-1015 | 5769 | 6297
2015-07-31 | [8 empty] | 2012-08-18 | 2012-09-28 | Vet Industrial, Inc. | W912DW-10-D-1021 | 4980 | 5253
2015-07-31 | [8 empty] | 2012-08-18 | 2012-08-29 | Alutiiq Diversified Services, LLC | W912DW-12-C-0040 | 10525 | 12966
2015-07-31 | [8 empty] | 2012-08-18 | 2012-09-28 | Bristol General Contractors, LLC | W912DW-12-D-1018 | 1979 | 2354
2015-07-31 | [8 empty] | 2012-08-18 | 2013-12-24 | Burr-MZT Joint Venture | W912DW-14-C-0001 | 919 | 983
2015-07-31 | [8 empty] | 2012-08-18 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6814 | 7342
2015-07-31 | [8 empty] | 2012-08-18 | 2014-06-20 | Bristol General Contractors, LLC | W912DW-14-C-0015 | 5288 | 6058
2015-07-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 |  | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | W9126G-12-C-0015 | 40532 | 40941 | 2012-04-24 |  | 2014-06-02 | 2014-07-11 | 0.89
2015-07-31 | [8 empty] | 2011-12-24 | 2014-03-04 | Alamo City Constructors, Inc. | W9126G-10-D-0001 | 36 | 43
2015-07-31 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67113 | Aviation Complex, Ph 3A |  | 2011-07-15 | 2012-06-07 | Watterson Construction Company | W911KB-12-C-0008 | 70591 | 71467 | 2012-06-14 | 2014-11-10 | 2014-08-03 | 2014-10-09 | 1
2015-07-31 | 2012 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 67466 | Army Reserve Center/Land |  | 2012-05-16 | 2012-09-18 | Continental Casualty Company | W912QR-12-C-0055 | 16212 | 16472 | 2012-10-10 |  | 2014-03-19 | 2014-06-12 | 0.66
2015-07-31 | 2012 | Army Reserve | Major Military Construction | COLORADO | UNITED STATES | 67658 | Army Reserve Center |  | 2011-11-29 | 2012-04-16 | Liberty Mutual Insurance Company | W912QR-12-C-0028 | 10545 | 10690 | 2012-05-11 |  | 2013-10-18 | 2013-10-18 | 0.88
2015-07-31 | 2012 | Army Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 67672 | Army Reserve Center/Land |  | 2011-11-16 | 2012-03-29 | Group III Mgt. Inc | W912QR-12-C-0021 | 10123 | 11126 | 2012-05-21 | 2014-10-20 | 2013-09-23 | 2014-09-18 | 0.97
2015-07-31 | 2012 | Army Reserve | Major Military Construction | INDIANA | UNITED STATES | 67673 | Army Reserve Center |  | 2012-02-14 | 2012-05-15 | Hunt Construction Group | W912QR-12-C-0029 | 44568 | 48192 | 2012-05-30 | 2014-09-22 | 2015-01-29 | 2015-07-09 | 1
2015-07-31 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67691 | Army Reserve Center |  | 2011-11-16 | 2012-05-03 | SCMC, LLC | W912QR-12-C-0025 | 18167 | 19497 | 2012-06-01 | 2014-05-21 | 2015-01-04 | 2015-05-30 | 0.96
2015-07-31 | 2012 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67713 | Army Reserve Center |  | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | W912QR-12-C-0068 | 13454 | 15784 | 2012-10-18 |  | 2014-07-10 | 2015-11-23 | 0.92
2015-07-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69286 | Infrastructure |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008 | 8733 | 2012-08-20 |  | 2013-09-13 | 2013-09-27 | 0.74
2015-07-31 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69432 | Army Reserve Center |  | 2012-12-21 | 2013-03-06 | MACNAK KORTE DESIGN BUILD LLC | W912QR-13-C-0009 | 14338 | 14032 | 2013-04-15 | 2014-11-12 | 2014-07-29 | 2014-08-15 | 0.97 | 390 | 69422
2015-07-31 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69489 | Combat Aviation Brigade Complex, Ph 1 |  | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772 | 56358 | 2012-07-30 |  | 2015-05-27 | 2015-06-11 | 0.64
2015-07-31 | 2012 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 69501 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2011-12-16 | 2012-09-27 | Archer Western Federal JV | W912QR-12-C-0058 | 40397 | 45467 | 2012-11-05 | 2014-12-15 | 2014-09-06 | 2014-12-14 | 1 | 10000 | 66745
2015-07-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 69614 | Barracks |  | 2012-03-02 | 2013-03-27 | Staatliches Hochbauamt Amberg | W912GB-10-C-0043 | 17523 | 18299 | 2013-03-27 | 2015-03-06 | 2014-12-31 | 2015-03-15 | 0.89
2015-07-31 | 2012 | Army Active | Major Military Construction |  | GERMANY | 69615 | Barracks |  | 2012-01-03 | 2012-09-27 | Bauamt Amberg-Sulzbach | W912GB-10-C-0007 | 17669 | 17972 | 2012-10-10 | 2014-10-25 | 2014-08-27 | 2014-09-25 | 0.98 | 2210 | 66745
2015-07-31 | 2012 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 69745 | Trainee Barracks Complex, Ph 3 |  | 2011-12-16 | 2012-05-08 | Compton Construction Company, Inc. | W9126G-11-D-0076 | 7898 | 7918 | 2012-05-18 | 2013-11-22 | 2014-08-23 | 2014-12-17 | 1 | 690 | 66745
2015-07-31 | [8 empty] | 2011-12-16 | 2012-05-08 | Windamir Development, Inc | W9126G-12-C-0027 | 11839 | 0
2015-07-31 | [8 empty] | 2011-12-16 | 2013-02-21 | SOCO Contracting Company, INC. | W9126G-13-C-0014 | 11020 | 11385
2015-07-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69828 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-07-16 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 8830 | 8867 | 2014-08-27 |  | 2016-01-04 | 2016-01-13 | 0.48
2015-07-31 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-08-26 | 2014-01-07 | Law Company, Inc. | W912DQ-14-C-4003 | 20079 | 20395 | 2012-12-11 |  | 2015-07-31 | 2015-08-04 | 0.69
2015-07-31 | [8 empty] | 2013-08-26 | 2012-11-01 | Arch Insurance Company | W912DQ-11-D-4011 | 5933 | 6086
2015-07-31 | 2012 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69835 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2014-08-25 | 2014-12-05 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 30589 | 31584 | 2015-01-05 |  | 2016-02-29 | 2016-04-04 | 0.08
2015-07-31 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 71569 | Westside Utilities Infrastructure |  | 2012-08-24 | 2012-11-15 | Contrack International Inc. | W912ER-11-D-0009 | 11924 | 10056 | 2012-12-12 | 2014-12-20 | 2014-03-07 | 2014-09-01 | 0.99
2015-07-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 9669 | 10202 | 2012-06-22 |  | 2015-01-25 | 2015-03-30 | 0.96
2015-07-31 | [8 empty] | 2011-12-19 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3844 | 3844
2015-07-31 | [8 empty] | 2011-12-19 | 2013-12-04 | Solis Constructors, Inc | W9126G-14-C-0006 | 5786 | 5928
2015-07-31 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 72650 | Barracks |  | 2011-11-10 | 2012-02-24 | Samsung C&T Corporation | W912UM-12-C-0012 | 27593 | 28811 | 2012-02-24 |  | 2015-12-05 | 2015-11-26 | 0.9
2015-07-31 | [8 empty] | 2011-11-10 | 2012-02-27 | Hanmi C&E Co., LTD. | W912UM-11-D-0007 | 64 | 4
2015-07-31 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74067 | Construct Drainage System, Ph 3 |  | 2012-04-27 | 2012-08-15 | ANHAM-ICSS JV | W912ER-11-D-0003 | 19903 | 22734 | 2012-10-09 | 2015-02-17 | 2014-06-01 | 2014-12-28 | 1
2015-07-31 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74084 | Barracks, Ph 5 |  | 2011-12-05 | 2012-04-12 | Bryan 77 Construction JV | W912ER-11-D-0004 | 19331 | 14239 | 2012-06-08 | 2014-09-18 | 2014-04-19 | 2014-11-17 | 1
2015-07-31 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76235 | Barracks Complex |  | 2012-02-02 | 2012-04-06 | Fine Construction Co., Ltd. | W912UM-12-C-0022 | 28610 | 29427 | 2012-02-09 | 2014-12-05 | 2014-07-02 | 2014-12-03 | 1 | 16000 | 66745, 80087
2015-07-31 | [8 empty] | 2012-02-02 | 2012-02-09 | Hanmi C&E Co., LTD. | W912UM-11-D-0007 | 18 | 90
2015-07-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76767 | Aviation Unit Complex, Ph 1A |  | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | W9126G-08-D-0044 | 24162 | 24502 | 2012-07-09 |  | 2015-08-21 | 2015-09-10 | 0.95
2015-07-31 | [8 empty] | 2011-12-19 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6360 | 6938
2015-07-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B |  | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | W912DW-12-C-0051 | 12950 | 13975 | 2012-11-29 | 2014-10-14 | 2015-05-21 | 2015-09-02 | 0.89
2015-07-31 | [8 empty] | 2012-08-20 | 2014-04-08 | Glen/Mar Construction, Inc. | W912DW-14-C-0009 | 4771 | 5147
2015-07-31 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility |  | 2015-03-12 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7473 | 8035 | 2012-06-22 |  | 2015-01-25 | 2015-03-30 | 0.95
2015-07-31 | [8 empty] | 2015-03-12 | 2012-03-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 | 5379 | 4709
2015-07-31 | [8 empty] | 2015-03-12 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3750 | 3750
2015-07-31 | [8 empty] | 2015-03-12 | 2013-12-04 | Solis Constructors, Inc | W9126G-14-C-0006 | 2790 | 2905
2015-07-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77264 | Barracks |  | 2012-06-01 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 53767 | 54845 | 2013-05-29 | 2015-03-16 | 2015-02-08 | 2015-03-16 | 0.99
2015-07-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77265 | Barracks |  | 2012-06-01 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 37229 | 37947 | 2013-05-29 | 2015-03-16 | 2015-02-08 | 2015-03-16 | 0.97
2015-07-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77302 | Control Tower |  | 2012-02-22 | 2012-08-02 | Hensel Phelps Construction Co. | W9128F-12-C-0048 | 10891 | 12512 | 2012-08-27 | 2014-03-31 | 2015-02-08 | 2015-03-16 | 0.99
2015-07-31 | [8 empty] | 2012-02-22 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 602 | 658
2015-07-31 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar |  | 2012-01-17 | 2012-08-09 | Hensel Phelps Construction Co. | W9128F-12-C-0055 | 44801 | 54672 | 2012-08-23 | 2014-10-31 | 2015-02-08 | 2015-03-16 | 1 | 1235 | 55121
2015-07-31 | [8 empty] | 2012-01-17 | 2012-09-26 | Hensel Phelps Construction Company | W9128F-12-C-0085 | 195 | 195
2015-07-31 | [8 empty] | 2012-01-17 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction | W9128F-13-C-0005 | 2669 | 2920
2015-07-31 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78475 | Family Housing Improvements |  | 2013-05-22 | 2014-11-18 | Klebl GmbH | W912GB-15-C-0003 | 14632 | 14632 | 2015-01-16 |  | 2016-06-09 | 2016-06-09 | 0.08
2015-07-31 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78505 | Family Housing New Construction |  | 2012-04-06 | 2013-08-07 | Staatliches Hochbauamt Amberg | W912GB-11-C-0027 | 13549 | 13780 | 2013-08-07 |  | 2015-09-14 | 2015-09-14 | 0.64
2015-07-31 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78506 | Family Housing New Construction |  | 2012-04-10 | 2013-09-30 | Bauamt Amberg-Sulzbach | W912GB-11-C-0016 | 12815 | 12905 | 2013-09-30 |  | 2015-08-11 | 2015-08-11 | 0.78
2015-07-31 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78841 | Family Housing Improvements |  | 2012-05-15 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0018 | 20429 | 21310 | 2012-10-15 |  | 2018-10-29 | 2019-05-16 | 0.51 | 6885 | 74861
2015-07-31 | [8 empty] | 2012-05-15 | 2013-05-09 | WAYSS & FREYTAG INGENIEURBAU AG | W912GB-12-D-0055 | 1168 | 1590
2015-07-31 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 79097 | Family Housing Improvements |  | 2012-05-12 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0017 | 17917 | 18916 | 2012-10-15 |  | 2018-04-02 | 2018-11-09 | 0.48
2015-07-31 | [8 empty] | 2012-05-12 | 2013-05-09 | WAYSS & FREYTAG INGENIEURBAU AG | W912GB-12-D-0055 | 0 | 0
2015-07-31 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79652 | Radar Security and Support Facilities |  | 2014-07-14 | 2012-08-20 | American Assurance Underwriters Group | W912ER-12-C-0046 | 3800 | 4171 | 2012-09-27 | 2014-11-19 | 2014-11-30 | 2014-11-30 | 0.95
2015-07-31 | [8 empty] | 2014-07-14 | 2014-07-28 | American Int'l Contractors Inc | W912ER-14-C-0021 | 1367 | 1387
2015-07-31 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79749 | Forward Operating Site |  | 2012-06-15 | 2012-08-30 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129 | 12293 | 2012-07-25 |  | 2014-11-30 | 2015-02-18 | 0.58
2015-07-31 | [8 empty] | 2012-06-15 | 2012-07-05 | EMTA CONSTRUCTION CO. INC. | W912GB-10-D-0020 | 320 | 320
2015-07-31 | [8 empty] | 2012-06-15 | 2013-03-19 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. | W912GB-12-D-0035 | 199 | 199
2015-07-31 | 2012 | Army Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 79846 | Electromag Interference Fac |  | 2014-07-11 | 2014-09-28 | Kiewit Federal Group, Inc. | W912DR-11-D-0021 | 3195 | 3195 | 2014-10-20 |  | 2015-12-01 | 2015-12-01 | 0.01
2015-07-31 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 80001 | Waste Management Complex (60 Tons) |  | 2012-05-25 | 2012-08-21 | Bryan 77 Construction JV | W912ER-11-D-0004 | 24436 | 23957 | 2012-11-14 | 2014-08-08 | 2014-03-27 | 2014-12-15 | 1
2015-07-31 | 2012 | Army Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 80231 | Replace Oil Water Separators |  | 2014-07-25 | 2014-09-28 | East Coast Utility Contractors, LTD. | W912DR-14-C-0041 | 1484 | 1484 | 2014-11-03 |  | 2015-09-25 | 2015-09-25 | 0.02
2015-07-31 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 5924 | Automated Infantry Squad Battle Course |  | 2013-01-22 | 2013-06-14 | Howard W. Pence, Inc. | W912QR-13-C-0020 | 3918 | 3948 | 2013-09-24 | 2014-09-23 | 2014-09-24 | 2014-11-22 | 0.98
2015-07-31 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650 | 46545 | 2013-10-15 |  | 2015-10-15 | 2015-10-15 | 0.68
2015-07-31 | [8 empty] | 2013-07-17 | 2014-09-03 | VISTA Construction LLC | W91236-14-C-0043 | 4055 | 4055
2015-07-31 | [8 empty] | 2013-07-17 | 2015-01-14 | Doyon Management Services, LLC | W91236-15-C-0017 | 14297 | 14297
2015-07-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 45116 | Aircraft Component Maintenance Shop |  | 2013-02-23 | 2013-07-25 | Anthony & Gordon Construction Company | N69450-13-C-0754 | 9806 | 10513 | 2013-08-08 |  | 2015-08-15 | 2015-08-15 | 0.79
2015-07-31 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center |  | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959 | 7227 | 2012-12-04 |  | 2015-02-15 | 2015-08-04 | 0.94
2015-07-31 | [8 empty] | 2013-05-16 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 0 | 2019
2015-07-31 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 |  | 2013-04-11 | 2013-08-15 | Caddell Construction Co. (DE), LLC | W912DQ-13-C-4024 | 33360 | 34380 | 2013-06-25 |  | 2015-09-12 | 2015-10-16 | 0.97
2015-07-31 | [8 empty] | 2013-04-11 | 2013-05-31 | Donald Maggi, Inc. | W912DQ-13-C-4010 | 11711 | 12293
2015-07-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 55460 | Aircraft Paint Shop |  | 2013-04-19 | 2013-09-27 | Anthony & Gordon Construction Company | N69450-13-C-0756 | 15340 | 16112 | 2013-10-22 |  | 2016-02-14 | 2016-02-14 | 0.41
2015-07-31 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 57794 | Digital Multipurpose Training Range |  | 2012-12-26 | 2013-05-10 | Caddell Construction Co. (DE), LLC | W912HN-10-D-0044 | 19523 | 19721 | 2014-02-04 |  | 2015-04-30 | 2015-07-06 | 0.92
2015-07-31 | 2013 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 58970 | Trainee Barracks Complex 2, Ph 2 |  | 2013-04-29 | 2013-10-30 | ACC Construction Co., Inc | W912HP-14-C-0003 | 21786 | 22001 | 2013-12-04 |  | 2015-05-28 | 2015-08-22 | 0.87
2015-07-31 | 2013 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 59626 | Digital Multipurpose Training Range |  | 2013-05-31 | 2013-08-23 | NEU Security Services, LLC | W9128F-13-C-0016 | 14080 | 16081 | 2013-09-18 |  | 2015-03-12 | 2015-08-06 | 0.87
2015-07-31 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex |  | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | W912QR-14-C-0007 | 25750 | 25812 | 2013-07-15 |  | 2015-08-26 | 2015-09-07 | 0.87
2015-07-31 | [8 empty] | 2012-12-06 | 2013-05-29 | Orocon-Carothers JV1 | W912QR-13-C-0010 | 23451 | 23838
2015-07-31 | 2013 | Army Active | Major Military Construction |  | JAPAN | 62783 | Satellite Communications Facility |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 84367 | 84367 | 2014-11-21 |  | 2021-06-09 | 2021-12-06 | 0.06
2015-07-31 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 65679 | Vehicle Maintenance Shop |  | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18727 | 19430 | 2013-06-27 |  | 2015-04-08 | 2015-06-15 | 0.96
2015-07-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 66023 | Automated Infantry Platoon Battle Course |  | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345 | 27341 | 2014-07-08 |  | 2016-09-09 | 2016-10-12 | 0.54
2015-07-31 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 66099 | Battalion Complex Facilities |  | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687 | 14606 | 2013-07-01 | 2014-12-31 | 2016-05-05 | 2016-05-05 | 0.7
2015-07-31 | [8 empty] | 2012-12-19 | 2015-01-20 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 6228 | 6259
2015-07-31 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 67545 | Convoy Live Fire Range |  | 2013-05-16 | 2013-08-22 | Vet Industrial Inc. | W912DW-10-D-1021 | 4991 | 5424 | 2013-09-10 | 2014-11-21 | 2015-01-03 | 2015-01-03 | 1
2015-07-31 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 67652 | Army Reserve Center |  | 2014-05-06 | 2015-03-31 | Cox Construction Co. | W912QR-15-C-0007 | 24044 | 24044 | 2015-04-24 |  | 2017-02-12 | 2017-02-12 | 0
2015-07-31 | 2013 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67659 | Army Reserve Center |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21779 | 22979 | 2014-01-13 |  | 2015-11-04 | 2015-12-31 | 0.63
2015-07-31 | 2013 | Army Reserve | Major Military Construction | NEVADA | UNITED STATES | 67660 | Army Reserve Center/AMSA |  | 2012-12-28 | 2013-06-12 | MACNAK Korte Team LLC | W912QR-13-C-0014 | 16649 | 18119 | 2013-07-10 | 2015-07-06 | 2015-05-01 | 2015-05-01 | 0.98
2015-07-31 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 67689 | Central Issue Facility |  | 2013-01-28 | 2013-06-14 | KEPA-TCI JV LLC | W912QR-13-C-0016 | 9302 | 10113 | 2013-07-08 |  | 2014-11-10 | 2015-08-20 | 0.98
2015-07-31 | 2013 | Army Reserve | Major Military Construction | WASHINGTON | UNITED STATES | 67715 | Army Reserve Center |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31523 | 32236 | 2013-07-11 |  | 2015-08-30 | 2015-08-30 | 0.92
2015-07-31 | 2013 | Army Reserve | Major Military Construction | MARYLAND | UNITED STATES | 68077 | Add/Alt Army Reserve Center |  | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890 | 7890 | 2014-07-30 |  | 2016-05-30 | 2016-05-30 | 0.1
2015-07-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71120 | Training Aids Center |  | 2013-03-08 | 2013-09-04 | PENTACON, LLC | W912DY-12-D-0030 | 21912 | 22002 | 2013-10-17 | 2015-06-09 | 2015-04-10 | 2015-04-10 | 0.66
2015-07-31 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 71482 | ORTC |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56039 | 61917 | 2014-03-19 |  | 2016-05-17 | 2016-05-27 | 0.31
2015-07-31 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 71675 | Flight Equipment Complex |  | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751 | 42904 | 2014-01-15 |  | 2016-01-15 | 2016-01-15 | 0.54
2015-07-31 | 2013 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71720 | Automated Infantry Squad Battle Course |  | 2012-12-13 | 2013-06-28 | Eastern Construction & Electric, Inc. | W912QR-13-C-0015 | 3094 | 3516 | 2013-07-17 | 2015-02-12 | 2014-07-17 | 2015-06-30 | 0.96
2015-07-31 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71997 | Dining Facility |  | 2013-01-22 | 2013-08-23 | TCI Architects Engineers Contractor Inc. | W912QR-13-C-0026 | 7744 | 8190 | 2013-10-02 |  | 2015-02-04 | 2015-04-01 | 0.87
2015-07-31 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 72088 | ECS TEMF |  | 2013-01-24 | 2013-06-13 | KSI-TCI JV LLC | W912QR-13-C-0018 | 19101 | 19590 | 2013-07-08 |  | 2015-06-08 | 2015-06-08 | 0.77
2015-07-31 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72160 | UPH Barracks |  | 2013-03-28 | 2013-08-27 | Pre Con Industries, Inc. | W912QR-13-C-0027 | 4384 | 4540 | 2013-11-18 | 2015-04-02 | 2014-11-03 | 2015-02-23 | 0.99
2015-07-31 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 73008 | Unmanned Aerial Vehicle Complex |  | 2013-03-22 | 2013-08-15 | Caddell Construction CO. (DE), LLC | W912HN-10-D-0044 | 20726 | 21072 | 2013-11-06 |  | 2015-03-01 | 2015-06-25 | 0.86
2015-07-31 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 75165 | Waste Water Treatment Plant |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77477 | 78753 | 2014-03-03 |  | 2016-03-02 | 2016-04-18 | 0.51
2015-07-31 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76086 | Lightning Protection System |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072 | 3072 | 2014-09-16 |  | 2015-12-30 | 2015-12-30 | 0.02
2015-07-31 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76091 | Engineering/Housing Maintenance Shop |  | 2014-05-15 | 2014-09-18 | Federal Solutions Group | W91238-14-C-0051 | 3212 | 3212 | 2014-10-08 |  | 2015-11-12 | 2015-11-12 | 0.32
2015-07-31 | 2013 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76196 | Battalion Headquarters Complex |  | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25853 | 28861 | 2013-05-14 |  | 2015-06-09 | 2016-05-29 | 0.37
2015-07-31 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 76239 | Unmanned Aerial Vehicle Complex |  | 2012-11-13 | 2013-05-31 | Archer Western Federal JV | W912QR-13-C-0012 | 16983 | 17497 | 2013-06-25 | 2015-06-17 | 2015-04-26 | 2015-06-06 | 0.95
2015-07-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76586 | Barracks |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717 | 32165 | 2013-07-23 |  | 2015-09-01 | 2016-06-01 | 0.73
2015-07-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76587 | Barracks |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410 | 39691 | 2013-07-23 |  | 2015-09-01 | 2016-06-01 | 0.69
2015-07-31 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76903 | Combat Aviation Brigade Barracks |  | 2012-11-26 | 2014-05-13 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749 | 69749 | 2014-06-26 |  | 2017-01-13 | 2017-04-13 | 0.07
2015-07-31 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 77416 | Ground Source Heat Transfer System |  | 2013-04-04 | 2013-05-29 | R. C. Construction Co., Inc. | W912HN-10-D-0058 | 8295 | 8490 | 2013-07-12 | 2015-02-27 | 2015-01-03 | 2015-03-04 | 0.99
2015-07-31 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 77419 | Ground Source Heat Transfer System |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 10400 | 10400 | 2015-01-06 |  | 2016-12-26 | 2017-01-09 | 0.11
2015-07-31 | 2013 | Army Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 78054 | Vehicle Storage Building, Installation |  | 2014-07-08 | 2015-03-17 | Akima Construction Services, LLC | W912DR-15-C-0013 | 3358 | 10015 | 2015-04-03 |  | 2016-09-24 | 2016-09-24 | 0
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE |  | 2013-05-17 | 2013-07-17 | Huffman Construction, LLC | W912DQ-13-C-4018 | 1438 | 1551 | 2012-12-10 |  | 2014-06-20 | 2015-06-14 | 0.93
2015-07-31 | [8 empty] | 2013-05-17 | 2012-09-30 | Zieson Construction Company, LLC | W912DQ-11-D-4007 | 15 | 15
2015-07-31 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80066 | Controlled Humidity Warehouse, Installatio |  | 2012-11-16 | 2013-09-20 | Tyler Construction Co., INC | W912HN-10-D-0060 | 6727 | 6769 | 2013-11-06 | 2015-06-30 | 2015-03-01 | 2015-03-20 | 0.96
2015-07-31 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80087 | Storage Building, General Purpose |  | 2012-07-16 | 2013-03-22 | Tyler Construction Group, Inc. | W912HN-10-D-0060 | 9038 | 9004 | 2013-04-18 | 2015-05-08 | 2014-08-11 | 2014-09-17 | 0.92
2015-07-31 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80112 | Unmanned Aerial Vehicle Complex |  | 2014-12-02 | 2015-04-23 | Sauer Inc. d/b/a Sauer Southeast | W91278-12-D-0039 | 10965 | 10965 | 2015-05-26 |  | 2016-07-19 | 2016-07-19 | 0
2015-07-31 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex |  | 2013-04-25 | 2013-08-15 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491 | 11443 | 2013-10-07 |  | 2016-01-04 | 2016-01-13 | 0.96
2015-07-31 | [8 empty] | 2013-04-25 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 591 | 591
2015-07-31 | [8 empty] | 2013-04-25 | 2013-08-30 | Carntribe-Clement 8aJV #1, LLC | W912HN-11-D-0028 | 5994 | 5977
2015-07-31 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar |  | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 39587 | 40272 | 2013-06-27 |  | 2015-12-02 | 2016-03-18 | 0.65
2015-07-31 | [8 empty] | 2012-12-12 | 2013-06-17 | Black Horse Group LLC | W912DS-09-D-0004 | 21578 | 22594
2015-07-31 | [8 empty] | 2012-12-12 | 2013-11-25 | Upstate Construction Services, Inc. | W912DS-09-D-0005 | 17287 | 17753
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80317 | WATER DISTRIBUTION LINES, POTABLE |  | 2013-08-14 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1791 | 1500 | 2014-01-13 | 2015-07-30 | 2014-09-10 | 2015-04-30 | 0.55
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | UTAH | UNITED STATES | 81106 | POLICE/MP STATION |  | 2013-06-11 | 2013-09-27 | Zumwalt Construction, Inc. | W91238-11-D-0026 | 1882 | 2431 | 2013-10-18 | 2015-07-15 | 2014-12-17 | 2015-06-15 | 0.7
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81300 | AIRCRAFT MAINTENANCE HANGAR |  | 2013-04-29 | 2013-09-12 | CMS of Colorado Springs, Inc. dba CMS | W9128F-13-C-0023 | 1731 | 1850 | 2013-10-29 | 2015-01-21 | 2014-08-25 | 2014-12-22 | 1
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81320 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL |  | 2013-08-08 | 2013-09-26 | Northcon, Inc. | W912DW-13-C-0047 | 1380 | 1380 | 2013-10-28 | 2015-02-19 | 2014-10-28 | 2015-01-26 | 0.94
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 81367 | EXPLOSIVES RECEIVING/SERVICE BUILDING, DEP |  | 2013-12-18 | 2014-04-16 | Cyber Professional Solution Corp | W912PL-14-C-0006 | 1784 | 1784 | 2014-05-08 | 2015-05-08 | 2015-05-08 | 2015-05-08 | 0.98
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE |  | 2013-08-15 | 2014-06-17 | PORTICO SERVICES, LLC | W912DR-14-C-0028 | 1793 | 1850 | 2014-07-15 |  | 2015-04-28 | 2015-07-31 | 0.95
2015-07-31 | [8 empty] | 2013-08-15 | 2014-09-30 | Portico Services | W912DR-14-C-0048 | 220 | 245
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  | 2014-08-21 | 2014-09-30 | Nan Inc | W9128A-12-D-0012 | 1556 | 1556 | 2014-10-28 |  | 2015-10-23 | 2015-10-23 | 0.11
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 81515 | CIDC FIELD OPERATIONS BUILDING |  | 2013-05-21 | 2013-09-29 | Guyco, Inc. | W9126G-09-D-0095 | 1784 | 1779 | 2013-12-04 | 2015-01-06 | 2014-12-04 | 2015-01-03 | 1
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 81629 | AIR CONDITIONING/REFRIGERATION PLANT |  | 2013-07-15 | 2013-09-27 | Team Henry Enterprises, LLC | W91236-13-D-0042 | 1089 | 1133 | 2013-10-17 | 2014-11-12 | 2014-08-13 | 2014-11-11 | 1
2015-07-31 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 79933 | Cadet Barracks |  | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402 | 166440 | 2013-08-26 |  | 2016-08-30 | 2016-09-11 | 0.39
2015-07-31 | 2014 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81186 | Cadet Barracks, Incr 2 | 79933 | 2012-11-06 | 2013-08-08 | 0 | W912DS-13-C-0032 | 0 | 0
2015-07-31 | 2015 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81187 | Cadet Barracks, Incr 3 | 79933 | 2012-11-06 | 2013-08-08 | 0 | W912DS-13-C-0032 | 0 | 0
2015-07-31 | 2014 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 51868 | Adv Individual Training Barracks Cplx, Ph2 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 55619 | 55956 | 2015-01-06 |  | 2016-12-26 | 2017-01-09 | 0.1
2015-07-31 | 2014 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036 | 40304 | 2014-10-09 |  | 2017-07-05 | 2017-07-05 | 0.02
2015-07-31 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 54106 | Automated Multipurpose Machine Gun Range |  | 2013-12-24 | 2014-05-28 | TSS-Garco Joint Venture | W912DW-14-C-0012 | 7716 | 7731 | 2014-08-18 |  | 2016-02-09 | 2016-02-09 | 0.55
2015-07-31 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 65277 | Consolidated Dining Facility |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 11895 | 12978 | 2014-04-23 |  | 2015-09-30 | 2015-09-30 | 0.35
2015-07-31 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex |  | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0019 | 14180 | 14413 | 2014-04-23 |  | 2016-09-06 | 2016-09-06 | 0.53
2015-07-31 | [8 empty] | 2013-08-28 | 2014-04-14 | Arctic-American JV | W911KB-14-C-0008 | 16180 | 16131
2015-07-31 | [8 empty] | 2013-08-28 | 2014-12-31 | ALCAN BUILDERS INC. | W911KB-15-C-0001 | 12375 | 12390
2015-07-31 | 2014 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69624 | Command and Control Facility |  | 2014-06-10 | 2014-07-21 | Brantley Construction Services, LLC | W912HN-10-D-0056 | 4720 | 4925 | 2014-08-27 |  | 2015-08-27 | 2015-09-08 | 0.84
2015-07-31 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 69669 | Central Issue Facility |  | 2014-01-31 | 2014-06-05 | Ranco Construction, Inc. | W912QR-14-C-0021 | 8783 | 8872 | 2014-07-07 |  | 2015-12-14 | 2015-12-14 | 0.2
2015-07-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 71221 | Fire Station |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542 | 12995 | 2014-08-27 |  | 2016-02-18 | 2016-06-01 | 0.36
2015-07-31 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777 | 50334 | 2014-08-05 |  | 2016-08-04 | 2016-11-17 | 0.16
2015-07-31 | [8 empty] | 2014-03-06 | 2014-12-19 | Zieson Construction Co. | W912DQ-14-D-4000 | 4796 | 4842
2015-07-31 | [8 empty] | 2014-03-06 | 2014-12-18 | Zieson Construction Company, LLC | W912DQ-15-C-4004 | 14313 | 14277
2015-07-31 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71769 | Modified Record Fire Range |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653 | 4658 | 2014-10-17 |  | 2016-04-09 | 2016-04-09 | 0.32
2015-07-31 | 2014 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71900 | Army Reserve Center |  | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129 | 22198 | 2014-12-02 |  | 2016-11-01 | 2016-11-14 | 0.19
2015-07-31 | 2014 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71999 | NCO Academy Dining Facility |  | 2013-12-12 | 2014-03-31 | Wilson Brigadier Joint Venture | W912QR-14-C-0013 | 5905 | 6675 | 2014-04-22 |  | 2015-08-25 | 2015-09-05 | 0.77
2015-07-31 | 2014 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72284 | TASS Training Center (TTC) |  | 2014-08-13 | 2014-09-30 | Bara Infoware Inc. | W912QR-14-C-0053 | 16187 | 16187 | 2014-10-20 |  | 2016-05-22 | 2016-05-22 | 0.1
2015-07-31 | 2014 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 74638 | Control Tower |  | 2013-11-07 | 2015-04-02 | SGS, LLC | W9126G-15-C-0091 | 13978 | 13978 | 2015-04-28 |  | 2017-01-02 | 2017-01-02 | 0.01
2015-07-31 | 2014 | Army Active | Military Family Housing | WISCONSIN | UNITED STATES | 74861 | Family Housing New Construction |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862 | 27689 | 2014-08-20 |  | 2016-08-09 | 2016-09-19 | 0.1
2015-07-31 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 75019 | Simulator Building |  | 2014-08-28 | 2014-11-06 | Zieson Construction Company, LLC | W912DQ-15-C-4000 | 3497 | 3515 | 2014-12-01 |  | 2015-12-01 | 2016-01-04 | 0.38
2015-07-31 | 2014 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 76024 | Simulations Center |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630 | 15722 | 2014-09-02 |  | 2016-02-24 | 2016-05-04 | 0.14
2015-07-31 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar |  | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25547 | 25547 | 2014-04-17 |  | 2016-03-21 | 2016-09-29 | 0.39
2015-07-31 | [8 empty] | 2013-08-30 | 2014-04-08 | ANCOR, INC. | W911KB-14-C-0003 | 2651 | 3283
2015-07-31 | [8 empty] | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC | W911KB-14-C-0005 | 9525 | 9705
2015-07-31 | [8 empty] | 2013-08-30 | 2014-04-08 | C.I. Contractors INC. | W911KB-14-C-0010 | 5007 | 6533
2015-07-31 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76776 | Airfield Operations Complex |  | 2015-03-23 | 2015-04-09 | Walsh Group Ventures | W912DW-15-C-0002 | 11319 | 11333 | 2015-05-18 |  | 2017-07-06 | 2017-07-06 | 0.01
2015-07-31 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar |  | 2014-06-25 | 2014-08-26 | Archer Western Federal JV | W912DW-14-C-0023 | 36998 | 37424 | 2014-09-23 |  | 2016-03-16 | 2016-03-16 | 0.33
2015-07-31 | [8 empty] | 2014-06-25 | 2014-09-03 | The Renew Group, Inc. | W912DW-14-C-0017 | 1106 | 1103
2015-07-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building |  | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165 | 17351 | 2014-08-21 |  | 2016-03-31 | 2016-05-10 | 0.33
2015-07-31 | [8 empty] | 2014-02-28 | 2014-08-28 | Medvolt, LLC | W9128F-14-C-0054 | 13195 | 13842
2015-07-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56721 | 57882 | 2014-08-18 |  | 2016-08-22 | 2016-09-08 | 0.33
2015-07-31 | [8 empty] | 2014-05-22 | 2014-09-04 | John Bowman, Inc. | W9128F-13-D-0013 | 2288 | 2269
2015-07-31 | [8 empty] | 2014-05-22 | 2014-09-04 | Hartland/Mass JV LLC | W9128F-13-D-0014 | 3339 | 3466
2015-07-31 | [8 empty] | 2014-05-22 | 2014-07-16 | SEK JV | W9128F-13-D-0015 | 3133 | 3520
2015-07-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar |  | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585 | 51439 | 2014-07-22 |  | 2016-08-22 | 2016-09-08 | 0.15
2015-07-31 | [8 empty] | 2014-07-09 | 2014-06-19 | Blackhorse Worldwide LLC | W9128F-13-D-0016 | 4214 | 4678
2015-07-31 | [8 empty] | 2014-07-09 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 891 | 891
2015-07-31 | [8 empty] | 2014-07-09 | 2015-01-16 | Agile Infrastructure Services, L.L.C. | W9128F-15-C-0002 | 2843 | 2843
2015-07-31 | 2014 | Army Active | Major Military Construction | FLORIDA | UNITED STATES | 77539 | Automated Sniper Field Fire Range |  | 2014-07-17 | 2014-09-26 | Barlovento, LLC | W91278-10-D-0072 | 4711 | 4711 | 2014-12-17 |  | 2015-12-17 | 2015-12-17 | 0.26
2015-07-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77885 | Runway |  | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9833 | 11417 | 2014-07-01 |  | 2015-07-01 | 2015-10-29 | 0.54
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 77980 | Cantonment Area, Roads, Paved |  | 2014-08-12 | 2014-09-16 | FutureNet Group, Inc. | W912QR-09-D-0050 | 1636 | 1642 | 2014-09-24 |  | 2015-08-20 | 2015-09-08 | 0.41
2015-07-31 | 2014 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 78778 | Battlefield Weather Support Facility |  | 2013-12-24 | 2014-06-18 | TJC Engineering | W912QR-14-C-0018 | 4275 | 4284 | 2014-06-27 |  | 2015-08-21 | 2015-10-09 | 0.47
2015-07-31 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 79618 | Simulator Building |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440 | 8569 | 2014-08-20 |  | 2016-02-11 | 2016-03-07 | 0.2
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 79679 | Materials Analysis Lab |  | 2014-02-03 | 2014-06-10 | Au' Authum Ki, Inc | W912PL-10-D-0109 | 2984 | 2984 | 2014-07-28 |  | 2015-09-01 | 2015-09-01 | 0.71
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 80477 | Fragmentation Simulation Lab |  | 2013-04-22 | 2013-12-13 | The Clement Group, L.L.C. | W91278-11-D-0029 | 2341 | 2345 | 2014-01-23 |  | 2015-07-17 | 2015-07-17 | 0.96
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80919 | Underground Electric Lines |  | 2014-08-12 | 2014-09-29 | Glen/Mar Construction, Inc. | W912DW-14-C-0029 | 1545 | 1631 | 2015-02-13 |  | 2016-02-13 | 2016-02-13 | 0.16
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | 80992 | Upgrade Power Distribution |  | 2015-02-06 | 2015-03-24 | Red One Construction, LLC | W9128A-15-C-0002 | 1696 | 1696 | 2015-04-29 |  | 2016-10-20 | 2016-10-20 | 0.06
2015-07-31 | 2014 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 81155 | Unmanned Aerial Vehicle Complex |  | 2014-05-02 | 2014-12-05 | SGS, LLC | W9126G-15-C-0005 | 32968 | 32968 | 2014-12-18 |  | 2016-04-11 | 2016-04-11 | 0.2
2015-07-31 | 2014 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 81875 | Operations and Maintenance Facilities |  | 2013-12-02 | 2014-05-12 | Edifice-Schlosser JV, LLC | W912DR-14-C-0017 | 17891 | 20501 | 2014-05-23 |  | 2015-03-19 | 2015-07-12 | 0.93
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 82268 | Illinois Ave (PREPO) Yd |  | 2014-07-22 | 2014-09-30 | Tarver Land Development, LLC | W9126G-14-C-0059 | 1749 | 1793 | 2014-12-03 | 2015-07-08 | 2015-04-02 | 2015-05-06 | 0.98
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 82371 | Power Plant Facility 994 |  | 2015-03-28 | 2014-09-30 | San Juan Construction, Inc. | W9128A-12-D-0010 | 1597 | 1587 | 2014-10-28 |  | 2015-09-07 | 2015-09-12 | 0.45
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | 85260 | Secure Operations Center |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1725 | 1744 | 2014-11-05 |  | 2015-11-05 | 2015-11-05 | 0.6
2015-07-31 | 2015 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81349 | Unmanned Aerial Vehicle Hangar |  | 2015-02-20 | 2015-06-04 | Upstate Construction SVCS, Inc. | W912DS-15-C-0008 | 19408 | 19408 | 2015-06-22 |  | 2016-12-18 | 2016-12-18 | 0
2015-07-31 | 2015 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 81357 | Unmanned Aerial Vehicle Hangar |  | 2015-04-13 | 2015-07-07 | David Boland, Inc. | W9128F-15-C-0017 | 26149 | 26149 | 2014-04-30 |  | 2016-12-12 | 2016-12-12 | 0
2015-07-31 | 2015 | Army Reserve | Major Military Construction | COLORADO | UNITED STATES | 81959 | Training Building Addition |  | 2015-03-06 | 2015-07-17 | ETD-TCG, LLC with RSP Architects | W912QR-15-C-0018 | 5215 | 5215 | 2015-08-16 |  | 2016-09-09 | 2016-09-09 | 0
2015-07-31 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 60344 | Air Support Operations Facilities |  | 2012-01-06 | 2012-03-09 | Performance Systems, Inc. | W912DW-10-D-1026 | 7512 | 8317 | 2012-08-17 | 2014-07-31 | 2013-07-31 | 2014-05-09 | 0.99
2015-07-31 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64456 | Battalion Complex |  | 2013-02-20 | 2013-05-17 | Tunista Construction, LLC | W912DW-13-C-0035 | 9432.86 | 11067.4575 | 2013-06-26 |  | 2014-12-18 | 2015-08-31 | 0.99
2015-07-31 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64456 | Battalion Complex |  | 2012-11-30 | 2013-06-18 | Megen Construction Company, Inc. | W912HN-11-D-0047 | 14849 | 15666.182 | 2013-07-11 |  | 2015-01-02 | 2016-01-30 | 0.96
2015-07-31 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64456 | Battalion Complex |  | 2013-04-13 | 2013-09-12 | Environet, Inc. | W912DW-13-C-0042 | 5661.506 | 7666.285 | 2013-10-02 |  | 2015-02-12 | 2016-04-13 | 0.98
2015-07-31 | 2015 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77305 | Aircraft Maintenance Hangar |  | 2015-01-30 | 2015-05-28 | Francisco Semsch, Architect, Inc. | W9128F-15-C-0010 | 3848.169 | 3848.169 | 2015-06-16 |  | 2016-06-15 | 2016-06-15 | 0
2015-07-31 | 2009 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420511 | Readiness Center, Add/Alt |  | 2011-08-31 | 2011-09-15 | Lobar Incorporated | DGS 961-20.1 | 5282 | 5738 | 2011-09-26 | 2013-08-15 | 2012-10-30 | 2015-05-31 | 0.99 | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-07-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540105 | Joint Interagency Training Education Center, PH 1 |  | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | DEFK10003 | 77500 | 72200 | 2009-10-01 | 2011-09-30 | 2011-09-28 | 2014-09-30 | 0.99 | 0 |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540206 | Multi-Purpose Building, PH II |  | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | DEFK10004 | 4755 | 4624 | 2010-02-01 | 2010-08-30 | 2010-08-26 | 2013-03-31 | 1 | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2015-07-31 | 2010 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060115 | Readiness Center, PH 1 |  | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | W912LA-10-C-0009 | 30711 | 23378 | 2010-11-15 | 2013-10-07 | 2012-02-06 | 2015-01-30 | 0.95 | 2900 | 390263 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2015-07-31 | 2010 | Army National Guard | Major Military Construction | GUAM | GUAM | 140300 | Readiness Center |  | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | N40192-10-C-1335 | 20766 | 20797 | 2010-05-03 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 0.98 | 3000 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2015-07-31 | 2010 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170611 | Readiness Center, Add/Alt |  | 2010-09-17 | 2010-09-22 | Capital Development Board | W91SMC-10-2-2001-100 | 5560 | 4319 | 2010-10-18 | 2012-03-31 | 2011-09-14 | 2011-09-14 | 1 | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2015-07-31 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320143 | Readiness Center |  | 2010-09-27 | 2010-09-27 | The Penta Building Company | SPWB-09-C-14 | 25807 | 19910 | 2010-10-25 | 2013-05-01 | 2012-01-23 | 2013-04-19 | 0.99 | 3112 | 060413 | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2015-07-31 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450252 | Army Aviation Support Facility, Add/Alt |  | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. | W912QG-10-C-0005 | 14759 | 14078 | 2011-02-07 | 2013-04-15 | 2011-12-14 | 2013-05-01 | 0.99 | 11000 | 090115, 220241 and 220243 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2015-07-31 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450353 | Army Aviation Support Facility |  | 2010-09-23 | 2010-09-24 | Hendrick Construction | 460114576 | 27936 | 27304 | 2010-11-17 | 2013-06-21 | 2012-08-10 | 2013-06-21 | 0.75 | 12100 | 220241, 220243, and 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936)
2015-07-31 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480175 | Armed Forces Reserve Center |  | 2010-08-05 | 2010-12-03 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 16441 | 14196 | 2011-01-24 | 2013-10-01 | 2012-07-17 | 2015-07-01 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-07-31 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480176 | Field Maintenance Shop, Joint |  | 2010-08-05 | 2010-12-03 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 5700 | 7021 | 2011-01-24 | 2013-10-01 | 2012-07-17 | 2015-07-01 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punchlist pending
2015-07-31 | 2010 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520014 | Regional Training Institute, PH 1 |  | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. | W9127P-10-C-0001 | 19978 | 19493 | 2010-07-01 | 2013-02-15 | 2012-02-20 | 2013-04-23 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060429 | Combined Arms Collective Training Facility |  | 2011-05-12 | 2011-09-20 | Cox Construction Company | W912LA-11-R-0005 | 12379 | 11525 | 2011-12-05 | 2013-06-15 | 2012-06-29 | 2013-09-27 | 0.99 | 6700 | 361103 | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080067 | Regional Training Institute |  | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC | W912LC-11-C-0008 | 50886 | 50932 | 2011-10-01 | 2014-12-15 | 2014-10-18 | 2014-10-03 | 1 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2,000 Formal Reprogramming $9,300 funds from FY10 project savings {PNs: 160120 ($6,000) & 350043 ($3,300)}
2015-07-31 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130123 | Readiness Center, Add/Alt |  | 2011-05-17 | 2012-04-17 | TEPA | W912JM-10-D-0018 | 10363 | 10349 | 2012-06-04 | 2013-09-30 | 2013-09-30 | 2014-04-30 | 0.9 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130127 | Readiness Center |  | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 41100-033-0000078159 | 16941 | 16726 | 2011-12-01 | 2013-05-15 | 2012-11-16 | 2012-11-16 | 0.85 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160093 | Barracks (ORTC), Ph 1 |  | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | W912J7-11-C-0002 | 17333 | 13811 | 2011-08-27 | 2013-10-03 | 2013-02-28 | 2014-04-15 | 1 | 2600 | 300216 | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220222 | Tactical Unmanned Aircraft System Facility |  | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company | LA11-C-139 | 5470 | 5018 | 2011-09-12 | 2012-12-11 | 2012-07-30 | 2013-06-18 | 0.99 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240186 | Tactical Unmanned Aircraft System Facility |  | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | N40080-10-D-0498 | 5480 | 5587 | 2012-06-01 | 2014-12-06 | 2013-06-15 | 2014-11-21 | 1 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330034 | Classroom Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-25 | Eckman Construction Company, Inc. | W912TF-09-2-2001 | 20742 | 19809 | 2011-11-07 | 2016-01-23 | 2013-06-01 | 2016-03-03 | 0.5 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330035 | Barracks Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-26 | Eckman Construction Company, Inc. | W912TF-09-2-2002 | 14880 | 14005 | 2011-11-07 | 2015-11-23 | 2013-06-01 | 2016-01-30 | 0.65 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 436021 | Multi Purpose Machine Gun Range |  | 2012-08-27 | 2012-08-29 | Eastern Construction and Electrical Inc. | W912LR-14-B-2004 | 9200 | 9758 | 2014-09-15 | 2015-01-26 | 2015-01-26 | 2015-09-14 | 0.66 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 436023 | Live Fire Shoot House |  | 2011-07-21 | 2011-09-22 | Remex Co. | W912LR-11-B-0001 | 3077 | 2562 | 2011-11-07 | 2012-09-18 | 2012-12-14 | 2012-12-14 | 0.65 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440009 | United States Property and Fiscal Office |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 19316 | 21433 | 2012-10-08 | 2015-01-31 | 2014-04-17 | 2015-03-31 | 0.99 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460085 | Readiness Center |  | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. | W912MM-06-2-20002 | 18255 | 17797 | 2011-11-07 | 2013-03-01 | 2013-01-14 | 2015-06-01 | 0.99 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($18,225)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | VIRGIN ISLANDS | VIRGIN ISLANDS, U.S. | 520034 | Readiness Center (JFHQ) |  | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | W9127P-11-C-0005 | 24850 | 22326 | 2011-11-01 | 2013-11-25 | 2012-08-20 | 2013-08-01 | 1 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530022 | Combined Support Maintenance Shop |  | 2011-06-07 | 2011-06-23 | Pease & Sons, Inc. | 2009-205 G 1-1 | 24880 | 24115 | 2011-08-22 | 2013-12-12 | 2012-11-03 | 2014-09-23 | 1 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011), State waiting on demolition of the old CSMS
2015-07-31 | 2011 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550139 | Aircraft Parking |  | 2011-08-16 | 2011-09-15 | Buteyn Peterson Construction Co. | NGB-47-11-C-0014 | 5689 | 5960 | 2011-11-01 | 2012-10-09 | 2012-10-29 | 2012-10-17 | 0.94 | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010263 | Readiness Center, Ph2 |  | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. | W912JA-12-C-0001 | 16413 | 14492 | 2012-08-17 | 2015-02-06 | 2014-09-17 | 2014-09-23 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040294 | Readiness Center |  | 2012-02-15 | 2012-08-16 | Haydon Building Corporation-Tem | M11-0045 | 17771 | 17655 | 2012-09-12 | 2013-11-04 | 2013-10-16 | 2014-01-31 | 0.05 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050172 | Convoy Live Fire/Entry Control Point Range |  | 2012-02-14 | 2012-08-16 | USPFO - AK | 9751104 | 3500 | 3604 | 2012-11-07 | 2015-02-01 | 2013-10-28 | 2014-07-15 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | 050190 | Wash Platform, Installation |  | 2013-09-12 | 2013-09-18 | Wilkins Construction, Inc. | W912JF-09-D-0016-0013 | 1195 | 1759 | 2014-03-10 | 2014-12-09 | 2014-06-23 | 2014-12-22 | 0.99 | 0
2015-07-31 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060170 | Field Maintenance Shop |  | 2012-06-19 | 2012-06-26 | Goshawk LLC | W912LA-12-C-0003 | 7985 | 7482 | 2012-11-08 | 2013-10-20 | 2013-10-14 | 2014-06-06 | 0.35 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 060432 | Barracks |  | 2012-06-27 | 2012-09-28 | WEP Enterprises | W912LA-11-D-0024 | 1400 | 1131 | 2012-10-15 | 2013-10-07 | 2013-09-20 | 2014-10-30 | 0.99 | 0 |  | FY07 Congressionally Directed, Used FY10 funds
2015-07-31 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060438 | Tactical Unmanned Aircraft System Facility |  | 2012-06-04 | 2012-07-20 | Red Mountain LLC | W912LA-12-C-0002 | 6114 | 5257 | 2012-08-06 | 2013-11-11 | 2013-10-28 | 2015-06-02 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080093 | Barracks Complex (ORTC) |  | 2012-08-30 | 2012-09-04 | FSA & JKC Joint Venture One, LLC. | W912LC-12-C-0009 | 42228 | 43823 | 2012-09-24 | 2015-02-02 | 2013-10-28 | 2015-06-30 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080206 | Tactical Unmanned Aircraft System Facility |  | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. | W912LC-12-C-0012 | 3592 | 3900 | 2012-11-05 | 2014-12-31 | 2013-10-28 | 2015-04-30 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130063 | Maneauver Area Training and Equipment Site, Ph 1 |  | 2012-01-12 | 2012-09-11 | J&S Construction Company, Inc. | W912JM-12-R-0011 | 19255 | 20542 | 2012-10-19 | 2013-11-18 | 2013-10-28 | 2015-08-15 | 0.87 | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2015-07-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130068 | Readiness Center Ph 1 |  | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC | 41100-044-0000082512 | 14457 | 14123 | 2012-09-14 | 2013-04-12 | 2014-03-14 | 2014-10-14 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130120 | Readiness Center |  | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. | 41100-044-0000082224 | 10991 | 11239 | 2012-09-10 | 2013-11-18 | 2013-10-28 | 2014-11-24 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | ILLINOIS | UNITED STATES | 171005 | Battalion Maintenance Shelter |  | 2012-09-24 | 2012-09-24 | H&N Construction | W91SMC-10-2-2005 | 1210 | 999 | 2012-10-01 | 2013-09-23 | 2013-10-31 | 2013-11-19 | 1 | 0 |  | (NGB 593)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180012 | JFHQ Add/Alt |  | 2012-09-19 | 2012-09-19 | F.A. WILHELM Construction, Inc. | MDI-SAB-13-C-0012 | 34971 | 34919 | 2012-11-15 | 2014-05-04 | 2013-10-28 | 2015-04-30 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2.000 FY09 {PN: 040026} & Formal Reprogramming $7,271 funds from FY09 project savings {PNs: 040226 ($2,540), 180116 ($3,805), 180137 ($510) and 260211 ($416)}
2015-07-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180142 | Railhead Expansion & Container Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 20908 | 19069 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180156 | Deployment Processing Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 8878 | 8255 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 0.96 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180160 | Operations Readiness Training Complex 1 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 24991 | 26136 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180161 | Operations Readiness Training Complx 2 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 27000 | 27520 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 220233 | Waste Water Treatment Facility |  | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. | LA12-C-117 | 2972 | 2881 | 2012-06-15 | 2013-07-15 | 2013-06-17 | 2014-12-02 | 1 | 0
2015-07-31 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230046 | Readiness Center |  | 2012-04-05 | 2012-09-26 | ITSI Gibane | W912JD-12-C-0003 | 14390 | 14919 | 2012-09-26 | 2015-07-01 | 2014-07-11 | 2015-09-30 | 0.97 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230071 | Armed Forces Reserve Center |  | 2012-11-10 | 2012-09-26 | J.C.N. Construction Co, Inc. | W912JD-12-C-0002 | 23058 | 24376 | 2012-09-26 | 2015-03-23 | 2014-10-12 | 2015-06-30 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-07-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240017 | Readiness Center Add/Alt |  | 2012-08-29 | 2012-09-11 | The Whiting-Turner Contracting Company | 001B3400152 | 15771 | 12074 | 2012-10-01 | 2015-06-20 | 2014-09-22 | 2015-08-31 | 0.82 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240187 | Readiness Center Add/Alt |  | 2012-07-23 | 2012-09-11 | Harkins Builders | 001B3400154 | 10296 | 8254 | 2012-10-01 | 2015-03-01 | 2014-09-22 | 2015-03-20 | 0.99 |  |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240193 | Readiness Center |  | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 001B3400155 | 9000 | 10075 | 2012-10-01 | 2015-07-11 | 2014-09-22 | 2015-09-15 | 0.81 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250135 | Readiness Center |  | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc. | MIL1001-DC1 | 8986 | 9630 | 2012-12-01 | 2013-11-18 | 2013-10-28 | 2014-10-28 | 0.75 | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2015-07-31 | 2012 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270266 | Multipurpose Machine Gun Range |  | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. | WGO010008 | 4718 | 4477 | 2012-09-17 | 2014-01-18 | 2013-12-15 | 2014-06-01 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,718)
2015-07-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEW HAMPSHIRE | UNITED STATES | 330052 | Readiness Center, Add/Alt |  | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 330052-GC | 1947 | 1943 | 2012-10-07 | 2013-07-29 | 2013-08-13 | 2013-08-13 | 1 | 0 |  | (Closeout procedures are in progress)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340115 | Army Aviation Support Facility |  | 2012-02-15 | 2012-09-19 | Senate Builders & Const Manager | W912KN-12-C-0006 | 48795 | 46258 | 2012-09-19 | 2015-01-31 | 2014-10-18 | 2015-01-31 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400605 | Upgrade: Combined Arms Collective Training Facility |  | 2012-01-12 | 2012-08-16 | Benham Companies, LLC | W90FYQ-09-D-0006-9J01 | 10343 | 9308 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2015-01-16 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400606 | Live Fire Shoot House |  | 2012-01-24 | 2012-08-15 | Benham Companies, LLC | W90FYQ-09-D-0006-9J02 | 2995 | 3161 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-06-28 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410026 | Readiness Center |  | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 410026D002 | 13800 | 13190 | 2012-12-01 | 2014-02-21 | 2013-12-28 | 2014-03-20 | 1 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430010 | Readiness Center |  | 2012-09-10 | 2012-09-18 | RB Construction Group Inc. | W912LR-12-C-0005 | 40565 | 38365 | 2012-12-01 | 2014-12-05 | 2013-10-28 | 2015-02-28 | 0.98 | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($40,565)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450403 | Readiness Center, Add/Alt |  | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. | 4600277403 | 4290 | 4255 | 2012-10-01 | 2013-09-01 | 2013-10-28 | 2013-10-28 | 0.1 | 0 |  | PL 112-25 (Budget Control Act, 2011), State Purchase Number E24-9751-CA
2015-07-31 | 2012 | Army National Guard | Major Military Construction | VIRGINIA | UNITED STATES | 510307 | Combined Arms Collective Training Facility |  | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | W912LQ-13-C-0001 | 8316 | 8874 | 2013-04-10 | 2015-04-10 | 2014-10-09 | 2015-02-27 | 0.98 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540085 | Readiness Center Ph1 |  | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | DEK 13002 | 9991 | 11545 | 2012-11-01 | 2014-08-25 | 2014-11-12 | 2014-11-12 | 0.75 | 0 |  | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550245 | Tactical Unmanned Aircraft System Facility |  | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. | NGB-47-12-C-0002 | 4250 | 3935 | 2012-07-01 | 2013-10-20 | 2013-05-20 | 2014-05-30 | 0.99 | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 011007 | National Guard Readiness Center, Add/Alt |  | 2013-09-24 | 2013-09-30 | Butler Construction Company, LLC. | AC-13-C-0051-S | 1920 | 1904 | 2013-12-31 | 2014-12-14 | 2014-10-01 | 2014-12-19 | 0.95 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010278 | Live Fire Shoot House |  | 2013-08-01 | 2013-08-27 | Hurst Construction, LLC | AC-13-C-0052-S | 5223 | 5437 | 2013-11-12 | 2015-06-08 | 2014-11-11 | 2015-06-08 | 0.98 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 040669 | Underground Electrical Lines |  | 2013-09-23 | 2014-04-04 | Ludvik Electric | M13-0037 | 2000 | 1833 | 2014-05-05 | 2014-10-31 | 2014-10-31 | 2014-10-31 | 0 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050139 | Field Maintenance Shop |  | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC | 9751312 | 6577 | 5231 | 2013-08-30 | 2015-01-15 | 2014-10-01 | 2014-10-01 | 1 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060413 | Maneuver Area Training & Equipment Site Ph 3 |  | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793 | 30572 | 2013-10-21 | 2014-10-01 | 2014-10-01 | 2015-09-30 | 0.97 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 ($1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090043 | Combined Support Maintenance Shop |  | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951 | 29988 | 2014-04-26 | 2015-10-01 | 2015-10-01 | 2015-10-09 | 0.72 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090115 | RIP RAP |  | 2014-08-28 | 2014-09-11 | Nutmeg Companies, Inc. | W91ZRS-12-D-0026-0005 | 3600 | 1398 | 2014-09-22 | 2015-03-31 | 2015-03-31 | 2015-05-27 | 1 | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 450252)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100010 | Regional Training Institute Ph1 |  | 2013-06-21 | 2013-07-25 | EDIS Company | 40325 | 5319 | 5329 | 2013-09-23 | 2014-12-15 | 2014-09-23 | 2014-12-04 | 0.99 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), Construction is finish, project completion is pending all closeout documentation
2015-07-31 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120102 | Readiness Center |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) | W911YN-11-2-2002 | 19345 | 21104 | 2014-03-03 | 2015-09-13 | 2015-07-26 | 2015-09-13 | 0.8 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120228 | Ready Building |  | 2013-09-05 | 2013-09-10 | Halfacre Construction Company | W911YN-13-2-2002 | 1939 | 1920 | 2013-10-14 | 2015-09-23 | 2015-05-16 | 2015-09-23 | 0.68 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | GUAM | GUAM | 140040 | JFHQ Ph 4 |  | 2013-08-22 | 2013-09-24 | NAVFAC Pacific | N40192-10-D-2800 | 8221 | 8089 | 2013-10-21 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 0.75 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150023 | Army Aviation Support Facility Ph1 |  | 2013-10-25 | 2014-09-26 | Watts Constructors, LLC | W912J6-14-C-0003 | 32625 | 33617 | 2014-11-12 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 0.23 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2015-07-31 | 2013 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160100 | ORTC (Barracks) Ph2 |  | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692 | 38006 | 2013-10-07 | 2014-08-01 | 2014-08-01 | 2016-03-09 | 0.77 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180106 | Field Maintenance Shop |  | 2013-09-24 | 2013-09-24 | Gamong Construction | MDI-SAB-14-C-0002 | 8705 | 8545 | 2014-07-21 | 2014-12-25 | 2014-12-25 | 2015-09-30 | 0.75 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180144 | Armed Forces Reserve Center Add/Alt |  | 2013-09-20 | 2013-09-20 | Ziolkowski Construction | MDI-SAB-14-C-0001 | 20311 | 22016 | 2014-04-21 | 2015-05-29 | 2015-08-23 | 2015-05-29 | 0.89 | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200102 | Taxiway, Ramp & Hangar Alterations |  | 2013-05-21 | 2013-06-14 | Senne & Co | W912JC-13-C-1307 | 9188 | 8555 | 2013-07-22 | 2014-05-02 | 2014-10-01 | 2014-07-04 | 0.7 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | KANSAS | UNITED STATES | 200127 | Water Distribution Lines, Portable |  | 2013-09-16 | 2013-09-24 | Harbin Construction | W912JC-12-D-5308 | 1440 | 1627 | 2014-04-07 | 2014-06-13 | 2014-06-13 | 2015-04-02 | 0.95 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210001 | Army Aviation Support Facility |  | 2013-05-17 | 2013-06-04 | DW Wilburn | CT2 1300000269 | 30953 | 26572 | 2013-07-08 | 2014-11-10 | 2014-10-01 | 2015-05-31 | 0.87 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220241 | National Guard Readiness Center |  | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300 | 8937 | 2014-09-22 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 0.05 | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353 )
2015-07-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220243 | Jackson Barracks Billeting Replacement |  | 2013-07-25 | 2014-07-25 | Gibbs Construction | LA06-C-081 | 5700 | 3817 | 2014-07-25 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 1 | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $3,000 - PN: 450252, $2,700 - PN: 450353)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 240194 | Combat Pistol/MP Firearms Qualification Course |  | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 1920 | 1788 | 2015-06-01 | 2015-09-18 | 2014-09-22 | 2015-12-18 | 0.2 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250065 | Unit Training Equipment Site |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279 | 21242 | 2014-04-07 | 2015-07-30 | 2015-07-30 | 2015-10-15 | 0.35 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250196 | Water Well, Non-Potable |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District | W912W3-11-D-0069 | 2000 | 1838 | 2013-06-03 | 2013-12-02 | 2013-12-01 | 2013-12-01 | 0 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270236 | Scout Reconnaissance Range |  | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. | 67879 | 12783 | 13455 | 2013-09-23 | 2015-08-01 | 2015-10-01 | 2016-01-01 | 0.8 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270238 | Readiness Center |  | 2013-08-08 | 2013-08-14 | LS Black Constructors | W912LM-13-C-0007 | 16443 | 17523 | 2013-09-30 | 2015-10-15 | 2015-10-15 | 2015-10-28 | 0.87 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290176 | Regional Training Institute |  | 2013-07-26 | 2013-08-01 | KCI Construction Company | T1203-01B | 17410 | 15890 | 2013-12-09 | 2015-02-28 | 2015-02-28 | 2015-07-21 | 0.98 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340110 | Regional Training Institute |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885 | 32130 | 2014-10-15 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 0.28 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340130 | Communication Lines and Ductbank, Underground |  | 2014-09-19 | 2014-09-26 | Rome Management Associates, LLC | W912KN-13-D-0029 | 2228 | 1481 | 2014-10-03 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 0.07 | 0 |  | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition |  | 2014-08-18 | 2014-09-24 | Smithco Inc. | AGND14-52 | 1194 | 2000 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-12-04 | 0.18 | 0
2015-07-31 | [10 empty] | Peterson Mechanical, Inc. | AGND14-53 | 468
2015-07-31 | [10 empty] | Grotberg Electrical, Inc. | AGND14-54 | 311
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380123 | RIP RAP |  | 2013-09-02 | 2013-12-02 | Close Construction Company | AGND14-01 | 1688 | 1889 | 2013-12-09 | 2014-08-30 | 2014-08-30 | 2015-06-30 | 0.91 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390230 | Readiness Center |  | 2013-04-01 | 2013-05-03 | Barton Marlow Company | ADJ-090001 | 11607 | 8789 | 2013-08-01 | 2015-03-13 | 2013-12-01 | 2015-03-13 | 0.99 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390256 | Field Maintenance Shop Add/Alt |  | 2013-06-07 | 2013-09-19 | Henderson Contractors, Inc. | W91364-13-D-0026 | 2998 | 3017 | 2013-11-04 | 2015-03-10 | 2014-07-02 | 2015-06-18 | 1 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), NGB 593 being reviewed
2015-07-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390263 | Hutments |  | 2014-05-12 | 2014-07-09 | KF Construction & Excavating LLC. | ADJ-140002 | 2900 | 2676 | 2014-07-16 | 2015-06-15 | 2015-06-15 | 2015-06-15 | 0.95 | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400066 | Operations Readiness Training Complex |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29197 | 27761 | 2013-10-25 | 2014-10-01 | 2014-10-01 | 2016-02-22 | 0.35 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 420542 | Controlled Access Secure Facility |  | 2014-07-22 | 2014-10-24 | Miller Bros. Construction, Inc. | W912KC-14-R-0005 | 1896 | 1908 | 2014-10-30 | 2015-11-13 | 2015-11-13 | 2015-11-21 | 0.15 | 0 |  | SIOH all in-house; awaiting NPDES
2015-07-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430081 | Readiness Center (JFHQ) |  | 2013-06-27 | 2013-09-26 | RB Construction Group Inc. | W912LR-13-C-0001 | 18294 | 17650 | 2014-03-03 | 2015-09-18 | 2015-09-18 | 2015-11-12 | 0.7 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | PUERTO RICO | 430622 | Sanitary Sewer |  | 2014-04-04 | 2014-08-27 | Integrated Construction Services, Inc. | W912LR-14-B-2005 | 1535 | 1897 | 2014-09-15 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430804 | Refill Station Building |  | 2013-06-25 | 2013-09-20 | Design Build S E | W912LR-13-C-0003 | 2128 | 433 | 2013-10-28 | 2015-05-08 | 2015-05-08 | 2015-05-08 | 0.06 | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430806 | Readiness Center |  | 2013-06-06 | 2013-09-26 | Design Build S E | W912LR-13-C-0002 | 3675 | 3667 | 2014-02-10 | 2015-05-15 | 2015-05-15 | 2015-06-19 | 0 | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | 440053 | Access Control Point |  | 2014-08-15 | 2015-01-06 | J J Cardosi, Inc | W912LD-11-D-0016 | 1032 | 1096 | 2015-01-06 | 2015-02-27 | 2015-02-27 | 2015-02-27 | 0 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490076 | BEQ Facility (Regional Training Institute) |  | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 137861 | 14508 | 15859 | 2013-08-12 | 2014-11-10 | 2014-10-01 | 2014-11-30 | 0.99 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490444 | Regional Training Institute Ph2 |  | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 137862 | 28772 | 28414 | 2013-08-26 | 2014-09-30 | 2014-09-30 | 2015-04-15 | 0.99 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | UTAH | UNITED STATES | 490803 | Unheated Aircraft Storage Hangar |  | 2013-11-06 | 2014-07-18 | Keller Construction Inc. | 147589 | 2000 | 1925 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 0.3 | 0
2015-07-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530015 | Readiness Center |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | W912DW-13-C-0044 | 33853 | 30989 | 2013-09-23 | 2015-08-28 | 2015-08-20 | 2015-09-29 | 0.9 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530035 | National Guard Readiness Center |  | 2014-08-15 | 2014-08-20 | Absher Construction | 2013-295 G(2-1) | 26000 | 23855 | 2014-10-06 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 0.3 | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540075 | Readiness Center |  | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734 | 14988 | 2014-04-07 | 2015-09-11 | 2015-09-11 | 2015-09-11 | 0.7 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550142 | Field Maintenance Shop |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673 | 9631 | 2013-10-28 | 2014-10-01 | 2014-10-01 | 2015-06-15 | 0.98 | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2014 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 011014 | National Guard Readiness Center Add/Alt |  | 2014-08-14 | 2014-08-22 | Carmon Construction, Inc. | AC-14-C-0005-S | 4000 | 3756 | 2014-10-07 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 0.35 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050182 | Scout REECE Gunnery Complex |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-B-0001 | 21000 | 16758 | 2014-10-20 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0.1 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120195 | Ready Building |  | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | W911YN-13-2-2004 | 5700 | 5300 | 2014-04-14 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 0.05 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170033 | National Guard Readiness Center |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2004-100 | 14000 | 16000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-11-01 | 0.18 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170127 | Aircraft Maintenance Hangar |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2003-100 | 28000 | 30000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-11-01 | 0.18 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250095 | Enlisted Barracks, Transient Training Addition |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000 | 20559 | 2014-09-15 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 0 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260051 | Enlisted Barracks, Transient Training |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000 | 17645 | 2014-08-11 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0.45 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270014 | National Guard Readiness Center |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000 | 18218 | 2014-10-22 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 0.3 | 0
2015-07-31 | 2014 | Army National Guard | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 281305 | Raw Sewage Lagoon and Oxidation Pond |  | 2014-09-24 | 2014-09-26 | Miller Enterprises | NGB22-14-C-0007-S | 1950 | 1039 | 2014-09-30 | 2005-04-30 | 2015-04-30 | 2015-07-15 | 0.99 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280272 | National Guard Readiness Center |  | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB22-14-C-0003-S | 4500 | 4718 | 2014-07-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280423 | Water Supply/Treatment Building, Potable |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000 | 4581 | 2014-08-15 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290191 | National Guard Vehicle Maintenance Shop |  | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01C | 9100 | 7414 | 2015-05-12 | 2012-04-30 | 2015-07-31 | 2015-06-26 | 0.72 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290221 | Aircraft Maintenance Hangar |  | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 5000 | 4459 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 2015-10-06 | 0.52 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360161 | National Guard Readiness Center Alteration |  | 2014-09-17 | 2014-09-30 | Design Resources Group Architects, A.I.A, Inc. | 44573 | 31000 | 29614 | 2014-10-20 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 0.3 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390292 | Sanitary Sewer |  | 2014-04-04 | 2014-09-04 | Rock Industries, Inc. | W91364-13-D-0003 | 5200 | 5027 | 2014-09-08 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 0.1 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420051 | Aircraft Maintenance Instructional Building |  | 2014-07-09 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 33133 | 33262 | 2014-10-20 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0.12 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430070 | Maneuver Area Training & Equipment Site Addition |  | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600 | 4418 | 2014-09-15 | 2015-05-30 | 2015-05-30 | 2015-05-30 | 0 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450131 | National Guard Vehicle Maintenance Shop |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | 460003 | 13000 | 12632 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2017-05-06 | 0.1 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450283 | National Guard Readiness Center |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | 460003 | 13000 | 12401 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0 | 0
2015-07-31 | 2014 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560081 | National Guard Readiness Center |  | 2013-12-16 | 2014-03-11 | Layton Construction Company, Inc. | 13002900601 | 10200 | 10124 | 2013-10-10 | 2015-03-31 | 2015-03-31 | 2015-12-31 | 0.75 | 0
2015-07-31 | 2015 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230113 | National Guard Reserve Center |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113-D | 32000 | 31097 | 2015-09-14 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 0 | 0 |  | Using State procedures the contract number is the same as the project number plus -D to delineate Construction
2015-07-31 | 2015 | Army National Guard | Major Military Construction | MONTANA | UNITED STATES | 300128 | National Guard Readiness Center Add/Alt |  | 2015-04-14 | 2015-04-20 | Swank Enterprises - Valier | W9124V-08-2-2001 | 38000 | 27573 | 2015-05-13 | 2017-05-31 | 2017-05-31 | 2017-05-13 | 0.01 | 0
2015-07-31 | 2015 | Army National Guard | Major Military Construction | NORTH DAKOTA | UNITED STATES | 380073 | National Guard Vehicle Maintenance Shop |  | 2015-05-28 | 2015-06-16 | T. F. Powers Construction Co. | AGND15-19 | 10800 | 12487 | 2015-07-13 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 0 | 0
2015-07-31 | 2015 | Army National Guard | Major Military Construction | VERMONT | UNITED STATES | 500036 | National Guard Vehicle Maintenance Shop |  | 2015-03-11 | 2015-04-06 | Spates Construction, Inc. | 0000000009999 | 4400 | 4458 | 2015-04-30 | 2015-10-31 | 2015-10-31 | 2015-12-31 | 0 | 0
2015-06-30 | 2013 | Defense Finance and Accounting Service | Major Military Construction | TEXAS | UNITED STATES | 80230 | DFAS Administration Building |  | 2013-04-24 | 2013-07-30 | US Army COE Guyco, INC | W9127S-09-D-6006 | 12903 | 12903 | 2013-09-11 | 2015-12-01 | 2015-03-05 | 2015-11-25 | 0.44
2015-07-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 75132 | Joint Navy-VA Project |  |  | 2013-09-27 | Billy W. Jarrett Const Co. Inc. | N62470 13 MPS 0046 | 1797 | 1899 | 2014-06-01 | 2016-01-29 | 2014-10-15 | 2016-01-29 | 0.1 |  |  | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2015-07-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81004 | Site Development, NiCOE |  | 2012-05-16 | 2012-06-05 | Sunland Builders, Inc. | N40085 09 D 9027 DO 0026 | 1363 | 1452 | 2012-08-01 | 2013-08-12 | 2013-08-29 | 2013-08-29 | 1 |  |  | Project is not financially closed.
2015-07-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction |  | GERMANY | 68974 | Computer Operations Center |  | 2011-02-01 | 2011-04-22 | Federal Republic of Germany | W912GB-09-D-0048 | 378 | 402 | 2011-05-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 1
2015-07-31 | [8 empty] | 2011-01-08 | 2011-03-14 | Wayss & Freytag |  | 1572 | 1548 | 2013-04-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 1
2015-07-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 77342 | Bldg 509 Alteration of Medical Laboratory |  | 2010-12-17 | 2011-01-28 | Odyssey International, Inc. | W912DR-11-C-0011 | 3294 | 3690 | 2011-02-16 | 2011-09-15 | 2011-09-15 | 2011-08-15 | 1 |  |  | Project is closed out;
2015-07-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 80093 | Medical Ed. & Training Facility |  | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc. | W9126G-09-D-0105 | 1698 | 1982 | 2012-08-14 | 2014-09-10 | 2013-11-14 | 2014-08-24 | 1 |  |  | Switch gear was changed on 18 FEB 2015. Project complete. No punch list items. Contract/project closeout and Evaluation not completed. All else is done.
2015-07-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction |  | JAPAN | 78853 | New Clinic Addition | [14 empty] | DHA issued DA memo dated 22 Dec 2014 cancelled the FY11 project. FY11 funds ($46,355.39) were revoked on 24 Jul 2015. No unobligated funds remain. Awaiting HQUSACE code 8 (Project Cancelled) design directive.
2015-07-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80792 | Site Development, NiCOE |  | 2012-06-18 | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service | W81W3G22363343 / 22443665 / 22443666 / 30793685 | 1600 | 1690 | 2012-09-10 | 2013-06-30 | 2013-05-31 | 2013-08-29 | 1 |  |  | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Project financial closeout is ongoing. Update 03 AUG 2015: Received release of claims from American Water and returned all unobligated MIPR'd funds. Still waiting for return of unobligated MIPR'd funds requested by POC for Dominion Virginian Power. Once these funds are returned project will be closed out.
2015-07-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80094 | Veterinary Clinic |  | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc. | W912BV-12-C-0030 | 1692 | 1710 | 2013-01-04 | 2014-12-12 | 2014-07-05 | 2014-12-12 | 0.98 |  |  | BOD Issued 12 Dec 14. LEED - Synergy resubmitting 22 June to address comments from USGBC. Final CADD As-Built's and O&M's turned over to BCE. O&M approved, As-Builts will require some modification after review by BCE. Landscape/Site has not yet been accepted. KTR slow to address punchlist items, serial letter is being drafted directing the work and dates for completion. LEED - Synergy has not resubmitted to USGBC to address earlier comments. Final O&M approved, As-Builts being modified by KTR after review/comment by BCE. Landscape/Site has not yet been accepted. Most punchlist is completed, however, unacceptable grass establishment needs addressing.
2015-07-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 82358 | Veterinary Clinic Replacement |  | 2015-05-28 | 2015-08-30 | [11 empty] | Cost reduction measures incorporated new HQCWE is $1.8M. DHA has increased PA to $1.9M. Received Authority to Advertise on 26 Apr 15. Advertised 09 Jul 15. Bids due on 11 Aug 15.
2015-07-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | DELAWARE | UNITED STATES | 86204 | Medical Warehouse Add/Alt |  | 2015-08-04 | 2015-09-30 | [11 empty] | Market Research completed. District seeking 8a waiver from SBA. Code A provided 15 Jun 15.
2015-07-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81631 | NiCOE Satellite, Infrastructure Support |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc. | W912HN-11-D-0043-0044 | 1436 | 1438 | 2014-06-30 | 2015-11-30 | 2016-02-01 | 2016-02-01 | 0.71 |  |  | The NiCOE Contractor (WM Jordan) on-going construction work on new clinic. WM Jordan has a weathered in roof, interior stud walls, primary duct work, and fire sprinkler mains installed. WM Jordan continues with masonry walls, electrical , communications, and plumbing rough-in. Site Contractor is installing curb and gutter in the Southern Parking Lot. Contingencies in district: $24,739.38
2015-07-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 81706 | NiCOE Satellite, Infrastructure Support |  | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 1795 | 1760 | 2014-09-15 | 2015-10-28 | 2015-10-28 | 2015-10-28 | 0.82 |  |  | The installation of the pad mounted transformer is complete as of 13 Jul 15. This completes all of phase II work. Phase III work is expected to begin on 2 Sep 15.
2015-07-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 1 |  | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 | 757737 | 774314 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 1
2015-07-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005A | Medical Center Add/Alt, Inc 2 | 005V | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 1 |  |  | Not financially closed. Final invoicing for equipment.
2015-07-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005B | Medical Center Add/Alt, Inc 3 | 005V | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 1
2015-07-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MISSISSIPPI | UNITED STATES | 478V | Community Hospital |  | 2009-04-01 | 2009-11-10 | W.G. Yates & Sons Construction Co. | N69450 10 C 0763 | 38252 | 42256 | 2010-01-01 | 2012-02-25 | 2011-09-11 | 2012-10-11 | 1 |  |  | Not financially closed. Final invoicing for equipment - working with DLA.
2015-07-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69427 | Hopsital Replacement, Inc 1 |  | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV | W91236-07-C-0053 | 649025 | 9428 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 1 |  |  | Project ready for closeout
2015-07-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69865 | Hopsital Replacement, Inc 4 | 69427 | 2007-06-12 | 2010-01-23 | Turner/Gilbane JV | W91236-07-C-0053 |  | 119266 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 1 |  |  | All Unobligated funds $245K were returned. 1354 is being prepared.
2015-07-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 77071 | Hopsital Replacement, Inc 5 | 69427 | 2007-06-12 | 2010-10-20 | Turner/Gilbane JV | W91236-07-C-0053 |  | 211800 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 1 |  |  | See above.
2015-07-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 1 |  | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 107589 | 135926 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 1 |  |  | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2015-07-31 | 2009 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64180 | San Antonio Regional MEDCEN, Inc 2 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 265100 | 279273 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 1 |  |  | See above.
2015-07-31 | 2010 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 69840 | San Antonio Regional MEDCEN, Inc 3 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 13748 | 243943 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 1 |  |  | See above.
2015-07-31 | 2011 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 70990 | San Antonio Regional MEDCEN, Inc 4 | 64179 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 37554 | 85520 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 1 |  |  | See above.
2015-07-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64188 | Health Clinic |  | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | W9126G-08-C-0024 | 33382 | 37382 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 1 |  |  | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2015-07-31 | 2010 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64241 | Dental Clinic |  | 2009-09-16 | 2010-05-04 | Forrester Construction Company | W912DR-10-C-0067 | 7541 | 8818 | 2010-05-18 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 1 |  |  | Construction Contract and Project in Close Out Phase. Final 1354 for CIP Transfer is in process. Fiscal Closeout now 31 OCT 2015, along with PN 71251.
2015-07-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 64156 | USAMRICD Replacement, Inc 1 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398 | 17027 | 2010-03-15 | 2015-06-30 | 2013-06-01 | 2015-06-10 | 0.99 |  |  | Final BOD for Building E was 10 Jun 15 with a follow on contract to investigate and fix systems commissioning and fume hoods in the lab. Currently working to get Facility Dynamics Engineering under contract to trouble shoot and establish COAs/Solutions to resolve the problems. Project fiscal closeout will follow pending resolution of remaining punchlist items and settlement of outstanding requests for equitable adjustment.
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77000 | Public Health Command Laboratory Replacement | 64156 | 2014-03-24 | 2015-08-07 | [11 empty] | The new scheduled award date is Friday, 7 August. DOL has just issued an updated wage determination, and during our award package external peer review we were informed that we must issue an amendment to the solicitation incorporating the new wage rates. This is a FAR requirement for any wage rate updates issued prior to award. An amendment was issued on 30 July 2015 asking offerors to acknowledge the new wage rates, confirm pricing, and to extend until next Friday. Offerors will have until 03 August 2015 to respond.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 65270 | Hospital Replacement, Inc 1 |  | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133 | 166777 | 2010-11-01 | 2014-03-18 | 2014-10-15 | 2016-03-15 | 0.99 | 71119 | FY13 - PN80308 FY10 - PN61401 | 3rd UXO found; work is stopped, but has restarted
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77154 | Ambulatory Care Center, Inc 1 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 197804 | 138256 | 2013-03-01 | 2016-11-01 | 2016-12-06 | 2018-01-01 | 0.67 |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 81291 | Ambulatory Care Center, Inc 2 | 77154 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 |  | 66430 | [7 empty] | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 |  | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 6887.87 | 7070.1979 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 1 |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC
2015-07-31 | [8 empty] | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 12000 | 12658 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 1 |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC. $9,000 rescinded as a result of Sequestration (04/29/13).
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67180 | USAMRICD Replacement, Inc 2 | 65731 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 1
2015-07-31 | [8 empty] | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 1
2015-07-31 | [8 empty] | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 100375 | 103745.3283 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 1 |  |  | Main Building $142,857,143 FY10 Increment Awarded at $100,375,000 on 5 Mar 10 ($109,567,007 funded per D. Pritchett 17 Mar 10 email)
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67181 | USAMRICD Replacement, Inc 3 | 65731 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 94608 | 96044.5065 | 2010-03-15 | 2015-06-30 | 2013-06-01 | 2015-06-10 | 0.99 |  |  | Full FY11 MILCON increment placed against contract.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67182 | USAMRICD Replacement, Inc 4 | 65731 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915.345 | 31686 | 2010-03-15 | 2015-06-30 | 2013-06-01 | 2015-06-10 | 0.99 |  |  | Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 30 Apr 2015 for remainder of spaces. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15.
2015-07-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657 | 2657 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 1 |  |  | Work complete. Contracts closed.
2015-07-31 | [8 empty] | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 1 |  |  | Work complete. Contracts closed.
2015-07-31 | [8 empty] | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 1 |  |  | Work complete. Contracts closed.
2015-07-31 | [8 empty] | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 1 |  |  | Work complete. Contracts closed.
2015-07-31 | [9 empty] | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 2866 | 2866 | 2008-07-15 | 2013-12-06 | 2011-05-06 | 2013-10-31 | 1 |  |  | Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project.
2015-07-31 | [8 empty] | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 15736 | 16161 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 0.95 |  |  | FY07. See FY2012 remarks. Contract active, but all funds on this increment obligated. Building to be operational NOV 2017.
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63418 | USAMRIID Replacement, Incr 2 | 58395 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 131264 | 138491 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 0.95 |  |  | FY 08. Contract completion date is 16 Dec 14; liquidated damages will be assessed.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63419 | USAMRIID Replacement, Incr 3 | 58395 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 185526 | 185630 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 0.95 |  |  | FY09. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract complete date is 16 Dec 14; liquidated damages will be assessed.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63420 | USAMRIID Replacement, Incr 4 | 58395 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 94000 | 100180 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 0.95 |  |  | FY10. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract completion date is 16 Dec 14; liquidated damages will be assessed.
2015-07-31 | [9 empty] | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 496 | 525 | 2008-07-15 | 2013-12-06 | 2013-10-31 | 2013-10-31 | 1 |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65324 | USAMRIID Replacement, Incr 5 | 58395 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 13497 | 12893 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 0.95 |  |  | FY11. See FY2012 remarks. Contract active, but all funds on this increment obligated. Contract completion date is 16 Dec 14; liquidated damages will be assessed. Approx $90,000 FY2011 P&D funds for parking design being returned.
2015-07-31 | [9 empty] | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603 | 638 | 2008-07-15 | 2013-12-06 | 2013-10-31 | 2013-10-31 | 1 |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71101 | USAMRIID Replacement, Incr 6 | 58395 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 66955 | 85381 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 0.95 |  |  | FY12. Scheduled 100%, Actual 95%. T&E change under negotiation with contractor. Re-installation of BSL4 lab coatings is 90% complete; cleaning smoke-damaged BSL3 area equipment, and commissioning remainder of facility. Plan is to accept admin, BSL2 and BSL3 labs Jun 2016 to start CDC certification and accept BSL4 labs Jul 2017. Contract completion 16 Dec 14; liquidated damages will be assessed. Still Request additional FY 12 project line item for next report relating to Contract 6 (North Parking).
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78210 | USAMRIID Replacement, Incr 7 | 58395 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 0 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2017-07-01 | 0 |  |  | Utilities, DDC, Certification and related costs.
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78211 | USAMRIID Replacement, Incr 8 | 58395 | 2015-01-22 | 2020-05-29 |  |  |  | 0 | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2017-07-01 | 0 |  |  | Remainder of certification costs this FY. South parking/demolition is budgeted for this PN but facilities are likely not able to be available for demolition until funds expire. We will coordinate a way ahead on this when main facility is closer to turnover.
2015-07-31 | [8 empty] | 2017-04-01 | 2017-08-01 |  |  |  | 0 | 2019-08-22 | 2020-10-21 | 2020-08-22 | 2020-10-31 | 0 |  |  | Notional schedule shown; dependent on CDC/DA Safety certification of USAMRIID primary facility and vacation/decommissioning of existing buildings 1408/1412/1414/1415. Due to delay in main contract, projections for award are moved out 2 years.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 |  | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 7782 | 11366 | 2013-05-29 | 2018-05-26 | 2016-11-26 | 2017-01-01 | 0.32 |  |  | NOTE 1 : Hospital - Construction Progress: Sch. 50% Act. 32%: Current contractual construction completion date is 1 Jan 2017. The estimated construction completion is currently 4th Q 2017 with a BOD of 3 Oct 2017. Placement to date: $205.4M as of 03 Aug 15. Momentum, subcontractor control, and quality continue to suffer setbacks in production of concrete, framing, roof, and CMU work. These quality and production issues are currently being addressed including backfill and onsite materials storage. Currently Hospital SOMD activities are complete through the 6th floor. 7th floor placement has begun; roof/penthouse level installing penetrations and available for rod busters (materials are currently being staged). Small light weight concrete roof placements continue throughout hospital. No hospital SOG placements have been accomplished since last report. Post and Girt continue throughout first four floors. Interior framing continues despite disagreement in isolated areas between prime and USACE direction; KTR has submitted revised shop drawings as of this week to validate direction, however variances are requested and we are currently evaluating. Hospital spray fire proofing continues along with MEP work. East Clinic progressing well: approx. 100% heavy steel up with decking complete through level 5; concrete deck placements have started through level 2; KTR anticipates framers to start within two weeks. West Clinic lagging East Clinic and is currently 75-80% complete. Admin erection of steel started 5 July with good progress to date; no issues. CUP progressing well with MEP, CMU, and roofing. Requirement for a second superintendent remains unaddressed; KTR has issued a letter indicating no one available. Potential AQC replacement has been informally submitted and appears to have potential; we anticipate it being accepted. SWF OC has responded to CMHP FOIA requesting further definition of what documents are required. No response back from CMHP to date. IO&T Execution Contract: Targeted for FY15 year-end award. At risk pending PARC review and resolution of concerns regarding procurement of equipment. * The principals held a "reset" meeting on Thursday, 30 Jul at SWF. The designer, construction contractor and the Government revisited the business rules and issued resolutions for the remainder of the project in an attempt to regain trust among the execution level team. A dashboard will be implemented as a tool for the principals to gauge issue resolution and provide timely and relevant information to the principals as well as help improve accountability among the team. * Possible $50M decrement to the FY16 increment being considered by Congress. If approved, an FY17 project would have to be created with a PA of $50M. No update.
2015-07-31 | [8 empty] | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345 | 47508 | 2011-11-02 | 2013-10-12 | 2013-08-13 | 2013-08-29 | 1 |  |  | Construction 100% Complete
2015-07-31 | [8 empty] | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 1 |  |  | Construction 100% Complete
2015-07-31 | [8 empty] | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848 | 3879 | 2012-08-28 | 2013-10-17 | 2013-06-19 | 2013-06-11 | 1 |  |  | Construction 100% Complete
2015-07-31 | [8 empty] | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960 | 2800 | 2014-07-30 | 2015-08-27 | 2014-09-28 | 2015-08-27 | 0.81 |  |  | Sch. 90% Act. 81%. The contractor began construction 3 Nov 14. Approximately 9577 lf of pipe has been installed. Contract Required Completion was 10 Aug 15; however, the contractor submitted a request for additional time and cost due to differing site conditions. EPWU finalized negotiations on this mode resulting in an additional 21 days and $98,576K with a revised contract required completion date of 27 Aug 15. Delay will not impact overall project.
2015-07-31 | [8 empty] | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047 | 4047 | 2012-09-04 | 2015-09-16 | 2014-01-04 | 2014-01-04 | 1 |  |  | Construction 100% Complete
2015-07-31 | [10 empty] | Temp Electric Contract | W9126G-11-P | 46 | 46 |  |  |  |  | 1 |  |  | Temp power costs.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77251 | Fort Bliss Hospital Repl, Incr 2 | 72481 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 68076 | 68076 | 2013-05-29 | 2018-05-26 | 2016-11-26 | 2017-01-01 | 0.32 |  |  | See Note 1 above.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72786 | Fort Bliss Hospital Repl, Incr 3 | 72481 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 69851 | 72931 | 2013-05-29 | 2018-05-26 | 2016-11-26 | 2017-01-01 | 0.32 |  |  | See Note 1 above.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 76558 | Fort Bliss Hospital Repl, Incr 4 | 72481 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 79914 | 165837 | 2013-05-29 | 2018-05-26 | 2016-11-26 | 2017-01-01 | 0.32 | 77163 | FY09 - PN00180 | See Note 1 above.
2015-07-31 | [8 empty] | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540 | 657 | 2013-10-21 | 2014-11-24 | 2014-10-24 | 2014-10-24 | 1 |  |  | Only the re-seeding of the Helipad area remains as a punchlist item; to be completed in Aug 2015.
2015-07-31 | [9 empty] | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479 | 1538 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-08-10 | 0.81 |  |  | Sch. 90% Act. 81%. The contractor began construction 3 Nov 14. Approximately 9577 lf of pipe has been installed. Contract Required Completion was 10 Aug 15; however, the contractor submitted a request for additional time and cost due to differing site conditions. EPWU finalized negotiations on this mode resulting in an additional 21 days and $98,576K with a revised contract required completion date of 27 Aug 15. Delay will not impact overall project.
2015-07-31 | [9 empty] | 2015-02-15 |  |  | 5562 | [5 empty] | 0 |  |  | Parking Package “B”:(small business- LPTA) Est. Award: $5.5M •Solicitation Package is complete. •Proposed Award Date: FY16
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77293 | Fort Bliss Hospital Repl, Incr 5 | 72481 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 198148 | 93144 | 2013-05-29 | 2018-05-26 | 2016-11-26 | 2017-01-01 | 0.32 |  |  | See Note 1 above.
2015-07-31 | [8 empty] | 2014-10-20 | 2014-12-10 | ACPs |  | 24755 | [5 empty] | 0 |  |  | ACP Package: (small business-Best Value) Est. Award: $24.7M •Solicitation package is complete. •Proposed Award Date: FY16
2015-07-31 | [9 empty] | 2015-03-30 | CAT E Equipment |  | 33125 | [5 empty] | 0 |  |  | No update this reporting period.
2015-07-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81047 | Fort Bliss Hospital Repl, Incr 6 | 72481 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 225199 | 85171 | 2013-05-29 | 2018-05-26 | 2016-11-26 | 2017-01-01 | 0.32 |  |  | See Note 1 above.
2015-07-31 | [8 empty] | 2015-03-30 | 2016-03-28 |  |  | 22616 | [5 empty] | 0 |  |  | Landscaping Package: (small business-LPTA) Est. Award: $22.7M •Solicitation package is complete. •Proposed Award Date: FY16.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 76038 | 79206 | 2012-11-01 | 2016-04-06 | 2014-07-29 | 2015-09-30 | 0.95 |  |  | 1. Construction Progress: Sch. 95%, Act. 95% 2. The current Ph 3 completion date is 30 Sept 2015 with a pending modification that will extend the completion date to approximately 30 Nov 3. Including the estimated cost of pending modifications the CWE remains within the current authorization 4. The BOD will shift from 1 Oct to 22 Dec 2015
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 80793 | Ambulatory Care Center Phase 3, Inc 2 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319 | 22371 | 2012-11-01 | 2016-04-06 | 2014-07-29 | 2015-09-30 | 0.95 |  |  | See Note 2 above.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  | 2012-03-15 |  | W912GB-10-C-0031 | 16787.2 | 16787.2 | 2014-01-13 |  | 2021-07-20 | 2021-12-31 | 0.05 |  |  | Environmental Compensation Also includes: Lots 7.2-7.4 Initial Compensation Measures - German government solicitation and award dates to German industry are estimated.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 265 | 265 | 2014-01-20 |  | 2014-04-04 | 2014-04-04 | 0.99 |  |  | Lot 1 Temporary Construction Fence - Construction essentially completed April 2014, with remaining access from the east closed off as of 1 May 2015. FRG Security Contractor is on site and will monitor access from the L369 construction gate on the west side.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 694.489 | 1711.694 | 2014-06-16 | 2014-08-29 | 2014-10-29 | 2015-01-21 | 1 |  |  | Lot 2.1 Demolition, Site Clearing - Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Final inspection held on 21 Jan 2015, and final contract document provided by FRG (ABG7).
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 5320 | 5320 | 2015-04-20 | 2016-04-30 | 2016-04-30 |  | 0 |  |  | Lot 2.2 Mass Grading - Contract solicitation went out on 11 Dec 2014; bid opening was 10 Feb 2015. NAU signed the ABG4 (contract to FRG) on 20 Apr 2015, LBB to countersign and awarded to industry 22 Apr 2015. Contract amount is $5.3M, substantially less than expected. Contractor mobilization began on 18 May 2015.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 10000 | 10000 | 2016-01-15 | 2016-01-15 | 2016-12-15 | 2016-12-15 | 0 |  |  | Lot 3.1 Utilities to site - original ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines. Change coordinated with DHA-Europe; 100% water supply will now come from civilian lines with redundancy. Change will also reduce risk in meeting German hygiene requirements for water supply. Re-design of water line complete in April 15;FRG currently preparing new solicitation package. Solicitation target is Jun 2015.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 141.235 | 141.235 | 2014-08-22 | 2015-03-30 | 2015-03-30 | 2015-05-01 | 1 |  |  | Lot 3.2 Traffic Light System - The Traffic Light System will be operational to coincide with the opening of the L369 construction gate on approx 1 May 2015.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 17.713 | 17.713 | 2014-10-08 | 2014-12-31 | 2014-12-31 | 2014-12-31 | 1 |  |  | Lot 3.3 Construction Sign - Completed in December 2013.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 482.902 | 482.902 | 2014-08-11 | 2014-10-16 | 2014-10-16 | 2014-10-16 | 1 |  |  | Lot 3.4 Gas Line Relocation - Construction complete.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 19335 | 19335 | 2016-05-30 | 2016-05-30 | 2018-02-28 | 2018-02-28 | 0 |  |  | Lot 3.5 Transformers/Substation - This portion of the ROBMCR project will be accomplished as a direct project through NAU. NAU currently coordinating D/B RFP package with target solicitation Jan/Feb 2016 and construction contract award targeted for May 2016.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 1000 | 1000 | 2015-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 0 |  |  | Lot 3.6 Water Connection to WZV-Weilerback system - The FRG will coordinate the connection requirements with water provider SWK. Dates forthcoming.
2015-07-31 | [9 empty] | 2012-03-15 |  | W912GB-10-C-0031 | 5339.748 | 5339.748 | 2014-12-10 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 0.01 |  |  | Lot 3.9 Site Security - FRG awarded contract in Dec 2013. Security contractor has mobilized and began operation on-site starting 1 May 2015.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  | 2012-03-15 |  | W912GB-10-C-0031 | 2500 | 2500 | 2015-11-30 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 0 |  |  | 3.10 Site Logistics - Details to be determined by FRG; contract will be for execution of the entire internal and external construction site logistics.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  | 2012-03-15 |  | W912GB-10-C-0031 | 82 | 82 | 2015-06-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 0.25 |  |  | Removal of X- Area Fencing - Coordination of the fence removal is underway.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  | 2012-03-15 |  | W912GB-10-C-0031 | 1 | 1 | 2014-10-23 | 2014-12-31 | 2014-12-31 | 2014-12-31 | 1 |  |  | Communications Cable relocation - Action 100% complete
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 | 76007 |  | 2012-03-15 |  | W912GB-10-C-0031 | 586 | 586 | 2015-03-30 | 2021-12-30 | 2021-12-30 | 2021-12-30 | 0 |  |  | Construction Additional Services
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction |  | GERMANY | 72661 | Medical Center Replacement, Incr 2 | 76007 |  | 2013-08-27 |  | W912GB-10-C-0031 | 59786.775 | 59786.775 | 2016-01-15 | 2016-12-30 | 2016-12-30 | 2016-12-30 | 0 |  |  | Construction Measures, Roadways, & Site Utilities - FRG revising and coordinating lot requirements for campus roadways, utilities, and additional construction measures not included in current lot packages.
2015-07-31 | [9 empty] | 2013-08-27 |  | W912GB-10-C-0031 | 39286 | 39286 | 2016-04-15 | 2018-04-15 | 2016-04-15 | 2016-04-15 | 0 |  |  | Lot 4 Access Control Point, Bridge, External Roadways - 65% OTS design review scheduled for August 2015. German government solicitation and award dates to German industry are estimated.
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction |  | GERMANY | 72662 | Medical Center Replacement, Incr 3 | 76007 |  | 2015-08-31 |  | W912GB-10-C-0031 | 60551 | 60551 | 2017-03-28 | 2019-04-30 | 2019-04-30 | 2019-04-30 | 0 |  |  | Lot 5.1 Parking Structures, Campus Roadways - Previously included in MedCen 20% design. FRG kicked off post 20% design on 9 Dec 2014. The FRG's AE is working on the next stage of design and coordinating with NAU. Schedule forthcoming.
2015-07-31 | 2015 | Defense Health Agency | Major Military Construction |  | GERMANY | 76872 | Medical Center Replacement, Incr 4/5 - 2015/2016 | 76007 |  | 2016-03-31 |  | W912GB-10-C-0031 | 593454 | 593454 | 2019-02-12 | 2022-11-08 | 2021-12-08 | 2022-03-30 | 0 |  |  | Medical Center (Bed Tower, D&T, Clinics, Admin) - US led 20% MedCen final design submitted 2 Aug 2013. USACE is transitioning design to FRG. FRG AE target selection date is now September 2015 for follow-on 20-100% design. FRG solicitation and award dates to German industry are estimated
2015-07-31 | 2007 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 52330 | Clinic Replacement, Inc 1 |  | 2007-02-16 | 2007-07-19 | Caddell Construction Co. Inc. | W91278-07-C-0037 | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 1 |  |  | Water intrusion problem update – Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. Construction Contractor reviewed their records and provided a response to AF reports 30 Jan 2015. A-E provided response on 2 Feb 2015. CESAM reviewed responses and is currently negotiating acquisition of building envelope specialist to prepare independent determination addressing the responsibilities of each party and estimate of damages by each party. Awarded pending. We expect initial findings within 180 days of award.
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 67647 | Clinic Replacement, Inc 2 | 52330 | 2007-02-16 | 2007-07-19 | Caddell Construction Co. Inc. | W91278-07-C-0037 | 32890 | 42183 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 1 |  |  | See 52330, Clinic Replacement, Inc 1
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71857 | Hospital Addition |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 31112 | 32854 | 2010-12-03 | 2013-07-15 | 2013-01-12 | 2013-07-15 | 1 | 28938 | PN - 59215 PN - 00101 PN - 53577 PN - 77154 | Funds used for FY00 Settlement, Ft. Wainwright. Residual activity on project funding items.
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) |  | 2009-04-08 | 2009-09-28 | Turner Construction Company | W912HN-09-C-0045 | 230018 | 275275 | 2009-10-22 | 2014-05-19 | 2013-02-03 | 2014-05-19 | 1 | 49919 |  | Commissioning of systems continues. Final TAB reports resubmitted and in review. Contingencies at District: $1,307.17. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 30 Oct 15. Benning DPW will assign # upon receipt of final 1354.
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | KANSAS | UNITED STATES | 47298 | Hospital Replacement |  | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110 | 282778 | 2010-05-03 | 2015-07-01 | 2013-07-23 | 2014-05-13 | 0.99 | 61000 | PN - 72754 | 7/24/15 Fort Riley Replacement Hospital. Current CCD: 13 May 2014 Placement: 99% actual vs. 100% scheduled (as of June's pay estimate). Construction in progress: TAB/commissioning nearing completion (Two exhaust fans remain). Inspections continue. Final inspections are progressing. Numerous life safety deficiencies remain unaddressed. HFPA furniture install started 06 July. Comments: The contractor exceeded the required completion date of 13 May 2014. Liquidated damages are being withheld at $16,500 per calendar day. Corporate/senior manager engagement continues. Prefinals are complete ground to L4; L5 mech space remains. Finals are 99% complete ground to L4; L5 still to do. TAB only has the 2 exhaust fans to finish (in process). No good estimate as to when BOD will actually occur. First patients will be in the building in mid-Jan. Ribbon cutting currently scheduled for 5 Jan.
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 63864 | Health Clinic Add/Alt |  | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | W91DS-08-C-0019 | 27483 | 35963 | 2008-11-07 | 2012-12-01 | 2011-02-18 | 2013-12-12 | 1 | 1000 | PN - 67647 | Award CWE
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69626 | Burn Rehabilitation Center |  | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | W9126G-08-C-0036 | 18512 | 19120 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 1 |  |  | Contract closeout ongoing.
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 64473 | Medical/Dental Clinic |  | 2008-07-29 | 2008-09-18 | The Korte Company | 912DW-08-C-0018 | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 1 |  |  | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2015-07-31 | 2008 | Defense Health Agency | Major Military Construction |  | GERMANY | 52332 | Medical Clinic Replacement |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 1 | 100 |  | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. German government confirmed 23 Jun 2015 that resolution will not be this fiscal year.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 71653 | Hospital Replacement (ARRA) |  | 2010-06-11 | 2010-09-01 | Clark/McCarthy, JV | N62473 10 C 0001 | 418039 | 425895 | 2010-12-03 | 2013-10-17 | 2014-01-07 | 2014-01-07 | 1 |  |  | Multiple residual closeout issues.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 73599 | Hospital Renovation & MRI Addition (Cong Add) |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178 | 29202 | 2010-12-03 | 2015-08-11 | 2015-01-02 | 2015-10-16 | 0.98 | 22803 | PN - 76558 | Active Project.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 55918 | Central Utility Plant |  | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034 | 13672 | 2009-10-01 | 2011-06-22 | 2011-02-07 | 2011-06-22 | 1 | 15121 | PN - 78146 | Residual closeout issues.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 70350 | Hospital Alteration (ARRA) |  | 2011-07-26 | 2011-09-15 | Federal Contracting DBA Bryan Construction | W9128F-06-D-0019 | 15929 | 20393 | 2011-11-08 | 2014-03-23 | 2013-11-27 | 2014-01-21 | 1 |  |  | Project closed. Returned unobligated FY09 funds in the amount of $39,330.97 on 17 Apr 15.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 70354 | Hospital Replacement (Supplemental) |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 159834 | 188955 | 2012-05-30 | 2017-07-16 | 2015-03-16 | 2017-05-17 | 0.39 | 92680 | FY13 - PN76558 | Significant changes in processes impacting water storage and the central utility plant are being resolved. Full impact of the changes on the project are unknown and continue to be addressed by the delivery team. Senior leadership continues to engage regularly to assist in resolution of project issues. Engineers continuously evaluating project design to identify concerns and remedies for way-ahead. Time impacts associated with past changes are currently in negotiation which should not result in considerable growth in time beyond previously reported. Senior leadership continues to engage regularly to assist in resolution of project issues. Team is working through engineering challenges impacting concrete decks and mechanical systems. Resolution anticipated by early August 2015. A Concrete deck conference was held by engineers from all stakeholder agencies. There is agreement on the way ahead with regard to the concrete decks and engineering concerns. The PDT is engaging the MCX for concurrence on the way ahead. All other unaffected work activities are continuing per plan. No other changes.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 79845 | Eglin Hospital Alteration (ARRA) |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction Company | W9126G-08-D-0057 | 51133 | 59456 | 2011-10-31 | 2015-03-12 | 2014-11-06 | 2015-07-28 | 0.99 |  |  | Contract including all currently identified modifications is at 99.58% of PA. Hospital Command moved into new building Dec 19. Urology, ENT, Lab II, Surgery Phase III move in also completed mid December. Contractor currently working punch list in PET/CT. Scheduled acceptance Aug. 3. User requested equipment mod is only item outstanding. Joint Commissioning is competed and generated no action items for the project to correct.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 59220 | Hospital Add/Alt (Supplemental) |  | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500 | 29404 | 2011-10-26 | 2015-07-15 | 2014-03-03 | 2015-07-15 | 0.99 | 5537 | FY13 - PN76558 | Modification was issued to extend contract completion to 20 Jul 15. Punch out completed on all floors. Exterior sitework ongoing.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) |  | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 76944 | 84365 | 2011-10-25 | 2015-03-18 | 2014-09-09 | 2015-04-17 | 0.99 | 22793 | FY13 - PN76558 | Exterior plenum work will go to a Service Disabled (SD) company with MILCON funding. RFP to perspective SD contractors by 10 July. All mod work completed. Punchlist significantly reduced to 12 items and effort continues to resolve all issues. Construction has been substantially complete since 17 Apr 2015. Hospital planning a 31 July ribbon cutting.
2015-07-31 | [8 empty] | 2011-03-07 | 2011-03-20 | A1 Tree Service |  | 9.6 | 9.6 | 2011-03-20 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 1 |  |  | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2015-07-31 | [8 empty] | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp | W912QR-11-C-0027 | 5395 | 5395 | 2011-07-01 | 2015-03-18 | 2014-09-27 | 2015-03-18 | 0.99 |  |  | Leased Swing Space awarded for risk mitigation.
2015-07-31 | [8 empty] | 2015-07-10 | 2015-08-30 | MATOC | [7 empty] | 0 |  |  | Exterior plenum work will go to a Service Disabled (SD) company with MILCON funding. Bids due from SD contractors by 13 Aug. All mod work completed and less than six punchlist items to be completed by 18 Sep. Construction has been substantially complete since 17 Apr 2015. Hospital ribbon cutting was 31 July 2015.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 62189 | Medical / Dental Clinic Replacement |  | 2008-10-27 | 2009-04-03 | Hensel-Phelps Const. Co. | W912BV-09-D-2016 | 47615 | 51375 | 2009-06-01 | 2012-06-04 | 2011-10-26 | 2012-02-09 | 1 | 7033 | FY09 - PN00001 VCOE FY13 - PN76558 | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub.
2015-07-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) |  | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989 | 549904 | 2010-11-08 | 2015-07-17 | 2014-05-31 | 2015-07-17 | 0.98 | 3850 | FY09A - PN100040 | CUP: final commissioning activities for electrical/mechanical/plumbing systems continue. Clinics: contractor working IO&T in all clinics. Hospital- continuing to work punchlist items on all floors. Garages: Contractor continues finishing work. Site: Contractor continues to work on parking lot repairs; site work is expected to be complete at the end of August.
2015-07-31 | [8 empty] | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc |  | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 1 |  |  | Construction 100% Complete
2015-07-31 | [8 empty] | 2010-02-12 | 2010-03-08 | TTG Utilities, LP | W9126G-10-C-0032 | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 1 |  |  | Construction 100% Complete
2015-07-31 | [8 empty] | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc. | W912DY-05-D-0011 | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 1 |  |  | Construction 100% Complete
2015-07-31 | [10 empty] | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0002 |  | 10156
2015-07-31 | [8 empty] | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0003 | 17290 | 15383 | 2011-01-06 | 2013-12-15 | 2012-06-29 | 2015-06-30 | 0.99 |  |  | Contractor working on additional punchlist items and close out documentation.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement |  | 2010-06-16 | 2010-12-14 | Vinci Construction UK Ltd. | CT/INT21/13625 | 13098 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 1 | 205 | PN - 14010 | Estimated financial closure: 31 Dec 2015. The base originally requested an additional $65,000 to replace the clinic main entrance doors. This was inadequate and a further $80,000 has been requested. Base will now have $145,000 to replace the doors.
2015-07-31 | [8 empty] | 2013-04-05 | 2013-06-15 | VolterFitzpatrick |  | 68 | 68 | 2013-07-01 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 1
2015-07-31 | [8 empty] | 2014-08-20 | 2014-08-25 | Vinci Facilities | CT/INT21/13625 | 69 | 69 | 2015-03-03 |  | 2015-01-30 | 2015-06-30 | 0 |  |  | Contractor has queried the original steelwork design, DIO currently investigating the query. No progress on site until resolved. DIO cannot close main project until this local order is complete. Awaiting contractor to provide detail to support claim that original steelwork design is not to standard.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61401 | Boundary Gate at Nallin Pond |  | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075 | 10119 | 2011-01-12 | 2014-12-31 | 2013-01-10 | 2015-01-08 | 1 |  |  | Remaining punchlist items completed. All pending modifications/REAs are settled. Project is in closeout phase.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61536 | Emergency Service Center |  | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | W912DR-10-C-0087 | 13478 | 13858 | 2010-07-19 | 2013-05-23 | 2012-09-16 | 2013-05-23 | 1 | 1028 | FY14 - PN77922 | In fiscal closeout. Construction contract held open longer to address a warranty repair.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) |  | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | W912HN-11-C-0002 | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 1 | 14458 | OSD - C project FY14 - PN77922 | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14. Financial close-out underway.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 71318 | Dental Clinic Replacement |  | 2009-10-28 | 2010-02-26 | JE Dunn Construction Company | W9126G-08-D-0057 | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 1 | 3144 | FY14 - PN77922 | Retainage on the project recently paid, processing close out. The project funds have been returned.
2015-07-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center, Phase 1 |  | 2010-06-11 | 2010-08-19 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0005) | 41566 | 45105 | 2010-10-04 | 2013-11-19 | 2013-02-20 | 2013-08-30 | 1 |  |  | 1. Phase 1B is complete and turned over to the Air Force. BOD was 19 Nov 13 and the Interim DD 1354 was signed by BCE on 5 Dec 13. The 1B warranty expired in Nov 2014. 2. Post Warranty Deficiencies: a. JE Dunn completed replacement of exterior stone block on the facade of 1B b. Repair of the concrete cracking in the garage (Ph 1A) was completed, but the work is under review c. JE Dunn’s plan to address the stone block on the parking garage is still pending d. JE Dunn has indicated they intend to address the Ph 1B bathrooms ABA/ADA Non-compliance; however, the details of the intended fixes have not been finalized, and JE Dunn has not yet submitted a schedule.
2015-07-31 | [8 empty] | 2010-06-11 | 2010-08-31 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0006) | 23216 | 24153 | 2010-10-04 | 2012-12-13 | 2012-02-26 | 2012-11-30 | 1 |  |  | Remarks noted above.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72752 | Ambulatory Care Center Phase 2 | 72430 | 2011-05-20 | 2011-09-28 | Skanska USA Building Inc. | W9126G-11-C-0053 | 80558 | 98282 | 2011-12-02 | 2016-04-06 | 2013-10-01 | 2015-12-22 | 0.91 | 75054 | FY11 - PN72727 FY11 - PN62886 FY14- PN77000 PN - 77000 | 1. Phase 2 is 91% complete / 91% scheduled 2. The Ph 2 BOD will shift as noted under Lackland ASC Ph 3 from 1 Oct to 22 Dec 2015 3. Including pending modifications the Ph 2 CWE remains within the current authorization
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77116 | NNMC Parking Expansion |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 14030 | 14392 | 2012-06-18 | 2013-12-02 | 2014-02-02 | 2014-07-18 | 1 | 1854 | PN - 72752 | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77115 | Transient Wounded Warrior Lodging |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133 | 48899 | 2012-06-18 | 2014-05-27 | 2014-02-02 | 2014-07-18 | 1 | 7233 | OSD C project for NATO HQ, Brussels PN - 77116 | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70482 | Health Clinic Addition/Alteration |  | 2010-11-19 | 2011-06-03 | McCarthy Building Companies, Inc. | W912HN-11-C-0006 | 23050 | 25062 | 2011-06-21 | 2013-11-29 | 2013-06-20 | 2014-05-19 | 1 | 3915 |  | Contingencies at District: $0. CAT E&F remaining at District: $0. Financial close-out underway.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MASSACHUSETTS | UNITED STATES | 71634 | Mental Health Clinic Addition |  | 2011-11-04 | 2011-12-23 | Watermark Environmental, Inc. | W912WJ-12-C-0002 | 2790 | 2790 | 2012-05-18 | 2013-02-16 | 2013-01-16 | 2013-03-01 | 1 |  |  | Final payment to Contractor complete. Signed/approved 1354 received from Hanscom AFB. Funds were returned.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 73360 | Consolidated Logistics Facility |  | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869 | 19957 | 2011-07-21 | 2014-10-07 | 2014-01-06 | 2014-10-07 | 1 |  |  | Targeting minor punchlist item completion Aug 2015. Project beginning closeout phase.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 62886 | Information Services Facility Expansion |  | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | W912DR-12-C-0004 | 4270 | 4624 | 2012-03-19 | 2015-02-10 | 2013-11-09 | 2015-02-10 | 1 |  |  | Facility turned over to garrison. Punchlist is complete.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67949 | NIBC Security Fending and Equipment |  | 2011-08-19 | 2012-02-14 | Rich Moe Enterprises, LLC | W912DR-12-C-0001 | 1701 | 1701 | 2012-04-02 | 2013-04-01 | 2013-04-02 | 2013-04-01 | 1 |  |  | Segment 1 - Project Closed. Segment 2 will be awarded on 17 Jul 15.
2015-07-31 | [8 empty] | 2015-03-10 | 2015-07-17 |  |  |  |  | 2015-07-06 | 2017-02-27 | 2016-12-27 | 2017-02-27 | 0 |  |  | RTA date for Fence Segment 2 was 30 Jan 15. Work structured as contract option in combined solicitation with USAMRIID Replacement North Parking which establishes overall site contours for fence construction. Contractor proposals received 21 Apr 15; source selection underway.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67953 | Supplemental Water Storage |  | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468 | 3944 | 2011-07-20 | 2015-08-31 | 2012-11-01 | 2015-08-31 | 0.98 |  |  | % Complete (Scheduled/Actual): 100/98 Contractor having difficulty completing pump facility. LD's being assessed from 30 May 2014. BOD slipped to 31 July 2015 due to contractor performance issues. Bonding company has been contacted. Tank has been filled and passed testing.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67951 | Water Treatment Plant Repair |  | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308 | 15599 | 2013-01-14 | 2015-09-30 | 2014-07-08 | 2015-09-30 | 0.97 |  |  | % Complete (Scheduled/Actual): 100/97 BOD slipped again due to contractor performance. Electrical subcontractor behind schedule.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 70472 | Health and Dental Clinic |  | 2010-11-02 | 2011-07-22 | Charpie-Korte Dsn-Bld JV S.B. L.L. | W9126G-11-C-0031 | 14837 | 15067 | 2011-08-18 | 2013-04-26 | 2013-03-30 | 2013-08-02 | 1 | 3773 | Various FY11 projects PN - 77000 | CLOSED OUT
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 71251 | Dental Clinic Replacement |  | 2009-09-16 | 2011-05-17 | Forrester Construction Company | W912DR-10-C-0067 | 2832 | 3185 | 2011-05-17 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 1 | 146 | PN - 72752 | Project and Contract is in Final Closeout phase. Final 1354 for CIP transfer is in process. Fiscal Closeout now 31 OCT 2015, along with Project # 64241.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66693 | Health/Dental Clinic Replacement |  | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | W912GB-09-C-0029-NA | 34294 | 34376 | 2014-02-03 | 2016-06-11 | 2016-04-12 | 2016-04-12 | 0.65 |  |  | Current work includes: Install of exterior flashing install is ongoing. Construction of interior drywall walls is ongoing (2nd flr), floor screed is ongoing (1st & 2nd flr). Electrical and mechanical rough-in is ongoing (1st flr & 2nd). Communications cabling is ongoing (1st & 2nd flr.), insulation of the ductwork is ongoing (1st & 2nd flr). Sprinkler and sanitary sewer line install is ongoing (1st & 2nd flr.). Parking lot curbstone and gutter install is substantially complete. Asphalt base course for the parking area has been installed. CRITICAL - CAT E/F Equipment must be awarded by 30 Sep 2015 as funds expire for new obligations. MEDCOM is aware and believes they can meet this date (DLA contract being used for ~$320k). German government negotiating commissioning modification.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66588 | Health Clinic Add/Alt |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 32103 | 32103 | 2013-04-08 | 2017-01-07 | 2016-05-30 | 2016-09-04 | 0.75 |  |  | Addition turned over 26 Jun 2015. Ribbon cutting for addition will be 14 Aug 15. Final construction completion (Renovation) may be delayed due to contractor delay request for 95 days. BauAmt currently evaluating delays.
2015-07-31 | 2011 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 51740 | Health/Dental Clinic Replacement |  | 2011-05-13 | 2011-08-26 | Ilsung Construction Co. Ltd. | W912UM-11-C-0024 | 9821 | 10169 | 2011-08-26 | 2014-04-23 | 2013-05-13 | 2014-04-23 | 1 | 6652 | PN - 71634 PN - 77000 | The Carroll Dental Clinic OIC and NCOIC were in the lead for a ribbon cutting ceremony, however, per HFPO, a ceremony does not appear to be occurring. Awaiting final billing ($17,794.00) from DLA for LOGCAT F equipment training.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 72727 | Medical/Dental Clinic Replacement |  | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd. | CT/INT21/13487 | 11958 | 11958 | 2014-05-06 | 2015-08-14 | 2015-10-30 | 2016-01-08 | 0.85 |  |  | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14. Contracting Officer has granted a nil cost extension of time to 25 Dec 2015 based on delays resulting from the original groundwork subcontractor withdrawing from the contract and from a national shortage of labor delaying the brickwork trade. Contractor has requested a further extension of time of 14 calendar days due to late information from SPAWAR. this is currently being reviewed by the Contracting Officer. Contracting Officer approved an extension of time to 8 Jan 2016.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65030 | Naval Hospital Great Lakes Health Clinic Demolition |  | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co. | N40083 12 C 0001 | 5835 | 6195 | 2012-09-12 | 2014-04-21 | 2013-09-13 | 2014-08-08 | 1 | 9210 | PN - 67951 PN - 71325 PN - 77154
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 79554 | Child Development Center |  | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200 | 14457 | 2013-03-01 | 2014-04-07 | 2014-02-22 | 2014-06-02 | 1 | 2000 | FY12 - PN67182
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71408 | Dental Clinic Replacement |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688 | 18689 | 2013-03-01 | 2017-01-06 | 2016-12-06 | 2017-11-08 | 0 |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | MISSISSIPPI | UNITED STATES | 71503 | Branch Health Clinic |  | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Construction | N69450 12 C 0754 | 19096 | 21131 | 2012-09-01 | 2016-04-30 | 2014-09-09 | 2016-01-31 | 0.75 | 8300 | PN - 72754 | Notification of contract termination 5 May 2015
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 70597 | Medical Clinic |  | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | W91278-12-C-0028 | 8897 | 9137 | 2012-10-17 | 2015-01-05 | 2014-10-07 | 2014-10-07 | 1 |  |  | Final document turnover in process. Performing post BOD changes at user request, PT room flooring, walk off matts, rear gate padlocks and door hardware. Final Pay anticipated April, 2015.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 72292 | Hospital Addition/Alteration Phase 2 |  | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778 | 44473 | 2012-10-15 | 2017-06-14 | 2016-10-14 | 2017-03-17 | 0.78 | 11000 | PN - 72754 | Contingencies at district: $361,300 of which $172,675 is for temp. swing space. Executed Option 5 on Trailer Lease. Approval to descope received 5 June 2015. Final inspection of ED complete. Contractor working on punch list for ED.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70438 | Hospital Addition/Alteration |  | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company | W912QR-12-C-0036 | 43466 | 46198 | 2012-08-22 | 2015-05-23 | 2015-02-21 | 2015-03-25 | 0.95 |  |  | The Contractor and his subs continue to make progress in renovation work. Until a modification changes the existing contract, the Contract Required Completion (CRC) date is 25 March 2015. End users and customers understand that our projected Construction Completion date is 27 Oct 2015. Update on the Curtain Wall claim resolution: Negotiations nearing completion.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 70351 | Hospital Alteration |  | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400 | 23770 | 2012-09-13 | 2016-01-20 | 2014-06-23 | 2015-04-05 | 0.83 | 23532 | PN - 71820 PN - 71503 | Contingencies at District: $69,771.04. Contractor has been issued an Interim Marginal CCASS. Fire Alarm testing + ICRA inspection completed in Emergency Dept with no deficiencies. Ceramic tile + finishes nearing completion phase 7. Temporary ED trailers have were demolized on 25 Jul 15. Negotiations underway on DHA approved User Change to delete work on 2 floors from the contract.
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70580 | Dental Clinic Addition /Alteration |  | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | W91DS-13-C-0002 | 4370 | 4370 | 2013-01-09 | 2014-12-19 | 2015-01-09 | 2014-12-19 | 1 |  |  | BOD 19 DEC 14. MOD work to repair Chiller line connection will start upon arrival of required material (estimated completion of repair OCT 15)
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70579 | Medical Clinic (SFCC) |  | 2012-10-05 | 2013-02-13 | Structural Associates Inc. | W912DS-13-C-0022 | 9934 | 9937 | 2013-03-15 | 2015-06-11 | 2015-03-06 | 2015-03-06 | 1 | 1273 | PN - 77154 PN - 79510 | BOD 5 MAR 15. Final Site inspection 3 Jun 15, Only punchlist item remaining is insufficient vegetation growing to close SWPPP. Corrective action has been taken. (expected acceptance NLT 30 SEP)
2015-07-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 51969 | Hospital Nutrition Care Department Add/Alt |  | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | W9126G-12-C-0050 | 28291 | 29084 | 2012-10-02 | 2015-11-02 | 2014-10-30 | 2015-12-23 | 0.97 |  |  | Contractor filed seven claims in Nov 14 totaling $1.4M; KO denied; DCAA audit ongoing, Alternative Dispute Resolution (ADR) tentatively scheduled for 13-14 Oct 15. Global modification awarded 15 May; $1.92M; extends BOD to 5 Oct 15; installs Quarry Tile Floor, modifies chefs counter, extends temporary facility lease. * Quarry Tile Floor Status: Tile and grout complete in storage areas. Tile in place in corridors. Cove base approx 75% complete. Grout approx 25% complete. 30 days ahead of schedule. *Chef's Counter arrived 20 Jul disassembled; final assembly ongoing. Base approx 90%; overshelves approx 50%. KTR is 30 days ahead of schedule.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 72808 | Medical Clinic Replacement |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703 | 19359 | 2014-02-28 | 2016-01-05 | 2015-03-16 | 2016-05-20 | 0.5
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 78143 | Navy Drug Lab Replacement |  | 2013-01-14 | 2013-08-22 | Blinderman Constr Co. | N40083 13 C 0003 | 14864 | 14884 | 2013-11-08 | 2015-04-15 | 2015-01-15 | 2016-03-15 | 0.98 | 644 | FY13-PN78146 | Drug Lab BOD Apr 2015, Second Contract to Demo Bldg 38H underway
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71507 | Branch Health Clinic Replacement |  | 2013-02-28 | 2013-12-18 | Turner Construction Company | N40080 14 C 0154 | 41408 | 42190 | 2014-04-30 | 2016-02-12 | 2015-10-15 | 2016-02-12 | 0.44
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80307 | Implement Base Installation Appearance Plan |  | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898 | 4789 | 2014-04-01 | 2016-03-18 | 2015-04-08 | 2016-03-18 | 0.05
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities |  | 2013-07-25 | 2012-09-12 | G-W Management Servicxes Inc. | N40080 10 D 0498 DO 0025 | 5286 | 5217 | 2013-10-15 | 2014-04-04 | 2013-12-13 | 2014-03-25 | 1 |  |  | Dosimetry Complete
2015-07-31 | [8 empty] | 2014-03-15
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80308 | Electrical Utility Upgrades |  | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947 | 27075 |  | 2016-04-14 | 2016-02-12 | 2016-04-14 | 0.15 | 4500 | FY10 - PN65270 | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 78144 | Medical Clinic Addition |  | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354 | 14777 | 2013-10-08 | 2015-08-31 | 2015-03-17 | 2015-09-25 | 0.97
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71317 | Medical Clinic Replacement |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744 | 40973 | 2013-12-06 | 2016-04-05 | 2016-12-30 | 2017-11-07 | 0.65
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 78146 | Veterinarian Facility |  | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254 | 7477 | 2014-02-28 | 2015-08-24 | 2014-12-06 | 2015-10-16 | 0.95
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 51639 | USARIEM Replacement High Altitude Research Lab |  | 2016-07-15 | 2016-09-30 | [11 empty] | Received FY11 P&D Funds ($441K-expire 30 Sep 15) for AE Task Order Award, IH Labor, and soil borings. City of Colorado Springs has selected AE for Summit House. Stakeholder Kickoff Meeting held 29 Jun 15. Omaha District preparing to provide multiple borings at revised site location late August. FY13 Authorization Extended in FY16 NDAA.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 72718 | Medical Logistics Warehouse Replacement |  | 2012-10-18 | 2013-06-18 | R&W Builders | W912QR-13-C-0021 | 2215.9 | 2215.9 | 2013-07-01 | 2014-07-30 | 2014-04-27 | 2014-07-23 | 1 |  |  | Project is fiscally complete and final DD1354 has been sent to Base CE.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 71679 | Dental Clinic |  | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture | W912DQ-13-C-4017 | 10687 | 10505 | 2013-12-02 | 2015-08-18 | 2015-02-19 | 2015-02-19 | 1 | 234 | FY13-PN72718 | Punch list completed. Boiler flues are to be replaced. Product data submitted and approved. Work to be scheduled once product is on hand. Also remaining is the seasonal commissioning which is scheduled for August. Design/Scope: Design-Build / Primary Facilities include the dental clinic (30 chairs), outdoor troop shelter and BIM/COBIE. Also includes demolition of nine buildings. Facility will facilitate soldier's dental readiness for deployments. Construction: Complete 19 Feb. Facility transferred and turned over keys. Schedule: Delivered on schedule. LEED: Silver required (solar panels for domestic hot water and solar light tubing). Still pending certification review by USGBC. Time Growth: None FISD: To be performed by HFPA after turnover.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71325 | Medical Clinic Replacement |  | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536 | 47116 | 2013-10-24 | 2017-07-21 | 2016-10-23 | 2016-12-22 | 0.22 |  |  | Structural steel erection continues. Contingencies at District: $279,302.19. Cat E&F Equip funds at District: $1,723,000
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77979 | Medical/Dental Clinic Replacement |  | 2013-09-03 | 2014-03-27 | JE Dunn + HWA | W9127S-13-D-6001 DM01 | 47044 | 52953 | 2014-04-28 | 2018-01-08 | 2017-10-25 | 2018-03-08 | 0.07 | 4000 | FY09-PNS0013 | Contractor working toward 100% Bldg design submittal, due 3 July 2015. 100% Site/Civil package "For Construction" to be issued 7 July 2015. Review period run from 3-27 July. Review conference scheduled for week of 3 August. C-008 New PFD final negotiated amount is $659,996, MILCON funds provided to SPA 9 July. PDT developed list of scope reductions as potential offsets to the cost of C-008. To date, $779,833 in modifications have been executed utilizing contingency funds. Current estimated value of offsets $500K. PDT has outlines potential cost saving modification for changes to Program for Design. Goal is to reduce overall cost impacts to $200K or less. Partial notice to proceed issued for Site/Civil work.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 73776 | Soldier Specality Care Clinic |  | 2012-11-15 | 2013-12-18 | Structural Associates Inc. | W91DS-14-C-0003 | 11163 | 10901 | 2014-01-06 | 2016-04-05 | 2016-01-06 | 2016-01-06 | 0.65 |  |  | Exterior masonry complete. Interior wall framing & drywall continues and rough-in of interior utilities continues.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72420 | Medical/Dental Clinic Addition |  | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. | W912UM-13-C-0018 | 8544 | 9056 | 2013-06-05 | 2015-05-06 | 2015-02-25 | 2015-03-29 | 0.99 |  |  | Contingency Amounts: District $1,811; HQ Mgmt $0. Final Inspection was completed and keys turned over 27 Mar 15. A simple ribbon cutting ceremony was conducted 6 May 2015. No invitations were sent to outside organizations. The separate CCD for explosive proof fan in room 126 is 27 Jul 2015 and for LPG system in room 141 is 31 Jul 2015. The contractor is awaiting off-shore material.
2015-07-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72419 | Hospital Addition/Alteration |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co. Ltd. | W912UM-13-C-0025 | 22361 | 22386 | 2013-09-26 | 2018-01-08 | 2017-08-08 | 2017-10-24 | 0.39 |  |  | Contingency Amounts: District $274,508; HQ Mgmt $824,232. Ongoing work: TPO membrane for roofing, EIFS, Main electrical work, HVAC duct work.
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80904 | Mechanical & Electrical Improvements |  | 2014-01-30 | 2015-03-30 | Whiting Turner Contracting Co | N40080 15 C 0156 | 38490 | 38490 | 2015-05-31 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 0.01
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80913 | Parking Garage |  | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835 | 15835 | 2014-11-30 | 2016-05-09 | 2016-04-16 | 2016-05-09 | 0
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77922 | Medical Clinic Replacement |  | 2014-02-25 | 2014-08-20 | Gilbane | W9127S-13-D-6000 DM01 | 45629 | 47382 | 2014-10-27 | 2018-08-16 | 2018-01-30 | 2018-01-30 | 0.09 | 1900 | FY14-PN81340 | Submittal #2 (65% Arch/MEP/Fire, 100% Foundation/Structural, IFC Civil/Site) Received 19 May 2015. Review completed, review conference held 15-19 June. Areas of concern with missing or incomplete information identified (several disciplines, including mechanical and plumbing). Identification of required information and due dates prior to next submittal underway. Groundbreaking ceremony and pre-construction meeting held 1 Jul. Partial notice to proceed for mobilization issued 13 July.
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81340 | SAMMC Hyperbaric Facility Addition |  | 2014-03-17 | 2014-06-30 | Gilbane | W9127S-13-D-6000 DY01 | 11289 | 11289 | 2015-07-10 | 2016-12-28 | 2016-09-30 | 2016-09-30 | 0.14 |  |  | 95% design review conference held 17-19 Jun. All review comments will be incorporated by 10 Jul with final design documents completed by 20 Jul. KTR delayed delivery of 100% corrected final drawings 5 days; will delay construction start but shouldn't delay completion.
2015-07-31 | 2014 | Defense Health Agency | Major Military Construction |  | BAHRAIN | 81436 | Medical/Dental Clinic Replacement |  | 2015-08-13 | 2015-11-27 | [11 empty] | Planned Aug 2015 award of a Design-Build contract with a one-year design period delayed to Nov 2015. Delay in advertisement/award due to site availability, pending completion of an on-going MCN project, the P908 Operations and Support Facilities. A large required security-related modification to this ongoing project is the primary cause of the schedule push. New site availability date is Nov 2016. RFP package is complete and ready to advertise. Authority to Advertise has been requested (anticipated o/a 13 Aug 15)
2015-07-31 | 2015 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 72414 | Dental Clinic Replacement |  | 2015-04-21 | 2015-07-30 | [11 empty] | Contracting (CENWO-CT-M) issued discussion items earlier this week (8/3/15) to the 3 medical des/bld MATOC contractor/proposers, with responses to be forwarded to Omaha District by 8/17/15. Do not know whether 31 Aug 15 TO Award Date is possible at this time.
2015-07-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81423 | Medical Clinic Replacement (Reid Clinic) |  | 2015-03-20 | 2015-08-08 | [5 empty] | 2018-03-16 | 2017-12-18 |  |  |  |  | Advertised on 20 MAR 2015. Bid Opening 14 MAY 2015. Source Selection Evaluation Board 18-22 May. Planned Award was 22 Jun 2015. Award delayed to 8 Aug 15.
2015-07-31 | 2015 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 81430 | Hospital Add/CUP Replacement |  | 2015-08-31 | 2016-01-06 | Ellerbe Becket & RLF JV | W912DY-09-D-0068 (AE-1) | 1279 | 496 | 2014-09-02 |  |  |  | 0 |  |  | The construction contract will also include turnkey FFE and medical equipment increasing the procurement to > $50M. DHA supports Jan 2016 award. NAO has obtained and MOA to secure capacity on the SWL iDBIO MATOC for award.
2015-07-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81627 | NiCOE Satellite, Infrastructure Support |  | 2015-09-30 | 2015-12-31 | [11 empty] | 29 JUL 15 - Final Design in-progress. Tracking toward mid-AUG RTA and early SEP Advertisement.
2015-07-31 | 2008 | Defense Intelligence Agency | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 154207 | Emergency Backup Water System |  | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC | W912DR-09-D-0024 448-0156A-08 | 1012 | 1012 | 2009-10-03 | 2012-01-20 | 2011-09-16 |  | 1 |  |  | Approp. - $1,012
2015-07-31 | 2010 | Defense Intelligence Agency | Major Military Construction | ALABAMA | UNITED STATES | DIA10-002 | Replace MSIC Explosive Ordinance Exploitation (EOE) Complex |  | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company | W91278-10-D-0064 0001 | 12000 | 12003 | 2012-07-20 |  | 2014-01-20 | 2014-05-21 | 1 |  |  | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved. Contingency funds will be used in FY15 for within scope modifications.
2015-07-31 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction |  | KOREA, SOUTH | DIA10-001 | FOB-K Renovation of Two Buildings to Include Administrative and SCIF Spaces |  | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd. | W912UM-11-C-0006/W912UM-12-C-004 | 4608 | 5224 | 2012-04-09 |  | 2013-10-09 | 2013-10-17 | 1 |  |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project closed out 10 May 2015.
2015-07-31 | 2011 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA11-002 | JBAB Paving of Gravel Parking Lot |  | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture | N40080-06-D-0004-0081 | 2984 | 2294 | 2011-07-20 | 2012-07-25 | 2012-07-18 | 2012-07-25 | 0.99 | 690 | DIA10-001 | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2015-07-31 | 2012 | Defense Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | DIA12000005 | Construction of Remote Delivery Facility (RDF) Meeting SCIF Standards |  | 2013-08-21 | 2013-09-25 | Heard Construction | W91236-09-D-0071:T044/W91236-13-C-0074 | 10758 | 6058 | 2013-10-10 |  | 2014-09-30 | 2015-07-31 | 0.98 |  |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Completion of all paving, negotiations for all final change orders completed, site grading and final roof work complete. Final punch list prepared for contractor action, architectural punch work in progress.
2015-07-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000001 | DIAC Parking Garage Replacement |  | 2014-06-16 | 2014-09-23 | Arriba | N4008-11-D-0496-0050/N0080-11-D-0495-0016 | 13586 | 13358 | 2014-10-23 |  | 2016-03-02 | 2016-06-30 | 0 |  |  | Approp. - $13,645 - $793,156 CAT I obligated. Construction contractor received the final approval on its Stormwater Management Plan from Washington District Dept. of Environment. Construction is scheduled to start 10 August 2015. Construction will require closures/reduction of available parking spaces in the West Parking Lot, street parking along Chappie James Boulevard, and in the North West parking lot.
2015-07-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000003 | DIAC Chilled Water Project for Data Center |  |  |  |  | N4008-09-D-0309-0017 | [9 empty] | Estimates indicate project costs exceed programmed amounts. DIA initiating reprogramming action to move funds to UPS for Data Center. Awaiting reprogramming action approval.
2015-07-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center |  |  |  |  | N40080-09-D-0309-0018 | [9 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions to add funds from the DIAC Chiller project. Reprogramming action currently with OMB; expect approval soon.
2015-07-31 | 2013 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA13000001 | Parking Garage Demolition | [14 empty] | This line was reduced due to sequestration. The remaining funds are insufficient to complete demolition of the existing parking garage. DIA is currently exploring options. Contract is not awarded at this time.
2015-07-31 | 2013 | Defense Information Systems Agency | Major Military Construction |  | GERMANY | 13DISA01 | DISA Europe Facility Upgrade | [14 empty] | PA: $2.224M. Awaiting USACE to schedule Design Kick Off Meeting. USCE determined this will be a n "Indirect" Contract. To ensure award is made NLT Sept 2015.
2015-07-31 | 2013 | Defense Information Systems Agency | Major Military Construction | ILLINOIS | UNITED STATES | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994 | 65994 | 2014-03-01 |  | 2015-12-30 | 2016-03-11 | 0.76 |  |  | PA: $77.515M. 3 separate contracts: Soil Rem complete Feb 14; Construction and , Demo Bldg 3189 - TBD. Construction Completion: 11 Mar 2016. Funding ($2.153M) for Demo of Bldg 3189 provided 30 Jun 2015.
2015-07-31 | 2014 | Defense Information Systems Agency | Major Military Construction | HAWAII | UNITED STATES | 14DISA01 | DISA Pacific Facility Upgrade | [14 empty] | PA: $2.615M. NAVFAC preparing RFP for Design. RFP will take into consideration the Navy's Energy Project to replace the 2 existing chillers. Telcon held with NAVFAC on 7 Jul 2015. Awaiting schedule dates for three (3) Day Charrette.
2015-07-31 | 2015 | Defense Information Systems Agency | Major Military Construction | ARIZONA | UNITED STATES | 15DISA01 | JITC Building 52120 Renovation | [14 empty] | PA: $1.871M. Design/Renovation of Garrison existing Bldg 52120 for JITC Fort Huachuca. USACE to conduct site survey 27-28 Apr 2015. Design charrette held 30 Jun 2015. The 65% design review to be scheduled end of August 2015.
2015-07-31 | 2015 | Defense Information Systems Agency | Major Military Construction | ARIZONA | UNITED STATES |  | Design of Bldgs 52101, 52110, 52111 for JITC | [14 empty] | PA: $745K. Design of Garrison existing Bldgs 52101, 52110, 52111 for JITC Fort Huachuca. Design charrette rescheduled Sept 2015. Design funding covered under consolidated FY15 Planning and Design Appropriation.
2015-07-31 | 2015 | Defense Information Systems Agency | Major Military Construction |  | AUSTRALIA | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) | [14 empty] | PA: $9.6M. NAVFAC to construct Electronic Equip Bldg, Antenna Foundations for AN/GSB 52B Medium Satellite Earth Terminals. RFI issued 16 Apr 15. No responses. J&A approved. Awaiting DB RFP pkg ESC Oct 2016. Project ESC: FY18.
2015-07-31 | 2008 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INC #1 - NAV SUP Fleet Logistics Center, Point Loma San Diego |  | 2008-02-20 | 2008-09-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 0.99 |  |  | wo# 861477
2015-07-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) - NAV SUP Fleet Logistics Center, Point Loma San Diego |  | 2008-02-20 | 2011-03-22 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 0.99 | 3109 | FY09 PH-H, FY10 Travis, FY13 New Cumberlan Sewage Treatment | wo#861477
2015-07-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC0908 | Replace Jet Fuel Storage Complex - Jacksonville ANG |  | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | W912EP-10-C-0023 | 8003 | 9988 | 2010-04-27 | 2014-04-10 | 2011-09-20 | 2014-09-30 | 1
2015-07-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | KOREA, SOUTH | DESC0907 | Hydrant Fuel System - Osan AB |  | 2009-12-17 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844 | 19369 | 2010-08-27 | 2015-04-20 | 2012-12-16 | 2015-04-30 | 0.99 | 2151 | FY12 New Cumberland General Purpose Warehous
2015-07-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) - Pt. Loma |  | 2008-02-20 | 2011-03-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 0.99 | 2385 | FY13 New Cumberland Sewage Treatment, FY14 Tinker | wo#974938
2015-07-31 | 2011 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX0802 | Replace Headquarters Facility - New Cumberland |  | 2011-11-23 | 2012-08-17 | Walsh Construction | W912DR-12-C-011 | 80775 | 82555 | 2012-08-30 | 2016-02-29 | 2015-09-18 | 2016-01-29 | 0.9 | 1950 | FY13 Andersen AFB
2015-07-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC0909 | Replace Fuel Pier - Craney Island |  | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | N40085-11-C-0001 | 28815 | 34079 | 2012-11-26 | 2015-05-30 | 2014-06-03 | 2015-05-30 | 0.98 | 3114 | FY14 Tinker | wo# 799865
2015-07-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC0503 | Hydrant Fuel System - Misawa AB |  | 2012-05-17 | 2012-09-22 | Tokyo Construction Co., Ltd. | W912HV-12-C-0013 | 25204 | 25586 | 2013-02-01 | 2015-03-06 | 2015-02-01 | 2015-05-13 | 1 | 2601 | FY14 Tinker
2015-07-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | UNITED KINGDOM | DESC0905 | Replace Hydrant Fuel System - RAF Mildenhall |  | 2011-04-19 | 2011-12-06 | Spiecapag | DEUSFMIL/13232 | 12535.429 | 12535 | 2011-12-09 | 2014-04-25 | 2013-03-14 | 2014-05-02 | 0.99
2015-07-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC1103 | Replace Hydrant Fuel System - Davis Montham AFB |  | 2012-05-04 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 18962 | 18882 | 2012-11-13 | 2015-04-09 | 2014-11-03 | 2015-05-15 | 0.99
2015-07-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1102 | Public Safety Facility - Tracy |  | 2012-03-06 | 2012-07-16 | MASCON, INC | W91238-12-C-0021 | 14615 | 16062 | 2012-08-29 | 2014-12-05 | 2014-03-24 | 2014-12-07 | 1
2015-07-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma |  | 2008-02-20 | 2012-03-29 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08C-7501 | 15512 | 164864 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 0.99 |  |  | wo# 113174
2015-07-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1205 | Replace Fuel Facilities - San Clemente Is. |  | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453 | 27840 | 2013-02-28 | 2015-08-30 | 2015-03-24 | 2015-08-30 | 0.82 |  |  | 2853 Reprogramming wo# 973902
2015-07-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESI1101 | Alter Warehouse Space - JB PH Hickam |  | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | N62478-11-D-4042/0004 | 5500 | 6430 | 2012-08-13 | 2014-09-30 | 2013-06-14 | 2014-04-29 | 0.99 |  |  | wo# 972725
2015-07-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | MASSACHUSETTS | UNITED STATES | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB |  | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 25181 | 25388 | 2013-06-18 | 2016-02-08 | 2015-12-10 | 2016-02-08 | 0.84 | 1761 | FY14 Iwakuni | 2853 Reprogramming
2015-07-31 | 2012 | DLA Defense Supply Center Columbus | Major Military Construction | OHIO | UNITED STATES | DSCC1201 | Security Enhancements - Columbus |  | 2012-02-09 | 2012-05-04 | Pinnacle Construction Development Group | W912QR-12-C-0031 | 8599 | 10555 | 2012-06-07 | 2014-09-26 | 2013-09-30 | 2014-09-26 | 0.99
2015-07-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1202 | Replace General Purpose Warehouse - New Cumberland |  | 2012-09-17 | 2013-11-20 | Corothers Construction Inc. | W912DR-14-C-0005 | 24622 | 25388 | 2014-01-14 | 2015-07-20 | 2015-08-27 | 2015-07-20 | 0.96 |  |  | 2853 Reprogramming
2015-07-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1203 | Upgrade Access Control Points - New Cumberland |  | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 15198 | 15912 | 2013-11-01 | 2016-09-18 | 2016-05-05 | 2016-09-18 | 0.26
2015-07-31 | 2012 | DLA Defense Supply Center Philadelphia | Major Military Construction | PENNSYLVANIA | UNITED STATES | DSCP1201 | Upgrade HVAC System - Philadelphia |  | 2012-03-28 | 2012-06-01 | WU & Associates, Inc. | N40085-10-D-9451 | 4775 | 7240 | 2012-06-14 | 2014-04-29 | 2013-07-17 | 2014-06-06 | 0.99 |  |  | wo# 971006
2015-07-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DESC1101 | Replace Fuel Storage Facility - Charleston AFB |  | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | N694501-12-C-1757 | 26700 | 26485 | 2012-11-30 | 2014-12-30 | 2014-07-21 | 2014-11-26 | 1 |  |  | 2853 Reprogramming wo# 972228
2015-07-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WEST VIRGINIA | UNITED STATES | DESC12S1 | Replace Hydrant Fuel System - Camp Dawson |  | 2012-03-27 | 2012-07-05 | Kinley Construction Company | W9128F-10D-0052 | 1930 | 2101 | 2012-07-03 | 2015-09-22 | 2013-05-31 | 2015-09-22 | 0.99
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC13S4 | Replace Truck Unload Facility - Yuma |  | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322 | 1454 | 2013-09-30 | 2015-10-11 | 2014-08-03 | 2015-10-11 | 0.06 |  |  | 2853 Reprogramming wo# 1124259
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC 1306 | Replace Fuel Pier - Pt Loma |  | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378 | 66999 | 2014-01-15 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 0.46 |  |  | wo# 1124159
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1304 | Replace Fuel Storage - Edwards AFB |  | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513 | 20077 | 2013-12-04 | 2017-03-07 | 2016-12-07 | 2017-03-07 | 0.77
2015-07-31 | 2013 | DLA Defense Reutilization and Marketing Service | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | DRMS12U2 | Warehouse 6 Distribution - Tracy |  | 2013-05-01 | 2013-05-15 | Kinley Construction Company | W91238-10-D0036 | 925 | 925 | 2013-06-01 | 2014-09-02 | 2013-12-05 | 2014-09-02 | 1
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | DELAWARE | UNITED STATES | DESC1305 | Replace Truck Off-Load Facility - Dover AFB |  | 2013-07-07 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800 | 1800 | 2013-11-04 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 0.78
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1391 | Construct Fuel Storage Facility - Hurlburt AFB |  | 2012-12-24 | 2013-08-01 | Nova Group Inc. | W91278-13-C1001 | 15105 | 15271 | 2013-09-24 | 2015-12-25 | 2015-09-14 | 2015-12-25 | 0.86
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | GUAM | GUAM | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB |  | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364 | 54533 | 2014-06-30 | 2016-09-06 | 2016-02-06 | 2016-10-26 | 0.24 |  |  | wo# 1125022
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | LOUISIANA | UNITED STATES | DESC1390 | Upgrade Pumphouse - Barksdale AFB |  | 2012-10-30 | 2013-08-13 | Environmental Management Resources | N69450-10-D-0787 | 4311 | 4455 | 2013-09-09 | 2015-02-26 | 2015-02-26 | 2015-02-26 | 0.96 |  |  | wo# 1123107
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | NORTH CAROLINA | UNITED STATES | DESC13S1 | Replace Transfer Fuel Line to Pump House #2 - Seymour Johnson |  | 2013-02-27 | 2013-07-09 | Shaw Environmental & Infrastructure, Inc. | W9128F-10-D-0073 | 1494 | 1551 | 2013-07-24 | 2014-10-21 | 2014-04-20 | 2014-10-07 | 1
2015-07-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1301 | Replace Communications Building - New Cumberland |  | 2014-05-15 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 6800 | 6800 | 2014-10-31 | 2016-07-27 | 2016-07-28 | 2016-08-03 | 0.15
2015-07-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland |  | 2013-06-13 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9658 | 9758 | 2014-07-11 | 2016-03-06 | 2016-01-02 | 2016-03-06 | 0.25 |  |  | 2853 Reprogramming
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC1203 | Replace Fuel Pier - GTMO |  | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366 | 36366 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-09-28 | 0.51 |  |  | wo# 1124257
2015-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC13S3 | Replace Truck Loading Facility - GTMO |  | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961 | 1961 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 0.38 |  |  | wo# 1303226
2015-07-31 | 2014 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | DESC14U2 | Replace Existing Refueler Parking Lot - Davis Monthan AFB |  | 2014-07-31 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 935 | 935 | 2012-11-13 | 2015-04-09 | 2014-11-03 | 2015-05-15 | 1
2015-07-31 | 2014 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1404 | General Purpose Warehouse - Tracy |  | 2014-02-11 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 32930 | 32930 | 2014-10-02 | 2016-04-04 | 2016-02-25 | 2016-04-04 | 0.05
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC14U1 | Upgrades to Fuel Pier for Fire Protection - Pt Loma |  | 2014-06-01 | 2014-07-01 | CB&I Federal Services LLC | N62583-09-D-0130 TO-027 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0.65 |  |  | wo#1360039
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City |  | 2014-03-28 | 2014-04-24 | Gilbane Federal | N62583-09-D-0129 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0.64 |  |  | wo# 1302082
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC13S2 | Replace Fuel Pipeline - Tyndall AFB |  | 2014-08-20 | 2015-01-27 | Reliable Contracting Group, LLC | W91278-15-C-0005 | 8456 | 8456 | 2015-01-27 | 2016-08-05 | 2016-05-06 | 2016-08-05 | 0.28
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1402 | Replace Fuel Pipeline - Jacksonville |  | 2014-01-16 | 2014-04-17 | Industrial Power Systems | N69450-14-C-1255 | 5438 | 5438 | 2014-06-30 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 0.78 |  |  | wo# 1163305
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC14S2 | Replace Ground Vehicle Fueling Facility - Moody AFB |  | 2014-01-09 | 2014-04-14 | Pond Constructors Inc. | W9128F-14-D-0051 | 3780 | 3942 | 2014-05-07 | 2015-12-24 | 2015-05-07 | 2015-12-24 | 0.66
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC1504 | Upgrade Fuel Island - Hunter AAF |  | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0011 | 13407 | 13407 | 2014-10-16 | 2016-07-07 | 2016-04-08 | 2016-07-07 | 0.16
2015-07-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Major Military Construction | HAWAII | UNITED STATES | DSFH1401 | Alter Warehouse Space - JB PH Hickam |  | 2014-12-08 | 2015-06-02 | Hako Plumbing Inc. | N62742-15-C-1310 | 5664 | 5664 | 2015-06-02 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 0 |  |  | wo# 1167459
2015-07-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | HAWAII | UNITED STATES | DSFH14U2 | Upgrade Administrative Space | DSFH1401 | 2014-12-08 | 2015-06-02 | Hako Plumbing Inc. | N62742-15-C-1310 | 2591 | 2591 | 2015-06-02 | 2016-06-01 | 2016-10-14 | 2016-10-14 | 0 |  |  | wo# 1362232
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW JERSEY | UNITED STATES | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637 | 8637 | 2014-11-18 | 2016-08-09 | 2016-05-11 | 2016-08-09 | 0.02
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NORTH DAKOTA | UNITED STATES | DESC1107 | Replace Fuel Pipeline - Minot AFB |  | 2014-02-28 | 2014-06-12 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4056 | 4166 | 2014-08-11 | 2016-08-01 | 2015-08-11 | 2015-08-19 | 0.92
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB |  | 2014-06-17 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0001 | 32060 | 32060 | 2015-01-19 | 2017-09-08 | 2017-05-23 | 2017-09-08 | 0.09 |  |  | 2853 Reprogramming
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1561 | Replace Refueler Parking, Altus AFB |  | 2014-03-10 | 2014-06-12 | Rockford Corporation | W9128F-10-D-0050 | 1917 | 1917 | 2014-07-11 | 2015-09-17 | 2015-09-17 | 2015-08-07 | 0.49
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW MEXICO | UNITED STATES | DESC1407 | Replace Hydrant Fuel System, Holloman AFB |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP-15-C-003 | 21288 | 21288 | 2015-04-28 | 2016-05-02 | 2017-01-10 | 2017-01-10 | 0
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | TENNESSEE | UNITED STATES | DESC1557 | Replace Ground Vehicle Fueling Facility - Arnold AFB |  | 2014-07-28 | 2015-05-14 | Cape Env. Mgmt. | W9128F-10-D-0075 | 3471 | 3471 | 2015-06-01 | 2016-10-05 | 2016-10-05 | 2017-01-03 | 0
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island |  | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749 | 8749 | 2014-11-30 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0.25 |  |  | wo#1140322
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC15S1 | Replace Ground Vehicle Fueling Facility - Atsugi |  | 2014-05-02 | 2014-07-29 | Ichibo Co. Ltd | W912HV-14-C-0002 | 1835 | 1857 | 2014-09-12 | 2015-10-23 | 2015-07-09 | 2015-06-19 | 0.99
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC1401 | Construct Type III Hydrant Fueling system - Iwakuni MCAS |  | 2015-02-27 | 2015-04-07 | Nippo Corporation | W912HV-15-C-005 | 32623 | 32623 | 2015-04-22 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 0
2015-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC1503 | Replace Diesel Fuel Pumps - Yokosuka |  | 2014-10-03 | 2015-04-23 | Tokyo Construction Co., Ltd. | W912HV-15-C-0007 | 6244 | 6244 | 2015-05-15 | 2016-07-19 | 2016-11-05 | 2016-07-19 | 0.01
2015-07-31 | 2014 | DLA Defense Supply Center Richmond | Major Military Construction | VIRGINIA | UNITED STATES | DSCR1401 | Operations Center Phase 1 |  | 2015-02-13 | 2015-06-12 | Hensel phelps Constuction co | W91236-15-C-0045 | 71969 | 71969 | 2015-07-09 | 2018-10-08 | 2018-07-08 | 2018-07-08 | 0
2015-07-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 17387653 | 58111 | 58111 | 2015-06-03 |  | 2018-03-01 | 2018-06-04 | 0.01
2015-07-31 | [8 empty] | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 39972656 | 3307 | 3307 | 2015-06-03 |  | 2018-03-01 | 2018-06-04 | 0.01
2015-07-31 | [8 empty] | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 45239562 | 0 | 0 | 2015-06-03 |  | 2018-03-01 | 2018-06-04 | 0.01
2015-07-31 | 2010 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM 856 07 | New Elementary School |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764 | 20564 | 2012-08-01 | 2014-08-01 | 2013-12-14 | 2014-07-09 | 0.99
2015-07-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) |  | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | W912GB-08-C-0046 / 14328568 | 15509.459 | 17800 | 2011-05-09 | 2013-09-13 | 2013-01-19 | 2013-09-25 | 1 |  |  | Remove at end of FY15
2015-07-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46694.9233 | 50836 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 0.87 | 1475 | PA00033
2015-07-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513.9133 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 0.87
2015-07-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 0.87
2015-07-31 | 2010 | DoD Education Activity | Major Military Construction |  | BELGIUM | EUR 8318 09 | Replace School (SHAPE ES) |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414.6336 | 33113 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 0.99
2015-07-31 | [8 empty] | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652.1853 | 1719.1947 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 0.95
2015-07-31 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School (Boblingen HS) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869.3221 | 46291 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 0.91 | 3999 | PA00033
2015-07-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 0.91
2015-07-31 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292.8744 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 0.91
2015-07-31 | 2011 | DoD Education Activity | Major Military Construction | NEW YORK | UNITED STATES | AM2455205 | Construct Addition and Renovate West Point MS |  | 2011-07-18 | 2011-10-20 | Bernard Associates | W912DS-12-C-0001 / 25312318 | 23974 | 26115 | 2011-11-28 | 2014-03-17 | 2014-09-28 | 2014-03-17 | 1 |  |  | Remove at end of FY15
2015-07-31 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) |  | 2012-04-18 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260 | 27139 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 0.99
2015-07-31 | [8 empty] | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843 | 6002 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 0.95
2015-07-31 | [8 empty] | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28674 | 29244 | 2012-08-01 | 2015-02-12 | 2015-01-13 | 2015-02-12 | 0.97
2015-07-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM8193 01 | Replace Elementary School (Antilles ES) |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968 | 51308 | 2012-07-18 |  | 2014-04-19 | 2015-09-30 | 0.77
2015-07-31 | 2011 | DoD Education Activity | Major Military Construction | VIRGINIA | UNITED STATES | AM2455206 | Replace/Consolidate Elementary Schools |  | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297 | 43644 | 2012-09-29 | 2015-04-13 | 2014-09-30 | 2015-06-01 | 1 |  |  | Remove at end of FY15
2015-07-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM100801 | Replace Elementary School (Murray ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121826 | 14851 | 16469 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 1 |  |  | Remove at end of FY15
2015-07-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AMD02051 | Replace Elementary School ( McNair ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121890 | 16413 | 17205 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 1 | 2056 | AM00025, PA00033 | $1,443 supported AM0025 and $613 supported PA00033. Remove end of FY15
2015-07-31 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB |  | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | W912HV-13-C-0002 / 29312081 | 9644 | 9773 | 2013-03-26 | 2015-05-01 | 2015-07-25 | 2015-10-18 | 0.99 | 634 | PA00033
2015-07-31 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00053 | Replace Elementary/Middle School (Ansbach EMS) |  | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 575 | 575 | 2013-10-28 |  | 2015-03-12 | 2015-08-19 | 0.8
2015-07-31 | [8 empty] | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11783.7717 | 12335 | 2013-10-28 |  | 2015-03-12 | 2015-08-19 | 0.8
2015-07-31 | 2012 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00020 | Replace Elementary School (Osan ES) |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187 | 31029 | 2013-09-30 |  | 2015-12-09 | 2016-03-01 | 0.48 | 6444 | PA00033
2015-07-31 | 2013 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00023 | Replace McBride Elementary School |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987 | 33393 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 0.46
2015-07-31 | [8 empty] | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 0.46
2015-07-31 | 2013 | DoD Education Activity | Major Military Construction | MASSACHUSETTS | UNITED STATES | AM00027 | Replace Hanscom Middle School |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 32260 | 33301 | 2014-02-11 |  | 2016-04-21 | 2016-08-19 | 0.43
2015-07-31 | 2013 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00028 | Replace Barkley Elementary School |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39362 | 39666 | 2014-03-27 |  | 2015-12-17 | 2016-05-16 | 0.36 | 800 | PA00033
2015-07-31 | 2012 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00026 | Replace Kingsolver/Pierce School |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685 | 33678 | 2014-03-11 |  | 2015-11-11 | 2016-01-30 | 0.29
2015-07-31 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School |  | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817336 | 0 | 0 | 2015-04-30 |  | 2017-06-03 | 2017-09-07 | 0
2015-07-31 | [8 empty] | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817338 | 2678 | 2678 | 2015-04-30 |  | 2017-06-03 | 2017-09-07 | 0
2015-07-31 | [8 empty] | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 34787 | 34919 | 2015-04-30 |  | 2017-06-03 | 2017-09-07 | 0
2015-07-31 | [8 empty] | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 635 | 1084 | 2015-04-30 |  | 2017-06-03 | 2017-09-07 | 0
2015-07-31 | 2012 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00025 | Replace Delalio Elementary School |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339 | 23970 | 2014-02-24 | 2017-05-20 | 2016-06-01 | 2017-05-20 | 0.38 |  |  | The occupancy date 1 Jun 16 is for the BOD of the school. This is the completion of Phase 1 of the project. The school can be occupied at this time. The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2015-07-31 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475 | 1475 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0.1
2015-07-31 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469 | 2469 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0.1
2015-07-31 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612 | 4612 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0.1
2015-07-31 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418 | 62722 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0.1
2015-07-31 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00062 | Netzaberg Middle School Addition |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 283 | 283 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 0.49
2015-07-31 | [8 empty] | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366 | 5427 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 0.49
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00024 | Faith Middle School Addition |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4897 | 4897 | 2014-10-28 |  | 2016-01-21 | 2016-04-20 | 0.19
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00040 | Replace Marshall Elementary School |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 34748 | 34880 | 2014-08-06 |  | 2016-03-28 | 2016-05-27 | 0.33
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00038 | Diamond Elementary School Replacement |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40093 | 39874 | 2014-10-15 |  | 2016-09-14 | 2017-01-07 | 0.13
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00018 | Daegu Middle/High School Replacement |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28954 | 28954 | 2014-09-29 |  | 2016-10-03 | 2016-12-10 | 0.1
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00030 | Replace Zukeran Elementary School |  | 2014-09-09 | 2014-11-06 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476 | 95476 | 2014-10-23 |  | 2017-04-01 | 2017-06-20 | 0.04
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00050 | White Elementary School Replacement |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791 | 31791 | 2014-12-16 |  | 2016-10-31 | 2017-01-29 | 0.07
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00034 | Replace Fort Campbell High School |  | 2014-06-20 | 2014-11-10 | Walsh Group Ventures | W912QR-15-C-0001/34496304 | 50931 | 50931 | 2015-01-27 |  | 2017-02-25 | 2017-04-29 | 0
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00031 | Pope Holbrook Elementary School |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278-12-D-0039/30132665 | 32124 | 32124 | 2015-02-11 |  | 2017-02-10 | 2017-05-11 | 0.04
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction | SOUTH CAROLINA | UNITED STATES | AM00037 | Replace Bolden-Galer Elementary School |  | 2014-07-25 | 2014-12-19 | Elkins Constructors, Inc. | N6945015C1606 | 35705 | 38435 | 2014-12-19 |  | 2017-10-31 | 2017-10-31 | 0 |  |  | Project will be re-awarded to second highest bidder following original contractor being terminated for cause.
2015-07-31 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00027 | Replace Yokota High School |  | 2014-07-25 | 2014-12-24 | Daiwa Odakyu Construction - JDC JV | W912HV-15-C-0002/ 29312181 | 40547 | 40547 | 2015-02-19 |  | 2018-12-21 | 2019-04-09 | 0
2015-07-31 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00035 | Kadena Middle School Addition/Renovation |  | 2014-09-23 | 2015-02-18 | Nippo Corporation | W912HV-15-C-0003 / 34596540 | 31459 | 31459 | 2015-03-06 |  | 2016-10-02 | 2016-12-02 | 0
2015-07-31 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P646 | DSS Headquarters Addition |  | 2012-09-21 | 2013-03-29 | Hensel Phelps Construction Co. | N40080-13-C-0155 | 25149 | 29009 | 2013-04-30 | 2014-09-26 | 2014-07-22 | 2015-09-09 | 0.99 |  |  | [Solicitation/Advertise Date: Phase I - 21-Sep-2012 Phase II - 20-Dec-2012]
2015-07-31 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P659 | Defense Access Road Improvements-Telegraph Rd |  | 2013-01-22 | 2013-07-15 | Shirley Contracting Company, LLC | DTFH71‐13‐C‐00041 | 2967 | 3171 | 2013-08-01 | 2015-05-15 | 2014-08-01 | 2015-05-15 | 0.98 |  |  | This project is being managed and funded via FHWA. [Solicitation/Advertise Date: Phase I - 22-Jan-2013 Phase II - 04-Apr-2013]. Placed in service date is the substantial completion date. Punchlist items remain.
2015-07-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 655 | Missile Test Vehicle Storage Facility |  | 2014-03-24 | 2014-05-09 | Arctic Slope Regional Corporation (ASRC) | W912DY-14-D-0042-0001 | 1832 | 1832 | 2014-06-17 | 2014-12-16 | 2014-12-11 | 2014-12-28 | 1 |  |  | Awaiting Interim 1354
2015-07-31 | 2010 | Missile Defense Agency | Major Military Construction | HAWAII | UNITED STATES | 627 | Aegis Ashore Missile Defense Test Complex |  | 2011-06-30 | 2011-08-03 | TOMCO CORP. | N62478-10-D-4024 | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 1 |  |  | Clearing and Grubbing Only
2015-07-31 | [8 empty] | 2012-01-19 | 2012-06-04 | URS GROUP, INC | N62742-09-D-1174 | 59616 | 69657 | 2012-07-04 | 2013-08-29 | 2013-09-12 | 2013-11-07 | 1 |  |  | GMAC Construction - awaiting Interim 1354
2015-07-31 | 2012 | Missile Defense Agency | Major Military Construction | ALABAMA | UNITED STATES | 633 | Von Braun Complex Phase IV |  | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | W91278-12-C-0017 | 51330 | 59842 | 2012-07-10 | 2014-06-26 | 2014-07-10 | 2014-10-15 | 1 |  |  | Awaiting Final 1354
2015-07-31 | 2013 | Missile Defense Agency | Major Military Construction | NEW YORK | UNITED STATES | 639 | In-Flight Interceptor Data Terminal Complex |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584 | 15270 | 2013-08-10 | 2015-02-04 | 2014-11-28 | 2015-09-12 | 0.99 | 1801 | 630 | Awaiting Final 1354
2015-07-31 | 2013 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 114560 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 0.8 |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2015-07-31 | 2014 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 646 | Aegis Ashore Missile Defense System Complex, Incr #2 | 630 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 66900 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 0.8 |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2015-07-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300 | 14193 | 2014-07-07 |  | 2016-01-06 | 2016-01-06 | 0.8 |  |  | Awaiting Interim 1354
2015-07-31 | 2014 | Missile Defense Agency | Major Military Construction |  | JAPAN | 648 | AN/TPY-2 Radar Site |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991 | 15786 | 2014-05-27 | 2015-02-03 | 2015-01-09 | 2015-02-20 | 1 |  |  | Site Identifier is pending as this is a new Installation.
2015-07-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838 | 46800 | 2014-05-27 |  | 2016-05-31 | 2016-05-31 | 0.4 | 22900 | 646 | Construction re-mobilized on 23 March 2015; Awaiting Interim 1354
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC |  | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | N4008510D5329 0002 | 12906 | 13460 | 2011-06-16 | 2015-09-15 | 2012-12-01 | 2015-09-15 | 0.94
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695005 | PAINT AND BLAST FACILITY |  | 2011-04-29 | 2011-09-16 | SAUER, INC. | N6945009D1277 0005 | 20345 | 19809 | 2011-09-30 | 2014-03-10 | 2013-05-16 | 2014-01-24 | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813005 | JOINT POW/MIA ACCOUNTING, USPACOM |  | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274211C1300 AWD | 95540 | 86304 | 2011-06-20 | 2015-08-13 | 2013-07-05 | 2015-08-13 | 0.91
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318006 | PHYSICAL FITNESS CENTER, CAMP SMITH |  | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | N6274209D1171 HC01 | 28891 | 27854 | 2011-06-30 |  | 2013-03-07 |  | 0.98
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695012 | CONTAINER STAGING AND LOADING LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3380 | 2529 | 2011-06-17 |  | 2013-12-05 |  | 0.99
2015-07-31 | 2011 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N61007015 | CALIBRATION FACILITY LAND ACQUISITION |  |  | 2011-12-31 | NAVY STANDARD DOCUMENT | N6945011RP00148 | 3149 | 3080 | 2012-01-14 |  |  |  | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695017 | HARDSTAND EXTENSION |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 12623 | 7904 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695022 | CONSOLIDATED WAREHOUSE FACILITY |  | 2010-11-22 | 2011-06-03 | SAUER, INC. | N6945009D1277 0003 | 13295 | 11139 | 2011-06-17 | 2013-12-20 | 2012-07-27 | 2013-12-20 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695023 | WASHRACK EXPANSION |  | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | N6945011D1259 0002 | 8877 | 8449 | 2011-06-15 | 2013-06-10 | 2012-11-19 | 2012-11-19 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695024 | CONTAINER STORAGE LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3702 | 3370 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N61755204A | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | N61755204 | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | N4019210D2803 0006 | 21579 | 16529 | 2012-12-12 |  | 2014-06-19 |  | 0.99 | 19244 | FY 15 Prior Year Rescission
2015-07-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE |  | 2011-02-04 | 2011-06-24 | FOPCO, INC | N6247810D4019 0006 | 7856 | 9022 | 2011-07-08 | 2013-06-03 | 2012-08-15 | 2013-04-30 | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411068 | ELECTROMAGNETIC SENSOR FACILITY |  | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | N4008511C7231 AWD | 24394 | 26541 | 2011-08-23 |  | 2013-08-22 |  | 0.98
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811014 | TRUCK COMPANY OPERATIONS COMPLEX |  | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | N6247311C0405 AWD | 52425 | 50707 | 2011-10-06 | 2015-08-21 | 2013-09-21 | 2015-08-15 | 0.96
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011034 | 2ND INTEL BN OPERATIONS COMPLEX |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 79767 | 81256 | 2011-07-13 | 2015-09-20 | 2014-02-28 | 2014-12-15 | 1 | 1292 | M67925001
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811043A | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | M006811043 | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | N6247310C5011 PC000001 | 29295 | 27015 | 2010-11-12 | 2015-07-08 | 2012-10-12 | 2015-08-21 | 0.75
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811044 | CONVEYANCE/WATER TREATMENT |  | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | N6247312C5033 AWD | 98236 | 84172 | 2012-10-13 | 2016-12-06 | 2016-01-13 | 2016-12-02 | 0.43
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604109 | CNAT/FRS AVIATION TRAINING AND BEQ |  | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0434 AWD | 51999 | 46315 | 2011-09-26 |  | 2014-01-08 |  | 0.99 | 15930 | M67925001, N61151162, Sequestration Reprogramming
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811109 | BACHELOR ENLISTED QUARTERS, LAS FLORES |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 36173 | 33977 | 2011-10-13 | 2014-06-05 | 2013-10-13 | 2014-10-17 | 1 | 1433 | M670011349
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604111 | MALS-39 MAINTENANCE HANGAR EXPANSION |  | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | N6247310D5409 0003 | 47061 | 33589 | 2011-07-06 |  | 2013-03-13 |  | 0.87 | 12329 | M67925001
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811113 | BACHELOR ENLISTED QUARTERS, 24 AREA |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 41889 | 39187 | 2011-10-13 | 2014-06-05 | 2013-10-13 | 2014-10-17 | 1 | 1752 | M670011349
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811200 | MARINE CORPS ENERGY INITIATIVE |  | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | N6247310D5483 0003 | 9779 | 9567 | 2011-08-09 | 2013-06-21 | 2012-08-04 | 2014-01-16 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 32625 | 31043 | 2011-07-13 | 2015-09-20 | 2014-02-28 |  | 0.94
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP |  | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | N4008510D0259 0007 | 6613 | 6032 | 2011-07-11 |  | 2012-08-20 |  | 0.92
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 43950 | 40338 | 2011-07-13 | 2015-07-31 | 2013-07-13 | 2015-04-11 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 40236 | 38215 | 2011-09-14 | 2015-07-30 | 2013-10-08 | 2014-06-24 | 1 | 689 | M67925001
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 39788 | 37929 | 2011-09-14 | 2015-07-30 | 2013-10-08 |  | 0.99 | 1421 | M67925001
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011256 | MESS HALL ADDITION, COURTHOUSE BAY |  | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0006 | 1499 | 1379 | 2011-06-16 |  | 2012-11-25 |  | 0.98
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011264 | UTILITY EXPANSION, HADNOT POINT |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 55206 | 56451 | 2011-10-10 | 2016-09-30 | 2013-10-22 | 2016-09-26 | 0.96
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011265 | UTILITY EXPANSION, FRENCH CREEK |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 54795 | 53401 | 2011-10-10 | 2016-09-30 | 2013-10-22 | 2016-09-26 | 0.97
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011267 | MESS HALL, FRENCH CREEK |  | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | N4008511C4022 AWD | 24316 | 21700 | 2011-06-16 |  | 2013-02-06 |  | 0.81
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146136 | BACHELOR ENLISTED QUARTERS |  | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | N4008511C4026 AWD | 42882 | 42057 | 2011-06-16 | 2015-07-22 | 2013-07-07 |  | 0.96
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146148 | MISSILE MAGAZINE |  | 2010-10-21 | 2011-06-02 | SAUER, INC. | N4008511C4010 P00003 | 4779 | 4779 | 2011-06-16 |  | 2012-07-10 |  | 0.99
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865152 | PARKING APRON/TAXIWAY EXPANSION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 32816 | 35501 | 2011-10-04 | 2015-07-01 | 2014-09-19 | 2014-09-19 | 1 | 28591 | N50092499, N60191527, Design, N47608561
2015-07-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151162 | AGILE CHEMICAL FACILITY PHASE 2 |  | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | N4008012C2001 AWD | 34869 | 45011 | 2012-08-24 | 2015-11-13 | 2014-06-16 | 2015-11-15 | 0.79
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE |  | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | N6247310C5007 PC000001 | 51987 | 51426 | 2011-06-17 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146164 | MARINER'S BAY LAND ACQUISITION BOGUE |  |  | 2011-07-01 | NAVY STANDARD DOCUMENT | N4008509RP00103 | 4002 | 3706 | 2011-07-15 |  |  |  | 0.93
2015-07-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443516A | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | N32443516 | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | N4008510C3006 P00003 | 68459 | 68873 | 2011-04-14 | 2015-12-31 | 2014-11-22 | 2015-10-02 | 0.79
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146176 | STATION INFRASTRUCTURE UPGRADES |  | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | N4008510D0261 0003 | 5850 | 7300 | 2011-06-15 | 2013-10-10 | 2012-11-25 | 2013-10-10 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865185 | HANGAR 4 ADDITION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 27121 | 27825 | 2011-10-04 | 2015-07-01 | 2014-09-19 |  | 0.99 | 4000 | M00681159, Design
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865192 | GTF-HANGAR MODIFICATION (HMT-302) |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 56417 | 54610 | 2011-10-04 | 2015-07-01 | 2014-09-19 |  | 0.99 | 33515 | N50092499, Design, FY 15 Prior Year Rescission
2015-07-31 | 2011 | Navy Active | Major Military Construction |  | JAPAN | N61057203 | AVIATION SIMULATOR TRAINING FACILITY |  | 2010-12-09 | 2011-07-29 | NAVY STANDARD DOCUMENT | N6274211MP00014 | 6764 | 6442 | 2011-08-12 |  | 2013-11-13 |  | 0.97
2015-07-31 | 2011 | Navy Active | Major Military Construction | GUAM | GUAM | N61755205 | DAR/DPRI-DEFENSE ACCESS ROAD IMPROVEMENTS (AGANA) |  |  | 2015-06-16 | OTHER - TRANSFER TO FEDERAL HIGHWAY ADMINISTRATION |  | 65236 | 65236 | 2015-06-30 |  |  |  | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A219 | GENERAL WAREHOUSE |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 7716 | 7780 | 2012-04-16 | 2015-07-01 | 2013-12-26 |  | 0.88
2015-07-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N60042260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  |  | 2011-09-29 | NAVY STANDARD DOCUMENT | N6247311RP00189 | 1421 | 1658 | 2011-10-13 |  |  |  | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC |  | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | N4008011C0154 AWD | 33033 | 34871 | 2011-06-16 | 2013-07-31 | 2012-07-30 | 2014-07-16 | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction | ALABAMA | UNITED STATES | N60508266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD |  | 2012-07-05 | 2012-09-28 | HEAD, INC. | N6945012C0760 AWD | 29901 | 29021 | 2012-10-12 |  | 2014-09-28 |  | 0.84
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE |  | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | N4008511C4008 AWD | 54720 | 54826 | 2011-09-13 | 2015-07-31 | 2013-09-07 |  | 0.99
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681310 | SMALL ARMS MAGAZINE, EDSON RANGE |  | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | N6247309D1618 0004 | 3760 | 3232 | 2011-06-21 |  | 2012-07-06 |  | 0.88
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4021 AWD | 43568 | 41166 | 2011-06-16 |  | 2013-08-30 |  | 0.99
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4020 AWD | 46005 | 42201 | 2011-06-16 | 2014-08-29 | 2013-08-13 | 2014-08-29 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 49005 | 44652 | 2011-07-13 | 2015-07-31 | 2013-07-13 |  | 0.97
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011323 | ARMORY II MEF, WALLACE CREEK |  | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | N4008511C4001 P00004 | 5941 | 5414 | 2011-12-20 | 2015-07-31 | 2013-07-13 | 2015-04-11 | 1 | 4148 | M00681159
2015-07-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245327 | BERTHING PIER 12 REPL & DREDGING |  | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | N6247311C2850 AWD | 99132 | 115867 | 2011-10-13 |  | 2013-10-22 |  | 0.77 | 1813 | N61151162
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | N6247310D5480 0012 | 9928 | 9373 | 2011-06-17 |  | 2012-06-17 |  | 0.98
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-10-08 | 2011-05-31 | URS-IAP LLC | N6247006D6009 0016-02 | 8868 | 8147 | 2011-06-14 |  | 2012-09-27 |  | 0.98
2015-07-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245405 | BACHELOR QUARTERS HOMEPORT ASHORE |  | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247311C2804 AWD | 72294 | 69994 | 2011-10-14 | 2013-12-03 | 2013-10-23 | 2013-12-03 | 1 | 3179 | N42237100
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169420 | PHYSICAL FITNESS CENTER, BEAUFORT |  | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | N6945011C1760 AWD | 14780 | 14868 | 2011-09-21 | 2013-05-24 | 2013-06-08 | 2013-07-16 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169444 | TRAINING AND SIMULATOR FACILITY |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 40940 | 38777 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974447A | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 30492 | 29303 | 2011-06-23 |  | 2012-10-08 |  | 0.99
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169454 | F-35B AIRCRAFT HANGAR FOR FRS-2 |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 45398 | 45880 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 47715 | 46254 | 2011-06-23 |  | 2012-10-08 |  | 0.99
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974533 | SIMULATOR FACILITY (JSF) |  | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0002 | 26438 | 23252 | 2011-06-17 |  | 2012-06-02 |  | 0.99 | 1897 | M67925001
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264541 | ADDITION, MCU RESEARCH CENTER |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 31343 | 29448 | 2012-10-09 | 2015-08-31 | 2014-08-16 |  | 0.98 | 3531 | Sequestration Reprogramming
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974546 | UTILITY UPGRADES (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 40106 | 36766 | 2011-06-21 |  | 2012-07-08 |  | 0.99 | 2879 | M67925001
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 |  | 2011-06-20 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 45465 | 37555 | 2012-12-14 | 2017-10-18 | 2016-11-06 | 2017-10-18 | 0.57 | 8039 | Sequestration Reprogramming
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) |  | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0002 | 19793 | 16195 | 2011-08-10 |  | 2012-07-25 |  | 0.99 | 525 | M67925001
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974578 | VAN PAD RELOCATION (JSF) |  | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | N6247309D1653 0003 | 15045 | 14670 | 2011-09-26 | 2013-01-22 | 2012-09-11 | 2012-09-11 | 1
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 54843 | 54497 | 2011-06-21 |  | 2012-07-08 |  | 0.99
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL |  | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | N6274209D1174 JU01 | 34087 | 30411 | 2011-10-14 | 2013-09-26 | 2013-08-09 | 2014-04-30 | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237601 | SECURITY ENCLAVE AND VEHICLE BARRIER |  | 2011-12-13 | 2012-03-16 | SAUER, INC. | N6945009D1277 0007 | 37278 | 39759 | 2012-03-30 |  | 2013-09-07 |  | 0.97 | 5445 | Sequestration Reprogramming
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264615 | SNCO ACADEMIC FACILITY ADDITION |  | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | N4008010D0493 0002 | 6836 | 6730 | 2011-07-04 |  | 2012-12-21 |  | 0.96
2015-07-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237620 | WATERFRONT EMERGENCY GENERATORS |  | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | N6945010D1271 0003 | 15010 | 17004 | 2011-09-02 |  | 2013-05-13 |  | 0.99
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001683 | HANGAR |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62154 | 59565 | 2011-06-17 |  | 2013-11-29 |  | 0.96
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001687 | MV-22 MAINTENANCE HANGAR (HMLA) |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62617 | 59771 | 2011-06-17 |  | 2013-11-29 |  | 0.99
2015-07-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436973F | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | N63402973 | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | N4425508C6003 PC000094 | 20026 | 19522 | 2010-11-24 |  | 2011-11-08 |  | 0.97
2015-07-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246750 | ROTARY HANGAR |  | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | N6247312C1406 P00001 | 64063 | 63863 | 2012-02-14 | 2013-12-10 | 2012-04-16 | 2014-03-11 | 1 | 1557 | N42237100
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318816 | WATERFRONT OPERATIONS FACILITY |  | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 0006 | 16634 | 15088 | 2011-07-14 | 2015-12-31 | 2013-11-16 |  | 0.79
2015-07-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE |  | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008511D6585 0001 | 1395 | 1273 | 2011-06-28 | 2012-11-07 | 2012-06-18 | 2012-11-07 | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436843 | CSDS-5 LABORATORY EXPANSION PHASE ! |  | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | N4425510D5006 0005 | 16042 | 16528 | 2011-06-17 |  | 2012-10-15 |  | 0.95
2015-07-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318858 | BACHELOR ENLISTED QUARTERS |  | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6247811C1492 AWD | 62691 | 62762 | 2011-09-14 | 2015-09-30 | 2014-08-21 | 2015-08-27 | 1 | 17925 | N60191527, N60191582, Sequestration Reprogramming
2015-07-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688862 | PIER 1 UPGRADES TO BERTH USNS COMFORT |  | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | N4008511C0020 AWD | 3659 | 2953 | 2011-08-09 |  | 2012-08-09 |  | 0.79 | 6185 | M00681159, N42237100
2015-07-31 | 2011 | Navy Active | Major Military Construction |  | SPAIN | N62863897 | AIR TRAFFIC CONTROL TOWER |  | 2012-01-13 | 2012-06-15 | SACYR SA | N3319112C0603 AWD | 19080 | 18520 | 2012-06-29 | 2016-01-15 | 2014-09-03 | 2016-01-27 | 0.8 | 2052 | N42237100
2015-07-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY |  | 2012-04-12 | 2012-08-17 | NAVY STANDARD DOCUMENT | N6247012MPE0064 | 41151 | 39060 | 2012-08-31 | 2015-07-27 | 2015-07-27 |  | 0.6 | 15471 | Sequestration Reprogramming
2015-07-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 14315 | 14798 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-08-28 | 1
2015-07-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A912 | PAVE EXTERNAL ROADS |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 3107 | 3469 | 2012-04-16 | 2015-07-01 | 2013-12-26 |  | 0.9
2015-07-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005954 | WATERFRONT DEVELOPMENT, PHASE 3 |  | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT | N6247012MPE0005 | 40713 | 40209 | 2012-03-14 | 2015-09-22 | 2014-11-26 | 2015-09-22 | 0.93 | 19865 | Sequestration Reprogramming
2015-07-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436987 | EMERGENCY GENERATOR, LIMITED AREA |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 11275 | 10364 | 2011-06-17 |  | 2013-06-26 |  | 0.99
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001030 | SQUAD BATTLE COURSE |  | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0003 | 16292 | 12445 | 2012-07-05 |  | 2014-05-17 |  | 0.97
2015-07-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY |  | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | N6247810D4022 0019 | 7708 | 7642 | 2012-04-19 |  | 2013-11-16 |  | 0.99
2015-07-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811046 | NORTH AREA WASTE WATER CONVEYANCE |  | 2014-08-28 | 2014-11-25 | ORION CONSTRUCTION CORPORATION | N6247310D5419 0012 | 75135 | 44012 | 2014-12-09 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 0.02
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE |  | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0002-PC000002 | 11746 | 9687 | 2012-04-06 |  | 2013-01-21 |  | 0.9 | 760 | N00246909
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811040 | INTERSECTION BRIDGE AND IMPROVEMENTS |  | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | N6247309D1606 0009 | 11432 | 14119 | 2012-09-07 | 2014-05-23 | 2013-09-27 | 2014-06-24 | 1
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811045 | NEW POTABLE WATER CONVEYANCE |  | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242 | 66570 | 2012-10-12 | 2016-10-31 | 2016-03-31 | 2016-03-31 | 0.52 | 16682 | N684691400
2015-07-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N68469110 | REPLACE CONDEMNED COATINGS LABORATORY |  | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0019 | 3805 | 3997 | 2012-09-11 | 2014-04-24 | 2013-08-28 | 2014-05-30 | 1
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604114 | MV-22 DOUBLE HANGAR REPLACEMENT |  | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0004 | 40539 | 39059 | 2012-08-03 | 2015-12-02 | 2015-08-10 | 2015-12-29 | 0.86 | 6761 | N684691400
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604116 | MV-22 AVIATION PAVEMENT |  | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | N6247309D1605 0012 | 14938 | 11650 | 2012-07-26 | 2015-09-04 | 2014-01-03 |  | 0.72 | 856 | N684691400
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604117 | MV-22 AVIATION FUEL STORAGE |  | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | N6247007D7000 FZN7 | 7437 | 7224 | 2013-11-21 | 2015-10-01 | 2013-10-07 | 2015-10-07 | 0.52
2015-07-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688123 | BACHELOR QUARTERS, HOMEPORT ASHORE |  | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | N4008512C4572 AWD | 74854 | 72266 | 2012-09-14 | 2015-07-16 | 2014-09-13 |  | 0.99 | 3084 | N684691400
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER |  | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | N4008512C7719 AWD | 74707 | 72185 | 2012-05-14 | 2015-08-30 | 2014-07-24 |  | 0.99
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK |  | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101 | 26510 | 2012-07-13 | 2015-11-15 | 2014-07-29 |  | 0.98
2015-07-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207153 | BAMS UAS OPERATOR TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 2851 | 2936 | 2012-07-09 |  | 2013-12-17 |  | 0.96 | 1321 | N42237100
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA |  | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819 | 20149 | 2012-08-27 | 2016-05-03 | 2014-09-02 | 2016-07-21 | 0.41
2015-07-31 | 2012 | Navy Active | Major Military Construction |  | DIEGO GARCIA | N68539184 | POTABLE WATER PLANT MODERNIZATION |  | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101 | 29328 | 2013-01-04 | 2015-08-26 | 2015-07-30 | 2015-08-26 | 0.78
2015-07-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N57095197 | DECENTRALIZE STEAM SYSTEM |  | 2012-04-17 | 2012-09-20 | SAUER, INC. | N4008509D5026 0004 | 27161 | 27144 | 2012-10-04 | 2015-07-17 | 2015-05-08 |  | 0.91
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399212 | CHILD DEVELOPMENT CENTER |  | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | N6247310D5412 0006 | 21313 | 20524 | 2012-06-19 |  | 2013-12-12 | 2015-09-01 | 0.84
2015-07-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151222 | DECENTRALIZE STEAM SYSTEM |  | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984 | 68816 | 2012-10-12 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 0.95
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011383 | BASE ENTRY POINT AND ROAD |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235 | 63583 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 0.88
2015-07-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443383 | CONTROLLED INDUSTRIAL FACILITY |  | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576 | 32956 | 2012-06-14 | 2016-02-16 | 2014-09-28 |  | 0.44 | 7621 | N684691400
2015-07-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N61064400 | NORTH LOOP ELECTRICAL REPLACEMENT |  | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | N6247811D4046 0005 | 6498 | 6130 | 2012-03-29 |  | 2014-01-02 |  | 0.88 | 2776 | N42237100
2015-07-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 |  | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | N4425510D5019 0002 | 13341 | 10852 | 2012-06-08 |  | 2013-12-24 |  | 0.89
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169442 | VERTICAL LANDING PADS FOR F-35B |  | 2011-12-06 | 2012-03-30 | HEAD, INC. | N6945012C1758 AWD | 18987 | 18048 | 2012-04-13 | 2013-10-21 | 2013-08-07 | 2013-09-27 | 1 | 2444 | N32414547
2015-07-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N50092499 | POWER DISTRIBUTION UPGRADES |  | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | N4008512C1704 AWD | 29520 | 28699 | 2012-10-08 |  | 2014-10-09 | 2015-08-01 | 0.94
2015-07-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS |  | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | N6945012C0757 AWD | 7518 | 10258 | 2012-08-29 |  | 2014-02-21 |  | 0.6
2015-07-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS |  | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599 | 19057 | 2012-10-11 | 2015-11-30 | 2014-10-12 |  | 0.71
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681532 | ARMORY, 1ST MARINE DIVISION |  | 2012-04-23 | 2012-08-31 | A&D GC INC | N6247309D1658 0006 | 11201 | 10485 | 2012-09-14 | 2014-04-23 | 2013-12-24 | 2014-12-23 | 1
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974535 | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | N6247308D8617 0004 | 32048 | 32618 | 2012-09-20 |  | 2014-07-07 |  | 0.99 | 5983 | N684691400
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399541 | MULTI-PURPOSE BUILDING ADDITION |  | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | N6247309D1655 0003 | 15610 | 14733 | 2012-10-11 | 2015-09-23 | 2014-04-20 |  | 0.79
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR |  | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0020 | 11118 | 11273 | 2012-09-25 | 2015-12-31 | 2014-03-28 |  | 0.99
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0003 | 79917 | 79669 | 2012-04-03 | 2014-12-17 | 2014-05-20 | 2014-12-03 | 1
2015-07-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232559 | E-2D AIRCREW TRAINING FACILITY |  | 2012-03-21 | 2012-06-29 | A&D GC INC | N6247309D1658 0012 | 13210 | 15244 | 2012-07-13 |  | 2013-10-07 |  | 0.98
2015-07-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 |  | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49890 | 47424 | 2014-07-14 | 2016-10-20 | 2016-04-01 | 2016-04-01 | 0.21
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 |  | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222 | 23971 | 2012-12-14 | 2017-10-18 | 2016-11-06 | 2017-10-18 | 0.76
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION |  | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | N4008010D0497 0011 | 6555 | 7009 | 2012-08-10 |  | 2013-09-05 |  | 0.9
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974575 | AUXILIARY LANDING FIELD (JSF) |  | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | N6247312C1802 AWD | 29475 | 28571 | 2012-07-09 |  | 2013-06-25 |  | 0.99 | 11951 | N42237636, FY 15 Prior Year Rescission, N32414547
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264611 | BACHELOR ENLISTED QUARTERS |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 32910 | 31756 | 2012-10-13 |  | 2014-10-16 |  | 0.99
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264612 | ENLISTED DINING FACILITY |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 5028 | 5176 | 2012-10-13 |  | 2014-10-16 |  | 0.98
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264621 | EMBASSY SECURITY GROUP FACILITIES |  | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081 | 25547 | 2013-03-14 | 2015-08-15 | 2015-03-15 | 2015-09-08 | 0.79
2015-07-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207624 | P-8A TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 14194 | 13886 | 2012-07-09 | 2014-03-24 | 2013-12-17 | 2014-04-09 | 1 | 11437 | N42237636, N42237100
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264632 | ACADEMIC INSTRUCTION FACILITY |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 60736 | 60289 | 2012-10-09 | 2015-08-31 | 2014-08-16 |  | 0.95 | 2502 | N47608561
2015-07-31 | 2012 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE |  | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167 | 36608 | 2014-05-01 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 0.43
2015-07-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207654 | P-8A HANGAR UPGRADES |  | 2012-12-20 | 2015-03-31 | HCR CONSTRUCTION INC | N6945015C1102 | 6448 | 5666 | 2015-04-14 | 2016-05-20 | 2016-05-19 | 2016-05-19 | 0.02
2015-07-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246705 | FITNESS CENTER, NORTH ISLAND |  | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | N6247310D5409 0013 | 46630 | 44478 | 2012-08-21 | 2015-07-27 | 2015-03-16 |  | 0.98
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001705 | AIRCRAFT MAINTENANCE HANGAR AND APRON |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 57582 | 65021 | 2012-06-12 | 2015-08-11 | 2014-07-07 | 2015-08-11 | 0.99 | 3690 | N32414547
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001710 | ORDNANCE LOADING AREA ADDITION |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 7768 | 7389 | 2012-06-12 | 2015-08-11 | 2014-07-07 | 2015-08-11 | 0.98 | 326 | N32414547
2015-07-31 | 2012 | Navy Active | Major Military Construction | ILLINOIS | UNITED STATES | N00128816 | DECENTRALIZE STEAM SYSTEM |  | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491 | 65168 | 2012-06-27 | 2015-11-06 | 2015-11-06 | 2015-11-06 | 0.72
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318822 | MCAS OPERATIONS COMPLEX |  | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 HC01 | 52970 | 51508 | 2012-05-02 |  | 2014-03-17 |  | 0.92
2015-07-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND |  | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977 | 57710 | 2012-07-17 | 2016-01-05 | 2015-03-30 |  | 0.92 | 1956 | Design
2015-07-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436913 | EHW SECURITY FORCE FACILITY |  | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | N4425512C3007 AWD | 13485 | 13554 | 2012-02-14 |  | 2013-08-08 |  | 0.76 | 7933 | N684691400
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204925 | DIP TANK CLEANING FACILITY |  | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | N6247309D1616 0009 | 7970 | 7893 | 2012-04-04 |  | 2013-09-27 |  | 0.92
2015-07-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE |  | 2012-02-17 | 2012-06-07 | NAVY STANDARD DOCUMENT | N6247012MPS0048 | 18810 | 20636 | 2012-06-21 |  | 2014-12-30 |  | 0.87
2015-07-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436985 | WRA VEHICLE BARRIERS |  | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | N4425510D5008 0012 | 9338 | 8948 | 2012-02-24 |  | 2013-12-10 |  | 0.86 | 7587 | N42237636
2015-07-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 1 OF 4 |  | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714 | 77927 | 2012-05-23 | 2016-01-13 | 2016-01-09 | 2016-01-11 | 0.93
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399991 | LAND EXPANSION |  | 2011-11-14 | 2015-01-15 | NAVY STANDARD DOCUMENT | N6247314MPRM002 | 2249 | 2092 | 2015-01-29 | 2016-01-15 |  |  | 0.37
2015-07-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY |  | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0003 | 14067 | 17444 | 2012-03-29 |  | 2013-08-14 |  | 0.97
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001003 | STAFF NCO ACADEMY FACILITIES |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260 | 28071 | 2013-09-19 | 2016-02-08 | 2015-09-01 | 2015-11-08 | 0.43
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557101A | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 | N41557101 | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | N6274210D1309 JQ01 | 24305 | 19381 | 2013-08-21 | 2015-12-15 | 2015-07-12 | 2015-12-15 | 0.74
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604113 | MV-22 AVIATION SIMULATOR BUILDING |  | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | N6247309D1619 0008 | 4380 | 4121 | 2013-06-27 |  | 2014-09-21 |  | 0.99
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811176 | SAN JACINTO ROAD EXTENSION |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428 | 4485 | 2014-10-08 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 0.12
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND |  | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091 | 27918 | 2013-09-19 | 2016-04-30 | 2016-01-18 | 2016-04-30 | 0.58
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865181 | HANGAR 5 RENOVATIONS & ADDITION |  | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0002 | 13634 | 14192 | 2013-09-27 | 2015-09-28 | 2015-09-28 | 2015-11-13 | 0.39 | 9166 | Design
2015-07-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB |  | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447 | 27961 | 2013-10-14 | 2016-04-17 | 2016-04-17 | 2016-06-16 | 0.84
2015-07-31 | 2013 | Navy Active | Major Military Construction | NEW JERSEY | UNITED STATES | N69213237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION |  | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | N4008513C3513 AWD | 34005 | 35160 | 2013-09-17 | 2015-02-12 | 2014-11-27 | 2015-06-26 | 1
2015-07-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620245 | EA-18G FLIGHT SIMULATOR FACILITY |  | 2012-08-16 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0009 | 5679 | 5973 | 2013-06-27 |  | 2014-11-25 |  | 0.97
2015-07-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY |  | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0007 | 14130 | 14112 | 2013-09-02 |  | 2015-03-12 | 2015-08-18 | 0.89
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243313 | ENTRY CONTROL POINT (GATE 5) |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974 | 10688 | 2014-01-03 |  | 2015-04-29 | 2016-02-25 | 0.51
2015-07-31 | 2013 | Navy Active | Major Military Construction | MISSISSIPPI | UNITED STATES | N63043317 | DINING FACILITY |  | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851 | 9291 | 2013-12-31 | 2015-12-02 | 2015-10-09 | 2015-10-09 | 0.35
2015-07-31 | 2013 | Navy Active | Major Military Construction |  | JAPAN | N61056353 | BACHELOR QUARTERS |  | 2013-01-24 | 2013-09-27 | NAVY STANDARD DOCUMENT | N6274213MP00015 | 5627 | 5521 | 2013-10-11 |  | 2015-01-05 |  | 0.93
2015-07-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151372 | PHYSICAL FITNESS CENTER |  | 2012-12-12 | 2013-09-27 | C.E.R. INC. | N4008010D0302 0021 | 11409 | 10856 | 2013-10-11 | 2015-09-16 | 2015-05-02 | 2015-09-16 | 0.94
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974378 | SECURITY OPERATIONS COMPLEX |  | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316 | 13766 | 2013-11-14 | 2015-07-31 | 2015-07-31 |  | 0.12
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M00263382 | FRONT GATE AT/FP IMPROVMENTS |  | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513 | 11094 | 2013-10-30 | 2015-10-11 | 2015-04-12 | 2015-10-11 | 0.76
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011384 | BASE ACCESS AND ROAD, PHASE 3 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666 | 30136 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 0.68
2015-07-31 | 2013 | Navy Active | Major Military Construction |  | ROMANIA | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | N6247014MPE0025 | 40018 | 38279 | 2014-05-14 | 2016-03-04 | 2015-03-01 | 2015-12-08 | 0.3
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169427 | GROUND SUPPORT EQUIPMENT SHOP |  | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | N6945013D1761 0001 | 10936 | 10809 | 2013-08-22 | 2015-08-14 | 2014-08-07 |  | 0.99
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169456 | SIMULATED LHD FLIGHT DECK |  | 2012-08-27 | 2013-06-26 | HEAD, INC. | N6945013C1773 AWD | 12302 | 12024 | 2013-07-10 | 2015-11-27 | 2014-07-11 |  | 0.97
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  | 2012-11-15 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643 | 37509 | 2014-08-29 | 2016-09-08 | 2016-09-08 | 2016-10-03 | 0.17
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169472 | AIRFIELD SECURITY UPGRADES |  | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | N6945013C1772 AWD | 11043 | 13288 | 2013-07-15 |  | 2014-03-28 | 2015-10-24 | 0.89
2015-07-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245500 | LCS TRAINING FACILITY |  | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553 | 40994 | 2013-10-14 | 2016-01-09 | 2015-10-24 | 2016-01-09 | 0.65 | 10760 | N42237100
2015-07-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191513 | A SCHOOL BARRACKS |  | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430 | 29196 | 2013-11-14 | 2016-04-01 | 2015-12-16 | 2015-12-30 | 0.45 | 5604 | N42237100
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462 | 28946 | 2013-10-07 | 2017-10-18 | 2016-11-06 | 2017-10-18 | 0.13
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974566 | COMBAT AIRCRAFT LOADING APRON |  | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247309D1603 0013 | 12671 | 12134 | 2013-10-11 |  | 2014-09-22 |  | 0.99 | 2574 | Design
2015-07-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191582 | UNDERSEA SURVEILLANCE SCIF FACILITY |  | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0003 | 4129 | 4853 | 2012-12-03 |  | 2013-11-29 |  | 0.99
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146601 | ARMORY |  | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0006 | 11782 | 11609 | 2013-09-19 | 2015-07-06 | 2015-04-08 | 2015-08-11 | 0.98
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264644 | WEAPONS TRAINING BATALLION MESS HALL |  | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168 | 12784 | 2013-09-18 | 2015-10-14 | 2015-04-22 | 2015-08-31 | 0.56
2015-07-31 | 2013 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207655 | BAMS MISSION CONTROL COMPLEX |  | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | N6945013C1257 AWD | 18180 | 18938 | 2013-08-28 | 2015-08-28 | 2014-12-27 | 2015-08-27 | 0.87
2015-07-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863709 | GENERAL PURPOSE WAREHOUSE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 2446 | 1935 | 2013-09-06 | 2015-08-15 | 2015-03-20 |  | 0.66
2015-07-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863710 | HIGH EXPLOSIVE MAGAZINE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 5849 | 6240 | 2013-09-06 | 2015-08-15 | 2015-03-20 |  | 0.63 | 3704 | Design
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001711 | PERSONNEL ADMINISTRATION CENTER |  | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0018 | 6449 | 5668 | 2013-09-20 | 2015-12-24 | 2015-07-06 | 2015-12-24 | 0.79
2015-07-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232900 | BAMS MAINTENANCE TRAINING FACILITY |  | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301 | 8754 | 2013-09-10 |  | 2014-11-21 |  | 0.5
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318904 | MV-22 HANGAR AND INFRASTRUCTURE |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 63056 | 56721 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-29 | 0.7
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318905 | AIRCRAFT STAGING AREA |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 11118 | 7842 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-29 | 0.65
2015-07-31 | 2013 | Navy Active | Major Military Construction |  | GREECE | N66691907 | AIRCRAFT PARKING APRON EXPANSION |  | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPAQOLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663 | 13453 | 2014-07-25 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 0.29 | 417 | FY Prior Year Rescission
2015-07-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246909 | H-60S SIMULATOR TRAINING FACILITY |  | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088 | 2962 | 2014-03-14 |  | 2015-03-15 |  | 0.85
2015-07-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990A | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 2 OF 4 | N68436990 | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 280041 | 259387 | 2012-11-15 | 2016-01-13 | 2016-01-09 | 2016-01-11 | 0.76
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212984 | REGIMENTAL HEADQUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028 | 10981 | 2013-09-13 | 2015-12-21 | 2015-06-26 | 2015-11-09 | 0.64
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212985 | BACHELOR ENLISTED QUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418 | 17922 | 2013-09-13 | 2015-12-21 | 2015-06-26 | 2015-11-09 | 0.58
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212986 | MOTOR TRANSPORTATION FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 5841 | 5738 | 2013-09-13 | 2015-08-27 | 2015-03-23 |  | 0.95
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212987 | SUPPLY WAREHOUSE FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 6987 | 6693 | 2013-09-13 | 2015-08-27 | 2015-03-23 |  | 0.94
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212989 | ARMORY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 3653 | 3535 | 2013-09-13 | 2015-08-27 | 2015-03-23 |  | 0.96
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613995 | MAINTENANCE HANGAR IMPROVEMENTS |  | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT | N6274214MP00027 | 4947 | 4926 | 2014-06-06 |  | 2015-06-14 |  | 0.38
2015-07-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH |  | 2014-04-07 | 2014-07-25 | NAVY STANDARD DOCUMENT | N6274214MP00039 | 6304 | 6304 | 2014-08-08 | 2015-09-24 | 2015-09-24 | 2015-09-24 | 0.6
2015-07-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE |  | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374 | 27765 | 2013-12-11 | 2016-02-12 | 2015-12-27 | 2015-12-27 | 0.67
2015-07-31 | 2014 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61152001 | MARFORCYBERCOM HQ-OPS BUILDING |  | 2014-01-13 | 2015-04-07 | NAVY STANDARD DOCUMENT | N6247015MPC0032 | 109736 | 106596 | 2015-04-21 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 0
2015-07-31 | 2014 | Navy Active | Major Military Construction |  | JAPAN | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458 | 9458 | 2014-10-03 | 2017-01-17 | 2016-08-16 | 2017-01-17 | 0
2015-07-31 | 2014 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249 | 121177 | 2014-09-03 | 2018-04-08 | 2018-06-20 | 2018-04-08 | 0.11
2015-07-31 | 2014 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411103 | HEWITT HALL RESEARCH CENTER |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319 | 13033 | 2014-08-14 | 2015-12-16 | 2015-12-16 | 2016-01-01 | 0.37
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820 | 57046 | 2014-05-21 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 0.12
2015-07-31 | 2014 | Navy Active | Major Military Construction | OKLAHOMA | UNITED STATES | N83447136 | TACAMO E-6B HANGAR |  | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19401 | 18672 | 2014-10-14 | 2016-04-06 | 2016-02-12 | 2016-03-02 | 0.09
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M002641406 | ATC TRANSMITTER/RECEIVER RELOCATION (MCAF) |  | 2014-12-18 | 2015-05-01 | BISCAYNE CONTRACTORS, INC. | N4008015C2007 | 4503 | 4270 | 2015-05-15 | 2016-11-21 | 2016-11-30 | 2016-11-21 | 0
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557J200 | NORTH RAMP UTILITIES II |  | 2014-04-11 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 | 53014 | 47830 | 2014-10-31 | 2016-10-03 | 2016-09-02 | 2016-09-02 | 0.03
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction |  | JAPAN | M67400201 | AIRFIELD SECURITY UPGRADES |  | 2013-11-08 | 2014-04-18 | NAVY STANDARD DOCUMENT | N6274214MP00024 | 2881 | 2861 | 2014-05-02 | 2015-10-26 | 2016-02-10 | 2015-10-26 | 0.21
2015-07-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A227 | ARMORY |  | 2014-02-26 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492 | 4227 | 2014-08-08 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 0.13
2015-07-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620239 | EA-18G FACILITY IMPROVEMENTS |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5004 | 29692 | 25445 | 2014-09-08 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 0.14
2015-07-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620251 | P-8A HANGAR AND TRAINING FACILITIES |  | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5002 AWD | 84889 | 80114 | 2014-08-04 | 2016-01-26 | 2016-01-12 | 2016-01-26 | 0.24
2015-07-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813270 | DRYDOCK WATERFRONT FACILITY |  | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355 | 20351 | 2014-03-03 | 2016-12-30 | 2015-12-11 | 2015-12-11 | 0.16
2015-07-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232281 | AIRCRAFT ENGINE TEST PADS |  | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | N6247309D1657 0016 | 6106 | 5760 | 2014-06-26 | 2015-11-30 | 2015-07-17 |  | 0.58
2015-07-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970 | 30557 | 2014-07-14 | 2017-10-27 | 2017-08-03 | 2017-10-27 | 0.29
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011353 | LANDFILL, PHASE 4 |  | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529 | 13951 | 2014-09-08 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 0.56
2015-07-31 | 2014 | Navy Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | N684691400 | NAVSEA HQ RESTORATION |  | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | N6247013D6019 JU01 | 48905 | 48845 | 2014-02-14 | 2015-01-30 | 2015-01-31 | 2015-01-31 | 1
2015-07-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179 | 10402 | 2014-08-01 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 0.11
2015-07-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201425 | LCS LOGISTICS SUPPORT FACILITY |  | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | N6945013D1765 0002 | 15842 | 15287 | 2014-06-13 | 2015-11-26 | 2015-11-26 | 2016-01-10 | 0.73
2015-07-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755425 | MODULAR STORAGE MAGAZINE |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865 | 47116 | 2014-05-26 | 2016-06-11 | 2016-06-11 | 2017-01-20 | 0.23
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011445 | STEAM DECENTRALIZATION (CAMP JOHNSON) |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 2123 | 1934 | 2015-02-06 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 0.4
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011447 | STEAM DECENTRALIZATION (HADNOT POINT) |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 9605 | 9042 | 2015-02-06 | 2016-02-07 | 2014-12-30 | 2016-02-19 | 0.06
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011448 | STEAM DECENTRALIZATION, BEQ NODES (HADNOT POINT) |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 15756 | 14899 | 2015-02-06 | 2016-02-07 | 2015-09-30 | 2016-02-19 | 0.06
2015-07-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365 | 1193 | 2014-07-14 | 2016-01-01 | 2016-01-01 | 2016-01-01 | 0.14
2015-07-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755518 | X-RAY WHARF IMPROVEMENTS |  | 2014-01-10 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085 | 43539 | 2014-06-17 | 2016-09-20 | 2016-10-20 | 2016-10-20 | 0.17
2015-07-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755566 | EMERGENT REPAIR FACILITY EXPANSION |  | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860 | 27784 | 2014-04-24 | 2016-05-12 | 2016-05-12 | 2016-06-29 | 0.3
2015-07-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232593 | BAMS CONSOLIDATED MAINTENANCE HANGAR |  | 2014-04-30 | 2015-01-16 | I E PACIFIC INC | N6247309D1657 0019 | 18400 | 17408 | 2015-01-30 | 2016-09-30 | 2016-09-17 | 2016-09-17 | 0.06
2015-07-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232599 | UNACCOMPANIED HOUSING CONVERSION (PORT HUENEME) |  |  | 2014-11-24 | NAVY STANDARD DOCUMENT | N6247314RP00165 | 33594 | 30093 | 2014-12-08 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 0.87
2015-07-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710 | 49709 | 2014-04-10 | 2016-04-25 | 2016-04-25 | 2016-09-23 | 0.17
2015-07-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY |  | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170 | 14391 | 2014-04-03 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 0.62
2015-07-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755638 | SIERRA WHARF IMPROVEMENTS |  | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | N4019210D2808 0009 | 1462 | 1229 | 2014-06-13 |  | 2015-03-26 |  | 0.87
2015-07-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION |  | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573 | 9288 | 2014-10-10 | 2016-06-26 | 2016-04-19 | 2016-06-26 | 0
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312 | 13282 | 2014-06-13 | 2016-03-31 | 2015-12-20 | 2015-12-20 | 0.23
2015-07-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151 | 13631 | 2014-08-29 | 2016-01-07 | 2016-01-07 | 2016-02-14 | 0.26
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001726 | REGIONAL COMMUNICATION STATION |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159 | 10037 | 2014-06-13 | 2016-03-31 | 2015-12-20 | 2015-12-20 | 0.23
2015-07-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446 | 11311 | 2014-09-30 | 2016-10-25 | 2016-10-25 | 2016-10-25 | 0.01
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318852 | 3RD RADIO BATTALION COMPLEX |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407 | 17505 | 2014-09-19 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 0.03
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318864 | AIRCRAFT MAINTENANCE EXPANSION |  | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | N6274214C1315 AWD | 16968 | 15248 | 2014-04-30 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 0.68
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720 | 15165 | 2014-10-14 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 0.06
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 | 47646 | 24012 | 2015-04-28 | 2017-04-03 | 2017-01-03 | 2017-01-03 | 0.01
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318908 | MV-22 HANGAR |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 | 53999 | 42777 | 2015-04-28 | 2017-04-03 | 2017-01-03 | 2017-01-03 | 0
2015-07-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990B | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990 | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 24880 | 13812 | 2014-01-14 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 0.63
2015-07-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A921 | UNACCOMPANIED HOUSING |  | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714 | 19593 | 2014-10-15 | 2016-07-25 | 2016-05-30 | 2016-07-25 | 0.27
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  | 2013-12-06 | 2014-09-10 | BLUEFORGE, LLC | N6945014D1271 0001 | 14685 | 14309 | 2014-09-24 | 2016-01-25 | 2016-01-25 | 2016-01-25 | 0.06
2015-07-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004954 | CERS DISPATCH FACILITY |  | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | N6945012D1769 0005 | 1248 | 1184 | 2014-06-16 |  | 2015-06-02 |  | 0.89
2015-07-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND |  | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904 | 8505 | 2014-08-18 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 0.24
2015-07-31 | 2015 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813048 | SUBMARINE MANEUVERING ROOM TRAINER FACILITY |  | 2014-10-20 | 2015-02-27 | JSR ECC, LLC | N6247814D4003 | 8667 | 8087 | 2015-03-13 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 0
2015-07-31 | 2015 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399159 | CAMP WILSON INFRASTRUCTURE UPGRADES |  | 2015-01-30 | 2015-04-15 | RQ-BERG JV | N6247310D5482 0009 | 28645 | 26826 | 2015-04-29 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 0
2015-07-31 | 2015 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N63042327 | F-35C OPERATIONAL TRAINING FACILITY |  | 2015-03-02 | 2015-06-26 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0007 | 21588 | 21401 | 2015-07-10 | 2016-10-17 |  | 2016-10-17 | 0
2015-07-31 | 2015 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N63042328 | F-35C FACILITY ADDITION AND MODIFICATION |  | 2015-02-24 | 2015-06-11 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0006 | 17017 | 15932 | 2015-06-25 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 0
2015-07-31 | 2015 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436422 | INTEGRATED WATER TREATMENT SYSTEM DD 1, 2 & 5 |  | 2014-12-01 | 2015-05-04 | TRITON MARINE CONSTRUCTION CORP. | N4425514D9007 0003 | 12592 | 11013 | 2015-05-18 | 2016-10-25 | 2016-10-25 | 2016-10-25 | 0.01
2015-07-31 | 2015 | Navy Active | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 | 34317 | 32014 | 2015-06-01 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 0
2015-07-31 | 2015 | Navy Active | Major Military Construction |  | JAPAN | M62613602 | SECURITY MODS DPRI MC167-T (CVW-5 E2D EA-18G) |  | 2014-11-21 | 2015-04-27 | NAVY STANDARD DOCUMENT | N6274215MP00014 | 4913 | 4742 | 2015-05-11 | 2016-09-12 | 2016-06-13 | 2016-06-13 | 0
2015-07-31 | 2015 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207631 | P-8A RUNWAY THRESHOLDS AND TAXIWAYS |  | 2014-04-01 | 2015-02-27 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 | 11078 | 10269 | 2015-03-13 | 2016-06-26 | 2016-04-19 | 2016-06-26 | 0.07
2015-07-31 | 2015 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207664 | MH-60 PARKING APRON |  | 2015-01-26 | 2015-04-30 | PHOENIX CONSTRUCTION SERVICES, INC. | N6945015C1104 | 7293 | 6516 | 2015-05-14 | 2016-04-29 | 2016-04-30 | 2016-04-30 | 0
2015-07-31 | 2015 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318778 | ARMORY ADDITION AND RENOVATION |  | 2014-01-10 | 2015-03-13 | DAWSON-HAWAIIAN BUILDERS I | N6274215C1316 | 14825 | 12576 | 2015-03-27 | 2017-08-09 | 2017-07-14 | 2017-08-09 | 0
2015-07-31 | 2015 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990C | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 4 OF 4 | N68436990 | 2011-12-13 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 80735 | 70746 | 2015-01-22 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 0.08
2015-07-31 | 2015 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204939 | ENGINE DYNAMOMETER FACILITY |  | 2015-01-14 | 2015-03-31 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0003 | 15300 | 14268 | 2015-04-14 | 2016-09-30 | 2016-10-06 | 2016-10-06 | 0
2015-07-31 | 2015 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  | 2013-12-10 | 2015-07-22 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 | 38595 | 37267 | 2015-08-05 | 2017-07-24 |  |  | 0
2015-07-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246730 | BACHELOR QUARTERS |  | 2013-05-29 | 2015-07-30 | HENSEL PHELPS CONSTRUCTION CO | N6247315C1614 | 74785 | 70541 | 2015-08-13 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 0
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054012 | CONSTRUCT NACCC ADDITION |  | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | N4008410D0014 0003 | 1380 | 1256 | 2011-06-24 | 2012-04-20 | 2012-04-13 | 2012-04-20 | 0.96
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) |  | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | N6247810D4020 0014 | 1559 | 1446 | 2011-10-03 | 2013-03-01 | 2012-12-24 | 2013-03-01 | 1
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N57095101 | ROAD IMPROVEMENTS CAMP ALLEN AREA |  | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | N4008509D5027 0003-PC000002 | 1381 | 1326 | 2011-02-28 | 2012-01-27 | 2011-09-21 | 2012-01-27 | 1
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY |  | 2011-05-26 | 2011-08-03 | JESSICO, INC | N4008511C3026 AWD | 2085 | 1989 | 2011-08-17 | 2012-11-13 | 2012-09-30 | 2012-11-13 | 0.98
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING |  | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | N4008506D6009 0008 | 928 | 950 | 2011-07-04 | 2012-04-16 | 2012-01-26 | 2012-04-30 | 1
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | N32414203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES |  | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | N4008512C5002 AWD | 1951 | 1838 | 2012-03-16 | 2012-08-28 | 2012-09-13 | 2012-09-13 | 1
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | N69213206 | CONSTRUCT DISPATCH CENTER |  | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | N4008510D9451 0005 | 1630 | 1633 | 2011-12-01 | 2013-03-26 | 2013-01-25 | 2013-03-29 | 1
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG |  | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008512C7000 AWD | 1725 | 1616 | 2011-11-18 | 2013-05-08 | 2012-07-21 | 2013-05-31 | 1
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042331 | WATER WELL |  | 2011-01-11 | 2011-09-30 | EPC CORPORATION | N6247310D5415 0012 | 2713 | 2887 | 2011-10-14 | 2013-11-22 | 2012-10-01 | 2013-05-21 | 1
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092199 | MSRON FOUR BOAT STORAGE BUILDING |  | 2012-10-31 | 2012-12-14 | JESSICO, INC | N4008511D3021 0008 | 970 | 938 | 2012-12-28 | 2013-11-15 | 2013-11-08 | 2013-11-15 | 1
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241294 | CONNECT TO KINGSVILLE WATER SYSTEM |  | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | N6945010D0776 0002 | 1658 | 1549 | 2012-10-08 | 2014-08-25 | 2014-03-21 | 2014-08-25 | 0.99
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 |  | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | N6247312C3410 AWD | 1980 | 1878 | 2012-09-12 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 1
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT |  | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | N6247312C3413 AWD | 2000 | 1897 | 2012-10-12 | 2014-03-05 | 2013-09-26 | 2014-03-05 | 1
2015-07-31 | 2012 | Marine Corps Active | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | M670011425 | OVERHEAD RANGE BAFFLE SYSTEM |  | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008511D8026 0008 | 2297 | 2215 | 2013-03-06 | 2014-11-29 | 2014-04-17 | 2014-11-29 | 0.97
2015-07-31 | 2012 | Marine Corps Reserve | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | N00206501 | MILITARY WORKING DOG FACILITY |  | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | N6945013C5571 AWD | 1286 | 1237 | 2013-08-29 | 2014-06-20 | 2014-05-22 | 2014-06-20 | 1
2015-07-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212543 | NAVELSG RESERVE FORCES MARSHALLING YARDS |  | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | N4008511D6588 0006 | 738 | 747 | 2013-01-30 | 2013-10-23 | 2014-01-21 | 2014-01-21 | 0.95
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63406563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 |  | 2012-06-20 | 2012-09-28 | NOVA R M F | N6247312D0245 0003 | 1939 | 1875 | 2012-10-12 | 2014-06-23 | 2013-09-27 | 2014-07-01 | 1
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863708 | CONSTRUCT LCAC BEACH ACCESS RAMP |  | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | N3319110D0219 0009 | 1751 | 1411 | 2013-10-13 | 2014-06-20 | 2014-05-28 | 2014-06-20 | 0.97
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N00204791 | HVAC JOINT AVIATION SURVIVAL TRAINING |  | 2012-07-25 | 2012-09-29 | R L BURNS INC. | N6945012C6343 AWD | 2038 | 1975 | 2012-10-13 | 2013-12-19 | 2013-08-08 | 2013-08-08 | 1
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436839 | RENOVATE LOWER BASE FIRE STATION |  | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | N4425509D4007 0017 | 1389 | 1333 | 2012-09-14 | 2013-08-31 | 2013-08-31 | 2013-11-22 | 1
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61014851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION |  | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | N6247314C2801 AWD | 1916 | 1895 | 2014-01-02 | 2014-12-31 | 2014-10-17 | 2014-12-31 | 1
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY |  | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | N6247311D0067 0004 | 1816 | 1742 | 2013-02-21 | 2015-01-28 | 2014-01-31 | 2014-10-17 | 0.99
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N47609003 | EOD/TEU RANGE SUPPORT FACILITY |  | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | N6247313D4608 0007 | 1896 | 1792 | 2014-06-27 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0.49
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054022 | IKEGO YOUTH CENTER (IKEGO HSG AREA - 3087) |  |  | 2014-02-06 | HIBIYA ENGINEERING LTD. | N4008410D0121 0035 | 840 | 898 | 2014-02-20 |  |  |  | 0.98
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | N32411056 | VPT TEST FACILITY |  | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | N4008510D9450 0006 | 2332 | 2331 | 2013-03-28 | 2013-11-21 | 2013-10-31 | 2013-12-13 | 0.99
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction |  | SINGAPORE | N61077123 | TEMPORARY LCS SUSTAINMENT FACILITY |  | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | N4008413C9001 AWD | 755 | 768 | 2012-12-20 | 2014-01-15 | 2013-03-10 | 2013-03-10 | 0.93
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction | OREGON | UNITED STATES | N00620246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY |  | 2013-06-18 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | N4425513C7005 AWD | 1120 | 1073 | 2013-10-14 | 2015-01-21 | 2014-09-30 | 2014-12-19 | 0.98
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 |  | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008513C7711 AWD | 1925 | 1890 | 2013-03-14 | 2013-09-12 | 2013-08-30 | 2013-09-29 | 0.86
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241288 | WASTEWATER SYSTEM |  | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | N6945014C0763 AWD | 1790 | 1682 | 2014-04-11 | 2015-07-17 | 2015-03-27 | 2015-05-27 | 0.96
2015-07-31 | 2013 | Marine Corps Active | Unspecified Minor Military Construction |  | JAPAN | M67400305 | DEMOLISH 45 HOUSING UNITS, KISHABA HOUSING |  | 2013-07-10 | 2014-09-25 | NAVY STANDARD DOCUMENT | N6274214MP00043 | 1729 | 1719 | 2014-10-09 | 2015-06-29 | 2015-06-29 | 2015-06-29 | 0.39
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436857 | FLOATING LABORATORY, MOORING DOLPHINS |  | 2013-01-16 | 2013-05-17 | NOVA GROUP INC | N4425510D5019 0003 | 3406 | 3121 | 2013-05-31 | 2014-05-19 | 2013-05-07 | 2014-01-15 | 1
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246943 | POWER DISTRIBUTION TO OP-3 TO SUPPORT ELMR |  | 2014-05-06 | 2014-09-16 | NAVY STANDARD DOCUMENT | N6247014POR0018 | 1652 | 1425 | 2014-09-30 |  |  |  | 0.44
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813058 | ROCKFALL PROTECTION AT RED HILL |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810 | 2654 | 2014-12-08 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 0
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | N60042116 | D5 MISSILE MOTOR MAGS MODS (NAVOBSSTA FLAGSTAFF AZ) |  |  | 2014-12-11 | NAVY STANDARD DOCUMENT | N6247315MPRM001 | 1725 | 1560 | 2014-12-25 |  |  |  | 0
2015-07-31 | 2014 | Marine Corps Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | M0031886167 | TEMPORARY MEDICAL FACILITY SITE PREPARATION |  | 2014-07-31 | 2014-12-22 | CT JV | N6247814D4004 KB01 | 1667 | 1630 | 2015-01-05 | 2015-09-16 | 2015-07-07 | 2015-08-14 | 0.89
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61057221 | HELO ALFS TEST ROOM, BUILDING 194 |  | 2014-06-12 | 2014-08-06 | NIHON MECCS CO., LTD. | N4008414C8302 AWD | 890 | 812 | 2014-08-20 | 2015-05-15 | 2015-02-03 | 2015-05-19 | 0.91
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61065240 | STANDARD MISSILE-6 ALL UP ROUND TEST FACILITY |  | 2015-02-23 | 2015-04-16 | TEEHEE ENGINEERING, INC. | N6247315C4204 | 1950 | 1863 | 2015-04-30 | 2016-09-30 | 2016-09-30 | 2016-10-21 | 0.02
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N00620257 | HANGAR 11 MODIFICATIONS FOR SEARCH AND RESCUE |  | 2014-06-20 | 2014-09-02 | RORE, INC. | N4425514C8012 | 1424 | 1384 | 2014-09-16 | 2015-01-30 | 2015-02-02 | 2015-02-02 | 1
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  | 2014-08-11 | 2014-09-30 | REILLY CONSTRUCTION, INC | N4008014D3014 AWD | 1453 | 1358 | 2014-10-14 | 2015-04-14 | 2015-05-26 | 2015-05-26 | 0.16
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042376 | VFA-94 HANGAR ALTERATIONS |  | 2014-08-27 | 2014-09-27 | COPPERTOP LEDCOR JV | N6247313D4608 0014 | 1839 | 1650 | 2014-10-11 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 0.11
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | GUAM | GUAM | N61755630 | HARDEN ELECTRICAL DISTRIBUTION LINE (POLARIS PT ROAD) |  | 2014-07-01 | 2014-09-30 | P&S CONSTRUCTION, INC. | N4019210D2804 0019 | 2000 | 1925 | 2014-10-14 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 0.23
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092662 | EOD ESU TWO EXPEDITIONARY LOGISTICS OVERHAUL WAREHOUSE |  | 2014-05-09 | 2014-08-06 | DOYON MANAGEMENT SERVICES, LLC | N4008514D2102 0001 | 1020 | 239 | 2014-08-20 | 2015-01-20 | 2014-11-21 | 2015-01-20 | 0.24
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863733 | PROVIDE ELECTROMAGNETIC CALIBRATION COMPLEX |  | 2014-08-29 | 2014-09-19 | NEWIMAR SA | N3319110D1801 0283 | 1144 | 713 | 2014-10-03 | 2015-08-21 | 2014-11-22 | 2016-11-11 | 0.17
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436855 | SUBMARINE BRIDGE TEAM SIMULATOR (BANGOR) |  | 2015-01-30 | 2015-06-30 | DOYON MANAGEMENT SERVICES, LLC | N4425515C8000 | 1951 | 1824 | 2015-07-14 | 2016-05-15 |  | 2016-05-27 | 0
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A917 | CRITICAL POWER FOR BULDING 200 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1120 | 1120 | 2014-06-05 |  |  |  | 1
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A918 | CRITICAL POWER FOR BUILDING T-130 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1175 | 1175 | 2014-06-05 |  |  |  | 1
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A919 | CRITICAL POWER FOR BLDGS 111, 113 AND 115 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1064 | 1064 | 2014-06-05 |  |  |  | 1
2015-07-31 | 2015 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N60508278 | PAVEMENT LANDING SYSTEMS (NOLF CHOCTAW/EGLIN AFB) |  | 2014-04-28 | 2015-07-22 | NAVY STANDARD DOCUMENT | N6247015MPS0050 | 1367 | 1364 | 2015-08-05 | 2016-01-26 | 2016-02-08 | 2016-02-08 | 0
2015-07-31 | 2011 | Marine Corps Active | Military Family Housing |  | GUANTANAMO BAY NAVAL BASE | N605141403 | REPLACE BASE HOUSING |  | 2015-03-06 | 2011-09-30 | LAKESHORE TOLTEST JV, LLC | N6945011C1260 AWD | 35175 | 38814 | 2011-10-14 |  | 2014-03-16 |  | 0.23439
2015-07-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 |  | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | N4008412D6501 0002 | 13357 | 12685 | 2012-08-13 | 2013-12-13 | 2013-11-23 | 2013-12-14 | 1
2015-07-31 | 2013 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 |  | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | N4008414C5500 AWD | 17551 | 16715 | 2014-06-22 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 0.14009
2015-07-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626131001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 |  | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | N4008412D6501 0004 | 11335 | 10953 | 2012-08-14 | 2015-02-20 | 2014-12-20 | 2015-02-02 | 0.99684
2015-07-31 | 2011 | Marine Corps Active | Military Family Housing Improvement | DISTRICT OF COLUMBIA | UNITED STATES | M670291101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 |  | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0001-07 | 41 | 39 | 2011-01-28 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 1
2015-07-31 | 2012 | Marine Corps Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  |  | 2012-01-04 |  |  | 45 | 45 | 2012-01-18 |  | 2012-01-31 |  | 1
2015-07-31 | 2014 | Marine Corps Active | Military Family Housing Improvement | GUAM | GUAM | N61755H106 | WHOLE HOUSE REVITALIZATION PHASE II AT LOCKWOOD TERRACE |  | 2013-11-14 | 2015-04-30 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 0002 | 24771 | 23121 | 2015-05-14 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 0.01796
2015-07-31 | 2012 | Marine Corps Reserve | Major Military Construction | TENNESSEE | UNITED STATES | M68479030 | RESERVE CENTER TRAINING CENTER - MEMPHIS |  | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | N4008313C0019 AWD | 9006 | 8565 | 2013-04-19 |  | 2015-02-17 |  | 0.98977
2015-07-31 | 2011 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | M68479060 | MARINE CORPS RESERVE CENTER |  | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0005 | 14630 | 14202 | 2011-10-11 | 2014-04-15 | 2013-02-08 | 2014-03-01 | 0.99789
2015-07-31 | 2011 | Marine Corps Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | M67399092 | TANK VEHICLE MAINTENANCE FACILITY |  | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | N6247309D1615 0041 | 6458 | 6168 | 2011-10-06 | 2013-03-11 | 2012-09-21 | 2013-03-28 | 0.99899
2015-07-31 | 2013 | Marine Corps Reserve | Major Military Construction | NEW YORK | UNITED STATES | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY |  | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911 | 4798 | 2013-09-19 | 2015-11-04 | 2014-12-04 | 2015-10-14 | 0.16286
2015-07-31 | 2014 | Marine Corps Reserve | Major Military Construction | MISSOURI | UNITED STATES | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019 | 16036 | 2014-09-05 | 2016-02-23 | 2016-02-23 | 2016-02-23 | 0.068553
2015-07-31 | 2011 | Marine Corps Reserve | Military Family Housing Improvement |  | JAPAN | M626130501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 |  | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | N4008411C5504 AWD | 11626 | 11102 | 2011-10-06 | 2013-02-28 | 2013-01-14 | 2013-02-28 | 1
2015-07-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER |  | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | N4008411C0129 AWD | 17378 | 16915 | 2011-07-15 | 2013-01-17 | 2012-12-03 | 2013-01-20 | 1
2015-07-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N627351102 | WHOLEHOUSE IMPROVEMENT |  | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | N4008411C0006 AWD | 8127 | 6990 | 2011-07-10 | 2013-01-18 | 2012-10-17 | 2013-02-14 | 1
2015-07-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) |  | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | N4008412C0108 AWD | 19730 | 18773 | 2012-08-01 | 2014-01-13 | 2014-01-13 | 2014-01-13 | 1
2015-07-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR |  | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | N4008412C8325 AWD | 5990 | 5654 | 2012-10-10 | 2013-11-22 | 2013-08-26 | 2013-11-22 | 1
2015-07-31 | 2012 | Navy Active | Military Family Housing Improvement |  | SPAIN | N628631201 | WHOLEHOUSE REVITALIZATION, LAS PALMERAS, PHASE 3 |  | 2014-04-29 | 2015-03-13 |  | 0DUMMY3295023 AWD | 13982 | 13478 | 2015-03-27 |  |  |  | 0.020337
2015-07-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 |  | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | N4008412C0109 AWD | 9033 | 9310 | 2012-08-22 |  | 2014-10-07 |  | 0.96493
2015-07-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) |  | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | N4008412C0004 AWD | 17540 | 14246 | 2012-08-29 | 2014-07-01 | 2013-12-09 | 2014-07-01 | 1
2015-07-31 | 2013 | Navy Active | Military Family Housing Improvement | GUAM | GUAM | N617551301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE |  | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 JQ02 | 26805 | 25413 | 2013-09-26 | 2015-10-09 | 2015-09-09 | 2015-10-10 | 0.92345
2015-07-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES |  | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | N4008414C8401 AWD | 12958 | 12050 | 2013-12-15 |  | 2015-03-31 |  | 0.95751
2015-07-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 |  | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791 | 7305 | 2014-07-29 | 2016-02-21 | 2016-02-21 | 2016-02-21 | 0.28296
2015-07-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) |  | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799 | 21589 | 2014-10-14 |  |  |  | 0.049712
2015-07-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 |  | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545 | 15632 | 2014-10-13 | 2016-02-02 | 2016-02-02 | 2016-02-02 | 0
2015-07-31 | 2014 | Navy Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611407 | SITE IMPROVEMENTS - GENERAL OFFICERS QUARTERS A |  |  | 2014-09-30 | QUALITY SUPPORT SERVICES, INC. | N4008314D1014 0003 | 75 | 93 | 2014-10-14 |  | 2014-11-30 |  | 0.035205
2015-07-31 | 2014 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | M68479031 | RESERVE BOAT MAINTENANCE AND STORAGE FACILITY |  | 2014-12-12 | 2015-03-24 | ACCEL PACIFIC JV | N4008314D3232 WE01 | 3497 | 3286 | 2015-04-07 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 0.011532
2015-07-31 | 2013 | Navy Reserve | Major Military Construction | TEXAS | UNITED STATES | N83447047 | COMMERCIAL VEHICLE INSPECTION SITE |  | 2013-01-22 | 2013-09-12 | KOMADA, LLC | N6945013D1767 0001 | 6894 | 7666 | 2013-09-26 |  | 2014-11-06 |  | 0.57066
2015-07-31 | 2011 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | N00206477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY |  | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | N6945011C0756 AWD | 13604 | 14492 | 2011-06-17 |  | 2013-06-07 |  | 0.953
2015-07-31 | 2011 | Navy Reserve | Major Military Construction | VIRGINIA | UNITED STATES | N69212743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX |  | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008509D5019 0003 | 15431 | 17547 | 2011-06-17 |  | 2013-04-27 |  | 0.98617 | 558 | Design
2015-07-31 | 2015 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | N00620234 | C-40 RESERVE MAINTENANCE HANGAR |  | 2014-12-30 | 2015-07-29 | SWINERTON BUILDERS | N4425515C6001 AWD | 59450 | 28020 | 2015-08-12 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 0
2015-07-31 | 2012 | Navy Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414860 | ARMED FORCES RESERVE CENTER, PITTSBURGH |  | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | N4008312C0005 AWD | 12033 | 12348 | 2012-08-14 |  | 2014-02-06 |  | 0.99443 | 500 | Design
2015-07-31 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | MISSOURI | UNITED STATES | NGA021 | Data Ctr West #1 Power & Cooling Upgrade |  | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors |  | 8202 | 11198 | 2012-08-06 | 2014-01-21 | 2013-08-06 | 2015-01-31 | 0.99 | 1975 |  | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 30 September 2015
2015-07-31 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | NGA013 | Technology Center Third Floor Fit-out |  | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 32387 | 39495 | 2012-11-02 | 2014-05-30 | 2014-01-02 | 2015-01-31 | 0.99 | 1975 | NGA021 | Technology Center Third Floor Fit-out - project period of performance extended to 31 May 2015
2015-07-31 | 2007 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES |  | Infrastructure Increments 1-3; NGA HQ's | [8 empty] | 2011-09-15 | 2013-06-15 | 31-Apr-2015 | 1 |  |  | ["Various" for Solicitation Date, Award Date, Start Date, Prime Contract Recipient (Company Name); "N/A" for Original Contract Amount, Current Contract Obligation, Diverted Funds Amount]
2015-07-31 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 65416 | NGA Headquarters, SCIF, All Phases |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture | W912DR-07-C-0027 | 1409901 | 1467244 | 2007-09-06 | 2011-04-19 | 2011-12-22 | 2015-11-21 | 0.99 |  |  | ["N/A" for Diverted Funds Amount]
2015-07-31 | 2009 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060 | 13760 | 2010-09-21 | 2013-01-17 | 2013-01-17 | 2014-04-18 | 0.99
2015-07-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223 | 129078 | 2010-09-21 | 2015-10-12 | 2014-04-18 | 2015-10-12 | 0.98 | 37500
2015-07-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443 | 4201 | 2010-09-09 | 2012-06-29 | 2011-09-26 | 2012-06-29 | 0.99
2015-07-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253 | 5792 | 2013-05-15 | 2014-11-30 | 2014-03-07 | 2015-05-04 | 0.999 |  |  | Completing remaining punch list items.
2015-07-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17781 | Tordella Chilled Water Backup Storage |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700 | 11700 | 2010-06-30 | 2012-05-30 | 2011-08-20 | 2012-05-30 | 1
2015-07-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17782 | R&E Chilled Water Backup Storage |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200 | 3200 | 2011-11-07 | 2014-10-31 | 2013-07-13 | 2015-07-31 | 0.78 |  |  | Due to problems with Commissioning of chiller plant the tank has been pushed out to Aug 2015
2015-07-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18052 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566 | 8257 | 2011-03-31 | 2014-05-14 | 2013-02-01 | 2014-05-14 | 1
2015-07-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18053 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095 | 16448 | 2012-01-31 | 2014-05-31 | 2013-02-01 | 2014-05-31 | 1
2015-07-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18054 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085 | 7316 | 2012-11-30 | 2014-08-31 | 2013-02-01 | 2014-08-31 | 0.92 |  |  | Commissioning of system completed November 26, 2014.
2015-07-31 | 2011 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900 | 130250 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-10-31 | 0.991 | 54500 | Mountainview, South Campus Electrical Utility Plant | Working in minor change orders and waiting for the demolition.
2015-07-31 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 20489 23994 | MOD II |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657 | 8867 | 2012-05-30 | 2014-03-03 | 2014-01-30 | 2015-01-16 | 1
2015-07-31 | [6 empty] | MOD II (Phase 2) |  | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620 | 2657 | 2013-11-26 | 2014-09-30 | 2014-02-28 | 2014-04-28 | 1
2015-07-31 | [6 empty] | Whitelaw Wedge |  | 2012-04-26 | 2012-06-18 | JAAT | W912HN-10-D-0063 | 15315 | 16526 | 2012-07-18 | 2015-09-30 | 30-Ja n-14 | 2014-10-23 | 1
2015-07-31 | 2012 | National Security Agency | Major Military Construction | COLORADO | UNITED STATES | 23051 | Mountainview |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975 | 130369 | 2012-11-02 | 2015-08-30 | 2015-05-03 | 2015-07-28 | 0.97
2015-07-31 | [6 empty] | Mountainview |  | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621 | 5627 | 2013-10-13 | 2014-04-30 | 2014-02-14 | 2015-09-30 | 1
2015-07-31 | 2012 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 24649 | High Performance Computing Center 2 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589 | 593687 | 2013-03-13 | 2015-10-20 | 2015-09-15 | 2015-10-20 | 0.91
2015-07-31 | 2013 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 26170 | East Campus Building 1 (ECB1) |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91866 | 98414 | 2013-10-24 | 2016-06-13 | 2015-10-11 | 2016-03-19 | 0.38 |  |  | Data as of April 29 $34.563M Cum Actual Total
2015-07-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | 61772 | Operations Complex |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30155148 | 16751 | 17554.9517 | 2012-01-31 | 2015-01-21 | 2013-04-25 | 2014-12-31 | 1
2015-07-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033003 | Vehicle Maintenance Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30136034 | 4575 | 5123.2845 | 2012-01-31 | 2015-03-05 | 2013-04-25 | 2015-03-05 | 1
2015-07-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033005 | Storage Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154837 | 3603 | 3766.2116 | 2012-01-31 | 2015-01-21 | 2013-04-25 | 2014-12-31 | 1
2015-07-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033019 | Air Operations Center |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154494 | 2931 | 3078.5666 | 2012-01-31 | 2015-01-21 | 2013-04-25 | 2014-12-31 | 1
2015-07-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64484 | Operations Additions |  | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | W912HN-11-C-0010 / 29379991 | 13388 | 15601 | 2011-08-25 |  | 2014-06-10 | 2015-10-21 | 0.99
2015-07-31 | 2011 | Special Operations Command | Major Military Construction | GEORGIA | UNITED STATES | 65395 | Company Support Facility |  | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391.578 | 15637.173 | 2011-12-27 | 2014-05-30 | 2013-06-19 | 2014-07-31 | 0.99
2015-07-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 66362 | C4 Facility - JSOC |  | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | W912HN-12-C-0009 / 29381338 | 41446 | 44329 | 2012-06-14 | 2015-01-05 | 2014-01-31 | 2015-06-16 | 1
2015-07-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69573 | Admin/Company Operations |  | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN-10-D-0058 / 29381912 | 8487 | 9166 | 2011-10-27 | 2013-11-21 | 2013-04-18 | 2013-11-21 | 0.99
2015-07-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063049 | Hangar / AMU (MC-130J) |  | 2011-05-13 | 2011-09-09 | Speegle Construction | W912PP-11-C-0029 / 30594756 | 19432 | 20310.9637 | 2011-10-11 | 2014-05-02 | 2013-12-01 | 2014-05-02 | 0.99
2015-07-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13613.73 | 13829.0421 | 2012-09-06 | 2014-06-03 | 2013-07-17 | 2014-06-03 | 0.99 | 7132 | 66362
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60272 | Communications Training Complex (SWCS) |  | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN-10-D-0049 / 29371639 | 8290.317 | 8466 | 2012-09-12 |  | 2014-03-06 | 2015-05-29 | 0.96
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60821 | Squadron Headquarters Addition |  | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN-10-D-0060 / 29389201 | 10605 | 10926 | 2012-06-06 | 2015-03-16 | 2014-06-06 | 2015-07-04 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66598 | Rotary Wing Hangar |  | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350 | 35269 | 2012-04-16 | 2015-05-05 | 2014-02-15 | 2015-04-29 | 0.99
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69458 | Battalion Operations Complex |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772.305 | 16795 | 2012-12-10 |  | 2014-06-03 | 2015-08-13 | 0.93 | 1738 | 69445
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69758 | Brigade Headquarters |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 15649.974 | 16178 |  |  | 2014-05-08 | 2015-12-28 | 0.68
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525.847 | 18786 | 2012-11-07 | 2015-04-27 | 2014-05-01 | 2015-04-27 | 1 | 2896 | 69445
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41071297 | 4506.8515 | 4506.8515 | 2012-11-07 | 2015-04-27 | 2015-03-01 | 2015-04-27 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 76363 | Company Operations Facility |  | 2012-04-18 | 2012-08-30 | Adept-Absher 1 Joint Venture | W912DW-12-C-0037 / 27917342 | 18751 | 19630 | 2014-06-20 | 2014-06-20 | 2014-04-01 | 2014-06-21 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76364 | Battalion Operations Facility |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201.3031 | 33435.0071 | 2012-12-04 |  | 2014-08-26 | 2015-12-15 | 0.93 | 5000 | 69445
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76366 | Company Operations Facility (GSTB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673.727 | 15674.302 | 2012-09-12 |  | 2015-09-12 | 2016-04-26 | 0.93
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76371 | Company Operations Facility (GSB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092.801 | 17144 | 2012-09-12 |  | 2015-09-12 | 2016-04-26 | 0.93
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 76374 | MH-47 Hangar |  | 2011-11-28 | 2012-05-07 | Hensel Phelps Construction Co. | W912QR-12-C-0035 / 28427841 | 32450 | 34200 | 2014-08-27 | 2014-08-27 | 2014-03-23 | 2014-08-29 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073014 | SOF C-130 Sq Ops Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 25127091 | 7413 | 7874.8241 | 2014-07-11 | 2014-07-11 | 2014-02-22 | 2014-07-11 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073018 | SOF C-130 Wash Rack Hangar |  | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | W912PP-12-C-0025 / 30667913 | 9329 | 9703.7394 | 2014-09-09 | 2014-09-09 | 2014-04-10 | 2014-08-29 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073021 | SOF AMXS Facility |  | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | W912PP-12-C-0033 / 25138433 | 14700 | 14966.2684 | 2013-01-10 | 2014-09-22 | 2014-12-22 | 2014-09-19 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083012A | SOF Hangar/AMU |  | 2012-04-20 | 2012-08-31 | Hensel Phelps | W912PP-12-C-0027 / 30858121 | 28160 | 29105.547 | 2012-10-24 | 2014-10-02 | 2014-12-23 | 2014-09-07 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083016 | SOF Squadron Operations Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 28791332 | 10615 | 11040 | 2012-11-09 | 2014-05-30 | 2015-01-06 | 2014-05-30 | 1 | 2293 | CZQZ063035
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV103011 | SOF Simulator Facility |  | 2012-05-01 | 2012-08-09 | Barlovento LLC. | W91278-10-D-0072 | 5551 | 5543 | 2012-09-13 | 2014-07-18 | 2013-12-24 | 2014-07-18 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1049 | Range 130 Support Projects |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129 | 8767 | 2013-06-03 |  | 2014-11-13 | 2015-11-13 | 0.42
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1174 | MWD Facility |  | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | N6247311D0068 #0003 | 3075 | 3304 | 2012-10-03 | 2014-11-14 | 2014-03-23 | 2014-11-14 | 0.99
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-164 | Logistics Support Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727 | 18855 | 2012-12-09 |  | 2014-07-24 | 2015-06-16 | 0.96
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-473 | SEAL Team Operations Facility |  | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366 | 27585 | 2014-08-13 |  | 2015-12-27 | 2015-12-27 | 0.54
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | ALASKA | UNITED STATES | P-531 | Cold Weather Maritime Training Facility |  | 2012-04-30 | 2012-09-27 | Alutiiq Diversified Service, LLC | N4425512C3011 | 17449 | 17449 | 2014-03-04 | 2015-05-06 | 2015-04-15 | 2015-04-15 | 1
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-769 | Building Renovation |  | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022 | 4067 | 2013-01-02 | 2015-02-20 | 2014-06-27 | 2015-02-20 | 0.99
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-826 | Military Working Dog Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139 | 18855 | 2012-12-09 |  | 2014-07-24 | 2015-06-16 | 0.96
2015-07-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH043055 | SOF Training Facility |  | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN-10-D-0063 / 25189640 | 4773.799 | 4752.7374 | 2012-05-31 | 2014-10-29 | 2013-11-22 | 2014-11-12 | 1
2015-07-31 | 2012 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-504 | SOF Operational Vehicle Storage Facility (6UMC) |  | 2013-03-12 | 2013-05-23 | Richard Brady & Associates, Inc. | N4008511D6591 #0010 | 1660 | 1730 | 2013-12-03 | 2015-04-18 | 2014-10-20 | 2015-01-15 | 1
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | ARIZONA | UNITED STATES | 53542 | Parachute Training Facility |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546.92 | 6546.92 | 2014-11-09 |  | 2016-05-09 | 2016-05-07 | 0.24
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 65052 | Medical Support Addition |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199.999 | 3272 | 2013-10-16 | 2015-01-23 | 2015-08-25 | 2015-04-17 | 0.99
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66597 | Landgraf Hangar Extension |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384.894 | 3384.894 | 2014-04-29 |  | 2015-10-21 | 2015-11-20 | 0.41
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 69257 | SOF Military Working Dog Kennel |  | 2014-03-11 | 2015-04-01 | Pease Construction, Inc. | W912DW-15-C-0003 | 4484.16 | 4484.16 |  |  |  | 2016-11-14 | 0.3
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69382 | Civil Affairs Battalion Complex |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816 | 25843 | 2013-10-16 |  | 2015-08-14 | 2015-08-14 | 0.86
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 69445 | SOF Battalion Operations Facility |  | 2013-02-01 | 2015-05-07 | RQ Construction LLC | W912DW-15-C-0006 | 45104 | 45104 |  |  |  | 2017-07-23 | 0
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 69447 | Group Support Battalion Detachment |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123.1802 | 22638 | 2014-04-14 |  | 2016-02-13 | 2016-05-15 | 0.66
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69493 | Sustainment Bde Headquarters |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085 | 23223 | 2014-06-18 |  | 2016-05-02 | 2016-09-25 | 0.37
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 76367 | SOF Battalion Operations Complex |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441 | 36737 | 2014-09-04 |  | 2016-06-16 | 2016-10-01 | 0.14
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287a | Battalion Operations Complex |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907.435 | 31092 | 2013-10-09 |  | 2015-05-13 | 2015-12-24 | 0.79
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287b | Battalion Operations Complex |  |  | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404 | 23709 | 2014-11-20 |  |  | 2016-11-01 | 0.14
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083013 | Combat Parking Apron |  | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP-14-C-0014 / 32077093 | 19481.9877 | 19871 | 2014-06-13 |  | 2015-08-13 | 2015-11-22 | 0.97
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTFA113004 | SOF AvFID Ops and MX Facilities |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942.3 | 30121 | 2013-11-05 |  | 2016-12-01 | 2017-05-14 | 0.7
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | NVZR083702 | Joint Special Operations University Facility |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753.0246 | 25259 | 2013-11-04 |  | 2015-09-15 | 2016-01-07 | 0.5
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1218 | Marine Battalion Company/Team Facilities |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46506 | 2014-02-20 |  | 2016-03-01 | 2016-01-23 | 0.54
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1393 | Survival Evasion Resistance Escape Trng Fac |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46506 | 2014-02-20 |  | 2016-01-18 | 2016-01-23 | 0.54
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-165 | CS/CSS Support Facility |  | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351 | 10272 | 2014-10-06 |  | 2015-09-09 | 2015-11-26 | 0.79
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-876 | Indoor Dynamic Shooting Facility |  |  | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290 | 24440 |  |  | 2016-10-01 | 2016-10-07 | 0.07
2015-07-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-888 | Close Quarters Combat Range, Phase II |  |  | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489 | 15440 |  |  | 2016-09-30 | 2016-09-29 | 0.07
2015-07-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 79655 | SOF Training Facility (4UMC) |  | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | W912PM-13-C-0003 | 1592 | 1608 | 2013-06-18 | 2014-10-01 | 2014-10-15 | 2014-08-21 | 1
2015-07-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 80233 | SOF Live-Fire Training Tower (6UMC) |  | 2013-06-16 | 2014-01-22 | Trend Construction, Inc. | W912HN-12-D-0030-DQ04 | 1531.7653 | 1570 | 2014-02-12 | 2015-03-04 | 2015-05-15 | 2015-03-04 | 1
2015-07-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81483 | Mtn Climb/Rappel Tower (5UMC) |  | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F-13-C-0006 | 1513 | 1643 | 2013-09-20 | 2014-11-26 | 2014-10-15 | 2015-01-25 | 0.98
2015-07-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NEW MEXICO | UNITED STATES | CZQZ100221 | Parachute Drying Tower (3 UMC) |  | 2014-03-06 | 2014-07-01 | Speegle Construction | W912PP-14-C-0017 / 39136021 | 1547 | 1572 | 2014-07-28 |  | 2015-05-24 | 2015-08-21 | 0.98
2015-07-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1410 | SOF EOD Expansion (1UMC) |  | 2013-09-04 | 2013-09-26 | Quadrant Construction, Inc | N4008510D0261 #0017 | 1566 | 1612 | 2013-10-15 |  | 2014-09-22 | 2015-06-30 | 0.98
2015-07-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1450 | Fires Platoon Storage Facility (7UMC) |  | 2013-12-20 | 2014-02-13 | Quadrant Construction, Inc | N4008510D0261 #0019 | 1459.25 | 1516 | 2014-03-13 |  | 2014-12-13 | 2015-07-17 | 0.97
2015-07-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-564 | NSWG-4 Paraloft Addition (2UMC) |  | 2013-06-14 | 2013-09-27 | Royce Homeland JV, LLC | N4008512D6305 #0005 | 1308 | 1383 | 2013-10-15 | 2015-02-12 | 2014-12-31 | 2015-02-12 | 1
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 61064 | SOF Upgrade Training Facility |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951 | 13951 | 2014-11-17 |  | 2016-05-10 | 2016-10-13 | 0.08
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 68526 | SOF Engineer Training Facility |  | 2014-03-26 | 2015-04-09 | Barlovento, LLC | W91278-10-D-0058-DQ01 | 10815.034 | 10815.034 | 2015-05-27 |  | 2017-04-07 | 2017-04-07 | 0
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 69446 | Group Support Battalion Detachment |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083.965 | 15214 | 2014-08-27 |  | 2016-02-18 | 2016-04-20 | 0.24
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76375 | Civil Affairs Battalion Annexes |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358 | 27391 | 2014-12-01 |  | 2016-07-23 | 2017-01-19 | 0.09
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76376 | Language and Cultural Center |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696.6683 | 51696.6683 | 2015-01-09 |  | 2017-06-27 | 2018-01-15 | 0.06
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 79438 | Combat Medic Skills Sustainment Course Bldg |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193.631 | 7230 | 2014-10-27 |  | 2016-04-19 | 2016-09-16 | 0.13
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 79440 | SOF Boat Docks |  |  | 2015-04-30 | Blueforge, LLC | N69450-14-D-1271 | 3695.8 | 3695.8 | 2015-04-30 |  | 2016-08-22 | 2016-08-22 | 0
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV083002 | Add/Alter Operations Facility |  | 2014-05-26 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048.867 | 7231 | 2014-09-02 |  | 2016-05-24 | 2016-10-20 | 0.14
2015-07-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1391 | SOF Sustainment Training Complex |  | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333 #0004 | 27546.924 | 27546.924 | 2014-09-13 |  | 2016-09-02 | 2016-09-02 | 0.21
2015-07-31 | 2014 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1469 | MSOB Support Facilities |  | 2014-08-20 | 2014-09-30 | Quadrant Construction, Inc | N4008510D0261/0022 | 2426 | 2430 | 2014-09-30 |  | 2015-09-25 | 2015-11-24 | 0.39
2015-07-31 | 2014 | Special Operations Command | Major Military Construction |  | JAPAN | 78024 | SOF Facility Augmentation |  | 2014-12-05 | 2015-06-09 | Nishimatsu Construction Co., Ltd. | W912HV-15-C-0004 | 46556 | 46556 | 2015-07-01 |  | 2018-05-05 | 2018-05-05 | 0
2015-07-31 | 2010 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80001 | Pentagon Electrical Upgrade |  | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power | HQ0034-13-C-0133 | 23269 | 23912 | 2013-11-07 | 2016-03-30 | 2015-02-05 | 2016-08-01 | 0.24 | 0
2015-07-31 | 2011 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES | 80002 | Power Plant Modernization Phase 3 (WPP) |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. | HQ0034-13-C-0062 | 43594 | 45578 | 2013-04-22 | 2016-06-30 | 2016-05-11 | 2016-09-30 | 0.32 | 4001 | Budget Sequester
2015-07-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80003 | Metro Entrance Facility/Visitor Screening Facility |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. | W912DR-11-R-0060 | 5609 | 6267 | 2013-11-01 | 2015-10-21 | 2015-06-01 | 2015-10-21 | 0.48 | 0
2015-07-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80004 | Secure Access Lane (SAL) |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC | W912DR-11-R-0062 | 5454 | 5856 | 2013-11-01 | 2016-05-30 | 2015-05-01 | 2016-06-30 | 0.16 | 0
2015-07-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80005 | Pentagon Heliport Control Tower/Fire Station | [12 empty] | 798 | Budget Sequester
2015-07-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80006 | Pentagon Memorial Pedestrian Plaza | [12 empty] | 176 | Budget Sequester
2015-07-31 | 2014 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80007 | PFPA Support Operations Center
2015-07-31 | 2014 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80008 | Boundary Channel Access Control Point
2015-07-31 | 2014 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES | 80009 | Raven Rock Admin Facility Upgrade
2015-07-31 | 2014 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES | 80010 | Raven Rock Exterior Cooling Towers
2015-07-31 | 2015 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES | 80011 | Redundant Chilled Water Loop

## DETAILED EXPENDITURES
Data as of Date | Fiscal Year | Component | Appropriation Fund Type | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Current Expenditure Amount ($000) | Remarks
2015-08-06 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 18281.46 | 1693.1664 | 8.9387
2015-08-06 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229 | 1729.9637 | 20.2313
2015-08-06 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 1530 | 0 | 0
2015-08-06 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400 | 7662.744 | 2289.4381
2015-08-06 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 13000 | 5601.4294 | 1157.3501
2015-08-06 | 2015 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 352.062 | 0.059493 | 0.001182
2015-08-06 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations. | 16738 | 5912.3801 | 1672.5569
2015-08-06 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 22613 | 0 | 0
2015-08-06 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892 | 636.1591 | 6.6828
2015-08-06 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 1400 | 0 | 0
2015-08-06 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700 | 123.6123 | 0
2015-08-06 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 6100 | 43.1837 | 0
2015-07-31 | 2009 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000 | 24000
2015-07-31 | 2010 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000 | 25000
2015-07-31 | 2011 | Army Active | Host Nation Support [HNS] | $29,944 Appropriated + $13,000 ATR Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 42944 | 42933 | 42905
2015-07-31 | 2012 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR + $9,000 ATR | 36000 | 35942 | 35254
2015-07-31 | 2013 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954 | 33863 | 33506
2015-07-31 | 2014 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000 | 22923 | 22126
2015-07-31 | 2015 | Army Active | Host Nation Support [HNS] | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33000 | 14972 | 13541
2015-07-31 | 2009 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 21855 | 21855 | 21855
2015-07-31 | 2010 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 28393 | 28392 | 28387
2015-07-31 | 2011 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 37328 | 37317 | 37311
2015-07-31 | 2012 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 34282 | 34262 | 34262
2015-07-31 | 2013 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 28086 | 27897 | 27858
2015-07-31 | 2014 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 20228 | 19788 | 18859
2015-07-31 | 2015 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 7000 | 6963 | 4251
2015-07-31 | 2010 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 60100 | 15687 | 15686
2015-07-31 | 2011 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 78330 | 1274 | 1274
2015-07-31 | 2009 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 220241 | 219362
2015-07-31 | 2010 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250432 | 248032
2015-07-31 | 2011 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 308676 | 263043 | 258216
2015-07-31 | 2012 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 213926 | 195110
2015-07-31 | 2013 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46112 | 45761 | 43532
2015-07-31 | 2014 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575 | 39112 | 35711
2015-07-31 | 2015 | Army Active | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 18127 | 12923 | 11663
2015-07-31 | 2009 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 576 | 575 | 548
2015-07-31 | 2010 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 3936 | 3921 | 2503
2015-07-31 | 2011 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 2036 | 2002 | 1367
2015-07-31 | 2012 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 7897 | 7718 | 7286
2015-07-31 | 2013 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 4635 | 4322 | 1379
2015-07-31 | 2014 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 4408 | 719 | 379
2015-07-31 | 2015 | Army Active | Planning and Design - Military Family Housing [MFH P&D] | Army Family Housing Construction for Projects | 1309 | 0 | 0
2015-07-31 | 2009 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28750 | 28394 | 26129
2015-07-31 | 2010 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 31250 | 31246 | 30370
2015-07-31 | 2011 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28704 | 28676 | 28658
2015-07-31 | 2012 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 20000 | 19685 | 19394
2015-07-31 | 2013 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 23696 | 20135
2015-07-31 | 2014 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 22343 | 11652
2015-07-31 | 2015 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 2861 | 114
2015-07-31 | 2011 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25604 | 25592 | 25592 | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2011 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14215 | 13232 | 13232 | PL 112-10 SEC 1119 (a) 0.2% Rescission & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191 | 19738 | 19738 | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2012 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14149 | 11562 | 11562 | PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17; Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 28155 | 7049 | 7049 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013); PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2013 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14562 | 14562 | 14562 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2015-07-31 | 2014 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930 | 2727 | 2727 | PL 113-76 P&D Rescission
2015-07-31 | 2014 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 12240 | 2133 | 2133
2015-07-31 | 2015 | Army National Guard | Planning and Design - Military Construction [MILCON P&D] | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 17600 | 6652 | 6652
2015-07-31 | 2015 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $3M | 13720 | 1873 | 1873
2015-06-30 | 2012 | Defense Finance and Accounting Service | Planning and Design - Military Construction [MILCON P&D] | Investigation and Design | 1992 | 748 | 709
2015-06-30 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction [UMMC] | Construction | 15404 | 14350 | 5875
2015-07-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 3979 | 3979 | 3979
2015-07-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 5547 | 3984 | 3984
2015-07-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4673 | 2735 | 2710
2015-07-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 5930 | 4757 | 4716
2015-07-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4608 | 3055 | 2377
2015-07-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 9578 | 525 | 165
2015-07-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4100 | 0 | 0
2015-07-31 | 2009 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 171255 | 170635 | 166145
2015-07-31 | 2010 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 72679 | 72543 | 69095
2015-07-31 | 2011 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 193126 | 144984 | 112771
2015-07-31 | 2012 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 209957 | 4853 | 4689
2015-07-31 | 2013 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 97411 | 0 | 0
2015-07-31 | 2014 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 244 | 0 | 0
2015-07-31 | 2015 | Defense Health Agency | Planning and Design - Military Construction [MILCON P&D] | P&D Funding of MILCON Projects | 105 | 0 | 0
2015-07-31 | 2010 | Defense Intelligence Agency | Planning and Design - Military Construction [MILCON P&D] | P&D for K-16 FOB-K renovation of two buildings to include Administrative and SCIF Spaces | 442 | $ - | 442 | Planning and Design MIPR sent to U.S. Army Engineer District, Far East for K-16 Design. MIPR has been fully executed.
2015-07-31 | 2012 | Defense Intelligence Agency | Planning and Design - Military Construction [MILCON P&D] | P&D for DIAC Parking Garage Replacement; P&D for DIAC Chilled Water Project for Data Center ($125K) and P&D for DIAC Cooling Tower for Data Center ($105K); P&D for UPS for Data Center Installation; P&D for Construction of JUIAF RDF | 3260 | 93 | 2520 | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $416K (CORRECTED AMOUNT) obligated as CAT I. Contract awarded on 23 September 2014.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 100% design completed.; Design complete.
2015-07-31 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 79739 | 62283 | 19486 | DISA Europe Facility Upgrades ($2,224); Construct New DISA Facility Scott AFB ($77,515)
2015-07-31 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2616 |  |  | DISA Pacific Facility Upgrade
2015-07-31 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction |  | 12216 |  |  | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) ($9,600); JITC Building 52120 Renovation ($1,871); P&D for design of JITC Buildings 52101, 52110, 52111 ($745K)
2015-07-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] | For design of projects from 2012 to 2016 | 36093 | 36093 | 36093
2015-07-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2011 to 2014 | 4864 | 4864 | 4864
2015-07-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] | For design of project from 2012 to 2016 | 34331 | 34238 | 34238
2015-07-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2012 to 2014 | 6312 | 6312 | 6312
2015-07-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] | For design of project from 2014 to 2017 | 30636 | 27227 | 27227
2015-07-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2012 to 2015 | 6686 | 1951 | 1951
2015-07-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] | For design of project from 2015 to 2018 | 6978 | 2266 | 2266
2015-07-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2013 to 2016 | 7430 | 0 | 0
2015-07-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction [MILCON P&D] |  | 0 | 0 | 0
2015-07-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2015 to 2019 | 5932 | 0 | 0
2014-08-04 | 2008 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design Efforts FY09 RCI and FY 08/09/ 10/11/12 MILCON projects | 5161 | 5161 | 5158 | RCI-Residential Communities Initiative
2014-08-04 | 2009 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13623 | 13623 | 12554
2014-08-04 | 2010 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 10/11/ 12/13 MILCON projects | 8829 | 8764 | 8722 | Reflects Sequestration Reduction
2014-08-04 | 2011 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 11/12/ 13 MILCON projects | 78666 | 78599 | 65167 | Reflects Sequestration Reduction
2014-08-04 | 2012 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 12/13 MILCON projects | 64551 | 64128 | 47901 | Reflects Sequestration Reduction
2014-08-04 | 2013 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 95666 | 48453 | Reflects Sequestration Reduction
2014-08-04 | 2014 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 14/15/16/17 MILCON projects | 75905 | 12115 | 13
2014-08-04 | 2015 | DoD Education Activity | Planning and Design - Military Construction [MILCON P&D] | Design efforts for FY 15/16/17/18 MILCON projects | 42387 | 0
2014-08-04 | 2009 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5 | 4 | 4 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2014-08-04 | 2013 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 3771 | 7 | 3764 | Reflects Sequestration Reduction
2014-08-04 | 2014 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5409 | 0
2014-08-04 | 2015 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 6846 | 0
2015-07-31 | 2011 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY15-16 MILCON Projects | 1186 | 1186 | 1186 | Funds transferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2015-07-31 | 2012 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY13-14 MILCON Projects | 8368 | 8368 | 8124 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2015-07-31 | 2013 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY13-14 MILCON Projects | 4191 | 4191 | 4062 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2015-07-31 | 2014 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY14-16 MILCON Projects | 10891 | 10891 | 9820 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2015-07-31 | 2015 | Missile Defense Agency | Planning and Design - Military Construction [MILCON P&D] | Design MDA FY16-17 MILCON Projects | 58704 | 17871 | 2368 | Supports design of the Aegis Ashore Poland site, Long Range Discrimination Radar System Complex, Clear AFS, AK, and IDT Switchgear Bldg, Fort Greely, AK.
2015-07-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY13/14 | 2243 | 2038 | 1793 | Supports the R&C Piping project at Fort Greely, AK and the Storage Facility, Meck Island. $1.186M transferred to DHA in April 2014 for swap of FY11 P&D funds. $205K returned to OSD in Sep 2014.
2015-07-31 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000 | 155 | 21 | Supports the Storage Facility, Meck Island project.
2015-07-31 | 2015 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY15/16 | 2000 | $ - | $ -
2015-07-31 | 2011 | Marine Corps Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 853 | 853 | 850
2015-07-31 | 2012 | Marine Corps Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719 | 719 | 719
2015-07-31 | 2013 | Marine Corps Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455 | 446 | 434
2015-07-31 | 2014 | Marine Corps Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463 | 462 | 292
2015-07-31 | 2015 | Marine Corps Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 472 | 75 | 0
2015-07-31 | 2011 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 11087 | 10789 | 10771
2015-07-31 | 2012 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 25327 | 23639 | 23634
2015-07-31 | 2013 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 17441 | 16715 | 2954
2015-07-31 | 2014 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 24253 | 15632 | 0
2015-07-31 | 2015 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 15940 | 0 | 0
2015-07-31 | 2011 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 2340 | 2340 | 2229
2015-07-31 | 2012 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2447 | 2438 | 2398
2015-07-31 | 2013 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609 | 1405 | 852
2015-07-31 | 2014 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975 | 0 | 0
2015-07-31 | 2015 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0
2015-07-31 | 2011 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 27773 | 27603 | 25364
2015-07-31 | 2012 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 68661 | 59244 | 47623
2015-07-31 | 2013 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 42739 | 34298 | 22141
2015-07-31 | 2014 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 44716 | 41249 | 3264
2015-07-31 | 2015 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
2015-07-31 | 2011 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 136314 | 135878 | 131144 | [Component: Navy-MC Active]
2015-07-31 | 2012 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 83943 | 83725 | 81183 | [Component: Navy-MC Active]
2015-07-31 | 2013 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 96888 | 96508 | 78242 | [Component: Navy-MC Active]
2015-07-31 | 2014 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638 | 72552 | 47065 | [Component: Navy-MC Active]
2015-07-31 | 2015 | Navy Active | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 33366 | 23928 | 22133 | [Component: Navy-MC Active]
2015-07-31 | 2011 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20757 | 20070 | 18981 | [Component: Navy-MC Active]
2015-07-31 | 2012 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20919 | 19802 | 18499 | [Component: Navy-MC Active]
2015-07-31 | 2013 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 15612 | 13385 | 9532 | [Component: Navy-MC Active]
2015-07-31 | 2014 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 19740 | 16766 | 9532 | [Component: Navy-MC Active]
2015-07-31 | 2015 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 3582 | 0 | 0 | [Component: Navy-MC Active]
2015-07-31 | 2011 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1854 | 1854 | 1854 | [Component: Navy-MC Reserve]
2015-07-31 | 2012 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478 | 2324 | 2232 | [Component: Navy-MC Reserve]
2015-07-31 | 2013 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995 | 1994 | 2232 | [Component: Navy-MC Reserve]
2015-07-31 | 2014 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2556 | 2078 | 2078 | [Component: Navy-MC Reserve]
2015-07-31 | 2015 | Navy Reserve | Planning and Design - Military Construction [MILCON P&D] | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 2123 | 0 | 0 | [Component: Navy-MC Reserve]
2015-07-31 | 2011 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 2194 | 1632 | 1548 | [Component: Navy-MC Reserve]
2015-07-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 1947 | 1237 | 1171 | [Component: Navy-MC Reserve]
2015-07-31 | 2013 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2015-07-31 | 2014 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2015-07-31 | 2015 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 4000 | 0 | 0 | [Component: Navy-MC Reserve]
2015-02-28 | 2010 | National Security Agency | Planning and Design - Military Construction [MILCON P&D] | Generators 10 & 11 | 440 | 440 |  | MIPR 12-045 from MHS to AFCEC, $240K moved from Power & Cooling
2015-05-15 | 2011 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 26469 | 25250 |  | As of 15May2015; Includes funds given to UK DIO
2015-07-16 | 2012 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 30308 | 28300 |  | As of 16July2015; Includes funds given to UK DIO
2015-07-16 | 2013 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 25454 | 15994 |  | As of 16July2015; Includes funds given to UK DIO
2015-07-16 | 2014 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 36866 | 20977 |  | As of 16July2015
2015-07-16 | 2015 | Special Operations Command | Planning and Design - Military Construction [MILCON P&D] | MILCON Design Work | 24197 | 0 |  | As of 16July2015
2015-07-16 | 2011 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 7531 | 7526 |  | As of 16July2015
2015-07-16 | 2012 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 8487 | 8068 |  | As of 16July2015
2015-07-16 | 2013 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 9216 | 8920 |  | As of 16July2015
2015-07-16 | 2014 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 5170 | 2833 |  | As of 16July2015
2015-07-16 | 2015 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 10334 | 0 |  | As of 16July2015
2015-07-16 | 2011 | Washington Headquarters Services | Planning and Design - Military Construction [MILCON P&D] | Planning and Design | 2285 | 2027 | 1157 | Sequester taken. Includes ECIP. Revised to deduct the $3,782K realigned and obligated on Pentagon Electrical Upgrade construction since it is no longer P&D
2015-07-16 | 2012 | Washington Headquarters Services | Planning and Design - Military Construction [MILCON P&D] | Planning and Design | 4870 | 3607 | 1950 | Sequester taken.
2015-07-16 | 2013 | Washington Headquarters Services | Planning and Design - Military Construction [MILCON P&D] | Planning and Design | 7508 | 1943 | 200 | Sequester and rescissions taken. Includes ECIP
2015-07-16 | 2014 | Washington Headquarters Services | Planning and Design - Military Construction [MILCON P&D] | Planning and Design | 6931 | 0 | 0
2015-07-16 | 2015 | Washington Headquarters Services | Planning and Design - Military Construction [MILCON P&D] | Planning and Design | 1183 | 0 | 0