## PROJECTS
Project Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Construction Project Type Name | State Name | Country Name | Project Number | Project Title | Sub-Project Number | Diverted Funds Total Amount | Diverted Funds Recipient Text | Construction Start Date | Original Construction Completion Date | Current Construction Completion Date | Construction Percent Complete | Current RPA Placed-In-Service Date
2018-07-11 | 2009 | Air Force Active | Major Military Construction |  | Afghanistan | ACC093972 | RUNWAY (FOB DWYER, GARMSIR, AFGHAN) |  |  |  | 2009-09-02 | 2010-12-22 | 2010-12-22 | 99% | 2010-09-15
2018-07-11 | 2018 | Air Force Active | Major Military Construction | Colorado | United States | ACC123301 | 13 ASOS Expansion |  |  |  | 2018-07-20 | 2020-01-15 | 2020-01-15 | 1% | 2020-01-15
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | Germany | AFAF140005 | Construct Airfield and Base Camp |  |  |  | 2016-03-31 | 2017-12-29 | 2018-09-28 | 63% | 2018-09-28
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143005A | KC-46A FTU ADAL FUEL CELL MAINTENANCE HANGAR |  |  |  | 2016-05-30 | 2017-05-26 | 2018-07-31 | 42% | 2018-07-31
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN173001 | KC-46A FTU FTC SIMULATOR FACILITY PHASE 2 |  |  |  | 2017-09-07 | 2019-03-01 | 2018-09-29 | 2% | 2019-03-01
2018-07-11 | 2013 | Air Force Active | Major Military Construction |  | Guam | AJJY123010 | Guam Strike Fuel Systems Maintenance Hangar |  |  |  | 2015-02-20 | 2017-04-16 | 2020-12-21 | 30% | 2020-12-21
2018-07-11 | 2014 | Air Force Active | Major Military Construction |  | Guam | AJJY133027 | Guam Strike Tanker Gp Maint Hangar/Amu/Sqd Ops (Incr 1) |  |  |  | 2015-01-22 | 2017-03-08 | 2018-09-03 | 28% | 2019-05-23
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Guam | AJJY133028 | PAR Low Observable/Corrosion Control/Composite Repair Shop |  |  |  | 2016-10-30 | 2018-09-20 | 2019-07-04 | 15% | 2019-07-04
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | Guam | AJJY143030 | APR SOUTH RAMP UTILITIES PHASE 2 |  |  |  | 2016-09-02 | 2018-03-26 | 2018-07-20 | 96% | 2018-07-20
2018-07-11 | 2014 | Air Force Active | Major Military Construction |  | Guam | AJJY143760 | Hardened Structures For POL Fuel Systems |  |  |  | 2014-10-07 | 2016-06-28 | 2019-12-11 | 16% | 2019-12-11
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | Guam | AJJY150600 | APR INSTALLATION CONTROL CENTER |  |  |  | 2018-04-01 | 2018-08-20 | 2019-11-07 | 4% | 2019-11-07
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | Guam | AJJY163004 | APR - Dispersed Maintenance Spares and SE Storage Facility |  |  |  | 2017-08-31 | 2019-10-21 | 2019-05-13 | 16% | 2019-03-13
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Maryland | United States | AJXF093000 | CONSTRUCT 21 POINT ENCLOSED FIRING RANGE |  |  |  | 2018-10-17 | 2020-02-25 | 2020-02-25 | 1% | 2019-10-22
2018-07-11 | 2014 | Air Force Active | Major Military Construction | Maryland | United States | AJXF103010 | Construct Helicopter Operations Facility |  |  |  | 2016-05-02 | 2017-03-09 | 2018-09-03 | 95% | 2018-09-03
2018-03-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA110032 | Fuel Truck Parking |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2018-03-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113002 | Fuels Laboratory |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2018-03-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113005 | C-17 Spare Parts Facility |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2018-03-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113006 | High Mast Lighting |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2018-03-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113009 | Entry Control Point |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2018-03-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113010 | Cryogenics Facility |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2018-03-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113012 | ELRS Storage Facility |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 42% | 2018-10-26
2018-03-13 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113026 | C-130 Aircraft Maintenance Unit |  |  |  | 2013-10-18 | 2014-12-06 | 2018-08-14 | 23% | 2018-10-26
2018-06-11 | 2016 | Air Force Active | Major Military Construction |  | Oman | AMAB120001 | AIRLIFT APRON |  |  |  | 2016-07-22 | 2015-11-11 | 2018-05-13 | 100% | 2018-05-23
2018-07-11 | 2013 | Air Force Active | Major Military Construction |  | Italy | ASHE103001 | F-16 Mission Training Center |  |  |  | 2015-05-04 | 2016-12-02 | 2018-09-30 | 97% | 2018-03-27
2018-07-11 | 2015 | Air Force Active | Unspecified Minor Military Construction |  | Italy | ASHE143006 | MILITARY WORKING DOG (MWD) KENNEL COMPLEX |  |  |  | 2018-07-18 | 2017-09-29 | 2019-03-01 | 2% | 2019-03-01
2018-07-11 | 2017 | Air Force Active | Unspecified Minor Military Construction | Louisiana | United States | AWUB105003 | FIRE STATION NO. 2 |  |  |  | 2018-07-18 | 2019-09-13 | 2019-09-13 | 1% | 2019-09-13
2018-07-11 | 2014 | Air Force Active | Major Military Construction | California | United States | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 3000000 | CADJ140004; | 2014-08-27 | 2016-08-26 | 2018-09-19 | 96% | 2018-07-11
2018-07-11 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Afghanistan | BAGR113023 | HELICOPTER RAMP EXPANSION |  |  |  | 2011-11-16 | 2012-10-30 | 2012-10-30 | 2% | 2012-10-15
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170001 | Construct Chabelley Access Road |  |  |  | 2018-07-30 | 2018-12-28 | 2018-12-28 | 1% | 2018-12-28
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170002 | Construct Parking Apron and Taxiway |  |  |  | 2018-07-30 | 2018-12-28 | 2018-12-28 | 1% | 2018-12-28
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Colorado | United States | CRWU063008 | Small Arms Range Complex |  |  |  | 2018-01-08 | 2018-04-06 | 2019-07-02 | 5% | 2019-06-01
2018-05-11 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ073050 | DORMITORY (144 RM) |  |  |  | 2014-08-14 | 2015-07-15 | 2018-03-15 | 100% | 2016-05-17
2018-07-11 | 2016 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ113000 | CONSTRUCT AT/FP GATE - PORTALES |  |  |  | 2017-10-16 | 2017-08-17 | 2018-11-12 | 70% | 2019-02-11
2018-07-11 | 2017 | Air Force Active | Unspecified Minor Military Construction | New Mexico | United States | CZQZ160010 | Add/Alter HVAC, RPA Ops Center, Bldg 848 |  |  |  | 2017-11-06 | 2018-06-14 | 2018-06-22 | 100% | 2018-06-22
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Florida | United States | DBEH063000 | Range Communications Facility |  |  |  | 2016-08-29 | 2018-06-20 | 2018-08-16 | 66% | 2018-11-14
2018-07-11 | 2018 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | DBEH133000 | Final Denial Barrier, South Gate |  |  |  | 2018-05-16 | 2019-07-30 | 2019-07-30 | 2% | 2018-10-31
2018-07-11 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF080145 | INFORMATION TRANSFER NODE |  |  |  | 2012-10-03 | 2012-10-30 | 2016-02-01 | 57% | 2014-12-01
2018-07-11 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF105000 | DINING FACILITY |  |  |  | 2012-10-03 | 2012-09-01 | 2016-01-12 | 7% | 2014-12-01
2018-07-11 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF110018 | Expeditionary Mission Support Group Headquarters |  |  |  | 2012-10-03 | 2012-09-10 | 2016-03-15 | 15% | 2014-12-01
2018-07-11 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF110019 | Kennel |  |  |  | 2012-10-03 | 2012-09-10 | 2015-10-01 | 84% | 2014-12-01
2018-07-11 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF120029 | Battlespace Command and Control Center (BC3) Site |  |  |  | 2013-08-14 | 2013-05-01 | 2013-05-01 | 2% | 2013-04-02
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | DXEB053005 | FIRE STATION |  |  |  | 2018-05-04 | 2019-05-10 | 2020-04-11 | 2% | 2020-05-11
2018-07-11 | 2015 | Air Force Active | Major Military Construction | Alaska | United States | DXEB133001 | EMERGENCY POWER PLANT FUEL STORAGE |  |  |  | 2017-10-10 | 2014-11-10 | 2019-11-07 | 2% | 2020-01-21
2018-07-11 | 2015 | Air Force Active | Unspecified Minor Military Construction | North Dakota | United States | EGYN083001 | CONSOLIDATED DORMITORY |  |  |  | 2017-08-24 | 2016-08-03 | 2018-08-24 | 2% | 2019-02-21
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Poland | EPLK150006 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2017-11-27 | 2019-03-29 | 2020-03-26 | 2% | 2020-08-25
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Poland | EPPW170003 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2017-11-27 | 2019-03-29 | 2020-03-26 | 2% | 2020-08-25
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | United Kingdom | EXSW123006 | CONSOLIDATED SATCOM/TECH CONTROL FACILITY |  |  |  | 2019-01-07 | 2016-07-29 | 2020-05-30 | 2% | 2020-05-30
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Lithuania | EYSA150022 | ERI: MUNITIONS STORAGE |  |  |  | 2019-04-15 | 2021-10-15 | 2021-10-15 | 2% | 2022-03-15
2018-07-11 | 2011 | Air Force Active | Major Military Construction | Arizona | United States | FBNV113002 | HC-130J Aerial Cargo Facility |  | 2000000 | YWHG111005; | 2011-11-09 | 2012-09-21 | 2018-10-30 | 95% | 2013-09-13
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | FBNV113005 | HC-130J Wash Rack |  |  |  | 2016-11-15 | 2018-02-15 | 2018-08-24 | 50% | 2018-08-24
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | FBNV113008 | HC-130J AGE Covered Storage |  |  |  | 2017-06-10 | 2017-07-20 | 2018-07-10 | 70% | 2018-07-10
2018-07-11 | 2017 | Air Force Active | Major Military Construction | California | United States | FSPM053503C | FLIGHT LINE FIRE STATION |  |  |  | 2018-04-13 | 2021-02-24 | 2021-02-24 | 2% | 2021-03-01
2018-07-11 | 2016 | Air Force Active | Major Military Construction | California | United States | FSPM153500 | COMBINED TEST FORCE (CTF) COMPOUND |  |  |  | 2017-06-09 | 2019-06-09 | 2019-06-09 | 25% | 2019-06-09
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Florida | United States | FTEV123007 | ADD TO 39 IOS FACILITY |  |  |  | 2017-07-17 | 2018-11-19 | 2018-12-26 | 60% | 2019-02-17
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA033003 | Flightline Fire Station |  |  |  | 2018-01-29 | 2019-07-23 | 2019-07-23 | 2% | 2019-06-28
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Alaska | United States | FTQW163011 | F-35A Flight Sim /ADAL Sqd Ops/AMU |  |  |  | 2016-12-22 | 2018-09-28 | 2018-09-19 | 63% | 2018-09-19
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170100 | F-35A ADAL FIELD TRAINING DETACHMENT (FTD) FACILITY |  |  |  | 2017-06-20 | 2019-08-29 | 2019-04-27 | 12% | 2019-07-01
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170106 | F-35A HANGAR/PROPULSION MAINT/DISPATCH |  |  |  | 2017-06-20 | 2019-05-10 | 2019-07-09 | 2% | 2019-08-01
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170112 | F-35A AIRCRAFT WEATHER SHELTER SQD #1 |  |  |  | 2018-02-05 | 2019-05-10 | 2019-10-18 | 2% | 2019-12-30
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170113 | F-35A EARTH COVERED MAGAZINES |  |  |  | 2017-04-18 | 2018-11-01 | 2018-11-01 | 19% | 2018-11-01
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170114 | F-35A HANGAR/SQUAD OPS/AMU SQD #2 |  |  |  | 2018-03-01 | 2019-05-10 | 2019-11-01 | 2% | 2019-11-01
2018-07-11 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180102 | F-35A OSS/Weapons/Intel Facility |  |  |  | 2018-02-28 | 2020-06-01 | 2019-05-24 | 2% | 2019-07-01
2018-07-11 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180103 | F-35A AGE Facility / Fillstand |  |  |  | 2018-02-28 | 2020-06-01 | 2019-08-01 | 2% | 2019-09-27
2018-07-11 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180105 | F-35A R-11 Fuel Truck Shelter |  |  |  | 2018-03-30 | 2020-07-07 | 2020-01-20 | 2% | 2020-03-14
2018-07-11 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180107 | F-35A Consolidated Munitions Admin Facility |  |  |  | 2018-04-05 | 2020-02-14 | 2020-02-14 | 2% | 2020-05-14
2018-07-11 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180111 | F-35A Extend Utiliduct to South Loop |  |  |  | 2018-02-27 | 2019-06-10 | 2019-11-28 | 2% | 2019-11-28
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW183001 | F-35A Aircraft Weather Shelter SQD #2 |  |  |  | 2018-06-15 | 2020-05-06 | 2020-05-06 | 2% | 2020-06-26
2018-07-11 | 2016 | Air Force Active | Major Military Construction | South Dakota | United States | FXBM063002 | DORMITORY (168 RM) |  |  |  | 2017-01-12 | 2019-01-12 | 2019-02-02 | 41% | 2018-10-01
2018-07-11 | 2015 | Air Force Active | Unspecified Minor Military Construction | Alaska | United States | FXSB041069 | COMMERCIAL VEHICLE SEARCH POST ROAD GATE |  |  |  | 2017-01-31 | 2017-04-28 | 2018-06-29 | 97% | 2018-06-29
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN083004 | MISSILE TRANSFER FACILITY |  |  |  | 2017-06-15 | 2018-05-18 | 2018-12-07 | 5% | 2018-09-10
2018-07-11 | 2012 | Air Force Active | Major Military Construction |  | Italy | HACC123204 | UAS SATCOM Relay Pads and Facility |  |  |  | 2016-10-04 | 2017-02-21 | 2019-02-04 | 60% | 2019-02-04
2018-07-11 | 2015 | Air Force Active | Major Military Construction | New Jersey | United States | HEKP103001 | FIRE STATION |  |  |  | 2016-05-05 | 2017-10-30 | 2017-12-30 | 97% | 2018-02-20
2018-07-11 | 2016 | Air Force Active | Unspecified Minor Military Construction | Virginia | United States | HERT137167 | Active Vehicle Barricades, Main Gate |  |  |  | 2018-04-09 | 2017-12-10 | 2018-08-17 | 5% | 2018-08-17
2018-04-16 | 2014 | Air Force Active | Major Military Construction | Hawaii | United States | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  |  |  | 2015-11-10 | 2016-04-17 | 2018-04-11 | 100%
2018-07-11 | 2014 | Air Force Active | Major Military Construction | Utah | United States | KRSM003009 | Fire Crash Rescue Station |  |  |  | 2015-04-28 | 2015-04-16 | 2018-04-16 | 99% | 2017-02-16
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Utah | United States | KRSM083007 | 649 MUNS Munitions STAMP/Maintenance & Inspection Facility |  |  |  | 2018-02-14 | 2019-05-30 | 2019-05-30 | 2% | 2019-05-30
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Utah | United States | KRSM103013 | F-35A HANGAR 40/42 ADAL AND AMU |  |  |  | 2016-10-07 | 2018-10-07 | 2018-10-07 | 36% | 2018-10-07
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Utah | United States | KRSM133002 | HAYMAN IGLOOS |  |  |  | 2016-09-13 | 2017-05-30 | 2018-09-13 | 80% | 2018-09-13
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Utah | United States | KRSM143006 | 649 MUNS Precision Guided Missile Maintenance Facility |  |  |  | 2018-02-12 | 2019-04-30 | 2019-04-30 | 2% | 2019-04-30
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Utah | United States | KRSM143007 | 649 MUNS Munitions Storage Magazines |  |  |  | 2017-07-10 | 2018-11-30 | 2019-11-07 | 6% | 2019-11-11
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Utah | United States | KRSM153001 | F-35A FLIGHT SIMULATOR ADDITION, PHASE 2 |  |  |  | 2016-09-23 | 2017-12-15 | 2018-03-31 | 77% | 2017-12-31
2018-07-11 | 2017 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD043006 | HAZARDOUS CARGO PAD AND TAXIWAY |  |  |  | 2017-09-15 | 2018-01-30 | 2019-01-15 | 42% | 2019-01-15
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Turkey | LJYC133003 | AIRFIELD FIRE / CRASH RESCUE STATION |  |  |  | 2018-06-06 | 2020-06-04 | 2020-06-04 | 1% | 2020-07-02
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150007 | ERI: EXTEND PARKING APRONS |  |  |  | 2019-04-30 | 2018-08-01 | 2020-05-28 | 2% | 2020-08-25
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150008 | ERI: CONSTRUCT MUNITIONS STORAGE AREA |  |  |  | 2019-04-30 | 2018-08-01 | 2020-05-28 | 2% | 2020-08-25
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150009 | ERI: CONSTRUCT ONE-BAY HANGAR |  |  |  | 2019-04-30 | 2018-08-01 | 2020-05-28 | 2% | 2020-08-25
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150010 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2018-11-09 | 2018-08-01 | 2020-05-28 | 2% | 2020-08-25
2018-07-11 | 2017 | Air Force Active | Major Military Construction | New Mexico | United States | MHMV103108 | COMBAT RESCUE HELICOPTER (CRH) SIMULATOR |  |  |  | 2018-02-06 | 2018-12-21 | 2019-06-11 | 10% | 2019-06-11
2018-07-11 | 2015 | Air Force Active | Major Military Construction | Texas | United States | MPLS3274JB | FIRE STATION |  |  |  | 2015-09-25 | 2016-07-29 | 2018-05-31 | 38% | 2018-05-31
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD073000 | SYSTEM MANAGEMENT ENGINEERING FACILITY |  |  |  | 2018-01-10 | 2022-02-25 | 2020-06-08 | 1% | 2020-06-08
2018-07-11 | 2015 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD083002 | DORMITORY (72 RM) |  |  |  | 2017-03-20 | 2016-10-25 | 2018-11-11 | 71% | 2018-11-13
2018-07-11 | 2014 | Air Force Active | Unspecified Minor Military Construction | Arkansas | United States | NKAK963001P | REFUELING VEHICLE REPAIR SHOP CORRECT LIFE HEALTH SAFETY |  |  |  | 2017-08-14 | 2015-10-14 | 2018-08-14 | 49% | 2018-10-22
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093009 | F-35A ADAL FUEL OFFLOAD FACILITY |  |  |  | 2018-02-22 | 2018-10-05 | 2018-12-10 | 38% | 2019-03-10
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093016 | COMMUNICATIONS FACILITY |  |  |  | 2018-04-02 | 2016-06-30 | 2020-03-27 | 2% | 2020-03-27
2018-03-13 | 2015 | Air Force Active | Major Military Construction | Arizona | United States | NUEX103005 | Construct Flightline Fillstands |  |  |  | 2016-01-01 | 2016-11-22 | 2018-03-08 | 100% | 2018-03-08
2018-05-11 | 2016 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | NUEX113001 | FLIGHT LINE SECURITY FENCE |  |  |  | 2017-01-25 | 2017-10-23 | 2018-03-15 | 100% | 2017-10-30
2018-04-16 | 2015 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123001 | F-35 Aircraft Maintenance Hangar (Squadron 2) |  |  |  | 2016-07-01 | 2017-05-16 | 2018-02-09 | 100% | 2018-02-09
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123002 | F-35A BOMB BUILD-UP FACILITY |  |  |  | 2018-03-30 | 2018-07-02 | 2018-07-06 | 7% | 2018-09-04
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123004 | F-35A SQUADRON OPERATIONS/AMU/HANGAR (SQUADRON 4) |  |  |  | 2016-12-01 | 2018-11-27 | 2018-06-18 | 91% | 2018-09-12
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123005 | F-35A AIRCRAFT MAINTENANCE HANGAR (SQUADRON 3) |  |  |  | 2016-12-16 | 2018-03-27 | 2018-04-19 | 99% | 2018-05-26
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Arizona | United States | NUEX133000 | F-35 SQUADRON OPERATIONS/AIRCRAFT MAINTENANCE UNIT #5 |  |  |  | 2018-06-27 | 2019-02-27 | 2019-06-03 | 10% | 2019-08-02
2018-07-11 | 2017 | Air Force Active | Major Military Construction |  | Australia | PAF150400 | APR EXPAND AIRCRAFT PARKING APRON |  |  |  | 2018-09-01 | 2019-08-01 | 2019-10-16 | 1% | 2019-10-16
2018-07-11 | 2014 | Air Force Active | Major Military Construction | Maryland | United States | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  |  |  | 2014-07-07 | 2017-04-13 | 2018-03-22 | 87% | 2018-01-01
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Estonia | PAYZ15001A | ERI: Improve Airfield Infrastructure |  |  |  | 2017-05-15 | 2018-10-14 | 2018-10-14 | 11% | 2019-03-13
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Lithuania | PAYZ15001B | ERI: Improve Airfield Infrastructure |  |  |  | 2018-02-28 | 2019-01-01 | 2019-01-25 | 2% | 2019-06-24
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Latvia | PAYZ15001C | ERI: Improve Airfield Infrastructure |  |  |  | 2018-02-27 | 2018-09-30 | 2019-03-05 | 3% | 2019-03-05
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Bulgaria | PAYZ15001D | ERI: Improve Airfield Infrastructure |  |  |  | 2018-05-08 | 2018-09-01 | 2018-09-11 | 10% | 2019-02-08
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Romania | PAYZ15001E | ERI: Improve Airfield Infrastructure |  |  |  | 2017-11-15 | 2018-06-26 | 2018-11-14 | 5% | 2018-12-14
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Italy | PAYZ15001H | ERI: Improve Weapons Storage Facility |  |  |  | 2017-12-11 | 2020-08-28 | 2020-06-12 | 1% | 2020-06-12
2018-07-11 | 2015 | Air Force Active | Major Military Construction |  | Poland | PAYZ15002A | ERI: Improve Support Infrastructure |  |  |  | 2017-11-28 | 2018-04-02 | 2019-04-12 | 1% | 2019-04-12
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Kansas | United States | PRQE105144 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2017-11-30 | 2017-09-25 | 2019-01-18 | 29% | 2019-01-18
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Kansas | United States | PRQE165113 | KC-46A ALTER FLIGHT SIMULATOR BLDGS |  |  |  | 2017-07-28 | 2018-07-20 | 2018-05-16 | 100% | 2018-07-21
2018-03-13 | 2017 | Air Force Active | Major Military Construction | Kansas | United States | PRQE175112 | KC-46A ADAL TAXIWAY DELTA |  |  |  | 2017-04-28 | 2018-04-12 | 2018-02-08 | 100% | 2018-02-08
2018-01-12 | 2013 | Air Force Active | Unspecified Minor Military Construction | New Jersey | United States | PTFL126001 | Addition To Maintenance Training Facility, Bldg 2324 |  |  |  | 2015-11-02 | 2016-06-29 | 2016-11-01 | 100% | 2017-03-24
2018-07-11 | 2016 | Air Force Active | Unspecified Minor Military Construction | New Jersey | United States | PTFL136001 | READINESS (C-CBRNE) BATTLE AXE FACILITY |  |  |  | 2018-06-15 | 2019-07-01 | 2019-07-01 | 1% | 2019-03-07
2018-04-16 | 2015 | Air Force Active | Unspecified Minor Military Construction | New Mexico | United States | PXLY100034 | RANGE GENERAL PURPOSE MAINT FAC, MAFR |  |  |  | 2017-03-06 | 2018-03-09 | 2018-03-29 | 100% | 2018-04-16
2018-04-16 | 2015 | Air Force Active | Unspecified Minor Military Construction | New Mexico | United States | PXLY100035 | RANGE OPS SUPPORT FAC, MAFR |  |  |  | 2017-03-06 | 2018-03-09 | 2018-03-29 | 100% | 2018-04-16
2018-03-13 | 2014 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF092009 | B-52 ADAL Aircraft Maintenance Unit (AMU) |  |  |  | 2016-03-23 | 2017-09-14 | 2018-02-08 | 100% | 2018-01-04
2018-02-13 | 2014 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF092013 | B-52 Munitions Storage Igloos |  |  |  | 2014-07-15 | 2016-01-06 | 2018-01-15 | 100% | 2018-01-15
2018-07-11 | 2015 | Air Force Active | Unspecified Minor Military Construction | North Dakota | United States | QJVF143101 | MISSILE MAINTENANCE B1134 ADDITION |  |  |  | 2017-04-19 | 2017-02-21 | 2018-07-29 | 90% | 2018-07-13
2018-05-11 | 2014 | Air Force Active | Military Family Housing Improvement |  | Japan | QKKA133001P1 | Improve Family Housing, Ph 1 |  |  |  | 2015-10-29 | 2014-09-30 | 2017-09-27 | 100% | 2017-06-30
2018-07-11 | 2016 | Air Force Active | Unspecified Minor Military Construction |  | Japan | QKKA153001 | DEMO AND CONSOLIDATE JET ENGINE MAINTENANCE STORAGE FACILITY |  |  |  | 2017-12-29 | 2017-11-09 | 2018-12-28 | 4% | 2018-10-07
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | Japan | QKKA154008 | IMPROVE FAMILY HOUSING PH 3, A/C, WEATHERIZATION |  |  |  | 2017-10-20 | 2018-06-23 | 2020-08-17 | 3% | 2020-09-14
2018-07-11 | 2015 | Air Force Active | Major Military Construction | Nevada | United States | RKMF143001 | F-35A Maintenance Hangar/Amu |  |  |  | 2016-02-15 | 2018-01-04 | 2018-08-13 | 90% | 2018-08-13
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Nevada | United States | RKMF143002 | F-35A LIVE ORDNANCE LOADING AREA |  |  |  | 2018-01-11 | 2019-07-31 | 2019-07-31 | 2% | 2019-05-09
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Nevada | United States | RKMF143003 | F-35A AIRFIELD PAVEMENTS |  |  |  | 2017-11-16 | 2019-03-29 | 2019-10-02 | 2% | 2019-02-02
2018-07-11 | 2012 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  |  |  | 2012-10-15 | 2016-02-15 | 2018-08-02 | 98% | 2018-08-02
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP150907 | DORMITORY (144 RM) |  |  |  | 2017-06-19 | 2018-12-25 | 2019-01-20 | 48% | 2019-03-21
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Florida | United States | SXHT013001 | FIRE/CRASH RESCUE STATION |  |  |  | 2018-01-29 | 2019-02-05 | 2019-03-11 | 14% | 2019-06-09
2018-07-11 | 2010 | Air Force Active | Major Military Construction |  | Germany | TYFR053037 | Aerospace Ground Equipment Maintenance Complex |  |  |  | 2012-08-06 | 2013-07-06 | 2018-06-29 | 99% | 2014-02-11
2018-07-11 | 2012 | Air Force Active | Major Military Construction |  | Germany | TYFR063017 | DORMITORY (192 RM) |  |  |  | 2015-08-10 | 2015-03-02 | 2019-08-16 | 74% | 2019-08-16
2018-07-11 | 2013 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR106020U | MUNITIONS SHIPPING AND RECEIVING FACILITY |  |  |  | 2016-05-24 | 2017-11-30 | 2018-09-28 | 86% | 2018-09-28
2018-02-13 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR106261 | PL-1 SECURITY MEASURES FOR COMMUNICATIONS COMPOUND |  |  |  | 2014-01-22 | 2014-12-12 | 2018-01-26 | 100% | 2016-02-04
2018-07-11 | 2016 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR136157 | ADD/ALTER LARGE VEHICLE INSPECTION STATION |  |  |  | 2016-04-04 | 2016-06-15 | 2018-07-16 | 90% | 2017-01-24
2018-01-12 | 2011 | Air Force Active | Major Military Construction |  | Germany | TYFU083507R2 | Dormitory (128 Rm) |  |  |  | 2014-06-16 | 2017-07-04 | 2017-12-18 | 100% | 2017-03-28
2018-07-11 | 2016 | Air Force Active | Unspecified Minor Military Construction | Georgia | United States | UHHZ110323W | AIRFIELD FENCE, GATES |  |  |  | 2017-01-26 | 2018-02-05 | 2018-02-05 | 40% | 2018-02-05
2018-01-12 | 2014 | Air Force Active | Unspecified Minor Military Construction |  | Germany | VYHK143301 | Catch Basin For Storm Water Discharge, Location 2, Welscherw |  |  |  | 2015-10-30 | 2017-09-14 | 2017-12-19 | 100% | 2017-12-19
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | Greenland | WWCX103027 | Thule Consolidation, Phase 1 |  |  |  | 2016-07-09 | 2017-06-27 | 2018-10-24 | 88% | 2018-07-20
2018-07-11 | 2014 | Air Force Active | Major Military Construction |  | Greenland | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  |  |  | 2014-08-20 | 2016-06-17 | 2018-02-23 | 93% | 2017-08-25
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK093003 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2017-05-17 | 2018-11-08 | 2018-11-08 | 23% | 2019-03-17
2018-07-11 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK129000 | AIR CONTROL GROUP SQUADRON OPERATIONS |  |  |  | 2016-04-14 | 2015-11-05 | 2018-05-31 | 53% | 2018-05-31
2018-07-11 | 2015 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK143004 | KC-46A DEPOT MAINT COMPLEX SUPPORT INFRASTRUCTURE |  |  |  | 2016-08-31 | 2017-11-10 | 2018-06-25 | 88% | 2018-07-25
2018-07-11 | 2015 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK153005 | KC-46A TWO-BAY DEPOT MAINTENANCE HANGAR |  |  |  | 2017-07-10 | 2017-11-10 | 2019-06-11 | 22% | 2019-09-25
2018-07-11 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK163002 | KC-46A Depot Maintenance Dock |  |  |  | 2017-04-17 | 2018-07-08 | 2018-10-23 | 33% | 2018-11-10
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK173003 | KC-46A DEPOT SYSTEM INTEGRATION LABORATORY |  |  |  | 2017-07-19 | 2017-12-07 | 2018-12-27 | 28% | 2019-03-22
2018-04-16 | 2015 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | XLWU121058 | F-22 LIVE ORDNANCE LOADING AREA |  |  |  | 2017-02-15 | 2018-01-14 | 2018-02-09 | 100% | 2018-04-05
2018-01-12 | 2016 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ094013 | Front Gates Force Protection Enhancements |  |  |  | 2017-04-03 | 2017-11-03 | 2017-12-21 | 100% | 2017-12-21
2018-07-11 | 2016 | Air Force Active | Unspecified Minor Military Construction | California | United States | XUMU131054C1 | JSpOC Backup Generators |  |  |  | 2018-04-24 | 2018-12-31 | 2018-12-31 | 2% | 2018-09-28
2018-07-11 | 2014 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV053302 | Add/Alter Foreign Materiel Exploitation Laboratory |  |  |  | 2015-09-09 | 2016-11-16 | 2018-07-27 | 98% | 2017-11-17
2018-07-11 | 2017 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV123205 | RELOCATE ENTRY CONTROL FACILITY 26A |  |  |  | 2017-08-20 | 2019-09-09 | 2019-09-09 | 2% | 2019-07-20
2018-07-11 | 2016 | Air Force Active | Unspecified Minor Military Construction | Ohio | United States | ZHTV146001 | CE MAINTENANCE SHOP |  |  |  | 2017-04-11 | 2018-12-07 | 2018-12-07 | 55% | 2018-11-02
2018-07-11 | 2016 | Air Force Active | Major Military Construction |  | Japan | ZNRE143000 | C-130J FLIGHT SIMULATOR FACILITY |  |  |  | 2017-02-14 | 2017-10-23 | 2018-12-31 | 41% | 2018-12-31
2018-07-11 | 2017 | Air Force Active | Unspecified Minor Military Construction |  | Japan | ZNRE163000 | ADAL Fuel System Maintenance Hangar For C-130J-30 |  |  |  | 2017-10-15 | 2018-06-11 | 2018-12-14 | 25% | 2018-12-14
2018-07-11 | 2016 | Air Force Active | Military Family Housing Improvement |  | Japan | ZNRE164331 | Improve Family Housing Ph 7 |  |  |  | 2017-11-17 | 2019-01-01 | 2020-06-12 | 5% | 2020-07-13
2018-07-01 | 2015 | Air Force Reserve | Major Military Construction | Texas | United States | DDPM130008 | Explosive Ordnance Disposal Facility |  |  |  | 2017-09-01 | 2016-07-27 | 2019-01-15 | 3%
2018-07-01 | 2012 | Air Force Reserve | Major Military Construction | South Carolina | United States | DKFX079003 | Red Horse Readiness And Training Facility |  |  |  | 2012-07-13 | 2013-03-01 | 2017-03-31 | 100% | 2016-10-11
2018-07-01 | 2014 | Air Force Reserve | Major Military Construction | California | United States | PDPG030130P1 | Joint Regional Deployment And Passenger Terminal Facility |  |  |  | 2015-05-05 | 2017-03-20 | 2017-09-20 | 100% | 2017-05-12
2018-07-01 | 2013 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ099095 | Flight Simulator Facility |  |  |  | 2014-08-05 | 2015-07-31 | 2017-02-28 | 100% | 2016-07-13
2018-07-01 | 2014 | Air Force Reserve | Major Military Construction | Oklahoma | United States | WWYK129000 | AIR CONTROL TOWER SQUADRON OPERATIONS |  |  |  | 2016-04-14 | 2017-09-21 | 2018-05-18 | 90% | 2018-03-11
2018-01-01 | 2016 | Air National Guard | Major Military Construction | New Jersey | United States | AQRC059093 | Fuel Cell and Corrosion Control Hangar and Shops |  |  |  | 2018-09-11 | 2020-04-08 | 2020-03-09 | 0%
2018-07-02 | 2015 | Air National Guard | Unspecified Minor Military Construction | Tennessee | United States | BKTZ129083 | Construct Cyber SCIF |  |  |  | 2015-10-28 | 2016-10-20 | 2018-03-20 | 100% | 2016-12-13
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Alabama | United States | BRKR999147 | Add to and Alter Distributed Ground Station Facility |  |  |  | 2014-10-31 | 2016-10-23 | 2019-04-30 | 99% | 2017-09-27
2018-07-02 | 2015 | Air National Guard | Unspecified Minor Military Construction | Connecticut | United States | CEKT129080 | Add to Fire Station |  |  |  | 2016-03-01 | 2018-08-18 | 2019-09-27 | 99% | 2019-09-27
2018-07-02 | 2015 | Air National Guard | Major Military Construction | Connecticut | United States | CEKT139004 | Construct C-130 Fuel Cell and Corrosion Control Facility |  |  |  | 2015-07-24 | 2019-05-24 | 2019-05-24 | 99% | 2019-05-24
2018-07-02 | 2017 | Air National Guard | Major Military Construction | Connecticut | United States | CEKT139042 | Construct Small Air Terminal |  |  |  | 2017-09-29 | 2023-03-22 | 2020-11-23 | 33% | 2020-11-23
2018-07-02 | 2017 | Air National Guard | Major Military Construction | Vermont | United States | CURZ159055 | F-35 Beddown 4- Bay Flight Simulator |  |  |  | 2017-06-17 | 2018-07-23 | 2018-07-30 | 97% | 2018-07-30
2018-06-05 | 2016 | Air National Guard | Unspecified Minor Military Construction | Virginia | United States | CVVM099000 | Joint Forces Headquarters - ANG Share |  |  |  | 2015-03-24 | 2015-10-31 | 2018-07-31 | 99% | 2018-07-31
2018-06-05 | 2017 | Air National Guard | Unspecified Minor Military Construction | Virginia | United States | CVVM179001 | Construct 200th Weather Flight Training Facility |  |  |  | 2017-09-12 | 2018-10-12 | 2018-10-31 | 42% | 2018-10-31
2018-06-05 | 2016 | Air National Guard | Major Military Construction | Florida | United States | DBEH143000 | NDAA Space Control Facility |  |  |  | 2018-09-07 | 2023-08-18 | 2019-07-26 | 1% | 2019-07-26
2018-06-05 | 2016 | Air National Guard | Major Military Construction | Alabama | United States | FAKZ059173 | TFI - Replace Squadron Operations Facility |  |  |  | 2018-09-05 | 2019-09-06 | 2020-01-20 | 5% | 2020-01-20
2018-07-02 | 2016 | Air National Guard | Major Military Construction | Iowa | United States | FFAN139009 | NDAA: AOG/CYBER Beddown - Renovate Bldg 430 |  |  |  | 2016-09-17 | 2017-09-14 | 2019-03-29 | 97% | 2017-12-18
2018-07-02 | 2015 | Air National Guard | Major Military Construction | Iowa | United States | FFAN139010 | NDAA: Remotely Piloted & Targeting Group Beddown |  |  |  | 2015-07-23 | 2016-08-07 | 2019-05-31 | 99% | 2016-10-07
2018-06-05 | 2016 | Air National Guard | Major Military Construction | North Carolina | United States | FJRP089066 | Replace C-130 Squadron Operations Facility |  |  |  | 2017-10-20 | 2019-01-13 | 2018-11-25 | 51%
2018-01-01 | 2017 | Air National Guard | Major Military Construction | North Carolina | United States | FJRP159073 | C-17 Type III Hydrant Refueling Sys/Ramp Expansion |  |  |  | 2018-10-30 | 2020-11-28 | 2020-10-29 | 0%
2018-07-02 | 2016 | Air National Guard | Major Military Construction | Maine | United States | FKNN059220 | Add to and Alter Fire Crash/Rescue Station |  |  |  | 2016-10-03 | 2017-10-15 | 2018-08-28 | 99% | 2018-08-28
2018-06-05 | 2015 | Air National Guard | Unspecified Minor Military Construction | Maine | United States | FKNN119013 | ANG Portion of Maine State JFHQ-Augusta |  |  |  | 2015-06-05 | 2017-07-05 | 2017-06-30 | 99% | 2017-04-01
2018-07-02 | 2017 | Air National Guard | Major Military Construction | Minnesota | United States | FMKM089018 | Load Crew Training/Weapon Shops |  |  |  | 2017-10-16 | 2019-03-03 | 2019-07-31 | 22% | 2018-11-12
2018-07-02 | 2014 | Air National Guard | Major Military Construction | New York | United States | FPBB129050 | MQ-9 Flight Training Unit Hangar |  |  |  | 2014-09-25 | 2015-08-04 | 2016-08-31 | 100% | 2015-11-04
2018-07-02 | 2015 | Air National Guard | Unspecified Minor Military Construction | Colorado | United States | FTAE129002 | Construct Range Control Facility & Fitness Center |  |  |  | 2016-04-26 | 2016-06-22 | 2018-07-26 | 99% | 2017-06-01
2018-01-01 | 2017 | Air National Guard | Major Military Construction | Texas | United States | FWJH099082 | Consolidate Crew Readiness Facility, Building 1397 |  |  |  | 2018-10-16 | 2019-10-16 | 2019-09-26 | 0%
2018-07-02 | 2014 | Air National Guard | Unspecified Minor Military Construction | Washington | United States | GJKZ129093 | Construct 2 Set DRBS Storage Facility |  |  |  | 2014-09-18 | 2015-03-17 | 2017-03-14 | 100% | 2016-12-02
2018-07-02 | 2016 | Air National Guard | Major Military Construction | Arkansas | United States | HKRZ129076 | NDAA Construct DGS RPA IS SCIF |  |  |  | 2018-02-01 | 2020-02-01 | 2020-02-01 | 3% | 2020-02-01
2018-06-05 | 2017 | Air National Guard | Unspecified Minor Military Construction | Wisconsin | United States | HTUV132007 | Add to Fire Station, Building 621 |  |  |  | 2018-06-01 | 2019-11-28 | 2019-08-11 | 10%
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Montana | United States | JKSE129321 | Intra-Theater Airlift Conversion |  |  |  | 2014-10-20 | 2018-03-12 | 2018-07-31 | 99% | 2018-05-16
2018-07-02 | 2016 | Air National Guard | Major Military Construction | Oregon | United States | KJAQ099058 | REPLACE FIRE CRASH/RESCUE STATION |  |  |  | 2017-06-07 | 2018-05-28 | 2018-12-01 | 25% | 2018-11-01
2018-07-02 | 2016 | Air National Guard | Major Military Construction | North Dakota | United States | KKGA129066 | Intel Targeting Facilities |  |  |  | 2017-07-18 | 2018-07-18 | 2018-04-30 | 99% | 2017-09-07
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Indiana | United States | LDXF099060 | Add/Alter Bldg 37 for Distributed Common Grnd Stn |  |  |  | 2014-10-16 | 2016-02-28 | 2018-01-31 | 99% | 2016-12-16
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Pennsylvania | United States | LKLW109037 | Communications Operations and Training Facility |  |  |  | 2014-10-01 | 2015-10-01 | 2016-05-31 | 100% | 2016-01-15
2018-07-02 | 2014 | Air National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | LKLW959716 | Consolidate Vehicle Maintenance Function |  |  |  | 2015-10-16 | 2016-07-12 | 2017-03-20 | 100% | 2016-10-13
2018-01-01 | 2017 | Air National Guard | Major Military Construction | Florida | United States | LSGA019179 | Replace Fire Crash/Rescue Station |  |  |  | 2018-10-29 | 2024-04-20 | 2019-07-18 | 1% | 2019-07-18
2018-07-02 | 2015 | Air National Guard | Unspecified Minor Military Construction | South Dakota | United States | LUXC139026 | Construct Addition, B16 Crash/Fire Rescue |  |  |  | 2016-04-01 | 2016-11-27 | 2016-12-07 | 100% | 2016-12-07
2018-07-02 | 2016 | Air National Guard | Major Military Construction | West Virginia | United States | LYBH049066 | Force Protection- Relocate Coonskin Road |  |  |  | 2016-07-20 | 2016-07-20 | 2017-06-11 | 100% | 2017-06-11
2018-07-02 | 2015 | Air National Guard | Major Military Construction | Michigan | United States | MBMV129060 | RPA Beddown |  |  |  | 2015-05-07 | 2016-05-14 | 2017-07-31 | 99% | 2016-02-15
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Maryland | United States | MMMD129073 | 175th Network Warfare Squadron Facility |  |  |  | 2017-09-19 | 2018-10-06 | 2018-10-12 | 56% | 2018-10-31
2018-07-02 | 2016 | Air National Guard | Unspecified Minor Military Construction | Arkansas | United States | NKAK139133 | Construct Small Air Terminal Coverd Storage |  |  |  | 2016-06-12 | 2017-06-12 | 2017-06-12 | 100% | 2017-06-12
2018-01-01 | 2018 | Air National Guard | Major Military Construction | California | United States | PDPG169013 | TFI Construct RPA Formal Training Unit |  |  |  | 2018-10-24 | 2020-04-16 | 2020-04-20 | 1% | 2020-04-20
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Maryland | United States | PJMS129058 | CYBER/ISR Facility |  |  |  | 2016-10-12 | 2017-10-12 | 2018-10-11 | 86% | 2018-10-11
2018-07-02 | 2017 | Air National Guard | Unspecified Minor Military Construction | West Virginia | United States | PJVY159064 | C-17 Const Munitions Storage |  |  |  | 2017-10-06 | 2018-06-29 | 2018-11-01 | 10% | 2018-09-01
2018-06-05 | 2017 | Air National Guard | Major Military Construction | South Carolina | United States | PSTE009070 | Replace Operations and Training Facility |  |  |  | 2017-09-27 | 2019-04-28 | 2018-04-30 | 35% | 2019-04-17
2018-07-02 | 2014 | Air National Guard | Unspecified Minor Military Construction | South Carolina | United States | PSTE129092 | Construct North Overrun |  |  |  | 2014-03-11 | 2014-12-24 | 2016-01-29 | 100% | 2014-12-08
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Tennessee | United States | PSXE109034 | TEC Expansion - Dormitory and Classroom Training Facility |  |  |  | 2014-07-22 | 2016-07-21 | 2016-11-29 | 100% | 2016-11-29
2018-07-02 | 2015 | Air National Guard | Unspecified Minor Military Construction | Tennessee | United States | PSXE139000 | Taxiway B Extension |  |  |  | 2015-07-10 | 2016-10-18 | 2017-09-01 | 100% | 2017-09-01
2018-01-01 | 2017 | Air National Guard | Unspecified Minor Military Construction | New Jersey | United States | PTFL129091 | Add to Vehicle Maintenance Facility, Bldg 3325 |  |  |  | 2018-09-28 | 2019-10-28 | 2019-09-28 | 0%
2018-07-02 | 2016 | Air National Guard | Major Military Construction | California | United States | QMSN099104 | Replace Vehicle Maintenance Facility |  |  |  | 2018-01-05 | 2019-03-06 | 2019-03-06 | 5% | 2019-03-06
2018-06-05 | 2016 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH079073 | Replace Squadron Operations Facility |  |  |  | 2018-02-19 | 2018-10-29 | 2019-08-30 | 5%
2018-07-02 | 2016 | Air National Guard | Major Military Construction | New York | United States | RVKQ139005 | Remotely Piloted Aircraft Beddown, Building 912 |  |  |  | 2016-11-07 | 2018-01-01 | 2018-02-07 | 98% | 2018-02-07
2018-07-02 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139901 | KC-46A ADAL Fuel Cell Building 253 |  |  |  | 2015-08-18 | 2016-11-19 | 2019-01-07 | 51% | 2019-01-07
2018-07-02 | 2016 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139903 | KC-46A Add/Alter Flight Simulator Bldg 156 |  |  |  | 2016-05-06 | 2017-07-31 | 2018-08-31 | 97% | 2018-01-30
2018-07-02 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139904 | KC-46A ADAL Maint Hangar Building 254 |  |  |  | 2015-08-18 | 2016-11-18 | 2019-10-07 | 3% | 2019-10-07
2018-07-02 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139905 | KC-46A ADAL Airfield Pavements & Hydrant Systems |  |  |  | 2017-10-18 | 2018-10-13 | 2018-12-31 | 7% | 2018-11-01
2018-06-05 | 2016 | Air National Guard | Unspecified Minor Military Construction | Oregon | United States | TQKD149054 | ANG Part of Oregon JFHQ |  |  |  | 2016-07-19 | 2017-08-13 | 2018-01-03 | 100% | 2018-01-03
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Rhode Island | United States | TWLR129077 | C-130J Flight Simulator Training Facility |  |  |  | 2015-03-15 | 2015-12-14 | 2019-01-31 | 95% | 2017-11-15
2018-06-05 | 2017 | Air National Guard | Unspecified Minor Military Construction | Rhode Island | United States | TWLR139040 | Add to Fire Station Building 11 |  |  |  | 2018-04-16 | 2019-05-16 | 2019-10-31 | 5% | 2019-09-30
2018-07-02 | 2017 | Air National Guard | Unspecified Minor Military Construction | Rhode Island | United States | TWLR159061 | ANG Share - Joint Forces Headquarters Facility |  |  |  | 2017-09-07 | 2020-02-28 | 2020-02-28 | 7% | 2019-09-30
2018-07-02 | 2014 | Air National Guard | Unspecified Minor Military Construction | Missouri | United States | ULYB112022 | Security Forces Admin and Storage Facility |  |  |  | 2014-10-29 | 2015-10-12 | 2017-12-04 | 100% | 2016-03-04
2018-07-02 | 2017 | Air National Guard | Unspecified Minor Military Construction | Missouri | United States | ULYB132009 | Construct EMEDS -CM Facility |  |  |  | 2017-11-15 | 2018-11-16 | 2018-11-15 | 35% | 2018-11-15
2018-07-02 | 2017 | Air National Guard | Major Military Construction | Iowa | United States | VSSB099014 | Construct Consolidated Support Functions |  |  |  | 2017-09-13 | 2018-09-28 | 2018-12-24 | 16% | 2018-09-30
2018-07-02 | 2016 | Air National Guard | Major Military Construction | Kansas | United States | VUBV109002 | Range Training Support Facilities |  |  |  | 2016-09-08 | 2017-11-03 | 2018-05-30 | 97% | 2017-12-05
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Ohio | United States | WAAR109002 | Alter Intelligence Operations Facility |  |  |  | 2014-12-01 | 2015-12-01 | 2017-06-30 | 100% | 2016-02-10
2018-07-02 | 2014 | Air National Guard | Unspecified Minor Military Construction | Kentucky | United States | WEAS129000 | Realign Grade Lane |  |  |  | 2015-08-20 | 2015-08-20 | 2016-06-15 | 100% | 2016-06-15
2018-07-02 | 2016 | Air National Guard | Unspecified Minor Military Construction | New York | United States | WKVB139016 | Add to Fuel Cell Complex Building 370 |  |  |  | 2017-03-06 | 2017-12-31 | 2018-05-01 | 59% | 2018-05-01
2018-07-02 | 2016 | Air National Guard | Unspecified Minor Military Construction | Ohio | United States | WYTD079032 | ACA Alert Crews Quarters Facility |  |  |  | 2016-06-21 | 2017-03-18 | 2018-01-26 | 100% | 2017-05-15
2018-07-02 | 2017 | Air National Guard | Major Military Construction | Ohio | United States | WYTD109008 | Indoor Small Arms Range |  |  |  | 2018-04-27 | 2018-11-09 | 2019-01-31 | 25% | 2018-11-30
2018-07-02 | 2016 | Air National Guard | Major Military Construction | Georgia | United States | XDQU949500 | C-130 Squadron Operations Facility |  |  |  | 2016-11-14 | 2017-11-08 | 2018-06-30 | 98% | 2018-05-31
2018-07-02 | 2014 | Air National Guard | Unspecified Minor Military Construction | Oklahoma | United States | XHZG129946 | Add to Fire Crash and Rescue Station, Building 403 |  |  |  | 2014-08-20 | 2015-08-15 | 2017-06-30 | 100% | 2015-10-08
2018-06-05 | 2017 | Air National Guard | Unspecified Minor Military Construction | New Jersey | United States | YKSX159100 | Replace Range Control Tower, Bldg 16 |  |  |  | 2017-11-14 | 2018-09-28 | 2018-11-13 | 10%
2018-07-02 | 2016 | Air National Guard | Major Military Construction | Oklahoma | United States | YZEU139006 | Medium Altitude Manned ISR Beddown |  |  |  | 2017-08-15 | 2018-08-15 | 2018-08-15 | 20% | 2018-08-15
2018-07-02 | 2015 | Air National Guard | Major Military Construction | Pennsylvania | United States | ZAWA159061 | RPA Operations Center |  |  |  | 2015-07-20 | 2016-02-15 | 2016-07-22 | 100% | 2016-07-22
2017-04-30 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 1235 | Physical Fitness Facility |  |  |  | 2012-07-12 | 2014-04-10 | 2016-03-31 | 95% | 2017-03-31
2017-05-31 | 2011 | Army Active | Major Military Construction | Colorado | United States | 13852 | Simulations Center |  |  |  | 2011-11-04 | 2016-07-23 | 2016-09-30 | 99% | 2016-12-12
2017-07-31 | 2012 | Army Active | Major Military Construction | Louisiana | United States | 17220 | Fire Station |  |  |  | 2013-11-06 | 2015-11-11 | 2017-01-19 | 99% | 2017-01-19
2018-06-30 | 2012 | Army Active | Major Military Construction | Kansas | United States | 2728 | Physical Fitness Facility |  |  |  | 2012-03-29 | 2017-02-08 | 2018-09-28 | 99%
2018-06-30 | 2013 | Army Active | Major Military Construction | Virginia | United States | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2013-10-15 | 2017-05-03 | 2018-03-14 | 98% | 2018-04-03
2018-06-30 | 2015 | Army Active | Major Military Construction | Virginia | United States | 41449 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  | 2016-10-17 | 2018-10-07 | 2018-12-18 | 75%
2017-07-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 45116 | Aircraft Component Maintenance Shop |  |  |  | 2013-08-08 | 2016-12-30 | 2016-12-30 | 97% | 2017-03-29
2017-07-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 5034 | Vehicle Maintenance Facility |  |  |  | 2013-01-24 | 2014-07-18 | 2017-01-31 | 99% | 2017-01-31
2017-07-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 51519 | Ballistic Evaluation Center |  |  |  | 2012-12-04 | 2015-02-15 | 2017-07-07 | 98% | 2017-07-14
2017-07-31 | 2014 | Army Active | Major Military Construction | Georgia | United States | 51868 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2015-01-06 | 2016-12-26 | 2017-07-21 | 94%
2018-06-30 | 2015 | Army Active | Major Military Construction | South Carolina | United States | 51937 | Trainee Barracks Complex 3, Ph1 |  |  |  | 2016-03-17 | 2018-03-17 | 2018-11-22 | 80%
2018-06-30 | 2014 | Army Active | Major Military Construction | Virginia | United States | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  | 1700000 | 79933, 92764 | 2014-10-09 | 2017-12-09 | 2018-03-13 | 98%
2018-06-30 | 2011 | Army Active | Major Military Construction | California | United States | 53789 | Advanced Individual Training Barracks |  |  |  | 2013-10-22 | 2018-06-15 | 2018-09-24 | 90%
2018-06-30 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 55121 | Aerial Gunnery Range |  |  |  | 2015-12-31 | 2017-12-30 | 2018-08-13 | 98%
2018-06-30 | 2016 | Army Active | Major Military Construction | New York | United States | 55578 | NCO Academy Complex |  | 1400000 | 92764 | 2017-05-23 | 2019-08-11 | 2018-11-14 | 72%
2018-06-30 | 2012 | Army Active | Major Military Construction | Utah | United States | 55823 | Life Sciences Test Facility Addition |  |  |  | 2012-08-29 | 2015-02-15 | 2018-03-19 | 100% | 2017-10-30
2017-07-31 | 2012 | Army Active | Major Military Construction |  | Germany | 55985 | Chapel |  |  |  | 2013-11-21 | 2016-03-23 | 2017-01-26 | 99% | 2017-01-30
2017-07-31 | 2011 | Army Active | Major Military Construction | Hawaii | United States | 56024 | Flood Mitigation |  |  |  | 2012-10-17 | 2014-10-14 | 2016-11-17 | 99% | 2017-04-06
2018-06-30 | 2012 | Army Active | Major Military Construction |  | Germany | 57594 | Satellite Communications Center |  |  |  | 2014-03-14 | 2017-11-05 | 2017-11-05 | 99% | 2016-12-27
2017-05-31 | 2011 | Army Active | Major Military Construction | Kentucky | United States | 58675 | Mout Collective Training Facility |  |  |  | 2011-07-06 | 2016-10-15 | 2016-09-09 | 99% | 2016-11-22
2018-06-30 | 2008 | Army Active | Major Military Construction |  | Korea, South | 58784 | Barracks Complex |  |  |  | 2008-04-22 | 2014-09-07 | 2018-01-18 | 99% | 2018-01-18
2018-06-30 | 2013 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility |  |  |  | 2016-04-13 | 2019-10-10 | 2019-10-10 | 73%
2018-06-30 | 2017 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility, Incr 2 | 86285 |  |  | 2016-04-13 | 2019-10-10 | 2019-10-10 | 73%
2018-06-30 | 2018 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility, Incr 3 | 86286 |  |  | 2016-04-13 | 2019-10-10 | 2019-10-10 | 73%
2018-06-30 | 2012 | Army Active | Major Military Construction |  | Germany | 58925 | Satellite Communications Center |  |  |  | 2014-03-14 | 2017-11-05 | 2018-08-31 | 99% | 2017-02-27
2018-06-30 | 2011 | Army Active | Major Military Construction | New York | United States | 59044 | Science Facility, Ph 2 |  |  |  | 2011-11-17 | 2016-01-29 | 2019-10-31 | 99%
2018-06-30 | 2014 | Army Active | Major Military Construction |  | Marshall Islands | 59779 | Pier |  | 2125000 | 92764 | 2016-08-17 | 2020-06-10 | 2020-08-05 | 46%
2017-07-31 | 2011 | Army Active | Major Military Construction |  | Germany | 60555 | Information Processing Center |  |  |  | 2012-06-18 | 2014-06-01 | 2017-01-31 | 99% | 2016-11-08
2017-07-31 | 2012 | Army Active | Major Military Construction |  | Germany | 61842 | Access Control Point |  |  |  | 2015-05-11 | 2016-12-01 | 2017-05-31 | 95% | 2017-06-19
2018-06-30 | 2014 | Army Active | Major Military Construction | Maryland | United States | 62204 | Hazardous Material Storage Building |  | 100000 | 92764 | 2016-02-23 | 2017-08-16 | 2018-11-30 | 48%
2017-07-31 | 2012 | Army Active | Major Military Construction | California | United States | 62657 | Water Treatment and Distro System |  |  |  | 2012-10-19 | 2015-10-19 | 2016-10-25 | 98% | 2017-04-28
2018-06-30 | 2013 | Army Active | Major Military Construction |  | Japan | 62663 | Vehicle Maintenance Shop |  |  |  | 2017-09-18 | 2019-04-01 | 2019-05-31 | 13%
2018-06-30 | 2013 | Army Active | Major Military Construction |  | Japan | 62783 | Satellite Communications Facility |  |  |  | 2014-11-21 | 2021-06-09 | 2021-12-06 | 52%
2018-06-30 | 2011 | Army Active | Major Military Construction | California | United States | 63015 | Satellite Communications Facility |  |  |  | 2011-09-21 | 2016-06-30 | 2018-09-18 | 86%
2018-06-30 | 2010 | Army Active | Major Military Construction | Virginia | United States | 63571 | Road and Access Control Point |  |  |  | 2016-04-28 | 2017-08-01 | 2018-07-11 | 87%
2018-06-30 | 2012 | Army Active | Major Military Construction | Washington | United States | 64014 | Battalion Complex |  | 600000 | 78196 | 2012-07-25 | 2015-04-08 | 2018-05-23 | 99% | 2018-05-23
2017-07-31 | 2012 | Army Active | Major Military Construction | Missouri | United States | 64365 | Vehicle Maintenance Facility |  |  |  | 2012-09-18 | 2014-08-25 | 2017-02-13 | 99% | 2016-05-12
2018-06-30 | 2013 | Army Active | Major Military Construction | Washington | United States | 64456 | Battalion Complex |  |  |  | 2013-06-26 | 2018-07-05 | 2018-12-31 | 70%
2017-04-30 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 64753 | Vehicle Maintenance Facility |  |  |  | 2012-07-19 | 2014-04-11 | 2016-04-14 | 98% | 2017-04-14
2018-06-30 | 2012 | Army Active | Major Military Construction | Texas | United States | 65374 | Operational Readiness Training Complex |  |  |  | 2012-09-05 | 2017-07-10 | 2017-11-03 | 100% | 2017-11-03
2017-07-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 65679 | Vehicle Maintenance Shop |  | 13450000 | 62663, 68826 | 2013-06-27 | 2016-08-06 | 2016-10-13 | 99% | 2016-10-13
2018-06-30 | 2012 | Army Active | Major Military Construction | Maryland | United States | 65755 | Brigade Complex |  |  |  | 2012-12-12 | 2018-01-06 | 2017-12-11 | 94% | 2018-01-25
2017-07-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 66023 | Automated Infantry Platoon Battle Course |  |  |  | 2014-07-08 | 2016-09-09 | 2017-02-17 | 99% | 2017-05-10
2017-07-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 66099 | Battalion Complex Facilities |  |  |  | 2013-07-01 | 2016-05-05 | 2017-02-23 | 98% | 2016-11-04
2018-06-30 | 2012 | Army Active | Major Military Construction | Washington | United States | 66206 | Infrastructure, Ph 1 |  |  |  | 2012-09-17 | 2017-06-10 | 2017-11-14 | 99% | 2017-11-20
2018-06-30 | 2016 | Army Active | Major Military Construction | Oklahoma | United States | 66575 | Training Support Facility |  |  |  | 2017-09-05 | 2018-11-29 | 2019-01-20 | 9%
2017-07-31 | 2011 | Army Active | Major Military Construction |  | Germany | 66595 | Barracks Complex |  |  |  | 2015-03-23 | 2017-09-28 | 2017-09-28 | 96%
2017-07-31 | 2009 | Army Active | Major Military Construction | New Jersey | United States | 66725 | Ballistic Evaluation Facility Ph 1 |  |  |  | 2012-12-04 | 2014-06-04 | 2017-07-07 | 92% | 2017-07-14
2017-07-31 | 2010 | Army Active | Major Military Construction | New Jersey | United States | 66726 | Ballistic Evaluation Facility, Ph 2 |  |  |  | 2012-12-04 | 2014-06-04 | 2017-07-07 | 98% | 2017-07-14
2017-04-30 | 2011 | Army Active | Major Military Construction |  | Germany | 66834 | Vehicle Maintenance Shop |  |  |  | 2011-12-12 | 2013-12-18 | 2016-01-15 | 97% | 2016-11-18
2018-06-30 | 2017 | Army Active | Major Military Construction | Georgia | United States | 67029 | Automated Qualification/Training Range |  |  |  | 2017-09-21 | 2019-03-15 | 2019-03-15 | 24%
2017-05-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 67116 | Aviation Battalion Complex |  |  |  | 2014-04-23 | 2016-09-06 | 2016-09-26 | 99% | 2016-10-03
2018-06-30 | 2014 | Army Active | Major Military Construction | Hawaii | United States | 67157 | Command and Control Facility - Admin |  |  |  | 2015-09-25 | 2017-12-13 | 2019-01-18 | 83%
2018-06-30 | 2012 | Army Active | Major Military Construction | Maryland | United States | 68050 | Command and Control Facility |  |  |  | 2016-02-24 | 2018-06-13 | 2018-11-30 | 51%
2016-11-30 | 2011 | Army Active | Major Military Construction |  | Germany | 68074 | Construct New ACP |  |  |  | 2014-03-05 | 2014-12-12 | 2015-01-09 | 99%
2018-06-30 | 2013 | Army Active | Major Military Construction | Texas | United States | 68530 | Barracks |  |  |  | 2015-11-18 | 2017-05-11 | 2019-02-13 | 15%
2016-11-30 | 2011 | Army Active | Major Military Construction |  | Germany | 68606 | Barracks |  |  |  | 2012-10-12 | 2014-05-25 | 2014-06-16 | 98%
2018-06-30 | 2015 | Army Active | Major Military Construction | Texas | United States | 68826 | Simulations Center |  |  |  | 2017-08-01 | 2019-09-30 | 2019-10-25 | 27%
2018-06-30 | 2011 | Army Active | Major Military Construction |  | Germany | 68866 | Sensitive Compartmented Information Fac |  |  |  | 2013-02-13 | 2015-09-19 | 2018-11-30 | 94% | 2017-10-10
2017-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 68993 | Electronics Maintenance Facility |  |  |  | 2012-08-08 | 2013-12-16 | 2016-11-12 | 99% | 2014-06-27
2017-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 69286 | Infrastructure |  |  |  | 2012-08-20 | 2013-09-13 | 2016-11-12 | 72% | 2012-10-22
2018-06-30 | 2012 | Army Active | Major Military Construction | Hawaii | United States | 69489 | Combat Aviation Brigade Complex, Ph 1 |  |  |  | 2012-07-30 | 2015-05-27 | 2018-07-25 | 92%
2018-06-30 | 2015 | Army Active | Major Military Construction | Pennsylvania | United States | 69649 | Rebuild Shop |  |  |  | 2015-11-12 | 2017-07-24 | 2018-10-06 | 98% | 2018-05-04
2018-06-30 | 2015 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility Complex |  |  |  | 2017-11-02 | 2021-11-07 | 2021-11-07 | 15%
2018-06-30 | 2017 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 2 | 76593 |  |  | 2017-11-02 | 2021-11-07 | 2021-11-07 | 15%
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 71035 | TRAINING AIDS CENTER |  |  |  | 2017-12-14 | 2019-11-12 | 2019-11-12 | 0%
2018-06-30 | 2012 | Army Active | Major Military Construction | Virginia | United States | 71149 | Road and Infrastucture Improvements |  |  |  | 2016-08-17 | 2018-08-17 | 2018-08-17 | 68%
2017-05-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 71221 | Fire Station |  |  |  | 2014-08-27 | 2016-02-18 | 2016-09-28 | 99% | 2016-10-24
2018-06-30 | 2010 | Army Active | Military Family Housing |  | Germany | 71421 | Family Housing Replacement Construction |  |  |  | 2015-04-07 | 2018-08-13 | 2018-09-29 | 70%
2018-06-30 | 2011 | Army Active | Military Family Housing |  | Germany | 71422 | Family Housing Replacement Construction |  |  |  | 2015-04-07 | 2018-07-27 | 2018-09-29 | 76%
2016-11-30 | 2011 | Army Active | Major Military Construction | New York | United States | 71472 | Brigade Complex Ph 1 |  | 9250000 | 62783 | 2011-08-05 | 2013-03-07 | 2014-07-23 | 99% | 2016-10-31
2017-07-31 | 2010 | Army Active | Major Military Construction |  | Kuwait | 71485 | APS Warehouses |  | 11339000 | 58925, 62783 | 2013-10-25 | 2015-10-30 | 2016-10-03 | 99% | 2016-10-03
2017-07-31 | 2014 | Army Active | Major Military Construction | Missouri | United States | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  |  |  | 2014-08-05 | 2016-08-04 | 2017-02-28 | 99% | 2017-03-08
2017-07-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 71675 | Flight Equipment Complex |  |  |  | 2014-01-15 | 2016-01-15 | 2017-08-11 | 98%
2018-06-30 | 2017 | Army Active | Major Military Construction | Texas | United States | 71777 | Automated Infantry Platoon Battle Course |  |  |  | 2017-11-28 | 2019-05-22 | 2019-05-22 | 35%
2018-06-30 | 2015 | Army Active | Major Military Construction | Virginia | United States | 73272 | Tactical Vehicle Hardstand |  |  |  | 2015-10-21 | 2016-10-20 | 2017-12-17 | 100% | 2017-12-18
2017-07-31 | 2014 | Army Active | Major Military Construction | Maryland | United States | 73384 | Entry Control Point |  |  |  | 2016-03-31 | 2017-03-31 | 2017-03-31 | 99% | 2017-07-01
2018-01-31 | 2015 | Army Active | Major Military Construction | Kentucky | United States | 73542 | Unmanned Aerial Vehicle Hangar |  | 3775000 | 85811, 92764 | 2015-09-04 | 2017-04-26 | 2017-10-13 | 100% | 2017-10-13
2018-04-30 | 2013 | Army Active | Unspecified Minor Military Construction | California | United States | 73738 | FIRE STATION |  |  |  | 2017-12-14 | 2018-11-28 | 2018-11-28 | 0%
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 74001 | PHYSICAL FITNESS FACILITY |  |  |  | 2017-12-14 | 2019-06-07 | 2019-06-07 | 0%
2017-07-31 | 2014 | Army Active | Major Military Construction | Texas | United States | 74638 | Control Tower |  |  |  | 2015-04-28 | 2017-01-02 | 2017-07-21 | 99% | 2017-04-20
2018-04-30 | 2017 | Army Active | Unspecified Minor Military Construction | California | United States | 74732 | Family Life Center (Chapel annex) |  |  |  | 2018-01-09 | 2019-06-13 | 2019-06-13 | 0%
2017-07-31 | 2014 | Army Active | Military Family Housing | Wisconsin | United States | 74861 | Family Housing New Construction |  |  |  | 2014-08-20 | 2016-08-09 | 2017-08-19 | 95% | 2017-07-14
2018-06-30 | 2013 | Army Active | Major Military Construction | Washington | United States | 75165 | Waste Water Treatment Plant |  |  |  | 2014-03-03 | 2016-03-02 | 2017-11-30 | 99% | 2017-10-04
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Texas | United States | 75307 | Lab and Test Building |  |  |  | 2017-11-09 | 2018-11-04 | 2018-12-03 | 20%
2018-06-30 | 2015 | Army Active | Military Family Housing | Illinois | United States | 75536 | Family Housing New Construction |  |  |  | 2016-09-13 | 2018-03-07 | 2018-08-17 | 85%
2018-06-30 | 2016 | Army Active | Military Family Housing | Illinois | United States | 75538 | Family Housing Replacement Construction |  |  |  | 2016-10-17 | 2018-04-10 | 2018-07-14 | 87%
2018-06-30 | 2017 | Army Active | Major Military Construction | Colorado | United States | 75893 | Unmanned Aerial Vehicle Hangar |  |  |  | 2017-10-25 | 2018-11-29 | 2018-11-29 | 38%
2018-06-30 | 2016 | Army Active | Major Military Construction | Alaska | United States | 75966 | Physical Readiness Training Facility |  | 1375000 | 92764 | 2016-07-28 | 2017-12-10 | 2018-02-28 | 87% | 2018-02-28
2018-06-30 | 2014 | Army Active | Major Military Construction | Kansas | United States | 76024 | Simulations Center |  |  |  | 2014-09-02 | 2018-09-24 | 2018-09-24 | 98%
2018-06-30 | 2013 | Army Active | Major Military Construction | California | United States | 76086 | Lightning Protection System |  |  |  | 2014-09-16 | 2018-05-30 | 2018-06-24 | 92%
2018-06-30 | 2015 | Army Active | Major Military Construction | California | United States | 76087 | General Purpose Maintenance Shop |  |  |  | 2015-11-30 | 2017-03-31 | 2018-06-30 | 89%
2017-07-31 | 2013 | Army Active | Major Military Construction |  | Korea, South | 76196 | Battalion Headquarters Complex |  | 9200000 | 62663 | 2013-05-14 | 2015-06-09 | 2017-04-28 | 95% | 2017-04-17
2017-07-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76586 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2017-01-13 | 97% | 2017-04-03
2017-07-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76587 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2017-01-13 | 95% | 2017-04-03
2016-10-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 76601 | Aviation Storage Hangar |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 91%
2017-07-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76767 | Aviation Unit Complex, Ph 1A |  |  |  | 2012-07-09 | 2017-01-18 | 2017-01-23 | 99% | 2017-01-23
2017-07-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76768 | Aviation Complex, Ph 1B |  | 25700000 | 49472, 68050, 71149 | 2012-11-29 | 2017-05-06 | 2017-06-22 | 99%
2018-06-30 | 2014 | Army Active | Major Military Construction | Washington | United States | 76776 | Airfield Operations Complex |  |  |  | 2015-05-18 | 2018-05-11 | 2018-10-31 | 92%
2018-06-30 | 2014 | Army Active | Major Military Construction | Washington | United States | 76777 | Aircraft Maintenance Hangar |  | 611000 | 79933 | 2014-09-23 | 2018-10-26 | 2018-11-05 | 95%
2018-06-30 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76903 | Combat Aviation Brigade Barracks |  | 5000000 | 81987 | 2014-06-26 | 2017-01-13 | 2017-12-12 | 99% | 2017-12-22
2017-07-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 77187 | Vehicle Maintenance Facility |  |  |  | 2012-06-22 | 2016-12-07 | 2017-02-26 | 98% | 2017-02-23
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77262 | Headquarters Building |  |  |  | 2014-08-21 | 2016-03-31 | 2017-07-26 | 94%
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77304 | Aircraft Maintenance Hangar |  |  |  | 2014-08-18 | 2016-08-22 | 2017-05-31 | 97% | 2017-05-31
2018-06-30 | 2015 | Army Active | Major Military Construction | Colorado | United States | 77305 | Aircraft Maintenance Hangar |  |  |  | 2015-06-16 | 2019-06-02 | 2019-07-03 | 8%
2018-06-30 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77405 | Aircraft Maintenance Hangar |  |  |  | 2014-07-22 | 2016-08-22 | 2017-11-28 | 95% | 2017-11-28
2017-07-31 | 2013 | Army Active | Major Military Construction | Georgia | United States | 77419 | Ground Source Heat Transfer System |  |  |  | 2015-01-06 | 2016-12-26 | 2017-07-21 | 97%
2017-04-30 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77885 | Runway |  |  |  | 2014-07-01 | 2015-07-01 | 2016-07-29 | 99% | 2017-04-24
2017-07-31 | 2013 | Army Active | Major Military Construction | District Of Columbia | United States | 78054 | Vehicle Storage Building, Installation |  |  |  | 2015-04-03 | 2016-09-24 | 2017-02-21 | 85% | 2017-03-31
2018-06-30 | 2014 | Army Active | Major Military Construction | Washington | United States | 78196 | Aviation Battalion Complex |  | 2726000 | 79933, 92764 | 2016-01-13 | 2018-04-05 | 2018-08-10 | 95%
2018-06-30 | 2016 | Army Active | Military Family Housing Improvement |  | Germany | 78366 | Family Housing Improvements |  |  |  | 2016-10-25 | 2017-12-09 | 2018-04-20 | 98% | 2018-04-27
2017-07-31 | 2012 | Army Active | Military Family Housing Improvement |  | Germany | 78475 | Family Housing Improvements |  |  |  | 2015-01-16 | 2016-09-27 | 2017-04-21 | 99% | 2017-06-20
2017-05-31 | 2012 | Army Active | Military Family Housing |  | Germany | 78505 | Family Housing New Construction |  |  |  | 2013-08-07 | 2015-09-14 | 2016-02-17 | 93%
2018-06-30 | 2014 | Army Active | Military Family Housing |  | Germany | 78712 | Family Housing New Construction |  |  |  | 2017-08-11 | 2019-11-25 | 2020-01-24 | 5%
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 79618 | Simulator Building |  |  |  | 2014-08-20 | 2016-02-11 | 2017-03-27 | 97% | 2017-04-13
2017-07-31 | 2012 | Army Active | Major Military Construction |  | Unspecified World Wide | 79749 | Forward Operating Site |  |  |  | 2012-07-25 | 2014-11-30 | 2017-07-15 | 91%
2017-07-31 | 2013 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks |  |  |  | 2013-08-26 | 2016-08-30 | 2017-02-07 | 98% | 2017-04-24
2017-07-31 | 2014 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 2 | 81186 |  |  | 2013-08-26 | 2016-08-30 | 2017-02-07 | 98% | 2017-04-24
2017-07-31 | 2015 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 3 | 81187 |  |  | 2013-08-26 | 2016-08-30 | 2017-02-07 | 98% | 2017-04-24
2017-07-31 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 80112 | Unmanned Aerial Vehicle Complex |  | 11900000 | 77305 | 2015-05-26 | 2016-07-19 | 2016-11-01 | 99% | 2016-11-01
2018-06-30 | 2012 | Army Active | Unspecified Minor Military Construction | Maryland | United States | 80231 | Replace Oil Water Separators |  |  |  | 2014-11-03 | 2015-11-03 | 2018-02-08 | 99% | 2018-06-08
2018-06-30 | 2013 | Army Active | Major Military Construction | New York | United States | 80246 | Aircraft Maintenance Hangar |  | 2000000 | 81987 | 2013-06-27 | 2015-12-02 | 2018-02-23 | 99% | 2018-03-15
2017-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | Virginia | United States | 80317 | WATER DISTRIBUTION LINES, POTABLE |  |  |  | 2014-01-13 | 2014-09-10 | 2016-11-30 | 97% | 2017-03-23
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 80353 | Waste/Central Hazardous Waste Facility |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 0%
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 80433 | Central Energy Plant |  |  |  | 2015-10-27 | 2016-10-26 | 2017-03-22 | 98% | 2017-03-27
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Mississippi | United States | 80666 | Precision Machine Shop |  |  |  | 2016-10-26 | 2018-04-19 | 2018-08-07 | 43%
2017-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | Hawaii | United States | 80992 | Upgrade Power Distribution |  |  |  | 2015-04-29 | 2016-10-20 | 2017-01-25 | 99% | 2017-01-25
2018-06-30 | 2014 | Army Active | Major Military Construction | Texas | United States | 81155 | Unmanned Aerial Vehicle Complex |  |  |  | 2014-12-18 | 2016-04-11 | 2018-04-20 | 100% | 2018-04-20
2018-06-30 | 2015 | Army Active | Military Family Housing |  | Korea, South | 81230 | Family Housing New Construction |  |  |  | 2015-08-19 | 2018-04-28 | 2018-07-08 | 75%
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Louisiana | United States | 81234 | Fire Station Addition |  |  |  | 2017-07-28 | 2018-07-28 | 2018-07-28 | 7%
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81242 | General Purpose Maintenance Shop |  |  |  | 2015-10-28 | 2016-10-27 | 2018-09-07 | 87%
2018-06-30 | 2017 | Army Active | Major Military Construction | Alaska | United States | 81347 | Unmanned Aerial Vehicle Hangar |  |  |  | 2017-04-19 | 2018-11-15 | 2018-11-15 | 44%
2018-06-30 | 2015 | Army Active | Major Military Construction | New York | United States | 81349 | Unmanned Aerial Vehicle Hangar |  | 4275000 | 85811 | 2015-06-22 | 2016-12-18 | 2017-12-31 | 99%
2017-07-31 | 2015 | Army Active | Major Military Construction | Colorado | United States | 81357 | Unmanned Aerial Vehicle Hangar |  |  |  | 2014-07-01 | 2017-01-18 | 2017-06-16 | 94% | 2017-06-29
2018-06-30 | 2015 | Army Active | Major Military Construction | California | United States | 81372 | Unmanned Aerial Vehicle Hangar |  |  |  | 2015-11-18 | 2017-11-07 | 2018-03-16 | 95%
2017-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81424 | Tracking Equipment Support Fac |  |  |  | 2015-11-10 | 2017-02-02 | 2017-03-24 | 99% | 2017-04-23
2018-06-30 | 2016 | Army Active | Military Family Housing |  | Korea, South | 81427 | Family Housing New Construction |  |  |  | 2016-09-29 | 2019-02-24 | 2019-03-01 | 24%
2018-06-30 | 2017 | Army Active | Military Family Housing |  | Korea, South | 81428 | Family Housing New Construction |  |  |  | 2017-09-08 | 2020-02-25 | 2020-02-25 | 1%
2017-07-31 | 2013 | Army Active | Unspecified Minor Military Construction |  | Marshall Islands | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  |  |  | 2014-10-28 | 2015-10-23 | 2016-12-01 | 62% | 2017-01-01
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | New Mexico | United States | 81658 | Organizational Storage Building |  |  |  | 2017-01-31 | 2017-10-28 | 2017-11-27 | 97% | 2017-12-27
2018-06-30 | 2014 | Army Active | Major Military Construction |  | Japan | 81987 | Company Operations Complex |  |  |  | 2017-11-02 | 2019-11-22 | 2019-11-22 | 5%
2018-06-30 | 2016 | Army Active | Unspecified Minor Military Construction | New York | United States | 82094 | CID Field Ops Facility |  |  |  | 2017-10-18 | 2019-04-11 | 2019-04-11 | 3%
2017-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | Oklahoma | United States | 82394 | Decontamination Facility |  |  |  | 2016-02-18 | 2017-02-12 | 2017-07-12 | 95%
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Kentucky | United States | 85185 | Contigency Operating Location SABER |  |  |  | 2016-10-26 | 2018-03-20 | 2018-01-11 | 99% | 2018-01-11
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 85260 | Secure Operations Center |  |  |  | 2014-11-05 | 2015-11-05 | 2016-01-13 | 99% | 2017-01-20
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 85683 | UPH Laundry Building, Detached |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 0%
2018-06-30 | 2016 | Army Active | Major Military Construction | Colorado | United States | 85710 | Rotary Wing Taxiway |  |  |  | 2017-02-28 | 2018-08-22 | 2018-08-29 | 57%
2018-06-30 | 2015 | Army Active | Major Military Construction |  | Romania | 85711 | ERI: Multi Modal Improvements |  |  |  | 2017-12-15 | 2020-12-09 | 2020-12-09 | 3%
2018-04-30 | 2016 | Army Active | Unspecified Minor Military Construction | California | United States | 85808 | Military Equipment Parking |  |  |  | 2017-05-08 | 2018-05-08 | 2018-05-08 | 66%
2018-06-30 | 2016 | Army Active | Major Military Construction | Georgia | United States | 85811 | Command and Control Facility |  |  |  | 2016-10-31 | 2018-07-23 | 2019-01-11 | 55%
2018-06-30 | 2014 | Army Active | Unspecified Minor Military Construction |  | Germany | 85817 | CANTONMENT AREA ROADS, PAVED |  |  |  | 2016-04-07 | 2016-08-25 | 2016-11-15 | 99%
2018-06-30 | 2017 | Army Active | Major Military Construction | Georgia | United States | 85818 | Cyber Protection Team Ops Facility |  |  |  | 2017-04-17 | 2018-10-09 | 2019-01-26 | 37%
2018-06-30 | 2015 | Army Active | Major Military Construction |  | Romania | 86404 | ERI: Hazardous Cargo Ramp |  |  |  | 2017-10-24 | 2019-12-13 | 2019-12-13 | 1%
2018-06-30 | 2015 | Army Active | Major Military Construction |  | Romania | 86405 | ERI: Fuel Storage Capacity |  |  |  | 2017-09-29 | 2020-11-03 | 2020-11-03 | 1%
2018-06-30 | 2016 | Army Active | Major Military Construction | Maryland | United States | 86408 | Access Control Point |  |  |  | 2016-11-17 | 2018-12-07 | 2018-12-07 | 11%
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Colorado | United States | 86573 | Wash Platform |  |  |  | 2016-08-03 | 2018-01-25 | 2018-03-26 | 100% | 2018-03-26
2018-06-30 | 2017 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction |  |  |  | 2017-10-31 | 2020-11-12 | 2020-11-24 | 3%
2018-06-30 | 2017 | Army Active | Major Military Construction |  | Germany | 86745 | Controlled Humidity Warehouse |  |  |  | 2017-10-13 | 2018-01-11 | 2018-11-07 | 3%
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 86787 | CIDC Field Operations Building |  |  |  | 2017-07-21 | 2018-07-21 | 2018-08-04 | 25%
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction |  | Honduras | 86859 | Continuing Education Facility |  |  |  | 2016-11-22 | 2018-04-26 | 2018-08-22 | 61%
2018-06-30 | 2016 | Army Active | Unspecified Minor Military Construction |  | Marshall Islands | 86914 | Storage Fuel Tank Repair |  |  |  | 2017-10-11 | 2018-12-12 | 2018-12-12 | 3%
2018-06-30 | 2017 | Army Active | Unspecified Minor Military Construction |  | Honduras | 87309 | Chapel |  |  |  | 2017-12-06 | 2019-08-07 | 2019-08-07 | 13%
2018-06-30 | 2016 | Army Active | Unspecified Minor Military Construction | Washington | United States | 87419 | MEDEVAC Aircraft Maintenance Hangar |  |  |  | 2018-01-30 | 2018-09-27 | 2018-09-27 | 39%
2018-06-30 | 2016 | Army Active | Unspecified Minor Military Construction | New York | United States | 87892 | Fire Suppression & Mass Notification Sys |  |  |  | 2017-10-23 | 2019-04-26 | 2019-04-29 | 13%
2018-06-30 | 2016 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 88047 | Supply Support Activity, CAB |  |  |  | 2018-03-19 | 2019-03-19 | 2019-03-22 | 4%
2018-06-30 | 2017 | Army Active | Unspecified Minor Military Construction | New Hampshire | United States | 88369 | Transformers |  |  |  | 2017-10-13 | 2018-10-13 | 2018-10-13 | 20%
2018-06-30 | 2016 | Army Active | Unspecified Minor Military Construction | Missouri | United States | 88386 | CIDC Field Operations Building |  |  |  | 2017-09-20 | 2018-09-20 | 2018-10-18 | 23%
2018-03-31 | 2017 | Army Active | Unspecified Minor Military Construction |  | Puerto Rico | 88722 | Fire Station |  |  |  | 2017-05-19 | 2018-07-13 | 2018-06-13 | 3%
2017-07-31 | 2016 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 89734 | Administrative Building, General Purpose |  |  |  | 2016-10-18 | 2017-05-16 | 2017-05-16 | 99%
2018-06-30 | 2015 | Army Active | Major Military Construction | Kentucky | United States | 8984 | Shipping and Receiving Building |  | 650000 | 92764 | 2016-10-18 | 2018-04-11 | 2018-07-19 | 89%
2018-07-13 | 2013 | Army National Guard | Unspecified Minor Military Construction | Alabama | United States | 011007 | National Guard Readiness Center, Add/Alt |  |  |  | 2013-12-31 | 2014-10-01 | 2017-03-01 | 99% | 2017-03-01
2018-01-12 | 2014 | Army National Guard | Major Military Construction | Alabama | United States | 011014 | National Guard Readiness Center Add/Alt |  |  |  | 2014-10-07 | 2015-12-10 | 2016-04-01 | 100% | 2016-09-01
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Alabama | United States | 011317 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-11-07 | 2017-09-15 | 2018-09-02 | 96% | 2018-09-02
2018-07-13 | 2015 | Army National Guard | Unspecified Minor Military Construction | Arizona | United States | 040730 | Water/Supply Treatment Building |  |  |  | 2016-11-07 | 2017-06-30 | 2017-06-30 | 1% | 2017-06-30
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Arkansas | United States | 050182 | Scout REECE Gunnery Complex |  |  |  | 2014-12-01 | 2016-12-01 | 2018-07-30 | 97% | 2016-12-01
2018-07-13 | 2016 | Army National Guard | Unspecified Minor Military Construction | Colorado | United States | 080213 | Airborne Equip/Parachute Repair Shop |  |  |  | 2018-05-14 | 2018-12-31 | 2018-12-31 | 1% | 2018-12-31
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Connecticut | United States | 090071 | Ready Building (CST-WMD) |  |  |  | 2016-11-26 | 2018-04-06 | 2018-04-06 | 90% | 2018-04-06
2018-05-15 | 2014 | Army National Guard | Unspecified Minor Military Construction | Connecticut | United States | 090088 | Storage Building General Purpose, Installation |  |  |  | 2015-12-01 | 2016-11-30 | 2016-12-31 | 100% | 2016-12-31
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Delaware | United States | 100082 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-10-01 | 2017-08-25 | 2018-06-29 | 93% | 2017-08-25
2018-07-13 | 2013 | Army National Guard | Major Military Construction | Florida | United States | 120102 | Readiness Center |  |  |  | 2014-01-21 | 2015-07-26 | 2018-07-13 | 99% | 2016-10-04
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Florida | United States | 120173 | National Guard Readiness Center |  |  |  | 2016-11-01 | 2018-03-31 | 2018-09-30 | 59% | 2018-04-27
2018-07-13 | 2015 | Army National Guard | Unspecified Minor Military Construction | Florida | United States | 120212 | Organizational Vehicle Parking, Paved |  |  |  | 2018-02-15 | 2018-06-30 | 2018-12-15 | 1% | 2018-06-30
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Georgia | United States | 130130 | Tactical Aerial Unmanned Systems |  |  |  | 2017-04-30 | 2017-11-03 | 2017-11-03 | 59% | 2017-11-03
2017-08-07 | 2014 | Army National Guard | Unspecified Minor Military Construction | Guam | Guam | 140055 | Aircraft Maintenance Bay |  |  |  | 2016-10-24 | 2017-09-29 | 2017-09-29 | 98% | 2017-09-29
2018-07-13 | 2013 | Army National Guard | Major Military Construction | Hawaii | United States | 150023 | Army Aviation Support Facility Ph1 |  | 1001 | 371301 | 2014-11-12 | 2016-11-01 | 2017-10-09 | 99% | 2017-10-09
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Hawaii | United States | 150035 | Combined Support Maintenance Shop |  |  |  | 2018-03-12 | 2019-06-30 | 2019-06-30 | 1% | 2019-06-30
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Illinois | United States | 170033 | National Guard Readiness Center |  |  |  | 2014-08-14 | 2016-10-01 | 2017-10-01 | 99% | 2017-10-01
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Illinois | United States | 170127 | Aircraft Maintenance Hangar |  |  |  | 2014-08-14 | 2017-10-01 | 2017-11-28 | 99% | 2017-10-01
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Illinois | United States | 171001 | Basic 10M-25M Firing Range (Zero) |  |  |  | 2016-11-01 | 2018-05-11 | 2018-05-11 | 95% | 2018-05-11
2018-07-13 | 2015 | Army National Guard | Unspecified Minor Military Construction | Indiana | United States | 180269 | Vehicle Storage Building, Installation |  |  |  | 2017-09-05 | 2018-03-04 | 2018-07-20 | 98% | 2018-10-27
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Iowa | United States | 190025 | National Guard Readiness Center |  |  |  | 2018-04-02 | 2019-06-28 | 2019-06-28 | 8% | 2019-06-28
2018-01-12 | 2016 | Army National Guard | Unspecified Minor Military Construction | Iowa | United States | 190192 | Combined Support Maintenance Shop Add/Alt |  |  |  | 2016-10-24 | 2017-07-31 | 2017-12-01 | 100% | 2017-12-01
2017-09-07 | 2016 | Army National Guard | Major Military Construction | Kansas | United States | 200112 | Automated Combat Pistol/Military Police Firearms Qualification Course |  |  |  | 2016-11-01 | 2017-03-01 | 2017-06-24 | 80% | 1996-01-01
2017-09-07 | 2016 | Army National Guard | Major Military Construction | Kansas | United States | 200113 | Modified Record Fire Range |  |  |  | 2016-11-01 | 2017-03-01 | 2017-06-24 | 80% | 2009-01-01
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Kansas | United States | 200117 | Geothermal and Occupancy Sensors |  |  |  | 2017-10-09 | 2018-09-28 | 2018-11-30 | 90% | 2018-03-01
2018-01-12 | 2013 | Army National Guard | Major Military Construction | Kentucky | United States | 210001 | Army Aviation Support Facility |  | 3830000 | 371301 | 2013-07-08 | 2014-10-01 | 2017-12-19 | 100% | 2015-10-21
2018-07-13 | 2012 | Army National Guard | Major Military Construction | Maine | United States | 230046 | Readiness Center |  |  |  | 2012-09-26 | 2014-07-11 | 2018-08-30 | 99% | 2015-08-28
2018-07-13 | 2015 | Army National Guard | Major Military Construction | Maine | United States | 230113 | National Guard Reserve Center |  |  |  | 2015-08-20 | 2017-08-03 | 2018-12-30 | 98% | 2018-04-02
2018-07-13 | 2015 | Army National Guard | Major Military Construction | Maryland | United States | 240165 | National Guard Readiness Center |  |  |  | 2015-10-19 | 2017-10-29 | 2018-08-15 | 99% | 2018-04-15
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Maryland | United States | 240173 | National Guard Readiness Center |  |  |  | 2017-05-15 | 2018-04-06 | 2019-01-25 | 45% | 2019-01-25
2018-07-13 | 2013 | Army National Guard | Major Military Construction | Massachusetts | United States | 250065 | Unit Training Equipment Site |  |  |  | 2014-04-07 | 2015-07-30 | 2017-05-17 | 84% | 2015-07-30
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Massachusetts | United States | 250095 | Enlisted Barracks, Transient Training Addition |  |  |  | 2014-09-15 | 2016-11-01 | 2017-01-16 | 99% | 2016-11-01
2018-07-13 | 2013 | Army National Guard | Unspecified Minor Military Construction | Massachusetts | United States | 250196 | Water Well, Non-Potable |  |  |  | 2013-06-03 | 2013-12-01 | 2013-12-01 | 95% | 2013-12-02
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Michigan | United States | 260051 | Enlisted Barracks, Transient Training |  |  |  | 2014-08-11 | 2016-10-01 | 2016-10-01 | 97% | 2016-10-01
2018-07-13 | 2015 | Army National Guard | Unspecified Minor Military Construction | Michigan | United States | 260222 | Ammunition Hut, Installation |  |  |  | 2019-10-04 | 2019-10-04 | 2019-10-04 | 1% | 2019-10-04
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Minnesota | United States | 270014 | National Guard Readiness Center |  |  |  | 2014-10-22 | 2016-04-15 | 2017-12-01 | 100% | 2017-02-03
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Minnesota | United States | 270109 | Transient Training Officer Quarters |  | 8000000 | 490706 | 2018-03-26 | 2019-05-31 | 2019-05-31 | 15% | 2019-05-31
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Minnesota | United States | 270240 | Enlisted Barracks, Transient Training |  | 17000000 | 200102 and 290176 | 2018-03-26 | 2019-05-31 | 2019-05-31 | 24% | 2019-05-31
2018-07-13 | 2017 | Army National Guard | Unspecified Minor Military Construction | Minnesota | United States | 270281 | Battalion Headquarters Bldg, Transient Training |  |  |  | 2018-03-26 | 2019-05-31 | 2019-05-31 | 38% | 2019-05-31
2018-07-13 | 2017 | Army National Guard | Unspecified Minor Military Construction | Minnesota | United States | 270282 | Vehicle Maintenance Shop, Transient Training |  |  |  | 2018-03-26 | 2019-05-31 | 2019-05-31 | 44% | 2019-05-31
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Mississippi | United States | 280327 | Aviation Classification and Repair Activity Depot |  |  |  | 2016-11-28 | 2019-06-28 | 2019-08-25 | 51% | 2019-08-25
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Mississippi | United States | 280423 | Water Supply/Treatment Building, Potable |  |  |  | 2014-08-27 | 2016-11-30 | 2016-11-30 | 71% | 2016-11-30
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Mississippi | United States | 281501 | National Guard Readiness Center |  |  |  | 2017-03-10 | 2018-02-09 | 2018-09-22 | 51% | 2018-09-22
2018-01-12 | 2015 | Army National Guard | Major Military Construction | Montana | United States | 300128 | National Guard Readiness Center Add/Alt |  |  |  | 2015-05-13 | 2017-05-13 | 2017-11-29 | 100% | 2017-06-28
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Nevada | United States | 320075 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-10-24 | 2017-06-23 | 2017-10-31 | 99% | 2017-10-31
2018-07-13 | 2012 | Army National Guard | Unspecified Minor Military Construction | Nevada | United States | 320141 | Clark County Armory, Add/Alt |  |  |  | 2016-04-04 | 2017-06-23 | 2017-06-23 | 48% | 2016-07-23
2018-07-13 | 2017 | Army National Guard | Major Military Construction | New Hampshire | United States | 330019 | National Guard Vehicle Maintenance Shop |  |  |  | 2017-04-05 | 2018-12-14 | 2018-12-14 | 98% | 2018-12-14
2018-07-13 | 2017 | Army National Guard | Major Military Construction | New Hampshire | United States | 330425 | National Guard Vehicle Maintenance Shop |  |  |  | 2017-04-19 | 2018-12-14 | 2018-12-14 | 33% | 2018-12-14
2018-07-13 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340110 | Regional Training Institute |  |  |  | 2014-10-15 | 2016-02-12 | 2017-09-06 | 99% | 2017-09-06
2018-07-13 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340124 | National Guard Vehicle Maintenance Shop |  |  |  | 2016-10-21 | 2017-09-23 | 2018-08-13 | 76% | 2018-08-13
2018-07-13 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340126 | Troop Dispensary/Health Clinic |  |  |  | 2016-08-01 | 2017-07-06 | 2018-05-13 | 99% | 2018-05-13
2018-07-13 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340127 | Engineering/Housing Maintenance Shop |  |  |  | 2016-10-21 | 2017-09-23 | 2018-08-13 | 76% | 2018-08-13
2018-07-13 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340128 | General Instruction Building |  |  |  | 2016-08-01 | 2017-07-06 | 2018-05-13 | 99% | 2018-05-13
2018-07-13 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340129 | Power Plant Building |  |  |  | 2016-10-14 | 2017-03-03 | 2017-03-13 | 98% | 2017-03-13
2018-07-13 | 2015 | Army National Guard | Major Military Construction | New Mexico | United States | 350029 | National Guard Readiness Center Add/Alt |  |  |  | 2016-06-20 | 2018-01-01 | 2018-07-22 | 75% | 2018-06-14
2018-07-13 | 2013 | Army National Guard | Major Military Construction | New York | United States | 360139 | Combined Support Maintenance Shop |  |  |  | 2016-04-04 | 2017-12-30 | 2018-06-01 | 100% | 2018-06-01
2018-07-13 | 2014 | Army National Guard | Major Military Construction | New York | United States | 360161 | National Guard Readiness Center Alteration |  |  |  | 2014-10-20 | 2016-09-29 | 2018-09-30 | 94% | 2018-10-01
2017-09-07 | 2013 | Army National Guard | Major Military Construction | New York | United States | 361103 | Access Control Point |  |  |  | 2016-03-07 | 2016-11-05 | 2017-07-14 | 99% | 2017-01-31
2018-07-13 | 2017 | Army National Guard | Major Military Construction | North Carolina | United States | 371301 | National Guard Readiness Center |  |  |  | 2017-11-15 | 2019-08-17 | 2019-08-17 | 32% | 2019-12-15
2018-07-13 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop |  |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 99% | 2017-07-18
2018-07-13 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 135 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 99% | 2017-07-18
2018-07-13 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 136 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 99% | 2017-07-18
2018-07-13 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 137 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 99% | 2017-07-18
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Ohio | United States | 390290 | Modified Record Fire Range |  |  |  | 2016-06-06 | 2018-05-18 | 2018-05-18 | 82% | 2018-08-01
2017-09-07 | 2014 | Army National Guard | Major Military Construction | Ohio | United States | 390292 | Sanitary Sewer |  |  |  | 2014-09-08 | 2016-07-02 | 2016-10-15 | 98% | 2016-10-15
2018-07-13 | 2013 | Army National Guard | Major Military Construction | Oklahoma | United States | 400066 | Operations Readiness Training Complex |  |  |  | 2013-10-25 | 2014-10-01 | 2017-09-30 | 94% | 2017-10-15
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Oklahoma | United States | 400601 | National Guard Readiness Center |  |  |  | 2017-10-16 | 2019-02-08 | 2019-02-08 | 1% | 2019-02-08
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Oregon | United States | 410301 | National Guard/Reserve Center Building Add/Alt (JFHQ) |  |  |  | 2016-11-29 | 2018-01-10 | 2018-06-30 | 92% | 2018-01-10
2018-07-13 | 2015 | Army National Guard | Major Military Construction | Oregon | United States | 411301 | Exterior/Interior Lighting Retrofit, Multiple Sites |  |  |  | 2017-06-25 | 2017-12-29 | 2018-12-29 | 30% | 2018-12-29
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420051 | Aircraft Maintenance Instructional Building |  |  |  | 2014-10-20 | 2016-04-22 | 2017-09-15 | 99% | 2017-09-15
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420354 | National Guard Readiness Center |  |  |  | 2017-10-16 | 2019-01-03 | 2019-01-03 | 45% | 2019-01-03
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420502 | Access Control Building |  |  |  | 2018-05-12 | 2018-10-26 | 2018-10-26 | 1% | 2018-10-26
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420522 | Training Aids Center |  |  |  | 2017-11-20 | 2018-08-24 | 2019-05-28 | 25% | 2018-08-24
2017-11-13 | 2013 | Army National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | 420533 | Sanitary Sewer |  |  |  | 2016-01-13 | 2016-06-17 | 2017-08-07 | 100% | 2017-09-07
2018-07-13 | 2015 | Army National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | 420586 | Tactical Unmanned Aerial Vehicle Hangar Addition |  |  |  | 2017-09-21 | 2018-02-28 | 2018-10-02 | 48% | 2018-10-02
2017-08-07 | 2013 | Army National Guard | Major Military Construction | Puerto Rico | Puerto Rico | 430803 | Readiness Center |  |  |  | 2015-10-19 | 2017-12-01 | 2018-04-08 | 50% | 2018-04-08
2018-01-12 | 2011 | Army National Guard | Major Military Construction | Rhode Island | United States | 440009 | United States Property and Fiscal Office |  |  |  | 2012-10-08 | 2014-04-17 | 2015-03-31 | 99% | 2015-01-31
2018-01-12 | 2013 | Army National Guard | Unspecified Minor Military Construction | Rhode Island | United States | 440053 | Access Control Point |  |  |  | 2015-10-01 | 2016-04-01 | 2016-12-15 | 98% | 2016-10-31
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Rhode Island | United States | 440064 | National Guard/Reserve Center Building (JFHQ) |  |  |  | 2017-10-02 | 2020-02-28 | 2020-02-28 | 27% | 2020-02-28
2018-05-15 | 2014 | Army National Guard | Major Military Construction | South Carolina | United States | 450131 | National Guard Vehicle Maintenance Shop |  |  |  | 2014-03-26 | 2017-04-06 | 2018-02-14 | 100% | 2017-04-06
2018-05-15 | 2014 | Army National Guard | Major Military Construction | South Carolina | United States | 450283 | National Guard Readiness Center |  |  |  | 2014-03-26 | 2017-04-06 | 2018-01-31 | 100% | 2017-05-06
2018-07-13 | 2014 | Army National Guard | Major Military Construction | Texas | United States | 480243 | Armed Forces Reserve Center |  |  |  | 2016-04-13 | 2017-06-09 | 2018-08-03 | 90% | 2017-07-08
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Utah | United States | 490601 | National Guard Readiness Center |  |  |  | 2017-10-19 | 2019-04-03 | 2019-04-12 | 40% | 2020-05-01
2018-05-15 | 2016 | Army National Guard | Major Military Construction | Vermont | United States | 500079 | National Guard Vehicle Maintenance Shop Addition |  |  |  | 2016-04-11 | 2017-03-31 | 2017-03-31 | 100% | 2017-03-31
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Virginia | United States | 510065 | National Guard/Reserve Center Building (JFHQ) |  |  |  | 2016-08-15 | 2018-03-18 | 2018-07-15 | 98% | 2018-05-25
2018-05-15 | 2013 | Army National Guard | Major Military Construction | Washington | United States | 530015 | Readiness Center |  | 2183000 | 371301 | 2013-09-23 | 2015-08-20 | 2016-03-10 | 100% | 2015-08-27
2017-11-13 | 2013 | Army National Guard | Major Military Construction | Washington | United States | 530035 | National Guard Readiness Center |  |  |  | 2014-10-06 | 2016-06-30 | 2016-11-06 | 100% | 2017-03-01
2018-07-13 | 2016 | Army National Guard | Major Military Construction | Washington | United States | 530041 | Enlisted Barracks, Transient Training |  |  |  | 2018-09-17 | 2020-04-17 | 2020-04-17 | 1% | 2020-04-17
2018-03-15 | 2013 | Army National Guard | Major Military Construction | Wisconsin | United States | 550142 | Field Maintenance Shop |  |  |  | 2013-10-28 | 2014-10-01 | 2015-06-15 | 100% | 2014-10-01
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Wyoming | United States | 560060 | General Instruction Building |  |  |  | 2017-06-30 | 2019-08-30 | 2019-04-02 | 29% | 2019-04-02
2018-07-13 | 2017 | Army National Guard | Major Military Construction | Wyoming | United States | 560084 | National Guard Readiness Center |  |  |  | 2017-06-01 | 2018-04-30 | 2018-09-01 | 61% | 2018-09-01
2018-06-30 | 2016 | Army Reserve | Major Military Construction |  | Puerto Rico | 58405 | Access Control Point |  |  |  | 2017-06-23 | 2019-05-04 | 2019-07-21 | 10%
2017-07-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 65277 | Consolidated Dining Facility |  |  |  | 2014-04-23 | 2015-09-30 | 2017-03-21 | 97% | 2017-03-29
2017-07-31 | 2012 | Army Reserve | Major Military Construction | North Carolina | United States | 67466 | Army Reserve Center/Land |  |  |  | 2012-10-10 | 2014-03-19 | 2017-03-22 | 93% | 2017-03-29
2018-06-30 | 2015 | Army Reserve | Major Military Construction | Wisconsin | United States | 67567 | Access Control Point/Mail/Freight Center |  |  |  | 2017-06-02 | 2018-11-24 | 2018-11-24 | 57%
2017-07-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 67652 | Army Reserve Center |  |  |  | 2015-04-24 | 2017-02-12 | 2017-05-30 | 98% | 2017-05-30
2017-07-31 | 2013 | Army Reserve | Major Military Construction | Illinois | United States | 67659 | Army Reserve Center |  |  |  | 2014-01-13 | 2015-11-04 | 2016-11-28 | 99% | 2017-01-05
2018-06-30 | 2015 | Army Reserve | Major Military Construction | New York | United States | 67661 | Army Reserve Center/AMSA |  |  |  | 2016-04-07 | 2018-03-08 | 2018-06-29 | 98%
2018-06-30 | 2014 | Army Reserve | Major Military Construction | Maryland | United States | 67663 | Army Reserve Center/Land |  |  |  | 2015-10-07 | 2017-09-06 | 2018-10-12 | 80%
2018-06-30 | 2012 | Army Reserve | Major Military Construction | Kansas | United States | 67681 | Army Reserve Center/Land |  |  |  | 2016-10-12 | 2018-01-05 | 2018-04-11 | 98% | 2018-04-11
2018-06-30 | 2014 | Army Reserve | Major Military Construction | New York | United States | 67690 | Army Reserve Center |  |  |  | 2017-06-29 | 2019-06-19 | 2020-01-14 | 14%
2018-06-30 | 2013 | Army Reserve | Major Military Construction | Maryland | United States | 67705 | Army Reserve Center |  |  |  | 2015-10-08 | 2017-09-07 | 2018-10-11 | 38% | 2017-12-07
2018-06-30 | 2012 | Army Reserve | Major Military Construction | Massachusetts | United States | 67709 | Army Reserve Center/Land |  |  |  | 2016-09-19 | 2018-03-23 | 2018-04-30 | 99% | 2018-06-20
2017-07-31 | 2013 | Army Reserve | Major Military Construction | Washington | United States | 67715 | Army Reserve Center |  |  |  | 2013-07-11 | 2016-01-15 | 2017-05-31 | 99% | 2017-05-31
2018-06-30 | 2013 | Army Reserve | Major Military Construction | Maryland | United States | 68077 | Add/Alt Army Reserve Center |  | 5455000 | 69562 | 2014-07-30 | 2016-05-30 | 2018-03-19 | 98% | 2017-12-18
2017-07-31 | 2011 | Army Reserve | Major Military Construction | Texas | United States | 69421 | Army Reserve Center/Land |  |  |  | 2012-08-21 | 2014-03-21 | 2017-08-30 | 84%
2018-06-30 | 2011 | Army Reserve | Major Military Construction | Virginia | United States | 69562 | Army Reserve Center |  |  |  | 2015-01-23 | 2017-05-10 | 2018-08-19 | 87%
2018-06-30 | 2010 | Army Reserve | Major Military Construction | Pennsylvania | United States | 69652 | Army Reserve Center/Land |  |  |  | 2012-04-03 | 2014-02-12 | 2017-10-27 | 99% | 2014-03-13
2018-06-30 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 71035 | TRAINING AIDS CENTER |  |  |  | 2017-12-14 | 2019-11-12 | 2019-11-12 | 0%
2018-06-30 | 2017 | Army Reserve | Major Military Construction | California | United States | 71036 | Emergency Services Center |  |  |  | 2018-03-27 | 2019-09-18 | 2019-09-18 | 4%
2017-07-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 71482 | ORTC |  |  |  | 2014-03-19 | 2016-05-17 | 2017-03-17 | 93% | 2017-03-17
2017-07-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71768 | Automated Multipurpose Machine Gun (MPMG) |  |  |  | 2015-11-19 | 2017-05-12 | 2017-05-15 | 98% | 2017-05-15
2017-07-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71769 | Modified Record Fire Range |  |  |  | 2014-10-17 | 2016-04-09 | 2016-10-18 | 99% | 2016-10-18
2017-07-31 | 2014 | Army Reserve | Major Military Construction | North Carolina | United States | 71900 | Army Reserve Center |  | 1700000 | 71720 | 2014-12-02 | 2016-11-01 | 2017-03-15 | 99% | 2017-03-15
2018-06-30 | 2015 | Army Reserve | Major Military Construction | California | United States | 71901 | Army Reserve Center/AMSA |  |  |  | 2016-03-02 | 2018-02-20 | 2018-10-09 | 78%
2018-06-30 | 2014 | Army Reserve | Major Military Construction | California | United States | 71903 | Army Reserve Center |  |  |  | 2016-11-28 | 2018-07-01 | 2018-10-01 | 67%
2017-07-31 | 2013 | Army Reserve | Major Military Construction | Wisconsin | United States | 72088 | ECS TEMF |  | 5455000 | 69562 | 2013-07-08 | 2016-12-12 | 2017-07-21 | 99% | 2017-07-21
2018-06-30 | 2014 | Army Reserve | Major Military Construction | California | United States | 72284 | TASS Training Center (TTC) |  |  |  | 2014-10-20 | 2016-05-22 | 2019-04-13 | 56%
2017-07-31 | 2015 | Army Reserve | Major Military Construction | Virginia | United States | 72291 | TASS Training Center |  |  |  | 2015-10-19 | 2017-08-28 | 2017-09-16 | 92%
2018-06-30 | 2013 | Army Reserve | Unspecified Minor Military Construction | California | United States | 73738 | FIRE STATION |  |  |  | 2017-12-14 | 2018-11-28 | 2018-11-28 | 1%
2018-06-30 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 74001 | PHYSICAL FITNESS FACILITY |  |  |  | 2017-12-14 | 2019-06-07 | 2019-06-07 | 1%
2018-06-30 | 2017 | Army Reserve | Unspecified Minor Military Construction | California | United States | 74732 | Family Life Center (Chapel annex) |  |  |  | 2018-01-09 | 2019-06-13 | 2019-06-13 | 0%
2018-06-30 | 2017 | Army Reserve | Major Military Construction | Arizona | United States | 77134 | Army Reserve Center |  |  |  | 2018-05-25 | 2020-05-14 | 2020-05-14 | 3%
2018-06-30 | 2015 | Army Reserve | Major Military Construction | New Jersey | United States | 77151 | Army Reserve Center |  |  |  | 2016-10-13 | 2018-09-13 | 2019-02-22 | 34%
2018-06-30 | 2016 | Army Reserve | Major Military Construction | Virginia | United States | 77186 | ECS Modified TEMF / Warehouse |  |  |  | 2017-08-01 | 2019-08-31 | 2019-08-31 | 9%
2018-06-30 | 2015 | Army Reserve | Major Military Construction | Illinois | United States | 77228 | Army Reserve Center |  |  |  | 2017-06-14 | 2019-04-25 | 2019-06-05 | 15%
2018-06-30 | 2018 | Army Reserve | Major Military Construction | Wisconsin | United States | 79003 | AT/MOB Dining Facility-1428 PN |  |  |  | 2018-06-20 | 2020-01-21 | 2020-01-21 | 0%
2018-06-30 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 80353 | Waste/Central Hazardous Waste Facility |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 1%
2018-06-30 | 2017 | Army Reserve | Major Military Construction | Wisconsin | United States | 80684 | AT/MOB Dining Facility |  |  |  | 2017-12-06 | 2019-10-17 | 2019-10-17 | 8%
2017-07-31 | 2015 | Army Reserve | Major Military Construction | Colorado | United States | 81959 | Training Building Addition |  |  |  | 2015-08-07 | 2016-12-09 | 2017-05-23 | 89% | 2017-05-23
2018-06-30 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 85683 | UPH Laundry Building, Detached |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 1%
2018-06-30 | 2016 | Army Reserve | Unspecified Minor Military Construction | California | United States | 85808 | Military Equipment Parking |  |  |  | 2017-05-08 | 2018-05-08 | 2018-05-08 | 99% | 2018-05-08
2018-06-30 | 2015 | Army Reserve | Major Military Construction | California | United States | 85812 | Army Reserve Center |  |  |  | 2015-11-02 | 2017-10-02 | 2018-05-22 | 99% | 2018-05-22
2018-06-30 | 2016 | Army Reserve | Major Military Construction | Florida | United States | 85813 | AR Center/ AS Facility |  |  |  | 2017-11-03 | 2019-10-04 | 2019-10-04 | 14%
2018-06-30 | 2017 | Army Reserve | Major Military Construction | California | United States | 86521 | Transient Training Barracks |  |  |  | 2017-11-07 | 2019-05-01 | 2019-05-01 | 20%
2018-06-30 | 2016 | Army Reserve | Major Military Construction | New York | United States | 86814 | Organizational Maintenance Shop |  |  |  | 2017-10-18 | 2018-10-18 | 2019-02-18 | 34%
2018-06-30 | 2016 | Army Reserve | Major Military Construction | California | United States | 86882 | Army Reserve Center |  |  |  | 2017-12-28 | 2019-12-18 | 2019-12-18 | 4%
2018-06-30 | 2017 | Army Reserve | Unspecified Minor Military Construction |  | Puerto Rico | 88722 | Fire Station |  |  |  | 2017-05-19 | 2018-07-13 | 2018-06-13 | 14%
2018-06-30 | 2017 | Army Reserve | Major Military Construction | Virginia | United States | 88733 | AMSA/OMS |  |  |  | 2017-06-29 | 2018-12-06 | 2019-02-24 | 18%
2017-11-23 | 2016 | DLA Defense Automation and Production Service | Major Military Construction | Virginia | United States | DSFF1501 | DLA Visitor Control Center, Ft. Belvoir |  |  |  | 2017-03-01 | 2018-01-31 | 2018-02-14 | 60%
2017-11-23 | 2016 | DLA Defense Automation and Production Service | Major Military Construction | Virginia | United States | DESC1607 | Replace Fuel Pier and Distribution Facility, Langley AFB, VA |  |  |  | 2016-10-12 | 2019-10-12 | 2019-12-12 | 36%
2018-07-31 | 2016 | DLA Defense Automation and Production Service | Major Military Construction | Virginia | United States | DSFF1501 | DLA Visitor Control Center, Ft. Belvoir |  |  |  | 2016-10-28 | 2017-10-28 | 2018-09-30 | 96%
2018-07-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1203 | Upgrade Access Control Points - New Cumberland |  |  |  | 2013-11-01 | 2015-05-05 | 2018-01-10 | 100% | 2018-01-10
2018-07-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1301 | Replace Communications Bldg - New Cumberland |  |  |  | 2014-10-31 | 2016-04-28 | 2016-12-05 | 96% | 2017-06-12
2018-07-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland |  |  |  | 2014-07-11 | 2016-01-02 | 2016-10-27 | 100% | 2016-02-12
2017-11-30 | 2014 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1309 | Phase I DDC, Upgrade Public Safety Facility |  |  |  | 2016-11-18 | 2018-02-20 | 2018-02-20 | 2%
2018-07-31 | 2014 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1309 A | Phase I DDC, Upgrade Public Safety Facility |  |  |  | 2016-11-18 | 2017-11-18 | 2019-02-06 | 40%
2018-07-31 | 2014 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1309 B | Phase II DDC, Upgrade Public Safety Facility |  |  |  | 2018-08-08 | 2019-08-23 | 2019-11-23 | 0%
2018-07-31 | 2014 | DLA Defense Distribution Center | Major Military Construction | California | United States | DDCX1404 | (Tracy) General Purpose warehouse San Joaquin |  |  |  | 2014-10-02 | 2016-02-28 | 2018-07-20 | 100% | 2018-07-16
2018-07-31 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701A | CONSTRUCT WAREHOUSE & OPEN STORAGE (GPW) |  |  |  | 2018-06-26 | 2020-06-18 | 2021-05-24 | 0%
2018-07-31 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701B | CONSTRUCT WAREHOUSE & OPEN STORAGE (OSA) |  |  |  | 2018-09-30 | 2020-09-30 | 2020-09-30 | 0%
2018-07-31 | 2015 | DLA Defense Distribution Center | Major Military Construction | Hawaii | United States | DESC15S2 | Replace JapanTS Fuel Tanks, |  |  |  | 2017-06-01 | 2017-12-10 | 2017-12-10 | 70%
2018-07-31 | 2015 | DLA Defense Distribution Center | Major Military Construction | South Carolina | United States | DESC1606 | Replace Fuel Distribution Facilities - MCAS Beaufort |  |  |  | 2015-12-16 | 2017-11-05 | 2019-12-22 | 75%
2018-07-31 | 2014 | DLA Defense Distribution Center | Unspecified Minor Military Construction | Hawaii | United States | DSFH1401 | Upgrade Administrative Space - JB PH Hickam | DSFH14U2 |  |  | 2015-06-02 | 2016-10-14 | 2018-04-19 | 97% | 2018-04-19
2018-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Pennsylvania | United States | DCX1305 | Replace Reservoir, New Cumberland, PA |  |  |  | 2017-07-12 | 2019-06-26 | 2020-03-02 | 55%
2017-12-11 | 2013 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC 1306 | Replace Fuel Pier - Pt Loma |  |  |  | 2014-01-15 | 2017-10-14 | 2017-10-14 | 99% | 2017-10-14
2017-12-11 | 2015 | DLA Defense Energy Support Center | Major Military Construction | South Dakota | United States | DESC 1463 | Construct Hydrant Fuel System - Ellsworth AFB |  |  |  | 2016-01-19 | 2016-10-31 | 2017-06-30 | 98%
2017-12-11 | 2014 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC 1509 | Replace Fuel Pipeline - MCAS Miramar |  |  |  | 2016-02-16 | 2016-12-30 | 2017-06-27 | 96%
2018-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | Cuba | DESC1203 | Replace Fuel Pier - GTMO |  |  |  | 2013-10-03 | 2016-11-04 | 2017-02-12 | 100%
2018-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Indiana | United States | DESC1301 | Replace Hydrant Fuel system - Grissom ARB |  |  |  | 2015-09-17 | 2017-04-09 | 2018-09-25 | 81% | 2018-09-25
2018-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Guam | Guam | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB |  |  |  | 2014-06-30 | 2016-02-06 | 2018-03-13 | 100% | 2018-03-13
2018-07-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1306 | Replace Fuel Pier - Pt Loma |  |  |  | 2014-01-15 | 2017-10-14 | 2018-01-11 | 100% | 2018-01-01
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1353 | Replace Hydrant Fuel System - Robins AFB |  |  |  | 2016-06-28 | 2018-06-18 | 2018-09-21 | 100% | 2018-05-24
2018-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1401 | Construct Type III Hydrant Fueling system - Iwakuni MCAS |  |  |  | 2015-04-26 | 2017-08-23 | 2018-11-15 | 95% | 2018-11-15
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction |  | Cuba | DESC1404 | Replace Fuel Storage Tanks, Guantanamo Bay, Cuba |  |  |  | 2016-03-01 | 2017-11-13 | 2017-12-13 | 30%
2018-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1407 | Replace Hydrant Fuel System, Holloman AFB |  |  |  | 2015-08-17 | 2017-01-10 | 2017-07-19 | 100% | 2017-04-17
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | South Dakota | United States | DESC1463 | Construct Hydrant Fuel System - Ellsworth AFB |  |  |  | 2016-01-19 | 2017-04-16 | 2017-06-15 | 99% | 2017-09-13
2018-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Jersey | United States | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst |  |  |  | 2014-11-18 | 2016-05-11 | 2018-05-03 | 100% | 2018-05-03
2017-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | 43 |  |  | 2015-08-10 | 2016-10-23 | 2017-07-18 | 99% | 2016-12-08
2018-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 A | Replace Fuel Distribution Facilities, Tinker AFB |  |  |  | 2015-01-19 | 2017-05-23 | 2018-01-18 | 99% | 2018-01-18
2018-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 B | Replace Fuel Distribution Facilities, Tinker AFB |  |  |  | 2015-08-10 | 2016-10-23 | 2017-07-18 | 99% | 2017-07-18
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Maryland | United States | DESC1507 | Construct Hydrant Fuel System Andrews AFB MD |  |  |  | 2016-10-31 | 2018-02-07 | 2018-10-15 | 93%
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1508 | Replace Fuel Storage And Distribution Facilities NAS Lemoore CA |  |  |  | 2016-03-01 | 2020-03-30 | 2020-05-25 | 38%
2018-07-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1509 | Replace Fuel Pipeline - MCAS Miramar |  |  |  | 2016-02-16 | 2016-12-30 | 2017-06-27 | 92% | 2016-12-30
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Michigan | United States | DESC1510 | Replace Fuel Distribution Facilities, Selfridge ANG |  |  |  | 2015-12-09 | 2018-04-07 | 2018-10-05 | 99% | 2018-03-28
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1515 | Replace and Alter Fuel Distribution Facilites, Craney Island DFSP |  |  |  | 2015-09-30 | 2017-06-26 | 2017-08-02 | 100% | 2018-05-15
2018-07-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Hawaii | United States | DESC1551 | Upgrade fire Suppression and Ventilation System - Rd Hill; JB Pearl Harbor - Hickam |  |  |  | 2015-09-30 | 2017-09-25 | 2018-01-31 | 99%
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1602 | ENERGY UPGRADES, DFSP Charleston AFB |  |  |  | 2017-04-30 | 2018-02-28 | 2018-04-11 | 100% | 2018-03-20
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Germany | DESC1603 | CONSTRUCT FUEL LINE NORTH TO SOUTH SIDE, SPANGDAHLEM AB |  |  |  | 2018-08-10 | 2020-08-10 | 2020-08-10 | 0%
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Delaware | United States | DESC1605 | Construct Hydrant Fuel System, Dover AFB, DE |  |  |  | 2017-07-06 | 2020-01-06 | 2019-07-06 | 12%
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1607 | Replace Fuel Pier and Distribution Facility, Langley AFB, VA |  |  |  | 2016-10-12 | 2018-05-29 | 2019-10-12 | 81%
2018-07-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1611 | REPLACE HYDRANT SYSTEM (G) |  |  |  | 2017-12-30 | 2020-03-10 | 2020-03-10 | 23%
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Nevada | United States | DESC1613 | Replace Hydrant Fuels System Nellis AFB Nevada |  |  |  | 2016-11-28 | 2019-07-06 | 2019-10-11 | 79%
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Djibouti | DESC1701 | Construct Fuel Storage Facilities, Camp Lemonnie, Djibouti, Horn-of-Africa |  |  |  | 2017-03-13 | 2019-01-07 | 2019-12-24 | 47%
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1702 | CONSTRUCT DISTIBUTION PT. SE RAMP, CANNON AFB |  |  |  | 2017-12-07 | 2019-06-25 | 2019-08-03 | 45%
2018-07-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Marshall Islands | DESC1704 | REPLACEMENT STORAGE TANKS |  |  |  | 2017-11-08 | 2020-12-27 | 2021-02-15 | 5%
2018-07-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Diego Garcia | DESC1705 | IMPROVE WHARF REFUELING CAPABILITY |  |  |  | 2017-06-30 | 2019-06-29 | 2019-06-29 | 43%
2018-07-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1706 | CONSTRUCT HYDRANT SYSTEM HOT CARGO PAD |  |  |  | 2017-09-19 | 2019-04-04 | 2019-04-26 | 1%
2018-07-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction | Alaska | United States | DESC1707 | CONSTRUCT TRUCK OFFLOAD FACILITY |  |  |  | 2017-08-24 | 2018-12-15 | 2018-12-03 | 23%
2018-07-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1708 | CONSTRUCT TRUCK FUEL RECEIPT SYSTEM |  |  |  | 2017-09-08 | 2019-09-08 | 2019-09-08 | 27%
2018-07-31 | 2018 | DLA Defense Energy Support Center | Major Military Construction |  | Guam | DESC1709 | Construct Fuel Truck Offload, Andersen AB |  |  |  | 2018-09-21 | 2019-12-15 | 2019-12-15 | 0%
2018-07-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1710 | Replace Truck Fill Stands, Moody AFB, Georgia |  |  |  | 2016-11-02 | 2018-04-26 | 2019-08-27 | 65%
2017-12-11 | 2015 | DLA Defense National Stockpile Center | Major Military Construction | Maryland | United States | DESC1507 | Construct Hydrant Fuel System Andrews AFB MD |  |  |  | 2016-10-31 | 2018-02-07 | 2018-02-14 | 75%
2018-07-31 | 2018 | DLA Defense Reutilization and Marketing Service | Major Military Construction | Florida | United States | DRMS1701 | Upgrade Open Storage Yard, Eglin AB |  |  |  | 2018-09-02 | 2019-07-06 | 2019-10-11 | 0%
2018-07-31 | 2016 | DLA Defense Supply Center Philadelphia | Major Military Construction | Pennsylvania | United States | DSCP1501 | DLA Toop Suport Headquarters, NSA Philadelphia, PA |  |  |  | 2016-10-01 | 2019-03-30 | 2020-01-02 | 11%
2018-07-31 | 2014 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1401 | Operations Center Phase 1 |  |  |  | 2015-08-26 | 2018-08-25 | 2018-10-31 | 98% | 2018-04-20
2018-07-31 | 2015 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1501 | Replace Access Control Point, Richmond |  |  |  | 2018-02-23 | 2019-08-12 | 2019-08-12 | 1%
2018-07-13 | 2017 | Defense Health Agency | Major Military Construction |  | Japan | 14022 | TLAMM-P Medical Warehouse |  |  |  | 2017-10-26 | 2019-10-26 | 2019-10-26 | 1% | 2020-02-01
2018-07-13 | 2008 | Defense Health Agency | Major Military Construction | Kansas | United States | 47298 | Hospital Replacement |  | 44000000 | PN 72754 | 2010-05-03 | 2013-07-23 | 2016-08-12 | 100% | 2016-03-15
2018-07-13 | 2008 | Defense Health Agency | Major Military Construction |  | Germany | 52332 | Medical Clinic Replacement |  |  |  | 2008-08-29 | 2012-05-15 | 2012-07-16 | 100% | 2011-10-08
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 |  |  |  | 2007-10-12 | 2008-06-13 | 2008-06-08 | 100% | 2008-07-23
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-01 |  |  | 2008-08-19 | 2009-02-15 | 2009-02-13 | 100% | 2009-03-03
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-02 |  |  | 2009-10-15 | 2010-04-13 | 2010-04-13 | 100% | 2010-04-13
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-03 |  |  | 2008-12-05 | 2009-07-24 | 2009-07-24 | 100% | 2009-07-24
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-04 |  |  | 2008-07-15 | 2011-05-06 | 2013-10-31 | 100% | 2013-12-06
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-05 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 2 | 63418 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 3 | 63419 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420-01 |  |  | 2008-07-15 | 2013-10-31 | 2016-12-06 | 100% | 2013-12-06
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324-01 |  |  | 2008-07-15 | 2013-10-31 | 2013-12-06 | 100% | 2013-12-06
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 99% | 2017-05-04
2018-07-13 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 99% | 2017-05-04
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-02 |  |  | 2017-10-26 | 2018-10-26 | 2018-10-26 | 9% | 2019-02-26
2018-07-13 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 8 | 78211 |  |  | 2009-06-01 | 2014-05-31 | 2018-12-31 | 98% | 2018-10-19
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | New York | United States | 59220 | Hospital Add/Alt (Supplemental) |  | 5537000 | PN 76558 | 2011-10-26 | 2015-08-03 | 2015-09-11 | 99% | 2015-07-15
2018-05-14 | 2010 | Defense Health Agency | Major Military Construction | Maryland | United States | 61401 | Boundary Gate at Nallin Pond |  |  |  | 2011-01-12 | 2013-01-10 | 2015-01-08 | 100% | 2014-12-31
2018-04-12 | 2009 | Defense Health Agency | Major Military Construction | Oklahoma | United States | 62189 | Medical / Dental Clinic Replacement |  | 7033000 | PN 00001 VCOE PN 76558 | 2009-06-01 | 2011-10-26 | 2012-02-09 | 100% | 2012-06-04
2018-07-13 | 2009 | Defense Health Agency | Base Realignment and Closures | Maryland | United States | 64156 | USAMRICD Replacement, Inc 1 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Illinois | United States | 65030 | Naval Hospital Great Lakes Health Clinic Demolition |  | 9210000 | PN 67951 PN 71325 PN 77154 | 2012-09-12 | 2013-09-13 | 2014-08-08 | 100% | 2014-04-21
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction |  | Guam | 65270 | Hospital Replacement, Inc 1 |  | 659000 | PN 61401 | 2010-11-01 | 2014-10-15 | 2016-09-06 | 100% | 2014-03-18
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 | 65731-01 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-01 |  |  | 2010-10-01 | 2011-09-30 | 2011-09-30 | 100% | 2011-10-01
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-02 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 3 | 67181 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 4 | 67182 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2018-07-13 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66588 | Health Clinic Add/Alt |  |  |  | 2013-04-08 | 2016-05-30 | 2017-05-03 | 100% | 2017-05-10
2018-07-13 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66693 | Health/Dental Clinic Replacement |  | 65000 | PN 66588 | 2014-02-03 | 2016-04-12 | 2016-06-30 | 100% | 2016-06-30
2018-07-13 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67949 | NIBC Security Fencing and Equipment |  |  |  | 2012-04-02 | 2013-04-02 | 2013-04-01 | 100% | 2013-04-01
2018-07-13 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67949 | NIBC Security Fencing and Equipment | 67949-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 99% | 2017-05-04
2018-04-12 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67951 | Water Treatment Plant Repair |  |  |  | 2013-01-14 | 2014-07-08 | 2016-06-01 | 100% | 2016-03-18
2018-05-14 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67953 | Supplemental Water Storage |  |  |  | 2011-07-20 | 2012-11-01 | 2016-12-01 | 100% | 2016-11-04
2018-03-13 | 2012 | Defense Health Agency | Major Military Construction | North Carolina | United States | 70351 | Hospital Alteration |  | 23532000 | PN 67182 PN 71503 | 2012-09-13 | 2014-06-23 | 2016-05-19 | 100% | 2016-05-19
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) |  | 92680000 | PN 76558 | 2012-05-30 | 2015-03-16 | 2018-06-29 | 99% | 2017-05-31
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) | 70354-01 |  |  | 2017-10-11 | 2018-05-01 | 2018-07-17 | 82% | 2018-07-30
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) | 70354-02 |  |  | 2017-11-09 | 2018-12-31 | 2018-12-31 | 9% | 2019-03-22
2018-03-13 | 2011 | Defense Health Agency | Major Military Construction | Georgia | United States | 70482 | Health Clinic Addition/Alteration |  |  |  | 2011-06-21 | 2013-06-20 | 2014-05-19 | 100% | 2013-11-29
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | South Carolina | United States | 71317 | Medical Clinic Replacement |  | 4000000 | PN 80306 | 2013-12-06 | 2016-12-30 | 2019-01-10 | 97% | 2016-12-02
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 71325 | Medical Clinic Replacement |  |  |  | 2013-10-24 | 2016-10-23 | 2018-06-01 | 92% | 2018-06-08
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 71408 | Dental Clinic Replacement |  |  |  | 2013-03-01 | 2016-12-06 | 2019-06-30 | 78% | 2018-09-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic |  | 8300000 | PN 72754 | 2012-09-01 | 2014-09-09 | 2016-01-31 | 100% | 2016-04-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic | 71503-01 |  |  | 2016-08-25 | 2017-12-25 | 2018-12-31 | 99% | 2018-08-07
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 71507 | Branch Health Clinic Replacement |  | 10052000 | PN 72722 PN 80306 PN 72738 | 2014-04-30 | 2015-10-15 | 2017-02-08 | 100% | 2017-12-04
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement |  | 205000 | PN 61401 | 2010-12-14 | 2012-08-10 | 2012-09-28 | 100% | 2012-09-28
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement | 71550-01 |  |  | 2013-07-01 | 2013-08-30 | 2013-08-30 | 100% | 2013-08-30
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement | 71550-02 |  |  | 2015-03-03 | 2015-06-30 | 2016-06-30 | 100% | 2016-06-30
2018-07-13 | 2016 | Defense Health Agency | Major Military Construction | Ohio | United States | 71642 | Satellite Pharmacy Replacement |  |  |  | 2016-10-14 | 2019-01-12 | 2019-01-12 | 58% | 2019-04-04
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Georgia | United States | 72292 | Hospital Addition/Alteration Phase 2 |  | 11500000 | PN 72754 PN 71503 | 2012-10-15 | 2016-10-14 | 2017-08-18 | 99% | 2017-08-18
2018-07-13 | 2015 | Defense Health Agency | Major Military Construction | Colorado | United States | 72414 | Dental Clinic Replacement |  |  |  | 2015-11-03 | 2018-06-26 | 2018-09-20 | 98% | 2018-09-10
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction |  | Korea, South | 72419 | Hospital Addition/Alteration |  | 6286000 | PN 72738 | 2013-09-26 | 2017-08-08 | 2019-01-01 | 93% | 2018-12-31
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72430 | Ambulatory Care Center, Phase 1 |  |  |  | 2010-10-04 | 2013-02-20 | 2013-11-19 | 100% | 2013-11-19
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72430 | Ambulatory Care Center, Phase 1 | 72430-01 |  |  | 2010-10-04 | 2012-02-26 | 2012-12-13 | 100% | 2012-12-13
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 |  |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 72251 |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-01 |  |  | 2011-11-02 | 2013-08-13 | 2013-10-12 | 100% | 2013-10-12
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-02 |  |  | 2011-08-23 | 2012-07-05 | 2012-12-31 | 100% | 2012-12-31
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-03 |  |  | 2012-08-28 | 2013-06-19 | 2013-10-17 | 100% | 2013-10-17
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-04 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-05 |  |  | 2012-09-04 | 2014-01-04 | 2015-09-16 | 100% | 2015-09-16
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-06 |  |  | 2011-08-25 | 2011-11-01 | 2011-11-01 | 100% | 2011-11-01
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 3 | 72786 |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-01 |  |  | 2013-10-21 | 2014-10-24 | 2014-10-24 | 99% | 2014-11-24
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-02 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2017-10-11 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 77251 |  |  | 2013-05-29 | 2016-11-26 | 2020-01-31 | 78% | 2018-09-03
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407 |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 7 | 81408 |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2018 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl. Incr 8 | 91301 |  |  | 2013-05-29 | 2016-11-26 | 2019-09-06 | 86% | 2020-02-01
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) |  | 22793000 | PN 76558 | 2011-10-25 | 2014-09-09 | 2015-04-17 | 100% | 2015-09-23
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-01 |  |  | 2011-03-20 | 2011-04-01 | 2011-04-01 | 100% | 2011-04-01
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-02 |  |  | 2011-07-01 | 2014-09-27 | 2015-03-18 | 100% | 2015-03-18
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-03 |  |  | 2015-11-30 | 2016-06-01 | 2016-06-08 | 100% | 2016-06-08
2018-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | United Kingdom | 72727 | Medical/Dental Clinic Replacement |  |  |  | 2014-05-06 | 2015-10-30 | 2016-01-06 | 100% | 2015-08-27
2018-07-13 | 2017 | Defense Health Agency | Major Military Construction | Texas | United States | 72738 | Medical/Dental Clinic Replacement |  | 1000000 | PN 80307 | 2017-10-26 | 2020-10-31 | 2020-10-31 | 2% | 2021-06-15
2018-07-13 | 2011 | Defense Health Agency | Major Military Construction | Texas | United States | 72752 | Ambulatory Care Center Phase 2 |  | 75054000 | PN 72727 PN 62886 PN 77000 | 2011-12-02 | 2013-10-01 | 2016-09-02 | 100% | 2016-09-02
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 2 | 80793 |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | California | United States | 72808 | Medical Clinic Replacement |  | 1500000 | PN 80309 | 2014-02-28 | 2015-03-16 | 2017-04-28 | 100% | 2016-06-23
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) |  | 3850000 | PN 100040 | 2010-11-08 | 2014-05-31 | 2016-02-15 | 99% | 2016-04-01
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-01 |  |  | 2010-06-15 | 2012-02-25 | 2012-06-02 | 100% | 2012-06-02
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-02 |  |  | 2010-04-05 | 2010-05-30 | 2010-06-30 | 100% | 2010-06-30
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-03 |  |  | 2010-06-18 | 2010-10-18 | 2010-10-05 | 100% | 2010-10-05
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-04 |  |  | 2010-07-20 | 2012-01-11 | 2012-09-20 | 100% | 2012-09-20
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-05 |  |  | 2011-01-06 | 2012-06-29 | 2013-12-15 | 99% | 2013-12-15
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 |  |  |  | 2014-01-13 | 2023-12-30 | 2023-12-30 | 7% | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 7 | 14043 |  |  | 2018-12-30 | 2022-12-30 | 2023-12-30 | 1% | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  | 2016-02-28 | 2016-04-30 | 2017-04-30 | 100% | 2017-02-28
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 72661-01 |  |  | 2017-07-30 | 2020-12-30 | 2020-12-30 | 13% | 2020-12-30
2017-11-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72661-02 |  |  | 2017-12-15 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2017-09-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 72661-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-12-30 | 12% | 2018-12-30
2017-06-30 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72661-2 |  |  | 2017-12-15 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72662 |  |  | 2018-08-30 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 72662-01 |  |  | 2020-12-30 | 2022-12-30 | 2022-12-30 | 1% | 2022-12-30
2018-06-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72662-02 |  |  | 2018-08-30 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2017-09-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72662-2 |  |  | 2017-12-15 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-01 |  |  | 2014-01-20 | 2014-04-04 | 2014-04-04 | 100% | 2014-04-04
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-02 |  |  | 2014-06-16 | 2014-10-29 | 2015-01-21 | 100% | 2015-01-21
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-03 |  |  | 2015-04-20 | 2016-04-30 | 2017-07-30 | 100% | 2016-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-04 |  |  | 2016-06-15 | 2016-12-15 | 2017-12-15 | 100% | 2018-01-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-05 |  |  | 2014-08-22 | 2015-03-30 | 2015-05-01 | 100% | 2015-05-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-06 |  |  | 2014-10-08 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-07 |  |  | 2014-08-11 | 2014-10-16 | 2014-10-16 | 100% | 2014-10-16
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-08 |  |  | 2016-08-15 | 2016-10-30 | 2016-12-30 | 100% | 2016-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-09 |  |  | 2016-11-30 | 2016-12-15 | 2019-12-30 | 50% | 2017-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1, Incr 6 | 76007-10 |  |  | 2014-12-10 | 2022-12-30 | 2023-12-30 | 10% | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 76007-11 |  |  | 2019-03-30 | 2023-12-30 | 2023-12-30 | 1% | 2023-12-30
2017-06-30 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-12 |  |  | 2017-07-30 | 2020-12-30 | 2020-12-30 | 1% | 2020-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-13 |  |  | 2014-10-23 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 through Incr 8 | 76007-14 |  |  | 2015-03-30 | 2022-12-30 | 2023-12-30 | 2% | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 76007-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-12-30 | 73% | 2018-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 4-8 | 76872 |  |  | 2018-12-30 | 2022-12-30 | 2023-12-30 | 1% | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 81412-02 |  |  | 2022-07-01 | 2023-12-30 | 2023-12-30 | 1% | 2023-12-30
2018-07-13 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement |  |  |  | 2015-09-08 | 2019-02-19 | 2019-03-20 | 62% | 2019-10-18
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 1 |  |  |  | 2013-03-01 | 2016-12-06 | 2019-06-30 | 94% | 2017-06-20
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 2 | 81291 |  |  | 2013-03-01 | 2016-12-06 | 2019-06-30 | 94% | 2017-06-20
2018-07-13 | 2014 | Defense Health Agency | Major Military Construction | New Mexico | United States | 77922 | Medical Clinic Replacement |  | 13900000 | PN 81430 PN 81340 PN 14019 | 2014-10-28 | 2018-01-23 | 2018-06-13 | 99% | 2018-06-13
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | New Mexico | United States | 77979 | Medical/Dental Clinic Replacement |  | 9000000 | PN 76558 | 2014-08-12 | 2018-02-10 | 2018-08-31 | 97% | 2018-03-09
2018-07-13 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition |  |  |  | 2016-12-14 | 2019-06-04 | 2019-07-04 | 22% | 2019-06-17
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Illinois | United States | 78143 | Navy Drug Lab Replacement |  | 5448000 | PN 78146 PN 72738 | 2013-11-08 | 2015-01-15 | 2018-05-31 | 100% | 2015-04-20
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Illinois | United States | 78143 | Navy Drug Lab Replacement | 78143-01 |  |  | 2017-05-29 | 2018-05-23 | 2018-05-31 | 100% | 2018-05-21
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 78144 | Medical Clinic Addition |  | 3211000 | PN 80306 PN 80906 | 2013-10-08 | 2015-03-17 | 2015-12-21 | 100% | 2015-09-11
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Virginia | United States | 78146 | Veterinarian Facility |  | 670000 | PN 77979 | 2014-02-28 | 2014-12-06 | 2015-11-23 | 100% | 2015-09-21
2018-07-13 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 78150 | Medical Clinic Replacement |  | 8000000 | PN 81430 | 2016-11-14 | 2018-12-21 | 2019-04-15 | 37% | 2019-05-19
2018-04-12 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 79554 | Child Development Center |  | 2000000 | PN 67182 | 2013-03-01 | 2014-02-22 | 2014-06-02 | 100% | 2014-04-07
2018-07-13 | 2009 | Defense Health Agency | Major Military Construction | Florida | United States | 79845 | Eglin Hospital Alteration (ARRA) |  |  |  | 2011-10-31 | 2014-11-06 | 2015-07-29 | 99% | 2015-03-12
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities |  |  |  | 2013-10-15 | 2013-12-13 | 2014-03-25 | 100% | 2014-04-04
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities | 80306-01 |  |  | 2016-10-04 | 2017-12-10 | 2018-07-20 | 99% | 2018-09-20
2018-07-13 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80307 | Implement Base Installation Appearance Plan |  |  |  | 2014-04-01 | 2015-04-08 | 2018-08-15 | 98% | 2018-08-15
2018-05-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80308 | Electrical Utility Upgrades |  | 24852000 | PN 65270 PN 72738 | 2014-10-23 | 2016-02-12 | 2016-10-31 | 100% | 2016-10-31
2018-07-13 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 |  |  |  | 2016-06-16 | 2017-12-08 | 2018-11-26 | 62% | 2019-01-19
2018-07-13 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 | 80412-01 |  |  | 2018-02-28 | 2020-05-21 | 2020-05-21 | 1% | 2020-09-18
2018-07-13 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 80904 | Mechanical & Electrical Improvements |  |  |  | 2015-05-31 | 2017-02-07 | 2018-08-30 | 98% | 2018-08-30
2018-07-13 | 2017 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 1 |  |  |  | 2017-12-22 | 2019-05-10 | 2019-05-10 | 10% | 2019-05-10
2018-07-13 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 80913 | Parking Garage |  |  |  | 2014-11-30 | 2016-04-16 | 2017-09-28 | 100% | 2017-09-29
2018-07-13 | 2014 | Defense Health Agency | Major Military Construction | Texas | United States | 81340 | SAMMC Hyperbaric Facility Addition |  |  |  | 2014-07-29 | 2016-07-28 | 2017-03-30 | 100% | 2017-05-12
2018-02-14 | 2016 | Defense Health Agency | Major Military Construction | Texas | United States | 81422 | Lackland Ambulatory Care Center Phase 4 |  |  |  | 2017-03-23 | 2017-06-23 | 2017-07-14 | 100% | 2017-07-14
2018-07-13 | 2016 | Defense Health Agency | Major Military Construction | Texas | United States | 81422 | Lackland Ambulatory Care Center Phase 4 | 81422-01 |  |  | 2017-03-23 | 2017-06-23 | 2017-07-14 | 100% | 2017-07-14
2018-07-13 | 2015 | Defense Health Agency | Major Military Construction | Texas | United States | 81423 | Medical Clinic Replacement (Reid Clinic) |  |  |  | 2015-09-28 | 2018-09-27 | 2018-11-10 | 99% | 2018-06-10
2018-07-13 | 2015 | Defense Health Agency | Major Military Construction | Virginia | United States | 81430 | Hospital Add/CUP Replacement |  |  |  | 2019-06-01 | 2021-03-18 | 2021-03-18 | 8% | 2021-06-30
2018-07-13 | 2014 | Defense Health Agency | Major Military Construction |  | Bahrain | 81436 | Medical/Dental Clinic Replacement |  | 2000000 | PN 80904 | 2016-04-20 | 2019-04-20 | 2019-08-19 | 27% | 2019-08-19
2018-07-13 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | Washington | United States | 81627 | NiCOE Satellite, Infrastructure Support |  |  |  | 2016-03-28 | 2017-11-14 | 2017-09-12 | 100% | 2017-09-12
2018-07-13 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | North Carolina | United States | 81631 | NiCOE Satellite, Infrastructure Support |  |  |  | 2014-06-30 | 2016-02-01 | 2018-06-06 | 98% | 2016-03-31
2018-04-12 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | Texas | United States | 81706 | NiCOE Satellite, Infrastructure Support |  |  |  | 2014-09-15 | 2015-10-28 | 2015-12-11 | 100% | 2015-11-20
2018-07-13 | 2016 | Defense Health Agency | Major Military Construction | Kentucky | United States | 86953 | Medical Clinic |  |  |  | 2017-04-13 | 2021-05-16 | 2021-05-09 | 23% | 2019-11-13
2017-11-14 | 2016 | Defense Health Agency | Major Military Construction | Kentucky | United States | 86953 | Medical Clinic | 86953-01 |  |  | 2017-04-13 | 2021-05-16 | 2021-05-16 | 6% | 2021-11-18
2018-07-13 | 2017 | Defense Health Agency | Unspecified Minor Military Construction | California | United States | 87015 | NICoE Satellite, Infrastructure Support |  |  |  | 2016-08-21 | 2018-04-06 | 2018-04-04 | 100% | 2018-04-04
2018-07-25 | 2013 | Defense Information Systems Agency | Major Military Construction |  | Germany | 13DISA01 | DISA Europe Facility Upgrade |  |  |  | 2015-08-19 | 2016-12-31 | 2016-12-31
2018-07-25 | 2014 | Defense Information Systems Agency | Major Military Construction | Hawaii | United States | 14DISA01 | DISA Pacific Facility Upgrade |  |  |  | 2018-01-11 | 2018-09-30 | 2018-09-30
2018-07-25 | 2015 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 15DISA01 | Design/Renovate Bldg 52120 for JITC
2018-07-25 | 2015 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 15DISA01 | Design of Bldgs 52101, 52110, 52111 for JITC | 1
2018-07-25 | 2015 | Defense Information Systems Agency | Major Military Construction |  | Australia | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton)
2018-05-25 | 2016 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 16DISA01 | Design of Bldgs 52101, 52111 for JITC
2018-05-25 | 2017 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 17DISA01 | Design of Bldg 52110 for JITC
2018-07-25 | 2018 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 18DISA01 | Advance Planning for New Facility JITC Ft Huachuca
2018-07-25 | 2013 | Defense Information Systems Agency | Major Military Construction | Illinois | United States | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  |  |  | 2014-03-01 | 2015-12-30 | 2016-03-11 | 100%
2017-12-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA12000001 | DIAC Parking Garage Replacement |  |  |  | 2016-11-09 | 2017-09-19 | 2017-12-31 | 99%
2018-03-04 | 2010 | DoD Education Activity | Major Military Construction | Georgia | United States | AM 856 07 | New Elementary School |  |  |  | 2012-08-01 | 2013-12-14 | 2014-07-21 | 100% | 2014-08-01
2018-07-10 | 2014 | DoD Education Activity | Major Military Construction | Virginia | United States | AM00021 | REPLACE QUANTICO MIDDLE/HIGH SCHOOL |  |  |  | 2017-12-04 | 2020-01-09 | 2020-01-09 | 8%
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00023 | Replace McBride Elementary School |  |  |  | 2013-12-11 | 2015-12-11 | 2016-08-03 | 99% | 2016-08-02
2018-01-04 | 2012 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00023 | Replace McBride Elementary School | 23 |  |  | 2013-12-11 | 2015-12-11 | 2016-08-03 | 99% | 2016-08-02
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00023 | Replace McBride Elementary School | 28 |  |  | 2013-12-11 | 2015-12-11 | 2016-08-03 | 99% | 2016-08-02
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00024 | Faith Middle School Addition |  |  |  | 2014-10-28 | 2016-01-21 | 2016-05-24 | 99% | 2016-08-02
2018-07-10 | 2012 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00025 | Replace Delalio Elementary School |  |  |  | 2014-02-24 | 2016-06-01 | 2019-04-30 | 96%
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00026 | Replace Kingsolver/Pierce School |  |  |  | 2014-03-11 | 2015-11-11 | 2016-05-31 | 99% | 2017-03-08
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00026 | Replace Consolidate Kingsolver/Pierce Elem Schools | 43 |  |  | 2015-12-01 | 2016-11-30 | 2016-12-01 | 100% | 2016-11-30
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00027 | Replace Hanscom Middle School |  |  |  | 2014-02-11 | 2016-04-21 | 2016-04-27 | 100% | 2016-04-22
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00027 | Replace Hanscom Middle School | 88 |  |  | 2014-02-11 | 2016-04-21 | 2016-04-27 | 100% | 2016-04-22
2018-03-04 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School |  | 800000 | PA00033 | 2014-03-27 | 2015-12-17 | 2016-09-19 | 100% | 2017-03-01
2018-01-04 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School | 27 |  |  | 2014-03-27 | 2015-12-17 | 2016-09-19 | 100% | 2017-03-01
2018-03-04 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School | 44 |  |  | 2014-03-27 | 2015-12-17 | 2016-09-19 | 100% | 2017-03-01
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School | 82 |  |  | 2018-01-09 | 2018-10-06 | 2018-10-06 | 0%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00031 | Pope Holbrook Elementary School |  |  |  | 2015-02-11 | 2017-02-10 | 2017-07-21 | 96% | 2017-10-31
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction | New York | United States | AM00033 | USMA - REPLACE WEST POINT ELEMENTARY SCHOOL (PN AM00033) |  |  |  | 2017-03-21 | 2020-03-05 | 2020-03-05 | 35%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction | Tennessee | United States | AM00034 | Replace Fort Campbell High School |  |  |  | 2015-01-27 | 2017-02-25 | 2017-10-18 | 99% | 2017-12-06
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction | South Carolina | United States | AM00035 | Repl Pierce Terrace Elementary School |  |  |  | 2017-04-26 | 2019-04-26 | 2019-04-26 | 0%
2018-07-10 | 2014 | DoD Education Activity | Major Military Construction | South Carolina | United States | AM00037 | Replace Bolden-Galer Elementary School |  |  |  | 2015-08-18 | 2018-06-28 | 2016-02-26 | 97%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00038 | Diamond Elementary School Replacement |  |  |  | 2014-10-15 | 2016-09-14 | 2017-07-21 | 99% | 2017-07-20
2018-04-09 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00038 | Diamond Elementary School Replacement | 29 |  |  | 2016-06-15 | 2017-01-11 | 2017-01-11 | 100% | 2016-12-23
2018-03-04 | 2014 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00040 | Replace Marshall Elementary School |  |  |  | 2014-08-06 | 2016-03-28 | 2016-06-10 | 100% | 2016-06-10
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | United States | AM00046 | Design and Construct new Primary School at Hanscom |  |  |  | 2014-02-11 | 2016-04-21 | 2016-04-27 | 100% | 2016-04-22
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00046 | Design and Construct new Primary School at Hanscom | 246 |  |  | 2017-03-23 | 2019-09-09 | 2019-09-09 | 30%
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School |  | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2020-07-11 | 33%
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 8 | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2020-07-11 | 33%
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 9 |  |  | 2016-10-20 | 2020-06-10 | 2020-07-11 | 33%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00050 | White Elementary School Replacement |  |  |  | 2014-12-16 | 2016-10-31 | 2017-12-21 | 99%
2018-07-10 | 2015 | DoD Education Activity | Major Military Construction |  | United States | AM00103 | Consolidate/Replace W.T. Sampson Elementary School |  |  |  | 2016-07-01 | 2018-11-26 | 2019-03-14 | 41%
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00110 | Replace/Renovate Maxwell ES/MS |  |  |  | 2017-04-12 | 2020-05-28 | 2020-07-24 | 30%
2017-04-03 | 2015 | DoD Education Activity | Major Military Construction |  | Spain | AM00115 | Rota Elementary and High School Additions |  |  |  | 2016-07-20 | 2019-03-27 | 2019-03-27 | 12%
2018-07-10 | 2016 | DoD Education Activity | Major Military Construction |  | Spain | AM00115 | Rota Elementary and High School Additions |  |  |  | 2016-07-20 | 2019-03-27 | 2019-07-31 | 52%
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00123 | AM00123 Ft Knox High School Addition |  |  |  | 2016-08-16 | 2018-05-08 | 2018-07-14 | 84%
2018-07-10 | 2015 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM001461 | LEJEUNE HIGH SCHOOL ADDITION/RENOVATION |  |  |  | 2017-04-12 | 2020-03-28 | 2020-03-28 | 29%
2017-11-05 | 2011 | DoD Education Activity | Major Military Construction |  | United States | AM8193 01 | Replace Elementary School (Antilles ES) |  |  |  | 2012-07-18 | 2014-04-19 | 2014-12-16 | 100% | 2016-08-10
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School |  |  |  | 2017-01-09 | 2019-05-08 | 2019-05-08 | 36%
2017-06-04 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School | 29 |  |  | 2017-01-09 | 2019-05-09 | 2019-05-09 | 2%
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School | 89 |  |  | 2017-01-09 | 2019-05-08 | 2019-05-08 | 36%
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School |  |  |  | 2016-09-12 | 2019-02-21 | 2019-04-21 | 55%
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School | 45 |  |  | 2016-09-12 | 2019-02-21 | 2019-04-21 | 55%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School |  |  |  | 2017-12-15 | 2022-01-23 | 2022-01-23 | 6%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 1 |  |  | 2017-12-15 | 2022-01-23 | 2022-01-23 | 6%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 2 |  |  | 2017-12-15 | 2022-01-23 | 2022-01-23 | 6%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 3 |  |  | 2017-12-15 | 2022-01-23 | 2022-01-23 | 6%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 4 |  |  | 2017-12-15 | 2022-01-23 | 2022-01-23 | 6%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 5 |  |  | 2017-12-15 | 2022-01-23 | 2022-01-23 | 6%
2018-04-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement |  |  |  | 2016-03-14 | 2016-06-22 | 2016-09-23 | 100% | 2016-10-21
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement | 6 |  |  | 2017-06-30 | 2019-11-04 | 2019-11-04 | 14%
2017-06-04 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement | 60 |  |  | 2017-05-12 | 2017-05-09 | 2017-05-09 | 90%
2017-06-04 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement | 61 |  |  | 2017-05-12 | 2019-06-18 | 2019-06-18 | 0%
2017-06-04 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement | 62 |  |  | 2017-05-12 | 2019-06-18 | 2019-06-18 | 0%
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School |  |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 94% | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 33 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 94% | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 34 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 94% | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 35 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 94% | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 36 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 94% | 2017-05-11
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00049 | Replace Hainerberg Elementary School |  |  |  | 2013-09-26 | 2022-10-18 | 2022-10-18 | 0%
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00051 | FY16 DoDEA-E EU00051 Replace Patch Elementary School |  |  |  | 2017-08-14 | 2020-05-10 | 2020-05-10 | 10%
2018-03-04 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00062 | Netzaberg Middle School Addition |  |  |  | 2014-06-05 | 2015-09-20 | 2015-11-24 | 100% | 2015-12-21
2018-03-04 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00062 | Netzaberg Middle School Addition | 42 |  |  | 2014-06-05 | 2015-09-20 | 2015-11-24 | 100% | 2015-12-21
2018-07-09 | 2015 | DoD Education Activity | Major Military Construction |  | Belgium | EU00064 | Replace Brussels Elementary/ High School |  |  |  | 2017-10-25 | 2020-10-24 | 2020-10-24 | 5%
2018-07-09 | 2015 | DoD Education Activity | Major Military Construction |  | Belgium | EU00064 | Replace Brussels Elementary/ High School | 64
2018-07-09 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00068 | Replace Grafenwoehr |  |  |  | 2017-09-25 | 2021-01-07 | 2021-01-07 | 0%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00072 | Replace Wiesbaden Middle School |  |  |  | 2016-04-21 | 2018-04-11 | 2018-04-11 | 80%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00072 | Replace Wiesbaden Middle School | 7 |  |  | 2016-04-21 | 2018-04-11 | 2018-04-11 | 80%
2018-07-09 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 99%
2017-10-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 3 |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 80%
2017-10-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 4 |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 80%
2018-07-09 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00017 | Killin Elementary School Replacement/Renovation |  |  |  | 2017-01-11 | 2020-11-17 | 2020-11-25 | 6%
2018-07-09 | 2014 | DoD Education Activity | Major Military Construction |  | Korea, South | PA00018 | Daegu Middle/High School Replacement |  |  |  | 2014-09-29 | 2016-10-03 | 2017-05-30 | 100% | 2017-06-26
2017-10-04 | 2013 | DoD Education Activity | Major Military Construction |  | Korea, South | PA00020 | Replace Elementary School (Osan ES) |  | 6444000 | PA00033 | 2013-09-30 | 2015-12-09 | 2016-06-14 | 100% | 2016-07-12
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00021 | Replace Sasebo Elementary School |  |  |  | 2016-04-04 | 2018-11-03 | 2019-03-14 | 32%
2018-07-09 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00023 | FY15 DODS PA00023 Renovate Edgren High School, Misawa Air Base, Japan |  |  |  | 2017-02-07 | 2019-05-28 | 2019-08-17 | 22%
2018-07-09 | 2012 | DoD Education Activity | Major Military Construction |  | Japan | PA00027 | Replace Yokota High School |  |  |  | 2015-02-19 | 2018-12-21 | 2019-02-17 | 97%
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00028 | FY13 DoDEA PA00028 Zama High School Renovation, Camp Zama, Japan |  |  |  | 2017-08-02 | 2019-07-19 | 2019-09-22 | 4%
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00030 | Replace Zukeran Elementary School |  |  |  | 2014-10-23 | 2017-04-01 | 2018-04-02 | 99%
2018-07-09 | 2017 | DoD Education Activity | Major Military Construction |  | Japan | PA00032 | Replace Kasena ES |  |  |  | 2018-04-02 | 2021-02-15 | 2021-02-15 | 1%
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  |  |  | 2014-07-07 | 2016-10-24 | 2018-01-09 | 99% | 2018-01-31
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 38 |  |  | 2014-07-07 | 2016-10-24 | 2018-01-09 | 99% | 2018-01-31
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 39 |  |  | 2014-07-07 | 2016-10-24 | 2018-01-09 | 99% | 2018-01-31
2018-07-09 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 40 |  |  | 2014-07-07 | 2016-10-24 | 2018-01-09 | 99% | 2018-01-31
2018-02-07 | 2014 | DoD Education Activity | Major Military Construction |  | Japan | PA00035 | Kadena Middle School Addition/Renovation |  |  |  | 2015-03-06 | 2016-10-02 | 2017-08-20 | 100% | 2017-06-15
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146193 | WATER TREATMENT PLANT REPLACEMENT |  |  |  | 2017-01-05 | 2020-02-28 | 2020-04-29 | 45% | 2020-03-28
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146194 | UNMANNED AIRCRAFT SYSTEM FACILITIES |  |  |  | 2016-09-14 | 2018-10-04 | 2018-10-04 | 59% | 2018-10-04
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146224 | CENTRAL HEATING PLANT CONVERSION |  |  |  | 2017-06-13 | 2019-01-31 | 2019-01-31 | 61% | 2019-01-31
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146229 | KC-130J ENLISTED AIR CREW TRAINER FACILITY |  |  |  | 2016-09-20 | 2017-10-02 | 2018-03-21 | 98% | 2018-05-15
2017-09-30 | 2013 | Marine Corps Active | Major Military Construction | California | United States | M00243313 | ENTRY CONTROL POINT (GATE 5) |  |  |  | 2014-01-03 | 2015-04-29 | 2016-11-30 | 99% | 2016-11-01
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | California | United States | M00243520 | STEAM PLANT DECENTRALIZATION |  |  |  | 2015-10-13 | 2018-01-11 | 2019-04-22 | 86% | 2019-02-11
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263398 | RANGE SAFETY IMPROVEMENTS & MODERNIZATION |  |  |  | 2016-10-11 | 2018-04-20 | 2018-04-20 | 83% | 2018-09-21
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M002641406 | ATC TX/RX RELOCATION |  |  |  | 2015-05-15 | 2016-11-21 | 2018-09-03 | 44% | 2017-11-21
2017-09-30 | 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  |  |  | 2013-10-07 | 2016-11-06 | 2018-01-22 | 39% | 2018-03-30
2017-09-30 | 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264572 | INFRASTRUCTURE WIDEN RUSSELL ROAD |  |  |  | 2015-10-15 | 2017-05-28 | 2017-05-28 | 33% | 2017-03-26
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264635 | AMMUNITION SUPPLY POINT EXPANSION |  |  |  | 2016-11-30 | 2018-03-25 | 2018-03-25 | 69% | 2019-04-26
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264677 | TECOM SCHOOLS ACADEMIC INSTRUCTION FACILITY |  |  |  | 2016-04-14 | 2018-01-05 | 2018-07-04 | 72% | 2018-10-01
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264707 | EMBASSY SECURITY GUARD BEQ & OPS FACILITY |  |  |  | 2017-05-11 | 2019-12-03 | 2019-12-03 | 12% | 2019-12-03
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318116 | P-8A DETACHMENT SUPPORT FACILITIES |  |  |  | 2016-08-22 | 2018-06-09 | 2018-08-14 | 82% | 2018-09-01
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318778 | ARMORY ADDITION AND RENOVATION |  |  |  | 2015-03-27 | 2017-08-09 | 2018-07-25 | 77% | 2018-10-13
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318852 | 3RD RADIO BATTALION COMPLEX |  |  |  | 2014-09-19 | 2016-10-04 | 2018-08-17 | 80% | 2018-08-17
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318861 | FACILITY MODIFICATIONS FOR VMU, MWSD AND CH53E |  |  |  | 2015-09-15 | 2018-08-11 | 2018-08-11 | 53% | 2019-09-17
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318863 | AIRCRAFT MAINTENANCE HANGAR UPGRADES |  |  |  | 2016-10-03 | 2019-04-17 | 2019-04-17 | 14% | 2020-02-28
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  |  |  | 2014-10-14 | 2016-12-18 | 2017-06-17 | 59% | 2018-12-18
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318902 | AIRFIELD LIGHTING MODERNIZATION |  |  |  | 2016-12-02 | 2019-06-06 | 2019-06-06 | 44% | 2019-09-06
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  |  |  | 2015-04-28 | 2017-01-03 | 2018-03-23 | 51% | 2018-05-28
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318908 | MV-22 HANGAR |  |  |  | 2015-04-28 | 2017-01-03 | 2018-03-23 | 81% | 2018-05-28
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318923 | REGIMENTAL CONSOLIDATED COMM/ELEC FACILITY |  |  |  | 2017-09-04 | 2020-03-08 | 2020-03-08 | 1% | 2020-03-08
2017-09-30 | 2013 | Marine Corps Active | Major Military Construction | California | United States | M006811132 | COMMUNICATION INFORMATION SYSTEMS OPS COMPLEX |  |  |  | 2016-04-07 | 2020-01-23 | 2020-06-13 | 27% | 2020-01-23
2017-09-30 | 2013 | Marine Corps Active | Major Military Construction | California | United States | M006811176 | SAN JACINTO ROAD EXTENSION |  |  |  | 2014-10-08 | 2016-04-21 | 2018-02-24 | 23% | 2018-02-28
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | California | United States | M00681970 | AMMUNITION SUPPLY POINT FACILITIES PULGAS |  |  |  | 2016-01-13 | 2018-04-27 | 2018-10-26 | 28% | 2019-04-27
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169464 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2017-07-13 | 2020-07-13 | 2020-07-13 | 9% | 2020-07-13
2017-09-30 | 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2014-08-29 | 2016-09-08 | 2017-07-15 | 97% | 2017-09-10
2018-06-30 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M62204930 | COMBAT VEHICLE REPAIR FACILITY |  |  |  | 2018-05-02 | 2020-05-02 | 2020-05-02 | 1% | 2020-05-02
2018-06-30 | 2016 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626130702 | WHOLEHOUSE REVITALIZATION MONZEN TOWNHOUSES PHASE 3 |  |  |  | 2016-10-06 | 2017-10-09 | 2017-09-25 | 100% | 2017-09-25
2018-06-30 | 2014 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131402 | WHOLEHOUSE REVITALIZATION SOQs |  |  |  | 2016-10-11 | 2018-03-04 | 2018-03-04 | 100% | 2018-03-02
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974617 | AVIATION MAINTENANCE AND SUPPORT COMPLEX |  |  |  | 2016-06-06 | 2017-11-29 | 2018-08-15 | 97% | 2018-06-27
2017-09-30 | 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001003 | STAFF NCO ACADEMY FACILITIES |  |  |  | 2013-09-19 | 2015-09-01 | 2017-03-31 | 99% | 2017-08-31
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011280 | 2ND RADIO BN COMPLEX PHASE 1 |  |  |  | 2017-06-13 | 2019-06-24 | 2019-09-03 | 30% | 2019-09-04
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011349 | SPECIAL OPERATIONS TRAINING COMPLEX |  |  |  | 2015-09-14 | 2017-03-21 | 2018-06-02 | 98% | 2018-06-02
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011428 | RANGE FACILITIES SAFETY IMPROVEMENTS |  |  |  | 2017-09-08 | 2019-05-08 | 2019-05-08 | 36% | 2019-05-08
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011445 | STEAM DECENTRALIZATION (CAMP JOHNSON) |  |  |  | 2015-02-06 | 2017-02-06 | 2017-08-11 | 95% | 2017-08-11
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011447 | STEAM DECENTRALIZATION - HADNOT POINT |  |  |  | 2015-02-06 | 2017-02-06 | 2017-08-11 | 100% | 2017-08-11
2017-09-30 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011448 | STEAM DECENTRALIZATION (BEQ NODES) |  |  |  | 2015-02-06 | 2017-02-06 | 2017-08-11 | 95% | 2017-08-11
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001674 | CORROSION CONTROL HANGAR |  |  |  | 2015-09-02 | 2017-03-11 | 2018-05-02 | 84% | 2018-10-26
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001686 | RADAR AIR TRAFFIC CONTROL FACILITY ADDITION |  |  |  | 2016-10-12 | 2018-04-06 | 2019-03-11 | 4% | 2019-03-11
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001726 | REGIONAL COMMUNICATION STATION |  |  |  | 2014-06-13 | 2015-12-20 | 2018-08-05 | 66% | 2018-05-31
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001729 | OPERATIONAL TRAINER FACILITY |  |  |  | 2016-10-12 | 2018-04-06 | 2019-03-11 | 89% | 2019-03-11
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  |  |  | 2014-11-17 | 2016-03-17 | 2018-03-06 | 100% | 2018-02-08
2018-06-30 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | Georgia | United States | M67004971 | CONSTRUCT LOGCOM OPEN STORAGE LOT |  |  |  | 2018-03-29 | 2018-11-06 | 2018-11-06 | 1% | 2018-11-06
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004972 | GROUND SOURCE HEAT PUMPS |  |  |  | 2017-04-05 | 2019-01-28 | 2019-02-23 | 56% | 2019-01-28
2018-06-30 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | District Of Columbia | United States | M67029007 | Communications Center for Marine Barracks, Washington, DC |  |  |  | 2017-05-03 | 2018-04-19 | 2018-04-19 | 42% | 2018-04-19
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | California | United States | M673991232 | MICROGRID EXPANSION |  |  |  | 2017-10-10 | 2019-04-19 | 2019-05-26 | 6% | 2019-04-19
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction | California | United States | M67399222 | E-LMR SLICE COMMUNICATION TOWERS |  |  |  | 2016-09-14 | 2019-03-04 | 2019-03-04 | 77% | 2019-03-04
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400213 | HANGAR & RINSE FACILITY MODERNIZATIONS
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M67400606 | MILITARY WORKING DOG FACILITIES (CAMP HANSEN) |  |  |  | 2016-09-29 | 2018-03-26 | 2018-03-26 | 74% | 2018-03-26
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400801 | LHD PRACTICE SITE IMPROVEMENTS |  |  |  | 2016-05-05 | 2017-07-29 | 2017-07-29 | 55% | 2017-07-29
2018-06-30 | 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400803 | AIRCRAFT MAINT HANGAR ALTERATIONS AND SAP-F |  |  |  | 2016-01-05 | 2017-09-12 | 2017-09-12 | 33% | 2017-09-12
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M67400809 | AIRCRAFT MAINT. SHELTERS & APRON |  |  |  | 2018-06-14 | 2020-01-21 | 2020-01-21 | 1% | 2020-01-21
2018-06-30 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M67604132 | ORDNANCE BULD-UP FACILITY |  |  |  | 2016-09-14 | 2017-10-30 | 2017-12-19 | 97% | 2017-12-18
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2018-02-07 | 2020-01-14 | 2020-01-14 | 22% | 2020-01-14
2018-06-30 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR - INC 2 | M67865198A |  |  | 2018-02-07 | 2020-01-14 | 2020-01-14 | 1% | 2020-01-14
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | California | United States | M67865200 | KC-130J ENLISTED AIR CREW TRAINER |  |  |  | 2017-06-08 | 2018-12-31 | 2019-02-02 | 37% | 2018-12-31
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865203 | F-35 F-35 Aircraft Parking Apron |  |  |  | 2018-02-07 | 2020-01-14 | 2020-01-14 | 13% | 2020-01-14
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865249 | F-35 COMM BUILDING & INFRASTRUCTURE UPGRADE |  |  |  | 2018-01-01 | 2019-09-24 | 2019-09-24 | 6% | 2019-09-24
2018-06-30 | 2014 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  | 21785000 | N68436438; N62688913 | 2014-05-21 | 2016-12-03 | 2017-10-10 | 95% | 2018-01-26
2018-05-30 | 2018 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557601 | AIRCRAFT MAINTENANCE HANGAR #2 |  |  |  | 2018-05-30 | 2020-10-02 | 2020-10-02 | 1% | 2020-10-02
2018-06-30 | 2016 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557715 | LIVE-FIRE TRAINING RANGE COMPLEX (NW FIELD) |  |  |  | 2017-09-07 | 2020-11-26 | 2020-11-26 | 3% | 2020-11-26
2018-06-30 | 2017 | Marine Corps Active | Major Military Construction | Guam | Guam | N61755102 | POWER UPGRADE - HARMON |  |  |  | 2017-09-14 | 2020-03-18 | 2020-03-18 | 18% | 2020-03-18
2018-06-30 | 2014 | Marine Corps Reserve | Major Military Construction | Missouri | United States | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  |  |  | 2014-09-05 | 2016-06-16 | 2016-06-16 | 88% | 2018-10-31
2018-06-30 | 2016 | Marine Corps Reserve | Major Military Construction | Louisiana | United States | M68479129 | RESERVE CENTER STORAGE FACILITY |  |  |  | 2017-10-13 | 2018-09-29 | 2018-09-29 | 50% | 2018-09-29
2018-06-30 | 2015 | Marine Corps Reserve | Major Military Construction | Washington | United States | N00620234 | C-40 RESERVE MAINTENANCE HANGAR |  |  |  | 2015-08-12 | 2016-12-15 | 2017-12-01 | 95% | 2017-12-01
2018-06-30 | 2016 | Marine Corps Reserve | Unspecified Minor Military Construction | Virginia | United States | N62688652 | COMMERCIAL VEHICLE INSPECTION STATION |  |  |  | 2017-08-02 | 2018-10-12 | 2018-10-12 | 34% | 2018-10-12
2018-06-30 | 2013 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  |  |  | 2013-07-31 | 2015-08-30 | 2016-11-30 | 99% | 2017-04-13
2018-06-30 | 2014 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #2 | 646 |  |  | 2013-07-31 | 2015-08-30 | 2016-11-30 | 99% | 2017-04-13
2018-06-30 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  |  |  | 2014-07-07 | 2016-01-06 | 2016-01-06 | 100% | 2016-01-06
2018-06-30 | 2013 | Missile Defense Agency | Major Military Construction | New York | United States | 639 | In-Flight Interceptor Data Terminal Complex |  | 1801000 | 630 | 2013-08-10 | 2014-11-28 | 2015-09-12 | 100% | 2015-08-03
2018-06-30 | 2016 | Missile Defense Agency | Major Military Construction |  | Poland | 640 | Aegis Ashore Missile Defense System Complex |  |  |  | 2016-03-14 | 2018-04-13 | 2020-06-19 | 57%
2018-06-30 | 2014 | Missile Defense Agency | Major Military Construction |  | Japan | 648 | AN/TPY-2 Radar Site |  |  |  | 2014-05-27 | 2015-01-09 | 2015-02-20 | 100% | 2015-02-03
2018-06-30 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 22900000 | 646 | 2014-05-27 | 2016-05-31 | 2016-05-31 | 100% | 2016-05-04
2018-06-30 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 653 | MDC Switchgear Facility |  |  |  | 2017-08-31 | 2019-08-14 | 2019-08-14 | 4%
2018-06-30 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 657 | Long Range Discrimination Radar Complex, Phase 1 |  |  |  | 2017-06-05 | 2020-11-27 | 2020-11-27 | 30%
2018-06-30 | 2016 | Missile Defense Agency | Unspecified Minor Military Construction |  | Wake Island | 661 | Flight Test Communication Facility |  |  |  | 2016-05-25 | 2016-08-31 | 2016-11-08 | 100% | 2016-10-17
2018-06-30 | 2017 | Missile Defense Agency | Major Military Construction |  | Wake Island | 662 | Test Support Facility |  |  |  | 2018-03-20 | 2018-11-27 | 2018-11-27 | 4%
2018-06-30 | 2017 | Missile Defense Agency | Unspecified Minor Military Construction |  | Israel | 673 | Integrated Electronic Security System (IESS) Installation & Security Infrastructure Upgrades |  |  |  | 2018-08-15 | 2019-05-31 | 2019-05-31 | 3%
2018-06-30 | 2018 | Missile Defense Agency | Major Military Construction | Alaska | United States | 674 | Missile Field #4 |  |  |  | 2018-04-25 | 2021-09-30 | 2021-09-30 | 0%
2017-11-15 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | Virginia | United States | 65416 | NGA Headquarters, SCIF, All Phases |  |  |  | 2007-09-06 | 2011-12-22 | 2018-09-03 | 99% | 2011-04-19
2018-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17781 | Tordella Chilled Water Backup Storage |  |  |  | 2010-06-30 | 2011-08-20 | 2012-05-30 | 100% | 2012-05-30
2018-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17782 | R&E Chilled Water Backup Storage |  |  |  | 2011-11-07 | 2013-07-13 | 2016-02-05 | 100% | 2016-02-05
2018-03-31 | 2011 | National Security Agency | Major Military Construction | Maryland | United States | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 54500000 | Mountainview, South Campus Electrical Utility Plant | 2011-10-04 | 2014-11-30 | 2015-10-31 | 99% | 2014-11-30
2018-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 37500000 | Due to a Congressional rescission of funds | 2010-09-21 | 2014-04-18 | 2015-11-30 | 99% | 2015-10-12
2018-03-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18052 | Power & Cooling Infrastructure Upgrade |  |  |  | 2011-03-31 | 2013-02-01 | 2014-05-14 | 100% | 2014-05-14
2018-03-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18053 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-01-31 | 2013-02-01 | 2014-05-31 | 100% | 2014-05-31
2018-03-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18054 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-11-30 | 2013-02-01 | 2014-08-31 | 100% | 2014-08-31
2018-03-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II |  |  |  | 2012-05-30 | 2014-01-30 | 2015-01-16 | 100% | 2014-03-03
2018-03-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II (Phase 2) | 2 |  |  | 2013-11-26 | 2014-02-28 | 2014-04-28 | 100% | 2014-09-30
2018-03-31 | 2009 | National Security Agency | Major Military Construction | Maryland | United States | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  |  |  | 2010-09-21 | 2013-01-17 | 2014-04-18 | 99% | 2013-01-17
2018-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  |  |  | 2010-09-09 | 2011-09-26 | 2012-06-29 | 99% | 2012-06-29
2018-03-31 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview |  |  |  | 2012-11-02 | 2015-05-03 | 2015-07-28 | 99% | 2015-08-30
2018-03-31 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview | 2 |  |  | 2013-10-13 | 2014-02-14 | 2015-09-30 | 100% | 2014-04-30
2018-03-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 23994 | Whitelaw Wedge |  |  |  | 2012-07-18 | 2014-01-30 | 2014-12-23 | 100% | 2015-08-28
2018-03-31 | 2012 | National Security Agency | Major Military Construction | Maryland | United States | 24649 | High Performance Computing Center 2 |  |  |  | 2013-03-13 | 2015-09-15 | 2016-02-08 | 100% | 2016-02-08
2018-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  |  |  | 1915-11-09 | 2014-03-07 | 2015-05-04 | 99% | 2014-11-30
2018-03-31 | 2013 | National Security Agency | Major Military Construction | Maryland | United States | 26170 | East Campus Building 1 (ECB1) |  |  |  | 2013-10-24 | 2015-10-11 | 2016-11-30 | 86% | 2017-02-24
2018-03-31 | 2015 | National Security Agency | Major Military Construction | Maryland | United States | 27532 | North Campus Buildings Feeders - Phase 1 |  |  |  | 2016-09-01 | 2018-03-01 | 2018-04-26 | 10% | 2018-10-25
2018-03-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 30583 | East Campus Building 2 (ECB2) |  |  |  | 2016-07-18 | 2020-09-09 | 2020-09-09 | 1%
2018-03-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 31066 | North Campus Buildings Feeders - Phase 2 |  |  |  | 2016-11-14 | 2018-08-08 | 2018-08-08 | 1% | 2018-08-08
2018-03-31 | 2016 | National Security Agency | Major Military Construction | Georgia | United States | 31934 | ICECUBE |  |  |  | 2015-11-19 | 2016-12-31 | 2016-12-31 | 90%
2018-03-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 32122 | VCP-1 |  |  |  | 2016-06-23 | 2018-06-08 | 2018-06-08 | 0%
2018-06-30 | 2016 | Navy Active | Major Military Construction | Virginia | United States | M00264714 | ELECTRICAL DISTRIBUTION UPGRADE |  |  |  | 2016-07-28 | 2017-07-29 | 2018-02-28 | 85% | 2018-08-31
2018-06-30 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | M00318910 | BACHELOR ENLISTED QUARTERS |  |  |  | 2016-07-26 | 2018-10-31 | 2018-10-31 | 55% | 2019-01-15
2018-06-30 | 2016 | Navy Active | Major Military Construction | California | United States | M006811220 | RAW WATER PIPELINE PENDLETON TO FALLBROOK |  |  |  | 2016-12-14 | 2019-03-30 | 2019-03-30 | 48% | 2019-03-30
2018-06-30 | 2016 | Navy Active | Major Military Construction |  | Japan | M62613604 | SECURITY MODIFICATIONS - CVW5/MAG12 HQ
2018-06-30 | 2016 | Navy Active | Major Military Construction | Arizona | United States | M62974602 | AIRCRAFT MAINT. FACILITIES & APRON (SO. CALA) |  |  |  | 2017-08-10 | 2019-06-30 | 2018-04-15 | 1% | 2019-06-30
2018-06-30 | 2016 | Navy Active | Major Military Construction | North Carolina | United States | M670011346 | SIMULATOR INTEGRATION/RANGE CONTROL FACILITY |  | 199000 | N60495393 | 2016-08-12 | 2018-08-13 | 2018-09-14 | 95% | 2018-10-19
2018-06-30 | 2017 | Navy Active | Unspecified Minor Military Construction | California | United States | M673991237 | FITNESS FACILITY/B-1533 |  |  |  | 2017-08-02 | 2018-04-30 | 2018-04-30 | 95% | 2018-06-06
2018-06-30 | 2017 | Navy Active | Unspecified Minor Military Construction |  | Japan | M67400308 | ACTIVE VEHICLE BARRIER GATE 7 |  |  |  | 2017-10-08 | 2018-08-10 | 2018-08-10 | 86% | 2018-08-10
2018-06-30 | 2016 | Navy Active | Major Military Construction | Florida | United States | N00204723 | A-SCHOOL UNACCOMPANIED HOUSING (CORRY STATION) |  |  |  | 2017-07-12 | 2019-10-16 | 2019-10-16 | 14% | 2019-10-16
2018-06-30 | 2016 | Navy Active | Major Military Construction | Florida | United States | N00207334 | FLEET SUPPORT FACILITY ADDITION |  |  |  | 2016-04-01 | 2017-06-11 | 2017-08-17 | 100% | 2018-02-15
2018-06-30 | 2016 | Navy Active | Major Military Construction | Florida | United States | N00207662 | TRITON MISSION CONTROL FACILITY |  |  |  | 2016-10-11 | 2017-11-06 | 2018-11-18 | 73% | 2018-11-18
2018-06-30 | 2014 | Navy Active | Major Military Construction | Florida | United States | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  |  |  | 2014-08-29 | 2016-02-08 | 2018-01-08 | 94% | 2017-07-28
2018-06-30 | 2017 | Navy Active | Major Military Construction | California | United States | N00245312 | UPGRADE PIER 10 TO 4160 VOLT |  |  |  | 2017-07-13 | 2018-09-30 | 2018-09-30 | 13% | 2018-09-30
2018-06-30 | 2016 | Navy Active | Major Military Construction | California | United States | N00245499 | LCS SUPPORT FACILITY |  |  |  | 2016-09-12 | 2018-08-29 | 2018-09-26 | 82% | 2018-09-26
2018-06-30 | 2015 | Navy Active | Major Military Construction | California | United States | N00245800 | STEAM DISTRIBUTION SYSTEM DECENTRALIZATION |  |  |  | 2015-10-01 | 2017-10-01 | 2018-07-02 | 98% | 2018-07-02
2018-06-30 | 2017 | Navy Active | Unspecified Minor Military Construction | California | United States | N002461017 | Upgrades for MV-22 Depot Maintenance Program |  |  |  | 2017-10-12 | 2018-10-05 | 2018-10-05 | 39% | 2018-10-05
2017-09-30 | 2013 | Navy Active | Major Military Construction | California | United States | N00246730 | BACHELOR QUARTERS |  |  |  | 2015-08-13 | 2017-07-29 | 2017-09-14 | 99% | 2017-07-10
2017-09-30 | 2013 | Navy Active | Major Military Construction | California | United States | N00246909 | H-60S SIMULATOR TRAINING FACILITY |  |  |  | 2014-03-14 | 2015-03-15 | 2017-07-03 | 96% | 2017-07-03
2018-06-30 | 2017 | Navy Active | Major Military Construction | California | United States | N00246947 | COASTAL CAMPUS ENTRY CONTROL POINT |  |  |  | 2017-04-13 | 2018-10-06 | 2018-12-14 | 55% | 2018-10-06
2018-06-30 | 2017 | Navy Active | Major Military Construction | California | United States | N00246963 | GRACE HOPPER DATA CENTER POWER UPGRADES |  |  |  | 2017-04-10 | 2018-10-03 | 2018-10-03 | 6% | 2018-10-03
2018-06-30 | 2017 | Navy Active | Major Military Construction | California | United States | N00246991 | COASTAL CAMPUS UTILITIES INFRASTRUCTURE |  | 4715000 | N32414547, M62613604 | 2017-04-13 | 2019-04-23 | 2019-04-23 | 53% | 2019-04-23
2018-06-30 | 2016 | Navy Active | Major Military Construction | California | United States | N00246998 | COASTAL CAMPUS UTILITIES |  | 615000 | N62688913 | 2016-02-02 | 2018-04-02 | 2018-09-30 | 96% | 2017-09-29
2018-06-30 | 2014 | Navy Active | Major Military Construction | Washington | United States | N00620239 | EA-18G FACILITY IMPROVEMENTS |  | 1044000 | Design; M62613604 | 2014-09-08 | 2017-05-26 | 2017-08-03 | 85% | 2017-02-15
2018-06-30 | 2017 | Navy Active | Major Military Construction | Washington | United States | N00620240 | TRITON MISSION CONTROL FACILITY |  |  |  | 2017-08-23 | 2020-03-26 | 2020-05-18 | 14% | 2020-06-30
2018-06-30 | 2015 | Navy Active | Major Military Construction | Washington | United States | N00620259 | P-8A AIRCRAFT APRON AND SUPPORTING FACILITIES |  |  |  | 2017-01-04 | 2018-06-19 | 2018-06-19 | 94% | 2018-06-18
2018-06-30 | 2014 | Navy Active | Major Military Construction | Rhode Island | United States | N32411103 | HEWITT HALL RESEARCH CENTER |  |  |  | 2014-08-14 | 2015-12-16 | 2016-12-07 | 100% | 2018-05-31
2018-06-30 | 2015 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  |  |  | 2015-06-01 | 2016-11-23 | 2018-10-21 | 88% | 2018-05-17
2018-06-30 | 2015 | Navy Active | Major Military Construction | Virginia | United States | N32443527 | SUBMARINE MAINTENANCE FACILITY |  |  |  | 2015-09-17 | 2017-04-20 | 2017-07-19 | 68% | 2018-12-14
2018-06-30 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATERFRONT UTILITIES |  |  |  | 2017-12-29 | 2021-04-15 | 2021-04-15 | 5% | 2021-04-15
2018-06-30 | 2017 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATERFRONT UTILITIES | N32443614A |  |  | 2017-12-29 | 2021-04-15 | 2021-04-15 | 5% | 2021-04-15
2018-06-30 | 2014 | Navy Active | Major Military Construction | Maine | United States | N32446266 | STRUCTURAL SHOPS CONSOLIDATION |  |  |  | 2015-08-31 | 2018-01-23 | 2018-09-23 | 83% | 2019-01-18
2018-06-30 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446285 | UNACCOMPANIED HOUSING |  |  |  | 2017-07-13 | 2019-05-10 | 2019-07-07 | 12% | 2019-06-27
2018-06-30 | 2014 | Navy Active | Major Military Construction | Maine | United States | N32446308 | NCTAMS VLF COMMERCIAL POWER CONNECTION |  | 1104000 | N68436993 | 2016-05-05 | 2018-10-25 | 2018-10-25 | 77% | 2018-10-25
2018-06-30 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446371 | UTILITY IMPROVEMENTS FOR NUCLEAR PLATFORMS |  |  |  | 2018-04-13 | 2021-09-14 | 2021-09-14 | 1% | 2021-09-14
2018-06-30 | 2015 | Navy Active | Unspecified Minor Military Construction |  | Djibouti | N3379A064 | POST OFFICE FACILITY |  |  |  | 2015-09-25 | 2017-01-23 | 2017-01-23 | 100% | 2017-01-09
2018-06-30 | 2017 | Navy Active | Major Military Construction |  | Djibouti | N3379A223 | OCO: MEDICAL/DENTAL FACILITY |  |  |  | 2018-07-12 | 2020-10-05 | 2020-10-05 | 1% | 2020-10-05
2018-06-30 | 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557230 | DPRI-GSE SHOPS AT NORTH RAMP |  |  |  | 2015-12-01 | 2018-06-19 | 2018-07-03 | 77% | 2018-08-08
2018-06-30 | 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557240 | DPRI-MWSS FACILITIES AT NORTH RAMP |  |  |  | 2015-10-13 | 2018-05-02 | 2018-09-04 | 85% | 2018-05-02
2018-06-30 | 2014 | Navy Active | Major Military Construction | Guam | Guam | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  | 4519000 | N68436401 | 2014-04-10 | 2016-04-25 | 2018-09-07 | 99% | 2017-12-21
2018-06-30 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N41557635 | MUNICIPAL SOLID WASTE LANDFILL CLOSURE |  |  |  | 2017-08-15 | 2019-02-22 | 2019-04-05 | 33% | 2019-02-22
2018-06-30 | 2015 | Navy Active | Major Military Construction | South Carolina | United States | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  |  |  | 2014-09-03 | 2018-06-20 | 2019-02-27 | 69% | 2019-04-16
2018-06-30 | 2014 | Navy Active | Major Military Construction | South Carolina | United States | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  |  |  | 2014-09-03 | 2018-06-20 | 2019-02-27 | 95% | 2019-04-16
2018-06-30 | 2017 | Navy Active | Unspecified Minor Military Construction | Georgia | United States | N42237671 | SUBMARINE BRIDGE TRAINER |  |  |  | 2018-01-30 | 2019-08-23 | 2019-08-23 | 1% | 2019-08-23
2018-06-30 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N47608155 | ATLANTIC TEST RANGE FACILITY |  |  |  | 2015-10-13 | 2017-08-20 | 2017-10-24 | 96% | 2018-03-15
2018-06-30 | 2014 | Navy Active | Unspecified Minor Military Construction | Maryland | United States | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  |  |  | 2014-10-13 | 2016-09-29 | 2017-06-06 | 98% | 2016-06-06
2018-06-30 | 2017 | Navy Active | Unspecified Minor Military Construction | Maryland | United States | N47608421 | Inert Storage Building Replacement |  |  |  | 2017-10-11 | 2018-10-24 | 2018-10-24 | 8% | 2018-10-24
2018-05-30 | 2016 | Navy Active | Major Military Construction | Maryland | United States | N47608975 | UNACCOMPANIED HOUSING |  |  |  | 2018-04-27 | 2020-02-02 | 2020-02-02 | 1% | 2020-02-02
2018-06-30 | 2016 | Navy Active | Military Family Housing Improvement | Virginia | United States | N500921602 | SKEETER LANE RENOVATION & CONVERSION |  |  |  | 2018-05-31 | 2019-10-04 | 2019-10-04 | 1% | 2019-10-04
2018-06-30 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N50092176 | ACU-4 ELECTRICAL UPGRADES |  |  |  | 2018-05-03 | 2019-07-08 | 2019-07-08 | 1% | 2019-07-08
2018-06-30 | 2015 | Navy Active | Major Military Construction | Virginia | United States | N50092354 | EOD CONSOLIDATED OPS AND LOGISTICS FACILITIES |  |  |  | 2015-10-12 | 2018-10-07 | 2019-01-17 | 96% | 2019-02-01
2018-06-30 | 2016 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N50092726 | ExMCM UUV OPERATIONS AND MAINTENANCE FACILITY |  |  |  | 2016-10-13 | 2018-04-07 | 2018-05-23 | 65% | 2018-07-31
2018-06-30 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N50092H238 | CONSTRUCT HOUSING WELCOME CENTER |  |  |  | 2018-05-31 | 2019-10-04 | 2019-10-04 | 1% | 2019-10-04
2018-06-30 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N60191603 | MARITIME SURVEILLANCE SYSTEM FACILITY |  |  |  | 2016-06-29 | 2017-06-30 | 2018-03-23 | 97% | 2018-06-27
2018-06-30 | 2014 | Navy Active | Major Military Construction | Virginia | United States | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  |  |  | 2014-09-30 | 2016-10-25 | 2018-02-20 | 76% | 2019-01-31
2018-06-30 | 2017 | Navy Active | Major Military Construction | Florida | United States | N60201154 | TRITON FORWARD OPERATING BASE HANGAR |  |  |  | 2017-07-13 | 2019-09-26 | 2019-09-26 | 18% | 2019-09-26
2018-06-30 | 2015 | Navy Active | Major Military Construction | Florida | United States | N60201423 | LCS OPERATIONAL TRAINING FACILITY |  |  |  | 2016-11-29 | 2018-04-09 | 2018-04-09 | 78% | 2019-01-09
2018-06-30 | 2016 | Navy Active | Major Military Construction | Florida | United States | N60201424 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2016-07-28 | 2018-02-05 | 2018-04-29 | 87% | 2018-09-05
2018-06-30 | 2017 | Navy Active | Unspecified Minor Military Construction | Texas | United States | N60241295 | HIGH EXPLOSIVES MAGAZINES |  |  |  | 2017-06-01 | 2018-11-17 | 2018-11-17 | 80% | 2018-11-17
2018-06-30 | 2016 | Navy Active | Major Military Construction | Nevada | United States | N60495111 | NAVOPSPTCEN FALLON |  |  |  | 2017-08-31 | 2019-02-25 | 2019-07-17 | 8% | 2019-03-11
2018-06-30 | 2017 | Navy Active | Major Military Construction | Nevada | United States | N60495111 | NAVOPSPTCEN FALLON (RAA funds) | N60495111A |  |  | 2017-08-31 | 2019-02-25 | 2019-02-25 | 1% | 2019-02-25
2018-06-30 | 2014 | Navy Active | Major Military Construction | Nevada | United States | N60495393 | WASTEWATER TREATMENT PLANT |  |  |  | 2018-05-03 | 2020-05-08 | 2020-05-08 | 1% | 2020-05-08
2018-06-30 | 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495420 | AIR WING TRAINING FACILITY |  |  |  | 2015-09-30 | 2017-11-24 | 2019-03-08 | 92% | 2018-05-22
2018-06-30 | 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495430 | FACILITY ALTERATION FOR F-35 TRAINING MISSION |  |  |  | 2016-10-13 | 2017-11-23 | 2018-08-22 | 80% | 2018-08-21
2018-06-30 | 2016 | Navy Active | Major Military Construction | Florida | United States | N60508274 | T-6B JPATS TRAINING OPERATIONS FACILITY |  |  |  | 2016-07-04 | 2018-03-24 | 2018-11-30 | 38% | 2018-10-19
2018-06-30 | 2017 | Navy Active | Major Military Construction | Florida | United States | N60508926 | WMD FIELD TRAINING FACILITIES |  |  |  | 2017-05-05 | 2019-06-24 | 2019-06-24 | 1% | 2019-06-24
2018-06-30 | 2014 | Navy Active | Major Military Construction |  | Japan | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  |  |  | 2014-10-03 | 2017-01-17 | 2017-01-17 | 7% | 2017-01-17
2018-06-30 | 2016 | Navy Active | Major Military Construction |  | Japan | N61054023 | CHILD DEVELOPMENT CENTER |  |  |  | 2017-01-02 | 2018-09-30 | 2018-09-30 | 1% | 2018-12-31
2018-06-30 | 2016 | Navy Active | Unspecified Minor Military Construction |  | Japan | N61054027 | CYBER MISSION FORCE SCIF CONSTRUCTION |  |  |  | 2017-06-08 | 2017-11-21 | 2017-11-21 | 1% | 2017-11-21
2018-06-30 | 2017 | Navy Active | Unspecified Minor Military Construction |  | Japan | N61056526 | PERSONNEL SUPPORT WAREHOUSE |  |  |  | 2018-01-24 | 2019-02-11 | 2019-02-11 | 1% | 2019-02-11
2018-06-30 | 2017 | Navy Active | Major Military Construction |  | Japan | N61058325 | SHORE POWER (JULIET PIER) |  |  |  | 2017-06-09 | 2019-08-14 | 2019-08-14 | 1% | 2019-08-14
2018-06-30 | 2014 | Navy Active | Major Military Construction | California | United States | N61065202 | NOSC MORENO VALLEY RESERVE TRAINING CENTER |  |  |  | 2016-09-12 | 2018-06-10 | 2018-06-10 | 14% | 2018-06-10
2018-06-30 | 2017 | Navy Active | Major Military Construction | California | United States | N61065223 | MISSILE MAGAZINES |  |  |  | 2017-05-11 | 2019-10-29 | 2019-10-29 | 24% | 2019-10-29
2018-06-30 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX, PHASE 2 |  |  |  | 2017-05-11 | 2019-09-06 | 2021-02-11 | 13% | 2019-09-06
2018-06-30 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX PH 2 | N61151190A |  |  | 2017-05-11 | 2020-01-13 | 2020-01-13 | 1% | 2020-01-13
2018-06-30 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151287 | MISSILE SUPPORT FACILITY |  |  |  | 2015-09-16 | 2017-07-17 | 2018-08-20 | 97% | 2018-08-10
2018-06-30 | 2014 | Navy Active | Major Military Construction | Maryland | United States | N61152001 | MARFORCYBERCOM HQ-OPS BUILDING |  |  |  | 2015-04-27 | 2017-05-05 | 2017-05-05 | 96% | 2017-05-05
2018-06-30 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61152621 | CYBER SECURITY STUDIES BUILDING |  |  |  | 2016-04-14 | 2019-09-08 | 2019-09-09 | 48% | 2019-09-08
2018-06-30 | 2014 | Navy Active | Military Family Housing Improvement | Guam | Guam | N617551403 | WHOLE HOUSE REVITALIZATION PHASE II AT LOCKWOOD TERRACE |  |  |  | 2015-05-14 | 2017-08-13 | 2018-02-28 | 94% | 2018-01-11
2018-06-30 | 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755425 | MODULAR STORAGE MAGAZINE |  | 4636000 | N62688913 | 2014-05-26 | 2016-06-11 | 2017-08-28 | 91% | 2018-06-30
2018-06-30 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N61755535 | SANITARY SEWER SYSTEM RECAPITALIZATION |  |  |  | 2017-09-04 | 2020-01-03 | 2020-01-03 | 14% | 2020-01-03
2018-06-30 | 2017 | Navy Active | Major Military Construction | Guam | Guam | N61755652 | HARDENING OF GUAM POL INFRASTRUCTURE |  |  |  | 2018-06-06 | 2020-04-03 | 2020-04-03 | 1% | 2020-04-03
2018-06-30 | 2016 | Navy Active | Unspecified Minor Military Construction | Guam | Guam | N61755656 | HEAVY WEATHER MOORING SIERRA WHARF, GUAM |  |  |  | 2016-09-29 | 2017-07-13 | 2018-03-03 | 96% | 2018-06-06
2018-06-30 | 2016 | Navy Active | Major Military Construction |  | Poland | N62592401 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  |  |  | 2016-05-20 | 2017-11-09 | 2019-11-05 | 80% | 2019-11-05
2018-06-30 | 2014 | Navy Active | Major Military Construction | Virginia | United States | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  |  |  | 2014-07-14 | 2016-01-01 | 2018-06-11 | 89% | 2018-06-11
2018-06-30 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688518 | MH-60 HELICOPTER TRAINING FACILITY |  |  |  | 2016-03-17 | 2017-09-29 | 2018-06-20 | 75% | 2018-06-20
2018-06-30 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688610 | ELECTRICAL REPAIRS TO PIERS 2,6,7, AND 11 |  |  |  | 2017-09-14 | 2019-10-25 | 2019-10-25 | 1% | 2019-10-25
2018-05-30 | 2018 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N62688762 | SUBMARINE UMM ANTENNA MAINTENANCE TOWER |  |  |  | 2018-05-16 | 2019-07-02 | 2019-07-02 | 1% | 2019-07-02
2018-06-30 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688913 | COMMUNICATIONS CENTER |  |  |  | 2018-05-07 | 2020-11-01 | 2020-11-01 | 1% | 2020-11-01
2018-06-30 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | N62813036 | WELDING SCHOOL SHOP CONSOLIDATION |  |  |  | 2016-02-09 | 2018-03-26 | 2018-04-29 | 16% | 2019-05-31
2018-06-30 | 2015 | Navy Active | Major Military Construction | Hawaii | United States | N62813048 | SUBMARINE MANEUVERING ROOM TRAINER FACILITY |  |  |  | 2015-03-13 | 2016-10-04 | 2017-02-10 | 90% | 2017-02-08
2018-06-30 | 2014 | Navy Active | Unspecified Minor Military Construction | Hawaii | United States | N62813058 | ROCKFALL PROTECTION AT RED HILL |  |  |  | 2014-12-08 | 2016-05-18 | 2016-05-18 | 11% | 2018-12-31
2018-06-30 | 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813270 | DRYDOCK WATERFRONT FACILITY |  |  |  | 2014-03-31 | 2015-12-08 | 2018-07-31 | 84% | 2018-07-30
2018-06-30 | 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  |  |  | 2014-07-14 | 2017-08-03 | 2018-06-17 | 91% | 2018-08-01
2018-06-30 | 2017 | Navy Active | Major Military Construction |  | Spain | N62863621 | COMMUNICATION STATION |  |  |  | 2017-09-14 | 2023-02-13 | 2023-02-13 | 19% | 2023-02-13
2018-06-30 | 2015 | Navy Active | Major Military Construction |  | Spain | N62863712 | SHIP BERTHING POWER UPGRADES |  |  |  | 2015-12-04 | 2018-05-23 | 2018-05-23 | 82% | 2019-01-29
2018-06-30 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995407 | TRITON HANGAR AND OPERATION FACILITY |  | 4099000 | N32414547 | 2016-12-06 | 2019-04-23 | 2019-07-10 | 6% | 2020-03-31
2018-06-30 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995655 | P-8A HANGAR AND FLEET SUPPORT FACILITY |  |  |  | 2016-12-06 | 2019-04-23 | 2019-07-10 | 20% | 2020-03-31
2018-06-30 | 2017 | Navy Active | Major Military Construction |  | Italy | N62995737 | UPGRADE ENTRY CONTROL POINT |  |  |  | 2017-03-14 | 2018-08-22 | 2018-08-22 | 21% | 2019-01-17
2018-06-30 | 2015 | Navy Active | Major Military Construction |  | Bahrain | N63005955 | P-8A HANGAR |  | 4857000 | N68436993; Design | 2015-09-30 | 2018-11-09 | 2018-11-09 | 75% | 2018-11-09
2017-09-30 | 2013 | Navy Active | Major Military Construction |  | Bahrain | N63005960 | BAMS OPERATIONAL FACILITIES |  |  |  | 2017-07-13 | 2019-12-23 | 2019-12-23 | 1% | 2019-12-23
2018-06-30 | 2016 | Navy Active | Major Military Construction |  | Bahrain | N63005970 | SHIP MAINTENANCE SUPPORT FACILITY |  | 5715000 | N62688913 | 2016-06-05 | 2018-11-06 | 2018-11-06 | 28% | 2018-07-06
2018-06-30 | 2016 | Navy Active | Major Military Construction |  | Bahrain | N63005976 | MINA SALMAN PIER REPLACEMENT
2018-06-30 | 2016 | Navy Active | Major Military Construction | California | United States | N63042218 | RTO AND MISSION DEBRIEF FACILITY |  |  |  | 2016-05-24 | 2017-11-16 | 2017-11-16 | 16% | 2017-11-16
2018-06-30 | 2015 | Navy Active | Major Military Construction | California | United States | N63042327 | F-35C OPERATIONAL TRAINING FACILITY |  |  |  | 2015-07-10 | 2016-10-17 | 2018-03-02 | 98% | 2017-02-10
2018-06-30 | 2015 | Navy Active | Major Military Construction | California | United States | N63042328 | F-35C FACILITY ADDITION AND MODIFICATION |  |  |  | 2015-06-25 | 2016-11-03 | 2018-04-20 | 98% | 2016-12-14
2018-06-30 | 2015 | Navy Active | Unspecified Minor Military Construction | California | United States | N63042377 | CARRIER AIR WING FOURTEEN (CVW-14) FACILITY |  |  |  | 2016-03-11 | 2016-05-26 | 2020-05-21 | 99% | 2017-04-30
2018-06-30 | 2016 | Navy Active | Major Military Construction | California | United States | N63042378 | F-35C HANGAR MODERNIZATION AND ADDITION |  |  |  | 2016-06-14 | 2017-12-07 | 2018-06-16 | 76% | 2018-02-28
2018-06-30 | 2016 | Navy Active | Major Military Construction | California | United States | N63042379 | F-35C TRAINING FACILITIES |  | 200000 | N62688913 | 2016-03-31 | 2017-03-31 | 2017-03-31 | 88% | 2017-05-23
2018-06-30 | 2017 | Navy Active | Major Military Construction | California | United States | N63042380 | F-35C ENGINE REPAIR FACILITY |  |  |  | 2017-04-14 | 2018-06-24 | 2018-08-25 | 78% | 2018-06-24
2018-05-30 | 2018 | Navy Active | Unspecified Minor Military Construction | California | United States | N63042394 | SECURITY UPGRADES TO AIRCRAFT SIMULATOR FACILITY |  |  |  | 2018-06-14 | 2019-08-30 | 2019-08-30 | 1% | 2019-08-30
2017-09-30 | 2013 | Navy Active | Major Military Construction |  | Greece | N66691908 | INTERMODAL ACCESS ROAD |  |  |  | 2016-08-25 | 2017-11-24 | 2018-04-04 | 44% | 2018-04-04
2018-06-30 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436401 | REGIONAL SHIP MAINTENANCE SUPPORT FACILITY |  |  |  | 2017-10-10 | 2020-01-04 | 2020-01-04 | 8% | 2020-01-04
2018-06-30 | 2014 | Navy Active | Major Military Construction | Washington | United States | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  | 6136000 | Design; N62688913 | 2014-08-01 | 2016-02-16 | 2016-11-16 | 95% | 2017-08-22
2018-06-30 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436422 | INTEGRATED WATER TREATMENT SYSTEM DD 1, 2 & 5 |  | 3890000 | Design; N68436993; N62688913 | 2015-05-18 | 2016-10-25 | 2016-10-25 | 82% | 2017-08-18
2018-06-30 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436431 | DRY DOCK 6 MODERNIZATION & UTILITY IMPROVE. |  |  |  | 2016-08-25 | 2017-11-14 | 2017-11-14 | 66% | 2018-08-01
2018-06-30 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436438 | NUCLEAR REPAIR FACILITY |  |  |  | 2018-05-07 | 2019-10-30 | 2019-10-30 | 1% | 2019-10-30
2018-06-30 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436876 | SERVICE PIER ELECTRICAL UPGRADES |  |  |  | 2017-12-14 | 2019-03-25 | 2019-03-25 | 27% | 2019-03-25
2018-06-30 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436983 | WRA LAND/WATER INTERFACE |  |  |  | 2016-10-05 | 2018-02-13 | 2019-03-27 | 19% | 2019-03-27
2017-09-30 | 2013 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | N68436990A |  |  | 2012-11-15 | 2016-01-09 | 2017-09-30 | 95% | 2016-12-23
2018-06-30 | 2014 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990B |  |  | 2013-12-16 | 2016-01-09 | 2017-09-30 | 69% | 2016-12-23
2018-06-30 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 - INC 4 | N68436990C | 2728000 | M67399222; N68436993 | 2015-01-22 | 2016-01-09 | 2017-09-30 | 95% | 2016-12-23
2018-06-30 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436993 | TPS PORT ANGELES FORWARD OPERATING LOCATION |  |  |  | 2016-09-13 | 2018-02-06 | 2018-07-31 | 88% | 2018-09-03
2018-06-30 | 2015 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY |  |  |  | 2017-11-16 | 2019-11-15 | 2019-11-15 | 1% | 2019-11-15
2018-06-30 | 2018 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY | N68469275A |  |  | 2017-11-16 | 2019-11-15 | 2019-11-15 | 2% | 2019-11-15
2018-06-30 | 2014 | Navy Active | Major Military Construction | Virginia | United States | N69212461 | SMALL ARMS RANGES |  |  |  | 2015-10-13 | 2017-02-25 | 2018-04-16 | 99% | 2018-04-16
2018-06-30 | 2015 | Navy Active | Major Military Construction | Virginia | United States | N69212991 | BACHELOR ENLISTED QUARTERS |  |  |  | 2016-03-22 | 2018-03-23 | 2018-04-21 | 78% | 2018-11-10
2018-06-30 | 2015 | Navy Active | Major Military Construction | Virginia | United States | N69212992 | FAST COMPANY TRAINING FACILITY |  |  |  | 2015-10-13 | 2016-09-28 | 2018-09-28 | 73% | 2016-09-28
2018-06-30 | 2014 | Navy Active | Major Military Construction | California | United States | N69232593 | BAMS CONSOLIDATED MAINTENANCE HANGAR |  |  |  | 2015-01-30 | 2016-09-17 | 2017-10-12 | 100% | 2018-04-02
2018-06-30 | 2016 | Navy Active | Major Military Construction | California | United States | N69232607 | TRITON AVIONICS AND FUEL SYSTEMS TRAINER |  |  |  | 2016-09-08 | 2017-11-08 | 2018-03-10 | 98% | 2018-03-10
2018-06-30 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Connecticut | United States | N00129664 | CORIVRON 8 RESERVE HVU DET SUPPORT FACILITIES |  |  |  | 2015-09-08 | 2016-09-08 | 2017-04-21 | 98% | 2017-07-14
2018-06-30 | 2017 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206500 | JOINT RESERVE INTELLIGENCE CENTER |  |  |  | 2017-07-13 | 2019-07-27 | 2019-08-06 | 25% | 2019-10-23
2018-06-30 | 2016 | Navy Reserve | Unspecified Minor Military Construction | Louisiana | United States | N00206509 | POLICE STATION ADDITION |  |  |  | 2016-10-14 | 2017-09-29 | 2017-09-30 | 99% | 2018-02-20
2017-09-30 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Florida | United States | N00207278 | CRS 10 BOAT MAINTENANCE FACILITY |  |  |  | 2015-10-14 | 2016-10-14 | 2017-07-21 | 95% | 2017-07-20
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | Kentucky | United States | 36977 | System Integration Maintenance Office Facility |  |  |  | 2015-09-10 | 2017-03-03 | 2017-10-17 | 98% | 2017-10-01
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | Colorado | United States | 47942 | Language Training Facility |  |  |  | 2016-07-08 | 2017-03-01 | 2018-08-03 | 78%
2018-04-01 | 2013 | Special Operations Command | Major Military Construction | Arizona | United States | 53542 | Parachute Training Facility |  |  |  | 2014-11-09 | 2016-02-07 | 2016-02-20 | 100%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | Georgia | United States | 57442 | SOF Company Operations Facility |  |  |  | 2017-04-27 | 2018-10-19 | 2019-04-18 | 36%
2018-04-01 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 61064 | SOF Upgrade Training Facility |  |  |  | 2014-11-17 | 2016-05-10 | 2016-10-20 | 100%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction | Georgia | United States | 61065 | TUAV Maintenance Facility |  |  |  | 2017-09-25 | 2018-11-24 | 2019-03-01 | 19%
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 68526 | SOF Engineer Training Facility |  |  |  | 2015-05-27 | 2016-11-17 | 2017-04-20 | 99% | 2017-04-17
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | Washington | United States | 69257 | SOF Military Working Dog Kennel |  |  |  | 2015-05-04 | 2016-09-15 | 2016-12-23 | 99% | 2017-03-24
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69287a | Battalion Operations Complex |  |  |  | 2013-10-09 | 2015-05-13 | 2015-10-30 | 99%
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69287b | Battalion Operations Complex |  |  |  | 2014-11-20 | 2016-12-02 | 2017-01-09 | 99%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 69302 | SOF Battalion Operations Facility |  |  |  | 2017-05-17 | 2019-05-07 | 2019-11-03 | 23%
2018-05-01 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69382 | Civil Affairs Battalion Complex |  |  |  | 2013-10-16 | 2015-08-14 | 2015-09-21 | 100% | 2015-11-04
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | Washington | United States | 69445 | SOF Battalion Operations Facility |  |  |  | 2015-06-30 | 2017-05-25 | 2018-05-18 | 97%
2018-05-01 | 2014 | Special Operations Command | Major Military Construction | Colorado | United States | 69446 | Group Support Battalion |  |  |  | 2014-08-27 | 2016-02-08 | 2016-06-09 | 100% | 2016-06-17
2018-05-01 | 2013 | Special Operations Command | Major Military Construction | Kentucky | United States | 69447 | Group Support Battalion Detachment |  |  |  | 2014-04-14 | 2016-02-13 | 2016-02-15 | 100% | 2016-02-15
2018-05-01 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69458 | Battalion Operations Complex |  | 1738000 | 69445 | 2012-12-10 | 2014-06-03 | 2015-01-03 | 100% | 2015-01-03
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69493 | Sustainment Bde Headquarters |  |  |  | 2014-06-18 | 2016-07-18 | 2016-12-16 | 99% | 2016-12-16
2018-07-13 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69758 | Brigade Headquarters |  |  |  | 2012-11-14 | 2014-05-08 | 2014-10-11 | 97% | 2016-12-06
2018-05-01 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 71224 | Group Headquarters |  | 2896000 | 68526 | 2012-11-07 | 2014-05-01 | 2017-06-02 | 100% | 2015-04-27
2018-07-13 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 76364 | Battalion Operations Facility |  | 5000000 | 69445 | 2012-12-04 | 2014-08-26 | 2015-04-17 | 99% | 2016-04-21
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | Kentucky | United States | 76365 | Group Special Troops Battalion |  |  |  | 2015-12-02 | 2017-10-02 | 2017-12-19 | 99%
2018-05-01 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76366 | Company Operations Facility (GSTB) |  |  |  | 2012-09-12 | 2015-09-12 | 2016-03-02 | 100% | 2016-03-02
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | Colorado | United States | 76367 | SOF Battalion Operations Complex |  |  |  | 2014-09-04 | 2016-07-20 | 2018-07-31 | 89%
2018-05-01 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76371 | Company Operations Facility (GSB) |  |  |  | 2012-09-12 | 2015-09-12 | 2016-03-02 | 100% | 2016-03-02
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76375 | Civil Affairs Battalion Annexes |  |  |  | 2014-12-01 | 2016-07-23 | 2015-08-07 | 99% | 2017-08-29
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76376 | Language and Cultural Center |  |  |  | 2015-01-09 | 2017-06-27 | 2018-01-19 | 99%
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 76513 | Special Tactics Facility, Phase 2 |  |  |  | 2017-09-19 | 2019-12-18 | 2020-05-16 | 9%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 76514 | SOF Special Tactics Facility, Ph 3 |  |  |  | 2018-05-05 | 2020-03-18 | 2020-08-15 | 0%
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 76518 | SOF Indoor Range |  |  |  | 2016-05-17 | 2016-05-17 | 2018-02-09 | 99%
2018-07-13 | 2014 | Special Operations Command | Major Military Construction |  | Japan | 78024 | Facility Augmentation |  |  |  | 2015-07-01 | 2017-12-12 | 2018-04-05 | 95%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79437 | SOF Training Command Building |  |  |  | 2016-10-28 | 2018-10-18 | 2019-10-19 | 21%
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 79438 | Combat Medic Skills Sustainment Course Bldg |  |  |  | 2014-10-27 | 2016-04-19 | 2016-10-07 | 99% | 2016-12-14
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | 79440 | SOF BOAT DOCKS |  |  |  | 2015-05-14 | 2016-08-22 | 2018-08-31 | 59%
2018-05-01 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79456 | SOF Tactical Equipment Maintenance Facility (TEMF) |  |  |  | 2015-05-21 | 2017-09-27 | 2017-02-13 | 99% | 2017-03-17
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 80773 | SOF Battalion Operations Facility |  |  |  | 2017-01-31 | 2019-01-31 | 2019-07-30 | 75%
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | Kentucky | United States | 81897 | Company Operations Headquarters |  |  |  | 2017-01-03 | 2018-08-26 | 2018-12-19 | 60%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction |  | Japan | AFSOC103022 | Airfield Apron |  |  |  | 2018-03-20 | 2019-02-04 | 2019-03-06 | 0%
2018-05-01 | 2011 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 7132000 | 66362 | 2012-09-06 | 2013-07-17 | 2014-06-03 | 100% | 2014-06-03
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ083021 | SOF 551 SOS Sq Ops Facility |  |  |  | 2017-03-23 | 2018-11-13 | 2018-11-18 | 86%
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | Florida | United States | FTEV073010 | SOF Fuel Cell Maintenance Facility |  |  |  | 2016-09-15 | 2018-09-15 | 2019-01-05 | 39%
2018-05-01 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | FTEV083002 | Add/Alter Operations Facility |  |  |  | 2014-09-02 | 2016-05-24 | 2016-10-14 | 100% | 2016-12-28
2018-05-01 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | FTFA113004 | SOF AvFID Ops and MX Facilities |  |  |  | 2013-11-05 | 2016-12-25 | 2017-05-26 | 99% | 2017-05-26
2018-05-01 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | NVZR083702 | Joint Special Operations University Facility |  |  |  | 2013-11-04 | 2015-06-28 | 2016-09-30 | 100% | 2016-09-30
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | Florida | United States | NVZR143703 | SOF Operations Support Facility |  |  |  | 2016-10-18 | 2019-01-26 | 2019-03-17 | 87%
2018-02-15 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-1119 | SOF COMMUNICATION / ELECTRONICS MAINTENANCE FACILITY |  |  |  | 2015-10-13 | 2016-04-06 | 2017-04-06 | 100% | 2017-04-06
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | California | United States | P-1126 | SOF COMBAT SERVICE SUPPORT FACILITY |  |  |  | 2016-08-22 | 2018-02-14 | 2018-03-20 | 90%
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1218 | SOF MARINE BATTALION COMPANY/TEAM FACILITIES |  |  |  | 2013-10-03 | 2016-01-18 | 2018-01-31 | 98%
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1219 | SOF Comm / Electronics Maintenance Facility |  |  |  | 2018-01-11 | 2020-01-12 | 2020-01-12 | 2%
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1288 | SOF Combat Support Service Facility |  |  |  | 2018-01-11 | 2020-01-12 | 2020-01-12 | 2%
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1393 | SOF SURVIVAL EVASION RESISTANCE ESCAPE TRAINING FACILITY |  |  |  | 2013-10-03 | 2016-01-18 | 2018-01-31 | 98%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1396 | SOF INTEL OPS EXPANSION |  |  |  | 2015-08-31 | 2017-03-09 | 2017-10-27 | 83%
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1410 | SOF EOD Expansion |  |  |  | 2013-10-10 | 2014-09-22 | 2015-06-30 | 99%
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P-157 | SOF HUMAN PERFORMANCE CENTER |  |  |  | 2016-03-11 | 2017-09-03 | 2018-06-12 | 74%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | P-166 | QDR SOF MOBILE COMMUNICATIONS DET SUPPORT FACILITY |  |  |  | 2015-10-05 | 2017-07-17 | 2017-11-30 | 83%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | Mississippi | United States | P-170 | SOF NAVSCIATTS APPLIED INSTRUCTION FACILITY |  |  |  | 2016-02-09 | 2017-10-17 | 2018-05-21 | 94%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | P-183 | SOF INDOOR DYNAMIC RANGE |  |  |  | 2014-05-01 | 2017-07-24 | 2017-07-24 | 92%
2018-07-13 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P-334 | SOF LOGSU TWO OPERATIONS FACILITY |  |  |  | 2016-02-24 | 2018-07-29 | 2018-09-26 | 44%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | Nevada | United States | P-418 | SOF TACTICAL GROUND MOBILITY VEHICLE MAINTENANCE FACILITY |  |  |  | 2015-09-01 | 2017-02-23 | 2018-02-12 | 92%
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | Hawaii | United States | P-475 | SOF-SDVT-1 WATERFRONT OPERATIONS FACILITY |  |  |  | 2016-02-08 | 2018-02-13 | 2018-06-09 | 77%
2018-07-13 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P-576 | SOF KNOWN DISTANCE RANGE TOWER |  |  |  | 2016-07-29 | 2016-08-14 | 2018-01-03 | 96%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-776 | SOF LOGSU ONE OPERATIONS FACILITY #1 |  |  |  | 2015-10-14 | 2017-10-23 | 2019-03-07 | 65%
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-876 | SOF INDOOR DYNAMIC SHOOTING FACILITY |  |  |  | 2014-10-10 | 2016-10-07 | 2017-08-11 | 99%
2018-07-13 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-888 | SOF CLOSE QUARTERS COMBAT AND DYNAMIC SHOOTING FACILITY (LA POSTA) |  |  |  | 2014-10-14 | 2016-09-29 | 2017-11-08 | 41%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-889 | SOF SEAL Team Ops Facility |  |  |  | 2017-10-12 | 2020-03-31 | 2020-03-31 | 9%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-890 | SOF SEAL Team Ops Facility |  |  |  | 2017-10-12 | 2020-03-31 | 2020-03-31 | 9%
2018-07-13 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-893 | SOF SUPPORT ACTIVITY OPERATIONS FACILITY #2 |  |  |  | 2015-10-14 | 2018-04-02 | 2018-07-16 | 84%
2018-02-15 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-915 | SOF MOBILE COMMUNICATIONS DETACHMENT SUPPORT FACILITY |  |  |  | 2015-09-24 | 2017-08-28 | 2017-08-28 | 97%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-919 | SOF Special RECON Team One Operations Facility |  |  |  | 2017-04-13 | 2018-10-22 | 2018-10-22 | 31%
2018-07-13 | 2016 | Special Operations Command | Major Military Construction | California | United States | P-920 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #2 |  |  |  | 2016-10-04 | 2018-10-13 | 2018-12-04 | 51%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-952 | SOF Human Performance Training Center |  |  |  | 2017-08-24 | 2019-11-22 | 2019-11-22 | 8%
2018-07-13 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-966 | SOF TRADET One Operations Facility |  |  |  | 2017-10-12 | 2020-04-19 | 2020-04-19 | 9%
2018-06-15 | 2010 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80001 | Pentagon Electrical Upgrade |  |  |  | 2013-11-07 | 2015-02-05 | 2019-04-04 | 1% | 2019-04-04
2018-06-15 | 2011 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80002 | Power Plant Modernization Phase 3 (WPP) |  | 4331051 | Budget Sequester: $4,001,00 Reprogramming: $330,051 to project 80003 | 2013-04-22 | 2016-05-11 | 2018-08-17 | 92% | 2018-08-17
2017-04-20 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80003 | Metro Entrance Facility/Visitor Screening Facility |  |  |  | 2013-11-01 | 2015-05-03 | 2016-08-30 | 99% | 2016-04-01
2018-06-15 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80004 | Secure Access Lane (SAL) |  |  |  | 2016-10-25 | 2018-05-18 | 2019-06-30 | 16% | 2019-06-30
2016-12-15 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80005 | Pentagon Heliport Control Tower/Fire Station |  | 798000 | Budget Sequester
2016-12-15 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80006 | Pentagon Memorial Pedestrian Plaza |  | 2285000 | $176,000 Budget Sequester $409,000 to 80003 $1.7M to 80004
2018-06-15 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80007 | PFPA Support Operations Center
2018-06-15 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80008 | Boundary Channel Access Control Point |  |  |  | 2016-06-01 | 2017-12-01 | 2018-12-18 | 57% | 2018-12-18
2018-06-15 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80009 | Raven Rock Admin Facility Upgrade |  | 500000 | Reprogramming: $500,000 to project 80002 | 2017-02-15 | 2019-10-21 | 2019-10-02 | 15% | 2019-10-02
2018-06-15 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80010 | Raven Rock Exterior Cooling Towers |  | 3929000 | Reprogramming: to project 80001
2018-06-15 | 2015 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80011 | Redundant Chilled Water Loop
2018-06-15 | 2017 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80916 | Pentagon Metro Entrance Facility.
2018-06-15 | 2017 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 87744 | Upgrade IT Facilities Infrastructure RRMC

## CONTRACTS
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Prime Contract Number | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date
2018-07-11 | 2009 | Air Force Active | ACC093972 |  | 2009-07-02 | 2009-09-01 | RED HORSE | RED HORSE | 13100000 | 13100000 | 2011-02-28 | 2011-02-28
2018-07-11 | 2018 | Air Force Active | ACC123301 |  | 2017-11-09 | 2018-06-27 | HHI Corporation | W9128F18C0011 | 12214241 | 12214241 | 2020-01-18 | 2020-01-18
2018-07-11 | 2016 | Air Force Active | AFAF140005 |  | 2016-02-29 | 2016-03-30 | LOGCAP - FLUOR | W52P1J07D00080013 | 9071647 | 9071647 | 2016-10-27 | 2018-08-14
2018-07-11 | 2016 | Air Force Active | AFAF140005 |  | 2016-02-11 | 2016-03-01 | RED HORSE | REDHORSE1640005 | 24606000 | 24606000 | 2017-12-21 | 2018-08-14
2018-07-11 | 2016 | Air Force Active | AFAF140005 |  | 2016-05-18 | 2016-06-17 | AFCAP - FLUOR | FA805115D00020003 | 2922353 | 2922353 | 2018-01-31 | 2018-08-14
2018-07-11 | 2016 | Air Force Active | AGGN143005A |  | 2015-09-18 | 2016-03-24 | The Ross Group Construct Org | W912BV16C0016 | 9290840 | 9506956 | 2017-07-16 | 2018-03-08
2018-07-11 | 2017 | Air Force Active | AGGN173001 |  | 2017-01-06 | 2017-07-06 | SGS, LLC | W912BV17C0010 | 10428748 | 10428748 | 2018-12-01 | 2018-12-01
2018-07-11 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 89918305 | 92040285 | 2017-04-16 | 2020-05-03
2018-07-11 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 96616619 | 101269359 | 2017-03-22 | 2018-09-03
2018-07-11 | 2015 | Air Force Active | AJJY133028 |  | 2016-06-01 | 2016-09-30 | Pernix Guam, LLC | N6274216C1309 | 26463336 | 27162460 | 2018-10-20 | 2019-07-04
2018-07-11 | 2016 | Air Force Active | AJJY143030 |  | 2017-01-03 | 2017-02-02 | International Archaeology, LLC | N6274215D18190010 | 188603 | 188603 | 2017-03-19 | 2018-07-20
2018-07-11 | 2016 | Air Force Active | AJJY143030 |  | 2016-06-03 | 2016-09-02 | Reliable Builders, Inc. | N4019216D2704 | 5790000 | 5937876 | 2018-03-26 | 2018-07-20
2018-07-11 | 2014 | Air Force Active | AJJY143760 |  | 2014-12-23 | 2015-01-22 | Environet Inc. | N4019210D00040012 | 101676 | 101676 | 2015-03-25 | 2019-12-11
2018-07-11 | 2014 | Air Force Active | AJJY143760 |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907700 | 20265076 | 2016-03-30 | 2019-12-11
2018-07-11 | 2016 | Air Force Active | AJJY150600 |  | 2017-08-23 | 2018-01-23 | Reliable Builders Incorporated | N4019218C1301 | 19970000 | 19970000 | 2019-11-22 | 2019-11-22
2018-07-11 | 2016 | Air Force Active | AJJY163004 |  | 2017-05-19 | 2017-08-31 | Tikigaq Construction LLC | N4019216D2706 | 13241000 | 13241000 | 2019-05-13 | 2019-05-13
2018-07-11 | 2017 | Air Force Active | AJXF093000 |  | 2017-08-02 | 2018-05-24 | ED IF IC E, LLC | N4008017D0009 | 11179388 | 11179388 | 2020-03-26 | 2020-02-25
2018-07-11 | 2014 | Air Force Active | AJXF103010 |  | 2014-08-15 | 2014-12-30 | The Haskell Company | N4008010D04910002 | 21754670 | 22683370 | 2017-04-05 | 2018-09-03
2018-03-13 | 2011 | Air Force Active | ALUA110032 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730623 | 793254 | 2014-12-06 | 2018-08-16
2018-03-13 | 2011 | Air Force Active | ALUA113002 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557438 | 801303 | 2014-12-06 | 2018-08-16
2018-03-13 | 2011 | Air Force Active | ALUA113005 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572399 | 796006 | 2014-12-06 | 2018-08-16
2018-03-13 | 2011 | Air Force Active | ALUA113006 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573056 | 647441 | 2014-12-06 | 2018-08-16
2018-03-13 | 2011 | Air Force Active | ALUA113009 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615612 | 234861 | 2014-12-06 | 2018-08-16
2018-03-13 | 2011 | Air Force Active | ALUA113010 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216400 | 755973 | 2014-12-06 | 2018-08-16
2018-03-13 | 2011 | Air Force Active | ALUA113012 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615533 | 788620 | 2014-12-06 | 2018-08-16
2018-03-13 | 2012 | Air Force Active | ALUA113026 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511518 | 605547 | 2014-12-06 | 2018-08-16
2018-06-11 | 2016 | Air Force Active | AMAB120001 |  | 2015-10-02 | 2016-06-15 | American International Contractors Inc. | W192ER11D00010008 | 24448000 | 24446352 | 2018-05-13
2018-07-11 | 2013 | Air Force Active | ASHE103001 |  | 2014-03-06 | 2015-02-26 | Coop Muratori & Cementisti CMC Di Ravenn | N6247015C5005 | 1780234 | 1819821 | 2016-12-02 | 2016-12-06
2018-07-11 | 2015 | Air Force Active | ASHE143006 |  | 2016-11-03 | 2017-07-24 | BB Government Services Srl | N3319117C1234 | 1147724 | 1147724 | 2019-02-02 | 2019-02-02
2018-07-11 | 2017 | Air Force Active | AWUB105003 |  | 2017-07-25 | 2018-06-21 | Optimum Construction | N6945018C2105 | 3370433 | 3370433 | 2019-10-13 | 2019-10-13
2018-07-11 | 2014 | Air Force Active | BAEY143000 |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699643 | 56449102 | 2016-11-04 | 2018-04-30
2018-07-11 | 2011 | Air Force Active | BAGR113023 |  | 2011-10-28 | 2011-11-12 | RED HORSE | RED HORSE | 722000 | 722000 | 2012-11-13 | 2012-11-13
2018-07-11 | 2017 | Air Force Active | CADJ170001 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 3194454 | 3194454 | 2019-12-01 | 2019-12-01
2018-07-11 | 2017 | Air Force Active | CADJ170002 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 4911856 | 4911856 | 2019-12-01 | 2019-12-01
2018-07-11 | 2017 | Air Force Active | CRWU063008 |  | 2017-08-14 | 2017-12-07 | Federal Contracting dba Bryan Const | W9128F18C0003 | 10590013 | 10590013 | 2019-07-02 | 2019-07-02
2018-05-11 | 2014 | Air Force Active | CZQZ073050 |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC | W912PP14C0020 | 19716709 | 19812313 | 2016-08-21 | 2016-12-01
2018-05-11 | 2014 | Air Force Active | CZQZ073050 |  | 2017-07-12 | 2017-08-11 | Jack Wayte Construction Co., Inc | W912PP17C0009 | 993496 | 993496 | 2018-05-28 | 2018-03-15
2018-07-11 | 2016 | Air Force Active | CZQZ113000 |  | 2016-11-18 | 2017-02-09 | GranCor Enterprises, Inc. | W912PP14D0022 | 8282561 | 8435763 | 2018-11-12 | 2018-11-12
2018-07-11 | 2017 | Air Force Active | CZQZ160010 |  | 2017-05-25 | 2017-08-22 | Ortega Plumbing & Heating | W912PP17C0012 | 2479860 | 2589163 | 2018-06-14
2018-07-11 | 2016 | Air Force Active | DBEH063000 |  | 2016-02-23 | 2016-07-29 | SAUER | W9127812D0039 | 18658000 | 18760052 | 2018-06-30 | 2018-08-15
2018-07-11 | 2018 | Air Force Active | DBEH133000 |  | 2017-11-02 | 2018-05-01 | CORE ENGINEERING & CONSTRUCTION | W9127818F0289 | 1467602 | 1467602 | 2019-04-30 | 2019-04-30
2018-07-11 | 2011 | Air Force Active | DHAF080145 |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 1073822 | 146939 | 2013-10-03 | 2017-03-14
2018-07-11 | 2011 | Air Force Active | DHAF080145 |  | 2015-01-16 | 2015-02-15 | RED HORSE | RED HORSE | 1376483 | 1376483 | 2017-03-21 | 2017-03-14
2018-07-11 | 2011 | Air Force Active | DHAF105000 |  | 2012-04-06 | 2012-07-31 | C Davis and Associates | W912ER12C0038 | 1003878 | 155733 | 2013-10-03 | 2017-04-09
2018-07-11 | 2011 | Air Force Active | DHAF105000 |  | 2015-02-11 | 2015-03-13 | RED HORSE | RED HORSE | 1532053 | 1532053 | 2017-04-16 | 2017-04-09
2018-07-11 | 2011 | Air Force Active | DHAF110018 |  | 2015-07-31 | 2015-08-30 | RED HORSE | RED HORSE | 581730 | 581730 | 2017-10-03 | 2017-09-26
2018-07-11 | 2011 | Air Force Active | DHAF110018 |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 1006756 | 191812 | 2013-10-03 | 2017-09-26
2018-07-11 | 2011 | Air Force Active | DHAF110019 |  | 2014-10-05 | 2014-11-04 | RED HORSE | RED HORSE | 740000 | 740000 | 2016-12-08 | 2016-12-01
2018-07-11 | 2011 | Air Force Active | DHAF110019 |  | 2012-04-06 | 2012-07-31 | C. Davis and Associates | W912ER12C0038 | 582994 | 128794 | 2013-10-03 | 2016-12-01
2018-07-11 | 2012 | Air Force Active | DHAF120029 |  | 2012-11-01 | 2013-07-08 | RED HORSE and JOC | RED HORSE | 950000 | 950000 | 2015-07-02 | 2015-07-02
2018-04-16 | 2017 | Air Force Active | DXEB053005 |  | 2017-04-26 | 2017-09-22 | Bethel Federal-UNIT JV | W911KB17C0001 | 17858000 | 17858000 | 2019-10-24 | 2019-10-24
2018-07-11 | 2017 | Air Force Active | DXEB053005 |  | 2017-04-26 | 2018-04-30 | Bethel Federal-UNIT JV | W911KB18C0006 | 19278001 | 19278001 | 2020-04-11 | 2020-04-11
2018-07-11 | 2015 | Air Force Active | DXEB133001 |  | 2014-12-09 | 2017-09-29 | Doyon Management Services, LLC | W911KB17C0046 | 16098080 | 16199080 | 2019-11-07 | 2019-11-07
2018-07-11 | 2015 | Air Force Active | EGYN083001 |  | 2017-07-24 | 2017-08-08 | Community Contractors, Inc. | W9128F17C0026 | 2655000 | 2655000 | 2018-08-24 | 2018-08-24
2018-07-11 | 2017 | Air Force Active | EPLK150006 |  | 2017-07-14 | 2017-09-20 | Wolf & Mueller and Erbud JV | W912GB15D0060 | 2533989 | 2533989 | 2020-03-26 | 2020-03-26
2018-07-11 | 2017 | Air Force Active | EPPW170003 |  | 2017-07-14 | 2017-09-21 | Wolff-Mueller & ERBUD JV | W912GB15D0060 | 2463632 | 2463632 | 2020-02-18 | 2020-03-26
2018-07-11 | 2016 | Air Force Active | EXSW123006 |  | 2016-08-19 | 2017-04-25 | Carillion Construction Ltd | DIOCB6/11N | 30041908 | 30041908 | 2019-09-05 | 2019-09-05
2018-07-11 | 2017 | Air Force Active | EYSA150022 |  | 2017-12-15 | 2018-04-13 | Sociedad Espanola De Montajes Industrial | W912GB15D0053 | 2927001 | 2927001 | 2020-04-26 | 2020-04-29
2018-07-11 | 2011 | Air Force Active | FBNV113002 |  | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223000 | 6665967 | 2013-05-02 | 2018-10-15
2018-07-11 | 2016 | Air Force Active | FBNV113005 |  | 2016-06-08 | 2016-09-14 | Creative Times, Inc. | W912PL16C0025 | 9300000 | 10412235 | 2017-12-09 | 2018-08-24
2018-07-11 | 2016 | Air Force Active | FBNV113008 |  | 2016-08-02 | 2017-03-29 | Mills Design Group, LLC | W912PL17C0013 | 1526250 | 1526250 | 2018-05-10 | 2018-05-10
2018-07-11 | 2017 | Air Force Active | FSPM053503C |  | 2017-05-12 | 2018-05-22 | I.E. Pacific, INC | W912PL8C0024 | 22414000 | 22414000 | 2020-06-11 | 2020-06-11
2018-07-11 | 2016 | Air Force Active | FSPM153500 |  | 2016-06-08 | 2017-05-11 | Harper Construction Comp, Inc | W912PL17C0019 | 69067750 | 69067750 | 2019-06-09 | 2019-06-09
2018-07-11 | 2016 | Air Force Active | FTEV123007 |  | 2017-03-09 | 2017-06-21 | Speegle Construction | W9127817C0019 | 11114940 | 11296097 | 2018-11-19 | 2018-12-26
2018-07-11 | 2017 | Air Force Active | FTFA033003 |  | 2017-12-12 | 2018-01-11 | Pac Comm, Inc (Demo) | FA282318F4602 | 300552 | 300552 | 2018-05-26 | 2019-07-29
2018-07-11 | 2017 | Air Force Active | FTFA033003 |  | 2017-08-28 | 2017-09-30 | The Green-Simmons Company, Inc | W9127816D0016 | 12034000 | 12034000 | 2019-07-29 | 2019-07-29
2018-07-11 | 2017 | Air Force Active | FTFA033003 |  | 2017-11-21 | 2017-12-21 | Yerkes South, Inc (Abatement) | FA282318F4654 | 13216 | 13216 | 2018-03-16 | 2019-07-29
2018-07-11 | 2016 | Air Force Active | FTQW163011 |  | 2016-06-22 | 2016-12-08 | Watterson Construction Company | W911KB17C0004 | 19754000 | 20782764 | 2018-09-19 | 2018-09-19
2018-07-11 | 2017 | Air Force Active | FTQW170100 |  | 2017-03-21 | 2017-06-06 | Silver Mountain Construction LLC | W911KB17C0021 | 17956192 | 17975192 | 2019-04-27 | 2019-04-27
2018-07-11 | 2017 | Air Force Active | FTQW170106 |  | 2017-03-17 | 2017-06-06 | Bethel Federal-UNIT JV | W911KB17C0022 | 35928400 | 36471323 | 2019-07-16 | 2019-07-23
2018-07-11 | 2017 | Air Force Active | FTQW170112 |  | 2017-08-24 | 2018-01-25 | Watterson Construction Co. | W911KB18C0006 | 58078800 | 58206300 | 2019-11-02 | 2019-11-02
2018-07-11 | 2017 | Air Force Active | FTQW170113 |  | 2016-12-13 | 2017-04-03 | Callahan/Watterson JV | W911KB17C0011 | 7841500 | 7945367 | 2018-11-20 | 2018-11-20
2018-07-11 | 2017 | Air Force Active | FTQW170114 |  | 2018-01-23 | 2018-02-22 | Bethel Federal-UNIT JV | W911KB18C0009 | 33156000 | 33156000 | 2019-12-09 | 2020-04-02
2018-07-11 | 2017 | Air Force Active | FTQW170114 |  | 2017-03-17 | 2017-06-06 | Bethel Federall-UNIT JV | W911KB17C0022 | 1332000 | 1632000 | 2020-03-26 | 2020-04-02
2018-07-11 | 2018 | Air Force Active | FTQW180102 |  | 2017-09-18 | 2018-02-16 | Eklutna Construction & Maint | W911KB18C0012 | 11824501 | 11824501 | 2019-06-05 | 2019-06-05
2018-07-11 | 2018 | Air Force Active | FTQW180103 |  | 2017-09-12 | 2018-02-20 | Alcan Builders, Inc. | W911KB18C0007 | 20092323 | 20092323 | 2019-08-01 | 2019-08-01
2018-07-11 | 2018 | Air Force Active | FTQW180105 |  | 2017-12-12 | 2018-03-23 | Bristol Design Build Services | W911KB18C0017 | 9898068 | 9898068 | 2020-01-20 | 2020-01-20
2018-07-11 | 2018 | Air Force Active | FTQW180107 |  | 2017-12-28 | 2018-03-23 | Callahan/Watterson Joint Ventu | W911KB18C0018 | 19051000 | 19051000 | 2020-02-14 | 2020-02-14
2018-07-11 | 2018 | Air Force Active | FTQW180111 |  | 2017-10-12 | 2018-02-15 | Haskell Corp/Davis Constructors JV | W911KB18C0014 | 44363105 | 44363105 | 2019-11-28 | 2019-11-28
2018-07-11 | 2017 | Air Force Active | FTQW183001 |  | 2018-01-30 | 2018-06-05 | Watterson Construction Company | W911KB18C0026 | 82125000 | 82125000 | 2020-05-06 | 2020-05-06
2018-07-11 | 2016 | Air Force Active | FXBM063002 |  | 2016-09-08 | 2016-12-19 | Dean Kurtz Construction | W9128F17C0008 | 20456953 | 20575767 | 2019-01-12 | 2019-02-08
2018-07-11 | 2015 | Air Force Active | FXSB041069 |  | 2016-08-15 | 2017-01-04 | Alutiiq Diversified Services, LLC | FA500012D0010 | 1651607 | 1742647 | 2018-01-31 | 2018-01-31
2018-07-11 | 2017 | Air Force Active | GHLN083004 |  | 2017-02-02 | 2017-04-21 | Zieson Construction Co | W9128F16D00550001 | 5129267 | 5129267 | 2018-12-07 | 2018-12-07
2018-07-11 | 2012 | Air Force Active | HACC123204 |  | 2014-12-15 | 2016-06-08 | JV SKE Italy 2012 | N3319115C0802 | 7723700 | 7723700 | 2018-04-07 | 2018-04-07
2018-07-11 | 2015 | Air Force Active | HEKP103001 |  | 2015-04-29 | 2016-04-01 | RANCO Construction Inc | W912DS16C0009 | 5407000 | 5496000 | 2017-11-01 | 2017-11-01
2018-07-11 | 2016 | Air Force Active | HERT137167 |  | 2017-06-25 | 2017-07-25 | Perimeter Security Partners | W912DY14D0006 | 2211009 | 2211009 | 2018-08-19 | 2017-09-06
2018-07-11 | 2016 | Air Force Active | HERT137167 |  | 2016-08-11 | 2017-04-21 | North Wind NEU Security Servic | W912DY14D0005EA01 | 2260696 | 35590 | 2018-11-19 | 2017-09-06
2018-04-16 | 2014 | Air Force Active | KNMD142222 |  | 2015-10-06 | 2015-11-05 | Jacobsen Construction Company, Inc | N6247816C1506 | 2699000 | 3310995 | 2016-10-30
2018-07-11 | 2014 | Air Force Active | KRSM003009 |  | 2014-05-06 | 2015-03-27 | Northern Construction LLC | W9123815C0001 | 12777054 | 14265625 | 2017-04-27 | 2018-04-26
2018-07-11 | 2017 | Air Force Active | KRSM083007 |  | 2017-05-30 | 2018-01-24 | Northern Construction | W9123818C0011 | 10103927 | 10103927 | 2020-02-14 | 2020-02-14
2018-07-11 | 2016 | Air Force Active | KRSM103013 |  | 2016-04-05 | 2016-09-02 | Mountain West Construction Group | W9123816C0023 | 19453853 | 19895124 | 2018-10-07 | 2019-03-23
2018-07-11 | 2016 | Air Force Active | KRSM133002 |  | 2016-02-11 | 2016-08-02 | KW-HHI JV | W9123816C0015 | 8099863 | 8167134 | 2018-09-13 | 2018-09-13
2018-07-11 | 2017 | Air Force Active | KRSM143006 |  | 2015-05-30 | 2018-01-19 | Shofar-CTI JV | W9123818C0006 | 6161226 | 6161226 | 2020-02-12 | 2020-02-12
2018-07-11 | 2017 | Air Force Active | KRSM143007 |  | 2017-04-22 | 2017-09-15 | Mountain West Precast, LLC | W9123817C0026 | 5418830 | 5418830 | 2019-11-06 | 2019-11-06
2018-07-11 | 2016 | Air Force Active | KRSM153001 |  | 2016-03-10 | 2016-08-25 | Provo Wasatch JV, LLC | W9123815D00110001 | 5671521 | 5614012 | 2017-12-17 | 2018-01-16
2018-07-11 | 2017 | Air Force Active | KWRD043006 |  | 2016-12-28 | 2017-05-03 | Mesa Verde Enterprises, Inc. | W912PP17R0005 | 8394468 | 8401117 | 2018-11-03 | 2018-11-03
2018-07-11 | 2017 | Air Force Active | LJYC133003 |  | 2017-11-08 | 2018-05-01 | Aytekin Serol Insaat Taan | W912GB18C0013 | 10199660 | 10199660 | 2020-08-18 | 2020-08-18
2018-07-11 | 2017 | Air Force Active | LRCT150007 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2575083 | 2575083 | 2020-03-12 | 2020-10-13
2018-07-11 | 2017 | Air Force Active | LRCT150008 |  | 2017-07-28 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0021 | 1711902 | 1711902 | 2020-02-01 | 2020-10-13
2018-07-11 | 2017 | Air Force Active | LRCT150009 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2356785 | 2356785 | 2020-03-12 | 2020-10-13
2018-07-11 | 2017 | Air Force Active | LRCT150010 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2021357 | 2021357 | 2020-03-12 | 2020-10-13
2018-07-11 | 2017 | Air Force Active | MHMV103108 |  | 2017-09-01 | 2017-12-19 | KL House Construction Co. | W912PP18C0001 | 6508000 | 6508000 | 2019-06-11 | 2019-06-11
2018-07-11 | 2015 | Air Force Active | MPLS3274JB |  | 2015-02-17 | 2015-06-03 | Solis Constructors, Inc. | W9126G14D00500002 | 6077000 | 6133616 | 2016-08-31 | 2018-06-12
2018-07-11 | 2017 | Air Force Active | MXRD073000 |  | 2017-07-07 | 2017-10-23 | J&J/BBIX Joint Venture | W912WJ18C0001 | 16977000 | 16977000 | 2019-11-22 | 2019-11-22
2018-07-11 | 2015 | Air Force Active | MXRD083002 |  | 2015-06-04 | 2016-08-08 | BBIX, LLC | W912WJ16C0011 | 12595000 | 12658733 | 2018-08-17 | 2018-08-17
2018-07-11 | 2014 | Air Force Active | NKAK963001P |  | 2015-12-08 | 2017-07-05 | ALESSI-KEYES CONSTRUCTION CO. | W9127S17C6002 | 3332825 | 3353401 | 2018-08-19 | 2018-09-06
2018-07-11 | 2016 | Air Force Active | NUEX093009 |  | 2016-10-07 | 2017-04-28 | TALON INDUSTRIES, INC | W912PL17C0004 | 4710360 | 4733541 | 2018-10-06 | 2018-12-10
2018-07-11 | 2016 | Air Force Active | NUEX093016 |  | 2017-10-05 | 2018-02-01 | Okland Construction, Co., Inc. | W912PL18C0013 | 16223496 | 16223496 | 2020-03-25 | 2020-03-25
2018-03-13 | 2016 | Air Force Active | NUEX093016 |  | 2017-10-05 | 2018-02-01 | Okland Construction, Co., Inc. | W912PL8C03 | 16223496 | 16223496 | 2020-03-02 | 2020-03-02
2018-03-13 | 2015 | Air Force Active | NUEX103005 |  | 2014-12-16 | 2015-04-30 | SAI-TALON JV | W912PL15C0005 | 13097800 | 13355276 | 2016-11-22 | 2017-10-12
2018-05-11 | 2016 | Air Force Active | NUEX113001 |  | 2016-09-10 | 2016-12-15 | Marsh Development, Inc. | W912PL16D0009 | 1307252 | 1541120 | 2017-10-14 | 2018-03-15
2018-04-16 | 2015 | Air Force Active | NUEX123001 |  | 2015-02-06 | 2015-08-19 | KORTE Construction Company | W912PL15C0015 | 10318700 | 10336618 | 2017-05-16
2018-07-11 | 2016 | Air Force Active | NUEX123002 |  | 2017-02-08 | 2017-06-02 | AU AUTHUM KI, INC | W912PL17C0020 | 4229464 | 4229464 | 2018-07-11 | 2018-07-11
2018-07-11 | 2016 | Air Force Active | NUEX123004 |  | 2016-01-05 | 2016-08-25 | Okland Construction Company, Inc | W912PL16C0015 | 23915372 | 24138094 | 2018-04-30 | 2018-06-18
2018-07-11 | 2016 | Air Force Active | NUEX123005 |  | 2016-02-15 | 2016-06-30 | OKLAND CONSTRUCTION COMPANY | W912PL16C0013 | 10687842 | 10800712 | 2018-03-27 | 2018-04-19
2018-07-11 | 2017 | Air Force Active | NUEX133000 |  | 2017-06-15 | 2017-09-21 | Okland Construction Co | W912PL17C0029 | 17085351 | 17210741 | 2019-04-05 | 2019-06-04
2018-07-11 | 2017 | Air Force Active | PAF150400 |  | 2017-11-21 | 2018-05-18 | AECOM Construction Inc. | N6274218C1314 | 24132880 | 24132780 | 2019-10-15 | 2019-10-16
2018-07-11 | 2014 | Air Force Active | PAYZ130011 |  | 2015-03-11 | 2015-04-10 | Clark Construction Group, LLC | W912DR15C0008 | 20623200 | 20959570 | 2017-09-09 | 2018-03-20
2018-07-11 | 2014 | Air Force Active | PAYZ130011 |  | 2016-06-28 | 2016-07-28 | Argo Systems, LLC | W912DR16C0021 | 1788000 | 1788000 | 2017-11-05 | 2018-03-20
2018-07-11 | 2014 | Air Force Active | PAYZ130011 |  | 2016-08-07 | 2016-09-06 | MA Mortenson Compamy | W912DR16D00170001 | 823063 | 823063 | 2017-10-16 | 2018-03-20
2018-07-11 | 2014 | Air Force Active | PAYZ130011 |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 245125000 | 263801138 | 2017-04-13 | 2018-03-20
2018-07-11 | 2015 | Air Force Active | PAYZ15001A |  | 2016-10-22 | 2016-11-21 | Bauschmidt OU | W912GB15D00310005 | 2834042 | 2834042 | 2018-06-29 | 2018-07-12
2018-07-11 | 2015 | Air Force Active | PAYZ15001A |  | 2016-06-07 | 2016-11-04 | SKE | W912GB15D00360003 | 5926719 | 5926719 | 2018-07-12 | 2018-07-12
2018-07-11 | 2015 | Air Force Active | PAYZ15001A |  | 2016-10-10 | 2016-11-09 | Astlanda Ehitus OU | W912GB15D00290002 | 3205839 | 3205839 | 2018-06-17 | 2018-07-12
2018-07-11 | 2015 | Air Force Active | PAYZ15001B |  | 2016-10-30 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00500002 | 7097718 | 7097718 | 2018-07-07 | 2018-07-06
2018-07-11 | 2015 | Air Force Active | PAYZ15001B |  | 2016-06-18 | 2016-11-21 | Vilmanto Statybos | W912GB15D00560002 | 1515821 | 1515821 | 2018-06-05 | 2018-07-06
2018-07-11 | 2015 | Air Force Active | PAYZ15001C |  | 2016-08-01 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00410003 | 4479631 | 4479631 | 2018-06-05 | 2018-06-05
2018-07-11 | 2015 | Air Force Active | PAYZ15001C |  | 2016-08-01 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00410002 | 1221288 | 1221288 | 2018-06-05 | 2018-06-05
2018-07-11 | 2015 | Air Force Active | PAYZ15001D |  | 2016-07-15 | 2016-11-05 | Ahntech-Badzak Bulgaria JV | W912GB16D00400003 | 1528908 | 1528908 | 2018-11-12 | 2018-11-12
2018-07-11 | 2015 | Air Force Active | PAYZ15001E |  | 2016-07-15 | 2016-10-20 | SKE SRL | W912GB13D00380006 | 2923496 | 2923496 | 2018-07-20 | 2019-03-09
2018-07-11 | 2015 | Air Force Active | PAYZ15001H |  | 2017-03-08 | 2017-09-22 | Cimolai S.p.A | N6247017C5002 | 27192353 | 27192353 | 2020-07-18 | 2020-07-18
2018-07-11 | 2015 | Air Force Active | PAYZ15002A |  | 2017-04-28 | 2017-09-21 | WARBUD-SKE JV | W912GB17C0014 | 12678470 | 12678470 | 2019-04-14 | 2019-04-14
2018-07-11 | 2017 | Air Force Active | PRQE105144 |  | 2017-01-02 | 2017-06-29 | Walsh Federal, LLC, Chicago IL | W912DQ17C4006 | 10542000 | 10542000 | 2019-01-18 | 2019-01-18
2018-07-11 | 2017 | Air Force Active | PRQE165113 |  | 2016-12-22 | 2017-04-28 | SES Civil Contractors, LLC | W912DQ17C4004 | 2748009 | 2748009 | 2018-06-26
2018-03-13 | 2017 | Air Force Active | PRQE175112 |  | 2016-12-15 | 2017-03-13 | LGC Global, Inc | W912DQ17C4002 | 3698982 | 3698982 | 2018-03-28 | 2018-04-12
2018-01-12 | 2013 | Air Force Active | PTFL126001 |  | 2015-08-04 | 2015-09-03 | Ranco Construction, INC | W912DS15C0009 | 1383300 | 1498375 | 2016-06-29 | 2016-09-23
2018-07-11 | 2016 | Air Force Active | PTFL136001 |  | 2017-12-30 | 2018-06-15 | TDX Quality, LLC | W912DS18C0006 | 2208028 | 2208028 | 2019-07-15 | 2019-07-15
2018-04-16 | 2015 | Air Force Active | PXLY100034 |  | 2016-11-08 | 2017-02-09 | KL House Construction | W912PP17C0044 | 1861000 | 1880008 | 2018-03-09
2018-04-16 | 2015 | Air Force Active | PXLY100035 |  | 2016-11-08 | 2017-02-09 | KL House Construction | W912PP16R0028 | 1710000 | 1732640 | 2018-03-09
2018-03-13 | 2014 | Air Force Active | QJVF092009 |  | 2015-02-11 | 2016-01-28 | Fluor Federal Solutions | W9128F16C0011 | 17648238 | 17828897 | 2017-09-14 | 2018-01-08
2018-02-13 | 2014 | Air Force Active | QJVF092013 |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540270 | 9701991 | 2016-01-06 | 2017-06-14
2018-07-11 | 2015 | Air Force Active | QJVF143101 |  | 2016-06-08 | 2017-03-22 | Rolac Contracting, Inc. | W9128F17C0019 | 2639800 | 2624893 | 2018-06-13 | 2018-06-19
2018-05-11 | 2014 | Air Force Active | QKKA133001P1 |  | 2017-05-24 | 2017-06-23 | Network Corporation | FA520517P0038 | 296096 | 316625 | 2017-10-06 | 2017-09-27
2018-05-11 | 2014 | Air Force Active | QKKA133001P1 |  | 2015-04-10 | 2015-09-29 | Nishimatsu Construction Corp | FA520515C0005 | 21841808 | 21678072 | 2017-09-27 | 2017-09-27
2018-05-11 | 2014 | Air Force Active | QKKA133001P1 |  | 2016-08-29 | 2016-09-28 | Materiel Control | FA520516P0042 | 43773 | 43773 | 2017-09-27 | 2017-09-27
2018-05-11 | 2014 | Air Force Active | QKKA133001P1 |  | 2016-08-23 | 2016-09-22 | Sanwa | F3D3A26215MC01 | 60848 | 60848 | 2017-09-27 | 2017-09-27
2018-07-11 | 2016 | Air Force Active | QKKA153001 |  | 2017-04-28 | 2017-11-27 | Nippo Construction | FA520516D0006 | 1863252 | 1863252 | 2018-12-29 | 2018-12-29
2018-07-11 | 2016 | Air Force Active | QKKA154008 |  | 2017-04-06 | 2017-09-21 | Nippo Corp | FA520517C0005 | 50968708 | 50968708 | 2020-10-19 | 2020-10-19
2018-07-11 | 2015 | Air Force Active | RKMF143001 |  | 2015-03-26 | 2015-09-16 | Harper Construction Co. | W912PL15C0017 | 22397265 | 23240360 | 2017-09-11 | 2018-08-13
2018-07-11 | 2016 | Air Force Active | RKMF143002 |  | 2017-01-31 | 2017-07-13 | Straub Construction Inc. | W912PL17C0025 | 29121000 | 29121000 | 2019-08-04 | 2019-08-04
2018-07-11 | 2016 | Air Force Active | RKMF143003 |  | 2017-03-24 | 2017-09-12 | Okland | W912PL17C0026 | 19055010 | 19055010 | 2019-10-02 | 2019-10-02
2018-07-11 | 2012 | Air Force Active | SGBP100904C |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 524445324 | 571848015 | 2016-09-10 | 2018-04-24
2018-07-11 | 2016 | Air Force Active | SGBP150907 |  | 2016-09-12 | 2017-01-17 | LS Black Constructors, INC | W9128F17C0013 | 18758000 | 18795824 | 2019-01-20 | 2019-01-20
2018-07-11 | 2017 | Air Force Active | SXHT013001 |  | 2017-02-16 | 2017-06-01 | LEEBC O R SER VIC ES, LLC | W9127816D0033 | 12383350 | 12402929 | 2019-03-11 | 2019-03-11
2018-07-11 | 2010 | Air Force Active | TYFR053037 |  | 2017-07-23 | 2017-08-22 | Eckhard GmbH Rodenbach | W912GB09C0022P08 | 12651 | 12651 | 2017-11-05 | 2017-11-01
2018-07-11 | 2010 | Air Force Active | TYFR053037 |  | 2012-05-16 | 2012-06-15 | D & b Bau GmbH, Neustadt | W912GB09C0022 | 10500000 | 10500000 | 2013-07-15 | 2017-11-01
2018-07-11 | 2012 | Air Force Active | TYFR063017 |  | 2012-04-24 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541693 | 29662433 | 2015-03-10 | 2019-08-16
2018-07-11 | 2013 | Air Force Active | TYFR106020U |  | 2015-08-31 | 2016-04-29 | Peter Gross LBB Kaiserslautern | CON0940460000 | 1278751 | 1277558 | 2017-05-24 | 2020-02-18
2018-02-13 | 2011 | Air Force Active | TYFR106261 |  | 2013-09-13 | 2013-11-13 | MICKAN | CON0114014000 | 1697911 | 1993581 | 2014-12-12 | 2015-03-23
2018-07-11 | 2016 | Air Force Active | TYFR136157 |  | 2015-11-21 | 2015-12-21 | MICKAN General-Bau-Gesellschaf | CON1440050000 | 1436235 | 1627804 | 2016-08-30 | 2018-07-16
2018-01-12 | 2011 | Air Force Active | TYFU083507R2 |  | 2014-03-25 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | 17945000 | 18209885 | 2016-05-30 | 2016-06-14
2018-07-11 | 2016 | Air Force Active | UHHZ110323W |  | 2016-04-28 | 2016-12-20 | KOMADA, LLC | W912HN13D0012 | 1673951 | 1673951 | 2017-12-07 | 2017-12-07
2018-01-12 | 2014 | Air Force Active | VYHK143301 |  | 2014-12-15 | 2015-09-03 | UVB, Bitburg | CON1473920000 | 1911000 | 1911000 | 2017-09-14 | 2018-02-11
2018-07-11 | 2016 | Air Force Active | WWCX103027 |  | 2016-03-08 | 2016-06-13 | MT Hojgaard | W912DS16C0010 | 24343934 | 24475738 | 2018-10-24 | 2018-10-24
2018-07-11 | 2014 | Air Force Active | WWCX103028 |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817609 | 39817609 | 2016-12-07 | 2016-12-07
2018-07-11 | 2016 | Air Force Active | WWYK093003 |  | 2016-09-09 | 2017-03-13 | Walsh Federal JV (Chicago/IL) | W912BV17C0005 | 12472000 | 12478599 | 2018-11-08 | 2018-11-08
2018-07-11 | 2014 | Air Force Active | WWYK129000 |  | 2015-10-08 | 2016-02-26 | Fortiss SBJV,LLC | W912BV16C0004 | 10958132 | 10958132 | 2017-09-06 | 2017-09-06
2018-07-11 | 2015 | Air Force Active | WWYK143004 |  | 2015-03-23 | 2016-05-05 | CWG-JV | W912BV16C0029 | 36114652 | 36531480 | 2018-03-17 | 2018-03-17
2018-07-11 | 2015 | Air Force Active | WWYK153005 |  | 2015-03-05 | 2017-03-30 | Walsh Federal Alberici JV | W912BV17C0004 | 97939000 | 98016962 | 2019-04-30 | 2019-04-30
2018-07-11 | 2016 | Air Force Active | WWYK163002 |  | 2016-03-08 | 2016-09-28 | Harper Construction | W912BV16C0045 | 33800153 | 33827077 | 2018-07-08 | 2018-07-08
2018-07-11 | 2017 | Air Force Active | WWYK173003 |  | 2017-02-08 | 2017-06-14 | Southwind Construction Svcs, Edmond, OK | W912BV17C0007 | 12439400 | 12439400 | 2019-01-25 | 2019-01-25
2018-04-16 | 2015 | Air Force Active | XLWU121058 |  | 2016-09-08 | 2017-01-25 | Drace | W9127814D0076 | 1931271 | 1947389 | 2018-01-14
2018-01-12 | 2016 | Air Force Active | XQPZ094013 |  | 2016-07-08 | 2016-11-08 | Federal/Bryan Construction | W9128F17C0004 | 5989953 | 6186157 | 2017-11-03 | 2018-01-06
2018-07-11 | 2016 | Air Force Active | XUMU131054C1 |  | 2018-01-09 | 2018-02-08 | GLR | W192PL18C0016 | 2588000 | 2588000 | 2019-01-03 | 2019-01-03
2018-02-13 | 2016 | Air Force Active | XUMU131054C1 |  | 2017-10-20 | 2017-10-27 | GLR | W912PL18C0001 | 2588000 | 2588000 | 2018-09-22 | 2018-09-22
2018-07-11 | 2014 | Air Force Active | ZHTV053302 |  | 2015-03-11 | 2015-06-23 | Messer Construction | W912QR15C0012 | 24166000 | 24641225 | 2017-06-02 | 2017-09-21
2018-07-11 | 2017 | Air Force Active | ZHTV123205 |  | 2017-05-09 | 2017-07-20 | Messer Construction Co | W912QR17R0024 | 9115000 | 9115000 | 2019-09-22 | 2019-09-22
2018-07-11 | 2016 | Air Force Active | ZHTV146001 |  | 2016-10-03 | 2017-03-03 | Northview Enterprises | W912QR1400220004 | 3286681 | 3349001 | 2018-03-07 | 2018-03-07
2018-07-11 | 2016 | Air Force Active | ZNRE143000 |  | 2016-09-02 | 2017-01-18 | Sangi-Unite Corporation JV | W912HV17C0003 | 6824713 | 6885900 | 2018-02-09 | 2018-04-10
2018-07-11 | 2017 | Air Force Active | ZNRE163000 |  | 2017-05-26 | 2017-09-26 | Obayashi Corporation | FA520915D0007 | 1086140 | 1086140 | 2018-12-14 | 2018-12-14
2018-07-11 | 2016 | Air Force Active | ZNRE164331 |  | 2017-03-28 | 2017-09-25 | Nippo Corporation | W912HV17D0015 | 34552945 | 34589620 | 2020-07-13 | 2020-07-13
2018-07-01 | 2015 | Air Force Reserve | DDPM130008 |  | 2017-06-22 | 2017-08-27 | Belt Built Con-Cor JV, LLC | N6945017F0860 | 3555250 | 3555250 | 2019-01-15 | 2019-01-15
2018-03-01 | 2015 | Air Force Reserve | DDPM130008 |  | 2015-06-22 | 2015-08-27 | K-W Construction | N6945013D17690003 | 2814000 | 2814000 | 2016-07-27 | 2019-01-15
2018-07-01 | 2012 | Air Force Reserve | DKFX079003 |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149000 | 9004770 | 2013-03-01 | 2017-03-31
2018-07-01 | 2014 | Air Force Reserve | PDPG030130P1 |  | 2014-12-02 | 2015-04-24 | Macro-Z Technology | W912QR15C0009 | 17092932 | 17258112 | 2017-03-20 | 2017-09-20
2018-07-01 | 2013 | Air Force Reserve | RVKQ099095 |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242986 | 5242986 | 2016-01-15 | 2017-02-28
2018-07-01 | 2014 | Air Force Reserve | WWYK129000 |  | 2015-10-08 | 2016-02-26 | Fortiss SBJV,LLC | W912BV16C0004 | 10958133 | 11164481 | 2017-09-21 | 2018-05-18
2018-07-02 | 2015 | Air National Guard | BKTZ129083 |  | 2015-07-29 | 2015-09-21 | RL Alvarez Constction, LLC | W912L715C0009 | 2358247 | 2358247 | 2016-10-20 | 2018-03-20
2018-07-02 | 2014 | Air National Guard | BRKR999147 |  | 2014-04-02 | 2014-08-13 | Southeast Cherokee Construction, Inc | W912JA14C0001 | 8201275 | 8201275 | 2016-10-23 | 2019-04-30
2018-07-02 | 2015 | Air National Guard | CEKT129080 |  | 2015-08-19 | 2016-01-15 | NUTMEG COMPANIES, INC. | W91ZRS12D00260006 | 1968645 | 1968645 | 2018-08-18 | 2019-09-27
2018-07-02 | 2015 | Air National Guard | CEKT139004 |  | 2015-02-17 | 2015-06-03 | Cutter Enterprises, LLC | W91ZRS15C0002 | 14859726 | 14859726 | 2019-05-24 | 2019-05-24
2018-07-02 | 2017 | Air National Guard | CEKT139042 |  | 2017-06-12 | 2017-09-29 | Cutter Enterprises LLC | W91ZRS17C0002 | 6097608 | 6097608 | 2023-03-22 | 2020-11-23
2018-07-02 | 2017 | Air National Guard | CURZ159055 |  | 2017-03-07 | 2017-06-23 | Stewart Construction, Inc | W912LN13D0017 | 3996551 | 3996551 | 2018-07-23 | 2018-07-30
2018-06-05 | 2016 | Air National Guard | CVVM099000 |  | 2015-02-10 | 2015-10-01 | S.B. BALLARD | ARMYS.B.BALLARD | 1022000 | 1022000 | 2015-10-31 | 2018-07-31
2018-06-05 | 2017 | Air National Guard | CVVM179001 |  | 2017-07-15 | 2017-09-12 | Harlan Construction Co., Inc. | W912LQ17C3001 | 1172030 | 1172030 | 2018-10-12 | 2018-10-31
2018-07-02 | 2016 | Air National Guard | FFAN139009 |  | 2016-05-26 | 2016-08-16 | Lang Construction Group, Inc | W912LP16C0008 | 6051599 | 6051599 | 2017-09-14 | 2019-03-29
2018-07-02 | 2015 | Air National Guard | FFAN139010 |  | 2015-03-01 | 2015-07-09 | Lang Construction | W912LP15C00010005 | 8154789 | 8154789 | 2016-08-07 | 2019-05-31
2018-06-05 | 2016 | Air National Guard | FJRP089066 |  | 2016-11-18 | 2017-09-01 | Edison Foard Construction Services, Inc. | W9124217R00010007 | 9660706 | 9660706 | 2019-01-13 | 2018-11-25
2018-07-02 | 2016 | Air National Guard | FKNN059220 |  | 2016-06-16 | 2016-09-15 | NICKERSON & O'DAY, INC. | W912JD16B20010004 | 4552775 | 4552775 | 2017-10-15 | 2018-08-28
2018-06-05 | 2015 | Air National Guard | FKNN119013 |  | 2015-03-23 | 2015-06-05 | Nickerson & O'Day | BGS#1806 | 2000000 | 2000000 | 2017-07-05 | 2017-06-30
2018-07-02 | 2017 | Air National Guard | FMKM089018 |  | 2017-03-10 | 2017-08-10 | Max Gray Construction | W912LM17C0002 | 7481566 | 7481566 | 2019-03-03 | 2019-07-31
2018-07-02 | 2014 | Air National Guard | FPBB129050 |  | 2014-07-17 | 2014-09-08 | R.J. Ortlieb | W912PQ12D00100008 | 4895886 | 4895886 | 2015-08-04 | 2016-08-31
2018-07-02 | 2015 | Air National Guard | FTAE129002 |  | 2015-04-24 | 2015-08-07 | Aztec General Contractors, LLC | W912LC15R5002 | 1789838 | 1789838 | 2016-06-22 | 2018-07-26
2018-07-02 | 2014 | Air National Guard | GJKZ129093 |  | 2014-04-22 | 2014-08-12 | Pacific Tech Construction | W912K311D00030005 | 1758438 | 1758438 | 2015-03-17 | 2017-03-14
2018-07-02 | 2016 | Air National Guard | HKRZ129076 |  | 2016-04-12 | 2017-12-22 | Alessi Keyes Construction Co | W912JF18C0001 | 14665029 | 14665029 | 2020-02-01 | 2020-02-01
2018-06-05 | 2017 | Air National Guard | HTUV132007 |  | 2017-08-25 | 2018-02-12 | KPH Construction Corp | W912J217D4005 | 2521404 | 2521404 | 2019-11-28 | 2019-08-11
2018-04-30 | 2014 | Air National Guard | JKSE129321 |  | 2014-07-15 | 2014-10-28 | Guy Tabacco Construction Co.. | W9124V12D00110003 | 1441500 | 1441500 | 2015-09-13 | 2016-02-19
2018-07-02 | 2014 | Air National Guard | JKSE129321 |  | 2017-11-07 | 2017-12-27 | Geranios Enterprises, Inc | W9124V18C5000 | 278657 | 278657 | 2018-03-12 | 2018-07-31
2018-04-30 | 2014 | Air National Guard | JKSE129321 |  | 2014-06-11 | 2014-09-16 | James Talcott Construction Inc | W9124V14C0004 | 20869050 | 20869050 | 2016-10-15 | 2017-08-01
2018-04-30 | 2014 | Air National Guard | JKSE129321 |  | 2014-09-24 | 2014-11-07 | Wadsworth Builders Co., Inc. | W9124V12D00090008 | 1261466 | 1261466 | 2015-10-03 | 2016-08-24
2018-07-02 | 2016 | Air National Guard | KJAQ099058 |  | 2016-12-30 | 2017-04-28 | Anthem Builders | W9133L17C0008 | 8259142 | 8259142 | 2018-05-28 | 2018-12-01
2018-07-02 | 2016 | Air National Guard | KKGA129066 |  | 2016-04-29 | 2016-07-08 | TF Powers | W901UZ16C0002 | 5802211 | 5802211 | 2018-07-18 | 2018-04-30
2018-07-02 | 2014 | Air National Guard | LDXF099060 |  | 2014-07-30 | 2014-09-22 | Patterson-Horth | W912L914D00110002 | 7071641 | 7071641 | 2016-02-28 | 2018-01-31
2018-07-02 | 2014 | Air National Guard | LKLW109037 |  | 2014-08-06 | 2014-09-25 | Lobar Associates | W912KC14C0008 | 7039937 | 7039937 | 2015-10-01 | 2016-05-31
2018-07-02 | 2014 | Air National Guard | LKLW959716 |  | 2015-07-29 | 2015-09-29 | Miller Bros CNS Inc | W912KC15C00270000 | 1904075 | 1904075 | 2016-07-12 | 2017-03-20
2018-07-02 | 2015 | Air National Guard | LUXC139026 |  | 2015-07-11 | 2016-02-22 | Golden Rule Construction Co., Inc. | W912MM12D00050009 | 1567590 | 1567590 | 2016-11-27 | 2016-12-07
2018-07-02 | 2016 | Air National Guard | LYBH049066 |  | 2016-04-20 | 2016-06-22 | Danhill Construction | W912L812D0014 | 2809109 | 2809109 | 2016-07-20 | 2017-06-11
2018-07-02 | 2015 | Air National Guard | MBMV129060 |  | 2015-03-01 | 2015-04-15 | Beckering Construction | W912JB15C2007 | 5952943 | 5952943 | 2016-05-14 | 2017-07-31
2018-07-02 | 2014 | Air National Guard | MMMD129073 |  | 2017-06-01 | 2017-09-06 | RITZ Construction INC | W912K617C5001 | 5881448 | 5881448 | 2018-10-06 | 2018-10-12
2018-07-02 | 2016 | Air National Guard | NKAK139133 |  | 2016-02-22 | 2016-05-17 | HGL | W912JF14D00130002 | 1328194 | 1328194 | 2017-06-12 | 2017-06-12
2018-07-02 | 2014 | Air National Guard | PJMS129058 |  | 2016-03-30 | 2016-09-29 | Kallidus Technologies, Inc. | W912K616C0005 | 12598568 | 12598568 | 2017-10-12 | 2018-10-11
2018-07-02 | 2017 | Air National Guard | PJVY159064 |  | 2017-07-18 | 2017-09-20 | SAF, Inc | W912L812D00060012 | 1498288 | 1498288 | 2018-06-29 | 2018-11-01
2018-06-05 | 2017 | Air National Guard | PSTE009070 |  | 2017-07-28 | 2017-09-27 | VSS Logistics | W912QG17C0009 | 7604644 | 7604644 | 2019-04-28 | 2018-01-31
2018-07-02 | 2014 | Air National Guard | PSTE129092 |  | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W9124209D0003S401 | 1813699 | 1813699 | 2014-12-24 | 2016-01-29
2018-07-02 | 2014 | Air National Guard | PSXE109034 |  | 2014-04-15 | 2014-07-01 | Howard Pence, Inc | W912L714C0004 | 17303286 | 17303286 | 2016-07-21 | 2016-11-29
2018-07-02 | 2015 | Air National Guard | PSXE139000 |  | 2015-03-29 | 2015-07-20 | Eutaw Construction | W912L71322101 | 1349711 | 1349711 | 2016-10-18 | 2017-09-01
2018-07-02 | 2016 | Air National Guard | QMSN099104 |  | 2017-07-31 | 2017-11-09 | Cox Construction | W912LA17C0001 | 8009177 | 8009177 | 2019-03-06 | 2019-03-06
2018-02-02 | 2016 | Air National Guard | RQLH079073 |  | 2016-12-13 | 2017-09-29 | Trimark Constructors, LLC | N6945017C1304 | 9438412 | 9438412 | 2018-10-29 | 2019-08-30
2018-07-02 | 2016 | Air National Guard | RVKQ139005 |  | 2016-05-02 | 2016-09-01 | ODDO Construction Services, LLC | W912PQ16R00050004 | 6550688 | 6550688 | 2018-01-01 | 2018-02-07
2018-07-02 | 2015 | Air National Guard | SZCQ139901 |  | 2015-01-28 | 2015-07-28 | Arch Insurance Company | W912TF15C05000008 | 16528108 | 16528108 | 2016-11-19 | 2019-01-07
2018-01-01 | 2016 | Air National Guard | SZCQ139903 |  | 2017-03-15 | 2017-05-19 | Cornerstone Construction Services | W912TF14D05070505 | 183282 | 183282 | 2017-07-31 | 2018-01-30
2018-07-02 | 2016 | Air National Guard | SZCQ139903 |  | 2015-12-29 | 2016-04-07 | Cutter Enterprises, LLC | W912TF14D05130501 | 2026954 | 2026954 | 2017-01-01 | 2018-08-31
2018-07-02 | 2015 | Air National Guard | SZCQ139904 |  | 2015-01-28 | 2015-07-27 | Arch Insurance Company | W912TF15C0500 | 16353767 | 16353767 | 2016-11-18 | 2019-10-07
2018-07-02 | 2015 | Air National Guard | SZCQ139905 |  | 2017-04-03 | 2017-09-28 | STRUCTURAL ASSOCIATES, INC. | W912TF17C0501 | 7263065 | 7263065 | 2018-10-13 | 2018-12-31
2018-03-12 | 2016 | Air National Guard | TQKD149054 |  | 2016-05-18 | 2016-07-19 | Unknown | DAHA410301D002. | 1351000 | 1351000 | 2017-08-13 | 2018-01-03
2018-07-02 | 2014 | Air National Guard | TWLR129077 |  | 2014-07-25 | 2014-11-14 | MARON CONSTRUCTION CO., INC. | W912LD15C0001 | 6394775 | 6394775 | 2015-12-14 | 2019-01-31
2018-07-02 | 2017 | Air National Guard | TWLR159061 |  | 2017-06-28 | 2017-09-06 | Maron Construction Co. Inc. | 3534532 | 1205000 | 1205000 | 2020-02-28 | 2020-02-28
2018-07-02 | 2014 | Air National Guard | ULYB112022 |  | 2014-07-30 | 2014-09-12 | E.L.Crawford Construction | W912NS14D00160002 | 1954163 | 1954163 | 2015-10-12 | 2017-12-04
2018-07-02 | 2017 | Air National Guard | ULYB132009 |  | 2017-09-04 | 2017-10-17 | Lee Grover Construction | W912NS14D00036001 | 1948312 | 1948312 | 2018-11-16 | 2018-11-15
2018-07-02 | 2017 | Air National Guard | VSSB099014 |  | 2017-05-23 | 2017-08-29 | Opus Design Build, LLC | W912LP17R00020005 | 11401570 | 11401570 | 2018-09-28 | 2018-12-24
2018-07-02 | 2016 | Air National Guard | VUBV109002 |  | 2016-04-04 | 2016-08-10 | SNODGRASS & SON 'S CONSTRUCTION CO., INC | W912JC12D53188016 | 2894050 | 2894050 | 2017-11-03 | 2018-05-30
2018-07-02 | 2014 | Air National Guard | WAAR109002 |  | 2014-07-02 | 2014-08-20 | AWA/Megen Joint Venture LLC | W9136414C0011 | 5944120 | 5944120 | 2015-12-01 | 2017-06-30
2018-07-02 | 2014 | Air National Guard | WEAS129000 |  | 2015-06-07 | 2015-08-20 | Mac Construction & Excavating Inc | W912KZ1222102 | 2630000 | 2630000 | 2015-08-20 | 2016-06-15
2018-07-02 | 2016 | Air National Guard | WKVB139016 |  | 2016-08-11 | 2016-12-01 | S & E Services | W912PQ17C0001 | 2417458 | 2417458 | 2017-12-31 | 2018-05-01
2018-07-02 | 2016 | Air National Guard | WYTD079032 |  | 2016-02-17 | 2016-05-18 | Quality Building Services | W9136416C0001 | 2750180 | 2750180 | 2017-03-18 | 2018-01-26
2018-07-02 | 2017 | Air National Guard | WYTD109008 |  | 2017-11-20 | 2018-04-13 | Shooting Range Industries | W9136418C8001 | 4500000 | 4500000 | 2018-11-09 | 2019-01-31
2018-07-02 | 2016 | Air National Guard | XDQU949500 |  | 2016-04-29 | 2016-09-22 | BSL Galbreath, Inc. | W912JM16C0013 | 8811106 | 8811106 | 2017-11-08 | 2018-06-30
2018-07-02 | 2014 | Air National Guard | XHZG129946 |  | 2014-06-25 | 2014-08-20 | Magnum Construction | W912L611D00010029 | 1979359 | 1979359 | 2015-08-15 | 2017-06-30
2018-06-05 | 2017 | Air National Guard | YKSX159100 |  | 2017-05-26 | 2017-09-29 | Eastern Construction (MATCO) | W912KN13D00190014 | 1102031 | 1102031 | 2018-09-28 | 2018-11-13
2018-07-02 | 2016 | Air National Guard | YZEU139006 |  | 2016-11-03 | 2017-08-15 | C Rallo Contracting Co Inc | W912L616R00070004 | 8102000 | 8102000 | 2018-08-15 | 2018-08-15
2018-07-02 | 2015 | Air National Guard | ZAWA159061 |  | 2015-05-20 | 2015-06-30 | Senate Builders | W912KC10D00170029 | 4185000 | 4185000 | 2016-02-15 | 2016-07-22
2017-04-30 | 2012 | Army Active | 1235 |  | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23139000 | 23189000 | 2014-04-10 | 2016-03-31
2017-05-31 | 2011 | Army Active | 13852 |  | 2011-07-15 | 2015-09-28 | Dawson Technical, LLC | W9128F-15-C-0044 | 1996000 | 2003000 | 2016-07-23 | 2016-09-30
2017-07-31 | 2012 | Army Active | 17220 |  | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12623000 | 12866000 | 2015-11-11 | 2017-01-19
2018-06-30 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2016-06-10 | Zieson Construction Company, LLC | W912DQ-15-D-4001 | 44000 | 65000 | 2016-12-21 | 2018-09-28
2017-07-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2014-07-02 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 727000 | 749000 | 2017-02-08 | 2016-10-12
2016-10-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 23320000 | 23379000 | 2013-09-20 | 2014-11-24
2018-06-30 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2015-01-14 | Doyon Management Services, LLC | W91236-15-C-0017 | 14297000 | 15018000 | 2017-05-03 | 2018-01-08
2016-10-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650000 | 46658000 | 2015-10-15 | 2015-10-16
2018-06-30 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2014-09-03 | VISTA Construction LLC | W91236-14-C-0043 | 4055000 | 4913000 | 2015-09-16 | 2018-03-14
2018-06-30 | 2015 | Army Active | 41449 |  | 2016-05-09 | 2016-09-15 | Purcell Construction Corporation | W91236-16-C-0018 | 58913000 | 58924000 | 2018-10-07 | 2018-12-18
2017-07-31 | 2013 | Army Active | 45116 |  | 2013-02-23 | 2013-07-25 | ANTHONY AND GORDON CONSTRUCTION COMPANY | N69450-13-C-0754 | 0 | 0 | 2016-12-30 | 2016-12-30
2017-07-31 | 2012 | Army Active | 5034 |  | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603000 | 13966000 | 2014-07-18 | 2017-01-31
2017-07-31 | 2013 | Army Active | 51519 |  | 2013-05-16 | 2013-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 0 | 2033000 | 2014-06-04 | 2017-07-07
2017-07-31 | 2013 | Army Active | 51519 |  | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959000 | 7327000 | 2015-02-15 | 2017-02-28
2017-07-31 | 2014 | Army Active | 51868 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 55619000 | 57495000 | 2016-12-26 | 2017-07-21
2018-06-30 | 2015 | Army Active | 51937 |  | 2015-07-28 | 2016-01-28 | ACC Construction Co., Inc | W912HP-16-C-0001 | 45035000 | 60059000 | 2018-03-17 | 2018-11-22
2018-06-30 | 2014 | Army Active | 53584 |  | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036000 | 42059000 | 2017-12-09 | 2018-03-13
2018-06-30 | 2011 | Army Active | 53789 |  | 2012-12-18 | 2013-09-30 | Halbert Construction Company, Inc. | W91238-13-C-0012 | 18519000 | 28864000 | 2015-01-05 | 2018-05-25
2018-06-30 | 2011 | Army Active | 53789 |  | 2012-12-18 | 2015-06-30 | SUNDT CONSTRUCTION INC | W91238-15-C-0007 | 56300000 | 56051000 | 2018-06-15 | 2018-09-24
2018-06-30 | 2013 | Army Active | 55121 |  | 2014-10-21 | 2015-07-31 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 40866000 | 43452000 | 2017-12-30 | 2018-08-13
2018-06-30 | 2016 | Army Active | 55578 |  | 2016-12-15 | 2017-05-11 | Upstate Construction Services, Inc. | W912DS-17-C-0008 | 14784000 | 15168000 | 2019-08-11 | 2018-11-14
2018-06-30 | 2012 | Army Active | 55823 |  | 2012-01-05 | 2012-07-26 | Big-D Construction Corp | W91238-12-C-0024 | 22609000 | 31907000 | 2015-02-15 | 2018-03-19
2017-07-31 | 2012 | Army Active | 55985 |  | 2012-01-10 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15916000 | 18152000 | 2016-03-23 | 2017-01-26
2017-07-31 | 2011 | Army Active | 56024 |  | 2012-06-29 | 2012-09-25 | Nan, Inc. | W9128A-12-C-0019 | 21105000 | 23910000 | 2014-10-14 | 2016-11-17
2018-06-30 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2016-09-27 | AWR ABBRUCH GMBH | W912GB-11-D-0021 | 0 | 0 | 2017-11-05 | 2017-11-05
2017-05-31 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565000 | 29775000 | 2015-10-05 | 2016-03-15
2017-05-31 | 2011 | Army Active | 58675 |  | 2011-02-22 | 2015-09-30 | Semper Tek, Inc. | W912QR-14-D-0023 | 354000 | 387000 | 2016-10-15 | 2016-09-09
2016-10-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2009-01-29 | Hanwha Engr. & Corporation Co., Ltd. | W912UM-09-C-0009 | 17815000 | 18941000 | 2011-01-01 | 2011-05-18
2016-10-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2008-03-31 | Shinsung Engr. & Const. Co., Ltd. | W912UM-08-C-0011 | 15961000 | 559000 | 2010-06-13 | 2008-10-22
2017-12-31 | 2008 | Army Active | 58784 |  | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32469000 | 36328000 | 2012-09-28 | 2017-10-11
2018-06-30 | 2008 | Army Active | 58784 |  | 2012-02-02 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | W912UM-12-C-0057 | 5458000 | 6999000 | 2014-03-16 | 2018-01-18
2018-06-30 | 2013 | Army Active | 58849 |  | 2015-06-02 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 177332000 | 302623000 | 2019-10-10 | 2019-10-10
2018-06-30 | 2017 | Army Active | 58849 | 86285 | 2016-01-24 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 177332000 | 302623000 | 2019-10-10 | 2019-10-10
2018-06-30 | 2018 | Army Active | 58849 | 86286 | 2015-06-02 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 177332000 | 302623000 | 2019-10-10 | 2019-10-10
2017-07-31 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 0 | 0 | 2015-10-05 | 2016-03-15
2018-06-30 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2014-09-05 | DBA ARGE JV PGWM NETCOM | W912GB-14-C-0037 | 29010000 | 33671000 | 2016-07-07 | 2018-08-31
2018-06-30 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2016-09-27 | AWR ABBRUCH GMBH | W912GB-11-D-0021 | 396000 | 420000 | 2017-11-05 | 2017-11-05
2018-06-30 | 2011 | Army Active | 59044 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270000 | 118642000 | 2016-01-29 | 2019-10-31
2018-06-30 | 2014 | Army Active | 59779 |  | 2016-02-24 | 2016-07-28 | San Juan Construction, Inc. | W9128A-16-C-0006 | 54844000 | 54044000 | 2020-06-10 | 2020-08-05
2017-07-31 | 2011 | Army Active | 60555 |  | 2010-12-16 | 2012-05-14 | Landesbetrieb Bau und Immobilien Hessen Zentrale | W912GB-08-C-0005 | 28704000 | 33835000 | 2014-06-01 | 2017-01-31
2017-07-31 | 2012 | Army Active | 61842 |  | 2012-03-13 | 2015-04-20 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0004 | 12172000 | 10478000 | 2016-12-01 | 2017-05-31
2018-06-30 | 2014 | Army Active | 62204 |  | 2015-03-19 | 2016-02-08 | Meltech Corp., Inc. | W912DR-14-D-0021 | 6840000 | 6840000 | 2017-08-16 | 2018-11-30
2017-07-31 | 2012 | Army Active | 62657 |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100113000 | 102060000 | 2015-10-19 | 2016-10-25
2018-06-30 | 2013 | Army Active | 62663 |  | 2016-10-07 | 2017-08-08 | Gilbane Japan GK | W912HV-17-C-0009 | 26908000 | 27010000 | 2019-04-01 | 2019-05-31
2018-06-30 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 84367000 | 85780000 | 2021-06-09 | 2021-12-06
2016-10-31 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV | W91238-11-C-0010 | 34801000 | 3567000 | 2013-06-12 | 2014-06-30
2018-06-30 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W91238-14-C-0040 | 38915000 | 47200000 | 2016-06-30 | 2018-09-18
2018-06-30 | 2010 | Army Active | 63571 |  | 2016-03-31 | 2016-04-12 | Akima Construction Services, LLC | W912DY-14-D-0001 | 16769000 | 17688000 | 2017-08-01 | 2018-07-11
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-06-28 | M.A. Mortenson Company | W9126G-08-D-0045 | 19332000 | 19731000 | 2013-11-17 | 2013-11-14
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-09-21 | 3D Contracting Inc. | W912DW-12-C-0046 | 14649000 | 15311000 | 2014-05-24 | 2014-12-09
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-01-03 | TSS-Garco Joint Venture | W912DW-13-C-0019 | 8912000 | 9318000 | 2014-08-06 | 2015-04-30
2018-06-30 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-09-26 | MEGEN Construction Company, Inc. | W912HN-11-D-0047 | 7295000 | 10168000 | 2015-04-08 | 2018-05-23
2017-07-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-07 | Arch Insurance Company | W912DQ-11-D-4011 | 8541000 | 9243000 | 2014-08-25 | 2017-02-13
2016-10-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-08-23 | KCI Construction Company | W912DQ-12-C-4009 | 30970000 | 32856000 | 2014-03-12 | 2014-10-27
2016-10-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | W912DQ-12-D-4006 | 2493000 | 3965000 | 2014-01-04 | 2015-12-08
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-05-17 | Tunista Construction, LLC | W912DW-13-C-0035 | 9433000 | 11453000 | 2014-12-18 | 2015-12-31
2018-06-30 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2016-09-22 | TSS-Garco Joint Venture | W912DW-16-C-0015 | 42468000 | 43082000 | 2018-07-05 | 2018-12-31
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-06-18 | Megen Construction Company, Inc. | W912HN-11-D-0047 | 14849000 | 16091000 | 2015-01-02 | 2016-08-19
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-09-12 | Environet, Inc. | W912DW-13-C-0042 | 5662000 | 11648000 | 2015-02-12 | 2016-07-28
2017-04-30 | 2012 | Army Active | 64753 |  | 2012-01-09 | 2012-07-13 | Liberty Mutual Insurance Company | W9126G-11-D-0061 | 6095000 | 6160000 | 2014-02-03 | 2016-04-14
2017-07-31 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503000 | 42856000 | 2014-07-28 | 2017-04-01
2016-10-31 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2013-01-07 | Turner Strategic Technologies, LLC | W91236-13-C-0017 | 8195000 | 8575000 | 2014-11-28 | 2015-05-28
2018-06-30 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2016-09-30 | ASJ Construction LLC | W9126G-16-C-0117 | 623000 | 623000 | 2017-07-10 | 2017-11-03
2017-07-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2015-09-30 | Fortis Networks, Inc. | W912DQ-14-D-4011 | 1828000 | 2406000 | 2016-08-06 | 2016-10-13
2016-10-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18727000 | 19913000 | 2015-04-08 | 2015-10-14
2018-06-30 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30762000 | 39332000 | 2015-12-12 | 2017-12-11
2018-06-30 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2016-05-27 | ARGO Systems LLC | W912DR-16-C-0016 | 6900000 | 7506000 | 2018-01-06 | 2018-01-06
2017-07-31 | 2013 | Army Active | 66023 |  | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345000 | 27541000 | 2016-09-09 | 2017-02-17
2016-10-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687000 | 14606000 | 2014-12-23 | 2014-12-31
2017-07-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2015-01-20 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 6228000 | 6529000 | 2016-05-05 | 2017-02-23
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6814000 | 7400000 | 2015-08-21 | 2015-10-09
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Bristol General Contractors, LLC | W912DW-12-D-1018 | 1979000 | 2354000 | 2013-05-30 | 2013-11-22
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-08-29 | Alutiiq Diversified Services, LLC | W912DW-12-C-0040 | 10525000 | 13116000 | 2014-03-11 | 2015-07-28
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Vet Industrial, Inc. | W912DW-10-D-1021 | 4980000 | 5253000 | 2013-11-01 | 2013-11-25
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-08-02 | James Talcott Construction, Inc. | W912DW-10-D-1015 | 5769000 | 6297000 | 2014-11-17 | 2015-02-06
2017-07-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-06-20 | Bristol General Contractors, LLC | W912DW-14-C-0015 | 5288000 | 6122000 | 2015-09-10 | 2017-05-26
2017-07-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2016-09-08 | Centennial Contractors Enterprises Inc. | W912DW-11-D-1002 | 460000 | 539000 | 2017-06-10 | 2017-06-01
2018-06-30 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2016-09-28 | National Native American Construction, Inc. | W912DQ-16-C-4017 | 1325000 | 1383000 | 2017-05-27 | 2017-11-14
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775000 | 14633000 | 2014-08-26 | 2015-03-02
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-12-24 | Burr-MZT Joint Venture | W912DW-14-C-0001 | 919000 | 983000 | 2014-08-04 | 2014-08-01
2018-06-30 | 2016 | Army Active | 66575 |  | 2016-12-02 | 2017-07-13 | Walga Ross Group JV | W912BV17C0008 | 13191000 | 13273000 | 2018-11-29 | 2019-01-20
2017-07-31 | 2011 | Army Active | 66595 |  | 2011-09-08 | 2015-01-19 | LBB Kaiserslautern | W912GB-09-C-0014 | 30046000 | 30636000 | 2017-09-28 | 2017-09-28
2017-07-31 | 2009 | Army Active | 66725 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7202000 | 7957000 | 2014-06-04 | 2017-07-07
2017-07-31 | 2010 | Army Active | 66726 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757000 | 9264000 | 2014-06-04 | 2017-07-07
2017-04-30 | 2011 | Army Active | 66834 |  | 2010-12-01 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 16173000 | 20463000 | 2013-12-18 | 2016-01-15
2018-06-30 | 2017 | Army Active | 67029 |  | 2017-05-16 | 2017-08-17 | Speegle Construction, Inc. | W91278-16-D-0031 | 13280000 | 13280000 | 2019-03-15 | 2019-03-15
2017-05-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-12-31 | ALCAN BUILDERS INC. | W911KB-15-C-0001 | 12375000 | 12770000 | 2016-09-06 | 2016-09-26
2016-10-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0019 | 14180000 | 14599000 | 2016-02-04 | 2016-05-10
2016-10-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-04-14 | Arctic-American JV | W911KB-14-C-0008 | 16180000 | 16156000 | 2015-10-15 | 2015-10-15
2018-06-30 | 2014 | Army Active | 67157 |  | 2015-05-13 | 2015-08-18 | Watts Constructors, LLC | W9128A-15-C-0003 | 63500000 | 64359000 | 2017-12-13 | 2019-01-18
2018-06-30 | 2012 | Army Active | 68050 |  | 2012-10-19 | 2016-01-15 | Whiting-Turner Contracting Company | W912DR-16-C-0002 | 30470000 | 61496000 | 2018-06-13 | 2018-11-30
2016-11-30 | 2011 | Army Active | 68074 |  | 2013-05-30 | 2013-08-12 | Hessisches Baumanagement Wiesbaden | W912GB-09-C-0059 | 6765000 | 7983000 | 2014-12-12 | 2015-01-09
2018-06-30 | 2013 | Army Active | 68530 |  | 2015-05-02 | 2015-09-23 | Solis Constructors, Inc. | W9126G-14-D-0050 | 18828000 | 20186000 | 2017-05-11 | 2019-02-13
2016-11-30 | 2011 | Army Active | 68606 |  | 2011-09-02 | 2012-10-12 | Bauamt Amberg-Sulzbach | W912GB-09-C-0017 | 18121000 | 18366000 | 2014-05-25 | 2014-06-16
2018-06-30 | 2015 | Army Active | 68826 |  | 2016-03-25 | 2017-06-16 | MW BUILDERS, INC. | W9126G-17-C-0042 | 55741000 | 55885000 | 2019-09-30 | 2019-10-25
2018-06-30 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | W912GB-11-D-0036 | 7198000 | 8645000 | 2014-06-25 | 2014-12-04
2018-06-30 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-23 | ECC International LLC | W912GB-13-C-0003 | 87011000 | 91824000 | 2015-09-19 | 2018-11-30
2018-06-30 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2014-06-24 | OBG Engineering GmbH & Co. KG | W912GB-14-D-0019 | 90000 | 90000 | 2014-10-07 | 2014-11-20
2016-10-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | W912BV-12-C-0003 | 9573000 | 9590000 | 2013-12-16 | 2014-06-27
2017-03-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 5118000 | 5118000 | 2013-09-13 | 2016-11-12
2017-03-31 | 2012 | Army Active | 69286 |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008000 | 8868000 | 2013-09-13 | 2016-11-12
2018-06-30 | 2012 | Army Active | 69489 |  | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772000 | 60207000 | 2015-05-27 | 2018-07-25
2018-06-30 | 2015 | Army Active | 69649 |  | 2015-08-13 | 2015-09-28 | Odyssey International, Inc | W912DR-15-C-0038 | 14675000 | 20090000 | 2017-07-24 | 2018-10-06
2018-06-30 | 2015 | Army Active | 70668 |  | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 103644000 | 106594000 | 2021-11-07 | 2021-11-07
2018-06-30 | 2017 | Army Active | 70668 | 76593 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 103644000 | 106594000 | 2021-11-07 | 2021-11-07
2018-04-30 | 2015 | Army Active | 71035 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-11-12 | 2019-11-12
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Eisterhold Associates Inc | W912WJ-16-D-0012 | 1749000 | 1749000 | 2017-09-15 | 2018-07-31
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Design and Production Incorporated | W912WJ-11-D-0008 | 55000 | 55000 | 2017-09-15 | 2018-07-31
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | The McGraw-Hill Companies Inc | W912WJ-08-M-0034 | 9000 | 9000 | 2017-09-15 | 2018-07-31
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Eisterhold Associates Inc | W912WJ-08-D-0006 | 12451000 | 12451000 | 2017-09-15 | 2018-07-31
2018-06-30 | 2012 | Army Active | 71149 |  | 2016-07-22 | 2016-08-04 | Shirley Contracting Company, LLC | W912DR-16-C-0030 | 19249000 | 20716000 | 2018-08-17 | 2018-08-17
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Design and Production Incorporated | W912WJ-16-D-0014 | 2206000 | 2206000 | 2017-09-15 | 2018-07-31
2017-05-31 | 2014 | Army Active | 71221 |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542000 | 14301000 | 2016-02-18 | 2016-09-28
2018-06-30 | 2010 | Army Active | 71421 |  | 2010-08-01 | 2015-01-06 | LBB Niederlassung Idar-Oberstein | W912GB-10-C-0042 | 18945000 | 18259000 | 2018-08-13 | 2018-09-29
2018-06-30 | 2011 | Army Active | 71422 |  | 2011-07-18 | 2011-09-14 | LBB Niederlassung Idar-Oberstein | W912GB-09-C-0007 | 34935000 | 32599000 | 2018-07-27 | 2018-09-29
2016-11-30 | 2011 | Army Active | 71472 |  | 2011-03-04 | 2011-08-15 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 18280000 | 19603000 | 2013-03-07 | 2014-07-23
2017-07-31 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2013-09-27 | Contrack Watts, Inc. | W912ER-13-C-0032 | 49413000 | 60476000 | 2015-03-25 | 2016-10-03
2016-10-31 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2014-04-03 | Contrack Watts, Inc. | W912ER-14-C-0011 | 6749000 | 6749000 | 2015-10-30 | 2015-12-08
2017-07-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-19 | Zieson Construction Co. | W912DQ-14-D-4000 | 4796000 | 5020000 | 2016-01-29 | 2016-11-22
2017-07-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-18 | Zieson Construction Company, LLC | W912DQ-15-C-4004 | 14313000 | 15213000 | 2016-07-22 | 2017-02-28
2017-07-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777000 | 54196000 | 2016-08-04 | 2017-02-23
2017-07-31 | 2013 | Army Active | 71675 |  | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751000 | 50161000 | 2016-01-15 | 2017-08-11
2018-06-30 | 2017 | Army Active | 71777 |  | 2017-06-16 | 2017-09-30 | McGoldrick Construction Services, Corp. | W9126G17C0111 | 8147000 | 8147000 | 2019-05-22 | 2019-05-22
2018-06-30 | 2015 | Army Active | 73272 |  | 2015-07-23 | 2015-09-28 | Joint forces Construction, LLC | W91236-15-C-0054 | 6350000 | 7722000 | 2016-10-20 | 2017-12-17
2017-07-31 | 2014 | Army Active | 73384 |  | 2015-03-10 | 2016-03-31 | Edifice-Schlosser JV, LLC | W912DR-15-C-0025 | 0 | 3077000 | 2017-03-31 | 2017-03-31
2018-01-31 | 2015 | Army Active | 73542 |  | 2015-01-23 | 2015-08-27 | Walsh Federal JV | W912QR-15-C-0024 | 17724000 | 18039000 | 2017-04-26 | 2017-10-13
2018-04-30 | 2013 | Army Active | 73738 |  | 2016-02-26 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2018-11-28 | 2018-11-28
2018-04-30 | 2015 | Army Active | 74001 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-07 | 2019-06-07
2017-07-31 | 2014 | Army Active | 74638 |  | 2013-11-07 | 2015-04-02 | SGS, LLC | W9126G-15-C-0091 | 13978000 | 13894000 | 2017-01-02 | 2017-07-21
2018-04-30 | 2017 | Army Active | 74732 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 9745000 | 9745000 | 2019-06-13 | 2019-06-13
2017-07-31 | 2014 | Army Active | 74861 |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862000 | 27828000 | 2016-08-09 | 2017-08-19
2018-06-30 | 2013 | Army Active | 75165 |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77477000 | 80637000 | 2016-03-02 | 2017-11-30
2018-06-30 | 2015 | Army Active | 75307 |  | 2017-03-15 | 2017-08-22 | Bristol General Contractors, LLC | W9126G-14-D-0061 | 4590000 | 4590000 | 2018-11-04 | 2018-12-03
2018-06-30 | 2015 | Army Active | 75536 |  | 2016-06-15 | 2016-08-18 | Debcon, Inc. | W912QR-16-C-0018 | 22837000 | 24552000 | 2018-03-07 | 2018-08-17
2018-06-30 | 2016 | Army Active | 75538 |  | 2016-08-02 | 2016-09-29 | Atherton Construction, LLC | W912QR-16-C-0026 | 23347000 | 24065000 | 2018-04-10 | 2018-07-14
2018-06-30 | 2017 | Army Active | 75893 |  | 2017-08-28 | 2017-09-29 | Medvolt, LLC | W9128F17C0047 | 5150000 | 5133000 | 2018-11-29 | 2018-11-29
2018-06-30 | 2016 | Army Active | 75966 |  | 2016-04-26 | 2016-07-21 | Weldin Construction, LLC | W911KB-16-C-0017 | 5490000 | 5541000 | 2017-12-10 | 2018-02-28
2017-07-31 | 2014 | Army Active | 76024 |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630000 | 16706000 | 2016-02-24 | 2017-04-20
2018-06-30 | 2014 | Army Active | 76024 |  | 2014-02-28 | 2017-09-26 | Tenoch Construction | W912DQ-17-D-4004 | 250000 | 250000 | 2018-09-24 | 2018-09-24
2016-10-31 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072000 | 3140000 | 2015-11-10 | 2016-06-03
2018-06-30 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2016-09-28 | Herman Construction Group, Inc. | W91238-15-D-0015 | 2623000 | 2871000 | 2018-05-30 | 2018-06-24
2018-06-30 | 2015 | Army Active | 76087 |  | 2015-06-01 | 2015-09-30 | GEMS Environmental Management Services, Inc. | W91238-15-D-0014 | 4860000 | 4886000 | 2017-03-31 | 2018-06-30
2017-07-31 | 2013 | Army Active | 76196 |  | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25853000 | 29398000 | 2015-06-09 | 2017-04-28
2017-07-31 | 2013 | Army Active | 76586 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717000 | 33295000 | 2015-09-01 | 2017-01-13
2017-07-31 | 2013 | Army Active | 76587 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410000 | 42391000 | 2015-09-01 | 2017-01-13
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC | W911KB-14-C-0005 | 9525000 | 10101000 | 2015-10-16 | 2016-08-29
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-08 | C.I. Contractors INC. | W911KB-14-C-0010 | 5007000 | 6855000 | 2015-04-17 | 2016-07-25
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25547000 | 26284000 | 2016-03-21 | 2016-09-29
2016-10-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | W9126G-08-D-0044 | 24162000 | 24502000 | 2013-12-31 | 2014-02-18
2016-10-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6360000 | 7003000 | 2015-08-21 | 2015-10-09
2017-07-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2016-09-09 | Centennial Contractors Enterprises Inc. | W912DW-11-D-1002 | 36000 | 36000 | 2017-01-18 | 2017-01-23
2017-07-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2016-09-13 | Centennial Contractors Enterprises, Inc. | W912DW-11-D-1002 | 146000 | 146000 | 2017-05-06 | 2017-04-28
2017-07-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2014-04-08 | Glen/Mar Construction, Inc. | W912DW-14-C-0009 | 4771000 | 5945000 | 2015-05-21 | 2017-06-22
2016-10-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | W912DW-12-C-0051 | 25901000 | 27950000 | 2014-05-23 | 2014-10-14
2018-06-30 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2016-09-20 | WHH Nisqually-Garco Joint Venture | W912DW-16-C-0020 | 12390000 | 12851000 | 2018-05-11 | 2018-10-31
2018-06-30 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-04-09 | Walsh Group Ventures | W912DW-15-C-0002 | 11319000 | 12511000 | 2017-07-06 | 2018-06-17
2018-06-30 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-07-09 | Vet Industrial, Inc. | W912DW-15-C-0007 | 11893000 | 12792000 | 2016-08-24 | 2016-08-24
2016-10-31 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2014-09-03 | The Renew Group, Inc. | W912DW-14-C-0017 | 1106000 | 1124000 | 2015-04-22 | 2015-09-04
2018-06-30 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2017-09-30 | Amcore-Cherokee Joint Venture, LLC | W912DW-17-C-0026 | 2593000 | 2699000 | 2018-10-26 | 2018-11-05
2018-06-30 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 23706000 | 24753000 | 2017-07-06 | 2018-06-01
2018-06-30 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2014-08-26 | Archer Western Federal JV | W912DW-14-C-0023 | 36998000 | 43757000 | 2016-03-16 | 2018-02-01
2018-06-30 | 2013 | Army Active | 76903 |  | 2012-11-26 | 2014-05-13 | Nan-Samsung | W9128A-14-C-0002 | 69749000 | 70379000 | 2017-01-13 | 2017-12-12
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3750000 | 1013000 | 2014-02-15 | 2013-08-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7473000 | 8035000 | 2013-12-14 | 2016-06-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 | 5379000 | 4709000 | 2013-06-21 | 2014-05-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2013-12-04 | Solis Constructors, Inc | W9126G-14-C-0006 | 0 | 0 | 2015-01-25 | 2016-03-31
2017-07-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2016-04-12 | AMIDON, INC. | W9126G-16-C-0030 | 3163000 | 3096000 | 2016-12-07 | 2017-02-26
2017-07-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165000 | 17853000 | 2016-02-12 | 2017-07-26
2017-07-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-08-28 | Medvolt, LLC | W9128F-14-C-0054 | 13195000 | 13994000 | 2016-03-31 | 2016-06-03
2016-10-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | Hartland/Mass JV LLC | W9128F-13-D-0014 | 3339000 | 3566000 | 2015-10-20 | 2016-01-05
2017-07-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56721000 | 59762000 | 2016-08-22 | 2017-05-31
2017-05-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | John Bowman, Inc. | W9128F-13-D-0013 | 2288000 | 2329000 | 2015-10-07 | 2015-12-17
2017-05-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-07-16 | SEK JV | W9128F-13-D-0015 | 3133000 | 3596000 | 2015-02-14 | 2015-07-07
2017-07-31 | 2015 | Army Active | 77305 |  | 2016-05-23 | 2016-05-28 | Francisco Semsch, Architect, Inc. | W9128F-15-C-0010 | 3848000 | 3848000 | 2016-06-15 | 2016-11-21
2018-06-30 | 2015 | Army Active | 77305 |  | 2016-05-23 | 2017-09-11 | Straub Construction, INC | W9128F-17-C-0032 | 61936000 | 62513000 | 2019-06-02 | 2019-07-03
2017-07-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 891000 | 891000 | 2016-08-22 | 2017-05-31
2017-07-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-07-19 | Blackhorse Worldwide LLC | W9128F-13-D-0016 | 4214000 | 4715000 | 2015-07-22 | 2016-01-14
2016-10-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2015-01-16 | Agile Infrastructure Services, L.L.C. | W9128F-15-C-0002 | 2843000 | 2902000 | 2016-02-11 | 2016-07-14
2018-06-30 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585000 | 53110000 | 2016-05-28 | 2017-11-28
2017-07-31 | 2013 | Army Active | 77419 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 10400000 | 11033000 | 2016-12-26 | 2017-07-21
2017-04-30 | 2014 | Army Active | 77885 |  | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9833000 | 12527000 | 2015-07-01 | 2016-07-29
2017-07-31 | 2013 | Army Active | 78054 |  | 2014-07-08 | 2015-03-17 | Akima Construction Services, LLC | W912DR-15-C-0013 | 3358000 | 11102000 | 2016-09-24 | 2017-02-21
2018-06-30 | 2014 | Army Active | 78196 |  | 2015-08-07 | 2016-09-21 | Veterans Northwest Construction LLC | W912DW-16-C-0016 | 11120000 | 11437000 | 2018-04-05 | 2018-08-10
2018-06-30 | 2014 | Army Active | 78196 |  | 2015-08-07 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 20099000 | 20683000 | 2017-07-06 | 2018-06-01
2018-06-30 | 2016 | Army Active | 78366 |  | 2016-08-24 | 2016-09-27 | Mickan Generalbaugesellschaft Amberg | W912GB-15-D-0072 | 2694000 | 2784000 | 2017-12-09 | 2018-04-20
2017-07-31 | 2012 | Army Active | 78475 |  | 2013-05-22 | 2014-11-18 | Klebl GmbH | W912GB-15-C-0003 | 14632000 | 15338000 | 2016-09-27 | 2017-04-21
2017-05-31 | 2012 | Army Active | 78505 |  | 2012-04-06 | 2013-08-07 | Staatliches Hochbauamt Amberg | W912GB-11-C-0027 | 13548000 | 13863000 | 2015-09-14 | 2016-02-17
2018-06-30 | 2014 | Army Active | 78712 |  | 2016-08-15 | 2017-08-08 | Staatliches Hochbauamt Amberg | W912GB-12-C-0012 | 20384000 | 20405000 | 2019-11-25 | 2020-01-24
2017-07-31 | 2014 | Army Active | 79618 |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440000 | 9567000 | 2016-02-11 | 2017-03-27
2017-07-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-08-30 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129000 | 12355000 | 2014-11-30 | 2017-07-15
2016-10-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2013-03-19 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. | W912GB-12-D-0035 | 199000 | 199000 | 2013-10-16 | 2013-10-17
2016-10-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-07-05 | EMTA CONSTRUCTION CO. INC. | W912GB-10-D-0020 | 320000 | 320000 | 2012-11-22 | 2012-11-22
2017-07-31 | 2013 | Army Active | 79933 |  | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 169650000 | 2016-08-30 | 2017-02-07
2017-07-31 | 2014 | Army Active | 79933 | 81186 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 169650000 | 2016-08-30 | 2017-02-07
2017-07-31 | 2015 | Army Active | 79933 | 81187 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 169650000 | 2016-08-30 | 2017-02-07
2017-07-31 | 2013 | Army Active | 80112 |  | 2014-12-02 | 2015-04-23 | Sauer Inc. | W91278-12-D-0039 | 10965000 | 11567000 | 2016-07-19 | 2016-11-01
2018-06-30 | 2012 | Army Active | 80231 |  | 2013-06-03 | 2014-09-28 | East Coast Utility Contractors | W912DR-14-C-0041 | 1484000 | 2471000 | 2015-11-03 | 2018-02-08
2018-06-30 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | Black Horse Group LLC | W912DS-09-D-0004 | 21578000 | 24664000 | 2015-06-22 | 2017-11-30
2018-06-30 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 39587000 | 42451000 | 2015-06-17 | 2018-02-23
2017-05-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-11-25 | Upstate Construction Services, Inc. | W912DS-09-D-0005 | 17287000 | 17827000 | 2015-12-02 | 2016-05-30
2017-07-31 | 2013 | Army Active | 80317 |  | 2013-08-14 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1791000 | 1771000 | 2014-09-10 | 2016-11-30
2018-04-30 | 2015 | Army Active | 80353 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2017-07-31 | 2014 | Army Active | 80433 |  | 2015-06-11 | 2015-09-22 | K.L. House Construction Co. | W9128F-15-C-0028 | 3423000 | 3435000 | 2016-10-26 | 2017-03-22
2018-06-30 | 2015 | Army Active | 80666 |  | 2016-06-15 | 2016-08-23 | CORE Engineering & Construction, Inc. | W91278-16-D-0014 | 3213000 | 3488000 | 2018-04-19 | 2018-08-07
2017-07-31 | 2014 | Army Active | 80992 |  | 2015-02-06 | 2015-03-24 | Red One Construction, LLC | W9128A-15-C-0002 | 1696000 | 1696000 | 2016-10-20 | 2017-01-25
2018-06-30 | 2014 | Army Active | 81155 |  | 2014-05-02 | 2014-12-05 | SGS, LLC | W9126G-15-C-0005 | 32968000 | 35421000 | 2016-04-11 | 2018-04-20
2018-06-30 | 2015 | Army Active | 81230 |  | 2015-05-08 | 2015-07-27 | Yojin Construction & Engineering Co., Ltd. | W912UM-15-C-0015 | 43753000 | 44815000 | 2018-04-28 | 2018-07-08
2018-06-30 | 2015 | Army Active | 81234 |  | 2017-02-15 | 2017-05-30 | Green Solar Louisiana, LLC | W9126G-17-C-0046 | 2580000 | 2580000 | 2018-07-28 | 2018-07-28
2018-06-30 | 2015 | Army Active | 81242 |  | 2015-08-19 | 2015-09-27 | BIC-SCC JV, LLC | W91278-13-D-0003 | 1740000 | 2208000 | 2016-10-27 | 2018-09-07
2018-06-30 | 2017 | Army Active | 81347 |  | 2016-10-17 | 2017-04-19 | UNIT COMPANY | W911KB-17-C-0010 | 33193000 | 33447000 | 2018-11-15 | 2018-11-15
2018-06-30 | 2015 | Army Active | 81349 |  | 2015-02-20 | 2015-06-04 | Upstate Construction Services, Inc. | W912DS-15-C-0008 | 19408000 | 20284000 | 2016-12-18 | 2017-12-31
2017-07-31 | 2015 | Army Active | 81357 |  | 2014-04-13 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 0 | 804000 | 2015-07-01 | 2016-07-29
2017-07-31 | 2015 | Army Active | 81357 |  | 2015-04-13 | 2015-07-07 | David Boland, Inc. | W9128F-15-C-0017 | 26149000 | 26299000 | 2017-01-18 | 2017-06-16
2018-06-30 | 2015 | Army Active | 81372 |  | 2015-03-31 | 2015-10-29 | Cox Construction Co. | W912PL-16-C-0002 | 26117000 | 31970000 | 2017-11-07 | 2018-03-16
2017-07-31 | 2014 | Army Active | 81424 |  | 2015-07-21 | 2015-09-30 | Southeast Cherokee Construction,Inc. | W91278-10-D-0064 | 3562000 | 3663000 | 2017-02-02 | 2017-03-24
2018-06-30 | 2016 | Army Active | 81427 |  | 2016-07-14 | 2016-09-08 | Daebo Engr. & Const. Co., Ltd | W912UM-16-C-0034 | 44367000 | 44382000 | 2019-02-24 | 2019-03-01
2018-06-30 | 2017 | Army Active | 81428 |  | 2017-06-16 | 2017-08-25 | Hwasan Engineering & construction Co., Ltd. | W912UM17C0043 | 45757000 | 45757000 | 2020-02-25 | 2020-02-25
2017-07-31 | 2013 | Army Active | 81462 |  | 2014-08-21 | 2014-09-30 | Nan, Inc., dba Ocean House Builders | W9128A-12-D-0012 | 1556000 | 1664000 | 2015-10-23 | 2016-12-01
2018-06-30 | 2015 | Army Active | 81658 |  | 2016-09-12 | 2016-12-13 | g2i, LLC | W912PP-17-C-0001 | 2511000 | 2591000 | 2017-10-28 | 2017-11-27
2018-06-30 | 2014 | Army Active | 81987 |  | 2017-06-08 | 2017-09-28 | CONTRACK WATTS-UEJO KOGYO JV | W912HV-17-D-0013 | 41223000 | 46762000 | 2019-11-22 | 2019-11-22
2018-06-30 | 2016 | Army Active | 82094 |  | 2017-03-28 | 2017-09-29 | Call Associates, Inc. | W912DS17C0013 | 1934000 | 1934000 | 2019-04-11 | 2019-04-11
2017-07-31 | 2014 | Army Active | 82394 |  | 2015-03-04 | 2015-12-31 | Red Cedar Enterprises, Inc. | W912BV-13-D-0011 | 2690000 | 2730000 | 2017-02-12 | 2017-07-12
2018-06-30 | 2015 | Army Active | 85185 |  | 2016-08-05 | 2016-09-27 | SEMPER TEK, INC. | W912QR-14-D-0023 | 1790000 | 1865000 | 2018-03-20 | 2018-01-11
2017-01-31 | 2014 | Army Active | 85260 |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1725000 | 1771000 | 2015-11-05 | 2016-01-13
2018-04-30 | 2015 | Army Active | 85683 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2018-06-30 | 2016 | Army Active | 85710 |  | 2016-10-27 | 2017-02-01 | American West Construction, LLC | W9128F-17-C-0015 | 5882000 | 6135000 | 2018-08-22 | 2018-08-29
2018-06-30 | 2015 | Army Active | 85711 |  | 2017-05-09 | 2017-09-28 | BRYAN 77 CONSTRUCTION JV | W912GB17C0019 | 15238000 | 15238000 | 2020-12-09 | 2020-12-09
2018-04-30 | 2016 | Army Active | 85808 |  | 2016-10-18 | 2017-04-25 | Martin Brothers Construction | W912QR-17-C-0014 | 2603000 | 2603000 | 2018-05-08 | 2018-05-08
2018-06-30 | 2016 | Army Active | 85811 |  | 2016-02-12 | 2016-08-29 | B.L. Harbert International, LLC | W912HN-16-C-0014 | 85100000 | 91227000 | 2018-07-23 | 2019-01-11
2018-06-30 | 2014 | Army Active | 85817 |  | 2015-09-22 | 2016-04-07 | LBB Kaiserslautern | W912GB-14-C-0020 | 1685000 | 1924000 | 2016-08-25 | 2016-11-15
2018-06-30 | 2017 | Army Active | 85818 |  | 2016-02-12 | 2017-04-17 | B.L. Harbert International, LLC | W912HN-16-C-0014 | 0 | 74871000 | 2018-10-09 | 2019-01-26
2018-06-30 | 2015 | Army Active | 86404 |  | 2017-05-09 | 2017-09-26 | MICHAEL M. TSONTOS SA | W912GB17D0015 | 6121000 | 6121000 | 2019-12-13 | 2019-12-13
2018-06-30 | 2015 | Army Active | 86405 |  | 2017-05-09 | 2017-09-26 | BRYAN 77 CONSTRUCTION JV | W912GB17C0020 | 13113216 | 13113216 | 2021-05-08 | 2021-05-08
2018-06-30 | 2016 | Army Active | 86408 |  | 2016-08-15 | 2016-09-26 | ZIESON CONSTRUCTION COMPANY , LLC | W912DY-14-D-0007 | 13930000 | 13930000 | 2018-12-07 | 2018-12-07
2018-06-30 | 2015 | Army Active | 86573 |  | 2016-03-29 | 2016-06-30 | Hartland/Mass Joint Venture, LLC | W9128F-15-D-0034 | 2345000 | 2423000 | 2018-01-25 | 2018-03-26
2018-06-30 | 2017 | Army Active | 86689 |  | 2017-06-13 | 2017-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM17C0044 | 121404000 | 121500000 | 2020-11-12 | 2020-11-24
2018-06-30 | 2017 | Army Active | 86745 |  | 2017-07-03 | 2017-09-20 | Mickan Generalbaugesellschaft Amberg | W912GB-17-D-0010 | 139000 | 139000 | 2018-01-11 | 2018-11-07
2018-06-30 | 2015 | Army Active | 86787 |  | 2017-03-29 | 2017-06-02 | Holland and Holland, Inc. | W912HN-17-C-0007 | 2638000 | 2650000 | 2018-07-21 | 2018-08-04
2018-06-30 | 2015 | Army Active | 86859 |  | 2016-07-15 | 2016-09-15 | ETERNA S.A. | W91278-13-D-0020 | 1400000 | 1428000 | 2018-04-26 | 2018-08-22
2018-06-30 | 2016 | Army Active | 86914 |  | 2017-07-03 | 2017-08-30 | Nan, Inc., dba Ocean House Builders | W9128A-12-D-0012 | 2523000 | 2523000 | 2018-12-12 | 2018-12-12
2018-06-30 | 2017 | Army Active | 87309 |  | 2017-08-07 | 2017-09-26 | Empresa de Construccion y Transporte Eterna, S.A. | W91278-16-D-0102 | 2440000 | 2440000 | 2019-08-07 | 2019-08-07
2018-06-30 | 2016 | Army Active | 87419 |  | 2017-08-22 | 2017-12-15 | Innovative Construction & Design, LTD | W912DW18C0001 | 2315000 | 2370000 | 2018-09-27 | 2018-09-27
2018-06-30 | 2016 | Army Active | 87892 |  | 2017-05-23 | 2017-09-29 | Kunj Construction Corp | W912DS17C0012 | 2650000 | 2650000 | 2019-04-26 | 2019-04-29
2018-06-30 | 2016 | Army Active | 88047 |  | 2017-07-17 | 2018-02-27 | Harbor Enterprises, Limited Liability Company | W912HN18C3000 | 2590000 | 2594000 | 2019-03-19 | 2019-03-22
2018-06-30 | 2017 | Army Active | 88369 |  | 2017-08-11 | 2017-09-28 | Mohawk Valley Utility | W912WJ17C0025 | 1796000 | 1796000 | 2018-10-13 | 2018-10-13
2017-09-30 | 2016 | Army Active | 88386 |  | 2017-05-26 | 2017-08-31 | Olgoonik Diversified Services, LLC | W912DQ-17-C-4005 | 2780000 | 2780000 | 2018-09-20 | 2018-09-20
2018-06-30 | 2016 | Army Active | 88386 |  | 2017-05-26 | 2017-08-31 | Olgoonik Diversified Services, LLC | W912DQ17C4005 | 2780000 | 2818000 | 2018-09-20 | 2018-10-18
2018-03-31 | 2017 | Army Active | 88722 |  | 2017-01-12 | 2017-04-14 | OAC Action Contruction, Corp | W912QR-17-C-0012 | 2202000 | 2202000 | 2018-07-13 | 2018-06-13
2017-07-31 | 2016 | Army Active | 89734 |  | 2016-08-15 | 2016-09-29 | TEYA SERVICES LLC | W912HN-16-C-0026 | 1874000 | 1874000 | 2017-05-16 | 2017-05-16
2018-06-30 | 2015 | Army Active | 8984 |  | 2016-03-17 | 2016-09-19 | Orocon - Carothers JV3 | W912QR-16-C-0017 | 13304000 | 13355000 | 2018-04-11 | 2018-07-19
2018-07-13 | 2013 | Army National Guard | 011007 |  | 2013-09-24 | 2013-09-30 | Butler Construction Company, LLC. | AC-13-C-0051-S | 1920000 | 1904000 | 2014-10-01 | 2017-03-01
2018-01-12 | 2014 | Army National Guard | 011014 |  | 2014-08-14 | 2014-08-22 | Carmon Construction, Inc. | AC-14-C-0005-S | 4000000 | 3785000 | 2015-12-10 | 2016-04-01
2018-07-13 | 2016 | Army National Guard | 011317 |  | 2016-08-25 | 2016-09-13 | M W Rogers Construction Company, LLC | AC-16-C-0023-S | 4500000 | 4942000 | 2017-09-15 | 2018-09-02
2018-07-13 | 2015 | Army National Guard | 040730 |  | 2016-07-28 | 2016-09-19 | SJ Anderson Company | M16-0068 | 2000000 | 1988000 | 2017-06-30 | 2017-06-30
2017-01-06 | 2014 | Army National Guard | 050182 |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-C -0003 | 12270000 | 16758000 | 2016-12-01 | 2017-06-30
2018-07-13 | 2014 | Army National Guard | 050182 |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-C-0003 | 12270000 | 16798000 | 2016-12-01 | 2018-07-30
2018-07-13 | 2016 | Army National Guard | 080213 |  | 2018-01-26 | 2018-04-19 | Iron Mike Construction, LLC | W912LC-16-2-2001 | 3000000 | 2944000 | 2018-12-31 | 2018-12-31
2018-07-13 | 2016 | Army National Guard | 090071 |  | 2016-08-09 | 2016-09-16 | Sealaska Constructors | W91ZRS-16-C-0001 | 11000000 | 10404000 | 2018-04-06 | 2018-05-23
2018-05-15 | 2014 | Army National Guard | 090088 |  | 2015-08-27 | 2015-09-19 | K-Con, Inc | BI-Q-670-DB | 1363000 | 1318000 | 2016-09-26 | 2017-10-12
2018-07-13 | 2016 | Army National Guard | 100082 |  | 2016-06-17 | 2016-09-02 | Wohlsen Construction | 07-2014 | 10800000 | 11892000 | 2017-08-25 | 2018-06-29
2018-07-13 | 2013 | Army National Guard | 120102 |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) | W911YN-11-2-2002 | 19950000 | 24275000 | 2015-07-26 | 2018-07-13
2018-07-13 | 2016 | Army National Guard | 120173 |  | 2016-08-04 | 2016-08-17 | West Construction, Inc. | W911YN-06-2-2001 | 18000000 | 17328000 | 2018-07-30 | 2018-09-30
2018-07-13 | 2015 | Army National Guard | 120212 |  | 2016-05-16 | 2016-05-26 | Hendrick Brothers Construction | WI11YN-15-2-2001 | 1911000 | 1933000 | 2017-10-13 | 2018-12-15
2018-07-13 | 2016 | Army National Guard | 130130 |  | 2016-09-16 | 2016-09-22 | Burns & McDonnell Engineering Company, Inc. | W9133L-15-D-0003-C003 | 6800000 | 6615000 | 2017-11-03 | 2017-11-03
2017-08-07 | 2014 | Army National Guard | 140055 |  | 2016-08-02 | 2016-09-30 | APC Construction, LLC/NAVFAC Pacific | N40192-16-D-2701 | 2000000 | 2057000 | 2017-09-29 | 2017-09-29
2018-07-13 | 2013 | Army National Guard | 150023 |  | 2013-10-25 | 2014-09-26 | Watts Constructors, LLC | W912J6-14-C-0003 | 32625000 | 35077000 | 2016-11-01 | 2017-10-09
2018-07-13 | 2017 | Army National Guard | 150035 |  | 2017-02-02 | 2017-09-28 | Alutiiq General Contractors LLC | W912J6-17-C-0001 | 31000000 | 28545000 | 2019-06-30 | 2019-06-30
2018-07-13 | 2014 | Army National Guard | 170033 |  | 2014-06-11 | 2014-06-27 | George Sollitt Construction Co. | W91SMC-14-2-2004-10001 | 17100000 | 16110000 | 2016-10-01 | 2017-10-01
2018-07-13 | 2014 | Army National Guard | 170127 |  | 2014-06-11 | 2014-06-27 | George Sollitt Construction Co. | W91SMC-14-2-2003-10001 | 38000000 | 38064000 | 2016-10-01 | 2017-10-01
2018-07-13 | 2016 | Army National Guard | 171001 |  | 2016-08-08 | 2016-09-30 | Fager-McGee | W91SMC-15-2-2001 | 1900000 | 2343000 | 2017-08-01 | 2017-08-01
2018-07-13 | 2015 | Army National Guard | 180269 |  | 2017-06-27 | 2017-07-28 | Patterson Horth | MDI-SAB-17-C-0051 | 1572000 | 1569000 | 2018-03-04 | 2018-07-20
2018-07-13 | 2017 | Army National Guard | 190025 |  | 2017-07-21 | 2017-09-25 | OPUS Design Build, L.L.C. | W912LP-17-C-0002 | 23000000 | 22006000 | 2019-06-28 | 2019-06-28
2018-01-12 | 2016 | Army National Guard | 190192 |  | 2016-09-23 | 2016-09-29 | Jensen Builders, LTD | W912LP-16-2-2001 | 1900000 | 1737000 | 2017-07-31 | 2017-12-01
2017-09-07 | 2016 | Army National Guard | 200112 |  | 2016-05-06 | 2016-08-26 | Harbin Construction | W912JC-12-D-5308 | 2400000 | 2136000 | 2018-03-09 | 2017-06-24
2017-09-07 | 2016 | Army National Guard | 200113 |  | 2016-05-06 | 2016-09-26 | Harbin Construction | W912JC-12-D-5308 | 4300000 | 3665000 | 2018-03-09 | 2017-06-24
2018-07-13 | 2014 | Army National Guard | 200117 |  | 2016-09-28 | 2017-08-08 | Bruner Contracting Company, LLC | W912JC-12-D-5305 | 2050000 | 1737000 | 2018-09-28 | 2018-11-30
2018-01-12 | 2013 | Army National Guard | 210001 |  | 2013-05-17 | 2013-06-04 | DW Wilburn, Inc. | CT2 1300000269 | 24778000 | 27092000 | 2014-10-01 | 2016-02-03
2018-07-13 | 2012 | Army National Guard | 230046 |  | 2012-04-05 | 2012-09-26 | ITSI Gibane | W912JD-12-C-0003 | 14390000 | 15844000 | 2014-07-11 | 2018-08-30
2018-07-13 | 2015 | Army National Guard | 230113 |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113-D | 30615000 | 31772000 | 2017-08-03 | 2018-12-30
2018-07-13 | 2015 | Army National Guard | 240165 |  | 2015-08-17 | 2015-09-23 | Harkins Builders | 001B6400136 | 16496000 | 12986000 | 2017-10-29 | 2018-04-15
2018-07-13 | 2016 | Army National Guard | 240173 |  | 2016-08-10 | 2016-09-28 | Harkins Builders | 1521010362 | 13800000 | 14543000 | 2018-04-06 | 2019-01-18
2018-07-13 | 2013 | Army National Guard | 250065 |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279000 | 21257000 | 2015-07-30 | 2017-05-17
2018-07-13 | 2014 | Army National Guard | 250095 |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000000 | 20747000 | 2016-11-01 | 2017-01-16
2018-07-13 | 2013 | Army National Guard | 250196 |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District | W912W3-11-D-0069 | 2000000 | 1884000 | 2013-12-01 | 2013-12-01
2018-07-13 | 2014 | Army National Guard | 260051 |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000000 | 17710000 | 2016-10-01 | 2016-10-01
2018-07-13 | 2015 | Army National Guard | 260222 |  | 2018-04-06 | 2018-06-29 | Ripman Construction Co Inc. | Y18228 | 1200000 | 1778000 | 2019-10-04 | 2019-10-04
2018-07-13 | 2014 | Army National Guard | 270014 |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000000 | 18331000 | 2016-04-15 | 2017-12-01
2018-07-13 | 2017 | Army National Guard | 270109 |  | 2017-08-17 | 2017-09-08 | W. Gohman Construction Co. | 130774 - BOQ | 8000000 | 5159000 | 2019-05-31 | 2019-05-31
2018-07-13 | 2017 | Army National Guard | 270240 |  | 2017-08-17 | 2017-09-08 | W. Gohman Construction Co. | 130774 - EB | 17000000 | 11147000 | 2019-05-31 | 2019-05-31
2018-07-13 | 2017 | Army National Guard | 270281 |  | 2017-08-17 | 2017-09-14 | W. Gohman Construction Co. | 130774 - VMS | 1550000 | 956000 | 2019-05-31 | 2019-05-31
2018-07-13 | 2017 | Army National Guard | 270282 |  | 2017-08-17 | 2017-09-14 | W. Gohman Construction Co. | 130774 - BnHQ | 3000000 | 2045000 | 2019-05-31 | 2019-05-31
2018-07-13 | 2016 | Army National Guard | 280327 |  | 2016-09-08 | 2016-09-21 | Orocon Construction LLC | NGB22-16-C-0005-S | 40000000 | 34355000 | 2019-06-28 | 2019-08-25
2018-07-13 | 2014 | Army National Guard | 280423 |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000000 | 3098000 | 2016-11-30 | 2016-11-30
2018-07-13 | 2016 | Army National Guard | 281501 |  | 2016-09-14 | 2016-09-26 | HANCO General Contractors | NGB22-16-C-0008-S | 12800000 | 12015000 | 2018-02-09 | 2018-09-22
2018-01-12 | 2015 | Army National Guard | 300128 |  | 2015-04-14 | 2015-04-20 | Swank Enterprises - Valier | W9124V-08-2-2001 | 38000000 | 28556000 | 2017-05-13 | 2017-11-20
2018-07-13 | 2016 | Army National Guard | 320075 |  | 2016-09-01 | 2016-09-08 | State Public Works Board | W9124X-15-2-2001 | 8000000 | 6711000 | 2017-06-23 | 2017-10-31
2018-07-13 | 2012 | Army National Guard | 320141 |  | 2015-10-01 | 2015-10-19 | Senate Builders & Const Manager | SPWB-09-C-14-109740 | 2000000 | 702000 | 2017-06-23 | 2017-07-15
2018-07-13 | 2017 | Army National Guard | 330019 |  | 2017-01-18 | 2017-02-10 | North Branch Construction Inc. | WI12TF-15-2-2001 | 11000000 | 10892000 | 2018-12-14 | 2018-12-14
2018-07-13 | 2017 | Army National Guard | 330425 |  | 2017-03-01 | 2017-03-13 | Hutter Construction Corp | W912TF-15-2-2002 | 8900000 | 7712000 | 2018-12-14 | 2018-12-14
2018-07-13 | 2013 | Army National Guard | 340110 |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885000 | 34885000 | 2016-02-12 | 2017-09-06
2018-07-13 | 2013 | Army National Guard | 340124 |  | 2016-09-23 | 2016-09-28 | Kallidus | W912KN-13-2-2001 | 3390000 | 2919000 | 2017-09-23 | 2018-05-23
2018-07-13 | 2013 | Army National Guard | 340126 |  | 2016-03-17 | 2016-07-06 | Ranco Construction, Inc. | W912KN-16-C-0002 | 4842000 | 4826000 | 2017-07-06 | 2018-08-13
2018-07-13 | 2013 | Army National Guard | 340127 |  | 2016-09-23 | 2016-09-30 | Kallidus | W912KN-13-2-2004 | 3632000 | 4161000 | 2017-09-23 | 2018-05-23
2018-07-13 | 2013 | Army National Guard | 340128 |  | 2016-03-17 | 2016-07-06 | Ranco Construction, Inc. | W912KN-16-C-0002 | 5036000 | 5011000 | 2017-07-06 | 2018-08-13
2016-10-07 | 2013 | Army National Guard | 340129 |  | 2016-09-23 | 2016-09-29 | USPFO - NJ | W912KN-13-2-2006 | 1937000 | 2028000 | 2017-03-13 | 2017-03-13
2018-07-13 | 2013 | Army National Guard | 340129 |  | 2016-09-23 | 2016-10-11 | Ranco Construction, Inc. | W912KN-13-D-0008 0009 | 1937000 | 2250000 | 2017-03-13 | 2017-03-13
2018-07-13 | 2015 | Army National Guard | 350029 |  | 2016-02-19 | 2016-05-26 | White Sands Construction Inc. | W912J3-13-2-2001 | 5000000 | 6190000 | 2018-01-01 | 2018-07-22
2017-03-03 | 2013 | Army National Guard | 360139 |  | 2015-09-02 | 2015-10-27 | Darland Construction Inc. (GC) Global Electrical Contracting of Westchester, Inc. (EC) S & O Construction Services, Inc (HC) S & L Plumbing & Heating Corp (PC) | 45011 (GC)45011(EC) 45011 (PC) 45011 (HC) | 23213000 | 21704000 | 2017-12-30 | 2017-06-30
2018-07-13 | 2013 | Army National Guard | 360139 |  | 2015-09-02 | 2015-10-27 | Darland Construction Inc. (GC) Global Electrical Contracting of Westchester, Inc. (EC) S & O Construction Services, Inc (HC) S & L Plumbing & Heating Corp (PC) | 45011 (GC) 45011(EC) 45011 (PC) 45011 (HC) | 23213000 | 22458000 | 2017-12-30 | 2018-03-01
2018-07-13 | 2014 | Army National Guard | 360161 |  | 2014-09-17 | 2014-09-30 | Rockmore Contracting Corp (GC) Global Electrical Contracting of Westchester, Inc (EC) AWL Industries, Inc (HC) Eastern Plumbing & Mechanical Contracting, Inc. (PC) | 44573 (GC) 44573 (EC) 44573 (HC) 44573 (PC) | 34814000 | 36741000 | 2016-09-29 | 2018-09-30
2017-09-07 | 2013 | Army National Guard | 361103 |  | 2015-09-03 | 2015-09-15 | Arold Construction Co., Inc (GC) Global Electrical Contracting of Westchester, Inc (EC) S & O Construction Services, Inc. (HC) S & O Construction Services, Inc. (PC) | 44897 (GC) 44897 (EC) 44897 (HC) 44897 (PC) | 6700000 | 6632000 | 2016-11-05 | 2017-07-14
2017-11-13 | 2017 | Army National Guard | 371301 |  | 2017-07-24 | 2017-09-25 | Daniels and Daniels Construction Company INC. | W91242-17-B-0005 | 15000000 | 16233000 | 2019-07-31 | 2019-07-31
2018-07-13 | 2017 | Army National Guard | 371301 |  | 2017-07-24 | 2017-09-25 | Daniels and Daniels Construction Company INC. | W91242-17-C-0005 | 15729000 | 16287000 | 2019-08-17 | 2019-08-17
2018-07-13 | 2015 | Army National Guard | 380073 |  | 2015-03-31 | 2015-06-15 | Strata Corp. | AGND15-18 | 3811000 | 12734000 | 2017-06-30 | 2019-09-15
2018-07-13 | 2015 | Army National Guard | 380073 | 135 | 2015-03-31 | 2015-06-15 | T.F. Powers Construction Co. | AGND15-19 | 6048000 |  | 2017-06-30 | 2017-07-18
2018-07-13 | 2015 | Army National Guard | 380073 | 136 | 2015-03-31 | 2015-06-15 | Manning Mechanical Inc. | AGND15-20 | 1421000 |  | 2017-06-30 | 2017-07-18
2018-07-13 | 2015 | Army National Guard | 380073 | 137 | 2015-03-31 | 2015-06-15 | Scott's Electric Inc. | AGND15-21 | 844000 |  | 2017-06-30 | 2017-07-18
2018-07-13 | 2016 | Army National Guard | 390290 |  | 2016-04-07 | 2016-04-28 | Leidos Engineering, LLC | W90FYQ-09-D-0006 | 3300000 | 3817000 | 2018-05-18 | 2018-08-01
2017-09-07 | 2014 | Army National Guard | 390292 |  | 2014-04-04 | 2014-09-04 | Rock Industries, Inc. | W91364-13-D-0003 | 5200000 | 5127000 | 2016-07-02 | 2016-10-15
2018-07-13 | 2013 | Army National Guard | 400066 |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29197000 | 29376000 | 2014-10-01 | 2017-09-30
2018-07-13 | 2017 | Army National Guard | 400601 |  | 2017-08-23 | 2017-08-30 | CMS Willowbrook | 17007DB | 22000000 | 20469000 | 2019-02-08 | 2019-02-08
2018-07-13 | 2016 | Army National Guard | 410301 |  | 2016-06-14 | 2016-07-13 | Fortis Construction Inc. | 410301D001 | 16500000 | 16500000 | 2018-01-10 | 2018-06-30
2017-04-07 | 2016 | Army National Guard | 410301 |  | 2016-06-14 | 2016-07-13 | Fortis Construction Inc. | 410301D002 | 16500000 | 15769000 | 2018-01-10 | 2018-01-10
2018-07-13 | 2015 | Army National Guard | 411301 |  | 2016-12-20 | 2017-03-02 | S&B James Construction Management | 140033D002 | 2850000 | 2724000 | 2017-12-29 | 2018-12-29
2018-07-13 | 2014 | Army National Guard | 420051 |  | 2014-07-09 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 33932000 | 35906000 | 2016-04-22 | 2017-09-15
2018-07-13 | 2017 | Army National Guard | 420354 |  | 2017-07-13 | 2017-08-17 | ECI Construction LLC | DGS-C-0961-0012 | 9300000 | 7040000 | 2019-01-03 | 2019-01-03
2018-07-13 | 2017 | Army National Guard | 420502 |  | 2017-08-07 | 2017-09-22 | USPFO - PA | W912DR-17-D-0015 | 20000000 | 7450000 | 2018-10-26 | 2018-10-26
2018-07-13 | 2016 | Army National Guard | 420522 |  | 2017-03-22 | 2017-04-20 | Miller Bros. Construction, Inc. | W912KC-16-R-0002 | 16000000 | 12170000 | 2018-08-24 | 2019-05-28
2017-11-13 | 2013 | Army National Guard | 420533 |  | 2015-07-17 | 2015-09-17 | ImbuTec | W912KC-11-D-0004 | 2400000 | 2895000 | 2016-06-17 | 2017-08-31
2018-07-13 | 2015 | Army National Guard | 420586 |  | 2017-02-01 | 2017-02-28 | Miller Bros. Construction, Inc. | W912KC-15-D-0007 | 1999000 | 1552000 | 2018-02-28 | 2018-08-15
2017-08-07 | 2013 | Army National Guard | 430803 |  | 2015-08-06 | 2015-09-15 | OSSAM Construction, Inc. | NGB70-15-C-0021 | 14218000 | 12866000 | 2017-03-25 | 2018-04-08
2018-01-12 | 2011 | Army National Guard | 440009 |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 19316000 | 21433000 | 2014-04-17 | 2015-03-31
2018-01-12 | 2013 | Army National Guard | 440053 |  | 2014-08-15 | 2015-01-06 | J J Cardosi, Inc | W912LD-11-D-0016 | 1032000 | 1203000 | 2015-11-01 | 2016-10-31
2018-07-13 | 2017 | Army National Guard | 440064 |  | 2017-09-06 | 2017-09-13 | Marion Construction Co Inc | W912LD-15-2-2001 | 20000000 | 19844000 | 2020-02-28 | 2020-02-28
2016-09-07 | 2014 | Army National Guard | 450131 |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | State Contract # 46000406465 | 13000000 | 12632000 | 2017-04-06 | 2017-07-06
2018-05-15 | 2014 | Army National Guard | 450131 |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | State Contract # 4600406465 | 13000000 | 12997769 | 2017-04-06 | 2018-02-14
2018-05-15 | 2014 | Army National Guard | 450283 |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | State Contract # 4600406370 | 13000000 | 12990000 | 2017-04-06 | 2018-01-31
2016-09-07 | 2014 | Army National Guard | 450283 |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | State Contract # 46000406370 | 13000000 | 12552000 | 2017-04-06 | 2017-05-06
2018-07-13 | 2014 | Army National Guard | 480243 |  | 2014-02-25 | 2015-09-28 | Burns & McDonnell | W912L1-15-0023 | 14270000 | 14984000 | 2017-06-09 | 2018-08-03
2018-07-13 | 2017 | Army National Guard | 490601 |  | 2017-09-21 | 2017-09-26 | Jacobsen Construction Company | 1875077 | 37000000 | 35965000 | 2019-04-03 | 2019-04-12
2018-05-15 | 2016 | Army National Guard | 500079 |  | 2016-02-22 | 2016-03-22 | Spates Construction, Inc. | State Contract # 30971 | 8030000 | 8404000 | 2017-03-31 | 2017-03-31
2016-09-07 | 2016 | Army National Guard | 500079 |  | 2016-02-22 | 2016-03-22 | Spates Construction, Inc. | 00000 | 7900000 | 8353000 | 2017-03-31 | 2017-03-31
2018-07-13 | 2016 | Army National Guard | 510065 |  | 2016-06-01 | 2016-06-24 | S. B. Ballard Construction Company | PC#123-18108-000 | 29000000 | 28200000 | 2018-03-18 | 2018-07-15
2018-05-15 | 2013 | Army National Guard | 530015 |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | W912DW-13-C-0044 | 31670000 | 31449000 | 2015-08-20 | 2016-03-10
2017-11-13 | 2013 | Army National Guard | 530035 |  | 2014-08-15 | 2014-08-20 | Absher Construction | 2013-295 G(2-1) | 26000000 | 23942000 | 2016-06-30 | 2017-05-30
2018-07-13 | 2016 | Army National Guard | 530041 |  | 2018-01-19 | 2018-06-28 | TDX Quality, LLC | W912DW-18-C-0015 | 19000000 | 20619000 | 2020-04-17 | 2020-04-17
2018-03-15 | 2013 | Army National Guard | 550142 |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673000 | 9627000 | 2014-10-01 | 2015-06-15
2018-07-13 | 2017 | Army National Guard | 560060 |  | 2016-09-14 | 2017-05-17 | The Haskell Company | 17011310701 | 31000000 | 30108000 | 2019-09-30 | 2019-04-02
2018-07-13 | 2017 | Army National Guard | 560084 |  | 2016-10-31 | 2017-02-03 | Layton Construction Company, Inc. | 17042027901 | 21000000 | 20634000 | 2018-04-30 | 2019-01-31
2018-06-30 | 2016 | Army Reserve | 58405 |  | 2016-12-29 | 2017-05-08 | Eastern Construction & Electric, Inc. | W912QR-17-C-0015 | 9133000 | 9192000 | 2019-05-04 | 2019-07-21
2017-07-31 | 2014 | Army Reserve | 65277 |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 11895000 | 13520000 | 2015-09-30 | 2017-03-21
2017-07-31 | 2012 | Army Reserve | 67466 |  | 2012-05-16 | 2012-09-18 | Continental Casualty Company | W912QR-12-C-0055 | 16212000 | 16472000 | 2014-03-19 | 2017-03-22
2018-06-30 | 2015 | Army Reserve | 67567 |  | 2017-02-01 | 2017-05-11 | Catamount Constructors, Inc. | W912QR-17-C-0018 | 9917000 | 9981000 | 2018-11-24 | 2018-11-24
2017-07-31 | 2013 | Army Reserve | 67652 |  | 2014-05-06 | 2015-03-31 | Cox Construction Co. | W912QR-15-C-0007 | 24044000 | 24621000 | 2017-02-12 | 2017-05-30
2017-07-31 | 2013 | Army Reserve | 67659 |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21779000 | 24488000 | 2015-11-04 | 2016-11-28
2018-06-30 | 2015 | Army Reserve | 67661 |  | 2015-12-01 | 2016-03-01 | Structural Associates, Inc. | W912QR-16-C-0009 | 20118000 | 20520000 | 2018-03-08 | 2018-06-29
2018-06-30 | 2014 | Army Reserve | 67663 |  | 2014-08-01 | 2015-08-28 | Sheffield Korte Joint Venture | W912QR-15-C-0027 | 21428000 | 22494000 | 2017-09-06 | 2018-10-12
2018-06-30 | 2012 | Army Reserve | 67681 |  | 2016-04-14 | 2016-08-25 | S&S - EXCEL CONSTRUCTORS JV | W912QR-16-C-0019 | 12078000 | 12306000 | 2018-01-05 | 2018-04-11
2018-06-30 | 2014 | Army Reserve | 67690 |  | 2017-03-24 | 2017-06-20 | Benaka, Inc | W912QR-17-C-0020 | 14397000 | 14462000 | 2019-06-19 | 2020-01-14
2018-06-30 | 2013 | Army Reserve | 67705 |  | 2015-02-13 | 2015-09-24 | Korte Construction Company | W912QR-15-C-0035 | 18104000 | 23080000 | 2017-09-07 | 2018-10-11
2018-06-30 | 2012 | Army Reserve | 67709 |  | 2016-04-11 | 2016-08-04 | J&J Contractors, Inc. | W912QR-16-C-0015 | 18542000 | 19362000 | 2018-03-23 | 2018-04-30
2017-07-31 | 2013 | Army Reserve | 67715 |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31523000 | 32775000 | 2016-01-15 | 2017-05-31
2018-06-30 | 2013 | Army Reserve | 68077 |  | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890000 | 8379000 | 2016-05-30 | 2018-03-19
2017-07-31 | 2011 | Army Reserve | 69421 |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4504000 | 4564000 | 2014-03-21 | 2017-08-30
2018-06-30 | 2011 | Army Reserve | 69562 |  | 2014-12-17 | 2015-09-10 | Blueridge General Inc | W912QR-15-C-0030 | 12568000 | 13621000 | 2017-05-10 | 2018-08-19
2017-07-31 | 2011 | Army Reserve | 69562 |  | 2014-11-14 | 2014-12-17 | Crossroads-Sergent Construction JV | W912QR-13-D-0026 | 1720000 | 1976000 | 2015-10-20 | 2017-06-19
2018-06-30 | 2010 | Army Reserve | 69652 |  | 2011-06-23 | 2011-09-23 | Charpie Korte Enterprise LLC | W912QR-11-C-0047 | 11535000 | 12852000 | 2014-02-12 | 2017-10-27
2018-06-30 | 2015 | Army Reserve | 71035 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-11-12 | 2019-11-12
2018-06-30 | 2017 | Army Reserve | 71036 |  | 2017-06-15 | 2018-03-02 | Heffler Contracting Group | W912QR18C0011 | 22590000 | 22590000 | 2019-09-18 | 2019-09-18
2017-07-31 | 2013 | Army Reserve | 71482 |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56039000 | 61973000 | 2016-05-17 | 2017-03-17
2017-07-31 | 2014 | Army Reserve | 71768 |  | 2015-08-20 | 2015-11-04 | Eastern Construction & Electric, Inc. | W912QR-16-C-0003 | 6433000 | 6818000 | 2017-05-12 | 2017-05-15
2017-07-31 | 2014 | Army Reserve | 71769 |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653000 | 4682000 | 2016-04-09 | 2016-10-18
2017-07-31 | 2014 | Army Reserve | 71900 |  | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129000 | 23020000 | 2016-11-01 | 2017-03-15
2018-06-30 | 2015 | Army Reserve | 71901 |  | 2015-05-26 | 2016-01-21 | Hal Hays Construction, Inc. | W912QR-16-C-0006 | 18508000 | 26271000 | 2018-02-20 | 2018-10-09
2018-06-30 | 2014 | Army Reserve | 71903 |  | 2014-07-28 | 2016-07-06 | David Boland, Inc. | W912QR-16-C-0013 | 17277000 | 17472000 | 2018-07-01 | 2018-10-01
2017-07-31 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2016-06-30 | AAECON General Contracting LLC | W912QR-14-D-0025 | 2520000 | 2682000 | 2016-12-12 | 2017-07-21
2016-10-31 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19101000 | 19893000 | 2015-06-08 | 2016-03-02
2018-06-30 | 2014 | Army Reserve | 72284 |  | 2014-08-13 | 2014-09-30 | North American Specialty Insurance Company | W912QR-14-C-0053 | 16187000 | 16485000 | 2016-05-22 | 2019-04-13
2017-07-31 | 2015 | Army Reserve | 72291 |  | 2015-05-01 | 2015-09-30 | Korte Construction Company | W912QR-15-C-0042 | 13283000 | 13805000 | 2017-08-28 | 2017-09-16
2018-06-30 | 2013 | Army Reserve | 73738 |  | 2016-02-26 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2018-11-28 | 2018-11-28
2018-06-30 | 2015 | Army Reserve | 74001 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-07 | 2019-06-07
2018-06-30 | 2017 | Army Reserve | 74732 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 9745000 | 9745000 | 2019-06-13 | 2019-06-13
2018-06-30 | 2017 | Army Reserve | 77134 |  | 2018-01-05 | 2018-04-26 | L.S. Black Constructors/Loeffel Construction JV | W912QR18C0015 | 23840000 | 23840000 | 2020-05-14 | 2020-05-14
2018-06-30 | 2015 | Army Reserve | 77151 |  | 2016-04-05 | 2016-09-29 | Boro Developers, Inc. d.b.a Boro Construction | W912QR-16-C-0024 | 19988000 | 20890000 | 2018-09-13 | 2019-02-22
2018-06-30 | 2016 | Army Reserve | 77186 |  | 2017-04-03 | 2017-07-13 | ACC Construction Co, Inc. | W912QR17C0021 | 19332000 | 19332000 | 2019-08-31 | 2019-08-31
2018-03-31 | 2015 | Army Reserve | 77228 |  | 2015-08-11 | 2016-05-02 | Blinderman Construction | W912QR-16-C-0007 | 42622000 | 0 | 2018-05-22 | 2018-05-22
2018-06-30 | 2015 | Army Reserve | 77228 |  | 2015-08-11 | 2017-05-12 | Blinderman Construction Co, Inc. | W912QR-17-C-0017 | 21411000 | 22128000 | 2019-04-25 | 2019-06-05
2018-06-30 | 2018 | Army Reserve | 79003 |  | 2018-01-24 | 2018-05-24 | L.S. Black Constructors, Inc. | W912QR18C0019 | 12044000 | 12044000 | 2020-01-21 | 2020-01-21
2018-06-30 | 2015 | Army Reserve | 80353 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2018-06-30 | 2017 | Army Reserve | 80684 |  | 2017-01-25 | 2017-10-19 | L.S.Black Constructors, Inc. | W912QR18C0002 | 13454000 | 13467000 | 2019-10-17 | 2019-10-17
2017-07-31 | 2015 | Army Reserve | 81959 |  | 2015-03-06 | 2015-07-17 | ETD-TCG, LLC with RSP Architects | W912QR-15-C-0018 | 5215000 | 5332000 | 2016-12-09 | 2017-05-23
2018-06-30 | 2015 | Army Reserve | 85683 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2018-06-30 | 2016 | Army Reserve | 85808 |  | 2016-10-18 | 2017-04-25 | Martin Brothers Construction | W912QR-17-C-0014 | 2603000 | 2603000 | 2018-05-08 | 2018-05-08
2018-06-30 | 2015 | Army Reserve | 85812 |  | 2015-08-11 | 2015-09-30 | Cox Construction Co. | W912QR-15-C-0044 | 21672000 | 22463000 | 2017-10-02 | 2018-05-22
2018-06-30 | 2016 | Army Reserve | 85813 |  | 2017-06-28 | 2017-09-28 | Hensel Phelps Construction Co. | W912QR-17-C-0043 | 49643000 | 49631000 | 2019-10-04 | 2019-10-04
2018-06-30 | 2017 | Army Reserve | 86521 |  | 2017-06-30 | 2017-09-19 | Cox Construction Co. | W912QR17C0035 | 17795000 | 17799000 | 2019-05-01 | 2019-05-01
2018-06-30 | 2016 | Army Reserve | 86814 |  | 2017-05-01 | 2017-09-29 | Nadiad, Inc | W912QR17C0044 | 4682000 | 4682000 | 2018-10-18 | 2019-02-18
2018-06-30 | 2016 | Army Reserve | 86882 |  | 2017-06-27 | 2017-11-09 | Cox Construction Co. | W912QR18C0003 | 21180000 | 21298000 | 2019-12-18 | 2019-12-18
2018-06-30 | 2017 | Army Reserve | 88722 |  | 2017-01-12 | 2017-04-14 | OAC Action Contruction, Corp | W912QR-17-C-0012 | 2202000 | 2202000 | 2018-07-13 | 2018-06-13
2018-06-30 | 2017 | Army Reserve | 88733 |  | 2017-03-16 | 2017-06-16 | Butt Construction Company | W912QR-15-D-0002 | 5986000 | 6321000 | 2018-12-06 | 2019-02-24
2017-11-30 | 2017 | Army Reserve | 88733 |  | 2017-03-16 | 2017-06-29 | Butt Construction Company | W912QR-17-F-0063 | 0 | 0 | 2019-01-05 | 2019-01-05
2017-08-14 | 2016 | DLA Defense Automation and Production Service | DSFF1501 |  | 2016-08-01 | 2016-09-30 | PER IMETER SECURITY PARTNERS LLC | W912DY-14-D-0006 | 4249000 | 4384000 | 2017-10-28 | 2018-02-14
2017-08-14 | 2016 | DLA Defense Automation and Production Service | DESC1607 |  | 2016-06-24 | 2016-09-16 | W.F. Magann Corporation | W91236-16-R-0008-0005 | 20646000 | 21088000 | 2019-10-12 | 2019-12-12
2018-07-31 | 2016 | DLA Defense Automation and Production Service | DSFF1501 |  | 2016-08-11 | 2016-09-30 | PER IMETER SECURITY PARTNERS LLC | W912DY-14-D-0006 | 4249000 | 4595000 | 2017-10-28 | 2018-09-30
2018-07-01 | 2012 | DLA Defense Distribution Center | DDCX1203 |  | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 15198000 | 17131997 | 2015-05-05
2018-07-01 | 2013 | DLA Defense Distribution Center | DDCX1301 |  | 2014-05-15 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 12049430 | 12586000 | 2016-04-28 | 2016-12-05
2018-07-01 | 2013 | DLA Defense Distribution Center | DDCX1303 |  | 2013-06-13 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9658000 | 10716 | 2016-01-02 | 2016-10-27
2017-08-14 | 2014 | DLA Defense Distribution Center | DDCX1309 |  | 2016-06-30 | 2016-09-27 | Belt Built CFM Construction Services JV, LLC | W912DR-16-C-0049 / 35958356 | 2597000 | 2597000 | 2016-11-18 | 2018-02-20
2018-07-31 | 2014 | DLA Defense Distribution Center | DDCX1309 A |  | 2016-06-30 | 2016-09-27 | Belt Built CFM Construction Services JV, LLC | W912DR-16-C-0049 / 35958356 | 2597449 | 2768000 | 2017-11-18 | 2019-02-06
2018-07-01 | 2014 | DLA Defense Distribution Center | DDCX1309 B |  | 2018-01-08 | 2018-06-25 | Belt Built CFM Construction Services JV, LLC | W912DR-18-C-0015 | 2468353 | 2468353 | 2019-08-23 | 2019-11-23
2018-07-01 | 2014 | DLA Defense Distribution Center | DDCX1404 |  | 2014-02-11 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 32930000 | 33682000 | 2016-02-28 | 2018-07-20
2018-07-31 | 2017 | DLA Defense Distribution Center | DDCX1701A |  | 2017-12-08 | 2018-04-12 | Carouthers Construction | W9126G-18-C-0018 | 36159560 | 36510784 | 2020-06-25 | 2021-05-24
2018-07-01 | 2017 | DLA Defense Distribution Center | DDCX1701B |  | 2018-04-03 | 2018-08-30 | Bristol Construction Services | W9126G-18-C-0066 | 3881804 | 3881804 | 2020-09-30 | 2020-09-30
2018-07-01 | 2015 | DLA Defense Distribution Center | DESC15S2 |  | 2015-08-25 | 2016-07-28 | Reliable Contracting Group | N62742-16-C-1318 | 3160763 | 3250652 | 2017-12-10 | 2017-12-10
2018-07-01 | 2015 | DLA Defense Distribution Center | DESC1606 |  | 2015-09-01 | 2015-11-16 | MEB General Contractors Inc | N69450-16-C-1604 | 36565000 | 56917697 | 2017-11-05 | 2019-12-22
2017-12-11 | 2015 | DLA Defense Distribution Center | DESC1606 |  | 2015-09-01 | 2015-11-16 | MEB General Contractors Inc | 1234 | 36443425 | 39151158 | 2018-07-01 | 2018-08-20
2018-07-01 | 2014 | DLA Defense Distribution Center | DSFH1401 | DSFH14U2 | 2015-01-28 | 2015-06-02 | Hako Plumbing, Inc. | N62742-15-C-1310B | 5663700 | 5691826 | 2016-10-14 | 2017-07-13
2018-07-31 | 2013 | DLA Defense Energy Support Center | DCX1305 |  | 2016-12-21 | 2017-06-01 | Lobar Inc | W912DR-17-C-0022 | 4831000 | 4865000 | 2019-06-26 | 2020-03-02
2017-08-15 | 2013 | DLA Defense Energy Support Center | DCX1305 |  | 2016-12-21 | 2017-06-01 | Lobar Inc | W912DR17R00100005 | 4831000 | 4831000 | 2019-06-24 | 2019-06-24
2017-12-11 | 2013 | DLA Defense Energy Support Center | DESC 1306 |  | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378000 | 68446006 | 2017-10-14 | 2018-01-31
2017-08-14 | 2015 | DLA Defense Energy Support Center | DESC 1463 |  | 2015-07-15 | 2015-09-30 | Structural Asspcoates Omc. | W9128F-15-C-0032 | 8518820 | 8267000 | 2017-02-17 | 2017-06-15
2017-08-14 | 2014 | DLA Defense Energy Support Center | DESC 1509 |  | 2015-07-27 | 2015-09-23 | CB&I Federal Contractors | N39430-15-D-1632 | 4783347 | 4860687 | 2016-12-30 | 2017-06-27
2018-07-01 | 2013 | DLA Defense Energy Support Center | DESC1203 |  | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 31181234 | 32476017 | 2015-09-28 | 2018-03-15
2018-07-31 | 2013 | DLA Defense Energy Support Center | DESC1301 |  | 2014-11-13 | 2015-08-28 | Rockford Corporation | W912QR-15-C-0026 | 36448000 | 37081000 | 2017-03-30 | 2018-09-25
2018-07-01 | 2013 | DLA Defense Energy Support Center | DESC1303 |  | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364400 | 66935017 | 2016-02-06 | 2018-03-13
2018-07-31 | 2013 | DLA Defense Energy Support Center | DESC1306 |  | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66377631 | 68688925 | 2017-10-14 | 2018-01-11
2018-07-31 | 2015 | DLA Defense Energy Support Center | DESC1353 |  | 2015-03-13 | 2015-08-19 | Middle Eastern Builders | W912HN-12C-0016 | 15685100 | 16568000 | 2018-05-23 | 2018-09-21
2018-07-01 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2014-12-12 | 2015-04-07 | Nippo Corporation | W912HV-15-C-0005 | 32623000 | 33122640 | 2017-08-23 | 2018-11-15
2017-08-14 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2015-02-27 | 2015-04-07 | Nippo Corporation | W912HV-15-C-005 | 32623000 | 33122640 | 2017-08-23 | 2017-10-30
2018-07-01 | 2015 | DLA Defense Energy Support Center | DESC1404 |  | 2015-04-23 | 2016-01-21 | Gilbane Federal | N39430-15-D-1634-JM01 | 9960000 | 10140442 | 2017-11-13 | 2017-12-13
2017-11-30 | 2014 | DLA Defense Energy Support Center | DESC1407 |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP-15-C-003 | 21288300 | 22083000 | 2017-02-01 | 2017-07-18
2018-07-01 | 2014 | DLA Defense Energy Support Center | DESC1407 |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP-15-C-0003 | 21288300 | 22083000 | 2017-02-01 | 2017-07-18
2018-07-01 | 2015 | DLA Defense Energy Support Center | DESC1463 |  | 2015-04-14 | 2015-09-30 | Structural Asspcoates Omc. | W9128F-15-C-0032 | 8518820 | 8267000 | 2017-04-16 | 2017-06-15
2018-07-31 | 2014 | DLA Defense Energy Support Center | DESC1501 |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637000 | 9333465 | 2016-05-11 | 2018-05-03
2017-06-18 | 2014 | DLA Defense Energy Support Center | DESC1502 | 43 | 2015-01-19 | 2016-04-06 | NOVA Group Inc. | W912BV15C0001 | 32060100 | 32244194 | 2017-05-05 | 2017-07-14
2017-06-18 | 2014 | DLA Defense Energy Support Center | DESC1502 | 43 | 2014-06-17 | 2015-05-04 | Rockford Corporation | W912BV-15-C-0017 | 4556371 | 4733000 | 2016-10-23 | 2017-09-08
2018-07-31 | 2014 | DLA Defense Energy Support Center | DESC1502 A |  | 2014-06-17 | 2014-10-21 | NOVA Group Inc. | W912BV-15-C-0001 | 32060100 | 322532000 | 2017-05-23 | 2018-01-18
2018-07-01 | 2014 | DLA Defense Energy Support Center | DESC1502 B |  | 2015-01-19 | 2015-05-04 | Rockford Corporation | W912BV-15-C-0017 | 4556371 | 4733000 | 2016-10-23 | 2017-07-18
2018-07-01 | 2015 | DLA Defense Energy Support Center | DESC1507 |  | 2015-02-02 | 2016-08-16 | Cape Environemental | N40080-16-C-0161 | 17178089 | 18765895 | 2018-02-07 | 2018-10-15
2018-07-01 | 2015 | DLA Defense Energy Support Center | DESC1508 |  | 2016-03-31 | 2017-03-30 | CB&I Federal Services, LLC | N62473-15-R-0001-0008 | 54095271 | 57324420 | 2020-03-30 | 2020-05-25
2018-07-31 | 2014 | DLA Defense Energy Support Center | DESC1509 |  | 2015-07-27 | 2015-09-23 | Aptim Federal Services | N39430-15-D-1632 | 4783347 | 5296355 | 2017-05-26 | 2018-08-31
2018-07-31 | 2015 | DLA Defense Energy Support Center | DESC1510 |  | 2015-02-02 | 2015-08-20 | Garco Construction Inc. | W912QR-15-C-0025 | 32964000 | 33847000 | 2018-04-07 | 2018-10-05
2018-07-01 | 2015 | DLA Defense Energy Support Center | DESC1515 |  | 2015-04-04 | 2015-08-31 | Meb Genetral Contractors | N4008515C0022 | 22944000 | 24095793 | 2017-07-26 | 2017-08-02
2018-07-01 | 2015 | DLA Defense Energy Support Center | DESC1551 |  | 2014-10-29 | 2015-08-25 | Hensel Phelps Constuction co | N62742-15-C-1308 | 42823800 | 46800984 | 2017-09-23 | 2018-01-31
2018-07-01 | 2016 | DLA Defense Energy Support Center | DESC1602 |  | 2016-08-25 | 2017-03-30 | Sierras Construction | N69450-17-D-2507 | 437270 | 479047 | 2018-02-28 | 2018-04-11
2018-07-01 | 2016 | DLA Defense Energy Support Center | DESC1603 |  | 2017-12-12 | 2018-08-10 | Bietergemeinschaft UVB | W912GB-14-C-0005 | 6125000 | 6125000 | 2019-06-02 | 2019-06-02
2018-07-31 | 2016 | DLA Defense Energy Support Center | DESC1605 |  | 2016-06-23 | 2017-06-02 | STRUCTURAL ASSOCIATES | W912BU16R00370006 | 23170900 | 23170900 | 2019-06-16 | 2019-06-26
2018-07-01 | 2016 | DLA Defense Energy Support Center | DESC1607 |  | 2016-06-24 | 2016-09-16 | W.F. Magann Corporation | W91236-16-C-0025 | 20646000 | 21280000 | 2019-10-12 | 2019-12-12
2018-07-01 | 2017 | DLA Defense Energy Support Center | DESC1611 |  | 2017-11-29 | 2017-11-30 | NOVA Group, Inc | N62473-18-C-2202 | 26868000 | 26926198 | 2020-03-10 | 2020-03-10
2018-07-31 | 2016 | DLA Defense Energy Support Center | DESC1613 |  | 2016-03-29 | 2016-09-28 | NOVA Group Inc | W912PL-16-C-0026 | 32813000 | 32780000 | 2019-07-06 | 2019-10-04
2017-03-23 | 2016 | DLA Defense Energy Support Center | DESC1613 |  | 2016-03-28 | 2016-09-28 | NOVA Group Inc | W912PL-16-C-0026 | 32813000 | 32813000 | 2019-10-04 | 2019-10-04
2017-08-14 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | w | 20577000 | 20577000 | 2019-01-07 | 2019-01-07
2018-07-01 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-22 | Ergotem S.A. | N62470-17-C-5003 | 20577000 | 20986605 | 2019-01-07 | 2019-12-24
2018-07-01 | 2016 | DLA Defense Energy Support Center | DESC1702 |  | 2017-02-09 | 2017-09-30 | MEB General Contractors, Inc. | W91299-17-C-0011 | 20973000 | 20992000 | 2019-06-25 | 2019-09-23
2018-07-01 | 2017 | DLA Defense Energy Support Center | DESC1704 |  | 2017-09-28 | 2017-09-29 | San Juan Construction, Inc. | W9128A-17-C-0008 | 63297670 | 63297670 | 2020-12-27 | 2021-01-06
2018-07-01 | 2017 | DLA Defense Energy Support Center | DESC1705 |  | 2017-05-29 | 2017-05-30 | Black Construction/Mace Internation | N62742-17-C-1313 | 26978100 | 26978100 | 2019-06-29 | 2019-06-29
2018-07-01 | 2017 | DLA Defense Energy Support Center | DESC1706 |  | 2017-09-18 | 2017-09-19 | Cape Environemental | N63450-17-C-1305 | 8783275 | 8783275 | 2019-04-04 | 2019-04-26
2018-07-31 | 2017 | DLA Defense Energy Support Center | DESC1707 |  | 2017-01-30 | 2017-08-07 | ASRC Builders | W911KB-17-C-0030 | 4088355 | 4129621 | 2018-12-15 | 2018-12-03
2018-07-31 | 2017 | DLA Defense Energy Support Center | DESC1708 |  | 2017-03-31 | 2017-08-04 | NIPPO Corporation | W912HV-17-C-0008 | 6804938 | 6817433 | 2019-09-08 | 2019-09-08
2018-07-01 | 2018 | DLA Defense Energy Support Center | DESC1709 |  | 2018-09-20 | 2018-09-21 | Tfs-Aptim JV | N40192-18-C-1300 | 21445996 | 21445996 | 2019-12-15 | 2019-12-15
2018-07-01 | 2016 | DLA Defense Energy Support Center | DESC1710 |  | 2016-06-15 | 2016-09-20 | RELIABLE CONTRACTING GROUP, LLC | W912HN-16-C-0017 / 43104748 | 9568000 | 10447000 | 2018-04-26 | 2019-08-27
2017-12-11 | 2015 | DLA Defense National Stockpile Center | DESC1507 |  | 2015-02-02 | 2015-09-30 | Structural Associates Inc | W9128F-15-C-0032 | 17178089 | 17906802 | 2017-03-23 | 2018-05-16
2018-07-01 | 2018 | DLA Defense Reutilization and Marketing Service | DRMS1701 |  | 2018-06-26 | 2018-08-31 | EMR Inc | N91278-16-C-0035 | 3788549 | 3788549 | 2019-07-06 | 2019-10-11
2018-07-01 | 2016 | DLA Defense Supply Center Philadelphia | DSCP1501 |  | 2016-03-11 | 2016-09-16 | Daniel J. keating Company | N40085-16-C-3037 | 46845550 | 57854412 | 2019-03-30 | 2020-01-02
2018-07-31 | 2014 | DLA Defense Supply Center Richmond | DSCR1401 |  | 2015-02-13 | 2015-06-12 | Hensel Phelps Constuction Co | W91236-15-C-0045 | 71969000 | 85500 | 2018-08-25 | 2018-10-31
2018-07-01 | 2015 | DLA Defense Supply Center Richmond | DSCR1501 |  | 2016-11-08 | 2017-12-14 | SAW Contracting | W91236-18-C-0008 | 6253160 | 6253160 | 2019-08-12 | 2019-08-12
2018-07-13 | 2017 | Defense Health Agency | 14022 |  | 2017-04-28 | 2017-09-13 | Mirait T-Acty JV | W912-HV-17-D-0014 | 14781000 | 14781000 | 2019-10-26 | 2019-10-26
2018-07-13 | 2008 | Defense Health Agency | 47298 |  | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 284436000 | 325143000 | 2013-07-23 | 2016-03-15
2018-07-13 | 2008 | Defense Health Agency | 52332 |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929000 | 28027000 | 2012-05-15 | 2012-08-06
2018-07-13 | 2007 | Defense Health Agency | 58395 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657000 | 2657000 | 2008-06-13 | 2008-06-08
2018-07-13 | 2007 | Defense Health Agency | 58395 | 58395-01 | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472000 | 1472000 | 2009-02-15 | 2009-02-13
2018-07-13 | 2007 | Defense Health Agency | 58395 | 58395-02 | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706000 | 706000 | 2010-04-13 | 2010-04-13
2018-07-13 | 2007 | Defense Health Agency | 58395 | 58395-03 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465000 | 2465000 | 2009-07-24 | 2009-07-24
2018-07-13 | 2007 | Defense Health Agency | 58395 | 58395-04 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 2866000 | 2866000 | 2011-05-06 | 2013-10-31
2018-07-13 | 2007 | Defense Health Agency | 58395 | 58395-05 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 15736000 | 16161000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2007 | Defense Health Agency | 58395 | 63418 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 131264000 | 138491000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2007 | Defense Health Agency | 58395 | 63419 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 185526000 | 185364000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2007 | Defense Health Agency | 58395 | 63420 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 94000000 | 100181000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2007 | Defense Health Agency | 58395 | 63420-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 496000 | 496000 | 2013-10-31 | 2014-01-02
2018-07-13 | 2007 | Defense Health Agency | 58395 | 65324 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 13497000 | 12893000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2007 | Defense Health Agency | 58395 | 65324-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 604000 | 2013-10-31 | 2013-12-06
2018-07-13 | 2007 | Defense Health Agency | 58395 | 71101 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 66955000 | 89587000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2007 | Defense Health Agency | 58395 | 71101-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 7750000 | 7335000 | 2017-03-31 | 2017-05-05
2018-07-13 | 2007 | Defense Health Agency | 58395 | 78210 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 3982000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2013 | Defense Health Agency | 58395 | 78210-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 0 | 141000 | 2017-03-31 | 2017-05-05
2018-07-13 | 2013 | Defense Health Agency | 58395 | 78210-02 | 2017-08-18 | 2017-09-27 | Doyon Project Services, LLC | W912DR-17-D-0012 | 1607000 | 1556000 | 2018-10-26 | 2018-10-26
2018-07-13 | 2014 | Defense Health Agency | 58395 | 78211 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 1000 | 1000 | 2014-05-31 | 2017-09-01
2018-07-13 | 2009 | Defense Health Agency | 59220 |  | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500000 | 29590000 | 2015-08-03 | 2015-09-11
2018-05-14 | 2010 | Defense Health Agency | 61401 |  | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075000 | 11029000 | 2013-01-10 | 2015-01-08
2018-04-12 | 2009 | Defense Health Agency | 62189 |  | 2008-10-27 | 2009-04-03 | Hensel-Phelps Const. Co. | W912BV-09-D-2016 | 47615000 | 51375000 | 2011-10-26 | 2012-02-09
2018-07-13 | 2009 | Defense Health Agency | 64156 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398000 | 17919000 | 2013-06-01 | 2015-06-10
2018-07-13 | 2012 | Defense Health Agency | 65030 |  | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co. | N40083 12 C 0001 | 5835000 | 6195000 | 2013-09-13 | 2014-08-08
2018-07-13 | 2010 | Defense Health Agency | 65270 |  | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133000 | 168708000 | 2014-10-15 | 2016-09-05
2018-07-13 | 2009 | Defense Health Agency | 65731 |  | 2009-01-07 | 2009-04-08 | Total Engineering INC | W912DR-09-C-0030 | 6758000 | 6758000 | 2010-08-08 | 2010-08-31
2018-07-13 | 2009 | Defense Health Agency | 65731 | 65731-01 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 12000000 | 12658000 | 2013-06-01 | 2015-06-10
2018-07-13 | 2009 | Defense Health Agency | 65731 | 67180 | 2009-01-07 | 2009-04-08 | Total Engineering INC | W912DR-09-C-0030 | 436000 | 436000 | 2010-08-08 | 2010-08-31
2018-07-13 | 2009 | Defense Health Agency | 65731 | 67180-01 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30
2018-07-13 | 2009 | Defense Health Agency | 65731 | 67180-02 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 100375000 | 103776000 | 2013-06-01 | 2015-06-10
2018-07-13 | 2009 | Defense Health Agency | 65731 | 67181 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 94608000 | 106045000 | 2013-06-01 | 2015-06-10
2018-07-13 | 2009 | Defense Health Agency | 65731 | 67182 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 37771000 | 2013-06-01 | 2015-06-10
2018-07-13 | 2011 | Defense Health Agency | 66588 |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 30080000 | 31830000 | 2016-05-30 | 2016-09-04
2018-07-13 | 2011 | Defense Health Agency | 66693 |  | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | W912GB-09-C-0029-NA | 31254000 | 32715000 | 2016-04-12 | 2016-05-23
2018-07-13 | 2011 | Defense Health Agency | 67949 |  | 2011-08-19 | 2012-02-14 | Rich Moe Enterprises, LLC | W912DR-12-C-0001 | 1701000 | 1697000 | 2013-04-02 | 2013-04-01
2018-07-13 | 2011 | Defense Health Agency | 67949 | 67949-01 | 2015-03-09 | 2015-09-18 | Edifice- Schlosser JV (Phase II) | W912DR-15-C-0025 | 660000 | 720000 | 2017-03-31 | 2017-05-05
2018-04-12 | 2011 | Defense Health Agency | 67951 |  | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308000 | 16141000 | 2014-07-08 | 2015-08-03
2018-05-14 | 2011 | Defense Health Agency | 67953 |  | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468000 | 3944000 | 2012-11-01 | 2014-05-30
2018-03-13 | 2012 | Defense Health Agency | 70351 |  | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400000 | 26670000 | 2014-06-23 | 2015-08-16
2018-07-13 | 2009 | Defense Health Agency | 70354 |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 162257000 | 212693000 | 2015-03-16 | 2017-12-31
2018-07-13 | 2009 | Defense Health Agency | 70354 | 70354-01 | 2017-07-28 | 2017-09-25 | Anna Lisa Luna Construction, Inc. | W912-PL-17-C-0042 | 3691544 | 4196000 | 2018-05-01 | 2018-06-26
2018-07-13 | 2009 | Defense Health Agency | 70354 | 70354-02 | 2017-07-12 | 2017-09-27 | BHATE Environmental Associates, Inc. | W912DY-15-D-0081 | 1118431 | 1118000 | 2018-12-31 | 2019-08-19
2018-03-13 | 2011 | Defense Health Agency | 70482 |  | 2010-11-19 | 2011-06-03 | McCarthy Building Companies, Inc. | W912HN-11-C-0007 | 23050000 | 25062000 | 2013-06-20 | 2013-12-04
2018-07-13 | 2013 | Defense Health Agency | 71317 |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744000 | 45778000 | 2016-12-30 | 2019-01-10
2018-07-13 | 2013 | Defense Health Agency | 71325 |  | 2012-11-30 | 2013-09-13 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536000 | 47478000 | 2016-10-23 | 2017-10-12
2018-07-13 | 2012 | Defense Health Agency | 71408 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688000 | 19168000 | 2016-12-06 | 2018-05-07
2018-07-13 | 2012 | Defense Health Agency | 71503 |  | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Construction | N69450 12 C 0754 | 19096000 | 20928000 | 2014-09-09 | 2018-05-06
2018-07-13 | 2012 | Defense Health Agency | 71503 | 71503-01 | 2012-03-22 | 2016-08-25 | Surety Company | N69450 12 C 0754 | 9548000 | 419000 | 2017-12-25 | 2018-03-07
2018-07-13 | 2013 | Defense Health Agency | 71507 |  | 2013-02-28 | 2013-12-18 | Turner Construction Company | N40080 14 C 0154 | 41408000 | 43481000 | 2015-10-15 | 2017-02-08
2018-07-13 | 2010 | Defense Health Agency | 71550 |  | 2010-06-16 | 2010-12-14 | Vinci Construction UK Ltd. | CT/INT21/13625 | 13425000 | 12421000 | 2012-08-10 | 2012-09-28
2018-07-13 | 2010 | Defense Health Agency | 71550 | 71550-01 | 2013-04-05 | 2013-06-15 | VolterFitzpatrick | DEUSF/13214 | 68000 | 68000 | 2013-08-30 | 2013-08-30
2018-07-13 | 2010 | Defense Health Agency | 71550 | 71550-02 | 2014-08-20 | 2014-08-25 | Vinci Facilities | CT/INT21/13625 | 69000 | 149000 | 2015-06-30 | 2016-06-30
2018-07-13 | 2016 | Defense Health Agency | 71642 |  | 2016-07-08 | 2016-09-30 | Butt Construction Co. | W912QR-15-D-0002-0014 | 6301000 | 6441000 | 2019-01-12 | 2019-01-12
2018-07-13 | 2012 | Defense Health Agency | 72292 |  | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778000 | 46390000 | 2016-10-14 | 2017-04-21
2018-07-13 | 2015 | Defense Health Agency | 72414 |  | 2015-04-21 | 2015-09-25 | Gilbane Federal JV | W9127S-13-D-6000 | 14598000 | 14654000 | 2018-06-26 | 2018-06-26
2018-07-13 | 2013 | Defense Health Agency | 72419 |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co. Ltd. | W912UM-13-C-0025 | 22361000 | 23519000 | 2017-08-08 | 2019-01-01
2018-07-13 | 2010 | Defense Health Agency | 72430 |  | 2010-06-11 | 2010-08-19 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0005) | 42604000 | 45105000 | 2013-02-20 | 2013-11-19
2018-07-13 | 2010 | Defense Health Agency | 72430 | 72430-01 | 2010-06-11 | 2010-08-31 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0006) | 23216000 | 24153000 | 2012-02-26 | 2012-12-13
2018-07-13 | 2010 | Defense Health Agency | 72481 |  | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 7782000 | 39197000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72251 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 68076000 | 68076000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72481-01 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-10-12
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72481-02 | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488000 | 10635000 | 2012-07-05 | 2012-12-31
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72481-03 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-10-17
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72481-04 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960000 | 2800000 | 2015-08-27 | 2015-11-30
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72481-05 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2015-09-16
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G-11-P | 46000 | 46000 | 2011-11-01 | 2011-11-01
2018-07-13 | 2010 | Defense Health Agency | 72481 | 72786 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 69851000 | 80080000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2010 | Defense Health Agency | 72481 | 76558 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 79914000 | 175303000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2010 | Defense Health Agency | 72481 | 76558-01 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540000 | 657000 | 2014-10-24 | 2014-10-24
2018-07-13 | 2010 | Defense Health Agency | 72481 | 76558-02 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2015-08-27 | 2015-11-30
2017-10-11 | 2010 | Defense Health Agency | 72481 | 77251 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 68076000 | 68076000 | 2016-11-26 | 2018-04-15
2018-07-13 | 2010 | Defense Health Agency | 72481 | 77293 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 198148000 | 124569000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2010 | Defense Health Agency | 72481 | 81407 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 225199000 | 117814000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2010 | Defense Health Agency | 72481 | 81408 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 56858000 | 174897000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2018 | Defense Health Agency | 72481 | 91301 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 100000000 | 188881000 | 2016-11-26 | 2019-07-25
2018-07-13 | 2009 | Defense Health Agency | 72722 |  | 2011-07-01 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 71357000 | 85518000 | 2014-09-09 | 2015-04-17
2018-07-13 | 2009 | Defense Health Agency | 72722 | 72722-01 | 2011-03-07 | 2011-03-20 | A1 Tree Service | W912QR-11-M-0043 | 9600 | 9600 | 2011-04-01 | 2011-04-01
2017-10-11 | 2009 | Defense Health Agency | 72722 | 72722-01 | 2011-03-07 | 2011-03-20 | A1 Tree Service | W912QR-11-C-0040-1 | 9600 | 9600 | 2011-04-01 | 2011-04-01
2018-07-13 | 2009 | Defense Health Agency | 72722 | 72722-02 | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp | W912QR-11-C-0027 | 4990000 | 5847000 | 2014-09-27 | 2015-03-18
2018-07-13 | 2009 | Defense Health Agency | 72722 | 72722-03 | 2015-07-10 | 2015-08-30 | Northview Enterprises | W912QR-14-D-0022-1 | 260000 | 260000 | 2016-06-01 | 2016-06-08
2018-05-14 | 2012 | Defense Health Agency | 72727 |  | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd. | CT/INT21/13487 | 11958000 | 11958000 | 2015-10-30 | 2016-01-06
2018-07-13 | 2017 | Defense Health Agency | 72738 |  | 2017-01-19 | 2017-09-13 | JE Dunn Construction Company | W912-BV-17-C-0014 | 67487000 | 67487000 | 2020-10-31 | 2020-10-31
2018-07-13 | 2011 | Defense Health Agency | 72752 |  | 2011-05-20 | 2011-09-28 | Skanska USA Building Inc. | W9126G-11-C-0053 | 80558000 | 102715000 | 2013-10-01 | 2016-09-02
2018-07-13 | 2012 | Defense Health Agency | 72754 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 76038000 | 82985000 | 2014-07-29 | 2016-09-02
2018-07-13 | 2012 | Defense Health Agency | 72754 | 80793 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22835000 | 2014-07-29 | 2016-09-02
2018-07-13 | 2013 | Defense Health Agency | 72808 |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703000 | 19971000 | 2015-03-16 | 2017-01-08
2018-07-13 | 2009 | Defense Health Agency | 74650 |  | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989000 | 552173000 | 2014-05-31 | 2015-11-04
2018-07-13 | 2009 | Defense Health Agency | 74650 | 74650-01 | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc | SP0600-08-C-8250 | 10225000 | 11093000 | 2012-02-25 | 2012-06-02
2018-07-13 | 2009 | Defense Health Agency | 74650 | 74650-02 | 2010-02-12 | 2010-03-08 | TTG Utilities, LP | W9126G-10-C-0032 | 301000 | 301000 | 2010-05-30 | 2010-06-30
2018-07-13 | 2009 | Defense Health Agency | 74650 | 74650-03 | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc. | W912DY-05-D-0011 | 1018000 | 1040000 | 2010-10-18 | 2010-10-05
2018-07-13 | 2009 | Defense Health Agency | 74650 | 74650-04 | 2010-04-11 | 2010-06-11 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0002 | 6304000 | 10156000 | 2012-01-11 | 2012-09-20
2018-07-13 | 2009 | Defense Health Agency | 74650 | 74650-05 | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0003 | 17290000 | 15383000 | 2012-06-29 | 2013-12-15
2018-07-13 | 2012 | Defense Health Agency | 76007 |  | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 14117000 | 2023-12-30 | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 14043 | 2018-03-30 | 2018-03-31 | Federal Republic of Germany | W912GB-10-C-0031 | 28618000 | 28618000 | 2022-12-30 | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, ABG4 P00058 | 2539000 | 3361000 | 2016-04-30 | 2017-01-30
2017-03-31 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 36640000 | 36640000 | 2020-12-30 | 2020-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00085 | 35933000 | 34966000 | 2020-12-30 | 2020-12-30
2017-05-31 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 36640000 | 36640000 | 2020-12-30 | 2020-12-30
2017-11-14 | 2012 | Defense Health Agency | 76007 | 72661-02 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 53054000 | 53054000 | 2019-04-30 | 2020-09-30
2017-09-13 | 2012 | Defense Health Agency | 76007 | 72661-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 21968000 | 21968000 | 2018-07-30 | 2018-12-30
2017-06-30 | 2012 | Defense Health Agency | 76007 | 72661-2 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 83000000 | 83000000 | 2019-04-30 | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 72662 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 57036000 | 57036000 | 2019-04-30 | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 72662-01 | 2015-08-19 | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 32075000 | 32075000 | 2022-12-30 | 2022-12-30
2018-06-13 | 2012 | Defense Health Agency | 76007 | 72662-02 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 56622000 | 56622000 | 2019-04-30 | 2020-09-30
2017-09-13 | 2012 | Defense Health Agency | 76007 | 72662-2 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 83000000 | 83000000 | 2019-04-30 | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-01 | 2012-02-01 | 2012-03-15 | Joint Venture Bautra Baugesellschaft mbH / SRS Service GmbH | W912GB-10-C-0031, ABG4 P00023 | 265000 | 297000 | 2014-04-04 | 2014-04-04
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-02 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00030 | 694489 | 1686000 | 2014-10-29 | 2015-01-21
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-03 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00043 | 5321000 | 6450000 | 2016-04-30 | 2016-08-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-04 | 2012-02-01 | 2012-03-15 | Hermanns RTE Rohrleitungs- undd Tiefbau Erfurt GmbH | W912GB-10-C-0031, ABG4 P00062 | 5444000 | 5628000 | 2016-12-15 | 2017-12-15
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-05 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH (ABG4 P00033) | W912GB-10-C-0031, ABG4 P00033 | 141234 | 142000 | 2015-03-30 | 2015-05-01
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-06 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH | W912GB-10-C-0031, ABG4 P00031 | 17713 | 17713 | 2014-12-31 | 2014-12-31
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-07 | 2012-02-01 | 2012-03-15 | FRG/CREOS GmbH | W912GB-10-C-0031, ABG4 P00032 | 482902 | 482902 | 2014-10-16 | 2014-10-16
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-08 | 2012-02-01 | 2012-03-15 | FRG/Omexom GA Sud GmbH | W912GB-10-C-0031, ABG4 P00066 | 89440 | 89440 | 2016-10-30 | 2016-12-30
2017-04-30 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB-10-C-0031 | 419000 | 419000 | 2016-12-15 | 2017-11-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB-10-C-0031, P00071 | 419000 | 419000 | 2016-12-15 | 2019-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-10 | 2012-02-01 | 2012-03-15 | FRG/Zeppelin STREIF Baulogistik GmbH | W912GB-10-C-0031, ABG4 P00039 | 5339748 | 6697000 | 2022-12-30 | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-11 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 5339000 | 5339000 | 2023-12-30 | 2023-12-30
2017-06-30 | 2012 | Defense Health Agency | 76007 | 76007-12 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 37601000 | 37601000 | 2020-12-30 | 2020-12-30
2017-05-31 | 2012 | Defense Health Agency | 76007 | 76007-12 | 2012-02-01 | 2012-03-15 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, ABG4 P00058 | 2539000 | 3109000 | 2016-04-30 | 2017-01-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-13 | 2012-02-01 | 2012-03-15 | FRG/Deutsche Telekom Technik GmbH | W912GB-10-C-0031, ABG4 P00037 | 1000 | 1000 | 2014-12-31 | 2014-12-31
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-14 | 2012-02-01 | 2012-03-15 | FRG/ABG3 | W912GB-10-C-0031 | 30820000 | 30820000 | 2022-12-30 | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76007-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 21968000 | 22309000 | 2018-07-30 | 2018-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 76872 | 2015-08-19 | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 580259000 | 580259000 | 2022-12-30 | 2023-12-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 81412-02 | 2017-04-25 | 2017-05-25 | Federal Republic of Germany | W912GB-10-C-0031 | 16591000 | 16591000 | 2023-12-30 | 2023-12-30
2018-07-13 | 2014 | Defense Health Agency | 77000 |  | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR-15-C-0015 | 206445000 | 212257000 | 2019-02-19 | 2019-03-20
2018-07-13 | 2012 | Defense Health Agency | 77154 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 131374000 | 139574000 | 2016-12-06 | 2018-04-01
2018-07-13 | 2012 | Defense Health Agency | 77154 | 81291 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 66430000 | 67012000 | 2016-12-06 | 2018-04-01
2018-07-13 | 2014 | Defense Health Agency | 77922 |  | 2014-02-25 | 2014-08-19 | Gilbane | W9127S-13-D-6000 DM01 | 45629000 | 47771000 | 2018-01-23 | 2018-06-13
2018-07-13 | 2013 | Defense Health Agency | 77979 |  | 2013-09-03 | 2014-03-27 | JE Dunn + HWA | W9127S-13-D-6001 DM01 | 45938000 | 48377000 | 2018-02-10 | 2018-08-31
2018-07-13 | 2016 | Defense Health Agency | 77986 |  | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005 | 27928000 | 27928000 | 2019-06-04 | 2019-06-04
2018-07-13 | 2013 | Defense Health Agency | 78143 |  | 2013-01-14 | 2013-08-22 | Blinderman Constr Co. | N40083 13 C 0003 | 14864000 | 14901000 | 2015-01-15 | 2018-03-22
2018-07-13 | 2013 | Defense Health Agency | 78143 | 78143-01 | 2016-10-30 | 2017-03-22 | accel Construction Services Group | N40085-17-C-0701 | 2077000 | 2077000 | 2018-05-23 | 2018-03-22
2018-07-13 | 2013 | Defense Health Agency | 78144 |  | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354000 | 14791000 | 2015-03-17 | 2015-12-21
2018-07-13 | 2013 | Defense Health Agency | 78146 |  | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254000 | 7413000 | 2014-12-06 | 2015-11-23
2018-07-13 | 2016 | Defense Health Agency | 78150 |  | 2015-11-05 | 2016-08-08 | Caddell-Nan joint Venture | N62742 16 C 1312 | 79722000 | 80819000 | 2018-12-21 | 2019-04-15
2018-04-12 | 2012 | Defense Health Agency | 79554 |  | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200000 | 14457000 | 2014-02-22 | 2014-06-02
2018-07-13 | 2009 | Defense Health Agency | 79845 |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction Company | W9126G-08-D-0057 CL01 | 51133000 | 53720000 | 2014-11-06 | 2016-12-31
2017-05-31 | 2009 | Defense Health Agency | 79845 |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction Company | W9126G-08-D-0057 | 51133000 | 59456000 | 2014-11-06
2018-07-13 | 2013 | Defense Health Agency | 80306 |  | 2013-07-25 | 2013-09-12 | G-W Management Services Inc. | N40080 10 D 0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25
2018-07-13 | 2013 | Defense Health Agency | 80306 | 80306-01 | 2014-03-15 | 2016-09-01 | Whiting Turner Contracting Co | N40080 16 C 0172 | 29435000 | 30018000 | 2017-12-10 | 2018-05-01
2018-07-13 | 2013 | Defense Health Agency | 80307 |  | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898000 | 6379000 | 2015-04-08 | 2018-07-16
2018-05-14 | 2013 | Defense Health Agency | 80308 |  | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947000 | 25013000 | 2016-02-12 | 2016-09-18
2018-07-13 | 2016 | Defense Health Agency | 80412 |  | 2016-01-27 | 2016-05-17 | Swinerton Builders | W9128A-16-C-0004 | 26084000 | 26932000 | 2017-12-08 | 2018-07-31
2018-07-13 | 2016 | Defense Health Agency | 80412 | 80412-01 | 2016-10-21 | 2018-02-08 | Hensel-Phelps Const. Co. | W9128A-18-C-0001 | 74987000 | 74987000 | 2020-05-21 | 2020-05-21
2018-07-13 | 2014 | Defense Health Agency | 80904 |  | 2014-01-30 | 2015-03-30 | Whiting Turner Contracting Co | N40080 15 C 0156 | 38490000 | 44151000 | 2017-02-07 | 2018-08-30
2018-07-13 | 2017 | Defense Health Agency | 80906 |  | 2017-05-23 | 2017-09-28 | Whiting Turner Contracting Co | N40080-17-C-0039 | 26410000 | 26409000 | 2019-05-10 | 2019-05-10
2018-07-13 | 2014 | Defense Health Agency | 80913 |  | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835000 | 15828000 | 2016-04-16 | 2017-06-08
2018-07-13 | 2014 | Defense Health Agency | 81340 |  | 2014-03-17 | 2014-06-30 | Gilbane | W9127S-13-D-6000 DY01 | 11684000 | 11685000 | 2016-07-28 | 2016-10-30
2018-02-14 | 2016 | Defense Health Agency | 81422 |  | 2016-12-01 | 2017-03-09 | AMG Contractors, LLC | W9126G-17-C-0020 | 1251000 | 1265000 | 2017-06-23 | 2017-07-14
2018-07-13 | 2016 | Defense Health Agency | 81422 | 81422-01 | 2016-12-01 | 2017-03-09 | AMG Contractors, LLC | W9126G-17-C-0020 | 1251000 | 1265000 | 2017-06-23 | 2017-06-23
2018-07-13 | 2015 | Defense Health Agency | 81423 |  | 2015-03-20 | 2015-09-03 | JE Dunn Construction Company | W9127S-13-D-6001 | 33473000 | 34115000 | 2018-09-27 | 2018-10-18
2018-07-13 | 2015 | Defense Health Agency | 81430 |  | 2016-06-20 | 2018-01-18 | JE Dunn Construction Company | W9127S-13-D-6001 TO W91236-18-F-0014 | 52181000 | 52181000 | 2021-03-18 | 2021-03-18
2018-07-13 | 2014 | Defense Health Agency | 81436 |  | 2015-08-25 | 2016-03-17 | Contrack Watts Inc. | W912ER-11-D-0009-0012 | 24784000 | 25447000 | 2019-04-20 | 2019-05-05
2018-07-13 | 2015 | Defense Health Agency | 81627 |  | 2015-10-30 | 2016-03-11 | Orion Construction, Inc. | W912DW-16-C-0006 | 2062000 | 2315000 | 2017-11-14 | 2017-09-14
2018-07-13 | 2014 | Defense Health Agency | 81631 |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc. | W912HN-11-D-0043-0044 | 1436000 | 1438000 | 2016-02-01 | 2016-02-01
2018-04-12 | 2014 | Defense Health Agency | 81706 |  | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 1795000 | 1819000 | 2015-10-28 | 2015-12-11
2018-07-13 | 2016 | Defense Health Agency | 86953 |  | 2016-07-25 | 2017-03-23 | M.A. Mortenson Company | W912QR-17-C-0009 | 54767000 | 54843000 | 2021-05-16 | 2021-05-09
2017-11-14 | 2016 | Defense Health Agency | 86953 | 86953-01 | 2016-07-25 | 2017-03-23 | M.A. Mortenson Company | W912QR-17-C-0009 | 1000 | 1000 | 2021-05-16 | 2021-05-16
2018-07-13 | 2017 | Defense Health Agency | 87015 |  | 2016-03-14 | 2016-07-21 | M&M | N62473 15 D 2437 DO 0003 | 2854000 | 2868000 | 2018-04-06 | 2018-04-04
2018-07-25 | 2013 | Defense Information Systems Agency | 13DISA01 |  | 2015-08-05 | 2015-08-19 | Bauamt Reutlingen | W912GB-15-C-011 | 2219820 | 2219820 | 2015-08-19 | 2016-12-31
2018-07-25 | 2014 | Defense Information Systems Agency | 14DISA01 |  | 2017-06-26 | 2017-07-13 | Heartwood Pacific, LLC | N6274217F0307 | 2615000 | 2615000
2018-07-25 | 2015 | Defense Information Systems Agency | 15DISA01 | 1 |  |  |  |  | 745000 | 745000
2018-07-25 | 2016 | Defense Information Systems Agency | 16DISA01
2018-07-25 | 2017 | Defense Information Systems Agency | 17DISA01
2018-07-25 | 2018 | Defense Information Systems Agency | 18DISA01
2018-07-25 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11
2017-05-05 | 2012 | Defense Intelligence Agency | DIA12000001 |  | 2016-10-09 | 2016-11-09 | Manhattan Construction Company | N40080-17-C-1601 | 12569000 | 12569000 | 2017-09-19 | 2017-12-31
2018-03-04 | 2010 | DoD Education Activity | AM 856 07 |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764000 | 20571550 | 2013-12-14 | 2014-07-09
2018-07-10 | 2014 | DoD Education Activity | AM00021 |  | 2016-11-07 | 2017-11-20 | John C. Grimberg CO., Inc. | N4008018C0006 | 46630000 | 49879381 | 2020-01-09 | 2020-01-09
2018-07-09 | 2012 | DoD Education Activity | AM00023 |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987000 | 34750000 | 2015-12-11 | 2016-05-30
2018-01-04 | 2012 | DoD Education Activity | AM00023 | 23 | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2015-12-11 | 2016-05-30
2018-07-09 | 2012 | DoD Education Activity | AM00023 | 28 | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2015-12-11 | 2016-05-30
2018-07-09 | 2014 | DoD Education Activity | AM00024 |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4896600 | 5048862 | 2016-01-21 | 2016-05-22
2018-07-10 | 2012 | DoD Education Activity | AM00025 |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 26406000 | 26367967 | 2016-06-01 | 2019-04-30
2018-07-09 | 2012 | DoD Education Activity | AM00026 |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685000 | 34810657 | 2015-11-11 | 2017-03-08
2018-07-09 | 2012 | DoD Education Activity | AM00026 | 43 | 2013-03-04 | 2015-11-05 | Northview Enterprises, Incorporated | W912QR-14-D-0022/36144721 | 1169000 | 1239078 | 2016-11-30 | 2016-11-30
2018-07-09 | 2012 | DoD Education Activity | AM00027 |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 32260396 | 34480 | 2016-04-21 | 2016-06-30
2017-01-08 | 2012 | DoD Education Activity | AM00027 |  | 2012-10-31 | 2013-12-20 | J&J Contractors, Inc. | W912WJ-14-C-0007 / 53881843 | 45000 | 45000 | 2016-04-21 | 2016-06-30
2018-07-09 | 2012 | DoD Education Activity | AM00027 | 88 | 2012-10-31 | 2013-12-20 | J&J Contractors, Inc. | W912WJ-14-C-0007 / 53881843 | 0 | 0 | 2016-04-21 | 2016-06-30
2018-03-04 | 2013 | DoD Education Activity | AM00028 |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39361936 | 41702289 | 2015-12-17 | 2017-03-01
2018-01-04 | 2013 | DoD Education Activity | AM00028 | 27 | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001/51839544 | 145726 | 145726 | 2015-12-17 | 2017-03-01
2018-03-04 | 2013 | DoD Education Activity | AM00028 | 44 | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001/51839544 | 145726 | 145726 | 2015-12-17 | 2017-03-01
2018-07-09 | 2013 | DoD Education Activity | AM00028 | 82 | 2013-03-14 | 2013-11-27 | Northview Enterprises, Inc. | W912QR-14-D-0022 / 59141072 | 1083000 | 1083000 | 2018-10-06 | 2018-12-06
2018-07-09 | 2014 | DoD Education Activity | AM00031 |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278-12-D-0039/30132665 | 32124000 | 33068283 | 2017-02-10 | 2017-10-31
2018-07-09 | 2016 | DoD Education Activity | AM00033 |  | 2016-07-25 | 2017-03-01 | DOBCO, Inc. | W912DS-17-C-0005 / 44966911 | 48535000 | 48667466 | 2020-03-05 | 2019-06-01
2018-07-09 | 2014 | DoD Education Activity | AM00034 |  | 2014-06-20 | 2014-11-10 | Walsh Group Ventures | W912QR-15-C-0001/34496304 | 50930542 | 52739 | 2017-02-25 | 2017-12-06
2018-07-09 | 2016 | DoD Education Activity | AM00035 |  | 2016-03-14 | 2017-03-29 | POETTKER CONSTRUCTION COMPANY | W912HN-17-C-0005 / 37035966 | 27223000 | 27187000 | 2019-04-26 | 2019-07-25
2018-07-10 | 2014 | DoD Education Activity | AM00037 |  | 2014-07-25 | 2015-08-18 | Roy Anderson Corp | N6945014R17600005 | 43348000 | 40458826 | 2018-06-28 | 2019-02-26
2018-07-09 | 2014 | DoD Education Activity | AM00038 |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40092900 | 40973370 | 2016-09-14 | 2017-07-03
2018-04-09 | 2014 | DoD Education Activity | AM00038 | 29 | 2014-07-22 | 2016-05-09 | Canoochee EMC | DACA87-01-D-0014 / 53303340 | 467157 | 467157 | 2017-01-11 | 2017-03-23
2018-03-04 | 2014 | DoD Education Activity | AM00040 |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 35264000 | 36161861 | 2016-03-28 | 2016-06-10
2018-07-09 | 2014 | DoD Education Activity | AM00046 |  | 2013-02-06 | 2013-12-20 | J&J Contractors, Inc. | W912WJ-14-C-0007 / 34504372 | 0 | 1292000 | 2016-04-21 | 2016-06-30
2018-07-09 | 2014 | DoD Education Activity | AM00046 | 246 | 2013-02-06 | 2016-03-16 | J&J Contractors & Engineers, Inc. | W912WJ-17-C-0004 / 57439943 | 35970000 | 36383000 | 2019-09-09 | 2019-08-20
2016-11-03 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc. | W91278-12--D-0037-CV03 | 45411000 | 45411000 | 2020-06-02 | 2020-06-02
2018-07-09 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037 / 39179628 | 25624589 | 26380000 | 2020-06-10 | 2020-05-03
2018-07-09 | 2016 | DoD Education Activity | AM00048 | 8 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037 / 54560299 | 4286000 | 4286000 | 2020-06-10 | 2019-05-03
2018-07-09 | 2016 | DoD Education Activity | AM00048 | 9 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037 / 54560300 | 15500000 | 15500000 | 2020-06-10 | 2019-05-03
2018-07-09 | 2014 | DoD Education Activity | AM00050 |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791250 | 33676000 | 2016-10-31 | 2018-05-30
2018-07-10 | 2015 | DoD Education Activity | AM00103 |  | 2015-09-15 | 2016-07-01 | Munilla Construction Management, LLC | N69450 16 C 1612 | 65190000 | 67780231 | 2018-11-26 | 2019-03-14
2018-07-09 | 2016 | DoD Education Activity | AM00110 |  | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278-12-D-0037 / 41084584 | 39010686 | 39139730 | 2020-05-28 | 2020-07-15
2018-07-10 | 2016 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N62470 16 C 6003 | 9233000 | 7351588 | 2019-03-27 | 2019-07-31
2017-07-28 | 2016 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N62470 16 c 6003 | 6498338 | 7093000 | 2019-03-27 | 2019-03-27
2017-04-03 | 2015 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N62470 16 c 6003 | 6498338 | 7089005 | 2019-03-27 | 2017-04-26
2018-07-09 | 2016 | DoD Education Activity | AM00123 |  | 2016-02-22 | 2016-07-21 | Walsh Construction Company II. LLC | W912QR-16-C-0012 / 44615921 | 20483300 | 21300023 | 2018-05-08 | 2018-08-31
2018-07-10 | 2015 | DoD Education Activity | AM001461 |  | 2016-02-26 | 2017-03-29 | WALSH FEDERAL, LLC | N4008517C8322 | 47374000 | 45187278 | 2020-03-28 | 2020-03-28
2017-11-07 | 2011 | DoD Education Activity | AM8193 01 |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968494 | 49871630 | 2014-04-19 | 2016-08-15
2017-10-04 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029 / 59013541 | 204000 | 204000 | 2019-05-08 | 2019-08-08
2017-06-04 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-08-19 | SKE Support Services GmbH | W912GB-15-D-0013 / 53705899 | 133430 | 133430 | 2017-02-15 | 2017-04-26
2018-07-09 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029 / 27243529 | 77816984 | 80093000 | 2019-05-08 | 2019-08-08
2018-07-09 | 2012 | DoD Education Activity | EU00031 | 89 | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029 / 59013541 | 0 | 204000 | 2019-05-08 | 2019-08-08
2018-07-09 | 2013 | DoD Education Activity | EU00034 |  | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006 / 44599966 | 41569129 | 42693778 | 2019-02-21 | 2019-05-22
2018-07-09 | 2013 | DoD Education Activity | EU00034 | 45 | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006 / 50005397 | 0 | 388829 | 2019-02-21 | 2019-05-22
2018-07-09 | 2014 | DoD Education Activity | EU00037 |  | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 52029275 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-04-09 | 2014 | DoD Education Activity | EU00037 | 1 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 52029275 | 89535967 | 89535967 | 2022-01-23 | 2021-08-10
2018-07-09 | 2014 | DoD Education Activity | EU00037 | 1 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 52029300 | 89535967 | 89535967 | 2022-01-23 | 2021-08-10
2018-07-09 | 2014 | DoD Education Activity | EU00037 | 2 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 55123733 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-04-09 | 2014 | DoD Education Activity | EU00037 | 2 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 52029275 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-04-09 | 2014 | DoD Education Activity | EU00037 | 3 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 52029275 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-07-09 | 2014 | DoD Education Activity | EU00037 | 3 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 55123739 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-04-09 | 2014 | DoD Education Activity | EU00037 | 4 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 52029275 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-07-09 | 2014 | DoD Education Activity | EU00037 | 4 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 55123745 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-07-09 | 2014 | DoD Education Activity | EU00037 | 5 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 55124187 | 0 | 0 | 2022-01-23 | 2021-08-10
2018-04-09 | 2014 | DoD Education Activity | EU00037 | 5 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024 / 52029275 | 0 | 0 | 2022-01-23 | 2021-08-10
2016-11-03 | 2014 | DoD Education Activity | EU00040 |  | 2016-03-14 | 2016-07-20 | LBB Kaiserslautern | W912GB-12-C-0025 / 52029339 | 2898099 | 2898099
2018-04-09 | 2014 | DoD Education Activity | EU00040 |  | 2015-10-21 | 2016-03-14 | SKE Support Services GmbH | W912GB-15-D-0013 / 51896424 | 133763 | 135866 | 2016-06-22 | 2016-10-21
2018-07-09 | 2014 | DoD Education Activity | EU00040 | 6 | 2016-10-21 | 2017-05-09 | LBB Kaiserslautern | W912GB-12-C-0025 / 52029339 | 43000974 | 116000 | 2019-11-04 | 2020-02-08
2017-06-04 | 2014 | DoD Education Activity | EU00040 | 60 | 2015-10-21 | 2016-09-06 | LBB Kaiserslautern | W912GB-12-C-0025 / 52029339 | 47851843 | 47881681 | 2017-05-09 | 2017-04-26
2017-06-04 | 2014 | DoD Education Activity | EU00040 | 61 | 2015-10-21 | 2016-09-06 | LBB Kaiserslautern | W912GB-12-C-0025 / 51896465 | 0 | 0 | 2019-06-18 | 2017-04-26
2017-06-04 | 2014 | DoD Education Activity | EU00040 | 62 | 2015-10-21 | 2016-09-06 | LBB Kaiserslautern | W912GB-12-C-0025 / 54333375 | 0 | 0 |  | 2017-04-26
2018-07-09 | 2013 | DoD Education Activity | EU00043 |  | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817336 | 0 | 0 | 2017-06-21 | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | EU00043 | 33 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817338 | 3597452 | 3597452 | 2017-06-21 | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | EU00043 | 34 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 42152391 | 44508000 | 2017-06-21 | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | EU00043 | 35 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 635478 | 797141 | 2017-06-21 | 2017-05-11
2018-07-09 | 2013 | DoD Education Activity | EU00043 | 36 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 46876264 | 1466278 | 1524447 | 2017-06-21 | 2017-05-11
2018-07-09 | 2014 | DoD Education Activity | EU00049 |  | 2015-11-24 | 2016-06-03 | Federal Republic of Germany | W912GB-12-C-0041 / 50728702 | 56357984 | 56357984 | 2022-10-18 | 2021-08-15
2018-07-09 | 2016 | DoD Education Activity | EU00051 |  | 2017-04-30 | 2017-07-20 | Staatliches Hochbauamt Reutlingen | W912GB-12-C-0030 / 54892650 | 7217000 | 7217000 | 2020-05-10 | 2020-05-10
2018-03-04 | 2012 | DoD Education Activity | EU00062 |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366274 | 5728662 | 2015-09-20 | 2016-01-01
2017-10-04 | 2012 | DoD Education Activity | EU00062 |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 282692 | 282692 | 2015-09-20 | 2016-01-01
2017-10-04 | 2012 | DoD Education Activity | EU00062 | 42 | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366274 | 5728662 | 2015-09-20 | 2016-01-01
2018-03-04 | 2012 | DoD Education Activity | EU00062 | 42 | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 282692 | 282692 | 2015-09-20 | 2016-01-01
2018-07-09 | 2015 | DoD Education Activity | EU00064 |  | 2017-06-29 | 2017-09-21 | Joint Venture WMV Brussels American School | W912GB-17-C-0018 / 44739768 | 28765 | 28765 | 2020-10-24 | 2021-04-22
2018-07-09 | 2015 | DoD Education Activity | EU00064 | 64 | 2017-06-29 |  |  | W912GB-17-C-0018 / 52162166 | 0 | 0
2018-07-09 | 2016 | DoD Education Activity | EU00068 |  | 2017-09-05 | 2018-04-20 | Staatliches Hochbauamt Amberg | W912GB-12-C-0036 / 57200363 | 31185000 | 31220000 | 2021-01-07 | 2021-02-16
2018-07-09 | 2014 | DoD Education Activity | EU00072 |  | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB-12-C-0022 / 48719947 | 51050171 | 51282000 | 2018-04-11 | 2018-07-10
2017-10-04 | 2014 | DoD Education Activity | EU00072 |  | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB-12-C-0022 / 50815967 | 16940 | 259896 | 2018-04-11 | 2018-07-10
2018-07-09 | 2014 | DoD Education Activity | EU00072 | 7 | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB-12-C-0022 / 50815967 | 16940 | 265000 | 2018-04-11 | 2018-07-10
2018-07-09 | 2010 | DoD Education Activity | EUR826708 |  | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 17387653 | 61455433 | 62345000 | 2018-03-01 | 2018-07-16
2017-11-07 | 2010 | DoD Education Activity | EUR826708 | 3 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 39972656 | 3327125 | 3332638 | 2018-03-01 | 2018-06-04
2017-11-07 | 2010 | DoD Education Activity | EUR826708 | 4 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 45239562 | 0 | 0 | 2018-03-01 | 2018-06-04
2018-07-09 | 2015 | DoD Education Activity | PA00017 |  | 2016-07-15 | 2016-12-23 | Nippo Corporation | W912HV-17-C-0004 / 37880445 | 61521811 | 61212666 | 2020-11-17 | 2021-01-22
2018-07-09 | 2014 | DoD Education Activity | PA00018 |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28953797 | 32062887 | 2016-10-03 | 2017-06-26
2017-11-07 | 2013 | DoD Education Activity | PA00020 |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187221 | 32377858 | 2015-12-09 | 2016-05-22
2018-07-09 | 2013 | DoD Education Activity | PA00021 |  | 2015-06-12 | 2016-02-19 | Nippo Corporation | W912HV-16-C-0004 / 32602254 | 47987000 | 48514855 | 2018-11-03 | 2019-03-05
2018-07-09 | 2015 | DoD Education Activity | PA00023 |  | 2016-06-13 | 2016-11-22 | NES PACIFIC LIMITED LIABILITY CO. | W912HV-17-C-0002 / 37064811 | 27722277 | 28350000 | 2019-05-28 | 2019-07-08
2018-07-09 | 2012 | DoD Education Activity | PA00027 |  | 2014-07-25 | 2014-12-24 | Daiwa Odakyu Construction - JDC JV | W912HV-15-C-0002/ 29312181 | 40546769 | 43885000 | 2018-12-21 | 2019-04-09
2018-07-09 | 2013 | DoD Education Activity | PA00028 |  | 2016-06-21 | 2017-07-18 | Gilbane Japan GK | W912HV-17-C-0007 / 32174203 | 26840313 | 26885072 | 2019-07-19 | 2020-01-30
2018-07-09 | 2013 | DoD Education Activity | PA00030 |  | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476284 | 104758000 | 2017-04-01 | 2018-04-02
2018-07-09 | 2017 | DoD Education Activity | PA00032 |  | 2017-06-22 | 2017-12-22 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV-18-C-0002 / 37880684 | 72844929 | 72844929 | 2021-02-15 | 2021-05-02
2018-07-09 | 2013 | DoD Education Activity | PA00033 |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475000 | 1475000 | 2016-10-24 | 2018-01-31
2018-07-09 | 2013 | DoD Education Activity | PA00033 | 38 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469000 | 2469000 | 2016-10-24 | 2018-01-31
2018-07-09 | 2013 | DoD Education Activity | PA00033 | 39 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612000 | 4612000 | 2016-10-24 | 2018-01-31
2018-07-09 | 2013 | DoD Education Activity | PA00033 | 40 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418175 | 68025893 | 2016-10-24 | 2018-01-31
2018-02-07 | 2014 | DoD Education Activity | PA00035 |  | 2014-09-23 | 2015-02-18 | Nippo Corporation | W912HV-15-C-0003 / 34596540 | 31459277 | 33004995 | 2016-10-02 | 2017-06-15
2018-06-30 | 2015 | Marine Corps Active | M00146193 |  | 2015-06-17 | 2016-12-22 | GARNEY COMPANIES, INC. | N4008517C8315 AWD | 55798000 | 53806000 | 2020-02-28 | 2020-04-29
2018-06-30 | 2016 | Marine Corps Active | M00146194 |  | 2016-03-29 | 2016-08-31 | M A MORTENSON COMPANY | N4008516C5506 AWD | 28561000 | 27659000 | 2018-10-04 | 2018-10-04
2018-06-30 | 2017 | Marine Corps Active | M00146224 |  | 2017-01-17 | 2017-05-30 | WHITING-TURNER CONTRACTING CO | N4008517C8306 AWD | 13208000 | 12752000 | 2019-01-31 | 2019-01-31
2018-06-30 | 2016 | Marine Corps Active | M00146229 |  | 2016-07-18 | 2016-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008516D6301 0002 | 4160000 | 4302000 | 2017-10-02 | 2018-03-21
2017-09-30 | 2013 | Marine Corps Active | M00243313 |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974000 | 12005000 | 2015-04-29 | 2016-11-30
2018-06-30 | 2014 | Marine Corps Active | M00243520 |  | 2015-01-29 | 2015-09-29 | MESA ENERGY SYSTEMS, INC. | N6247315C3602 AWD | 43778000 | 35059000 | 2018-01-11 | 2019-04-22
2018-06-30 | 2016 | Marine Corps Active | M00263398 |  | 2016-07-22 | 2016-09-27 | R. C. CONSTRUCTION | N4008516C5505 AWD | 25643000 | 24384000 | 2018-04-20 | 2018-04-20
2018-06-30 | 2014 | Marine Corps Active | M002641406 |  | 2014-12-18 | 2015-05-01 | BISCAYNE CONTRACTORS, INC. | N4008015C2007 AWD | 4439000 | 4369000 | 2016-11-21 | 2018-09-03
2017-09-30 | 2013 | Marine Corps Active | M00264562 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462000 | 29578000 | 2016-11-06 | 2018-01-22
2017-09-30 | 2013 | Marine Corps Active | M00264572 |  | 2015-04-24 | 2015-09-30 | CORINTHIAN CONTRACTORS, INC | N4008015C0169 | 14182000 | 13927000 | 2017-05-28 | 2017-05-28
2018-06-30 | 2015 | Marine Corps Active | M00264635 |  | 2016-05-16 | 2016-11-16 | G-W MANAGEMENT SERVICES, LLC | N4008017C0014 AWD | 10883000 | 10949000 | 2018-03-25 | 2018-03-25
2017-11-30 | 2015 | Marine Corps Active | M00264635 |  | 2016-05-16 | 2016-11-16 | G-W MANAGEMENT SERVICES, LLC | N4008015C2010 *AWD | 10883000 | 10375000 | 2018-03-25 | 2018-03-25
2018-06-30 | 2014 | Marine Corps Active | M00264677 |  | 2015-10-28 | 2016-03-31 | HARKINS BUILDERS INC. | N4008016C0151 AWD | 27064000 | 26555000 | 2018-01-05 | 2018-07-04
2018-06-30 | 2016 | Marine Corps Active | M00264707 |  | 2016-05-16 | 2017-04-27 | WHITING-TURNER CONTRACTING CO | N4008017C4421 AWD | 42763000 | 40422000 | 2019-12-03 | 2019-12-03
2017-11-30 | 2016 | Marine Corps Active | M00264707 |  | 2016-05-16 | 2017-04-27 | WHITING-TURNER CONTRACTING CO | N4008017C4421 | 42763000 | 40271000 | 2019-12-03 | 2019-12-03
2017-11-30 | 2016 | Marine Corps Active | M00318116 |  | 2016-03-16 | 2016-08-08 | 1GBR7 - PAVE-TECH INC | N6274216C1307 | 12857000 | 12024000 | 2018-06-09 | 2018-06-09
2018-06-30 | 2016 | Marine Corps Active | M00318116 |  | 2016-03-16 | 2016-08-08 | PAVE-TECH INC | N6274216C1307 AWD | 12857000 | 13726000 | 2018-06-09 | 2018-08-14
2018-06-30 | 2015 | Marine Corps Active | M00318778 |  | 2014-01-10 | 2015-03-13 | DAWSON-HAWAIIAN BUILDERS I | N6274215C1316 AWD | 14825000 | 13443000 | 2017-08-09 | 2018-07-25
2018-06-30 | 2014 | Marine Corps Active | M00318852 |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407000 | 19001000 | 2016-10-04 | 2018-08-17
2018-06-30 | 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274215C1305 AWD | 51071000 | 48197000 | 2018-08-11 | 2018-08-11
2017-11-30 | 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | HORIKAWA, NORINE E | N62742 15 C 1305 | 51071000 | 47746000 | 2017-09-28 | 2018-08-11
2018-06-30 | 2014 | Marine Corps Active | M00318863 |  | 2015-07-14 | 2016-09-19 | CONTRACK WATTS, INC | N6274216C1325 AWD | 50583000 | 47911000 | 2019-04-17 | 2019-04-17
2018-06-30 | 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720000 | 15624000 | 2016-12-18 | 2017-06-17
2018-06-30 | 2016 | Marine Corps Active | M00318902 |  | 2016-05-27 | 2016-11-18 | NOVA GROUP INC | N6274217C1320 AWD | 24797000 | 21630000 | 2019-06-06 | 2019-06-06
2018-06-30 | 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 47645000 | 39045000 | 2017-01-03 | 2018-03-23
2018-06-30 | 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 53999000 | 47822000 | 2017-01-03 | 2018-03-23
2018-06-30 | 2017 | Marine Corps Active | M00318923 |  | 2017-04-07 | 2017-08-21 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6274217C1307 AWD | 72494000 | 65225000 | 2020-03-08 | 2020-03-08
2017-09-30 | 2013 | Marine Corps Active | M006811132 |  | 2014-11-18 | 2016-03-24 | BETHEL-WEBCOR JV-1 | N6247316C0606 AWD | 79521000 | 75585000 | 2020-01-23 | 2020-06-13
2017-09-30 | 2013 | Marine Corps Active | M006811176 |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428000 | 4975000 | 2016-04-21 | 2018-02-24
2018-06-30 | 2014 | Marine Corps Active | M00681970 |  | 2014-07-01 | 2015-12-30 | SOLPAC CONSTRUCTION INC | N6247310D5411 0012 | 19459000 | 18946000 | 2018-04-27 | 2018-10-26
2018-06-30 | 2017 | Marine Corps Active | M60169464 |  | 2017-02-23 | 2017-06-29 | THE HASKELL COMPANY | N4008517C8327 AWD | 78310000 | 75324000 | 2020-07-13 | 2020-07-13
2017-09-30 | 2013 | Marine Corps Active | M60169465 |  | 2012-11-15 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643000 | 38956000 | 2016-09-08 | 2017-07-15
2018-06-30 | 2018 | Marine Corps Active | M62204930 |  | 2017-03-07 | 2018-04-18 | M A MORTENSON COMPANY | N6247318D5850 N6247318F4497 | 23592000 | 22054000 |  | 2020-05-02
2018-06-30 | 2016 | Marine Corps Active | M626130702 |  | 2016-06-22 | 2016-09-22 | Nippo Corporation | N4008414R0001 X099 | 6941000 | 6611000 | 2017-10-09 | 2017-09-25
2018-06-30 | 2014 | Marine Corps Active | M626131402 |  | 2016-07-13 | 2016-09-27 | NIPPO CORPORATION | N4008414D0010 0013 | 3478000 | 3312000 | 2018-03-04 | 2018-03-04
2018-06-30 | 2015 | Marine Corps Active | M62974617 |  | 2016-02-29 | 2016-05-23 | HARPER CONSTRUCTION COMPANY, INC | N6247315D2432 0004 | 16694000 | 16825000 | 2017-11-29 | 2018-08-15
2017-09-30 | 2013 | Marine Corps Active | M67001003 |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260000 | 29253000 | 2015-09-01 | 2017-03-31
2018-06-30 | 2016 | Marine Corps Active | M670011280 |  | 2016-12-16 | 2017-05-30 | CADDELL CONSTRUCTION CO. (DE), LLC | N4008517C8325 AWD | 47882000 | 35243000 | 2019-06-24 | 2019-09-03
2018-06-30 | 2014 | Marine Corps Active | M670011349 |  | 2014-02-27 | 2015-08-31 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0014 | 25742000 | 26047000 | 2017-03-21 | 2018-06-02
2018-06-30 | 2017 | Marine Corps Active | M670011428 |  | 2017-06-23 | 2017-08-25 | WHITING-TURNER CONTRACTING CO | N4008517C8317 AWD | 18579000 | 17553000 | 2019-05-08 | 2019-05-08
2018-06-30 | 2014 | Marine Corps Active | M670011445 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 2123000 | 2025000 | 2017-02-06 | 2017-08-11
2018-06-30 | 2014 | Marine Corps Active | M670011447 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 9605000 | 10497000 | 2017-02-06 | 2017-08-11
2017-09-30 | 2014 | Marine Corps Active | M670011448 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 15756000 | 14998000 | 2017-02-06 | 2017-08-11
2018-06-30 | 2014 | Marine Corps Active | M67001674 |  | 2014-02-03 | 2015-08-19 | BRISTOL GENERAL CONTRACTORS, LLC | N4008515C0320 AWD | 17032000 | 16559000 | 2017-03-11 | 2018-05-02
2018-06-30 | 2016 | Marine Corps Active | M67001686 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 3640000 | 3499000 | 2018-04-06 | 2019-03-11
2018-06-30 | 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159000 | 17298000 | 2015-12-20 | 2018-08-05
2018-06-30 | 2016 | Marine Corps Active | M67001729 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 1885000 | 2213000 | 2018-04-06 | 2019-03-11
2018-06-30 | 2014 | Marine Corps Active | M67004934 |  | 2013-12-06 | 2014-11-03 | GULF BUILDING CORP & HERNANDEZCONSULTANTS | N6945014D1274 0002 | 14685000 | 15700000 | 2016-03-17 | 2018-03-06
2018-06-30 | 2018 | Marine Corps Active | M67004971 |  | 2017-12-12 | 2018-03-15 | DRACE CONSTRUCTION CORP. | N4008516D5524 N4008518F5082 | 1982000 | 1858000 | 2018-11-06 | 2018-11-06
2018-06-30 | 2016 | Marine Corps Active | M67004972 |  | 2016-12-14 | 2017-03-22 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N6945016D1112 WE01 | 8625000 | 8264000 | 2019-01-28 | 2019-02-23
2018-06-30 | 2016 | Marine Corps Active | M67029007 |  | 2016-10-25 | 2017-04-19 | TIDEWATER, INC | N4008017C0024 AWD | 1257000 | 1160000 | 2018-04-19 | 2018-04-19
2017-11-30 | 2016 | Marine Corps Active | M673991232 |  | 2017-07-10 | 2017-09-29 | BENAKA INC. | N4008514D0030 N4008517F5514 | 2728000 | 2598000 | 2018-09-29 | 2018-09-29
2018-06-30 | 2016 | Marine Corps Active | M673991232 |  | 2017-06-27 | 2017-09-26 | PROCAL ELECTRIC INC | N6247316D1861 N6247317F4699 | 9329000 | 9073000 | 2019-04-19 | 2019-05-26
2018-06-30 | 2015 | Marine Corps Active | M67399222 |  | 2016-02-22 | 2016-08-31 | AT&T GOVERNMENT SOLUTIONS, INC | N6247316C0601 AWD | 12948000 | 13632000 | 2019-03-04 | 2019-03-04
2018-06-30 | 2015 | Marine Corps Active | M67400213 | [5 empty] | 3481000 | 3255000
2018-06-30 | 2016 | Marine Corps Active | M67400606 |  | 2016-07-20 | 2016-09-15 | NAVY STANDARD DOCUMENT | N4008516C5505 AWD | 8853000 | 8600000 | 2018-03-26 | 2018-03-26
2018-06-30 | 2015 | Marine Corps Active | M67400801 |  | 2015-08-27 | 2016-04-21 | NAVY STANDARD DOCUMENT | USACE | 29352000 | 37683000 | 2017-07-29 | 2017-07-29
2018-06-30 | 2015 | Marine Corps Active | M67400803 |  | 2015-08-21 | 2015-12-22 | NAVY STANDARD DOCUMENT | USACE | 20221000 | 21368000 | 2017-09-12 | 2017-09-12
2018-06-30 | 2016 | Marine Corps Active | M67400809 |  | 2018-01-19 | 2018-05-31 | NAVY STANDARD DOCUMENT | USACE | 24491000 | 23602560 | 2020-01-21 | 2020-01-21
2018-06-30 | 2016 | Marine Corps Active | M67604132 |  | 2016-07-08 | 2016-08-31 | REYES CONSTRUCTION INC | N6247314D0068 0008 | 2887000 | 2603000 | 2017-10-30 | 2017-12-19
2018-06-30 | 2017 | Marine Corps Active | M67865198 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 4529000 | 75967000 | 2020-01-14 | 2020-01-14
2018-06-30 | 2018 | Marine Corps Active | M67865198 | M67865198A | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 32022000 | 30502000 | 2020-01-14 | 2020-01-14
2018-06-30 | 2016 | Marine Corps Active | M67865200 |  | 2017-02-28 | 2017-05-25 | R A BURCH CONSTRUCTION CO INC | N6247317D4626 0003 | 10638000 | 10057000 | 2018-12-31 | 2019-02-02
2018-06-30 | 2017 | Marine Corps Active | M67865203 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 182000 | 36115000 | 2020-01-14 | 2020-01-14
2018-06-30 | 2017 | Marine Corps Active | M67865249 |  | 2017-09-19 | 2017-12-18 | R A BURCH CONSTRUCTION CO INC | N6247316D1884 N6247318F4138 | 30390000 | 30469000 | 2019-09-24 | 2019-09-24
2018-06-30 | 2014 | Marine Corps Active | N41557109 |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820000 | 57703000 | 2016-12-03 | 2017-10-10
2018-06-30 | 2016 | Marine Corps Active | N41557715 |  | 2016-04-06 | 2017-08-24 | BLACK CONSTRUCTION CORP. | N6274217C1319 AWD | 123661000 | 84105000 | 2020-11-26 | 2020-11-26
2018-06-30 | 2017 | Marine Corps Active | N61755102 |  | 2017-04-19 | 2017-08-31 | HENSEL PHELPS CONSTRUCTION CO. | N6274217C1300 AWD | 35769000 | 30835000 | 2020-03-18 | 2020-03-18
2018-06-30 | 2014 | Marine Corps Reserve | M67386139 |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019000 | 16659000 | 2016-06-16 | 2016-06-16
2017-11-30 | 2016 | Marine Corps Reserve | M68479129 |  | 2016-03-29 | 2017-09-26 | TOMPCO, INC | N4425517C8002 AWD | 17270000 | 16137000 | 2020-01-04 | 2020-01-04
2018-06-30 | 2016 | Marine Corps Reserve | M68479129 |  | 2017-07-10 | 2017-09-29 | BENAKA INC. | N4008514D0030 N4008517F5514 | 2728000 | 2628000 | 2018-09-29 | 2018-09-29
2018-06-30 | 2015 | Marine Corps Reserve | N00620234 |  | 2014-12-30 | 2015-07-29 | SWINERTON BUILDERS | N4425515C6001 AWD | 29746000 | 29619000 | 2016-12-15 | 2017-12-01
2018-06-30 | 2016 | Marine Corps Reserve | N62688652 |  | 2017-04-24 | 2017-07-19 | TURNER STRATEGIC TECHNOLOGIES, LLC | N4008514D8156 N4008517F4344 | 2800000 | 2657000 | 2018-10-12 | 2018-10-12
2018-06-30 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 114390000 | 2015-08-30 | 2016-11-30
2018-06-30 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 66900000 | 2015-08-30 | 2016-11-30
2018-06-30 | 2014 | Missile Defense Agency | 634 |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300000 | 15604000 | 2016-01-06 | 2016-05-02
2018-06-30 | 2013 | Missile Defense Agency | 639 |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584000 | 16235009 | 2014-11-28 | 2016-05-02
2018-06-30 | 2016 | Missile Defense Agency | 640 |  | 2015-06-10 | 2016-02-10 | AMEC PROGRAMS, INC. | W912GB-16-C-0005 | 141906057 | 169153000 | 2018-11-09 | 2021-01-15
2018-06-30 | 2014 | Missile Defense Agency | 648 |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991000 | 15673220 | 2015-01-09 | 2015-02-20
2018-06-30 | 2014 | Missile Defense Agency | 649 |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838000 | 50712661 | 2016-05-31 | 2016-05-31
2018-06-30 | 2017 | Missile Defense Agency | 653 |  | 2017-02-01 | 2017-07-25 | AMES 1/Conam JV | W911KB-17-C-0029 | 6954581 | 6954581 | 2019-08-14 | 2019-08-14
2018-04-30 | 2017 | Missile Defense Agency | 657 |  | 2017-11-14 | 2018-02-15 | STG Pacific, LLC | TBD | 24399601 | 24399601 | 2019-08-30 | 2019-08-30
2018-06-30 | 2017 | Missile Defense Agency | 657 |  | 2016-12-14 | 2017-04-28 | UNIT-ASRC Construction, LLC | W911KB-17-C-0002 | 112949720 | 114038153 | 2020-11-27 | 2020-11-27
2018-06-30 | 2017 | Missile Defense Agency | 657 |  | 2017-11-14 | 2018-02-15 | STG Pacific, LLC | W911KB-18-C-0015 | 24399601 | 24399601 | 2019-08-30 | 2019-08-30
2018-06-30 | 2016 | Missile Defense Agency | 661 |  | 2015-07-16 | 2016-02-05 | BRICE ENVIRONMENTAL SERVICES CORPORATION | FA8903-16-C-0001 | 1672076 | 1789384 | 2016-08-31 | 2016-11-10
2018-06-30 | 2017 | Missile Defense Agency | 662 |  | 2017-01-23 | 2017-09-06 | Black Construction Corporation | N62742-17-C-1305 | 12420870 | 11641479 | 2019-01-04 | 2019-01-04
2018-06-30 | 2017 | Missile Defense Agency | 673 |  | 2017-04-15 | 2017-08-03 | Indyne, Inc. | W912DY-11-D-0002 | 877752 | 877752 | 2019-06-27 | 2019-08-02
2018-06-30 | 2018 | Missile Defense Agency | 674 |  | 2018-02-05 | 2018-04-10 | CP01-Alaska Aggregate Products, LLC | W911KB18C0023 | 2600710 | 2600710 | 2018-06-30 | 2018-06-30
2018-06-30 | 2018 | Missile Defense Agency | 674 |  | 2018-01-05 | 2018-05-07 | CP02-Brice Civil Constructors | TBD | 18965310 | 18965310 | 2018-10-30 | 2018-10-30
2018-06-30 | 2018 | Missile Defense Agency | 674 |  | 2018-01-05 | 2018-06-07 | CP02TP-Construction Services SATOC | Pending | 2432439 | 2432439 | 2018-10-31 | 2018-10-31
2015-06-01 | 2008 | National Geospatial-Intelligence Agency | 65416 |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture | W912DR-07-C-0027 | 1409901000 | 1467244000 | 2011-12-22 | 2015-11-21
2018-03-31 | 2010 | National Security Agency | 17781 |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700000 | 11700000 | 2011-08-20 | 2012-05-30
2018-03-31 | 2010 | National Security Agency | 17782 |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200000 | 3200000 | 2013-07-13 | 2015-11-30
2018-03-31 | 2011 | National Security Agency | 17866 |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900000 | 131089216 | 2014-11-30 | 2015-10-31
2018-03-31 | 2010 | National Security Agency | 17872 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223000 | 129078000 | 2014-04-18 | 2015-10-12
2018-03-31 | 2010 | National Security Agency | 18052 |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566000 | 8257000 | 2013-02-01 | 2014-05-14
2018-03-31 | 2010 | National Security Agency | 18053 |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095000 | 16448000 | 2013-02-01 | 2014-05-31
2018-03-31 | 2010 | National Security Agency | 18054 |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085000 | 7316000 | 2013-02-01 | 2014-08-31
2018-03-31 | 2011 | National Security Agency | 20489 |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657000 | 8867000 | 2014-01-30 | 2015-01-16
2018-03-31 | 2011 | National Security Agency | 20489 | 2 | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620000 | 2657000 | 2014-02-28 | 2014-04-28
2018-03-31 | 2009 | National Security Agency | 21120 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060000 | 13760000 | 2013-01-17 | 2014-04-18
2018-03-31 | 2010 | National Security Agency | 21372 |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443000 | 4201000 | 2011-09-26 | 2012-06-29
2018-03-31 | 2012 | National Security Agency | 23051 |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975000 | 132008057 | 2015-05-03 | 2016-01-01
2018-03-31 | 2012 | National Security Agency | 23051 | 2 | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621000 | 5621000 | 2014-02-14 | 2015-09-30
2018-03-31 | 2011 | National Security Agency | 23994 |  | 2012-04-26 | 2012-06-18 | JAAAT | W912HN-10-D-0063 | 15315000 | 16526000 | 2014-01-30 | 2014-12-23
2018-03-31 | 2012 | National Security Agency | 24649 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589000 | 608357051 | 2015-09-15 | 2016-02-08
2018-03-31 | 2010 | National Security Agency | 25047 |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253000 | 5792000 | 2014-03-07 | 2015-05-04
2018-03-31 | 2013 | National Security Agency | 26170 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91777000 | 100657014 | 2015-10-11 | 2016-11-30
2018-03-31 | 2015 | National Security Agency | 27532 |  | 2015-06-30 | 2016-04-05 | Hensel-Phelps | W912DR-15-D-0032 | 40081050 | 40081050 | 2018-10-25 | 2018-10-25
2018-03-31 | 2016 | National Security Agency | 30583 |  | 2015-12-18 | 2016-06-17 | Clark Construction | W912DR-15-R-0024 | 616311000 | 636971000 | 2020-09-09 | 2020-09-09
2018-03-31 | 2016 | National Security Agency | 31066 |  | 2015-06-30 | 2016-04-05 | Hensel-Phelps | W912DR-15-D-0032 DO 0002 | 30538350 | 30538350 | 2018-08-08 | 2018-08-08
2018-03-31 | 2016 | National Security Agency | 31934 |  | 2015-07-08 | 2015-09-15 | Whiting-Turner | W912DR-15-C-0026 | 24554985 | 26225082 | 2016-12-31 | 2016-12-31
2018-03-31 | 2016 | National Security Agency | 32122 |  | 2016-04-01 | 2016-05-23 | Argo | WH12DR-14-D-0019 | 22375000 | 22375000 | 2018-06-08 | 2018-06-08
2018-06-30 | 2016 | Navy Active | M00264714 |  | 2016-05-02 | 2016-07-14 | CHEROKEE NATION CONSTRUCTIONSERVICES, LLC | N4008016C0162 AWD | 7003000 | 6694000 | 2017-07-29 | 2018-02-28
2018-06-30 | 2016 | Navy Active | M00318910 |  | 2015-11-24 | 2016-07-12 | ABSHER CONSTRUCTION CO | N6274216C1322 AWD | 67105000 | 61521000 | 2018-10-31 | 2018-10-31
2018-06-30 | 2016 | Navy Active | M006811220 |  | 2016-06-24 | 2016-11-30 | J. R. FILANC CONSTRUCTION COMPANY,INC | N6247317C3403 AWD | 39860000 | 35826000 | 2019-03-30 | 2019-03-30
2018-06-30 | 2016 | Navy Active | M62613604 | [5 empty] | 12010000 | 11177488
2018-06-30 | 2016 | Navy Active | M62974602 |  | 2017-03-31 | 2017-07-27 | STRAUB CONSTRUCTION, INC. | N6247316D1887 N6247317F4044 | 43119000 | 39124000 | 2019-06-30 | 2018-04-15
2018-06-30 | 2016 | Navy Active | M670011346 |  | 2016-02-26 | 2016-07-29 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008516C5500 AWD | 45118000 | 40811000 | 2018-08-13 | 2018-09-14
2018-06-30 | 2017 | Navy Active | M673991237 |  | 2017-04-10 | 2017-07-19 | COMPENDIUM INTERNATIONAL, INC. | N6247317C3410 AWD | 2994000 | 2868000 | 2018-04-30 | 2018-04-30
2018-06-30 | 2017 | Navy Active | M67400308 |  | 2017-08-15 | 2017-09-24 | TOA-OSHIRO JV | N4008414D2011 N4008417F4365 | 2081000 | 1853000 | 2018-08-10 | 2018-08-10
2017-11-30 | 2017 | Navy Active | M67400308 |  | 2016-04-08 | 2017-05-23 | NAVY STANDARD DOCUMENT | USACE | 55319000 | 55319000
2018-06-30 | 2016 | Navy Active | N00204723 |  | 2016-11-23 | 2017-06-28 | EMR, INC. | N6945017D0507 N6945017F1003 | 20056000 | 19058000 | 2019-10-16 | 2019-10-16
2018-06-30 | 2016 | Navy Active | N00207334 |  | 2015-11-06 | 2016-03-18 | HICAPS, INC. | N6945014D1275 0003 | 5881000 | 5931000 | 2017-06-11 | 2017-08-17
2017-11-30 | 2016 | Navy Active | N00207334 |  | 2015-11-06 | 2016-03-18 | HICAPS, INC. | N69450 14 D 1275 | 5881000 | 5803000 | 2017-06-11 | 2017-06-11
2018-06-30 | 2016 | Navy Active | N00207662 |  | 2016-06-17 | 2016-09-27 | WHITESELL-GREEN, INC. | N6945016C1103 AWD | 9719000 | 10180000 | 2017-11-06 | 2018-11-18
2018-06-30 | 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151000 | 14413000 | 2016-02-08 | 2018-01-08
2018-06-30 | 2017 | Navy Active | N00245312 |  | 2017-04-25 | 2017-06-29 | SYNERGY ELECTRIC COMPANY INC | N6247316D1862 N6247317F4054 | 2527000 | 2418000 | 2018-09-30 | 2018-09-30
2018-06-30 | 2016 | Navy Active | N00245499 |  | 2016-04-07 | 2016-08-29 | RQ CONSTRUCTION, LLC | N6247316D1885 0001 | 32629000 | 30812000 | 2018-08-29 | 2018-09-26
2018-06-30 | 2015 | Navy Active | N00245800 |  | 2015-06-15 | 2015-09-17 | S & R CONSTRUCTIONA JOINT VENTURE | N6247315C1604 AWD | 41838000 | 44475000 | 2017-10-01 | 2018-07-02
2018-06-30 | 2017 | Navy Active | N002461017 |  | 2017-03-22 | 2017-09-28 | WEST POINT CONTRACTORS, INC. | N6247317C0815 AWD | 2943000 | 2662000 | 2018-10-05 | 2018-10-05
2017-11-30 | 2017 | Navy Active | N002461017 |  | 2017-08-03 | 2017-09-27 | REILLY CONSTRUCTION, INC | N4008017D0012 N4008017F4480 | 2627000 | 2437000 | 2018-10-24 | 2018-10-24
2017-09-30 | 2013 | Navy Active | N00246730 |  | 2013-05-29 | 2015-07-30 | HENSEL PHELPS CONSTRUCTION CO | N6247315C1614 AWD | 72648000 | 71868000 | 2017-07-29 | 2017-09-14
2017-09-30 | 2013 | Navy Active | N00246909 |  | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088000 | 3082000 | 2015-03-15 | 2017-07-03
2018-06-30 | 2017 | Navy Active | N00246947 |  | 2017-01-30 | 2017-03-30 | REYES CONSTRUCTION INC | N6247314D0068 0009 | 11659000 | 13720000 | 2018-10-06 | 2018-12-14
2018-06-30 | 2017 | Navy Active | N00246963 |  | 2017-01-19 | 2017-03-27 | KKP ELECTRICAL CONTRACTORS, LLC | N6247316D1859 0003 | 12157000 | 11485000 | 2018-10-03 | 2018-10-03
2018-06-30 | 2017 | Navy Active | N00246991 |  | 2016-11-23 | 2017-03-30 | RQ-DPR JV | N6247317C0808 AWD | 61541000 | 60182000 | 2019-04-23 | 2019-04-23
2018-06-30 | 2016 | Navy Active | N00246998 |  | 2015-07-29 | 2016-01-19 | RQ-DPR JV | N6247315C1609 | 3443000 | 4091000 | 2018-04-02 | 2018-09-30
2018-06-30 | 2014 | Navy Active | N00620239 |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY | N4425514C5004 AWD | 29692000 | 28005000 | 2017-05-26 | 2017-08-03
2018-06-30 | 2017 | Navy Active | N00620240 |  | 2016-06-14 | 2017-08-09 | BETHEL-WEBCOR JV-1 | N4425517D4032 N4425517F4132 | 28966000 | 26486000 | 2020-03-26 | 2020-05-18
2018-06-30 | 2015 | Navy Active | N00620259 |  | 2015-02-27 | 2016-12-21 | WATTS CONTRACK A JV | N4425517C8001 AWD | 32386000 | 31598000 | 2018-06-19 | 2018-06-19
2018-06-30 | 2014 | Navy Active | N32411103 |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319000 | 14162000 | 2015-12-16 | 2016-12-07
2018-06-30 | 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 AWD | 34317000 | 39753000 | 2016-11-23 | 2018-10-21
2018-06-30 | 2015 | Navy Active | N32443527 |  | 2014-12-19 | 2015-09-03 | WHITESELL-GREEN, INC. | N4008513D7776 0007 | 11256000 | 10822000 | 2017-04-20 | 2017-07-19
2018-06-30 | 2016 | Navy Active | N32443614 |  | 2017-06-01 | 2017-12-15 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 42280000 | 41502000 | 2021-04-15 | 2021-04-15
2018-06-30 | 2017 | Navy Active | N32443614 | N32443614A | 2017-06-01 | 2017-12-15 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 2624000 | 0 | 2021-04-15 | 2021-04-15
2017-12-31 | 2017 | Navy Active | N32443614 | N32443614A |  |  |  |  | 2624000 | 529000
2018-06-30 | 2014 | Navy Active | N32446266 |  | 2013-12-30 | 2015-08-17 | METHUEN CONSTRUCTION CO., INC | N4008515C8746 AWD | 31542000 | 36418000 | 2018-01-23 | 2018-09-23
2018-06-30 | 2017 | Navy Active | N32446285 |  | 2017-01-17 | 2017-06-29 | L.S. BLACK CONSTRUCTORS-LOEFFELCONSTRUCTION | N4008517C5056 AWD | 18927000 | 18862000 | 2019-05-10 | 2019-07-07
2018-06-30 | 2014 | Navy Active | N32446308 |  | 2015-09-29 | 2016-04-21 | TRITON MARINE CONSTRUCTION CORP. | N4008516C3013 AWD | 34722000 | 33755000 | 2018-10-25 | 2018-10-25
2018-06-30 | 2017 | Navy Active | N32446371 |  | 2017-09-19 | 2018-03-30 | ENGINEERED CONSTRUCTION SERVICES,INC | N4008518C8719 AWD | 29577000 | 28703000 | 2021-09-14 | 2021-09-14
2018-06-30 | 2015 | Navy Active | N3379A064 |  | 2015-03-12 | 2015-09-11 | ZAFER TAAJJIT OMSAAT VE TOCARET A S | N62470 15 C 5006 | 1407000 | 1653000 | 2017-01-23 | 2017-01-23
2018-06-30 | 2017 | Navy Active | N3379A223 |  | 2017-10-13 | 2018-06-28 | J/V P. & C. DEVELOPMENT S.A. -ERGOTEM S.A. | N6247018C4015 AWD | 22804000 | 21718000 | 2020-10-05 | 2020-10-05
2018-06-30 | 2015 | Navy Active | N41557230 |  | 2015-04-02 | 2015-11-17 | RELYANT GLOBAL LLC | N6274216C1317 AWD | 20799000 | 15899000 | 2018-06-19 | 2018-07-03
2018-06-30 | 2015 | Navy Active | N41557240 |  | 2015-06-16 | 2015-09-29 | WATTS CONSTRUCTORS, LLC | N6274215C1303 AWD | 27345000 | 17623000 | 2018-05-02 | 2018-09-04
2018-06-30 | 2014 | Navy Active | N41557625 |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710000 | 52388000 | 2016-04-25 | 2018-09-07
2018-06-30 | 2016 | Navy Active | N41557635 |  | 2016-06-24 | 2017-08-01 | TIKIGAQ CONSTRUCTION, LLC | N4019217C1305 AWD | 8715000 | 9119000 | 2019-02-22 | 2019-04-05
2018-06-30 | 2015 | Navy Active | N42237099 |  | 2014-02-24 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 39730000 | 41398000 | 2018-06-20 | 2019-02-27
2018-06-30 | 2014 | Navy Active | N42237100 |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249000 | 131747000 | 2018-06-20 | 2019-02-27
2018-06-30 | 2017 | Navy Active | N42237671 |  | 2017-08-10 | 2018-01-16 | DESIGN BUILD INCORPORATED | N6945016D1111 | 2910000 | 2813000 | 2019-08-23 | 2019-08-23
2018-06-30 | 2015 | Navy Active | N47608155 |  | 2015-04-30 | 2015-09-29 | G-W MANAGEMENT SERVICES, LLC | N4008015C0168 AWD | 11273000 | 11538000 | 2017-08-20 | 2017-10-24
2018-06-30 | 2014 | Navy Active | N47608262 |  | 2014-08-11 | 2014-09-29 | REILLY CONSTRUCTION, INC | N4008014D3014 0001 | 1426000 | 1678000 | 2016-09-29 | 2017-06-06
2017-11-30 | 2017 | Navy Active | N47608421 |  | 2017-08-15 | 2017-09-24 | TOA-OSHIRO JV | N4008414D2011 N4008417F4365 | 2081000 | 1853000 | 2018-08-10 | 2018-08-10
2018-06-30 | 2017 | Navy Active | N47608421 |  | 2017-08-03 | 2017-09-27 | REILLY CONSTRUCTION, INC | N4008017D0012 N4008017F4480 | 2627000 | 2446000 | 2018-10-24 | 2018-10-24
2018-05-30 | 2016 | Navy Active | N47608975 |  | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N4008018C0311 AWD | 38795000 | 36407000 |  | 2020-02-02
2018-06-30 | 2016 | Navy Active | N500921602 |  | 2016-12-20 | 2018-05-17 | DELMARVA VETERAN BUILDERS, LLC | N4008518C6720 AWD | 4992000 | 4755000 | 2019-10-04 | 2019-10-04
2018-06-30 | 2018 | Navy Active | N50092176 |  | 2017-09-14 | 2018-04-19 | CIVIL WORKS CONTRACTING LLC | N4008517D0358 N4008518F5423 | 2670000 | 2500000 |  | 2019-07-08
2018-06-30 | 2015 | Navy Active | N50092354 |  | 2015-07-31 | 2015-09-28 | HOURIGAN-SUNDT, A JOINT VENTURE | N4008515C0011 AWD | 40638000 | 39377000 | 2018-10-07 | 2019-01-17
2018-06-30 | 2016 | Navy Active | N50092726 |  | 2016-06-30 | 2016-09-29 | GP ABSHER ONE, LLC | N4008515D0094 0003 | 2351000 | 2801000 | 2018-04-07 | 2018-05-23
2018-06-30 | 2016 | Navy Active | N50092H238 |  | 2016-12-20 | 2018-05-17 | DELMARVA VETERAN BUILDERS, LLC | N4008518C6720 AWD | 291900 | 278000 | 2019-10-04 | 2019-10-04
2018-06-30 | 2016 | Navy Active | N60191603 |  | 2016-02-18 | 2016-06-15 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008516C6119 AWD | 22770000 | 22611000 | 2017-06-30 | 2018-03-23
2018-06-30 | 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446000 | 14222000 | 2016-10-25 | 2018-02-20
2018-06-30 | 2017 | Navy Active | N60201154 |  | 2017-02-23 | 2017-06-29 | HENSEL PHELPS CONSTRUCTION CO | N6945014D1269 N6945017F0700 | 40518000 | 38996000 | 2019-09-26 | 2019-09-26
2018-06-30 | 2015 | Navy Active | N60201423 |  | 2015-08-28 | 2016-11-15 | SAUER, INC. | N6945017C0902 AWD | 27912000 | 27581000 | 2018-04-09 | 2018-04-09
2018-06-30 | 2016 | Navy Active | N60201424 |  | 2016-01-26 | 2016-07-14 | ARTEC GROUP (THE) INC | N6945016D1110 0001 | 14616000 | 14181000 | 2018-02-05 | 2018-04-29
2018-06-30 | 2017 | Navy Active | N60241295 |  | 2017-04-20 | 2017-05-19 | SOLID STRUCTURES INC | N6945017C6810 AWD | 2786000 | 2621000 | 2018-11-17 | 2018-11-17
2018-01-31 | 2017 | Navy Active | N60241295 | [5 empty] | 2786000 | 2621000
2018-06-30 | 2016 | Navy Active | N60495111 |  | 2016-05-31 | 2017-08-17 | BRISTOL GENERAL CONTRACTORS, LLC | N6247315D2404 N6247317F4334 | 11253000 | 9795000 | 2019-02-25 | 2019-07-17
2018-06-30 | 2017 | Navy Active | N60495111 | N60495111A | 2016-05-31 | 2017-08-17 | BRISTOL GENERAL CONTRACTORS, LLC | N6247315D2404 N6247317F4334 | 4751000 | 4525000 | 2019-02-25 | 2019-02-25
2018-06-30 | 2014 | Navy Active | N60495393 |  | 2017-02-28 | 2018-04-19 | WALTERS, K. G. CONSTRUCTION CO., IN | N6247318C2205 AWD | 15675000 | 14657000 |  | 2020-05-08
2018-06-30 | 2015 | Navy Active | N60495420 |  | 2015-07-17 | 2015-09-16 | STRAUB CONSTRUCTION, INC. | N6247315D2427 0002 | 25541000 | 26926000 | 2017-11-24 | 2019-03-08
2018-06-30 | 2015 | Navy Active | N60495430 |  | 2015-10-08 | 2016-09-29 | VANDER WERFF, PETER CONSTRUCTION | N6247314D0039 0012 | 7713000 | 7662000 | 2017-11-23 | 2018-08-22
2018-06-30 | 2016 | Navy Active | N60508274 |  | 2016-01-15 | 2016-06-20 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0008 | 11628000 | 11537000 | 2018-03-24 | 2018-11-30
2018-06-30 | 2017 | Navy Active | N60508926 |  | 2017-02-15 | 2017-04-21 | NAVY STANDARD DOCUMENT | USACE | 20047000 | 18602021 | 2019-06-24 | 2019-06-24
2018-06-30 | 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458000 | 9458000 | 2017-01-17 | 2017-01-17
2018-06-30 | 2016 | Navy Active | N61054023 |  | 2016-08-03 | 2016-12-19 | NAVY STANDARD DOCUMENT | USACE | 14479000 | 14438680 | 2018-09-30 | 2018-09-30
2018-06-30 | 2016 | Navy Active | N61054027 |  | 2016-11-28 | 2017-05-25 | GILBANE FEDERAL | N6274217C1309 AWD | 1637000 | 1559031 | 2017-11-21 | 2017-11-21
2018-06-30 | 2017 | Navy Active | N61056526 |  | 2017-10-13 | 2018-01-10 | ONAKA GUMI CO., LTD. | N4008416D0008 N4008418F4087 | 4577000 | 2167000 | 2019-02-11 | 2019-02-11
2018-06-30 | 2017 | Navy Active | N61058325 |  | 2017-02-16 | 2017-05-26 | NAVY STANDARD DOCUMENT | USACE | 14878000 | 13951838 | 2019-08-14 | 2019-08-14
2018-06-30 | 2014 | Navy Active | N61065202 |  | 2014-12-11 | 2016-08-29 | VANDER WERFF, PETER CONSTRUCTION | N6247314D0039 0011 | 15972000 | 14421000 | 2018-06-10 | 2018-06-10
2018-06-30 | 2017 | Navy Active | N61065223 |  | 2017-02-17 | 2017-04-27 | REYES CONSTRUCTION INC | N6247314D0068 0010 | 20504000 | 19616000 | 2019-10-29 | 2019-10-29
2018-06-30 | 2015 | Navy Active | N61151190 |  | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 15316000 | 14643000 | 2019-09-06 | 2021-02-11
2018-06-30 | 2017 | Navy Active | N61151190 | N61151190A | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 6546000 | 4399000 | 2020-01-13 | 2020-01-13
2018-06-30 | 2015 | Navy Active | N61151287 |  | 2015-03-04 | 2015-09-02 | M A MORTENSON COMPANY | N4008015C0167 AWD | 25679000 | 27694000 | 2017-07-17 | 2018-08-20
2018-06-30 | 2014 | Navy Active | N61152001 |  | 2014-01-10 | 2015-04-13 | NAVY STANDARD DOCUMENT | N6247015MPC0032 | 109808000 | 106627000 | 2017-05-05 | 2017-05-05
2018-06-30 | 2015 | Navy Active | N61152621 |  | 2015-07-15 | 2016-03-31 | TURNER CONSTRUCTION COMPANY | N4008016C0156 AWD | 120181000 | 117989000 | 2019-09-08 | 2019-09-09
2018-06-30 | 2014 | Navy Active | N617551403 |  | 2013-11-14 | 2015-04-30 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 0002 | 24771000 | 26021000 | 2017-08-13 | 2018-02-28
2018-06-30 | 2014 | Navy Active | N61755425 |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865000 | 54901000 | 2016-06-11 | 2017-08-28
2017-11-30 | 2016 | Navy Active | N61755535 |  | 2016-11-10 | 2017-08-21 | Contrack Watts, Inc. | N6274217C1325 *AWD | 47314000 | 44237000 | 2020-01-03 | 2020-01-03
2018-06-30 | 2016 | Navy Active | N61755535 |  | 2016-11-10 | 2017-08-21 | CONTRACK WATTS, INC | N6274217C1325 AWD | 47314000 | 44260000 | 2020-01-03 | 2020-01-03
2018-06-30 | 2017 | Navy Active | N61755652 |  | 2017-06-12 | 2018-05-23 | APTIM FEDERAL SERVICES, LLC | N6274218C1318 AWD | 28975000 | 26230000 | 2020-04-03 | 2020-04-03
2018-06-30 | 2016 | Navy Active | N61755656 |  | 2016-08-02 | 2016-09-15 | AIC INTERNATIONAL, INC. | N4019216D2700 0005 | 1656000 | 1696000 | 2017-07-13 | 2018-03-03
2018-06-30 | 2016 | Navy Active | N62592401 |  | 2015-11-09 | 2016-05-06 | NAVY STANDARD DOCUMENT | USACE | 41851000 | 53025000 | 2017-11-09 | 2019-11-05
2018-06-30 | 2014 | Navy Active | N62688500 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365000 | 2444000 | 2016-01-01 | 2018-06-11
2018-06-30 | 2016 | Navy Active | N62688518 |  | 2015-11-23 | 2016-03-03 | SYNCON, LLC | N4008514D8152 0007 | 4575000 | 5258000 | 2017-09-29 | 2018-06-20
2018-06-30 | 2016 | Navy Active | N62688610 |  | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N4008517C0307 AWD | 34675000 | 32785000 | 2019-10-25 | 2019-10-25
2018-06-30 | 2016 | Navy Active | N62688913 |  | 2017-03-23 | 2018-04-23 | WHITING-TURNER CONTRACTING CO | N4008518C1134 AWD | 114000000 | 109083000 |  | 2020-11-01
2018-06-30 | 2016 | Navy Active | N62813036 |  | 2015-10-28 | 2016-01-26 | BETHEL-WEBCOR JV-1 | N6247814D4001 KB01 | 8520000 | 7905000 | 2018-03-26 | 2018-04-29
2018-06-30 | 2015 | Navy Active | N62813048 |  | 2014-10-20 | 2015-02-27 | JSR ECC, LLC | N6247814D4003 KB01 | 8667000 | 10188000 | 2016-10-04 | 2017-02-10
2018-06-30 | 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810000 | 2676000 | 2016-05-18 | 2016-05-18
2018-06-30 | 2014 | Navy Active | N62813270 |  | 2013-12-05 | 2014-03-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355000 | 7812000 | 2015-12-08 | 2018-07-31
2018-06-30 | 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970000 | 32762000 | 2017-08-03 | 2018-06-17
2018-06-30 | 2017 | Navy Active | N62863621 |  | 2017-03-07 | 2017-08-31 | CONSTRUCCIONES FELIPE CASTELLANOCOBRA INSTALACIONES Y SERVICIOS | N6247017C5006 AWD | 21868000 | 19888000 | 2023-02-13 | 2023-02-13
2018-06-30 | 2015 | Navy Active | N62863712 |  | 2015-04-11 | 2015-11-20 | COBRA INSTALCIONES Y SERVICIOS SA | N6247016C6001 AWD | 19252000 | 18224000 | 2018-05-23 | 2018-05-23
2018-06-30 | 2016 | Navy Active | N62995407 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 23632000 | 20175000 | 2019-04-23 | 2019-07-10
2018-06-30 | 2016 | Navy Active | N62995655 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 42852000 | 27420000 | 2019-04-23 | 2019-07-10
2018-06-30 | 2017 | Navy Active | N62995737 |  | 2016-09-09 | 2017-02-28 | ENVIRONMENTAL CHEMICAL CORPORATION | N3319116D1010 JN01 | 6096000 | 5771000 | 2018-08-22 | 2018-08-22
2018-06-30 | 2015 | Navy Active | N63005955 |  | 2015-04-15 | 2015-09-16 | KOOHEJI CONTRACTORS | N3319113D0832 *New TO | 21897000 | 22704000 | 2018-11-09 | 2018-11-09
2017-09-30 | 2013 | Navy Active | N63005960 |  | 2016-12-01 | 2017-06-29 | NAVY STANDARD DOCUMENT | USACE | 21128000 | 21128000 | 2019-12-23 | 2019-12-23
2018-06-30 | 2016 | Navy Active | N63005970 |  | 2016-03-07 | 2016-06-10 | NAVY STANDARD DOCUMENT | USACE | 39277000 | 39163000 | 2018-11-06 | 2018-11-06
2018-06-30 | 2016 | Navy Active | N63005976 | [5 empty] | 55319000 | 55319000
2018-06-30 | 2016 | Navy Active | N63042218 |  | 2015-12-10 | 2016-05-10 | A&D GC INC | N6247315D2403 0003 | 7386000 | 6951000 | 2017-11-16 | 2017-11-16
2018-06-30 | 2015 | Navy Active | N63042327 |  | 2015-03-02 | 2015-06-26 | SOLPAC CONSTRUCTION INC | N6247310D5411 0007 | 22497000 | 24363000 | 2016-10-17 | 2018-03-02
2018-06-30 | 2015 | Navy Active | N63042328 |  | 2015-02-24 | 2015-06-11 | SOLPAC CONSTRUCTION INC | N6247310D5411 0006 | 17016000 | 17958000 | 2016-11-03 | 2018-04-20
2018-06-30 | 2015 | Navy Active | N63042377 |  | 2015-10-27 | 2016-02-26 | NORTH STAR CONSTRUCTION & ENGINEERING, INC | N6247309D1643 X087 | 2561000 | 2591000 | 2016-05-26 | 2020-05-21
2018-06-30 | 2016 | Navy Active | N63042378 |  | 2016-02-12 | 2016-05-31 | STRAUB CONSTRUCTION, INC. | N6247316C4602 AWD | 52939000 | 56876000 | 2017-12-07 | 2018-06-16
2018-06-30 | 2016 | Navy Active | N63042379 |  | 2016-01-28 | 2016-03-17 | A&D GC INC | N6247315D2403 0002 | 7489000 | 7507000 | 2017-03-31 | 2017-03-31
2018-06-30 | 2017 | Navy Active | N63042380 |  | 2017-02-14 | 2017-03-31 | SOLPAC CONSTRUCTION INC | N6247315D2426 0005 | 18226000 | 18039000 | 2018-06-24 | 2018-08-25
2017-09-30 | 2013 | Navy Active | N66691908 |  | 2016-03-17 | 2016-08-11 | TSONTOS MICHAEL M. S.A. | N6247016C6008 AWD | 1383000 | 1229000 | 2017-11-24 | 2018-04-04
2017-11-30 | 2016 | Navy Active | N68436401 |  | 2017-03-22 | 2017-09-28 | WEST POINT CONTRACTORS, INC. | N6247317C0815 AWD | 2943000 | 2748000 | 2018-10-05 | 2018-10-05
2018-06-30 | 2016 | Navy Active | N68436401 |  | 2016-03-29 | 2017-09-26 | TOMPCO, INC | N4425517C8002 AWD | 17270000 | 16148000 | 2020-01-04 | 2020-01-04
2018-06-30 | 2014 | Navy Active | N68436420 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179000 | 11599000 | 2016-02-16 | 2016-11-16
2018-06-30 | 2015 | Navy Active | N68436422 |  | 2014-12-01 | 2015-05-04 | TRITON MARINE CONSTRUCTION CORP. | N4425514D9007 0003 | 12592000 | 11479000 | 2016-10-25 | 2016-10-25
2018-06-30 | 2016 | Navy Active | N68436431 |  | 2016-03-31 | 2016-08-11 | NOVA GROUP INC | N4425516C7002 AWD | 19943000 | 19212000 | 2017-11-14 | 2017-11-14
2018-06-30 | 2017 | Navy Active | N68436438 |  | 2017-01-20 | 2018-04-23 | VET INDUSTRIAL INC | N4425517D4007 N4425518F4134 | 10040000 | 9563000 |  | 2019-10-30
2018-06-30 | 2017 | Navy Active | N68436876 |  | 2017-08-09 | 2017-11-30 | DOYON PROJECT SERVICES, LLC | N4425517D4036 N4425518F4016 | 17584000 | 16746000 | 2019-03-25 | 2019-03-25
2018-06-30 | 2016 | Navy Active | N68436983 |  | 2016-04-15 | 2016-09-21 | NOVA GROUP INC | N4425516C7005 AWD | 31744000 | 28192000 | 2018-02-13 | 2019-03-27
2017-09-30 | 2013 | Navy Active | N68436990 | N68436990A | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 266304000 | 265129000 | 2016-01-09 | 2017-09-30
2018-06-30 | 2014 | Navy Active | N68436990 | N68436990B | 2011-12-13 | 2013-12-02 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00002 | 24880000 | 16665000 | 2016-01-09 | 2017-09-30
2018-06-30 | 2015 | Navy Active | N68436990 | N68436990C | 2010-07-07 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00004 | 80735000 | 80751000 | 2016-01-09 | 2017-09-30
2018-06-30 | 2015 | Navy Active | N68436993 |  | 2015-09-30 | 2016-08-30 | WATTS-ORION JV | N4425516C7004 AWD | 32047000 | 30312000 | 2018-02-06 | 2018-07-31
2018-06-30 | 2015 | Navy Active | N68469275 |  | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 30696000 | 29425000 | 2019-11-15 | 2019-11-15
2018-06-30 | 2018 | Navy Active | N68469275 | N68469275A | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 39776000 | 37882000 | 2019-11-15 | 2019-11-15
2018-01-31 | 2018 | Navy Active | N68469275 | N68469275A |  |  |  |  | 39776000 | 37882000
2018-06-30 | 2014 | Navy Active | N69212461 |  | 2015-07-24 | 2015-09-29 | VIRTEXCO CORPORATION | N4008515C0043 AWD | 14051000 | 14952000 | 2017-02-25 | 2018-04-16
2018-06-30 | 2015 | Navy Active | N69212991 |  | 2015-08-05 | 2016-03-08 | PURCELL CONSTRUCTION CORP. | N4008516C6145 AWD | 20817000 | 19954000 | 2018-03-23 | 2018-04-21
2018-06-30 | 2015 | Navy Active | N69212992 |  | 2015-03-13 | 2015-09-29 | OCEAN CONSTRUCTION SERVICES | N4008515D0095 AWD | 5272000 | 7040000 | 2016-09-28 | 2018-09-28
2018-06-30 | 2014 | Navy Active | N69232593 |  | 2014-04-30 | 2015-01-16 | I E PACIFIC INC | N6247309D1657 0019 | 18400000 | 19412000 | 2016-09-17 | 2017-10-12
2018-06-30 | 2016 | Navy Active | N69232607 |  | 2016-03-24 | 2016-08-25 | I E PACIFIC INC | N6247311D0066 0008 | 3892000 | 3563000 | 2017-11-08 | 2018-03-10
2018-06-30 | 2015 | Navy Reserve | N00129664 |  | 2015-08-24 | 2015-08-25 | VETERANS CONSTRUCTION, LLC | N4008515C9610 AWD | 1989000 | 1941000 | 2016-09-08 | 2017-04-21
2018-06-30 | 2017 | Navy Reserve | N00206500 |  | 2016-11-04 | 2017-06-29 | SAUER, INC. | N6945017C1613 AWD | 11589000 | 11076000 | 2019-07-27 | 2019-08-06
2018-06-30 | 2016 | Navy Reserve | N00206509 |  | 2016-08-01 | 2016-09-30 | AMES 1 , LLC | N6945016C6534 | 1375000 | 1371000 | 2017-09-29 | 2017-09-30
2017-09-30 | 2015 | Navy Reserve | N00207278 |  | 2015-07-30 | 2015-09-30 | SWEAT LLC | N6945015C1113 AWD | 1699000 | 1796000 | 2016-10-14 | 2017-07-21
2018-07-13 | 2015 | Special Operations Command | 36977 |  | 2015-04-15 | 2015-08-20 | Walsh Group Ventures | W912QR-15-C-0021 / 43320000 | 14851238 | 15390945 | 2017-03-03 | 2017-10-18
2018-05-01 | 2016 | Special Operations Command | 47942 |  | 2015-12-22 | 2016-06-24 | Medvolt LLC | W9128F-16-C-0033 | 9065868 | 9065868 | 2017-03-01 | 2017-03-01
2018-07-13 | 2016 | Special Operations Command | 47942 |  | 2015-12-22 | 2016-06-24 | Medvolt LLC | W9128F-16-C-0033 / 38804715 | 9065868 | 9065868 | 2018-06-04 | 2018-08-03
2018-05-01 | 2013 | Special Operations Command | 53542 |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546920 | 6654000 | 2016-02-07 | 2016-05-20
2018-07-13 | 2015 | Special Operations Command | 57442 |  | 2016-03-23 | 2017-03-17 | Brantley Construction Services, LLC | W912HN-17-C-0006 | 8456354 | 8501845 | 2018-10-19 | 2018-11-02
2018-05-01 | 2014 | Special Operations Command | 61064 |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951000 | 14335000 | 2016-05-10 | 2017-02-17
2018-07-13 | 2017 | Special Operations Command | 61065 |  | 2017-03-24 | 2017-07-21 | R. C. Construction Co., Inc. | W912HN17C0008 / 46909583 | 4609000 | 4609000 | 2018-12-01 | 2019-03-01
2018-05-01 | 2017 | Special Operations Command | 61065 |  | 2017-03-24 | 2017-07-21 | R.C Construction Co, Inc | W912HN17C0008 | 4609000 | 4609000 | 2018-11-24 | 2018-11-24
2018-07-13 | 2014 | Special Operations Command | 68526 |  | 2014-03-26 | 2015-04-09 | Barlovento, LLC | W91278-10-D-0058-DQ01 | 10815034 | 12431294 | 2016-11-17 | 2017-04-17
2018-07-13 | 2013 | Special Operations Command | 69257 |  | 2014-03-11 | 2015-04-01 | Pease Construction, Inc. | W912DW-15-C-0003 | 4484160 | 4895000 | 2016-09-15 | 2017-01-22
2018-07-13 | 2013 | Special Operations Command | 69287a |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907435 | 31157000 | 2015-05-13 | 2016-06-15
2018-07-13 | 2013 | Special Operations Command | 69287b |  | 2014-05-14 | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404000 | 25361000 | 2016-11-01 | 2017-05-14
2018-07-13 | 2015 | Special Operations Command | 69302 |  | 2015-11-12 | 2017-04-03 | Sauer Incorporated | W91278-12-D-0039 | 36061000 | 36061000 | 2019-05-07 | 2019-05-07
2018-05-01 | 2013 | Special Operations Command | 69382 |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816000 | 26046000 | 2015-08-14 | 2015-11-04
2018-07-13 | 2013 | Special Operations Command | 69445 |  | 2013-02-01 | 2015-05-07 | RQ Construction LLC | W912DW-15-C-0006 | 45104149 | 49361228 | 2017-05-25 | 2017-11-19
2018-05-01 | 2014 | Special Operations Command | 69446 |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083965 | 15665000 | 2016-02-08 | 2016-06-15
2018-05-01 | 2013 | Special Operations Command | 69447 |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123180 | 22826000 | 2016-02-13 | 2016-04-29
2018-05-01 | 2012 | Special Operations Command | 69458 |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772305 | 16854000 | 2014-06-03 | 2016-02-15
2018-07-13 | 2013 | Special Operations Command | 69493 |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085000 | 23066000 | 2016-07-18 | 2016-12-12
2018-07-13 | 2012 | Special Operations Command | 69758 |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 16429000 | 16005000 | 2014-05-08 | 2016-12-06
2018-05-01 | 2012 | Special Operations Command | 69758 |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 | 15649974 | 16004823 | 2014-05-08 | 2016-12-06
2018-05-01 | 2012 | Special Operations Command | 71224 |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525847 | 18831000 | 2014-05-01 | 2015-04-27
2018-07-13 | 2012 | Special Operations Command | 76364 |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201303 | 33465000 | 2014-08-26 | 2016-04-01
2018-07-13 | 2014 | Special Operations Command | 76365 |  | 2015-07-15 | 2015-11-12 | B.L. Harbert International, LLC | W912QR-16-C-0002/38708732 | 22740000 | 23804325 | 2017-10-02 | 2017-11-30
2018-05-01 | 2012 | Special Operations Command | 76366 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673727 | 15674302 | 2015-09-12 | 2016-04-26
2018-07-13 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-10 | Raass Brothers, Inc | W9128F-14-C-0018/43307123 | 8983000 | 9568000 | 2017-03-01 | 2017-06-15
2018-07-13 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441000 | 37500000 | 2016-07-20 | 2016-12-30
2018-05-01 | 2012 | Special Operations Command | 76371 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092801 | 17224000 | 2015-09-12 | 2016-01-27
2018-07-13 | 2014 | Special Operations Command | 76375 |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358000 | 29712704 | 2016-07-23 | 2017-08-07
2018-07-13 | 2014 | Special Operations Command | 76376 |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696668 | 53678000 | 2017-06-27 | 2018-01-15
2018-07-13 | 2016 | Special Operations Command | 76513 |  | 2016-05-25 | 2017-08-02 | Caddell Construction CO. | W912PM17C0004 | 42661500 | 42661500 | 2019-12-18 | 2019-12-18
2018-07-13 | 2017 | Special Operations Command | 76514 |  | 2017-03-02 | 2018-04-05 | SOF Special Tactics Facility, Phase 3 | W912PM18C0011 / 46145884 | 34937000 | 34937000 | 2020-03-18 | 2020-08-15
2018-07-13 | 2016 | Special Operations Command | 76518 |  | 2015-11-23 | 2016-03-17 | Bristol Environmental Remediation Servic | W912DY-12-D-0053 | 8465006 | 9104000 | 2017-05-17 | 2018-02-09
2018-07-13 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | Nishimatsu Construction Co., Ltd. | W912HV-15-004 / 35808936 | 54777000 | 54821000 | 2017-12-12 | 2018-04-05
2018-07-13 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | Nishimatsu Construction Co., Ltd. | W912HV-15-C-0004 / 35808936 | 46555863 | 61629962 | 2017-12-12 | 2017-12-12
2018-07-13 | 2015 | Special Operations Command | 79437 |  | 2016-06-27 | 2016-09-28 | SAUER Incorporated, d/b/a Sauer Southeast | W91278-12-D-0039 / 43665546 | 38659000 | 38659000 | 2019-02-11 | 2019-02-11
2018-07-13 | 2014 | Special Operations Command | 79438 |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193631 | 7896819 | 2016-04-19 | 2016-10-26
2018-07-13 | 2014 | Special Operations Command | 79440 |  | 2014-12-15 | 2015-04-30 | ARGO SYSTEMS, LLC | N6945014D1271 0003 | 4140000 | 4171000 | 2016-08-22 | 2018-08-31
2018-05-01 | 2015 | Special Operations Command | 79456 |  | 2015-05-21 | 2015-08-31 | Lifecycle Construction Services, LLC | W912HN-13-D-0002-DQ01 | 5798000 | 5817000 | 2016-11-11 | 2017-02-13
2018-07-13 | 2016 | Special Operations Command | 80773 |  | 2016-07-27 | 2016-11-21 | ACC Construction Co., Inc. | W912PM-17-C-0001 / 46240484 | 32661077 | 32673914 | 2019-01-31 | 2019-01-30
2018-07-13 | 2016 | Special Operations Command | 81897 |  | 2015-12-18 | 2016-11-18 | BUTT CONSTRUCTION COMPANY, INC | W912QR-17-C-0002 / 46150444 | 11975000 | 12016878 | 2018-08-26 | 2018-08-26
2018-07-13 | 2017 | Special Operations Command | AFSOC103022 |  | 2018-01-16 | 2018-02-16 | MIRAIT.T-ACTY JV | W912HV15D0032 / 45884453 | 3470750 | 3470750 | 2019-02-04 | 2019-03-06
2018-05-01 | 2011 | Special Operations Command | CZQZ063052A |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13829000 | 13829042 | 2013-07-17 | 2014-06-03
2018-07-13 | 2016 | Special Operations Command | CZQZ083021 |  | 2016-06-16 | 2017-02-08 | SHEFFIELD KORTE JOINT VENTURE | W912PP-14-D-0025 | 11900000 | 11900000 | 2018-11-13 | 2018-11-18
2018-07-13 | 2016 | Special Operations Command | FTEV073010 |  | 2016-03-19 | 2016-08-02 | Cutter Enterprises, LLC | W91278-16-C-0021 / 53891665 | 14173000 | 14173000 | 2018-09-15 | 2019-01-05
2018-05-01 | 2014 | Special Operations Command | FTEV083002 |  | 2014-05-01 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048867 | 7230868 | 2016-05-24 | 2016-10-20
2018-05-01 | 2014 | Special Operations Command | FTEV083002 |  | 2014-05-01 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 48908883 | 1573300 | 1603464 | 2016-05-24 | 2016-10-20
2018-05-01 | 2013 | Special Operations Command | FTFA113004 |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942300 | 30416000 | 2016-12-25 | 2017-04-06
2018-05-01 | 2013 | Special Operations Command | NVZR083702 |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753024 | 27764000 | 2015-06-28 | 2016-09-30
2018-07-13 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co. | W91278-12-D-0038 / 54346656 | 13223000 | 13223000 | 2019-01-26 | 2019-03-17
2018-07-13 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co. | W91278-12-D-0038 / 44336728 | 20933000 | 20933000 | 2019-01-26 | 2019-04-26
2018-02-15 | 2015 | Special Operations Command | P-1119 |  | 2015-08-14 | 2015-09-29 | Cox Construction Company | N62473-15-D-2405-0003 | 11080000 | 11080000 | 2017-04-06 | 2017-04-06
2018-02-15 | 2015 | Special Operations Command | P-1119 |  | 2015-08-05 | 2015-09-29 | COX CONSTRUCTION CO | N6247315D2405 0003 | 12428000 | 11906000 | 2016-04-06 | 2017-04-06
2018-07-13 | 2016 | Special Operations Command | P-1126 |  | 2016-05-10 | 2016-08-08 | A&D GC INC | N6247315D2403 0005 | 10911000 | 10787000 | 2018-02-14 | 2018-03-20
2018-07-13 | 2013 | Special Operations Command | P-1218 |  | 2013-06-11 | 2013-09-19 | RQ-DPR JV | N4008513C6000 AWD | 47295000 | 50165000 | 2016-01-18 | 2018-01-31
2018-02-15 | 2013 | Special Operations Command | P-1218 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370000 | 48044000 | 2016-03-01 | 2016-05-31
2018-07-13 | 2016 | Special Operations Command | P-1219 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 63726000 | 60825000 | 2020-01-12 | 2020-01-12
2018-07-13 | 2016 | Special Operations Command | P-1288 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 14521000 | 13934000 | 2020-01-12 | 2020-01-12
2018-07-13 | 2013 | Special Operations Command | P-1393 |  | 2013-06-11 | 2013-09-19 | RQ-DPR Construction Joint Venture | N4008513C6000 AWD | 4903000 | 4796000 | 2016-01-18 | 2018-01-31
2018-02-15 | 2013 | Special Operations Command | P-1393 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370000 | 48044000 | 2016-01-18 | 2016-05-31
2018-07-13 | 2015 | Special Operations Command | P-1396 |  | 2015-05-29 | 2015-08-17 | The Whiting-Turner Contracting Co | N40085-10-D-5330-0012 | 10331000 | 12493000 | 2017-03-09 | 2017-10-27
2018-07-13 | 2013 | Special Operations Command | P-1410 |  | 2013-09-04 | 2013-09-26 | Quadrant Construction | N4008510D0261 | 1826000 | 1809000 | 2014-09-22 | 2015-06-30
2018-02-15 | 2014 | Special Operations Command | P-157 |  | 2014-10-24 | 2016-02-26 | DPR Hardin Construction-WGI JV | N40085-10-D-5333 #0008 | 17300000 | 17300000 | 2017-09-03 | 2017-09-03
2018-07-13 | 2014 | Special Operations Command | P-157 |  | 2014-11-13 | 2016-02-26 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0008 | 19230000 | 18960000 | 2017-09-03 | 2018-06-12
2018-07-13 | 2015 | Special Operations Command | P-166 |  | 2015-05-05 | 2015-09-21 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0011 | 13588000 | 12798000 | 2017-07-17 | 2017-11-30
2018-07-13 | 2015 | Special Operations Command | P-170 |  | 2015-03-10 | 2016-01-26 | PENTACON, LLC | N6945014D0757 0002 | 10593000 | 10448000 | 2017-10-17 | 2018-05-21
2018-07-13 | 2015 | Special Operations Command | P-183 |  | 2014-04-17 | 2015-08-12 | CLARK NEXSEN - CH2M HILL - NORFOLK | N6247011D1010 WE11 | 15050000 | 16091000 | 2017-07-24 | 2017-07-24
2018-07-13 | 2014 | Special Operations Command | P-334 |  | 2015-07-21 | 2016-02-10 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0007 | 29668000 | 29436000 | 2018-07-29 | 2018-09-26
2018-02-15 | 2014 | Special Operations Command | P-334 |  | 2015-07-21 | 2016-02-10 | DPR Hardin Construction-WGI JV | N40085-10_D-5333 | 26731230 | 26731230 | 2018-07-01 | 2018-07-01
2018-07-13 | 2015 | Special Operations Command | P-418 |  | 2015-06-12 | 2015-08-18 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0006 | 20585000 | 21211000 | 2017-02-23 | 2018-02-12
2018-07-13 | 2013 | Special Operations Command | P-475 |  | 2014-07-31 | 2016-01-25 | BETHEL-WEBCOR JV-1 | N6247814D4001 0006 | 22462000 | 21669000 | 2018-02-13 | 2018-06-09
2018-07-13 | 2013 | Special Operations Command | P-576 |  | 2016-03-17 | 2016-07-15 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N4008515D0096 0003 | 2519000 | 2515000 | 2016-08-14 | 2018-01-03
2018-07-13 | 2015 | Special Operations Command | P-776 |  | 2015-08-26 | 2015-09-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247315D2426 0002 | 30528000 | 35854000 | 2017-10-23 | 2019-03-07
2018-07-13 | 2013 | Special Operations Command | P-876 |  | 2014-05-05 | 2014-09-26 | RQ CONSTRUCTION, LLC | N6247310D5409 0015 | 27636000 | 27577000 | 2016-10-07 | 2017-08-11
2018-02-15 | 2013 | Special Operations Command | P-876 |  | 2014-05-05 | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290000 | 24440000 | 2016-10-01 | 2016-10-07
2018-07-13 | 2013 | Special Operations Command | P-888 |  | 2014-04-01 | 2014-09-30 | KOO CONSTRUCTION INC | N6247309D1655 0005 | 14869000 | 13739000 | 2016-09-29 | 2017-11-08
2018-02-15 | 2013 | Special Operations Command | P-888 |  | 2014-04-01 | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489000 | 15440000 | 2016-09-30 | 2016-09-29
2018-07-13 | 2017 | Special Operations Command | P-889 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N6247314D0061 | 36321000 | 33725000 | 2020-03-31 | 2020-03-31
2018-07-13 | 2017 | Special Operations Command | P-890 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N6247317C0830 | 32902000 | 33165000 | 2020-03-31 | 2020-03-31
2018-07-13 | 2015 | Special Operations Command | P-893 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N6247315C1609 AWD | 24873000 | 23704000 | 2018-04-02 | 2018-07-16
2018-02-15 | 2013 | Special Operations Command | P-915 |  | 2015-02-12 | 2015-09-10 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0011 | 10605000 | 10039000 | 2017-03-18 | 2017-03-18
2018-07-13 | 2017 | Special Operations Command | P-919 |  | 2016-09-20 | 2017-03-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 18210000 | 16966000 | 2018-10-22 | 2018-10-22
2018-07-13 | 2016 | Special Operations Command | P-920 |  | 2016-05-12 | 2016-09-20 | RQ CONSTRUCTION, LLC | N6247315D2428 0003 | 47022000 | 44874000 | 2018-10-13 | 2018-12-04
2018-07-13 | 2017 | Special Operations Command | P-952 |  | 2017-04-28 | 2017-08-10 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 16668000 | 16432000 | 2019-11-22 | 2019-11-22
2018-07-13 | 2017 | Special Operations Command | P-966 |  | 2017-04-28 | 2017-09-28 | M A MORTENSON COMPANY | N6247317D0819 | 46106000 | 42893000 | 2020-04-19 | 2020-04-19
2018-06-15 | 2010 | Washington Headquarters Services | 80001 |  | 2013-07-15 | 2013-09-30 | Cherokee Nation | HQ0034-13-C-0133 | 9669575 |  | 2019-04-04 | 2019-04-04
2018-06-15 | 2010 | Washington Headquarters Services | 80001 |  | 2013-09-01 | 2013-09-30 | Virginia Electric and Power Company | HQ0034-13-F-0027 | 13679273 | 13679273 | 2015-01-31 | 2019-04-04
2018-06-15 | 2011 | Washington Headquarters Services | 80002 |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. | HQ0034-13-C-0062 | 43594000 | 47874804 | 2016-07-01 | 2018-08-17
2017-04-20 | 2011 | Washington Headquarters Services | 80003 |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. | W912DR-11-R-0060 | 5609000 | 6357500 | 2015-05-03 | 2016-07-01
2016-09-15 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC | W912DR-11-R-0062 | 5454000 | 5492659 | 2015-05-01 | 2015-10-01
2018-06-15 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2016-09-30 | Turtle Associates | W912DR-16-C-0039 | 6814002 | 7261766 | 2018-05-18 | 2019-06-30
2016-12-15 | 2012 | Washington Headquarters Services | 80005
2016-12-15 | 2012 | Washington Headquarters Services | 80006
2018-04-15 | 2014 | Washington Headquarters Services | 80007
2018-06-15 | 2014 | Washington Headquarters Services | 80008 |  | 2016-02-11 | 2016-04-29 | ACS | W912DR-16-C-0009 | 5797374 | 5953439 | 2017-12-01 | 2018-12-18
2018-06-15 | 2014 | Washington Headquarters Services | 80009 |  | 2016-08-12 | 2017-01-26 | Grunley Construction Company, Inc. | HQ0034-17-C-0009 | 28542500 | 28542500 | 2019-10-02 | 2019-10-02
2017-01-19 | 2014 | Washington Headquarters Services | 80009 |  | 2016-08-12
2018-06-15 | 2014 | Washington Headquarters Services | 80010
2018-06-15 | 2015 | Washington Headquarters Services | 80011
2018-06-15 | 2017 | Washington Headquarters Services | 80916
2018-06-15 | 2017 | Washington Headquarters Services | 87744

## EXPENDITURES
Expenditure Data as of Date | Appropriation Fiscal Year | Project Sponsor Component Name | Appropriation Fund Type Name | Use of Funds | Aggregated Appropriated Amount | Aggregated Current Obligated Amount | Aggregated Current Expenditure Amount
2017-08-31 | 2007 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232000 | 329292795 | 329291135
2017-08-31 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093000 | 52028269 | 50853230
2017-08-31 | 2011 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192950 | 69188207 | 68867780
2017-08-31 | 2010 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558000 | 59491476 | 59491476
2017-08-31 | 2009 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513728 | 205771643 | 205771643
2017-08-31 | 2006 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773860 | 281664955 | 281661594
2017-08-31 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936577 | 3286902 | 3285965
2017-08-31 | 2012 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407000 | 22327424 | 22167664
2017-08-31 | 2008 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 259262000 | 238683341 | 238309413
2017-08-31 | 2017 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 56984000 | 0 | 0
2017-08-31 | 2016 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 150649000 | 0 | 0
2017-08-31 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2015 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2016 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2017 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 0 | 0 | 0
2017-08-31 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing. Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - | 0 | 0 | 0
2017-08-31 | 2013 | Air Force Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 410408 | 374528 | 293493
2017-08-31 | 2006 | Air Force Active | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 63753948 | 60476986 | 59548924
2017-08-31 | 2007 | Air Force Active | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 74021000 | 72589483 | 72587358
2017-08-31 | 2008 | Air Force Active | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 30148000 | 29351160 | 29351161
2017-08-31 | 2009 | Air Force Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105196187 | 103418802 | 103114992
2017-08-31 | 2010 | Air Force Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 112785000 | 108330390 | 107446014
2017-08-31 | 2011 | Air Force Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 63903328 | 62896357 | 62804641
2017-08-31 | 2012 | Air Force Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 78413000 | 76693893 | 76457270
2017-08-31 | 2014 | Air Force Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314000 | 11308781 | 11308781
2017-08-31 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 22238000 | 18410164 | 16128168
2017-08-31 | 2016 | Air Force Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 89164000 | 83824615 | 72702203
2017-08-31 | 2017 | Air Force Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 199393000 | 111062039 | 57918557
2017-08-31 | 2010 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302000 | 4120000 | 4120000
2017-08-31 | 2006 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782960 | 27379308 | 26595117
2017-08-31 | 2008 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210000 | 12161823 | 12161823
2017-08-31 | 2017 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY17 MILCON; design of FY19 non-PB projects if any; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4368000 | 0 | 0
2017-08-31 | 2016 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY16 MILCON; design of FY15 non-PB projects if any; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 9849000 | 4739044 | 4385234
2017-08-31 | 2014 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267000 | 4107328 | 4093791
2017-08-31 | 2009 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703000 | 7524947 | 7524947
2017-08-31 | 2013 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY14 MILCON; design of FY13 non-PB projects if any; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 8251846 | 6261242 | 3959867
2017-08-31 | 2012 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056000 | 4055206 | 4055206
2017-08-31 | 2011 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153000 | 3921567 | 3921567
2017-08-31 | 2007 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064000 | 12735924 | 12735924
2017-08-31 | 2010 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 35000000 | 23989413 | 23989413
2017-08-31 | 2009 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15927089 | 15778887 | 15778887
2017-08-31 | 2008 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20741321 | 16952139 | 16952139
2017-08-31 | 2016 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22900000 | 9017396 | 1366760
2017-08-31 | 2011 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 67548000 | 53598603 | 50902386
2017-08-31 | 2012 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000000 | 19911381 | 19087364
2017-08-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 18175975 | 18055630 | 17556319
2017-08-31 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22613000 | 15830063 | 3187978
2017-08-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 40000000 | 2479860 | 0
2017-08-31 | 2006 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 19369988 | 16716208 | 15244277
2017-08-31 | 2007 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 24108245 | 17277124 | 17217001
2017-08-31 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448000 | 17299514 | 13806700
2018-07-01 | 2012 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200000 | 2117881 | 2082312
2018-07-01 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229000 | 1805573 | 701099
2018-07-01 | 2006 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289570 | 5289120 | 5289120
2018-07-01 | 2007 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109000 | 5072462 | 5072462
2018-07-01 | 2011 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649694 | 1521061 | 1521061
2018-07-01 | 2010 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139000 | 8001719 | 6000916
2018-07-01 | 2009 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165000 | 6133583 | 6123256
2018-07-01 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892000 | 741524 | 218201
2018-07-01 | 2016 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 13400000 | 0 | 0
2018-07-01 | 2008 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300000 | 5270797 | 5270797
2018-07-01 | 2017 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs. | 4500000 | 0 | 0
2018-07-01 | 2013 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875201 | 2362653 | 2155523
2018-07-01 | 2009 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443000 | 5442927 | 5442927
2018-07-01 | 2011 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2753482 | 2728949 | 2651597
2018-07-01 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997361 | 355600 | 38552
2018-07-01 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400000 | 0 | 0
2018-07-01 | 2006 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960000 | 3959698 | 3959698
2018-07-01 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5434000 | 4216309 | 3745090
2018-07-01 | 2010 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 800000 | 752889 | 752889
2018-07-01 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530000 | 0 | 0
2018-07-01 | 2008 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909000 | 4909000 | 4909000
2018-07-01 | 2007 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477000 | 4476971 | 4476971
2018-07-01 | 2017 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1500000 | 0 | 0
2018-07-01 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6121000 | 0 | 0
2017-10-04 | 2016 | Air National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 5104000 | 4473157 | 4024
2017-10-04 | 2009 | Air National Guard | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056000 | 19040836 | 19036989
2017-10-04 | 2013 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994721 | 3980871 | 3980869
2017-10-04 | 2008 | Air National Guard | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721000 | 10619035 | 10619035
2017-10-04 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700000 | 7593622 | 6808998
2017-10-04 | 2007 | Air National Guard | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050000 | 19043340 | 19043339
2017-10-04 | 2010 | Air National Guard | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670441 | 19601297 | 19515670
2017-10-04 | 2006 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006000 | 28018596 | 28018596
2018-12-01 | 2018 | Air National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY98 MILCON; fund Congressionally directed designs. | 17462000 | 4090322 | 1622856
2017-10-04 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400000 | 13343698 | 12753891
2017-10-04 | 2012 | Air National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225000 | 12193435 | 12175493
2017-10-04 | 2017 | Air National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY98 MILCON; fund Congressionally directed designs. | 17462000 | 9142787 | 2326898
2017-10-04 | 2011 | Air National Guard | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195572 | 9131194 | 9080194
2017-10-04 | 2009 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243000 | 34240844 | 34240811
2017-10-04 | 2008 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184000 | 14184000 | 14184000
2017-10-04 | 2007 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000000 | 5999999 | 5999999
2017-10-04 | 2006 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882000 | 6882000 | 6882000
2018-12-01 | 2018 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17495000 | 8348805 | 185370
2017-10-04 | 2017 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17495000 | 10973523 | 858237
2017-10-04 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6100000 | 6061295 | 5959238
2017-10-04 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000000 | 12935481 | 11065498
2017-10-04 | 2013 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892214 | 5889014 | 5879035
2017-10-04 | 2012 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000000 | 8967453 | 8880194
2017-10-04 | 2011 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984000 | 7975387 | 7975387
2017-10-04 | 2010 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913559 | 44873041 | 44638026
2017-10-04 | 2016 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7734000 | 7445247 | 7058920
2018-06-30 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000000 | 22970399 | 22925429
2018-06-30 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000000 | 33873062 | 33873062
2018-06-30 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36500000 | 35954915 | 35954915
2018-06-30 | 2011 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 42944000 | 42931330 | 42931330
2018-06-30 | 2015 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28000000 | 27950526 | 27804089
2018-06-30 | 2016 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36000000 | 35715579 | 34232507
2018-06-30 | 2017 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 18000000 | 17413176 | 14775947
2018-06-30 | 2018 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28700000 | 2582790 | 2507070
2017-06-30 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000000 | 23999817 | 23999817
2018-06-30 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000000 | 24984362 | 24984362
2018-06-30 | 2010 | Army Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 305903000 | 266258784 | 265671175
2018-06-30 | 2011 | Army Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 379238000 | 263258550 | 262118280
2018-06-30 | 2012 | Army Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 265741000 | 253749605 | 250730832
2018-06-30 | 2013 | Army Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46173000 | 46097705 | 44697493
2018-06-30 | 2014 | Army Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575000 | 41308325 | 40959349
2018-06-30 | 2015 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 18127000 | 23015572 | 22899441
2018-06-30 | 2016 | Army Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 73245000 | 71795554 | 67214399
2018-06-30 | 2017 | Army Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 110559000 | 94133541 | 63493060
2018-06-30 | 2018 | Army Active | Planning and Design - Military Construction | Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 97770000 | 30157914 | 8762170
2017-06-30 | 2009 | Army Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766000 | 221199954 | 220667673
2017-06-30 | 2009 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 579000 | 552554 | 548104
2018-06-30 | 2018 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 33559000 | 4850372 | 1325356
2018-06-30 | 2017 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2618000 | 2215845 | 1479928
2018-06-30 | 2016 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7195000 | 7152314 | 6915585
2018-06-30 | 2015 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 1309000 | 1305364 | 1236406
2018-06-30 | 2014 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4408000 | 4368949 | 4217939
2018-06-30 | 2013 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4641000 | 4605750 | 4605750
2018-06-30 | 2012 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7897000 | 7844640 | 7611329
2018-06-30 | 2011 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2036000 | 2029690 | 1579653
2018-06-30 | 2010 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 3936000 | 3198487 | 2745401
2018-06-30 | 2015 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24182617 | 19966369
2018-06-30 | 2012 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 20000000 | 19985763 | 19984463
2018-06-30 | 2011 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 28704000 | 28693975 | 28693975
2018-06-30 | 2010 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 31250000 | 30861396 | 30861396
2017-11-30 | 2018 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 31500000 | 0 | 0
2018-06-30 | 2016 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 19303921 | 12676229
2018-06-30 | 2017 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 35000000 | 22625621 | 2315441
2018-06-30 | 2013 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24894268 | 24148313
2018-06-30 | 2014 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24708017 | 21447300
2017-06-30 | 2009 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 28750000 | 28467081 | 27359122
2018-07-13 | 2018 | Army National Guard | Planning and Design - Military Construction | Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 36271000 | 8195000 | 8195000
2018-07-13 | 2014 | Army National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930000 | 14917000 | 14917000
2018-07-13 | 2015 | Army National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 17600000 | 12917000 | 12917000
2016-12-06 | 2012 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191000 | 20125000 | 20125000
2018-07-13 | 2017 | Army National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20729000 | 2653000 | 2653000
2018-07-13 | 2016 | Army National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20337000 | 261000 | 261000
2017-09-07 | 2013 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17; Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 28155000 | 27519000 | 27519000
2018-07-13 | 2016 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 15000000 | 167000 | 167000
2018-07-13 | 2017 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 12001000 | 1569000 | 1569000
2018-07-13 | 2018 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 26731000 | 0 | 0
2016-12-06 | 2012 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14149000 | 14227000 | 14227000
2017-09-07 | 2013 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14562000 | 14562000 | 14562000
2018-07-13 | 2015 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 13720000 | 10934000 | 10934000
2018-07-13 | 2014 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 12240000 | 12240000 | 12240000
2018-07-01 | 2012 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34331000 | 34331000
2018-07-01 | 2016 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For Design of projects from 2014 to 2019 | 31772000 | 363952 | 363952
2018-07-01 | 2013 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 30636000 | 30636000
2018-07-01 | 2011 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 5247000 | 3801453 | 3801453
2018-07-01 | 2013 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2265551 | 2265551
2015-02-28 | 2012 | Defense Finance and Accounting Service | Planning and Design - Military Construction | Investigation and Design | 1992 | 712 | 711
2015-02-28 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction | Construction | 15404 | 13902 | 13713
2018-06-30 | 2017 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 70000 | 0 | 0
2018-06-30 | 2018 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 40220000 | 19004000 | 12580000
2018-06-30 | 2016 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 94000 | 0 | 0
2018-06-30 | 2015 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 4855000 | 4346000 | 4002000
2018-06-30 | 2014 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 3652000 | 2063000 | 955000
2018-06-30 | 2013 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 78165000 | 52314000 | 17230000
2018-06-30 | 2012 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 64097000 | 59231000 | 30747000
2018-06-30 | 2011 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 172299000 | 171585000 | 153553000
2018-06-30 | 2010 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 72679000 | 72338000 | 70166000
2018-06-30 | 2009 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 171255000 | 170591000 | 170157000
2018-06-30 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 10000000 | 0 | 0
2018-06-30 | 2017 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 8500000 | 0 | 0
2018-06-30 | 2016 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5000000 | 0 | 0
2018-06-30 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4100000 | 0 | 0
2018-06-30 | 2009 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 3979000 | 3979000 | 3979000
2018-06-30 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4608000 | 4571000 | 4550000
2018-06-30 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5930000 | 5256000 | 5256000
2018-06-30 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 3273000 | 2758000 | 2758000
2018-06-30 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4019000 | 3984000 | 3984000
2018-06-30 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4952000 | 3854000 | 3805000
2018-07-25 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2615000 | 46800 | 5000
2018-07-25 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 79739000 | 69643972 | 57967778
2018-07-25 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction |  | 10600000 | 1555392 | 980965
2015-08-31 | 2010 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for K-16 FOB-K renovation of two buildings to include Administrative and SCIF Spaces | 442000 | 0 | 442000
2017-05-05 | 2012 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for DIAC Parking Garage Replacement; P&D for DIAC Chilled Water Project for Data Center ($125K) and P&D for DIAC Cooling Tower for Data Center ($105K); P&D for UPS for Data Center Installation; P&D for Construction of JUIAF RDF | 29335000 | 617649.46 | 19008436.56
2018-07-01 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of projects from 2012 to 2016 | 36093000 | 35966000 | 35966000
2018-07-01 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction |  | 0 | 0 | 0
2018-07-01 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 27241500 | 27415000
2018-07-01 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2015 to 2018 | 6978000 | 0 | 0
2018-07-01 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34239000 | 34239000
2018-07-01 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2013 to 2016 | 7430000 | 0 | 0
2018-07-01 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 4864000 | 4501000 | 4501000
2018-07-01 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2015 to 2019 | 5932000 | 0 | 0
2018-07-01 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2014 | 6312000 | 6312000 | 6312000
2018-07-01 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2266000 | 2266000
2018-06-13 | 2011 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 11/12/ 13 MILCON projects | 75242000 | 75050000 | 75050000
2018-06-13 | 2015 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42387000 | 31707000 | 31707000
2018-06-13 | 2016 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42183000 | 0 | 0
2018-06-13 | 2017 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 23585000 | 0 | 0
2018-06-13 | 2008 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI andFY 08/09/ 10/11/12 MILCON projects | 5161000 | 5159000 | 5159000
2018-06-13 | 2013 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 13/14/15/16 MILCON projects | 97290000 | 94136000 | 94136000
2018-06-13 | 2012 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 12/13 MILCON projects | 64551000 | 63975000 | 63975000
2018-06-13 | 2014 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 14/15/16/17 MILCON projects | 62739000 | 61731000 | 61731000
2018-06-13 | 2010 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 10/11/ 12/13 MILCON projects | 8755000 | 8755000 | 8755000
2018-06-13 | 2009 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13593000 | 13496000 | 13496000
2018-06-13 | 2017 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3000000 | 0 | 0
2018-06-13 | 2015 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 6846000 | 2888000 | 2888000
2018-06-13 | 2014 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5409000 | 5409000 | 5409000
2018-06-13 | 2013 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3771000 | 3771000 | 3771000
2018-06-13 | 2009 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5000 | 4000 | 4000
2018-07-02 | 2015 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 15940000 | 13322000 | 12529000
2017-09-30 | 2013 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 17441000 | 17270000 | 16261000
2018-07-02 | 2018 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 9377000 | 0 | 0
2018-07-02 | 2017 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 11047000 | 0 | 0
2018-07-02 | 2016 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 7857000 | 6457000 | 6047000
2018-07-02 | 2014 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 20011000 | 19372000 | 18241000
2018-07-02 | 2018 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 972000 | 0 | 0
2018-07-02 | 2014 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463000 | 462000 | 462000
2018-07-02 | 2017 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 693000 | 0 | 0
2018-07-02 | 2016 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 430000 | 0 | 0
2017-09-30 | 2013 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455084 | 445000 | 445000
2018-07-02 | 2015 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 75000 | 75000 | 75000
2018-06-30 | 2014 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY14-16 MILCON Projects | 21891000 | 17566765 | 15064703
2018-06-30 | 2015 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY16-17 MILCON Projects | 26290000 | 26273103 | 25675732
2018-06-30 | 2017 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY18-19 MILCON Projects | 15000000 | 4517134 | 1587993
2018-06-30 | 2016 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY17-19 MILCON Projects | 12664000 | 12408346 | 3963174
2018-06-30 | 2015 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY15/16 | 2000000 | 1253815 | 252876
2018-06-30 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY14/15/16 | 2000000 | 1944383 | 1744617
2018-06-30 | 2017 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY18/19 | 2414000 | 0 | 0
2018-06-30 | 2018 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY18/19 | 3000000 | 0 | 0
2018-03-31 | 2015 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - North, VCP1, NSAW Feeders - Central, ECB1 | 99728000 | 99013044 | 78772761
2018-03-31 | 2016 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - Central, ECB2 | 68642000 | 67433339 | 55391021
2018-03-31 | 2017 | National Security Agency | Construction - Major Military Construction | Feeders Ph. 3, ECB2, Access Control Facility | 247890000 | 211580487 | 106926322
2018-03-31 | 2012 | National Security Agency | Construction - Major Military Construction | Mountainview, Whitelaw Wedge, HPCC2, ICECUBE, ECB1, HPCC1, MHS Generator Plant | 333439089 | 333428379 | 326022753
2018-03-31 | 2013 | National Security Agency | Construction - Major Military Construction | MOD II, VCP1, Mountainview, HPCC2, ICECUBE, ECB1, HPCC1 | 511067383 | 508342401 | 467044424
2018-03-31 | 2014 | National Security Agency | Construction - Major Military Construction | HPCC2, ECB1 | 507598526 | 507592511 | 483395530
2018-03-31 | 2017 | National Security Agency | Planning and Design - Military Construction | General P&D | 24780000 | 10667612 | 1783218
2018-03-31 | 2016 | National Security Agency | Planning and Design - Military Construction | General P&D | 1078000 | 1078000 | 703340
2018-03-31 | 2015 | National Security Agency | Planning and Design - Military Construction | General P&D | 599000 | 599000 | 34284
2018-03-31 | 2014 | National Security Agency | Planning and Design - Military Construction | General P&D | 17561473 | 13034315 | 7632783
2018-03-31 | 2012 | National Security Agency | Planning and Design - Military Construction | General P&D | 23800910 | 23594029 | 21176191
2018-03-31 | 2013 | National Security Agency | Planning and Design - Military Construction | General P&D | 4123616 | 3255628 | 3255628
2018-03-31 | 2013 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3530000 | 3530000 | 2521458
2018-03-31 | 2015 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 4229000 | 4205889 | 1198419
2018-03-31 | 2014 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 1500000 | 1442778 | 1350778
2018-03-31 | 2017 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3913000 | 2352742 | 0
2017-09-30 | 2013 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 42740000 | 39135000 | 36887000
2018-07-02 | 2018 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 26874000 | 0 | 0
2018-07-02 | 2017 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
2018-07-02 | 2016 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 3658000 | 0 | 0
2018-07-02 | 2014 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 44716000 | 37165000 | 28540000
2018-07-02 | 2015 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
2018-07-02 | 2014 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 99774000 | 99768000 | 97319000
2017-09-30 | 2013 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 120717000 | 120647000 | 114084000
2018-07-02 | 2015 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 41875000 | 41872000 | 41290000
2018-07-02 | 2016 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 91649000 | 91232000 | 87846000
2018-07-02 | 2017 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 140623000 | 132157000 | 88700000
2018-07-02 | 2018 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 254116000 | 84546000 | 32872000
2017-09-30 | 2013 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609000 | 3567000 | 3530000
2018-07-02 | 2014 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975000 | 3974000 | 2287000
2018-07-02 | 2015 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0
2018-07-02 | 2016 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 3838000 | 3455000 | 2630000
2018-07-02 | 2017 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 3449000 | 757000 | 8000
2018-07-02 | 2018 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 3446000 | 0 | 0
2018-07-02 | 2016 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 22590000 | 21314000 | 9805000
2018-07-02 | 2017 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 29790000 | 14362000 | 2682000
2018-07-02 | 2018 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 33842000 | 0 | 0
2018-07-02 | 2015 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 7163000 | 7061000 | 6554000
2018-07-02 | 2014 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 19740000 | 19460000 | 15838000
2017-09-30 | 2013 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 15612000 | 15309000 | 14132000
2018-07-02 | 2014 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2540000 | 2540000 | 2540000
2018-07-02 | 2017 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 2917000 | 2876000 | 2650000
2018-07-02 | 2016 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 2208000 | 2206000 | 2202000
2018-07-02 | 2015 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 2123000 | 2123000 | 2121000
2017-09-30 | 2013 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995000 | 1995000 | 1992000
2018-07-02 | 2018 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 23762000 | 2357000 | 2127000
2018-07-02 | 2014 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0
2018-07-02 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 4000000 | 2808000 | 2649000
2018-07-02 | 2016 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 1468000 | 0 | 0
2018-07-02 | 2017 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0
2018-07-02 | 2018 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 11504000 | 0 | 0
2017-09-30 | 2013 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0
2018-07-13 | 2013 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 25454000 | 24343000 | 24343000
2018-07-13 | 2014 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 36866000 | 34788000 | 34788000
2018-07-13 | 2015 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 24197000 | 22764000 | 22764000
2018-07-13 | 2016 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 31628000 | 25818000 | 25818000
2018-07-13 | 2017 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 27653000 | 9644000 | 9644000
2018-07-13 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 9216000 | 9116000 | 9116000
2018-07-13 | 2014 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5170000 | 5003000 | 5003000
2018-07-13 | 2015 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 10334000 | 7664000 | 7664000
2018-07-13 | 2016 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 15676000 | 0 | 0
2018-07-13 | 2017 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5994000 | 0 | 0
2018-06-15 | 2014 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 6931000 | 3915105 | 900588
2018-06-15 | 2015 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 1183000 | 0 | 0
2017-09-21 | 2013 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 7508000 | 7508000 | 2860637
2018-06-15 | 2017 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 3427000 | 0 | 0
2016-09-15 | 2012 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4870000 | 4870000 | 3922831
2018-06-15 | 2016 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 3041000 | 0 | 0