## Projects
Submittal date | Fiscal Year | Component | Project type | State or Country | State or country title | Installation | Project number | Project Title | Solicitation/ advertise date | Award date | Contract recipient | Original contract amount ($000) | Current contract obligation ($000) | Start date | Occupancy date | Original completion date | Current completion date | % complete | Funds diverted ($000) (if applicable) | Remarks
2013-04-15 | 2009 | WHS | Major Construction | VA | VIRGINIA | PENTAGON |  | PENTAGON ATHLETIC CLUB (PAC) PHASE II | 2009-10-08 | 2009-12-10 | HSU | 4765 | 5748 | 2009-12-17 | 2011-08-14 | 2010-12-16 | 2011-09-14 | 100 | 40083 | $.0.40083 to SAL ($99K remaining)
2013-04-15 | 2009 | WHS | Major Construction | VA | VIRGINIA | PENTAGON |  | PENTAGON EMERGENCY RESPONSE CENTER (PERC) | 2009-02-05 | 2009-09-21 | THE CHRISTMAN COMPANY | 12469 | 14967 | 2009-09-28 | 2011-12-12 | 2011-07-20 | 2012-05-11 | 99.5 | 683486 | $0.683486 to SAL
2013-04-15 | 2010 | WHS | Major Construction | VA | VIRGINIA | PENTAGON |  | UPGRADE ELECTRICAL SYSTEM | 2012-06-04 |  | TBD | [6 empty] | 0 |  | (Reprogrammed to P&D) $5,700
2013-04-15 | 2010 | WHS | Major Construction | PA | PENNSYLVANIA | RRMC |  | SECONDARY UPS SYSTEM | 2010-06-16 | 2010-09-27 | IRON BRIDGE CONSTRUCTION | 5192 | 7515 | 2010-09-27 |  | 2012-02-29 | 2013-01-31 | 13
2013-04-15 | 2011 | WHS | Major Construction | PA | PENNSYLVANIA | RRMC |  | POWER PLANT MODERNIZATION PHASE 3 WEST POWER PLANT | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc | 43594 | 43594 | 2013-04-22 |  | 2016-05-11 | 2016-05-11 | 0
2013-04-15 | 2011 | WHS | Major Construction | VA | VIRGINIA | PENTAGON |  | METRO ENTRANCE & CORRIDOR 8 | 2012-01-10 |  | TBD | [6 empty] | 0
2013-04-15 | 2011 | WHS | Major Construction | VA | VIRGINIA | PENTAGON |  | SECURE ACCESS LANE (SAL) | 2011-08-08 |  | TBD | [6 empty] | 0
2013-04-15 | 2012 | WHS | Major Construction | VA | VIRGINIA | PENTAGON |  | PENTAGON HELIPORT CONTROL TOWER AND FIRE STATION |  |  | TBD
2013-04-15 | 2012 | WHS | Major Construction | VA | VIRGINIA | PENTAGON |  | PENTAGON WEST-END SAFETY UPGRADE | 2012-08-15 | 2012-09-15 | TBD |  |  |  | 2014-03-15 |  |  | 1
2013-04-15 | 2009 | MDA | Minor Construction | TU | TURKEY | EUCOM SITE | 638 | EUROPEAN PHASED ADAPTIVE APPROACH, PHASE I RADAR SITE | 2011-09-15 | 2011-10-19 | EMTA INSAAT TAAHUT VE TICARET A.S. | 1885 | 1650 | 2011-10-26 | 2011-12-31 | 2011-12-31 | 2013-06-30 | 95 | 0
2013-04-15 | 2009 | MDA | Minor Construction | AK | ALASKA | FORT GREELY | 647 | READINESS & CONTROL (R&C) FACILITY REDUNDANT CHILLED WATER DISTRIBUTION PIPING |  | 2013-03-21 |  | 1564 | 1207 |  | 2013-06-30 | 2013-06-30 | 2013-06-30
2013-04-15 | 2010 | MDA | Minor Construction | AK | ALASKA | FORT GREELY | 647 | READINESS & CONTROL (R&C) FACILITY REDUNDANT CHILLED WATER DISTRIBUTION PIPING |  | 2013-03-21 |  | 1564 | 54 |  | 2013-06-30 | 2013-06-30 | 2013-06-30
2013-04-15 | 2010 | MDA | Major Construction | VA | VIRGINIA | NSWC DAHLGREN | 609 | AEGIS BMD FACILITY EXPANSION | 2010-03-23 | 2010-06-30 | Sauer Incorporated | 18813 | 18681 | 2010-07-15 | 2012-07-31 | 2012-10-31 | 2012-10-31 | 99 | 5700 | (Reprogrammed to P&D) $5,700
2013-04-15 | 2010 | MDA | Major Construction | HI | HAWAII | PMRF | 627 | AEGIS ASHORE MISSILE DEFENSE TEST COMPLEX - CLEARING AND GRUBBING ONLY | 2011-06-30 | 2011-08-03 | TOMCO CORP. | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 100 | 0
2013-04-15 | 2010 | MDA | Major Construction | HI | HAWAII | PMRF | 627 | AEGIS ASHORE MISSILE DEFENSE TEST COMPLEX - CONSTRUCTION | 2012-01-19 | 2012-06-04 | URS GROUP, INC | 59616 | 59616 | 2012-07-04 | 2013-08-12 | 2013-09-12 | 2013-09-12 | 56 | 0
2013-04-15 | 2012 | MDA | Major Construction | AL | ALABAMA | REDSTONE ARSENAL | 633 | VON BRAUN COMPLEX PHASE IV | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | 51330 | 51330 | 2012-07-10 | 2014-07-31 | 2014-10-31 | 2014-10-31 | 14 | 0
2013-04-15 | 2006 | Air Force Active | MFH Construction | NC | NORTH CAROLINA | SEYMOUR JOHNSON AIR FORCE BASE | VKAG056002R1 | REPLACE FAMILY HOUSING (PH 9) | 2007-10-19 | 2009-01-09 | R&O Construction Ogden, Utah | 53054 | 53230 | 2009-03-24 | 2013-04-02 | 2010-09-20 | 2013-04-02 | 98 | 8185
2013-04-15 | 2006 | Air Force Active | MFH improvement | GM | GERMANY | RAMSTEIN AIR BASE | TYFR064009 | IMPROVE FAMILY HOUSING, PH C | 2007-08-01 | 2007-12-06 | Bilfinger Berger | 1802 | 1893 | 2007-12-06 | 2013-04-15 | 2008-07-15 | 2013-02-22 | 99 | -389
2013-04-15 | 2006 | Air Force Active | MFH improvement | GM | GERMANY | RAMSTEIN AIR BASE | TYFR064009 | IMPROVE FAMILY HOUSING, PH C | 2007-08-01 | 2007-12-06 | OBG | 1118 | 1172 | 2007-12-06 | 2013-04-15 | 2008-07-15 | 2013-02-22 | 99 | 0
2013-04-15 | 2007 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT053012 | C-17 ALTER HANGARS (BLDGS 715, 945) | 2007-06-15 | 2007-09-28 | Odyssey | 11816 | 10875 | 2007-11-08 | 2010-11-30 | 2010-10-27 | 2012-10-05 | 100 | 1712
2013-04-15 | 2007 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT053012 | C-17 ALTER HANGARS (BLDGS 715, 945) | 2007-06-15 | 2010-05-07 | Pride | 3397 | 3397 | 2007-11-08 | 2010-11-30 | 2010-10-27 | 2012-10-05 | 100 | 0
2013-04-15 | 2007 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT053012 | C-17 ALTER HANGARS (BLDGS 715, 945) | 2007-06-15 | 2010-11-19 | Pride | 58 | 58 | 2007-11-08 | 2010-11-30 | 2010-10-27 | 2012-10-05 | 100 | 0
2013-04-15 | 2007 | Air Force Active | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ033011 | ADVANCED METAL FINISHING FACILITY (DMRT) | 2007-05-07 | 2008-06-25 | Benham Constructors | 27454 | 27763 | 2008-07-11 | 2013-04-29 | 2010-07-12 | 2013-04-28 | 99 | 1489
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2008-05-30 | Joseph H. Henderson, Gurnee, IL | 16203 | 16230 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 1139
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2008-08-07 | Garco Construction, Inc | 45487 | 46502 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2008-09-21 | Oswood Construction Company | 3711 | 3807 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2009-08-25 | Joseph H. Henderson, Gurnee, IL | 21279 | 21718 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2010-05-11 | Talcott | 12893 | 12959 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2010-09-28 | Affilated Constr | 738 | 732 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2011-07-14 | Garco Constr | 14612 | 15102 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-04-15 | 2007 | Air Force Active | MFH Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS034008 | REPLACE FAMILY HOUSING | 2009-06-05 | 2011-08-31 | Performance Sys | 10264 | 10239 | 2009-09-11 | 2013-11-30 | 2011-08-31 | 2013-10-01 | 93 | 0
2013-04-15 | 2007 | Air Force Active | MFH improvement | GM | GERMANY | RAMSTEIN AIR BASE | TYFR074035 | IMPROVE FAMILY HOUSING, PH D | 2010-04-21 | 2010-08-26 | BilfingerBerger Government Service | 2310 | 1776 | 2010-10-14 | 2012-12-21 | 2008-08-01 | 2012-10-19 | 100 | 380
2013-04-15 | 2007 | Air Force Active | MFH improvement | GM | GERMANY | RAMSTEIN AIR BASE | TYFR074035 | IMPROVE FAMILY HOUSING, PH D | 2010-04-21 | 2011-09-07 | OBG Bau GMBH&CoKG | 1402 | 1402 | 2010-10-14 | 2012-12-21 | 2008-08-01 | 2012-10-19 | 100 | 0
2013-04-15 | 2007 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ074215 | IMPROVE FAMILY HOUSING, PH 7 | 2008-08-01 | 2008-09-29 | OBAYASHI CORPORATION | 99294 | 105428 | 2008-11-18 | 2013-05-30 | 2012-09-01 | 2013-05-31 | 99 | -6532
2013-04-15 | 2007 | Air Force Active | MFH improvement | JA | JAPAN | YOKOTA AIR BASE | ZNRE074306 | IMPROVE MFH (PHASE 5) | 2009-05-26 | 2009-09-22 | Nishimatsu Corporation | 38062 | 40339 | 2009-10-22 | 2012-11-09 | 2009-07-01 | 2012-11-09 | 100 | 5840
2013-04-15 | 2007 | Air Force Active | Minor Construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU073005 | MILITARY WORKING DOG KENNEL | 2006-09-01 | 2007-08-17 | Toltest.Inc | 240 | 240 | 2010-06-29 | 2011-10-27 | 2008-08-17 | 2012-06-26 | 98 | 1753
2013-04-15 | 2007 | Air Force Active | Minor Construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU073005 | MILITARY WORKING DOG KENNEL | 2006-09-01 | 2010-06-03 | D-Squared and AAK (Joint Ventures) | 1312 | 1312 | 2010-06-29 | 2011-10-27 | 2008-08-17 | 2012-06-26 | 98 | 0
2013-04-15 | 2008 | Air Force Active | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT073002 | C-17 SOUTHWEST LANDING ZONE | 2008-07-12 | 2009-02-18 | Baldi Bros Constructors | 12270 | 15319 | 2010-03-01 | 2013-03-26 | 2009-10-15 | 2013-04-16 | 99 | -3081
2013-04-15 | 2008 | Air Force Active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR053714B | REPLACE USCENTCOM HEADQUARTERS | 2009-05-05 | 2007-08-15 | temp fac foundation | 896 | 896 | 2009-08-10 | 2012-10-31 | 2012-01-12 | 2012-10-30 | 100 | -34265
2013-04-15 | 2008 | Air Force Active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR053714B | REPLACE USCENTCOM HEADQUARTERS | 2009-05-05 | 2008-11-21 | Peak Contracting Inc-Early Site | 2476 | 2538 | 2009-08-10 | 2012-10-31 | 2012-01-12 | 2012-10-30 | 100 | 0
2013-04-15 | 2008 | Air Force Active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR053714B | REPLACE USCENTCOM HEADQUARTERS | 2009-05-05 | 2009-06-30 | Clark Construction Group | 61068 | 71895 | 2009-08-10 | 2012-10-31 | 2012-01-12 | 2012-10-30 | 100 | 0
2013-04-15 | 2008 | Air Force Active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU063009 | 1 AF AFFOR CENTER, PH 3 | 2008-07-02 | 2008-09-05 | Speegle Construction, Inc. | 7529 | 7696 | 2008-10-20 | 2010-06-08 | 2010-12-15 | 2013-05-07 | 95 | 355
2013-04-15 | 2008 | Air Force Active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU063009 | 1 AF AFFOR CENTER, PH 3 | 2008-07-02 | 2012-09-25 | SB Ktr for Parking Lot | 306 | 306 | 2008-10-20 | 2010-06-08 | 2010-12-15 | 2013-05-07 | 95 | 0
2013-04-15 | 2008 | Air Force Active | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ053002 | COMMAND POST FACILITY | 2008-07-03 | 2008-09-30 | J2 Engineering, Inc. | 4333 | 4451 | 2008-11-12 | 2011-09-12 | 2010-05-06 | 2011-07-29 | 99 | -41
2013-04-15 | 2008 | Air Force Active | Major construction | NJ | NEW JERSEY | MAJOR CONSTRUCTIONRUCTIONGUIRE AIR FORCE BASE | PTFL083004 | USAF EC JIEDDO TRAINING FACILITY | 2009-08-03 | 2009-09-23 | Eagle Construction Services | 4446 | 4495 | 2009-10-19 | 2011-11-21 | 2011-04-18 | 2012-04-30 | 99 | -850
2013-04-15 | 2008 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALDA053001B | MULTI-AIRCRAFT MAINTENANCE HANGER | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | 15238 | 15238 | 2010-08-23 | 2013-07-30 | 2009-10-30 | 2013-05-31 | 58 | 0
2013-04-15 | 2008 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA073004 | CAS PARKING APRON | 2009-05-22 | 2010-04-14 | American International Contractors, Inc | 55884 | 57367 | 2010-05-20 | 2013-04-15 | 2009-10-31 | 2013-04-15 | 99 | 2000
2013-04-15 | 2008 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA073008A | FACILITY REPLACEMENTS | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | 26245 | 26245 | 2010-08-23 | 2013-07-30 | 2010-06-30 | 2013-05-31 | 58 | 457
2013-04-15 | 2008 | Air Force Active | Major construction | TX | TEXAS | LAUGHLIN AIR FORCE BASE | MXDP073000 | CONSOLIDATED STUDENT ACTIVITY CENTER/LIBRARY | 2009-07-06 | 2009-09-01 | Cooley Constructors, Oklahoma City, OK | 4407 | 5001 | 2009-11-05 | 2011-10-31 | 2010-03-31 | 2013-04-30 | 99 | 749
2013-04-15 | 2008 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ084216 | IMPROVE FAMILY HOUSING, PH 8 | 2009-06-23 | 2009-10-29 | Nishimatsu Construction Corporation | 140248 | 143688 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 76 | 28229
2013-04-15 | 2008 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ084216 | IMPROVE FAMILY HOUSING, PH 8 | 2009-06-23 | 2010-07-23 | PASCO Corporation (Meguro-KU) *Arch Test Digs* | 30 | 30 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 76 | 0
2013-04-15 | 2008 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ084216 | IMPROVE FAMILY HOUSING, PH 8 | 2009-06-23 | 2012-06-22 | Okinawa Elevator Maintenance Union (Naha) *CCT4506 leak rpr* | 43 | 43 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 76 | 0
2013-04-15 | 2008 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ084216 | IMPROVE FAMILY HOUSING, PH 8 | 2009-06-23 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 405 | 405 | 2010-02-04 | 2014-11-15 | 2010-12-30 | 2014-11-15 | 76 | 0
2013-04-15 | 2008 | Air Force Active | MFH improvement | JA | JAPAN | MISAWA AIR BASE | QKKA084025 | IMPROVE FAMILY HOUSING, PH. 3 | 2008-11-21 | 2009-03-31 | Nishimatsu Construction Co. Lt | 35226 | 36790 | 2011-08-31 | 2013-12-14 | 2010-09-01 | 2013-12-14 | 50 | 15873
2013-04-15 | 2008 | Air Force Active | MFH improvement | JA | JAPAN | YOKOTA AIR BASE | ZNRE084303 | IMPROVE MFH (PHASE 6) | 2010-02-12 | 2010-07-08 | Nishimatsu | 31373 | 32642 | 2010-08-02 | 2012-12-21 | 2011-01-01 | 2012-12-25 | 100 | -3587
2013-04-15 | 2008 | Air Force Active | MFH improvement | TU | TURKEY | INCIRLIK AIR BASE ADANA | LJYC084001 | IMPROVE FAMILY HOUSING 515 UNITS | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | 41970 | 41673 | 2009-12-04 | 2014-07-15 | 2011-06-30 | 2014-06-15 | 13 | 14622
2013-04-15 | 2008 | Air National Guard | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU059006 | SQUADRON OPERATIONS FACILITY | 2008-07-11 | 2008-09-19 | Aleut Facilities Support Services, LLC | 6676 | 7904 | 2008-10-24 | 2010-01-27 | 2009-10-19 | 2013-02-18 | 100 | 604
2013-04-15 | 2008 | Air National Guard | Major construction | FL | FLORIDA | JACKSONVILLE INTERNATIONAL AIRPORT | LSGA029009 | COMMUNICATIONS TRAINING FACILITY | 2008-08-25 | 2008-09-26 | Cooley Constructors, Inc. | 4809 | 5661 | 2008-10-15 | 2010-12-12 | 2010-01-18 | 2011-10-25 | 100 | -339
2013-04-15 | 2008 | Air National Guard | Major construction | IN | INDIANA | HULMAN REGIONAL AIRPORT | LDXF069062 | TFI - DISTRIBUTED GROUND STATION (DGS) BEDDOWN | 2008-07-16 | 2008-09-26 | Hannig Construction Incorporated | 2901 | 5074 | 2008-10-15 | 2010-10-01 | 2009-10-15 | 2012-06-01 | 100 | 251
2013-04-15 | 2008 | Air National Guard | Major construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB019121 | ADD/ALTER SECURITY FORCES AND COMMUNICATIONS FACILITY | 2010-10-29 | 2011-01-14 | Kingery Construction | 1181 | 1567 | 2011-02-01 | 2011-11-07 | 2011-02-13 | 2012-02-01 | 100 | -108
2013-04-15 | 2008 | Air National Guard | Major construction | VT | VERMONT | BURLINGTON INTERNATIONAL AIRPORT | CURZ049023 | SECURITY IMPROVEMENTS- RELOCATE POOR FARM ROAD | 2011-01-03 | 2011-09-24 | Stewart Construction INC | 4730 | 6102 | 2011-10-14 | 2012-11-15 | 2012-09-18 | 2013-05-15 | 99 | -641
2013-04-15 | 2008 | Air National Guard | Minor Construction | MA | MASSACHUSETTS | BARNES MUNICIPAL AIRPORT | AXQD109075 | SNOW REMOVAL EQUIPMENT STORAGE FACILITY | 2011-05-23 | 2012-03-09 | Classic Site Solutions, Inc | 1494 | 1694 | 2012-04-20 | 2013-05-31 | 2012-10-17 | 2013-05-31 | 70 | 0
2013-04-15 | 2008 | Air National Guard | Minor Construction | OR | OREGON | KLAMATH FALLS AIRPORT-KINGSLEY FIELD | KJAQ109022 | EXPAND NORTH ARM DISARM APRON | 2012-06-02 | 2012-08-01 | J.I. Garcia | 1931 | 1950 | 2012-08-14 | 2013-05-31 | 2012-12-14 | 2013-07-31 | 75 | 0
2013-04-15 | 2009 | Air Force Active | Major construction | AF | AFGHANISTAN | BAGRAM AB | ATUH093150 | CAS APRON | 2010-05-06 | 2010-09-07 | CH2MHILL | 14119 | 20209 | 2010-10-15 | 2012-07-31 | 2011-07-15 | 2012-10-10 | 100 | -10026
2013-04-15 | 2009 | Air Force Active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | CONSTRUCT CHILD DEVELOPMENT CENTER | 2009-07-31 | 2009-09-29 | MaxFour, Englewood, Co | 8114 | 8150 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | -490
2013-04-15 | 2009 | Air Force Active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | CONSTRUCT CHILD DEVELOPMENT CENTER | 2009-07-31 | 2012-03-05 | M&SS | 31 | 31 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | 0
2013-04-15 | 2009 | Air Force Active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | CONSTRUCT CHILD DEVELOPMENT CENTER | 2009-07-31 | 2012-08-28 | American Demolition Inc | 59 | 59 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | 0
2013-04-15 | 2009 | Air Force Active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA113007 | CONSTRUCT CHILD DEVELOPMENT CENTER | 2009-07-31 | 2012-11-15 | M&SS | 89 | 89 | 2009-10-22 | 2011-12-29 | 2011-03-31 | 2013-01-31 | 100 | 0
2013-04-15 | 2009 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT993002 | ADAL PHYSICAL FITNESS CENTER | 2009-05-11 | 2009-09-03 | Richard Y. Johnson & Son Inc | 11414 | 12457 | 2009-09-17 | 2011-11-18 | 2010-10-06 | 2013-01-31 | 100 | -5654
2013-04-15 | 2009 | Air Force Active | Major construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU063004 | 325 ACS OPS TRAINING COMPLEX | 2009-05-28 | 2009-09-08 | Speegle Construction, Inc. | 7136 | 8401 | 2009-10-14 | 2011-11-29 | 2011-09-08 | 2013-02-07 | 100 | -2284
2013-04-15 | 2009 | Air Force Active | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ023005 | AIRCRAFT HANGAR | 2008-11-07 | 2009-05-01 | Benham Constructors | 20661 | 20927 | 2009-05-20 | 2011-04-27 | 2011-06-27 | 2012-07-10 | 99 | -715
2013-04-15 | 2009 | Air Force Active | Major construction | GM | GERMANY | SPANGDAHLEM AIR BASE | VYHK093005 | CONSTRUCT CHILD DEVELOPMENT CENTER | 2012-01-07 | 2011-09-02 | LBB (EBC AWD) | 9924 | 10171 | 2012-07-09 | 2014-03-30 | 2011-03-09 | 2014-01-30 | 32 | 1307
2013-04-15 | 2009 | Air Force Active | Major construction | GM | GERMANY | SPANGDAHLEM AIR BASE | VYHK093005 | CONSTRUCT CHILD DEVELOPMENT CENTER | 2012-01-07 | 2012-05-15 | Peter Gross GmbH | 1263 | 1263 | 2012-07-09 | 2014-03-30 | 2011-03-09 | 2014-01-30 | 32 | 0
2013-04-15 | 2009 | Air Force Active | Major construction | MS | MISSISSIPPI | KEESLER AIR FORCE BASE | MAHG033002 | INDOOR FIRING RANGE | 2009-07-15 | 2010-06-23 | North Wind, Inc. | 5329 | 5451 | 2010-07-19 | 2012-03-28 | 2011-11-21 | 2012-10-23 | 100 | -570
2013-04-15 | 2009 | Air Force Active | Major construction | MS | MISSISSIPPI | KEESLER AIR FORCE BASE | MAHG043000 | DORMITORY (144 PN) | 2009-07-08 | 2009-08-28 | Anderson Drace JV | 14453 | 15527 | 2009-10-28 | 2011-05-10 | 2011-07-04 | 2013-05-31 | 99 | -3677
2013-04-15 | 2009 | Air Force Active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000 | UPGRADE WEAPONS STORAGE AREA, PHASE I | 2009-08-06 | 2009-09-26 | Doyon Project Services, Federal Way, WA | 10481 | 12002 | 2009-11-11 | 2012-12-10 | 2009-08-07 | 2013-05-31 | 99 | 4995
2013-04-15 | 2009 | Air Force Active | Major construction | NV | NEVADA | CREECH AIR FORCE BASE | LKTC093101 | UAS OPS FACILITY | 2008-12-12 | 2009-04-28 | USACE | 9388 | 13931 | 2009-07-23 | 2013-05-06 | 2010-08-03 | 2013-05-06 | 98 | -332
2013-04-15 | 2009 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF083011 | F-16 AGGRESSOR SQUADRON OPS/INFRASTRUCTURE | 2008-12-29 | 2009-03-24 | HARDY CONSTRUCTION, LAS VEGAS, NV | 5344 | 6197 | 2009-04-23 | 2013-01-10 | 2010-07-05 | 2013-03-15 | 100 | -3001
2013-04-15 | 2009 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF083011 | F-16 AGGRESSOR SQUADRON OPS/INFRASTRUCTURE | 2008-12-29 | 2010-04-21 | CJW-MZT Project II | 5188 | 5188 | 2009-04-23 | 2013-01-10 | 2010-07-05 | 2013-03-15 | 100 | 0
2013-04-15 | 2009 | Air Force Active | Major construction | NJ | NEW JERSEY | MAJOR CONSTRUCTIONRUCTIONGUIRE AIR FORCE BASE | PTFL073003P1 | SECURITY FORCES OPERATIONS FACILITY PH 1 | 2009-06-02 | 2009-08-10 | Eastern Const & Electric Wrightstown NJ | 6610 | 7200 | 2009-08-27 | 2012-08-29 | 2011-08-17 | 2013-01-31 | 99 | 561
2013-04-15 | 2009 | Air Force Active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF072003 | DORMITORY (168 RM) | 2009-06-27 | 2009-08-25 | Graham Construction Services | 18860 | 19749 | 2009-09-24 | 2011-09-19 | 2011-09-14 | 2013-09-30 | 97 | -7268
2013-04-15 | 2009 | Air Force Active | Major construction | OH | OHIO | WRIGHT PATTERSON AIR FORCE BASE | ZHTV063202 | SECURITY FORCES OPERATIONS FACILITY | 2009-04-02 | 2009-06-04 | WIL CON Corporation | 12152 | 13870 | 2009-06-24 | 2011-03-01 | 2010-12-13 | 2013-03-01 | 100 | 884
2013-04-15 | 2009 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA080126 | TEMPORARY WEST MUNITIONS STORAGE AREA | 2010-02-19 | 2010-06-03 | American International Contractors, Inc. | 18079 | 15944 | 2010-08-05 | 2013-02-27 | 2010-12-15 | 2013-02-09 | 100 | 2000
2013-04-15 | 2009 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS093002 | CNS ADDITION TO CHILD DEVELOPMENT CENTER (CDC) B8210 | 2009-07-14 | 2009-08-31 | MAPCO, Inc. | 5913 | 6605 | 2009-10-15 | 2012-08-20 | 2011-02-22 | 2013-09-30 | 95 | 1030
2013-04-15 | 2009 | Air Force Active | Major construction | GB | UNITED KINGDOM | RAF LAKENHEATH | MSET023002 | LARGE VEHICLE INSPECTION STATION | 2009-09-16 | 2010-11-23 | MANSELL PLC | 12684 | 12684 | 2011-01-10 | 2012-11-15 | 2010-08-07 | 2012-11-15 | 100 | 5710
2013-04-15 | 2009 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ094217 | IMPROVE FAMILY HOUSING, PH9 | 2009-06-23 | 2009-09-24 | Nishimatsu Construction Co Ltd | 104812 | 105912 | 2010-02-04 | 2015-10-15 | 2015-10-20 | 2015-10-20 | 76 | 4765
2013-04-15 | 2009 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ094217 | IMPROVE FAMILY HOUSING, PH9 | 2009-06-23 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 140 | 140 | 2010-02-04 | 2015-10-15 | 2015-10-20 | 2015-10-20 | 76 | 0
2013-04-15 | 2009 | Air Force Active | Minor Construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY086000 | INTERIM HORIZONTAL LANDFILL EXPANSION | 2009-07-31 | 2010-03-11 | RMA Land Construction | 910 | 910 | 2010-03-29 | 2013-04-30 | 2010-12-15 | 2013-04-30 | 99 | 2000
2013-04-15 | 2009 | Air Force Active | Minor Construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS086006 | REPLACE MWD KENNEL FACILITY | 2011-02-02 | 2011-07-26 | Oswood Construction, GF, MT | 1904 | 1904 | 2011-08-15 | 2012-11-30 | 2012-11-02 | 2012-12-20 | 92 | 1989
2013-04-15 | 2009 | Air Force Active | Minor Construction | TU | TURKEY | ANKARA ADMINISTRATION OFFICE | AKNR041053 | CNS REPLACE ASF ADMIN BLDG 2621 | 2011-02-22 | 2011-09-23 | MATOC Contractor | 1367 | 1367 | 2012-02-15 | 2014-10-31 | 2011-05-12 | 2014-09-01 | 11 | 1505
2013-04-15 | 2009 | Air National Guard | ARRA | IN | INDIANA | ATTERBURY RESERVE FORCES TRAINING AREA | AQXG029005 | RANGE SUPPORT FACILITY COMPLEX | 2010-06-02 | 2010-07-28 | Dunlap & Co. Inc. | 1052 | 1157 | 2010-09-21 | 2012-06-30 | 2011-07-18 | 2012-06-30 | 100 | 0
2013-04-15 | 2009 | Air National Guard | ARRA | IA | IOWA | DES MOINES INTERNATIONAL AIRPORT | FFAN049054 | REPLACE COMMUNICATIONS FACILITY | 2009-05-05 | 2009-06-23 | Breiholz Construction | 5761 | 6428 | 2009-07-16 | 2010-12-15 | 2010-07-16 | 2012-07-20 | 100 | 431
2013-04-15 | 2009 | Air National Guard | ARRA | PA | PENNSYLVANIA | FT INDIANTOWN GAP ANG STATION | LKLW959714 | REPLACE TROOP TRAINING QUARTERS | 2009-08-05 | 2009-09-30 | Miller Bros Construction | 4986 | 5834 | 2009-10-15 | 2010-11-15 | 2010-10-15 | 2012-01-31 | 100 | -1166
2013-04-15 | 2009 | Air National Guard | ARRA | UT | UTAH | SALT LAKE CITY INTERNATIONAL AIRPORT | USEB889585B | CONSTRUCT MOBILITY PROCESSING AND EOD FACILITY | 2009-05-27 | 2009-08-31 | Zwick Construction Company | 2167 | 2450 | 2009-09-08 | 2012-02-05 | 2011-05-01 | 2012-06-14 | 100 | -2600
2013-04-15 | 2009 | Air National Guard | ARRA | WV | WEST VIRGINIA | EWVRA-SHEPHERD FIELD | PJVY049072 | C-5 AVIONICS SHOP | 2009-07-31 | 2009-09-28 | LDH Electrical Co | 2274 | 2660 | 2009-10-23 | 2010-12-20 | 2010-10-23 | 2011-10-31 | 99 | -1617
2013-04-15 | 2009 | Air National Guard | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU029003 | ALERT CREW HEADQUARTERS | 2009-04-17 | 2009-09-09 | Tower One Construction Company | 2451 | 2877 | 2009-10-30 | 2011-02-11 | 2010-10-30 | 2013-06-20 | 99 | -1323
2013-04-15 | 2009 | Air National Guard | Major construction | CT | CONNECTICUT | BRADLEY INTERNATIONAL AIRPORT | CEKT069119 | TFI - UPGRADE ENGINE SHOP | 2009-06-18 | 2010-01-08 | Cutter Enterprises | 4360 | 5403 | 2010-02-01 | 2012-12-24 | 2010-12-04 | 2013-02-28 | 100 | -2095
2013-04-15 | 2009 | Air National Guard | Major construction | DE | DELAWARE | NEW CASTLE COUNTY AIRPORT | JLWS019057 | REPLACE C-130 AIRCRAFT MAINTENANCE SHOPS | 2009-02-03 | 2009-06-12 | DJ's Mechanical Inc. | 9323 | 9987 | 2009-06-30 | 2011-01-20 | 2010-06-30 | 2011-12-15 | 99 | -1705
2013-04-15 | 2009 | Air National Guard | Major construction | MD | MARYLAND | MARTIN STATE AIRPORT | PJMS959554 | REPLACE FIRE STATION | 2009-07-20 | 2009-09-24 | Milestone Construction Services | 6321 | 7178 | 2009-09-24 | 2011-09-01 | 2011-03-23 | 2012-10-31 | 100 | -739
2013-04-15 | 2009 | Air National Guard | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN079049 | TFI-DIGITAL GROUND STATION- IOC | 2009-09-18 | 2009-09-30 | Endicott Construction | 11792 | 14036 | 2009-10-20 | 2013-03-22 | 2011-04-13 | 2013-04-15 | 93 | -264
2013-04-15 | 2009 | Air National Guard | Major construction | MN | MINNESOTA | MINNEAPOLIS ST PAUL INTL AIRPORT | QJKL079050 | AIRCRAFT DE-ICING DRAINAGE SYSTEM | 2010-09-08 | 2010-09-08 | Hamline Construction | 1161 | 1260 | 2010-10-07 | 2011-06-30 | 2010-10-08 | 2012-02-29 | 100 | -240
2013-04-15 | 2009 | Air National Guard | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB039126 | REPLACE FIRE STATION/TRAINING FACILITY | 2008-06-20 | 2009-11-19 | CITY of St Joseph | 999 | 1063 | 2009-12-19 | 2012-05-20 | 2010-12-14 | 2012-05-20 | 100 | -942
2013-04-15 | 2009 | Air National Guard | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB039126 | REPLACE FIRE STATION/TRAINING FACILITY | 2009-09-01 | 2009-09-28 | Wolfe Construction 836 Osage Ave | 2730 | 2995 | 2009-09-30 | 2011-09-23 | 2010-10-28 | 2011-10-28 | 100 | 0
2013-04-15 | 2009 | Air National Guard | Major construction | NY | NEW YORK | FRANCIS S. GABRESKI AIRPORT | WKVB079038 | REPLACE PARARESCUE OPS FACILITY, PH2 | 2009-06-20 | 2009-03-20 | Racanelli Constrution Company, Inc (631)-454-1010 | 5554 | 5838 | 2009-04-14 | 2012-07-27 | 2010-07-13 | 2012-08-30 | 100 | -1662
2013-04-15 | 2009 | Air National Guard | Major construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP049130 | REPLACE FIRE CRASH RESCUE STATION | 2009-06-22 | 2009-07-29 | Edison Foard, Inc; | 3629 | 5875 | 2009-08-04 | 2010-07-16 | 2010-05-31 | 2012-04-30 | 100 | -1125
2013-04-15 | 2009 | Air National Guard | Major construction | ND | NORTH DAKOTA | HECTOR INTERNATIONAL AIRPORT | KKGA029115 | FIRE CRASH AND RESCUE STATION | 2009-06-20 | 2010-01-27 | TF Powers | 4775 | 5203 | 2010-01-27 | 2011-07-28 | 2011-01-27 | 2012-01-31 | 99 | -2310
2013-04-15 | 2009 | Air National Guard | Major construction | OH | OHIO | SPRINGFIELD-BECKLEY MUNICIPAL AIRPORT | WAAR009098 | COMBAT COMMUNICATIONS TRAINING FACILITY | 2011-04-13 | 2011-08-01 | Tamsah Marker JV | 10601 | 11476 | 2011-08-19 | 2013-05-24 | 2012-08-18 | 2013-06-03 | 96 | -1044
2013-04-15 | 2009 | Air National Guard | Major construction | RI | RHODE ISLAND | QUONSET STATE AIRPORT | TWLR039186 | CONSTRUCT AIR TRAFFIC CONTROL TOWER | 2010-01-08 | 2010-07-23 | Cutter Enterprises, LLC | 6290 | 7708 | 2010-10-26 | 2012-08-10 | 2011-06-01 | 2013-04-30 | 100 | 11
2013-04-15 | 2009 | Air National Guard | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC079089 | AIRCRAFT READY SHELTERS/AMU | 2010-10-05 | 2011-02-02 | Golden Rule Constuction Co., Inc. | 3506 | 3622 | 2011-04-24 | 2012-01-10 | 2011-12-28 | 2012-04-19 | 100 | -878
2013-04-15 | 2009 | Air National Guard | Major construction | TN | TENNESSEE | MAJOR CONSTRUCTIONRUCTIONGHEE TYSON AIRPORT | PSXE999134 | REPLACE SQUADRON OPERATIONS | 2009-08-03 | 2009-09-23 | Hickory Construction, Inc. | 5890 | 6262 | 2009-10-05 | 2011-09-14 | 2011-05-28 | 2011-10-14 | 100 | -1738
2013-04-15 | 2009 | Air National Guard | Major construction | UT | UTAH | SALT LAKE CITY INTERNATIONAL AIRPORT | USEB889585 | REPLACE FIRE STATION | 2009-05-27 | 2009-08-31 | Zwick Construction Company | 5072 | 5975 | 2009-09-08 | 2012-02-10 | 2011-05-01 | 2012-10-31 | 100 | -2525
2013-04-15 | 2009 | Air National Guard | Major construction | VT | VERMONT | BURLINGTON INTERNATIONAL AIRPORT | CURZ069220 | SECURITY FORCES AND COMMUNICATIONS FACILITY | 2011-08-23 | 2011-09-26 | Stewart Construction | 5347 | 6130 | 2011-11-18 | 2013-02-16 | 2013-01-03 | 2013-04-30 | 99 | -470
2013-04-15 | 2009 | Air National Guard | Major construction | WA | WASHINGTON | MAJOR CONSTRUCTIONRUCTIONCHORD AIR FORCE BASE | PQWY059045 | 262D INFO WARFARE AGGRESSOR SQUADRON FACILITY | 2009-08-10 | 2009-09-29 | Pine Island/Takisaki | 5659 | 6792 | 2009-10-02 | 2011-07-25 | 2010-09-27 | 2012-08-01 | 100 | -1808
2013-04-15 | 2009 | Air National Guard | Major construction | WV | WEST VIRGINIA | YEAGER AIRPORT | LYBH009134 | FUEL SYSTEM/CORROSION CONTROL HANGAR | 2009-07-29 | 2009-09-30 | BBL Carlton LLC | 20068 | 21860 | 2009-11-05 | 2011-11-30 | 2011-04-29 | 2012-12-05 | 100 | -1193
2013-04-15 | 2009 | Air National Guard | Minor Construction | AL | ALABAMA | BIRMINGHAM INTERNATIONAL AIRPORT | BRKR029059 | AKC-135 ALERT CREW QUARTERS | 2009-08-21 | 2009-09-29 | North American Specialty Insurance Company | 1232 | 1590 | 2009-10-29 | 2012-12-27 | 2010-12-23 | 2012-12-27 | 99 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG099009 | DRBS STORAGE FACILITY | 2012-07-26 | 2012-09-27 | Marsh Creek Construction | 1412 | 1452 | 2012-10-31 | 2014-01-12 | 2012-10-31 | 2014-01-12 | 0 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | CA | CALIFORNIA | SOUTHERN CALIFORNIA LOGISTICS APT | SCLT109080 | PREDATOR LRE STORAGE FACILITY | 2012-07-26 | 2012-09-27 | Marsh Creek Construction | 1597 | 1637 | 2012-10-31 | 2014-01-14 | 2012-10-31 | 2014-01-14 | 5 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU109069 | REPLACE CRTC AGE FACILITY | 2012-06-05 | 2012-07-19 | HCR Construction Inc | 927 | 1011 | 2012-09-17 | 2013-04-30 | 2013-04-28 | 2013-05-31 | 85 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | IN | INDIANA | FORT WAYNE INTERNATIONAL AIRPORT | ATQZ109537 | A10 CONVERSION ADD AND ALTER AIRCRAFT SHOPS | 2011-03-22 | 2011-09-25 | Patterson Horth | 1406 | 1432 | 2011-09-28 | 2012-10-01 | 2012-08-20 | 2012-10-01 | 70 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | KS | KANSAS | SMOKY HILL ANG RANGE | VUBV119025 | CONSTRUCT VEHICLE MAINTENANCE FACILITY | 2012-11-15 | 2012-12-19 | SBA Construction Company | 1861 | 1920 | 2013-01-18 | 2014-01-17 | 2014-01-18 | 2014-01-14 | 8 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | NY | NEW YORK | EASTERN AIR DEFENSE SECTOR (EADS) ANG | GRCL109071 | ADD TO AND ALTER NEADS OPERATIONS BUILDING | 2012-06-15 | 2012-08-20 | VETCO Contracting Services LLC. | 1331 | 1381 | 2012-08-21 | 2013-06-17 | 2013-06-17 | 2013-06-17 | 84 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP099064 | AANG SHARE- JOINT OPS CENTER | 2009-04-01 | 2009-06-05 | Shelco, Inc | 823 | 823 | 2009-07-13 | 2011-09-30 | 2011-07-13 | 2012-02-15 | 100 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | OH | OHIO | RICKENBACKER INTERNATIONAL AIRPORT (ANG) | NLZG069111 | AIRCRAFT SUPPORT EQUIPMENT (ASE) FACILITY | 2012-02-29 | 2012-05-14 | Puente/CCE - JV | 785 | 5709 | 2012-05-23 | 2013-04-30 | 2013-02-17 | 2013-04-30 | 90 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | OH | OHIO | RICKENBACKER INTERNATIONAL AIRPORT (ANG) | NLZG082014 | SECURITY GATE | 2011-08-24 | 2011-09-22 | SherrickWoolpert Co | 1917 | 1959 | 2011-11-10 | 2012-08-31 | 2012-08-06 | 2013-01-25 | 100 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD109045 | ADD TO AND ALTER CRASH/FIRE STATION | 2010-10-13 | 2011-01-20 | Major ConstructionTech Industries | 1205 | 1542 | 2011-02-03 | 2011-12-29 | 2012-02-03 | 2012-02-29 | 100 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONENTIRE JOINT NATIONAL GUARD BASE | PSTE119018 | PAVEMENTS AND GROUNDS FACILITY | 2012-11-30 | 2013-01-10 | Lyn-Rich Contracting Company | 1560 | 1607 | 2013-02-25 | 2013-08-26 | 2013-08-08 | 2013-08-26 | 0 | 0
2013-04-15 | 2009 | Air National Guard | Minor Construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC079133 | CONVENTIONAL MUNITIONS STORAGE COMPLEX | 2009-08-18 | 2009-09-30 | Golden Rule Construction Co | 1559 | 1792 | 2009-10-16 | 2010-08-19 | 2010-07-13 | 2011-11-30 | 100 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | BAGRAM AB | ATUH103400 | AVIATION OPERATIONS & MAINTENANCE FACILITIES | 2010-05-06 | 2010-09-07 | CH2MHILL | 3085 | 4661 | 2010-10-15 | 2012-11-20 | 2011-07-15 | 2012-11-20 | 100 | -3700
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | BAGRAM AB | ATUH103500 | EXPEDITIONARY FIGHTER SHELTER | 2010-05-06 | 2010-09-07 | CH2MHILL | 2959 | 3868 | 2010-10-15 | 2013-06-15 | 2011-07-15 | 2013-06-15 | 95 | -2072
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | CAMP BASTION | CMBA113100 | PARALLEL TAXIWAY | 2011-01-03 | 2011-05-10 | Enterprise Chemical Corporation/Burlingame/CA | 29770 | 30973 | 2011-05-10 | 2012-05-17 | 2012-02-14 | 2012-10-13 | 100 | -51000
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | CAMP BASTION | CMBA113200 | REFUELER APRON | 2011-01-03 | 2011-05-10 | Environmental Chemical Corporation/Burlingame/CA | 13298 | 13408 | 2011-05-10 | 2012-10-04 | 2012-01-02 | 2012-10-13 | 100 | -39000
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | FOB DWYER | ACC103910 | CARGO HANDLING AREA | 2010-05-10 | 2010-06-25 | ACI-SCC (JV) | 4154 | 4154 | 2010-07-28 | 2013-06-30 | 2011-01-25 | 2013-06-30 | 84 | 106
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | KANDAHAR AB | KARD113100 | EXPAND CARGO HANDLING AREA | 2010-11-23 | 2011-02-14 | Yenigun Insaat Sanayi ve Ticaret A.S. | 5337 | 6121 | 2011-03-30 | 2013-02-01 | 2011-11-21 | 2013-04-12 | 100 | 7100
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | KANDAHAR AB | KARD113200 | EXPEDITIONARY AIRLIFT SHELTER | 2010-11-23 | 2011-02-14 | Yenigun Insaat Sanayi ve Ticaret A.S. | 6743 | 6777 | 2011-03-30 | 2013-05-30 | 2011-11-21 | 2013-05-30 | 99 | 7659
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | KANDAHAR AB | LYAV103500 | ISR APRON EXPANSION | 2010-06-08 | 2010-09-30 | CH2MHill | 21235 | 21668 | 2010-11-02 | 2012-03-23 | 2011-04-29 | 2013-04-12 | 100 | -14877
2013-04-15 | 2010 | Air Force Active | Major construction | AF | AFGHANISTAN | KANDAHAR AB | LYAV103900 | RELOCATE NORTH AIRFIELD ROAD | 2011-03-08 | 2011-07-29 | Contrack International Inc. | 4012 | 5587 | 2011-09-03 | 2012-07-13 | 2011-05-04 | 2012-11-09 | 100 | -8000
2013-04-15 | 2010 | Air Force Active | Major construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW083007 | REPAIR CENTRAL HEAT AND POWER PLANT BOILERS, PHASE 1 | 2010-07-12 | 2011-06-02 | Haskell Corporation | 26981 | 28330 | 2011-06-17 | 2015-01-26 | 2014-11-23 | 2015-01-26 | 26 | 31702
2013-04-15 | 2010 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV103001 | CSAR HC-130J SIMULATOR FACILITY | 2010-04-16 | 2010-08-20 | KISAQ-RQ LLC | 4852 | 5081 | 2010-09-22 | 2013-02-17 | 2012-12-17 | 2013-04-30 | 97 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV103002 | CSAR HC-130J RESCUE SQUADRON OPERATIONS FACILITY | 2010-04-16 | 2010-08-20 | KISAQ-RQ LLC | 4868 | 5035 | 2010-09-22 | 2013-02-17 | 2012-12-17 | 2013-04-30 | 97 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV103003 | CSAR HC-130J INFRASTRUCTURE | 2010-04-16 | 2010-08-20 | KISAQ-RQ LLC | 4150 | 4347 | 2010-09-22 | 2013-02-17 | 2011-05-20 | 2013-04-30 | 98 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT063010 | TAXIWAY MIKE BYPASS ROAD | 2011-06-14 | 2012-01-06 | Hal Hays Construction, Inc | 4899 | 4946 | 2012-01-06 | 2012-12-20 | 2013-01-31 | 2013-01-28 | 99 | 562
2013-04-15 | 2010 | Air Force Active | Major construction | CA | CALIFORNIA | VANDENBERG AIR FORCE BASE | XUMU003000 | CHILD DEVELOPMENT CENTER | 2009-12-04 | 2010-03-18 | The Korte Company | 9777 | 10061 | 2010-04-06 | 2012-05-11 | 2011-01-14 | 2013-01-11 | 100 | -265
2013-04-15 | 2010 | Air Force Active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA093004 | EAST GATE REALIGNMENT | 2011-08-26 | 2011-12-29 | Komada | 5290 | 5467 | 2012-01-26 | 2013-04-30 | 2011-09-30 | 2013-04-30 | 95 | -328
2013-04-15 | 2010 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT033003 | CONSOL COMMUNICATIONS FACILITY | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | 10187 | 11184 | 2010-10-13 | 2013-08-05 | 2011-11-09 | 2014-05-30 | 89 | 1005
2013-04-15 | 2010 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT093000A | CHAPEL CENTER | 2010-06-07 | 2010-11-24 | Gardiner and Gardiner Contracting, LLC | 7719 | 7748 | 2011-01-03 | 2012-11-16 | 2012-05-08 | 2013-02-13 | 100 | 1275
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA053025 | CONSTRUCT DORMITORY (96 RM) | 2009-10-16 | 2010-02-11 | Whitesell-Green, Inc/Yates & Sons, JV | 7635 | 8472 | 2010-09-03 | 2013-03-29 | 2011-08-01 | 2013-03-29 | 100 | 503
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA061726 | F-35 POL OPS FACILITY | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | 4309 | 4384 | 2010-10-27 | 2013-10-30 | 2010-12-30 | 2013-12-31 | 98 | 72
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073902 | F-35 HYDRANT REFUELING SYSTEM PHASE 1 | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | 9452 | 9944 | 2010-07-15 | 2013-10-30 | 2011-02-28 | 2013-12-31 | 99 | -85
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073904 | F-35 JP-8 FLIGHTLINE FILLSTANDS | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | 3217 | 3264 | 2010-10-07 | 2013-10-30 | 2010-12-30 | 2013-12-31 | 97 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073905 | F-35 JP-8 WEST SIDE BULK FUEL TANK UPGRADES | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | 1464 | 1494 | 2010-06-15 | 2013-10-30 | 2010-12-30 | 2013-12-31 | 99 | 85
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073911 | F-35 LIVE ORDNANCE LOAD FACILITY | 2010-03-25 | 2010-06-04 | R.C. Construction Co., Inc. | 14320 | 14551 | 2010-06-28 | 2011-11-01 | 2011-06-30 | 2013-03-11 | 100 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR033702 | CONSOLIDATED COMMUNICATIONS FACILITY | 2010-05-19 | 2010-07-07 | Carothers Construction | 16518 | 16820 | 2010-08-11 | 2013-08-10 | 2013-08-10 | 2013-08-10 | 85 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | MACDILL AIR FORCE BASE | NVZR063708 | DORMITORY (120 ROOM) | 2009-08-21 | 2010-02-19 | David Boland | 10095 | 12251 | 2010-06-09 | 2012-08-13 | 2012-02-04 | 2012-11-05 | 100 | 1724
2013-04-15 | 2010 | Air Force Active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT013025 | COMBAT WEAPONS TRAINING FACILITY | 2010-07-09 | 2010-09-22 | Harkins Development Corp | 8381 | 8511 | 2010-12-03 | 2012-06-22 | 2011-09-30 | 2013-08-29 | 99 | 1544
2013-04-15 | 2010 | Air Force Active | Major construction | GM | GERMANY | RAMSTEIN AIR BASE | TYFR053037 | AEROSPACE GROUND EQUIPMENT MAINTENANCE COMPLEX | 2012-01-27 | 2011-09-30 | LBB (EBC AWD) | 10500 | 10500 | 2012-06-15 | 2014-01-15 | 2012-09-26 | 2013-12-11 | 18 | -2987
2013-04-15 | 2010 | Air Force Active | Major construction | GM | GERMANY | RAMSTEIN AIR BASE | TYFR0530402 | CONTINGENCY RESPONSE GROUP COMMAND | 2011-06-26 | 2011-08-26 | Bodo Freimuth GmbH (Demo AWD) | 235 | 299 | 2012-01-01 | 2014-02-28 | 2012-09-26 | 2014-01-31 | 40 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | GM | GERMANY | RAMSTEIN AIR BASE | TYFR0530402 | CONTINGENCY RESPONSE GROUP COMMAND | 2011-06-26 | 2011-09-24 | LBB (EBC AWD) | 19788 | 19788 | 2012-01-01 | 2014-02-28 | 2012-09-26 | 2014-01-31 | 40 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | GM | GERMANY | SPANGDAHLEM AIR BASE | VYHK043100 | FITNESS CENTER | 2011-01-22 | 2011-05-30 | Peter Gross Bau | 17881 | 18317 | 2011-06-07 | 2013-06-14 | 2006-04-15 | 2013-05-15 | 82 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | HI | HAWAII | HICKAM AIR FORCE BASE | KNMD063003 | GROUND CONTROL TOWER | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | 7379 | 7379 | 2012-09-07 | 2014-02-14 | 2011-10-28 | 2014-02-28 | 8 | 4435
2013-04-15 | 2010 | Air Force Active | Major construction | IL | ILLINOIS | SCOTT AIR FORCE BASE | VDYD040181 | AEROMEDICAL EVACUATION FACIUTY | 2010-03-01 | 2010-05-10 | Charpie-Korte Joint Venture | 5851 | 6460 | 2010-05-25 | 2012-01-31 | 2011-11-09 | 2012-09-04 | 99 | -164
2013-04-15 | 2010 | Air Force Active | Major construction | IT | ITALY | NAVAL AIR STATION SIGONELLA | USAFE073006 | GLOBAL HAWK AIRCRAFT MAINT AND OPS COMPLEX | 2010-03-20 | 2010-09-24 | C.M.C. di Ravenna | 16487 | 16487 | 2010-09-30 | 2012-10-04 | 2009-01-31 | 2012-10-04 | 99 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | MD | MARYLAND | ANDREWS AIR FORCE BASE | AJXF063009 | REPLACE MUNITIONS STORAGE AREA | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | 10465 | 10753 | 2011-06-23 | 2013-12-02 | 2011-12-16 | 2013-12-02 | 78 | 1994
2013-04-15 | 2010 | Air Force Active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG081001 | LAND ACQUISITION NORTH & SOUTH BOUNDARIES | 2012-05-09 | 2012-09-12 | In-House Work Force-NWK | 3475 | 3475 | 2012-09-12 | 2013-10-18 | 2013-02-28 | 2013-10-18 | 50 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | MT | MONTANA | MALMSTROM AIR FORCE BASE | NZAS003000A | UPGRADE WEAPONS STORAGE AREA | 2012-04-23 | 2012-11-28 | RSCI | 9475 | 9475 | 2013-01-07 | 2015-01-07 | 2012-02-29 | 2014-11-10 | 2 | 99
2013-04-15 | 2010 | Air Force Active | Major construction | NE | NEBRASKA | OFFUTT AIR FORCE BASE | SGBP120902 | STRATCOM GATE | 2010-07-08 | 2010-09-24 | JE Dunn Construction Company, Kansas City MO | 10842 | 11328 | 2010-10-14 | 2013-05-28 | 2012-07-15 | 2013-03-29 | 51 | 1910
2013-04-15 | 2010 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063002 | CONSOLIDATED COMMUNICATION FACILITY | 2010-01-14 | 2010-03-24 | San Juan Construction, Inc. | 12305 | 13622 | 2010-04-21 | 2014-02-24 | 2008-06-15 | 2014-01-24 | 41 | 11992
2013-04-15 | 2010 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063002 | CONSOLIDATED COMMUNICATION FACILITY | 2010-01-14 | 2012-01-26 | Spiral Solutions | 1930 | 1930 | 2010-04-21 | 2014-02-24 | 2008-06-15 | 2014-01-24 | 41 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063019 | SOF C-130 FUEL CELL AND CORROSION CONTROL HANGAR | 2009-09-24 | 2010-04-09 | Hensel Phelps Construction | 38933 | 39028 | 2010-05-11 | 2013-03-15 | 2013-03-15 | 2013-03-15 | 99 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073015 | SOF AC-130 MUNITIONS LOADOUT APRON PHASE 1 | 2010-08-19 | 2010-09-30 | Nick Griego & Son's Consruct | 6196 | 6296 | 2010-11-03 | 2012-10-10 | 2012-04-04 | 2012-10-10 | 100 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD103003 | UAS FTU COMPLEX | 2010-05-18 | 2010-09-02 | Mesa Verde Enterprises | 9947 | 12830 | 2010-11-15 | 2012-07-17 | 2012-08-03 | 2013-04-30 | 98 | 5000
2013-04-15 | 2010 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD103003 | UAS FTU COMPLEX | 2010-05-18 | 2010-09-07 | Creative Times | 16695 | 16695 | 2010-11-15 | 2012-07-17 | 2012-08-03 | 2013-04-30 | 98 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | NC | NORTH CAROLINA | POPE AIR FORCE BASE | TMKH063006CT | AIR TRAFFIC CONTROL TOWER | 2010-05-25 | 2010-08-11 | LIFECYCLE CONSTRUCTION SERVICE | 7462 | 7789 | 2010-09-10 | 2013-02-18 | 2011-03-03 | 2013-05-31 | 96 | 108
2013-04-15 | 2010 | Air Force Active | Major construction | NC | NORTH CAROLINA | SEYMOUR JOHNSON AIR FORCE BASE | VKAG013004A | RADAR APPROACH CONTROL COMPLEX, PH 1 | 2010-06-28 | 2010-09-21 | Sanford Group | 5655 | 6168 | 2010-09-29 | 2013-07-29 | 2012-02-06 | 2013-06-28 | 65 | 432
2013-04-15 | 2010 | Air Force Active | Major construction | ND | NORTH DAKOTA | GRAND FORKS AIR FORCE BASE | JFSD200113 | CONSOLIDATED SECURITY FORCES FACILITY | 2010-07-19 | 2010-09-17 | CONSTRUCTION ENGINEERS, INC, Grand Forks ND | 9180 | 9632 | 2010-10-26 | 2012-09-18 | 2012-09-15 | 2013-05-30 | 99 | -1275
2013-04-15 | 2010 | Air Force Active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF082003 | DORMITORY (168 RM) | 2010-05-21 | 2010-08-20 | RAASS Brothers Inc. | 16590 | 17063 | 2010-10-05 | 2012-05-09 | 2012-05-09 | 2013-11-01 | 95 | 18373
2013-04-15 | 2010 | Air Force Active | Major construction | OH | OHIO | WRIGHT PATTERSON AIR FORCE BASE | ZHTV053204 | INFORMATION TECHNOLOGY COMPLEX PH 1 | 2009-11-06 | 2010-02-23 | Messer Construction Company, Dayton, OH | 21970 | 25219 | 2010-03-12 | 2012-06-01 | 2012-02-15 | 2013-05-15 | 99 | 1517
2013-04-15 | 2010 | Air Force Active | Major construction | OH | OHIO | WRIGHT PATTERSON AIR FORCE BASE | ZHTV063301 | CONVERSION FOR ADVANCED POWER RESEARCH LAB | 2009-12-10 | 2010-06-16 | Messer Construction Company, Dayton, OH | 17884 | 19090 | 2010-07-07 | 2013-06-28 | 2012-04-24 | 2013-06-28 | 97 | 245
2013-04-15 | 2010 | Air Force Active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | CHILD DEVELOPMENT CENTER | 2010-03-17 | 2010-05-27 | Nationview/BhateJV | 8649 | 9382 | 2010-05-27 | 2013-04-30 | 2011-12-15 | 2013-04-30 | 98 | 10408
2013-04-15 | 2010 | Air Force Active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | CHILD DEVELOPMENT CENTER | 2010-03-17 | 2010-09-27 | MA-CHIS KAWV TWO, LLC | 231 | 231 | 2010-05-27 | 2013-04-30 | 2011-12-15 | 2013-04-30 | 98 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK043003A | CHILD DEVELOPMENT CENTER | 2010-03-17 | 2010-09-30 | Nationview Bhate - Kitchen Equip - B. Opt 6 | 167 | 167 | 2010-05-27 | 2013-04-30 | 2011-12-15 | 2013-04-30 | 98 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK103019 | T-9 NOISE SUPPRESSOR | 2010-07-23 | 2010-09-24 | Downey Construction LLC, Oklahoma City, OK | 5598 | 5660 | 2010-11-02 | 2012-12-19 | 2011-07-31 | 2012-12-20 | 100 | 1010
2013-04-15 | 2010 | Air Force Active | Major construction | OK | OKLAHOMA | VANCE AIR FORCE BASE | XTLF033303 | CONTROL TOWER | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | 8850 | 9511 | 2010-10-05 | 2013-12-13 | 2012-05-31 | 2013-09-23 | 48 | 673
2013-04-15 | 2010 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA073006A | BLATCHFORD-PRESTON COMPLEX PH II | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | 35759 | 35574 | 2010-12-16 | 2013-08-02 | 2012-02-15 | 2013-07-02 | 48 | 1993
2013-04-15 | 2010 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA103001 | CONSTRUCT NETWORK CONTROL CENTER | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | 2580 | 2580 | 2012-07-05 | 2013-09-08 | 2011-08-15 | 2013-09-08 | 14 | 2911
2013-04-15 | 2010 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA107000 | COALITION COMPOUND BILLETING | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | 45273 | 45273 | 2012-04-16 | 2014-03-06 | 2013-11-30 | 2014-03-06 | 14 | 52000
2013-04-15 | 2010 | Air Force Active | Major construction | SC | SOUTH CAROLINA | SHAW AIR FORCE BASE | VLSB073002 | ADD/ALT USAFCENT HEADQUARTERS | 2010-06-22 | 2010-09-21 | Roy Anderson Corp | 14431 | 16353 | 2010-09-21 | 2012-12-11 | 2012-10-01 | 2013-05-17 | 97 | 1852
2013-04-15 | 2010 | Air Force Active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104200 | STRATEGIC AIRLIFT APRON (MAZAR-E-SHARIF) | 2010-08-23 | 2011-04-08 | Yuksel Insaat A.S./Bestepelar-Ankara/Turkey | 6934 | 7461 | 2011-04-26 | 2013-04-04 | 2011-12-23 | 2013-04-04 | 100 | -18000
2013-04-15 | 2010 | Air Force Active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104210 | HELICOPTER APRON (MAZAR-E-SHARIF) | 2010-08-23 | 2011-04-08 | Yuksel Insaat A.S./Bestepelar-Ankara/Turkey | 22607 | 22876 | 2011-04-26 | 2013-04-04 | 2011-12-23 | 2013-04-04 | 100 | -24000
2013-04-15 | 2010 | Air Force Active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104600 | SOF HELICOPTER APRON (SHINDAND) | 2010-11-19 | 2011-04-29 | Contrack International Inc/Major ConstructionructionLean/VA | 6834 | 7121 | 2011-04-29 | 2012-11-30 | 2012-01-31 | 2012-11-30 | 100 | -11000
2013-04-15 | 2010 | Air Force Active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104601 | SOF ISR APRON & SUPPORT COMPLEX (SHINDAND) | 2010-11-19 | 2011-04-29 | Contrack International Inc/Major ConstructionructionLean/VA | 6083 | 6382 | 2011-04-29 | 2012-11-30 | 2012-01-31 | 2012-11-30 | 100 | -3700
2013-04-15 | 2010 | Air Force Active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104650 | MUNITIONS STORAGE AREA (SHINDAND) | 2010-07-27 | 2010-09-29 | Road and Roof Construction Company (RRCC) | 9812 | 9601 | 2010-11-02 | 2012-11-30 | 2011-07-28 | 2012-11-30 | 100 | -8000
2013-04-15 | 2010 | Air Force Active | Major construction | SC | SOUTH CAROLINA | US CENTRAL COMMAND AIR FORCE | WACC104660 | ISR APRON (SHINDAND) | 2010-11-19 | 2011-04-29 | Contrack International Inc/Major ConstructionructionLean/VA | 21192 | 22252 | 2011-04-29 | 2012-11-30 | 2012-01-31 | 2012-11-30 | 100 | -26504
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU043002 | CONSOLIDATED LEARNING CENTER | 2010-07-06 | 2010-09-10 | The Ross Group | 10657 | 10918 | 2010-09-17 | 2012-10-09 | 2011-09-30 | 2013-06-11 | 99 | 19
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU053000 | JOINT INTEL TECHNICAL TRAINING FACILITY, PH 1 (TFI) | 2010-04-12 | 2010-08-16 | PBS&J Constructors, Inc. | 11390 | 12550 | 2010-10-13 | 2013-07-31 | 2011-06-01 | 2013-07-15 | 87 | 1611
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | GOODFELLOW AIR FORCE BASE | JCGU083001 | STUDENT DORMITORY (100 ROOM) | 2010-02-02 | 2010-06-18 | Triune Beck Joint Venture | 12721 | 13981 | 2010-08-24 | 2013-01-18 | 2011-07-01 | 2013-01-18 | 100 | 916
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083005 | EVASION, CONDUCT AFTER CAPTURE TRAINING | 2009-12-04 | 2010-03-12 | Gideon Marshall Joint Venture | 5160 | 5131 | 2010-04-15 | 2011-08-24 | 2010-12-31 | 2013-04-22 | 98 | 1010
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083005 | EVASION, CONDUCT AFTER CAPTURE TRAINING | 2009-12-04 | 2012-08-12 | JSR Incorporated | 234 | 234 | 2010-04-15 | 2011-08-24 | 2010-12-31 | 2013-04-22 | 98 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | RECRUIT DORMITORY 2, PHASE 2 | 2009-10-15 | 2010-04-20 | Martin Harris (M&H) Enterprises | 41573 | 42488 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2013-04-03 | 100 | -1701
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R2 | RECRUIT DORMITORY 2, PHASE 2 | 2009-10-15 | 2011-05-31 | SB-Federal Program Integrators, NA Corp. | 6663 | 7247 | 2010-05-19 | 2013-04-10 | 2012-06-01 | 2013-04-03 | 100 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S1 | BASIC MILITARY TRAINING SATELLITE CLASSROOM/DINING FACILITY | 2009-12-10 | 2010-02-11 | Lyda Swinerton | 23484 | 25585 | 2010-05-05 | 2012-10-31 | 2011-09-01 | 2012-10-31 | 99 | 533
2013-04-15 | 2010 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S1 | BASIC MILITARY TRAINING SATELLITE CLASSROOM/DINING FACILITY | 2009-12-10 | 2010-06-11 | Telecomm Ductbank Contractor | 1409 | 1602 | 2010-05-05 | 2012-10-31 | 2011-09-01 | 2012-10-31 | 99 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | TU | TURKEY | INCIRLIK AIR BASE ADANA | LJYC003006 | CONSOLIDATED COMMUNITY CENTER | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | 7881 | 8180 | 2010-04-26 | 2014-09-06 | 2008-04-15 | 2014-07-08 | 5 | 930
2013-04-15 | 2010 | Air Force Active | Major construction | AE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF100031 | CONSTRUCT MAINTENANCE OPERATIONS CENTER AND COMMAND POST | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | 1672 | 1710 | 2011-06-03 | 2013-05-15 | 2011-06-15 | 2013-05-15 | 74 | 2138
2013-04-15 | 2010 | Air Force Active | Major construction | AE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF100120 | CONSTRUCT SATCOM FACILITY | 2010-10-28 | 2010-05-06 | Lakeshore Engineering Services, Inc. | 1137 | 1184 | 2011-06-03 | 2013-05-15 | 2011-09-15 | 2013-05-15 | 74 | 1700
2013-04-15 | 2010 | Air Force Active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM043003 | F-22A RADAR CROSS SECTION TESTING FACILITY | 2010-01-06 | 2010-05-27 | Okland Construction | 18401 | 18788 | 2010-06-29 | 2013-05-15 | 2011-12-22 | 2013-05-15 | 94 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | VA | VIRGINIA | AIR COMBAT COMMAND | WACC113220 | RUNWAY (SHARANA) | 2010-06-21 | 2010-09-10 | METAG Insaat Ticaret A.S. | 18251 | 17597 | 2010-10-16 | 2011-10-30 | 2011-10-30 | 2011-10-30 | 29 | 21677
2013-04-15 | 2010 | Air Force Active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | MUHJ053008 | WEST & LASALLE GATES FORCE PROTECTION/ACCESS | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | 7186 | 7690 | 2010-08-04 | 2013-07-02 | 2011-04-28 | 2013-07-02 | 80 | 1303
2013-04-15 | 2010 | Air Force Active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ060074 | REFUELING VEHICLE MAINTENANCE FACILITY | 2010-07-15 | 2010-09-08 | Doyon Project Services LLC, Washington | 3428 | 3533 | 2010-10-14 | 2012-07-17 | 2012-02-28 | 2012-10-19 | 100 | -5
2013-04-15 | 2010 | Air Force Active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ920012P1 | SERE FORCE SUPPORT COMPLEX, PHASE 1 | 2010-07-19 | 2010-09-24 | Yost-Moody-Pugh, Spokane, WA | 7857 | 8473 | 2010-10-18 | 2012-06-28 | 2012-02-28 | 2013-04-30 | 97 | -931
2013-04-15 | 2010 | Air Force Active | Major construction | WY | WYOMING | FRANCIS E WARREN AIR FORCE BASE | GHLN053010 | ADAL MISSILE SERVICE COMPLEX | 2009-10-16 | 2010-03-11 | Lindgren RF Enclosures | 329 | 351 | 2010-04-07 | 2011-11-10 | 2011-09-19 | 2013-06-28 | 99 | 0
2013-04-15 | 2010 | Air Force Active | Major construction | WY | WYOMING | FRANCIS E WARREN AIR FORCE BASE | GHLN053010 | ADAL MISSILE SERVICE COMPLEX | 2009-10-16 | 2010-03-11 | RSCI | 4944 | 5324 | 2010-04-07 | 2011-11-10 | 2011-09-19 | 2013-06-28 | 99 | 0
2013-04-15 | 2010 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ104126 | IMPROVE FAMILY HOUSING, PH 10 | 2010-04-21 | 2010-08-10 | Obayashi Corporation | 54864 | 56112 | 2010-10-01 | 2013-11-01 | 2012-10-01 | 2014-01-01 | 67 | 0
2013-04-15 | 2010 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ104126 | IMPROVE FAMILY HOUSING, PH 10 | 2010-04-21 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 270 | 270 | 2010-10-01 | 2013-11-01 | 2012-10-01 | 2014-01-01 | 67 | 0
2013-04-15 | 2010 | Air Force Active | Minor Construction | AF | AFGHANISTAN | BAGRAM AB | ATUH103046 | CONSTRUCT NETWORK CONTROL CENTER | 2012-01-31 | 2012-05-18 | CH2M Hill | 1274 | 1274 | 2012-06-07 | 2013-06-27 | 2012-07-27 | 2013-06-27 | 37 | 1445
2013-04-15 | 2010 | Air Force Active | Minor Construction | AF | AFGHANISTAN | BAGRAM AB | ATUH103051 | INSTALL AREA LIGHTING ON BRAVO APRON | 2012-01-31 | 2012-05-18 | CH2MHill | 1704 | 1704 | 2012-06-07 | 2013-06-27 | 2012-07-27 | 2013-06-27 | 43 | 1932
2013-04-15 | 2010 | Air Force Active | Minor Construction | AF | AFGHANISTAN | KANDAHAR AB | LYAV100053 | MQ 1/9 OPERATIONS AND MAINTENANCE ADMIN FACILITY | 2012-01-02 | 2012-03-15 | Entire-Ashna-Vertex JV | 1026 | 1026 | 2012-04-14 | 2013-04-15 | 2012-07-13 | 2013-04-15 | 95 | 1180
2013-04-15 | 2010 | Air Force Active | Minor Construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW106001 | CONSTRUCT ARCTIC SURVIVAL FORWARD OPERATING LOCATION | 2011-09-08 | 2011-09-22 | Bristol Design Build Services | 1275 | 1321 | 2011-09-29 | 2012-09-28 | 2012-11-15 | 2012-10-25 | 100 | 1408
2013-04-15 | 2010 | Air Force Active | Minor Construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT073008 | CONSTRUCT MILITARY WORKING DOG & SUPPORTING FACILITY | 2011-07-25 | 2011-09-28 | IE PACIFIC INC | 1620 | 1620 | 2011-10-20 | 2012-09-28 | 2012-09-10 | 2013-02-22 | 87 | 1884
2013-04-15 | 2010 | Air Force Active | Minor Construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA093001 | MILITARY WORKING DOG KENNELS | 2010-08-19 | 2010-11-01 | Barlovento, LLC; Dothan AL | 1772 | 1806 | 2010-12-09 | 2012-05-04 | 2011-12-02 | 2012-12-10 | 100 | 1920
2013-04-15 | 2010 | Air Force Active | Minor Construction | KG | KYRGYZSTAN | MANAS TRANSIT CENTER | BRVN060310 | OPERATIONS TOWN DINING FACILITY | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 936 | 936 | 2011-12-19 | 2013-09-30 | 2012-12-31 | 2013-09-30 | 63 | 1098
2013-04-15 | 2010 | Air Force Active | Minor Construction | KG | KYRGYZSTAN | MANAS TRANSIT CENTER | BRVN100460 | CONSTRUCT FLIGHTLINE FIRE STATION | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 1243 | 1243 | 2011-12-19 | 2013-08-30 | 2012-12-31 | 2013-08-30 | 67 | 1397
2013-04-15 | 2010 | Air Force Active | Minor Construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG101003 | CNST MLA & MHU TRAILER STORAGE FACILITY | 2011-06-17 | 2011-09-23 | Carlson Constructors Corp | 1750 | 1812 | 2011-10-26 | 2013-01-23 | 2012-08-17 | 2013-01-23 | 100 | 1922
2013-04-15 | 2010 | Air Force Active | Minor Construction | WA | WASHINGTON | MAJOR CONSTRUCTIONCHORD AIR FORCE BASE | PQWY093000 | SATELLITE FIRE STATION | 2010-05-07 | 2010-08-19 | Garco Construction | 1824 | 1824 | 2010-09-02 | 2011-09-22 | 2011-04-22 | 2011-09-29 | 99 | 1899
2013-04-15 | 2010 | Air National Guard | Major construction | CA | CALIFORNIA | FRESNO YOSEMITE INTERNATIONAL ANG | HAYW049133 | REPLACE SQUADRON OPERATIONS FACILITY | 2010-12-10 | 2011-02-22 | J.I. Garcia | 8437 | 9724 | 2011-04-14 | 2013-09-30 | 2012-07-12 | 2013-09-30 | 52 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | CA | CALIFORNIA | SOUTH CALIFORNIA LOGISTICS AIRPORT | SCLA069165 | TFI - PREDATOR BEDDOWN - FTU/LRE SITE | 2010-01-22 | 2010-08-02 | PAC West Builders | 4628 | 6404 | 2010-08-30 | 2012-03-13 | 2011-08-30 | 2012-04-30 | 99 | -2012
2013-04-15 | 2010 | Air National Guard | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU019119 | ADAL WEAPON RELEASE FACILITY | 2010-05-28 | 2010-09-23 | Tower One Construction Company | 3025 | 3634 | 2010-10-27 | 2012-02-09 | 2011-08-23 | 2013-06-10 | 98 | -394
2013-04-15 | 2010 | Air National Guard | Major construction | CT | CONNECTICUT | BRADLEY INTERNATIONAL AIRPORT | CEKT079036 | TFI - CNAF BEDDOWN - UPGRADE FACILITIES | 2012-02-21 | 2010-05-26 | LUPACHINO & SALVATORE, INC. | 6107 | 6751 | 2010-06-21 | 2013-05-24 | 2011-06-25 | 2013-09-27 | 99 | -2249
2013-04-15 | 2010 | Air National Guard | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069208 | TFI - F-22 LO/COMPOSITE REPAIR FACILITY | 2009-12-02 | 2010-04-20 | SU MO-NAN, LLC | 23250 | 27109 | 2010-05-24 | 2012-04-19 | 2011-12-25 | 2012-05-15 | 99 | 426
2013-04-15 | 2010 | Air National Guard | Major construction | IL | ILLINOIS | ABRAHAM LINCOLN CAPITAL AIRPORT | DCFT039115 | SECURITY IMPROVEMENTS - RELOCATE BASE ENTRANCE | 2010-05-13 | 2010-09-17 | Perry Broughton Trucking and Excavating | 3391 | 3668 | 2010-10-26 | 2012-07-30 | 2010-10-26 | 2012-07-30 | 100 | 670
2013-04-15 | 2010 | Air National Guard | Major construction | IL | ILLINOIS | GENERAL WAYNE A. DOWNING PEORIA IAP(ANG) | JLQN069160 | SQUADRON OPERATIONS FACILITY | 2010-02-18 | 2010-06-21 | JM Industrial Supply, Inc./River City Construction | 9132 | 10262 | 2010-08-17 | 2012-07-02 | 2012-02-13 | 2012-06-30 | 100 | 1849
2013-04-15 | 2010 | Air National Guard | Major construction | IA | IOWA | DES MOINES INTERNATIONAL AIRPORT | FFAN029023 | ADD TO AND ALTER SECURITY FORCES FACILITY | 2010-08-06 | 2010-09-24 | Neuman Brothers | 4014 | 4247 | 2010-10-01 | 2011-09-11 | 2011-06-28 | 2012-07-27 | 100 | -353
2013-04-15 | 2010 | Air National Guard | Major construction | KS | KANSAS | MAJOR CONSTRUCTIONRUCTIONCONNELL AIR FORCE BASE | PRQE089032 | TFI - UPGRADE DCGS FACILITIES | 2010-05-11 | 2010-08-04 | Key Construction Company | 8223 | 9002 | 2010-08-16 | 2011-11-21 | 2011-08-16 | 2013-04-30 | 99 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | ME | MAINE | BANGOR INTERNATIONAL AIRPORT | FKNN089019 | REPLACE AIRCRAFT MAINTENANCE HANGAR AND SHOPS | 2009-09-29 | 2010-05-12 | Sheridan Corp | 15064 | 17786 | 2010-11-05 | 2012-08-01 | 2012-11-24 | 2013-03-28 | 98 | -9513
2013-04-15 | 2010 | Air National Guard | Major construction | MD | MARYLAND | JOINT BASE ANDREWS | AJXF049104 | REPLACE MUNITIONS MAINTENANCE AND STORAGE COMPLEX | 2010-02-03 | 2011-04-15 | Charter Environmental, Inc. | 14521 | 15179 | 2010-09-13 | 2013-02-26 | 2010-11-12 | 2013-07-28 | 71 | 1662
2013-04-15 | 2010 | Air National Guard | Major construction | MA | MASSACHUSETTS | BARNES MUNICIPAL AIRPORT | AXQD089070 | AIRCRAFT READY SHELTERS | 2010-08-02 | 2010-09-30 | Maron Construction | 5428 | 6534 | 2010-10-26 | 2012-12-31 | 2011-10-26 | 2013-01-31 | 100 | -1300
2013-04-15 | 2010 | Air National Guard | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN019136 | REPLACE OPS AND TRAINING /ADAL DGS | 2010-07-16 | 2010-09-27 | P&S Construction | 2487 | 3073 | 2010-11-01 | 2013-02-25 | 2011-10-27 | 2013-02-15 | 31 | -1000
2013-04-15 | 2010 | Air National Guard | Major construction | MA | MASSACHUSETTS | OTIS ANG BASE | SPBN019136 | REPLACE OPS AND TRAINING /ADAL DGS | 2010-07-22 | 2010-09-30 | K-CON | 6752 | 8938 | 2010-11-01 | 2013-11-29 | 2011-12-29 | 2013-12-31 | 31 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | MI | MICHIGAN | ALPENA COUNTY REGIONAL AIRPORT | TDVG029066 | REPLACE TROOP TRAINING QUARTERS | 2010-06-18 | 2010-08-24 | B&B General Contracting Inc. | 6793 | 7279 | 2010-08-30 | 2012-01-23 | 2011-08-15 | 2013-05-31 | 99 | -1250
2013-04-15 | 2010 | Air National Guard | Major construction | MI | MICHIGAN | SELFRIDGE AIR NATIONAL GUARD BASE | VGLZ059023 | ADD TO AND ALTER SQUADRON OPERATIONS FACILITY | 2010-08-20 | 2010-09-28 | Rock Industries, Inc. | 5698 | 6670 | 2010-11-15 | 2012-11-20 | 2012-01-10 | 2013-04-12 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | MI | MICHIGAN | W. K. KELLOGG AIRPORT | MBMV079055 | TFI - CNAF BEDDOWN - UPGRADE BULDING 6923 | 2010-08-26 | 2010-09-30 | Beckering Advisors, Inc. | 8851 | 10730 | 2010-10-17 | 2012-04-06 | 2012-04-17 | 2012-10-30 | 99 | -1494
2013-04-15 | 2010 | Air National Guard | Major construction | MN | MINNESOTA | MINNEAPOLIS ST PAUL INTL AIRPORT | QJKL089207 | ALTER STARBASE FACILITY | 2010-09-01 | 2010-09-29 | L.S. Black Constructors, Inc. | 1775 | 2177 | 2010-11-08 | 2011-10-17 | 2011-08-08 | 2012-03-01 | 100 | 277
2013-04-15 | 2010 | Air National Guard | Major construction | MS | MISSISSIPPI | GULFPORT - BILOXI REGIONAL AIRPORT | JTVE099057 | FORCE PROTECTION MEASURES - RELOCATE BASE ENTRANCE | 2012-08-15 | 2012-09-27 | Gottfried Contracting | 3823 | 3903 | 2012-10-10 | 2013-07-08 | 2013-06-24 | 2013-07-08 | 1 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | MO | MISSOURI | ROSECRANS MEMORIAL AIRPORT | ULYB099003 | ADD TO FIRE STATION | 2010-03-01 | 2010-07-25 | Lee Grover Constrution | 5709 | 6532 | 2010-08-04 | 2013-05-31 | 2011-07-30 | 2013-07-31 | 64 | -2644
2013-04-15 | 2010 | Air National Guard | Major construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB079069 | JOINT FORCES OPERATIONS CENTER - ANG SHARE | 2009-11-13 | 2010-02-17 | Hausmann Construction, Inc. | 1306 | 1500 | 2010-02-18 | 2012-09-17 | 2011-09-16 | 2012-09-17 | 95 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | NV | NEVADA | RENO-TAHOE INTERNATIONAL AIRPORT | UCTL919637 | REPLACE FIRE STATION | 2010-07-27 | 2010-09-07 | Gilbane Building Company | 9263 | 10246 | 2010-09-23 | 2011-12-25 | 2012-03-21 | 2012-09-30 | 99 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | NH | NEW HAMPSHIRE | PEASE INTERNATIONAL TRADEPORT ANG | SZCQ089023 | REPLACE SQUADRON OPERATIONS FACILITIES | 2011-03-09 | 2011-09-19 | NUTMEG Companies, Inc. | 10752 | 11692 | 2011-10-24 | 2013-04-15 | 2013-02-15 | 2013-05-14 | 80 | 2000
2013-04-15 | 2010 | Air National Guard | Major construction | NJ | NEW JERSEY | JOINT BASE MAJOR CONSTRUCTIONRUCTIONGUIRE-DIX-LAKEHURST | PTFL029107 | REPLACE BASE CIVIL ENGINEER COMPLEX | 2010-07-14 | 2010-09-28 | Puente Construction Enterprises Inc | 6573 | 8230 | 2010-10-21 | 2012-05-07 | 2012-04-20 | 2013-04-30 | 95 | -950
2013-04-15 | 2010 | Air National Guard | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATION | FPBB069168 | REAPER LRE BEDDOWN | 2012-07-27 | 2012-10-17 | Black Horse Group | 3155 | 3201 | 2012-10-17 | 2013-04-26 | 2013-11-11 | 2013-04-26 | 3 | 555
2013-04-15 | 2010 | Air National Guard | Major construction | OH | OHIO | MANSFIELD LAHM AIRPORT | PBXP069219 | TFI - RED HORSE SQUADRON BEDDOWN | 2009-10-15 | 2010-04-12 | Butcher and Baeker Construction | 6368 | 6862 | 2010-05-17 | 2011-09-30 | 2011-06-21 | 2012-02-03 | 100 | -4536
2013-04-15 | 2010 | Air National Guard | Major construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD929753 | REPLACE MUNITIONS STORAGE COMPLEX (ASA) | 2010-07-24 | 2011-04-08 | Penick-Nordic | 10533 | 11857 | 2011-05-24 | 2012-06-15 | 2012-05-07 | 2012-12-31 | 99 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | OK | OKLAHOMA | WILL ROGERS WORLD AIRPORT | YZEU069106 | TFI - ASOS BEDDOWN | 2010-02-05 | 2010-05-06 | Magnum Construction | 4808 | 5206 | 2010-05-05 | 2012-04-18 | 2011-04-30 | 2012-12-04 | 100 | -1111
2013-04-15 | 2010 | Air National Guard | Major construction | OR | OREGON | KLAMATH FALLS AIRPORT-KINGSLEY FIELD | KJAQ029041 | REPLACE SECURITY FORCES FACILITIES | 2010-05-28 | 2010-09-29 | S&B James | 5599 | 5842 | 2010-11-03 | 2012-06-05 | 2012-05-04 | 2012-10-12 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONENTIRE JOINT NATIONAL GUARD BASE | PSTE089005 | JOINT FORCES HEADQUARTERS - ANG PORTION | 2010-05-28 | 2010-08-31 | IKAHANA/CHOATE | 1300 | 1300 | 2010-08-31 | 2012-09-24 | 2011-08-26 | 2013-03-02 | 99 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC059827 | ADD TO MUNITIONS MAINTENANCE COMPLEX, | 2010-08-17 | 2010-09-30 | Sunkota Construction, Inc. | 1054 | 1113 | 2010-10-21 | 2011-08-05 | 2011-07-23 | 2012-01-06 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | SD | SOUTH DAKOTA | JOE FOSS FIELD | LUXC069080 | ADDITION TO ABOVE GROUND MULTI-CUBE MAGAZINE STORAGE | 2010-08-17 | 2010-09-30 | Sunkota Construction, Inc. | 964 | 1011 | 2010-10-21 | 2011-08-05 | 2011-07-23 | 2012-01-06 | 100 | -262
2013-04-15 | 2010 | Air National Guard | Major construction | TN | TENNESSEE | MEMPHIS INTERNATIONAL AIRPORT | PYKL009136 | BASE CIVIL ENGINEER MAINTENANCE AND TRAINING FACILITIES | 2010-07-14 | 2010-09-21 | Chris Wood Construction Co, Inc. | 6069 | 7351 | 2010-10-19 | 2012-10-31 | 2012-10-18 | 2013-02-28 | 97 | -2130
2013-04-15 | 2010 | Air National Guard | Major construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM972002 | ADD TO AND ALTER AVIONICS/ECM SHOP | 2010-07-15 | 2010-09-20 | Triune-Beck JV | 1890 | 1986 | 2011-09-01 | 2012-09-20 | 2011-10-28 | 2012-10-15 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Major construction | TX | TEXAS | KELLY FIELD ANNEX | KELL089001 | ADD/ALT AIRCRAFT MAINTENANCE SHOPS | 2011-07-18 | 2010-09-30 | FA Nunnelly | 4546 | 4948 | 2010-12-17 | 2013-01-23 | 2011-10-30 | 2013-04-01 | 99 | -1000
2013-04-15 | 2010 | Air National Guard | Major construction | VT | VERMONT | BURLINGTON INTERNATIONAL AIRPORT | CURZ029000 | ADD TO AND ALTER FIRE CRASH/RESCUE STATION | 2010-06-12 | 2010-09-27 | EF Wall & Associates, Inc; | 4741 | 5044 | 2010-10-15 | 2012-01-10 | 2011-08-11 | 2012-01-10 | 100 | -955
2013-04-15 | 2010 | Air National Guard | Major construction | WV | WEST VIRGINIA | EWVRA-SHEPHERD FIELD | PJVY069225 | C-5 AIRCRAFT UPGRADE TAXIWAYS | 2010-06-09 | 2010-09-24 | Atlantic Contracting & Material Co., INC | 8080 | 9469 | 2010-10-05 | 2012-08-17 | 2011-11-25 | 2012-09-28 | 100 | -7000
2013-04-15 | 2010 | Air National Guard | Major construction | WI | WISCONSIN | GENERAL MITCHELL INTERNATIONAL AIRPORT | HTUV039088 | ADD TO AND ALTER KC-135 CORROSION CONTROL HANGAR | 2009-11-25 | 2010-08-17 | KPH | 3805 | 4215 | 2010-09-13 | 2012-01-31 | 2011-06-10 | 2012-10-22 | 100 | -782
2013-04-15 | 2010 | Air National Guard | Major construction | WY | WYOMING | CHEYENNE REGIONAL AIRPORT | DPEZ019148A | ADD TO SQUADRON OPERATIONS | 2011-02-04 | 2011-06-02 | Various Contractors | 975 | 1303 | 2011-06-01 | 2011-12-01 | 2011-11-28 | 2012-11-30 | 89 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW009192 | ADD TO COMMUNICATIONS TRAINING FACILITY | 2012-11-07 | 2012-12-27 | G2 Construction | 1448 | 1510 | 2013-01-24 | 2013-10-15 | 2014-01-24 | 2013-10-31 | 4 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | FL | FLORIDA | CAMP BLANDING MILITARY RESERVATION | CYQL099005 | DRBS STORAGE FACILITY | 2012-10-01 | 2013-02-11 | Sweat, LLC | 1143 | 1143 | 2013-02-11 | 2014-02-10 | 2013-11-08 | 2014-02-10 | 5 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU109096 | CRTC SQUADRON OPERATION ADDITION | 2012-11-13 | 2012-12-27 | Holland and Holland, Inc. | 1209 | 1310 | 2013-01-17 | 2014-01-31 | 2014-01-17 | 2014-02-28 | 5 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY099016 | DRBS STORAGE FACILITY | 2011-07-15 | 2011-09-29 | Serrano Construction and Development | 1643 | 1777 | 2011-09-29 | 2013-04-30 | 2012-08-23 | 2013-04-30 | 40 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | IN | INDIANA | FORT WAYNE INTERNATIONAL AIRPORT | ATQZ099062 | A-10 FLIGHT SIMULATOR ADDITION | 2011-09-15 | 2011-04-19 | Patterson Horth | 1028 | 1146 | 2011-05-20 | 2012-02-15 | 2012-03-15 | 2012-02-15 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | MA | MASSACHUSETTS | HANSCOM AFB | MXRD089075 | JOINT FORCES OPERATIONS CENTER- ANG SHARE | 2010-02-10 | 2010-05-27 | CTA Constr | 1500 | 1500 | 2010-05-27 | 2011-11-29 | 2010-05-27 | 2011-11-29 | 10 | 1500
2013-04-15 | 2010 | Air National Guard | Minor Construction | MI | MICHIGAN | ALPENA COUNTY REGIONAL AIRPORT | TDVG072909A | REPLACE CLASSROOM TRAINING FACILITIES | 2012-11-15 | 2012-12-27 | Meridan Contracting Services, LLC | 1437 | 1527 | 2013-03-25 | 2013-10-31 | 2013-08-24 | 2013-10-31 | 3 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | NE | NEBRASKA | LINCOLN MUNICIPAL AIRPORT | NGCB109082 | ALTER BASE ENTRY COMPLEX | 2012-10-30 | 2012-12-27 | American Contracting, LLC | 1297 | 1336 | 2013-01-23 | 2013-11-20 | 2014-01-23 | 2013-11-20 | 1 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | NH | NEW HAMPSHIRE | PEASE INTERNATIONAL TRADEPORT ANG | SZCQ119041 | CONSTRUCT DRBS STORAGE FACILITY | 2012-09-28 | 2012-12-27 | Cornerstone Construction Service LLC | 1604 | 1604 | 2013-03-01 | 2013-10-27 | 2013-10-23 | 2013-10-27 | 0 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | NJ | NEW JERSEY | ATLANTIC CITY INTERNATIONAL AIRPORT | AQRC059017 | MUNITIONS ADMINISTRATIVE FACILITY | 2010-07-16 | 2010-09-29 | Ranco Construction Inc | 1510 | 1607 | 2010-10-25 | 2011-11-25 | 2011-10-25 | 2011-11-25 | 98 | 1607
2013-04-15 | 2010 | Air National Guard | Minor Construction | NC | NORTH CAROLINA | CHARLOTTE/DOUGLAS INTERNATIONAL AIRPORT | FJRP089051 | PRIME BEEF "S TEAMS" BEDDOWN | 2010-06-01 | 2010-09-28 | D.E. Walker Constructing Inc | 1778 | 1970 | 2010-11-22 | 2012-07-12 | 2011-11-22 | 2012-07-12 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | OH | OHIO | MANSFIELD LAHM AIRPORT | PBXP099056 | DRBS STORAGE FACILITY | 2010-09-01 | 2010-09-30 | Blue Scope Construction | 650 | 760 | 2010-09-30 | 2011-08-02 | 2011-04-28 | 2012-01-17 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | OH | OHIO | TOLEDO EXPRESS AIRPORT | WYTD009206 | MULTI-USE INSTRUCTIONAL FACILITY | 2010-08-30 | 2010-09-21 | Rock Industries | 1614 | 1730 | 2010-10-07 | 2011-12-29 | 2011-10-07 | 2012-03-01 | 100 | 1730
2013-04-15 | 2010 | Air National Guard | Minor Construction | OH | OHIO | ZANESVILLE AIR GUARD STATION | ZRVL099068 | SUPPLY WAREHOUSE | 2010-09-17 | 2010-10-27 | Henderson Contractors Corporation | 938 | 1233 | 2010-11-04 | 2012-08-31 | 2011-08-01 | 2013-03-29 | 99 | 1225
2013-04-15 | 2010 | Air National Guard | Minor Construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM109901 | ADD TO CIVIL ENGINEERING FACILITY | 2012-08-19 | 2012-11-21 | Triune-Beck JV | 1479 | 1529 | 2013-02-12 | 2013-11-15 | 2014-06-03 | 2013-11-29 | 5 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | TX | TEXAS | CARSWELL AIR RESERVE STATION | DDPM119026 | MULTI USE TRAINING FACILITY | 2012-08-19 | 2012-11-21 | Tribune-Beck JV | 1697 | 1747 | 2013-02-12 | 2013-11-15 | 2013-11-30 | 2013-11-29 | 5 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | TX | TEXAS | ELLINGTON FIELD | FWJH079112 | MUNITIONS MAINTENANCE SHOP | 2010-04-30 | 2010-09-28 | All American Brothers | 1762 | 1890 | 2010-10-06 | 2012-01-30 | 2011-04-04 | 2012-01-05 | 100 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | TX | TEXAS | KELLY FIELD ANNEX | KELL099067 | F-16 MISSION TRAINING CENTER (FLIGHT SIM) FACILITY | 2010-05-13 | 2011-09-28 | HJD Capital Electric, Inc | 1578 | 1685 | 2011-09-30 | 2013-02-28 | 2012-09-29 | 2013-02-28 | 99 | 0
2013-04-15 | 2010 | Air National Guard | Minor Construction | VA | VIRGINIA | CAMP PENDLETON MILITARY RESERVATION | ERVD099006 | DRBS STORAGE FACILITY | 2011-07-15 | 2011-09-23 | Vanguard Contractors | 854 | 865 | 2012-03-12 | 2012-04-30 | 2012-09-08 | 2012-05-31 | 80 | 0
2013-04-15 | 2010 | Air Force Reserves | Major construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG050237 | SMALL ARMS FIRING RANGE | 2010-07-21 | 2010-09-13 | P&S Construction, Inc. | 8578 | 9092 | 2010-10-14 | 2012-04-06 | 2012-02-16 | 2012-04-06 | 98 | 0
2013-04-15 | 2010 | Air Force Reserves | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT089021 | C-5 SQUADRON OPERATIONS AND AIRCRAFT MAINTENANCE FACILITY | 2010-07-21 | 2010-09-20 | Solpac | 6402 | 7049 | 2010-09-20 | 2012-05-15 | 2011-09-19 | 2012-05-15 | 99 | 0
2013-04-15 | 2010 | Air Force Reserves | Major construction | FL | FLORIDA | HOMESTEAD AIR RESERVE BASE | KYJM049010 | TROOP FEEDING/COMMUNITY ACTIVITY CENTER | 2010-07-26 | 2010-09-21 | JCI | 5117 | 5647 | 2010-12-29 | 2013-04-15 | 2012-05-22 | 2013-07-31 | 95 | -539
2013-04-15 | 2010 | Air Force Reserves | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT033002 | ISO DOCK EXTENSION HANGAR 630 | 2010-07-23 | 2010-09-27 | Sea Tech of the Florida Keys | 2471 | 3346 | 2011-01-04 | 2013-07-19 | 2011-09-15 | 2013-07-19 | 88 | 0
2013-04-15 | 2010 | Air Force Reserves | Major construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ023012 | DEPLOYMENT READINESS AND TRAINING CENTER | 2010-06-17 | 2010-08-31 | EDT Constructors | 5431 | 5669 | 2010-11-02 | 2012-12-06 | 2012-03-06 | 2012-12-06 | 99 | 0
2013-04-15 | 2010 | Air Force Reserves | Major construction | MS | MISSISSIPPI | KEESLER AIR FORCE BASE | MAHG063003 | AERIAL PORT SQUADRON FACILITY | 2010-03-30 | 2010-08-09 | W. G. Yates & Sons Const. Co. | 6827 | 8077 | 2010-08-26 | 2012-08-16 | 2012-03-01 | 2013-01-08 | 100 | 0
2013-04-15 | 2010 | Air Force Reserves | Major construction | NY | NEW YORK | NIAGARA FALLS IAP-AIR RESERVE STATION | RVKQ109091 | INDOOR SMALL ARMS RANGE | 2010-07-16 | 2010-09-22 | R.B. Mac Construction, Inc. | 6236 | 6565 | 2010-11-05 | 2012-10-10 | 2011-11-04 | 2012-10-10 | 99 | 1323
2013-04-15 | 2010 | Air Force Reserves | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | KELL043010A | WING TRAINING AND READINESS FACILITY | 2010-07-26 | 2010-09-30 | EDT Construction | 5627 | 5627 | 2010-11-02 | 2012-10-15 | 2011-09-30 | 2012-10-15 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | AF | AFGHANISTAN | BAGRAM AB | ATUH110101 | CONSOLIDATED RIGGING FACILITY | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest, JV, LLC | 8364 | 9839 | 2011-08-10 | 2013-08-22 | 2012-03-14 | 2013-08-22 | 39 | 1313
2013-04-15 | 2011 | Air Force Active | Major construction | AF | AFGHANISTAN | BAGRAM AB | ATUH110103 | MEDEVAC RAMP EXPANSION/ FIRE STATION | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest JV, LLC | 9537 | 10755 | 2011-08-10 | 2013-10-13 | 2012-03-14 | 2013-10-13 | 39 | 994
2013-04-15 | 2011 | Air Force Active | Major construction | AF | AFGHANISTAN | BAGRAM AB | ATUH110104 | FIGHTER HANGAR | 2010-12-22 | 2011-07-27 | Lakeshore-Toltest IV, LLC | 8305 | 10417 | 2011-08-10 | 2013-09-24 | 2012-03-14 | 2013-09-24 | 61 | 3837
2013-04-15 | 2011 | Air Force Active | Major construction | AF | AFGHANISTAN | HERAT | KLZT103000 | SOF HELICOPTER APRON | 2012-01-02 | 2012-03-05 | State Corps Limited/Kabul/Afghanistan | 6920 | 305 | 2013-02-13 | 2013-09-30 | 2012-12-21 | 2013-09-30 | 2 | 8200
2013-04-15 | 2011 | Air Force Active | Major construction | AL | ALABAMA | MAXWELL AIR FORCE BASE | PNQS983126 | ADAL AIR UNIVERSITY LIBRARY | 2010-12-07 | 2011-06-14 | Southeast Cherokee Construction | 10211 | 10967 | 2011-07-18 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 89 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | AK | ALASKA | EIELSON AIR FORCE BASE | FTQW083008 | REPAIR CENTRAL HEAT AND POWER PLANT BOILER | 2010-07-12 | 2011-06-02 | Haskell Corporation | 26981 | 26981 | 2011-06-17 | 2015-01-26 | 2014-11-24 | 2015-01-26 | 26 | 2000
2013-04-15 | 2011 | Air Force Active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB073012 | F-22 ADD/ALTER WEAPONS RELEASE SYSTEMS SHOP & AME (TFI) | 2010-09-29 | 2011-09-29 | Bristol Design Build Services, LLC | 5608 | 6046 | 2011-10-12 | 2013-05-22 | 2012-07-23 | 2013-05-22 | 85 | 247
2013-04-15 | 2011 | Air Force Active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB123201 | ADD/ALTER AIR SUPPORT OPERATIONS SQUADRON TRAINING FACILITY | 2010-08-10 | 2011-07-19 | Tunista | 4237 | 4202 | 2011-07-29 | 2012-10-11 | 2012-01-20 | 2012-10-11 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV063501 | AMARG HANGAR | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | 22282 | 22262 | 2011-09-07 | 2014-01-14 | 2013-03-11 | 2014-01-14 | 18 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV103005 | HC-130J PARTS STORE | 2011-05-06 | 2011-09-28 | Benchmark INC, DBA Cobblestone/ Las Vegas/ NV | 5195 | 5258 | 2011-11-17 | 2013-10-17 | 2012-07-30 | 2013-10-17 | 41 | 423
2013-04-15 | 2011 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV113002 | HC-130J AERIAL CARGO FACILITY | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | 7223 | 7223 | 2011-11-09 | 2013-10-16 | 2012-09-21 | 2013-10-16 | 72 | -2491
2013-04-15 | 2011 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV113007 | HC-130 AGE MAINTENANCE FACILITY | 2010-12-03 | 2011-06-06 | Benchmark Contr DBA Cobblestone Constr Las Vegas NV | 4078 | 4256 | 2011-07-05 | 2013-05-10 | 2012-03-12 | 2013-05-10 | 92 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093000 | F-35 ACADEMIC TRAINING CENTER | 2012-04-18 | 2012-08-30 | Archer Western Contractors | 43347 | 43706 | 2012-11-05 | 2014-06-07 | 2013-06-28 | 2014-07-08 | 8 | -2434
2013-04-15 | 2011 | Air Force Active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | NUEX093001 | F-35 SQUADRON OPS FACILITY | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | 9109 | 9109 | 2012-10-09 | 2013-12-10 | 2013-06-28 | 2014-01-26 | 29 | 273
2013-04-15 | 2011 | Air Force Active | Major construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU073004 | SECURITY FORCES OPERATIONS FACILITY | 2010-09-14 | 2011-06-01 | Roche Constructors, Inc. | 8274 | 8472 | 2011-07-05 | 2013-02-01 | 2011-06-24 | 2013-02-01 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | CO | COLORADO | PETERSON AIR FORCE BASE | TDKA093005 | RAIDRS SPACE CONTROL FACILITY | 2010-11-12 | 2011-06-08 | Bryan Construction | 14284 | 14276 | 2011-06-08 | 2013-05-15 | 2012-08-17 | 2013-05-15 | 96 | -2269
2013-04-15 | 2011 | Air Force Active | Major construction | CO | COLORADO | USAF ACADEMY | XQPZ084017 | CONST CENTER FOR CHARACTER & LEADERSHIP DEVELOPMENT | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | 24996 | 24716 | 2013-01-14 | 2014-09-29 | 2014-05-15 | 2014-09-29 | 3 | 1205
2013-04-15 | 2011 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT113001 | C-5M/C-17 MAINTENANCE TRAINING FACILITY, PH 2 | 2011-03-09 | 2011-08-02 | Asset Group, Incorporated, Oklahoma City, Oklahoma | 2952 | 2947 | 2011-08-11 | 2013-09-27 | 2012-05-30 | 2013-10-09 | 44 | 127
2013-04-15 | 2011 | Air Force Active | Major construction | DC | DISTRICT OF COLUMBIA | BOLLING AIR FORCE BASE | BXUR105000 | JOINT AIR DEFENSE OPERATIONS CENTER | 2011-03-02 | 2011-08-05 | Sauer Inc. | 11978 | 12622 | 2011-08-05 | 2013-07-30 | 2012-02-29 | 2013-07-30 | 70 | 1783
2013-04-15 | 2011 | Air Force Active | Major construction | FL | FLORIDA | EGLIN AIR FORCE BASE | FTFA073908 | F-35 FUEL CELL MAINTENANCE HANGAR | 2010-10-06 | 2011-06-23 | Sauer Inc. | 6957 | 7164 | 2011-08-17 | 2013-05-01 | 2013-01-05 | 2013-05-24 | 80 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV023010 | ADD TO VISITING QUARTERS (24 RM) | 2010-09-24 | 2011-06-15 | DWG & Associates, Inc. | 3516 | 3572 | 2011-08-11 | 2013-06-14 | 2012-01-10 | 2013-07-18 | 92 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV023013 | ADAL SPECIAL OPERATIONS SCHOOL FACILITY | 2010-09-23 | 2011-06-20 | Barlovento, LLC | 4536 | 4849 | 2011-07-28 | 2013-03-01 | 2012-05-15 | 2013-04-19 | 94 | 121
2013-04-15 | 2011 | Air Force Active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | BASE LOGISTICS FACILITY | 2010-09-22 | 2011-06-06 | Sauer Incorporated | 16031 | 16569 | 2011-07-19 | 2013-07-25 | 2011-07-25 | 2013-07-25 | 68 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | BASE LOGISTICS FACILITY | 2010-09-22 | 2011-08-29 | AEROSTAR ENVIRONMENTAL SERVICES, INC. | 192 | 192 | 2011-07-19 | 2013-07-25 | 2011-07-25 | 2013-07-25 | 68 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV043016 | BASE LOGISTICS FACILITY | 2010-09-22 | 2012-10-03 | STOA Architects | 163 | 163 | 2011-07-19 | 2013-07-25 | 2011-07-25 | 2013-07-25 | 68 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT053001 | AIR FORCE TECHNICAL APPLICATIONS CENTER | 2010-11-04 | 2011-06-03 | Hensel Phelps | 70619 | 73970 | 2011-07-06 | 2014-01-31 | 2015-06-30 | 2015-12-02 | 50 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | GM | GERMANY | KAPAUN ADMINISTRATION ANX | TYFU083507R2 | DORMITORY (128 RM) | 2013-04-26 | 2011-09-16 | LBB (EBC AWD) | 17945 | 17945 | 2013-06-24 | 2015-07-15 | 2013-03-06 | 2015-02-09 | 1 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | GM | GERMANY | RAMSTEIN AIR BASE | TYFR073143 | UAS SATCOM RELAY PADS AND FACILITY | 2011-08-12 | 2011-09-26 | Bidder C | 8352 | 8352 | 2011-12-15 | 2013-07-15 | 2012-12-30 | 2013-06-03 | 60 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | GM | GERMANY | RAMSTEIN AIR BASE | TYFR083001 | DEICING FLUID STORAGE & DISPENSING FACILITY | 2012-05-10 | 2011-09-02 | LBB | 2671 | 2671 | 2012-10-31 | 2013-09-11 | 2011-08-17 | 2013-07-17 | 30 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | GM | GERMANY | RAMSTEIN AIR BASE | TYFR123063 | C-130J FLIGHT SIMULATOR FACILITY | 2013-07-02 | 2011-09-02 | LBB (EBC AWD) | 7024 | 7024 | 2013-11-20 | 2015-01-28 | 2012-04-29 | 2014-12-26 | 1 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | GM | GERMANY | VILSECK | VILS093001 | AIR SUPPORT OPERATIONS SQUADRON (ASOS) COMPLEX | 2011-07-01 | 2011-09-23 | Mickan Amber | 10734 | 10890 | 2011-10-05 | 2013-05-04 | 2013-01-13 | 2013-04-04 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY113007 | GUAM STRIKE OPS GROUP & TANKER TASK FORCE RENOVATION (TFI) | 2010-09-17 | 2011-09-12 | P & S Construction | 8627 | 9013 | 2011-09-27 | 2013-11-06 | 2012-08-13 | 2013-11-06 | 84 | 629
2013-04-15 | 2011 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY336509 | GUAM STRIKE SOUTH RAMP UTILITIES PHASE 1 (TFI) | 2010-09-17 | 2011-07-28 | P & S Construction | 9582 | 9536 | 2011-08-18 | 2013-06-15 | 2013-01-30 | 2013-06-15 | 91 | -1369
2013-04-15 | 2011 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | SAKW091006 | PRTC - RED HORSE HEADQUARTERS/ENGINEERING FACILITY | 2010-08-18 | 2011-06-07 | Overland Corporation | 6538 | 7220 | 2011-06-30 | 2013-02-27 | 2012-10-09 | 2013-04-30 | 99 | 372
2013-04-15 | 2011 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | SAKW123002 | PRTC - COMBAT COMMUNICATIONS OPERATIONS FACILITY | 2010-08-13 | 2011-06-06 | Guam Pacific International, LLC | 7548 | 7532 | 2011-06-30 | 2012-11-23 | 2012-11-23 | 2012-12-21 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | IT | ITALY | AVIANO AIR BASE | ASHE083011 | AIR SUPPORT OPERATIONS SQUADRON (ASOS) FACILITY | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | 7174 | 7201 | 2011-12-15 | 2013-11-30 | 2013-06-06 | 2013-10-30 | 31 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | IT | ITALY | AVIANO AIR BASE | ASHE123000 | DORMITORY (144 RM) | 2011-02-14 | 2011-07-28 | A.T.I. TACOSE S.c.a.r.l. | 13672 | 13684 | 2011-10-11 | 2013-07-30 | 2013-01-13 | 2013-06-18 | 65 | -247
2013-04-15 | 2011 | Air Force Active | Major construction | KR | KOREA | KUNSAN AIR BASE | MLWR093183 | CONSTRUCT DMT FLIGHT SIMULATOR FACILITY | 2010-08-18 | 2011-07-07 | Kum Sung Construction Co., Ltd | 6568 | 6717 | 2011-07-07 | 2013-02-28 | 2012-06-29 | 2014-01-31 | 98 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | LA | LOUISIANA | BARKSDALE AIR FORCE BASE | AWUB025502 | WEAPONS LOAD CREW TRAINING FACILITY | 2010-10-22 | 2011-08-03 | Pacific - Tech - Sauer JV | 15903 | 15903 | 2011-08-03 | 2013-11-14 | 2013-01-28 | 2013-11-14 | 29 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NV | NEVADA | CREECH AIR FORCE BASE | LKTC113102 | UAS AIRFIELD FIRE/CRASH RESCUE STATION | 2010-12-10 | 2011-06-29 | Jaynes Corporation | 7345 | 7423 | 2011-09-02 | 2013-08-01 | 2013-03-01 | 2013-07-15 | 42 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF093004 | F-35A MAINTENANCE HANGAR/AMU | 2011-03-23 | 2011-09-15 | Straub Construction, Inc | 20049 | 20517 | 2011-11-09 | 2013-12-15 | 2013-02-06 | 2013-12-01 | 36 | -3071
2013-04-15 | 2011 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103002 | F-35 ADD/ALTER 422 TEST EVALUATION SQUADRON FACILITY | 2010-01-07 | 2011-07-25 | Teehee-Straub JV | 5912 | 6773 | 2011-09-14 | 2013-05-15 | 2012-08-01 | 2013-05-15 | 95 | 747
2013-04-15 | 2011 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103007 | F-35 FLIGHT SIMULATOR FACILITY | 2010-11-18 | 2011-07-27 | Swinerton Builders | 8725 | 9028 | 2011-09-19 | 2013-05-15 | 2012-08-01 | 2013-05-15 | 95 | -2887
2013-04-15 | 2011 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103008 | F-35A ADD/ALTER FLIGHT TEST INSTRUMENTATION FACILITY | 2011-01-07 | 2011-08-02 | Power Services Inc. | 1508 | 1538 | 2011-09-09 | 2012-09-17 | 2012-02-02 | 2012-11-30 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NJ | NEW JERSEY | MAJOR CONSTRUCTIONRUCTIONGUIRE AIR FORCE BASE | PTFL063000 | BASE OPS/COMMAND POST FACILITY (TFI) | 2010-12-08 | 2011-06-30 | Marco Builders, Inc | 6714 | 6714 | 2011-07-30 | 2013-04-30 | 2012-01-30 | 2013-03-31 | 87 | -127
2013-04-15 | 2011 | Air Force Active | Major construction | NJ | NEW JERSEY | MAJOR CONSTRUCTIONRUCTIONGUIRE AIR FORCE BASE | PTFL083003 | DORMITORY (120 ROOM) | 2010-12-08 | 2011-08-04 | Ranco Construction Inc | 13772 | 13772 | 2011-10-19 | 2013-06-28 | 2012-05-30 | 2013-07-09 | 32 | -2921
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063049 | SOF HANGER/AMU (MAJOR CONSTRUCTIONRUCTION-130J) | 2011-06-09 | 2011-09-09 | Speegle Construction | 20092 | 20092 | 2011-10-13 | 2014-02-05 | 2014-02-05 | 2014-02-05 | 61 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063051 | SOF C-130 AIRCRAFT PARKING APRON | 2011-02-24 | 2011-08-03 | Sundt | 9643 | 9643 | 2011-10-05 | 2012-10-12 | 2012-06-06 | 2012-06-06 | 99 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063052 | SOF OPERATIONS AND TRAINING COMPLEX | 2011-04-26 | 2011-10-26 | Speegle Construction | 29138 | 29138 | 2012-01-12 | 2014-05-12 | 2014-05-12 | 2014-05-12 | 22 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ063054 | SOF C-130 PARKING APRON (RECAP) PHASE I | 2011-02-08 | 2011-08-03 | Sundt | 20016 | 20016 | 2011-10-05 | 2012-10-12 | 2012-10-12 | 2012-10-12 | 99 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073005 | DORMITORY (96 RM) | 2011-10-07 | 2012-02-15 | Charpie Korte Builders, LLC | 12413 | 12413 | 2012-04-19 | 2013-10-11 | 2012-07-02 | 2013-10-11 | 62 | -121
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073012 | SOF ADAL SIMULATOR FACILITY FOR MAJOR CONSTRUCTIONRUCTION-130 (RECAP) | 2011-05-25 | 2011-08-25 | PACE Pacific | 9324 | 9483 | 2011-11-03 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 94 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ093004 | UAS SQUADRON OPS FACILITY | 2011-04-27 | 2011-10-11 | Speegle Construction Inc | 13126 | 13126 | 2012-01-10 | 2014-03-28 | 2013-01-18 | 2014-03-28 | 43 | -4437
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD093013 | UAS ADD/ALTER MAINTENANCE HANGAR | 2011-06-22 | 2011-09-13 | Candelaria Corporation | 10254 | 10254 | 2011-10-12 | 2013-10-03 | 2012-07-02 | 2013-10-03 | 15 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD093016 | UAS MAINTENANCE HANGAR | 2011-07-29 | 2011-09-29 | Hensel Phelps Construction Company | 19498 | 19644 | 2011-11-03 | 2013-10-25 | 2013-01-18 | 2013-10-25 | 71 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV053114A | ARMAMENT SHOP | 2011-07-13 | 2011-09-23 | K.L. House | 3548 | 3548 | 2011-11-09 | 2013-09-09 | 2012-01-26 | 2013-07-31 | 80 | -1178
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV083114 | H/MAJOR CONSTRUCTIONRUCTION-130 FUEL SYSTEM MAINTENANCE FACILITY | 2011-02-11 | 2011-09-23 | K.L House | 11178 | 11596 | 2011-11-09 | 2013-09-09 | 2012-05-01 | 2013-07-31 | 74 | -737
2013-04-15 | 2011 | Air Force Active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV083118 | AERIAL DELIVERY ADDITION | 2011-07-21 | 2011-09-16 | TLW | 3036 | 3180 | 2011-10-11 | 2012-11-26 | 2011-05-26 | 2012-11-09 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATION | WACC073020 | 20TH AIR SUPPORT OPERATIONS SQUADRON COMPLEX | 2010-10-21 | 2011-07-29 | Vetco Contracting Services, LLC | 15197 | 15223 | 2011-08-09 | 2013-02-15 | 2012-07-13 | 2013-02-15 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF012002 | CONTROL TOWER/BASE OPERATIONS FACILITY | 2010-11-23 | 2011-06-06 | Mason & Hanger, Inc. | 14560 | 14793 | 2011-08-15 | 2013-07-05 | 2012-05-01 | 2013-07-26 | 80 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | OK | OKLAHOMA | TINKER AIR FORCE BASE | WWYK083003B | UPGRADE BUILDING 3001 INFRASTRUCTURE, PH III | 2010-10-07 | 2011-07-22 | Korte Construction Company, St Louis, MO | 12687 | 13230 | 2011-07-22 | 2013-01-19 | 2012-06-01 | 2013-01-17 | 100 | 269
2013-04-15 | 2011 | Air Force Active | Major construction | MU | OMAN | AL MUSANAH AB | AMAB110001 | AIRLIFT RAMP AND FUEL FACILITIES | 2011-11-03 | 2012-05-10 | American Int'l Contractors, Inc. (AICI) | 36782 | 37020 | 2012-06-04 | 2014-04-15 | 2011-12-31 | 2014-04-29 | 15 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | MU | OMAN | AL MUSANAH AB | AMAB110002 | PARALLEL TAXIWAY EXTENSION | 2012-01-19 | 2012-07-05 | American Int'l Contractors, Inc. | 19348 | 19415 | 2012-08-06 | 2014-05-01 | 2013-11-01 | 2014-05-05 | 19 | 44245
2013-04-15 | 2011 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA073006B | BLATCHFORD-PRESTON COMPLEX, PHASE III | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | 34177 | 34177 | 2012-03-26 | 2014-05-15 | 2013-03-31 | 2014-05-15 | 2 | 1390
2013-04-15 | 2011 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA113001 | THEATER COMMUNICATIONS FACILITY | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | 9913 | 9913 | 2012-05-02 | 2014-02-12 | 2012-12-21 | 2014-02-12 | 14 | 12000
2013-04-15 | 2011 | Air Force Active | Major construction | QA | QATAR | AL UDEID AB | ALUA113031 | MUNITIONS STORAGE AREA COMPLEX | 2011-12-21 | 2012-05-24 | American International Contractors, Inc | 42778 | 42778 | 2012-05-24 | 2014-01-14 | 2012-12-21 | 2014-01-14 | 55 | 49000
2013-04-15 | 2011 | Air Force Active | Major construction | SC | SOUTH CAROLINA | CHARLESTON AIR FORCE BASE | DKFX913001P1 | CIVIL ENGINEER COMPLEX (TFI) - PHASE 1 | 2011-01-20 | 2011-06-03 | Sauer, Inc. | 11649 | 12334 | 2011-06-03 | 2013-04-18 | 2013-03-08 | 2013-06-18 | 91 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | TX | TEXAS | DYESS AIR FORCE BASE | FNWZ103010 | C-130J ADD/ALTER FLIGHT SIMULATOR FACILITY | 2011-02-28 | 2012-01-24 | Federal Program Integrators, L | 4464 | 4489 | 2012-03-06 | 2013-06-14 | 2012-09-28 | 2013-06-14 | 70 | 777
2013-04-15 | 2011 | Air Force Active | Major construction | TX | TEXAS | FORT SAM HOUSTON | MPLS116414JB | ONE COMPANY FIRE STATION | 2011-01-21 | 2011-06-17 | Blackhawk Ventures, LLC | 4845 | 4923 | 2011-07-08 | 2013-04-16 | 2012-01-31 | 2013-04-16 | 98 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R3 | RECRUIT DORMITORIES PHASE 3 | 2010-12-06 | 2011-09-20 | Satterfield and Pontikes Construction (S&P) | 45885 | 46339 | 2011-11-01 | 2014-02-28 | 2012-12-28 | 2014-02-28 | 56 | 2000
2013-04-15 | 2011 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R3 | RECRUIT DORMITORIES PHASE 3 | 2010-12-06 | 2012-08-09 | PSI | 6887 | 6887 | 2011-11-01 | 2014-02-28 | 2012-12-28 | 2014-02-28 | 56 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737S2 | BMT SATELLITE CLASSROOMS/DINING FACILITY NO.2 | 2011-03-07 | 2011-07-08 | Kellogg Brown Root | 26018 | 26420 | 2011-08-29 | 2013-12-20 | 2013-06-30 | 2013-10-20 | 38 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS093737V | BMT VISITORS RECEPTION CENTER | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | 21500 | 21696 | 2011-09-30 | 2013-09-23 | 2011-07-01 | 2013-09-02 | 26 | 1369
2013-04-15 | 2011 | Air Force Active | Major construction | GB | UNITED KINGDOM | RAF MILDENHALL | QFQE063007 | EXTEND TAXIWAY ALPHA | 2011-03-14 | 2011-09-29 | BALFOUR BEATTY | 9900 | 9900 | 2012-01-30 | 2013-04-17 | 2013-02-28 | 2013-05-03 | 87 | -1559
2013-04-15 | 2011 | Air Force Active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | MUHJ063017 | F-22 ADD/ALTER HANGAR BAY LO/CR FACILITY - TFI | 2010-10-15 | 2011-06-16 | Leebcor Services, LLC | 6595 | 6656 | 2011-11-18 | 2013-02-11 | 2012-07-16 | 2013-02-11 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Major construction | WY | WYOMING | CAMP GUERNSEY | AFSPC053012 | NUCLEAR/SPACE SECURITY TACTICS TRAINING CENTER (NSSTTC) | 2010-10-13 | 2011-06-02 | R.C. Heath Construction Co. | 3854 | 4061 | 2011-06-29 | 2012-12-13 | 2012-09-21 | 2013-06-28 | 99 | 0
2013-04-15 | 2011 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ114127 | IMPROVE FAMILY HOUSING, PH 11 | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | 64622 | 64622 | 2012-05-07 | 2016-05-31 | 2014-12-01 | 2015-11-04 | 6 | 14598
2013-04-15 | 2011 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ114127 | IMPROVE FAMILY HOUSING, PH 11 | 2011-05-09 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan) *ArchTestDigs* | 50 | 50 | 2012-05-07 | 2016-05-31 | 2014-12-01 | 2015-11-04 | 6 | 0
2013-04-15 | 2011 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ114127 | IMPROVE FAMILY HOUSING, PH 11 | 2011-05-09 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT* | 72 | 72 | 2012-05-07 | 2016-05-31 | 2014-12-01 | 2015-11-04 | 6 | 0
2013-04-15 | 2011 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ114127 | IMPROVE FAMILY HOUSING, PH 11 | 2011-05-09 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | 319 | 319 | 2012-05-07 | 2016-05-31 | 2014-12-01 | 2015-11-04 | 6 | 0
2013-04-15 | 2011 | Air Force Active | Minor Construction | AF | AFGHANISTAN | BAGRAM AB | ATUH085082 | EMSG HEADQUARTERS AND TOWN HALL | 2012-01-31 | 2012-05-18 | CH2MHill | 998 | 998 | 2012-06-07 | 2013-06-27 | 2013-01-18 | 2013-06-27 | 51 | 1134
2013-04-15 | 2011 | Air Force Active | Minor Construction | AF | AFGHANISTAN | BAGRAM AB | BAGR113008 | OPERATIONS GROUP COMMAND AND CONTROL (C2) FACILITY | 2012-01-31 | 2012-05-18 | CH2MHill | 1618 | 1618 | 2012-06-07 | 2013-06-27 | 2013-01-18 | 2013-06-27 | 45 | 1838
2013-04-15 | 2011 | Air Force Active | Minor Construction | AF | AFGHANISTAN | BAGRAM AB | BAGR113010 | TACTICAL FIGHTER AMU | 2012-01-31 | 2012-05-18 | CH2MHill | 1306 | 1306 | 2012-06-07 | 2013-06-27 | 2013-01-18 | 2013-06-27 | 40 | 1650
2013-04-15 | 2011 | Air Force Active | Minor Construction | AF | AFGHANISTAN | BAGRAM AB | BAGR113011 | TACTICAL FIGHTER SQUAD OPS | 2012-01-31 | 2012-05-18 | CH2MHill | 1578 | 1578 | 2012-06-07 | 2013-05-27 | 2013-01-18 | 2013-05-27 | 51 | 1792
2013-04-15 | 2011 | Air Force Active | Minor Construction | AF | AFGHANISTAN | BAGRAM AB | BAGR113022 | FLIGHT LINE FIRE STATION | 2012-01-31 | 2012-05-18 | CH2M Hill | 1519 | 1519 | 2012-06-07 | 2013-06-27 | 2013-01-18 | 2013-06-27 | 37 | 1725
2013-04-15 | 2011 | Air Force Active | Minor Construction | AF | AFGHANISTAN | KANDAHAR AB | LYAV100026 | 451 AEW SCIF | 2012-01-02 | 2012-03-15 | Entire-Ashna-Vertex JV | 871 | 871 | 2012-04-14 | 2013-05-14 | 2012-07-13 | 2013-05-14 | 80 | 1719
2013-04-15 | 2011 | Air Force Active | Minor Construction | FL | FLORIDA | HURLBURT FIELD | FTEV063000 | SOF SQUADRON OPERATIONS ANNEX, 4 SOS | 2011-03-25 | 2011-06-23 | DWG & Associates | 1629 | 1698 | 2011-07-25 | 2012-12-18 | 2012-11-20 | 2013-02-22 | 100 | 0
2013-04-15 | 2011 | Air Force Active | Minor Construction | FL | FLORIDA | HURLBURT FIELD | FTEV083015 | RELOCATE FAMILY CAMPING FACILITY | 2012-02-16 | 2012-06-15 | Green Simmons | 1870 | 1961 | 2012-07-09 | 2013-03-16 | 2013-03-29 | 2013-03-29 | 84 | 1975
2013-04-15 | 2011 | Air Force Active | Minor Construction | GA | GEORGIA | MOODY AIR FORCE BASE | QSEU090402 | ADAL HC-130J AERIAL DELIVERY/LOGISTICS FACILITY | 2012-04-26 | 2012-07-05 | USCS | 1716 | 1716 | 2012-07-19 | 2012-11-30 | 2012-12-21 | 2013-05-01 | 77 | 1968
2013-04-15 | 2011 | Air Force Active | Minor Construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ113001R1 | CONVERT BLDG 660 TO C-17 COMBINED PROGRAM OFFICE | 2011-09-29 | 2011-12-08 | MAPCO, INC. | 938 | 978 | 2011-12-20 | 2012-06-15 | 2012-06-20 | 2012-10-25 | 100 | 1700
2013-04-15 | 2011 | Air Force Active | Minor Construction | GM | GERMANY | SPANGDAHLEM AIR BASE | VYHK113003 | CATCH BASIN FOR WASTE WATER TREATMENT | 2012-03-30 | 2012-07-31 | UVB BITBURG | 1762 | 1762 | 2012-08-15 | 2013-09-30 | 2013-09-15 | 2013-09-15 | 25 | 1762
2013-04-15 | 2011 | Air Force Active | Minor Construction | ID | IDAHO | MOUNTAIN HOME AIR FORCE BASE | QYZH090057 | RELOCATE ARRESTING SYSTEMS, RUNWAYS 12 & 30 | 2013-04-12 | 2012-05-25 | North Wind Services | 2145 | 2145 | 2012-06-05 | 2012-12-10 | 2012-08-31 | 2012-08-31 | 70 | 2284
2013-04-15 | 2011 | Air Force Active | Minor Construction | KU | KUWAIT | ALI AL SALEM AB | AEWV111136 | SEWAGE TREATMENT SYSTEM | 2012-08-29 | 2013-01-09 | ARABI CO. W.L.L. | 1592 | 1592 | 2013-02-21 | 2014-01-31 | 2013-08-15 | 2014-01-31 | 1 | 1788
2013-04-15 | 2011 | Air Force Active | Minor Construction | KG | KYRGYZSTAN | MANAS TRANSIT CENTER | NZYY110190 | AIR FREIGHT FACILITY | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 926 | 926 | 2011-12-19 | 2013-08-30 | 2013-02-28 | 2013-08-30 | 62 | 1041
2013-04-15 | 2011 | Air Force Active | Minor Construction | KG | KYRGYZSTAN | MANAS TRANSIT CENTER | NZYY110200 | AERIAL PORT C2 FACILITY | 2011-08-01 | 2011-12-19 | Nileco General Contracting/Bishkek/Kyrgyzstan | 1282 | 1282 | 2011-12-19 | 2013-08-30 | 2013-02-28 | 2013-08-30 | 64 | 1440
2013-04-15 | 2011 | Air Force Active | Minor Construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF113020 | MEDICAL EDUCATION & TRAINING FACILITY REPLACEMENT | 2012-03-01 | 2012-05-31 | Synergy Systems Inc | 1698 | 1698 | 2012-08-14 | 2013-09-30 | 2013-04-17 | 2013-11-27 | 13 | 0
2013-04-15 | 2011 | Air Force Active | Minor Construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD110006A | CONSTRUCT CDC ADDITION, B650 | 2011-06-20 | 2011-08-11 | MODULAR MANAGEMENT GROUP, INC | 600 | 600 | 2011-08-30 | 2013-05-28 | 2012-09-12 | 2013-05-28 | 42 | 0
2013-04-15 | 2011 | Air Force Active | Minor Construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113004 | F-16 HYDRAZINE FACILITY | 2011-10-21 | 2012-02-08 | ITSI | 1689 | 1689 | 2012-02-27 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 90 | 1800
2013-04-15 | 2011 | Air Force Active | Minor Construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV113101 | P-341 ADD COMPOSITES REPAIR SHOP TO CORROSION CONTROL FACILITY | 2011-08-12 | 2011-09-23 | K.L. House | 1351 | 1375 | 2011-11-09 | 2013-09-09 | 2012-10-31 | 2013-07-31 | 97 | 1699
2013-04-15 | 2011 | Air Force Active | Minor Construction | AE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF080145 | INFORMATION TRANSFER NODE | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 1074 | 1074 | 2012-10-03 | 2013-10-01 | 2012-10-30 | 2013-10-01 | 10 | 1318
2013-04-15 | 2011 | Air Force Active | Minor Construction | AE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF105000 | DINING FACILITY | 2012-04-06 | 2012-07-31 | C Davis and Associates | 1004 | 1004 | 2012-10-03 | 2013-10-01 | 2012-09-01 | 2013-10-01 | 10 | 1233
2013-04-15 | 2011 | Air Force Active | Minor Construction | AE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF110018 | EMSG HQ | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 1007 | 1007 | 2012-10-03 | 2013-10-01 | 2012-09-10 | 2013-10-01 | 10 | 1236
2013-04-15 | 2011 | Air Force Active | Minor Construction | AE | UNITED ARAB EMIRATES | AL DHAFRA AB | DHAF110019 | KENNEL | 2012-04-06 | 2012-07-31 | C. Davis and Associates | 583 | 583 | 2012-10-03 | 2013-10-01 | 2012-09-10 | 2013-10-01 | 10 | 716
2013-04-15 | 2011 | Air National Guard | Major construction | AL | ALABAMA | MONTGOMERY REGIONAL AIRPORT (ANG) BASE | FAKZ959574 | FUEL CELL AND CORROSION CONTROL HANGAR | 2011-03-15 | 2011-07-22 | Lord and Son Constrution, Inc | 7249 | 7477 | 2011-10-12 | 2013-06-28 | 2013-01-22 | 2013-06-28 | 72 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV089069 | TFI - PREDATOR FOC – INCREASED MISSION ORBIT TASKING | 2011-05-13 | 2011-07-29 | Komada, LLC | 3761 | 4037 | 2011-09-08 | 2012-12-17 | 2012-09-07 | 2013-03-15 | 100 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | AZ | ARIZONA | FORT HUACHUCA | HFHA069130 | TFI - PREDATOR LRE BEDDOWN | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | 9434 | 10056 | 2013-04-08 | 2014-07-02 | 2014-06-02 | 2014-06-02 | 0 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | DE | DELAWARE | NEW CASTLE COUNTY AIRPORT | JLWS079103 | JOINT FORCES OPERATIONS CENTER - ANG SHARE | 2011-06-29 | 2011-09-16 | Vigil Contracting, Inc. | 1134 | 1164 | 2011-12-12 | 2013-03-22 | 2013-06-09 | 2013-03-22 | 60 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | FL | FLORIDA | JACKSONVILLE INTERNATIONAL AIRPORT | LSGA029009A | SECURITY FORCES TRAINING FACILITY | 2010-11-12 | 2011-06-06 | Americaan Patriot Construction -IMajor Constructionruction, LLC | 3909 | 4156 | 2011-08-05 | 2013-02-22 | 2012-12-03 | 2013-02-22 | 95 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU069150 | RELOCATE ASOS FACILITIES | 2011-04-20 | 2011-06-29 | Choice Concrete Construction LLC | 5962 | 6687 | 2011-08-01 | 2012-08-20 | 2012-07-28 | 2013-04-15 | 99 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069209 | TFI - F-22 HANGAR, SQUADRON OPERATIONS AND AMU | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | 37110 | 42076 | 2011-07-15 | 2013-07-05 | 2013-07-14 | 2013-07-05 | 87 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069215 | TFI - F-22 UPGRADE MUNITIONS COMPLEX | 2012-01-11 | 2012-05-24 | Nan Inc. | 17142 | 19378 | 2012-06-14 | 2013-12-11 | 2013-12-11 | 2013-12-11 | 49 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109500 | TFI - F-22 BEDDOWN INFRASTRUCTURE SUPPORT | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | 5155 | 6449 | 2011-08-15 | 2013-08-14 | 2013-07-14 | 2013-08-14 | 84 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | IL | ILLINOIS | ABRAHAM LINCOLN CAPITAL AIRPORT | DCFT069059 | TFI - CNAF BEDDOWN - UPGRADE FACILITIES | 2010-12-15 | 2012-04-26 | JM Industrial Supply, Inc. | 13733 | 15347 | 2012-06-01 | 2013-12-31 | 2013-03-20 | 2014-01-08 | 59 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | IN | INDIANA | HULMAN REGIONAL AIRPORT | LDXF069123 | TFI - ASOS BEDDOWN - UPGRADE FACILITIES | 2011-03-08 | 2011-06-13 | Hannig Construction | 3571 | 3674 | 2011-07-07 | 2012-09-04 | 2012-07-06 | 2012-10-31 | 95 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | MD | MARYLAND | MARTIN STATE AIRPORT | PJMS909928 | REPLACE OPERATIONS AND MEDICAL TRAINING FACILITY | 2011-08-17 | 2011-09-28 | Costello Construction of MD, Inc. | 11802 | 12448 | 2012-07-20 | 2014-03-31 | 2013-10-18 | 2014-03-31 | 45 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | NY | NEW YORK | FORT DRUM MILITARY RESERVATION | FPBB109013 | TFI - REAPER INFRASTRUCTURE SUPPORT | 2012-07-27 | 2012-10-17 | Black Horse Group | 2040 | 2131 | 2012-10-17 | 2014-04-26 | 2013-10-12 | 2014-04-26 | 10 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | NY | NEW YORK | STEWART INTERNATIONAL AIRPORT | WHAY089079 | BASE DEFENSE GROUP BEDDOWN | 2011-07-30 | 2011-09-23 | APS Contractors Inc | 13401 | 14152 | 2011-10-13 | 2014-08-29 | 2013-05-05 | 2014-08-29 | 35 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | NC | NORTH CAROLINA | STANLY COUNTY AIRPORT | WEFM089029 | UPGRADE ASOS FACILITIES | 2011-04-19 | 2011-08-26 | DOT Construction | 1660 | 1873 | 2011-10-24 | 2013-03-22 | 2012-07-21 | 2013-03-29 | 98 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | PA | PENNSYLVANIA | STATE COLLEGE ANG STATION | WFGE089076 | ADD TO AND ALTER AOS FACILITY | 2010-04-16 | 2011-08-25 | HSCC | 3903 | 4222 | 2011-08-25 | 2012-11-27 | 2012-08-24 | 2013-05-01 | 99 | 0
2013-04-15 | 2011 | Air National Guard | Major construction | TX | TEXAS | ELLINGTON FIELD | FWJH069194 | TFI - ALTER UAV MAINTENANCE HANGAR (BLDG 1382) | 2012-01-06 | 2012-06-14 | LeeTex Construction | 5038 | 5619 | 2012-07-23 | 2014-01-22 | 2013-07-23 | 2013-09-01 | 50 | 0
2013-04-15 | 2011 | Air National Guard | Minor Construction | CA | CALIFORNIA | MOFFETT FIELD (NASA), SAN JOSE, (ANG) | QMSN099051 | FORCE PROTECTION MEASURES - RELOCATE MAIN GATE | 2011-11-04 | 2012-02-09 | Herrera Corporation | 1875 | 1952 | 2011-03-02 | 2013-01-07 | 2011-08-29 | 2013-02-04 | 99 | 0
2013-04-15 | 2011 | Air National Guard | Minor Construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU119021 | RELOCATE TAXIWAY JULIET | 2012-06-22 | 2012-08-23 | JE Hurley Construction, Inc. | 1824 | 1918 | 2012-09-12 | 2013-04-07 | 2013-03-01 | 2013-05-14 | 96 | 0
2013-04-15 | 2011 | Air National Guard | Minor Construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD109032 | TFI- F-22 BEDDOWN- ADD TO COMMUNICATION FACILITY | 2012-01-04 | 2012-06-12 | HAKO PLUMBING, INC. | 1695 | 1844 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 20 | 0
2013-04-15 | 2011 | Air National Guard | Minor Construction | WY | WYOMING | CHEYENNE REGIONAL AIRPORT | DPEZ089083 | RELOCATE ROSC | 2011-07-18 | 2012-04-11 | Recco, Inc. | 1636 | 1988 | 2012-04-25 | 2012-12-31 | 2012-10-22 | 2012-12-31 | 90 | 0
2013-04-15 | 2011 | Air Force Reserves | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT043000 | WEAPONS MAINTENANCE FACILITY | 2011-05-20 | 2011-07-22 | S&M and Associates, Inc./Pascagoula MS | 2937 | 3006 | 2011-10-03 | 2013-01-25 | 2012-05-25 | 2013-01-25 | 100 | 0
2013-04-15 | 2011 | Air Force Reserves | Minor Construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ103007 | UTILITY AND INFRASTRUCTURE SUPPORT FOR TEMPORARY FACILITIES | 2011-03-01 | 2011-09-29 | First Choice Gov | 1791 | 1791 | 2011-10-28 | 2012-06-15 | 2012-04-25 | 2012-04-25 | 90 | 1947
2013-04-15 | 2012 | Air Force Active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | BRIGADE COMBAT TEAM (LIGHT) COMPLEX, (480 RM) | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | 53805 | 53988 | 2012-06-19 | 2014-08-12 | 2013-11-20 | 2014-08-12 | 10 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | BRIGADE COMBAT TEAM (LIGHT) COMPLEX, (480 RM) | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | 3230 | 3230 | 2012-06-19 | 2014-08-12 | 2013-11-20 | 2014-08-12 | 10 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | BRIGADE COMBAT TEAM (LIGHT) COMPLEX, (480 RM) | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | 4979 | 4979 | 2012-06-19 | 2014-08-12 | 2013-11-20 | 2014-08-12 | 10 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | BRIGADE COMBAT TEAM (LIGHT) COMPLEX, (480 RM) | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | 1874 | 2192 | 2012-06-19 | 2014-08-12 | 2013-11-20 | 2014-08-12 | 10 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AK | ALASKA | ELMENDORF AIR FORCE BASE | FXSB061561 | BRIGADE COMBAT TEAM (LIGHT) COMPLEX, (480 RM) | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | 1799 | 1799 | 2012-06-19 | 2014-08-12 | 2013-11-20 | 2014-08-12 | 10 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV103006P1 | EC-130H SIMULATOR/TRAINING OPERATIONS | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | 14348 | 14348 | 2013-02-05 | 2014-12-27 | 2013-10-07 | 2014-12-27 | 2 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | FBNV123002 | HC-130J JOINT USE FUEL CELL | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | 12361 | 12361 | 2012-10-31 | 2014-03-07 | 2014-04-28 | 2014-04-28 | 3 | 1256
2013-04-15 | 2012 | Air Force Active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | AETC120010 | F-35 ADAL AIRCRAFT MAINTENANCE UNIT | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | 4781 | 4793 | 2012-10-09 | 2013-12-10 | 2012-11-30 | 2014-01-26 | 22 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AZ | ARIZONA | LUKE AIR FORCE BASE | AETC120011 | F-35 SQUAD OPS/AMU 2 | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | 12359 | 12359 | 2013-10-08 | 2014-09-19 | 2012-11-30 | 2014-12-06 | 1 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK111089A | EMERGENCY PERMANENT REPAIR HANGAR 245 | 2012-04-06 | 2012-07-11 | Blackhawk Ventures, LLC | 2404 | 2404 | 2012-08-28 | 2013-08-27 | 2014-04-25 | 2013-06-28 | 30 | 2727
2013-04-15 | 2012 | Air Force Active | Major construction | AR | ARKANSAS | LITTLE ROCK AIR FORCE BASE | NKAK133004 | EMERGENCY PEST MANAGEMENT FACILITY | 2012-04-30 | 2012-08-14 | Guyco, Inc. | 1452 | 1452 | 2012-09-25 | 2013-11-24 | 2014-06-16 | 2013-09-25 | 18 | 1702
2013-04-15 | 2012 | Air Force Active | Major construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | XDAT083003 | DORMITORY (144 RM) | 2011-12-22 | 2012-05-11 | Barnhart-Balfour-Beatty, Inc; San Diego CA | 18492 | 18588 | 2012-06-11 | 2013-11-04 | 2013-11-11 | 2013-11-11 | 18 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | CA | CALIFORNIA | VANDENBERG AIR FORCE BASE | XUMU033002 | EDUCATION CENTER | 2011-12-13 | 2012-02-28 | TEEHEE-STRAUB JV | 13185 | 13398 | 2012-03-29 | 2013-11-12 | 2013-08-23 | 2013-11-12 | 26 | 693
2013-04-15 | 2012 | Air Force Active | Major construction | CO | COLORADO | USAF ACADEMY | XQPZ044003 | CONST VEHICLE SEARCH FACILITY | 2011-11-18 | 2012-03-30 | Komada LLC | 5941 | 5763 | 2012-05-01 | 2013-12-28 | 2013-12-15 | 2013-10-28 | 21 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | DE | DELAWARE | DOVER AIR FORCE BASE | FJXT123000 | C-5M FORMAL TRAINING UNIT FACILITY | 2011-11-14 | 2012-05-07 | Eastern Sun Enterprises, Incorporated | 2085 | 2085 | 2012-06-12 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 5 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | FL | FLORIDA | HURLBURT FIELD | FTEV103011 | SOF SIMULATOR FACILITY | 2012-05-31 | 2012-08-09 | Barlovento, LLC | 5391 | 5408 | 2012-09-13 | 2014-02-05 | 2014-02-05 | 2014-02-07 | 19 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | FL | FLORIDA | PATRICK AIR FORCE BASE | SXHT053001A | AIR FORCE TECHNICAL APPLICATIONS CENTER | 2011-09-30 | 2012-02-24 | Hensel Phelps | 70613 | 71625 | 2012-02-24 | 2014-01-31 | 2015-12-02 | 2015-12-02 | 50 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GM | GERMANY | RAMSTEIN AIR BASE | TYFR063017 | DORMITORY (192 RM) | 2013-10-12 | 2012-05-24 | LBB (EBC AWD) | 29542 | 29542 | 2014-03-31 | 2015-11-16 | 2015-03-02 | 2015-09-15 | 1 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GM | GERMANY | US AIR FORCES, EUROPE | USAFE17001 | AIRCRAFT APRON/TAXIWAY AND MAINTENANCE SHELTERS | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | 6740 | 6811 | 2012-05-02 | 2013-07-22 | 2013-02-03 | 2013-07-22 | 84 | 8177
2013-04-15 | 2012 | Air Force Active | Major construction | GM | GERMANY | US AIR FORCES, EUROPE | USAFE17002 | COMBAT AIRCRAFT LOADING AREA | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | 43421 | 43421 | 2012-10-01 | 2014-01-16 | 2014-01-16 | 2014-01-16 | 9 | 154000
2013-04-15 | 2012 | Air Force Active | Major construction | GM | GERMANY | US AIR FORCES, EUROPE | USAFE17003 | PARALLEL TAXIWAY EXTENSION | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | 10522 | 10522 | 2012-10-01 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 9 | 24000
2013-04-15 | 2012 | Air Force Active | Major construction | GM | GERMANY | US AIR FORCES, EUROPE | USAFE17004 | EXPEDITIONARY LODGING | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | 26588 | 26588 | 2012-10-20 | 2014-03-15 | 2013-09-30 | 2014-03-21 | 16 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GL | GREENLAND | THULE AIR BASE | WWCX103033 | DORMITORY (72 PN) | 2011-12-05 | 2012-05-11 | MTHojgaard | 27936 | 27555 | 2012-06-06 | 2014-11-26 | 2014-12-26 | 2014-12-26 | 15 | 2000
2013-04-15 | 2012 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY123009 | GUAM STRIKE - CLEAR WATER RINSE FACILITY | 2011-11-15 | 2012-04-21 | Niking Corporation | 6739 | 6739 | 2012-06-11 | 2013-10-17 | 2013-12-30 | 2013-10-17 | 15 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY123011 | GUAM STRIKE COVENTIONAL MUNITION MAINTENANCE FACILITY | 2011-11-22 | 2012-04-27 | P & S Construction | 9527 | 9527 | 2012-05-11 | 2014-07-19 | 2014-07-19 | 2014-07-19 | 23 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY123011 | GUAM STRIKE COVENTIONAL MUNITION MAINTENANCE FACILITY | 2011-11-22 | 2012-05-29 | Navy Crane Center | 59 | 59 | 2012-05-11 | 2014-07-19 | 2014-07-19 | 2014-07-19 | 23 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | AJJY983202 | AIR FREIGHT TERMINAL COMPLEX | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | 30047 | 31707 | 2012-07-18 | 2014-10-16 | 2014-03-31 | 2014-10-16 | 5 | 674
2013-04-15 | 2012 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | SAKW059101 | PRTC - RED HORSE CANTONMENT OPERATIONS FACILITY | 2011-12-30 | 2012-04-27 | Pacific West Builders | 9491 | 9491 | 2012-05-14 | 2013-10-07 | 2013-10-07 | 2013-10-07 | 23 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | SAKW091002 | PRTC - COMBAT COMMUNICATIONS TRANSMISSION SYSTEMS FACILITY | 2011-11-28 | 2012-04-27 | Guam Pacific International | 3960 | 3960 | 2012-05-14 | 2013-11-02 | 2013-11-02 | 2013-11-02 | 20 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | GQ | GUAM | ANDERSEN AIR FORCE BASE | SAKW101001 | PRTC - COMBAT COMMUNICATIONS COMBAT SUPPORT FACILITY | 2011-11-28 | 2012-04-27 | Guam Pacific International | 6212 | 6212 | 2012-05-14 | 2013-11-02 | 2013-11-02 | 2013-11-02 | 20 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | IT | ITALY | AVIANO AIR BASE | ASHE163000 | CHILD DEVELOPMENT CENTER ADDITION | 2012-06-06 | 2012-09-30 | Collodetto Angelo Costruzioni | 890 | 890 | 2012-09-30 | 2014-01-29 | 2014-06-01 | 2013-11-25 | 2 | 1900
2013-04-15 | 2012 | Air Force Active | Major construction | KS | KANSAS | FT RILEY | HACC123302 | AIR SUPPORT OPERATIONS CENTER | 2011-12-05 | 2012-05-01 | Vengas Engineering Management & Const, Inc. | 5475 | 5529 | 2012-05-14 | 2013-08-20 | 2013-06-28 | 2013-06-21 | 62 | -1483
2013-04-15 | 2012 | Air Force Active | Major construction | KR | KOREA | OSAN AIR BASE | SMYU123002 | DORMITORY (156 RM) | 2011-09-05 | 2012-03-13 | Seohee Construction Co., Ltd. | 14839 | 14917 | 2012-03-14 | 2014-04-30 | 2014-04-30 | 2014-03-01 | 17 | -2674
2013-04-15 | 2012 | Air Force Active | Major construction | LA | LOUISIANA | BARKSDALE AIR FORCE BASE | AWUB105002 | MISSION SUPPORT GROUP COMPLEX | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | 17998 | 17998 | 2012-03-26 | 2013-12-17 | 2013-06-17 | 2013-12-17 | 30 | -3184
2013-04-15 | 2012 | Air Force Active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG071005 | WSA SECURITY CONTROL FACILITY | 2011-11-23 | 2012-02-27 | Carlson Constructors | 4173 | 4173 | 2012-03-16 | 2013-11-06 | 2012-10-16 | 2013-11-06 | 14 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG111005 | FORCE SUPPORT SQUADRON FACILITY | 2012-06-01 | 2012-08-23 | Titan Construction Organizatio | 5388 | 5388 | 2012-09-07 | 2013-09-09 | 2013-09-09 | 2013-09-09 | 30 | 5997
2013-04-15 | 2012 | Air Force Active | Major construction | NE | NEBRASKA | OFFUTT AIR FORCE BASE | SGBP100904C | USSTRATCOM REPLACEMENT FACILITY - INCR 1 | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | 102754 | 102911 | 2012-09-11 | 2016-01-15 | 2016-02-15 | 2016-09-09 | 2 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103001 | F-35A AGE FACILITY | 2011-11-17 | 2012-06-01 | R.L. Reed, Inc. | 11097 | 11215 | 2012-06-19 | 2014-06-15 | 2013-07-15 | 2014-06-15 | 25 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103003 | COMMUNICATIONS NETWORK CONTROL CENTER | 2011-11-17 | 2012-04-24 | A4 Construction | 9327 | 9515 | 2012-05-22 | 2014-01-13 | 2013-03-15 | 2013-11-13 | 36 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NV | NEVADA | NELLIS AIR FORCE BASE | RKMF103010 | F-35 ADD/ALTER ENGINE SHOP | 2011-11-17 | 2012-05-24 | Au Authum KI, Inc | 1867 | 1867 | 2012-08-03 | 2013-09-15 | 2013-06-15 | 2013-09-15 | 2 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073014 | SOF C-130 SQUADRON OPERATIONS FACILITY | 2012-06-13 | 2012-10-26 | Bradbury Stamm Construction | 7413 | 7413 | 2012-11-29 | 2014-05-30 | 2014-12-09 | 2014-02-24 | 8 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073018 | SOF C-130 WASH RACK HANGAR | 2012-06-05 | 2012-08-27 | SOLIS CONSTRUCTORS INC. | 9329 | 9329 | 2012-11-16 | 2014-06-18 | 2014-04-10 | 2014-04-10 | 7 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ073021 | SOF AMXS FACILITY | 2012-06-06 | 2012-09-13 | K.L. House Construction | 14700 | 14700 | 2013-02-25 | 2014-09-22 | 2014-08-08 | 2014-08-08 | 2 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ123001 | DORMITORY (96 RM) | 2012-06-13 | 2012-08-31 | USACE | 12463 | 12537 | 2012-09-26 | 2014-03-07 | 2013-07-31 | 2014-02-10 | 21 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | CANNON AIR FORCE BASE | CZQZ133001 | ADAL WASTEWATER TREATMENT PLANT | 2012-04-26 | 2012-07-11 | KEAR Civil Corporation | 7787 | 7787 | 2012-09-11 | 2014-02-03 | 2013-12-31 | 2013-11-04 | 51 | 1083
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD013003 | CHILD DEVELOPMENT CENTER | 2012-05-18 | 2012-08-17 | Turner Atlantic Construction | 9844 | 9844 | 2012-11-08 | 2014-07-11 | 2012-06-15 | 2014-07-11 | 3 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD083007 | PARALLEL TAXIWAY, RWY 07/25 | 2012-03-15 | 2012-06-08 | Mesa Verde Enterprises, Inc. | 6349 | 6349 | 2012-07-02 | 2013-07-19 | 2013-04-05 | 2013-07-19 | 11 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113005 | F-16 ACADEMIC TRAINING FACILITY | 2012-02-03 | 2012-06-13 | White Sands Construction | 4990 | 4990 | 2012-07-09 | 2013-12-02 | 2013-07-12 | 2013-12-02 | 13 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | HOLLOMAN AIR FORCE BASE | KWRD113010 | F-16 SEAD TRAINING FACILITY | 2012-02-03 | 2012-06-13 | White Sands Construction | 3614 | 3614 | 2012-07-09 | 2013-12-02 | 2013-02-04 | 2013-12-02 | 13 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | MHMV093108 | AFNWC SUSTAINMENT CENTER | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | 21110 | 21110 | 2012-07-09 | 2014-08-08 | 2014-08-08 | 2014-08-08 | 7 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NC | NORTH CAROLINA | POPE AIR FORCE BASE | TMKH043055 | SOF TRAINING FACILITY DET 1 | 2012-02-02 | 2012-04-24 | JAAAT Technical Services, LLC | 5496 | 5496 | 2012-05-31 | 2014-01-21 | 2013-10-31 | 2013-11-22 | 29 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | NC | NORTH CAROLINA | POPE AIR FORCE BASE | TMKH083003 | C-130 FLIGHT SIMULATOR | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | 4630 | 4630 | 2012-07-24 | 2013-12-04 | 2013-12-31 | 2013-12-31 | 12 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092001 | DORMITORY (168 RM) | 2011-11-15 | 2012-02-14 | Graham Construction | 17775 | 17795 | 2012-03-21 | 2013-09-25 | 2013-08-08 | 2014-03-11 | 59 | -2049
2013-04-15 | 2012 | Air Force Active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092010 | B-52 3-BAY CONVENTIONAL MUNITIONS MTC FACILITY | 2012-01-24 | 2012-05-03 | Creative Times, Inc. | 10490 | 10734 | 2012-05-31 | 2014-04-21 | 2013-08-01 | 2014-04-21 | 10 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF092012 | B-52 TWO-BAY PHASE MAINTENANCE DOCK | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | 32123 | 32112 | 2012-05-22 | 2014-10-09 | 2014-02-11 | 2014-10-09 | 8 | 1813
2013-04-15 | 2012 | Air Force Active | Major construction | TX | TEXAS | JOINT BASE FT SAM HOUSTON | MPLS11473JB | ADVANCE INDIVIDUAL TRAINEE (AIT) BARRACKS (300 RM) | 2011-12-15 | 2012-03-30 | Hensel-Phelps Constr. Co. | 34889 | 35007 | 2012-07-20 | 2014-03-14 | 2014-08-05 | 2014-03-14 | 70 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | TX | TEXAS | LACKLAND AIR FORCE BASE | MPLS083737R4 | BMT RECRUIT DORMITORY, PHASE IV | 2011-12-16 | 2012-07-17 | SpawGlass Contractors, Inc. | 50529 | 50951 | 2012-11-26 | 2015-03-26 | 2013-10-01 | 2014-11-02 | 2 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | UT | UTAH | HILL AIR FORCE BASE | KRSM123011R | F-22 SYSTEM SUPPORT FACILITY | 2011-12-09 | 2012-06-05 | Creative Times Inc | 9598 | 9598 | 2012-07-24 | 2014-02-20 | 2013-12-05 | 2014-06-05 | 10 | -4155
2013-04-15 | 2012 | Air Force Active | Major construction | VA | VIRGINIA | LANGLEY AIR FORCE BASE | WACC120007 | AIT BARRACKS COMPLEX, PH 2 | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | 33915 | 33915 | 2012-10-12 | 2014-04-30 | 2014-04-01 | 2014-05-30 | 7 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ860009 | WING HEADQUARTERS | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | 11957 | 12216 | 2012-05-21 | 2014-06-24 | 2014-01-15 | 2014-09-25 | 10 | 0
2013-04-15 | 2012 | Air Force Active | Major construction | WA | WASHINGTON | FAIRCHILD AIR FORCE BASE | GJKZ920012P2 | SERE FORCE SUPPORT COMPLEX, PHASE 2 | 2011-11-21 | 2012-07-05 | Total Site Services/Garco | 11724 | 11776 | 2012-07-20 | 2014-03-13 | 2014-05-20 | 2014-06-15 | 3 | 0
2013-04-15 | 2012 | Air Force Active | MFH improvement | JA | JAPAN | KADENA AIR BASE | LXEZ124285 | IMPROVE FAMILY HOUSING INFRASTRUCTURE, PH 1 | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | 17707 | 17707 | 2013-06-02 | 2013-12-01 | 2014-03-01 | 2014-03-01 | 1 | 15000
2013-04-15 | 2012 | Air Force Active | MFH improvement | JA | JAPAN | MISAWA AIR BASE | QKKA124002 | IMPROVE MFH INFRASTRUCTURE, PHASE 1 | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | 19550 | 19550 | 2012-06-11 | 2014-11-13 | 2014-11-13 | 2014-11-13 | 6 | -78
2013-04-15 | 2012 | Air Force Active | Minor Construction | CO | COLORADO | BUCKLEY AIR FORCE BASE | CRWU123005 | PL-1 ENTRY CONTROL FACILITY | 2013-01-31 | 2013-04-04 | Hartland/Mass JV | 1125 | 1125 | 2013-05-27 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 1 | 1800
2013-04-15 | 2012 | Air Force Active | Minor Construction | FL | FLORIDA | TYNDALL AIR FORCE BASE | XLWU121019 | F-22 ADAL DEPLOYMENT PROCESSING CENTER | 2012-06-13 | 2012-09-20 | MTNT Properties, Inc | 1890 | 1890 | 2012-10-04 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 8 | 1985
2013-04-15 | 2012 | Air Force Active | Minor Construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ110047 | ADAL CORROSION CONTROL HANGAR (BLDG 89) | 2012-06-25 | 2012-11-21 | GSC Construction, Inc. | 1831 | 1831 | 2013-04-15 | 2013-11-10 | 2013-10-20 | 2013-11-17 | 1 | 3989
2013-04-15 | 2012 | Air Force Active | Minor Construction | GA | GEORGIA | ROBINS AIR FORCE BASE | UHHZ110048 | ADAL CORROSION CONTROL HANGAR (BLDG 54) | 2012-06-25 | 2012-11-21 | GSC Construction, Inc. | 1819 | 1819 | 2013-04-18 | 2013-12-15 | 2013-12-22 | 2013-12-22 | 1 | 1923
2013-04-15 | 2012 | Air Force Active | Minor Construction | IN | INDIANA | GRISSOM AIR RESERVE BASE | CTGB102040 | ADDITION TO BOWST SIMULATOR | 2012-04-23 | 2012-08-03 | ITSI | 1031 | 1031 | 2012-08-06 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 35 | 1031
2013-04-15 | 2012 | Air Force Active | Minor Construction | NJ | NEW JERSEY | MAJOR CONSTRUCTIONGUIRE AIR FORCE BASE | PTFL106001 | CONSTRUCT COVERED STORAGE | 2012-06-22 | 2012-09-10 | Complete Technical Inc | 1295 | 1295 | 2012-06-26 | 2013-12-30 | 2013-12-30 | 2013-12-30 | 74 | 1295
2013-04-15 | 2012 | Air Force Active | Minor Construction | ND | NORTH DAKOTA | MINOT AIR FORCE BASE | QJVF123101 | ADDITION TO HIGH FIDELITY TRAINER | 2012-07-16 | 2012-09-11 | Ainsworth-Benning of Wyoming, | 1639 | 1639 | 2013-05-20 | 2013-10-18 | 2013-10-20 | 2013-10-20 | 1 | 1639
2013-04-15 | 2012 | Air Force Active | Minor Construction | TX | TEXAS | SHEPPARD AIR FORCE BASE | VNVP113003 | UPGRADE METALS TRAINING FACILITY | 2012-06-29 | 2012-09-19 | Koht'aene Enterprises Co (KEC) | 1722 | 1722 | 2012-10-03 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 90 | 1722
2013-04-15 | 2012 | Air Force Active | Minor Construction | UT | UTAH | HILL AIR FORCE BASE | KRSM123015 | CONSTRUCT HAYMAN TYPE IGLOO | 2012-10-15 | 2013-01-15 | Hal Hays Construction, Inc. | 1055 | 1055 | 2013-02-04 | 2014-04-30 | 2014-04-28 | 2014-04-30 | 2 | 1190
2013-04-15 | 2012 | Air National Guard | Major construction | CA | CALIFORNIA | BEALE AIR FORCE BASE | BAEY029154 | WING OPERATIONS AND TRAINING FACILITY | 2012-07-27 | 2012-09-26 | SM Construction | 4960 | 5269 | 2012-12-03 | 2014-05-01 | 2013-12-03 | 2014-05-01 | 6 | 0
2013-04-15 | 2012 | Air National Guard | Major construction | CA | CALIFORNIA | MOFFETT FIELD (NASA), SAN JOSE, (ANG) | QMSN019029 | REPLACE PARARESCUE TRAINING FACILITY | 2012-08-05 | 2012-09-26 | Flintco Construction | 25535 | 26487 | 2013-01-10 | 2014-04-15 | 2014-04-10 | 2014-04-15 | 11 | 0
2013-04-15 | 2012 | Air National Guard | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069212 | TFI - F-22 FLIGHT SIMULATOR FACILITY | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | 18842 | 21232 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 18 | 0
2013-04-15 | 2012 | Air National Guard | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069213 | TFI - F-22 WEAPONS LOAD CREW TRAINING FACILITY | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | 6473 | 7206 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 16 | 0
2013-04-15 | 2012 | Air National Guard | Major construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | KNMD069216 | TFI - F-22 COMBAT AIRCRAFT PARKING APRON | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | 9682 | 10311 | 2012-08-08 | 2013-08-08 | 2013-08-08 | 2013-08-08 | 5 | 0
2013-04-15 | 2012 | Air National Guard | Major construction | OH | OHIO | SPRINGFIELD-BECKLEY MUNICIPAL AIRPORT | WAAR109001 | ALTER PREDATOR OPERATIONS CENTER FACILITY | 2012-08-17 | 2012-09-26 | UTS-DAG Construction Co., LLC | 5296 | 5933 | 2012-12-05 | 2013-11-29 | 2013-11-01 | 2013-12-13 | 27 | 0
2013-04-15 | 2012 | Air National Guard | Minor Construction | GA | GEORGIA | SAVANNAH/HILTON HEAD IAP | XDQU129062 | VEHICLE MAINTENANCE ADDITION | 2012-05-24 | 2012-08-17 | Tyler Construction Group, Inc. | 1500 | 1500 | 2012-08-17 | 2013-08-15 | 2013-02-13 | 2013-08-30 | 45 | 0
2013-04-15 | 2012 | Air National Guard | Minor Construction | ME | MAINE | BANGOR INTERNATIONAL AIRPORT | FKNN049094 | PAVEMENTS AND GROUNDS FACILITY | 2012-05-16 | 2012-09-12 | Cornerstone Construction | 1277 | 1523 | 2012-09-19 | 2013-10-19 | 2013-03-18 | 2013-09-19 | 0 | 0
2013-04-15 | 2012 | Air National Guard | Minor Construction | MN | MINNESOTA | DULUTH INTERNATIONAL AIRPORT | FMKM099063 | MUNITIONS STORAGE IGLOOS | 2012-08-29 | 2012-09-26 | Max Gray Construction, INC. | 1798 | 1846 | 2012-11-13 | 2013-08-13 | 2013-03-13 | 2013-08-13 | 17 | 0
2013-04-15 | 2012 | Air Force Reserves | Major construction | CA | CALIFORNIA | MARCH AIR RESERVE BASE | PDPG020143 | CONSTRUCT NEW AIRFIELD CONTROL TOWER, B1295 & BASE OP'S B395 | 2012-03-16 | 2012-07-26 | Flintco, LLC. | 16915 | 17008 | 2012-08-22 | 2014-07-24 | 2013-04-23 | 2015-01-22 | 19 | 1928
2013-04-15 | 2012 | Air Force Reserves | Major construction | MO | MISSOURI | WHITEMAN AIR FORCE BASE | YWHG111420 | 442: CONSTRUCT LRS FACILITY | 2012-08-09 | 2012-09-26 | J & S Construction Co, Inc., Cookeville, TN | 3507 | 3507 | 2012-12-19 | 2013-11-30 | 2013-12-20 | 2014-01-01 | 8 | 3840
2013-04-15 | 2012 | Air Force Reserves | Major construction | SC | SOUTH CAROLINA | JOINT BASE CHARLESTON ISSOT NORTH CHARLESTON | DKFX079003 | RED HORSE READINESS AND TRAINING FACILITY | 2012-02-08 | 2012-07-13 | IKHANA | 8149 | 8149 | 2012-07-13 | 2014-01-10 | 2013-03-01 | 2014-01-10 | 12 | 0
2013-04-15 | 2012 | Air Force Reserves | Minor Construction | FL | FLORIDA | HURLBURT FIELD | FTEV111226B | ALTER BUILDING 90131 FOR 2 SOS | 2012-06-05 | 2012-09-13 | HCG, LLC | 926 | 959 | 2012-10-22 | 2013-05-20 | 2013-04-16 | 2013-05-20 | 42 | 1000
2013-04-15 | 2009 | Army Active | Major Construction | MI | MICHIGAN | DETROIT ARSENAL | 033447 | CHILD DEVELOPMENT CENTER | 2011-07-22 08:00 | 2011-09-29 | Atlantic Marine Construction Co Inc. | 4198.8477 | 4219.8108 | 2011-10-09 | 2013-04-30 | 2013-04-01 | 2013-04-18 | 98
2013-04-15 | 2009 | Army Active | Major Construction | KY | KENTUCKY | FORT KNOX | 080656 | HEADQUARTERS BUILDING, WARRIOR IN TRANSITI | 2012-07-19 08:00 | 2012-09-28 | Intersteel, Inc. | 2614.888 | 2614.888 | 2012-10-31 | 2014-03-10 | 2014-01-24 | 2014-01-24 | 0
2013-04-15 | 2009 | Army Reserve | Major Construction | ID | IDAHO | PVT LLOYD D MAJOR CONSTRUCTIONRUCTION CARTER USARC | 067654 | AR CENTER/OMS/UNHEATED STORAGE | 2009-04-10 | 2009-06-24 | LCC-MZT Team 1 | 8200.6 | 8809.0398 | 2009-07-27 | 2013-04-01 | 2011-01-18 | 2011-06-30 | 99
2013-04-15 | 2009 | Army Reserve | Major Construction | MD | MARYLAND | CURTIS BAY, MD | 069422 | ARMY RESERVE CENTER | 2009-04-30 | 2010-02-11 | James W. Ancel, Inc. | 9850.314 | 11923.0445 | 2010-04-12 | 2013-08-30 | 2011-10-04 | 2012-08-17 | 96
2013-04-15 | 2009 | Army Reserve | Major Construction | NV | NEVADA | RYLAND G TAYLOR AFRC | 069436 | ARMY RESERVE CENTER | 2010-06-11 08:00 | 2010-09-01 | MW Builders of Texas, Inc. | 24441 | 25074.818 | 2010-11-09 | 2013-06-13 | 2012-08-30 | 2012-09-19 | 97
2013-04-15 | 2010 | Army Reserve | Major Construction | FL | FLORIDA | GEORGE P WENTWORTH USARC | 069470 | ARMY RESERVE CENTER/LAND | 2012-01-05 | 2012-08-29 | Leebcor Services, Inc. | 6353.27 | 6353.27 | 2012-10-15 | 2014-04-30 | 2014-02-17 | 2014-02-17 | 8
2013-04-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | JAMES W REESE USARC, PA | 069430 | ARMY RESERVE CENTER/LAND | 2011-07-28 | 2011-09-29 | Lobar Inc. | 18538 | 18637.065 | 2012-01-18 | 2014-05-07 | 2013-11-08 | 2013-11-08 | 10
2013-04-15 | 2010 | Army Reserve | Major Construction | FL | FLORIDA | ELLIOTT BABCOCK MEMORIAL AFRC | 069471 | ARMY RESERVE CENTER/LAND | 2011-07-05 | 2012-04-02 | Blackhawk-JaMajor Constructionructiono, A SDVOB Joint Venture | 16009 | 15798.358 | 2012-05-22 | 2013-10-24 | 2013-09-24 | 2013-09-24 | 15
2013-04-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | CHAPLAIN L J SABALIS MEMORIAL USARC | 069561 | ARMY RESERVE CENTER | 2010-04-12 08:00 | 2010-06-24 | P&S Construction, Inc. | 8967 | 10286.013 | 2010-08-10 | 2013-09-03 | 2011-12-13 | 2012-10-18 | 85
2013-04-15 | 2010 | Army Reserve | Major Construction | RQ | PUERTO RICO | JUAN PONCE DE LEON ARMORY | 069568 | ARMY RESERVE CENTER/LAND | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | 12506.39 | 12631.8076 | 2011-11-15 | 2013-09-30 | 2013-08-06 | 2013-08-06 | 18
2013-04-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | UNIONTOWN USARC/AMSA 104 SS 2 (G) | 069652 | ARMY RESERVE CENTER/LAND | 2011-06-23 08:00 | 2011-09-23 | Charpie Korte Enterprise LLC | 11807.704 | 11807.704 | 2012-04-03 | 2013-12-04 | 2014-02-12 | 2013-09-06 | 43
2013-04-15 | 2010 | Army Reserve | Major Construction | PA | PENNSYLVANIA | HARRISBURG USARC | 070511 | ARMY RESERVE CENTER | 2010-07-13 08:00 | 2011-03-31 | Eagle ACN Joint Venture | 7740.007 | 8813.1125 | 2011-04-18 | 2014-03-05 | 2012-08-20 | 2012-08-20 | 44
2013-04-15 | 2010 | Army Reserve | Major Construction | TX | TEXAS | COMSTOCK, US BORDER PATROL STATION | 075110 | TACTICAL EQUIPMENT MAINTENANCE FACILITY | 2011-10-04 08:00 | 2012-01-26 | Leetex Construction LLC | 9487.777 | 9487.777 | 2012-04-05 | 2013-11-06 | 2013-09-12 | 2013-09-22 | 11
2013-04-15 | 2011 | Army Active | Minor Construction | OH | OHIO | LIMA ARMY TANK CENTER | 074757 | FIRE ALARM SYSTEM | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | 1763.338 | 1763.338 | 2012-09-05 | 2013-10-24 | 2013-08-01 | 2013-08-01 | 42
2013-04-15 | 2011 | Army Reserve | Major Construction | FL | FLORIDA | ORLANDO, FL | 069608 | ARMY RESERVE CENTER/LAND | 2011-06-17 | 2011-09-16 | Harkins Development LLC | 7914.55 | 8028.5875 | 2011-11-01 | 2013-06-01 | 2013-03-05 | 2013-04-03 | 95
2013-04-15 | 2011 | Army Reserve | Major Construction | IA | IOWA | FORT SHERIDAN | 070654 | ARMY RESERVE CENTER | 2011-11-15 | 2012-03-14 | Greenleaf Construction Co., Inc. | 9013.152 | 9060.208 | 2012-04-09 | 2013-09-30 | 2013-08-12 | 2013-10-01 | 33
2013-04-15 | 2011 | Army Reserve | Major Construction | CA | CALIFORNIA | FORT HUNTER LIGGETT | 072097 | ECS TACTICAL EQUIPMENT MAINT FACILITY | 2010-12-02 08:00 | 2011-06-09 | Kisaq-RQ 8A 2 JV | 20251.66 | 20375.399 | 2011-08-03 | 2013-09-07 | 2013-05-24 | 2013-05-24 | 68
2013-04-15 | 2011 | Army Reserve | Major Construction | TX | TEXAS | DENTON, TX | 071304 | ARMY RESERVE CENTER/LAND | 2011-04-20 | 2011-09-27 | GCC Major ConstructionructionCarthy Joint Venture II | 11726.351 | 11783.317 | 2011-10-19 | 2013-04-18 | 2013-04-11 | 2013-04-21 | 87
2013-04-15 | 2011 | Army Reserve | Major Construction | CA | CALIFORNIA | FORT HUNTER LIGGETT | 072098 | TACTICAL VEHICLE WASH RACK | 2011-07-29 08:00 | 2011-09-30 | P&S Construction | 8481.2 | 8533.8001 | 2011-10-11 | 2013-05-22 | 2013-02-12 | 2013-05-30 | 90
2013-04-15 | 2011 | Army Reserve | Major Construction | TX | TEXAS | RIO GRAND, TX | 069421 | ARMY RESERVE CENTER/LAND | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | 4504 | 4504 | 2012-08-21 | 2014-04-20 | 2014-03-21 | 2014-03-21 | 0
2013-04-15 | 2011 | Army Reserve | Major Construction | CA | CALIFORNIA | CONCORD, CA | 069563 | ARMY RESERVE CENTER | 2010-10-18 | 2011-05-13 | Walbridge Overaa, A Joint Venture | 23881 | 24355.998 | 2011-06-06 | 2013-06-10 | 2013-03-27 | 2013-03-27 | 96
2013-04-15 | 2011 | Army Reserve | Major Construction | NM | NEW MEXICO | LAS CRUCES, NM | 069582 | ARMY RESERVE CENTER/LAND | 2012-06-13 08:00 | 2012-09-21 | Old Veteran Construction, Inc. | 10535 | 10535 | 2012-11-07 | 2014-06-24 | 2014-05-01 | 2014-05-01 | 5
2013-04-15 | 2011 | Army Reserve | Major Construction | NY | NEW YORK | BINGHAMTON, NY (UTICA) | 069599 | ARMY RESERVE CENTER/LAND | 2012-07-25 | 2012-09-25 | J. Kokolakis Contracting, Inc. | 12974.5 | 12974.5 | 2012-10-25 | 2014-05-28 | 2014-04-03 | 2014-04-03 | 0
2013-04-15 | 2011 | Army Reserve | Major Construction | IN | INDIANA | MICHIGAN CITY, IN | 069617 | ARMY RESERVE CENTER/LAND | 2011-08-22 | 2011-09-30 | Better Built Construction Services, Inc. | 15456.53 | 15214.9682 | 2011-10-17 | 2013-09-16 | 2013-01-20 | 2013-07-27 | 82
2013-04-15 | 2011 | Army Reserve | Major Construction | TX | TEXAS | SAN MARCOS MEMORIAL USARC | 070621 | ARMY RESERVE CENTER/LAND | 2011-01-24 | 2011-07-12 | VCS ACN Joint Venture | 7545.8 | 8230.606 | 2011-08-19 | 2013-04-30 | 2012-12-21 | 2013-02-03 | 96
2013-04-15 | 2011 | Army Reserve | Major Construction | IL | ILLINOIS | QUINCY, IL | 070627 | ARMY RESERVE CENTER/LAND | 2011-04-11 08:00 | 2011-09-22 | Old Veteran Construction, Inc. | 11561.7 | 11572.493 | 2011-10-10 | 2013-04-02 | 2013-02-11 | 2013-04-12 | 97
2013-04-15 | 2011 | Army Reserve | Major Construction | VA | VIRGINIA | ROANOKE, VA | 070641 | ARMY RESERVE CENTER/LAND | 2011-08-18 | 2011-11-23 | Anthony & Gordon Construction Co, Inc. | 13504 | 13883.305 | 2012-01-12 | 2013-08-19 | 2013-05-06 | 2013-05-06 | 62
2013-04-15 | 2011 | Army Reserve | Major Construction | FL | FLORIDA | CAPE CORAL, FL / FT. MEYERS | 071303 | ARMY RESERVE CENTER/LAND | 2011-05-03 | 2011-12-13 | FSA + JKC Joint Venture One, LLC | 11088.5 | 11092.977 | 2012-03-06 | 2013-08-28 | 2013-07-09 | 2013-07-09 | 32
2013-04-15 | 2011 | Army Reserve | Major Construction | GA | GEORGIA | MACON, GA | 074212 | ARMY RESERVE CENTER/LAND | 2011-08-12 | 2011-09-28 | CSC- New South, a Joint Venture | 11117.366 | 11151.243 | 2011-10-27 | 2013-04-21 | 2013-02-28 | 2013-03-10 | 98
2013-04-15 | 2011 | Army Reserve | Major Construction | FL | FLORIDA | TALLAHASSEE, FL | 074220 | ARMY RESERVE CENTER/LAND | 2011-05-19 | 2011-09-23 | Greenleaf Construction Co., Inc. | 8969.571 | 8730.976 | 2011-10-21 | 2013-05-23 | 2013-03-24 | 2013-04-19 | 63
2013-04-15 | 2011 | Army Reserve | Major Construction | MO | MISSOURI | INDEPENDENCE, MO | 074209 | ARMY RESERVE CENTER | 2011-08-04 08:00 | 2011-09-29 | S&S - EXCEL CONSTRUCTORS JV | 10755.532 | 11030.28 | 2011-10-24 | 2013-05-07 | 2013-03-17 | 2013-03-17 | 97
2013-04-15 | 2011 | Army Reserve | Major Construction | TN | TENNESSEE | MILLINGTON, TN | 078256 | TEMF/AMSA | 2011-09-14 | 2011-12-23 | Orocon-Carothers JV1 | 9478.98 | 9823.0446 | 2012-02-01 | 2013-07-29 | 2013-06-05 | 2013-07-29 | 67
2013-04-15 | 2011 | Army Reserve | Major Construction | RQ | PUERTO RICO | FORT BUCHANAN | 077807 | ENGINEERING/HOUSING MAINTENANCE SHOP | 2011-07-14 | 2011-09-28 | Consigli Construction Company, Inc. | 16861.765 | 16924.5089 | 2011-11-08 | 2013-10-01 | 2013-07-30 | 2013-07-30 | 60
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 018646 | VEHICLE MAINTENANCE FACILITY | 2011-12-09 | 2012-05-08 | J & S Construction Company, Inc. | 12240.9707 | 12273.3567 | 2012-05-30 | 2013-10-22 | 2013-08-23 | 2013-08-31 | 51
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 065147 | PHYSICAL FITNESS FACILITY | 2011-11-10 | 2012-03-15 | Paladin-Hoar Construction, LLC | 16199.3 | 16276.763 | 2012-03-28 | 2013-09-19 | 2013-07-21 | 2013-08-03 | 57
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 064297 | VEHICLE MAINTENANCE FACILITY | 2011-12-05 08:00 | 2012-05-18 | TJC Engineering, Inc | 23597.2131 | 32575.3091 | 2012-05-31 | 2014-05-31 | 2014-03-12 | 2014-04-08 | 36
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 064297 | VEHICLE MAINTENANCE FACILITY | 2011-12-05 08:00 | 2012-05-01 | J&S Construction Company, Inc. | 8483.139 | 32575.3091 | 2012-05-17 | 2013-10-05 | 2013-09-09 | 2013-09-09 | 62
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 071703 | SCOUT/RECCE GUNNERY RANGE | 2012-02-17 08:00 | 2012-05-10 | The Ross Group Construction Corp | 9236.2 | 9306.042 | 2012-06-04 | 2013-10-19 | 2013-08-20 | 2013-09-16 | 75
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT KNOX | 064823 | AUTOMATED INFANTRY PLATOON BATTLE COURSE | 2011-12-20 08:00 | 2012-03-16 | Barlovento, L. L. C | 4197.37 | 4212.149 | 2012-04-02 | 2013-07-08 | 2013-05-27 | 2013-05-27 | 68
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT KNOX | 065293 | BATTALION COMPLEX | 2012-02-10 | 2012-06-29 | B>L> Harbert International, LLC | 40887 | 40931.521 | 2012-07-18 | 2014-07-08 | 2014-03-18 | 2014-04-05 | 30
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 069501 | UNMANNED AERIAL VEHICLE MAINTENANCE HANGAR | 2011-12-16 08:00 | 2012-09-27 | Archer Western Federal JV | 40397 | 40451.405 | 2012-11-05 | 2014-11-05 | 2014-09-06 | 2014-10-08 | 11
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 073541 | BARRACKS | 2011-11-30 08:00 | 2012-05-18 | Sundt Construction, Inc. | 21465.283 | 21474.008 | 2012-06-07 | 2014-01-28 | 2013-11-29 | 2013-12-14 | 30
2013-04-15 | 2012 | Army Active | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 072684 | BARRACKS COMPLEX | 2011-11-17 | 2012-05-16 | Balfour Beatty Construction, LLC | 50995.657 | 51104.438 | 2012-06-11 | 2014-04-30 | 2014-03-23 | 2014-03-23 | 23
2013-04-15 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | NAVAL STATION STATEN ISLAND USARC | 069432 | ARMY RESERVE CENTER | 2012-12-21 | 2013-03-06 | Macnak-Korte Design Build LLC | 14338.486 | 14338.486 | 5-Apr-13 (S) | 2014-09-27 | 2014-08-07 | 2014-08-07 | 0
2013-04-15 | 2012 | Army Reserve | Major Construction | CA | CALIFORNIA | FORT HUNTER LIGGETT | 071702 | AUTOMATED MULTIPURPOSE MACHINE GUN (MPMG) | 2012-03-05 08:00 | 2012-05-31 | Cooper Chase Construction | 4837.501 | 4777.796 | 2012-06-26 | 2014-02-12 | 2013-12-03 | 2013-12-03 | 65
2013-04-15 | 2012 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 067720 | MODIFIED RECORD FIRE KNOWN DISTANCE RANGE | 2011-12-27 08:00 | 2012-03-27 | Range and Civil Construction , LLC | 5053 | 5059.625 | 2012-04-18 | 2013-09-23 | 2013-08-06 | 2013-08-06 | 91
2013-04-15 | 2012 | Army Reserve | Major Construction | MO | MISSOURI | WELDON SPRINGS, MO | 067581 | ARMY RESERVE CENTER | 2012-04-20 08:00 | 2012-07-13 | K&S Associates, Inc. | 16725 | 16934.841 | 2012-08-14 | 2014-03-15 | 2014-01-21 | 2014-03-07 | 14
2013-04-15 | 2012 | Army Reserve | Major Construction | IN | INDIANA | FORT BENJAMIN HARRISON | 067673 | ARMY RESERVE CENTER | 2012-02-14 | 2012-05-15 | Hunt Construction Group | 44568.206 | 45524.8232 | 2012-05-30 | 2014-07-09 | 2015-01-29 | 2015-03-19 | 18
2013-04-15 | 2012 | Army Reserve | Major Construction | IL | ILLINOIS | HOMEWOOD, IL - P2#331461 | 067713 | ARMY RESERVE CENTER | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | 13454 | 13454 | 2012-10-18 | 2014-10-19 | 2014-07-10 | 2014-07-10 | 5
2013-04-15 | 2012 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 067684 | CONTAINER LOADING FACILITY | 2011-11-17 | 2012-03-30 | Carntribe-Clement 3, A Joint Venture, LLC | 5061.521 | 5086.521 | 2012-06-27 | 2013-10-30 | 2013-10-30 | 2013-11-04 | 20
2013-04-15 | 2012 | Army Reserve | Major Construction | NC | NORTH CAROLINA | GREENSBORO, NC - P2#333014 | 067466 | ARMY RESERVE CENTER/LAND | 2012-05-16 | 2012-09-18 | IKHANA, LL | 16212 | 16212 | 2012-10-10 | 2014-06-19 | 2014-03-19 | 2014-03-19 | 7
2013-04-15 | 2012 | Army Reserve | Major Construction | IL | ILLINOIS | ROCKFORD, IL - P2#333015 | 067664 | ARMY RESERVE CENTER/LAND | 2012-01-18 | 2012-05-02 | Charpie Korte Industries | 10690.067 | 10755.067 | 2012-06-29 | 2014-01-15 | 2013-12-06 | 2013-12-06 | 22
2013-04-15 | 2012 | Army Reserve | Major Construction | SC | SOUTH CAROLINA | ORANGEBURG, SC - P2#333016 | 067672 | ARMY RESERVE CENTER/LAND | 2011-11-16 | 2012-03-29 | Group III Mgt. Inc | 10539.52 | 10539.52 | 2012-05-21 | 2014-02-09 | 2013-09-23 | 2013-10-20 | 15
2013-04-15 | 2012 | Army Reserve | Major Construction | MN | MINNESOTA | ST. JOSEPH, MN - P2#333017 | 067674 | ARMY RESERVE CENTER | 2011-11-30 | 2012-04-13 | LS Black Constructors, Inc | 10501.332 | 10671.232 | 2012-06-27 | 2014-02-28 | 2013-12-04 | 2014-02-05 | 9
2013-04-15 | 2012 | Army Reserve | Major Construction | NY | NEW YORK | SCHENECTADY, NY - P2#333019 | 067691 | ARMY RESERVE CENTER | 2011-11-16 | 2012-05-03 | SENECA - SCMajor Constructionruction, LLC | 18367 | 18367 | 2012-06-01 | 2013-12-30 | 2014-02-21 | 2014-02-21 | 21
2013-04-15 | 2012 | Army Reserve | Major Construction | CO | COLORADO | FORT COLLINS | 067658 | ARMY RESERVE CENTER | 2011-11-29 | 2012-04-16 | Greenleaf Construction Co., Inc. | 10544.965 | 10624.661 | 2012-05-11 | 2014-04-16 | 2013-10-18 | 2013-10-18 | 7
2013-04-15 | 2012 | Army Reserve | Major Construction | WI | WISCONSIN | Fort McCoy | 074310 | NCOA PHASE III - BILLETING | 2012-06-04 08:00 | 2012-08-14 | Carlson Constructors Corp | 11918.15 | 11918.15 | 2012-09-20 | 2014-04-22 | 2014-02-27 | 2014-02-27 | 6
2013-04-15 | 2008 | Army Active | Major Construction | GM | GERMANY | GRAFENWOEHR GERMANY | 055978 | BRIGADE COMPLEX-MAINTENANCE/OPERATIONS | 2008-02-13 08:00 | 2008-07-23 | Federal Republic of Germany | 16031.1154 | 16031.1154 | 2008-07-28 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 0
2013-04-15 | 2008 | Army Active | Major Construction | BG | BULGARIA | EUROPE VARIOUS | 063714 | BASE CAMP | 2008-06-20 | 2012-07-30 | PLANEX Ltd. | 2317.2382 | 2317.2382 | 2012-09-13 | 2013-07-06 | 2013-03-12 | 2013-05-07 | 68
2013-04-15 | 2008 | Army Active | Major Construction | BG | BULGARIA | EUROPE VARIOUS | 063714 | BASE CAMP | 2008-06-20 | 2012-07-30 | Planex ltd. | 2076.5335 | 2076.5335 | 2012-09-13 | 2014-11-02 | 2014-09-03 | 2014-09-03 | 11
2013-04-15 | 2008 | Army Reserve | Major Construction | NJ | NEW JERSEY | FORT DIX | 067680 | TACTICAL TRAINING BASE PHASE 1 | 2008-05-28 17:00 | 2010-11-24 | Complete Technical Service, Inc. | 3965.265 | 3965.265 | 2011-01-05 | 2013-04-15 | 2012-05-09 | 2013-03-15 | 99
2013-04-15 | 2008 | Army Active | Major Construction - AFH | GM | GERMANY | ANSBACH, GERMANY | 066253 | FAMILY HOUSING REPLACEMENT CONSTRUCTION | 2012-10-05 08:00 | 2013-02-14 | Staatliches Hochbauamt Nurnberg II | 0 | 0 | 2013-03-13 | 2014-04-12 | 2014-03-13 | 2014-03-13 | 96
2013-04-15 | 2009 | Army Active | Major Construction | PA | PENNSYLVANIA | CARLISLE BARRACKS | 057142 | MUSEUM SUPPORT FACILITY | 2009-05-08 17:00 | 2012-07-13 | HCR Construction Inc. | 196.9332 | 10696.5568 | 2012-08-27 | 2013-07-29 | 2013-05-24 | 2013-05-24 | 52
2013-04-15 | 2009 | Army Active | Major Construction | GM | GERMANY | VILSECK | 069416 | AIRCRAFT/VEHICLE MAINTENANCE COMPLEX | 2008-12-05 08:00 | 2011-03-17 | Federal Republic of Germany | 11251.6674 | 8862.4178 | 2011-06-29 | 2013-08-17 | 2013-04-01 | 2013-09-30 | 89
2013-04-15 | 2009 | Army Active | Major Construction | NL | NETHERLANDS | BELGIUM AVERAGE | 058275 | CHILD DEVELOPMENT CENTER | 2010-08-24 | 2010-11-29 | Bilfinger Berger Government Services GmbH | 10104.9968 | 9116.493 | 2011-03-14 | 2013-04-22 | 2012-09-04 | 2013-04-19 | 90
2013-04-15 | 2009 | Army Active | Major Construction | NJ | NEW JERSEY | PICATINNY ARSENAL | 066725 | BALLISTIC EVALUATION FACILITY PH 1 | 2012-05-11 08:00 | 2012-09-28 | APS Contracting Inc. | 7201.728 | 7201.728 | 2012-12-04 | 2014-09-02 | 2014-06-04 | 2014-06-04 | 3
2013-04-15 | 2009 | Army Active | Major Construction | GM | GERMANY | ANSBACH, GERMANY | 060238 | CHILD DEVELOPMENT CENTER | 2011-07-08 | 2011-09-29 | Staatliches Hochbauamt Nurnberg II | 8392.9995 | 6677.5592 | 2011-10-07 | 2013-07-30 | 2013-04-14 | 2013-04-14 | 90
2013-04-15 | 2009 | Army Active | Major Construction | GM | GERMANY | ANSBACH, GERMANY | 062511 | CHILD DEVELOPMENT CENTER | 2011-07-08 | 2011-09-22 | Staatliches Hochbauamt Nurnberg II | 11350.716 | 9130.4995 | 2011-10-13 | 2013-08-30 | 2013-06-10 | 2013-06-10 | 59
2013-04-15 | 2009 | Army Active | Major Construction | GM | GERMANY | LANDSTUHL GERMANY | 053874 | CHILD YOUTH SERVICES CENTER | 2011-12-22 | 2012-05-22 | LBB Kaiserslautern | 5288.7701 | 4190.6001 | 2012-08-14 | 2014-01-16 | 2013-10-18 | 2013-10-18 | 17
2013-04-15 | 2009 | Army Active | Major Construction - AFH | GM | GERMANY | WIESBADEN GERMANY | 062327 | FAMILY HOUSING REPLACEMENT CONSTRUCTION | 2008-11-20 08:01 | 2009-12-08 | Federal Republic of Germany | 27419.2613 | 23614.2092 | 2009-12-08 | 2013-08-05 | 2012-12-25 | 2013-06-06 | 97
2013-04-15 | 2009 | Army Active | Major Construction - AFH | GM | GERMANY | WIESBADEN GERMANY | 066245 | FAMILY HOUSING REPLACEMENT CONSTRUCTION | 2008-11-20 08:00 | 2009-12-08 | Federal Republic of Germany | 17007.8508 | 14213.0341 | 2009-12-08 | 2013-08-05 | 2012-12-25 | 2013-06-06 | 97
2013-04-15 | 2009 | Army Active | Major Construction - AFH | GM | GERMANY | WIESBADEN GERMANY | 066318 | FAMILY HOUSING REPLACEMENT CONSTRUCTION | 2010-04-12 | 2009-12-08 | Federal Republic of Germany | 31148.1363 | 25858.8772 | 2009-12-08 | 2013-08-05 | 2012-12-25 | 2013-06-06 | 98
2013-04-15 | 2009 | Army Active | Major Construction - AFH | GM | GERMANY | WIESBADEN GERMANY | 066318 | FAMILY HOUSING REPLACEMENT CONSTRUCTION | 2010-04-12 | 2009-12-08 | Federal Republic of Germany | 0 | 25858.8772 | 2009-12-08 | 2013-08-05 | 2012-12-25 | 2013-06-06 | 97
2013-04-15 | 2009 | Army Active | Major Construction - AFH | GM | GERMANY | WIESBADEN GERMANY | 066319 | FAMILY HOUSING REPLACEMENT CONSTRUCTION | 2008-11-20 17:00 | 2009-12-09 | Federal Republic of Germany | 33696.2033 | 28192.2194 | 2009-12-09 | 2013-06-06 | 2012-11-10 | 2013-04-22 | 97
2013-04-15 | 2009 | Army Active | Major Construction - AFH | GM | GERMANY | WIESBADEN GERMANY | 062486 | FAMILY HOUSING IMPROVEMENTS | 2009-02-20 | 2011-12-22 | Noelke GmbH Malerbetrieb | 14394.7135 | 14260.1676 | 2012-01-06 | 2014-02-18 | 2013-07-07 | 2013-09-05 | 30
2013-04-15 | 2010 | Army Active | Major Construction | MD | MARYLAND | FORT DETRICK | 058625 | SATELLITE COMMUNICATIONS FACILITY | 2009-10-09 08:00 | 2010-02-05 | Harkins Builders, Inc. | 11717.005 | 18800.0395 | 2010-03-06 | 2014-05-01 | 2012-09-01 | 2013-08-09 | 95
2013-04-15 | 2010 | Army Active | Major Construction | VA | VIRGINIA | FORT A P HILL | 067011 | AUTOMATED INFANTRY PLATOON BATTLE COURSE | 2010-01-27 10:00 | 2011-07-06 | Rand Enterprises, Inc. | 4598.4944 | 5066.3114 | 2011-08-11 | 2013-06-01 | 2012-08-10 | 2013-06-01 | 99
2013-04-15 | 2010 | Army Active | Major Construction | GM | GERMANY | KATTERBACH GERMANY | 063394 | BARRACKS | 2010-03-15 08:00 | 2011-12-13 | Staatliches Hochbauamt Nurnberg II | 16357.9196 | 13347.5576 | 2012-01-09 | 2013-11-29 | 2013-09-06 | 2013-09-06 | 44
2013-04-15 | 2010 | Army Active | Major Construction | GM | GERMANY | KAISERSLAUTERN GERMANY | 066596 | BARRACKS | 2011-11-14 | 2012-06-20 | Federal Republic of Germany | 16925.5868 | 13136.7379 | 2012-09-05 | 2014-06-27 | 2014-04-28 | 2014-04-28 | 12
2013-04-15 | 2010 | Army Active | Major Construction | GM | GERMANY | ILLESHEIM GERMANY | 069616 | BARRACKS | 2012-03-16 | 2012-07-11 | Staatliches Hochbauamt Nurnberg II | 13907.2139 | 10763.4844 | 2012-08-06 | 2014-02-28 | 2014-01-10 | 2014-01-10 | 11
2013-04-15 | 2010 | Army Active | Major Construction | VA | VIRGINIA | FORT EUSTIS | 066714 | TRANSIENT UPH, ADVANCED INDIVIDUAL TRAINEE | 2010-11-30 08:00 | 2010-09-29 | Balfour Beatty Construction | 18618.72 | 39066.284 | 2010-10-14 | 2012-05-31 | 2012-01-19 | 2012-06-14 | 99
2013-04-15 | 2010 | Army Active | Major Construction | VA | VIRGINIA | FORT EUSTIS | 066714 | TRANSIENT UPH, ADVANCED INDIVIDUAL TRAINEE | 2010-11-30 08:00 | 2011-04-05 | Mortenson Construction | 18932 | 39066.284 | 2011-05-09 | 2013-01-11 | 2012-11-09 | 2013-04-18 | 95
2013-04-15 | 2010 | Army Active | Major Construction | MD | MARYLAND | ABERDEEN PROVING GROUND | 059978 | ANALYTICAL CHEM WING-ADVANCED CHEM LAB | 2010-11-22 | 2011-04-27 | JOHN C GRIMBERG CO., INC. | 14904 | 15371.6875 | 2011-06-02 | 2013-06-30 | 2012-12-31 | 2012-12-31 | 94
2013-04-15 | 2010 | Army Active | Major Construction | MD | MARYLAND | FORT DETRICK | 060027 | AUDITORIUM AND TRAINING CENTER EXPANSION | 2011-02-23 | 2011-07-08 | Grunley/Goel JV D LLC | 7530 | 7869.692 | 2011-08-18 | 2013-11-15 | 2013-08-17 | 2013-10-02 | 67
2013-04-15 | 2010 | Army Active | Major Construction | NJ | NEW JERSEY | PICATINNY ARSENAL | 066726 | BALLISTIC EVALUATION FACILITY, PH 2 | 2012-05-11 08:00 | 2012-09-28 | APS Contracting Inc. | 8757.272 | 8757.272 | 2012-12-04 | 2014-09-02 | 2014-06-04 | 2014-06-04 | 3
2013-04-15 | 2010 | Army Active | Minor Construction | VA | VIRGINIA | FORT BELVOIR | 074885 | FIRE STATION | 2011-08-25 | 2012-07-17 | ARGO SYSTEMS, LLC | 1636.889 | 1636.889 | 2012-08-03 | 2014-01-25 | 2014-01-25 | 2014-01-25 | 10
2013-04-15 | 2010 | Army Active | Major Construction - AFH | GM | GERMANY | WIESBADEN GERMANY | 074358 | FAMILY HOUSING REPLACEMENT CONST INC 2 | 2008-11-20 17:00 | 2009-12-08 | Federal Republic of Germany | 25.062 | 18.0747 | 2009-12-08 | 2013-08-05 | 2012-12-25 | 2013-06-06 | 97
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | WEST POINT MILITARY ACADEMY | 059044 | SCIENCE FACILITY, PH 2 | 2011-06-23 08:00 | 2011-09-30 | Walsh Construction Company II L.L.C. | 105270 | 105345.001 | 2011-11-17 | 2016-04-29 | 2015-11-14 | 2015-11-14 | 22
2013-04-15 | 2011 | Army Active | Major Construction | VA | VIRGINIA | FORT A P HILL | 065726 | MOUT COLLECTIVE TRAINING FAC | 2011-11-14 08:00 | 2012-01-03 | Jordan-Versar, LLC | 55547 | 56148.214 | 2012-01-20 | 2013-10-24 | 2013-10-21 | 2013-10-24 | 51
2013-04-15 | 2011 | Army Active | Major Construction | VA | VIRGINIA | FORT A P HILL | 065789 | INDOOR FIRING RANGE | 2011-11-14 08:00 | 2012-01-03 | Jordan-Versar, LLC | 6520 | 6536.097 | 2012-01-20 | 2013-10-24 | 2013-10-21 | 2013-10-24 | 51
2013-04-15 | 2011 | Army Active | Major Construction | VA | VIRGINIA | FORT A P HILL | 065791 | 1200 METER RANGE | 2011-08-15 08:00 | 2011-09-26 | Jordan-Versar, LLC | 10235.943 | 10469.251 | 2011-10-17 | 2013-07-18 | 2013-07-18 | 2013-07-18 | 99
2013-04-15 | 2011 | Army Active | Major Construction | VA | VIRGINIA | FORT A P HILL | 065792 | KNOWN DISTANCE RANGE | 2011-08-15 08:00 | 2011-09-26 | Jordan-Versar, LLC | 2979.244 | 2981.033 | 2011-10-17 | 2013-07-18 | 2013-07-18 | 2013-07-18 | 99
2013-04-15 | 2011 | Army Active | Major Construction | MD | MARYLAND | FORT MEADE | 065793 | INDOOR FIRING RANGE | 2011-06-17 | 2011-09-21 | John C. Grimberg Company, Inc. | 7241 | 7844.4912 | 2011-10-13 | 2013-12-20 | 2013-04-05 | 2013-04-25 | 74
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 057712 | TRANSIENT TRAINING BARRACKS | 2011-06-14 | 2011-09-28 | Purcell-Lawman JV | 46427.807 | 46504.732 | 2011-10-14 | 2013-07-10 | 2013-04-11 | 2013-04-11 | 84
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | WIESBADEN GERMANY | 060555 | INFORMATION PROCESSING CENTER | 2012-10-01 | 2012-05-14 | Hessisches Baumanagement Wiesbaden | 27446.5978 | 19897.3221 | 2012-06-18 | 2013-11-22 | 2013-10-23 | 2013-10-23 | 23
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 062580 | AIRCRAFT FUEL STORAGE COMPLEX | 2011-08-17 08:00 | 2011-09-29 | Green Jacket- DC Building Systems Joint Venture | 13411.4 | 13642.492 | 2011-10-24 | 2013-09-07 | 2013-04-21 | 2013-06-09 | 83
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | WIESBADEN GERMANY | 068866 | SENSITIVE COMPARTMENTED INFORMATION FAC | 2012-05-22 | 2013-01-23 | ECC International LLC | 87011.483 | 69436.554 | 2013-02-22 | 2015-08-17 | 2015-08-17 | 2015-08-17 | 0
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | WIESBADEN GERMANY | 068866 | SENSITIVE COMPARTMENTED INFORMATION FAC | 2012-05-22 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | 7198.2416 | 69436.554 | 2013-02-13 | 2014-04-14 | 2014-02-13 | 2014-02-13 | 4
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 057735 | INFANTRY SQUAD BATTLE COURSE | 2011-12-21 | 2012-04-25 | Dynamic Construction of Northern New York, LLC | 6675 | 6675 | 2012-08-26 | 2014-05-23 | 2014-02-22 | 2014-02-22 | 41
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | KATTERBACH GERMANY | 059434 | PHYSICAL FITNESS CENTER | 2012-06-15 17:00 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II | 14482.3279 | 10492.9932 | 2012-11-30 | 2014-08-31 | 2014-06-08 | 2014-06-08 | 0
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 067532 | AIRCRAFT MAINTENANCE HANGAR | 2010-11-23 | 2011-07-01 | Upstate Construction Services, Inc. | 10792.444 | 14137.854 | 2011-07-22 | 2013-04-12 | 2013-01-12 | 2013-01-12 | 99
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 067532 | AIRCRAFT MAINTENANCE HANGAR | 2010-11-23 | 2012-09-27 | Black Horse Group | 2966.8 | 14137.854 | 2012-10-19 | 2014-07-16 | 2014-04-17 | 2014-04-17 | 2
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | GRAFENWOEHR GERMANY | 067968 | BARRACKS | 2011-07-17 | 2011-11-23 | Federal Republic of Germany | 16357.4626 | 11947.6319 | 2011-12-12 | 2013-11-19 | 2013-04-09 | 2013-04-09 | 49
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | EAST CAMP GRAFENWOEHR | 068606 | BARRACKS | 2012-05-04 08:00 | 2012-10-12 | Bundeskasse Trier | 18121.4668 | 13083.14 | 2012-10-12 | 2014-05-09 | 2014-05-09 | 2014-05-09 | 4
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | VILSECK | 069612 | BARRACKS | 2011-10-21 | 2012-02-15 | Federal Republic of Germany | 18034.1312 | 13112.1777 | 2012-02-29 | 2014-01-14 | 2013-11-08 | 2013-11-08 | 47
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | GRAFENWOEHR GERMANY | 069613 | BARRACKS | 2011-10-21 | 2012-02-15 | Federal Republic of Germany | 18352.1994 | 13347.4297 | 2012-02-29 | 2014-01-14 | 2013-11-08 | 2013-11-08 | 45
2013-04-15 | 2011 | Army Active | Major Construction | MD | MARYLAND | FORT MEADE | 057595 | WIDEBAND SATCOM OPERATIONS CENTER | 2010-11-23 17:00 | 2011-08-08 | Lebolo-Watts Constructors 01 JV LLC | 18392 | 18759.247 | 2011-09-06 | 2013-09-15 | 2013-04-28 | 2013-04-28 | 73
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 067045 | BATTALION COMPLEX | 2011-03-04 17:00 | 2011-09-01 | Upstate Construction Services, Inc. | 18658.7 | 40417.805 | 2011-09-26 | 2013-06-17 | 2013-03-19 | 2013-03-19 | 96
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 067045 | BATTALION COMPLEX | 2011-03-04 17:00 | 2011-07-07 | Purcell-Lawman JV | 21480.218 | 40417.805 | 2011-08-05 | 2013-06-17 | 2013-01-26 | 2013-01-26 | 97
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 071472 | BRIGADE COMPLEX PH 1 | 2011-03-04 17:00 | 2011-08-15 | VETCO Contracting Services, LLC | 18279.51 | 32707.529 | 2011-09-14 | 2013-06-05 | 2013-03-07 | 2013-03-07 | 68
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 071472 | BRIGADE COMPLEX PH 1 | 2011-03-04 17:00 | 2011-07-07 | Purcell-Lawman JV | 13948.957 | 32707.529 | 2011-08-05 | 2013-06-17 | 2013-01-26 | 2013-01-26 | 97
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 014456 | TRAINING AIDS CENTER | 2010-12-03 | 2011-07-07 | Black Horse Group, LLC | 12412.4 | 12511.894 | 2011-08-02 | 2013-07-20 | 2013-04-21 | 2013-04-21 | 98
2013-04-15 | 2011 | Army Active | Major Construction | DE | DELAWARE | KATTERBACH GERMANY | 066834 | VEHICLE MAINTENANCE SHOP | 2011-05-26 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | 16289.8057 | 12213.707 | 2011-12-12 | 2014-01-18 | 2013-12-18 | 2013-12-18 | 70
2013-04-15 | 2011 | Army Active | Major Construction | VA | VIRGINIA | FORT LEE | 071114 | TRAINING AIDS CENTER | 2010-09-30 17:00 | 2011-07-14 | TRS Range Services, LLC | 4699.764 | 4746.619 | 2011-09-22 | 2013-07-01 | 2013-01-06 | 2013-04-09 | 70
2013-04-15 | 2011 | Army Active | Major Construction | NY | NEW YORK | WEST POINT MILITARY ACADEMY | 065166 | URBAN ASSAULT COURSE | 2011-08-09 17:00 | 2012-05-17 | Doyle Contracting Inc | 4465 | 4465 | 2012-06-19 | 2014-03-14 | 2013-12-17 | 2013-12-17 | 77
2013-04-15 | 2011 | Army Active | Minor Construction | NJ | NEW JERSEY | PICATINNY ARSENAL | 074943 | IGLOO STORAGE, INSTALLATION | 2012-03-13 | 2012-07-18 | Senate Builders & Construction Managers Inc. | 1756.106 | 1756.106 | 2012-08-10 |  | 2013-07-07 | 2013-07-07 | 39
2013-04-15 | 2011 | Army Active | Minor Construction | MD | MARYLAND | FORT MEADE | 070788 | MAPES ROAD AND COOPER AVE IMPROVEMENTS | 2011-08-22 | 2011-12-16 | Chugach World Services, Inc. | 1612.5431 | 1612.5431 | 2012-01-11 | 2014-02-25 | 2013-12-27 | 2013-12-27 | 9
2013-04-15 | 2011 | Army Active | Minor Construction | MD | MARYLAND | FORT MEADE | 068162 | SITE PREPARATION, RELOCATABLE | 2012-09-13 | 2011-09-28 | Akima Construction Services, LLC | 16896.8591 | 16897.8091 | 2011-11-07 | 2013-09-20 | 2012-07-11 | 2012-08-17 | 20
2013-04-15 | 2012 | Army Active | Major Construction | MD | MARYLAND | FORT MEADE | 065755 | BRIGADE COMPLEX | 2012-05-01 08:00 | 2012-10-30 | Skanska USA Building Inc. | 30761.85 | 30816.734 | 2012-12-12 | 2016-04-10 | 2015-12-12 | 2015-12-12 | 0
2013-04-15 | 2012 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 061235 | CHAPEL | 2012-05-16 | 2012-08-03 | Structural Associates Inc. | 7601.3 | 7601.3 | 2012-09-06 | 2014-06-03 | 2014-03-05 | 2014-03-05 | 11
2013-04-15 | 2012 | Army Active | Major Construction | GM | GERMANY | LANDSTUHL GERMANY | 057594 | SATELLITE COMMUNICATIONS CENTER | 2013-01-22 | 2013-03-20 | LBB Kaiserslautern | 22708.5465 | 17048.8816 |  | 2016-03-09 | 2016-03-08 | 2016-03-08 | 0%
2013-04-15 | 2012 | Army Active | Major Construction | GM | GERMANY | VILSECK | 069615 | BARRACKS | 2012-06-01 | 2012-09-27 | Bundeskasse Trier | 17668.7874 | 13261.1894 | 2012-10-10 | 2014-10-28 | 2014-08-27 | 2014-08-27 | 2
2013-04-15 | 2012 | Army Active | Major Construction | NY | NEW YORK | FORT DRUM | 058005 | AMMUNITION SUPPLY POINT | 2011-12-22 | 2012-04-17 | Black Horse Group | 4680.9 | 4680.9 | 2012-05-18 | 2013-11-13 | 2013-08-15 | 2013-08-15 | 25
2013-04-15 | 2012 | Army Active | Major Construction | MD | MARYLAND | FORT MEADE | 064939 | APPLIED INSTRUCTION FACILITY | 2012-06-20 | 2012-09-24 | Grimberg/Amatea JV | 30554 | 30554 | 2012-11-20 | 2015-01-22 | 2014-11-20 | 2014-11-20 | 3
2013-04-15 | 2012 | Army Active | Major Construction | GM | GERMANY | GRAFENWOEHR GERMANY | 065129 | CONVOY LIVE FIRE RANGE | 2012-08-17 08:00 | 2012-10-29 | Bundeskasse Trier | 3406.8394 | 2557.182 | 2012-10-29 | 2013-12-30 | 2014-05-15 | 2014-05-15 | 32
2013-04-15 | 2012 | Army Active | Major Construction | MD | MARYLAND | ABERDEEN PROVING GROUND | 066750 | AUTO TECHNOLOGY EVALUATION FAC, PH 3 | 2012-07-12 | 2012-09-28 | Meltech/W.M.Schlosser, LLC B, Joint Venture | 12988 | 13018 | 2012-10-17 | 2014-07-15 | 2014-04-15 | 2014-04-15 | 6
2013-04-15 | 2012 | Army Active | Major Construction | GM | GERMANY | OBERDACHSTATTEN GERMANY | 071906 | AUTOMATED RECORD FIRE RANGE | 2012-11-16 | 2013-01-22 | Staatliches Hochbauamt Nurnberg II | 9782.4347 | 7353.9774 | 2013-02-06 | 2014-06-20 | 2014-05-16 | 2014-05-16 | 4
2013-04-15 | 2012 | Army Active | Major Construction | VA | VIRGINIA | JOINT BASE LANGLEY-EUSTIS | 059005 | AVIATION TRAINING FACILITY | 2012-03-20 08:00 | 2012-05-16 | Oyster Point Construction | 13849 | 14020.086 | 2012-06-14 | 2013-12-13 | 2013-12-06 | 2013-12-13 | 28
2013-04-15 | 2012 | Army Active | Major Construction | TU | TURKEY | TURKEY VARIOUS | 079749 | FORWARD OPERATING SITE | 2012-06-15 17:00 | 2012-08-30 | EMTA INSAAT A.S | 12129.1464 | 12449.0483 | 2012-09-13 | 2014-04-06 | 2014-02-05 | 2014-02-05 | 0
2013-04-15 | 2012 | Army Active | Major Construction - AFH | GM | GERMANY | ANSBACH, GERMANY | 079097 | FAMILY HOUSING IMPROVEMENTS | 2013-02-04 17:00 | 2012-09-13 | Klebl GmbH | 17917.1392 | 13421.729 | 2012-10-15 | 2018-05-11 | 2018-04-02 | 2018-04-02 | 4
2013-04-15 | 2012 | Army Active | Major Construction - AFH | GM | GERMANY | ANSBACH, GERMANY | 078841 | FAMILY HOUSING IMPROVEMENTS | 2013-02-04 17:00 | 2012-09-13 | Klebl GmbH | 20428.5583 | 15303.033 | 2012-10-15 | 2018-12-07 | 2018-10-29 | 2018-10-29 | 3
2013-04-15 | 2009 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 070102 | CHILD DEVELOPMENT CENTER | 2009-08-03 17:00 | 2009-09-16 | Pease Construction, Inc. | 20178.729 | 26180.4245 | 2009-10-20 | 2013-07-15 | 2011-11-01 | 2013-02-16 | 94
2013-04-15 | 2010 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 065133 | BRIGADE COMPLEX | 2011-05-16 | 2011-07-15 | Better Built Construction Services Inc. | 13542 | 41238.9776 | 2011-08-15 | 2013-05-27 | 2012-10-28 | 2013-03-28 | 87
2013-04-15 | 2010 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 065935 | BRIGADE COMPLEX, INC 4 | 2009-04-13 08:00 | 2011-09-22 | Bristol Engineering Services Corporation | 0 | 6032.8481 | 2012-01-15 | 2013-11-12 | 2013-08-25 | 2013-09-13 | 59
2013-04-15 | 2011 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 057194 | BARRACKS | 2010-12-15 | 2011-12-23 | Hunt Building Company, LTD | 19471.9 | 19946.119 | 2012-01-26 | 2013-09-30 | 2013-06-19 | 2013-08-12 | 61
2013-04-15 | 2011 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 055198 | BARRACKS COMPLEX | 2010-12-01 08:00 | 2011-09-26 | MEGEN Construction Co., INC. | 11816 | 30481.79 | 2012-02-15 | 2013-09-03 | 2013-07-05 | 2013-07-05 | 71
2013-04-15 | 2011 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 067137 | BRIGADE COMPLEX | 2011-03-18 | 2011-05-19 | TEPA EC, LLC | 14407.47 | 46293.0589 | 2011-06-07 | 2013-06-16 | 2012-11-28 | 2013-06-02 | 91
2013-04-15 | 2011 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 067137 | BRIGADE COMPLEX | 2011-03-18 | 2011-05-19 | M.A. Mortenson Company dba Mortenson Construction Co. | 6529 | 46293.0589 | 2011-06-20 | 2013-08-18 | 2013-03-11 | 2013-06-19 | 98
2013-04-15 | 2011 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 065009 | GENERAL INSTRUCTION BUILDING | 2010-09-25 | 2011-05-18 | TMG Services, Inc. | 6615.899 | 7263.359 | 2011-06-20 | 2013-04-14 | 2012-12-11 | 2013-04-14 | 95
2013-04-15 | 2011 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 068721 | TRANSIENT ADVANCED TRAINEE BARRACKS, PH 2 | 2011-02-15 | 2011-05-24 | MW Builders of Texas, Inc. | 18943 | 26031.776 | 2011-06-23 | 2013-09-22 | 2012-11-04 | 2013-05-25 | 99
2013-04-15 | 2011 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 065386 | SNIPER FIELD FIRE RANGE | 2012-02-23 | 2012-04-09 | Vet Industrial | 3610.997 | 3618.903 | 2012-04-25 | 2013-06-24 | 2013-04-25 | 2013-04-25 | 98
2013-04-15 | 2011 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 064520 | INFORMATION SYSTEMS FACILITY | 2010-10-22 17:00 | 2011-05-27 | Curtiss Manes Schulte, Inc. | 12605.318 | 13774.688 | 2011-07-12 | 2013-05-14 | 2012-12-03 | 2013-05-14 | 93
2013-04-15 | 2011 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 065460 | AUTOMATED QUALIFICATION/TRAINING RANGE | 2011-05-10 17:00 | 2011-08-04 | Zieson Construction Company, LLC | 4696.958 | 5315.11 | 2011-09-08 | 2013-08-18 | 2012-11-21 | 2013-08-18 | 82
2013-04-15 | 2011 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 065714 | BATTALION COMPLEX, PH 1 | 2011-04-27 | 2011-05-13 | Alutiiq International Solutions, LLC | 7138.55 | 22948.14 | 2011-06-01 | 2013-06-21 | 2012-08-24 | 2013-05-22 | 86
2013-04-15 | 2011 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 064457 | BARRACKS | 2011-07-11 08:00 | 2011-09-26 | Archer Western Contractors, LTD | 31747 | 61791.8949 | 2011-11-07 | 2013-11-04 | 2013-05-20 | 2013-09-05 | 85
2013-04-15 | 2011 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 064457 | BARRACKS | 2011-07-11 08:00 | 2011-09-22 | Bristol Engineering Services Corporation | 26919.634 | 61791.8949 | 2012-01-15 | 2013-11-12 | 2013-08-25 | 2013-09-13 | 59
2013-04-15 | 2011 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 013852 | SIMULATIONS CENTER | 2011-07-15 | 2011-09-14 | Native American Services Corp. | 27829.194 | 28806.967 | 2011-11-04 | 2013-11-24 | 2013-04-27 | 2013-09-25 | 54
2013-04-15 | 2011 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 065171 | KNOWN DISTANCE RANGE | 2011-05-10 17:00 | 2011-08-04 | Zieson Construction Company, LLC | 4653.926 | 5035.974 | 2011-09-08 | 2013-08-18 | 2012-11-21 | 2013-08-18 | 82
2013-04-15 | 2011 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 072055 | BRIGADE HEADQUARTERS | 2010-10-19 17:00 | 2011-05-18 | Major ConstructionructionTech Corp | 10563 | 11034.777 | 2011-06-16 | 2013-04-26 | 2012-10-28 | 2013-04-17 | 97
2013-04-15 | 2011 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 072838 | REGIONAL LOGISTIC SPT COMPLEX WAREHOUSE | 2011-08-16 | 2011-09-28 | Innovative Technical Solutions, Inc. | 23442.954 | 24700.38 | 2011-10-12 | 2013-09-15 | 2013-04-04 | 2013-04-04 | 50
2013-04-15 | 2011 | Army Active | Major Construction | WA | WASHINGTON | FORT LEWIS | 072854 | REGIONAL LOGISTIC SUPPORT COMPLEX | 2012-11-09 08:00 | 2013-01-22 | Garco Construction, Inc. | 36247 | 36247 | 2013-02-13 | 2014-10-06 | 2014-08-07 | 2014-08-07 | 0
2013-04-15 | 2011 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 075078 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL | 2010-06-16 | 2011-05-19 | ASSET Group Inc. | 5873.409 | 5915.8434 | 2011-07-20 | 2013-05-31 | 2012-10-12 | 2012-11-05 | 87
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 058046 | OPERATIONAL READINESS TRAINING CPLX, PH 1 | 2012-06-29 17:00 | 2013-04-01 | TSS-Garco Joint Venture | 16416 | 16416 | 2013-04-16 | 2014-12-07 | 2014-10-08 | 2014-10-08 | 0
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 053637 | BRIGADE COMPLEX, PH 2 | 2012-03-30 | 2012-11-09 | MEGEN Construction Co., INC. | 14398 | 48644.842 | 2012-12-18 | 2014-07-17 | 2014-06-11 | 2014-06-11 | 0
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 053637 | BRIGADE COMPLEX, PH 2 | 2012-03-30 | 2012-06-07 | Bristol General Contractors, LLC | 19374.564 | 48644.842 | 2012-07-03 | 2013-09-01 | 2013-07-03 | 2013-07-03 | 27
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 053637 | BRIGADE COMPLEX, PH 2 | 2012-03-30 | 2012-06-14 | Archer Western Contractors, Ltd | 14691 | 48644.842 | 2012-06-29 | 2013-12-21 | 2013-10-22 | 2013-10-22 | 38
2013-04-15 | 2012 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 061211 | CHAPEL | 2011-11-22 | 2012-05-31 | TMG Services, Inc. | 7104.944 | 7213.603 | 2012-06-29 | 2013-12-01 | 2013-08-25 | 2013-10-02 | 28
2013-04-15 | 2012 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 064365 | VEHICLE MAINTENANCE FACILITY | 2012-02-03 | 2012-08-23 | KCI Construction Company | 30970 | 42208.84 | 2012-09-18 | 2014-05-11 | 2014-03-12 | 2014-03-12 | 9
2013-04-15 | 2012 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 064365 | VEHICLE MAINTENANCE FACILITY | 2012-02-03 | 2012-11-07 | Greenleaf Construction Co., Inc | 8541.461 | 42208.84 | 2013-04-30 | 2014-08-23 | 2014-06-24 | 2014-06-24 | 0
2013-04-15 | 2012 | Army Active | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 064365 | VEHICLE MAINTENANCE FACILITY | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | 2493.149 | 42208.84 | 2013-01-04 | 2014-02-10 | 2014-01-04 | 2014-01-04 | 1
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 060344 | AIR SUPPORT OPERATIONS FACILITIES | 2012-01-06 | 2012-03-09 | Performance Systems, Inc. | 7511.891 | 7515.619 | 2012-04-17 | 2013-09-29 | 2013-07-31 | 2013-08-15 | 26
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 064014 | BATTALION COMPLEX | 2012-11-05 08:00 | 2012-06-28 | M.A. Mortenson Company | 19332 | 43207.901 | 2012-07-25 | 2014-01-16 | 2013-11-17 | 2013-11-17 | 56
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 064014 | BATTALION COMPLEX | 2012-11-05 08:00 | 2013-01-03 | TSS-Garco Joint Venture | 8912 | 43207.901 | 2013-02-12 | 2014-10-05 | 2014-08-06 | 2014-08-06 | 0
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 064014 | BATTALION COMPLEX | 2012-11-05 08:00 | 2012-09-21 | 3D Contracting Inc. | 14649 | 43207.901 | 2012-11-30 | 2014-07-23 | 2014-05-24 | 2014-05-24 | 1
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 066206 | INFRASTRUCTURE, PH 1 | 2012-08-22 08:00 | 2013-01-25 | CeSight Joint Venture | 13775.4 | 31628.212 | 2013-03-01 | 2014-10-22 | 2014-08-23 | 2014-08-23 | 1
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 066206 | INFRASTRUCTURE, PH 1 | 2012-08-22 08:00 | 2012-08-29 | Alutiiq Diversified Services, LLC | 10525 | 31628.212 | 2012-09-17 | 2014-05-10 | 2014-03-11 | 2014-03-11 | 4
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 066206 | INFRASTRUCTURE, PH 1 | 2012-08-22 08:00 | 2012-09-28 | Vet Industrial, Inc. | 4980.322 | 31628.212 | 2012-11-05 | 2013-12-30 | 2013-10-31 | 2013-10-31 | 39
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 066206 | INFRASTRUCTURE, PH 1 | 2012-08-22 08:00 | 2012-09-28 | Bristol General Contractors, LLC | 1979.415 | 31628.212 | 2012-11-01 | 2013-05-15 | 2013-05-30 | 2013-05-30 | 48
2013-04-15 | 2012 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 059148 | DEPLOYMENT SUPPORT FACILITY | 2012-02-01 | 2012-03-23 | Alexander-Weitz JV | 3901.252 | 3941.315 | 2012-04-10 | 2013-06-09 | 2013-04-10 | 2013-04-10 | 89
2013-04-15 | 2012 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 002728 | PHYSICAL FITNESS FACILITY | 2011-12-09 17:00 | 2012-03-16 | Better Built Construction Services Inc. | 11660 | 11650.376 | 2012-03-29 | 2013-11-19 | 2013-09-20 | 2013-09-20 | 15
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 076767 | AVIATION UNIT COMPLEX, PH 1A | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | 24162 | 24356.151 | 2012-07-09 | 2014-03-01 | 2013-12-31 | 2014-02-18 | 12
2013-04-15 | 2012 | Army Active | Major Construction | WA | WASHINGTON | JOINT BASE LEWIS-MAJOR CONSTRUCTIONRUCTIONCHORD | 076768 | AVIATION COMPLEX, PH 1B | 2012-08-20 08:00 | 2012-09-28 | CJW Construction, Inc. | 12950.4 | 12950.4 | 2012-11-29 | 2014-07-22 | 2014-05-23 | 2014-05-23 | 0
2013-04-15 | 2012 | Army Active | Major Construction | KS | KANSAS | FORT RILEY | 069834 | UNMANNED AERIAL VEHICLE MAINTENANCE HANGAR | 2013-07-31 17:00 | 2012-11-01 | Greenleaf Construction Co., Inc | 5932.641 | 5932.641 | 2012-12-11 | 2014-06-24 | 2014-03-16 | 2014-03-16 | 2
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 065602 | BRIGADE HEADQUARTERS | 2012-02-07 08:00 | 2012-09-26 | Hensel Phelps Construction Company | 0 | 10532.611 | TBD | 2014-08-21 | 2014-06-22 | 2014-06-22 | 0
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 065602 | BRIGADE HEADQUARTERS | 2012-02-07 08:00 | 2012-03-30 | Komada, LLC | 9947 | 10532.611 | 2012-04-18 | 2013-12-06 | 2013-07-12 | 2013-10-07 | 51
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077265 | BARRACKS | 2012-06-01 | 2012-09-26 | Hensel Phelps Construction Company | 0 | 0 | TBD | 2014-08-21 | 2014-06-22 | 2014-06-22 | 0
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077264 | BARRACKS | 2012-06-01 | 2012-09-26 | Hensel Phelps Construction Company | 0 | 0 | TBD | 2014-08-21 | 2014-06-22 | 2014-06-22 | 0
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077306 | AIRCRAFT MAINTENANCE HANGAR | 2012-01-17 08:00 | 2012-09-26 | Hensel Phelps Construction Company | 98674 | 144531.345 | TBD | 2014-08-21 | 2014-06-22 | 2014-06-22 | 0
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077306 | AIRCRAFT MAINTENANCE HANGAR | 2012-01-17 08:00 | 2012-08-09 | Hensel Phelps Construction Company | 44801 | 144531.345 | 2012-08-23 | 2014-05-06 | 2014-02-14 | 2014-03-07 | 9
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077302 | CONTROL TOWER | 2012-02-22 17:00 | 2012-09-26 | Hensel Phelps Construction Company | 0 | 10954.421 | TBD | 2014-08-21 | 2014-06-22 | 2014-06-22 | 0
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077302 | CONTROL TOWER | 2012-02-22 17:00 | 2012-08-02 | Hensel Phelps Construction Co. | 10891 | 10954.421 | 2012-08-27 | 2014-03-30 | 2014-01-05 | 2014-01-29 | 16
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077319 | AIRCRAFT LOADING AREA | 2012-04-06 17:00 | 2012-09-19 | Komada, LLC | 6524.909 | 31936.439 | 2012-10-10 | 2013-12-09 | 2013-10-10 | 2013-10-10 | 16
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077319 | AIRCRAFT LOADING AREA | 2012-04-06 17:00 | 2012-08-10 | Loyd Contracting Co., Inc. | 18222 | 31936.439 | 2012-09-07 | 2013-11-06 | 2013-09-07 | 2013-09-07 | 15
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077319 | AIRCRAFT LOADING AREA | 2012-04-06 17:00 | 2012-08-09 | Hartland/Mass JV, LLC | 3212.3 | 31936.439 | 2012-09-06 | 2013-11-05 | 2013-09-06 | 2013-09-06 | 1
2013-04-15 | 2012 | Army Active | Major Construction | CO | COLORADO | FORT CARSON | 077319 | AIRCRAFT LOADING AREA | 2012-04-06 17:00 | 2012-08-13 | Komada, LLC | 3832.74 | 31936.439 | 2012-09-05 | 2013-11-29 | 2013-09-05 | 2013-09-30 | 26
2013-04-15 | 2012 | Army Active | Minor Construction | KS | KANSAS | FORT RILEY | 071259 | INFILL AN EXISTING AREA OF EXISTING RAMP AT MANHATTAN AIRPORT | 2012-08-13 17:00 | 2012-09-24 | K & P Construction, LLC | 1486.711 | 1486.711 | 2012-10-12 | 2013-10-07 | 2013-08-08 | 2013-08-08 | 1
2013-04-15 | 2011 | Army Active | Major Construction | AK | ALASKA | FORT GREELY | 055873 | FIRE STATION | 2010-10-01 | 2012-09-17 | C.I. Contractors INC. | 692.182 | 18246.011 | 2012-09-26 | 2013-07-01 | 2013-02-03 | 2013-02-21 | 94
2013-04-15 | 2011 | Army Active | Major Construction | AK | ALASKA | FORT RICHARDSON | 057369 | SIMULATIONS CENTER | 2010-10-04 17:00 | 2011-05-11 | UNIT COMPANY | 20025.555 | 21815.551 | 2011-05-18 | 2013-07-29 | 2013-05-17 | 2013-07-29 | 94
2013-04-15 | 2011 | Army Active | Major Construction | AK | ALASKA | FORT WAINWRIGHT | 067112 | AVIATION TASK FORCE COMPLEX, PH 2A (HNGAR) | 2010-07-19 17:00 | 2011-05-10 | Watterson Construction Company | 67814 | 67402.869 | 2011-05-17 | 2013-08-14 | 2013-08-14 | 2013-09-22 | 95
2013-04-15 | 2011 | Army Active | Major Construction | AK | ALASKA | FORT RICHARDSON | 055695 | BRIGADE COMPLEX, PH 1 | 2011-03-01 17:00 | 2011-05-11 | Korte-Purcell JV | 23898.777 | 47822.2155 | 2011-05-25 | 2013-05-12 | 2013-03-24 | 2013-05-12 | 90
2013-04-15 | 2012 | Army Active | Major Construction | AK | ALASKA | FORT RICHARDSON | 061515 | PHYSICAL FITNESS FACILITY | 2011-10-19 17:00 | 2012-06-22 | Bethel Federal Services LLC | 0 | 22592.771 | 2012-07-03 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 0
2013-04-15 | 2012 | Army Active | Major Construction | AK | ALASKA | FORT RICHARDSON | 061515 | PHYSICAL FITNESS FACILITY | 2011-10-19 17:00 | 2012-11-07 | Bristol General Contractors, LLC | 21813.389 | 22592.771 | 2013-03-16 | 2014-05-24 | 2014-12-06 | 2014-12-06 | 0
2013-04-15 | 2012 | Army Active | Major Construction | AK | ALASKA | FORT WAINWRIGHT | 067113 | AVIATION COMPLEX, PH 3A | 2011-07-15 17:00 | 2012-06-07 | Watterson Construction Company | 70591 | 46959.837 | 2012-06-14 | 2014-10-15 | 2014-08-03 | 2014-09-16 | 10
2013-04-15 | 2012 | Army Active | Major Construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | 072270 | BRIGADE COMPLEX, PH 2 | 2011-12-22 08:00 | 2012-05-03 | KICC - Alcan General JV | 23170.1 | 51135.504 | 2012-05-16 | 2013-12-27 | 2013-12-27 | 2014-01-11 | 37
2013-04-15 | 2012 | Army Active | Major Construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | 072270 | BRIGADE COMPLEX, PH 2 | 2011-12-22 08:00 | 2012-02-02 | UNIT COMPANY | 24839.9 | 51135.504 | 2012-02-10 | 2014-02-25 | 2014-02-09 | 2014-02-09 | 59
2013-04-15 | 2012 | Army Active | Major Construction | AK | ALASKA | JOINT BASE ELMENDORF-RICHARDSON | 072270 | BRIGADE COMPLEX, PH 2 | 2011-12-22 08:00 | 2012-02-02 | ANCOR, INC. | 2353 | 51135.504 | 2012-04-06 | 2013-06-17 | 2012-08-14 | 2013-06-17 | 90
2013-04-15 | 2009 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 068786 | BRIGADE COMPLEX | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 26656 | 26777.518 | 2011-04-15 | 2014-03-28 | 2014-03-14 | 2014-03-14 | 56
2013-04-15 | 2009 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 068821 | BATTALION COMPLEX | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 31084 | 31695.576 | 2011-04-15 | 2014-03-28 | 2014-03-14 | 2014-03-14 | 56
2013-04-15 | 2009 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 068822 | BATTALION COMPLEX | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 9840 | 9961.518 | 2011-04-15 | 2014-03-28 | 2014-03-14 | 2014-03-14 | 56
2013-04-15 | 2009 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 069308 | INFRASTRUCTURE EXPANSION | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | 60385 | 61060.844 | 2011-04-15 | 2014-03-28 | 2014-03-14 | 2014-03-14 | 56
2013-04-15 | 2010 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 055274 | VEHICLE MAINTENANCE SHOP | 2010-09-21 | 2011-02-25 | Walsh RMA Joint Venture | 37872 | 38118.344 | 2011-03-28 | 2013-06-17 | 2013-04-17 | 2013-04-17 | 88
2013-04-15 | 2010 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 055281 | VEHICLE MAINTENANCE SHOP | 2010-06-30 17:00 | 2010-09-17 | Ledcor Construction Hawaii LLC | 15366 | 16180.879 | 2010-10-27 | 2013-05-03 | 2012-10-18 | 2013-04-19 | 90
2013-04-15 | 2010 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 069521 | WARRIOR IN TRANSITION (WT) BARRACKS | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 32745.37 | 32978.588 | 2011-07-27 | 2014-07-10 | 2013-10-12 | 2013-10-12 | 18
2013-04-15 | 2010 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 071553 | WARRIOR IN TRANSITION COMPLEX | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | 26339.63 | 26458.002 | 2011-07-27 | 2014-07-10 | 2013-10-12 | 2013-10-12 | 18
2013-04-15 | 2011 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 052267 | BARRACKS | 2010-11-30 | 2011-06-30 | Absher Construction Company | 35275.888 | 64360.119 | 2011-08-29 | 2013-10-24 | 2013-08-29 | 2013-10-10 | 66
2013-04-15 | 2011 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 052267 | BARRACKS | 2010-11-30 | 2011-09-01 | SUMO-NAN LLC | 28024.553 | 64360.119 | 2011-10-28 | 2013-10-28 | 2013-10-17 | 2013-10-17 | 47
2013-04-15 | 2011 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 052269 | BARRACKS | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | 41466.255 | 41467.942 | 2011-10-17 | 2014-07-30 | 2013-10-14 | 2014-07-16 | 12
2013-04-15 | 2011 | Army Active | Major Construction | HI | HAWAII | FORT SHAFTER | 056024 | FLOOD MITIGATION | 2012-06-29 | 2012-09-25 | Nan, Inc. dba Ocean House Builders | 21105.273 | 21105.273 | 2012-10-17 | 2015-02-05 | 2014-10-14 | 2014-10-14 | 1
2013-04-15 | 2011 | Army Active | Major Construction | HI | HAWAII | TRIPLER ARMY MEDICAL CENTER | 067258 | BARRACKS | 2010-12-20 17:00 | 2011-05-25 | SUMO-NAN LLC | 15996.619 | 16530.512 | 2011-06-15 | 2014-03-28 | 2013-09-12 | 2013-12-12 | 27
2013-04-15 | 2011 | Army Active | Major Construction | HI | HAWAII | FORT SHAFTER | 065650 | COMMAND AND CONTROL FACILITY, PH 1 | 2011-11-04 | 2012-02-28 | Niking Corporation | 46780 | 47421.369 | 2012-04-03 | 2014-10-03 | 2014-04-23 | 2014-08-03 | 17
2013-04-15 | 2011 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 064760 | TRAINING AIDS CENTER | 2012-06-29 | 2012-09-19 | SRB International LLC | 13310.008 | 13310.008 | 2012-10-31 | 2014-10-21 | 2014-08-17 | 2014-08-17 | 0
2013-04-15 | 2011 | Army Active | Minor Construction | HI | HAWAII | SCHOFIELD BARRACKS | 065454 | POLICE/MP STATION | 2011-08-26 | 2011-11-10 | Polu Kai Services, LLC | 1404.5127 | 1432.3857 | 2012-01-04 | 2013-05-15 | 2013-01-03 | 2013-01-05 | 68
2013-04-15 | 2012 | Army Active | Major Construction | HI | HAWAII | FORT SHAFTER | 064967 | CHILD DEVELOPMENT CENTER | 2011-10-06 | 2012-02-27 | 57 Builders, Ltd. | 9573.118 | 9575.531 | 2012-03-23 | 2014-06-11 | 2013-12-13 | 2013-12-13 | 5
2013-04-15 | 2012 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 069489 | COMBAT AVIATION BRIGADE COMPLEX, PH 1 | 2012-01-24 | 2012-06-29 | David Boland, Inc. | 54772 | 54772 | 2012-07-30 | 2015-09-30 | 2015-05-27 | 2015-05-27 | 5
2013-04-15 | 2012 | Army Active | Major Construction | HI | HAWAII | SCHOFIELD BARRACKS | 059581 | CENTRALIZED WASH FACILITY | 2011-10-13 08:00 | 2012-01-27 | Watts Constructors, LLC | 28300 | 28525.121 | 2012-02-08 | 2014-02-11 | 2013-12-14 | 2013-12-14 | 37
2013-04-15 | 2008 | Army Active | Major Construction | KR | KOREA | HUMPHREYS, KOREA | 058784 | BARRACKS COMPLEX | 2012-02-02 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | 5457.7516 | 5457.7516 | 2012-09-17 | 2014-10-06 | 2014-03-16 | 2014-08-02 | 0 |  | Per contract, site not available until 29-Mar-13
2013-04-15 | 2008 | Army Active | Major Construction | KR | KOREA | HUMPHREYS, KOREA | 058784 | BARRACKS COMPLEX | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | 32468.604 | 32468.604 | 2012-09-17 | 2014-10-06 | 2014-09-07 | 2014-09-07 | 4 |  | Per contract, site was not available until 29-Jan-13.
2013-04-15 | 2010 | Army Active | Major Construction | KR | KOREA | HUMPHREYS, KOREA | 060783 | FIRE STATIONS | 2009-11-20 | 2010-02-05 | Namkwang Construction Co., Ltd. | 9688.181 | 13235011.662 | 2010-04-07 | 2013-04-01 | 2011-12-08 | 2012-10-08 | 21 |  | T4D (8 Jun 12) - Namkwang Construction Co., Ltd.; project being completed by Il Kwang Engr. & Cons. Co., Ltd.
2013-04-15 | 2010 | Army Active | Major Construction | KR | KOREA | HUMPHREYS, KOREA | 060783 | FIRE STATIONS | 2009-11-20 | 2012-07-26 | Il Kwang Engr. & Cons. Co., Ltd. | 7385.2095 | 13235011.662 | 2012-07-26 | 2013-07-26 | 2013-04-22 | 2013-07-26 | 60
2013-04-15 | 2011 | Army Active | Major Construction | KR | KOREA | CAMP WALKER KOREA | 061551 | ELECTRICAL SYS UPGRADE & NATURAL GAS SYS | 2010-11-04 08:00 | 2011-05-13 | Lim kwang Engr. & Const. Co., Ltd. | 15608.2713 | 20537633.708 | 2011-05-13 | 2013-08-17 | 2013-02-01 | 2013-09-10 | 93
2013-04-15 | 2012 | Army Active | Major Construction | KR | KOREA | CAMP HENRY/GEORGE, KOREA | 076235 | BARRACKS COMPLEX | 2012-02-02 | 2012-04-06 | Fine Construction Co., Ltd. | 28609.5284 | 31599274.305 | 2012-04-06 | 2014-07-22 | 2014-06-22 | 2014-06-25 | 6
2013-04-15 | 2012 | Army Active | Major Construction | KR | KOREA | CAMP HENRY/GEORGE, KOREA | 076235 | BARRACKS COMPLEX | 2012-02-02 | 2012-02-09 | Hanmi C&E Co., LTD. | 72.2037 | 31599274.305 | 2012-02-09 | 2014-08-02 | 2014-07-02 | 2014-07-02 | 27
2013-04-15 | 2012 | Army Active | Major Construction | KR | KOREA | CAMP CARROLL, KOREA | 072650 | BARRACKS | 2011-11-10 | 2012-02-24 | Samsung C&T Corporation | 27592.9923 | 30514535.651 | 2012-02-24 | 2016-01-05 | 2015-12-05 | 2015-12-07 | 8
2013-04-15 | 2012 | Army Active | Major Construction | KR | KOREA | CAMP CARROLL, KOREA | 072650 | BARRACKS | 2011-11-10 | 2012-02-27 | Hanmi C&E Co., LTD. | 63.7852 | 30514535.651 | 2012-02-27 | 2015-11-30 | 2015-10-31 | 2015-10-31 | 0
2013-04-15 | 2012 | Army Active | Minor Construction | RM | MARSHALL ISLANDS | KWAJALEIN ATOLL | 080026 | SECONDARY WASTE WATER TREATMENT | 2012-09-06 | 2012-09-28 | San Juan Construction, Inc. | 1399.217 | 1399.217 | 2012-10-25 | 2014-03-31 | 2014-01-29 | 2014-01-29 | 1
2013-04-15 | 2008 | Army Active | Major Construction | AL | ALABAMA | ANNISTON ARMY DEPOT, AL | 027259 | INDUSTRIAL WASTE WATER TREATMENT PLANT | 2012-03-22 17:00 | 2012-06-07 | Southeastern Industrial Construction Co., Inc. | 1860.159 | 1860.159 | 2012-06-28 | 2013-09-26 | 2013-06-28 | 2013-06-28 | 97
2013-04-15 | 2008 | Army Active | Major Construction | GA | GEORGIA | FORT STEWART | 068796 | QUARTERMASTER UNIT OPERATIONS FACILITIES | 2009-08-10 | 2011-03-31 | The Davis Group, Inc. | 6136.067 | 6136.067 | 2011-08-12 | 2013-05-04 | 2013-02-02 | 2013-02-02 | 99
2013-04-15 | 2008 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 068818 | AMMUNITION SUPPLY POINT/VEH MAIN FAC | 2008-05-22 | 2012-05-10 | Barnhill Contracting Company | 551.67 | 551.67 | 2012-06-08 | 2013-06-28 | 2013-02-03 | 2013-02-03 | 90
2013-04-15 | 2013 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 080087 | STORAGE BUILDING, GENERAL PURPOSE | 2012-07-16 08:00 | 2013-03-22 | Tyler Construction Group, Inc. | 9037.592 | 9037.592 |  | 2014-07-29 | 2014-07-29 | 2014-07-29 | 0
2013-04-15 | 2009 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 069742 | TRAINING AREA INFRASTRUCTURE-NORTHERN AREA | 2009-11-23 | 2012-12-03 | Komada, LLC | 3199.854 | 17091.169 | 2012-12-19 | 2014-01-18 | 2013-12-19 | 2013-12-19 | 23
2013-04-15 | 2009 | Army Active | Major Construction - OCO | MS | MISSISSIPPI | MISSISSIPPI ARMY AMMO PLANT | 075436 | MAJOR CALIBER LOADING PLANT | 2010-06-30 08:00 | 2010-07-01 | Speegle Construction, Inc. | 9182 | 39895.7437 | 2010-11-29 | 2013-09-23 | 2011-11-29 | 2013-09-23 | 67
2013-04-15 | 2009 | Army Active | Major Construction - OCO | MS | MISSISSIPPI | MISSISSIPPI ARMY AMMO PLANT | 075436 | MAJOR CALIBER LOADING PLANT | 2010-06-30 08:00 | 2010-11-30 | Sauer, Incorporated | 27349.7 | 39895.7437 | 2011-01-12 | 2013-06-08 | 2012-07-05 | 2013-06-08 | 94
2013-04-15 | 2009 | Army Active | Major Construction - OCO | MS | MISSISSIPPI | MISSISSIPPI ARMY AMMO PLANT | 075436 | MAJOR CALIBER LOADING PLANT | 2010-06-30 08:00 | 2010-12-08 | SpecPro Environmental Services, LLC | 2675.21 | 39895.7437 | 2010-12-08 | 2012-10-28 | 2011-12-08 | 2013-04-29 | 96
2013-04-15 | 2010 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 065557 | TRAINING AREA TANK TRAILS | 2010-05-28 08:00 | 2012-12-03 | Komada, LLC | 0 | 9448.3986 | 2012-12-19 | 2014-01-18 | 2013-12-19 | 2013-12-19 | 23
2013-04-15 | 2010 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 068759 | AUTOMATED MULTIPURPOSE MACHINE GUN | 2010-11-29 08:00 | 2011-06-30 | Trend Construction, Inc. | 5975.7354 | 6070.185 | 2011-08-31 | 2013-05-21 | 2013-02-21 | 2013-02-21 | 97
2013-04-15 | 2010 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 069150 | TRAINING BATTALION COMPLEX | 2009-11-24 | 2012-08-23 | Brasfield & Gorrie LLC | 21400 | 35112.7256 | 2012-09-20 | 2014-10-26 | 2014-08-21 | 2014-08-21 | 15
2013-04-15 | 2010 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 069417 | TRAINING BATTALION COMPLEX | 2009-11-03 | 2010-06-24 | Balfour Beatty Construction, LLC | 43613.85 | 49104.8417 | 2010-07-27 | 2013-10-01 | 2013-06-03 | 2013-10-01 | 86
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 057836 | STAGING AREA COMPLEX | 2011-02-18 08:00 | 2011-06-06 | SFL+A Architects, PA | 12614.6 | 13320.8096 | 2011-06-21 | 2013-08-24 | 2012-12-12 | 2013-03-27 | 98
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 053555 | BRIGADE COMPLEX | 2011-05-24 | 2011-09-19 | Polote Corp. | 10869 | 38675.256 | 2012-03-15 | 2013-10-08 | 2013-05-09 | 2013-08-09 | 41
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 053555 | BRIGADE COMPLEX | 2011-05-24 | 2011-09-16 | Atlantic Marine Construction Company, Inc | 1209.6245 | 38675.256 | 2011-11-29 | 2014-07-31 | 2012-11-28 | 2014-05-02 | 44
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 053555 | BRIGADE COMPLEX | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | 15752.3734 | 38675.256 | 2011-11-21 | 2014-04-20 | 2014-01-29 | 2014-02-19 | 77
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 053555 | BRIGADE COMPLEX | 2011-05-24 | 2011-12-09 | H-S Joint Venture, LLC | 10469.241 | 38675.256 | 2012-01-05 | 2013-09-28 | 2013-06-28 | 2013-07-14 | 55
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 057317 | BATTALION COMPLEX | 2011-05-24 | 2011-09-19 | Polote Corp. | 3908 | 18018.2806 | 2012-03-15 | 2013-10-08 | 2013-05-09 | 2013-08-09 | 41
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 057317 | BATTALION COMPLEX | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | 13850.4196 | 18018.2806 | 2011-11-21 | 2014-04-20 | 2014-01-29 | 2014-02-19 | 77
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 065204 | COMPANY OPERATIONS FACILITIES | 2011-03-07 | 2011-08-08 | Tyler Construction Group, Inc. | 8526 | 9878.5589 | 2011-09-08 | 2013-06-30 | 2013-03-01 | 2013-04-25 | 71
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 065204 | COMPANY OPERATIONS FACILITIES | 2011-03-07 | 2011-09-15 | Atlantic Marine Construction Company, Inc | 1352.2359 | 9878.5589 | 2011-11-29 | 2014-01-27 | 2013-01-22 | 2013-12-28 | 28
2013-04-15 | 2011 | Army Active | Major Construction | AL | ALABAMA | FORT RUCKER | 060459 | AVIATION MAINTENANCE FACILITY | 2010-11-22 17:00 | 2011-05-20 | Hensel Phelps Construction Company | 30495 | 31691.385 | 2011-08-08 | 2013-07-31 | 2013-07-28 | 2013-07-31 | 96
2013-04-15 | 2011 | Army Active | Major Construction | FL | FLORIDA | EGLIN AIR FORCE BASE | 071492 | CHAPEL | 2011-01-26 | 2011-06-30 | Barlovento LLC | 4992.44 | 5739.7856 | 2011-08-10 | 2013-03-29 | 2012-11-02 | 2013-04-19 | 92
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT STEWART | 072188 | AUTOMATED MULTIPURPOSE MACHINE GUN RANGE | 2010-12-03 | 2011-05-12 | Trend Construction, Inc. | 6457.6011 | 8492.2391 | 2011-05-25 | 2013-08-24 | 2012-05-24 | 2013-04-06 | 85
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 072456 | TRAINING BATTALION COMPLEX, PH 2 | 2011-07-20 08:00 | 2011-09-29 | IAP-Leopardo Construction, Inc. | 22100.1 | 22100.1 | 2011-10-13 | 2014-02-09 | 2013-04-05 | 2013-12-11 | 45
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 072457 | TRAINING BATTALION COMPLEX, PH 2 | 2011-07-20 08:00 | 2011-09-29 | IAP-Leopardo Construction, Inc. | 22157.9 | 22157.9 | 2011-10-13 | 2014-02-09 | 2013-04-05 | 2013-12-11 | 46
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 044968 | COMMAND AND CONTROL FACILITY | 2011-01-12 | 2011-06-13 | Sauer Inc. | 33708 | 35677.0257 | 2011-07-11 | 2013-12-19 | 2013-06-10 | 2013-09-20 | 86
2013-04-15 | 2011 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 053794 | TRAINEE BARRACKS COMPLEX, PH 1 | 2011-07-15 08:00 | 2011-08-30 | W. G. YATES & SONS CONSTRUCTION COMPANY | 20249.7 | 35304.198 | 2012-01-04 | 2013-10-07 | 2013-06-27 | 2013-10-07 | 73
2013-04-15 | 2011 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 053794 | TRAINEE BARRACKS COMPLEX, PH 1 | 2011-07-15 08:00 | 2012-04-16 | H-S JOINT VENTURE, LLC | 10186.85 | 35304.198 | 2012-07-13 | 2013-10-06 | 2013-07-08 | 2013-07-15 | 45
2013-04-15 | 2011 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 053794 | TRAINEE BARRACKS COMPLEX, PH 1 | 2011-07-15 08:00 | 2012-07-03 | LIFECYCLE CONSTRUCTION SERVICES, LLC | 2731.143 | 35304.198 | 2012-08-09 | 2013-11-02 | 2013-08-04 | 2013-08-04 | 52
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 064340 | BRIGADE COMPLEX | 2011-08-03 08:00 | 2011-09-23 | GSC Construction, Inc. | 4282.55 | 23763.1445 | 2011-11-17 | 2013-09-10 | 2013-02-09 | 2013-06-12 | 90
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 064340 | BRIGADE COMPLEX | 2011-08-03 08:00 | 2011-09-29 | Polote Corporation | 19315.777 | 23763.1445 | 2011-12-05 | 2013-09-30 | 2013-05-28 | 2013-08-27 | 48
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 064342 | BRIGADE COMPLEX | 2011-04-06 | 2011-06-02 | Walbridge Aldinger Company | 15158.7 | 30237.5874 | 2011-06-16 | 2013-08-23 | 2012-10-27 | 2013-03-26 | 99
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 064342 | BRIGADE COMPLEX | 2011-04-06 | 2011-08-29 | Better Built Construction Services, Inc. | 13311 | 30237.5874 | 2011-09-28 | 2013-09-21 | 2013-03-21 | 2013-09-07 | 67
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT STEWART | 069830 | AVIATION UNIT OPERATIONS COMPLEX | 2010-12-23 | 2011-06-22 | Sauer Inc. d/b/a Sauer Southeast | 27688 | 28872.124 | 2011-07-27 | 2013-05-23 | 2012-12-08 | 2013-05-06 | 79
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT STEWART | 071583 | BATTALION COMPLEX | 2011-04-28 | 2011-06-23 | Q.B.S.Incorporated | 12552.888 | 17262.537 | 2011-09-28 | 2013-10-03 | 2013-05-20 | 2013-07-05 | 76
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT STEWART | 071583 | BATTALION COMPLEX | 2011-04-28 | 2011-09-15 | Better Built Construction Services, Inc. | 4233 | 17262.537 | 2012-01-30 | 2013-06-03 | 2013-03-05 | 2013-03-05 | 99
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 072324 | TRAINEE BARRACKS PH 2 | 2010-10-26 08:00 | 2011-09-09 | Leebcor Services, LLC | 6994.184 | 16615.8278 | 2012-02-23 | 2013-07-17 | 2013-05-18 | 2013-05-18 | 91
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 072324 | TRAINEE BARRACKS PH 2 | 2010-10-26 08:00 | 2011-09-29 | Anthony and Gordon Construction Company, Inc | 7936 | 16615.8278 | 2011-11-07 | 2013-07-26 | 2013-04-30 | 2013-05-27 | 77
2013-04-15 | 2011 | Army Active | Major Construction | FL | FLORIDA | HOMESTEAD AIR FORCE BASE | 061533 | COMMAND AND CONTROL FACILITY | 2011-05-10 | 2011-07-29 | Carothers Construction, Inc. | 37718.1 | 39581.223 | 2011-09-20 | 2015-01-04 | 2014-10-06 | 2014-10-06 | 50
2013-04-15 | 2011 | Army Active | Major Construction | HO | HONDURAS | HONDURAS VARIOUS | 061383 | BARRACKS | 2011-05-18 17:00 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | 15146.5804 | 15114.0127 | 2012-01-10 | 2014-04-09 | 2014-01-09 | 2014-05-04 | 36
2013-04-15 | 2011 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 073299 | TRAINEE BARRACKS | 2011-01-14 08:00 | 2011-07-29 | CLARK CONSTRUCTION GROUP LLC | 16984 | 17402.154 | 2011-12-06 | 2013-07-20 | 2013-04-21 | 2013-06-20 | 86
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 073947 | VEHICLE MAINTENANCE SHOP | 2011-05-13 | 2011-06-29 | Bristol Design Build Services, LLC | 7490.722 | 7591.2 | 2011-08-18 | 2013-07-14 | 2013-02-08 | 2013-03-16 | 97
2013-04-15 | 2011 | Army Active | Major Construction | GA | GEORGIA | FORT STEWART | 039614 | SIMULATIONS CENTER | 2011-07-26 08:00 | 2011-09-12 | IAP-Leopardo Construction, Inc. | 17954.066 | 18038.2581 | 2011-10-12 | 2013-07-05 | 2013-04-04 | 2013-04-13 | 91
2013-04-15 | 2011 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 073930 | STUDENT BARRACKS | 2011-03-07 | 2011-08-08 | Tyler Construction Group, Inc. | 12754 | 12760.349 | 2011-09-08 | 2013-09-30 | 2013-03-01 | 2013-04-25 | 71
2013-04-15 | 2011 | Army Active | Major Construction | AL | ALABAMA | FORT RUCKER | 060463 | AVIATION COMPONENT MAINTENANCE SHOP | 2010-12-14 17:00 | 2011-05-18 | Carothers Construction, Inc | 19712.66 | 20119.006 | 2011-09-20 | 2013-08-01 | 2013-09-09 | 2013-09-25 | 90
2013-04-15 | 2011 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 071119 | TRAINING AIDS CENTER | 2011-06-03 17:00 | 2011-08-03 | PENTACON, LLC | 14999.9 | 15082.271 | 2011-09-08 | 2014-09-28 | 2013-03-01 | 2013-09-21 | 10
2013-04-15 | 2011 | Army Active | Minor Construction | GA | GEORGIA | FORT STEWART | 075601 | SENSITIVE COMPARTMENTED INFORMATION FAC | 2011-12-06 08:00 | 2012-04-26 | Brantley Construction Services LLC | 1649.25 | 1680.958 | 2012-05-22 | 2013-07-21 | 2013-05-22 | 2013-05-22 | 85
2013-04-15 | 2011 | Army Active | Minor Construction | AL | ALABAMA | FORT RUCKER | 075027 | EMERGENCY MEDICAL SERVICES FACILITY | 2011-08-19 08:00 | 2011-09-30 | ESA South, Inc. | 1700 | 1757.871 | 2011-12-08 | 2013-03-06 | 2012-12-08 | 2013-04-10 | 98
2013-04-15 | 2012 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 069745 | TRAINEE BARRACKS COMPLEX, PH 3 | 2011-12-16 | 2012-05-08 | Compton Construction Company, Inc. | 7898 | 7898 | 2012-05-18 | 2014-01-08 | 2013-11-09 | 2013-11-09 | 47
2013-04-15 | 2012 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 069745 | TRAINEE BARRACKS COMPLEX, PH 3 | 2011-12-16 | 2012-05-08 | Windamir Development, Inc | 11839.321 | 7898 |  | 2014-10-12 | 2014-08-13 | 2014-08-13 | 0
2013-04-15 | 2012 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 062955 | TRAINEE BARRACKS COMPLEX, PH 2 | 2012-02-16 | 2012-03-28 | CLARK CONSTRUCTION GROUP LLC | 44267 | 44267 | 2012-07-23 | 2014-04-14 | 2014-01-14 | 2014-03-27 | 29
2013-04-15 | 2012 | Army Active | Major Construction | GA | GEORGIA | FORT BENNING | 062953 | RAIL LOADING FACILITY | 2012-06-04 | 2012-08-14 | R. C. Construction Co., Inc. | 7409 | 7409.18 | 2012-09-05 | 2014-05-11 | 2014-02-27 | 2014-02-27 | 37
2013-04-15 | 2012 | Army Active | Major Construction | SC | SOUTH CAROLINA | FORT JACKSON | 067022 | MODIFIED RECORD FIRE RANGE | 2011-09-23 08:00 | 2012-06-29 | TREND CONSTRUCTION INC | 4375.259 | 4375.259 | 2012-09-06 | 2014-03-14 | 2013-12-30 | 2013-12-30 | 20
2013-04-15 | 2012 | Army Active | Major Construction | GA | GEORGIA | FORT GORDON, GA | 071705 | HAND GRENADE FAMILIARIZATION RANGE | 2011-12-16 | 2012-03-30 | Atkinson Incorporated | 1450 | 1491.9128 | 2012-04-19 | 2013-10-11 | 2013-04-19 | 2013-05-31 | 85
2013-04-15 | 2012 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 043335 | NCO ACADEMY | 2012-05-08 | 2012-07-30 | Caddell Construction CO., INC | 34647 | 34710.411 | 2012-10-03 | 2014-10-16 | 2014-07-15 | 2014-07-15 | 27
2013-04-15 | 2012 | Army Active | Major Construction | AL | ALABAMA | FORT RUCKER | 065429 | COMBAT READINESS CENTER | 2011-10-28 08:00 | 2012-01-25 | Bates Engineers/Contractors, Inc. | 8698 | 8878.554 | 2012-03-21 | 2014-04-10 | 2014-01-10 | 2014-02-03 | 60
2013-04-15 | 2012 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 070751 | BRIGADE COMPLEX FACILITIES | 2012-04-19 | 2012-01-26 | Balfour Beatty Construction, LLC | 10447 | 22251.423 | 2012-02-29 | 2013-11-22 | 2014-02-18 | 2014-02-18 | 68
2013-04-15 | 2012 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 070751 | BRIGADE COMPLEX FACILITIES | 2012-04-19 | 2012-06-29 | Brantley Construction Services, Inc. | 11681.588 | 22251.423 | 2012-07-31 | 2014-08-20 | 2014-07-21 | 2014-07-21 | 17
2013-04-15 | 2012 | Army Active | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 076958 | BATTLE COMMAND TRAINING CENTER | 2011-12-06 | 2012-02-01 | SFL+A Architects, PA | 17927.666 | 17877.1646 | 2012-03-01 | 2013-12-21 | 2013-08-23 | 2013-08-23 | 32
2013-04-15 | 2012 | Army Active | Major Construction | GA | GEORGIA | FORT STEWART | 062728 | DOG KENNEL | 2012-06-04 08:00 | 2012-09-27 | SEPI Engineering & Construction, Inc. | 2829.662 | 2829.662 | 2012-10-23 | 2014-01-05 | 2013-10-23 | 2013-10-23 | 4
2013-04-15 | 2011 | Army Active | Major Construction | CA | CALIFORNIA | PRESIDIO OF MONTEREY | 060285 | GENERAL INSTRUCTION BUILDING | 2010-10-07 17:00 | 2011-05-18 | RQ Construction, Inc. | 29886 | 32096.108 | 2011-06-07 | 2014-08-21 | 2013-05-24 | 2013-11-18 | 66
2013-04-15 | 2011 | Army Active | Major Construction | CA | CALIFORNIA | CAMP ROBERTS | 063015 | SATELLITE COMMUNICATIONS FACILITY | 2011-01-07 17:00 | 2011-08-30 | Watts/Webcor A JV | 34801.408 | 35283.472 | 2011-09-21 | 2015-05-15 | 2013-06-12 | 2013-10-22 | 3
2013-04-15 | 2011 | Army Active | Minor Construction | CA | CALIFORNIA | FORT IRWIN | 077876 | CREW/TES BATTERY FACILITY | 2011-11-16 08:00 | 2011-12-16 | Rick Garcia Construction Company | 1727.5 | 1878.015 | 2012-01-25 | 2013-04-23 | 2013-01-23 | 2013-02-13 | 98
2013-04-15 | 2012 | Army Active | Major Construction | UT | UTAH | DUGWAY PROVING GROUND | 055823 | LIFE SCIENCES TEST FACILITY ADDITION | 2012-04-12 17:00 | 2012-07-26 | Big-D Construction | 22608.566 | 22705.698 | 2012-08-29 | 2015-06-15 | 2015-02-15 | 2015-02-15 | 5
2013-04-15 | 2012 | Army Active | Major Construction | CA | CALIFORNIA | PRESIDIO OF MONTEREY | 056425 | GENERAL INSTRUCTION BUILDING | 2012-08-20 17:00 | 2012-09-29 | Souza Construction, Inc. | 2996 | 2996 | 2012-11-06 | 2014-03-12 | 2013-11-06 | 2013-11-06 | 0
2013-04-15 | 2012 | Army Active | Major Construction | CA | CALIFORNIA | FORT IRWIN | 070517 | QUALIFICATION TRAINING RANGE | 2012-02-14 17:00 | 2012-05-31 | Cox Construction Co. | 9599 | 9719.856 | 2012-07-24 | 2014-01-15 | 2014-02-14 | 2014-02-14 | 81
2013-04-15 | 2012 | Army Active | Major Construction | CA | CALIFORNIA | FORT IRWIN | 071707 | INFANTRY SQUAD BATTLE COURSE | 2011-11-01 08:00 | 2012-03-15 | Shanks Electric Corporation | 3387.6 | 3397.749 | 2012-04-16 | 2013-07-10 | 2013-04-11 | 2013-04-11 | 94
2013-04-15 | 2012 | Army Active | Major Construction | CA | CALIFORNIA | FORT IRWIN | 062657 | WATER TREATMENT PLANT | 2012-05-21 17:00 | 2012-09-12 | CDM Constructors, Inc. | 100112.66 | 100112.66 | 2012-10-19 | 2016-03-28 | 2015-10-19 | 2015-10-19 | 3
2013-04-15 | 2012 | Army Active | Minor Construction | AZ | ARIZONA | FORT HUACHUCA | 079959 | ANTENNA | 2012-04-23 17:00 | 2012-09-10 | KAYA Associates | 1670.866 | 1676.638 | 2012-10-17 | 2013-10-02 | 2013-07-14 | 2013-08-03 | 18
2013-04-15 | 2008 | Army Active | Major Construction | LA | LOUISIANA | FORT POLK | 054785 | CHILD DEVELOPMENT CENTER | 2010-12-13 | 2011-08-05 | ASSET Group, Inc. | 7835.188 | 7946 | 2011-09-23 | 2013-12-31 | 2013-01-25 | 2013-12-31 | 23
2013-04-15 | 2009 | Army Active | Major Construction | LA | LOUISIANA | FORT POLK | 069199 | UNIT OPERATIONS FACILITIES | 2011-04-07 | 2011-07-06 | Q.B.S., Inc. | 7076 | 27909.3628 | 2011-08-24 | 2013-11-30 | 2013-04-05 | 2013-08-05 | 73
2013-04-15 | 2009 | Army Active | Major Construction | TX | TEXAS | JOINT BASE SAN ANTONIO | 064202 | TRAINEE BARRACKS COMPLEX | 2010-10-01 08:00 | 2011-09-08 | KOMADA | 101.092 | 85857.547 | 2011-09-28 | 2013-04-19 | 2013-01-20 | 2013-04-12 | 95
2013-04-15 | 2009 | Army Active | Major Construction | TX | TEXAS | JOINT BASE SAN ANTONIO | 047338 | AIT BARRACKS | 2009-05-22 08:00 | 2012-03-30 | Hensel Phelps Construction Company | 1655 | 41905.77 | 2012-04-25 | 2014-03-14 | 2014-01-15 | 2014-01-15 | 69
2013-04-15 | 2010 | Army Active | Major Construction | TX | TEXAS | JOINT BASE SAN ANTONIO | 064209 | ACCESS CONTROL POINT AND ROAD IMPROVEMENTS | 2010-01-15 08:00 | 2010-07-15 | Greenleaf Construction Co.,Inc | 9840 | 11511.224 | 2010-08-03 | 2012-10-31 | 2013-02-28 | 2012-12-21 | 100
2013-04-15 | 2010 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071515 | FAMILY LIFE CENTER | 2010-06-18 08:00 | 2010-09-22 | MAPCO Inc. | 7966 | 8043.2903 | 2010-11-10 | 2013-04-30 | 2012-05-03 | 2013-03-02 | 98
2013-04-15 | 2011 | Army Active | Major Construction | LA | LOUISIANA | FORT POLK | 060130 | BARRACKS | 2011-01-28 | 2011-08-10 | Sundt Construction Inc | 24390.053 | 24368.112 | 2011-09-21 | 2013-08-05 | 2013-03-14 | 2013-05-19 | 76
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 065941 | TRANSIENT TRAINING COMPLEX | 2010-10-22 | 2011-11-04 | LMG Construction Services, LLC | 8253 | 35980.076 | 2011-12-02 | 2013-05-30 | 2013-03-26 | 2013-03-31 | 95
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 065941 | TRANSIENT TRAINING COMPLEX | 2010-10-22 | 2011-06-27 | LMG Construction Services, LLC | 18210.696 | 35980.076 | 2011-08-18 | 2013-02-20 | 2012-12-10 | 2012-12-22 | 96
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 057434 | INDOOR SWIMMING POOL | 2011-08-08 08:00 | 2011-09-14 | Megen Construction Company, Inc. | 13606.4 | 13718.199 | 2011-10-18 | 2013-05-10 | 2013-01-08 | 2013-04-12 | 98
2013-04-15 | 2011 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 065299 | GENERAL PURPOSE STORAGE BUILDING | 2010-10-26 17:00 | 2011-09-15 | GSC Construction, Inc. | 11951.46 | 12033.798 | 2011-11-17 | 2013-08-26 | 2013-04-19 | 2013-06-27 | 53
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 072178 | AUTOMATED MULTIPURPOSE MACHINE GUN RANGE | 2011-06-30 | 2011-09-27 | Sundt Construction Inc | 7493 | 7545.788 | 2012-01-05 | 2013-02-21 | 2013-01-29 | 2013-01-29 | 99
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 072182 | DIGITAL MULTIPURPOSE TRAINING RANGE | 2011-01-18 | 2011-05-31 | Tug Hill Construction | 20520.5 | 21326.1 | 2011-11-02 | 2013-03-15 | 2013-01-15 | 2013-02-11 | 99
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | JOINT BASE SAN ANTONIO | 071116 | TRAINING AIDS CENTER | 2010-11-17 | 2011-06-09 | Blackhawk Ventures, LLC | 6317.777 | 6339.5881 | 2011-09-01 | 2013-05-20 | 2012-08-31 | 2012-09-20 | 99
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071465 | COMPANY OPERATIONS FACILITIES | 2011-03-21 | 2011-09-29 | MW Builders | 3048.91 | 3413.2637 | 2012-06-19 | 2014-03-11 | 2013-11-11 | 2013-11-11 | 24
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071462 | BATTALION COMPLEX | 2011-08-02 08:00 | 2011-09-30 | JAMA Constructors | 6572.777 | 25743.1972 | 2012-07-30 | 2014-08-30 | 2014-01-21 | 2014-01-21 | 11
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071462 | BATTALION COMPLEX | 2011-08-02 08:00 | 2011-09-12 | Major ConstructionructionGoldrick Construction Services, Corp. | 3097 | 25743.1972 | 2011-11-15 | 2013-04-09 | 2012-11-14 | 2013-07-24 | 94
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071462 | BATTALION COMPLEX | 2011-08-02 08:00 | 2011-09-29 | MW Builders | 8779.712 | 25743.1972 | 2012-06-19 | 2014-03-11 | 2013-11-11 | 2013-11-11 | 24
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071639 | BRIGADE COMPLEX | 2010-12-16 | 2011-06-01 | Sundt Construction Inc | 6608 | 6763 | 2011-07-13 | 2013-01-07 | 2013-01-03 | 2013-01-24 | 100
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071639 | BRIGADE COMPLEX | 2011-01-21 | 2011-09-29 | MW Builders | 11652.378 | 11689 | 2012-06-19 | 2014-03-11 | 2013-11-11 | 2013-11-11 | 24
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | JOINT BASE SAN ANTONIO | 067194 | SIMULATIONS CENTER | 2010-11-18 08:00 | 2012-03-13 | Blackhawk Ventrues, LLC | 14554.1 | 14559.527 | 2012-04-10 | 2013-11-12 | 2013-08-09 | 2013-08-09 | 63
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 072845 | UNMANNED AERIAL SYSTEM (UAS) HANGAR | 2010-12-23 17:00 | 2011-07-21 | Satterfield & Pontikes Construction Inc. | 37388.894 | 39400.165 | 2011-12-13 | 2014-04-11 | 2013-11-12 | 2014-02-15 | 52
2013-04-15 | 2011 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 066532 | CONVOY LIVE FIRE | 2011-05-19 08:00 | 2011-08-12 | Major ConstructionructionGoldrick Construction Services, Corp. | 3131.7 | 3146.8541 | 2011-10-13 | 2013-04-29 | 2012-09-06 | 2012-09-10 | 94
2013-04-15 | 2011 | Army Active | Major Construction | NM | NEW MEXICO | WHITE SANDS MISSILE RANGE | 077553 | CENTRAL DES FACILITY | 2011-05-12 | 2011-08-31 | UCC-HBC | 13282.176 | 13819.118 | 2011-10-12 | 2013-03-15 | 2013-02-03 | 2013-03-30 | 99
2013-04-15 | 2011 | Army Active | Minor Construction | NM | NEW MEXICO | WHITE SANDS MISSILE RANGE | 073641 | PHYSICS LAB | 2011-08-18 | 2012-01-20 | Denco | 1443.431 | 1443.431 | 2012-02-16 | 2013-05-15 | 2013-01-31 | 2013-05-01 | 98
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 061846 | RAIL DEPLOYMENT FACILITY | 2012-01-27 | 2012-04-25 | Terra Construction | 3497.82 | 3497.82 | 2012-05-29 | 2013-08-12 | 2013-04-29 | 2013-05-28 | 54
2013-04-15 | 2012 | Army Active | Major Construction | LA | LOUISIANA | FORT POLK | 062622 | MILITARY WORKING DOG FACILITY | 2012-03-01 08:00 | 2012-06-30 | JaMajor Constructionructiono Ventures, LLC | 2437 | 2445.1074 | 2012-08-14 | 2013-10-08 | 2013-08-09 | 2013-08-09 | 2
2013-04-15 | 2012 | Army Active | Major Construction | LA | LOUISIANA | FORT POLK | 064415 | BRIGADE COMPLEX | 2012-02-21 | 2012-03-23 | Blackhawk Ventures, LLC | 10283 | 22238.8876 | 2012-05-15 | 2014-03-06 | 2013-11-06 | 2013-11-25 | 22
2013-04-15 | 2012 | Army Active | Major Construction | LA | LOUISIANA | FORT POLK | 064415 | BRIGADE COMPLEX | 2012-02-21 | 2012-08-17 | The Ross Group Construction Corporation | 11856.9 | 22238.8876 | 2012-10-09 | 2014-05-30 | 2014-04-02 | 2014-04-19 | 9
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 001235 | PHYSICAL FITNESS FACILITY | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | 23138.91 | 23121.051 | 2012-07-12 | 2014-08-13 | 2014-04-10 | 2014-04-28 | 7
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 020697 | CHAPEL | 2012-01-27 | 2012-08-30 | Greenleaf Construction Co.,Inc | 12999.823 | 12999.823 | 2012-09-20 | 2014-05-08 | 2014-01-28 | 2014-01-28 | 2
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 058537 | RECEPTION STATION, PH 1 | 2011-11-21 | 2012-05-23 | Zachry Federal Construction Corporation | 32234.496 | 32224.904 | 2012-06-15 | 2014-06-26 | 2014-03-26 | 2014-03-26 | 12
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | MAJOR CONSTRUCTIONRUCTIONALESTER ARMY AMMO PLANT | 058207 | RAILROAD TRACKS | 2011-11-29 | 2012-03-26 | Major ConstructionructionAlester Contract | 6323.7745 | 0 | 2012-05-09 | 2014-01-04 | 2013-10-06 | 2013-10-06 | 15
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071682 | VEHICLE MAINTENANCE FACILITY | 2011-12-19 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | 3844.2 | 13513.6345 | 2012-08-24 | 2014-04-16 | 2014-02-15 | 2014-02-15 | 4
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 071682 | VEHICLE MAINTENANCE FACILITY | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | 9669.4345 | 13513.6345 | 2012-06-22 | 2014-02-02 | 2013-12-14 | 2013-12-14 | 23
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | JOINT BASE SAN ANTONIO | 005034 | VEHICLE MAINTENANCE FACILITY | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | 8603 | 8603 | 2013-01-24 | 2014-12-15 | 2014-07-18 | 2014-07-18 | 0
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 064753 | VEHICLE MAINTENANCE FACILITY | 2012-01-09 | 2012-06-29 | Harper Construction Company, Inc. | 37867.635 | 43962.357 | 2012-07-19 | 2014-07-03 | 2014-04-11 | 2014-04-11 | 20
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 064753 | VEHICLE MAINTENANCE FACILITY | 2012-01-09 | 2012-07-13 | GSC Construction, Inc. | 6094.722 | 43962.357 | 2012-09-26 | 2014-05-06 | 2014-02-03 | 2014-02-03 | 3
2013-04-15 | 2012 | Army Active | Major Construction | LA | LOUISIANA | FORT POLK | 067033 | MULTIPURPOSE MACHINE GUN RANGE | 2012-03-13 | 2012-08-03 | JaMajor Constructionructiono Ventures, LLC. | 8493 | 8493 | 2012-10-25 | 2014-02-24 | 2013-10-25 | 2013-11-04 | 7
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 068993 | ELECTRONICS MAINTENANCE FACILITY | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | 9573 | 14690.965 | 2012-08-08 | 2014-02-14 | 2013-12-16 | 2013-12-16 | 14
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 068993 | ELECTRONICS MAINTENANCE FACILITY | 2011-12-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | 5117.965 | 14690.965 | 2012-08-20 | 2014-07-31 | 2013-09-13 | 2013-09-13 | 40
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 069286 | INFRASTRUCTURE | 2011-09-16 08:00 | 2012-07-26 | Venegas Engineering & Management Construction Company | 9008.411 | 8631.554 | 2012-08-20 | 2014-07-31 | 2013-09-13 | 2013-09-13 | 40
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 070514 | VEHICLE MAINTENANCE FACILITY | 2011-12-15 17:00 | 2012-03-30 | J&M Contractors | 3921.5 | 13788.477 | 2012-05-31 | 2013-12-06 | 2013-10-08 | 2013-10-08 | 30
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 070514 | VEHICLE MAINTENANCE FACILITY | 2011-12-15 17:00 | 2012-03-30 | Urban Associates, Inc. | 9815.87 | 13788.477 | 2012-05-30 | 2013-11-13 | 2013-09-13 | 2013-09-20 | 41
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | RED RIVER ARMY DEPOT | 066691 | MANEUVER SYSTEMS SUSTAINMENT CTR, PH 3 | 2011-12-24 | 2012-03-23 | GCC Major ConstructionructionCarthy Joint Venture IV | 40532.114 | 40779.149 | 2012-04-24 | 2014-07-23 | 2014-04-24 | 2014-06-16 | 11
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 064815 | BATTLE COMMAND TRAINING CENTER | 2011-12-22 | 2012-04-10 | Harper Construction Company, Inc. | 20720.265 | 20727.506 | 2012-07-09 | 2014-06-10 | 2014-03-19 | 2014-03-19 | 31
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT BLISS | 074845 | WATER WELL, POTABLE | 2012-01-04 | 2012-08-01 | Bailey CKY JV | 2248.08 | 2248.08 | 2012-08-28 | 2013-09-30 | 2013-05-25 | 2013-05-25 | 29
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 065374 | OPERATIONAL READINESS TRAINING COMPLEX | 2012-07-19 08:00 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | 38503 | 46698.202 | 2012-09-05 | 2014-11-10 | 2014-07-28 | 2014-07-28 | 5
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 065374 | OPERATIONAL READINESS TRAINING COMPLEX | 2012-07-19 08:00 | 2013-01-07 | Turner Strategic Technologies, LLC | 8195.202 | 46698.202 | 2013-03-08 | 2015-03-31 | 2014-11-28 | 2014-11-28 | 0
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 077187 | VEHICLE MAINTENANCE FACILITY | 2011-12-19 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | 3749.6 | 16601.2535 | 2012-08-24 | 2014-04-16 | 2014-02-15 | 2014-02-15 | 4
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 077187 | VEHICLE MAINTENANCE FACILITY | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | 7472.9455 | 16601.2535 | 2012-06-22 | 2014-02-02 | 2013-12-14 | 2013-12-14 | 23
2013-04-15 | 2012 | Army Active | Major Construction | TX | TEXAS | FORT HOOD | 077187 | VEHICLE MAINTENANCE FACILITY | 2011-12-19 | 2012-03-28 | RMA Land Construction, Inc. | 5378.708 | 16601.2535 | 2012-06-26 | 2013-12-18 | 2013-06-21 | 2013-06-21 | 11
2013-04-15 | 2012 | Army Active | Major Construction | OK | OKLAHOMA | FORT SILL | 074690 | THAAD INSTRUCTION FACILITY | 2012-01-09 | 2012-03-29 | Roy Anderson Corp. | 25942 | 25942 | 2012-07-26 | 2014-07-25 | 2014-04-16 | 2014-04-16 | 20
2013-04-15 | 2012 | Army Active | Minor Construction | OK | OKLAHOMA | FORT SILL | 080407 | SIMULATOR BUILDING (NON-MOTION-BASED) | 2011-12-16 08:00 | 2012-06-22 | Comanche Nation Construction | 1700.971 | 1753.259 | 2012-06-22 | 2014-01-06 | 2013-09-15 | 2013-10-15 | 43
2013-04-15 | 2008 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 064131 | NEW ROADS | 2009-07-20 17:00 | 2009-09-23 | Global Operation & Trust Construction Ltd JV | 17780.3681 | 17993.9287 | 2009-10-27 | 2014-01-30 | 2011-10-17 | 2013-07-31 | 68
2013-04-15 | 2009 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 070037 | SOF HQ COMPLEX | 2009-05-22 | 2010-02-12 | EMTA Insaat VE Ticaret A.S. | 11619.3495 | 17755.8152 | 2010-03-22 | 2013-10-30 | 2011-05-16 | 2013-03-27 | 78
2013-04-15 | 2009 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 073090 | UTILITIES, PH 1 | 2009-05-20 17:00 | 2009-09-14 | Road & Roof Construction Company | 21195.4629 | 23123.2986 | 2009-11-05 | 2013-05-15 | 2010-10-31 | 2012-11-18 | 98
2013-04-15 | 2009 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 072125 | SOF ALPHA RAMP FACILITIES | 2012-04-04 | 2010-01-30 | ALMajor ConstructionO Limited | 9047.5 | 3194 | 2010-03-17 | 2011-11-30 | 2011-06-10 | 2011-06-10 | 93
2013-04-15 | 2009 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 072125 | SOF ALPHA RAMP FACILITIES | 2012-04-04 | 2012-08-23 | Prime Projects International Construction Ltd | 7995.5256 | 8318.3674 | 2012-09-26 | 2013-11-11 | 2013-08-13 | 2013-08-13 | 57
2013-04-15 | 2009 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 073088 | SOUTH PARK DRAINAGE, PH 1 | 2009-05-20 17:00 | 2009-09-14 | Road & Roof Construction Company | 3925.6249 | 6500.72 | 2009-11-05 | 2013-05-15 | 2010-10-31 | 2012-11-18 | 98
2013-04-15 | 2009 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 072605 | TROOP HOUSING, PH 3 | 2010-07-25 | 2010-09-06 | EMTA Insaat VE Ticaret A.S. | 10990.1872 | 11387.8558 | 2010-10-09 | 2014-01-14 | 2013-02-25 | 2013-12-09 | 80
2013-04-15 | 2010 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 071488 | COALITION OPERATION CENTER | 2011-10-11 08:00 | 2011-12-14 | Ch2m Hill-Yuksel Joint Venture | 39961.861 | 40499.6412 | 2012-03-16 | 2013-12-01 | 2013-07-09 | 2013-09-04 | 34
2013-04-15 | 2010 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 072126 | COMMAND AND CONTROL FACILITY | 2010-06-16 08:00 | 2010-09-24 | Metag Insaat Ticaret A.S. | 16908.8471 | 25700.8967 | 2010-10-24 | 2013-09-29 | 2012-01-17 | 2013-05-15 | 92
2013-04-15 | 2010 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 069398 | FUEL SYSTEM PH 6 | 2009-12-18 08:00 | 2010-03-31 | EMTA Insaat VE Ticaret A.S. | 5001.829 | 5307.514 | 2010-04-20 | 2013-06-28 | 2011-10-12 | 2012-09-12 | 97
2013-04-15 | 2010 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 071489 | BARRACKS | 2010-05-03 08:00 | 2010-09-25 | Zafer Construction Company | 11196.317 | 12387.6006 | 2010-10-25 | 2013-06-15 | 2012-05-17 | 2013-03-13 | 98
2013-04-15 | 2010 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 073124 | DRAINAGE SYSTEM, PH 2 | 2011-06-01 | 2011-08-17 | Yuksel Insaat A.S. | 13900 | 14403.0404 | 2011-09-08 | 2013-12-31 | 2013-04-10 | 2013-11-10 | 80
2013-04-15 | 2010 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 072477 | USFOR-A HEADQUARTERS & HOUSING | 2011-03-28 | 2011-08-05 | Contrack International Inc. | 47160.85 | 47339.4736 | 2011-09-09 | 2014-01-27 | 2013-12-07 | 2014-01-27 | 9
2013-04-15 | 2010 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 074292 | WAREHOUSE | 2010-06-29 08:00 | 2010-09-15 | YDA-AFCON JV | 13546.718 | 14698.9476 | 2010-11-03 | 2012-12-01 | 2011-08-30 | 2012-09-05 | 93
2013-04-15 | 2010 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 074195 | WATER DISTRIBUTION SYSTEM | 2011-07-29 | 2012-01-26 | Technologists, Inc. | 2859 | 2859 | 2012-03-28 | 2013-12-01 | 2012-12-23 | 2013-11-01 | 21
2013-04-15 | 2011 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 068083 | CONSOLIDATED COMMUNITY SUPPORT AREA | 2011-02-15 08:00 | 2011-05-23 | Zafer Construction Company | 12944.211 | 15398.1341 | 2011-06-21 | 2013-12-31 | 2012-11-22 | 2013-10-09 | 48
2013-04-15 | 2011 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 071602 | BARRACKS | 2011-11-14 | 2012-02-07 | Bryan 77 Construction JV | 16732.683 | 17267.32 | 2012-03-06 | 2014-02-15 | 2013-11-26 | 2014-01-25 | 37
2013-04-15 | 2011 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 071604 | EASTSIDE UTILITIES INFRASTRUCTURE | 2012-05-30 | 2012-09-04 | ANHAM-ICSS Joint Venture | 26826.989 | 26826.989 | 2012-10-18 | 2014-08-04 | 2014-06-05 | 2014-06-05 | 3
2013-04-15 | 2011 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 071605 | EASTSIDE ELECTRICAL DISTRIBUTION | 2011-07-15 | 2012-07-26 | Fluor Intercontinental, Inc. | 10944.278 | 10944.278 | 2012-07-26 | 2013-10-11 | 2013-08-12 | 2013-08-12 | 42
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN | 075210 | NORTH AREA UTILITIES, PH 2 | 2011-03-09 | 2011-07-29 | Contrack International, Inc. | 12133.874 | 12869.6461 | 2011-09-03 | 2013-04-01 | 2012-09-02 | 2013-01-30 | 98
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 072606 | TROOP HOUSING, PH 4 | 2010-12-07 17:00 | 2011-06-01 | Yuksel Insaat A.S. | 14226.7 | 14902.7385 | 2011-06-22 | 2013-10-31 | 2012-10-29 | 2013-07-24 | 64
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 074090 | TROOP HOUSING, PH 5 | 2011-01-07 | 2011-07-05 | Yuksel Insaat A.S. | 18499.9 | 19150.3584 | 2011-08-15 | 2013-12-01 | 2012-11-12 | 2013-07-11 | 73
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 074155 | TROOP HOUSING, PH 6 | 2010-12-22 | 2011-07-08 | Yuksel Insaat A.S. | 18499.9 | 19232.7109 | 2011-08-07 | 2013-06-30 | 2012-11-04 | 2013-07-04 | 87
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 074104 | COMMAND & CONTROL FACILITY | 2010-11-17 | 2012-01-11 | YUKSEL INSAAT A.S. | 7090.5 | 7237.9317 | 2012-04-05 | 2013-10-31 | 2013-07-09 | 2013-08-08 | 28
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 074925 | DINING FACILITY | 2011-07-05 08:00 | 2012-02-16 | Zafer Construction Company | 5217.732 | 5405.321 | 2012-04-18 | 2013-10-01 | 2013-05-03 | 2013-06-25 | 52
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 075202 | COMMAND & CONTROL FACILITY | 2012-03-16 | 2012-06-11 | Road & Roof Construction Company | 5027.586 | 5027.586 | 2012-07-16 | 2013-11-25 | 2013-07-26 | 2013-07-26 | 20
2013-04-15 | 2011 | Army Active | Major Construction | AF | AFGHANISTAN | AFGHANISTAN | 071606 | ENTRY CONTROL POINT | 2011-06-10 17:00 | 2011-11-09 | 77 Construction Contracting & Trading Company | 6490.6192 | 6796.1149 | 2012-02-06 | 2013-10-01 | 2013-05-06 | 2013-06-28 | 67
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 077119 | ROADS AND UTILITIES, PH 1 | 2011-07-29 17:00 | 2012-01-26 | Technologists, Inc. | 14706 | 13761 | 2012-03-28 | 2013-12-01 | 2012-12-23 | 2013-11-01 | 21
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 077054 | REPLACE TEMPORARY GUARD TOWERS | 2011-01-08 | 2011-09-21 | Metag Insaat Ticaret A.S. | 2647 | 2647 | 2011-11-15 | 2013-10-01 | 2013-01-18 | 2013-10-28 | 39
2013-04-15 | 2011 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 077066 | MP HQ | 2011-01-08 | 2011-09-21 | Metag Insaat Ticaret A.S. | 3352 | 3849 | 2011-11-15 | 2013-10-01 | 2013-01-18 | 2013-10-28 | 39
2013-04-15 | 2011 | Army Active | Minor Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 079762 | PRIMARY WASTE WATER TREATMENT | 2011-05-04 | 2011-08-05 | Contrack International Inc. | 1387 | 1386.997 | 2011-09-09 | 2014-01-27 | 2013-12-07 | 2014-01-27 | 9
2013-04-15 | 2011 | Army Active | Minor Construction | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 079770 | WATER WELL, POTABLE | 2011-05-13 08:00 | 2011-08-05 | Contrack International Inc. | 1331 | 1330.83 | 2011-09-09 | 2014-01-27 | 2013-12-07 | 2014-01-27 | 9
2013-04-15 | 2012 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN | 074084 | BARRACKS, PH 5 | 2011-12-05 08:00 | 2012-04-12 | Bryan 77 Construction JV | 19331.277 | 19792.59 | 2012-06-09 | 2014-12-31 | 2014-04-20 | 2014-07-04 | 13
2013-04-15 | 2012 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN VARIOUS | 074067 | DRAINAGE SYSTEM, PH 3 | 2012-04-27 | 2012-08-15 | ANHAM-ICSS Joint Venture | 19902.989 | 19902.989 | 2012-10-09 | 2014-07-31 | 2014-06-01 | 2014-06-01 | 10
2013-04-15 | 2012 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN | 071570 | WESTSIDE ELECTRICAL DISTRIBUTION | 2012-07-03 | 2012-08-23 | Inglett & Stubbs, International LTD | 8117.7809 | 8117.7809 | 2012-08-23 | 2013-09-29 | 2013-07-29 | 2013-07-29 | 62
2013-04-15 | 2012 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN | 071568 | EASTSIDE ELECTRICAL DISTRIBUTION, PH 2 | 2012-06-14 | 2012-08-03 | Fluor Intercontinental, Inc. | 6506.937 | 6506.937 | 2012-08-07 | 2013-08-02 | 2013-06-03 | 2013-06-03 | 27
2013-04-15 | 2012 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN | 071569 | WESTSIDE UTILITIES INFRASTRUCTURE | 2012-08-24 | 2012-11-15 | Contrack International Inc. | 11924.059 | 11924.059 | 2012-12-12 | 2014-05-06 | 2014-03-07 | 2014-03-07 | 0
2013-04-15 | 2012 | Army Active | Major Construction | WW | WORLD WIDE | VARIOUS WORLDWIDE LOCATIONS | 079652 | RADAR SECURITY AND SUPPORT FACILITIES | 2012-05-25 08:00 | 2012-08-20 | State Corps | 3800 | 3800 | 2012-09-27 | 2013-08-23 | 2013-07-24 | 2013-07-24 | 12
2013-04-15 | 2012 | Army Active | Major Construction - OCO | AF | AFGHANISTAN | AFGHANISTAN | 080001 | WASTE MANAGEMENT COMPLEX (60 TONS) | 2012-05-25 08:00 | 2012-08-21 | Bryan 77 Construction JV | 24435.92 | 24364.399 | 2012-11-14 | 2014-01-13 | 2013-11-14 | 2013-11-14 | 10
2013-04-15 | 2010 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 004 | APCSS CONFERENCE & TECHNOLOGY LEARNING CENTER | 2010-05-25 | 2010-07-28 | Awarded by Other Agency | 11431 | 12775 | 2010-08-11 | 2012-06-12 | 2012-06-12 | 2012-06-12 | 86
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | 12906 | 12019 | 2011-06-16 | 2013-10-02 | 2012-12-01 | 2013-01-15 | 81
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | MAJOR CONSTRUCTIONRUCTIONSF BLOUNT ISLAND | 005 | PAINT AND BLAST FACILITY | 2011-04-29 | 2011-09-16 | SAUER, INC. | 20345 | 19380 | 2011-09-30 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 62
2013-04-15 | 2011 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 005 | JOINT POW/MIA ACCOUNTING, USPACOM | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | 95540 | 70740 | 2011-06-20 | 2013-10-09 | 2013-07-05 | 2013-09-08 | 39
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | MAJOR CONSTRUCTIONRUCTIONSF BLOUNT ISLAND | 006 | PORT OPERATIONS FACILITY | 2010-04-30 | 2010-09-23 | CMS CORP/TOLTEST JV IV | 3981 | 3659 | 2010-10-07 | 2013-01-08 | 2012-08-20 | 2013-01-08 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | HI | HAWAII | MAJOR CONSTRUCTIONRUCTIONB HAWAII KANEOHE | 006 | PHYSICAL FITNESS CENTER, CAMP SMITH | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | 28891 | 27324 | 2011-06-30 | 2013-09-17 | 2013-03-07 | 2013-09-17 | 69
2013-04-15 | 2009 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 010 | AUTONOMOUS SYSTEMS RESEARCH LAB | 2009-06-29 | 2009-09-29 | JOHN C. GRIMBERG CO., INC. | 19721 | 21408 | 2009-10-13 | 2012-03-09 | 2011-04-07 | 2011-08-11 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 010 | EODMU TEN OPERATIONS FACILITY | 2008-11-14 | 2009-03-02 | BAY ELECTRIC CO INC | 7985 | 8286 | 2009-03-16 | 2011-03-16 | 2010-09-08 | 2011-03-16 | 94
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | MAJOR CONSTRUCTIONRUCTIONSF BLOUNT ISLAND | 012 | CONTAINER STAGING AND LOADING LOT | 2010-11-26 | 2011-06-03 | Major ConstructionructionCARTHY IMPROVEMENT COMPANY | 3380 | 1938 | 2011-06-17 | 2013-05-03 | 2013-05-03 | 2013-05-03 | 20
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | JA | JAPAN | COMFLEACT YOKOSUKA JA | 012 | CONSTRUCT NACCC ADDITION | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | 1380 | 1256 | 2011-06-24 | 2012-04-20 | 2012-04-13 | 2012-04-20 | 96
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVAL SUPPORT ACTIVITY ORLANDO | 015 | CALIBRATION FACILITY LAND ACQUISITION |  | 2011-12-23 | LAND ACQUISITION | 3149 | 2920 | 2012-01-06 | N/A | N/A | N/A | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 016 | E-2D AIRCREW TRAINER FACILITY | 2009-12-07 | 2010-05-07 | HOURIGAN CONSTRUCTION CORPORATION | 5737 | 5671 | 2010-05-21 | 2011-11-21 | 2011-07-23 | 2011-12-02 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | MAJOR CONSTRUCTIONRUCTIONSF BLOUNT ISLAND | 017 | HARDSTAND EXTENSION | 2010-11-26 | 2011-06-03 | Major ConstructionructionCARTHY IMPROVEMENT COMPANY | 12623 | 7660 | 2011-06-17 | 2013-05-03 | 2013-05-03 | 2013-05-03 | 66
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 019 | CHILD DEVELOPMENT CENTER | 2009-04-21 | 2009-09-29 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | 22378 | 24108 | 2009-10-13 | 2012-01-17 | 2011-10-29 | 2012-01-17 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAS LEMOORE CA | 020 | MARINE CORPS RESERVE CENTER | 2009-05-04 | 2009-06-19 | T. B. PENICK & SONS, INC. | 11530 | 13131 | 2009-07-03 | 2011-02-10 | 2010-07-04 | 2011-06-30 | 86
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 020 | CHILD DEVELOPMENT CENTER | 2009-09-29 | 2009-12-17 | RMA-ECC, A JOINT VENTURE | 19438 | 17993 | 2009-12-31 | 2012-05-29 | 2012-01-16 | 2012-05-31 | 90
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 022 | CHILD DEVELOPMENT CENTER | 2009-05-28 | 2009-11-30 | VETERANS NORTHWEST CONSTRUCTION LLC | 11771 | 12558 | 2009-12-14 | 2011-10-27 | 2011-06-09 | 2012-01-03 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | MAJOR CONSTRUCTIONRUCTIONSF BLOUNT ISLAND | 022 | CONSOLIDATED WAREHOUSE FACILITY | 2010-11-22 | 2011-06-03 | SAUER, INC. | 13295 | 10868 | 2011-06-17 | 2012-07-27 | 2012-07-27 | 2013-02-28 | 62
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 023 | CHILD DEVELOPMENT CENTER | 2009-06-18 | 2009-08-28 | THR ENTERPRISES, INC. | 11498 | 11336 | 2009-09-11 | 2012-07-06 | 2011-02-13 | 2012-01-16 | 90
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | MAJOR CONSTRUCTIONRUCTIONSF BLOUNT ISLAND | 023 | WASHRACK EXPANSION | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | 8877 | 8111 | 2011-06-15 | 2013-04-30 | 2012-11-19 | 2012-11-19 | 81
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MD | MARYLAND | NAS PATUXENT RIVER SEC DET | 024 | CHILD DEVELOPMENT CENTER | 2009-12-22 | 2010-11-04 | GRUNLEY/GOEL JV E LLC | 12558 | 13211 | 2010-11-18 | 2013-04-12 | 2012-05-27 | 2013-04-12 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | MAJOR CONSTRUCTIONRUCTIONSF BLOUNT ISLAND | 024 | CONTAINER STORAGE LOT | 2010-11-26 | 2011-06-03 | Major ConstructionructionCARTHY IMPROVEMENT COMPANY | 3702 | 2992 | 2011-06-17 | 2013-05-03 | 2013-05-03 | 2013-05-03 | 60
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 026 | BACHELOR ENLISTED QUARTERS, LAS PULGAS | 2008-12-24 | 2009-07-27 | TURNER-PENICK | 34235 | 34183 | 2009-08-10 | 2011-08-04 | 2011-08-04 | 2011-08-04 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 030 | SQUAD BATTLE COURSE | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | 16292 | 14116 | 2012-07-05 | 2014-05-17 | 2014-05-17 | 2014-05-17 | 14
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 032 | INFANTRY PLATOON BATTLE COURSE SR-1 | 2011-05-03 | 2011-06-28 | WHITING-TURNER CONTRACTING CO | 17259 | 18995 | 2011-07-12 | 2013-09-19 | 2013-03-04 | 2013-09-19 | 75
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAL WEAPONS STATION EARLE NJ | 034 | MAIN GATE SECURITY IMPROVEMENTS | 2009-12-25 | 2010-03-18 | P&S CONSTRUCTION, INC. | 7328 | 8973 | 2010-04-01 | 2012-09-26 | 2011-09-29 | 2012-11-30 | 94
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 034 | ORDNANCE HANDLING CARGO OPS & TRNG SUPT CTR | 2009-01-29 | 2009-05-27 | VIRTEXCO CORPORATION | 11564 | 13703 | 2009-06-10 | 2011-11-03 | 2010-09-22 | 2011-04-27 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | TX | TEXAS | NAS JRB FT WORTH TX | 039 | REPLACE JOINT BASE COMMUNICATIONS BLDG | 2010-05-21 | 2010-08-06 | I LEETEX/HILL & WILKINSON LLC | 5061 | 4624 | 2010-08-20 | 2012-04-20 | 2011-11-19 | 2012-04-20 | 99
2013-04-15 | 2012 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | 7708 | 7280 | 2012-04-19 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 52
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 043 | BACHELOR ENLISTED QUARTERS, PICO (24) AREA | 2009-07-13 | 2009-09-22 | HARPER CONSTRUCTION COMPANY, INC | 31059 | 31487 | 2009-10-06 | 2012-03-05 | 2011-06-06 | 2012-03-05 | 100
2013-04-15 | 2010 | Navy - MC Active | Minor Construction | TX | TEXAS | NAS JRB FT WORTH TX | 044 | HAZARDOUS MATERIAL STOREHOUSE | 2011-07-27 | 2011-09-26 | AFFILIATED WESTERN, INC | 2019 | 1948 | 2011-10-10 | 2012-10-19 | 2012-07-16 | 2012-10-19 | 97
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 046 | BACHELOR ENLISTED QUARTERS, AREA 41 | 2009-07-15 | 2009-09-25 | HARPER CONSTRUCTION COMPANY, INC | 32038 | 32091 | 2009-10-09 | 2011-08-19 | 2011-03-19 | 2011-08-19 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | LA | LOUISIANA | HDQTRS 4TH MARDIV NEW ORLEANS | 048 | RESERVE CENTER, JOLIET IL | 2010-05-27 | 2010-09-30 | CHARPIE-KORTE JOINT VENTURE | 8794 | 8748 | 2010-10-14 | 2012-08-15 | 2011-12-15 | 2012-05-20 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAS LEMOORE CA | 049 | RESERVE CENTER ADDITION, ALAMEDA | 2010-07-21 | 2010-09-24 | J I GARCIA CONSTRUCTION INC | 6236 | 7001 | 2010-10-08 | 2012-08-01 | 2012-04-01 | 2012-08-01 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 051 | BACHELOR ENLISTED QUARTERS, HEADQUARTERS | 2009-05-06 | 2009-09-18 | HENSEL PHELPS SOLTEK, JV | 31967 | 32132 | 2009-10-02 | 2011-12-22 | 2011-07-18 | 2012-02-20 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 052 | BACHELOR ENLISTED QUARTERS, HEADQUARTERS | 2009-05-06 | 2009-09-18 | HENSEL PHELPS SOLTEK, JV | 33768 | 33632 | 2009-10-02 | 2011-12-22 | 2011-07-18 | 2012-02-20 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | TX | TEXAS | NAS JRB FT WORTH TX | 055 | JOINT RESERVE CENTER | 2010-06-18 | 2010-12-03 | Awarded by Other Agency | 6024 | 5063 | 2010-12-17 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 71
2013-04-15 | 2011 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE | 2011-02-04 | 2011-06-24 | FOPCO, INC | 7856 | 8519 | 2011-07-08 | 2013-04-30 | 2012-08-15 | 2013-03-15 | 85
2013-04-15 | 2013 | Navy - MC Active | Minor Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 056 | VPT TEST FACILITY | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | 2332 | 2154 | 2013-03-28 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 0
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 060 | MARINE RESOURCE AND RECOVERY CENTER | 2009-08-07 | 2009-09-30 | BARNHART-BALFOUR BEATTY, INC. | 23928 | 22741 | 2009-10-14 | 2011-10-15 | 2011-10-15 | 2011-10-15 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | LA | LOUISIANA | HDQTRS 4TH MARDIV NEW ORLEANS | 060 | MARINE CORPS RESERVE CENTER | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | 14630 | 14032 | 2011-10-11 | 2013-07-17 | 2013-02-08 | 2013-07-23 | 21
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVWPNSTA SEAL BEACH | 063 | MARINE CORPS RESERVE TRAINING CENTER | 2010-07-23 | 2010-09-30 | RMA LAND CONSTRUCTION, INC. | 12044 | 11446 | 2010-10-14 | 2012-05-23 | 2012-04-07 | 2013-04-20 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 068 | ELECTROMAGNETIC SENSOR FACILITY | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | 24394 | 22606 | 2011-08-23 | 2013-08-12 | 2013-08-22 | 2013-09-14 | 67
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | 1559 | 1446 | 2011-10-03 | 2013-03-01 | 2012-12-24 | 2013-03-01 | 96
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 073 | BACHELOR ENLISTED QUARTERS, DEL MAR | 2008-12-24 | 2009-07-27 | TURNER-PENICK | 30496 | 31401 | 2009-08-10 | 2011-08-04 | 2011-08-04 | 2011-08-04 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 082 | UNMANNED ASW SUPPORT FACILITY | 2010-03-05 | 2010-07-12 | MARON CONSTRUCTION CO INC | 7459 | 7464 | 2010-07-26 | 2013-03-20 | 2012-01-29 | 2012-12-15 | 87
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS CAMP PENDLETON CA | 086 | EXPAND COMBAT AIRCRAFT LOADING APRON | 2010-01-26 | 2010-03-23 | REYES CONSTRUCTION INC | 6795 | 6041 | 2010-04-06 | 2011-11-09 | 2011-09-12 | 2011-11-09 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 092 | INFANTRY TRAINING CENTER, SOI | 2009-03-04 | 2009-05-01 | STRAUB CONSTRUCTION, INC. | 10894 | 10573 | 2009-05-15 | 2010-09-03 | 2010-11-07 | 2010-12-01 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 092 | TANK VEHICLE MAINTENANCE FACILITY | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | 6458 | 6159 | 2011-10-06 | 2013-03-11 | 2012-09-21 | 2013-03-28 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 094 | BACHELOR ENLISTED QUARTERS, SAN MATEO AREA | 2009-02-02 | 2009-08-14 | TURNER-PENICK | 32072 | 31943 | 2009-08-28 | 2012-12-06 | 2011-08-22 | 2012-12-06 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVAL SUPPORT ACTIVITY ORLANDO | 100 | JCSE SQUADRON FACILITY | 2008-10-30 | 2009-03-16 | Awarded by Other Agency | 22474 | 22349 | 2009-03-30 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 94
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GQ | GUAM | NSA ANDERSEN GUAM | 100 | NORTH RAMP UTILITIES, INC 1 OF 2 | 2010-06-30 | 2011-03-31 | GUAM PACIFIC INTERNATIONAL, LLCDBA CMS CORP TOLTEST JV | 22524 | 17406 | 2011-04-14 | 2014-02-22 | 2013-03-03 | 2014-02-24 | 60
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 101 | MAINTENANCE SHOP, WHEELED | 2010-07-28 | 2010-09-30 | I E PACIFIC INC | 15940 | 14556 | 2010-10-14 | 2012-10-14 | 2012-10-14 | 2013-04-04 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GQ | GUAM | NSA ANDERSEN GUAM | 101 | NORTH RAMP PARKING, INC 1 OF 2 | 2010-06-30 | 2011-04-06 | PERINI/NORTON A JOINT VENTURE | 88797 | 83999 | 2011-04-20 | 2014-07-21 | 2014-01-15 | 2014-07-21 | 55
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NAVSUPPACT HAMPTON ROADS VA | 101 | ROAD IMPROVEMENTS CAMP ALLEN AREA | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | 1381 | 1324 | 2011-02-28 | 2012-01-27 | 2011-09-21 | 2012-01-27 | 87
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 103 | MAINTENANCE SUNSHADES, WHEELED | 2010-07-02 | 2010-09-29 | ALLEN ENGINEERING CONTRACTOR, INC | 14455 | 12981 | 2010-10-13 | 2013-01-30 | 2012-10-13 | 2013-01-28 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 104 | COMM/ELEC MAINTENANCE & STORAGE, HORNO | 2009-05-08 | 2009-06-30 | STRAUB CONSTRUCTION, INC. | 9751 | 9497 | 2009-07-14 | 2011-03-11 | 2011-01-06 | 2011-03-18 | 100
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 105 | NETWARCOM FACILITY, BLDG LF-18, NSN | 2009-08-19 | 2009-09-29 | PIPELINE & INDUSTRIAL GROUP, INC | 2000 | 1899 | 2009-10-13 | 2012-05-25 | 2010-08-25 | 2012-05-16 | 97
2013-04-15 | 2010 | Navy - MC Active | Major Construction | TX | TEXAS | NAS CORPUS CHRISTI TX | 105 | RESERVE TRAINING CENTER | 2010-04-15 | 2010-06-30 | GIDEON MARSHALL JOINT VENTURE | 2666 | 2598 | 2010-07-14 | 2011-09-23 | 2011-07-13 | 2011-09-02 | 94
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 105 | TRACKED VEHICLE MAINTENANCE COVER | 2012-03-06 | 2012-06-15 | ALLEN ENGINEERING CONTRACTOR, INC | 13925 | 13105 | 2012-06-29 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 4
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 107 | COMM/ELECT MAINTENANCE/STORAGE | 2010-07-22 | 2010-09-30 | ALLEN ENGINEERING CONTRACTOR, INC | 13564 | 12395 | 2010-10-14 | 2012-10-14 | 2012-10-14 | 2013-03-30 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS CAMP PENDLETON CA | 107 | AVIATION TRANSMITTER/RECEIVER SITE | 2011-04-14 | 2011-07-29 | RQ-BERG JV | 10261 | 8838 | 2011-08-12 | 2013-05-01 | 2013-01-19 | 2013-01-19 | 84
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS CAMP PENDLETON CA | 109 | CNAT/FRS AVIATION TRAINING AND BEQ | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | 51999 | 44134 | 2011-09-26 | 2014-05-21 | 2014-01-08 | 2014-01-08 | 28 | -5000
2013-04-15 | 2012 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 110 | REPLACE CONDEMNED COATINGS LABORATORY | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | 3805 | 3703 | 2012-09-11 | 2013-08-28 | 2013-08-28 | 2013-08-28 | 6
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS CAMP PENDLETON CA | 111 | MALS-39 MAINTENANCE HANGAR EXPANSION | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | 47061 | 28286 | 2011-07-06 | 2013-05-15 | 2013-03-13 | 2013-05-15 | 62
2013-04-15 | 2009 | Navy - MC Active | Major Construction | GA | GEORGIA | NAS ATLANTA GA | 112 | MARINE CORPS RESERVE CENTER | 2008-12-09 | 2009-03-24 | SLONE ASSOCIATES INC. | 7734 | 8095 | 2009-04-07 | 2011-11-25 | 2010-09-30 | 2011-06-24 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 113 | WATER/WW TDS/TOC CORROSION CONTROL | 2009-01-05 | 2010-06-21 | CDM CONSTRUCTORS INC | 52393 | 50023 | 2010-07-05 | 2013-08-21 | 2012-12-03 | 2013-06-11 | 90
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 114 | ARRA-INSTALL PHOTOVOLTAIC SYSTEMS | 2009-04-22 | 2009-06-29 | ATLANTIC CONTINGENCY CONSTRUCTION,LLC | 26098 | 23466 | 2009-07-13 | 2013-01-04 | 2009-11-30 | 2012-12-21 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 114 | DINING FACILITY, NORTH MAINSIDE | 2010-07-02 | 2010-09-28 | STRAUB MARTIN A JOINT VENTURE | 17260 | 16787 | 2010-10-12 | 2012-10-12 | 2012-10-12 | 2013-06-17 | 73
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS CAMP PENDLETON CA | 114 | MV-22 DOUBLE HANGAR REPLACEMENT | 2012-03-19 | 2012-07-20 | BARNHART-BALFOUR BEATTY, INC. | 40539 | 37666 | 2012-08-03 | 2015-08-10 | 2015-08-10 | 2015-08-10 | 1
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 115 | ARRA-REPLACE STEAM LINE | 2009-01-19 | 2009-07-22 | PIPELINE & INDUSTRIAL GROUP, INC | 1072 | 1125 | 2009-08-05 | 2010-08-31 | 2010-03-29 | 2010-09-10 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 115 | MULTI-PURPOSE FLIGHT SIMULATOR | 2010-08-18 | 2010-09-29 | Awarded by Other Agency | 6254 | 6337 | 2010-10-13 | 2011-10-20 | 2011-10-20 | 2011-10-20 | 87
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 116 | ARRA-STEAM PLANT DECENTRALIZATION | 2009-10-19 | 2010-07-15 | TESORO CORPORATION | 12982 | 14367 | 2010-07-29 | 2013-01-09 | 2013-01-13 | 2013-01-13 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 116 | BACHELOR ENLISTED QUARTERS, 1ST TANKS | 2010-07-02 | 2010-09-28 | STRAUB MARTIN A JOINT VENTURE | 38546 | 36088 | 2010-10-12 | 2012-10-12 | 2012-10-12 | 2013-06-17 | 86
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS CAMP PENDLETON CA | 116 | MV-22 AVIATION PAVEMENT | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | 14938 | 8912 | 2012-07-26 | 2014-01-03 | 2014-01-03 | 2014-01-03 | 2
2013-04-15 | 2010 | Navy - MC Active | Minor Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 120 | CONSTRUCT ADDITIONAL BERTHING FOR SOCOM | 2010-04-23 | 2010-08-09 | PRIME PROJECTS INTERNATIONAL | 872 | 1589 | 2010-08-23 | 2011-02-01 | 2011-02-01 | 2011-02-01 | 84
2013-04-15 | 2009 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NSA NORTH POTOMAC | 121 | ARRA-REPLACE UNDERGROUND STEAM LINES | 2009-04-09 | 2009-04-17 | MARADA CONTRACTING, INC | 1206 | 1249 | 2009-05-01 | 2010-04-15 | 2009-11-30 | 2010-04-03 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 121 | MAINTENANCE SHOP, TRACKED | 2010-07-27 | 2010-09-24 | I E PACIFIC INC | 20672 | 18283 | 2010-10-08 | 2012-10-13 | 2012-10-13 | 2013-04-04 | 97
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 123 | BACHELOR QUARTERS, HOMEPORT ASHORE | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | 74854 | 70776 | 2012-09-14 | 2015-02-03 | 2014-09-13 | 2015-01-27 | 3
2013-04-15 | 2013 | Navy - MC Active | Minor Construction | SN | SINGAPORE | SINGAPORE AREA COORDINATOR | 123 | TEMPORARY LCS SUSTAINMENT FACILITY | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | 755 | 662 | 2012-12-20 | 2013-03-10 | 2013-03-10 | 2013-03-10 | 72
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 126 | STATION COMM FACILITY & INFRASTRUCTURE | 2010-07-16 | 2010-09-27 | R A BURCH CONSTRUCTION CO INC | 40766 | 39507 | 2010-10-11 | 2012-10-20 | 2012-10-20 | 2013-04-07 | 78
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 127 | SUB-STATION AND ELECTRICAL UPGRADES | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 16493 | 25653 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 128 | ELEC INFRASTRUCTURE UPGRADE, 34.5KV TO 115KV | 2008-01-17 | 2011-06-02 | SOUTHERN CALIFORNIA EDISON | 41774 | 39631 | 2011-06-16 | TBD | 1996-10-08 | 2015-12-30 | 96
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 129 | ELEC POWER PLANT/CO-GEN/GAS TURBINE | 2010-07-16 | 2010-09-24 | T. B. PENICK & SONS, INC. | 54824 | 51940 | 2010-10-08 | 2013-01-29 | 2012-06-30 | 2013-01-29 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 129 | PUBLIC WORKS SHOPS CONSOLIDATION | 2009-11-17 | 2010-08-06 | HALBERT CONSTRUCTION | 8880 | 7166 | 2010-08-20 | 2012-02-27 | 2012-05-25 | 2012-06-15 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 130 | WATER IMPROVEMENTS AND STORAGE TANK | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 16911 | 25450 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 93
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 131 | SEWAGE SYSTEM IMPROVEMENTS | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 4735 | 4832 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 132 | HTHW/CHILLED WATER SYSTEM | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 14341 | 16216 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 132 | SOF CAFETERIA | 2011-05-10 | 2011-08-30 | SAUER, INC. | 11346 | 10351 | 2011-09-13 | 2013-07-08 | 2012-12-21 | 2013-02-20 | 64
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 133 | NATURAL GAS SYSTEM EXTENSION | 2009-10-22 | 2010-09-29 | HENSEL PHELPS CONSTRUCTION CO | 20931 | 14972 | 2010-10-13 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | IL | ILLINOIS | GREAT LAKES NAVAL STATION | 133 | NOSC CONSOLIDATION BATTLE CREEK MI | 2010-08-13 | 2011-01-26 | FACILITY DEFENSE CONSULTANTS INC.DBA HANKE CONSTRUCTORS | 8899 | 8473 | 2011-02-09 | 2012-09-06 | 2012-06-01 | 2012-09-06 | 94
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 134 | BACHELOR ENLISTED QUARTERS, HEADQUARTERS | 2009-05-06 | 2009-09-18 | HENSEL PHELPS SOLTEK, JV | 32868 | 32721 | 2009-10-02 | 2011-12-22 | 2011-07-18 | 2012-02-20 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 135 | BACHELOR ENLISTED QUARTERS | 2008-11-14 | 2009-03-26 | THE HASKELL COMPANY | 26167 | 25945 | 2009-04-09 | 2011-03-17 | 2011-01-25 | 2011-09-09 | 100 | -1900
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 136 | BACHELOR ENLISTED QUARTERS | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | 42882 | 40048 | 2011-06-16 | 2013-09-27 | 2013-07-07 | 2013-09-27 | 26
2013-04-15 | 2012 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | 26101 | 24598 | 2012-07-13 | 2014-08-29 | 2014-07-29 | 2014-08-30 | 13
2013-04-15 | 2010 | Navy - MC Active | Major Construction | MD | MARYLAND | NAVAL AIR STATION PAX RIVER | 140 | SPECIAL COMMUNICATIONS REQUIREMENTS ENGINEERING FACILITY | 2011-05-12 | 2011-08-08 | G-W MANAGEMENT SERVICES, LLC | 11304 | 11422 | 2011-08-22 | 2013-10-28 | 2013-01-23 | 2013-07-12 | 50
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 141 | EMS/FIRE VEHICLE FACILITY | 2009-12-14 | 2010-03-31 | CHAVIS' INC. | 6459 | 6143 | 2010-04-14 | 2012-03-15 | 2011-10-22 | 2012-03-18 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 143 | CONSTRUCT ROADS, NORTH MAINSIDE | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 22236 | 20582 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 146 | INDUSTRIAL WASTE WATER IMPROVEMENTS | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 1994 | 3561 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 146 | ORDNANCE MAGAZINES | 2010-10-21 | 2010-12-16 | SAUER, INC. | 3700 | 3371 | 2010-12-30 | 2013-05-30 | 2012-07-10 | 2013-05-30 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 148 | MISSILE MAGAZINE | 2010-10-21 | 2011-06-02 | SAUER, INC. | 4779 | 4779 | 2011-06-16 | 2013-05-30 | 2012-07-10 | 2013-05-30 | 75
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 152 | PARKING APRON/TAXIWAY EXPANSION | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | 32816 | 34087 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 82 | -22730
2013-04-15 | 2012 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 153 | BAMS UAS OPERATOR TRAINING FACILITY | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | 2851 | 2690 | 2012-07-09 | 2013-12-17 | 2013-12-17 | 2013-12-17 | 63
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 159 | OPERATIONS ACCESS POINTS - RED BEACH | 2012-03-30 | 2013-03-25 | HAL HAYS CONSTRUCTION INC | 21540 | 15407 | 2013-04-08 | TBD | TBD | TBD | 0
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 160 | BACHELOR ENLISTED QUARTERS, DEL MAR (21) AREA | 2009-07-14 | 2009-09-22 | HARPER CONSTRUCTION COMPANY, INC | 33655 | 33612 | 2009-10-06 | 2012-03-05 | 2011-06-06 | 2012-03-05 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 161 | BACHELOR ENLISTED QUARTERS, DEL MAR | 2009-05-06 | 2009-09-18 | HENSEL PHELPS SOLTEK, JV | 33003 | 33105 | 2009-10-02 | 2011-12-22 | 2011-07-18 | 2012-02-20 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 162 | AGILE CHEMICAL FACILITY PHASE 2 | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | 34869 | 32677 | 2012-08-24 | 2014-10-17 | 2016-08-22 | 2014-10-17 | 2
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | 51987 | 50432 | 2011-06-17 | 2012-10-12 | 2012-10-12 | 2013-06-17 | 85
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 164 | COMBAT TRAINING TANK COMPLEX | 2009-02-16 | 2009-04-06 | T. B. PENICK & SONS, INC. | 10320 | 9925 | 2009-04-20 | 2010-11-15 | 2010-10-13 | 2010-11-12 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVSTA EVERETT WA | 164 | SMALL CRAFT LAUNCH | 2011-05-05 | 2011-07-07 | MANSON CONSTRUCTION CO | 3120 | 3205 | 2011-07-21 | 2012-11-16 | 2012-05-02 | 2012-11-22 | 85
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 164 | MARINER'S BAY LAND ACQUISITION BOGUE |  | 2011-06-22 | LAND ACQUISITION | 4002 | 3539 | 2011-07-06 | N/A | N/A | N/A | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 165 | MILITARY WORKING DOG FACILITY | 2009-06-03 | 2009-06-29 | HALBERT CONSTRUCTION | 3702 | 3868 | 2009-07-13 | 2010-10-24 | 2010-07-17 | 2011-04-04 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 166 | ENERGETICS SYSTEMS & TECH. LAB COMPLEX - PH 1 | 2009-07-10 | 2009-09-30 | AMATEA/GRIMBERG JV | 12047 | 12837 | 2009-10-14 | 2012-09-29 | 2011-03-31 | 2012-03-29 | 95
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONLB BARSTOW CA | 167 | BACHELOR ENLISTED QUARTERS | 2009-08-07 | 2009-09-30 | SOLPAC INCDBA SOLTEK PACIFIC | 7784 | 8428 | 2009-10-14 | 2011-02-24 | 2011-04-08 | 2011-04-08 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 170 | BACHELOR ENLISTED QUARTERS, 1ST TANKS | 2010-07-02 | 2010-09-28 | STRAUB MARTIN A JOINT VENTURE | 38644 | 36056 | 2010-10-12 | 2012-10-12 | 2012-10-12 | 2013-06-17 | 84
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 171 | LAYDOWN SITE WORK, NORTH MAINSIDE | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 20560 | 23399 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 172 | SECONDARY ELEC DISTRIBUTION, NORTH MAINSIDE | 2010-01-14 | 2010-06-03 | HENSEL PHELPS CONSTRUCTION CO | 16654 | 21940 | 2010-06-17 | 2012-10-31 | 2012-03-28 | 2013-02-15 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 173 | ARMORY, 1ST TANKS | 2010-07-20 | 2010-09-29 | I E PACIFIC INC | 11038 | 10257 | 2010-10-13 | 2012-10-22 | 2012-10-22 | 2013-04-04 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVSUPPACT MONTEREY CA | 174 | MARINE METEOROLOGY CENTER | 2010-08-11 | 2010-09-29 | SOLTEK PACIFIC CONSTRUCTION CO | 10961 | 9825 | 2010-10-13 | 2012-12-04 | 2012-04-21 | 2012-12-04 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 176 | STATION INFRASTRUCTURE UPGRADES | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | 5850 | 7131 | 2011-06-15 | 2013-09-10 | 2012-11-25 | 2013-09-10 | 62
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 177 | WASH RACK | 2010-02-05 | 2010-03-31 | HAL HAYS CONSTRUCTION INC | 3509 | 3224 | 2010-04-14 | 2011-07-31 | 2011-04-15 | 2011-07-31 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 177 | MULTI-USE OPERATIONAL FITNESS AREA | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | 18819 | 17835 | 2012-08-27 | 2014-09-02 | 2014-09-02 | 2014-09-02 | 7
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 178 | AIRCRAFT PARKING APRON MODIFICATION | 2010-07-28 | 2010-12-15 | BALDI BROS INC201 CALIFORNIA AVENUE | 9184 | 8649 | 2010-12-29 | 2013-08-06 | 2012-12-29 | 2013-08-06 | 22
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 180 | IN-LINE FUELING STATION MODIFICATION | 2010-07-28 | 2010-12-15 | BALDI BROS INC201 CALIFORNIA AVENUE | 22403 | 23547 | 2010-12-29 | 2013-08-06 | 2012-12-29 | 2013-08-06 | 94
2013-04-15 | 2009 | Navy - MC Active | Major Construction | IO | DIEGO GARCIA | NAVSUPPFAC DIEGO GARCIA IO | 181 | WHARF UPGRADES & WAREHOUSE | 2009-03-06 | 2009-08-27 | BLACK CONSTRUCTION CORP. | 35032 | 22451 | 2009-09-10 | 2011-09-15 | 2011-08-17 | 2011-08-17 | 84
2013-04-15 | 2010 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 182 | MISSILE MAGAZINES, WEST LOCH | 2009-12-14 | 2010-01-28 | DCK PACIFIC CONSTRUCTION, LLC | 16223 | 14095 | 2010-02-11 | 2011-12-16 | TBD | 2011-12-20 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | IO | DIEGO GARCIA | NAVSUPPFAC DIEGO GARCIA IO | 184 | POTABLE WATER PLANT MODERNIZATION | 2012-10-25 | 2012-07-07 | BLACK CONSTRUCTION/MACE INTERNATIONAL JOINT VENTURE | 35656 | 28147 | 2012-07-21 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 0
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 185 | HANGAR 4 ADDITION | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | 27121 | 27063 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 91
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 187 | CHANNEL DREDGING | 2010-06-14 | 2010-08-23 | Awarded by Other Agency | 29757 | 45299 | 2010-09-06 | 2012-08-03 | 2012-08-03 | 2012-08-03 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NSA NORTH POTOMAC | 188 | RDT&E SUPPORT FACILITY | 2010-07-16 | 2010-09-28 | WHITING-TURNER CONTRACTING CO | 7736 | 7493 | 2010-10-12 | 2012-02-08 | 2012-06-28 | 2012-06-28 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NSA NORTH POTOMAC | 189 | RDT&E SUPPORT FACILITY | 2010-07-16 | 2010-09-28 | WHITING-TURNER CONTRACTING CO | 6177 | 6051 | 2010-10-12 | 2012-02-08 | 2012-06-28 | 2012-06-28 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 190 | BACHELOR ENLISTED QUARTERS, SAN MATEO AREA | 2009-02-02 | 2009-08-14 | TURNER-PENICK | 34235 | 34937 | 2009-08-28 | 2012-12-06 | 2011-08-22 | 2012-12-06 | 97
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 190 | AIRCRAFT REFUELING | 2009-09-05 | 2009-09-30 | AKEA, INC. | 3925 | 3770 | 2009-10-14 | 2011-04-15 | 2010-09-30 | 2012-06-06 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 191 | 2ND MAW COMMAND OPERATIONS FACILITY | 2009-03-11 | 2009-06-15 | PCL CONSTRUCTION SERVICES, INC | 16280 | 20059 | 2009-06-29 | 2011-03-17 | 2011-05-06 | 2011-07-18 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 192 | CHILD DEVELOPMENT CENTER | 2009-03-23 | 2009-06-30 | SAUER, INC. | 7929 | 11013 | 2009-07-14 | 2011-06-09 | 2010-12-01 | 2011-08-31 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 192 | GTF-HANGAR MODIFICATION (HMT-302) | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | 56417 | 54138 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 81 | -23000
2013-04-15 | 2010 | Navy - MC Active | Major Construction | LA | LOUISIANA | HDQTRS 4TH MAW NEW ORLEANS LA | 196 | RESERVE VEHICLE MAINTENANCE FACILITY | 2009-11-25 | 2010-03-11 | TEAM CONSTRUCTION, LLC J/V MILITARY& FEDERAL CONSTRUCTION CO.,INC/W.T | 3517 | 3028 | 2010-03-25 | 2011-11-30 | 2011-04-14 | 2011-09-06 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVSUPPACT MONTEREY CA | 197 | EDUCATION FACILITY GSB&PP | 2009-08-14 | 2009-09-24 | SOLTEK PACIFIC CONSTRUCTION CO | 7671 | 7914 | 2009-10-08 | 2011-06-21 | 2010-11-23 | 2011-03-13 | 99
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSUPPACT HAMPTON ROADS VA | 197 | DECENTRALIZE STEAM SYSTEM | 2012-04-17 | 2012-09-20 | SAUER, INC. | 27161 | 15543 | 2012-10-04 | 2015-03-09 | 2015-03-09 | 2015-03-09 | 4
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 199 | MSRON FOUR BOAT STORAGE BUILDING | 2012-10-31 | 2012-12-14 | JESSICO, INC | 970 | 911 | 2012-12-28 | 2013-11-08 | 2013-11-08 | 2013-11-08 | 0
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 200 | SEWAGE TREATMENT PLANT UPGRADES | 2008-11-21 | 2009-03-31 | THE HASKELL COMPANY | 14283 | 14576 | 2009-04-14 | 2011-09-01 | 2010-10-03 | 2011-11-29 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WW | WORLD WIDE | Z/VARLOCS MILCON | 200 | JOINT OPERATIONS & SUPPORT COMPLEX | 2010-04-06 | 2010-07-29 | WATTS-OBAYASHI A JV | 16763 | 15060 | 2010-08-12 | 2012-07-09 | 2011-10-13 | 2012-04-30 | 100
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY | 2011-05-26 | 2011-08-03 | JESSICO, INC | 2085 | 1998 | 2011-08-17 | 2012-11-13 | 2012-09-30 | 2012-11-13 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 202 | JOINT FORCES DEPLOYMENT STAGING AREA | 2008-10-16 | 2009-02-12 | NAN INC. DBAOCEAN HOUSE BUILDERS | 3217 | 3711 | 2009-02-26 | 2010-09-30 | 2010-04-30 | 2010-10-06 | 100
2013-04-15 | 2009 | Navy - MC Active | MFH Improvement | JA | JAPAN | NMAJOR CONSTRUCTION EAD DET SASEBO | 0202 | W/H REVITALIZATION - DRAGON CREST (44 APTS) | 2009-02-01 | 2009-07-27 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | 9397 | 8912 | 2009-08-10 | 2011-10-11 | 2011-10-08 | 2011-10-08 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 202 | COMMISSARY, MWTC | 2010-11-29 | 2012-01-25 | KBR FEDERAL SERVICES,LLC | 8128 | 8166 | 2012-02-08 | 2013-02-07 | 2013-02-07 | 2013-02-19 | 79
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | 928 | 950 | 2011-07-04 | 2012-04-16 | 2012-01-26 | 2012-04-30 | 100
2013-04-15 | 2009 | Navy - MC Active | MFH Improvement | GQ | GUAM | COMNAVMARIANAS GUAM | 0203 | RECONFIGURE INTERIOR OF 6 HOMES AT FLAG CIRCLE | 2009-04-08 | 2010-03-25 | BME & SONS, INC | 1021 | 1119 | 2010-04-08 | 2009-10-26 | 2009-10-30 | 2009-11-13 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | JA | JAPAN | NAF ATSUGI JA | 203 | AVIATION SIMULATOR TRAINING FACILITY | 2010-12-09 | 2011-07-28 | Awarded by Other Agency | 6764 | 6442 | 2011-08-11 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 34
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | 1951 | 1838 | 2012-03-16 | 2012-08-28 | 2012-09-13 | 2012-09-13 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 204 | APRA HARBOR WHARF IMPROVEMENT, INC 1 OF 2 | 2010-05-14 | 2010-09-30 | GUAM MACC BUILDERS A JV | 133082 | 104596 | 2010-10-14 | 2013-10-29 | 2013-08-27 | 2013-10-29 | 66
2013-04-15 | 2009 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 205 | FULL SCALE ELECTRIC DRIVE TEST FACILITY | 2009-02-19 | 2009-06-18 | WHITING-TURNER CONTRACTING | 20322 | 21271 | 2009-07-02 | 2013-05-22 | 2011-01-09 | 2013-08-30 | 89
2013-04-15 | 2010 | Navy - MC Active | Major Construction | WV | WEST VIRGINIA | NIOC SUGAR GROVE WV | 205 | EMERGENCY SERVICES CENTER | 2010-05-24 | 2010-09-28 | ARCHER WESTERN CONTRACTORS, LTD | 9178 | 8133 | 2010-10-12 | 2013-07-31 | 2012-04-25 | 2012-07-12 | 78
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 206 | ACADEMIC FIRE INSTRUCTIONAL FACILITY | 2009-06-05 | 2009-08-28 | CHEROKEE GENERAL CORPORATION | 3707 | 3696 | 2009-09-11 | 2011-08-12 | 2011-03-16 | 2011-08-30 | 100 | -1788
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | NJ | NEW JERSEY | NAVAL WEAPONS STATION EARLE NJ | 206 | CONSTRUCT DISPATCH CENTER | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | 1630 | 1621 | 2011-12-01 | 2013-01-25 | 2013-01-25 | 2013-03-29 | 92
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MS | MISSISSIPPI | CBC GULFPORT MS | 208 | 25TH NAVAL CONSTRUCTION REGIMENTAL HQ FAC | 2009-03-04 | 2009-04-30 | DRACE CONSTRUCTION CORP. | 8175 | 8189 | 2009-05-14 | 2011-01-28 | 2010-11-08 | 2011-01-01 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAF EL CENTRO CA | 211 | CHILD DEVELOPMENT CENTER | 2008-11-17 | 2009-01-30 | T. B. PENICK & SONS, INC. | 8761 | 9234 | 2009-02-13 | 2010-07-23 | 2010-07-29 | 2010-07-29 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 212 | CHILD DEVELOPMENT CENTER | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | 21313 | 19647 | 2012-06-19 | 2013-12-12 | 2013-12-12 | 2013-12-12 | 6
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MS | MISSISSIPPI | CBC GULFPORT MS | 215 | BATTALION MAINTENANCE FAC & EQUIPMENT YARD | 2009-08-18 | 2010-07-20 | J.J. SOSA AND ASSOCIATES, INC. | 6658 | 6502 | 2010-08-03 | 2012-08-13 | 2012-01-30 | 2012-07-24 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WW | WORLD WIDE | Z/VARLOCS MILCON | 218 | DATA CENTER | 2008-12-22 | 2009-03-25 | NISHIMATSU CONSTRUCTION CO.,LTD | 35061 | 36675 | 2009-04-08 | 2010-09-30 | 2010-09-30 | 2011-04-15 | 98
2013-04-15 | 2011 | Navy - MC Active | Major Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 219 | GENERAL WAREHOUSE | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 7716 | 7514 | 2012-04-16 | 2014-06-14 | 2013-12-26 | 2014-02-19 | 16
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 220 | AMMUNITION SUPPLY POINT | 2012-04-30 | 2012-09-10 | CH2M HILL-METAG JOINT VENTURE | 13922 | 12163 | 2012-09-24 | 2014-05-14 | 2014-04-30 | 2014-04-30 | 8
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 222 | DECENTRALIZE STEAM SYSTEM | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | 69984 | 66434 | 2012-10-12 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 15
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 235 | SECURITY FENCING 1 | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 11850 | 10274 | 2012-04-16 | 2014-06-14 | 2013-12-26 | 2014-02-19 | 34
2013-04-15 | 2010 | Navy - MC Active | Minor Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 235 | RELOCATE SECURITY | 2009-08-19 | 2009-12-14 | TOMPCO-TRITON | 3001 | 2887 | 2009-12-28 | 2010-07-29 | 2010-04-24 | 2010-09-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 236 | ARRA-REPLACE WATER DISTRIBUTION SYSTEM | 2009-05-12 | 2009-09-28 | BULLTRACK-WATTS-II, A JOINT VENTUREKELLY GREGORY | 13700 | 14130 | 2009-10-12 | 2011-06-16 | 2011-03-31 | 2011-06-16 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 237 | FIRE STATION | 2010-05-03 | 2010-07-21 | UNITED INFRASTRUCTURE PROJECTS FZCO | 4598 | 3863 | 2010-08-04 | 2013-04-30 | 2012-03-02 | 2012-11-06 | 87
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 242 | BACHELOR ENLISTED QUARTERS, PICO | 2009-07-13 | 2009-09-22 | HARPER CONSTRUCTION COMPANY, INC | 30364 | 30506 | 2009-10-06 | 2012-03-05 | 2011-06-06 | 2012-03-05 | 100
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | 1725 | 1615 | 2011-11-18 | 2013-04-23 | 2012-07-21 | 2013-04-23 | 81
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA NORFOLK NAVY SHIPYARD | 247 | ARRA-RELACE SUBSTATION Q10 | 2011-02-25 | 2011-04-14 | YORK RIVER ELECTRIC, INC. | 1907 | 1842 | 2011-04-28 | 2012-01-16 | 2012-04-22 | 2012-04-22 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CT | CONNECTICUT | NAVSUBASE NEW LONDON CT | 248 | ARRA-REPLACE STEAM AND CONDENSATE PIPING | 2010-10-07 | 2011-03-18 | VETERANS CONSTRUCTION, LLC | 3643 | 3406 | 2011-04-01 | 2012-06-18 | 2012-03-16 | 2012-06-18 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAIRENGSTA LAKEHURST | 251 | ADVANCED ARRESTING GEAR TEST SITE | 2009-02-11 | 2009-06-24 | RANCO CONSTRUCTION INC | 10772 | 10771 | 2009-07-08 | 2010-10-18 | 2010-07-29 | 2010-08-19 | 100 | -4500
2013-04-15 | 2013 | Navy - MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES | 1925 | 1744 | 2013-03-14 | TBD | TBD | TBD | 2
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAF EL CENTRO CA | 260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  | 2011-09-23 | LAND ACQUISITION | 1421 | 1426 | 2011-10-07 | N/A | N/A | N/A | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | MD | MARYLAND | NAVAL AIR STATION PAX RIVER | 263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | 33033 | 34592 | 2011-06-16 | 2013-03-22 | 2012-07-30 | 2013-08-01 | 96
2013-04-15 | 2011 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD | 2012-07-05 | 2012-09-28 | HEAD, INC. | 29901 | 21313 | 2012-10-12 | 2014-09-28 | 2014-09-28 | 2014-09-28 | 17
2013-04-15 | 2009 | Navy - MC Active | Major Construction | ME | MAINE | NSS PORTSMOUTH NAVY SHIPYARD | 268 | DD#3 WATERFRONT SUPPORT FACILITY | 2010-06-24 | 2010-09-29 | CONSIGLI CONSTRUCTION CO., INC | 21004 | 21141 | 2010-10-13 | 2013-03-29 | 2012-09-12 | 2012-12-22 | 88
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 273 | T-6B JPATS TRAINING OPS PARALOFT FACILITY | 2010-04-16 | 2011-01-05 | ARROW-IMajor Constructionruction, JOINT VENTURE | 3168 | 3238 | 2011-01-19 | 2013-03-29 | 2012-01-10 | 2012-11-21 | 47
2013-04-15 | 2009 | Navy - MC Active | Major Construction | TX | TEXAS | NAS KINGSVILLE TX | 279 | FITNESS CENTER KINGSVILLE | 2009-08-25 | 2010-03-02 | THE ROSS GROUP CONSTRUCTION CORP.DBA THE ROSS GROUP | 11585 | 13454 | 2010-03-16 | 2012-10-23 | 2011-07-27 | 2012-10-22 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | ME | MAINE | NSS PORTSMOUTH NAVY SHIPYARD | 280 | GATE 2 IMPROVEMENTS | 2011-08-31 | 2012-02-21 | Major ConstructionructionC CONSTRUCTION CORPORATION | 7403 | 7440 | 2012-03-06 | 2013-05-22 | 2013-03-21 | 2013-04-22 | 52
2013-04-15 | 2009 | Navy - MC Active | Major Construction | ME | MAINE | NSS PORTSMOUTH NAVY SHIPYARD | 282 | CONSOLIDATE GLOBAL SUB COMPLEX FACILITY | 2010-03-09 | 2010-09-30 | J. C. N. CONST. CO., INC. | 10656 | 11206 | 2010-10-14 | 2012-06-28 | 2012-03-28 | 2012-06-30 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | TX | TEXAS | NAS KINGSVILLE TX | 287 | RENEWABLE ENERGY DEMO PROJECT - SOLAR PANEL ARRAY | 2010-07-16 | 2010-09-10 | CHEVRON U.S.A. INC. | 3694 | 3420 | 2010-09-24 | 2011-12-08 | 2011-09-05 | 2011-09-05 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 293 | RECRUIT BARRACKS, SUPPORT BATTALION | 2009-04-21 | 2009-08-18 | HARPER CONSTRUCTION COMPANY, INC | 23924 | 27753 | 2009-09-01 | 2011-09-30 | 2011-06-13 | 2012-07-22 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 294 | RECRUIT BARRACKS | 2009-04-21 | 2009-08-18 | HARPER CONSTRUCTION COMPANY, INC | 26898 | 35865 | 2009-09-01 | 2011-09-30 | 2011-06-13 | 2012-07-22 | 100
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | TX | TEXAS | NAS KINGSVILLE TX | 294 | CONNECT TO KINGSVILLE WATER SYSTEM | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | 1658 | 1549 | 2012-10-08 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 0
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 296 | MESSHALL EXPANSION | 2010-01-15 | 2010-05-03 | R A BURCH CONSTRUCTION CO INC | 19100 | 17219 | 2010-05-17 | 2012-04-12 | 2011-11-09 | 2012-05-12 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NV | NEVADA | NAS FALLON NV | 306 | WARRIOR PHYSICAL TRAINING FACILITY (FITNESS CENTER) | 2010-07-21 | 2010-09-28 | STRAUB CONSTRUCTION, INC. | 11177 | 9940 | 2010-10-12 | 2012-06-07 | 2012-04-05 | 2012-05-12 | 95
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 307 | BATTALION SQUADRON HEADQUARTERS | 2010-08-16 | 2010-12-16 | SOLTEK PACIFIC CONSTRUCTION CO | 8026 | 7810 | 2010-12-30 | 2012-04-25 | 2011-12-31 | 2012-04-25 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 307 | PRODUCTION SERVICES SUPPORT FACILITY | 2010-08-11 | 2010-09-29 | MANSON-NAN HAWAII JV | 19165 | 17458 | 2010-10-13 | 2012-11-21 | 2012-06-29 | 2012-11-21 | 100
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 310 | LASER SYSTEM DEVELOPMENT LABORATORY | 2009-06-30 | 2009-06-30 | GRUNLEY/GOEL JV, LLC | 2685 | 2720 | 2009-07-14 | 2013-03-26 | 2010-10-15 | 2012-04-07 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 310 | SMALL ARMS MAGAZINE, EDSON RANGE | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | 3760 | 3108 | 2011-06-21 | 2013-08-02 | 2012-07-06 | 2012-07-06 | 10
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 311 | PARALLEL TAXIWAY | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 9283 | 8426 | 2011-06-17 | 2014-05-11 | 2013-11-29 | 2014-07-04 | 52
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA SOUTH POTOMAC | 311 | ELECTROMAGNETIC RESEARCH & ENGINEERING FAC ADDITION PHASE 2 | 2010-06-16 | 2010-09-14 | G-W MANAGEMENT SERVICES, LLC | 3721 | 3665 | 2010-09-28 | 2013-03-29 | 2012-04-04 | 2013-03-20 | 76
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MS | MISSISSIPPI | NAS MERIDIAN MS | 314 | FITNESS CENTER - MERIDIAN | 2009-05-19 | 2009-08-28 | F AND T JOINT VENTURE | 7687 | 7462 | 2009-09-11 | 2011-08-08 | 2011-03-06 | 2011-08-07 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 316 | RECRUIT RECONDITIONING FACILITY | 2009-04-21 | 2009-08-18 | HARPER CONSTRUCTION COMPANY, INC | 12710 | 16596 | 2009-09-01 | 2011-09-30 | 2011-06-13 | 2012-07-22 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MS | MISSISSIPPI | NAS MERIDIAN MS | 319 | ARRA-CHILD DEVELOPMENT CENTER | 2010-04-29 | 2010-08-04 | I LEETEX/HILL & WILKINSON LLC | 5907 | 6168 | 2010-08-18 | 2012-02-16 | 2012-02-10 | 2012-02-18 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MD | MARYLAND | NAVSUPPACT ANNAPOLIS | 327 | CHILD DEVELOPMENT CENTER | 2009-07-02 | 2009-12-17 | HASCON, LLC | 8923 | 9180 | 2009-12-31 | 2011-12-21 | 2011-07-22 | 2011-12-21 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE SAN DIEGO | 327 | BERTHING PIER 12 REPL & DREDGING | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | 99132 | 88376 | 2011-10-13 | 2013-10-22 | 2013-10-22 | 2013-10-22 | 57 | -1813
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAS LEMOORE CA | 329 | ARRA-EXPAND CHILD DEVELOPMENT CENTER | 2009-04-03 | 2009-06-15 | T. B. PENICK & SONS, INC. | 7726 | 7785 | 2009-06-29 | 2010-11-05 | 2010-11-05 | 2010-11-05 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 330 | PHYSICAL FITNESS CENTER, HORNO | 2009-06-29 | 2009-08-25 | SOLTEK PACIFIC CONSTRUCTION CO | 6590 | 10890 | 2009-09-08 | 2011-11-18 | 2010-08-20 | 2011-12-12 | 100
2013-04-15 | 2011 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAS LEMOORE CA | 331 | WATER WELL | 2011-01-11 | 2011-09-30 | EPC CORPORATION | 2713 | 2874 | 2011-10-14 | 2013-05-21 | 2012-10-01 | 2013-05-21 | 17
2013-04-15 | 2010 | Navy - MC Active | Major Construction | IN | INDIANA | NAVAL SUPPORT ACTIVITY CRANE | 340 | STRATEGIC WEAPONS SYSTEM ENGINEERING | 2010-05-26 | 2010-08-25 | CANT BE BEAT FENCE ANDCONSTRUCTION, LLC | 14613 | 13035 | 2010-09-08 | 2012-05-28 | 2012-01-05 | 2012-05-28 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 347 | FITNESS CENTER, NEWPORT | 2009-03-24 | 2009-08-10 | CONSIGLI CONSTRUCTION CO., INC | 22201 | 38141 | 2009-08-24 | 2013-09-07 | 2011-09-18 | 2013-09-07 | 77
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 357 | BACHELOR ENLISTED QUARTERS, MARGARITA(33)AREA | 2009-07-15 | 2009-09-25 | HARPER CONSTRUCTION COMPANY, INC | 30862 | 31423 | 2009-10-09 | 2011-08-19 | 2011-03-19 | 2011-08-19 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONRD/BEAUFORT PI SC | 360 | ELECTRICAL SUBSTATION AND SYSTEM UPGRADE | 2010-04-30 | 2010-08-31 | TEAM CONSTRUCTION, LLC J/V MILITARY& FEDERAL CONSTRUCTION CO.,INC/W.T | 6455 | 5108 | 2010-09-14 | 2013-11-30 | 2012-03-08 | 2013-12-18 | 70
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAS LEMOORE CA | 363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | 1980 | 1869 | 2012-09-12 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 73
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAS LEMOORE CA | 364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | 2000 | 1835 | 2012-10-12 | 2013-09-26 | 2013-09-26 | 2013-09-26 | 11
2013-04-15 | 2009 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONRD/BEAUFORT PI SC | 367 | RECRUIT BARRACKS - 3RD BATTALION, PHASE 2 | 2008-04-25 | 2008-10-31 | WALTON CONSTRUCTION - A CORECOMPANY, LLC | 38098 | 37397 | 2008-11-14 | 2011-05-26 | 2010-09-21 | 2011-05-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONRD/BEAUFORT PI SC | 371 | RECRUIT BARRACKS, 3RD BATTALION, PHASE 3 | 2008-04-25 | 2009-04-22 | WALTON CONSTRUCTION - A CORECOMPANY, LLC | 21122 | 26292 | 2009-05-06 | 2011-05-26 | 2010-09-21 | 2011-05-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | TN | TENNESSEE | NAVSUPPACT MIDSOUTH MEMPHIS TN | 371 | ARRA-CHILD DEVELOPMENT CENTER | 2009-05-01 | 2009-06-30 | SHERRICK CONSTRUCTION INC. | 10217 | 11552 | 2009-07-14 | 2011-11-21 | 2011-12-02 | 2011-12-02 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA NORFOLK NAVY SHIPYARD | 383 | CONTROLLED INDUSTRIAL FACILITY | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | 60576 | 29547 | 2012-06-14 | 2014-11-11 | 2014-09-28 | 2014-11-11 | 6
2013-04-15 | 2009 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONRD/BEAUFORT PI SC | 396 | CHILD DEVELOPMENT CENTER | 2009-07-21 | 2009-09-09 | SAUER, INC. | 9854 | 14290 | 2009-09-23 | 2011-12-13 | 2011-03-18 | 2011-12-30 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MARCORPRCUITDEP SAN DIEGO CA | 400 | MARINE CORPS ENERGY INITIATIVE | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | 9928 | 9373 | 2011-06-17 | 2012-06-15 | 2012-06-17 | 2012-07-11 | 98
2013-04-15 | 2012 | Navy - MC Active | Major Construction | HI | HAWAII | PACMISRANFAC HAWAIIAN AREA | 400 | NORTH LOOP ELECTRICAL REPLACEMENT | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | 6498 | 6083 | 2012-03-29 | 2014-01-02 | 2014-01-02 | 2014-01-02 | 17
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 402 | SALTWATER COOLING AND FIRE PROTECTION IMPRS | 2009-06-19 | 2009-09-11 | WATTS CONSTRUCTORS, LLC | 4756 | 4541 | 2009-09-25 | 2010-11-30 | 2010-09-26 | 2010-12-31 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE SAN DIEGO | 405 | BACHELOR QUARTERS HOMEPORT ASHORE | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | 72294 | 69170 | 2011-10-14 | 2013-12-03 | 2013-10-23 | 2013-12-03 | 69
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 406 | OPERATIONAL FLIGHT SIMULATOR | 2010-03-17 | 2010-07-15 | GDI/ALLEN & SHARIFF JOINT VENTURE | 3370 | 3219 | 2010-07-29 | 2012-04-25 | 2011-08-15 | 2011-09-16 | 99
2013-04-15 | 2012 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | 13341 | 10307 | 2012-06-08 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 50
2013-04-15 | 2011 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS BEAUFORT SC | 420 | PHYSICAL FITNESS CENTER, BEAUFORT | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | 14780 | 14481 | 2011-09-21 | 2013-05-15 | 2013-06-08 | 2013-07-16 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | PACMISRANFAC HAWAIIAN AREA | 422 | ADVANCED RADAR DETECTION LABORATORY | 2009-06-10 | 2009-09-29 | TOMajor ConstructionructionO CORP | 22050 | 24511 | 2009-10-13 | 2013-05-30 | 2011-07-31 | 2012-05-15 | 98
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 424 | DRY DOCK 5 INTEGRATAED WATER TREATMENT SYSTEM | 2009-06-02 | 2009-08-31 | WATTS CONSTRUCTORS, LLC | 1979 | 1832 | 2009-09-14 | 2012-02-02 | 2010-09-15 | 2011-08-25 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS BEAUFORT SC | 428 | EOD/ORDNANCE OPERATIONS FACILITY | 2008-11-14 | 2009-03-06 | TEAM CONSTRUCTION, LLC J/V MILITARY& FEDERAL CONSTRUCTION CO.,INC/W.T | 5540 | 7022 | 2009-03-20 | 2011-09-29 | 2010-09-12 | 2011-08-08 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | TX | TEXAS | NAS CORPUS CHRISTI TX | 437 | OPERATIONAL FACILITIES FOR T-6, GOLIAD OLF | 2011-01-11 | 2011-08-05 | THE ROSS GROUP CONSTRUCTION CORP.DBA THE ROSS GROUP | 21037 | 20306 | 2011-08-19 | 2012-09-26 | 2012-05-26 | 2012-09-26 | 93
2013-04-15 | 2010 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS BEAUFORT SC | 441 | WIDE BODY AIRCRAFT FUEL LANE | 2009-12-09 | 2010-01-25 | SMALL BUSINESS GROUP, INC | 1037 | 923 | 2010-02-08 | 2010-11-03 | 2011-01-28 | 2011-01-28 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS BEAUFORT SC | 442 | VERTICAL LANDING PADS FOR F-35B | 2011-12-06 | 2012-03-30 | HEAD, INC. | 18987 | 17963 | 2012-04-13 | 2013-08-07 | 2013-08-07 | 2013-08-07 | 57
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 443 | MESS HALL, OCS | 2009-07-22 | 2009-12-30 | SAUER, INC. | 11842 | 13292 | 2010-01-13 | 2013-03-29 | 2011-07-30 | 2013-03-29 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS BEAUFORT SC | 444 | TRAINING AND SIMULATOR FACILITY | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | 40940 | 37654 | 2011-06-20 | 2013-09-23 | 2013-09-03 | 2013-09-23 | 87
2013-04-15 | 2010 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 447 | AIRCRAFT MAINTENANCE HANGAR, PHASE 1 (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | 19374 | 18624 | 2011-06-23 | 2012-12-07 | 2012-10-08 | 2012-12-31 | 91
2013-04-15 | 2009 | Navy - MC Active | Major Construction | TX | TEXAS | NAS CORPUS CHRISTI TX | 448 | PARKING APRON RECAPITALIZATION | 2009-05-26 | 2009-07-27 | GRACE PAVING & CONSTRUCTION INC | 3513 | 3312 | 2009-08-10 | 2010-08-04 | 2010-08-11 | 2010-08-11 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 451 | OFFICER TRAINING COMMAND QUARTERS | 2010-02-12 | 2010-08-13 | ABSHER CONSTRUCTION CO | 44074 | 43802 | 2010-08-27 | 2013-05-22 | 2012-12-28 | 2013-05-22 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS BEAUFORT SC | 454 | F-35B AIRCRAFT HANGAR FOR FRS-2 | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | 45398 | 40900 | 2011-06-20 | 2013-09-23 | 2013-09-03 | 2013-09-23 | 69
2013-04-15 | 2011 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | 47715 | 43854 | 2011-06-23 | 2012-12-07 | 2012-10-08 | 2012-12-31 | 97
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | TX | TEXAS | NAS CORPUS CHRISTI TX | 462 | FIRE STATION/CRASH CREW FACILITY | 2010-01-01 | 2010-02-25 | THE DLP GROUP INCDLP CONSULTING | 1385 | 1400 | 2010-03-11 | 2011-10-21 | 2011-03-12 | 2011-03-12 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CT | CONNECTICUT | NAVSUBASE NEW LONDON CT | 464 | PIER 31 REPLACEMENT | 2009-03-16 | 2009-07-01 | AMERICAN BRIDGE COMPANY | 46217 | 42262 | 2009-07-15 | 2012-02-28 | 2011-07-26 | 2012-02-29 | 97
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 465 | CONSOLIDATED SLC TRAINING & CSS-15 HQ FAC | 2009-11-01 | 2010-05-10 | DCK-ECC PACIFIC GUAM, LLC | 30672 | 24746 | 2010-05-24 | 2013-02-27 | 2011-11-30 | 2012-09-27 | 75
2013-04-15 | 2009 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 469 | BACHELOR ENLISTED QUARTERS, MAIN BASE | 2009-02-06 | 2009-04-30 | HENSEL PHELPS CONSTRUCTION CO. | 59978 | 58289 | 2009-05-14 | 2011-05-12 | 2011-05-15 | 2011-05-15 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | LA | LOUISIANA | NAS JRB NEW ORLEANS LA | 477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | 13604 | 13714 | 2011-06-17 | 2013-08-14 | 2013-06-07 | 2013-09-28 | 78
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 479 | INFRASTRUCTURE, RUSSELL ROAD, PHASE 1 | 2009-07-01 | 2009-09-29 | GDI/ALLEN & SHARIFF JOINT VENTURE | 7516 | 8237 | 2009-10-13 | 2010-11-30 | 2010-09-30 | 2010-12-09 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CT | CONNECTICUT | NAVSUBASE NEW LONDON CT | 481 | INDOOR SMALL ARMS RANGE | 2010-02-19 | 2010-07-22 | WATERMARK ENVIRONMENTAL, INC. | 10940 | 10361 | 2010-08-05 | 2012-09-14 | 2012-02-06 | 2012-07-12 | 94
2013-04-15 | 2010 | Navy - MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 482 | RENOVATION OF SENIOR ENLISTED ACADEMY (BLDG 1269) | 2011-02-03 | 2011-04-14 | CUTTER ENTERPRISES, LLC | 6550 | 8240 | 2011-04-28 | 2013-04-23 | 2012-07-20 | 2013-04-26 | 89
2013-04-15 | 2010 | Navy - MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 485 | RENOVATIONS TO PERRY HALL (NAPS TRAINING SUPPORT SPACE) | 2010-09-17 | 2010-11-05 | WATERMARK ENVIRONMENTAL, INC. | 8454 | 8427 | 2010-11-19 | 2012-12-17 | 2012-01-14 | 2013-06-30 | 82
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MD | MARYLAND | NAS PATUXENT RIVER SEC DET | 492 | ADDITION TO CHILD DEVELOPMENT CENTER | 2009-12-22 | 2010-11-04 | GRUNLEY/GOEL JV E LLC | 2604 | 2811 | 2010-11-18 | 2013-04-12 | 2012-05-27 | 2013-04-12 | 74
2013-04-15 | 2009 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 495 | APPLIED INSTRUCTION FACILITY, MAWTS | 2009-03-26 | 2009-07-06 | T. B. PENICK & SONS, INC. | 17817 | 19901 | 2009-07-20 | 2011-11-16 | 2010-11-15 | 2011-11-16 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 499 | POWER DISTRIBUTION UPGRADES | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | 29520 | 21152 | 2012-10-08 | 2014-10-09 | 2014-10-09 | 2014-10-09 | 3
2013-04-15 | 2011 | Navy - MC Active | MFH Improvement | JA | JAPAN | MAJOR CONSTRUCTIONAS IWAKUNI JA | 0501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | 11626 | 11102 | 2011-10-06 | 2013-02-28 | 2013-01-14 | 2013-02-28 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 503 | CHILD DEVELOPMENT CENTER | 2009-04-30 | 2009-06-30 | BARNHART-BALFOUR BEATTY, INC. | 11565 | 12633 | 2009-07-14 | 2012-01-23 | 2011-01-21 | 2012-01-12 | 96
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 503 | ADD/ALTER MARINE MAMMAL SURGICAL CENTER | 2010-08-23 | 2010-09-30 | SYNERGY SYSTEMS INC | 2992 | 2771 | 2010-10-14 | 2012-09-21 | 2012-06-02 | 2012-08-28 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | 7518 | 7143 | 2012-08-29 | 2014-02-21 | 2014-02-21 | 2014-02-21 | 1
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 511 | CONSTRUCT MARINE MAMMAL PIER | 2009-02-27 | 2009-05-04 | ALLEN ENGINEERING CONTRACTOR, INC | 1972 | 2002 | 2009-05-18 | 2010-03-03 | 2009-12-31 | 2011-11-15 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA NORFOLK NAVY SHIPYARD | 516 | SHIP REPAIR PIER REPLACEMENT INC 1 OF 2 | 2010-05-27 | 2010-09-29 | SKANSKA USA CIVIL SOUTHEAST INC | 133014 | 121056 | 2010-10-13 | 2015-06-07 | 2014-11-22 | 2015-06-09 | 71
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 517 | AIRCRAFT MAINTENANCE HANGAR, TYPE II | 2008-12-19 | 2009-05-07 | ARCHER WESTERN CONTRACTORS, LTD | 26840 | 29229 | 2009-05-21 | 2012-01-04 | 2011-03-07 | 2012-01-04 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 518 | ARRA-CHILD DEVELOPMENT CENTER | 2009-07-30 | 2009-09-30 | T. B. PENICK & SONS, INC. | 9724 | 9986 | 2009-10-14 | 2011-06-28 | 2011-01-22 | 2011-09-05 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 520 | BACHELOR ENLISTED QUARTERS, HORNO | 2008-12-24 | 2009-07-27 | TURNER-PENICK | 37582 | 37811 | 2009-08-10 | 2011-08-04 | 2011-08-04 | 2011-08-04 | 100
2013-04-15 | 2010 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 521 | CONSTRUCT EOD FACILITY | 2010-09-03 | 2010-09-30 | RORE, INC. | 1984 | 1882 | 2010-10-14 | 2012-07-23 | 2011-10-15 | 2012-07-23 | 97
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | 18599 | 17396 | 2012-10-11 | 2014-10-31 | 2014-10-12 | 2014-10-12 | 6
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 528 | TORPEDO EXERCISE SUPPORT BUILDING | 2009-11-01 | 2010-05-10 | DCK-ECC PACIFIC GUAM, LLC | 6399 | 7996 | 2010-05-24 | 2013-02-27 | 2011-11-30 | 2012-09-27 | 84
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 532 | ARMORY, 1ST MARINE DIVISION | 2012-04-23 | 2012-08-31 | A&D GC INC | 11201 | 10568 | 2012-09-14 | 2013-12-24 | 2013-12-24 | 2013-12-24 | 8
2013-04-15 | 2011 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 533 | SIMULATOR FACILITY (JSF) | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | 26438 | 22851 | 2011-06-17 | 2013-03-05 | 2012-06-02 | 2013-03-05 | 92
2013-04-15 | 2009 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 534 | WSTEWTR COLLECTION SYS REPAIRS & UPGR PHASE 1 | 2008-12-03 | 2009-08-25 | CORE TECH INTERNATIONAL CORPORATION | 18410 | 16126 | 2009-09-08 | 2012-02-10 | 2011-09-24 | 2011-12-29 | 91
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CU | CUBA | NAVSTA GUANTANAMO BAY | 535 | FITNESS CENTER, GUANTANAMO | 2009-12-11 | 2009-09-30 | BRDC, A JOINT VENTURE | 18562 | 21819 | 2009-10-14 | 2013-05-31 | 2012-11-29 | 2013-03-24 | 78
2013-04-15 | 2012 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 535 | AIRCRAFT MAINTENANCE HANGAR (JSF) | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | 32048 | 29773 | 2012-09-20 | 2014-07-07 | 2014-07-07 | 2014-07-07 | 6
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 541 | ADDITION, MAJOR CONSTRUCTIONRUCTIONU RESEARCH CENTER | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | 31343 | 28291 | 2012-10-09 | 2014-10-16 | 2014-08-16 | 2014-08-16 | 5
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 541 | MULTI-PURPOSE BUILDING ADDITION | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | 15610 | 14642 | 2012-10-11 | 2014-04-20 | 2014-04-20 | 2014-04-20 | 0
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | 11118 | 10551 | 2012-09-25 | 2014-03-28 | 2014-03-28 | 2014-03-28 | 10
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 543 | NAVELSG RESERVE FORCES MARSHALLING YARDS | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | 738 | 696 | 2013-01-30 | 2014-01-21 | 2014-01-21 | 2014-01-21 | 1
2013-04-15 | 2012 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | 79917 | 75012 | 2012-04-03 | 2014-05-20 | 2014-05-20 | 2014-05-20 | 25
2013-04-15 | 2011 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 546 | UTILITY UPGRADES (JSF) | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | 40106 | 35848 | 2011-06-21 | 2013-02-12 | 2012-07-08 | 2013-01-15 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 547 | STUDENT BARRACKS, THE BASIC SCHOOL PHASE 3 | 2008-12-23 | 2009-05-01 | HARKINS BUILDERS INC. | 25299 | 26358 | 2009-05-15 | 2012-06-01 | 2012-04-30 | 2012-10-12 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 548 | STUDENT DINING FACILITY, THE BASIC SCHOOL | 2010-06-11 | 2010-10-19 | HARKINS BUILDERS INC. | 15483 | 14106 | 2010-11-02 | 2013-03-29 | 2012-08-09 | 2013-04-11 | 74
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 550 | FIRE STATION RENOVATION, MWTC | 2010-01-25 | 2010-03-25 | J I GARCIA CONSTRUCTION INC | 4631 | 4289 | 2010-04-08 | 2012-07-09 | 2011-07-19 | 2012-09-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 555 | INSTRUCTION FACILITY, THE BASIC SCHOOL, PH 1 | 2008-12-23 | 2009-05-01 | HARKINS BUILDERS INC. | 24624 | 25140 | 2009-05-15 | 2012-06-01 | 2012-04-30 | 2012-10-12 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 556 | AIRFIELD ELECTRICAL DISTRIBUTION & CONTROL | 2010-03-15 | 2010-06-24 | MAC ELECTRIC INC | 1727 | 1598 | 2010-07-08 | 2011-11-30 | 2011-06-24 | 2011-12-15 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE VENTURA CTY PT MUGU CA | 559 | E-2D AIRCREW TRAINING FACILITY | 2012-03-21 | 2012-06-29 | ALLEN ENGINEERING CONTRACTOR, INC | 13210 | 12371 | 2012-07-13 | 2013-10-07 | 2013-10-07 | 2013-10-07 | 18
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE POINT LOMA | 563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 | 2012-06-20 | 2012-09-28 | NOVA R M F | 1939 | 1775 | 2012-10-12 | 2013-09-27 | 2013-09-27 | 2013-09-27 | 29
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 565 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 4 | 2010-06-11 | 2010-10-19 | HARKINS BUILDERS INC. | 33584 | 30792 | 2010-11-02 | 2013-03-29 | 2012-08-09 | 2013-04-11 | 93
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 | 2011-06-20 | 2012-05-02 | HENSEL PHELPS CONSTRUCTION CO. | 45465 | 36331 | 2012-05-16 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 | 2011-10-05 | 2012-05-02 | HENSEL PHELPS CONSTRUCTION CO. | 27222 | 24940 | 2012-05-16 | 2015-05-17 | 2015-05-17 | 2015-05-17 | 3
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 570 | HEADQUARTERS FACILITY, OCS | 2009-07-22 | 2009-12-30 | SAUER, INC. | 5581 | 5551 | 2010-01-13 | 2013-03-29 | 2011-07-30 | 2013-03-29 | 99
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | 6555 | 6244 | 2012-08-10 | 2013-09-05 | 2013-09-05 | 2013-09-05 | 14
2013-04-15 | 2011 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | 19793 | 15877 | 2011-08-10 | 2012-12-14 | 2012-07-25 | 2012-12-14 | 99
2013-04-15 | 2012 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 575 | AUXILIARY LANDING FIELD (JSF) | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | 29475 | 26494 | 2012-07-09 | 2013-06-25 | 2013-06-25 | 2013-06-25 | 47
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 578 | FITNESS CENTER, PEARL HARBOR | 2008-10-07 | 2009-07-06 | KIEWIT BUILDING GROUP INC. | 29510 | 32836 | 2009-07-20 | 2012-04-25 | 2012-02-17 | 2012-04-25 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 578 | VAN PAD RELOCATION (JSF) | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | 15045 | 14649 | 2011-09-26 | 2013-01-22 | 2012-09-11 | 2013-03-20 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA NORFOLK NAVY SHIPYARD | 581 | INDUSTRIAL ACCESS IMPROVEMENTS, MAIN GATE 15 | 2010-04-06 | 2010-06-24 | YORK RIVER ELECTRIC, INC. | 8428 | 8137 | 2010-07-08 | 2012-11-05 | 2012-07-12 | 2012-11-07 | 94
2013-04-15 | 2013 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 582 | UNDERSEA SURVEILLANCE SCIF FACILITY | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | 3923 | 3808 | 2012-12-03 | 2013-11-29 | 2013-11-29 | 2013-11-29 | 1
2013-04-15 | 2011 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | 54843 | 44679 | 2011-06-21 | 2013-02-12 | 2012-07-08 | 2013-01-15 | 78
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 590 | CHILD DEVELOPMENT CENTER | 2009-12-17 | 2010-05-10 | BIG DESBUILD JOINT VENTURE INC. | 16587 | 17152 | 2010-05-24 | 2013-01-31 | 2011-11-15 | 2012-07-31 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | 34087 | 30822 | 2011-10-14 | 2013-08-09 | 2013-08-09 | 2013-08-09 | 60
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAF EL CENTRO CA | 600 | RESERVE CENTER MOVE TO LUKE AFB, NOSC PHOENIX | 2010-01-21 | 2010-04-22 | A&D GC INC | 11667 | 10607 | 2010-05-06 | 2011-12-16 | 2011-09-19 | 2011-11-21 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 601 | ARRA-CHILD DEVELOPMENT CENTER | 2009-08-13 | 2009-09-25 | HARPER CONSTRUCTION COMPANY, INC | 11287 | 12508 | 2009-10-09 | 2011-02-24 | 2011-02-06 | 2011-06-14 | 98
2013-04-15 | 2011 | Navy - MC Active | Major Construction | GA | GEORGIA | SUBASE KINGS BAY GA | 601 | SECURITY ENCLAVE AND VEHICLE BARRIER | 2011-12-13 | 2012-03-16 | SAUER, INC. | 37278 | 33834 | 2012-03-30 | 2013-09-07 | 2013-09-07 | 2013-09-07 | 37
2013-04-15 | 2012 | Navy - MC Active | MFH Improvement | JA | JAPAN | MAJOR CONSTRUCTIONAS IWAKUNI JA | 0601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | 13357 | 12685 | 2012-08-13 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 0
2013-04-15 | 2009 | Navy - MC Active | Major Construction | GA | GEORGIA | SUBASE KINGS BAY GA | 602 | REACTION FORCE FACILITY COMMUNICATIONS ADDN | 2009-08-10 | 2009-09-30 | DCK NORTH AMERICA, LLC | 4174 | 4645 | 2009-10-14 | 2011-09-30 | 2011-04-09 | 2011-04-09 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 602 | ARMED FORCES RESERVE CENTER | 2011-06-30 | 2011-09-16 | Awarded by Other Agency | 11400 | 10203 | 2011-09-30 | TBD | TBD | TBD | 58
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 604 | CHILD DEVELOPMENT CENTER | 2010-04-21 | 2010-08-31 | T. B. PENICK & SONS, INC. | 15101 | 14127 | 2010-09-14 | 2013-05-31 | 2012-02-02 | 2012-11-02 | 97
2013-04-15 | 2010 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVMAG INDIAN ISLAND WA | 605 | ORDNANCE STORAGE PADS WITH COVERS (2) | 2010-04-14 | 2010-08-17 | ADVANCED TECHNOLOGY CONSTRUCTION | 3803 | 4564 | 2010-08-31 | 2013-04-27 | 2012-02-23 | 2013-06-06 | 94
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 610 | RECRUIT MARKSMANSHIP TRAINING FACILITY | 2010-04-26 | 2010-08-17 | A&D GC INC | 13594 | 11879 | 2010-08-31 | 2012-06-11 | 2012-02-23 | 2012-06-14 | 94
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 611 | BACHELOR ENLISTED QUARTERS | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | 32910 | 31342 | 2012-10-13 | 2014-10-16 | 2014-10-16 | 2014-10-16 | 4
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 612 | ENLISTED DINING FACILITY | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | 5028 | 4811 | 2012-10-13 | 2014-10-16 | 2014-10-16 | 2014-10-16 | 8
2013-04-15 | 2009 | Navy - MC Active | Major Construction | MD | MARYLAND | NAVSUPPACT ANNAPOLIS | 613 | ARRA-REPLACE STEAM GENERATION PLANT | 2009-06-04 | 2009-07-15 | GDI/ALLEN & SHARIFF JOINT VENTURE | 2421 | 2544 | 2009-07-29 | 2010-11-30 | 2010-09-30 | 2010-11-30 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 614 | SOTG BATTLE COURSE | 2009-08-26 | 2009-09-30 | REYES CONSTRUCTION INC | 22245 | 21894 | 2009-10-14 | 2012-05-08 | 2011-04-23 | 2012-05-10 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 614 | SOUTH MAINSIDE ELECTRICAL SUBSTATION | 2010-07-22 | 2010-09-29 | WHITING-TURNER CONTRACTING CO | 11138 | 11426 | 2010-10-13 | 2014-04-01 | 2012-04-11 | 2013-12-31 | 97
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 615 | APRON EXPANSION, PHASE 1 | 2009-01-13 | 2009-03-30 | BARNES & POWELL ELECTRICAL CO, INC | 6006 | 7291 | 2009-04-13 | 2010-12-16 | 2010-09-02 | 2011-01-13 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 615 | SNCO ACADEMIC FACILITY ADDITION | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | 6836 | 6681 | 2011-07-04 | 2013-05-31 | 2012-12-21 | 2013-03-01 | 86
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 619 | INSTRUCTION FACILITY ADDITION, TBS | 2008-12-23 | 2009-05-01 | HARKINS BUILDERS INC. | 6207 | 6379 | 2009-05-15 | 2012-06-01 | 2012-04-30 | 2012-10-12 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 619 | TACTICAL SUPPORT VAN PAD ADDITION | 2009-10-14 | 2010-01-26 | ALDERMAN BUILDING CO., INC. | 3469 | 3347 | 2010-02-09 | 2011-07-14 | 2011-01-26 | 2011-08-20 | 93
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 620 | ENLISTED DINING FACILITY | 2009-02-20 | 2009-05-27 | SAUER, INC. | 14043 | 13451 | 2009-06-10 | 2011-07-26 | 2010-12-17 | 2012-03-01 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 620 | BATTALION TRAINING FACILITY, MSGBN | 2010-05-28 | 2010-09-30 | SAUER, INC. | 10980 | 10445 | 2010-10-14 | 2012-02-24 | 2011-11-11 | 2011-11-11 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | GA | GEORGIA | SUBASE KINGS BAY GA | 620 | WATERFRONT EMERGENCY GENERATORS | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | 15010 | 14259 | 2011-09-02 | 2013-05-13 | 2013-05-13 | 2013-05-13 | 83
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 621 | EMBASSY SECURITY GROUP FACILITIES | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | 26082 | 24570 | 2013-03-14 | TBD | TBD | TBD | 0
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 623 | P-8A INTEGRATED TRAINING CENTER | 2009-03-02 | 2009-09-04 | WHITING-TURNER CONTRACTING CO | 42945 | 48670 | 2009-09-18 | 2011-08-03 | 2011-06-30 | 2011-08-03 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 624 | P-8A TRAINING FACILITY | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | 14194 | 13671 | 2012-07-09 | 2013-12-17 | 2013-12-17 | 2013-12-17 | 44
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 625 | MAJOR CONSTRUCTIONRUCTION INFORMATION OPERATIONS CENTER | 2010-05-07 | 2010-09-28 | THE HASKELL COMPANY | 29630 | 25462 | 2010-10-12 | 2012-09-19 | 2012-05-13 | 2012-09-18 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 629 | ARMED FORCES RESERVE CENTER | 2010-08-20 | 2010-09-30 | Awarded by Other Agency | 7568 | 7641 | 2010-10-14 | 2013-04-11 | 2013-04-11 | 2013-04-11 | 33
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS JACKSONVILLE FL | 630 | P-8A (MMA) FACILITIES MODIFICATION | 2010-04-29 | 2010-06-30 | SAUER, INC. | 3916 | 7302 | 2010-07-14 | 2011-11-08 | 2011-08-04 | 2011-10-30 | 83
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 632 | BACHELOR ENLISTED QUARTERS, NEW RIVER | 2008-04-23 | 2008-11-12 | CADDELL CONSTRUCTION COMPANY, INC. | 34840 | 32321 | 2008-11-26 | 2011-03-31 | 2010-08-09 | 2011-02-15 | 96 | -2895
2013-04-15 | 2012 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 632 | ACADEMIC INSTRUCTION FACILITY | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | 60736 | 57243 | 2012-10-09 | 2014-10-16 | 2014-08-16 | 2014-08-16 | 5
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 636 | BACHELOR ENLISTED QUARTERS, NEW RIVER | 2008-04-23 | 2008-11-12 | CADDELL CONSTRUCTION COMPANY, INC. | 25550 | 22080 | 2008-11-26 | 2011-03-31 | 2010-08-09 | 2011-02-15 | 93
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 652 | VMMT-204 MAINTENANCE HANGAR, PHASE 3 | 2010-07-14 | 2010-09-27 | F & S MECHANICAL AND PLUMBINGSERVICES, INC. | 26687 | 25079 | 2010-10-11 | 2013-12-30 | 2013-09-30 | 2013-12-29 | 75
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 683 | HANGAR | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 62154 | 56111 | 2011-06-17 | 2014-05-11 | 2013-11-29 | 2014-07-04 | 32
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 686 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE | 2008-11-14 | 2009-05-01 | STRAUB MARTIN A JOINT VENTURE | 42264 | 50775 | 2009-05-15 | 2011-09-16 | 2011-03-28 | 2011-08-20 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 687 | MV-22 MAINTENANCE HANGAR (HMLA) | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 62617 | 57143 | 2011-06-17 | 2014-05-11 | 2013-11-29 | 2014-07-04 | 29
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 688 | APRON EXPANSION, PHASE 2 | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | 32726 | 28295 | 2011-06-17 | 2014-05-11 | 2013-11-29 | 2014-07-04 | 58
2013-04-15 | 2009 | Navy - MC Active | MFH Improvement | JA | JAPAN | MAJOR CONSTRUCTIONAS IWAKUNI JA | 0701 | WHOLEHOUSE RESTORATION, MONZEN TOWNHOUSES, PH-2 | 2009-04-16 | 2009-09-07 | NIPPO CORPORATION | 8828 | 8645 | 2009-09-21 | 2012-04-06 | 2012-04-15 | 2012-04-15 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 701 | FIRE STATION | 2009-07-30 | 2009-09-30 | Z-CORP | 7131 | 7397 | 2009-10-14 | 2011-08-16 | 2011-02-22 | 2011-08-16 | 97
2013-04-15 | 2010 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVSTA EVERETT WA | 702 | SPECIALIZED SERE TRAINING AREA | 2009-12-06 | 2010-03-31 | LCC-MZT TEAM II | 13266 | 12615 | 2010-04-14 | 2011-11-17 | 2011-09-02 | 2011-10-10 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 704 | BERTH LIMA CONVERSION | 2008-12-16 | 2009-02-06 | BARNHART-BALFOUR BEATTY, INC. | 35111 | 40154 | 2009-02-20 | 2010-03-19 | 2010-03-31 | 2012-07-01 | 99
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 705 | FITNESS CENTER, NORTH ISLAND | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | 46630 | 42319 | 2012-08-21 | 2015-03-16 | 2015-03-16 | 2015-07-27 | 2
2013-04-15 | 2012 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 705 | AIRCRAFT MAINTENANCE HANGAR AND APRON | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | 57582 | 54100 | 2012-06-12 | 2014-07-07 | 2014-07-07 | 2014-07-07 | 21
2013-04-15 | 2012 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 710 | ORDNANCE LOADING AREA ADDITION | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | 7768 | 7273 | 2012-06-12 | 2014-07-07 | 2014-07-07 | 2014-07-07 | 15
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 714 | GYMNASIUM/OUTDOOR POOL | 2009-07-24 | 2010-12-09 | WHITING-TURNER CONTRACTING CO | 17792 | 16244 | 2010-12-23 | 2012-08-23 | 2010-08-14 | 2013-02-28 | 79
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 715 | CHILD DEVELOPMENT CENTER ADDITION | 2009-08-21 | 2009-09-28 | LIFECYCLE CONSTRUCTION SERVICES,LLC | 1793 | 1657 | 2009-10-12 | 2011-06-06 | 2010-09-23 | 2011-06-20 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS PENSACOLA FL | 724 | CORRY 'A' SCHOOL BACHELOR ENLISTED QUARTERS | 2010-04-23 | 2010-07-26 | ANDERSON DRACE JOINT VENTURE | 16929 | 19576 | 2010-08-09 | 2013-06-28 | 2012-08-18 | 2013-07-26 | 71
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 726 | REGIMENTAL MAINTENANCE SUPPLY PHASE 3 | 2009-07-30 | 2009-09-30 | HARPER CONSTRUCTION COMPANY, INC | 25237 | 29032 | 2009-10-14 | 2011-10-20 | 2011-03-04 | 2011-10-20 | 96
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 740 | BACHELOR ENLISTED QUARTERS, SAN CLEMENTE | 2009-06-30 | 2009-09-30 | STRONGHOLD ENGINEERING INC | 24053 | 28027 | 2009-10-14 | 2012-08-23 | 2011-08-31 | 2011-11-23 | 97
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 741 | ARRA-COMBINED BACHELOR QUARTERS, SAN CLEMENTE ISLAND | 2010-06-28 | 2010-08-31 | T. B. PENICK & SONS, INC. | 18474 | 17288 | 2010-09-14 | 2012-12-10 | 2012-02-14 | 2012-02-14 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 742 | ARRA-BACHELOR ENLISTED QUARTERS | 2009-06-25 | 2009-09-30 | HENSEL PHELPS CONSTRUCTION CO | 66282 | 68621 | 2009-10-14 | 2012-03-01 | 2011-10-29 | 2012-04-18 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVAL WEAPONS STATION YORKTOWN | 743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | 15431 | 16937 | 2011-06-17 | 2013-05-28 | 2013-02-17 | 2013-05-03 | 92
2013-04-15 | 2009 | Navy - MC Active | Major Construction | IL | ILLINOIS | GREAT LAKES NAVAL STATION | 744 | RTC SPECIAL PROGRAMS BARRACKS | 2006-01-12 | 2008-12-17 | CBZG DESIGN BUILDERS, LLC | 58371 | 53475 | 2008-12-31 | 2010-12-31 | 2010-09-30 | 2010-09-30 | 100 | -4600
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | MAJOR CONSTRUCTIONRUCTIONB HAWAII KANEOHE | 750 | BACHELOR ENLISTED QUARTERS | 2008-10-01 | 2009-08-17 | NAN INC. DBAOCEAN HOUSE BUILDERS | 18768 | 19362 | 2009-08-31 | 2012-03-30 | 2012-02-03 | 2012-03-31 | 97
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 750 | ROTARY HANGAR | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | 64063 | 62194 | 2012-02-14 | 2013-11-06 | 2012-04-16 | 2013-12-10 | 55
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 753 | POOL REPLACEMENT AT NAS NORTH ISLAND | 2009-08-14 | 2009-09-29 | HALBERT CONSTRUCTION | 6820 | 8132 | 2009-10-13 | 2013-11-22 | 2011-02-07 | 2013-11-22 | 46
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 760 | FITNESS CENTER ADDITION, MAYPORT | 2011-01-12 | 2011-05-06 | SAUER, INC. | 27356 | 26133 | 2011-05-20 | 2013-05-14 | 2013-05-14 | 2013-06-07 | 79
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 761 | ARRA-CHILD DEVELOPMENT CENTER | 2009-07-21 | 2009-09-15 | SAUER, INC. | 7803 | 8183 | 2009-09-29 | 2011-03-15 | 2011-03-14 | 2011-03-14 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 777 | WHARF CHARLIE REPLACEMENT | 2010-05-24 | 2010-08-25 | MISENER MARINE CONSTRUCTION, INC. | 26695 | 27927 | 2010-09-08 | 2013-09-01 | 2012-08-24 | 2013-02-12 | 66
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS PENSACOLA FL | 782 | SIMULATOR ADDITION FOR UMFO PROGRAM | 2009-12-18 | 2010-04-27 | KAISERKANE, INC. | 3605 | 3456 | 2010-05-11 | 2012-03-09 | 2011-05-02 | 2011-09-27 | 93
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | FL | FLORIDA | NAS PENSACOLA FL | 791 | HVAC JOINT AVIATION SURVIVAL TRAINING | 2012-07-25 | 2012-09-29 | R L BURNS INC. | 2038 | 1945 | 2012-10-13 | 2013-08-08 | 2013-08-08 | 2013-08-08 | 61
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS PENSACOLA FL | 793 | ARRA-CHILLER PLANT MODIFICATION B3903 & 3291 | 2011-02-09 | 2011-03-29 | ONEIDA TOTAL INTEGRATED ENTERPRISESLLC | 3385 | 3277 | 2011-04-12 | 2012-06-25 | 2012-04-26 | 2012-06-26 | 100
2013-04-15 | 2010 | Navy - MC Active | MFH Improvement | JA | JAPAN | MAJOR CONSTRUCTIONAS IWAKUNI JA | 0801 | WHOLEHOUSE RESTORATION, FAMILY HOUSING MIDRISE # 1200 | 2010-01-14 | 2010-05-18 | NISHIMATSU CONSTRUCTION CO.,LTD | 10324 | 10125 | 2010-06-01 | 2011-10-11 | 2011-10-13 | 2011-10-13 | 100
2013-04-15 | 2010 | Navy - MC Active | MFH Improvement | SP | SPAIN | NAVSTA ROTA SP | 0803 | DUPLEX CONVERSION PH II | 2010-07-08 | 2010-12-28 | UTE CASTELLANO COBRA MATOC | 8348 | 9039 | 2011-01-11 | 2013-05-28 | 2012-04-10 | 2013-04-27 | 97 | -2704
2013-04-15 | 2011 | Navy - MC Active | Major Construction | HI | HAWAII | MAJOR CONSTRUCTIONRUCTIONB HAWAII KANEOHE | 816 | WATERFRONT OPERATIONS FACILITY | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | 16634 | 14368 | 2011-07-14 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 22
2013-04-15 | 2012 | Navy - MC Active | Major Construction | IL | ILLINOIS | GREAT LAKES NAVAL STATION | 816 | DECENTRALIZE STEAM SYSTEM | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | 89491 | 61651 | 2012-06-27 | 2015-11-06 | 2015-11-06 | 2015-11-06 | 8
2013-04-15 | 2012 | Navy - MC Active | Major Construction | HI | HAWAII | MAJOR CONSTRUCTIONRUCTIONB HAWAII KANEOHE | 822 | MAJOR CONSTRUCTIONRUCTIONAS OPERATIONS COMPLEX | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | 52970 | 49973 | 2012-05-02 | 2014-09-02 | 2014-03-17 | 2014-09-02 | 9
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | 1395 | 1254 | 2011-06-28 | 2012-11-07 | 2012-06-18 | 2012-11-07 | 95
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | MAJOR CONSTRUCTIONRUCTIONB HAWAII KANEOHE | 835 | ARRA-CHILD DEVELOPMENT CENTER | 2009-03-17 | 2009-07-31 | AMEC - NAN JOINT VENTURE | 11810 | 10896 | 2009-08-14 | 2011-09-27 | 2011-02-07 | 2011-10-31 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAS OCEANA VA | 837 | C-40 HANGAR | 2009-11-24 | 2010-03-31 | HOURIGAN CONSTRUCTION CORPORATION | 18008 | 18555 | 2010-04-14 | 2012-05-03 | 2012-03-30 | 2012-10-31 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 838 | E-2D FACILITIES UPGRADE | 2010-08-27 | 2010-11-10 | VIRTEXCO CORPORATION | 5434 | 5773 | 2010-11-24 | 2012-12-18 | 2012-01-02 | 2012-12-30 | 93
2013-04-15 | 2010 | Navy - MC Active | Major Construction | HI | HAWAII | MAJOR CONSTRUCTIONRUCTIONB HAWAII KANEOHE | 839 | RANGE, 1000 YARDS, PUULOA | 2010-08-10 | 2010-09-30 | NIKING CORP. | 7464 | 6657 | 2010-10-14 | 2012-02-22 | 2011-08-26 | 2012-02-10 | 100
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 839 | RENOVATE LOWER BASE FIRE STATION | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | 1389 | 1322 | 2012-09-14 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 15
2013-04-15 | 2011 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 843 | CSDS-5 LABORATORY EXPANSION PHASE ! | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | 16042 | 15762 | 2011-06-17 | 2013-06-20 | 2012-10-15 | 2013-02-18 | 67
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CT | CONNECTICUT | NAVSUBASE NEW LONDON CT | 848 | MK-48 TORPEDO MAGAZINE | 2011-01-28 | 2011-03-03 | LAROSA BUILDING GROUP, LLC | 6137 | 4622 | 2011-03-17 | 2012-11-28 | 2013-01-28 | 2013-03-22 | 80
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 851 | NAVAL CONSTRUCTION DIV OPERATIONS CONTROL FAC | 2010-03-10 | 2010-06-22 | NOAH ENTERPRISES AND MID EASTERNBUILDERS INC JV1 | 13184 | 11451 | 2010-07-06 | 2013-04-15 | 2012-07-06 | 2013-04-15 | 86
2013-04-15 | 2011 | Navy - MC Active | Major Construction | HI | HAWAII | MAJOR CONSTRUCTIONRUCTIONB HAWAII KANEOHE | 858 | BACHELOR ENLISTED QUARTERS | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | 62691 | 56456 | 2011-09-14 | 2014-08-21 | 2014-08-21 | 2014-11-27 | 16 | -15440
2013-04-15 | 2012 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 860 | ARMED FORCES RESERVE CENTER, PITTSBURGH | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | 12033 | 11226 | 2012-08-14 | 2014-02-06 | 2014-02-06 | 2014-02-06 | 16
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 862 | PIER 1 UPGRADES TO BERTH USNS COMFORT | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | 3659 | 2944 | 2011-08-09 | 2012-09-18 | 2012-08-09 | 2012-09-28 | 78
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 874 | BUILDING 830 RENOVATION | 2009-05-21 | 2009-09-25 | RICHARD BRADY AND ASSOCIATES INC | 1903 | 1719 | 2009-10-09 | 2010-08-15 | 2010-04-23 | 2010-10-13 | 87
2013-04-15 | 2010 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NSA NORFOLK NAVY SHIPYARD | 878 | AUTOMOTIVE ORGANIZATIONAL SHOP | 2010-01-26 | 2010-05-04 | CLARK ENTERPRISES, INC., J.W. | 1574 | 1511 | 2010-05-18 | 2012-01-30 | 2011-05-14 | 2012-03-12 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 879 | NORFOLK HARBOR CHANNEL DREDGING | 2011-01-05 | 2011-03-24 | NORFOLK DREDGING COMPANY | 24782 | 23844 | 2011-04-07 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 93
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | 56977 | 52657 | 2012-07-17 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 1
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 882 | ENLISTED DINING FACILITY | 2009-04-21 | 2009-07-31 | CLAYCO, INC. | 12168 | 14074 | 2009-08-14 | 2011-08-31 | 2011-04-08 | 2012-01-05 | 84 | -6860
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE CORONADO | 896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY | 2012-12-07 | 2013-02-06 | NEI CONTRACTING AND ENGINEERING INC | 1816 | 1687 | 2013-02-20 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 0
2013-04-15 | 2011 | Navy - MC Active | Major Construction | SP | SPAIN | NAVSTA ROTA SP | 897 | AIR TRAFFIC CONTROL TOWER | 2012-01-13 | 2012-06-15 | SACYR SA | 19080 | 14459 | 2012-06-29 | 2014-09-03 | 2014-09-03 | 2014-09-03 | 14
2013-04-15 | 2010 | Navy - MC Active | Major Construction | SP | SPAIN | NAVSTA ROTA SP | 898 | PROVIDE RECEPTION AIRFIELD FACILITIES | 2010-04-28 | 2010-09-28 | COPCISA SA ELECNOR SA U.T.E. | 12001 | 11535 | 2010-10-12 | 2013-06-28 | 2013-01-25 | 2013-04-15 | 87
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | CA | CALIFORNIA | NAVBASE CORONADO | 899 | STAND ALONE SWITCHGEAR FOR B-1482 | 2009-09-11 | 2009-09-29 | ENGINEERING PARTNERS, INC., THE | 1916 | 1759 | 2009-10-13 | 2010-10-30 | 2010-10-30 | 2010-10-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO | 901 | ARRA-CHILD CARE CENTER 24/7 | 2009-07-30 | 2009-09-29 | HUGO ALONSO INC. | 2262 | 2134 | 2009-10-13 | 2010-12-16 | 2010-10-15 | 2010-11-05 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 908 | BACHELOR ENLISTED QUARTERS | 2008-11-14 | 2009-05-01 | STRAUB MARTIN A JOINT VENTURE | 31267 | 35141 | 2009-05-15 | 2011-09-16 | 2011-03-28 | 2011-08-20 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | BA | BAHRAIN | NAVSUPPACT BAHRAIN | 908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY | 2012-04-12 | 2012-08-09 | NAVY STANDARD DOCUMENT | 41151 | 37986 | 2012-08-23 | 2014-09-11 | 2014-09-11 | 2014-09-11 | 0
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 909 | BACHELOR ENLISTED QUARTERS | 2008-11-14 | 2009-05-01 | STRAUB MARTIN A JOINT VENTURE | 31492 | 35025 | 2009-05-15 | 2011-09-16 | 2011-03-28 | 2011-08-20 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 909 | AIRCRAFT PARKING APRON | 2009-02-20 | 2009-03-19 | URS-IAP LLC | 14194 | 14925 | 2009-04-02 | 2011-04-30 | 2009-09-28 | 2011-04-01 | 99
2013-04-15 | 2011 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | 14315 | 13088 | 2011-06-17 | 2013-06-26 | 2013-06-26 | 2013-07-09 | 96
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 912 | ARRA-CONSTRUCT WATERFRONT STEAM PLANT | 2010-08-20 | 2010-09-30 | KAISERKANE, INC. | 3236 | 3580 | 2010-10-14 | 2011-11-01 | 2011-06-24 | 2011-10-31 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 912 | PAVE EXTERNAL ROADS | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 3107 | 2617 | 2012-04-16 | 2014-06-14 | 2013-12-26 | 2014-02-19 | 38
2013-04-15 | 2012 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 913 | EHW SECURITY FORCE FACILITY | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | 13485 | 11746 | 2012-02-14 | 2013-09-18 | 2013-08-08 | 2013-09-12 | 9
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DJ | DJIBOUTI | CAMP LEMONNIER DJIBOUTI | 916 | INTERIOR PAVED ROADS | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | 15666 | 13853 | 2012-04-16 | 2014-06-14 | 2013-12-26 | 2014-02-19 | 22
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 923 | CHILD DEVELOPMENT CENTER | 2009-01-09 | 2009-06-30 | ARCHER WESTERN CONTRACTORS, LTD | 8885 | 9473 | 2009-07-14 | 2010-11-04 | 2010-09-18 | 2010-09-18 | 96
2013-04-15 | 2010 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 925 | BEQ EOD SCHOOL, PHASE 2 | 2010-02-05 | 2010-07-30 | Awarded by Other Agency | 22769 | 22239 | 2010-08-13 | TBD | TBD | TBD | 98
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONLB BARSTOW CA | 925 | DIP TANK CLEANING FACILITY | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | 7970 | 7503 | 2012-04-04 | 2013-09-27 | 2013-09-27 | 2013-09-27 | 7
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 926 | LIFELONG LEARNING CENTER, PHASE 1 | 2009-07-24 | 2009-09-28 | HALBERT CONSTRUCTION | 8844 | 9755 | 2009-10-12 | 2013-01-11 | 2011-04-06 | 2011-04-06 | 98
2013-04-15 | 2012 | Navy - MC Active | Major Construction | FL | FLORIDA | NAS WHITING FLD MILTON FL | 927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE | 2012-02-17 | 2012-06-07 | Awarded by Other Agency | 18810 | 18878 | 2012-06-21 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 8
2013-04-15 | 2010 | Navy - MC Active | Major Construction | BA | BAHRAIN | NAVSUPPACT BAHRAIN | 928 | WATERFRONT DEVELOPMENT PHASE 2 | 2010-03-19 | 2010-09-28 | NAVY STANDARD DOCUMENT | 33904 | 29337 | 2010-10-12 | 2012-10-24 | 2012-10-24 | 2012-10-24 | 88
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GA | GEORGIA | MAJOR CONSTRUCTIONRUCTIONLB ALBANY GA | 930 | MAJOR CONSTRUCTIONRUCTIONA HARDSTAND, PHASE 1 | 2010-05-28 | 2010-08-18 | HCR/CAPE JV, LLC | 3102 | 3272 | 2010-09-01 | 2012-05-31 | 2011-08-18 | 2013-03-19 | 76
2013-04-15 | 2009 | Navy - MC Active | Major Construction | GA | GEORGIA | MAJOR CONSTRUCTIONRUCTIONLB ALBANY GA | 942 | BACHELOR ENLISTED QUARTERS | 2009-03-17 | 2009-06-03 | SUFFOLK CONSTRUCTION CO INC | 16449 | 15723 | 2009-06-17 | 2011-03-18 | 2010-12-01 | 2011-03-18 | 89
2013-04-15 | 2010 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 952 | INSTALL HVAC SYSTEM AT NOSC AVOCA PA | 2011-01-06 | 2011-02-25 | WU & ASSOCIATES INC | 3191 | 3136 | 2011-03-11 | 2012-08-06 | 2011-12-10 | 2012-10-01 | 95
2013-04-15 | 2011 | Navy - MC Active | Major Construction | BA | BAHRAIN | NAVSUPPACT BAHRAIN | 954 | WATERFRONT DEVELOPMENT, PHASE 3 | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT | 40713 | 35205 | 2012-03-14 | 2014-03-25 | 2014-03-25 | 2014-03-25 | 20
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 974 | ENGINEERING PRODUCT SUPPORT FACILITY | 2008-10-22 | 2009-02-10 | THE HASKELL COMPANY | 16801 | 17571 | 2009-02-24 | 2010-10-22 | 2010-11-22 | 2011-01-23 | 100
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 974 | ARMORY | 2009-10-26 | 2010-01-21 | YORK RIVER ELECTRIC, INC. | 1547 | 1676 | 2010-02-04 | 2010-12-08 | 2010-11-27 | 2010-12-09 | 100
2013-04-15 | 2012 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 985 | WRA VEHICLE BARRIERS | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | 9338 | 7412 | 2012-02-24 | 2013-12-10 | 2013-12-10 | 2013-12-10 | 4
2013-04-15 | 2011 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 987 | EMERGENCY GENERATOR, LIMITED AREA | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | 11275 | 10447 | 2011-06-17 | 2013-06-26 | 2013-06-26 | 2013-07-09 | 73
2013-04-15 | 2012 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | 81714 | 77592 | 2012-05-23 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 47
2013-04-15 | 2012 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONAS CHERRY POINT NC | 991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | 14067 | 13097 | 2012-03-29 | 2013-12-02 | 2013-08-14 | 2013-12-02 | 36
2013-04-15 | 2010 | Navy - MC Active | Minor Construction | VA | VIRGINIA | NSA NORFOLK NAVY SHIPYARD | 992 | COMMISSARY UTILITIES | 2010-06-29 | 2010-08-27 | CLARK ENTERPRISES, INC., J.W. | 1117 | 1163 | 2010-09-10 | 2012-10-29 | 2011-05-09 | 2012-10-29 | 92
2013-04-15 | 2009 | Navy - MC Active | Minor Construction | JA | JAPAN | COMFLEACT YOKOSUKA JA | 997 | SSN 21/774 SUPPORT AT CFAY BERTH 13 | 2009-06-23 | 2009-08-28 | PENTA-OCEAN DREDGING CO.,LTD. | 1288 | 1460 | 2009-09-11 | TBD | 2010-03-26 | 2010-03-26 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | FL | FLORIDA | NAVSTA MAYPORT FL | 999 | ALPHA WHARF IMPROVEMENTS | 2009-03-23 | 2009-05-18 | MISENER MARINE CONSTRUCTION, INC. | 13606 | 13199 | 2009-06-01 | 2011-12-05 | 2011-05-18 | 2011-11-23 | 100
2013-04-15 | 2010 | Navy - MC Active | MFH Improvement | DC | DISTRICT OF COLUMBIA | MARBKS WASHINGTON DC | 1001 | WHOLE HOUSE REVITAL'N TO "HOME OF THE COMMANDANTS" | 2010-03-18 | 2010-06-17 | G-W MANAGEMENT SERVICES, LLC | 3599 | 4140 | 2010-07-01 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 100
2013-04-15 | 2012 | Navy - MC Active | MFH Improvement | JA | JAPAN | MAJOR CONSTRUCTIONAS IWAKUNI JA | 1001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | 11335 | 10765 | 2012-08-14 | 2014-12-20 | 2014-12-20 | 2014-12-20 | 0
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 1003 | MILITARY WORKING DOG RELOCATION, APRA HARBOR | 2010-06-10 | 2010-09-29 | PACIFIC WEST BUILDERS | 11792 | 9083 | 2010-10-13 | 2013-07-31 | 2012-09-28 | 2012-09-28 | 38
2013-04-15 | 2010 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 1006 | DEFENSE ACCESS ROAD IMPROVEMENTS | 2010-04-02 | 2010-12-03 | Department of Transportation, Federal Highway Administration | 8608 | 661 | 2010-12-17 | N/A | N/A | N/A | 4
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1008 | BACHELOR ENLISTED QUARTERS, BASIC RECON COURSE | 2009-02-02 | 2009-08-14 | TURNER-PENICK | 54551 | 38771 | 2009-08-28 | 2012-12-06 | 2011-08-22 | 2012-12-06 | 64
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1011 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON | 2009-04-01 | 2009-06-18 | ARCHER WESTERN/RQ JOINT VENTURE | 28702 | 36258 | 2009-07-02 | 2013-04-15 | 2011-08-19 | 2013-02-06 | 100 | -2570
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1012 | ANGLICO OPERATIONS COMPLEX | 2010-06-29 | 2010-09-28 | WEBCOR/ RA BURCH A JV | 26348 | 23505 | 2010-10-12 | 2014-01-31 | 2013-01-25 | 2013-06-14 | 89
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1014 | TRUCK COMPANY OPERATIONS COMPLEX | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | 52425 | 49648 | 2011-10-06 | 2014-03-07 | 2013-09-21 | 2013-10-06 | 15
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1016 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON | 2009-04-01 | 2009-06-18 | ARCHER WESTERN/RQ JOINT VENTURE | 17949 | 22843 | 2009-07-02 | 2013-04-15 | 2011-08-19 | 2013-02-06 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1016 | RECONNAISANCE BN OPERATIONS COMPLEX | 2010-06-29 | 2010-09-28 | WEBCOR/ RA BURCH A JV | 81206 | 74013 | 2010-10-12 | 2014-01-31 | 2013-01-25 | 2013-06-14 | 91
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1017 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK | 2009-04-01 | 2009-06-18 | ARCHER WESTERN/RQ JOINT VENTURE | 21937 | 31644 | 2009-07-02 | 2013-04-15 | 2011-08-19 | 2013-02-06 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1019 | COMM/ELEC MAINTENANCE FACILITIES | 2010-07-30 | 2010-09-23 | RQ CONSTRUCTION, LLC | 12911 | 12612 | 2010-10-07 | 2013-01-31 | 2012-04-02 | 2012-11-05 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1029 | WFTBN SUPPORT FACILITIES, EDSON RANGE | 2010-05-17 | 2010-08-17 | BILBRO CONSTRUCTION COMPANY | 16282 | 14454 | 2010-08-31 | 2012-07-25 | 2012-03-09 | 2012-06-22 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1033 | ENLISTED DINING FACILITY, EDSON RANGE | 2010-05-28 | 2010-09-10 | WHITING-TURNER CONTRACTING CO | 38259 | 34873 | 2010-09-24 | 2013-06-06 | 2012-09-24 | 2013-04-30 | 94
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1034 | 2ND INTEL BN OPERATIONS COMPLEX | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | 79767 | 76337 | 2011-07-13 | 2014-06-01 | 2014-02-28 | 2014-03-27 | 20
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE | 2011-07-28 | 2012-03-23 | BARNHART-BALFOUR BEATTY, INC. | 11746 | 9457 | 2012-04-06 | 2013-06-10 | 2013-01-21 | 2013-05-21 | 49
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1040 | INTERSECTION BRIDGE AND IMPROVEMENTS | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | 11432 | 10838 | 2012-09-07 | 2013-09-27 | 2013-09-27 | 2013-09-27 | 14
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1041 | EXPANSION OF SRTTP TO 7.5 MGD | 2010-07-29 | 2010-09-28 | CDM-FILANC JV | 51114 | 43848 | 2010-10-12 | 2014-04-08 | 2012-10-12 | 2014-02-05 | 70
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1043 | NORTH REGION TERITARY TREATMENT PLANT INC 1 OF 2 | 2010-07-29 | 2010-09-28 | CDM-FILANC JV | 117679 | 92960 | 2010-10-12 | 2014-04-08 | 2012-10-12 | 2014-02-05 | 38
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1044 | CONVEYANCE/WATER TREATMENT | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | 98236 | 81523 | 2012-10-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 3
2013-04-15 | 2012 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1045 | NEW POTABLE WATER CONVEYANCE | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | 85242 | 60764 | 2012-10-12 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1047 | BACHELOR ENLISTED QUARTERS, HADNOT POINT | 2009-04-01 | 2009-06-18 | ARCHER WESTERN/RQ JOINT VENTURE | 25273 | 37427 | 2009-07-02 | 2013-04-15 | 2011-08-19 | 2013-02-06 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1048 | GAS/ELECTRICAL UPGRADES | 2011-07-14 | 2011-09-28 | RQ-BERG JV | 49713 | 39429 | 2011-10-12 | 2013-11-06 | 2014-01-15 | 2014-01-15 | 38
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1067 | BACHELOR ENLISTED QUARTERS, LAS FLORES | 2010-06-29 | 2010-09-28 | WEBCOR/ RA BURCH A JV | 41375 | 37657 | 2010-10-12 | 2014-01-31 | 2013-01-25 | 2013-06-14 | 96
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1069 | RECRUIT BARRACKS, EDSON RANGE | 2010-04-20 | 2010-09-21 | HARPER CONSTRUCTION COMPANY, INC | 48523 | 44308 | 2010-10-05 | 2013-02-28 | 2012-10-16 | 2012-12-14 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1084 | ENLISTED DINING FACILITY | 2010-05-28 | 2010-09-10 | WHITING-TURNER CONTRACTING CO | 32421 | 29720 | 2010-09-24 | 2013-06-06 | 2012-09-24 | 2013-04-30 | 92
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1086 | RECRUIT BARRACKS, FIELD/K-SPAN | 2010-04-06 | 2010-09-07 | T. B. PENICK & SONS, INC. | 20164 | 18701 | 2010-09-21 | 2013-07-01 | 2012-09-30 | 2013-01-10 | 66
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1093 | COMMUNICATIONS UPGRADES | 2010-06-30 | 2010-09-28 | URS GROUP, INC. | 71427 | 69499 | 2010-10-12 | 2014-01-28 | 2012-10-21 | 2014-02-21 | 85
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1094 | ELECTRICAL DISTRIBUTION SYSTEM | 2010-06-30 | 2010-09-28 | URS GROUP, INC. | 73986 | 65966 | 2010-10-12 | 2014-01-28 | 2012-10-21 | 2014-02-21 | 64
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1100 | WOUNDED WARRIOR BATTALION HEADQUARTERS | 2009-08-07 | 2009-09-30 | BARNHART-BALFOUR BEATTY, INC. | 9452 | 8861 | 2009-10-14 | 2011-10-15 | 2011-10-15 | 2011-10-15 | 100
2013-04-15 | 2011 | Navy - MC Active | MFH Improvement | DC | DISTRICT OF COLUMBIA | MARBKS WASHINGTON DC | 1101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | 41 | 39 | 2011-01-28 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 100
2013-04-15 | 2011 | Navy - MC Active | MFH Improvement | JA | JAPAN | COMFLEACT YOKOSUKA JA | 1101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | 17378 | 16915 | 2011-07-15 | 2013-01-17 | 2012-12-03 | 2013-01-20 | 90
2013-04-15 | 2011 | Navy - MC Active | MFH Improvement | JA | JAPAN | NMAJOR CONSTRUCTION EAD DET SASEBO | 1102 | WHOLEHOUSE IMPROVEMENT | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | 8127 | 6990 | 2011-07-10 | 2013-01-18 | 2012-10-17 | 2013-02-14 | 95
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1104 | BACHELOR ENLISTED QUARTERS, HADNOT POINT | 2009-04-01 | 2009-06-18 | ARCHER WESTERN/RQ JOINT VENTURE | 27044 | 39261 | 2009-07-02 | 2013-04-15 | 2011-08-19 | 2013-02-06 | 100 | -3875
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1109 | BACHELOR ENLISTED QUARTERS, LAS FLORES | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | 36173 | 33967 | 2011-10-13 | 2014-03-27 | 2013-10-13 | 2013-12-26 | 36
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1112 | BACHELOR ENLISTED QUARTERS, 22 AREA | 2009-07-13 | 2009-09-22 | HARPER CONSTRUCTION COMPANY, INC | 44838 | 44756 | 2009-10-06 | 2012-03-05 | 2011-06-06 | 2012-03-05 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1113 | CHILD DEVELOPMENT CENTER, HADNOT POINT | 2009-07-10 | 2009-09-11 | SHIEL SEXTON COMPANY, INC. | 7725 | 10254 | 2009-09-25 | 2012-04-03 | 2011-07-27 | 2012-12-09 | 90
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1113 | BACHELOR ENLISTED QUARTERS, 24 AREA | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | 41889 | 39106 | 2011-10-13 | 2014-03-27 | 2013-10-13 | 2013-12-26 | 31
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1114 | BACHELOR ENLISTED QUARTERS, 33 AREA | 2009-07-15 | 2009-09-25 | HARPER CONSTRUCTION COMPANY, INC | 29198 | 29747 | 2009-10-09 | 2011-08-19 | 2011-03-19 | 2011-08-19 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1115 | BACHELOR ENLISTED QUARTERS, LAS PULGAS AREA | 2008-12-24 | 2009-07-27 | TURNER-PENICK | 15046 | 13588 | 2009-08-10 | 2011-08-04 | 2011-08-04 | 2011-08-04 | 97
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1116 | BACHELOR ENLISTED QUARTERS, 62 AREA | 2009-02-02 | 2009-08-14 | TURNER-PENICK | 24989 | 24557 | 2009-08-28 | 2012-12-06 | 2011-08-22 | 2012-12-06 | 97
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1136 | MODIFICATIONS OF K-RANGES PHASE 2 | 2010-07-23 | 2010-09-27 | VIRTEXCO CORPORATION | 14049 | 14032 | 2010-10-11 | 2013-03-30 | 2012-04-19 | 2013-04-12 | 97
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1142 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY | 2009-04-01 | 2009-06-18 | ARCHER WESTERN/RQ JOINT VENTURE | 27557 | 37059 | 2009-07-02 | 2013-04-15 | 2011-08-19 | 2013-02-06 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1160 | PHYSICAL FITNESS CENTER | 2009-08-27 | 2010-03-23 | SUFFOLK CONSTRUCTION CO INC | 22908 | 21695 | 2010-04-06 | 2013-05-10 | 2012-01-27 | 2013-05-10 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1188 | MARSOC CHILD DEVELOPMENT CENTER | 2009-07-08 | 2009-08-27 | IKHANA-CHOATE-1 LLC | 8512 | 9579 | 2009-09-10 | 2011-12-21 | 2011-06-28 | 2012-01-08 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1193 | BACHELOR ENLISTED QUARTERS, HADNOT POINT | 2009-04-01 | 2009-06-18 | ARCHER WESTERN/RQ JOINT VENTURE | 24778 | 34444 | 2009-07-02 | 2013-04-15 | 2011-08-19 | 2013-02-06 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1194 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 24810 | 31704 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 85
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1195 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 25300 | 31956 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 86
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1196 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 25300 | 32055 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 77
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1197 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 24047 | 28924 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 73
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1200 | MARINE CORPS ENERGY INITIATIVE | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | 9779 | 9162 | 2011-08-09 | 2013-05-07 | 2012-08-04 | 2012-08-04 | 97
2013-04-15 | 2012 | Navy - MC Active | MFH Improvement | JA | JAPAN | COMFLEACT YOKOSUKA JA | 1201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | 19730 | 18737 | 2012-08-01 | 2014-01-13 | 2014-01-13 | 2014-01-13 | 3
2013-04-15 | 2012 | Navy - MC Active | MFH Improvement | JA | JAPAN | NAF ATSUGI JA | 1201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | 5990 | 5533 | 2012-10-10 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 0
2013-04-15 | 2012 | Navy - MC Active | MFH Improvement | JA | JAPAN | COMFLEACT YOKOSUKA JA | 1202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | 9033 | 8379 | 2012-08-22 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 0
2013-04-15 | 2012 | Navy - MC Active | MFH Improvement | JA | JAPAN | NAF ATSUGI JA | 1202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | 17540 | 14942 | 2012-08-29 | 2014-02-10 | 2013-12-09 | 2014-02-10 | 0
2013-04-15 | 2010 | Navy - MC Active | MFH Improvement | GQ | GUAM | COMNAVMARIANAS GUAM | 1210 | INSTALL WINDOW SHUTTERS, 146 UNITS AT NEW APRA | 2010-04-15 | 2010-04-22 | SERRANO CONSTRUCTION ANDDEVELOPMENT CORPORATION | 1005 | 977 | 2010-05-06 | 2011-01-03 | 2010-11-19 | 2011-01-12 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1212 | MESS HALL, HADNOT POINT 400 AREA | 2009-04-21 | 2009-07-31 | CLAYCO, INC. | 10862 | 11675 | 2009-08-14 | 2011-08-31 | 2011-04-08 | 2012-01-05 | 97
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1233 | MAINTENANCE/OPERATIONS COMPLEX | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 29621 | 25827 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 70 | -20100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | 32625 | 28937 | 2011-07-13 | 2014-06-01 | 2014-02-28 | 2014-03-27 | 55
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | 6613 | 5895 | 2011-07-11 | 2013-04-30 | 2012-08-20 | 2013-03-03 | 86
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1247 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 22509 | 17094 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 74
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | 43950 | 39447 | 2011-07-13 | 2013-12-14 | 2013-07-13 | 2013-12-14 | 65
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | 40236 | 37775 | 2011-09-14 | 2013-10-08 | 2013-10-08 | 2013-10-08 | 56
2013-04-15 | 2012 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | 74707 | 68315 | 2012-05-14 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 12
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | 39788 | 37741 | 2011-09-14 | 2013-10-08 | 2013-10-08 | 2013-10-08 | 62
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1256 | MESS HALL ADDITION, COURTHOUSE BAY | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | 1499 | 1391 | 2011-06-16 | 2012-11-25 | 2012-11-25 | 2012-11-25 | 98
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1264 | UTILITY EXPANSION, HADNOT POINT | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | 55206 | 52477 | 2011-10-10 | 2014-07-26 | 2013-10-22 | 2013-12-26 | 65
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1265 | UTILITY EXPANSION, FRENCH CREEK | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | 54795 | 40002 | 2011-10-10 | 2014-07-26 | 2013-10-22 | 2013-12-26 | 46
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1266 | UTILITY EXPANSION COURTHOUSE BAY | 2011-03-30 | 2011-05-19 | WALBRIDGE ALDINGER COMPANY, INC. | 30983 | 28881 | 2011-06-02 | 2014-01-21 | 2013-06-30 | 2014-01-26 | 76
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1267 | MESS HALL, FRENCH CREEK | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | 24316 | 17182 | 2011-06-16 | 2013-06-01 | 2013-02-06 | 2013-03-23 | 75
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1268 | SOI EAST FACILITIES, CAMP GEIGER | 2010-03-19 | 2010-08-16 | DCK NORTH AMERICA, LLC | 33644 | 43741 | 2010-08-30 | 2014-10-24 | 2013-04-10 | 2014-10-21 | 53
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1269 | FIELD TRAINING FACILITY, DEVIL DOG SOI | 2010-04-02 | 2010-08-24 | ARCHER WESTERN CONTRACTORS, LTD | 35465 | 29336 | 2010-09-07 | 2013-05-27 | 2012-12-05 | 2013-06-13 | 87
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | 54720 | 52197 | 2011-09-13 | 2014-03-07 | 2013-09-07 | 2013-09-07 | 49
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1297 | 4TH INFANTRY BATTALION OPS COMPLEX | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 31109 | 26885 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 68 | -20878
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1298 | ROAD NETWORK, WALLACE CREEK | 2009-09-15 | 2010-02-25 | WHITING-TURNER CONTRACTING CO | 10943 | 13334 | 2010-03-11 | 2013-10-03 | 2012-10-27 | 2013-10-03 | 46
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1304 | MP WORKING DOG KENNEL RELOCATION | 2010-08-17 | 2010-09-01 | THR ENTERPRISES, INC. | 6073 | 5593 | 2010-09-15 | 2013-02-08 | 2012-03-09 | 2012-10-22 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1310 | PRE-TRIAL DETAINEE FACILITY | 2010-02-02 | 2010-08-26 | TEAM ENVIRO JOINT VENTURE II | 16332 | 15859 | 2010-09-09 | 2012-09-18 | 2012-03-18 | 2013-02-08 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1311 | CONSOLIDATED INFOTECH/TELCOM COMPLEX | 2010-12-16 | 2011-03-04 | DANIELS & DANIELS GRUNLEYJOINT VENTURE | 35011 | 32243 | 2011-03-18 | 2013-10-08 | 2014-07-01 | 2014-07-01 | 83
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | 43568 | 41020 | 2011-06-16 | 2013-10-14 | 2013-08-30 | 2013-10-14 | 66
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | 46005 | 42196 | 2011-06-16 | 2013-06-28 | 2013-08-13 | 2013-09-27 | 80
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | 49005 | 43945 | 2011-07-13 | 2013-12-14 | 2013-07-13 | 2013-12-14 | 18
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1323 | ARMORY II MEF, WALLACE CREEK | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | 5941 | 5202 | 2011-12-20 | 2013-12-14 | 2013-07-13 | 2013-12-14 | 20
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1330 | WOUNDED WARRIOR BATTALION HEADQUARTERS | 2009-07-10 | 2009-09-23 | VIRTEXCO CORPORATION | 3060 | 3517 | 2009-10-07 | 2013-02-08 | 2011-10-30 | 2013-03-15 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1357 | ARRA-CHILD DEVELOPMENT CENTER | 2010-08-24 | 2010-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | 8201 | 8576 | 2010-10-12 | 2013-03-14 | 2012-01-21 | 2012-11-02 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1378 | MARINE RESOURCE AND RECOVERY CENTER | 2009-07-10 | 2009-09-23 | VIRTEXCO CORPORATION | 16106 | 17942 | 2009-10-07 | 2013-02-08 | 2011-10-30 | 2013-03-15 | 92
2013-04-15 | 2010 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1382 | NEW BASE ENTRY POINT AND ROAD PHASE 1 | 2011-11-08 | 2010-07-12 | SKANSKA USA CIVIL SOUTHEAST INC | 64692 | 66707 | 2010-07-26 | 2014-02-19 | 2013-01-10 | 2013-12-26 | 68
2013-04-15 | 2012 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1383 | BASE ENTRY POINT AND ROAD | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | 64235 | 51193 | 2012-04-17 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 17
2013-04-15 | 2011 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 1400 | MARINE CORPS ENERGY INITIATIVE | 2010-10-08 | 2011-05-31 | URS-IAP LLC | 8868 | 8186 | 2011-06-14 | 2012-12-06 | 2012-09-27 | 2012-12-31 | 98
2013-04-15 | 2010 | Navy - MC Active | MFH Improvement | GQ | GUAM | COMNAVMARIANAS GUAM | 1411 | INSTALL WINDOW SHUTTERS PH III AND IV , LOCKWOOD TERRACE | 2009-11-13 | 2010-03-17 | GPPC, INC. | 1810 | 1669 | 2010-03-31 | 2010-10-28 | 2010-08-24 | 2010-08-24 | 100
2013-04-15 | 2012 | Navy - MC Active | Minor Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONB CAMP LEJEUNE NC | 1425 | OVERHEAD RANGE BAFFLE SYSTEM | 2012-12-17 | 2013-02-13 | MILITARY & FEDERAL CONSTRUCTION CO, INC. | 2297 | 2167 | 2013-02-27 | TBD | TBD | TBD | 1
2013-04-15 | 2009 | Navy - MC Active | MFH Improvement | JA | JAPAN | NMAJOR CONSTRUCTION EAD DET SASEBO | 1502 | W/H REVITALIZATION - SAKURA TOWER (68 APTS) | 2009-02-01 | 2009-07-27 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | 10935 | 10415 | 2009-08-10 | 2011-10-11 | 2011-10-08 | 2011-10-08 | 100
2013-04-15 | 2009 | Navy - MC Active | MFH Improvement | JA | JAPAN | NMAJOR CONSTRUCTION EAD DET SASEBO | 1602 | W/H IMPROV'T-HARIO VILLAGE & MAIN BASE TOWNHOMES | 2009-04-23 | 2009-08-26 | TOA CORPORATION | 31969 | 30794 | 2009-09-09 | 2013-06-20 | 2012-10-07 | 2013-06-20 | 93
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 001V | CRYSTAL PARK 5 MOVE TO ARLINGTON SERVICE CENT | 2010-04-16 | 2010-09-17 | HITT CONTRACTING, INC | 49600 | 70640 | 2010-10-01 | 2012-01-13 | 2011-08-01 | 2012-07-09 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 003A | NAVY SYSTEMS MGMT ACTIVITY RELOCATION INC 2 | 2009-07-06 | 2009-09-30 | ATLANTIC CONTINGENCY CONSTRUCTION,LLC | 71699 | 72534 | 2009-10-14 | 2011-09-28 | 2011-06-30 | 2011-09-28 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 003V | NAVY SYSTEMS MANAGEMENT ACTIVITY RELOCATION | 2009-07-06 | 2009-09-30 | ATLANTIC CONTINGENCY CONSTRUCTION,LLC | 14963 | 15390 | 2009-10-14 | 2011-09-28 | 2011-06-30 | 2011-09-28 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 006V | NAVY SYSTEMS MANAGEMENT ACTIVITY WAREHOUSE | 2009-07-06 | 2009-09-30 | ATLANTIC CONTINGENCY CONSTRUCTION,LLC | 6783 | 6456 | 2009-10-14 | 2011-09-28 | 2011-06-30 | 2011-09-28 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 012A | COLLOCATE MILDEP INVESTIG AGENCIES INC 2 OF 2 | 2008-02-20 | 2008-07-30 | HENSEL PHELPS CONSTRUCTION CO. | 207745 | 210718 | 2008-08-13 | 2010-12-23 | 2010-12-01 | 2010-12-23 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | ME | MAINE | NAS BRUNSWICK ME | 028V | MARINE CORPS RESERVE CENTER | 2010-02-15 | 2010-07-23 | NUTMEG COMPANIES, INC., THE | 9314 | 9684 | 2010-08-06 | 2011-10-14 | 2011-07-28 | 2011-11-23 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 103M | ARRA-REPAIR BACHELOR ENLISTED QUARTERS | 2009-05-19 | 2009-06-29 | ALDERMAN BUILDING CO., INC. | 3310 | 3501 | 2009-07-13 | 2011-03-14 | 2010-09-22 | 2011-03-14 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 1043A | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | 29295 | 25338 | 2010-11-12 | 2014-04-08 | 2012-10-12 | 2014-02-05 | 0
2013-04-15 | 2009 | Navy - MC Active | Major Construction | RI | RHODE ISLAND | NAVAL STATION NEWPORT RI | 112V | MARITIME SUBSURFACE SENSOR OPS FACILITY | 2008-12-17 | 2009-05-08 | H.V. COLLINS COMPANY | 13320 | 12984 | 2009-05-22 | 2011-05-01 | 2010-11-29 | 2011-05-01 | 97
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NSA NORTH POTOMAC | 149V | CRYSTAL PARK 5 TO ARLINGTON SERVICE CENTER | 2010-04-16 | 2010-09-17 | HITT CONTRACTING, INC | 7275 | 10016 | 2010-10-01 | 2012-01-13 | 2011-08-01 | 2012-07-09 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAIRENGSTA LAKEHURST | 150A | HELICOPTER HGRS & MAG HQ (MAJOR CONSTRUCTIONRUCTIONGUIRE AFB) 2 OF 2 | 2008-04-24 | 2008-08-06 | BORO DEVELOPERS INC | 41481 | 41564 | 2008-08-20 | 2010-10-30 | 2010-10-30 | 2011-10-30 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAIRENGSTA LAKEHURST | 151A | FLEET LOGS OPS FAC (MAJOR CONSTRUCTIONRUCTIONGUIRE AFB) INC 2 OF 2 | 2008-04-22 | 2008-08-26 | C-PYRAMID ENTERPRISES INC | 28177 | 35396 | 2008-09-09 | 2012-02-09 | 2010-09-15 | 2012-02-09 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAIRENGSTA LAKEHURST | 156V | C-130 FLIGHT SIMULATOR FACILITY (MAJOR CONSTRUCTIONRUCTIONGUIRE AFB) | 2008-04-22 | 2008-08-26 | C-PYRAMID ENTERPRISES INC | 4016 | 4235 | 2008-09-09 | 2012-02-09 | 2010-09-15 | 2012-02-09 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAIRENGSTA LAKEHURST | 157V | MUNITIONS MAINTENANCE SHOP (MAJOR CONSTRUCTIONRUCTIONGUIRE AFB) | 2009-08-05 | 2009-09-22 | INTERCONTINENTAL CNSTR CONTG | 1669 | 1237 | 2009-10-06 | 2010-11-30 | 2010-10-06 | 2012-02-03 | 98
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 159A | OPERATION ACCESS POINTS | 2011-07-29 | 2011-09-14 | REYES CONSTRUCTION INC | 13347 | 11592 | 2011-09-28 | 2013-10-07 | 2013-10-07 | 2013-10-07 | 13
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAIRENGSTA LAKEHURST | 161V | AVIATION SUPT FAC HANGAR RENOV (MAJOR CONSTRUCTIONRUCTIONGUIRE AFB) | 2009-06-30 | 2009-09-17 | MAGNUM INC | 11056 | 12310 | 2009-10-01 | 2011-09-06 | 2011-03-08 | 2011-08-28 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NJ | NEW JERSEY | NAVAIRENGSTA LAKEHURST | 162V | AIMD OPS FAC/AVIATION SUP DEPOT (MAJOR CONSTRUCTIONRUCTIONGUIRE AFB) | 2009-05-13 | 2009-08-21 | ARCHER WESTERN CONTRACTORS, LTD | 25457 | 24941 | 2009-09-04 | 2011-03-11 | 2011-03-05 | 2011-09-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND WA | 169A | HANGAR 5 RECAPITALIZATION INC 2 OF 2 | 2006-09-15 | 2008-12-08 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | 28595 | 28042 | 2008-12-22 | 2010-07-09 | 2010-06-30 | 2010-06-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 176V | HRSC CONSOLIDATION | 2009-07-13 | 2009-09-11 | STRAUB CONSTRUCTION, INC. | 18719 | 20478 | 2009-09-25 | 2011-08-01 | 2011-02-19 | 2011-07-01 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 183V | WNY-A-12 BRAC RELOCATION TO BLDG 183 | 2010-08-16 | 2010-11-29 | ALLEN AND SHARIFF CORP | 7517 | 8778 | 2010-12-13 | 2012-04-10 | 2011-08-30 | 2011-08-30 | 98
2013-04-15 | 2011 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 204A | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | 21579 | 15245 | 2012-12-12 | 2014-06-19 | 2014-06-19 | 2014-06-19 | 1
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSUPPACT HAMPTON ROADS VA | 208A | JOINT REGIONAL CORRECTIONAL FAC INC 2 OF 2 | 2009-02-06 | 2009-08-21 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | 42521 | 42506 | 2009-09-04 | 2011-06-15 | 2011-05-01 | 2011-06-15 | 94
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSUPPACT HAMPTON ROADS VA | 208V | JOINT REGIONAL CORRECTIONAL FAC INC 1 OF 2 | 2009-02-06 | 2009-08-21 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | 30499 | 29624 | 2009-09-04 | 2011-06-15 | 2011-05-01 | 2011-06-15 | 98
2013-04-15 | 2009 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 212V | BUILDING 9 RENOVATION | 2009-07-22 | 2009-08-26 | DTC ENGINEERS AND CONSTRUCTORS LLC | 20571 | 21208 | 2009-09-09 | 2011-05-31 | 2011-03-11 | 2011-04-25 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 220V | WNY-220, PEO-EIS PMW 200 & 240 BRAC TO BLDG 220 | 2010-08-18 | 2010-11-29 | ARRIBA CORPORATION | 7580 | 8473 | 2010-12-13 | 2013-01-09 | 2011-08-30 | 2012-10-24 | 87
2013-04-15 | 2010 | Navy - MC Active | Major Construction | VA | VIRGINIA | JNTEXPBASE LITTLE CREEK FS VA | 221V | BUILDING 1558 RENOVATIONS FOR SPAWAR | 2010-04-23 | 2010-07-26 | NOAH ENTERPRISES, INC. | 2081 | 1801 | 2010-08-09 | 2011-08-19 | 2011-07-18 | 2011-10-07 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | NAVSTA NORFOLK VA | 223V | RENOVATE V47 FOR COMBAT CRAFT FACILITY | 2008-11-21 | 2009-09-23 | COAKLEY & WILLIAMS CONSTR CO | 11081 | 11446 | 2009-10-07 | 2011-07-14 | 2010-11-25 | 2011-07-14 | 96
2013-04-15 | 2009 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 234V | MAJOR CONSTRUCTIONRUCTIONRC MOUNDVILLE TO NMAJOR CONSTRUCTIONRUCTIONRC PITTSBURGH | 2009-07-31 | 2009-09-30 | EAGLE DESIGN INC | 2010 | 1929 | 2009-10-14 | 2010-11-15 | 2010-10-15 | 2011-01-15 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | NAVAL SUPPORT ACTY CHASN | 300V | CONSOLIDATED BRIG ADDITION | 2009-09-08 | 2009-12-18 | HUNT CONSTRUCTION GROUP, INC. | 8647 | 8445 | 2010-01-01 | 2011-05-04 | 2011-05-04 | 2011-05-04 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | SC | SOUTH CAROLINA | NAVAL SUPPORT ACTY CHASN | 301V | SPAWAR DATA CENTER | 2009-11-25 | 2010-05-05 | SUFFOLK CONSTRUCTION CO INC | 10694 | 10333 | 2010-05-19 | 2011-07-28 | 2011-06-06 | 2011-07-28 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | ME | MAINE | NSS PORTSMOUTH NAVY SHIPYARD | 327V | SPECIAL PURPOSE BN OPERATIONS FACILITY | 2010-02-16 | 2010-05-11 | ENVIRONMENTAL CHEMICAL CORPORATIONDBA ECC REMEDIATION SERVICES | 5587 | 4578 | 2010-05-25 | 2011-06-10 | 2011-05-26 | 2011-06-10 | 89
2013-04-15 | 2009 | Navy - MC Active | Major Construction | DC | DISTRICT OF COLUMBIA | NAVAL SUPPORT ACTIVITY WASH | 339B | NATIONAL MARITIME INTEL CENTER INC 3 OF 3 | 2007-02-15 | 2010-04-01 | HENSEL PHELPS CONSTRUCTION CO. | 12439 | 12144 | 2010-04-15 | 2010-08-08 | 2010-08-08 | 2010-08-08 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 356A | CVN MAINTENANCE PIER REPLACEMENT INC 2 OF 2 | 2007-11-07 | 2010-01-25 | NOVA GROUP/TUTOR-SALIBAA JOINT VENTURE | 72353 | 61407 | 2010-02-08 | 2012-01-10 | 2012-01-05 | 2012-01-26 | 90
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 438M | ARRA-REPAIR BACHELOR ENLISTED QUARTERS | 2009-04-24 | 2009-06-18 | BARNHART-BALFOUR BEATTY, INC. | 7643 | 8195 | 2009-07-02 | 2010-04-15 | 2010-03-01 | 2010-04-22 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | AZ | ARIZONA | MAJOR CONSTRUCTIONRUCTIONAS YUMA AZ | 447A | AIRCRAFT MAINTENANCE HANGAR (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | 30492 | 28017 | 2011-06-23 | 2012-12-07 | 2012-10-08 | 2012-12-31 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | VA | VIRGINIA | MARINE CORPS BASE QUANTICO VA | 495A | AIRCRAFT PARKING APRON - GREEN SIDE | 2008-12-19 | 2009-05-07 | ARCHER WESTERN CONTRACTORS, LTD | 17752 | 18364 | 2009-05-21 | 2012-01-04 | 2011-03-07 | 2012-01-04 | 99 | -11720
2013-04-15 | 2009 | Navy - MC Active | Major Construction | GQ | GUAM | NAVBASE GUAM | 502A | KILO WHARF EXTENSION INC 2 OF 2 | 2007-10-05 | 2008-11-12 | IBC/TOA CORPORATION | 50909 | 47935 | 2008-11-26 | 2010-10-15 | 2010-03-31 | 2010-05-18 | 85
2013-04-15 | 2010 | Navy - MC Reserves | Major Construction | LA | LOUISIANA | NSA NEW ORLEANS LA | 506V | FLAG HOUSING - QUARTERS A | 2010-11-29 | 2011-01-20 | AMERICAN CONTRACTOR AND TECHNOLOGY | 1814 | 1794 | 2011-02-03 | 2011-09-26 | 2011-08-18 | 2011-10-13 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | VA | VIRGINIA | NSA NORFOLK NAVY SHIPYARD | 516A | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | 68459 | 56664 | 2011-04-14 | 2015-06-07 | 2014-11-22 | 2015-06-09 | 31
2013-04-15 | 2009 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 587A | SUB DRIVE-IN MSF, BECKONING POINT INC 2 OF 3 | 2008-01-10 | 2009-01-15 | WATTS-HEALY TIBBITTS A JV | 41088 | 38988 | 2009-01-29 | 2010-12-30 | 2010-10-10 | 2010-10-10 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | HI | HAWAII | JBPHH PEARL HARBOR HI | 587B | SUB DRIVE-IN MSF, BECKONING POINT INC 3 OF 3 | 2008-01-10 | 2010-01-13 | WATTS-HEALY TIBBITTS A JV | 8155 | 6978 | 2010-01-27 | 2010-12-30 | 2010-10-10 | 2010-10-10 | 100
2013-04-15 | 2010 | Navy - MC Reserves | Major Construction | IL | ILLINOIS | GREAT LAKES NAVAL STATION | 630V | ARMED FORCES RESERVE CENTER | 2009-10-23 | 2010-02-26 | BETTER BUILT + CLARK LLC | 12660 | 12608 | 2010-03-12 | 2011-09-15 | 2011-06-08 | 2011-08-17 | 99
2013-04-15 | 2010 | Navy - MC Active | Minor Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONB CAMP LEJEUNE NC | 678X | AIR TRAFFIC CONTROL TOWER EXTENSION | 2010-07-14 | 2010-09-27 | F & S MECHANICAL AND PLUMBINGSERVICES, INC. | 2013 | 2213 | 2010-10-11 | 2013-12-30 | 2013-09-30 | 2013-12-29 | 75
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 704V | RENOVATE FACILITIES - ORDNANCE AREA | 2009-01-20 | 2009-03-12 | BARNHART-BALFOUR BEATTY, INC. | 9270 | 8770 | 2009-03-26 | 2010-05-21 | 2010-05-23 | 2010-05-23 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 712V | ORDNANCE STORAGE FACILITIES | 2009-05-06 | 2009-05-28 | SOLTEK PACIFIC CONSTRUCTION CO | 8585 | 8248 | 2009-06-11 | 2010-09-08 | 2010-09-08 | 2010-09-08 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 719V | WEAPONS AND ARMAMENT FACILITY | 2008-12-22 | 2009-03-10 | SOLTEK PACIFIC CONSTRUCTION CO | 29568 | 28586 | 2009-03-24 | 2010-12-11 | 2010-12-12 | 2010-12-12 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 777V | WEAPONS DYNAMICS RDT&E CENTER | 2009-10-22 | 2010-02-08 | VANDER WERFF, PETER CONSTRUCTION | 4893 | 4723 | 2010-02-22 | 2010-12-15 | 2010-10-06 | 2010-12-15 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 780V | CONSTRUCT ORDNANCE STORAGE FACILITIES #2 | 2009-05-06 | 2009-05-28 | SOLTEK PACIFIC CONSTRUCTION CO | 12838 | 12088 | 2009-06-11 | 2010-09-08 | 2010-09-08 | 2010-09-08 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAS MIRAMAR | 790V | REGIONAL CONFINEMENT FACILITY | 2009-06-30 | 2009-09-04 | CLARK CONSTRUCTION GROUP-CALIFORNIALP | 31872 | 30944 | 2009-09-18 | 2011-03-01 | 2011-02-28 | 2011-12-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONB CAMP PENDLETON CA | 856M | ARRA-PHOTOVOLTAIC SYSTEM | 2009-08-14 | 2009-12-03 | SYNERGY ELECTRIC COMPANY INC | 9853 | 10374 | 2009-12-17 | 2011-01-21 | 2010-12-17 | 2011-01-21 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | NC | NORTH CAROLINA | MAJOR CONSTRUCTIONRUCTIONB CAMP LEJEUNE NC | 857M | ARRA-FACILITY AND PHOTOVOLTAIC ENERGY UPGRADES | 2009-06-10 | 2009-06-29 | QUALITY ROOFERS & GUTTERING | 12844 | 13523 | 2009-07-13 | 2011-04-13 | 2010-12-21 | 2011-03-31 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | NAWS CHINA LAKE | 908F | F-35 EDWARDS RAMP EXTENSION (EDWARDS AFB) | 2009-06-01 | 2010-02-03 | NAVY STANDARD DOCUMENT | 1983 | 1944 | 2010-02-17 | 2010-06-01 | 2010-06-01 | 2010-06-01 | 100
2013-04-15 | 2010 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONLB BARSTOW CA | 947V | INDUSTRIAL MACHINE SHOP FACILITY | 2009-09-21 | 2010-03-18 | HENSEL PHELPS CONSTRUCTION CO | 6718 | 6286 | 2010-04-01 | 2010-12-15 | 2010-12-27 | 2010-12-27 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | PA | PENNSYLVANIA | NAVSUPPACT MECHANICSBURG PA | 948V | RADAR MAINTENANCE FACILITY (TOBYHANNA) | 2009-12-05 | 2010-03-01 | Awarded by Other Agency | 7128 | 6853 | 2010-03-15 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 99
2013-04-15 | 2009 | Navy - MC Active | Major Construction | CA | CALIFORNIA | MAJOR CONSTRUCTIONRUCTIONAGCC TWENTYNINE PALMS CA | 971B | COMBINED ARMS MOUT, PHASE 2 | 2009-03-03 | 2009-07-02 | SOLTEK PACIFIC CONSTRUCTION CO | 19891 | 20954 | 2009-07-16 | 2012-10-31 | 2010-07-01 | 2012-10-30 | 100
2013-04-15 | 2009 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 973D | LIMITED AREA PRODUCTION/STRG CMPLX INC 5 OF 7 | 2006-11-20 | 2008-12-01 | KIEWIT-GENERAL, A JOINT VENTURE | 50700 | 50700 | 2008-12-15 | 2012-06-01 | 2011-11-08 | 2011-11-19 | 99
2013-04-15 | 2010 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 973E | LIMITED AREA PRODUCTION/STRG CMPLX INC 6 OF 7 | 2006-11-20 | 2010-01-04 | KIEWIT-GENERAL, A JOINT VENTURE | 91449 | 87292 | 2010-01-18 | 2012-06-01 | 2011-11-08 | 2011-11-19 | 100
2013-04-15 | 2011 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 973F | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | 20026 | 13520 | 2010-11-24 | 2012-06-01 | 2011-11-08 | 2011-11-19 | 15
2013-04-15 | 2010 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 977A | ENCLAVE FENCING/PARKING | 2010-06-18 | 2010-09-30 | WATTS-GRANITE A JV | 69877 | 36525 | 2010-10-14 | 2013-05-29 | 2012-11-28 | 2013-05-10 | 59
2013-04-15 | 2013 | Navy - MC Active | Major Construction | WA | WASHINGTON | NAVAL BASE KITSAP BREMERTON WA | 990A | EXPLOSIVES HANDLING WHARF #2 INC 2 OF 4 | 2011-12-13 | 2012-10-31 | EHW CONSTRUCTORS, A JOINT VENTURE | 280041 | 205636 | 2012-11-14 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 0
2013-04-15 | 2011 | Navy - MC Active | MFH Construction | CU | CUBA | NAVSTA GUANTANAMO BAY | H106 | REPLACE BASE HOUSING | 2011-03-16 | 2011-09-30 | LAKESHORE TOLTEST JV, LLC | 35175 | 34347 | 2011-10-14 | 2014-03-16 | 2014-03-16 | 2014-04-02 | 28
2013-04-15 | 2010 | Navy - MC Active | MFH Construction | KR | KOREA | FLEET ACTIVITIES CHINHAE KS | H115 | CONSTRUCT FH WELCOME CENTER , WAREHOUSE, SELF-HELP | 2010-01-06 | 2010-08-12 | TIME ENGINEERING & CONSTRUCTIONCO.,LTD | 3576 | 3261 | 2010-08-26 | 2013-05-17 | 2012-10-30 | 2013-05-17 | 78
2013-04-15 | 2009 | Navy - MC Active | MFH Construction | CU | CUBA | NAVSTA GUANTANAMO BAY | H541 | REPLACE GRANADILLO CIRCLE HOUSING | 2009-12-11 | 2009-09-30 | BRDC, A JOINT VENTURE | 16600 | 15026 | 2009-10-14 | 2013-05-31 | 2012-11-29 | 2013-03-24 | 85
2013-04-15 | 2009 | Navy - MC Active | MFH Construction | CU | CUBA | NAVSTA GUANTANAMO BAY | H543 | REPLACE GRANADILLO POINT HOUSING | 2009-12-11 | 2009-09-30 | BRDC, A JOINT VENTURE | 22275 | 21413 | 2009-10-14 | 2013-05-31 | 2012-11-29 | 2013-03-24 | 72
2013-04-15 | 2009 | Navy - MC Active | MFH Construction | CU | CUBA | NAVSTA GUANTANAMO BAY | H544 | REPLACE BARGO HOUSING | 2009-12-11 | 2009-09-30 | BRDC, A JOINT VENTURE | 19983 | 20312 | 2009-10-14 | 2013-05-31 | 2012-11-29 | 2013-03-24 | 77
2013-04-15 | 2010 | Navy - MC Active | MFH Construction | GQ | GUAM | COMNAVMARIANAS GUAM | H952 | REPLACEMENT, 30 UNITS AT NORTH TIPALAO, PH3 | 2010-02-15 | 2010-06-16 | FED-CON A JV | 16587 | 16279 | 2010-06-30 | 2013-08-02 | 2011-10-09 | 2012-01-05 | 65
2013-04-15 | 2008 | DODEA | Major Construction | GM | GERMANY | WIESBADEN GERMANY | WHS00902J | HH ARNOLD HS, CONSTRUCT GYM, ART & MUSIC + RENOVATIONS | 2008-03-15 | 2009-06-10 | Federal Republic of Germany | 15735 | 17059 | 2009-06-29 | 2013-05-15 | 2012-05-04 | 2013-05-15 | 90
2013-04-15 | 2010 | DoDEA | Major Construction | GA | GEORGIA | FORT STEWART | AM 856 07 | NEW ELEMENTARY SCHOOL | 2011-02-25 | 2011-06-03 | Sauer, Inc | 22494 | 19957 | 2012-08-01 | 2014-03-29 | 2013-12-14 | 2013-12-29 | 25 |  | Third award protest recently denied.
2013-04-15 | 2010 | DoDEA | Major Construction | GM | GERMANY | RAMSTEIN AB | EUR 8197 02 | MULTI-PURPOSE ROOM, BUS AREA & SPORTS FIELDS (KAISERSLAUTERN COMPLEX) | 2010-07-15 | 2010-09-23 | Peter Gross | 16993 | 18476 | 2011-03-30 | 2013-09-05 | 2013-09-05 | 2013-09-05 | 90
2013-04-15 | 2010 | DoDEA | Major Construction | GM | GERMANY | USAG WIESBADEN | EUR 8198 03 | CAFETERIA & KITCHEN (HH ARNOLD (WEISBADEN) HS) | 2010-04-15 | 2010-05-18 | Hessisches Baumanagement Wiesbaden | 5379 | 6113 | 2010-09-20 | 2013-04-29 | 2013-03-04 | 2013-03-04 | 100
2013-04-15 | 2010 | DoDEA | Major Construction | GM | GERMANY | USAG STUTTGART | EUR 8320 03 | REPLACE SCHOOL (BOBLINGEN ES) | 2010-03-18 | 2010-03-18 | Staatliches Hochbauamt Reutlingen | 47837 | 47920 | 2011-12-20 | 2015-07-01 | 2015-06-01 | 2015-06-01 | 6
2013-04-15 | 2010 | DoDEA | Major Construction | BE | BELGIUM | USAG BENELUX | EUR 8318 09 | REPLACE SCHOOL (SHAPE ES) | 2011-07-07 | 2011-12-09 | Besix SA | 35444 | 33375 | 2012-01-18 | 2014-06-18 | 2014-04-19 | 2014-04-19 | 32
2013-04-15 | 2011 | DoDEA | Major Construction | NY | NEW YORK | WEST POINT MILRES | AM2455205 | CONSTRUCT ADDITION AND RENOVATE MS | 2011-07-18 | 2011-10-20 | Bernard Associates | 26679 | 26679 | 2011-11-28 | 2014-11-01 | 2014-09-28 | 2014-11-25 | 62 |  | Phased BOD dates
2013-04-15 | 2011 | DoDEA | Major Construction | BE | BELGIUM | USAG BENELUX | D9124-1 | REPLACE SCHOOLS (SHAPE MS/HS) | 2011-07-07 | 2011-12-09 | Besix SA | 29628 | 26291 | 2012-01-18 | 2014-06-25 | 2014-04-17 | 2014-04-17 | 42 |  | Recently awarded. Project includes a high school portion that has not been funded yet. Will track as a separate line item after award.
2013-04-15 | 2011 | DoDEA | Major Construction | NC | NORTH CAROLINA | CAMP LEJEUNE | AM2455207 | REPLACE SCHOOL (ADDITION TO TARAWA TERRACE II) | 2011-04-21 | 2011-08-09 | Kisaq-RQ | 16103 | 16103 | 2011-08-09 | 2013-04-02 | 2012-10-28 | 2013-03-26 | 99 |  | Design-Build Contract
2013-04-15 | 2011 | DoDEA | Major Construction | NC | NORTH CAROLINA | FORT BUCHANAN | AM8193 01 | REPLACE ELEMENTARY SCHOOL (ANTILLES ES) | 2012-03-16 | 2012-06-12 | Gilbane Building Company | 50968 | 50975 | 2012-07-18 | 2014-04-19 | 2014-04-19 | 2014-04-19 | 8 |  | Design-Build Contract
2013-04-15 | 2011 | DoDEA | Major Construction | VA | VIRGINIA | MAJOR CONSTRUCTIONRUCTIONB QUANTICO | AM2455206 | REPLACE/CONSOLIDATE ELEMENTARY SCHOOLS | 2012-06-29 | 2012-09-28 | Homeland Contracting Corp. | 47260 | 47260 | 2012-09-28 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 6
2013-04-15 | 2011 | DoDEA | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | AM100801 | REPLACE ELEMENTARY SCHOOL (MURRAY ES) | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | 14851 | 14887 | 2012-09-12 | 2014-06-02 | 2014-12-01 | 2014-04-03 | 20
2013-04-15 | 2011 | DoDEA | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | AMD02051 | REPLACE ELEMENTARY SCHOOL ( MAJOR CONSTRUCTIONRUCTIONNAIR ES) | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | 16413 | 16449 | 2012-09-12 | 2014-06-02 | 2014-12-01 | 2014-04-03 | 20 |  | Combined with Murray ES- AM100801
2013-04-15 | 2012 | DODEA | Major Construction | JA | JAPAN | YOKOTA AIR BASE | PA00019 | OTH PA00019 REPLACE TEMP CLASSROOM BLDG, JK MENDEL ES, YOKOTA AB | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | 9644 | 9644 | 2013-03-26 | 2015-10-18 | 2015-07-25 | 2015-07-25 | 0
2013-04-15 | 2012 | DoDEA | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | AM00022 | REPLACE FACILITY (DSO) | 2012-09-15 | 2012-08-22 | Guerrero Builders, LLC | 3226 | 3195 | 2012-10-02 | 2014-02-14 | 2013-10-02 | 2013-11-01 | 7
2013-04-15 | 2008 | NSA | Major Construction | UK | UNITED KINGDOM | MHS | 17309 (MWHL08003) | BUILDING 45 EXTENSION | 2008-06-19 | 2008-09-05 | AFCEE/ECC Corporation FA8903-06-D-8511 0043 | 26731 | 30336 | 2009-06-01 | 2011-11-09 | 2010-08-15 | 2013-06-14 | 100 | 180 | Funds diverted will be used for Power Availability and Infrastructure Improvements
2013-04-15 | 2008 | NSA | Major Construction | UK | UNITED KINGDOM | MHS | 17312 (MWHL08-3002) | POWER AVAILABILITY AND INFRASTRUCTURE IMPROVEMENTS | 2009-09-14 | 2009-12-22 | Balfour Beatty Engieneering Services (Haden Young) | 10180 | 10179 | 2010-01-25 | N/A | 2011-06-15 | 2013-05-31 | 100 |  | AFCEE returned Additional Funds rom PAII back to Building 1045 Extension.
2013-04-15 | 2009 | NSA | Major Construction | MD | MARYLAND | NSAW | 21120 | SOUTH CAMPUS ELECTRICAL UTILITY PLANT-SCEUP (PHASE 1) | 2010-05-03 | 2010-08-30 | Clark/ Major Constructionruction Dean | 18550 | 18550 | 2010-09-21 | N/A | 2014-04-18 | 2013-01-17 | 99 |  | AFCEE returned Additional Funds rom PAII back to Building 1045 Extension.
2013-04-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17872 | SOUTH CAMPUS ELECTRICAL UTILITY PLANT -SCEUP (PHASE 2) | 2010-05-03 | 2010-08-30 | Clark/ Major Constructionruction Dean | 138400 | 138091 | 2010-09-21 | N/A | 2014-04-18 | 2014-05-13 | 56 | 37500 | The funds diverted in this project have not been assigned to other project at the present time.
2013-04-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 21372 | NSAW VEHICLE ENTRANCE BARRIER (VCP-6) | 2009-05-04 | 2010-08-26 | Goels/Grunley | 4443 | 4544 | 2010-09-09 | N/A | 2011-09-26 | 2012-06-29 | 100 |  | The construction cost is $4,443,532.86, which $4,393,532.86 is for construction and $50,000 is for escorts.
2013-04-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 25047 | NSAW VEHICLE ENTRANCE BARRIER (VCP-2) | 2012-10-17 | 2013-02-19 | District Veterans Contracting | 5253 | 6206 | 2013-05-15 | 2014-01-21 | 2014-02-19 | 2014-02-19 | 0
2013-04-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17781 | TORDELLA CHILLED WATER BACKUP STORAGE | 2009-08-24 | 2010-06-24 | Nothern Tiaga Venture,LLC Inc. (NTVI) | 11700 | 11700 | 2010-06-30 | N/A | 2011-08-20 | 2012-05-30 | 100
2013-04-15 | 2010 | NSA | Major Construction | MD | MARYLAND | NSAW | 17782 | R&E CHILLED WATER BACKUP STORAGE | 2011-05-31 | 2011-08-30 | Walsh Construction Company | 3200 | 3200 | 2011-11-07 | N/A | 2013-07-13 | 2013-07-13 | 30 |  | The projects have different Projects Number but one MILCON funding line.
2013-04-15 | 2008 | NSA | Major Construction | UK | UNITED KINGDOM | MHS | 18052 (MWHL10-3001) | POWER & COOLING INFRASTRUCTURE UPGRADE |  | 2011-03-15 | NPGL | 37588 | 37588 | 2011-03-31 |  | 2013-02-01 | 2014-04-01 | 80
2013-04-15 | 2008 | NSA | Major Construction | UK | UNITED KINGDOM | MHS | 18053 (MWHL10-3001) | POWER & COOLING INFRASTRUCTURE UPGRADE |  | 2012-02-15 | IUS | 37588 | 37588 | 2012-01-31 |  | 2013-02-01 | 2014-05-31 | 44
2013-04-15 | 2010 | NSA | Major Construction | UK | UNITED KINGDOM | MHS | 18054 (MWHL10-3001) | POWER & COOLING INFRASTRUCTURE UPGRADE |  | 2012-08-12 | Balfour Beaty Engineering Services | 37588 | 37588 | 2012-11-30 |  | 2013-02-01 | 2014-08-31 | 35 |  | NEDL - Offsite work. IUS - Onsite. Power and Cooling Infrastructure Upgrade includes the Power Upgrade OFF Base, Power Upgrade On Base, Power DSS AA&BB, Power Water Borehole and Power UPS and Cooling
2013-04-15 | 2011 | NSA | Major Construction | MD | MARYLAND | NSAW | 17866 | NORTH CAMPUS ELECTRICAL UTILITY PLANT (NCEUP) | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | 125900 | 125900 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-01-16 | 55 | 50100 | The project was recently awarded. Pending for the Notice to Proceed (NTP). Funds diverted used to support Mountainview project.
2013-04-15 | 2011 | NSA | Major Construction | GA | GEORGIA | BACKHALL CAMPUS/SWEET TEA ANNEX | 20489 | MOD II | 2011-12-23 | 2012-04-13 | Brantley Co. | 9636 | 10206 | 2012-05-30 | 2013-05-31 | 2014-01-30 | 2013-06-21 | 60
2013-04-15 | 2012 | NSA | Major Construction | GA | GEORGIA | WHITELAW | 23994 | WHITELAW WEDGE | 2012-04-26 | 2012-06-18 | JAAAT | 17117 | 17705 | 2012-07-18 | 2014-01-09 | 2014-01-30 | 2014-02-28 | 31
2013-04-15 | 2012 | NSAC | Major Construction | CO | COLORADO | ADFC | 23051 | MOUNTAINVIEW | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | 116975 | 116975 | 2012-11-02 | 2015-05-28 | 2015-05-03 | 2015-05-03 | 2
2013-04-15 | 2012 | NSA | Major Construction | MD | MARYLAND | NSAW | 24649 | HIGH PERFORMANCE COMPUTING CENTER 2 | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | 564689000 | 564689000 | 2013-03-12 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 1
2013-04-15 | 2013 | NSA | Major Construction | UT | UTAH | CAMP WILLIAMS | 21078 | BUMBLEHIVE / IC CNCI DATA CENTER 1 | 2009-12-18 | 2010-09-24 | Balfour Beatty/DPR/Big-D, A Joint Venture (BDB) | 1201370 | 1090919 | 2010-11-08 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 89 |  | The Utah Data Center Project is a fully authorized project in the amount of $1,529,500,000.00 which is incrementally funded over the following FY's: FY09- $109,500,000 FY10-$600,000,000 FY11-$397.562,000 FY12-$246,401,000 FY13-$176,037,000 The United States Army Corps of Engineers (USACE) is the construction agent for the NSA. The major contract for the project which is to design and construct the data center was awarded to Balfour Beatty/DPR/Big-D, A Joint Venture (BDB) in the amount of $1,198,950,000. There have been several contracts that have supplemented and supported the main construction effort for the UDC project which include, but are not limited to, the following: - Early Earthwork - $49,422,999 - Substation - $23,269,749 - Military Installation Development Authority (MIDA) - $70,000,000 - USACE Supervision & Administration/Supervision, Inspection & Overhead (S&A/SIOH) - $77,037,086 Note: The exact current obligation amount is $837,927,788 Original Contract Amount: $1,201,369,992
2013-04-15 | 2008 | SOCOM | Major Construction | QA | QATAR | AL UDEID | 61772 | OPERATIONS COMPLEX | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 16751 | 16751 | 2012-01-31 | 2014-02-22 | 2013-04-24 | 2014-02-22 | 20 | 4071
2013-04-15 | 2008 | SOCOM | Major Construction | QA | QATAR | AL UDEID | AFSOC033003 | VEHICLE MAINTENANCE FACILITY | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 4575 | 4575 | 2012-01-31 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 24 | 2071
2013-04-15 | 2008 | SOCOM | Major Construction | QA | QATAR | AL UDEID | AFSOC033005 | STORAGE FACILITY | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 3603 | 3603 | 2012-01-31 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 24 | 1386
2013-04-15 | 2008 | SOCOM | Major Construction | QA | QATAR | AL UDEID | AFSOC033019 | AIR OPERATIONS CENTER | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | 2931 | 2931 | 2012-01-31 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 24 | -2023
2013-04-15 | 2008 | SOCOM | Major Construction | QA | QATAR | AL UDEID | ALUA073010 | LOGISTICS STORAGE WAREHOUSE | 2009-02-13 | 2009-09-01 01:00 | IAP Worldwide Services, Inc | 6639 | 6745 | 2009-11-12 | 2012-11-15 | 2011-02-05 | 2012-11-12 | 85 | 652
2013-04-15 | 2008 | SOCOM | Major Construction | FL | FLORIDA | MACDILL AFB | NVZR53712A | SOF 501D BUILDING ADDITION PHASE II (PARKING GARAGE), MACDILL AFB, FL | 2008-05-16 | 2012-09-27 | RUSH RORE, Joint Venture | 1015 | 1015 | 2012-12-03 | 2013-07-01 | 2013-03-11 | 2013-05-01 | 27
2013-04-15 | 2009 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 26542 | EXPAND TRAINING COMPOUND | 2009-01-09 | 2009-09-10 01:00 | Heery International, Inc. | 11823 | 12745 | 2009-10-15 | 2012-03-13 | 2011-07-02 | 2012-09-30 | 99 | 671
2013-04-15 | 2009 | SOCOM | Major Construction | WA | WASHINGTON | FT LEWIS | 50347 | RANGER BATTALION COMPLEX | 2009-04-20 | 2009-08-13 01:00 | Korte Construction Company | 24176 | 25423 | 2009-09-23 | 2011-03-17 | 2011-05-16 | 2011-03-24 | 99 | -11240
2013-04-15 | 2009 | SOCOM | Major Construction | FL | FLORIDA | MACDILL AFB | NVZR063711 | ADD / ALTER 501B (HQ SOCOM) | 2010-10-28 | 2011-03-30 | Carothers Construction, Inc. | 7186 | 7176 | 2011-05-09 | 2013-02-13 | 2012-09-20 | 2013-02-13 | 83 | -1881
2013-04-15 | 2010 | SOCOM | Major Construction | KY | KENTUCKY | FT CAMPBELL | 50349 | BATTALION OPERATIONS COMPLEX | 2009-11-09 | 2010-04-09 01:00 | ACC Construction Company, Incorporated | 20800 | 22409 | 2010-04-26 | 2012-05-18 | 2012-02-25 | 2012-05-14 | 99 | -6717
2013-04-15 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 60833 | SPECIAL OPS PREP & CONDITIONING COURSE | 2010-05-17 | 2010-09-29 01:00 | Caddell Construction CO., INC | 15072 | 15081 | 2010-11-30 | 2012-11-30 | 2012-08-31 | 2012-11-24 | 99 | -2512
2013-04-15 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 61874 | BATTALION & COMPANY HEADQUARTERS | 2009-11-13 | 2010-09-30 01:00 | Windamir Development, Inc | 9327 | 11049 | 2010-11-02 | 2013-07-15 | 2012-03-16 | 2013-06-04 | 81 | -3685
2013-04-15 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 64669 | OPERATIONS SUPPORT ADDITION | 2010-03-29 | 2010-09-30 01:00 | Sauer, Inc. | 6662 | 7490 | 2010-10-22 | 2013-03-08 | 2012-04-14 | 2012-09-11 | 98 | -5316
2013-04-15 | 2010 | SOCOM | Major Construction | WA | WASHINGTON | FT LEWIS | 65446 | SUPPORT COMPANY FACILITY | 2010-04-09 | 2010-09-22 01:00 | Vet Industrial, Inc. | 10947 | 11474 | 2011-01-05 | 2012-12-03 | 2012-10-04 | 2012-10-04 | 99 | -2813
2013-04-15 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 66227 | BATTALION HEADQUARTERS FACILITY | 2010-07-01 | 2010-09-25 01:00 | Caddell Construction CO., INC | 11713 | 12301 | 2010-11-09 | 2013-08-06 | 2012-12-31 | 2013-04-08 | 98 | 1200
2013-04-15 | 2010 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 66315 | OPERATIONS ADDITION NORTH | 2010-04-27 | 2010-08-05 01:00 | Sauer, Inc. | 18649 | 19361 | 2010-08-25 | 2013-10-28 | 2013-02-10 | 2013-07-30 | 80 | -3617
2013-04-15 | 2010 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063019 | FUEL CELL HANGAR (MAJOR CONSTRUCTIONRUCTION-130) | 2009-09-24 | 2010-04-09 01:00 | Hensel Phelps Construction Co. | 32766 | 34363 | 2010-05-11 | 2012-12-24 | 2012-02-26 | 2012-12-24 | 99 | 955
2013-04-15 | 2010 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063035 | AMU ADDITION (CV-22) | 2010-08-10 | 2010-10-25 01:00 | A4 Construction Company, Inc. | 9530 | 12714 | 2010-12-16 | 2013-04-24 | 2012-08-07 | 2013-04-24 | 97 | 330
2013-04-15 | 2010 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ073015 | AC-130 MUNITIONS LOADOUT APR PH 1 (INSERT) | 2010-08-20 | 2010-09-30 01:00 | Nick Griego & Son's Construction, Inc. | 6196 | 10918 | 2010-11-03 | 2012-10-10 | 2011-10-29 | 2012-10-08 | 99 | 877
2013-04-15 | 2010 | SOCOM | Major Construction | VA | VIRGINIA | NAB LITTLE CREEK | P-773 | SUPPORT ACTIVITY OPERATIONS FACILITY | 2010-07-06 | 2011-02-28 | Virtexco | 8960 | 8960 | 2011-03-15 | 2013-01-30 | 2012-02-05 | 2013-02-07 | 90 | -4998
2013-04-15 | 2010 | SOCOM | Major Construction | CA | CALIFORNIA | NAB CORONADO | P-781 | CLOSE QUARTERS COMBAT FACILITY | 2010-08-17 | 2011-09-30 | Barnhart Balfour Beatty Inc. | 13684 | 13684 | 2011-10-15 | 2013-05-30 | 2013-04-22 | 2013-04-22 | 50 | 98
2013-04-15 | 2011 | SOCOM | Major Construction | AZ | ARIZONA | YUMA | 62070 | MILITARY FREE FALL SIMULATOR | 2011-04-11 | 2012-06-21 | Pilkington Commercial Co., Inc. | 10030 | 10030 | 2012-07-02 | 2014-05-06 | 2013-12-30 | 2014-01-05 | 59 | 1982
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 64484 | OPERATIONS ADDITIONS | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | 13388 | 13751 | 2011-08-25 | 2014-08-14 | 2014-06-10 | 2014-06-10 | 37 | -32
2013-04-15 | 2011 | SOCOM | Major Construction | KY | KENTUCKY | FT CAMPBELL | 64989 | BATTALION OPERATIONS COMPLEX | 2010-11-16 | 2011-07-06 | Korte Construction Company | 21572 | 23412 | 2011-08-05 | 2013-07-24 | 2013-06-05 | 2013-05-29 | 94 | -12144
2013-04-15 | 2011 | SOCOM | Major Construction | GA | GEORGIA | FT BENNING | 65395 | COMPANY SUPPORT FACILITY | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | 15392 | 15392 | 2011-12-27 | 2013-09-16 | 2013-06-12 | 2013-07-18 | 59 | -1214
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 66362 | C4 FACILITY - JSOC | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | 41446 | 42879 | 2012-06-14 | 2014-09-24 | 2014-06-26 | 2014-06-26 | 20 | 8643
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 66443 | OPERATIONS SUPPORT FACILITY | 2010-12-23 | 2011-06-20 | SFL+A Architects, AP | 9591 | 10135 | 2011-07-19 | 2013-10-02 | 2012-09-18 | 2013-05-31 | 85 | -27
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 66444 | OPERATIONAL COMMUNICATIONS FACILITY - JCU | 2011-02-18 | 2011-08-10 | Pacific Tech Sauer J.V. | 9674 | 9830 | 2011-09-14 | 2013-10-21 | 2012-12-26 | 2013-04-24 | 77 | 738
2013-04-15 | 2011 | SOCOM | Major Construction | GA | GEORGIA | FT BENNING | 69261 | MWD KENNEL COMPLEX | 2010-12-17 | 2011-09-30 | Komada, LLC | 3103.928 | 3227 | 2012-01-09 | 2013-05-09 | 2013-02-09 | 2013-03-07 | 92 | -7
2013-04-15 | 2011 | SOCOM | Major Construction | CO | COLORADO | FT CARSON | 69278 | TUAV HANGAR | 2011-07-07 | 2012-04-06 | Iron Mike Construction LLC | 3506 | 3506 | 2012-05-16 | 2013-10-08 | 2013-08-09 | 2013-08-09 | 52 | 497
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 69573 | ADMIN/COMPANY OPERATIONS | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | 8487 | 9166 | 2011-10-27 | 2013-11-21 | 2013-04-18 | 2013-08-26 | 66 | -21
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 76511 | JOINT INTELLIGENCE BRIGADE | 2011-05-12 | 2011-09-30 | Archer Western Contractors | 28900 | 29658 |  | 2014-01-03 | 2013-05-11 | 2013-07-07 | 87 | 1257
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 78253 | ELECTRONIC EQUIPMENT LAB | 2011-09-19 | 2011-09-30 | Kiewit Federal Services | 1411 | 1785 | 2011-09-30 | 2012-11-02 | 2012-09-29 | 2012-12-27 | 94
2013-04-15 | 2011 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 78497 | SOLSE MOTOR POOL ADDITION | 2011-08-24 | 2011-09-29 | Military and Federal Construction Co., Inc. | 1725 | 1767 | 2011-10-20 | 2013-01-31 | 2012-10-19 | 2013-01-29 | 99
2013-04-15 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063049 | HANGAR / AMU (MAJOR CONSTRUCTIONRUCTION-130J) | 2011-05-13 | 2011-09-09 | Speegle Construction | 19432 | 19976 | 2011-10-11 | 2014-02-05 | 2013-10-30 | 2014-01-22 | 64 | -2049
2013-04-15 | 2011 | SOCOM | Minor Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063051 | AIRCRAFT PARKING APRON | 2011-02-23 | 2011-08-03 | Sundt Corporation | 23744 | 24820 | 2011-10-05 | 2012-10-12 | 2012-11-03 | 2012-12-07 | 99 | -1023
2013-04-15 | 2011 | SOCOM | Minor Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063052A | OPERATIONS & TRAINING COMPLEX (3RD UAS) | 2011-04-15 | 2011-10-26 | Speegle Construction | 13614 | 16814 | 2012-09-06 | 2014-04-28 | 2013-07-17 | 2014-03-28 | 43 | -7211
2013-04-15 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063052B | OPERATIONS & TRAINING COMPLEX (130 SOS SQ OPS) | 2011-04-15 | 2011-10-26 | KL House | 13260 | 16558 | 2012-01-10 | 2013-06-15 | 2013-01-13 | 2013-05-16 | 95
2013-04-15 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063054A | C-130 PARKING APRON (RECAP), PHASE 1 | 2011-02-23 | 2011-08-03 | Sundt Corporation | 16206.9 | 16206.9 | 2011-10-05 | 2012-11-03 | 2012-11-03 | 2012-12-24 | 99 | -2048
2013-04-15 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ063054B | C-130 PARKING APRON (RECAP), PHASE 1 | 2011-02-23 | 2011-08-03 | Hensel Phelps Construction Co. | 3213 | 3235 | 2011-10-05 | 2012-12-04 | 2012-10-04 | 2012-12-24 | 99
2013-04-15 | 2011 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ073012 | ADAL SIMULATOR FACILITY FOR MAJOR CONSTRUCTIONRUCTION-130 (RECAP) | 2011-05-26 | 2011-08-25 | PACE Pacific Corporation | 8868 | 9067 | 2011-11-03 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 97 | -27
2013-04-15 | 2011 | SOCOM | Major Construction | FL | FLORIDA | HURLBURT FIELD | FTEV063000 | SQUAD OPS ANNEX 4 SOS (1UMAJOR CONSTRUCTION) | 2011-03-28 | 2011-06-23 | DWG & Associates, Inc. | 1629 | 1629 | 2011-09-22 | 2012-11-20 | 2012-11-17 | 2013-02-18 | 97
2013-04-15 | 2011 | SOCOM | Major Construction | HI | HAWAII | PEARL HARBOR | P-462 | NSWG3 COMMAND & OPS FACILITY | 2011-01-19 | 2011-06-16 | dkc/TtEC, LLC | 17886 | 17886 | 2011-07-01 | 2013-02-28 | 2013-01-07 | 2013-03-08 | 99 | -8046
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 60272 | COMMUNICATIONS TRAINING COMPLEX (SWCS) | 2012-04-11 | 2012-07-24 | GSC Construction Inc. |  | 8290 |  | 2014-04-05 | 2013-08-23 | 2014-03-06 | 7
2013-04-15 | 2012 | SOCOM | Minor Construction | NC | NORTH CAROLINA | FT BRAGG | 60821 | SQUADRON HEADQUARTERS ADDITION | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | 10605 | 10641 | 2012-06-06 | 2014-08-05 | 2013-12-09 | 2013-12-09 | 20 | 1397
2013-04-15 | 2012 | SOCOM | Major Construction | KY | KENTUCKY | FT CAMPBELL | 66598 | ROTARY WING HANGAR | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | 34350 | 34572 | 2012-04-16 | 2014-04-16 | 2014-02-28 | 2014-03-09 | 19
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 69277 | ENTRY CONTROL POINT | 2012-04-24 | 2012-07-30 | Lifecyle Construction Services, LLC | 2196 | 2214 |  | 2013-11-20 | 2014-02-27 | 2013-08-22 | 33 | 401
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 69458 | BATTALION OPERATIONS COMPLEX | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors |  | 16772 |  | 2014-10-01 |  | 2014-06-03 | 4 | 864
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 69758 | BRIGADE HEADQUARTERS | 2012-05-09 | 2012-09-17 | JAAAT Technical Services |  | 16429 |  | 2014-11-22 |  | 2014-07-25 | 1
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 71224 | GROUP HEADQUARTERS | 2012-06-06 | 2012-09-25 | Engineering Design Technologies |  | 18526 |  | 2014-08-29 | 2014-06-20 | 2014-06-20 | 5
2013-04-15 | 2012 | SOCOM | Major Construction | WA | WASHINGTON | FT LEWIS | 76363 | COMPANY OPERATIONS FACILITY | 2012-04-18 | 2012-08-30 | Adept - Absher 1 Joint Venture | 18751 | 18820 |  | 2014-05-31 |  | 2014-04-01 | 9 | 155
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 76364 | BATTALION OPERATIONS FACILITY |  | 2012-10-25 |  |  | 29232 |  | 2014-08-18 |  | 2014-07-28 | 4
2013-04-15 | 2012 | SOCOM | Major Construction | FL | FLORIDA | EGLIN AFB | 76366 | COMPANY OPERATIONS FACILITY (GSTB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | 16664 | 14746 |  | 2015-12-11 | 2014-06-27 | 2015-09-12 | 9 | 1990
2013-04-15 | 2012 | SOCOM | Major Construction | FL | FLORIDA | EGLIN AFB | 76371 | COMPANY OPERATIONS FACILITY (GSB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | 19093 | 17143 |  | 2015-12-11 | 2013-09-30 | 2015-09-12 | 9 | 2000
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | FT BRAGG | 76373 | ADMINISTRATIVE ANNEX | 2012-03-01 | 2012-06-21 | GSC Construction Inc |  | 9810 |  | 2014-06-27 | 2013-12-10 | 2013-12-10 | 12 | 17
2013-04-15 | 2012 | SOCOM | Major Construction | KY | KENTUCKY | FT CAMPBELL | 76374 | MH-47 HANGAR | 2011-11-28 | 2012-05-07 | Hensel Phelps | 32450 | 32874 |  | 2014-05-22 |  | 2014-03-23 | 22
2013-04-15 | 2012 | SOCOM | Major Construction | CO | COLORADO | FT CARSON | 80234 | SOF CLASSIFIED OPERATIONS FACILITY (4UMAJOR CONSTRUCTION) | 2012-03-21 | 2012-05-25 | Facilities Contracting, Inc. | 1822 | 1822 | 2012-06-19 | 2012-12-16 | 2012-12-16 | 2013-02-04 | 66
2013-04-15 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ073014 | SOF C-130 SQ OPS FACILITY | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | 18028 | 18028 | 2012-11-09 | 2015-01-07 | 2015-01-06 | 2015-01-06 | 7 | -1613
2013-04-15 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ073018 | SOF C-130 WASH RACK HANGAR | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | 9329 | 9283 |  | 2014-06-18 | 2014-07-18 | 2014-04-10 | 10
2013-04-15 | 2012 | SOCOM | Minor Construction | NM | NEW MEXICO | CANNON AFB | CZQZ073021 | SOF AMXS FACILITY | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | 14700 | 14700 | 2013-01-10 | 2014-09-22 | 2014-12-22 | 2014-08-09 | 1 | 1613
2013-04-15 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ083011 | SOF APRON AND TAXIWAY | 2012-04-23 | 2012-08-31 | Okland/Geneva Joint Venture | 26836 | 26836 | 2012-10-03 | 2014-05-07 | 2014-01-26 | 2014-05-06 | 0
2013-04-15 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ083012 | SOF HANGAR/AMU | 2012-04-20 | 2012-08-31 | Hensel Phelps | 28160 | 28160 | 2012-10-24 | 2014-10-31 | 2014-12-23 | 2014-10-31 | 0
2013-04-15 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ083012 | SOF HANGAR/AMU | 2012-04-20 |  | Oakland/Geneva Joint Venture | 4608 | 4608 | 2012-10-30 | 2014-05-22 | 2014-02-22 | 2014-02-22 | 11
2013-04-15 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ083014 | SOF ADAL SIMULATOR FACILITY | 2012-04-17 | 2012-09-07 | PACE Pacific Corporation | 7349 | 7349 | 2012-10-03 | 2014-03-25 | 2014-01-26 | 2014-01-26 | 36
2013-04-15 | 2012 | SOCOM | Major Construction | NM | NEW MEXICO | CANNON AFB | CZQZ083016 | SOF SQUADRON OPERATIONS FACILITY | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | 18028 | 18028 | 2012-11-09 | 2014-05-30 | 2015-01-06 | 2014-05-30 | 7
2013-04-15 | 2012 | SOCOM | Major Construction | FL | FLORIDA | HURLBURT FIELD | FTEV093007 | SOF ENCLOSED ENGINE NOISE SUPPRESSORS | 2012-01-11 | 2012-03-29 | Carter's Contracting Services, Inc. | 2843 | 2865 | 2012-04-16 | 2012-12-12 | 2012-12-12 | 2013-02-02 | 97 | 200
2013-04-15 | 2012 | SOCOM | Major Construction | FL | FLORIDA | HURLBURT FIELD | FTEV103011 | SOF SIMULATOR FACILITY | 2012-05-01 | 2012-08-09 | Barlovento LLC. | 5551 | 5551 | 2012-09-13 | 2014-05-06 | 2013-12-24 | 2014-02-07 | 14
2013-04-15 | 2012 | SOCOM | Major Construction | FL | FLORIDA | MACDILL AFB | NVZR123709 | ACQUISTIONS CENTER PHASE II (PRKG GARAGE) | 2012-05-15 | 2012-07-31 | The Clement Group, L.L.C. | 8504 | 8504 | 2012-09-06 | 2014-04-18 | 2014-01-19 | 2014-01-19 | 31 | 1477
2013-04-15 | 2012 | SOCOM | Major Construction | CA | CALIFORNIA | CAMP PENDLETON | P-1174 | MWD FACILITY | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | 3075 | 3075 | 2012-10-03 | 2014-03-23 | 2014-03-23 | 2014-03-23 | 5
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | CAMP LEJEUNE | P-1285 | ARMORY FACILITY EXPANSION | 2012-01-26 | 2012-05-07 | Team Construction, LLC. | 4004 | 4004 | 2012-07-16 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 35
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | CAMP LEJEUNE | P-1419 | MILAM AID STATION EXPANSION (1UMAJOR CONSTRUCTION) | 2012-02-29 | 2012-04-19 | Graham Construction | 1465 | 1465 | 2012-08-01 | 2013-04-19 | 2013-04-19 | 2013-04-19 | 60
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | CAMP LEJEUNE | P-1440 | SOF G3-X TRAINING FACILITIES (5UMAJOR CONSTRUCTION) | 2012-08-20 | 2012-09-27 | Alderman Building Company, Inc. | 1541 | 1541 | 2013-01-15 | 2013-09-22 | 2013-09-22 | 2013-09-22 | 5
2013-04-15 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | DAM NECK | P-164 | LOGISTICS SUPPORT FACILITY | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | 11727 | 11727 | 2012-12-09 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 5
2013-04-15 | 2012 | SOCOM | Minor Construction | AK | ALASKA | KODIAK | P-531 | COLD WEATHER MARITIME TRAINING FACILITY |  | 2012-09-27 | Alutiiq Diversified Service, LLC | 17449 | 17449 |  | 2015-04-15 | 2015-04-15 | 2015-04-15 | 0 | 1487
2013-04-15 | 2012 | SOCOM | Minor Construction | VA | VIRGINIA | DAM NECK | P-769 | BUILDING RENOVATION | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | 3022 | 3022 | 2013-01-02 | 2014-06-27 | 2014-06-27 | 2014-06-27 | 5
2013-04-15 | 2012 | SOCOM | Major Construction | VA | VIRGINIA | DAM NECK | P-826 | MILITARY WORKING DOG FACILITY | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | 4139 | 4139 | 2012-12-09 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 5
2013-04-15 | 2012 | SOCOM | Major Construction | NC | NORTH CAROLINA | POPE AFB | TMKH043055 | SOF TRAINING FACILITY | 2012-01-31 | 2012-04-24 | JAAAT Technical Services, LLC | 4774 | 4783 | 2012-05-31 | 2014-01-21 | 2013-11-22 | 2013-11-22 | 29 | 111
2013-04-15 | 2010 | TMA | Major Construction | MD | MARYLAND | BETHESDA | 401V | TRAFFIC MITIGATION INCREMENT 1 | 2010-03-05 | 2010-05-10 | Clark/Balfour Beatty, Joint Venture, Gates N&S Wood Dr | 9512 | 10848 | N/A | N/A | 2010-03-10 | 2012-07-12 | 100
2013-04-15 | 2011 | TMA | Major Construction | MD | MARYLAND | BETHESDA | 401V | TRAFFIC MITIGATION INCREMENT 1 | 2010-03-16 | 2010-06-21 | Whiting-Turner, University Road & Perimeter Road/Palmer Road | 6800 | 10291 | 2010-07-01 | N/A | 2011-08-31 | 2011-08-31 | 100
2013-04-15 | 2011 | TMA | Major Construction | MD | MARYLAND | BETHESDA | 401A | TRAFFIC MITIGATION INCREMENT 2 | 2010-11-14 | 2011-04-21 | RMA Land Construction Inc, Gates Gunnell & Grier | 5132 | 5982 | N/A | N/A | 2012-12-06 | 2012-12-06 | 100
2013-04-15 | 2007 | TMA | BRAC | VA | VIRGINIA | FORT BELVOIR | 64238 | HOSPITAL REPLACEMENT, INCREMENT 1 | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV | 403400 | 403400 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100
2013-04-15 | 2008 | TMA | BRAC | MD | MARYLAND | BETHESDA NAVAL HOSPITAL | 005V | MEDICAL CENTER ADDITION/ALTERATION, INC 1 | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | 109025.544 | 774748 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2011-09-11 | 100
2013-04-15 | 2010 | TMA | BRAC | VA | VIRGINIA | FORT BELVOIR | 64241 | DENTAL CLINIC | 2009-09-16 | 2010-05-04 | Forrester Construction Company | 7541 | 8799 | 2010-05-18 | 2011-09-06 | 2011-09-10 | 2011-09-10 | 100
2013-04-15 | 2009 | TMA | BRAC | MS | MISSISSIPPI | KEESLER AFB | 478V | COMMUNITY HOSPITAL | 2009-04-09 | 2009-11-10 | W.G. Yates & Sons Constuction Co | 37258 | 42184 | 2010-01-01 | 2012-12-11 | 2011-09-11 | 2012-10-11 | 100
2013-04-15 | 2009 | TMA | BRAC | MD | MARYLAND | BETHESDA | 020V | SITE UTILITY INFRA UPGRADE FOR NICOE | 2008-07-08 | 2008-12-22 | Turner Construction Company | 7294.531 | 7371 | 2009-01-01 | 2010-03-29 | 2010-03-06 | 2010-04-30 | 100
2013-04-15 | 2008 | TMA | BRAC | TX | TEXAS | FORT SAM HOUSTON | 64188 | HEALTH CLINIC | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | 33382 | 37402 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 100
2013-04-15 | 2009 | TMA | BRAC | MD | MARYLAND | BETHESDA | 796V | SUPT FAC FOR WTC ADMIN CTR (BQ/DINING) | 2009-04-01 | 2009-08-26 | Whiting-Turner | 117555 | 126445 | 2010-02-01 | 2011-08-01 | 2011-08-31 | 2011-09-11 | 100
2013-04-15 | 2008 | TMA | BRAC | MD | MARYLAND | BETHESDA | 701V | CONSOLIDATION OF ADMINISTRATION SPACES (WTU ADMIN) | 2009-04-01 | 2009-08-26 | Whiting-Turner | 63440 | 78196 | 2010-02-01 | 2011-08-01 | 2011-08-31 | 2011-09-11 | 100
2013-04-15 | 2009 | TMA | BRAC | MD | MARYLAND | ABERDEEN PROVING GROUND | 65731 | USAMRICD REPLACEMENT, INC 1 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | 6887.87 | 7070.1979 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100
2013-04-15 | 2010 | TMA | BRAC | MD | MARYLAND | ABERDEEN PROVING GROUND | 67180 | USAMRICD REPLACEMENT, INC 2 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100
2013-04-15 | 2010 | TMA | BRAC | MD | MARYLAND | ABERDEEN PROVING GROUND | 67180 | USAMRICD REPLACEMENT, INC 2 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 100
2013-04-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | FORT DETRICK | 58395 | USAMRIID REPLACEMENT STAGE I, INCREMENT 1 | 2007-06-30 | 2007-09-29 | Cont # 1 - Offiste San Sewer & Storm (James Construction) | 2808.7 | 2809 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 100
2013-04-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | FORT DETRICK | 58395 | USAMRIID REPLACEMENT STAGE I, INCREMENT 1 | 2008-01-10 | 2008-08-01 | Con # 2 - Storm Lat 1&3A (James Construction) | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 100
2013-04-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | FORT DETRICK | 58395 | USAMRIID REPLACEMENT STAGE I, INCREMENT 1 | 2008-05-01 | 2009-09-28 | Con# 3 - IMP Pond (James Corporation) | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 100
2013-04-15 | 2007 | TMA | Major Const Incremental | MD | MARYLAND | FORT DETRICK | 58395 | USAMRIID REPLACEMENT STAGE I, INCREMENT 1 | 2008-01-10 | 2008-09-25 | Cont # 4 - Early Site/Utility (Grunley/Goel JVA LLC) | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 100
2013-04-15 | 2010 | TMA | Major Const Incremental | TX | TEXAS | FORT BLISS | 72481 | FORT BLISS HOSPITAL REPL, INCR 1 | 2011-03-25 | 2011-06-17 | Janco - Water Tower | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 100
2013-04-15 | 2007 | TMA | Major Const Incremental | FL | FLORIDA | MACDILL AFB | 52330 | CLINIC REPLACEMENT | 2007-02-16 | 2007-07-19 | Caddell Construction Co., Inc | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100
2013-04-15 | 2008 | TMA | Major Const Incremental | FL | FLORIDA | MACDILL AFB | 67647 | CLINIC REPLACEMENT, INC II | 2007-02-16 | 2007-07-19 | Caddell Construction Co., Inc | 32890 | 42183 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100
2013-04-15 | 2007 | TMA | Major Const Incremental | AK | ALASKA | FORT RICHARDSON | 64773 | HEALTH CLINIC | 2007-03-02 | 2007-05-16 | Bristol Design Build Services LLC | 26317 | 29824 | 2007-03-01 | 2009-01-01 | 2009-09-15 | 2009-01-21 | 100 | 4000
2013-04-15 | 2007 | TMA | Major Const Incremental | CA | CALIFORNIA | FORT IRWIN | 47627 | DENTAL CLINIC ADDITION/ALTERATION | 2006-11-24 | 2007-03-30 | Hal Hays Construction, Inc. | 4736 | 4864 | 2007-05-16 | 2008-08-12 | 2008-09-07 | 2008-09-21 | 100 | 751
2013-04-15 | 2007 | TMA | Major Const Incremental | IL | ILLINOIS | NH GREAT LAKES | 55924 | FED HEALTH CARE, (PARKING STRUCTURE) (TOTAL AUTH = $133M) | 2006-08-28 | 2007-05-25 | Joseph J Henderson & Son, Inc | 16061.8 | 17588 | 2007-07-02 | 2008-12-30 | 2008-06-30 | 2008-12-30 | 100
2013-04-15 | 2007 | TMA | Major Construction | HI | HAWAII | NS PEARL HARBOR | 59178 | EPMU 6 REPLACEMENT FACILITY | 2006-10-30 | 2007-07-05 | Primatech Construction, Inc | 6763 | 6950 | 2007-09-01 | 2009-03-26 | 2008-11-26 | 2009-03-26 | 100
2013-04-15 | 2007 | TMA | Major Construction | NY | NEW YORK | FORT DRUM | 57724 | DENTAL CLINIC | 2007-03-28 | 2007-07-16 | SLR Contracting & Service Co., Inc | 8121 | 8468 | 2007-08-13 | 2009-05-20 | 2009-02-03 | 2009-04-20 | 100
2013-04-15 | 2007 | TMA | Major Construction | TX | TEXAS | FORT HOOD | 59210 | WOMEN'S HEALTH ADD/ALT | 2006-11-06 | 2008-03-07 | Akima Construction Services | 17545 | 17820 | 2008-04-08 | 2010-12-17 | 2010-04-08 | 2010-11-17 | 100
2013-04-15 | 2007 | TMA | Major Construction | IT | ITALY | VICENZA | 62455 | ENHANCED HEALTH SERVICE CENTER**FOREIGN CURRENCY | 2007-02-12 | 2007-08-16 | Consorzio Bilfinger Berger Pizzarotti | 34790.371 | 37828 | N/A | N/A | 2010-04-27 | 2010-09-15 | 100
2013-04-15 | 2008 | TMA | Major Construction | FL | FLORIDA | MACDILL AFB | 64809 | PHARMACARE ADDITION/ALTERATION | 2007-09-27 | 2008-02-29 | J2 Engineering, Inc | 3381 | 3489 | 2008-03-24 | 2009-03-24 | 2009-03-24 | 2009-03-24 | 100
2013-04-15 | 2008 | TMA | Major Construction | IL | ILLINOIS | NH GREAT LAKES | 65028 | FEDERAL HEALTHCARE FACILITY | 2007-10-01 | 2008-02-27 | Flannery Fire Protection | 6781.5 | 7382 | 2008-04-01 | 2009-09-02 | 2009-09-02 | 2009-09-02 | 100
2013-04-15 | 2008 | TMA | Major Construction | IL | ILLINOIS | NH GREAT LAKES | 65028 | FEDERAL HEALTHCARE FACILITY | 2008-02-22 | 2008-06-17 | Walsh Construction Company of Illinois | 71567 | 75921 | 2008-08-01 | 2010-10-01 | 2010-07-31 | 2010-09-27 | 100
2013-04-15 | 2008 | TMA | Major Construction | TX | TEXAS | CAMP BULLIS | 17153 | HEALTH CLINIC REPLACEMENT | 2008-02-15 | 2008-05-08 | Guyco, Inc. | 5214 | 5430 | 2008-05-08 | 2009-11-18 | 2009-11-16 | 2010-03-17 | 100
2013-04-15 | 2008 | TMA | Major Construction | VA | VIRGINIA | NS NORFOLK | 53577 | ENVIRON. PREV. MED UNIT 2 REPLACEMENT | 2008-10-31 | 2009-03-31 | Virtexco Corporation | 5951 | 6558 | 2009-05-01 | 2010-10-15 | 2010-05-04 | 2010-09-08 | 100
2013-04-15 | 2008 | TMA | Major Construction | WA | WASHINGTON | FORT LEWIS | 64473 | MEDICAL/DENTAL CLINIC | 2008-07-29 | 2008-09-18 | The Korte Company | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 100 | 1885
2013-04-15 | 2008 | TMA | Major Construction | GM | GERMANY | SPANGDAHLEM AB | 52332 | MEDICAL CLINIC REPLACEMENT | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 100
2013-04-15 | 2009 | TMA | Major Construction | CO | COLORADO | BUCKLEY AFB | 64709 | SATELLITE PHARMACY | 2009-03-04 | 2009-05-21 | Liberty-Mass II | 1963 | 2014 | 2009-02-13 | 2010-09-03 | 2010-09-09 | 2010-09-09 | 100
2013-04-15 | 2009 | TMA | Major Construction | FL | FLORIDA | NAS JACKSONVILLE | 971B | HOSPITAL ALTERATION (ARRA) | 2009-09-09 | 2009-12-18 | Brasfield & Gorrie, LLC | 8000 | 13282 | 2010-01-20 | 2011-12-11 | 2011-12-11 | 2011-12-11 | 100
2013-04-15 | 2009 | TMA | Major Construction | GA | GEORGIA | FORT BENNING | 65080 | CONSOLIDATED TROOP MEDICAL CLINIC | 2008-11-12 | 2009-02-25 | Mathis and Sons, Inc. | 2983 | 3084 | 2009-03-16 | 2010-05-07 | 2010-03-16 | 2010-05-07 | 100
2013-04-15 | 2009 | TMA | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 64573 | MEDICAL/DENTAL CLINIC | 2008-12-10 | 2009-05-26 | The Korte Company | 14342 | 14611 | 2009-05-22 | 2011-03-30 | 2011-05-15 | 2011-03-30 | 100 | 3867
2013-04-15 | 2009 | TMA | Major Construction | MD | MARYLAND | BETHESDA | 75585 | VISION CENTER OF EXCELLENCE | 2010-02-17 | 2010-06-25 | Clark/Balfour Beatty, Joint Venture | 3473 | 3900 | 2011-03-01 | 2011-08-01 | 2011-07-31 | 2011-07-31 | 100
2013-04-15 | 2009 | TMA | Major Construction | TX | TEXAS | FORT HOOD | 74650 | SANITARY SEWER | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc, Sanitary Sewer | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 100
2013-04-15 | 2009 | TMA | Major Construction | TX | TEXAS | FORT HOOD | 74650 | RELOCATION OF GAS & ELECTRIC UTILITIES | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 100
2013-04-15 | 2009 | TMA | Major Construction | TX | TEXAS | FORT HOOD | 74650 | DEMOLITION OF HOOD STADIUM | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc., Demolition of Hood Stadium | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 100
2013-04-15 | 2009 | TMA | Major Construction | TX | TEXAS | FORT SAM HOUSTON | 53341 | MEDICAL INSTRUCTIONAL FACILITY | 2008-11-13 | 2009-02-20 | Innovative Technology Solutions, Inc | 10432 | 15334 | 2010-01-27 | 2012-08-14 | 2010-06-02 | 2010-11-12 | 100
2013-04-15 | 2009 | TMA | Major Construction | GQ | GUAM | NH GUAM | 55918 | CENTRAL UTILITY PLANT | 2009-03-15 | 2009-09-15 | PDI - HSW Joint Venture | 13034 | 13672 | 2009-10-01 | 2011-06-01 | 2011-02-07 | 2011-02-07 | 100
2013-04-15 | 2010 | TMA | Major Construction | AK | ALASKA | ELMENDORF AFB | 71310 | AEROMEDICAL SERVICES/MENTAL HEALTH CLINIC | 2009-09-18 | 2010-02-25 | Davis Constructors & Engineers, Inc. | 19839 | 20258 | 2010-03-11 | 2011-11-29 | 2011-10-15 | 2011-11-29 | 100
2013-04-15 | 2010 | TMA | Major Construction | AK | ALASKA | FORT RICHARDSON | 69805 | HEALTH CLINIC ADD/ALT | 2009-11-30 | 2010-02-10 | Bristol Design Build Services LLC | 3087 | 3140 | 2010-02-22 | 2011-03-18 | 2011-05-23 | 2011-03-18 | 100
2013-04-15 | 2010 | TMA | Major Construction | CO | COLORADO | FORT CARSON | 69295 | HEALTH AND DENTAL CLINICS | 2010-04-26 | 2010-09-23 | Korte Construction Company | 17616 | 18171 | 2010-10-20 | 2012-02-27 | 2012-02-13 | 2012-02-27 | 100
2013-04-15 | 2010 | TMA | Major Construction | GA | GEORGIA | FORT BENNING | 64481 | BLOOD DONOR CENTER REPLACEMENT | 2009-11-05 | 2010-09-24 | IAP-Leopardo | 7792 | 7904 | 2010-11-12 | 2012-08-05 | 2012-05-05 | 2012-05-05 | 100
2013-04-15 | 2010 | TMA | Major Construction | GA | GEORGIA | FORT BENNING | 71620 | DENTAL CLINIC | 2009-12-23 | 2010-03-31 | EJS Contracting, Inc. | 2549 | 2619 | 2010-04-28 | 2011-03-11 | 2011-04-28 | 2011-03-11 | 100
2013-04-15 | 2010 | TMA | Major Construction | GA | GEORGIA | FORT STEWART | 70481 | HEALTH AND DENTAL CLINICS | 2009-11-25 | 2010-09-30 | Brafield & Gorrie, LLC | 9742 | 10101 | 2010-10-21 | 2012-06-04 | 2012-03-22 | 2012-03-22 | 100
2013-04-15 | 2010 | TMA | Major Construction | KY | KENTUCKY | FORT CAMPBELL | 70557 | HEALTH CLINIC ADDITION/ALTERATION | 2010-04-12 | 2010-09-27 | Charpie-Korte Joint Venture | 4018 | 4034 | 2010-09-30 | 2011-06-30 | 2012-02-05 | 2011-06-30 | 100
2013-04-15 | 2010 | TMA | Major Construction | MO | MISSOURI | FORT LEONARD WOOD | 64153 | DENTAL CLINIC ADDITION/ALTERATION | 2009-10-20 | 2010-07-02 | TMG Services | 3890 | 4319 | 2010-07-22 | 2012-03-19 | 2012-01-13 | 2012-03-15 | 100
2013-04-15 | 2010 | TMA | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 64244 | CONSOLIDATED HEALTH CLINIC | 2009-10-28 | 2010-09-30 | Korte Construction Company | 15313 | 15501 | 2010-10-21 | 2012-10-26 | 2012-05-18 | 2012-10-26 | 100
2013-04-15 | 2010 | TMA | Major Construction | NC | NORTH CAROLINA | FORT BRAGG | 69353 | BEHAVIORAL HEALTH CLINIC (NDAA 2011 CHANGE TO BHC) | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 100
2013-04-15 | 2010 | TMA | Major Construction | OK | OKLAHOMA | FORT SILL | 69711 | DENTAL CLINIC | 2009-11-03 | 2010-06-16 | The Korte Company | 8199 | 8199 | 2010-07-30 | 2012-03-04 | 2012-01-04 | 2012-01-04 | 100
2013-04-15 | 2010 | TMA | Major Construction | TX | TEXAS | FORT BLISS | 69294 | HEALTH AND DENTAL CLINICS | 2010-02-17 | 2010-11-17 | LEC-CMS, LP | 12743 | 13226 | 2011-02-07 | 2012-08-20 | 2012-05-22 | 2012-12-31 | 100
2013-04-15 | 2010 | TMA | Major Construction | TX | TEXAS | LACKLAND AFB | 71318 | DENTAL CLINIC REPLACEMENT | 2009-10-28 | 2010-02-26 | J E Dunn Construction Company | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 100 | 438.761
2013-04-15 | 2010 | TMA | Major Construction | WA | WASHINGTON | FORT LEWIS | 70343 | HEALTH AND DENTAL CLINIC ADDITIONS | 2009-12-04 | 2010-03-24 | Vet Industrial of Bremerton, WA | 7219 | 7583 | 2010-04-19 | 2011-05-13 | 2011-05-07 | 2011-05-02 | 100
2013-04-15 | 2010 | TMA | Major Construction | UK | UNITED KINGDOM | RAF ALCONBURY | 71550 | MEDICAL/DENTAL CLINIC REPLACEMENT | 2010-06-16 | 2010-12-14 | Vinci Construction UK | 13097.501 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 100
2013-04-15 | 2011 | TMA | Major Construction | VA | VIRGINIA | FORT BELVOIR | 71251 | DENTAL CLINIC REPLACEMENT | 2009-09-16 | 2011-05-17 | Forrester Construction Company | 2832 | 3021 | 2011-05-17 | 2013-01-31 | 2012-07-11 | 2013-01-31 | 100
2013-04-15 | 2011 | NSA | Major Construction | WW | CLASSIFIED LOCATION | CLASSIFIED LOCATION | 22573 | CLASSIFIED PROJECT | 2012-08-15 | 2012-09-30 | Kaseman |  |  | 2012-12-01 | 2012-09-15 | 2012-09-30 | 2012-09-30 | 10
2013-04-15 | 2100 | NSA | Major Construction | WW | CLASSIFIED LOCATION | CLASSIFIED LOCATION | 22573 | CLASSIFIED PROJECT | 2012-08-01 | 2012-09-21 | Hardline |  |  | 2012-09-25 | 2012-09-15 | 2013-04-04 | 2013-04-04 | 35
2013-04-15 | 2008 | DLA | Major Construction | CA | CALIFORNIA | NAV SUP FLEET LOGISTICS CENTER SAN DIEGO, POINT LOMA | DESC0704 | REPLACE FUEL STORAGE FACILITIES INCR#1 (OF 4 INCREMENTS) | 2008-02-20 | 2008-09-30 | Nova Group Inc - Underground Construction Company - AJV | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 98 | 0 | Increments 1-3 awarded
2013-04-15 | 2008 | DLA | Major Construction | PA | PENNSYLVANIA | DLA DISTRIBUTION NEW CUMBERLAND | DDCX0702 | REPLACE CENTRAL HEAT PLANT | 2008-07-14 | 2008-09-28 | John C. Grimberg Company | 19757 | 20753 | 2008-11-03 | 2011-10-21 | 2011-07-21 | 2012-10-21 | 99 | 0
2013-04-15 | 2009 | DLA | Major Construction | CA | CALIFORNIA | DLA DISTRIBUTION DEPOT SAN JOAQUIN AT TRACY | DDCX1002 | REPLACE GENERAL PURPOSE WAREHOUSE | 2008-11-11 | 2009-03-11 | Whiting Turner Contracting Co. | 29345 | 30469 | 2009-04-02 | 2012-01-05 | 2012-03-17 | 2013-03-20 | 100 | -6,600 | Rescinded per PL 111-117
2013-04-15 | 2009 | DLA | Major Construction | FL | FLORIDA | NAV SUP FLEET LOGISTICS CENTER JACKSONVILLE | DESC0801 | REPLACE FUEL STORAGE TANKS | 2009-03-11 | 2009-09-22 | Mid Eastern Builders INC | 22226 | 24240 | 2009-10-30 | 2012-12-31 | 2012-09-22 | 2012-12-15 | 99 | -9,000 | Rescinded per PL 111-117
2013-04-15 | 2009 | DLA | Major Construction | GM | GERMANY | DLA DISTRIBUTION EUROPE AT GERMERSHEIM | DDCX0904 | LOGISTICS DISTRIBUTION CENTER | 2010-02-12 | 2010-05-18 | Wolfe & Muller Regionalbau GmbH & Co. / Peter Gross GmbH & Co. | 34991 | 36800 | 2010-06-16 | 2012-01-25 | 2012-01-04 | 2012-01-04 | 100 | -10,400 | Rescinded by 0SD 24 May 11A, PROJECT COMPLETE
2013-04-15 | 2009 | DLA | Major Construction | HI | HAWAII | NAV SUP FLEET LOGISTICS CENTER PEARL HARBOR | DESC0808 | REPLACE FUEL PIPELINE | 2009-05-01 | 2009-06-12 | Watts Construction LLC | 17336 | 21792 | 2009-07-12 | 2012-12-30 | 2011-07-12 | 2013-03-31 | 99 | -5,300 | Rescinded per PL 111-117
2013-04-15 | 2009 | DLA | Major Construction | NM | NEW MEXICO | KIRTLAND AIR FORCE BASE | DESC0802 | REPLACE FUEL STORAGE TANKS | 2009-04-06 | 2009-08-20 | Kinley Construction | 7355 | 7762 | 2009-10-14 | 2011-03-18 | 2011-06-11 | 2011-06-11 | 100 | -5,900 | Rescinded per PL 111-117, PROJECT COMPLETE
2013-04-15 | 2009 | DLA | Major Construction | UT | UTAH | HILL AIR FORCE BASE | DESC0608 | HYDRANT FUEL SYSTEM | 2009-01-29 | 2009-05-22 | Rockford Corp | 14636 | 15416 | 2009-06-18 | 2011-04-21 | 2011-05-13 | 2011-05-13 | 100 | -3000 | Rescinded by 0SD 24 May 11A, PROJECT COMPLETE
2013-04-15 | 2009 | DLA | Major Construction | VA | VIRGINIA | DEFENSE FUEL SUPPORT POINT CRANEY ISLAND | DESC0703 | REPLACE FUEL STORAGE TANKS | 2009-04-01 | 2009-07-31 | Mid Eastern Builders INC | 36371 | 38025 | 2009-09-03 | 2012-12-29 | 2012-08-29 | 2013-02-03 | 99 | 0
2013-04-15 | 2010 | DLA | Major Construction | CA | CALIFORNIA | NAV SUP FLEET LOGISTICS CENTER SAN DIEGO, POINT LOMA | DESC0704 | REPLACE FUEL STORAGE FACILITIES INCR#2 (OF 4 INCREMENTS) |  | 2011-03-22 | Nova Group Inc - Underground Construction Company - AJV | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 98 | 0 | Increments 1-3 awarded
2013-04-15 | 2010 | DLA | Major Construction | CA | CALIFORNIA | TRAVIS AIR FORCE BASE | DESC0803 | REPLACE FUEL DISTRIBUTION SYSTEM | 2010-11-10 | 2011-02-18 | Kinley Construction | 13621 | 14084 | 2011-05-10 | 2013-03-01 | 2012-08-26 | 2013-03-20 | 95 | 0
2013-04-15 | 2010 | DLA | Major Construction | FL | FLORIDA | JACKSONVILLE INTERNATIONAL AIRPORT | DESC0908 | REPLACE JET FUEL STORAGE COMPLEX | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | 7909 | 9553 | 2010-04-27 | 2012-08-09 | 2011-09-20 | 2013-06-23 | 88 | -1900 | Rescinded by 0SD 18 May 11A
2013-04-15 | 2010 | DLA | Major Construction | MN | MINNESOTA | DULUTH AIR NATIONAL GUARD | DESC1002 | REPLACE JET FUEL STORAGE COMPLEX | 2010-03-10 | 2010-07-16 | Talon Industries Inc. | 11195 | 11195 | 2010-08-30 | 2012-01-12 | 2011-11-01 | 2012-01-09 | 100 | -2000 | Rescinded by 0SD 18 May 11A, PROJECT COMPLETE
2013-04-15 | 2010 | DLA | Major Construction | NC | NORTH CAROLINA | MARINE CORPS AIR STATION NEW RIVER | DESC11S3 | REPLACE PUMP STATION | 2010-02-20 | 2010-09-29 | North State Mechanical Inc. | 947 | 981 | 2011-01-15 | 2012-11-16 | 2011-12-08 | 2012-08-10 | 99 | 0
2013-04-15 | 2010 | DLA | Minor Construction | CU | CUBA | NAVAL STATION GUANTANAMO BAY | DESC0904 | REPLACE FUEL STORAGE TANK | 2010-01-19 | 2010-05-27 | Toltest, Inc | 8594 | 8658 | 2010-05-27 | 2011-11-28 | 2012-11-28 | 2012-11-28 | 100 | -2200 | Rescinded by 0SD 18 May 11A, PROJECT COMPLETE
2013-04-15 | 2010 | DLA | Major Construction | GR | GREECE | NAVAL SUPPORT ACTIVITY SOUDA BAY, CRETE | DESC0707A | FUEL TANKS AND PIPELINE REPLACEMENT | 2010-01-29 | 2010-09-30 | AKTORS, S.A. | 19667 | 21010 | 2010-01-12 | 2013-01-11 | 2012-07-09 | 2013-05-29 | 87 | -8,250 | Rescinded by 0SD 18 May 11A
2013-04-15 | 2010 | DLA | Major Construction | KR | KOREA | OSAN AIR BASE | DESC0907 | HYDRANT FUEL SYSTEM | 2010-01-12 | 2010-04-16 | Namwha Construction Co. | 17844 | 18975 | 2010-08-27 | 2014-02-16 | 2013-11-18 | 2013-05-13 | 73 | -7,000 | Rescinded by 0SD 18 May 11A
2013-04-15 | 2010 | DLA | Major Construction | UK | UNITED KINGDOM | ROYAL AIR FORCE BASE MILDENHALL | DESC0910 | CONNECT FUEL TANK TO DISTRIBUTION PIPELINE | 2010-04-23 | 2010-09-16 | Entrepose Industrial Services | 3300 | 3300 | 2011-03-07 | 2013-03-04 | 2011-08-18 | 2011-12-16 | 100 | 0 | PROJECT COMPLETE
2013-04-15 | 2011 | DLA | Major Construction | CA | CALIFORNIA | NAV SUP FLEET LOGISTICS CENTER SAN DIEGO, POINT LOMA | DESC0704 | REPLACE FUEL STORAGE FACILITIES INCR#3 (OF 4 INCREMENTS) |  | 2011-03-30 | Nova Group Inc - Underground Construction Company - AJV | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 98 | 0 | Increments 1-3 awarded
2013-04-15 | 2011 | DLA | Major Construction | CA | CALIFORNIA | NAVAL BASE VENTURA COUNTY, POINT MUGU | DESC10S4 | AIRCRAFT DIRECT FUELING STATION | 2011-04-29 | 2011-06-30 | RORE, INC. | 2553 | 2553 | 2011-07-30 | 2014-04-24 | 2012-08-13 | 2014-04-24 | 71 | 0 | Design/Build 35% 11/01/11
2013-04-15 | 2011 | DLA | Major Construction | CA | CALIFORNIA | EDWARDS AIR FORCE BASE | DESC11U1 | TRUCK OFFLOAD FACILITY | 2012-03-16 | 2012-07-12 | Kinley Construction Company | 1019 | 1019 | 2012-07-26 | 2013-05-14 | 2013-05-31 | 2013-08-01 | 1 | 0
2013-04-15 | 2011 | DLA | Minor Construction | GA | GEORGIA | HUNTER ARMY ARIFIELD | DESC11S4 | FUEL UNLOAD FACILITY | 2011-06-03 | 2011-09-15 | Ponds Constructors, Inc | 1199 | 1199 | 2011-10-26 | 2012-10-25 | 2012-10-31 | 2013-10-25 | 13 | -980 | Rescinded by OSD 23 Mar 12A, Design-Build Effort
2013-04-15 | 2011 | DLA | Major Construction | HI | HAWAII | HICKAM AIR FORCE BASE | DESC1190 | ALTER FUEL STORAGE TANKS | 2011-01-03 | 2011-05-26 | Reliable Contracting Group, LLC | 7584 | 8071 | 2011-06-22 | 2013-02-13 | 2012-12-13 | 2013-02-13 | 99 | 0
2013-04-15 | 2011 | DLA | Major Construction | ID | IDAHO | MOUNTAIN HOME AIR FORCE BASE | DESC1113 | REPLACE FUEL STORAGE TANKS | 2011-03-30 | 2011-09-02 | Garco Construction, Inc. | 16480 | 16573 | 2011-10-12 | 2014-06-11 | 2012-04-12 | 2014-06-11 | 67 | -8380 | Rescinded by OSD 23 Mar 12A
2013-04-15 | 2011 | DLA | Major Construction | MD | MARYLAND | ANDREWS AIR FORCE BASE | DESC1003 | REPLACE FUEL STORAGE AND DISTRIBUTION FACILITIES | 2011-05-15 | 2011-10-31 | MEB General Contractors | 7971 | 7971 | 2011-11-21 | 2013-05-18 | 2013-05-18 | 2013-08-01 | 80 | -4872 | Rescinded by OSD 23 Mar 12A
2013-04-15 | 2011 | DLA | Major Construction | PA | PENNSYLVANIA | DLA DISTRIBUTION NEW CUMBERLAND | DDCX0802 | REPLACE HEADQUARTERS FACILITY | 2011-11-23 | 2012-08-17 | Walsh Construction | 80775 | 80775 | 2012-08-30 | 2015-12-18 | 2015-09-18 | 2015-10-30 | 8 | 0
2013-04-15 | 2011 | DLA | Major Construction | OH | OHIO | DLA LAND AND MARITIME COLUMBUS | DSCC0802 | REPLACE PUBLIC SAFETY FACILITY | 2011-04-04 | 2011-10-21 | Industria Paschen Group JV | 5883 | 6089 | 2011-11-10 | 2013-03-21 | 2013-03-21 | 2013-04-24 | 91 | 0
2013-04-15 | 2011 | DLA | Major Construction | VA | VIRGINIA | DEFENSE FUEL SUPPORT POINT CRANEY ISLAND | DESC0909 | REPLACE FUEL PIER | 2010-10-20 | 2011-09-12 | Major Constructionructionlean Contracting Company | 28815 | 29322 | 2012-10-26 | 2014-06-30 | 2014-07-03 | 2014-08-29 | 43 | -9428 | Rescinded by OSD 23 Mar 12A
2013-04-15 | 2011 | DLA | Major Construction | JA | JAPAN | KADENA AIR BASE OKINAWA | DESC11S1 | INSTALL FUEL FILTER/SEPARATORS | 2010-10-07 | 2011-06-27 | Nippo Corporation | 1175 | 1175 | 2011-07-13 | 2012-11-09 | 2012-10-27 | 2012-10-27 | 100 | 0 | PROJECT COMPLETE
2013-04-15 | 2011 | DLA | Major Construction | JA | JAPAN | MISAWA AIR BASE | DESC0503 | HYDRANT FUEL SYSTEM | 2012-05-12 | 2012-09-22 | Tokyo Construction Co., Ltd. | 25204 | 25204 | 2013-04-01 | 2015-01-27 | 2014-11-08 | 2015-11-08 | 1 | 0
2013-04-15 | 2011 | DLA | Major Construction | UK | UNITED KINGDOM | ROYAL AIR FORCE BASE MILDENHALL | DESC0905 | REPLACE HYDRANT FUEL SYSTEM | 2011-04-19 | 2011-12-06 | Spiecapag | 12535.429 | 12535 | 2011-12-09 | 2013-03-14 | 2013-03-14 | 2013-05-30 | 70 | 0
2013-04-15 | 2012 | DLA | Major Construction | AK | ALASKA | EIELSON AIR FORCE BASE | DESC1108 | UPGRADE RAIL LINE | 2012-02-29 | 2012-07-06 | G2 Construction, Inc. | 12210 | 12332 | 2012-07-16 | 2014-04-03 | 2013-12-05 | 2014-04-03 | 37 | 0
2013-04-15 | 2012 | DLA | Major Construction | AZ | ARIZONA | DAVIS MONTHAN AIR FORCE BASE | DESC1103 | REPLACE HYDRANT FUEL SYSTEM | 2012-05-04 | 2012-09-25 | Nova Group Inc. | 18252 | 18252 | 2012-11-13 | 2015-03-29 | 2014-11-03 | 2015-01-02 | 13 | -1322 | Diverted to Altus
2013-04-15 | 2012 | DLA | Major Construction | CA | CALIFORNIA | NAVBASE CORONADO, SAN CLEMENTE ISLAND | DESC1205 | REPLACE FUEL FACILITIES | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | 27453 | 27453 | 2013-02-28 | 2015-03-24 | 2015-03-24 | 2015-03-24 | 0 | 9000 | Additional funds Formal Reprogramming FY09 Germersheim
2013-04-15 | 2012 | DLA | Major Construction | CA | CALIFORNIA | NAV SUP FLEET LOGISTICS CENTER SAN DIEGO, POINT LOMA | DESC0704 | REPLACE FUEL STORAGE FACILITIES INCR#4 (OF 4 INCREMENTS) |  | 2012-03-29 | Nova Group Inc - Underground Construction Company - AJV | 15512 | 15512 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-01-17 | 98 | -7000 | 10 USC 2853 submitted 23 Apr 12. Increments 1-4 awarded
2013-04-15 | 2012 | DLA | Major Construction | CA | CALIFORNIA | DLA DISTRIBUTION TRACY | DDCX1102 | PUBLIC SAFETY FACILITY | 2012-04-13 | 2012-07-16 | MASCON, INC | 14615 | 14615 | 2012-08-29 | 2014-06-15 | 2014-03-24 | 2014-09-30 | 5 | 900 | Additional funds from FY 09 Bid Savings
2013-04-15 | 2012 | DLA | Major Construction | FL | FLORIDA | NAVAL AIR STATION WHITING FIELD | DESC12S3 | TRUCK LOAD/UNLOAD FACILITY | 2012-01-13 | 2012-03-21 | Weston Solutions Inc. | 2500 | 3009 | 2012-03-21 | 2013-03-15 | 2013-03-24 | 2013-03-24 | 21 | 0
2013-04-15 | 2012 | DLA | Major Construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | DESC12S5 | UPGRADE REFUELER PARKING AREA | 2011-10-21 | 2012-03-13 | RAASS Brothers INC | 5079 | 5384 | 2012-08-05 | 2013-04-09 | 2013-04-09 | 2013-09-12 | 46 | 0
2013-04-15 | 2012 | DLA | Major Construction | HI | HAWAII | JOINT BASE PEARL HARBOR - HICKAM | DESC1101 | ALTER WAREHOUSE SPACE | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | 5500 | 5511 | 2012-08-13 | 2013-06-14 | 2013-06-14 | 2013-06-14 | 52 | 0
2013-04-15 | 2012 | DLA | Major Construction | LA | LOUISIANA | BARKSDALE AIR FORCE BASE | DESC1106 | HYDRANT FUEL SYSTEM | 2011-10-04 | 2012-01-30 | Thrash Commercial Contractors INC | 4687 | 4953 | 2012-02-28 | 2013-03-14 | 2013-03-14 | 2013-03-11 | 32 | 0
2013-04-15 | 2012 | DLA | Major Construction | MS | MISSISSIPPI | COLUMBUS AIR FORCE BASE | DESC11S2 | REPLACE REFUELER PARKING FACILITY | 2012-02-14 | 2012-04-30 | Reliable Contracting Group, LLC | 2360 | 2360 | 2012-06-07 | 2013-05-20 | 2013-03-15 | 2013-03-15 | 88 | 0
2013-04-15 | 2012 | DLA | Major Construction | OH | OHIO | DLA LAND & MARITIME COLUMBUS | DSCC1201 | SECURITY ENHANCEMENTS | 2012-02-19 | 2012-05-03 | Pinnacle Construction Development Group | 8550 | 9041 | 2012-06-03 | 2014-01-06 | 2013-10-16 | 2013-10-16 | 20 | 0
2013-04-15 | 2012 | DLA | Major Construction | OK | OKLAHOMA | ALTUS AIR FORCE BASE | DESC1201 | REPLACE FUEL TRANSFER PIPELINE | 2012-03-26 | 2012-09-17 | Reliable Contracting Group, LLC | 8856 | 8856 | 2012-11-01 | 2014-05-27 | 2014-03-01 | 2014-03-01 | 17 | 1322 | Additional funds from Davis Monthan
2013-04-15 | 2012 | DLA | Major Construction | PA | PENNSYLVANIA | DLA TROOP SUPPORT PHILADELPHIA | DSCP1201 | UPGRADE HVAC SYSTEM | 2012-03-28 | 2012-06-01 | WU & Associates, Inc | 4775 | 4775 | 2012-06-14 | 2013-09-09 | 2013-07-17 | 2013-07-17 | 38 | 0
2013-04-15 | 2012 | DLA | Major Construction | SC | SOUTH CAROLINA | CHARLESTON AIR FORCE BASE | DESC1101 | REPLACE FUEL STORAGE FACILITY | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | 26085 | 26085 | 2012-11-30 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 1 | 5132 | Additional funds from Formal Reprogramming
2013-04-15 | 2012 | DLA | Major Construction | WA | WASHINGTON | MAJOR CONSTRUCTIONRUCTIONCHORD AIR FORCE BASE | DESC1004 | REPLACE HYDRANT FUEL SYSTEM | 2011-10-28 | 2012-02-02 | Garco Construction, Inc. | 10217 | 10413 | 2012-02-27 | 2013-09-15 | 2013-05-17 | 2013-05-17 | 64 | 0
2013-04-15 | 2012 | DLA | Major Construction | WA | WASHINGTON | NAS WHIDBEY ISLAND | DESC1104 | REPLACE FUEL PIPELINE | 2012-03-20 | 2013-02-28 | Talon Industries Inc. | 16984 | 16984 |  | 2014-08-30 | 2014-08-30 | 2014-08-30 | 0 | 0
2013-04-15 | 2012 | DLA | Major Construction | WV | WEST VIRGINIA | CAMP DAWSON | DESC12S1 | REPLACE HYDRANT FUEL SYSTEM | 2012-04-26 | 2012-07-05 | Kinley Construction Company | 1930 | 1930 | 2012-07-03 | 2013-12-01 | 2013-12-05 | 2013-12-05 | 5 | 0
2013-04-15 | 2008 | DIA | Major Construction | DC | DISTRICT OF COLUMBIA | DIAC | 154207 | EMERGENCY BACK UP WATER SYSTEM | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC | 1012000 | 1012000 | 2009-10-03 | 2012-01-20 | 2011-09-16 |  | 100 |  | Approp. - $1,012
2013-04-15 | 2010 | DIA | Major Construction | AL | ALABAMA | MSIC, REDSTONE ARSENAL | DIA10-002 | DESIGN/BUILD CONSTRUCTION PROJECT TO REPLACE MSIC EXPLOSIVE ORDNANCE EXPLOITATION (EOE) COMPLEX | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company | 12000000 | 12003435.59 | 2012-07-20 |  | 2013-01-20 |  | 15 |  | Approp. - $12,000; Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Roof installation on Pods A and D, utility installation, pad preparation for Pods E and F. Pad for Pod F is complete. All underground utilities are complted. Completion date extended dut to weather delays.
2013-04-15 | 2010 | DIA | Major Construction | KR | KOREA | K16 AIR FIELD | DIA10-001 | FOB-K RENOVATION OF TWO BUILDING TO INCLUDE ADMINISTRATIVE AND SCIF SPACE | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd | 4360 | 5050 | 2012-04-09 |  | 2013-10-09 | 2013-10-09 | 15 |  | Reprogramming action completed and MIPR HHM402-2-0273 for $690K added to current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Installing duct work, sprinklers, rigid steel conduits and metal studs. R foil installation on-going in Building 604. Off-shore secure shipping container will arrive May 31, 20313.
2013-04-15 | 2011 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA11-002 | JBAB PAVING OF GRAVEL PARKING LOT | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture | 2984 | 2819 | 2011-07-20 | 2012-07-25 | 2012-07-18 | 2012-07-25 | 99 | 700000 | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012, minor punchlist items have been identified. Final re-seeding of the landscape occurred in mid-October. Interim DD form 1354 issues, awaiting final fiscal closeouts.
2013-04-15 | 2012 | DIA | Minor Construction | VA | VIRGINIA | JUIAF | DIA12000005 | CONSTRUCTION OF REMOTE DELIVERY FACILITY (RDF) MEETING SCIF STANDARDS |  |  |  | 0 | 6058 | [6 empty] | Approp. - $10,758; Site Selected. Working with USACE on requirements. CAT I Reimbursable acceptance recieveded on 12-17-2012. 65% design review meeting held 23 April 2013. Final design expected 16 May 2013.
2013-04-15 | 2012 | DIA | Major Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000001 | DIAC PARKING GARAGE REPLACEMENT |  |  |  | 0 | 793 | [6 empty] | Approp. - $13,645 - Planning and Design (P&D) & Construction MIPRs were both sent to the Navy; P&D MIPR accepted, still pending construction MIPR acceptance. The Design Directive was forwarded to the Navy end of May; Navy confirmed receipt and is currently working on the design. $793,156 CAT I obligated. Working with JBAB on siting approval. NAVAC Gold Team is working to award the A/E contract mid-May.
2013-04-15 | 2012 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000003 | DIAC CHILLED WATER PROJECT FOR DATA CENTER |  |  |  | 0 | 0 | [6 empty] | Approp. - $1,121 - Planning and Design (P&D) MIPR was sent to the Navy and has been accepted. The Construction MIPR has been accepted. The Design Directive was forwarded to the Navy end of June; Navy confirmed receipt. NAVFAC awarded the design contract 30 Jan 2013. A-E firm conducted extensive site survey on 5 March 2013 and follow on site surveys on 13/14 March 2013. Awaiting 35% design.
2013-04-15 | 2012 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000003 | DIAC COOLING TOWER FOR DATA CENTER |  |  |  | 0 | 0 | [6 empty] | Approp. - $941 - Planning and Design (P&D) MIPR was sent to the Navy and has been accepted. The Construction MIPR has also been accepted. The Design Directive was forwarded to the Navy end of June; Navy confirmed receipt and is scheduling meetings with our Project Management Team.A-E firm conducted extensive site survey on 5 March 2013 and follow on site surveys on 13/14 March 2013. Awaiting 35% design.
2013-04-15 | 2012 | DIA | Minor Construction | DC | DISTRICT OF COLUMBIA | DIAC | DIA12000002 | UNINTERRUPTED POWER SUPPLY (UPS) FOR DATA CENTER |  |  |  | 0 | 1200 | [6 empty] | Approp. - $1,076 - Planning and Design (P&D) and Construction MIPR's was sent to the Navy; still pending MIPR acceptance. The Design Directive was fowarded to the Navy end of June; Navy confirmed receipt. NAVFAC and DAL conducted On Site Visit 11 October 2012.NAVFAC awarded design contract on 30 January 2013. 35% due 10 May 2013.
2013-04-15 | 2012 | DIA | Minor Construction | AL | ALABAMA | MSIC, REDSTONE ARSENAL |  | CHILLER PLANT OPTIMIZATION | [11 empty] | Approp. $1,200 - MIPR sent and accepted by Huntsville COE in August 2012, however existing contract vehicle reached its ceiling, therefore a new contract vehicle had to be awarded. Project solicitation issued, pre-bi walk-thru held 26 Feb 2013, proplsals recieved were too high. Project resoliciation expected 10 May 2013, award expected in June.
2013-04-15 | 2009 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010154 | Multi Purpose Machine Gun Range | 2009-04-28 | 2009-05-05 | HDH General Contractors, Inc. | 2704000 | 1636116.62 | 2008-12-01 | 2011-07-19 | 2011-11-16 | 2011-11-16 | 95 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | AK | ALASKA | Bethel | 020123 | Readiness Center | 2009-08-17 | 2009-09-01 | USPFO - AK | 15668000 | 13754358 |  | 2011-10-20 | 2011-03-18 | 2011-03-18 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | AZ | ARIZONA | Camp Navajo | 040014 | Readiness Center | 2009-09-01 | 2009-09-18 | Smith Construction Management, LLC | 11780000 | 7592484.42 | 2009-02-01 | 2011-09-19 | 2011-02-21 | 2011-02-21 | 100 | 0 | Grow the Army PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | AZ | ARIZONA | Florence | 040170 | Readiness Center | 2009-08-18 | 2009-08-21 | The Benham Companies, LLC | 12360000 | 7534991.58 | 2008-11-01 | 2012-12-10 | 2011-02-07 | 2011-02-07 | 100 | 0 | Grow the Army PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | AZ | ARIZONA | Papago Park | 040226 | Readiness Center | 2009-09-01 | 2009-09-02 | SDVO Constructors, LP | 21620000 | 14115026.93 | 2008-11-01 | 1 Jul 11 | 2011-04-01 | 2011-04-01 | 100 | 0 | Grow the Army PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | AR | ARKANSAS | Cabot | 050167 | Readiness Center | 2009-09-14 | 2009-09-14 | Nabholz Construction | 10868000 | 10139505.37 |  | 2011-04-05 | 2011-04-01 | 2011-04-01 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | CO | COLORADO | Fort Lupton | 080203 | Readiness Center | 2009-08-31 | 2009-09-10 | GH Phipps Construction Companies | 8920000 | 8330742.03 | 2008-12-01 | 2011-05-20 | 2011-03-20 | 2011-03-20 | 100 | 0 | Grow the Army PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | CO | COLORADO | Grand Junction | 080204 | Readiness Center | 2010-09-21 | 2010-09-22 | FCI Constructors | 9000000 | 8159279.48 | 2009-06-01 | 2011-09-23 | 2011-09-20 | 2011-09-20 | 100 | 0 | Grow the Army PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | CO | COLORADO | Centennial | 080560 | Mailroon and Plaza Reconfiguration | 2010-06-29 | 2010-09-10 | A&P Contracting | 1277000 | 1307577.85 |  |  | 2011-06-01 | 2011-06-01 | 0 | 0 | Used FY10 funds
2013-04-15 | 2009 | Army National Guard | Major Construction | CT | CONNECTICUT | East Haven | 090044 | KD Range, Add/Alt | 2009-05-25 | 2009-06-08 | Enfield Builders, Inc. | 12756000 | 9837295.07 | 2009-05-01 | 2011-08-01 | 2010-04-05 | 2010-04-05 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | CT | CONNECTICUT | Camp Rell | 090047 | Regional Training Institute | 2009-02-19 | 2009-02-19 | The Fusco Corporation | 28000000 | 27526508 | 2008-10-01 | 2011-11-01 | 2011-09-06 | 2011-09-06 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | DE | DELAWARE | New Castle | 100046 | Army Aviation Support Facility, Add/Alt | 2009-07-06 | 2009-07-15 | Wohlsen Construction Company | 27037000 | 23288221.04 | 2009-03-01 | 2011-06-01 | 2010-12-27 | 2010-12-27 | 95 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120164 | Ammunition Supply Point | 2009-09-01 | 2009-09-02 | McCorkle Construction Company | 11574000 | 8344966.26 | 2009-01-01 | N/A | 2010-09-20 | 2010-09-20 | 95 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120191 | Regional Training Institute, PH 4 | 2009-06-25 | 2009-07-07 | The Tower Group | 20557000 | 18060266.8 |  | 2011-01-31 | 2010-07-23 | 2010-07-23 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | GA | GEORGIA | Marietta | 130109 | Armed Forces Reserve Center | 2009-09-09 | 2009-09-09 | New South Construction Company, Inc. | 28830000 | 27900485.75 | 2008-11-01 | 2011-11-01 | 2011-04-11 | 2011-04-11 | 95 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | ID | IDAHO | Orchard Training Area | 160115 | Live Fire Shoot House | 2009-02-19 | 2009-02-23 | TRS Range Services | 1850000 | 1849611.13 | 2009-05-01 | 2010-04-29 | 2010-02-22 | 2010-02-22 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | ID | IDAHO | Boise | 160119 | RCOE Operations and Maintenance Building | 2008-11-18 | 2009-03-03 | PSI | 1710000 | 1635000 |  |  |  |  | 0 | 0
2013-04-15 | 2009 | Army National Guard | Major Construction | IL | ILLINOIS | Urbana | 170614 | Readiness Center | 2009-09-02 | 2009-09-18 | Capital Development Board | 15762000 | 13930566.66 |  | 2012-12-31 | 2011-03-07 | 2011-03-07 | 95 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180114 | Multipurpose Machine Gun Range | 2011-09-16 | 2011-09-21 | Bruns-Gutzwiller Inc. | 5800000 | 5346367.77 | 2009-04-01 | 2013-05-01 | 2012-09-21 | 2012-09-21 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | IN | INDIANA | Lawrence | 180116 | Readiness Center | 2009-05-11 | 2009-05-19 | Shiel Sexton Company, Inc. | 19254000 | 15325453.33 | 2009-02-01 | 2011-04-18 | 2010-09-01 | 2010-09-01 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | IN | INDIANA | Muscatatuck | 180137 | Combined Arms Collective Training Facility, PH I | 2009-09-22 | 2009-09-23 | DV Contracting, LLC | 5927000 | 5416969.39 | 2011-12-09 | 2011-06-07 | 2010-10-25 | 2010-10-25 | 100 | 0 | Congressional Add PL 111-117 Rescission (NGB 593)
2013-04-15 | 2009 | Army National Guard | Major Construction | IA | IOWA | Davenport | 190136 | Readiness Center, Add/Alt | 2009-08-04 | 2009-08-06 | Russell Construction Co., Inc. | 1550000 | 1498050.66 |  | 2010-10-18 | 2010-04-20 | 2010-04-20 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | IA | IOWA | Mount Pleasant | 190146 | Readiness Center, Add/Alt | 2009-09-10 | 2009-09-11 | Woodruff Construction Co. | 1500000 | 1870716 |  | 2010-11-08 | 2010-12-01 | 2010-12-01 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | IA | IOWA | Camp Dodge | 190150 | MOUT Site, Add/Alt | 2009-09-24 | 2009-09-25 | Pinnacle Construction Group | 1351000 | 820644.01 |  | 2011-01-18 | 2010-01-18 | 2010-01-18 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | KY | KENTUCKY | London | 210290 | Aviation Operations Facility, PH 3 | 2009-09-18 | 2009-09-18 | D.W. Milburn | 6845000 | 6821902.03 |  | 2011-04-27 | 2010-08-14 | 2010-08-14 | 95 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | LA | LOUISIANA | Camp Minden | 220154 | Regional Training Institute, PH I | 2009-09-01 | 2009-09-02 | McInnis Brothers Construction, Inc. | 23875000 | 24722216.63 |  | 2011-05-30 | 2010-05-27 | 2010-05-27 | 100 | 0 | Emerging Requirement
2013-04-15 | 2009 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230070 | Regional Training Institute, PH 1 | 2009-04-08 | 2009-04-16 | Nickerson & O'Day, Inc. | 18813000 | 14313529.52 | 2009-02-01 | 2011-06-13 | 2011-06-13 | 2011-06-13 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MD | MARYLAND | Salisbury | 240031 | Readiness Center, Add/Alt | 2010-05-17 | 2010-05-21 | Nason Construction Company, Inc. | 8800000 | 7135789.36 | 2009-06-01 | 2012-03-07 | 2012-03-07 | 2012-03-07 | 95 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MD | MARYLAND | Edgewood | 240189 | Army Aviation Support Facility, Add/Alt | 2009-05-05 | 2009-09-28 | Tetra-Tech Facilities Construction, LLC | 27627000 | 27168439.57 | 2009-03-01 | 5 Jan 13 | 2010-09-27 | 2010-09-27 | 95 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Methuen | 250106 | Readiness Center, Add/Alt (ADRS) | 2009-06-03 | 2009-06-05 | JK Scanlan Company, Inc. | 19101000 | 11505953 | 2008-11-01 | 2011-04-01 | 2011-11-16 | 2011-11-16 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260180 | Barracks Replacement, PH 1 | 2009-07-31 | 2009-08-06 | Hallmark Construction, Inc. | 16943000 | 17125496.12 |  | 2011-03-31 | 2011-10-07 | 2011-10-07 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260210 | Live Fire Shoot House | 2009-08-19 | 2009-09-01 | Graham Construction, Inc. | 1959000 | 1784914.04 |  | 2010-07-01 | 2010-07-21 | 2010-07-21 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260211 | Urban Assault Course | 2009-08-19 | 2009-09-01 | Beckering Advisor, Inc. | 1882000 | 1451840.8 |  | 2010-09-15 | 2010-06-18 | 2010-06-18 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260212 | Infantry Squad Battle Course | 2009-08-19 | 2009-09-02 | The Garrison Company | 2000000 | 2116999.7 |  | 2010-06-30 | 2010-05-18 | 2010-05-18 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270260 | Readiness Center | 2009-08-04 | 2009-08-07 | Holte/Graham, JV | 13413000 | 12528763.58 | 2009-02-01 | 2012-05-01 | 2010-12-14 | 2010-12-14 | 95 | 0 | Grow the Army PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | MO | MISSOURI | Springfield | 290107 | AVCRAD, PH 2 | 2009-08-26 | 2009-09-01 | Walton Construction Company, LLC | 51829000 | 36357670.77 |  | 2011-07-13 | 2011-05-23 | 2011-05-23 | 95 | 0 | Emerging Requirement
2013-04-15 | 2009 | Army National Guard | Major Construction | NV | NEVADA | Elko | 320069 | Readiness Center | 2011-10-27 | 2012-06-01 | Nevada State Public Works | 11375000 | 7669997.45 |  | 2013-04-30 | 2013-07-12 | 2013-07-12 | 10 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | NV | NEVADA | North NV Militay Depot (Carson City) | 320152 | Paint Booth | 2009-06-04 | 2009-09-01 | Nevada State Public Works | 1500000 | 1074962.56 |  |  |  |  | 0 | 0 | Congressionally Directed
2013-04-15 | 2009 | Army National Guard | Minor Construction | NJ | NEW JERSEY | Sea Girt | 340701 | Water System Replacement |  | 2010-02-18 | Mark Woszcak Mechanical Contractors, Inc. | 1116000 | 1330412 |  |  | 2011-05-28 | 2011-05-28 | 0 | 0
2013-04-15 | 2009 | Army National Guard | Major Construction | NY | NEW YORK | Fort Drum | 360191 | Maneuver Area Training and Equipment Site, PH 3 | 2009-09-04 | 2009-09-30 | Beardsley Design Associates | 10924000 | 9497979 | 2009-04-01 | 2011-06-15 | 2010-07-26 | 2010-07-26 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | NY | NEW YORK | Queensbury | 360193 | Field Maintenance Shop | 2009-03-19 | 2009-03-23 | BCI Construction Corporation | 5590000 | 4816825.09 | 2009-03-01 | 2010-11-15 | 2010-10-15 | 2010-10-15 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | ND | NORTH DAKOTA | Fargo | 380095 | Readiness Center Unit Storage Building | 2009-01-05 | 2009-09-01 | Roers' Contruction Inc. | 1943000 | 1018898.95 |  |  | 2010-10-30 | 2010-10-30 | 0 | 0
2013-04-15 | 2009 | Army National Guard | Major Construction | OH | OHIO | Camp Perry | 390257 | Barracks | 2009-07-29 | 2009-08-06 | Studer-Obringer, Inc. | 1916000 | 1645633.64 | 2009-11-02 | 2010-12-27 | 2010-06-01 | 2010-06-01 | 100 | 0 | Congressional Add PL 111-117 Rescission (NGB 593)
2013-04-15 | 2009 | Army National Guard | Major Construction | OH | OHIO | Ravenna | 390264 | Barracks | 2009-09-11 | 2009-09-11 | QBS Inc. | 1985000 | 1838000 |  | 2011-03-03 | 2010-09-01 | 2010-09-01 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | OH | OHIO | Newton Falls | 390270 | Ravenna TTB Utilities | 2009-12-15 | 2010-01-28 | Portage County Water Resources Department | 1600000 | 1600000 |  |  |  |  | 100 | 0
2013-04-15 | 2009 | Army National Guard | Major Construction | PA | PENNSYLVANIA | Honesdale | 420511 | Readiness Center, Add/Alt | 2011-08-31 | 2011-09-15 | Lobar Incorporated | 6117000 | 5462543.21 |  | under construction | 2012-09-30 | 2012-09-30 | 60 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | RI | RHODE ISLAND | North Kingstown | 440039 | Army Aviation Support Facility (additional funds for FY08 project) | 2008-12-01 | 2008-12-09 | Bacon Construction Co., Inc. | 4863000 | 4150000 |  | 2010-06-25 | 2010-02-12 | 2010-02-12 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Eastover | 450115 | Joint Forces Headquarters | 2009-09-24 | 2009-09-24 | Ikhana-Choate | 26401000 | 28331540.06 | 2009-04-01 | 2012-04-18 | 2011-09-28 | 2011-09-28 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Florence | 450185 | Field Maintenance Shop, PH I | 2010-11-01 | 2010-12-09 | FBI Construction, Inc. | 4600000 | 3716588.75 |  | 2012-07-04 | 2011-12-21 | 2011-12-21 | 95 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Anderson | 450218 | Readiness Center | 2009-08-27 | 2009-09-09 | C. Marshall Carithers | 11010000 | 9867298.85 | 2009-03-01 | 2012-03-30 | 2011-04-18 | 2011-04-18 | 95 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Beaufort | 450367 | Readiness Center, Add/Alt | 2009-08-25 | 2009-09-01 | Summerfield Associates, Inc. | 3157000 | 2308193.47 | 2008-11-01 | 2010-09-30 | 2010-09-20 | 2010-09-20 | 95 | 0 | Grow the Army PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Rapid City | 460077 | Armed Forces Reserve Center | 2009-03-31 | 2009-04-17 | J Scull Construction | 28793000 | 27821891.07 | 2008-11-01 | 2011-06-24 | 2011-11-14 | 2011-11-14 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 460132 | Barracks/Dining/Admin & Parking Complex, PH I | 2009-06-11 | 2009-06-24 | J Scull Construction | 12801000 | 11645594.24 |  | 2011-03-02 | 2010-12-15 | 2010-12-15 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | TN | TENNESSEE | Tullahoma | 470043 | Readiness Center | 2009-09-16 | 2009-09-25 | Sain Construction Co. | 8818000 | 7706138.13 |  | 2011-09-15 | 2011-01-21 | 2011-07-05 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | TX | TEXAS | Laredo | 480195 | Readiness Center, Add/Alt | 2009-11-10 | 2010-04-22 | CG Construction, Inc. | 1165000 | 809473.45 |  |  | 2011-07-12 | 2011-07-12 | 100 | 0 | Congressionally Directed
2013-04-15 | 2009 | Army National Guard | Major Construction | UT | UTAH | Camp HG Williams | 490101 | Ammunition Supply Point | 2009-09-17 | 2009-09-18 | Creative Times Inc. | 13901000 | 12044859.22 | 2008-11-01 | 2011-07-30 | 2010-10-01 | 2010-10-01 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | UT | UTAH | American Fork | 490903 | Readiness Center Structural Upgrade | 2009-08-26 | 2009-09-18 | Interwest Construction Company, Inc. | 1424000 | 676976.64 |  |  | 2010-07-30 | 2010-12-26 | 0 | 0
2013-04-15 | 2009 | Army National Guard | Minor Construction | UT | UTAH | Price | 490904 | Readiness Center Structural Upgrade | 2009-08-26 | 2009-10-14 | Bud Mahas Construction, Inc. | 2156000 | 757942.09 |  |  | 2010-08-31 | 2010-08-31 | 0 | 0
2013-04-15 | 2009 | Army National Guard | Major Construction | VT | VERMONT | Ethan Allen Firing Range Jericho | 500052 | Readiness Center | 2009-05-12 | 2009-05-15 | E.F. Wall & Associates, Inc. | 9878000 | 8580167 |  | 2010-09-01 | 2010-09-01 | 2010-09-01 | 100 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | VT | VERMONT | Westminister Training Site | 500066 | Westminister Zero Range | 2009-04-17 | 2009-09-24 | Clemons Construction | 1789000 | 1367920 |  |  | 2010-08-01 | 2010-08-01 | 0 | 0 | Congressionally Directed
2013-04-15 | 2009 | Army National Guard | Minor Construction | VT | VERMONT | Colchester | 500072 | Readiness Center, Add/Alt | 2011-08-09 | 2011-08-11 | Stewart Construction | 1909000 | 1862957 |  |  |  |  | 0 | 0
2013-04-15 | 2009 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510148 | Multipurpose Machine Gun Range | 2009-09-24 | 2009-09-25 | US Army Corps Engineers, Norfolk District | 2950000 | 3203496.75 | 2009-04-01 | 2011-04-20 | 2010-06-21 | 2010-06-21 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | VI | VIRGIN ISLAND | Bethlehem Military Compound Christiansted | 520035 | Construct Main Gate | 2009-02-17 | 2009-09-23 | Barlovento, LLC | 1946000 | 2032865 |  |  |  |  | 100 | 0
2013-04-15 | 2009 | Army National Guard | Minor Construction | VI | VIRGIN ISLAND | Bethlehem Military Compound Christiansted | 520036 | Restoration LTC Jackson Armory | 2009-04-14 | 2009-09-23 | K-CON Inc. | 2990000 | 2997901.82 |  |  | 2010-10-31 | 2010-10-31 | 95 | 0
2013-04-15 | 2009 | Army National Guard | Major Construction | WA | WASHINGTON | Fort Lewis (Gray Field) | 530012 | Readiness Center | 2009-09-11 | 2009-09-11 | Wade Perrow Construction, LLC | 30358000 | 24954481.35 | 2009-03-01 | 2011-07-28 | 2011-01-31 | 2011-01-31 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540006 | Shoot House | 2009-09-23 | 2009-09-23 | Renew Resources, Inc. | 2620000 | 2602564.68 |  | under construction | 2010-08-23 | 2010-08-23 | 100 | 0 | Congressional Add PL 111-117 Rescission, Formal Reprogramming funds from FY07 project savings
2013-04-15 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Kingwood | 540105 | Joint Interagency Training Education Center, PH I | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | 77500000 | 68920722.34 |  | under construction | 2011-09-28 | 2011-09-28 | 95 | 0 | Emerging Requirement
2013-04-15 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540205 | Access Control Point | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | 3945000 | 3693718.77 |  | under construction | 2010-09-20 | 2010-09-20 | 95 | 0 | Congressional Add PL 111-117 Rescission, Formal Reprogramming $2,358,000 funds from FY09 project savings {PN: 490101}
2013-04-15 | 2009 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Camp Dawson | 540206 | Multi-Purpose Building, PH II | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | 4755000 | 3911042.51 |  | under construction | 2010-08-26 | 2010-08-26 | 95 | 0 | Congressional Add PL 111-117 Rescission
2013-04-15 | 2009 | Army National Guard | Minor Construction | WV | WEST VIRGINIA | Kenova | 540208 | Tri-State Armory Addition | 2009-04-24 | 2009-09-23 | Neighborgall Construction Company | 2000000 | 2000000 |  |  |  |  | 0 | 0 | Congressionally Directed
2013-04-15 | 2009 | Army National Guard | Major Construction | VA | VIRGINIA | Arlington | 570402 | ARNG Addition, PH II | 2008-09-23 | 2008-11-18 | Tompkins Builders, Inc. | 14516000 | 16459974.37 | 2008-12-01 | 2011-06-30 | 2010-03-15 | 2010-03-15 | 100 | 0 | PL 111-117 Rescission
2013-04-15 | 2010 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010279 | Urban Assault Course | 2010-09-06 | 2010-09-10 | Baggette Construction, Inc. | 3000000 | 2351754 | 2009-12-01 | 2011-10-11 | 2011-08-08 | 2011-08-08 | 95 | 0
2013-04-15 | 2010 | Army National Guard | Minor Construction | AK | ALASKA | Fort Richardson | 020903 | Regional Training Institute, Add/Alt | 2010-05-14 | 2010-09-03 | H. Watt & Scott, Inc. | 1992000 | 1785276 |  |  | 2011-09-30 | 2011-09-30 | 100 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | AZ | ARIZONA | Camp Navajo | 040227 | Combat Pistol Qualification Course | 2010-06-14 | 2010-06-15 | Norquay Construction | 3000000 | 1867492.4 | 2009-12-01 | 2011-07-15 | 2010-12-31 | 2010-12-31 | 100 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | CA | CALIFORNIA | Los Alamitos | 060115 | Readiness Center, PH 1 | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | 20505000 | 21935468.01 | 2010-03-01 | projected for Oct 13 | 2012-02-06 | 2014-04-18 | 0 | 0 | 2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | GA | GEORGIA | Fort Benning | 130077 | Readiness Center | 2010-01-28 | 2010-02-04 | USACOE Louisville District | 10609000 | 8622378.6 | 2009-12-01 | 2011-11-15 | 2011-09-14 | 2011-09-14 | 95 | 0 | Grow the Army/2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | GA | GEORGIA | Hunter AAF | 130112 | Readiness Center | 2010-09-29 | 2010-09-29 | Choice Concrete Construction | 8967000 | 7696026.5 |  | 2011-08-01 | 2012-03-20 | 2012-03-20 | 95 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | GQ | GUAM | Barrigada | 140300 | Readiness Center | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | 20537000 | 20797256 | 2009-11-01 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 95 | 0 | Grow the Army/2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | ID | IDAHO | Gowen Field | 160120 | Combined Arms Collective Training Facility | 2010-04-27 | 2010-05-25 | Performance Systems Inc. | 7824080 | 7773072.34 | 2010-04-01 | 2012-01-31 | 2011-10-04 | 2011-10-04 | 100 | 0 | 2853 Notification
2013-04-15 | 2010 | Army National Guard | Minor Construction | ID | IDAHO | Orchard Range TS, Boise | 160127 | Fixed Tactical Internet Infrastruture | 2011-07-20 | 2011-09-15 | USPFO - Idaho | 1369000 | 1426280.59 |  |  |  |  | 0 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | IL | ILLINOIS | Milan | 170611 | Readiness Center, Add/Alt | 2010-09-17 | 2010-09-22 | Capital Development Board | 5600000 | 4322417.72 |  | 2012-03-31 | 2011-09-14 | 2011-09-14 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | IN | INDIANA | Muscatatuck | 180145 | Combined Arms Collective Training Facility, PH Ib | 2010-04-20 | 2010-04-22 | McKellar Corporation | 10100000 | 7507610.33 | 2010-08-12 | 2011-06-15 | 2010-09-20 | 2010-09-20 | 100 | 0 | (NGB 593)
2013-04-15 | 2010 | Army National Guard | Minor Construction | IA | IOWA | Iowa Falls | 190139 | Readiness Center, Add/Alt | 2010-02-18 | 2010-07-20 | Larson Construction company | 2000000 | 1794105.78 |  |  | 2011-08-30 | 2011-08-30 | 100 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Minor Construction | IA | IOWA | Davenport | 190151 | Army Aviation Support Facility, Add/Alt | 2010-02-18 | 2010-09-20 | Russell Construction Co., Inc. | 2000000 | 1937949.47 |  |  | 2011-11-30 | 2011-11-30 | 100 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Major Construction | IA | IOWA | Johnston (Camp Dodge) | 190154 | FEH Associates, Inc. (USPFO) | 2010-08-10 | 2010-08-16 | SKE International, Inc. | 4000000 | 3981146.73 |  | N/A | 2011-08-15 | 2011-08-15 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Minor Construction | IA | IOWA | Fairfield | 190155 | Field Maintenance Shop, Add/Alt | 2010-02-18 | 2010-09-20 | Jean C. Wiley & Sons, Inc. | 2000000 | 1948912.25 |  |  | 2011-09-06 | 2011-09-06 | 100 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Minor Construction | IA | IOWA | Camp Dodge | 190157 | Motor Vehicle Storage Buildings, Freedom Center | 2010-02-18 | 2010-07-20 | Septagon Construction Co. | 1963000 | 1267240.25 |  |  | 2011-05-01 | 2011-05-01 | 100 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Major Construction | KS | KANSAS | Salina | 200103 | Taxiway Alterations, ARNG AASF | 2010-08-24 | 2010-08-25 | Pavers Inc. | 2227000 | 1988414.86 |  | 2011-04-29 | 2011-07-18 | 2011-07-18 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | KY | KENTUCKY | Owensboro | 210291 | Readiness Center | 2010-06-07 | 2010-08-16 | A & K Construction Company, Inc. | 10500000 | 9957000 |  | 2012-04-14 | 2011-08-28 | 2011-08-28 | 95 | 0 | Programmatic Plus Up
2013-04-15 | 2010 | Army National Guard | Minor Construction | KY | KENTUCKY | London | 210292 | Aviation Operations Facility, Add/Alt, PH IV | 2010-09-07 | 2010-09-24 | Septagon Construction Co. | 1805000 | 1686139.5 |  |  | 2011-11-25 | 2011-11-25 | 100 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Minor Construction | ME | MAINE | Waterville | 230806 | CST Ready Bay Addition | 2011-07-01 | 2011-09-07 | USPFO - Maine | 1927000 | 1124179.73 |  |  |  |  | 0 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230114 | Regional Training Institute, PH II | 2010-08-11 | 2010-08-16 | Nickerson & O'Day, Inc. | 15500000 | 14434438.6 |  | 2012-07-01 | 2011-07-01 | 2011-07-01 | 100 | 0 | Programmatic Plus Up
2013-04-15 | 2010 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Hanscom AFB | 250087 | Armed Forces Reserve Center (JFHQ) | 2010-06-07 | 2010-06-25 | CTA Construction | 29000000 | 25396535.96 | 2010-03-01 | 2012-01-15 | 2011-10-19 | 2011-10-19 | 100 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | MI | MICHIGAN | Fort Custer (Augusta) | 260213 | Organizational Maintenance Shop (ADRS) | 2010-08-04 | 2010-09-22 | LD Dosca Associates, Inc. | 7732000 | 7420434.81 |  | 2012-03-01 | 2011-10-18 | 2011-10-18 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Minor Construction | MI | MICHIGAN | Camp Grayling | 260232 | Dining Facility | 2010-07-09 | 2010-09-24 | Ripman Construction Co., Inc. | 1998000 | 1991296.11 |  |  | 2011-09-30 | 2011-09-30 | 100 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270252 | Urban Assault Course | 2011-07-11 | 2011-08-18 | Saginaw Contracting, Inc. | 1710000 | 1188279.74 | 2010-03-01 | 2012-07-18 | 2013-03-18 | 2013-03-18 | 95 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270261 | Readiness Center, PH 2 | 2010-08-30 | 2010-09-07 | MAVCON | 3183584 | 2855434.49 | 2009-10-01 | Spring 2013 | 2011-07-18 | 2011-07-18 | 95 | 0 | Grow the Army/2853 Notification
2013-04-15 | 2010 | Army National Guard | Minor Construction | MN | MINNESOTA | St. Paul | 270263 | CST, Add/Alt | 2011-08-09 | 2011-08-19 | LS Black Constructors | 1954000 | 1888550.04 |  |  |  |  | 95 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | MS | MISSISSIPPI | Monticello | 280308 | Readiness Center | 2010-09-22 | 2010-09-23 | Mac's Construction Co., Inc. | 8383350 | 8008358 |  | 2012-06-26 | 2012-01-06 | 2012-01-06 | 95 | 0 | Congressional Add/2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280352 | Combined Arms Collective Training Facility, Add/Alt | 2010-04-09 | 2010-04-22 | B. W. Sullivan Building Contractor, Inc. | 7260000 | 7020324 | 2010-01-01 | 2011-11-20 | 2010-08-23 | 2010-08-23 | 95 | 0 | 2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | MO | MISSOURI | Boonville | 290213 | Readiness Center, PH 2 | 2010-04-16 | 2010-04-22 | SIRCAL Contracting | 1800000 | 1011411.5 | 2010-05-01 | 2011-02-17 | 2010-10-18 | 2010-10-18 | 100 | 0 | Grow the Army
2013-04-15 | 2010 | Army National Guard | Minor Construction | MT | MONTANA | Fort Harrison | 300202 | Troop Medical Clinic, Add/Alt | 2010-04-23 | 2010-09-13 | R&R Taylor Construction | 1750000 | 1657794.99 |  |  | 2011-06-30 | 2011-06-30 | 0 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Major Construction | NE | NEBRASKA | Lincoln | 310076 | Armed Forces Reserve Center (JFHQ) | 2010-01-26 | 2010-02-16 | Hausman Construction, Inc. | 23000000 | 21804833.39 | 2010-04-01 | 2012-07-17 | 2011-09-30 | 2011-09-30 | 95 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | NE | NEBRASKA | Mead Training Site | 310122 | Water Supply & Distribution System | 2010-08-23 | 2010-08-25 | Rutjens Construction, Inc. | 2000000 | 1842956.65 | 2010-08-25 | 2011-07-15 | 2011-07-25 | 2011-07-25 | 100 | 0 | Programmatic Plus Up (NGB 593)
2013-04-15 | 2010 | Army National Guard | Major Construction | NV | NEVADA | North Las Vegas | 320143 | Readiness Center | 2010-09-27 | 2010-09-27 | The Penta Building Group | 26000000 | 19822607.28 | 2010-05-01 | 2013-05-01 | 2012-01-23 | 2013-03-23 | 100 | 0 | Grow the Army
2013-04-15 | 2010 | Army National Guard | Major Construction | NV | NEVADA | Carson City | 320197 | Renewable Energy Sustainable Projects | 2010-09-21 | 2010-09-24 | RHP Mechanical Systems (Contractor) | 2000000 | 1917039 |  | 2011-10-26 | 2011-04-04 | 2011-04-04 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | NM | NEW MEXICO | Santa Fe | 350043 | Army Aviation Support Facility | 2010-06-29 | 2010-07-02 | US Army Corps of Engineers | 35700000 | 31834806.4 | 2009-12-01 | 2012-03-20 | 2011-09-14 | 2011-09-14 | 100 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | NC | NORTH CAROLINA | East Flat Rock | 370896 | Readiness Center, Add/Alt | 2010-09-07 | 2010-09-10 | Architectural Design Studio | 2516000 | 2033369.25 |  | 2011-10-13 | 2011-09-30 | 2011-10-17 | 95 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | NC | NORTH CAROLINA | Fort Bragg | 370897 | Tactical UAS Support Facility | 2010-09-10 | 2010-09-27 | J.M. Thompson Co | 2589623 | 2719001.8 |  | 2012-03-02 | 2012-06-08 | 2011-08-15 | 95 | 0 | Congressional Add/2853 Notification
2013-04-15 | 2010 | Army National Guard | Minor Construction | ND | NORTH DAKOTA | Bismarck | 380118 | Raymond J. Bohn Readiness Center, Addition | 2010-04-01 | 2010-09-28 | Associated Builders, Inc. | 2000000 | 1198567.21 |  |  | 2011-12-31 | 2011-12-31 | 0 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Major Construction | ND | NORTH DAKOTA | Camp Grafton | 380119 | Shoreline Stabilization | 2010-02-12 | 2010-03-01 | Ames Construction | 2000000 | 1747147.76 |  | 2010-08-17 | 2011-08-30 | 2011-08-30 | 100 | 0 | Programmatic Plus Up
2013-04-15 | 2010 | Army National Guard | Minor Construction | ND | NORTH DAKOTA | Camp Grafton, Devils Lake | 380120 | Dike Construction | 2010-07-26 | 2010-09-03 | Ames Construction | 1569000 | 1943779.7 |  |  | 2012-08-20 | 2012-08-20 | 0 | 0
2013-04-15 | 2010 | Army National Guard | Minor Construction | OH | OHIO | Beightler | 390261 | Joint Forces Headquarters (JOC), Addition | 2010-02-03 | 2010-08-05 | Elford, Inc. | 2000000 | 1839130.8 |  |  | 2011-07-18 | 2011-07-18 | 100 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Minor Construction | OH | OHIO | Ravenna | 390267 | Shoot House | 2009-12-14 | 2010-09-20 | USPFO - Ohio | 2000000 | 1946920.12 |  |  | 2011-10-25 | 2011-10-25 | 100 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Major Construction | OR | OREGON | Polk County | 410120 | Readiness Center | 2010-09-14 | 2010-09-21 | Lease Crutcher Lewis | 12100000 | 11892715.57 |  | 2012-09-01 | 2012-12-01 | 2012-12-01 | 85 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | OR | OREGON | Clastop County (Warrenton) (Camp Rilea) | 410820 | Water Supply Company | 2010-09-10 | 2010-09-21 | Hoffman Construction Company | 3369000 | 3367999.48 |  | 2011-08-01 | 2011-10-02 | 2011-10-02 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Minor Construction | PA | PENNSYLVANIA | Fort Indiantown Gap | 420507 | CSMS Paint Stripping & Prep Shop | 2010-06-01 | 2010-08-27 | Arthur Funk & Sons, Inc. | 1998000 | 1587766.47 |  |  | 2011-06-01 | 2011-06-01 | 100 | 0
2013-04-15 | 2010 | Army National Guard | Minor Construction | RQ | PUERTO RICO | Camp Santiago | 436019 | Urban Assault Course | 2009-12-01 | 2010-09-29 | Remex Co. | 1669000 | 1845996.46 |  |  |  |  | 95 | 0 | Congressionally Directed
2013-04-15 | 2010 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Eastover | 450252 | Army Aviation Support Facility, Add/Alt | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. | 14758680 | 14078418 | 2010-01-01 | 2011-12-14 | 2011-12-14 | 2011-12-14 | 95 | 0 | 2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Greenville | 450353 | Army Aviation Support Facility | 2010-09-23 | 2010-09-24 | Hendrick Construction | 27935984 | 27303538 | 2009-12-01 | 2012-08-10 | 2012-08-10 | 2012-08-10 | 95 | 0 | 2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 460141 | Joint Force HQ Readiness Center Supplemental | 2010-08-26 | 2010-09-03 | J. Scull Construction Services, Inc. | 5705000 | 5270893.64 |  | 2012-04-14 | 2012-04-14 | 2012-04-14 | 100 | 0 | Congressional Add/2853 Notification
2013-04-15 | 2010 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Camp Rapid | 461536 | Troop Medical Clinic, Add/Alt | 2010-09-01 | 2010-09-07 | J. Scull Construction Services, Inc. | 1950000 | 1723490.87 |  | 2011-05-23 | 2011-05-01 | 2011-05-01 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | TX | TEXAS | Austin-Bergstrom Airport | 480175 | Armed Forces Reserve Center | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | 16500000 | 13801269.95 | 2009-12-01 | 2012-07-17 | 2012-06-15 | 2012-06-15 | 95 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | TX | TEXAS | Austin-Bergstrom Airport | 480176 | Field Maintenance Shop, Joint | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | 5700000 | 6829724.93 | 2009-12-01 | 2012-07-17 | 2012-06-15 | 2012-06-15 | 95 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | VT | VERMONT | Ethan Allen Firing Range | 500071 | Bachelor Officer Quarters additions and improvement | 2010-09-14 | 2010-09-20 | Summit/Catamount Construction | 1996000 | 2163551 |  | 2011-06-30 | 2011-08-15 | 2011-08-15 | 100 | 0 | Congressional Add
2013-04-15 | 2010 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510302 | Regional Training Institute, PH 2 | 2010-01-27 | 2010-02-26 | Barton Marlow Company | 32000000 | 30249051.23 | 2009-12-01 | 2008-07-27 | 2011-02-07 | 2011-02-07 | 95 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | VI | VIRGIN ISLAND | St. Croix | 520014 | Regional Training Institute, PH 1 | 2010-04-12 | 2010-04-23 | Tiptop Construction | 20000000 | 19493319.3 | 2010-01-01 | 2012-06-20 | 2011-03-07 | 2012-06-20 | 95 | 0
2013-04-15 | 2010 | Army National Guard | Minor Construction | WA | WASHINGTON | Camp Murray | 530033 | Entrance Gate w/Access Control Buildings | 2011-09-15 | 2011-09-19 | Berschauer Construction | 2994000 | 2994000 |  |  |  |  | 0 | 0
2013-04-15 | 2010 | Army National Guard | Major Construction | WV | WEST VIRGINIA | St. Albans | 540217 | Readiness Center Addition/Life Safety Upgrades | 2010-09-24 | 2010-09-26 | Hayslett Construction Company | 2000000 | 1135206.62 |  | 2011-10-21 | 2011-09-18 | 2011-09-18 | 95 | 0 | Congressional Add
2013-04-15 | 2011 | Army National Guard | Major Construction | AZ | ARIZONA | Florence | 040023 | Readiness Center | 2011-08-01 | 2011-09-01 | Haydon Building Corporation-Tem | 16467000 | 15814116.49 | 2010-10-01 | 2012-12-10 | 2012-12-14 | 2012-12-14 | 80 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | AK | ARKANSAS | Camp Robinson | 050043 | Combined Support Maintenance Shop | 2011-06-24 | 2011-07-01 | CDI Contractors, LLC | 29940000 | 28273500 | 2010-11-01 | 2013-08-01 | 2013-07-01 | 2013-07-01 | 32 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | AK | ARKANSAS | Fort Chaffee | 050163 | Combined Arms Collective Training Facility | 2010-12-21 | 2011-05-23 | Crossland Construction Company, Inc. | 8857560 | 7412601 | 2010-12-01 | 2013-03-01 | 2012-03-23 | 2012-03-23 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission/2853 Notification
2013-04-15 | 2011 | Army National Guard | Major Construction | AK | ARKANSAS | Fort Chaffee | 050173 | Live Fire Shoot House | 2011-05-26 | 2011-06-14 | Ross Sparks Builders, Inc. | 2495000 | 2266871.38 |  | 2012-09-18 | 2012-06-07 | 2012-06-07 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060429 | Combined Arms Collective Training Facility | 2011-05-12 | 2011-09-20 | Cox Construction Company | 12379000 | 11452201.7 | 2010-12-01 | projected for Aug 13 | 2012-06-29 | 2012-06-29 | 100 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission/2853 Notification
2013-04-15 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Gypsum/Eagle | 080062 | HAATS/AASF | 2011-05-19 | 2011-07-13 | Hensel Phelps Construction Company | 38922000 | 36353779.05 | 2010-11-01 | 2013-04-01 | 2013-03-31 | 2013-03-31 | 40 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Fort Carson | 080067 | Regional Training Institute | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC | 49220000 | 42218396 | 2010-10-01 | 2013-10-01 | 2013-10-18 | 2013-10-18 | 35 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission. Informal Reprogramming $2,293,000 Formal Reprogramming $9,300,000 funds from FY10 project savings {PNs: 160120, ($6,000.00) & 350043 ($3,300.00)}
2013-04-15 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Colorado Springs | 080201 | Readiness Center | 2011-08-12 | 2011-09-16 | Pahl Architecture | 19960000 | 18501666.33 | 2010-12-01 | 2013-10-01 | 2013-09-30 | 2013-09-30 | 10 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | CO | COLORADO | Windsor | 080202 | Readiness Center | 2011-08-05 | 2011-08-16 | AP Mountain States | 7485000 | 7472624.83 | 2010-12-01 | 2012-09-01 | 2012-10-19 | 2012-10-19 | 95 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | CT | CONNECTICUT | Windsor Locks | 090010 | Readiness Center (Aviation) | 2011-05-27 | 2011-09-22 | USPFO - CT | 40918000 | 31484477 | 2010-11-01 |  | 2012-10-16 | 2012-10-16 | 55 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | DE | DELAWARE | New Castle | 100037 | Armed Forces Reserve Center (JFHQ) | 2011-08-03 | 2011-08-18 | Vigil Contracting, Inc. | 26946000 | 24954530.43 | 2010-12-01 | under construction | 2012-04-27 | 2012-04-27 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | GA | GEORGIA | Dobbins | 130123 | Readiness Center, Add/Alt | 2011-05-17 | 2012-04-17 | TEPA | 10379000 | 9865655.77 | 2011-01-01 | under construction / 30 Sep 13 | 2013-09-30 | 2013-09-30 | 10 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | GA | GEORGIA | Cumming | 130127 | Readiness Center | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 16966000 | 16347179.71 | 2010-12-01 | 2013-05-15 | 2012-11-16 | 2012-11-16 | 85 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | GQ | GUAM | Barrigada | 140001 | Combined Support Maintenance Shop, Ph 1 | 2011-05-31 | 2011-09-01 | NAVFAC Pacific | 18962000 | 19150383.04 | 2011-05-01 | 2013-04-19 | 2012-04-20 | 2012-04-20 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | HI | HAWAII | Kalaeloa | 150077 | Combined Support Maintenance Shop, Ph 2A | 2011-08-11 | 2011-12-29 | BCP Construction of Hawaii, Inc. | 37924000 | 35805957.95 | 2011-03-01 | 2013-08-18 | 2012-11-16 | 2012-11-16 | 80 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | ID | IDAHO | Gowen Field | 160093 | Barracks (ORTC), Ph 1 | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | 12969000 | 13337492.58 | 2010-12-01 | 2013-03-16 | 2013-02-28 | 2013-02-28 | 45 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission/2853 Notification
2013-04-15 | 2011 | Army National Guard | Major Construction | ID | IDAHO | Mountain Home | 160122 | Tactical Unmanned Aircraft System Facility | 2011-05-23 | 2011-08-02 | Construction Inc, Moutain Home | 6287000 | 5475779.24 | 2010-12-01 | 2013-02-23 | 2013-02-22 | 2013-02-22 | 40 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | IL | ILLINOIS | Springfield | 179237 | Combined Support Maintenance Shop, Add/Alt | 2011-09-15 | 2011-09-20 | CORE Construction | 14970000 | 14447600 | 2010-12-01 | 2013-05-31 | 2012-10-05 | 2012-10-05 | 85 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | KS | KANSAS | Wichita East | 200063 | Readiness Center | 2011-07-15 | 2011-08-11 | Straub Construction Co., Inc. | 26283000 | 24235376.19 | 2011-04-01 | 2013-03-12 | 2012-12-07 | 2012-12-07 | 75 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission/2853 Notification
2013-04-15 | 2011 | Army National Guard | Major Construction | KS | KANSAS | Wichita | 200090 | Field Maintenance Shop | 2011-09-01 | 2011-09-28 | The Law Company, Inc. | 13243800 | 12144967.58 | 2010-12-01 | 2013-08-18 | 2012-10-19 | 2012-10-19 | 10 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission/2853 Notification
2013-04-15 | 2011 | Army National Guard | Major Construction | KY | KENTUCKY | Burlington | 210034 | Readiness Center | 2011-08-31 | 2011-09-16 | DW Wilburn | 19461000 | 18638127 | 2010-12-01 | 2013-01-30 | 2013-03-01 | 2013-01-30 | 10 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | LA | LOUISIANA | Minden | 220114 | Readiness Center | 2011-06-23 | 2011-08-08 | Walton Construction Co., LLC. | 19307000 | 20389625.23 | 2011-02-01 | 2013-03-18 | 2013-01-14 | 2013-01-14 | 30 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission/2853 Notification
2013-04-15 | 2011 | Army National Guard | Major Construction | LA | LOUISIANA | Fort Polk | 220222 | Tactical Unmanned Aircraft System Facility | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company | 5489000 | 4887784.27 | 2011-08-01 | 2012-10-08 | 2012-07-30 | 2012-07-30 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | MD | MARYLAND | Webster Field, St Inigoes | 240186 | Tactical Unmanned Aircraft System Facility | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | 5489000 | 5199924 | 2011-06-01 | under construction | 2012-06-15 | 2013-06-28 | 35 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Hanscom AFB | 250136 | Armed Forces Reserve Center (JFHQ), Ph 2 | 2011-09-15 | 2011-09-22 | Nauset Construction Corp | 22954000 | 22140868.98 | 2010-12-01 |  | 2012-10-27 | 2012-10-27 | 80 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | MI | MICHIGAN | Camp Grayling | 260207 | Combined Arms Collective Training Facility | 2011-06-22 | 2011-08-18 | Saylor-Beall Manufacturing Company | 18962000 | 13795083.02 | 2011-02-01 | 2012-03-09 | 2012-03-09 | 2012-03-09 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270096 | Infantry Squad Battle Course | 2011-06-28 | 2011-07-01 | Eagle Construction Company, Inc. | 4291000 | 2231974.6 | 2010-11-01 | 2012-10-30 | 2012-07-06 | 2012-07-06 | 100 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission - Closed
2013-04-15 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Arden Hills | 270202 | Field Maintenance Shop | 2011-07-19 | 2011-08-08 | Stahl Construction Company | 28942000 | 26258147.88 | 2011-01-01 | 18 Apr 13 (estimated) | 2013-01-18 | 2013-01-18 | 15 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270267 | Tactical Unmanned Aircraft System Facility | 2011-07-21 | 2011-08-08 | Donlar Construction Company | 4441000 | 3548418 | 2010-12-01 | 2012-10-26 | 2012-10-26 | 2012-10-26 | 90 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | NE | NEBRASKA | Mead | 310107 | Readiness Center | 2011-06-15 | 2011-07-12 | The Weitz Company, LLC | 11377000 | 11088282 | 2011-03-01 | 2012-09-15 | 2012-10-12 | 2012-04-27 | 95 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | NE | NEBRASKA | Lincoln | 310110 | Readiness Center, Add/Alt | 2011-08-16 | 2011-08-19 | Kingery Construction Company | 3293000 | 3295098.59 | 2010-11-01 | 2012-10-15 | 2012-08-20 | 2012-11-07 | 80 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | NH | NEW HAMPSHIRE | Pembroke | 330034 | Classroom Facility (Regional Training Institute) | 2011-05-09 | 2011-08-25 | TLT Construction Corp. | 20958000 | 14113265.69 | 2010-11-01 |  | 2012-09-21 | 2012-09-21 | 100 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | NH | NEW HAMPSHIRE | Pembroke | 330035 | Barracks Facility (Regional Training Institute) | 2011-05-09 | 2011-08-26 | TLT Construction Corp | 14970000 | 12098806.21 | 2010-12-01 |  | 2012-09-21 | 2012-09-21 | 100 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | NM | NEW MEXICO | Farmington | 350075 | Readiness Center, Add/Alt | 2011-04-19 | 2011-09-29 | Jaynes Corporation | 8483000 | 10292037.78 | 2010-12-01 | 2012-12-25 | 2012-10-31 | 2012-10-31 | 95 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | NC | NORTH CAROLINA | High Point | 370898 | Readiness Center, Add/Alt | 2011-09-08 | 2011-09-15 | Holden Building Company, Inc. | 1548672 | 1590022.94 | 2010-11-01 | 2012-08-01 | 2012-10-26 | 2012-10-26 | 95 | 0 | Grow the Army, PL 112-10 SEC 1119 (a) 0.2% Recission, On PBAS Report shows Reprogramming
2013-04-15 | 2011 | Army National Guard | Major Construction | ND | NORTH DAKOTA | Camp Grafton | 380014 | Readiness Center, Add/Alt | 2011-06-15 | 2011-07-19 | Comstock Construction, Inc. | 11178000 | 11742926.68 | 2011-01-01 | 2012-08-04 | 2012-07-15 | 2012-07-15 | 100 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Minor Construction | ND | NORTH DAKOTA | Camp Grafton, Devils Lake | 380121 | Levee Pump Station | 2011-09-22 | 2011-10-11 | Swanberg Construction, Inc. | 1695000 | 1928576.85 |  |  | 2012-12-15 | 2012-12-15 | 0 | 0 | Used FY11 funds
2013-04-15 | 2011 | Army National Guard | Major Construction | RQ | PUERTO RICO | Camp Santiago | 436023 | Live Fire Shoot House | 2011-07-21 | 2011-09-22 | Remex | 3094000 | 2544174.56 | 2010-11-01 | 2012-09-18 | 2012-12-14 | 2012-12-14 | 65 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | RI | RHODE ISLAND | East Greenwich | 440009 | United States Property and Fiscal Office | 2011-08-25 | 2011-09-30 | USPFO - RI, Purchasing & Contracting | 26946000 | 20702565 | 2010-12-01 |  | 2012-10-24 | 2012-10-24 | 85 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | SD | SOUTH DAKOTA | Watertown | 460085 | Readiness Center | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. | 18225100 | 17556129.36 | 2010-11-01 | 2013-03-01 | 2013-01-14 | 2013-01-14 | 25 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission/2853 Notification
2013-04-15 | 2011 | Army National Guard | Major Construction | TX | TEXAS | Camp Maxey | 480267 | Combat Pistol/Military Pistol Qualification Course | 2011-04-06 | 2011-09-12 | Unified Services of Texas, Inc. | 2495000 | 1936863.29 | 2010-12-01 | 2012-09-28 | 2012-03-31 | 2012-03-31 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | TX | TEXAS | Camp Swift | 480290 | Urban Assault Course | 2011-08-25 | 2011-09-12 | Gaeke Construction Co., Inc. | 2595000 | 2142293.8 | 2010-11-01 | 2012-09-27 | 2012-08-20 | 2012-08-20 | 95 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | VI | VIRGIN ISLAND | St. Croix | 520034 | Readiness Center (JFHQ) | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | 24950000 | 21792220.75 | 2010-11-01 | under construction / Nov 13 | 2013-11-01 | 2013-11-01 | 10 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | WA | WASHINGTON | Tacoma | 530022 | Combined Support Maintenance Shop | 2011-06-07 | 2011-06-23 | Walsh Construction Co, II, LLC | 24950000 | 22826782 | 2010-12-01 | 2013-12-12 | 2012-11-03 | 2012-11-03 | 75 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Morgantown | 540068 | Readiness Center | 2011-09-21 | 2011-09-22 | Massaro Corporation | 20958000 | 18933052.72 | 2010-10-01 | under construction | 2013-03-26 | 2013-03-26 | 50 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Moorefield | 540084 | Readiness Center | 2011-06-01 | 2011-09-21 | Langan General Contracting Corp | 14172000 | 13320661.98 | 2010-12-01 | under construction | 2013-03-24 | 2013-03-24 | 65 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | WI | WISCONSIN | Madison | 550139 | Aircraft Parking | 2011-09-15 | 2011-09-22 | Buteyn Peterson Construction Co. | 5689000 | 5772594.5 | 2010-12-01 | 2012-09-30 | 2012-10-17 | 2012-10-17 | 90 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2011 | Army National Guard | Major Construction | WY | WYOMING | Laramie | 560116 | Field Maintenance Shop | 2011-07-28 | 2011-08-16 | Health Construction | 14371000 | 11133511.38 | 2010-12-01 | projected for Apr 13 | 2013-06-30 | 2013-06-30 | 12 | 0 | PL 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2012 | Army National Guard | Minor Construction | AL | ALABAMA | Talladega | 011006 | Readiness Center, Add/Alt | 2012-09-13 | 2012-09-21 | Metro D. Constructions, LLC. | 2000000 | 1900448.6 |  |  |  |  | 0 | 0 | Used FY12 funds
2013-04-15 | 2012 | Army National Guard | Major Construction | AL | ALABAMA | Fort McClellan | 010263 | Readiness Center Ph2 | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. | 16500000 | 14296735 | 2011-12-01 |  | 2013-12-10 | 2013-12-10 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | AZ | ARIZONA | Papago Military Reservation | 040294 | Readiness Center | 2012-02-15 | 2012-08-16 | Haydon Building Corporation - Tem | 17800000 | 17091279.24 | 2011-12-01 |  | 2013-10-16 | 2013-10-16 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | AK | ARKANSAS | Fort Chafee | 050172 | Convoy Live Fire/Entry Control Point Range | 2012-02-14 | 2012-08-16 | SAIC | 3500000 | 3559384.39 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060009 | Utilities Replacement Ph1 | 2012-07-09 | 2012-08-01 | Cox Construction Co. | 32000000 | 22352884.2 | 2011-12-01 |  | 2015-03-01 | 2015-03-01 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp San Luis Obispo | 060170 | Field Maintenance Shop | 2012-06-19 | 2012-06-26 | Goshawk LLC | 8000000 | 7379346.69 | 2011-12-01 |  | 2013-10-14 | 2013-09-22 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Minor Construction | CA | CALIFORNIA | Los Alamitos | 060432 | Barracks | 2012-06-27 | 2012-09-28 | WEP Enterprises | 1400000 | 867723.5 |  |  |  |  | 0 | 0 | FY07 Congressionally Directed, Used FY10 funds
2013-04-15 | 2012 | Army National Guard | Major Construction | CA | CALIFORNIA | Camp Roberts | 060438 | Tactical Unmanned Aircraft System Facility | 2012-06-04 | 2012-07-20 | USPFO Contracting California | 4834795.71 | 4849498.22 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | 2853 Notification
2013-04-15 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Fort Carson | 080093 | Barracks Complex (ORTC) | 2012-08-30 | 2012-09-04 | Jacob's | 43000000 | 42528524.8 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Alamosa | 080126 | Readiness Center | 2012-06-12 | 2012-06-22 | FCI Constructors, Inc. | 6400000 | 6103821.48 | 2011-12-01 |  | 2013-10-14 | 2013-10-14 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | CO | COLORADO | Aurora | 080206 | Tactical Unmanned Aircraft System Facility | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. | 3600000 | 3858949.17 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | DC | DISTRICT OF COLUMBIA | Anacostia | 110007 | US Property & Fiscal Office Add/Alt | 2012-08-21 | 2012-08-28 | Allen & Shariff Corporation | 5300000 | 4671855 | 2012-03-01 |  | 2013-12-13 | 2013-12-13 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120188 | Convoy Live Fire/Entry Control Point Range | 2012-07-31 | 2012-08-16 | Breaking Ground Constracting Co. | 2400000 | 2918900 | 2011-12-01 |  | 2013-10-16 | 2013-10-16 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | FL | FLORIDA | Camp Blanding | 120193 | Live Fire Shoot House | 2012-04-10 | 2012-04-27 | STG Contracting Group | 3100000 | 2554645.89 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Minor Construction | FL | FLORIDA | Camp Blanding, Starke | 120277 | Unit Storage Building (TUAS) | 2012-08-30 | 2012-09-14 | C. Young Construction | 821000 | 821000 |  |  |  |  | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Hinesville | 130063 | Maneuver Area Training & Equipment Site Ph1 | 2012-01-12 | 2012-09-11 | USPFO - GA | 17500000 | 18938573.24 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Macon | 130068 | Readiness Center Ph 1 | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC | 14500000 | 13849724 | 2011-12-01 |  | 2014-03-15 | 2014-03-15 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | GA | GEORGIA | Atlanta | 130120 | Readiness Center | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. | 11000000 | 10970551.18 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | HI | HAWAII | Kalaeloa | 150043 | Readiness Center Ph 1 | 2012-02-15 | 2012-07-11 | Dawson Technical, LLC | 33000000 | 32208735.52 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | IL | ILLINOIS | Normal | 170801 | Readiness Center | 2012-09-13 | 2012-09-13 | River City Construction | 10870650 | 10410493.43 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | Grow the Army/2853 Notification
2013-04-15 | 2012 | Army National Guard | Minor Construction | IL | ILLINOIS | Sparta | 171005 | Battalion Maintenance Shelter | 2012-09-24 | 2012-09-24 | H&N Construction | 1210000 | 996756.79 | 2011-12-01 |  |  |  | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Indianapolis | 180012 | JFHQ Add/Alt | 2012-09-19 | 2012-09-19 | F.A. WILHELM Construction., Inc. | 25700000 | 27428000 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180142 | Railhead Expansion & Container Facility | 2012-09-11 | 2012-09-12 | Milestone Contractors, L.P. | 21000000 | 19068700 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180156 | Deployment Processing Facility | 2012-09-11 | 2012-09-12 | Milestone Contractors, L.P. | 8900000 | 8214000 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180160 | Operations Readiness Training Complex 1 | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | 25000000 | 26136137 | 2011-12-01 |  | 2013-10-25 | 2013-10-25 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | IN | INDIANA | Camp Atterbury | 180161 | Operations Readiness Training Cmplx 2 | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | 27000000 | 27520300 | 2011-12-01 |  | 2013-10-25 | 2013-10-25 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Minor Construction | LA | LOUISIANA | Camp Minden | 220233 | Waste Water Treatment Facility | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. | 2972000 | 2847329 |  |  |  |  | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | ME | MAINE | Bangor | 230046 | Readiness Center | 2012-08-28 | 2012-08-28 | ITSI Gibane | 15600000 | 14690109 | 2011-12-01 |  | 2013-10-21 | 2013-10-21 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | ME | MAINE | Brunswick | 230071 | Armed Forces Reserve Center | 2012-06-06 | 2012-06-14 | Nickerson & O'Day, Inc. | 23866635.14 | 23866635.14 | 2011-12-01 |  | 2013-10-21 | 2013-10-21 | 0 | 0 | Informal Reprogramming
2013-04-15 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | Dundalk | 240017 | Readiness Center Add/Alt | 2012-08-29 | 2012-09-11 | The Whiting Turner Contracting Company | 16000000 | 10719063 | 2011-10-01 |  | 2014-09-19 | 2014-09-19 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | Westminster | 240187 | Readiness Center Add/Alt | 2012-07-23 | 2012-09-11 | Harkins Builders | 10400000 | 7095000 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | MD | MARYLAND | La Plata | 240193 | Readiness Center | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 9000000 | 9280000 | 2011-12-01 |  | 2014-09-19 | 2014-09-19 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | MA | MASSACHUSETTS | Natick | 250135 | Readiness Center | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc | 9324695 | 8564265 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | Grow the Army, Informal Reprogramming
2013-04-15 | 2012 | Army National Guard | Minor Construction | MA | MASSACHUSETTS | Camp Edwards | 250178 | J-1 Range North Pump and Treat Facility | 2012-10-25 | 2012-11-15 | Tetra Tech/Mead & Hunt JV | 2972000 | 2394000 |  |  |  |  | 0 | 0 | Used FY13 funds
2013-04-15 | 2012 | Army National Guard | Major Construction | MN | MINNESOTA | Camp Ripley | 270266 | Multipurpose Machine Gun Range | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. | 4718468 | 4467803.97 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | 2853 Notification
2013-04-15 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280315 | Troop Housing (ORTC) Ph1 | 2012-01-12 | 2012-06-22 | DCD-YATES | 20709500 | 20003954.24 | 2011-12-01 |  | 2013-10-21 | 2013-10-21 | 0 | 0 | 2853 Notification
2013-04-15 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280387 | Deployment Processing Facility | 2012-05-31 | 2012-07-11 | Hanco Corporation | 9222260 | 8803310 | 2011-12-01 |  | 2013-10-16 | 2013-10-16 | 0 | 0 | 2853 Notification
2013-04-15 | 2012 | Army National Guard | Major Construction | MS | MISSISSIPPI | Camp Shelby | 280389 | Operations Readiness Training Cmplx Ph1 | 2012-01-12 | 2012-06-22 | DCD-YATES | 24411040 | 23526448.76 | 2011-12-01 |  | 2013-10-21 | 2013-10-21 | 0 | 0 | 2853 Notification
2013-04-15 | 2012 | Army National Guard | Major Construction | NE | NEBRASKA | Grand Island | 310085 | Readiness Center | 2012-05-29 | 2012-06-05 | Sampson Construction Company, Inc. | 22000000 | 18586418 | 2011-12-01 |  | 2013-10-25 | 2013-10-25 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | NE | NEBRASKA | Mead | 310086 | Readiness Center | 2012-04-09 | 2012-04-27 | Boyd Jones Construction | 9100000 | 9784197 | 2011-12-01 |  | 2013-06-25 | 2013-06-25 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Minor Construction | NE | NEBRASKA | Ashland | 310142 | CATS Waste Water Treatment Facility | 2012-06-28 | 2012-08-10 | All Purpose Construction | 1536000 | 1582713 |  |  |  |  | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | NV | NEVADA | Las Vegas | 320070 | Field Maintenance Shop | 2012-01-12 | 2012-04-17 | CORE Construction | 23000000 | 20845104.16 | 2011-12-01 |  | 2013-10-25 | 2013-10-25 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Minor Construction | NH | NEW HAMPSHIRE | Milford | 330052 | Readiness Center, Add/Alt | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 1947000 | 1895000 |  |  |  |  | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | NJ | NEW JERSEY | Lakehurst | 340115 | Army Aviation Support Facility | 2012-06-07 | 2012-08-15 | Senate Builders & Construction Managers | 49000000 | 44483821 | 2011-12-01 |  | 2014-09-30 | 2014-09-30 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | NM | NEW MEXICO | Santa Fe | 350115 | Readiness Center Add/Alt | 2012-01-03 | 2012-04-10 | Jaynes Corporation | 5200000 | 4309487.61 | 2011-12-01 |  | 2013-06-01 | 2013-06-01 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | NC | NORTH CAROLINA | Greensboro | 370899 | Readiness Center Add/Alt | 2012-09-04 | 2012-09-04 | Holden Building Company, Inc. | 3700000 | 3351169.65 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | OK | OKLAHOMA | Camp Gruber | 400605 | Upgrade-Combined Arms Collective Training Fac | 2012-01-12 | 2012-08-16 | PentaCon, LLC | 10361000 | 8970164.68 | 2011-12-01 |  | 2013-10-16 | 2013-10-16 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | OK | OKLAHOMA | Camp Gruber | 400606 | Live Fire Shoot House | 2012-01-24 | 2012-08-15 | PentaCon, LLC | 3000000 | 3073646.94 | 2011-12-01 |  | 2013-12-16 | 2013-12-16 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | OR | OREGON | The Dalles | 410026 | Readiness Center | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 13800000 | 13189960 | 2011-12-01 |  | 2013-12-28 | 2013-12-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | RQ | PUERTO RICO | Fort Buchanan | 430010 | Readiness Center | 2012-09-10 | 2012-09-18 | RB Construction Group Inc | 40565271.7 | 37803671.38 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | 2853 Notification
2013-04-15 | 2012 | Army National Guard | Major Construction | SC | SOUTH CAROLINA | Allendale | 450403 | Readiness Center Add/Alt | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. | 4300000 | 3998000 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | UT | UTAH | Camp Williams | 490618 | Multi Purpose Machine Gun Range | 2012-09-06 | 2012-09-27 | USPFO - UT | 6500000 | 6576914.72 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | VA | VIRGINIA | Fort Pickett | 510307 | Combined Arms Collective Training Facility | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | 11000000 | 8316000 | 2011-12-01 |  |  |  | 0 | 0
2013-04-15 | 2012 | Army National Guard | Major Construction | WV | WEST VIRGINIA | Buckhannon | 540085 | Readiness Center Ph1 | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | 10000000 | 11387900.52 | 2011-12-01 |  | 2013-10-08 | 2013-10-08 | 0 | 0 | Grow the Army
2013-04-15 | 2012 | Army National Guard | Major Construction | WI | WISCONSIN | Camp Williams | 550245 | Tactical Unmanned Aircraft System Facility | 2012-07-18 | 2012-07-24 | Nuvo Construction Company Inc. | 4149560 | 3968751.26 | 2011-12-01 |  | 2013-04-18 | 2013-04-18 | 0 | 0 | Grow the Army/2853 Notification
2013-04-15 | 2012 | Army National Guard | Major Construction | WY | WYOMING | Cheyenne | 560702 | Readiness Center | 2012-04-27 | 2012-04-18 | Hensel Phelps | 8900000 | 10341796 | 2011-12-01 |  | 2013-10-28 | 2013-10-28 | 0 | 0
Formulas:
Original completion date = [Start date]+380

## P&D
Submittal Date | Fiscal Year | Component | Type of funds | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Notes/remarks
2013-04-15 | 2010 | WHS | General P&D | Complete design or RFP development of FY11 MILCON projects | 3575 | 3575
2013-04-15 | 2011 | WHS | General P&D | Complete design or RFP development of FY12 MILCON projects | 6257 | 0
2013-04-15 | 2012 | WHS | General P&D | Complete design or RFP development of FY13 MILCON projects
2013-04-15 | 2007 | MDA | General P&D | Design MDA 609 - Aegis-BMD Facility Expansion, Dahlgren, VA. | 770 | 770 | Completed RFP for design-build (D-B) project.
2013-04-15 | 2009 | MDA | General P&D | Design MDA FY10-FY13 MILCON Projects | 14889 | 14363 | Supports design of the Aegis Ashore Test Complex, East Coast Comm site, Aegis Ashore Romania site, UEWR Modifications at Clear AFS, AK and completes RFP for D-B Von Braun Complex, Phase IV.
2013-04-15 | 2010 | MDA | General P&D | Design MDA FY12-13 MILCON Projects | 7700 | 7672 | Supports design of the Aegis Ashore Romania site and EUCOM Radar site. Includes $5,700,000 reprogrammed from MILCON.
2013-04-15 | 2012 | MDA | General P&D | Design MDA FY13-14 MILCON Projects | 8368 | 8368 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2013-04-15 | 2013 | MDA | General P&D | Design MDA FY13-14 MILCON Projects | 4548 | 699 | Supports design of the UEWR Modifications at Clear AFS, AK and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2013-04-15 | 2009 | MDA | UMC | Used for accomplishing urgent unforeseen construction projects in FY12 | 3457 | 1650 | Obligated funds support the EUCOM Radar Site. EUCOM work to resume from Winter break on 1 May 2013. Pending obligation of funds for the Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping project at Fort Greely, AK
2013-04-15 | 2010 | MDA | UMC | Used for accomplishing urgent unforeseen construction projects in FY12-13 | 3717 | 0 | Pending obligation of funds to support the R&C Piping project at Fort Greely, AK.
2013-04-15 | 2006 | Air Force | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; GWOT Supplemental | 65284 | 59451
2013-04-15 | 2006 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27783 | 27252
2013-04-15 | 2006 | Air Force Reserve | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5290 | 5289
2013-04-15 | 2006 | Air National Guard | General P&D | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006 | 28076
2013-04-15 | 2007 | Air Force | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements ; GWOT Supplemental | 76246 | 75068
2013-04-15 | 2007 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12983
2013-04-15 | 2007 | Air Force Reserve | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109 | 5087
2013-04-15 | 2007 | Air National Guard | General P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050 | 19044
2013-04-15 | 2008 | Air Force | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; GWOT Supplemental | 51202 | 50373
2013-04-15 | 2008 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12162
2013-04-15 | 2008 | Air Force Reserve | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300 | 5276
2013-04-15 | 2008 | Air National Guard | General P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721 | 10619
2013-04-15 | 2009 | Air Force | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105506 | 101565
2013-04-15 | 2009 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7708 | 7633
2013-04-15 | 2009 | Air Force Reserve | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165 | 5983
2013-04-15 | 2009 | Air National Guard | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056 | 18547
2013-04-15 | 2010 | Air Force | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 112785 | 103974
2013-04-15 | 2010 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4314 | 1411
2013-04-15 | 2010 | Air Force Reserve | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 3869 | 2318
2013-04-15 | 2010 | Air National Guard | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 20021 | 19017
2013-04-15 | 2011 | Air Force | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 76625 | 53123
2013-04-15 | 2011 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4216 | 3359
2013-04-15 | 2011 | Air Force Reserve | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1650 | 1241
2013-04-15 | 2011 | Air National Guard | General P&D | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9196 | 8366
2013-04-15 | 2012 | Air Force | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 81913 | 17704
2013-04-15 | 2012 | Air Force | MFH P&D | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4208 | 3313
2013-04-15 | 2012 | Air Force Reserve | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200 | 679
2013-04-15 | 2012 | Air National Guard | General P&D | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225 | 5835
2013-04-15 | 2009 | Army Active | MCA-P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 221123
2013-04-15 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000
2013-04-15 | 2010 | Army Active | MCA-P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250780
2013-04-15 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000
2013-04-15 | 2011 | Army Active | MCA-P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 219636 | 250920
2013-04-15 | 2011 | Army Active | Host Nation Support | $29,944 Appropriated + $13,000 ATR | 42944 | 42902
2013-04-15 | 2012 | Army Active | MCA-P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 119467
2013-04-15 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25500 | 25476
2013-04-15 | 2013 | Army Active | MCA-P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 65000
2013-04-15 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000 | 12467
2013-04-15 | 2009 | Army Active | UMMCA | Unspecified Minor Construction for Projects < $2.M | 23000 | 26641
2013-04-15 | 2010 | Army Active | UMMCA | Unspecified Minor Construction for Projects < $2.M | 25000 | 30691
2013-04-15 | 2010 | Army Active | Overseas Contingency Operations | Unspecified Minor Construction for Projects < $2.M | 60100 | 15087
2013-04-15 | 2011 | Army Active | UMMCA | Unspecified Minor Construction for Projects < $2.M | 23000 | 20799
2013-04-15 | 2011 | Army Active | Overseas Contingency Operations | Unspecified Minor Construction for Projects < $2.M | 78330 | 1281
2013-04-15 | 2012 | Army Active | UMMCA | Unspecified Minor Construction for Projects < $2.M | 20000 | 18438
2013-04-15 | 2009 |  | AFHC | Army Family Housing Construction for Projects | 579 | 574
2013-04-15 | 2010 |  | AFHC | Army Family Housing Construction for Projects | 3936 | 3676
2013-04-15 | 2011 |  | AFHC | Army Family Housing Construction for Projects | 2040 | 1895
2013-04-15 | 2012 |  | AFHC | Army Family Housing Construction for Projects | 7897 | 1714
2013-04-15 | 2009 | Navy - MC Active | General P&D | Excluding OCOS: Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs | 246528 | 246431 | Design funds in the amount of $3.5M withdrawn in May 2009 for transfer to the Federal Highway Administration to support the Guam Defense Access Road Improvement project, factored into the Current Obligated Amount.
2013-04-15 | 2010 | Navy - MC Active | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs | 179652 | 215190 | Design funds in the amount of $4.0M withdrawn in April/August/December 2010, for transfer to the Federal Highway Administration to support one Camp Lejeune and two Guam Defense Access Road Improvement projects, factored into the Current Obligated Amount. Reprogrammed Amount of $40,978,000 added to FY10 MCON P&D which is not reflected in the original Appropriated Amount. Due to this, obligations will exceed the figure shown in the Appropriated Amount.
2013-04-15 | 2011 | Navy - MC Active | General P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 119809 | 119693 | Spend Plan represented in Appropriated Amount. Appropriated Amount is $120.050M.
2013-04-15 | 2012 | Navy - MC Active | General P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 84362 | 78310
2013-04-15 | 2013 | Navy - MC Active | General P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 102619 | 20873 | Design funds received under CRA $30,038
2013-04-15 | 2009 | Navy - MC Active | MFH P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs | 2169 | 2147
2013-04-15 | 2010 | Navy - MC Active | MFH P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs | 2771 | 2262
2013-04-15 | 2011 | Navy - MC Active | MFH P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 3248.49 | 2702
2013-04-15 | 2012 | Navy - MC Active | MFH P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 3199 | 2898
2013-04-15 | 2013 | Navy - MC Active | MFH P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1616 | 764
2013-04-15 | 2009 | Navy - MC Reserves | General P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs | 2045 | 2044.939
2013-04-15 | 2010 | Navy - MC Reserves | General P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs | 2951 | 2951
2013-04-15 | 2011 | Navy - MC Reserves | General P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1853.286 | 1849 | Spend Plan represented in Appropriated Amount. Appropriated Amount is $1.857M.
2013-04-15 | 2012 | Navy - MC Reserves | General P&D | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2591 | 1789
2013-04-15 | 2013 | Navy - MC Reserves | General P&D | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 2118 | 0 | Design funds received under CRA $451
2013-04-15 | 2009 | Navy - MC Active | General P&D | Complete design of FY09 ARRA | 4331 | 0 | Design funds in the amount of $3.781M moved to construction to fund ARRA Add projects; remaining funds withdrawn by OSD after 12/31/12
2013-04-15 | 2009 | Navy - MC Active | General P&D | Complete design of FY09 OCOS | 11000 | 10993
2013-04-15 | 2008 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 3400 | 3348 | RCI-Residential Communities Initiative
2013-04-15 | 2008 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 08/09/ 10/11/12 MILCON projects | 1891 | 1891
2013-04-15 | 2009 | DoDEA | P&D - RCI Funds (Army Funded) | Design Efforts FY09 RCI MILCON projects | 1830 | 1830
2013-04-15 | 2009 | DoDEA | P&D-FAD from OSD May 2009 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 5000 | 5000
2013-04-15 | 2009 | DoDEA | P&D-FAD from OSD May 2010 | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 7000 | 7000
2013-04-15 | 2010 | DoDEA | P&D-FAD from OSD Jan 2010 | Design efforts for FY 10/11/ 12/13 MILCON projects | 8855 | 8855
2013-04-15 | 2011 | DoDEA | P&D-FAD from OSD 24 Feb 2011 | Design efforts for FY 11/12/ 13 MILCON projects | 7840 | 7840
2013-04-15 | 2011 | DoDEA | P&D-FAD from ODS 2 June 2011 | Design efforts for FY 11/12/13 MILCON projects | 71763 | 71483
2013-04-15 | 2012 | DoDEA | P&D-FAD from OSD 6 Jan 2012 | Design efforts for FY 12/13 MILCON projects | 66974 | 63828
2013-04-15 | 2008 | DoDEA |  | Unspecified Minor Construction for projects < $2.M | 666 | 0
2013-04-15 | 2009 | DoDEA |  | Unspecified Minor Construction for projects < $2.M | 382 | 4 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2013-04-15 | 2010 | DoDEA |  | Unspecified Minor Construction for projects < $2.M | 6800 | 0
2013-04-15 | 2011 | DoDEA |  | Unspecified Minor Construction for projects < $2.M | 3486 | 0
2013-04-15 | 2008 | NSA | General P&D | MoonPenny Distribution Substation | 396 | 396
2013-04-15 | 2009 | NSA | General P&D | Power & Cooling Infrastructure | 4000 | 4000 | P & D for High Voltage Power Upgrade
2013-04-15 | 2010 | NSA | General P&D | MoonPenny Distribution Substation | 144 | 144
2013-04-15 | 2010 | NSA | General P&D | Power & Cooling Infrastructure | 240 | 240 | Additional Funding, assume from MHS Backup Power Generation Facility Reprogramming
2013-04-15 | 2010 | NSA | General P&D | Generators 10 & 11 | 200 | 200
2013-04-15 | 2011 | NSA | General P&D | A&E Design for Colorado Powerhouse | 3000 | 3000
2013-04-15 | 2012 | NSA | General P&D | East Campus Building 1 | 12000 | 12000
2013-04-15 | 2009 | SOCOM | General P&D | MILCON | 14533 | 14081 | As of Apr 2013
2013-04-15 | 2010 | SOCOM | General P&D | MILCON | 4069 | 3937 | As of Apr 2013
2013-04-15 | 2011 | SOCOM | General P&D | MILCON | 26782 | 22722 | As of Apr 2013
2013-04-15 | 2012 | SOCOM | General P&D | MILCON | 31468 | 17043 | As of Apr 2013
2013-04-15 | 2013 | SOCOM | General P&D | MILCON | 27620 | 936 | As of Apr 2013
2013-04-15 | 2007 | TMA | MCA - P&D | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 80052 | 79993
2013-04-15 | 2008 | TMA | MCA - P&D | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 113065 | 112747
2013-04-15 | 2009 | TMA | MCA - P&D | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 172087 | 162217
2013-04-15 | 2010 | TMA | MCA - P&D | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 73306 | 66308
2013-04-15 | 2011 | TMA | MCA - P&D | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 217528 | 98667
2013-04-15 | 2007 | TMA | UMC | Unspecified Minor Construction for projects < $2.M | 3204 | 2905
2013-04-15 | 2008 | TMA | UMC | Unspecified Minor Construction for projects < $2.M | 3499 | 3495
2013-04-15 | 2009 | TMA | UMC | Unspecified Minor Construction for projects < $2.M | 3990 | 3853
2013-04-15 | 2010 | TMA | UMC | Unspecified Minor Construction for projects < $2.M | 4525 | 2402
2013-04-15 | 2011 | TMA | UMC | Unspecified Minor Construction for projects < $2.M | 4874 | 2274
2013-04-15 | 2009 | DLA | General P&D | Design efforts for FY 10/11/12 MILCON projects | 4342 | 4333
2013-04-15 | 2010 | DLA | General P&D | Design efforts for FY 11/12/13 MILCON projects | 12603 | 12591 | OSD provided additional P&D 15 Jun 11
2013-04-15 | 2011 | DLA | General P&D | Design efforts for FY 11/12/13 MILCON projects | 36649 | 36484 | OSD provided additional P&D 07 Mar 12
2013-04-15 | 2012 | DLA | General P&D | Design efforts for FY 12/13/14 MILCON projects | 17390 | 2087 | OSD provided additional P&D 22 Nov 12
2013-04-15 | 2013 | DLA | General P&D | Design efforts for FY 13/14/15 MILCON projects | 0 | 0
2013-04-15 | 2012 | DIA | General P&D | P&D for DIAC parking garage replacement | 1498 | 1254 | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. Design Charette scheduled for Sept. $1,254k obligated as CAT I acceptance for fee.
2013-04-15 | 2012 | DIA | General P&D | P&D for DIAC chilled water project for data center | 125 | 0 | Planning and Design (P&D) Directive forwarded to NAVFAC. Site visit held 9 August 2012.
2013-04-15 | 2012 | DIA | General P&D | P&D for DIAC cooling tower for data center | 105 | 0 | Planning and Design (P&D) Directive forwarded to NAVFAC. Site visit held 9 August 2012.
2013-04-15 | 2012 | DIA | General P&D | P&D for UPS for data center installation | 120 | 120 | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Site visit held 9 August 2012. MIPR accepted as CAT I for full amount of this project.
2013-04-15 | 2012 | DIA | General P&D | P&D for construction of JUIAF RDF | 1195 | 1195 | $1,195 obligated as CAT I acceptance. Working with USACE on requirements.
2013-04-15 | 2009 | Army National Guard | Planning and Design (P&D) | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 60950 | 60927
2013-04-15 | 2010 | Army National Guard | Planning and Design (P&D) | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 46352 | 43285
2013-04-15 | 2011 | Army National Guard | Planning and Design (P&D) | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25611 | 25563 | P.L. 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2012 | Army National Guard | Planning and Design (P&D) | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20671 | 7163
2013-04-15 | 2013 | Army National Guard | Planning and Design (P&D) | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 26622 | 0 | Continuing Resolution (CR) 1 Oct 12 - 27 Mar 13
2013-04-15 | 2009 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 23775 | 19017
2013-04-15 | 2010 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 35811 | 29550
2013-04-15 | 2011 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 11377 | 11253 | P.L. 112-10 SEC 1119 (a) 0.2% Recission
2013-04-15 | 2012 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 11700 | 7271
2013-04-15 | 2013 | Army National Guard | Unspecified Minor Military Construction (UMMC) | Unspecified Minor Military Construction for projects < $2M | 12633 | 2394 | Continuing Resolution (CR) 1 Oct 12 - 27 Mar 13