## PROJECTS
Project Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Construction Project Type Name | State Name | Country Name | Project Number | Project Title | Sub-Project Number | Diverted Funds Total Amount | Diverted Funds Recipient Text | Construction Start Date | Original Construction Completion Date | Current Construction Completion Date | Construction Percent Complete | Current RPA Placed-In-Service Date | Project Remarks | Project Remarks
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Tennessee | United States | ACC123183 | Air Support Operations Center |  |  |  | 2014-09-29 | 2015-08-03 | 2016-04-20 | 85% | 2016-04-20
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Texas | United States | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 |  |  |  | 2014-05-15 | 2015-06-09 | 2016-03-30 | 98% | 2015-06-30
2016-04-15 | 2012 | Air Force Active | Unspecified Minor Military Construction | Oklahoma | United States | AGGN123002P | Communications Network Control Center Consolidation |  |  |  | 2014-03-10 | 2014-03-31 | 2016-01-28 | 100% | 2016-01-28
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS |  |  |  | 2014-07-30 | 2015-11-12 | 2016-03-14 | 99% | 2015-04-13
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu |  |  |  | 2015-01-14 | 2015-12-24 | 2016-05-05 | 53% | 2016-06-03
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 |  |  |  | 2014-06-19 | 2015-10-12 | 2016-03-26 | 90% | 2016-03-26
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN143004 | KC-46A FTU FTC Simulator Facility Phase 1 |  |  |  | 2014-06-19 | 2015-10-12 | 2016-03-26 | 90% | 2016-02-19
2016-04-15 | 2013 | Air Force Active | Major Military Construction | Guam | Guam | AJJY123010 | Guam Strike Fuel Systems Maintenance Hangar |  |  |  | 2015-03-25 | 2017-04-16 | 2017-04-16 | 8% | 2017-03-21
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | AJJY133027 | Guam Strike Tanker Gp Maint Hangar/Amu/Sqd Ops (Incr 1) |  |  |  | 2015-02-01 | 2017-03-08 | 2017-03-08 | 10% | 2017-01-30
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | AJJY143760 | Hardened Structures For POL Fuel Systems |  |  |  | 2014-11-19 | 2016-04-12 | 2018-04-27 | 6% | 2018-04-27
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility |  |  |  | 2014-10-24 | 2016-07-20 | 2016-07-20 | 60% | 2016-07-20
2016-04-15 | 2010 | Air Force Active | Major Military Construction | Maryland | United States | AJXF063009 | Replace Munitions Storage Area |  |  |  | 2011-06-23 | 2011-12-16 | 2016-03-09 | 94% | 2016-03-09
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Maryland | United States | AJXF103010 | Construct Helicopter Operations Facility |  |  |  | 2015-01-26 | 2017-03-09 | 2017-03-09 | 2% | 2017-03-09
2016-04-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Maryland | United States | AJXF106000 | Construct Taxiway To North Of ACA Facility Bldg 2489 |  |  |  | 2015-04-09 | 2016-04-08 | 2016-05-08 | 2% | 2016-05-08
2016-04-15 | 2011 | Air Force Active | Major Military Construction |  | Qatar | ALUA073006B | Blatchford-Preston Complex, Phase III |  |  |  | 2012-09-27 | 2016-01-29 | 2016-01-29 | 60% | 2016-05-17 | Original Construcion Completion Date changed from 31 Jan 13 to resolve error; | Original Construcion Completion Date changed from 31 Jan 13 to resolve error;
2016-04-15 | 2008 | Air Force Active | Major Military Construction |  | Qatar | ALUA073008A | Facility Replacements |  |  |  | 2011-03-01 | 2010-06-30 | 2015-10-06 | 100% | 2015-10-13
2016-04-15 | 2010 | Air Force Active | Major Military Construction |  | Qatar | ALUA107000 | Coalition Compound Billeting |  |  |  | 2012-06-05 | 2013-11-30 | 2015-12-04 | 94% | 2016-02-04
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA110032 | Fuel Truck Parking |  |  |  | 2013-08-15 | 2014-12-06 | 2016-06-30 | 42% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Major Military Construction |  | Qatar | ALUA113001 | Theater Communications Facility |  |  |  | 2012-06-01 | 2012-12-21 | 2016-08-30 | 75% | 2016-10-30
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113002 | Fuels Laboratory |  |  |  | 2013-08-15 | 2014-12-06 | 2016-06-30 | 42% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113005 | C-17 Spare Parts Facility |  |  |  | 2013-08-15 | 2014-12-06 | 2016-06-30 | 42% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113006 | High Mast Lighting |  |  |  | 2013-08-15 | 2014-12-06 | 2016-06-30 | 42% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113009 | Entry Control Point |  |  |  | 2013-08-15 | 2014-12-06 | 2016-06-30 | 42% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113010 | Cryogenics Facility |  |  |  | 2013-08-15 | 2014-12-06 | 2016-06-30 | 42% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113012 | ELRS Storage Facility |  |  |  | 2013-08-15 | 2014-04-17 | 2016-06-30 | 42% | 2016-06-30
2016-04-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113026 | C-130 Aircraft Maintenance Unit |  |  |  | 2013-09-12 | 2014-04-09 | 2016-06-30 | 23% | 2016-06-30
2016-04-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113027 | Air Defense Artillery Maintenance Facility |  |  |  | 2013-08-28 | 2014-04-09 | 2016-01-31 | 99% | 2016-01-15
2016-04-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113032 | Precision Measurement Equipment Laboratory |  |  |  | 2013-08-28 | 2014-04-09 | 2016-01-31 | 99% | 2016-01-31
2016-04-15 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | Qatar | ALUA113034 | AFOSI Regional And Local Facility |  |  |  | 2013-08-28 | 2014-04-09 | 2016-01-31 | 99% | 2016-01-15
2016-04-15 | 2011 | Air Force Active | Major Military Construction |  | Italy | ASHE083011 | Air Support Operations Squadron (ASOS) Facility |  | 1453000 | KRSM103011; | 2011-12-16 | 2013-06-06 | 2016-03-14 | 97% | 2016-02-03
2016-04-15 | 2013 | Air Force Active | Major Military Construction |  | Italy | ASHE103001 | F-16 Mission Training Center |  |  |  | 2015-05-04 | 2016-12-02 | 2017-01-25 | 22% | 2016-10-03
2016-04-15 | 2012 | Air Force Active | Major Military Construction | Louisiana | United States | AWUB105002 | Mission Support Group Complex |  |  |  | 2012-03-26 | 2013-06-17 | 2015-09-16 | 99% | 2014-12-23
2016-04-15 | 2013 | Air Force Active | Major Military Construction | California | United States | BAEY133001 | Civil Engineer Administration/Operations Facility |  |  |  | 2014-07-09 | 2016-03-30 | 2016-09-29 | 18% | 2016-03-30
2016-04-15 | 2014 | Air Force Active | Major Military Construction | California | United States | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 3000000 | CADJ140004; | 2014-08-27 | 2016-08-26 | 2016-11-04 | 18% | 2016-12-10
2016-04-15 | 2015 | Air Force Active | Major Military Construction |  | Djibouti | CADJ140004 | Construct Perimeter Boundary - Chabelley Airfield, Djibouti |  |  |  | 2015-09-29 | 2016-12-30 | 2016-12-30 | 2% | 2016-11-30
2016-04-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ013004 | Airman And Family Readiness Center |  |  |  | 2015-06-11 | 2015-06-23 | 2016-06-10 | 40% | 2016-08-10
2016-04-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ073023A | Satellite Dining Facility |  |  |  | 2015-01-27 | 2016-11-19 | 2016-11-24 | 76% | 2016-08-26
2016-04-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ073050 | Dormitory (144 Rm) |  |  |  | 2014-08-14 | 2015-07-15 | 2016-08-03 | 87% | 2016-04-30
2016-04-15 | 2010 | Air Force Active | Major Military Construction |  | United Arab Emirates | DHAF100031 | Construct Maintenance Operations Center And Command Post |  |  |  | 2011-09-19 | 2011-06-15 | 2016-04-15 | 99% | 2016-04-15
2016-04-15 | 2010 | Air Force Active | Major Military Construction |  | United Arab Emirates | DHAF100120 | Construct SatCom Facility |  |  |  | 2011-09-19 | 2011-09-15 | 2016-04-15 | 99% | 2016-04-15
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF120037 | Clinic |  |  |  | 2014-09-29 | 2014-10-05 | 2016-06-30 | 40% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF120057 | Fire Protection Water Storage |  |  |  | 2014-09-15 | 2014-10-05 | 2016-03-31 | 87% | 2016-03-31
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | United Arab Emirates | DHAF124001 | EOD Facility |  |  |  | 2014-12-01 | 2014-10-05 | 2016-06-30 | 40% | 2016-06-30
2016-04-15 | 2011 | Air Force Active | Major Military Construction | Arizona | United States | FBNV063501 | AMARG Hangar |  |  |  | 2011-09-12 | 2013-03-11 | 2016-03-16 | 97% | 2016-03-16
2016-04-15 | 2011 | Air Force Active | Major Military Construction | Arizona | United States | FBNV113002 | HC-130J Aerial Cargo Facility |  | 2000000 | YWHG111005; | 2011-11-09 | 2012-09-21 | 2016-10-20 | 95% | 2013-09-13
2016-04-15 | 2012 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | FBNV133500 | T-10 Engine Test Cell (AMARG) |  |  |  | 2014-08-12 | 2015-06-08 | 2016-03-20 | 80% | 2016-03-20
2016-04-15 | 2010 | Air Force Active | Major Military Construction | Delaware | United States | FJXT033003 | Consol Communications Facility |  |  |  | 2011-01-03 | 2011-11-09 | 2016-08-31 | 95% | 2014-09-12
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | FTFA073007 | CNST Modular Storage Magazines |  |  |  | 2015-02-05 | 2015-10-13 | 2016-02-09 | 98% | 2016-05-09
2016-04-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Florida | United States | FTFA123000 | Advanced Energetics Development Office Facility |  |  |  | 2014-12-05 | 2015-12-05 | 2016-03-04 | 98% | 2016-03-07
2016-04-15 | 2012 | Air Force Active | Major Military Construction | Alaska | United States | FTQW083005 | Dormitory (168 RM) |  |  |  | 2014-08-26 | 2016-08-15 | 2016-08-15 | 41% | 2016-09-26
2016-04-15 | 2010 | Air Force Active | Major Military Construction | Alaska | United States | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 |  |  |  | 2011-06-17 | 2014-11-23 | 2016-12-22 | 87% | 2015-06-28
2016-04-15 | 2011 | Air Force Active | Major Military Construction | Alaska | United States | FTQW083008 | Repair Central Heat And Power Plant Boiler |  |  |  | 2011-06-17 | 2014-11-24 | 2016-12-22 | 87% | 2016-12-22
2016-04-15 | 2012 | Air Force Active | Major Military Construction | Alaska | United States | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) |  | 19165000 | ALUA073006B;WWYK143004A;YWHG111005;ZHTV053302; | 2012-06-26 | 2013-11-20 | 2016-06-29 | 98% | 2016-06-29
2016-04-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Washington | United States | GJKZ130025 | ADAL, Physiological Tng Fac, Convert To PMEL; B2145 |  |  |  | 2015-01-27 | 2015-12-17 | 2016-08-01 | 35% | 2016-08-01
2016-04-15 | 2012 | Air Force Active | Major Military Construction |  | Italy | HACC123204 | UAS SATCOM Relay Pads and Facility |  |  |  | 2015-09-04 | 2017-02-21 | 2016-11-30 | 2% | 2016-12-30
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Hawaii | United States | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  |  |  | 2014-08-21 | 2016-10-15 | 2016-09-15 | 2% | 2016-09-15
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Utah | United States | KRSM003009 | Fire Crash Rescue Station |  |  |  | 2015-04-28 | 2015-04-16 | 2017-04-16 | 6% | 2017-04-16
2016-04-15 | 2013 | Air Force Active | Major Military Construction | Utah | United States | KRSM103012 | F-35 Adal Hangar 45W/AMU |  |  |  | 2014-01-27 | 2015-08-27 | 2016-05-30 | 96% | 2016-05-30
2016-04-15 | 2012 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD013003 | Child Development Center |  |  |  | 2012-11-08 | 2014-05-17 | 2016-03-15 | 99% | 2014-06-14
2016-04-15 | 2008 | Air Force Active | Military Family Housing Improvement |  | Turkey | LJYC084001 | Improve Family Housing 515 Units |  |  |  | 2012-03-08 | 2011-06-30 | 2016-03-16 | 90% | 2015-07-19
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction |  | Turkey | LJYC106001 | EOD Facility |  |  |  | 2015-10-06 | 2016-10-05 | 2016-10-05 | 2% | 2016-10-05
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | LKTC073101 | Land Acquisition |  |  |  | 2014-09-02 | 2016-05-28 | 2016-05-28 | 2% | 2016-05-28
2016-04-15 | 2013 | Air Force Active | Major Military Construction | Nevada | United States | LKTC133101 | RPA Mission Complex Physical Protection System |  |  |  | 2014-08-19 | 2015-08-19 | 2015-12-21 | 98% | 2015-10-13
2016-04-15 | 2011 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ114127 | Improve Family Housing, Ph 11 |  |  |  | 2012-10-24 | 2014-12-01 | 2015-10-16 | 100% | 2015-10-16
2016-04-15 | 2012 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 |  |  |  | 2013-06-04 | 2014-03-01 | 2015-10-16 | 100% | 2015-10-15
2016-04-15 | 2013 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 |  |  |  | 2013-08-29 | 2015-11-27 | 2016-03-19 | 95% | 2016-03-19
2016-04-15 | 2014 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ144287 | Improve MFH Infrastructure, Phase 3 |  |  |  | 2014-08-04 | 2015-12-15 | 2016-04-06 | 69% | 2016-04-06
2016-04-15 | 2014 | Air Force Active | Major Military Construction | New Mexico | United States | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 |  |  |  | 2014-08-25 | 2016-02-08 | 2016-12-12 | 62% | 2017-03-28
2016-04-15 | 2013 | Air Force Active | Major Military Construction | Texas | United States | MPLS083008 | Dormitory (96 Rm) |  |  |  | 2014-03-15 | 2014-12-25 | 2016-06-20 | 86% | 2016-06-25
2016-04-15 | 2011 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R3 | Recruit Dormitories Phase 3 |  | 4894000 | KRSM103011; | 2011-11-11 | 2015-09-05 | 2016-12-15 | 90% | 2015-06-06 | Original Construcion Completion Date changed from 28 Dec 12 to resolve error | Original Construcion Completion Date changed from 28 Dec 12 to resolve error
2016-04-15 | 2012 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R4 | BMT Recruit Dormitory, Phase IV |  |  |  | 2013-01-26 | 2016-01-03 | 2016-06-30 | 90% | 2015-09-11 | Original Construcion Completion Date changed from 1 Oct 13 to resolve error | Original Construcion Completion Date changed from 1 Oct 13 to resolve error
2016-04-15 | 2011 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 |  |  |  | 2011-09-05 | 2015-04-24 | 2014-06-30 | 100% | 2015-03-15 | Original Construcion Completion Date changed from 30 Jun 13 to resolve error | Original Construcion Completion Date changed from 30 Jun 13 to resolve error
2016-04-15 | 2010 | Air Force Active | Major Military Construction | Virginia | United States | MUHJ053008 | West & Lasalle Gates Force Protection/Access |  |  |  | 2010-07-07 | 2015-08-25 | 2015-12-03 | 99% | 2013-07-19 | Original Construcion Completion Date changed from 28 Apr 11 to resolve error | Original Construcion Completion Date changed from 28 Apr 11 to resolve error
2016-04-15 | 2013 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK103006 | C-130J Fuel Systems Maintenance Hangar |  | 2000000 | KRSM103012; | 2013-07-23 | 2014-11-19 | 2015-12-18 | 100% | 2015-12-18
2016-04-15 | 2013 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK113005 | C-130J Flight Simulator Addition |  |  |  | 2014-10-21 | 2015-03-20 | 2016-03-31 | 70% | 2016-03-31
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093007 | Construct Addition, Field Training Facility, B936 |  |  |  | 2014-12-01 | 2015-07-07 | 2015-12-30 | 100% | 2015-11-09
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) |  | 1200000 | CADJ140004; | 2015-06-15 | 2016-02-14 | 2016-03-20 | 79% | 2016-03-20
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Arizona | United States | NUEX103005 | Construct Flightline Fillstands |  |  |  | 2015-06-01 | 2016-11-22 | 2016-11-23 | 13% | 2016-11-23
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Arizona | United States | NUEX123001 | F-35 Aircraft Maintenance Hangar (Squadron 2) |  |  |  | 2015-09-24 | 2016-08-19 | 2016-08-19 | 8% | 2016-09-20
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Maryland | United States | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  |  |  | 2014-07-07 | 2016-04-13 | 2017-04-13 | 23% | 2017-04-13
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar |  | 10500000 | SGBP100904C; | 2014-08-10 | 2016-01-05 | 2016-03-29 | 83% | 2016-05-06
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145118 | KC-46A Fuselage Trainer |  |  |  | 2015-05-18 | 2016-05-04 | 2016-05-17 | 16% | 2016-07-16
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145121 | KC-46A ADAL Flight Simulator Buildings |  |  |  | 2015-03-30 | 2016-04-19 | 2016-03-30 | 38% | 2016-03-20
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems |  | 2500000 | SGBP100904C; | 2014-09-02 | 2015-12-17 | 2015-10-13 | 100% | 2015-10-13
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145138 | KC-46A Alter Aircraft Parking Apron |  | 600000 | PRQE145121; | 2014-08-18 | 2016-06-24 | 2017-03-10 | 59% | 2017-03-16
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE145142 | KC-46A 1-Bay Maintenance Hangar |  | 3000000 | SGBP100904C; | 2014-09-19 | 2016-05-27 | 2016-04-12 | 95% | 2016-05-16
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155118 | KC-46A Adal Mobility Bag Storage Expansion |  |  |  | 2015-05-18 | 2016-02-05 | 2016-05-17 | 16% | 2016-07-16
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar |  | 19000000 | SGBP100904C; | 2014-09-30 | 2015-12-26 | 2017-03-16 | 47% | 2017-03-16
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) |  |  |  | 2014-10-30 | 2015-07-24 | 2016-03-15 | 98% | 2016-04-15
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Kansas | United States | PRQE155124 | KC-46A Alter Taxiway Foxtrot |  |  |  | 2015-05-12 | 2016-11-02 | 2016-05-11 | 35% | 2016-06-14
2016-04-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | New Jersey | United States | PTFL126001 | Addition To Maintenance Training Facility, Bldg 2324 |  |  |  | 2015-10-03 | 2016-06-29 | 2016-06-29 | 2% | 2016-09-27
2016-04-15 | 2014 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF092013 | B-52 Munitions Storage Igloos |  |  |  | 2014-07-15 | 2014-10-01 | 2016-06-22 | 77% | 2016-06-22
2016-04-15 | 2014 | Air Force Active | Military Family Housing Improvement |  | Japan | QKKA133001P1 | Improve Family Housing, Ph 1 |  |  |  | 2015-10-29 | 2017-09-01 | 2017-09-01 | 2% | 2017-10-03
2016-04-15 | 2013 | Air Force Active | Military Family Housing Improvement |  | Japan | QKKA134001 | Improve Mfh Infrastructure, Phase 2 |  |  |  | 2013-10-29 | 2015-04-15 | 2015-11-18 | 100% | 2015-12-22
2016-04-15 | 2014 | Air Force Active | Military Family Housing Improvement |  | Japan | QKKA144002 | Improve MFH Infrastructure, Phase 3 |  |  |  | 2014-11-06 | 2016-11-10 | 2017-01-14 | 23% | 2017-02-13
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Georgia | United States | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility |  |  |  | 2014-11-19 | 2015-02-18 | 2015-11-23 | 75% | 2015-11-23
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF083002 | Dormitory |  |  |  | 2014-07-11 | 2016-09-28 | 2016-12-07 | 35% | 2016-07-15
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103005 | F-35A ADAL AME Storage Facility |  |  |  | 2015-04-01 | 2016-02-18 | 2016-04-30 | 51% | 2016-04-18
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103006 | F-35A Parts Store |  | 1400000 | CADJ140004; | 2015-04-30 | 2016-01-06 | 2016-04-12 | 85% | 2016-04-05
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar |  |  |  | 2015-03-03 | 2015-12-16 | 2016-03-01 | 94% | 2016-03-31
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Nevada | United States | RKMF113005 | RPA Weapons School |  | 2000000 | CADJ140004; | 2014-08-12 | 2016-02-15 | 2016-05-03 | 76% | 2016-07-15
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Nevada | United States | RKMF123007 | F-35A Weapons School Addition |  |  |  | 2015-08-10 | 2017-04-01 | 2017-04-01 | 6% | 2017-07-15
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Nevada | United States | RKMF133001 | F-22 Flight Simulator Facility |  |  |  | 2015-07-09 | 2017-01-19 | 2017-02-27 | 6% | 2017-02-15
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Nevada | United States | RKMF143001 | F-35A Maintenance Hangar/Amu |  |  |  | 2015-10-22 | 2016-08-15 | 2018-02-15 | 2% | 2018-02-15
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Guam | Guam | SAKW059006 | PRTC - Red Horse Logistics Facility |  |  |  | 2015-03-07 | 2016-04-10 | 2016-06-07 | 69% | 2016-06-07
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | SAKW113003 | PRTC - Red Horse Airfield Operations Facility (TFI) |  |  |  | 2015-03-06 | 2016-07-08 | 2016-07-08 | 39% | 2016-07-08
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Guam | Guam | SAKW113008 | PRTC - Combat Communications Infrastructure Facility |  |  |  | 2015-08-15 | 2016-06-21 | 2016-06-21 | 31% | 2016-06-21
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Guam | Guam | SAKW133005 | PRTC Silver Flag Fire Rescue & Emergency Management Training |  |  |  | 2015-03-30 | 2017-02-01 | 2017-02-01 | 23% | 2016-12-25
2016-04-15 | 2015 | Air Force Active | Major Military Construction | Guam | Guam | SAKW143031 | PRTC Satellite Fire Station |  |  |  | 2015-03-06 | 2016-07-30 | 2016-07-30 | 44% | 2016-07-30
2016-04-15 | 2012 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  |  |  | 2012-10-15 | 2016-02-15 | 2016-12-30 | 68% | 2017-01-17
2016-04-15 | 2011 | Air Force Active | Major Military Construction | Florida | United States | SXHT053001 | Air Force Technical Applications Center |  |  |  | 2012-01-23 | 2015-06-30 | 2016-03-01 | 99% | 2014-03-03
2016-04-15 | 2010 | Air Force Active | Major Military Construction |  | Germany | TYFR053037 | Aerospace Ground Equipment Maintenance Complex |  |  |  | 2012-08-06 | 2013-07-06 | 2016-04-01 | 99% | 2016-05-01
2016-04-15 | 2011 | Air Force Active | Major Military Construction |  | Germany | TYFR083001 | Deicing Fluid Storage & Dispensing Facility |  | 155000 | KRSM103011; | 2012-11-13 | 2013-05-19 | 2016-06-01 | 96% | 2016-06-01
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR106261 | PL-1 Security Measures For Communications Compound |  |  |  | 2014-01-22 | 2014-12-12 | 2016-05-01 | 97% | 2016-05-01
2016-04-15 | 2013 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR126175 | Expand AOC Parking Structure |  |  |  | 2014-08-08 | 2015-02-24 | 2016-05-01 | 99% | 2015-10-22
2016-04-15 | 2011 | Air Force Active | Major Military Construction |  | Germany | TYFU083507R2 | Dormitory (128 Rm) |  |  |  | 2014-06-16 | 2015-07-15 | 2017-07-19 | 99%
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Georgia | United States | UHHZ123001 | Convert Cooler Area B/660 To AFLCMC/WFM C-17 Program Office |  |  |  | 2015-02-11 | 2016-05-11 | 2016-05-11 | 2% | 2016-05-16
2016-04-15 | 2012 | Air Force Active | Major Military Construction |  | Djibouti | USAFE17002 | Combat Aircraft Loading Area |  |  |  | 2012-12-24 | 2014-01-16 | 2016-03-31 | 98% | 2015-10-01
2016-04-15 | 2012 | Air Force Active | Major Military Construction |  | Djibouti | USAFE17003 | Parallel Taxiway Extension |  |  |  | 2012-12-24 | 2014-05-24 | 2016-01-31 | 99% | 2015-10-01
2016-04-15 | 2012 | Air Force Active | Major Military Construction |  | Djibouti | USAFE17004 | Expeditionary Lodging |  |  |  | 2013-03-15 | 2013-09-30 | 2016-01-31 | 99% | 2014-10-20
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | North Carolina | United States | VKAG133001 | Operations Support Squadron/War Room Facility |  |  |  | 2015-07-01 | 2016-01-22 | 2016-01-25 | 36% | 2016-01-25
2016-04-15 | 2008 | Air Force Active | Major Military Construction | South Carolina | United States | VLSB083007 | Base Infrastructure |  |  |  | 2008-10-27 | 2016-06-02 | 2016-06-02 | 99% | 2010-03-08
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction |  | Germany | VYHK143301 | Catch Basin For Storm Water Discharge, Location 2, Welscherw |  |  |  | 2015-09-15 | 2017-09-14 | 2017-10-30 | 2% | 2017-10-30
2016-04-15 | 2014 | Air Force Active | Major Military Construction |  | Greenland | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  |  |  | 2014-08-19 | 2016-06-17 | 2016-06-17 | 55% | 2016-09-14
2016-04-15 | 2013 | Air Force Active | Major Military Construction |  | Greenland | WWCX103032 | Dormitory (48 Pn) |  |  |  | 2013-08-15 | 2015-07-29 | 2015-10-09 | 99% | 2015-10-27
2016-04-15 | 2013 | Air Force Active | Major Military Construction | Florida | United States | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair |  |  |  | 2013-08-21 | 2014-07-20 | 2016-01-21 | 100% | 2015-06-10
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Florida | United States | XLWU103007 | F-22 Muntions Storage Complex |  |  |  | 2015-06-26 | 2016-11-11 | 2016-11-11 | 19% | 2017-01-01
2016-04-15 | 2011 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ084017 | Const Center For Character & Leadership Development |  |  |  | 2013-01-15 | 2014-08-29 | 2016-06-30 | 99% | 2016-06-30
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | XQPZ124003 | Const Perm ECP-Pine Drive |  |  |  | 2015-05-13 | 2015-12-09 | 2016-01-18 | 100% | 2016-01-18
2016-04-15 | 2010 | Air Force Active | Major Military Construction | Oklahoma | United States | XTLF033303 | Control Tower |  |  |  | 2010-10-05 | 2012-02-12 | 2015-12-10 | 100% | 2015-09-18
2016-04-15 | 2012 | Air Force Active | Major Military Construction | Missouri | United States | YWHG071005 | WSA Security Control Facility |  |  |  | 2012-03-16 | 2013-09-06 | 2016-01-06 | 100% | 2014-08-15
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Missouri | United States | YWHG111010 | WSA: Construct Two New MOP Igloos |  |  |  | 2014-08-11 | 2015-11-13 | 2016-01-07 | 100% | 2016-01-07
2016-04-15 | 2014 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV053302 | Add/Alter Foreign Materiel Exploitation Laboratory |  |  |  | 2015-07-13 | 2016-11-16 | 2017-06-02 | 4% | 2017-08-10
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Ohio | United States | ZHTV126003 | Add Standby Generator (NASIC) (P-341) |  |  |  | 2015-09-15 | 2015-11-25 | 2016-04-14 | 10% | 2016-06-30
2016-04-05 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Indiana | United States | CTGB109003 | Reserve Fire Station Annex |  |  |  | 2014-11-04 | 2015-11-04 | 2016-09-18 | 40% | 2016-09-18
2016-04-05 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Texas | United States | DDPM120009 | Add Simulator Bay, Bulding 1792 |  |  |  | 2015-09-30 | 2016-10-28 | 2016-09-28 | 45% | 2016-10-28
2016-04-05 | 2015 | Air Force Reserve | Major Military Construction | Texas | United States | DDPM130008 | Explosive Ordnance Disposal Facility |  |  |  | 2015-08-27 | 2016-07-27 | 2017-01-16 | 2% | 2017-01-16
2016-04-05 | 2012 | Air Force Reserve | Major Military Construction | South Carolina | United States | DKFX079003 | Red Horse Readiness And Training Facility |  |  |  | 2012-07-13 | 2013-03-01 | 2016-06-16 | 92% | 2016-06-16
2016-04-05 | 2014 | Air Force Reserve | Major Military Construction | California | United States | PDPG030130P1 | Joint Regional Deployment And Passenger Terminal Facility |  |  |  | 2015-05-05 | 2016-08-01 | 2017-03-20 | 18% | 2017-03-20
2016-04-05 | 2013 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ099095 | Flight Simulator Facility |  |  |  | 2014-08-05 | 2015-07-31 | 2016-06-13 | 82% | 2016-06-13
2016-04-05 | 2012 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ120572 | Vehicle Maintenance Facility |  |  |  | 2014-09-22 | 2015-03-21 | 2016-03-01 | 100% | 2015-10-25
2016-04-07 | 2014 | Air Force Reserve | Major Military Construction | Oklahoma | United States | WWYK129000 | AIR CONTROL TOWER SQUADRON OPERATIONS |  |  |  | 2016-02-26 |  | 2017-08-31 | 2%
2016-04-15 | 2013 | Air National Guard | Unspecified Minor Military Construction | Indiana | United States | ATQZ099073 | MCCA: A-10 Conversion-Expand Arm/Disarm Apron-T/W Bravo |  |  |  | 2014-12-08 | 2016-04-21 | 2016-04-15 | 99% | 2015-08-15
2016-04-15 | 2012 | Air National Guard | Major Military Construction | Indiana | United States | ATQZ099080 | A-10 Facility Conversion - Munitions Complex |  |  |  | 2014-08-27 | 2015-11-20 | 2016-05-27 | 92% | 2016-03-18
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Massachusetts | United States | AXQD119004 | Add to and Alter Survival Equipment Shop |  |  |  | 2013-07-16 | 2014-02-07 | 2016-02-28 | 100% | 2016-01-31
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Massachusetts | United States | AXQD129074 | F 15 Shop Addition |  |  |  | 2015-01-13 | 2016-07-16 | 2017-07-16 | 15% | 2016-07-16
2016-04-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Tennessee | United States | BKTZ129083 | Construct Cyber SCIF |  |  |  | 2015-10-28 | 2016-10-20 | 2016-10-25 | 3% | 2016-10-25
2016-04-15 | 2014 | Air National Guard | Major Military Construction | Alabama | United States | BRKR999147 | Add to and Alter Distributed Ground Station Facility |  |  |  | 2014-10-31 | 2016-10-23 | 2016-08-02 | 18% | 2016-08-02
2016-04-15 | 2015 | Air National Guard | Major Military Construction | Connecticut | United States | CEKT139004 | Construct C-130 Fuel Cell and Corrosion Control Facility |  |  |  | 2015-07-24 | 2016-12-05 | 2016-12-23 | 5% | 2016-12-23
2016-04-15 | 2013 | Air National Guard | Major Military Construction | Wyoming | United States | DPEZ089017 | C-130 Flight Simulator Training Facility |  |  |  | 2013-09-27 | 2016-03-15 | 2016-05-27 | 99% | 2016-03-25
2016-04-15 | 2015 | Air National Guard | Major Military Construction | Iowa | United States | FFAN139010 | NDAA: Remotely Piloted & Targeting Group Beddown |  |  |  | 2015-07-23 | 2016-08-07 | 2016-08-04 | 48% | 2016-08-29
2016-04-15 | 2014 | Air National Guard | Major Military Construction | New York | United States | FPBB129050 | MQ-9 Flight Training Unit Hangar |  |  |  | 2014-09-25 | 2015-08-04 | 2015-11-20 | 99% | 2015-11-04
2016-04-15 | 2013 | Air National Guard | Major Military Construction | California | United States | HAYW109006 | F-15 Conversion |  |  |  | 2014-12-02 | 2016-02-25 | 2016-04-26 | 93% | 2016-02-15
2016-04-15 | 2013 | Air National Guard | Major Military Construction | Hawaii | United States | KNMD119001 | TFI - F-22 Combat Apron Addition |  |  |  | 2013-10-31 | 2015-04-24 | 2016-04-29 | 98% | 2016-04-29
2016-04-15 | 2014 | Air National Guard | Major Military Construction | Indiana | United States | LDXF099060 | Add/Alter Bldg 37 for Distributed Common Grnd Stn |  |  |  | 2014-10-16 | 2016-02-28 | 2016-06-30 | 62% | 2016-06-30
2016-04-15 | 2014 | Air National Guard | Major Military Construction | Pennsylvania | United States | LKLW109037 | Communications Operations and Training Facility |  |  |  | 2014-10-16 | 2015-10-25 | 2016-05-31 | 98% | 2016-01-15
2016-04-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | LKLW959716 | Consolidate Vehicle Maintenance Function |  |  |  | 2015-10-16 | 2016-07-12 | 2016-07-12 | 11% | 2016-07-12
2016-04-15 | 2015 | Air National Guard | Major Military Construction | Michigan | United States | MBMV129060 | RPA Beddown |  |  |  | 2015-05-07 | 2016-05-14 | 2016-05-06 | 80% | 2016-05-06
2016-04-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | South Carolina | United States | PSTE129092 | Construct North Overrun |  |  |  | 2014-03-11 | 2014-12-24 | 2016-01-29 | 99% | 2014-12-08
2016-04-15 | 2014 | Air National Guard | Major Military Construction | Tennessee | United States | PSXE109034 | TEC Expansion - Dormitory and Classroom Training Facility |  |  |  | 2014-07-22 | 2016-07-21 | 2016-07-20 | 56% | 2016-07-20
2016-04-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Tennessee | United States | PSXE139000 | Taxiway B Extension |  |  |  | 2015-07-10 | 2016-10-18 | 2016-09-30 | 30% | 2016-09-30
2016-04-15 | 2012 | Air National Guard | Major Military Construction | Massachusetts | United States | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities |  |  |  | 2013-09-24 | 2014-09-24 | 2016-03-31 | 95% | 2016-01-28
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Massachusetts | United States | SPBN089050 | Relocate Main Gate |  |  |  | 2015-09-28 | 2016-09-08 | 2016-09-28 | 6% | 2016-09-28
2016-04-15 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139901 | KC-46A ADAL Fuel Cell Building 253 |  |  |  | 2015-08-18 | 2016-11-19 | 2018-02-02 | 12% | 2018-02-02
2016-04-15 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139904 | KC-46A ADAL Maint Hangar Building 254 |  |  |  | 2015-08-18 | 2016-11-18 | 2018-02-02 | 2% | 2018-02-02
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Oregon | United States | TQKD129072 | Construct Alert Hangar Bay |  |  |  | 2014-09-03 | 2015-03-19 | 2016-01-29 | 95% | 2015-07-30
2016-04-15 | 2013 | Air National Guard | Unspecified Minor Military Construction | Oregon | United States | TQKD139018 | Relocate Base Boundary Fence |  |  |  | 2015-02-02 | 2015-08-01 | 2016-02-28 | 79% | 2016-01-01
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Puerto Rico | Puerto Rico | TUMR109004 | Joint Force HQ - ANG Share Fort Buchanan |  |  |  | 2013-11-25 | 2015-10-06 | 2017-03-31 | 98% | 2016-03-18
2016-04-15 | 2014 | Air National Guard | Major Military Construction | Rhode Island | United States | TWLR129077 | C-130J Flight Simulator Training Facility |  |  |  | 2015-03-15 | 2015-12-14 | 2016-06-08 | 65% | 2016-06-02
2016-04-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Missouri | United States | ULYB112022 | Security Forces Admin and Storage Facility |  |  |  | 2014-10-29 | 2015-10-12 | 2016-05-05 | 99% | 2016-01-08
2016-04-15 | 2014 | Air National Guard | Major Military Construction | Ohio | United States | WAAR109002 | Alter Intelligence Operations Facility |  |  |  | 2014-12-01 | 2015-12-01 | 2016-02-29 | 96% | 2016-02-10
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Ohio | United States | WAAR129078 | Relocate Main Gate |  |  |  | 2013-08-27 | 2014-02-23 | 2016-06-30 | 95% | 2014-10-31
2016-04-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Kentucky | United States | WEAS129000 | Realign Grade Lane |  |  |  | 2015-08-20 | 2015-08-20 | 2016-06-15 | 30% | 2016-06-15
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | New York | United States | WKVB099052 | Add to Fire Station |  |  |  | 2015-06-26 | 2016-04-23 | 2016-06-28 | 15% | 2016-06-28
2016-04-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Oklahoma | United States | XHZG129946 | Add to Fire Crash and Rescue Station, Building 403 |  |  |  | 2014-08-20 | 2015-08-15 | 2015-10-08 | 99% | 2015-10-08
2016-04-15 | 2015 | Air National Guard | Major Military Construction | Pennsylvania | United States | ZAWA159061 | RPA Operations Center |  |  |  | 2015-07-20 | 2016-02-15 | 2016-03-31 | 5% | 2016-03-31
2016-03-31 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 1235 | Physical Fitness Facility |  |  |  | 2012-07-12 | 2014-04-10 | 2016-03-16 | 94%
2016-03-31 | 2011 | Army Active | Major Military Construction | Colorado | United States | 13852 | Simulations Center |  |  |  | 2011-11-04 | 2016-07-23 | 2016-07-23 | 95%
2016-03-31 | 2012 | Army Active | Major Military Construction | Louisiana | United States | 17220 | Fire Station |  |  |  | 2013-11-06 | 2015-11-11 | 2016-03-30 | 88%
2016-03-31 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 20697 | Chapel |  |  |  | 2012-09-20 | 2014-01-28 | 2016-01-20 | 93%
2016-03-31 | 2012 | Army Active | Major Military Construction | Kansas | United States | 2728 | Physical Fitness Facility |  |  |  | 2012-03-29 | 2017-02-08 | 2017-02-08 | 88%
2016-03-31 | 2013 | Army Active | Major Military Construction | Virginia | United States | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2013-10-15 | 2017-05-03 | 2017-05-03 | 71%
2016-03-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 45116 | Aircraft Component Maintenance Shop |  |  |  | 2013-08-08 | 2016-02-08 | 2016-02-08 | 88% | 2016-03-08
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 5034 | Vehicle Maintenance Facility |  |  |  | 2013-01-24 | 2014-07-18 | 2016-06-30 | 88%
2016-03-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 51519 | Ballistic Evaluation Center |  |  |  | 2012-12-04 | 2015-02-15 | 2016-02-29 | 98% | 2016-03-31
2016-03-31 | 2014 | Army Active | Major Military Construction | Georgia | United States | 51868 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2015-01-06 | 2016-12-26 | 2017-01-24 | 41%
2016-03-31 | 2015 | Army Active | Major Military Construction | South Carolina | United States | 51937 | Trainee Barracks Complex 3, Ph1 |  |  |  | 2016-03-17 | 2018-03-17 | 2018-03-17 | 0%
2016-03-31 | 2014 | Army Active | Major Military Construction | Virginia | United States | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  | 2014-10-09 | 2017-12-09 | 2017-12-09 | 48%
2016-03-31 | 2011 | Army Active | Major Military Construction | California | United States | 53789 | Advanced Individual Training Barracks |  |  |  | 2013-10-22 | 2015-01-05 | 2016-12-01 | 16%
2016-03-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 54106 | Automated Multipurpose Machine Gun Range |  |  |  | 2014-08-18 | 2016-02-09 | 2016-02-09 | 95% | 2016-02-09
2016-03-31 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 55121 | Aerial Gunnery Range |  |  |  | 2015-12-31 | 2017-12-30 | 2017-12-30 | 15%
2016-03-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 55460 | Aircraft Paint Shop |  |  |  | 2013-10-22 | 2016-02-14 | 2016-02-14 | 60% | 2016-02-13
2016-03-31 | 2012 | Army Active | Major Military Construction | Utah | United States | 55823 | Life Sciences Test Facility Addition |  |  |  | 2012-08-29 | 2015-02-15 | 2016-03-03 | 97%
2016-03-31 | 2012 | Army Active | Major Military Construction |  | Germany | 55985 | Chapel |  |  |  | 2013-11-21 | 2016-03-23 | 2016-09-30 | 72%
2016-03-31 | 2011 | Army Active | Major Military Construction | Hawaii | United States | 56024 | Flood Mitigation |  |  |  | 2012-10-17 | 2014-10-14 | 2016-09-01 | 98%
2016-03-31 | 2012 | Army Active | Major Military Construction | Virginia | United States | 57508 | Information Dominance Center, Ph 1 |  |  |  | 2013-08-19 | 2015-03-12 | 2015-11-20 | 95% | 2015-10-16
2016-03-31 | 2012 | Army Active | Major Military Construction |  | Germany | 57594 | Satellite Communications Center |  |  |  | 2014-03-14 | 2015-10-05 | 2016-03-15 | 99%
2016-03-31 | 2011 | Army Active | Major Military Construction | Maryland | United States | 57595 | Wideband SATCOM Operations Center |  |  |  | 2011-09-06 | 2015-12-22 | 2015-12-11 | 98% | 2015-12-11
2016-03-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 58046 | Operational Readiness Training Cplx, Ph 1 |  |  |  | 2013-05-21 | 2014-11-12 | 2015-10-30 | 95% | 2015-11-03
2016-03-31 | 2011 | Army Active | Major Military Construction | Kentucky | United States | 58675 | Mout Collective Training Facility |  |  |  | 2011-07-06 | 2016-10-15 | 2016-08-16 | 96%
2016-03-31 | 2008 | Army Active | Major Military Construction |  | Korea, South | 58784 | Barracks Complex |  |  |  | 2008-04-22 | 2014-09-07 | 2016-04-15 | 97% | 2016-03-07
2016-03-31 | 2012 | Army Active | Major Military Construction |  | Germany | 58925 | Satellite Communications Center |  |  |  | 2014-03-14 | 2016-07-07 | 2017-01-13 | 50%
2016-03-31 | 2013 | Army Active | Major Military Construction | South Carolina | United States | 58970 | Trainee Barracks Complex 2, Ph 2 |  |  |  | 2013-12-04 | 2015-05-28 | 2015-11-05 | 99% | 2016-03-31
2016-03-31 | 2011 | Army Active | Major Military Construction | New York | United States | 59044 | Science Facility, Ph 2 |  |  |  | 2011-11-17 | 2015-11-14 | 2016-04-29 | 97%
2016-03-31 | 2013 | Army Active | Major Military Construction | Colorado | United States | 59626 | Digital Multipurpose Training Range |  |  |  | 2013-09-18 | 2015-03-12 | 2015-10-15 | 96% | 2016-02-26
2016-03-31 | 2011 | Army Active | Major Military Construction |  | Germany | 60555 | Information Processing Center |  |  |  | 2012-06-18 | 2014-06-01 | 2016-03-29 | 98%
2016-03-31 | 2011 | Army Active | Major Military Construction | Virginia | United States | 61453 | Replace Fire Station |  |  |  | 2013-06-05 | 2014-11-27 | 2016-03-31 | 96% | 2016-03-31
2016-03-31 | 2012 | Army Active | Major Military Construction | Alaska | United States | 61515 | Physical Fitness Facility |  |  |  | 2013-03-16 | 2014-12-06 | 2016-01-22 | 90% | 2016-01-22
2016-03-31 | 2013 | Army Active | Major Military Construction | Kentucky | United States | 61810 | Battalion Headquarters Complex |  |  |  | 2013-07-15 | 2015-08-26 | 2015-10-19 | 100% | 2015-10-19
2016-03-31 | 2012 | Army Active | Major Military Construction |  | Germany | 61842 | Access Control Point |  |  |  | 2015-05-11 | 2016-12-01 | 2016-12-01 | 44%
2016-03-31 | 2014 | Army Active | Major Military Construction | Maryland | United States | 62204 | Hazardous Material Storage Building |  |  |  | 2016-02-23 | 2017-08-16 | 2017-09-20 | 0%
2016-03-31 | 2012 | Army Active | Major Military Construction | California | United States | 62657 | Water Treatment Plant |  |  |  | 2012-10-19 | 2015-10-19 | 2016-07-06 | 94%
2016-03-31 | 2013 | Army Active | Major Military Construction |  | Japan | 62783 | Satellite Communications Facility |  |  |  | 2014-11-21 | 2021-06-09 | 2021-12-06 | 17%
2016-03-31 | 2011 | Army Active | Major Military Construction | California | United States | 63015 | Satellite Communications Facility |  |  |  | 2011-09-21 | 2016-09-30 | 2016-10-22 | 30%
2016-03-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 64014 | Battalion Complex |  |  |  | 2012-07-25 | 2015-04-08 | 2016-10-24 | 95%
2016-03-31 | 2012 | Army Active | Major Military Construction | Missouri | United States | 64365 | Vehicle Maintenance Facility |  |  |  | 2012-09-18 | 2014-08-25 | 2016-04-29 | 94%
2016-03-31 | 2012 | Army Active | Major Military Construction | Louisiana | United States | 64415 | Brigade Complex |  |  |  | 2012-05-15 | 2014-04-02 | 2016-01-08 | 99% | 2016-01-27
2016-03-31 | 2013 | Army Active | Major Military Construction | Washington | United States | 64456 | Battalion Complex |  |  |  | 2013-06-26 | 2015-02-12 | 2016-05-31 | 94%
2016-03-31 | 2011 | Army Active | Major Military Construction | Missouri | United States | 64520 | Information Systems Facility |  |  |  | 2011-07-12 | 2016-04-18 | 2016-04-18 | 98%
2016-03-31 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 64753 | Vehicle Maintenance Facility |  |  |  | 2012-07-19 | 2014-04-11 | 2015-11-06 | 95%
2016-03-31 | 2011 | Army Active | Major Military Construction | Hawaii | United States | 64760 | Training Aids Center |  |  |  | 2012-10-31 | 2014-08-17 | 2016-04-15 | 90%
2016-03-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 64939 | Applied Instruction Facility |  |  |  | 2012-11-20 | 2014-11-20 | 2016-01-10 | 99% | 2016-03-10
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 65374 | Operational Readiness Training Complex |  |  |  | 2012-09-05 | 2014-11-28 | 2016-04-29 | 97%
2016-03-31 | 2011 | Army Active | Major Military Construction | Hawaii | United States | 65650 | Command and Control Facility, Ph 1 |  |  |  | 2012-04-03 | 2014-04-23 | 2015-10-23 | 98%
2016-03-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 65679 | Vehicle Maintenance Shop |  |  |  | 2013-06-27 | 2016-08-06 | 2016-08-06 | 88%
2016-03-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 65755 | Brigade Complex |  |  |  | 2012-12-12 | 2015-12-12 | 2017-08-08 | 79%
2016-03-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 66023 | Automated Infantry Platoon Battle Course |  |  |  | 2014-07-08 | 2016-09-09 | 2016-10-12 | 73%
2016-03-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 66099 | Battalion Complex Facilities |  |  |  | 2013-07-01 | 2016-05-05 | 2016-09-02 | 79%
2016-03-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 66206 | Infrastructure, Ph 1 |  |  |  | 2012-09-17 | 2015-09-10 | 2016-04-15 | 96%
2016-03-31 | 2010 | Army Active | Major Military Construction | Oklahoma | United States | 66545 | General Purpose Storage Building |  |  |  | 2010-11-22 | 2015-09-22 | 2016-01-20 | 99% | 2016-01-25
2016-03-31 | 2011 | Army Active | Major Military Construction |  | Germany | 66595 | Barracks Complex |  |  |  | 2015-03-23 | 2017-09-28 | 2017-09-28 | 36%
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 |  |  |  | 2012-04-24 | 2014-06-02 | 2016-05-31 | 95% | 2015-12-17
2016-03-31 | 2009 | Army Active | Major Military Construction | New Jersey | United States | 66725 | Ballistic Evaluation Facility Ph 1 |  |  |  | 2012-12-04 | 2014-06-04 | 2016-02-29 | 87% | 2016-03-31
2016-03-31 | 2010 | Army Active | Major Military Construction | New Jersey | United States | 66726 | Ballistic Evaluation Facility, Ph 2 |  |  |  | 2012-12-04 | 2014-06-04 | 2016-02-29 | 95% | 2016-03-31
2016-03-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 66750 | Auto Technology Evaluation Fac, Ph 3 |  |  |  | 2012-10-17 | 2014-09-23 | 2015-10-27 | 99% | 2015-12-11
2016-03-31 | 2011 | Army Active | Major Military Construction |  | Germany | 66834 | Vehicle Maintenance Shop |  |  |  | 2011-12-12 | 2013-12-18 | 2016-01-15 | 95% | 2016-03-31
2016-03-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 67116 | Aviation Battalion Complex |  |  |  | 2014-04-23 | 2016-09-06 | 2016-09-06 | 86%
2016-03-31 | 2014 | Army Active | Major Military Construction | Hawaii | United States | 67157 | Command and Control Facility - Admin |  |  |  | 2015-09-25 | 2017-12-13 | 2017-12-13 | 5%
2016-03-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 68050 | Command and Control Facility |  |  |  | 2016-02-24 | 2018-02-13 | 2018-02-13 | 11%
2016-03-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 68530 | Barracks |  |  |  | 2015-11-18 | 2017-05-11 | 2017-05-11 | 4%
2016-03-31 | 2011 | Army Active | Major Military Construction |  | Germany | 68866 | Sensitive Compartmented Information Fac |  |  |  | 2013-02-13 | 2015-09-19 | 2017-01-31 | 59%
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 68993 | Electronics Maintenance Facility |  |  |  | 2012-08-08 | 2013-12-16 | 2016-01-31 | 99% | 2014-06-27
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 69286 | Infrastructure |  |  |  | 2012-08-20 | 2013-09-13 | 2016-01-31 | 73% | 2012-10-22
2016-03-31 | 2012 | Army Active | Major Military Construction | Hawaii | United States | 69489 | Combat Aviation Brigade Complex, Ph 1 |  |  |  | 2012-07-30 | 2015-05-27 | 2016-02-13 | 80%
2016-03-31 | 2015 | Army Active | Major Military Construction | Pennsylvania | United States | 69649 | Rebuild Shop |  |  |  | 2015-11-12 | 2017-03-26 | 2017-03-05 | 1%
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 69828 | Unmanned Aerial Vehicle Maintenance Hangar |  |  |  | 2014-08-27 | 2016-01-04 | 2016-07-15 | 79%
2016-03-31 | 2012 | Army Active | Major Military Construction | Kansas | United States | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  |  |  | 2012-12-11 | 2015-07-31 | 2016-02-08 | 97% | 2016-02-10
2016-03-31 | 2012 | Army Active | Major Military Construction | North Carolina | United States | 69835 | Unmanned Aerial Vehicle Maintenance Hangar |  |  |  | 2015-01-05 | 2016-02-29 | 2016-04-04 | 72%
2016-03-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 71120 | Training Aids Center |  |  |  | 2013-10-17 | 2015-04-10 | 2016-04-19 | 94%
2016-03-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 71221 | Fire Station |  |  |  | 2014-08-27 | 2016-02-18 | 2016-06-13 | 72%
2016-03-31 | 2010 | Army Active | Military Family Housing |  | Germany | 71421 | Family Housing Replacement Construction |  |  |  | 2015-04-07 | 2017-04-23 | 2017-06-22 | 6%
2016-03-31 | 2011 | Army Active | Military Family Housing |  | Germany | 71422 | Family Housing Replacement Construction |  |  |  | 2015-04-07 | 2015-09-24 | 2018-07-27 | 5%
2016-03-31 | 2010 | Army Active | Major Military Construction |  | Kuwait | 71485 | APS Warehouses |  | 11339000 | 58925, 62783 | 2013-10-25 | 2015-10-30 | 2015-12-31 | 90% | 2016-03-31
2016-03-31 | 2010 | Army Active | Major Military Construction |  | Afghanistan | 71488 | Coalition Operation Center |  |  |  | 2012-03-16 | 2014-09-14 | 2015-10-01 | 99% | 2015-06-29
2016-03-31 | 2014 | Army Active | Major Military Construction | Missouri | United States | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  |  |  | 2014-08-05 | 2016-08-04 | 2016-11-17 | 48%
2016-03-31 | 2011 | Army Active | Major Military Construction | Georgia | United States | 71583 | Battalion Complex |  |  |  | 2011-09-28 | 2015-12-21 | 2015-12-16 | 98% | 2016-01-15
2016-03-31 | 2011 | Army Active | Major Military Construction | Texas | United States | 71639 | Brigade Complex |  |  |  | 2011-07-13 | 2015-01-30 | 2016-03-30 | 99% | 2016-03-31
2016-03-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 71675 | Flight Equipment Complex |  |  |  | 2014-01-15 | 2016-01-15 | 2017-03-08 | 85%
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 71682 | Vehicle Maintenance Facility |  |  |  | 2012-06-22 | 2015-01-25 | 2016-04-22 | 97%
2016-03-31 | 2012 | Army Active | Major Military Construction |  | Korea, South | 72650 | Barracks |  |  |  | 2012-02-24 | 2015-12-05 | 2015-11-25 | 100%
2016-03-31 | 2011 | Army Active | Major Military Construction | Washington | United States | 72854 | Regional Logistic Support Complex |  |  |  | 2011-10-12 | 2015-10-24 | 2015-10-19 | 98% | 2015-12-23
2016-03-31 | 2013 | Army Active | Major Military Construction | Georgia | United States | 73008 | Unmanned Aerial Vehicle Complex |  |  |  | 2013-11-06 | 2015-03-01 | 2015-12-01 | 98% | 2015-12-01
2016-03-31 | 2015 | Army Active | Major Military Construction | Virginia | United States | 73272 | Tactical Vehicle Hardstand |  |  |  | 2015-10-21 | 2016-10-20 | 2016-10-20 | 0%
2016-03-31 | 2014 | Army Active | Major Military Construction | Maryland | United States | 73384 | Entry Control Point |  |  |  | 2015-10-08 | 2017-03-31 | 2017-03-31 | 1%
2016-03-31 | 2015 | Army Active | Major Military Construction | Kentucky | United States | 73542 | Unmanned Aerial Vehicle Hangar |  |  |  | 2015-09-04 | 2017-04-26 | 2017-05-11 | 23%
2016-03-31 | 2014 | Army Active | Major Military Construction | Texas | United States | 74638 | Control Tower |  |  |  | 2015-04-28 | 2017-01-02 | 2017-01-30 | 18%
2016-03-31 | 2011 | Army Active | Unspecified Minor Military Construction | Ohio | United States | 74757 | Fire Alarm System |  |  |  | 2012-09-05 | 2013-08-01 | 2015-12-04 | 99% | 2013-01-10
2016-03-31 | 2014 | Army Active | Military Family Housing | Wisconsin | United States | 74861 | Family Housing New Construction |  |  |  | 2014-08-20 | 2016-08-09 | 2016-09-19 | 23%
2016-03-31 | 2014 | Army Active | Major Military Construction | Missouri | United States | 75019 | Simulator Building |  |  |  | 2014-12-01 | 2015-12-01 | 2016-02-25 | 98% | 2016-02-25
2016-03-31 | 2013 | Army Active | Major Military Construction | Washington | United States | 75165 | Waste Water Treatment Plant |  |  |  | 2014-03-03 | 2016-03-02 | 2016-10-19 | 87%
2016-03-31 | 2015 | Army Active | Military Family Housing | Illinois | United States | 75536 | Family Housing New Construction |  |  |  | 2016-06-06 | 2018-06-06 | 2018-06-06 | 0%
2016-03-31 | 2014 | Army Active | Major Military Construction | Kansas | United States | 76024 | Simulations Center |  |  |  | 2014-09-02 | 2016-02-24 | 2016-08-27 | 45%
2016-03-31 | 2013 | Army Active | Major Military Construction | California | United States | 76086 | Lightning Protection System |  |  |  | 2014-09-16 | 2015-11-10 | 2016-07-07 | 48%
2016-03-31 | 2015 | Army Active | Major Military Construction | California | United States | 76087 | General Purpose Maintenance Shop |  |  |  | 2015-11-30 | 2017-03-31 | 2017-03-31 | 0%
2016-03-31 | 2013 | Army Active | Major Military Construction | California | United States | 76091 | Engineering/Housing Maintenance Shop |  |  |  | 2014-10-08 | 2015-11-12 | 2016-02-23 | 86% | 2016-03-23
2016-03-31 | 2013 | Army Active | Major Military Construction |  | Korea, South | 76196 | Battalion Headquarters Complex |  |  |  | 2013-05-14 | 2015-06-09 | 2016-11-02 | 64%
2016-03-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76586 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2016-11-10 | 82%
2016-03-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76587 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2016-11-10 | 85%
2016-03-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 76601 | Aviation Storage Hangar |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 78%
2016-03-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76767 | Aviation Unit Complex, Ph 1A |  |  |  | 2012-07-09 | 2015-08-21 | 2015-10-09 | 99% | 2015-10-09
2016-03-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76768 | Aviation Complex, Ph 1B |  |  |  | 2012-11-29 | 2015-05-21 | 2016-04-01 | 98%
2016-03-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 76776 | Airfield Operations Complex |  |  |  | 2015-05-18 | 2017-07-06 | 2017-07-06 | 24%
2016-03-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 76777 | Aircraft Maintenance Hangar |  |  |  | 2014-09-23 | 2017-07-06 | 2017-07-06 | 41%
2016-03-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76903 | Combat Aviation Brigade Barracks |  |  |  | 2014-06-26 | 2017-01-13 | 2017-04-13 | 33%
2016-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 77187 | Vehicle Maintenance Facility |  |  |  | 2012-06-22 | 2018-05-07 | 2018-05-07 | 96%
2016-03-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77262 | Headquarters Building |  |  |  | 2014-08-21 | 2016-03-31 | 2016-07-18 | 70%
2016-03-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77304 | Aircraft Maintenance Hangar |  |  |  | 2014-08-18 | 2016-08-22 | 2016-09-13 | 65%
2016-03-31 | 2015 | Army Active | Major Military Construction | Colorado | United States | 77305 | Aircraft Maintenance Hangar |  |  |  | 2015-06-16 | 2016-06-15 | 2016-06-15 | 59%
2016-03-31 | 2012 | Army Active | Major Military Construction | Colorado | United States | 77319 | Aircraft Loading Area |  |  |  | 2012-09-05 | 2016-06-11 | 2016-06-11 | 99%
2016-03-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77405 | Aircraft Maintenance Hangar |  |  |  | 2014-07-22 | 2016-08-22 | 2016-09-26 | 43%
2016-03-31 | 2013 | Army Active | Major Military Construction | Georgia | United States | 77419 | Ground Source Heat Transfer System |  |  |  | 2015-01-06 | 2016-12-26 | 2017-01-24 | 78%
2016-03-31 | 2014 | Army Active | Major Military Construction | Florida | United States | 77539 | Automated Sniper Field Fire Range |  |  |  | 2014-12-17 | 2015-12-17 | 2016-02-28 | 92% | 2016-03-31
2016-03-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77885 | Runway |  |  |  | 2014-07-01 | 2015-07-01 | 2016-07-06 | 81% | 2016-03-24
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction | Kentucky | United States | 77980 | Cantonment Area, Roads, Paved |  |  |  | 2014-09-24 | 2015-08-20 | 2015-11-24 | 85% | 2015-12-21
2016-03-31 | 2013 | Army Active | Major Military Construction | District Of Columbia | United States | 78054 | Vehicle Storage Building, Installation |  |  |  | 2015-04-03 | 2016-09-24 | 2017-02-21 | 16%
2016-03-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 78196 | Aviation Battalion Complex |  |  |  | 2016-01-13 | 2017-07-06 | 2017-07-06 | 0%
2016-03-31 | 2012 | Army Active | Military Family Housing Improvement |  | Germany | 78475 | Family Housing Improvements |  |  |  | 2015-01-16 | 2016-09-27 | 2016-09-27 | 36%
2016-03-31 | 2012 | Army Active | Military Family Housing |  | Germany | 78505 | Family Housing New Construction |  |  |  | 2013-08-07 | 2015-09-14 | 2016-02-17 | 93%
2016-03-31 | 2012 | Army Active | Military Family Housing |  | Germany | 78506 | Family Housing New Construction |  |  |  | 2013-09-30 | 2015-10-27 | 2015-10-29 | 96%
2016-03-31 | 2014 | Army Active | Major Military Construction | Kentucky | United States | 78778 | Battlefield Weather Support Facility |  |  |  | 2014-06-27 | 2015-08-21 | 2016-02-22 | 97% | 2016-02-22
2016-03-31 | 2012 | Army Active | Military Family Housing Improvement |  | Germany | 78841 | Family Housing Improvements |  | 6885000 | 74861 | 2012-10-15 | 2018-10-29 | 2016-04-21 | 61%
2016-03-31 | 2012 | Army Active | Military Family Housing Improvement |  | Germany | 79097 | Family Housing Improvements |  | 7650000 | 75536 | 2012-10-15 | 2018-04-02 | 2016-01-22 | 54% | 2016-01-27
2016-03-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 79618 | Simulator Building |  |  |  | 2014-08-20 | 2016-02-11 | 2016-09-23 | 52%
2016-03-31 | 2012 | Army Active | Major Military Construction |  | Unspecified World Wide | 79749 | Forward Operating Site |  |  |  | 2012-07-25 | 2014-11-30 | 2016-07-31 | 81%
2016-03-31 | 2012 | Army Active | Unspecified Minor Military Construction | Maryland | United States | 79846 | Electromag Interference Fac |  |  |  | 2014-10-20 | 2015-12-01 | 2016-04-07 | 100%
2016-03-31 | 2013 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks |  |  |  | 2013-08-26 | 2016-08-30 | 2016-11-15 | 68%
2016-03-31 | 2014 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 2 | 81186 |  |  | 2013-08-26 | 2016-08-30 | 2016-11-15 | 68%
2016-03-31 | 2015 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 3 | 81187 |  |  | 2013-08-26 | 2016-08-30 | 2016-11-15 | 68%
2016-03-31 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 80112 | Unmanned Aerial Vehicle Complex |  |  |  | 2015-05-26 | 2016-07-19 | 2016-09-11 | 37%
2016-03-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 80113 | Unmanned Aerial Vehicle Complex |  |  |  | 2013-10-07 | 2016-01-04 | 2016-05-27 | 97%
2016-03-31 | 2012 | Army Active | Unspecified Minor Military Construction | Maryland | United States | 80231 | Replace Oil Water Separators |  |  |  | 2014-11-03 | 2015-09-25 | 2017-03-18 | 19%
2016-03-31 | 2013 | Army Active | Major Military Construction | New York | United States | 80246 | Aircraft Maintenance Hangar |  |  |  | 2013-06-27 | 2015-12-02 | 2017-03-01 | 78%
2016-03-31 | 2013 | Army Active | Unspecified Minor Military Construction | Virginia | United States | 80317 | WATER DISTRIBUTION LINES, POTABLE |  |  |  | 2014-01-13 | 2014-09-10 | 2016-03-15 | 90% | 2016-01-31
2016-03-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 80433 | Central Energy Plant |  |  |  | 2015-10-27 | 2016-10-26 | 2016-10-26 | 6%
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction | Washington | United States | 80919 | Underground Electric Lines |  |  |  | 2015-02-13 | 2016-02-13 | 2016-02-13 | 98% | 2016-02-13
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction | Hawaii | United States | 80992 | Upgrade Power Distribution |  |  |  | 2015-04-29 | 2016-10-20 | 2016-10-20 | 9%
2016-03-31 | 2013 | Army Active | Unspecified Minor Military Construction | Utah | United States | 81106 | POLICE/MP STATION |  |  |  | 2013-10-18 | 2014-12-17 | 2016-02-09 | 94% | 2016-02-09
2016-03-31 | 2014 | Army Active | Major Military Construction | Texas | United States | 81155 | Unmanned Aerial Vehicle Complex |  |  |  | 2014-12-18 | 2016-04-11 | 2016-04-27 | 82%
2016-03-31 | 2015 | Army Active | Military Family Housing |  | Korea, South | 81230 | Family Housing New Construction |  |  |  | 2015-08-19 | 2018-04-28 | 2018-04-28 | 1%
2016-03-31 | 2015 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81242 | General Purpose Maintenance Shop |  |  |  | 2015-10-28 | 2016-10-27 | 2016-10-27 | 5%
2016-03-31 | 2015 | Army Active | Major Military Construction | New York | United States | 81349 | Unmanned Aerial Vehicle Hangar |  |  |  | 2015-06-22 | 2016-12-18 | 2017-01-11 | 15%
2016-03-31 | 2015 | Army Active | Major Military Construction | Colorado | United States | 81357 | Unmanned Aerial Vehicle Hangar |  |  |  | 2015-08-27 | 2017-01-18 | 2017-01-18 | 12%
2016-03-31 | 2015 | Army Active | Major Military Construction | California | United States | 81372 | Unmanned Aerial Vehicle Hangar |  |  |  | 2015-11-18 | 2017-12-16 | 2017-12-16 | 0%
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81424 | Tracking Equipment Support Fac |  |  |  | 2015-11-10 | 2017-02-02 | 2017-02-02 | 1%
2016-03-31 | 2013 | Army Active | Unspecified Minor Military Construction |  | Marshall Islands | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  |  |  | 2014-10-28 | 2015-10-23 | 2016-04-22 | 60%
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction | Oklahoma | United States | 82394 | Decontamination Facility |  |  |  | 2016-02-18 | 2017-02-12 | 2017-02-12 | 0%
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 85260 | Secure Operations Center |  |  |  | 2014-11-05 | 2015-11-05 | 2016-01-13 | 93%
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction |  | Germany | 85817 | CANTONMENT AREA ROADS, PAVED |  |  |  | 2016-03-15 | 2016-08-01 | 2016-08-01 | 0%
2016-03-31 | 2014 | Army Active | Major Military Construction | California | United States | 86033 | Water Well, Potable |  |  |  | 2015-11-13 | 2016-09-08 | 2016-09-08 | 1%
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Alabama | United States | 010278 | Live Fire Shoot House |  |  |  | 2013-11-12 | 2014-11-11 | 2015-06-08 | 98% | 2015-06-08 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Alabama | United States | 011007 | National Guard Readiness Center, Add/Alt |  |  |  | 2013-12-31 | 2014-10-01 | 2014-12-19 | 98% | 2014-12-14
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Alabama | United States | 011014 | National Guard Readiness Center Add/Alt |  |  |  | 2014-10-07 | 2015-12-10 | 2016-04-22 | 97% | 2015-12-10
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Arizona | United States | 040294 | Readiness Center |  |  |  | 2012-09-12 | 2013-10-16 | 2014-01-31 | 100% | 2013-11-04 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Arizona | United States | 040669 | Underground Electrical Lines |  |  |  | 2014-05-05 | 2014-10-31 | 2014-10-31 | 100% | 2014-10-31
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Arkansas | United States | 050182 | Scout REECE Gunnery Complex |  |  |  | 2014-12-01 | 2016-12-01 | 2016-12-01 | 45% | 2016-12-01
2016-04-08 | 2010 | Army National Guard | Major Military Construction | California | United States | 060115 | Readiness Center, PH 1 |  | 2900000 | 390263 | 2010-11-15 | 2012-02-06 | 2015-01-30 | 99% | 2013-10-07 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505) | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | California | United States | 060170 | Field Maintenance Shop |  |  |  | 2012-11-08 | 2013-10-14 | 2014-06-06 | 98% | 2013-10-20 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | California | United States | 060413 | Maneuver Area Training & Equipment Site Ph 3 |  |  |  | 2013-10-21 | 2014-10-01 | 2016-02-29 | 100% | 2016-02-29 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 ($1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)} | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 ($1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)}
2016-04-08 | 2011 | Army National Guard | Major Military Construction | California | United States | 060429 | Combined Arms Collective Training Facility |  | 6700000 | 361103 | 2011-12-05 | 2012-06-29 | 2013-09-27 | 99% | 2013-06-15 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2016-04-08 | 2012 | Army National Guard | Unspecified Minor Military Construction | California | United States | 060432 | Barracks |  |  |  | 2012-10-15 | 2013-09-20 | 2014-10-30 | 99% | 2013-10-07 | FY07 Congressionally Directed, Used FY10 funds | FY07 Congressionally Directed, Used FY10 funds
2016-04-08 | 2012 | Army National Guard | Major Military Construction | California | United States | 060438 | Tactical Unmanned Aircraft System Facility |  |  |  | 2012-08-06 | 2013-10-28 | 2015-06-02 | 99% | 2013-11-11 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835) | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Connecticut | United States | 090043 | Combined Support Maintenance Shop |  |  |  | 2014-04-26 | 2015-10-01 | 2016-08-16 | 95% | 2015-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Unspecified Minor Military Construction | Connecticut | United States | 090088 | Storage Building General Purpose, Installation |  |  |  | 2015-12-01 | 2016-09-26 | 2016-11-30 | 15% | 2016-11-30
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Delaware | United States | 100010 | Regional Training Institute Ph1 |  |  |  | 2013-09-23 | 2014-09-23 | 2014-12-04 | 99% | 2014-12-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), Construction is finish, project completion is pending all closeout documentation | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), Construction is finish, project completion is pending all closeout documentation
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Florida | United States | 120102 | Readiness Center |  |  |  | 2014-01-21 | 2015-07-26 | 2016-02-24 | 98% | 2015-09-13 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) & Formal Reprogramming $5,482 funds from FY12 project savings {PNs: 060009 ($4,452) & 240187 ($1,030)} | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) & Formal Reprogramming $5,482 funds from FY12 project savings {PNs: 060009 ($4,452) & 240187 ($1,030)}
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Florida | United States | 120195 | Ready Building |  |  |  | 2015-05-11 | 2016-04-05 | 2016-04-05 | 95% | 2016-04-05
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Florida | United States | 120228 | Ready Building |  |  |  | 2014-09-08 | 2015-05-16 | 2015-09-22 | 99% | 2015-09-23 | Awaiting final pay request and close-out docoumentation | Awaiting final pay request and close-out docoumentation
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Georgia | United States | 130063 | Maneuver Area Training and Equipment Site, Ph 1 |  |  |  | 2012-10-19 | 2013-10-28 | 2016-01-22 | 98% | 2016-01-22 | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077 | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Georgia | United States | 130068 | Readiness Center Ph 1 |  |  |  | 2012-09-14 | 2014-03-14 | 2014-10-14 | 100% | 2013-04-12 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Georgia | United States | 130120 | Readiness Center |  |  |  | 2012-09-10 | 2013-10-28 | 2014-11-24 | 100% | 2013-11-18 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | Major Military Construction | Georgia | United States | 130123 | Readiness Center, Add/Alt |  |  |  | 2012-06-04 | 2013-09-30 | 2014-04-30 | 100% | 2013-09-30 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | Major Military Construction | Georgia | United States | 130127 | Readiness Center |  |  |  | 2011-12-01 | 2012-11-16 | 2012-11-16 | 98% | 2013-05-15 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Guam | Guam | 140040 | JFHQ Ph 4 |  |  |  | 2013-09-25 | 2015-04-29 | 2015-11-20 | 99% | 2014-10-20 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2010 | Army National Guard | Major Military Construction | Guam | Guam | 140300 | Readiness Center |  | 3000000 | 530035 | 2010-05-03 | 2012-01-07 | 2012-11-16 | 100% | 2012-04-12 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537) | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Hawaii | United States | 150023 | Army Aviation Support Facility Ph1 |  |  |  | 2014-11-12 | 2016-11-01 | 2016-11-01 | 70% | 2016-11-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)} | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2016-04-08 | 2011 | Army National Guard | Major Military Construction | Idaho | United States | 160093 | Barracks (ORTC), Ph 1 |  | 2600000 | 300216 | 2011-08-27 | 2013-02-28 | 2014-04-15 | 100% | 2013-10-03 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Idaho | United States | 160100 | ORTC (Barracks) Ph2 |  |  |  | 2013-10-07 | 2014-08-01 | 2016-03-09 | 92% | 2014-08-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Illinois | United States | 170033 | National Guard Readiness Center |  |  |  | 2014-08-14 | 2016-10-01 | 2017-03-12 | 65% | 2017-03-12
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Illinois | United States | 170127 | Aircraft Maintenance Hangar |  |  |  | 2014-08-14 | 2016-10-01 | 2017-03-12 | 65% | 2017-03-12
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Indiana | United States | 180106 | Field Maintenance Shop |  |  |  | 2014-07-21 | 2014-12-25 | 2015-11-01 | 95% | 2016-01-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Indiana | United States | 180144 | Armed Forces Reserve Center Add/Alt |  |  |  | 2014-04-21 | 2015-08-23 | 2016-01-05 | 100% | 2015-05-29 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Kansas | United States | 200102 | Taxiway, Ramp & Hangar Alterations |  |  |  | 2013-07-22 | 2014-10-01 | 2014-07-04 | 99% | 2014-05-02 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Kansas | United States | 200127 | Water Distribution Lines, Portable |  |  |  | 2014-04-07 | 2014-06-13 | 2015-04-02 | 95% | 2014-06-13
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Kentucky | United States | 210001 | Army Aviation Support Facility |  |  |  | 2013-07-08 | 2014-10-01 | 2015-08-16 | 99% | 2015-10-21 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Louisiana | United States | 220241 | National Guard Readiness Center |  |  |  | 2014-09-22 | 2016-10-30 | 2016-10-30 | 72% | 2016-10-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353) | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Maine | United States | 230046 | Readiness Center |  |  |  | 2012-09-26 | 2014-07-11 | 2016-03-30 | 99% | 2015-08-28 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2015 | Army National Guard | Major Military Construction | Maine | United States | 230113 | National Guard Reserve Center |  |  |  | 2015-08-20 | 2017-08-03 | 2017-08-03 | 12% | 2017-08-03 | Using State procedures the contract number is the same as the project number plus -D to delineate Construction | Using State procedures the contract number is the same as the project number plus -D to delineate Construction
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Maryland | United States | 240017 | Readiness Center Add/Alt |  |  |  | 2012-10-01 | 2014-09-22 | 2016-01-25 | 100% | 2016-02-06 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2015 | Army National Guard | Major Military Construction | Maryland | United States | 240165 | National Guard Readiness Center |  |  |  | 2015-10-19 | 2017-10-29 | 2017-10-29 | 10% | 2017-10-29
2016-04-08 | 2011 | Army National Guard | Major Military Construction | Maryland | United States | 240186 | Tactical Unmanned Aircraft System Facility |  |  |  | 2012-06-01 | 2013-06-15 | 2014-11-21 | 99% | 2014-12-06 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Maryland | United States | 240187 | Readiness Center Add/Alt |  | 1030000 | 120102 | 2012-10-01 | 2014-09-22 | 2015-03-20 | 100% | 2015-03-01 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Maryland | United States | 240193 | Readiness Center |  |  |  | 2012-10-01 | 2014-09-22 | 2016-06-01 | 95% | 2016-06-01 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Maryland | United States | 240194 | Combat Pistol/MP Firearms Qualification Course |  |  |  | 2015-06-01 | 2014-09-22 | 2016-03-29 | 85% | 2016-03-29
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Massachusetts | United States | 250065 | Unit Training Equipment Site |  |  |  | 2014-04-07 | 2015-07-30 | 2015-10-15 | 35% | 2015-07-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Massachusetts | United States | 250095 | Enlisted Barracks, Transient Training Addition |  |  |  | 2014-09-15 | 2016-11-01 | 2016-11-01 | 1% | 2016-11-01
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Massachusetts | United States | 250135 | Readiness Center |  |  |  | 2012-12-01 | 2013-10-28 | 2014-10-28 | 100% | 2013-11-18 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Massachusetts | United States | 250196 | Water Well, Non-Potable |  |  |  | 2013-06-03 | 2013-12-01 | 2013-12-01 | 1% | 2013-12-02
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Michigan | United States | 260051 | Enlisted Barracks, Transient Training |  |  |  | 2014-08-11 | 2016-10-01 | 2016-10-01 | 45% | 2016-10-01
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Minnesota | United States | 270014 | National Guard Readiness Center |  |  |  | 2014-10-22 | 2016-04-15 | 2016-04-24 | 65% | 2016-04-24
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Minnesota | United States | 270236 | Scout Reconnaissance Range |  |  |  | 2013-09-23 | 2015-10-01 | 2016-06-30 | 99% | 2015-08-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Minnesota | United States | 270238 | Readiness Center |  |  |  | 2013-09-30 | 2015-10-15 | 2015-11-29 | 100% | 2016-01-06 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Mississippi | United States | 280272 | National Guard Readiness Center |  |  |  | 2014-09-03 | 2016-04-30 | 2016-09-07 | 70% | 2016-04-30
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Mississippi | United States | 280423 | Water Supply/Treatment Building, Potable |  |  |  | 2014-08-27 | 2016-11-30 | 2016-11-30 | 10% | 2016-11-30
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Missouri | United States | 290176 | Regional Training Institute |  |  |  | 2015-01-31 | 2015-01-31 | 2015-08-01 | 99% | 2015-08-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011); withholding money for site work & LEED cert | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011); withholding money for site work & LEED cert
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Missouri | United States | 290191 | National Guard Vehicle Maintenance Shop |  |  |  | 2015-06-26 | 2015-06-26 | 2015-12-31 | 95% | 2015-10-27 | Taken beneficial occupancy of building; witholding money for site work & LEED cert / contracted lagoon work separtely to meet State code, completion 9May16 | Taken beneficial occupancy of building; witholding money for site work & LEED cert / contracted lagoon work separtely to meet State code, completion 9May16
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Missouri | United States | 290221 | Aircraft Maintenance Hangar |  |  |  | 2015-10-06 | 2015-10-06 | 2015-10-06 | 99% | 2015-10-05 | Final Closeout documents; As-Builts; (New code stating Optical Flame Detectors not yet required. We have proposal but are checking estimates) | Final Closeout documents; As-Builts; (New code stating Optical Flame Detectors not yet required. We have proposal but are checking estimates)
2016-04-08 | 2015 | Army National Guard | Major Military Construction | Montana | United States | 300128 | National Guard Readiness Center Add/Alt |  |  |  | 2015-05-13 | 2017-05-31 | 2017-05-13 | 37% | 2017-05-31
2016-04-08 | 2015 | Army National Guard | Major Military Construction | Montana | United States | 300216 | Dining Facility Transient Training |  |  |  | 2015-10-19 | 2017-06-24 | 2016-08-22 | 20% | 2016-09-09 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY11, PN: 160093) | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY11, PN: 160093)
2016-04-08 | 2012 | Army National Guard | Unspecified Minor Military Construction | Nevada | United States | 320141 | Clark County Armory, Add/Alt |  |  |  | 2016-04-04 | 2017-06-23 | 2017-06-23 | 48% | 2016-07-23 | FY10 Congressionally Directed | FY10 Congressionally Directed
2016-04-08 | 2010 | Army National Guard | Major Military Construction | Nevada | United States | 320143 | Readiness Center |  | 3112000 | 060413 | 2010-10-25 | 2012-01-23 | 2013-04-19 | 99% | 2013-05-01 | PL 112-25 (Budget Control Act, 2011), (Closeout procedures are in progress) Working one warranty item prior to closeout | PL 112-25 (Budget Control Act, 2011), (Closeout procedures are in progress) Working one warranty item prior to closeout
2016-04-08 | 2011 | Army National Guard | Major Military Construction | New Hampshire | United States | 330034 | Classroom Facility (Regional Training Institute) |  |  |  | 2011-11-07 | 2013-06-01 | 2016-04-01 | 70% | 2016-04-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | Major Military Construction | New Hampshire | United States | 330035 | Barracks Facility (Regional Training Institute) |  |  |  | 2011-11-07 | 2013-06-01 | 2016-04-01 | 95% | 2016-04-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | New Hampshire | United States | 330053 | National Guard Readiness Center, Add/Alt |  |  |  | 2016-05-16 | 2017-02-15 | 2017-02-15 | 1% | 2018-04-02
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | New Hampshire | United States | 330057 | National Guard Readiness Center, Add/Alt |  |  |  | 2015-10-19 | 2017-06-09 | 2016-10-31 | 50% | 2016-10-31
2016-04-08 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340110 | Regional Training Institute |  |  |  | 2014-10-15 | 2016-02-12 | 2016-02-12 | 75% | 2016-02-12 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | New Jersey | United States | 340115 | Army Aviation Support Facility |  |  |  | 2012-09-19 | 2014-10-18 | 2015-01-31 | 100% | 2015-01-31 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | New Jersey | United States | 340130 | Communication Lines and Ductbank, Underground |  |  |  | 2014-10-03 | 2015-08-31 | 2016-03-30 | 99% | 2015-08-31 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | New York | United States | 360139 | Combined Support Maintenance Shop |  |  |  | 2016-04-04 | 2017-12-30 | 2017-12-30 | 3% | 2018-01-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Major Military Construction | New York | United States | 360161 | National Guard Readiness Center Alteration |  |  |  | 2014-10-20 | 2016-05-30 | 2016-11-21 | 46% | 2016-12-01 | Formal Reprogramming $3,814 funds from FY11 project savings (PN: 090010) | Formal Reprogramming $3,814 funds from FY11 project savings (PN: 090010)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | New York | United States | 361103 | Access Control Point |  |  |  | 2016-03-07 | 2016-11-05 | 2016-11-05 | 2% | 2016-12-01 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY11, PN: 060429) | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY11, PN: 060429)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | North Dakota | United States | 380053 | National Guard Vehicle Maintenance Shop Addition |  |  |  | 2014-10-06 | 2015-10-30 | 2015-12-11 | 94% | 2015-10-21
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | North Dakota | United States | 380053 | National Guard Vehicle Maintenance Shop Addition | 87 |  |  | 2014-10-06 | 2015-10-30 | 2015-12-11 | 94% | 2015-10-21
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | North Dakota | United States | 380053 | National Guard Vehicle Maintenance Shop Addition | 88 |  |  | 2014-10-06 | 2015-10-30 | 2015-12-11 | 94% | 2015-10-21
2016-04-08 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop |  |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 38% | 2017-07-18
2016-04-08 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 135 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 38% | 2017-07-18
2016-04-08 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 136 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 38% | 2017-07-18
2016-04-08 | 2015 | Army National Guard | Major Military Construction | North Dakota | United States | 380073 | National Guard Vehicle Maintenance Shop | 137 |  |  | 2015-07-13 | 2017-06-30 | 2017-07-18 | 38% | 2017-07-18
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Ohio | United States | 390292 | Sanitary Sewer |  |  |  | 2014-09-08 | 2016-07-31 | 2016-07-31 | 92% | 2016-07-31 | Awaiting USACE Review of streem cut plan. 45 Day window ends on 26 Feb 16 | Awaiting USACE Review of streem cut plan. 45 Day window ends on 26 Feb 16
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Oklahoma | United States | 400066 | Operations Readiness Training Complex |  |  |  | 2013-10-25 | 2014-10-01 | 2016-02-22 | 60% | 2014-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Oklahoma | United States | 400605 | Upgrade: Combined Arms Collective Training Facility |  |  |  | 2012-11-01 | 2014-02-19 | 2015-01-16 | 99% | 2014-03-07 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Oklahoma | United States | 400606 | Live Fire Shoot House |  |  |  | 2012-11-01 | 2014-02-19 | 2014-06-28 | 99% | 2014-03-07 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Oregon | United States | 410026 | Readiness Center |  |  |  | 2012-12-01 | 2013-12-28 | 2014-03-20 | 100% | 2014-02-21 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420051 | Aircraft Maintenance Instructional Building |  |  |  | 2014-10-20 | 2016-04-22 | 2016-08-10 | 57% | 2016-04-22
2016-04-08 | 2009 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420511 | Readiness Center, Add/Alt |  |  |  | 2011-09-26 | 2012-10-30 | 2015-12-31 | 99% | 2013-08-15 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punch list pending | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punch list pending
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | 420533 | Sanitary Sewer |  |  |  | 2015-09-28 | 2016-06-17 | 2016-06-17 | 1% | 2016-06-17
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Pennsylvania | United States | 420542 | Controlled Access Secure Facility |  |  |  | 2014-10-30 | 2015-11-13 | 2015-12-17 | 90% | 2015-12-17 | SIOH all in-house; awaiting NPDES | SIOH all in-house; awaiting NPDES
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Puerto Rico | Puerto Rico | 430070 | Maneuver Area Training & Equipment Site Addition |  |  |  | 2014-09-15 | 2016-05-30 | 2016-11-01 | 70% | 2015-05-30
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Puerto Rico | Puerto Rico | 430081 | Readiness Center (JFHQ) |  |  |  | 2014-03-03 | 2015-09-18 | 2016-02-05 | 98% | 2015-09-18 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)} | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Puerto Rico | Puerto Rico | 430803 | Readiness Center |  |  |  | 2015-10-19 | 2017-03-25 | 2017-03-25 | 10% | 2017-03-25 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | Major Military Construction | Rhode Island | United States | 440009 | United States Property and Fiscal Office |  |  |  | 2012-10-08 | 2014-04-17 | 2015-03-31 | 99% | 2015-01-31 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project) Working warranty issues | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project) Working warranty issues
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Rhode Island | United States | 440053 | Access Control Point |  |  |  | 2015-09-01 | 2015-11-01 | 2016-04-01 | 25% | 2016-04-01 | Contractor delayed. Submittal process ongoing. Construction to start this month. | Contractor delayed. Submittal process ongoing. Construction to start this month.
2016-04-08 | 2014 | Army National Guard | Major Military Construction | South Carolina | United States | 450131 | National Guard Vehicle Maintenance Shop |  |  |  | 2014-03-26 | 2017-04-06 | 2017-07-06 | 10% | 2017-04-06 | State Project Number E24-9770-JM | State Project Number E24-9770-JM
2016-04-08 | 2010 | Army National Guard | Major Military Construction | South Carolina | United States | 450252 | Army Aviation Support Facility, Add/Alt |  | 11000000 | 090115, 220241 and 220243 | 2010-10-24 | 2012-04-25 | 2013-04-23 | 100% | 2013-01-14 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759) | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2016-04-08 | 2014 | Army National Guard | Major Military Construction | South Carolina | United States | 450283 | National Guard Readiness Center |  |  |  | 2014-03-26 | 2017-04-06 | 2017-05-06 | 15% | 2017-05-06 | State Project Number E24-9764-JM | State Project Number E24-9764-JM
2016-04-08 | 2010 | Army National Guard | Major Military Construction | South Carolina | United States | 450353 | Army Aviation Support Facility |  | 12100000 | 220241, 220243 and 530035 | 2010-11-23 | 2012-08-18 | 2013-06-21 | 99% | 2013-06-21 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936) | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | South Carolina | United States | 450403 | Readiness Center, Add/Alt |  |  |  | 2012-10-01 | 2014-01-08 | 2014-04-30 | 100% | 2014-06-27 | PL 112-25 (Budget Control Act, 2011), State Project Number E24-9751-CA | PL 112-25 (Budget Control Act, 2011), State Project Number E24-9751-CA
2016-04-08 | 2014 | Army National Guard | Major Military Construction | Texas | United States | 480243 | Armed Forces Reserve Center |  |  |  | 2016-04-13 | 2017-06-09 | 2017-06-09 | 1% | 2017-06-09
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Utah | United States | 490076 | BEQ Facility (Regional Training Institute) |  |  |  | 2013-08-12 | 2014-10-01 | 2016-03-01 | 100% | 2014-12-19 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), NGB 593 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), NGB 593
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Utah | United States | 490444 | Regional Training Institute Ph2 |  |  |  | 2013-08-26 | 2014-09-30 | 2015-04-15 | 99% | 2014-09-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Utah | United States | 490803 | Unheated Aircraft Storage Hangar |  |  |  | 2016-01-26 | 2016-01-26 | 2016-01-26 | 98% | 2016-01-26
2016-04-08 | 2015 | Army National Guard | Major Military Construction | Vermont | United States | 500036 | National Guard Vehicle Maintenance Shop |  |  |  | 2015-04-30 | 2015-12-31 | 2016-01-31 | 100% | 2016-03-15 | Site corrections & punch list items pending to make final payment April/early May 2016 | Site corrections & punch list items pending to make final payment April/early May 2016
2016-04-08 | 2016 | Army National Guard | Major Military Construction | Vermont | United States | 500079 | National Guard Vehicle Maintenance Shop Addition |  |  |  | 2016-04-11 | 2017-03-31 | 2017-03-31 | 1% | 2017-03-31
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Virginia | United States | 510307 | Combined Arms Collective Training Facility |  |  |  | 2013-04-10 | 2014-10-09 | 2015-02-27 | 99% | 2015-04-10 | PL 112-25 (Budget Control Act, 2011), 3rd Party investigation underway for roof failure. Modification contract to include further testing has been executed. Contractor to start 10 Mar 16. Target installation underway (PEO-STRI). Some issues with water in comms rooms, which have been addressed. New issues at existing MOUT Site, Ft Pickett (part of CTF Project included upgrade in old site), with roof leaks. Contract in place to repair 1 of 3 [existing} building with leaks. | PL 112-25 (Budget Control Act, 2011), 3rd Party investigation underway for roof failure. Modification contract to include further testing has been executed. Contractor to start 10 Mar 16. Target installation underway (PEO-STRI). Some issues with water in comms rooms, which have been addressed. New issues at existing MOUT Site, Ft Pickett (part of CTF Project included upgrade in old site), with roof leaks. Contract in place to repair 1 of 3 [existing} building with leaks.
2016-04-08 | 2010 | Army National Guard | Major Military Construction | Virgin Islands | Virgin Islands, U.S. | 520014 | Regional Training Institute, PH 1 |  |  |  | 2010-07-01 | 2012-02-20 | 2013-04-26 | 100% | 2013-04-26 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | Major Military Construction | Virgin Islands | Virgin Islands, U.S. | 520034 | Readiness Center (JFHQ) |  |  |  | 2011-11-01 | 2013-11-26 | 2014-04-17 | 100% | 2014-04-17 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Washington | United States | 530015 | Readiness Center |  |  |  | 2013-09-23 | 2015-08-20 | 2016-03-10 | 99% | 2016-01-09 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Washington | United States | 530035 | National Guard Readiness Center |  |  |  | 2014-10-06 | 2016-06-30 | 2016-06-30 | 65% | 2016-06-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163) | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2016-04-08 | 2013 | Army National Guard | Major Military Construction | West Virginia | United States | 540075 | Readiness Center |  |  |  | 2014-04-07 | 2015-09-11 | 2015-11-29 | 99% | 2015-09-11 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | West Virginia | United States | 540085 | Readiness Center Ph1 |  |  |  | 2012-11-01 | 2014-11-12 | 2014-11-12 | 99% | 2014-08-25 | PL 112-25 (Budget Control Act, 2011) | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2009 | Army National Guard | Major Military Construction | West Virginia | United States | 540105 | Joint Interagency Training Education Center, PH 1 |  |  |  | 2009-10-01 | 2011-09-28 | 2014-09-30 | 99% | 2011-09-30 | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2009 | Army National Guard | Major Military Construction | West Virginia | United States | 540206 | Multi-Purpose Building, PH II |  |  |  | 2010-02-01 | 2010-08-26 | 2013-03-31 | 100% | 2010-08-30 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2016-04-08 | 2013 | Army National Guard | Major Military Construction | Wisconsin | United States | 550142 | Field Maintenance Shop |  |  |  | 2013-10-28 | 2014-10-01 | 2015-06-15 | 99% | 2014-10-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | Major Military Construction | Wisconsin | United States | 550245 | Tactical Unmanned Aircraft System Facility |  |  |  | 2012-07-01 | 2013-05-20 | 2014-05-30 | 100% | 2013-10-20 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250) | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2016-03-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 65277 | Consolidated Dining Facility |  |  |  | 2014-04-23 | 2015-09-30 | 2016-05-13 | 46%
2016-03-31 | 2012 | Army Reserve | Major Military Construction | North Carolina | United States | 67466 | Army Reserve Center/Land |  |  |  | 2012-10-10 | 2014-03-19 | 2016-12-15 | 65%
2016-03-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 67652 | Army Reserve Center |  |  |  | 2015-04-24 | 2017-02-12 | 2017-02-12 | 17%
2016-03-31 | 2013 | Army Reserve | Major Military Construction | Illinois | United States | 67659 | Army Reserve Center |  |  |  | 2014-01-13 | 2015-11-04 | 2016-09-30 | 90%
2016-03-31 | 2015 | Army Reserve | Major Military Construction | New York | United States | 67661 | Army Reserve Center/AMSA |  |  |  | 2016-04-15 | 2017-09-22 | 2017-09-22 | 3%
2016-03-31 | 2014 | Army Reserve | Major Military Construction | Maryland | United States | 67663 | Army Reserve Center/Land |  |  |  | 2015-10-07 | 2017-09-06 | 2017-09-06 | 6%
2016-03-31 | 2012 | Army Reserve | Major Military Construction | New York | United States | 67691 | Army Reserve Center |  |  |  | 2012-06-01 | 2014-02-21 | 2015-11-30 | 99% | 2014-05-21
2016-03-31 | 2013 | Army Reserve | Major Military Construction | Maryland | United States | 67705 | Army Reserve Center |  |  |  | 2015-10-08 | 2017-09-07 | 2017-09-07 | 6%
2016-03-31 | 2012 | Army Reserve | Major Military Construction | Illinois | United States | 67713 | Army Reserve Center |  |  |  | 2012-10-18 | 2014-07-10 | 2016-03-04 | 99% | 2016-03-23
2016-03-31 | 2013 | Army Reserve | Major Military Construction | Washington | United States | 67715 | Army Reserve Center |  |  |  | 2013-07-11 | 2016-02-24 | 2016-06-30 | 98%
2016-03-31 | 2013 | Army Reserve | Major Military Construction | Maryland | United States | 68077 | Add/Alt Army Reserve Center |  | 5455000 | 69562 | 2014-07-30 | 2016-05-30 | 2016-08-26 | 39%
2016-03-31 | 2011 | Army Reserve | Major Military Construction | Texas | United States | 69421 | Army Reserve Center/Land |  |  |  | 2012-08-21 | 2014-03-21 | 2017-03-31 | 26%
2016-03-31 | 2010 | Army Reserve | Major Military Construction | Connecticut | United States | 69461 | Army Reserve Center/Land |  |  |  | 2011-11-29 | 2015-12-21 | 2016-04-29 | 87%
2016-03-31 | 2010 | Army Reserve | Major Military Construction | Florida | United States | 69471 | Army Reserve Center/Land |  |  |  | 2012-05-22 | 2013-09-24 | 2016-06-17 | 93%
2016-03-31 | 2011 | Army Reserve | Major Military Construction | Virginia | United States | 69562 | Army Reserve Center |  |  |  | 2015-01-23 | 2017-05-10 | 2017-07-10 | 0%
2016-03-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 69669 | Central Issue Facility |  |  |  | 2014-07-07 | 2015-12-14 | 2016-05-27 | 49%
2016-03-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 71482 | ORTC |  |  |  | 2014-03-19 | 2016-05-17 | 2016-08-15 | 34%
2016-03-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71768 | Automated Multipurpose Machine Gun (MPMG) |  |  |  | 2015-11-19 | 2017-05-12 | 2017-05-12 | 22%
2016-03-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71769 | Modified Record Fire Range |  |  |  | 2014-10-17 | 2016-04-09 | 2016-06-30 | 24%
2016-03-31 | 2014 | Army Reserve | Major Military Construction | North Carolina | United States | 71900 | Army Reserve Center |  |  |  | 2014-12-02 | 2016-11-01 | 2016-11-30 | 84%
2016-03-31 | 2015 | Army Reserve | Major Military Construction | California | United States | 71901 | Army Reserve Center/AMSA |  |  |  | 2016-03-02 | 2018-02-20 | 2018-02-20 | 16%
2016-03-31 | 2014 | Army Reserve | Major Military Construction | Wisconsin | United States | 71999 | NCO Academy Dining Facility |  |  |  | 2014-04-22 | 2015-08-25 | 2015-11-16 | 51% | 2015-11-16
2016-03-31 | 2013 | Army Reserve | Major Military Construction | Wisconsin | United States | 72088 | ECS TEMF |  | 5455000 | 69562 | 2013-07-08 | 2015-06-08 | 2016-03-02 | 94% | 2016-03-02
2016-03-31 | 2014 | Army Reserve | Major Military Construction | California | United States | 72284 | TASS Training Center (TTC) |  |  |  | 2014-10-20 | 2016-05-22 | 2016-09-01 | 24%
2016-03-31 | 2015 | Army Reserve | Major Military Construction | Virginia | United States | 72291 | TASS Training Center |  |  |  | 2015-10-19 | 2017-08-28 | 2017-08-28 | 4%
2016-03-31 | 2015 | Army Reserve | Major Military Construction | Illinois | United States | 77228 | Army Reserve Center |  |  |  | 2016-02-27 | 2018-02-16 | 2018-02-16 | 6%
2016-03-31 | 2015 | Army Reserve | Major Military Construction | Colorado | United States | 81959 | Training Building Addition |  |  |  | 2015-08-07 | 2016-12-09 | 2016-12-30 | 7%
2016-03-31 | 2015 | Army Reserve | Major Military Construction | California | United States | 85812 | Army Reserve Center |  |  |  | 2015-11-02 | 2017-10-02 | 2017-10-02 | 4%
2016-03-08 | 2011 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX0802 | Replace Headquarters Facility - New Cumberland |  | 1950000 | FY13 Andersen / FY13 Grissom | 2012-08-30 | 2015-09-18 | 2016-08-08 | 98% | 2016-09-01 | See also DDCX0803 | See also DDCX0803
2016-04-13 | 2012 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1202 | Replace General Purpose Warehouse - New Cumberland |  |  |  | 2014-01-14 | 2015-08-27 | 2016-02-19 | 99% | 2016-04-19 | 2853 Reprogramming | 2853 Reprogramming
2016-04-13 | 2012 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1203 | Upgrade Access Control Points - New Cumberland |  |  |  | 2013-11-01 | 2015-05-05 | 2016-10-30 | 74% | 2016-11-07
2016-04-13 | 2013 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1301 | Replace Communications Building - New Cumberland |  |  |  | 2014-10-31 | 2016-04-28 | 2016-09-22 | 65% | 2016-10-13
2016-04-13 | 2013 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland |  |  |  | 2014-07-11 | 2016-01-04 | 2016-09-27 | 56% | 2016-10-27 | 2853 Reprogramming | 2853 Reprogramming
2016-04-13 | 2014 | DLA Defense Distribution Center | Major Military Construction | California | United States | DDCX1404 | General Purpose Warehouse - Tracy |  |  |  | 2014-10-02 | 2016-02-28 | 2016-08-28 | 10% | 2016-10-03
2016-04-13 | 2014 | DLA Defense Distribution Center | Major Military Construction | Hawaii | United States | DSFH1401 | Alter Warehouse Space - JB PH Hickam |  |  |  | 2015-06-02 | 2016-10-14 | 2016-10-14 | 9% | 2016-11-30 | wo# 1167459 | wo# 1167459
2016-03-08 | 2014 | DLA Defense Distribution Center | Unspecified Minor Military Construction | Hawaii | United States | DSFH1401 | Upgrade Administrative Space - JB PH Hickam | DSFH14U2 |  |  | 2015-06-02 | 2016-10-14 | 2016-10-14 | 9% | 2016-11-30 | wo# 1362232 | wo# 1362232
2016-04-13 | 2013 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC 1306 | Replace Fuel Pier - Pt Loma |  |  |  | 2014-01-15 | 2017-10-14 | 2017-10-14 | 66% | 2017-10-14 | wo# 1124259 | wo# 1124259
2016-03-08 | 2015 | DLA Defense Energy Support Center | Major Military Construction | South Dakota | United States | DESC 1463 | Construct Hydrant Fuel System - Ellsworth AFB |  |  |  | 2016-01-19 | 2017-02-01 | 2017-02-01 | 0%
2016-03-08 | 2014 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC 1509 | Replace Fuel Pipeline - MCAS Miramar |  |  |  | 2016-02-16 | 2016-12-30 | 2016-12-30 | 1% |  | NTP Estimated | NTP Estimated
2016-02-08 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC0503 | Hydrant Fuel System - Misawa AB |  | 2601000 | FY14 Tinker | 2013-02-01 | 2015-02-01 | 2015-05-13 | 100% | 2015-03-06
2016-03-08 | 2010 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC0704 | Rplc Fuel Strg Fac INCR #2 (of 4) - NAV SUP FLC, Pt. Loma, San Diego |  | 3109000 | FY09 PH-H, FY10 Travis, FY13 New Cumberlan Sewage Treatment | 2011-03-22 | 2013-09-23 | 2014-02-28 | 100% | 2014-01-17 | wo#861477 | wo#861477
2016-02-08 | 2008 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC0704 | Rplc Fuel Strg Fac INC #1 - NAV SUP FLC, Pt. Loma San Diego |  |  |  | 2008-10-22 | 2013-09-23 | 2014-02-28 | 100% | 2014-01-17 | wo# 861477 | wo# 861477
2016-03-08 | 2011 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC0704 | Rplc Fuel Strg Fac Iincr #3 (of 4) - Pt. Loma, San Diego |  | 3770000 | FY13 New Cumberland Sewage Treatment, FY14 Tinker | 2011-03-30 | 2013-09-23 | 2014-02-28 | 100% | 2014-01-17 | wo#974938 | wo#974938
2016-04-13 | 2012 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma |  | 7345000 | FY13 Grissom | 2012-03-29 | 2015-05-11 | 2016-07-27 | 91% | 2016-05-16 | wo# 113174 | wo# 113174
2016-03-08 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | Korea, South | DESC0907 | Hydrant Fuel System - Osan AB |  | 2151000 | FY12 New Cumberland General Purpose Warehous | 2013-08-12 | 2014-08-14 | 2016-04-30 | 99% | 2016-04-30 | Tank 2 coating deficiencies have delayed final contract. | Tank 2 coating deficiencies have delayed final contract.
2016-03-09 | 2011 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC0909 | Replace Fuel Pier - Craney Island |  | 3114000 | FY14 Tinker / FY13 Grissom | 2012-11-26 | 2014-06-03 | 2015-05-30 | 100% | 2015-09-04 | wo# 799865 | wo# 799865
2016-04-13 | 2012 | DLA Defense Energy Support Center | Major Military Construction | Massachusetts | United States | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB |  | 1761000 | FY14 Iwakuni | 2013-06-18 | 2015-12-10 | 2016-06-15 | 93% | 2016-08-14 | 2853 Reprogramming | 2853 Reprogramming
2016-01-14 | 2012 | DLA Defense Energy Support Center | Major Military Construction | Arizona | United States | DESC1103 | Replace Hydrant Fuel System - Davis Montham AFB |  |  |  | 2012-11-13 | 2014-11-03 | 2015-05-15 | 100% | 2015-04-09
2016-03-08 | 2014 | DLA Defense Energy Support Center | Major Military Construction | North Dakota | United States | DESC1107 | Replace Fuel Pipeline - Minot AFB |  |  |  | 2014-08-11 | 2015-08-11 | 2015-08-24 | 98% | 2015-07-21
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City |  |  |  | 2014-06-30 | 2015-11-15 | 2016-01-08 | 95% | 2016-04-11 | wo# 1302082 | wo# 1302082
2016-04-13 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | Guantanamo Bay Naval Base | DESC1203 | Replace Fuel Pier - GTMO |  |  |  | 2013-10-28 | 2015-09-28 | 2016-04-16 | 87% |  | wo# 1124257 | wo# 1124257
2016-02-09 | 2012 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1205 | Replace Fuel Facilities - San Clemente Is. |  |  |  | 2013-02-28 | 2015-03-11 | 2016-08-11 | 88% |  | 2853 Reprogramming wo# 973902 | 2853 Reprogramming wo# 973902
2016-03-08 | 2012 | DLA Defense Energy Support Center | Major Military Construction | West Virginia | United States | DESC12S1 | Replace Hydrant Fuel System - Camp Dawson |  |  |  | 2012-07-13 | 2013-05-31 | 2015-07-24 | 100% | 2015-09-22
2016-03-09 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Indiana | United States | DESC1301 | Replace Hydrant Fuel system - Grissom ARB |  |  |  | 2015-09-17 | 2017-04-09 | 2017-06-05 | 0% |  | 2853 Reprogramming | 2853 Reprogramming
2016-03-08 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Guam | Guam | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB |  |  |  | 2014-06-30 | 2016-02-06 | 2016-08-02 | 54% |  | wo# 1125022 | wo# 1125022
2016-03-08 | 2013 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1304 | Replace Fuel Storage - Edwards AFB |  | 3470000 | FY13 Grissom | 2013-12-04 | 2016-12-07 | 2016-12-07 | 99% | 2017-03-07
2016-03-08 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Delaware | United States | DESC1305 | Replace Truck Off-Load Facility - Dover AFB |  |  |  | 2013-10-18 | 2015-04-11 | 2015-08-14 | 99% | 2015-11-02
2016-03-08 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1353 | Replace Hydrant Fuel System - Robins AFB |  |  |  | 2017-09-27 | 2017-09-27 | 2017-09-27 | 0% |  | Award Protested - estimated Construction Start and Completion Dates | Award Protested - estimated Construction Start and Completion Dates
2016-04-13 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Louisiana | United States | DESC1390 | Upgrade Pumphouse - Barksdale AFB |  | 575000 | FY13 Hurlburt | 2013-09-09 | 2015-02-26 | 2015-05-11 | 100% | 2015-05-11 | wo# 1123107 | wo# 1123107
2016-03-08 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC1391 | Construct Fuel Storage Facility - Hurlburt AFB |  |  |  | 2013-09-24 | 2015-09-14 | 2015-12-05 | 100% | 2015-12-05
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC13S2 | Replace Fuel Pipeline - Tyndall AFB |  |  |  | 2015-01-27 | 2016-05-06 | 2016-09-14 | 86% | 2016-08-05
2016-03-08 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | Guantanamo Bay Naval Base | DESC13S3 | Replace Truck Loading Facility - GTMO |  |  |  | 2013-10-28 | 2015-09-28 | 2016-04-16 | 81% | 2016-06-15 | wo# 1303226 | wo# 1303226
2016-04-13 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Arizona | United States | DESC13S4 | Replace Truck Unload Facility - Yuma |  |  |  | 2013-09-30 | 2014-08-03 | 2016-04-24 | 31% |  | 2853 Reprogramming wo# 1133398 | 2853 Reprogramming wo# 1133398
2016-01-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1401 | Construct Type III Hydrant Fueling system - Iwakuni MCAS |  |  |  | 2015-04-22 | 2017-08-23 | 2017-10-20 | 4%
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Florida | United States | DESC1402 | Replace Fuel Pipeline - Jacksonville |  |  |  | 2014-06-30 | 2015-10-10 | 2015-10-10 | 99% | 2016-09-26 | wo# 1163305 | wo# 1163305
2016-02-09 | 2015 | DLA Defense Energy Support Center | Major Military Construction |  | Cuba | DESC1404 | Replace Fuel Storage Tanks, Guantanamo Bay, Cuba |  |  |  | 2016-03-01 | 2017-11-13 | 2017-11-13 | 0% |  | Construction start date estimated | Construction start date estimated
2016-03-08 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island |  |  |  | 2014-11-30 | 2016-04-22 | 2016-04-22 | 98% | 2016-01-14 | wo#1140322 | wo#1140322
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1407 | Replace Hydrant Fuel System, Holloman AFB |  |  |  | 2015-08-17 | 2017-01-10 | 2017-02-01 | 31% | 2017-04-02
2016-04-13 | 2015 | DLA Defense Energy Support Center | Major Military Construction | North Carolina | United States | DESC1459 | Replace Hydrant Fuel System, Seymour Johnson AFB |  |  |  | 2015-09-10 | 2017-05-02 | 2017-05-02 | 10% | 2017-08-26
2016-03-09 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC14S2 | Replace Ground Vehicle Fueling Facility - Moody AFB |  |  |  | 2014-05-07 | 2015-05-07 | 2016-02-12 | 99% | 2015-11-19
2016-01-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC14U1 | Upgrades to Fuel Pier for Fire Protection - Pt Loma |  |  |  | 2014-06-30 | 2015-11-15 | 2015-11-15 | 100% | 2015-11-30 | wo# 1170569 | wo# 1170569
2016-03-09 | 2014 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | Arizona | United States | DESC14U2 | Replace Existing Refueler Parking Lot - Davis Monthan AFB |  |  |  | 2014-11-15 | 2015-11-03 | 2015-05-15 | 100% | 2015-04-09
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Jersey | United States | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst |  |  |  | 2014-11-18 | 2016-05-11 | 2016-11-07 | 34% | 2016-12-07
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB |  |  |  | 2015-01-19 | 2017-05-23 | 2017-06-08 | 36% | 2017-09-08 | 2853 Reprogramming | 2853 Reprogramming
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | 43 |  |  | 2015-08-10 | 2016-10-23 | 2016-10-23 | 8% | 2016-09-08 | 2853 Reprogramming | 2853 Reprogramming
2016-03-09 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1503 | Replace Diesel Fuel Pumps - Yokosuka |  |  |  | 2015-05-15 | 2016-11-05 | 2016-11-05 | 41% | 2017-01-07
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1504 | Upgrade Fuel Island - Hunter AAF |  |  |  | 2014-10-16 | 2016-04-08 | 2016-07-18 | 76% | 2016-10-16
2016-04-13 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Michigan | United States | DESC1510 | Replace Fuel Distribution Facilities, Selfridge ANG |  |  |  | 2015-12-09 | 2018-04-07 | 2018-04-07 | 1% | 2018-10-05
2016-04-13 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1515 | Replace and Alter Fuel Distribution Facilites, Craney Island DFSP |  |  |  | 2015-09-30 | 2017-06-26 | 2017-06-26 | 5% |  | wo# 1302502 | wo# 1302502
2016-04-13 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Hawaii | United States | DESC1551 | Upgrade fire Suppression and Ventilation System - Rd Hill; JB Pearl Harbor - Hickam |  |  |  | 2015-09-30 | 2017-10-23 | 2017-10-23 | 10% |  | wo# 1306143 | wo# 1306143
2016-03-09 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Tennessee | United States | DESC1557 | Replace Ground Vehicle Fueling Facility - Arnold AFB |  |  |  | 2015-06-18 | 2016-10-11 | 2016-10-11 | 7% | 2017-01-09
2016-04-13 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1561 | Replace Refueler Parking, Altus AFB |  |  |  | 2014-07-11 | 2015-04-07 | 2015-12-15 | 100% | 2015-12-18
2015-12-14 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC15S1 | Replace Ground Vehicle Fueling Facility - Atsugi |  |  |  | 2014-09-12 | 2015-07-24 | 2015-05-15 | 100% | 2015-07-09
2016-04-13 | 2015 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1606 | Replace Fuel Distribution Facilities - MCAS Beaufort |  |  |  | 2015-12-16 | 2017-11-16 | 2017-11-05 | 1% |  | wo# 1309397 | wo# 1309397
2016-02-09 | 2012 | DLA Defense Energy Support Center | Major Military Construction | Hawaii | United States | DESI1101 | Alter Warehouse Space - JB PH Hickam |  |  |  | 2012-08-13 | 2013-06-14 | 2014-10-10 | 100% | 2014-09-30 | wo# 972725 | wo# 972725
2016-02-09 | 2012 | DLA Defense Supply Center Philadelphia | Major Military Construction | Pennsylvania | United States | DSCP1201 | Upgrade HVAC System - Philadelphia |  |  |  | 2012-06-14 | 2013-07-17 | 2014-06-06 | 100% | 2014-04-29 | wo# 971006 | wo# 971006
2016-04-13 | 2014 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1401 | Operations Center Phase 1 |  |  |  | 2015-08-26 | 2018-08-25 | 2018-08-24 | 9% | 2018-08-25
2015-02-28 | 2013 | Defense Finance and Accounting Service | Major Military Construction | Texas | United States | 80230 | DFAS Administration Building |  |  |  | 2013-09-11 | 2015-03-05 | 2016-04-30 | 94%
2016-03-31 | 2008 | Defense Health Agency | Major Military Construction | Kansas | United States | 47298 | Hospital Replacement |  | 44000000 | PN - 72754 | 2010-05-03 | 2013-07-23 | 2016-08-12 | 99% | 2016-03-15 | Life Safety Deficiencies: All remaining life safety deficiencies have been cleared. The Contracting Officer has issued a letter to the Contractor stating that this project is considered substantially complete as of March 15, 2016. This letter also identified contract requirements and items remaining to be completed or submitted in order to proceed with contract closeout. Remaining construction activities: There are a few actions remaining to be completed before contract closeout can proceed. Several contract modification actions are underway and some warranty work is ongoing, primarily associated with mechanical systems. For example, modifications to the heat recovery chillers are ongoing to correct a problem affecting temperature control in the data center. This work must be completed and checked out operationally before the data center can be moved from the old hospital to the new, we anticipate completing these chiller repairs in the next few weeks. We are tracking 1672 open punchlist items, the contractor's current schedule shows these being completed by 13 May however these actions have no impact on HFPA's ongoing activities. HFPA: HFPA now controls the facility. They require 120 days after completion and testing of some of the work on the mechanical systems (i.e. chiller repairs discussed above) before the hospital will actually open for patient care. Congressional visits by Senator Moran and Senior Staffer for Senator Tim Huelskamp on 31 Mar 16. | Life Safety Deficiencies: All remaining life safety deficiencies have been cleared. The Contracting Officer has issued a letter to the Contractor stating that this project is considered substantially complete as of March 15, 2016. This letter also identified contract requirements and items remaining to be completed or submitted in order to proceed with contract closeout. Remaining construction activities: There are a few actions remaining to be completed before contract closeout can proceed. Several contract modification actions are underway and some warranty work is ongoing, primarily associated with mechanical systems. For example, modifications to the heat recovery chillers are ongoing to correct a problem affecting temperature control in the data center. This work must be completed and checked out operationally before the data center can be moved from the old hospital to the new, we anticipate completing these chiller repairs in the next few weeks. We are tracking 1672 open punchlist items, the contractor's current schedule shows these being completed by 13 May however these actions have no impact on HFPA's ongoing activities. HFPA: HFPA now controls the facility. They require 120 days after completion and testing of some of the work on the mechanical systems (i.e. chiller repairs discussed above) before the hospital will actually open for patient care. Congressional visits by Senator Moran and Senior Staffer for Senator Tim Huelskamp on 31 Mar 16.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction |  | Korea, South | 51740 | Health/Dental Clinic Replacement |  | 6652000 | PN - 71634 PN - 77000 | 2011-08-26 | 2013-05-13 | 2013-05-16 | 100% | 2014-04-23 | $17,794.00 revoked from DLA for LOGCAT F equipment training that's no longer required. Funds were subsequently returned to HQUSACE. Closeout in progress. | $17,794.00 revoked from DLA for LOGCAT F equipment training that's no longer required. Funds were subsequently returned to HQUSACE. Closeout in progress.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 51969 | Hospital Nutrition Care Department Add/Alt |  |  |  | 2012-10-02 | 2014-10-30 | 2015-12-23 | 99% | 2015-11-20 | DHA approved HFPA/DNM discretionary user change request to replace servery hood with a deeper model - Proposed contractor cost of $780K may exceed both the DHA imposed $476K discretionary change limit and the project's programmed amount; awaiting formal proposal from contractor and negotiations prior to engaging DHA for approvals. - Earliest completion is May 16 * Warranty issues continue to be identified and corrected. * Tray conveyor (warranty issue) continues to be carried as an action item for repair | DHA approved HFPA/DNM discretionary user change request to replace servery hood with a deeper model - Proposed contractor cost of $780K may exceed both the DHA imposed $476K discretionary change limit and the project's programmed amount; awaiting formal proposal from contractor and negotiations prior to engaging DHA for approvals. - Earliest completion is May 16 * Warranty issues continue to be identified and corrected. * Tray conveyor (warranty issue) continues to be carried as an action item for repair
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Florida | United States | 52330 | Clinic Replacement, Inc 1 |  |  |  | 2007-09-04 | 2009-12-17 | 2011-06-05 | 100% | 2009-09-11 | Water intrusion problem update - Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. Construction Contractor reviewed their records and provided a response to AF reports 30 Jan 2015. A-E provided response on 2 Feb 2015. CESAM reviewed responses and has awarded the services of a building envelope specialist to prepare independent determination addressing the responsibilities of each party and estimate of damages by each party. The building envelope specialist conducted their initial site visit 21-23 Oct 2015; Initial discussion provided by the A-E indicated the issues may have been caused by many sources. The building contract specialist's last report was received on 14 March 2016 marked FOUO. The report is being reviewed in Counsel for decision on actions. | Water intrusion problem update - Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. Construction Contractor reviewed their records and provided a response to AF reports 30 Jan 2015. A-E provided response on 2 Feb 2015. CESAM reviewed responses and has awarded the services of a building envelope specialist to prepare independent determination addressing the responsibilities of each party and estimate of damages by each party. The building envelope specialist conducted their initial site visit 21-23 Oct 2015; Initial discussion provided by the A-E indicated the issues may have been caused by many sources. The building contract specialist's last report was received on 14 March 2016 marked FOUO. The report is being reviewed in Counsel for decision on actions.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Florida | United States | 52330 | Clinic Replacement, Inc 2 | 67647 |  |  | 2007-09-04 | 2009-12-17 | 2011-06-05 | 100% | 2009-09-11
2016-03-31 | 2008 | Defense Health Agency | Major Military Construction |  | Germany | 52332 | Medical Clinic Replacement |  |  |  | 2008-08-29 | 2012-05-15 | 2012-07-13 | 100% | 2011-10-08 | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. German government stated that the contractor has until Dec 2016 to submit additional information for compensation. German government informally stated that the contractor intends to provide the additional information before summer. | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. German government stated that the contractor has until Dec 2016 to submit additional information for compensation. German government informally stated that the contractor intends to provide the additional information before summer.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Guam | Guam | 55918 | Central Utility Plant |  | 696000 | PN - 78146 | 2009-10-01 | 2011-02-07 | 2011-06-22 | 100% | 2011-06-22 | Residual closeout issues. | Residual closeout issues.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 |  |  |  | 2007-10-12 | 2008-06-13 | 2008-06-08 | 100% | 2008-07-23 | FY07. Work complete. Contracts closed. | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-01 |  |  | 2008-08-19 | 2009-02-15 | 2009-02-13 | 100% | 2009-03-03 | FY07. Work complete. Contracts closed. | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-02 |  |  | 2009-10-15 | 2010-04-13 | 2010-04-13 | 100% | 2010-04-13 | FY07. Work complete. Contracts closed. | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-03 |  |  | 2008-12-05 | 2009-07-24 | 2009-07-24 | 100% | 2009-07-24 | FY07. Work complete. Contracts closed. | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-04 |  |  | 2008-07-15 | 2011-05-06 | 2013-10-31 | 100% | 2013-12-06 | FY07. Work accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project. | FY07. Work accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-05 |  |  | 2009-06-01 | 2014-05-31 | 2016-09-21 | 95% | 2017-07-01 | FY07. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point. | FY07. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 2 | 63418 |  |  | 2009-06-01 | 2014-05-31 | 2016-09-21 | 95% | 2017-07-01 | FY08. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point. | FY08. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 3 | 63419 |  |  | 2009-06-01 | 2014-05-31 | 2016-09-21 | 95% | 2017-07-01 | FY09. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point. | FY09. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  | 2009-06-01 | 2014-05-31 | 2016-09-21 | 95% | 2017-07-01 | FY10. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point. | FY10. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420-01 |  |  | 2008-07-15 | 2013-10-31 | 2013-10-31 | 100% | 2013-12-06 | FY10. Line added to show correct FY funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project. | FY10. Line added to show correct FY funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324 |  |  | 2009-06-01 | 2014-05-31 | 2016-09-21 | 95% | 2017-07-01 | FY12. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point. | FY12. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324-01 |  |  | 2008-07-15 | 2013-10-31 | 2013-10-31 | 100% | 2013-12-06 | FY11. Line added to show correct FY funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project. | FY11. Line added to show correct FY funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101 |  |  | 2009-06-01 | 2014-05-31 | 2016-09-21 | 95% | 2017-07-01 | FY12. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point. | FY12. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-03-31 | 5% | 2017-06-29 | FY12. Contract awarded 18 Sep 15. NTP issued. | FY12. Contract awarded 18 Sep 15. NTP issued.
2016-03-31 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210 |  |  | 2009-06-01 | 2014-05-31 | 2017-07-01 | 95% | 2017-07-01 | FY13. Utilities, DDC, Certification and modifications for primary facility (Contract # 5). The work in the facility includes installing equipment in BSL4 area; sealing conduits in BSL3 area, installing testing and evalution comms lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point. | FY13. Utilities, DDC, Certification and modifications for primary facility (Contract # 5). The work in the facility includes installing equipment in BSL4 area; sealing conduits in BSL3 area, installing testing and evalution comms lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | New York | United States | 59220 | Hospital Add/Alt (Supplemental) |  | 5537000 | FY13 - PN76558 | 2011-10-26 | 2015-08-03 | 2015-09-11 | 99% | 2015-07-15 | Awaiting additional funds from HFPA for the REA for the Monaco Claim that was just negotiated. Replacement door frames are in and will be installed over the next few weekends. The Metal Panel and Curtain wall punchlist still has a few open items. Commissioning is almost complete, awaiting final documents. | Awaiting additional funds from HFPA for the REA for the Monaco Claim that was just negotiated. Replacement door frames are in and will be installed over the next few weekends. The Metal Panel and Curtain wall punchlist still has a few open items. Commissioning is almost complete, awaiting final documents.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Maryland | United States | 61401 | Boundary Gate at Nallin Pond |  |  |  | 2011-01-12 | 2013-01-10 | 2015-01-08 | 100% | 2014-12-31 | All pending modifications/REAs are settled. USAG-funded security equipment mod issued/completed. Working with USAG Ft Detrick to resolve issues with VCC flooring and pop-up barriers. Construction contract/project fiscal closeout activities will follow. | All pending modifications/REAs are settled. USAG-funded security equipment mod issued/completed. Working with USAG Ft Detrick to resolve issues with VCC flooring and pop-up barriers. Construction contract/project fiscal closeout activities will follow.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Maryland | United States | 61536 | Emergency Service Center |  | 1028000 | FY14 - PN77922 | 2010-07-19 | 2012-09-16 | 2013-05-23 | 100% | 2013-05-23 | Facility turned over to USAG Ft Detrick. Punchlist is complete. Working toward project fiscal closeout. | Facility turned over to USAG Ft Detrick. Punchlist is complete. Working toward project fiscal closeout.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Oklahoma | United States | 62189 | Medical / Dental Clinic Replacement |  | 7033000 | FY09 - PN00001 VCOE FY13 - PN76558 | 2009-06-01 | 2011-10-26 | 2012-02-09 | 100% | 2012-06-04 | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub. | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 62886 | Information Services Facility Expansion |  |  |  | 2012-03-19 | 2013-11-09 | 2015-02-10 | 100% | 2015-02-10 | Facility turned over to USAG Ft Detrick. Punchlist is complete. Working toward project fiscal closeout. | Facility turned over to USAG Ft Detrick. Punchlist is complete. Working toward project fiscal closeout.
2016-03-31 | 2008 | Defense Health Agency | Major Military Construction | New York | United States | 63864 | Health Clinic Add/Alt |  | 1000000 | PN - 67647 | 2008-11-07 | 2011-02-18 | 2013-12-12 | 100% | 2012-12-01 | Financial closeout pending A-E Damages Resolution. Resolution has been delayed and fiscal closeout slipped to 4/30/16. | Financial closeout pending A-E Damages Resolution. Resolution has been delayed and fiscal closeout slipped to 4/30/16.
2016-03-31 | 2009 | Defense Health Agency | Base Realignment and Closures | Maryland | United States | 64156 | USAMRICD Replacement, Inc 1 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10 | Contract is active, but all funds on this increment obligated. Contract closeout pending final completion of punch list items and comissioning challenges in Bldgs E&F. Additional BRAC funds will be required to maintain cost sharing split (93.7 DODM/6.3% BRAC) with companion DODM project. | Contract is active, but all funds on this increment obligated. Contract closeout pending final completion of punch list items and comissioning challenges in Bldgs E&F. Additional BRAC funds will be required to maintain cost sharing split (93.7 DODM/6.3% BRAC) with companion DODM project.
2016-03-31 | 2008 | Defense Health Agency | Base Realignment and Closures | Texas | United States | 64179 | San Antonio Regional MEDCEN, Inc 1 |  |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 100% | 2011-08-15 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received. | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | Base Realignment and Closures | Texas | United States | 64179 | San Antonio Regional MEDCEN, Inc 2 | 64180 |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 100% | 2011-08-15 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received. | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | Base Realignment and Closures | Texas | United States | 64179 | San Antonio Regional MEDCEN, Inc 3 | 69840 |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 100% | 2011-08-15 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received. | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | Base Realignment and Closures | Texas | United States | 64179 | San Antonio Regional MEDCEN, Inc 4 | 70990 |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 100% | 2011-08-15 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received. | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | Base Realignment and Closures | Texas | United States | 64188 | Health Clinic |  |  |  | 2008-06-30 | 2010-05-10 | 2010-05-10 | 100% | 2010-05-17 | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor. | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2016-03-31 | 2008 | Defense Health Agency | Major Military Construction | Washington | United States | 64473 | Medical/Dental Clinic |  |  |  | 2008-09-30 | 2010-02-20 | 2010-03-17 | 100% | 2010-03-17 | Copy of DD1354 sent to HQUSACE, 7 Mar 16. | Copy of DD1354 sent to HQUSACE, 7 Mar 16.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Illinois | United States | 65030 | Naval Hospital Great Lakes Health Clinic Demolition |  | 9210000 | PN - 67951 PN - 71325 PN - 77154 | 2012-09-12 | 2013-09-13 | 2014-08-08 | 100% | 2014-04-21 | Residual closeout issues | Residual closeout issues
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Guam | Guam | 65270 | Hospital Replacement, Inc 1 |  | 20119000 | FY13 - PN80308 FY10 - PN61401 | 2010-11-01 | 2014-10-15 | 2016-09-06 | 99% | 2014-03-18 | 3rd UXO found; work has restarted | 3rd UXO found; work has restarted
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31 | FY09. All funds on this increment have been obligated. This contract has been terminated for default. | FY09. All funds on this increment have been obligated. This contract has been terminated for default.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 | 65731-01 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01 | FY09. All funds on this increment obligated. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway. | FY09. All funds on this increment obligated. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31 | FY10. All funds on this increment have been obligated. This contract has been terminated for default. | FY10. All funds on this increment have been obligated. This contract has been terminated for default.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-01 |  |  | 2010-10-01 | 2011-09-30 | 2011-09-30 | 100% | 2011-10-01 | FY10. All funds on this increment have been obligated. Gasline construction complete. | FY10. All funds on this increment have been obligated. Gasline construction complete.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-02 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01 | FY10. All funds on this increment have been obligated. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway. | FY10. All funds on this increment have been obligated. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 3 | 67181 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10 | FY11. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway. | FY11. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 4 | 67182 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10 | FY12. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway. | FY12. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66588 | Health Clinic Add/Alt |  |  |  | 2013-04-08 | 2016-05-30 | 2016-09-04 | 80% | 2017-01-07 | Addition turned over 26 Jun 2015; flooring punchlist items corrected in Jan 16. BMEDDAC Safety Officer identified safety issue with the water feature; the elevation difference (20-30 cm) meets German criteria, but not US. Coordination ongoing to provide solution. Customer BOD of Health Clinic Addition on 26JUN15. X-ray room wall extension completed on 15FEB16. Concrete floor slab surface imperfection corrected with topping slab (Phase 3). Interior wall layout and erection ongoing (Phase 3). Utility tie-in from Addition (Phase 2) to Renovation (Phase 3) ongoing. Final construction completion (Renovation) may be delayed due to cumulative modification delays. BauAmt's negotiations on delay and associated costs (worst case 320k euro) have been are taking longer than anticipated due to the unforeseen site conditions found during the renovation phase (bowed roof, inproperly applied screed, and deteriorated and unmarked existing utilities that may also impact the schedule. Anticipated completion of the Alteration is 16 Feb 17. | Addition turned over 26 Jun 2015; flooring punchlist items corrected in Jan 16. BMEDDAC Safety Officer identified safety issue with the water feature; the elevation difference (20-30 cm) meets German criteria, but not US. Coordination ongoing to provide solution. Customer BOD of Health Clinic Addition on 26JUN15. X-ray room wall extension completed on 15FEB16. Concrete floor slab surface imperfection corrected with topping slab (Phase 3). Interior wall layout and erection ongoing (Phase 3). Utility tie-in from Addition (Phase 2) to Renovation (Phase 3) ongoing. Final construction completion (Renovation) may be delayed due to cumulative modification delays. BauAmt's negotiations on delay and associated costs (worst case 320k euro) have been are taking longer than anticipated due to the unforeseen site conditions found during the renovation phase (bowed roof, inproperly applied screed, and deteriorated and unmarked existing utilities that may also impact the schedule. Anticipated completion of the Alteration is 16 Feb 17.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66693 | Health/Dental Clinic Replacement |  |  |  | 2014-02-03 | 2016-04-12 | 2016-04-12 | 95% | 2016-06-11 | Preliminary cleanup ongoing throughout facility.-Priming, painting, and touch up of interior rooms (1st & 2nd floors) continues. Electrical and mechanical systems, communications cabling, ductwork nsulation, sprinkler, and sanitary sewer line trimout and programming ongoing. Pre-Final Inspections by Bauamt and A/E ongoing. Commissioning Agent (Jacobs Engineering) onsite for Pre-Commissioning Inspection during week of 29FEB16. Commissioning contract change to be negotiated by the BauAmt by mid March. Current value approximately 310k Euro to include a no cost time extension; commissioning will occur shortly after original completion date of 12 Apr 16. Pending modification for water softening to meet requirements for dental sterilizer/washer (~50-60k euro). | Preliminary cleanup ongoing throughout facility.-Priming, painting, and touch up of interior rooms (1st & 2nd floors) continues. Electrical and mechanical systems, communications cabling, ductwork nsulation, sprinkler, and sanitary sewer line trimout and programming ongoing. Pre-Final Inspections by Bauamt and A/E ongoing. Commissioning Agent (Jacobs Engineering) onsite for Pre-Commissioning Inspection during week of 29FEB16. Commissioning contract change to be negotiated by the BauAmt by mid March. Current value approximately 310k Euro to include a no cost time extension; commissioning will occur shortly after original completion date of 12 Apr 16. Pending modification for water softening to meet requirements for dental sterilizer/washer (~50-60k euro).
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67949 | NIBC Security Fencing and Equipment |  |  |  | 2012-04-02 | 2013-04-02 | 2013-04-01 | 100% | 2013-04-01 | Segment 1 - Work complete. | Segment 1 - Work complete.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67949 | NIBC Security Fencing and Equipment | 67949-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-03-31 | 1% | 2017-06-29 | Segment 2 - Work structured as contract option in combined solicitation with USAMRIID Replacement North Parking (Contract # 6) which establishes overall site contours for fence construction. Contract option was awarded 17 Sep 15. Notice to proceed was issued/acknowledged 8 Oct 15. BOD is 29 Jun 17. | Segment 2 - Work structured as contract option in combined solicitation with USAMRIID Replacement North Parking (Contract # 6) which establishes overall site contours for fence construction. Contract option was awarded 17 Sep 15. Notice to proceed was issued/acknowledged 8 Oct 15. BOD is 29 Jun 17.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67951 | Water Treatment Plant Repair |  |  |  | 2013-01-14 | 2014-07-08 | 2016-03-18 | 97% | 2016-03-18 | % Complete (Scheduled/Actual): 100/97 . BOD revised to 18 Mar 16 due to systems commissioning schedule impact related to replacement of defective valves. Commissioning effort resumed 1 Feb 16. Testing is progressing successfully. | % Complete (Scheduled/Actual): 100/97 . BOD revised to 18 Mar 16 due to systems commissioning schedule impact related to replacement of defective valves. Commissioning effort resumed 1 Feb 16. Testing is progressing successfully.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 67953 | Supplemental Water Storage |  |  |  | 2011-07-20 | 2012-11-01 | 2016-03-04 | 98% | 2016-03-04 | % Complete (Scheduled/Actual): 100/98. Contractor performance issues; liquidated damages being assessed from 30 May 14. Bonding company has arranged for 3rd party payment to subcontractors. Tank has been filled and passed testing. Remaining work is limited to completion of pump station equipment/controls. Subcontractors are responding and performing work. | % Complete (Scheduled/Actual): 100/98. Contractor performance issues; liquidated damages being assessed from 30 May 14. Bonding company has arranged for 3rd party payment to subcontractors. Tank has been filled and passed testing. Remaining work is limited to completion of pump station equipment/controls. Subcontractors are responding and performing work.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | North Carolina | United States | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) |  | 14458000 | OSD - C project FY14 - PN77922 | 2011-05-13 | 2012-10-12 | 2012-11-15 | 100% | 2012-11-15 | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14. Financial close-out underway. Final UDO cleared 19 Aug 15 and funding returned; three doors have to be replaced to complete the Final Punch List for project. | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14. Financial close-out underway. Final UDO cleared 19 Aug 15 and funding returned; three doors have to be replaced to complete the Final Punch List for project.
2016-03-31 | 2008 | Defense Health Agency | Major Military Construction | Texas | United States | 69626 | Burn Rehabilitation Center |  |  |  | 2008-08-21 | 2011-07-15 | 2013-05-01 | 100% | 2011-08-15 | Contract closeout ongoing. | Contract closeout ongoing.
2016-03-31 | 2008 | Defense Health Agency | Major Military Construction | Georgia | United States | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) |  |  |  | 2009-10-22 | 2013-02-03 | 2014-05-19 | 100% | 2014-05-19 | Commissioning of systems complete including seasonal tests which were completed in Feb 2016. Contingencies at District: $1,354,242.84. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 31 Mar 16. Resident Office settled four REA's found to have merit in amount of $1.353M on 15 Jan 2016. One pending REA under investigation for merit. Benning DPW will assign # upon receipt of final 1354. | Commissioning of systems complete including seasonal tests which were completed in Feb 2016. Contingencies at District: $1,354,242.84. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 31 Mar 16. Resident Office settled four REA's found to have merit in amount of $1.353M on 15 Jan 2016. One pending REA under investigation for merit. Benning DPW will assign # upon receipt of final 1354.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | North Carolina | United States | 70351 | Hospital Alteration |  | 23532000 | PN - 71820 PN - 71503 | 2012-09-13 | 2014-06-23 | 2016-05-01 | 95% | 2016-05-01 | Contingencies at District: $686,130.62. CAT E&F funds at District is $1,962,798.85. Contractor has been issued an Interim Marginal CCASS. Emergency Dept completed and open for patients. 3rd Floor (North) renovations completed 10 Dec 15, furniture installation underway. Negotiations completed on DHA approved User Change to delete work on 2 floors from the contract. 5th and 6th Floor warranty inspections completed. Final inspection completed in Area 3B. Pre-Final inspections completed in 2nd and 3rd floor penthouse. Landscaping underway for ED site. Area 3S work initiated 29 Jan 16. | Contingencies at District: $686,130.62. CAT E&F funds at District is $1,962,798.85. Contractor has been issued an Interim Marginal CCASS. Emergency Dept completed and open for patients. 3rd Floor (North) renovations completed 10 Dec 15, furniture installation underway. Negotiations completed on DHA approved User Change to delete work on 2 floors from the contract. 5th and 6th Floor warranty inspections completed. Final inspection completed in Area 3B. Pre-Final inspections completed in 2nd and 3rd floor penthouse. Landscaping underway for ED site. Area 3S work initiated 29 Jan 16.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) |  | 92680000 | FY13 - PN76558 | 2012-05-30 | 2015-03-16 | 2017-08-16 | 57% | 2017-07-16 | Significant changes in processes impacting water storage and the central utility plant are being resolved. Resolution requires modifying the project Environmental Assessment (EA) to account for permittable items previously not considered. A bilateral agreement for time impacts associated with mandatory engineering changes has been reached resulting in a 359 day adjustment to the construction schedule. This adjustment provides for a re-baseline of the project schedule and development of a true integrated master schedule. Agreement for time does not constitute agreement for compensable time. Compensable days are to be negotiated. USACE Engineers are continuously evaluating project design to identify concerns and remedies for way-ahead. Senior leadership continues to engage regularly to assist in resolution of project issues. All other unaffected work activities are continuing per plan. | Significant changes in processes impacting water storage and the central utility plant are being resolved. Resolution requires modifying the project Environmental Assessment (EA) to account for permittable items previously not considered. A bilateral agreement for time impacts associated with mandatory engineering changes has been reached resulting in a 359 day adjustment to the construction schedule. This adjustment provides for a re-baseline of the project schedule and development of a true integrated master schedule. Agreement for time does not constitute agreement for compensable time. Compensable days are to be negotiated. USACE Engineers are continuously evaluating project design to identify concerns and remedies for way-ahead. Senior leadership continues to engage regularly to assist in resolution of project issues. All other unaffected work activities are continuing per plan.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Kentucky | United States | 70438 | Hospital Addition/Alteration |  |  |  | 2012-08-22 | 2015-02-21 | 2015-10-27 | 100% | 2015-10-27 | All work complete effective 27 Oct 2015. Ribbon cutting 17 December 2015. Closing Out | All work complete effective 27 Oct 2015. Ribbon cutting 17 December 2015. Closing Out
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Georgia | United States | 70482 | Health Clinic Addition/Alteration |  | 1012000 | PN - 72414 | 2011-06-21 | 2013-06-20 | 2014-05-19 | 100% | 2013-11-29 | Contingencies at District: $0. CAT E&F remaining at District: $0. Financial close-out underway. | Contingencies at District: $0. CAT E&F remaining at District: $0. Financial close-out underway.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | New York | United States | 70579 | Medical Clinic (SFCC) |  | 1773000 | PN - 77154 PN - 79510 PN - 70438 | 2013-03-15 | 2015-03-06 | 2015-03-06 | 100% | 2015-03-05 | Project Fiscally complete 9 DEC 15 | Project Fiscally complete 9 DEC 15
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | New York | United States | 70580 | Dental Clinic Addition /Alteration |  |  |  | 2013-01-09 | 2015-01-09 | 2014-12-19 | 100% | 2014-12-19 | Project Fiscally complete 4 DEC 15 | Project Fiscally complete 4 DEC 15
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Florida | United States | 70597 | Medical Clinic |  |  |  | 2012-10-17 | 2014-10-07 | 2014-10-07 | 100% | 2015-01-05 | Final document turnover in process. Performing post BOD changes at user request, PT room flooring, walk off matts, rear gate padlocks and door hardware. Final Pay anticipated April, 2015. | Final document turnover in process. Performing post BOD changes at user request, PT room flooring, walk off matts, rear gate padlocks and door hardware. Final Pay anticipated April, 2015.
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | South Carolina | United States | 71317 | Medical Clinic Replacement |  |  |  | 2013-12-06 | 2016-12-30 | 2018-02-13 | 82% | 2016-04-19 | In construction | In construction
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 71318 | Dental Clinic Replacement |  | 3144000 | FY14 - PN77922 | 2010-04-06 | 2012-01-06 | 2012-09-01 | 100% | 2012-04-30
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 71325 | Medical Clinic Replacement |  |  |  | 2013-10-24 | 2016-10-23 | 2016-12-22 | 41% | 2017-07-21 | Structural steel erection complete. Steel bar joist and metal deck work underway. Concrete placement complete in Area C complete. HVAC piping and ductwork underway in Area C. Metal Stud work underway in area C. Contingencies at District: $279,302.19. Cat E&F Equip funds at District: $1,723,000 | Structural steel erection complete. Steel bar joist and metal deck work underway. Concrete placement complete in Area C complete. HVAC piping and ductwork underway in Area C. Metal Stud work underway in area C. Contingencies at District: $279,302.19. Cat E&F Equip funds at District: $1,723,000
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 71408 | Dental Clinic Replacement |  |  |  | 2013-03-01 | 2016-12-06 | 2018-03-05 | 1% | 2017-01-06 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K. | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic |  | 8300000 | PN - 72754 | 2012-09-01 | 2014-09-09 | 2017-12-31 | 75% | 2016-04-30 | Notification of contract termination 5 May 2015 | Notification of contract termination 5 May 2015
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 71507 | Branch Health Clinic Replacement |  | 100000 | FY13 - PN72722 | 2014-04-30 | 2015-10-15 | 2016-08-01 | 78% | 2016-05-16 | In construction | In construction
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement |  | 205000 | PN - 14010 | 2010-12-14 | 2012-08-10 | 2012-09-28 | 100% | 2012-09-28 | Estimated financial closure: 31 Jul 2016. DIO cannot close this main project financially until the local order for the new main door is complete. | Estimated financial closure: 31 Jul 2016. DIO cannot close this main project financially until the local order for the new main door is complete.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement | 71550-01 |  |  | 2013-07-01 | 2013-08-30 | 2013-08-30 | 100% | 2013-08-30
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction |  | United Kingdom | 71550 | Medical/Dental Clinic Replacement | 71550-02 |  |  | 2015-03-03 | 2015-06-30 | 2016-06-30 | 3% | 2016-06-30 | DIO cannot close main project until this local order is complete. Structural Survey for new doors carried out. Report received at the Base. Base requested DIO (1Mar 2016) to proceed with the works. | DIO cannot close main project until this local order is complete. Structural Survey for new doors carried out. Report received at the Base. Base requested DIO (1Mar 2016) to proceed with the works.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 71653 | Hospital Replacement (ARRA) |  |  |  | 2010-12-03 | 2014-01-07 | 2014-01-07 | 100% | 2013-10-17 | Financially Closed | Financially Closed
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | Missouri | United States | 71679 | Dental Clinic |  | 234000 | FY13-PN72718 | 2013-12-02 | 2015-02-19 | 2015-02-19 | 100% | 2015-10-01 | DD1354 Complete on 19 Feb 16. Project Closeout scheduled for 15 Aug 16 due to recent heat issue in sterilization storage room. | DD1354 Complete on 19 Feb 16. Project Closeout scheduled for 15 Aug 16 due to recent heat issue in sterilization storage room.
2016-03-31 | 2008 | Defense Health Agency | Major Military Construction | North Carolina | United States | 71857 | Hospital Addition |  | 14587000 | PN - 59215 PN - 00101 PN - 53577 PN - 77154 | 2010-12-03 | 2013-01-12 | 2013-07-15 | 100% | 2013-07-15 | Funds used for FY00 Settlement, Ft. Wainwright. Financially Closed | Funds used for FY00 Settlement, Ft. Wainwright. Financially Closed
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Georgia | United States | 72292 | Hospital Addition/Alteration Phase 2 |  | 11000000 | PN - 72754 | 2012-10-15 | 2016-10-14 | 2017-03-17 | 86% | 2017-06-14 | Contingencies at District: $117,727.72 of which $67,869.95 is for temp. swing space. Cat E&F at District is $341,865.73. Executed Option 5 on Trailer Lease. Approval to descope received 5 June 2015. ED addition turned over 16 Nov 15. Kitchen renovation completed on 18 Dec 15. Renovations continues in Areas C, D, G and H. | Contingencies at District: $117,727.72 of which $67,869.95 is for temp. swing space. Cat E&F at District is $341,865.73. Executed Option 5 on Trailer Lease. Approval to descope received 5 June 2015. ED addition turned over 16 Nov 15. Kitchen renovation completed on 18 Dec 15. Renovations continues in Areas C, D, G and H.
2016-03-31 | 2015 | Defense Health Agency | Major Military Construction | Colorado | United States | 72414 | Dental Clinic Replacement |  |  |  | 2015-11-03 | 2017-10-23 | 2017-10-23 | 6% | 2017-12-22 | ISSUES/COMMENTS: 35% design review comments: There was no progress in closing out comments last week. Of the 639 comments, 390 are pending backcheck and 239 are closed. The COR will continue to review all comments pending backcheck and close them, with the reviewers concurrence. HVAC System: The way ahead is to request a UFC waiver, for the GHP system, from DHA/FD. The Waiver Package was sent to CENWO-PM and CENWO-ED on 9 Mar 16 for review. An updated LCCA was completed by SES, 14 Mar 16. and revised 17 Mar 16. AFCEC prepared a Project Financial Status Report, 17 Mar 16. The package was submitted to AFMSA for review, 23 Mar 16. LAD submitted a draft revision to DIPC, 24 Mar 16. This revision eliminates one of the oral surgery rooms and increases the size of the Decon, Sterilization and Sterilization Storage, the 3 functions that comprise DIPC. | ISSUES/COMMENTS: 35% design review comments: There was no progress in closing out comments last week. Of the 639 comments, 390 are pending backcheck and 239 are closed. The COR will continue to review all comments pending backcheck and close them, with the reviewers concurrence. HVAC System: The way ahead is to request a UFC waiver, for the GHP system, from DHA/FD. The Waiver Package was sent to CENWO-PM and CENWO-ED on 9 Mar 16 for review. An updated LCCA was completed by SES, 14 Mar 16. and revised 17 Mar 16. AFCEC prepared a Project Financial Status Report, 17 Mar 16. The package was submitted to AFMSA for review, 23 Mar 16. LAD submitted a draft revision to DIPC, 24 Mar 16. This revision eliminates one of the oral surgery rooms and increases the size of the Decon, Sterilization and Sterilization Storage, the 3 functions that comprise DIPC.
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction |  | Korea, South | 72419 | Hospital Addition/Alteration |  |  |  | 2013-09-26 | 2017-08-08 | 2018-02-07 | 69% | 2018-04-24 | Contingency Amounts: District $140,517; HQ Mgmt $794,834. Ongoing work: UL Paint, Concrete Curbs and Pavement, VCT and Carpet, Light Fixture, Acoustical Ceiling Tile, Sprinkler Head, Feeder Cable. Concurrrent delays caused by malfunctioning existing backup generator (govt delay) and by wrong procurement of DDC system wiring (contractor delay) is causing an approximate 22 calendar days schedule slip. | Contingency Amounts: District $140,517; HQ Mgmt $794,834. Ongoing work: UL Paint, Concrete Curbs and Pavement, VCT and Carpet, Light Fixture, Acoustical Ceiling Tile, Sprinkler Head, Feeder Cable. Concurrrent delays caused by malfunctioning existing backup generator (govt delay) and by wrong procurement of DDC system wiring (contractor delay) is causing an approximate 22 calendar days schedule slip.
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction |  | Korea, South | 72420 | Medical/Dental Clinic Addition |  |  |  | 2013-06-05 | 2015-02-25 | 2015-03-29 | 100% | 2015-03-27 | Contingency Amounts: District $0; HQ Mgmt $0. Final Inspection was completed and keys turned over 27 Mar 15. Final payment made 18 Feb 2016. Closeout in progress. | Contingency Amounts: District $0; HQ Mgmt $0. Final Inspection was completed and keys turned over 27 Mar 15. Final payment made 18 Feb 2016. Closeout in progress.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72430 | Ambulatory Care Center, Phase 1 |  |  |  | 2010-10-04 | 2013-02-20 | 2013-08-30 | 100% | 2013-11-19 | 1. Phase 1B was turned over to the Air Force (BOD was 19 Nov 2013) 2. Post Warranty Deficiencie corrections are underway 3. JE Dunn is correcting ADA/ABA non-compliance as a latent deficiency. Work is approximately 90% complete. 4. JE Dunn to submit plan to correct Life Health Safety deficiencies and original punch that were not previously addressed. | 1. Phase 1B was turned over to the Air Force (BOD was 19 Nov 2013) 2. Post Warranty Deficiencie corrections are underway 3. JE Dunn is correcting ADA/ABA non-compliance as a latent deficiency. Work is approximately 90% complete. 4. JE Dunn to submit plan to correct Life Health Safety deficiencies and original punch that were not previously addressed.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72430 | Ambulatory Care Center, Phase 1 | 72430-01 |  |  | 2010-10-04 | 2012-02-26 | 2012-11-30 | 100% | 2012-12-13 | 1. Phase 1B was turned over to the Air Force (BOD was 19 Nov 2013) 2. Post Warranty Deficiencie corrections are underway 3. JE Dunn is correcting ADA/ABA non-compliance as a latent deficiency. Work is approximately 90% complete. 4. JE Dunn to submit plan to correct Life Health Safety deficiencies and original punch that were not previously addressed. | 1. Phase 1B was turned over to the Air Force (BOD was 19 Nov 2013) 2. Post Warranty Deficiencie corrections are underway 3. JE Dunn is correcting ADA/ABA non-compliance as a latent deficiency. Work is approximately 90% complete. 4. JE Dunn to submit plan to correct Life Health Safety deficiencies and original punch that were not previously addressed.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 |  |  |  | 2013-05-29 | 2016-11-26 | 2017-01-08 | 43% | 2018-09-03 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement. | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-01 |  |  | 2011-11-02 | 2013-08-13 | 2013-08-29 | 100% | 2013-10-12 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-02 |  |  | 2011-08-23 | 2012-07-05 | 2012-08-20 | 100% | 2012-12-31 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-03 |  |  | 2012-08-28 | 2013-06-19 | 2013-06-11 | 100% | 2013-10-17 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-04 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 99% | 2015-11-30 | Sch. 100% Act. 99%. The contractor began construction 3 Nov 14. Pipe installation was completed 26 Aug. Pavement was completed 27 Aug. Remaining punchlist item is providing electrical power to the metering manhole. | Sch. 100% Act. 99%. The contractor began construction 3 Nov 14. Pipe installation was completed 26 Aug. Pavement was completed 27 Aug. Remaining punchlist item is providing electrical power to the metering manhole.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-05 |  |  | 2012-09-04 | 2014-01-04 | 2014-01-04 | 100% | 2015-09-16 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-06 |  |  | 2011-08-25 | 2011-11-01 | 2011-11-01 | 100% | 2011-11-01 | Temp power costs. | Temp power costs.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 3 | 72786 |  |  | 2013-05-29 | 2016-11-26 | 2017-01-08 | 43% | 2018-09-03 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement. | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 | 77163000 | FY09 - PN00180 | 2013-05-29 | 2016-11-26 | 2017-01-08 | 43% | 2018-09-03 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement. | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-01 |  |  | 2013-10-21 | 2014-10-24 | 2014-10-24 | 99% | 2014-11-24 | Only the re-seeding of the Helipad area remains as a punchlist item (scheduled for Spring 2016). | Only the re-seeding of the Helipad area remains as a punchlist item (scheduled for Spring 2016).
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-02 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 99% | 2015-11-30 | Sch. 100% Act. 99%. The contractor began construction 3 Nov 14. Pipe installation was completed 26 Aug. Pavement was completed 27 Aug. Remaining punchlist item is providing electrical power to the metering manhole. | Sch. 100% Act. 99%. The contractor began construction 3 Nov 14. Pipe installation was completed 26 Aug. Pavement was completed 27 Aug. Remaining punchlist item is providing electrical power to the metering manhole.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 77251 |  |  | 2013-05-29 | 2016-11-26 | 2017-01-08 | 43% | 2018-09-03 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement. | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 |  |  | 2013-05-29 | 2016-11-26 | 2017-01-08 | 43% | 2018-09-03 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement. | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407 |  |  | 2013-05-29 | 2016-11-26 | 2017-01-08 | 43% | 2018-09-03 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement. | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 7 | 81408 |  |  | 2013-05-29 | 2016-11-26 | 2017-01-08 | 43% | 2018-09-03 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement. | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) |  | 22793000 | FY13 - PN76558 | 2011-10-25 | 2014-09-09 | 2015-04-17 | 100% | 2015-03-18 | All mod work completed. Completion of last punch list item in progress. Construction has been substantially complete since 17 Apr 2015. All physical work less plenum to be complete 30 Jan. | All mod work completed. Completion of last punch list item in progress. Construction has been substantially complete since 17 Apr 2015. All physical work less plenum to be complete 30 Jan.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-01 |  |  | 2011-03-20 | 2011-04-01 | 2011-04-01 | 100% | 2011-04-01 | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation. | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-02 |  |  | 2011-07-01 | 2014-09-27 | 2015-03-18 | 99% | 2015-03-18 | Leased Swing Space awarded for risk mitigation. | Leased Swing Space awarded for risk mitigation.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Ohio | United States | 72722 | Hospital Renovation (Supplemental) | 72722-03 |  |  | 2015-11-30 | 2016-09-01 | 2016-09-01 | 1% | 2016-09-01 | Construction award made 11 Sep 15. After Contract award Winter Exclusionary Period began. Contractor intends to mobilize on site 15 March 2016. Weekly Construction meetings on going. Submittal process ongoing. Baseline schedule submitted and currently under review by LRL. | Construction award made 11 Sep 15. After Contract award Winter Exclusionary Period began. Contractor intends to mobilize on site 15 March 2016. Weekly Construction meetings on going. Submittal process ongoing. Baseline schedule submitted and currently under review by LRL.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | United Kingdom | 72727 | Medical/Dental Clinic Replacement |  |  |  | 2014-05-06 | 2015-10-30 | 2015-12-18 | 100% | 2015-08-27 | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14. Contracting Officer has granted a nil cost extension of time to 25 Dec 2015 based on delays resulting from the original groundwork subcontractor withdrawing from the contract and from a national shortage of labour delaying the brickwork trade. Contractor has requested a further extension of time of 14 calendar days due to late information from SPAWAR. this is currently being reviewed by the Contracting Officer. Contracting Officer approved an extension of time to 8 Jan 2016. Construction complete and BOD achieved 27 August 2015. US Outfitting contractor SIOTS to carry out work under separate contract and to facilitate move from existing clinic (Building 140). VINCI will remobilise in November to demolish building 140 to complete the contract. US outfitting contractor nearing completion, clinic proposed to open for patients 8 Oct 2015. Ribbon cutting 6 Nov 2015. Asbestos surveys to be carried out in building 140 once vacated by Med Group prior to demolition. Mobilisation Meeting for Demolition of Building 140 3 November 2015. Building 140 Old Clinic is now 50% demolished. Contract completed 18 Dec 2015. Demolition of Building 140 completed on 17 Dec 2015 with landscaping (grass seeding) to be done in Spring 2016. | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14. Contracting Officer has granted a nil cost extension of time to 25 Dec 2015 based on delays resulting from the original groundwork subcontractor withdrawing from the contract and from a national shortage of labour delaying the brickwork trade. Contractor has requested a further extension of time of 14 calendar days due to late information from SPAWAR. this is currently being reviewed by the Contracting Officer. Contracting Officer approved an extension of time to 8 Jan 2016. Construction complete and BOD achieved 27 August 2015. US Outfitting contractor SIOTS to carry out work under separate contract and to facilitate move from existing clinic (Building 140). VINCI will remobilise in November to demolish building 140 to complete the contract. US outfitting contractor nearing completion, clinic proposed to open for patients 8 Oct 2015. Ribbon cutting 6 Nov 2015. Asbestos surveys to be carried out in building 140 once vacated by Med Group prior to demolition. Mobilisation Meeting for Demolition of Building 140 3 November 2015. Building 140 Old Clinic is now 50% demolished. Contract completed 18 Dec 2015. Demolition of Building 140 completed on 17 Dec 2015 with landscaping (grass seeding) to be done in Spring 2016.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Texas | United States | 72752 | Ambulatory Care Center Phase 2 |  | 75054000 | FY11 - PN72727 FY11 - PN62886 FY14- PN77000 PN - 77000 | 2011-12-02 | 2013-10-01 | 2016-05-23 | 99% | 2016-05-23 | 1. Construction status: 99% complete / 99% scheduled 2. CCD/BOD is 23 May 2016 3. Remaining critical path: generator testing, install HVAC smoke dampers, correct Life Health Safety Deficiencies, and complete commissioning. 4. Generators were run to 100% load, but operated near high exhaust gas temp alarm point. Skanska to submit plan (way forward) to include additional testing to correct any remaining issues or establish the units can meet contract requirements. 4. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business. 5. Ph 2 CWE = $114,136,156 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161 | 1. Construction status: 99% complete / 99% scheduled 2. CCD/BOD is 23 May 2016 3. Remaining critical path: generator testing, install HVAC smoke dampers, correct Life Health Safety Deficiencies, and complete commissioning. 4. Generators were run to 100% load, but operated near high exhaust gas temp alarm point. Skanska to submit plan (way forward) to include additional testing to correct any remaining issues or establish the units can meet contract requirements. 4. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business. 5. Ph 2 CWE = $114,136,156 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  |  |  | 2012-11-01 | 2014-07-29 | 2016-05-23 | 98% | 2016-05-23 | 1. Construction status: Scheduled 98%, Actual 98% 2. Schedule: CCD/BOD is 23 May. 3. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business + 6-months to complete reutilization process for an approximate building turnover in Jun 2017. 4. Completion of Ph 3 critical path: correction of Life Health Safety Deficiencies, and complete commissioning. 5. Ph 3 CWE = $122,490,265, Appropriation = $122,634,000 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161 | 1. Construction status: Scheduled 98%, Actual 98% 2. Schedule: CCD/BOD is 23 May. 3. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business + 6-months to complete reutilization process for an approximate building turnover in Jun 2017. 4. Completion of Ph 3 critical path: correction of Life Health Safety Deficiencies, and complete commissioning. 5. Ph 3 CWE = $122,490,265, Appropriation = $122,634,000 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 2 | 80793-01 |  |  | 2012-11-01 | 2014-07-29 | 2016-05-23 | 98% | 2016-05-23 | 1. Construction status: Scheduled 98%, Actual 98% 2. Schedule: CCD/BOD is 23 May. 3. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business + 6-months to complete reutilization process for an approximate building turnover in Jun 2017. 4. Completion of Ph 3 critical path: correction of Life Health Safety Deficiencies, and complete commissioning. 5. Ph 3 CWE = $122,490,265, Appropriation = $122,634,000 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161 | 1. Construction status: Scheduled 98%, Actual 98% 2. Schedule: CCD/BOD is 23 May. 3. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business + 6-months to complete reutilization process for an approximate building turnover in Jun 2017. 4. Completion of Ph 3 critical path: correction of Life Health Safety Deficiencies, and complete commissioning. 5. Ph 3 CWE = $122,490,265, Appropriation = $122,634,000 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | California | United States | 72808 | Medical Clinic Replacement |  |  |  | 2014-02-28 | 2015-03-16 | 2016-08-30 | 94% | 2016-03-30 | In construction | In construction
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 73360 | Consolidated Logistics Facility |  | 500000 | PN - 72414 | 2011-07-21 | 2014-01-06 | 2014-10-07 | 100% | 2014-10-07 | Targeting minor punchlist item completion relating to roll-up doors by mid-Mar 2016. Construction contract/project fiscal closeout will follow. | Targeting minor punchlist item completion relating to roll-up doors by mid-Mar 2016. Construction contract/project fiscal closeout will follow.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | North Carolina | United States | 73599 | Hospital Renovation & MRI Addition (Cong Add) |  | 5623000 | PN - 76558 | 2010-12-03 | 2015-01-02 | 2015-10-16 | 100% | 2015-09-18 | Completed | Completed
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | New York | United States | 73776 | Soldier Specality Care Clinic |  |  |  | 2014-01-06 | 2016-01-06 | 2016-01-06 | 100% | 2016-01-06 | BOD 6 JAN 16. Project physcial completion will be May 16 when grass has been established. | BOD 6 JAN 16. Project physcial completion will be May 16 when grass has been established.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) |  | 3850000 | FY09A - PN100040 | 2010-11-08 | 2014-05-31 | 2016-02-15 | 99% | 2016-04-01 | Sch. 100% Act. 99%. Currently working on completing punch list items (approx 20 remaining); USACE and Balfour-Beaty/ McCarthy (BBM) continue to address all issues as they are presented by the hospital command; contiuing to work the DD1354 for the site work; IO&T operations continue. Ribbon cutting ceremony scheduled for 20 June 16. | Sch. 100% Act. 99%. Currently working on completing punch list items (approx 20 remaining); USACE and Balfour-Beaty/ McCarthy (BBM) continue to address all issues as they are presented by the hospital command; contiuing to work the DD1354 for the site work; IO&T operations continue. Ribbon cutting ceremony scheduled for 20 June 16.
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-01 |  |  | 2010-06-15 | 2012-02-25 | 2012-05-02 | 100% | 2012-06-02 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-02 |  |  | 2010-04-05 | 2010-05-30 | 2010-06-07 | 100% | 2010-06-30 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-03 |  |  | 2010-06-18 | 2010-10-18 | 2010-10-04 | 100% | 2010-10-05 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-04 |  |  | 2010-07-20 | 2012-01-11 | 2012-09-20 | 100% | 2012-09-20 | Construction 100% Complete | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Texas | United States | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 74650-05 |  |  | 2011-01-06 | 2012-06-29 | 2015-06-30 | 99% | 2013-12-15 | Contractor working close out documentation. | Contractor working close out documentation.
2016-03-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | Florida | United States | 75132 | Joint Navy-VA Project |  |  |  | 2014-06-01 | 2014-10-15 | 2016-04-08 | 82% | 2016-01-29 | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out. | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 |  |  |  | 2014-01-13 | 2021-07-20 | 2022-03-30 | 5% | 2022-03-30 | Environmental Compensation Also includes: Lots 7.2-7.4 Initial Compensation Measures - German government solicitation and award dates to German industry are estimated. | Environmental Compensation Also includes: Lots 7.2-7.4 Initial Compensation Measures - German government solicitation and award dates to German industry are estimated.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  | 2017-04-30 | 2019-04-30 | 2019-04-30 | 1% | 2019-04-30 | Note: this line item has now been combined with Lot 5.1. Construction Measures, Roadways, & Site Utilities - FRG revising and coordinating lot requirements for campus roadways, utilities, and additional construction measures not included in current lot packages. Dates subject to change pending refinement of lots and corresponding schedules. This portion overlaps with Lot 5.1, based on the 35% submittal for that lot. Still awaiting validation from FRG, then will combine with Lot 5.1 line item. | Note: this line item has now been combined with Lot 5.1. Construction Measures, Roadways, & Site Utilities - FRG revising and coordinating lot requirements for campus roadways, utilities, and additional construction measures not included in current lot packages. Dates subject to change pending refinement of lots and corresponding schedules. This portion overlaps with Lot 5.1, based on the 35% submittal for that lot. Still awaiting validation from FRG, then will combine with Lot 5.1 line item.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661-01 |  |  | 2016-11-15 | 2019-12-15 | 2019-12-15 | 1% | 2019-12-15 | Lot 4 Access Control Point, Bridge, External Roadways - 65% OTS review for ACP was held 22 Sep 2015. 95% review of the Bridge held on 6 Oct 2015. ACP 95% submittal now anticipated for 22 Mar 2016 due to LBB's issues with their designer ATI. The ACP and Bridge will be one contract. At present, the entire lot is scheduled for contract award in the Oct/Nov 2016 timeframe (slipped from Aug 2016) due to aforementioned issues with ATI. Construction completion is still targeted for December 2019, based on US Forces putting the ACP/Bridge into operation at that time. LBB has coordinated sequencing of the ACP & Bridge with the PIK Traffic Circle on L369. | Lot 4 Access Control Point, Bridge, External Roadways - 65% OTS review for ACP was held 22 Sep 2015. 95% review of the Bridge held on 6 Oct 2015. ACP 95% submittal now anticipated for 22 Mar 2016 due to LBB's issues with their designer ATI. The ACP and Bridge will be one contract. At present, the entire lot is scheduled for contract award in the Oct/Nov 2016 timeframe (slipped from Aug 2016) due to aforementioned issues with ATI. Construction completion is still targeted for December 2019, based on US Forces putting the ACP/Bridge into operation at that time. LBB has coordinated sequencing of the ACP & Bridge with the PIK Traffic Circle on L369.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 72662 |  |  | 2017-04-30 | 2019-04-30 | 2019-04-30 | 1% | 2019-04-30 | Lot 5.1 Parking structures, surface parking, campus roadways, campus utilities, helipad, site drainage, retention ponds, water tank - previously included in MedCen 20% design. The 35% review meeting held on 27 Oct 2015. Based on the 35% submittal, this lot was much larger that previously expected and contained scope that had not previously been assigned to a particular lot. FRG must validate that the features/costs are not double counted with other infrastructure lots. This is an issue due to the LBB's 35% cost estimate, which is approx 100M Euro, much more than is being tracked as CWE for this particular lot --- their designer ATI's estimate is approx 71M Euro. NAU had been tracking a separate line item (line 89 of this spreadsheet) and a separate amount for Lot 3.11 for most of those items that have now been included in Lot 5.1 per the 35% submittal. NAU has requested that LBB coordinate with their A/E to determine disparities with their cost estimates. NAU had previously been tracking 47M Euro for this lot, which of course did not include the 37M USD from line 89 of this spreadsheet nor the amount for Lot 3.11. Aside from this issue, the Parking structures will be pursued as functional design package prepared by LBB's infrastructure designer. NAU requested that LBB consider delaying award of the parking structures until after the MedCen contract is awarded; however, a final decision has not been reached yet on this issue. NAU still awaits clarification from the LBB regarding scope/cost; however, estimated construction cost is now reflected as $92.8M; line 89 of this spreadsheet has been zeroed out. | Lot 5.1 Parking structures, surface parking, campus roadways, campus utilities, helipad, site drainage, retention ponds, water tank - previously included in MedCen 20% design. The 35% review meeting held on 27 Oct 2015. Based on the 35% submittal, this lot was much larger that previously expected and contained scope that had not previously been assigned to a particular lot. FRG must validate that the features/costs are not double counted with other infrastructure lots. This is an issue due to the LBB's 35% cost estimate, which is approx 100M Euro, much more than is being tracked as CWE for this particular lot --- their designer ATI's estimate is approx 71M Euro. NAU had been tracking a separate line item (line 89 of this spreadsheet) and a separate amount for Lot 3.11 for most of those items that have now been included in Lot 5.1 per the 35% submittal. NAU has requested that LBB coordinate with their A/E to determine disparities with their cost estimates. NAU had previously been tracking 47M Euro for this lot, which of course did not include the 37M USD from line 89 of this spreadsheet nor the amount for Lot 3.11. Aside from this issue, the Parking structures will be pursued as functional design package prepared by LBB's infrastructure designer. NAU requested that LBB consider delaying award of the parking structures until after the MedCen contract is awarded; however, a final decision has not been reached yet on this issue. NAU still awaits clarification from the LBB regarding scope/cost; however, estimated construction cost is now reflected as $92.8M; line 89 of this spreadsheet has been zeroed out.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-01 |  |  | 2014-01-20 | 2014-04-04 | 2014-04-04 | 99% | 2014-04-04 | Lot 1 Temporary Construction Fence - Construction essentially completed April 2014, with remaining access from the east closed off as of 1 May 2015. FRG Security Contractor is on site and will monitor access from the L369 construction gate on the west side. | Lot 1 Temporary Construction Fence - Construction essentially completed April 2014, with remaining access from the east closed off as of 1 May 2015. FRG Security Contractor is on site and will monitor access from the L369 construction gate on the west side.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-02 |  |  | 2014-06-16 | 2014-10-29 | 2015-01-21 | 100% | 2014-08-29 | Lot 2.1 Demolition, Site Clearing - Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Final inspection held on 21 Jan 2015, and final contract document provided by FRG (ABG7). | Lot 2.1 Demolition, Site Clearing - Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Final inspection held on 21 Jan 2015, and final contract document provided by FRG (ABG7).
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-03 |  |  | 2015-04-20 | 2016-04-30 | 2016-05-30 | 90% | 2016-05-30 | Lot 2.2 Mass Grading - Contract awarded April 2015. Based on discussions with the FRG, an additional 910k Euro (non-negotiated) have been identified. NAU and DHA-E have implemented the Change Management process in these mods. Awaiting further information from the LBB regarding negotiation timeline. LBB has stated that none of that work affects the schedule at present. Work is on-going, and actual work completion is still targeted for end of April 2016. Dates in columns X and Y have been changed to May 2016, due to actual contract completion. | Lot 2.2 Mass Grading - Contract awarded April 2015. Based on discussions with the FRG, an additional 910k Euro (non-negotiated) have been identified. NAU and DHA-E have implemented the Change Management process in these mods. Awaiting further information from the LBB regarding negotiation timeline. LBB has stated that none of that work affects the schedule at present. Work is on-going, and actual work completion is still targeted for end of April 2016. Dates in columns X and Y have been changed to May 2016, due to actual contract completion.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-04 |  |  | 2016-07-15 | 2016-12-15 | 2017-12-15 | 1% | 2017-12-15 | Lot 3.1 Utilities to site - original ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines and change to double-wall pipe through water protection zone. Due to longer than expected review by the German water authority on those specific issues, SGD-Sud, and continued difficulty and quality issues with the LBB A/E firm, the LBB anicipates solicitation release by mid-March 2016, award by Jun 2016, and construction start in Jul 2016. Construction originally targeted for completion Dec 2016; however, now reliant on Lot 3.7 and City of Ktown completion of 6km sewer line connection. Construction completion now targeted for Dec 2017. Solicitation date slip has not affected the overall completion date of Dec 2017. | Lot 3.1 Utilities to site - original ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines and change to double-wall pipe through water protection zone. Due to longer than expected review by the German water authority on those specific issues, SGD-Sud, and continued difficulty and quality issues with the LBB A/E firm, the LBB anicipates solicitation release by mid-March 2016, award by Jun 2016, and construction start in Jul 2016. Construction originally targeted for completion Dec 2016; however, now reliant on Lot 3.7 and City of Ktown completion of 6km sewer line connection. Construction completion now targeted for Dec 2017. Solicitation date slip has not affected the overall completion date of Dec 2017.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-05 |  |  | 2014-08-22 | 2015-03-30 | 2015-05-01 | 100% | 2015-03-30 | Lot 3.2 Traffic Light System - Traffic light system in operation since May 2015. | Lot 3.2 Traffic Light System - Traffic light system in operation since May 2015.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-06 |  |  | 2014-10-08 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31 | Lot 3.3 Construction Sign - Completed in December 2013. | Lot 3.3 Construction Sign - Completed in December 2013.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-07 |  |  | 2014-08-11 | 2014-10-16 | 2014-10-16 | 100% | 2014-10-16 | Lot 3.4 Gas Line Relocation - Construction complete. | Lot 3.4 Gas Line Relocation - Construction complete.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-08 |  |  | 2016-06-30 | 2018-04-30 | 2018-04-30 | 1% | 2018-04-30 | Lot 3.5 Transformers/Substation - This portion of the ROBMCR project is being run as a direct project through NAU. Contract has a "directed subcontractor clause" to allow the electrical provider, the Pfalzwerke, to participate in the design and construction through the contractor, which ensure compatibility with the electrical grid. J&A for that action was finally approved by the PARC on 4 Feb 2016, after nearly 3 months review time. NAU sent out Phase I solicitation (qualifications) of the D/B RFP package on 5 Feb 2016. Bid opening was 7 Mar 2016, with completion of Phase I by the end of Mar 2016. Phase II (technical) is targeted for release in April 2016, with construction contract award still targeted for June 2016. The construction contract will be set up such that the Southern substation will come on line by Dec 2017, and the Northern substation will come on line by Jul 2018. | Lot 3.5 Transformers/Substation - This portion of the ROBMCR project is being run as a direct project through NAU. Contract has a "directed subcontractor clause" to allow the electrical provider, the Pfalzwerke, to participate in the design and construction through the contractor, which ensure compatibility with the electrical grid. J&A for that action was finally approved by the PARC on 4 Feb 2016, after nearly 3 months review time. NAU sent out Phase I solicitation (qualifications) of the D/B RFP package on 5 Feb 2016. Bid opening was 7 Mar 2016, with completion of Phase I by the end of Mar 2016. Phase II (technical) is targeted for release in April 2016, with construction contract award still targeted for June 2016. The construction contract will be set up such that the Southern substation will come on line by Dec 2017, and the Northern substation will come on line by Jul 2018.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-09 |  |  | 2016-04-30 | 2016-12-15 | 2016-12-15 | 1% | 2016-12-15 | Lot 3.6 Water Connection to SWK (Kaiserslautern) system - The FRG received a bid from provider SWK in September 2015; however, the bid was incomplete. The FRG continuing to coordinate with SWK for complete bid. Concurrently, "water providing rights" belong to both the communities of Ramstein Miesenbach and Weilerbach, and they both must officialy and legally transfer authority to the City of Kaiserslautern (Utility Company - SWK) to provide the water. This official action has become a multi-step process; agreements are in draft form and must be ratified by each community mayor/city council. FRG anticipates that the agreement between the communities will be finalized by March or Apr 2016, with target contract award to SWK in Apr 2016 timeframe. This will basically be handled as a connection fee, and FRG has reported that this item will not delay any other features. | Lot 3.6 Water Connection to SWK (Kaiserslautern) system - The FRG received a bid from provider SWK in September 2015; however, the bid was incomplete. The FRG continuing to coordinate with SWK for complete bid. Concurrently, "water providing rights" belong to both the communities of Ramstein Miesenbach and Weilerbach, and they both must officialy and legally transfer authority to the City of Kaiserslautern (Utility Company - SWK) to provide the water. This official action has become a multi-step process; agreements are in draft form and must be ratified by each community mayor/city council. FRG anticipates that the agreement between the communities will be finalized by March or Apr 2016, with target contract award to SWK in Apr 2016 timeframe. This will basically be handled as a connection fee, and FRG has reported that this item will not delay any other features.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-10 |  |  | 2014-12-10 | 2021-12-17 | 2022-03-30 | 1% | 2021-12-17 | Lot 3.9 Site Security - FRG awarded contract in Dec 2013. Security contractor has mobilized and began operation on-site starting 1 May 2015. | Lot 3.9 Site Security - FRG awarded contract in Dec 2013. Security contractor has mobilized and began operation on-site starting 1 May 2015.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-11 |  |  | 2016-08-30 | 2021-12-17 | 2022-03-30 | 1% | 2021-12-17 | 3.10 Site Logistics - Details to be determined by FRG; contract will be for execution of the entire internal and external construction site logistics, basically, the coordination of site activities between the various contractors. FRG anticipates that they can provide initial scope/package for review in Apr/May 2016. | 3.10 Site Logistics - Details to be determined by FRG; contract will be for execution of the entire internal and external construction site logistics, basically, the coordination of site activities between the various contractors. FRG anticipates that they can provide initial scope/package for review in Apr/May 2016.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-12 |  |  | 2016-02-28 | 2016-04-30 | 2016-08-15 | 5% | 2016-08-15 | Lot 2.3 Landfill Remediation. The contract documents spent several months under ABB legal review (Oct 2015 to Jan 2016). Previously, the LBB was trying to rule out the two low bids, but this was not legally supported. ABB made their final ruling that the low bidder proposal was valid, and the LBB awarded the contract to Firma Peter Gross on 5 Feb 2016 (NAU processed ABG4 contract award documentation on 4 Feb 2016). Presently, construciton is underway with no issues; LBB has informed NAU that the construction completion date is 1 Aug 2016. The delay in getting this contract awarded has not caused any delay to other construction activities. | Lot 2.3 Landfill Remediation. The contract documents spent several months under ABB legal review (Oct 2015 to Jan 2016). Previously, the LBB was trying to rule out the two low bids, but this was not legally supported. ABB made their final ruling that the low bidder proposal was valid, and the LBB awarded the contract to Firma Peter Gross on 5 Feb 2016 (NAU processed ABG4 contract award documentation on 4 Feb 2016). Presently, construciton is underway with no issues; LBB has informed NAU that the construction completion date is 1 Aug 2016. The delay in getting this contract awarded has not caused any delay to other construction activities.
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-13 |  |  | 2014-10-23 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31 | Communications Cable relocation - Action 100% complete | Communications Cable relocation - Action 100% complete
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-14 |  |  | 2015-03-30 | 2021-12-30 | 2021-12-30 | 1% | 2021-12-30 | Construction Additional Services | Construction Additional Services
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 4 | 76872 |  |  | 2019-02-12 | 2021-12-08 | 2022-03-30 | 1% | 2022-11-08 | Medical Center (Bed Tower, D&T, Clinics, Admin) - US led 20% MedCen final design submitted 2 Aug 2013. LBB awarded the post-20% MedCen design contract to HDR-TMK on 7 December 2015. Kick-off meeting was held 26-27 January 2016 in Landstuhl. TMK initially submitted 168 questions on the 20% design, all of which were answered prior to the kick-off meeting. TMK submitted an additional 404 questions on 16 Feb 2016, for which answers were provided back to LBB/TMK on 7 Mar 2016. The LBB will have TMK adjust the 20% design through May 2016; the 35% design phase is targeted to begin Jun 2016 and last through Jun 2017. The schedule dates are estimated at this time and will be refined as AE#2 progresses the design. The German govt still supports the goal of construction contract award by the end of calendar year 2017, or shortly thereafter, and project completion in 2022. | Medical Center (Bed Tower, D&T, Clinics, Admin) - US led 20% MedCen final design submitted 2 Aug 2013. LBB awarded the post-20% MedCen design contract to HDR-TMK on 7 December 2015. Kick-off meeting was held 26-27 January 2016 in Landstuhl. TMK initially submitted 168 questions on the 20% design, all of which were answered prior to the kick-off meeting. TMK submitted an additional 404 questions on 16 Feb 2016, for which answers were provided back to LBB/TMK on 7 Mar 2016. The LBB will have TMK adjust the 20% design through May 2016; the 35% design phase is targeted to begin Jun 2016 and last through Jun 2017. The schedule dates are estimated at this time and will be refined as AE#2 progresses the design. The German govt still supports the goal of construction contract award by the end of calendar year 2017, or shortly thereafter, and project completion in 2022.
2016-03-31 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement |  |  |  | 2015-09-08 | 2019-03-09 | 2019-03-09 | 2% | 2019-10-18 | Contractor has mobilized on-site. Preliminary schedule received; review underway. Contractor has started phase one of initial site excavation and spoil site development. Formal partnering is a contract requirment. Initial partnering session was conducted 19/20 Nov 15 with a follow-up session scheduled for 24 Mar 16. Asset ID requested from USAG APG DPW; awaiting response. | Contractor has mobilized on-site. Preliminary schedule received; review underway. Contractor has started phase one of initial site excavation and spoil site development. Formal partnering is a contract requirment. Initial partnering session was conducted 19/20 Nov 15 with a follow-up session scheduled for 24 Mar 16. Asset ID requested from USAG APG DPW; awaiting response.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 77115 | Transient Wounded Warrior Lodging |  | 10111000 | OSD C project for NATO HQ, Brussels PN - 77116 PN - 72414 | 2012-06-18 | 2014-02-02 | 2014-07-18 | 100% | 2014-05-27 | Residual closeout issues. | Residual closeout issues.
2016-03-31 | 2011 | Defense Health Agency | Major Military Construction | Maryland | United States | 77116 | NNMC Parking Expansion |  | 1854000 | PN - 72752 | 2012-06-18 | 2014-02-02 | 2014-07-18 | 100% | 2013-12-02 | Financially Closed | Financially Closed
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 1 |  |  |  | 2013-03-01 | 2016-12-06 | 2018-03-05 | 77% | 2017-06-20 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 2 | 81291 |  |  | 2013-03-01 | 2016-12-06 | 2018-03-05 | 76% | 2017-06-20 | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14 | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2016-03-31 | 2014 | Defense Health Agency | Major Military Construction | New Mexico | United States | 77922 | Medical Clinic Replacement |  | 1900000 | FY14-PN81340 | 2014-10-27 | 2018-01-30 | 2018-01-30 | 26% | 2018-08-16 | Design complete. Project is under construction. Foundation in place. AMEPLS (Arch, Mech, Elec, Plumbing, and landscape) NTP issued 19 Jan 16; IFC (issued for construction) drawings issued; Structural steel demobilized on 15 Feb 16; Second deck concrete placement completed; exterior masonry block has arrived, preparing to drill for dowels and have started placing masonry block. Interior stud framing now going in. | Design complete. Project is under construction. Foundation in place. AMEPLS (Arch, Mech, Elec, Plumbing, and landscape) NTP issued 19 Jan 16; IFC (issued for construction) drawings issued; Structural steel demobilized on 15 Feb 16; Second deck concrete placement completed; exterior masonry block has arrived, preparing to drill for dowels and have started placing masonry block. Interior stud framing now going in.
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | New Mexico | United States | 77979 | Medical/Dental Clinic Replacement |  | 4000000 | FY09-PNS0013 | 2014-04-28 | 2018-02-10 | 2018-06-08 | 22% | 2018-01-08 | Construction activity began on 29 Jul 2015. Work is ongoing. Building footings/spread footings are complete. Prep work for Slab On Grade is about 50% complete. Placement of Slab On Grade for Area C is complete, Area D placement is scheduled for week of 1 Feb. "For Construction" Plans and Specifications for the entire project have been received. NTP for Building Construction was issued on 20 Jan 2016. Despite some weather delays slowing down the foundation placement recently, the building pad is complete, underground utilities are complete and the project is back on track with structural steel going vertical and progressing well. | Construction activity began on 29 Jul 2015. Work is ongoing. Building footings/spread footings are complete. Prep work for Slab On Grade is about 50% complete. Placement of Slab On Grade for Area C is complete, Area D placement is scheduled for week of 1 Feb. "For Construction" Plans and Specifications for the entire project have been received. NTP for Building Construction was issued on 20 Jan 2016. Despite some weather delays slowing down the foundation placement recently, the building pad is complete, underground utilities are complete and the project is back on track with structural steel going vertical and progressing well.
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | Illinois | United States | 78143 | Navy Drug Lab Replacement |  | 644000 | FY13-PN78146 | 2013-11-08 | 2015-01-15 | 2017-06-25 | 98% | 2015-04-20 | Drug Lab BOD Apr 2015, Second Contract to Demo Bldg 38H underway | Drug Lab BOD Apr 2015, Second Contract to Demo Bldg 38H underway
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 78144 | Medical Clinic Addition |  |  |  | 2013-10-08 | 2015-03-17 | 2015-12-21 | 100% | 2015-09-11 | Construction Complete | Construction Complete
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | Virginia | United States | 78146 | Veterinarian Facility |  |  |  | 2014-02-28 | 2014-12-06 | 2015-11-23 | 100% | 2015-09-21 | Construction Complete | Construction Complete
2016-03-31 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 79554 | Child Development Center |  | 2607000 | FY12 - PN67182 FY11 - PN72752 | 2013-03-01 | 2014-02-22 | 2014-06-02 | 100% | 2014-04-07 | Residual closeout issues | Residual closeout issues
2016-03-31 | 2009 | Defense Health Agency | Major Military Construction | Florida | United States | 79845 | Eglin Hospital Alteration (ARRA) |  |  |  | 2011-10-31 | 2014-11-06 | 2015-07-28 | 99% | 2015-03-12 | Contract including all currently identified modifications is at 99.58% of PA. Hospital Command moved into new building Dec 19. Urology, ENT, Lab II, Surgery Phase III move in also completed mid December. Acceptance Aug. 29. Joint Commissioning is competed and generated no action items for the project to correct. Completing punch list items and modification and requests after turnover. | Contract including all currently identified modifications is at 99.58% of PA. Hospital Command moved into new building Dec 19. Urology, ENT, Lab II, Surgery Phase III move in also completed mid December. Acceptance Aug. 29. Joint Commissioning is competed and generated no action items for the project to correct. Completing punch list items and modification and requests after turnover.
2016-03-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | Nevada | United States | 80093 | Medical Ed. & Training Facility |  |  |  | 2012-08-14 | 2013-11-14 | 2014-08-24 | 100% | 2014-09-10 | Switch gear was changed on 18 FEB 2015. Project complete. No punch list items. Contract/project closeout and Evaluation not completed. All else is done. | Switch gear was changed on 18 FEB 2015. Project complete. No punch list items. Contract/project closeout and Evaluation not completed. All else is done.
2016-03-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | Washington | United States | 80094 | Veterinary Clinic |  |  |  | 2013-01-04 | 2014-07-05 | 2014-12-12 | 100% | 2014-12-12 | All contract requirements completed. Final Payment has been processed. | All contract requirements completed. Final Payment has been processed.
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities |  |  |  | 2013-10-15 | 2013-12-13 | 2014-03-25 | 100% | 2014-04-04 | Dosimetry Complete | Dosimetry Complete
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80307 | Implement Base Installation Appearance Plan |  |  |  | 2014-04-01 | 2015-04-08 | 2017-02-28 | 7% | 2016-10-15 | In construction | In construction
2016-03-31 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80308 | Electrical Utility Upgrades |  | 4500000 | FY10 - PN65270 | 2014-10-23 | 2016-02-12 | 2016-09-07 | 60% | 2016-06-27 | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014. | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2016-03-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | Virginia | United States | 80792 | Site Development, NiCOE |  |  |  | 2012-09-10 | 2013-05-31 | 2013-08-29 | 100% | 2013-06-30 | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Project financial closeout is ongoing. Update 03 AUG 2015: Received release of claims from American Water and returned all unobligated MIPR'd funds. Still waiting for return of unobligated MIPR'd funds requested by POC for Dominion Virginian Power. Once these funds are returned project will be closed out. UPDATE 8 JAN: NAO UFC determined that outstanding bill had actually been paid from the wrong line item. This error has been corrected and the project can now be closed out. UPDATE 5 FEB: PM is currently preparing a RED Form (CENAB form used for the Contract Closeout) and submitting it to Contracting Division for final close out actions. UPDATE 07 MAR: NAB has requested Ft. Belvoir DPW return Unliquidated Obligation of $124.88. | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Project financial closeout is ongoing. Update 03 AUG 2015: Received release of claims from American Water and returned all unobligated MIPR'd funds. Still waiting for return of unobligated MIPR'd funds requested by POC for Dominion Virginian Power. Once these funds are returned project will be closed out. UPDATE 8 JAN: NAO UFC determined that outstanding bill had actually been paid from the wrong line item. This error has been corrected and the project can now be closed out. UPDATE 5 FEB: PM is currently preparing a RED Form (CENAB form used for the Contract Closeout) and submitting it to Contracting Division for final close out actions. UPDATE 07 MAR: NAB has requested Ft. Belvoir DPW return Unliquidated Obligation of $124.88.
2016-03-31 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 80904 | Mechanical & Electrical Improvements |  |  |  | 2015-05-31 | 2017-02-07 | 2017-05-18 | 20% | 2017-05-10 | In construction | In construction
2016-03-31 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 80913 | Parking Garage |  |  |  | 2014-11-30 | 2016-04-16 | 2017-02-06 | 5% | 2017-03-01 | In construction | In construction
2016-03-31 | 2014 | Defense Health Agency | Major Military Construction | Texas | United States | 81340 | SAMMC Hyperbaric Facility Addition |  |  |  | 2015-07-10 | 2016-09-30 | 2016-09-30 | 43% | 2016-12-28 | * Scope: FY14 Design-Build project to relocate the existing 6-person hyperbaric chamber from WHMC at JBSA (Lackland AFB) to SAMMC Hospital. * Contractor re-base-lined schedule in Jan; informally notified USACE in Feb that the schedule would slip approximately 10 weeks. Contractor stated delay is from concrete subcontractors performance. Awaiting formal revised schedule. USACE coordinated with AFCEC, AFMSA, and 59MDW. End user is planning additional time in their transition schedule to accommodate any construction related schedule delay. * Floor slab placed 28 Mar 16. * Steel erection complete. * Coordination with 59MDW for transition and chamber relocation ongoing | * Scope: FY14 Design-Build project to relocate the existing 6-person hyperbaric chamber from WHMC at JBSA (Lackland AFB) to SAMMC Hospital. * Contractor re-base-lined schedule in Jan; informally notified USACE in Feb that the schedule would slip approximately 10 weeks. Contractor stated delay is from concrete subcontractors performance. Awaiting formal revised schedule. USACE coordinated with AFCEC, AFMSA, and 59MDW. End user is planning additional time in their transition schedule to accommodate any construction related schedule delay. * Floor slab placed 28 Mar 16. * Steel erection complete. * Coordination with 59MDW for transition and chamber relocation ongoing
2016-03-31 | 2015 | Defense Health Agency | Major Military Construction | Texas | United States | 81423 | Medical Clinic Replacement (Reid Clinic) |  |  |  | 2015-11-03 | 2017-12-18 | 2017-12-18 | 6% | 2018-03-16 | * Contract awarded to J.E. Dunn construction (on SWL Air Force Medical MATOC) on 3 Sep 2015. * Design Charrette held 9-13 Nov * 35% Design Review conference held 22-27 Feb 16; 65% design review scheduled for 23 May | * Contract awarded to J.E. Dunn construction (on SWL Air Force Medical MATOC) on 3 Sep 2015. * Design Charrette held 9-13 Nov * 35% Design Review conference held 22-27 Feb 16; 65% design review scheduled for 23 May
2016-03-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | Washington | United States | 81627 | NiCOE Satellite, Infrastructure Support |  |  |  | 2016-03-28 | 2017-11-14 | 2017-11-14 | 1% | 2017-11-14 | Partnering Conference scheduled the week of 11 Apr 16. | Partnering Conference scheduled the week of 11 Apr 16.
2016-03-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | North Carolina | United States | 81631 | NiCOE Satellite, Infrastructure Support |  |  |  | 2014-06-30 | 2016-02-01 | 2016-05-01 | 98% | 2016-05-01 | The NICoE Clinic Ribbon Cutting Ceremony was held at 11 AM Thursday, 31 Mar 16. The Contractor submitted an engineering report on 2 Mar 16 with direction to conduct a test pit by removing underlain layer of silty sand or clay to achieve the proper drainage in the two Infiltration Basins. | The NICoE Clinic Ribbon Cutting Ceremony was held at 11 AM Thursday, 31 Mar 16. The Contractor submitted an engineering report on 2 Mar 16 with direction to conduct a test pit by removing underlain layer of silty sand or clay to achieve the proper drainage in the two Infiltration Basins.
2016-03-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | Texas | United States | 81706 | NiCOE Satellite, Infrastructure Support |  |  |  | 2014-09-15 | 2015-10-28 | 2015-12-11 | 99% | 2015-11-20 | All site work complete as of 22 Feb 16; Building contractor has completely vacated site. Ribbon cutting completed as of 9 Mar 16. Awaiting DD1354 to be signed by end-user. Also waiting on final as-built drawings from site contractor. | All site work complete as of 22 Feb 16; Building contractor has completely vacated site. Ribbon cutting completed as of 9 Mar 16. Awaiting DD1354 to be signed by end-user. Also waiting on final as-built drawings from site contractor.
2015-10-30 | 2013 | Defense Information Systems Agency | Major Military Construction |  | Germany | 13DISA01 | DISA Europe Facility Upgrade |  |  |  | 2015-08-19 | 2016-12-31 | 2016-12-31 |  |  | PA: $2.224M. Contract awarded to Bauamt on 19 Aug 2015. Kick Off Meeting held 20 Oct 2015.. Next meeting scheduled 2 Dec 2015. | PA: $2.224M. Contract awarded to Bauamt on 19 Aug 2015. Kick Off Meeting held 20 Oct 2015.. Next meeting scheduled 2 Dec 2015.
2015-10-30 | 2014 | Defense Information Systems Agency | Major Military Construction | Hawaii | United States | 14DISA01 | DISA Pacific Facility Upgrade | [8 empty] | PA: $2.615M. NAVFAC preparing RFP for Design. Kick off mtg 13 Oct. Three day design charrette scheduled 8-10 Dec 2015. No contract award. Currently all work done in-house. | PA: $2.615M. NAVFAC preparing RFP for Design. Kick off mtg 13 Oct. Three day design charrette scheduled 8-10 Dec 2015. No contract award. Currently all work done in-house.
2015-10-30 | 2015 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 15DISA01 | Design/Renovate Bldg 52120 for JITC | [8 empty] | PA: $1.871M. Design/Renovation of Bldg 52120. USACE conducted site survey 27-28 Apr 2015. Design charrette held 30 Jun 2015. 65% design comments provided. 65% design review 30 Nov-2 Dec 2015. No contract award. Currently all work done in-house. | PA: $1.871M. Design/Renovation of Bldg 52120. USACE conducted site survey 27-28 Apr 2015. Design charrette held 30 Jun 2015. 65% design comments provided. 65% design review 30 Nov-2 Dec 2015. No contract award. Currently all work done in-house.
2015-10-30 | 2015 | Defense Information Systems Agency | Major Military Construction | Arizona | United States | 15DISA01 | Design of Bldgs 52101, 52110, 52111 for JITC | 1 | [7 empty] | PA: $745K. Design of Garrison existing Bldgs 52101, 52110, 52111 for JITC Fort Huachuca. Design charrette scheduled 30 Nov-2 Dec 2015. Design funding covered under consolidated FY15 Planning and Design Appropriation. USACE will schedule early FY16. | PA: $745K. Design of Garrison existing Bldgs 52101, 52110, 52111 for JITC Fort Huachuca. Design charrette scheduled 30 Nov-2 Dec 2015. Design funding covered under consolidated FY15 Planning and Design Appropriation. USACE will schedule early FY16.
2015-10-30 | 2015 | Defense Information Systems Agency | Major Military Construction |  | Australia | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) | [8 empty] | PA: $9.6M. NAVFAC to construct Electronic Equip Bldg, Antenna Foundations for AN/GSB 52B Medium Satellite Earth Terminals. DB RFP slated 25 Nov 2015. No contract award. Currently all work done in-house. | PA: $9.6M. NAVFAC to construct Electronic Equip Bldg, Antenna Foundations for AN/GSB 52B Medium Satellite Earth Terminals. DB RFP slated 25 Nov 2015. No contract award. Currently all work done in-house.
2015-10-30 | 2013 | Defense Information Systems Agency | Major Military Construction | Illinois | United States | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  |  |  | 2014-03-01 | 2015-12-30 | 2016-03-11 | 85% |  | PA: $77.515M. 3 separate contracts: Soil Remediation; Construction; Demo Bldg 3189. Soil Remediation: COMPLETED; Construction ESC: 11 Mar 2016;. Demo of Bldg 3189 funding ($2.153M) provided to USACE on 30 Jun 2015. | PA: $77.515M. 3 separate contracts: Soil Remediation; Construction; Demo Bldg 3189. Soil Remediation: COMPLETED; Construction ESC: 11 Mar 2016;. Demo of Bldg 3189 funding ($2.153M) provided to USACE on 30 Jun 2015.
2015-08-31 | 2008 | Defense Intelligence Agency | Major Military Construction | District Of Columbia | United States | 154207 | Emergency Backup Water System |  |  |  | 2009-10-03 | 2011-09-16 | 2012-01-20 | 100% | 2012-01-20 | Approp. - $1,012 | Approp. - $1,012
2015-08-31 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction |  | Korea, South | DIA10-001 | FOB-K Renovation of Two Buildings to Include Administrative and SCIF Spaces |  |  |  | 2012-04-09 | 2013-10-09 | 2013-10-17 | 100% |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project closed out 10 May 2015. | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project closed out 10 May 2015.
2015-08-31 | 2010 | Defense Intelligence Agency | Major Military Construction | Alabama | United States | DIA10-002 | Replace MSIC Explosive Ordinance Exploitation (EOE) Complex |  |  |  | 2012-07-20 | 2014-01-20 | 2014-05-21 | 100% |  | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Contingency funds will be used in FY15 for within scope modifications. | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Contingency funds will be used in FY15 for within scope modifications.
2015-08-31 | 2011 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA11-002 | JBAB Paving of Gravel Parking Lot |  | 690000 | DIA10-001 | 2011-07-20 | 2012-07-18 | 2012-07-25 | 99% | 2012-07-25 | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout. | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA12000001 | DIAC Parking Garage Replacement |  |  |  | 2014-10-23 | 2016-03-02 | 2016-10-20 | 25% |  | Approp. - $13,645 - $793,156 CAT I obligated. Building pad grading completed. Geo-Constructors continues geo-pier installation. A total of 268 out of 407 piers have been installed. Current activities include sediment and erosion control repairs and cleanup of group spillage inside the DIA security barrier. Working on the elevator penthouse design. Amount of $1.6M added to this project from Construction of the Remote Delivery Facility, DIA project DIA12000005 as a below threshhold realignment. Funds are committed awaiting contract award (obligation). | Approp. - $13,645 - $793,156 CAT I obligated. Building pad grading completed. Geo-Constructors continues geo-pier installation. A total of 268 out of 407 piers have been installed. Current activities include sediment and erosion control repairs and cleanup of group spillage inside the DIA security barrier. Working on the elevator penthouse design. Amount of $1.6M added to this project from Construction of the Remote Delivery Facility, DIA project DIA12000005 as a below threshhold realignment. Funds are committed awaiting contract award (obligation).
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center | [8 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions to add funds from the DIAC Chiller project. Reprogamming action approved for FY-15 but not FY-16. DIA assessing options. | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions to add funds from the DIAC Chiller project. Reprogamming action approved for FY-15 but not FY-16. DIA assessing options.
2015-08-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA12000003 | DIAC Chilled Water Project for Data Center |  | 2070000 | $2,070K diverted to DIA (UPS) Data Center, project DIA12000002, approved MILCON Reprogramming. | [5 empty] | Estimates indicate project costs exceed programmed amounts. DIA initiating reprogramming action to move funds to UPS for Data Center. Awaiting reprogramming action approval. | Estimates indicate project costs exceed programmed amounts. DIA initiating reprogramming action to move funds to UPS for Data Center. Awaiting reprogramming action approval.
2015-08-31 | 2012 | Defense Intelligence Agency | Major Military Construction | Virginia | United States | DIA12000005 | Construction of Remote Delivery Facility (RDF) Meeting SCIF Standards |  | 1600000 | $1.6M diverted to DIA Parking Garage, project DIA12000001 as a below threshhold re-alignment. | 2013-10-10 | 2014-09-30 | 2015-07-31 | 100% |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Final as-builts received. All warranty issues have been resolved. Amount of $1.6M diverted to DIA Parking Garage Replacement, project DIA12000001 as a below threshhold re-alignment. | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Final as-builts received. All warranty issues have been resolved. Amount of $1.6M diverted to DIA Parking Garage Replacement, project DIA12000001 as a below threshhold re-alignment.
2015-08-31 | 2013 | Defense Intelligence Agency | Unspecified Minor Military Construction | District Of Columbia | United States | DIA13000001 | Parking Garage Demolition | [8 empty] | This line was reduced due to sequestration. The remaining funds are insufficient to complete demolition of the existing parking garage. DIA is currently exploring options. Contract is not awarded at this time. | This line was reduced due to sequestration. The remaining funds are insufficient to complete demolition of the existing parking garage. DIA is currently exploring options. Contract is not awarded at this time.
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction | Georgia | United States | AM 856 07 | New Elementary School |  |  |  | 2012-08-01 | 2013-12-14 | 2014-03-14 | 99% | 2014-08-01
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00023 | Replace McBride Elementary School |  |  |  | 2013-12-11 | 2015-12-11 | 2016-04-04 | 85%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00023 | Replace McBride Elementary School | 28 |  |  | 2013-12-11 | 2015-12-11 | 2016-04-04 | 85%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00024 | Faith Middle School Addition |  |  |  | 2014-10-28 | 2016-01-21 | 2016-04-22 | 75%
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00025 | Replace Delalio Elementary School |  |  |  | 2014-02-24 | 2016-06-01 | 2017-05-20 | 39% |  | The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17. | The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00026 | Replace Kingsolver/Pierce School |  |  |  | 2014-03-11 | 2015-11-11 | 2016-04-29 | 75%
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00026 | Replace Consolidate Kingsolver/Pierce Elem Schools | 43 |  |  | 2015-12-01 | 2016-11-30 | 2016-11-30 | 0%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00027 | Replace Hanscom Middle School |  |  |  | 2014-02-11 | 2016-04-21 | 2016-04-27 | 88%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School |  | 800000 | PA00033 | 2014-03-27 | 2015-12-17 | 2016-04-16 | 83%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00028 | Replace Barkley Elementary School | 44 |  |  | 2014-03-27 | 2015-12-17 | 2016-04-16 | 83%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00031 | Pope Holbrook Elementary School |  |  |  | 2015-02-11 | 2017-02-10 | 2017-03-04 | 21%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction | Tennessee | United States | AM00034 | Replace Fort Campbell High School |  |  |  | 2015-01-27 | 2017-02-25 | 2017-06-16 | 35%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction | South Carolina | United States | AM00037 | Replace Bolden-Galer Elementary School |  |  |  | 2015-08-18 | 2018-06-28 | 2018-06-28 | 5% |  | Project was awarded to second highest bidder following original contractor being terminated for cause. | Project was awarded to second highest bidder following original contractor being terminated for cause.
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00038 | Diamond Elementary School Replacement |  |  |  | 2014-10-15 | 2016-09-14 | 2016-12-05 | 43%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction | Kentucky | United States | AM00040 | Replace Marshall Elementary School |  |  |  | 2014-08-06 | 2016-03-28 | 2016-05-16 | 88%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00050 | White Elementary School Replacement |  |  |  | 2014-12-16 | 2016-10-31 | 2016-12-18 | 32%
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM100801 | Replace Elementary School (Murray ES) |  |  |  | 2012-09-12 | 2014-04-03 | 2014-08-27 | 100% | 2014-08-25 | Remove at end of FY15 | Remove at end of FY15
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction | New York | United States | AM2455205 | Construct Addition and Renovate West Point MS |  |  |  | 2011-11-28 | 2014-09-28 | 2014-03-17 | 100% | 2014-03-17 | Remove at end of FY15 | Remove at end of FY15
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction | Virginia | United States | AM2455206 | Replace/Consolidate Elementary Schools |  |  |  | 2012-09-29 | 2014-09-30 | 2016-01-21 | 100% | 2015-04-13 | Remove at end of FY16 | Remove at end of FY16
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction | Puerto Rico | Puerto Rico | AM8193 01 | Replace Elementary School (Antilles ES) |  |  |  | 2012-07-18 | 2014-04-19 | 2014-05-10 | 92%
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction | North Carolina | United States | AMD02051 | Replace Elementary School ( McNair ES) |  | 2056000 | AM00025, PA00033 | 2012-09-12 | 2014-04-03 | 2014-08-27 | 100% | 2014-08-25 | $1,443 supported AM0025 and $613 supported PA00033. Remove end of FY15 | $1,443 supported AM0025 and $613 supported PA00033. Remove end of FY15
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction |  | Belgium | D9124-1 | Replace Schools (SHAPE MS/HS) |  |  |  | 2012-01-18 | 2014-04-17 | 2015-05-31 | 99% | 2014-07-04
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction |  | Belgium | D9124-1 | Replace Schools (SHAPE MS/HS) | 17 |  |  | 2012-07-05 | 2015-07-23 | 2016-09-29 | 95% | 2012-12-05
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction |  | Belgium | D9124-1 | Replace Schools (SHAPE MS/HS) | 18 |  |  | 2012-08-01 | 2015-01-13 | 2015-09-19 | 99% | 2015-02-12
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School |  |  |  | 2016-06-06 | 2016-02-24 | 2016-02-24 | 0%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School | 45 |  |  | 2016-06-06 | 2016-02-24 | 2016-02-24 | 0%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement |  |  |  | 2016-12-19 | 2019-08-01 | 2019-08-01 | 0%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School |  |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 36%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 33 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 36%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 34 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 36%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00043 | Replace Wiesbaden High School | 35 |  |  | 2015-05-18 | 2017-06-21 | 2017-06-21 | 36%
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00053 | Replace Elementary/Middle School (Ansbach EMS) |  |  |  | 2013-10-28 | 2015-03-10 | 2015-08-20 | 99% | 2015-09-23
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00053 | Replace Elementary/Middle School (Ansbach EMS) | 25 |  |  | 2013-10-28 | 2015-03-10 | 2015-08-20 | 99% | 2015-09-23
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00062 | Netzaberg Middle School Addition |  |  |  | 2014-06-05 | 2015-09-20 | 2015-11-24 | 100% | 2015-12-21
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00062 | Netzaberg Middle School Addition | 42 |  |  | 2014-06-05 | 2015-09-20 | 2015-11-24 | 100% | 2015-12-21
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) |  |  |  | 2011-05-09 | 2013-01-19 | 2013-01-19 | 100% | 2013-09-13 | Remove at end of FY15 | Remove at end of FY15
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8268 02 | Replace School (Boblingen HS) |  | 3999000 | PA00033 | 2013-07-29 | 2015-04-30 | 2015-06-23 | 99% | 2015-08-25
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8268 02 | Replace School (Boblingen HS) | 13 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 99% | 2015-08-25
2016-04-04 | 2011 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8268 02 | Replace School (Boblingen HS) | 14 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 99% | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Belgium | EUR 8318 09 | Replace School (SHAPE ES) |  |  |  | 2012-01-18 | 2014-04-17 | 2015-05-31 | 99% | 2014-07-04
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Belgium | EUR 8318 09 | Replace School (SHAPE ES) | 11 |  |  | 2012-07-05 | 2015-07-23 | 2016-09-29 | 95% | 2012-12-05
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8320 03 | Replace School (Boblingen ES) |  | 1475000 | PA00033 | 2013-07-29 | 2015-04-30 | 2015-06-23 | 99% | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8320 03 | Replace School (Boblingen ES) | 8 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 99% | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR 8320 03 | Replace School (Boblingen ES) | 9 |  |  | 2013-07-29 | 2015-04-30 | 2015-06-23 | 99% | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 12%
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 3 |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 12%
2016-04-04 | 2010 | DoD Education Activity | Major Military Construction |  | Germany | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 4 |  |  | 2015-06-03 | 2018-03-01 | 2018-03-01 | 12%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction |  | Korea, South | PA00018 | Daegu Middle/High School Replacement |  |  |  | 2014-09-29 | 2016-10-03 | 2016-11-11 | 39%
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction |  | Japan | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB |  | 634000 | PA00033 | 2013-03-26 | 2015-07-25 | 2015-07-25 | 100% | 2015-05-01 | Remove at end of FY15 | Remove at end of FY15
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction |  | Korea, South | PA00020 | Replace Elementary School (Osan ES) |  | 6444000 | PA00033 | 2013-09-30 | 2015-12-09 | 2016-05-10 | 92%
2016-04-04 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00021 | Replace Sasebo Elementary School |  |  |  | 2016-04-04 | 2018-11-03 | 2018-11-03 | 0%
2016-04-04 | 2012 | DoD Education Activity | Major Military Construction |  | Japan | PA00027 | Replace Yokota High School |  |  |  | 2015-02-19 | 2018-12-21 | 2018-12-21 | 7%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction |  | Japan | PA00030 | Replace Zukeran Elementary School |  |  |  | 2014-10-23 | 2017-04-01 | 2017-04-05 | 16%
2016-04-06 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  |  |  | 2014-07-07 | 2016-10-24 | 2017-01-16 | 30%
2016-04-06 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 38 |  |  | 2014-07-07 | 2016-10-24 | 2017-01-16 | 30%
2016-04-06 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 39 |  |  | 2014-07-07 | 2016-10-24 | 2017-01-16 | 30%
2016-04-06 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 40 |  |  | 2014-07-07 | 2016-10-24 | 2017-01-16 | 30%
2016-04-04 | 2014 | DoD Education Activity | Major Military Construction |  | Japan | PA00035 | Kadena Middle School Addition/Renovation |  |  |  | 2015-03-06 | 2016-10-02 | 2016-10-31 | 20%
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND |  |  |  | 2013-09-19 | 2016-01-18 | 2016-07-09 | 89% | 2016-05-20
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146601 | ARMORY |  |  |  | 2013-09-19 | 2015-04-08 | 2015-11-20 | 100% | 2015-11-20
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY |  |  |  | 2012-03-29 | 2013-08-14 | 2014-11-24 | 100% | 2014-04-29
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M00243313 | ENTRY CONTROL POINT (GATE 5) |  |  |  | 2014-01-03 | 2015-04-29 | 2016-05-05 | 88% | 2015-04-29
| 2014 | Marine Corps Active | Major Military Construction | California | United States | M00243520 | STEAM PLANT DECENTRALIZATION |  |  |  | 2015-10-13 | 2018-01-11 | 2018-01-11 | 3% | 2018-01-11
| 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263382 | FRONT GATE AT/FP IMPROVMENTS |  |  |  | 2013-10-30 | 2015-04-12 | 2016-01-31 | 97% | 2015-12-09
| 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M002641406 | ATC TX/RX RELOCATION |  |  |  | 2015-05-15 | 2016-11-21 | 2016-11-21 | 4% | 2016-11-21
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR |  |  |  | 2012-09-25 | 2014-03-28 | 2014-12-09 | 100% | 2014-09-01
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  |  |  | 2013-10-07 | 2016-11-06 | 2017-12-22 | 13% | 2017-12-22
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 |  | 2982000 | N32446308 | 2012-12-14 | 2016-11-06 | 2017-12-22 | 98% | 2017-12-22
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION |  |  |  | 2012-08-10 | 2013-09-05 | 2015-06-12 | 100% | 2015-06-12
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264572 | INFRASTRUCTURE WIDEN RUSSELL ROAD |  |  |  | 2015-10-15 | 2017-05-28 | 2017-05-28 | 10% | 2017-03-26
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264611 | BACHELOR ENLISTED QUARTERS |  |  |  | 2012-10-13 | 2014-10-16 | 2015-07-22 | 100% | 2015-05-21
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264612 | ENLISTED DINING FACILITY |  |  |  | 2012-10-13 | 2014-10-16 | 2015-07-22 | 100% | 2015-05-21
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264621 | EMBASSY SECURITY GROUP FACILITIES |  |  |  | 2013-03-14 | 2015-03-15 | 2016-07-21 | 100% | 2015-08-15
| 2012 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264632 | ACADEMIC INSTRUCTION FACILITY |  | 9500000 | N47608561; N32446308 | 2012-10-09 | 2014-08-16 | 2015-08-17 | 100% | 2015-08-17
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264644 | WEAPONS TRAINING BATALLION MESS HALL |  |  |  | 2013-09-18 | 2015-04-22 | 2016-04-30 | 95% | 2016-06-30
| 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264677 | TECOM SCHOOLS ACADEMIC INSTRUCTION FACILITY |  |  |  | 2016-04-14 | 2018-01-05 | 2018-01-05 | 1% | 2018-01-05
| 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318778 | ARMORY ADDITION AND RENOVATION |  |  |  | 2015-03-27 | 2017-08-09 | 2017-08-09 | 5% | 2017-08-09
| 2012 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318822 | MCAS OPERATIONS COMPLEX |  |  |  | 2012-05-02 | 2014-03-17 | 2014-12-29 | 100% | 2014-12-29
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318852 | 3RD RADIO BATTALION COMPLEX |  |  |  | 2014-09-19 | 2016-10-04 | 2016-10-04 | 5% | 2017-04-30
| 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318861 | FACILITY MODIFICATIONS FOR VMU, MWSD AND CH53E |  |  |  | 2015-09-15 | 2017-09-28 | 2017-09-28 | 1% | 2017-09-28
| 2014 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | M0031886167 | TEMPORARY MEDICAL FACILITY SITE PREPARATION |  |  |  | 2015-01-05 | 2015-07-07 | 2015-09-11 | 100% | 2016-04-07
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318864 | AIRCRAFT MAINTENANCE EXPANSION |  |  |  | 2014-04-30 | 2015-09-09 | 2015-10-18 | 100% | 2015-10-22
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  |  |  | 2014-10-14 | 2016-12-18 | 2016-12-18 | 6% | 2017-10-10
| 2013 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318904 | MV-22 HANGAR AND INFRASTRUCTURE |  |  |  | 2013-12-31 | 2015-09-10 | 2015-09-29 | 100% | 2016-06-30
| 2013 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318905 | AIRCRAFT STAGING AREA |  |  |  | 2013-12-31 | 2015-09-10 | 2015-09-29 | 100% | 2016-06-30
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  |  |  | 2015-04-28 | 2017-01-03 | 2017-01-03 | 5% | 2017-08-18
| 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318908 | MV-22 HANGAR |  |  |  | 2015-04-28 | 2017-01-03 | 2017-01-03 | 15% | 2017-08-18
| 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318924 | ROAD & INFRASTRUCTURE IMPROVEMENTS |  |  |  | 2015-10-12 | 2016-11-24 | 2016-11-24 | 1% | 2016-12-27
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M006811037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE |  | 3288000 | N00246909; N32446308 | 2012-04-06 | 2013-01-21 | 2013-08-05 | 100% | 2013-08-05
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M006811040 | INTERSECTION BRIDGE AND IMPROVEMENTS |  |  |  | 2012-09-07 | 2013-09-27 | 2014-06-24 | 100% | 2014-05-23
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M006811045 | NEW POTABLE WATER CONVEYANCE |  | 16682000 | N684691400 | 2012-10-12 | 2016-03-31 | 2016-03-31 | 79% | 2017-12-01
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M006811132 | COMMUNICATION INFORMATION SYSTEMS OPS COMPLEX |  |  |  | 2016-04-07 | 2020-01-23 | 2020-01-23 | 1% | 2020-01-23
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M006811176 | SAN JACINTO ROAD EXTENSION |  |  |  | 2014-10-08 | 2016-04-21 | 2016-06-17 | 20% | 2016-08-29
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M00681532 | ARMORY, 1ST MARINE DIVISION |  | 1586000 | M00681970 | 2012-09-14 | 2013-12-24 | 2014-12-23 | 100% | 2014-04-23
| 2014 | Marine Corps Active | Major Military Construction | California | United States | M00681970 | AMMUNITION SUPPLY POINT FACILITIES PULGAS |  |  |  | 2016-01-13 | 2018-04-27 | 2018-04-27 | 1% | 2018-04-27
| 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169427 | GROUND SUPPORT EQUIPMENT SHOP |  |  |  | 2013-08-22 | 2014-08-14 | 2015-01-20 | 100% | 2015-12-01
| 2012 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169442 | VERTICAL LANDING PADS FOR F-35B |  | 2444000 | N32414547 | 2012-04-13 | 2013-08-07 | 2013-09-27 | 100% | 2013-10-21
| 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169456 | SIMULATED LHD FLIGHT DECK |  |  |  | 2013-07-10 | 2014-07-11 | 2015-12-29 | 100% | 2016-01-29
| 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2014-08-29 | 2016-09-08 | 2017-02-15 | 56% | 2017-02-15
| 2013 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169472 | AIRFIELD SECURITY UPGRADES |  |  |  | 2013-07-15 | 2014-03-28 | 2015-10-24 | 100% | 2014-10-28
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M62204925 | DIP TANK CLEANING FACILITY |  |  |  | 2012-04-04 | 2013-09-27 | 2014-04-09 | 100% | 2014-09-18
| 2015 | Marine Corps Active | Major Military Construction | California | United States | M62204939 | ENGINE DYNAMOMETER FACILITY |  |  |  | 2015-04-14 | 2016-10-06 | 2016-10-06 | 43% | 2016-10-06
| 2012 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626130601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 |  |  |  | 2012-08-13 | 2013-11-23 | 2013-12-14 | 100% | 2013-12-13
| 2013 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626130901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 |  |  |  | 2014-06-22 | 2015-10-13 | 2015-10-13 | 100% | 2016-03-28
| 2012 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 |  |  |  | 2012-08-14 | 2014-12-20 | 2015-02-02 | 100% | 2015-02-20
| 2015 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131502 | WHOLEHOUSE REVITALIZATION MIDRISE 656 |  |  |  | 2015-10-11 | 2017-01-30 | 2017-01-30 | 1% | 2017-01-30
| 2013 | Marine Corps Active | Major Military Construction |  | Japan | M62613995 | MAINTENANCE HANGAR IMPROVEMENTS |  |  |  | 2014-06-06 | 2015-06-14 | 2015-06-14 | 100% | 2015-06-14
| 2013 | Marine Corps Active | Major Military Construction |  | Japan | M62613996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH |  |  |  | 2014-08-08 | 2015-09-24 | 2015-09-24 | 100% | 2015-09-24
| 2013 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974378 | SECURITY OPERATIONS COMPLEX |  |  |  | 2013-11-14 | 2015-07-31 | 2016-09-26 | 41% | 2016-04-28
| 2012 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974535 | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 5983000 | N684691400 | 2012-09-20 | 2014-07-07 | 2015-06-27 | 100% | 2015-03-12
| 2012 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) |  |  |  | 2012-04-03 | 2014-05-20 | 2014-12-03 | 100% | 2014-12-17
| 2013 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974566 | COMBAT AIRCRAFT LOADING APRON |  | 2574000 | Design | 2013-10-11 | 2014-09-22 | 2015-07-26 | 100% | 2015-03-15
| 2012 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974575 | AUXILIARY LANDING FIELD (JSF) |  | 11951000 | N42237636, FY 15 Prior Year Rescission, N32414547 | 2012-07-09 | 2013-06-25 | 2014-01-31 | 100% | 2014-02-21
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001003 | STAFF NCO ACADEMY FACILITIES |  |  |  | 2013-09-19 | 2015-09-01 | 2016-05-18 | 100% | 2016-06-14
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001030 | SQUAD BATTLE COURSE |  | 3994000 | M00681970; N32446308 | 2012-07-05 | 2014-05-17 | 2015-01-24 | 100% | 2015-01-24
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER |  |  |  | 2012-05-14 | 2014-07-24 | 2016-03-02 | 100% | 2016-03-02
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011349 | SPECIAL OPERATIONS TRAINING COMPLEX |  |  |  | 2015-09-14 | 2017-03-21 | 2017-03-21 | 5% | 2017-03-21
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011353 | LANDFILL, PHASE 4 |  |  |  | 2014-09-08 | 2016-03-01 | 2016-03-01 | 87% | 2016-09-01
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK |  |  |  | 2012-07-13 | 2014-07-29 | 2016-08-31 | 100% | 2016-08-31
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011383 | BASE ENTRY POINT AND ROAD |  |  |  | 2012-04-17 | 2015-04-18 | 2016-09-14 | 97% | 2016-09-14
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011384 | BASE ACCESS AND ROAD, PHASE 3 |  |  |  | 2012-04-17 | 2015-04-18 | 2016-09-14 | 81% | 2016-09-14
| 2012 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011425 | OVERHEAD RANGE BAFFLE SYSTEM |  |  |  | 2013-03-06 | 2014-04-17 | 2014-11-29 | 100% | 2014-11-29
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011445 | STEAM DECENTRALIZATION (CAMP JOHNSON) |  |  |  | 2015-02-06 | 2017-02-04 | 2017-04-20 | 85% | 2017-04-20
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011447 | STEAM DECENTRALIZATION - HADNOT POINT |  |  |  | 2015-02-06 | 2016-02-19 | 2017-04-20 | 29% | 2017-04-20
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011448 | STEAM DECENTRALIZATION (BEQ NODES) |  |  |  | 2015-02-06 | 2016-02-19 | 2016-02-19 | 20% | 2016-03-23
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001674 | CORROSION CONTROL HANGAR |  |  |  | 2015-09-02 | 2017-03-11 | 2017-03-11 | 6% | 2017-05-24
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY |  |  |  | 2014-06-13 | 2015-12-20 | 2016-03-30 | 13% | 2016-07-20
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001705 | AIRCRAFT MAINTENANCE HANGAR AND APRON |  | 3690000 | N32414547 | 2012-06-12 | 2014-07-07 | 2015-08-11 | 100% | 2015-08-11
| 2012 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001710 | ORDNANCE LOADING AREA ADDITION |  | 1614000 | N32414547, M00681970 | 2012-06-12 | 2014-07-07 | 2015-08-11 | 100% | 2015-08-11
| 2013 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001711 | PERSONNEL ADMINISTRATION CENTER |  |  |  | 2013-09-20 | 2015-07-06 | 2016-04-16 | 99% | 2016-04-30
| 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001726 | REGIONAL COMMUNICATION STATION |  |  |  | 2014-06-13 | 2015-12-20 | 2016-03-30 | 47% | 2016-07-20
| 2014 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  |  |  | 2014-09-24 | 2016-01-25 | 2016-01-25 | 18% | 2016-01-25
| 2014 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004954 | CERS DISPATCH FACILITY |  |  |  | 2014-06-16 | 2015-06-02 | 2015-06-02 | 100% | 2015-06-02
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67399105 | TRACKED VEHICLE MAINTENANCE COVER |  |  |  | 2012-06-29 | 2014-03-22 | 2014-03-22 | 100% | 2013-04-10
| 2015 | Marine Corps Active | Major Military Construction | California | United States | M67399159 | CAMP WILSON INFRASTRUCTURE UPGRADES |  |  |  | 2015-04-29 | 2017-05-01 | 2017-05-01 | 30% | 2017-05-01
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA |  |  |  | 2012-08-27 | 2014-09-02 | 2016-09-20 | 89% | 2016-05-03
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67399212 | CHILD DEVELOPMENT CENTER |  |  |  | 2012-06-19 | 2013-12-12 | 2016-02-01 | 100% | 2016-02-01
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67399541 | MULTI-PURPOSE BUILDING ADDITION |  |  |  | 2012-10-11 | 2014-04-20 | 2016-04-20 | 100% | 2016-04-20
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67399991 | LAND EXPANSION |  | 2320000 | N32446308 | 2015-01-29 | 2016-01-15 | 2016-01-15 | 1% | 2016-01-15
| 2014 | Marine Corps Active | Major Military Construction |  | Japan | M67400201 | AIRFIELD SECURITY UPGRADES |  |  |  | 2014-05-02 | 2015-10-26 | 2015-10-26 | 89% | 2015-10-26
| 2013 | Marine Corps Active | Unspecified Minor Military Construction |  | Japan | M67400305 | DEMOLISH 45 HOUSING UNITS, KISHABA HOUSING |  |  |  | 2014-10-09 | 2015-06-29 | 2015-06-29 | 100% | 2015-06-29
| 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400803 | AIRCRAFT MAINT HANGAR ALTERATIONS AND SAP-F |  |  |  | 2016-01-05 | 2017-09-12 | 2017-09-12 | 1% | 2017-09-12
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M67604113 | MV-22 AVIATION SIMULATOR BUILDING |  |  |  | 2013-06-27 | 2014-09-21 | 2014-09-21 | 100% | 2014-09-18
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67604114 | MV-22 DOUBLE HANGAR REPLACEMENT |  | 7556000 | N684691400; N32446308 | 2012-08-03 | 2015-08-10 | 2015-12-29 | 100% | 2015-12-29
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67604116 | MV-22 AVIATION PAVEMENT |  | 856000 | N684691400 | 2012-07-26 | 2014-01-03 | 2015-03-27 | 100% | 2015-11-03
| 2012 | Marine Corps Active | Major Military Construction | California | United States | M67604117 | MV-22 AVIATION FUEL STORAGE |  |  |  | 2013-11-21 | 2016-04-29 | 2016-10-14 | 64% | 2015-10-01
| 2012 | Marine Corps Active | Military Family Housing Improvement | Louisiana | United States | M678611201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  |  |  | 2012-01-18 | 2012-01-31 | 2012-01-31 | 100%
| 2013 | Marine Corps Active | Major Military Construction | California | United States | M67865181 | HANGAR 5 RENOVATIONS & ADDITION |  | 9166000 | Design | 2013-09-27 | 2015-09-28 | 2016-05-20 | 96% | 2016-05-20
| 2013 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557101A | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 |  |  |  | 2013-08-21 | 2015-07-12 | 2016-06-12 | 83% | 2015-12-15
| 2014 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  |  |  | 2014-05-21 | 2016-12-03 | 2016-12-21 | 41% | 2016-12-29
| 2014 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557J200 | NORTH RAMP UTILITIES II |  |  |  | 2014-10-31 | 2016-09-02 | 2016-09-02 | 1% | 2016-10-03
| 2014 | Marine Corps Active | Military Family Housing Improvement | Guam | Guam | N61755H106 | WHOLE HOUSE REVITALIZATION PHASE II AT LOCKWOOD TERRACE |  |  |  | 2015-05-14 | 2017-08-13 | 2017-08-13 | 1% | 2017-08-13
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | N69212984 | REGIMENTAL HEADQUARTERS |  |  |  | 2013-09-13 | 2015-06-26 | 2016-09-04 | 86% | 2016-09-30
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | N69212985 | BACHELOR ENLISTED QUARTERS |  |  |  | 2013-09-13 | 2015-06-26 | 2016-09-04 | 92% | 2016-09-30
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | N69212986 | MOTOR TRANSPORTATION FACILITY |  |  |  | 2013-09-13 | 2015-03-23 | 2015-04-19 | 100% | 2016-02-22
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | N69212987 | SUPPLY WAREHOUSE FACILITY |  |  |  | 2013-09-13 | 2015-03-23 | 2015-04-19 | 100% | 2016-02-22
| 2013 | Marine Corps Active | Major Military Construction | Virginia | United States | N69212989 | ARMORY |  |  |  | 2013-09-13 | 2015-03-23 | 2015-04-19 | 100% | 2016-02-22
| 2014 | Marine Corps Reserve | Major Military Construction | Missouri | United States | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  |  |  | 2014-09-05 | 2016-02-23 | 2016-02-23 | 28% | 2016-02-23
| 2012 | Marine Corps Reserve | Major Military Construction | Tennessee | United States | M68479030 | RESERVE CENTER TRAINING CENTER - MEMPHIS |  |  |  | 2013-04-19 | 2015-02-17 | 2015-02-17 | 100% | 2015-04-21
| 2013 | Marine Corps Reserve | Major Military Construction | New York | United States | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY |  |  |  | 2013-09-19 | 2014-12-04 | 2015-10-13 | 66% | 2016-04-29
| 2012 | Marine Corps Reserve | Unspecified Minor Military Construction | Louisiana | United States | N00206501 | MILITARY WORKING DOG FACILITY |  |  |  | 2013-08-29 | 2014-05-22 | 2014-06-20 | 100% | 2014-06-20
| 2015 | Marine Corps Reserve | Major Military Construction | Washington | United States | N00620234 | C-40 RESERVE MAINTENANCE HANGAR |  |  |  | 2015-08-12 | 2016-12-15 | 2016-12-15 | 16% | 2016-12-15
2016-03-31 | 2010 | Missile Defense Agency | Major Military Construction | Hawaii | United States | 627 | Aegis Ashore Missile Defense Test Complex |  |  |  | 2011-09-08 | 2011-11-18 | 2011-11-18 | 100% | 2011-11-18 | Clearing and Grubbing Only | Clearing and Grubbing Only
2016-03-31 | 2010 | Missile Defense Agency | Major Military Construction | Hawaii | United States | 627 | Aegis Ashore Missile Defense Test Complex | 1 |  |  | 2012-07-04 | 2013-09-12 | 2013-11-07 | 100% | 2013-08-29 | GMAC Construction - awaiting final 1354 | GMAC Construction - awaiting final 1354
2016-03-31 | 2013 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  |  |  | 2013-07-31 | 2015-08-30 | 2016-05-01 | 96% |  | Receiving individual facility Interim 1354s; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015. | Receiving individual facility Interim 1354s; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2016-03-31 | 2014 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #2 | 646 |  |  | 2013-07-31 | 2015-08-30 | 2016-05-01 | 96% |  | Receiving individual facility Interim 1354s; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015. | Receiving individual facility Interim 1354s; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2016-03-31 | 2012 | Missile Defense Agency | Major Military Construction | Alabama | United States | 633 | Von Braun Complex Phase IV |  |  |  | 2012-07-10 | 2014-07-10 | 2014-10-15 | 100% | 2014-06-26 | Awaiting Final 1354 | Awaiting Final 1354
2016-03-31 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  |  |  | 2014-07-07 | 2016-01-06 | 2016-01-06 | 100% | 2016-01-06 | Interim 1354 received on 2/16/2016. Awaiting Final 1354. | Interim 1354 received on 2/16/2016. Awaiting Final 1354.
2016-03-31 | 2013 | Missile Defense Agency | Major Military Construction | New York | United States | 639 | In-Flight Interceptor Data Terminal Complex |  | 1801000 | 630 | 2013-08-10 | 2014-11-28 | 2015-09-12 | 100% | 2015-02-04 | Awaiting Final 1354 | Awaiting Final 1354
2016-03-31 | 2016 | Missile Defense Agency | Major Military Construction |  | Poland | 640 | Aegis Ashore Missile Defense System Complex |  |  |  | 2016-03-14 | 2018-03-30 | 2018-03-30 | 0% |  | Site ID is pending as this will be a new Installation. | Site ID is pending as this will be a new Installation.
2016-03-31 | 2014 | Missile Defense Agency | Major Military Construction |  | Japan | 648 | AN/TPY-2 Radar Site |  |  |  | 2014-05-27 | 2015-01-09 | 2015-02-20 | 100% | 2015-02-03 | Site ID is pending as this is a new Installation. Awaiting signed final 1354 | Site ID is pending as this is a new Installation. Awaiting signed final 1354
2016-03-31 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 22900000 | 646 | 2014-05-27 | 2016-05-31 | 2016-05-31 | 93% |  | Awaiting Interim 1354 | Awaiting Interim 1354
2016-03-31 | 2016 | Missile Defense Agency | Unspecified Minor Military Construction |  | Wake Island | 661 | Flight Test Communication Facility |  |  |  | 2016-05-25 | 2016-08-31 | 2016-08-31 | 0% |  | Materials barge is due to arrive on 24 May 2016. | Materials barge is due to arrive on 24 May 2016.
2016-04-01 | 2015 | National Geospatial-Intelligence Agency | Major Military Construction | Virginia | United States | 030 | Parking Lot |  |  |  | 2016-07-15 | 2016-09-16 | 2016-10-14 | 0%
2016-04-01 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | Virginia | United States | 65416 | NGA Headquarters, SCIF, All Phases |  |  |  | 2007-09-06 | 2011-12-22 | 2016-07-01 | 99% | 2011-04-19 | ["N/A" for Diverted Funds Amount] | ["N/A" for Diverted Funds Amount]
2016-01-01 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | Virginia | United States | NGA013 | Technology Center Third Floor Fit-out |  | 1975000 | NGA021 | 2012-11-02 | 2014-01-02 | 2014-05-30 | 100% | 2014-05-30 | Technology Center Third Floor Fit-out - project period of performance extended to 31 May 2015. USACE target closeout date is 31Dec15 | Technology Center Third Floor Fit-out - project period of performance extended to 31 May 2015. USACE target closeout date is 31Dec15
2016-01-01 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA021 | Data Ctr West #1 Power & Cooling Upgrade |  |  |  | 2012-08-06 | 2013-08-06 | 2014-01-21 | 100% | 2014-01-21 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 30 September 2015 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 30 September 2015
2016-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17781 | Tordella Chilled Water Backup Storage |  |  |  | 2010-06-30 | 2011-08-20 | 2012-05-30 | 100% | 2012-05-30
2016-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17782 | R&E Chilled Water Backup Storage |  |  |  | 2011-11-07 | 2013-07-13 | 2016-02-05 | 100% | 2016-02-05 | Storage Tank is constructed and complete. The Commissioning is complete. The only thing left is a black start. The USACE is working with Walsh and the FCC to determine if it is warranted. | Storage Tank is constructed and complete. The Commissioning is complete. The only thing left is a black start. The USACE is working with Walsh and the FCC to determine if it is warranted.
2016-03-31 | 2011 | National Security Agency | Major Military Construction | Maryland | United States | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 54500000 | Mountainview, South Campus Electrical Utility Plant | 2011-10-04 | 2014-11-30 | 2015-10-31 | 99% | 2014-11-30 | Working in minor change orders and waiting for the demolition. | Working in minor change orders and waiting for the demolition.
2016-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 37500000 | Due to a Congressional rescission of funds | 2010-09-21 | 2014-04-18 | 2015-11-30 | 99% | 2015-10-12
2016-03-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18052 | Power & Cooling Infrastructure Upgrade |  |  |  | 2011-03-31 | 2013-02-01 | 2014-05-14 | 100% | 2014-05-14 | Project Phase Complete. | Project Phase Complete.
2016-03-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18053 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-01-31 | 2013-02-01 | 2014-05-31 | 100% | 2014-05-31 | Project Phase Complete. | Project Phase Complete.
2016-03-31 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18054 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-11-30 | 2013-02-01 | 2014-08-31 | 100% | 2014-08-31 | Project Phase Complete. | Project Phase Complete.
2016-03-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II |  |  |  | 2012-05-30 | 2014-01-30 | 2015-01-16 | 100% | 2014-03-03
2016-03-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II (Phase 2) | 2 |  |  | 2013-11-26 | 2014-02-28 | 2014-04-28 | 100% | 2014-09-30
2016-03-31 | 2009 | National Security Agency | Major Military Construction | Maryland | United States | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  |  |  | 2010-09-21 | 2013-01-17 | 2014-04-18 | 99% | 2013-01-17
2016-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  |  |  | 2010-09-09 | 2011-09-26 | 2012-06-29 | 99% | 2012-06-29
2016-03-31 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview |  |  |  | 2012-11-02 | 2015-05-03 | 2015-11-30 | 99% | 2015-08-30 | BOD issued on 28 July 2015. Working on final submittal, O&Ms, As-Builts. | BOD issued on 28 July 2015. Working on final submittal, O&Ms, As-Builts.
2016-03-31 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview | 2 |  |  | 2013-10-13 | 2014-02-14 | 2015-09-30 | 100% | 2014-04-30
2016-03-31 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 23994 | Whitelaw Wedge |  |  |  | 2012-07-18 | 2014-01-30 | 2014-12-23 | 100% | 2015-08-28
2016-03-31 | 2012 | National Security Agency | Major Military Construction | Maryland | United States | 24649 | High Performance Computing Center 2 |  |  |  | 2013-03-13 | 2015-09-15 | 2016-02-08 | 98% | 2016-02-08 | Interior bulding turnover completed. Commissioning activities are operating under escort conditions. Client telecommunications fit up activities are ongoing. | Interior bulding turnover completed. Commissioning activities are operating under escort conditions. Client telecommunications fit up activities are ongoing.
2016-03-31 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  |  |  | 1915-11-09 | 2014-03-07 | 2015-05-04 | 99% | 2014-11-30 | Waiting for MDE approval for the removal of the ES&C measures. | Waiting for MDE approval for the removal of the ES&C measures.
2016-03-31 | 2013 | National Security Agency | Major Military Construction | Maryland | United States | 26170 | East Campus Building 1 (ECB1) |  |  |  | 2013-10-24 | 2015-10-11 | 2016-06-11 | 69% | 2016-09-05 | Site work beginning to advance with better weather and interior finishes progressing. Extensive progress towards providing electrical service and starting commissioning exercises. Multiple user requested changes and design corrections being settled that may impact service date. | Site work beginning to advance with better weather and interior finishes progressing. Extensive progress towards providing electrical service and starting commissioning exercises. Multiple user requested changes and design corrections being settled that may impact service date.
2016-03-31 | 2015 | National Security Agency | Major Military Construction | Maryland | United States | 27532 | North Campus Buildings Feeders |  |  |  | 2016-09-01 | 2018-03-01 | 2018-07-01 | 0% |  | Contract Awarded 9/29/15. Protest received 10/19/15. Protest was withdrawn. A Correction Action Amendment was sent to the Contractors with a letter discussing the offeror's proposal weaknesses. Offerors submitted new proposal. Proposals went through review boards. Contractor was selected. The Source Selection Decision Document is currently in review with the PARC. Still waiting for approval. Award pushed out to mid-April 2016. | Contract Awarded 9/29/15. Protest received 10/19/15. Protest was withdrawn. A Correction Action Amendment was sent to the Contractors with a letter discussing the offeror's proposal weaknesses. Offerors submitted new proposal. Proposals went through review boards. Contractor was selected. The Source Selection Decision Document is currently in review with the PARC. Still waiting for approval. Award pushed out to mid-April 2016.
| 2015 | Navy Active | Unspecified Minor Military Construction | North Carolina | United States | M00146996 | UTILITY SERVICE UPGRADES, BUILDING 245 |  |  |  | 2015-09-16 | 2017-02-23 | 2016-12-10 | 1% | 2016-12-10
| 2012 | Navy Active | Major Military Construction | California | United States | M006811046 | NORTH AREA WASTE WATER CONVEYANCE |  |  |  | 2014-12-09 | 2016-12-08 | 2016-12-08 | 9% | 2016-12-08
| 2014 | Navy Active | Military Family Housing Improvement |  | Japan | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 |  |  |  | 2014-10-13 | 2016-02-02 | 2016-02-02 | 98% | 2016-02-19
| 2015 | Navy Active | Major Military Construction |  | Japan | M62613602 | SECURITY MODS DPRI MC167-T (CVW-5 E2D EA-18G) |  |  |  | 2015-05-11 | 2016-06-24 | 2016-06-24 | 38% | 2016-06-24
| 2014 | Navy Active | Military Family Housing Improvement | Louisiana | United States | M678611407 | SITE IMPROVEMENTS - GENERAL OFFICERS QUARTERS A |  |  |  | 2014-10-14 | 2014-11-30 | 2015-07-30 | 100% | 2015-10-22
| 2012 | Navy Active | Major Military Construction | Illinois | United States | N00128816 | DECENTRALIZE STEAM SYSTEM |  |  |  | 2012-06-27 | 2016-06-30 | 2016-06-30 | 83% | 2015-08-26
| 2012 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N00204791 | HVAC JOINT AVIATION SURVIVAL TRAINING |  |  |  | 2012-10-13 | 2013-08-08 | 2013-08-08 | 100% | 2013-12-19
| 2012 | Navy Active | Major Military Construction | Florida | United States | N00207153 | BAMS UAS OPERATOR TRAINING FACILITY |  | 1321000 | N42237100 | 2012-07-09 | 2013-12-17 | 2014-04-09 | 100% | 2014-03-24
| 2016 | Navy Active | Major Military Construction | Florida | United States | N00207334 | FLEET SUPPORT FACILITY ADDITION |  |  |  | 2016-04-01 | 2017-06-11 | 2017-06-11 | 1% | 2017-06-11
| 2012 | Navy Active | Major Military Construction | Florida | United States | N00207624 | P-8A TRAINING FACILITY |  | 11437000 | N42237636, N42237100 | 2012-07-09 | 2013-12-17 | 2014-04-09 | 100% | 2014-03-24
| 2015 | Navy Active | Major Military Construction | Florida | United States | N00207631 | P-8A RUNWAY THRESHOLDS AND TAXIWAYS |  |  |  | 2015-03-13 | 2016-04-19 | 2016-06-26 | 84% | 2016-07-26
| 2012 | Navy Active | Major Military Construction | Florida | United States | N00207654 | P-8A HANGAR UPGRADES |  |  |  | 2015-04-14 | 2016-05-17 | 2016-06-04 | 54% | 2016-11-01
| 2013 | Navy Active | Major Military Construction | Florida | United States | N00207655 | BAMS MISSION CONTROL COMPLEX |  |  |  | 2013-08-28 | 2014-12-27 | 2015-12-08 | 100% | 2015-12-08
| 2014 | Navy Active | Major Military Construction | Florida | United States | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION |  |  |  | 2014-10-10 | 2016-04-19 | 2016-06-26 | 75% | 2016-07-26
| 2015 | Navy Active | Major Military Construction | Florida | United States | N00207664 | MH-60 PARKING APRON |  |  |  | 2015-05-14 | 2016-04-30 | 2016-10-12 | 15% | 2016-11-08
| 2014 | Navy Active | Major Military Construction | Florida | United States | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  |  |  | 2014-08-29 | 2016-01-07 | 2016-01-07 | 70% | 2016-05-09
| 2013 | Navy Active | Major Military Construction | California | United States | N00245500 | LCS TRAINING FACILITY |  | 10760000 | N42237100 | 2013-10-14 | 2015-10-24 | 2016-05-13 | 89% | 2016-05-13
| 2015 | Navy Active | Major Military Construction | California | United States | N00245800 | STEAM DISTRIBUTION SYSTEM DECENTRALIZATION |  |  |  | 2015-10-01 | 2017-10-01 | 2017-10-01 | 2% | 2017-10-01
| 2012 | Navy Active | Major Military Construction | California | United States | N00246705 | FITNESS CENTER, NORTH ISLAND |  | 1542000 | N32446308 | 2012-08-21 | 2015-03-16 | 2015-08-26 | 100% | 2015-07-27
| 2013 | Navy Active | Major Military Construction | California | United States | N00246730 | BACHELOR QUARTERS |  |  |  | 2015-08-13 | 2017-07-29 | 2017-09-14 | 9% | 2017-07-29
| 2012 | Navy Active | Major Military Construction | California | United States | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND |  | 1956000 | Design | 2012-07-17 | 2015-03-30 | 2015-10-18 | 99% | 2016-01-20
| 2012 | Navy Active | Unspecified Minor Military Construction | California | United States | N00246896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY |  |  |  | 2013-02-21 | 2014-01-31 | 2014-10-17 | 100% | 2015-01-28
| 2013 | Navy Active | Major Military Construction | California | United States | N00246909 | H-60S SIMULATOR TRAINING FACILITY |  |  |  | 2014-03-14 | 2015-03-15 | 2015-05-14 | 100% | 2015-12-18
| 2014 | Navy Active | Major Military Construction | California | United States | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND |  |  |  | 2014-08-18 | 2016-02-10 | 2016-03-24 | 93% | 2016-03-16
| 2015 | Navy Active | Unspecified Minor Military Construction | California | United States | N00246987 | PIER 21 UPGRADES FOR MARK VI PATROL BOAT |  |  |  | 2015-09-30 | 2016-09-19 | 2016-09-19 | 96% | 2016-09-19
| 2016 | Navy Active | Major Military Construction | California | United States | N00246998 | SOCOM COASTAL CAMPUS UTILITIES |  |  |  | 2016-02-02 | 2018-04-02 | 2018-09-30 | 1% | 2017-09-29
| 2014 | Navy Active | Major Military Construction | Washington | United States | N00620239 | EA-18G FACILITY IMPROVEMENTS |  |  |  | 2014-09-08 | 2017-05-26 | 2017-05-26 | 43% | 2016-11-26
| 2013 | Navy Active | Major Military Construction | Washington | United States | N00620245 | EA-18G FLIGHT SIMULATOR FACILITY |  |  |  | 2013-06-27 | 2014-11-25 | 2015-03-11 | 97% | 2015-01-26
| 2013 | Navy Active | Unspecified Minor Military Construction | Washington | United States | N00620246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY |  |  |  | 2013-10-14 | 2014-09-30 | 2014-12-19 | 100% | 2015-01-21
| 2014 | Navy Active | Major Military Construction | Washington | United States | N00620251 | P-8A HANGAR AND TRAINING FACILITIES |  |  |  | 2014-08-04 | 2016-01-12 | 2016-03-25 | 72% | 2016-04-15
| 2014 | Navy Active | Unspecified Minor Military Construction | Washington | United States | N00620257 | HANGAR 11 MODIFICATIONS FOR SEARCH AND RESCUE |  |  |  | 2014-09-16 | 2015-02-02 | 2015-02-02 | 100% | 2015-01-30
| 2013 | Navy Active | Unspecified Minor Military Construction | Rhode Island | United States | N32411056 | VPT TEST FACILITY |  |  |  | 2013-03-28 | 2013-10-31 | 2013-12-13 | 100% | 2013-11-21
| 2014 | Navy Active | Major Military Construction | Rhode Island | United States | N32411103 | HEWITT HALL RESEARCH CENTER |  |  |  | 2014-08-14 | 2015-12-16 | 2016-01-01 | 92% | 2015-12-16
| 2015 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  |  |  | 2015-06-01 | 2016-11-23 | 2016-11-23 | 22% | 2016-12-23
| 2012 | Navy Active | Major Military Construction | Virginia | United States | N32443383 | CONTROLLED INDUSTRIAL FACILITY |  | 7621000 | N684691400 | 2012-06-14 | 2014-09-28 | 2015-06-15 | 100% | 2016-06-17
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N32443527 | SUBMARINE MAINTENANCE FACILITY |  |  |  | 2015-09-17 | 2017-04-20 | 2017-04-20 | 8% | 2017-04-20
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE |  |  |  | 2013-12-11 | 2015-12-27 | 2016-03-13 | 98% | 2016-05-11
| 2014 | Navy Active | Major Military Construction | Maine | United States | N32446266 | STRUCTURAL SHOPS CONSOLIDATION |  |  |  | 2015-08-31 | 2018-01-23 | 2018-01-23 | 9% | 2018-01-23
| 2015 | Navy Active | Unspecified Minor Military Construction |  | Djibouti | N3379A064 | POST OFFICE FACILITY |  |  |  | 2015-09-25 | 2017-01-23 | 2017-01-23 | 34% | 2017-01-09
| 2014 | Navy Active | Major Military Construction |  | Djibouti | N3379A227 | ARMORY |  |  |  | 2014-08-08 | 2015-09-28 | 2016-06-29 | 91% | 2016-06-29
| 2015 | Navy Active | Major Military Construction |  | Djibouti | N3379A330 | ENTRY CONTROL POINT |  |  |  | 2015-09-25 | 2017-01-18 | 2017-01-18 | 34% | 2017-01-18
| 2014 | Navy Active | Major Military Construction |  | Djibouti | N3379A921 | UNACCOMPANIED HOUSING |  |  |  | 2014-10-15 | 2016-05-30 | 2016-07-25 | 75% | 2016-07-25
| 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557230 | DPRI-GSE SHOPS AT NORTH RAMP |  |  |  | 2015-12-01 | 2018-06-11 | 2018-06-11 | 2% | 2018-06-19
| 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557240 | DPRI-MWSS FACILITIES AT NORTH RAMP |  |  |  | 2015-10-13 | 2018-05-02 | 2018-05-02 | 4% | 2018-05-11
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  |  |  | 2014-04-10 | 2016-04-25 | 2017-01-16 | 40% | 2016-04-25
| 2015 | Navy Active | Major Military Construction | South Carolina | United States | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  |  |  | 2015-08-05 | 2017-07-21 | 2017-07-21 | 2% | 2017-07-21
| 2014 | Navy Active | Major Military Construction | South Carolina | United States | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  |  |  | 2014-09-03 | 2018-06-20 | 2018-04-22 | 37% | 2018-04-21
| 2012 | Navy Active | Major Military Construction | Georgia | United States | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE |  |  |  | 2014-05-01 | 2017-04-16 | 2017-04-16 | 58% | 2017-04-16
| 2015 | Navy Active | Major Military Construction | Maryland | United States | N47608155 | ATLANTIC TEST RANGE FACILITY |  |  |  | 2015-10-14 | 2017-08-20 | 2017-08-20 | 7% | 2017-08-20
| 2014 | Navy Active | Unspecified Minor Military Construction | Maryland | United States | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  |  |  | 2014-10-14 | 2016-09-29 | 2017-04-29 | 87% | 2016-04-06
| 2012 | Navy Active | Major Military Construction | Maryland | United States | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 |  |  |  | 2014-07-14 | 2016-04-01 | 2016-06-23 | 43% | 2016-12-29
| 2013 | Navy Active | Unspecified Minor Military Construction | California | United States | N47609003 | EOD/TEU RANGE SUPPORT FACILITY |  |  |  | 2014-06-27 | 2015-06-26 | 2015-06-26 | 100% | 2015-06-26
| 2012 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N50092199 | MSRON FOUR BOAT STORAGE BUILDING |  |  |  | 2012-12-28 | 2013-11-08 | 2013-11-15 | 100% | 2013-11-15
| 2013 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N50092255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 |  |  |  | 2013-03-14 | 2013-08-30 | 2013-09-29 | 100% | 2013-09-12
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N50092354 | EOD CONSOLIDATED OPS AND LOGISTICS FACILITIES |  |  |  | 2015-10-12 | 2018-10-07 | 2018-10-07 | 10% | 2018-10-07
| 2012 | Navy Active | Major Military Construction | Virginia | United States | N50092499 | POWER DISTRIBUTION UPGRADES |  |  |  | 2012-10-08 | 2014-10-09 | 2015-08-01 | 100% | 2015-04-27
| 2014 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N50092662 | EOD ESU TWO EXPEDITIONARY LOGISTICS OVERHAUL WAREHOUSE |  |  |  | 2014-08-20 | 2014-11-21 | 2015-01-20 | 100% | 2015-01-20
| 2012 | Navy Active | Major Military Construction | Virginia | United States | N57095197 | DECENTRALIZE STEAM SYSTEM |  |  |  | 2012-10-04 | 2015-05-08 | 2015-07-07 | 100% | 2015-08-20
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N60191513 | A SCHOOL BARRACKS |  | 5604000 | N42237100 | 2013-11-14 | 2015-12-16 | 2016-04-06 | 83% | 2016-08-15
| 2012 | Navy Active | Major Military Construction | Virginia | United States | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS |  |  |  | 2012-10-11 | 2014-10-12 | 2015-05-07 | 100% | 2016-05-01
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N60191582 | UNDERSEA SURVEILLANCE SCIF FACILITY |  |  |  | 2012-12-03 | 2013-11-29 | 2014-06-27 | 100% | 2014-06-25
| 2014 | Navy Active | Major Military Construction | Virginia | United States | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  |  |  | 2014-09-30 | 2016-10-25 | 2017-04-04 | 14% | 2018-01-25
| 2014 | Navy Active | Major Military Construction | Florida | United States | N60201425 | LCS LOGISTICS SUPPORT FACILITY |  |  |  | 2014-06-13 | 2015-11-26 | 2016-04-27 | 100% | 2015-11-26
| 2012 | Navy Active | Major Military Construction | Florida | United States | N60201503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS |  |  |  | 2012-08-29 | 2014-02-21 | 2015-03-02 | 100% | 2016-07-15
| 2013 | Navy Active | Unspecified Minor Military Construction | Texas | United States | N60241288 | WASTEWATER SYSTEM |  |  |  | 2014-04-11 | 2015-03-27 | 2015-05-27 | 100% | 2015-07-17
| 2012 | Navy Active | Unspecified Minor Military Construction | Texas | United States | N60241294 | CONNECT TO KINGSVILLE WATER SYSTEM |  |  |  | 2012-10-08 | 2014-03-21 | 2014-08-25 | 100% | 2014-08-25
| 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495420 | AIR WING TRAINING FACILITY |  |  |  | 2015-09-30 | 2017-11-24 | 2018-11-24 | 1% | 2017-11-24
| 2015 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60508278 | PAVEMENT LANDING SYSTEMS |  |  |  | 2015-08-05 | 2016-02-16 | 2016-04-28 | 42% | 2016-04-28
| 2012 | Navy Active | Major Military Construction | Florida | United States | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE |  |  |  | 2012-06-21 | 2015-11-24 | 2015-11-24 | 96% | 2015-11-24
| 2012 | Navy Active | Unspecified Minor Military Construction | California | United States | N61014851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION |  |  |  | 2014-01-02 | 2014-10-17 | 2014-12-31 | 100% | 2014-12-31
| 2014 | Navy Active | Major Military Construction |  | Japan | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  |  |  | 2014-10-03 | 2017-01-17 | 2017-01-17 | 4% | 2017-01-17
| 2012 | Navy Active | Military Family Housing Improvement |  | Japan | N610541201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) |  |  |  | 2012-08-01 | 2014-01-13 | 2014-01-13 | 100% | 2014-01-13
| 2012 | Navy Active | Military Family Housing Improvement |  | Japan | N610541202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 |  |  |  | 2012-08-22 | 2014-10-07 | 2015-06-10 | 100% | 2015-05-19
| 2013 | Navy Active | Military Family Housing Improvement |  | Japan | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 |  |  |  | 2014-07-29 | 2016-02-21 | 2016-02-21 | 80% | 2016-02-21
| 2013 | Navy Active | Major Military Construction |  | Japan | N61056353 | BACHELOR QUARTERS |  | 1936000 | M00681970 | 2013-10-11 | 2015-01-12 | 2015-01-12 | 100% | 2015-01-12
| 2012 | Navy Active | Military Family Housing Improvement |  | Japan | N610571201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR |  |  |  | 2012-10-10 | 2013-08-26 | 2013-11-22 | 100% | 2013-11-22
| 2012 | Navy Active | Military Family Housing Improvement |  | Japan | N610571202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) |  |  |  | 2012-08-29 | 2013-12-09 | 2014-07-01 | 100% | 2014-07-01
| 2013 | Navy Active | Military Family Housing Improvement |  | Japan | N610571302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES |  |  |  | 2013-12-15 | 2015-03-31 | 2015-05-05 | 100% | 2015-05-04
| 2014 | Navy Active | Unspecified Minor Military Construction |  | Japan | N61057221 | HELO ALFS TEST ROOM, BUILDING 194 |  |  |  | 2014-08-20 | 2015-02-03 | 2015-05-19 | 100% | 2015-05-15
| 2014 | Navy Active | Military Family Housing Improvement |  | Japan | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) |  |  |  | 2014-10-14 | 2016-01-01 | 2016-01-01 | 55% | 2016-01-01
| 2012 | Navy Active | Major Military Construction | Hawaii | United States | N61064400 | NORTH LOOP ELECTRICAL REPLACEMENT |  | 2776000 | N42237100 | 2012-03-29 | 2014-01-02 | 2014-12-31 | 100% | 2013-12-24
| 2013 | Navy Active | Major Military Construction | California | United States | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB |  |  |  | 2013-10-14 | 2016-04-17 | 2016-06-16 | 98% | 2015-11-12
| 2014 | Navy Active | Unspecified Minor Military Construction | California | United States | N61065240 | STANDARD MISSILE-6 ALL UP ROUND TEST FACILITY |  |  |  | 2015-04-30 | 2016-10-21 | 2016-10-21 | 17% | 2016-10-21
| 2016 | Navy Active | Major Military Construction | Washington | United States | N61066603 | SHORE POWER TO AMMUNITION PIER |  |  |  | 2016-02-19 | 2017-03-06 | 2017-03-06 | 1% | 2017-03-06
| 2013 | Navy Active | Unspecified Minor Military Construction |  | Singapore | N61077123 | TEMPORARY LCS SUSTAINMENT FACILITY |  |  |  | 2012-12-20 | 2013-03-10 | 2013-03-10 | 100% | 2014-01-15
| 2012 | Navy Active | Major Military Construction | Maryland | United States | N61151222 | DECENTRALIZE STEAM SYSTEM |  |  |  | 2012-10-12 | 2016-07-14 | 2016-07-14 | 99% | 2016-07-14
| 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151287 | MISSILE SUPPORT FACILITY |  |  |  | 2015-09-16 | 2017-07-17 | 2018-05-08 | 6% | 2018-02-02
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N61151290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY |  |  |  | 2013-09-02 | 2015-03-12 | 2015-12-03 | 100% | 2015-12-28
| 2013 | Navy Active | Major Military Construction | Virginia | United States | N61151372 | PHYSICAL FITNESS CENTER |  |  |  | 2013-10-11 | 2015-05-02 | 2015-12-18 | 98% | 2016-01-05
| 2014 | Navy Active | Major Military Construction | Maryland | United States | N61152001 | MARFORCYBERCOM HQ-OPS BUILDING |  |  |  | 2015-04-21 | 2017-05-04 | 2017-05-04 | 9% | 2017-05-04
| 2015 | Navy Active | Major Military Construction | Maryland | United States | N61152621 | CYBER SECURITY STUDIES BUILDING |  |  |  | 2016-04-14 | 2019-03-22 | 2019-03-22 | 4% | 2019-03-21
| 2013 | Navy Active | Military Family Housing Improvement | Guam | Guam | N617551301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE |  |  |  | 2013-09-26 | 2015-09-09 | 2015-10-10 | 100% | 2015-09-29
| 2014 | Navy Active | Military Family Housing Improvement | Guam | Guam | N617551403 | WHOLE HOUSE REVITALIZATION PHASE II AT LOCKWOOD TERRACE |  |  |  | 2015-05-14 | 2017-08-13 | 2017-08-13 | 30% | 2017-09-29
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755425 | MODULAR STORAGE MAGAZINE |  |  |  | 2014-05-26 | 2016-06-11 | 2017-04-20 | 43% | 2016-06-11
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755518 | X-RAY WHARF IMPROVEMENTS |  |  |  | 2014-06-17 | 2016-10-20 | 2017-03-15 | 42% | 2016-09-20
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755566 | EMERGENT REPAIR FACILITY EXPANSION |  |  |  | 2014-04-24 | 2016-05-12 | 2016-06-29 | 65% | 2016-05-12
| 2014 | Navy Active | Unspecified Minor Military Construction | Guam | Guam | N61755630 | HARDEN ELECTRICAL DISTRIBUTION LINE (POLARIS PT ROAD) |  |  |  | 2014-10-14 | 2015-12-24 | 2015-12-24 | 100% | 2016-02-29
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY |  |  |  | 2014-04-03 | 2016-04-11 | 2016-05-09 | 87% | 2016-04-11
| 2014 | Navy Active | Major Military Construction | Guam | Guam | N61755638 | SIERRA WHARF IMPROVEMENTS |  |  |  | 2014-06-13 | 2015-03-26 | 2015-04-25 | 100% | 2015-04-24
| 2013 | Navy Active | Major Military Construction |  | Romania | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  |  |  | 2014-05-14 | 2016-03-04 | 2016-03-04 | 92% | 2016-03-04
| 2012 | Navy Active | Major Military Construction | Virginia | United States | N62688123 | BACHELOR QUARTERS, HOMEPORT ASHORE |  | 3089218 | N684691400; N32446308 | 2012-09-14 | 2014-09-13 | 2015-07-16 | 100% | 2015-07-16
| 2014 | Navy Active | Major Military Construction | Virginia | United States | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  |  |  | 2014-07-14 | 2016-01-01 | 2016-08-06 | 72% | 2016-06-09
| 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688518 | MH60 HELICOPTER TRAINING FACILITY |  |  |  | 2016-03-17 | 2017-09-29 | 2017-09-29 | 1% | 2017-09-29
| 2016 | Navy Active | Major Military Construction | Hawaii | United States | N62813036 | WELDING SCHOOL SHOP CONSOLIDATION |  |  |  | 2016-02-09 | 2018-03-26 | 2018-04-29 | 1% | 2018-03-26
| 2012 | Navy Active | Major Military Construction | Hawaii | United States | N62813041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY |  |  |  | 2012-04-19 | 2013-11-16 | 2014-11-09 | 100% | 2014-11-09
| 2015 | Navy Active | Major Military Construction | Hawaii | United States | N62813048 | SUBMARINE MANEUVERING ROOM TRAINER FACILITY |  |  |  | 2015-03-13 | 2016-10-04 | 2016-10-04 | 26% | 2016-10-04
| 2014 | Navy Active | Unspecified Minor Military Construction | Hawaii | United States | N62813058 | ROCKFALL PROTECTION AT RED HILL |  |  |  | 2014-12-08 | 2016-05-18 | 2016-05-18 | 1% | 2016-12-30
| 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813270 | DRYDOCK WATERFRONT FACILITY |  |  |  | 2014-03-03 | 2015-12-11 | 2015-12-11 | 20% | 2018-12-30
| 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  |  |  | 2014-07-14 | 2017-08-03 | 2017-12-18 | 61% | 2017-12-18
| 2012 | Navy Active | Military Family Housing Improvement |  | Spain | N628631201 | WHOLEHOUSE REVITALIZATION, LAS PALMERAS, PHASE 3 |  |  |  | 2015-03-27 | 2017-07-13 | 2017-07-13 | 12%
| 2012 | Navy Active | Unspecified Minor Military Construction |  | Spain | N62863708 | CONSTRUCT LCAC BEACH ACCESS RAMP |  |  |  | 2013-10-13 | 2014-05-28 | 2014-06-20 | 100% | 2014-06-20
| 2013 | Navy Active | Major Military Construction |  | Spain | N62863709 | GENERAL PURPOSE WAREHOUSE |  |  |  | 2013-09-06 | 2015-03-20 | 2015-03-20 | 100% | 2015-10-16
| 2013 | Navy Active | Major Military Construction |  | Spain | N62863710 | HIGH EXPLOSIVE MAGAZINE |  | 3704000 | Design | 2013-09-06 | 2015-03-20 | 2015-03-20 | 100% | 2015-10-16
| 2015 | Navy Active | Major Military Construction |  | Spain | N62863712 | SHIP BERTHING POWER UPGRADES |  |  |  | 2015-12-04 | 2018-05-23 | 2018-05-23 | 9% | 2018-05-23
| 2014 | Navy Active | Unspecified Minor Military Construction |  | Spain | N62863733 | PROVIDE ELECTROMAGNETIC CALIBRATION COMPLEX |  |  |  | 2014-10-03 | 2014-11-22 | 2014-11-22 | 100% | 2015-08-21
| 2015 | Navy Active | Major Military Construction |  | Bahrain | N63005955 | P-8A HANGAR |  |  |  | 2015-09-30 | 2018-11-09 | 2018-11-09 | 5% | 2018-11-09
| 2015 | Navy Active | Major Military Construction | California | United States | N63042327 | F-35C OPERATIONAL TRAINING FACILITY |  |  |  | 2015-07-10 | 2016-10-17 | 2016-11-02 | 28% | 2016-10-17
| 2015 | Navy Active | Major Military Construction | California | United States | N63042328 | F-35C FACILITY ADDITION AND MODIFICATION |  |  |  | 2015-06-25 | 2016-07-22 | 2016-08-29 | 31% | 2016-07-22
| 2012 | Navy Active | Unspecified Minor Military Construction | California | United States | N63042363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 |  |  |  | 2012-09-12 | 2013-08-29 | 2013-08-29 | 100% | 2013-08-29
| 2012 | Navy Active | Unspecified Minor Military Construction | California | United States | N63042364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT |  |  |  | 2012-10-12 | 2013-09-26 | 2014-03-05 | 100% | 2014-03-05
| 2014 | Navy Active | Unspecified Minor Military Construction | California | United States | N63042376 | VFA-94 HANGAR ALTERATIONS |  |  |  | 2014-10-11 | 2016-09-27 | 2016-06-17 | 62% | 2016-09-27
| 2015 | Navy Active | Unspecified Minor Military Construction | California | United States | N63042377 | CARRIER AIR WING FOURTEEN (CVW-14) FACILITY |  |  |  | 2016-03-11 | 2016-05-26 | 2020-05-21 | 1% | 2017-04-30
| 2016 | Navy Active | Major Military Construction | California | United States | N63042379 | F-35C TRAINING FACILITIES |  |  |  | 2016-03-31 | 2017-03-31 | 2017-03-31 | 1% | 2017-03-31
| 2013 | Navy Active | Major Military Construction | Mississippi | United States | N63043317 | DINING FACILITY |  |  |  | 2013-12-31 | 2015-10-09 | 2015-11-30 | 76% | 2016-06-03
| 2012 | Navy Active | Unspecified Minor Military Construction | California | United States | N63406563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 |  |  |  | 2012-10-12 | 2013-09-27 | 2014-07-01 | 100% | 2014-06-23
| 2013 | Navy Active | Major Military Construction |  | Greece | N66691907 | AIRCRAFT PARKING APRON EXPANSION |  | 417000 | FY Prior Year Rescission | 2014-07-25 | 2016-05-15 | 2016-05-15 | 70% | 2016-08-04
| 2012 | Navy Active | Major Military Construction | Washington | United States | N68436419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 |  | 1000000 | N32446308 | 2012-06-08 | 2013-12-24 | 2014-11-10 | 100% | 2013-06-27
| 2014 | Navy Active | Major Military Construction | Washington | United States | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  |  |  | 2014-08-01 | 2016-02-16 | 2016-02-16 | 56% | 2016-10-18
| 2015 | Navy Active | Major Military Construction | Washington | United States | N68436422 | INTEGRATED WATER TREATMENT SYSTEM DD 1, 2 & 5 |  |  |  | 2015-05-18 | 2016-10-25 | 2016-10-25 | 27% | 2017-02-24
| 2012 | Navy Active | Unspecified Minor Military Construction | Washington | United States | N68436839 | RENOVATE LOWER BASE FIRE STATION |  |  |  | 2012-09-14 | 2013-08-31 | 2013-11-22 | 100% | 2013-08-31
| 2014 | Navy Active | Unspecified Minor Military Construction | Washington | United States | N68436855 | SUBMARINE BRIDGE TEAM SIMULATOR |  |  |  | 2015-07-14 | 2016-05-15 | 2016-05-15 | 16% | 2016-05-15
| 2013 | Navy Active | Unspecified Minor Military Construction | Washington | United States | N68436857 | FLOATING LABORATORY, MOORING DOLPHINS |  |  |  | 2013-05-31 | 2014-05-19 | 2014-05-19 | 100% | 2014-06-27
| 2012 | Navy Active | Major Military Construction | Washington | United States | N68436913 | EHW SECURITY FORCE FACILITY |  | 7933000 | N684691400 | 2012-02-14 | 2013-08-08 | 2014-02-16 | 100% | 2014-06-11
| 2012 | Navy Active | Major Military Construction | Washington | United States | N68436985 | WRA VEHICLE BARRIERS |  | 7587000 | N42237636 | 2012-02-24 | 2013-12-10 | 2014-06-30 | 100% | 2013-12-11
| 2012 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 |  |  |  | 2012-05-23 | 2016-01-09 | 2016-05-04 | 93% | 2016-07-31
| 2013 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | N68436990A |  |  | 2012-11-15 | 2016-01-09 | 2016-05-04 | 95% | 2016-07-31
| 2014 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990B |  |  | 2014-01-14 | 2016-01-09 | 2016-05-04 | 67% | 2016-07-31
| 2015 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 - INC 4 | N68436990C |  |  | 2015-01-22 | 2016-01-09 | 2016-05-04 | 56% | 2016-07-31
| 2012 | Navy Active | Major Military Construction | Maryland | United States | N68469110 | REPLACE CONDEMNED COATINGS LABORATORY |  |  |  | 2012-09-11 | 2013-08-28 | 2014-05-30 | 100% | 2014-04-24
| 2014 | Navy Active | Major Military Construction | District Of Columbia | United States | N684691400 | NAVSEA HQ RESTORATION |  |  |  | 2014-02-14 | 2015-01-31 | 2015-01-31 | 100% | 2015-01-30
| 2012 | Navy Active | Major Military Construction |  | Diego Garcia | N68539184 | POTABLE WATER PLANT MODERNIZATION |  |  |  | 2013-01-04 | 2015-07-30 | 2015-08-26 | 100% | 2016-04-30
| 2014 | Navy Active | Major Military Construction | Virginia | United States | N69212461 | SMALL ARMS RANGES |  |  |  | 2015-10-13 | 2017-02-25 | 2017-04-28 | 13% | 2017-04-28
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N69212991 | BACHELOR ENLISTED QUARTERS |  |  |  | 2016-03-22 | 2018-03-23 | 2018-03-23 | 1% | 2018-03-23
| 2015 | Navy Active | Major Military Construction | Virginia | United States | N69212992 | FAST COMPANY TRAINING FACILITY |  |  |  | 2015-10-13 | 2016-09-28 | 2016-09-28 | 1% | 2016-09-28
| 2013 | Navy Active | Major Military Construction | New Jersey | United States | N69213237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION |  |  |  | 2013-09-17 | 2014-11-27 | 2015-06-26 | 100% | 2015-02-12
| 2014 | Navy Active | Major Military Construction | California | United States | N69232281 | AIRCRAFT ENGINE TEST PADS |  |  |  | 2014-06-26 | 2015-07-17 | 2015-07-17 | 100% | 2015-09-18
| 2012 | Navy Active | Major Military Construction | California | United States | N69232559 | E-2D AIRCREW TRAINING FACILITY |  |  |  | 2012-07-13 | 2014-06-25 | 2015-03-20 | 100% | 2015-03-20
| 2016 | Navy Active | Major Military Construction | California | United States | N69232565 | E-2C/D HANGAR ADDITIONS AND RENOVATIONS |  |  |  | 2016-04-13 | 2017-04-14 | 2017-04-14 | 1% | 2017-04-30
| 2014 | Navy Active | Major Military Construction | California | United States | N69232593 | BAMS CONSOLIDATED MAINTENANCE HANGAR |  |  |  | 2015-01-30 | 2016-09-17 | 2016-09-17 | 27% | 2017-01-17
| 2014 | Navy Active | Major Military Construction | California | United States | N69232599 | UNACCOMPANIED HOUSING CONVERSION (PORT HUENEME) |  |  |  | 2014-12-08 | 2016-03-12 | 2016-03-12 | 1% | 2016-03-12
| 2013 | Navy Active | Major Military Construction | California | United States | N69232900 | BAMS MAINTENANCE TRAINING FACILITY |  |  |  | 2013-09-10 | 2014-11-21 | 2015-10-31 | 93% | 2015-10-29
| 2014 | Navy Active | Major Military Construction | Texas | United States | N83447136 | TACAMO E-6B HANGAR |  |  |  | 2014-10-14 | 2016-02-12 | 2016-03-27 | 62% | 2016-08-05
| 2014 | Navy Reserve | Major Military Construction | South Carolina | United States | M68479031 | RESERVE BOAT MAINTENANCE AND STORAGE FACILITY |  |  |  | 2015-04-07 | 2016-03-23 | 2016-03-23 | 90% | 2016-04-07
| 2015 | Navy Reserve | Unspecified Minor Military Construction | Connecticut | United States | N00129664 | CORIVRON 8 RESERVE HVU DET SUPPORT FACILITIES |  |  |  | 2015-09-08 | 2016-09-08 | 2016-09-08 | 11% | 2016-09-08
| 2013 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206470 | TRANSIENT QUARTERS |  |  |  | 2015-09-15 | 2017-03-09 | 2017-03-09 | 11% | 2017-03-09
| 2015 | Navy Reserve | Unspecified Minor Military Construction | Florida | United States | N00207278 | CRS 10 BOAT MAINTENANCE FACILITY |  |  |  | 2015-10-14 | 2016-10-14 | 2016-11-13 | 1% | 2016-10-14
| 2012 | Navy Reserve | Major Military Construction | Pennsylvania | United States | N32414860 | ARMED FORCES RESERVE CENTER, PITTSBURGH |  | 500000 | Design | 2012-08-14 | 2014-02-06 | 2014-05-31 | 100% | 2014-05-31
| 2012 | Navy Reserve | Unspecified Minor Military Construction | Virginia | United States | N69212543 | NAVELSG RESERVE FORCES MARSHALLING YARDS |  |  |  | 2013-01-30 | 2014-01-21 | 2014-01-21 | 100% | 2013-10-23
| 2013 | Navy Reserve | Major Military Construction | Texas | United States | N83447047 | COMMERCIAL VEHICLE INSPECTION SITE |  |  |  | 2013-09-26 | 2014-11-06 | 2015-05-03 | 100% | 2015-07-15
2016-02-28 | 2015 | Special Operations Command | Major Military Construction | Kentucky | United States | 36977 | System Integration Maintenance Office Facility |  |  |  | 2015-09-10 | 2017-03-03 | 2017-06-01 | 8%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Arizona | United States | 53542 | Parachute Training Facility |  |  |  | 2014-11-09 | 2016-02-07 | 2016-02-20 | 93%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 61064 | SOF Upgrade Training Facility |  |  |  | 2014-11-17 | 2016-05-10 | 2016-10-20 | 43%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 65052 | Medical Support Addition |  |  |  | 2013-10-16 | 2015-08-25 | 2015-02-16 | 98% | 2015-01-23
2016-04-12 | 2011 | Special Operations Command | Major Military Construction | Georgia | United States | 65395 | Company Support Facility |  |  |  | 2011-12-27 | 2013-06-19 | 2014-07-31 | 99% | 2014-05-30
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Kentucky | United States | 66597 | Landgraf Hangar Extension |  |  |  | 2014-04-29 | 2015-10-21 | 2016-03-07 | 83%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | Kentucky | United States | 66598 | Rotary Wing Hangar |  |  |  | 2012-04-16 | 2014-02-15 | 2015-02-15 | 99% | 2015-05-05
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 68526 | SOF Engineer Training Facility |  |  |  | 2015-05-27 | 2016-11-17 | 2017-01-16 | 9%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Washington | United States | 69257 | SOF Military Working Dog Kennel |  |  |  | 2015-05-04 | 2016-09-15 | 2016-09-15 | 24%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69287a | Battalion Operations Complex |  |  |  | 2013-10-09 | 2015-05-13 | 2015-10-30 | 98%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69287b | Battalion Operations Complex |  |  |  | 2014-11-20 | 2016-12-02 | 2016-12-07 | 58%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69382 | Civil Affairs Battalion Complex |  |  |  | 2013-10-16 | 2015-08-14 | 2015-09-21 | 99% | 2015-11-04
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Washington | United States | 69445 | SOF Battalion Operations Facility |  |  |  | 2015-06-30 | 2017-05-25 | 2017-07-24 | 8%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | Colorado | United States | 69446 | Group Support Battalion |  |  |  | 2014-08-27 | 2016-02-08 | 2016-05-24 | 68%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Kentucky | United States | 69447 | Group Support Battalion Detachment |  |  |  | 2014-04-14 | 2016-02-13 | 2016-02-15 | 99%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69458 | Battalion Operations Complex |  | 1738000 | 69445 | 2012-12-10 | 2014-06-03 | 2015-08-13 | 95%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | 69493 | Sustainment Bde Headquarters |  |  |  | 2014-06-18 | 2016-07-18 | 2016-10-14 | 62%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 69758 | Brigade Headquarters |  |  |  | 2012-11-14 | 2014-05-08 | 2014-10-11 | 87%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 71224 | Group Headquarters |  | 2896000 | 68526 | 2012-11-07 | 2014-05-01 | 2015-02-06 | 99% | 2015-04-27
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | North Carolina | United States | 76364 | Battalion Operations Facility |  | 5000000 | 69445 | 2012-12-04 | 2014-08-26 | 2015-04-07 | 99%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | Kentucky | United States | 76365 | Group Special Troops Battalion |  |  |  | 2015-12-02 | 2017-10-02 | 2017-10-02 | 5%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76366 | Company Operations Facility (GSTB) |  |  |  | 2012-09-12 | 2015-09-12 | 2016-03-02 | 99% | 2016-03-02
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Colorado | United States | 76367 | SOF Battalion Operations Complex |  |  |  | 2014-09-04 | 2016-07-20 | 2016-09-23 | 33%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | Florida | United States | 76371 | Company Operations Facility (GSB) |  |  |  | 2012-09-12 | 2015-09-12 | 2016-03-02 | 99% | 2016-03-02
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76375 | Civil Affairs Battalion Annexes |  |  |  | 2014-12-01 | 2016-07-23 | 2016-08-04 | 19%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76376 | Language and Cultural Center |  |  |  | 2015-01-09 | 2017-06-27 | 2017-07-08 | 23%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction |  | Japan | 78024 | Facility Augmentation |  |  |  | 2015-07-01 | 2017-12-12 | 2017-12-12 | 6%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 79438 | Combat Medic Skills Sustainment Course Bldg |  |  |  | 2014-10-27 | 2016-04-19 | 2016-10-07 | 59%
2016-02-28 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79456 | SOF Tactical Equipment Maintenance Facility (TEMF) |  |  |  | 2015-05-21 | 2017-09-27 | 2016-11-15 | 7%
2016-02-28 | 2011 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 7132000 | 66362 | 2012-09-06 | 2013-07-17 | 2014-06-03 | 99% | 2014-06-03
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | FTEV083002 | Add/Alter Operations Facility |  |  |  | 2014-09-02 | 2016-05-24 | 2016-10-20 | 22%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | FTFA113004 | SOF AvFID Ops and MX Facilities |  |  |  | 2013-11-05 | 2016-12-25 | 2016-12-25 | 78%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Florida | United States | NVZR083702 | Joint Special Operations University Facility |  |  |  | 2013-11-04 | 2015-06-28 | 2016-05-11 | 69%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | California | United States | P-1049 | Range 130 Support Projects |  |  |  | 2013-06-03 | 2014-11-13 | 2016-03-06 | 93%
2016-02-28 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-1119 | SOF Comm / Electronics Maintenance Facility |  |  |  | 2015-10-29 | 2017-04-06 | 2017-04-06 | 0%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1218 | Marine Battalion Company/Team Facilities |  |  |  | 2014-02-20 | 2016-03-01 | 2016-05-31 | 62%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1391 | SOF Sustainment Training Complex |  |  |  | 2014-08-29 | 2016-09-02 | 2016-09-02 | 36%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1393 | Survival Evasion Resistance Escape Trng Facility |  |  |  | 2014-02-20 | 2016-01-18 | 2016-05-31 | 62%
2016-02-28 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1396 | Intel/Ops Expansion |  |  |  | 2015-12-07 | 2017-03-09 | 2017-03-09 | 5%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-164 | Logistics Support Facility |  |  |  | 2012-12-09 | 2014-07-24 | 2015-06-16 | 97%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | Virginia | United States | P-165 | CS/CSS Support Facility |  |  |  | 2014-10-06 | 2015-09-09 | 2015-11-26 | 98%
2016-02-28 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P-334 | LOGSU Two Ops Facility |  |  |  | 2016-02-29 | 2018-07-01 | 2018-07-01 | 0%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-473 | SEAL Team Operations Facility |  |  |  | 2014-08-13 | 2015-12-27 | 2015-12-27 | 68%
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-769 | Building Renovation |  |  |  | 2013-01-02 | 2014-06-27 | 2015-02-20 | 99% | 2015-02-20
2016-02-28 | 2012 | Special Operations Command | Major Military Construction | Virginia | United States | P-826 | Military Working Dog Facility |  |  |  | 2012-12-09 | 2014-07-24 | 2015-06-16 | 97%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-876 | Indoor Dynamic Shooting Facility |  |  |  | 2015-01-29 | 2016-10-01 | 2016-10-07 | 9%
2016-02-28 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-888 | Close Quarters Combat Range, Phase II |  |  |  | 2015-01-30 | 2016-09-30 | 2016-09-29 | 7% |  | DB Design not yet accepted: Start date listed as 1-mo after award. | DB Design not yet accepted: Start date listed as 1-mo after award.
2016-03-17 | 2010 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80001 | Pentagon Electrical Upgrade |  |  |  | 2013-11-07 | 2015-02-05 | 2016-12-31 | 48% | 2016-12-31
2016-03-17 | 2011 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80002 | Power Plant Modernization Phase 3 (WPP) |  | 4331051 | Budget Sequester: $4,001,00 Reprogramming: $330,051 to project 80003 | 2013-04-22 | 2016-05-11 | 2017-01-18 | 56% | 2017-01-18
2016-03-17 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80003 | Metro Entrance Facility/Visitor Screening Facility |  |  |  | 2013-11-01 | 2015-05-03 | 2016-05-30 | 97% | 2016-04-01
2016-03-17 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80004 | Secure Access Lane (SAL) |  |  |  | 2013-11-01 | 2015-05-01 | 2016-07-30 | 17% | 2016-07-30
2016-03-17 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80005 | Pentagon Heliport Control Tower/Fire Station |  | 798000 | Budget Sequester
2016-03-17 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80006 | Pentagon Memorial Pedestrian Plaza |  | 2285000 | $176,000 Budget Sequester $409,000 to 80003 $1.7M to 80004 | [5 empty] | Project Cancelled | Project Cancelled
2016-03-17 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80007 | PFPA Support Operations Center
2016-03-17 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80008 | Boundary Channel Access Control Point
2016-03-17 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80009 | Raven Rock Admin Facility Upgrade |  | 500000 | Reprogramming: $500,000 to project 80002
2016-03-17 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80010 | Raven Rock Exterior Cooling Towers |  | 3929000 | Reprogramming: to project 80001 | [5 empty] | Project Cancelled | Project Cancelled
2016-03-17 | 2015 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80011 | Redundant Chilled Water Loop

## CONTRACTS
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Prime Contract Number | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date | Contract Remarks
2016-04-15 | 2014 | Air Force Active | ACC123183 |  | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143462 | 7200020 | 2016-02-20 | 2016-04-11
2016-04-15 | 2014 | Air Force Active | AETC176870 |  | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265367 | 3310071 | 2015-06-09 | 2015-06-30
2016-04-15 | 2012 | Air Force Active | AGGN123002P |  | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619171 | 1662571 | 2014-12-19 | 2014-12-19
2016-04-15 | 2014 | Air Force Active | AGGN143001 |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164308 | 1178891 | 2015-12-24 | 2016-01-01
2016-04-15 | 2014 | Air Force Active | AGGN143002 |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111892 | 7219701 | 2015-12-24 | 2016-01-12
2016-04-15 | 2014 | Air Force Active | AGGN143003 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645200 | 5645200 | 2015-10-12 | 2015-10-12
2016-04-15 | 2014 | Air Force Active | AGGN143004 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000000 | 11112754 | 2015-10-12 | 2015-11-14
2016-04-15 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 89918305 | 89918305 | 2017-04-16 | 2017-04-16
2016-04-15 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 96616619 | 96775605 | 2017-03-08 | 2017-03-08
2016-04-15 | 2014 | Air Force Active | AJJY143760 |  | 2014-07-30 | 2015-01-22 | Environet Inc. | N4019210D00040012 | 101676 | 101676 | 2015-02-08 | 2015-02-08
2016-04-15 | 2014 | Air Force Active | AJJY143760 |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907700 | 17907700 | 2016-04-12 | 2016-04-12
2016-04-15 | 2014 | Air Force Active | AJJY153011 |  | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177269 | 6168044 | 2016-08-17 | 2016-08-17
2016-04-15 | 2010 | Air Force Active | AJXF063009 |  | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464830 | 10060192 | 2013-05-13 | 2013-05-25
2016-04-15 | 2014 | Air Force Active | AJXF103010 |  | 2014-08-15 | 2014-12-30 | The Haskell Company | N4008010D04910002 | 21754670 | 21754670 | 2017-04-05 | 2017-04-05
2016-04-15 | 2013 | Air Force Active | AJXF106000 |  | 2014-08-07 | 2015-03-04 | Heard Contracting | W912DR15C0010 | 2132837 | 2151817 | 2016-04-08 | 2016-04-08
2016-04-15 | 2011 | Air Force Active | ALUA073006B |  | 2014-09-02 | 2015-01-23 | Federal Contracting, Inc. | W912ER15C0003 | 4899425 | 4899425 | 2016-01-29 | 2016-10-16
2016-04-15 | 2011 | Air Force Active | ALUA073006B |  | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177236 | 34717491 | 2014-05-15 | 2017-03-30
2016-04-15 | 2011 | Air Force Active | ALUA073006B |  | 2015-08-17 | 2015-09-17 | American International Contractors, Inc. | W912ER15C0008 | 9848000 | 9848000 |  | 2016-10-16
2016-04-15 | 2008 | Air Force Active | ALUA073008A |  | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244838 | 31385349 | 2012-08-22 | 2015-10-15
2016-04-15 | 2010 | Air Force Active | ALUA107000 |  | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272835 | 48848300 | 2014-04-06 | 2015-05-04
2016-04-15 | 2011 | Air Force Active | ALUA110032 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730623 | 1730623 | 2014-12-06 | 2014-12-06
2016-04-15 | 2011 | Air Force Active | ALUA113001 |  | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912567 | 10464450 | 2014-04-02 | 2014-06-11
2016-04-15 | 2011 | Air Force Active | ALUA113002 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557438 | 1557438 | 2014-12-06 | 2014-12-06
2016-04-15 | 2011 | Air Force Active | ALUA113005 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572399 | 1572399 | 2014-12-06 | 2014-12-06
2016-04-15 | 2011 | Air Force Active | ALUA113006 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573056 | 1573056 | 2014-12-06 | 2014-12-06
2016-04-15 | 2011 | Air Force Active | ALUA113009 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615612 | 615612 | 2014-12-06 | 2014-12-06
2016-04-15 | 2011 | Air Force Active | ALUA113010 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216400 | 1216400 | 2014-12-06 | 2014-12-06
2016-04-15 | 2011 | Air Force Active | ALUA113012 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615533 | 1615533 | 2014-12-06 | 2014-12-06
2016-04-15 | 2012 | Air Force Active | ALUA113026 |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511518 | 1511518 | 2014-12-06 | 2014-12-06
2016-04-15 | 2012 | Air Force Active | ALUA113027 |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265194 | 1277795 | 2014-11-06 | 2014-12-06
2016-04-15 | 2012 | Air Force Active | ALUA113032 |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403744 | 1423578 | 2015-02-19 | 2015-02-24
2016-04-15 | 2012 | Air Force Active | ALUA113034 |  | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214606 | 1219631 | 2015-02-19 | 2015-02-19
2016-04-15 | 2011 | Air Force Active | ASHE083011 |  | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N3319107D02110002 | 7174169 | 8608121 | 2013-09-05 | 2015-03-15
2016-04-15 | 2013 | Air Force Active | ASHE103001 |  | 2014-03-06 | 2015-02-26 | Coop Muratori & Cementisti CMC Di Ravenn | N6247015C5005 | 1780234 | 1780234 | 2016-12-02 | 2016-12-02
2016-04-15 | 2012 | Air Force Active | AWUB105002 |  | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998000 | 18717502 | 2013-11-24 | 2014-03-16
2016-04-15 | 2013 | Air Force Active | BAEY133001 |  | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947269 | 16020495 | 2016-03-30 | 2016-05-29
2016-04-15 | 2014 | Air Force Active | BAEY143000 |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699643 | 53699643 | 2016-11-04 | 2016-11-04
2016-04-15 | 2015 | Air Force Active | CADJ140004 |  | 2015-06-30 | 2015-09-29 | AICI, Burlingame, CA | N3319113D0839 | 6960000 | 6960000 | 2017-02-02 | 2017-02-02
2016-04-15 | 2014 | Air Force Active | CZQZ013004 |  | 2015-01-29 | 2015-05-18 | Speegle Construction Inc. | W912PP15C0006 | 5102200 | 5109277 | 2016-06-10 | 2016-06-10
2016-04-15 | 2014 | Air Force Active | CZQZ073023A |  | 2014-08-04 | 2014-12-05 | Speegle Construction Inc. | W912PP15C0001 | 7001000 | 7034098 | 2016-11-19 | 2016-11-24
2016-04-15 | 2014 | Air Force Active | CZQZ073050 |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19716709 | 19781648 | 2016-08-21 | 2016-08-21
2016-04-15 | 2010 | Air Force Active | DHAF100031 |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671642 | 1986140 | 2012-02-28 | 2015-11-11
2016-04-15 | 2010 | Air Force Active | DHAF100120 |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136701 | 1184030 | 2012-02-28 | 2015-11-11
2016-04-15 | 2011 | Air Force Active | DHAF120037 |  | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhabi UAE) | W912BU13C0060 | 1514583 | 1625700 | 2015-01-20 | 2016-02-04
2016-04-15 | 2011 | Air Force Active | DHAF120057 |  | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120380 | 1192114 | 2014-11-24 | 2015-09-30
2016-04-15 | 2011 | Air Force Active | DHAF124001 |  | 2013-07-18 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1044893 | 1073954 | 2015-10-02 | 2015-12-21
2016-04-15 | 2011 | Air Force Active | FBNV063501 |  | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282136 | 23526207 | 2013-08-27 | 2014-09-24
2016-04-15 | 2011 | Air Force Active | FBNV113002 |  | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223000 | 7534524 | 2013-05-02 | 2013-09-13
2016-04-15 | 2012 | Air Force Active | FBNV133500 |  | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D01100001 | 1795000 | 1817300 | 2015-06-08 | 2015-10-17
2016-04-15 | 2010 | Air Force Active | FJXT033003 |  | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248940 | 11773483 | 2013-10-12 | 2014-10-21
2016-04-15 | 2014 | Air Force Active | FTFA073007 |  | 2014-07-24 | 2014-12-30 | Southeast Cherokee Constructio | W9127810D00780008 | 1457737 | 1457737 | 2016-02-05 | 2016-02-05
2016-04-15 | 2013 | Air Force Active | FTFA123000 |  | 2014-07-28 | 2014-10-30 | Barlovento LLC | W9127810D00720015 | 1756830 | 1756830 | 2015-12-05 | 2015-12-05
2016-04-15 | 2012 | Air Force Active | FTQW083005 |  | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061944 | 33834183 | 2016-08-15 | 2016-08-15
2016-04-15 | 2010 | Air Force Active | FTQW083007 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981132 | 28919519 | 2015-01-27 | 2016-12-22
2016-04-15 | 2011 | Air Force Active | FTQW083008 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981132 | 30891695 | 2015-01-27 | 2016-12-22
2016-04-15 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874106 | 2191910 | 2012-11-17 | 2012-11-17
2016-04-15 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805300 | 56511659 | 2014-06-19 | 2015-03-17
2016-04-15 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230292 | 3230292 | 2013-10-04 | 2013-10-04
2016-04-15 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978807 | 4978807 | 2013-08-28 | 2013-08-28
2016-04-15 | 2012 | Air Force Active | FXSB061561 |  | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799228 | 1799228 | 2012-12-16 | 2012-12-16
2016-04-15 | 2013 | Air Force Active | GJKZ130025 |  | 2014-08-01 | 2014-12-31 | Ahtna Engineering | FA462013DB0040003 | 1698195 | 1742635 | 2015-12-17 | 2015-12-17
2016-04-15 | 2012 | Air Force Active | HACC123204 |  | 2015-01-13 | 2015-08-21 | JV SKE Italy 2012 | N33191-15-C-0802 | 9591161 | 9591161 | 2017-02-21 | 2017-02-21
2016-04-15 | 2014 | Air Force Active | KNMD142222 |  | 2015-10-05 | 2015-11-05 | Jacobsen Construction Company, Inc | N6247816C1506 | 2699000 | 2699000 | 2016-10-15 | 2016-10-15
2016-04-15 | 2014 | Air Force Active | KRSM003009 |  | 2014-05-06 | 2015-03-27 | Northern Construction LLC | W9123815C0001 | 12777054 | 12960228 | 2017-04-27 | 2017-07-28
2016-04-15 | 2013 | Air Force Active | KRSM103012 |  | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781000 | 9728790 | 2015-07-21 | 2016-06-19
2016-04-15 | 2013 | Air Force Active | KRSM103012 |  | 2015-07-27 | 2015-08-27 | BRINKERHOFF EXCAVATING AND CONSTRUCTION, | FA820112D0013 | 536389 | 536389 |  | 2016-01-04
2016-04-15 | 2012 | Air Force Active | KWRD013003 |  | 2012-05-18 | 2012-08-17 | Turner Atlantic Construction | W912PP12C0026 | 9843654 | 10234330 | 2014-05-17 | 2014-11-24
2016-04-15 | 2008 | Air Force Active | LJYC084001 |  | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970022 | 42315654 | 2012-10-19 | 2016-09-30
2016-04-15 | 2014 | Air Force Active | LJYC106001 |  | 2015-06-02 | 2015-09-30 | KIRNAK Ins.San. Ve Tic. Ltd. | FA5685-15-C-0009 | 1530537 | 1530537 | 2016-09-28 | 2016-09-28
2016-04-15 | 2014 | Air Force Active | LKTC073101 |  | 2014-07-18 | 2014-09-02 | USACE | W81EYN42417577 | 11450000 | 11450000 | 2014-12-01 | 2014-12-01
2016-04-15 | 2014 | Air Force Active | LKTC073101 |  | 2015-03-31 | 2015-08-14 | Penick-Nordic JV | W912PL10D00720003 | 3100312 | 3100312 | 2016-05-28 | 2016-05-28
2016-04-15 | 2013 | Air Force Active | LKTC133101 |  | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643420 | 10801343 | 2015-08-19 | 2015-10-18
2016-04-15 | 2011 | Air Force Active | LXEZ114127 |  | 2012-01-03 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan)*Arch TestDigs* | FA527012P0058 | 50185 | 50185 | 2012-09-03 | 2012-09-03
2016-04-15 | 2011 | Air Force Active | LXEZ114127 |  | 2012-02-02 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT" | FA527012P0080 | 72005 | 72005 | 2012-09-24 | 2012-09-24
2016-04-15 | 2011 | Air Force Active | LXEZ114127 |  | 2013-12-13 | 2014-06-11 | OSC Solutions, Inc. (West Palm Beach, FL) **Appliances** | FA527014P0055 | 401356 | 401356 | 2014-09-09 | 2014-09-09
2016-04-15 | 2011 | Air Force Active | LXEZ114127 |  | 2011-09-21 | 2012-03-19 | OTIE Milwauke, WI; *Title 2 Contract support* | FA890308D87820014 | 1896559 | 1896559 | 2015-08-30 | 2015-08-30
2016-04-15 | 2011 | Air Force Active | LXEZ114127 |  | 2012-03-16 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) ** Appliances** | FA527012FA045 | 319431 | 319431 | 2012-12-11 | 2012-12-11
2016-04-15 | 2011 | Air Force Active | LXEZ114127 |  | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621760 | 67931188 | 2015-11-08 | 2015-12-03
2016-04-15 | 2012 | Air Force Active | LXEZ124285 |  | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706668 | 17706668 | 2016-05-10 | 2016-05-10
2016-04-15 | 2013 | Air Force Active | LXEZ134286 |  | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698072 | 15051564 | 2015-11-27 | 2016-02-08
2016-04-15 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288680 | 6353977 | 2015-08-27 | 2015-11-25
2016-04-15 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202135 | 4234497 | 2015-12-15 | 2015-12-15
2016-04-15 | 2014 | Air Force Active | LXEZ144287 |  | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473449 | 2514800 | 2014-07-23 | 2014-09-06
2016-04-15 | 2014 | Air Force Active | MHMV103105B |  | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285500 | 21563852 | 2016-11-01 | 2016-11-28
2016-04-15 | 2013 | Air Force Active | MPLS083008 |  | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170185 | 17241355 | 2015-06-12 | 2015-07-07
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2010-12-06 | 2014-11-10 | AE Merrick & Company-Tittle 2 Svs $59,036x3 | W9126G08D00060053 | 177108 | 177108 | 2015-09-05 | 2015-09-05
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-09-06 | 2012-10-19 | SB FPI, LLC/JSR Inc-Refencing | W9126G11C0009 | 175358 | 175358 | 2013-06-01 | 2013-06-01
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2010-12-06 | 2011-09-20 | LB SutherfielfPontikes, LLC-Main Facility Construction | W9126G11C0024 | 45885000 | 46365642 | 2013-10-31 | 2014-02-25
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2011-09-02 | 2011-11-08 | LB Koonz Brown & Root (DCF2 Ktr)-Free Zone Fence | W9126G11C0027 | 95464 | 95464 | 2011-12-08 | 2011-12-08
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-02-15 | 2014-06-25 | SVS-Am Eagle Protective Svs Corp-Gate Monitor, OY2 | W9126G12C0017P0002 | 100466 | 100466 | 2015-01-31 | 2015-01-31
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2013-03-18 | 2013-06-03 | SB FPI, LLC/JSR Inc-DCF2s Gary Rd portion 2/3 | W9126G13C0098 | 91850 | 91850 | 2013-11-06 | 2013-11-06
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2014-08-14 | 2014-10-10 | SB Red Cedar Enterprises Inc-Quadrangle Main 3/4 | W9126G14D00190007 | 3102034 | 3102034 | 2015-09-05 | 2015-09-05
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-05-09 | 2012-05-29 | AE RabaKistner Consultants-Sidewalk Survey $1865.12 | PNASA1205700 | 1889 | 1889 | 2012-06-09 | 2012-06-09
2016-04-15 | 2011 | Air Force Active | MPLS083737R3 |  | 2012-05-09 | 2012-08-09 | SB JSR Inc-Exterior Facilties & Grounds | W912BV11C0038 | 6886921 | 7284529 | 2014-04-04 | 2014-04-04
2016-04-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2011-12-16 | 2012-10-31 | AE-Merrick&Company (E&D) | W9126G08D00060055 | 400152 | 400152 | 2013-11-06 | 2013-11-06
2016-04-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2014-08-14 | 2014-10-10 | SB Red Cedar Enterprise Inc-Ext Facs/Kneewall/Quad | W9126G14D00190007 | 7301694 | 7301694 | 2016-01-03 | 2016-02-20
2016-04-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2013-03-18 | 2013-06-03 | SB FPI/JSR Inc/DCF2 Ktr - Gary Rd 3/3 | W9126G13C0098 | 91850 | 91850 | 2013-11-06 | 2013-11-06
2016-04-15 | 2012 | Air Force Active | MPLS083737R4 |  | 2011-12-16 | 2013-07-17 | LB-SpawGlass Contractors, Inc. | W9126G12C0023 | 50528593 | 52398956 | 2014-11-26 | 2015-10-27
2016-04-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2011-03-07 | 2015-04-24 | SB Gideon Contracting | W9126G14D00570019 | 54574 | 54574 | 2015-04-24 | 2015-04-24
2016-04-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2012-12-12 | 2013-06-03 | SB JSR Inc (Gary Rd Realign Pt 2of3) | W9126G13C0098 | 152927 | 155310 | 2014-01-18 | 2014-01-18
2016-04-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2012-02-15 | 2014-01-16 | AEP Services Corp (Gate Monitor Svs 100K x 2 yrs | W9126G12C00170001 | 202008 | 202008 | 2015-01-31 | 2015-01-31
2016-04-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2011-02-25 | 2011-06-30 | LB-KBR General Contract | W9126G11C0027 | 25985137 | 27613958 | 2013-04-20 | 2014-06-30
2016-04-15 | 2011 | Air Force Active | MPLS083737S2 |  | 2011-03-07 | 2012-10-31 | Merrick & Company (Tittle II Services) $59,036.40 | W9126G08D00060054 | 118073 | 118073 | 2015-04-24 | 2015-04-24
2016-04-15 | 2010 | Air Force Active | MUHJ053008 |  | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185824 | 8498082 | 2012-01-26 | 2013-07-19
2016-04-15 | 2010 | Air Force Active | MUHJ053008 |  | 2014-07-29 | 2014-09-29 | Homeland Contracting Corporation | F4A0012D00040013 | 231490 | 231490 | 2015-08-25 | 2015-08-25
2016-04-15 | 2013 | Air Force Active | NKAK103006 |  | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869000 | 21464974 | 2015-07-23 | 2015-11-02
2016-04-15 | 2013 | Air Force Active | NKAK113005 |  | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218502 | 4350114 | 2015-10-21 | 2015-11-28
2016-04-15 | 2014 | Air Force Active | NUEX093007 |  | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699907 | 4710819 | 2015-07-07 | 2015-11-30
2016-04-15 | 2014 | Air Force Active | NUEX093011 |  | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513636 | 15782045 | 2016-02-14 | 2016-03-15
2016-04-15 | 2015 | Air Force Active | NUEX103005 |  | 2014-12-16 | 2015-04-30 | SAI-TALON JV | W912PL15C0005 | 13097800 | 13097800 | 2016-11-22 | 2016-11-22
2016-04-15 | 2015 | Air Force Active | NUEX123001 |  | 2015-02-06 | 2015-08-19 | KORTE Construction Company | W912PL15C0015 | 10318700 | 10318700 | 2017-05-16 | 2017-05-16
2016-04-15 | 2014 | Air Force Active | PAYZ130011 |  | 2012-09-11 | 2015-04-10 | Clark Construction Group, LLC | W912DR15C0008 | 20623200 | 20623200 | 2016-07-30 | 2016-07-30
2016-04-15 | 2014 | Air Force Active | PAYZ130011 |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 245125000 | 245125000 | 2016-04-13 | 2016-04-13
2016-04-15 | 2014 | Air Force Active | PRQE145117 |  | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924500 | 64665525 | 2016-01-05 | 2016-02-04
2016-04-15 | 2015 | Air Force Active | PRQE145118 |  | 2015-01-26 | 2015-04-03 | Hanke Constructors | W912DQ14D40030001 | 6389509 | 6389509 | 2016-05-04 | 2016-05-04
2016-04-15 | 2014 | Air Force Active | PRQE145121 |  | 2014-03-14 | 2015-03-02 | Aerostar SES, Inc | W912DQ15C4005 | 3061137 | 3104687 | 2016-04-19 | 2016-05-16
2016-04-15 | 2014 | Air Force Active | PRQE145136 |  | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100500 | 8268701 | 2015-12-17 | 2015-12-19
2016-04-15 | 2014 | Air Force Active | PRQE145138 |  | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976000 | 976000 | 2017-03-10 | 2017-03-10
2016-04-15 | 2014 | Air Force Active | PRQE145142 |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200000 | 26126594 | 2017-01-19 | 2017-02-18
2016-04-15 | 2015 | Air Force Active | PRQE155118 |  | 2015-01-26 | 2015-04-03 | Hanke Constructors | W912DQ14D40030001 | 2286153 | 2286153 | 2016-05-04 | 2016-05-04
2016-04-15 | 2014 | Air Force Active | PRQE155119 |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959000 | 54644437 | 2015-12-26 | 2016-01-25
2016-04-15 | 2014 | Air Force Active | PRQE155122 |  | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306162 | 7372673 | 2015-10-15 | 2015-11-04
2016-04-15 | 2015 | Air Force Active | PRQE155124 |  | 2015-01-26 | 2015-04-17 | K&K Industries, Inc | W912DQ14D40090002 | 5679326 | 5690143 | 2016-11-02 | 2016-11-02
2016-04-15 | 2013 | Air Force Active | PTFL126001 |  | 2014-06-05 | 2015-09-03 | Ranco Construction, INC | W912DS15C0009 | 1383300 | 1383300 | 2016-06-29 | 2016-06-29
2016-04-15 | 2014 | Air Force Active | QJVF092013 |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540270 | 9500491 | 2016-01-06 | 2016-01-06
2016-04-15 | 2014 | Air Force Active | QKKA133001P1 |  | 2015-04-10 | 2015-09-29 | Nishimatsu Construction Corp | FA520515C0005 | 21841808 | 21841808 | 2017-09-28 | 2017-09-28
2016-04-15 | 2013 | Air Force Active | QKKA134001 |  | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336739 | 14948824 | 2015-09-23 | 2016-01-11
2016-04-15 | 2014 | Air Force Active | QKKA144002 |  | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302110 | 25302110 | 2017-01-14 | 2017-01-14
2016-04-15 | 2014 | Air Force Active | QSEU123003 |  | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547470 | 1547470 | 2015-11-19 | 2015-11-19
2016-04-15 | 2014 | Air Force Active | RKMF083002 |  | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381000 | 30397469 | 2016-09-28 | 2016-12-07
2016-04-15 | 2014 | Air Force Active | RKMF103005 |  | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D01130012 | 4829984 | 4829984 | 2016-02-18 | 2016-02-18
2016-04-15 | 2014 | Air Force Active | RKMF103006 |  | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974014 | 7142028 | 2016-01-06 | 2016-03-01
2016-04-15 | 2014 | Air Force Active | RKMF103009 |  | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066000 | 8450619 | 2015-12-16 | 2015-12-31
2016-04-15 | 2014 | Air Force Active | RKMF113005 |  | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922700 | 14938360 | 2016-08-01 | 2016-08-01
2016-04-15 | 2015 | Air Force Active | RKMF123007 |  | 2015-03-05 | 2015-07-21 | CTI, OGDEN, UT | W912PL15C0013 | 7733000 | 7733000 | 2017-04-01 | 2017-04-01
2016-04-15 | 2015 | Air Force Active | RKMF133001 |  | 2015-01-22 | 2015-06-12 | CTI | W912PL15C0010 | 11361000 | 11361000 | 2017-01-19 | 2017-01-19
2016-04-15 | 2015 | Air Force Active | RKMF143001 |  | 2015-03-26 | 2015-09-16 | Harper Construction Co. | W912PL15C0017 | 22397265 | 22397265 | 2017-09-11 | 2017-09-11
2016-04-15 | 2015 | Air Force Active | SAKW059006 |  | 2014-11-07 | 2015-03-07 | P&S Construction Inc | N4019210D28040025 | 2841600 | 2841600 | 2016-04-10 | 2016-04-10
2016-04-15 | 2014 | Air Force Active | SAKW113003 |  | 2014-01-23 | 2015-03-06 | P&S Construction Inc | N4019210D28040023 | 7050506 | 7050506 | 2016-07-08 | 2016-07-08
2016-04-15 | 2015 | Air Force Active | SAKW113008 |  | 2015-03-20 | 2015-06-30 | GSI-EA JV, LLC | N4019210D28090004 | 3586194 | 3586194 | 2016-06-21 | 2016-06-21
2016-04-15 | 2014 | Air Force Active | SAKW133005 |  | 2014-03-04 | 2015-03-05 | P & S Construction | N4019210D2804KB01 | 3587000 | 3587000 | 2017-02-06 | 2017-02-06
2016-04-15 | 2015 | Air Force Active | SAKW143031 |  | 2014-12-05 | 2015-03-06 | P&S Construction Inc | N4019210D28040024 | 6205000 | 6205000 | 2016-07-30 | 2016-07-30
2016-04-15 | 2012 | Air Force Active | SGBP100904C |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 524445324 | 542271417 | 2016-09-10 | 2016-12-21
2016-04-15 | 2011 | Air Force Active | SXHT053001 |  | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231044 | 147964878 | 2015-12-02 | 2015-12-02
2016-04-15 | 2011 | Air Force Active | SXHT053001 |  | 2013-12-03 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99768 | 99768 | 2014-09-30 | 2014-09-30
2016-04-15 | 2010 | Air Force Active | TYFR053037 |  | 2012-01-27 | 2012-06-15 | D & b Bau GmbH, Neustadt | W912GB09C0022 | 5745698 | 5997071 | 2013-07-06 | 2013-07-06
2016-04-15 | 2011 | Air Force Active | TYFR083001 |  | 2012-05-10 | 2012-09-26 | Peter Gross GmbH | W912GB10C0001A | 2140702 | 2253365 | 2013-05-19 | 2013-05-19
2016-04-15 | 2011 | Air Force Active | TYFR106261 |  | 2013-09-13 | 2013-11-13 | MICKAN | C11-4014 | 1840288 | 1840288 | 2014-12-12 | 2014-12-12
2016-04-15 | 2013 | Air Force Active | TYFR126175 |  | 2014-01-21 | 2014-07-23 | MICKAN Generalbau | C124019 | 1664151 | 1737129 | 2015-02-24 | 2015-06-04
2016-04-15 | 2011 | Air Force Active | TYFU083507R2 |  | 2013-08-30 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | 16251895 | 16251895 | 2015-07-15 | 2015-07-15
2016-04-15 | 2014 | Air Force Active | UHHZ123001 |  | 2014-08-01 | 2015-01-15 | Garbutt Construction Company | W912HN10D00340002 | 1779360 | 1779360 | 2016-05-11 | 2016-05-11
2016-04-15 | 2012 | Air Force Active | USAFE17002 |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421000 | 43939851 | 2014-01-16 | 2015-10-10
2016-04-15 | 2012 | Air Force Active | USAFE17003 |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521530 | 10521530 | 2014-05-24 | 2015-10-01
2016-04-15 | 2012 | Air Force Active | USAFE17004 |  | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587915 | 27299359 | 2014-04-13 | 2015-01-27
2016-04-15 | 2014 | Air Force Active | VKAG133001 |  | 2014-07-18 | 2015-01-28 | Crew MW, LLC | FA480915CC001 | 1864766 | 1864766 | 2016-06-05 | 2016-07-25
2016-04-15 | 2008 | Air Force Active | VLSB083007 |  | 2015-05-24 | 2015-07-23 | Bell & Carrington | W912HN15P0034 | 7320 | 7320 | 2017-07-22 | 2017-07-22
2016-04-15 | 2008 | Air Force Active | VLSB083007 |  | 2015-05-29 | 2015-07-28 | Property Solutions, LLC | W912HN15P0036 | 14350 | 14350 | 2017-01-18 | 2017-01-18
2016-04-15 | 2008 | Air Force Active | VLSB083007 |  | 2008-07-31 | 2008-09-29 | Prime Ktr Golf Course CNS (Phase 1) | N6945008C2846 | 2771874 | 2827760 | 2009-09-29 | 2009-09-29
2016-04-15 | 2008 | Air Force Active | VLSB083007 |  | 2011-04-11 | 2011-06-10 | J2 Engineering (Phase 2) | N6945008D17820005 | 3446432 | 5339270 | 2012-10-10 | 2014-01-30
2016-04-15 | 2014 | Air Force Active | VYHK143301 |  | 2014-12-15 | 2015-09-03 | UVB, Bitburg | C14-7392 | 1911000 | 1911000 | 2017-09-14 | 2017-09-14
2016-04-15 | 2014 | Air Force Active | WWCX103028 |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817608 | 39817608 | 2016-08-08 | 2016-08-08
2016-04-15 | 2013 | Air Force Active | WWCX103032 |  | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031649 | 24018115 | 2015-07-29 | 2015-07-29
2016-04-15 | 2013 | Air Force Active | XLWU103002 |  | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 12555018 | 13564863 | 2015-08-11 | 2016-08-26
2016-04-15 | 2014 | Air Force Active | XLWU103007 |  | 2015-03-10 | 2015-04-14 | Southeast Cherokee Construction | W9127810D00780009 | 9094468 | 9158994 | 2016-11-11 | 2016-11-25
2016-04-15 | 2011 | Air Force Active | XQPZ084017 |  | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995500 | 25607151 | 2014-09-29 | 2015-03-07
2016-04-15 | 2014 | Air Force Active | XQPZ124003 |  | 2014-12-03 | 2015-03-25 | John Bowman Incorporated (JBI) | W9128F12D00370011 | 1581000 | 1588581 | 2015-12-09 | 2016-01-20
2016-04-15 | 2010 | Air Force Active | XTLF033303 |  | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849633 | 9592033 | 2012-02-12 | 2012-06-29
2016-04-15 | 2012 | Air Force Active | YWHG071005 |  | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172600 | 4308791 | 2013-09-07 | 2014-08-15
2016-04-15 | 2014 | Air Force Active | YWHG111010 |  | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817700 | 3828847 | 2015-12-04 | 2016-01-10
2016-04-15 | 2014 | Air Force Active | ZHTV053302 |  | 2015-03-11 | 2015-06-23 | Messer Construction | W912QR15C0012 | 24166000 | 24166000 | 2017-06-02 | 2017-06-02
2016-04-15 | 2014 | Air Force Active | ZHTV126003 |  | 2014-11-13 | 2015-04-02 | Ma Chis Kawv | W912QR14D0013 | 1989978 | 1998690 | 2016-04-14 | 2016-04-14
2016-04-05 | 2013 | Air Force Reserve | CTGB109003 |  | 2014-07-30 | 2014-09-30 | Ma-Chis KAWV V, LLC | W912QR14D00130004 | 1078904 | 1110040 | 2015-11-04 | 2016-07-18
2016-04-05 | 2013 | Air Force Reserve | DDPM120009 |  | 2015-02-22 | 2015-09-16 | IICON CONSTRUCTION GROUP | FA667515C0002 | 1697850 | 1697850 | 2016-09-29 | 2016-09-29
2016-04-05 | 2015 | Air Force Reserve | DDPM130008 |  | 2015-06-22 | 2015-08-27 | K-W Construction | N6945013D17690003 | 2814000 | 2814000 | 2016-07-27 | 2017-01-16 | Bids are still very high. Base has started Termination for Convenience (T4C) actions
2016-04-05 | 2012 | Air Force Reserve | DKFX079003 |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149000 | 9004770 | 2013-07-13 | 2016-03-15
2016-04-05 | 2014 | Air Force Reserve | PDPG030130P1 |  | 2014-12-02 | 2015-04-24 | Macro-Z Technology | W912QR15C0009 | 17092932 | 17092932 | 2016-10-26 | 2016-10-26
2016-04-05 | 2013 | Air Force Reserve | RVKQ099095 |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242986 | 5242986 | 2016-01-15 | 2016-06-13
2016-04-05 | 2012 | Air Force Reserve | RVKQ120572 |  | 2013-01-04 | 2014-08-21 | Oddo Construction Services | FA667014R00040001 | 2087131 | 2137512 | 2015-03-21 | 2016-03-15
2016-04-15 | 2013 | Air National Guard | ATQZ099073 |  | 2014-10-01 | 2014-12-08 | E & B Paving, Inc | W912L91322101 | 1498405 | 1498405 | 2016-04-21 | 2016-04-15
2016-04-15 | 2012 | Air National Guard | ATQZ099080 |  | 2014-05-10 | 2014-08-27 | Patterson Horth, Inc. | W912L910D00090055 | 4241000 | 4241000 | 2015-11-20 | 2016-05-27
2016-04-15 | 2012 | Air National Guard | AXQD119004 |  | 2013-04-10 | 2013-07-12 | Cornerstone Construction Svs | W912SV10D00080004 | 1240639 | 1240639 | 2014-02-07 | 2016-02-28
2016-04-15 | 2012 | Air National Guard | AXQD129074 |  | 2014-09-12 | 2014-12-15 | Cutter Enterprises LLC | W912SV15C0001 | 1680218 | 1680218 | 2016-07-16 | 2017-07-16
2016-04-15 | 2015 | Air National Guard | BKTZ129083 |  | 2015-07-29 | 2015-09-21 | RL Alvarez Constction, LLC | W912L715C0009 | 2358247 | 2358247 | 2016-10-20 | 2016-10-25
2016-04-15 | 2014 | Air National Guard | BRKR999147 |  | 2014-04-02 | 2014-08-13 | Southeast Cherokee Conwstruction, Inc | W912JA14C0001 | 8201275 | 8201275 | 2016-10-23 | 2016-08-02
2016-04-15 | 2015 | Air National Guard | CEKT139004 |  | 2015-02-17 | 2015-06-03 | Cutter Enterprises, LLC | W91ZRS15C0002 | 14859726 | 14859726 | 2016-12-05 | 2016-12-23
2016-04-15 | 2013 | Air National Guard | DPEZ089017 |  | 2013-08-28 | 2013-09-27 | Faith Enterprises | W912L313D00030001 | 5389532 | 5389532 | 2016-03-15 | 2016-05-27
2016-04-15 | 2015 | Air National Guard | FFAN139010 |  | 2015-03-01 | 2015-07-09 | Lang Construction | W912LP15C00010005 | 8154789 | 8154789 | 2016-08-07 | 2016-08-04
2016-04-15 | 2014 | Air National Guard | FPBB129050 |  | 2014-07-17 | 2014-09-08 | R.J. Ortlieb | W912PQ12D00100008 | 4895886 | 4895886 | 2015-08-04 | 2015-11-20
2016-04-15 | 2013 | Air National Guard | HAYW109006 |  | 2014-08-15 | 2014-10-26 | Cooper Chase | W912LA11D00040002 | 1261072 | 1261072 | 2016-02-25 | 2016-04-26
2016-04-15 | 2013 | Air National Guard | KNMD119001 |  | 2013-03-04 | 2013-09-12 | Nan Inc. | W912J613C0006 | 5593905 | 5593905 | 2015-04-24 | 2016-04-29
2016-04-15 | 2014 | Air National Guard | LDXF099060 |  | 2014-07-30 | 2014-09-22 | Patterson-Horth | W912L914D00110002 | 7071641 | 7071641 | 2016-02-28 | 2016-06-30
2016-04-15 | 2014 | Air National Guard | LKLW109037 |  | 2014-08-06 | 2014-09-25 | Lobar Associates | W912KC14C0008 | 7039937 | 7039937 | 2015-10-25 | 2016-05-31
2016-04-15 | 2014 | Air National Guard | LKLW959716 |  | 2015-07-29 | 2015-09-29 | Miller Bros CNS Inc | W912KC15C00270000 | 1904075 | 1904075 | 2016-07-12 | 2016-07-12
2016-04-15 | 2015 | Air National Guard | MBMV129060 |  | 2015-03-01 | 2015-04-15 | Beckering Construction | W912JB15C2007 | 5952943 | 5952943 | 2016-05-14 | 2016-05-06
2016-04-15 | 2014 | Air National Guard | PSTE129092 |  | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W9124209D0003S401 | 1813699 | 1813699 | 2014-12-24 | 2016-01-29
2016-04-15 | 2014 | Air National Guard | PSXE109034 |  | 2014-04-15 | 2014-07-01 | Howard Pence, Inc | W912L714C0004 | 17303286 | 17303286 | 2016-07-21 | 2016-07-20
2016-04-15 | 2015 | Air National Guard | PSXE139000 |  | 2015-03-29 | 2015-07-20 | Eutaw Construction | W912L71322101 | 1349711 | 1349711 | 2016-10-18 | 2016-09-30
2016-04-15 | 2012 | Air National Guard | SPBN079047 |  | 2013-05-08 | 2013-08-29 | Maron Construction Co. | W912SV13C0003 | 8178006 | 8178006 | 2014-09-24 | 2016-01-29
2016-04-15 | 2012 | Air National Guard | SPBN089050 |  | 2015-07-09 | 2015-08-10 | Maron Construction Company | W912SV10D00170007 | 1922000 | 1922000 | 2016-09-08 | 2016-09-28
2016-04-15 | 2015 | Air National Guard | SZCQ139901 |  | 2015-01-28 | 2015-07-28 | Cutter Enterprises, LLC | W912TF15C05000008 | 16475861 | 16475861 | 2016-11-19 | 2018-02-02
2016-04-15 | 2015 | Air National Guard | SZCQ139904 |  | 2015-01-28 | 2015-07-27 | Cutter Enterprises, LLC | W912TF15C0500 | 16344691 | 16344691 | 2016-11-18 | 2018-02-02
2016-04-15 | 2012 | Air National Guard | TQKD129072 |  | 2014-03-25 | 2014-07-22 | Total Site Services | W912JV14C0006 | 1802993 | 1802993 | 2015-03-19 | 2016-01-29
2016-04-15 | 2013 | Air National Guard | TQKD139018 |  | 2014-11-03 | 2015-01-20 | Andrews Contracting Services | W912JV15C0001 | 912772 | 912772 | 2015-07-09 | 2016-02-28
2016-04-15 | 2013 | Air National Guard | TQKD139018 |  | 2014-10-09 | 2014-12-16 | Port of Portland | W912JV1422150 | 130000 | 130000 | 2015-08-01 | 2016-01-15
2016-04-15 | 2012 | Air National Guard | TUMR109004 |  | 2013-04-30 | 2013-09-26 | R.B. Construction Group, Inc. | W912LR13C0001 | 1500000 | 1500000 | 2015-10-06 | 2017-03-31
2016-04-15 | 2014 | Air National Guard | TWLR129077 |  | 2014-07-25 | 2014-11-14 | MARON CONSTRUCTION CO., INC. | W912LD15C0001 | 6315747 | 6315747 | 2015-12-14 | 2016-06-08
2016-04-15 | 2014 | Air National Guard | ULYB112022 |  | 2014-07-30 | 2014-09-12 | E.L.Crawford Construction | W912NS14D00160002 | 1954163 | 1954163 | 2015-10-12 | 2016-05-05
2016-04-15 | 2014 | Air National Guard | WAAR109002 |  | 2014-07-02 | 2014-08-20 | AWA/Megen Joint Venture LLC | W9136414C0011 | 5944120 | 5944120 | 2015-12-01 | 2016-02-29
2016-04-15 | 2012 | Air National Guard | WAAR129078 |  | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | W9136413D00050002 | 1793652 | 1793652 | 2014-02-23 | 2016-06-30
2016-04-15 | 2014 | Air National Guard | WEAS129000 |  | 2015-06-07 | 2015-08-20 | Mac Construction & Excavating Inc | W912KZ1222102 | 2630000 | 2630000 | 2015-08-20 | 2016-06-15
2016-04-15 | 2012 | Air National Guard | WKVB099052 |  | 2014-12-04 | 2015-03-25 | Regiment | W912PQ15C0003 | 2021340 | 2021340 | 2016-04-23 | 2016-06-28
2016-04-15 | 2014 | Air National Guard | XHZG129946 |  | 2014-06-25 | 2014-08-20 | Magnum Constrution | W912L611D00010029 | 1979359 | 1979359 | 2015-08-15 | 2015-10-08
2016-04-15 | 2015 | Air National Guard | ZAWA159061 |  | 2015-03-01 | 2015-06-30 | Senate Builders | W912KC10D00170029 | 4185000 | 4185000 | 2016-02-15 | 2016-02-15
2016-04-15 | 2015 | Air National Guard | ZAWA159061 |  | 2015-05-20 | 2015-09-30 | Marteen Inc | W912KC15R00160000 | 1500000 | 1500000 | 2016-01-18 | 2016-03-31
2016-03-31 | 2012 | Army Active | 1235 |  | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23139000 | 23149000 | 2014-04-10 | 2016-03-16
2016-03-31 | 2011 | Army Active | 13852 |  | 2011-07-15 | 2011-09-14 | Native American Services Corp. | W9128F-11-C-0061 | 27829000 | 34679000 | 2013-04-27 | 2015-01-16
2016-03-31 | 2011 | Army Active | 13852 |  | 2011-07-15 | 2015-09-28 | Dawson Technical, LLC | W9128F-15-C-0044 | 1996000 | 1996000 | 2016-07-23 | 2016-07-23
2016-03-31 | 2012 | Army Active | 17220 |  | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12623000 | 12866000 | 2015-11-11 | 2016-03-30
2016-03-31 | 2012 | Army Active | 20697 |  | 2012-01-27 | 2012-08-30 | Liberty Mutual Insurance Company | W912BV-12-C-0018 | 13000000 | 13225000 | 2014-01-28 | 2016-01-20
2016-03-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 11660000 | 11694000 | 2013-09-20 | 2014-11-24
2016-03-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2014-07-02 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 727000 | 745000 | 2017-02-08 | 2017-02-08
2016-03-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2015-01-14 | Doyon Management Services, LLC | W91236-15-C-0017 | 14297000 | 14297000 | 2017-05-03 | 2017-05-03
2016-03-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650000 | 46658000 | 2015-10-15 | 2015-10-16
2016-03-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2014-09-03 | VISTA Construction LLC | W91236-14-C-0043 | 4055000 | 4055000 | 2015-09-16 | 2016-07-31
2016-03-31 | 2012 | Army Active | 5034 |  | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603000 | 13341000 | 2014-07-18 | 2016-06-30
2016-03-31 | 2013 | Army Active | 51519 |  | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959000 | 7308000 | 2015-02-15 | 2015-12-31
2016-03-31 | 2013 | Army Active | 51519 |  | 2012-05-16 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 2033000 | 2033000 | 2014-06-04 | 2016-02-29
2016-03-31 | 2014 | Army Active | 51868 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 55619000 | 56304000 | 2016-12-26 | 2017-01-24
2016-03-31 | 2015 | Army Active | 51937 |  | 2015-07-28 | 2016-01-28 | ACC Construction Co., Inc | W912HP-16-C-0001 | 45035000 | 45035000 | 2018-03-17 | 2018-03-17
2016-03-31 | 2014 | Army Active | 53584 |  | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036000 | 40565000 | 2017-12-09 | 2017-12-09
2016-03-31 | 2011 | Army Active | 53789 |  | 2012-12-18 | 2013-09-30 | Halbert Construction Company, Inc. | W91238-13-C-0012 | 18519000 | 27801000 | 2015-01-05 | 2016-12-01
2016-03-31 | 2014 | Army Active | 54106 |  | 2013-12-24 | 2014-05-28 | TSS-Garco Joint Venture | W912DW-14-C-0012 | 7716000 | 7754000 | 2016-02-09 | 2016-02-09
2016-03-31 | 2013 | Army Active | 55121 |  | 2014-10-21 | 2015-07-31 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 40866000 | 40866000 | 2017-12-30 | 2017-12-30
2016-03-31 | 2012 | Army Active | 55823 |  | 2012-01-05 | 2012-07-26 | Big-D Construction Corp | W91238-12-C-0024 | 22609000 | 29930000 | 2015-02-15 | 2016-03-03
2016-03-31 | 2012 | Army Active | 55985 |  | 2012-01-10 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15916000 | 17260000 | 2016-03-23 | 2016-09-30
2016-03-31 | 2011 | Army Active | 56024 |  | 2012-06-29 | 2012-09-25 | Nan, Inc. | W9128A-12-C-0019 | 21105000 | 22909000 | 2014-10-14 | 2016-09-01
2016-03-31 | 2012 | Army Active | 57508 |  | 2013-03-15 | 2013-07-22 | Hensel Phelps Construction Co. | W912DR-13-C-0035 | 39700000 | 44968000 | 2015-03-12 | 2015-11-20
2016-03-31 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565000 | 29485000 | 2015-10-05 | 2016-03-15
2016-03-31 | 2011 | Army Active | 57595 |  | 2010-11-23 | 2015-06-01 | Argo Systems LLC | W912DR-14-D-0019 | 734000 | 734000 | 2015-12-22 | 2015-12-11
2016-03-31 | 2011 | Army Active | 57595 |  | 2010-11-23 | 2011-08-08 | Lebolo-Watts Constructors 01 JV LLC | W912DR-11-C-0033 | 18392000 | 21049000 | 2013-04-28 | 2014-04-15
2016-03-31 | 2012 | Army Active | 58046 |  | 2011-10-25 | 2013-04-01 | TSS-Garco Joint Venture | W912DW-12-C-0043 | 16416000 | 16346000 | 2014-11-12 | 2015-10-30
2016-03-31 | 2011 | Army Active | 58675 |  | 2011-02-22 | 2015-09-30 | Semper Tek, Inc. | W912QR-14-D-0023 | 354000 | 354000 | 2016-10-15 | 2016-08-16
2016-03-31 | 2011 | Army Active | 58675 |  | 2011-02-22 | 2011-06-20 | ACC Construction, Inc. | W912QR-11-C-0025 | 9853000 | 10340000 | 2012-10-28 | 2012-12-04
2016-03-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2008-03-31 | Shinsung Engr. & Const. Co., Ltd. | W912UM-08-C-0011 | 15961000 | 559000 | 2010-06-13 | 2008-10-22
2016-03-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2009-01-29 | Hanwha Engr. & Corporation Co., Ltd. | W912UM-09-C-0009 | 17815000 | 18941000 | 2011-01-01 | 2011-05-18
2016-03-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | W912UM-12-C-0057 | 5458000 | 6347000 | 2014-03-16 | 2016-04-15
2016-03-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32469000 | 35297000 | 2014-09-07 | 2015-06-09
2016-03-31 | 2012 | Army Active | 58925 |  | 2012-03-12 | 2014-09-05 | DBA ARGE JV PGWM NETCOM | W912GB-14-C-0037 | 29010000 | 29800000 | 2016-07-07 | 2017-01-13
2016-03-31 | 2013 | Army Active | 58970 |  | 2013-04-29 | 2013-10-30 | ACC Construction Co., Inc | W912HP-14-C-0003 | 21786000 | 22292000 | 2015-05-28 | 2015-11-05
2016-03-31 | 2011 | Army Active | 59044 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270000 | 116533000 | 2015-11-14 | 2016-04-29
2016-03-31 | 2013 | Army Active | 59626 |  | 2013-05-31 | 2013-08-23 | NEU Security Services, LLC | W9128F-13-C-0016 | 14080000 | 16109000 | 2015-03-12 | 2015-10-15
2016-03-31 | 2011 | Army Active | 60555 |  | 2010-12-16 | 2012-05-14 | Hessisches Baumanagement Wiesbaden | W912GB-08-C-0005 | 28606000 | 33197000 | 2014-06-01 | 2016-03-29
2016-03-31 | 2011 | Army Active | 61453 |  | 2012-08-06 | 2013-05-23 | TMG SERVICES, INC. Linda Frazier | W912DR-13-C-0030 | 6189000 | 6584000 | 2014-11-27 | 2016-03-31
2016-03-31 | 2012 | Army Active | 61515 |  | 2011-10-19 | 2012-11-07 | Bristol General Contractors, LLC | W911KB-13-C-0002 | 21813000 | 22240000 | 2014-12-06 | 2016-01-22
2016-03-31 | 2013 | Army Active | 61810 |  | 2012-12-06 | 2013-05-29 | Orocon-Carothers JV1 | W912QR-13-C-0010 | 23451000 | 23838000 | 2014-12-07 | 2015-02-02
2016-03-31 | 2013 | Army Active | 61810 |  | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | W912QR-14-C-0007 | 25750000 | 25812000 | 2015-08-26 | 2015-10-19
2016-03-31 | 2012 | Army Active | 61842 |  | 2012-03-13 | 2015-04-20 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0004 | 12172000 | 10255000 | 2016-12-01 | 2016-12-01
2016-03-31 | 2014 | Army Active | 62204 |  | 2015-03-19 | 2016-02-08 | Meltech Corp., Inc. | W912DR-14-D-0021 | 6840000 | 6840000 | 2017-08-16 | 2017-09-20
2016-03-31 | 2012 | Army Active | 62657 |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100113000 | 101256000 | 2015-10-19 | 2016-07-06
2016-03-31 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 84367000 | 85036000 | 2021-06-09 | 2021-12-06
2016-03-31 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV | W91238-11-C-0010 | 34801000 | 3567000 | 2013-06-12 | 2014-06-30
2016-03-31 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W91238-14-C-0040 | 38915000 | 38935000 | 2016-09-30 | 2016-10-22
2016-03-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-06-28 | M.A. Mortenson Company | W9126G-08-D-0045 | 19332000 | 19731000 | 2013-11-17 | 2013-11-14
2016-03-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-09-26 | MEGEN Construction Company, Inc. | W912HN-11-D-0047 | 7295000 | 9157000 | 2015-04-08 | 2016-10-24
2016-03-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-01-03 | TSS-Garco Joint Venture | W912DW-13-C-0019 | 8912000 | 9169000 | 2014-08-06 | 2015-04-30
2016-03-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-09-21 | 3D Contracting Inc. | W912DW-12-C-0046 | 14649000 | 15311000 | 2014-05-24 | 2014-12-09
2016-03-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | W912DQ-12-D-4006 | 2493000 | 3965000 | 2014-01-04 | 2015-12-08
2016-03-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-08-23 | KCI Construction Company | W912DQ-12-C-4009 | 30970000 | 32860000 | 2014-03-12 | 2014-10-27
2016-03-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-07 | Arch Insurance Company | W912DQ-11-D-4011 | 8541000 | 8904000 | 2014-08-25 | 2016-04-29
2016-03-31 | 2012 | Army Active | 64415 |  | 2011-12-16 | 2012-03-23 | Blackhawk Ventures, LLC | W9126G-09-D-0093 | 10283000 | 11234000 | 2013-11-06 | 2016-01-08
2016-03-31 | 2012 | Army Active | 64415 |  | 2011-12-16 | 2012-08-17 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 11857000 | 12236000 | 2014-04-02 | 2015-04-16
2016-03-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-05-17 | Tunista Construction, LLC | W912DW-13-C-0035 | 9433000 | 11453000 | 2014-12-18 | 2015-12-31
2016-03-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-06-18 | Megen Construction Company, Inc. | W912HN-11-D-0047 | 14849000 | 16091000 | 2015-01-02 | 2016-05-31
2016-03-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-09-12 | Environet, Inc. | W912DW-13-C-0042 | 5662000 | 11614000 | 2015-02-12 | 2016-04-13
2016-03-31 | 2011 | Army Active | 64520 |  | 2010-10-22 | 2015-09-30 | Olgoonik Diversified Services, LLC | W912DQ-14-D-4006 | 175000 | 174000 | 2016-04-18 | 2016-04-18
2016-03-31 | 2011 | Army Active | 64520 |  | 2010-10-22 | 2011-05-27 | Curtiss Manes Schulte, Inc. | W912DQ-11-C-4013 | 10639000 | 14060000 | 2012-12-03 | 2013-05-14
2016-03-31 | 2012 | Army Active | 64753 |  | 2012-01-09 | 2012-06-29 | Harper Construction Company, Inc. | W912BV-12-C-0012 | 37868000 | 38440000 | 2014-04-11 | 2014-08-29
2016-03-31 | 2012 | Army Active | 64753 |  | 2012-01-09 | 2012-07-13 | Liberty Mutual Insurance Company | W9126G-11-D-0061 | 6095000 | 6155000 | 2014-02-03 | 2015-11-06
2016-03-31 | 2011 | Army Active | 64760 |  | 2011-02-08 | 2012-09-19 | SRB International LLC | W9128A-12-C-0013 | 13310000 | 13370000 | 2014-08-17 | 2016-04-15
2016-03-31 | 2012 | Army Active | 64939 |  | 2012-06-20 | 2012-09-24 | Grimberg/Amatea JV | W912DR-12-C-0023 | 30554000 | 35660000 | 2014-11-20 | 2016-01-10
2016-03-31 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503000 | 42184000 | 2014-07-28 | 2016-04-29
2016-03-31 | 2012 | Army Active | 65374 |  | 2012-01-05 | 2013-01-07 | Turner Strategic Technologies, LLC | W91236-13-C-0017 | 8195000 | 8565000 | 2014-11-28 | 2015-05-28
2016-03-31 | 2011 | Army Active | 65650 |  | 2011-11-04 | 2012-02-28 | Niking Corporation | W9128A-12-C-0003 | 46780000 | 50128000 | 2014-04-23 | 2015-10-23
2016-03-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18727000 | 19899000 | 2015-04-08 | 2015-10-14
2016-03-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2015-09-30 | Fortis Networks, Inc. | W912DQ-14-D-4011 | 1828000 | 1828000 | 2016-08-06 | 2016-08-06
2016-03-31 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30762000 | 38201000 | 2015-12-12 | 2017-08-08
2016-03-31 | 2013 | Army Active | 66023 |  | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345000 | 27237000 | 2016-09-09 | 2016-10-12
2016-03-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2015-01-20 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 6228000 | 6423000 | 2016-05-05 | 2016-09-02
2016-03-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687000 | 14606000 | 2014-12-23 | 2014-12-31
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775000 | 14633000 | 2014-08-26 | 2015-03-02
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Vet Industrial, Inc. | W912DW-10-D-1021 | 4980000 | 5253000 | 2013-11-01 | 2013-11-25
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-08-29 | Alutiiq Diversified Services, LLC | W912DW-12-C-0040 | 10525000 | 13116000 | 2014-03-11 | 2015-07-28
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-08-02 | James Talcott Construction, Inc. | W912DW-10-D-1015 | 5769000 | 6297000 | 2014-11-17 | 2015-02-06
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Bristol General Contractors, LLC | W912DW-12-D-1018 | 1979000 | 2354000 | 2013-05-30 | 2013-11-22
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-06-20 | Bristol General Contractors, LLC | W912DW-14-C-0015 | 5288000 | 6122000 | 2015-09-10 | 2016-04-15
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6814000 | 7356000 | 2015-08-21 | 2015-10-09
2016-03-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-12-24 | Burr-MZT Joint Venture | W912DW-14-C-0001 | 919000 | 983000 | 2014-08-04 | 2014-08-01
2016-03-31 | 2010 | Army Active | 66545 |  | 2010-05-17 | 2014-06-16 | Red Cedar Enterprises, Inc. | W912BV-13-D-0011 | 1581000 | 1870000 | 2015-09-22 | 2016-01-20
2016-03-31 | 2010 | Army Active | 66545 |  | 2010-05-17 | 2012-05-16 | Easky Construction, LLC | W912BV-09-D-2019 | 757000 | 757000 | 2012-10-19 | 2012-09-11
2016-03-31 | 2010 | Army Active | 66545 |  | 2010-05-17 | 2010-09-22 | Anderson Drace Joint Venture | W912BV-10-C-2007 | 11779000 | 12311000 | 2011-11-22 | 2013-06-25
2016-03-31 | 2011 | Army Active | 66595 |  | 2011-09-08 | 2015-01-19 | LBB Kaiserslautern | W912GB-09-C-0014 | 30046000 | 30148000 | 2017-09-28 | 2017-09-28
2016-03-31 | 2012 | Army Active | 66691 |  | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | W9126G-12-C-0015 | 40532000 | 41217000 | 2014-04-24 | 2016-05-31
2016-03-31 | 2012 | Army Active | 66691 |  | 2011-12-24 | 2014-03-04 | Alamo City Constructors, Inc. | W9126G-10-D-0001 | 36000 | 43000 | 2014-06-02 | 2014-06-16
2016-03-31 | 2009 | Army Active | 66725 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7202000 | 7965000 | 2014-06-04 | 2016-02-29
2016-03-31 | 2010 | Army Active | 66726 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757000 | 9039000 | 2014-06-04 | 2016-02-29
2016-03-31 | 2012 | Army Active | 66750 |  | 2012-07-12 | 2013-09-09 | Sovereign Consulting, Inc | W912WJ-10-D-0003 | 1300000 | 1550000 | 2014-09-23 | 2015-10-27
2016-03-31 | 2012 | Army Active | 66750 |  | 2012-07-12 | 2012-09-28 | Meltech/W.M.Schlosser, LLC B, Joint Venture | W912DR-12-C-0020 | 12988000 | 13508000 | 2014-04-15 | 2014-05-20
2016-03-31 | 2011 | Army Active | 66834 |  | 2010-12-01 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 16286000 | 20591000 | 2013-12-18 | 2016-01-15
2016-03-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0019 | 14180000 | 14540000 | 2016-02-04 | 2016-04-07
2016-03-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-12-31 | ALCAN BUILDERS INC. | W911KB-15-C-0001 | 12375000 | 12643000 | 2016-09-06 | 2016-09-06
2016-03-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-04-14 | Arctic-American JV | W911KB-14-C-0008 | 16180000 | 16156000 | 2015-10-15 | 2015-10-15
2016-03-31 | 2014 | Army Active | 67157 |  | 2015-05-13 | 2015-08-18 | Watts Constructors, LLC | W9128A-15-C-0003 | 63500000 | 64100000 | 2017-12-13 | 2017-12-13
2016-03-31 | 2012 | Army Active | 68050 |  | 2012-10-19 | 2016-01-15 | Whiting-Turner Contracting Company | W912DR-16-C-0002 | 30470000 | 30634000 | 2018-02-13 | 2018-02-13
2016-03-31 | 2013 | Army Active | 68530 |  | 2015-05-02 | 2015-09-23 | Solis Constructors, Inc. | W9126G-14-D-0050 | 18828000 | 20186000 | 2017-05-11 | 2017-05-11
2016-03-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2014-06-24 | OBG Engineering GmbH & Co. KG | W912GB-14-D-0019 | 90000 | 90000 | 2014-10-07 | 2014-11-20
2016-03-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | W912GB-11-D-0036 | 7198000 | 8645000 | 2014-06-25 | 2014-12-04
2016-03-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-23 | ECC International LLC | W912GB-13-C-0003 | 87011000 | 90193000 | 2015-09-19 | 2017-01-31
2016-03-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | W912BV-12-C-0003 | 9573000 | 9590000 | 2013-12-16 | 2014-06-27
2016-03-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 5118000 | 5118000 | 2013-09-13 | 2016-01-31
2016-03-31 | 2012 | Army Active | 69286 |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008000 | 8749000 | 2013-09-13 | 2016-01-31
2016-03-31 | 2012 | Army Active | 69489 |  | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772000 | 58632000 | 2015-05-27 | 2016-02-13
2016-03-31 | 2015 | Army Active | 69649 |  | 2015-08-13 | 2015-09-28 | Odyssey International, Inc | W912DR-15-C-0038 | 14675000 | 14675000 | 2017-03-26 | 2017-03-05
2016-03-31 | 2012 | Army Active | 69828 |  | 2013-07-16 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 8830000 | 8857000 | 2016-01-04 | 2016-07-15
2016-03-31 | 2012 | Army Active | 69834 |  | 2012-05-01 | 2014-01-07 | Law Company, Inc. | W912DQ-14-C-4003 | 20079000 | 20769000 | 2015-07-31 | 2016-02-08
2016-03-31 | 2012 | Army Active | 69834 |  | 2012-05-01 | 2012-11-01 | Arch Insurance Company | W912DQ-11-D-4011 | 5933000 | 6086000 | 2014-03-16 | 2015-03-16
2016-03-31 | 2012 | Army Active | 69835 |  | 2014-08-25 | 2014-12-05 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 30589000 | 31980000 | 2016-02-29 | 2016-04-04
2016-03-31 | 2013 | Army Active | 71120 |  | 2013-03-08 | 2013-09-04 | PENTACON, LLC | W912DY-12-D-0030 | 21912000 | 22175000 | 2015-04-10 | 2016-04-19
2016-03-31 | 2014 | Army Active | 71221 |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542000 | 13650000 | 2016-02-18 | 2016-06-13
2016-03-31 | 2010 | Army Active | 71421 |  | 2010-08-01 | 2015-01-06 | LBB Niederlassung Idar-Oberstein | W912GB-10-C-0042 | 18945000 | 17470000 | 2017-04-23 | 2017-06-22
2016-03-31 | 2011 | Army Active | 71422 |  | 2011-07-18 | 2011-09-14 | LBB Niederlassung Idar-Oberstein | W912GB-09-C-0007 | 34935000 | 31454000 | 2015-09-24 | 2018-07-27
2016-03-31 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2013-09-27 | Contrack Watts, Inc. | W912ER-13-C-0032 | 49413000 | 56257000 | 2015-03-25 | 2015-12-31
2016-03-31 | 2010 | Army Active | 71485 |  | 2013-11-06 | 2014-04-03 | Contrack Watts, Inc. | W912ER-14-C-0011 | 6749000 | 6749000 | 2015-10-30 | 2015-12-08
2016-03-31 | 2010 | Army Active | 71488 |  | 2011-10-11 | 2014-08-30 | Inglett & Stubbs, International LTD | W5J9JE-14-P-0044 | 56000 | 56000 | 2014-09-14 | 2014-09-12
2016-03-31 | 2010 | Army Active | 71488 |  | 2011-10-11 | 2011-12-14 | Ch2m Hill-Yuksel Joint Venture | W912ER-11-D-0008 | 39962000 | 46779000 | 2013-07-09 | 2015-10-01
2016-03-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-19 | Zieson Construction Co. | W912DQ-14-D-4000 | 4796000 | 4937000 | 2016-01-29 | 2016-07-02
2016-03-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777000 | 52173000 | 2016-08-04 | 2016-11-17
2016-03-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-18 | Zieson Construction Company, LLC | W912DQ-15-C-4004 | 14313000 | 14934000 | 2016-07-22 | 2016-09-24
2016-03-31 | 2011 | Army Active | 71583 |  | 2011-04-28 | 2015-09-11 | Turner Strategic Technologies, LLC | W912HN-14-D-0008 | 34000 | 34000 | 2015-12-21 | 2015-12-16
2016-03-31 | 2011 | Army Active | 71583 |  | 2011-04-28 | 2011-09-15 | Better Built Construction Services, Inc. | W912HN-10-D-0053 | 4233000 | 4309000 | 2013-03-05 | 2013-04-01
2016-03-31 | 2011 | Army Active | 71583 |  | 2011-04-28 | 2011-06-23 | Q.B.S.Incorporated | W912HN-08-D-0038 | 13186000 | 12984000 | 2013-05-20 | 2013-10-31
2016-03-31 | 2011 | Army Active | 71639 |  | 2010-12-16 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 11652000 | 12179000 | 2013-11-11 | 2014-05-05
2016-03-31 | 2011 | Army Active | 71639 |  | 2010-12-16 | 2013-09-30 | Bristol General Contractors, LLC | W9126G-13-C-0061 | 15175000 | 15298000 | 2015-01-30 | 2016-03-30
2016-03-31 | 2011 | Army Active | 71639 |  | 2010-12-16 | 2011-06-01 | Sundt Construction Inc | W9126G-09-D-0004 | 6608000 | 6783000 | 2013-01-03 | 2012-11-01
2016-03-31 | 2013 | Army Active | 71675 |  | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751000 | 45019000 | 2016-01-15 | 2017-03-08
2016-03-31 | 2012 | Army Active | 71682 |  | 2011-12-19 | 2013-12-04 | Solis Constructors, Inc | W9126G-14-C-0006 | 5786000 | 6872000 | 2015-01-25 | 2016-02-26
2016-03-31 | 2012 | Army Active | 71682 |  | 2011-12-19 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3844000 | 896000 | 2014-02-15 | 2013-08-13
2016-03-31 | 2012 | Army Active | 71682 |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 9669000 | 10202000 | 2013-12-14 | 2016-04-22
2016-03-31 | 2012 | Army Active | 72650 |  | 2011-11-10 | 2012-02-27 | Hanmi C&E Co., LTD. | W912UM-11-D-0007 | 64000 | 4000 | 2015-10-31 | 2014-02-21
2016-03-31 | 2012 | Army Active | 72650 |  | 2011-11-10 | 2012-02-24 | Samsung C&T Corporation | W912UM-12-C-0012 | 27593000 | 28895000 | 2015-12-05 | 2015-11-25
2016-03-31 | 2011 | Army Active | 72854 |  | 2011-05-02 | 2011-09-28 | Innovative Technical Solutions, Inc. | W9126G-08-D-0085 | 8894000 | 11287000 | 2013-04-04 | 2013-12-20
2016-03-31 | 2011 | Army Active | 72854 |  | 2011-05-02 | 2014-09-26 | Wm. Dickson Company | W912DW-14-C-0028 | 1628000 | 2411000 | 2015-10-24 | 2015-10-19
2016-03-31 | 2011 | Army Active | 72854 |  | 2011-05-02 | 2013-01-22 | Garco Construction, Inc. | W912DW-13-C-0020 | 36247000 | 40781000 | 2014-08-07 | 2014-12-15
2016-03-31 | 2011 | Army Active | 72854 |  | 2011-05-02 | 2014-04-30 | Maanilaq Services LLC | W912DW-14-C-0011 | 3373000 | 3366000 | 2014-10-17 | 2014-11-21
2016-03-31 | 2013 | Army Active | 73008 |  | 2013-03-22 | 2013-08-15 | Caddell Construction CO. (DE), LLC | W912HN-10-D-0044 | 20726000 | 21186000 | 2015-03-01 | 2015-12-01
2016-03-31 | 2015 | Army Active | 73272 |  | 2015-07-23 | 2015-09-28 | Joint forces Construction, LLC | W91236-15-C-0054 | 6350000 | 6350000 | 2016-10-20 | 2016-10-20
2016-03-31 | 2015 | Army Active | 73542 |  | 2015-01-23 | 2015-08-27 | Walsh Federal JV | W912QR-15-C-0024 | 17724000 | 17763000 | 2017-04-26 | 2017-05-11
2016-03-31 | 2014 | Army Active | 74638 |  | 2013-11-07 | 2015-04-02 | SGS, LLC | W9126G-15-C-0091 | 13978000 | 13985000 | 2017-01-02 | 2017-01-30
2016-03-31 | 2011 | Army Active | 74757 |  | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | W912QR-12-C-0050 | 1763000 | 3083000 | 2013-08-01 | 2015-12-04
2016-03-31 | 2014 | Army Active | 74861 |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862000 | 27715000 | 2016-08-09 | 2016-09-19
2016-03-31 | 2014 | Army Active | 75019 |  | 2014-06-26 | 2014-11-06 | Zieson Construction Company, LLC | W912DQ-15-C-4000 | 3497000 | 3746000 | 2015-12-01 | 2016-02-25
2016-03-31 | 2013 | Army Active | 75165 |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77477000 | 80362000 | 2016-03-02 | 2016-10-19
2016-03-31 | 2015 | Army Active | 75536 |  | 2015-05-17 | 2015-09-30 | Atherton Construction, LLC | W912QR-15-C-0040 | 18708000 | 18708000 | 2018-06-06 | 2018-06-06
2016-03-31 | 2014 | Army Active | 76024 |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630000 | 16098000 | 2016-02-24 | 2016-08-27
2016-03-31 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072000 | 3135000 | 2015-11-10 | 2016-07-07
2016-03-31 | 2015 | Army Active | 76087 |  | 2015-06-01 | 2015-09-30 | GEMS Environmental Management Services | W91238-15-D-0014 | 4860000 | 4860000 | 2017-03-31 | 2017-03-31
2016-03-31 | 2013 | Army Active | 76091 |  | 2014-05-15 | 2014-09-18 | Federal Solutions Group | W91238-14-C-0051 | 3212000 | 3234000 | 2015-11-12 | 2016-02-23
2016-03-31 | 2013 | Army Active | 76196 |  | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25853000 | 28855000 | 2015-06-09 | 2016-11-02
2016-03-31 | 2013 | Army Active | 76586 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717000 | 32896000 | 2015-09-01 | 2016-11-10
2016-03-31 | 2013 | Army Active | 76587 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410000 | 41633000 | 2015-09-01 | 2016-11-10
2016-03-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC | W911KB-14-C-0005 | 9525000 | 10037000 | 2015-10-16 | 2016-04-01
2016-03-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-08 | ANCOR, INC. | W911KB-14-C-0003 | 2651000 | 3348000 | 2014-10-23 | 2015-08-14
2016-03-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-08 | C.I. Contractors INC. | W911KB-14-C-0010 | 5007000 | 6575000 | 2015-04-17 | 2016-07-30
2016-03-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25547000 | 25832000 | 2016-03-21 | 2016-09-29
2016-03-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6360000 | 6954000 | 2015-08-21 | 2015-10-09
2016-03-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | W9126G-08-D-0044 | 24162000 | 24502000 | 2013-12-31 | 2014-02-18
2016-03-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | W912DW-12-C-0051 | 12950000 | 13975000 | 2014-05-23 | 2014-10-14
2016-03-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2014-04-08 | Glen/Mar Construction, Inc. | W912DW-14-C-0009 | 4771000 | 5372000 | 2015-05-21 | 2016-04-01
2016-03-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-04-09 | Walsh Group Ventures | W912DW-15-C-0002 | 11319000 | 11510000 | 2017-07-06 | 2017-07-06
2016-03-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-07-09 | Vet Industrial, Inc. | W912DW-15-C-0007 | 11893000 | 12422000 | 2016-08-24 | 2016-12-07
2016-03-31 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 23706000 | 23706000 | 2017-07-06 | 2017-07-06
2016-03-31 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2014-08-26 | Archer Western Federal JV | W912DW-14-C-0023 | 36998000 | 38022000 | 2016-03-16 | 2016-03-16
2016-03-31 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2014-09-03 | The Renew Group, Inc. | W912DW-14-C-0017 | 1106000 | 1124000 | 2015-04-22 | 2015-09-04
2016-03-31 | 2013 | Army Active | 76903 |  | 2012-11-26 | 2014-05-13 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749000 | 69749000 | 2017-01-13 | 2017-04-13
2016-03-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 | 5379000 | 4709000 | 2013-06-21 | 2014-05-13
2016-03-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3750000 | 1013000 | 2014-02-15 | 2013-08-13
2016-03-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7473000 | 8035000 | 2013-12-14 | 2016-04-22
2016-03-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-08-28 | Medvolt, LLC | W9128F-14-C-0054 | 13195000 | 13954000 | 2016-03-31 | 2016-05-29
2016-03-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165000 | 17730000 | 2016-02-12 | 2016-07-18
2016-03-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56721000 | 59250000 | 2016-08-22 | 2016-09-13
2016-03-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-07-16 | SEK JV | W9128F-13-D-0015 | 3133000 | 3546000 | 2015-02-14 | 2015-07-07
2016-03-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | Hartland/Mass JV LLC | W9128F-13-D-0014 | 3339000 | 3566000 | 2015-10-20 | 2016-01-05
2016-03-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | John Bowman, Inc. | W9128F-13-D-0013 | 2288000 | 2329000 | 2015-10-07 | 2015-12-17
2016-03-31 | 2015 | Army Active | 77305 |  | 2015-04-15 | 2015-05-28 | Francisco Semsch, Architect, Inc. | W9128F-15-C-0010 | 3848000 | 3848000 | 2016-06-15 | 2016-06-15
2016-03-31 | 2012 | Army Active | 77319 |  | 2012-04-06 | 2016-01-27 | Betance Enterprises, Inc. | W9128F-16-D-0003 | 95000 | 95000 | 2016-06-11 | 2016-06-11
2016-03-31 | 2012 | Army Active | 77319 |  | 2012-04-06 | 2012-08-09 | Hartland/Mass JV, LLC | W9128F-12-D-0040 | 3212000 | 3287000 | 2013-09-06 | 2014-03-21
2016-03-31 | 2012 | Army Active | 77319 |  | 2012-04-06 | 2012-08-10 | Loyd Contracting Co., Inc. | W9128F-12-C-0032 | 18222000 | 19064000 | 2013-09-07 | 2014-06-17
2016-03-31 | 2012 | Army Active | 77319 |  | 2012-04-06 | 2012-08-13 | Komada, LLC | W9128F-12-C-0051 | 3833000 | 4156000 | 2013-09-05 | 2013-11-01
2016-03-31 | 2012 | Army Active | 77319 |  | 2012-04-06 | 2012-09-19 | Komada, LLC | W9128F-12-C-0095 | 6525000 | 6333000 | 2013-10-10 | 2013-12-19
2016-03-31 | 2014 | Army Active | 77405 |  | 2014-06-09 | 2014-06-19 | Blackhorse Worldwide LLC | W9128F-13-D-0016 | 4214000 | 4715000 | 2015-07-22 | 2016-01-14
2016-03-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 891000 | 888000 | 2016-08-22 | 2016-09-13
2016-03-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2015-01-16 | Agile Infrastructure Services, L.L.C. | W9128F-15-C-0002 | 2843000 | 2902000 | 2016-02-11 | 2016-05-01
2016-03-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585000 | 52162000 | 2016-05-28 | 2016-09-26
2016-03-31 | 2013 | Army Active | 77419 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 10400000 | 10421000 | 2016-12-26 | 2017-01-24
2016-03-31 | 2014 | Army Active | 77539 |  | 2014-07-17 | 2014-09-26 | Barlovento, LLC | W91278-10-D-0072 | 4711000 | 4842000 | 2015-12-17 | 2016-02-28
2016-03-31 | 2014 | Army Active | 77885 |  | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9833000 | 12144000 | 2015-07-01 | 2016-07-06
2016-03-31 | 2014 | Army Active | 77980 |  | 2014-08-12 | 2014-09-16 | FutureNet Group, Inc. | W912QR-09-D-0050 | 1636000 | 1906000 | 2015-08-20 | 2015-11-24
2016-03-31 | 2013 | Army Active | 78054 |  | 2014-07-08 | 2015-03-17 | Akima Construction Services, LLC | W912DR-15-C-0013 | 3358000 | 10299000 | 2016-09-24 | 2017-02-21
2016-03-31 | 2014 | Army Active | 78196 |  | 2015-08-07 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 20099000 | 20099000 | 2017-07-06 | 2017-07-06
2016-03-31 | 2012 | Army Active | 78475 |  | 2013-05-22 | 2014-11-18 | Klebl GmbH | W912GB-15-C-0003 | 14632000 | 14863000 | 2016-09-27 | 2016-09-27
2016-03-31 | 2012 | Army Active | 78505 |  | 2012-04-06 | 2013-08-07 | Staatliches Hochbauamt Amberg | W912GB-11-C-0027 | 13549000 | 13857000 | 2015-09-14 | 2016-02-17
2016-03-31 | 2012 | Army Active | 78506 |  | 2012-04-10 | 2013-09-30 | Bauamt Amberg-Sulzbach | W912GB-11-C-0016 | 12815000 | 12953000 | 2015-10-27 | 2015-10-29
2016-03-31 | 2014 | Army Active | 78778 |  | 2013-12-24 | 2014-06-18 | TJC Engineering | W912QR-14-C-0018 | 4275000 | 4371000 | 2015-08-21 | 2016-02-22
2016-03-31 | 2012 | Army Active | 78841 |  | 2012-05-04 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0018 | 20429000 | 21316000 | 2018-10-29 | 2016-04-21
2016-03-31 | 2012 | Army Active | 78841 |  | 2012-05-04 | 2013-05-09 | WAYSS & FREYTAG INGENIEURBAU AG | W912GB-12-D-0055 | 1168000 | 1590000 | 2014-09-05 | 2014-10-13
2016-03-31 | 2012 | Army Active | 79097 |  | 2012-05-04 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0017 | 17917000 | 18916000 | 2018-04-02 | 2016-01-22
2016-03-31 | 2014 | Army Active | 79618 |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440000 | 9385000 | 2016-02-11 | 2016-09-23
2016-03-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-08-30 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129000 | 12309000 | 2014-11-30 | 2016-07-31
2016-03-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2013-03-19 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. | W912GB-12-D-0035 | 199000 | 199000 | 2013-10-16 | 2013-10-17
2016-03-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-07-05 | EMTA CONSTRUCTION CO. INC. | W912GB-10-D-0020 | 320000 | 320000 | 2012-11-22 | 2012-11-22
2016-03-31 | 2012 | Army Active | 79846 |  | 2013-07-03 | 2014-09-28 | Kiewit Federal Group, Inc. | W912DR-11-D-0021 | 3195000 | 3195000 | 2015-12-01 | 2016-04-07
2016-03-31 | 2013 | Army Active | 79933 |  | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 167910000 | 2016-08-30 | 2016-11-15
2016-03-31 | 2014 | Army Active | 79933 | 81186 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 167910000 | 2016-08-30 | 2016-11-15
2016-03-31 | 2015 | Army Active | 79933 | 81187 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 167910000 | 2016-08-30 | 2016-11-15
2016-03-31 | 2013 | Army Active | 80112 |  | 2014-12-02 | 2015-04-23 | Sauer Inc. d/b/a Sauer Southeast | W91278-12-D-0039 | 10965000 | 11238000 | 2016-07-19 | 2016-09-11
2016-03-31 | 2013 | Army Active | 80113 |  | 2013-03-12 | 2013-08-30 | Carntribe-Clement 8aJV #1, LLC | W912HN-11-D-0028 | 5994000 | 5981000 | 2014-11-27 | 2015-02-05
2016-03-31 | 2013 | Army Active | 80113 |  | 2013-03-12 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 591000 | 700000 | 2016-01-04 | 2016-05-27
2016-03-31 | 2013 | Army Active | 80113 |  | 2013-03-12 | 2013-08-15 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491000 | 11454000 | 2015-05-30 | 2015-07-20
2016-03-31 | 2012 | Army Active | 80231 |  | 2013-06-03 | 2014-09-28 | East Coast Utility Contractors | W912DR-14-C-0041 | 1484000 | 1643000 | 2015-09-25 | 2017-03-18
2016-03-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-11-25 | Upstate Construction Services, Inc. | W912DS-09-D-0005 | 17287000 | 17823000 | 2015-12-02 | 2016-05-30
2016-03-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 39587000 | 42379000 | 2015-06-17 | 2016-01-25
2016-03-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | Black Horse Group LLC | W912DS-09-D-0004 | 21578000 | 24667000 | 2015-06-22 | 2017-03-01
2016-03-31 | 2013 | Army Active | 80317 |  | 2013-08-14 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1791000 | 1560000 | 2014-09-10 | 2016-03-15
2016-03-31 | 2014 | Army Active | 80433 |  | 2015-06-11 | 2015-09-22 | K.L. House Construction Co. | W9128F-15-C-0028 | 3423000 | 3423000 | 2016-10-26 | 2016-10-26
2016-03-31 | 2014 | Army Active | 80919 |  | 2014-08-12 | 2014-09-29 | Glen/Mar Construction, Inc. | W912DW-14-C-0029 | 1545000 | 1779000 | 2016-02-13 | 2016-02-13
2016-03-31 | 2014 | Army Active | 80992 |  | 2015-02-06 | 2015-03-24 | Red One Construction, LLC | W9128A-15-C-0002 | 1696000 | 1696000 | 2016-10-20 | 2016-10-20
2016-03-31 | 2013 | Army Active | 81106 |  | 2013-06-11 | 2013-09-27 | Zumwalt Construction, Inc. | W91238-11-D-0026 | 1882000 | 2491000 | 2014-12-17 | 2016-02-09
2016-03-31 | 2014 | Army Active | 81155 |  | 2014-05-02 | 2014-12-05 | SGS, LLC | W9126G-15-C-0005 | 32968000 | 32985000 | 2016-04-11 | 2016-04-27
2016-03-31 | 2015 | Army Active | 81230 |  | 2015-05-08 | 2015-07-27 | Yojin Construction & Engineering Co., Ltd. | W912UM-15-C-0015 | 43753000 | 43911000 | 2018-04-28 | 2018-04-28
2016-03-31 | 2015 | Army Active | 81242 |  | 2015-08-19 | 2015-09-27 | BIC-SCC JV, LLC | W91278-13-D-0003 | 1740000 | 1740000 | 2016-10-27 | 2016-10-27
2016-03-31 | 2015 | Army Active | 81349 |  | 2015-02-20 | 2015-06-04 | Upstate Construction Services, Inc. | W912DS-15-C-0008 | 19408000 | 19896000 | 2016-12-18 | 2017-01-11
2016-03-31 | 2015 | Army Active | 81357 |  | 2015-04-13 | 2015-07-07 | David Boland, Inc. | W9128F-15-C-0017 | 26149000 | 26194000 | 2017-01-18 | 2017-01-18
2016-03-31 | 2015 | Army Active | 81372 |  | 2015-03-31 | 2015-10-29 | COX CONSTRUCTION CO | W912PL-16-C-0002 | 26117000 | 26117000 | 2017-12-16 | 2017-12-16
2016-03-31 | 2014 | Army Active | 81424 |  | 2015-07-21 | 2015-09-30 | Southeast Cherokee Construction,Inc. | W91278-10-D-0064 | 3562000 | 3562000 | 2017-02-02 | 2017-02-02
2016-03-31 | 2013 | Army Active | 81462 |  | 2014-08-21 | 2014-09-30 | Nan Inc | W9128A-12-D-0012 | 1556000 | 1664000 | 2015-10-23 | 2016-04-22
2016-03-31 | 2014 | Army Active | 82394 |  | 2015-03-04 | 2015-12-31 | Red Cedar Enterprises, Inc. | W912BV-13-D-0011 | 2690000 | 2690000 | 2017-02-12 | 2017-02-12
2016-03-31 | 2014 | Army Active | 85260 |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1725000 | 1771000 | 2015-11-05 | 2016-01-13
2016-03-31 | 2014 | Army Active | 85817 |  | 2015-09-22 | 2015-11-18 | LBB Kaiserslautern | W912GB-14-C-0020 | 1506000 | 1506000 | 2016-08-01 | 2016-08-01
2016-03-31 | 2014 | Army Active | 86033 |  | 2015-05-13 | 2015-09-24 | Engineering Design Technologies, Inc. | W9126G-15-D-0003 | 2965000 | 2965000 | 2016-09-08 | 2016-09-08
2016-04-08 | 2013 | Army National Guard | 010278 |  | 2013-08-01 | 2013-08-27 | Hurst Construction, LLC | AC-13-C-0052-S | 5223000 | 5437000 | 2014-11-11 | 2015-06-08 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 011007 |  | 2013-09-24 | 2013-09-30 | Butler Construction Company, LLC. | AC-13-C-0051-S | 1920000 | 1904000 | 2014-10-01 | 2014-12-19
2016-04-08 | 2014 | Army National Guard | 011014 |  | 2014-08-14 | 2014-08-22 | Carmon Construction, Inc. | AC-14-C-0005-S | 4000000 | 3785000 | 2015-12-10 | 2015-12-10
2016-04-08 | 2012 | Army National Guard | 040294 |  | 2012-02-15 | 2012-08-16 | Haydon Building Corporation-Tem | M11-0045 | 17771000 | 17655000 | 2013-10-16 | 2014-01-31 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 040669 |  | 2013-09-23 | 2014-04-04 | Ludvik Electric | M13-0037 | 2000000 | 1833000 | 2014-10-31 | 2014-10-31
2016-04-08 | 2014 | Army National Guard | 050182 |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-C -0003 | 12270000 | 16758000 | 2016-12-01 | 2016-12-01
2016-04-08 | 2010 | Army National Guard | 060115 |  | 2010-09-21 | 2010-09-24 | Silva Barnhart Joint Venture | W912LA-10-C-0009 | 30711000 | 23378000 | 2012-02-06 | 2015-01-30 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2016-04-08 | 2012 | Army National Guard | 060170 |  | 2012-06-19 | 2012-06-26 | Goshawk LLC | W912LA-12-C-0003 | 7985000 | 7482000 | 2013-10-14 | 2014-06-06 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 060413 |  | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793000 | 30766000 | 2014-10-01 | 2016-02-29 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 ($1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)}
2016-04-08 | 2011 | Army National Guard | 060429 |  | 2011-05-12 | 2011-09-20 | Cox Construction Company | W912LA-11-R-0005 | 12379000 | 11525000 | 2012-06-29 | 2013-09-27 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2016-04-08 | 2012 | Army National Guard | 060432 |  | 2012-06-27 | 2012-09-28 | WEP Enterprises | W912LA-11-D-0024 | 1400000 | 1131000 | 2013-09-20 | 2014-10-30 | FY07 Congressionally Directed, Used FY10 funds
2016-04-08 | 2012 | Army National Guard | 060438 |  | 2012-06-04 | 2012-07-20 | Red Mountain LLC | W912LA-12-C-0002 | 6114000 | 5257000 | 2013-10-28 | 2015-06-02 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,835)
2016-04-08 | 2013 | Army National Guard | 090043 |  | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951000 | 31486000 | 2015-10-01 | 2016-08-16 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | 090088 |  | 2015-08-27 | 2015-09-19 | K-Con, Inc | BI-Q-670-DB | 1363000 | 1269000 | 2016-09-26 | 2016-11-30
2016-04-08 | 2013 | Army National Guard | 100010 |  | 2013-06-21 | 2013-07-25 | EDIS Company | 40325 | 5319000 | 5322000 | 2014-09-23 | 2014-12-04 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), Construction is finish, project completion is pending all closeout documentation
2016-04-08 | 2013 | Army National Guard | 120102 |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) | W911YN-11-2-2002 | 19950000 | 22681000 | 2015-07-26 | 2016-02-24 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) & Formal Reprogramming $5,482 funds from FY12 project savings {PNs: 060009 ($4,452) & 240187 ($1,030)}
2016-04-08 | 2014 | Army National Guard | 120195 |  | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | W911YN-13-2-2004 | 5700000 | 5300000 | 2016-04-05 | 2016-04-05
2016-04-08 | 2013 | Army National Guard | 120228 |  | 2013-09-05 | 2013-09-10 | Halfacre Construction Company | W911YN-13-2-2002 | 1939000 | 1920000 | 2015-05-16 | 2015-09-23 | Awaiting final pay request and close-out documentation
2016-04-08 | 2012 | Army National Guard | 130063 |  | 2012-01-12 | 2012-09-11 | J&S Construction Company, Inc. | W912JM-12-R-0011 | 19255000 | 20570000 | 2013-10-28 | 2016-01-22 | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2016-04-08 | 2012 | Army National Guard | 130068 |  | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC | 41100-044-0000082512 | 14457000 | 14123000 | 2014-03-14 | 2014-10-14 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 130120 |  | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. | 41100-044-0000082224 | 10991000 | 11239000 | 2013-10-28 | 2014-11-24 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | 130123 |  | 2011-05-17 | 2012-04-17 | TEPA | W912JM-10-D-0018 | 10363000 | 10349000 | 2013-09-30 | 2014-04-30 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | 130127 |  | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 41100-033-0000078159 | 16941000 | 16726000 | 2012-11-16 | 2012-11-16 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 140040 |  | 2013-04-02 | 2013-09-25 | P&S Construction, Inc. | N40192-10-D-2804 | 8221000 | 8089000 | 2015-04-29 | 2015-11-20 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2010 | Army National Guard | 140300 |  | 2009-11-24 | 2010-03-10 | DCK Pacific, LLC. | N40192-10-C-1335 | 20766000 | 20797000 | 2012-01-07 | 2012-11-16 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2016-04-08 | 2013 | Army National Guard | 150023 |  | 2013-10-25 | 2014-09-26 | Watts Constructors, LLC | W912J6-14-C-0003 | 32625000 | 33695000 | 2016-11-01 | 2016-11-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2016-04-08 | 2011 | Army National Guard | 160093 |  | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | W912J7-11-C-0002 | 17333000 | 13811000 | 2013-02-28 | 2014-04-15 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2016-04-08 | 2013 | Army National Guard | 160100 |  | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692000 | 38193000 | 2014-08-01 | 2016-03-09 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | 170033 |  | 2014-06-11 | 2014-06-27 | George Sollitt Construction Co. | W91SMC-14-2-2004-10001 | 14000000 | 16000000 | 2016-10-01 | 2017-03-12
2016-04-08 | 2014 | Army National Guard | 170127 |  | 2014-06-11 | 2014-06-27 | George Sollitt Construction Co. | W91SMC-14-2-2003-10001 | 28000000 | 30000000 | 2016-10-01 | 2017-03-12
2016-04-08 | 2013 | Army National Guard | 180106 |  | 2013-09-23 | 2013-09-24 | Gamong Construction | MDI-SAB-14-C-0002 | 8705000 | 8545000 | 2014-12-25 | 2015-11-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 180144 |  | 2013-09-19 | 2013-09-20 | Ziolkowski Construction | MDI-SAB-14-C-0001 | 20311000 | 22122000 | 2015-08-23 | 2015-11-07 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 200102 |  | 2013-05-21 | 2013-06-14 | Senne & Co | W912JC-13-C-1307 | 9188000 | 8799000 | 2014-10-01 | 2014-07-04 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 200127 |  | 2013-09-16 | 2013-09-24 | Harbin Construction | W912JC-12-D-5308 | 1440000 | 1627000 | 2014-06-13 | 2015-04-02
2016-04-08 | 2013 | Army National Guard | 210001 |  | 2013-05-17 | 2013-06-04 | DW Wilburn, Inc. | CT2 1300000269 | 24778000 | 27053000 | 2014-10-01 | 2015-08-16 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 220241 |  | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300000 | 8937000 | 2016-10-30 | 2016-10-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353)
2016-04-08 | 2012 | Army National Guard | 230046 |  | 2012-04-05 | 2012-09-26 | ITSI Gibane | W912JD-12-C-0003 | 14390000 | 14919000 | 2014-07-11 | 2016-03-30 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2015 | Army National Guard | 230113 |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113-D | 30616000 | 31449000 | 2017-08-03 | 2017-08-03 | Using State procedures the contract number is the same as the project number plus -D to delineate Construction
2016-04-08 | 2012 | Army National Guard | 240017 |  | 2012-08-29 | 2012-09-11 | The Whiting-Turner Contracting Company | 001B3400152 | 15771000 | 12230000 | 2014-09-22 | 2016-01-25 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2015 | Army National Guard | 240165 |  | 2015-08-17 | 2015-09-23 | Harkins Builders | 001B6400136 | 12400000 | 12406000 | 2017-10-29 | 2017-10-29
2016-04-08 | 2011 | Army National Guard | 240186 |  | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | N40080-10-D-0498 | 5480000 | 5592000 | 2013-06-15 | 2014-11-21 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 240187 |  | 2012-07-23 | 2012-09-11 | Harkins Builders | 001B3400154 | 10296000 | 8254000 | 2014-09-22 | 2015-03-20 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 240193 |  | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 001B3400155 | 9000000 | 10084000 | 2014-09-22 | 2016-06-01 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 240194 |  | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 1920000 | 1829000 | 2014-09-22 | 2016-03-29
2016-04-08 | 2013 | Army National Guard | 250065 |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279000 | 21242000 | 2015-07-30 | 2015-10-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | 250095 |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000000 | 20559000 | 2016-11-01 | 2016-11-01
2016-04-08 | 2012 | Army National Guard | 250135 |  | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc. | MIL1001-DC1 | 8986000 | 9630000 | 2013-10-28 | 2014-10-28 | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2016-04-08 | 2013 | Army National Guard | 250196 |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District | W912W3-11-D-0069 | 2000000 | 1838000 | 2013-12-01 | 2013-12-01
2016-04-08 | 2014 | Army National Guard | 260051 |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000000 | 17645000 | 2016-10-01 | 2016-10-01
2016-04-08 | 2014 | Army National Guard | 270014 |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000000 | 18331000 | 2016-04-15 | 2016-04-24
2016-04-08 | 2013 | Army National Guard | 270236 |  | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. | 67879 | 12783000 | 13806000 | 2015-10-01 | 2016-06-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 270238 |  | 2013-08-08 | 2013-08-14 | LS Black Constructors | W912LM-13-C-0007 | 16443000 | 17530000 | 2015-10-15 | 2016-12-28 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | 280272 |  | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB22-14-C-0003-S | 4500000 | 4718000 | 2016-04-30 | 2016-09-07
2016-04-08 | 2014 | Army National Guard | 280423 |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000000 | 2613000 | 2016-11-30 | 2016-11-30
2016-04-08 | 2013 | Army National Guard | 290176 |  | 2013-07-26 | 2013-08-01 | KCI Construction Company | T1203-01 | 14906000 | 15890000 | 2015-01-30 | 2015-08-01 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011); withholding money for site work & LEED cert
2016-04-08 | 2014 | Army National Guard | 290191 |  | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01 | 6834000 | 7826000 | 2015-06-26 | 2016-05-09 | Taken beneficial occupancy of building; witholding money for site work & LEED cert / contracted lagoon work separtely to meet State code, completion 9May16
2016-04-08 | 2014 | Army National Guard | 290221 |  | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 4399000 | 4494000 | 2015-10-06 | 2015-10-06 | Final Closeout documents; As-Builts; (New code stating Optical Flame Detectors not yet required. We have proposal but are checking estimates)
2016-04-08 | 2015 | Army National Guard | 300128 |  | 2015-04-14 | 2015-04-20 | Swank Enterprises - Valier | W9124V-08-2-2001 | 38000000 | 27661000 | 2017-05-31 | 2017-05-13
2016-04-08 | 2015 | Army National Guard | 300216 |  | 2015-09-03 | 2015-09-19 | Golden Eagle Construction INC | W9124V-15-2-2001 | 2600000 | 2687000 | 2017-06-24 | 2016-08-22 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY11, PN: 160093)
2016-04-08 | 2012 | Army National Guard | 320141 |  | 2015-10-01 | 2015-10-19 | Senate Builders & Const Manager | SPWB-09-C-14-109740 | 2000000 | 684000 | 2017-06-23 | 2017-07-15 | FY10 Congressionally Directed
2016-04-08 | 2010 | Army National Guard | 320143 |  | 2010-09-26 | 2010-09-27 | The Penta Building Company | SPWB-09-C-14-5681 | 25807000 | 19910000 | 2012-01-23 | 2013-04-19 | PL 112-25 (Budget Control Act, 2011), (Closeout procedures are in progress) Working one warranty item prior to closeout
2016-04-08 | 2011 | Army National Guard | 330034 |  | 2011-05-09 | 2011-08-25 | Eckman Construction Company, Inc. | W912TF-09-2-2001 | 20742000 | 19809000 | 2013-06-01 | 2016-04-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | 330035 |  | 2011-05-09 | 2011-08-26 | Eckman Construction Company, Inc. | W912TF-09-2-2002 | 14880000 | 14005000 | 2013-06-01 | 2016-04-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 330053 |  | 2015-12-07 | 2016-01-19 | JCN Construction Co., Inc. | W912TF-14-D-0502 | 1900000 | 1793000 | 2017-02-15 | 2017-02-15
2016-04-08 | 2013 | Army National Guard | 330057 |  | 2015-07-14 | 2015-08-28 | Meridian Construction | 80731R-B | 1438000 | 1703000 | 2017-06-09 | 2016-10-31
2016-04-08 | 2013 | Army National Guard | 340110 |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885000 | 32462000 | 2016-02-12 | 2016-02-12 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 340115 |  | 2012-02-15 | 2012-09-19 | Senate Builders & Const Manager | W912KN-12-C-0006 | 48795000 | 46289000 | 2014-10-18 | 2015-01-31 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 340130 |  | 2014-09-19 | 2014-09-26 | Rome Management Associates, LLC | W912KN-13-D-0029 | 2228000 | 1535000 | 2015-08-31 | 2016-03-30 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2016-04-08 | 2013 | Army National Guard | 360139 |  | 2015-09-02 | 2015-10-27 | Darland Construction Inc. | 45011C | 23213000 | 17891000 | 2017-12-30 | 2017-12-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | 360161 |  | 2014-09-17 | 2014-09-30 | Design Resources Group Architects, A.I.A, Inc. | 44573 | 34814000 | 34742000 | 2016-05-30 | 2016-11-21 | Formal Reprogramming $3,814 funds from FY11 project savings (PN: 090010)
2016-04-08 | 2013 | Army National Guard | 361103 |  | 2015-09-03 | 2015-09-15 | Arnold Construction Co., Inc. | 44897C | 6700000 | 5824000 | 2016-11-05 | 2016-11-05 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY11, PN: 060429)
2016-04-08 | 2013 | Army National Guard | 380053 |  | 2014-08-18 | 2014-09-24 | Smithco Inc. | AGND14-52 | 1194000 | 2000000 | 2015-10-30 | 2015-12-11
2016-04-08 | 2013 | Army National Guard | 380053 | 87 | 2014-08-18 | 2014-09-24 | Peterson Mechanical, Inc. | AGND14-53 | 468000 |  | 2015-10-30 | 2015-12-11
2016-04-08 | 2013 | Army National Guard | 380053 | 88 | 2014-08-18 | 2014-09-24 | Grotberg Electrical, Inc. | AGND14-54 | 311000 |  | 2015-10-30 | 2015-12-11
2016-04-08 | 2015 | Army National Guard | 380073 |  | 2015-03-31 | 2015-06-15 | Strata Corp. | AGND15-18 | 3811000 | 12568000 | 2017-06-30 | 2017-07-18
2016-04-08 | 2015 | Army National Guard | 380073 | 135 | 2015-03-31 | 2015-06-15 | T.F. Powers Construction Co. | AGND15-19 | 6048000 |  | 2017-06-30 | 2017-07-18
2016-04-08 | 2015 | Army National Guard | 380073 | 136 | 2015-03-31 | 2015-06-15 | Manning Mechanical Inc. | AGND15-20 | 1421000 |  | 2017-06-30 | 2017-07-18
2016-04-08 | 2015 | Army National Guard | 380073 | 137 | 2015-03-31 | 2015-06-15 | Scott's Electric Inc. | AGND15-21 | 844000 |  | 2017-06-30 | 2017-07-18
2016-04-08 | 2014 | Army National Guard | 390292 |  | 2014-04-04 | 2014-09-04 | Rock Industries, Inc. | W91364-13-D-0003 | 5200000 | 5027000 | 2016-07-31 | 2016-07-31 | Awaiting USACE Review of streem cut plan. 45 Day window ends on 26 Feb 16
2016-04-08 | 2013 | Army National Guard | 400066 |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29197000 | 27771000 | 2014-10-01 | 2016-02-22 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2016-04-08 | 2012 | Army National Guard | 400605 |  | 2012-01-12 | 2012-08-16 | Benham Companies, LLC | W90FYQ-09-D-0006-9J01 | 10343000 | 9308000 | 2014-02-19 | 2015-01-16 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 400606 |  | 2012-01-24 | 2012-08-15 | Benham Companies, LLC | W90FYQ-09-D-0006-9J02 | 2995000 | 3161000 | 2014-02-19 | 2014-06-28 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 410026 |  | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 410026D002 | 13800000 | 13190000 | 2013-12-28 | 2014-03-20 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | 420051 |  | 2014-07-09 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 31939000 | 32604000 | 2016-04-22 | 2016-08-10
2016-04-08 | 2009 | Army National Guard | 420511 |  | 2011-08-31 | 2011-09-15 | Lobar Incorporated | DGS 961-20.1 | 4733000 | 5738000 | 2012-10-30 | 2015-12-31 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Site corrections & electrical punch list pending
2016-04-08 | 2013 | Army National Guard | 420533 |  | 2015-07-17 | 2015-09-17 | ImbuTec | W912KC-11-D-0004 | 2400000 | 2637000 | 2016-06-17 | 2016-06-17
2016-04-08 | 2013 | Army National Guard | 420542 |  | 2014-07-22 | 2014-10-24 | Miller Bros. Construction, Inc. | W912KC-14-R-0005 | 1896000 | 1959000 | 2015-11-13 | 2015-12-17 | SIOH all in-house; awaiting NPDES
2016-04-08 | 2014 | Army National Guard | 430070 |  | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600000 | 4418000 | 2015-05-30 | 2016-11-01
2016-04-08 | 2013 | Army National Guard | 430081 |  | 2013-06-27 | 2013-09-26 | RB Construction Group Inc. | W912LR-13-C-0001 | 18294000 | 17879000 | 2015-09-18 | 2016-02-05 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2016-04-08 | 2013 | Army National Guard | 430803 |  | 2015-08-06 | 2015-09-15 | OSSAM Construction, Inc. | NGB70-15-C-0021 | 14218000 | 12823000 | 2017-03-25 | 2017-03-25 | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | 440009 |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 19316000 | 21433000 | 2014-04-17 | 2015-03-31 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project) Working warranty issues
2016-04-08 | 2013 | Army National Guard | 440053 |  | 2014-08-15 | 2015-01-06 | J J Cardosi, Inc | W912LD-11-D-0016 | 1032000 | 1096000 | 2015-11-01 | 2016-04-01 | Contractor delayed. Submittal process ongoing. Construction to start this month.
2016-04-08 | 2014 | Army National Guard | 450131 |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | State Contract # 46000406465 | 13000000 | 12632000 | 2017-04-06 | 2017-07-06 | State Project Number E24-9770-JM
2016-04-08 | 2010 | Army National Guard | 450252 |  | 2010-07-12 | 2010-07-14 | Choate Construction | W912QG-10-C-0005 | 14759000 | 14078000 | 2012-04-25 | 2013-04-23 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2016-04-08 | 2014 | Army National Guard | 450283 |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | State Contract # 46000406370 | 13000000 | 12552000 | 2017-04-06 | 2017-05-06 | State Project Number E24-9764-JM
2016-04-08 | 2010 | Army National Guard | 450353 |  | 2010-09-23 | 2010-09-24 | Hendrick Construction | State Contract # 460114576 | 27936000 | 27304000 | 2012-08-18 | 2013-06-21 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,936)
2016-04-08 | 2012 | Army National Guard | 450403 |  | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. | State Contract # 4600277403 | 4290000 | 4255000 | 2014-01-08 | 2014-04-30 | PL 112-25 (Budget Control Act, 2011), State Project Number E24-9751-CA
2016-04-08 | 2014 | Army National Guard | 480243 |  | 2014-02-25 | 2015-09-28 | USPFO - TX | W912L1-15--0023 | 14270000 | 14785 | 2017-06-09 | 2017-06-09
2016-04-08 | 2013 | Army National Guard | 490076 |  | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 137861 | 14508000 | 15794000 | 2014-10-01 | 2014-11-30 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011), NGB 593
2016-04-08 | 2013 | Army National Guard | 490444 |  | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 137862 | 28772000 | 28414000 | 2014-09-30 | 2015-04-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2016-04-08 | 2013 | Army National Guard | 490803 |  | 2013-11-06 | 2014-07-18 | Keller Construction Inc. | 147589 | 2000000 | 1950000 | 2016-01-26 | 2016-01-26
2016-04-08 | 2015 | Army National Guard | 500036 |  | 2015-03-11 | 2015-04-06 | Spates Construction, Inc. | 0000000028707 | 4268000 | 4458000 | 2015-12-31 | 2016-01-31 | Site corrections & punch list items pending to make final payment April/early May 2016
2016-04-08 | 2016 | Army National Guard | 500079 |  | 2016-02-22 | 2016-03-22 | Spates Construction, Inc. | 00000 | 7900000 | 6280000 | 2017-03-31 | 2017-03-31
2016-04-08 | 2012 | Army National Guard | 510307 |  | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | W912LQ-13-C-0001 | 8316000 | 8875000 | 2014-10-09 | 2015-02-27 | PL 112-25 (Budget Control Act, 2011), 3rd Party investigation underway for roof failure. Modification contract to include further testing has been executed. Contractor to start 10 Mar 16. Target installation underway (PEO-STRI). Some issues with water in comms rooms, which have been addressed. New issues at existing MOUT Site, Ft Pickett (part of CTF Project included upgrade in old site), with roof leaks. Contract in place to repair 1 of 3 [existing} building with leaks.
2016-04-08 | 2010 | Army National Guard | 520014 |  | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. | W9127P-10-C-0001 | 19978000 | 19494000 | 2012-02-20 | 2013-04-23 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2011 | Army National Guard | 520034 |  | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | W9127P-11-C-0005 | 24850000 | 22326000 | 2012-08-20 | 2013-08-01 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 530015 |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | W912DW-13-C-0044 | 33853000 | 31373000 | 2015-08-20 | 2016-03-10 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | 530035 |  | 2014-08-15 | 2014-08-20 | Absher Construction | 2013-295 G(2-1) | 26000000 | 23879000 | 2016-06-30 | 2016-06-30 | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500 - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2016-04-08 | 2013 | Army National Guard | 540075 |  | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734000 | 15111000 | 2015-09-11 | 2015-11-29 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 540085 |  | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | DEK 13002 | 9991000 | 11603000 | 2014-11-12 | 2014-11-12 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2009 | Army National Guard | 540105 |  | 2009-09-24 | 2009-09-25 | The Whiting-Turner Contracting Company | DEFK10003 | 77500000 | 72200000 | 2011-09-28 | 2014-09-30 | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2009 | Army National Guard | 540206 |  | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | DEFK10004 | 4755000 | 4624000 | 2010-08-26 | 2013-03-31 | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2016-04-08 | 2013 | Army National Guard | 550142 |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673000 | 9634000 | 2014-10-01 | 2015-06-15 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2012 | Army National Guard | 550245 |  | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. | NGB-47-12-C-0002 | 4250000 | 3939000 | 2013-05-20 | 2014-05-30 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2016-03-31 | 2014 | Army Reserve | 65277 |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 11895000 | 13191000 | 2015-09-30 | 2016-05-13
2016-03-31 | 2012 | Army Reserve | 67466 |  | 2012-05-16 | 2012-09-18 | Continental Casualty Company | W912QR-12-C-0055 | 16212000 | 16472000 | 2014-03-19 | 2016-12-15
2016-03-31 | 2013 | Army Reserve | 67652 |  | 2014-05-06 | 2015-03-31 | Cox Construction Co. | W912QR-15-C-0007 | 24044000 | 24084000 | 2017-02-12 | 2017-02-12
2016-03-31 | 2013 | Army Reserve | 67659 |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21779000 | 23153000 | 2015-11-04 | 2016-09-30
2016-03-31 | 2015 | Army Reserve | 67661 |  | 2015-12-01 | 2016-03-01 | Structural Associates, Inc. | W912QR-16-C-0009 | 20118000 | 20118000 | 2017-09-22 | 2017-09-22
2016-03-31 | 2014 | Army Reserve | 67663 |  | 2014-08-01 | 2015-08-28 | Sheffield Korte Joint Venture | W912QR-15-C-0027 | 21428000 | 21428000 | 2017-09-06 | 2017-09-06
2016-03-31 | 2012 | Army Reserve | 67691 |  | 2011-11-16 | 2012-05-03 | SCMC, LLC | W912QR-12-C-0025 | 18167000 | 19574000 | 2014-02-21 | 2015-11-30
2016-03-31 | 2013 | Army Reserve | 67705 |  | 2015-02-13 | 2015-09-24 | Korte Construction Company | W912QR-15-C-0035 | 18104000 | 18104000 | 2017-09-07 | 2017-09-07
2016-03-31 | 2012 | Army Reserve | 67713 |  | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | W912QR-12-C-0068 | 13454000 | 15970000 | 2014-07-10 | 2016-03-04
2016-03-31 | 2013 | Army Reserve | 67715 |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31523000 | 32528000 | 2016-02-24 | 2016-06-30
2016-03-31 | 2013 | Army Reserve | 68077 |  | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890000 | 7922000 | 2016-05-30 | 2016-08-26
2016-03-31 | 2011 | Army Reserve | 69421 |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4504000 | 4564000 | 2014-03-21 | 2017-03-31
2016-03-31 | 2010 | Army Reserve | 69461 |  | 2014-02-11 | 2014-07-10 | Carothers Construction, Inc. | W912QR-14-C-0024 | 13543000 | 17621000 | 2015-12-21 | 2016-04-29
2016-03-31 | 2010 | Army Reserve | 69471 |  | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | W912QR-12-C-0022 | 16009000 | 16247000 | 2013-09-24 | 2016-06-17
2016-03-31 | 2011 | Army Reserve | 69562 |  | 2014-10-17 | 2014-11-14 | Crossroads-Sergent Construction JV | W912QR-13-D-0026 | 860000 | 860000 | 2015-10-20 | 2016-05-06
2016-03-31 | 2011 | Army Reserve | 69562 |  | 2014-12-17 | 2015-09-10 | Blueridge General Inc | W912QR-15-C-0030 | 12568000 | 12568000 | 2017-05-10 | 2017-07-10
2016-03-31 | 2014 | Army Reserve | 69669 |  | 2014-01-31 | 2014-06-05 | Ranco Construction, Inc. | W912QR-14-C-0021 | 8783000 | 8872000 | 2015-12-14 | 2016-05-27
2016-03-31 | 2013 | Army Reserve | 71482 |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56039000 | 61897000 | 2016-05-17 | 2016-08-15
2016-03-31 | 2014 | Army Reserve | 71768 |  | 2015-08-20 | 2015-11-04 | Eastern Construction & Electric, Inc. | W912QR-16-C-0003 | 6433000 | 6433000 | 2017-05-12 | 2017-05-12
2016-03-31 | 2014 | Army Reserve | 71769 |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653000 | 4661000 | 2016-04-09 | 2016-06-30
2016-03-31 | 2014 | Army Reserve | 71900 |  | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129000 | 22267000 | 2016-11-01 | 2016-11-30
2016-03-31 | 2015 | Army Reserve | 71901 |  | 2015-05-26 | 2016-01-21 | Hal Hays Construction, Inc. | W912QR-16-C-0006 | 18508000 | 18508000 | 2018-02-20 | 2018-02-20
2016-03-31 | 2014 | Army Reserve | 71999 |  | 2013-12-12 | 2014-03-31 | Wilson Brigadier Joint Venture | W912QR-14-C-0013 | 5905000 | 6764000 | 2015-08-25 | 2015-11-16
2016-03-31 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19101000 | 19893000 | 2015-06-08 | 2016-03-02
2016-03-31 | 2014 | Army Reserve | 72284 |  | 2014-08-13 | 2014-09-30 | Bara Infoware Inc. | W912QR-14-C-0053 | 16187000 | 16182000 | 2016-05-22 | 2016-09-01
2016-03-31 | 2015 | Army Reserve | 72291 |  | 2015-05-01 | 2015-09-30 | Korte Construction Company | W912QR-15-C-0042 | 13283000 | 13283000 | 2017-08-28 | 2017-08-28
2016-03-31 | 2015 | Army Reserve | 77228 |  | 2015-08-11 | 2016-01-28 | Blinderman Construction | W912QR-16-C-0007 | 21311000 | 21311000 | 2018-02-16 | 2018-02-16
2016-03-31 | 2015 | Army Reserve | 81959 |  | 2015-03-06 | 2015-07-17 | ETD-TCG, LLC with RSP Architects | W912QR-15-C-0018 | 5215000 | 5252000 | 2016-12-09 | 2016-12-30
2016-03-31 | 2015 | Army Reserve | 85812 |  | 2015-08-11 | 2015-09-30 | Cox Construction Co. | W912QR-15-C-0044 | 21672000 | 21672000 | 2017-10-02 | 2017-10-02
2015-12-14 | 2011 | DLA Defense Distribution Center | DDCX0802 |  | 2011-11-23 | 2012-08-17 | Walsh Construction | W912DR-12-C-011 | 80775000 | 82555000 | 2015-09-18 | 2016-01-29
2015-12-14 | 2012 | DLA Defense Distribution Center | DDCX1202 |  | 2012-09-17 | 2013-11-20 | Corothers Construction Inc. | W912DR-14-C-0005 | 24622000 | 25388000 | 2015-08-27 | 2016-02-29 | 2853 Reprogramming
2015-12-14 | 2012 | DLA Defense Distribution Center | DDCX1203 |  | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 15198000 | 15912000 | 2016-05-05 | 2016-09-18
2015-12-14 | 2013 | DLA Defense Distribution Center | DDCX1301 |  | 2014-05-15 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 6800000 | 6800000 | 2016-07-28 | 2016-08-03
2015-12-14 | 2013 | DLA Defense Distribution Center | DDCX1303 |  | 2013-06-13 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9658000 | 9758000 | 2016-01-02 | 2016-03-06 | 2853 Reprogramming
2015-12-14 | 2014 | DLA Defense Distribution Center | DDCX1404 |  | 2014-02-11 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 32930000 | 32930000 | 2016-02-25 | 2016-04-04
2015-12-14 | 2014 | DLA Defense Distribution Center | DSFH1401 |  | 2015-01-28 | 2015-06-02 | Hako Plumbing, Inc | N62742-15-C-1310 | 2800000 | 2800000 | 2016-10-14 | 2016-10-14
2015-12-14 | 2014 | DLA Defense Distribution Center | DSFH1401 | DSFH14U2 | 2015-01-28 | 2015-06-02 | Hako Plumbing, Inc. | N62742-15-C-1310B | 3000000 | 3000000 | 2016-10-14 | 2016-10-14
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC 1306 |  | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378000 | 66999000 | 2017-10-14 | 2017-10-14 | wo# 1124159
2015-12-14 | 2015 | DLA Defense Energy Support Center | DESC 1463 |  | 2015-07-15 | 2015-09-30 | Structural Asspcoates Omc. | W9128F-15-C-0032 | 8518820 | 8518820 | 2017-02-17 | 2017-02-01
2016-01-15 | 2014 | DLA Defense Energy Support Center | DESC 1509 |  | 2015-07-27 | 2015-09-23 | CB&I Federal Contractors | N39430-15-D-1632 | 4882257 | 4882257 | 2016-12-06 | 2016-12-06
2015-12-14 | 2011 | DLA Defense Energy Support Center | DESC0503 |  | 2012-05-17 | 2012-09-22 | Tokyo Construction Co., Ltd. | W912HV-12-C-0013 | 25204000 | 25586000 | 2015-02-01 | 2015-05-13
2015-12-14 | 2012 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2012-03-29 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08C-7501 | 15512000 | 16393973 | 2013-09-23 | 2014-02-28 | wo# 113174
2015-12-14 | 2008 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2008-09-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 52443000 | 55647000 | 2013-09-25 | 2015-07-01 | wo# 861477
2015-12-14 | 2010 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2011-03-22 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 79509000 | 88774000 | 2013-09-23 | 2014-02-28 | wo#861477
2015-12-14 | 2011 | DLA Defense Energy Support Center | DESC0704 |  | 2008-02-20 | 2011-03-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 17400000 | 18653063 | 2013-09-23 | 2014-02-28 | wo#974938
2015-12-14 | 2010 | DLA Defense Energy Support Center | DESC0907 |  | 2009-12-17 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844000 | 19369000 | 2012-12-16 | 2015-04-30
2016-03-08 | 2011 | DLA Defense Energy Support Center | DESC0909 |  | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | N40085-11-C-0001 | 28815000 | 33890078 | 2014-06-03 | 2015-05-30 | wo# 799865
2015-12-14 | 2012 | DLA Defense Energy Support Center | DESC1102 |  | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 25181000 | 25388000 | 2015-12-10 | 2016-02-08 | 2853 Reprogramming
2015-12-14 | 2012 | DLA Defense Energy Support Center | DESC1103 |  | 2012-05-04 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 18962000 | 18902000 | 2014-11-03 | 2015-05-15
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1107 |  | 2014-02-28 | 2014-06-12 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4056000 | 4166000 | 2015-08-11 | 2015-08-19
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC11U2 |  | 2014-03-28 | 2014-04-24 | Gilbane Federal | N62583-09-D-0129 | 1994000 | 1994000 | 2015-11-15 | 2015-11-15 | wo# 1302082
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1203 |  | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366000 | 36366000 | 2015-10-28 | 2015-09-28 | wo# 1124257
2015-12-14 | 2012 | DLA Defense Energy Support Center | DESC1205 |  | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453000 | 27840000 | 2015-03-24 | 2015-08-30 | 2853 Reprogramming wo# 973902
2015-12-14 | 2012 | DLA Defense Energy Support Center | DESC12S1 |  | 2012-03-27 | 2012-07-05 | Kinley Construction Company | W9128F-10D-0052 | 1930000 | 2101000 | 2017-04-19 | 2015-09-22
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1301 |  | 2014-11-13 | 2015-08-28 | Rockford Corporation | W912QR-15-C-0026 | 33997000 | 33997000 | 2017-03-30 | 2017-03-30
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1303 |  | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364000 | 54533000 | 2016-02-06 | 2016-10-26 | wo# 1125022
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1304 |  | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513000 | 20077000 | 2016-12-07 | 2017-03-07
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1305 |  | 2013-07-07 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800000 | 1800000 | 2015-04-11 | 2015-04-28
2015-12-14 | 2015 | DLA Defense Energy Support Center | DESC1353 |  | 2015-03-13 | 2015-08-09 | Middle Eastern Builders | W912HN-12C-0016 | 17900000 | 17900000 | 2017-09-27 | 2017-12-26
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1390 |  | 2012-10-30 | 2013-08-13 | Environmental Management Resources | N69450-10-D-0787 | 4311000 | 4455000 | 2015-02-26 | 2015-02-26 | wo# 1123107
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC1391 |  | 2012-12-24 | 2013-08-01 | Nova Group Inc. | W91278-13-C1001 | 15105000 | 15271000 | 2016-02-18 | 2015-12-25
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC13S2 |  | 2014-08-20 | 2015-01-27 | Reliable Contracting Group, LLC | W91278-15-C-0005 | 8456000 | 8456000 | 2016-05-06 | 2016-08-05
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC13S3 |  | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961000 | 1961000 | 2015-10-28 | 2015-10-28 | wo# 1303226
2015-12-14 | 2013 | DLA Defense Energy Support Center | DESC13S4 |  | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322000 | 1454000 | 2014-08-03 | 2015-10-11 | 2853 Reprogramming wo# 1124259
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2015-02-27 | 2015-04-07 | Nippo Corporation | W912HV-15-C-005 | 32623000 | 32623000 | 2018-10-20 | 2018-10-20
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1402 |  | 2014-01-16 | 2014-04-17 | Industrial Power Systems | N69450-14-C-1255 | 5438000 | 5438000 | 2015-10-10 | 2015-10-10 | wo# 1163305
2016-02-09 | 2015 | DLA Defense Energy Support Center | DESC1404 |  | 2015-04-23 | 2016-01-21 | Gilbane Federal | N39430-15-D-1634-JM01 | 9960000
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1405 |  | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749000 | 8786000 | 2016-04-22 | 2016-04-22 | wo#1140322
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1407 |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP-15-C-003 | 21288000 | 21288000 | 2017-01-10 | 2017-01-10
2015-12-14 | 2015 | DLA Defense Energy Support Center | DESC1459 |  | 2015-02-26 | 2015-08-12 | CB&I Federal Services LLC | W912HN-15-C-0017 | 5949000 | 5949000 | 2017-03-30 | 2017-03-30
2016-03-09 | 2014 | DLA Defense Energy Support Center | DESC14S2 |  | 2014-01-09 | 2014-04-14 | Pond Constructors Inc. | W9128F-14-D-0051 | 3780000 | 3942000 | 2015-05-07 | 2016-02-16
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC14U1 |  | 2014-06-01 | 2014-07-01 | CB&I Federal Services LLC | N62583-09-D-0130 TO-027 | 1994000 | 1994000 | 2015-11-15 | 2015-11-15 | wo# 1170569
2016-03-09 | 2014 | DLA Defense Energy Support Center | DESC14U2 |  | 2014-07-31 | 2014-11-14 | Nova Group Inc. | W912PL-12-C-0029 | 935000 | 935000 | 2015-05-03 | 2015-05-31
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1501 |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637000 | 8637000 | 2016-05-11 | 2016-08-09
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1502 |  | 2014-06-17 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0001 | 32060000 | 32060000 | 2017-05-23 | 2017-09-08 | 2853 Reprogramming
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1502 | 43 | 2014-06-17 | 2015-05-04 | Rockford Corporation | W912BV-15-C-0017 | 4556000 | 4556000 | 2016-10-23 | 2016-12-08 | 2853 Reprogramming
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1503 |  | 2014-10-03 | 2015-04-23 | Tokyo Construction Co., Ltd. | W912HV-15-C-0007 | 6244000 | 6244000 | 2016-11-05 | 2016-07-19
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1504 |  | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0011 | 13407000 | 13407000 | 2016-04-08 | 2016-07-07
2015-12-14 | 2015 | DLA Defense Energy Support Center | DESC1510 |  | 2015-02-02 | 2015-08-20 | Graco Construction Inc. | W912QR-15-C-0025 | 32592000 | 32592000 | 2018-01-16 | 2017-09-06
2015-12-14 | 2015 | DLA Defense Energy Support Center | DESC1515 |  | 2015-02-12 | 2015-08-31 | MEB General Contractors Inc. | N40085-15-C-0022 | 22944000 | 22944000 | 2017-06-26 | 2017-06-26 | wo# 1302502
2015-12-14 | 2015 | DLA Defense Energy Support Center | DESC1551 |  | 2014-10-29 | 2015-09-01 | Hensel Phelps Constuction co | N62742-15-C-1308 | 42823000 | 42823000 | 2018-07-08 | 2018-07-08 | wo# 1306143
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1557 |  | 2014-07-28 | 2015-05-14 | Cape Env. Mgmt. | W9128F-10-D-0075 | 3471000 | 3471000 | 2016-10-05 | 2017-01-03
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC1561 |  | 2014-03-10 | 2014-06-12 | Rockford Corporation | W9128F-10-D-0050 | 1917000 | 1917000 | 2015-09-17 | 2015-08-07
2015-12-14 | 2014 | DLA Defense Energy Support Center | DESC15S1 |  | 2014-05-02 | 2014-07-29 | Ichibo Co. Ltd | W912HV-14-C-0002 | 1835000 | 1857000 | 2015-07-24 | 2015-05-15
2015-12-14 | 2015 | DLA Defense Energy Support Center | DESC1606 |  | 2014-12-23 | 2015-11-16 | MEB General Contractors | N69450-16-C-1604 | 365650000 | 365650000 | 2017-12-17 | 2017-12-17
2015-12-14 | 2012 | DLA Defense Energy Support Center | DESI1101 |  | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | N62478-11-D-4042/0004 | 5500000 | 6430000 | 2013-06-14 | 2014-04-29 | wo# 972725
2015-12-14 | 2012 | DLA Defense Supply Center Philadelphia | DSCP1201 |  | 2012-03-28 | 2012-06-01 | WU & Associates, Inc. | N40085-10-D-9451 | 4775000 | 7240000 | 2013-07-17 | 2014-06-06 | wo# 971006
2015-12-14 | 2014 | DLA Defense Supply Center Richmond | DSCR1401 |  | 2015-02-13 | 2015-06-12 | Hensel Phelps Constuction Co | W91236-15-C-0045 | 71969000 | 71969000 | 2018-07-08 | 2018-07-08
2015-12-31 | 2013 | Defense Finance and Accounting Service | 80230 |  | 2013-04-24 | 2013-07-30 | US Army COE, Guyco, Inc. | W9127S-09-D-6006 | 12903 | 13902 | 2015-03-05 | 2016-02-03
2016-03-31 | 2008 | Defense Health Agency | 47298 |  | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110000 | 282778000 | 2013-07-23 | 2016-08-12 | Life Safety Deficiencies: All remaining life safety deficiencies have been cleared. The Contracting Officer has issued a letter to the Contractor stating that this project is considered substantially complete as of March 15, 2016. This letter also identified contract requirements and items remaining to be completed or submitted in order to proceed with contract closeout. Remaining construction activities: There are a few actions remaining to be completed before contract closeout can proceed. Several contract modification actions are underway and some warranty work is ongoing, primarily associated with mechanical systems. For example, modifications to the heat recovery chillers are ongoing to correct a problem affecting temperature control in the data center. This work must be completed and checked out operationally before the data center can be moved from the old hospital to the new, we anticipate completing these chiller repairs in the next few weeks. We are tracking 1672 open punchlist items, the contractor's current schedule shows these being completed by 13 May however these actions have no impact on HFPA's ongoing activities. HFPA: HFPA now controls the facility. They require 120 days after completion and testing of some of the work on the mechanical systems (i.e. chiller repairs discussed above) before the hospital will actually open for patient care. Congressional visits by Senator Moran and Senior Staffer for Senator Tim Huelskamp on 31 Mar 16.
2016-03-31 | 2011 | Defense Health Agency | 51740 |  | 2011-05-13 | 2011-08-26 | Ilsung Construction Co. Ltd. | W912UM-11-C-0024 | 9821000 | 10169000 | 2013-05-13 | 2013-05-16 | $17,794.00 revoked from DLA for LOGCAT F equipment training that's no longer required. Funds were subsequently returned to HQUSACE. Closeout in progress.
2016-03-31 | 2012 | Defense Health Agency | 51969 |  | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | W9126G-12-C-0050 | 28291000 | 29451000 | 2014-10-30 | 2015-12-23 | DHA approved HFPA/DNM discretionary user change request to replace servery hood with a deeper model - Proposed contractor cost of $780K may exceed both the DHA imposed $476K discretionary change limit and the project's programmed amount; awaiting formal proposal from contractor and negotiations prior to engaging DHA for approvals. - Earliest completion is May 16 * Warranty issues continue to be identified and corrected. * Tray conveyor (warranty issue) continues to be carried as an action item for repair
2016-03-31 | 2007 | Defense Health Agency | 52330 |  | 2007-02-16 | 2007-07-19 | Caddell Construction Co. Inc. | W91278-07-C-0037 | 40902000 | 45600000 | 2009-12-17 | 2011-06-05 | Water intrusion problem update - Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. Construction Contractor reviewed their records and provided a response to AF reports 30 Jan 2015. A-E provided response on 2 Feb 2015. CESAM reviewed responses and has awarded the services of a building envelope specialist to prepare independent determination addressing the responsibilities of each party and estimate of damages by each party. The building envelope specialist conducted their initial site visit 21-23 Oct 2015; Initial discussion provided by the A-E indicated the issues may have been caused by many sources. The building contract specialist's last report was received on 14 March 2016 marked FOUO. The report is being reviewed in Counsel for decision on actions.
2016-03-31 | 2007 | Defense Health Agency | 52330 | 67647 | 2007-02-16 | 2007-07-19 | Caddell Construction Co. Inc. | W91278-07-C-0037 | 32890000 | 42183000 | 2009-12-17 | 2011-06-05
2016-03-31 | 2008 | Defense Health Agency | 52332 |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929000 | 26866000 | 2012-05-15 | 2012-07-13 | The contractor is filing a claim in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. German government stated that the contractor has until Dec 2016 to submit additional information for compensation. German government informally stated that the contractor intends to provide the additional information before summer.
2016-03-31 | 2009 | Defense Health Agency | 55918 |  | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034000 | 13672000 | 2011-02-07 | 2011-06-22 | Residual closeout issues.
2016-03-31 | 2007 | Defense Health Agency | 58395 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657000 | 2657000 | 2008-06-13 | 2008-06-08 | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 58395-01 | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472000 | 1472000 | 2009-02-15 | 2009-02-13 | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 58395-02 | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706000 | 706000 | 2010-04-13 | 2010-04-13 | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 58395-03 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465000 | 2465000 | 2009-07-24 | 2009-07-24 | FY07. Work complete. Contracts closed.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 58395-04 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 2866000 | 2866000 | 2011-05-06 | 2013-10-31 | FY07. Work accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 58395-05 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 15736000 | 16161000 | 2014-05-31 | 2016-09-21 | FY07. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 63418 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 131264000 | 138491000 | 2014-05-31 | 2016-09-21 | FY08. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 63419 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 185526000 | 185630000 | 2014-05-31 | 2016-09-21 | FY09. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 63420 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 94000000 | 100180000 | 2014-05-31 | 2016-09-21 | FY10. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 63420-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 496000 | 525000 | 2013-10-31 | 2013-10-31 | FY10. Line added to show correct FY funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 65324 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 13497000 | 12893000 | 2014-05-31 | 2016-09-21 | FY12. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 65324-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 638000 | 2013-10-31 | 2013-10-31 | FY11. Line added to show correct FY funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 71101 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 66955000 | 90432000 | 2014-05-31 | 2016-09-21 | FY12. Contract # 5. Installing equipment in BSL4 area; sealing conduits in BSL3 area, installing Testing and Evaluation communication lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 71101-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 7750000 | 7750000 | 2017-03-31 | 2017-03-31 | FY12. Contract awarded 18 Sep 15. NTP issued.
2016-03-31 | 2007 | Defense Health Agency | 58395 | 78210 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 75000 | 2014-05-31 | 2017-07-01 | FY13. Utilities, DDC, Certification and modifications for primary facility (Contract # 5). The work in the facility includes installing equipment in BSL4 area; sealing conduits in BSL3 area, installing testing and evalution comms lines in BSL2, and commissioning remainder of facility. Plan is to accept facility in a single phase Jul 2017. Contract completion revised to 21 Sep 16; liquidated damages will be assessed past this point.
2016-03-31 | 2009 | Defense Health Agency | 59220 |  | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500000 | 29404000 | 2015-08-03 | 2015-09-11 | Awaiting additional funds from HFPA for the REA for the Monaco Claim that was just negotiated. Replacement door frames are in and will be installed over the next few weekends. The Metal Panel and Curtain wall punchlist still has a few open items. Commissioning is almost complete, awaiting final documents.
2016-03-31 | 2010 | Defense Health Agency | 61401 |  | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075000 | 10119000 | 2013-01-10 | 2015-01-08 | All pending modifications/REAs are settled. USAG-funded security equipment mod issued/completed. Working with USAG Ft Detrick to resolve issues with VCC flooring and pop-up barriers. Construction contract/project fiscal closeout activities will follow.
2016-03-31 | 2010 | Defense Health Agency | 61536 |  | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | W912DR-10-C-0087 | 13478000 | 13858000 | 2012-09-16 | 2013-05-23 | Facility turned over to USAG Ft Detrick. Punchlist is complete. Working toward project fiscal closeout.
2016-03-31 | 2009 | Defense Health Agency | 62189 |  | 2008-10-27 | 2009-04-03 | Hensel-Phelps Const. Co. | W912BV-09-D-2016 | 47615000 | 51375000 | 2011-10-26 | 2012-02-09 | HP will not sign release of claim so that SWT can issue final payment. HP is stating that they have a subcontractor that has filed a claim against them so their policy is to not sign until resolved. They gave no indication when resolution would occur with their sub.
2016-03-31 | 2011 | Defense Health Agency | 62886 |  | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | W912DR-12-C-0004 | 4270000 | 4624000 | 2013-11-09 | 2015-02-10 | Facility turned over to USAG Ft Detrick. Punchlist is complete. Working toward project fiscal closeout.
2016-03-31 | 2008 | Defense Health Agency | 63864 |  | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | W91DS-08-C-0019 | 27483000 | 35963000 | 2011-02-18 | 2013-12-12 | Financial closeout pending A-E Damages Resolution. Resolution has been delayed and fiscal closeout slipped to 4/30/16.
2016-03-31 | 2009 | Defense Health Agency | 64156 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398000 | 17027000 | 2013-06-01 | 2015-06-10 | Contract is active, but all funds on this increment obligated. Contract closeout pending final completion of punch list items and comissioning challenges in Bldgs E&F. Additional BRAC funds will be required to maintain cost sharing split (93.7 DODM/6.3% BRAC) with companion DODM project.
2016-03-31 | 2008 | Defense Health Agency | 64179 |  | 2008-04-03 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 107589000 | 135926000 | 2011-07-15 | 2013-05-01 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | 64179 | 64180 | 2008-04-03 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 265100000 | 279273000 | 2011-07-15 | 2013-05-01 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | 64179 | 69840 | 2008-04-03 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 13748000 | 243943000 | 2011-07-15 | 2013-05-01 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | 64179 | 70990 | 2008-04-03 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 37554000 | 85520000 | 2011-07-15 | 2013-05-01 | There are still actions on-going that will prevent close-out (work is 100% complete - not all payments have been made): 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Tentative resolution date is 9 Jun 2017. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments were suspended. They provided the telephones for the project. The invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. The Contractor EYAK signed a release of claim and all remaining funds were deobligated off the Contract and sent back to HQUSACE via revocation. Approx $77K. There is another ULO for approx $10K that is still unpaid to Siemens for a piece of Cat E Equipment. PM is working with DLA in Philadelphia to have Siemens provide a final invoice. This was for the last piece of training on the equipment and the training is complete according to SAMMC POC. 3. TEAM Integrated Services Task Orders. TEAM agreed with DCMA Audited rate determination and TEAM will submit final invoices by end of Jul 2015. These will be reviewed and processed for final payment after they are received.
2016-03-31 | 2008 | Defense Health Agency | 64188 |  | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | W9126G-08-C-0024 | 33382000 | 37382000 | 2010-05-10 | 2010-05-10 | REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2016-03-31 | 2008 | Defense Health Agency | 64473 |  | 2008-07-29 | 2008-09-18 | The Korte Company | 912DW-08-C-0018 | 17497000 | 18181000 | 2010-02-20 | 2010-03-17 | Copy of DD1354 sent to HQUSACE, 7 Mar 16.
2016-03-31 | 2012 | Defense Health Agency | 65030 |  | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co. | N40083 12 C 0001 | 5835000 | 6195000 | 2013-09-13 | 2014-08-08 | Residual closeout issues
2016-03-31 | 2010 | Defense Health Agency | 65270 |  | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133000 | 168551000 | 2014-10-15 | 2016-09-06 | 3rd UXO found; work has restarted
2016-03-31 | 2009 | Defense Health Agency | 65731 |  | 2009-01-07 | 2009-04-08 | Clark Construction Group, LLC | W912DR-09-C-0030 | 6887870 | 7070197 | 2010-08-08 | 2010-08-31 | FY09. All funds on this increment have been obligated. This contract has been terminated for default.
2016-03-31 | 2009 | Defense Health Agency | 65731 | 65731-01 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 12000000 | 12658000 | 2013-06-01 | 2015-06-10 | FY09. All funds on this increment obligated. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2009 | Defense Health Agency | 65731 | 67180 | 2009-01-07 | 2009-04-08 | Clark Construction Group, LLC | W912DR-09-C-0030 | 461470 | 824748 | 2010-08-08 | 2010-08-31 | FY10. All funds on this increment have been obligated. This contract has been terminated for default.
2016-03-31 | 2009 | Defense Health Agency | 65731 | 67180-01 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30 | FY10. All funds on this increment have been obligated. Gasline construction complete.
2016-03-31 | 2009 | Defense Health Agency | 65731 | 67180-02 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 100375000 | 103745328 | 2013-06-01 | 2015-06-10 | FY10. All funds on this increment have been obligated. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2009 | Defense Health Agency | 65731 | 67181 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 94608000 | 96044506 | 2013-06-01 | 2015-06-10 | FY11. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2009 | Defense Health Agency | 65731 | 67182 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 31686000 | 2013-06-01 | 2015-06-10 | FY12. Early site package and gasline construction complete. Early BOD of admin spaces (Bldgs A/B/C/CUP) on 19 Nov 14. BOD of Building F and remaining sitework achieved 15 Apr 15. Final BOD for Building E was 10 Jun 15. Third party contract for Jacobs/Facility Dynamics Engineers (FDE) was awarded on 15 Sep 15. USACE has retained FDE to investigate two primary issues associated with the E Building lab complications of the USAMRICD Replacement Facility. Projected date for FDE overall report and recommendations is 11 Mar 16. PDT will analyze the recommendations and execute aquisition plan for final implementation in May 2016. Third issue of high noise level readings in E&F Building has been investigated by the A/E (FLAD Architects) over the last several months. AE produced scope and estimate for all rooms that don't meet required noise criteria on 25 Nov 15. Projected contract award for physical acoustic testing/investigation by early-Mar 16. Projected testing complete June 2016 - will then analyze requirements/costs for full implementation; schedule to be determined. Contractor submitted a certified claim for cummulative impacts on 18 Dec 15 in the amount of $27.3M; review underway.
2016-03-31 | 2011 | Defense Health Agency | 66588 |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 32103000 | 32103000 | 2016-05-30 | 2016-09-04 | Addition turned over 26 Jun 2015; flooring punchlist items corrected in Jan 16. BMEDDAC Safety Officer identified safety issue with the water feature; the elevation difference (20-30 cm) meets German criteria, but not US. Coordination ongoing to provide solution. Customer BOD of Health Clinic Addition on 26JUN15. X-ray room wall extension completed on 15FEB16. Concrete floor slab surface imperfection corrected with topping slab (Phase 3). Interior wall layout and erection ongoing (Phase 3). Utility tie-in from Addition (Phase 2) to Renovation (Phase 3) ongoing. Final construction completion (Renovation) may be delayed due to cumulative modification delays. BauAmt's negotiations on delay and associated costs (worst case 320k euro) have been are taking longer than anticipated due to the unforeseen site conditions found during the renovation phase (bowed roof, inproperly applied screed, and deteriorated and unmarked existing utilities that may also impact the schedule. Anticipated completion of the Alteration is 16 Feb 17.
2016-03-31 | 2011 | Defense Health Agency | 66693 |  | 2013-07-09 | 2013-09-30 | Federal Republic of Germany | W912GB-09-C-0029-NA | 34294000 | 34376000 | 2016-04-12 | 2016-04-12 | Preliminary cleanup ongoing throughout facility.-Priming, painting, and touch up of interior rooms (1st & 2nd floors) continues. Electrical and mechanical systems, communications cabling, ductwork nsulation, sprinkler, and sanitary sewer line trimout and programming ongoing. Pre-Final Inspections by Bauamt and A/E ongoing. Commissioning Agent (Jacobs Engineering) onsite for Pre-Commissioning Inspection during week of 29FEB16. Commissioning contract change to be negotiated by the BauAmt by mid March. Current value approximately 310k Euro to include a no cost time extension; commissioning will occur shortly after original completion date of 12 Apr 16. Pending modification for water softening to meet requirements for dental sterilizer/washer (~50-60k euro).
2016-03-31 | 2011 | Defense Health Agency | 67949 |  | 2011-08-19 | 2012-02-14 | Rich Moe Enterprises, LLC | W912DR-12-C-0001 | 1701000 | 1701000 | 2013-04-02 | 2013-04-01 | Segment 1 - Work complete.
2016-03-31 | 2011 | Defense Health Agency | 67949 | 67949-01 | 2015-03-09 | 2015-09-18 | Edifice- Schlosser JV (Phase II) | W912DR-15-C-0025 | 660000 | 660000 | 2017-03-31 | 2017-03-31 | Segment 2 - Work structured as contract option in combined solicitation with USAMRIID Replacement North Parking (Contract # 6) which establishes overall site contours for fence construction. Contract option was awarded 17 Sep 15. Notice to proceed was issued/acknowledged 8 Oct 15. BOD is 29 Jun 17.
2016-03-31 | 2011 | Defense Health Agency | 67951 |  | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308000 | 15639000 | 2014-07-08 | 2016-03-18 | % Complete (Scheduled/Actual): 100/97 . BOD revised to 18 Mar 16 due to systems commissioning schedule impact related to replacement of defective valves. Commissioning effort resumed 1 Feb 16. Testing is progressing successfully.
2016-03-31 | 2011 | Defense Health Agency | 67953 |  | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468000 | 3944000 | 2012-11-01 | 2016-03-04 | % Complete (Scheduled/Actual): 100/98. Contractor performance issues; liquidated damages being assessed from 30 May 14. Bonding company has arranged for 3rd party payment to subcontractors. Tank has been filled and passed testing. Remaining work is limited to completion of pump station equipment/controls. Subcontractors are responding and performing work.
2016-03-31 | 2010 | Defense Health Agency | 69353 |  | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | W912HN-11-C-0002 | 14725000 | 15287000 | 2012-10-12 | 2012-11-15 | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14. Financial close-out underway. Final UDO cleared 19 Aug 15 and funding returned; three doors have to be replaced to complete the Final Punch List for project.
2016-03-31 | 2008 | Defense Health Agency | 69626 |  | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | W9126G-08-C-0036 | 18512000 | 19120000 | 2011-07-15 | 2013-05-01 | Contract closeout ongoing.
2016-03-31 | 2008 | Defense Health Agency | 70235 |  | 2009-04-08 | 2009-09-28 | Turner Construction Company | W912HN-09-C-0045 | 230018000 | 275275000 | 2013-02-03 | 2014-05-19 | Commissioning of systems complete including seasonal tests which were completed in Feb 2016. Contingencies at District: $1,354,242.84. Ribbon cutting held 7 Nov 2014. Final payment scheduled for 31 Mar 16. Resident Office settled four REA's found to have merit in amount of $1.353M on 15 Jan 2016. One pending REA under investigation for merit. Benning DPW will assign # upon receipt of final 1354.
2016-03-31 | 2012 | Defense Health Agency | 70351 |  | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400000 | 23770000 | 2014-06-23 | 2016-05-01 | Contingencies at District: $686,130.62. CAT E&F funds at District is $1,962,798.85. Contractor has been issued an Interim Marginal CCASS. Emergency Dept completed and open for patients. 3rd Floor (North) renovations completed 10 Dec 15, furniture installation underway. Negotiations completed on DHA approved User Change to delete work on 2 floors from the contract. 5th and 6th Floor warranty inspections completed. Final inspection completed in Area 3B. Pre-Final inspections completed in 2nd and 3rd floor penthouse. Landscaping underway for ED site. Area 3S work initiated 29 Jan 16.
2016-03-31 | 2009 | Defense Health Agency | 70354 |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 159834000 | 192057000 | 2015-03-16 | 2017-08-16 | Significant changes in processes impacting water storage and the central utility plant are being resolved. Resolution requires modifying the project Environmental Assessment (EA) to account for permittable items previously not considered. A bilateral agreement for time impacts associated with mandatory engineering changes has been reached resulting in a 359 day adjustment to the construction schedule. This adjustment provides for a re-baseline of the project schedule and development of a true integrated master schedule. Agreement for time does not constitute agreement for compensable time. Compensable days are to be negotiated. USACE Engineers are continuously evaluating project design to identify concerns and remedies for way-ahead. Senior leadership continues to engage regularly to assist in resolution of project issues. All other unaffected work activities are continuing per plan.
2016-03-31 | 2012 | Defense Health Agency | 70438 |  | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company | W912QR-12-C-0036 | 43466000 | 51638000 | 2015-02-21 | 2015-10-27 | All work complete effective 27 Oct 2015. Ribbon cutting 17 December 2015. Closing Out
2016-03-31 | 2011 | Defense Health Agency | 70482 |  | 2010-11-19 | 2011-06-03 | McCarthy Building Companies, Inc. | W912HN-11-C-0006 | 23050000 | 25062000 | 2013-06-20 | 2014-05-19 | Contingencies at District: $0. CAT E&F remaining at District: $0. Financial close-out underway.
2016-03-31 | 2012 | Defense Health Agency | 70579 |  | 2012-10-05 | 2013-02-13 | Structural Associates Inc. | W912DS-13-C-0022 | 9934000 | 9937000 | 2015-03-06 | 2015-03-06 | Project Fiscally complete 9 DEC 15
2016-03-31 | 2012 | Defense Health Agency | 70580 |  | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | W91DS-13-C-0002 | 4370000 | 4370000 | 2015-01-09 | 2014-12-19 | Project Fiscally complete 4 DEC 15
2016-03-31 | 2012 | Defense Health Agency | 70597 |  | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | W91278-12-C-0028 | 8897000 | 9137000 | 2014-10-07 | 2014-10-07 | Final document turnover in process. Performing post BOD changes at user request, PT room flooring, walk off matts, rear gate padlocks and door hardware. Final Pay anticipated April, 2015.
2016-03-31 | 2013 | Defense Health Agency | 71317 |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744000 | 42119000 | 2016-12-30 | 2018-02-13 | In construction
2016-03-31 | 2010 | Defense Health Agency | 71318 |  | 2009-10-28 | 2010-02-26 | JE Dunn Construction Company | W9126G-08-D-0057 | 22680000 | 23591000 | 2012-01-06 | 2012-09-01
2016-03-31 | 2013 | Defense Health Agency | 71325 |  | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536000 | 47116000 | 2016-10-23 | 2016-12-22 | Structural steel erection complete. Steel bar joist and metal deck work underway. Concrete placement complete in Area C complete. HVAC piping and ductwork underway in Area C. Metal Stud work underway in area C. Contingencies at District: $279,302.19. Cat E&F Equip funds at District: $1,723,000
2016-03-31 | 2012 | Defense Health Agency | 71408 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688000 | 18689000 | 2016-12-06 | 2018-03-05 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2016-03-31 | 2012 | Defense Health Agency | 71503 |  | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Construction | N69450 12 C 0754 | 19096000 | 21223000 | 2014-09-09 | 2017-12-31 | Notification of contract termination 5 May 2015
2016-03-31 | 2013 | Defense Health Agency | 71507 |  | 2013-02-28 | 2013-12-18 | Turner Construction Company | N40080 14 C 0154 | 41408000 | 42607000 | 2015-10-15 | 2016-08-01 | In construction
2016-03-31 | 2010 | Defense Health Agency | 71550 |  | 2010-06-16 | 2010-12-14 | Vinci Construction UK Ltd. | CT/INT21/13625 | 13425000 | 12421000 | 2012-08-10 | 2012-09-28 | Estimated financial closure: 31 Jul 2016. DIO cannot close this main project financially until the local order for the new main door is complete.
2016-03-31 | 2010 | Defense Health Agency | 71550 | 71550-01 | 2013-04-05 | 2013-06-15 | VolterFitzpatrick | DEUSF/13214 | 68000 | 68000 | 2013-08-30 | 2013-08-30
2016-03-31 | 2010 | Defense Health Agency | 71550 | 71550-02 | 2014-08-20 | 2014-08-25 | Vinci Facilities | CT/INT21/13625 | 69000 | 69000 | 2015-06-30 | 2016-06-30 | DIO cannot close main project until this local order is complete. Structural Survey for new doors carried out. Report received at the Base. Base requested DIO (1Mar 2016) to proceed with the works.
2016-03-31 | 2009 | Defense Health Agency | 71653 |  | 2010-06-11 | 2010-09-01 | Clark/McCarthy, JV | N62473 10 C 0001 | 418039000 | 425895000 | 2014-01-07 | 2014-01-07 | Financially Closed
2016-03-31 | 2013 | Defense Health Agency | 71679 |  | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture | W912DQ-13-C-4017 | 10687000 | 10505000 | 2015-02-19 | 2015-02-19 | DD1354 Complete on 19 Feb 16. Project Closeout scheduled for 15 Aug 16 due to recent heat issue in sterilization storage room.
2016-03-31 | 2008 | Defense Health Agency | 71857 |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 31112000 | 32857000 | 2013-01-12 | 2013-07-15 | Funds used for FY00 Settlement, Ft. Wainwright. Financially Closed
2016-03-31 | 2012 | Defense Health Agency | 72292 |  | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778000 | 44473000 | 2016-10-14 | 2017-03-17 | Contingencies at District: $117,727.72 of which $67,869.95 is for temp. swing space. Cat E&F at District is $341,865.73. Executed Option 5 on Trailer Lease. Approval to descope received 5 June 2015. ED addition turned over 16 Nov 15. Kitchen renovation completed on 18 Dec 15. Renovations continues in Areas C, D, G and H.
2016-03-31 | 2015 | Defense Health Agency | 72414 |  | 2015-04-21 | 2015-09-25 | Gilbane Federal JV | W9127S-13-D-6000 | 15137000 | 15137000 | 2017-10-23 | 2017-10-23 | ISSUES/COMMENTS: 35% design review comments: There was no progress in closing out comments last week. Of the 639 comments, 390 are pending backcheck and 239 are closed. The COR will continue to review all comments pending backcheck and close them, with the reviewers concurrence. HVAC System: The way ahead is to request a UFC waiver, for the GHP system, from DHA/FD. The Waiver Package was sent to CENWO-PM and CENWO-ED on 9 Mar 16 for review. An updated LCCA was completed by SES, 14 Mar 16. and revised 17 Mar 16. AFCEC prepared a Project Financial Status Report, 17 Mar 16. The package was submitted to AFMSA for review, 23 Mar 16. LAD submitted a draft revision to DIPC, 24 Mar 16. This revision eliminates one of the oral surgery rooms and increases the size of the Decon, Sterilization and Sterilization Storage, the 3 functions that comprise DIPC.
2016-03-31 | 2013 | Defense Health Agency | 72419 |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co. Ltd. | W912UM-13-C-0025 | 22361000 | 22550000 | 2017-08-08 | 2018-02-07 | Contingency Amounts: District $140,517; HQ Mgmt $794,834. Ongoing work: UL Paint, Concrete Curbs and Pavement, VCT and Carpet, Light Fixture, Acoustical Ceiling Tile, Sprinkler Head, Feeder Cable. Concurrrent delays caused by malfunctioning existing backup generator (govt delay) and by wrong procurement of DDC system wiring (contractor delay) is causing an approximate 22 calendar days schedule slip.
2016-03-31 | 2013 | Defense Health Agency | 72420 |  | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. | W912UM-13-C-0018 | 8544000 | 9081000 | 2015-02-25 | 2015-03-29 | Contingency Amounts: District $0; HQ Mgmt $0. Final Inspection was completed and keys turned over 27 Mar 15. Final payment made 18 Feb 2016. Closeout in progress.
2016-03-31 | 2010 | Defense Health Agency | 72430 |  | 2010-06-11 | 2010-08-19 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0005) | 41566000 | 45105000 | 2013-02-20 | 2013-08-30 | 1. Phase 1B was turned over to the Air Force (BOD was 19 Nov 2013) 2. Post Warranty Deficiencie corrections are underway 3. JE Dunn is correcting ADA/ABA non-compliance as a latent deficiency. Work is approximately 90% complete. 4. JE Dunn to submit plan to correct Life Health Safety deficiencies and original punch that were not previously addressed.
2016-03-31 | 2010 | Defense Health Agency | 72430 | 72430-01 | 2010-06-11 | 2010-08-31 | JE Dunn Construction Company | W9126G-08-D-0057 (TO 0006) | 23216000 | 24153000 | 2012-02-26 | 2012-11-30 | 1. Phase 1B was turned over to the Air Force (BOD was 19 Nov 2013) 2. Post Warranty Deficiencie corrections are underway 3. JE Dunn is correcting ADA/ABA non-compliance as a latent deficiency. Work is approximately 90% complete. 4. JE Dunn to submit plan to correct Life Health Safety deficiencies and original punch that were not previously addressed.
2016-03-31 | 2010 | Defense Health Agency | 72481 |  | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 7782000 | 11366000 | 2016-11-26 | 2017-01-08 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 72481-01 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-08-29 | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | 72481 | 72481-02 | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488000 | 10635000 | 2012-07-05 | 2012-08-20 | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | 72481 | 72481-03 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-06-11 | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | 72481 | 72481-04 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960000 | 2800000 | 2015-08-27 | 2015-11-30 | Sch. 100% Act. 99%. The contractor began construction 3 Nov 14. Pipe installation was completed 26 Aug. Pavement was completed 27 Aug. Remaining punchlist item is providing electrical power to the metering manhole.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 72481-05 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2014-01-04 | Construction 100% Complete
2016-03-31 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G-11-P | 46000 | 46000 | 2011-11-01 | 2011-11-01 | Temp power costs.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 72786 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 69851000 | 72931000 | 2016-11-26 | 2017-01-08 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 76558 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 79914000 | 165839000 | 2016-11-26 | 2017-01-08 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 76558-01 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540000 | 657000 | 2014-10-24 | 2014-10-24 | Only the re-seeding of the Helipad area remains as a punchlist item (scheduled for Spring 2016).
2016-03-31 | 2010 | Defense Health Agency | 72481 | 76558-02 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2015-08-27 | 2015-11-30 | Sch. 100% Act. 99%. The contractor began construction 3 Nov 14. Pipe installation was completed 26 Aug. Pavement was completed 27 Aug. Remaining punchlist item is providing electrical power to the metering manhole.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 77251 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 68076000 | 68076000 | 2016-11-26 | 2017-01-08 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 77293 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 198148000 | 93144000 | 2016-11-26 | 2017-01-08 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 81407 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 225199000 | 85171000 | 2016-11-26 | 2017-01-08 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2010 | Defense Health Agency | 72481 | 81408 | 2012-08-07 | 2013-01-29 | CM JV | W9126G-13-C-0004 | 56858000 | 0 | 2016-11-26 | 2017-01-08 | HOSPITAL - Construction Progress: Sch. 75% Act. 43%: Current contractual construction completion date is 8 Jan 2017. The estimated construction completion date is March 2018. Placement to date: $277.5M as of 26 Feb 16. "Tiger teams" established to implement processes for performance imporvement; proejct leadership realignment between USACE, CMHP and HDR implemented. Dispute resolution board established to expedite issue resolution. USACE in process of refining initial ATR request ($50M from the FY16 decrement), 2nd ATR for the remaining funding requirement will be prepared once there is more fidelity on requirement.
2016-03-31 | 2009 | Defense Health Agency | 72722 |  | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 76944000 | 84365000 | 2014-09-09 | 2015-04-17 | All mod work completed. Completion of last punch list item in progress. Construction has been substantially complete since 17 Apr 2015. All physical work less plenum to be complete 30 Jan.
2016-03-31 | 2009 | Defense Health Agency | 72722 | 72722-01 | 2011-03-07 | 2011-03-20 | A1 Tree Service | W912QR-11-C-0040-1 | 9600 | 9600 | 2011-04-01 | 2011-04-01 | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2016-03-31 | 2009 | Defense Health Agency | 72722 | 72722-02 | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp | W912QR-11-C-0027 | 5395000 | 5395000 | 2014-09-27 | 2015-03-18 | Leased Swing Space awarded for risk mitigation.
2016-03-31 | 2009 | Defense Health Agency | 72722 | 72722-03 | 2015-07-10 | 2015-08-30 | Northview Enterprises | W912QR-14-D-0022-1 | 260000 | 260000 | 2016-09-01 | 2016-09-01 | Construction award made 11 Sep 15. After Contract award Winter Exclusionary Period began. Contractor intends to mobilize on site 15 March 2016. Weekly Construction meetings on going. Submittal process ongoing. Baseline schedule submitted and currently under review by LRL.
2016-03-31 | 2012 | Defense Health Agency | 72727 |  | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd. | CT/INT21/13487 | 11958000 | 11958000 | 2015-10-30 | 2015-12-18 | Contractor has requested an extension of time but this has not yet been approved by the Contract Officer. Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14. Contracting Officer has granted a nil cost extension of time to 25 Dec 2015 based on delays resulting from the original groundwork subcontractor withdrawing from the contract and from a national shortage of labour delaying the brickwork trade. Contractor has requested a further extension of time of 14 calendar days due to late information from SPAWAR. this is currently being reviewed by the Contracting Officer. Contracting Officer approved an extension of time to 8 Jan 2016. Construction complete and BOD achieved 27 August 2015. US Outfitting contractor SIOTS to carry out work under separate contract and to facilitate move from existing clinic (Building 140). VINCI will remobilise in November to demolish building 140 to complete the contract. US outfitting contractor nearing completion, clinic proposed to open for patients 8 Oct 2015. Ribbon cutting 6 Nov 2015. Asbestos surveys to be carried out in building 140 once vacated by Med Group prior to demolition. Mobilisation Meeting for Demolition of Building 140 3 November 2015. Building 140 Old Clinic is now 50% demolished. Contract completed 18 Dec 2015. Demolition of Building 140 completed on 17 Dec 2015 with landscaping (grass seeding) to be done in Spring 2016.
2016-03-31 | 2011 | Defense Health Agency | 72752 |  | 2011-05-20 | 2011-09-28 | Skanska USA Building Inc. | W9126G-11-C-0053 | 80558000 | 101218000 | 2013-10-01 | 2016-05-23 | 1. Construction status: 99% complete / 99% scheduled 2. CCD/BOD is 23 May 2016 3. Remaining critical path: generator testing, install HVAC smoke dampers, correct Life Health Safety Deficiencies, and complete commissioning. 4. Generators were run to 100% load, but operated near high exhaust gas temp alarm point. Skanska to submit plan (way forward) to include additional testing to correct any remaining issues or establish the units can meet contract requirements. 4. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business. 5. Ph 2 CWE = $114,136,156 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161
2016-03-31 | 2012 | Defense Health Agency | 72754 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 76038000 | 82164000 | 2014-07-29 | 2016-05-23 | 1. Construction status: Scheduled 98%, Actual 98% 2. Schedule: CCD/BOD is 23 May. 3. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business + 6-months to complete reutilization process for an approximate building turnover in Jun 2017. 4. Completion of Ph 3 critical path: correction of Life Health Safety Deficiencies, and complete commissioning. 5. Ph 3 CWE = $122,490,265, Appropriation = $122,634,000 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161
2016-03-31 | 2012 | Defense Health Agency | 72754 | 80793-01 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22808000 | 2014-07-29 | 2016-05-23 | 1. Construction status: Scheduled 98%, Actual 98% 2. Schedule: CCD/BOD is 23 May. 3. Initial Outfitting start 24 May 2016 with approximate 7-month performance period to Jan 2017 for Open-for-Business + 6-months to complete reutilization process for an approximate building turnover in Jun 2017. 4. Completion of Ph 3 critical path: correction of Life Health Safety Deficiencies, and complete commissioning. 5. Ph 3 CWE = $122,490,265, Appropriation = $122,634,000 6. Pre-final is complete. Total findings (Ph 2 + Ph 3) = 10,195; Open = 2161
2016-03-31 | 2013 | Defense Health Agency | 72808 |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703000 | 19797000 | 2015-03-16 | 2016-08-30 | In construction
2016-03-31 | 2011 | Defense Health Agency | 73360 |  | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869000 | 19957000 | 2014-01-06 | 2014-10-07 | Targeting minor punchlist item completion relating to roll-up doors by mid-Mar 2016. Construction contract/project fiscal closeout will follow.
2016-03-31 | 2009 | Defense Health Agency | 73599 |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178000 | 29293000 | 2015-01-02 | 2015-10-16 | Completed
2016-03-31 | 2013 | Defense Health Agency | 73776 |  | 2012-11-15 | 2013-12-18 | Structural Associates Inc. | W91DS-14-C-0003 | 11163000 | 10901000 | 2016-01-06 | 2016-01-06 | BOD 6 JAN 16. Project physcial completion will be May 16 when grass has been established.
2016-03-31 | 2009 | Defense Health Agency | 74650 |  | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989000 | 550241000 | 2014-05-31 | 2016-02-15 | Sch. 100% Act. 99%. Currently working on completing punch list items (approx 20 remaining); USACE and Balfour-Beaty/ McCarthy (BBM) continue to address all issues as they are presented by the hospital command; contiuing to work the DD1354 for the site work; IO&T operations continue. Ribbon cutting ceremony scheduled for 20 June 16.
2016-03-31 | 2009 | Defense Health Agency | 74650 | 74650-01 | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc | SP0600-08-C-8250 | 10225000 | 11445000 | 2012-02-25 | 2012-05-02 | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | 74650 | 74650-02 | 2010-02-12 | 2010-03-08 | TTG Utilities, LP | W9126G-10-C-0032 | 301000 | 301000 | 2010-05-30 | 2010-06-07 | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | 74650 | 74650-03 | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc. | W912DY-05-D-0011 | 1018000 | 1040000 | 2010-10-18 | 2010-10-04 | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | 74650 | 74650-04 | 2010-04-11 | 2010-06-11 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0002 | 6304000 | 10156000 | 2012-01-11 | 2012-09-20 | Construction 100% Complete
2016-03-31 | 2009 | Defense Health Agency | 74650 | 74650-05 | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 TO#0003 | 17290000 | 15383000 | 2012-06-29 | 2015-06-30 | Contractor working close out documentation.
2016-03-31 | 2011 | Defense Health Agency | 75132 |  | 2013-06-14 | 2013-09-27 | Billy W. Jarrett Const Co. Inc. | N62470 13 MPS 0046 | 1797000 | 1834000 | 2014-10-15 | 2016-04-08 | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2016-03-31 | 2012 | Defense Health Agency | 76007 |  | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 16787200 | 16787200 | 2021-07-20 | 2022-03-30 | Environmental Compensation Also includes: Lots 7.2-7.4 Initial Compensation Measures - German government solicitation and award dates to German industry are estimated.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 0 | 0 | 2019-04-30 | 2019-04-30 | Note: this line item has now been combined with Lot 5.1. Construction Measures, Roadways, & Site Utilities - FRG revising and coordinating lot requirements for campus roadways, utilities, and additional construction measures not included in current lot packages. Dates subject to change pending refinement of lots and corresponding schedules. This portion overlaps with Lot 5.1, based on the 35% submittal for that lot. Still awaiting validation from FRG, then will combine with Lot 5.1 line item.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 39286000 | 39286000 | 2019-12-15 | 2019-12-15 | Lot 4 Access Control Point, Bridge, External Roadways - 65% OTS review for ACP was held 22 Sep 2015. 95% review of the Bridge held on 6 Oct 2015. ACP 95% submittal now anticipated for 22 Mar 2016 due to LBB's issues with their designer ATI. The ACP and Bridge will be one contract. At present, the entire lot is scheduled for contract award in the Oct/Nov 2016 timeframe (slipped from Aug 2016) due to aforementioned issues with ATI. Construction completion is still targeted for December 2019, based on US Forces putting the ACP/Bridge into operation at that time. LBB has coordinated sequencing of the ACP & Bridge with the PIK Traffic Circle on L369.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 72662 | 2015-08-19 | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 92750000 | 92750000 | 2019-04-30 | 2019-04-30 | Lot 5.1 Parking structures, surface parking, campus roadways, campus utilities, helipad, site drainage, retention ponds, water tank - previously included in MedCen 20% design. The 35% review meeting held on 27 Oct 2015. Based on the 35% submittal, this lot was much larger that previously expected and contained scope that had not previously been assigned to a particular lot. FRG must validate that the features/costs are not double counted with other infrastructure lots. This is an issue due to the LBB's 35% cost estimate, which is approx 100M Euro, much more than is being tracked as CWE for this particular lot --- their designer ATI's estimate is approx 71M Euro. NAU had been tracking a separate line item (line 89 of this spreadsheet) and a separate amount for Lot 3.11 for most of those items that have now been included in Lot 5.1 per the 35% submittal. NAU has requested that LBB coordinate with their A/E to determine disparities with their cost estimates. NAU had previously been tracking 47M Euro for this lot, which of course did not include the 37M USD from line 89 of this spreadsheet nor the amount for Lot 3.11. Aside from this issue, the Parking structures will be pursued as functional design package prepared by LBB's infrastructure designer. NAU requested that LBB consider delaying award of the parking structures until after the MedCen contract is awarded; however, a final decision has not been reached yet on this issue. NAU still awaits clarification from the LBB regarding scope/cost; however, estimated construction cost is now reflected as $92.8M; line 89 of this spreadsheet has been zeroed out.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-01 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 265000 | 265000 | 2014-04-04 | 2014-04-04 | Lot 1 Temporary Construction Fence - Construction essentially completed April 2014, with remaining access from the east closed off as of 1 May 2015. FRG Security Contractor is on site and will monitor access from the L369 construction gate on the west side.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-02 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 694489 | 1711694 | 2014-10-29 | 2015-01-21 | Lot 2.1 Demolition, Site Clearing - Contract completion date was 12 Dec 2014; however contractor did not meet the date. Per FRG requirement, Contractor given to 14 Jan 2015 to complete work. Final inspection held on 21 Jan 2015, and final contract document provided by FRG (ABG7).
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-03 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5320000 | 5616000 | 2016-04-30 | 2016-05-30 | Lot 2.2 Mass Grading - Contract awarded April 2015. Based on discussions with the FRG, an additional 910k Euro (non-negotiated) have been identified. NAU and DHA-E have implemented the Change Management process in these mods. Awaiting further information from the LBB regarding negotiation timeline. LBB has stated that none of that work affects the schedule at present. Work is on-going, and actual work completion is still targeted for end of April 2016. Dates in columns X and Y have been changed to May 2016, due to actual contract completion.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-04 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5000000 | 5000000 | 2016-12-15 | 2017-12-15 | Lot 3.1 Utilities to site - original ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package delayed due to change in water supply lines and change to double-wall pipe through water protection zone. Due to longer than expected review by the German water authority on those specific issues, SGD-Sud, and continued difficulty and quality issues with the LBB A/E firm, the LBB anicipates solicitation release by mid-March 2016, award by Jun 2016, and construction start in Jul 2016. Construction originally targeted for completion Dec 2016; however, now reliant on Lot 3.7 and City of Ktown completion of 6km sewer line connection. Construction completion now targeted for Dec 2017. Solicitation date slip has not affected the overall completion date of Dec 2017.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-05 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 141235 | 141235 | 2015-03-30 | 2015-05-01 | Lot 3.2 Traffic Light System - Traffic light system in operation since May 2015.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-06 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 17713 | 17713 | 2014-12-31 | 2014-12-31 | Lot 3.3 Construction Sign - Completed in December 2013.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-07 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 482902 | 482902 | 2014-10-16 | 2014-10-16 | Lot 3.4 Gas Line Relocation - Construction complete.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-08 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 19335000 | 19335000 | 2018-04-30 | 2018-04-30 | Lot 3.5 Transformers/Substation - This portion of the ROBMCR project is being run as a direct project through NAU. Contract has a "directed subcontractor clause" to allow the electrical provider, the Pfalzwerke, to participate in the design and construction through the contractor, which ensure compatibility with the electrical grid. J&A for that action was finally approved by the PARC on 4 Feb 2016, after nearly 3 months review time. NAU sent out Phase I solicitation (qualifications) of the D/B RFP package on 5 Feb 2016. Bid opening was 7 Mar 2016, with completion of Phase I by the end of Mar 2016. Phase II (technical) is targeted for release in April 2016, with construction contract award still targeted for June 2016. The construction contract will be set up such that the Southern substation will come on line by Dec 2017, and the Northern substation will come on line by Jul 2018.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 1000000 | 1000000 | 2016-12-15 | 2016-12-15 | Lot 3.6 Water Connection to SWK (Kaiserslautern) system - The FRG received a bid from provider SWK in September 2015; however, the bid was incomplete. The FRG continuing to coordinate with SWK for complete bid. Concurrently, "water providing rights" belong to both the communities of Ramstein Miesenbach and Weilerbach, and they both must officialy and legally transfer authority to the City of Kaiserslautern (Utility Company - SWK) to provide the water. This official action has become a multi-step process; agreements are in draft form and must be ratified by each community mayor/city council. FRG anticipates that the agreement between the communities will be finalized by March or Apr 2016, with target contract award to SWK in Apr 2016 timeframe. This will basically be handled as a connection fee, and FRG has reported that this item will not delay any other features.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-10 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5339748 | 5339748 | 2021-12-17 | 2022-03-30 | Lot 3.9 Site Security - FRG awarded contract in Dec 2013. Security contractor has mobilized and began operation on-site starting 1 May 2015.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-11 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 2500000 | 2500000 | 2021-12-17 | 2022-03-30 | 3.10 Site Logistics - Details to be determined by FRG; contract will be for execution of the entire internal and external construction site logistics, basically, the coordination of site activities between the various contractors. FRG anticipates that they can provide initial scope/package for review in Apr/May 2016.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-12 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 5000000 | 5000000 | 2016-04-30 | 2016-08-15 | Lot 2.3 Landfill Remediation. The contract documents spent several months under ABB legal review (Oct 2015 to Jan 2016). Previously, the LBB was trying to rule out the two low bids, but this was not legally supported. ABB made their final ruling that the low bidder proposal was valid, and the LBB awarded the contract to Firma Peter Gross on 5 Feb 2016 (NAU processed ABG4 contract award documentation on 4 Feb 2016). Presently, construciton is underway with no issues; LBB has informed NAU that the construction completion date is 1 Aug 2016. The delay in getting this contract awarded has not caused any delay to other construction activities.
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-13 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 1000 | 1000 | 2014-12-31 | 2014-12-31 | Communications Cable relocation - Action 100% complete
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76007-14 | 2012-02-01 | 2012-03-15 | Federal Republic of Germany | W912GB-10-C-0031 | 586000 | 586000 | 2021-12-30 | 2021-12-30 | Construction Additional Services
2016-03-31 | 2012 | Defense Health Agency | 76007 | 76872 | 2015-08-19 | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 593454000 | 593454000 | 2021-12-08 | 2022-03-30 | Medical Center (Bed Tower, D&T, Clinics, Admin) - US led 20% MedCen final design submitted 2 Aug 2013. LBB awarded the post-20% MedCen design contract to HDR-TMK on 7 December 2015. Kick-off meeting was held 26-27 January 2016 in Landstuhl. TMK initially submitted 168 questions on the 20% design, all of which were answered prior to the kick-off meeting. TMK submitted an additional 404 questions on 16 Feb 2016, for which answers were provided back to LBB/TMK on 7 Mar 2016. The LBB will have TMK adjust the 20% design through May 2016; the 35% design phase is targeted to begin Jun 2016 and last through Jun 2017. The schedule dates are estimated at this time and will be refined as AE#2 progresses the design. The German govt still supports the goal of construction contract award by the end of calendar year 2017, or shortly thereafter, and project completion in 2022.
2016-03-31 | 2014 | Defense Health Agency | 77000 |  | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR-15-C-0015 | 209917000 | 221672000 | 2019-03-09 | 2019-03-09 | Contractor has mobilized on-site. Preliminary schedule received; review underway. Contractor has started phase one of initial site excavation and spoil site development. Formal partnering is a contract requirment. Initial partnering session was conducted 19/20 Nov 15 with a follow-up session scheduled for 24 Mar 16. Asset ID requested from USAG APG DPW; awaiting response.
2016-03-31 | 2011 | Defense Health Agency | 77115 |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133000 | 48899000 | 2014-02-02 | 2014-07-18 | Residual closeout issues.
2016-03-31 | 2011 | Defense Health Agency | 77116 |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 14030000 | 14392000 | 2014-02-02 | 2014-07-18 | Financially Closed
2016-03-31 | 2012 | Defense Health Agency | 77154 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 131374000 | 138850000 | 2016-12-06 | 2018-03-05 | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2016-03-31 | 2012 | Defense Health Agency | 77154 | 81291 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 66430000 | 67101000 | 2016-12-06 | 2018-03-05 | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2016-03-31 | 2014 | Defense Health Agency | 77922 |  | 2014-02-25 | 2014-08-20 | Gilbane | W9127S-13-D-6000 DM01 | 45629000 | 51665000 | 2018-01-30 | 2018-01-30 | Design complete. Project is under construction. Foundation in place. AMEPLS (Arch, Mech, Elec, Plumbing, and landscape) NTP issued 19 Jan 16; IFC (issued for construction) drawings issued; Structural steel demobilized on 15 Feb 16; Second deck concrete placement completed; exterior masonry block has arrived, preparing to drill for dowels and have started placing masonry block. Interior stud framing now going in.
2016-03-31 | 2013 | Defense Health Agency | 77979 |  | 2013-09-03 | 2014-03-27 | JE Dunn + HWA | W9127S-13-D-6001 DM01 | 47044000 | 53817000 | 2018-02-10 | 2018-06-08 | Construction activity began on 29 Jul 2015. Work is ongoing. Building footings/spread footings are complete. Prep work for Slab On Grade is about 50% complete. Placement of Slab On Grade for Area C is complete, Area D placement is scheduled for week of 1 Feb. "For Construction" Plans and Specifications for the entire project have been received. NTP for Building Construction was issued on 20 Jan 2016. Despite some weather delays slowing down the foundation placement recently, the building pad is complete, underground utilities are complete and the project is back on track with structural steel going vertical and progressing well.
2016-03-31 | 2013 | Defense Health Agency | 78143 |  | 2013-01-14 | 2013-08-22 | Blinderman Constr Co. | N40083 13 C 0003 | 14864000 | 14901000 | 2015-01-15 | 2017-06-25 | Drug Lab BOD Apr 2015, Second Contract to Demo Bldg 38H underway
2016-03-31 | 2013 | Defense Health Agency | 78144 |  | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354000 | 14791000 | 2015-03-17 | 2015-12-21 | Construction Complete
2016-03-31 | 2013 | Defense Health Agency | 78146 |  | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254000 | 7477000 | 2014-12-06 | 2015-11-23 | Construction Complete
2016-03-31 | 2012 | Defense Health Agency | 79554 |  | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200000 | 14457000 | 2014-02-22 | 2014-06-02 | Residual closeout issues
2016-03-31 | 2009 | Defense Health Agency | 79845 |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction Company | W9126G-08-D-0057 | 51133000 | 59456000 | 2014-11-06 | 2015-07-28 | Contract including all currently identified modifications is at 99.58% of PA. Hospital Command moved into new building Dec 19. Urology, ENT, Lab II, Surgery Phase III move in also completed mid December. Acceptance Aug. 29. Joint Commissioning is competed and generated no action items for the project to correct. Completing punch list items and modification and requests after turnover.
2016-03-31 | 2011 | Defense Health Agency | 80093 |  | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc. | W9126G-09-D-0105 | 1698000 | 1982000 | 2013-11-14 | 2014-08-24 | Switch gear was changed on 18 FEB 2015. Project complete. No punch list items. Contract/project closeout and Evaluation not completed. All else is done.
2016-03-31 | 2012 | Defense Health Agency | 80094 |  | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc. | W912BV-12-C-0030 | 1692000 | 1710000 | 2014-07-05 | 2014-12-12 | All contract requirements completed. Final Payment has been processed.
2016-03-31 | 2013 | Defense Health Agency | 80306 |  | 2013-07-25 | 2013-09-12 | G-W Management Servicxes Inc. | N40080 10 D 0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25 | Dosimetry Complete
2016-03-31 | 2013 | Defense Health Agency | 80307 |  | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898000 | 4789000 | 2015-04-08 | 2017-02-28 | In construction
2016-03-31 | 2013 | Defense Health Agency | 80308 |  | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947000 | 27174000 | 2016-02-12 | 2016-09-07 | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2016-03-31 | 2012 | Defense Health Agency | 80792 |  | 2012-06-18 | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service | W81W3G22363343 / 22443665 / 22443666 / 30793685 | 1600000 | 1690000 | 2013-05-31 | 2013-08-29 | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Project financial closeout is ongoing. Update 03 AUG 2015: Received release of claims from American Water and returned all unobligated MIPR'd funds. Still waiting for return of unobligated MIPR'd funds requested by POC for Dominion Virginian Power. Once these funds are returned project will be closed out. UPDATE 8 JAN: NAO UFC determined that outstanding bill had actually been paid from the wrong line item. This error has been corrected and the project can now be closed out. UPDATE 5 FEB: PM is currently preparing a RED Form (CENAB form used for the Contract Closeout) and submitting it to Contracting Division for final close out actions. UPDATE 07 MAR: NAB has requested Ft. Belvoir DPW return Unliquidated Obligation of $124.88.
2016-03-31 | 2014 | Defense Health Agency | 80904 |  | 2014-01-30 | 2015-03-30 | Whiting Turner Contracting Co | N40080 15 C 0156 | 38490000 | 38798000 | 2017-02-07 | 2017-05-18 | In construction
2016-03-31 | 2014 | Defense Health Agency | 80913 |  | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835000 | 15835000 | 2016-04-16 | 2017-02-06 | In construction
2016-03-31 | 2014 | Defense Health Agency | 81340 |  | 2014-03-17 | 2014-06-30 | Gilbane | W9127S-13-D-6000 DY01 | 11289000 | 11289000 | 2016-09-30 | 2016-09-30 | * Scope: FY14 Design-Build project to relocate the existing 6-person hyperbaric chamber from WHMC at JBSA (Lackland AFB) to SAMMC Hospital. * Contractor re-base-lined schedule in Jan; informally notified USACE in Feb that the schedule would slip approximately 10 weeks. Contractor stated delay is from concrete subcontractors performance. Awaiting formal revised schedule. USACE coordinated with AFCEC, AFMSA, and 59MDW. End user is planning additional time in their transition schedule to accommodate any construction related schedule delay. * Floor slab placed 28 Mar 16. * Steel erection complete. * Coordination with 59MDW for transition and chamber relocation ongoing
2016-03-31 | 2015 | Defense Health Agency | 81423 |  | 2015-03-20 | 2015-09-03 | JE Dunn Construction Company | W9127S-13-D-6001 | 33473000 | 33473000 | 2017-12-18 | 2017-12-18 | * Contract awarded to J.E. Dunn construction (on SWL Air Force Medical MATOC) on 3 Sep 2015. * Design Charrette held 9-13 Nov * 35% Design Review conference held 22-27 Feb 16; 65% design review scheduled for 23 May
2016-03-31 | 2015 | Defense Health Agency | 81627 |  | 2015-10-30 | 2016-03-11 | Orion Construction, Inc. | W912DW-16-C-0006 | 2062000 | 2062000 | 2017-11-14 | 2017-11-14 | Partnering Conference scheduled the week of 11 Apr 16.
2016-03-31 | 2014 | Defense Health Agency | 81631 |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc. | W912HN-11-D-0043-0044 | 1436000 | 1438000 | 2016-02-01 | 2016-05-01 | The NICoE Clinic Ribbon Cutting Ceremony was held at 11 AM Thursday, 31 Mar 16. The Contractor submitted an engineering report on 2 Mar 16 with direction to conduct a test pit by removing underlain layer of silty sand or clay to achieve the proper drainage in the two Infiltration Basins.
2016-03-31 | 2014 | Defense Health Agency | 81706 |  | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 1795000 | 1760000 | 2015-10-28 | 2015-12-11 | All site work complete as of 22 Feb 16; Building contractor has completely vacated site. Ribbon cutting completed as of 9 Mar 16. Awaiting DD1354 to be signed by end-user. Also waiting on final as-built drawings from site contractor.
2015-10-30 | 2013 | Defense Information Systems Agency | 13DISA01 |  | 2015-08-05 | 2015-08-19 | Bauamt Reutlingen | W912GB-15-C-011 | 2219820 | 2219820 | 2015-08-19 | 2016-12-31 | PA: $2.224M. Contract awarded to Bauamt on 19 Aug 2015. Kick Off Meeting scheduled 20 Oct 2015.. Next meeting scheduled 2 Dec 2015.
2015-10-30 | 2014 | Defense Information Systems Agency | 14DISA01 | [5 empty] | 2615000 | 2615000 |  |  | PA: $2.615M. NAVFAC preparing RFP for Design. Design charrette scheduled 8-10 Dec 2015. No contract award. Currently all work done in-house.
2015-10-30 | 2015 | Defense Information Systems Agency | 15DISA01 | [5 empty] | 1871000 | 1871000 |  |  | PA: $1.871M. Design/Renovation of Bldg 52120.. USACE conducted site survey 27-28 Apr 2015. Design charrette held 30 Jun 2015. The 65% design comment provided. 65% design mtg scheduled 30 Nov-2 Dec 2015. Currently all work done in-house.
2015-10-30 | 2015 | Defense Information Systems Agency | 15DISA01 | 1 |  |  |  |  | 745000 | 745000 |  |  | PA: $745K. Design of Garrison existing Bldgs 52101, 52110, 52111 for JITC Fort Huachuca. Design charrette scheduled 30 Nov-2Dec 2015. No contract award. Currently all work done in-house.
2015-10-30 | 2015 | Defense Information Systems Agency | 15DISA02 | [5 empty] | 9600000 | 9600000 |  |  | PA: $9.6M. NAVFAC to construct Electronic Equip Bldg, Antenna Foundations for AN/GSB 52B Medium Satellite Earth Terminals. DB RFP to be issued 25 Nov 2015. Construction Timeline: IOC Oct 2017.. No contract award. Currently all work done in-house.
2015-10-30 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11 | PA: $77.515M. 3 separate contracts: Soil Remediation; Construction; Demo Bldg 3189. Soil Remediation: COMPLETED; Construction ESC: 11 Mar 2016;. Demo of Bldg 3189 funding ($2.153M) provided to USACE on 30 Jun 2015.
2015-08-31 | 2008 | Defense Intelligence Agency | 154207 |  | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC | W912DR-09-D-0024 448-0156A-08 | 1012000 | 1012000 | 2011-09-16 | 2012-01-20 | Approp. - $1,012
2015-08-31 | 2010 | Defense Intelligence Agency | DIA10-001 |  | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd. | W912UM-11-C-0006/W912UM-12-C-004 | 4608000 | 5224000 | 2013-10-09 | 2013-10-17 | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project closed out 10 May 2015.
2015-08-31 | 2010 | Defense Intelligence Agency | DIA10-002 |  | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company | W91278-10-D-0064 0001 | 12000000 | 12003000 | 2014-01-20 | 2014-05-21 | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved. Contingency funds will be used in FY15 for within scope modifications.
2015-08-31 | 2011 | Defense Intelligence Agency | DIA11-002 |  | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture | N40080-06-D-0004-0081 | 2984000 | 2294000 | 2012-07-18 | 2012-07-25 | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000001 |  | 2014-06-16 | 2014-09-23 | Arriba | N4008-11-D-0496-0050/N0080-11-D-0495-0016 | 15186000 | 13358000 | 2016-03-02 | 2016-06-30 | Approp. - $13,645 - $793,156 CAT I obligated. Construction start 10 August 2015. NAVFAC met with Contractor leadership and strongly expressed dissatisfaction with state of project. NAVFAC issued interim Unsatisfactory Rating. Contractor is estimated at 20-25 days behind schedule. Amount of $1.6M added to this project from Construction of the Remote Delivery Facility, DIA project DIA12000005 as a below threshhold realignment. Funds are committed awaiting contract award (obligation).
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000002 | [9 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions to add funds from the DIAC Chiller project. Reprogamming action currently with OMB; expect approval soon.
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000003 | [9 empty] | Estimates indicate project costs exceed programmed amounts. DIA initiating reprogramming action to move funds to UPS for Data Center. Awaiting reprogramming action approval.
2015-08-31 | 2012 | Defense Intelligence Agency | DIA12000005 |  | 2013-08-21 | 2013-09-25 | Heard Construction | W91236-09-D-0071:T044/W91236-13-C-0074 | 10758000 | 6058000 | 2014-09-30 | 2015-07-31 | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Final walkthru completed. Equipment training completed. DD Form 1354 completed. Waiting for CIO to complete communication (fiber/phones/CPU installation). Amount of $1.6M diverted to DIA Parking Garage Replacement, project DIA12000001 as a below threshhold re-alignment.
2015-08-31 | 2013 | Defense Intelligence Agency | DIA13000001 | [9 empty] | This line was reduced due to sequestration. The remaining funds are insufficient to complete demolition of the existing parking garage. DIA is currently exploring options. Contract is not awarded at this time.
2016-04-04 | 2010 | DoD Education Activity | AM 856 07 |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764000 | 20563823 | 2013-12-14 | 2014-07-09
2016-04-04 | 2013 | DoD Education Activity | AM00023 |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987000 | 33827998 | 2015-12-11 | 2016-05-30
2016-04-04 | 2013 | DoD Education Activity | AM00023 | 28 | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2015-12-11 | 2016-05-30
2016-04-04 | 2014 | DoD Education Activity | AM00024 |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4896600 | 4929362 | 2016-01-21 | 2016-04-20
2016-04-04 | 2012 | DoD Education Activity | AM00025 |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339200 | 24655000 | 2016-06-01 | 2017-05-20 | The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2016-04-04 | 2012 | DoD Education Activity | AM00026 |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685000 | 34349456 | 2015-11-11 | 2016-08-18
2016-04-04 | 2012 | DoD Education Activity | AM00026 | 43 | 2013-03-04 | 2015-11-05 | Northview Enterprises, Incorporated | W912QR-14-D-0022/36144721 | 1169000 | 1169000 | 2016-11-30 | 2016-11-30
2016-04-04 | 2013 | DoD Education Activity | AM00027 |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 32260396 | 34106701 | 2016-04-21 | 2016-06-30
2016-04-04 | 2013 | DoD Education Activity | AM00028 |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39361936 | 40179510 | 2015-12-17 | 2016-10-05
2016-04-04 | 2013 | DoD Education Activity | AM00028 | 44 | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001/51839544 | 145726 | 145726 | 2015-12-17 | 2016-10-05
2016-04-04 | 2014 | DoD Education Activity | AM00031 |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278-12-D-0039/30132665 | 32124000 | 32094834 | 2017-02-10 | 2017-06-02
2016-04-04 | 2014 | DoD Education Activity | AM00034 |  | 2014-06-20 | 2014-11-10 | Walsh Group Ventures | W912QR-15-C-0001/34496304 | 50930542 | 51381952 | 2017-02-25 | 2017-08-01
2016-04-04 | 2014 | DoD Education Activity | AM00037 |  | 2014-07-25 | 2015-08-18 | Roy Anderson Corp | N6945014R17600005 | 38343900 | 41237415 | 2018-06-28 | 2018-06-28 | Project awarded to second highest bidder following original contractor being terminated for cause.
2016-04-04 | 2014 | DoD Education Activity | AM00038 |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40092900 | 40325461 | 2016-09-14 | 2017-03-05
2016-04-04 | 2014 | DoD Education Activity | AM00040 |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 35264000 | 36002015 | 2016-03-28 | 2016-05-27
2016-04-04 | 2014 | DoD Education Activity | AM00050 |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791250 | 31921717 | 2016-10-31 | 2017-01-29
2016-04-04 | 2011 | DoD Education Activity | AM100801 |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121826 | 14851000 | 16468608 | 2014-04-03 | 2014-07-15 | Remove at end of FY15
2016-04-04 | 2011 | DoD Education Activity | AM2455205 |  | 2011-07-18 | 2011-10-20 | Bernard Associates | W912DS-12-C-0001 / 25312318 | 23974000 | 26115000 | 2014-09-28 | 2014-03-17 | Remove at end of FY15
2016-04-04 | 2011 | DoD Education Activity | AM2455206 |  | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297000 | 44111956 | 2014-09-30 | 2016-01-21
2016-04-04 | 2011 | DoD Education Activity | AM8193 01 |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968494 | 51507845 | 2014-04-19 | 2016-06-03
2016-04-04 | 2011 | DoD Education Activity | AMD02051 |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121890 | 16413000 | 17204544 | 2014-04-03 | 2014-07-15 | $1,443 supported AM0025 and $613 supported PA00033. Remove end of FY15
2016-04-04 | 2011 | DoD Education Activity | D9124-1 |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260170 | 27246631 | 2014-04-17 | 2014-07-04
2016-04-04 | 2011 | DoD Education Activity | D9124-1 | 17 | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843004 | 6002409 | 2015-07-23 | 2013-01-04
2016-04-04 | 2011 | DoD Education Activity | D9124-1 | 18 | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28673973 | 30365039 | 2015-01-13 | 2015-02-12
2016-04-04 | 2013 | DoD Education Activity | EU00034 |  | 2015-12-01 | 2015-12-08 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006 / 44599966 | 57877488 | 57877488 | 2016-02-24 | 2016-05-24
2016-04-04 | 2013 | DoD Education Activity | EU00034 | 45 | 2015-12-01 | 2015-12-08 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006 / 50005397 | 0 | 0 | 2016-02-24 | 2016-05-24
2016-04-04 | 2014 | DoD Education Activity | EU00040 |  | 2016-01-12 | 2016-03-03 | LBB Kaiserslautern | W912GB-12-C-0025 / 52029339 | 2898099 | 2898099 | 2019-08-01 | 2019-10-30
2016-04-04 | 2013 | DoD Education Activity | EU00043 |  | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817336 | 0 | 0 | 2017-06-21 | 2017-04-28
2016-04-04 | 2013 | DoD Education Activity | EU00043 | 33 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 43817338 | 3370754 | 3370754 | 2017-06-21 | 2017-04-28
2016-04-04 | 2013 | DoD Education Activity | EU00043 | 34 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 36086200 | 36324466 | 2017-06-21 | 2017-04-28
2016-04-04 | 2013 | DoD Education Activity | EU00043 | 35 | 2014-09-12 | 2015-03-25 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 635478 | 1083561 | 2017-06-21 | 2017-04-28
2016-04-04 | 2012 | DoD Education Activity | EU00053 |  | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 574911 | 574911 | 2015-03-10 | 2015-08-28
2016-04-04 | 2012 | DoD Education Activity | EU00053 | 25 | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11783771 | 12334944 | 2015-03-10 | 2015-08-28
2016-04-04 | 2012 | DoD Education Activity | EU00062 |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 282692 | 282692 | 2015-09-20 | 2016-01-01
2016-04-04 | 2012 | DoD Education Activity | EU00062 | 42 | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366274 | 5624572 | 2015-09-20 | 2016-01-01
2016-04-04 | 2010 | DoD Education Activity | EUR 8197 02 |  | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | W912GB-08-C-0046 / 14328568 | 15509459 | 17767938 | 2013-01-19 | 2013-09-25 | Remove at end of FY15
2016-04-04 | 2011 | DoD Education Activity | EUR 8268 02 |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869322 | 47502295 | 2015-04-30 | 2015-08-25
2016-04-04 | 2011 | DoD Education Activity | EUR 8268 02 | 13 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2015-04-30 | 2015-08-25
2016-04-04 | 2011 | DoD Education Activity | EUR 8268 02 | 14 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292874 | 2015-04-30 | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | EUR 8318 09 |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414633 | 33177784 | 2014-04-17 | 2014-07-04
2016-04-04 | 2010 | DoD Education Activity | EUR 8318 09 | 11 | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652185 | 1719194 | 2015-07-23 | 2013-01-04
2016-04-04 | 2010 | DoD Education Activity | EUR 8320 03 |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46694923 | 51260464 | 2015-04-30 | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | EUR 8320 03 | 8 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513913 | 2015-04-30 | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | EUR 8320 03 | 9 | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2015-04-30 | 2015-08-25
2016-04-04 | 2010 | DoD Education Activity | EUR826708 |  | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 17387653 | 58128307 | 58128307 | 2018-03-01 | 2018-06-04
2016-04-04 | 2010 | DoD Education Activity | EUR826708 | 3 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 39972656 | 3327125 | 3327125 | 2018-03-01 | 2018-06-04
2016-04-04 | 2010 | DoD Education Activity | EUR826708 | 4 | 2014-12-06 | 2015-05-13 | LBB Kaiserslautern | W912GB-12-C-0008 / 45239562 | 0 | 0 | 2018-03-01 | 2018-06-04
2016-04-04 | 2014 | DoD Education Activity | PA00018 |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28953797 | 30484381 | 2016-10-03 | 2016-12-10
2016-04-04 | 2012 | DoD Education Activity | PA00019 |  | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | W912HV-13-C-0002 / 29312081 | 9643581 | 9772878 | 2015-07-25 | 2015-10-18 | Remove at end of FY15
2016-04-04 | 2012 | DoD Education Activity | PA00020 |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187221 | 31583010 | 2015-12-09 | 2016-05-22
2016-04-04 | 2013 | DoD Education Activity | PA00021 |  | 2015-06-12 | 2016-02-19 | Nippo Corporation | W912HV-16-C-0004 / 32602254 | 47987000 | 47987000 | 2018-11-03 | 2018-11-03
2016-04-04 | 2012 | DoD Education Activity | PA00027 |  | 2014-07-25 | 2014-12-24 | Daiwa Odakyu Construction - JDC JV | W912HV-15-C-0002/ 29312181 | 40546769 | 40787340 | 2018-12-21 | 2019-04-09
2016-04-04 | 2014 | DoD Education Activity | PA00030 |  | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476284 | 96257596 | 2017-04-01 | 2017-06-20
2016-04-04 | 2013 | DoD Education Activity | PA00033 |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475000 | 1475000 | 2016-10-24 | 2017-03-26
2016-04-04 | 2013 | DoD Education Activity | PA00033 | 38 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469000 | 2469000 | 2016-10-24 | 2017-03-26
2016-04-04 | 2013 | DoD Education Activity | PA00033 | 39 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612000 | 4612000 | 2016-10-24 | 2017-03-26
2016-04-04 | 2013 | DoD Education Activity | PA00033 | 40 | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418175 | 63771356 | 2016-10-24 | 2017-03-26
2016-04-04 | 2014 | DoD Education Activity | PA00035 |  | 2014-09-23 | 2015-02-18 | Nippo Corporation | W912HV-15-C-0003 / 34596540 | 31459277 | 31607183 | 2016-10-02 | 2016-12-02
| 2013 | Marine Corps Active | M00146163 |  | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091000 | 28172000 | 2016-01-18 | 2016-07-09
| 2013 | Marine Corps Active | M00146601 |  | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0006 | 11782000 | 11763000 | 2015-04-08 | 2015-11-20
| 2012 | Marine Corps Active | M00146991 |  | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0003 | 14067000 | 17453000 | 2013-08-14 | 2014-11-24
| 2013 | Marine Corps Active | M00243313 |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974000 | 11531000 | 2015-04-29 | 2016-05-05
| 2014 | Marine Corps Active | M00243520 |  | 2015-01-29 | 2015-09-29 | MESA ENERGY SYSTEMS, INC. | N6247315C3602 AWD | 43778000 | 29319000 | 2018-01-11 | 2018-01-11
| 2013 | Marine Corps Active | M00263382 |  | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513000 | 11209000 | 2015-04-12 | 2016-01-31
| 2014 | Marine Corps Active | M002641406 |  | 2014-12-18 | 2015-05-01 | BISCAYNE CONTRACTORS, INC. | N4008015C2007 AWD | 4439000 | 4292000 | 2016-11-21 | 2016-11-21
| 2012 | Marine Corps Active | M00264543 |  | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0020 | 11118000 | 11318000 | 2014-03-28 | 2014-12-09
| 2013 | Marine Corps Active | M00264562 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462000 | 29126000 | 2016-11-06 | 2017-12-22
| 2012 | Marine Corps Active | M00264567 |  | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222000 | 23994000 | 2016-11-06 | 2017-12-22
| 2012 | Marine Corps Active | M00264571 |  | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | N4008010D0497 0011 | 6555000 | 8038000 | 2013-09-05 | 2015-06-12
| 2013 | Marine Corps Active | M00264572 |  | 2015-04-24 | 2015-09-30 | CORINTHIAN CONTRACTORS, INC | N4008015C0169 | 14182000 | 13364000 | 2017-05-28
| 2012 | Marine Corps Active | M00264611 |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 32910000 | 31760000 | 2014-10-16 | 2015-07-22
| 2012 | Marine Corps Active | M00264612 |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 5028000 | 5170000 | 2014-10-16 | 2015-07-22
| 2012 | Marine Corps Active | M00264621 |  | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081000 | 28513000 | 2015-03-15 | 2016-07-21
| 2012 | Marine Corps Active | M00264632 |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 60736000 | 61268000 | 2014-08-16 | 2015-08-17
| 2013 | Marine Corps Active | M00264644 |  | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168000 | 12094000 | 2015-04-22 | 2016-04-30
| 2014 | Marine Corps Active | M00264677 |  | 2015-10-28 | 2016-03-31 | HARKINS BUILDERS INC. | N4008016C0151 AWD | 27064000 | 25849000 | 2018-01-05 | 2018-01-05
| 2015 | Marine Corps Active | M00318778 |  | 2014-01-10 | 2015-03-13 | DAWSON-HAWAIIAN BUILDERS I | N6274215C1316 AWD | 14825000 | 12742000 | 2017-08-09 | 2017-08-09
| 2012 | Marine Corps Active | M00318822 |  | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 HC01 | 52970000 | 51558000 | 2014-03-17 | 2014-12-29
| 2014 | Marine Corps Active | M00318852 |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407000 | 17558000 | 2016-10-04 | 2016-10-04
| 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | HORIKAWA, NORINE E | N62742 15 C 1305 | 51071000 | 47445000 | 2018-03-31
| 2014 | Marine Corps Active | M0031886167 |  | 2014-07-31 | 2014-09-25 | CT JV | N6247814D4004 KB01 | 1667000 | 1673000 | 2015-07-07 | 2015-09-11
| 2014 | Marine Corps Active | M00318864 |  | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | N6274214C1315 AWD | 16968000 | 15301000 | 2015-09-09 | 2015-10-18
| 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720000 | 15187000 | 2016-12-18 | 2016-12-18
| 2013 | Marine Corps Active | M00318904 |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 63056000 | 57546000 | 2015-09-10 | 2015-09-29
| 2013 | Marine Corps Active | M00318905 |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 11118000 | 7860000 | 2015-09-10 | 2015-09-29
| 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 47645000 | 24543000 | 2017-01-03 | 2017-01-03
| 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 53999000 | 43927000 | 2017-01-03 | 2017-01-03
| 2015 | Marine Corps Active | M00318924 |  | 2014-12-01 | 2015-09-28 | DAWSON TECHNICAL LLC | N62742 15 C 1306 | 2197000 | 2082000 | 2016-09-26
| 2012 | Marine Corps Active | M006811037 |  | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0002-PC000002 | 11746000 | 9691000 | 2013-01-21 | 2013-08-05
| 2012 | Marine Corps Active | M006811040 |  | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | N6247309D1606 0009 | 11432000 | 14119000 | 2013-09-27 | 2014-06-24
| 2012 | Marine Corps Active | M006811045 |  | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242000 | 69031000 | 2016-03-31 | 2016-03-31
| 2013 | Marine Corps Active | M006811132 |  | 2014-11-18 | 2016-03-24 | BETHEL-WEBCOR JV-1 | N6247316C0606 AWD | 78418000 | 73988000 | 2020-01-23 | 2020-01-23
| 2013 | Marine Corps Active | M006811176 |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428000 | 4405000 | 2016-04-21 | 2016-06-17
| 2012 | Marine Corps Active | M00681532 |  | 2012-04-23 | 2012-08-31 | A&D GC INC | N6247309D1658 0006 | 11201000 | 10486000 | 2013-12-24 | 2014-12-23
| 2014 | Marine Corps Active | M00681970 |  | 2014-07-01 | 2015-12-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0012 | 37184000 | 17747000 | 2018-04-27 | 2018-04-27
| 2013 | Marine Corps Active | M60169427 |  | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | N6945013D1761 0001 | 11042000 | 10871000 | 2014-08-14 | 2015-01-20
| 2012 | Marine Corps Active | M60169442 |  | 2011-12-06 | 2012-03-30 | HEAD, INC. | N6945012C1758 AWD | 18987000 | 18048000 | 2013-08-07 | 2013-09-27
| 2013 | Marine Corps Active | M60169456 |  | 2012-08-27 | 2013-06-26 | HEAD, INC. | N6945013C1773 AWD | 12302000 | 12638000 | 2014-07-11 | 2015-12-29
| 2013 | Marine Corps Active | M60169465 |  | 2012-11-15 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643000 | 38604000 | 2016-09-08 | 2017-02-15
| 2013 | Marine Corps Active | M60169472 |  | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | N6945013C1772 AWD | 11043000 | 13306000 | 2014-03-28 | 2015-10-24
| 2012 | Marine Corps Active | M62204925 |  | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | N6247309D1616 0009 | 7970000 | 7894000 | 2013-09-27 | 2014-04-09
| 2015 | Marine Corps Active | M62204939 |  | 2015-01-14 | 2015-03-31 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0003 | 15300000 | 14416000 | 2016-10-06 | 2016-10-06
| 2012 | Marine Corps Active | M626130601 |  | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | N4008412D6501 0002 | 13357000 | 12685000 | 2013-11-23 | 2013-12-14
| 2013 | Marine Corps Active | M626130901 |  | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | N4008414C5500 AWD | 17551000 | 16715000 | 2015-10-13 | 2015-10-13
| 2012 | Marine Corps Active | M626131001 |  | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | N4008412D6501 0004 | 11335000 | 10958000 | 2014-12-20 | 2015-02-02
| 2015 | Marine Corps Active | M626131502 |  | 2015-07-15 | 2015-09-27 | NIPPO CORPORATION | N4008415C0009 AWD | 14308000 | 13569000 | 2017-01-30 | 2017-01-30
| 2013 | Marine Corps Active | M62613995 |  | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT | N6274214MP00027 | 4947000 | 4926000 | 2015-06-14 | 2015-06-14
| 2013 | Marine Corps Active | M62613996 |  | 2014-04-07 | 2014-07-25 | NAVY STANDARD DOCUMENT | N6274214MP00039 | 6304000 | 6304000 | 2015-09-24 | 2015-09-24
| 2013 | Marine Corps Active | M62974378 |  | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316000 | 13656000 | 2015-07-31 | 2016-09-26
| 2012 | Marine Corps Active | M62974535 |  | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | N6247308D8617 0004 | 32048000 | 32711000 | 2014-07-07 | 2015-06-27
| 2012 | Marine Corps Active | M62974545 |  | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0003 | 79917000 | 79669000 | 2014-05-20 | 2014-12-03
| 2013 | Marine Corps Active | M62974566 |  | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247309D1603 0013 | 12671000 | 12136000 | 2014-09-22 | 2015-07-26
| 2012 | Marine Corps Active | M62974575 |  | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | N6247312C1802 AWD | 29475000 | 28959000 | 2013-06-25 | 2014-01-31
| 2013 | Marine Corps Active | M67001003 |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260000 | 29159000 | 2015-09-01 | 2016-05-18
| 2012 | Marine Corps Active | M67001030 |  | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0003 | 16292000 | 12459000 | 2014-05-17 | 2015-01-24
| 2012 | Marine Corps Active | M670011253 |  | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | N4008512C7719 AWD | 74707000 | 72488000 | 2014-07-24 | 2016-03-02
| 2014 | Marine Corps Active | M670011349 |  | 2014-02-27 | 2015-08-31 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0014 | 25742000 | 24416000 | 2017-03-21 | 2017-03-21
| 2014 | Marine Corps Active | M670011353 |  | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529000 | 14060000 | 2016-03-01 | 2016-03-01
| 2012 | Marine Corps Active | M67001138 |  | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101000 | 26883000 | 2014-07-29 | 2016-08-31
| 2012 | Marine Corps Active | M670011383 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235000 | 66051000 | 2015-04-18 | 2016-09-14
| 2013 | Marine Corps Active | M670011384 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666000 | 36921000 | 2015-04-18 | 2016-09-14
| 2012 | Marine Corps Active | M670011425 |  | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008511D8026 0008 | 2276000 | 2215000 | 2014-04-17 | 2014-11-29
| 2014 | Marine Corps Active | M670011445 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 2123000 | 2250000 | 2017-02-04 | 2017-04-20
| 2014 | Marine Corps Active | M670011447 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 9605000 | 9188000
| 2014 | Marine Corps Active | M670011448 |  | 2014-03-31 | 2015-01-23 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0006 | 15756000 | 15145000
| 2014 | Marine Corps Active | M67001674 |  | 2014-02-03 | 2015-08-19 | BRISTOL GENERAL CONTRACTORS, LLC | N4008515C0320 AWD | 17032000 | 16149000 | 2017-03-11 | 2017-03-11
| 2014 | Marine Corps Active | M67001676 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312000 | 13461000 | 2015-12-20 | 2016-03-30
| 2012 | Marine Corps Active | M67001705 |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 57582000 | 65129000 | 2014-07-07 | 2015-08-11
| 2012 | Marine Corps Active | M67001710 |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 7768000 | 7390000 | 2014-07-07 | 2015-08-11
| 2013 | Marine Corps Active | M67001711 |  | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0018 | 6449000 | 6213000 | 2015-07-06 | 2016-04-16
| 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159000 | 10081000 | 2015-12-20 | 2016-03-30
| 2014 | Marine Corps Active | M67004934 |  | 2013-12-06 | 2014-09-10 | BLUEFORGE, LLC | N6945014D1271 0001 | 14685000 | 14360000 | 2016-01-25 | 2016-01-25
| 2014 | Marine Corps Active | M67004954 |  | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | N6945012D1769 0005 | 1248000 | 1193000 | 2015-06-02 | 2015-06-02
| 2012 | Marine Corps Active | M67399105 |  | 2012-03-06 | 2012-06-15 | ALLEN ENGINEERING CONTRACTOR, INC | N6247309D1654 0005 | 13925000 | 13442000 | 2014-03-22 | 2014-03-22
| 2015 | Marine Corps Active | M67399159 |  | 2015-01-30 | 2015-04-15 | RQ-BERG JV | N6247310D5482 0009 | 28644000 | 27080000 | 2017-05-01 | 2017-05-01
| 2012 | Marine Corps Active | M67399177 |  | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819000 | 20254000 | 2014-09-02 | 2016-09-20
| 2012 | Marine Corps Active | M67399212 |  | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | N6247310D5412 0006 | 21313000 | 20668000 | 2013-12-12 | 2016-02-01
| 2012 | Marine Corps Active | M67399541 |  | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | N6247309D1655 0003 | 15610000 | 15591000 | 2014-04-20 | 2016-04-20
| 2012 | Marine Corps Active | M67399991 |  | 2015-01-14 | 2015-01-15 | NAVY STANDARD DOCUMENT | N6247314MPRM002 | 2249000 | 2092000
| 2014 | Marine Corps Active | M67400201 |  | 2013-11-08 | 2014-04-18 | NAVY STANDARD DOCUMENT | N6274214MP00024 | 2881000 | 2761000 | 2015-10-26 | 2015-10-26
| 2013 | Marine Corps Active | M67400305 |  | 2013-07-10 | 2014-09-25 | NAVY STANDARD DOCUMENT | N6274214MP00043 | 1729000 | 1719000 | 2015-06-29 | 2015-06-29
| 2015 | Marine Corps Active | M67400803 |  | 2015-08-21 | 2015-12-22 | NAVY STANDARD DOCUMENT | USACE | 19643000 | 19643000 | 2017-09-12 | 2017-09-12
| 2013 | Marine Corps Active | M67604113 |  | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | N6247309D1619 0008 | 4380000 | 4121000 | 2014-09-21 | 2014-09-21
| 2012 | Marine Corps Active | M67604114 |  | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0004 | 40539000 | 39504000 | 2015-08-10 | 2015-12-29
| 2012 | Marine Corps Active | M67604116 |  | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | N6247309D1605 0012 | 14938000 | 12114000 | 2014-01-03 | 2015-03-27
| 2012 | Marine Corps Active | M67604117 |  | 2013-08-01 | 2013-11-07 | AUSTIN BROCKENBROUGH ASSOC., L.L.P. | N6247007D7000 FZN7 | 7437000 | 7219000 | 2016-04-29 | 2016-10-14
| 2012 | Marine Corps Active | M678611201 |  | 2012-01-03 | 2012-01-04 | NAVY STANDARD DOCUMENT | TBD | 45000 | 45000
| 2013 | Marine Corps Active | M67865181 |  | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0002 | 13634000 | 15102000 | 2015-09-28 | 2016-05-20
| 2013 | Marine Corps Active | N41557101A |  | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | N6274210D1309 JQ01 | 24305000 | 19425000 | 2015-07-12 | 2016-06-12
| 2014 | Marine Corps Active | N41557109 |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820000 | 57168000 | 2016-12-03 | 2016-12-21
| 2014 | Marine Corps Active | N41557J200 |  | 2014-10-16 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 | 53014000 | 47830000 | 2016-09-02 | 2016-09-02
| 2014 | Marine Corps Active | N61755H106 |  | 2013-11-14 | 2015-04-30 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 0002 | 24771000 | 23121000 | 2017-08-13 | 2017-08-13
| 2013 | Marine Corps Active | N69212984 |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028000 | 11014000 | 2015-06-26 | 2016-09-04
| 2013 | Marine Corps Active | N69212985 |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418000 | 17973000 | 2015-06-26 | 2016-09-04
| 2013 | Marine Corps Active | N69212986 |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 5841000 | 5970000 | 2015-03-23 | 2015-04-19
| 2013 | Marine Corps Active | N69212987 |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 6987000 | 6826000 | 2015-03-23 | 2015-04-19
| 2013 | Marine Corps Active | N69212989 |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 3653000 | 3599000 | 2015-03-23 | 2015-04-19
| 2014 | Marine Corps Reserve | M67386139 |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019000 | 16343000 | 2016-02-23 | 2016-02-23
| 2012 | Marine Corps Reserve | M68479030 |  | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | N4008313C0019 AWD | 9006000 | 8571000 | 2015-02-17 | 2015-02-17
| 2013 | Marine Corps Reserve | M68479130 |  | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911000 | 4934000 | 2014-12-04 | 2015-10-13
| 2012 | Marine Corps Reserve | N00206501 |  | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | N6945013C5571 AWD | 1286000 | 1237000 | 2014-05-22 | 2014-06-20
| 2015 | Marine Corps Reserve | N00620234 |  | 2014-12-30 | 2015-07-29 | SWINERTON BUILDERS | N4425515C6001 AWD | 29746000 | 28482000 | 2016-12-15 | 2016-12-15
2016-03-31 | 2010 | Missile Defense Agency | 627 |  | 2011-06-30 | 2011-08-03 | TOMCO CORP. | N62478-10-D-4024 | 294000 | 294000 | 2011-11-18 | 2011-11-18 | Clearing and Grubbing Only
2016-03-31 | 2010 | Missile Defense Agency | 627 | 1 | 2012-01-19 | 2012-06-04 | URS GROUP, INC | N62742-09-D-1174 | 59616000 | 69657000 | 2013-09-12 | 2013-11-07 | GMAC Construction - awaiting final 1354
2016-03-31 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 114560000 | 2015-08-30 | 2016-05-01 | Receiving individual facility Interim 1354s; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2016-03-31 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 63176613 | 2015-08-30 | 2016-05-01 | Receiving individual facility Interim 1354s; 2853 notification made 10 Apr 2015. ATR request to congress approved on 22 May 2015.
2016-03-31 | 2012 | Missile Defense Agency | 633 |  | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | W91278-12-C-0017 | 51330000 | 59842000 | 2014-07-10 | 2014-10-15 | Awaiting Final 1354
2016-03-31 | 2014 | Missile Defense Agency | 634 |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300000 | 14846628 | 2016-01-06 | 2016-01-06 | Interim 1354 received on 2/16/2016. Awaiting Final 1354.
2016-03-31 | 2013 | Missile Defense Agency | 639 |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584000 | 16006511 | 2014-11-28 | 2015-09-12 | Awaiting Final 1354
2016-03-31 | 2016 | Missile Defense Agency | 640 |  | 2015-06-10 | 2016-02-10 | AMEC PROGRAMS, INC. | W912GB-16-C-0005 | 141906057 | 151129950 | 2018-03-30 | 2018-03-30 | Contract award includes base plus 4 options.
2016-03-31 | 2014 | Missile Defense Agency | 648 |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991000 | 14975122 | 2015-01-09 | 2015-02-20 | Site ID is pending as this is a new Installation. Awaiting signed final 1354
2016-03-31 | 2014 | Missile Defense Agency | 649 |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838000 | 48347415 | 2016-05-31 | 2016-05-31 | Construction re-mobilized on 23 March 2015; Awaiting Interim 1354
2016-03-31 | 2016 | Missile Defense Agency | 661 |  | 2015-07-16 | 2016-02-05 | BRICE ENVIRONMENTAL SERVICES CORPORATION | FA8903-16-C-0001 | 1637189 | 1637189 | 2016-08-31 | 2016-08-31 | Materials barge is due to arrive on 24 May 2016.
2016-02-10 | 2015 | National Geospatial-Intelligence Agency | 030 |  | 2015-09-14 | 2015-11-23 | Greenway Enterprises, Inc. | W912DR-13-D-0023 | 6098135.18 | 6098135.18 | 2016-09-25 | 2016-09-25
2015-06-01 | 2008 | National Geospatial-Intelligence Agency | 65416 |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture | W912DR-07-C-0027 | 1409901000 | 1467244000 | 2011-12-22 | 2015-11-21 | ["N/A" for Diverted Funds Amount]
2015-06-01 | 2012 | National Geospatial-Intelligence Agency | NGA013 |  | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty-NCE, A Joint Venture | W912DR-12-C-0027 | 32387000 | 39495000 | 2014-01-02 | 2015-01-31 | Technology Center Third Floor Fit-out - project period of performance extended to 31 May 2015
2015-06-01 | 2012 | National Geospatial-Intelligence Agency | NGA021 |  | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors | W912DQ-12-D-4002 | 8202000 | 11198000 | 2013-08-06 | 2015-01-31 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 30 September 2015
2016-03-31 | 2010 | National Security Agency | 17781 |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700000 | 11700000 | 2011-08-20 | 2012-05-30
2016-03-31 | 2010 | National Security Agency | 17782 |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200000 | 3200000 | 2013-07-13 | 2015-11-30 | Storage Tank is being constructed and expected to be complete 100% up and running 3 December barring any additional weather events.
2016-03-31 | 2011 | National Security Agency | 17866 |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900000 | 130751000 | 2014-11-30 | 2015-10-31 | Working in minor change orders and waiting for the demolition.
2016-03-31 | 2010 | National Security Agency | 17872 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223000 | 129078000 | 2014-04-18 | 2015-10-12
2016-03-31 | 2010 | National Security Agency | 18052 |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566000 | 8257000 | 2013-02-01 | 2014-05-14
2016-03-31 | 2010 | National Security Agency | 18053 |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095000 | 16448000 | 2013-02-01 | 2014-05-31
2016-03-31 | 2010 | National Security Agency | 18054 |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085000 | 7316000 | 2013-02-01 | 2014-08-31 | Commissioning of system completed November 26, 2014.
2016-03-31 | 2011 | National Security Agency | 20489 |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657000 | 8867000 | 2014-01-30 | 2015-01-16
2016-03-31 | 2011 | National Security Agency | 20489 | 2 | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620000 | 2657000 | 2014-02-28 | 2014-04-28
2016-03-31 | 2009 | National Security Agency | 21120 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060000 | 13760000 | 2013-01-17 | 2014-04-18
2016-03-31 | 2010 | National Security Agency | 21372 |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443000 | 4201000 | 2011-09-26 | 2012-06-29
2016-03-31 | 2012 | National Security Agency | 23051 |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975000 | 131954362 | 2015-05-03 | 2016-01-01 | BOD issued on 28 July 2015. Working on final submittal, O&Ms, As-Builts.
2016-03-31 | 2012 | National Security Agency | 23051 | 2 | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621000 | 5621000 | 2014-02-14 | 2015-09-30
2016-03-31 | 2011 | National Security Agency | 23994 |  | 2012-04-26 | 2012-06-18 | JAAAT | W912HN-10-D-0063 | 15315000 | 16526000 | 2014-01-30 | 2014-12-23
2016-03-31 | 2012 | National Security Agency | 24649 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589000 | 605470545 | 2015-09-15 | 2016-02-08 | Interior bulding turnover completed. Commissioning activities are operating under escort conditions. Client telecommunications fit up activities are ongoing.
2016-03-31 | 2010 | National Security Agency | 25047 |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253000 | 5792000 | 2014-03-07 | 2015-05-04 | Waiting for MDE approval for the removal of the ES&C measures.
2016-03-31 | 2013 | National Security Agency | 26170 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91777000 | 98827869 | 2015-10-11 | 2016-06-11 | Data from RMS run 31 Mar 2016.
2016-02-29 | 2015 | National Security Agency | 27532 |  | 2015-06-30 | 2015-09-29 | Hensel-Phelps | W912DR-15-D-0032 | 40667766 | 40667766 |  |  | Contract Awarded 9/29/15. Protest received 10/19/15. Protest was withdrawn. A Correction Action Amendment was sent to the Contractors with a letter discussing the offeror's proposal weaknesses. Offerors submitted new proposal. Proposals went through review boards. Contractor was selected. The Source Selection Decision Document is currently in review with the PARC. Still waiting for approval. Award pushed out to mid-April 2016.
| 2015 | Navy Active | M00146996 |  | 2015-06-04 | 2015-09-02 | WHITING-TURNER CONTRACTING CO | N4008510D5330 | 1350000 | 1311000 | 2017-03-31
| 2012 | Navy Active | M006811046 |  | 2014-08-28 | 2014-11-25 | ORION CONSTRUCTION CORPORATION | N6247310D5419 0012 | 75135000 | 44182000 | 2016-12-08 | 2016-12-08
| 2014 | Navy Active | M626131403 |  | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545000 | 15632000 | 2016-02-02 | 2016-02-02
| 2015 | Navy Active | M62613602 |  | 2014-11-21 | 2015-04-30 | NAVY STANDARD DOCUMENT | N6274215MP00014 | 4913000 | 4972000 | 2016-06-24 | 2016-06-24
| 2014 | Navy Active | M678611407 |  | 2014-07-17 | 2014-09-30 | QUALITY SUPPORT SERVICES, INC. | N4008314D1014 0003 | 75000 | 93000 | 2014-11-30 | 2015-07-30
| 2012 | Navy Active | N00128816 |  | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491000 | 80169000 | 2016-06-30 | 2016-06-30
| 2012 | Navy Active | N00204791 |  | 2012-07-25 | 2012-09-29 | R L BURNS INC. | N6945012C6343 AWD | 2038000 | 1975000 | 2013-08-08 | 2013-08-08
| 2012 | Navy Active | N00207153 |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 2851000 | 2936000 | 2013-12-17 | 2014-04-09
| 2016 | Navy Active | N00207334 |  | 2015-11-06 | 2016-03-18 | HICAPS, INC. | N69450 14 D 1275 | 5881000 | 5601000 | 2017-06-11 | 2017-06-11
| 2012 | Navy Active | N00207624 |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 14194000 | 13912000 | 2013-12-17 | 2014-04-09
| 2015 | Navy Active | N00207631 |  | 2014-04-01 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 11078000 | 11633000 | 2016-04-19 | 2016-06-26
| 2012 | Navy Active | N00207654 |  | 2012-12-20 | 2015-03-20 | HCR CONSTRUCTION INC | N6945015C1102 AWD | 6448000 | 5683000 | 2016-05-17 | 2016-06-04
| 2013 | Navy Active | N00207655 |  | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | N6945013C1257 AWD | 18180000 | 19328000 | 2014-12-27 | 2015-12-08
| 2014 | Navy Active | N00207659 |  | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573000 | 10597000 | 2016-04-19 | 2016-06-26
| 2015 | Navy Active | N00207664 |  | 2015-01-26 | 2015-04-30 | PHOENIX CONSTRUCTION SERVICES, INC. | N6945015C1104 AWD | 7293000 | 7222000 | 2016-04-30 | 2016-10-12
| 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151000 | 13948000 | 2016-01-07 | 2016-01-07
| 2013 | Navy Active | N00245500 |  | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553000 | 47775000 | 2015-10-24 | 2016-05-13
| 2015 | Navy Active | N00245800 |  | 2015-06-15 | 2015-09-17 | S & R CONSTRUCTIONA JOINT VENTURE | N6247315C1604 AWD | 41838000 | 38420000 | 2017-10-01 | 2017-10-01
| 2012 | Navy Active | N00246705 |  | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | N6247310D5409 0013 | 46630000 | 44494000 | 2015-03-16 | 2015-08-26
| 2013 | Navy Active | N00246730 |  | 2013-05-29 | 2015-07-30 | HENSEL PHELPS CONSTRUCTION CO | N6247315C1614 AWD | 72648000 | 70918000 | 2017-07-29 | 2017-09-14
| 2012 | Navy Active | N00246880 |  | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977000 | 57929000 | 2015-03-30 | 2015-10-18
| 2012 | Navy Active | N00246896 |  | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | N6247311D0067 0004 | 1816000 | 1745000 | 2014-01-31 | 2014-10-17
| 2013 | Navy Active | N00246909 |  | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088000 | 2955000 | 2015-03-15 | 2015-05-14
| 2014 | Navy Active | N00246957 |  | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904000 | 8568000 | 2016-02-10 | 2016-03-24
| 2015 | Navy Active | N00246987 |  | 2015-07-14 | 2015-09-16 | BUENA VISTA CONTRACTING INC | N6247315C1613 AWD | 906000 | 865000 | 2016-09-19 | 2016-09-19
| 2016 | Navy Active | N00246998 |  | 2015-07-29 | 2016-01-19 | RQ-DPR JV | N6247315C1609 | 3443000 | 3279000 | 2018-04-02 | 2018-09-30
| 2014 | Navy Active | N00620239 |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY | N4425514C5004 AWD | 29692000 | 27719000 | 2017-05-26 | 2017-05-26
| 2013 | Navy Active | N00620245 |  | 2013-06-12 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0009 | 5679000 | 5973000 | 2014-11-25 | 2015-03-11
| 2013 | Navy Active | N00620246 |  | 2013-06-18 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | N4425513C7005 AWD | 1120000 | 1076000 | 2014-09-30 | 2014-12-19
| 2014 | Navy Active | N00620251 |  | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY | N4425514C5002 AWD | 84889000 | 81589000 | 2016-01-12 | 2016-03-25
| 2014 | Navy Active | N00620257 |  | 2014-06-20 | 2014-09-02 | RORE, INC. | N4425514C8012 | 1424000 | 1392000
| 2013 | Navy Active | N32411056 |  | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | N4008510D9450 0006 | 2332000 | 2332000 | 2013-10-31 | 2013-12-13
| 2014 | Navy Active | N32411103 |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319000 | 13304000 | 2015-12-16 | 2016-01-01
| 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 AWD | 34317000 | 33420000 | 2016-11-23 | 2016-11-23
| 2012 | Navy Active | N32443383 |  | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576000 | 34792000 | 2014-09-28 | 2015-06-15
| 2015 | Navy Active | N32443527 |  | 2014-12-19 | 2015-09-03 | WHITESELL-GREEN, INC. | N4008513D7776 0007 | 11256000 | 10557000 | 2017-04-20 | 2017-04-20
| 2013 | Navy Active | N32443998 |  | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374000 | 29994000 | 2015-12-27 | 2016-03-13
| 2014 | Navy Active | N32446266 |  | 2013-12-30 | 2015-08-17 | METHUEN CONSTRUCTION CO., INC | N4008515C8746 AWD | 31542000 | 29924000 | 2018-01-23 | 2018-01-23
| 2015 | Navy Active | N3379A064 |  | 2015-03-12 | 2015-09-11 | ZAFER TAAJJIT OMSAAT VE TOCARET A S | N62470 15 C 5006 | 1407000 | 1367000 | 2017-01-16
| 2014 | Navy Active | N3379A227 |  | 2014-02-26 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492000 | 4248000 | 2015-09-28 | 2016-06-29
| 2015 | Navy Active | N3379A330 |  | 2015-03-12 | 2015-09-11 | ZAFER TAAJJIT OMSAAT VE TOCARET A S | N6247015C5006 AWD | 8104000 | 7704000 | 2017-01-18 | 2017-01-18
| 2014 | Navy Active | N3379A921 |  | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714000 | 19670000 | 2016-05-30 | 2016-07-25
| 2015 | Navy Active | N41557230 |  | 2015-04-02 | 2015-11-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6247013C3000 | 20799000 | 15452000 | 2018-06-11 | 2018-06-11
| 2015 | Navy Active | N41557240 |  | 2015-06-16 | 2015-09-29 | WATTS CONSTRUCTORS, LLC | N6274215C1303 | 27345000 | 16958000 | 2018-05-02 | 2018-05-02
| 2014 | Navy Active | N41557625 |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710000 | 49870000 | 2016-04-25 | 2017-01-16
| 2015 | Navy Active | N42237099 |  | 2014-02-24 | 2015-07-22 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 | 38595000 | 38553000
| 2014 | Navy Active | N42237100 |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249000 | 124626000 | 2018-06-20 | 2018-04-22
| 2012 | Navy Active | N42237636 |  | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167000 | 54753000 | 2017-04-16 | 2017-04-16
| 2015 | Navy Active | N47608155 |  | 2015-04-30 | 2015-09-29 | G-W MANAGEMENT SERVICES, LLC | N4008015C0168 AWD | 11273000 | 10643000 | 2017-08-20 | 2017-08-20
| 2014 | Navy Active | N47608262 |  | 2014-08-11 | 2014-09-29 | REILLY CONSTRUCTION, INC | N4008014D3014 0001 | 1453000 | 1678000 | 2016-09-29 | 2017-04-29
| 2012 | Navy Active | N47608561 |  | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49890000 | 48828000 | 2016-04-01 | 2016-06-23
| 2013 | Navy Active | N47609003 |  | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | N6247313D4608 0007 | 1896000 | 1809000 | 2015-06-26 | 2015-06-26
| 2012 | Navy Active | N50092199 |  | 2012-10-31 | 2012-12-14 | JESSICO, INC | N4008511D3021 0008 | 970000 | 938000 | 2013-11-08 | 2013-11-15
| 2013 | Navy Active | N50092255 |  | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008513C7711 AWD | 1925000 | 1890000 | 2013-08-30 | 2013-09-29
| 2015 | Navy Active | N50092354 |  | 2015-07-31 | 2015-09-28 | HOURIGAN-SUNDT, A JOINT VENTURE | N4008515C0011 AWD | 40638000 | 38222000 | 2018-10-07 | 2018-10-07
| 2012 | Navy Active | N50092499 |  | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | N4008512C1704 AWD | 29520000 | 28699000 | 2014-10-09 | 2015-08-01
| 2014 | Navy Active | N50092662 |  | 2014-05-09 | 2014-08-06 | DOYON MANAGEMENT SERVICES, LLC | N4008514D2102 0001 | 1020000 | 241000 | 2014-11-21 | 2015-01-20
| 2012 | Navy Active | N57095197 |  | 2012-04-17 | 2012-09-20 | SAUER, INC. | N4008509D5026 0004 | 27161000 | 27157000 | 2015-05-08 | 2015-07-07
| 2013 | Navy Active | N60191513 |  | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430000 | 29642000 | 2015-12-16 | 2016-04-06
| 2012 | Navy Active | N60191527 |  | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599000 | 19664000 | 2014-10-12 | 2015-05-07
| 2013 | Navy Active | N60191582 |  | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0003 | 4129000 | 4849000 | 2013-11-29 | 2014-06-27
| 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446000 | 11572000 | 2016-10-25 | 2017-04-04
| 2014 | Navy Active | N60201425 |  | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | N6945013D1765 0002 | 15842000 | 15540000 | 2015-11-26 | 2016-04-27
| 2012 | Navy Active | N60201503 |  | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | N6945012C0757 AWD | 7518000 | 10334000 | 2014-02-21 | 2015-03-02
| 2013 | Navy Active | N60241288 |  | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | N6945014C0763 AWD | 1790000 | 1701000 | 2015-03-27 | 2015-05-27
| 2012 | Navy Active | N60241294 |  | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | N6945010D0776 0002 | 1658000 | 1549000 | 2014-03-21 | 2014-08-25
| 2015 | Navy Active | N60495420 |  | 2015-07-17 | 2015-09-16 | STRAUB CONSTRUCTION, INC. | N6247315D2427 0002 | 25541000 | 24414000 | 2017-11-24 | 2018-11-24
| 2015 | Navy Active | N60508278 |  | 2015-04-08 | 2015-08-19 | NAVY STANDARD DOCUMENT | N6247015MPS0050 | 1367000 | 1364000 | 2016-02-16 | 2016-04-28
| 2012 | Navy Active | N60508927 |  | 2012-02-17 | 2012-06-07 | NAVY STANDARD DOCUMENT | N6247012MPS0048 | 18810000 | 20636000 | 2015-11-24 | 2015-11-24
| 2012 | Navy Active | N61014851 |  | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | N6247314C2801 AWD | 1916000 | 1895000 | 2014-10-17 | 2014-12-31
| 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458000 | 9458000 | 2017-01-17 | 2017-01-17
| 2012 | Navy Active | N610541201 |  | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | N4008412C0108 AWD | 19730000 | 18773000 | 2014-01-13 | 2014-01-13
| 2012 | Navy Active | N610541202 |  | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | N4008412C0109 AWD | 9033000 | 9298000 | 2014-10-07 | 2015-06-10
| 2013 | Navy Active | N610541305 |  | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791000 | 7305000 | 2016-02-21 | 2016-02-21
| 2013 | Navy Active | N61056353 |  | 2013-01-24 | 2013-09-27 | NAVY STANDARD DOCUMENT | N6274213MP00015 | 5627000 | 5521000 | 2015-01-12 | 2015-01-12
| 2012 | Navy Active | N610571201 |  | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | N4008412C8325 AWD | 5990000 | 5654000 | 2013-08-26 | 2013-11-22
| 2012 | Navy Active | N610571202 |  | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | N4008412C0004 AWD | 17540000 | 14246000 | 2013-12-09 | 2014-07-01
| 2013 | Navy Active | N610571302 |  | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | N4008414C8401 AWD | 12958000 | 12051000 | 2015-03-31 | 2015-05-05
| 2014 | Navy Active | N61057221 |  | 2014-06-12 | 2014-08-06 | NIHON MECCS CO., LTD. | N4008414C8302 AWD | 890000 | 812000 | 2015-02-03 | 2015-05-19
| 2014 | Navy Active | N610581401 |  | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799000 | 21637000
| 2012 | Navy Active | N61064400 |  | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | N6247811D4046 0005 | 6498000 | 5907000 | 2014-01-02 | 2014-12-31
| 2013 | Navy Active | N61065229 |  | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447000 | 28008000 | 2016-04-17 | 2016-06-16
| 2014 | Navy Active | N61065240 |  | 2015-02-23 | 2015-04-16 | TEEHEE ENGINEERING, INC. | N6247315C4204 AWD | 1950000 | 1892000 | 2016-10-21 | 2016-10-21
| 2016 | Navy Active | N61066603 |  | 2015-08-19 | 2016-02-05 | NORTH STAR CONSTRUCTION &ENGINEERING, INC | N4425515D0018 0004 | 5585000 | 5275000 | 2017-03-06 | 2017-03-06
| 2013 | Navy Active | N61077123 |  | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | N4008413C9001 AWD | 755000 | 768000 | 2013-03-10 | 2013-03-10
| 2012 | Navy Active | N61151222 |  | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984000 | 69578000 | 2016-07-14 | 2016-07-14
| 2015 | Navy Active | N61151287 |  | 2015-03-04 | 2015-09-02 | M A MORTENSON COMPANY | N4008015C0167 AWD | 25679000 | 24495000 | 2017-07-17 | 2018-05-08
| 2013 | Navy Active | N61151290 |  | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0007 | 14130000 | 14375000 | 2015-03-12 | 2015-12-03
| 2013 | Navy Active | N61151372 |  | 2012-12-12 | 2013-09-27 | NAVY STANDARD DOCUMENT | N4008010D0302 0021 | 11409000 | 10996000 | 2015-05-02 | 2015-12-18
| 2014 | Navy Active | N61152001 |  | 2014-01-13 | 2015-04-13 | NAVY STANDARD DOCUMENT | N6247015MPC0032 | 109736000 | 106597000 | 2017-05-04 | 2017-05-04
| 2015 | Navy Active | N61152621 |  | 2015-07-15 | 2016-03-31 | TURNER CONSTRUCTION COMPANY | N40080 16 C 0156 | 11293000 | 113935000 | 2019-03-22 | 2019-03-22
| 2013 | Navy Active | N617551301 |  | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 JQ02 | 26805000 | 25414000 | 2015-09-09 | 2015-10-10
| 2014 | Navy Active | N617551403 |  | 2013-11-14 | 2015-04-30 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 0002 | 24771000 | 23129000 | 2017-08-13 | 2017-08-13
| 2014 | Navy Active | N61755425 |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865000 | 49745000 | 2016-06-11 | 2017-04-20
| 2014 | Navy Active | N61755518 |  | 2014-06-02 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085000 | 44997000 | 2016-10-20 | 2017-03-15
| 2014 | Navy Active | N61755566 |  | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860000 | 28700000 | 2016-05-12 | 2016-06-29
| 2014 | Navy Active | N61755630 |  | 2014-07-01 | 2014-09-30 | P&S CONSTRUCTION, INC. | N4019210D2804 0019 | 2000000 | 1937000 | 2015-12-24 | 2015-12-24
| 2014 | Navy Active | N61755637 |  | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170000 | 14520000 | 2016-04-11 | 2016-05-09
| 2014 | Navy Active | N61755638 |  | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | N4019210D2808 0009 | 1462000 | 1232000 | 2015-03-26 | 2015-04-25
| 2013 | Navy Active | N62590400 |  | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | N6247014MPE0025 | 40018000 | 39312000
| 2012 | Navy Active | N62688123 |  | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | N4008512C4572 AWD | 74854000 | 72343000 | 2014-09-13 | 2015-07-16
| 2014 | Navy Active | N62688500 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365000 | 1623000 | 2016-01-01 | 2016-08-06
| 2016 | Navy Active | N62688518 |  | 2015-11-23 | 2016-03-03 | SYNCON, LLC | N4008514D8152 0007 | 4575000 | 4357000 | 2017-09-29 | 2017-09-29
| 2016 | Navy Active | N62813036 |  | 2015-10-28 | 2016-01-26 | BETHEL-WEBCOR JV-1 | N6247814D4001 KB01 | 8520000 | 7870000 | 2018-03-26 | 2018-04-29
| 2012 | Navy Active | N62813041 |  | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | N6247810D4022 0019 | 7708000 | 7630000 | 2013-11-16 | 2014-11-09
| 2015 | Navy Active | N62813048 |  | 2014-10-20 | 2015-02-27 | JSR ECC, LLC | N6247814D4003 KB01 | 8667000 | 8128000 | 2016-10-04 | 2016-10-04
| 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810000 | 2656000 | 2016-05-18 | 2016-05-18
| 2014 | Navy Active | N62813270 |  | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355000 | 20428000 | 2015-12-11 | 2015-12-11
| 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970000 | 32009000 | 2017-08-03 | 2017-12-18
| 2012 | Navy Active | N628631201 |  | 2014-04-29 | 2015-03-13 | SOCIEDAD ESPNOLA DE MONTAJES INDUSTRIALES SA DBA SEMI | 0DUMMY3295023 AWD | 13982000 | 13500000
| 2012 | Navy Active | N62863708 |  | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | N3319110D0219 0009 | 1751000 | 1411000 | 2014-05-28 | 2014-06-20
| 2013 | Navy Active | N62863709 |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 2446000 | 2030000 | 2015-03-20 | 2015-03-20
| 2013 | Navy Active | N62863710 |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 5849000 | 6637000 | 2015-03-20 | 2015-03-20
| 2015 | Navy Active | N62863712 |  | 2015-04-11 | 2015-11-20 | COBRA INSTALCIONES Y SERVICIOS SA | N6247016C6001 AWD | 19252000 | 17936000 | 2018-05-23 | 2018-05-23
| 2014 | Navy Active | N62863733 |  | 2014-08-29 | 2014-10-29 | NEWIMAR SA | N3319110D1801 0283 | 1144000 | 901000 | 2014-11-22 | 2014-11-22
| 2015 | Navy Active | N63005955 |  | 2015-04-15 | 2015-09-16 | KOOHEJI CONTRACTORS | N3319113D0832 *New TO | 21897000 | 21718000
| 2015 | Navy Active | N63042327 |  | 2015-03-02 | 2015-06-26 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0007 | 21588000 | 21992000 | 2016-10-17 | 2016-11-02
| 2015 | Navy Active | N63042328 |  | 2015-02-24 | 2015-06-11 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0006 | 17017000 | 16353000 | 2016-07-22 | 2016-08-29
| 2012 | Navy Active | N63042363 |  | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | N6247312C3410 AWD | 1980000 | 1878000 | 2013-08-29 | 2013-08-29
| 2012 | Navy Active | N63042364 |  | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION INC | N6247312C3413 AWD | 2000000 | 1899000 | 2013-09-26 | 2014-03-05
| 2014 | Navy Active | N63042376 |  | 2014-08-27 | 2014-09-27 | COPPERTOP LEDCOR JV | N6247313D4608 0014 | 1839000 | 1690000 | 2016-09-27 | 2016-06-17
| 2015 | Navy Active | N63042377 |  | 2015-10-27 | 2016-02-26 | NORTH STAR CONSTRUCTION & ENGINEERING, INC | N6247309D1643 X087 | 5041000 | 2363000 | 2016-05-26 | 2020-05-21
| 2016 | Navy Active | N63042379 |  | 2016-01-28 | 2016-03-17 | A&D GC INC | N6247315D2403 0002 | 7489000 | 7007000 | 2017-03-31 | 2017-03-31
| 2013 | Navy Active | N63043317 |  | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851000 | 9343000 | 2015-10-09 | 2015-11-30
| 2012 | Navy Active | N63406563 |  | 2012-06-20 | 2012-09-28 | NOVA R M F | N6247312D0245 0003 | 1939000 | 1875000 | 2013-09-27 | 2014-07-01
| 2013 | Navy Active | N66691907 |  | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPA?OLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663000 | 13479000 | 2016-05-15 | 2016-05-15
| 2012 | Navy Active | N68436419 |  | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | N4425510D5019 0002 | 13341000 | 10903000 | 2013-12-24 | 2014-11-10
| 2014 | Navy Active | N68436420 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179000 | 10677000 | 2016-02-16 | 2016-02-16
| 2015 | Navy Active | N68436422 |  | 2014-12-01 | 2015-05-04 | TRITON MARINE CONSTRUCTION CORP. | N4425514D9007 0003 | 12592000 | 11158000 | 2016-10-25 | 2016-10-25
| 2012 | Navy Active | N68436839 |  | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | N4425509D4007 0017 | 1389000 | 1333000 | 2013-08-31 | 2013-11-22
| 2014 | Navy Active | N68436855 |  | 2015-01-30 | 2015-06-30 | DOYON MANAGEMENT SERVICES, LLC | N4425509R4013 X090 | 1951000 | 1856000
| 2013 | Navy Active | N68436857 |  | 2013-01-16 | 2013-05-17 | NOVA GROUP INC | N4425510D5019 0003 | 3406000 | 3127000
| 2012 | Navy Active | N68436913 |  | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | N4425512C3007 AWD | 13485000 | 13638000 | 2013-08-08 | 2014-02-16
| 2012 | Navy Active | N68436985 |  | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | N4425510D5008 0012 | 9338000 | 8948000 | 2013-12-10 | 2014-06-30
| 2012 | Navy Active | N68436990 |  | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714000 | 78002000 | 2016-01-09 | 2016-05-04
| 2013 | Navy Active | N68436990 | N68436990A | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 266304000 | 260899000 | 2016-01-09 | 2016-05-04
| 2014 | Navy Active | N68436990 | N68436990B | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 24880000 | 16633000
| 2015 | Navy Active | N68436990 | N68436990C | 2010-07-07 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 80735000 | 76442000
| 2012 | Navy Active | N68469110 |  | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0019 | 3805000 | 3997000 | 2013-08-28 | 2014-05-30
| 2014 | Navy Active | N684691400 |  | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | N6247013D6019 JU01 | 48905000 | 48850000 | 2015-01-31 | 2015-01-31
| 2012 | Navy Active | N68539184 |  | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101000 | 29967000 | 2015-07-30 | 2015-08-26
| 2014 | Navy Active | N69212461 |  | 2015-07-24 | 2015-09-29 | VIRTEXCO CORPORATION | N4008515C0043 AWD | 14051000 | 13004000 | 2017-02-25 | 2017-04-28
| 2015 | Navy Active | N69212991 |  | 2015-08-05 | 2016-03-08 | PURCELL CONSTRUCTION CORP. | N4008516C6145 AWD | 20817000 | 19652000 | 2018-03-23 | 2018-03-23
| 2015 | Navy Active | N69212992 |  | 2015-03-13 | 2015-09-29 | OCEAN CONSTRUCTION SERVICES | N4008515D0095 AWD | 5272000 | 4982000 | 2016-09-28 | 2016-09-28
| 2013 | Navy Active | N69213237 |  | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | N4008513C3513 AWD | 34005000 | 35142000 | 2014-11-27 | 2015-06-26
| 2014 | Navy Active | N69232281 |  | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | N6247309D1657 0016 | 6106000 | 5820000 | 2015-07-17 | 2015-07-17
| 2012 | Navy Active | N69232559 |  | 2012-03-21 | 2013-09-30 | A&D GC INC | N6247309D1658 0012 | 13210000 | 15242000 | 2014-06-25 | 2015-03-20
| 2016 | Navy Active | N69232565 |  | 2016-01-25 | 2016-03-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247315D2426 0003 | 20557000 | 19578000 | 2017-04-14 | 2017-04-14
| 2014 | Navy Active | N69232593 |  | 2014-04-30 | 2015-01-16 | I E PACIFIC INC | N6247309D1657 0019 | 18400000 | 17449000 | 2016-09-17 | 2016-09-17
| 2014 | Navy Active | N69232599 |  | 2014-11-23 | 2014-11-24 | NAVY STANDARD DOCUMENT | N6247314RP00165 | 33594000 | 30093000 | 2016-03-12 | 2016-03-12
| 2013 | Navy Active | N69232900 |  | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301000 | 9198000 | 2014-11-21 | 2015-10-31
| 2014 | Navy Active | N83447136 |  | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19401000 | 18901000 | 2016-02-12 | 2016-03-27
| 2014 | Navy Reserve | M68479031 |  | 2014-12-12 | 2015-03-24 | ACCEL PACIFIC JV | N4008314D3232 WE01 | 3497000 | 3332000 | 2016-03-23 | 2016-03-23
| 2015 | Navy Reserve | N00129664 |  | 2015-08-09 | 2015-08-25 | VETERANS CONSTRUCTION, LLC | N4008515C9610 AWD | 1989000 | 1874000 | 2016-09-08 | 2016-09-08
| 2013 | Navy Reserve | N00206470 |  | 2013-04-23 | 2015-09-01 | WEBCO L.L.C. | N6945015D0612 0002 | 9648000 | 9422000 | 2017-03-09 | 2017-03-09
| 2015 | Navy Reserve | N00207278 |  | 2015-07-30 | 2015-09-30 | SWEAT LLC | N6945015C1113 AWD | 1699000 | 1714000 | 2016-10-14 | 2016-11-13
| 2012 | Navy Reserve | N32414860 |  | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | N4008312C0005 AWD | 12033000 | 12357000 | 2014-02-06 | 2014-05-31
| 2012 | Navy Reserve | N69212543 |  | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | N4008511D6588 0006 | 738000 | 747000 | 2014-01-21 | 2014-01-21
| 2013 | Navy Reserve | N83447047 |  | 2013-01-22 | 2013-09-12 | KOMADA, LLC | N6945013D1767 0001 | 6894000 | 7671000 | 2014-11-06 | 2015-05-03
2016-02-28 | 2015 | Special Operations Command | 36977 |  | 2015-04-15 | 2015-08-20 | Walsh Group Ventures | W912QR-15-C-0021 / 43320000 | 14851238 | 14987000 | 2017-03-03 | 2017-08-11
2016-02-28 | 2013 | Special Operations Command | 53542 |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546920 | 6546920 | 2016-02-07 | 2016-05-07
2016-02-28 | 2014 | Special Operations Command | 61064 |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951000 | 14335000 | 2016-05-10 | 2016-10-20
2016-02-28 | 2013 | Special Operations Command | 65052 |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199999 | 3272000 | 2015-08-25 | 2015-04-17
2016-02-28 | 2011 | Special Operations Command | 65395 |  | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391578 | 15637173 | 2013-06-19 | 2014-07-31
2016-02-28 | 2013 | Special Operations Command | 66597 |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384894 | 3384894 | 2015-10-21 | 2016-03-07
2015-02-28 | 2012 | Special Operations Command | 66598 |  | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350000 | 35586000 | 2014-02-15 | 2015-05-05
2016-02-28 | 2014 | Special Operations Command | 68526 |  | 2014-03-26 | 2015-04-09 | Barlovento, LLC | W91278-10-D-0058-DQ01 | 10815034 | 11992000 | 2017-04-07 | 2017-04-07
2016-02-28 | 2013 | Special Operations Command | 69257 |  | 2014-03-11 | 2015-04-01 | Pease Construction, Inc. | W912DW-15-C-0003 | 4484160 | 4484160 | 2016-09-15 | 2016-09-15
2016-02-28 | 2013 | Special Operations Command | 69287a |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907435 | 31157000 | 2015-05-13 | 2016-04-01
2016-02-28 | 2013 | Special Operations Command | 69287b |  | 2014-05-14 | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404000 | 25094000 | 2016-11-01 | 2017-05-06
2016-02-28 | 2013 | Special Operations Command | 69382 |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816000 | 26064000 | 2015-08-14 | 2015-11-04
2016-02-28 | 2013 | Special Operations Command | 69445 |  | 2013-02-01 | 2015-05-07 | RQ Construction LLC | W912DW-15-C-0006 | 45104000 | 45718000 | 2017-05-25 | 2017-07-31
2016-02-28 | 2014 | Special Operations Command | 69446 |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083965 | 15643000 | 2016-02-08 | 2016-08-08
2016-02-28 | 2013 | Special Operations Command | 69447 |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123180 | 22807000 | 2016-02-13 | 2016-04-13
2015-02-28 | 2012 | Special Operations Command | 69458 |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772305 | 16820000 | 2014-06-03 | 2016-02-15
2016-02-28 | 2013 | Special Operations Command | 69493 |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085000 | 23223000 | 2016-07-18 | 2016-10-14
2015-02-28 | 2012 | Special Operations Command | 69758 |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 16429000 | 16277000 | 2014-05-08 | 2016-05-14
2015-02-28 | 2012 | Special Operations Command | 71224 |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525847 | 18786000 | 2014-05-01 | 2015-04-27
2015-02-28 | 2012 | Special Operations Command | 76364 |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201303 | 33465000 | 2014-08-26 | 2016-04-01
2015-02-28 | 2012 | Special Operations Command | 76366 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673727 | 15674302 | 2015-09-12 | 2016-04-26
2016-02-28 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441000 | 37258000 | 2016-07-20 | 2016-12-30
2015-02-28 | 2012 | Special Operations Command | 76371 |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092801 | 17224000 | 2015-09-12 | 2016-01-27
2016-02-28 | 2014 | Special Operations Command | 76375 |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358000 | 27536000 | 2016-07-23 | 2017-01-19
2016-02-28 | 2014 | Special Operations Command | 76376 |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696668 | 52401000 | 2017-06-27 | 2018-01-15
2016-02-28 | 2014 | Special Operations Command | 78024 |  | 2014-12-05 | 2015-06-09 | Nishimatsu Construction Co., Ltd. | W912HV-15-C-0004 / 35808936 | 46555863 | 46600000 | 2017-12-12 | 2018-04-05
2016-02-28 | 2014 | Special Operations Command | 79438 |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193631 | 7402000 | 2016-04-19 | 2016-12-05
2016-02-28 | 2015 | Special Operations Command | 79456 |  | 2015-05-21 | 2015-08-31 | Lifecycle Construction Services, LLC | W912HN-13-D-0002-DQ01 | 5798000 | 5798000 |  | 2017-02-13
2016-02-28 | 2011 | Special Operations Command | CZQZ063052A |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13829000 | 13829042 | 2013-07-17 | 2014-06-03 | Contract is essentially complete. HVAC problems relating to USACE design deficiency is being investigated and will probably result in a major modification to the project.
2016-02-28 | 2014 | Special Operations Command | FTEV083002 |  | 2014-05-01 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 48908883 | 1573300 | 1603464 | 2016-05-24 | 2016-10-20
2016-02-28 | 2014 | Special Operations Command | FTEV083002 |  | 2014-05-01 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048867 | 7230868 | 2016-05-24 | 2016-10-20
2016-02-28 | 2013 | Special Operations Command | FTFA113004 |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942300 | 30416000 | 2016-12-25 | 2016-12-25
2016-02-28 | 2013 | Special Operations Command | NVZR083702 |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753024 | 27073000 | 2015-06-28 | 2016-05-31
2015-02-28 | 2012 | Special Operations Command | P-1049 |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129000 | 8767000 | 2014-11-13 | 2015-11-13
2015-02-28 | 2012 | Special Operations Command | P-1049 |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648#0003 | 8129000 | 8774782 | 2014-11-13 | 2016-03-16
2016-02-28 | 2015 | Special Operations Command | P-1119 |  | 2015-08-14 | 2015-09-29 | Cox Construction Company | N62473-15-D-2405-0003 | 11080 | 11080 | 2017-04-06 | 2017-04-06 | Mobilization 08Feb2016
2016-02-28 | 2013 | Special Operations Command | P-1218 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 48044 | 2016-03-01 | 2016-05-31
2016-02-28 | 2014 | Special Operations Command | P-1391 |  | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333#0004 | 27547 | 27858 | 2016-09-02 | 2016-09-02
2016-02-28 | 2013 | Special Operations Command | P-1393 |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 48044 | 2016-01-18 | 2016-05-31
2015-02-28 | 2012 | Special Operations Command | P-164 |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727000 | 18855000 | 2014-07-24 | 2015-06-16
2016-02-28 | 2013 | Special Operations Command | P-165 |  | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351000 | 10272000 | 2015-09-09 | 2015-11-26
2016-02-28 | 2014 | Special Operations Command | P-334 |  | 2015-07-21 | 2016-02-10 | DPR Hardin Construction-WGI JV | N40085-10_D-5333 | 26731230 | 26731230 | 2018-07-01 | 2018-07-01
2015-02-28 | 2012 | Special Operations Command | P-473 |  | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366000 | 27585000 | 2015-12-27 | 2015-12-27
2015-02-28 | 2012 | Special Operations Command | P-769 |  | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022000 | 4067000 | 2014-06-27 | 2015-02-20
2015-02-28 | 2012 | Special Operations Command | P-826 |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139000 | 18855000 | 2014-07-24 | 2015-06-16
2016-02-28 | 2013 | Special Operations Command | P-876 |  | 2014-05-05 | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290000 | 24440000 | 2016-10-01 | 2016-10-07
2016-02-28 | 2013 | Special Operations Command | P-888 |  | 2014-04-01 | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489000 | 15440000 | 2016-09-30 | 2016-09-29 | DB Design not yet accepted: Start date listed as 1-mo after award.
2016-03-17 | 2010 | Washington Headquarters Services | 80001 |  | 2013-09-01 | 2013-09-30 | Virginia Electric and Power Company | HQ0034-13-F-0027 | 13679273 | 13679273 | 2015-01-31 | 2015-01-31
2016-03-17 | 2010 | Washington Headquarters Services | 80001 |  | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power | HQ0034-13-C-0133 | 9669575 | 10923401 | 2015-02-05 | 2015-09-14
2016-03-17 | 2011 | Washington Headquarters Services | 80002 |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. | HQ0034-13-C-0062 | 43594000 | 47720885 | 2016-05-11 | 2016-09-30
2016-03-17 | 2011 | Washington Headquarters Services | 80003 |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. | W912DR-11-R-0060 | 5609000 | 6299239 | 2015-05-03 | 2016-02-03
2016-03-17 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC | W912DR-11-R-0062 | 5454000 | 5492659 | 2015-05-01 | 2015-10-01
2016-03-17 | 2012 | Washington Headquarters Services | 80005
2016-03-17 | 2012 | Washington Headquarters Services | 80006
2016-03-17 | 2014 | Washington Headquarters Services | 80007
2016-03-17 | 2014 | Washington Headquarters Services | 80008
2016-03-17 | 2014 | Washington Headquarters Services | 80009
2016-03-17 | 2014 | Washington Headquarters Services | 80010
2016-03-17 | 2015 | Washington Headquarters Services | 80011

## EXPENDITURES
Expenditure Data as of Date | Appropriation Fiscal Year | Project Sponsor Component Name | Appropriation Fund Type Name | Use of Funds | Aggregated Appropriated Amount | Aggregated Current Obligated Amount | Aggregated Current Expenditure Amount | Expenditure Remarks
2016-04-15 | 2012 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407 | 22219 | 21193
2016-04-15 | 2011 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192 | 56338 | 56333
2016-04-15 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936 | 2941 | 2797
2016-04-15 | 2006 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773 | 6350 | 6350
2016-04-15 | 2010 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558 | 59491 | 59491
2016-04-15 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093 | 40903 | 14240
2016-04-15 | 2007 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232 | 329296 | 329290
2016-04-15 | 2008 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 294262 | 238649 | 236421
2016-04-15 | 2009 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513 | 205884 | 201525
2016-04-15 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 399 | 313 | 208
2016-04-15 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 468 | 444 | 410
2016-04-15 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing. Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - | 609 | 608 | 608
2016-04-15 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 529 | 510 | 508
2016-04-15 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 448 | 434 | 428
2016-04-15 | 2015 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 352 | 0 | 0
2016-04-15 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 544 | 514 | 512
2016-04-15 | 2012 | Air Force Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 78413 | 77889 | 75344
2016-04-15 | 2013 | Air Force Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 410 | 374 | 266
2016-04-15 | 2014 | Air Force Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314 | 11180 | 10202
2016-04-15 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 10738 | 9559 | 6278
2016-04-15 | 2006 | Air Force Active | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for GWOT Projects. | 63753 | 24438 | 24438
2016-04-15 | 2007 | Air Force Active | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for GWOT Projects. | 74021 | 72840 | 72335
2016-04-15 | 2008 | Air Force Active | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Design for GWOT Projects. | 30148 | 29576 | 29329
2016-04-15 | 2009 | Air Force Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105506 | 103467 | 102661
2016-04-15 | 2010 | Air Force Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 87562 | 86913 | 85496
2016-04-15 | 2011 | Air Force Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations; Design for OCO Projects | 63903 | 63520 | 60517
2016-04-15 | 2013 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3951 | 0 | 0
2016-04-15 | 2007 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12876 | 12730
2016-04-15 | 2012 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056 | 4031 | 4031
2016-04-15 | 2010 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302 | 1396 | 1396
2016-04-15 | 2006 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782 | 989 | 989
2016-04-15 | 2008 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12161 | 12161
2016-04-15 | 2014 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267 | 0 | 0
2016-04-15 | 2009 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703 | 7524 | 7524
2016-04-15 | 2011 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153 | 3921 | 3921
2016-04-15 | 2006 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15769 | 4749 | 4749
2016-04-15 | 2011 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 17964 | 17428 | 17021
2016-04-15 | 2008 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14081 | 14081
2016-04-15 | 2010 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 20000 | 19887 | 19887
2016-04-15 | 2012 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000 | 19546 | 17633
2016-04-15 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22613 | 0 | 0
2016-04-15 | 2007 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14163 | 14163
2016-04-15 | 2009 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14851 | 14848
2016-04-15 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448 | 1702 | 1618
2016-04-15 | 2013 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 18175 | 4060 | 3444
2016-04-01 | 2006 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289570 | 5289120 | 5289120
2016-04-01 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892000 | 741524 | 218201
2016-04-01 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229000 | 1805573 | 701099
2016-04-01 | 2013 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875201 | 2362653 | 2155523
2016-04-01 | 2012 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200000 | 2117881 | 2082312
2016-04-01 | 2011 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649694 | 1521061 | 1521061
2016-04-01 | 2010 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139000 | 8001719 | 6000916
2016-04-01 | 2009 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165000 | 6133583 | 6123256
2016-04-01 | 2008 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300000 | 5270797 | 5270797
2016-04-01 | 2007 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109000 | 5072462 | 5072462
2016-04-01 | 2008 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909000 | 4909000 | 4909000
2016-04-01 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400000 | 0 | 0
2016-04-01 | 2010 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 800000 | 752889 | 752889
2016-04-01 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530000 | 0 | 0
2016-04-01 | 2007 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477000 | 4476971 | 4476971
2016-04-01 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997361 | 355600 | 38552
2016-04-01 | 2009 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443000 | 5442927 | 5442927
2016-04-01 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5434000 | 4216309 | 3745090
2016-04-01 | 2011 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2753482 | 2728949 | 2651597
2016-04-01 | 2006 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960000 | 3959698 | 3959698
2016-04-15 | 2007 | Air National Guard | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050000 | 19043340 | 19043339
2016-04-15 | 2008 | Air National Guard | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721000 | 10619035 | 10619035
2016-04-15 | 2009 | Air National Guard | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056000 | 19040835 | 19005487
2016-04-15 | 2010 | Air National Guard | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670441 | 19601297 | 19481332
2016-04-15 | 2011 | Air National Guard | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195572 | 9162259 | 8935618
2016-04-15 | 2012 | Air National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225000 | 12131867 | 11736638
2016-04-15 | 2013 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994721 | 3935386 | 3838412
2016-04-15 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400000 | 9450417 | 6178436
2016-04-15 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7700000 | 3465201 | 1025312
2016-04-15 | 2006 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006000 | 28018596 | 28018596
2016-04-15 | 2007 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000000 | 5999999 | 5999999
2016-04-15 | 2008 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184000 | 14184000 | 14184000
2016-04-15 | 2009 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243000 | 34243000 | 34235708
2016-04-15 | 2010 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913559 | 44865425 | 44503239
2016-04-15 | 2006 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882000 | 6882000 | 6882000
2016-04-15 | 2012 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000000 | 8951300 | 6377684
2016-04-15 | 2013 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892214 | 4731567 | 4709096
2016-04-15 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000000 | 12217453 | 2921286
2016-04-15 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6100000 | 7236247 | 1009473
2016-04-15 | 2011 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984000 | 7982986 | 7929226
2016-03-31 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000000 | 24984363 | 24984363
2016-03-31 | 2011 | Army Active | Host Nation Support | $27,944 Appropriated + $13,000 ATR +2,000 BTR Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 42944000 | 42931330 | 42931330
2016-03-31 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR + $9,000 ATR | 36000000 | 35901649 | 35571270
2016-03-31 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000000 | 33856711 | 33840930
2016-03-31 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000000 | 22889672 | 22208023
2016-03-31 | 2015 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $33,000 Appropriated - $5,000 reprogrammed to FY15 MCA P&D | 28000000 | 25783932 | 23772165
2016-03-31 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000000 | 23999818 | 23999818
2016-03-31 | 2016 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36000000 | 3799547 | 2312747
2016-03-31 | 2009 | Army Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766000 | 220910283 | 219788872
2016-03-31 | 2010 | Army Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 305903000 | 266118944 | 264559307
2016-03-31 | 2011 | Army Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 379238000 | 264261770 | 260950926
2016-03-31 | 2012 | Army Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 265741000 | 249908096 | 228510401
2016-03-31 | 2013 | Army Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46173000 | 45853360 | 44043081
2016-03-31 | 2014 | Army Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575000 | 39812443 | 38872647
2016-03-31 | 2015 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements.$18,127 Appropriated + $5,000 moved from FY15 HNS | 23127000 | 19551113 | 18934920
2016-03-31 | 2016 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 73245000 | 7586879 | 881827
2016-03-31 | 2016 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7195000 | 366737 | 366737
2016-03-31 | 2009 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 579000 | 575050 | 548105
2016-03-31 | 2010 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 3936000 | 3921090 | 2503183
2016-03-31 | 2011 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2036000 | 2029691 | 1401165
2016-03-31 | 2012 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7897000 | 7829700 | 7456060
2016-03-31 | 2013 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4641000 | 4549050 | 3925804
2016-03-31 | 2014 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4408000 | 1654479 | 1631161
2016-03-31 | 2015 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 1309000 | 929275 | 139137
2016-03-31 | 2009 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 28750000 | 28424458 | 26159102
2016-03-31 | 2010 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 31250000 | 31240730 | 30517799
2016-03-31 | 2011 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 28704000 | 28703986 | 28693976
2016-03-31 | 2012 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 20000000 | 19737211 | 19431374
2016-03-31 | 2013 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 24187753 | 22842032
2016-03-31 | 2015 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 12642067 | 521239
2016-03-31 | 2014 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 25000000 | 19931922 | 17562981
2016-04-08 | 2013 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17; Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 28155000 | 19967000 | 19967000 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013); PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930000 | 2782000 | 2782000 | PL 113-76 P&D Recission
2016-04-08 | 2015 | Army National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 17600000 | 7135000 | 7135000
2016-04-08 | 2016 | Army National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20337000 | 0 | 0
2016-04-08 | 2012 | Army National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191000 | 20185000 | 20185000 | PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2013 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14562000 | 14562000 | 14562000 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2016-04-08 | 2014 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 12240000 | 9878000 | 9878000
2016-04-08 | 2015 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 13720000 | 1517000 | 1517000
2016-04-08 | 2016 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 15000000 | 0 | 0
2016-04-08 | 2012 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $2M | 14149000 | 11573000 | 11573000 | PL 112-25 (Budget Control Act, 2011)
2016-02-26 | 2016 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For Design of projects from 2014 to 2019 | 31772000 | 363952 | 363952
2016-02-22 | 2012 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34331000 | 34331000
2016-02-24 | 2013 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 30636000 | 30636000
2015-11-05 | 2013 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2265551 | 2265551
2015-11-05 | 2011 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 5247000 | 3801453 | 3801453 | Appropriation per PL 112-10
2015-02-28 | 2012 | Defense Finance and Accounting Service | Planning and Design - Military Construction | Investigation and Design | 1992 | 748 | 709
2015-02-28 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction | Construction | 15404 | 13902 | 13197
2016-03-31 | 2014 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 244000 | 0 | 0
2016-03-31 | 2013 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 97411000 | -708000 | -733000
2016-03-31 | 2012 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 75957000 | 24498000 | 8062000
2016-03-31 | 2011 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 190481000 | 172238000 | 135868000
2016-03-31 | 2015 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 105000 | 0 | 0
2016-03-31 | 2016 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2016-03-31 | 2010 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 72679000 | 72459000 | 69569000
2016-03-31 | 2009 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 171255000 | 170779000 | 166410000
2016-03-31 | 2016 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5000000 | 0 | 0
2016-03-31 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4100000 | 0 | 0
2016-03-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 9578000 | 3208000 | 837000
2016-03-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4608000 | 3713000 | 3403000
2016-03-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5930000 | 5394000 | 5394000
2016-03-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4673000 | 4609000 | 4609000
2016-03-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5547000 | 3984000 | 3984000
2016-03-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 3979000 | 3979000 | 3979000
2015-10-30 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction |  | 12216000 | 11471000 | 146000 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) ($9,600); JITC Building 52120 Design/Renovation ($1,871); P&D for design of JITC Buildings 52101, 52110, 52111 ($745K)
2015-10-30 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction |  | 2615000 | 46800 | 5000 | DISA Pacific Facility Upgrade
2015-10-30 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction |  | 79739000 | 69643972 | 57967778 | DISA Europe Facility Upgrades ($2,224); Construct New DISA Facility Scott AFB ($77,515)
2015-08-31 | 2010 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for K-16 FOB-K renovation of two buildings to include Administrative and SCIF Spaces | 442000 | 0 | 442000 | Planning and Design MIPR sent to U.S. Army Engineer District, Far East for K-16 Design. MIPR has been fully executed.
2015-08-31 | 2012 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for DIAC Parking Garage Replacement; P&D for DIAC Chilled Water Project for Data Center ($125K) and P&D for DIAC Cooling Tower for Data Center ($105K); P&D for UPS for Data Center Installation; P&D for Construction of JUIAF RDF | 2914673 | 73272 | 2841401 | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $416K (CORRECTED AMOUNT) obligated as CAT I. Contract awarded on 23 September 2014.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.; Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 100% design completed.; Design complete.
2015-08-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction |  | 0 | 0 | 0
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2015 to 2018 | 6978000 | 0 | 0
2015-08-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34239000 | 34239000
2015-08-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of projects from 2012 to 2016 | 36093000 | 35966000 | 35966000
2015-08-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 27241500 | 27415000
2015-08-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2266000 | 2266000
2015-08-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2014 | 6312000 | 6312000 | 6312000
2015-08-31 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2015 to 2019 | 5932000 | 0 | 0
2015-08-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 4864000 | 4501000 | 4501000
2015-08-31 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2013 to 2016 | 7430000 | 0 | 0
2016-03-31 | 2009 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13617000 | 13617000 | 12865187
2016-03-31 | 2008 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI andFY 08/09/ 10/11/12 MILCON projects | 5159000 | 5159000 | 5157915 | RCI-Residential Communities Initiative
2016-03-31 | 2010 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 10/11/ 12/13 MILCON projects | 8829000 | 8755000 | 8722301 | Reflects Sequestration Reduction
2016-03-31 | 2011 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 11/12/ 13 MILCON projects | 78666000 | 75242000 | 67373157 | Reflects Sequestration Reduction
2016-03-31 | 2012 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 12/13 MILCON projects | 64551000 | 64537000 | 51268841 | Reflects Sequestration Reduction
2016-03-31 | 2013 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 13/14/15/16 MILCON projects | 97290000 | 97016000 | 70340623 | Reflects Sequestration Reduction
2016-03-31 | 2015 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42387000 | 0 | 0
2016-03-31 | 2014 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 14/15/16/17 MILCON projects | 75905000 | 20244000 | 2446485
2016-03-31 | 2016 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42183000 | 0 | 0
2016-03-31 | 2009 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5000 | 4000 | 4025 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2016-03-31 | 2013 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3771000 | 0 | 0 | Reflects Sequestration Reduction
2016-03-31 | 2014 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5409000 | 0 | 0
2016-03-31 | 2015 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 6846000 | 0 | 0
2016-01-31 | 2013 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 17441000 | 16715000 | 16715000
2016-01-31 | 2014 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 24253000 | 15632000 | 15623000
2016-01-31 | 2015 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 15940000 | 13292000 | 0
2016-01-31 | 2016 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 7857000 | 0 | 0
2016-01-31 | 2012 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 25327000 | 23639000 | 23639000
2016-01-31 | 2016 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 613000 | 0 | 0
2016-01-31 | 2012 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719000 | 719000 | 719000
2016-01-31 | 2013 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455000 | 445000 | 445000
2016-01-31 | 2014 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463000 | 462000 | 411000
2016-01-31 | 2015 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 472000 | 75000 | 75000
2016-03-31 | 2014 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY14-16 MILCON Projects | 10891000 | 10891000 | 10482000 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2016-03-31 | 2016 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY16-18 MILCON Projects | 15000000 | 0 | 0 | Design requirements in the CONUS to include Hawaii and Alaska
2016-03-31 | 2015 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY16-17 MILCON Projects | 58704000 | 24715000 | 15219468 | Supports design of the Aegis Ashore Poland site, Long Range Discrimination Radar System Complex, Clear AFS, AK, IDT Switchgear Bldg, Fort Greely, AK, and the Test Support Facility, Wake Island.
2016-03-31 | 2011 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY15-16 MILCON Projects | 1186000 | 1186000 | 1186000 | Funds tranferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2016-03-31 | 2012 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY13-14 MILCON Projects | 8368000 | 8368000 | 8124000 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, UEWR Modifications at Clear AFS, AK, and the Test Suppport Facility at Wake Island .
2016-03-31 | 2013 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY13-14 MILCON Projects | 4191000 | 4191000 | 4114000 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2016-03-31 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000000 | 2000000 | 55000 | Supports the Storage Facility, Meck Island project and Communication Test Facility, Wake island project.
2016-03-31 | 2015 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY15/16 | 2000000 | 335000 | 0 | Supports the Communication Test Facility, Wake island project.
2016-03-31 | 2013 | National Security Agency | Construction - Major Military Construction | MOD II, Mountainview, HPCC2, ICECUBE, ECB1, HPCC1 | 507542000 | 456623579 | 411358064
2016-03-31 | 2014 | National Security Agency | Construction - Major Military Construction | HPCC2, ECB1 | 489000000 | 488956384 | 452569695
2016-03-31 | 2012 | National Security Agency | Construction - Major Military Construction | Mountainview, Whitelaw Wedge, HPCC2, ICECUBE, ECB1, HPCC1, MHS Generator Plant | 328757000 | 328754770 | 286302600
2016-03-31 | 2015 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - North, ECB1 | 99728000 | 95724434 | 15858900
2016-03-31 | 2016 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - Central, ECB2 | 68642000 | 68180919 | 0
2016-03-31 | 2015 | National Security Agency | Planning and Design - Military Construction | General P&D | 599000 | 0 | 0
2016-03-31 | 2016 | National Security Agency | Planning and Design - Military Construction | General P&D | 1078000 | 0 | 0
2016-03-31 | 2013 | National Security Agency | Planning and Design - Military Construction | General P&D | 7649000 | 4123616 | 4074270
2016-03-31 | 2012 | National Security Agency | Planning and Design - Military Construction | General P&D | 28483000 | 23800910 | 22216581
2016-03-31 | 2014 | National Security Agency | Planning and Design - Military Construction | General P&D | 39400000 | 8040307 | 2163674
2016-03-31 | 2015 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 2994000 | 0 | 0
2016-03-31 | 2014 | National Security Agency | Unspecified Minor Military Construction | Cooper Ave, General UMMC | 1500000 | 235000 | 0
2016-03-31 | 2013 | National Security Agency | Unspecified Minor Military Construction | Cooper Ave | 2765000 | 2660000 | 0
2016-01-31 | 2016 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 3658000 | 0 | 0
2016-01-31 | 2014 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 44716000 | 41319000 | 18102000
2016-01-31 | 2015 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
2016-01-31 | 2012 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 68661000 | 59244000 | 49102000
2016-01-31 | 2013 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 42740000 | 34298000 | 28595000
2016-01-31 | 2014 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638000 | 77797000 | 70815000 | [Component: Navy-MC Active]
2016-01-31 | 2015 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 33366000 | 32439000 | 29171000 | [Component: Navy-MC Active]
2016-01-31 | 2012 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 85899000 | 85861000 | 83486000 | [Component: Navy-MC Active]
2016-01-31 | 2013 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 112333000 | 110391000 | 93072000 | [Component: Navy-MC Active]
2016-01-31 | 2016 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 91649000 | 39854000 | 20930000 | [Component: Navy-MC Active]
2016-01-31 | 2012 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2446000 | 2439000 | 2400000
2016-01-31 | 2013 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3610000 | 2303000 | 1364000
2016-01-31 | 2014 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975000 | 0 | 0
2016-01-31 | 2015 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0
2016-01-31 | 2016 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 3975000 | 0 | 0
2016-01-31 | 2012 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 20919000 | 19845000 | 18816000 | [Component: Navy-MC Active]
2016-01-31 | 2016 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 22590000 | 0 | 0
2016-01-31 | 2013 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 15612000 | 14028000 | 11579000 | [Component: Navy-MC Active]
2016-01-31 | 2015 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 7163000 | 5376000 | 513000 | [Component: Navy-MC Active]
2016-01-31 | 2014 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 19740000 | 14028000 | 9182000 | [Component: Navy-MC Active]
2016-01-31 | 2016 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs | 2208000 | 0 | 0 | [Component: Navy-MC Reserve]
2016-01-31 | 2015 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 2123000 | 1605000 | 835000 | [Component: Navy-MC Reserve]
2016-01-31 | 2014 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2540000 | 2540000 | 2531000 | [Component: Navy-MC Reserve]
2016-01-31 | 2013 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995000 | 1995000 | 1992000 | [Component: Navy-MC Reserve]
2016-01-31 | 2012 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478000 | 2468000 | 2360000 | [Component: Navy-MC Reserve]
2016-01-31 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 4000000 | 1564000 | 27000 | [Component: Navy-MC Reserve]
2016-01-31 | 2014 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2016-01-31 | 2013 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Component: Navy-MC Reserve]
2016-01-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 2447000 | 2040000 | 1171000 | [Component: Navy-MC Reserve]
2016-01-31 | 2016 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 1468000 | 0 | 0
2016-04-01 | 2014 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 36866000 | 30920000 | 30920000
2016-02-28 | 2011 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 26469000 | 26468000 | 26468000 | Does not include funds being returned from UK DIO.
2016-04-01 | 2012 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 30308000 | 29459000 | 29459000
2016-04-01 | 2013 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 25454000 | 18194000 | 18194000
2016-04-01 | 2015 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 24197000 | 0 | 0
2016-04-01 | 2011 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 7531000 | 7526000 | 7526000
2016-04-01 | 2012 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 8487000 | 8070000 | 8070000
2016-04-01 | 2015 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 10334000 | 0 | 0
2016-04-01 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 9216000 | 8977000 | 8977000
2016-04-01 | 2014 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5170000 | 2928000 | 2928000
2016-03-17 | 2015 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 1183000 | 0 | 0
2016-03-17 | 2012 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4870000 | 4823915 | 3201000 | Sequester taken.
2016-03-17 | 2013 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 7508000 | 3134063 | 1397000 | Sequester and recissions taken. Includes ECIP
2016-03-17 | 2014 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 6931000 | 0 | 0