## PROJECTS
Project Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Construction Project Type Name | State Name | Country Name | Project Number | Project Title | Sub-Project Number | Diverted Funds Total Amount | Diverted Funds Recipient Text | Construction Start Date | Original Construction Completion Date | Current Construction Completion Date | Construction Percent Complete | Current RPA Placed-In-Service Date
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Kuwait | AEWV171012 | Dining Facility Addition |  |  |  | 2019-03-27 | 2020-08-08 | 2021-11-01 | 42% | 2021-11-01
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN053009 | FIRE RESCUE CENTER |  |  |  | 2019-11-17 | 2022-04-19 | 2021-09-26 | 27% | 2022-08-17
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN123003 | DORMITORY (120 RM) |  |  |  | 2019-11-06 | 2021-10-26 | 2021-10-26 | 65% | 2022-04-30
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN173001 | KC-46A FTU FTC SIMULATOR FACILITY PHASE 2 |  |  |  | 2017-09-07 | 2019-03-01 | 2021-09-11 | 99% | 2019-09-09
2020-10-31 | 2018 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN193001 | KC-46A FTU Fuselage Trainer Phase 2 |  |  |  | 2018-11-15 | 2020-03-13 | 2020-09-14 | 100% | 2020-09-14
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | AGGN213001 | KC-46A FTU Fuselage Trainer Phase 3 |  |  |  | 2019-08-14 | 2021-02-04 | 2021-06-08 | 59% | 2021-06-08
2021-04-30 | 2020 | Air Force Active | Major Military Construction |  | Guam | AJJY073105P3 | APSI - MUNITIONS STORAGE IGLOOS PHASE 3 |  |  |  | 2021-04-05 | 2023-06-16 | 2023-06-16 | 14% | 2023-06-16
2021-04-30 | 2013 | Air Force Active | Major Military Construction |  | Guam | AJJY123010 | Guam Strike Fuel Systems Maintenance Hangar |  |  |  | 2015-03-18 | 2017-03-21 | 2021-06-30 | 98% | 2021-06-30
2021-04-30 | 2014 | Air Force Active | Major Military Construction |  | Guam | AJJY133027 | PAR - TANKER GP MAINT HANGAR/AMU/SQD OPS |  |  |  | 2015-01-08 | 2017-03-22 | 2021-07-31 | 98% | 2021-07-31
2021-04-30 | 2015 | Air Force Active | Major Military Construction |  | Guam | AJJY133028 | PAR Low Observable/Corrosion Control/Composite Repair Shop |  |  |  | 2016-11-18 | 2018-10-20 | 2021-09-30 | 60% | 2021-09-30
2020-12-31 | 2014 | Air Force Active | Major Military Construction |  | Guam | AJJY143760 | Hardened Structures For POL Fuel Systems |  |  |  | 2014-10-07 | 2016-06-28 | 2020-12-31 | 100% | 2021-03-01
2020-12-31 | 2016 | Air Force Active | Major Military Construction |  | Guam | AJJY163004 | APR - Dispersed Maintenance Spares and SE Storage Facility |  |  |  | 2017-08-31 | 2019-05-13 | 2020-12-04 | 100% | 2021-12-04
2021-04-30 | 2020 | Air Force Active | Unspecified Minor Military Construction |  | Guam | AJJY183017 | CONSOLIDATED CONTINGENCY CENTER |  |  |  | 2020-10-07 | 2022-03-22 | 2022-06-25 | 9% | 2022-06-25
2021-04-30 | 2021 | Air Force Active | Major Military Construction |  | Guam | AJJY203001 | STAND OFF WEAPONS COMPLEX, MSA 2 |  |  |  | 2021-04-19 | 2023-10-23 | 2023-10-23 | 1% | 2023-10-23
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Maryland | United States | AJXF093000 | CONSTRUCT 21 POINT ENCLOSED FIRING RANGE |  |  |  | 2018-05-24 | 2020-09-13 | 2021-07-30 | 88% | 2021-07-30
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Maryland | United States | AJXF173021 | PRESIDENTIAL AIRCRAFT RECAPITALIZATION COMPLEX |  |  |  | 2018-08-19 | 2021-10-18 | 2022-04-10 | 58% | 2021-12-11
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Qatar | ALUA113023 | Consolidated Squadron Operations Facility |  |  |  | 2019-10-28 | 2021-01-20 | 2021-05-27 | 73% | 2021-06-19
2021-01-31 | 2015 | Air Force Active | Unspecified Minor Military Construction |  | Italy | ASHE143006 | MILITARY WORKING DOG (MWD) KENNEL COMPLEX |  |  |  | 2017-08-01 | 2019-02-02 | 2021-01-07 | 100% | 2021-01-07
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Italy | ASHE143008 | GUARDIAN ANGEL OPERATIONS FACILITY |  |  |  | 2020-05-25 | 2021-01-29 | 2021-11-30 | 27% | 2021-11-30
2021-04-30 | 2017 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF164000 | DINING FACILITY |  |  |  | 2018-09-11 | 2020-03-04 | 2021-06-30 | 96% | 2021-06-30
2021-04-30 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100A | OIR: MSAB - AIRFIELD PAVEMENTS |  |  |  | 2020-06-01 | 2023-03-28 | 2023-03-28 | 8% | 2023-06-26
2021-04-30 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100B | OIR: MSAB - ISR SHELTERS |  |  |  | 2020-06-01 | 2023-03-28 | 2023-03-28 | 8% | 2023-06-26
2021-04-30 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100C | OIR: MSAB - CAS REVETMENTS/SUNSHADES |  |  |  | 2020-06-01 | 2023-03-28 | 2023-03-28 | 8% | 2023-06-26
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Jordan | ASVF183100D | OIR: MSAB - DORMITORY |  |  |  | 2019-04-05 | 2020-08-29 | 2021-08-20 | 92% | 2021-10-20
2021-04-30 | 2018 | Air Force Active | Unspecified Minor Military Construction |  | Jordan | ASVF183100E | OIR: MSAB - CARGO MARSHALLING YARD FACILITY |  |  |  | 2020-06-01 | 2023-03-28 | 2023-03-28 | 10% | 2023-06-26
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Jordan | ASVF183100F | OIR: MSAB - SUPPORTING FACILITIES/UTILITIES |  |  |  | 2018-09-11 | 2023-03-28 | 2023-03-28 | 44% | 2023-06-26
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Louisiana | United States | AWUB095000 | Consolidated Communication Facility |  |  |  | 2019-07-17 | 2022-04-02 | 2022-04-02 | 13% | 2022-07-14
2021-04-30 | 2017 | Air Force Active | Unspecified Minor Military Construction | Louisiana | United States | AWUB105003 | FIRE STATION NO. 2 |  |  |  | 2018-07-21 | 2020-10-08 | 2021-04-05 | 100% | 2021-02-23
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Iceland | BIKF180001 | ERI: AIRFIELD REPAIRS AND UPGRADES |  |  |  | 2019-08-12 | 2020-04-15 | 2021-02-13 | 100% | 2021-02-13
2021-04-30 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190001 | EDI: AIRFIELD UPGRADES - APRON EXPANSION |  |  |  | 2021-01-30 | 2023-03-05 | 2023-03-05 | 1% | 2023-03-06
2021-04-30 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190002 | EDI: BEDDOWN SITE PREPARATION |  |  |  | 2021-01-30 | 2023-03-05 | 2023-03-05 | 1% | 2023-03-06
2021-04-30 | 2020 | Air Force Active | Major Military Construction |  | Iceland | BIKF190003 | EDI: AIRFIELD UPGRADES - DANGEROUS CARGO PAD |  |  |  | 2021-01-30 | 2023-03-05 | 2023-03-05 | 1% | 2023-03-06
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170001 | Construct Chabelley Access Road |  |  |  | 2018-08-05 | 2019-11-01 | 2021-06-26 | 76% | 2021-07-13
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Djibouti | CADJ170002 | Construct Parking Apron and Taxiway |  |  |  | 2018-08-05 | 2019-11-01 | 2021-12-31 | 58% | 2022-01-31
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Colorado | United States | CRWU093002 | SBIRS Operations Facility |  |  |  | 2019-12-17 | 2021-03-21 | 2021-06-30 | 83% | 2021-06-30
2021-04-30 | 2019 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | CRWU173001 | Large Vehicle Inspection Point (LVIP) |  |  |  | 2020-12-01 | 2021-12-12 | 2021-12-12 | 21% | 2021-12-12
2021-01-31 | 2017 | Air Force Active | Major Military Construction | New Mexico | United States | CZQZ083500 | North Fitness Center |  |  |  | 2018-09-20 | 2020-06-16 | 2020-11-19 | 100% | 2020-12-04
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | United Arab Emirates | DHAF152900 | LARGE AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2019-09-26 | 2021-10-15 | 2021-10-15 | 33% | 2022-02-17
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | DXEB053005 | FIRE STATION |  |  |  | 2018-05-04 | 2020-07-06 | 2021-08-27 | 97% | 2021-08-27
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Estonia | EEEI150006 | ERI: Construct Bulk Fuel Storage |  |  |  | 2020-10-28 | 2023-04-28 | 2023-04-28 | 1% | 2023-06-28
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Estonia | EEEI180001 | ERI: POL CAPACITY PHASE 2 |  |  |  | 2020-10-28 | 2023-04-28 | 2023-04-28 | 1% | 2023-06-28
2020-12-31 | 2017 | Air Force Active | Major Military Construction |  | Poland | EPLK150006 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2017-11-27 | 2020-03-26 | 2020-12-08 | 100% | 2020-12-08
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Poland | EPPW170003 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2017-11-27 | 2020-03-26 | 2021-01-27 | 100% | 2021-01-27
2021-01-31 | 2018 | Air Force Active | Major Military Construction |  | Latvia | EVGA180001 | ERI: EXPAND STRATEGIC AIRLIFT APRON |  |  |  | 2019-01-09 | 2021-01-03 | 2020-12-15 | 100% | 2021-01-01
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Arizona | United States | FBNV033002 | UPL-Aerospace Ground Equipment (AGE) Complex |  |  |  | 2019-12-10 | 2023-05-08 | 2023-05-08 | 5% | 2023-05-08
2021-04-30 | 2019 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | FBNV163001 | Add/Alter MXG Engine Maintenance Facility |  |  |  | 2020-04-09 | 2021-10-01 | 2021-07-01 | 94% | 2021-07-31
2021-03-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Arizona | United States | FBNV163001 | Add/Alter MXG Engine Maintenance Facility |  |  |  | 2020-04-09 | 2021-10-01 | 2020-04-09 | 80% | 2021-10-31
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Delaware | United States | FJXT133000 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2020-04-24 | 2022-01-23 | 2022-01-23 | 16% | 2022-05-25
2021-04-30 | 2016 | Air Force Active | Unspecified Minor Military Construction | Texas | United States | FNWZ100071A | Military Working Dogs Facs - Multi |  |  |  | 2018-10-22 | 2019-10-22 | 2021-10-30 | 42% | 2021-12-31
2021-04-30 | 2017 | Air Force Active | Major Military Construction | California | United States | FSPM053503C | FLIGHT LINE FIRE STATION |  |  |  | 2018-06-19 | 2021-01-12 | 2021-04-30 | 100% | 2020-07-31
2021-04-30 | 2020 | Air Force Active | Major Military Construction | California | United States | FSPM173504 | Joint Simulation Environment Facility - Edwards |  |  |  | 2021-06-09 | 2024-01-09 | 2024-01-09 | 1% | 2021-04-30
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA033003 | Flightline Fire Station |  |  |  | 2018-01-29 | 2019-07-23 | 2021-02-26 | 100% | 2020-02-26
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Florida | United States | FTFA043000 | Advanced Munitions Technology Complex |  |  |  | 2019-04-24 | 2021-04-26 | 2021-10-15 | 63% | 2022-01-13
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Florida | United States | FTFA053017 | Dormitories Replace Dorm 19 |  |  |  | 2019-11-06 | 2021-11-05 | 2022-01-15 | 40% | 2022-04-15
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA093965 | F-35A Student Dormitory II |  |  |  | 2019-05-02 | 2021-05-01 | 2021-06-01 | 86% | 2021-08-30
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Florida | United States | FTFA143913 | F-35A Integrated Trng Center Academics Bldg |  |  |  | 2019-06-11 | 2021-06-10 | 2021-06-10 | 95% | 2021-09-08
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Florida | United States | FTFA163003 | F-35A Armament Research Facility Addition (B614) |  |  |  | 2018-11-01 | 2020-08-22 | 2021-05-28 | 98% | 2021-05-28
2021-04-30 | 2020 | Air Force Active | Major Military Construction | Florida | United States | FTFA163007 | Cyberspace Test Facility |  |  |  | 2020-11-10 | 2022-10-31 | 2022-10-31 | 10% | 2022-10-31
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1053834 | F-35 Aircraft Maintenance Unit Admin Facility |  |  |  | 2019-08-05 | 2021-05-31 | 2021-07-17 | 86% | 2021-06-28
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW1054329 | F-35 Conventional Munitions Maintenance Fac |  |  |  | 2019-10-16 | 2021-07-31 | 2021-09-23 | 67% | 2021-09-13
2021-01-31 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW170107 | F-35A MISSILE MAINTENANCE FACILITY |  |  |  | 2019-06-14 | 2020-10-31 | 2021-01-08 | 100% | 2021-01-08
2020-10-31 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180106 | F-35A SATELLITE DINING FACILITY |  |  |  | 2018-09-05 | 2020-08-05 | 2020-09-22 | 100% | 2020-10-01
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180107 | F-35A Consolidated Munitions Admin Facility |  |  |  | 2018-04-05 | 2020-02-14 | 2021-08-11 | 97% | 2020-07-02
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Alaska | United States | FTQW180109 | F-35A School Age Facility |  |  |  | 2019-03-12 | 2020-08-01 | 2021-07-01 | 97% | 2021-07-01
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FTQW183001 | F-35A Aircraft Weather Shelter SQD #2 |  |  |  | 2018-06-15 | 2020-05-06 | 2021-03-18 | 100% | 2021-03-18
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Alaska | United States | FXSB982839 | ADD/ALTER AWACS ALERT HANGAR |  |  |  | 2020-04-16 | 2022-03-17 | 2022-03-17 | 45% | 2022-05-27
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN083004 | MISSILE TRANSFER FACILITY |  |  |  | 2017-06-15 | 2020-10-05 | 2020-12-31 | 100% | 2020-08-06
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Wyoming | United States | GHLN153001 | FE WARREN--WEAPON STORAGE FACILITY |  |  |  | 2019-02-20 | 2022-06-04 | 2022-11-05 | 22% | 2023-03-05
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Washington | United States | GJKZ040009 | SERE PIPELINE DORMITORY (150 RM) |  |  |  | 2019-02-22 | 2021-09-19 | 2021-09-19 | 79% | 2021-11-18
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Washington | United States | GJLK1053425 | ADD/ALTER Joint Personnel Recovery Agency Command & Control, Mission Support Facility |  |  |  | 2020-09-24 | 2022-10-20 | 2022-10-20 | 4% | 2022-10-20
2021-01-31 | 2012 | Air Force Active | Major Military Construction |  | Italy | HACC123204 | UAS SATCOM Relay Pads and Facility |  |  |  | 2016-07-23 | 2018-04-07 | 2021-01-27 | 100% | 2021-01-27
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Hawaii | United States | KNMD043004 | F-22 FIGHTER ALERT FACILITY |  |  |  | 2018-11-01 | 2020-10-22 | 2021-11-23 | 84% | 2021-05-28
2021-04-30 | 2020 | Air Force Active | Major Military Construction | Utah | United States | KRSM1065068 | GBSD Mission Integration Facility |  |  |  | 2020-08-17 | 2023-01-15 | 2023-04-04 | 15% | 2023-06-03
2021-04-30 | 2017 | Air Force Active | Unspecified Minor Military Construction | Utah | United States | KRSM113031 | Construct East Gate Canopy and Inspection Facility |  |  |  | 2021-03-19 | 2022-07-29 | 2022-07-29 | 1% | 2022-07-29
2020-11-30 | 2017 | Air Force Active | Major Military Construction | Utah | United States | KRSM143006 | 649 MUNS Precision Guided Missile Maintenance Facility |  |  |  | 2018-02-12 | 2020-02-12 | 2020-11-17 | 100% | 2020-11-17
2021-04-30 | 2018 | Air Force Active | Major Military Construction | New Mexico | United States | KWRD143000 | RPA FIXED GROUND CONTROL STATION FACILITY |  |  |  | 2020-02-28 | 2021-06-21 | 2021-06-21 | 83% | 2021-09-19
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Bulgaria | LBPG150008 | ERI: FIGHTER RAMP EXTENSION |  |  |  | 2019-02-11 | 2022-01-21 | 2022-01-13 | 3% | 2022-06-20
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Bulgaria | LBPG150009 | ERI: CONSTRUCT SQUADRON OPERATIONS/OPERATION ALERT FACILITY |  |  |  | 2019-02-11 | 2022-02-11 | 2022-02-11 | 3% | 2022-07-11
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Turkey | LJYC133003 | AIRFIELD FIRE / CRASH RESCUE STATION |  |  |  | 2019-03-04 | 2023-04-12 | 2023-04-12 | 40% | 2023-07-14
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Turkey | LJYC183004 | REPLACE PERIMETER FENCE |  |  |  | 2019-06-11 | 2023-06-07 | 2023-06-07 | 40% | 2023-07-10
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | LKTC203101 | MQ-9 CPIP GCS Operations Facility |  |  |  | 2019-10-13 | 2021-07-03 | 2021-12-28 | 50% | 2021-12-28
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | LKTC203102 | MQ-9 CPIP Ops & Command Center Facility |  |  |  | 2019-11-13 | 2021-11-02 | 2021-12-14 | 50% | 2021-12-28
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150007 | ERI: EXTEND PARKING APRONS |  |  |  | 2018-01-17 | 2021-08-02 | 2021-08-02 | 38% | 2021-08-02
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150008 | ERI: CONSTRUCT MUNITIONS STORAGE AREA |  |  |  | 2020-04-21 | 2021-03-12 | 2021-05-20 | 16% | 2021-11-12
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150009 | ERI: CONSTRUCT ONE-BAY HANGAR |  |  |  | 2020-07-01 | 2021-08-02 | 2021-08-02 | 38% | 2021-08-02
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Romania | LRCT150010 | ERI: CONSTRUCT SQUADRON OPERATIONS FACILITY |  |  |  | 2020-04-21 | 2021-03-12 | 2021-05-12 | 38% | 2021-11-12
2021-01-31 | 2018 | Air Force Active | Major Military Construction |  | Romania | LRCT180001 | ERI: UPGRADE INSTALLATION UTILITIES INFRASTRUCTURE |  |  |  | 2019-01-18 | 2021-01-17 | 2021-01-17 | 100% | 2021-06-16
2021-04-30 | 2016 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ154288 | IMPROVE FAMILY HSG INFRASTRUCTURE, PH 4 |  |  |  | 2018-11-26 | 2020-11-25 | 2022-02-03 | 84% | 2022-04-04
2021-04-30 | 2016 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ164289 | IMPROVE FAMILY HSG INFRASTRUCTURE, PH 5 |  |  |  | 2018-11-26 | 2020-11-25 | 2022-02-03 | 84% | 2022-04-04
2021-04-30 | 2018 | Air Force Active | Military Family Housing Improvement |  | Japan | LXEZ184546 | IMPROVE FAMILY HOUSING, KAB SEBILLE MANOR (100 UN) |  |  |  | 2020-10-01 | 2022-12-30 | 2022-12-30 | 2% | 2023-01-29
2021-04-30 | 2017 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173002 | ENTRY GATE INSPECTION AREA |  |  |  | 2020-06-15 | 2021-06-26 | 2021-07-19 | 48% | 2021-07-19
2021-04-30 | 2017 | Air Force Active | Unspecified Minor Military Construction | Mississippi | United States | MAHG173003 | COMMERCIAL VEHICLE INSPECTION |  |  |  | 2020-06-15 | 2021-06-26 | 2021-07-19 | 48% | 2021-07-19
2020-10-31 | 2016 | Air Force Active | Major Military Construction | New Mexico | United States | MHMV043095 | SPACE VEHICLES COMPONENT DEVELOPMENT LAB |  |  |  | 2018-08-21 | 2020-01-13 | 2020-10-15 | 100% | 2020-12-14
2021-04-30 | 2018 | Air Force Active | Major Military Construction | New Mexico | United States | MHMV083126A | Replace Fire Station 3 |  |  |  | 2020-11-19 | 2021-03-26 | 2021-10-13 | 1% | 2021-09-22
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R5 | BMT RECRUIT DORMITORY 5 |  |  |  | 2019-03-20 | 2021-10-12 | 2021-10-12 | 16% | 2022-01-22
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737R6 | BMT RECRUIT DORMITORY 6 |  |  |  | 2020-05-10 | 2022-10-27 | 2022-10-27 | 10% | 2022-12-15
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Texas | United States | MPLS083737S3 | BMT CLASSROOMS/DINING FACILITY PHASE 3 |  |  |  | 2019-05-01 | 2022-06-22 | 2022-06-22 | 16% | 2021-12-12
2021-04-30 | 2016 | Air Force Active | Unspecified Minor Military Construction | Texas | United States | MPLS113003A | Telephone Maintenance Facility |  |  |  | 2019-05-02 | 2020-06-30 | 2021-05-21 | 95% | 2021-07-21
2021-04-30 | 2015 | Air Force Active | Major Military Construction | Texas | United States | MPLS3274JB | FIRE STATION |  |  |  | 2015-07-08 | 2020-06-03 | 2021-06-11 | 95% | 2021-03-15
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET143006 | CONSOLIDATED CORROSION CONTROL FACILITY |  |  |  | 2021-04-26 | 2023-04-27 | 2023-04-27 | 3% | 2023-05-31
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153501 | F-35A FLIGHT SIMULATOR FACILITY |  |  |  | 2019-07-18 | 2020-11-01 | 2021-12-01 | 65% | 2022-01-02
2021-04-30 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153503 | F-35A FUEL SYSTEM MAINTENANCE DOCK 2 BAY |  |  |  | 2020-10-05 | 2022-01-28 | 2022-06-02 | 2% | 2022-04-01
2021-04-30 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153504 | F-35A PARKING APRON |  |  |  | 2020-09-04 | 2021-07-26 | 2021-11-26 | 2% | 2021-11-01
2021-04-30 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153505 | F-35A AGE FACILITY |  |  |  | 2020-01-17 | 2021-04-01 | 2021-07-12 | 91% | 2021-07-12
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153506 | F-35A FIELD TRAINING DETACHMENT FACILITY |  |  |  | 2020-09-04 | 2022-02-09 | 2022-04-06 | 2% | 2022-03-09
2020-11-30 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153507 | F-35A ADAL PARTS STORE |  |  |  | 2019-12-11 | 2020-12-18 | 2020-12-18 | 1% | 2021-02-01
2021-04-30 | 2019 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153508 | F-35A 6-BAY HANGAR |  |  |  | 2020-11-09 | 2022-05-11 | 2022-05-11 | 17% | 2022-04-01
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153509 | F-35A INFRASTRUCTURE |  |  |  | 2020-04-09 | 2022-08-31 | 2022-11-30 | 38% | 2022-11-30
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153513 | F-35A 6-BAY HANGAR |  |  |  | 2022-08-05 | 2022-03-21 | 2022-08-05 | 3% | 2022-02-07
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | United Kingdom | MSET153514 | F-35A SQUADRON OPERATIONS AND AMU |  |  |  | 2019-07-18 | 2021-02-01 | 2022-03-01 | 64% | 2022-03-30
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Massachusetts | United States | MXRD153006 | MIT-Lincoln Laboratory (West Lab CSL/MIF) |  |  |  | 2022-03-01 | 2022-05-18 | 2024-11-22 | 2% | 2025-03-01
2021-04-30 | 2020 | Air Force Active | Major Military Construction | Arkansas | United States | NKAK123007 | C-130H/J FUSELAGE TRAINER FACILITY |  |  |  | 2020-09-28 | 2022-10-15 | 2022-10-15 | 1% | 2022-10-15
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Arizona | United States | NUEX093016 | COMMUNICATIONS FACILITY |  |  |  | 2018-02-26 | 2020-02-26 | 2021-06-30 | 97% | 2021-06-30
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Florida | United States | NVZR153710 | KC135 Beddown Add Flt Simltr Training |  |  |  | 2020-03-20 | 2021-05-26 | 2021-08-26 | 49% | 2021-06-23
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Florida | United States | NVZR153711 | KC135 Beddown OG/MXG HQ |  |  |  | 2019-10-20 | 2021-05-11 | 2021-05-24 | 73% | 2021-08-22
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Montana | United States | NZAS043002 | TACTICAL RESPONSE FORCE ALERT FACILITY |  |  |  | 2018-08-22 | 2020-08-14 | 2020-08-31 | 100% | 2020-08-31
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Montana | United States | NZAS173001 | Relocate Missile Maintenance Dispatch Facility (MMDF) |  |  |  | 2019-06-25 | 2021-05-15 | 2021-05-15 | 77% | 2021-05-15
2021-04-30 | 2017 | Air Force Active | Major Military Construction |  | Australia | PAF150400 | APR EXPAND AIRCRAFT PARKING APRON |  |  |  | 2018-08-01 | 2019-10-15 | 2021-06-11 | 99% | 2020-12-17
2021-04-30 | 2018 | Air Force Active | Major Military Construction |  | Australia | PAF160600 | APR - BULK FUEL STORAGE TANKS |  |  |  | 2019-10-26 | 2022-10-25 | 2023-06-01 | 37% | 2023-06-01
2021-04-30 | 2020 | Air Force Active | Major Military Construction |  | Australia | PAF180300 | APSI - EARTH COVERED MAGAZINES |  |  |  | 2020-11-02 | 2022-05-20 | 2022-02-03 | 17% | 2022-02-03
2021-04-30 | 2015 | Air Force Active | Major Military Construction |  | Lithuania | PAYZ15001B | ERI: Improve Airfield Infrastructure |  |  |  | 2017-01-12 | 2021-07-15 | 2021-07-15 | 90% | 2021-08-15
2021-04-30 | 2015 | Air Force Active | Major Military Construction |  | Italy | PAYZ15001H | ERI: Improve Weapons Storage Facility |  |  |  | 2017-12-04 | 2020-08-28 | 2022-12-17 | 64% | 2022-12-17
2021-04-30 | 2016 | Air Force Active | Major Military Construction |  | Japan | PAYZ16000B | Munitions Storage Igloos |  |  |  | 2020-10-07 | 2021-09-07 | 2021-09-07 | 2% | 2021-09-06
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Alabama | United States | PNQS072140 | JAG School Expansion |  |  |  | 2019-07-10 | 2020-12-31 | 2021-05-28 | 57% | 2021-05-28
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Alabama | United States | PNQS103165 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2019-12-03 | 2021-05-26 | 2021-06-25 | 52% | 2021-09-23
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Kansas | United States | PRQE055155 | Combat Arms Facility |  |  |  | 2018-10-24 | 2021-06-30 | 2021-06-30 | 98% | 2020-10-15
2021-04-30 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163001 | KC-46A ADAL B2319 FOR BOOM OPERATOR TRAINER |  |  |  | 2019-03-19 | 2021-11-03 | 2021-11-03 | 93% | 2021-11-03
2021-04-30 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163006 | KC-46A ADAL B3209 FOR FUSELAGE TRAINER |  |  |  | 2018-11-05 | 2019-11-09 | 2021-08-30 | 99% | 2021-07-24
2020-10-31 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163007 | KC-46A ALTER FACILITIES FOR MAINTENANCE |  |  |  | 2019-04-30 | 2020-04-29 | 2020-10-05 | 100% | 2020-10-05
2021-04-30 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163010 | KC-46A Alter BLDGS FOR OPS AND TFI AMU-AMXS |  |  |  | 2019-09-26 | 2021-05-07 | 2021-10-04 | 44% | 2021-10-18
2021-04-30 | 2018 | Air Force Active | Major Military Construction | New Jersey | United States | PTFL163019 | KC-46A TWO BAY GENERAL PURPOSE MX HANGAR |  |  |  | 2019-08-23 | 2021-07-23 | 2021-10-17 | 73% | 2021-10-17
2021-04-30 | 2018 | Air Force Active | Major Military Construction | North Dakota | United States | QJVF012005 | Indoor Firing Range |  |  |  | 2019-09-11 | 2020-08-18 | 2021-08-21 | 75% | 2021-09-20
2020-10-31 | 2016 | Air Force Active | Major Military Construction |  | Japan | QKKA154008 | IMPROVE FAMILY HOUSING PH 3, A/C, WEATHERIZATION |  |  |  | 2017-10-20 | 2020-10-19 | 2020-10-07 | 100% | 2020-10-19
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Georgia | United States | QSEU083023 | PERSONNEL RECOVERY 4-BAY HANGAR/HMU |  |  |  | 2020-10-28 | 2022-10-28 | 2022-10-28 | 1% | 2023-03-28
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Nevada | United States | RKMF063004 | RED FLAG 5th GEN FACILITY ADDITION |  |  |  | 2019-08-13 | 2021-08-02 | 2021-08-27 | 45% | 2021-08-27
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Nevada | United States | RKMF103011 | F-35A MUNITIONS MAINTENANCE FACILITIES |  |  |  | 2020-01-30 | 2021-08-22 | 2021-10-16 | 50% | 2021-10-16
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Nevada | United States | RKMF123009 | CRH Simulator |  |  |  | 2019-11-20 | 2021-06-02 | 2021-06-02 | 79% | 2021-07-02
2021-04-30 | 2020 | Air Force Active | Major Military Construction | Nevada | United States | RKMF163007 | 365 ISR Group Consolidated Facility |  |  |  | 2020-12-16 | 2022-12-04 | 2022-12-04 | 3% | 2022-11-10
2020-11-30 | 2017 | Air Force Active | Major Military Construction | Nevada | United States | RKMF173001 | F-35A POL FILL STAND ADDITION |  |  |  | 2019-03-14 | 2020-11-03 | 2020-09-03 | 100% | 2020-09-03
2021-04-30 | 2018 | Air Force Active | Unspecified Minor Military Construction | Nevada | United States | RKMF173010 | HYDRAZINE FUEL STORAGE & SERVICING FACILITY |  |  |  | 2019-11-12 | 2020-11-11 | 2021-12-01 | 90% | 2021-12-01
2020-11-30 | 2018 | Air Force Active | Major Military Construction | Nevada | United States | RKMF183001 | VIRTUAL WARFARE CENTER OPERATIONS FACILITY |  |  |  | 2018-08-10 | 2020-07-30 | 2020-11-13 | 100% | 2020-09-28
2021-04-30 | 2020 | Air Force Active | Major Military Construction | Nevada | United States | RKMF203001 | F-35A MUNITIONS ASSEMBLY CONVEYOR (MAC) FACILITY |  |  |  | 2020-10-22 | 2021-09-30 | 2021-12-31 | 2% | 2021-12-31
2021-04-30 | 2020 | Air Force Active | Major Military Construction | Nevada | United States | RKMF203007 | Joint Simulation Environment (JSE) - Nellis |  |  |  | 2020-08-03 | 2022-07-24 | 2022-07-24 | 8% | 2022-08-23
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Nebraska | United States | SGBP1047602 | PARKING LOT, USSTRATCOM |  |  |  | 2019-05-30 | 2020-08-21 | 2020-08-21 | 100% | 2020-08-21
2021-04-30 | 2019 | Air Force Active | Unspecified Minor Military Construction |  | Korea, South | SMYU073011 | MILITARY WORKING DOG KENNEL SUPPORTING FACILITY |  |  |  | 2019-09-30 | 2021-05-03 | 2021-02-04 | 100% | 2021-02-04
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Florida | United States | SXHT013001 | FIRE/CRASH RESCUE STATION |  |  |  | 2017-07-26 | 2019-03-12 | 2021-06-01 | 96% | 2021-01-15
2021-01-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | TDKA063002D | MWD Kennel Facility |  |  |  | 2019-09-09 | 2020-12-02 | 2020-12-28 | 100% | 2020-12-28
2021-04-30 | 2020 | Air Force Active | Major Military Construction | Colorado | United States | TDKA143002 | SOCNORTH THEATER OPERATIONAL SUPPORT FACILITY |  |  |  | 2022-04-01 | 2023-08-13 | 2023-08-13 | 1% | 2023-08-13
2021-04-30 | 2012 | Air Force Active | Major Military Construction |  | Germany | TYFR063017 | DORMITORY (192 RM) |  |  |  | 2015-07-28 | 2017-06-27 | 2022-03-30 | 73% | 2022-03-30
2020-10-31 | 2013 | Air Force Active | Unspecified Minor Military Construction |  | Germany | TYFR106020U | MUNITIONS SHIPPING AND RECEIVING FACILITY |  |  |  | 2016-05-24 | 2017-11-30 | 2020-06-17 | 100% | 2020-06-17
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Georgia | United States | UHHZ163000 | COMMERCIAL VEHICLE VISITOR CONTROL FACILITY |  |  |  | 2020-06-18 | 2021-12-10 | 2021-12-10 | 3% | 2022-03-10
2021-04-30 | 2019 | Air Force Active | Major Military Construction | New York | United States | ULDF123001 | Anti-terrorism Perimeter Security/Entry Control Point |  |  |  | 2020-02-10 | 2021-08-03 | 2021-11-25 | 5% | 2021-11-25
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Illinois | United States | VDYD101053 | Consolidated Communications Facility Add/Alt |  |  |  | 2020-09-25 | 2022-05-10 | 2023-10-01 | 17% | 2023-12-27
2021-04-30 | 2016 | Air Force Active | Major Military Construction | North Carolina | United States | VKAG013004R5 | AIR TRAFFIC CONTROL TOWER/BASE OPERATIONS FACILITY |  |  |  | 2019-08-14 | 2021-03-04 | 2021-05-23 | 88% | 2021-06-15
2021-04-30 | 2019 | Air Force Active | Major Military Construction | South Carolina | United States | VLSB193001 | CPIP MQ-9 MCE GROUP (MILCON) |  |  |  | 2021-02-02 | 2023-03-01 | 2023-03-01 | 1% | 2023-03-01
2020-10-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Texas | United States | VNVP177501 | Repair Sheppard Gate Entry Control Facility |  |  |  | 2019-04-25 | 2020-04-04 | 2020-10-09 | 100% | 2020-10-09
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK093003 | AIR TRAFFIC CONTROL TOWER |  |  |  | 2017-05-17 | 2019-03-07 | 2021-04-14 | 100% | 2021-04-14
2021-04-30 | 2015 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK153005 | KC-46A TWO-BAY DEPOT MAINTENANCE HANGAR |  |  |  | 2017-05-11 | 2019-04-30 | 2021-05-31 | 99% | 2021-01-21
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193001 | KC-46A Depot Maintenance Hangar |  |  |  | 2019-10-10 | 2022-03-19 | 2022-08-14 | 27% | 2022-08-15
2021-04-30 | 2017 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193003 | E-3G MISSION AND FLIGHT SIMULATOR TRAINING FACILITY |  |  |  | 2019-03-05 | 2021-03-04 | 2021-07-12 | 73% | 2021-07-12
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Oklahoma | United States | WWYK193014 | KC-46A Depot Fuel Maintenance Hangar |  |  |  | 2019-10-30 | 2022-03-20 | 2022-03-20 | 19% | 2022-08-29
2021-04-30 | 2020 | Air Force Active | Major Military Construction | California | United States | XDAT1026962 | KC-46A ALTER B181/B185/B187 SQUAD OPS/AMU |  |  |  | 2020-07-16 | 2021-09-19 | 2021-11-27 | 47% | 2021-11-27
2021-04-30 | 2018 | Air Force Active | Major Military Construction | California | United States | XDAT1051930 | KC-46A Aircraft 3-Bay Maintenance Hangar |  |  |  | 2020-12-30 | 2022-06-17 | 2022-06-17 | 35% | 2022-05-03
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU193005 | FIRE STATION #2 |  |  |  | 2019-12-10 | 2021-11-29 | 2022-06-21 | 22% | 2022-08-20
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU193006 | ACS Flight Simulator |  |  |  | 2019-12-03 | 2021-11-22 | 2022-04-02 | 40% | 2022-03-21
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Florida | United States | XLWU203006 | Child Development Center |  |  |  | 2020-10-16 | 2022-12-26 | 2022-09-16 | 8% | 2022-12-15
2020-10-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | XQPZ124004 | Const Perm ECP-N Stad Blvd |  |  |  | 2018-11-15 | 2020-11-14 | 2020-10-01 | 100% | 2020-09-11
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Colorado | United States | XQPZ164001 | Air Force CyberWorx |  |  |  | 2021-07-15 | 2023-08-13 | 2023-08-13 | 6% | 2023-08-13
2021-04-30 | 2020 | Air Force Active | Unspecified Minor Military Construction | Colorado | United States | XQPZ174006 | Expand Midfield Facility |  |  |  | 2021-07-15 | 2023-02-27 | 2023-02-27 | 2% | 2023-02-27
2021-04-30 | 2016 | Air Force Active | Major Military Construction | Missouri | United States | YWHG031002R2 | YWHG031002R2, Consolidated Stealth Operations & Nuclear Alert Facility |  |  |  | 2019-03-19 | 2021-04-30 | 2021-05-11 | 76% | 2021-06-01
2021-04-30 | 2019 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV093301 | ADAL Intelligence Production Facility |  |  |  | 2020-09-06 | 2024-06-10 | 2024-06-10 | 3% | 2023-01-22
2021-04-30 | 2018 | Air Force Active | Major Military Construction | Ohio | United States | ZHTV153201 | FIRE/CRASH RESCUE STATION |  |  |  | 2020-05-18 | 2021-09-03 | 2021-09-03 | 60% | 2021-11-03
2021-04-30 | 2020 | Air Force Active | Military Family Housing Improvement |  | Japan | ZNRE204308 | Improve Family Housing Phase 8a |  |  |  | 2020-09-16 | 2022-09-06 | 2022-09-06 | 7% | 2023-01-05
2021-04-30 | 2020 | Air Force Reserve | Major Military Construction | Maryland | United States | AJXF223744 | Aeromedical Evacuation Squadron Training/Admin. Facility |  |  |  | 2020-09-23 | 2022-05-26 | 2022-05-26 | 2%
2021-04-30 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Louisiana | United States | AWUB105005 | Missile Maintenance Facility |  |  |  | 2019-03-30 | 2020-03-31 | 2021-08-31 | 50%
2021-04-30 | 2019 | Air Force Reserve | Major Military Construction | Indiana | United States | CTGB169002 | Aerial Port Facility |  |  |  | 2019-08-26 | 2020-10-27 | 2021-07-01 | 38%
2021-04-30 | 2019 | Air Force Reserve | Major Military Construction | Indiana | United States | CTGB989003 | Aircraft Maintenance Hanger, Bldg. 437 |  |  |  | 2020-09-16 | 2022-05-04 | 2022-05-04 | 7%
2021-04-30 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Texas | United States | DDPM130007 | Munitions Training/Admin Facility |  |  |  | 2018-12-12 | 2020-09-14 | 2021-01-31 | 100%
2021-04-30 | 2016 | Air Force Reserve | Major Military Construction | Georgia | United States | FGWB009002 | Fire Station |  |  |  | 2017-12-13 | 2019-06-06 | 2021-09-01 | 91%
2021-04-30 | 2018 | Air Force Reserve | Major Military Construction | Hawaii | United States | KNMD624007 | Consolidated Training Facility |  |  |  | 2021-01-29 | 2022-07-11 | 2022-07-11 | 2%
2021-04-30 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Mississippi | United States | MAHG063004 | Aeromedical Staging Squadron Facility |  |  |  | 2019-12-11 | 2020-10-31 | 2021-07-09 | 86%
2021-04-30 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | California | United States | PDPG120514 | Satellite Fire Station |  |  |  | 2018-09-14 | 2019-11-08 | 2021-05-14 | 93%
2021-04-30 | 2019 | Air Force Reserve | Major Military Construction | New York | United States | RVKQ079104 | Physical Fitness Center |  |  |  | 2019-09-02 | 2021-07-23 | 2021-08-21 | 74%
2021-04-30 | 2018 | Air Force Reserve | Major Military Construction | Florida | United States | SXHT103001 | Guardian Angel Facility |  |  |  | 2018-08-29 | 2020-07-19 | 2021-10-02 | 61%
2021-04-30 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Florida | United States | SXHT171217 | Addition To 39 RQS B 673 |  |  |  | 2020-03-01 | 2021-03-15 | 2021-05-14 | 90%
2021-04-30 | 2019 | Air Force Reserve | Major Military Construction | Florida | United States | SXHT203000 | HC-130J General Maintenance Hanger |  |  |  | 2020-09-24 | 2022-07-25 | 2022-07-25 | 2%
2021-04-30 | 2018 | Air Force Reserve | Major Military Construction | Georgia | United States | UHHZ073003 | Consolidated Mission Complex, Phase 2 |  |  |  | 2019-11-07 | 2021-11-26 | 2022-02-20 | 47%
2021-04-30 | 2020 | Air Force Reserve | Major Military Construction | Georgia | United States | UHHZ073005 | Consolidated Mission Complex, Phase 3 |  |  |  | 2021-03-18 | 2023-04-11 | 2023-04-11 | 2%
2021-04-30 | 2017 | Air Force Reserve | Major Military Construction | North Carolina | United States | VKAG159021 | KC-46A Construct Two Bay Corrosion/Fuel Cell Hangar |  |  |  | 2017-09-27 | 2020-09-09 | 2021-05-15 | 97%
2019-01-31 | 2017 | Air Force Reserve | Major Military Construction | North Carolina | United States | VKAG159022 | KC-46A ADAL Bldg For AGE/Fuselage Training |  |  |  | 2017-11-08 | 2019-04-19 | 2019-12-31 | 99%
2021-04-30 | 2018 | Air Force Reserve | Major Military Construction | North Carolina | United States | VKAG159026 | KC-46A ADAL Bldg. for Alternate Mission Equipment Storage |  |  |  | 2020-09-29 | 2022-07-08 | 2022-07-08 | 2%
2021-04-30 | 2018 | Air Force Reserve | Major Military Construction | Massachusetts | United States | YTPM059004 | Indoor Small Arms Range |  |  |  | 2019-11-04 | 2020-12-12 | 2021-05-30 | 99%
2021-04-30 | 2017 | Air National Guard | Major Military Construction | Maryland | United States | AJXF039040 | Munitions Load Crew Training |  |  |  | 2019-11-14 | 2021-05-15 | 2021-05-12 | 6% | 2021-03-12
2020-09-30 | 2016 | Air National Guard | Major Military Construction | New Jersey | United States | AQRC059093 | Fuel Cell and Corrosion Control Hangar and Shops |  |  |  | 2019-02-06 | 2020-08-04 | 2020-11-02 | 94% | 2020-07-31
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Alabama | United States | BRKR999147 | Add to and Alter Distributed Ground Station Facility |  |  |  | 2014-10-31 | 2016-10-23 | 2019-04-30 | 99% | 2017-09-27
2019-08-06 | 2015 | Air National Guard | Unspecified Minor Military Construction | Connecticut | United States | CEKT129080 | Add to Fire Station |  |  |  | 2016-03-01 | 2021-02-03 | 2018-05-18 | 99% | 2017-11-01
2019-09-10 | 2015 | Air National Guard | Major Military Construction | Connecticut | United States | CEKT139004 | Construct C-130 Fuel Cell and Corrosion Control Facility |  |  |  | 2015-07-24 | 2019-05-24 | 2020-05-24 | 99% | 2020-05-24
2021-04-30 | 2018 | Air National Guard | Major Military Construction | Connecticut | United States | CEKT139029 | Construct Base Entry Complex |  |  |  | 2019-01-22 | 2024-05-20 | 2023-02-24 | 99% | 2023-02-24
2021-01-31 | 2017 | Air National Guard | Major Military Construction | Connecticut | United States | CEKT139042 | Construct Small Air Terminal |  |  |  | 2017-09-29 | 2021-01-11 | 2021-02-28 | 98% | 2020-12-01
2021-04-30 | 2018 | Air National Guard | Unspecified Minor Military Construction | Connecticut | United States | CEKT149052 | Add/Alter B10018 for Security Forces |  |  |  | 2018-12-18 | 2024-12-26 | 2022-04-30 | 99% | 2020-09-15
2020-09-30 | 2016 | Air National Guard | Major Military Construction | Colorado | United States | CRWU069125 | ASE Maintenance and Storage Facility |  |  |  | 2019-08-20 | 2020-07-30 | 2020-12-30 | 84% | 2020-09-30
2019-09-10 | 2016 | Air National Guard | Unspecified Minor Military Construction | Virginia | United States | CVVM099000 | Joint Forces Headquarters - ANG Share |  |  |  | 2015-03-24 | 2015-10-31 | 2018-07-31 | 99% | 2018-07-31
2021-04-30 | 2017 | Air National Guard | Unspecified Minor Military Construction | Virginia | United States | CVVM179001 | Construct 200th Weather Flight Training Facility |  |  |  | 2017-09-12 | 2021-10-31 | 2020-10-01 | 99% | 2018-10-31
2020-09-30 | 2016 | Air National Guard | Major Military Construction | Florida | United States | DBEH143000 | NDAA Space Control Facility |  |  |  | 2018-09-07 | 2023-08-18 | 2020-10-15 | 99% | 2020-02-03
2020-09-30 | 2016 | Air National Guard | Major Military Construction | Alabama | United States | FAKZ059173 | TFI - Replace Squadron Operations Facility |  |  |  | 2018-09-05 | 2021-06-01 | 2021-11-01 | 87% | 2021-11-01
2021-04-30 | 2017 | Air National Guard | Major Military Construction | North Carolina | United States | FJRP159062 | C-17 Corrosion Control & Fuel Cell Hgr |  |  |  | 2019-05-17 | 2020-10-28 | 2021-08-31 | 87% | 2021-08-31
2021-04-30 | 2017 | Air National Guard | Major Military Construction | North Carolina | United States | FJRP159073 | C-17 Type III Hydrant Refueling Sys/Ramp Expansion |  |  |  | 2019-01-28 | 2021-01-27 | 2021-07-16 | 89% | 2021-07-16
2021-04-30 | 2019 | Air National Guard | Unspecified Minor Military Construction | North Carolina | United States | FJRP199080 | C-17 Simulator Facility |  |  |  | 2019-08-27 | 2020-08-26 | 2021-08-16 | 63% | 2021-08-16
2020-09-30 | 2016 | Air National Guard | Major Military Construction | Maine | United States | FKNN059220 | Add to and Alter Fire Crash/Rescue Station |  |  |  | 2016-10-03 | 2020-08-03 | 2020-11-15 | 99% | 2018-08-28
2019-08-06 | 2015 | Air National Guard | Unspecified Minor Military Construction | Maine | United States | FKNN119013 | ANG Portion of Maine State JFHQ-Augusta |  |  |  | 2015-06-05 | 2017-08-03 | 2019-07-19 | 99% | 2018-04-02
2020-03-05 | 2017 | Air National Guard | Major Military Construction | Minnesota | United States | FMKM089018 | Load Crew Training/Weapon Shops |  |  |  | 2017-10-16 | 2021-09-25 | 2019-12-31 | 99% | 2019-05-31
2019-09-10 | 2015 | Air National Guard | Unspecified Minor Military Construction | Colorado | United States | FTAE129002 | Construct Range Control Facility & Fitness Center |  |  |  | 2016-04-26 | 2016-06-22 | 2019-08-28 | 99% | 2017-06-01
2021-03-31 | 2017 | Air National Guard | Major Military Construction | Texas | United States | FWJH099082 | Consolidate Crew Readiness Facility, Building 1397 |  |  |  | 2018-10-16 | 2019-10-16 | 2021-04-20 | 98% | 2021-03-09
2020-08-31 | 2018 | Air National Guard | Major Military Construction | New York | United States | HAAW169006 | ISR: Add to Flight Training Unit, Building 641 |  |  |  | 2019-05-08 | 2020-05-07 | 2020-10-01 | 99% | 2020-07-06
2021-04-30 | 2018 | Air National Guard | Unspecified Minor Military Construction | New York | United States | HAAW179035 | ISR: ADAL Reaper Operations Center (B643) |  |  |  | 2020-07-30 | 2021-08-08 | 2021-05-21 | 13% | 2021-05-21
2020-09-30 | 2016 | Air National Guard | Major Military Construction | Arkansas | United States | HKRZ129076 | ISR: Construct DGS RPA IS SCIF |  |  |  | 2018-02-01 | 2020-02-01 | 2020-11-15 | 94% | 2020-05-01
2021-04-30 | 2017 | Air National Guard | Unspecified Minor Military Construction | Wisconsin | United States | HTUV132007 | Add to Fire Station, Building 621 |  |  |  | 2018-06-01 | 2021-11-02 | 2021-06-30 | 99% | 2020-07-16
2021-04-30 | 2017 | Air National Guard | Unspecified Minor Military Construction | Wisconsin | United States | HTUV169001 | Const Main gate Fac/and Roads |  |  |  | 2019-08-13 | 2020-12-15 | 2021-05-28 | 99% | 2020-12-01
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Montana | United States | JKSE129321 | Intra-Theater Airlift Conversion |  |  |  | 2014-10-20 | 2018-03-12 | 2018-07-31 | 99% | 2018-05-16
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Montana | United States | JKSE169101 | Construct Aircraft Apron |  |  |  | 2020-04-01 | 2020-10-25 | 2021-08-03 | 68% | 2021-08-03
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Illinois | United States | JLQN049119 | Construct New Fire Crash/Rescue Station |  |  |  | 2019-06-01 | 2023-10-18 | 2021-07-18 | 90% | 2021-07-18
2021-04-30 | 2018 | Air National Guard | Major Military Construction | Oregon | United States | KJAQ119006 | Construct Corrosion Control Hangar |  |  |  | 2020-04-09 | 2021-03-26 | 2021-08-01 | 25% | 2021-08-01
2021-04-30 | 2018 | Air National Guard | Major Military Construction | Oregon | United States | KJAQ159096 | Construct Indoor Range |  |  |  | 2021-03-19 | 2022-05-05 | 2022-04-05 | 1%
2021-04-30 | 2018 | Air National Guard | Unspecified Minor Military Construction | Hawaii | United States | KNMD179040 | MCCA Install 15 KVA Power Lines for Microgrid |  |  |  | 2019-05-14 | 2021-05-23 | 2021-06-15 | 80% | 2020-11-30
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Hawaii | United States | KNMD189008 | 3rd Bay F-22 LO/CRF B3408 |  |  |  | 2020-08-07 | 2023-03-05 | 2023-02-03 | 1%
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Indiana | United States | LDXF099060 | Add/Alter Bldg 37 for Distributed Common Grnd Stn |  |  |  | 2014-10-16 | 2016-02-28 | 2018-01-31 | 99% | 2016-12-16
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Pennsylvania | United States | LKLW099101 | Replace Operations Training/Dining Hall |  |  |  | 2020-01-07 | 2021-11-07 | 2021-11-10 | 74% | 2021-08-10
2021-04-30 | 2017 | Air National Guard | Major Military Construction | Florida | United States | LSGA019179 | Replace Fire Crash/Rescue Station |  |  |  | 2018-10-29 | 2024-04-20 | 2021-07-01 | 98% | 2021-01-29
2019-08-06 | 2015 | Air National Guard | Major Military Construction | Michigan | United States | MBMV129060 | RPA Beddown |  |  |  | 2015-05-07 | 2016-05-14 | 2017-07-31 | 99% | 2016-02-15
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Maryland | United States | MMMD129073 | 175th Network Warfare Squadron Facility |  |  |  | 2017-09-19 | 2018-10-06 | 2018-10-12 | 56% | 2018-10-31
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Virginia | United States | MUHJ179000 | Construct Cyber Ops Facility |  |  |  | 2021-02-20 | 2023-01-31 | 2022-12-01 | 1% | 2022-10-17
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Ohio | United States | PBXP929798 | Replace Fire Station |  |  |  | 2020-02-18 | 2022-01-08 | 2021-12-09 | 32% | 2022-05-25
2020-10-31 | 2018 | Air National Guard | Major Military Construction | California | United States | PDPG169013 | TFI Construct RPA Formal Training Unit |  |  |  | 2018-10-24 | 2020-04-16 | 2020-12-01 | 99% | 2020-09-01
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Maryland | United States | PJMS129058 | CYBER/ISR Facility |  |  |  | 2016-10-12 | 2017-10-12 | 2018-10-11 | 86% | 2018-10-11
2021-04-30 | 2018 | Air National Guard | Unspecified Minor Military Construction | South Carolina | United States | PSTE139022 | Add to Fire Station |  |  |  | 2019-11-05 | 2021-04-22 | 2021-06-01 | 18% | 2021-04-01
2021-04-30 | 2018 | Air National Guard | Major Military Construction | Tennessee | United States | PSXE999132 | Replace KC-135 Maintenance Hangar and Shops |  |  |  | 2019-08-22 | 2021-08-22 | 2021-11-26 | 70% | 2021-11-26
2021-02-28 | 2017 | Air National Guard | Unspecified Minor Military Construction | New Jersey | United States | PTFL129091 | Add to Vehicle Maintenance Facility, Bldg 3325 |  |  |  | 2018-11-14 | 2022-05-02 | 2021-03-25 | 98% | 2021-01-31
2020-09-30 | 2016 | Air National Guard | Major Military Construction | California | United States | QMSN099104 | Replace Vehicle Maintenance Facility |  |  |  | 2018-01-05 | 2020-03-20 | 2020-10-30 | 99% | 2019-07-15
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH059034 | NORTHCOM - Construct Alert Apron |  |  |  | 2021-03-11 | 2024-10-01 | 2024-10-01 | 1%
2020-09-30 | 2016 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH079073 | Replace Squadron Operations Facility |  |  |  | 2018-02-19 | 2020-12-25 | 2020-10-30 | 99% | 2020-06-04
2021-04-30 | 2019 | Air National Guard | Major Military Construction | Louisiana | United States | RQLH189009 | NORTHCOM - Construct Alert Facilities |  |  |  | 2021-03-11 | 2021-03-11 | 2021-09-11 | 1%
2019-09-10 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139901 | KC-46A ADAL Fuel Cell Building 253 |  |  |  | 2015-08-18 | 2016-11-19 | 2019-10-30 | 86% | 2019-08-05
2019-09-10 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139904 | KC-46A ADAL Maint Hangar Building 254 |  |  |  | 2015-08-18 | 2016-11-18 | 2021-04-09 | 8% | 2021-03-09
2019-09-10 | 2015 | Air National Guard | Major Military Construction | New Hampshire | United States | SZCQ139905 | KC-46A ADAL Airfield Pavements & Hydrant Systems |  |  |  | 2017-10-18 | 2018-10-13 | 2019-08-30 | 95% | 2018-12-05
2018-07-02 | 2014 | Air National Guard | Major Military Construction | Rhode Island | United States | TWLR129077 | C-130J Flight Simulator Training Facility |  |  |  | 2015-03-15 | 2015-12-14 | 2019-01-31 | 95% | 2017-11-15
2021-03-31 | 2017 | Air National Guard | Unspecified Minor Military Construction | Rhode Island | United States | TWLR139040 | Add to Fire Station Building 11 |  |  |  | 2018-04-16 | 2022-07-04 | 2021-04-30 | 99% | 2020-02-14
2021-03-31 | 2017 | Air National Guard | Unspecified Minor Military Construction | Rhode Island | United States | TWLR159061 | ANG Share - Joint Forces Headquarters Facility |  |  |  | 2017-09-07 | 2022-04-29 | 2021-04-30 | 98% | 2020-02-28
2021-04-30 | 2018 | Air National Guard | Major Military Construction | Missouri | United States | ULYB049040 | Replace Communications Facility |  |  |  | 2019-09-25 | 2021-03-23 | 2021-08-20 | 72% | 2021-07-30
2021-04-30 | 2020 | Air National Guard | Major Military Construction | Missouri | United States | ULYB169010 | C-130 Flight Simulator Facility |  |  |  | 2020-10-06 | 2022-03-31 | 2022-07-06 | 10% | 2022-07-06
2020-09-30 | 2017 | Air National Guard | Major Military Construction | Iowa | United States | VSSB099014 | Construct Consolidated Support Functions |  |  |  | 2017-09-13 | 2021-09-27 | 2020-10-25 | 97% | 2019-03-25
2021-04-30 | 2018 | Air National Guard | Major Military Construction | Kentucky | United States | WEAS079054 | Add/Alter Response Forces (RF) Facility (MCCA) |  |  |  | 2020-06-15 | 2021-11-17 | 2021-12-14 | 53% | 2021-11-14
2021-01-31 | 2019 | Air National Guard | Major Military Construction | New York | United States | WKVB109058 | Security Forces/Communication Training Facility |  |  |  | 2020-09-08 | 2022-01-01 | 2021-12-02 | 0%
2021-04-30 | 2018 | Air National Guard | Major Military Construction | Ohio | United States | WYTD079031 | NORTHCOM - Construct Alert Hangar |  |  |  | 2019-05-27 | 2020-07-23 | 2021-08-10 | 92% | 2021-01-13
2021-04-30 | 2020 | Air National Guard | Major Military Construction | Georgia | United States | XDQU109057 | Consolidated Joint Air Dominance Hangar&amp;&#x23;x2f&#x3b;Shops |  |  |  | 2020-10-27 | 2022-01-23 | 2022-07-31 | 6% | 2022-06-20
2021-04-30 | 2018 | Air National Guard | Unspecified Minor Military Construction | Georgia | United States | XDQU139458 | Add to Maint Shop B1923 |  |  |  | 2019-10-17 | 2020-11-15 | 2021-07-15 | 96% | 2021-03-25
2021-04-30 | 2020 | Air National Guard | Major Military Construction | Wisconsin | United States | XGFG189001 | F-35 Simulator Facility-B424 |  |  |  | 2021-04-15 | 2022-12-01 | 2022-11-01 | 1%
2020-11-30 | 2017 | Air National Guard | Unspecified Minor Military Construction | New Jersey | United States | YKSX159100 | Replace Range Control Tower, Bldg 16 |  |  |  | 2017-11-14 | 2021-07-06 | 2020-12-19 | 99% | 2020-03-19
2017-04-30 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 1235 | Physical Fitness Facility |  |  |  | 2012-07-12 | 2014-04-10 | 2016-03-31 | 95% | 2017-03-31
2017-05-31 | 2011 | Army Active | Major Military Construction | Colorado | United States | 13852 | Simulations Center |  |  |  | 2011-11-04 | 2016-07-23 | 2016-09-30 | 99% | 2016-12-12
2017-07-31 | 2012 | Army Active | Major Military Construction | Louisiana | United States | 17220 | Fire Station |  |  |  | 2013-11-06 | 2015-11-11 | 2017-01-19 | 99% | 2017-01-19
2019-08-31 | 2012 | Army Active | Major Military Construction | Kansas | United States | 2728 | Physical Fitness Facility |  |  |  | 2012-03-29 | 2017-02-08 | 2019-06-30 | 99% | 2019-06-30
2018-08-31 | 2013 | Army Active | Major Military Construction | Virginia | United States | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2013-10-15 | 2017-05-03 | 2018-03-14 | 98% | 2018-04-03
2021-04-30 | 2019 | Army Active | Major Military Construction | Kentucky | United States | 35782 | Digital Air/Ground Integration Range |  |  |  | 2020-02-06 | 2022-02-05 | 2022-08-01 | 28%
2019-08-31 | 2015 | Army Active | Major Military Construction | Virginia | United States | 41449 | Adv Individual Training Barracks Cplx, Ph3 |  |  |  | 2016-10-17 | 2018-10-07 | 2018-12-18 | 98% | 2019-05-15
2017-07-31 | 2013 | Army Active | Major Military Construction | Texas | United States | 45116 | Aircraft Component Maintenance Shop |  |  |  | 2013-08-08 | 2016-12-30 | 2016-12-30 | 97% | 2017-03-29
2017-07-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 5034 | Vehicle Maintenance Facility |  |  |  | 2013-01-24 | 2014-07-18 | 2017-01-31 | 99% | 2017-01-31
2018-08-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 51519 | Ballistic Evaluation Center |  |  |  | 2012-12-04 | 2015-02-15 | 2018-02-13 | 99% | 2017-07-14
2017-07-31 | 2014 | Army Active | Major Military Construction | Georgia | United States | 51868 | Adv Individual Training Barracks Cplx, Ph2 |  |  |  | 2015-01-06 | 2016-12-26 | 2017-07-21 | 94%
2019-08-31 | 2015 | Army Active | Major Military Construction | South Carolina | United States | 51937 | Trainee Barracks Complex 3, Ph1 |  |  |  | 2016-03-17 | 2018-03-17 | 2019-05-31 | 96% | 2019-07-01
2021-04-30 | 2019 | Army Active | Major Military Construction | Hawaii | United States | 52203 | Rotary Wing Parking Apron |  |  |  | 2020-11-13 | 2022-08-03 | 2022-08-03 | 3%
2018-08-31 | 2014 | Army Active | Major Military Construction | Virginia | United States | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  | 1700000 | 79933, 92764 | 2014-10-09 | 2017-12-09 | 2018-03-13 | 99% | 2018-07-09
2020-08-31 | 2011 | Army Active | Major Military Construction | California | United States | 53789 | Advanced Individual Training Barracks |  |  |  | 2013-10-22 | 2018-06-15 | 2020-06-30 | 98% | 2020-08-09
2021-04-30 | 2018 | Army Active | Major Military Construction | Georgia | United States | 55112 | Air Traffic Control Tower |  |  |  | 2019-04-17 | 2020-10-08 | 2021-06-20 | 66%
2018-08-31 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 55121 | Aerial Gunnery Range |  |  |  | 2015-12-31 | 2017-12-30 | 2018-05-01 | 98% | 2018-05-04
2021-04-30 | 2018 | Army Active | Major Military Construction | Washington | United States | 55199 | Fire Station |  |  |  | 2019-12-10 | 2021-11-29 | 2022-02-08 | 44%
2020-08-31 | 2016 | Army Active | Major Military Construction | New York | United States | 55578 | NCO Academy Complex |  | 2400000 | 71057, 71057, 92764 | 2017-05-23 | 2019-08-11 | 2020-03-27 | 99% | 2020-07-01
2017-07-31 | 2012 | Army Active | Major Military Construction |  | Germany | 55985 | Chapel |  |  |  | 2013-11-21 | 2016-03-23 | 2017-01-26 | 99% | 2017-01-30
2017-07-31 | 2011 | Army Active | Major Military Construction | Hawaii | United States | 56024 | Flood Mitigation |  |  |  | 2012-10-17 | 2014-10-14 | 2016-11-17 | 99% | 2017-04-06
2018-06-30 | 2012 | Army Active | Major Military Construction |  | Germany | 57594 | Satellite Communications Center |  |  |  | 2014-03-14 | 2017-11-05 | 2017-11-05 | 99% | 2016-12-27
2017-05-31 | 2011 | Army Active | Major Military Construction | Kentucky | United States | 58675 | Mout Collective Training Facility |  |  |  | 2011-07-06 | 2016-10-15 | 2016-09-09 | 99% | 2016-11-22
2018-08-31 | 2008 | Army Active | Major Military Construction |  | Korea, South | 58784 | Barracks Complex |  |  |  | 2008-04-22 | 2014-09-07 | 2018-01-18 | 99% | 2018-01-18
2020-08-31 | 2013 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility |  |  |  | 2016-04-13 | 2019-10-10 | 2019-11-13 | 99% | 2019-11-13
2020-08-31 | 2017 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility, Incr 2 | 86285 |  |  | 2016-04-13 | 2019-10-10 | 2019-11-13 | 99% | 2019-11-13
2020-08-31 | 2018 | Army Active | Major Military Construction | Virginia | United States | 58849 | Secure Admin/Operations Facility, Incr 3 | 86286 |  |  | 2016-04-13 | 2019-10-10 | 2019-11-13 | 99% | 2019-11-13
2021-04-30 | 2011 | Army Active | Major Military Construction | New York | United States | 59044 | Science Facility, Ph 2 |  |  |  | 2011-11-17 | 2016-01-29 | 2021-07-30 | 99%
2021-04-30 | 2014 | Army Active | Major Military Construction |  |  | 59779 | Pier |  | 2125000 | 92764 | 2016-08-17 | 2020-06-10 | 2021-10-24 | 82%
2017-07-31 | 2011 | Army Active | Major Military Construction |  | Germany | 60555 | Information Processing Center |  |  |  | 2012-06-18 | 2014-06-01 | 2017-01-31 | 99% | 2016-11-08
2021-04-30 | 2018 | Army Active | Major Military Construction | Washington | United States | 61147 | Confinement Facility |  |  |  | 2019-12-06 | 2022-08-22 | 2022-10-23 | 49%
2021-04-30 | 2019 | Army Active | Major Military Construction |  | Honduras | 61388 | Barracks |  |  |  | 2019-07-30 | 2022-07-14 | 2022-10-13 | 64%
2017-07-31 | 2012 | Army Active | Major Military Construction |  | Germany | 61842 | Access Control Point |  |  |  | 2015-05-11 | 2016-12-01 | 2017-05-31 | 95% | 2017-06-19
2020-08-31 | 2014 | Army Active | Major Military Construction | Maryland | United States | 62204 | Hazardous Material Storage Building |  | 100000 | 92764 | 2016-02-23 | 2017-08-16 | 2020-06-30 | 96% | 2020-07-22
2021-04-30 | 2017 | Army Active | Major Military Construction |  | Germany | 62380 | Training Support Center |  |  |  | 2018-02-22 | 2022-05-11 | 2022-05-28 | 39%
2017-07-31 | 2012 | Army Active | Major Military Construction | California | United States | 62657 | Water Treatment and Distro System |  |  |  | 2012-10-19 | 2015-10-19 | 2016-10-25 | 98% | 2017-04-28
2020-08-31 | 2013 | Army Active | Major Military Construction |  | Japan | 62663 | Vehicle Maintenance Shop |  |  |  | 2017-09-18 | 2019-04-01 | 2020-08-31 | 99% | 2019-10-11
2021-04-30 | 2013 | Army Active | Major Military Construction |  | Japan | 62783 | Satellite Communications Facility |  |  |  | 2014-11-21 | 2021-06-09 | 2022-08-11 | 78%
2021-04-30 | 2020 | Army Active | Major Military Construction | Michigan | United States | 62856 | Substation |  |  |  | 2020-08-20 | 2022-08-20 | 2022-08-20 | 1%
2021-04-30 | 2019 | Army Active | Major Military Construction |  | Kuwait | 62866 | Vehicle Maintenance Shop |  | 14950000 | 86409, 88380 | 2019-09-30 | 2021-05-02 | 2021-05-02 | 26%
2020-08-31 | 2011 | Army Active | Major Military Construction | California | United States | 63015 | Satellite Communications Facility |  |  |  | 2011-09-21 | 2016-06-30 | 2020-07-23 | 95% | 2019-12-20
2021-04-30 | 2019 | Army Active | Major Military Construction | New Jersey | United States | 63054 | Munitions Disassembly Complex |  | 4300000 | 64026 | 2019-11-04 | 2021-11-03 | 2022-11-30 | 50%
2019-08-31 | 2010 | Army Active | Major Military Construction | Virginia | United States | 63571 | Road and Access Control Point |  |  |  | 2016-04-28 | 2017-08-01 | 2019-06-20 | 99% | 2019-06-20
2018-08-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 64014 | Battalion Complex |  | 600000 | 78196 | 2012-07-25 | 2015-04-08 | 2018-05-23 | 99% | 2018-05-23
2017-07-31 | 2012 | Army Active | Major Military Construction | Missouri | United States | 64365 | Vehicle Maintenance Facility |  |  |  | 2012-09-18 | 2014-08-25 | 2017-02-13 | 99% | 2016-05-12
2021-04-30 | 2013 | Army Active | Major Military Construction | Washington | United States | 64456 | Battalion Complex |  |  |  | 2013-06-26 | 2018-07-05 | 2021-02-26 | 99% | 2019-08-05
2017-04-30 | 2012 | Army Active | Major Military Construction | Oklahoma | United States | 64753 | Vehicle Maintenance Facility |  |  |  | 2012-07-19 | 2014-04-11 | 2016-04-14 | 98% | 2017-04-14
2017-07-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 65679 | Vehicle Maintenance Shop |  | 13450000 | 62663, 68826 | 2013-06-27 | 2016-08-06 | 2016-10-13 | 99% | 2016-10-13
2021-04-30 | 2018 | Army Active | Major Military Construction | Florida | United States | 65699 | Multipurpose Range Complex |  |  |  | 2019-03-08 | 2020-10-28 | 2020-10-13 | 99% | 2020-10-13
2019-08-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 65755 | Brigade Complex |  |  |  | 2012-12-12 | 2018-01-06 | 2017-12-21 | 99% | 2019-01-22
2017-07-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 66023 | Automated Infantry Platoon Battle Course |  |  |  | 2014-07-08 | 2016-09-09 | 2017-02-17 | 99% | 2017-05-10
2017-07-31 | 2013 | Army Active | Major Military Construction | Missouri | United States | 66099 | Battalion Complex Facilities |  |  |  | 2013-07-01 | 2016-05-05 | 2017-02-23 | 98% | 2016-11-04
2018-08-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 66206 | Infrastructure, Ph 1 |  |  |  | 2012-09-17 | 2017-06-10 | 2017-11-14 | 99% | 2017-11-20
2020-08-31 | 2016 | Army Active | Major Military Construction | Oklahoma | United States | 66575 | Training Support Facility |  |  |  | 2017-09-05 | 2018-11-29 | 2020-05-21 | 88%
2017-07-31 | 2011 | Army Active | Major Military Construction |  | Germany | 66595 | Barracks Complex |  |  |  | 2015-03-23 | 2017-09-28 | 2017-09-28 | 96%
2018-08-31 | 2009 | Army Active | Major Military Construction | New Jersey | United States | 66725 | Ballistic Evaluation Facility Ph 1 |  |  |  | 2012-12-04 | 2014-06-04 | 2018-02-13 | 93% | 2017-07-14
2018-08-31 | 2010 | Army Active | Major Military Construction | New Jersey | United States | 66726 | Ballistic Evaluation Facility, Ph 2 |  |  |  | 2012-12-04 | 2014-06-04 | 2018-02-13 | 98% | 2017-07-14
2017-04-30 | 2011 | Army Active | Major Military Construction |  | Germany | 66834 | Vehicle Maintenance Shop |  |  |  | 2011-12-12 | 2013-12-18 | 2016-01-15 | 97% | 2016-11-18
2019-08-31 | 2017 | Army Active | Major Military Construction | Georgia | United States | 67029 | Automated Qualification/Training Range |  |  |  | 2017-09-21 | 2019-03-15 | 2019-06-29 | 85% | 2019-06-29
2017-05-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 67116 | Aviation Battalion Complex |  |  |  | 2014-04-23 | 2016-09-06 | 2016-09-26 | 99% | 2016-10-03
2020-08-31 | 2014 | Army Active | Major Military Construction | Hawaii | United States | 67157 | Command and Control Facility - Admin |  |  |  | 2015-09-25 | 2017-12-13 | 2019-10-28 | 94% | 2019-10-28
2019-08-31 | 2012 | Army Active | Major Military Construction | Maryland | United States | 68050 | Command and Control Facility |  |  |  | 2016-02-24 | 2018-06-13 | 2019-05-02 | 98% | 2019-05-02
2016-11-30 | 2011 | Army Active | Major Military Construction |  | Germany | 68074 | Construct New ACP |  |  |  | 2014-03-05 | 2014-12-12 | 2015-01-09 | 99%
2021-04-30 | 2013 | Army Active | Major Military Construction | Texas | United States | 68530 | Barracks |  |  |  | 2015-11-18 | 2018-12-17 | 2021-07-08 | 29%
2016-11-30 | 2011 | Army Active | Major Military Construction |  | Germany | 68606 | Barracks |  |  |  | 2012-10-12 | 2014-05-25 | 2014-06-16 | 98%
2020-08-31 | 2015 | Army Active | Major Military Construction | Texas | United States | 68826 | Simulations Center |  | 11200000 | 75661, 77779, 85794 | 2017-08-01 | 2019-09-30 | 2020-02-25 | 99% | 2020-02-25
2020-08-31 | 2011 | Army Active | Major Military Construction |  | Germany | 68866 | Sensitive Compartmented Information Fac |  |  |  | 2013-02-13 | 2015-09-19 | 2019-11-30 | 98% | 2019-11-08
2017-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 68993 | Electronics Maintenance Facility |  |  |  | 2012-08-08 | 2013-12-16 | 2016-11-12 | 99% | 2014-06-27
2017-03-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 69286 | Infrastructure |  |  |  | 2012-08-20 | 2013-09-13 | 2016-11-12 | 72% | 2012-10-22
2021-04-30 | 2020 | Army Active | Major Military Construction | Kentucky | United States | 69347 | General Purpose Maintenance Shop |  | 3092000 | 77538 | 2020-06-11 | 2022-07-11 | 2022-10-08 | 24%
2019-08-31 | 2012 | Army Active | Major Military Construction | Hawaii | United States | 69489 | Combat Aviation Brigade Complex, Ph 1 |  |  |  | 2012-07-30 | 2015-05-27 | 2018-10-30 | 95% | 2019-02-25
2021-04-30 | 2015 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility Complex |  |  |  | 2017-11-02 | 2021-11-07 | 2022-03-11 | 88%
2021-04-30 | 2018 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 3 | 58857 |  |  | 2017-11-02 | 2021-11-07 | 2022-03-11 | 88%
2021-04-30 | 2017 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 2 | 76593 |  |  | 2017-11-02 | 2021-11-07 | 2022-03-11 | 88%
2021-04-30 | 2019 | Army Active | Major Military Construction | Hawaii | United States | 70668 | Command and Control Facility, Incr 4 | 76595 |  |  | 2017-11-02 | 2021-11-07 | 2022-03-11 | 88%
2021-04-30 | 2018 | Army Active | Major Military Construction | Georgia | United States | 70677 | Access Control Point |  |  |  | 2018-12-17 | 2020-12-16 | 2021-08-09 | 90%
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 71035 | TRAINING AIDS CENTER |  |  |  | 2017-12-14 | 2019-11-12 | 2019-11-12 | 0%
2021-04-30 | 2016 | Army Active | Major Military Construction | California | United States | 71057 | Pier |  |  |  | 2018-08-16 | 2020-08-01 | 2021-04-30 | 91% | 2021-04-30
2021-04-30 | 2012 | Army Active | Major Military Construction | Virginia | United States | 71149 | Road and Infrastucture Improvements |  |  |  | 2016-08-17 | 2018-08-17 | 2020-12-25 | 100% | 2020-07-15
2017-05-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 71221 | Fire Station |  |  |  | 2014-08-27 | 2016-02-18 | 2016-09-28 | 99% | 2016-10-24
2019-08-31 | 2011 | Army Active | Military Family Housing |  | Germany | 71422 | Family Housing Replacement Construction |  |  |  | 2015-04-07 | 2018-07-27 | 2019-04-05 | 95% | 2019-04-05
2016-11-30 | 2011 | Army Active | Major Military Construction | New York | United States | 71472 | Brigade Complex Ph 1 |  | 9250000 | 62783 | 2011-08-05 | 2013-03-07 | 2014-07-23 | 99% | 2016-10-31
2017-07-31 | 2010 | Army Active | Major Military Construction |  | Kuwait | 71485 | APS Warehouses |  | 11339000 | 58925, 62783 | 2013-10-25 | 2015-10-30 | 2016-10-03 | 99% | 2016-10-03
2017-07-31 | 2014 | Army Active | Major Military Construction | Missouri | United States | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  |  |  | 2014-08-05 | 2016-08-04 | 2017-02-28 | 99% | 2017-03-08
2017-07-31 | 2013 | Army Active | Major Military Construction | New Jersey | United States | 71675 | Flight Equipment Complex |  |  |  | 2014-01-15 | 2016-01-15 | 2017-08-11 | 98%
2021-04-30 | 2020 | Army Active | Major Military Construction | Kentucky | United States | 71725 | Automated Infantry Platoon Battle Course |  |  |  | 2020-05-12 | 2021-05-12 | 2021-07-09 | 42%
2019-08-31 | 2017 | Army Active | Major Military Construction | Texas | United States | 71777 | Automated Infantry Platoon Battle Course |  | 5000000 | 77779 | 2017-11-28 | 2019-05-22 | 2019-05-29 | 99% | 2019-06-28
2020-08-31 | 2017 | Army Active | Major Military Construction | Colorado | United States | 72176 | Automated Infantry Platoon Battle Course |  |  |  | 2018-08-08 | 2020-01-30 | 2020-03-23 | 99% | 2020-08-20
2020-08-31 | 2018 | Army Active | Major Military Construction | Texas | United States | 72843 | Battalion Headquarters Complex |  |  |  | 2018-11-08 | 2020-01-02 | 2020-07-24 | 99% | 2020-07-24
2018-08-31 | 2011 | Army Active | Major Military Construction | Washington | United States | 72854 | Regional Logistic Support Complex |  |  |  | 2011-10-12 | 2015-10-24 | 2018-08-23 | 99% | 2018-08-23
2018-08-31 | 2015 | Army Active | Major Military Construction | Virginia | United States | 73272 | Tactical Vehicle Hardstand |  |  |  | 2015-10-21 | 2016-10-20 | 2017-12-17 | 99% | 2017-12-18
2021-04-30 | 2018 | Army Active | Major Military Construction | Colorado | United States | 73375 | Ammunition Supply Point |  |  |  | 2018-11-02 | 2020-06-24 | 2020-12-01 | 98% | 2020-09-16
2017-07-31 | 2014 | Army Active | Major Military Construction | Maryland | United States | 73384 | Entry Control Point |  |  |  | 2016-03-31 | 2017-03-31 | 2017-03-31 | 99% | 2017-07-01
2021-04-30 | 2020 | Army Active | Major Military Construction | Virginia | United States | 73391 | Adv Individual Training Barracks Cplx, Ph4 |  |  |  | 2020-11-03 | 2022-11-03 | 2022-11-03 | 7%
2018-04-30 | 2013 | Army Active | Unspecified Minor Military Construction | California | United States | 73738 | FIRE STATION |  |  |  | 2017-12-14 | 2018-11-28 | 2018-11-28 | 0%
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 74001 | PHYSICAL FITNESS FACILITY |  |  |  | 2017-12-14 | 2019-06-07 | 2019-06-07 | 0%
2021-04-30 | 2019 | Army Active | Military Family Housing | Wisconsin | United States | 74618 | Family Housing New Construction |  |  |  | 2019-06-10 | 2020-06-09 | 2020-12-01 | 97% | 2020-12-01
2017-07-31 | 2014 | Army Active | Major Military Construction | Texas | United States | 74638 | Control Tower |  |  |  | 2015-04-28 | 2017-01-02 | 2017-07-21 | 99% | 2017-04-20
2018-04-30 | 2017 | Army Active | Unspecified Minor Military Construction | California | United States | 74732 | Family Life Center (Chapel annex) |  |  |  | 2018-01-09 | 2019-06-13 | 2019-06-13 | 0%
2017-07-31 | 2014 | Army Active | Military Family Housing | Wisconsin | United States | 74861 | Family Housing New Construction |  |  |  | 2014-08-20 | 2016-08-09 | 2017-08-19 | 95% | 2017-07-14
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 74989 | Supply Support Activity |  |  |  | 2019-04-16 | 2020-10-07 | 2021-06-20 | 96%
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 75157 | Supply Support Activity |  |  |  | 2020-12-02 | 2022-02-25 | 2022-03-29 | 13%
2018-08-31 | 2013 | Army Active | Major Military Construction | Washington | United States | 75165 | Waste Water Treatment Plant |  |  |  | 2014-03-03 | 2016-03-02 | 2017-11-30 | 99% | 2017-10-04
2019-08-31 | 2015 | Army Active | Unspecified Minor Military Construction | Texas | United States | 75307 | Lab and Test Building |  |  |  | 2017-11-09 | 2018-11-04 | 2019-05-31 | 97% | 2019-05-31
2018-08-31 | 2015 | Army Active | Military Family Housing | Illinois | United States | 75536 | Family Housing New Construction |  |  |  | 2016-09-13 | 2018-03-07 | 2018-09-03 | 88%
2019-08-31 | 2016 | Army Active | Military Family Housing | Illinois | United States | 75538 | Family Housing Replacement Construction |  |  |  | 2016-10-17 | 2018-04-10 | 2018-10-19 | 99% | 2018-10-19
2021-04-30 | 2017 | Army Active | Major Military Construction | Missouri | United States | 75660 | Fire Station |  |  |  | 2019-02-05 | 2020-02-05 | 2020-11-20 | 97% | 2020-11-20
2021-04-30 | 2016 | Army Active | Major Military Construction | Oklahoma | United States | 75661 | Reception Barracks Complex Ph2 |  |  |  | 2019-02-05 | 2020-12-26 | 2021-05-03 | 89%
2021-04-30 | 2018 | Army Active | Military Family Housing | Massachusetts | United States | 75718 | Family Housing Replacement Construction |  |  |  | 2019-06-03 | 2021-06-02 | 2021-12-26 | 79%
2019-08-31 | 2017 | Army Active | Major Military Construction | Colorado | United States | 75893 | Unmanned Aerial Vehicle Hangar |  |  |  | 2017-10-25 | 2018-11-29 | 2018-12-10 | 99% | 2019-06-08
2020-09-30 | 2016 | Army Active | Unspecified Minor Military Construction | New York | United States | 75906 | New Warehouse |  |  |  | 2018-11-30 | 2019-12-16 | 2020-09-16 | 90%
2018-08-31 | 2014 | Army Active | Major Military Construction | Kansas | United States | 76024 | Simulations Center |  |  |  | 2014-09-02 | 2018-09-24 | 2018-09-24 | 98%
2018-08-31 | 2013 | Army Active | Major Military Construction | California | United States | 76086 | Lightning Protection System |  |  |  | 2014-09-16 | 2018-05-30 | 2018-09-14 | 97%
2019-08-31 | 2015 | Army Active | Major Military Construction | California | United States | 76087 | General Purpose Maintenance Shop |  |  |  | 2015-11-30 | 2017-03-31 | 2019-01-31 | 92% | 2019-03-08
2021-04-30 | 2015 | Army Active | Major Military Construction | California | United States | 76093 | Access Control Point |  |  |  | 2019-07-08 | 2020-06-02 | 2021-06-11 | 73% | 2021-04-30
2017-07-31 | 2013 | Army Active | Major Military Construction |  | Korea, South | 76196 | Battalion Headquarters Complex |  | 9200000 | 62663 | 2013-05-14 | 2015-06-09 | 2017-04-28 | 95% | 2017-04-17
2017-07-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76586 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2017-01-13 | 97% | 2017-04-03
2017-07-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76587 | Barracks |  |  |  | 2013-07-23 | 2015-09-01 | 2017-01-13 | 95% | 2017-04-03
2016-10-31 | 2014 | Army Active | Major Military Construction | Alaska | United States | 76601 | Aviation Storage Hangar |  |  |  | 2014-04-17 | 2016-03-21 | 2016-09-29 | 91%
2021-04-30 | 2020 | Army Active | Major Military Construction | Alabama | United States | 76673 | Aircraft and Flight Equipment Building |  |  |  | 2021-01-04 | 2022-12-25 | 2022-12-25 | 7%
2017-07-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76767 | Aviation Unit Complex, Ph 1A |  |  |  | 2012-07-09 | 2017-01-18 | 2017-01-23 | 99% | 2017-01-23
2017-07-31 | 2012 | Army Active | Major Military Construction | Washington | United States | 76768 | Aviation Complex, Ph 1B |  | 25700000 | 49472, 68050, 71149 | 2012-11-29 | 2017-05-06 | 2017-06-22 | 99%
2020-08-31 | 2014 | Army Active | Major Military Construction | Washington | United States | 76776 | Airfield Operations Complex |  |  |  | 2015-05-18 | 2018-04-21 | 2019-10-29 | 99% | 2019-10-29
2021-04-30 | 2014 | Army Active | Major Military Construction | Washington | United States | 76777 | Aircraft Maintenance Hangar |  | 611000 | 79933 | 2014-09-23 | 2018-10-26 | 2020-11-13 | 100% | 2019-01-01
2018-08-31 | 2013 | Army Active | Major Military Construction | Hawaii | United States | 76903 | Combat Aviation Brigade Barracks |  | 5000000 | 81987 | 2014-06-26 | 2017-01-13 | 2017-12-12 | 99% | 2017-12-22
2021-04-30 | 2018 | Army Active | Major Military Construction | Arizona | United States | 77102 | General Instruction Building |  |  |  | 2018-12-13 | 2020-06-05 | 2021-06-22 | 91%
2017-07-31 | 2012 | Army Active | Major Military Construction | Texas | United States | 77187 | Vehicle Maintenance Facility |  |  |  | 2012-06-22 | 2016-12-07 | 2017-02-26 | 98% | 2017-02-23
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77262 | Headquarters Building |  |  |  | 2014-08-21 | 2016-03-31 | 2017-07-26 | 94%
2021-04-30 | 2019 | Army Active | Major Military Construction | Colorado | United States | 77301 | Vehicle Maintenance Shop |  |  |  | 2019-09-03 | 2021-05-04 | 2021-11-03 | 81%
2021-04-30 | 2020 | Army Active | Major Military Construction | Colorado | United States | 77303 | Company Operations Facility |  |  |  | 2020-09-10 | 2022-06-12 | 2022-07-19 | 21%
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77304 | Aircraft Maintenance Hangar |  |  |  | 2014-08-18 | 2016-08-22 | 2017-05-31 | 97% | 2017-05-31
2021-04-30 | 2015 | Army Active | Major Military Construction | Colorado | United States | 77305 | Aircraft Maintenance Hangar |  | 1000000 | 77779 | 2015-06-16 | 2019-06-02 | 2021-03-25 | 98% | 2020-11-06
2018-08-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77405 | Aircraft Maintenance Hangar |  |  |  | 2014-07-22 | 2016-08-22 | 2017-11-28 | 97% | 2018-08-06
2017-07-31 | 2013 | Army Active | Major Military Construction | Georgia | United States | 77419 | Ground Source Heat Transfer System |  |  |  | 2015-01-06 | 2016-12-26 | 2017-07-21 | 97%
2021-04-30 | 2017 | Army Active | Major Military Construction | Utah | United States | 77538 | Live Fire Exercise Shoothouse |  |  |  | 2018-08-31 | 2020-02-22 | 2022-01-23 | 62%
2021-04-30 | 2020 | Army Active | Major Military Construction | Washington | United States | 77728 | Information Systems Facility |  |  |  | 2020-07-14 | 2022-12-31 | 2022-12-31 | 15%
2021-04-30 | 2018 | Army Active | Major Military Construction | Virginia | United States | 77779 | Aircraft Maintenance Instructional Bldg |  |  |  | 2019-06-26 | 2021-02-15 | 2021-06-11 | 70%
2021-04-30 | 2015 | Army Active | Major Military Construction |  | Japan | 77831 | Missile Magazine |  |  |  | 2019-12-02 | 2021-05-25 | 2021-05-25 | 89%
2017-04-30 | 2014 | Army Active | Major Military Construction | Colorado | United States | 77885 | Runway |  |  |  | 2014-07-01 | 2015-07-01 | 2016-07-29 | 99% | 2017-04-24
2017-07-31 | 2013 | Army Active | Major Military Construction | District Of Columbia | United States | 78054 | Vehicle Storage Building, Installation |  |  |  | 2015-04-03 | 2016-09-24 | 2017-02-21 | 85% | 2017-03-31
2021-04-30 | 2014 | Army Active | Major Military Construction | Washington | United States | 78196 | Aviation Battalion Complex |  | 2726000 | 79933, 92764 | 2016-01-13 | 2018-04-05 | 2020-11-13 | 100% | 2019-01-01
2018-08-31 | 2016 | Army Active | Military Family Housing Improvement |  | Germany | 78366 | Family Housing Improvements |  |  |  | 2016-10-25 | 2017-12-09 | 2018-04-20 | 98% | 2018-04-27
2017-07-31 | 2012 | Army Active | Military Family Housing Improvement |  | Germany | 78475 | Family Housing Improvements |  |  |  | 2015-01-16 | 2016-09-27 | 2017-04-21 | 99% | 2017-06-20
2017-05-31 | 2012 | Army Active | Military Family Housing |  | Germany | 78505 | Family Housing New Construction |  |  |  | 2013-08-07 | 2015-09-14 | 2016-02-17 | 93%
2021-04-30 | 2014 | Army Active | Military Family Housing |  | Germany | 78712 | Family Housing New Construction |  |  |  | 2017-08-11 | 2019-11-25 | 2021-05-31 | 98%
2021-04-30 | 2019 | Army Active | Major Military Construction | New York | United States | 78804 | Engineering Center |  |  |  | 2021-01-04 | 2025-01-04 | 2025-01-04 | 0%
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 79618 | Simulator Building |  |  |  | 2014-08-20 | 2016-02-11 | 2017-03-27 | 97% | 2017-04-13
2017-07-31 | 2012 | Army Active | Major Military Construction |  | Unspecified World Wide | 79749 | Forward Operating Site |  |  |  | 2012-07-25 | 2014-11-30 | 2017-07-15 | 91%
2017-07-31 | 2013 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks |  |  |  | 2013-08-26 | 2016-08-30 | 2017-02-07 | 98% | 2017-04-24
2017-07-31 | 2014 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 2 | 81186 |  |  | 2013-08-26 | 2016-08-30 | 2017-02-07 | 98% | 2017-04-24
2017-07-31 | 2015 | Army Active | Major Military Construction | New York | United States | 79933 | Cadet Barracks, Incr 3 | 81187 |  |  | 2013-08-26 | 2016-08-30 | 2017-02-07 | 98% | 2017-04-24
2020-08-31 | 2016 | Army Active | Unspecified Minor Military Construction | North Carolina | United States | 80037 | Aberdeen Training Fac Wastewater Treatment |  |  |  | 2018-10-16 | 2019-07-13 | 2019-11-21 | 90% | 2019-12-18
2017-07-31 | 2013 | Army Active | Major Military Construction | North Carolina | United States | 80112 | Unmanned Aerial Vehicle Complex |  | 11900000 | 77305 | 2015-05-26 | 2016-07-19 | 2016-11-01 | 99% | 2016-11-01
2018-08-31 | 2012 | Army Active | Unspecified Minor Military Construction | Maryland | United States | 80231 | Replace Oil Water Separators |  |  |  | 2014-11-03 | 2015-11-03 | 2018-02-08 | 99% | 2018-06-08
2018-08-31 | 2013 | Army Active | Major Military Construction | New York | United States | 80246 | Aircraft Maintenance Hangar |  | 2000000 | 81987 | 2013-06-27 | 2015-12-02 | 2018-02-23 | 99% | 2018-03-15
2017-07-31 | 2013 | Army Active | Unspecified Minor Military Construction | Virginia | United States | 80317 | WATER DISTRIBUTION LINES, POTABLE |  |  |  | 2014-01-13 | 2014-09-10 | 2016-11-30 | 97% | 2017-03-23
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 80353 | Waste/Central Hazardous Waste Facility |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 0%
2017-07-31 | 2014 | Army Active | Major Military Construction | Colorado | United States | 80433 | Central Energy Plant |  |  |  | 2015-10-27 | 2016-10-26 | 2017-03-22 | 98% | 2017-03-27
2018-09-30 | 2015 | Army Active | Unspecified Minor Military Construction | Mississippi | United States | 80666 | Precision Machine Shop |  |  |  | 2016-10-26 | 2018-04-19 | 2018-09-26 | 91%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Arizona | United States | 80748 | Raw Sewage Lagoon and Oxidation Pond |  |  |  | 2019-04-16 | 2021-04-15 | 2021-04-15 | 78%
2019-08-31 | 2016 | Army Active | Major Military Construction | Virginia | United States | 80851 | Training Support Facility |  | 500000 | 77779 | 2017-06-22 | 2018-12-14 | 2019-07-31 | 90% | 2019-07-31
2020-08-31 | 2018 | Army Active | Major Military Construction | Georgia | United States | 80855 | Training Support Facility |  | 7234000 | 77538, 77831 | 2018-08-14 | 2020-02-05 | 2020-07-30 | 98% | 2020-08-28
2017-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | Hawaii | United States | 80992 | Upgrade Power Distribution |  |  |  | 2015-04-29 | 2016-10-20 | 2017-01-25 | 99% | 2017-01-25
2019-08-31 | 2015 | Army Active | Military Family Housing |  | Korea, South | 81230 | Family Housing New Construction |  |  |  | 2015-08-19 | 2018-04-28 | 2019-01-31 | 99% | 2019-03-14
2021-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | Louisiana | United States | 81234 | Fire Station Addition |  |  |  | 2018-09-27 | 2019-09-27 | 2021-11-19 | 61%
2021-04-30 | 2015 | Army Active | Unspecified Minor Military Construction |  | Germany | 81236 | Fire Station Addition |  |  |  | 2020-07-29 | 2021-05-31 | 2021-08-05 | 42%
2018-11-30 | 2015 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81242 | General Purpose Maintenance Shop |  |  |  | 2015-10-28 | 2016-10-27 | 2018-09-07 | 87%
2020-11-30 | 2018 | Army Active | Major Military Construction | Colorado | United States | 81283 | Battlefield Weather Facility |  |  |  | 2018-12-13 | 2020-04-06 | 2020-12-01 | 98% | 2020-09-14
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | California | United States | 81316 | Library Main |  |  |  | 2020-08-18 | 2021-08-18 | 2021-08-18 | 29%
2019-09-30 | 2017 | Army Active | Major Military Construction | Alaska | United States | 81347 | Unmanned Aerial Vehicle Hangar |  | 6000000 | 71057 | 2017-04-19 | 2018-11-15 | 2019-10-01 | 96%
2018-08-31 | 2015 | Army Active | Major Military Construction | New York | United States | 81349 | Unmanned Aerial Vehicle Hangar |  | 4275000 | 85811 | 2015-06-22 | 2016-12-18 | 2017-12-31 | 99% | 2018-07-31
2017-07-31 | 2015 | Army Active | Major Military Construction | Colorado | United States | 81357 | Unmanned Aerial Vehicle Hangar |  |  |  | 2014-07-01 | 2017-01-18 | 2017-06-16 | 94% | 2017-06-29
2017-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 81424 | Tracking Equipment Support Fac |  |  |  | 2015-11-10 | 2017-02-02 | 2017-03-24 | 99% | 2017-04-23
2020-08-31 | 2016 | Army Active | Military Family Housing |  | Korea, South | 81427 | Family Housing New Construction |  | 1220000 | 75718 | 2016-09-29 | 2019-02-24 | 2020-02-25 | 99% | 2019-08-27
2021-04-30 | 2017 | Army Active | Military Family Housing |  | Korea, South | 81428 | Family Housing New Construction |  |  |  | 2017-09-08 | 2021-07-14 | 2021-09-16 | 83%
2021-04-30 | 2019 | Army Active | Military Family Housing |  | Korea, South | 81429 | Family Housing Replacement Construction |  |  |  | 2019-10-31 | 2022-09-05 | 2022-09-24 | 14%
2017-07-31 | 2013 | Army Active | Unspecified Minor Military Construction |  | Marshall Islands | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  |  |  | 2014-10-28 | 2015-10-23 | 2016-12-01 | 62% | 2017-01-01
2021-04-30 | 2014 | Army Active | Major Military Construction |  | Japan | 81987 | Company Operations Complex |  |  |  | 2017-11-02 | 2019-11-22 | 2021-03-19 | 95% | 2021-04-05
2019-08-31 | 2016 | Army Active | Unspecified Minor Military Construction | New York | United States | 82094 | CID Field Ops Facility |  |  |  | 2017-10-18 | 2019-04-11 | 2019-06-10 | 98% | 2019-06-11
2021-04-30 | 2019 | Army Active | Major Military Construction | North Carolina | United States | 82254 | Dining Facility |  |  |  | 2020-01-07 | 2021-06-30 | 2021-07-19 | 57%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Washington | United States | 82337 | REPAIR BAYS, NON-DOL/DPW |  |  |  | 2020-02-12 | 2021-04-07 | 2021-04-26 | 78% | 2021-04-26
2017-07-31 | 2014 | Army Active | Unspecified Minor Military Construction | Oklahoma | United States | 82394 | Decontamination Facility |  |  |  | 2016-02-18 | 2017-02-12 | 2017-07-12 | 95%
2017-01-31 | 2014 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 85260 | Secure Operations Center |  |  |  | 2014-11-05 | 2015-11-05 | 2016-01-13 | 99% | 2017-01-20
2018-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | California | United States | 85683 | UPH Laundry Building, Detached |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 0%
2019-08-31 | 2016 | Army Active | Major Military Construction | Colorado | United States | 85710 | Rotary Wing Taxiway |  |  |  | 2017-02-28 | 2018-08-22 | 2018-11-07 | 99% | 2019-04-11
2021-04-30 | 2015 | Army Active | Major Military Construction |  | Romania | 85711 | ERI: Multi Modal Improvements |  |  |  | 2017-12-15 | 2020-12-09 | 2021-12-23 | 69%
2021-04-30 | 2017 | Army Active | Major Military Construction | Georgia | United States | 85794 | Company Operations Facility |  |  |  | 2019-02-20 | 2020-06-14 | 2021-05-31 | 96%
2018-04-30 | 2016 | Army Active | Unspecified Minor Military Construction | California | United States | 85808 | Military Equipment Parking |  |  |  | 2017-05-08 | 2018-05-08 | 2018-05-08 | 66%
2019-08-31 | 2016 | Army Active | Major Military Construction | Georgia | United States | 85811 | Command and Control Facility |  |  |  | 2016-10-31 | 2018-07-23 | 2019-05-14 | 96% | 2018-12-10
2019-08-31 | 2014 | Army Active | Unspecified Minor Military Construction |  | Germany | 85817 | CANTONMENT AREA ROADS, PAVED |  |  |  | 2016-04-07 | 2016-08-25 | 2016-11-15 | 83% | 2018-12-06
2020-08-31 | 2017 | Army Active | Major Military Construction | Georgia | United States | 85818 | Cyber Protection Team Ops Facility |  |  |  | 2016-10-31 | 2020-02-10 | 2020-01-22 | 97% | 2020-07-28
2021-04-30 | 2015 | Army Active | Unspecified Minor Military Construction |  | Germany | 86094 | Child Development Center Addition |  |  |  | 2020-05-18 | 2021-09-05 | 2021-09-10 | 16%
2021-04-30 | 2015 | Army Active | Major Military Construction |  | Romania | 86404 | ERI: Hazardous Cargo Ramp |  |  |  | 2017-10-24 | 2019-12-13 | 2021-12-02 | 43%
2018-08-31 | 2015 | Army Active | Major Military Construction |  | Romania | 86405 | ERI: Fuel Storage Capacity |  |  |  | 2017-09-29 | 2020-11-03 | 2020-11-03 | 1%
2020-08-31 | 2016 | Army Active | Major Military Construction | Maryland | United States | 86408 | Access Control Point |  |  |  | 2016-11-17 | 2018-12-07 | 2020-01-09 | 99% | 2020-05-26
2020-08-31 | 2015 | Army Active | Unspecified Minor Military Construction | New York | United States | 86414 | Electrical Switching Station |  |  |  | 2019-01-11 | 2020-03-06 | 2020-12-01 | 91%
2020-08-31 | 2017 | Army Active | Unspecified Minor Military Construction | Arizona | United States | 86442 | RDT&E Building, Compact Repair Shop |  |  |  | 2018-12-14 | 2020-06-06 | 2020-06-11 | 98% | 2020-08-06
2021-04-30 | 2018 | Army Active | Major Military Construction | Georgia | United States | 86479 | Automation-Aided Instructional Building |  | 4550000 | 61147, 77538 | 2018-11-27 | 2020-03-21 | 2020-10-04 | 97% | 2020-07-29
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Washington | United States | 86518 | Aircraft Engine Test Building |  |  |  | 2019-08-16 | 2020-08-15 | 2021-06-02 | 77%
2021-04-30 | 2017 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction |  |  |  | 2017-10-31 | 2020-11-12 | 2021-07-24 | 53%
2021-04-30 | 2019 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 3 | 86877 |  |  | 2019-02-26 | 2022-07-25 | 2023-01-13 | 53%
2021-04-30 | 2018 | Army Active | Military Family Housing |  | Korea, South | 86689 | Family Housing New Construction Incr 2 | 91380 |  |  | 2017-10-31 | 2020-11-12 | 2021-07-24 | 53%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 86711 | Vehicle Paint and Prep Shop, DOL/DPW/IMMA/ |  |  |  | 2019-03-20 | 2020-07-21 | 2021-03-16 | 92%
2019-08-31 | 2017 | Army Active | Major Military Construction |  | Germany | 86745 | Controlled Humidity Warehouse |  |  |  | 2017-10-13 | 2018-01-11 | 2019-09-28 | 72%
2019-08-31 | 2015 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 86787 | CIDC Field Operations Building |  |  |  | 2017-07-21 | 2018-07-21 | 2019-03-15 | 90% | 2019-05-01
2021-04-30 | 2018 | Army Active | Major Military Construction | Alabama | United States | 86816 | Training Support Facility |  |  |  | 2019-10-21 | 2021-10-10 | 2022-03-08 | 25%
2021-04-30 | 2016 | Army Active | Major Military Construction |  | Germany | 86824 | Vehicle Maintenance Shop |  | 4000000 | 55199 | 2019-06-17 | 2022-05-01 | 2023-08-24 | 6%
2021-04-30 | 2018 | Army Active | Major Military Construction |  | Turkey | 86832 | Forward Operating Site |  |  |  | 2018-10-02 | 2022-03-25 | 2023-07-04 | 18%
2018-09-30 | 2015 | Army Active | Unspecified Minor Military Construction |  | Honduras | 86859 | Continuing Education Facility |  |  |  | 2016-11-22 | 2018-04-26 | 2018-10-15 | 94% | 2018-09-21
2021-04-30 | 2016 | Army Active | Unspecified Minor Military Construction |  |  | 86914 | Storage Fuel Tank Repair |  |  |  | 2017-10-11 | 2018-12-12 | 2021-06-11 | 83%
2021-04-30 | 2018 | Army Active | Major Military Construction |  | Germany | 86991 | Administrative Building |  |  |  | 2020-04-03 | 2022-06-22 | 2023-03-19 | 23%
2021-04-30 | 2018 | Army Active | Military Family Housing | Georgia | United States | 87205 | Family Housing New Construction |  |  |  | 2021-02-26 | 2022-08-20 | 2022-08-20 | 1%
2019-08-31 | 2017 | Army Active | Unspecified Minor Military Construction |  | Honduras | 87309 | Chapel |  |  |  | 2017-12-06 | 2019-08-07 | 2019-10-06 | 98%
2018-08-31 | 2016 | Army Active | Unspecified Minor Military Construction | Washington | United States | 87419 | MEDEVAC Aircraft Maintenance Hangar |  |  |  | 2018-01-30 | 2018-09-27 | 2018-09-27 | 77%
2019-08-31 | 2016 | Army Active | Unspecified Minor Military Construction | New York | United States | 87892 | Fire Suppression & Mass Notification Sys |  |  |  | 2017-10-23 | 2019-04-26 | 2019-04-29 | 96% | 2019-04-29
2021-04-30 | 2020 | Army Active | Major Military Construction | New York | United States | 87933 | Unmanned Aerial Vehicle Hangar |  |  |  | 2020-10-21 | 2022-10-11 | 2022-10-11 | 6%
2021-04-30 | 2016 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 87980 | Develop Good Hope Heavy Maunevuer Training |  |  |  | 2020-01-10 | 2021-01-09 | 2021-05-26 | 84%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Kansas | United States | 88028 | Support Maintenance Warehouse |  |  |  | 2019-02-25 | 2020-02-25 | 2020-09-29 | 88% | 2020-10-21
2019-08-31 | 2016 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 88047 | Supply Support Activity, CAB |  |  |  | 2018-03-19 | 2019-03-19 | 2019-05-11 | 97% | 2019-06-20
2021-04-30 | 2020 | Army Active | Major Military Construction | Pennsylvania | United States | 88077 | General Instruction Building INC 1 |  |  |  | 2020-04-01 | 2023-04-01 | 2023-03-31 | 31%
2021-04-30 | 2016 | Army Active | Unspecified Minor Military Construction | New York | United States | 88231 | Upgrade Access Control Point, South Gate |  |  |  | 2019-04-26 | 2020-04-25 | 2020-11-20 | 95% | 2021-01-20
2019-08-31 | 2017 | Army Active | Unspecified Minor Military Construction | New Hampshire | United States | 88369 | Transformers |  |  |  | 2017-10-13 | 2018-10-13 | 2019-05-01 | 98% | 2019-06-30
2021-04-30 | 2018 | Army Active | Major Military Construction | Texas | United States | 88380 | Vehicle Maintenance Shop |  |  |  | 2019-11-04 | 2021-08-15 | 2021-11-17 | 57%
2019-08-31 | 2016 | Army Active | Unspecified Minor Military Construction | Missouri | United States | 88386 | CIDC Field Operations Building |  |  |  | 2017-09-20 | 2018-09-20 | 2019-01-24 | 92% | 2019-01-24
2021-04-30 | 2019 | Army Active | Major Military Construction |  | Poland | 88542 | EDI: Rail Extension and Railhead |  |  |  | 2019-10-30 | 2022-04-17 | 2022-03-21 | 27%
2018-03-31 | 2017 | Army Active | Unspecified Minor Military Construction |  | Puerto Rico | 88722 | Fire Station |  |  |  | 2017-05-19 | 2018-07-13 | 2018-06-13 | 3%
2021-04-30 | 2019 | Army Active | Major Military Construction | Georgia | United States | 88724 | Cyber Instructional Fac and Network Ctr |  |  |  | 2020-07-17 | 2022-07-07 | 2022-10-11 | 5%
2021-04-30 | 2020 | Army Active | Major Military Construction | Georgia | United States | 88725 | Cyber Instructional Fac (Admin/Command)INC |  |  |  | 2021-05-05 | 2024-04-19 | 2024-04-19 | 3%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Louisiana | United States | 88844 | Overhead Protection |  |  |  | 2020-01-16 | 2021-01-15 | 2021-06-01 | 68%
2021-04-30 | 2020 | Army Active | Major Military Construction | North Carolina | United States | 89057 | Dining Facility |  |  |  | 2020-09-16 | 2022-03-10 | 2022-03-10 | 11%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 89128 | AIRCRAFT ENGINE TEST BUILDING |  |  |  | 2019-04-03 | 2020-07-26 | 2021-06-15 | 73%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Kansas | United States | 89203 | Railroad Tracks |  |  |  | 2020-02-26 | 2020-12-02 | 2020-12-14 | 67% | 2020-12-14
2021-04-30 | 2017 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 89215 | Maneuver/Training Area Heavy Forces |  |  |  | 2020-01-10 | 2021-01-09 | 2021-05-23 | 73%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Alaska | United States | 89227 | Combat Readiness Training Facility |  |  |  | 2019-08-29 | 2020-11-21 | 2021-03-09 | 90% | 2021-03-09
2021-04-30 | 2018 | Army Active | Major Military Construction | Virginia | United States | 89235 | Security Fence |  | 4500000 | 61147, 77538 | 2019-01-07 | 2020-07-05 | 2020-07-05 | 98% | 2020-12-30
2017-07-31 | 2016 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 89734 | Administrative Building, General Purpose |  |  |  | 2016-10-18 | 2017-05-16 | 2017-05-16 | 99%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Mississippi | United States | 89821 | Engineer Research & Development |  |  |  | 2020-01-21 | 2021-07-14 | 2021-07-14 | 89%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction |  | Kuwait | 89831 | Underground Electrical Lines |  |  |  | 2020-01-24 | 2021-03-17 | 2021-03-03 | 100%
2018-08-31 | 2015 | Army Active | Major Military Construction | Kentucky | United States | 8984 | Shipping and Receiving Building |  | 650000 | 92764 | 2016-10-18 | 2018-04-11 | 2018-08-02 | 93%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 89946 | Engineer Research & Development |  |  |  | 2020-02-27 | 2021-05-28 | 2021-06-03 | 90%
2021-04-30 | 2018 | Army Active | Major Military Construction | Arizona | United States | 90351 | Ground Transport Equipment Building |  |  |  | 2021-04-21 | 2023-02-10 | 2021-12-21 | 0%
2021-04-30 | 2018 | Army Active | Major Military Construction | New York | United States | 90722 | Cemetery |  | 1300000 | 88724 | 2019-10-17 | 2021-09-01 | 2022-04-06 | 36%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | North Carolina | United States | 91252 | Pedestrian Bridges |  |  |  | 2020-04-10 | 2021-05-15 | 2022-02-11 | 10%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 91311 | Support Maintenance Warehouse |  |  |  | 2019-10-17 | 2020-12-10 | 2021-04-26 | 55%
2021-04-30 | 2020 | Army Active | Unspecified Minor Military Construction | Texas | United States | 91328 | Ready Building-Tactical Operations Center |  |  |  | 2020-11-09 | 2021-11-09 | 2021-11-09 | 1%
2020-08-31 | 2018 | Army Active | Unspecified Minor Military Construction | Massachusetts | United States | 91359 | Organizational Storage Building |  |  |  | 2018-10-12 | 2019-10-27 | 2020-05-31 | 93% | 2020-06-15
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Massachusetts | United States | 91360 | Mail Distribution Center |  |  |  | 2019-09-04 | 2020-10-03 | 2020-10-03 | 99% | 2020-09-08
2021-04-30 | 2020 | Army Active | Unspecified Minor Military Construction | North Carolina | United States | 91397 | Field Research Facility Annex |  |  |  | 2020-11-20 | 2021-11-15 | 2021-12-22 | 0%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | California | United States | 91528 | Brigade (BDE) Headquarters Building |  |  |  | 2019-09-12 | 2020-10-02 | 2021-05-18 | 89%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction |  | Romania | 91732 | Power Substation/Switching Station Bldg |  |  |  | 2018-10-30 | 2020-10-24 | 2021-10-30 | 51%
2021-04-30 | 2018 | Army Active | Major Military Construction | Hawaii | United States | 91742 | Operational Readiness Tng Cplx (Brks), Ph1 |  | 8500000 | 88724 | 2019-10-04 | 2021-09-23 | 2022-03-01 | 34%
2021-04-30 | 2020 | Army Active | Major Military Construction | Texas | United States | 91996 | Vehicle Bridge |  |  |  | 2020-11-19 | 2022-07-12 | 2022-07-19 | 7%
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Georgia | United States | 92022 | Battle Lab |  |  |  | 2019-08-22 | 2020-06-17 | 2021-05-05 | 92%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Washington | United States | 92526 | Clear Water Rinse System |  |  |  | 2019-09-18 | 2020-09-17 | 2020-10-30 | 100% | 2020-09-17
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Alabama | United States | 92781 | Flight Control Towers |  |  |  | 2019-10-21 | 2021-02-12 | 2021-04-24 | 97% | 2021-04-24
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Kansas | United States | 93000 | Storage Building, General Purpose, Install |  |  |  | 2019-09-13 | 2020-09-12 | 2021-03-22 | 92%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Texas | United States | 93016 | Aviation Parts Storage |  |  |  | 2019-09-23 | 2020-09-22 | 2021-06-24 | 96%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Washington | United States | 93019 | Aviation Parts Storage |  |  |  | 2019-08-28 | 2020-08-27 | 2020-10-07 | 96% | 2020-12-04
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Hawaii | United States | 93021 | Aviation Parts Storage |  |  |  | 2020-05-18 | 2022-01-08 | 2022-01-08 | 0%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Alaska | United States | 93022 | Aviation Parts Storage |  |  |  | 2019-06-17 | 2020-09-09 | 2021-08-06 | 89%
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction |  | Germany | 93209 | Aircraft Parts Storage |  |  |  | 2021-06-14 | 2022-11-14 | 2023-02-12 | 0%
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 94606 | Yuma Project 2 |  |  |  | 2019-11-12 | 2021-06-08 | 2021-06-29 | 0%
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 94607 | Yuma Project 10/27 |  |  |  | 2019-11-12 | 2021-06-08 | 2021-06-29 | 83%
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 94608 | Yuma Project 3 |  |  |  | 2020-01-09 | 2021-01-08 | 2021-04-27 | 74% | 2021-04-27
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 94609 | San Diego Project 4 |  |  |  | 2019-12-04 | 2021-03-03 | 2021-05-21 | 47%
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 94610 | Yuma Project 6 |  |  |  | 2020-01-21 | 2021-07-20 | 2021-08-29 | 0%
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 94611 | El Paso Project 2 |  |  |  | 2020-01-25 | 2021-01-25 | 2021-09-02 | 0%
2021-04-30 | 2019 | Army Active | Major Military Construction | Texas | United States | 94612 | El Paso Project 8 |  |  |  | 2020-01-25 | 2021-01-24 | 2021-09-02 | 0%
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Alabama | United States | 010908 | National Guard Readiness Center |  |  |  | 2020-09-01 | 2021-09-30 | 2022-02-25 | 20% | 2022-02-25
2021-05-20 | 2019 | Army National Guard | Major Military Construction | Alaska | United States | 020143 | United States Property and Fiscal Office Building |  |  |  | 2019-08-12 | 2021-04-23 | 2021-05-14 | 69% | 2021-05-14
2020-11-12 | 2018 | Army National Guard | Unspecified Minor Military Construction | Arkansas | United States | 050156 | Dining Facility Addition/Alteration |  |  |  | 2019-10-21 | 2020-09-30 | 2020-10-28 | 100% | 2020-10-28
2021-05-20 | 2019 | Army National Guard | Unspecified Minor Military Construction | Arkansas | United States | 050220 | Access Control Building |  |  |  | 2020-10-19 | 2021-10-15 | 2021-10-15 | 15% | 2021-10-15
2021-05-20 | 2017 | Army National Guard | Major Military Construction | Colorado | United States | 080115 | National Guard Readiness Center |  |  |  | 2019-05-20 | 2021-07-23 | 2020-09-30 | 99% | 2020-09-30
2021-05-20 | 2016 | Army National Guard | Unspecified Minor Military Construction | Colorado | United States | 080213 | Airborne Equip/Parachute Repair Shop |  |  |  | 2018-05-14 | 2018-12-31 | 2020-05-30 | 99% | 2018-12-31
2021-05-20 | 2018 | Army National Guard | Unspecified Minor Military Construction | Colorado | United States | 080220 | Unheated Aircraft Storage Hangar |  |  |  | 2020-08-01 | 2021-05-01 | 2021-05-01 | 1% | 2021-05-01
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Delaware | United States | 100040 | Combined Support Maintenance Shop |  |  |  | 2019-04-08 | 2020-12-31 | 2020-11-20 | 99% | 2020-12-31
2021-04-20 | 2016 | Army National Guard | Major Military Construction | Florida | United States | 120173 | National Guard Readiness Center |  |  |  | 2016-11-01 | 2018-03-31 | 2020-07-30 | 95% | 2020-07-30
2021-04-20 | 2015 | Army National Guard | Unspecified Minor Military Construction | Florida | United States | 120212 | Organizational Vehicle Parking, Paved |  |  |  | 2018-02-15 | 2018-06-30 | 2020-08-30 | 40% | 2020-08-30
2021-05-20 | 2017 | Army National Guard | Major Military Construction | Hawaii | United States | 150035 | Combined Support Maintenance Shop |  |  |  | 2018-02-26 | 2019-06-30 | 2021-06-15 | 92% | 2020-12-31
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Idaho | United States | 160024 | Railroad Tracks |  |  |  | 2020-09-22 | 2022-09-02 | 2022-03-16 | 30% | 2022-03-16
2021-05-20 | 2018 | Army National Guard | Unspecified Minor Military Construction | Idaho | United States | 160174 | Water Storage Tank, Potable |  |  |  | 2020-01-13 | 2021-01-23 | 2021-06-01 | 95% | 2021-06-01
2021-03-16 | 2018 | Army National Guard | Major Military Construction | Idaho | United States | 160176 | Digital Air/Ground Integration Range |  |  |  | 2019-04-08 | 2020-05-12 | 2020-10-14 | 100% | 2020-10-14
2021-05-20 | 2019 | Army National Guard | Unspecified Minor Military Construction | Idaho | United States | 160193 | Fire Station Addition |  |  |  | 2020-09-25 | 2021-08-20 | 2021-10-02 | 45% | 2021-10-02
2021-05-20 | 2014 | Army National Guard | Unspecified Minor Military Construction | Illinois | United States | 171303 | Nonorganizational Vehicle Parking, Paved |  |  |  | 2019-04-15 | 2019-08-30 | 2020-09-30 | 100% | 2020-11-11
2021-05-20 | 2019 | Army National Guard | Major Military Construction | Illinois | United States | 171510 | Automated Record Fire Range |  |  |  | 2020-04-06 | 2020-10-16 | 2021-09-01 | 85% | 2021-09-01
2021-03-16 | 2014 | Army National Guard | Unspecified Minor Military Construction | Indiana | United States | 180234 | National Guard Readiness Center Add/Alt |  |  |  | 2018-11-15 | 2019-12-31 | 2020-11-13 | 93% | 2020-09-08
2021-05-20 | 2020 | Army National Guard | Unspecified Minor Military Construction | Iowa | United States | 190005 | Enlisted Barracks, Transient Training Addition |  |  |  | 2020-09-21 | 2021-04-15 | 2021-04-15 | 1% | 2021-04-15
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Iowa | United States | 190130 | Vehicle Maintenance Instructional Building Addition |  |  |  | 2018-10-15 | 2019-12-31 | 2021-04-30 | 65% | 2021-04-30
2021-05-20 | 2017 | Army National Guard | Major Military Construction | Kansas | United States | 200101 | National Guard Readiness Center |  |  |  | 2018-12-04 | 2020-12-23 | 2021-03-08 | 93% | 2021-03-08
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Kansas | United States | 200151 | Enlisted Barracks, Transient Training |  |  |  | 2018-10-10 | 2020-05-14 | 2020-11-27 | 99% | 2020-11-27
2021-05-20 | 2015 | Army National Guard | Major Military Construction | Maine | United States | 230113 | National Guard Reserve Center |  |  |  | 2015-08-20 | 2017-08-03 | 2021-03-31 | 99% | 2018-04-02
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Maine | United States | 230135 | National Guard Readiness Center |  |  |  | 2018-09-17 | 2020-09-01 | 2021-08-31 | 92% | 2020-09-01
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Maryland | United States | 240149 | National Guard Readiness Center |  |  |  | 2018-11-01 | 2020-10-30 | 2021-04-30 | 97% | 2021-05-01
2021-05-20 | 2013 | Army National Guard | Major Military Construction | Massachusetts | United States | 250065 | Unit Training Equipment Site |  |  |  | 2014-04-07 | 2015-07-30 | 2017-05-17 | 84% | 2015-07-30
2021-05-20 | 2015 | Army National Guard | Unspecified Minor Military Construction | Michigan | United States | 260222 | Ammunition Hut, Installation |  |  |  | 2019-05-01 | 2019-10-04 | 2020-12-31 | 78% | 2020-01-26
2021-05-20 | 2020 | Army National Guard | Unspecified Minor Military Construction | Michigan | United States | 260269 | Aircraft Maintenance Bay |  |  |  | 2020-10-05 | 2021-11-05 | 2021-11-05 | 5% | 2021-11-05
2021-05-20 | 2019 | Army National Guard | Unspecified Minor Military Construction | Michigan | United States | 260274 | Waste Water Treatment Plant Add/Alt |  |  |  | 2020-05-27 | 2020-10-02 | 2021-04-20 | 80% | 2020-05-31
2021-04-20 | 2017 | Army National Guard | Major Military Construction | Minnesota | United States | 270109 | Transient Training Officer Quarters |  | 8000000 | 490706 | 2017-10-03 | 2019-05-31 | 2019-10-16 | 100% | 2019-10-16
2021-05-20 | 2017 | Army National Guard | Unspecified Minor Military Construction | Minnesota | United States | 270127 | Vehicle Storage Building, Installation Alteration |  |  |  | 2019-03-04 | 2020-04-10 | 2020-04-17 | 100% | 2020-04-10
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Minnesota | United States | 270132 | National Guard Readiness Center |  |  |  | 2018-10-05 | 2020-08-24 | 2020-07-01 | 99% | 2020-07-01
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Minnesota | United States | 270203 | National Guard Vehicle Maintenance Shop |  |  |  | 2021-04-19 | 2022-08-20 | 2022-08-20 | 1% | 2022-08-20
2021-05-20 | 2018 | Army National Guard | Unspecified Minor Military Construction | Minnesota | United States | 270233 | BN Headquarters Transient Training |  |  |  | 2021-05-03 | 2023-07-20 | 2023-07-20 | 1% | 2023-07-20
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Mississippi | United States | 280408 | Automated Multipurpose Machine Gun Range |  |  |  | 2020-09-15 | 2021-09-30 | 2021-09-30 | 26% | 2021-09-30
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Missouri | United States | 290109 | Aircraft Maintenance Hangar Addition (AVCRAD) |  |  |  | 2018-11-19 | 2020-11-18 | 2020-11-18 | 96% | 2020-11-18
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Missouri | United States | 290186 | National Guard Readiness Center |  |  |  | 2020-08-01 | 2021-08-18 | 2021-09-23 | 12% | 2021-09-23
2021-05-20 | 2019 | Army National Guard | Major Military Construction | Montana | United States | 300031 | National Guard Readiness Center |  |  |  | 2019-06-03 | 2021-04-09 | 2020-12-04 | 99% | 2020-12-04
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Nebraska | United States | 310103 | Training Site Rebuild |  |  |  | 2020-09-01 | 2022-10-28 | 2022-10-28 | 15% | 2022-10-28
2021-05-20 | 2021 | Army National Guard | Major Military Construction | Nebraska | United States | 310140 | National Guard Vehicle Maintenance Shop |  |  |  | 2021-04-01 | 2022-09-20 | 2022-09-20 | 1% | 2022-09-20
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Nebraska | United States | 310168 | Flood Control Levee/Floodwall |  |  |  | 2020-10-05 | 2021-04-30 | 2021-05-14 | 80% | 2021-05-14
2021-04-20 | 2019 | Army National Guard | Major Military Construction | Nevada | United States | 320157 | National Guard Readiness Center |  |  |  | 2019-02-05 | 2020-05-28 | 2020-06-30 | 99% | 2020-06-30
2021-04-20 | 2019 | Army National Guard | Major Military Construction | New Hampshire | United States | 330043 | National Guard Readiness Center |  |  |  | 2019-03-18 | 2020-06-30 | 2020-09-30 | 100% | 2020-09-30
2021-05-20 | 2020 | Army National Guard | Major Military Construction | New Hampshire | United States | 330050 | National Guard Readiness Center |  |  |  | 2020-10-05 | 2022-09-02 | 2022-09-02 | 1% | 2022-09-02
2021-04-20 | 2017 | Army National Guard | Unspecified Minor Military Construction | New Hampshire | United States | 330475 | National Guard Ready Building Add/Alt |  |  |  | 2019-02-15 | 2019-09-23 | 2020-09-30 | 100% | 2020-09-30
2021-05-20 | 2018 | Army National Guard | Major Military Construction | New Mexico | United States | 350200 | National Guard Readiness Center Addition |  |  |  | 2019-04-08 | 2020-10-01 | 2021-02-26 | 80% | 2021-02-26
2021-05-20 | 2020 | Army National Guard | Major Military Construction | New York | United States | 361811 | National Guard Readiness Center Alteration |  |  |  | 2020-10-19 | 2022-09-16 | 2022-09-16 | 8% | 2022-09-16
2021-05-20 | 2017 | Army National Guard | Major Military Construction | North Carolina | United States | 371301 | National Guard Readiness Center |  |  |  | 2017-11-15 | 2019-08-17 | 2020-05-01 | 96% | 2020-03-15
2021-05-20 | 2019 | Army National Guard | Major Military Construction | North Dakota | United States | 380116 | National Guard Readiness Center |  |  |  | 2019-06-10 | 2021-06-30 | 2021-06-30 | 60% | 2021-06-30
2021-05-20 | 2019 | Army National Guard | Major Military Construction | Ohio | United States | 390285 | Automated Multipurpose Machine Gun (MPMG) Range |  |  |  | 2020-09-28 | 2022-09-30 | 2022-09-30 | 1% | 2022-09-30
2021-03-16 | 2016 | Army National Guard | Unspecified Minor Military Construction | Oklahoma | United States | 401221 | Fire Station |  |  |  | 2019-05-06 | 2020-09-25 | 2020-09-25 | 1% | 2020-09-25
2021-03-16 | 2019 | Army National Guard | Major Military Construction | Oklahoma | United States | 401301 | Aircraft Maintenance Bay (Aircraft Storage) |  |  |  | 2019-11-18 | 2020-10-30 | 2020-10-30 | 1% | 2020-10-30
2021-05-20 | 2019 | Army National Guard | Major Military Construction | Oregon | United States | 410818 | Tactical Unmanned Aerial Vehicle Hangar |  |  |  | 2020-06-01 | 2021-10-22 | 2021-11-22 | 30% | 2021-10-22
2021-05-20 | 2019 | Army National Guard | Unspecified Minor Military Construction | Oregon | United States | 411104 | Water Supply/Treatment Building, Potable |  |  |  | 2020-07-07 | 2020-12-31 | 2021-06-30 | 75% | 2020-12-31
2021-05-20 | 2015 | Army National Guard | Major Military Construction | Oregon | United States | 411300 | BIOMASS Heating |  |  |  | 2020-04-13 | 2020-09-30 | 2021-01-19 | 100% | 2020-09-30
2021-05-20 | 2015 | Army National Guard | Major Military Construction | Oregon | United States | 411301 | Exterior/Interior Lighting Retrofit, Multiple Sites |  |  |  | 2017-10-12 | 2018-12-29 | 2021-06-30 | 95% | 2020-10-01
2021-05-20 | 2016 | Army National Guard | Unspecified Minor Military Construction | Oregon | United States | 411503 | Waste Water Treatment Facility |  |  |  | 2020-07-22 | 2021-01-31 | 2021-06-30 | 60% | 2021-01-31
2021-05-20 | 2017 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420502 | Access Control Building |  |  |  | 2019-05-12 | 2020-09-26 | 2020-09-26 | 4% | 2022-05-26
2021-05-20 | 2016 | Army National Guard | Major Military Construction | Pennsylvania | United States | 420522 | Training Aids Center |  |  |  | 2017-11-20 | 2018-08-24 | 2019-12-30 | 99% | 2020-07-06
2021-05-20 | 2017 | Army National Guard | Major Military Construction | Rhode Island | United States | 440064 | National Guard/Reserve Center Building (JFHQ) |  |  |  | 2017-10-02 | 2020-02-28 | 2021-09-30 | 98% | 2020-02-28
2021-05-20 | 2019 | Army National Guard | Major Military Construction | South Dakota | United States | 460115 | National Guard Readiness Center |  |  |  | 2019-05-01 | 2020-11-01 | 2020-11-15 | 27% | 2020-11-15
2021-05-20 | 2020 | Army National Guard | Unspecified Minor Military Construction | South Dakota | United States | 465001 | Access Control Building |  |  |  | 2020-08-24 | 2021-08-27 | 2021-08-27 | 1% | 2021-08-27
2021-05-20 | 2015 | Army National Guard | Unspecified Minor Military Construction | Tennessee | United States | 470035 | Sanitary Sewer |  |  |  | 2020-05-01 | 2021-01-20 | 2021-06-15 | 75% | 2021-01-20
2021-05-20 | 2014 | Army National Guard | Major Military Construction | Texas | United States | 480243 | Armed Forces Reserve Center |  |  |  | 2016-04-13 | 2017-06-09 | 2019-07-03 | 90% | 2019-07-03
2021-05-20 | 2017 | Army National Guard | Major Military Construction | Utah | United States | 490601 | National Guard Readiness Center |  |  |  | 2017-10-19 | 2019-04-03 | 2020-08-20 | 99% | 2020-04-15
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Vermont | United States | 500110 | General Instruction Building |  |  |  | 2020-10-12 | 2022-09-02 | 2022-09-02 | 1% | 2022-09-02
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Virginia | United States | 511503 | National Guard Readiness Center |  |  |  | 2018-11-05 | 2020-08-31 | 2021-04-29 | 99% | 2021-04-29
2020-11-12 | 2020 | Army National Guard | Unspecified Minor Military Construction | Virginia | United States | 511863 | Access Control Building |  |  |  | 2020-10-05 | 2021-09-10 | 2021-09-10 | 1% | 2021-09-10
2021-05-20 | 2016 | Army National Guard | Major Military Construction | Washington | United States | 530041 | Enlisted Barracks, Transient Training |  |  |  | 2018-09-17 | 2020-04-17 | 2021-08-29 | 80% | 2021-09-30
2021-05-20 | 2018 | Army National Guard | Major Military Construction | Washington | United States | 530129 | National Guard Readiness Center |  |  |  | 2018-10-15 | 2020-09-01 | 2021-07-15 | 96% | 2021-07-30
2021-05-20 | 2020 | Army National Guard | Major Military Construction | Washington | United States | 531201 | National Guard Readiness Center |  |  |  | 2020-10-01 | 2022-03-21 | 2022-03-21 | 19% | 2022-03-21
2021-05-20 | 2017 | Army National Guard | Unspecified Minor Military Construction | Wisconsin | United States | 550280 | National Guard/Reserve Center Building Alteration |  |  |  | 2019-05-20 | 2021-04-09 | 2021-04-09 | 1% | 2021-04-09
2021-05-20 | 2020 | Army National Guard | Unspecified Minor Military Construction | Virginia | United States | 571863 | Access Control Building |  |  |  | 2021-06-01 | 2022-07-30 | 2022-07-30 | 1% | 2022-07-30
2020-08-31 | 2016 | Army Reserve | Major Military Construction |  | Puerto Rico | 58405 | Access Control Point |  |  |  | 2017-06-23 | 2019-05-04 | 2020-02-21 | 97% | 2019-12-10
2017-07-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 65277 | Consolidated Dining Facility |  |  |  | 2014-04-23 | 2015-09-30 | 2017-03-21 | 97% | 2017-03-29
2017-07-31 | 2012 | Army Reserve | Major Military Construction | North Carolina | United States | 67466 | Army Reserve Center/Land |  |  |  | 2012-10-10 | 2014-03-19 | 2017-03-22 | 93% | 2017-03-29
2021-04-30 | 2015 | Army Reserve | Major Military Construction | Wisconsin | United States | 67567 | Access Control Point/Mail/Freight Center |  |  |  | 2017-06-02 | 2019-12-22 | 2021-05-26 | 97%
2017-07-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 67652 | Army Reserve Center |  |  |  | 2015-04-24 | 2017-02-12 | 2017-05-30 | 98% | 2017-05-30
2017-07-31 | 2013 | Army Reserve | Major Military Construction | Illinois | United States | 67659 | Army Reserve Center |  |  |  | 2014-01-13 | 2015-11-04 | 2016-11-28 | 99% | 2017-01-05
2018-08-31 | 2015 | Army Reserve | Major Military Construction | New York | United States | 67661 | Army Reserve Center/AMSA |  |  |  | 2016-04-07 | 2018-03-08 | 2018-06-29 | 98% | 2018-07-02
2019-08-31 | 2014 | Army Reserve | Major Military Construction | Maryland | United States | 67663 | Army Reserve Center/Land |  |  |  | 2015-10-07 | 2017-09-06 | 2018-10-31 | 98% | 2019-01-23
2018-08-31 | 2012 | Army Reserve | Major Military Construction | Kansas | United States | 67681 | Army Reserve Center/Land |  |  |  | 2016-10-12 | 2018-01-05 | 2018-04-11 | 98% | 2018-04-11
2021-04-30 | 2014 | Army Reserve | Major Military Construction | New York | United States | 67690 | Army Reserve Center |  |  |  | 2017-06-29 | 2019-06-19 | 2020-10-01 | 99% | 2020-09-25
2020-08-31 | 2013 | Army Reserve | Major Military Construction | Maryland | United States | 67705 | Army Reserve Center |  | 1143000 | 71900, 72088 | 2015-10-08 | 2017-09-07 | 2019-12-20 | 93% | 2020-01-07
2018-08-31 | 2012 | Army Reserve | Major Military Construction | Massachusetts | United States | 67709 | Army Reserve Center/Land |  |  |  | 2016-09-19 | 2018-03-23 | 2018-04-30 | 99% | 2018-08-02
2017-07-31 | 2013 | Army Reserve | Major Military Construction | Washington | United States | 67715 | Army Reserve Center |  |  |  | 2013-07-11 | 2016-01-15 | 2017-05-31 | 99% | 2017-05-31
2017-07-31 | 2011 | Army Reserve | Major Military Construction | Texas | United States | 69421 | Army Reserve Center/Land |  |  |  | 2012-08-21 | 2014-03-21 | 2017-08-30 | 84%
2019-08-31 | 2011 | Army Reserve | Major Military Construction | Virginia | United States | 69562 | Army Reserve Center |  |  |  | 2015-01-23 | 2017-05-10 | 2019-07-02 | 98% | 2019-07-02
2018-08-31 | 2010 | Army Reserve | Major Military Construction | Pennsylvania | United States | 69652 | Army Reserve Center/Land |  |  |  | 2012-04-03 | 2014-02-12 | 2017-10-27 | 99% | 2014-03-13
2020-08-31 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 71035 | TRAINING AIDS CENTER |  |  |  | 2017-12-14 | 2019-11-12 | 2019-11-12 | 95% | 2019-11-12
2020-08-31 | 2017 | Army Reserve | Major Military Construction | California | United States | 71036 | Emergency Services Center |  |  |  | 2018-03-27 | 2019-09-18 | 2020-04-08 | 99% | 2020-04-10
2017-07-31 | 2013 | Army Reserve | Major Military Construction | California | United States | 71482 | ORTC |  |  |  | 2014-03-19 | 2016-05-17 | 2017-03-17 | 93% | 2017-03-17
2017-07-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71768 | Automated Multipurpose Machine Gun (MPMG) |  |  |  | 2015-11-19 | 2017-05-12 | 2017-05-15 | 98% | 2017-05-15
2017-07-31 | 2014 | Army Reserve | Major Military Construction | New Jersey | United States | 71769 | Modified Record Fire Range |  |  |  | 2014-10-17 | 2016-04-09 | 2016-10-18 | 99% | 2016-10-18
2020-08-31 | 2015 | Army Reserve | Major Military Construction | California | United States | 71901 | Army Reserve Center/AMSA |  |  |  | 2016-03-02 | 2018-02-20 | 2020-06-18 | 96% | 2020-06-18
2019-08-31 | 2014 | Army Reserve | Major Military Construction | California | United States | 71903 | Army Reserve Center |  |  |  | 2016-11-28 | 2018-07-01 | 2019-05-22 | 94% | 2019-05-22
2017-07-31 | 2013 | Army Reserve | Major Military Construction | Wisconsin | United States | 72088 | ECS TEMF |  | 5455000 | 69562 | 2013-07-08 | 2016-12-12 | 2017-07-21 | 99% | 2017-07-21
2020-08-31 | 2014 | Army Reserve | Major Military Construction | California | United States | 72284 | TASS Training Center (TTC) |  |  |  | 2014-10-20 | 2016-05-22 | 2019-11-01 | 99% | 2019-11-01
2017-07-31 | 2015 | Army Reserve | Major Military Construction | Virginia | United States | 72291 | TASS Training Center |  |  |  | 2015-10-19 | 2017-08-28 | 2017-09-16 | 92%
2019-08-31 | 2013 | Army Reserve | Unspecified Minor Military Construction | California | United States | 73738 | FIRE STATION |  |  |  | 2017-12-14 | 2018-11-28 | 2018-11-28 | 25% | 2018-11-28
2019-08-31 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 74001 | PHYSICAL FITNESS FACILITY |  |  |  | 2017-12-14 | 2019-06-07 | 2019-06-07 | 23% | 2019-06-07
2021-04-30 | 2017 | Army Reserve | Unspecified Minor Military Construction | California | United States | 74732 | Family Life Center (Chapel annex) |  |  |  | 2018-01-09 | 2019-06-13 | 2020-12-14 | 94% | 2020-12-14
2021-04-30 | 2018 | Army Reserve | Major Military Construction |  | Puerto Rico | 77074 | Army Reserve Center |  |  |  | 2019-10-30 | 2021-04-22 | 2022-01-26 | 42%
2021-04-30 | 2017 | Army Reserve | Major Military Construction | Arizona | United States | 77134 | Army Reserve Center |  | 1722000 | 88731 | 2018-05-25 | 2020-05-14 | 2021-01-05 | 99% | 2021-01-05
2020-08-31 | 2015 | Army Reserve | Major Military Construction | New Jersey | United States | 77151 | Army Reserve Center |  |  |  | 2016-10-13 | 2018-09-13 | 2020-07-02 | 96% | 2020-07-02
2021-04-30 | 2016 | Army Reserve | Major Military Construction | Mississippi | United States | 77163 | Army Reserve Center |  |  |  | 2019-11-01 | 2021-06-23 | 2022-04-29 | 24%
2021-04-30 | 2016 | Army Reserve | Major Military Construction | Virginia | United States | 77186 | ECS Modified TEMF / Warehouse |  |  |  | 2017-08-01 | 2019-08-31 | 2020-12-15 | 97% | 2021-01-04
2020-08-31 | 2015 | Army Reserve | Major Military Construction | Illinois | United States | 77228 | Army Reserve Center |  | 2000000 | 88731 | 2017-06-14 | 2019-04-25 | 2019-11-12 | 99% | 2019-11-12
2021-04-30 | 2018 | Army Reserve | Major Military Construction | California | United States | 77238 | Army Reserve Center |  |  |  | 2018-10-22 | 2020-11-20 | 2021-04-15 | 99% | 2021-04-15
2021-04-30 | 2019 | Army Reserve | Major Military Construction | California | United States | 77268 | ECS Modified TEMF/ Warehouse |  |  |  | 2019-03-25 | 2020-11-21 | 2021-09-02 | 78%
2021-04-30 | 2018 | Army Reserve | Major Military Construction | Washington | United States | 77324 | Army Reserve Center |  |  |  | 2018-10-11 | 2020-09-30 | 2020-12-07 | 100% | 2021-01-14
2020-08-31 | 2018 | Army Reserve | Major Military Construction | Wisconsin | United States | 79003 | AT/MOB Dining Facility-1428 PN |  |  |  | 2018-06-20 | 2019-08-14 | 2020-03-13 | 99% | 2020-03-13
2019-08-31 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 80353 | Waste/Central Hazardous Waste Facility |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 35% | 2019-06-06
2020-08-31 | 2017 | Army Reserve | Major Military Construction | Wisconsin | United States | 80684 | AT/MOB Dining Facility |  |  |  | 2017-12-06 | 2019-09-11 | 2020-03-04 | 99% | 2020-03-04
2021-04-30 | 2019 | Army Reserve | Major Military Construction | Wisconsin | United States | 80690 | Transient Training Barracks |  |  |  | 2019-11-01 | 2021-08-22 | 2021-12-05 | 81%
2021-04-30 | 2020 | Army Reserve | Major Military Construction | Wisconsin | United States | 81802 | Transient Training Barracks |  |  |  | 2020-10-28 | 2022-12-17 | 2022-12-17 | 7%
2017-07-31 | 2015 | Army Reserve | Major Military Construction | Colorado | United States | 81959 | Training Building Addition |  |  |  | 2015-08-07 | 2016-12-09 | 2017-05-23 | 89% | 2017-05-23
2019-08-31 | 2015 | Army Reserve | Unspecified Minor Military Construction | California | United States | 85683 | UPH Laundry Building, Detached |  |  |  | 2017-12-14 | 2019-06-06 | 2019-06-06 | 24% | 2019-06-06
2018-08-31 | 2016 | Army Reserve | Unspecified Minor Military Construction | California | United States | 85808 | Military Equipment Parking |  |  |  | 2017-05-08 | 2018-05-08 | 2018-05-08 | 99% | 2018-05-08
2021-04-30 | 2016 | Army Reserve | Major Military Construction | Florida | United States | 85813 | AR Center/ AS Facility |  |  |  | 2017-11-03 | 2019-10-04 | 2021-05-07 | 95%
2019-08-31 | 2017 | Army Reserve | Major Military Construction | California | United States | 86521 | Transient Training Barracks |  |  |  | 2017-11-07 | 2019-05-01 | 2019-07-17 | 99% | 2019-07-17
2020-08-31 | 2016 | Army Reserve | Major Military Construction | New York | United States | 86814 | Organizational Maintenance Shop |  |  |  | 2017-10-18 | 2018-10-18 | 2020-09-30 | 96%
2021-04-30 | 2020 | Army Reserve | Major Military Construction | Delaware | United States | 86823 | Army Reserve Center |  |  |  | 2020-05-27 | 2022-03-28 | 2021-09-15 | 75%
2021-04-30 | 2016 | Army Reserve | Major Military Construction | California | United States | 86882 | Army Reserve Center |  |  |  | 2017-12-28 | 2019-12-18 | 2021-05-31 | 98%
2021-04-30 | 2018 | Army Reserve | Unspecified Minor Military Construction | Massachusetts | United States | 88585 | Range Support Building |  |  |  | 2018-10-23 | 2020-01-26 | 2020-10-09 | 99% | 2020-11-23
2021-04-30 | 2017 | Army Reserve | Unspecified Minor Military Construction |  | Puerto Rico | 88722 | Fire Station |  |  |  | 2017-05-19 | 2018-07-13 | 2020-10-30 | 90% | 2021-01-28
2021-04-30 | 2018 | Army Reserve | Major Military Construction |  | Puerto Rico | 88731 | AR Center Training Building |  |  |  | 2019-06-28 | 2020-12-19 | 2021-12-15 | 52%
2021-04-30 | 2019 | Army Reserve | Major Military Construction | Washington | United States | 90202 | ECS Modified TEMF |  |  |  | 2020-09-22 | 2022-06-22 | 2022-06-22 | 0%
2021-04-30 | 2019 | Army Reserve | Unspecified Minor Military Construction | Hawaii | United States | 90303 | Administrative Building, General Purpose |  |  |  | 2019-03-18 | 2020-06-10 | 2020-10-14 | 98% | 2021-01-04
2021-04-30 | 2020 | Army Reserve | Unspecified Minor Military Construction | Washington | United States | 90912 | Organizational Vehicle Parking, Unpaved |  |  |  | 2020-06-12 | 2021-07-22 | 2021-07-22 | 47%
2021-04-30 | 2018 | Army Reserve | Unspecified Minor Military Construction |  | Puerto Rico | 91427 | Physical Fitness Center Annex |  |  |  | 2018-11-05 | 2020-02-28 | 2020-10-02 | 98% | 2020-10-02
2021-05-31 | 2016 | DLA Defense Automation and Production Service | Major Military Construction | Virginia | United States | DESC1607 | Replace Fuel Pier and Distribution Facility, Langley AFB, VA |  |  |  | 2016-10-12 | 2019-10-12 | 2019-12-12 | 99% | 2019-12-31
2021-05-31 | 2018 | DLA Defense Automation and Production Service | Major Military Construction | Utah | United States | DESC1714 | DESC 1714 Replace POL Pumphouse, Hill AFB |  |  |  | 2019-06-07 | 2021-07-12 | 2021-07-12 | 80%
2021-05-31 | 2018 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | Virginia | United States | DESC18U1 | Pier A Rebiuld, Craney Island, VA |  |  |  | 2019-03-13 | 2020-03-13 | 2020-04-30 | 100% | 2020-05-11
2021-04-30 | 2013 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DCX1305 | Replace Reservoir, New Cumberland, PA |  |  |  | 2017-07-12 | 2019-06-26 | 2020-06-30 | 100% | 2019-06-18
2021-04-30 | 2014 | DLA Defense Distribution Center | Major Military Construction | Pennsylvania | United States | DDCX1309 A | Phase I DDC, Upgrade Public Safety Facility |  |  |  | 2016-11-18 | 2017-11-18 | 2019-07-06 | 100% | 2019-10-01
2021-05-31 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701A | CONSTRUCT WAREHOUSE & OPEN STORAGE (GPW) |  |  |  | 2018-06-26 | 2020-06-18 | 2020-06-18 | 94%
2021-05-31 | 2017 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1701B | CONSTRUCT WAREHOUSE & OPEN STORAGE (OSA) |  |  |  | 2018-09-30 | 2020-09-30 | 2020-09-30 | 75%
2021-05-31 | 2019 | DLA Defense Distribution Center | Major Military Construction | Texas | United States | DDCX1901 | Construct General Purpose Warehouse, Red River Army Depot |  |  |  | 2019-06-19 | 2023-07-31 | 2023-01-31 | 95%
2021-04-30 | 2015 | DLA Defense Distribution Center | Major Military Construction | South Carolina | United States | DESC1606 | Replace Fuel Distribution Facilities - MCAS Beaufort |  |  |  | 2015-12-16 | 2017-11-05 | 2019-11-22 | 100% | 2019-11-22
2021-04-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | Indiana | United States | DESC1301 | Replace Hydrant Fuel system - Grissom ARB |  |  |  | 2015-09-17 | 2017-04-09 | 2018-12-07 | 100% | 2018-09-25
2021-04-30 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1353 | Replace Hydrant Fuel System - Robins AFB |  |  |  | 2016-06-28 | 2018-06-18 | 2018-09-21 | 100% | 2018-05-24
2021-04-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1401 | Construct Type III Hydrant Fueling system - Iwakuni MCAS |  |  |  | 2015-04-26 | 2017-08-23 | 2018-11-15 | 100% | 2018-11-15
2021-05-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction |  | Cuba | DESC1404 | Replace Fuel Storage Tanks, Guantanamo Bay, Cuba |  |  |  | 2016-03-01 | 2017-11-13 | 2020-12-13 | 100% | 2020-12-07
2021-04-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1407 | Replace Hydrant Fuel System, Holloman AFB |  |  |  | 2015-08-17 | 2017-01-10 | 2017-07-19 | 100% | 2017-04-17
2021-05-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | South Dakota | United States | DESC1463 | Construct Hydrant Fuel System - Ellsworth AFB |  |  |  | 2016-01-19 | 2017-04-16 | 2017-06-15 | 100% | 2017-09-13
2021-04-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | New Jersey | United States | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst |  |  |  | 2014-11-18 | 2016-05-11 | 2018-05-03 | 100% | 2018-05-03
2021-04-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | 43 |  |  | 2015-08-10 | 2016-10-23 | 2017-07-18 | 100% | 2016-12-08
2021-04-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 A | Replace Fuel Distribution Facilities, Tinker AFB |  |  |  | 2015-01-19 | 2017-05-23 | 2018-01-18 | 100% | 2017-09-18
2021-04-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC1502 B | Replace Fuel Distribution Facilities, Tinker AFB |  |  |  | 2015-08-10 | 2016-10-23 | 2017-07-18 | 100% | 2017-07-18
2021-05-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Maryland | United States | DESC1507 | Construct Hydrant Fuel System Andrews AFB MD |  |  |  | 2016-10-31 | 2018-02-07 | 2018-10-15 | 100% | 2020-01-27
2021-05-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1508 | Replace Fuel Storage And Distribution Facilities NAS Lemoore CA |  |  |  | 2016-03-01 | 2020-03-30 | 2020-05-25 | 100% | 2020-09-18
2021-05-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | United States | DESC1513 | Replace JP-8 Fuel Storage Tanks, Patrick AFB, FL-Demolition |  |  |  | 2019-07-15 | 2020-09-15 | 2020-09-15 | 100%
2021-05-31 | 2015 | DLA Defense Energy Support Center | Major Military Construction | Hawaii | United States | DESC1551 | Upgrade fire Suppression and Ventilation System - Rd Hill; JB Pearl Harbor - Hickam |  |  |  | 2015-09-30 | 2017-09-25 | 2018-01-31 | 100% | 2018-01-31
2021-05-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Germany | DESC1603 | CONSTRUCT FUEL LINE NORTH TO SOUTH SIDE, SPANGDAHLEM AB |  |  |  | 2019-08-10 | 2020-08-10 | 2019-10-02 | 100% | 2020-12-07
2021-05-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Delaware | United States | DESC1605 | Construct Hydrant Fuel System, Dover AFB, DE |  |  |  | 2019-07-06 | 2020-01-06 | 2020-05-03 | 100% | 2020-05-23
2021-05-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1607 | Replace Fuel Pier and Distribution Facility, Langley AFB, VA |  |  |  | 2016-10-12 | 2018-05-29 | 2019-10-12 | 100% | 1900-04-06
2021-05-31 | 2018 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1608 | Consolidate Fuel Facilities at Shaw AFB, SC |  |  |  | 2019-06-13 | 2021-03-19 | 2021-09-11 | 90%
2021-05-31 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1609 | Ft Belvoir, Replace Ground Fueling Facility |  |  |  | 2019-07-15 | 2021-07-15 | 2021-07-15 | 96%
2021-05-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction | California | United States | DESC1611 | REPLACE HYDRANT SYSTEM (G) Travis AFB |  |  |  | 2017-12-30 | 2020-03-10 | 2020-03-10 | 100% | 2020-07-24
2021-05-31 | 2019 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | Virginia | United States | DESC16U1 | Construct Craney North Pier D Breasting Dolphin |  |  |  | 2018-09-12 | 2019-09-29 | 2020-04-01 | 100% | 2020-03-12
2021-05-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction |  | Djibouti | DESC1701 | Construct Fuel Storage Facilities, Camp Lemonnie, Djibouti, Horn-of-Africa |  |  |  | 2017-03-13 | 2020-11-30 | 2021-02-24 | 95%
2021-05-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | New Mexico | United States | DESC1702 | CONSTRUCT DISTIBUTION PT. SE RAMP, CANNON AFB |  |  |  | 2017-12-07 | 2019-06-25 | 2019-08-03 | 100% | 2019-07-19
2021-05-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Marshall Islands | DESC1704 | REPLACEMENT STORAGE TANKS |  |  |  | 2017-11-08 | 2020-12-27 | 2022-06-30 | 60%
2021-05-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Diego Garcia | DESC1705 | IMPROVE WHARF REFUELING CAPABILITY Diego Garcia |  |  |  | 2017-06-30 | 2019-06-29 | 2020-01-20 | 100% | 2020-04-28
2021-05-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction | South Carolina | United States | DESC1706 | CONSTRUCT HYDRANT SYSTEM HOT CARGO PAD |  |  |  | 2017-09-19 | 2019-04-04 | 2019-05-26 | 100% | 2019-06-20
2021-05-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction | Alaska | United States | DESC1707 | CONSTRUCT TRUCK OFFLOAD FACILITY |  |  |  | 2017-08-24 | 2018-12-15 | 2018-12-03 | 100%
2021-05-31 | 2017 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1708 | CONSTRUCT TRUCK FUEL RECEIPT SYSTEM |  |  |  | 2017-09-08 | 2019-09-08 | 2019-09-08 | 95%
2021-05-31 | 2018 | DLA Defense Energy Support Center | Major Military Construction |  | Guam | DESC1709 | Construct Fuel Truck Offload, Andersen AB |  |  |  | 2018-09-21 | 2019-12-15 | 2021-12-15 | 85%
2021-05-31 | 2016 | DLA Defense Energy Support Center | Major Military Construction | Georgia | United States | DESC1710 | Replace Truck Fill Stands, Moody AFB, Georgia |  |  |  | 2016-11-02 | 2018-04-26 | 2019-08-27 | 100% | 2019-03-01
2021-05-31 | 2019 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | California | United States | DESC17U3 | New Fuels lab-Point Loma |  |  |  | 2020-01-20 | 2021-01-15 | 2021-01-15 | 90%
2021-05-31 | 2018 | DLA Defense Energy Support Center | Major Military Construction |  | Japan | DESC1805 | FY18 DLA DESC1805 Upgrade Fuel Wharf, Yokose Fuel Terminal, Japan SABO JAPAN |  |  |  | 2019-03-13 | 2021-04-21 | 2021-05-31 | 40%
2021-05-31 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Oklahoma | United States | DESC18S2 | Replace Bulk Diesel System,McAlester Army Ammo Plant |  |  |  | 2019-09-19 | 2021-02-26 | 2021-07-26 | 80%
2021-05-31 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Washington | United States | DESC1905 | Hot Refuel ReplacementJoint Base Lewis-McChord |  |  |  | 2019-08-19 | 2021-03-31 | 2021-03-31 | 80%
2021-05-31 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Virginia | United States | DESC1909 | Replace Flight Line Aviation POL Yard, Joint Base Langley-Eustis |  |  |  | 2019-09-30 | 2020-12-31 | 2021-06-30 | 68%
2021-05-31 | 2019 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | Virginia | United States | DESC1914 | Replace Ground Vehicle Fuel Facility, Joint Base Langley-Eustis |  |  |  | 2019-06-17 | 2020-12-31 | 2021-05-30 | 81%
2021-05-31 | 2019 | DLA Defense Energy Support Center | Major Military Construction | Texas | United States | DESC19I1 | Construct Aerospace Facility Joint Base San Antonio |  |  |  | 2019-08-07 | 2020-11-20 | 2021-09-30 | 85%
2021-05-31 | 2019 | DLA Defense Energy Support Center | Major Military Construction |  | Guam | DESC19S2 | Convert Bulk Tanks at Sasa Valley, Guam |  |  |  | 2019-11-04 | 2022-03-15 | 2022-03-15 | 75%
2021-05-31 | 2015 | DLA Defense National Stockpile Center | Major Military Construction | Maryland | United States | DESC1507 | Construct Hydrant Fuel System Andrews AFB MD |  |  |  | 2016-10-31 | 2018-02-07 | 2019-11-13 | 100% | 2019-11-13
2021-05-31 | 2018 | DLA Defense Reutilization and Marketing Service | Major Military Construction | Florida | United States | DRMS1701 | Upgrade Open Storage Yard, Eglin AB |  |  |  | 2018-09-02 | 2019-07-06 | 2019-10-18 | 100% | 2019-10-18
2021-05-31 | 2016 | DLA Defense Supply Center Philadelphia | Major Military Construction | Pennsylvania | United States | DSCP1501 | DLA Toop Suport Headquarters, NSA Philadelphia, PA |  |  |  | 2016-10-01 | 2019-03-30 | 2022-01-02 | 100% | 2019-12-01
2021-05-31 | 2015 | DLA Defense Supply Center Richmond | Major Military Construction | Virginia | United States | DSCR1501 | Replace Access Control Point, Richmond |  |  |  | 2018-02-23 | 2019-08-12 | 2020-10-12 | 100% | 2021-06-01
2021-05-14 | 2017 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14019 | Dental Clinic Replacement |  |  |  | 2018-07-20 | 2020-07-13 | 2021-07-12 | 92% | 2021-05-04
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | California | United States | 14021 | Ambulatory Care Center Replacement (Area 13) |  |  |  | 2020-01-02 | 2022-05-10 | 2022-05-10 | 62% | 2022-05-10
2021-05-14 | 2017 | Defense Health Agency | Major Military Construction |  | Japan | 14022 | TLAMM-P Medical Warehouse |  | 572000 | PN 14041 | 2017-10-26 | 2019-10-26 | 2020-11-30 | 100% | 2020-11-30
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14041 | Ambulatory Care Center/Dental Clinic Replacement (Hadnot Point) |  |  |  | 2019-10-12 | 2021-10-30 | 2021-10-30 | 59% | 2021-10-30
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | North Carolina | United States | 14042 | Ambulatory Care Center/Dental Clinic Wallace Creek) |  |  |  | 2019-10-12 | 2021-10-30 | 2021-10-30 | 59% | 2021-11-19
2021-05-14 | 2008 | Defense Health Agency | Major Military Construction |  | Germany | 52332 | Medical Clinic Replacement |  |  |  | 2008-08-29 | 2012-05-15 | 2012-07-16 | 100% | 2011-10-08
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 |  |  |  | 2007-10-12 | 2008-06-13 | 2008-06-08 | 100% | 2008-07-23
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-01 |  |  | 2008-08-19 | 2009-02-15 | 2009-02-13 | 100% | 2009-03-03
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-02 |  |  | 2009-10-15 | 2010-04-13 | 2010-04-13 | 100% | 2010-04-13
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-03 |  |  | 2008-12-05 | 2009-07-24 | 2009-07-24 | 100% | 2009-07-24
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-04 |  |  | 2008-07-15 | 2011-05-06 | 2013-10-31 | 100% | 2013-12-06
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 1 | 58395-05 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 2 | 63418 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 3 | 63419 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 4 | 63420-01 |  |  | 2008-07-15 | 2013-10-31 | 2016-12-06 | 100% | 2013-12-06
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 5 | 65324-01 |  |  | 2008-07-15 | 2013-10-31 | 2013-12-06 | 100% | 2013-12-06
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 6 | 71101-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 100% | 2017-05-04
2021-05-14 | 2007 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-01 |  |  | 2015-10-08 | 2017-03-31 | 2017-05-04 | 100% | 2017-05-04
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 7 | 78210-02 |  |  | 2017-10-26 | 2018-10-26 | 2019-05-11 | 98% | 2019-07-03
2021-05-14 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 58395 | USAMRIID Replacement, Incr 8 | 78211 |  |  | 2009-06-01 | 2014-05-31 | 2022-12-31 | 98% | 2021-03-31
2021-05-14 | 2009 | Defense Health Agency | Base Realignment and Closures | Maryland | United States | 64156 | USAMRICD Replacement, Inc 1 |  |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 |  |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 1 | 65731-01 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180 |  |  | 2009-08-19 | 2010-08-08 | 2010-08-31 | 100% | 2010-08-31
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-01 |  |  | 2010-10-01 | 2011-09-30 | 2011-09-30 | 100% | 2011-10-01
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 2 | 67180-02 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2014-11-01
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 3 | 67181 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | Maryland | United States | 65731 | USAMRICD Replacement, Inc 4 | 67182 |  |  | 2010-03-15 | 2013-06-01 | 2015-06-10 | 99% | 2015-06-10
2021-05-14 | 2011 | Defense Health Agency | Major Military Construction |  | Germany | 66588 | Health Clinic Add/Alt |  |  |  | 2013-04-08 | 2016-05-30 | 2017-05-03 | 100% | 2017-05-10
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Texas | United States | 67402 | Blood Processing Center |  |  |  | 2020-07-02 | 2022-04-03 | 2022-04-03 | 23% | 2022-04-03
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) |  | 92680000 | PN 76558 | 2012-05-30 | 2015-03-16 | 2018-03-01 | 100% | 2017-05-31
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) | 70354-01 |  |  | 2017-10-11 | 2018-05-01 | 2018-08-14 | 100% | 2018-08-14
2021-05-14 | 2009 | Defense Health Agency | Major Military Construction | California | United States | 70354 | Hospital Replacement (Supplemental) | 70354-02 |  |  | 2017-11-09 | 2018-12-31 | 2019-08-19 | 100% | 2019-03-22
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | South Carolina | United States | 71317 | Medical Clinic Replacement |  | 4000000 | PN 80306 | 2013-12-06 | 2016-12-30 | 2019-02-15 | 100% | 2016-12-02
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | North Carolina | United States | 71325 | Medical Clinic Replacement |  |  |  | 2013-10-24 | 2016-10-23 | 2018-06-01 | 99% | 2018-06-08
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 71408 | Dental Clinic Replacement |  | 312000 | PN 71503 | 2013-03-01 | 2016-12-06 | 2019-02-15 | 100% | 2019-01-03
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic |  | 8300000 | PN 72754 | 2012-09-01 | 2014-09-09 | 2016-01-31 | 100% | 2016-04-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction | Mississippi | United States | 71503 | Branch Health Clinic | 71503-01 |  |  | 2016-08-25 | 2017-12-25 | 2019-05-10 | 100% | 2018-07-31
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 71507 | Branch Health Clinic Replacement |  | 10692000 | PN 72722 PN 80306 PN 72738 PN 72419 | 2014-04-30 | 2015-10-15 | 2017-02-08 | 100% | 2017-12-04
2021-05-14 | 2017 | Defense Health Agency | Major Military Construction | Maine | United States | 71509 | Medical/Dental Clinic Replacement |  |  |  | 2019-02-01 | 2021-01-24 | 2021-06-07 | 87% | 2021-05-31
2020-01-13 | 2016 | Defense Health Agency | Major Military Construction | Ohio | United States | 71642 | Satellite Pharmacy Replacement |  |  |  | 2016-10-14 | 2019-01-12 | 2018-11-13 | 99% | 2018-11-13
2021-02-14 | 2015 | Defense Health Agency | Major Military Construction | Colorado | United States | 72414 | Dental Clinic Replacement |  | 4861000 | PN 81407 PN 89838 | 2015-11-03 | 2017-10-23 | 2018-10-23 | 100% | 2018-10-23
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction |  | Korea, South | 72419 | Hospital Addition/Alteration |  |  |  | 2013-09-26 | 2017-08-08 | 2020-06-20 | 100% | 2019-10-31
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 |  |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 72251 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-01 |  |  | 2011-11-02 | 2013-08-13 | 2013-10-12 | 100% | 2013-10-12
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-02 |  |  | 2011-08-23 | 2012-07-05 | 2012-12-31 | 100% | 2012-12-31
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-03 |  |  | 2012-08-28 | 2013-06-19 | 2013-10-17 | 100% | 2013-10-17
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-04 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-05 |  |  | 2012-09-04 | 2014-01-04 | 2015-09-16 | 100% | 2015-09-16
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 1 | 72481-06 |  |  | 2011-08-25 | 2011-11-01 | 2011-11-01 | 100% | 2011-11-01
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 3 | 72786 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 98% | 2020-02-01
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-01 |  |  | 2013-10-21 | 2014-10-24 | 2014-10-24 | 99% | 2014-11-24
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 4 | 76558-02 |  |  | 2014-07-30 | 2015-08-27 | 2015-11-30 | 100% | 2015-11-30
2017-10-11 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 2 | 77251 |  |  | 2013-05-29 | 2016-11-26 | 2020-01-31 | 78% | 2018-09-03
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 5 | 77293 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 6 | 81407 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2021-05-14 | 2010 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Fort Bliss Hospital Repl, Incr 7 | 81408 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Texas | United States | 72481 | Hospital Replacement, Increment 8 | 91301 |  |  | 2013-05-29 | 2016-11-26 | 2020-02-29 | 99% | 2020-02-29
2021-05-14 | 2017 | Defense Health Agency | Major Military Construction | Texas | United States | 72738 | Medical/Dental Clinic Replacement |  |  |  | 2017-10-26 | 2020-10-31 | 2021-07-30 | 97% | 2021-07-30
2021-05-14 | 2021 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center |  |  |  | 2021-09-07 | 2022-06-07 | 2022-06-07 | 2% | 2022-07-07
2021-05-14 | 2020 | Defense Health Agency | Major Military Construction |  | Germany | 72742 | Ambulatory Care Center |  |  |  | 2021-05-11 | 2021-08-26 | 2021-08-26 | 1% | 2021-09-09
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction | Texas | United States | 72754 | Ambulatory Care Center Phase 3, Inc 2 | 80793 |  |  | 2012-11-01 | 2014-07-29 | 2016-09-02 | 100% | 2016-09-02
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | California | United States | 72808 | Medical Clinic Replacement |  | 1765000 | PN 80309 PN 72292 | 2014-02-28 | 2015-03-16 | 2017-04-28 | 100% | 2016-06-23
2020-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 6 |  |  |  | 2014-01-13 | 2025-12-30 | 2025-12-30 | 7% | 2025-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 7 | 14043 |  |  | 2021-10-30 | 2025-12-30 | 2026-06-30 | 1% | 2026-06-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 72661 |  |  | 2016-02-28 | 2016-04-30 | 2017-04-30 | 100% | 2017-02-28
2021-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72661, 72662-02 |  |  | 2018-09-07 | 2021-01-30 | 2021-04-30 | 94% | 2021-04-30
2021-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 72661, 76007-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-12-30 | 100% | 2018-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 72661-01 |  |  | 2017-07-30 | 2021-03-31 | 2021-09-30 | 99% | 2021-07-30
2017-11-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72661-02 |  |  | 2017-12-15 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2017-09-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 72661-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-12-30 | 12% | 2018-12-30
2017-06-30 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72661-2 |  |  | 2017-12-15 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72662 |  |  | 2018-08-30 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 72662-01 |  |  | 2021-09-30 | 2024-06-30 | 2024-06-30 | 1% | 2024-06-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72662-02 |  |  | 2018-09-07 | 2021-01-30 | 2021-07-30 | 99% | 2021-04-30
2017-09-13 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 and Incr 3 | 72662-2 |  |  | 2017-12-15 | 2019-04-30 | 2020-09-30 | 1% | 2020-09-30
2021-02-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 6 | 76007, 81412 |  |  | 2014-01-13 | 2025-12-30 | 2026-06-30 | 7% | 2025-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-01 |  |  | 2014-01-20 | 2014-04-04 | 2014-04-04 | 100% | 2014-04-04
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-02 |  |  | 2014-06-16 | 2014-10-29 | 2015-01-21 | 100% | 2015-01-21
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-03 |  |  | 2015-04-20 | 2016-04-30 | 2017-07-30 | 100% | 2016-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-04 |  |  | 2016-06-15 | 2016-12-15 | 2017-12-15 | 100% | 2018-01-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-05 |  |  | 2014-08-22 | 2015-03-30 | 2015-05-01 | 100% | 2015-05-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-06 |  |  | 2014-10-08 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-07 |  |  | 2014-08-11 | 2014-10-16 | 2014-10-16 | 100% | 2014-10-16
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-08 |  |  | 2016-08-15 | 2016-10-30 | 2016-12-30 | 100% | 2016-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-09 |  |  | 2016-11-30 | 2020-03-30 | 2020-03-30 | 100% | 2020-03-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1, Incr 6 | 76007-10 |  |  | 2014-12-10 | 2025-12-30 | 2026-06-30 | 10% | 2025-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 2 | 76007-11 |  |  | 2020-12-30 | 2025-12-30 | 2026-06-30 | 1% | 2025-12-30
2017-06-30 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-12 |  |  | 2017-07-30 | 2020-12-30 | 2020-12-30 | 1% | 2020-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 | 76007-13 |  |  | 2014-10-23 | 2014-12-31 | 2014-12-31 | 100% | 2014-12-31
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 through Incr 8 | 76007-14 |  |  | 2015-03-30 | 2025-12-30 | 2026-06-30 | 2% | 2025-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 2 | 76007-15 |  |  | 2016-09-26 | 2018-07-30 | 2018-12-30 | 100% | 2018-12-30
2020-08-12 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 4-8 | 76872 |  |  | 2020-11-30 | 2024-06-30 | 2025-12-30 | 1% | 2025-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 1 and Incr 6 | 81412 |  |  | 2014-01-13 | 2025-12-30 | 2026-06-30 | 7% | 2025-12-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 3 | 81412-02 |  |  | 2023-07-01 | 2026-06-30 | 2026-06-30 | 1% | 2026-06-30
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement, Incr 8 | 90921 |  |  | 2023-09-01 | 2025-06-30 | 2025-06-30 | 1% | 2023-09-01
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction |  | Germany | 76007 | Medical Center Replacement Incr 2-9 | 95984 |  |  | 2021-10-30 | 2025-12-30 | 2026-06-30 | 1% | 2026-06-30
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Georgia | United States | 76934 | Blood Donor Center Replacement |  |  |  | 2019-03-12 | 2020-09-02 | 2021-03-14 | 88% | 2021-06-12
2021-05-14 | 2014 | Defense Health Agency | Major Military Construction | Maryland | United States | 77000 | Public Health Command Laboratory Replacement |  | 327000 | PN 81436 | 2015-09-08 | 2019-02-19 | 2021-12-31 | 98% | 2021-08-31
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 77140 | Blood Processing Center Replacement |  |  |  | 2019-03-26 | 2020-09-16 | 2021-02-15 | 99% | 2021-02-12
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 1 |  | 150000 | PN 71408 | 2013-03-01 | 2016-12-06 | 2021-08-31 | 99% | 2017-06-20
2021-05-14 | 2012 | Defense Health Agency | Major Military Construction | Maryland | United States | 77154 | Ambulatory Care Center, Inc 2 | 81291 |  |  | 2013-03-01 | 2016-12-06 | 2021-08-31 | 99% | 2017-06-20
2021-05-14 | 2016 | Defense Health Agency | Major Military Construction |  | Germany | 77986 | Dental/ Medical Clinic Addition |  | 536000 | PN 67402 | 2016-12-14 | 2019-06-04 | 2022-02-02 | 85% | 2022-03-02
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Colorado | United States | 77987 | Medical/Dental Clinic Addition/Alteration |  | 2110000 | PN 77140 PN 76934 | 2018-10-23 | 2021-06-17 | 2022-07-14 | 49% | 2021-08-16
2021-05-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 78150 | Medical Clinic Replacement |  | 41463000 | PN 81430 PN 67402 PN 86557 | 2016-11-14 | 2018-12-21 | 2020-08-31 | 100% | 2020-07-31
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities |  |  |  | 2013-10-15 | 2013-12-13 | 2014-03-25 | 100% | 2014-04-04
2021-05-14 | 2013 | Defense Health Agency | Major Military Construction | Maryland | United States | 80306 | Temporary Facilities | 80306-01 |  |  | 2018-11-07 | 2017-12-10 | 2018-08-31 | 100% | 2018-11-07
2021-05-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 |  |  |  | 2016-06-16 | 2017-12-08 | 2019-03-29 | 100% | 2019-04-19
2021-05-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 | 80412-01 | 2000000 | PN 86953 | 2018-02-28 | 2020-05-21 | 2020-11-20 | 99% | 2021-02-21
2021-05-14 | 2016 | Defense Health Agency | Major Military Construction | Hawaii | United States | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 | 80412-02 |  |  | 2020-10-19 | 2022-05-02 | 2022-05-02 | 1% | 2022-06-01
2021-05-14 | 2017 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 1 |  |  |  | 2017-12-22 | 2019-05-10 | 2021-04-30 | 99% | 2021-03-17
2021-05-14 | 2020 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 4 | 14044 |  |  | 2020-07-01 | 2026-03-01 | 2027-01-28 | 10% | 2027-05-01
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 2 | 81420 |  |  | 2020-07-01 | 2026-03-01 | 2027-01-28 | 10% | 2026-03-01
2021-05-14 | 2020 | Defense Health Agency | Major Military Construction | Maryland | United States | 80906 | Medical Center Add/Alt, Inc 3 | 85667 |  |  | 2020-07-01 | 2026-03-01 | 2027-01-28 | 10% | 2027-05-01
2021-05-14 | 2016 | Defense Health Agency | Major Military Construction | Texas | United States | 81422 | Lackland Ambulatory Care Center Phase 4 |  | 2000000 | PN 78210 | 2018-10-24 | 2021-04-01 | 2021-11-04 | 43% | 2021-05-07
2021-04-13 | 2015 | Defense Health Agency | Major Military Construction | Texas | United States | 81423 | Medical Clinic Replacement (Reid Clinic) |  |  |  | 2015-09-28 | 2018-09-27 | 2018-11-10 | 100% | 2018-06-10
2021-05-14 | 2015 | Defense Health Agency | Major Military Construction | Virginia | United States | 81430 | Hospital Add/CUP Replacement |  |  |  | 2019-06-01 | 2021-03-18 | 2021-08-18 | 63% | 2021-06-30
2021-05-14 | 2014 | Defense Health Agency | Major Military Construction |  | Bahrain | 81436 | Medical/Dental Clinic Replacement |  | 4000000 | PN 80904 PN 78211 | 2016-04-20 | 2019-04-20 | 2020-01-20 | 99% | 2019-12-30
2019-06-12 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | North Carolina | United States | 81631 | NiCOE Satellite, Infrastructure Support |  |  |  | 2014-06-30 | 2016-02-01 | 2018-06-06 | 98% | 2016-03-31
2021-05-14 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | Delaware | United States | 86204 | Armed Forces Medical Examiner Medical Warehouse Addition/Alteration |  |  |  | 2021-01-07 | 2022-02-03 | 2022-02-03 | 5% | 2022-06-14
2021-05-14 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | Colorado | United States | 86943 | NiCOE Satellite, Infrastructure Support |  |  |  | 2019-12-03 | 2021-06-15 | 2022-04-22 | 70% | 2022-02-25
2021-05-14 | 2016 | Defense Health Agency | Major Military Construction | Kentucky | United States | 86953 | Medical Clinic |  | 2000000 | PN 78211 | 2017-04-13 | 2021-05-07 | 2021-08-25 | 93% | 2021-11-16
2017-11-14 | 2016 | Defense Health Agency | Major Military Construction | Kentucky | United States | 86953 | Medical Clinic | 86953-01 |  |  | 2017-04-13 | 2021-05-16 | 2021-05-16 | 6% | 2021-11-18
2021-05-14 | 2018 | Defense Health Agency | Unspecified Minor Military Construction |  | Japan | 87208 | Medical Clinic Addition/Alteration, Building 704 |  |  |  | 2019-05-29 | 2020-08-21 | 2021-01-30 | 98% | 2020-12-15
2021-05-14 | 2019 | Defense Health Agency | Major Military Construction | North Carolina | United States | 89838 | Ambulatory Care CTR/Dental Clinic Replacement |  |  |  | 2019-09-30 | 2021-10-30 | 2022-07-05 | 17% | 2022-07-05
2021-05-14 | 2019 | Defense Health Agency | Major Military Construction | South Carolina | United States | 89902 | Consolidated Storage and Distribution Center |  |  |  | 2020-08-18 | 2022-09-03 | 2022-09-03 | 1% | 2022-09-03
2021-05-14 | 2020 | Defense Health Agency | Major Military Construction | California | United States | 89906 | Ambulatory Care Center Replacement (Area 21) |  |  |  | 2020-11-30 | 2022-10-30 | 2022-10-30 | 8% | 2022-10-30
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Phase 1 & Phase 2 |  |  |  | 2019-10-14 | 2023-10-13 | 2023-10-13 | 38% | 2023-10-13
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Phase 1 & Phase 2 | 77168 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-13 | 38% | 2023-10-13
2021-05-14 | 2018 | Defense Health Agency | Major Military Construction | Missouri | United States | 91884 | Hospital Replacement, Phase 1 & Phase 2 | 94335 |  |  | 2019-10-14 | 2023-10-13 | 2023-10-13 | 38% | 2023-10-13
2021-05-14 | 2019 | Defense Health Agency | Major Military Construction | South Carolina | United States | 93298 | High Altitude Airdrop Mission Support (HAAMS) |  |  |  | 2020-11-30 | 2022-06-30 | 2022-06-30 | 13% | 2022-06-30
2021-05-14 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | Florida | United States | 93775 | NiCOE Satellite, Infrastructure Support |  |  |  | 2019-03-25 | 2020-03-24 | 2020-07-22 | 100% | 2020-08-26
2021-05-28 | 2013 | Defense Information Systems Agency | Major Military Construction |  | Germany | 13DISA01 | DISA Europe Facility Upgrade |  |  |  | 2015-08-19 | 2016-12-31 | 2020-12-31 | 10%
2021-05-28 | 2014 | Defense Information Systems Agency | Major Military Construction | Hawaii | United States | 14DISA01 | DISA Pacific Facility Upgrade |  |  |  | 2018-01-11 | 2018-12-31 | 2020-10-31 | 97%
2012-05-28 | 2015 | Defense Information Systems Agency | Major Military Construction |  | Australia | 15DISA02 | Combined Communications Gateway Geraldton (DoD Teleport Geraldton) |  |  |  | 2018-10-01 | 2019-03-31 | 2020-03-11 | 100%
2021-05-28 | 2013 | Defense Information Systems Agency | Major Military Construction | Illinois | United States | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  |  |  | 2014-03-01 | 2015-12-30 | 2016-03-11 | 100%
2021-06-02 | 2014 | DoD Education Activity | Major Military Construction | Virginia | United States | AM00021 | REPLACE QUANTICO MIDDLE/HIGH SCHOOL |  |  |  | 2017-12-04 | 2020-01-09 | 2020-10-13 | 49%
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00031 | Pope Holbrook Elementary School |  |  |  | 2015-02-11 | 2017-02-10 | 2017-07-21 | 99% | 2017-10-31
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction | New York | United States | AM00033 | USMA - REPLACE WEST POINT ELEMENTARY SCHOOL (PN AM00033) |  |  |  | 2017-03-21 | 2020-03-05 | 2021-04-23 | 99% | 2020-01-06
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction | South Carolina | United States | AM00035 | Repl Pierce Terrace Elementary School |  |  |  | 2017-04-26 | 2019-04-26 | 2019-08-15 | 98% | 2019-08-15
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction | Massachusetts | United States | AM00046 | Design and Construct new Primary School at Hanscom | 246 |  |  | 2017-03-23 | 2019-09-09 | 2019-10-16 | 99% | 2019-08-16
2021-06-01 | 2017 | DoD Education Activity | Major Military Construction | Delaware | United States | AM00047 | AM00047 FY17 WELCH ES - DOVER AIR BASE MS AT DOVER AFB |  |  |  | 2019-03-30 | 2021-12-24 | 2022-07-08 | 43%
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School |  | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2021-02-09 | 99%
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 8 | 4286000 | PA00025 | 2016-10-20 | 2020-06-10 | 2021-02-09 | 99%
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00048 | AM00048 Ft Rucker Elementary and Primary School | 9 |  |  | 2016-10-20 | 2020-06-10 | 2021-02-09 | 99%
2021-05-02 | 2014 | DoD Education Activity | Major Military Construction | Georgia | United States | AM00050 | White Elementary School Replacement |  |  |  | 2014-12-16 | 2016-10-31 | 2018-06-09 | 100% | 2018-06-08
2021-04-30 | 2015 | DoD Education Activity | Major Military Construction | North Carolina | United States | AM00051 | LEJEUNE HIGH SCHOOL ADDITION/RENOVATION |  |  |  | 2017-04-12 | 2020-03-28 | 2021-01-15 | 100%
2021-06-02 | 2015 | DoD Education Activity | Major Military Construction |  | United States | AM00103 | Consolidate/Replace W.T. Sampson Elementary School |  |  |  | 2016-07-01 | 2018-11-26 | 2020-09-04 | 98%
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00110 | Replace/Renovate Maxwell ES/MS |  |  |  | 2017-04-12 | 2020-05-28 | 2021-01-23 | 87%
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction | Alabama | United States | AM00110 | Replace/Renovate Maxwell ES/MS | 27 |  |  | 2017-04-12 | 2020-05-28 | 2021-01-23 | 87%
2021-06-02 | 2016 | DoD Education Activity | Major Military Construction |  | Spain | AM00115 | Rota Elementary and High School Additions |  |  |  | 2016-07-20 | 2019-03-27 | 2020-04-27 | 92%
2021-06-01 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School |  |  |  | 2017-01-09 | 2019-05-08 | 2019-07-01 | 97% | 2019-10-31
2021-06-01 | 2012 | DoD Education Activity | Major Military Construction |  | Germany | EU00031 | FY12 DoDEA-E EU00031 Construct Bitburg (Spangdahlem) Middle/High School | 89 |  |  | 2017-01-09 | 2019-05-08 | 2019-07-01 | 97% | 2019-10-31
2021-06-01 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School |  |  |  | 2016-09-12 | 2018-12-24 | 2019-03-15 | 97% | 2019-08-22
2021-06-01 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00034 | Replace Vogelweh Elementary School | 45 |  |  | 2016-09-12 | 2018-12-24 | 2019-03-15 | 97% | 2019-08-22
2021-05-02 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School |  |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 92%
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 1 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 92% | 2021-05-12
2021-05-02 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 2 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 92%
2021-05-02 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 3 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 92%
2021-05-02 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 4 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 92%
2021-05-02 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 5 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 92%
2021-05-02 | 2013 | DoD Education Activity | Major Military Construction |  | Germany | EU00037 | Replace Ramstein High School | 6 |  |  | 2018-01-08 | 2021-03-29 | 2021-03-29 | 92%
2021-06-01 | 2017 | DoD Education Activity | Major Military Construction |  | Germany | EU00039 | Replace Sembach Middle/High School |  |  |  | 2019-07-08 | 2022-05-27 | 2022-05-27 | 0%
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00040 | Kaiserslautern Elementary School Replacement |  |  |  | 2017-06-30 | 2020-01-12 | 2020-06-28 | 91% | 2021-03-26
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00049 | Replace Hainerberg Elementary School |  |  |  | 2018-07-09 | 2021-07-23 | 2021-07-23 | 84% | 2021-04-23
2021-05-02 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00051 | FY16 DoDEA-E EU00051 Replace Patch Elementary School |  |  |  | 2019-01-23 | 2021-01-23 | 2021-01-23 | 49%
2021-05-02 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00051 | FY16 DoDEA-E EU00051 Replace Patch Elementary School | 50 |  |  | 2019-01-23 | 2021-01-23 | 2021-01-23 | 49%
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00051 | FY16 DoDEA-E EU00051 Replace Patch Elementary School | 51 |  |  | 2019-01-23 | 2021-01-23 | 2021-01-23 | 59%
2021-06-01 | 2015 | DoD Education Activity | Major Military Construction |  | Belgium | EU00064 | Replace Brussels Elementary/ High School |  |  |  | 2017-10-25 | 2020-10-24 | 2020-10-24 | 25%
2021-06-01 | 2016 | DoD Education Activity | Major Military Construction |  | Germany | EU00068 | Replace Grafenwoehr |  |  |  | 2018-09-12 | 2021-03-16 | 2021-06-08 | 78%
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00072 | Replace Wiesbaden Middle School |  |  |  | 2016-04-21 | 2019-04-19 | 2019-04-19 | 95% | 2018-07-26
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00072 | Replace Wiesbaden Middle School | 7 |  |  | 2016-04-21 | 2019-04-19 | 2019-04-19 | 95% | 2018-07-26
2021-06-01 | 2014 | DoD Education Activity | Major Military Construction |  | Germany | EU00072 | Replace Wiesbaden Middle School | 720 |  |  | 2016-04-21 | 2019-04-19 | 2019-04-19 | 95% | 2018-07-26
2021-06-02 | 2018 | DoD Education Activity | Major Military Construction |  | Italy | EU00117 | Vicenza High School Replacement |  |  |  | 2019-09-27 | 2022-01-27 | 2022-12-02 | 37%
2021-06-01 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00017 | Killin Elementary School Replacement/Renovation |  |  |  | 2017-01-11 | 2020-11-17 | 2022-11-23 | 72%
2021-06-01 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00021 | Replace Sasebo Elementary School |  |  |  | 2016-04-04 | 2018-11-03 | 2019-03-14 | 100% | 2019-08-19
2021-06-01 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00022 | E.J King HS Addition/ Renovate |  |  |  | 2019-08-21 | 2022-08-05 | 2022-08-05 | 47%
2021-06-01 | 2015 | DoD Education Activity | Major Military Construction |  | Japan | PA00023 | FY15 DODS PA00023 Renovate Edgren High School, Misawa Air Base, Japan |  |  |  | 2017-02-07 | 2019-05-28 | 2020-01-24 | 97%
2021-06-01 | 2013 | DoD Education Activity | Major Military Construction |  | Japan | PA00028 | FY13 DoDEA PA00028 Zama High School Renovation, Camp Zama, Japan |  |  |  | 2017-08-02 | 2019-07-19 | 2021-07-31 | 96% | 2021-02-25
2021-06-01 | 2017 | DoD Education Activity | Major Military Construction |  | Japan | PA00032 | Replace Kadena ES |  |  |  | 2018-04-02 | 2021-02-15 | 2021-03-10 | 100% | 2021-03-10
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146130F | MOTOR TRANSPORTATION/COMM SHOP REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 3% | 2025-08-12
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146142F | FIRE STATIONS REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 3% | 2025-08-12
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146162F | PMO/H&HS & MWHS-2 HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 7% | 2025-08-12
2021-05-11 | 2015 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146193 | WATER TREATMENT PLANT REPLACEMENT |  |  |  | 2017-01-05 | 2020-02-28 | 2021-11-23 | 95% | 2021-11-23
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146194 | UNMANNED AIRCRAFT SYSTEM FACILITIES |  |  |  | 2016-09-14 | 2018-10-04 | 2019-01-29 | 99% | 2020-01-30
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146199 | AIRCRAFT MAINTENANCE HANGAR - INC 1 |  |  |  | 2020-01-06 | 2022-07-14 | 2023-02-07 | 55% | 2023-02-07
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146222 | AIRFIELD SECURITY IMPROVEMENTS |  |  |  | 2019-05-02 | 2021-06-10 | 2021-06-10 | 80% | 2021-06-10
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146235 | FLIGHTLINE UTILITY MODERNIZATION - INC 1 |  |  |  | 2020-01-06 | 2022-07-14 | 2023-02-07 | 61% | 2023-02-07
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146246F | BT-11 RANGE OPERATIONS CENTER REPLACEMENT |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 1% | 2025-08-12
2021-05-11 | 2020 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M00146249 | MCAS CHERRY POINT PERIMETER SECURITY: SLOCUM/NUGENT |  |  |  | 2021-03-04 | 2022-03-05 | 2022-03-05 | 1% | 2022-03-05
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M00146254F | STATION ACADEMIC FACILITY/AUDITORIUM REPLACE |  |  |  | 2020-08-26 | 2025-08-12 | 2025-08-12 | 3% | 2025-08-12
2021-05-11 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M00146766 | F-35B LIFT SYSTEM REPAIR FACILITY |  |  |  | 2018-10-13 | 2020-01-08 | 2020-04-15 | 96% | 2021-04-01
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M00243312 | PMO FACILITY REPLACEMENT |  |  |  | 2022-02-03 | 2022-02-03 | 2022-02-03 | 1% | 2022-02-03
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263403 | RECRUIT RECONDITIONING CENTER & BARRACKS |  |  |  | 2018-08-14 | 2021-02-28 | 2021-11-03 | 59% | 2021-11-03
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | South Carolina | United States | M00263404 | RANGE IMPROVEMENTS & MODERNIZATION, PHASE 2 |  |  |  | 2019-07-24 | 2021-08-17 | 2021-11-04 | 63% | 2021-11-04
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264542 | TBS FIRE STATION BUILDING 533 REPLACEMENT |  |  |  | 2019-06-13 | 2020-10-30 | 2021-12-31 | 27% | 2022-04-18
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264588 | FULLER ROAD IMPROVEMENTS |  |  |  | 2018-10-13 | 2020-06-06 | 2021-04-09 | 99% | 2021-04-09
2021-05-11 | 2015 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264635 | AMMUNITION SUPPLY POINT EXPANSION |  |  |  | 2016-11-30 | 2018-03-25 | 2020-02-28 | 99% | 2021-05-21
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264677 | TECOM SCHOOLS ACADEMIC INSTRUCTION FACILITY |  |  |  | 2016-04-14 | 2018-01-05 | 2018-10-23 | 97% | 2019-12-02
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264719 | WARGAMING CENTER |  |  |  | 2021-04-05 | 2023-07-05 | 2023-07-05 | 1% | 2023-07-05
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | Virginia | United States | M00264724 | AMMUNITION SUPPLY POINT UPGRADE, PHASE 2 |  |  |  | 2019-08-29 | 2021-01-30 | 2021-07-01 | 94% | 2021-07-01
2021-05-11 | 2020 | Marine Corps Active | Unspecified Minor Military Construction | Virginia | United States | M00264733 | RUNWAY 02 INSTRUMENT LANDING SYSTEM (ILS) |  |  |  | 2020-10-13 | 2021-11-10 | 2021-11-10 | 2% | 2021-11-10
2021-05-11 | 2015 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318861 | FACILITY MODIFICATIONS FOR VMU, MWSD AND CH53E |  |  |  | 2015-09-15 | 2018-08-11 | 2021-02-03 | 98% | 2021-02-03
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318863 | AIRCRAFT MAINTENANCE HANGAR UPGRADES |  |  |  | 2016-10-03 | 2019-04-17 | 2020-02-21 | 67% | 2022-03-01
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318877 | MOKAPU GATE ENTRY CONTROL AT/FP COMPLIANCE |  |  |  | 2020-10-07 | 2022-01-07 | 2022-01-07 | 17% | 2022-03-23
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  |  |  | 2014-10-14 | 2016-12-18 | 2019-10-24 | 96% | 2019-10-28
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318887 | LHD PAD CONVERSIONS MV-22 LANDING PADS |  |  |  | 2019-01-11 | 2020-08-19 | 2021-01-25 | 80% | 2021-03-17
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318902 | AIRFIELD LIGHTING MODERNIZATION |  |  |  | 2016-12-02 | 2019-06-06 | 2021-08-29 | 93% | 2019-11-29
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318907 | MV-22 PARKING APRON/INFRASTRUCTURE |  |  |  | 2015-04-28 | 2017-01-03 | 2020-12-15 | 99% | 2018-06-20
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318908 | MV-22 HANGAR |  |  |  | 2015-04-28 | 2017-01-03 | 2020-12-15 | 100% | 2018-06-20
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318923 | REGIMENTAL CONSOLIDATED COMM/ELEC FACILITY |  |  |  | 2017-09-04 | 2020-03-08 | 2021-04-05 | 97% | 2021-05-04
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | Hawaii | United States | M00318946 | CORROSION CONTROL HANGAR |  |  |  | 2019-06-14 | 2021-09-07 | 2022-08-27 | 24% | 2022-08-27
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681079 | POTABLE WATER DISTRIBUTION IMPROVEMENTS |  |  |  | 2019-12-26 | 2022-05-30 | 2022-05-30 | 45% | 2022-05-30
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M006811090 | 1 MEF CONSOLIDATED INFORMATION CENTER |  |  |  | 2020-10-08 | 2024-01-07 | 2024-01-07 | 1% | 2024-01-07
2021-05-11 | 2021 | Marine Corps Active | Major Military Construction | California | United States | M006811090A | 1 MEF CONSOLIDATED INFORMATION CENTER (INC)
2021-05-11 | 2021 | Marine Corps Active | Major Military Construction | California | United States | M006811130 | 1ST MARDIV OPERATIONS COMPLEX |  |  |  | 2021-03-04 | 2023-05-13 | 2023-05-13 | 1% | 2023-05-13
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M006811310 | AMMUNITION SUPPLY POINT UPGRADE |  |  |  | 2018-10-11 | 2020-10-10 | 2021-10-05 | 39% | 2021-11-30
2021-05-11 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M006811599 | STUART MESA ROAD SAFETY IMPROVEMENT |  |  |  | 2019-03-13 | 2020-02-26 | 2020-02-26 | 79% | 2020-04-16
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006811901 | AAV-ACV MAINTENANCE & WAREHOUSE FACILITY |  |  |  | 2019-05-16 | 2022-06-09 | 2022-12-09 | 42% | 2022-12-09
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | California | United States | M006812000 | 62 AREA MESS HALL AND CONSOLIDATED WAREHOUSE |  |  |  | 2020-12-31 | 2025-02-14 | 2025-02-14 | 1% | 2025-02-14
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681334 | SUPPLY WAREHOUSE SOI - WEST |  |  |  | 2019-09-05 | 2021-08-06 | 2021-10-13 | 73% | 2021-10-13
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006815001 | FULL MOTION TRAINER FACILITY |  |  |  | 2019-04-23 | 2020-10-15 | 2021-06-14 | 70% | 2021-06-14
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M006815002 | ELECTRICAL UPGRADES |  |  |  | 2019-04-08 | 2020-03-30 | 2020-03-20 | 100% | 2020-03-19
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M00681574 | FIRE EMERGENCY RESPONSE STATION |  |  |  | 2019-09-05 | 2021-06-07 | 2021-08-25 | 53% | 2021-08-25
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | California | United States | M00681970 | AMMUNITION SUPPLY POINT FACILITIES PULGAS |  |  |  | 2016-01-13 | 2018-04-27 | 2019-09-14 | 97% | 2021-08-31
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction | South Carolina | United States | M60169464 | AIRCRAFT MAINTENANCE HANGAR |  |  |  | 2017-07-13 | 2020-07-13 | 2021-03-10 | 86% | 2021-08-28
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M62204930 | COMBAT VEHICLE REPAIR FACILITY |  |  |  | 2018-05-02 | 2020-05-02 | 2020-05-17 | 98% | 2020-09-22
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction |  | Japan | M626131005 | VTOL PAD - SOUTH
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction |  | Japan | M626131006 | KC130J ENLISTED AIRCREW TRAINER FACILITY
2021-05-11 | 2017 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626131701 | WHOLEHOUSE REVITALIZATION NORTH SIDE TOWNHOUSES PHASE 2
2021-05-11 | 2020 | Marine Corps Active | Military Family Housing Improvement |  | Japan | M626132001 | WHOLEHOUSE REVITALIZATION MIDRISE 1209 |  |  |  | 2021-02-25 | 2023-07-02 | 2023-07-02 | 1% | 2023-07-02
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M62613604 | SECURITY MODIFICATIONS - CVW5/MAG12 HQ
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974539 | ENLISTED DINING FACILITY & COMMUNITY BLDGS |  |  |  | 2018-07-17 | 2021-07-02 | 2021-10-08 | 90% | 2021-10-08
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974602 | AIRCRAFT MAINT. FACILITIES & APRON (SO. CALA) |  |  |  | 2017-08-10 | 2019-06-30 | 2020-06-22 | 100% | 2020-06-18
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction | Arizona | United States | M62974612 | VMX-22 MAINTENANCE HANGAR |  |  |  | 2019-06-27 | 2022-06-06 | 2023-01-23 | 45% | 2023-01-23
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011199F | CLB HEADQUARTERS FACILITIES REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 1% | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011203F | COURTHOUSE BAY FIRE STATION REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011280 | 2ND RADIO BN COMPLEX PHASE 1 |  |  |  | 2017-06-13 | 2019-06-24 | 2022-04-21 | 74% | 2022-08-18
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011300F | 2D TANK BN/CO HQ AND ARMORY REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 1% | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011312F | MCES APPLIED INSTRUCTION FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011320 | BACHELOR ENLISTED QUARTERS |  |  |  | 2018-10-12 | 2020-10-23 | 2021-10-01 | 69% | 2021-10-01
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011338F | II MEF SIMULATION/TRAINING CENTER REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-05-27 | 1% | 2025-05-27
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011387F | ONSLOW BEACH BRIDGE REPLACEMENT |  |  |  | 2020-08-07 | 2025-03-06 | 2025-03-06 | 15% | 2025-03-06
2021-05-11 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011479 | OUTDOOR INFANTRY IMMERSION TRAINER SITE PREP |  |  |  | 2019-06-28 | 2020-10-26 | 2021-03-28 | 91% | 2021-09-24
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011483 | ACV-AAV MAINTENANCE FACILITY UPGRADES |  |  |  | 2020-10-09 | 2021-09-28 | 2021-09-28 | 1% | 2021-09-30
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011495 | 10TH MARINES HIMARS COMPLEX |  |  |  | 2020-08-27 | 2023-03-05 | 2023-03-05 | 1% | 2023-03-05
2021-05-11 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011498 | WC504 MECHANICAL SYSTEM REPLACEMENT |  |  |  | 2018-11-28 | 2019-11-09 | 2021-07-22 | 91% | 2021-07-22
2021-05-11 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | North Carolina | United States | M670011503 | WC500 MECHANICAL SYSTEM REPLACEMENT |  |  |  | 2018-11-28 | 2019-11-09 | 2021-07-22 | 88% | 2021-07-22
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011505F | RAILROAD TRESTLE REPLACEMENT |  |  |  | 2020-08-07 | 2025-03-06 | 2025-03-06 | 8% | 2025-03-06
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011506F | NCIS FACILITIES REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011507F | WTBN HEADQUARTERS REPLACEMENT |  |  |  | 2020-09-29 | 2024-05-27 | 2024-05-27 | 1% | 2024-05-27
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011509F | 2D MARDIV REGIMENTAL HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 11% | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011512F | MCCSSS LOG OPS SCHOOL REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-05-27 | 1% | 2025-05-27
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011518F | HADNOT POINT FIRE STATION REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011519F | LSSS FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011520F | 1ST BN, 8TH MARINES BN HQ REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 1% | 2024-10-12
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011522F | 22D, 24TH, AND 26TH MEU HEADQUARTERS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 15% | 2024-10-12
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011524F | 2D TRANSPORTATION SUPPORT BN HQS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 3% | 2024-10-12
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011525F | ENVIRONMENTAL MANAGEMENT DIVISION REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 1% | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011527F | LOGCOM CSP WAREHOUSE REPLACEMENT |  |  |  | 2020-09-14 | 2025-05-27 | 2025-05-27 | 1% | 2025-05-27
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011529F | MC ADVISOR BATTALION HQS REPLACEMENT |  |  |  | 2020-08-07 | 2024-10-12 | 2024-10-12 | 1% | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011533F | PMO FACILITY REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800 | II MEF OPERATIONS CENTER REPLACEMENT |  |  |  | 2021-01-05 | 2026-07-23 | 2026-07-23 | 1% | 2026-07-23
2021-05-11 | 2021 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011800A | II MEF OPERATIONS CENTER REPLACEMENT (INC) |  |  |  | 2021-03-16 | 2026-07-23 | 2026-07-23 | 1% | 2026-07-23
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M670011801 | 2ND MARDIV/2ND MLG OPS CENTER REPLACEMENT |  |  |  | 2021-01-05 | 2026-07-23 | 2026-07-23 | 1% | 2026-07-23
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001378F | CH-53K MAINTENANCE HANGAR REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001686 | RADAR AIR TRAFFIC CONTROL FACILITY ADDITION |  |  |  | 2016-10-12 | 2018-04-06 | 2021-04-22 | 95% | 2021-03-30
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001695F | CNATT CLASSROOM BUILDING REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001707F | BACHELOR ENLISTED QUARTERS REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2021-05-11 | 2014 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001726 | REGIONAL COMMUNICATION STATION |  |  |  | 2014-06-13 | 2015-12-20 | 2019-02-01 | 98% | 2018-05-31
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001728F | C-12W AIRCRAFT MAINTENANCE HANGAR REPLACEMENT |  |  |  | 2020-09-14 | 2024-10-12 | 2025-02-18 | 1% | 2025-02-18
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001729 | OPERATIONAL TRAINER FACILITY |  |  |  | 2016-10-12 | 2018-04-06 | 2021-04-22 | 93% | 2021-03-30
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | North Carolina | United States | M67001883F | HADNOT POINT MESS HALL REPLACEMENT |  |  |  | 2020-09-14 | 2024-09-30 | 2025-09-27 | 1% | 2025-09-27
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004947 | WELDING AND BODY REPAIR SHOP FACILITY |  |  |  | 2020-02-14 | 2022-05-04 | 2022-05-04 | 18% | 2022-05-04
2021-05-11 | 2018 | Marine Corps Active | Unspecified Minor Military Construction | Georgia | United States | M67004971 | CONSTRUCT LOGCOM OPEN STORAGE LOT |  |  |  | 2018-03-29 | 2018-11-06 | 2019-07-05 | 92% | 2019-07-10
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004972 | GROUND SOURCE HEAT PUMPS |  |  |  | 2017-04-05 | 2019-01-28 | 2019-02-23 | 99% | 2021-10-01
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | Georgia | United States | M67004977 | COMBAT VEHICLE WAREHOUSE |  |  |  | 2019-03-21 | 2021-04-29 | 2021-05-27 | 98% | 2021-03-02
2021-05-11 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | District Of Columbia | United States | M67029007 | Communications Center for Marine Barracks, Washington, DC |  |  |  | 2017-05-03 | 2018-04-19 | 2020-07-30 | 98% | 2019-12-23
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | California | United States | M673991232 | MICROGRID EXPANSION |  |  |  | 2017-10-10 | 2019-04-19 | 2021-04-23 | 96% | 2021-04-23
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67399192 | POTABLE WATER TREATMENT/BLENDING FACILITY |  |  |  | 2018-10-13 | 2021-09-28 | 2022-05-10 | 61% | 2022-05-10
2021-05-11 | 2015 | Marine Corps Active | Major Military Construction | California | United States | M67399222 | E-LMR SLICE COMMUNICATION TOWERS |  |  |  | 2016-09-14 | 2019-03-04 | 2020-02-14 | 100% | 2020-02-06
2021-05-11 | 2015 | Marine Corps Active | Major Military Construction |  | Japan | M67400213 | HANGAR & RINSE FACILITY MODERNIZATIONS
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction |  | Japan | M67400606 | MILITARY WORKING DOG FACILITIES (CAMP HANSEN) |  |  |  | 2016-09-29 | 2018-03-26 | 2021-11-19 | 100% | 2019-09-03
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction |  | Japan | M67400807 | AIRCRAFT MAINTENANCE COMPLEX
2021-05-11 | 2016 | Marine Corps Active | Unspecified Minor Military Construction | California | United States | M67604132 | ORDNANCE BULD-UP FACILITY |  |  |  | 2016-09-14 | 2017-10-30 | 2017-10-30 | 100% | 2017-12-18
2021-05-11 | 2020 | Marine Corps Active | Major Military Construction | Florida | United States | M67695009 | POLICE STATION AND EOC FACILITY REPLACEMENT |  |  |  | 2020-09-30 | 2022-03-25 | 2022-03-25 | 1% | 2022-03-25
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR - INC 1 |  |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 100% | 2020-06-26
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67865198 | AIRCRAFT MAINTENANCE HANGAR - INC 2 | M67865198A |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 98% | 2020-06-26
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865203 | F-35 F-35 Aircraft Parking Apron |  |  |  | 2018-02-07 | 2020-01-14 | 2020-06-26 | 100% | 2020-06-26
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | California | United States | M67865210 | F-35 SIMULATOR FACILITY |  |  |  | 2018-09-13 | 2020-05-20 | 2021-02-26 | 99% | 2021-01-20
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M67865222 | F-35 VERTICAL LANDING PADS AND TAXIWAY |  |  |  | 2019-03-28 | 2020-09-27 | 2021-02-06 | 91% | 2020-07-28
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | California | United States | M67865238 | AIRFIELD SECURITY IMPROVEMENTS |  |  |  | 2019-03-22 | 2020-04-06 | 2020-04-06 | 47% | 2019-11-25
2021-05-11 | 2017 | Marine Corps Active | Major Military Construction | California | United States | M67865249 | COMMUNICATIONS COMPLEX & INFRASTRUCTURE UPGRADE |  |  |  | 2018-01-01 | 2019-09-24 | 2020-10-01 | 98% | 2020-08-19
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557270 | ACE GYM & DINING |  |  |  | 2019-09-26 | 2022-03-25 | 2022-03-25 | 31% | 2022-03-25
2021-05-11 | 2019 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557295 | ORDNANCE OPS |  |  |  | 2019-09-30 | 2021-12-04 | 2021-12-04 | 61% | 2021-12-04
2021-05-11 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557296 | ORDNANCE OPERATIONS ADMIN |  |  |  | 2021-03-31 | 2023-03-28 | 2023-03-28 | 1% | 2023-03-28
2021-05-11 | 2018 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557601 | AIRCRAFT MAINTENANCE HANGAR #2 |  |  |  | 2018-05-30 | 2020-10-02 | 2021-03-27 | 93% | 2021-08-16
2021-05-11 | 2016 | Marine Corps Active | Major Military Construction | Guam | Guam | N41557715 | LIVE-FIRE TRAINING RANGE COMPLEX (NW FIELD) |  |  |  | 2017-09-07 | 2020-11-26 | 2021-11-08 | 69% | 2021-11-08
2021-05-11 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159311 | CENTRAL FUEL STATION |  |  |  | 2021-03-29 | 2023-08-23 | 2023-08-23 | 1% | 2023-08-23
2021-05-11 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159312 | DISTRIBUTION WAREHOUSE
2021-05-11 | 2021 | Marine Corps Active | Major Military Construction | Guam | Guam | N61159804 | CENTRAL ISSUE FACILITY
2021-05-11 | 2019 | Marine Corps Active | Unspecified Minor Military Construction | Hawaii | United States | N62813216 | ELECTRICAL DISTRIBUTION INTERCONNECT |  |  |  | 2020-02-17 | 2020-12-29 | 2022-01-02 | 7% | 2022-02-02
2021-05-11 | 2018 | Marine Corps Reserve | Major Military Construction | Louisiana | United States | M67861650 | AIRCRAFT APRON, TAXIWAY & SUPPORT FACILITIES |  |  |  | 2019-04-02 | 2020-11-20 | 2020-11-20 | 4% | 2020-11-20
2021-05-11 | 2017 | Marine Corps Reserve | Major Military Construction | Louisiana | United States | M68479135 | ELECTRIC FEEDER DUCTBANK |  |  |  | 2019-02-05 | 2020-01-28 | 2020-10-31 | 88% | 2020-11-04
2021-05-11 | 2016 | Marine Corps Reserve | Major Military Construction | Virginia | United States | N50092152 | RESERVE TRAINING CENTER COMPLEX |  |  |  | 2019-10-14 | 2021-09-14 | 2021-10-05 | 46% | 2021-10-21
2021-05-11 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447091 | HANGAR 1050 ADDITION VMGR-234 PROP SHOP
2021-05-11 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447181 | HEADQUARTERS BUILDING ADDITION
2021-05-11 | 2020 | Marine Corps Reserve | Unspecified Minor Military Construction | Texas | United States | N83447222 | OVERHEAD COVER AT MARINE CORPS RESERVE CENTER, EL PASO |  |  |  | 2020-10-08 | 2021-09-21 | 2021-09-21 | 1% | 2021-12-13
2021-04-30 | 2013 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  |  |  | 2013-07-31 | 2015-08-30 | 2016-05-12 | 99% | 2017-04-13
2021-04-30 | 2014 | Missile Defense Agency | Major Military Construction |  | Romania | 630 | Aegis Ashore Missile Defense System Complex, Incr #2 | 646 |  |  | 2013-07-31 | 2015-08-30 | 2016-05-12 | 99% | 2017-04-13
2021-04-30 | 2014 | Missile Defense Agency | Major Military Construction | Alaska | United States | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  | 164000 | 657 | 2014-07-07 | 2016-01-06 | 2016-01-06 | 100% | 2016-01-06
2021-04-30 | 2016 | Missile Defense Agency | Major Military Construction |  | Poland | 640 | Aegis Ashore Missile Defense System Complex |  |  |  | 2016-03-14 | 2018-05-30 | 2022-07-13 | 92%
2021-04-30 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 653 | MDC Switchgear Facility |  | 379000 | 657 | 2017-08-31 | 2019-08-14 | 2021-07-19 | 92%
2021-04-30 | 2017 | Missile Defense Agency | Major Military Construction | Alaska | United States | 657 | Long Range Discrimination Radar Complex, Phase 1 |  |  |  | 2017-06-05 | 2020-11-27 | 2020-09-29 | 100%
2021-04-30 | 2019 | Missile Defense Agency | Major Military Construction | Alaska | United States | 659 | Long Range Discrimination Radar Complex, Phase 2 |  |  |  | 2019-04-29 | 2021-06-30 | 2021-08-21 | 80%
2021-04-30 | 2017 | Missile Defense Agency | Unspecified Minor Military Construction |  | Israel | 673 | Integrated Electronic Security System (IESS) Installation & Security Infrastructure Upgrades |  |  |  | 2018-08-15 | 2019-05-31 | 2021-04-30 | 99%
2021-04-30 | 2018 | Missile Defense Agency | Major Military Construction | Alaska | United States | 674 | Missile Field #4 |  |  |  | 2018-04-25 | 2021-09-30 | 2022-09-09 | 86%
2021-04-30 | 2021 | Missile Defense Agency | Major Military Construction | Alaska | United States | 680 | Communications Center |  |  |  | 2021-03-22 | 2023-01-31 | 2023-01-31 | 0%
2017-11-15 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | Virginia | United States | 65416 | NGA Headquarters, SCIF, All Phases |  |  |  | 2007-09-06 | 2011-12-22 | 2018-09-03 | 99% | 2011-04-19
2021-04-30 | 2018 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016A | Next NGA West (N2W) Complex, Ph. 1 |  |  |  | 2019-04-23 | 2023-10-19 | 2024-01-02 | 26%
2021-04-30 | 2018 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016A-IPO | IPO Temporary Facility associated with Next NGA West (N2W) Complex, Ph. 1 |  |  |  | 2019-07-10 | 2024-07-08 | 2024-07-08 | 48%
2021-04-30 | 2019 | National Geospatial-Intelligence Agency | Major Military Construction | Missouri | United States | NGA-016B | Next NGA West (N2W) Complex, Ph. 2 |  |  |  | 2019-04-23 | 2023-10-19 | 2024-01-02 | 25%
2020-12-09 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17781 | Tordella Chilled Water Backup Storage |  |  |  | 2010-06-30 | 2011-08-20 | 2012-05-30 | 100% | 2012-05-30
2020-12-09 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17782 | R&E Chilled Water Backup Storage |  |  |  | 2011-11-07 | 2013-07-13 | 2016-02-05 | 100% | 2016-02-05
2020-12-09 | 2011 | National Security Agency | Major Military Construction | Maryland | United States | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 54500000 | Mountainview, South Campus Electrical Utility Plant | 2011-10-04 | 2014-11-30 | 2015-10-31 | 100% | 2014-11-30
2020-12-09 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 37500000 | Due to a Congressional rescission of funds | 2010-09-21 | 2014-04-18 | 2015-11-30 | 100% | 2015-10-12
2020-12-09 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18052 | Power & Cooling Infrastructure Upgrade |  |  |  | 2011-03-31 | 2013-02-01 | 2014-05-14 | 100% | 2014-05-14
2020-12-09 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18053 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-01-31 | 2013-02-01 | 2014-05-31 | 100% | 2014-05-31
2020-12-09 | 2010 | National Security Agency | Major Military Construction |  | United Kingdom | 18054 | Power & Cooling Infrastructure Upgrade |  |  |  | 2012-11-30 | 2013-02-01 | 2014-08-31 | 100% | 2014-08-31
2020-12-09 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II |  |  |  | 2012-05-30 | 2014-01-30 | 2015-01-16 | 100% | 2014-03-03
2020-12-09 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 20489 | MOD II (Phase 2) | 2 |  |  | 2013-11-26 | 2014-02-28 | 2014-04-28 | 100% | 2014-09-30
2020-12-09 | 2009 | National Security Agency | Major Military Construction | Maryland | United States | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  |  |  | 2010-09-21 | 2013-01-17 | 2014-04-18 | 100% | 2013-01-17
2020-12-09 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  |  |  | 2010-09-09 | 2011-09-26 | 2012-06-29 | 100% | 2012-06-29
2020-12-09 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview |  |  |  | 2012-11-02 | 2015-05-03 | 2015-07-28 | 100% | 2015-08-30
2020-12-09 | 2012 | National Security Agency | Major Military Construction | Colorado | United States | 23051 | Mountainview | 2 |  |  | 2013-10-13 | 2014-02-14 | 2015-09-30 | 100% | 2014-04-30
2020-12-09 | 2011 | National Security Agency | Major Military Construction | Georgia | United States | 23994 | Whitelaw Wedge |  |  |  | 2012-07-18 | 2014-01-30 | 2014-12-23 | 100% | 2015-08-28
2020-12-09 | 2012 | National Security Agency | Major Military Construction | Maryland | United States | 24649 | High Performance Computing Center 2 |  |  |  | 2013-03-13 | 2015-09-15 | 2016-02-08 | 100% | 2016-02-08
2020-12-09 | 2010 | National Security Agency | Major Military Construction | Maryland | United States | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  |  |  | 1915-11-09 | 2014-03-07 | 2015-05-04 | 100% | 2014-11-30
2020-12-09 | 2013 | National Security Agency | Major Military Construction | Maryland | United States | 26170 | East Campus Building 1 (ECB1) |  |  |  | 2013-10-24 | 2015-10-11 | 2016-11-30 | 99% | 2020-12-31
2020-12-09 | 2015 | National Security Agency | Major Military Construction | Maryland | United States | 27532 | North Campus Buildings Feeders - Phase 1 |  |  |  | 2016-09-01 | 2018-03-01 | 2019-04-03 | 100% | 2019-04-30
2021-03-31 | 2018 | National Security Agency | Major Military Construction | Hawaii | United States | 30439 | NSAH Kunia Tunnel Entrance |  |  |  | 2020-12-01 | 2020-03-01 | 2021-03-25 | 100% | 2021-03-25
2021-03-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 30583 | East Campus Building 2 (ECB2) |  |  |  | 2016-07-18 | 2020-09-10 | 2022-02-01 | 91% | 2022-02-01
2020-12-09 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 31066 | North Campus Buildings Feeders - Phase 2 |  |  |  | 2016-08-08 | 2018-08-08 | 2018-12-18 | 100% | 2018-12-18
2020-12-09 | 2017 | National Security Agency | Major Military Construction | Maryland | United States | 31067 | North Campus Buildings Feeders - Phase 3 |  |  |  | 2018-01-29 | 2019-01-29 | 2019-05-22 | 100% | 2019-05-22
2020-12-09 | 2016 | National Security Agency | Major Military Construction | Georgia | United States | 31934 | ICECUBE |  |  |  | 2015-09-15 | 2016-12-31 | 2016-12-31 | 100% | 2017-02-28
2021-03-31 | 2019 | National Security Agency | Major Military Construction | Maryland | United States | 32100 | Mission Support Operations Warehouse Facility |  |  |  | 2020-02-27 | 2022-11-17 | 2022-11-17 | 15% | 2022-11-17
2020-12-31 | 2016 | National Security Agency | Major Military Construction | Maryland | United States | 32122 | VCP-1 |  |  |  | 2016-06-23 | 2018-06-08 | 2020-11-30 | 100% | 2021-01-06
2020-12-09 | 2018 | National Security Agency | Major Military Construction |  | United Kingdom | 34490 | RAF Main Gate Rehabilitation
2021-03-31 | 2019 | National Security Agency | Major Military Construction | Maryland | United States | 35168 | NSAW Recapitalization Building 3 |  |  |  | 2019-05-01 | 2023-04-30 | 2023-05-09 | 17% | 2023-05-09
2021-05-11 | 2016 | Navy Active | Major Military Construction | California | United States | M006811220 | RAW WATER PIPELINE PENDLETON TO FALLBROOK |  |  |  | 2016-12-14 | 2019-03-30 | 2019-03-30 | 97% | 2019-10-02
2021-05-11 | 2016 | Navy Active | Major Military Construction |  | Japan | M62613603 | E-2D OPERATIONAL TRAINER COMPLEX |  |  |  | 2019-01-01 | 2020-07-08 | 2021-03-12 | 1% | 2021-03-12
2021-05-11 | 2014 | Navy Active | Major Military Construction | Illinois | United States | N00128714 | UNACCOMPANIED HOUSING |  |  |  | 2018-08-13 | 2020-08-14 | 2020-10-23 | 98% | 2020-10-23
2021-05-11 | 2017 | Navy Active | Major Military Construction | Illinois | United States | N00128714 | UNACCOMPANIED HOUSING | N00128714A |  |  | 2018-08-13 | 2020-08-14 | 2020-10-23 | 100% | 2020-10-23
2021-05-11 | 2020 | Navy Active | Major Military Construction | Connecticut | United States | N00129898 | SSN BERTHING PIER 32 |  |  |  | 2020-10-13 | 2022-10-26 | 2022-10-26 | 1% | 2022-10-26
2021-05-11 | 2016 | Navy Active | Major Military Construction | Florida | United States | N00204723 | A-SCHOOL UNACCOMPANIED HOUSING (CORRY STATION) |  |  |  | 2017-07-12 | 2019-10-16 | 2020-09-20 | 99% | 2021-02-10
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N00207674 | AIRCRAFT COMPONENT FACILITY |  |  |  | 2019-05-31 | 2020-10-13 | 2020-11-13 | 94% | 2021-04-30
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N00207711 | SECURITY FENCE - AGUADA BOUNDARY |  |  |  | 2019-09-27 | 2020-09-14 | 2020-09-14 | 100% | 2020-09-14
2021-05-11 | 2014 | Navy Active | Major Military Construction | Florida | United States | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  |  |  | 2014-08-29 | 2016-02-08 | 2018-01-08 | 100% | 2017-07-28
2021-05-11 | 2019 | Navy Active | Major Military Construction | Florida | United States | N00213720 | AUTEC AUSTERE QUARTERS |  |  |  | 2019-10-10 | 2021-12-13 | 2022-01-07 | 8% | 2022-01-07
2021-05-11 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213731 | FIRE STATION |  |  |  | 2019-10-03 | 2020-11-30 | 2020-09-30 | 50% | 2020-09-30
2021-05-11 | 2018 | Navy Active | Major Military Construction | Florida | United States | N00213741 | NAVY GATEWAY INN & SUITES (NGIS) FACILITY |  |  |  | 2019-10-11 | 2022-01-17 | 2022-08-25 | 40% | 2022-08-25
2021-05-11 | 2018 | Navy Active | Major Military Construction | Texas | United States | N00216450 | CONSOLIDATED SQUADRON OPERATIONS & FLIGHT TRAINING BUILDING |  |  |  | 2018-09-19 | 2021-09-04 | 2022-07-08 | 23% | 2022-07-08
2021-05-11 | 2018 | Navy Active | Major Military Construction | Texas | United States | N00216485 | HAZARDOUS WASTE STORAGE AND TRANSFER FACILITY |  |  |  | 2018-09-05 | 2020-03-14 | 2021-01-30 | 88% | 2021-02-26
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N002450888 | HARBOR DRIVE SWITCHING STATION |  |  |  | 2019-04-11 | 2021-08-18 | 2022-07-07 | 64% | 2022-07-07
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N00245110 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2019-08-26 | 2021-03-23 | 2021-03-23 | 95% | 2021-06-15
2021-05-11 | 2017 | Navy Active | Major Military Construction | California | United States | N00245312 | UPGRADE PIER 10 TO 4160 VOLT |  |  |  | 2017-07-13 | 2018-09-30 | 2018-12-15 | 100% | 2018-12-12
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N00245440 | PIER 8 REPLACEMENT - INC 1 |  |  |  | 2019-06-28 | 2021-10-27 | 2021-10-31 | 99% | 2021-10-31
2021-05-11 | 2021 | Navy Active | Major Military Construction | California | United States | N00245443 | PIER 6 REPLACEMENT
2021-05-11 | 2015 | Navy Active | Major Military Construction | California | United States | N00245800 | STEAM DISTRIBUTION SYSTEM DECENTRALIZATION |  |  |  | 2015-10-01 | 2017-10-01 | 2019-04-10 | 100% | 2019-04-10
2021-05-11 | 2017 | Navy Active | Unspecified Minor Military Construction | California | United States | N002461017 | Upgrades for MV-22 Depot Maintenance Program |  |  |  | 2017-10-12 | 2018-12-12 | 2018-12-12 | 100% | 2018-12-06
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N002461018 | CMV-22B AIRFIELD IMPROVEMENTS |  |  |  | 2019-08-08 | 2022-07-25 | 2022-07-25 | 38% | 2022-07-25
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N002461024 | NAVY V-22 HANGAR |  |  |  | 2020-06-25 | 2023-01-01 | 2023-01-01 | 1% | 2023-03-03
2021-05-11 | 2017 | Navy Active | Major Military Construction | California | United States | N00246947 | COASTAL CAMPUS ENTRY CONTROL POINT |  |  |  | 2017-04-13 | 2018-10-06 | 2020-03-31 | 100% | 2021-04-30
2021-05-11 | 2018 | Navy Active | Major Military Construction | California | United States | N00246988 | UNDERSEA RESCUE COMMAND OPERATIONS BUILDING |  |  |  | 2018-09-13 | 2021-03-22 | 2021-03-22 | 64% | 2022-03-22
2021-05-11 | 2017 | Navy Active | Major Military Construction | California | United States | N00246991 | COASTAL CAMPUS UTILITIES INFRASTRUCTURE |  | 4715000 | N32414547, M62613604 | 2017-04-13 | 2019-04-23 | 2021-04-30 | 97% | 2021-04-30
2021-05-11 | 2017 | Navy Active | Major Military Construction | Washington | United States | N00620240 | TRITON MISSION CONTROL FACILITY |  |  |  | 2017-08-23 | 2020-03-26 | 2021-01-19 | 99% | 2020-07-16
2021-05-11 | 2019 | Navy Active | Major Military Construction | Washington | United States | N00620253 | FLEET SUPPORT FACILITY |  |  |  | 2019-03-25 | 2020-11-28 | 2021-01-31 | 93% | 2021-06-11
2021-05-11 | 2017 | Navy Active | Major Military Construction | Washington | United States | N00620256 | E/A-18G MAINTENANCE HANGAR |  |  |  | 2019-02-13 | 2021-07-19 | 2021-07-19 | 85% | 2021-08-11
2021-05-11 | 2019 | Navy Active | Major Military Construction | Washington | United States | N00620258 | NEXT GENERATION JAMMER FACILITY |  |  |  | 2019-03-12 | 2021-03-08 | 2021-01-29 | 94% | 2021-01-29
2021-05-11 | 2019 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414106 | SUBMARINE PROPULSOR MANUFACTURING SUPPORT FAC |  |  |  | 2019-06-26 | 2022-02-13 | 2022-07-15 | 25% | 2022-07-15
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Pennsylvania | United States | N324141098 | SUBMARINE PROPULSOR MACHINE SHOP STAGING FACILITY |  |  |  | 2019-06-26 | 2022-02-13 | 2022-07-15 | 97% | 2022-07-15
2021-05-11 | 2015 | Navy Active | Major Military Construction | Pennsylvania | United States | N32414547 | OHIO REPLACEMENT POWER & PROPULSION FACILITY |  |  |  | 2015-06-01 | 2017-01-12 | 2021-11-19 | 86% | 2022-01-24
2021-05-11 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N32443257 | SHIP REPAIR TRAINING FACILITY |  |  |  | 2018-10-01 | 2021-06-18 | 2021-08-17 | 79% | 2021-12-31
2021-05-11 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATERFRONT UTILITIES |  |  |  | 2017-12-29 | 2021-04-15 | 2021-06-30 | 98% | 2021-06-30
2021-05-11 | 2017 | Navy Active | Major Military Construction | Virginia | United States | N32443614 | ENERGY - WATER FRONT UTILITIES | N32443614A |  |  | 2017-12-29 | 2021-04-15 | 2021-06-30 | 100% | 2021-06-30
2021-05-11 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N32443653 | DRY DOCK FLOOD PROTECTION IMPROVEMENTS |  |  |  | 2020-09-18 | 2023-06-17 | 2023-06-17 | 1% | 2023-06-17
2021-05-11 | 2019 | Navy Active | Major Military Construction | Maine | United States | N324461074 | EXTEND PORTAL CRANE RAIL |  |  |  | 2019-12-05 | 2021-01-27 | 2022-03-20 | 48% | 2021-12-15
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Maine | United States | N324461088 | ENTRY CONTROL POINT MODERNIZATION |  |  |  | 2019-08-19 | 2020-10-31 | 2021-06-30 | 94% | 2021-06-30
2021-05-11 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446285 | UNACCOMPANIED HOUSING |  |  |  | 2017-07-13 | 2019-05-10 | 2021-01-21 | 99% | 2020-03-31
2021-05-11 | 2018 | Navy Active | Major Military Construction | Maine | United States | N32446293 | PAINT, BLAST AND RUBBER FACILITY |  |  |  | 2019-10-09 | 2022-08-09 | 2022-08-09 | 39% | 2022-08-09
2021-05-11 | 2014 | Navy Active | Major Military Construction | Maine | United States | N32446308 | NCTAMS VLF COMMERCIAL POWER CONNECTION |  | 1104000 | N68436993 | 2016-05-05 | 2018-10-25 | 2018-10-25 | 98% | 2018-10-25
2021-05-11 | 2019 | Navy Active | Major Military Construction | Maine | United States | N32446310 | DRY DOCK #1 SUPERFLOOD BASIN |  |  |  | 2019-12-05 | 2021-01-27 | 2022-03-20 | 73% | 2021-12-15
2021-05-11 | 2017 | Navy Active | Major Military Construction | Maine | United States | N32446371 | UTILITY IMPROVEMENTS FOR NUCLEAR PLATFORMS |  |  |  | 2018-04-13 | 2021-09-14 | 2021-09-14 | 100% | 2021-09-14
2021-05-11 | 2018 | Navy Active | Unspecified Minor Military Construction | Maine | United States | N32446385 | COMMUNICATIONS ANTENNA |  |  |  | 2018-10-04 | 2019-10-08 | 2019-10-08 | 97% | 2019-10-15
2021-05-11 | 2017 | Navy Active | Major Military Construction |  | Djibouti | N3379A223 | OCO: MEDICAL/DENTAL FACILITY |  |  |  | 2018-07-12 | 2020-10-05 | 2021-07-23 | 40% | 2021-07-23
2021-05-11 | 2018 | Navy Active | Major Military Construction |  | Djibouti | N3379A505 | AIRCRAFT PARKING APRON EXPANSION |  |  |  | 2018-11-09 | 2020-06-18 | 2021-01-05 | 49% | 2021-01-05
2021-05-11 | 2021 | Navy Active | Major Military Construction | California | United States | N360423271 | F-35C SIMULATOR FACILITY & ELECTRICAL UPGRADES |  |  |  | 2021-04-08 | 2023-05-03 | 2023-05-03 | 1% | 2023-05-03
2021-05-11 | 2015 | Navy Active | Major Military Construction | Guam | Guam | N41557230 | GSE SHOPS AT NORTH RAMP |  |  |  | 2015-12-01 | 2018-06-19 | 2019-01-29 | 96% | 2019-01-28
2021-05-11 | 2018 | Navy Active | Major Military Construction |  | Japan | N41557250 | MALS FACILITIES |  |  |  | 2018-10-08 | 2021-01-21 | 2021-07-27 | 89% | 2021-07-27
2021-05-11 | 2018 | Navy Active | Major Military Construction | Guam | Guam | N41557260 | CORROSION CONTROL HANGAR |  |  |  | 2018-10-05 | 2020-12-28 | 2021-07-27 | 75% | 2021-07-27
2021-05-11 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N41557635 | MUNICIPAL SOLID WASTE LANDFILL CLOSURE |  |  |  | 2017-08-15 | 2019-02-22 | 2021-07-29 | 73% | 2021-08-05
2021-05-11 | 2017 | Navy Active | Major Military Construction | Guam | Guam | N41557H279 | REPLACE ANDERSEN HOUSING PH I |  |  |  | 2019-10-03 | 2022-07-05 | 2022-07-05 | 31% | 2022-07-05
2021-05-11 | 2018 | Navy Active | Major Military Construction | Guam | Guam | N41557H280 | REPLACE ANDERSEN HOUSING PH II |  |  |  | 2019-10-03 | 2022-07-05 | 2022-07-05 | 13% | 2022-07-05
2021-05-11 | 2019 | Navy Active | Major Military Construction | Guam | Guam | N41557H282 | REPLACE ANDERSEN HOUSING PH III |  |  |  | 2019-10-03 | 2022-07-05 | 2022-07-05 | 11% | 2022-07-05
2021-05-11 | 2015 | Navy Active | Major Military Construction | South Carolina | United States | N42237099 | NUCLEAR POWER OPERATIONAL SUPPORT FACILITY |  |  |  | 2014-09-03 | 2018-06-20 | 2019-03-27 | 93% | 2020-05-13
2021-05-11 | 2017 | Navy Active | Unspecified Minor Military Construction | Georgia | United States | N42237671 | SUBMARINE BRIDGE TRAINER |  |  |  | 2018-01-30 | 2019-08-23 | 2019-11-22 | 99% | 2020-02-12
2021-05-11 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N47608265 | UCLASS RDT&E HANGAR |  |  |  | 2019-02-13 | 2020-09-28 | 2021-06-21 | 91% | 2021-07-25
2021-05-11 | 2017 | Navy Active | Unspecified Minor Military Construction | Maryland | United States | N47608421 | Inert Storage Building Replacement |  |  |  | 2017-10-11 | 2018-10-24 | 2020-06-16 | 96% | 2020-08-14
2021-05-11 | 2016 | Navy Active | Major Military Construction | Maryland | United States | N47608975 | UNACCOMPANIED HOUSING |  |  |  | 2018-04-27 | 2020-02-02 | 2020-07-23 | 98% | 2020-07-23
2021-05-11 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N47608975 | UNACCOMPANIED HOUSING | N47608975A |  |  | 2018-04-27 | 2020-02-02 | 2020-12-29 | 100% | 2020-12-29
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091900 | HANGAR 3 REPLACEMENT, APRON, TAXIWAY & UTILITIES FOR RDT&E |  |  |  | 2020-09-24 | 2023-11-30 | 2023-11-30 | 1% | 2023-11-30
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091901 | INTEGRATION LABORATORY
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091902 | AIR OPERATIONS FACILITY & AIR TRAFFIC CONTROL TOWER
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091903 | MICHELSON MISSION SYSTEMS INTEGRATION LABORATORY |  |  |  | 2020-10-01 | 2022-11-04 | 2022-11-04 | 1% | 2022-11-04
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091907 | AIRCRAFT PARKING APRON IN SUPPORT OF HANGAR 2 REPLACEMENT
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091908 | ADVANCED WARFARE HANGAR
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091914 | STRUCTUAL/AIRCRAFT FIRE AND RESCUE STATION
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091916 | COMMUNITY SUPPORT FACILITIES |  |  |  | 2020-09-17 | 2022-09-19 | 2022-09-19 | 1% | 2022-09-19
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091918 | ORDANCE TEST SUPPORT AND TECHNICAL SERVICES LABORATORY |  |  |  | 2021-03-17 | 2023-05-03 | 2023-05-03 | 1% | 2023-05-03
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N476091924 | ACADEMIC TRAINING BUILDING |  |  |  | 2021-02-05 | 2023-02-06 | 2023-02-06 | 1% | 2023-02-06
2021-05-11 | 2020 | Navy Active | Major Military Construction | California | United States | N47609810 | RUNWAY & TAXIWAY EXTENSION |  |  |  | 2020-07-10 | 2022-04-10 | 2022-04-10 | 17% | 2022-04-14
2021-05-11 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N50092176 | ACU-4 ELECTRICAL UPGRADES |  |  |  | 2018-05-03 | 2019-07-08 | 2019-08-05 | 99% | 2019-05-02
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N60042117 | MISSLE MOTOR MAGAZINES AND U&SI
2021-05-11 | 2020 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N601911026 | AIR INTELLIGENCE SUPPORT FACILITY |  |  |  | 2020-12-25 | 2022-06-10 | 2022-06-10 | 1% | 2022-07-22
2021-05-11 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N60191160 | ISR OPERATIONS FACILITY EXPAN |  |  |  | 2020-02-28 | 2022-03-01 | 2022-07-04 | 1% | 2022-08-18
2021-05-11 | 2014 | Navy Active | Major Military Construction | Virginia | United States | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  |  |  | 2014-09-30 | 2016-10-25 | 2019-03-21 | 94% | 2021-02-05
2021-05-11 | 2017 | Navy Active | Major Military Construction | Florida | United States | N60201154 | TRITON FORWARD OPERATING BASE HANGAR |  |  |  | 2017-07-13 | 2019-09-26 | 2019-12-27 | 100% | 2019-12-05
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60201195 | HEAVY WEATHER MOORINGS AT BRAVO WHARF |  |  |  | 2019-08-30 | 2020-08-29 | 2021-03-31 | 99% | 2020-07-27
2021-05-11 | 2018 | Navy Active | Major Military Construction | Florida | United States | N60201421 | MISSILE MAGAZINES |  |  |  | 2018-08-17 | 2020-08-04 | 2022-06-25 | 17% | 2022-06-25
2021-05-11 | 2016 | Navy Active | Major Military Construction | Florida | United States | N60201424 | LCS MISSION MODULE READINESS CENTER |  |  |  | 2016-07-28 | 2018-02-05 | 2019-02-05 | 100% | 2019-08-06
2021-05-11 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60201426 | LCS SUPPORT FACILITY |  |  |  | 2019-09-27 | 2021-04-02 | 2021-10-07 | 75% | 2022-02-25
2021-05-11 | 2019 | Navy Active | Major Military Construction | Florida | United States | N60201427 | LCS OPERATIONAL TRAINING FACILITY ADDITION |  |  |  | 2019-03-08 | 2021-02-05 | 2021-06-04 | 100% | 2021-04-09
2021-05-11 | 2016 | Navy Active | Major Military Construction | Nevada | United States | N60495111 | NAVOPSPTCEN FALLON |  |  |  | 2017-08-31 | 2019-03-11 | 2020-07-18 | 94% | 2021-02-12
2021-05-11 | 2014 | Navy Active | Major Military Construction | Nevada | United States | N60495393 | WASTEWATER TREATMENT PLANT |  |  |  | 2018-05-03 | 2020-05-08 | 2020-11-30 | 99% | 2020-08-31
2021-05-11 | 2015 | Navy Active | Major Military Construction | Nevada | United States | N60495420 | AIR WING TRAINING FACILITY |  |  |  | 2015-09-30 | 2017-11-24 | 2019-10-31 | 97% | 2020-05-19
2021-05-11 | 2018 | Navy Active | Unspecified Minor Military Construction | Nevada | United States | N60495426 | SECURITY FENCE TO ENCLAVE AIRFIELD |  |  |  | 2019-01-11 | 2019-10-25 | 2019-10-25 | 100% | 2020-05-06
2021-05-11 | 2017 | Navy Active | Major Military Construction | Nevada | United States | N60495440 | AIR WING SIMULATOR FACILITY |  |  |  | 2018-08-20 | 2020-08-25 | 2020-10-17 | 100% | 2020-12-01
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Florida | United States | N60508288 | AHTS TEMPORARY MAINTENANCE HANGAR FOUNDATION |  |  |  | 2020-01-24 | 2021-01-11 | 2022-03-30 | 100% | 2022-03-30
2021-05-11 | 2019 | Navy Active | Major Military Construction |  | Cuba | N60514160 | SOLID WASTE MANAGEMENT FACILITY |  |  |  | 2019-10-03 | 2022-03-18 | 2022-03-18 | 39% | 2022-03-18
2021-05-11 | 2019 | Navy Active | Major Military Construction |  | Cuba | N60514343 | CONSOLIDATED FIRE STATION |  |  |  | 2019-10-04 | 2021-09-20 | 2022-01-01 | 47% | 2022-01-01
2021-05-11 | 2014 | Navy Active | Major Military Construction |  | Japan | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  |  |  | 2014-10-03 | 2020-01-23 | 2020-02-23 | 100% | 2020-02-23
2021-05-11 | 2021 | Navy Active | Military Family Housing Improvement |  | Japan | N610542101 | WHOLE HOUSE REVITALIZATION, IKEGO TOWNHOUSE PH2 |  |  |  | 2021-03-19 | 2024-05-01 | 2024-05-01 | 1% | 2024-05-01
2021-05-11 | 2019 | Navy Active | Major Military Construction |  | Japan | N61056512 | TACTICAL OPERATIONS CENTER
2021-05-11 | 2017 | Navy Active | Major Military Construction | Hawaii | United States | N61064402 | UPGRADE POWER PLANT & ELECTRICAL DIST SYS |  |  |  | 2019-01-09 | 2021-07-13 | 2021-07-13 | 85% | 2021-09-27
2021-05-11 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | N61064416 | PMRF POWER GRID CONSOLIDATION |  |  |  | 2018-09-20 | 2020-05-28 | 2022-02-07 | 70% | 2022-02-07
2021-05-11 | 2014 | Navy Active | Major Military Construction | California | United States | N61065202 | NOSC MORENO VALLEY RESERVE TRAINING CENTER |  |  |  | 2016-09-12 | 2018-06-10 | 2019-12-11 | 100% | 2019-12-11
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N61065224 | CAUSEWAY, BOAT CHANNEL & TURNING BASIN |  |  |  | 2019-07-29 | 2022-10-27 | 2024-06-18 | 47% | 2024-03-18
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N61065241 | MISSILE MAGAZINES |  |  |  | 2019-09-02 | 2021-04-15 | 2021-08-30 | 77% | 2021-08-30
2021-05-11 | 2018 | Navy Active | Major Military Construction | Washington | United States | N61066604 | MISSILE MAGAZINES
2021-05-11 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N61151163 | AGILE CHEMICAL FACILITY PHASE 3/GAP B |  |  |  | 2018-10-13 | 2021-08-14 | 2021-08-14 | 96% | 2021-05-31
2021-05-11 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX, PHASE 2 |  |  |  | 2017-05-11 | 2019-09-06 | 2023-04-09 | 22% | 2023-10-31
2021-05-11 | 2017 | Navy Active | Major Military Construction | Maryland | United States | N61151190 | ADVANCED ENERGETICS RESEARCH LAB COMPLEX PH 2 | N61151190A |  |  | 2017-05-11 | 2019-09-06 | 2023-04-09 | 4% | 2023-10-31
2021-05-11 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61151287 | MISSILE SUPPORT FACILITY |  |  |  | 2015-09-16 | 2017-07-17 | 2019-10-31 | 100% | 2019-10-26
2021-05-11 | 2015 | Navy Active | Major Military Construction | Maryland | United States | N61152621 | CYBER SECURITY STUDIES BUILDING |  |  |  | 2016-04-14 | 2019-09-08 | 2020-05-22 | 99% | 2020-09-04
2021-05-11 | 2020 | Navy Active | Major Military Construction | Guam | Guam | N61755491 | EOD COMPOUND FACILITIES |  |  |  | 2020-08-21 | 2022-12-20 | 2022-12-20 | 1% | 2022-12-20
2021-05-11 | 2016 | Navy Active | Major Military Construction | Guam | Guam | N61755535 | SANITARY SEWER SYSTEM RECAPITALIZATION |  |  |  | 2017-09-04 | 2020-01-03 | 2020-01-03 | 83% | 2021-07-05
2021-05-11 | 2019 | Navy Active | Major Military Construction | Guam | Guam | N61755640 | UNACCOMPANIED ENLISTED HOUSING |  |  |  | 2019-07-09 | 2022-10-07 | 2022-12-24 | 40% | 2023-07-21
2021-05-11 | 2017 | Navy Active | Major Military Construction | Guam | Guam | N61755652 | HARDENING OF GUAM POL INFRASTRUCTURE |  |  |  | 2018-06-06 | 2020-04-03 | 2020-06-10 | 81% | 2021-06-30
2021-05-11 | 2018 | Navy Active | Unspecified Minor Military Construction | Guam | Guam | N61755680 | HARDEN ELECTRICAL CIRCUIT |  |  |  | 2018-10-12 | 2019-09-27 | 2021-05-26 | 82% | 2021-01-07
2021-05-11 | 2017 | Navy Active | Major Military Construction |  | Italy | N62588307 | ERI: P-8A HANGAR UPGRADE |  |  |  | 2019-01-03 | 2021-02-09 | 2021-02-09 | 59% | 2021-04-27
2021-05-11 | 2017 | Navy Active | Major Military Construction |  | Italy | N62588308 | ERI: P-8A AIRCRAFT RINSE RACK |  |  |  | 2019-01-03 | 2021-02-09 | 2021-02-09 | 62% | 2021-04-27
2021-05-11 | 2019 | Navy Active | Major Military Construction |  | Italy | N62588312 | EDI: P-8 BASE IMPROVEMENTS
2021-05-11 | 2019 | Navy Active | Major Military Construction | Mississippi | United States | N62604855 | EXPEDITIONARY COMBAT SKILLS STUDENT BERTHING |  |  |  | 2019-05-29 | 2022-06-30 | 2022-05-13 | 61% | 2022-06-30
2021-05-11 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N62688495 | CHAMBERS FIELD MAGAZINE RECAP PH 1 |  |  |  | 2018-10-12 | 2021-02-04 | 2022-01-05 | 17% | 2022-11-01
2021-05-11 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688610 | ELECTRICAL REPAIRS TO PIERS 2,6,7, AND 11 |  |  |  | 2017-09-14 | 2019-10-25 | 2020-12-30 | 100% | 2020-12-22
2021-05-11 | 2017 | Navy Active | Major Military Construction | Virginia | United States | N62688610 | ELECTRICAL REPAIRS TO PIERS 2,6,7, AND 11 | N62688610A |  |  | 2017-09-14 | 2019-10-25 | 2020-12-30 | 100% | 2020-12-22
2021-05-11 | 2018 | Navy Active | Unspecified Minor Military Construction | Virginia | United States | N62688762 | SUBMARINE UMM ANTENNA MAINTENANCE TOWER |  |  |  | 2018-05-16 | 2019-07-17 | 2021-01-03 | 91% | 2021-01-26
2021-05-11 | 2016 | Navy Active | Major Military Construction | Virginia | United States | N62688913 | COMMUNICATIONS CENTER |  |  |  | 2018-05-07 | 2020-11-01 | 2021-05-09 | 90% | 2022-03-01
2021-05-11 | 2018 | Navy Active | Major Military Construction | Hawaii | United States | N62813013 | COMMUNICATIONS/CRYPTO FAC (WAHIAWA) |  |  |  | 2019-08-09 | 2021-04-26 | 2021-09-25 | 69% | 2021-09-25
2021-05-11 | 2020 | Navy Active | Major Military Construction | Hawaii | United States | N62813033 | MAGAZINE CONSOLIDATION, PHASE 1 |  |  |  | 2020-08-24 | 2022-09-09 | 2022-09-09 | 1% | 2022-09-12
2021-05-11 | 2016 | Navy Active | Major Military Construction | Hawaii | United States | N62813036 | WELDING SCHOOL SHOP CONSOLIDATION |  |  |  | 2016-02-09 | 2018-03-26 | 2021-02-06 | 91% | 2021-05-21
2021-05-11 | 2021 | Navy Active | Major Military Construction | Hawaii | United States | N62813044 | WATERFRONT IMPROVEMENTS WHARVES S8-S10 |  |  |  | 2021-05-14 | 2023-11-12 | 2023-11-12 | 1% | 2023-11-12
2021-05-11 | 2014 | Navy Active | Unspecified Minor Military Construction | Hawaii | United States | N62813058 | ROCKFALL PROTECTION AT RED HILL |  |  |  | 2014-12-08 | 2016-05-18 | 2019-12-31 | 99% | 2019-11-06
2021-05-11 | 2021 | Navy Active | Major Military Construction | Hawaii | United States | N628131006 | WATERFRONT WHARVES S1, S11-13, S20-21 |  |  |  | 2021-05-14 | 2023-11-12 | 2023-11-12 | 1% | 2023-11-12
2021-05-11 | 2019 | Navy Active | Major Military Construction | Hawaii | United States | N62813169 | WATER TRANSMISSION LINE |  |  |  | 2019-04-12 | 2022-01-24 | 2022-08-03 | 55% | 2022-08-03
2021-05-11 | 2014 | Navy Active | Major Military Construction | Hawaii | United States | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  |  |  | 2014-07-14 | 2017-08-03 | 2020-10-06 | 100% | 2020-09-01
2021-05-11 | 2018 | Navy Active | Major Military Construction | Hawaii | United States | N62813704 | SEWER LIFT STATION & RELIEF SEWER LINE |  |  |  | 2019-03-26 | 2021-06-19 | 2021-06-23 | 82% | 2021-07-30
2021-05-11 | 2020 | Navy Active | Major Military Construction |  | Spain | N62863605 | SEAMANSHIP TRAINING FACILITY |  |  |  | 2021-04-06 | 2023-01-17 | 2023-01-17 | 1% | 2023-01-17
2021-05-11 | 2017 | Navy Active | Major Military Construction |  | Spain | N62863621 | COMMUNICATION STATION |  |  |  | 2017-09-14 | 2023-02-13 | 2023-07-07 | 91% | 2023-07-07
2021-05-11 | 2015 | Navy Active | Major Military Construction |  | Spain | N62863712 | SHIP BERTHING POWER UPGRADES |  |  |  | 2015-12-04 | 2018-05-23 | 2022-02-24 | 96% | 2022-02-21
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction |  | Spain | N62863812 | PROVIDE SHIP TO SHORE ELECTRICAL SUBSTATIONS AT PIER #1 |  |  |  | 2020-10-07 | 2022-06-30 | 2022-06-30 | 1% | 2022-06-30
2021-05-11 | 2020 | Navy Active | Major Military Construction |  | Italy | N62995130 | COMMUNICATIONS STATION |  |  |  | 2020-10-13 | 2025-06-05 | 2025-06-05 | 1% | 2025-06-05
2021-05-11 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995407 | TRITON HANGAR AND OPERATION FACILITY |  | 4099000 | N32414547 | 2016-12-06 | 2018-06-28 | 2021-02-26 | 52% | 2021-09-30
2021-05-11 | 2016 | Navy Active | Major Military Construction |  | Italy | N62995655 | P-8A HANGAR AND FLEET SUPPORT FACILITY |  |  |  | 2016-12-06 | 2019-04-23 | 2021-02-26 | 47% | 2021-09-30
2021-05-11 | 2017 | Navy Active | Major Military Construction |  | Italy | N62995737 | UPGRADE ENTRY CONTROL POINT |  |  |  | 2017-03-14 | 2018-08-22 | 2021-01-21 | 100% | 2021-05-03
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction |  | Bahrain | N63005955U | P8A CLEAR WATER RINSE FACILITY
2021-05-11 | 2016 | Navy Active | Major Military Construction |  | Bahrain | N63005976 | MINA SALMAN PIER REPLACEMENT
2021-05-11 | 2017 | Navy Active | Unspecified Minor Military Construction |  | Bahrain | N63005985 | FIRE WATER TANK |  |  |  | 2019-06-28 | 2021-03-25 | 2021-03-25 | 46% | 2021-09-22
2021-05-11 | 2016 | Navy Active | Major Military Construction | California | United States | N63042218 | RTO AND MISSION DEBRIEF FACILITY |  |  |  | 2016-05-24 | 2019-11-03 | 2020-03-13 | 95% | 2020-07-10
2021-05-11 | 2018 | Navy Active | Major Military Construction | California | United States | N63042282 | F/A 18 AVIONICS REPAIR FACILITY REPLACEMENT |  |  |  | 2018-10-03 | 2021-02-24 | 2021-09-03 | 91% | 2021-09-03
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N63042284 | F-35 MAINTENANCE HANGAR |  |  |  | 2019-09-30 | 2021-11-17 | 2021-12-03 | 98% | 2021-12-03
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N63042392 | COMMUNICATIONS LINE OPS TO ADMIN |  |  |  | 2019-08-13 | 2021-05-06 | 2021-05-06 | 100% | 2020-12-28
2021-05-11 | 2018 | Navy Active | Major Military Construction |  | Greece | N66691911 | STRATEGIC AIRCRAFT PARKING APRON EXPANSION |  |  |  | 2018-12-26 | 2021-02-14 | 2021-02-14 | 86% | 2021-05-19
2021-05-11 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436400 | SUBMARINE REFIT MAINT SUPPORT FACILITY |  |  |  | 2018-10-13 | 2021-06-30 | 2022-03-12 | 31% | 2022-03-12
2021-05-11 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436401 | REGIONAL SHIP MAINTENANCE SUPPORT FACILITY |  |  |  | 2017-10-10 | 2020-01-04 | 2021-03-23 | 97% | 2021-06-30
2021-05-11 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436431 | DRY DOCK 6 MODERNIZATION & UTILITY IMPROVE. |  |  |  | 2016-08-25 | 2017-11-14 | 2021-08-06 | 98% | 2021-08-06
2021-05-11 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436438 | NUCLEAR REPAIR FACILITY |  |  |  | 2018-05-07 | 2019-10-30 | 2020-08-14 | 100% | 2020-05-27
2021-05-11 | 2020 | Navy Active | Major Military Construction | Washington | United States | N68436447 | DRY DOCK 4 & PIER 3 MODERNIZATION |  |  |  | 2020-06-22 | 2023-08-02 | 2023-08-02 | 1% | 2023-08-02
2021-05-11 | 2017 | Navy Active | Major Military Construction | Washington | United States | N68436834 | SEAWOLF CLASS SERVICE PIER |  |  |  | 2020-02-17 | 2022-07-04 | 2022-07-04 | 76% | 2022-08-18
2021-05-11 | 2016 | Navy Active | Major Military Construction | Washington | United States | N68436983 | WRA LAND/WATER INTERFACE |  |  |  | 2016-10-05 | 2018-02-13 | 2019-04-21 | 87% | 2020-03-24
2021-05-11 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436990 | EXPLOSIVES HANDLING WHARF #2 - INC 4 | N68436990C | 2728000 | M67399222; N68436993 | 2015-01-22 | 2016-01-09 | 2017-09-30 | 99% | 2016-12-23
2021-05-11 | 2015 | Navy Active | Major Military Construction | Washington | United States | N68436993 | TPS PORT ANGELES FORWARD OPERATING LOCATION |  |  |  | 2016-09-13 | 2018-02-06 | 2019-08-07 | 95% | 2018-09-03
2021-05-11 | 2019 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469001 | MASTER TIME CLOCKS & OPERATIONS FACILITY - INC 1 |  |  |  | 2019-09-30 | 2024-09-15 | 2024-09-15 | 100% | 2025-10-10
2021-05-11 | 2015 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY |  |  |  | 2017-11-16 | 2021-06-16 | 2022-01-20 | 30% | 2022-12-30
2021-05-11 | 2018 | Navy Active | Major Military Construction | District Of Columbia | United States | N68469275 | ELECTRONICS SCIENCE AND TECHNOLOGY LABORATORY | N68469275A |  |  | 2017-11-16 | 2021-06-16 | 2022-01-20 | 98% | 2022-12-30
2021-05-11 | 2020 | Navy Active | Major Military Construction | Virginia | United States | N69212169 | NMC ORDNANCE FACILITIES RECAP |  |  |  | 2021-04-08 | 2023-06-25 | 2023-06-25 | 1% | 2023-06-25
2021-05-11 | 2018 | Navy Active | Major Military Construction | Virginia | United States | N69212995 | BACHELOR ENLISTED QUARTERS |  |  |  | 2019-02-14 | 2021-06-25 | 2021-11-25 | 55% | 2022-03-15
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N69232586 | MISSILE ASSEMBLY BUILDING AND HIGH EXPLOSIVE MAG |  |  |  | 2019-10-10 | 2021-02-15 | 2021-07-01 | 82% | 2021-07-01
2021-05-11 | 2019 | Navy Active | Major Military Construction | California | United States | N69232777 | DIRECTED ENERGY SYSTEMS INTEGRATION LAB |  |  |  | 2019-09-11 | 2021-01-11 | 2021-05-20 | 45% | 2021-09-23
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Texas | United States | N83447084 | CDC STORM SHELTER |  |  |  | 2019-10-01 | 2020-09-20 | 2021-02-25 | 88% | 2021-02-25
2021-05-11 | 2017 | Navy Reserve | Major Military Construction | Louisiana | United States | M68479777 | MARINE CORPS RESERVE CENTER |  |  |  | 2020-02-19 | 2021-08-30 | 2022-04-02 | 26% | 2022-04-02
2021-05-11 | 2015 | Navy Reserve | Unspecified Minor Military Construction | Connecticut | United States | N00129664 | CORIVRON 8 RESERVE HVU DET SUPPORT FACILITIES |  |  |  | 2015-09-08 | 2016-09-08 | 2017-04-21 | 98% | 2017-07-14
2021-05-11 | 2020 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206475 | ENTRY CONTROL FACILITY UPGRADES |  |  |  | 2020-08-27 | 2023-03-06 | 2023-03-06 | 13% | 2023-03-06
2021-05-11 | 2019 | Navy Reserve | Unspecified Minor Military Construction | Louisiana | United States | N00206493 | FLIGHT LINE ACCESS CONTROL AND SECURITY
2021-05-11 | 2017 | Navy Reserve | Major Military Construction | Louisiana | United States | N00206500 | JOINT RESERVE INTELLIGENCE CENTER |  |  |  | 2017-07-13 | 2019-07-27 | 2020-09-03 | 96% | 2020-08-21
2021-05-11 | 2018 | Navy Reserve | Major Military Construction | Georgia | United States | N42237642 | NAVY OPERATIONAL SUPPORT CENTER FORT GORDON |  |  |  | 2018-09-26 | 2020-01-06 | 2021-07-10 | 97% | 2021-07-29
2021-05-11 | 2019 | Navy Reserve | Major Military Construction | Georgia | United States | N42237643 | RESERVE TRAINING CENTER
2021-05-11 | 2019 | Navy Reserve | Major Military Construction | California | United States | N61065160 | RESERVE TRAINING CENTER |  |  |  | 2019-02-07 | 2021-02-07 | 2021-06-01 | 93% | 2021-06-01
2021-05-11 | 2018 | Navy Reserve | Major Military Construction | California | United States | N63042366 | NAVAL OPERATIONAL SUPPORT CENTER LEMOORE |  |  |  | 2019-04-25 | 2021-03-26 | 2021-06-25 | 98% | 2021-02-24
2021-05-11 | 2018 | Navy Reserve | Major Military Construction | Texas | United States | N83447077 | K-C130J EACTS FACILITY |  |  |  | 2018-10-10 | 2019-12-31 | 2020-12-31 | 96% | 2021-03-02
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | Colorado | United States | 47942 | Language Training Facility |  |  |  | 2016-07-08 | 2017-03-01 | 2018-10-10 | 98%
2019-09-30 | 2015 | Special Operations Command | Major Military Construction | Georgia | United States | 57442 | SOF Company Operations Facility |  |  |  | 2017-04-27 | 2018-10-19 | 2019-02-21 | 97%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | Georgia | United States | 61065 | TUAV Maintenance Facility |  |  |  | 2017-09-25 | 2018-11-24 | 2019-08-20 | 99% | 2019-08-05
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | 63850 | SOF Support Battalion Admin Facility |  |  |  | 2018-10-02 | 2020-03-25 | 2021-06-29 | 99%
2019-09-30 | 2019 | Special Operations Command | Major Military Construction | Kentucky | United States | 66813 | SOF Logistics Support Operations Facility |  |  |  | 2019-06-12 | 2020-12-03 | 2021-08-16 | 89%
2019-09-30 | 2019 | Special Operations Command | Major Military Construction | Kentucky | United States | 67039 | MOUT/Aerial Gunnery Range |  |  |  | 2019-06-12 | 2020-12-03 | 2021-05-17 | 98%
2019-09-30 | 2019 | Special Operations Command | Major Military Construction | North Carolina | United States | 69251 | SOF Replace Maze and Tower |  |  |  | 2019-05-20 | 2020-05-20 | 2021-01-26 | 99%
2019-09-30 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 69302 | SOF Battalion Operations Facility |  |  |  | 2017-05-17 | 2019-05-07 | 2021-02-09 | 96%
2019-09-30 | 2013 | Special Operations Command | Major Military Construction | Washington | United States | 69445 | SOF Battalion Operations Facility |  |  |  | 2015-06-30 | 2017-05-25 | 2018-05-18 | 99% | 2018-05-18
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 69552 | Tactical Equipment Maintenance Complex |  |  |  | 2019-03-19 | 2020-11-08 | 2021-11-05 | 75%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 74813 | SOF Parachute Rigging Facility |  |  |  | 2018-07-17 | 2020-01-08 | 2021-07-25 | 95%
2019-09-30 | 2013 | Special Operations Command | Major Military Construction | Colorado | United States | 76367 | SOF Battalion Operations Complex |  |  |  | 2014-09-04 | 2016-07-20 | 2020-06-19 | 100% | 2021-03-23
2019-09-01 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76375 | Civil Affairs Battalion Annexes |  |  |  | 2014-12-01 | 2016-07-23 | 2017-09-11 | 99% | 2017-08-29
2019-09-30 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 76376 | Language and Cultural Center |  |  |  | 2015-01-09 | 2017-06-27 | 2018-01-19 | 99% | 2018-01-19
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 76513 | Special Tactics Facility, Phase 2 |  |  |  | 2017-09-19 | 2019-12-18 | 2021-01-11 | 99%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 76514 | SOF Special Tactics Facility, Ph 3 |  |  |  | 2018-07-02 | 2020-03-23 | 2021-03-30 | 95%
2019-09-30 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | 79437 | SOF Training Command Building |  |  |  | 2017-02-21 | 2019-02-11 | 2021-08-20 | 78%
2019-09-01 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | 79438 | Combat Medic Skills Sustainment Course Bldg |  |  |  | 2014-10-27 | 2016-04-19 | 2016-12-16 | 99% | 2016-12-14
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 79439 | SOF Intelligence Center |  |  |  | 2018-11-14 | 2020-05-07 | 2021-09-27 | 89%
2019-09-30 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | 79440 | SOF BOAT DOCKS |  |  |  | 2015-05-14 | 2016-08-22 | 2018-12-02 | 78%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | 79443 | SOF Human Performance Training Center |  |  |  | 2019-02-26 | 2020-12-27 | 2021-08-31 | 88%
2019-09-30 | 2019 | Special Operations Command | Major Military Construction | Colorado | United States | 79447 | SOF Human Performance Training Center |  |  |  | 2019-06-11 | 2021-05-31 | 2021-11-10 | 42%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | 79453 | Tactical Equipment Maintenance Complex |  |  |  | 2019-03-19 | 2020-11-08 | 2021-12-14 | 57%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | Virginia | United States | 80771 | Battalion Complex |  |  |  | 2019-02-25 | 2020-12-26 | 2021-07-31 | 96%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | 80773 | SOF Battalion Operations Facility |  |  |  | 2017-01-31 | 2019-01-31 | 2019-06-06 | 99%
2020-11-30 | 2019 | Special Operations Command | Major Military Construction | North Carolina | United States | 80774 | SOF SERE Resistance Training Compound |  |  |  | 2020-01-07 | 2021-01-06 | 2022-03-07 | 32%
2020-11-30 | 2019 | Special Operations Command | Major Military Construction |  | United States | 80775 | Battalion Complex Ph 2 |  |  |  | 2020-11-02 | 2022-11-02 | 2023-03-13 | 1%
2020-11-30 | 2020 | Special Operations Command | Major Military Construction |  | United States | 80778 | Battalion Complex Ph 3 |  |  |  | 2020-11-02 | 2022-11-02 | 2023-03-13 | 1%
2021-04-27 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | 81165 | SOF Human Platform-Force Generation Facility |  |  |  | 2020-12-08 | 2023-06-11 | 2023-05-28 | 3%
2019-09-30 | 2018 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | 81894 | SOF Telecom Reliability Facility |  |  |  | 2018-11-27 | 2019-11-27 | 2020-12-29 | 99%
2019-09-01 | 2016 | Special Operations Command | Major Military Construction | Kentucky | United States | 81897 | Company Operations Headquarters |  |  |  | 2017-01-03 | 2018-08-26 | 2019-02-15 | 99%
2019-09-30 | 2019 | Special Operations Command | Major Military Construction | Colorado | United States | 81899 | SOF Mountaineeering Facility |  |  |  | 2019-06-11 | 2021-05-31 | 2021-10-03 | 39%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction |  | Japan | 81903 | Tactical Equipment Maintenance Complex |  |  |  | 2019-04-19 | 2021-04-18 | 2022-01-15 | 33%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | North Carolina | United States | 85958 | SOF Combat Medic Training Facility |  |  |  | 2019-06-18 | 2021-04-28 | 2021-10-18 | 50%
2021-04-27 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | 86021 | SOF Assessmant & Selection Training Compound |  |  |  | 2020-09-09 | 2022-09-09 | 2022-11-08 | 0%
2021-05-24 | 2019 | Special Operations Command | Major Military Construction | Kentucky | United States | 87438 | SOF Multi-Use Hilicopter Training |  |  |  | 2021-01-06 | 2022-05-01 | 2022-07-30 | 0%
2021-04-27 | 2020 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | 87539 | SOF Ops Facility Secure Work Area |  |  |  | 2020-08-06 | 2022-01-28 | 2022-03-29 | 15%
2021-04-27 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | 92594 | SOF Operations Support Facility |  |  |  | 2020-09-09 | 2022-05-08 | 2022-07-07 | 2%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction |  | Japan | AFSOC103002 | Airfield Pavements |  |  |  | 2018-11-01 | 2020-10-21 | 2021-03-23 | 99%
2021-05-24 | 2017 | Special Operations Command | Major Military Construction |  | Japan | AFSOC103010 | Simulator Facilitry |  |  |  | 2021-05-23 | 2023-05-23 | 2023-05-23 | 0%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction |  | Japan | AFSOC103022 | Airfield Apron |  |  |  | 2018-03-20 | 2021-01-26 | 2022-05-21 | 44%
2019-09-30 | 2015 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ063029 | SOF ST SQ OPS Facility |  |  |  | 2019-01-17 | 2021-05-16 | 2022-04-20 | 61%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ103006 | SOF C-130 AGE FACILITY |  |  |  | 2018-11-14 | 2020-01-13 | 2020-01-13 | 61%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | New Mexico | United States | CZQZ133003 | SOF ST Operations Training Facilities |  |  |  | 2019-01-17 | 2021-05-16 | 2021-04-20 | 61%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | Florida | United States | FTEV073010 | SOF Fuel Cell Maintenance Facility |  |  |  | 2016-09-15 | 2018-09-15 | 2021-05-17 | 100% | 2021-05-17
2021-04-27 | 2018 | Special Operations Command | Unspecified Minor Military Construction | Florida | United States | FTEV151114 | SOF Munitions Storage Facility |  |  |  | 2020-12-08 | 2021-12-08 | 2022-03-08 | 15%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153003 | SOF SIMULATOR & FUSELAGE TRAINER FACILITY |  |  |  | 2018-10-31 | 2020-04-23 | 2021-06-15 | 99%
2021-04-27 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153007 | SOF Maintenance Training Facility |  |  |  | 2020-12-02 | 2022-11-22 | 2023-02-20 | 1%
2020-08-10 | 2018 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153008 | SOF Combat Parking Apron (AC-130J) (CAPA) |  |  |  | 2020-04-02 | 2023-03-18 | 2023-06-16 | 41%
2021-04-27 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153009 | SOF AMU and Weapons Hangar Facility |  |  |  | 2021-04-19 | 2024-05-18 | 2024-08-16 | 0%
2020-11-30 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | FTEV153010 | SOF Combined Squadron Operations |  |  |  | 2020-09-09 | 2021-10-20 | 2022-01-18 | 6%
2020-11-30 | 2018 | Special Operations Command | Major Military Construction | Florida | United States | FTFA163001 | Fimulator Facility |  |  |  | 2020-10-06 | 2022-03-30 | 2022-06-28 | 22%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction |  | Japan | LXEZ123484 | Simulator Facility |  |  |  | 2020-01-29 | 2021-07-22 | 2021-09-18 | 39%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | Florida | United States | NVZR143703 | SOF Operations Support Facility |  |  |  | 2016-10-18 | 2019-01-26 | 2019-11-19 | 99%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1219 | SOF Comm / Electronics Maintenance Facility |  |  |  | 2018-01-11 | 2020-01-12 | 2020-04-03 | 55%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1288 | SOF Combat Support Service Facility |  |  |  | 2018-01-11 | 2020-01-12 | 2020-04-03 | 47%
2019-09-30 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1393 | SOF SURVIVAL EVASION RESISTANCE ESCAPE TRAINING FACILITY |  |  |  | 2013-10-03 | 2016-01-18 | 2018-01-31 | 98%
2019-09-30 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1396 | SOF INTEL OPS EXPANSION |  |  |  | 2015-08-31 | 2017-03-09 | 2017-10-27 | 96%
2019-09-30 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P-1410 | SOF EOD Expansion |  |  |  | 2013-10-10 | 2014-09-22 | 2015-06-30 | 99%
2019-09-30 | 2015 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | P-1475 | MARSOC Cultural Assimilation Center |  |  |  | 2018-07-03 | 2019-09-13 | 2019-10-13 | 28%
2019-09-30 | 2016 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | P-1481 | INDIVIDUAL TRAINING COURSE TEAM TRAINING FACILITY |  |  |  | 2018-09-14 | 2019-11-11 | 2020-03-17 | 65%
2019-09-30 | 2016 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P-225 | SOF NSWG-10 UAS SUPPORT FACILITY |  |  |  | 2018-08-17 | 2019-08-30 | 2019-10-22 | 53%
2020-06-12 | 2018 | Special Operations Command | Major Military Construction | Virginia | United States | P-241 | SOF NSWG-4 BOAT SUPPORT FACILITY |  |  |  | 2019-09-26 | 2020-11-18 | 2020-11-18 | 23%
2019-09-30 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P-334 | SOF LOGSU TWO OPERATIONS FACILITY |  |  |  | 2016-02-24 | 2018-07-29 | 2020-01-31 | 90%
2019-09-30 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-776 | SOF LOGSU ONE OPERATIONS FACILITY #1 |  |  |  | 2015-10-14 | 2017-10-23 | 2019-03-07 | 98%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | Virginia | United States | P-777 | SOF APPLIED INSTRUCTION FACILITY |  |  |  | 2018-07-30 | 2020-10-09 | 2020-12-13 | 28%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | Virginia | United States | P-791 | SOF SATEC RANGE EXPANSION |  |  |  | 2018-09-27 | 2021-03-17 | 2021-03-17 | 19%
2020-05-29 | 2018 | Special Operations Command | Major Military Construction | California | United States | P-855 | Basic Training Command |  |  |  | 2019-09-30 | 2022-08-30 | 2022-08-30 | 4%
2019-09-30 | 2013 | Special Operations Command | Major Military Construction | California | United States | P-888 | SOF CLOSE QUARTERS COMBAT AND DYNAMIC SHOOTING FACILITY (LA POSTA) |  |  |  | 2014-10-14 | 2016-09-29 | 2017-11-08 | 89%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-890 | SOF SEAL Team Ops Facility |  |  |  | 2017-10-12 | 2020-03-31 | 2020-03-31 | 75%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | California | United States | P-892 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2018-09-27 | 2021-03-31 | 2021-03-31 | 29%
2019-09-30 | 2015 | Special Operations Command | Major Military Construction | California | United States | P-893 | SOF SUPPORT ACTIVITY OPERATIONS FACILITY #2 |  |  |  | 2015-10-14 | 2018-04-02 | 2019-03-11 | 97%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | Virginia | United States | P-900 | SOF Multi-Purpose Canine Operations Facility |  |  |  | 2019-02-22 | 2020-02-10 | 2020-08-14 | 3%
2020-05-29 | 2019 | Special Operations Command | Major Military Construction | California | United States | P-918 | SOF NSWCEN Close Quarters Combat Facility |  |  |  | 2019-09-26 | 2021-10-09 | 2021-10-28 | 6%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-919 | SOF Special RECON Team One Operations Facility |  |  |  | 2017-04-13 | 2018-10-22 | 2019-07-03 | 97%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | California | United States | P-920 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #2 |  |  |  | 2016-10-04 | 2018-10-13 | 2019-12-27 | 97%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | California | United States | P-921 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #3 |  |  |  | 2018-08-09 | 2021-02-15 | 2021-02-15 | 14%
2020-05-29 | 2019 | Special Operations Command | Major Military Construction | California | United States | P-949 | SOF NSWCEN ATC Applied Instruction Facility |  |  |  | 2019-10-20 | 2022-05-19 | 2022-05-19 | 3%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-952 | SOF Human Performance Training Center |  |  |  | 2017-08-24 | 2019-11-22 | 2019-11-22 | 97%
2019-09-30 | 2018 | Special Operations Command | Major Military Construction | California | United States | P-964 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2018-09-13 | 2021-09-13 | 2021-09-13 | 26%
2019-09-30 | 2017 | Special Operations Command | Major Military Construction | California | United States | P-966 | SOF TRADET One Operations Facility |  |  |  | 2017-10-12 | 2020-04-19 | 2020-04-19 | 65%
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | California | United States | P1119 | SOF COMMUNICATION / ELECTRONICS MAINTENANCE FACILITY |  |  |  | 2015-10-13 | 2016-04-06 | 2016-04-06 | 100% | 2017-06-01
2021-05-11 | 2016 | Special Operations Command | Major Military Construction | California | United States | P1126 | SOF COMBAT SERVICE SUPPORT FACILITY |  |  |  | 2016-08-22 | 2018-02-14 | 2019-02-28 | 99% | 2019-03-15
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P1218 | SOF MARINE BATTALION COMPANY/TEAM FACILITIES |  |  |  | 2013-10-03 | 2016-01-18 | 2018-01-31 | 100% | 2018-01-31
2021-05-11 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | P1219 | SOF MARINE BATTALION COMPANY/TEAM FACILITIES |  |  |  | 2018-01-11 | 2020-01-12 | 2021-07-12 | 97%
2021-05-11 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | P1288 | SOF COMBAT SERVICE SUPPORT FACILITY |  |  |  | 2018-01-11 | 2020-01-12 | 2021-07-12 | 94%
2021-05-11 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | P1362 | SOF HUMAN PERFORMANCE TRAINING CENTER |  |  |  | 2020-08-05 | 2022-02-07 | 2022-02-07 | 2%
2021-05-11 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | P1391 | SOF SUSTAINMENT TRAINING COMPLEX |  |  |  | 2014-09-11 | 2016-09-02 | 2019-01-31 | 100% | 2018-06-06
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P1393 | SOF SURVIVAL EVASION RESISTANCE ESCAPE TRAINING FACILITY |  |  |  | 2013-10-03 | 2016-01-18 | 2018-01-31 | 100% | 2018-01-31
2021-05-11 | 2018 | Special Operations Command | Major Military Construction | North Carolina | United States | P1394 | SOF MOTOR TRANSPORT MAINTENANCE EXPANSION |  |  |  | 2020-04-10 | 2021-10-04 | 2021-10-23 | 70%
2021-05-11 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | P1395 | SOF MARINE RAIDER REGIMENT HQ |  |  |  | 2020-04-10 | 2021-10-04 | 2023-02-17 | 0%
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | North Carolina | United States | P1396 | SOF INTEL OPS EXPANSION |  |  |  | 2015-08-31 | 2017-03-09 | 2017-10-27 | 100% | 2017-10-25
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P1410 | SOF EOD EXPANSION |  |  |  | 2013-10-10 | 2014-09-22 | 2015-06-30 | 99% | 2015-06-30
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | North Carolina | United States | P1450 | SOF FIRES PLATOON STORAGE FACILITY |  |  |  | 2014-02-27 | 2014-12-10 | 2015-10-30 | 100% | 2015-10-30
2021-05-11 | 2014 | Special Operations Command | Major Military Construction | North Carolina | United States | P1469 | SOF MSOB SUPPORT FACILITIES |  |  |  | 2014-10-14 | 2015-11-24 | 2016-08-25 | 99% | 2016-08-25
2021-05-11 | 2015 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | P1475 | MARSOC CULTURAL ASSIMILATION FACILITY |  |  |  | 2018-07-03 | 2019-09-13 | 2021-01-14 | 94% | 2021-01-13
2021-05-11 | 2016 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | P1481 | INDIVIDUAL TRAINING COURSE TEAM TRAINING FACILITY |  |  |  | 2018-09-14 | 2019-11-11 | 2020-07-06 | 99% | 2020-07-06
2021-05-11 | 2020 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | P1482 | MARINE SPECIAL OPERATIONS SCHOOL 120 MAN CLASSROOMS |  |  |  | 2020-10-06 | 2021-09-18 | 2022-01-11 | 0%
2021-05-11 | 2020 | Special Operations Command | Major Military Construction | North Carolina | United States | P1534 | REPLACE MARSOC ITC TEAM FACILITY |  |  |  | 2020-09-29 | 2024-05-27 | 2024-05-27 | 0%
2021-05-11 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P157 | SOF HUMAN PERFORMANCE CENTER |  |  |  | 2016-03-11 | 2017-09-03 | 2020-09-16 | 100% | 2021-01-20
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | Virginia | United States | P165 | SOF COMBAT SERVICES SUPPORT FACILITY - EAST |  |  |  | 2013-10-08 | 2015-09-09 | 2015-11-26 | 100% | 2015-11-13
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | P166 | QDR SOF MOBILE COMMUNICATIONS DET SUPPORT FACILITY |  |  |  | 2015-10-05 | 2017-07-17 | 2019-03-04 | 100% | 2019-03-04
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | Mississippi | United States | P170 | SOF NAVSCIATTS APPLIED INSTRUCTION FACILITY |  |  |  | 2016-02-09 | 2017-10-17 | 2018-06-16 | 100% | 2018-06-27
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | Virginia | United States | P183 | SOF INDOOR DYNAMIC RANGE |  |  |  | 2014-05-01 | 2017-07-24 | 2018-05-18 | 100% | 2018-05-18
2021-05-11 | 2019 | Special Operations Command | Major Military Construction | California | United States | P200 | SOF NSWG-1 OPERATIONS SUPPORT FACILITY |  |  |  | 2020-07-14 | 2023-01-20 | 2023-01-20 | 12%
2021-05-11 | 2020 | Special Operations Command | Major Military Construction | Virginia | United States | P224 | SOF NSWG-10 OPERATIONS SUPPORT FACILITY |  |  |  | 2021-02-12 | 2023-08-05 | 2023-08-05 | 0%
2021-05-11 | 2016 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P225 | SOF NSWG-10 UAS SUPPORT FACILITY |  |  |  | 2018-08-17 | 2019-08-30 | 2020-01-07 | 99% | 2020-01-07
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | Mississippi | United States | P240 | SOF LAND ACQUISITION WESTERN MANEUVER AREA |  |  |  | 2019-07-29 | 2020-03-25 | 2020-01-25 | 100% | 2019-12-31
2021-05-11 | 2018 | Special Operations Command | Unspecified Minor Military Construction | North Carolina | United States | P241 | SOF NSWG4 BOAT SUPPORT FACILITY |  |  |  | 2019-10-10 | 2020-11-13 | 2021-01-14 | 85% | 2021-04-16
2021-05-11 | 2014 | Special Operations Command | Major Military Construction | Virginia | United States | P334 | SOF LOGSU TWO OPERATIONS FACILITY |  |  |  | 2016-02-24 | 2018-07-29 | 2020-05-01 | 99% | 2020-05-01
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | Nevada | United States | P418 | SOF TACTICAL GROUND MOBILITY VEHICLE MAINTENANCE FACILITY |  |  |  | 2015-09-01 | 2017-02-23 | 2018-02-12 | 100% | 2018-02-02
2021-05-11 | 2020 | Special Operations Command | Major Military Construction | Hawaii | United States | P463 | SOF UNDERSEA OPERATIONAL TRAINING FACILITY |  |  |  | 2020-04-29 | 2022-04-15 | 2022-04-15 | 0%
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | Hawaii | United States | P475 | SOF-SDVT-1 WATERFRONT OPERATIONS FACILITY |  |  |  | 2016-02-08 | 2018-02-13 | 2018-06-24 | 100% | 2018-06-22
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | Virginia | United States | P564 | CONSTRUCT ADDITION TO BUILDING 120 |  |  |  | 2013-10-14 | 2014-12-31 | 2015-02-12 | 100% | 2015-02-12
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | Virginia | United States | P576 | SOF KNOWN DISTANCE RANGE TOWER |  |  |  | 2016-07-29 | 2016-08-14 | 2018-01-03 | 100% | 2018-02-22
2021-05-11 | 2018 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P698 | SOF PHYSICAL SECURITY BUILDING ADDITION (DAM NECK) |  |  |  | 2021-04-07 | 2022-08-08 | 2022-08-08 | 0%
2021-05-11 | 2014 | Special Operations Command | Major Military Construction | Arizona | United States | P771 | SOF DESERT WARFARE TRAINING CENTER |  |  |  | 2018-10-03 | 2020-02-02 | 2021-04-21 | 97% | 2021-04-21
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | California | United States | P776 | SOF LOGSU ONE OPERATIONS FACILITY #1 |  |  |  | 2015-10-14 | 2017-10-23 | 2019-07-23 | 99% | 2021-04-30
2021-05-11 | 2016 | Special Operations Command | Major Military Construction | Virginia | United States | P777 | SOF APPLIED INSTRUCTION FACILITY |  |  |  | 2018-07-30 | 2020-10-09 | 2020-12-13 | 81%
2021-05-11 | 2018 | Special Operations Command | Major Military Construction | Virginia | United States | P791 | SOF SATEC RANGE EXPANSION |  |  |  | 2018-09-27 | 2021-03-17 | 2022-01-12 | 71%
2021-05-11 | 2020 | Special Operations Command | Major Military Construction | Virginia | United States | P824 | SOF DTC COMPLEX EXPANSION |  |  |  | 2020-10-14 | 2022-08-16 | 2022-08-16 | 0%
2021-05-11 | 2019 | Special Operations Command | Major Military Construction | Virginia | United States | P834 | SOF MAGAZINES |  |  |  | 2019-11-26 | 2021-05-20 | 2021-08-18 | 18% | 2021-08-18
2021-05-11 | 2018 | Special Operations Command | Major Military Construction | California | United States | P855 | SOF BASIC TRAINING COMMAND |  |  |  | 2019-10-14 | 2022-08-30 | 2022-12-07 | 16% | 2023-04-28
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | California | United States | P876 | SOF INDOOR DYNAMIC SHOOTING FACILITY |  |  |  | 2014-10-10 | 2016-10-07 | 2017-08-11 | 100% | 2017-06-19
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | California | United States | P888 | SOF CLOSE QUARTERS COMBAT AND DYNAMIC SHOOTING FACILITY (LA POSTA) |  |  |  | 2014-10-14 | 2016-09-29 | 2017-11-08 | 89% | 2021-06-30
2021-05-11 | 2017 | Special Operations Command | Major Military Construction | California | United States | P889 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2017-10-12 | 2020-03-31 | 2021-01-31 | 100% | 2020-05-08
2021-05-11 | 2017 | Special Operations Command | Major Military Construction | California | United States | P890 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2017-10-12 | 2020-03-31 | 2021-01-31 | 100% | 2020-05-08
2021-05-11 | 2018 | Special Operations Command | Major Military Construction | California | United States | P892 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2018-09-27 | 2021-03-31 | 2021-03-31 | 100% | 2021-05-17
2021-05-11 | 2015 | Special Operations Command | Major Military Construction | California | United States | P893 | SOF SUPPORT ACTIVITY OPERATIONS FACILITY #2 |  |  |  | 2015-10-14 | 2018-04-02 | 2019-03-11 | 99% | 2020-08-20
2021-05-11 | 2017 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P900 | SOF MULTI-PURPOSE CANINE OPERATIONS FACILITY |  |  |  | 2018-06-28 | 2020-02-10 | 2020-10-16 | 99% | 2021-04-16
2021-03-10 | 2020 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P914 | SOF NSWG2 TRAINING FACILITY |  |  |  | 2020-10-21 | 2022-04-23 | 2022-04-23 | 0%
2021-05-11 | 2020 | Special Operations Command | Unspecified Minor Military Construction | Virginia | United States | P914U | SOF NSWG2 TRAINING FACILITY |  |  |  | 2020-10-21 | 2022-04-23 | 2022-04-23 | 0%
2021-05-11 | 2013 | Special Operations Command | Major Military Construction | California | United States | P915 | SOF MOBILE COMMUNICATIONS DETACHMENT SUPPORT FACILITY |  |  |  | 2015-09-24 | 2017-08-28 | 2018-06-07 | 100% | 2020-08-21
2021-05-11 | 2019 | Special Operations Command | Major Military Construction | California | United States | P918 | SOF CLOSE QUARTERS COMBAT FACILITY |  |  |  | 2019-10-10 | 2021-10-09 | 2021-11-04 | 55%
2021-05-11 | 2017 | Special Operations Command | Major Military Construction | California | United States | P919 | SOF SPECIAL RECON TEAM ONE OPERATIONS FACILITY |  |  |  | 2017-04-13 | 2018-10-22 | 2020-03-06 | 100% | 2021-04-30
2021-05-11 | 2016 | Special Operations Command | Major Military Construction | California | United States | P920 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #2 |  |  |  | 2016-10-04 | 2018-10-13 | 2019-12-27 | 97% | 2021-04-30
2021-05-11 | 2018 | Special Operations Command | Major Military Construction | California | United States | P921 | SOF LOGISTICS SUPPORT UNIT ONE OPERATIONS FACILITY #3 |  |  |  | 2018-08-09 | 2021-02-15 | 2021-06-18 | 98% | 2021-04-30
2021-05-11 | 2014 | Special Operations Command | Major Military Construction | Florida | United States | P9440 | SOF BOAT DOCKS |  |  |  | 2015-05-14 | 2016-08-22 | 2019-07-17 | 100% | 2019-07-17
2021-05-11 | 2020 | Special Operations Command | Major Military Construction | Florida | United States | P945 | SOF WATERCRAFT MAINTENANCE FACILITY |  |  |  | 2021-01-29 | 2022-10-31 | 2022-10-31 | 0%
2021-05-11 | 2019 | Special Operations Command | Major Military Construction | California | United States | P949 | SOF ATC APPLIED INSTRUCTION FACILITY |  |  |  | 2019-11-11 | 2022-05-19 | 2022-09-12 | 21%
2021-05-11 | 2019 | Special Operations Command | Major Military Construction | California | United States | P950 | SOF ATC TRAINING FACILITY |  |  |  | 2019-11-11 | 2022-05-19 | 2022-09-12 | 11%
2021-05-11 | 2017 | Special Operations Command | Major Military Construction | California | United States | P952 | SOF HUMAN PERFORMANCE TRAINING CENTER |  |  |  | 2017-08-24 | 2019-11-22 | 2020-03-02 | 100% | 2021-04-16
2021-05-11 | 2018 | Special Operations Command | Major Military Construction | California | United States | P964 | SOF SEAL TEAM OPS FACILITY |  |  |  | 2018-09-27 | 2021-03-31 | 2021-03-31 | 99%
2021-05-11 | 2017 | Special Operations Command | Major Military Construction | California | United States | P966 | SOF TRADET ONE OPERATIONS FACILITY |  |  |  | 2017-10-12 | 2020-04-19 | 2020-11-20 | 100% | 2021-04-16
2021-05-11 | 2020 | Special Operations Command | Major Military Construction | Virginia | United States | P999 | SOF NSWG2 JSOTF OPERATIONS TRAINING FACILITY |  |  |  | 2021-02-12 | 2023-08-05 | 2023-08-05 | 0%
2021-04-27 | 2020 | Special Operations Command | Major Military Construction | Washington | United States | PQWY083008 | 22 STS Operations Facility |  |  |  | 2020-06-16 | 2022-06-16 | 2021-11-10 | 42%
2019-09-30 | 2016 | Special Operations Command | Major Military Construction | North Carolina | United States | TMKH003003 | SOF 21 STS Operations Facility |  |  |  | 2018-07-31 | 2020-01-22 | 2020-10-19 | 80%
2021-05-10 | 2010 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80001 | Pentagon Electrical Upgrade |  |  |  | 2013-11-07 | 2015-02-05 | 2021-07-01 | 95% | 2021-07-30
2021-05-10 | 2010 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80001A | Pentagon Electrical Upgrade |  |  |  | 2013-11-07 | 2015-02-05 | 2020-04-30 | 100% | 2020-04-30
2017-04-20 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80003 | Metro Entrance Facility/Visitor Screening Facility |  |  |  | 2013-11-01 | 2015-05-03 | 2016-08-30 | 99% | 2016-04-01
2021-03-03 | 2011 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80004 | Secure Access Lane (SAL) |  |  |  | 2016-10-25 | 2018-05-18 | 2018-10-26 | 34% | 2020-05-22
2016-12-15 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80005 | Pentagon Heliport Control Tower/Fire Station |  | 798000 | Budget Sequester
2016-12-15 | 2012 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80006 | Pentagon Memorial Pedestrian Plaza |  | 2285000 | $176,000 Budget Sequester $409,000 to 80003 $1.7M to 80004
2021-05-10 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80007 | PFPA Support Operations Center |  |  |  | 2018-06-27 | 2020-09-23 | 2021-08-31 | 92% | 2021-10-31
2021-03-03 | 2014 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80008 | Boundary Channel Access Control Point |  |  |  | 2016-06-01 | 2017-12-01 | 2020-08-01 | 100% | 2020-08-01
2021-03-03 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80009 | Raven Rock Admin Facility Upgrade |  | 500000 | Reprogramming: $500,000 to project 80002 | 2017-02-15 | 2019-10-02 | 2020-07-01 | 100% | 2020-07-01
2019-12-04 | 2014 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 80010 | Raven Rock Exterior Cooling Towers |  | 3929000 | Reprogramming: to project 80001
2021-05-10 | 2015 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80011 | Redundant Chilled Water Loop |  |  |  | 2020-04-01 | 2021-06-21 | 2022-04-15 | 25% | 2022-04-15
2019-08-15 | 2017 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 80916 | Pentagon Metro Entrance Facility.
2021-05-10 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 87637 | Pentagon Corridor 8 Pedestrian Access Control Point |  |  |  | 2020-09-28 | 2022-06-21 | 2022-08-16 | 12% | 2022-10-16
2021-05-10 | 2019 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 87645 | North Village Secondary VACP and Fencing |  | 383475 | Reprogramming $383,475 to project 87744 | 2020-10-15 | 2021-04-23 | 2021-12-31 | 18% | 2022-02-28
2021-05-10 | 2017 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 87744 | Upgrade IT Facilities Infrastructure RRMC |  | 383475 | Reprogramming received from project 87645 bid savings | 2020-08-01 | 2021-08-13 | 2021-07-26 | 94% | 2021-10-04
2021-05-10 | 2019 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 88790 | Exterior Infrastructure and Security Improvements |  |  |  | 2020-04-24 | 2022-08-17 | 2022-08-17 | 20% | 2022-10-17
2021-05-10 | 2018 | Washington Headquarters Services | Major Military Construction | Pennsylvania | United States | 88963 | Security Upgrades |  |  |  | 2020-02-12 | 2022-01-20 | 2022-01-20 | 62% | 2022-04-22
2021-05-10 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91474 | Southest Safety Traffic and Parking Improvements |  |  |  | 2020-02-01 | 2021-01-22 | 2023-02-28 | 12% | 2023-04-23
2021-05-10 | 2018 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91474A | Southest Safety Traffic and Parking Improvements |  |  |  | 2019-03-18 | 2019-06-18 | 2019-06-18 | 100% | 2021-09-22
2021-05-10 | 2020 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 91531 | Backup Generator
2021-05-10 | 2020 | Washington Headquarters Services | Major Military Construction | Virginia | United States | 92232 | Control Tower and Fire Day Station |  |  |  | 2021-09-30 | 2023-04-30 | 2023-04-30

## CONTRACTS
Contract Data as of Date | Project Fiscal Year | Project Sponsor Component Name | Project Number | Sub-Project Number | Contract Solicitation Date | Contract Award Date | Prime Contract Recipient Name | Prime Contract Number | Original Contract Amount | Current Contract Obligation Amount | Original Contract Completion Date | Current Contract Completion Date
2021-04-30 | 2018 | Air Force Active | AEWV171012 |  | 2018-08-01 | 2019-03-01 | Black & Veatch Special Project | W912ER18D0005 | 3705150 | 3726765 | 2020-08-08 | 2020-11-21
2021-04-30 | 2018 | Air Force Active | AGGN053009 |  | 2020-02-22 | 2020-03-23 | Original Award | W912BV20C0005 | 20353334 | 20353334 | 2022-04-22 | 2021-09-26
2021-04-30 | 2016 | Air Force Active | AGGN123003 |  | 2018-06-14 | 2019-09-27 | Sheffield-Korte Team | W912BV19C0024 | 22471409 | 22627538 | 2019-09-27 | 2023-05-14
2021-04-30 | 2017 | Air Force Active | AGGN173001 |  | 2017-01-06 | 2017-07-06 | SGS, LLC | W912BV17C0010 | 10428748 | 10774827 | 2018-12-01 | 2019-10-15
2020-10-31 | 2018 | Air Force Active | AGGN193001 |  | 2017-12-26 | 2018-09-26 | Terra Construction | W912BV18C0018 | 5175672 | 5175672 | 2020-05-08 | 2020-05-08
2021-04-30 | 2019 | Air Force Active | AGGN213001 |  | 2018-10-29 | 2019-06-17 | SGS, LLC; Yukon OK | W912BV19C0011 | 12250972 | 12250972 | 2021-02-14 | 2021-02-14
2021-04-30 | 2020 | Air Force Active | AJJY073105P3 |  | 2020-01-17 | 2020-09-16 | Core Tech-Hawaiian Dredging | N6274220C1324 | 49686730 | 49686730 | 2023-07-16 | 2023-07-16
2021-04-30 | 2013 | Air Force Active | AJJY123010 |  | 2014-05-28 | 2015-02-20 | CORE TECH-AMEC-SKEC, LLC. | N6274210D1307JQ01 | 89918305 | 92069698 | 2017-03-21 | 2020-06-18
2021-04-30 | 2014 | Air Force Active | AJJY133027 |  | 2014-04-28 | 2014-12-18 | CORE-TECH-AMEC-SK | N6274210D13070002 | 96616619 | 102815679 | 2017-03-08 | 2021-07-17
2021-04-30 | 2015 | Air Force Active | AJJY133028 |  | 2016-06-01 | 2016-09-30 | Pernix Guam, LLC | N6274216C1309 | 26463336 | 29396424 | 2018-11-08 | 2021-05-28
2020-12-31 | 2014 | Air Force Active | AJJY143760 |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907700 | 25244110 | 2016-03-30 | 2021-12-31
2020-12-31 | 2016 | Air Force Active | AJJY163004 |  | 2017-05-19 | 2017-08-31 | Tikigaq Construction LLC | N4019216D2706 | 12841000 | 13185296 | 2019-05-13 | 2021-01-23
2021-04-30 | 2020 | Air Force Active | AJJY183017 |  | 2020-06-15 | 2020-09-30 | Serrano Construction | N4019218D2804 | 3967372 | 3967372 | 2022-06-30 | 2022-06-30
2021-04-30 | 2021 | Air Force Active | AJJY203001 |  | 2020-09-16 | 2021-02-25 | Granite-Obayashi, a Joint Venture | N6274221C1338 | 41944700 | 41944700 | 2023-03-17 | 2023-03-17
2021-04-30 | 2017 | Air Force Active | AJXF093000 |  | 2017-08-02 | 2018-05-24 | EDIFICE, LLC | N4008017D0009 | 11179388 | 11179388 | 2020-02-25 | 2020-02-25
2021-04-30 | 2018 | Air Force Active | AJXF173021 |  | 2018-06-05 | 2018-07-05 | Oncore Group, LLC | N4008018C2018 | 1490854 | 1490854 | 2019-01-26 | 2019-01-26
2021-04-30 | 2018 | Air Force Active | AJXF173021 |  | 2018-11-12 | 2018-12-12 | Clark Construction Group, LLC | N4008019C0008 | 220000000 | 220000000 | 2022-05-25 | 2022-05-25
2021-04-30 | 2018 | Air Force Active | ALUA113023 |  | 2019-05-29 | 2019-09-26 | MVL USA, Inc. / Houston / TX | W912ER19C0016 | 13890460 | 13683606 | 2021-01-20 | 2021-05-27
2021-01-31 | 2015 | Air Force Active | ASHE143006 |  | 2016-11-03 | 2017-07-24 | BB Government Services Srl | N3319117C1234 | 1147724 | 1618955 | 2019-02-02 | 2019-02-02
2021-04-30 | 2018 | Air Force Active | ASHE143008 |  | 2018-01-04 | 2018-09-28 | CMC | N6247018C4004 | 15453726 | 16235042 | 2022-08-23 | 2022-08-23
2021-04-30 | 2017 | Air Force Active | ASVF164000 |  | 2017-09-16 | 2018-09-11 | RED HORSE | FA571018P0325 | 2200000 | 2348000 | 2020-03-04 | 2021-06-30
2021-04-30 | 2018 | Air Force Active | ASVF183100A |  | 2019-01-11 | 2020-04-10 | American International Contractors, (Pkg 2, Aprons) | W912ER20C0009 | 32474636 | 32474636 | 2023-03-28 | 2023-03-28
2021-04-30 | 2018 | Air Force Active | ASVF183100B |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER20C0009 | 9862845 | 9856753 | 2023-03-28 | 2023-03-28
2021-04-30 | 2018 | Air Force Active | ASVF183100C |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc, (Pkg 2, Aprons) | W912ER20C0009 | 8267668 | 8267668 | 2023-03-28 | 2023-03-28
2021-04-30 | 2018 | Air Force Active | ASVF183100D |  | 2018-06-28 | 2019-04-05 | The Morganti Group, Inc / Danbury, CT (Pkg 3, Dorm) | W912ER19C0008 | 10434344 | 10386944 | 2020-08-29 | 2021-10-20
2020-10-31 | 2018 | Air Force Active | ASVF183100D |  | 2018-06-28 | 2019-04-05 | The Morganti Group, Inc / Danbury, CT (Pkg 2, Aprons) | W912ER18R0007 | 10434344 | 10386944 | 2020-08-29 | 2020-10-14
2021-04-30 | 2018 | Air Force Active | ASVF183100E |  | 2019-01-11 | 2020-04-10 | American International Contractors, Inc.(Pkg 2, Aprons) | W912ER20C0009 | 804821 | 804821 | 2023-03-28 | 2023-03-28
2021-04-30 | 2018 | Air Force Active | ASVF183100F |  | 2018-02-23 | 2018-08-22 | The Morganti Group, Inc. (Pkg 1, LSA), Danbury, CT | W912ER18C0029 | 15147990 | 16244162 | 2020-03-04 | 2020-11-01
2021-04-30 | 2018 | Air Force Active | ASVF183100F |  | 2019-03-06 | 2019-04-05 | The Morganti Group, Inc (Pkg 3, Dorm), Danbury, CT | W912ER19C0008 | 118048 | 118048 | 2020-10-13 | 2021-02-18
2021-04-30 | 2018 | Air Force Active | ASVF183100F |  | 2020-03-11 | 2020-04-10 | American International Contractors, Inc (Pkg 2, Aprons) | W912ER20C0009 | 28401350 | 28401350 | 2023-03-21 | 2023-05-25
2021-04-30 | 2018 | Air Force Active | ASVF183100F |  | 2019-10-21 | 2019-11-20 | The Morganti Group, Inc (Pkg 2, Aprons),Danbury/CT | W912ER20C0002 | 100000 | 350000 | 2020-01-04 | 2020-09-05
2021-04-30 | 2017 | Air Force Active | AWUB095000 |  | 2016-12-02 | 2019-07-17 | Consolidated Communication Facility | N6945013D1771 | 24961520 | 24961520 | 2022-01-02 | 2022-04-02
2020-08-31 | 2017 | Air Force Active | AWUB105003 |  | 2017-07-10 | 2018-06-21 | FIRE STATION NO. 2 | N6945018C2105 | 3600686 | 3774341 | 2019-10-08 | 2020-01-27
2021-04-30 | 2017 | Air Force Active | AWUB105003 |  | 2017-07-10 | 2018-06-21 | FIRE STATION NO. 2 | N69450-18C2105 | 3396587 | 3396587 | 2019-10-08 | 2021-04-05
2021-04-30 | 2018 | Air Force Active | BIKF180001 |  | 2018-05-02 | 2018-12-06 | Iceland Prime Contractor, LTD | N6247018R4005 | 14146220 | 14146220 | 2021-10-20 | 2021-10-20
2021-04-30 | 2020 | Air Force Active | BIKF190001 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 19776676 | 19776676 | 2023-04-04 | 2023-04-04
2021-04-30 | 2020 | Air Force Active | BIKF190002 |  | 2019-11-15 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 4671392 | 4671392 | 2023-04-04 | 2023-04-04
2021-04-30 | 2020 | Air Force Active | BIKF190003 |  | 2019-11-08 | 2020-09-21 | Icelandic Prime Contractors | N6247020C0010 | 14404448 | 14404448 | 2023-04-04 | 2023-04-04
2021-04-30 | 2017 | Air Force Active | CADJ170001 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 3194454 | 3361236 | 2020-02-06 | 2021-10-09
2021-04-30 | 2017 | Air Force Active | CADJ170002 |  | 2017-10-06 | 2018-04-30 | Consortio Stabile GMG SOC | N3319116D1035 | 4911856 | 5375981 | 2020-02-06 | 2022-03-20
2021-04-30 | 2018 | Air Force Active | CRWU093002 |  | 2018-02-01 | 2018-12-18 | Mortenson | W9128F18R00040030 | 34249000 | 35079522 | 2021-06-20 | 2021-11-15
2021-04-30 | 2019 | Air Force Active | CRWU173001 |  | 2020-07-15 | 2020-09-25 | Iron Mike Construction | W9128F20C0048 | 4763991 | 4730531 | 2021-12-12 | 2021-12-12
2021-01-31 | 2017 | Air Force Active | CZQZ083500 |  | 2018-02-21 | 2018-08-08 | The Ross Group Construction Corp | W912PP18C0018 | 17063090 | 17144431 | 2020-06-16 | 2020-08-03
2021-04-30 | 2017 | Air Force Active | DHAF152900 |  | 2018-04-01 | 2019-09-06 | Amana Contracting & Steel Building Co. WLL, Abu Dhabi UAE | W912ER19C0015 | 25152460 | 25152460 | 2021-10-15 | 2021-10-15
2021-04-30 | 2017 | Air Force Active | DXEB053005 |  | 2017-04-26 | 2018-04-30 | Bethel-Unit JV | W911KB18C0006 | 19278001 | 19948643 | 2020-04-11 | 2021-01-29
2021-04-30 | 2017 | Air Force Active | EEEI150006 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB15D0029 | 1451631 | 1451631 | 2023-05-28 | 2023-05-28
2021-04-30 | 2018 | Air Force Active | EEEI180001 |  | 2020-02-18 | 2020-08-19 | Astlanda Ehitus OU | W912GB15D0029 | 1210326 | 1210326 | 2023-05-28 | 2023-05-28
2020-12-31 | 2017 | Air Force Active | EPLK150006 |  | 2017-07-14 | 2017-09-20 | Wolf & Mueller and Erbud JV | W912GB15D0060 | 2533989 | 2533989 | 2020-03-26 | 2020-03-26
2021-04-30 | 2017 | Air Force Active | EPPW170003 |  | 2017-07-14 | 2017-09-21 | Wolff & Mueller & Erbud JV | W912GB15D0060 | 2463632 | 2463632 | 2020-03-26 | 2020-03-26
2021-01-31 | 2018 | Air Force Active | EVGA180001 |  | 2018-05-18 | 2018-09-30 | ARCERS SIA | W912GB15D0039 | 3880548 | 3880548 | 2021-01-03 | 2021-01-03
2021-04-30 | 2019 | Air Force Active | FBNV033002 |  | 2019-07-10 | 2019-09-28 | BFL Construction CO | W912PL19C0035 | 10792977 | 10792977 | 2021-06-02 | 2021-06-02
2021-04-30 | 2019 | Air Force Active | FBNV163001 |  | 2019-04-10 | 2020-01-17 | Chase, Carson, & White LLC | W912PL20C0008 | 3190900 | 3190900 | 2021-02-15 | 2021-02-15
2021-03-31 | 2017 | Air Force Active | FBNV163001 |  | 2019-04-10 | 2020-01-17 | Chase, Carson, & White LLC | W912PL20C0008 | 3190900 | 3190900 | 2021-02-15 | 2021-02-15
2021-04-30 | 2017 | Air Force Active | FJXT133000 |  | 2020-03-01 | 2020-03-31 | Aircraft Maintenance Hangar | W912BU20C0015 | 44643899 | 44643899 | 2021-12-31 | 2022-01-23
2021-04-30 | 2016 | Air Force Active | FNWZ100071A |  | 2018-05-09 | 2018-08-08 | Basecom Construction Services | W4126C18C0049 | 4378953 | 4378953 | 2019-10-22 | 2019-11-20
2021-04-30 | 2017 | Air Force Active | FSPM053503C |  | 2017-05-12 | 2018-05-22 | I.E. Pacific, INC | W912PL8C0024 | 22414000 | 22537509 | 2020-06-18 | 2020-08-28
2021-04-30 | 2020 | Air Force Active | FSPM173504 |  | 2020-01-31 | 2020-08-06 | Korte Construction Company | W912PL20C0030 | 34420210 | 34420210 | 2020-08-06 | 2023-08-09
2021-04-30 | 2017 | Air Force Active | FTFA033003 |  | 2017-08-28 | 2017-09-30 | The Green-Simmons Company, Inc | W9127816D0016 | 12034000 | 12208303 | 2019-07-29 | 2020-02-20
2021-04-30 | 2017 | Air Force Active | FTFA033003 |  | 2017-12-12 | 2018-01-11 | Pac Comm, Inc (Demo) | FA282318F4602 | 300552 | 300552 | 2018-05-26 | 2018-05-26
2021-04-30 | 2017 | Air Force Active | FTFA033003 |  | 2017-11-21 | 2017-12-21 | Yerkes South, Inc (Abatement) | FA282318F4654 | 13216 | 13216 | 2018-03-16 | 2018-03-16
2021-04-30 | 2017 | Air Force Active | FTFA043000 |  | 2018-06-07 | 2019-03-15 | Hensel Phelps | W9127819C00006 | 59456363 | 59676833 | 2020-11-11 | 2020-11-11
2021-04-30 | 2017 | Air Force Active | FTFA043000 |  | 2018-06-07 | 2019-03-15 | Speegle | W9127816D0031 | 7687194 | 7712303 | 2020-03-16 | 2020-03-16
2021-04-30 | 2018 | Air Force Active | FTFA053017 |  | 2019-05-20 | 2019-09-30 | Dormitories Replace Dorm 19 | W9127819C0034 | 43336911 | 43336911 | 2021-11-05 | 2022-01-15
2021-04-30 | 2019 | Air Force Active | FTFA093965 |  | 2018-11-12 | 2019-03-21 | Whitesell-Green | W9127819C0012 | 26376465 | 26387419 | 2021-04-21 | 2021-04-21
2021-04-30 | 2019 | Air Force Active | FTFA143913 |  | 2019-03-26 | 2019-04-25 | Korte Construction | W9127819C0013 | 31295038 | 31286284 | 2020-04-24 | 2020-04-26
2021-04-30 | 2018 | Air Force Active | FTFA163003 |  | 2018-06-28 | 2018-09-28 | Speegle Constrcution, Inc | W9127818C0026 | 8007902 | 8052184 | 2020-08-22 | 2020-09-25
2021-04-30 | 2020 | Air Force Active | FTFA163007 |  | 2020-07-07 | 2020-09-29 | Cyberspace Test Facility | W9127820C0033 | 30147298 | 30147298 | 2022-04-30 | 2022-10-31
2021-04-30 | 2019 | Air Force Active | FTQW1053834 |  | 2019-01-03 | 2019-07-18 | F-35 Aircraft Maintenance Unit Admin | W911KB19R0008 | 7985684 | 7985684 | 2021-03-10 | 2021-07-17
2021-04-30 | 2019 | Air Force Active | FTQW1054329 |  | 2019-06-07 | 2019-09-30 | F-35 A Conventional Munitions Maintenance facility | W911KB19C0030 | 14585410 | 14585410 | 2021-07-31 | 2021-09-23
2021-01-31 | 2017 | Air Force Active | FTQW170107 |  | 2018-01-11 | 2019-06-12 | Bristol Design Build Services LLC | W911KB19C0009 | 18687206 | 18857457 | 2020-10-31 | 2020-11-19
2020-10-31 | 2018 | Air Force Active | FTQW180106 |  | 2018-03-29 | 2018-08-10 | Alcan Builders, Inc. | W911KB18C0031 | 7755869 | 7855766 | 2020-08-05 | 2020-09-22
2021-04-30 | 2018 | Air Force Active | FTQW180107 |  | 2020-05-31 | 2020-06-30 | Sundance - EA II, LLC | W911KB17F0055 | 24237 | 24237 | 2020-08-14 | 2020-08-14
2021-04-30 | 2018 | Air Force Active | FTQW180107 |  | 2017-12-28 | 2018-03-23 | Callahan/Watterson Joint Ventu | W911KB18C0018 | 19051000 | 20237814 | 2020-02-14 | 2020-08-11
2021-04-30 | 2018 | Air Force Active | FTQW180107 |  | 2020-05-25 | 2020-06-24 | AECOM Technical Services, Inc | W911KB19F0159 | 19611 | 19611 | 2020-08-08 | 2020-08-08
2021-04-30 | 2019 | Air Force Active | FTQW180109 |  | 2018-09-27 | 2019-02-28 | GHEMM Company, Inc | W911KB19C0013 | 19794920 | 19893239 | 2020-07-30 | 2020-09-22
2021-04-30 | 2017 | Air Force Active | FTQW183001 |  | 2020-05-31 | 2020-06-30 | Sundance - EA II, LLC | W911KB17F0055 | 744425 | 744425 | 2020-08-14 | 2020-08-14
2021-04-30 | 2017 | Air Force Active | FTQW183001 |  | 2018-01-30 | 2018-06-05 | Watterson Construction Company | W911KB18C0026 | 82125000 | 84389702 | 2020-05-06 | 2021-03-03
2021-04-30 | 2017 | Air Force Active | FTQW183001 |  | 2020-05-25 | 2020-06-24 | AECOM Technical Services, Inc | W911KB19F0159 | 602336 | 602336 | 2020-08-08 | 2020-08-08
2021-04-30 | 2017 | Air Force Active | FXSB982839 |  | 2017-02-22 | 2020-04-01 | ADD/ALTER AWACS ALERT HANGAR | W911KB20C008 | 47985111 | 47985111 | 2022-03-17 | 2022-03-17
2020-10-31 | 2017 | Air Force Active | FXSB982839 |  | 2017-02-22 | 2020-04-01 | Unit Company | W911KB20C0008 | 44975700 | 44975700 | 2022-03-17 | 2022-03-17
2021-04-30 | 2017 | Air Force Active | GHLN083004 |  | 2017-05-16 | 2017-06-15 | W9128F16R0011 | W9128F16D00550001 | 5129267 | 5129267 | 2019-01-21 | 2020-12-31
2021-04-30 | 2016 | Air Force Active | GHLN153001 |  | 2017-09-19 | 2018-12-07 | Construction Contract | W9128F19C0005 | 154269651 | 154269651 | 2022-04-20 | 2022-11-05
2021-04-30 | 2017 | Air Force Active | GJKZ040009 |  | 2018-08-10 | 2018-12-28 | GARCO Construction | W912DW19C0002 | 23481000 | 23481000 | 2021-11-14 | 2021-11-14
2021-04-30 | 2019 | Air Force Active | GJLK1053425 |  | 2020-06-25 | 2020-09-24 | Garco Construction INC | W912DW20C0015 | 12230000 | 12230000 | 2020-09-24 | 2023-06-05
2021-01-31 | 2012 | Air Force Active | HACC123204 |  | 2016-05-09 | 2016-06-08 | M+W LOTOS ITALY SOC CONSORTILE A RL. | N3319115C0802 | 7723700 | 10116708 | 2018-01-24 | 2019-11-19
2021-04-30 | 2016 | Air Force Active | KNMD043004 |  | 2018-02-01 | 2018-09-29 | Nordic PCL Construction | W9128A18C0009 | 41476374 | 41533334 | 2020-10-22 | 2021-01-30
2021-04-30 | 2020 | Air Force Active | KRSM1065068 |  | 2020-04-24 | 2020-07-15 | GBSD Mission Integration Facility | W9123820C0012 | 36073172 | 36073172 | 2023-09-12 | 2023-04-04
2021-04-30 | 2017 | Air Force Active | KRSM113031 |  | 2019-01-11 | 2020-12-30 | The Povolny Group, Inc | W9123821C0007 | 3892900 | 3892900 | 2020-12-31 | 2023-03-20
2020-11-30 | 2017 | Air Force Active | KRSM143006 |  | 2015-05-30 | 2018-01-19 | Shofar-CTI JV | W9123818C0006 | 6161226 | 6161226 | 2020-02-12 | 2020-02-12
2021-04-30 | 2018 | Air Force Active | KWRD143000 |  | 2018-08-22 | 2019-10-31 | RPA Fixed Ground Control Station | W912PP19C0019 | 4963246 | 4963246 | 2020-12-30 | 2021-06-21
2021-04-30 | 2017 | Air Force Active | LBPG150008 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB17F0444 | 1611283 | 1611283 | 2021-01-21 | 2021-01-21
2021-04-30 | 2017 | Air Force Active | LBPG150009 |  | 2018-06-29 | 2018-09-30 | Joint Venture Ahntech-Badzak | W912GB17F0461 | 1978602 | 1978602 | 2022-02-11 | 2022-02-11
2021-04-30 | 2017 | Air Force Active | LJYC133003 |  | 2017-11-08 | 2018-05-01 | Aytekin Serol Insaat Taan | W912GB18C0013 | 10199660 | 10199660 | 2021-05-22 | 2021-05-22
2021-04-30 | 2018 | Air Force Active | LJYC183004 |  | 2018-08-29 | 2019-05-13 | EMTA INSAAT TAAHHUT VE TICARET ANONIUM SI | W912GB19F0076 | 3795142 | 3795142 | 2021-09-28 | 2021-09-28
2021-04-30 | 2019 | Air Force Active | LKTC203101 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL19C0028 | 25007200 | 25296112 | 2021-10-02 | 2021-10-02
2021-04-30 | 2019 | Air Force Active | LKTC203102 |  | 2019-07-31 | 2019-09-26 | KORTE | W912PL19C0028 | 24652900 | 24732573 | 2021-11-02 | 2021-12-07
2021-04-30 | 2017 | Air Force Active | LRCT150007 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2575083 | 2575083 | 2020-03-12 | 2020-10-13
2021-04-30 | 2017 | Air Force Active | LRCT150008 |  | 2017-07-28 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0021 | 1711902 | 1711902 | 2022-05-06 | 2023-01-16
2021-04-30 | 2017 | Air Force Active | LRCT150009 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2356785 | 2356785 | 2022-08-25 | 2023-03-28
2021-04-30 | 2017 | Air Force Active | LRCT150010 |  | 2017-07-25 | 2017-12-27 | TSONTOS, MICHAEL M., S.A. | W912GB18F0020 | 2021357 | 2021357 | 2022-06-15 | 2023-01-16
2021-01-31 | 2018 | Air Force Active | LRCT180001 |  | 2018-08-01 | 2018-09-30 | SKE International Gmbh | W912GB18F0467 | 1049315 | 1049315 | 2021-01-17 | 2021-01-17
2021-04-30 | 2016 | Air Force Active | LXEZ154288 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV16D0009 | 33322662 | 33322662 | 2021-01-14 | 2021-01-14
2021-04-30 | 2016 | Air Force Active | LXEZ164289 |  | 2017-11-01 | 2018-07-31 | Nishimatsu Construction Co. Ltd | W912HV16D0009 | 26546290 | 26546290 | 2021-01-14 | 2021-01-14
2021-04-30 | 2018 | Air Force Active | LXEZ184546 |  | 2019-11-27 | 2020-05-18 | Kyowa Exeo Corporation | W912HV20B00010004 | 57456449 | 57456449 | 2022-12-30 | 2022-12-30
2020-07-31 | 2017 | Air Force Active | MAHG173002 |  | 2019-05-22 | 2020-05-28 | U-SMC/DeMaria JV, LLC | N69450 19D0921 | 3591891 | 3591891 | 2021-06-26 | 2021-06-26
2021-04-30 | 2017 | Air Force Active | MAHG173002 |  | 2019-05-22 | 2020-05-28 | U-SMC/DeMaria JV, LLC | N6945019D0921 | 3591891 | 3591891 | 2021-06-25 | 2021-06-25
2020-07-31 | 2017 | Air Force Active | MAHG173003 |  | 2019-06-12 | 2020-05-28 | TU-SMC/DeMaria JV, LLC | N69450 19D0921 | 4007591 | 4007591 | 2021-06-26 | 2021-06-26
2021-04-30 | 2017 | Air Force Active | MAHG173003 |  | 2019-06-12 | 2020-05-28 | TU-SMC/DeMaria JV, LLC | N6945019D0921 | 4007591 | 4007591 | 2021-06-25 | 2021-06-25
2020-10-31 | 2016 | Air Force Active | MHMV043095 |  | 2017-12-20 | 2018-07-16 | K L House Construction Company | W912PP18C016 | 11219000 | 11219000 | 2020-01-13 | 2020-01-13
2021-04-30 | 2018 | Air Force Active | MHMV083126A |  | 2020-08-14 | 2020-11-20 | Encanto Facillity Services 2 | W912PP19D0037 | 8427275 | 8427275 | 2022-03-31 | 2022-03-31
2021-04-30 | 2016 | Air Force Active | MPLS083737R5 |  | 2017-11-29 | 2019-01-16 | Cadell Construction Co | W9126G19C0001 | 103156897 | 98410381 | 2021-08-03 | 2021-10-12
2021-04-30 | 2016 | Air Force Active | MPLS083737R5 |  | 2019-05-27 | 2019-06-26 | SB Demo | W9126G19C0035 | 5546178 | 5546178 | 2019-07-26 | 2021-10-12
2021-04-30 | 2017 | Air Force Active | MPLS083737R6 |  | 2019-01-22 | 2019-09-26 | ATC 6 | W9126G19C0023 | 103001487 | 103001487 | 2022-04-13 | 2022-10-27
2021-04-30 | 2016 | Air Force Active | MPLS083737S3 |  | 2017-11-29 | 2019-01-16 | Caddell Construction - DCF 3 | W9126G19C0001 | 55663720 | 55663720 | 2021-08-03 | 2022-06-22
2021-04-30 | 2016 | Air Force Active | MPLS113003A |  | 2018-11-30 | 2019-03-01 | Express Contracting | W9126G19C0019 | 2872000 | 2872000 | 2020-06-30 | 2020-06-30
2021-04-30 | 2015 | Air Force Active | MPLS3274JB |  | 2015-02-17 | 2015-06-03 | Solis Constructors, Inc. | W9126G14D00500002 | 6077000 | 6133616 | 2016-08-31 | 2018-06-12
2021-04-30 | 2018 | Air Force Active | MSET143006 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 18542509 | 18542509 | 2023-12-24 | 2023-12-24
2021-04-30 | 2018 | Air Force Active | MSET153501 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 23292923 | 23292923 | 2021-10-05 | 2021-10-05
2021-04-30 | 2019 | Air Force Active | MSET153503 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 22219318 | 22219318 | 2024-01-21 | 2024-01-21
2021-04-30 | 2019 | Air Force Active | MSET153504 |  | 2018-10-15 | 2018-11-14 | KVF35 | DIOCB2076 | 33031258 | 33031258 | 2023-01-21 | 2023-01-21
2021-04-30 | 2019 | Air Force Active | MSET153505 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 11543865 | 11543865 | 2022-07-04 | 2022-07-04
2021-04-30 | 2018 | Air Force Active | MSET153506 |  | 2018-06-04 | 2018-11-14 | KVF 35 | DIOCB2076 | 16724478 | 16724478 | 2022-12-21 | 2022-12-21
2020-11-30 | 2019 | Air Force Active | MSET153507 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 12913377 | 12913377 | 2022-02-28 | 2022-02-28
2021-04-30 | 2019 | Air Force Active | MSET153508 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 36198139 | 36198139 | 2024-01-21 | 2024-01-21
2021-04-30 | 2018 | Air Force Active | MSET153509 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 6211718 | 6211718 | 2023-12-26 | 2023-12-26
2021-04-30 | 2018 | Air Force Active | MSET153513 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 22251003 | 22251003 | 2023-09-30 | 2023-09-30
2021-04-30 | 2018 | Air Force Active | MSET153514 |  | 2018-06-08 | 2018-11-14 | KVF 35 | DIOCB2076 | 39101561 | 39101561 | 2021-10-05 | 2021-10-05
2021-04-30 | 2019 | Air Force Active | MXRD153006 |  | 2019-07-07 | 2019-08-06 | Ritter & Paratore Contracting Inc | W912WJ19C0014 | 2347000 | 2347000 | 2020-05-17 | 2020-04-26
2021-04-30 | 2020 | Air Force Active | NKAK123007 |  | 2020-05-15 | 2020-08-31 | The Ross Group Construction | W9127S20C6006 | 35396600 | 35396600 | 2020-08-31 | 2023-10-15
2021-04-30 | 2016 | Air Force Active | NUEX093016 |  | 2017-10-05 | 2018-02-01 | Okland Construction, Co. Inc. | W912PL18C0013 | 16223496 | 16246162 | 2020-02-26 | 2020-04-11
2021-01-31 | 2019 | Air Force Active | NVZR153710 |  | 2019-08-09 | 2020-02-26 | HCR | TBD | 3351127 | 3351127 | 2021-06-18 | 2021-06-18
2021-04-30 | 2019 | Air Force Active | NVZR153710 |  | 2019-08-09 | 2020-02-26 | HCR | W9127820C0010 | 3351127 | 3351127 | 2021-06-18 | 2021-06-18
2021-04-30 | 2018 | Air Force Active | NVZR153711 |  | 2019-07-19 | 2019-09-26 | Southeast Cherokee Constr. Inc | W9127816D0015 | 8163765 | 8163765 | 2021-06-17 | 2021-06-17
2021-04-30 | 2016 | Air Force Active | NZAS043002 |  | 2019-05-06 | 2019-06-05 | Construct MMDF | W912DW19C008 | 19868428 | 19868428 | 2020-12-26 | 2020-08-31
2021-04-30 | 2017 | Air Force Active | NZAS173001 |  | 2019-05-20 | 2019-06-19 | MMDF | W912DW19C0008 | 19868428 | 19868428 | 2021-03-10 | 2021-05-15
2021-04-30 | 2017 | Air Force Active | PAF150400 |  | 2017-11-21 | 2018-05-18 | AECOM | N6274218C1314 | 24132780 | 32137430 | 2019-11-15 | 2020-04-06
2021-04-30 | 2018 | Air Force Active | PAF160600 |  | 2019-05-07 | 2019-09-26 | Nova Nacap JV | N6274219C1316 | 62585000 | 62834002 | 2022-10-25 | 2022-10-25
2021-04-30 | 2020 | Air Force Active | PAF180300 |  | 2019-12-05 | 2020-05-28 | ICON SI (Aust) Pty Ltd | N6274220C1303 | 10310997 | 10351471 | 2022-02-03 | 2022-02-03
2021-04-30 | 2015 | Air Force Active | PAYZ15001B |  | 2016-10-30 | 2016-11-29 | Mitnijos Turto Valdymas UAB | W912GB15D00500002 | 7097718 | 7097718 | 2018-07-07 | 2018-07-07
2021-04-30 | 2015 | Air Force Active | PAYZ15001B |  | 2016-06-18 | 2016-11-21 | Vilmanto Statybos | W912GB15D00560002 | 1515821 | 1515821 | 2018-07-06 | 2018-07-06
2021-04-30 | 2015 | Air Force Active | PAYZ15001H |  | 2017-03-08 | 2017-09-22 | Cimolai S.p.A | N6247017C5002 | 27192353 | 37466344 | 2020-08-30 | 2022-12-22
2021-04-30 | 2016 | Air Force Active | PAYZ16000B |  | 2020-03-31 | 2020-08-19 | Onaka Gumi Co., Ltd. | W912HV20C0006 | 2413198 | 2413198 | 2021-09-07 | 2021-09-07
2021-04-30 | 2017 | Air Force Active | PNQS072140 |  | 2018-01-01 | 2019-05-08 | Southeast Cherokee | W9127819C0017 | 13341000 | 13341000 | 2021-04-20 | 2021-04-20
2021-04-30 | 2019 | Air Force Active | PNQS103165 |  | 2019-07-17 | 2019-09-30 | Bear Brothers, INC | W9127819C0037 | 12768107 | 12768107 | 2021-05-26 | 2021-05-26
2021-04-30 | 2018 | Air Force Active | PRQE055155 |  | 2018-06-28 | 2018-09-28 | CNS Source Selection Sensitive | W912DQ18C4051 | 17296912 | 17296912 | 2018-11-13 | 2021-06-30
2021-04-30 | 2018 | Air Force Active | PTFL163001 |  | 2018-08-24 | 2019-02-27 | RANCO CONSTRUCTION INC | W912DS18B00210013 | 4427200 | 4604956 | 2021-03-08 | 2021-03-08
2021-04-30 | 2018 | Air Force Active | PTFL163006 |  | 2018-08-24 | 2018-09-28 | Sun Construction Services Inc. | W912DS18C0027 | 3159200 | 3237588 | 2019-11-09 | 2019-12-02
2020-10-31 | 2018 | Air Force Active | PTFL163007 |  | 2018-08-24 | 2019-02-27 | Ranco Construction Inc | W912DS19C0005 | 3209084 | 3279825 | 2020-04-29 | 2020-05-06
2021-04-30 | 2018 | Air Force Active | PTFL163010 |  | 2019-06-12 | 2019-09-25 | TDX Quality | W912DS19B007 | 7994996 | 8019376 | 2021-03-19 | 2021-03-19
2021-04-30 | 2018 | Air Force Active | PTFL163019 |  | 2018-10-29 | 2019-07-11 | Walsh Federal LLC | W912DS19C0011 | 52324000 | 52687100 | 2021-07-23 | 2021-07-23
2021-04-30 | 2018 | Air Force Active | QJVF012005 |  | 2019-01-25 | 2019-05-29 | Minot Indoor Firing Range | W9128F18C0026 | 24993526 | 24993526 | 2021-02-17 | 2021-08-21
2020-10-31 | 2016 | Air Force Active | QKKA154008 |  | 2017-04-06 | 2017-09-21 | Nippo Corp | FA520517C0005 | 50968708 | 50534155 | 2020-10-19 | 2020-10-19
2021-04-30 | 2017 | Air Force Active | QSEU083023 |  | 2020-06-23 | 2020-09-03 | McKnight Construction | W912HN20C3007 | 23471929 | 23471929 | 2022-10-03 | 2022-10-03
2021-04-30 | 2018 | Air Force Active | RKMF063004 |  | 2018-06-03 | 2018-07-03 | Record Steel and Construction, Inc., dba RSCI | W912PL19C0023 | 21623000 | 21813532 | 2020-08-06 | 2021-08-27
2021-04-30 | 2016 | Air Force Active | RKMF103011 |  | 2019-03-13 | 2019-12-17 | BRISTOL | W912PL20C0007 | 2667515 | 5042612 | 2020-11-25 | 2021-10-16
2021-04-30 | 2019 | Air Force Active | RKMF123009 |  | 2019-04-17 | 2019-08-27 | GUARDIAN/EC JV LLC | W912PL19C0024 | 5555674 | 5555674 | 2021-06-02 | 2021-06-02
2021-04-30 | 2020 | Air Force Active | RKMF163007 |  | 2020-07-23 | 2020-09-30 | KORTE | W912PL20C0021 | 36685652 | 36685652 | 2022-12-28 | 2022-12-28
2020-11-30 | 2017 | Air Force Active | RKMF173001 |  | 2018-09-20 | 2019-02-12 | Fortis Nova Group A Joint Venture LLC | W912PL19C0006 | 9050000 | 9200944 | 2020-11-03 | 2020-11-03
2021-04-30 | 2018 | Air Force Active | RKMF173010 |  | 2019-03-04 | 2019-10-02 | Bristol Prime Contractors, LLC | W912PL20C0001 | 3698666 | 3783934 | 2020-11-11 | 2020-11-13
2020-11-30 | 2018 | Air Force Active | RKMF183001 |  | 2018-03-01 | 2018-07-13 | KORTE CONST CO | W912PL18C0026 | 28985169 | 30703117 | 2020-07-30 | 2020-11-13
2021-04-30 | 2020 | Air Force Active | RKMF203001 |  | 2020-06-15 | 2020-09-16 | GUARDIAN | W912PL20C0035 | 5659450 | 5659450 | 2021-12-01 | 2021-12-01
2021-04-30 | 2020 | Air Force Active | RKMF203007 |  | 2020-03-13 | 2020-06-19 | Record Steel and Construction, Inc., dba RsCI | W912PL20C0018 | 27554000 | 27554000 | 2022-07-24 | 2022-07-24
2021-04-30 | 2019 | Air Force Active | SGBP1047602 |  | 2019-03-18 | 2019-05-20 | Sapper Construction - PARKING LOT, USSTRATCOM | W9128F19C0023 | 8623365 | 8623365 | 2019-06-19 | 2020-08-21
2021-04-30 | 2019 | Air Force Active | SMYU073011 |  | 2019-06-27 | 2019-09-27 | Kumsung Construction Co., Ltd | W912UM19C0017 | 1227670 | 1227670 | 2021-02-21 | 2021-02-21
2021-04-30 | 2017 | Air Force Active | SXHT013001 |  | 2017-02-16 | 2017-06-01 | LEEBC O R SER VIC ES, LLC | W9127816D0033 | 12383350 | 12447196 | 2019-03-12 | 2020-05-27
2021-01-31 | 2018 | Air Force Active | TDKA063002D |  | 2018-11-07 | 2019-08-16 | JE Hurley Inc | W9128F19R0006 | 3888005 | 3930515 | 2020-12-02 | 2020-12-27
2021-04-30 | 2020 | Air Force Active | TDKA143002 |  | 2020-10-06 | 2021-04-27 | No Data | W912F21C0019 | 43789430 | 43789430 | 2023-09-14 | 2023-09-14
2021-04-30 | 2012 | Air Force Active | TYFR063017 |  | 2012-03-01 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541693 | 29662433 | 2017-01-18 | 2026-06-18
2020-10-31 | 2013 | Air Force Active | TYFR106020U |  | 2015-08-31 | 2016-04-29 | Peter Gross LBB Kaiserslautern | CON0940460000 | 1278751 | 1277558 | 2017-05-24 | 2021-01-25
2021-04-30 | 2018 | Air Force Active | UHHZ163000 |  | 2018-12-12 | 2020-05-20 | Hensel Phelps, Orlando, FL | W912HN20F4009 | 10827560 | 10827560 | 2021-12-10 | 2021-12-10
2021-04-30 | 2019 | Air Force Active | ULDF123001 |  | 2019-07-18 | 2020-01-17 | FOUR TRIBES ENTERPRISES, LLC | W912DS20C0005 | 13147968 | 13147968 | 2021-08-03 | 2021-08-03
2021-04-30 | 2017 | Air Force Active | VDYD101053 |  | 2020-02-24 | 2020-07-29 | River City Construction, LLC/East Peoria IL | W912QR20C0028 | 30100000 | 30100000 | 2023-03-08 | 2023-03-08
2021-04-30 | 2016 | Air Force Active | VKAG013004R5 |  | 2017-08-21 | 2019-06-28 | Walsh Federal Construction Contract-SJ ATCT | W912HN19C3006 | 23716745 | 23716745 | 2019-07-28 | 2021-05-23
2021-04-30 | 2019 | Air Force Active | VLSB193001 |  | 2020-08-11 | 2020-12-30 | B.L. Harbert International, L.L.C. | N6945021C0004 | 46487791 | 46487791 | 2022-12-30 | 2022-12-30
2020-10-31 | 2017 | Air Force Active | VNVP177501 |  | 2018-08-22 | 2019-01-25 | Terra Construction | W912BV19F0016 | 4960700 | 4960700 | 2020-02-19 | 2020-02-19
2021-04-30 | 2016 | Air Force Active | WWYK093003 |  | 2016-09-09 | 2017-03-13 | Walsh Federal JV (Chicago/IL) | W912BV17C0005 | 12472000 | 12809463 | 2018-11-08 | 2019-01-12
2021-04-30 | 2015 | Air Force Active | WWYK153005 |  | 2015-03-05 | 2017-03-30 | Walsh Federal Alberici JV | W912BV17C0004 | 97939000 | 98825383 | 2019-04-30 | 2019-08-19
2021-04-30 | 2019 | Air Force Active | WWYK193001 |  | 2018-08-31 | 2019-08-29 | Korte | W912BV19C0015 | 69771792 | 69771792 | 2022-03-19 | 2022-03-19
2021-04-30 | 2017 | Air Force Active | WWYK193003 |  | 2017-12-22 | 2019-02-07 | Record Steel and Construction | W912BV19C0002 | 24873819 | 24873819 | 2020-11-24 | 2020-11-24
2021-04-30 | 2019 | Air Force Active | WWYK193014 |  | 2018-10-01 | 2019-09-27 | Korte Const Co | W912BV19C0017 | 71921672 | 71921672 | 2022-03-20 | 2022-03-20
2021-04-30 | 2020 | Air Force Active | XDAT1026962 |  | 2020-06-20 | 2020-07-16 | J.I Garcia Construction | N6247318D5817 | 4679000 | 4887389 | 2021-09-09 | 2021-11-27
2021-04-30 | 2018 | Air Force Active | XDAT1051930 |  | 2018-10-26 | 2019-12-30 | Walsh Federal | N6247320C0613 | 123643850 | 124327472 | 2022-06-17 | 2022-06-17
2021-04-30 | 2019 | Air Force Active | XLWU193005 |  | 2019-08-12 | 2019-09-23 | Green Simmons Company INC | W9127819F0486 | 12369134 | 12369134 | 2021-11-09 | 2021-11-09
2021-04-30 | 2019 | Air Force Active | XLWU193006 |  | 2019-08-26 | 2019-09-26 | Southeast Cherokee Const INC | W9127810518 | 16624000 | 16614000 | 2021-11-02 | 2021-11-02
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2020-07-24 | 2020-09-25 | Caddell Constr Co. Montgomery | W912HN20D3003 | 25994000 | 25994000 | 2022-09-16 | 2022-09-16
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | SCLIN 1019AG | 102203 | 102203 | 2023-03-12 | 2023-03-12
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN 1019AE | 16114 | 16114 | 2023-03-12 | 2023-03-12
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN 1019AD | 599343 | 599343 | 2023-03-12 | 2023-03-12
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN 1019AC | 35974 | 35974 | 2023-03-12 | 2023-03-12
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN 1019AB | 237126 | 237126 | 2023-03-12 | 2023-03-12
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN 1019AA | 73710 | 73710 | 2023-03-12 | 2023-03-12
2021-04-30 | 2019 | Air Force Active | XLWU203006 |  | 2021-01-26 | 2021-02-25 | Gulf Coast Electric Cooperative | S/CLIN 1019AF | 8437 | 8437 | 2023-03-12 | 2023-03-12
2020-10-31 | 2018 | Air Force Active | XQPZ124004 |  | 2018-08-16 | 2018-09-29 | John Bowman INC | W9128F18C0041 | 1310200 | 1482100 | 2020-11-14 | 2020-11-14
2021-04-30 | 2018 | Air Force Active | XQPZ164001 |  | 2020-04-16 | 2020-08-21 | Bryan Construction | W9128F20C0038 | 26744525 | 26778818 | 2023-08-13 | 2023-08-13
2021-04-30 | 2020 | Air Force Active | XQPZ174006 |  | 2020-09-23 | 2021-01-29 | JBI Inc | W9128F21C0013 | 5040100 | 5040100 | 2023-02-27 | 2023-02-27
2021-04-30 | 2016 | Air Force Active | YWHG031002R2 |  | 2018-07-02 | 2019-01-31 | YWHG031002R2, Consolidated Stealth Operations & Nuclear Alert Facility | W912DQ19C4001 | 26957316 | 26957316 | 2020-09-09 | 2021-05-11
2021-04-30 | 2019 | Air Force Active | ZHTV093301 |  | 2019-07-17 | 2019-08-16 | ADAL Intelligence Production Facility, Golf Course | W912QR19C0027 | 2173425 | 2173425 | 2020-06-11 | 2024-06-10
2021-04-30 | 2019 | Air Force Active | ZHTV093301 |  | 2019-10-20 | 2019-11-19 | Add/Alter Intelligence Production Facility, Road and Utilities Relocation | W912QR19B00160005 | 4911384 | 4911384 | 2020-10-14 | 2024-06-10
2021-04-30 | 2018 | Air Force Active | ZHTV153201 |  | 2020-01-27 | 2020-04-14 | Butt Construction | W912QR20C0011 | 6610000 | 6610000 | 2021-09-15 | 2021-09-15
2021-02-28 | 2020 | Air Force Active | ZNRE204308 |  | 2020-06-25 | 2020-08-18 | Nippo Construction | W912HV17D001520F0041 | 8901454 | 8901454 | 2022-09-06 | 2022-09-06
2021-04-30 | 2020 | Air Force Active | ZNRE204308 |  | 2020-06-25 | 2020-08-18 | Improve MFH PAIP 8A | W912HV17D001520F004 | 9895245 | 9895245 | 2022-09-06 | 2022-09-06
2021-04-30 | 2020 | Air Force Reserve | AJXF223744 |  | 2020-06-01 | 2020-09-23 | Kinsley Construction, Inc. | W912QR20C0049 | 9992147 | 9992147 | 2022-06-03 | 2022-06-03
2021-04-30 | 2018 | Air Force Reserve | AWUB105005 |  | 2018-07-12 | 2019-03-30 | Justin J. Reeves, L.L.C. | N6945019C2105 | 2907892 | 2907892 | 2020-03-31 | 2021-08-31
2020-03-31 | 2019 | Air Force Reserve | CTGB169002 |  | 2019-04-23 | 2019-08-01 | NISOU LGC JV, LLC | W912QR-19-C-0026 | 9928185 | 9928185 | 2020-09-30 | 2020-09-30
2021-04-30 | 2019 | Air Force Reserve | CTGB169002 |  | 2019-04-23 | 2019-08-01 | NISOU LGC JV, LLC | W912QR19C0026 | 9928185 | 9928185 | 2020-10-27 | 2021-07-01
2021-04-30 | 2019 | Air Force Reserve | CTGB989003 |  | 2020-06-01 | 2020-09-16 | Messer Construction Co. | W912QR20C0039 | 11471000 | 11471000 | 2022-05-04 | 2022-05-04
2021-04-30 | 2018 | Air Force Reserve | DDPM130007 |  | 2018-06-29 | 2018-12-12 | Unified Sevices of Texas, Inc. | N6945019F1275 | 2179491 | 2179491 | 2020-09-14 | 2021-01-31
2020-03-31 | 2018 | Air Force Reserve | DDPM130007 |  | 2018-06-29 | 2018-12-12 | Unified Sevices of Texas, Inc. | N6945015D1618 | 2179491 |  | 2019-10-31 | 2020-07-31
2021-04-30 | 2016 | Air Force Reserve | FGWB009002 |  | 2017-01-06 | 2017-09-21 | DRACE CONSTRUCTION COMPANY | W912QR17C0038 | 9397411 | 10249989 | 2019-06-06 | 2021-04-30
2021-04-30 | 2018 | Air Force Reserve | KNMD624007 |  | 2020-09-01 | 2020-12-17 | Hensel Phelps Construction Co. | N6247820D4003 | 8552000 | 8552000 | 2022-07-11 | 2022-07-11
2020-03-31 | 2019 | Air Force Reserve | MAHG063004 |  | 2019-10-01 | 2019-12-11 | EMR, Inc. | N69450D170507 | 5057057 |  | 2020-10-31 | 2021-03-31
2021-04-30 | 2019 | Air Force Reserve | MAHG063004 |  | 2019-10-01 | 2019-12-11 | EMR, Inc. | N6945020F0870 | 5057057 | 5057057 | 2020-10-31 | 2021-07-09
2021-04-30 | 2016 | Air Force Reserve | PDPG120514 |  | 2018-08-20 | 2018-09-14 | Lead Builders Inc | W912QR18C0031 | 4968200 | 5056600 | 2019-11-08 | 2021-05-14
2021-04-30 | 2019 | Air Force Reserve | RVKQ079104 |  | 2019-04-29 | 2019-07-03 | LGC Global, Inc. | W912QR19C0021 | 11311046 | 11333785 | 2021-07-23 | 2021-08-21
2021-04-30 | 2018 | Air Force Reserve | SXHT103001 |  | 2018-03-01 | 2018-05-25 | Ashford Leebcor Enterpises, LLC | W912QR18C0018 | 25242688 | 22626925 | 2020-07-19 | 2021-10-02
2020-03-31 | 2019 | Air Force Reserve | SXHT171217 |  | 2019-06-24 | 2019-09-28 | Roundhouse PBN | W912QR-17-C-0049 | 2863596 | 2863596 | 2021-04-01 | 2021-10-01
2021-04-30 | 2019 | Air Force Reserve | SXHT171217 |  | 2019-06-24 | 2019-09-28 | Roundhouse PBN | W912QR17C0049 | 2863596 | 2863596 | 2021-03-15 | 2021-03-15
2021-04-30 | 2019 | Air Force Reserve | SXHT203000 |  | 2020-06-01 | 2020-09-24 | Patriot Construction | W912QR20C0050 | 20438870 | 20438870 | 2022-07-25 | 2022-07-25
2021-04-30 | 2018 | Air Force Reserve | UHHZ073003 |  | 2019-06-28 | 2019-09-24 | ACC Construction Company, Inc. | W912QR19C0042 | 32093710 | 28917160 | 2021-11-26 | 2021-02-20
2021-04-30 | 2020 | Air Force Reserve | UHHZ073005 |  | 2020-11-15 | 2021-01-29 | ACC Construction Company, Inc. | W912QR19C0009 | 31229066 | 31229066 | 2023-04-11 | 2023-04-11
2021-04-30 | 2017 | Air Force Reserve | VKAG159021 |  | 2017-05-19 | 2017-09-27 | Walbridge Aldinger LLC | W912QR17C0031 | 52493799 | 58903514 | 2020-09-09 | 2022-05-15
2019-01-31 | 2017 | Air Force Reserve | VKAG159022 |  | 2017-08-01 | 2017-09-25 | Southeast Cherokee Const, Inc | W912QR17C0041 | 4834000 | 4834000 | 2019-03-19 | 2019-09-19
2021-04-30 | 2018 | Air Force Reserve | VKAG159026 |  | 2020-06-01 | 2020-09-29 | Ocean Construction Services, Inc. | W912QR20C0056 | 4628152 | 4628152 | 2022-07-08 | 2022-07-08
2021-04-30 | 2018 | Air Force Reserve | YTPM059004 |  | 2019-04-08 | 2019-08-01 | P & S Construction, Inc. | W912QR19C0020 | 10383981 | 9832232 | 2020-12-12 | 2021-05-30
2021-05-03 | 2017 | Air National Guard | AJXF039040 |  | 2019-07-01 | 2019-09-30 | Lawley Construction/Kochendorfe Group USA Inc | W912R119C5000 | 5005729 | 4801000 | 2021-05-15 | 2021-05-15
2020-09-30 | 2016 | Air National Guard | AQRC059093 |  | 2018-06-07 | 2018-09-11 | Ranco Construction Inc | W912KN18C6001 | 11942478 | 11942478 | 2020-08-04 | 2020-11-02
2018-07-02 | 2014 | Air National Guard | BRKR999147 |  | 2014-04-02 | 2014-08-13 | Southeast Cherokee Construction, Inc | W912JA14C0001 | 8201275 | 8201275 | 2016-10-23 | 2019-04-30
2019-08-06 | 2015 | Air National Guard | CEKT129080 |  | 2015-08-19 | 2016-01-15 | NUTMEG COMPANIES, INC. | W91ZRS12D00260006 | 1968645 | 1968645 | 2021-02-03 | 2018-05-18
2019-09-10 | 2015 | Air National Guard | CEKT139004 |  | 2015-02-17 | 2015-06-03 | Cutter Enterprises, LLC | W91ZRS15C0002 | 14859726 | 14859726 | 2019-05-24 | 2020-05-24
2021-05-03 | 2018 | Air National Guard | CEKT139029 |  | 2018-06-30 | 2018-11-20 | LAROSA BUILDING GROUP, LLC | W91ZRS18R00020002 | 6707992 | 6353569 | 2024-05-20 | 2024-05-20
2021-01-31 | 2017 | Air National Guard | CEKT139042 |  | 2017-06-12 | 2017-09-29 | Cutter Enterprises LLC | W91ZRS17C0002 | 6097608 | 6097608 | 2021-01-11 | 2021-02-28
2021-05-03 | 2018 | Air National Guard | CEKT149052 |  | 2018-06-30 | 2018-12-18 | LAROSA BUILDING GROUP, LLC | W91ZRS18R50010002 | 4979466 | 4990118 | 2024-12-26 | 2024-12-26
2020-09-30 | 2016 | Air National Guard | CRWU069125 |  | 2019-04-12 | 2019-07-31 | Centerre Construction | W912LC19C5001 | 5564000 | 5564000 | 2020-07-30 | 2020-09-30
2019-06-04 | 2016 | Air National Guard | CVVM099000 |  | 2015-08-15 | 2015-10-01 | S.B. BALLARD | ARMYS.B.BALLARD | 1022000 | 1022000 | 2015-10-31 | 2018-07-31
2021-05-03 | 2017 | Air National Guard | CVVM179001 |  | 2017-07-15 | 2017-09-12 | Harlan Construction Co., Inc. | W912LQ17C3001 | 1172030 | 1172030 | 2021-10-31 | 2021-10-31
2020-09-30 | 2016 | Air National Guard | DBEH143000 |  | 2017-08-25 | 2018-08-14 | Rush Construction, Inc. | W911YN18C0001 | 5222619 | 5222619 | 2023-08-18 | 2020-10-15
2020-09-30 | 2016 | Air National Guard | FAKZ059173 |  | 2018-01-05 | 2018-08-07 | Bear Brothers, Inc. | W912JA18C6003 | 6826545 | 6826545 | 2021-06-01 | 2021-11-01
2021-05-03 | 2017 | Air National Guard | FJRP159062 |  | 2018-09-19 | 2019-03-29 | Cleveland Construction Inc | W9124219C5004 | 29161433 | 28170000 | 2020-10-28 | 2020-10-28
2021-05-03 | 2017 | Air National Guard | FJRP159073 |  | 2018-02-23 | 2018-10-30 | Bodell Construction Company | W9124219C5001 | 20879519 | 20323383 | 2021-01-27 | 2021-01-27
2021-05-03 | 2019 | Air National Guard | FJRP199080 |  | 2019-03-28 | 2019-07-12 | GVA-AVM Joint Venture | W9124219C5007 | 5224985 | 5049432 | 2020-08-26 | 2020-08-26
2020-09-30 | 2016 | Air National Guard | FKNN059220 |  | 2016-06-16 | 2016-09-15 | NICKERSON & O'DAY, INC. | W912JD16B20010004 | 4552775 | 4552775 | 2020-08-03 | 2020-10-01
2019-08-06 | 2015 | Air National Guard | FKNN119013 |  | 2015-03-23 | 2015-06-05 | Nickerson & O'Day | BGS#1806 | 2000000 | 2000000 | 2017-08-03 | 2019-07-19
2020-03-05 | 2017 | Air National Guard | FMKM089018 |  | 2017-03-10 | 2017-08-10 | Max Gray Construction | W912LM17C0002 | 7481566 | 7481566 | 2021-09-25 | 2019-12-31
2019-09-10 | 2015 | Air National Guard | FTAE129002 |  | 2015-04-24 | 2015-08-07 | Aztec General Contractors, LLC | W912LC15R5002 | 1789838 | 1789838 | 2016-06-22 | 2019-08-28
2021-03-31 | 2017 | Air National Guard | FWJH099082 |  | 2018-05-05 | 2018-09-26 | WEBCO, LLC | W912L118C7010 | 5285298 | 5276124 | 2019-10-16 | 2019-10-16
2020-08-31 | 2018 | Air National Guard | HAAW169006 |  | 2019-02-22 | 2019-05-06 | RJ Ortlieb Construction | W912PQ19C8001 | 5117282 | 5117282 | 2020-05-07 | 2020-10-01
2021-05-03 | 2018 | Air National Guard | HAAW179035 |  | 2020-04-30 | 2020-07-14 | SJ Thomas Co Inc | W50S8N20C0001 | 3428805 | 3325800 | 2021-08-08 | 2021-08-08
2020-09-30 | 2016 | Air National Guard | HKRZ129076 |  | 2016-04-12 | 2017-12-22 | Alessi Keyes Construction Co | W912JF18C0001 | 14665029 | 14665029 | 2020-02-01 | 2020-09-01
2021-05-03 | 2017 | Air National Guard | HTUV132007 |  | 2017-08-25 | 2018-02-12 | KPH Construction Corp | W912J217D4005 | 2521404 | 2578759 | 2021-11-02 | 2021-11-02
2021-05-03 | 2017 | Air National Guard | HTUV169001 |  | 2019-01-29 | 2019-07-16 | J&B Builders, Inc. | W912J217D4001 | 2545831 | 2808761 | 2020-12-15 | 2020-12-15
2018-11-01 | 2014 | Air National Guard | JKSE129321 |  | 2014-06-11 | 2014-09-16 | James Talcott Construction Inc | W9124V14C0004 | 20869050 | 20869050 | 2016-10-15 | 2017-08-01
2018-07-02 | 2014 | Air National Guard | JKSE129321 |  | 2017-11-07 | 2017-12-27 | Geranios Enterprises, Inc | W9124V18C5000 | 278657 | 278657 | 2018-03-12 | 2018-07-31
2018-04-30 | 2014 | Air National Guard | JKSE129321 |  | 2014-09-24 | 2014-11-07 | Wadsworth Builders Co., Inc. | W9124V12D00090008 | 1261466 | 1261466 | 2015-10-03 | 2016-08-24
2018-04-30 | 2014 | Air National Guard | JKSE129321 |  | 2014-07-15 | 2014-10-28 | Guy Tabacco Construction Co.. | W9124V12D00110003 | 1441500 | 1441500 | 2015-09-13 | 2016-02-19
2021-05-03 | 2019 | Air National Guard | JKSE169101 |  | 2019-07-15 | 2020-01-24 | United Materials of Great Falls | W9124V20C0002 | 8971404 | 8544808 | 2020-10-25 | 2020-10-25
2021-05-03 | 2019 | Air National Guard | JLQN049119 |  | 2019-02-18 | 2019-06-01 | A. WBE-CCI Joint Venture One, LLC | W91SMC19C6001 | 8184676 | 7901690 | 2023-10-18 | 2023-10-18
2021-05-03 | 2018 | Air National Guard | KJAQ119006 |  | 2019-12-04 | 2020-02-25 | AWBE-Cornerstone JV Cnstr | W50S8Z20C0001 | 12181613 | 11877000 | 2021-03-26 | 2021-03-26
2021-05-03 | 2018 | Air National Guard | KJAQ159096 |  | 2020-09-23 | 2021-02-19 | Ahtna Environmental Inc | W50S8Z21C0001 | 7873129 | 7697582 | 2022-05-05 | 2022-05-05
2021-05-03 | 2018 | Air National Guard | KNMD179040 |  | 2018-06-15 | 2019-05-07 | HI Technology Devel. Corp. | W912J61822021 | 3126987 | 2868023 | 2021-05-23 | 2021-05-23
2018-07-02 | 2014 | Air National Guard | LDXF099060 |  | 2014-07-30 | 2014-09-22 | Patterson-Horth | W912L914D00110002 | 7071641 | 7071641 | 2016-02-28 | 2018-01-31
2021-03-31 | 2019 | Air National Guard | LKLW099101 |  | 2019-08-21 | 2019-08-30 | State of PA per MCCA | 42190131 | 6923749 | 6758732 | 2020-10-04 | 2020-10-04
2021-05-03 | 2017 | Air National Guard | LSGA019179 |  | 2018-05-22 | 2018-10-26 | ABBA Constrution Inc-Hold | W911YN19C0001 | 6346208 | 6410955 | 2024-04-20 | 2024-04-20
2019-08-06 | 2015 | Air National Guard | MBMV129060 |  | 2015-03-01 | 2015-04-15 | Beckering Construction | W912JB15C2007 | 5952943 | 5952943 | 2016-05-14 | 2017-07-31
2018-07-02 | 2014 | Air National Guard | MMMD129073 |  | 2017-06-01 | 2017-09-06 | RITZ Construction INC | W912K617C5001 | 5881448 | 5881448 | 2018-10-06 | 2018-10-12
2021-05-03 | 2019 | Air National Guard | MUHJ179000 |  | 2020-11-03 | 2020-12-23 | Ocean Construction Services | W9123621C2013 | 7644604 | 6748367 | 2023-01-31 | 2023-01-31
2021-05-03 | 2019 | Air National Guard | PBXP929798 |  | 2019-10-25 | 2020-02-18 | CANCO, LLC | W50S8R20C0003 | 10316495 | 10050000 | 2022-01-08 | 2022-01-08
2020-10-31 | 2018 | Air National Guard | PDPG169013 |  | 2018-06-28 | 2018-09-26 | Macro-Z-Technology Co | W912LA18C8004 | 15442023 | 15442023 | 2020-04-16 | 2020-12-01
2018-07-02 | 2014 | Air National Guard | PJMS129058 |  | 2016-03-30 | 2016-09-29 | Kallidus Technologies, Inc. | W912K616C0005 | 12598568 | 12598568 | 2017-10-12 | 2018-10-11
2021-05-03 | 2018 | Air National Guard | PSTE139022 |  | 2019-04-04 | 2019-09-30 | Expert Maintenance & Construction Services | W912QG19C0006 | 3123581 | 3035885 | 2021-04-22 | 2021-04-22
2021-05-03 | 2018 | Air National Guard | PSXE999132 |  | 2018-06-08 | 2019-08-05 | Messer Construction Company | W912L719C7001 | 29613217 | 29989631 | 2021-08-22 | 2021-08-22
2021-02-28 | 2017 | Air National Guard | PTFL129091 |  | 2018-07-13 | 2018-09-28 | TDX Quality LLC1 | W912KN18C5001 | 1949611 | 1949611 | 2022-05-02 | 2021-01-31
2020-09-30 | 2016 | Air National Guard | QMSN099104 |  | 2017-07-31 | 2017-11-09 | Cox Construction | W912LA17C0001 | 8009177 | 8009177 | 2020-03-20 | 2020-10-01
2021-05-03 | 2019 | Air National Guard | RQLH059034 |  | 2020-08-20 | 2021-03-11 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945021C0005 | 7261649 | 6401000 | 2024-10-01 | 2024-10-01
2020-09-30 | 2016 | Air National Guard | RQLH079073 |  | 2016-12-13 | 2017-09-29 | Trimark Constructors, LLC | N6945017C1304 | 9438412 | 9438412 | 2020-12-25 | 2020-10-01
2019-09-10 | 2015 | Air National Guard | SZCQ139901 |  | 2015-01-28 | 2015-07-28 | Arch Insurance Company | W912TF15C05000008 | 16528108 | 16528108 | 2016-11-19 | 2019-10-30
2019-09-10 | 2015 | Air National Guard | SZCQ139904 |  | 2015-01-28 | 2015-07-27 | Arch Insurance Company | W912TF15C0500 | 16353645 | 16353645 | 2016-11-18 | 2021-04-09
2019-09-10 | 2015 | Air National Guard | SZCQ139905 |  | 2017-04-03 | 2017-09-28 | STRUCTURAL ASSOCIATES, INC. | W912TF17C0501 | 7263065 | 7263065 | 2018-10-13 | 2019-08-30
2018-07-02 | 2014 | Air National Guard | TWLR129077 |  | 2014-07-25 | 2014-11-14 | MARON CONSTRUCTION CO., INC. | W912LD15C0001 | 6394775 | 6394775 | 2015-12-14 | 2019-01-31
2021-03-31 | 2017 | Air National Guard | TWLR139040 |  | 2017-11-20 | 2018-04-16 | Tower Construction Co | W912LD1722101 | 2745544 | 2747000 | 2022-07-04 | 2022-07-04
2021-03-31 | 2017 | Air National Guard | TWLR159061 |  | 2017-06-28 | 2017-09-06 | Maron Construction Co. Inc. | 3534532 | 1205000 | 1205000 | 2022-04-29 | 2022-04-29
2021-05-03 | 2018 | Air National Guard | ULYB049040 |  | 2019-04-28 | 2019-09-25 | MCON, LLC | 413180 | 3025568 | 2860050 | 2019-11-22 | 2019-11-22
2021-05-03 | 2018 | Air National Guard | ULYB049040 |  | 2019-07-02 | 2019-08-21 | Lee Grover Construction | W912NS19C6003 | 6052456 | 6037893 | 2021-03-23 | 2021-03-23
2021-05-03 | 2020 | Air National Guard | ULYB169010 |  | 2020-06-09 | 2020-09-02 | Lee Grover | W50S7G20C0001 | 5962100 | 5685773 | 2022-03-31 | 2022-03-31
2020-09-30 | 2017 | Air National Guard | VSSB099014 |  | 2017-05-23 | 2017-08-29 | Opus Design Build, LLC | W912LP17R00020005 | 11401570 | 11401570 | 2021-09-27 | 2020-10-01
2021-05-03 | 2018 | Air National Guard | WEAS079054 |  | 2020-04-17 | 2020-06-15 | Wescott Construction | MCCA | 8489791 | 7662000 | 2021-11-17 | 2021-11-17
2021-01-31 | 2019 | Air National Guard | WKVB109058 |  | 2019-12-31 | 2020-09-08 | Kallidus Technologies, Inc. | W50S8E20C0005 | 16524337 | 16524337 | 2022-01-01 | 2021-12-02
2019-11-05 | 2019 | Air National Guard | WKVB109058 |  | 2018-04-30 | 2019-09-23 | Stop Work 08OCT19. S & E Services Inc | W912PQ19C9001 | 17536508 | 17536508 | 2021-01-24 | 2020-12-25
2021-03-31 | 2018 | Air National Guard | WYTD079031 |  | 2018-10-24 | 2019-04-30 | R.J. Runge Co. | W9136419C8002 | 8756532 | 8751426 | 2020-07-23 | 2020-07-23
2021-05-03 | 2020 | Air National Guard | XDQU109057 |  | 2020-06-23 | 2020-09-25 | Ashford Leebcor Enterprises IV LLC | W50S7020C0002 | 20213955 | 20408734 | 2022-01-23 | 2022-01-23
2021-05-03 | 2018 | Air National Guard | XDQU139458 |  | 2019-06-14 | 2019-09-30 | Collins Construction Services, Inc. | W912JM19C0012 | 2842543 | 2833466 | 2020-11-15 | 2020-11-15
2019-10-07 | 2018 | Air National Guard | XDQU139458 |  | 2019-06-14 | 2019-09-30 | Collins Construction Services, Inc. | W912JM19C0012P00001 | 2928229 | 2928229 | 2020-11-15 | 2020-10-16
2021-05-03 | 2020 | Air National Guard | XGFG189001 |  | 2020-08-20 | 2021-04-15 | J. H. FINDORFF & SON, INC. | W50S9F21C0001 | 10552302 | 9080644 | 2022-12-01 | 2022-12-01
2020-11-30 | 2017 | Air National Guard | YKSX159100 |  | 2017-05-26 | 2017-09-29 | Eastern Construction (MATCO) | W912KN13D00190014 | 1102031 | 1102031 | 2021-07-06 | 2020-10-01
2017-04-30 | 2012 | Army Active | 1235 |  | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23139000 | 23189000 | 2014-04-10 | 2016-03-31
2017-05-31 | 2011 | Army Active | 13852 |  | 2011-07-15 | 2015-09-28 | Dawson Technical, LLC | W9128F-15-C-0044 | 1996000 | 2003000 | 2016-07-23 | 2016-09-30
2017-07-31 | 2012 | Army Active | 17220 |  | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12623000 | 12866000 | 2015-11-11 | 2017-01-19
2019-08-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2016-06-10 | Zieson Construction Company, LLC | W912DQ-15-D-4001 | 44000 | 65000 | 2016-12-21 | 2019-06-30
2017-07-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2014-07-02 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 727000 | 749000 | 2017-02-08 | 2016-10-12
2016-10-31 | 2012 | Army Active | 2728 |  | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 23320000 | 23379000 | 2013-09-20 | 2014-11-24
2018-08-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2014-09-03 | VISTA Construction LLC | W91236-14-C-0043 | 4055000 | 4913000 | 2015-09-16 | 2018-03-14
2016-10-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650000 | 46658000 | 2015-10-15 | 2015-10-16
2018-08-31 | 2013 | Army Active | 33771 |  | 2013-07-17 | 2015-01-14 | Doyon Management Services, LLC | W91236-15-C-0017 | 14297000 | 15018000 | 2017-05-03 | 2018-01-08
2021-04-30 | 2019 | Army Active | 35782 |  | 2019-08-09 | 2019-09-26 | P & R JV | W912QR19C0039 | 22897000 | 23091000 | 2022-02-05 | 2022-08-01
2019-08-31 | 2015 | Army Active | 41449 |  | 2016-05-09 | 2016-09-15 | Purcell Construction Corporation | W91236-16-C-0018 | 58913000 | 58586000 | 2018-10-07 | 2018-12-18
2017-07-31 | 2013 | Army Active | 45116 |  | 2013-02-23 | 2013-07-25 | ANTHONY AND GORDON CONSTRUCTION COMPANY | N69450-13-C-0754 | 0 | 0 | 2016-12-30 | 2016-12-30
2017-07-31 | 2012 | Army Active | 5034 |  | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603000 | 13966000 | 2014-07-18 | 2017-01-31
2018-08-31 | 2013 | Army Active | 51519 |  | 2012-05-16 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 0 | 2033000 | 2014-06-04 | 2018-02-13
2017-07-31 | 2013 | Army Active | 51519 |  | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959000 | 7327000 | 2015-02-15 | 2017-02-28
2017-07-31 | 2014 | Army Active | 51868 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 55619000 | 57495000 | 2016-12-26 | 2017-07-21
2019-08-31 | 2015 | Army Active | 51937 |  | 2015-07-28 | 2016-01-28 | ACC Construction Co., Inc | W912HP-16-C-0001 | 45035000 | 60449000 | 2018-03-17 | 2019-05-31
2021-04-30 | 2019 | Army Active | 52203 |  | 2020-02-27 | 2020-09-29 | Kiewit Infrastructure West Co. | W9128A20C0006 | 44925000 | 44925000 | 2022-08-03 | 2022-08-03
2018-08-31 | 2014 | Army Active | 53584 |  | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036000 | 41919000 | 2017-12-09 | 2018-03-13
2020-08-31 | 2011 | Army Active | 53789 |  | 2012-12-18 | 2013-09-30 | Halbert Construction Company, Inc. | W91238-13-C-0012 | 18519000 | 29495000 | 2015-01-05 | 2020-06-30
2019-08-31 | 2011 | Army Active | 53789 |  | 2012-12-18 | 2015-06-30 | SUNDT CONSTRUCTION INC | W91238-15-C-0007 | 56300000 | 56069000 | 2018-06-15 | 2019-05-17
2021-04-30 | 2018 | Army Active | 55112 |  | 2018-08-14 | 2019-02-22 | ACC Construction Co. | W912HN19C3003 | 21437000 | 22244000 | 2020-10-08 | 2021-06-20
2018-08-31 | 2013 | Army Active | 55121 |  | 2014-10-21 | 2015-07-31 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 40866000 | 43452000 | 2017-12-30 | 2018-05-01
2021-04-30 | 2018 | Army Active | 55199 |  | 2018-07-11 | 2019-10-15 | WHH Nisqually-Garco JV | W912DW20C0001 | 21087000 | 21190000 | 2021-11-29 | 2022-02-08
2020-08-31 | 2016 | Army Active | 55578 |  | 2016-12-15 | 2017-05-11 | Upstate Construction Services, Inc. | W912DS-17-C-0008 | 15051000 | 16180000 | 2019-08-11 | 2020-03-27
2017-07-31 | 2012 | Army Active | 55985 |  | 2012-01-10 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15916000 | 18152000 | 2016-03-23 | 2017-01-26
2017-07-31 | 2011 | Army Active | 56024 |  | 2012-06-29 | 2012-09-25 | Nan, Inc. | W9128A-12-C-0019 | 21105000 | 23910000 | 2014-10-14 | 2016-11-17
2017-05-31 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565000 | 29775000 | 2015-10-05 | 2016-03-15
2018-06-30 | 2012 | Army Active | 57594 |  | 2012-03-12 | 2016-09-27 | AWR ABBRUCH GMBH | W912GB-11-D-0021 | 0 | 0 | 2017-11-05 | 2017-11-05
2017-05-31 | 2011 | Army Active | 58675 |  | 2011-02-22 | 2015-09-30 | Semper Tek, Inc. | W912QR-14-D-0023 | 354000 | 387000 | 2016-10-15 | 2016-09-09
2018-08-31 | 2008 | Army Active | 58784 |  | 2012-02-02 | 2012-09-17 | Chung Kwang Construction Co., Ltd. | W912UM-12-C-0057 | 5458000 | 6999000 | 2014-03-16 | 2018-01-18
2016-10-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2009-01-29 | Hanwha Engr. & Corporation Co., Ltd. | W912UM-09-C-0009 | 17815000 | 18941000 | 2011-01-01 | 2011-05-18
2018-08-31 | 2008 | Army Active | 58784 |  | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32469000 | 36328000 | 2014-09-07 | 2018-01-12
2016-10-31 | 2008 | Army Active | 58784 |  | 2007-12-27 | 2008-03-31 | Shinsung Engr. & Const. Co., Ltd. | W912UM-08-C-0011 | 15961000 | 559000 | 2010-06-13 | 2008-10-22
2020-08-31 | 2013 | Army Active | 58849 |  | 2015-06-02 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 177332000 | 305568000 | 2019-10-10 | 2019-11-13
2020-08-31 | 2017 | Army Active | 58849 | 86285 | 2015-06-02 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 177332000 | 305568000 | 2019-10-10 | 2019-11-13
2020-08-31 | 2018 | Army Active | 58849 | 86286 | 2015-06-02 | 2016-02-23 | Manhattan Construction Company | W912DR-16-C-0004 | 177332000 | 305568000 | 2019-10-10 | 2019-11-13
2021-04-30 | 2011 | Army Active | 59044 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270000 | 127696000 | 2016-01-29 | 2021-07-30
2021-04-30 | 2014 | Army Active | 59779 |  | 2016-02-24 | 2016-07-28 | San Juan Construction, Inc. | W9128A-16-C-0006 | 54844000 | 58213000 | 2020-06-10 | 2021-10-24
2017-07-31 | 2011 | Army Active | 60555 |  | 2010-12-16 | 2012-05-14 | Landesbetrieb Bau und Immobilien Hessen Zentrale | W912GB-08-C-0005 | 28704000 | 33835000 | 2014-06-01 | 2017-01-31
2021-04-30 | 2018 | Army Active | 61147 |  | 2018-06-20 | 2019-11-15 | Walsh Federal JV | W912DW20C0002 | 77308000 | 78946000 | 2022-08-22 | 2022-10-23
2021-04-30 | 2019 | Army Active | 61388 |  | 2019-03-15 | 2019-06-14 | EMPRESA DE CONSTRUCCION Y TRANSPORTE ETERNA, S.A. DE C.V. | W9127819C0019 | 18881000 | 18950000 | 2022-07-14 | 2022-10-13
2017-07-31 | 2012 | Army Active | 61842 |  | 2012-03-13 | 2015-04-20 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0004 | 12172000 | 10478000 | 2016-12-01 | 2017-05-31
2020-08-31 | 2014 | Army Active | 62204 |  | 2015-03-19 | 2016-02-08 | Meltech Corp., Inc. | W912DR-14-D-0021 | 6840000 | 6943000 | 2017-08-16 | 2020-06-30
2021-04-30 | 2017 | Army Active | 62380 |  | 2018-08-13 | 2018-10-22 | Staatliches Hochbauamt Amberg | W912GB-16-C-0007 | 20950000 | 21188000 | 2022-05-11 | 2022-05-28
2017-07-31 | 2012 | Army Active | 62657 |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100113000 | 102060000 | 2015-10-19 | 2016-10-25
2020-08-31 | 2013 | Army Active | 62663 |  | 2015-06-05 | 2017-08-08 | Gilbane Japan GK | W912HV-17-C-0009 | 53816000 | 55369000 | 2019-04-01 | 2020-08-31
2021-04-30 | 2013 | Army Active | 62783 |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan | W912HV-14-C-0007 | 84367000 | 86006000 | 2021-06-09 | 2022-08-11
2021-04-30 | 2020 | Army Active | 62856 |  | 2020-04-14 | 2020-07-21 | Walsh Motor City JV | W912QR20C0027 | 22344000 | 23010000 | 2022-08-20 | 2022-08-20
2021-04-30 | 2019 | Army Active | 62866 |  | 2019-07-12 | 2019-09-30 | MVL USA Inc | W912ER19C0018 | 25397000 | 25397000 | 2021-05-02 | 2021-05-02
2020-08-31 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W91238-14-C-0040 | 38915000 | 47413000 | 2016-06-30 | 2020-07-23
2016-10-31 | 2011 | Army Active | 63015 |  | 2011-01-07 | 2011-08-30 | Watts/Webcor A JV | W91238-11-C-0010 | 34801000 | 3567000 | 2013-06-12 | 2014-06-30
2021-04-30 | 2019 | Army Active | 63054 |  | 2019-07-26 | 2019-09-27 | Benard Associates, Inc | W912DS19C0033 | 25164000 | 27733000 | 2021-11-03 | 2022-11-30
2019-08-31 | 2010 | Army Active | 63571 |  | 2016-02-13 | 2016-04-12 | Akima Construction Services, LLC | W912DY-14-D-0001 | 16769000 | 18658000 | 2017-08-01 | 2019-06-20
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-09-21 | 3D Contracting Inc. | W912DW-12-C-0046 | 14649000 | 15311000 | 2014-05-24 | 2014-12-09
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-01-03 | TSS-Garco Joint Venture | W912DW-13-C-0019 | 8912000 | 9318000 | 2014-08-06 | 2015-04-30
2018-08-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2013-09-26 | MEGEN Construction Company, Inc. | W912HN-11-D-0047 | 7295000 | 10168000 | 2015-04-08 | 2018-05-23
2016-10-31 | 2012 | Army Active | 64014 |  | 2012-04-18 | 2012-06-28 | M.A. Mortenson Company | W9126G-08-D-0045 | 19332000 | 19731000 | 2013-11-17 | 2013-11-14
2016-10-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-08-23 | KCI Construction Company | W912DQ-12-C-4009 | 30970000 | 32856000 | 2014-03-12 | 2014-10-27
2017-07-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-07 | Arch Insurance Company | W912DQ-11-D-4011 | 8541000 | 9243000 | 2014-08-25 | 2017-02-13
2016-10-31 | 2012 | Army Active | 64365 |  | 2012-02-03 | 2012-11-14 | Robinson Mechanical Contractors, Inc. | W912DQ-12-D-4006 | 2493000 | 3965000 | 2014-01-04 | 2015-12-08
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-05-17 | Tunista Construction, LLC | W912DW-13-C-0035 | 9433000 | 11453000 | 2014-12-18 | 2015-12-31
2021-04-30 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2016-09-22 | TSS-Garco Joint Venture | W912DW-16-C-0015 | 42468000 | 44380000 | 2018-07-05 | 2021-02-26
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-09-12 | Environet, Inc. | W912DW-13-C-0042 | 5662000 | 11648000 | 2015-02-12 | 2016-07-28
2016-10-31 | 2013 | Army Active | 64456 |  | 2012-11-19 | 2013-06-18 | Megen Construction Company, Inc. | W912HN-11-D-0047 | 14849000 | 16091000 | 2015-01-02 | 2016-08-19
2017-04-30 | 2012 | Army Active | 64753 |  | 2012-01-09 | 2012-07-13 | Liberty Mutual Insurance Company | W9126G-11-D-0061 | 6095000 | 6160000 | 2014-02-03 | 2016-04-14
2016-10-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18727000 | 19913000 | 2015-04-08 | 2015-10-14
2017-07-31 | 2013 | Army Active | 65679 |  | 2013-01-30 | 2015-09-30 | Fortis Networks, Inc. | W912DQ-14-D-4011 | 1828000 | 2406000 | 2016-08-06 | 2016-10-13
2021-04-30 | 2018 | Army Active | 65699 |  | 2018-08-16 | 2018-09-30 | Leebcor Services, LLC | W91278-16-D-0033 | 16707000 | 17901000 | 2020-10-28 | 2020-10-13
2018-08-31 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30762000 | 39447000 | 2015-12-12 | 2017-12-11
2019-08-31 | 2012 | Army Active | 65755 |  | 2012-05-01 | 2016-05-27 | ARGO Systems LLC | W912DR-16-C-0016 | 6900000 | 7628000 | 2018-01-06 | 2018-01-06
2017-07-31 | 2013 | Army Active | 66023 |  | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345000 | 27541000 | 2016-09-09 | 2017-02-17
2016-10-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687000 | 14606000 | 2014-12-23 | 2014-12-31
2017-07-31 | 2013 | Army Active | 66099 |  | 2012-12-19 | 2015-01-20 | Zieson Construction Company, LLC | W912DQ-14-D-4000 | 6228000 | 6529000 | 2016-05-05 | 2017-02-23
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-12-24 | Burr-MZT Joint Venture | W912DW-14-C-0001 | 919000 | 983000 | 2014-08-04 | 2014-08-01
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775000 | 14633000 | 2014-08-26 | 2015-03-02
2017-07-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-06-20 | Bristol General Contractors, LLC | W912DW-14-C-0015 | 5288000 | 6122000 | 2015-09-10 | 2017-05-26
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6814000 | 7400000 | 2015-08-21 | 2015-10-09
2017-07-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2016-09-08 | Centennial Contractors Enterprises Inc. | W912DW-11-D-1002 | 460000 | 539000 | 2017-06-10 | 2017-06-01
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-08-29 | Alutiiq Diversified Services, LLC | W912DW-12-C-0040 | 10525000 | 13116000 | 2014-03-11 | 2015-07-28
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Bristol General Contractors, LLC | W912DW-12-D-1018 | 1979000 | 2354000 | 2013-05-30 | 2013-11-22
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2012-09-28 | Vet Industrial, Inc. | W912DW-10-D-1021 | 4980000 | 5253000 | 2013-11-01 | 2013-11-25
2016-10-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2013-08-02 | James Talcott Construction, Inc. | W912DW-10-D-1015 | 5769000 | 6297000 | 2014-11-17 | 2015-02-06
2018-08-31 | 2012 | Army Active | 66206 |  | 2012-06-15 | 2016-09-28 | National Native American Construction, Inc. | W912DQ-16-C-4017 | 1325000 | 1422000 | 2017-05-27 | 2017-11-14
2020-08-31 | 2016 | Army Active | 66575 |  | 2016-12-02 | 2017-07-13 | Walga Ross Group JV | W912BV17C0008 | 13191000 | 13707000 | 2018-11-29 | 2020-05-21
2017-07-31 | 2011 | Army Active | 66595 |  | 2011-09-08 | 2015-01-19 | LBB Kaiserslautern | W912GB-09-C-0014 | 30046000 | 30636000 | 2017-09-28 | 2017-09-28
2018-08-31 | 2009 | Army Active | 66725 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7202000 | 7957000 | 2014-06-04 | 2018-02-13
2018-08-31 | 2010 | Army Active | 66726 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757000 | 9269000 | 2014-06-04 | 2018-02-13
2017-04-30 | 2011 | Army Active | 66834 |  | 2010-12-01 | 2011-12-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 16173000 | 20463000 | 2013-12-18 | 2016-01-15
2019-08-31 | 2017 | Army Active | 67029 |  | 2017-05-16 | 2017-08-17 | Speegle Construction, Inc. | W91278-16-D-0031 | 13280000 | 13361000 | 2019-03-15 | 2019-06-29
2017-05-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-12-31 | ALCAN BUILDERS INC. | W911KB-15-C-0001 | 12375000 | 12770000 | 2016-09-06 | 2016-09-26
2016-10-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-04-14 | Arctic-American JV | W911KB-14-C-0008 | 16180000 | 16156000 | 2015-10-15 | 2015-10-15
2016-10-31 | 2014 | Army Active | 67116 |  | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0019 | 14180000 | 14599000 | 2016-02-04 | 2016-05-10
2020-08-31 | 2014 | Army Active | 67157 |  | 2015-05-13 | 2015-08-18 | Watts Constructors, LLC | W9128A-15-C-0003 | 63500000 | 64601000 | 2017-12-13 | 2019-10-28
2019-08-31 | 2012 | Army Active | 68050 |  | 2012-10-19 | 2016-01-15 | Whiting-Turner Contracting Company | W912DR-16-C-0002 | 30470000 | 63939000 | 2018-06-13 | 2019-05-02
2016-11-30 | 2011 | Army Active | 68074 |  | 2013-05-30 | 2013-08-12 | Hessisches Baumanagement Wiesbaden | W912GB-09-C-0059 | 6765000 | 7983000 | 2014-12-12 | 2015-01-09
2021-04-30 | 2013 | Army Active | 68530 |  | 2015-05-02 | 2015-09-23 | Solis Constructors, Inc. | W9126G-14-D-0050 | 37657000 | 55028000 | 2018-12-17 | 2021-07-08
2016-11-30 | 2011 | Army Active | 68606 |  | 2011-09-02 | 2012-10-12 | Bauamt Amberg-Sulzbach | W912GB-09-C-0017 | 18121000 | 18366000 | 2014-05-25 | 2014-06-16
2020-08-31 | 2015 | Army Active | 68826 |  | 2016-03-25 | 2017-06-16 | MW BUILDERS, INC. | W9126G-17-C-0042 | 55741000 | 58325000 | 2019-09-30 | 2020-02-25
2020-08-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-23 | ECC International | W912GB-13-C-0003 | 87011000 | 101141000 | 2015-09-19 | 2019-11-30
2018-07-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2014-06-24 | OBG Engineering GmbH & Co. KG | W912GB-14-D-0019 | 90000 | 90000 | 2014-10-07 | 2014-11-20
2018-07-31 | 2011 | Army Active | 68866 |  | 2008-11-25 | 2013-01-16 | OBG Hochbau GmbH & Co. KG | W912GB-11-D-0036 | 7198000 | 8645000 | 2014-06-25 | 2014-12-04
2016-10-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | W912BV-12-C-0003 | 9573000 | 9590000 | 2013-12-16 | 2014-06-27
2017-03-31 | 2012 | Army Active | 68993 |  | 2011-12-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 5118000 | 5118000 | 2013-09-13 | 2016-11-12
2017-03-31 | 2012 | Army Active | 69286 |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008000 | 8868000 | 2013-09-13 | 2016-11-12
2021-04-30 | 2020 | Army Active | 69347 |  | 2020-02-06 | 2020-05-20 | B.L. Harbert Internationl | W912QR20C0022 | 37142000 | 38522000 | 2022-07-11 | 2022-10-08
2019-08-31 | 2012 | Army Active | 69489 |  | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772000 | 60110000 | 2015-05-27 | 2018-10-30
2021-04-30 | 2015 | Army Active | 70668 |  | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 320692000 | 2021-11-07 | 2022-03-11
2020-07-31 | 2018 | Army Active | 70668 | 58857 | 2016-12-21 | 2018-08-31 | West Coast Contractors of Nevada | DACA05-01-C-0015 | 284440000 | 308770000 | 2022-08-26 | 2022-08-26
2021-04-30 | 2018 | Army Active | 70668 | 58857 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 320692000 | 2021-11-07 | 2022-03-11
2021-04-30 | 2017 | Army Active | 70668 | 76593 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 320692000 | 2021-11-07 | 2022-03-11
2021-04-30 | 2019 | Army Active | 70668 | 76595 | 2016-12-21 | 2017-09-28 | Hensel Phelps Construction Co. | W9128A17C0005 | 284440000 | 320692000 | 2021-11-07 | 2022-03-11
2021-04-30 | 2018 | Army Active | 70677 |  | 2018-02-26 | 2018-09-14 | ACC Construction Co. | W912HN18C3002 | 29857000 | 33143000 | 2020-12-16 | 2021-08-09
2018-04-30 | 2015 | Army Active | 71035 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-11-12 | 2019-11-12
2021-04-30 | 2016 | Army Active | 71057 |  | 2014-08-28 | 2018-07-19 | Kiewit/Manson MOTCO, AJV | W9123818C0015 | 87549000 | 98444000 | 2020-08-01 | 2021-04-30
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Design and Production Incorporated | W912WJ-16-D-0014 | 2206000 | 2206000 | 2017-09-15 | 2018-07-31
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Eisterhold Associates Inc | W912WJ-16-D-0012 | 1749000 | 1749000 | 2017-09-15 | 2018-07-31
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Design and Production Incorporated | W912WJ-11-D-0008 | 55000 | 55000 | 2017-09-15 | 2018-07-31
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | The McGraw-Hill Companies Inc | W912WJ-08-M-0034 | 9000 | 9000 | 2017-09-15 | 2018-07-31
2017-06-30 | 2012 | Army Active | 71149 |  | 2016-05-10 | 2016-08-04 | Eisterhold Associates Inc | W912WJ-08-D-0006 | 12451000 | 12451000 | 2017-09-15 | 2018-07-31
2021-04-30 | 2012 | Army Active | 71149 |  | 2016-08-17 | 2016-08-24 | Shirley Contracting | W912DR-16-C-0030 | 19249000 | 24899000 | 2018-08-17 | 2020-12-25
2017-05-31 | 2014 | Army Active | 71221 |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542000 | 14301000 | 2016-02-18 | 2016-09-28
2019-08-31 | 2011 | Army Active | 71422 |  | 2011-07-18 | 2011-09-14 | LBB Niederlassung Idar-Oberstein | W912GB-09-C-0007 | 34935000 | 32635000 | 2018-07-27 | 2019-04-05
2016-11-30 | 2011 | Army Active | 71472 |  | 2011-03-04 | 2011-08-15 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 18280000 | 19603000 | 2013-03-07 | 2014-07-23
2017-07-31 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2013-09-27 | Contrack Watts, Inc. | W912ER-13-C-0032 | 49413000 | 60476000 | 2015-03-25 | 2016-10-03
2016-10-31 | 2010 | Army Active | 71485 |  | 2013-06-21 | 2014-04-03 | Contrack Watts, Inc. | W912ER-14-C-0011 | 6749000 | 6749000 | 2015-10-30 | 2015-12-08
2017-07-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777000 | 54196000 | 2016-08-04 | 2017-02-23
2017-07-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-18 | Zieson Construction Company, LLC | W912DQ-15-C-4004 | 14313000 | 15213000 | 2016-07-22 | 2017-02-28
2017-07-31 | 2014 | Army Active | 71502 |  | 2014-03-06 | 2014-12-19 | Zieson Construction Co. | W912DQ-14-D-4000 | 4796000 | 5020000 | 2016-01-29 | 2016-11-22
2017-07-31 | 2013 | Army Active | 71675 |  | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751000 | 50161000 | 2016-01-15 | 2017-08-11
2021-04-30 | 2020 | Army Active | 71725 |  | 2020-02-19 | 2020-04-29 | Intec Group, LLC | W912QR20C0019 | 6106000 | 6159000 | 2021-05-12 | 2021-07-09
2019-08-31 | 2017 | Army Active | 71777 |  | 2017-06-16 | 2017-09-30 | McGoldrick Construction Services, Corp. | W9126G17C0111 | 8147000 | 8143000 | 2019-05-22 | 2019-05-29
2020-08-31 | 2017 | Army Active | 72176 |  | 2017-10-16 | 2018-07-09 | HHI Corporation | W9128F18C0017 | 8086000 | 8805000 | 2020-01-30 | 2020-03-23
2020-08-31 | 2018 | Army Active | 72843 |  | 2018-06-21 | 2018-09-29 | Emerson Construction Company, Inc. | W9126G18C0078 | 10453000 | 10771000 | 2020-01-02 | 2020-07-21
2019-09-30 | 2018 | Army Active | 72843 |  | 2018-05-09 | 2018-09-29 | Emerson Construction Company, Inc. | W9126G18C | 0 | 0 | 2020-09-27 | 2020-09-27
2020-08-31 | 2018 | Army Active | 72843 |  | 2018-06-21 | 2018-09-29 | Emerson Construction Company, Inc. | W9126G18C0079 | 9854000 | 10074000 | 2020-01-02 | 2020-07-24
2018-08-31 | 2011 | Army Active | 72854 |  | 2011-05-02 | 2013-01-22 | Garco Construction, Inc. | W912DW-13-C-0020 | 36247000 | 42197000 | 2014-08-07 | 2018-08-23
2018-08-31 | 2015 | Army Active | 73272 |  | 2015-07-23 | 2015-09-28 | Joint forces Construction, LLC | W91236-15-C-0054 | 6350000 | 7722000 | 2016-10-20 | 2017-12-17
2021-04-30 | 2018 | Army Active | 73375 |  | 2018-07-13 | 2018-09-25 | HHI Corporation | W9128F18C0037 | 18943000 | 19040000 | 2020-06-24 | 2020-12-01
2017-07-31 | 2014 | Army Active | 73384 |  | 2015-03-10 | 2016-03-31 | Edifice-Schlosser JV, LLC | W912DR-15-C-0025 | 0 | 3077000 | 2017-03-31 | 2017-03-31
2021-04-30 | 2020 | Army Active | 73391 |  | 2020-06-12 | 2020-09-29 | Purcell Construction | W9123620C2027 | 47269000 | 47269000 | 2022-11-03 | 2022-11-03
2018-04-30 | 2013 | Army Active | 73738 |  | 2016-02-26 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2018-11-28 | 2018-11-28
2018-04-30 | 2015 | Army Active | 74001 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-07 | 2019-06-07
2021-04-30 | 2019 | Army Active | 74618 |  | 2019-02-22 | 2019-05-15 | Relyant Global LLC | W9128F19C0022 | 6560000 | 6633000 | 2020-06-09 | 2020-12-01
2017-07-31 | 2014 | Army Active | 74638 |  | 2013-11-07 | 2015-04-02 | SGS, LLC | W9126G-15-C-0091 | 13978000 | 13894000 | 2017-01-02 | 2017-07-21
2018-04-30 | 2017 | Army Active | 74732 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 9745000 | 9745000 | 2019-06-13 | 2019-06-13
2017-07-31 | 2014 | Army Active | 74861 |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862000 | 27828000 | 2016-08-09 | 2017-08-19
2021-04-30 | 2019 | Army Active | 74989 |  | 2018-11-09 | 2019-03-08 | Carothers | W9126G19C0020 | 22822000 | 23434000 | 2020-10-07 | 2021-06-20
2021-04-30 | 2019 | Army Active | 75157 |  | 2020-05-22 | 2020-08-13 | NASCO | W9126G20C0005 | 8315000 | 8322000 | 2022-02-25 | 2022-03-29
2018-08-31 | 2013 | Army Active | 75165 |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77477000 | 80637000 | 2016-03-02 | 2017-11-30
2019-08-31 | 2015 | Army Active | 75307 |  | 2017-03-15 | 2017-08-22 | Bristol General Contractors, LLC | W9126G-14-D-0061 | 4590000 | 4606000 | 2018-11-04 | 2019-05-31
2018-08-31 | 2015 | Army Active | 75536 |  | 2016-06-15 | 2016-08-18 | Debcon, Inc. | W912QR-16-C-0018 | 22837000 | 24655000 | 2018-03-07 | 2018-09-03
2019-08-31 | 2016 | Army Active | 75538 |  | 2016-08-02 | 2016-09-29 | Atherton Construction, LLC | W912QR-16-C-0026 | 23347000 | 25553000 | 2018-04-10 | 2018-10-19
2021-04-30 | 2017 | Army Active | 75660 |  | 2018-02-28 | 2018-12-21 | Zodiac-Poettker Joint Venture II, LLC | W912DQ19C4000 | 8690000 | 9021000 | 2020-02-05 | 2020-11-20
2021-04-30 | 2016 | Army Active | 75661 |  | 2017-11-30 | 2018-12-14 | Harper Construction | W912BV19C0003 | 59467000 | 59467000 | 2020-12-26 | 2021-05-03
2021-04-30 | 2018 | Army Active | 75718 |  | 2018-07-02 | 2019-05-09 | Tocci Building Corporation | W912WJ19C0011 | 20612000 | 26280000 | 2021-06-02 | 2021-12-26
2019-08-31 | 2017 | Army Active | 75893 |  | 2017-08-28 | 2017-09-29 | Medvolt, LLC | W9128F17C0047 | 5150000 | 5120000 | 2018-11-29 | 2018-12-10
2020-09-30 | 2016 | Army Active | 75906 |  | 2018-06-08 | 2018-09-28 | Adirondack Construction, A Division of VMJR Companies LLC. | W912DS18C0014 | 7400000 | 7783000 | 2019-12-16 | 2020-09-16
2017-07-31 | 2014 | Army Active | 76024 |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630000 | 16706000 | 2016-02-24 | 2017-04-20
2018-08-31 | 2014 | Army Active | 76024 |  | 2014-02-28 | 2017-09-26 | Tenoch Construction | W912DQ-17-D-4004 | 250000 | 250000 | 2018-09-24 | 2018-09-24
2018-08-31 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2016-09-28 | Herman Construction Group, Inc. | W91238-15-D-0015 | 2623000 | 2897000 | 2018-05-30 | 2018-09-14
2016-10-31 | 2013 | Army Active | 76086 |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072000 | 3140000 | 2015-11-10 | 2016-06-03
2019-08-31 | 2015 | Army Active | 76087 |  | 2015-06-01 | 2015-09-30 | GEMS Environmental Management Services, Inc. | W91238-15-D-0014 | 4860000 | 4924000 | 2017-03-31 | 2019-01-31
2021-04-30 | 2015 | Army Active | 76093 |  | 2018-06-29 | 2019-05-31 | ARS Aleut Construction | W9123819C0015 | 8916000 | 9903000 | 2020-06-02 | 2021-06-11
2017-07-31 | 2013 | Army Active | 76196 |  | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25853000 | 29398000 | 2015-06-09 | 2017-04-28
2017-07-31 | 2013 | Army Active | 76586 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717000 | 33295000 | 2015-09-01 | 2017-01-13
2017-07-31 | 2013 | Army Active | 76587 |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410000 | 42391000 | 2015-09-01 | 2017-01-13
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25547000 | 26284000 | 2016-03-21 | 2016-09-29
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-08 | C.I. Contractors INC. | W911KB-14-C-0010 | 5007000 | 6855000 | 2015-04-17 | 2016-07-25
2016-10-31 | 2014 | Army Active | 76601 |  | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC | W911KB-14-C-0005 | 9525000 | 10101000 | 2015-10-16 | 2016-08-29
2021-04-30 | 2020 | Army Active | 76673 |  | 2020-06-29 | 2020-11-10 | Turner Construction Company | W9127821C0006 | 34050000 | 34050000 | 2022-12-25 | 2022-12-25
2016-10-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2012-05-29 | MW Builders, Inc. | W9126G-08-D-0044 | 24162000 | 24502000 | 2013-12-31 | 2014-02-18
2017-07-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2016-09-09 | Centennial Contractors Enterprises Inc. | W912DW-11-D-1002 | 36000 | 36000 | 2017-01-18 | 2017-01-23
2016-10-31 | 2012 | Army Active | 76767 |  | 2011-12-19 | 2014-03-19 | TSS-Garco Joint Venture | W912DW-14-C-0004 | 6360000 | 7003000 | 2015-08-21 | 2015-10-09
2017-07-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2014-04-08 | Glen/Mar Construction, Inc. | W912DW-14-C-0009 | 4771000 | 5945000 | 2015-05-21 | 2017-06-22
2017-07-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2016-09-13 | Centennial Contractors Enterprises, Inc. | W912DW-11-D-1002 | 146000 | 146000 | 2017-05-06 | 2017-04-28
2016-10-31 | 2012 | Army Active | 76768 |  | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | W912DW-12-C-0051 | 25901000 | 27950000 | 2014-05-23 | 2014-10-14
2018-08-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-04-09 | Walsh Group Ventures | W912DW-15-C-0002 | 11319000 | 12682000 | 2017-07-06 | 2018-09-07
2019-08-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2016-09-20 | WHH Nisqually-Garco Joint Venture | W912DW-16-C-0020 | 12390000 | 13506000 | 2018-05-11 | 2018-10-31
2020-08-31 | 2014 | Army Active | 76776 |  | 2014-07-18 | 2015-07-09 | Vet Industrial, Inc. | W912DW-15-C-0007 | 11893000 | 13761000 | 2016-08-24 | 2019-10-29
2021-04-30 | 2014 | Army Active | 76777 |  | 2014-05-19 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 23706000 | 25623000 | 2017-07-06 | 2020-11-13
2018-08-31 | 2013 | Army Active | 76903 |  | 2012-11-26 | 2014-05-13 | Nan-Samsung | W9128A-14-C-0002 | 69749000 | 71376000 | 2017-01-13 | 2017-12-12
2021-04-30 | 2018 | Army Active | 77102 |  | 2018-03-15 | 2018-09-21 | Creative Times Dayschool, Inc | W912PL-18-C-0036 | 20265000 | 23227000 | 2020-06-05 | 2021-06-22
2017-07-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2016-04-12 | AMIDON, INC. | W9126G-16-C-0030 | 3163000 | 3096000 | 2016-12-07 | 2017-02-26
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | STREETER-SUMMIT JV 1, LLC | W9126G-12-C-0019 | 3750000 | 1013000 | 2014-02-15 | 2013-08-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2013-12-04 | Solis Constructors, Inc | W9126G-14-C-0006 | 0 | 0 | 2015-01-25 | 2016-03-31
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-28 | RMA Land Construction, Inc. | W9126G-09-D-0100 | 5379000 | 4709000 | 2013-06-21 | 2014-05-13
2016-10-31 | 2012 | Army Active | 77187 |  | 2011-12-15 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7473000 | 8035000 | 2013-12-14 | 2016-06-13
2017-07-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165000 | 17853000 | 2016-02-12 | 2017-07-26
2017-07-31 | 2014 | Army Active | 77262 |  | 2014-02-28 | 2014-08-28 | Medvolt, LLC | W9128F-14-C-0054 | 13195000 | 13994000 | 2016-03-31 | 2016-06-03
2021-04-30 | 2019 | Army Active | 77301 |  | 2019-04-03 | 2019-08-09 | Federal/Bryan | W9128F19C0029 | 69147000 | 70224000 | 2021-05-04 | 2021-11-03
2021-04-30 | 2020 | Army Active | 77303 |  | 2020-02-28 | 2020-06-19 | TEPA EC | W9128F20C0029 | 46209000 | 46411000 | 2022-06-12 | 2022-07-19
2016-10-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | Hartland/Mass JV LLC | W9128F-13-D-0014 | 3339000 | 3566000 | 2015-10-20 | 2016-01-05
2017-05-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-09-04 | John Bowman, Inc. | W9128F-13-D-0013 | 2288000 | 2329000 | 2015-10-07 | 2015-12-17
2017-05-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-07-16 | SEK JV | W9128F-13-D-0015 | 3133000 | 3596000 | 2015-02-14 | 2015-07-07
2017-07-31 | 2014 | Army Active | 77304 |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56721000 | 59762000 | 2016-08-22 | 2017-05-31
2021-04-30 | 2015 | Army Active | 77305 |  | 2016-05-23 | 2017-09-11 | Straub Construction, INC | W9128F-17-C-0032 | 61936000 | 62889000 | 2019-06-02 | 2021-03-25
2017-07-31 | 2015 | Army Active | 77305 |  | 2016-05-23 | 2016-05-28 | Francisco Semsch, Architect, Inc. | W9128F-15-C-0010 | 3848000 | 3848000 | 2016-06-15 | 2016-11-21
2016-10-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2015-01-16 | Agile Infrastructure Services, L.L.C. | W9128F-15-C-0002 | 2843000 | 2902000 | 2016-02-11 | 2016-07-14
2017-07-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-07-19 | Blackhorse Worldwide LLC | W9128F-13-D-0016 | 4214000 | 4715000 | 2015-07-22 | 2016-01-14
2017-07-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 891000 | 891000 | 2016-08-22 | 2017-05-31
2018-08-31 | 2014 | Army Active | 77405 |  | 2014-07-09 | 2014-08-06 | David Boland, Inc. | W9128F-14-C-0068 | 50585000 | 53110000 | 2016-05-28 | 2017-11-28
2017-07-31 | 2013 | Army Active | 77419 |  | 2014-05-29 | 2014-11-06 | Caddell Construction Co. (DE) LLC | W912HN-10-D-0044 | 10400000 | 11033000 | 2016-12-26 | 2017-07-21
2021-04-30 | 2017 | Army Active | 77538 |  | 2018-02-12 | 2018-07-09 | GEC-HHI Joint Venture | W9123818C0020 | 7970000 | 10409000 | 2020-02-22 | 2022-01-23
2021-04-30 | 2020 | Army Active | 77728 |  | 2020-02-07 | 2020-06-26 | Walsh Federal, LLC | W912DW20C0007 | 38027000 | 38084000 | 2022-12-31 | 2022-12-31
2021-04-30 | 2018 | Army Active | 77779 |  | 2018-06-22 | 2019-06-06 | S.B. Ballard Construction Company | W9123619C0014 | 40458000 | 40812000 | 2021-02-15 | 2021-06-11
2019-04-30 | 2015 | Army Active | 77831 |  | 2018-02-26 |  |  | 406796 | 0 | 0 | 2020-12-02 | 2020-12-02
2021-04-30 | 2015 | Army Active | 77831 |  | 2018-02-26 | 2019-05-07 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV16D0009 | 18324000 | 18905000 | 2021-05-25 | 2021-05-25
2017-04-30 | 2014 | Army Active | 77885 |  | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9833000 | 12527000 | 2015-07-01 | 2016-07-29
2017-07-31 | 2013 | Army Active | 78054 |  | 2014-07-08 | 2015-03-17 | Akima Construction Services, LLC | W912DR-15-C-0013 | 3358000 | 11102000 | 2016-09-24 | 2017-02-21
2018-08-31 | 2014 | Army Active | 78196 |  | 2015-08-07 | 2016-09-21 | Veterans Northwest Construction LLC | W912DW-16-C-0016 | 11120000 | 11437000 | 2018-04-05 | 2018-08-10
2021-04-30 | 2014 | Army Active | 78196 |  | 2015-08-07 | 2015-11-17 | Jabez-Absher Small Business Joint Venture | W912DW-16-C-0001 | 20099000 | 20818000 | 2017-07-06 | 2020-11-13
2018-08-31 | 2016 | Army Active | 78366 |  | 2016-08-24 | 2016-09-27 | Mickan Generalbaugesellschaft Amberg | W912GB-15-D-0072 | 2694000 | 2784000 | 2017-12-09 | 2018-04-20
2017-07-31 | 2012 | Army Active | 78475 |  | 2013-05-22 | 2014-11-18 | Klebl GmbH | W912GB-15-C-0003 | 14632000 | 15338000 | 2016-09-27 | 2017-04-21
2017-05-31 | 2012 | Army Active | 78505 |  | 2012-04-06 | 2013-08-07 | Staatliches Hochbauamt Amberg | W912GB-11-C-0027 | 13548000 | 13863000 | 2015-09-14 | 2016-02-17
2021-04-30 | 2014 | Army Active | 78712 |  | 2016-08-15 | 2017-08-08 | Staatliches Hochbauamt Amberg | W912GB-12-C-0012 | 20384000 | 20292000 | 2019-11-25 | 2021-05-31
2021-04-30 | 2019 | Army Active | 78804 |  | 2020-06-03 | 2020-12-04 | DOBCO GROUP, INC. | W912DS21C0002 | 186676000 | 186822000 | 2025-01-04 | 2025-01-04
2017-07-31 | 2014 | Army Active | 79618 |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440000 | 9567000 | 2016-02-11 | 2017-03-27
2017-07-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-08-30 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129000 | 12355000 | 2014-11-30 | 2017-07-15
2016-10-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2012-07-05 | EMTA CONSTRUCTION CO. INC. | W912GB-10-D-0020 | 320000 | 320000 | 2012-11-22 | 2012-11-22
2016-10-31 | 2012 | Army Active | 79749 |  | 2012-06-15 | 2013-03-19 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. | W912GB-12-D-0035 | 199000 | 199000 | 2013-10-16 | 2013-10-17
2017-07-31 | 2013 | Army Active | 79933 |  | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 169650000 | 2016-08-30 | 2017-02-07
2017-07-31 | 2014 | Army Active | 79933 | 81186 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 169650000 | 2016-08-30 | 2017-02-07
2017-07-31 | 2015 | Army Active | 79933 | 81187 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 163402000 | 169650000 | 2016-08-30 | 2017-02-07
2020-08-31 | 2016 | Army Active | 80037 |  | 2018-06-08 | 2018-09-20 | Old North Utility Services | W912PM18C0023 | 3036000 | 3119000 | 2019-07-13 | 2019-11-21
2017-07-31 | 2013 | Army Active | 80112 |  | 2014-12-02 | 2015-04-23 | Sauer Inc. | W91278-12-D-0039 | 10965000 | 11567000 | 2016-07-19 | 2016-11-01
2018-08-31 | 2012 | Army Active | 80231 |  | 2013-06-03 | 2014-09-28 | East Coast Utility Contractors | W912DR-14-C-0041 | 1484000 | 2471000 | 2015-11-03 | 2018-02-08
2017-05-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-11-25 | Upstate Construction Services, Inc. | W912DS-09-D-0005 | 17287000 | 17827000 | 2015-12-02 | 2016-05-30
2018-08-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 39587000 | 42451000 | 2015-06-17 | 2018-02-23
2018-08-31 | 2013 | Army Active | 80246 |  | 2012-12-12 | 2013-06-17 | Black Horse Group LLC | W912DS-09-D-0004 | 21578000 | 24664000 | 2015-06-22 | 2017-11-30
2017-07-31 | 2013 | Army Active | 80317 |  | 2013-08-14 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1791000 | 1771000 | 2014-09-10 | 2016-11-30
2018-04-30 | 2015 | Army Active | 80353 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2017-07-31 | 2014 | Army Active | 80433 |  | 2015-06-11 | 2015-09-22 | K.L. House Construction Co. | W9128F-15-C-0028 | 3423000 | 3435000 | 2016-10-26 | 2017-03-22
2018-09-30 | 2015 | Army Active | 80666 |  | 2016-06-15 | 2016-08-23 | CORE Engineering & Construction, Inc. | W91278-16-D-0014 | 3213000 | 3488000 | 2018-04-19 | 2018-09-26
2021-04-30 | 2018 | Army Active | 80748 |  | 2018-08-07 | 2019-01-25 | Nicklaus Engineering, Inc | W912PL19C0007 | 3994000 | 3994000 | 2021-04-15 | 2021-04-15
2019-08-31 | 2016 | Army Active | 80851 |  | 2016-10-27 | 2017-03-03 | S.B. Ballard Construction Company | W91236-17-C-0003 | 28181000 | 29419000 | 2018-12-14 | 2018-12-14
2020-08-31 | 2018 | Army Active | 80855 |  | 2018-03-05 | 2018-07-10 | ACC Construction Company, Inc. | W912HN18C3001 | 17474000 | 18441000 | 2020-02-05 | 2020-07-30
2017-07-31 | 2014 | Army Active | 80992 |  | 2015-02-06 | 2015-03-24 | Red One Construction, LLC | W9128A-15-C-0002 | 1696000 | 1696000 | 2016-10-20 | 2017-01-25
2019-08-31 | 2015 | Army Active | 81230 |  | 2015-05-08 | 2015-07-27 | Yojin Construction & Engineering Co., Ltd. | W912UM-15-C-0015 | 43753000 | 44988000 | 2018-04-28 | 2019-01-31
2021-04-30 | 2015 | Army Active | 81234 |  | 2017-02-15 | 2018-09-14 | Aegis Security Insurance Company | W9126G-17-C-0046 | 2580000 | 2708000 | 2019-09-27 | 2021-11-19
2021-04-30 | 2015 | Army Active | 81236 |  | 2017-09-28 | 2020-06-23 | LBB Landau | W912GB-16-C-0003 | 2579000 | 2693000 | 2021-05-31 | 2021-08-05
2018-11-30 | 2015 | Army Active | 81242 |  | 2015-08-19 | 2015-09-27 | BIC-SCC JV, LLC | W91278-13-D-0003 | 1740000 | 2208000 | 2016-10-27 | 2018-09-07
2020-11-30 | 2018 | Army Active | 81283 |  | 2018-08-23 | 2018-11-02 | Faith Enterprises Incorporated | W9128F19C0002 | 7936000 | 8088000 | 2020-04-06 | 2020-12-01
2021-04-30 | 2019 | Army Active | 81316 |  | 2020-03-10 | 2020-06-23 | Anna Lisa Luna Construction, Inc. | W912PL20C0019 | 5481000 | 5481000 | 2021-08-18 | 2021-08-18
2019-09-30 | 2017 | Army Active | 81347 |  | 2016-10-17 | 2017-04-19 | UNIT | W911KB-17-C-0010 | 33123000 | 37120000 | 2018-11-15 | 2019-10-01
2018-08-31 | 2015 | Army Active | 81349 |  | 2015-02-20 | 2015-06-04 | Upstate Construction Services, Inc. | W912DS-15-C-0008 | 19408000 | 20284000 | 2016-12-18 | 2017-12-31
2017-07-31 | 2015 | Army Active | 81357 |  | 2014-04-13 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 0 | 804000 | 2015-07-01 | 2016-07-29
2017-07-31 | 2015 | Army Active | 81357 |  | 2015-04-13 | 2015-07-07 | David Boland, Inc. | W9128F-15-C-0017 | 26149000 | 26299000 | 2017-01-18 | 2017-06-16
2017-07-31 | 2014 | Army Active | 81424 |  | 2015-07-21 | 2015-09-30 | Southeast Cherokee Construction,Inc. | W91278-10-D-0064 | 3562000 | 3663000 | 2017-02-02 | 2017-03-24
2020-08-31 | 2016 | Army Active | 81427 |  | 2016-07-14 | 2016-09-08 | Daebo Engr. & Const. Co., Ltd | W912UM-16-C-0034 | 44367000 | 44366000 | 2019-02-24 | 2020-02-25
2020-08-31 | 2017 | Army Active | 81428 |  | 2017-06-16 | 2017-08-25 | Hwasan Engineering & construction Co., Ltd. | W912UM17C0043 | 91514000 | 5760000 | 2020-02-25 | 2018-12-31
2021-04-30 | 2017 | Army Active | 81428 |  | 2019-03-21 | 2019-06-03 | Daebo E & C | W912UM19C0015 | 43171000 | 50406000 | 2021-07-14 | 2021-09-16
2021-04-30 | 2019 | Army Active | 81429 |  | 2019-07-22 | 2019-10-30 | Daebo Engineering & Construction Co., Ltd. | W912UM20C0001 | 54939000 | 54741000 | 2022-09-05 | 2022-09-24
2017-07-31 | 2013 | Army Active | 81462 |  | 2014-08-21 | 2014-09-30 | Nan, Inc., dba Ocean House Builders | W9128A-12-D-0012 | 1556000 | 1664000 | 2015-10-23 | 2016-12-01
2021-04-30 | 2014 | Army Active | 81987 |  | 2017-06-08 | 2017-09-28 | CONTRACK WATTS-UEJO KOGYO JV | W912HV-17-D-0013 | 58908000 | 65889000 | 2019-11-22 | 2021-03-19
2019-08-31 | 2016 | Army Active | 82094 |  | 2017-03-28 | 2017-09-29 | Call Associates, Inc. | W912DS17C0013 | 1934000 | 2071000 | 2019-04-11 | 2019-06-10
2021-04-30 | 2019 | Army Active | 82254 |  | 2019-06-18 | 2019-09-30 | ACC Construction Company, Inc. | W912PM19C0043 | 9649000 | 9669000 | 2021-06-30 | 2021-07-19
2021-04-30 | 2019 | Army Active | 82337 |  | 2019-06-28 | 2020-01-16 | National Native American Construction Inc. | W912DW19C0016 | 3869000 | 3909000 | 2021-04-07 | 2021-04-26
2017-07-31 | 2014 | Army Active | 82394 |  | 2015-03-04 | 2015-12-31 | Red Cedar Enterprises, Inc. | W912BV-13-D-0011 | 2690000 | 2730000 | 2017-02-12 | 2017-07-12
2017-01-31 | 2014 | Army Active | 85260 |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1725000 | 1771000 | 2015-11-05 | 2016-01-13
2018-04-30 | 2015 | Army Active | 85683 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2019-08-31 | 2016 | Army Active | 85710 |  | 2016-10-27 | 2017-02-01 | American West Construction, LLC | W9128F-17-C-0015 | 5882000 | 6132000 | 2018-08-22 | 2018-11-07
2021-04-30 | 2015 | Army Active | 85711 |  | 2017-05-09 | 2017-09-28 | BRYAN 77 CONSTRUCTION JV | W912GB17C0019 | 15238000 | 17739000 | 2020-12-09 | 2021-12-23
2021-04-30 | 2017 | Army Active | 85794 |  | 2018-05-25 | 2019-01-18 | Odyssey International | W912HN19C3000 | 14000000 | 14425000 | 2020-06-14 | 2021-05-31
2018-04-30 | 2016 | Army Active | 85808 |  | 2016-10-18 | 2017-04-25 | Martin Brothers Construction | W912QR-17-C-0014 | 2603000 | 2603000 | 2018-05-08 | 2018-05-08
2019-08-31 | 2016 | Army Active | 85811 |  | 2016-02-12 | 2016-08-29 | B.L. Harbert International, LLC | W912HN-16-C-0014 | 85289000 | 95061000 | 2018-07-23 | 2019-05-14
2019-08-31 | 2014 | Army Active | 85817 |  | 2015-09-22 | 2016-04-07 | LBB Landau | W912GB-14-C-0020 | 1685000 | 1924000 | 2016-08-25 | 2016-11-15
2020-08-31 | 2017 | Army Active | 85818 |  | 2016-02-12 | 2016-08-29 | B.L. Harbert International, LLC | W912HN-16-C-0014 | 0 | 79998000 | 2020-02-10 | 2020-01-22
2021-04-30 | 2015 | Army Active | 86094 |  | 2019-02-11 | 2020-04-01 | Staatliches Hochbauamt Amberg | W912GB-16-C-0006 | 2418000 | 2653000 | 2021-09-05 | 2021-09-10
2021-04-30 | 2015 | Army Active | 86404 |  | 2017-05-09 | 2017-09-26 | MICHAEL M.TSONTOS S.A. | W912GB17D0015 | 6121000 | 6301000 | 2019-12-13 | 2021-12-02
2018-08-31 | 2015 | Army Active | 86405 |  | 2017-05-09 | 2017-09-26 | BRYAN 77 CONSTRUCTION JV | W912GB17C0020 | 13113216 | 13113216 | 2021-05-08 | 2021-05-08
2020-08-31 | 2016 | Army Active | 86408 |  | 2016-09-16 | 2016-09-26 | Fidelity and Deposit Company of Maryland | W912DY-14-D-0007 | 13930000 | 15559000 | 2018-12-07 | 2020-01-09
2020-08-31 | 2015 | Army Active | 86414 |  | 2018-08-09 | 2018-10-05 | Oddo Construction Services LLC | W912DS19C0002 | 3260000 | 3933000 | 2020-03-06 | 2020-12-01
2020-08-31 | 2017 | Army Active | 86442 |  | 2018-06-19 | 2018-11-08 | Anchor-41 Construction, LLC | W912PL19C0004 | 3757000 | 3938000 | 2020-06-06 | 2020-06-11
2021-04-30 | 2018 | Army Active | 86479 |  | 2018-06-25 | 2018-09-25 | Gilbane Federal | W912HN18C3003 | 12255000 | 12784000 | 2020-03-21 | 2020-10-04
2021-04-30 | 2018 | Army Active | 86518 |  | 2019-04-24 | 2019-07-17 | Doyon Management Services, LLC | W912DW19C0012 | 5076000 | 5239000 | 2020-08-15 | 2021-06-02
2021-04-30 | 2017 | Army Active | 86689 |  | 2017-06-13 | 2017-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM17C0044 | 382205000 | 387338000 | 2020-11-12 | 2021-07-24
2021-04-30 | 2019 | Army Active | 86689 | 86877 | 2018-10-10 | 2019-02-26 | Yojin | W912UM19C0007 | 382205000 | 387338000 | 2022-07-25 | 2023-01-13
2021-04-30 | 2018 | Army Active | 86689 | 91380 | 2018-07-27 | 2018-08-31 | Daewoo Engineering & Construction. Co., Ltd. | W912UM17C0044 | 382205000 | 387338000 | 2020-11-12 | 2021-07-24
2021-04-30 | 2018 | Army Active | 86711 |  | 2018-11-08 | 2019-02-08 | Windamir Development | W912HN19C3001 | 2854000 | 2889000 | 2020-05-13 | 2021-03-16
2021-04-30 | 2018 | Army Active | 86711 |  | 2018-11-08 | 2019-05-24 | Canoochee EMC | DACA87-01-D-0014 | 8000 | 8000 | 2020-07-21 | 2021-02-19
2019-08-31 | 2017 | Army Active | 86745 |  | 2017-08-05 | 2017-09-20 | Mickan Generalbaugesellschaft Amberg | W912GB-17-D-0010 | 139000 | 252000 | 2018-01-11 | 2019-09-28
2019-08-31 | 2015 | Army Active | 86787 |  | 2017-03-29 | 2017-06-02 | Holland and Holland, Inc. | W912HN-17-C-0007 | 2638000 | 2655000 | 2018-07-21 | 2019-03-15
2021-04-30 | 2018 | Army Active | 86816 |  | 2019-03-21 | 2019-09-10 | The Robins & Morton Group | W9127819C0024 | 32995000 | 33564000 | 2021-10-10 | 2022-03-08
2021-04-30 | 2016 | Army Active | 86824 |  | 2019-04-08 | 2019-04-18 | Staatliches Hochbauamt Amberg | W912GB-15-C-0007 | 42195000 | 44832000 | 2022-05-01 | 2023-08-24
2021-04-30 | 2018 | Army Active | 86832 |  | 2018-04-24 | 2018-08-15 | Aytekin-Serol Eng Cons Trade Co. LTD. | W912GB-15-D-0084 | 4004000 | 4004000 | 2022-03-25 | 2023-07-04
2018-09-30 | 2015 | Army Active | 86859 |  | 2016-07-15 | 2016-09-15 | ETERNA | W91278-13-D-0020 | 1400000 | 1430000 | 2018-04-26 | 2018-10-15
2021-04-30 | 2016 | Army Active | 86914 |  | 2017-07-03 | 2017-08-30 | Nan, Inc., dba Ocean House Builders | W9128A-12-D-0012 | 2523000 | 2573000 | 2018-12-12 | 2021-06-11
2021-04-30 | 2018 | Army Active | 86991 |  | 2019-03-28 | 2020-01-27 | Landesbetrieb Bau und Immobilien Hessen Zentrale | W912GB-17-C-0002 | 43508000 | 43702000 | 2022-06-22 | 2023-03-19
2021-04-30 | 2018 | Army Active | 87205 |  | 2020-02-25 | 2020-04-30 | Allen-Batchelor Construction Co., Inc. | W912HN20C3004 | 6187000 | 6187000 | 2022-08-20 | 2022-08-20
2019-08-31 | 2017 | Army Active | 87309 |  | 2017-08-07 | 2017-09-26 | ETERNA | W91278-16-D-0102 | 2440000 | 2462000 | 2019-08-07 | 2019-10-06
2018-08-31 | 2016 | Army Active | 87419 |  | 2017-08-22 | 2017-12-15 | Innovative Construction & Design, LTD | W912DW18C0001 | 2315000 | 2393000 | 2018-09-27 | 2018-09-27
2019-08-31 | 2016 | Army Active | 87892 |  | 2017-05-23 | 2017-09-29 | KUNJI CONSTRUCTION CORPORATION | W912DS17C0012 | 2650000 | 2650000 | 2019-04-26 | 2019-04-29
2021-04-30 | 2020 | Army Active | 87933 |  | 2020-03-06 | 2020-09-25 | Structural Associates, Inc. | W912DS20C0025 | 21732000 | 21736000 | 2022-10-11 | 2022-10-11
2021-04-30 | 2016 | Army Active | 87980 |  | 2019-02-12 | 2019-11-12 | C&C Contractors | W912HN20C3001 | 5155000 | 5230000 | 2021-01-09 | 2021-05-26
2021-04-30 | 2018 | Army Active | 88028 |  | 2018-10-03 | 2018-12-06 | Fortis Networks, Inc. | W912DQ17D4016 | 1979000 | 1990000 | 2020-02-25 | 2020-09-29
2019-08-31 | 2016 | Army Active | 88047 |  | 2017-07-17 | 2018-02-27 | Harbor Enterprises, Limited Liability Company | W912HN18C3000 | 2590000 | 2594000 | 2019-03-19 | 2019-05-11
2021-04-30 | 2020 | Army Active | 88077 |  | 2019-11-20 | 2020-03-09 | Manhattan Construction Company | W912DR20C0007 | 76399000 | 79283000 | 2023-04-01 | 2023-03-31
2021-04-30 | 2016 | Army Active | 88231 |  | 2018-08-20 | 2019-04-01 | Call Associates, Inc | W912DS19C0008 | 4185000 | 5123000 | 2020-04-25 | 2020-11-20
2019-08-31 | 2017 | Army Active | 88369 |  | 2017-08-11 | 2017-09-28 | Mohawk Valley Utility | W912WJ17C0025 | 1796000 | 2188000 | 2018-10-13 | 2019-05-01
2021-04-30 | 2018 | Army Active | 88380 |  | 2019-06-18 | 2019-09-05 | M.W. Builders | W9126G19C0119 | 30477000 | 36004000 | 2021-08-15 | 2021-11-17
2019-08-31 | 2016 | Army Active | 88386 |  | 2017-05-26 | 2017-08-31 | Olgoonik Diversified Services, LLC | W912DQ17C4005 | 2780000 | 2879000 | 2018-09-20 | 2019-01-24
2017-09-30 | 2016 | Army Active | 88386 |  | 2017-05-26 | 2017-08-31 | Olgoonik Diversified Services, LLC | W912DQ-17-C-4005 | 2780000 | 2780000 | 2018-09-20 | 2018-09-20
2021-04-30 | 2019 | Army Active | 88542 |  | 2019-06-24 | 2019-09-25 | EIFFAGE INFRAESTRUCTURAS SA | W912GB19D0039 | 11399000 | 11399000 | 2022-04-17 | 2022-03-21
2018-03-31 | 2017 | Army Active | 88722 |  | 2017-01-12 | 2017-04-14 | OAC Action Contruction, Corp | W912QR-17-C-0012 | 2202000 | 2202000 | 2018-07-13 | 2018-06-13
2021-04-30 | 2019 | Army Active | 88724 |  | 2019-05-31 | 2020-06-19 | Gilbane Federal | W912HN20C3006 | 193807000 | 194997000 | 2022-07-07 | 2022-10-11
2021-04-30 | 2020 | Army Active | 88725 |  | 2020-12-02 | 2021-04-02 | J. KOKOLAKIS CONTRACTING | W912HN21C3003 | 112377000 | 112377000 | 2024-04-19 | 2024-04-19
2021-04-30 | 2018 | Army Active | 88844 |  | 2019-05-14 | 2019-11-12 | Tarver Land Development, LLC | W9126G20C0004 | 3999000 | 3999000 | 2021-01-15 | 2021-06-01
2021-04-30 | 2020 | Army Active | 89057 |  | 2020-01-16 | 2020-05-29 | Sauer | W912PM20C0014 | 10480000 | 10482000 | 2022-03-10 | 2022-03-10
2021-04-30 | 2018 | Army Active | 89128 |  | 2018-11-29 | 2019-03-08 | Windamir Development | W912HN19C3004 | 3402000 | 3548000 | 2020-07-26 | 2021-06-15
2021-04-30 | 2019 | Army Active | 89203 |  | 2019-07-29 | 2019-10-07 | GBA Builders, LLC. | W912DQ20C4000 | 2714000 | 4499000 | 2020-12-02 | 2020-12-14
2021-04-30 | 2017 | Army Active | 89215 |  | 2019-02-12 | 2019-11-13 | C&C Contractors | W912HN20C3002 | 4996000 | 5081000 | 2021-01-09 | 2021-05-23
2021-04-30 | 2019 | Army Active | 89227 |  | 2019-06-18 | 2019-08-19 | Heritage General Contracting | W911KB-17-D-0010 | 6390000 | 6751000 | 2020-11-21 | 2021-03-09
2021-04-30 | 2018 | Army Active | 89235 |  | 2018-07-31 | 2018-09-12 | Sagres Construction Corporation | W912DR18C0046 | 10980000 | 11534000 | 2020-07-05 | 2020-07-05
2017-07-31 | 2016 | Army Active | 89734 |  | 2016-08-15 | 2016-09-29 | TEYA SERVICES LLC | W912HN-16-C-0026 | 1874000 | 1874000 | 2017-05-16 | 2017-05-16
2021-04-30 | 2018 | Army Active | 89821 |  | 2019-05-28 | 2019-11-27 | Southeast Cherokee Construction, Inc. | W91278-16-D-0015 | 5391000 | 5726000 | 2021-07-14 | 2021-07-14
2021-04-30 | 2019 | Army Active | 89831 |  | 2019-09-05 | 2020-01-24 | Nahdhat Al Omma Est. for Gen. Trad. Co | W912ER20C0007 | 2278000 | 2278000 | 2021-03-17 | 2021-03-03
2018-08-31 | 2015 | Army Active | 8984 |  | 2016-03-17 | 2016-09-19 | Orocon - Carothers JV3 | W912QR-16-C-0017 | 13304000 | 13432000 | 2018-04-11 | 2018-08-02
2021-04-30 | 2018 | Army Active | 89946 |  | 2019-10-29 | 2020-01-31 | CCI Utility and Construction Services, LLC | W9127820C0008 | 5292000 | 5387000 | 2021-05-28 | 2021-06-03
2021-04-30 | 2018 | Army Active | 90351 |  | 2020-09-18 | 2021-03-19 | AMG | W912PL21C0007 | 26473000 | 26473000 | 2023-02-10 | 2021-12-21
2021-04-30 | 2018 | Army Active | 90722 |  | 2019-07-11 | 2019-08-30 | Intercontinental Construction Contracting, INC. | W912DS19C0018 | 14893000 | 16410000 | 2021-09-01 | 2022-04-06
2021-04-30 | 2018 | Army Active | 91252 |  | 2019-05-10 | 2019-08-14 | Crowder Construction Company | W912PM19C0027 | 3864000 | 3864000 | 2021-05-15 | 2022-02-11
2021-04-30 | 2019 | Army Active | 91311 |  | 2019-07-02 | 2019-08-26 | TDX Quality, LLC | W912HN19C3010 | 3463000 | 3467000 | 2020-12-10 | 2021-04-26
2021-04-30 | 2020 | Army Active | 91328 |  | 2020-06-25 | 2020-09-15 | Weldin Construction, LLC | W912BV17D0017 | 4623000 | 4623000 | 2021-11-09 | 2021-11-09
2020-08-31 | 2018 | Army Active | 91359 |  | 2018-07-18 | 2018-09-28 | CMGC Building Corporation | W912WJ18C0035 | 2254000 | 2510000 | 2019-10-27 | 2020-05-31
2021-04-30 | 2019 | Army Active | 91360 |  | 2019-05-24 | 2019-08-15 | Monument Construction, LLC | W912WJ18D0004 | 2323000 | 2472000 | 2020-10-03 | 2020-10-03
2021-04-30 | 2020 | Army Active | 91397 |  | 2020-08-13 | 2020-09-24 | A.R. CHESSON CONSTRUCTION COMPANY | W912HN20C3011 | 7034000 | 7034000 | 2021-11-15 | 2021-12-22
2021-04-30 | 2018 | Army Active | 91528 |  | 2019-01-15 | 2019-06-18 | Ral Investment Corporation | W912PL19C0017 | 5099000 | 5248000 | 2020-10-02 | 2021-05-18
2021-04-30 | 2018 | Army Active | 91732 |  | 2018-07-30 | 2018-09-28 | MICHAEL M.TSONTOS S.A. | W912GB17D0015 | 844000 | 1038000 | 2020-10-24 | 2021-10-30
2021-04-30 | 2018 | Army Active | 91742 |  | 2019-05-17 | 2019-09-05 | Nakasato Contracting, LLC | W9128A19C0006 | 14200000 | 15266000 | 2021-09-23 | 2022-03-01
2021-04-30 | 2020 | Army Active | 91996 |  | 2020-06-30 | 2020-09-22 | James Construction Group | W9126G20C0038 | 13350000 | 13132000 | 2022-07-12 | 2022-07-19
2021-04-30 | 2018 | Army Active | 92022 |  | 2019-06-07 | 2019-07-25 | Siler Excavating LLC | W912HN19C3008 | 4635000 | 4639000 | 2020-06-17 | 2021-05-05
2021-04-30 | 2019 | Army Active | 92526 |  | 2019-05-07 | 2019-08-21 | Advanced Technology Construction Corporation | W912DW19C0018 | 3890000 | 4309000 | 2020-09-17 | 2020-10-30
2021-04-30 | 2019 | Army Active | 92781 |  | 2019-07-02 | 2019-09-13 | Speegle Construction, Inc. | W91278-16-D-0031 | 3258000 | 3283000 | 2021-02-12 | 2021-04-24
2021-04-30 | 2019 | Army Active | 93000 |  | 2019-06-20 | 2019-07-29 | LGC Global, Inc. | W912DQ19D4001 | 2595000 | 2599000 | 2020-09-12 | 2021-03-22
2021-04-30 | 2019 | Army Active | 93016 |  | 2019-07-03 | 2019-08-29 | Perikin Enterprise, LLC | W9126G19C0124 | 2404000 | 2469000 | 2020-09-22 | 2021-06-24
2021-04-30 | 2019 | Army Active | 93019 |  | 2019-06-06 | 2019-07-29 | DAP Construction Management, LLC | W912DW19C0015 | 2844000 | 2877000 | 2020-08-27 | 2020-10-07
2021-04-30 | 2019 | Army Active | 93021 |  | 2019-10-24 | 2020-04-07 | Anderson Burton Construction, Inc. | W9128A-16-D-0005 | 5827000 | 5827000 | 2022-01-08 | 2022-01-08
2021-04-30 | 2019 | Army Active | 93022 |  | 2019-03-29 | 2019-05-31 | TBI | W911KB-17-D-0012 | 5379000 | 6653000 | 2020-09-09 | 2021-08-06
2021-04-30 | 2019 | Army Active | 94606 |  | 2019-09-27 | 2019-11-06 | BFBC, LLC | W912PL20C0002 | 15233000 | 14906000 | 2021-06-08
2021-04-30 | 2019 | Army Active | 94607 |  | 2019-09-27 | 2019-11-06 | BFBC, LLC | W912PL20C0002 | 245241000 | 404677000 | 2021-06-08
2021-04-30 | 2019 | Army Active | 94608 |  | 2019-10-22 | 2019-12-02 | Fisher Sand & Gravel CO. | W912PL20C0004 | 268073000 | 419850000 | 2021-01-08
2021-04-30 | 2019 | Army Active | 94609 |  | 2019-10-11 | 2019-11-19 | CJW Joint Venture | W9126G19D0024 | 55842000 | 121858000 | 2021-03-03
2021-04-30 | 2019 | Army Active | 94610 |  | 2019-11-07 | 2020-01-10 | SLSCO, Ltd | W9126G19D0021 | 37106000 | 47319000 | 2021-07-20
2021-04-30 | 2019 | Army Active | 94611 |  | 2019-11-16 | 2020-01-17 | SLSCO, Ltd | W9126G19D0021 | 130750000 | 178637000 | 2021-01-25
2021-04-30 | 2019 | Army Active | 94612 |  | 2019-11-16 | 2020-01-17 | SLSCO, Ltd | W9126G19D0021 | 43620000 | 66268000 | 2021-01-24
2021-05-20 | 2020 | Army National Guard | 010908 |  | 2020-07-10 | 2020-07-19 | Nearen Construction Company | AC-20-C-0014-S | 12000000 | 11704000 | 2021-09-30 | 2022-02-25
2021-05-20 | 2019 | Army National Guard | 020143 |  | 2018-10-02 | 2019-07-19 | TDX Quality, LLC | W91ZRU-16-2-2001 | 27000000 | 22475000 | 2021-04-23 | 2021-05-14
2020-11-12 | 2018 | Army National Guard | 050156 |  | 2019-08-29 | 2019-09-12 | Carson and Associates, Inc. | 9751834 | 3000000 | 2371000 | 2020-09-30 | 2020-10-28
2021-05-20 | 2019 | Army National Guard | 050220 |  | 2020-09-17 | 2020-09-23 | Ross Sparks Builders, Inc. | 9752002 | 2150000 | 1475000 | 2021-10-15 | 2021-10-15
2021-05-20 | 2017 | Army National Guard | 080115 |  | 2018-02-16 | 2019-01-16 | IICON Construction Group, LLC | W912LC-19-C-0001 | 16500000 | 16466000 | 2021-07-23 | 2020-09-30
2021-05-20 | 2016 | Army National Guard | 080213 |  | 2018-01-26 | 2018-04-19 | Iron Mike Construction, LLC | W912LC-16-2-2001 | 3000000 | 2997000 | 2018-12-31 | 2020-05-30
2021-05-20 | 2018 | Army National Guard | 080220 |  | 2020-04-07 | 2020-04-13 | Iron Mike Construction, LLC | W912LC-18-2-2001 | 6000000 | 5757000 | 2021-05-01 | 2021-05-01
2021-05-20 | 2018 | Army National Guard | 100040 |  | 2018-09-07 | 2018-09-13 | Harkins Builders, Inc. | 09-2016 | 36000000 | 35726000 | 2020-12-31 | 2020-12-31
2021-04-20 | 2016 | Army National Guard | 120173 |  | 2016-08-04 | 2016-08-17 | West Construction, Inc. | W911YN-06-2-2001 | 18000000 | 17328000 | 2018-07-30 | 2020-07-30
2021-04-20 | 2015 | Army National Guard | 120212 |  | 2016-05-16 | 2016-05-26 | Hendrick Brothers Construction | WI11YN-15-2-2001 | 1911000 | 2353000 | 2017-10-13 | 2020-08-30
2021-05-20 | 2017 | Army National Guard | 150035 |  | 2017-02-02 | 2017-09-28 | Alutiiq General Contractors LLC | W912J6-17-C-0001 | 31000000 | 30462000 | 2019-06-30 | 2020-12-31
2021-05-20 | 2020 | Army National Guard | 160024 |  | 2020-08-25 | 2020-08-31 | IMCO Construction | W912J7-19-2-2001 | 29000000 | 29598000 | 2022-09-02 | 2022-03-16
2021-05-20 | 2018 | Army National Guard | 160174 |  | 2019-12-03 | 2019-12-12 | C-2 Construction Inc. | NGBID-20-B-0009 | 3000000 | 2395415 | 2021-01-23 | 2021-06-01
2021-03-16 | 2018 | Army National Guard | 160176 |  | 2018-09-11 | 2018-09-12 | Hap Taylor & Sons INC/Knife River | NGBID-19-B-0002 | 22000000 | 21958076 | 2020-06-12 | 2020-10-14
2021-05-20 | 2019 | Army National Guard | 160193 |  | 2020-09-16 | 2020-09-18 | HC Company | W912J7-19-2-2002 | 6000000 | 5399000 | 2021-08-20 | 2021-10-02
2021-05-20 | 2014 | Army National Guard | 171303 |  | 2018-08-30 | 2018-09-07 | Martin & Company Excavating Co. | W91SMC-15-2-2002 | 1750000 | 1799000 | 2020-05-12 | 2020-09-30
2021-05-20 | 2019 | Army National Guard | 171510 |  | 2019-09-10 | 2019-09-13 | Vissering Construction Company | W91SMC-19-2-2001 | 5000000 | 4524000 | 2020-10-16 | 2021-09-01
2021-03-16 | 2014 | Army National Guard | 180234 |  | 2018-09-20 | 2018-09-28 | Hamilton Hunter Builders Inc. | MDI-SAB-18-C-1077 | 3000000 | 2731000 | 2019-11-15 | 2020-11-13
2021-05-20 | 2020 | Army National Guard | 190005 |  | 2020-09-08 | 2020-09-11 | Happe Commercial | 8425A033 | 3000000 | 2984000 | 2021-04-15 | 2021-04-15
2021-05-20 | 2018 | Army National Guard | 190130 |  | 2018-08-27 | 2018-08-30 | Rochon Corp of Iowa | C85148014 | 8500000 | 6667000 | 2019-12-31 | 2021-04-30
2021-05-20 | 2017 | Army National Guard | 200101 |  | 2018-06-12 | 2018-11-27 | The Law Company Inc. | A-013650 | 29000000 | 28329072 | 2020-12-23 | 2021-03-08
2021-05-20 | 2018 | Army National Guard | 200151 |  | 2018-09-12 | 2018-09-14 | Straub Construction Co., Inc. | W912JC-18-2-20001 | 19000000 | 18828000 | 2020-05-14 | 2020-11-27
2021-05-20 | 2015 | Army National Guard | 230113 |  | 2015-02-10 | 2015-06-16 | Nickerson & O'Day, Inc. | 230113-D | 30615000 | 32821000 | 2017-08-03 | 2021-03-31
2021-05-20 | 2018 | Army National Guard | 230135 |  | 2018-07-20 | 2018-08-14 | Devoe Construction | 230135-D | 17500000 | 18623000 | 2020-09-01 | 2020-12-31
2021-05-20 | 2018 | Army National Guard | 240149 |  | 2018-09-17 | 2018-09-18 | Towson Mechanical Inc. | M-900-160-0004 | 19000000 | 17704000 | 2021-04-23 | 2021-05-23
2021-05-20 | 2013 | Army National Guard | 250065 |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279000 | 21610000 | 2015-07-30 | 2017-05-17
2021-05-20 | 2015 | Army National Guard | 260222 |  | 2018-04-06 | 2018-06-29 | Ripman Construction Co Inc. | Y18228 | 1200000 | 1777000 | 2019-10-04 | 2020-12-31
2021-05-20 | 2020 | Army National Guard | 260269 |  | 2020-09-10 | 2020-09-25 | Ripman Construction Co Inc. | Y20410 | 4141000 | 4055000 | 2021-11-05 | 2021-11-05
2021-05-20 | 2019 | Army National Guard | 260274 |  | 2019-12-18 | 2020-01-03 | Ripman Construction Co Inc. | Y20003 | 3000000 | 2904000 | 2020-10-02 | 2021-04-20
2021-04-20 | 2017 | Army National Guard | 270109 |  | 2017-08-17 | 2017-09-08 | W. Gohman Construction Co. | 130774 - BOQ | 8000000 | 5264000 | 2019-05-31 | 2019-11-30
2021-05-20 | 2017 | Army National Guard | 270127 |  | 2018-12-26 | 2019-01-18 | Eagle Construction Company, Inc. | 151541 | 2400000 | 2030000 | 2020-04-10 | 2020-04-10
2021-05-20 | 2018 | Army National Guard | 270132 |  | 2018-08-31 | 2018-09-06 | Stahl Construction Company | Swift #147206 | 39000000 | 40396000 | 2020-02-14 | 2020-08-24
2021-05-20 | 2020 | Army National Guard | 270203 |  | 2020-12-29 | 2021-01-08 | Donlar Construction Company | 187596 | 11200000 | 12150000 | 2022-08-20 | 2022-08-20
2021-05-20 | 2018 | Army National Guard | 270233 |  | 2021-01-12 | 2021-01-13 | Project One Construction, Inc. | 188046 | 1730000 | 1305000 | 2023-07-20 | 2023-07-20
2021-05-20 | 2020 | Army National Guard | 280408 |  | 2020-07-20 | 2020-07-31 | Chris Albrition Construction | NGB22-20-C-0002 | 8100000 | 6069000 | 2021-09-30 | 2021-09-30
2021-05-20 | 2018 | Army National Guard | 290109 |  | 2018-09-19 | 2018-09-20 | KCI Construction Company | T1818-01 | 32000000 | 24525000 | 2020-11-18 | 2020-11-18
2021-05-20 | 2020 | Army National Guard | 290186 |  | 2020-05-28 | 2020-07-10 | Pro-Prost Joint Venture | T1809-01 | 12000000 | 9889000 | 2021-08-18 | 2021-09-23
2021-05-20 | 2019 | Army National Guard | 300031 |  | 2019-02-26 | 2019-02-27 | Swank Enterprises - Valier | W9124V-16-2-2001 | 12806888 | 16803433 | 2020-12-04 | 2020-12-04
2021-05-20 | 2020 | Army National Guard | 310103 |  | 2020-08-26 | 2020-08-31 | Sampson Construction Company, Inc. | W91243-19-2-2001 | 35000000 | 25651000 | 2022-10-28 | 2022-10-28
2021-05-20 | 2021 | Army National Guard | 310140 |  | 2021-01-14 | 2021-02-06 | Perry Reid Construction | W91243-18-2-2001 | 9300000 | 8006000 | 2022-09-20 | 2022-09-20
2021-05-20 | 2020 | Army National Guard | 310168 |  | 2020-09-18 | 2020-09-24 | Western Contracting Corporation | W9128F20C0056 | 8500000 | 8500000 | 2021-04-30 | 2021-05-14
2021-04-20 | 2019 | Army National Guard | 320157 |  | 2018-12-12 | 2019-02-15 | Core Construction | 109954 | 32000000 | 31437000 | 2020-05-28 | 2020-06-30
2021-04-20 | 2019 | Army National Guard | 330043 |  | 2018-11-08 | 2018-11-20 | D.E.W. Construction Corps | W912TF-16-2-2001 | 12000000 | 11452000 | 2020-12-30 | 2020-09-30
2021-05-20 | 2020 | Army National Guard | 330050 |  | 2020-09-03 | 2020-09-21 | Turnstone Corporation | W912TF-18-2-2001 | 5950000 | 6539000 | 2022-09-02 | 2022-09-02
2021-04-20 | 2017 | Army National Guard | 330475 |  | 2018-11-08 | 2018-11-20 | Fulcrum Associates Inc. | W912TF-17-2-2001 | 3000000 | 2868000 | 2019-09-23 | 2020-09-30
2021-05-20 | 2018 | Army National Guard | 350200 |  | 2018-09-25 | 2018-09-27 | Jaynes Corporation | W912J3-16-2-2001 | 8600000 | 8849000 | 2020-10-01 | 2021-02-26
2021-05-20 | 2020 | Army National Guard | 361811 |  | 2020-09-17 | 2020-09-30 | Suffolk Construction Co., Inc. | 46086C | 91000000 | 67804000 | 2022-09-16 | 2022-09-16
2021-05-20 | 2017 | Army National Guard | 371301 |  | 2017-07-24 | 2017-09-25 | Daniels and Daniels Construction Company INC. | W91242-17-C-0005 | 15729000 | 16942000 | 2019-08-17 | 2020-05-01
2021-05-20 | 2019 | Army National Guard | 380116 |  | 2019-05-31 | 2019-06-05 | Gast Construction | AGND 19-17 | 32000000 | 28697000 | 2021-06-30 | 2021-06-30
2021-05-20 | 2019 | Army National Guard | 390285 |  | 2020-08-06 | 2020-09-02 | USPFO - OH | W91364-20-B-0001 | 7400000 | 6945000 | 2022-09-30 | 2022-09-30
2021-03-16 | 2016 | Army National Guard | 401221 |  | 2019-01-02 | 2019-04-05 | Diversified Construction | 18042DB | 3000000 | 2739000 | 2020-09-25 | 2020-09-25
2021-03-16 | 2019 | Army National Guard | 401301 |  | 2019-07-22 | 2019-09-18 | Flintco, LLC | 19280DB | 11000000 | 10550000 | 2020-10-30 | 2020-10-30
2021-05-20 | 2019 | Army National Guard | 410818 |  | 2019-09-24 | 2019-09-30 | Apollo INC. | 410818D002 | 11000000 | 10726000 | 2021-10-22 | 2021-10-22
2021-05-20 | 2019 | Army National Guard | 411104 |  | 2020-05-26 | 2020-07-10 | Silvercreek Contracting, LLC | 411104A0001 | 3000000 | 3000000 | 2020-12-31 | 2021-04-30
2021-05-20 | 2015 | Army National Guard | 411300 |  | 2019-06-13 | 2019-09-20 | Fortis Construction, Inc | 179997D002 | 6031000 | 5900000 | 2020-09-30 | 2021-01-11
2021-05-20 | 2015 | Army National Guard | 411301 |  | 2017-04-18 | 2017-09-28 | Abacus Resource Management Co. | 140033D002 | 2850000 | 2850000 | 2018-12-29 | 2020-11-30
2021-05-20 | 2016 | Army National Guard | 411503 |  | 2020-05-29 | 2020-07-22 | Rotschy, Inc. | 411305C001 | 3000000 | 2970000 | 2021-01-31 | 2021-06-30
2021-05-20 | 2017 | Army National Guard | 420502 |  | 2017-08-07 | 2017-09-22 | USPFO - PA | W912DR-17-D-0015 | 20000000 | 20753000 | 2018-10-26 | 2022-05-26
2021-05-20 | 2016 | Army National Guard | 420522 |  | 2017-03-22 | 2017-04-20 | Miller Bros. Construction, Inc. | W912KC-16-R-0002 | 16000000 | 12799000 | 2018-08-24 | 2020-07-06
2021-05-20 | 2017 | Army National Guard | 440064 |  | 2017-09-06 | 2017-09-13 | Marion Construction Co Inc | W912LD-15-2-2001 | 20000000 | 20595000 | 2020-02-28 | 2021-09-30
2021-05-20 | 2019 | Army National Guard | 460115 |  | 2019-02-07 | 2019-02-15 | RCS Construction, Inc. | W912MM-17-2-2001 | 15000000 | 12785000 | 2020-11-15 | 2020-11-15
2021-05-20 | 2020 | Army National Guard | 465001 |  | 2020-08-07 | 2020-08-20 | Ainsworth-Benning | W912MM-20-2-2001 | 3000000 | 3474000 | 2021-08-27 | 2020-08-28
2021-05-20 | 2015 | Army National Guard | 470035 |  | 2020-02-20 | 2020-04-14 | Marbury Construction | W912l7-18-R-0005 | 1606000 | 1536000 | 2021-01-20 | 2021-06-15
2021-05-20 | 2014 | Army National Guard | 480243 |  | 2014-02-25 | 2015-09-28 | Burns & McDonnell | W912L1-15-0023 | 14270000 | 15373000 | 2017-06-09 | 2019-07-03
2021-05-20 | 2017 | Army National Guard | 490601 |  | 2017-09-21 | 2017-09-26 | Jacobsen Construction Company | 1875077 | 37000000 | 37610000 | 2019-04-03 | 2020-08-20
2021-05-20 | 2020 | Army National Guard | 500110 |  | 2020-09-22 | 2020-09-29 | Dew Construction | 40766 | 30000000 | 28090000 | 2022-09-02 | 2022-09-02
2021-05-20 | 2018 | Army National Guard | 511503 |  | 2018-09-11 | 2018-09-12 | S. B. Ballard Construction Company | PC123-18312-000 | 15000000 | 16999000 | 2020-08-31 | 2021-04-29
2020-11-12 | 2020 | Army National Guard | 511863 |  | 2020-07-22 | 2020-09-25 | RZJames Construction | 19-0007 C | 3000000 | 2521000 | 2021-09-10 | 2021-09-10
2021-05-20 | 2016 | Army National Guard | 530041 |  | 2018-01-19 | 2018-06-28 | TDX Quality, LLC | W912DW-18-C-0015 | 19000000 | 20619000 | 2020-04-17 | 2021-09-30
2021-05-20 | 2018 | Army National Guard | 530129 |  | 2018-09-05 | 2018-09-11 | Pease Constructoin | 2016-0008 G (1-1) | 31000000 | 30987000 | 2020-09-01 | 2020-11-08
2021-05-20 | 2020 | Army National Guard | 531201 |  | 2020-06-02 | 2020-09-25 | Fowler General Construction, Inc. | 2018-586 G (1-1) | 11400000 | 10861000 | 2022-03-21 | 2022-03-21
2021-05-20 | 2017 | Army National Guard | 550280 |  | 2018-11-20 | 2019-01-28 | JH Findorff & Son | NGB-47-17-C-0002 | 1900000 | 1715000 | 2021-04-09 | 2021-04-09
2021-05-20 | 2020 | Army National Guard | 571863 |  | 2021-02-25 | 2021-03-08 | TBD | NGB-01 | 3000000 | 2865000 | 2022-07-30 | 2022-07-30
2020-08-31 | 2016 | Army Reserve | 58405 |  | 2016-12-29 | 2017-05-08 | Eastern Construction & Electric, Inc. | W912QR-17-C-0015 | 9133000 | 10012000 | 2019-05-04 | 2020-02-21
2017-07-31 | 2014 | Army Reserve | 65277 |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 11895000 | 13520000 | 2015-09-30 | 2017-03-21
2017-07-31 | 2012 | Army Reserve | 67466 |  | 2012-05-16 | 2012-09-18 | Continental Casualty Company | W912QR-12-C-0055 | 16212000 | 16472000 | 2014-03-19 | 2017-03-22
2021-04-30 | 2015 | Army Reserve | 67567 |  | 2018-02-01 | 2018-08-09 | RELYANT GLOBAL LLC | W912QR18C0026 | 7030000 | 7358000 | 2019-12-22 | 2021-05-26
2019-08-31 | 2015 | Army Reserve | 67567 |  | 2017-03-01 | 2017-05-11 | Catamount Constructors, Inc. | W912QR-17-C-0018 | 9917000 | 9995000 | 2018-11-24 | 2018-11-07
2017-07-31 | 2013 | Army Reserve | 67652 |  | 2014-05-06 | 2015-03-31 | Cox Construction Co. | W912QR-15-C-0007 | 24044000 | 24621000 | 2017-02-12 | 2017-05-30
2017-07-31 | 2013 | Army Reserve | 67659 |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21779000 | 24488000 | 2015-11-04 | 2016-11-28
2018-08-31 | 2015 | Army Reserve | 67661 |  | 2015-12-01 | 2016-03-01 | Structural Associates, Inc. | W912QR-16-C-0009 | 20118000 | 20520000 | 2018-03-08 | 2018-06-29
2019-08-31 | 2014 | Army Reserve | 67663 |  | 2014-08-01 | 2015-08-28 | Sheffield Korte Joint Venture | W912QR-15-C-0027 | 21428000 | 22917000 | 2017-09-06 | 2018-10-31
2018-08-31 | 2012 | Army Reserve | 67681 |  | 2016-04-14 | 2016-08-25 | S&S - EXCEL CONSTRUCTORS JV | W912QR-16-C-0019 | 12078000 | 12306000 | 2018-01-05 | 2018-04-11
2021-04-30 | 2014 | Army Reserve | 67690 |  | 2017-03-24 | 2017-06-20 | Benaka, Inc | W912QR-17-C-0020 | 14397000 | 15488000 | 2019-06-19 | 2020-10-01
2020-08-31 | 2013 | Army Reserve | 67705 |  | 2015-02-13 | 2015-09-24 | Korte Construction Company | W912QR-15-C-0035 | 18104000 | 23536000 | 2017-09-07 | 2019-12-20
2018-08-31 | 2012 | Army Reserve | 67709 |  | 2016-04-11 | 2016-08-04 | J&J Contractors, Inc. | W912QR-16-C-0015 | 18542000 | 19403000 | 2018-03-23 | 2018-04-30
2017-07-31 | 2013 | Army Reserve | 67715 |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31523000 | 32775000 | 2016-01-15 | 2017-05-31
2017-07-31 | 2011 | Army Reserve | 69421 |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4504000 | 4564000 | 2014-03-21 | 2017-08-30
2019-08-31 | 2011 | Army Reserve | 69562 |  | 2014-12-17 | 2015-09-10 | Blueridge General Inc | W912QR-15-C-0030 | 12568000 | 13677000 | 2017-05-10 | 2019-07-02
2017-07-31 | 2011 | Army Reserve | 69562 |  | 2014-11-14 | 2014-12-17 | Crossroads-Sergent Construction JV | W912QR-13-D-0026 | 1720000 | 1976000 | 2015-10-20 | 2017-06-19
2018-08-31 | 2010 | Army Reserve | 69652 |  | 2011-06-23 | 2011-09-23 | Charpie Korte Enterprise LLC | W912QR-11-C-0047 | 11535000 | 12852000 | 2014-02-12 | 2017-10-27
2020-08-31 | 2015 | Army Reserve | 71035 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-11-12 | 2019-11-12
2020-08-31 | 2017 | Army Reserve | 71036 |  | 2017-06-15 | 2018-03-02 | Heffler Contracting Group | W912QR18C0011 | 22590000 | 22961000 | 2019-09-18 | 2020-04-08
2017-07-31 | 2013 | Army Reserve | 71482 |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56039000 | 61973000 | 2016-05-17 | 2017-03-17
2017-07-31 | 2014 | Army Reserve | 71768 |  | 2015-08-20 | 2015-11-04 | Eastern Construction & Electric, Inc. | W912QR-16-C-0003 | 6433000 | 6818000 | 2017-05-12 | 2017-05-15
2017-07-31 | 2014 | Army Reserve | 71769 |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653000 | 4682000 | 2016-04-09 | 2016-10-18
2020-08-31 | 2015 | Army Reserve | 71901 |  | 2015-05-26 | 2016-01-21 | Hal Hays Construction, Inc. | W912QR-16-C-0006 | 18508000 | 26481000 | 2018-02-20 | 2020-06-18
2019-08-31 | 2014 | Army Reserve | 71903 |  | 2014-07-28 | 2016-07-06 | David Boland, Inc. | W912QR-16-C-0013 | 17277000 | 17812000 | 2018-07-01 | 2019-05-22
2017-07-31 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2016-06-30 | AAECON General Contracting LLC | W912QR-14-D-0025 | 2520000 | 2682000 | 2016-12-12 | 2017-07-21
2016-10-31 | 2013 | Army Reserve | 72088 |  | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19101000 | 19893000 | 2015-06-08 | 2016-03-02
2020-08-31 | 2014 | Army Reserve | 72284 |  | 2014-08-13 | 2014-09-30 | North American Specialty Insurance Company | W912QR-14-C-0053 | 16187000 | 16498000 | 2016-05-22 | 2019-11-01
2017-07-31 | 2015 | Army Reserve | 72291 |  | 2015-05-01 | 2015-09-30 | Korte Construction Company | W912QR-15-C-0042 | 13283000 | 13805000 | 2017-08-28 | 2017-09-16
2019-08-31 | 2013 | Army Reserve | 73738 |  | 2016-02-26 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2018-11-28 | 2018-11-28
2019-08-31 | 2015 | Army Reserve | 74001 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-07 | 2019-06-07
2021-04-30 | 2017 | Army Reserve | 74732 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 9745000 | 10726000 | 2019-06-13 | 2020-12-14
2021-04-30 | 2018 | Army Reserve | 77074 |  | 2019-08-05 | 2019-09-27 | RBC Constuction | W912QR19C0046 | 18838000 | 19063000 | 2021-04-22 | 2022-01-26
2021-04-30 | 2017 | Army Reserve | 77134 |  | 2018-01-05 | 2018-04-26 | LS Black Constructor | W912QR18C0015 | 23840000 | 24557000 | 2020-05-14 | 2021-01-05
2020-08-31 | 2015 | Army Reserve | 77151 |  | 2016-04-05 | 2016-09-29 | Boro Developers, Inc. d.b.a Boro Construction | W912QR-16-C-0024 | 19988000 | 21475000 | 2018-09-13 | 2020-07-02
2021-04-30 | 2016 | Army Reserve | 77163 |  | 2019-08-02 | 2019-09-29 | Trans4Fed, LLC | W912QR19C0045 | 10304000 | 10373000 | 2021-06-23 | 2022-04-29
2021-04-30 | 2016 | Army Reserve | 77186 |  | 2017-04-03 | 2017-07-13 | ACC Construction Co, Inc. | W912QR17C0021 | 19332000 | 19415000 | 2019-08-31 | 2020-12-15
2020-08-31 | 2015 | Army Reserve | 77228 |  | 2015-08-11 | 2017-05-12 | Blinderman Construction Co, Inc. | W912QR-17-C-0017 | 21411000 | 22652000 | 2019-04-25 | 2019-11-12
2018-03-31 | 2015 | Army Reserve | 77228 |  | 2015-08-11 | 2016-05-02 | Blinderman Construction | W912QR-16-C-0007 | 42622000 | 0 | 2018-05-22 | 2018-05-22
2021-04-30 | 2018 | Army Reserve | 77238 |  | 2018-05-30 | 2018-09-25 | Cox Construction | W912QR18C0036 | 33051000 | 34523000 | 2020-11-20 | 2021-04-15
2021-04-30 | 2019 | Army Reserve | 77268 |  | 2018-11-20 | 2019-02-28 | Straub Construction, Inc. | W912QR19C0012 | 28937000 | 30253000 | 2020-11-21 | 2021-09-02
2021-04-30 | 2018 | Army Reserve | 77324 |  | 2018-08-10 | 2018-09-29 | SHEFFIELD KORTE TEAM LLC | W912QR18C0040 | 27228000 | 28027000 | 2020-09-30 | 2020-12-07
2020-08-31 | 2018 | Army Reserve | 79003 |  | 2018-01-24 | 2018-05-24 | LS Black Constructors, Inc. | W912QR18C0019 | 12384000 | 12851000 | 2019-08-14 | 2020-03-13
2019-08-31 | 2015 | Army Reserve | 80353 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2020-08-31 | 2017 | Army Reserve | 80684 |  | 2017-01-25 | 2017-10-19 | LS Black Constructors, Inc. | W912QR18C0002 | 13454000 | 13595000 | 2019-09-11 | 2020-03-04
2021-04-30 | 2019 | Army Reserve | 80690 |  | 2019-06-10 | 2019-09-27 | LS Black Constructors | W912QR19C0051 | 20684000 | 21545000 | 2021-08-22 | 2021-12-05
2021-04-30 | 2020 | Army Reserve | 81802 |  | 2020-07-30 | 2020-09-29 | LS Black Constructors | W912QR20C0052 | 18824000 | 18832000 | 2022-12-17 | 2022-12-17
2017-07-31 | 2015 | Army Reserve | 81959 |  | 2015-03-06 | 2015-07-17 | ETD-TCG, LLC with RSP Architects | W912QR-15-C-0018 | 5215000 | 5332000 | 2016-12-09 | 2017-05-23
2019-08-31 | 2015 | Army Reserve | 85683 |  | 2017-07-27 | 2017-11-14 | Straub Construction Inc. | W912QR18C0005 | 0 | 0 | 2019-06-06 | 2019-06-06
2018-08-31 | 2016 | Army Reserve | 85808 |  | 2016-10-18 | 2017-04-25 | Martin Brothers Construction | W912QR-17-C-0014 | 2603000 | 2603000 | 2018-05-08 | 2018-05-08
2021-04-30 | 2016 | Army Reserve | 85813 |  | 2017-06-28 | 2017-09-28 | Hensel Phelps Construction Co. | W912QR-17-C-0043 | 49643000 | 51733000 | 2019-10-04 | 2021-05-07
2019-08-31 | 2017 | Army Reserve | 86521 |  | 2017-06-30 | 2017-09-19 | Cox Construction Co. | W912QR17C0035 | 17795000 | 17966000 | 2019-05-01 | 2019-07-17
2020-08-31 | 2016 | Army Reserve | 86814 |  | 2017-05-01 | 2017-09-29 | Nadiad, Inc | W912QR17C0044 | 4682000 | 4843000 | 2018-10-18 | 2020-09-30
2021-04-30 | 2020 | Army Reserve | 86823 |  | 2019-11-01 | 2020-03-26 | Harkins Builders | W912QR20C0012 | 19751000 | 20183000 | 2022-03-28 | 2021-09-15
2021-04-30 | 2016 | Army Reserve | 86882 |  | 2017-06-27 | 2017-11-09 | Cox Construction Co. | W912QR18C0003 | 21180000 | 22717000 | 2019-12-18 | 2021-05-31
2021-04-30 | 2018 | Army Reserve | 88585 |  | 2018-07-11 | 2018-09-29 | Hernandez Consulting | W912QR18C0048 | 2459000 | 2644000 | 2020-01-26 | 2020-10-09
2021-04-30 | 2017 | Army Reserve | 88722 |  | 2017-01-12 | 2017-04-14 | OAC Action Contruction, Corp | W912QR-17-C-0012 | 2202000 | 2192000 | 2018-07-13 | 2020-10-30
2021-04-30 | 2018 | Army Reserve | 88731 |  | 2018-06-29 | 2019-06-05 | Caribe General Constructors | W912QR19C0018 | 17399000 | 18231000 | 2020-12-19 | 2021-12-15
2021-04-30 | 2019 | Army Reserve | 90202 |  | 2020-02-18 | 2020-09-04 | WHH Nisqually-Garco JVW | W912QR20C0035 | 20217000 | 20217000 | 2022-06-22 | 2022-06-22
2021-04-30 | 2019 | Army Reserve | 90303 |  | 2018-11-02 | 2019-02-28 | Dean S.H. Pak Inc | W912QR19C0009 | 1831000 | 1819000 | 2020-06-10 | 2020-10-14
2021-04-30 | 2020 | Army Reserve | 90912 |  | 2020-01-13 | 2020-05-19 | James Dean Construction, Inc. | W912QR20C0009 | 3703000 | 4838000 | 2021-07-22 | 2021-07-22
2021-04-30 | 2018 | Army Reserve | 91427 |  | 2018-06-25 | 2018-09-27 | BIM Contractors, LLC | W912QR18C0037 | 1692000 | 1717000 | 2020-02-28 | 2020-10-02
2021-05-31 | 2016 | DLA Defense Automation and Production Service | DESC1607 |  | 2016-06-24 | 2016-09-16 | W.F. Magann Corporation | W91236-16-R-0008-0005 | 20646000 | 21088000 | 2019-10-12 | 2019-12-12
2021-05-31 | 2013 | DLA Defense Distribution Center | DCX1305 |  | 2016-12-21 | 2017-06-01 | Lobar Inc | W912DR-17-C-0022 | 4831000 | 4865000 | 2019-06-26 | 2020-03-02
2021-05-31 | 2014 | DLA Defense Distribution Center | DDCX1309 A |  | 2016-06-30 | 2016-09-27 | Belt Built CFM Construction Services JV, LLC | W912DR-16-C-0049 / 35958356 | 2597449 | 2768000 | 2017-11-18 | 2019-10-25
2021-05-31 | 2017 | DLA Defense Distribution Center | DDCX1701A |  | 2017-12-08 | 2018-04-12 | Carouthers Construction | W9126G-18-C-0018 | 36159560 | 36510784 | 2020-06-25 | 2021-05-24
2021-05-31 | 2017 | DLA Defense Distribution Center | DDCX1701B |  | 2018-04-03 | 2018-08-30 | Bristol Construction Services | W9126G-18-C-0066 | 3881804 | 3881804 | 2020-09-30 | 2020-09-30
2021-05-31 | 2015 | DLA Defense Distribution Center | DESC1606 |  | 2015-09-01 | 2015-11-16 | MEB General Contractors Inc | N69450-16-C-1604 | 36565000 | 57832172 | 2017-11-05 | 2019-12-22
2021-05-31 | 2015 | DLA Defense Distribution Center | DESC1606 |  | 2015-09-01 | 2015-11-16 | MEB General Contractors Inc | 1234 | 36443425 | 39151158 | 2018-07-01 | 2018-08-20
2021-05-31 | 2013 | DLA Defense Energy Support Center | DESC1301 |  | 2014-11-13 | 2015-08-28 | Rockford Corporation | W912QR-15-C-0026 | 36448000 | 37081000 | 2017-03-30 | 2021-04-25
2021-05-31 | 2015 | DLA Defense Energy Support Center | DESC1353 |  | 2015-03-13 | 2015-08-19 | Middle Eastern Builders | W912HN-12C-0016 | 15685100 | 16568000 | 2018-05-23 | 2018-09-21
2021-05-31 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2014-12-12 | 2015-04-07 | Nippo Corporation | W912HV-15-C-0005 | 32623000 | 33122640 | 2017-08-23 | 2018-11-15
2021-05-31 | 2014 | DLA Defense Energy Support Center | DESC1401 |  | 2015-02-27 | 2015-04-07 | Nippo Corporation | W912HV-15-C-005 | 32623000 | 33122640 | 2017-08-23 | 2022-09-30
2021-05-31 | 2015 | DLA Defense Energy Support Center | DESC1404 |  | 2015-04-23 | 2016-01-21 | Gilbane Federal | N39430-15-D-1634-JM01 | 9960000 | 10140442 | 2017-11-13 | 2017-12-13
2021-05-31 | 2014 | DLA Defense Energy Support Center | DESC1407 |  | 2014-04-18 | 2015-04-02 | Nova Group Inc. Underground Construction | W912PP-15-C-003 | 21288300 | 22083000 | 2017-02-01 | 2017-07-18
2021-05-31 | 2015 | DLA Defense Energy Support Center | DESC1463 |  | 2015-04-14 | 2015-09-30 | Structural Asspcoates Omc. | W9128F-15-C-0032 | 8518820 | 8267000 | 2017-04-16 | 2017-06-15
2021-05-31 | 2014 | DLA Defense Energy Support Center | DESC1501 |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637000 | 9333465 | 2016-05-11 | 2020-11-03
2021-05-31 | 2014 | DLA Defense Energy Support Center | DESC1502 | 43 | 2014-06-17 | 2015-05-04 | Rockford Corporation | W912BV-15-C-0017 | 4556371 | 4733000 | 2016-10-23 | 2017-09-08
2021-05-31 | 2014 | DLA Defense Energy Support Center | DESC1502 A |  | 2014-06-17 | 2014-10-21 | NOVA Group Inc. | W912BV-15-C-0001 | 32060100 | 322532000 | 2017-05-23 | 2018-01-18
2021-05-31 | 2014 | DLA Defense Energy Support Center | DESC1502 B |  | 2015-01-19 | 2015-05-04 | Rockford Corporation | W912BV-15-C-0017 | 4556371 | 4733000 | 2016-10-23 | 2017-07-18
2021-05-31 | 2015 | DLA Defense Energy Support Center | DESC1507 |  | 2015-02-02 | 2016-08-16 | Cape Environemental | N40080-16-C-0161 | 17178089 | 18765895 | 2018-02-07 | 2018-10-15
2021-05-31 | 2015 | DLA Defense Energy Support Center | DESC1508 |  | 2016-03-31 | 2017-03-30 | CB&I Federal Services, LLC | N62473-15-R-0001-0008 | 54095271 | 58620122 | 2020-03-30 | 2020-08-25
2021-05-31 | 2017 | DLA Defense Energy Support Center | DESC1513 |  | 2018-04-30 | 2018-09-20 | Bhate Zapata | W912EP-16-D-0008 / 6465583 | 1300000 | 1300000 | 2019-07-06 | 2019-07-06
2021-05-31 | 2015 | DLA Defense Energy Support Center | DESC1551 |  | 2014-10-29 | 2015-08-25 | Hensel Phelps Constuction co | N62742-15-C-1308 | 42823800 | 46800984 | 2017-09-23 | 2018-01-31
2021-05-31 | 2016 | DLA Defense Energy Support Center | DESC1603 |  | 2017-12-12 | 2018-08-10 | Bietergemeinschaft UVB | W912GB-14-C-0005 | 6125000 | 6125000 | 2019-06-02 | 2019-06-02
2021-05-31 | 2016 | DLA Defense Energy Support Center | DESC1605 |  | 2016-06-23 | 2017-06-02 | STRUCTURAL ASSOCIATES | W912BU16R00370006 | 23170900 | 23170900 | 2019-06-16 | 2019-06-26
2021-05-31 | 2016 | DLA Defense Energy Support Center | DESC1607 |  | 2016-06-24 | 2016-09-16 | W.F. Magann Corporation | W91236-16-C-0025 | 20646000 | 21280000 | 2019-10-12 | 2019-12-12
2021-05-31 | 2019 | DLA Defense Energy Support Center | DESC1609 |  | 2018-08-01 | 2019-06-28 | SES Energy Services, LLC | W9128F19C0032 / 42718510 | 7499541 | 7716000 | 2019-07-06 | 2021-07-15
2021-05-31 | 2017 | DLA Defense Energy Support Center | DESC1611 |  | 2017-11-29 | 2017-11-30 | NOVA Group, Inc | N62473-18-C-2202 | 26868000 | 26926198 | 2020-03-10 | 2020-03-10
2021-05-31 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-22 | Ergotem S.A. | N62470-17-C-5003 | 20577000 | 20986605 | 2019-01-07 | 2019-12-24
2021-05-31 | 2016 | DLA Defense Energy Support Center | DESC1701 |  | 2016-09-23 | 2016-12-12 | Ergotem S.A. | w | 20577000 | 20577000 | 2019-01-07 | 2019-01-07
2021-05-31 | 2016 | DLA Defense Energy Support Center | DESC1702 |  | 2017-02-09 | 2017-09-30 | MEB General Contractors, Inc. | W91299-17-C-0011 | 20973000 | 21083000 | 2019-06-25 | 2019-09-23
2021-05-31 | 2017 | DLA Defense Energy Support Center | DESC1704 |  | 2017-09-28 | 2017-09-29 | San Juan Construction, Inc. | W9128A-17-C-0008 | 63297670 | 63297670 | 2020-12-27 | 2022-06-11
2021-05-31 | 2017 | DLA Defense Energy Support Center | DESC1705 |  | 2017-05-29 | 2017-05-30 | Black Construction/Mace Internation | N62742-17-C-1313 | 26978100 | 28361127 | 2019-06-29 | 2020-01-31
2021-05-31 | 2017 | DLA Defense Energy Support Center | DESC1706 |  | 2017-09-18 | 2017-09-19 | Cape Environemental | N63450-17-C-1305 | 8783275 | 8783275 | 2019-04-04 | 2019-04-26
2021-05-31 | 2017 | DLA Defense Energy Support Center | DESC1707 |  | 2017-01-30 | 2017-08-07 | ASRC Builders | W911KB-17-C-0030 | 4088355 | 4129621 | 2018-12-15 | 2018-12-03
2021-05-31 | 2017 | DLA Defense Energy Support Center | DESC1708 |  | 2017-03-31 | 2017-08-04 | NIPPO Corporation | W912HV-17-C-0008 | 6804938 | 6817433 | 2019-09-08 | 2022-09-08
2021-05-31 | 2018 | DLA Defense Energy Support Center | DESC1709 |  | 2018-09-20 | 2018-09-21 | Tfs-Aptim JV | N40192-18-C-1300 | 21445996 | 21445996 | 2019-12-15 | 2019-12-15
2021-05-31 | 2016 | DLA Defense Energy Support Center | DESC1710 |  | 2016-06-15 | 2016-09-20 | RELIABLE CONTRACTING GROUP, LLC | W912HN-16-C-0017 / 43104748 | 9568000 | 10447000 | 2018-04-26 | 2019-08-27
2021-05-31 | 2015 | DLA Defense National Stockpile Center | DESC1507 |  | 2015-02-02 | 2015-09-30 | Structural Associates Inc | W9128F-15-C-0032 | 17178089 | 17906802 | 2017-03-23 | 2018-05-16
2021-05-31 | 2018 | DLA Defense Reutilization and Marketing Service | DRMS1701 |  | 2018-06-26 | 2018-08-31 | EMR Inc | N91278-16-C-0035 | 3788549 | 3788549 | 2019-07-06 | 2019-10-11
2021-05-31 | 2016 | DLA Defense Supply Center Philadelphia | DSCP1501 |  | 2016-03-11 | 2016-09-16 | Daniel J. keating Company | N40085-16-C-3037 | 46845550 | 57854412 | 2019-03-30 | 2020-01-02
2021-05-31 | 2015 | DLA Defense Supply Center Richmond | DSCR1501 |  | 2016-11-08 | 2017-12-14 | SAW Contracting | W91236-18-C-0008 | 6253160 | 7509000 | 2019-08-12 | 2020-10-12
2021-05-14 | 2017 | Defense Health Agency | 14019 |  | 2017-06-23 | 2018-06-29 | RQ-DPRI | N40085-18-C-0637 | 35000000 | 31499000 | 2020-07-13 | 2021-07-12
2021-05-14 | 2018 | Defense Health Agency | 14021 |  | 2018-06-12 | 2019-12-18 | Soltek Pacific Construction Co. | N6247318D5855 | 27087000 | 27799000 | 2022-05-10 | 2022-05-10
2021-05-14 | 2017 | Defense Health Agency | 14022 |  | 2017-04-28 | 2017-09-13 | Mirait T-Acty JV | W912-HV-17-D-0014 | 14781000 | 15015000 | 2019-10-26 | 2020-11-30
2021-05-14 | 2018 | Defense Health Agency | 14041 |  | 2018-06-13 | 2019-09-28 | Whiting Turner Contracting Co | N6247016D6006 | 22911000 | 22919000 | 2021-10-30 | 2021-10-30
2021-05-14 | 2018 | Defense Health Agency | 14042 |  | 2018-06-06 | 2019-09-28 | Whiting Turner Contracting Co | N4008519C9266 | 21875000 | 21963000 | 2021-10-30 | 2021-10-30
2021-05-14 | 2008 | Defense Health Agency | 52332 |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany | W912GB-07-C-0007-NA | 25929000 | 28027000 | 2012-05-15 | 2012-07-16
2021-05-14 | 2007 | Defense Health Agency | 58395 |  | 2007-06-30 | 2007-09-29 | James Construction | W912DR-07-C-0070 | 2657000 | 2657000 | 2008-06-13 | 2008-06-08
2021-05-14 | 2007 | Defense Health Agency | 58395 | 58395-01 | 2008-01-10 | 2008-08-01 | James Construction | W912DR-08-C-0038 | 1472000 | 1472000 | 2009-02-15 | 2009-02-13
2021-05-14 | 2007 | Defense Health Agency | 58395 | 58395-02 | 2008-05-01 | 2009-09-28 | James Construction | W912DR-08-C-0078 | 706000 | 706000 | 2010-04-13 | 2010-04-13
2021-05-14 | 2007 | Defense Health Agency | 58395 | 58395-03 | 2008-01-10 | 2008-09-25 | Grunley/Goel JVA LLC | W912DR-08-C-0053 | 2465000 | 2465000 | 2009-07-24 | 2009-07-24
2021-05-14 | 2007 | Defense Health Agency | 58395 | 58395-04 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 604000 | 2013-10-31 | 2013-12-06
2021-05-14 | 2007 | Defense Health Agency | 58395 | 58395-05 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 3949000 | 2014-05-31 | 2022-12-31
2018-09-13 | 2007 | Defense Health Agency | 58395 | 63418 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 131264000 | 138491000 | 2014-05-31 | 2019-01-18
2018-09-13 | 2007 | Defense Health Agency | 58395 | 63419 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 185526000 | 185364000 | 2014-05-31 | 2018-12-31
2018-09-13 | 2007 | Defense Health Agency | 58395 | 63420 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 94000000 | 100181000 | 2014-05-31 | 2019-01-18
2018-09-13 | 2007 | Defense Health Agency | 58395 | 63420-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 496000 | 496000 | 2013-10-31 | 2016-12-06
2018-09-13 | 2007 | Defense Health Agency | 58395 | 65324 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 13497000 | 12893000 | 2014-05-31 | 2019-01-18
2020-01-13 | 2007 | Defense Health Agency | 58395 | 65324-01 | 2008-06-15 | 2008-07-15 | John C. Grimberg Co. Inc. | W912DR-08-C-0016 | 603000 | 604000 | 2013-10-31 | 2013-12-06
2018-09-13 | 2007 | Defense Health Agency | 58395 | 71101 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 66955000 | 89587000 | 2014-05-31 | 2019-01-18
2021-05-14 | 2007 | Defense Health Agency | 58395 | 71101-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 7750000 | 7335000 | 2017-03-31 | 2017-05-04
2020-01-13 | 2007 | Defense Health Agency | 58395 | 78210 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 0 | 3949000 | 2014-05-31 | 2019-03-19
2021-05-14 | 2013 | Defense Health Agency | 58395 | 78210-01 | 2015-03-09 | 2015-09-18 | Edifice-Schlosser JV | W912DR-15-C-0025 | 0 | 141000 | 2017-03-31 | 2017-05-04
2021-05-14 | 2013 | Defense Health Agency | 58395 | 78210-02 | 2017-08-18 | 2017-09-27 | Doyon Project Services, LLC | W912DR-17-D-0012 | 1607000 | 1580000 | 2018-10-26 | 2019-05-11
2021-05-14 | 2014 | Defense Health Agency | 58395 | 78211 | 2008-08-14 | 2009-03-27 | Manhattan/Torcon JV | W912DR-09-C-0026 | 3200000 | 3200000 | 2014-05-31 | 2022-12-31
2021-05-14 | 2009 | Defense Health Agency | 64156 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398000 | 17919000 | 2013-06-01 | 2015-06-10
2021-05-14 | 2009 | Defense Health Agency | 65731 |  | 2009-01-07 | 2009-04-08 | Total Engineering INC | W912DR-09-C-0030 | 436000 | 436000 | 2010-08-08 | 2010-08-31
2021-05-14 | 2009 | Defense Health Agency | 65731 | 65731-01 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 37771000 | 2013-06-01 | 2015-06-10
2020-01-13 | 2009 | Defense Health Agency | 65731 | 67180 | 2009-01-07 | 2009-04-08 | Total Engineering INC | W912DR-09-C-0030 | 436000 | 436000 | 2010-08-08 | 2010-08-31
2021-05-14 | 2009 | Defense Health Agency | 65731 | 67180-01 | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280922 | 280922 | 2011-09-30 | 2011-09-30
2018-09-13 | 2009 | Defense Health Agency | 65731 | 67180-02 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 100375000 | 103776000 | 2013-06-01 | 2015-06-10
2018-09-13 | 2009 | Defense Health Agency | 65731 | 67181 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 94608000 | 106045000 | 2013-06-01 | 2015-06-10
2020-01-13 | 2009 | Defense Health Agency | 65731 | 67182 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 7915345 | 37771000 | 2013-06-01 | 2015-06-10
2021-05-14 | 2011 | Defense Health Agency | 66588 |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany | W912GB-09-C-0038 | 30080000 | 31830000 | 2016-05-30 | 2017-05-03
2021-05-14 | 2018 | Defense Health Agency | 67402 |  | 2019-07-29 | 2020-01-30 | SGS, LLC | W9126G-20-C-0009 | 8996000 | 8996000 | 2022-04-03 | 2022-04-03
2021-05-14 | 2009 | Defense Health Agency | 70354 |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 162257000 | 213468000 | 2015-03-16 | 2018-03-01
2021-05-14 | 2009 | Defense Health Agency | 70354 | 70354-01 | 2017-07-28 | 2017-09-25 | Anna Lisa Luna Construction, Inc. | W912-PL-17-C-0042 | 3691544 | 4392000 | 2018-05-01 | 2018-08-14
2021-05-14 | 2009 | Defense Health Agency | 70354 | 70354-02 | 2017-07-12 | 2017-09-27 | BHATE Environmental Associates, Inc. | W912DY-15-D-0081 | 1118431 | 1474000 | 2018-12-31 | 2019-08-19
2021-05-14 | 2013 | Defense Health Agency | 71317 |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744000 | 46104000 | 2016-12-30 | 2019-02-15
2021-05-14 | 2013 | Defense Health Agency | 71325 |  | 2012-11-30 | 2013-09-13 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536000 | 47478000 | 2016-10-23 | 2018-06-01
2021-05-14 | 2012 | Defense Health Agency | 71408 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688000 | 20359000 | 2016-12-06 | 2019-02-15
2021-05-14 | 2012 | Defense Health Agency | 71503 |  | 2012-03-22 | 2016-08-25 | Surety Company | N69450 12 C 0754 | 9548000 | 2026000 | 2017-12-25 | 2019-05-10
2020-01-13 | 2012 | Defense Health Agency | 71503 | 71503-01 | 2012-03-22 | 2016-08-25 | Surety Company | N69450 12 C 0754 | 9548000 | 2026000 | 2017-12-25 | 2019-03-10
2021-05-14 | 2013 | Defense Health Agency | 71507 |  | 2013-02-28 | 2013-12-18 | Turner Construction Company | N40080 14 C 0154 | 41408000 | 43481000 | 2015-10-15 | 2017-02-08
2021-05-14 | 2017 | Defense Health Agency | 71509 |  | 2017-06-30 | 2018-12-26 | KBE BLDG CORP | N4008519C9070 | 35912000 | 31560000 | 2021-01-24 | 2021-06-07
2020-01-13 | 2016 | Defense Health Agency | 71642 |  | 2016-07-08 | 2016-09-30 | Butt Construction Co. | W912QR-15-D-0002-0014 | 6301000 | 6482000 | 2019-01-12 | 2018-11-13
2021-02-14 | 2015 | Defense Health Agency | 72414 |  | 2015-04-21 | 2015-09-25 | Gilbane Federal JV | W9127S-13-D-6000 | 16629000 | 16581000 | 2017-10-23 | 2018-10-23
2021-05-14 | 2013 | Defense Health Agency | 72419 |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co. Ltd. | W912UM-13-C-0025 | 22361000 | 24475000 | 2017-08-08 | 2020-06-20
2021-05-14 | 2010 | Defense Health Agency | 72481 |  | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 56858000 | 254896000 | 2016-11-26 | 2020-02-29
2018-09-13 | 2010 | Defense Health Agency | 72481 | 72251 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 68076000 | 68076000 | 2016-11-26 | 2019-09-30
2021-05-14 | 2010 | Defense Health Agency | 72481 | 72481-01 | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. | W912G-09-D-0004-0008 | 39345000 | 47508000 | 2013-08-13 | 2013-10-12
2021-05-14 | 2010 | Defense Health Agency | 72481 | 72481-02 | 2011-03-25 | 2011-06-17 | Janco | W9126G-09-D-0096-0002 | 10488000 | 10634000 | 2012-07-05 | 2012-12-31
2021-05-14 | 2010 | Defense Health Agency | 72481 | 72481-03 | 2012-03-16 | 2012-07-19 | VEMAC | W9126G-12-C-0038 | 3848000 | 3879000 | 2013-06-19 | 2013-10-17
2021-05-14 | 2010 | Defense Health Agency | 72481 | 72481-04 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2015-08-27 | 2015-11-30
2021-05-14 | 2010 | Defense Health Agency | 72481 | 72481-05 | 2012-02-08 | 2012-09-04 | El Paso Electric Company | W9126G-12-P-0014 | 4047000 | 4047000 | 2014-01-04 | 2015-09-16
2019-04-15 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G-11-P | 46000 | 46000 | 2011-11-01 | 2011-11-01
2021-05-14 | 2010 | Defense Health Agency | 72481 | 72481-06 | 2011-07-25 | 2011-08-25 | Temp Electric Contract | W9126G-11-P-0208 | 46000 | 46000 | 2011-11-01 | 2011-11-01
2018-09-13 | 2010 | Defense Health Agency | 72481 | 72786 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 69851000 | 80080000 | 2016-11-26 | 2019-09-30
2018-09-13 | 2010 | Defense Health Agency | 72481 | 76558 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 79914000 | 175303000 | 2016-11-26 | 2019-09-30
2021-05-14 | 2010 | Defense Health Agency | 72481 | 76558-01 | 2013-08-08 | 2013-09-13 | Licon Engineering Company, Inc. dba LEC Group | W9126G-13-C-0046 | 1540000 | 657000 | 2014-10-24 | 2014-10-24
2020-01-13 | 2010 | Defense Health Agency | 72481 | 76558-02 | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 479000 | 1538000 | 2015-08-27 | 2015-11-30
2017-10-11 | 2010 | Defense Health Agency | 72481 | 77251 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 68076000 | 68076000 | 2016-11-26 | 2018-04-15
2018-09-13 | 2010 | Defense Health Agency | 72481 | 77293 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 198148000 | 124569000 | 2016-11-26 | 2019-09-30
2018-09-13 | 2010 | Defense Health Agency | 72481 | 81407 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 225199000 | 117814000 | 2016-11-26 | 2019-09-30
2020-01-13 | 2010 | Defense Health Agency | 72481 | 81408 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 56858000 | 179776000 | 2016-11-26 | 2019-12-31
2021-05-14 | 2018 | Defense Health Agency | 72481 | 91301 | 2012-08-07 | 2013-01-29 | Clark McCarthy Joint Venture | W9126G-13-C-0004 | 251330000 | 206136000 | 2016-11-26 | 2020-02-29
2021-05-14 | 2017 | Defense Health Agency | 72738 |  | 2017-01-19 | 2017-09-13 | JE Dunn Construction Company | W912-BV-17-C-0014 | 67487000 | 67762000 | 2020-10-31 | 2021-07-30
2021-05-14 | 2021 | Defense Health Agency | 72742 |  | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005 | 1898000 | 1898000 | 2022-06-07 | 2022-06-07
2021-05-14 | 2020 | Defense Health Agency | 72742 |  | 2020-08-12 | 2020-09-30 | Federal Republic of Germany | W912GB-17-C-0005 | 352000 | 352000 | 2021-08-26 | 2021-08-26
2021-05-14 | 2012 | Defense Health Agency | 72754 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22835000 | 2014-07-29 | 2016-09-02
2020-01-13 | 2012 | Defense Health Agency | 72754 | 80793 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc. | W9126G-12-C-0051 | 16319000 | 22835000 | 2014-07-29 | 2016-09-02
2021-05-14 | 2013 | Defense Health Agency | 72808 |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc. | N62473 10 D 5412 DO 0007 | 18703000 | 19971000 | 2015-03-16 | 2017-04-28
2020-08-12 | 2012 | Defense Health Agency | 76007 |  | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 14187000 | 2025-12-30 | 2025-12-30
2019-10-14 | 2012 | Defense Health Agency | 76007 | 14043 | 2018-03-30 | 2018-03-31 | Federal Republic of Germany | W912GB-10-C-0031 | 30315000 | 30315000 | 2024-06-30 | 2025-06-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, ABG4 P00058 | 2359000 | 3563000 | 2016-04-30 | 2017-04-30
2017-03-31 | 2012 | Defense Health Agency | 76007 | 72661 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 36640000 | 36640000 | 2020-12-30 | 2020-12-30
2021-02-14 | 2012 | Defense Health Agency | 76007 | 72661, 72662-02 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00102 | 56039000 | 56985000 | 2021-01-30 | 2021-04-30
2021-02-14 | 2012 | Defense Health Agency | 76007 | 72661, 76007-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 21988000 | 24175000 | 2018-07-30 | 2018-12-30
2017-05-31 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 36640000 | 36640000 | 2020-12-30 | 2020-12-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 72661-01 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00085 | 33888000 | 34523000 | 2021-03-31 | 2021-09-30
2017-11-14 | 2012 | Defense Health Agency | 76007 | 72661-02 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 53054000 | 53054000 | 2019-04-30 | 2020-09-30
2017-09-13 | 2012 | Defense Health Agency | 76007 | 72661-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 21968000 | 21968000 | 2018-07-30 | 2018-12-30
2017-06-30 | 2012 | Defense Health Agency | 76007 | 72661-2 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 83000000 | 83000000 | 2019-04-30 | 2020-09-30
2018-07-13 | 2012 | Defense Health Agency | 76007 | 72662 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 57036000 | 57036000 | 2019-04-30 | 2020-09-30
2018-09-13 | 2012 | Defense Health Agency | 76007 | 72662-01 | 2015-08-19 | 2015-08-31 | Federal Republic of Germany | W912GB-10-C-0031 | 32200000 | 32200000 | 2023-12-30 | 2023-12-30
2018-09-13 | 2012 | Defense Health Agency | 76007 | 72662-02 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 56039000 | 56039000 | 2019-04-30 | 2020-09-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 72662-02 | 2013-07-15 | 2013-08-27 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, P00102 | 56039000 | 56985000 | 2021-01-30 | 2021-07-30
2017-09-13 | 2012 | Defense Health Agency | 76007 | 72662-2 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 83000000 | 83000000 | 2019-04-30 | 2020-09-30
2021-02-14 | 2012 | Defense Health Agency | 76007 | 76007, 81412 | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 14187000 | 2025-12-30 | 2026-06-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-01 | 2012-02-01 | 2012-03-15 | Joint Venture Bautra Baugesellschaft mbH / SRS Service GmbH | W912GB-10-C-0031, ABG4 P00023 | 261000 | 261000 | 2014-04-04 | 2014-04-04
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-02 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00030 | 681000 | 1747000 | 2014-10-29 | 2015-01-21
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-03 | 2012-02-01 | 2012-03-15 | Bodo Freimuth Abbruch und Recycling GmbH | W912GB-10-C-0031, ABG4 P00043 | 5321000 | 6586000 | 2016-04-30 | 2017-07-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-04 | 2012-02-01 | 2012-03-15 | Hermanns RTE Rohrleitungs- undd Tiefbau Erfurt GmbH | W912GB-10-C-0031, ABG4 P00062 | 5444000 | 6199000 | 2016-12-15 | 2017-12-15
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-05 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH (ABG4 P00033) | W912GB-10-C-0031, ABG4 P00033 | 141234 | 142000 | 2015-03-30 | 2015-05-01
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-06 | 2012-02-01 | 2012-03-15 | FRG/Swarco Traffic Systems GmbH | W912GB-10-C-0031, ABG4 P00031 | 17713 | 17713 | 2014-12-31 | 2014-12-31
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-07 | 2012-02-01 | 2012-03-15 | FRG/CREOS GmbH | W912GB-10-C-0031, ABG4 P00032 | 473000 | 492000 | 2014-10-16 | 2014-10-16
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-08 | 2012-02-01 | 2012-03-15 | FRG/Omexom GA Sud GmbH | W912GB-10-C-0031, ABG4 P00066 | 62000 | 68000 | 2016-10-30 | 2016-12-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB-10-C-0031, P00071 | 419000 | 419000 | 2020-03-30 | 2020-03-30
2017-04-30 | 2012 | Defense Health Agency | 76007 | 76007-09 | 2012-02-01 | 2012-03-15 | SWK/Kaiserslautern Utility Company | W912GB-10-C-0031 | 419000 | 419000 | 2016-12-15 | 2017-11-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-10 | 2012-02-01 | 2012-03-15 | FRG/Zeppelin STREIF Baulogistik GmbH | W912GB-10-C-0031, ABG4 P00039 | 5235000 | 7121000 | 2025-12-30 | 2026-06-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-11 | 2018-10-14 | 2018-10-15 | Federal Republic of Germany | W912GB-10-C-0031 | 29261000 | 29261000 | 2025-06-30 | 2025-06-30
2017-06-30 | 2012 | Defense Health Agency | 76007 | 76007-12 | 2013-07-15 | 2013-08-27 | Federal Republic of Germany | W912GB-10-C-0031 | 37601000 | 37601000 | 2020-12-30 | 2020-12-30
2017-05-31 | 2012 | Defense Health Agency | 76007 | 76007-12 | 2012-02-01 | 2012-03-15 | FRG/Peter Gross Hoch- und Tiefbau GmbH & Co KG | W912GB-10-C-0031, ABG4 P00058 | 2539000 | 3109000 | 2016-04-30 | 2017-01-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-13 | 2012-02-01 | 2012-03-15 | FRG/Deutsche Telekom Technik GmbH | W912GB-10-C-0031, ABG4 P00037 | 1000 | 1000 | 2014-12-31 | 2014-12-31
2018-09-13 | 2012 | Defense Health Agency | 76007 | 76007-14 | 2012-02-01 | 2012-03-15 | FRG/ABG3 | W912GB-10-C-0031 | 30820000 | 30820000 | 2022-12-30 | 2023-12-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 76007-15 | 2012-02-01 | 2012-03-15 | DIRECT/ BB Government Services | W912GB-16-C-0038 | 21988000 | 24175000 | 2018-07-30 | 2018-12-30
2020-01-13 | 2012 | Defense Health Agency | 76007 | 76872 | 2018-10-14 | 2018-10-15 | Federal Republic of Germany | W912GB-10-C-0031 | 29261000 | 29261000 | 2025-06-30 | 2025-06-30
2021-05-14 | 2012 | Defense Health Agency | 76007 | 81412 | 2012-02-01 | 2012-03-15 | FRG/Rech Baugesellschaft mbH (P00024) / Waldhof-Weismann UG (P00034) / VSV Abbruch GmbH (P00045) / Bundesanstalt fur Immobilienaufgaben - Bundesforst (P00063) / F+R Industriedemontage und Abbruch GmbH (P00067) | W912GB-10-C-0031, ABG4: P00024, P00034, P00045, P00063, P00067 | 16019000 | 14187000 | 2025-12-30 | 2026-06-30
2018-09-13 | 2012 | Defense Health Agency | 76007 | 81412-02 | 2017-04-25 | 2017-05-25 | Federal Republic of Germany | W912GB-10-C-0031 | 16591000 | 16591000 | 2023-12-30 | 2023-12-30
2019-12-13 | 2012 | Defense Health Agency | 76007 | 90921 | 2018-10-14 | 2018-10-15 | Federal Republic of Germany | W912GB-10-C-0031 | 29261000 | 29261000 | 2025-06-30 | 2025-06-30
2021-05-14 | 2018 | Defense Health Agency | 76934 |  | 2018-05-24 | 2019-02-08 | Gilbane Federal JV | W912HN-19-C-3002 | 10042000 | 2562000 | 2020-09-02 | 2021-03-14
2021-05-14 | 2014 | Defense Health Agency | 77000 |  | 2014-03-24 | 2015-08-06 | Walsh Gilbane Joint Venture | W912DR-15-C-0015 | 206445000 | 218365000 | 2019-02-19 | 2021-12-31
2021-05-14 | 2018 | Defense Health Agency | 77140 |  | 2018-06-22 | 2019-01-24 | Walga Ross Group JV | W912DQ-19-F-4003 | 10585000 | 10530000 | 2020-09-16 | 2021-02-15
2021-05-14 | 2012 | Defense Health Agency | 77154 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 66430000 | 70594000 | 2016-12-06 | 2021-08-31
2020-01-13 | 2012 | Defense Health Agency | 77154 | 81291 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 66430000 | 68271000 | 2016-12-06 | 2019-11-01
2021-05-14 | 2016 | Defense Health Agency | 77986 |  | 2016-01-07 | 2016-12-14 | Federal Republic of Germany | W912GB-13-C-0005 | 24970000 | 31925000 | 2019-06-04 | 2022-02-02
2021-05-14 | 2018 | Defense Health Agency | 77987 |  | 2018-03-22 | 2018-09-21 | JJ Brun JV LLC | W9128F-18-0281 | 11396000 | 13579000 | 2021-06-17 | 2022-07-14
2021-05-14 | 2016 | Defense Health Agency | 78150 |  | 2015-11-05 | 2016-08-08 | Caddell-Nan joint Venture | N62742 16 C 1312 | 79722000 | 83356000 | 2018-12-21 | 2020-08-31
2021-05-14 | 2013 | Defense Health Agency | 80306 |  | 2013-07-25 | 2013-09-12 | G-W Management Services Inc. | N40080 10 D 0498 DO 0025 | 5286000 | 5217000 | 2013-12-13 | 2014-03-25
2021-05-14 | 2013 | Defense Health Agency | 80306 | 80306-01 | 2014-03-15 | 2016-09-01 | Whiting Turner Contracting Co | N40080 16 C 0172 | 29435000 | 30582000 | 2017-12-10 | 2018-08-31
2021-05-14 | 2016 | Defense Health Agency | 80412 |  | 2016-01-27 | 2016-05-17 | Swinerton Builders | W9128A-16-C-0004 | 26084000 | 27183000 | 2017-12-08 | 2019-03-29
2021-05-14 | 2016 | Defense Health Agency | 80412 | 80412-01 | 2016-10-21 | 2018-02-08 | Hensel-Phelps Const. Co. | W9128A-18-C-0001 | 74987000 | 73999000 | 2020-05-21 | 2020-11-20
2021-05-14 | 2016 | Defense Health Agency | 80412 | 80412-02 | 2020-07-31 | 2020-09-21 | Su-Mo Builders Inc. | W9128A-16-D-0011 TO W9128A20F0067 | 1484000 | 1484000 | 2022-05-02 | 2022-05-02
2021-05-14 | 2017 | Defense Health Agency | 80906 |  | 2017-05-23 | 2017-09-28 | Whiting Turner Contracting Co | N40080-17-C-0039 | 26338000 | 31488000 | 2019-05-10 | 2021-04-30
2021-05-14 | 2018 | Defense Health Agency | 80906 | 81420 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080-20-C0001 | 570000000 | 147197000 | 2026-03-01 | 2027-01-28
2021-05-14 | 2020 | Defense Health Agency | 80906 | 85667 | 2018-05-08 | 2019-11-12 | Clark Construction Group, LLC | N40080-20-C0001 | 570000000 | 147197000 | 2026-03-01 | 2027-01-28
2021-05-14 | 2016 | Defense Health Agency | 81422 |  | 2017-11-27 | 2018-09-24 | United Excel Corportation (now StructSure Projects) | W9126G-18-C-0077 | 40138000 | 47586000 | 2021-04-01 | 2021-11-04
2018-02-14 | 2016 | Defense Health Agency | 81422 |  | 2016-12-01 | 2017-03-09 | AMG Contractors, LLC | W9126G-17-C-0020 | 1251000 | 1265000 | 2017-06-23 | 2017-07-14
2021-04-13 | 2015 | Defense Health Agency | 81423 |  | 2015-03-20 | 2015-09-03 | JE Dunn Construction Company | W9127S-13-D-6001 | 33473000 | 34135000 | 2018-09-27 | 2018-11-10
2021-05-14 | 2015 | Defense Health Agency | 81430 |  | 2016-06-20 | 2018-01-18 | JE Dunn Construction Company | W9127S-13-D-6001 TO W91236-18-F-0014 | 52181000 | 56349000 | 2021-03-18 | 2021-08-18
2021-05-14 | 2014 | Defense Health Agency | 81436 |  | 2015-08-25 | 2016-03-17 | Contrack Watts Inc. | W912ER-11-D-0009-0012 | 24784000 | 26972000 | 2019-04-20 | 2020-01-20
2019-06-12 | 2014 | Defense Health Agency | 81631 |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc. | W912HN-11-D-0043-0044 | 1436000 | 1438000 | 2016-02-01 | 2016-02-01
2021-05-14 | 2018 | Defense Health Agency | 86204 |  | 2020-04-21 | 2020-07-08 | Kimball Construction Company, Inc | W912BU20C0033 | 3407000 | 3407000 | 2022-02-03 | 2022-02-03
2021-05-14 | 2019 | Defense Health Agency | 86943 |  | 2019-09-10 | 2019-12-15 | NVE-HHI JV | W9128F-20-C-0006 | 3384000 | 3384000 | 2021-06-15 | 2022-04-22
2021-05-14 | 2016 | Defense Health Agency | 86953 |  | 2016-07-25 | 2017-03-23 | M.A. Mortenson Company | W912QR-17-C-0009 | 54817000 | 55248000 | 2021-05-07 | 2021-08-25
2017-11-14 | 2016 | Defense Health Agency | 86953 | 86953-01 | 2016-07-25 | 2017-03-23 | M.A. Mortenson Company | W912QR-17-C-0009 | 1000 | 1000 | 2021-05-16 | 2021-05-16
2021-05-14 | 2018 | Defense Health Agency | 87208 |  | 2018-10-12 | 2019-04-10 | Shinsampeikensetsu-Unite Corporation JV | W912HV-19-C-0005 | 4111000 | 4265000 | 2020-08-21 | 2021-01-30
2021-05-14 | 2019 | Defense Health Agency | 89838 |  | 2019-07-09 | 2019-09-30 | DeMaria Building Co | N4008519C9124 | 28729000 | 28273000 | 2021-10-30 | 2022-07-05
2021-05-14 | 2019 | Defense Health Agency | 89902 |  | 2020-02-25 | 2020-08-18 | Korte Construction Company | N6945019D0910 | 10333000 | 21895000 | 2022-09-03 | 2022-09-03
2021-05-14 | 2020 | Defense Health Agency | 89906 |  | 2020-08-04 | 2020-09-30 | Soltek Pacific Construction Co. | N6247318D5855 | 15767000 | 15767000 | 2022-10-30 | 2022-10-30
2021-05-14 | 2018 | Defense Health Agency | 91884 |  | 2019-01-31 | 2019-08-08 | J.E. Dunn Construction | W912DQ-19-C-4011 | 296899000 | 302200000 | 2023-10-13 | 2023-10-13
2021-05-14 | 2019 | Defense Health Agency | 93298 |  | 2020-02-17 | 2020-08-25 | GCBJV1, Pensacola, FL | N6945019D0920 | 3859000 | 3910000 | 2022-06-30 | 2022-06-30
2021-05-14 | 2018 | Defense Health Agency | 93775 |  | 2019-03-19 | 2019-03-20 | Yerkes South, Inc | FA2823-19-C-A022 | 187008000 | 1877995000 | 2020-03-24 | 2020-07-22
2021-05-28 | 2013 | Defense Information Systems Agency | 13DISA01 |  | 2015-08-05 | 2015-08-19 | Bauamt Reutlingen | W912GB-15-C-011 | 2219820 | 2219820 | 2015-08-19 | 2021-06-30
2021-05-28 | 2014 | Defense Information Systems Agency | 14DISA01 |  | 2017-04-12 | 2017-07-13 | Heartwood Pacific, LLC | N6274217F0307 | 1781248 | 1781248 | 2018-12-31 | 2021-05-07
2012-05-28 | 2015 | Defense Information Systems Agency | 15DISA02 |  | 2018-05-02 | 2018-08-09 | Cockram Construction Australia Pty Ltd. 675 Victoria Street, Abbotsford Victoria 3067, Austrialia | N6274218C1306 | 8794967 | 12189000 | 2019-03-31 | 2020-03-31
2021-05-28 | 2013 | Defense Information Systems Agency | VDYDS97032 |  | 2013-05-24 | 2013-09-30 | River City Corporation, LLC | W912QR-13-0032 | 65994000 | 65994000 | 2015-12-30 | 2016-03-11
2021-06-02 | 2014 | DoD Education Activity | AM00021 |  | 2016-11-07 | 2017-11-20 | John C. Grimberg CO., Inc. | N4008018C0006 | 52553000 | 52183000 | 2020-01-09 | 2020-10-13
2021-06-01 | 2014 | DoD Education Activity | AM00031 |  | 2014-09-09 | 2014-11-06 | SAUER Incorporated | W91278-12-D-0039/30132665 | 32124000 | 33068283 | 2017-02-10 | 2017-10-31
2021-06-01 | 2016 | DoD Education Activity | AM00033 |  | 2016-07-25 | 2017-03-01 | DOBCO, Inc. | W912DS-17-C-0005/44966911 | 48535000 | 50878598 | 2020-03-05 | 2020-01-06
2021-06-01 | 2016 | DoD Education Activity | AM00035 |  | 2016-03-14 | 2017-03-29 | POETTKER CONSTRUCTION COMPANY | W912HN-17-C-0005/37035966 | 27223000 | 27209938 | 2019-04-26 | 2019-08-15
2021-06-01 | 2014 | DoD Education Activity | AM00046 | 246 | 2013-02-06 | 2016-03-16 | J&J Contractors & Engineers, Inc. | W912WJ-17-C-0004/57439943 | 35970000 | 37442688 | 2019-09-09 | 2019-08-20
2021-06-01 | 2017 | DoD Education Activity | AM00047 |  | 2018-01-03 | 2019-02-27 | Dobco, Inc. | W912BU-19-C-0017/53356011 | 47962590 | 49650036 | 2021-12-24 | 2022-02-25
2021-06-01 | 2016 | DoD Education Activity | AM00048 |  | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/39179628 | 25629526 | 27156016 | 2020-06-10 | 2021-05-10
2021-06-01 | 2016 | DoD Education Activity | AM00048 | 8 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/54560299 | 4286000 | 4286000 | 2020-06-10 | 2021-05-10
2021-06-01 | 2016 | DoD Education Activity | AM00048 | 9 | 2015-12-23 | 2016-09-30 | Carothers Construction, Inc | W91278-12-D-0037/54560300 | 15500000 | 15500000 | 2020-06-10 | 2021-05-10
2021-05-02 | 2014 | DoD Education Activity | AM00050 |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791250 | 33828106 | 2016-10-31 | 2018-05-30
2021-04-30 | 2015 | DoD Education Activity | AM00051 |  | 2016-02-26 | 2017-03-29 | WALSH FEDERAL, LLC | N4008517C8322 | 47374000 | 48359000 | 2020-03-28 | 2021-01-15
2021-06-02 | 2015 | DoD Education Activity | AM00103 |  | 2015-09-15 | 2016-07-01 | Munilla Construction Management, LLC | N6945016C1612 | 21000 | 70408000 | 2018-11-26 | 2020-09-04
2021-06-01 | 2016 | DoD Education Activity | AM00110 |  | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278-12-D-0037/41084584 | 27895686 | 30016180 | 2020-05-28 | 2021-04-23
2021-06-01 | 2016 | DoD Education Activity | AM00110 | 27 | 2015-12-15 | 2017-03-28 | Carothers Construction, Inc | W91278-12-D-0037/57076763 | 11115000 | 11115000 | 2020-05-28 | 2021-04-23
2021-06-02 | 2016 | DoD Education Activity | AM00115 |  | 2016-02-09 | 2016-07-20 | Construction SAN Jose SA | N6247016C6003 | 9233000 | 8295000 | 2019-03-27 | 2020-04-27
2021-06-01 | 2012 | DoD Education Activity | EU00031 |  | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029/27243529 | 77816984 | 88592980 | 2019-05-08 | 2019-10-31
2021-06-01 | 2012 | DoD Education Activity | EU00031 | 89 | 2016-07-07 | 2016-11-18 | LBB Trier | W912GB-11-C-0029/59013541 | 0 | 204671 | 2019-05-08 | 2019-10-31
2021-06-01 | 2013 | DoD Education Activity | EU00034 |  | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006/44599966 | 41569129 | 43920418 | 2018-12-24 | 2019-06-13
2021-06-01 | 2013 | DoD Education Activity | EU00034 | 45 | 2015-12-08 | 2016-07-22 | LBB Niederlassung Idar-Oberstein | W912GB-12-C-0006/50005397 | 0 | 388829 | 2018-12-24 | 2019-06-13
2021-05-02 | 2014 | DoD Education Activity | EU00037 |  | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/52029275 | 0 | 0 | 2021-03-29 | 2021-06-28
2021-06-01 | 2014 | DoD Education Activity | EU00037 | 1 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/52029300 | 89535967 | 96626581 | 2021-03-29 | 2021-06-28
2021-05-02 | 2014 | DoD Education Activity | EU00037 | 2 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/55123733 | 0 | 0 | 2021-03-29 | 2021-06-28
2021-05-02 | 2014 | DoD Education Activity | EU00037 | 3 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/55123739 | 0 | 0 | 2021-03-29 | 2021-06-28
2021-05-02 | 2014 | DoD Education Activity | EU00037 | 4 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/55123745 | 0 | 0 | 2021-03-29 | 2021-06-28
2021-05-02 | 2014 | DoD Education Activity | EU00037 | 5 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/55124187 | 0 | 0 | 2021-03-29 | 2021-06-28
2021-05-02 | 2013 | DoD Education Activity | EU00037 | 6 | 2017-06-09 | 2017-12-08 | LBB Kaiserslautern | W912GB-12-C-0024/64646665 | 0 | 0 | 2021-03-29 | 2021-06-28
2021-06-01 | 2017 | DoD Education Activity | EU00039 |  | 2019-03-19 | 2019-09-16 | LBB Kaiserslautern | W912GB-15-C-0013/47316927 | 42112535 | 42430404 | 2022-05-27 | 2023-08-08
2021-06-01 | 2014 | DoD Education Activity | EU00040 |  | 2016-10-21 | 2017-05-09 | LBB Kaiserslautern | W912GB-12-C-0025/52029339 | 43000974 | 49386020 | 2020-01-12 | 2021-03-26
2021-06-01 | 2014 | DoD Education Activity | EU00049 |  | 2015-11-24 | 2016-06-03 | Federal Republic of Germany | W912GB-12-C-0041/50728702 | 56357984 | 57165192 | 2021-07-23 | 2021-08-23
2021-05-02 | 2016 | DoD Education Activity | EU00051 |  | 2017-04-30 | 2017-07-20 | Staatliches Hochbauamt Reutlingen | W912GB-12-C-0030/54892604 | 0 | 0 | 2021-01-23 | 2022-05-30
2021-05-02 | 2016 | DoD Education Activity | EU00051 | 50 | 2017-04-30 | 2017-07-20 | Staatliches Hochbauamt Reutlingen | W912GB-12-C-0030/54892649 | 0 | 0 | 2021-01-23 | 2022-05-30
2021-06-01 | 2016 | DoD Education Activity | EU00051 | 51 | 2017-04-30 | 2017-07-20 | Staatliches Hochbauamt Reutlingen | W912GB-12-C-0030/54892650 | 46915286 | 50469213 | 2021-01-23 | 2022-05-30
2021-06-01 | 2015 | DoD Education Activity | EU00064 |  | 2017-06-29 | 2017-09-21 | Joint Venture WMV Brussels American School | W912GB-17-C-0018/44739768 | 28765482 | 29039105 | 2020-10-24 | 2023-03-31
2021-06-01 | 2016 | DoD Education Activity | EU00068 |  | 2017-09-05 | 2018-04-20 | Staatliches Hochbauamt Amberg | W912GB-12-C-0036/57200363 | 33667431 | 36405610 | 2021-03-16 | 2022-03-30
2021-06-01 | 2014 | DoD Education Activity | EU00072 |  | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB-12-C-0022/48719947 | 50967096 | 52541001 | 2019-04-19 | 2018-07-26
2021-06-01 | 2014 | DoD Education Activity | EU00072 | 7 | 2015-11-24 | 2016-04-21 | Federal Republic of Germany | W912GB-12-C-0022/50815967 | 16940 | 227603 | 2019-04-19 | 2018-07-26
2021-06-01 | 2014 | DoD Education Activity | EU00072 | 720 | 2015-11-25 | 2016-04-22 | Federal Republic of Germany | W912GB-12-C-0022/57804120 | 75891 | 85778 | 2019-04-19 | 2018-07-26
2021-06-02 | 2018 | DoD Education Activity | EU00117 |  | 2019-05-01 | 2019-09-27 | ICM SPA | N6247019C5007 | 36391000 | 39667000 | 2022-01-27 | 2022-12-02
2021-06-01 | 2015 | DoD Education Activity | PA00017 |  | 2016-07-15 | 2016-12-23 | Nippo Corporation | W912HV-17-C-0004/37880445 | 61521811 | 88403066 | 2020-11-17 | 2023-01-22
2021-06-01 | 2013 | DoD Education Activity | PA00021 |  | 2015-06-12 | 2016-02-19 | Nippo Corporation | W912HV-16-C-0004/32602254 | 47986812 | 49347680 | 2018-11-03 | 2019-03-14
2021-06-01 | 2015 | DoD Education Activity | PA00022 |  | 2018-09-21 | 2019-07-29 | Nippo Corporation | W912HV19C0007/36943919 | 52447552 | 52441293 | 2022-08-05 | 2022-08-05
2021-06-01 | 2015 | DoD Education Activity | PA00023 |  | 2016-06-13 | 2016-11-22 | NES PACIFIC LIMITED LIABILITY CO. | W912HV-17-C-0002/37064811 | 27722277 | 30088971 | 2019-05-28 | 2021-01-21
2021-06-01 | 2013 | DoD Education Activity | PA00028 |  | 2016-06-21 | 2017-07-18 | Gilbane Japan GK | W912HV-17-C-0007/32174203 | 26840313 | 28001030 | 2019-07-19 | 2021-02-25
2021-06-01 | 2017 | DoD Education Activity | PA00032 |  | 2017-06-22 | 2017-12-22 | NISHIMATSU CONSTRUCTION CO., LTD. | W912HV18C0002/37880684 | 72844929 | 80065080 | 2021-02-15 | 2021-03-10
2021-05-11 | 2019 | Marine Corps Active | M00146130F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 33831000 | 33926000 | 2025-08-12 | 2025-08-12
2021-05-11 | 2019 | Marine Corps Active | M00146142F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 40771000 | 41043000 | 2025-08-12 | 2025-08-12
2021-05-11 | 2019 | Marine Corps Active | M00146162F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 41270000 | 43407000 | 2025-08-12 | 2025-08-12
2021-05-11 | 2015 | Marine Corps Active | M00146193 |  | 2015-06-17 | 2016-12-22 | GARNEY COMPANIES, INC. | N4008517C8315 AWD | 55798000 | 55755000 | 2021-11-23 | 2021-11-23
2021-05-11 | 2016 | Marine Corps Active | M00146194 |  | 2016-03-29 | 2016-08-31 | M A MORTENSON COMPANY | N4008516C5506 AWD | 28561000 | 27798000 | 2019-01-29 | 2019-01-29
2021-05-11 | 2019 | Marine Corps Active | M00146199 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N4008520C8501 AWD | 5813000 | 126433000 | 2022-07-14 | 2023-02-07
2021-05-11 | 2016 | Marine Corps Active | M00146222 |  | 2019-01-23 | 2019-04-18 | SAUER, INC. | N4008519C9021 | 21793000 | 21233000 | 2021-06-10 | 2021-06-10
2021-05-11 | 2019 | Marine Corps Active | M00146235 |  | 2019-08-05 | 2019-12-23 | WALSH FEDERAL, LLC | N4008520C8501 AWD | 53073000 | 105329000 | 2022-07-14 | 2023-02-07
2021-05-11 | 2020 | Marine Corps Active | M00146246F |  | 2020-02-06 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 17747042 | 18812000 | 2025-08-12 | 2025-08-12
2021-05-11 | 2020 | Marine Corps Active | M00146249 |  | 2020-10-26 | 2021-02-18 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008516D6303 N4008521F4682 | 1368000 | 1313000 | 2022-03-05 | 2022-03-05
2021-05-11 | 2019 | Marine Corps Active | M00146254F |  | 2020-02-07 | 2020-08-12 | WHITING-TURNER CONTRACTING CO | N4008520C0055 AWD | 30990000 | 30879000 | 2025-08-12 | 2025-08-12
2021-05-11 | 2018 | Marine Corps Active | M00146766 |  | 2018-09-04 | 2018-09-29 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008516D6303 N4008518F7217 | 2468000 | 2430000 | 2020-01-08 | 2020-04-15
2021-05-11 | 2020 | Marine Corps Active | M00243312 |  | 2020-03-02 | 2020-05-29 | BRISTOL DESIGN BUILD SERVICES, LLC | N6247317D4627 N6247320F4683 | 9525039 | 10213000 | 2022-02-03 | 2022-02-03
2021-05-11 | 2017 | Marine Corps Active | M00263403 |  | 2017-01-27 | 2018-07-31 | KORTE CONSTRUCTION COMPANY | N4008518C0640 AWD | 30382000 | 29524000 | 2021-02-28 | 2021-11-03
2021-05-11 | 2019 | Marine Corps Active | M00263404 |  | 2019-02-14 | 2019-07-10 | R. C. CONSTRUCTION | N4008519C9017 AWD | 36938000 | 35698000 | 2021-08-17 | 2021-11-04
2021-05-11 | 2018 | Marine Corps Active | M00264542 |  | 2018-08-08 | 2019-05-30 | ARCHER WESTERN FEDERAL JV | N4008019C0023 AWD | 21419000 | 20772000 | 2020-10-30 | 2021-12-31
2021-05-11 | 2014 | Marine Corps Active | M00264588 |  | 2017-02-10 | 2018-09-29 | WHITING-TURNER CONTRACTING CO | N4008018C0034 AWD | 23040000 | 21739000 | 2020-06-06 | 2021-04-09
2021-05-11 | 2015 | Marine Corps Active | M00264635 |  | 2016-05-16 | 2016-11-16 | G-W MANAGEMENT SERVICES, LLC | N4008017C0014 AWD | 10883000 | 12101000 | 2018-03-25 | 2020-02-28
2021-05-11 | 2014 | Marine Corps Active | M00264677 |  | 2015-10-28 | 2016-03-31 | HARKINS BUILDERS INC. | N4008016C0151 AWD | 27064000 | 26782000 | 2018-01-05 | 2018-10-23
2021-05-11 | 2020 | Marine Corps Active | M00264719 |  | 2020-10-26 | 2021-03-22 | CLARK CONSTRUCTION GROUP, LLC. | N4008021C0005 AWD | 586000 | 586000 | 2023-07-05 | 2023-07-05
2021-05-11 | 2019 | Marine Corps Active | M00264724 |  | 2019-06-05 | 2019-08-15 | G-W MANAGEMENT SERVICES, LLC | N4008019D0015 N4008019F4870 | 14142000 | 13757000 | 2021-01-30 | 2021-07-01
2021-05-11 | 2020 | Marine Corps Active | M00264733 |  | 2020-07-23 | 2020-09-29 | TUCKMAN-BARBEE CONSTRUCTION | N4008019D0018 N4008020F5390 | 3040000 | 2941000 | 2021-11-10 | 2021-11-10
2021-05-11 | 2015 | Marine Corps Active | M00318861 |  | 2015-04-09 | 2015-09-01 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274215C1305 AWD | 51071000 | 52395000 | 2018-08-11 | 2021-02-03
2021-05-11 | 2014 | Marine Corps Active | M00318863 |  | 2015-07-14 | 2016-09-19 | CONTRACK WATTS, INC | N6274216C1325 AWD | 50583000 | 49122000 | 2019-04-17 | 2020-02-21
2021-05-11 | 2018 | Marine Corps Active | M00318877 |  | 2020-05-20 | 2020-09-23 | NIKING CORP. | N6274220C1304 AWD | 34513000 | 18044000 | 2022-01-07 | 2022-01-07
2020-11-16 | 2018 | Marine Corps Active | M00318877
2021-05-11 | 2014 | Marine Corps Active | M00318884 |  | 2014-02-14 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720000 | 16261000 | 2016-12-18 | 2019-10-24
2021-05-11 | 2018 | Marine Corps Active | M00318887 |  | 2018-04-04 | 2018-12-28 | KIEWIT INFRASTRUCTURE WEST CO. | N6274219C1321 AWD | 18697000 | 19210000 | 2020-08-19 | 2021-01-25
2021-05-11 | 2016 | Marine Corps Active | M00318902 |  | 2016-05-27 | 2016-11-18 | NOVA GROUP INC | N6274217C1320 AWD | 24797000 | 29675000 | 2019-06-06 | 2021-08-29
2021-05-11 | 2014 | Marine Corps Active | M00318907 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 47645000 | 40870000 | 2020-09-18 | 2020-12-15
2021-05-11 | 2014 | Marine Corps Active | M00318908 |  | 2014-10-02 | 2015-04-14 | HENSEL PHELPS CONSTRUCTION CO. | N6274215C1301 AWD | 53999000 | 50638000 | 2020-09-18 | 2020-12-15
2021-05-11 | 2017 | Marine Corps Active | M00318923 |  | 2017-04-07 | 2017-08-21 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6274217C1307 AWD | 72494000 | 71579000 | 2020-03-08 | 2021-04-05
2021-05-11 | 2019 | Marine Corps Active | M00318946 |  | 2018-11-20 | 2019-05-31 | HENSEL PHELPS CONSTRUCTION CO. | N6274219C1303 AWD | 62559000 | 62307000 | 2021-09-07 | 2022-08-27
2021-05-11 | 2019 | Marine Corps Active | M00681079 |  | 2019-07-24 | 2019-12-12 | ORION CONSTRUCTION CORPORATION | N6247320C0612 AWD | 35918000 | 34354000 | 2022-05-30 | 2022-05-30
2021-05-11 | 2020 | Marine Corps Active | M006811090 |  | 2020-04-16 | 2020-09-24 | DPR-RQ CONSTRUCTION, LLC | N6247320C0055 AWD | 53546419 | 58462000 | 2024-01-07 | 2024-01-07
2021-05-11 | 2021 | Marine Corps Active | M006811090A
2021-05-11 | 2021 | Marine Corps Active | M006811130 |  | 2020-07-23 | 2021-02-18 | HARPER CONSTRUCTION COMPANY, INC | N6247321D1206 N6247321F4378 | 42661879 | 42661879 | 2023-05-13 | 2023-05-13
2021-03-10 | 2021 | Marine Corps Active | M006811130
2021-05-11 | 2018 | Marine Corps Active | M006811310 |  | 2018-04-12 | 2018-09-27 | HARPER CONSTRUCTION COMPANY, INC | N6247317D0817 | 62328000 | 44725000 | 2020-10-10 | 2021-10-05
2021-05-11 | 2018 | Marine Corps Active | M006811599 |  | 2019-01-15 | 2019-02-27 | ORION CONSTRUCTION CORPORATION | N6247318D5860 N6247319F4359 | 1876000 | 2007000 | 2020-02-26 | 2020-02-26
2021-05-11 | 2019 | Marine Corps Active | M006811901 |  | 2018-11-27 | 2019-05-02 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F4561 | 46146000 | 46269000 | 2022-06-09 | 2022-12-09
2021-05-11 | 2020 | Marine Corps Active | M006812000 |  | 2020-05-28 | 2020-12-17 | WHITING-TURNER CONTRACTING CO | N6247318D5858 N6247321F4212 | 3056000 | 3056000 | 2025-02-14 | 2025-02-14
2021-05-11 | 2019 | Marine Corps Active | M00681334 |  | 2019-06-21 | 2019-08-22 | I E PACIFIC INC | N6247317D4628 N6247319F5136 | 14684000 | 14911000 | 2021-08-06 | 2021-10-13
2021-05-11 | 2019 | Marine Corps Active | M006815001 |  | 2019-01-30 | 2019-04-09 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 | 9032000 | 8748000 | 2020-10-15 | 2021-06-14
2021-05-11 | 2019 | Marine Corps Active | M006815002 |  | 2019-02-05 | 2019-03-25 | SYNERGY ELECTRIC COMPANY INC | N6247319D2430 | 3326000 | 3443000 | 2020-03-30 | 2020-03-20
2021-05-11 | 2019 | Marine Corps Active | M00681574 |  | 2019-07-09 | 2019-08-22 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 N6247319F5115 | 12715000 | 12544000 | 2021-06-07 | 2021-08-25
2021-05-11 | 2014 | Marine Corps Active | M00681970 |  | 2014-07-01 | 2015-12-30 | SOLPAC CONSTRUCTION INC | N6247310D5411 0012 | 19459000 | 22991000 | 2018-04-27 | 2019-09-14
2021-05-11 | 2017 | Marine Corps Active | M60169464 |  | 2017-02-23 | 2017-06-29 | THE HASKELL COMPANY | N4008517C8327 AWD | 78310000 | 78924000 | 2020-07-13 | 2021-03-10
2021-05-11 | 2018 | Marine Corps Active | M62204930 |  | 2017-03-07 | 2018-04-18 | M A MORTENSON COMPANY | N6247318D5850 N6247318F4497 | 23592000 | 23033000 | 2020-05-02 | 2020-05-17
2021-05-11 | 2020 | Marine Corps Active | M626131005
2021-05-11 | 2018 | Marine Corps Active | M626131006
2021-05-11 | 2017 | Marine Corps Active | M626131701
2021-05-11 | 2020 | Marine Corps Active | M626132001 |  | 2020-11-13 | 2021-02-11 | SANKYO REINETSU CO., LTD. | N4008420D0073 N4008421F4127 | 18797000 | 17902000 | 2023-07-02 | 2023-07-02
2021-05-11 | 2016 | Marine Corps Active | M62613604
2021-05-11 | 2018 | Marine Corps Active | M62974539 |  | 2018-05-02 | 2018-07-03 | WHITING-TURNER CONTRACTING CO | N6247317D0822 N6247318F4783 | 37962000 | 37684000 | 2020-06-28 | 2021-10-08
2021-05-11 | 2016 | Marine Corps Active | M62974602 |  | 2017-03-31 | 2017-07-27 | STRAUB CONSTRUCTION, INC. | N6247316D1887 N6247317F4044 | 43119000 | 40941000 | 2019-06-30 | 2020-06-22
2021-05-11 | 2017 | Marine Corps Active | M62974612 |  | 2017-07-12 | 2019-06-13 | HARPER CONSTRUCTION COMPANY, INC | N6247316D1881 N6247319F4705 | 62293000 | 61877000 | 2022-06-06 | 2023-01-23
2021-05-11 | 2019 | Marine Corps Active | M670011199F |  | 2019-10-15 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 19142000 | 19343000 | 2024-10-12 | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | M670011203F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 27688000 | 28212000 | 2024-09-30 | 2025-09-27
2021-05-11 | 2016 | Marine Corps Active | M670011280 |  | 2016-12-16 | 2017-05-30 | CADDELL CONSTRUCTION CO. (DE), LLC | N4008517C8325 AWD | 47882000 | 50835000 | 2019-06-24 | 2022-04-21
2021-05-11 | 2019 | Marine Corps Active | M670011300F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 17826000 | 18293000 | 2024-10-12 | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | M670011312F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 55017000 | 57370000 | 2024-09-30 | 2025-09-27
2021-05-11 | 2018 | Marine Corps Active | M670011320 |  | 2018-08-09 | 2018-09-28 | SAUER, INC. | N4008518C0610 AWD | 37174000 | 35527000 | 2020-10-23 | 2021-10-01
2021-05-11 | 2020 | Marine Corps Active | M670011338F |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N4008520C0145 AWD | 51246000 | 52052000 | 2025-05-27 | 2025-05-27
2021-05-11 | 2019 | Marine Corps Active | M670011387F |  | 2019-10-09 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N4008520C8505 AWD | 64921000 | 62987000 | 2025-03-06 | 2025-03-06
2021-05-11 | 2018 | Marine Corps Active | M670011479 |  | 2018-11-06 | 2019-06-14 | SAUER, INC. | N4008519C9053 AWD | 3247000 | 3258000 | 2020-10-26 | 2021-03-28
2021-05-11 | 2020 | Marine Corps Active | M670011483 |  | 2020-07-17 | 2020-09-25 | SAUER, INC. | N4008520D0035 N4008520F6732 | 11460484 | 12079000 | 2021-09-28 | 2021-09-28
2021-05-11 | 2020 | Marine Corps Active | M670011495 |  | 2019-12-05 | 2020-08-13 | RQ CONSTRUCTION, LLC | N4008520C0145 AWD | 35517314 | 37433000 | 2023-03-05 | 2023-03-05
2021-05-11 | 2018 | Marine Corps Active | M670011498 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N4008514D7742 N4008519F4172 | 3135000 | 3321000 | 2019-11-09 | 2021-07-22
2021-05-11 | 2018 | Marine Corps Active | M670011503 |  | 2018-07-14 | 2018-11-14 | MECHWORKS MECHANICAL CONTRACTORS | N4008514D7742 N4008519F4172 | 3833000 | 3931000 | 2019-11-09 | 2021-07-22
2021-05-11 | 2019 | Marine Corps Active | M670011505F |  | 2020-01-23 | 2020-07-24 | ARCHER WESTERN CONSTRUCTION, LLC | N4008520C8505 AWD | 66036000 | 63805000 | 2019-10-25 | 2025-03-06
2021-05-11 | 2020 | Marine Corps Active | M670011506F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 28045000 | 30283000 | 2024-09-30 | 2025-09-27
2021-05-11 | 2020 | Marine Corps Active | M670011507F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 17318680 | 20461000 | 2024-05-27 | 2024-05-27
2021-05-11 | 2019 | Marine Corps Active | M670011509F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 33391000 | 39917000 | 2017-05-30 | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | M670011512F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 135347000 | 137292000 | 2025-05-27 | 2025-05-27
2021-05-11 | 2020 | Marine Corps Active | M670011518F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 29242000 | 29594000 | 2024-09-30 | 2025-09-27
2021-05-11 | 2020 | Marine Corps Active | M670011519F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 36463000 | 37373000 | 2024-09-30 | 2025-09-27
2021-05-11 | 2019 | Marine Corps Active | M670011520F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 15383000 | 15577000 | 2019-10-25 | 2024-10-12
2021-05-11 | 2019 | Marine Corps Active | M670011522F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 26607000 | 26732000 | 2019-10-25 | 2024-10-12
2021-05-11 | 2019 | Marine Corps Active | M670011524F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 14143000 | 14259000 | 2021-06-16 | 2024-10-12
2021-05-11 | 2019 | Marine Corps Active | M670011525F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 7375000 | 7534000 | 2020-12-29 | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | M670011527F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 48103000 | 48492000 | 2025-05-27 | 2025-05-27
2021-05-11 | 2020 | Marine Corps Active | M670011529F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 22970805 | 24250000 | 2024-10-12 | 2024-10-12
2021-05-11 | 2020 | Marine Corps Active | M670011533F |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 43802000 | 44885000 | 2024-09-30 | 2025-09-27
2021-05-11 | 2020 | Marine Corps Active | M670011800 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N4008521C0017 AWD | 5850000 | 5850000 | 2026-07-23 | 2026-07-23
2021-05-11 | 2021 | Marine Corps Active | M670011800A |  | 2020-07-10 | 2021-03-02 | ARCHER WESTERN FEDERAL JV | N4008521C0017 P00002 | 102629610 | 102629610 | 2026-07-23 | 2026-07-23
2021-05-11 | 2020 | Marine Corps Active | M670011801 |  | 2020-07-10 | 2020-12-22 | ML: CON21 DC/AM | N4008521C0017 AWD | 5850000 | 5850000 | 2026-07-23 | 2026-07-23
2021-05-11 | 2020 | Marine Corps Active | M67001378F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 223502000 | 226220000 | 2024-10-12 | 2025-02-18
2021-05-11 | 2016 | Marine Corps Active | M67001686 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 3640000 | 3728000 | 2018-04-06 | 2021-04-22
2021-05-11 | 2020 | Marine Corps Active | M67001695F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 67658000 | 69088000 | 2024-10-12 | 2025-02-18
2021-05-11 | 2020 | Marine Corps Active | M67001707F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 79978000 | 81720000 | 2024-10-12 | 2025-02-18
2021-05-11 | 2014 | Marine Corps Active | M67001726 |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159000 | 20092000 | 2019-02-01 | 2019-02-01
2021-05-11 | 2020 | Marine Corps Active | M67001728F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 48575000 | 49303000 | 2024-10-12 | 2025-02-18
2021-05-11 | 2016 | Marine Corps Active | M67001729 |  | 2016-08-05 | 2016-09-28 | BLUE ROCK STRUCTURES, INC.P.O. BOX 129 (INVOICES/ACTIONS) | N4008516D6300 0003 | 1885000 | 2514000 | 2018-04-06 | 2021-04-22
2021-05-11 | 2020 | Marine Corps Active | M67001883F |  | 2020-02-14 | 2020-07-24 | RQ-DPR JV | N4008520C0044 AWD | 54587000 | 56313000 | 2024-09-30 | 2025-09-27
2021-05-11 | 2019 | Marine Corps Active | M67004947 |  | 2019-08-07 | 2020-01-31 | THE HASKELL COMPANY | N4008520C8504 AWD | 29418000 | 28267000 | 2022-05-04 | 2022-05-04
2021-05-11 | 2018 | Marine Corps Active | M67004971 |  | 2017-12-12 | 2018-03-15 | DRACE CONSTRUCTION CORP. | N4008516D5524 N4008518F5082 | 1982000 | 1918000 | 2019-07-05 | 2019-07-05
2021-05-11 | 2016 | Marine Corps Active | M67004972 |  | 2016-12-14 | 2017-03-22 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N6945016D1112 WE01 | 8625000 | 8270000 | 2019-01-28 | 2019-02-23
2021-05-11 | 2018 | Marine Corps Active | M67004977 |  | 2018-07-18 | 2019-03-07 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008519C9126 | 23298000 | 23893000 | 2021-04-29 | 2021-05-27
2021-05-11 | 2016 | Marine Corps Active | M67029007 |  | 2016-10-25 | 2017-04-19 | TIDEWATER, INC | N4008017C0024 AWD | 1257000 | 1311000 | 2018-04-19 | 2020-07-30
2021-05-11 | 2016 | Marine Corps Active | M673991232 |  | 2017-06-27 | 2017-09-26 | PROCAL ELECTRIC INC | N6247316D1861 N6247317F4699 | 9329000 | 10999000 | 2019-04-19 | 2021-04-23
2021-05-11 | 2018 | Marine Corps Active | M67399192 |  | 2017-10-17 | 2018-09-29 | CDM CONSTRUCTORS INC | N6247318C4602 AWD | 55390000 | 53588000 | 2021-09-28 | 2022-05-10
2021-05-11 | 2015 | Marine Corps Active | M67399222 |  | 2016-02-22 | 2016-08-31 | AT&T GOVERNMENT SOLUTIONS, INC | N6247316C0601 AWD | 12948000 | 15100000 | 2019-03-04 | 2020-02-14
2021-05-11 | 2015 | Marine Corps Active | M67400213
2021-05-11 | 2016 | Marine Corps Active | M67400606 |  | 2016-07-20 | 2016-09-15 | NAVY STANDARD DOCUMENT | N4008516C5505 AWD | 8853000 | 8792000 | 2019-08-03 | 2018-03-26
2021-05-11 | 2017 | Marine Corps Active | M67400807
2021-05-11 | 2016 | Marine Corps Active | M67604132 |  | 2016-07-08 | 2016-08-31 | REYES CONSTRUCTION INC | N6247314D0068 0008 | 2887000 | 2720000 | 2017-10-30 | 2017-10-30
2020-11-16 | 2020 | Marine Corps Active | M67695009
2021-05-11 | 2020 | Marine Corps Active | M67695009 |  | 2020-06-26 | 2020-09-16 | THE CLEMENT GROUP LLC | N6945019D0918 N6945020F0894 | 10933245 | 11101000 | 2022-03-25 | 2022-03-25
2021-05-11 | 2017 | Marine Corps Active | M67865198 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 35632000 | 39482000 | 2020-01-14 | 2020-06-26
2021-05-11 | 2018 | Marine Corps Active | M67865198 | M67865198A | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 79399000 | 81408000 | 2020-01-14 | 2020-06-26
2021-05-11 | 2017 | Marine Corps Active | M67865203 |  | 2017-08-29 | 2018-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318C4605 AWD | 38707000 | 41834000 | 2020-01-14 | 2020-06-26
2021-05-11 | 2018 | Marine Corps Active | M67865210 |  | 2018-05-16 | 2018-08-30 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247318F4873 | 34513000 | 39628000 | 2020-05-20 | 2021-02-26
2021-05-11 | 2019 | Marine Corps Active | M67865222 |  | 2018-11-16 | 2019-03-14 | Granite Construction, Inc | N62473-19-C-5826 | 11358000 | 12459000 | 2020-09-27 | 2021-02-06
2021-05-11 | 2019 | Marine Corps Active | M67865238 |  | 2019-01-03 | 2019-03-08 | Teehee Engineering Inc. | N6247319C2425 | 4828000 | 7007000 | 2020-04-06 | 2020-04-06
2021-05-11 | 2017 | Marine Corps Active | M67865249 |  | 2017-09-19 | 2017-12-18 | R A BURCH CONSTRUCTION CO INC | N6247316D1884 N6247318F4138 | 32536000 | 34617000 | 2019-09-24 | 2020-10-01
2021-05-11 | 2019 | Marine Corps Active | N41557270 |  | 2019-01-25 | 2019-09-12 | GILBANE SMCC ECC LLC | N6274219D1331 N6274219F9926 | 27191000 | 25271000 | 2022-03-25 | 2022-03-25
2021-05-11 | 2019 | Marine Corps Active | N41557295 |  | 2019-04-15 | 2019-09-16 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274219C1301 AWD | 18002000 | 16498000 | 2021-12-04 | 2021-12-04
2021-05-11 | 2021 | Marine Corps Active | N41557296 |  | 2020-08-18 | 2021-03-17 | CORE TECH-HDCC-KAJIMA LLC | N6274219D1330 N6274221F9928 | 17683000 | 17683000 | 2023-03-28 | 2023-03-28
2021-05-11 | 2018 | Marine Corps Active | N41557601 |  | 2017-06-30 | 2018-05-16 | HENSEL PHELPS CONSTRUCTION CO. | N6274218C1316 AWD | 75233000 | 69204000 | 2020-10-02 | 2021-03-27
2021-05-11 | 2016 | Marine Corps Active | N41557715 |  | 2016-04-06 | 2017-08-24 | BLACK CONSTRUCTION CORP. | N6274217C1319 AWD | 123661000 | 100002000 | 2020-11-26 | 2021-11-08
2021-05-11 | 2021 | Marine Corps Active | N61159311 |  | 2020-09-14 | 2021-03-15 | HENSEL PHELPS CONSTRUCTION CO. | N6274219D1332 N6274221F9927 | 27795000 | 27795000 | 2023-08-23 | 2023-08-23
2021-05-11 | 2021 | Marine Corps Active | N61159312
2021-05-11 | 2021 | Marine Corps Active | N61159804
2021-05-11 | 2019 | Marine Corps Active | N62813216 |  | 2019-09-06 | 2020-02-03 | RORE, INC. | N6247818D4024 N6274220F4001 | 17897000 | 17408000 | 2020-12-29 | 2022-01-02
2021-05-11 | 2018 | Marine Corps Reserve | M67861650 |  | 2018-12-13 | 2019-03-19 | NAVY STANDARD DOCUMENT | USACE | 11741000 | 11065000 | 2020-11-20 | 2020-11-20
2021-05-11 | 2017 | Marine Corps Reserve | M68479135 |  | 2018-08-16 | 2019-01-22 | OAK GROUP, INC., THE | N4008517D5038 N4008519F4510 | 2109000 | 2127000 | 2020-01-28 | 2020-10-31
2021-05-11 | 2016 | Marine Corps Reserve | N50092152 |  | 2019-05-02 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N4008519C9061 AWD | 18501000 | 17603000 | 2021-09-14 | 2021-10-05
2021-05-11 | 2020 | Marine Corps Reserve | N83447091
2021-05-11 | 2020 | Marine Corps Reserve | N83447181
2021-05-11 | 2020 | Marine Corps Reserve | N83447222 |  | 2020-05-08 | 2020-09-24 | N6945020C2575 AWD | N6945020C2575 AWD | 1763000 | 1763000 | 2021-09-20 | 2021-09-21
2020-11-16 | 2020 | Marine Corps Reserve | N83447222
2021-04-30 | 2013 | Missile Defense Agency | 630 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 114390000 | 2015-08-30 | 2016-05-12
2021-04-30 | 2014 | Missile Defense Agency | 630 | 646 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300000 | 66900000 | 2015-08-30 | 2016-05-12
2021-04-30 | 2014 | Missile Defense Agency | 634 |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300000 | 15604000 | 2016-01-06 | 2016-05-02
2021-04-30 | 2016 | Missile Defense Agency | 640 |  | 2015-06-10 | 2016-02-10 | AMEC PROGRAMS, INC. | W912GB-16-C-0005 | 141906057 | 171152000 | 2018-11-09 | 2022-07-13
2021-04-30 | 2017 | Missile Defense Agency | 653 |  | 2017-02-01 | 2017-07-25 | AMES 1/Conam JV | W911KB-17-C-0029 | 6954581 | 8191098 | 2019-08-14 | 2021-07-19
2021-04-30 | 2017 | Missile Defense Agency | 657 |  | 2016-12-14 | 2017-04-28 | UNIT-ASRC Construction, LLC | W911KB-17-C-0002 | 112949720 | 119078184 | 2019-08-23 | 2020-06-01
2021-04-30 | 2017 | Missile Defense Agency | 657 |  | 2017-11-14 | 2018-02-15 | STG Pacific, LLC | W911KB-18-C-0015 | 24399601 | 24558572 | 2019-08-30 | 2019-06-27
2021-04-30 | 2017 | Missile Defense Agency | 657 |  | 2018-04-05 | 2018-09-07 | White Mountain Construction Company LLC | W911KB-18-R-0006 | 13335000 | 14660442 | 2020-09-30 | 2020-09-29
2021-04-30 | 2019 | Missile Defense Agency | 659 |  | 2019-09-23 | 2019-12-18 | CP04-RED POINT CONSTRUCTION, LLC | W911KB20C0002 | 13820000 | 15307457 | 2021-06-14 | 2021-08-16
2021-04-30 | 2019 | Missile Defense Agency | 659 |  | 2018-10-10 | 2019-03-08 | CP03-UNIT-ASRC Construction LLC | W911KB19C0001 | 128657500 | 131992899 | 2021-06-30 | 2021-08-21
2021-04-30 | 2017 | Missile Defense Agency | 673 |  | 2017-04-15 | 2017-08-03 | Indyne, Inc. | W912DY-11-D-0002 | 877752 | 1098939 | 2019-06-27 | 2021-04-30
2021-04-30 | 2018 | Missile Defense Agency | 674 |  | 2018-01-05 | 2018-05-07 | CP02-Brice Civil Constructors | W911KB18C0028 | 18965310 | 19525000 | 2018-10-30 | 2018-10-11
2021-04-30 | 2018 | Missile Defense Agency | 674 |  | 2018-02-16 | 2018-06-07 | CP02TP-Construction Services SATOC | W912DY-14-D-0042 | 2432439 | 2432439 | 2018-10-31 | 2018-10-11
2021-04-30 | 2018 | Missile Defense Agency | 674 |  | 2018-04-17 | 2018-07-20 | CP03-Watterson Construction Company | W911KB18C0030 | 28807000 | 32089650 | 2020-11-01 | 2021-03-29
2021-04-30 | 2018 | Missile Defense Agency | 674 |  | 2018-09-23 | 2018-12-20 | CP04-NEESER CONSTRUCTION, INC | W911KB19C0006 | 83991000 | 99292922 | 2021-09-30 | 2022-09-09
2021-04-30 | 2018 | Missile Defense Agency | 674 |  | 2018-02-05 | 2018-04-10 | CP01-Alaska Aggregate Products, LLC | W911KB18C0023 | 2600710 | 2549000 | 2018-06-30 | 2018-06-30
2021-04-30 | 2021 | Missile Defense Agency | 680 |  | 2020-09-28 | 2021-03-17 | Davis Constructors & Engineers, Inc | W911KB21C0012 | 45487063 | 43824960 | 2023-01-31 | 2023-01-31
2015-06-01 | 2008 | National Geospatial-Intelligence Agency | 65416 |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture | W912DR-07-C-0027 | 1409901000 | 1467244000 | 2011-12-22 | 2015-11-21
2021-04-30 | 2018 | National Geospatial-Intelligence Agency | NGA-016A |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ-17-R-7000 | 319965869 | 326291269 | 2023-10-19 | 2024-01-02
2021-04-30 | 2018 | National Geospatial-Intelligence Agency | NGA-016A-IPO |  | 2019-04-07 | 2019-07-10 | Modular Management Group (MMG) | W912DQ-17-C-7002 | 3146064 | 3152373 | 2024-07-08 | 2024-07-08
2021-04-30 | 2019 | National Geospatial-Intelligence Agency | NGA-016B |  | 2018-04-20 | 2019-03-19 | McCarthy HITT - Next NGA West JV | W912DQ-17-R-7000 | 315507977 | 323850426 | 2023-10-19 | 2024-01-02
2020-12-09 | 2010 | National Security Agency | 17781 |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700000 | 11700000 | 2011-08-20 | 2012-05-30
2020-12-09 | 2010 | National Security Agency | 17782 |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200000 | 3200000 | 2013-07-13 | 2015-11-30
2020-12-09 | 2011 | National Security Agency | 17866 |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900000 | 131089216 | 2014-11-30 | 2015-10-31
2020-12-09 | 2010 | National Security Agency | 17872 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223000 | 129078000 | 2014-04-18 | 2015-10-12
2020-12-09 | 2010 | National Security Agency | 18052 |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566000 | 8257000 | 2013-02-01 | 2014-05-14
2020-12-09 | 2010 | National Security Agency | 18053 |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095000 | 16448000 | 2013-02-01 | 2014-05-31
2020-12-09 | 2010 | National Security Agency | 18054 |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085000 | 7316000 | 2013-02-01 | 2014-08-31
2020-12-09 | 2011 | National Security Agency | 20489 |  | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620000 | 2657000 | 2014-02-28 | 2014-04-28
2016-11-30 | 2011 | National Security Agency | 20489 | 2 | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620000 | 2657000 | 2014-02-28 | 2014-04-28
2020-12-09 | 2009 | National Security Agency | 21120 |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060000 | 13760000 | 2013-01-17 | 2014-04-18
2020-12-09 | 2010 | National Security Agency | 21372 |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443000 | 4201000 | 2011-09-26 | 2012-06-29
2020-12-09 | 2012 | National Security Agency | 23051 |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975000 | 132008057 | 2015-05-03 | 2015-07-28
2020-12-09 | 2012 | National Security Agency | 23051 | 2 | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621000 | 5621000 | 2014-02-14 | 2015-09-30
2020-12-09 | 2011 | National Security Agency | 23994 |  | 2012-04-26 | 2012-06-18 | JAAAT | W912HN-10-D-0063 | 15315000 | 16526000 | 2014-01-30 | 2014-12-23
2020-12-09 | 2012 | National Security Agency | 24649 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589000 | 608357051 | 2015-09-15 | 2016-02-08
2020-12-09 | 2010 | National Security Agency | 25047 |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253000 | 5792000 | 2014-03-07 | 2015-05-04
2020-12-09 | 2013 | National Security Agency | 26170 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 123058382 | 158058212 | 2015-10-11 | 2020-12-31
2020-12-09 | 2015 | National Security Agency | 27532 |  | 2015-04-15 | 2016-04-05 | Hensel-Phelps | W912DR-15-D-0032 | 40081050 | 45544834 | 2018-10-25 | 2019-04-03
2021-03-31 | 2018 | National Security Agency | 30439 |  | 2018-07-19 | 2018-09-30 | Alutiiq Construction Services, LLC | W9128A-18-C-0016 | 4800000 | 4800000 | 2020-03-01 | 2021-03-25
2020-12-09 | 2018 | National Security Agency | 30439
2021-03-31 | 2016 | National Security Agency | 30583 |  | 2015-09-30 | 2016-06-17 | Clark Construction | W912DR-16-C-0013 | 616311000 | 705331074 | 2020-09-10 | 2022-02-01
2016-11-30 | 2016 | National Security Agency | 30583 |  | 2015-12-18 | 2016-06-17 | Clark Construction | W912DR-15-R-0024 | 616311000 | 636971000 | 2020-09-09 | 2020-09-09
2020-12-09 | 2016 | National Security Agency | 31066 |  | 2015-04-15 | 2016-06-06 | Hensel-Phelps | W912DR-15-D-0032 DO 0002 | 30538350 | 33305344 | 2018-08-08 | 2018-12-18
2020-12-09 | 2017 | National Security Agency | 31067 |  | 2015-04-15 | 2018-01-18 | Hensel-Phelps | W912DR-15-D-0032 DO 0003 | 13900000 | 14104547 | 2019-01-29 | 2019-05-22
2020-12-09 | 2016 | National Security Agency | 31934 |  | 2015-07-08 | 2015-09-15 | Whiting-Turner | W912DR-15-C-0026 | 24554985 | 26455691 | 2016-12-31 | 2017-02-28
2021-03-31 | 2019 | National Security Agency | 32100 |  | 2019-03-18 | 2020-01-30 | Hensel-Phelps | W912DR-20-C-0004 | 34227105 | 34367966 | 2022-11-17 | 2022-11-17
2020-12-31 | 2016 | National Security Agency | 32122 |  | 2016-04-01 | 2016-05-23 | Argo | WH12DR-14-D-0019 | 22375000 | 31400000 | 2018-06-08 | 2021-01-06
2020-12-09 | 2018 | National Security Agency | 34490
2021-03-31 | 2019 | National Security Agency | 35168 |  | 2018-10-04 | 2019-03-28 | Hensel-Phelps | W912DR-19-C-0013 | 650261000 | 448955735 | 2023-04-30 | 2023-05-09
2021-05-11 | 2016 | Navy Active | M006811220 |  | 2016-06-24 | 2016-11-30 | J. R. FILANC CONSTRUCTION COMPANY,INC | N6247317C3403 AWD | 39860000 | 43244000 | 2019-03-30 | 2019-03-30
2021-05-11 | 2016 | Navy Active | M62613603 |  | 2016-03-01 | 2018-12-18 | Awarded by Other Agency | N40084USACE02 AWD | 8904000 | 8904000 | 2020-07-08 | 2021-03-12
2021-05-11 | 2014 | Navy Active | N00128714 |  | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N4008518C8707 AWD | 32940000 | 31523000 | 2020-08-14 | 2020-10-23
2021-05-11 | 2017 | Navy Active | N00128714 | N00128714A | 2018-05-07 | 2018-07-30 | CLARK BLINDERMAN, JOINT VENTURE | N4008518C8707 AWD | 37695000 | 35655000 | 2020-08-14 | 2020-10-23
2021-05-11 | 2020 | Navy Active | N00129898 |  | 2020-04-07 | 2020-09-29 | WEEKS MARINE, INC | N4008520C0074 AWD | 2468000 | 75716000 | 2022-10-26 | 2022-10-26
2020-11-16 | 2020 | Navy Active | N00129898
2021-05-11 | 2016 | Navy Active | N00204723 |  | 2016-11-23 | 2017-06-28 | EMR, INC. | N6945017D0507 N6945017F1003 | 20056000 | 19270000 | 2019-10-16 | 2020-09-20
2021-05-11 | 2019 | Navy Active | N00207674 |  | 2019-02-08 | 2019-05-17 | DESBUILD INCORPORATEDDBA DES BUILD | N6945016D1111 N6945019F0712 | 3036000 | 3060000 | 2020-10-13 | 2020-11-13
2021-05-11 | 2019 | Navy Active | N00207711 |  | 2019-07-18 | 2019-09-13 | UP-SIDE MANAGEMENT COMPANY | N6945019C5648 AWD | 2323000 | 2213000 | 2020-09-14 | 2020-09-14
2021-05-11 | 2014 | Navy Active | N00213678 |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151000 | 14261000 | 2018-01-08 | 2018-01-08
2021-05-11 | 2019 | Navy Active | N00213720 |  | 2019-04-17 | 2019-09-26 | THE HASKELL COMPANY | N6945019D0909 N6945019F0874 | 30995000 | 29502000 | 2021-12-13 | 2022-01-07
2021-05-11 | 2018 | Navy Active | N00213731 |  | 2019-06-25 | 2019-09-19 | BURNS & MCDONNELL ENGINEERINGCOMPANY, INC. | N6945016D0100 N6945019F0105 | 9097000 | 8732000 | 2020-11-30 | 2020-09-30
2021-05-11 | 2018 | Navy Active | N00213741 |  | 2019-05-15 | 2019-09-27 | KORTE CONSTRUCTION COMPANY | N6945019C0903 AWD | 63582000 | 61419000 | 2022-01-17 | 2022-08-25
2021-05-11 | 2018 | Navy Active | N00216450 |  | 2018-05-25 | 2018-09-05 | URS GROUP, INC. | N6247013D6022 N6247018F4121 | 50430000 | 49641000 | 2021-09-04 | 2022-07-08
2021-05-11 | 2018 | Navy Active | N00216485 |  | 2018-06-28 | 2018-08-22 | GFP GROUP, L.L.C. | N6945016D0615 N6945018F2384 | 4213000 | 4567000 | 2020-03-14 | 2021-01-30
2021-05-11 | 2019 | Navy Active | N002450888 |  | 2019-01-02 | 2019-03-28 | HELIX ELECTRIC, INC. | N6247316D3201 0010 | 36336000 | 47302000 | 2021-08-18 | 2022-07-07
2021-05-11 | 2019 | Navy Active | N00245110 |  | 2019-04-19 | 2019-08-12 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247319F5055 | 14817000 | 13881000 | 2021-03-23 | 2021-03-23
2021-05-11 | 2017 | Navy Active | N00245312 |  | 2017-04-25 | 2017-06-29 | SYNERGY ELECTRIC COMPANY INC | N6247316D1862 N6247317F4054 | 2527000 | 2463000 | 2018-12-15 | 2018-12-15
2021-05-11 | 2019 | Navy Active | N00245440 |  | 2019-05-01 | 2019-06-14 | MANSON CONSTRUCTION CO | N6247319C1208 AWD | 47724000 | 51081000 | 2021-10-27 | 2021-10-31
2021-05-11 | 2021 | Navy Active | N00245443
2021-05-11 | 2015 | Navy Active | N00245800 |  | 2015-06-15 | 2015-09-17 | S & R CONSTRUCTIONA JOINT VENTURE | N6247315C1604 AWD | 41838000 | 45750000 | 2019-04-10 | 2019-04-10
2021-05-11 | 2017 | Navy Active | N002461017 |  | 2017-03-22 | 2017-09-28 | WEST POINT CONTRACTORS, INC. | N6247317C0815 AWD | 2943000 | 2788000 | 2018-12-12 | 2018-12-12
2021-05-11 | 2019 | Navy Active | N002461018 |  | 2019-04-03 | 2019-07-25 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247319C1211 AWD | 53283000 | 61502000 | 2021-05-28 | 2022-07-25
2021-05-11 | 2020 | Navy Active | N002461024 |  | 2019-10-16 | 2020-06-11 | HARPER CONSTRUCTION COMPANY, INC | N6247320C0553 AWD | 69801056 | 73479000 | 2023-01-01 | 2023-01-01
2021-05-11 | 2017 | Navy Active | N00246947 |  | 2017-01-30 | 2017-03-30 | REYES CONSTRUCTION INC | N6247314D0068 0009 | 11659000 | 15038000 | 2018-10-06 | 2020-03-31
2021-05-11 | 2018 | Navy Active | N00246988 |  | 2018-06-06 | 2018-08-30 | RQ CONSTRUCTION, LLC | N6247317D0820 N6247318F5040 | 32923000 | 31617000 | 2021-03-22 | 2021-03-22
2021-05-11 | 2017 | Navy Active | N00246991 |  | 2016-11-23 | 2017-03-30 | RQ-DPR JV | N6247317C0808 AWD | 61541000 | 76100000 | 2019-04-23 | 2021-04-30
2021-05-11 | 2017 | Navy Active | N00620240 |  | 2016-06-14 | 2017-08-09 | BETHEL-WEBCOR JV-1 | N4425517D4032 N4425517F4132 | 28966000 | 29815000 | 2020-03-26 | 2021-01-19
2021-05-11 | 2019 | Navy Active | N00620253 |  | 2018-10-12 | 2019-03-11 | BETHEL-WEBCOR JV-1 | N4425517D4032 XN4425519F4123 | 12949000 | 13756000 | 2020-11-28 | 2021-01-31
2021-05-11 | 2017 | Navy Active | N00620256 |  | 2018-04-05 | 2019-01-30 | RQ CONSTRUCTION, LLC | N4425519C0003 AWD | 45981000 | 45728000 | 2021-07-19 | 2021-07-19
2021-05-11 | 2019 | Navy Active | N00620258 |  | 2018-11-14 | 2019-02-26 | TOMPCO, INC | N4425517D4014 N4425519F4091 | 7114000 | 7064000 | 2021-03-08 | 2021-01-29
2021-05-11 | 2019 | Navy Active | N32414106 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N4008519C9057 AWD | 66625000 | 66095000 | 2022-02-13 | 2022-07-15
2021-05-11 | 2019 | Navy Active | N324141098 |  | 2019-03-21 | 2019-06-12 | WHITING-TURNER CONTRACTING CO | N4008519C9057 AWD | 3142000 | 3103000 | 2022-02-13 | 2022-07-15
2021-05-11 | 2015 | Navy Active | N32414547 |  | 2014-08-21 | 2015-05-18 | WHITING-TURNER CONTRACTING CO | N4008515C8739 AWD | 34317000 | 57913000 | 2016-11-23 | 2021-11-19
2021-05-11 | 2018 | Navy Active | N32443257 |  | 2017-11-03 | 2018-09-17 | RQ CONSTRUCTION, LLC | N4008518C1107 AWD | 73055000 | 69909000 | 2021-06-18 | 2021-08-17
2021-05-11 | 2016 | Navy Active | N32443614 |  | 2017-06-01 | 2017-12-15 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 45614000 | 43978000 | 2021-04-15 | 2021-06-30
2021-05-11 | 2017 | Navy Active | N32443614 | N32443614A | 2017-06-01 | 2017-12-14 | MEB GENERAL CONTRACTORS, INC. | N4008518C1116 AWD | 2624000 | 2584000 | 2021-04-15 | 2021-06-30
2021-05-11 | 2020 | Navy Active | N32443653 |  | 2020-04-16 | 2020-09-04 | MEB GENERAL CONTRACTORS, INC. | N4008520C0063 AWD | 46986935 | 49477000 | 2023-06-17 | 2023-06-17
2021-05-11 | 2019 | Navy Active | N324461074 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N4008520C8500 AWD | 43523000 | 43016000 | 2021-01-27 | 2022-03-20
2021-05-11 | 2019 | Navy Active | N324461088 |  | 2019-05-23 | 2019-08-05 | TANTARA ASSOCIATES CORPORATION | N4008517D5049 N4008519F6032 | 3458000 | 3381000 | 2020-10-31 | 2021-06-30
2021-05-11 | 2017 | Navy Active | N32446285 |  | 2017-01-17 | 2017-06-29 | L.S. BLACK CONSTRUCTORS-LOEFFELCONSTRUCTION | N4008517C5056 AWD | 18927000 | 19727000 | 2019-05-10 | 2021-01-21
2021-05-11 | 2018 | Navy Active | N32446293 |  | 2018-08-31 | 2019-09-25 | METHUEN CONSTRUCTION CO., INC | N4008519C9261 AWD | 62457000 | 59903000 | 2022-08-09 | 2022-08-09
2021-05-11 | 2014 | Navy Active | N32446308 |  | 2015-09-29 | 2016-04-21 | TRITON MARINE CONSTRUCTION CORP. | N4008516C3013 AWD | 34722000 | 34943000 | 2018-10-25 | 2018-10-25
2021-05-11 | 2019 | Navy Active | N32446310 |  | 2019-02-19 | 2019-11-21 | CIANBRO CORPORATION | N4008520C8500 AWD | 177914000 | 132967000 | 2021-01-27 | 2022-03-20
2021-05-11 | 2017 | Navy Active | N32446371 |  | 2017-09-19 | 2018-03-30 | ENGINEERED CONSTRUCTION SERVICES,INC | N4008518C8719 AWD | 30414000 | 30758000 | 2021-09-14 | 2021-09-14
2021-05-11 | 2018 | Navy Active | N32446385 |  | 2018-07-05 | 2018-09-20 | STRUCTURAL ASSOCIATES, INC | N4008517D5048 N4008518F6907 | 975000 | 819000 | 2019-10-08 | 2019-10-08
2021-05-11 | 2017 | Navy Active | N3379A223 |  | 2017-10-13 | 2018-06-28 | J/V P. & C. DEVELOPMENT S.A. -ERGOTEM S.A. | N6247018C4015 AWD | 25219000 | 22891000 | 2020-10-05 | 2021-07-23
2021-05-11 | 2018 | Navy Active | N3379A505 |  | 2018-06-12 | 2018-10-26 | ECC MEZZ LLC | N6247019D5002 N6247019F9001 | 11315000 | 11623000 | 2020-06-18 | 2021-01-05
2021-05-11 | 2021 | Navy Active | N360423271 |  | 2020-10-30 | 2021-03-25 | SYNERGY ELECTRIC COMPANY INC | N6247319D2430 N6247321F4370 | 1000 | 1110000 | 2023-05-03 | 2023-05-03
2021-05-11 | 2015 | Navy Active | N41557230 |  | 2015-04-02 | 2015-11-17 | RELYANT GLOBAL LLC | N6274216C1317 AWD | 20799000 | 16473000 | 2019-01-29 | 2019-01-29
2021-05-11 | 2018 | Navy Active | N41557250 |  | 2018-01-24 | 2018-09-24 | BLACK CONSTRUCTION CORP. | N6274218C1300 AWD | 43203000 | 41154000 | 2021-01-21 | 2021-07-27
2021-05-11 | 2018 | Navy Active | N41557260 |  | 2018-01-24 | 2018-09-21 | BLACK CONSTRUCTION CORP. | N6274218C1300 AWD | 53554000 | 50148000 | 2020-12-28 | 2021-07-27
2021-05-11 | 2016 | Navy Active | N41557635 |  | 2016-06-24 | 2017-08-01 | TIKIGAQ CONSTRUCTION, LLC | N4019217C1305 AWD | 8715000 | 11155000 | 2019-02-22 | 2021-07-29
2021-05-11 | 2017 | Navy Active | N41557H279 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 78787000 | 74869000 | 2022-07-05 | 2022-07-05
2021-05-11 | 2018 | Navy Active | N41557H280 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 40850000 | 38574000 | 2022-07-05 | 2022-07-05
2021-05-11 | 2019 | Navy Active | N41557H282 |  | 2019-03-28 | 2019-09-19 | BLACK CONSTRUCTION CORP. | N6274219C1309 AWD | 83378000 | 78910000 | 2022-07-05 | 2022-07-05
2021-05-11 | 2015 | Navy Active | N42237099 |  | 2014-02-24 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 39730000 | 41728000 | 2018-06-20 | 2019-03-27
2021-05-11 | 2017 | Navy Active | N42237671 |  | 2017-08-10 | 2018-01-16 | DESIGN BUILD INCORPORATED | N6945016D1111 | 2979000 | 2988000 | 2019-08-23 | 2019-11-22
2021-05-11 | 2017 | Navy Active | N47608265 |  | 2018-04-10 | 2019-01-30 | B.L. HARBERT INTERNATIONAL, L.L.C. | N4008019C2015 AWD | 46919000 | 50847000 | 2020-09-28 | 2021-06-21
2021-05-11 | 2017 | Navy Active | N47608421 |  | 2017-08-03 | 2017-09-27 | REILLY CONSTRUCTION, INC | N4008017D0012 N4008017F4480 | 2627000 | 2553000 | 2018-10-24 | 2020-06-16
2021-05-11 | 2016 | Navy Active | N47608975 |  | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N4008018C0311 AWD | 38795000 | 38693000 | 2020-02-02 | 2020-07-23
2021-05-11 | 2017 | Navy Active | N47608975 | N47608975A | 2016-10-31 | 2018-04-13 | HARKINS BUILDERS INC. | N4008018C0311 AWD | 2145000 | 2043000 | 2020-02-02 | 2020-12-29
2021-05-11 | 2020 | Navy Active | N476091900 |  | 2020-05-08 | 2020-09-10 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247320F5226 | 437309406 | 476478000 | 2023-11-30 | 2023-11-30
2021-05-11 | 2020 | Navy Active | N476091901
2021-05-11 | 2020 | Navy Active | N476091902
2021-01-08 | 2020 | Navy Active | N476091903
2021-05-11 | 2020 | Navy Active | N476091903 |  | 2020-05-22 | 2020-09-17 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247320F5462 | 111944000 | 108209000 | 2022-11-04 | 2022-11-04
2021-05-11 | 2020 | Navy Active | N476091907
2021-05-11 | 2020 | Navy Active | N476091908
2021-05-11 | 2020 | Navy Active | N476091914
2021-05-11 | 2020 | Navy Active | N476091916 |  | 2020-05-15 | 2020-09-03 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247320F5296 | 53426000 | 52493000 | 2022-09-19 | 2022-09-19
2020-11-16 | 2020 | Navy Active | N476091916
2021-05-11 | 2020 | Navy Active | N476091918 |  | 2020-11-23 | 2021-03-03 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247321F4428 | 50924000 | 51076000 | 2023-05-03 | 2023-05-03
2021-02-09 | 2020 | Navy Active | N476091924
2021-05-11 | 2020 | Navy Active | N476091924 |  | 2020-10-16 | 2021-01-22 | BARNHART-REESE CONSTRUCTION INC | N6247317D4635 N6247321F4264 | 1660000 | 581000 | 2023-02-06 | 2023-02-06
2021-05-11 | 2020 | Navy Active | N47609810 |  | 2020-04-15 | 2020-06-26 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247319D2438 N6247320F4817 | 53866451 | 56762000 | 2022-04-10 | 2022-04-10
2021-05-11 | 2018 | Navy Active | N50092176 |  | 2017-09-14 | 2018-04-19 | CIVIL WORKS CONTRACTING LLC | N4008517D0358 N4008518F5423 | 2670000 | 2602000 | 2019-08-05 | 2019-08-05
2021-05-11 | 2019 | Navy Active | N60042117
2021-05-11 | 2020 | Navy Active | N601911026 |  | 2020-07-23 | 2020-12-11 | TAZEWELL-BGI JV, LLC | N4008518D1144 N4008521F4343 | 4218000 | 4218000 | 2022-06-10 | 2022-06-10
2021-05-11 | 2018 | Navy Active | N60191160 |  | 2019-08-28 | 2020-02-14 | SYNCON, LLC | N4008520C8503 AWD | 25795000 | 24567000 | 2022-03-01 | 2022-07-04
2021-05-11 | 2014 | Navy Active | N60191815 |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446000 | 18135000 | 2016-10-25 | 2019-03-21
2021-05-11 | 2017 | Navy Active | N60201154 |  | 2017-02-23 | 2017-06-29 | HENSEL PHELPS CONSTRUCTION CO | N6945014D1269 N6945017F0700 | 40518000 | 40485000 | 2019-09-26 | 2019-12-27
2021-05-11 | 2019 | Navy Active | N60201195 |  | 2019-06-18 | 2019-08-16 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N6945016D1112 N6945019F0716 | 3600000 | 3709000 | 2020-08-29 | 2021-03-31
2021-05-11 | 2018 | Navy Active | N60201421 |  | 2017-10-16 | 2018-08-03 | DESBUILD INCORPORATEDDBA DES BUILD | N6945016D1111 N6945018F0723 | 11062000 | 11655000 | 2020-08-04 | 2022-06-25
2021-05-11 | 2016 | Navy Active | N60201424 |  | 2016-01-26 | 2016-07-14 | ARTEC GROUP (THE) INC | N6945016D1110 0001 | 14616000 | 15881000 | 2019-02-05 | 2019-02-05
2021-05-11 | 2019 | Navy Active | N60201426 |  | 2019-05-31 | 2019-09-13 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014D1267 N6945019F0708 | 76123000 | 73092000 | 2021-04-02 | 2021-10-07
2021-05-11 | 2019 | Navy Active | N60201427 |  | 2018-07-30 | 2019-02-22 | Archer Western Federal JV | N6945019F0855 | 27496000 | 26620000 | 2021-02-05 | 2021-06-04
2021-05-11 | 2016 | Navy Active | N60495111 |  | 2016-05-31 | 2017-08-17 | BRISTOL GENERAL CONTRACTORS, LLC | N6247315D2404 N6247317F4334 | 11253000 | 10653000 | 2019-02-25 | 2020-07-18
2021-05-11 | 2014 | Navy Active | N60495393 |  | 2017-02-28 | 2018-04-19 | WALTERS, K. G. CONSTRUCTION CO., IN | N6247318C2205 AWD | 15675000 | 15520000 | 2020-05-08 | 2020-11-30
2021-05-11 | 2015 | Navy Active | N60495420 |  | 2015-07-17 | 2015-09-16 | STRAUB CONSTRUCTION, INC. | N6247315D2427 0002 | 25541000 | 28442000 | 2017-11-24 | 2019-10-31
2021-05-11 | 2018 | Navy Active | N60495426 |  | 2018-11-07 | 2018-12-28 | J I GARCIA CONSTRUCTION INC | N6247318D5817 N6247319F4162 | 3295000 | 3234000 | 2019-10-25 | 2019-10-25
2021-05-11 | 2017 | Navy Active | N60495440 |  | 2017-07-20 | 2018-08-06 | STRAUB CONSTRUCTION, INC. | N6247316D1887 N6247318F4874 | 18936000 | 19002000 | 2020-08-25 | 2020-10-17
2021-05-11 | 2019 | Navy Active | N60508288 |  | 2019-07-26 | 2020-01-10 | EMR, INC. | N6945018D1318 N6945020F0875 | 2466000 | 4479000 | 2021-01-11 | 2022-03-30
2021-05-11 | 2019 | Navy Active | N60514160 |  | 2018-12-10 | 2019-09-19 | RQ CONSTRUCTION, LLC | N6945019C0501 AWD | 66357000 | 62544000 | 2022-03-18 | 2022-03-18
2021-05-11 | 2019 | Navy Active | N60514343 |  | 2019-06-04 | 2019-09-20 | ISLANDS MECHANICAL CONTRACTOR | N6945018D1313 N6945019F1007 | 12440000 | 11911000 | 2021-09-20 | 2022-01-01
2021-05-11 | 2014 | Navy Active | N61054011 |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458000 | 8792000 | 2017-01-17 | 2017-01-17
2021-05-11 | 2021 | Navy Active | N610542101 |  | 2020-10-23 | 2021-03-05 | NIPPO CORPORATION | N4008419D0075 N4008421F4145 | 1382000 | 2107000 | 2024-05-01 | 2024-05-01
2021-05-11 | 2019 | Navy Active | N61056512
2021-05-11 | 2017 | Navy Active | N61064402 |  | 2018-04-20 | 2018-12-26 | NOVA GROUP INC | N6274219C1320 AWD | 25137000 | 24178000 | 2021-07-13 | 2021-07-13
2021-05-11 | 2016 | Navy Active | N61064416 |  | 2018-04-19 | 2018-09-06 | HELIX ELECTRIC, INC. | N6247818C1516 AWD | 23932000 | 25756000 | 2020-05-28 | 2022-02-07
2021-05-11 | 2014 | Navy Active | N61065202 |  | 2014-12-11 | 2016-08-29 | VANDER WERFF, PETER CONSTRUCTION | N6247314D0039 0011 | 15972000 | 14713000 | 2018-06-10 | 2019-12-11
2021-05-11 | 2019 | Navy Active | N61065224 |  | 2018-12-10 | 2019-07-15 | MANSON/CONNOLLY SEAL BEACH JV | N6247319C2450 AWD | 111089000 | 109706000 | 2022-06-30 | 2024-06-18
2021-05-11 | 2019 | Navy Active | N61065241 |  | 2019-06-17 | 2019-08-19 | REYES CONSTRUCTION INC | N6247318D5862 N6247319F4995 | 23001000 | 22095000 | 2021-04-15 | 2021-08-30
2021-05-11 | 2018 | Navy Active | N61066604
2021-05-11 | 2018 | Navy Active | N61151163 |  | 2018-02-12 | 2018-09-29 | JOHN C. GRIMBERG CO., INC. | N4008018C0008 AWD | 37296000 | 35786000 | 2021-08-14 | 2021-08-14
2021-05-11 | 2015 | Navy Active | N61151190 |  | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 15316000 | 14741000 | 2019-09-06 | 2023-04-09
2021-05-11 | 2017 | Navy Active | N61151190 | N61151190A | 2015-06-17 | 2017-04-27 | JOHN C. GRIMBERG CO., INC. | N4008017C0030 AWD | 6546000 | 4583000 | 2020-01-13 | 2023-04-09
2021-05-11 | 2015 | Navy Active | N61151287 |  | 2015-03-04 | 2015-09-02 | M A MORTENSON COMPANY | N4008015C0167 AWD | 25679000 | 29157000 | 2017-07-17 | 2019-10-31
2021-05-11 | 2015 | Navy Active | N61152621 |  | 2015-07-15 | 2016-03-31 | TURNER CONSTRUCTION COMPANY | N4008016C0156 AWD | 120181000 | 140102000 | 2019-09-08 | 2020-05-22
2021-05-11 | 2020 | Navy Active | N61755491 |  | 2020-03-02 | 2020-08-07 | BLACK CONSTRUCTION-TUTOR PERINI JV | N6274219D1328 N6274220F9924 | 50514009 | 53553000 | 2022-12-20 | 2022-12-20
2021-05-11 | 2016 | Navy Active | N61755535 |  | 2016-11-10 | 2017-08-21 | CONTRACK WATTS, INC | N6274217C1325 AWD | 47314000 | 44985000 | 2020-01-03 | 2020-01-03
2021-05-11 | 2019 | Navy Active | N61755640 |  | 2019-02-20 | 2019-06-25 | GILBANE FEDERAL | N6274219C1310 AWD | 36419000 | 36132000 | 2022-10-07 | 2022-12-24
2021-05-11 | 2017 | Navy Active | N61755652 |  | 2017-06-12 | 2018-05-23 | APTIM FEDERAL SERVICES, LLC | N6274218C1318 AWD | 28975000 | 27803000 | 2020-04-03 | 2020-06-10
2021-05-11 | 2018 | Navy Active | N61755680 |  | 2018-08-03 | 2018-09-28 | RELIABLE BUILDERS, INC. | N4019216D2704 N4019218F4410 | 2804000 | 2385000 | 2019-09-27 | 2021-05-26
2021-05-11 | 2017 | Navy Active | N62588307 |  | 2018-04-03 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N6247019C5009 AWD | 10833000 | 10744000 | 2021-02-09 | 2021-02-09
2021-05-11 | 2017 | Navy Active | N62588308 |  | 2018-08-09 | 2018-12-20 | RIZZANI DE ECCHER (USA) INC. | N6247019C5009 AWD | 4894000 | 4718000 | 2021-02-09 | 2021-02-09
2021-05-11 | 2019 | Navy Active | N62588312
2021-05-11 | 2019 | Navy Active | N62604855 |  | 2019-02-22 | 2019-05-15 | EMR, INC. | N6945017D0507 N6945019F0710 | 21022000 | 21246000 | 2022-06-30 | 2022-05-13
2021-05-11 | 2018 | Navy Active | N62688495 |  | 2017-07-10 | 2018-09-28 | WHITING-TURNER CONTRACTING CO | N4008518C1148 AWD | 35158000 | 33613000 | 2021-02-04 | 2022-01-05
2021-05-11 | 2016 | Navy Active | N62688610 |  | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N4008517C0307 AWD | 34675000 | 37904000 | 2019-10-25 | 2020-12-30
2021-05-11 | 2017 | Navy Active | N62688610 | N62688610A | 2016-11-21 | 2017-08-31 | RQ-BLACKWATER JV | N4008517C0307 AWD | 12166000 | 12166000 | 2019-10-25 | 2020-12-30
2021-05-11 | 2018 | Navy Active | N62688762 |  | 2018-01-25 | 2018-05-02 | TAZEWELL HOMELAND JV, LLC | N4008518R1123 | 2573000 | 2905000 | 2019-07-02 | 2021-01-03
2021-05-11 | 2016 | Navy Active | N62688913 |  | 2017-03-23 | 2018-04-23 | WHITING-TURNER CONTRACTING CO | N4008518C1134 AWD | 114000000 | 109887000 | 2020-11-01 | 2021-05-09
2021-05-11 | 2018 | Navy Active | N62813013 |  | 2018-12-14 | 2019-07-26 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274219C1317 AWD | 59383000 | 62509000 | 2021-04-26 | 2021-09-25
2021-05-11 | 2020 | Navy Active | N62813033 |  | 2020-04-22 | 2020-08-10 | HDR ENGINEERING, INC.DBA HONOLULU HDR HAWAII PACIFIC | N6247820C4016 AWD | 50430000 | 33645000 | 2022-09-09 | 2022-09-09
2020-11-16 | 2020 | Navy Active | N62813033
2021-05-11 | 2016 | Navy Active | N62813036 |  | 2015-10-28 | 2016-01-26 | BETHEL-WEBCOR JV-1 | N6247814D4001 KB01 | 8520000 | 9184000 | 2018-03-26 | 2021-02-06
2021-05-11 | 2021 | Navy Active | N62813044 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N6247820D4015 N6247821F4087 | 2072000 | 2072000 | 2023-11-12 | 2023-11-12
2021-05-11 | 2014 | Navy Active | N62813058 |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810000 | 2679000 | 2016-05-18 | 2019-12-31
2021-05-11 | 2021 | Navy Active | N628131006 |  | 2020-11-02 | 2021-04-30 | TNT CONSTRUCTORS | N6247820D4015 N6247821F4087 | 2072000 | 2072000 | 2023-11-12 | 2023-11-12
2021-05-11 | 2019 | Navy Active | N62813169 |  | 2018-10-15 | 2019-03-29 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N62742-19-C-1319 | 64705000 | 69996000 | 2022-01-24 | 2022-08-03
2021-05-11 | 2014 | Navy Active | N62813320 |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970000 | 36741000 | 2017-08-03 | 2020-10-06
2021-05-11 | 2018 | Navy Active | N62813704 |  | 2018-09-21 | 2019-03-12 | KIEWIT INFRASTRUCTURE WEST CO. | N62478-19-C-1515 | 73199000 | 70966000 | 2021-06-19 | 2021-06-23
2021-05-11 | 2020 | Navy Active | N62863605 |  | 2020-09-03 | 2021-04-12 | UTE CASTELLANO COBRA MACC | N3319119D0801 N3319121F4133 | 7127000 | 8934000 | 2023-01-17 | 2023-01-17
2021-05-11 | 2017 | Navy Active | N62863621 |  | 2017-03-07 | 2017-08-31 | CONSTRUCCIONES FELIPE CASTELLANOCOBRA INSTALACIONES Y SERVICIOS | N6247017C5006 AWD | 21868000 | 21710000 | 2023-06-09 | 2023-07-07
2021-05-11 | 2015 | Navy Active | N62863712 |  | 2015-04-11 | 2015-11-20 | COBRA INSTALCIONES Y SERVICIOS SA | N6247016C6001 AWD | 19252000 | 22349000 | 2018-05-23 | 2022-02-24
2021-05-11 | 2019 | Navy Active | N62863812 |  | 2020-05-14 | 2020-09-23 | CONSTRUCTORA SAN JOSE SA | N6247020C0009 AWD | 137000 | 5161000 | 2022-06-30 | 2022-06-30
2021-05-11 | 2020 | Navy Active | N62995130 |  | 2020-07-06 | 2020-09-29 | WOLFF & MULLER GOVERNMENT SERVICES | N6247020C0013 AWD | 39712368 | 45568000 | 2025-06-05 | 2025-06-05
2021-05-11 | 2016 | Navy Active | N62995407 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 23632000 | 22590000 | 2019-04-23 | 2021-02-26
2021-05-11 | 2016 | Navy Active | N62995655 |  | 2016-02-25 | 2016-11-22 | ICM SPA | N6247017C5005 AWD | 28340000 | 50432000 | 2019-04-23 | 2021-02-26
2021-05-11 | 2017 | Navy Active | N62995737 |  | 2016-09-09 | 2017-02-28 | ENVIRONMENTAL CHEMICAL CORPORATION | N3319116D1010 JN01 | 6096000 | 12405000 | 2018-08-22 | 2021-01-21
2021-05-11 | 2019 | Navy Active | N63005955U
2021-05-11 | 2016 | Navy Active | N63005976
2021-05-11 | 2017 | Navy Active | N63005985 |  | 2018-02-13 | 2019-06-14 | JUDE & L CONSTRUCTION, LLC | N3319119C0805 AWD | 3407000 | 3268000 | 2021-03-25 | 2021-03-25
2021-05-11 | 2016 | Navy Active | N63042218 |  | 2015-12-10 | 2016-05-10 | A&D GC INC | N6247315D2403 0003 | 7386000 | 7531000 | 2017-11-16 | 2020-03-13
2021-05-11 | 2018 | Navy Active | N63042282 |  | 2018-01-23 | 2018-09-19 | R A BURCH CONSTRUCTION CO INC | N6247318C2201 AWD | 52594000 | 49438000 | 2021-02-24 | 2021-09-03
2021-05-11 | 2019 | Navy Active | N63042284 |  | 2018-11-09 | 2019-09-16 | HARPER CONSTRUCTION COMPANY, INC | N6247319C2455 AWD | 107641000 | 102651000 | 2021-11-17 | 2021-12-03
2021-05-11 | 2019 | Navy Active | N63042392 |  | 2019-05-09 | 2019-07-30 | POWER PRO PLUS INC. | N6247319D2428 N6247319F4769 | 13545000 | 13522000 | 2021-05-06 | 2021-05-06
2021-05-11 | 2018 | Navy Active | N66691911 |  | 2018-06-18 | 2018-12-12 | AKTOR S.A. - TSONTOS S.A. J/V | N6247019C5006 AWD | 10141000 | 3408000 | 2021-02-14 | 2021-02-14
2021-05-11 | 2017 | Navy Active | N68436400 |  | 2017-08-10 | 2018-09-29 | CUSTOM MECHANICAL SYSTEMS CORP(CMS) | N4425517D4034 N4425518F4438 | 38496000 | 39875000 | 2021-06-30 | 2022-03-12
2021-05-11 | 2016 | Navy Active | N68436401 |  | 2016-03-29 | 2017-09-26 | TOMPCO, INC | N4425517C8002 AWD | 17270000 | 17336000 | 2020-01-04 | 2021-03-23
2021-05-11 | 2016 | Navy Active | N68436431 |  | 2016-03-31 | 2016-08-11 | NOVA GROUP INC | N4425516C7002 AWD | 19943000 | 22696000 | 2017-11-14 | 2021-08-06
2021-05-11 | 2017 | Navy Active | N68436438 |  | 2017-01-20 | 2018-04-23 | VET INDUSTRIAL INC | N4425517D4007 N4425518F4134 | 10040000 | 10498000 | 2019-10-30 | 2020-08-14
2020-11-16 | 2020 | Navy Active | N68436447
2021-05-11 | 2020 | Navy Active | N68436447 |  | 2020-01-10 | 2020-06-08 | N4425520C1002 AWD | N4425520C1002 AWD | 1876000 | 50386000 | 2023-08-02 | 2023-08-02
2021-05-11 | 2017 | Navy Active | N68436834 |  | 2019-03-18 | 2020-02-03 | MANSON CONSTRUCTION CO | N4425520C2002 AWD | 73000000 | 101029000 | 2022-07-04 | 2022-07-04
2021-05-11 | 2016 | Navy Active | N68436983 |  | 2016-04-15 | 2016-09-21 | NOVA GROUP INC | N4425516C7005 AWD | 31744000 | 35219000 | 2018-02-13 | 2019-04-21
2021-05-11 | 2015 | Navy Active | N68436990 | N68436990C | 2010-07-07 | 2015-01-08 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00004 | 80735000 | 82565000 | 2017-09-30 | 2017-09-30
2021-05-11 | 2015 | Navy Active | N68436993 |  | 2015-09-30 | 2016-08-30 | WATTS-ORION JV | N4425516C7004 AWD | 32047000 | 32211000 | 2019-08-07 | 2019-08-07
2021-05-11 | 2019 | Navy Active | N68469001 |  | 2019-06-07 | 2019-09-16 | ENVIRONMENTAL CHEMICAL CORPORATION | N6247019D8025 N6247019F9101 | 40000000 | 102008000 | 2024-09-15 | 2024-09-15
2021-05-11 | 2015 | Navy Active | N68469275 |  | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 31151000 | 44659000 | 2019-11-15 | 2022-01-20
2021-05-11 | 2018 | Navy Active | N68469275 | N68469275A | 2015-10-29 | 2017-11-02 | MANHATTAN CONSTRUCTION COMPANY | N4008018C0005 AWD | 39776000 | 37882000 | 2019-11-15 | 2022-01-20
2021-05-11 | 2020 | Navy Active | N69212169 |  | 2020-11-09 | 2021-03-25 | SAUER, INC. | N4008521C0028 AWD | 52191740 | 52191740 | 2023-06-25 | 2023-06-25
2021-05-11 | 2018 | Navy Active | N69212995 |  | 2018-12-19 | 2019-01-31 | AECOM CONSTRUCTION, INC. | N4008519D9066 N4008519F4710 | 31074000 | 29729000 | 2021-06-25 | 2021-11-25
2021-05-11 | 2019 | Navy Active | N69232586 |  | 2019-02-08 | 2019-09-26 | SOLPAC CONSTRUCTION INC | N6247318D5855 N6247319F5449 | 27152000 | 26600000 | 2020-02-15 | 2021-07-01
2021-05-11 | 2019 | Navy Active | N69232777 |  | 2019-05-30 | 2019-08-28 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F5130 | 19686000 | 21032000 | 2021-01-11 | 2021-05-20
2021-05-11 | 2019 | Navy Active | N83447084 |  | 2019-07-31 | 2019-09-17 | UNIFIED SERVICES OF TEXAS | N6945015D1618 N6945019F2598 | 2500000 | 2480000 | 2020-09-20 | 2021-02-25
2021-05-11 | 2017 | Navy Reserve | M68479777 |  | 2017-07-25 | 2020-02-05 | OAK GROUP, INC., THE | N4008517D5038 N4008520F4527 | 17729000 | 25059000 | 2021-08-30 | 2022-04-02
2021-05-11 | 2015 | Navy Reserve | N00129664 |  | 2015-08-24 | 2015-08-25 | VETERANS CONSTRUCTION, LLC | N4008515C9610 AWD | 1989000 | 1973000 | 2017-04-21 | 2017-04-21
2021-05-11 | 2020 | Navy Reserve | N00206475 |  | 2020-01-30 | 2020-08-13 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6945019D0908 N6945020F0891 | 6796000 | 25876000 | 2023-03-06 | 2023-03-06
2021-05-11 | 2019 | Navy Reserve | N00206493
2021-05-11 | 2017 | Navy Reserve | N00206500 |  | 2016-11-04 | 2017-06-29 | SAUER, INC. | N6945017C1613 AWD | 11589000 | 12471000 | 2019-07-27 | 2020-09-03
2021-05-11 | 2018 | Navy Reserve | N42237642 |  | 2018-05-04 | 2018-09-12 | LEEBCOR SERVICES LLC | N6945016D1113 N6945018F0731 | 14240000 | 15537000 | 2020-01-06 | 2021-07-10
2021-05-11 | 2019 | Navy Reserve | N42237643
2021-05-11 | 2019 | Navy Reserve | N61065160 |  | 2018-11-01 | 2019-01-24 | HARPER CONSTRUCTION COMPANY, INC | N6247318D5853 N6247319F4183 | 19180000 | 20136000 | 2021-02-07 | 2021-06-01
2021-05-11 | 2018 | Navy Reserve | N63042366 |  | 2018-06-04 | 2019-04-11 | SOLPAC CONSTRUCTION INC | N6247318D5855 | 16347000 | 16539000 | 2021-03-26 | 2021-06-25
2021-05-11 | 2018 | Navy Reserve | N83447077 |  | 2018-05-14 | 2018-09-26 | EMR, INC. | N6945018D1318 N6945018F0894 | 11343000 | 11156000 | 2019-12-31 | 2020-12-31
2019-09-30 | 2016 | Special Operations Command | 47942 |  | 2015-12-22 | 2016-06-24 | Medvolt LLC | W9128F-16-C-0033 / 38804715 | 9065868 | 9434000 | 2018-05-30 | 2018-10-10
2019-09-30 | 2015 | Special Operations Command | 57442 |  | 2016-03-23 | 2017-03-17 | Brantley Construction Services, LLC | W912HN-17-C-0006 | 8456354 | 8827000 | 2018-10-19 | 2019-02-21
2019-09-30 | 2017 | Special Operations Command | 61065 |  | 2017-03-24 | 2017-07-21 | R.C. Construction Co | W912HN17C0008 | 4609000 | 5099620 | 2018-12-01 | 2019-07-18
2019-09-30 | 2017 | Special Operations Command | 61065 |  | 2017-03-24 | 2017-07-21 | R. C. Construction Co., Inc. | W912HN17C0008 / 46909583 | 4609000 | 5083000 | 2018-12-01 | 2019-08-20
2019-09-30 | 2018 | Special Operations Command | 63850 |  | 2018-04-18 | 2018-08-27 | 4K Global-ACC JV LLC | W912PM18C0015 / 55139238 | 12187000 | 12196000 | 2020-03-25 | 2020-06-03
2019-09-30 | 2019 | Special Operations Command | 66813 |  | 2018-09-17 | 2019-05-23 | Howard W. Pence, Inc | W912QR-15-D-0001 / 60330652 | 5405390 | 5405390 | 2020-12-03 | 2020-12-03
2019-09-30 | 2019 | Special Operations Command | 67039 |  | 2018-11-27 | 2019-05-23 | Howard W. Pence, Inc | W912QR19C0017 / 56979070 | 8825159 | 8825159 | 2020-12-03 | 2020-12-03
2019-09-01 | 2019 | Special Operations Command | 69251 |  | 2018-12-20 | 2019-04-05 | Sauer | W912PM19C0016 / 57218835 | 9776000 | 9776000 | 2020-05-19 | 2020-05-19
2019-09-30 | 2019 | Special Operations Command | 69251 |  | 2018-12-20 | 2019-04-05 | Sauer | W912PM19C0016 | 9776000 | 9776000 | 2020-05-20 | 2020-05-20
2019-09-30 | 2015 | Special Operations Command | 69302 |  | 2015-11-12 | 2017-04-03 | Sauer Incorporated | W91278-12-D-0039 | 36277000 | 39719551 | 2019-05-07 | 2020-02-26
2019-09-30 | 2013 | Special Operations Command | 69445 |  | 2013-02-01 | 2015-05-07 | RQ Construction LLC | W912DW-15-C-0006 | 47917000 | 49466000 | 2017-05-25 | 2018-05-18
2019-09-01 | 2017 | Special Operations Command | 69552 |  | 2017-03-02 | 2019-01-15 | ACC Construction Co, Inc | W912PM19C0008 / 51720250 | 30006388 | 30006000 | 2020-11-08 | 2021-04-07
2019-09-30 | 2017 | Special Operations Command | 69552 |  | 2017-03-02 | 2019-01-15 | ACC Construction Co, Inc | W912PM19C0008 | 30006388 | 30006000 | 2020-11-08 | 2020-11-08
2019-09-30 | 2017 | Special Operations Command | 74813 |  | 2017-11-16 | 2018-06-15 | ACC Construction Co., Inc. | W912PM18C0014 | 17972000 | 20961198 | 2020-03-11 | 2020-08-08
2019-09-01 | 2017 | Special Operations Command | 74813 |  | 2017-11-16 | 2018-07-11 | ACC Construction Co., Inc. | W912PM18C0014 / 66450870 | 2974000 | 2974000 | 2020-01-27 | 2020-01-27
2019-09-30 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2018-11-21 | Medvolt, LLC | W9128F19C0003 / 62566788 | 16908000 | 20459485 | 2020-03-18 | 2020-03-18
2019-09-30 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-10 | Raass Brothers, Inc | W9128F-14-C-0018/43307123 | 8983000 | 6496871 | 2017-04-19 | 2017-09-14
2019-09-30 | 2013 | Special Operations Command | 76367 |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441000 | 33301000 | 2016-07-20 | 2017-08-21
2019-09-01 | 2014 | Special Operations Command | 76375 |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27449000 | 27521000 | 2016-07-23 | 2017-09-11
2019-09-30 | 2014 | Special Operations Command | 76376 |  | 2014-04-09 | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51807000 | 61769562 | 2017-06-27 | 2018-01-19
2019-09-30 | 2016 | Special Operations Command | 76513 |  | 2016-05-25 | 2017-08-02 | Caddell Construction CO. | W912PM17C0004 | 42661500 | 45381840 | 2019-12-18 | 2020-11-12
2019-09-30 | 2017 | Special Operations Command | 76514 |  | 2017-03-02 | 2018-04-05 | RQ Construction, LLC | W912PM18C0011 / 46145884 | 34937000 | 35129832 | 2020-03-23 | 2020-05-19
2019-09-30 | 2015 | Special Operations Command | 79437 |  | 2016-06-27 | 2016-09-28 | SAUER Incorporated, d/b/a Sauer Southeast | W91278-12-D-0039 / 43665546 | 38801000 | 52561471 | 2019-02-11 | 2021-06-18
2019-09-01 | 2014 | Special Operations Command | 79438 |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193631 | 7402000 | 2016-04-19 | 2016-12-16
2019-09-30 | 2016 | Special Operations Command | 79439 |  | 2018-04-06 | 2018-08-14 | Archer Western Contractors, LLC | W912PM18C0016 | 24955000 | 25162875 | 2020-05-07 | 2020-05-26
2019-09-01 | 2014 | Special Operations Command | 79440 |  | 2014-12-15 | 2015-04-30 | ARGO SYSTEMS, LLC | N6945014D1271 0003 | 4140000 | 4140000 | 2016-08-22 | 2018-12-02
2019-09-30 | 2018 | Special Operations Command | 79443 |  | 2018-09-07 | 2018-12-19 | ACC Construction Co, Inc | W912PM19C0007 / 38690394 | 16474525 | 16644341 | 2020-08-19 | 2020-10-18
2019-09-30 | 2019 | Special Operations Command | 79447 |  | 2019-01-09 | 2019-05-03 | A4 Construction Co | W9128F19C0018 | 12309817 | 12309817 | 2021-05-31 | 2021-06-30
2019-09-30 | 2018 | Special Operations Command | 79453 |  | 2018-01-12 | 2019-01-23 | ACC Construction Co, Inc | W912PM19C0011 / 55139310 | 21039018 | 21075142 | 2020-11-08 | 2020-11-19
2019-09-30 | 2018 | Special Operations Command | 80771 |  | 2017-11-16 | 2018-09-27 | MEB General Contractors | W912618C0025 | 50027000 | 50187295 | 2020-12-26 | 2020-12-26
2019-09-01 | 2016 | Special Operations Command | 80773 |  | 2016-07-27 | 2016-11-21 | ACC Construction Co., Inc. | W912PM-17-C-0001 / 46240484 | 32661077 | 33183000 | 2019-01-31 | 2019-07-30
2019-09-30 | 2016 | Special Operations Command | 80773 |  | 2016-07-27 | 2016-11-21 | ACC Construction Co., Inc. | W912PM-17-C-0001 | 32661077 | 33194000 | 2019-01-31 | 2019-06-06
2021-04-27 | 2020 | Special Operations Command | 81165 |  | 2020-07-24 | 2020-09-18 | ACC | W912PM20C0031 | 24885638 | 25100257 | 2024-03-29 | 2024-03-29
2019-09-30 | 2018 | Special Operations Command | 81894 |  | 2018-06-19 | 2018-09-07 | Attaway Construction & Associates, LLC. | W912PM18C0019 / 55785376 | 4123000 | 4123000 | 2019-03-27 | 2020-03-03
2019-09-01 | 2016 | Special Operations Command | 81897 |  | 2015-12-18 | 2016-11-18 | BUTT CONSTRUCTION COMPANY, INC | W912QR-17-C-0002 / 46150444 | 11975000 | 12209000 | 2018-08-26 | 2019-02-15
2019-09-30 | 2019 | Special Operations Command | 81899 |  | 2019-01-10 | 2019-04-19 | A4 Construction Co | W9128F19C0016 | 8794325 | 8794325 | 2021-05-31 | 2021-05-03
2019-09-01 | 2019 | Special Operations Command | 81899 |  | 2019-01-10 | 2019-04-19 | A4 Construction Co | W9128F19C0016 / 59036942 | 8794325 | 8794325 | 2021-04-22 | 2021-06-21
2019-09-30 | 2018 | Special Operations Command | 81903 |  | 2018-10-30 | 2019-03-25 | Kyudenko Corporation | W912HV19C0004 / 49128911 | 16975565 | 17014601 | 2021-04-18 | 2021-04-25
2019-09-30 | 2017 | Special Operations Command | 85958 |  | 2017-12-01 | 2019-04-11 | Windamir Development | W912PM19C0020 | 11507959 | 11507959 | 2020-12-09 | 2020-12-09
2021-04-27 | 2020 | Special Operations Command | 86021 |  | 2020-02-28 | 2020-05-05 | - | W912PM20C0018 | 10284300 | 10284300 | 2023-12-15 | 2023-12-15
2021-05-24 | 2019 | Special Operations Command | 87438 |  | 2019-05-28 | 2019-11-30 | Archer Western Contractors, LLC | W912QR21C0003 | 4970 | 4970 | 2023-08-09 | 2023-08-09
2021-04-27 | 2020 | Special Operations Command | 87539 |  | 2020-01-30 | 2020-05-18 | - | W912PM20C0012 | 4983661 | 9983661 | 2023-03-21 | 2023-03-21
2021-04-27 | 2020 | Special Operations Command | 92594 |  | 2020-02-12 | 2020-06-19 | Sauer | W912PM20C0016 | 20768000 | 20768000 | 2024-01-09 | 2024-01-09
2019-09-30 | 2016 | Special Operations Command | AFSOC103002 |  | 2018-04-09 | 2018-09-28 | Nippo Corporation | W912HV-16-D-0008 | 33752000 | 33721000 | 2020-10-21 | 2020-11-01
2019-09-01 | 2016 | Special Operations Command | AFSOC103002 |  | 2018-04-09 | 2018-09-28 | Nippo Corporation | W912HV-16-D-0008 / 45665928 | 33752000 | 32844000 | 2020-10-21 | 2021-01-19
2021-05-24 | 2017 | Special Operations Command | AFSOC103010 |  | 2020-07-24 | 2021-04-14 | - | W912HV21C0002 | 10760 | 10760
2019-09-30 | 2017 | Special Operations Command | AFSOC103022 |  | 2018-01-16 | 2018-02-16 | MIRAIT.T-ACTY JV | W912HV15D0032 / 45884453 | 3470750 | 3587463 | 2019-02-04 | 2019-03-21
2019-09-30 | 2017 | Special Operations Command | AFSOC103022 |  | 2018-03-23 | 2019-08-02 | Nippo Construction | W912HV-17-D-0015 | 63052343 | 63052343 | 2021-12-26 | 2022-01-21
2019-09-30 | 2015 | Special Operations Command | CZQZ063029 |  | 2016-12-13 | 2018-05-24 | Federal Contracting, Inc. | W912PP19C0001 / 62022393 | 36206044 | 36445426 | 2021-05-16 | 2021-09-13
2019-09-30 | 2018 | Special Operations Command | CZQZ103006 |  | 2018-04-26 | 2018-09-28 | Walga Ross Group JV | W912PP18C0022 / 59702316 | 5732000 | 5747074 | 2020-01-13 | 2020-01-13
2019-09-30 | 2016 | Special Operations Command | CZQZ133003 |  | 2017-04-05 | 2018-05-24 | Federal Contracting, Inc. | W912PP19C0001 | 16606634 | 16702680 | 2021-05-16 | 2021-09-13
2019-09-01 | 2016 | Special Operations Command | CZQZ133003 |  | 2017-04-05 | 2018-05-24 | Federal Contracting, Inc. | W912PP19C0001 / 62023605 | 16606634 | 16606 | 2021-05-16 | 2021-08-14
2019-09-01 | 2016 | Special Operations Command | FTEV073010 |  | 2016-03-19 | 2016-08-02 | Cutter Enterprises, LLC | W91278-16-C-0021 / 53891665 | 14173000 | 14207000 | 2018-09-15 | 2019-11-27
2019-09-30 | 2016 | Special Operations Command | FTEV073010 |  | 2016-03-19 | 2016-08-02 | Cutter Enterprises, LLC | W91278-16-C-0021 | 16065430 | 16098745 | 2018-09-15 | 2020-09-30
2021-04-27 | 2018 | Special Operations Command | FTEV151114 |  | 2020-03-26 | 2020-10-23 | - | W9127821C0004 | 2630353 | 2630353 | 2022-09-07 | 2022-09-07
2019-09-30 | 2018 | Special Operations Command | FTEV153003 |  | 2018-07-27 | 2018-09-27 | Leebcor Services LLC. | W91278-16-D-0033 / 55139768 | 10264000 | 10265000 | 2020-04-23 | 2020-07-22
2021-04-27 | 2020 | Special Operations Command | FTEV153007 |  | 2020-06-03 | 2020-09-30 | - | W9127820C0026 | 11836700 | 11836700 | 2023-08-25 | 2023-08-25
2021-04-27 | 2020 | Special Operations Command | FTEV153009 |  | 2020-11-06 | 2021-02-26 | HENSEL PHELPS CONSTRUCTION CO. | W9127821C0008 | 66581000 | 66581000 | 2024-09-13 | 2023-09-13
2019-09-30 | 2017 | Special Operations Command | LXEZ123484 |  | 2018-04-12 | 2019-05-30 | Nishimatsu Construction Co, LTD | W912HV-16-D-0009 | 16739026 | 16739026 | 2021-07-22 | 2021-07-22
2019-09-30 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co. | W91278-12-D-0038 | 34157000 | 38234191 | 2019-01-26 | 2019-11-19
2019-09-01 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co. | W91278-12-D-0038 / 54346656 | 13223000 | 14536000 | 2019-01-26 | 2019-04-19
2019-09-01 | 2016 | Special Operations Command | NVZR143703 |  | 2016-05-10 | 2016-09-20 | Hensel Phelps Construction Co. | W91278-12-D-0038 / 44336728 | 20934000 | 20934000 | 2019-01-26 | 2019-03-04
2019-09-30 | 2016 | Special Operations Command | P-1219 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 63726000 | 62718000 | 2020-01-12 | 2020-04-03
2019-09-30 | 2016 | Special Operations Command | P-1288 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 14521000 | 14420000 | 2020-01-12 | 2020-04-03
2019-09-30 | 2013 | Special Operations Command | P-1393 |  | 2013-06-11 | 2013-09-19 | RQ-DPR Construction Joint Venture | N4008513C6000 AWD | 4903000 | 4796000 | 2016-01-18 | 2018-01-31
2019-09-30 | 2015 | Special Operations Command | P-1396 |  | 2015-05-29 | 2015-08-17 | The Whiting-Turner Contracting Co | N40085-10-D-5330-0012 | 10331000 | 12706000 | 2017-03-09 | 2017-10-27
2019-09-30 | 2013 | Special Operations Command | P-1410 |  | 2013-09-04 | 2013-09-26 | Quadrant Construction | N4008510D0261 | 1826000 | 1809000 | 2014-09-22 | 2015-06-30
2019-09-30 | 2015 | Special Operations Command | P-1475 |  | 2018-02-07 | 2018-06-19 | Military & Federal Construction Co, Inc | TBD | 3136000 | 3025000 | 2018-09-13 | 2020-04-09
2019-09-30 | 2016 | Special Operations Command | P-1481 |  | 2018-03-05 | 2018-08-31 | LARION HUMPHREY CONSTRUCTION LLC | TBD | 3716000 | 3555000 | 2019-11-11 | 2020-03-17
2019-09-30 | 2016 | Special Operations Command | P-225 |  | 2017-09-05 | 2018-08-03 | TIKIGAG CONSTRUCTION | N4008517D0362 | 3455000 | 3373000 | 2019-08-30 | 2019-10-22
2020-06-12 | 2018 | Special Operations Command | P-241 |  | 2019-04-16 | 2019-09-26 | DANIELS AND DANIELS CONSTRUCTION | N4008514D1322 | 4194000 | 4281431 | 2020-11-13 | 2020-11-18
2019-09-30 | 2014 | Special Operations Command | P-334 |  | 2015-07-21 | 2016-02-10 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0007 | 29668000 | 29734000 | 2018-07-29 | 2020-01-31
2019-09-30 | 2015 | Special Operations Command | P-776 |  | 2015-08-26 | 2015-09-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247315D2426 0002 | 30528000 | 37018000 | 2017-10-23 | 2019-07-23
2019-09-30 | 2016 | Special Operations Command | P-777 |  | 2016-10-31 | 2018-07-16 | WHITING-TURNER CONTRACTING CO | TBD | 24780000 | 23193000 | 2020-10-09 | 2020-12-13
2019-09-30 | 2018 | Special Operations Command | P-791 |  | 2018-01-19 | 2018-09-13 | HOURIGAN CONSTRUCTION CO | N4008518C1103 | 24701000 | 22642000 | 2021-03-17 | 2021-03-17
2019-09-30 | 2013 | Special Operations Command | P-888 |  | 2014-04-01 | 2014-09-30 | KOO CONSTRUCTION INC | N6247309D1655 0005 | 14869000 | 14223000 | 2016-09-29 | 2017-11-08
2019-09-30 | 2017 | Special Operations Command | P-890 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N6247317C0830 | 32902000 | 33724000 | 2020-03-31 | 2020-03-31
2019-09-30 | 2018 | Special Operations Command | P-892 |  | 2017-11-07 | 2018-09-13 | RQ CONSTRUCTION LLC | N6247319C1103 | 49562000 | 47202000 | 2021-03-31 | 2021-03-31
2019-09-01 | 2018 | Special Operations Command | P-892 |  | 2017-11-07 | 2018-09-13 | RQ CONSTRUCTION LLC | TBD | 49562000 | 46788000 | 2021-03-31 | 2021-03-31
2019-09-30 | 2015 | Special Operations Command | P-893 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N6247315C1609 AWD | 24873000 | 24387000 | 2018-04-02 | 2019-03-11
2019-09-30 | 2017 | Special Operations Command | P-900 |  | 2018-06-28 | 2019-02-22 | SYNCON, LLC | N4008518D1143 | 3422000 | 3145000 | 2020-02-10 | 2020-02-10
2019-09-30 | 2017 | Special Operations Command | P-919 |  | 2016-09-20 | 2017-03-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 18210000 | 17315000 | 2018-10-22 | 2019-07-03
2019-09-30 | 2016 | Special Operations Command | P-920 |  | 2016-05-12 | 2016-09-20 | RQ CONSTRUCTION, LLC | N6247315D2428 0003 | 47022000 | 45790000 | 2018-10-13 | 2019-12-27
2019-09-01 | 2018 | Special Operations Command | P-921 |  | 2018-02-14 | 2018-07-26 | RQ CONSTRUCTION LLC | TBD | 47550000 | 44397000 | 2021-02-15 | 2021-02-15
2019-09-30 | 2018 | Special Operations Command | P-921 |  | 2018-02-14 | 2018-07-26 | RQ CONSTRUCTION LLC | N6247318D0820 | 47550000 | 44413000 | 2021-02-15 | 2021-02-15
2019-09-30 | 2017 | Special Operations Command | P-952 |  | 2017-04-28 | 2017-08-10 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 16668000 | 16561000 | 2019-11-22 | 2019-11-22
2019-09-30 | 2018 | Special Operations Command | P-964 |  | 2018-02-22 | 2018-09-13 | RQ CONSTRUCTION LLC | N6247318C1017 | 39378000 | 37049000 | 2020-04-19 | 2021-03-31
2019-09-01 | 2018 | Special Operations Command | P-964 |  | 2018-02-22 | 2018-09-13 | TBD | TBD | 39378000 | 37023000 | 2020-04-19 | 2020-04-19
2019-09-30 | 2017 | Special Operations Command | P-966 |  | 2017-04-28 | 2017-09-28 | M A MORTENSON COMPANY | N6247317D0819 | 46106000 | 43175000 | 2020-04-19 | 2020-04-19
2021-05-11 | 2015 | Special Operations Command | P1119 |  | 2015-08-05 | 2015-09-29 | COX CONSTRUCTION CO | N6247315D2405 0003 | 12428 | 12167 | 2016-04-06 | 2016-04-06
2021-05-11 | 2016 | Special Operations Command | P1126 |  | 2016-05-10 | 2016-08-08 | A&D GC INC | N6247315D2403 0005 | 10911 | 11642 | 2018-02-14 | 2019-02-28
2021-05-11 | 2013 | Special Operations Command | P1218 |  | 2013-06-11 | 2013-09-19 | RQ-DPR JV | N4008513C6000 AWD | 47295 | 49983 | 2016-01-18 | 2018-01-31
2021-05-11 | 2016 | Special Operations Command | P1219 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 63726 | 64967 | 2020-01-12 | 2021-07-12
2021-05-11 | 2016 | Special Operations Command | P1288 |  | 2017-01-27 | 2017-12-28 | RQ CONSTRUCTION, LLC | N4008518C0614 | 14521 | 15120 | 2020-01-12 | 2021-07-12
2021-05-11 | 2018 | Special Operations Command | P1362 |  | 2020-01-27 | 2020-07-22 | PATRIOT CONSTRUCTION, LLC | N4008520C0142 AWD | 7962 | 7583 | 2022-02-07 | 2022-02-07
2021-05-11 | 2014 | Special Operations Command | P1391 |  | 2014-05-29 | 2014-08-28 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0004 | 30963 | 30841 | 2016-09-02 | 2019-01-31
2021-05-11 | 2013 | Special Operations Command | P1393 |  | 2013-06-11 | 2013-09-19 | RQ-DPR JV | N4008513C6000 AWD | 4903 | 4796 | 2016-01-18 | 2018-01-31
2021-05-11 | 2018 | Special Operations Command | P1394 |  | 2019-09-17 | 2020-03-27 | WHITING-TURNER CONTRACTING CO | N4008520D0036 | 11658 | 11660 | 2021-10-04 | 2021-10-23
2021-05-11 | 2020 | Special Operations Command | P1395 |  | 2020-07-14 | 2020-12-18 | WHITING-TURNER CONTRACTING CO | N4008521C0018 AWD | 13438 | 1349 | 2022-12-17 | 2023-02-17
2021-05-11 | 2015 | Special Operations Command | P1396 |  | 2015-05-29 | 2015-08-17 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0012 | 10331 | 12849 | 2017-03-09 | 2017-10-27
2021-05-11 | 2013 | Special Operations Command | P1410 |  | 2013-09-04 | 2013-09-26 | QUADRANT CONSTRUCTION, INC | N4008510D0261 | 1826 | 1809 | 2014-09-22 | 2015-06-30
2021-05-11 | 2013 | Special Operations Command | P1450 |  | 2013-12-20 | 2014-02-13 | QUADRANT CONSTRUCTION, INC | N4008510D0261 | 1732 | 1721 | 2014-12-10 | 2015-10-30
2021-05-11 | 2014 | Special Operations Command | P1469 |  | 2014-08-20 | 2014-09-30 | Awarded by Other Agency | N4008510D0261 | 1944 | 1938 | 2015-11-24 | 2016-08-25
2021-05-11 | 2015 | Special Operations Command | P1475 |  | 2018-02-07 | 2018-06-19 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008518C6101 | 3136 | 3130 | 2019-09-13 | 2021-01-14
2021-05-11 | 2016 | Special Operations Command | P1481 |  | 2018-03-05 | 2018-08-31 | LARION HUMPHREY CONSTRUCTION LLC | N4008518C6118 | 3716 | 3594 | 2019-11-11 | 2020-07-06
2021-05-11 | 2020 | Special Operations Command | P1482 |  | 2020-06-30 | 2020-09-22 | QUADRANT CONSTRUCTION, INC | N4008515D0851 N4008520F6725 | 4524 | 258 | 2021-09-18 | 2022-01-11
2021-05-11 | 2020 | Special Operations Command | P1534 |  | 2020-03-30 | 2020-09-15 | RQ CONSTRUCTION, LLC | N4008520D0034 N4008520F6501 | 38218 | 26765 | 2024-05-27 | 2024-05-27
2021-05-11 | 2014 | Special Operations Command | P157 |  | 2014-11-13 | 2016-02-26 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0008 | 19230 | 19585 | 2017-09-03 | 2020-09-16
2021-05-11 | 2013 | Special Operations Command | P165 |  | 2013-05-16 | 2013-09-24 | LEEBCOR SERVICES LLC | N4008512D6304 | 10741 | 10072 | 2015-09-09 | 2015-11-26
2021-05-11 | 2015 | Special Operations Command | P166 |  | 2015-05-05 | 2015-09-21 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0011 | 13588 | 13368 | 2017-07-17 | 2019-03-04
2021-05-11 | 2015 | Special Operations Command | P170 |  | 2015-03-10 | 2016-01-26 | PENTACON, LLC | N6945014D0757 0002 | 10593 | 10433 | 2017-10-17 | 2018-06-16
2021-05-11 | 2015 | Special Operations Command | P183 |  | 2015-08-12 | 2016-04-17 | CLARK NEXSEN - CH2M HILL - NORFOLK | N6247011D1010 WE11 | 15050 | 16167 | 2017-07-24 | 2018-05-18
2021-05-11 | 2019 | Special Operations Command | P200 |  | 2019-01-30 | 2020-06-30 | RQ CONSTRUCTION, LLC | N6247317D0820 N6247320F4839 | 26431 | 27117 | 2023-01-20 | 2023-01-20
2021-05-11 | 2020 | Special Operations Command | P224 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N4008519D9070 N4008521F4540 | 1828 | 1828 | 2023-08-05 | 2023-08-05
2021-05-11 | 2016 | Special Operations Command | P225 |  | 2017-09-05 | 2018-08-03 | TIKIGAQ CONSTRUCTION, LLC | N4008517D0362 | 3455 | 3445 | 2019-08-30 | 2020-01-07
2021-05-11 | 2015 | Special Operations Command | P240 |  | 2019-04-22 | 2019-07-29 | TIKIGAQ CONSTRUCTION, LLC | N6945019C5214 | 18436 | 16974 | 2020-03-25 | 2020-01-25
2021-05-11 | 2018 | Special Operations Command | P241 |  | 2019-08-08 | 2019-09-26 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008514D1322 | 4921 | 4916 | 2020-11-13 | 2021-01-14
2021-05-11 | 2014 | Special Operations Command | P334 |  | 2015-07-21 | 2016-02-10 | DPR HARDIN CONSTRUCTIONWGI JOINT VENTURE | N4008510D5333 0007 | 29668 | 31020 | 2018-07-29 | 2020-05-01
2021-05-11 | 2015 | Special Operations Command | P418 |  | 2015-06-12 | 2015-08-18 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0006 | 20585 | 21217 | 2017-02-23 | 2018-02-12
2021-05-11 | 2020 | Special Operations Command | P463 |  | 2019-08-29 | 2020-04-15 | HENSEL PHELPS CONSTRUCTION CO. | N6247819D5029 | 54279 | 3365 | 2022-04-15 | 2022-04-15
2021-05-11 | 2013 | Special Operations Command | P475 |  | 2014-07-31 | 2016-01-25 | BETHEL-WEBCOR JV-1 | N6247814D4001 0006 | 22462 | 21682 | 2018-02-13 | 2018-06-24
2021-05-11 | 2013 | Special Operations Command | P564 |  | 2013-08-01 | 2013-09-30 | ROYCE HOMELAND JV, LLC | N4008512D6305 | 1517 | 1445 | 2014-12-31 | 2015-02-12
2021-05-11 | 2013 | Special Operations Command | P576 |  | 2016-03-17 | 2016-07-15 | SOUTHEAST CHEROKEE CONSTRUCTION INC | N4008515D0096 0003 | 2519 | 2515 | 2016-08-14 | 2018-01-03
2021-05-11 | 2018 | Special Operations Command | P698 |  | 2020-12-21 | 2021-03-24 | SYNCON, LLC | N4008518D1143 N4008521F4963 | 2846 | 2776 | 2022-08-08 | 2022-08-08
2021-05-11 | 2014 | Special Operations Command | P771 |  | 2018-07-13 | 2018-09-19 | SOLPAC CONSTRUCTION INC | N6247317D0821 | 32 | 33999 | 2020-02-02 | 2021-04-21
2021-05-11 | 2015 | Special Operations Command | P776 |  | 2015-08-26 | 2015-09-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247315D2426 0002 | 30528 | 37040 | 2017-10-23 | 2019-07-23
2021-05-11 | 2016 | Special Operations Command | P777 |  | 2016-10-31 | 2018-07-16 | WHITING-TURNER CONTRACTING CO | N4008518C1137 | 24780 | 23709 | 2020-10-09 | 2020-12-13
2021-05-11 | 2018 | Special Operations Command | P791 |  | 2018-01-19 | 2018-09-13 | HOURIGAN CONSTRUCTION CORPORATION | N4008518C1103 | 24701 | 24233 | 2021-03-17 | 2022-01-12
2021-05-11 | 2020 | Special Operations Command | P824 |  | 2020-08-05 | 2020-09-30 | ASTURIAN-CONSIGLI JV, LLC | N4008518D1124 N4008520F6689 | 11130 | 12399 | 2022-08-16 | 2022-08-16
2021-05-11 | 2019 | Special Operations Command | P834 |  | 2019-03-22 | 2019-11-12 | Awarded by Other Agency | N4008518D1125 N4008520F4066 | 10586 | 10127 | 2021-05-20 | 2021-08-18
2021-05-11 | 2018 | Special Operations Command | P855 |  | 2017-11-08 | 2019-09-30 | WHITING-TURNER CONTRACTING CO | N6247319C1238 | 96932 | 94895 | 2022-08-30 | 2022-12-07
2021-05-11 | 2013 | Special Operations Command | P876 |  | 2014-05-05 | 2014-09-26 | RQ CONSTRUCTION, LLC | N6247310D5409 0015 | 27636 | 27585 | 2016-10-07 | 2017-08-11
2021-05-11 | 2013 | Special Operations Command | P888 |  | 2014-04-01 | 2014-09-30 | KOO CONSTRUCTION INC | N6247309D1655 0005 | 14869 | 14223 | 2016-09-29 | 2017-11-08
2021-05-11 | 2017 | Special Operations Command | P889 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N6247314D0061 | 36321 | 34720 | 2020-03-31 | 2021-01-31
2021-05-11 | 2017 | Special Operations Command | P890 |  | 2017-04-05 | 2017-09-28 | RQ CONSTRUCTION, LLC | N6247317C0830 | 32902 | 35554 | 2020-03-31 | 2021-01-31
2021-05-11 | 2018 | Special Operations Command | P892 |  | 2017-11-07 | 2018-09-13 | RQ CONSTRUCTION, LLC | N6247318C1017 | 49562 | 48060 | 2021-03-31 | 2021-03-31
2021-05-11 | 2015 | Special Operations Command | P893 |  | 2015-07-29 | 2015-09-30 | RQ-DPR JV | N6247315C1609 AWD | 24873 | 24379 | 2018-04-02 | 2019-03-11
2021-05-11 | 2017 | Special Operations Command | P900 |  | 2018-06-28 | 2019-02-22 | SYNCON, LLC | N4008518D1143 | 3422 | 3314 | 2020-02-10 | 2020-10-16
2021-04-13 | 2020 | Special Operations Command | P914 |  | 2020-07-09 | 2020-10-07 | ASTURIAN-CONSIGLI JV, LLC | N4008518D1124 N4008521F4027 | 4626 | 4876 | 2022-04-23 | 2022-04-23
2021-05-11 | 2020 | Special Operations Command | P914U |  | 2020-07-09 | 2020-10-07 | ASTURIAN-CONSIGLI JV, LLC | N4008518D1124 N4008521F4027 | 4626 | 4876 | 2022-04-23 | 2022-04-23
2021-05-11 | 2013 | Special Operations Command | P915 |  | 2015-02-12 | 2015-09-10 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0011 | 10605 | 10408 | 2017-08-28 | 2018-06-07
2021-05-11 | 2019 | Special Operations Command | P918 |  | 2019-05-01 | 2019-09-26 | THE HASKELL COMPANY | N6247317D0818 | 15182 | 14530 | 2021-10-09 | 2021-11-04
2021-05-11 | 2017 | Special Operations Command | P919 |  | 2016-09-20 | 2017-03-30 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 18210 | 18062 | 2018-10-22 | 2020-03-06
2021-05-11 | 2016 | Special Operations Command | P920 |  | 2016-05-12 | 2016-09-20 | RQ CONSTRUCTION, LLC | N6247315D2428 0003 | 47022 | 45974 | 2018-10-13 | 2019-12-27
2021-05-11 | 2018 | Special Operations Command | P921 |  | 2018-02-14 | 2018-07-26 | RQ CONSTRUCTION, LLC | N6247318D0820 | 47550 | 45333 | 2021-02-15 | 2021-06-18
2021-05-11 | 2014 | Special Operations Command | P9440 |  | 2014-12-15 | 2015-04-30 | ARGO SYSTEMS, LLC | N6945014D1271 0003 | 4140 | 4090 | 2016-08-22 | 2019-07-17
2021-05-11 | 2020 | Special Operations Command | P945 |  | 2020-01-23 | 2021-01-15 | EG DESIGNBUILD, L.L.C | N6945019D0919 N6945021F0872 | 17165 | 18090 | 2022-10-31 | 2022-10-31
2021-05-11 | 2019 | Special Operations Command | P949 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N6247317D0822 N6247320F4023 | 15467 | 14837 | 2022-05-19 | 2022-09-12
2021-05-11 | 2019 | Special Operations Command | P950 |  | 2019-02-28 | 2019-10-28 | WHITING-TURNER CONTRACTING CO | N6247317D0822 N6247320F4023 | 18434 | 18685 | 2022-05-19 | 2022-09-12
2021-05-11 | 2017 | Special Operations Command | P952 |  | 2017-04-28 | 2017-08-10 | SOLTEK PACIFIC CONSTRUCTION CO | N6247317D0821 | 16668 | 16776 | 2019-11-22 | 2020-03-02
2021-05-11 | 2018 | Special Operations Command | P964 |  | 2018-02-22 | 2018-09-13 | RQ CONSTRUCTION, LLC | N6247318C1017 | 39378 | 37861 | 2021-03-31 | 2021-03-31
2021-05-11 | 2017 | Special Operations Command | P966 |  | 2017-04-28 | 2017-09-28 | M A MORTENSON COMPANY | N6247317D0819 | 46106 | 44923 | 2020-04-19 | 2020-11-20
2021-05-11 | 2020 | Special Operations Command | P999 |  | 2020-08-10 | 2021-01-29 | WHITING-TURNER CONTRACTING CO | N4008519D9070 N4008521F4540 | 1828 | 1828 | 2023-08-05 | 2023-08-05
2021-04-27 | 2020 | Special Operations Command | PQWY083008 |  | 2019-12-13 | 2020-05-28 | - | W912DW20C0005 | 42743158 | 43199311 | 2023-10-04 | 2023-10-04
2019-09-30 | 2016 | Special Operations Command | TMKH003003 |  | 2017-04-07 | 2018-06-07 | Leebcor Services, LLC | W912PM18C0013 | 15241000 | 15182000 | 2020-06-20 | 2020-09-20
2021-03-03 | 2010 | Washington Headquarters Services | 80001 |  | 2013-09-01 | 2013-09-30 | Virginia Electric and Power Company | HQ0034-13-F-0027 | 13679273 | 13679273 | 2015-01-31 | 2020-11-30
2021-05-10 | 2010 | Washington Headquarters Services | 80001 |  | 2013-07-15 | 2013-09-30 | Cherokee Nation | HQ0034-13-C-0133 | 9669575 |  | 2019-04-02 | 2021-07-01
2021-05-10 | 2010 | Washington Headquarters Services | 80001A |  | 2013-09-01 | 2013-09-30 | Virginia Electric and Power Company | HQ0034-13-F-0027 | 13679273 | 13679273 | 2015-01-31 | 2020-04-30
2017-04-20 | 2011 | Washington Headquarters Services | 80003 |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. | W912DR-11-R-0060 | 5609000 | 6357500 | 2015-05-03 | 2016-07-01
2016-09-15 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC | W912DR-11-R-0062 | 5454000 | 5492659 | 2015-05-01 | 2015-10-01
2021-03-03 | 2011 | Washington Headquarters Services | 80004 |  | 2011-08-08 | 2016-09-30 | Turtle Associates | W912DR-16-C-0039 | 4836640 | 7901675 | 2018-05-18 | 2020-05-22
2016-12-15 | 2012 | Washington Headquarters Services | 80005
2016-12-15 | 2012 | Washington Headquarters Services | 80006
2018-04-15 | 2014 | Washington Headquarters Services | 80007
2021-05-10 | 2014 | Washington Headquarters Services | 80007 |  | 2017-04-24 | 2018-05-23 | Grunley Construction Company, Inc. | HQ0034-18-C-0042 | 21716999 | 21716999 | 2020-09-23 | 2021-08-31
2021-03-03 | 2014 | Washington Headquarters Services | 80008 |  | 2016-02-11 | 2016-04-29 | ACS | W912DR-16-C-0009 | 5797374 | 9174933 | 2017-12-01 | 2020-08-01
2017-01-19 | 2014 | Washington Headquarters Services | 80009 |  | 2016-08-12
2021-03-03 | 2014 | Washington Headquarters Services | 80009 |  | 2016-08-12 | 2017-01-26 | Grunley Construction Company, Inc. | HQ0034-17-C-0009 | 28542500 | 32047000 | 2019-10-02 | 2020-07-01
2018-09-20 | 2014 | Washington Headquarters Services | 80010
2021-05-10 | 2015 | Washington Headquarters Services | 80011 |  | 2018-08-20 | 2019-05-09 | Cherokee Nations Environmental Solutions | HQ0034-19-C-0043 | 15100000 | 15100000 | 2021-06-21 | 2022-04-15
2019-04-18 | 2015 | Washington Headquarters Services | 80011 |  | 2018-08-20
2019-08-15 | 2017 | Washington Headquarters Services | 80916 |  | 2018-04-06
2021-05-10 | 2018 | Washington Headquarters Services | 87637 |  | 2018-07-05 | 2020-03-27 | Sauer Incorporated | W912DR-20-C-0014 | 9711000 | 9711000 | 2022-06-21 | 2022-08-16
2020-03-09 | 2018 | Washington Headquarters Services | 87637
2021-05-10 | 2019 | Washington Headquarters Services | 87645 |  | 2019-07-22 | 2019-09-30 | John C. Grimberg Co, Inc. | W912DR19C0057 | 9255000 | 9255000 | 2021-04-23 | 2021-12-31
2019-09-19 | 2019 | Washington Headquarters Services | 87645
2021-05-10 | 2017 | Washington Headquarters Services | 87744 |  | 2019-03-27 | 2020-01-21 | M.A. Mortenson Company | W912DR-16-D-0017 | 7232827 |  | 2021-08-13 | 2021-08-13
2020-01-08 | 2017 | Washington Headquarters Services | 87744
2021-05-10 | 2019 | Washington Headquarters Services | 88790 |  | 2019-10-25 | 2020-03-27 | Grunley Construction Company, Inc. | W912DR-20-C-0015 | 20553000 | 20553000 | 2022-07-05 | 2022-08-17
2020-03-09 | 2019 | Washington Headquarters Services | 88790
2020-01-08 | 2018 | Washington Headquarters Services | 88963
2021-05-10 | 2018 | Washington Headquarters Services | 88963 |  | 2019-05-22 | 2020-01-07 | HSU Development, Inc | W912DR-17-D-0015 | 11774418 | 11774418 | 2022-01-20 | 2022-01-20
2021-05-10 | 2018 | Washington Headquarters Services | 91474 |  | 2019-03-08 | 2019-06-28 | Grunley Construction Company, Inc. | W912DR-17-D-0002 | 24006000 | 24006000 | 2021-01-22 | 2023-02-28
2019-05-16 | 2018 | Washington Headquarters Services | 91474
2021-05-10 | 2018 | Washington Headquarters Services | 91474A |  | 2018-03-06 | 2018-09-25 | MC DEAN | HQ0034-17-D-0006 | 1186116 | 1186116 | 2019-06-18 | 2019-06-18
2021-05-10 | 2020 | Washington Headquarters Services | 91531
2021-05-10 | 2020 | Washington Headquarters Services | 92232 |  | 2020-03-12 | 2021-03-25 | Grunley Construction Company, Inc. | W912DR-21-C-0009 | 16690000 | 16690000 | 2023-04-30 | 2023-04-30
2021-03-03 | 2020 | Washington Headquarters Services | 92232

## EXPENDITURES
Expenditure Data as of Date | Appropriation Fiscal Year | Project Sponsor Component Name | Appropriation Fund Type Name | Use of Funds | Aggregated Appropriated Amount | Aggregated Current Obligated Amount | Aggregated Current Expenditure Amount
2021-03-31 | 2015 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 0 | 0 | 0
2021-03-31 | 2021 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 94245000 | 0 | 0
2021-03-31 | 2017 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 56984000 | 42238000 | 298000
2021-03-31 | 2016 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 94590000 | 34883000 | 48104000
2021-03-31 | 2013 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73937000 | 60600000 | 58504000
2021-03-31 | 2018 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 80617000 | 7765000 | 2000
2021-03-31 | 2019 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 75247000 | 0 | 0
2021-03-31 | 2020 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53584000 | 0 | 0
2021-03-31 | 2012 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407000 | 20380000 | 20220000
2021-03-31 | 2014 | Air Force Active | Improvements - Military Family Housing | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093000 | 3217000 | 18007000
2021-03-31 | 2020 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 122590000 | 121750000 | 34133000
2021-03-31 | 2019 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 158232000 | 158899000 | 87006000
2021-03-31 | 2018 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 138783000 | 137461000 | 91436000
2021-03-31 | 2017 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 124813000 | 121905000 | 106291000
2021-03-31 | 2016 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 142144000 | 139293000 | 133483000
2021-03-31 | 2021 | Air Force Active | Military Family Housing - Operations and Maintenance | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 140666000 | 115031000 | 4804000
2021-03-31 | 2013 | Air Force Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 379000 | 112000 | 63000
2021-03-31 | 2021 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 271356000 | 6084000 | 201000
2021-03-31 | 2012 | Air Force Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 78384000 | 60140000 | 60137000
2021-03-31 | 2014 | Air Force Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 23291000 | 4684000 | 4684000
2021-03-31 | 2018 | Air Force Active | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 217485000 | 118780000 | 143752000
2021-03-31 | 2015 | Air Force Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 10738000 | 1252000 | 31000
2021-03-31 | 2020 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 347636000 | 144361000 | 8464000
2021-03-31 | 2019 | Air Force Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 450277000 | 298996000 | 303624000
2021-03-31 | 2017 | Air Force Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 199393000 | 32274000 | 35931000
2021-03-31 | 2016 | Air Force Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 87809000 | 7707000 | 3097000
2021-03-31 | 2020 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3409000 | 1796000 | 1260000
2021-03-31 | 2019 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY20 MILCON; design of FY19 non-PB projects if any; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3199000 | 173000 | 173000
2021-03-31 | 2018 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY19 MILCON; design of FY18 non-PB projects if any; start design of F20 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4445000 | 1449000 | 3371000
2021-03-31 | 2017 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY18 MILCON; design of FY17 non-PB projects if any; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4368000 | 2825000 | 3937000
2021-03-31 | 2016 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY17 MILCON; design of FY16 non-PB projects if any; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 9849000 | 2517000 | 2464000
2021-03-31 | 2014 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267000 | 0 | 0
2021-03-31 | 2013 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY14 MILCON; design of FY13 non-PB projects if any; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3952000 | 294000 | 735000
2021-03-31 | 2012 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056000 | 3868000 | 3874000
2021-03-31 | 2021 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY21 MILCON; design of FY20 non-PB projects if any; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 2969000 | 105000 | 77000
2021-03-31 | 2015 | Air Force Active | Planning and Design - Military Family Housing | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 0 | 0 | 0
2021-03-31 | 2018 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 41400000 | 19115000 | 20398000
2021-03-31 | 2019 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 38500000 | 7058000 | 7353000
2021-03-31 | 2020 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 92482000 | 9771000 | 47000
2021-03-31 | 2015 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22613000 | 18226000 | 17335000
2021-03-31 | 2016 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22900000 | 8154000 | 11338000
2021-03-31 | 2014 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448000 | 1739000 | 2658000
2021-03-31 | 2021 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 85000000 | 0 | 0
2021-03-31 | 2013 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 19006000 | 2573000 | 2545000
2021-03-31 | 2017 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 41237000 | 22727000 | 18288000
2021-03-31 | 2012 | Air Force Active | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 19157000 | 11384000 | 11333000
2021-04-30 | 2020 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 4604000 | 697000 | 11000
2019-01-31 | 2008 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300000 | 4834592 | 4834592
2019-01-31 | 2009 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165000 | 5019558 | 5019558
2019-01-31 | 2010 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139000 | 5503365 | 5408431
2019-01-31 | 2006 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289570 | 4749220 | 4749220
2019-01-31 | 2007 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109000 | 4692276 | 4692276
2021-02-28 | 2021 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY22 MILCON; start design of FY23 MILCON; fund Congressionally directed designs. | 3270000 | 0 | 0
2021-04-30 | 2011 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1650000 | 1521000 | 1521000
2021-04-30 | 2012 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200000 | 1285000 | 1287000
2021-04-30 | 2013 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 2875000 | 426000 | 426000
2021-04-30 | 2014 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229000 | 66000 | 66000
2021-04-30 | 2015 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 6892000 | 81000 | 300000
2021-04-30 | 2016 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 13400000 | 999000 | 661000
2021-04-30 | 2017 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs. | 13500000 | 6466000 | 6637000
2021-04-30 | 2018 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs. | 24725000 | 13171000 | 18336000
2021-04-30 | 2019 | Air Force Reserve | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs. | 4055000 | 3011000 | 282000
2021-04-30 | 2020 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 12146000 | 0 | 0
2021-04-30 | 2019 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3358000 | 0 | 0
2019-01-31 | 2006 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 3960000 | 3960000 | 3960000
2019-01-31 | 2009 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 5443000 | 5442927 | 5442927
2019-01-31 | 2010 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 800000 | 800000 | 800000
2019-01-31 | 2008 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 4909000 | 4909000 | 4909000
2021-02-28 | 2021 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5647000 | 0 | 0
2019-01-31 | 2007 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construction thresholds specified in 10 USC 2805(a). | 4477000 | 4476971 | 4476971
2021-04-30 | 2018 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13610000 | 3424000 | 1573000
2021-04-30 | 2017 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1500000 | 0 | 0
2021-04-30 | 2016 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6121000 | 1125000 | 2946000
2021-04-30 | 2015 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1400000 | 608000 | 665000
2021-04-30 | 2014 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530000 | 44000 | 59000
2021-04-30 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1997000 | 0 | 0
2021-04-30 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5434000 | 2260000 | 2258000
2021-04-30 | 2011 | Air Force Reserve | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 2753000 | 2646000 | 2646000
2021-04-30 | 2017 | Air National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; start design of FY19 MILCON; fund Congressionally directed designs. | 17338633 | 15923027 | 14037396
2021-04-30 | 2013 | Air National Guard | Planning and Design - Military Construction | Complete design of FY14 MILCON; start design of FY15 MILCON; fund Congressionally directed designs. | 3980871 | 3980871 | 3980871
2021-04-30 | 2014 | Air National Guard | Planning and Design - Military Construction | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3388764 | 13382296 | 13012455
2021-04-30 | 2015 | Air National Guard | Planning and Design - Military Construction | Complete design of FY16 MILCON; start design of FY17 MILCON; fund Congressionally directed designs. | 7687900 | 7672205 | 7544884
2021-04-30 | 2016 | Air National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; start design of FY18 MILCON; fund Congressionally directed designs. | 5093544 | 5029002 | 4905663
2021-01-31 | 2011 | Air National Guard | Planning and Design - Military Construction | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9162273 | 9164763 | 9160060
2020-07-01 | 2006 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006000 | 28018596 | 28018596
2020-07-01 | 2010 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 19670441 | 19601297 | 19515670
2020-07-01 | 2009 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 19056000 | 19040836 | 19036989
2020-07-01 | 2008 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 10721000 | 10619035 | 10619035
2020-07-01 | 2007 | Air National Guard | Planning and Design - Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 19050000 | 19043340 | 19043339
2021-04-30 | 2021 | Air National Guard | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 3414000 | 0 | 0
2021-04-30 | 2020 | Air National Guard | Planning and Design - Military Construction | Complete design of FY21 MILCON; start design of FY22 MILCON; fund Congressionally directed designs. | 36961520 | 0 | 0
2021-04-30 | 2019 | Air National Guard | Planning and Design - Military Construction | Complete design of FY20 MILCON; start design of FY21 MILCON; fund Congressionally directed designs. | 13862973 | 6658936 | 2736412
2021-04-30 | 2018 | Air National Guard | Planning and Design - Military Construction | Complete design of FY19 MILCON; start design of FY20 MILCON; fund Congressionally directed designs. | 31403314 | 34444820 | 24963521
2021-04-30 | 2012 | Air National Guard | Planning and Design - Military Construction | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12193435 | 12186246 | 12175493
2021-04-30 | 2015 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6097905 | 6061295 | 6059418
2021-04-30 | 2016 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7732740 | 7641690 | 7625190
2021-01-31 | 2011 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). Minor construction projects Supporting the Overseas Contingency Operations (OCO) | 7975387 | 7975387 | 7975387
2021-04-30 | 2014 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1900736 | 12935481 | 11336603
2020-07-01 | 2009 | Air National Guard | Unspecified Minor Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 34243000 | 34243000 | 34235708
2021-04-30 | 2021 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 0 | 0 | 0
2020-07-01 | 2007 | Air National Guard | Unspecified Minor Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 6000000 | 5999999 | 5999999
2021-04-30 | 2020 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 27191000 | 2014000 | 0
2020-07-01 | 2008 | Air National Guard | Unspecified Minor Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 14184000 | 14184000 | 14184000
2021-04-30 | 2019 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3432227 | 5578285 | 592359
2020-07-01 | 2010 | Air National Guard | Unspecified Minor Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 44913559 | 44873041 | 44638026
2021-04-30 | 2018 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 22857101 | 21222500 | 14262328
2020-07-01 | 2006 | Air National Guard | Unspecified Minor Military Construction | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 6882000 | 6882000 | 6882000
2021-04-30 | 2017 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17018110 | 17847462 | 17135777
2021-04-30 | 2013 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5889014 | 5889014 | 5889455
2021-04-30 | 2012 | Air National Guard | Unspecified Minor Military Construction | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 8967453 | 8967453 | 8949992
2020-04-30 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000000 | 24984362 | 24984362
2017-06-30 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000000 | 23999817 | 23999817
2021-03-31 | 2011 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 42944000 | 42931330 | 42931330
2021-03-31 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36500000 | 35954915 | 35954915
2021-04-30 | 2021 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 39000000 | 2914124 | 2856499
2021-04-30 | 2020 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 31000000 | 30850013 | 26990255
2021-04-30 | 2016 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 36000000 | 35998550 | 35777322
2021-04-30 | 2018 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28700000 | 28698793 | 27799217
2021-04-30 | 2017 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 18000000 | 17999931 | 17998791
2021-04-30 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 34000000 | 33873062 | 33873062
2021-04-30 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000000 | 22999621 | 22999621
2021-04-30 | 2015 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 28000000 | 27985359 | 27985359
2021-04-30 | 2019 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 16000000 | 15961505 | 14330167
2021-04-30 | 2021 | Army Active | Planning and Design - Military Construction | Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 108000000 | 29463447 | 12520135
2021-04-30 | 2020 | Army Active | Planning and Design - Military Construction | Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 105099000 | 89208177 | 74701865
2021-04-30 | 2019 | Army Active | Planning and Design - Military Construction | Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 115068000 | 96318298 | 88261922
2021-04-30 | 2018 | Army Active | Planning and Design - Military Construction | Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 97770000 | 112780994 | 105884763
2021-04-30 | 2017 | Army Active | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 80159000 | 132009011 | 126333998
2021-04-30 | 2016 | Army Active | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 73245000 | 73163238 | 71791746
2021-04-30 | 2015 | Army Active | Planning and Design - Military Construction | Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 23127000 | 23126879 | 23108716
2021-04-30 | 2014 | Army Active | Planning and Design - Military Construction | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575000 | 41573970 | 41492805
2021-04-30 | 2013 | Army Active | Planning and Design - Military Construction | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46173000 | 46111486 | 46090533
2021-03-31 | 2012 | Army Active | Planning and Design - Military Construction | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 265741000 | 258433178 | 257150321
2021-03-31 | 2011 | Army Active | Planning and Design - Military Construction | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 379238000 | 266994454 | 266994454
2017-06-30 | 2009 | Army Active | Planning and Design - Military Construction | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766000 | 221199954 | 220667673
2020-04-30 | 2010 | Army Active | Planning and Design - Military Construction | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 305903000 | 269936476 | 269936476
2021-04-30 | 2021 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 3300000 | 2396018 | 83766
2021-03-31 | 2012 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7897000 | 7833556 | 7833556
2021-04-30 | 2016 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 7195000 | 7180054 | 7067947
2021-04-30 | 2013 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4641000 | 4605750 | 4605750
2020-04-30 | 2010 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 3936000 | 3156350 | 3156350
2017-06-30 | 2009 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 579000 | 552554 | 548104
2021-04-30 | 2017 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2618000 | 2617410 | 2585337
2021-04-30 | 2015 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 1309000 | 1305379 | 1275379
2021-04-30 | 2014 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 4408000 | 4370513 | 4350513
2021-04-30 | 2020 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 9222000 | 7498160 | 1562460
2021-04-30 | 2019 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 18326000 | 18100585 | 5141248
2021-04-30 | 2018 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 29271000 | 29159803 | 27328589
2021-03-31 | 2011 | Army Active | Planning and Design - Military Family Housing | Army Family Housing Construction for Projects | 2036000 | 1821474 | 1821474
2021-04-30 | 2013 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24887655 | 24800103
2021-04-30 | 2014 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24997276 | 24774632
2021-04-30 | 2015 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 24864679 | 24487186
2021-04-30 | 2016 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 25000000 | 22899941 | 21359109
2021-04-30 | 2017 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 35000000 | 29667221 | 25029624
2021-04-30 | 2018 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 41500000 | 28651425 | 26050151
2021-04-30 | 2019 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 82000000 | 79411021 | 58246913
2021-04-30 | 2020 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 70600000 | 62820112 | 28840983
2021-03-31 | 2011 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 28704000 | 28693975 | 28693975
2021-03-31 | 2012 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 20000000 | 19998378 | 19991469
2020-04-30 | 2010 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects <= $3.M | 31250000 | 31249999 | 31249999
2017-06-30 | 2009 | Army Active | Unspecified Minor Military Construction | Unspecified Minor Construction for Projects < $2.M | 28750000 | 28467081 | 27359122
2021-05-20 | 2021 | Army National Guard | Planning and Design - Military Construction | Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 44593000 | 0 | 0
2021-05-20 | 2020 | Army National Guard | Planning and Design - Military Construction | Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 26469000 | 3918620 | 3918620
2021-05-20 | 2019 | Army National Guard | Planning and Design - Military Construction | Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 16622000 | 16246754 | 16246754
2021-05-20 | 2018 | Army National Guard | Planning and Design - Military Construction | Complete design of FY19 MILCON; design of FY18 Congressional Inserts & Recovery from Hurricanes; start design of FY20 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 74741000 | 63173774 | 63173774
2021-05-20 | 2017 | Army National Guard | Planning and Design - Military Construction | Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20729000 | 19918425 | 19918425
2021-04-20 | 2016 | Army National Guard | Planning and Design - Military Construction | Complete design of FY17 MILCON; design of FY16 Congressional Inserts; start design of FY18 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20337000 | 20271926 | 20271926
2021-04-20 | 2016 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 15000000 | 15000000 | 15000000
2021-05-20 | 2021 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 45744000 | 0 | 0
2021-05-20 | 2020 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 15000000 | 6299049 | 6299049
2021-05-20 | 2019 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 28100000 | 14104181 | 14104181
2021-05-20 | 2018 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $6M | 26731000 | 26712237 | 26712237
2021-05-20 | 2017 | Army National Guard | Unspecified Minor Military Construction | Unspecified Minor Military Construction for projects < $3M | 12001000 | 11657992 | 11657992
2018-12-01 | 2016 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For Design of projects from 2014 to 2019 | 31772000 | 363952 | 363952
2018-12-01 | 2012 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34331000 | 34331000
2018-12-01 | 2013 | DLA Defense Automation and Production Service | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 30636000 | 30636000
2018-12-01 | 2011 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 5247000 | 3801453 | 3801453
2018-12-01 | 2013 | DLA Defense Automation and Production Service | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2265551 | 2265551
2015-02-28 | 2012 | Defense Finance and Accounting Service | Planning and Design - Military Construction | Investigation and Design | 1992 | 712 | 711
2015-02-28 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction | Construction | 15404 | 13902 | 13713
2021-04-30 | 2010 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2021-04-30 | 2019 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 55729000 | 54856000 | 43156000
2021-04-30 | 2018 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 40255000 | 39087000 | 36140000
2021-04-30 | 2015 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 4855000 | 4720000 | 4716000
2021-04-30 | 2016 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 94000 | 0 | 0
2021-04-30 | 2011 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 0 | 0 | 0
2021-04-30 | 2012 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 54013000 | 48757000 | 44688000
2021-04-30 | 2013 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 67943000 | 47239000 | 34069000
2021-04-30 | 2014 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 3897000 | 3889000 | 3244000
2019-05-31 | 2009 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 171255000 | 170899000 | 170899000
2021-04-30 | 2017 | Defense Health Agency | Planning and Design - Military Construction | P&D Funding of MILCON Projects | 70000 | 0 | 0
2019-05-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 3979000 | 3979000 | 3979000
2021-04-30 | 2019 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2021-04-30 | 2018 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 7700000 | 3492000 | 2439000
2021-04-30 | 2017 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 8433000 | 5669000 | 893000
2021-04-30 | 2016 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5000000 | 4927000 | 2297000
2021-04-30 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4608000 | 4550000 | 4550000
2021-04-30 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4952000 | 3819000 | 3819000
2021-04-30 | 2015 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 4100000 | 2200000 | 2151000
2021-04-30 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2021-04-30 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 0 | 0 | 0
2021-04-30 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | UMC Projects | 5664000 | 5208000 | 5208000
2021-05-28 | 2013 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 79430000 | 68213820 | 68213820
2021-05-28 | 2014 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 2615000 | 2810000 | 2810000
2012-05-28 | 2015 | Defense Information Systems Agency | Construction - Major Military Construction | For Minor Construction | 9600000 | 12189000 | 12189000
2020-06-30 | 2012 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for DIAC Parking Garage Replacement; P&D for DIAC Chilled Water Project for Data Center ($125K) and P&D for DIAC Cooling Tower for Data Center ($105K); P&D for UPS for Data Center Installation; P&D for Construction of JUIAF RDF | 29335000 | 610664 | 19009231
2020-06-30 | 2010 | Defense Intelligence Agency | Planning and Design - Military Construction | P&D for K-16 FOB-K renovation of two buildings to include Administrative and SCIF Spaces | 442000 | 0 | 441992
2018-12-01 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of projects from 2012 to 2016 | 36093000 | 35966000 | 35966000
2018-12-01 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2014 to 2017 | 30636000 | 27241500 | 27415000
2018-12-01 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2015 to 2018 | 6978000 | 0 | 0
2018-12-01 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction |  | 0 | 0 | 0
2018-12-01 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design - Military Construction | For design of project from 2012 to 2016 | 34331000 | 34239000 | 34239000
2018-12-01 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2011 to 2014 | 4864000 | 4501000 | 4501000
2018-12-01 | 2014 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2013 to 2016 | 7430000 | 0 | 0
2018-12-01 | 2015 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2015 to 2019 | 5932000 | 0 | 0
2018-12-01 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2014 | 6312000 | 6312000 | 6312000
2018-12-01 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction | For minor construction projects from 2012 to 2015 | 6686000 | 2266000 | 2266000
2021-05-30 | 2017 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 23585000 | 15433664 | 15433664
2021-05-30 | 2016 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42183000 | 33304435 | 33304435
2021-05-30 | 2015 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 15/16/17/18 MILCON projects | 42387000 | 36954952 | 36954952
2021-05-30 | 2014 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 14/15/16/17 MILCON projects | 75905000 | 74930826 | 74930826
2021-05-30 | 2013 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 13/14/15/16 MILCON projects | 97290000 | 96946976 | 96946976
2021-05-30 | 2012 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 12/13 MILCON projects | 64551000 | 64526903 | 64526903
2021-05-30 | 2011 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 11/12/ 13 MILCON projects | 75242000 | 75050000 | 75050000
2021-05-30 | 2010 | DoD Education Activity | Planning and Design - Military Construction | Design efforts for FY 10/11/ 12/13 MILCON projects | 8755000 | 8755000 | 8755000
2021-05-30 | 2008 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI andFY 08/09/ 10/11/12 MILCON projects | 5161000 | 5159000 | 5159000
2021-05-30 | 2009 | DoD Education Activity | Planning and Design - Military Construction | Design Efforts FY09 RCI and FY 09/10/ 11/12/13 MILCON projects | 13593000 | 13496000 | 13496000
2021-05-30 | 2015 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 6846000 | 5507025 | 5507025
2021-05-30 | 2014 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5409000 | 5409000 | 5409000
2021-05-30 | 2013 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3771000 | 3771000 | 3771000
2021-05-30 | 2009 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 5000000 | 4000000 | 4000000
2021-05-30 | 2017 | DoD Education Activity | Unspecified Minor Military Construction | Unspecified Minor Construction for projects < $2.M | 3000000 | 1107975 | 1107975
2021-05-11 | 2021 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
2021-05-11 | 2020 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 16856000 | 0 | 0
2021-05-11 | 2019 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 16638000 | 5870000 | 0
2021-05-11 | 2018 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 9377000 | 9377000 | 0
2021-05-11 | 2017 | Marine Corps Active | Improvements - Military Family Housing | Military Family Housing Improvement | 2655000 | 2655000 | 0
2021-05-11 | 2020 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 3017000 | 0 | 0
2021-05-11 | 2021 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 2726000 | 0 | 0
2021-05-11 | 2019 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 988000 | 238000 | 0
2021-05-11 | 2018 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 201000 | 201000 | 11000
2021-05-11 | 2017 | Marine Corps Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 0 | 0 | 0
2021-04-30 | 2019 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY20-21 MILCON Projects | 6184000 | 5908445 | 1827584
2021-04-30 | 2017 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY18-19 MILCON Projects | 15000000 | 14817642 | 12306135
2021-04-30 | 2020 | Missile Defense Agency | Planning and Design - Military Construction | Design MDA FY21-23 MILCON Projects | 35472000 | 3447236 | 737968
2021-04-30 | 2018 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY18/19 | 344000 | 272085 | 243567
2021-04-30 | 2019 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY19/20 | 10000000 | 0 | 0
2021-04-30 | 2021 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY21/22 | 4922000 | 0 | 0
2021-04-30 | 2020 | Missile Defense Agency | Unspecified Minor Military Construction | Used for accomplishing urgent unforeseen construction projects in FY19/20 | 10000000 | 0 | 0
2021-04-30 | 2021 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 2, Incr. 3) | 119000000 | 106000000 | 0
2021-04-30 | 2020 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 2, Incr. 2) | 218800000 | 218800000 | 0
2021-04-30 | 2019 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 1, Incr. 2 & Ph. 2, Incr. 1) | 291000000 | 291000000 | 92934124
2021-04-30 | 2018 | National Geospatial-Intelligence Agency | Construction - Major Military Construction | Design-Build Project (Next NGA West (N2W) Complex, Ph. 1, Incr. 1); Small Business Project for IPO temporary facility | 200000000 | 200000000 | 98948876
2021-04-30 | 2021 | National Security Agency | Construction - Major Military Construction | ECB3, Mission Support Compound | 251589780 | 241038603 | 0
2021-04-30 | 2017 | National Security Agency | Construction - Major Military Construction | Feeders Ph. 3, ECB2, Access Control Facility | 243533714 | 238515701 | 216224061
2021-04-30 | 2012 | National Security Agency | Construction - Major Military Construction | Mountainview, Whitelaw Wedge, HPCC2, ICECUBE, ECB1, HPCC1, MHS Generator Plant | 333439089 | 333411359 | 331999386
2021-04-30 | 2013 | National Security Agency | Construction - Major Military Construction | MOD II, VCP1, Mountainview, HPCC2, ICECUBE, ECB1, HPCC1 | 510067383 | 506627864 | 504252864
2021-04-30 | 2014 | National Security Agency | Construction - Major Military Construction | HPCC2, ECB1 | 511998526 | 511997906 | 511298932
2021-04-30 | 2015 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - North, VCP1, NSAW Feeders - Central, ECB1, Access Control Facility | 99728000 | 96737553 | 96479560
2021-04-30 | 2016 | National Security Agency | Construction - Major Military Construction | NSAW Feeders - Central, ECB2 | 67764547 | 67429087 | 67096776
2021-04-30 | 2018 | National Security Agency | Construction - Major Military Construction | ECB2, EE Infra Construction | 318424461 | 318423202 | 300107160
2021-04-30 | 2019 | National Security Agency | Construction - Major Military Construction | ECB2, ECB3 | 407000000 | 404129788 | 234628265
2021-04-30 | 2020 | National Security Agency | Construction - Major Military Construction | ECB3, Mission Support Compound | 478000000 | 421366498 | 63785946
2021-04-30 | 2012 | National Security Agency | Planning and Design - Military Construction | General P&D | 23800910 | 23297538 | 21172538
2021-04-30 | 2018 | National Security Agency | Planning and Design - Military Construction | General P&D | 20000000 | 19796830 | 13563826
2021-04-30 | 2021 | National Security Agency | Planning and Design - Military Construction | General P&D | 10303000 | 0 | 0
2021-04-30 | 2013 | National Security Agency | Planning and Design - Military Construction | General P&D | 3823616 | 3255628 | 3255628
2021-04-30 | 2020 | National Security Agency | Planning and Design - Military Construction | General P&D | 15000000 | 11477759 | 6123711
2021-04-30 | 2014 | National Security Agency | Planning and Design - Military Construction | General P&D | 13161473 | 12667680 | 12087585
2021-04-30 | 2015 | National Security Agency | Planning and Design - Military Construction | General P&D | 599000 | 591520 | 591520
2021-04-30 | 2016 | National Security Agency | Planning and Design - Military Construction | General P&D | 1078000 | 1077928 | 1077928
2021-04-30 | 2017 | National Security Agency | Planning and Design - Military Construction | General P&D | 13180000 | 13126406 | 12976535
2021-04-30 | 2021 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 0 | 0 | 0
2021-04-30 | 2020 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3228000 | 0 | 0
2021-04-30 | 2015 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 4229000 | 3873686 | 3873686
2021-04-30 | 2014 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 1500000 | 1493362 | 1493362
2021-04-30 | 2013 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 3530000 | 3353911 | 3353911
2021-04-30 | 2018 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 2254000 | 2202264 | 2202264
2021-04-30 | 2017 | National Security Agency | Unspecified Minor Military Construction | General UMMC | 26085 | 26085 | 26085
2021-05-11 | 2021 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 37043000 | 12415000 | 0
2021-05-11 | 2020 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 24942000 | 24771000 | 0
2021-05-11 | 2019 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 0 | 0 | 0
2021-05-11 | 2017 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 6854000 | 6624000 | 1498000
2021-05-11 | 2018 | Navy Active | Improvements - Military Family Housing | Military Family Housing Improvement | 26874000 | 15332000 | 1477000
2021-05-11 | 2020 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 328035000 | 170749000 | 132853000
2021-05-11 | 2021 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 272500000 | 88854000 | 33695000
2021-05-11 | 2017 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 141936000 | 140522000 | 137959000
2021-05-11 | 2018 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 276981000 | 236681000 | 222032000
2021-05-11 | 2019 | Navy Active | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 257005000 | 199771000 | 172564000
2021-05-11 | 2017 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 2929000 | 2929000 | 2582000
2021-05-11 | 2020 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 2846000 | 0 | 0
2021-05-11 | 2019 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 3514000 | 0 | 0
2021-05-11 | 2018 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 2303000 | 265000 | 104000
2021-05-11 | 2021 | Navy Active | Planning and Design - Military Family Housing | Family Housing Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 3128000 | 0 | 0
2021-05-11 | 2017 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 29790000 | 28874000 | 26467000
2021-05-11 | 2019 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 28579000 | 17283000 | 11454000
2021-05-11 | 2020 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 81237000 | 23111000 | 5189000
2021-05-11 | 2021 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 38983000 | 0 | 0
2021-05-11 | 2018 | Navy Active | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 33842000 | 31112000 | 25036000
2021-05-11 | 2017 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY18 MILCON; design of FY17 Congressional Inserts; start design of FY19 MILCON; fund Congressionally directed designs | 3783000 | 2817000 | 2746000
2021-05-11 | 2018 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY19 MILCON; design of FY18 Congressional Inserts; start design of FY20 MILCON; fund Congressionally directed designs | 21907000 | 21896000 | 17984000
2021-05-11 | 2019 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY20 MILCON; design of FY19 Congressional Inserts; start design of FY21 MILCON; fund Congressionally directed designs | 4695000 | 3629000 | 3134000
2021-05-11 | 2020 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY21 MILCON; design of FY20 Congressional Inserts; start design of FY22 MILCON; fund Congressionally directed designs | 4780000 | 0 | 0
2021-05-11 | 2021 | Navy Reserve | Planning and Design - Military Construction | Navy and Marine Corps MCON: Complete design of FY22 MILCON; design of FY21 Congressional Inserts; start design of FY23 MILCON; fund Congressionally directed designs | 3485000 | 0 | 0
2021-05-11 | 2017 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 0 | 0 | 0
2021-05-11 | 2018 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 11504000 | 11389000 | 3989000
2021-05-11 | 2019 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 3000000 | 2580000 | 251000
2021-05-11 | 2020 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 24915000 | 3470000 | 566000
2021-05-11 | 2021 | Navy Reserve | Unspecified Minor Military Construction | Unspecified Minor Construction [UMC] | 3000000 | 0 | 0
2019-09-01 | 2013 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 25454000 | 24343000 | 24343000
2020-11-30 | 2017 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 27653000 | 27653000 | 27653000
2021-03-01 | 2021 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 32624000 | 1882000 | 1882000
2020-11-30 | 2020 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 52532000 | 52522184 | 52522184
2020-11-30 | 2019 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 55925000 | 55867712 | 55867712
2020-11-30 | 2018 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 39746000 | 39720873 | 39720973
2020-11-30 | 2016 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 31628000 | 31230197 | 31230197
2020-11-30 | 2015 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 24197000 | 22764000 | 22764000
2019-09-01 | 2014 | Special Operations Command | Planning and Design - Military Construction | MILCON Design Work | 36866000 | 34788000 | 34788000
2020-11-30 | 2017 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5994000 | 5993339 | 5993339
2021-03-01 | 2021 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 17698000 | 0 | 0
2020-11-30 | 2016 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 15676000 | 15501297 | 15501297
2020-11-30 | 2020 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 28564000 | 11796811 | 11796811
2019-09-01 | 2013 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 9216000 | 9116000 | 9116000
2020-11-30 | 2018 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 7384000 | 7384000 | 7384000
2020-11-30 | 2014 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 5170000 | 5003000 | 5003000
2020-11-30 | 2019 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 13462000 | 13642000 | 13642000
2020-11-30 | 2015 | Special Operations Command | Unspecified Minor Military Construction | Construction Costs for UMC Projects | 10334000 | 7664000 | 7664000
2021-05-10 | 2017 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 3427000 | 3427000 | 3002157
2021-05-10 | 2018 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 1942000 | 1942000 | 1534307
2021-05-10 | 2019 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 2036000 | 898523 | 617702
2021-05-10 | 2020 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4890000 | 0 | 0
2016-09-15 | 2012 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 4870000 | 4870000 | 3922831
2021-04-08 | 2016 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 3041000 | 3040223 | 2907925
2017-09-21 | 2013 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 7508000 | 7508000 | 2860637
2019-12-04 | 2014 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 3915266 | 3915105 | 2431365
2019-12-04 | 2015 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 677000 | 677000 | 548258
2021-05-10 | 2021 | Washington Headquarters Services | Planning and Design - Military Construction | Planning and Design | 0 | 0 | 0