## PROJECTS
Data as of Date | Fiscal Year | Component | Construction Project Type | State | Country | Project Number | Project Title | Parent Project Number [Initial Appropriation] | Solicitation Date | Award Date | Prime Contract Recipient (Company Name) | Prime Contract Number | Original Contract Amount ($000) | Current Contract Obligation ($000) | Start Date | Placed-In-Service Date | Original Completion Date | Current Completion Date | Percent Complete | Diverted Funds Amount ($000) | Diverted Funds Recipient Project | Remarks
12/05/2014 | 2006 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR064009 | Improve Family Housing, Ph C |  | 2007-08-01 | 2007-12-06 | Bilfinger Berger | C 04-1006BB | 1801.8135 | 1893.4955 | 2007-12-17 |  | 2008-07-13 | 2013-02-22 | 99%
12/05/2014 | [8 empty] | 2007-08-01 | 2007-12-06 | OBG | C 04-1006OBG | 1118.3451 | 1171.5011 | 2007-12-17 |  | 2007-12-06 | 2013-02-22
12/05/2014 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALDA053001B | Multi-Aircraft Maintenance Hanger |  | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 15238.069 | 16847.5048 | 2011-03-01 |  | 2011-10-11 | 2015-07-31 | 99%
12/05/2014 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALUA073008A | Facility Replacements |  | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244.838 | 28675.3487 | 2011-03-01 |  | 2011-10-11 | 2015-01-15 | 99%
12/05/2014 | 2008 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR084014 | Improve Family Housing, Ph E |  | 2012-08-21 | 2013-05-17 | MICKAN | C07-1003 | 4638.8202 | 5011.6997 | 2013-07-08 |  | 2014-05-02 | 2014-12-31 | 85%
12/05/2014 | 2008 | Air Force Active | Military Family Housing Improvement |  | TURKEY | LJYC084001 | Improve Family Housing 515 Units |  | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970.0225 | 42315.6545 | 2012-03-08 |  | 2012-08-15 | 2015-07-19 | 37%
12/05/2014 | 2009 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS093002 | CNS Addition To Child Development Center (Cdc) B8210 |  | 2009-07-14 | 2009-08-31 | MAPCO, Inc. | W9126G09D00340002 | 5913.251 | 6604.8908 | 2009-10-15 | 2012-11-27 | 2011-02-27 | 2014-12-30 | 95%
12/05/2014 | [8 empty] | 2013-04-15 | 2013-06-15 | JSR | FA301612D00050008 | 366.5141 | 366.5141 | 2013-07-15 |  | 2013-12-27 | 2014-12-30
12/05/2014 | 2009 | Air Force Active | Unspecified Minor Military Construction |  | TURKEY | AKNR041053 | CNS Replace Asf Admin Bldg 2621 |  | 2011-02-22 | 2011-09-23 | MATOC Contractor | W912GB09D00690007 | 1367.06 | 1367.06 | 2012-02-15 |  | 2012-09-17 | 2015-02-01 | 13%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 28616.5445 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT033003 | Consol Communications Facility |  | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248.94 | 11773.483 | 2011-01-03 | 2014-09-12 | 2013-09-20 | 2015-09-01 | 95%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD063003 | Ground Control Tower |  | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | N6274209D1186HC08 | 7379.329 | 7423.376 | 2013-02-20 |  | 2014-01-30 | 2015-01-16 | 76%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF063009 | Replace Munitions Storage Area |  | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464.83 | 10753.2604 | 2011-06-23 |  | 2013-03-05 | 2015-03-09 | 89%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG081001 | Land Acquisition North & South Boundaries |  | 2012-05-09 | 2012-09-12 | In-House Work Force-NWK | PN-329217-LAWAFB | 3474.5 | 3474.5 | 2012-09-12 |  | 2014-03-06 | 2014-12-17 | 85%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | MONTANA | UNITED STATES | NZAS003000A | Upgrade Weapons Storage Area |  | 2012-04-23 | 2012-11-28 | RSCI | W912DW13C0013 | 9474.72 | 9462.564 | 2013-12-09 |  | 2014-10-19 | 2015-02-28 | 57%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | XTLF033303 | Control Tower |  | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849.633 | 9518.0403 | 2010-10-05 |  | 2012-01-11 | 2015-06-04 | 89%
12/05/2014 | 2010 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R2 | Recruit Dormitory 2, Phase 2 |  | 2009-12-23 | 2010-04-20 | M&H Enterprises, dba Martin-Harris Construction | W9126G10C0021 | 41573.312 | 52088.9967 | 2010-05-20 | 2013-04-10 | 2012-05-23 | 2014-12-30 | 99%
12/05/2014 | [8 empty] | 2010-10-29 | 2011-01-28 | Federal Pogram Integrators, LLC with JSR Inc. | W9126G11C0009 | 6662.534 | 7474.996 | 2011-02-28 |  | 2012-12-29 | 2014-12-30
12/05/2014 | [8 empty] | 2012-02-15 | 2012-02-15 | American Eagle Protective Services Corp. | W9126G12C00170001 | 97.8389 | 86.71 | 2012-03-01 |  | 2013-01-31 | 2014-12-30
12/05/2014 | [8 empty] | 2013-06-18 | 2013-08-12 | JSR Incorporated | FA304713D00130003B | 227.6075 | 234.4318 | 2013-09-12 |  | 2014-12-31 | 2014-12-30
12/05/2014 | [8 empty] | 2013-08-28 | 2013-08-29 | JSR Incorporated | W9126G12D00180022 | 98.6814 | 98.6814 | 2013-09-29 |  | 2014-01-25 | 2014-12-30
12/05/2014 | 2010 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility |  | 2009-11-19 | 2010-02-11 | Lyda Swinerton Builders, Inc. | W9126G10C0017 | 23483.61 | 25785.2822 | 2010-02-11 | 2012-10-31 | 2011-12-26 | 2015-09-30 | 99%
12/05/2014 | [8 empty] | 2010-05-14 | 2010-06-11 | Federal Pogram Integrators, LLC - JSR Inc. | W9126G10C0072 | 1409.452 | 1601.6059 | 2010-06-11 |  | 2011-06-03 | 2015-09-30
12/05/2014 | [8 empty] | 2009-12-10 | 2014-09-29 | COE JOC Gideon Cntrg (Handrails/Screening Retrofit) | W9126G14D00570016 | 60.931 | 60.931 |  |  | 2014-09-29 | 2015-09-30
12/05/2014 | [8 empty] | 2014-09-29 | 2014-09-30 | Gideon Contracting, LLC | W9126G12C0024 | 60.931 | 60.931 | 2014-09-30 |  | 2015-09-29 | 2015-09-30
12/05/2014 | 2010 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | MUHJ053008 | West & Lasalle Gates Force Protection/Access |  | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185.824 | 8498.0821 | 2010-07-07 | 2013-07-19 | 2011-12-17 | 2015-09-03 | 99%
12/05/2014 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006A | Blatchford-Preston Complex Ph II |  | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | W912ER11C0001 | 35758.85 | 37149.4231 | 2011-01-21 |  | 2013-02-03 | 2014-12-15 | 95%
12/05/2014 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA103001 | Construct Network Control Center |  | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | W912ER12C0028 | 2579.93 | 3160.1562 | 2012-08-19 |  | 2013-09-08 | 2014-12-15 | 76%
12/05/2014 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA107000 | Coalition Compound Billeting |  | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272.835 | 44968.0368 | 2012-06-05 |  | 2014-03-17 | 2015-03-16 | 76%
12/05/2014 | 2010 | Air Force Active | Major Military Construction |  | TURKEY | LJYC003006 | Consolidated Community Center |  | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | W912GB09D00690003 | 7880.644 | 8179.6972 | 2013-01-15 |  | 2011-09-22 | 2015-01-04 | 46%
12/05/2014 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100031 | Construct Maintenance Operations Center And Command Post |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671.642 | 1986.1406 | 2011-09-19 |  | 2012-01-31 | 2015-07-20 | 93%
12/05/2014 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100120 | Construct SatCom Facility |  | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136.701 | 1184.0301 | 2011-09-19 |  | 2011-01-31 | 2015-07-20 | 93%
12/05/2014 | 2010 | Air Force Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | XDAT073008 | Construct Military Working Dog & Supporting Facility |  | 2011-07-25 | 2011-09-28 | IE PACIFIC INC | N62473-07-D-2008 | 1620 | 1620 | 2012-02-27 | 2013-02-21 | 2012-09-27 | 2013-02-22 | 99%
12/05/2014 | [8 empty] | 2014-07-18 | 2014-07-18 | CREW MW | FA442710D01022058 | 71.771 | 71.771 | 2014-07-18 |  | 2014-09-16 | 2013-02-22
12/05/2014 | 2010 | Air National Guard | Major Military Construction | COLORADO | UNITED STATES | CRWU019119 | ADAL Weapon Release Facility |  | 2010-05-28 | 2010-09-23 | Tower One Construction Company | W912LC10C0001 | 3.025 | 3.649 | 2010-10-27 | 2012-02-09 | 2011-08-23 | 2014-05-26 | 99%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | KANSAS | UNITED STATES | PRQE089032 | TFI - Upgrade DCGS Facilities |  | 2010-05-11 | 2010-08-04 | Key Construction Company | W912JC10C0004 | 8.223 | 9.068 | 2010-08-16 | 2011-11-21 | 2011-08-16 | 2013-11-01 | 99%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | MAINE | UNITED STATES | FKNN089019 | Replace Aircraft Maintenance Hangar and Shops |  | 2009-09-29 | 2010-05-12 | Sheridan Corp | W912JD10C0001 | 15.064 | 17.786 | 2010-11-05 | 2012-08-01 | 2012-11-24 | 2013-03-28 | 98% | 2200 | KNMD109501;
12/05/2014 | 2010 | Air National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | SPBN019136 | Replace Ops and Training /ADAL DGS |  | 2010-07-16 | 2010-09-27 | P&S Construction | W912SV10R0040 | 2.487 | 3.12 | 2010-11-01 | 2013-06-17 | 2011-10-27 | 2013-07-31 | 50%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | JTVE099057 | Force Protection Measures - Relocate Base Entrance |  | 2012-08-15 | 2012-09-27 | Gottfried Contracting | W9127Q09D00090005 | 3.823 | 4.11 | 2012-10-10 | 2014-06-30 | 2013-06-24 | 2014-06-30 | 56%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | MISSOURI | UNITED STATES | ULYB099003 | Add to Fire Station |  | 2009-09-23 | 2009-09-23 | Lee Grover Construction | W912NS1022102 | 0.293 | 0.358 | 2009-09-23 | 2014-04-30 | 2012-08-29 | 2014-05-30 | 99%
12/05/2014 | [8 empty] | 2010-03-01 | 2010-07-25 | Lee Grover Constrution | W912NS08D00100014 | 5.709 | 6.678 | 2010-08-04 |  | 2011-07-30 | 2014-05-30
12/05/2014 | 2010 | Air National Guard | Major Military Construction | NEBRASKA | UNITED STATES | NGCB079069 | Joint Forces Operations Center - ANG Share |  | 2009-11-13 | 2010-02-17 | Hausmann Construction, Inc. | W912430422013 | 1.306 | 1.5 | 2010-02-18 | 2012-09-17 | 2011-09-16 | 2012-09-17 | 98% |  |  | This projects uses a state contract executed through a Military Construction Cooperative Agreement (MCCA).
12/05/2014 | 2010 | Air National Guard | Major Military Construction | NEVADA | UNITED STATES | UCTL919637 | Replace Fire Station |  | 2010-07-27 | 2010-09-07 | Gilbane Building Company | W9124X10C0003 | 9.263 | 10.246 | 2010-09-23 | 2011-12-25 | 2012-03-21 | 2012-09-30 | 99%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | SZCQ089023 | Replace Squadron Operations Facilities |  | 2011-03-09 | 2011-09-19 | NUTMEG Companies, Inc. | W912TF11C0503 | 10.752 | 11.906 | 2011-10-24 | 2013-11-13 | 2013-02-15 | 2014-03-14 | 98%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | NEW YORK | UNITED STATES | FPBB069168 | Reaper LRE Beddown |  | 2012-07-27 | 2012-10-17 | Black Horse Group | W912PQ12D00130003 | 3.155 | 3.252 | 2012-10-17 | 2014-06-16 | 2013-11-11 | 2014-06-16 | 99%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | TENNESSEE | UNITED STATES | PYKL009136 | Base Civil Engineer Maintenance and Training Facilities |  | 2010-07-14 | 2010-09-21 | Chris Wood Construction Co, Inc. | W912L710C0017 | 6.069 | 7.366 | 2010-10-19 | 2012-10-31 | 2012-10-18 | 2014-06-30 | 98%
12/05/2014 | 2010 | Air National Guard | Major Military Construction | WYOMING | UNITED STATES | DPEZ019148A | Add to Squadron Operations |  | 2011-02-04 | 2011-06-02 | Various Contractors | W912L311F00200000 | 0.975 | 1.303 | 2011-06-02 | 2011-08-01 | 2011-11-28 | 2014-01-31 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | ALASKA | UNITED STATES | FTQW009192 | Add to Communications Training Facility |  | 2012-11-07 | 2012-12-27 | G2 Construction | W91ZRU10D00150003 | 1.448 | 1.695 | 2013-01-24 | 2014-02-19 | 2014-01-24 | 2014-06-30 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | CYQL099005 | DRBS Storage Facility |  | 2012-10-01 | 2013-02-11 | Sweat, LLC | W911YN13C0001 | 1.143 | 1.143 | 2013-02-11 | 2014-05-15 | 2013-11-08 | 2014-02-15 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | XDQU109096 | CRTC Squadron Operation Addition |  | 2012-11-13 | 2012-12-27 | Holland and Holland, Inc. | W912JM10D00010005 | 1.209 | 1.363 | 2013-01-17 | 2014-01-31 | 2014-01-17 | 2014-07-31 | 98%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | IOWA | UNITED STATES | VSSB069014 | Add To Security Forces Facility |  | 2013-06-19 | 2013-08-05 | H&R Construction | W912LP12D00010002 | 1.304 | 1.377 | 2013-08-15 | 2014-02-19 | 2013-08-15 | 2014-06-04 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | PJMS119034 | A10 Flight Simulator Facility |  | 2012-11-01 | 2013-01-08 | SAF, Inc. | W912K612R2016 | 1.818 | 1.994 | 2013-01-24 | 2014-06-04 | 2014-03-26 | 2014-06-30 | 94%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | MXRD089075 | Joint Forces Operations Center- ANG Share |  | 2010-02-10 | 2010-05-27 | CTA Constr | W912SV10C0101 | 1.5 | 1.5 | 2010-05-27 | 2012-10-01 | 2010-05-27 | 2011-11-29 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | MICHIGAN | UNITED STATES | TDVG072909A | Replace Classroom Training Facilities |  | 2012-11-15 | 2012-12-27 | Meridan Contracting Services, LLC | W912JB09D20030013 | 1.437 | 1.608 | 2013-03-25 | 2014-01-10 | 2013-08-24 | 2014-04-10 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | NEBRASKA | UNITED STATES | NGCB109082 | Alter Base Entry Complex |  | 2012-10-30 | 2012-12-27 | American Contracting, LLC | W9124313B00010002 | 1.297 | 1.404 | 2013-01-23 | 2014-02-23 | 2014-01-23 | 2014-02-24 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | TWLR099087 | C-130 Parking Apron |  | 2013-04-08 | 2013-11-01 | TRAC Builders | W912LD11D00250004 | 1.6 | 1.688 | 2013-12-12 | 2014-09-11 | 2013-12-12 | 2014-09-11 | 42%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | TENNESSEE | UNITED STATES | BKTZ139025 | Convert RPA Interim SCIF, B720 |  | 2013-05-08 | 2013-06-20 | Codell Construction Company | W912L710D00060021 | 1.651 | 1.811 | 2013-07-01 | 2014-04-28 | 2014-04-16 | 2014-06-13 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | DDPM109901 | Add to Civil Engineering Facility |  | 2012-08-19 | 2012-11-21 | Triune-Beck JV | W912L111d00120200 | 1.479 | 1.544 | 2013-02-12 | 2014-06-13 | 2014-06-03 | 2014-06-13 | 90%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | DDPM119026 | Multi Use Training Facility |  | 2012-08-19 | 2012-11-21 | Tribune-Beck JV | W912L111d00120043 | 1.697 | 1.785 | 2013-02-12 | 2014-06-13 | 2013-11-30 | 2014-06-13 | 90%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | KELL099067 | F-16 Mission Training Center (Flight Sim) Facility |  | 2010-05-13 | 2011-09-28 | HJD Capital Electric, Inc | W912L111C0033 | 1.578 | 1.685 | 2011-09-30 | 2013-02-28 | 2012-09-29 | 2013-02-28 | 99%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | FPBD109001 | Add to Vehicle Maintenance Facility |  | 2013-06-05 | 2013-12-26 | Mirador Enterprise, Inc | W912L111D00090008 | 1.4 | 1.45 | 2014-01-06 |  | 2015-01-06 | 2015-01-25 | 22%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | LYBH079028 | BCE Pavements and Grounds Facility |  | 2013-02-19 | 2013-06-14 | Wycliffe Enterprises, Inc | W912L812D00080002 | 0.899 | 0.93 | 2013-07-09 | 2014-05-30 | 2014-04-05 | 2014-05-30 | 43%
12/05/2014 | 2010 | Air National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | LYBH119145 | Convert Hangar 107 for Aeromedical Relocation |  | 2013-07-02 | 2013-09-03 | Wycliffe Inc | W912L812D00080003 | 1.743 | 1.826 | 2013-09-16 | 2014-07-31 | 2014-10-03 | 2014-08-15 | 46%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083008 | Repair Central Heat And Power Plant Boiler |  | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 30243.0655 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV063501 | AMARG Hangar |  | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282.136 | 23098.357 | 2011-09-12 | 2014-08-22 | 2013-07-17 | 2015-01-30 | 95%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV113002 | HC-130J Aerial Cargo Facility |  | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223 | 7526.036 | 2011-11-09 | 2014-08-12 | 2013-03-14 | 2015-01-23 | 96% | 2000 | YWHG111005;
12/05/2014 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093000 | F-35 Academic Training Center |  | 2012-04-18 | 2012-08-30 | Archer Western Contractors | W912PL12C0017 | 43347.122 | 46730.2939 | 2012-11-05 |  | 2014-01-31 | 2014-12-31 | 99%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093001 | F-35 Squadron Ops Facility |  | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | W912PL12C0027 | 9108.814 | 9246.9817 | 2012-10-09 | 2014-01-06 | 2013-09-10 | 2015-01-30 | 99%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | COLORADO | UNITED STATES | XQPZ084017 | Const Center For Character & Leadership Development |  | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995.5 | 25002.256 | 2013-01-15 |  | 2014-06-12 | 2015-04-30 | 65%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | SXHT053001 | Air Force Technical Applications Center |  | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231.0449 | 146030.7225 | 2011-07-06 | 2014-03-03 | 2015-12-02 | 2015-12-02 | 98%
12/05/2014 | [8 empty] | 2013-09-27 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99.768 | 99.768 | 2014-02-13 |  | 2014-08-02 | 2015-12-02
12/05/2014 | 2011 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB025502 | Weapons Load Crew Training Facility |  | 2010-10-22 | 2011-08-03 | Pacific - Tech - Sauer JV | N6945011C1754 | 14996 | 16332.5158 | 2011-08-03 | 2014-08-28 | 2013-01-24 | 2014-12-30 | 99%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC113102 | UAS Airfield Fire/Crash Rescue Station |  | 2010-12-10 | 2011-06-29 | Jaynes Corporation | W912PL11C0004 | 7345.225 | 7423.225 | 2012-06-15 | 2014-09-30 | 2013-06-18 | 2014-11-25 | 99%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX913001P1 | Civil Engineer Complex (TFI) - Phase 1 |  | 2011-01-20 | 2011-06-03 | Sauer, Inc. | N6945009D12740008 | 11649 | 12333.8989 | 2011-06-03 |  | 2012-12-10 | 2014-03-13 | 95%
12/05/2014 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R3 | Recruit Dormitories Phase 3 |  | 2010-12-06 | 2011-09-20 | Satterfield & Pontikes Const Inc. | W9126G11C0024 | 45885.001 | 46354.6403 | 2011-09-20 |  | 2013-10-31 | 2014-12-30 | 98% | 4894 | KRSM103011;
12/05/2014 | [8 empty] | 2011-09-02 | 2011-11-08 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 95.464 | 95.464 | 2011-11-08 |  | 2011-12-08 | 2014-12-30
12/05/2014 | [8 empty] | 2012-05-09 | 2012-05-29 | Raba-Kistner Consultants | PNASA1205700 | 1.8889 | 1.8889 | 2012-05-29 |  | 2012-06-09 | 2014-12-30
12/05/2014 | [8 empty] | 2012-05-09 | 2012-08-09 | Federal Pogram Integrators, LLC - JSR Inc. | W912BV11C0038 | 6886.921 | 7267.8431 | 2012-08-09 |  | 2014-04-04 | 2014-12-30
12/05/2014 | [8 empty] | 2012-09-06 | 2012-10-19 | Federal Program Integrators, LLC with JSR Inc. | W9126G11C0009 | 175.3584 | 175.3584 | 2012-10-19 |  | 2013-06-01 | 2014-12-30
12/05/2014 | [8 empty] | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06 | 2014-12-30
12/05/2014 | [8 empty] | 2012-02-15 | 2014-06-25 | American Eagle Protective Services Corp. | W9126G12C0017P0002 | 97.8954 | 97.8954 | 2014-06-25 |  | 2015-01-31 | 2014-12-30
12/05/2014 | [8 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00190007 | 1792.428 | 1792.428 | 2014-10-10 |  | 2015-09-05 | 2014-12-30
12/05/2014 | [8 empty] | 2010-12-06 | 2014-11-10 | AE Merrick & Company-Tittle 2 Svs $59,036x3 | W9126G08D00060053 | 177.1085 | 177.1085 |  |  | 2014-11-10 | 2014-12-30
12/05/2014 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 |  | 2011-02-25 | 2011-06-30 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 25985.138 | 27504.8574 | 2011-09-05 |  | 2013-04-20 | 2015-01-15 | 97%
12/05/2014 | [8 empty] | 2011-03-07 | 2011-07-08 | LB-KBR General Contract | 1234567890 | 25985.138 | 25985.138 |  |  | 2013-06-27 | 2015-01-15
12/05/2014 | [8 empty] | 2011-03-07 | 2012-10-31 | Merrick & Company (Tittle II Services) $59,036.40 | W9126G08D00060054 | 0 | 0 |  |  | 2012-10-31 | 2015-01-15
12/05/2014 | [8 empty] | 2012-12-12 | 2013-06-03 | Federal Pogram Integrators, LLC - JSR Inc. | W9126G13C0098 | 334.244 | 152.927 | 2013-06-03 |  | 2014-01-18 | 2015-01-15
12/05/2014 | [8 empty] | 2012-02-15 | 2014-01-16 | American Eagle Protective Services Corporation | W9126G12C00170001 | 97.8954 | 202.0082 | 2014-01-16 |  | 2015-01-31 | 2015-01-15
12/05/2014 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS093737V | BMT Visitors Reception Center |  | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | F48903-06-R-9991-R | 21500.479 | 21500.479 |  |  | 2013-09-22 | 2014-12-28 | 97%
12/05/2014 | [8 empty] | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | FA890306D85110085 | 21500.479 | 21664.63 | 2012-09-19 |  | 2013-09-22 | 2014-12-28
12/05/2014 | [8 empty] | 2011-05-09 | 2014-05-01 | Merrick's & Company-Redesign Parking $31,364.14+$19,435.86 | F48 | 50.8 | 50.8 |  |  | 2014-05-31 | 2014-12-28
12/05/2014 | [8 empty] | 2014-08-14 | 2014-11-10 | Red Cedar Enterprises, Inc. | W9126G14D00190007 | 498.711 | 498.711 | 2014-12-10 |  | 2015-02-10 | 2014-12-28
12/05/2014 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR083001 | Deicing Fluid Storage & Dispensing Facility |  | 2012-05-10 | 2011-09-02 | LBB | W912GB10C0001 | 2671 | 2783.6637 | 2012-11-13 |  | 2012-12-25 | 2015-08-31 | 96% | 155 | KRSM103011; | Removed for contract correction
12/05/2014 | [8 empty] | 2012-05-10 | 2012-09-26 | Peter Gross GmbH | W912GB-10-C-0001A | -530.298 | -530.298 | 2012-11-13 |  | 2013-04-14 | 2015-08-31
12/05/2014 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFR123063 | C-130J Flight Simulator Facility |  | 2013-08-12 | 2011-09-02 | LBB (EBC AWD) | W912GB-10-C-002EB | 7112.8996 | 7280.7879 | 2014-01-06 |  | 2011-09-02 | 2015-01-29 | 83% |  |  | Removed for contract correction
12/05/2014 | [8 empty] | 2013-08-12 | 2013-11-13 | OBG Hochbau GmbH & Co. KG | W912GB10C0002 | -949.3042 | -949.3042 | 2014-01-06 |  | 2014-10-23 | 2015-01-29
12/05/2014 | 2011 | Air Force Active | Major Military Construction |  | GERMANY | TYFU083507R2 | Dormitory (128 Rm) |  | 2013-08-30 | 2011-09-16 | LBB (EBC AWD) | W | 17945 | 17945 | 2014-06-16 |  | 2013-09-05 | 2015-11-12 | 9% |  |  | Removed for contract correction
12/05/2014 | [8 empty] | 2013-08-30 | 2014-04-24 | Wolff & Muller Gov Serv GmbH Wolff & Muller Regionalbau | W912GB10C0009 | -1693.1044 | -1693.1044 | 2014-06-16 |  | 2015-05-29 | 2015-11-12
12/05/2014 | 2011 | Air Force Active | Major Military Construction |  | ITALY | ASHE083011 | Air Support Operations Squadron (ASOS) Facility |  | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N33191-07-D-0211 | 7174.1698 | 7895.7036 | 2011-12-16 |  | 2013-06-20 | 2014-09-15 | 65% | 1453 | KRSM103011;
12/05/2014 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006B | Blatchford-Preston Complex, Phase III |  | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177.236 | 34649.116 | 2012-09-27 |  | 2014-05-15 | 2015-09-30 | 39%
12/05/2014 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility |  | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | W912ER11D00010007 | 40848 | 40848 | 2013-08-07 |  | 2015-08-30 | 2015-09-16 | 1%
12/05/2014 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA113001 | Theater Communications Facility |  | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912.5671 | 10408.1954 | 2012-06-01 |  | 2014-04-02 | 2015-09-30 | 57%
12/05/2014 | 2011 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ114127 | Improve Family Housing, Ph 11 |  | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621.7601 | 65174.5107 | 2012-10-24 |  | 2015-08-27 | 2015-11-08 | 73%
12/05/2014 | [8 empty] | 2011-05-09 | 2012-03-19 | OTIE Milwauke, WI; *Title 2 Contract support* | FA890308D878200014 | 1896.559 | 1896.559 |  |  | 2012-03-19 | 2015-11-08
12/05/2014 | [8 empty] | 2011-05-09 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan) *ArchTestDigs* | FA5270-12-P-0058 | 50.1855 | 50.1855 | 2012-10-24 |  | 2012-07-01 | 2015-11-08
12/05/2014 | [8 empty] | 2011-05-09 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT* | FA5270-12-P-0080 | 72.2669 | 72.2669 | 2012-10-24 |  | 2012-07-31 | 2015-11-08
12/05/2014 | [8 empty] | 2011-05-09 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | FA5270-12-FA-045 | 319.4136 | 319.4136 | 2012-10-24 |  | 2012-09-12 | 2015-11-08
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR106261 | PL-1 Security Measures For Communications Compound |  | 2013-09-17 | 2013-11-13 | Mikan | C11-4014 | 1840.2888 | 1840.2888 | 2014-01-22 |  | 2014-08-10 | 2015-01-30 | 21%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | VYHK113003 | Catch Basin For Waste Water Treatment |  | 2012-04-16 | 2012-07-31 | UVB BITBURG | 113003 | 1762.2 | 1762.2 | 2012-10-01 |  | 2013-03-28 | 2014-10-30 | 90%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA110032 | Fuel Truck Parking |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730.623 | 1730.623 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113002 | Fuels Laboratory |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557.438 | 1557.438 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113005 | C-17 Spare Parts Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572.399 | 1572.399 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113006 | High Mast Lighting |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573.056 | 1573.056 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113009 | Entry Control Point |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615.612 | 615.612 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113010 | Cryogenics Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216.4 | 1216.4 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113012 | ELRS Storage Facility |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615.533 | 1615.533 | 2013-08-15 |  | 2014-11-08 | 2016-02-29 | 42%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120037 | Clinic |  | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhab,i UAE) | W912BU13C0060 | 1514.583 | 1514.583 | 2014-09-29 |  | 2015-01-20 | 2015-06-02 | 5%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120057 | Fire Protection Water Storage |  | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120.38 | 1120.38 | 2014-09-15 |  | 2014-11-24 | 2015-03-25 | 25%
12/05/2014 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF124001 | EOD Facility |  | 2013-07-18 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1044.893 | 1044.893 | 2014-08-08 |  | 2015-08-14 | 2015-12-03 | 2% |  |  | Original contract terminated for default
12/05/2014 | 2011 | Air National Guard | Major Military Construction | ALABAMA | UNITED STATES | FAKZ959574 | Fuel Cell and Corrosion Control Hangar |  | 2011-03-15 | 2011-07-22 | Lord and Son Constrution, Inc | W912JA11C0005 | 7.249 | 7.783 | 2011-10-12 | 2013-11-01 | 2013-01-22 | 2014-04-30 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | ARIZONA | UNITED STATES | HFHA069130 | TFI - Predator LRE Beddown |  | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | W912L213C0001 | 9.434 | 10.25 | 2013-04-08 | 2014-07-02 | 2014-06-02 | 2014-06-02 | 62%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | DELAWARE | UNITED STATES | JLWS079103 | Joint Forces Operations Center - ANG Share |  | 2011-06-29 | 2011-09-16 | Vigil Contracting, Inc. | W912L511B0001 | 1.134 | 1.164 | 2011-12-12 | 2014-01-31 | 2013-06-09 | 2014-01-31 | 98%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | FLORIDA | UNITED STATES | LSGA029009A | Security Forces Training Facility |  | 2010-11-12 | 2011-06-06 | Americaan Patriot Construction -IMC, LLC | W911YN11C0003 | 3.909 | 4.2 | 2011-08-05 | 2013-04-08 | 2012-12-03 | 2014-08-29 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069209 | TFI - F-22 Hangar, Squadron Operations and AMU |  | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | W912J611C0002 | 37.11 | 43.051 | 2011-07-15 | 2014-01-10 | 2013-07-14 | 2014-04-08 | 98% | 2001 | KNMD069215;
12/05/2014 | 2011 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069215 | TFI - F-22 Upgrade Munitions Complex |  | 2012-01-11 | 2012-05-24 | Nan Inc. | W912J612C0001 | 17.142 | 20.85 | 2012-06-14 | 2014-03-14 | 2013-12-11 | 2014-03-31 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD109500 | TFI - F-22 Beddown Infrastructure Support |  | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | W912J611C0002 | 5.155 | 6.794 | 2011-08-15 | 2014-01-10 | 2013-07-14 | 2013-11-23 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | ILLINOIS | UNITED STATES | DCFT069059 | TFI - cNAF Beddown - Upgrade Facilities |  | 2010-12-15 | 2012-04-26 | JM Industrial Supply, Inc. | W91SMC12C0003 | 13.733 | 15.077 | 2012-06-01 | 2014-02-21 | 2013-03-20 | 2014-02-21 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | MARYLAND | UNITED STATES | PJMS909928 | Replace Operations and Medical Training Facility |  | 2011-08-17 | 2011-09-28 | Costello Construction of MD, Inc. | W912K611C0016 | 11.802 | 13.263 | 2012-07-20 | 2014-02-28 | 2013-10-18 | 2014-07-15 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | NEW YORK | UNITED STATES | FPBB109013 | TFI - Reaper Infrastructure Support |  | 2012-07-27 | 2012-10-17 | Black Horse Group | W912PQ12D00130003 | 2.04 | 2.196 | 2012-10-17 | 2014-06-16 | 2013-10-12 | 2014-06-16 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | NEW YORK | UNITED STATES | WHAY089079 | Base Defense Group Beddown |  | 2011-07-30 | 2011-09-23 | APS Contractors Inc | W912PQ11B00040004 | 13.401 | 14.451 | 2011-10-13 | 2014-05-15 | 2013-05-05 | 2014-06-30 | 95%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | WEFM089029 | Upgrade ASOS Facilities |  | 2011-04-19 | 2011-08-26 | DOT Construction | W9124209D00010904 | 1.66 | 1.873 | 2011-10-24 | 2013-03-25 | 2012-07-21 | 2014-06-07 | 99%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | TENNESSEE | UNITED STATES | BKTZ069078 | TFI- Renovate Intel Squadron Facilities |  | 2013-09-20 | 2013-11-21 | Codell Construction Company | W912L710D00060037 | 6.074 | 6.592 | 2013-12-02 | 2014-09-29 | 2014-10-17 | 2014-10-17 | 0%
12/05/2014 | 2011 | Air National Guard | Major Military Construction | TEXAS | UNITED STATES | FWJH069194 | TFI - Alter UAV Maintenance Hangar (Bldg 1382) |  | 2012-01-06 | 2012-06-14 | LeeTex Construction | W912L112C0012 | 5.038 | 5.938 | 2012-07-23 | 2014-07-01 | 2013-07-23 | 2014-07-01 | 93%
12/05/2014 | 2011 | Air National Guard | Unspecified Minor Military Construction | HAWAII | UNITED STATES | KNMD109032 | TFI- F-22 Beddown- Add to Communication Facility |  | 2012-01-04 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C0003 | 1.695 | 1.952 | 2012-06-17 | 2014-04-15 | 2014-06-07 | 2014-08-17 | 99%
12/05/2014 | 2011 | Air National Guard | Unspecified Minor Military Construction | WYOMING | UNITED STATES | DPEZ089083 | Relocate ROSC |  | 2011-07-18 | 2012-04-11 | Recco, Inc. | W912L312C0003 | 1.636 | 1.953 | 2012-04-25 | 2013-07-31 | 2012-10-22 | 2014-06-30 | 99%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083005 | Dormitory (168 RM) |  | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061.944 | 33061.944 | 2014-08-26 |  | 2016-08-02 | 2016-08-15 | 2%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) |  | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805.3 | 56108.943 | 2012-06-19 |  | 2014-06-19 | 2015-03-16 | 69% | 19165 | ALUA073006B; YWHG111005; WWYK143004A; ZHTV053302;
12/05/2014 | [8 empty] | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230.2925 | 3230.2925 | 2012-06-26 |  | 2013-09-27 | 2015-03-16
12/05/2014 | [8 empty] | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978.8077 | 4978.8077 | 2012-06-26 |  | 2013-08-28 | 2015-03-16
12/05/2014 | [8 empty] | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874.106 | 2191.91 | 2012-07-02 |  | 2012-11-20 | 2015-03-16
12/05/2014 | [8 empty] | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799.2288 | 1799.2288 | 2012-07-27 |  | 2013-01-23 | 2015-03-16
12/05/2014 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV103006P1 | EC-130H Simulator/Training Operations |  | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | W912PL12C0011 | 14347.6 | 14438.88 | 2013-02-10 | 2014-08-28 | 2014-03-07 | 2015-01-23 | 99% | 4333 | WWYK143004A; LKTC093101;
12/05/2014 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV123002 | HC-130J Joint Use Fuel Cell |  | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | W912PL12C0018 | 12361 | 12415.286 | 2013-01-10 |  | 2014-03-14 | 2015-01-15 | 86%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120010 | F-35 ADAL Aircraft Maintenance Unit |  | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | W912PL12C0027 | 4781.113 | 4980.026 | 2012-10-09 | 2014-01-06 | 2013-09-10 | 2014-12-31 | 99%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120011 | F-35 Squad Ops/AMU 2 |  | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | W912PL13C0006 | 12358.5 | 12799.937 | 2013-10-08 |  | 2014-08-29 | 2014-12-16 | 80%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY983202 | Air Freight Terminal Complex |  | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | N6274210D1308JQ01 | 30047.253 | 32363.6898 | 2012-07-18 |  | 2014-05-14 | 2015-03-02 | 87%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility |  | 2011-12-30 | 2012-04-28 | Pacific West Builders | N4019210D28100003 | 9490.73 | 9433.61 | 2012-05-14 | 2014-08-15 | 2013-10-07 | 2015-01-23 | 99% | 2100 | ZHTV053302;
12/05/2014 | 2012 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB105002 | Mission Support Group Complex |  | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998 | 18551.6272 | 2012-03-26 |  | 2013-09-17 | 2014-11-14 | 99%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG071005 | WSA Security Control Facility |  | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172.6 | 4300.1692 | 2012-03-16 | 2014-08-15 | 2013-08-20 | 2015-08-15 | 98%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | NEBRASKA | UNITED STATES | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 |  | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 102754.426 | 102442.3087 | 2012-10-15 |  | 2016-08-15 | 2016-09-12 | 31%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103003 | Communications Network Control Center |  | 2011-11-17 | 2012-04-24 | A4 Construction | W912PL12C0008 | 9326.701 | 9525.511 | 2012-12-01 | 2014-05-01 | 2014-04-24 | 2014-12-15 | 95% | 800 | ZHTV053302;
12/05/2014 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV093108 | AFNWC Sustainment Center |  | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | W912PP12C0016 | 21110 | 21507.2863 | 2012-07-09 |  | 2014-04-03 | 2014-12-15 | 98% | 1100 | ZHTV053302;
12/05/2014 | 2012 | Air Force Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH083003 | C-130 Flight Simulator |  | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | W912HN10D00630003 | 4630 | 4712.131 | 2013-04-30 |  | 2013-12-12 | 2014-12-29 | 91%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock |  | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | W9128F12C0013 | 32123.257 | 33407.635 | 2012-05-22 |  | 2014-09-06 | 2014-12-14 | 95%
12/05/2014 | 2012 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R4 | BMT Recruit Dormitory, Phase IV |  | 2011-12-16 | 2012-10-31 | AE-Merrick&Company ($400,140 shown under DDC) | W9126G08D00060055 | 0 | 0 |  |  | 2012-10-31 | 2015-04-11 | 71%
12/05/2014 | [8 empty] | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06 | 2015-04-11
12/05/2014 | [8 empty] | 2011-12-16 | 2013-07-17 | Spawglass Contractors Inc. | W9126G12C0023 | 50528.593 | 52100.097 | 2013-07-17 |  | 2014-11-26 | 2015-04-11
12/05/2014 | [8 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00J190007 | 6732.163 | 7301.64 | 2014-10-10 |  | 2016-01-03 | 2015-04-11
12/05/2014 | 2012 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | WACC120007 | AIT Barracks Complex, Ph 2 |  | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | W9123608D00140003 | 33915.149 | 34107.6364 | 2012-10-15 |  | 2014-09-19 | 2015-01-14 | 98% | 10112 | WWYK143004A; LKTC093101; ZHTV053302;
12/05/2014 | 2012 | Air Force Active | Major Military Construction | WASHINGTON | UNITED STATES | GJKZ860009 | Wing Headquarters |  | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | W912DW12C0030 | 11957.25 | 12236.213 | 2013-03-18 | 2014-03-07 | 2013-12-26 | 2014-11-10 | 96%
12/05/2014 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17001 | Aircraft Apron/Taxiway And Maintenance Shelters |  | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | N3319109D01200011 | 6740.135 | 6640.535 | 2012-05-15 | 2014-02-02 | 2013-01-27 | 2015-01-30 | 99%
12/05/2014 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17002 | Combat Aircraft Loading Area |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421 | 43728.4594 | 2012-12-24 |  | 2013-12-26 | 2015-03-12 | 49%
12/05/2014 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17003 | Parallel Taxiway Extension |  | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521.53 | 10521.53 | 2012-12-24 |  | 2014-05-03 | 2015-04-23 | 31%
12/05/2014 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17004 | Expeditionary Lodging |  | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587.915 | 27299.359 | 2013-03-15 |  | 2014-03-20 | 2015-01-09 | 86%
12/05/2014 | 2012 | Air Force Active | Major Military Construction |  | GERMANY | TYFR063017 | Dormitory (192 RM) |  | 2012-03-29 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541.6935 | 29541.6935 | 2014-07-01 |  | 2013-11-15 | 2015-09-15 | 1% | 1624 | WWYK143004A; ZHTV053302;
12/05/2014 | 2012 | Air Force Active | Major Military Construction |  | ITALY | ASHE163000 | Child Development Center Addition |  | 2012-06-06 | 2012-09-30 | Collodetto Angelo Costruzioni | N3319112R06220002 | 890.2326 | 910.2126 | 2013-04-01 |  | 2013-12-29 | 2014-07-17 | 80%
12/05/2014 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 |  | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706.6686 | 17706.6686 | 2013-06-04 |  | 2015-10-13 | 2015-11-20 | 62%
12/05/2014 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA124002 | Improve MFH Infrastructure, Phase 1 |  | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | W912HV12C0003 | 19550.171 | 20009.1332 | 2012-07-31 |  | 2014-10-21 | 2015-03-31 | 98%
12/05/2014 | 2012 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | AGGN123002P | Communications Network Control Center Consolidation |  | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619.1715 | 1619.1715 | 2014-03-10 |  | 2014-10-03 | 2014-12-19 | 49%
12/05/2014 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113026 | C-130 Aircraft Maintenance Unit |  | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511.518 | 1511.518 | 2013-09-12 |  | 2014-11-08 | 2016-02-29 | 23%
12/05/2014 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113027 | Air Defense Artillery Maintenance Facility |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265.194 | 1265.194 | 2013-08-28 |  | 2014-08-19 | 2015-06-19 | 21%
12/05/2014 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113032 | Precision Measurement Equipment Laboratory |  | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403.744 | 1409.0421 | 2013-08-28 |  | 2014-12-02 | 2015-07-24 | 21%
12/05/2014 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113034 | AFOSI Regional And Local Facility |  | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214.606 | 1214.606 | 2013-08-28 |  | 2015-01-14 | 2015-02-19 | 21%
12/05/2014 | 2012 | Air Force Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | PDPG020143 | Construct New Airfield Control Tower, B1295 & Base Op'S B395 |  | 2012-03-16 | 2012-07-26 | Flintco, LLC. | W912QR12C0048 | 16915 | 17335.163 | 2012-08-22 | 2014-06-23 | 2014-12-16 | 2015-01-22 | 98%
12/05/2014 | 2012 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ120572 | Vehicle Maintenance Facility |  | 2013-01-04 | 2014-08-22 | Oddo Construction Services | FA667014C0002 | 2087.131 | 2087.131 | 2014-09-22 |  | 2016-02-13 | 2015-07-31 | 2%
12/05/2014 | 2012 | Air Force Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX079003 | Red Horse Readiness And Training Facility |  | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149 | 9004.77 | 2012-07-13 |  | 2013-07-13 | 2014-12-15 | 92%
12/05/2014 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | UTAH | UNITED STATES | KRSM099001 | Fire Station #4 Annex |  | 2013-06-11 | 2013-09-25 | Grand Enterprises, LLC | FA820112D00250004 | 1322.061 | 1392.139 | 2013-10-11 | 2014-08-22 | 2014-05-28 | 2014-11-01 | 98%
12/05/2014 | 2012 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY029154 | Wing Operations and Training Facility |  | 2012-07-27 | 2012-09-26 | SM Construction | W912LA12C0008 | 4.96 | 5.48 | 2012-12-03 | 2014-06-16 | 2013-12-03 | 2014-06-13 | 95%
12/05/2014 | 2012 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | QMSN019029 | Replace Pararescue Training Facility |  | 2012-08-05 | 2012-09-26 | Flintco Construction | W912LA12C7025 | 25.161 | 27.749 | 2013-01-10 | 2014-08-15 | 2014-04-10 | 2014-08-14 | 74%
12/05/2014 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069212 | TFI - F-22 Flight Simulator Facility |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C0003 | 18.842 | 21.659 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 81%
12/05/2014 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069213 | TFI - F-22 Weapons Load Crew Training Facility |  | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | W912J612C0003 | 6.473 | 7.944 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 75%
12/05/2014 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron |  | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | W9128A12C0007 | 9.682 | 10.875 | 2012-08-08 | 2013-11-18 | 2013-08-08 | 2015-03-29 | 70%
12/05/2014 | [8 empty] | 2013-03-04 | 2013-09-12 | Nan, Inc | W912J613C0006 | 2 | 2 | 2013-09-30 |  | 2015-03-29 | 2015-03-29
12/05/2014 | 2012 | Air National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities |  | 2013-05-08 | 2013-08-29 | Maron Construction Co. | W912SV13C0003 | 7.919 | 8.226 | 2013-09-24 |  | 2013-09-28 | 2015-02-11 | 26%
12/05/2014 | 2012 | Air National Guard | Major Military Construction | OHIO | UNITED STATES | WAAR109001 | Alter Predator Operations Center Facility |  | 2012-08-17 | 2012-09-26 | UTS-DAG Construction Co., LLC | W9136412C0046 | 5.296 | 7.09 | 2012-12-05 | 2013-10-31 | 2013-11-01 | 2014-06-15 | 99%
12/05/2014 | 2012 | Air National Guard | Unspecified Minor Military Construction | ALASKA | UNITED STATES | FXSB121354 | Construct Aerospace Support Equipment Storage Facility |  | 2013-07-31 | 2013-09-27 | H. Watt & Scott | W91ZRU10D00060011 | 1.088 | 1.088 | 2013-10-02 | 2014-08-24 | 2014-03-01 | 2014-08-24 | 20%
12/05/2014 | 2012 | Air National Guard | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | XDQU129062 | Vehicle Maintenance Addition |  | 2012-05-24 | 2012-08-17 | Tyler Construction Group, Inc. | W912JM10D00040001 | 1.5 | 1.5 | 2012-08-17 | 2013-09-30 | 2013-02-13 | 2014-05-31 | 99%
12/05/2014 | 2012 | Air National Guard | Unspecified Minor Military Construction | MAINE | UNITED STATES | FKNN049094 | Pavements and Grounds Facility |  | 2012-05-16 | 2012-09-12 | Cornerstone Construction | W912JD11D00070003 | 1.277 | 1.329 | 2012-09-19 | 2013-11-25 | 2013-03-18 | 2014-07-01 | 99%
12/05/2014 | 2012 | Air National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | AXQD119004 | Add to and Alter Survival Equipment Shop |  | 2013-04-10 | 2013-07-12 | Cornerstone Construction Svs | W912SV10D00080004 | 1.19 | 1.241 | 2013-07-16 | 2014-05-23 | 2014-02-07 | 2014-05-30 | 95%
12/05/2014 | 2012 | Air National Guard | Unspecified Minor Military Construction | OHIO | UNITED STATES | WAAR129078 | Relocate Main Gate |  | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | W9136413D00050002 | 1.713 | 1.884 | 2013-08-27 | 2014-05-22 | 2014-03-12 | 2014-05-22 | 84%
12/05/2014 | 2012 | Air National Guard | Unspecified Minor Military Construction | OREGON | UNITED STATES | KJAQ119031 | Addition Squadron Operations Facility |  | 2013-10-08 | 2014-01-29 | Anthem Builders, Inc | W912JV14C0002 | 1.678 | 1.76 | 2014-03-12 |  | 2014-11-10 | 2014-12-19 | 12%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK103006 | C-130J Fuel Systems Maintenance Hangar |  | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869 | 20869 | 2013-07-23 |  | 2015-06-25 | 2015-07-23 | 36%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK113005 | C-130J Flight Simulator Addition |  | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218.503 | 4218.503 | 2014-10-24 |  | 2015-09-24 | 2015-10-26 | 1%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY133001 | Civil Engineer Administration/Operations Facility |  | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947.269 | 15947.269 | 2014-07-09 |  | 2016-03-01 | 2016-03-30 | 2%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair |  | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 13298.609 | 13356.965 | 2013-08-21 |  | 2015-05-21 | 2015-02-11 | 74%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | QSEU103008 | HC-130J Simulator Facility |  | 2012-12-07 | 2013-06-28 | IBKI, Inc. Choctaw, MS | W912HN13C0011 | 7692.387 | 7805.965 | 2013-08-12 |  | 2014-11-20 | 2015-04-15 | 97%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | ACC123184 | Air Support Operations Center |  | 2013-03-14 | 2013-09-24 | Better Built Construction Serv | W912HN10D00530003 | 6458 | 6458 | 2013-11-07 |  | 2015-03-18 | 2015-05-01 | 17%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC133101 | RPA Mission Complex Physical Protection System |  | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643.42 | 10643.42 | 2014-08-19 |  | 2015-07-24 | 2015-09-01 | 2%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD123004 | MQ-9 Maintenance Hangar |  | 2013-03-01 | 2013-06-17 | HEW-Phelps | W912PP13C0019 | 20620 | 20726.768 | 2013-08-30 |  | 2015-03-09 | 2014-12-30 | 92%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092011 | B-52 Add/Alter Munitions Age Facility |  | 2012-11-19 | 2013-05-31 | Rolac Contracting, Inc. | W9128F13C0008 | 4376.727 | 4260.351 | 2013-06-19 |  | 2014-11-22 | 2014-12-11 | 48%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083008 | Dormitory (96 Rm) |  | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170.185 | 17170.185 | 2014-03-15 |  | 2015-03-07 | 2015-06-25 | 18%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103012 | F-35 Adal Hangar 45W/AMU |  | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781 | 6934.456 | 2014-01-27 |  | 2015-06-13 | 2015-08-15 | 29%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103030 | F-35A Modular Storage Magazines |  | 2012-08-08 | 2013-12-17 | Zumwalt Construction, Inc. | W9123811D00260006 | 2028.458 | 2033.5187 | 2014-01-27 |  | 2015-06-10 | 2015-10-25 | 9%
12/05/2014 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM113028 | F-35 Adal Building 118 For Flight Simulator |  | 2012-08-08 | 2013-12-17 | Creative Times, Inc. (CTI) | W9123811D00240002 | 3878.926 | 3888.2676 | 2014-01-29 |  | 2015-02-15 | 2015-04-30 | 43%
12/05/2014 | 2013 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103032 | Dormitory (48 Pn) |  | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031.649 | 23031.649 | 2013-08-15 |  | 2015-05-21 | 2015-07-29 | 43%
12/05/2014 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 |  | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698.0727 | 14787.5107 | 2013-08-29 |  | 2015-10-16 | 2016-01-04 | 19%
12/05/2014 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA133001P2 | Improve Family Housing, Ph 2 |  | 2013-05-16 | 2013-09-30 | Nishimatsu Construction Co., Ltd | FZ520513C0005 | 13989.4156 | 13746.0243 | 2013-10-29 |  | 2015-05-23 | 2015-05-22 | 69%
12/05/2014 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA134001 | Improve Mfh Infrastructure, Phase 2 |  | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336.739 | 14803.5238 | 2013-10-23 |  | 2015-08-29 | 2015-08-31 | 39%
12/05/2014 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | FBNV133500 | T-10 Engine Test Cell (AMARG) |  | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D0110 | 1795 | 1795 | 2014-08-12 |  | 2015-05-04 | 2015-08-04 | 10%
12/05/2014 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | NKAK113003 | C130J Propeller Repair Training Facility |  | 2013-11-19 | 2014-02-21 | HGL Construction | FA446011D00075014 | 727 | 727 | 2014-06-20 |  | 2015-02-21 | 2015-02-20 | 1%
12/05/2014 | 2013 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 |  | 2013-03-06 | 2013-05-23 | Southwind Construction | W912BV12D00180003 | 1525.212 | 1525.212 | 2013-06-07 |  | 2015-07-19 | 2015-08-03 | 66%
12/05/2014 | 2013 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ099095 | Flight Simulator Facility |  | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242.986 | 5242.986 | 2014-08-05 |  | 2015-09-18 | 2016-01-15 | 2%
12/05/2014 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | KYJM129022 | Add Simulator Bay, Building 191 |  | 2013-06-07 | 2013-09-23 | CCI | W9127810D001180020 | 1552.029 | 1591.6019 | 2013-12-16 |  | 2014-07-07 | 2015-02-12 | 82%
12/05/2014 | 2013 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | HAYW109006 | F-15 Conversion |  | 2013-08-23 | 2013-09-27 | RS Morris Construction | W912LA11D00180010 | 3.747 | 4.055 | 2013-11-01 |  | 2015-01-25 | 2015-06-23 | 0%
12/05/2014 | [8 empty] | 2013-08-23 | 2013-09-30 | RS Morris Cosntruction | W912LA11D00180011 | 2.402 | 2.575 | 2013-11-01 |  | 2015-01-25 | 2015-06-23
12/05/2014 | 2013 | Air National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV119001 | Alter Target Intelligence Facility |  | 2013-05-22 | 2013-10-10 | K.L. HOUSE CONSTRUCTION CO. | W912J314C1001 | 4.569 | 5.026 | 2014-01-27 |  | 2015-01-27 | 2015-02-23 | 13%
12/05/2014 | 2013 | Air National Guard | Major Military Construction | WYOMING | UNITED STATES | DPEZ089017 | C-130 Flight Simulator Training Facility |  | 2013-08-28 | 2013-09-27 | Faith Enterprises | W912L313D0003 | 5.062 | 5.294 | 2013-09-27 |  | 2015-03-21 | 2015-03-21 | 5%
12/05/2014 | 2013 | Air National Guard | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | FJRP079016 | BCE pavements and Grounds Facility |  | 2013-12-23 | 2014-04-07 | Showalter Construction | W9124209D0013N908 | 1.22 | 1.258 | 2014-06-01 |  | 2015-03-03 | 2015-03-28 | 1%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093007 | Construct Addition, Field Training Facility, B936 |  | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699.907 | 4699.907 | 2014-04-23 |  | 2015-06-11 | 2015-07-07 | 7%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) |  | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513.636 | 15513.636 | 2014-06-24 |  | 2016-01-11 | 2016-02-14 | 7%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility |  | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699.643 | 53699.643 | 2014-08-27 |  | 2016-10-15 | 2017-02-21 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction |  | GUAM | AJJY143760 | Hardened Structures For POL Fuel Systems |  | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907.7 | 17907.7 | 2014-12-01 |  | 2016-03-30 | 2017-04-15 | 5%
12/05/2014 | 2014 | Air Force Active | Major Military Construction |  | GUAM | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility |  | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177.269 | 6177.269 | 2014-10-24 |  | 2016-07-20 | 2016-07-20 | 3%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 |  | 2013-11-18 | 2014-06-17 | SRB International LLC | N6274214C1312 | 2699 | 2699 | 2014-08-21 |  | 2015-05-08 | 2015-06-07 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar |  | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924.5 | 63924.5 | 2014-06-24 |  | 2015-12-03 | 2017-03-10 | 7% | 10500 | SGBP100904C;
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems |  | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100.5 | 8100.5 | 2014-09-02 |  | 2015-11-19 | 2015-12-19 | 25% | 2500 | SGBP100904C;
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145137 | KC-46A Alter Miscellaneous Facilities |  | 2014-03-10 | 2014-06-27 | Red Cedar Enterprises, Inc | W912DQ13D40010002 | 838.705 | 838.705 | 2014-07-12 |  | 2015-02-22 | 2015-03-11 | 78%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145138 | KC-46A Alter Aircraft Parking Apron |  | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976 | 976 | 2014-08-18 |  | 2017-02-06 | 2017-03-10 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145142 | KC-46A 1-Bay Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200 | 25200 | 2014-09-19 |  | 2016-12-18 | 2017-03-10 | 4% | 3000 | SGBP100904C;
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar |  | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959 | 53959 | 2014-06-24 |  | 2015-11-24 | 2017-03-10 | 2% | 19000 | SGBP100904C;
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) |  | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306.162 | 7306.162 | 2014-10-30 |  | 2015-09-23 | 2015-10-15 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | KENTUCKY | UNITED STATES | ACC123183 | Air Support Operations Center |  | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143.462 | 7143.462 | 2014-09-29 |  | 2016-02-13 | 2015-12-13 | 1%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | PAYZ130011 | U.S. Cyber Command Joint Operations Center |  | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 57000 | 57000 | 2014-07-07 |  | 2016-03-26 | 2017-04-13 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111010 | WSA: Construct Two New MOP Igloos |  | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817.7 | 3817.7 | 2014-08-11 |  | 2015-09-06 | 2015-11-13 | 23%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC073101 | Land Acquisition |  | 2014-07-18 | 2014-09-02 | USACE | W81EYN42417577 | 11.45 | 11.45 | 2014-09-02 |  | 2014-12-01 | 2016-03-15 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF083002 | Dormitory |  | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381 | 30381 | 2014-08-05 |  | 2016-08-22 | 2016-09-27 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103005 | F-35A ADAL AME Storage Facility |  | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D0113 | 4829.984 | 4829.984 | 2014-08-27 |  | 2016-01-15 | 2015-08-15 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103006 | F-35A Parts Store |  | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974.014 | 6974.014 | 2014-08-15 |  | 2015-12-01 | 2016-01-15 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar |  | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066 | 8066 | 2014-06-24 |  | 2015-11-12 | 2015-09-01 | 5%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF113005 | RPA Weapons School |  | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922.7 | 14922.7 | 2014-08-12 |  | 2016-05-31 | 2016-06-01 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073050 | Dormitory (144 Rm) |  | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19224.874 | 19224.874 | 2014-07-10 |  | 2016-07-07 | 2015-07-15 | 4%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 |  | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285.5 | 21285.5 | 2014-08-25 |  | 2016-09-30 | 2016-02-08 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092013 | B-52 Munitions Storage Igloos |  | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540.27 | 9540.27 | 2014-07-15 |  | 2015-12-01 | 2015-09-21 | 5%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164.308 | 1164.308 | 2014-07-30 |  | 2015-12-08 | 2015-03-12 | 5%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu |  | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111.892 | 7111.892 | 2014-07-02 |  | 2015-12-08 | 2015-12-17 | 2%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645.2 | 5645.2 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 24%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143004 | KC-46A FTU Ftc Simulator Facility Phase 1 |  | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000 | 11000 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 24%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 |  | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265.367 | 3265.367 | 2014-05-15 |  | 2015-05-17 | 2015-06-09 | 22%
12/05/2014 | 2014 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103011 | F-35 ADAL Hangar 45E/AMU |  | 2013-07-22 | 2014-04-10 | CTI | W912PL14C0005 | 6587 | 8797.06 | 2014-05-20 |  | 2015-10-02 | 2015-10-15 | 29%
12/05/2014 | 2014 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility |  | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817.6089 | 39817.6089 | 2014-08-19 |  | 2016-07-10 | 2016-06-17 | 2%
12/05/2014 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ144287 | Improve MFH Infrastructure, Phase 3 |  | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288.6807 | 6288.6807 | 2014-08-15 |  | 2016-01-07 | 2016-01-07 | 3%
12/05/2014 | [8 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202.136 | 4202.136 | 2014-07-23 |  | 2014-06-30 | 2016-01-07
12/05/2014 | [8 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473.4496 | 2473.4496 | 2014-08-06 |  | 2015-09-10 | 2016-01-07
12/05/2014 | [8 empty] | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302.11 | 25302.11 | 2014-10-30 |  | 2016-12-05 | 2016-12-24
12/05/2014 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility |  | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547.47 | 1547.47 | 2014-11-24 |  | 2015-07-29 | 2015-11-23 | 1%
12/05/2014 | 2014 | Air National Guard | Unspecified Minor Military Construction | SOUTH CAROLINA | UNITED STATES | PSTE129092 | Construct North Overrun |  | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W912420930003S401 | 1.702 | 1.78 | 2014-03-11 |  | 2014-12-24 | 2014-12-31 | 2%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 71569 | Westside Utilities Infrastructure |  | 2012-08-24 | 2012-11-15 | Contrack International Inc. | W912ER-11-D-0009 | 11924.059 | 10017.2264 | 2012-12-12 |  | 2014-03-07 | 2014-08-02 | 99%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | AFGHANISTAN | 71602 | Barracks |  | 2011-11-14 | 2012-01-28 | Bryan 77 Construction JV |  | 16732.683 | 17774.538 | 2012-03-06 | 2014-05-24 | 2013-11-26 | 2014-05-15 | 99%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | AFGHANISTAN | 71604 | Eastside Utilities Infrastructure |  | 2012-05-30 | 2012-09-04 | ANHAM-ICSS Joint Venture | W912ER-11-D-0003 | 26826.989 | 24722.776 | 2012-10-18 |  | 2014-06-05 | 2015-01-31 | 68.5%
2014-11-30 | 2009 | Army Active | Major Military Construction |  | AFGHANISTAN | 72125 | SOF Alpha Ramp Facilities |  | 2012-04-04 | 2012-08-23 | Prime Projects Int'l (Const) Limited | W912ER-12-C-0040 | 5739 | 8416 | 2012-09-27 | 2014-11-30 | 2013-08-13 | 2014-03-01 | 89%
2014-11-30 | 2010 | Army Active | Major Military Construction |  | AFGHANISTAN | 72477 | USFOR-A Headquarters & Housing |  | 2011-03-28 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 47160.85 | 32282.8094 | 2011-09-09 |  | 2013-12-07 | 2014-08-25 | 97.48%
2014-11-30 | 2009 | Army Active | Major Military Construction |  | AFGHANISTAN | 73090 | Utilities, Ph 1 |  | 2009-05-20 | 2009-09-14 | Road & Roof Construction Company | W912ER-09-C-0038 | 21195.4629 | 23326.2986 | 2009-11-02 | 2014-04-03 | 2010-10-28 | 2014-02-28 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74067 | Construct Drainage System, Ph 3 |  | 2012-04-27 | 2012-08-15 | ANHAM-ICSS JV | W912ER-11-D-0003 | 19902.989 | 20833.6265 | 2012-10-09 |  | 2014-06-01 | 2014-10-31 | 94.13%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | AFGHANISTAN | 74084 | Barracks, Ph 5 |  | 2011-12-08 | 2012-04-12 | Bryan 77 Construction JV | W912ER-11-D-0004 | 19331.277 | 14238.5882 | 2012-06-08 | 2014-09-17 | 2014-04-19 | 2014-09-17 | 91.8%
2014-11-30 | 2011 | Army Active | Unspecified Minor Military Construction |  | AFGHANISTAN | 79762 | PRIMARY WASTE WATER TREATMENT |  | 2011-05-04 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 1386.997 | 1386.997 | 2011-09-09 |  | 2013-12-07 | 2014-08-25 | 99%
2014-11-30 | 2011 | Army Active | Unspecified Minor Military Construction |  | AFGHANISTAN | 79770 | WATER WELL, POTABLE |  | 2011-05-13 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 1330.83 | 1330.83 | 2011-09-09 |  | 2013-12-07 | 2014-08-25 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | GERMANY | 55985 | Chapel |  | 2013-07-12 | 2013-11-05 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15915.6532 | 16173.2402 | 2013-11-21 |  | 2016-03-23 | 2016-03-23 | 21.83%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | GERMANY | 57594 | Satellite Communications Center |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565.3511 | 27788.0021 | 2014-03-14 |  | 2015-12-14 | 2016-02-27 | 15.49%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | GERMANY | 58925 | Satellite Communications Center |  | 2012-03-12 | 2014-02-07 | JV PGWM SATCOM | W912GB-14-C-0037 | 29010.1333 | 29010.1333 | 2014-10-16 |  | 2015-12-14 | 2016-07-07 | 0% | 6000 | 71485
2014-11-30 | 2011 | Army Active | Major Military Construction |  | GERMANY | 59434 | Physical Fitness Center |  | 2010-12-01 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0040 | 13513.2866 | 14113.426 | 2012-11-30 |  | 2014-11-28 | 2014-11-28 | 89.06%
2014-11-30 | [8 empty] | 2012-06-15 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II |  | 969.0413 | 1109.3938 | 2012-11-30 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 63.67%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | GERMANY | 60555 | Information Processing Center |  | 2011-06-20 | 2012-05-14 | Hessisches Baumanagement Wiesbaden | W912GB-08-C-0005 | 27799.1141 | 31738.9806 | 2012-06-18 | 2014-12-07 | 2014-06-01 | 2014-12-19 | 95.54%
2014-11-30 | 2010 | Army Active | Major Military Construction |  | GERMANY | 63394 | Barracks |  | 2010-03-15 | 2011-12-13 | Staatliches Hochbauamt Nurnberg II |  | 16797.4108 | 17199.0165 | 2012-01-09 | 2014-05-05 | 2013-09-06 | 2014-03-31 | 97.31%
2014-11-30 | 2009 | Army Active | Military Family Housing |  | GERMANY | 66318 | Family Housing Replacement Construction |  | 2010-04-12 | 2010-05-28 | Federal Republic of Germany |  | 21654.8608 | 22077.7617 | 2009-12-08 | 2012-08-15 | 2012-12-25 | 2013-07-06 | 99%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66465 | Confinement Facility |  | 2012-03-06 | 2013-03-07 | LBB Kaiserslautern | W912GB-09-C-0039 | 9459.8812 | 9696.9647 | 2013-04-29 | 2014-11-20 | 2014-09-21 | 2014-09-25 | 97.69%
2014-11-30 | [8 empty] | 2012-11-21 | 2012-06-19 | LBB Kaiserslautern |  | 472.7664 | 470.1863 | 2013-04-29 | 2014-09-25 | 2014-09-21 | 2014-09-25 | 83.93%
2014-11-30 | 2010 | Army Active | Major Military Construction |  | GERMANY | 66596 | Barracks |  | 2010-09-07 | 2010-09-30 | Federal Republic of Germany | W912GB-09-C-0012 | 16925.5868 | 17646.1493 | 2012-09-05 | 2014-09-12 | 2014-05-20 | 2014-07-14 | 98%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | GERMANY | 66834 | Vehicle Maintenance Shop |  | 2010-12-01 | 2011-06-16 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 15984.7877 | 17308.6172 | 2011-12-12 |  | 2013-12-18 | 2015-05-31 | 87.62%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68074 | Construct New ACP |  | 2013-11-15 | 2013-08-12 | Hessisches Baumanagement Wiesbaden |  | 6303.8821 | 7213.2685 | 2014-03-05 |  | 2014-12-12 | 2014-12-12 | 89.23%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | GERMANY | 68866 | Sensitive Compartmented Information Fac |  | 2012-05-22 | 2013-01-23 | ECC International LLC | W912GB-13-C-0003 | 87011.483 | 89200.6517 | 2013-02-22 |  | 2015-09-19 | 2015-10-31 | 18.2% | 33782 | 65714, 68822, 69936
2014-11-30 | [8 empty] | 2012-05-22 | 2013-02-04 | OBG Hochbau GmbH & Co. KG |  | 7198.2416 | 7716.9736 | 2014-07-09 | 2014-11-16 | 2014-10-07 | 2015-02-02 | 98%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | GERMANY | 69614 | Barracks |  | 2012-03-02 | 2013-03-27 | Staatliches Hochbauamt Amberg | W912GB-10-C-0043 | 17523.1242 | 18638.6582 | 2013-03-27 |  | 2014-12-31 | 2014-11-26 | 80%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | GERMANY | 69615 | Barracks |  | 2012-01-03 | 2012-03-15 | Bauamt Amberg-Sulzbach | W912GB-10-C-0007 | 17668.7874 | 17947.0405 | 2012-10-10 | 2014-10-25 | 2014-08-27 | 2014-09-25 | 93.94%
2014-11-30 | 2010 | Army Active | Major Military Construction |  | GERMANY | 69616 | Barracks |  | 2012-03-16 | 2012-07-11 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0010 | 13259.0374 | 13576 | 2012-08-06 | 2014-07-01 | 2014-02-10 | 2014-06-30 | 98.59%
2014-11-30 | 2010 | Army Active | Military Family Housing |  | GERMANY | 71421 | Family Housing Replacement Construction |  | 2010-08-01 | 2010-09-30 | LBB Niederlassung Idar-Oberstein | W912GB-07-D-0026 | 19120.2952 | 19120.2952 |  |  |  | 2017-09-29 | 3.496%
2014-11-30 | 2011 | Army Active | Military Family Housing |  | GERMANY | 71422 | Family Housing Replacement Construction |  | 2011-07-18 | 2011-09-14 | LBB Niederlassung Idar-Oberstein | W912GB-09-C-0007 | 1907.6823 | 1907.6823 |  |  | 2012-02-23 | 2017-09-29 | 0.853%
2014-11-30 | [8 empty] | 2014-10-15 | 2011-09-14 | LBB Niederlassung Idar-Oberstein |  | 33110.8094 | 33110.8094 |  |  | 2012-02-23 | 2017-09-29 | 4.998%
2014-11-30 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78475 | Family Housing Improvements |  | 2013-05-22 | 2014-11-24 | Klebl GmbH | W912GB-15-C-0003 | 14631.5966 | 14631.5966 | 2016-08-09 |  | 2016-06-10 | 2016-06-10 | 0%
2014-11-30 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78505 | Family Housing New Construction |  | 2012-04-06 | 2013-08-07 | Staatliches Hochbauamt Amberg |  | 13548.8862 | 13641.2361 | 2013-08-07 |  | 2015-09-14 | 2015-11-05 | 32.54%
2014-11-30 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78506 | Family Housing New Construction |  | 2012-04-10 | 2013-09-30 | Bauamt Amberg-Sulzbach |  | 12815.485 | 12884.7251 | 2013-09-30 |  | 2015-08-11 | 2015-08-11 | 61%
2014-11-30 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78841 | Family Housing Improvements |  | 2012-05-15 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0018 | 20428.5583 | 20922.1831 | 2012-10-15 |  | 2018-10-29 | 2018-11-25 | 36.57%
2014-11-30 |  |  |  |  | GERMANY | 78841 | Family Housing Improvements |  | 2012-05-15 | 2012-09-13 | WAYSS & FREYTAG INGENIEURBAU AG |  | 1168 | 1590 | 2013-05-23 |  | 2014-09-05 | 2014-10-05 | 99%
2014-11-30 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 79097 | Family Housing Improvements |  | 2012-05-12 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0017 | 17917.1392 | 18722.9467 | 2012-10-15 |  | 2018-04-02 | 2018-04-02 | 31%
2014-11-30 | 2011 | Army Active | Major Military Construction |  | HONDURAS | 61383 | Barracks |  | 2011-05-18 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | W91278-11-C-0028 | 15146.5804 | 15633.3629 | 2012-01-10 |  | 2014-01-09 | 2014-09-24 | 99%
2014-11-30 | 2013 | Army Active | Major Military Construction |  | JAPAN | 62783 | Satellite Communications Facility |  | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 6488.2629 | 6488.2629 | 2014-11-21 |  | 2021-06-09 | 2021-06-09 | 0% | 24810 | 36113, 61562, 64474, 66441, 69999, 71472, 71485, 72242
2014-11-30 | 2013 | Army Active | Major Military Construction |  | JAPAN | 62783 | Satellite Communications Facility |  | 2013-03-27 | 2014-09-18 | Prime Projects International Japan Co., Ltd. |  | 61071.4985 | 61071.4985 | 2014-11-21 |  | 2021-06-09 | 2021-06-09 | 0%
2014-11-30 | 2008 | Army Active | Major Military Construction |  | KOREA, SOUTH | 58784 | Barracks Complex |  | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32468.604 | 35207.0311 | 2012-09-17 |  | 2014-09-07 | 2015-06-09 | 79.09% | 28300 | 55313, 59557, 59804, 60045, 60151, 60241, 61148, 61355, 61873, 62077, 63662, 64143, 64903, 65795, 65796, 67038, 67169, 68458, 68763, 68769, 68784, 68840, 68847, 68863, 68877, 70979
2014-11-30 | 2008 | Army Active | Major Military Construction |  | KOREA, SOUTH | 58784 | Barracks Complex |  | 2012-02-03 | 2012-09-17 | Shinsung Engr. & Const. Co., Ltd. |  | 17815.4345 | 18941.388 | 2012-09-17 | 2011-08-12 | 2014-03-16 | 2014-10-26 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 72650 | Barracks |  | 2011-11-10 | 2012-02-24 | Samsung C&T Corporation | W912UM-12-C-0012 | 27592.9923 | 28582.68 | 2012-02-24 |  | 2015-12-05 | 2015-10-07 | 48.48%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 72650 | Barracks |  | 2011-11-28 | 2012-02-27 | Hanmi C&E Co., LTD. |  | 63.7852 | 4.2522 | 2012-02-27 |  | 2015-10-31 | 2015-10-31 | 100%
2014-11-30 | 2013 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76196 | Battalion Headquarters Complex |  | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25852.7608 | 28686.0028 | 2013-05-14 |  | 2015-06-09 | 2016-05-01 | 23.64%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76235 | Barracks Complex |  | 2012-02-02 | 2012-04-06 | Fine Construction Co., Ltd. | W912UM-12-C-0022 | 28609.5284 | 29387.3996 | 2012-04-06 | 2014-12-05 | 2014-06-22 | 2014-11-23 | 96.66%
2014-11-30 | 2012 | Army Active | Major Military Construction |  | KOREA, SOUTH | 76235 | Barracks Complex |  | 2012-02-02 | 2012-02-09 | Hanmi C&E Co., LTD. |  | 18.1909 | 90.3946 | 2012-02-09 | 2014-12-05 | 2014-07-02 | 2014-12-03 | 58.48%
2014-11-30 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses |  | 2013-06-21 | 2013-09-27 | Contrack International, Inc. | W912ER-13-C-0032 | 49412.74 | 54675.778 | 2013-10-25 |  | 2015-03-25 | 2015-03-25 | 18.15%
2014-11-30 | 2010 | Army Active | Major Military Construction |  | KUWAIT | 71485 | APS Warehouses |  | 2013-11-06 | 2014-04-03 | Contrack International, Inc. |  | 6749.291 | 6749.291 | 2014-05-08 |  | 2015-10-30 | 2015-10-30 | 6.131%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK |  | 2014-08-21 | 2014-09-30 | Nan Inc | W9128A-12-D-0012 | 1555.718 | 1555.718 | 2014-10-28 |  | 2015-10-23 | 2015-10-23 | 0%
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction | MARSHALL ISLANDS | MARSHALL ISLANDS | 82371 | Power Plant Facility 994 |  | 2014-09-28 | 2014-09-30 | San Juan Construction, Inc. | W9128A-12-D-0010 | 1596.834 | 1596.834 | 2014-10-28 |  | 2015-09-07 | 2015-09-07 | 0%
2014-11-30 | 2010 | Army Reserve | Major Military Construction | PUERTO RICO | PUERTO RICO | 69568 | Army Reserve Center/Land |  | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | W912QR-11-C-0046 | 12356.39 | 12640.4564 | 2011-11-15 |  | 2013-08-06 | 2014-12-31 | 98.08%
2014-11-30 | 2011 | Army Active | Major Military Construction | ALABAMA | UNITED STATES | 60463 | Aviation Component Maintenance Shop |  | 2010-12-14 | 2011-05-18 | Carothers Construction, Inc | W91278-07-D-0033 | 19712.66 | 21518.654 | 2011-09-20 | 2013-07-30 | 2013-09-09 | 2015-01-05 | 99%
2014-11-30 | 2011 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 57369 | Simulations Center |  | 2010-10-04 | 2011-05-11 | UNIT COMPANY | W911KB-07-D-0014 | 20025.555 | 22497.391 | 2011-05-18 | 2013-10-23 | 2013-05-17 | 2013-10-24 | 100%
2014-11-30 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 61515 | Physical Fitness Facility |  | 2011-10-19 | 2012-11-07 | Bristol General Contractors, LLC | W911KB-13-C-0002 | 21813.389 | 22240.075 | 2013-03-16 |  | 2014-12-06 | 2015-08-04 | 47.85%
2014-11-30 | 2012 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67113 | Aviation Complex, Ph 3A |  | 2011-07-15 | 2012-06-07 | Watterson Construction Company | W911KB-12-C-0008 | 70591 | 71467.009 | 2012-06-14 | 2014-11-10 | 2014-08-03 | 2014-12-16 | 98.01% | 27000 | 68962, 71539
2014-11-30 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex |  | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0008 | 14180.4971 | 14206.8744 | 2014-05-15 |  | 2016-02-04 | 2016-04-19 | 10.88% | 3850 | 63799
2014-11-30 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex |  | 2013-08-28 | 2014-04-14 | Arctic-American JV |  | 16180.297 | 16131.008 | 2014-04-23 |  | 2015-10-15 | 2015-12-16 | 39.37%
2014-11-30 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar |  | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25546.7 | 25546.7 | 2014-06-30 |  | 2016-03-21 | 2016-09-02 | 6.016%
2014-11-30 | 2014 | Army Active | Major Military Construction | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar |  | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC |  | 9525 | 9486.903 | 2014-04-25 |  | 2015-10-16 | 2015-12-18 | 38.41%
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 79679 | Materials Analysis Lab |  | 2014-02-03 | 2014-06-10 | Au' Authum Ki, Inc | W912PL-10-D-0109 | 2983.983 | 2983.983 | 2014-07-28 |  | 2015-02-23 | 2015-02-23 | 16.79%
2014-11-30 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 56425 | General Instruction Building |  | 2012-08-20 | 2012-09-29 | Souza Construction, Inc. | W91238-10-D-0010 | 2996 | 3163.422 | 2012-11-06 |  | 2013-11-06 | 2015-01-01 | 95.79%
2014-11-30 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60285 | General Instruction Building |  | 2010-10-07 | 2011-05-18 | RQ Construction, LLC | W91238-11-C-0005 | 29886 | 32382.623 | 2011-06-07 | 2014-09-08 | 2013-05-24 | 2014-12-31 | 97.96%
2014-11-30 | 2009 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 60859 | Water Treatment Plant |  | 2008-12-04 | 2009-05-13 | Cushman Contracting Corporation | W91238-09-C-0009 | 4795 | 6424.5692 | 2009-06-17 | 2011-07-24 | 2010-12-09 | 2014-10-31 | 99.97%
2014-11-30 | 2012 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 62657 | Water Treatment Plant |  | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100112.66 | 99541.018 | 2012-10-19 |  | 2015-10-19 | 2016-01-05 | 59.44%
2014-11-30 | 2011 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility |  | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W912PP-08-C-0019 | 38914.5 | 38914.5 | 2014-09-19 |  | 2016-06-30 | 2016-06-30 | 0.815% | 12900 | 73686
2014-11-30 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 71482 | ORTC |  | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56000.64 | 61736.64 | 2014-03-19 |  | 2016-05-17 | 2016-05-17 | 7.071%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72160 | UPH Barracks |  | 2013-03-28 | 2013-08-27 | Pre Con Industries, Inc. | W912QR-13-C-0027 | 4384.284 | 4381.945 | 2013-11-18 |  | 2014-11-03 | 2015-01-05 | 63.14%
2014-11-30 | 2014 | Army Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | 72284 | TASS Training Center (TTC) |  | 2014-08-13 | 2014-09-30 | Bara Infoware Inc. | W912QR-14-C-0053 | 16186.7042 | 16186.7042 | 2014-10-20 |  | 2016-05-22 | 2016-05-22 | 0%
2014-11-30 | 2011 | Army Reserve | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 74731 | Training Exercise Warehouse |  | 2011-08-19 | 2012-07-13 | Total Team Construction Services | W912QR-12-C-0042 | 1612.061 | 1612.773 | 2012-09-11 |  | 2013-08-07 | 2014-12-15 | 94.43%
2014-11-30 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76086 | Lightning Protection System |  | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072 | 3072 | 2014-09-16 |  | 2015-12-30 | 2015-12-30 | 0%
2014-11-30 | 2013 | Army Active | Major Military Construction | CALIFORNIA | UNITED STATES | 76091 | Engineering/Housing Maintenance Shop |  | 2014-05-15 | 2014-09-18 | Federal Solutions Group | W91238-14-C-0051 | 3211.6056 | 3211.6056 | 2014-10-08 |  | 2015-11-12 | 2015-11-12 | 0%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 81367 | EXPLOSIVES RECEIVING/SERVICE BUILDING, DEP |  | 2013-12-18 | 2014-04-16 | Cyber Professional Solution Corp | W912PL-14-C-0006 | 1783.729 | 1783.729 | 2014-05-08 |  | 2015-05-08 | 2015-05-08 | 60.12%
2014-11-30 | 2011 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 13852 | Simulations Center |  | 2011-07-15 | 2011-09-14 | Native American Services Corp. | W9128F-11-C-0061 | 27829.194 | 34671.3993 | 2011-11-04 | 2014-09-02 | 2013-04-27 | 2014-10-31 | 99%
2014-11-30 | 2013 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 59626 | Digital Multipurpose Training Range |  | 2013-05-31 | 2013-08-23 | NEU Security Services, LLC | W9128F-13-C-0016 | 14080 | 15393.603 | 2013-09-18 |  | 2015-03-12 | 2015-05-01 | 57.29%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | COLORADO | UNITED STATES | 67658 | Army Reserve Center |  | 2011-11-29 | 2012-04-16 | Liberty Mutual Insurance Company | W912QR-12-C-0028 | 10450.922 | 10580.378 | 2012-05-11 |  | 2013-10-18 | 2015-03-01 | 82.64%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 71221 | Fire Station |  | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542.275 | 11881.525 | 2014-08-27 |  | 2016-02-18 | 2016-02-18 | 1.831%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building |  | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165.0006 | 17165.0006 | 2014-08-21 |  | 2016-02-12 | 2016-02-12 | 0.6049%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77262 | Headquarters Building |  | 2014-03-01 | 2014-08-28 | Medvolt, LLC |  | 13195.378 | 13195.378 | 2014-10-08 |  | 2016-03-31 | 2016-03-31 | 1.1%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar |  | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56720.967 | 56730.945 | 2014-09-02 |  | 2016-08-22 | 2016-08-22 | 2.531%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar |  | 2014-05-23 | 2014-09-04 | SEK JV |  | 3339.182 | 3339.182 | 2014-10-20 |  | 2015-10-20 | 2015-10-20 | 23.7%
2014-11-30 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar |  | 2012-01-17 | 2012-08-09 | Hensel Phelps Construction Co. | W9128F-12-C-0055 | 44801 | 54672.156 | 2012-08-23 | 2014-10-31 | 2014-02-14 | 2014-10-31 | 95.14%
2014-11-30 | 2012 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar |  | 2012-01-17 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction |  | 2669.032 | 2920.134 | 2013-05-31 |  | 2015-02-08 | 2015-02-08 | 85.25%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar |  | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585 | 50585 | 2014-10-06 |  | 2016-05-28 | 2016-05-28 | 0.6472%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar |  | 2014-07-10 | 2014-06-19 | Swinerton Builders |  | 4214.264 | 4214.264 | 2014-07-22 |  | 2015-08-17 | 2015-08-17 | 6.056%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 77885 | Runway |  | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9832.807 | 10054.009 | 2014-07-01 |  | 2015-07-01 | 2015-07-01 | 13.7%
2014-11-30 | 2014 | Army Active | Major Military Construction | COLORADO | UNITED STATES | 79618 | Simulator Building |  | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440 | 8440 | 2014-08-20 |  | 2016-02-11 | 2016-02-11 | 0.6844%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81300 | AIRCRAFT MAINTENANCE HANGAR |  | 2013-04-29 | 2013-09-12 | CMS of Colorado Springs, Inc. dba CMS | W9128F-13-C-0023 | 1730.8978 | 1854.3718 | 2013-10-29 |  | 2014-08-25 | 2014-12-10 | 79.37%
2014-11-30 | 2013 | Army Reserve | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 82067 | Unheated Storage Building |  | 2013-07-23 | 2013-12-05 | Komada, LLC | W912QR-14-C-0003 | 1626.125 | 1676.586 | 2013-12-23 |  | 2014-12-23 | 2014-12-15 | 86.87%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE |  | 2013-08-15 | 2014-06-17 | PORTICO SERVICES, LLC | W912DR-14-C-0028 | 1793.105 | 1798.8087 | 2014-07-15 |  | 2015-03-12 | 2015-03-12 | 26.42%
2014-11-30 | 2010 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 69471 | Army Reserve Center/Land |  | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | W912QR-12-C-0022 | 16009 | 16319.55 | 2012-05-22 |  | 2013-09-24 | 2015-03-21 | 77.99%
2014-11-30 | 2011 | Army Reserve | Major Military Construction | FLORIDA | UNITED STATES | 74220 | Army Reserve Center/Land |  | 2011-05-19 | 2011-09-23 | Liberty Mutual Insurance Company | W912QR-11-C-0048 | 8807.148 | 8793.328 | 2011-10-21 |  | 2013-03-24 | 2014-11-13 | 99%
2014-11-30 | 2014 | Army Active | Major Military Construction | FLORIDA | UNITED STATES | 77539 | Automated Sniper Field Fire Range |  | 2014-07-17 | 2014-09-26 | Barlovento LLC | W91278-10-D-0072 | 4201.077 | 4201.077 |  |  | 2015-12-15 | 2015-12-15 | 0%
2014-11-30 | 2013 | Army Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 81597 | AMSA Addition/Alteration |  | 2013-08-27 | 2013-09-30 | FutureNet Group, Inc. | W912QR-13-D-0023 | 1379.863 | 1393.566 | 2013-10-09 |  | 2014-09-24 | 2014-12-31 | 35.12%
2014-11-30 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 57794 | Digital Multipurpose Training Range |  | 2012-12-26 | 2013-05-10 | Caddell Construction Co. (DE), LLC | W912HN-10-D-0044 | 19523 | 19679.251 | 2014-02-04 |  | 2015-04-30 | 2015-04-30 | 44.31%
2014-11-30 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 67017 | Multipurpose Machine Gun Range |  | 2012-11-19 | 2013-05-16 | Bristol Environmental Remediation Service | W912DY-12-D-0053 | 6483.273 | 6528.523 | 2013-07-11 |  | 2014-08-05 | 2014-09-27 | 93.89%
2014-11-30 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72324 | Trainee Barracks Ph 2 |  | 2010-10-26 | 2013-01-10 | Caddell Construction | W912HN-10-D-0044 | 20847 | 21397.928 | 2013-02-12 | 2014-11-11 | 2014-05-08 | 2014-09-12 | 81.38%
2014-11-30 | 2011 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 72324 | Trainee Barracks Ph 2 |  | 2010-10-27 | 2013-01-10 | Leebcor Services, LLC |  | 7936 | 7951.8818 |  | 2014-01-14 | 2013-05-18 | 2013-06-24 | 99.61%
2014-11-30 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 73008 | Unmanned Aerial Vehicle Complex |  | 2013-03-22 | 2013-08-15 | Caddell Construction CO. (DE), LLC | W912HN-10-D-0044 | 20726 | 21007.716 | 2013-11-06 |  | 2015-03-01 | 2015-03-08 | 51.71%
2014-11-30 | 2013 | Army Active | Major Military Construction | GEORGIA | UNITED STATES | 77416 | Ground Source Heat Transfer System |  | 2013-04-04 | 2013-05-29 | R. C. Construction Co., Inc. | W912HN-10-D-0058 | 8295 | 8464.6715 | 2013-07-12 |  | 2015-01-03 | 2015-01-03 | 97.08%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | 81273 | CIDC FIELD OPERATIONS BUILDING |  | 2013-07-17 | 2013-09-20 | Wolf Creek Federal Services, Inc. | W912HN-13-C-0014 | 2841.632 | 2847.757 | 2013-10-29 | 2014-11-11 | 2014-08-25 | 2014-09-05 | 97.21%
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | 85260 | Secure Operations Center |  | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1724.858 | 1724.858 | 2014-11-05 |  | 2015-11-05 | 2015-11-05 | 0%
2014-11-30 | 2008 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 50950 | Barracks Complex |  | 2009-01-30 | 2010-03-26 | Kiewit Building Group Inc. | W9128A-10-C-0005 | 44500 | 45992.851 | 2010-04-26 | 2012-11-06 | 2012-03-10 | 2012-10-15 | 98.95%
2014-11-30 | 2008 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 50950 | Barracks Complex |  | 2009-01-30 | 2010-03-26 | Kiewit Building Group Inc. |  | 421.263 | 421.263 | 2010-04-26 | 2012-10-15 | 2012-03-10 | 2012-10-15 | 53.41%
2014-11-30 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 52269 | Barracks |  | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | W9128A-11-C-0016 | 23984.24 | 24982.959 | 2011-10-17 | 2014-11-18 | 2014-07-16 | 2015-02-11 | 93.84%
2014-11-30 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 52269 | Barracks |  | 2011-04-29 | 2011-09-20 | Nan, Inc. dba Ocean House Builders |  | 1329.054 | 16477.087 | 2011-10-17 |  | 2014-07-16 | 2015-02-11 | 94.3%
2014-11-30 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 56024 | Flood Mitigation |  | 2012-06-29 | 2012-09-25 | Nan, Inc | W9128A-12-C-0019 | 21105.273 | 21927.727 | 2012-10-17 |  | 2014-10-14 | 2015-06-30 | 65.61%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 57176 | Wideband SATCOM Operations Center |  | 2008-10-28 | 2013-09-18 | NCASI JV, LLC | W9128A-12-D-0007 | 295 | 319 | 2013-09-30 | 2014-04-18 | 2014-03-11 | 2014-04-18 | 100%
2014-11-30 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 59581 | Centralized Wash Facility |  | 2011-10-13 | 2012-01-27 | Watts Constructors, LLC | W9128A-12-C-0001 | 28300 | 29982.274 | 2012-02-08 | 2014-11-14 | 2013-12-14 | 2014-11-14 | 97.74%
2014-11-30 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64760 | Training Aids Center |  | 2012-06-29 | 2012-09-19 | SRB International LLC | W9128A-12-C-0013 | 13310.008 | 13309.7969 | 2012-10-31 |  | 2014-08-17 | 2015-01-07 | 82.67%
2014-11-30 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 64967 | Child Development Center |  | 2011-10-06 | 2012-02-27 | 57 Builders, Ltd. | W9128A-12-C-0002 | 9573.118 | 10193.638 | 2012-03-23 |  | 2013-12-13 | 2015-02-28 | 86.1%
2014-11-30 | 2011 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 65650 | Command and Control Facility, Ph 1 |  | 2011-11-04 | 2012-02-28 | Niking Corporation | W9128A-12-C-0003 | 46780 | 48950.577 | 2012-04-03 |  | 2014-04-23 | 2015-06-30 | 84.02%
2014-11-30 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 66023 | Automated Infantry Platoon Battle Course |  | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345 | 27345 | 2014-07-08 |  | 2016-09-09 | 2016-09-09 | 0%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68786 | Brigade Complex |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 24779 | 28683.795 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 99%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68786 | Brigade Complex |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC |  | 1877 | 1893.723 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 99%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68821 | Battalion Complex |  | 2010-06-23 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 29140 | 33821.435 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 99%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68821 | Battalion Complex |  | 2010-06-24 | 2011-03-28 | dck-ecc pacific, LLC |  | 1944 | 1974.141 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 99%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68822 | Battalion Complex |  | 2010-06-25 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 9103 | 10807.795 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 99%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 68822 | Battalion Complex |  | 2010-06-26 | 2011-03-28 | dck-ecc pacific, LLC |  | 737 | 753.723 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 99%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69308 | Infrastructure Expansion |  | 2010-06-27 | 2011-03-28 | dck-ecc pacific, LLC | W9128A-11-C-0004 | 58240 | 63670.64 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 98.31%
2014-11-30 | 2009 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69308 | Infrastructure Expansion |  | 2010-06-28 | 2011-03-28 | dck-ecc pacific, LLC |  | 2145 | 2492.357 | 2011-04-15 | 2014-10-31 | 2014-03-14 | 2014-10-31 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69489 | Combat Aviation Brigade Complex, Ph 1 |  | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772 | 55761.886 | 2012-07-30 |  | 2015-05-27 | 2015-06-11 | 50.29%
2014-11-30 | 2010 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69521 | Warrior in Transition (WT) Barracks |  | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | W9128A-11-C-0003 | 30812.375 | 31222.153 | 2011-07-27 | 2014-08-25 | 2013-10-12 | 2014-08-25 | 90.87%
2014-11-30 | 2010 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 69521 | Warrior in Transition (WT) Barracks |  | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. |  | 1932.995 | 1981.502 | 2011-07-14 | 2014-09-10 | 2013-10-12 | 2014-08-25 | 99.82%
2014-11-30 | 2010 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 71553 | Warrior in Transition Complex |  | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. | W9128A-11-C-0003 | 24321.069 | 24674.494 | 2011-07-27 | 2014-08-25 | 2013-10-12 | 2014-08-25 | 99.68%
2014-11-30 | 2010 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 71553 | Warrior in Transition Complex |  | 2010-05-10 | 2011-03-24 | Nordic PCL Construction, Inc. |  | 2018.561 | 2038.561 | 2011-07-14 | 2014-09-10 | 2013-10-12 | 2014-08-25 | 99.67%
2014-11-30 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76586 | Barracks |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717.476 | 30993.561 | 2013-07-23 |  | 2015-09-01 | 2015-11-21 | 49.87%
2014-11-30 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76587 | Barracks |  | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410.03 | 37733.657 | 2013-07-23 |  | 2015-09-01 | 2015-11-21 | 52.93%
2014-11-30 | 2013 | Army Active | Major Military Construction | HAWAII | UNITED STATES | 76903 | Combat Aviation Brigade Barracks |  | 2012-11-26 | 2014-05-13 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749.203 | 69749.203 | 2014-06-26 |  | 2017-01-13 | 2017-01-13 | 3.14%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67659 | Army Reserve Center |  | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21575 | 22583.9084 | 2014-01-13 |  | 2015-11-04 | 2015-12-31 | 28.22%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | ILLINOIS | UNITED STATES | 67713 | Army Reserve Center |  | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | W912QR-12-C-0068 | 13312 | 14525.3652 | 2012-10-18 |  | 2014-07-10 | 2015-05-18 | 73.7%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | INDIANA | UNITED STATES | 67673 | Army Reserve Center |  | 2012-03-13 | 2012-05-15 | Hunt Construction Group | W912QR-12-C-0029 | 44046.206 | 46654.1922 | 2012-05-30 | 2014-09-17 | 2015-01-29 | 2015-03-19 | 98.59%
2014-11-30 | 2011 | Army Reserve | Major Military Construction | IOWA | UNITED STATES | 70654 | Army Reserve Center |  | 2011-11-15 | 2012-03-14 | The Vertex Companies | W912QR-12-C-0014 | 8931.622 | 8999.53 | 2012-04-09 |  | 2013-08-12 | 2015-02-15 | 94.65%
2014-11-30 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 2728 | Physical Fitness Facility |  | 2011-12-09 | 2012-03-16 | Better Built Construction Services Inc. | W912DQ-10-D-4006 | 11660 | 11694.8087 | 2012-03-29 | 2014-11-05 | 2013-09-20 | 2014-11-05 | 98.39%
2014-11-30 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 2728 | Physical Fitness Facility |  | 2011-12-09 | 2014-07-02 | Zieson Construction Co. |  | 727.389 | 727.389 | 2015-03-13 |  | 2016-03-12 | 2016-03-12 | 0%
2014-11-30 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-08-26 | 2014-01-07 | Law Company, Inc. | W912DQ-14-C-4003 | 20078.9 | 20089.068 | 2014-02-06 |  | 2015-07-31 | 2015-07-31 | 28.7%
2014-11-30 | 2012 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-08-27 | 2012-11-01 | Arch Insurance Company |  | 5932.641 | 6058.041 | 2012-12-11 |  | 2014-03-16 | 2014-12-31 | 86.28%
2014-11-30 | 2014 | Army Active | Major Military Construction | KANSAS | UNITED STATES | 76024 | Simulations Center |  | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630 | 15630 | 2014-09-02 |  | 2016-02-24 | 2016-02-24 | 0%
2014-11-30 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 5924 | Automated Infantry Squad Battle Course |  | 2013-01-22 | 2013-06-14 | Howard W. Pence, Inc. | W912QR-13-C-0020 | 3918.0746 | 3947.5402 | 2013-09-24 | 2014-09-23 | 2014-09-24 | 2014-11-28 | 98.42%
2014-11-30 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex |  | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | W912QR-14-C-0007 | 25750 | 25750 | 2014-03-04 |  | 2015-08-26 | 2015-08-26 | 27.99%
2014-11-30 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex |  | 2012-12-07 | 2013-05-29 | Orocon-Carothers JV1 |  | 23450.6124 | 23804.1364 | 2013-07-15 |  | 2014-12-07 | 2014-12-30 | 90.78%
2014-11-30 | 2012 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 69501 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2011-12-16 | 2012-09-27 | Archer Western Federal JV | W912QR-12-C-0058 | 40397 | 45489.755 | 2012-11-05 |  | 2014-09-06 | 2014-12-14 | 90.78%
2014-11-30 | 2013 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 76239 | Unmanned Aerial Vehicle Complex |  | 2012-11-13 | 2013-05-31 | Archer Western Federal JV | W912QR-13-C-0012 | 16983 | 17359.385 | 2013-06-25 |  | 2015-04-26 | 2015-04-26 | 90.57%
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 77980 | Cantonment Area, Roads, Paved |  | 2014-08-12 | 2014-09-16 | FutureNet Group, Inc. | W912QR-09-D-0050 | 1635.599 | 1635.599 | 2014-09-24 |  | 2015-08-20 | 2015-08-20 | 2%
2014-11-30 | 2014 | Army Active | Major Military Construction | KENTUCKY | UNITED STATES | 78778 | Battlefield Weather Support Facility |  | 2013-12-24 | 2014-06-18 | TJC Engineering | W912QR-14-C-0018 | 4275.114 | 4283.952 | 2014-06-27 |  | 2015-08-21 | 2015-08-21 | 5.388%
2014-11-30 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 17220 | Fire Station |  | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12622.8 | 12644.8 | 2013-11-06 |  | 2015-11-11 | 2015-11-11 | 17.06% | 5000 | 65745
2014-11-30 | 2008 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 54785 | Child Development Center |  | 2010-12-13 | 2011-08-05 | ASSET Group, Inc. | W9127S-11-C-6011 | 7835.188 | 7946.4612 | 2011-09-23 |  | 2013-01-25 | 2015-01-23 | 92.2% | 2750 | 68772
2014-11-30 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex |  | 2011-12-16 | 2012-08-17 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 11856.9 | 12236.1292 | 2012-10-09 | 2014-11-19 | 2014-04-02 | 2014-11-19 | 91.62%
2014-11-30 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 64415 | Brigade Complex |  | 2012-02-21 | 2012-03-23 | Blackhawk Ventures, LLC |  | 10283 | 10964.2248 | 2012-05-15 |  | 2013-11-06 | 2014-12-19 | 93.88%
2014-11-30 | 2012 | Army Active | Major Military Construction | LOUISIANA | UNITED STATES | 67033 | Multipurpose Machine Gun Range |  | 2012-03-13 | 2012-08-03 | Jamco Ventures, LLC. | W9126G-09-D-0096 | 8493 | 8536.2517 | 2012-10-25 | 2014-09-30 | 2013-10-25 | 2014-08-08 | 99.13%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 81515 | CIDC FIELD OPERATIONS BUILDING |  | 2013-05-21 | 2013-09-29 | Guyco, Inc. | W9126G-09-D-0095 | 1784.466 | 1779.289 | 2013-12-04 |  | 2014-12-04 | 2015-01-03 | 78.86%
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 82268 | Illinois Ave (PREPO) Yd |  | 2014-07-22 | 2014-09-30 | Tarver Land Development, LLC | W9126G-14-C-0059 | 1748.75 | 1748.75 |  |  | 2015-03-03 | 2015-03-03 | 0%
2014-11-30 | 2010 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 60027 | Auditorium and Training Center Expansion |  | 2011-02-18 | 2011-07-08 | Grunley/Goel JV D LLC | W912DR-11-C-0027 | 7530 | 8217.982 | 2011-08-18 | 2014-07-31 | 2013-08-17 | 2014-07-30 | 98.53%
2014-11-30 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 64939 | Applied Instruction Facility |  | 2012-06-20 | 2012-09-24 | Grimberg/Amatea JV | W912DR-12-C-0023 | 30554 | 30965.465 | 2012-11-20 |  | 2014-11-20 | 2015-01-08 | 83.03%
2014-11-30 | 2012 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65755 | Brigade Complex |  | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30761.85 | 32589.148 | 2012-12-12 |  | 2015-12-12 | 2016-10-10 | 59.08% | 3500 | 34129, 52856, 64797, 65138, 69167, 69999, 71539
2014-11-30 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65793 | Indoor Firing Range |  | 2011-06-17 | 2011-09-21 | John C. Grimberg Co., Inc. | W912DR-11-C-0018 | 7241 | 8127.413 | 2011-10-13 | 2014-08-30 | 2013-04-05 | 2014-08-30 | 100%
2014-11-30 | 2011 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 65793 | Indoor Firing Range |  | 2011-06-16 | 2011-09-29 | Aisow Technologies Corporation |  | 280.9012 | 280.9012 | 2011-10-26 | 2012-01-30 | 2011-12-28 | 2012-01-30 | 100%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | MARYLAND | UNITED STATES | 68077 | Add/Alt Army Reserve Center |  | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890.05 | 7890.05 | 2014-07-30 |  | 2016-05-30 | 2016-05-30 | 0%
2014-11-30 | 2014 | Army Active | Major Military Construction | MARYLAND | UNITED STATES | 81875 | Operations and Maintenance Facilities |  | 2013-12-02 | 2014-05-12 | Edifice-Schlosser JV, LLC | W912DR-14-C-0017 | 17891 | 19635.8096 | 2014-05-23 |  | 2015-03-19 | 2015-04-29 | 35.28%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | MASSACHUSETTS | UNITED STATES | 71721 | Combat Pistol/MP Firearms Qualification |  | 2013-03-04 | 2013-08-23 | Security Construction Services, Inc. | W912QR-13-C-0025 | 3375.2884 | 3463.9844 | 2013-11-12 | 2014-09-10 | 2014-09-08 | 2014-09-26 | 100%
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 80477 | Fragmentation Simulation Lab |  | 2013-04-22 | 2013-12-13 | The Clement Group, L.L.C. | W91278-11-D-0029 | 2341.157 | 2345.214 | 2014-01-23 |  | 2015-07-17 | 2015-07-17 | 24.23%
2014-11-30 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 |  | 2013-04-11 | 2013-08-15 | Caddell Construction Co. (DE), LLC | W912DQ-13-C-4024 | 33360 | 34012.5126 | 2013-09-12 |  | 2015-09-12 | 2015-10-16 | 65.57%
2014-11-30 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 |  | 2013-01-18 | 2013-05-31 | Donald Maggi, Inc. |  | 11711 | 12144.9042 | 2013-06-25 |  | 2014-12-17 | 2015-01-26 | 90.42%
2014-11-30 | 2012 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 64365 | Vehicle Maintenance Facility |  | 2012-02-03 | 2012-08-23 | KCI Construction Company | W912DQ-12-C-4009 | 30970 | 32804.147 | 2012-09-18 | 2014-09-19 | 2014-03-12 | 2014-10-31 | 97.7%
2014-11-30 | 2012 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 64365 | Vehicle Maintenance Facility |  | 2012-02-04 | 2012-11-14 | Robinson Mechanical Contractors, Inc. |  | 8541.461 | 8570.425 |  | 2014-06-24 | 2014-08-25 | 2015-08-29 | 29.77%
2014-11-30 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 65679 | Vehicle Maintenance Shop |  | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18726.852 | 19105.258 | 2013-06-27 |  | 2015-04-08 | 2015-04-18 | 67.4%
2014-11-30 | 2013 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 66099 | Battalion Complex Facilities |  | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687 | 14517.617 | 2013-07-01 |  | 2014-12-23 | 2015-01-11 | 86.41%
2014-11-30 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 |  | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777 | 48267.396 | 2014-08-05 |  | 2016-08-04 | 2016-08-04 | 3.278%
2014-11-30 | 2014 | Army Active | Major Military Construction | MISSOURI | UNITED STATES | 75019 | Simulator Building |  | 2014-08-28 | 2014-11-06 | Zieson Construction Co. | W912DQ-15-C-4000 | 3496.695 | 3496.695 | 2014-12-01 |  | 2015-12-01 | 2015-12-01 | 0%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE |  | 2013-05-17 | 2013-07-17 | Huffman Construction, LLC |  | 1437.6 | 1423.518 | 2013-09-23 |  | 2014-06-20 | 2014-12-31 | 86.56%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | NEVADA | UNITED STATES | 67660 | Army Reserve Center/AMSA |  | 2012-12-28 | 2013-06-12 | MACNAK Korte Team LLC | W912QR-13-C-0014 | 16436.543 | 16830.4403 | 2013-07-10 |  | 2015-05-01 | 2015-05-01 | 73.16%
2014-11-30 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center |  | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959 | 6325.204 | 2013-10-23 |  | 2015-02-15 | 2015-08-03 | 66.96%
2014-11-30 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center |  | 2013-05-16 | 2012-09-28 | APS Contracting Inc. |  | 2019.198 | 2019.198 | 2012-12-04 |  | 2014-06-04 | 2015-05-15 | 77.93%
2014-11-30 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 65277 | Consolidated Dining Facility |  | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 10798.9 | 10798.9 | 2014-04-23 |  | 2015-09-30 | 2015-09-30 | 4.989%
2014-11-30 | 2009 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66725 | Ballistic Evaluation Facility Ph 1 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7201.728 | 7660.728 | 2012-12-04 | 2014-12-01 | 2014-06-04 | 2015-02-28 | 49.11%
2014-11-30 | 2010 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 66726 | Ballistic Evaluation Facility, Ph 2 |  | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757.272 | 8954.263 | 2012-12-04 |  | 2014-06-04 | 2015-05-15 | 62.92%
2014-11-30 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 69669 | Central Issue Facility |  | 2014-01-31 | 2014-06-05 | Ranco Construction, Inc. | W912QR-14-C-0021 | 8783.22 | 8783.22 | 2014-07-07 |  | 2015-12-14 | 2015-12-14 | 0.8239%
2014-11-30 | 2013 | Army Active | Major Military Construction | NEW JERSEY | UNITED STATES | 71675 | Flight Equipment Complex |  | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751 | 42814.595 | 2014-01-15 |  | 2016-01-15 | 2016-03-10 | 23.79%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71720 | Automated Infantry Squad Battle Course |  | 2012-12-13 | 2013-06-28 | Eastern Construction & Electric, Inc. | W912QR-13-C-0015 | 3093.8904 | 3311.1024 | 2013-07-17 |  | 2014-07-17 | 2015-01-06 | 92.89%
2014-11-30 | 2014 | Army Reserve | Major Military Construction | NEW JERSEY | UNITED STATES | 71769 | Modified Record Fire Range |  | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653 | 4653 | 2014-11-13 |  | 2016-05-06 | 2016-05-06 | 0%
2014-11-30 | 2011 | Army Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | 74943 | Igloo Storage, Installation |  | 2012-03-13 | 2012-07-18 | Senate Builders & Construction Managers Inc. | W912DS-12-C-0017 | 1756.106 | 1851.3294 | 2012-08-10 | 2013-10-15 | 2013-07-07 | 2014-05-15 | 99%
2014-11-30 | 2011 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 59044 | Science Facility, Ph 2 |  | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270 | 112995.901 | 2011-11-17 |  | 2015-11-14 | 2016-01-29 | 81.96%
2014-11-30 | 2009 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67579 | Add/Alt Army Reserve Center |  | 2009-02-19 | 2009-06-18 | E. W. Howell Company, Inc. | W912QR-09-C-0040 | 15041.2 | 16141.3502 | 2009-07-21 |  | 2011-07-11 | 2015-01-30 | 99%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 67691 | Army Reserve Center |  | 2011-11-16 | 2012-05-03 | SCMC, LLC | W912QR-12-C-0025 | 17931 | 18716.0068 | 2012-06-01 | 2014-05-21 | 2014-02-21 | 2015-04-30 | 94.91%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69432 | Army Reserve Center |  | 2012-12-21 | 2013-03-06 | MACNAK-Korte Design Build LLC | W912QR-13-C-0009 | 14115.817 | 13770.0623 | 2013-04-15 | 2014-11-06 | 2014-07-29 | 2014-11-06 | 97.25%
2014-11-30 | 2011 | Army Reserve | Major Military Construction | NEW YORK | UNITED STATES | 69599 | Army Reserve Center/Land |  | 2012-07-25 | 2012-09-25 | J. Kokolakis Contracting, Inc. | W912QR-12-C-0057 | 12353.9 | 12881.4 | 2012-10-25 |  | 2014-04-03 | 2015-01-14 | 99%
2014-11-30 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 79933 | Cadet Barracks |  | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 72000 | 72259.616 | 2013-08-26 |  | 2016-08-30 | 2016-10-28 | 50.2%
2014-11-30 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar |  | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 26825.868 | 27139.258 | 2013-06-27 |  | 2015-06-17 | 2015-06-17 | 32%
2014-11-30 | 2013 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar |  | 2012-12-12 | 2013-11-25 | VETCO Contracting Services, LLC |  | 21577.777 | 21390.014 | 2013-07-02 |  | 2015-06-22 | 2015-06-22 | 16%
2014-11-30 | 2014 | Army Active | Major Military Construction | NEW YORK | UNITED STATES | 81186 | Cadet Barracks, Incr 2 | 79933 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 40000 | 40119.542 | 2013-08-26 |  | 2016-07-08 | 2016-07-08 | 0%
2014-11-30 | 2012 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 43335 | NCO Academy |  | 2012-05-08 | 2012-07-30 | Caddell Construction CO., INC | W912HN-10-D-0044 | 34647 | 34719.9415 | 2012-10-03 |  | 2014-07-15 | 2014-09-28 | 99.45%
2014-11-30 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex |  | 2011-05-24 | 2011-09-23 | ACC Construction Co. Inc. | W912HN-11-C-0013 | 15752.3734 | 16600.8144 | 2011-11-21 | 2013-07-10 | 2014-01-29 | 2014-12-12 | 98.67%
2014-11-30 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 53555 | Brigade Complex |  | 2011-05-23 | 2013-04-15 | Polote Corp. |  | 10869 | 11254.7578 | 2013-04-29 | 2014-04-30 | 2013-11-25 | 2015-04-18 | 96.02%
2014-11-30 | 2011 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 57317 | Battalion Complex |  | 2011-05-23 | 2011-09-23 | Polote Corp. |  | 13850.4196 | 14717.2466 | 2012-03-15 | 2014-04-30 | 2014-01-29 | 2014-12-12 | 98.41%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 67466 | Army Reserve Center/Land |  | 2012-05-16 | 2012-09-18 | IKHANA, LL | W912QR-12-C-0055 | 15942 | 15977.219 | 2012-10-10 |  | 2014-03-19 | 2015-05-05 | 66.71%
2014-11-30 | 2014 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69624 | Command and Control Facility |  | 2014-06-10 | 2014-07-21 | Brantley Construction Services, LLC | W912HN-10-D-0056 | 4720.25 | 4726.269 | 2014-08-27 |  | 2015-08-27 | 2015-08-27 | 11.74%
2014-11-30 | 2012 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 70751 | Brigade Complex Facilities |  | 2012-04-19 | 2012-06-29 | Brantley Construction Services, LLC |  | 11681.588 | 12284.927 | 2012-07-31 | 2014-03-19 | 2014-07-21 | 2014-08-05 | 99%
2014-11-30 | 2014 | Army Reserve | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71900 | Army Reserve Center |  | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129.201 | 22129.201 | 2014-12-02 |  | 2016-11-01 | 2016-11-01 | 0%
2014-11-30 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80066 | Controlled Humidity Warehouse, Installatio |  | 2012-11-16 | 2013-09-20 | Tyler Construction Co., INC | W912HN-10-D-0060 | 6726.987 | 6769.3467 | 2013-11-06 |  | 2015-03-01 | 2015-04-08 | 53.81% | 8600 | 62955
2014-11-30 | 2013 | Army Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | 80087 | Storage Building, General Purpose |  | 2012-07-16 | 2013-03-22 | Tyler Construction Group, Inc. | W912HN-10-D-0060 | 9037.592 | 9003.526 | 2013-04-18 |  | 2014-08-11 | 2015-01-19 | 77.97% | 12600 | 76235
2014-11-30 | 2011 | Army Active | Unspecified Minor Military Construction | OHIO | UNITED STATES | 74757 | Fire Alarm System |  | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | W912QR-12-C-0050 | 1763.338 | 1782.2016 | 2012-09-05 |  | 2013-08-01 | 2015-03-20 | 78.89%
2014-11-30 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 1235 | Physical Fitness Facility |  | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23138.91 | 23149.051 | 2012-07-12 |  | 2014-04-10 | 2015-03-06 | 71.17%
2014-11-30 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 20697 | Chapel |  | 2012-01-27 | 2012-08-30 | Liberty Mutual Insurance Company | W912BV-12-C-0018 | 12999.823 | 13082.662 | 2012-09-20 |  | 2014-01-28 | 2015-04-30 | 49.53%
2014-11-30 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58207 | Railroad Tracks |  | 2011-11-29 | 2012-03-26 | McAlester Contract | W44XGQ80956921 | 6323.7745 | 6323.7745 | 2012-05-09 | 2014-12-02 | 2013-10-06 | 2014-09-15 | 0%
2014-11-30 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 58537 | Reception Station, Ph 1 |  | 2011-11-21 | 2012-05-23 | Zachry Federal Construction Corporation | W912BV-12-C-0010 | 32234.496 | 33035.398 | 2012-06-15 | 2014-10-22 | 2014-03-26 | 2014-10-22 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 64753 | Vehicle Maintenance Facility |  | 2012-01-17 | 2012-06-29 | Harper Construction Company, Inc. | W912BV-12-C-0012 | 37867.635 | 38213.797 | 2012-07-19 | 2014-08-15 | 2014-04-11 | 2014-07-03 | 85.46%
2014-11-30 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 64753 | Vehicle Maintenance Facility |  | 2012-01-17 | 2012-07-13 | GSC Construction, Inc. |  | 6094.722 | 6094.722 | 2012-09-26 |  | 2014-02-03 | 2015-09-19 | 43.9%
2014-11-30 | 2013 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 67037 | Modified Record Fire Range |  | 2012-12-07 | 2013-06-13 | Diversified Construction of Oklahoma, Inc. | W912BV-13-D-0005 | 4160.3398 | 4160.3398 | 2013-09-16 | 2014-11-03 | 2014-08-10 | 2014-09-12 | 93.08%
2014-11-30 | 2012 | Army Active | Major Military Construction | OKLAHOMA | UNITED STATES | 74690 | THAAD Instruction Facility |  | 2012-01-09 | 2012-03-29 | Roy Anderson Corp. | W912BV-12-C-0002 | 25942 | 26669.2433 | 2012-07-26 | 2014-09-02 | 2014-04-16 | 2014-10-31 | 97.15%
2014-11-30 | 2010 | Army Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | 69430 | Army Reserve Center/Land |  | 2011-07-28 | 2011-09-29 | Lobar Inc. | W912QR-11-C-0062 | 18272 | 18791.879 | 2012-01-18 |  | 2013-11-08 | 2015-04-07 | 79.13%
2014-11-30 | 2012 | Army Reserve | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 79315 | Heated Storage Building |  | 2012-11-28 | 2013-02-25 | Q.B.S., Inc. | W912QR-09-D-0018 | 1560.1607 | 1698.0767 | 2013-04-16 | 2014-05-30 | 2014-04-16 | 2015-01-30 | 97.95%
2014-11-30 | 2013 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 58970 | Trainee Barracks Complex 2, Ph 2 |  | 2013-04-29 | 2013-10-30 | ACC Construction Co., Inc | W912HP-14-C-0003 | 21786.027 | 21850.968 | 2013-12-04 |  | 2015-05-28 | 2015-06-07 | 46.63%
2014-11-30 | 2012 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 62955 | Trainee Barracks Complex, Ph 2 |  | 2012-02-22 | 2012-03-28 | CLARK CONSTRUCTION GROUP LLC | W9126G-11-D-0049 | 44267 | 48060.634 | 2012-07-23 | 2014-11-13 | 2014-01-14 | 2014-11-06 | 97.28%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 67672 | Army Reserve Center/Land |  | 2011-11-17 | 2012-03-29 | Group III Mgt. Inc | W912QR-12-C-0021 | 10122.796 | 10709.552 | 2012-05-21 | 2014-10-24 | 2013-09-23 | 2014-10-02 | 93.97%
2014-11-30 | 2010 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 69417 | Training Battalion Complex |  | 2010-02-11 | 2010-09-24 | BL Harbert International, LLC |  | 43613.85 | 49882.5857 | 2010-10-28 | 2012-11-26 | 2013-06-03 | 2014-12-31 | 97.5%
2014-11-30 | 2011 | Army Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71119 | Training Aids Center |  | 2011-06-03 | 2011-08-03 | PENTACON, LLC | W912HP-11-D-0007 | 14999.9 | 15915.2921 | 2011-09-08 | 2014-10-14 | 2013-03-01 | 2014-10-14 | 95.31%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility |  | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603 | 9101.83 | 2013-01-24 |  | 2014-07-18 | 2015-04-14 | 55.25% | 3900 | 65745
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility |  | 2012-10-23 | 2013-09-27 | Anthony & Gordon Construction Co. Inc. |  | 4150 | 4150 | 2013-01-24 |  | 2014-07-18 | 2015-04-14 | 32.61%
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 57434 | Indoor Swimming Pool |  | 2011-08-08 | 2011-09-14 | Megen Construction Company, Inc. | W912DY-11-D-0039 | 13606.4 | 13808.217 | 2011-10-18 | 2013-05-09 | 2013-01-08 | 2013-05-09 | 99%
2014-11-30 | 2010 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 64209 | Access Control Point and Road Improvements |  | 2010-01-15 | 2010-07-15 | Liberty A / Vertex | W9128F-10-C-0056 | 9839.658 | 11751.452 | 2010-08-03 | 2012-10-31 | 2012-01-25 | 2014-09-30 | 98.17%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex |  | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503 | 39614.9008 | 2012-09-05 |  | 2014-07-28 | 2015-06-30 | 70.01%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex |  | 2012-07-19 | 2013-01-07 | Turner Strategic Technologies, LLC |  | 8195.202 | 8267.659 | 2013-03-08 |  | 2014-11-28 | 2015-02-25 | 81.75%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 |  | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | W9126G-12-C-0015 | 40532.114 | 40793.3202 | 2012-04-24 |  | 2014-04-24 | 2015-07-10 | 66.59%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 |  | 2011-12-24 | 2014-03-04 | Alamo City Constructors, Inc. |  | 35.6595 | 43.1903 | 2014-03-04 | 2014-06-16 | 2014-06-02 | 2014-06-16 | 99%
2014-11-30 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 66911 | Multipurpose Machine Gun Range |  | 2012-12-21 | 2013-05-13 | Blackhawk Ventures, LLC | W9126G-09-D-0093 | 6397 | 6434.605 | 2013-06-10 | 2014-06-27 | 2014-07-05 | 2014-07-10 | 99%
2014-11-30 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 67020 | Modified Record Fire Range |  | 2012-11-30 | 2013-05-31 | Better Built Construction Services, Inc | W912DY-12-D-0026 | 4094.684 | 4099.3545 | 2013-08-02 | 2014-09-16 | 2014-09-05 | 2014-09-05 | 85%
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 67194 | Simulations Center |  | 2010-11-18 | 2011-05-31 | Blackhawk Ventrues, LLC | W9126G-09-D-0093 | 14554.1 | 15176.5831 | 2012-04-10 | 2014-09-15 | 2013-08-09 | 2014-07-31 | 98.17%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 68993 | Electronics Maintenance Facility |  | 2011-12-16 | 2012-03-30 | Walbridge Aldinger Company | W912BV-12-C-0003 | 9573 | 9589.672 | 2012-08-08 | 2014-07-14 | 2013-12-16 | 2014-07-14 | 100%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 68993 | Electronics Maintenance Facility |  | 2011-12-17 | 2013-09-20 | Venegas Engineering & Management Construction Company |  | 5117.965 | 5117.965 | 2012-08-08 |  | 2014-05-05 | 2014-12-30 | 97.76%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69286 | Infrastructure |  | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008.411 | 8732.566 | 2012-08-20 |  | 2013-09-13 | 2014-12-30 | 97.56%
2014-11-30 | 2011 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 69421 | Army Reserve Center/Land |  | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4454 | 4454 | 2012-08-21 |  | 2014-03-21 | 2015-12-31 | 6.893%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 69828 | Unmanned Aerial Vehicle Maintenance Hangar |  | 2013-07-16 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 8829.807 | 8829.807 | 2014-08-27 |  | 2016-01-04 | 2016-01-18 | 0%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 70514 | Vehicle Maintenance Facility |  | 2011-12-15 | 2012-03-30 | Urban Associates, Inc. | W912BV-12-C-0005 | 9815.87 | 10561.552 | 2012-05-30 | 2014-04-30 | 2013-09-13 | 2014-01-10 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 70514 | Vehicle Maintenance Facility |  | 2011-12-15 | 2014-05-07 | J&M Contractors |  | 3921.5 | 3931.5 | 2013-10-17 | 2014-03-07 | 2014-05-05 | 2014-06-14 | 99%
2014-11-30 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71120 | Training Aids Center |  | 2013-03-08 | 2013-09-04 | PENTACON, LLC | W912DY-12-D-0030 | 21912 | 22001.757 | 2013-10-17 |  | 2015-04-10 | 2015-05-25 | 28.9%
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex |  | 2011-01-24 | 2011-09-30 | JAMA Constructors | W912HN-11-D-0035 | 6572.777 | 8448.4512 | 2012-07-30 |  | 2014-01-21 | 2015-01-05 | 89.68%
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71462 | Battalion Complex |  | 2011-08-02 | 2012-06-29 | Sundt Construction Inc |  | 8779.712 | 9297.0101 | 2012-06-19 | 2014-05-19 | 2013-11-11 | 2015-01-31 | 96.92%
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71465 | Company Operations Facilities |  | 2011-03-21 | 2011-09-29 | MW Builders | W912HN-11-D-0035 | 3048.91 | 3461.2134 | 2012-06-19 | 2014-04-14 | 2013-11-11 | 2015-08-09 | 90.04%
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71465 | Company Operations Facilities |  | 2010-12-16 | 2012-06-29 | Sundt Construction Inc |  | 289.3681 | 362.8121 | 2011-07-13 | 2013-01-07 | 2013-01-03 | 2013-01-24 | 98.63%
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex |  | 2012-12-19 | 2011-09-29 | MW Builders | W9126G-13-C-0061 | 11652.378 | 12094.0635 | 2012-06-19 | 2014-05-05 | 2013-11-11 | 2014-09-11 | 98.99% | 3289 | 65745
2014-11-30 | 2011 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71639 | Brigade Complex |  | 2012-12-19 | 2013-09-30 | Bristol General Contractors, LLC |  | 15175 | 15225 | 2013-11-06 |  | 2015-01-30 | 2015-03-19 | 21%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 9669.4345 | 10104.662 | 2012-06-22 |  | 2013-12-14 | 2014-09-11 | 86.85%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility |  | 2011-12-19 | 2013-12-04 | STREETER-SUMMIT JV 1, LLC |  | 5786.309 | 5786.309 | 2014-01-15 |  | 2015-01-25 | 2015-02-14 | 32.96%
2014-11-30 | 2010 | Army Reserve | Major Military Construction | TEXAS | UNITED STATES | 75110 | Tactical Equipment Maintenance Facility |  | 2011-10-04 | 2012-01-26 | Leetex Construction LLC | W912QR-12-C-0010 | 9433.577 | 9433.577 | 2012-04-05 |  | 2013-09-12 | 2014-12-18 | 95.57%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility |  | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7472.9455 | 7802.2463 | 2012-06-22 |  | 2013-12-14 | 2014-08-31 | 84.45%
2014-11-30 | 2012 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility |  | 2011-12-19 | 2013-12-04 | STREETER-SUMMIT JV 1, LLC |  | 5378.708 | 4774.586 | 2014-01-15 |  | 2015-07-09 | 2015-07-29 | 99%
2014-11-30 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex |  | 2013-04-25 | 2013-08-15 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491.27 | 11423.509 | 2013-10-07 |  | 2015-05-30 | 2015-06-15 | 54.94%
2014-11-30 | 2013 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex |  | 2013-03-12 | 2014-05-29 | JAM-MAP JV |  | 5994.434 | 5994.434 | 2014-08-27 |  | 2016-01-04 | 2016-01-04 | 68.03%
2014-11-30 | 2014 | Army Active | Major Military Construction | TEXAS | UNITED STATES | 81155 | Unmanned Aerial Vehicle Complex |  | 2014-05-02 | 2014-07-24 | Archer Western Federal JV | W9126G-14-P-0032 | 30197 | 30197 |  |  | 2016-04-23 | 2016-04-23 | 0%
2014-11-30 | 2012 | Army Active | Major Military Construction | UTAH | UNITED STATES | 55823 | Life Sciences Test Facility Addition |  | 2012-04-12 | 2012-07-26 | Big-D Construction Corp | W91238-12-C-0024 | 22608.566 | 29440.871 | 2012-08-29 |  | 2015-02-15 | 2015-12-03 | 77.06%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | UTAH | UNITED STATES | 81106 | POLICE/MP STATION |  | 2013-06-11 | 2013-09-27 | Zumwalt Construction, Inc. | W91238-11-D-0026 | 1768.28 | 1768.28 | 2013-10-18 |  | 2014-12-17 | 2015-03-23 | 32.31%
2014-11-30 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650 | 46659.0739 | 2013-10-15 |  | 2015-10-15 | 2015-10-15 | 51.68%
2014-11-30 | 2013 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 |  | 2013-07-17 | 2014-09-03 | VISTA Construction LLC |  | 4055.4 | 4055.4 | 2014-09-16 |  | 2015-09-16 | 2015-09-16 | 0.8077%
2014-11-30 | 2014 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 53584 | Adv Individual Training Barracks Cplx, Ph3 |  | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036.48 | 40036.48 | 2014-10-09 |  | 2017-07-05 | 2017-07-05 | 0%
2014-11-30 | 2010 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 53663 | Upgrade Marshalling Area |  | 2010-07-28 | 2010-09-29 | Leebcor Services, LLC | W91236-08-D-0077 | 6330.28 | 7129.33 | 2010-11-04 | 2012-11-27 | 2011-11-14 | 2014-11-27 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 57508 | Information Dominance Center, Ph 1 |  | 2013-03-15 | 2013-07-22 | Hensel Phelps Construction Co. | W912DR-13-C-0035 | 39700.01 | 40664.2065 | 2013-08-19 |  | 2015-03-12 | 2015-04-24 | 65.92%
2014-11-30 | 2012 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 59005 | Aviation Training Facility |  | 2012-03-20 | 2012-05-16 | Oyster Point Construction Company | W91236-12-C-0035 | 13849 | 14321.249 | 2012-06-14 | 2014-09-25 | 2013-12-06 | 2014-06-14 | 99%
2014-11-30 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 61453 | Replace Fire Station |  | 2012-08-06 | 2013-05-23 | TMG SERVICES, INC. Linda Frazier | W912DR-13-C-0030 | 6189 | 6378.06 | 2013-06-05 |  | 2014-11-27 | 2015-05-15 | 54.8% | 2580 | 68961
2014-11-30 | 2011 | Army Active | Major Military Construction | VIRGINIA | UNITED STATES | 65789 | Indoor Firing Range |  | 2011-11-14 | 2012-01-03 | Jordan-Versar, LLC | W91236-08-D-0056 | 6520 | 6749.174 | 2012-01-20 | 2013-10-24 | 2013-10-21 | 2013-10-24 | 99%
2014-11-30 | 2011 | Army Reserve | Major Military Construction | VIRGINIA | UNITED STATES | 70641 | Army Reserve Center/Land |  | 2011-08-18 | 2011-11-23 | Anthony & Gordon Construction Co, Inc. | W912QR-12-C-0004 | 13345 | 13570.305 | 2012-01-12 | 2014-10-31 | 2013-05-06 | 2014-10-31 | 98.83%
2014-11-30 | 2010 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 74885 | Fire Station |  | 2011-08-25 | 2012-07-17 | ARGO SYSTEMS, LLC | W912DR-12-C-0010 | 1636.889 | 1647.659 | 2012-08-03 | 2014-07-29 | 2014-01-25 | 2014-04-25 | 99%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80317 | WATER DISTRIBUTION LINES, POTABLE |  | 2013-08-14 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1790.839 | 1790.839 | 2014-01-13 | 2014-12-10 | 2014-09-10 | 2014-12-10 | 6.234%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 81629 | AIR CONDITIONING/REFRIGERATION PLANT |  | 2013-07-15 | 2013-09-27 | Team Henry Enterprises, LLC |  | 1089.1834 | 1132.5334 | 2013-10-17 | 2014-11-11 | 2014-08-13 | 2014-11-11 | 90.95%
2014-11-30 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 54106 | Automated Multipurpose Machine Gun Range |  | 2013-12-24 | 2014-05-28 | TSS-Garco Joint Venture | W912DW-14-C-0012 | 7716 | 7716 | 2014-08-18 |  | 2016-02-09 | 2016-02-09 | 0.6%
2014-11-30 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 58046 | Operational Readiness Training Cplx, Ph 1 |  | 2012-06-29 | 2013-04-01 | TSS-Garco Joint Venture | W912DW-12-C-0043 | 16416 | 16268.76 | 2013-05-21 |  | 2014-11-12 | 2015-03-25 | 49.71%
2014-11-30 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex |  | 2012-08-14 | 2012-09-21 | 3D Contracting Inc. | W9126G-08-D-0045 | 19332 | 19731.034 | 2012-11-30 | 2014-11-09 | 2014-05-24 | 2014-10-10 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 64014 | Battalion Complex |  | 2013-07-29 | 2013-09-26 | MEGEN Construction Company, Inc. |  | 7295 | 3293 | 2013-10-15 |  | 2015-04-08 | 2015-04-08 | 43%
2014-11-30 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 |  | 2012-08-18 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775.4 | 14557.3098 | 2013-03-04 |  | 2014-08-26 | 2015-03-20 | 90.45%
2014-11-30 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 |  | 2014-03-12 | 2014-06-20 | Vet Industrial, Inc. |  | 10525 | 12521.074 | 2014-08-06 | 2014-08-01 | 2015-09-10 | 2015-09-10 | 80.33%
2014-11-30 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 67545 | Convoy Live Fire Range |  | 2013-05-16 | 2013-08-22 | Vet Industrial Inc. | W912DW-10-D-1021 | 4990.675 | 5406.016 | 2013-09-10 |  | 2015-01-03 | 2015-01-03 | 91.16%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | WASHINGTON | UNITED STATES | 67715 | Army Reserve Center |  | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31219 | 31269.786 | 2013-07-11 |  | 2015-08-30 | 2015-08-30 | 58.56%
2014-11-30 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex |  | 2011-05-02 | 2011-09-26 | Garco Construction, Inc. | W912DW-13-C-0020 | 36247 | 37009.146 | 2013-02-13 |  | 2014-08-07 | 2014-08-07 | 87.91%
2014-11-30 | 2011 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex |  | 2014-08-15 | 2014-09-26 | Wm. Dickson Company |  | 8893.541 | 11287.2752 | 2014-05-20 | 2013-12-20 | 2015-10-11 | 2015-10-11 | 99%
2014-11-30 | 2010 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 74408 | Ft Lewis-McChord AFB Joint Access |  | 2013-05-10 | 2013-08-29 | TSS-Garco Joint Venture | W912DW-13-C-0040 | 7327 | 7645.264 | 2013-09-25 |  | 2015-01-28 | 2015-01-28 | 71.67%
2014-11-30 | 2013 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 75165 | Waste Water Treatment Plant |  | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77476.628 | 77926.828 | 2014-03-03 |  | 2016-03-02 | 2016-03-02 | 19.72%
2014-11-30 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B |  | 2012-08-20 | 2012-09-28 | CJW Construction, Inc. | W912DW-12-C-0051 | 12950.4 | 13974.8006 | 2012-11-29 | 2014-10-14 | 2014-05-23 | 2014-12-15 | 99%
2014-11-30 | 2012 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B |  | 2013-12-04 | 2014-04-08 | Glen/Mar Construction, Inc. |  | 4771.02 | 4810.946 | 2014-05-21 |  | 2015-05-21 | 2015-05-31 | 10.92%
2014-11-30 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar |  | 2014-06-25 | 2014-08-26 | Archer Western Federal JV | W912DW-14-C-0023 | 36998 | 36998 | 2014-09-23 |  | 2016-03-16 | 2016-03-16 | 0.5662%
2014-11-30 | 2014 | Army Active | Major Military Construction | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar |  | 2014-05-19 | 2014-09-03 | The Renew Group, Inc. |  | 1106.039 | 1106.039 | 2014-10-24 |  | 2015-04-22 | 2015-04-22 | 0%
2014-11-30 | 2011 | Army Reserve | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 79128 | DEPMEDS |  | 2013-03-26 | 2013-09-30 | Imperial Construction | W912QR-13-C-0046 | 1560.895 | 1652.152 | 2013-10-11 |  | 2014-09-26 | 2014-12-15 | 68.93%
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80919 | Underground Electric Lines |  | 2014-08-12 | 2014-09-29 | Glen/Mar Construction, Inc. | W912DW-14-C-0029 | 1544.779 | 1544.779 |  |  | 2015-10-29 | 2015-10-29 | 0%
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81320 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL |  | 2013-08-08 | 2013-09-26 | Northcon, Inc. | W912DW-13-C-0047 | 1380.171 | 1380.171 | 2013-10-28 |  | 2014-10-28 | 2014-10-28 | 79.94%
2014-11-30 | 2012 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 67684 | Container Loading Facility |  | 2011-11-17 | 2012-03-30 | Carntribe-Clement 3, A Joint Venture | W912QR-12-C-0023 | 5049.662 | 5206.7425 | 2012-06-27 | 2014-08-06 | 2013-10-30 | 2014-11-15 | 99%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 67689 | Central Issue Facility |  | 2013-01-28 | 2013-06-14 | KEPA-TCI JV LLC | W912QR-13-C-0016 | 9302.203 | 9461.4485 | 2013-07-08 |  | 2014-11-10 | 2015-05-04 | 54.82%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71997 | Dining Facility |  | 2013-01-22 | 2013-08-23 | TCI Architects Engineers Contractor Inc. | W912QR-13-C-0026 | 7738.253 | 7787.9736 | 2013-10-02 |  | 2015-02-04 | 2015-03-25 | 29.12%
2014-11-30 | 2014 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 71999 | NCO Academy Dining Facility |  | 2013-12-12 | 2014-03-31 | Wilson Brigadier Joint Venture | W912QR-14-C-0013 | 5900 | 5900 | 2014-04-22 |  | 2015-08-25 | 2015-08-25 | 22.14%
2014-11-30 | 2013 | Army Reserve | Major Military Construction | WISCONSIN | UNITED STATES | 72088 | ECS TEMF |  | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19021.6 | 19084.545 | 2013-07-08 |  | 2015-06-08 | 2015-06-08 | 43.02%
2014-11-30 | 2014 | Army Active | Military Family Housing | WISCONSIN | UNITED STATES | 74861 | Family Housing New Construction |  | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862.0909 | 21862.0909 | 2014-08-20 |  | 2016-08-09 | 2016-08-09 | 2.743%
2014-11-30 | 1905-07-04 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79652 | Radar Security and Support Facilities |  | 2012-05-25 | 2012-08-20 | American Assurance Underwriters Group |  | 3800 | 4171.3837 | 2012-09-27 |  | 2013-07-24 |  | 81.75%
2014-11-30 | 1905-07-04 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79652 | Radar Security and Support Facilities |  | 2014-07-14 | 2014-07-28 | American Int'l Contractors Inc |  | 1366.6 | 1366.6 | 2014-07-29 |  | 2014-11-30 | 2014-11-30 | 82%
2014-11-30 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79749 | Forward Operating Site |  | 2012-06-15 | 2012-08-17 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129.1464 | 12151.695 | 2013-12-05 |  | 2015-04-29 | 2015-07-31 | 28.13%
2014-11-30 | 2012 | Army Active | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79749 | Forward Operating Site |  | 2012-06-15 | 2012-08-17 | PIRIL INSAAT TIC. BILG. ELEKTR. BURO. DONANIMLARI A.S. |  | 198.982 | 198.982 | 2013-12-05 | 2013-10-17 | 2015-04-29 | 2015-07-31 | 99%
2014-11-30 | 2009 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010154 | Multipurpose Machine Gun Range |  | 2009-04-28 | 2009-05-05 | HDH General Contractors, Inc. | AC-09-C-0014-S | 2671 | 1636 | 2009-05-11 | 2011-11-21 | 2011-11-16 | 2011-11-16 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130109 | Armed Forces Reserve Center |  | 2009-09-09 | 2009-09-09 | New South Construction Company, Inc. | 41100-044-0000070579 | 36015 | 27900 | 2009-09-21 | 2011-11-01 | 2011-04-11 | 2013-09-24 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230070 | Regional Training Institute, PH 1 |  | 2009-04-08 | 2009-04-16 | Nickerson & O'Day, Inc. | 230070-D | 18713 | 14314 | 2009-05-18 | 2011-06-13 | 2011-06-13 | 2011-06-13 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240189 | Army Aviation Support Facility, Add/Alt |  | 2009-05-05 | 2009-09-28 | Tetra-Tech Facilities Construction, LLC | W912K6-09-C-0002 | 27603 | 27193 | 2010-03-01 | 2012-06-01 | 2010-09-27 | 2012-06-30 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Project has claim with ASBC and claim has not been finalized, schedule to go to trial in Oct 15
2014-11-30 | 2009 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260212 | Infantry Squad Battle Course |  | 2009-08-19 | 2009-09-02 | The Garrison Company | Y09127 | 2000 | 2167 | 2009-09-07 | 2010-06-30 | 2010-05-18 | 2010-05-18 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270260 | Readiness Center |  | 2009-08-04 | 2009-08-07 | Holte/Graham, JV | W912LM-09-C-0005 | 13390 | 12529 | 2009-08-10 | 2011-12-01 | 2010-12-14 | 2013-05-31 | 99% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320069 | Readiness Center |  | 2011-10-27 | 2012-06-01 | Nevada State Public Works | W9124X-11-2-2001 | 11246 | 7762 | 2012-06-11 | 2013-04-30 | 2013-07-12 | 2013-03-27 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2014-11-30 | 2009 | Army National Guard | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 320152 | Paint Booth |  | 2009-06-04 | 2009-09-01 | Nevada State Public Works | W9124X-09-2-2003 | 1500 | 1075 | 2009-09-16 | 2012-05-24 | 2012-05-21 | 2012-05-21 | 100% | 0 |  | Congressionally Directed
2014-11-30 | 2009 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360191 | Maneauver Area Training and Equipment Site, PH 3 |  | 2009-09-04 | 2009-09-30 | Beardsley Design Associates | DAHA30-00-0009 | 10879 | 9544 | 2010-03-10 | 2012-09-30 | 2011-03-09 | 2013-04-11 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Unspecified Minor Military Construction | OHIO | UNITED STATES | 390270 | Ravenna TTB Utilities |  | 2009-12-15 | 2010-01-28 | Portage County Water Resources Department |  | 1600 | 1600 | 2011-11-01 | 2012-02-22 | 2012-01-30 | 2012-12-06 | 100% | 0
2014-11-30 | 2009 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420511 | Readiness Center, Add/Alt |  | 2011-08-31 | 2011-09-15 | Lobar Incorporated | DGS 961-20.1 | 6117 | 5738 | 2011-09-26 | 2013-08-15 | 2012-10-30 | 2014-12-31 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440039 | Army Aviation Support Facility, Add/Alt (additional funds for FY08 project) |  | 2008-07-09 | 2008-09-25 | Bacon Construction Co., Inc. | W912LD-08-C-0036 | 4848 | 4150 | 2009-01-09 | 2012-01-06 | 2011-01-09 | 2014-07-31 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460077 | Armed Forces Reserve Center |  | 2009-03-31 | 2009-04-17 | J Scull Construction | W912MM-04-2-2001 | 28762 | 27822 | 2010-04-05 | 2011-06-24 | 2011-11-14 | 2011-11-14 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460132 | Barracks/Dining/Admin & Parking Complex, PH1 |  | 2009-06-11 | 2009-06-24 | J Scull Construction | W912-MM-09-2-2001 | 12765 | 11645 | 2009-08-10 | 2011-03-02 | 2010-12-15 | 2010-12-15 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | TENNESSEE | UNITED STATES | 470043 | Readiness Center |  | 2009-09-16 | 2009-09-25 | Sain Construction Co. | W912L7-09-C-0008 | 8787 | 7706 | 2009-10-01 | 2011-09-15 | 2011-01-21 | 2011-07-05 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490101 | Ammunition Supply Point |  | 2009-09-17 | 2009-09-18 | Creative Times Inc. |  | 13843 | 12045 | 2009-09-21 | 2011-07-30 | 2010-10-01 | 2010-10-01 | 100% | 2358 | 540205 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530012 | Readiness Center |  | 2009-09-11 | 2009-09-11 | Wade Perrow Construction, LLC | W912K3-09-C-0001 | 30265 | 24954 | 2009-09-12 | 2011-07-28 | 2011-01-31 | 2011-01-31 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540105 | Joint Interagency Training Education Center, PH 1 |  | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | DEFK10003 | 69711 | 72200 | 2009-10-01 | 2011-09-30 | 2011-09-28 | 2014-09-30 | 99% | 0 |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Generator work being completed
2014-11-30 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540205 | Access Control Point |  | 2009-09-25 | 2009-09-25 | DanHill Construction | DEFK13007 | 3823 | 3694 | 2013-05-01 | 2013-12-16 | 2013-12-11 | 2014-02-28 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Formal Reprogramming $2,358 funds from FY09 project savings {PN: 490101}, PM Assigned
2014-11-30 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540206 | Multi-Purpose Building, PH II |  | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | DEFK10004 | 4755 | 4624 | 2010-02-01 | 2010-08-30 | 2010-08-26 | 2013-03-31 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2014-11-30 | 2009 | Army National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | 540208 | Tri-State Armory Addition |  | 2009-04-24 | 2009-09-23 | Neighborgall Construction Company |  | 2000 | 2000 | 2009-10-01 | 2010-08-11 | 2010-07-16 | 2010-08-31 | 100% | 0 |  | Congressionally Directed, PM Assigned
2014-11-30 | 2010 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010279 | Urban Assault Course |  | 2010-09-06 | 2010-09-10 | Baggette Construction, Inc. | AC-10-C-0045-S | 2980 | 2396 | 2010-12-01 | 2011-10-11 | 2011-08-08 | 2011-08-08 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040227 | Combat Pistol Qualification Course |  | 2010-06-14 | 2010-06-15 | Norquay Construction | M10-0015 | 2964 | 1867 | 2010-06-28 | 2011-07-15 | 2010-12-31 | 2010-12-31 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060115 | Readiness Center, PH 1 |  | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | W912LA-10-C-0009 | 30711 | 23127 | 2010-11-15 | 2013-10-07 | 2012-02-06 | 2014-10-31 | 97% | 2900 | 390263 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | GUAM | GUAM | 140300 | Readiness Center |  | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | N40192-10-C-1335 | 20766 | 20797 | 2010-05-03 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 95% | 3000 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170611 | Readiness Center, Add/Alt |  | 2010-09-17 | 2010-09-22 | Capital Development Board | W91SMC-10-2-2001-100 | 5560 | 4319 | 2010-10-18 | 2012-03-31 | 2011-09-14 | 2011-09-14 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210291 | Readiness Center |  | 2010-06-07 | 2010-08-16 | A & K Construction Company, Inc. | CT2 785 1000000319 1 | 10483 | 10024 | 2010-08-23 | 2012-04-14 | 2011-08-28 | 2011-08-28 | 100% | 0 |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230114 | Regional Training Institute, PH II |  | 2010-08-11 | 2010-09-21 | Nickerson & O'Day, Inc. | 230070-D | 15464 | 14399 | 2010-09-21 | 2012-08-17 | 2012-07-21 | 2014-01-31 | 100% | 0 |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250087 | Armed Forces Reserve Center (JFHQ) |  | 2010-06-07 | 2010-06-25 | CTA Construction |  | 27595 | 26247 | 2010-07-12 | 2012-01-15 | 2011-10-19 | 2014-04-30 | 100% | 2000 | 060413 | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260213 | Organizational Maintenance Shop (ADRS) |  | 2010-08-04 | 2010-09-22 | LD Dosca Associates, Inc. | W912JB-09-D-2014 | 7722 | 7419 | 2010-10-01 | 2012-03-01 | 2011-10-18 | 2011-10-18 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Unspecified Minor Military Construction | MICHIGAN | UNITED STATES | 260232 | Dining Facility |  | 2010-07-09 | 2010-09-23 | Ripman Construction Co., Inc. | Y10342 | 1998 | 1991 | 2010-10-01 | 2011-06-27 | 2011-09-30 | 2011-12-01 | 100% | 0
2014-11-30 | 2010 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270252 | Urban Assault Course |  | 2011-07-11 | 2011-08-18 | Saginaw Contracting, Inc. | W912LM-10-D-0016 | 1693 | 1192 | 2011-08-22 | 2012-07-18 | 2013-03-18 | 2014-07-18 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270261 | Readiness Center, PH 2 |  | 2010-08-30 | 2010-09-07 | MAVCON | W912LM-10-C-0003 | 3079 | 2855 | 2010-09-27 | 2012-05-01 | 2011-07-18 | 2013-05-31 | 100% | 3500 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($3,184)
2014-11-30 | 2010 | Army National Guard | Unspecified Minor Military Construction | MINNESOTA | UNITED STATES | 270263 | CST, Add/Alt |  | 2011-08-09 | 2011-08-19 | LS Black Constructors | W912LM-10-D-0004 | 1954 | 1897 | 2011-09-12 | 2012-11-20 | 2012-08-24 | 2013-12-20 | 100% | 0
2014-11-30 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320143 | Readiness Center |  | 2010-09-27 | 2010-09-27 | The Penta Building Company |  | 25807 | 19910 | 2010-10-25 | 2013-05-01 | 2012-01-23 | 2013-04-19 | 99% | 3112 | 060413 | PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320197 | Renewable Energy Sustainable Projects |  | 2010-09-21 | 2010-09-24 | Ray Heating Products Inc. | W9124X-10-2-2001 | 1997 | 1899 | 2010-10-04 | 2011-10-26 | 2011-04-04 | 2011-04-04 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350043 | Army Aviation Support Facility |  | 2010-06-29 | 2010-07-02 | PCL Construction Services Inc. | W912PP-10-C-0022 | 35577 | 31835 | 2010-09-13 | 2012-03-20 | 2011-09-14 | 2011-09-14 | 100% | 3300 | 080067 | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370896 | Readiness Center, Add/Alt |  | 2010-09-07 | 2010-09-10 | Architectural Design Studio |  | 2501 | 2033 | 2010-09-27 | 2011-10-13 | 2011-09-30 | 2011-10-17 | 99% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380120 | Dike Construction |  | 2010-07-26 | 2010-07-26 | Ames Construction |  | 1569 | 1818 | 2010-11-01 | 2012-08-13 | 2012-08-20 | 2014-08-30 | 100% | 0 |  | NGB 593 will be completed once the Dept of Transportation asks for final payment
2014-11-30 | 2010 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410120 | Readiness Center |  | 2010-09-14 | 2010-09-21 | Lease Crutcher Lewis | 410120D002 | 12093 | 11893 | 2010-10-08 | 2012-09-01 | 2012-12-01 | 2012-12-01 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410820 | Water Supply Company |  | 2010-09-10 | 2010-09-21 | Hoffman Construction Company | 410820D002 | 3369 | 3368 | 2010-10-01 | 2011-08-01 | 2011-10-02 | 2011-10-02 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | UNITED STATES | 436019 | Urban Assault Course |  | 2009-12-01 | 2010-09-29 | Remex Co. | W912LR-10-B-0001 | 1669 | 1846 | 2010-10-01 | 2011-10-03 | 2011-09-23 | 2011-09-23 | 100% | 0 |  | Congressionally Directed
2014-11-30 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450252 | Army Aviation Support Facility, Add/Alt |  | 2010-07-12 | 2010-07-14 | Willis Mechanical, Inc. |  | 14627 | 14078 | 2011-02-07 | 2013-04-15 | 2011-12-14 | 2013-05-01 | 99% | 11000 | 090115, 220241 and 220243 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($14,759)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450353 | Army Aviation Support Facility |  | 2010-09-23 | 2010-09-24 | Hendrick Construction | 460114576 | 27500 | 27304 | 2010-11-17 | 2013-06-21 | 2012-08-10 | 2013-06-21 | 75% | 12100 | 220241, 220243, and 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($27,9369)
2014-11-30 | 2010 | Air National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460141 | Joint Force HQ Readiness Center, Supplemental |  | 2010-08-26 | 2010-09-03 | J. Scull Construction Services, Inc. | W912MM-09-2-2003 | 5308 | 5257 | 2010-09-27 | 2012-04-14 | 2012-04-14 | 2012-04-14 | 100% | 2500 | 530035 | Congressional Add, PL 112-25 (Budget Control Act, 2011)/2853 Notification ($5,705), Delays in getting LEED Certification, State holding funds from A-E for this. Tentative submission date is May 2015
2014-11-30 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480175 | Armed Forces Reserve Center |  | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 16441 | 14196 | 2011-01-01 | 2012-07-17 | 2012-06-15 | 2013-11-04 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480176 | Field Maintenance Shop, Joint |  | 2010-09-23 | 2010-09-27 | Satterfield & Pontikes Construction, Inc. | TX10-ENG-25 | 5700 | 7021 | 2011-01-01 | 2012-07-17 | 2013-06-15 | 2013-11-04 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | VIRGINIA | UNITED STATES | 510302 | Regional Training Institute, PH 2 |  | 2010-01-27 | 2010-02-26 | Barton Marlow Company | W91236-08-C-0079-P00001 | 31946 | 30249 | 2010-07-01 | 2011-07-06 | 2012-09-10 | 2012-08-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | VIRGIN ISLAND | VIRGIN ISLANDS, U.S. | 520014 | Regional Training Institute, PH 1 |  | 2010-04-12 | 2010-04-23 | Tip Top Construction, Inc. | W9127P-10-C-0001 | 19978 | 19493 | 2010-07-01 | 2013-02-15 | 2012-02-20 | 2013-04-23 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540217 | Readiness Center Addition/Life Safety Upgrades |  | 2010-09-24 | 2010-09-26 | Hayslett Construction Company | DEFK11013 | 1073 | 1135 | 2010-10-01 | 2011-10-21 | 2011-09-18 | 2011-09-18 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040023 | Readiness Center |  | 2011-08-01 | 2011-09-01 | Haydon Building Corporation-Tem | M11-31 | 16446 | 16320 | 2011-09-19 | 2013-03-19 | 2012-12-14 | 2013-03-19 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050043 | Combined Support Maintenance Shop |  | 2011-06-24 | 2011-07-01 | CDI Contractor, LLC | 970816 | 29887 | 28574 | 2011-11-01 | 2013-08-15 | 2013-07-01 | 2013-10-01 | 95% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050163 | Combined Arms Collective Training Facility |  | 2010-12-21 | 2011-05-23 | Crossland Construction Company, Inc. | 9751022 | 18609 | 7413 | 2011-09-19 | 2013-06-13 | 2012-03-23 | 2013-10-15 | 99% | 6500 | 530035 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($8,858)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050173 | Live Fire Shoot House |  | 2011-05-26 | 2011-06-14 | Ross Sparks Builders, Inc. | 9751028 | 2488 | 2267 | 2011-07-01 | 2012-09-18 | 2012-06-07 | 2013-10-15 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060429 | Combined Arms Collective Training Facility |  | 2011-05-12 | 2011-09-20 | Cox Construction Company | W912LA-11-R-0005 | 12025 | 11525 | 2011-12-05 | 2013-06-15 | 2012-06-29 | 2013-09-27 | 99% | 6700 | 361103 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,379)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080062 | HAATS/AASF |  | 2011-05-19 | 2011-07-13 | Hensel Phelps Construction Company |  | 38862 | 37413 | 2011-11-01 | 2013-04-01 | 2013-03-31 | 2013-10-31 | 95% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080067 | Regional Training Institute |  | 2011-07-21 | 2011-09-15 | Mass Service & Supply, LLC |  | 39916 | 50926 | 2011-10-01 | 2013-10-01 | 2014-10-18 | 2014-10-03 | 95% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2,000 Formal Reprogramming $9,300 funds from FY10 project savings {PNs: 160120 ($6,000) & 350043 ($3,300)}
2014-11-30 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080201 | Readiness Center |  | 2011-08-12 | 2011-09-16 | Smith Construction Management, LLC |  | 19934 | 18999 | 2011-12-01 | 2013-10-01 | 2013-09-30 | 2014-09-10 | 98% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080202 | Readiness Center |  | 2011-08-05 | 2011-08-16 | AP Mountain States |  | 7485 | 7469 | 2011-12-01 | 2012-11-01 | 2012-10-19 | 2012-10-19 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-11-30 | 2011 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090010 | Readiness Center (Aviation) |  | 2011-05-27 | 2011-09-22 | Walsh Construction Co. | W912RS-11-C-0017 | 40616 | 32004 | 2011-10-01 | 2013-11-05 | 2013-10-19 | 2013-10-19 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100037 | Armed Forces Reserve Center (JFHQ) |  | 2011-08-03 | 2011-08-18 | Vigil Contracting, Inc. | W912L5-09-2-2001 | 26879 | 25717 | 2011-12-01 | 2014-04-01 | 2013-07-10 | 2014-05-08 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130123 | Readiness Center, Add/Alt |  | 2011-05-17 | 2012-04-17 | TEPA | W912JM-10-D-0018 | 10363 | 10349 | 2012-06-04 | 2013-09-30 | 2013-09-30 | 2014-04-30 | 10% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130127 | Readiness Center |  | 2011-07-19 | 2011-07-27 | Cooper & Company General Contractors, Inc. | 41100-033-0000078159 | 16941 | 16726 | 2011-12-01 | 2013-05-15 | 2012-11-16 | 2012-11-16 | 85% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | GUAM | GUAM | 140001 | Combined Support Maintenance Shop, Ph 1 |  | 2011-05-31 | 2011-09-01 | NAVFAC Pacific | N40192-10-D-2801-0004 | 18961 | 19300 | 2011-09-12 | 2013-04-19 | 2012-04-20 | 2012-04-20 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-11-30 | 2011 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150077 | Combined Support Maintenance Shop, Ph 2A |  | 2011-08-11 | 2011-12-29 | BCP Construction of Hawaii, Inc. | W912J6-11-C-0002 | 37843 | 37193 | 2012-02-01 | 2014-03-20 | 2013-08-18 | 2014-03-20 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160093 | Barracks (ORTC), Ph 1 |  | 2011-05-03 | 2011-08-09 | Ewing Company, Inc. | W912J7-11-C-0002 | 17333 | 13811 | 2011-08-27 | 2013-10-03 | 2013-02-28 | 2014-04-15 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($12,969)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160122 | Tactical Unmanned Aircraft System Facility |  | 2011-05-23 | 2011-08-02 | Construction Inc, Moutain Home | W912J7-11-C-0001 | 6258 | 5477 | 2011-09-13 | 2013-11-14 | 2013-10-22 | 2013-11-14 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 179237 | Combined Support Maintenance Shop, Add/Alt |  | 2011-09-15 | 2011-09-20 | CORE Construction | W91SMC-09-2-2002 | 14954 | 14464 | 2011-10-24 | 2013-07-17 | 2012-10-05 | 2014-07-31 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200063 | Readiness Center |  | 2011-07-15 | 2011-08-11 | Straub Construction Co., Inc. |  | 31031 | 23235 | 2011-09-23 | 2013-07-01 | 2012-12-07 | 2013-07-15 | 99% | 12461 | 150023 and 490444 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($26,283)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200090 | Field Maintenance Shop |  | 2011-09-01 | 2011-09-26 | The Law Company, Inc. |  | 23579 | 12402 | 2011-11-18 | 2014-04-15 | 2012-10-19 | 2014-04-15 | 99% | 9000 | 150023 and 400066 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($13,244)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210034 | Readiness Center |  | 2011-08-31 | 2011-09-16 | D.W. Wilburn | CT2 785 1200000063 1 | 19426 | 18776 | 2011-11-09 | 2013-05-29 | 2013-03-01 | 2013-05-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220114 | Readiness Center |  | 2011-06-23 | 2011-08-08 | Walton Construction Co., LLC. | LA11-C-125 | 27676 | 22524 | 2011-08-29 | 2013-09-03 | 2013-01-14 | 2013-08-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($19,308), Closeout procedures pending
2014-11-30 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220222 | Tactical Unmanned Aircraft System Facility |  | 2011-06-29 | 2011-08-09 | Ratcliff Construction Company | LA11-C-139 | 5470 | 5018 | 2011-09-12 | 2012-12-11 | 2012-07-30 | 2013-06-18 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240186 | Tactical Unmanned Aircraft System Facility |  | 2011-07-14 | 2011-08-24 | G-W Management Services, LLC | N40080-10-D-0498 | 5480 | 5583 | 2011-09-23 | 2013-09-27 | 2013-06-15 | 2014-04-15 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250136 | Armed Forces Reserve Center (JFHQ), Ph 2 |  | 2011-09-15 | 2011-09-22 | Nauset Construction Corp. | W912SV-11-C-0004 | 22927 | 21885 | 2011-10-17 | 2012-11-17 | 2012-10-27 | 2014-04-04 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260207 | Combined Arms Collective Training Facility |  | 2011-06-22 | 2011-08-18 | Saylor Construction LLC | Y11261 | 18799 | 13823 | 2011-09-20 | 2013-04-05 | 2012-03-09 | 2013-11-18 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270096 | Infantry Squad Battle Course |  | 2011-06-28 | 2011-07-01 | Eagle Construction Company, Inc. | EAG010025 | 4226 | 2232 | 2011-11-01 | 2013-02-15 | 2012-07-06 | 2013-02-15 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270202 | Field Maintenance Shop |  | 2011-07-19 | 2011-08-08 | Stahl Construction Company | STA006002 | 28894 | 26314 | 2011-10-26 | 2013-05-03 | 2013-01-18 | 2014-04-18 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270267 | Tactical Unmanned Aircraft System Facility |  | 2011-07-21 | 2011-08-08 | Donlar Construction Company | DON050003 | 4413 | 3544 | 2012-04-03 | 2012-12-13 | 2012-10-27 | 2012-12-13 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310107 | Readiness Center |  | 2011-06-15 | 2011-07-12 | The Weltz Company, LLC |  | 11368 | 11339 | 2012-05-07 | 2013-05-06 | 2012-08-08 | 2013-04-01 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310110 | Readiness Center, Add/Alt |  | 2011-08-16 | 2011-08-19 | Kingery Construction Company |  | 3293 | 3339 | 2011-10-01 | 2013-05-06 | 2012-11-06 | 2013-04-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330034 | Classroom Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-25 | Eckman Construction Company, Inc. | 80342R-G | 20742 | 19649 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-03 | 15% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | 330035 | Barracks Facility (Regional Training Institute) |  | 2011-05-09 | 2011-08-26 | Eckman Construction Company, Inc. | 80342R-G | 14880 | 13736 | 2011-11-07 | 2013-09-23 | 2013-06-01 | 2015-10-30 | 15% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350075 | Readiness Center, Add/Alt |  | 2011-04-19 | 2011-09-29 | Jaynes Corporation | 12-705-0000-1213 | 8481 | 10306 | 2011-12-05 | 2012-12-25 | 2012-10-31 | 2012-10-31 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370898 | Readiness Center, Add/Alt |  | 2011-09-08 | 2011-09-15 | Holden Building Company, Inc. | W912421022003 | 1547 | 1590 | 2011-11-05 | 2012-08-01 | 2012-10-26 | 2012-10-26 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | NORTH DAKOTA | UNITED STATES | 380014 | Readiness Center, Add/Alt |  | 2011-06-15 | 2011-06-22 | Comstock Construction, Inc. | AGND11-30 | 11174 | 11743 | 2011-08-08 | 2012-09-11 | 2012-07-15 | 2013-02-26 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2011 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380121 | Levee Pump Station |  | 2011-09-22 | 2011-09-30 | Swanberg Construction, Inc. | AGND11-71 | 1695 | 19238 | 2011-10-24 | 2012-10-31 | 2012-12-15 | 2014-05-30 | 100% | 0 |  | (NGB 593)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | UNITED STATES | 436021 | Multi Purpose Machine Gun Range |  | 2012-08-27 | 2012-08-29 | Eastern Construction and Electrical Inc. | W912LR-14-B-2004 | 9200 | 9567 | 2014-09-15 | 2015-01-26 | 2015-01-26 | 2015-01-26 | 0% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | PUERTO RICO | UNITED STATES | 436023 | Live Fire Shoot House |  | 2011-07-21 | 2011-09-22 | Remex Co. | W912LR-11-B-0001 | 3077 | 2562 | 2011-11-07 | 2012-09-18 | 2012-12-14 | 2012-12-14 | 65% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440009 | United States Property and Fiscal Office |  | 2011-07-26 | 2012-07-20 | Maron Construction Co Inc. | W912LD-12-C-0001 | 26713 | 21433 | 2012-08-20 | 2014-07-04 | 2014-04-17 | 2014-08-31 | 96% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), (Note SB Size Protest delayed award and construction start of project)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460085 | Readiness Center |  | 2011-05-25 | 2011-06-03 | Breitbach Construction Company, Inc. | W912MM-06-2-20002 | 24719 | 17797 | 2011-11-07 | 2013-03-01 | 2013-01-14 | 2014-11-01 | 99% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($18,225)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480267 | Combat Pistol/Military Pistol Qualification Course |  | 2011-04-06 | 2011-09-12 | Unified Services of Texas, Inc. | TX11-ENG-10 | 2477 | 1962 | 2011-09-26 | 2012-10-31 | 2012-03-31 | 2012-10-31 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480290 | Urban Assault Course |  | 2011-08-25 | 2011-09-12 | Gaeke Construction Co., Inc. | TX11-ENG-06 | 2581 | 2172 | 2011-11-01 | 2013-01-21 | 2012-08-20 | 2013-08-01 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | VIRGIN ISLAND | VIRGIN ISLANDS, U.S. | 520034 | Readiness Center (JFHQ) |  | 2011-05-19 | 2011-09-06 | Tip Top Construction, Inc. | W9127P-11-C-0005 | 24850 | 22324 | 2011-11-01 | 2013-11-25 | 2012-08-20 | 2013-08-01 | 62% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530022 | Combined Support Maintenance Shop |  | 2011-06-07 | 2011-06-23 | Pease & Sons, Inc. |  | 24880 | 24115 | 2011-08-22 | 2013-12-12 | 2012-11-03 | 2014-09-23 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), State waiting on demolition of the old CSMS
2014-11-30 | 2011 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540068 | Readiness Center |  | 2011-09-21 | 2011-09-22 | Massaro Corporation |  | 20895 | 19502 | 2011-11-14 | 2013-04-09 | 2013-03-26 | 2013-03-26 | 75% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540084 | Readiness Center |  | 2011-06-01 | 2011-09-21 | Langan General Contracting Corp | DEFK1200 | 14145 | 13573 | 2011-10-08 | 2013-04-22 | 2013-03-24 | 2014-06-23 | 90% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550139 | Aircraft Parking |  | 2011-08-16 | 2011-09-15 | Buteyn Peterson Construction Co. | NGB-47-11-C-0014 | 5689 | 5960 | 2011-11-01 | 2012-10-09 | 2012-10-29 | 2012-10-17 | 94% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560116 | Field Maintenance Shop |  | 2011-07-28 | 2011-08-16 | Health Construction | 11041922101 | 14280 | 11196 | 2011-09-12 | 2013-03-19 | 2013-06-30 | 2014-06-03 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 011006 | Readiness Center, Add/Alt |  | 2012-09-13 | 2012-09-23 | Metro D. Constructions, LLC | AC-12-C-0036-S | 2000 | 1999 | 2012-11-18 | 2013-10-01 | 2013-09-16 | 2014-01-28 | 10% | 0
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 010263 | Readiness Center, Ph2 |  | 2012-06-15 | 2012-06-21 | Baggette Construction, Inc. | W912JA-12-C-0001 | 16413 | 14492 | 2012-09-14 | 2013-12-24 | 2013-12-10 | 2013-12-10 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040294 | Readiness Center |  | 2012-02-15 | 2012-08-16 | Haydon Building Corporation-Tem | M11-0045 | 17771 | 17655 | 2012-09-12 | 2013-11-04 | 2013-10-16 | 2014-01-31 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050172 | Convoy Live Fire/Entry Control Point Range |  | 2012-02-14 | 2012-08-16 | USPFO - AK | 9751104 | 3500 | 3604 | 2012-11-07 | 2013-12-20 | 2013-10-28 | 2014-07-15 | 97% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | 050190 | Wash Platform, Installation |  | 2013-09-12 | 2013-09-18 | Wilkins Construction, Inc. |  | 1195 | 1759 | 2014-03-10 | 2014-06-23 | 2014-06-23 | 2014-12-22 | 33% | 0
2014-11-30 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060009 | Utilities Replacement Ph1 |  | 2012-07-09 | 2012-08-01 | Cox Construction Co. | W912LA-12-C-0007 | 31073 | 25066 | 2012-12-01 | 2014-09-26 | 2015-03-01 | 2015-04-30 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060170 | Field Maintenance Shop |  | 2012-06-19 | 2012-06-26 | Goshawk LLC | W912LA-12-C-0003 | 7985 | 7456 | 2012-11-08 | 2013-10-20 | 2013-10-14 | 2014-06-06 | 30% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 060432 | Barracks |  | 2012-06-27 | 2012-09-28 | WEP Enterprises | W912LA-11-D-0024 | 1400 | 1131 | 2012-10-15 | 2013-10-07 | 2013-09-20 | 2014-10-30 | 99% | 0 |  | FY07 Congressionally Directed, Used FY10 funds
2014-11-30 | 2012 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060438 | Tactical Unmanned Aircraft System Facility |  | 2012-06-04 | 2012-07-20 | Red Mountain LLC | W912LA-12-C-0002 | 6114 | 5236 | 2012-08-06 | 2013-11-11 | 2013-10-28 | 2014-11-15 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4835)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080093 | Barracks Complex (ORTC) |  | 2012-08-30 | 2012-09-04 | FSA & JKC Joint Venture One, LLC. |  | 42228 | 43744 | 2012-09-24 | 2013-12-03 | 2013-10-28 | 2015-01-11 | 82% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080126 | Readiness Center |  | 2012-06-12 | 2012-06-22 | FCI Constructors, Inc. |  | 6397 | 6276 | 2012-09-10 | 2013-12-02 | 2013-10-14 | 2013-10-14 | 85% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080206 | Tactical Unmanned Aircraft System Facility |  | 2012-09-04 | 2012-09-07 | McCauley Constructors, Inc. |  | 3592 | 3892 | 2012-11-05 | 2013-12-03 | 2013-10-28 | 2014-08-15 | 83% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 110007 | US Property & Fiscal Office Add/Alt |  | 2012-08-21 | 2012-08-28 | Allen & Shariff Corporation | N40080-10-D-0496-0017 | 5300 | 4714 | 2013-03-01 | 2014-06-04 | 2013-12-13 | 2014-06-04 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120188 | Convoy Live Fire/Entry Control Point Range |  | 2012-07-31 | 2012-08-16 | Breaking Ground Contracting Co. |  | 2400 | 2919 | 2013-02-13 | 2013-12-16 | 2013-12-02 | 2013-12-02 | 11% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120193 | Live Fire Shoot House |  | 2012-04-10 | 2012-04-27 | STG Contracting Group |  | 3099 | 2556 | 2012-05-21 | 2013-03-04 | 2013-10-28 | 2013-04-19 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120277 | Unit Storage Building (TUAS) |  | 2012-08-30 | 2012-09-14 | C. Young Construction |  | 821 | 821 | 2013-04-13 | 2013-10-19 | 2013-09-12 | 2013-09-12 | 20% | 0
2014-11-30 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130063 | Maneauver Area Training and Equipment Site, Ph 1 |  | 2012-01-12 | 2012-09-11 | J&S Construction Company, Inc. | W912JM-12-R-0011 | 19255 | 19288 | 2012-10-19 | 2013-11-18 | 2013-10-28 | 2015-02-02 | 22% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $2,331 funds from FY10 project savings PN: 130077
2014-11-30 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130068 | Readiness Center Ph 1 |  | 2012-08-13 | 2012-08-16 | Juneau Construction Company, LLC |  | 14457 | 14123 | 2012-09-14 | 2013-04-12 | 2014-03-14 | 2014-10-14 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130120 | Readiness Center |  | 2012-07-09 | 2012-08-02 | McKnight Construction Co, Inc. |  | 10991 | 11225 | 2012-09-10 | 2013-11-18 | 2013-10-28 | 2014-08-14 | 90% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150043 | Readiness Center Ph 1 |  | 2012-02-15 | 2012-07-11 | Dawson Technical, LLC | W912J6-12-R-0002 | 31992 | 32580 | 2012-07-23 | 2014-08-11 | 2014-07-23 | 2014-07-23 | 12% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170801 | Readiness Center |  | 2012-09-13 | 2012-09-13 | River City Construction | W91SMC-10-2-2005 | 10000 | 10557 | 2012-11-05 | 2013-05-31 | 2014-10-28 | 2014-09-30 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($10,870)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | ILLINOIS | UNITED STATES | 171005 | Battalion Maintenance Shelter |  | 2012-09-24 | 2012-09-24 | H&N Construction | W91SMC-10-2-2005 | 1210 | 999 | 2012-10-01 | 2013-06-30 | 2013-10-31 | 2014-09-30 | 99% | 0 |  | (Completed - State working on NGB 593)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180012 | JFHQ Add/Alt |  | 2012-09-19 | 2012-09-19 | F.A. WILHELM Construction, Inc. | MDI-SAB-13-C-0012 | 25700 | 34528 | 2012-11-15 | 2014-05-04 | 2013-10-28 | 2014-10-31 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming $2M FY09 {PN: 040026} & Formal Reprogramming $7,271 funds from FY09 project savings {PNs: 040226 ($2,540), 180116 ($3,805), 180137 ($510) and 260211 ($416)}
2014-11-30 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180142 | Railhead Expansion & Container Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 20908 | 19069 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180156 | Deployment Processing Facility |  | 2012-09-11 | 2012-09-12 | Milestone, Contractors, L.P. | MDI-SAB-13-C-0011 | 8878 | 8255 | 2012-12-01 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 96% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180160 | Operations Readiness Training Complex 1 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 24991 | 26136 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180161 | Operations Readiness Training Complx 2 |  | 2012-04-12 | 2012-05-17 | Hunt Construction Group, Inc. | MDI-SAB-12-C-0031 | 27000 | 27520 | 2012-12-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 220233 | Waste Water Treatment Facility |  | 2012-03-23 | 2012-06-01 | Max Foote Construction Co., Inc. | LA12-C-117 | 2972 | 2881 | 2012-06-15 | 2013-07-15 | 2013-06-17 | 2014-12-02 | 99% | 0
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230046 | Readiness Center |  | 2012-04-05 | 2012-09-26 | ITSI Gibane |  | 15584 | 14878 | 2012-09-26 | 2014-07-30 | 2014-07-11 | 2015-05-01 | 72% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230071 | Armed Forces Reserve Center |  | 2012-11-10 | 2012-09-26 | J.C.N. Construction Co, Inc. |  | 22997 | 24094 | 2012-09-26 | 2012-10-26 | 2014-10-12 | 2014-12-19 | 73% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240017 | Readiness Center Add/Alt |  | 2012-08-29 | 2012-09-11 | The Whiting-Turner Contracting Company | 001B3400152 | 15771 | 12027 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2014-11-12 | 40% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240187 | Readiness Center Add/Alt |  | 2012-07-23 | 2012-09-11 | Harkins Builders | 001B3400154 | 10296 | 8075 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2015-01-16 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240193 | Readiness Center |  | 2012-09-06 | 2012-09-19 | Coakley & Williams Construction Inc. | 001B3400155 | 9000 | 9998 | 2012-10-01 | 2014-10-06 | 2014-09-22 | 2015-06-22 | 25% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250135 | Readiness Center |  | 2012-08-22 | 2012-09-14 | J & J Contractors, Inc. | MIL1001-DC1 | 8986 | 9630 | 2012-12-01 | 2013-11-18 | 2013-10-28 | 2014-10-28 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011), Informal Reprogramming
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250178 | J-1 Range North Pump and Treat Facility |  | 2012-10-25 | 2012-11-15 | Tetra Tech/Mead & Hunt JV | DACW33-03-D-0006 | 2504 | 2394 | 2013-03-04 | 2013-10-21 | 2013-10-21 | 2014-10-21 | 12% | 0 |  | Used FY13 funds
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270266 | Multipurpose Machine Gun Range |  | 2012-07-10 | 2012-08-01 | W. Gohman Construction Co. | WGO010008 | 8324 | 4477 | 2012-09-17 | 2014-01-18 | 2013-12-15 | 2014-06-01 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,718)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280315 | Troop Housing (ORTC) Ph1 |  | 2012-01-12 | 2012-06-22 | DCD-YATES | W9127Q-12-C-0004 | 24794 | 20041 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,710)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280387 | Deployment Processing Facility |  | 2012-05-31 | 2012-07-11 | Hanco Corporation |  | 12521 | 8803 | 2012-12-01 | 2014-03-19 | 2013-10-16 | 2014-03-19 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($9,222) (NGB 593)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280389 | Operations Readiness Training Complx Ph1 |  | 2012-01-12 | 2012-06-22 | DCD-YATES | W9127Q-12-C-0004 | 23645 | 23621 | 2012-12-01 | 2013-11-15 | 2013-10-21 | 2014-10-21 | 5% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($24,411)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310085 | Readiness Center |  | 2012-05-29 | 2012-06-05 | Sampson Construction Company, Inc. |  | 21913 | 18727 | 2012-07-01 | 2013-12-13 | 2013-11-22 | 2014-03-25 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310086 | Readiness Center |  | 2012-04-09 | 2012-04-27 | Boyd Jones Construction |  | 9099 | 10002 | 2012-05-01 | 2013-11-01 | 2013-06-27 | 2014-05-23 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEBRASKA | UNITED STATES | 310142 | CATS Waste Water Treatment Facility |  | 28 Jun1 2 | 2012-08-10 | All Purpose Construction |  | 1536 | 1661 | 2012-09-01 | 2013-10-11 | 2013-09-19 | 2014-04-30 | 98% | 0
2014-11-30 | 2012 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320070 | Field Maintenance Shop |  | 2012-01-12 | 2012-04-17 | CORE Construction |  | 22932 | 21352 | 2012-12-01 | 2013-11-08 | 2013-10-25 | 2014-10-31 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEW HAMPSHIRE | UNITED STATES | 330052 | Readiness Center, Add/Alt |  | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 330052-GC | 1947 | 1943 | 2012-10-07 | 2013-07-29 | 2013-08-13 | 2013-08-13 | 100% | 0 |  | (Closeout procedures are in progress)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340115 | Army Aviation Support Facility |  | 2012-02-15 | 2012-09-19 | Senate Builders & Const Manager | W912KN-12-C-0006 | 48795 | 46138 | 2012-09-19 | 2014-12-15 | 2014-10-18 | 2014-12-05 | 92% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350115 | Readiness Center, Add/Alt |  | 2012-01-03 | 2012-04-10 | Jaynes Corporation | 12-08-0000-1219 | 5172 | 4440 | 2012-12-01 | 2013-07-13 | 2013-06-01 | 2013-06-01 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | 370899 | Readiness Center, Add/Alt |  | 2012-09-04 | 2012-09-04 | Holden Building Company, Inc. | W9123210220004 | 3680 | 3457 | 2012-12-01 | 2013-11-04 | 2013-10-28 | 2013-10-28 | 99% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400605 | Upgrade: Combined Arms Collective Training Facility |  | 2012-01-12 | 2012-08-16 | Benham Companies, LLC | W90FYQ-09-D-0006-9J01 | 10343 | 9246 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-06-20 | 96% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400606 | Live Fire Shoot House |  | 2012-01-24 | 2012-08-15 | Benham Companies, LLC | W90FYQ-09-D-0006-9J02 | 2995 | 3149 | 2012-11-01 | 2014-03-07 | 2014-02-19 | 2014-06-28 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410026 | Readiness Center |  | 2012-03-02 | 2012-03-19 | Hoffman Construction Company | 410026D002 | 13800 | 13190 | 2012-12-01 | 2014-02-21 | 2013-12-28 | 2014-03-20 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | PUERTO RICO | UNITED STATES | 430010 | Readiness Center |  | 2012-09-10 | 2012-09-18 | RB Construction Group Inc. | W912LR-12-C-0005 | 56285 | 38259 | 2012-12-01 | 2014-12-05 | 2013-10-28 | 2014-11-19 | 17% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($40,565)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450403 | Readiness Center, Add/Alt |  | 2012-09-24 | 2012-09-25 | M. B. Kahn Construction Co., Inc. |  | 4290 | 4255 | 2012-10-01 | 2013-09-01 | 2013-10-28 | 2013-10-28 | 10% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490618 | Multi-Purpose Machine Gun Range |  | 2012-09-06 | 2012-09-27 | Cracar Construction | W911YP-12-C-0007 | 6498 | 6577 | 2012-12-01 | 2014-01-06 | 2013-10-28 | 2013-10-28 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | VIRGINIA | UNITED STATES | 510307 | Combined Arms Collective Training Facility |  | 2012-11-08 | 2013-02-05 | Joint Forces Construction LLC | W912LQ-13-C-0001 | 10912 | 8798 | 2013-04-01 | 2014-10-09 | 2014-10-09 | 2015-01-30 | 77% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540085 | Readiness Center Ph1 |  | 2012-09-20 | 2012-09-25 | Paramount Builders LLC | DEK 13002 | 9991 | 11545 | 2012-11-01 | 2014-08-25 | 2014-11-12 | 2014-11-12 | 75% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550245 | Tactical Unmanned Aircraft System Facility |  | 2012-04-26 | 2012-05-30 | Nuvo Construction Company Inc. | NGB-47-12-C-0002 | 6943 | 3986 | 2012-07-01 | 2013-10-20 | 2013-05-20 | 2014-05-30 | 98% | 0 |  | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($4,250)
2014-11-30 | 2012 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560702 | Readiness Center |  | 2012-04-27 | 2012-04-18 | Hensel Phelps | 12014512201 | 8898 | 10342 | 2012-12-01 | 2013-06-17 | 2013-10-28 | 2013-06-17 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 010007 | National Guard Readiness Center |  | 2013-09-24 | 2013-09-26 | Butler Construction Company, LLC. | AC-13-B-0051-S | 1920 | 1891 | 2014-02-03 | 2015-04-24 | 2015-04-24 | 2014-10-01 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010278 | Live Fire Shoot House |  | 2013-08-01 | 2013-08-23 | Hurst Construction, LLC | AC-13-C-0052-S | 5223 | 5382 | 2013-09-23 | 2014-08-15 | 2014-08-15 | 2014-08-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 040669 | Underground Electrical Lines |  | 2013-09-23 | 2014-04-04 | Ludvik Electric | M13-0037 | 2000 | 1833 | 2014-05-05 | 2014-10-31 | 2014-10-31 | 2014-10-31 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050139 | Field Maintenance Shop |  | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC | 9751312 | 6577 | 5231 | 2013-08-30 | 2014-10-27 | 2014-10-01 | 2014-10-01 | 94% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060413 | Maneuver Area Training & Equipment Site Ph 3 |  | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793 | 30449 | 2013-10-21 | 2014-10-01 | 2014-10-01 | 2015-09-30 | 67% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 (1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090043 | Combined Support Maintenance Shop |  | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951 | 29441 | 2014-04-26 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 20% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090115 | RIP RAP |  | 2014-08-28 | 2014-09-11 | Nutmeg Companies, Inc. | W91ZRS-12-D-0026-0005 | 3600 | 1292 | 2014-09-22 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 0% | 0 |  | 11 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 450252)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100010 | Regional Training Institute Ph1 |  | 2013-06-28 | 2013-07-05 | EDIS Company | 40452 | 5319 | 5225 | 2013-09-23 | 2014-10-20 | 2014-10-01 | 2014-11-30 | 65% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120102 | Readiness Center |  | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) |  | 19345 | 20932 | 2014-03-03 | 2015-02-20 | 2015-02-20 | 2015-09-03 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120192 | Upgrade: Combined Arms Collective Training Facility |  | 2013-06-07 | 2013-06-25 | Thomas May Construction Company |  | 8705 | 6452 | 2013-10-04 | 2014-10-20 | 2014-10-01 | 2014-10-01 | 2% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120228 | Ready Building |  | 2013-09-05 | 2013-09-10 | Halfacre Construction Company |  | 1939 | 1920 | 2013-10-14 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | GUAM | GUAM | 140040 | JFHQ Ph 4 |  | 2013-08-22 | 2013-09-24 | NAVFAC Pacific | N40192-10-D-2800 | 8221 | 8089 | 2013-10-21 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) [Removed striked-out entries of Prime Contract Numbers: N40192-10-D-2801, N40192-10-D-2802,N40192-10-D-2803,N40192-10-D-2804, N40192-10-D-2810
2014-11-30 | 2013 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150023 | Army Aviation Support Facility Ph1 |  | 2013-11-13 | 2014-09-11 | USPFO - HI | W912J6-14-R-00001 | 35078 | 33472 | 2014-09-22 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2014-11-30 | 2013 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160100 | ORTC (Barracks) Ph2 |  | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692 | 37607 | 2013-10-07 | 2014-08-01 | 2014-08-01 | 2015-12-10 | 34% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180106 | Field Maintenance Shop |  | 2013-09-24 | 2013-09-24 | Gamong Construction | MDI-SAB-14-C-0002 | 8705 | 8481 | 2014-07-21 | 2014-12-25 | 2014-12-25 | 2015-05-30 | 40% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180144 | Armed Forces Reserve Center Add/Alt |  | 2013-09-20 | 2013-09-20 | Ziolkowski Construction | MDI-SAB-14-C-0001 | 20311 | 22016 | 2014-04-21 | 2015-05-29 | 2015-08-23 | 2015-05-29 | 21% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | IOWA | UNITED STATES | 190142 | Urban Assault Course |  | 2013-05-29 | 2013-06-07 | Rochon Corporation of Iowa | C751SI088 | 2902 | 2545 | 2013-08-09 | 2014-05-30 | 2014-04-30 | 2014-08-25 | 100% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200102 | Taxiway, Ramp & Hangar Alterations |  | 2013-05-21 | 2013-06-14 | Senne & Co |  | 9188 | 8405 | 2013-07-22 | 2014-05-02 | 2014-10-01 | 2014-07-04 | 70% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | KANSAS | UNITED STATES | 200127 | Water Distribution Lines, Portable |  | 2013-09-16 | 2013-09-24 | Harbin Construction | W912JC-12-D-5308 | 1440 | 1445 | 2014-04-07 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 75% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210001 | Army Aviation Support Facility |  | 2013-05-17 | 2013-06-04 | DW Wilburn | CT2 1300000269 | 30953 | 26217 | 2013-07-08 | 2014-11-10 | 2014-10-01 | 2014-10-01 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220241 | National Guard Readiness Center |  | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300 | 8937 | 2014-09-22 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 1% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353 )
2014-11-30 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220243 | Jackson Barracks Billeting Replacement |  | 2013-07-25 | 2014-07-25 | Gibbs Construction | LA06-C-081 | 5700 | 3817 | 2014-07-25 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 99% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $3,000 - PN: 450252, $2,700 - PN: 450353)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 240194 | Combat Pistol/MP Firearms Qualification Course |  | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 1920 | 1740 | 2014-04-21 | 2014-09-22 | 2014-09-22 | 2014-09-22 | 1% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250065 | Unit Training Equipment Site |  | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279 | 21202 | 2014-04-07 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250196 | Water Well, Non-Potable |  | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District |  | 2000 | 1838 | 2013-06-03 | 2013-12-02 | 2013-12-01 | 2013-12-01 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270236 | Scout Reconnaissance Range |  | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. |  | 16443 | 13235 | 2013-09-23 | 2015-08-01 | 2015-10-01 | 2016-01-01 | 50% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270238 | Readiness Center |  | 2013-08-08 | 2013-08-14 | LS Black Constructors | W912LM-13-C-0007 | 16443 | 17496 | 2013-09-30 | 2015-10-15 | 2015-10-15 | 2015-10-28 | 29% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290176 | Regional Training Institute |  | 2013-07-26 | 2013-08-01 | KCI Construction Company | T1203-01B | 17410 | 15704 | 2013-12-09 | 2015-02-28 | 2015-02-28 | 2015-07-21 | 60% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290215 | Readiness Center Add/Alt |  | 2013-09-10 | 2013-09-17 | Larrison Construction Inc. | T1206-01 | 1837 | 1857 | 2013-09-30 | 2014-05-27 | 2014-06-30 | 2014-06-30 | 100% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290216 | Readiness Center Add/Alt |  | 2013-06-02 | 2013-08-09 | Branco Enterprises | T1205-01B | 793 | 819 | 2014-09-23 | 2014-06-20 | 2014-05-09 | 2014-08-15 | 100% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290217 | Readiness Center Add/Alt |  | 2013-07-31 | 2013-08-05 | Zoellner Construction Co, Inc. | T1204-04 | 677 | 525 | 2013-10-21 | 2014-05-19 | 2014-02-14 | 2014-05-19 | 100% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | MONTANA | UNITED STATES | 300032 | Readiness Center |  | 2013-05-29 | 2013-06-07 | Jackson Contractor Group, Inc. |  | 10693 | 12421 | 2013-07-08 | 2014-12-15 | 2015-01-09 | 2015-01-21 | 78% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340110 | Regional Training Institute |  | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885 | 31977 | 2014-10-15 | 2016-08-01 | 2016-02-12 | 2016-07-12 | 5% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340130 | Communication Lines and Ductbank, Underground |  | 2014-09-19 | 2014-09-26 | Rome Management Associates, LLC | W912KN-13-D-0029 | 2228 | 1393 | 2014-10-03 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 0% | 0 |  | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition |  | 2014-09-24 | 2014-10-02 | Smithco Inc. | AGND14-52 | 1950 | 2000 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380123 | RIP RAP |  | 2013-09-24 | 2013-12-02 | Close Construction Company | AGND14-01 | 2000 | 1889 | 2013-12-09 | 2014-08-30 | 2014-08-30 | 2014-11-07 | 6% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390230 | Readiness Center |  | 2013-04-01 | 2013-05-03 | Barton Marlow Company | Construction ADJ-090001 | 11607 | 8736 | 2013-08-01 | 2014-01-10 | 2013-12-01 | 2014-11-18 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Air National Guard | Major Military Construction | OHIO | UNITED STATES | 390256 | Field Maintenance Shop Add/Alt |  | 2013-06-07 | 2013-09-19 | Henderson Contractors, Inc. | W91364-13-Q-0003 | 1998 | 2943 | 2013-11-04 | 2014-10-28 | 2014-07-02 | 2014-12-01 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390263 | Hutments |  | 2014-05-12 | 2014-07-09 | USPFO - OH | USPFO - OH | 2900 | 2662 | 2014-07-16 | 2015-06-15 | 2015-06-15 | 2015-06-15 | 35% | 0 |  | 11 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400066 | Operations Readiness Training Complex |  | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29185 | 27536 | 2013-10-25 | 2014-10-01 | 2014-10-01 | 2016-02-22 | 19% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 420542 | Controlled Access Secure Facility |  | 2014-07-09 | 2014-10-24 | Miller Bros. Construction, Inc. | W912KC-14-R-0005 | 1825 | 1896 | 2014-10-30 | 2015-11-13 | 2015-11-13 | 2015-11-13 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430081 | Readiness Center (JFHQ) |  | 2013-06-27 | 2013-09-26 | R B Construction Group Inc. | W912LR-13-C-0001 | 18294 | 17448 | 2014-03-03 | 2015-09-18 | 2015-09-18 | 2015-09-25 | 23% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | PUERTO RICO | 430622 | Sanitary Sewer |  | 2014-04-04 | 2014-08-27 | Integrated Construction Services, Inc. | W912LR-14-B-2005 | 1535 | 1897 | 2014-09-15 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430804 | Refill Station Building |  | 2013-06-25 | 2013-09-20 | Design Build S E |  | 2128 | 2577 | 2013-10-28 | 2015-05-08 | 2015-05-08 | 2015-05-08 | 0% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430806 | Readiness Center |  | 2013-06-06 | 2013-09-26 | Design Build S E |  | 3675 | 3643 | 2014-02-10 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 0% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490076 | BEQ Facility (Regional Training Institute) |  | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 137861 | 14508 | 15765 | 2013-08-12 | 2014-11-10 | 2014-10-01 | 2014-11-30 | 75% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490444 | Regional Training Institute Ph2 |  | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 137862 | 28772 | 28259 | 2013-08-26 | 2014-09-30 | 2014-09-30 | 2015-03-30 | 72% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | UTAH | UNITED STATES | 490803 | Unheated Aircraft Storage Hangar |  | 2013-11-06 | 2014-07-18 | Keller Construction Inc. | 147589 | 2000 | 1889 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 0% | 0
2014-11-30 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530015 | Readiness Center |  | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | USACE Construction Contract | 33853 | 30257 | 2013-09-23 | 2015-10-26 | 2015-08-20 | 2015-08-27 | 19% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530035 | National Guard Readiness Center |  | 2014-08-15 | 2014-08-20 | Absher Construction | Absher Construction | 26000 | 23740 | 2014-10-06 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 0% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500M - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540075 | Readiness Center |  | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734 | 14988 | 2014-04-07 | 2015-09-11 | 2015-09-11 | 2015-09-11 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550142 | Field Maintenance Shop |  | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673 | 9180 | 2013-10-28 | 2014-10-01 | 2014-10-01 | 2015-04-15 | 25% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction | WISCONSIN | UNITED STATES | 550161 | National Guard Readiness Center Addition |  | 2013-09-24 | 2013-09-25 | Miron Construction | NGB-47-13-C-0009 | 1920 | 909 | 2013-12-12 | 2014-09-01 | 2015-07-01 | 2014-08-01 | 80% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 011014 | National Guard Readiness Center Add/Alt |  | 2014-08-14 | 2014-08-19 | Carmon Construction, Inc. | AC-14-C-0045-S | 4000 | 3756 | 2014-10-06 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050182 | Scout REECE Gunnery Complex |  | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-B-0001 | 21000 | 16758 | 2014-10-20 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120195 | Ready Building |  | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | 120195 D-B Kokolakis | 5700 | 5300 | 2014-04-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170033 | National Guard Readiness Center |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2004-100 | 14000 | 16000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170127 | Aircraft Maintenance Hangar |  | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2003-100 | 28000 | 30000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250095 | Enlisted Barracks, Transient Training Addition |  | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000 | 20559 | 2014-09-15 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260051 | Enlisted Barracks, Transient Training |  | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000 | 17398 | 2014-08-11 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270014 | National Guard Readiness Center |  | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000 | 17943 | 2014-09-29 | 2016-04-09 | 2016-04-09 | 2016-04-09 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 281305 | Raw Sewage Lagoon and Oxidation Pond |  | 2014-09-24 | 2014-09-26 | Miller Enterprises |  | 1950 | 1039 | 2014-09-30 | 2005-04-30 | 2015-04-30 | 2015-04-30 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280272 | National Guard Readiness Center |  | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB-22-14-C-0003-S | 4500 | 4718 | 2014-07-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280423 | Water Supply/Treatment Building, Potable |  | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000 | 2581 | 2014-08-15 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290191 | National Guard Vehicle Maintenance Shop |  | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01C | 9100 | 7188 | 2015-05-12 | 2012-04-30 | 2015-07-31 | 2014-05-19 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290221 | Aircraft Maintenance Hangar |  | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 5000 | 4399 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360161 | National Guard Readiness Center Alteration |  | 2014-09-17 | 2014-09-30 | Design Resources Group Architects, A.I.A, Inc. |  | 31000 | 29608 | 2014-10-20 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390292 | Sanitary Sewer |  | 2014-04-04 | 2014-09-04 | USPFO - OH | W91364-13-D-0003 | 5200 | 4974 | 2014-09-08 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 30% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420051 | Aircraft Maintenance Instructional Building |  | 2014-08-29 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 40000 | 31940 | 2014-10-20 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430070 | Maneuver Area Training & Equipment Site Addition |  | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600 | 4418 | 2014-09-15 | 2015-05-30 | 2015-05-30 | 2015-05-30 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450131 | National Guard Vehicle Maintenance Shop |  | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | 460003 | 13000 | 12400 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450283 | National Guard Readiness Center |  | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | 460003 | 13000 | 12401 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-11-30 | 2014 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560081 | National Guard Readiness Center |  | 2013-12-16 | 2014-03-11 | Layton Construction Company, Inc. | 13002900601 | 10200 | 9748 | 2013-10-10 | 2015-03-31 | 2015-03-31 | 2015-08-31 | 25% | 0
11/31/2014 | 2013 | Defense Finance and Accounting Service | Major Military Construction | TEXAS | UNITED STATES | 80230 | DFAS Administration Building | 80230 | 2013-04-24 | 2013-07-30 | US Army COE Guyco, INC | Contract No. W9127S-09-D-6006 | 12903 | 12903 | 2013-09-11 | 2015-09-05 | 2015-03-05 | 2015-04-10 | 24%
2014-11-30 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 77620 | Fisher House Utility Upgrade |  | 2010-03-01 | 2010-05-04 | NICC JV LLC | N40080 08 D 0305 DO 0816 | 180 | 180 | 2010-05-30 | 2010-10-19 | 2010-08-09 | 2010-08-09 | 100% |  |  | Financially closed
2014-11-30 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 78145 | Satellite Pharmacy (Corry Station) |  | 2011-08-17 | 2011-10-20 | American Contractor & Technology, Inc | N69450 12 C 6323 | 1236 | 1321 | 2011-12-01 | 2013-04-01 | 2012-09-18 | 2013-04-01 | 100% |  |  | Project is not financially closed.
2014-11-30 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 79923 | LRC Extension |  | 2011-09-12 | 2011-09-29 | Grunley/Growel JV, LLC | N40080 06 D 0004 DO 9001 | 694 | 799 | 2011-12-21 | 2012-10-19 | 2012-06-22 | 2012-08-10 | 100% |  |  | Financially closed
2014-11-30 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 75132 | Joint Navy-VA Project |  |  | 2013-09-27 | Billy W. Jarrett Const Co Inc | N62470 13 MPS 0046 | 1797 | 1899 |  |  | 2014-10-15 | 2014-10-15 |  |  |  | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2014-11-30 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81004 | Site Development, NiCOE |  | 2012-05-16 | 2012-06-05 | Sunland Builders, Inc | N40085 09 D 9027 DO 0026 | 1363 | 1452 | 2012-08-01 | 2013-08-12 | 2013-08-29 | 2013-08-29 | 100% |  |  | Project is not financially closed.
2014-11-30 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | GUANTANAMO BAY NAVAL BASE | GUANTANAMO BAY NAVAL BASE | 82095 | Veterinary Treatment Facility Alterations
2014-11-30 | 2008 | Defense Health Agency | Unspecified Minor Military Construction | DELAWARE | UNITED STATES | 69371 | Bio-Environmental Engineering Facility |  | 2009-05-12 | 2009-08-21 | Ventresca Brothers |  | 1354 | 1374 | 2009-09-08 | 2011-01-19 | 2010-09-10 | 2010-09-30 | 100% |  |  | Final payment made 20 July 2012. Contract is closed. Financial closeout complete.
2014-11-30 | 2009 | Defense Health Agency | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 74085 | Medical Admin Annex |  | 2010-06-22 | 2010-09-28 | John Bowman, Inc |  | 1757 | 1810 | 2010-10-20 | 2011-01-19 | 2011-08-01 | 2011-07-29 | 100% |  |  | Project completed and closed. DD1354 information requested. Looking into best source to provide DHA w/transfer documents.
2014-11-30 | 2009 | Defense Health Agency | Unspecified Minor Military Construction |  | GERMANY | 68974 | Computer Operations Center |  | 2011-02-01 | 2011-04-22 | Federal Republic of Germany |  | 1950 | 1950 | 2011-05-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100%
2014-11-30 | [8 empty] | 2011-01-08 | 2011-03-14 | Wayss & Freytag |  | 1572 | 1548 | 2013-04-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100%
2014-11-30 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 77342 | Bldg 509 Alteration of Medical Laboratory |  | 2010-12-17 | 2011-01-28 | Odyssey International, Inc |  | 3294 | 3690 | 2011-02-16 | 2011-09-15 | 2011-09-15 | 2011-08-15 | 100% |  |  | Undelivered orders/commitments ($36,173) returned. Preparation for fiscal closeout.
2014-11-30 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 77216 | Flight Medicine Addition |  | 2010-08-10 | 2010-09-30 | Synergy Systems, Inc |  | 1679 | 1694 | 2010-10-27 | 2012-02-16 | 2011-11-18 | 2011-11-18 | 100% |  |  | 1 Feb 13 - Customer has taken occupancy of the building. Project closed.
2014-11-30 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 80093 | Medical Ed. & Training Facility |  | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc |  | 1698 | 1982 | 2012-08-14 | 2014-09-10 | 2013-11-14 | 2014-08-24 | 100% |  |  | Preconstruction Meeting held 31 JAN 2014. Physical Construction (mobilization) started FEB 2014. BOD 11 AUG 2014. Project Complete. The field office is currently working with the contractor on punch list items. Some of punch list items might require the shut down at least 10 hours to the Mike O'Callaghan Federal Medical Center so the contractor can repair a shutter in the switch gear. Coordination for the shutdown between the affected departments is in progress. The field office is trying to see if it can happen before the 31 December to minimize the impact to the patients.
2014-11-30 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | JAPAN | JAPAN | 78853 | New Clinic Addition |  | 2015-07-02 | 2015-09-15 | [11 empty] | DHA said a new DA will be provided to make a new project for $3M. Utilization of a MATOC will mean that the contractors have to submit an offer. However, that does not guarantee that the offers will result in a CWE less than the stat limit. FY11 funds expire 30 Sep 2015.
2014-11-30 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 81247 | Site Dev in Support of NiCOE |  | 2012-08-15 | 2012-09-28 | GKK | W91278-10-D-0047 | 1589 | 1638 | 2012-10-28 | 2014-07-30 | 2014-01-03 | 2014-07-15 | 99% |  |  | Contractor has completed deficiencies listed during the Final Inspection. Currently awaiting the Contractor's final billing with the signed ENG 93 and Release of Claims. Anticipate Final Payment to occur before the end of September. LRD Returned $2K, what is the status of the project?
2014-11-30 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80792 | Site Development, NiCOE |  |  | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service |  |  | 1690 |  | 2013-06-30 |  |  | 100% |  |  | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Work executed via FBVA contract. 100% complete. BOD achieved 30 June 2013. Received invoice from DLA rep who manages American Water (water & wastewater) showing that they were paid in full, don't have a separate document from American Water that is a Release of Claims. Received from DPW a copy of a "Project Completion Form" sent by Dominion Virginia Power (electricity). PM was told this is what DPW requires from DVP when a project is complete. Received the last "Release of Claims" from NEC/ITA/Verizon with the statement, "All, I attached the MIPR Acceptance Form for the NICOE Building 1259. NEC was provided $68,141.25 to install the Outside Plant Copper and Fiber Cables. NEC/ITA/Verizon Federal completed the installation July 2013. No further funding required." Project Fiscal Closeout Ongoing. [Removed text entry of "N/A" from Original Contract Amount, Start Date, Original Completion Date, and Current Completion Date cells.]
2014-11-30 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80094 | Veterinary Clinic |  | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc | W912BV-12-C-0030 | 2021 | 2047 | 2013-01-04 | 2014-12-05 | 2014-07-05 | 2015-02-01 | 67% |  |  | Vet Clinic (Synergy Services): This $2M project replaces the existing facility with a safe and sanitary environment for the Military Working Dogs and the civilian pet population. Questionable concrete sidewalk quality resolved by removal and replacement. Recently paved asphalt parking lot still contains a questionable area of grading and some paving possibly needs to be seal-coated due to possible separation of aggregate. Resolution will be dependent upon how the asphalt performs through the winter. We will revisit this topic in April '15. Concrete floors being buffed in prep for sealer application.
2014-11-30 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 82358 | Veterinary Clinic Replacement |  | 2014-05-26 | 2015-08-30 | [6 empty] | 2016-05-30 |  |  |  |  | PA is $1.5M and CWE is $1.98M. PDT identified cost reduction measures. Once a confidence level is established that the requirements of the RFP have been adjusted to achieve the target CWE, a revised solicitation will be issued to the SWL SB Medical MATOC pool and proposals requested. SAM will develop a schedule and budget to complete this action. New projected award date is 30 August 2015. AFMSA demands USACE use AF 1600 page iDBIO RFP Template which will cause the price to be $$775/sqft. USACE will not use AF RFP becuase it will cause another bid bust. Need DHA to concur or or increase the PA on this project.
2014-11-30 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | DELAWARE | UNITED STATES | 86204 | Medical Warehouse Add/Alt | [9 empty] | 2016-06-16 | 2016-06-16 | 0% |  |  | Design Build admin space. NAD what is the status?
2014-11-30 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81631 | NiCOE Satellite, Infrastructure Support |  | 2014-03-21 | 2014-06-18 | Boykin Contracting, Inc | W912HN-11-D-0043-0044 | 1436303 | 1436303 | 2014-06-30 | 2015-11-25 | 2015-04-24 | 2015-04-24 | 35% |  |  | The Site Support Contractor has promised unfettered access to the building pad by completing the two parking lots 4-inch stone base course. The Site Support Contractor will still be working on the communication duct bank (directional bore & MHs) and gas line after 19 Dec 14. SUS should have the Transformer pad set by 19 Dec 14. ONUS will be completing their work (Fire Main, Domestic Water, SS, Lift Station) after 19 Dec 14. With the Building Contractor mobilizing personnel one week after rebar delivery on 29 Dec 14, the Site Support Contractor should be able to complete the remaining utilities so that their work will not interfere with the Building Contractor. Contingencies in district: $26,813.38
2014-11-30 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 81706 | NiCOE Satellite, Infrastructure Support |  | 2014-08-01 | 2014-08-21 | NAVAR Inc. | W9126G-14-C-0045 | 2166 | 1795 | 2014-09-15 | 2015-10-01 | 2016-08-19 | 2016-08-19 | 41% |  |  | Overall demo at 100%. Design is complete, contracting waiting on IFC letter to be signed; Rough grading of the site continues; installation of water and gas lines lines coninue; parking area receiving fill; Sanitary sewer prep scheduled for Wednesday (3 Dec 14); contractor has mobilized to the site and is currently excavating the building foundation.
2014-11-30 | 2010 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 401V | Traffic Mitigation Increment 1 | MPLS083737S1 | 2010-03-05 | 2010-05-10 | Clark/Balfour Beatty, JV, Gates N&S Wood Drive | N40080 10 C 1504 | 9512 | 10848 | 2010-07-01 | 2011-08-15 | 2011-07-31 | 2011-08-15 | 100% |  |  | Authorization of Project is financially closed.
2014-11-30 | [8 empty] | 2010-03-16 | 2010-06-21 | Whiting-Turner, University Road & Perimeter Road/Palmer Road | N40080 10 C 1505 | 8800 | 10291 | 2010-07-01 | 2011-08-15 | 2011-08-31 | 2011-08-23 | 100% |  |  | Authorization of Project is financially closed.
2014-11-30 | 2011 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 401A | Traffic Mitigation Increment 2 | MPLS083737S1 | 2010-11-14 | 2011-04-21 | RMA Land Construction Inc, Gates Gunnell & Grier | N62742 09 D 1185 | 5572 | 5982 |  | 2012-09-02 | 2012-12-06 | 2012-11-26 | 100% |  |  | Authorization of Project is financially closed.
2014-11-30 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 1 |  | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 | 757737 | 774314 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100%
2014-11-30 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005A | Medical Center Add/Alt, Inc 2 |  | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100%
2014-11-30 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005B | Medical Center Add/Alt, Inc 3 |  | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 |  |  | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100%
2014-11-30 | 2009 | Defense Health Agency | Base Realignment and Closures | MISSISSIPPI | UNITED STATES | 478V | Community Hospital |  | 2009-04-01 | 2009-11-10 | W.G. Yates & Sons Construction Co. | N69450 10 C 0763 | 38252 | 42256 | 2010-01-01 | 2012-02-25 | 2011-09-11 | 2012-10-11 | 100% |  |  | Not financially closed. Final invoicing for equipment - working with DLA.
2014-11-30 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 020V | Site Utility Infra Upgrade for NiCOE |  | 2008-07-08 | 2008-12-22 | Turner Construction Company | N40080 09 C 1502 | 7295 | 7371 | 2009-01-01 | 2010-03-29 | 2010-03-06 | 2010-04-30 | 100% |  |  | Project is financially closed.
2014-11-30 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 796V | Supt Fac for WTC Admin Ctr (BQ/Dining) |  | 2009-04-01 | 2009-08-26 | Whiting-Turner | N40080 09 C 0018 | 117555 | 126445 | 2010-02-01 | 2011-07-13 | 2011-05-31 | 2011-09-11 | 100% |  |  | Project is financially closed.
2014-11-30 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 701V | Consolidation of Administration Spaces (WTU Admin), Inc 1 |  | 2009-04-01 | 2009-08-26 | Whiting-Turner | N40080 09 C 0018 | 68529 | 78196 | 2010-02-01 | 2011-08-01 | 2011-08-01 | 2011-09-11 | 100% |  |  | Project is financially closed.
2014-11-30 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 701A | Consolidation of Administration Spaces (WTU Admin), Inc 2 |  | 2009-04-01 | 2009-08-26 | Whiting-Turner | N40080 09 C 0018 |  |  | 2010-02-01 | 2011-08-01 | 2011-08-01 | 2011-09-11 | 100% |  |  | Project is financially closed.
2014-11-30 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69427 | Hopsital Replacement, Inc 1 |  | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV |  | 649025 | 9428 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | $10M claim withdrawn. DCAA Audit negotiations were successful. Bi-lateral mod and final release to be sent to T/G by 15 Dec. No add'l funds will be needed. Approx $302,026 will be deobligated and returned to DHA. One remaining MIPR to MEDCOM needs a contract de-obligation of $332K (DLA action). Weekly call with MEDCOM to track progress. Target contract closeout 30 Jan 2015. Project Closeout in P2 by 15 Mar 2015. Funds will be returned by March 2015.
2014-11-30 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64238 | Hopsital Replacement, Inc 2 | 69427 | 2007-06-12 | 2008-04-04 | Turner/Gilbane JV |  |  | 376782 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | $10M claim withdrawn. DCAA Audit negotiations were successful. Bi-lateral mod and final release to be sent to T/G by 15 Dec. No add'l funds will be needed. Approx $302,026 will be deobligated and returned to DHA. One remaining MIPR to MEDCOM needs a contract de-obligation of $332K (DLA action). Weekly call with MEDCOM to track progress. Target contract closeout 30 Jan 2015. Project Closeout in P2 by 15 Mar 2015. Funds will be returned by March 2015.
2014-11-30 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 65676 | Hopsital Replacement, Inc 3 | 69427 | 2007-06-12 | 2008-12-23 | Turner/Gilbane JV |  |  | 241353 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | $10M claim withdrawn. DCAA Audit negotiations were successful. Bi-lateral mod and final release to be sent to T/G by 15 Dec. No add'l funds will be needed. Approx $302,026 will be deobligated and returned to DHA. One remaining MIPR to MEDCOM needs a contract de-obligation of $332K (DLA action). Weekly call with MEDCOM to track progress. Target contract closeout 30 Jan 2015. Project Closeout in P2 by 15 Mar 2015. Funds will be returned by March 2015.
2014-11-30 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 69865 | Hopsital Replacement, Inc 4 | 69427 | 2007-06-12 | 2010-01-23 | Turner/Gilbane JV |  |  | 119266 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | $10M claim withdrawn. DCAA Audit negotiations were successful. Bi-lateral mod and final release to be sent to T/G by 15 Dec. No add'l funds will be needed. Approx $302,026 will be deobligated and returned to DHA. One remaining MIPR to MEDCOM needs a contract de-obligation of $332K (DLA action). Weekly call with MEDCOM to track progress. Target contract closeout 30 Jan 2015. Project Closeout in P2 by 15 Mar 2015. Funds will be returned by March 2015.
2014-11-30 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 77071 | Hopsital Replacement, Inc 5 | 69427 | 2007-06-12 | 2010-10-20 | Turner/Gilbane JV |  |  | 211800 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | $10M claim withdrawn. DCAA Audit negotiations were successful. Bi-lateral mod and final release to be sent to T/G by 15 Dec. No add'l funds will be needed. Approx $302,026 will be deobligated and returned to DHA. One remaining MIPR to MEDCOM needs a contract de-obligation of $332K (DLA action). Weekly call with MEDCOM to track progress. Target contract closeout 30 Jan 2015. Project Closeout in P2 by 15 Mar 2015. Funds will be returned by March 2015.
2014-11-30 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 1 | SPBN019136 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 107589 | 135926 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | There are still actions on-going that will prevent close-out: 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Resolution period to be determined. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments have been suspended. They provided the telephones for the project. Throughout USACE invoices from EYAK Technology, Inc continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. USACE does not expect this matter to be resolved by the Department of Justice during FY 2014. The status is unchanged. The SWF invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. I do not expect this matter to be resolved by the Department of Justice during FY 2014. - Per USACE CT Office 3. TEAM Integrated Services Task Orders. Last DCAA audit is estimated to be completed 31 Dec 2015.
2014-11-30 | 2009 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64180 | San Antonio Regional MEDCEN, Inc 2 | SPBN019136 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 265100 | 279273 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | There are still actions on-going that will prevent close-out: 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Resolution period to be determined. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments have been suspended. They provided the telephones for the project. Throughout USACE invoices from EYAK Technology, Inc continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. USACE does not expect this matter to be resolved by the Department of Justice during FY 2014. The status is unchanged. The SWF invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. I do not expect this matter to be resolved by the Department of Justice during FY 2014. - Per USACE CT Office 3. TEAM Integrated Services Task Orders. Last DCAA audit is estimated to be completed 31 Dec 2015.
2014-11-30 | 2010 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 69840 | San Antonio Regional MEDCEN, Inc 3 | SPBN019136 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 13748 | 243943 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | There are still actions on-going that will prevent close-out: 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Resolution period to be determined. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments have been suspended. They provided the telephones for the project. Throughout USACE invoices from EYAK Technology, Inc continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. USACE does not expect this matter to be resolved by the Department of Justice during FY 2014. The status is unchanged. The SWF invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. I do not expect this matter to be resolved by the Department of Justice during FY 2014. - Per USACE CT Office 3. TEAM Integrated Services Task Orders. Last DCAA audit is estimated to be completed 31 Dec 2015.
2014-11-30 | 2011 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 70990 | San Antonio Regional MEDCEN, Inc 4 | SPBN019136 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction | W9126G-08-C-0036 | 37554 | 85520 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | There are still actions on-going that will prevent close-out: 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Resolution period to be determined. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments have been suspended. They provided the telephones for the project. Throughout USACE invoices from EYAK Technology, Inc continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. USACE does not expect this matter to be resolved by the Department of Justice during FY 2014. The status is unchanged. The SWF invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. I do not expect this matter to be resolved by the Department of Justice during FY 2014. - Per USACE CT Office 3. TEAM Integrated Services Task Orders. Last DCAA audit is estimated to be completed 31 Dec 2015.
2014-11-30 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64188 | Health Clinic |  | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction | W9126G-08-C-0024 | 33382 | 37382 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 99% |  |  | Construction 100% Complete. REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2014-11-30 | 2010 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64241 | Dental Clinic |  | 2009-09-16 | 2010-05-04 | Forrester Construction Company |  | 7541 | 8818 | 2010-05-18 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | NAB received 0516 BRAC Consolidated funding, executed the Global Settlement Modification, paid Final Invoice, and received Release of Claims from Contractor. Construction Contract and Project in Close Out Phase. Fiscal Closeout is scheduled, and tracking for 13 Jan 2015.
2014-11-30 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 64156 | USAMRICD Replacement, Inc 1 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398 | 16018.3843 | 2010-03-15 | 2015-01-15 | 2013-06-01 | 2014-12-22 | 99% |  |  | (11/21/14) Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 15 Jan 2015 for remainder of spaces. Contractor continues to struggle with comissioning activities, significantly impacting schedule & timeline for final acceptance of equipment/systems. (Historical data: Project reprogrammed through ACSIM as a BTR 02/27/13. Increase = $1.699M. No new BRAC obligations post 15 Sept 2011. Expenditure of BRAC funds will occur on mandatory changes through completion of project.) Split funded with DODM. Possible $21M Claim.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | GUAM GU | GUAM | 65270 | Hospital Replacement, Inc 1 |  | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133 | 165418 | 2010-11-01 | 2014-03-18 | 2014-10-15 | 2015-03-27 | 98% | 19460 |  | 93% complete is 100% of the hospital completion. The remaining 7% is the demo of the existing facility. Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77154 | Ambulatory Care Center, Inc 1 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 197804 | 137444 | 2013-03-01 | 2016-12-06 | 2016-12-06 | 2017-11-08 | 44% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 81291 | Ambulatory Care Center, Inc 2 |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV |  |  | 66430 | [7 empty] | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 |  | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 6887.87 | 7070.1979 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 12000 | 12658 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC. $9,000 recinded as a result of Sequestration (04/29/13).
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67180 | USAMRICD Replacement, Inc 2 |  | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100%
2014-11-30 | [8 empty] | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract | W912DR-10-F-0217 | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 100%
2014-11-30 | [8 empty] | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 100375 | 103745.3283 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | Main Building $142,857,143 FY10 Increment Awarded at $100,375,000 on 5 Mar 10 ($109,567,007 funded per D. Pritchett 17 Mar 10 email)
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67181 | USAMRICD Replacement, Inc 3 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 94608 | 96044.5065 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | Full FY11 MILCON increment placed against contract.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67182 | USAMRICD Replacement, Inc 4 |  | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 7915.345 | 29838.8249 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | (11/21/14) Early BOD of admin spaces (Bldgs A/B/C/Cup) on 19 Nov 14, with follow on remaining BOD on 22 Dec 14 for remainder of spaces. Contractor continues to struggle with comissioning activities, significantly impacting schedule & timeline for final acceptance of equipment/systems. DHA On-Site Quarterly scheduled for 08 October 2014. (Historical data: Project reprogrammed through ACSIM as a BTR 02/27/13. Increase = $1.699M. No new BRAC obligations post 15 Sept 2011. Expenditure of BRAC funds will occur on mandatory changes through completion of project.) Split funded with DODM. NAB will provide financial close out date.
2014-11-30 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement, Incr 1 |  | 2007-06-30 | 2007-09-29 | Cont #1 - Offiste San Sewer & Storm (James Construction) | W912DR-07-C-0070 | 2657 | 2657 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 99% |  |  | Work complete. Contracts closed.
2014-11-30 | [8 empty] | 2008-01-10 | 2008-08-01 | Cont #2 - Storm Lat 1&3A (James Construction) | W912DR-08-C-0038 | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 99% |  |  | Work complete. Contracts closed.
2014-11-30 | [8 empty] | 2008-05-01 | 2009-09-28 | Cont #3 - IMP Pond (James Corporation) | W912DR-08-C-0078 | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 99% |  |  | Work complete. Contracts closed.
2014-11-30 | [8 empty] | 2008-01-10 | 2008-09-25 | Cont #4 - Early Site/Utility (Grunley/Goel JVA LLC) | W912DR-08-C-0053 | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 99% |  |  | Work complete. Contracts closed.
2014-11-30 | [9 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 2866 | 2866 | 2008-07-15 | 2013-12-06 | 2011-05-06 | 2013-10-31 | 99% | 2289 |  | Work being accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project. *** Need to add Contract #7 line items for FY 10/11 funding. FY 10: original contract amount ($496,221) and current contract/total obligation ($524,505.60). FY 11: original contract amount ($603,803) and current contract/total obligation ($638,219.77). DHA provided $800K of reprogrammed FY10 MILCON funds from the Blood Donor Center, Ft. Benning project to the FY07 SSP project via 0$FAD on 3/4/14. [Removed text entry of "N/A(SSP Mod" from Solicitation Date cell.]
2014-11-30 | [8 empty] | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 15736 | 16161 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 94% |  |  | % Complete (Scheduled/Actual): 99/94 Phase I - MTJV contract increments are fully funded. Systems commissioning activities underway. T&E change under negotiation. Primary facility BOD is changed to 1 Jul 17 due to fire in BSL-4 area. Work continues in unaffected areas of the facility. FY07, FY08, FY10, and FY11 funds fully obligated. Project has consumed original 5% contingency, but has $15M remaining for certification. Two-phase occupancy acceptance planned - Jun 2016 for admin, BSL2, and BSL3 suites, July 2017 for BSL4. Expect a good paint testing report by 22 Dec 2014. Liquidated Damages assessed since 21-Oct-2014 the old contract completion date. NAD to provide a current construction completion date.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63418 | USAMRIID Replacement, Incr 2 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 131264 | 138491 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 94% |  |  | Phase I - FY 08 (note corrected PN)
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63419 | USAMRIID Replacement, Incr 3 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 185526 | 185630 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 94% |  |  | Phase I - FY 09 UPDATE JUN 13: PA decremented due to sequestration.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 63420 | USAMRIID Replacement, Incr 4 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 94000 | 100180 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 94% |  |  | Phase I - FY 10 UPDATE JUN 13: PA decremented due to sequestration.
2014-11-30 | [9 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 496 | 525 | 2008-07-15 | 2013-12-06 |  | 2013-10-31 | 99% |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project. [Removed text entry of "N/A(SSP Mod" from Solicitation Date cell.]
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65324 | USAMRIID Replacement, Incr 5 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 13497 | 12893 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 94% |  |  | Phase I - FY 11 (note - previous report inadvertently included the contract 7 value - the amount has been corrected to avoid doublecounting)
2014-11-30 | [9 empty] | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 603 | 638 | 2008-07-15 | 2013-12-06 |  | 2013-10-31 | 99% |  |  | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project. [Removed text entry of "N/A(SSP Mod" from Solicitation Date cell.]
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71101 | USAMRIID Replacement, Incr 6 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 66955 | 83767 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 94% |  |  | Phase I - FY 12. UPDATE JUN 13: PA decremented due to sequestration.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78210 | USAMRIID Replacement, Incr 7 | 58395 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 0 | 0 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2016-10-21 | 94% |  |  | Utilities, DDC, amd related costs associated with Contract # 5 for primary facility. UPDATE JUN 13: PA decremented due to sequestration.
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 78211 | USAMRIID Replacement, Incr 8 | 58395 | 2015-01-22 | 2015-05-29 | Cont # 6 (North Parking) (TBD) |  |  | 0 | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | CENAB in-house resources completing design. RTA date for North Parking adjusted to 30 Jan 15 and schedule readjusted to allow additional time for Maryland Dept of Environment approvals. Contract solicitation will include NIBC Fence - Ph II (FY 11 DODM) and Entry Control Point. [Removed text entry of "TBD" from Original Contract Amount cell.]
2014-11-30 | [8 empty] | 2017-04-01 | 2017-08-01 | Cont # 8 (South Parking/Demolition) (TBD) |  |  | 0 | 2019-08-22 | 2020-10-21 | 2020-08-22 | 2020-10-31 | 0% |  |  | Notional schedule shown; dependent on CDC/DA Safety certification of USAMRIID primary facility and vacation/decommissioniung of existing buildings 1408/1412/1414/1415. Due to delay in main contract, projections for award are moved out 2 years. [Removed text entry of "TBD" from Original Contract Amount cell.]
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 |  | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 7782 | 11366 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 22% |  |  | •Construction Progress: Sch. 26% Act. 22% : The Hospital Contractor is currently working to the late finish schedule plus 90 days due to pier and structural steel delays. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed •Excavation for the lift station is ongoing. Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony.
2014-11-30 | [8 empty] | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. - Infrastructure | W912G-09-D-0004-0008 | 39345 | 47508 | 2011-11-02 | 2013-10-12 | 2013-08-13 | 2013-08-29 | 99% |  |  | Construction 100% Complete
2014-11-30 | [8 empty] | 2011-03-25 | 2011-06-17 | Janco - Water Tower | W9126G-09-D-0096-0002 | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 99% |  |  | Construction 100% Complete
2014-11-30 | [8 empty] | 2012-03-16 | 2012-07-19 | VEMAC - Parking Pkg A | W9126G-12-C-0038 | 3848 | 3879 | 2012-08-28 | 2013-10-17 | 2013-06-19 | 2013-06-11 | 99% |  |  | Construction 100% Complete
2014-11-30 | [8 empty] | 2013-02-19 | 2014-07-25 | El Paso Water Utility | W9126G-14-P-0150 | 3960 | 2800 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-08-06 | 8% |  |  | 8% Construction Complete. The contractor began construction 3 Nov 14. He began at the southernmost end (Stockmeyer) and will work towards Pebble Hills. He reached Pebble Hills on 11/21/14. Contractor is constructing this line in 1,000 LF sections. Contracting also awarded the modification to EPWU for the revised bid amount of: $4,338,247.84 on 14 Nov 14.
2014-11-30 | [8 empty] | 2012-02-08 | 2012-09-04 | El Paso Electrical Substation | W9126G-12-P-0014 | 4047 | 4047 | 2012-09-04 | 2015-09-16 | 2014-01-04 | 2014-01-04 | 99% |  |  | Construction 100% Complete
2014-11-30 | [10 empty] | Temp Electric Contract |  | 46 | 46 |  |  |  |  | 100% |  |  | Temp power costs.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77251 | Fort Bliss Hospital Repl, Incr 2 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 68076 | 68076 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 22% |  |  | •Construction Progress: Sch. 26% Act. 22% : The Hospital Contractor is currently working to the late finish schedule plus 90 days due to pier and structural steel delays. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed •Excavation for the lift station is ongoing. Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72786 | Fort Bliss Hospital Repl, Incr 3 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV | W9126G-13-C-0004 | 69851 | 72931 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 22% |  |  | •Construction Progress: Sch. 26% Act. 22% : The Hospital Contractor is currently working to the late finish schedule plus 90 days due to pier and structural steel delays. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed •Excavation for the lift station is ongoing. Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 76558 | Fort Bliss Hospital Repl, Incr 4 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 79914 | 160491 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 22% |  |  | •Construction Progress: Sch. 26% Act. 22% : The Hospital Contractor is currently working to the late finish schedule plus 90 days due to pier and structural steel delays. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed •Excavation for the lift station is ongoing. Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony.
2014-11-30 | [8 empty] | 2013-08-08 | 2013-09-13 | Helipad | W9126G-13-C-0046 | 1540 | 657 | 2013-10-21 | 2014-11-24 | 2014-10-24 | 2014-10-24 | 99% |  |  | Helipad Construction Progress: Sch. 100% Act. 99%: •Asphalt for the outer helipad buffer zone was completed on 11 Sep 14. •The Contractor is Working on the lighting installation. •USACE has provided a copy of the Helipad package to El Paso International for review. El Paso International completed their review on 24 Sep 14 with no exceptions found except that furhter coordination would be required for the operational flight patterns. A pre-final inspection has been scheduled for 24 Oct 14.
2014-11-30 | [9 empty] | 2014-07-25 | El Paso Water Utility Pmt 2 / Sewer Contract | W9126G-14-P-0150 | 479 | 1538 |  |  |  |  | 8% |  |  | 8% Construction Complete. The contractor began construction 3 Nov 14. He began at the southernmost end (Stockmeyer) and will work towards Pebble Hills. He reached Pebble Hills on 11/21/14. Contractor is constructing this line in 1,000 LF sections. Contracting also awarded the modification to EPWU for the revised bid amount of: $4,338,247.84 on 14 Nov 14. [Removed text entry of "N/A" from Solicitation Date cell.]
2014-11-30 | [9 empty] | 2015-02-15 | Parking Pkg B |  | 5562 | [5 empty] | 0% |  |  | Parking Package “B”:(small business- LPTA) Est. Award: $5.5M •Solicitation Package is complete. •Proposed Award Date: 15 Feb 15 [Removed text entry of "TBD" from Original Contract Obligation, and "TBD(NOTES)" from Solicitation Date, Start Date, Placed In Service Date, Original Completion Date, and Current Completion Date cells.]
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 77293 | Fort Bliss Hospital Repl, Incr 5 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 198148 | 77700 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 22% |  |  | •Construction Progress: Sch. 26% Act. 22% : The Hospital Contractor is currently working to the late finish schedule plus 90 days due to pier and structural steel delays. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed •Excavation for the lift station is ongoing. Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony.
2014-11-30 | [8 empty] | 2014-10-20 | 2014-12-10 | ACPs |  | 24755 |  | 2014-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 0% |  |  | ACP Package: (small business-Best Value) Est. Award: $24.7M •Solicitation package is complete. •Proposed Award Date: 10 Dec 14 [Removed text entry of "TBD" from Current Contract Obligation cell.]
2014-11-30 | [9 empty] | 2015-03-30 | CAT E Equipment |  | 33125 | [5 empty] | 0% |  |  | No update this reporting period. [Removed text entry of "N/A" from Solicitation Date, "TBD" from Current Contract Obligation, Start Date, Placed In Service Date, Original Completion Date, and Current Completion Date cells.]
2014-11-30 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81047 | Fort Bliss Hospital Repl, Incr 6 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 225199 | 0 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 22% |  |  | •Construction Progress: Sch. 26% Act. 22% : The Hospital Contractor is currently working to the late finish schedule plus 90 days due to pier and structural steel delays. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed •Excavation for the lift station is ongoing. Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony.
2014-11-30 | [8 empty] | 2015-03-30 | 2016-03-28 | Landscaping |  | 22616 |  | 2015-07-30 | 2016-07-30 | 2016-07-30 | 2016-07-30 | 0% |  |  | Landscaping Package: (small business-LPTA) Est. Award: $22.7M •Solicitation package is complete. •Proposed Award Date: 28 Mar 16 with a potential early award in May of 2016. [Removed text entry of "TBD" from Current Contract Obligation cell.]
2014-11-30 | 2016 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81408 | Fort Bliss Hospital Repl, Incr 7 | 72481 | 2012-08-07 | 2013-01-29 | Hospital Contract | W9126G-13-C-0004 | 56858 |  | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 22% |  |  | •Construction Progress: Sch. 26% Act. 22% : The Hospital Contractor is currently working to the late finish schedule plus 90 days due to pier and structural steel delays. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed •Excavation for the lift station is ongoing. Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony. [Removed text entry of "TBD" from Current Contract Obligation cell.]
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72754 | Ambulatory Care Center Phase 3, Inc 1 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc | W9126G-12-C-0051 | 76038 | 75644 | 2012-11-01 | 2015-06-30 | 2014-07-29 | 2015-04-17 | 84% |  |  | Construction Progress: Sch. 84% Act. 84%. Above Threshold Reprogramming (ATR) action for phase 3 was approved and funds are at USACE HQ. Headquarters has released $10M to SWF to replenish CAT-E and fund current Mods. Negotiated mods have been within estimates...expect to finish project within the funds provided. BOD of 30 Jun 2015. Includes Buildings G, H, J, K, L & M. Building construction on-schedule. Contractor has begun MEP punch-out, and some finish work is ongoing in various buildings. Final stages of exterior work is ongoing. Site work: dining plaza footings underway, concrete placement continues and ballard installation ongoing. Parking Lot C has been turned over pending approval of interim DD 1354. The initial Red Zone Meeting was held on 20 Nov 2014.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 80793 | Ambulatory Care Center Phase 3, Inc 2 |  | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc | W9126G-12-C-0051 | 16319 | 21250 | 2012-11-01 | 2015-06-30 | 2014-07-29 | 2015-04-17 | 84% |  |  | Construction Progress: Sch. 84% Act. 84%. Above Threshold Reprogramming (ATR) action for phase 3 was approved and funds are at USACE HQ. Headquarters has released $10M to SWF to replenish CAT-E and fund current Mods. Negotiated mods have been within estimates...expect to finish project within the funds provided. BOD of 30 Jun 2015. Includes Buildings G, H, J, K, L & M. Building construction on-schedule. Contractor has begun MEP punch-out, and some finish work is ongoing in various buildings. Final stages of exterior work is ongoing. Site work: dining plaza footings underway, concrete placement continues and ballard installation ongoing. Parking Lot C has been turned over pending approval of interim DD 1354. The initial Red Zone Meeting was held on 20 Nov 2014.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 76007 | Medical Center Replacement, Incr 1 |  |  |  | Environmental Compensation |  | 15042 | 1731 | 2014-01-13 |  | 2021-07-20 |  | 5% |  |  | German government solicitation and award dates to German industry are estimated. [Removed text entry of "N/A" from Solicitation Date, "Constr Oblig to FRG 3/15/2012" from Award Date, and "TBD" from Current Completion Date and "NA" from Placed-In-Service Date cells.]
2014-11-30 | [10 empty] | Lot 1 Temporary Construction Fence |  | 260 | 260 | 2014-01-20 |  | 2014-04-04 | 2014-04-04 | 99% |  |  | Construction essentially completed April 2014; however, access from the east is still open. Once the security contract is awarded, the German govt will close the openings (roadway access from the east) in the construction fence. [Removed text entry of "N/A" from Solicitation Date, "Constr Oblig to FRG 3/15/2012" from Award Date, "NA" from Placed-In-Service Date cells.]
2014-11-30 | [10 empty] | Lot 2.1 Demolition, Site Clearing |  | 1099 | 1099 | 2014-06-16 | 2014-08-29 | 2014-10-29 | 2014-12-12 | 80% |  |  | Contractor mobilized 16 June 2014. Fourteen bunkers have been uncovered and are being removed. Final stump and root clearing work was added by modification to this contract. Completion anticipated for 12 Dec 2014. [Removed text entry of "N/A" from Solicitation Date,and "Constr Oblig to FRG 3/15/2012" from Award Date cells.]
2014-11-30 | [10 empty] | Lot 2.2 Mass Grading |  | 20158 |  | 2015-03-15 | 2016-04-15 | 2016-04-15 |  | 0% |  |  | 100% P&S received 28 July 14 and approved 7 Aug 14. Release of solicitation by German govt is anticipated for December 2014. [Removed text entry of "N/A" from Solicitation Date, "Constr Oblig to FRG 3/15/2012" from Award Date, and "TBD" from Current Completion Date cells.]
2014-11-30 | [10 empty] | Transformers/Substation |  | 19557 |  | 2015-03-15 | 2017-01-15 | 2017-01-15 |  | 0% |  |  | FRG to solicit in est. 2QFY15. German government solicitation and award dates to German industry are estimated. [Removed text entry of "N/A" from Solicitation Date, and "Constr Oblig to FRG 3/15/2012" from Award Date cells and "TBD" from Current Completion Date cell.]
2014-11-30 | [10 empty] | Lot 3.9 Site Security |  | 6215 | 6215 | 2015-01-05 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 0% |  |  | Contract for overall site security. Contract will run through the end of construction. [Removed text entry of "N/A" from Solicitation Date, and "Constr Oblig to FRG 3/15/2012" from Award Date cells.]
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 72661 | Medical Center Replacement, Incr 2 | 76007 |  |  | Lot 3.1 Construction Preparatory Measures |  | 26097 |  | 2015-04-15 | 2016-04-15 | 2016-04-15 | 2015-12-30 | 0% |  |  | ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package awaiting solicitation pending resolve of water/supply/ redundancy/ hygiene discussions. Anticipated to be released for solicitation late Nov 2014. [Removed text entry of "N/A" from Solicitation Date, and "Constr Oblig to FRG 8/27/2013" from Award Date cells.]
2014-11-30 | [10 empty] | Lot 4 Access Control Point, Bridge, External Roadways |  | 54539 |  | 2016-02-15 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Currently at 35% design. German government solicitation and award dates to German industry are estimated. [Removed text entry of "N/A" from Solicitation Date, and "Constr Oblig to FRG 8/27/2013" from Award Date cells and "TBD" from Current Completion Date cell.]
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 72662 | Medical Center Replacement, Incr 3 | 76007 |  |  | Lot 5.1 Parking Structures, Campus Roadways |  | 59043 |  | 2016-06-17 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Included in MedCen 20% design. EUD provided letter authorizing the design kickoff, currently targeted for Nov 2014. German government solicitation and award dates to German industry are estimated. [Removed text entry of "N/A" from Solicitation Date, and "Constr Obligation to FRG est. Mar 2015" from Award Date cells, and "TBD" from Current Completion Date cell.]
2014-11-30 | 2015 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 76872 | Medical Center Replacement, Incr 4/5 | 76007 |  |  | Medical Center (Bed Tower, D&T, Clinics, Admin) |  | 635222 |  | 2019-02-12 | 2022-11-08 | 2021-12-08 |  | 0% |  |  | US led 20% MedCen final design submitted 2 Aug 2013. USACE is transitioning design to German government. German govt AE target selection date is est. Dec 2014 for follow-on 20-100% design. German government solicitation and award dates to German industry are estimated. Note must be updated. Admin now apart of Med Ctr. [Removed text entry of "N/A" from Solicitation Date, and "Constr Oblig Est. Mar 16" from Award Date cells, and "TBD" from Current Completion Date cell.]
2014-11-30 | 2017 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 81410 | Medical Center Replacement, Incr 6 | 76007 |  |  | Lot 5.2 Central Utility Plants, Helipads |  | 55874 |  | 2017-03-06 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Pending funding profile determinations, currently estimated for construction obligation in FY15. German government solicitation and award dates to German industry are TBD. [Removed text entry of "N/A" from Solicitation Date, and "Constr Oblig Est. Mar 17" from Award Date cells, and "TBD" from Current Completion Date cell.]
2014-11-30 | [10 empty] | CAT E/F Equipment |  | 29261 | [5 empty] | 0% |  |  | [Removed text entry of "TBD" from Current Completion Date cell.]
2014-11-30 | 2007 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 52330 | Clinic Replacement, Inc 1 |  | 2007-02-16 | 2007-07-19 | Caddell Construction Co, Inc | W91278-07-C-0037 | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100% |  |  | Water intrusion problem update - AE and Contractor being contacted - expect AE response Jan 2015.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 67647 | Clinic Replacement, Inc 2 | 52330 | 2007-02-16 | 2007-07-19 | Caddell Construction Co, Inc | W91278-07-C-0037 | 32890 | 42183 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100% |  |  | Clinic has experienced water intrusion through building envelope. Air Force hired a consultant to perform assessment including destructive tests in select areas and provide a written report. SAM has initiated discussions with Construction Contractor and is in process of developing a letter of inquiry to the designer of record requesting an assessment.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65028 | Federal Healthcare Facility |  | 2007-10-01 | 2008-02-27 | Flannery Fire Protection | N40083 08 C 0069 | 6782 | 7382 | 2008-04-01 | 2009-09-02 | 2009-09-02 | 2009-09-02 | 100% |  |  | Project is financially closed.
2014-11-30 | [8 empty] | 2008-02-22 | 2008-06-17 | Walsh Construction Company of Illinois | N40083 08 C 0059 | 71567 | 75921 | 2008-08-01 | 2010-10-01 | 2010-08-27 | 2010-09-27 | 100%
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71857 | Hospital Addition |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 31112 | 32852 | 2010-12-03 | 2013-07-15 | 2013-01-12 | 2013-07-15 | 100% | 3486 |  | Funds used for FY00 Settlement, Ft. Wainwright. Residual activity on project funding items.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 53577 | Environ. Prev. Med Unit 2 Replacement |  | 2008-10-31 | 2009-03-31 | Virtexo Corporation | N40085 09 D 5033 DO 0002 | 5951 | 6558 | 2009-05-01 | 2010-10-15 | 2010-05-04 | 2010-09-08 | 100% |  |  | Project is financially closed.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 64809 | Pharacare Addition/Alteration |  | 2007-09-27 | 2008-02-29 | J2 Engineering, Inc | W91278-07-D-0073-0002 | 3381 | 3489 | 2008-03-24 | 2009-03-24 | 2009-03-24 | 2009-03-24 | 100%
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) |  | 2009-04-08 | 2009-09-28 | Turner Construction Company | W912HN-09-C-0045 | 230018 | 274954 | 2009-10-22 | 2014-05-19 | 2013-02-03 | 2014-05-19 | 99% |  |  | Contract awarded on 28 Sep 09. Received GAO protests from the two non-selecteed firms on 5 Nov 09. Contractor Terminated for Convenience on 24 Mar 10. Amended solicitation for remaining offerors on 5 May 10. Contract with Turner reinstated 5 Aug 10. Contractor on schedule; inspections and punch-outs continue. Contingencies at District: $850,131. Ribbon cutting held 7 Nov 2014.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | KANSAS | UNITED STATES | 47298 | Hospital Replacement |  | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110 | 282778 | 2010-05-03 | 2015-07-01 | 2013-07-23 | 2015-01-30 | 97% |  |  | 11/19/2014 Fort Riley Replacement Hospital. a. Current CCD: 13 May 2014 b. Placement: 97% actual vs. 100% scheduled (as of October's pay estimate). c. Construction in progress: Logic changes to multiple air handlers work has been completed and TAB/commissioning has restarted (with some adjustments still being made to the logic); site work in the healing garden area has started with initial concrete placements made to receive flagstone; completing the healing garden site work first pushes the testing of the atrium curtain walls to about 10 Dec; expansion joint continues on both sides of the building but is now expected to extend into Nov due to their sub not having some transition joints which will require additional fabrication; roofing subcontractor has completed replacing wet materials on the high roof; Pre-final Inspections have restarted as of 3 Nov. d. Contractor's Schedule: Schedule not accepted as of November 2013 update. Schedule updates are being analyzed by NIBS and rejected. e. Estimated Completion: USACE estimated completion is 30 Jan 2015, but the Contractor will not finish by this date if he is unable to mobilize more resources to complete work. There will be an overlap of the Hospital IO&T and IMF contractors and final Integrated Systems Commissioning and Final Inspections. The first furniture arrives on 12 January 2014. The contractor exceeded the required completion date of 13 May 2014. Liquidated damages are being withheld at $16,500 per calendar day. Corporate/senior manager engagement continues. IBA back on site testing windows, but several areas have not been repaired to allow retesting of the windows that previously failed, nor are they prepared to do the outside chamber test to verify head conditions (scheduled to come back next week). HFPA update and Council of Colonels meeting held 18 November 2014.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 63864 | Health Clinic Add/Alt |  | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC | W91DS-08-C-0019 | 27483 | 35963 | 2008-11-07 | 2012-12-01 | 2011-02-18 | 2013-12-12 | 99% |  |  | DFAS Processing MIPR Payment.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 17153 | Health Clinic Replacement |  | 2008-02-15 | 2008-05-08 | Guyco, Inc. | W9126G-08-C-0021 | 5214 | 5430 | 2008-05-08 | 2009-11-18 | 2009-11-16 | 2010-03-17 | 100% |  |  | BOD was 2 Aug 10. Ribboncutting held 28 Sep 10.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69626 | Burn Rehabilitation Center |  | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture | W9126G-08-C-0036 | 18512 | 19120 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100% |  |  | Part of SAMMC-N (Part of 4TH Floor in Tower): BRU is turned over and in use, contract closeout ongoing. Project will show 100% when final payments are made. SWF provide new closeout date!!!!
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 64473 | Medical/Dental Clinic |  | 2008-07-29 | 2008-09-18 | The Korte Company |  | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 100% | 1885 |  | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2014-11-30 | 2008 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 52332 | Medical Clinic Replacement |  | 2008-05-05 | 2008-08-29 | Federal Republic of Germany |  | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 100% |  |  | Project is 100% complete with ABG7 signed 13 Jul '12. Ribbon cutting event 07 Sep '12. The contractor is in the process of filing a claim through the host nation for an amount in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. NAU will provide details on the claim.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 71653 | Hospital Replacement (ARRA) |  | 2010-06-11 | 2010-09-01 | Clark/McCarthy, JV | N62473 10 C 0001 | 418039 | 425895 | 2010-12-03 | 2013-10-17 | 2014-01-07 | 2014-01-07 | 100% |  |  | Multiple residual closeout issues.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 971B | Hospital Alteration (ARRA) |  | 2009-09-09 | 2009-12-18 | Brasfield & Gorrie, LLC | N69450 10 C 1258 | 8000 | 13282 | 2010-01-20 | 2011-12-11 | 2011-12-11 | 2011-12-11 | 100% |  |  | Project is financially closed.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 75585 | Vision Center of Excellence |  | 2010-02-17 | 2010-06-25 | Clark / Balfour Beatty, JV | N40080 10 C 1506 | 3900 | 3900 | 2011-03-01 | 2011-07-21 | 2011-07-31 | 2011-07-31 | 100% |  |  | Project is financially closed.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 73599 | Hospital Renovation & MRI Addition (Cong Add) |  | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178 | 28389 | 2010-12-03 | 2014-04-01 | 2015-01-02 | 2015-03-04 | 88% |  |  | Active Project.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | GUAM GU | GUAM | 55918 | Central Utility Plant |  | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034 | 13672 | 2009-10-01 | 2011-06-22 | 2011-02-07 | 2011-06-22 | 100% |  |  | Residual closeout issues.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 70350 | Hospital Alteration (ARRA) |  | 2011-07-26 | 2011-09-15 | Federal Contracting DBA Bryan Construction |  | 15929 | 20393 | 2011-11-08 | 2014-03-23 | 2013-11-27 | 2014-01-21 | 99% |  |  | -------CONSTRUCTION STATUS------- Overall Construction Completion - 100% Temp AHU-100%; AHU#6-100% --4th Floor-- BOD 20 May 2013 --5th Floor-- BOD 20 Jan 2014 -Chiller Plant- Need warmer weather to fully test chillers and finish commisioning.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 70354 | Hospital Replacement (Supplemental) |  | 2011-12-19 | 2012-05-09 | Turner Construction Company | W912PL-12-C-0005 | 159834 | 163146 | 2012-05-30 | 2017-07-16 | 2015-03-16 | 2017-05-15 | 30% |  |  | A Partial suspension of work associated with the water tank for a period of 120 days WAS LIFTED 5 DEC 2014. USACE ISSUED NTP FOR WATER TANKS ON 2 DEC 2014.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 64709 | Satellite Pharmacy |  | 2009-03-04 | 2009-05-21 | Liberty-Mass II |  | 1963 | 2014 | 2009-07-01 | 2010-09-03 | 2010-09-09 | 2010-09-09 | 100% |  |  | Project closed. All remaining distgrict funds were returned on 1 Apr 11. DD1354 requested. Looking into the best source for DHA to acquire final DD1354's. NWD - have you provide the 1354 to DHA?
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 79845 | Eglin Hospital Alteration (ARRA) |  | 2011-07-01 | 2011-09-23 | JE Dunn Construction | W9126G-08-D-0057 | 51133 | 59375 | 2011-10-31 | 2015-03-12 | 2014-11-06 | 2015-01-26 | 95% |  |  | Current total obligations shown in column S are for ARRA MILCON only. Current completion percentage is 95%. Obligated ARRA MILCON amount $63,930,588.18/Disbursed Amount $61,155,035.07. Required completion date 21-Dec-14/Scheduled completion 26-Jan-15. Schedule analysis shows contractor is 36 days behind schedule. Contract including all currently identified modifications is at 99.58% of PA. Unknown extent of mold, rust and unforseen site conditions of areas to be renovated present a moderate to high risk that mandatory modifications will exceed PA. CT/PET initial proposal excessive. CT/PET RFP reissued and and received 17-Sep-14. Parts of scope still under discussion with AF medical comands. This date may be extended, area under partial suspension of work due to CT/PET equipment hold by AF. Surgery Suite Phase 3, Lab phase 2, B2794 Command Office, ENT, Plastics under construction. Contractor has submitted requests for equitable adjustment. Currently there are no outstanding funds requests. $560K REA is being discussed.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 65080 | Consolidated Troop Medical Clinic |  | 2008-11-12 | 2009-02-25 | Mathis and Sons, Inc |  | 2983 | 3084 | 2009-03-16 | 2010-05-07 | 2010-03-16 | 2010-05-07 | 100% |  |  | Construction complete. Project financially complete.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 64573 | Medical / Dental Clinic |  | 2008-12-10 | 2009-05-26 | The Korte Company |  | 14342 | 14700 | 2009-05-22 | 2011-03-30 | 2011-05-15 | 2011-03-30 | 100% | 5367 |  | NTP was 11 Jun 09 // BOD is 01 Jun 2011; FAD 10-0012-04323 28 Jan 10 increased construction funds by $454,808 (from $17,178,439 to $17,633,247). Returned $500,000. Fiscal Closeout 31 Oct 13. $1.5M diverted to Wright Patterson Hospital Renovation PN72722 on August 26, 2013 by DHA.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 59987 | Primary Care Clinic Add/Alt |  |  | 2009-07-15 | MAXFour Weitz JV |  | 13627 | 14503 | 2009-08-24 | 2011-07-28 | 2011-05-30 | 2011-07-28 | 100% | 1500 |  | Project closed.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 59220 | Hospital Add/Alt (Supplemental) |  | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500 | 29108 | 2011-10-26 | 2015-06-01 | 2014-03-03 | 2015-05-26 | 69% |  |  | Delivery date of first set of curtain walls scheduled for 22 Dec 14. Electrical subcontractor continues work on permanent power within the building. Elevator power connected, rails and platform installed. Air Vapor Barrier installation is 99% complete. Metal panel installation is on going on penthouse. Penthouse roof is complete. Main Roof being installed. Drywall installation continues on 2nd floor and has started on ground and first corridors only. Contractor & Corps working together on improving date for curtain wall glass installation so as to maintain the BOD above.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) |  | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture | W912QR-11-C-0040 | 76944 | 82983 | 2011-10-25 | 2015-03-18 | 2014-09-09 | 2015-03-18 | 92% |  |  | Large dollar changes prompted a funding request for an additional $4.88M. $4M delivered on 18 Jun 14 and Logistics/Facilities back in contract. All user requested changes to be approved by DHA. Mandatory mods being approved by DHA was causing delays. Kitchen and the impact to putting Logistics/Facilities back in have been negotiated. The new contract completion date is 18 March 2015. BOD will also be 18 March 2015. 31 of 34 departments will be in full use and possession by Air Force on 22 Dec 14. Projections are the project will finish well within the $4.88M funds.
2014-11-30 | [8 empty] | 2011-03-07 | 2011-03-20 | A1 Tree Service (Tree Cutting) |  | 9.6 | 9.6 | 2011-03-20 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 100% |  |  | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation. [Removed "UNK" from "Prime Contract Number"]
2014-11-30 | [8 empty] | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp (Swing Space) | W912QR-11-C-0027 | 5395 | 5395 | 2011-07-01 | 2011-12-05 | 2014-09-27 | 2014-09-27 | 98% |  |  | Swing Space awarded for risk mitigation: avoidance of delays in removation execution due to construction of transition space for phasing. Swing Space is BOD and contract is now in lease period.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 62189 | Medical / Dental Clinic Replacement |  | 2008-10-27 | 2009-04-03 | Hensel Phelps |  | 47615 | 51375 | 2009-06-01 | 2012-06-04 | 2011-10-26 | 2012-02-09 | 98% |  |  | Ribbon-cutting took place 29 June 2012. SWD - will provide additional details on possible claim.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) |  | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy | W9126G-10-C-0087 | 529989 | 559532 | 2010-11-08 | 2015-03-01 | 2014-05-31 | 2015-06-30 | 89% |  |  | Hospital- Interior continues in all parts of the Hospital. Flooring continues in ER area, Corian Wall Panels for OR continue. Wood casework continues on 1st Floors and 2nd Floors. Mechanical and Electrical finish work on going. HVAC systems undergoing Pre-Functional Testing for commissioning. Contractor prepping and installing Major medical equipment (CT scan, Surgical Lights). Continuing elevator install and testing. Installing trash/linen pneumatic tubes along with supply pneumatic tube system. CCD was contractualy 23 Nov 14; however, the contractor missed the date and USACE is assessing liquidated damages. Clinics: Medical equipment move-in for West Clinic continues; contiuing to work punchlist items in West/North Clinic. Interior work continues for South Clinic and we expect to begin furniture move in for South Clinic- 5 Jan 15. Continue exterior finish work. Garages: Contractor continues erecting stairs. Elevator install continues. Continuing electrical rough-in and installing lights. Installing trash/linen pneumatic tubes and supply pneumatic system. Site: Contractor continues to work outside the bubble on Santa Fe. Currently working on north side of Santa Fe and Wratten. Continue sidewalk and drives around the facilities. The project continues to experience delays due to production and schedule management issues by the general contractor and we expect the BOD to slip further. The government is currenlty review the new schedule logic proposed by the contractor and assessing the impacts of the potential BOD slippage with HFPA.
2014-11-30 | [8 empty] | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc, Sanitary Sewer |  | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 100% |  |  | Construction 100% Complete
2014-11-30 | [8 empty] | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities | W9126G-10-C-0032 | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 100% |  |  | Construction 100% Complete
2014-11-30 | [8 empty] | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc., Demolition of Hood Stadium | W912DY-05-D-0011 | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 100% |  |  | Construction 100% Complete
2014-11-30 | [8 empty] | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. New Stadium | W9126G-09-D-0100 | 17290 | 15383 | 2011-01-06 | 2013-12-15 | 2012-06-29 | 2013-12-15 | 99% |  |  | Contractor working on additional punchlist items and close out documentation.
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74728 | Hospital Replacement, Electrical Funding (100% ARRA) | 74650 | 2010-05-21 | 2010-06-11 | RMA Land Construction, Inc., Infrastructure, Electrical Distribution & Telecomm | W9126G-09-D-0100 | 9698 | 10156 | 2010-07-20 | 2012-09-20 | 2012-07-26 | 2012-09-20 | 100% |  |  | Construction 100% Complete
2014-11-30 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 53341 | Medical Instruction Facility |  | 2008-11-13 | 2009-02-20 | Innovative Technology Solutions, Inc | W9126G-08-D-0085 | 10432 | 15334 | 2010-01-27 | 2012-08-14 | 2010-06-02 | 2010-11-12 | 100% | -1539 |  | Revoke $1,538,899.27 of FY09 DODM Const Funds from HQ USACE (see Line 3 attached MS Excel Summary) from FY09, PN53341, Medical Instruction Facility, Fort Sam Houston, TX. This project is 'Fiscally Complete' and these funds are no longer required at HQ USACE.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | UNITED KINGDOM | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement |  | 2010-06-16 | 2010-12-14 | Vinci Construction UK |  | 13098 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 100% |  |  | Estimated financial closure: 31 Dec 2014
2014-11-30 | [8 empty] | 2013-04-05 | 2013-06-15 | VolterFitzpatrick (Sidewalk) |  | 68 | 68 | 2013-07-01 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 100%
2014-11-30 | [8 empty] | 2014-08-20 | 2014-08-25 | Vinci Facilities (Entrance door amendments) |  | 69 | 69 | 2015-01-06 |  | 2015-01-30 | 2015-01-30 | 0% |  |  | DIO cannot close main project until this local order is complete. [Removed text entry of "N/A" from Placed-In-Service Date cell.]
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | ALASKA | UNITED STATES | 71310 | Aeromedical Services/Mental Health Clinic |  | 2009-09-18 | 2010-02-25 | Davis Constructors & Engineers, Inc. |  | 19839 | 20258 | 2010-03-11 | 2011-11-29 | 2011-10-15 | 2011-11-29 | 100% | -577 |  | Project closeout occurred 18 June 2012.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | ALASKA | UNITED STATES | 69805 | Health Clinic Add/Alt |  | 2009-11-30 | 2010-02-10 | Bristol Design Build Services LLC |  | 3087 | 3140 | 2010-02-22 | 2011-03-18 | 2011-05-23 | 2011-03-18 | 100% |  |  | Project closeout occurred 19 Apr 2012.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 69295 | Health and Dental Clinics |  | 2010-04-26 | 2010-09-23 | Korte Construction Company |  | 17616 | 18171 | 2010-10-20 | 2012-02-27 | 2012-02-13 | 2012-02-27 | 100% |  |  | Project closed.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 64481 | Blood Donor Center Replacement |  | 2009-11-05 | 2010-09-24 | IAP-Leopardo |  | 7792 | 7904 | 2010-11-12 | 2012-08-05 | 2012-05-05 | 2012-05-05 | 100% | -3185 |  | Project is Financially Complete. DHA provided $800K of reprogrammed FY10 MILCON funds from the Blood Donor Center, Ft. Benning project to the FY07 SSP project via 0$FAD on 3/4/14. Contingencies at District: $0
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 71620 | Dental Clinic |  | 2009-12-23 | 2010-03-31 | EJS Contracting, Inc. |  | 2549 | 2619 | 2010-04-28 | 2011-03-11 | 2011-04-28 | 2011-03-11 | 100% | -168 |  | NTP issued on 28 April 2010. FAD 11-0012-01830, 16 Nov 10, $54,040, additional construction funds. Project Financially complete.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70481 | Health and Dental Clinics |  | 2009-11-25 | 2010-09-30 | Brafield & Gorrie, LLC | W912HN-10-C-0068 | 9742 | 10101 | 2010-10-21 | 2012-06-04 | 2012-03-22 | 2012-03-22 | 100% | -818 |  | D/B contract awarded 30 Sep 10. Bid savings withdrawn by DHA. Construction Complete. Contingencies at District: $0. Project Fiscally Complete.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70557 | Health Clinic Addition/Alteration |  | 2010-04-12 | 2010-09-27 | Charpie-Korte Joint Venture |  | 4018 | 4034 | 2010-09-30 | 2011-06-30 | 2012-02-05 | 2011-06-30 | 100% | -2278 |  | Project was Closed Out at LRL - 20 Mar 12 (A) . Any remaining funds may be returned. DHA moved $785K of FY10 bid savings from the Health Clinic, Ft. Campbell project to Boundary Gate, Nalin Pond, project at Ft. Detrick, MD on 3/4/14.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61401 | Boundary Gate at Nallin Pond |  | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075 | 10119 | 2011-01-12 | 2014-12-31 | 2013-01-10 | 2014-12-31 | 94% | 785 |  | % Complete (Scheduled/Actual): 96/94 Intersection work underway . BOD is 31 Dec 14; slip due to old utility pole removal/relocation. All pending modifications/REAs are settled. Remaining contg is $33k. Project is current within Congressional authority (NTE $12.692M).
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61536 | Emergency Service Center |  | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | W912DR-10-C-0087 | 13478 | 13858 | 2010-07-19 | 2013-05-23 | 2012-09-16 | 2013-05-23 | 100% |  |  | BOD achieved 23 May 13. Final punchlist item complete. Reviewing payroll documentation prior to processing final pay. No additional contingency required. Expected to closeout March 2015..
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67948 | NIBC Truck Inspection Station & Road |  | 2010-09-02 | 2010-10-29 | CFM Engineering | W912DR-11-C-0002 | 2880 | 3132 | 2010-12-15 | 2012-07-05 | 2011-12-15 | 2012-07-05 | 99% |  |  | PDT is currently planning for project fiscal closeout (19 Dec 14) to include dates for all remaining activities.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 64153 | Dental Clinic Addition/Alteration |  | 2009-10-20 | 2010-07-02 | TMG Services |  | 3890 | 4319 | 2010-07-22 | 2012-03-19 | 2012-01-13 | 2012-03-15 | 100% | -712 |  | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64244 | Consolidated Health Clinic |  | 2009-10-28 | 2010-09-30 | Korte Construction Company | W912HN-10-C-0069 | 15313 | 16186 | 2010-10-21 | 2012-10-26 | 2012-05-18 | 2012-10-26 | 100% | -6655 |  | D/B contract awarded 30 Sep 10. Construction complete. Contingencies at District: $0.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) |  | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. | W912HN-11-C-0002 | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 100% | -458 |  | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0. Final Payment made to contractor on 20 Aug 14.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 69711 | Dental Clinic |  | 2009-11-03 | 2010-06-16 | The Korte Company |  | 8199 | 8199 | 2010-07-30 | 2012-03-04 | 2012-01-04 | 2012-01-04 | 100% | -1016 |  | Project Financially Closed 20-MAR-2013
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69294 | Health and Dental Clinics |  | 2010-02-17 | 2010-11-17 | LEC-CMS, LP | W9126G-11-C-0005 | 12743 | 13018 | 2011-02-07 | 2012-08-20 | 2012-05-22 | 2012-12-31 | 100% | -3280 |  | All funds have been returned.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 71318 | Dental Clinic Replacement |  | 2009-10-28 | 2010-02-26 | J E Dunn Construction Company | W9126G-08-D-0057 | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 99% | -3144.239 |  | Contract Complete 1 Spet 12. Waiting on payroll issues to be resolved before we can close out financially. SWF to provide a New close out date shortly. Retainage being held.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 70343 | Health and Dental Clinic Additions |  | 2009-12-04 | 2010-03-24 | Vet Industrial of Bremerton, WA |  | 7219 | 7583 | 2010-04-19 | 2011-05-13 | 2011-05-07 | 2011-05-02 | 100% | -2109 |  | Project complete/closed. DD1354 requested. Looking into best source for DHA to acquire transfer documents.
2014-11-30 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center, Phase 1 |  | 2010-06-11 | 2010-08-19 | J E Dunn Construction Company (Bldg 1 & CEP) | W9126G-08-D-0057 (TO 0005) | 41566 | 45105 | 2010-10-04 | 2013-11-19 | 2013-02-20 | 2013-08-30 | 99% |  |  | Building 1 is complete and turned over to the Air Force. BOD is 19 Nov 13. Interim DD 1354 has been signed by BCE 5 Dec 13. Closeout Correction and verification of punchlist deficiencies continues. Contractor working stone issue.
2014-11-30 | [8 empty] | 2010-06-11 | 2010-08-31 | J E Dunn Construction Company (Parking Structure & Temp Parking) | W9126G-08-D-0057 (TO 0006) | 23216 | 24153 | 2010-10-04 | 2012-12-13 | 2012-02-26 | 2012-11-30 | 99% |  |  | Phase 1A consisting of a multi-story parking garage and a Central Energy Plant is complete and turned over to the Air Force. BOD 13 Dec 2012. Parking garage stone header failure repair under evaulation by SWF Structural Engineering. Awaiting installation of type A1 and A2 signage.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77116 | NNMC Parking Expansion |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 14030 | 14392 | 2012-06-18 | 2013-12-02 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77115 | Transient Wounded Warrior Lodging |  | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133 | 48829 | 2012-06-18 | 2014-05-27 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70482 | Health Clinic Addition/Alteration |  | 2010-11-19 | 2011-06-03 | McCarthy Building Companies | W912HN-11-C-0006 | 23050 | 26519 | 2011-06-21 | 2013-11-29 | 2013-06-20 | 2014-05-06 | 100% |  |  | The contract completion date has passed. Commissioning underway. The IO&T contract has began and the building is currently under joint occupancy. Contingencies at District: $841,649. Will return funds ASAP. New close out date to be provided. Commissioning complete.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MASSACHUSETTS | UNITED STATES | 71634 | Mental Health Clinic Addition |  | 2011-11-04 | 2011-12-23 | Watermark Environmental, Inc. | W912WJ-12-C-0002 | 2790 | 2790 | 2012-05-18 | 2013-02-16 | 2013-01-16 | 2013-03-01 | 99% |  |  | Contract substantially complete 16 Feb, Customer move-in complete. AS-Built issues have been resolved and they are complete. 1354 was submitted to the customer for signature. 1354 issues with the Customer have been resolved. AE contract that needed to be modified for a descop/deobligation is complete. 1354 will be modified by early December with the final project accounting and provided to Customer for final review.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 73360 | Consolidated Logistics Facility |  | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869 | 19957 | 2011-07-21 | 2014-12-05 | 2014-01-06 | 2014-11-14 | 99% |  |  | % Complete (Scheduled/Actual): 99/99 1354 signed 7 Oct 14. Punchlist item completion by mid Dec 14. Furniture funding for both CONLOG buildings was received; anticipating install Feb 2015.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 62886 | Information Services Facility Expansion |  | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | W912DR-12-C-0004 | 4270 | 4626 | 2012-03-19 | 2015-02-10 | 2013-11-09 | 2015-02-28 | 85% | 232 |  | % Complete (Scheduled/Actual): 85/85. Building interior being painted. Furniture contract awarded for installation 20 Jan 15. Below Threshold Reprogramming (BTR) of $232K from Health and Dental Clinics, White Sands to Information Services Facility, Ft. Detrick, MD executed on May 6, 2014.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67949 | NIBC Security Fending and Equipment |  | 2011-08-19 | 2012-02-14 | Cont #1 (Segment 1) (Rich Moe Enterprises, LLC) | W912DR-12-C-0001 | 1701 | 1701 | 2012-04-02 | 2013-04-01 | 2013-04-02 | 2013-04-01 | 100% |  |  | Construction contract closeout underway.
2014-11-30 | [8 empty] | 2015-02-13 | 2015-05-29 | Cont #2 (Segment 2) (TBD) |  |  |  | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | 95% design under review. RTA date for Fence Segment 2 is 30 Jan 15. Contract solicitation will include USAMRIID Replacement North Parking which establishes overall site contours for fence construction. Combine with RID. [Removed text entry of "TBD" from Original Contract Amount and Current Contract Obligation cells.]
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67953 | Supplemental Water Storage |  | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468 | 3944 | 2011-07-20 | 2015-01-15 | 2012-11-01 | 2014-05-30 | 97% | 263 |  | % Complete (Scheduled/Actual): 100/97 Contractor having difficulty completing pump facility. LD's being assessed. BOD remains 15 Jan 15 due to contractor performance and need to secure final MDE water system connection permit. Liquidated damages assessed since 30 May 2014. NAD will provide a new CCD soon.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67951 | Water Treatment Plant Repair |  | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308 | 15434 | 2013-01-14 | 2015-04-30 | 2014-07-08 | 2014-11-17 | 83% | 5000 |  | % Complete (Scheduled/Actual): 93/85 BOD slipped due to city sewer connection and contractor performance. Commissioning underway. Potential CWE is showing 105% above PA.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 70472 | Health and Dental Clinic |  | 2010-11-02 | 2011-07-22 | Charpie-Korte Dsn-Bld JV S.B. L.L. |  | 14837 | 15067 | 2011-08-18 | 2013-04-26 | 2013-03-30 | 2013-08-02 | 99% | -1095 |  | Clinic Construction Virtually Complete. Landscaping Items are finishing up and Punch List remain to be completed. Final Payment scheduled for 13 Dec 2013, Project clousout scheduled for Feb 2014. DHA reprogrammed FY11 MILCON funds @ $600k from Health and Dental Clinic, White Sands to Fort Detrick Water Treatment Plant on 3/13/14.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72752 | Ambulatory Care Center Phase 2 | 72430 | 2011-05-20 | 2011-09-28 | SKANSKA USA Building Inc. | W9126G-11-C-0053 | 80558 | 92111 | 2011-12-02 | 2015-03-15 | 2013-10-01 | 2015-02-03 | 96% |  |  | PH 2 Construction Progress: Sch. 96% Act. 96% with BOD of 15 Mar 2015. Phase 2 includes Buildings A, B & C. Different levels of MEP work are underway or finishing. Casework installation is ongoing. Punch list continues on exterior elevations. Central Energy plant equipment startup, testing, and commissioning is ongoing. An Un-priced Change Order (UCO) was issued with an NTE of $310,000 to allow immediate work on previously identified pending modifications. As a requirement of this modification the Contractor (Skanska) is required to submit a proposal is within 20 days, and the UCO modification will be finalized w/i 30 days. This modification is expected to add up to 50 days to the Phase 2 completion date (currently 3 Feb 2015). As a result the construction completion date is expected to shift to mid-March, and the BOD to April. Funds being used to help end state of project.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 71251 | Dental Clinic Replacement |  | 2009-09-16 | 2011-05-17 | Forrester Construction Company |  | 2832 | 3185 | 2011-05-17 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | Project Complete. Paid Final Invoice, and received Release of Claims from Contractor. Construction Contract and Project now in Close Out Phase. Fiscal Closeout is scheduled, and tracking for 13 Jan 2015, along with Project # 64241.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 47344 | Preventive Medicine Facility |  | 2011-05-03 | 2011-09-13 | Charpie-Korte Group LLC |  | 7230 | 7676 | 2011-10-14 | 2013-02-28 | 2013-02-28 | 2013-02-28 | 100% |  |  | Project closed.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 66693 | Health/Dental Clinic Replacement |  | 2013-07-09 | 2013-09-30 | Federal Republic of Germany |  | 34294 | 34376 | 2014-02-03 | 2016-06-11 | 2015-08-22 | 2016-04-12 | 24% |  |  | 03DEC14 CONSTRUCTION STATUS: Concrete roof slab and bituminous membrane is substantially complete; roof installation is ongoing. Exterior window and heating line installation is ongoing. Interior plaster work has started. Foundation work for the mechanical enclosure is continuing along with the parking lot curbstone and gutter installation.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 66588 | Health Clinic Add/Alt |  | 2012-11-07 | 2013-03-18 | Federal Republic of Germany |  | 32103 | 32103 | 2013-04-08 | 04 Oct '16 | 2016-04-12 | 04 Sep '16 | 55% |  |  | 03DEC14 CONSTRUCTION STATUS: - Interior mechanical & electrical work continues along with plumbing, ductwork and communications on the 1st and 2nd floor. Erecting walls and door frames on 1st and 2nd floors. Interior finish work continuing including painting, tiling, walls, and flooring. Continuing installation of exterior facade and work on rooftop mechanical room.Construction of new lobby between existing and new clinic ongoing. Work on the building perimeter fire lane, new entry, and site grading is continuing.
2014-11-30 | 2011 | Defense Health Agency | Major Military Construction | KOREA, SOUTH | KOREA, SOUTH | 51740 | Health/Dental Clinic Replacement |  | 2011-05-13 | 2011-08-26 | Ilsung Construction Co., Ltd. | W912UM-11-C-0024 | 9821 | 10169 | 2011-08-26 | 2014-04-23 | 2013-05-13 | 2014-04-23 | 100% |  |  | New health/dental clinic building transferred 16 May 13. Existing health clinic is being retained by the DPW at their request. Existing dental clinic demolished 19 Mar 14. Project BOD is actualized at 23 Apr 14. POF discussed the ribbon cutting ceremony with HFPO (LTC Marsh) who responded that the 65th MED BDE is conducting the ceremony and will issue invitations. As of 4 Aug 14, no ceremony date has been set. Delay was due to deficiencies, however, all have been corrected as of 22 Jul 14. The Carroll Dental Clinic OIC and NCOIC were in the lead for the ceremony, however, per HFPO, preparations for a ceremony does not appear to be occurring. Total project BOD (incl demo) was actualized at 23 Apr 14. Final payment on the construction contract was disbursed 27 Aug 14. Awaiting final billing and return of excess funs from Huntsville Center for LOGCAT F procurement.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | UNITED KINGDOM | UNITED KINGDOM | 72727 | Medical/Dental Clinic Replacement |  | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd |  | 11958 | 11958 | 2014-05-06 | 2015-07-31 | 2015-10-30 | 2015-11-17 | 33% | 13060 |  | Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65030 | Naval Hospital Great Lakes Health Clinic Demolition |  | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co | N40083 12 C 0001 | 5835 | 6195 | 2012-09-12 | 2014-04-21 | 2013-09-13 | 2014-08-08 | 100% | -3994
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 79554 | Child Development Center |  | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200 | 14457 | 2013-03-01 | 2014-04-07 | 2014-02-22 | 2014-06-02 | 100%
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71408 | Dental Clinic Replacement |  | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18688 | 18688 | 2013-03-01 | 2016-12-06 | 2016-09-29 | 2017-01-28 | 0% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | MISSISSIPPI | UNITED STATES | 71503 | Branch Health Clinic |  | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Constr, Inc | N69450 12 C 0754 | 19096 | 19758 | 2012-09-01 | 2014-09-09 | 2014-09-09 | 2015-05-22 | 78% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 70597 | Medical Clinic |  | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC | W91278-12-C-0028 | 8897 | 9123 | 2012-10-17 | 2015-01-05 | 2014-10-07 | 2014-10-07 | 99% |  |  | Contingencies at District available for obligation $122,390. Project on schedule no issues.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 72292 | Hospital Addition/Alteration Phase 2 |  | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. | W912HN-12-C-0019 | 37778 | 42842 | 2012-10-15 | 2017-03-23 | 2016-10-14 | 2017-02-14 | 66% |  |  | Design error (for exterior precast panels) required work stoppage to remove, redesign, & replace the panels. 145 days were added to the emergency dept interim milestone & 83 days to overall project completion. Modification to add medical air was issued unilaterally and could impact schedule. Contingencies at district: $540,678. Potential AE Liabilities.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70438 | Hospital Addition/Alteration |  | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company (DBA: Mortenson Construction) | W912QR-12-C-0036 | 43466 | 46142 | 2012-08-22 | 2015-05-23 | 2015-02-21 | 2015-03-25 | 82% |  |  | Curtain Wall - Flood Event Issue: Work continues to move forward with the KTR's Alternate Design. The exterior enclosure work has commenced at all locations with the framing and sheathing finishing up in all locations and air barrier to begin shortly. Still waiting to see a claim/REA from the Contractor that shows the cost impact due to the Curtain Wall issue. 21 2 day delay. Claim could cause an ATR if KO approves current amount of about $5M.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 70351 | Hospital Alteration |  | 2012-02-22 | 2012-08-10 | The Robins & Morton Group | W912HN-12-C-0013 | 22400 | 23219 | 2012-09-13 | 2014-09-30 | 2014-06-23 | 2015-12-04 | 66% |  |  | Contractor behind schedule 73%. 6th floor final completed; 5th floor final completed; 3rd floor final completed; 4th floor pre-final completed. Contingencies at District: $272,903. SAS to provide new BOD. Contractor has been issued an Interim Marginal CCASS. Contractor has had issues since June with resources and rework. Contractor has also experienced issues with properly managing and scheduling work on site. Quality Control has slipped as well causing undue rework thus additional schedule slip. Several face to face and telephone meetings have been held between SAS and upper level at R&M. Contractor has made some improvements between mid Aug and Sept with resources.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70580 | Dental Clinic Addition /Alteration |  | 2012-08-02 | 2012-12-10 | Structural Associates Inc. | W91DS-13-C-0002 | 4370 | 4370 | 2013-01-09 | 2015-04-09 | 2015-01-09 | 2015-01-09 | 98% |  |  | Completing punch list item. Commissioning of systems underway.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70579 | Medical Clinic (SFCC) |  | 2012-10-05 | 2013-02-13 | Structural Associates. Inc. | W912DS-13-C-0022 | 8934 | 8934 | 2013-03-15 | 2015-06-11 | 2015-03-11 | 2015-03-11 | 87% |  |  | Continue interior framing and drywall installation. Continue rough-in of electrical, mech., plumbing, fire protection. Site work ongoing and installation of utilities complete.
2014-11-30 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 51969 | Hospital Nutrition Care Department Add/Alt |  | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company | W9126G-12-C-0050 | 28291 | 26993 | 2012-10-02 | 2015-02-26 | 2014-10-30 | 2015-04-13 | 74% |  |  | Project RFP included a detailed equipment list which included the statement “For Information Only,” permitting the contractor to deviate from the equipment list, resulting in a design which changed the meal preparation and distribution operations and increased staffing. Health Facilities Planning Agency (HFPA) requested a redesign to eliminate these problems. The re-design resulted in a 283 day delay. The contractor's estimate was $1.5M greater than the government's. Negotiations concluded on 4 April without the contractor and government in agreement. The government issued a unilateral contract modification 9 April 14. *The contractor subsequently filed seven claims regarding this issue on 31 Sep 14, totaling $1,370,385. Total available contingency is6 currently $2,667,364. - KO reviewing claims for merit - OC extended response date to 15 Jan 2015.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 72808 | Medical Clinic Replacement |  | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc | N62473 10 D 5412 DO 0007 | 18703 | 18703 | 2014-02-28 | 2015-04-16 | 2015-03-16 | 2015-03-16 | 13%
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 78143 | Navy Drug Lab Replacement |  | 2013-01-14 | 2013-08-22 | Blinderman Constr Co | N40083 13 C 0003 | 14864 | 14774 | 2013-11-08 | 2015-02-15 | 2015-01-15 | 2015-04-18 | 74%
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71507 | Branch Health Clinic Replacement |  | 2013-02-28 | 2013-12-18 | Turner Construction Co | N40080 14 C 0154 | 41408 | 41451 | 2014-04-30 | 2016-04-04 | 2015-10-15 | 2015-11-18 | 19% |  |  | Groundbreaking is the 18 April 2014.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80307 | Implement Base Installation Appearance Plan |  | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898 | 4608 | 2014-04-01 | 2015-03-17 | 2015-03-31 | 2015-06-15 | 3%
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities |  | 2013-07-25 | 2012-09-12 | G-W Management Servicxes Inc (Dosimetry Award) | N40080 10 D 0498 DO 0025 | 5286 | 5217 | 2013-10-15 | 2014-04-04 | 2013-12-13 | 2014-03-25 | 100%
2014-11-30 | [8 empty] | 2014-03-15 | [12 empty] | On hold per DHA [Removed text entry of "No Entry" from Award Date cell.]
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80308 | Electrical Utility Upgrades |  | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947 | 26947 |  |  | 2016-02-12 | 2016-02-12 | 1% | 19460 |  | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 78144 | Medical Clinic Addition |  | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354 | 14586 | 2013-10-08 | 2015-03-31 | 2015-03-17 | 2015-07-08 | 69%
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71317 | Medical Clinic Replacement |  | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744 | 39996 | 2013-12-06 | 2017-10-08 | 2016-12-30 | 2017-08-16 | 26%
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 78146 | Veterinarian Facility |  | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254 | 7450 | 2014-02-28 | 2015-05-15 | 2014-12-06 | 2015-06-22 | 33%
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 51639 | USARIEM Replacement High Altitude Research Lab |  | 2015-07-30 | 2015-12-31 | [11 empty] | Received Code 7 Directive on 26 Jun 14. PM met with stakeholders the week of 28 Jul 14 to discuss the way forward and develop the revised design schedule. The most significant action impacting project completion will likely be the preparation of NEPA documents by the City of Colorado Springs. Will need Funds authorization extension. EXPECT CODE A request by 15 March 2015.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 72718 | Medical Logistics Warehouse Replacement |  | 2012-10-18 | 2013-06-18 | R&W Builders | W912QR-13-C-0021 | 2215.9 | 2215.9 | 2013-07-01 | 2014-07-30 | 2014-04-27 | 2014-07-23 | 100% |  |  | Project awarded 18 Jun 13, NTP issued 1 Jul 13. A contract time extension for weather delays was issued due to adverse weather conditions. Contingency balance available: $44,318 Potential UCRs: 0001- Emergency Generator Connection Point, 0002- Humidity Control in Open Bay., 0003- Walk-In Cooler Contingency Reserve: $66,477
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 71679 | Dental Clinic |  | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture |  | 10687 | 10505 | 2013-12-02 | 2015-04-29 | 2015-02-19 | 2015-02-19 | 76% |  |  | Design/Scope: Design-Build / Primary Facilities include the dental clinic (30 chairs), outdoor troop shelter and building information systems. Also includes demolition of nine buildings. End users are IET soldiers. Construction: Brick work is 100% complete, roofing is 100% complete; mechanical, electrical, plumbing (MEP) rough-in is 99%, drywall and insulation is 99%. Troop shelter is installed on the South East corner, Entry parking is striped and light poles 100% installed. Back service entrance construction is complete. Final grading and landscape is ongoing (80%), sod being placed (80%). Windows are in, exterior doors are installed. Fiber optic cable has been pulled through manholes and tested for 100% conductivity. Schedule: On schedule. LEED: Silver required (solar panels for domestic hot water and solar light tubing). Time Growth: None to date FISD: Included in contract completion date (19 Feb, 2015).
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71325 | Medical Clinic Replacement |  | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 | W9126G-08-D-0056-CV01 | 45536 | 47116 | 2013-10-24 | 2017-07-21 | 2016-04-30 | 2016-10-23 | 13% |  |  | Awarded 13 Sep 2013. NTP 24 Oct 2013. Final design underway. Contractor has begun start site work and site demo. Contingencies at District: $697,507.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77979 | Medical/Dental Clinic Replacement |  | 2013-09-03 | 2014-03-27 | JE DUNN + HWA | W9127S-13-D-6001 | 47044 | 47044 | 2014-04-28 | 2018-01-08 | 2017-10-25 | 2017-10-25 | 2% |  |  | Award on 27 March 2014. Questions raised about UST and abandoned housing debris and utilities on site 09 May 14. USACE Albq proposed courses of action and fowarded to DHA on 20 May 14. NTP was issued 12 August. Project Kickoff/Design Charrette will occur 16-19 September. Request for Equitable Adjustment for Gov't delay after award submitted by Contractor on 21 AUG 14. IGE for REA completed. Follow-up interviews with Med Group staff held 12 & 13 Nov. 2% PROGRESS FROM LAST MONTH HAS NOT CHANGED.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 73776 | Soldier Specality Care Clinic |  | 2012-11-15 | 2013-12-18 | Structural Associates | W91DS-14-C-0003 | 11163 | 11163 | 2014-01-06 | 2016-04-05 | 2016-01-06 | 2016-01-06 | 18% |  |  | Site work and underground Utility installation continues. Contractor has started construction of the building foundation. 100% Design review conducted 18 NOV 14. Minor revisions being made.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | KOREA, SOUTH | KOREA, SOUTH | 72420 | Medical/Dental Clinic Addition |  | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. |  | 8544 | 8745 | 2013-06-05 | 2015-05-16 | 2015-02-25 | 2015-03-29 | 72% |  |  | Contingency Amounts: District $48,970; HQ Mgmt $155,861. 32 days have been added to the CCD, however, BOD has not been changed. Contractor has completed the standing seam roofing and exterior insulation finish system work except final coating work. Working on HVAC ducts and piping, domestic water piping, fire sprinkler piping, electrical conduit, cable tray installation work at 2nd floor. Major issue is the DIPC user-requested change. The change request will be routed for approval based on the interim change guidance (including all additional signatures). Release of some management reserve is anticipated.
2014-11-30 | 2013 | Defense Health Agency | Major Military Construction | KOREA, SOUTH | KOREA, SOUTH | 72419 | Hospital Addition/Alteration |  | 2013-07-26 | 2013-09-26 | Seohee Construction Co., Ltd. |  | 22361 | 22325 | 2013-09-26 | 2017-10-23 | 2017-08-08 | 2017-08-08 | 21% |  |  | Contingency Amounts: District $354,535; HQ Mgmt $805,909. Completed 1) Form Removal Concrete Wall & Column for the lower level; 2) Waterproofing Walls; 3) Temp Power & Switch Gear Con'c Foundation; 4) Water Line Re-routing. Started Phase 0 work on 14 Oct 14.
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80904 | Mechanical & Electrical Improvements |  | 2014-01-30 | 2015-02-27
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80913 | Parking Garage |  | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835 | 15835 |  |  | 2016-04-16 | 2016-04-16 | 0%
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 71511 | Ambulatory Care Center | [14 empty] | Code 8 Received 30 April 2014, project is cancelled [Removed text entry of "Cancelled" from Solicitation Date, Award Date, Start Date, Placed In Service Date, Original Completion Date, and Current Completion Date cells.]
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77000 | Public Health Command Laboratory Replacement |  | 2014-03-24 | 2015-04-30 | [8 empty] | 0% |  |  | (UPDATE: 11/21/14): Project currently unawardable and undergoing Source Selection coordination (Procurement Sensitive). Source selection boards reconvened week of 06 October 2014. Briefing to DHA scheduled for 09 Dec 14. Projected contract award 30 Apr 15 subject to change pending coordination of Congressional reprogramming timeline. AB215 [Removed text entry of "TBD" from Start Date, Placed In Service Date, Original Completion Date, and Current Completion Date cells.]
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77922 | Medical Clinic Replacement |  | 2014-02-25 | 2014-08-20 | Gilbane | W9127S-13-D-6000 | 45629 | 45629 | 2014-10-27 | 2018-08-16 | 2018-01-30 | 2018-01-30 | 1% | 23279 |  | (Contractor is Gilbane Federal Joint Venture, San Antonio, TX Award Amount: $45,629,836.00. Reprogrammed $1.9M from Medical Clinic Replacement, Holloman, AFB, NM to FY14 Hyperbaric Addition at San Antonio, TX on 24 Jun 14. Scheduled the 'Pre-Work' conference and D-B Kickoff meeting / Design Charrette in October. 'Pre-Work' conference and D-B Kickoff meeting / Design Charrette held 28-31 October 2014. Gilbane submitted revised floor plans on 21 Nov 14. Floor plan telecon scheduled for 2 Dec 14.
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81340 | SAMMC Hyperbaric Facility Addition |  | 2014-03-17 | 2014-06-30 | Gilbane |  | 11289 | 11289 | 2015-07-10 | 2016-12-28 | 2016-09-30 | 2016-09-30 | 0% | 1900 |  | Contract awarded to Gilbane on 30-Jun-14. Pre-Con held 29-Jul-14. May 2013 directive increased PA to $12.6M. Construction start scheduled for 10-Jul-15. *A requirement for on-call and on-site explosive safety personnel for different phases of excavation was identified late in the RFP solicitation phase and not included in the base contract. Discussions with the installation, AFCEC and DHA should resolve issue by 5-Dec-14.
2014-11-30 | 2014 | Defense Health Agency | Major Military Construction | BAHRAIN | BAHRAIN | 81436 | Medical/Dental Clinic Replacement |  | 2015-04-15 | 2015-08-15 | [11 empty] | 1 Dec 14 - The D-B package is complete and on the shelf pending advertisement in Apr 2015 and Award in Aug 2015. This award schedule is being driven by site availability, upon completion of an on-going MCN project, the P908 Operations and Support Facilities, scheduled for completion in July 2016. TAM is planning award of the D-B contract for the Medical/Dental Clinic in Aug 2015 with a one year design period before the contractor begins construction in Aug 2016. The project CWE is $43,823,020; this CWE is up-to-date as of completion of the 35% design that will be included in the D-B RFP, and takes into account the projected award date of 15 Aug 15. TAM will have the AE re-validate this estimate upon completion of a design code refresh and BCOE review of the RFP package prior to advertisement in April. On 17 Oct 14, TAM-PM met with DHA (CAPT Berchtold) and provided a status update of project milestones and progress on construction of P908. Code update to complete by Jan 2015. P908 issues are being resolved, expect no additional schedule slippage. Code A will be requested March 2015.
2014-11-30 | 2015 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 72414 | Dental Clinic Replacement |  | 2014-12-30 | 2015-03-30 | [11 empty] | Final draft RFP submittal review complete. Revising RFP to follow the last template.
2014-11-30 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81423 | Medical Clinic Replacement (Reid Clinic) |  | 2015-01-20 | 2015-06-10 | [5 empty] | 2017-12-31 |  | 2017-08-31 | 0% |  |  | AE1 contract awarded 6 Aug 14 for $946,487.69. 35% RFP review conference held 24 Nov 14. On track for scheduled RTA 28 Jan 15.
2014-11-30 | 2015 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 81430 | Hospital Add/CUP Replacement |  | 2015-07-09 | 2015-12-15 | [11 empty] | Received Code 7 on 16 Oct 13. Orginal scheduled AE1 contract award date was 30-APR-14. Actual award on 02-SEP-14. Primary cause for delay in award of the AE1 was conflicting scope requirements and level of design for the D-B RFP between DHA and the MX. The AE1 PoP to RTA provides an Advertise date of 01 June 2015. The construction contract will also include turnkey FFE and medical equipment. Thus increasing the procurement to > $50M. FY15 award is considered high risk due to the potential for an extended period (multiple rounds of discussion) for review of D-B contract proposals [Removed text entry of "TBD" from Start Date, Placed In Service Date, and Original Completion Date cells.]
2014-11-30 | 2016 | Defense Health Agency | Major Military Construction | HAWAII | UNITED STATES | 78150 | Medical Clinic Replacement
2014-11-30 | 2016 | Defense Health Agency | Major Military Construction | HAWAII | UNITED STATES | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 |  | 2015-10-20 | 2016-03-14 | (Parking Structure) |  |  |  | 2016-04-12 | 2017-12-05 |  |  | 0% |  |  | DHA issued DA memo dated 29 Jul 13 for phase 1 with PA of $140.3M. On 16 Oct 13, DHA approved split strategy to award design-bid-build contract for parking structure, and a design-build contract for the clinic. DHA DA memo dated 30 Jun 14 provided revised 1391 and new PA $126.2M. Parking design Charrette conducted 29 Aug 14. Clinic A-E design contractor selected, award is projected in Dec 14. ISSUES: Project scope has evolved. Design time was lost. Environmental concerns limit building height due to the location in a historic district.
2014-11-30 | [8 empty] | 2015-12-10 | 2016-08-05 | (Clinic) |  |  |  | 2016-09-06 | 2017-06-22 |  |  | 0%
2014-11-30 | 2016 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 71642 | Satellite Pharmacy Replacement | [14 empty] | Code 7 received. DA dated Jan 14 moved project to FY16. Expect CWE to reach $7M due to increase in CY and new criteria on fire pumps. Complete scrub of all design criteria and RFP documents will be required. [Removed text entry of "TBD" from Solicitation Date, and Award Date cells.]
2014-11-30 | 2016 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81422 | Ambulatory Care Center Phase 4 | [11 empty] | 0% |  |  | AF is currently updating DD1391 from 2008 vintage to include HazMat and other costs. New design authorization code (Code 6) and P&D funds request will likely be the ensuing action upon receipt of revised DD1391. SWF to provide acquisition plan by 12 Dec 2014. We must have the updated 1391 in order to make schedule, can DHA help? [Removed text entry of "TBD" from Solicitation Date, and Award Date cells.]
2014-11-30 | 2016 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 77986 | Dental/ Medical Clinic Replacement |  | 2016-01-27 | 2016-06-30 | [11 empty] | Code 3 received from DHA on 26 July 2013. July 2013. 1391 amount PA has been reduced from $37M to $35M effective 08 June'14.. Presentation to DHA was held on 21 May 2014 in Washington. 20% design completed and transferred to the German government. The German AE is on board and the transition meeting was held on 28 May 2014. Started 35% design 25 July 2014; 35% submittal due first week of Dec 2014. On schedule for a June 2016 award to industry. Awaiting guidance on BIM decision. Request DHA to provide guidance.
2014-11-30 | 2017 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 72742 | Medical Clinic Replacement
2014-11-30 | 2017 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 67402 | Blood Donor Center Replacement |  | 2015-01-15 | 2015-06-25 | [8 empty] | 0% |  |  | Project is now in the FY17 DOD Medical POM and is currently Design Code 5, Deferred. SWF/SWD have not authority to expend P&D Funds on any design activity
2014-11-30 | 2017 | Defense Health Agency | Major Military Construction | GERMANY | GERMANY | 77139 | Behavioral Health Clinic Addition/Alteration | [14 empty] | When can DHA provide DA? FY17 award is at risk if DA not provided soon.
2014-11-30 | 2010 | Defense Intelligence Agency | Major Military Construction | ALABAMA | UNITED STATES | DIA10-002 | Replace MSIC Explosive Ordinance Exploitation (EOE) Complex |  | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company |  | 12000 | 12003 | 2012-07-20 |  | 2014-01-20 | 2014-05-21 | 100% |  |  | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved.
2014-11-30 | 2008 | Defense Intelligence Agency | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 154207 | Emergency Backup Water System |  | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC |  | 1012 | 1012 | 2009-10-03 | 2012-01-20 | 2011-09-16 |  | 100% |  |  | Approp. - $1,012
2014-11-30 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA11-002 | JBAB Paving of Gravel Parking Lot |  | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture |  | 2984 | 2819 | 2011-07-20 | 2012-07-25 | 2012-07-18 | 2012-07-25 | 99% | 700 |  | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2014-11-30 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000001 | DIAC Parking Garage Replacement |  | 2014-06-16 | 2014-09-23 | Arriba |  |  | 739156 | 2014-10-23 |  | 2016-03-02 | 2016-03-02 | 0% |  |  | Approp. - $13,645 - $793,156 CAT I obligated. NAVFAC Gold Team awarded the A/E contract in June 2013. Conducted the Design Charette on 18 July 2013. First NCPC, CFO and SHPO review conducted on 2 August 2013. Contract awarded on 23 September 2014. Concept Design Workshop was conducted on 20 November 2014.
2014-11-30 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center | [6 empty] | 1200 | [7 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-11-30 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000003 | DIAC Chilled Water Project for Data Center | [14 empty] | Approp. - $1,121 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-11-30 | [6 empty] | DIAC Cooling Tower for Data Center | [14 empty] | Approp. - $941 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-11-30 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | ECIP 120001 | Chiller Plant Operation |  |  | 2013-08-08 | Honeywell |  | 997 | 1071 | 2013-08-21 |  | 2014-08-08 | 2015-03-31 | 80% |  |  | Approp. - $1,200 - Project awarded August 2013. Kickoff meeting held 5 September 2013. All VFDs and field component sensors (flows, temperatures) have been installed. Optimization controls programming and graphics updates to be completed by January 2015. Commissioning (40 hours) will take place starting late February 2015. Training will be video-recorded per contract modification.
2014-11-30 | 2012 | Defense Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | DIA12000005 | Construction of Remote Delivery Facility (RDF) Meeting SCIF Standards |  | 2013-08-21 | 2013-09-25 | Heard Construction |  | 10758 | 6058 | 2013-10-10 |  | 2014-09-30 | 2015-03-11 | 46% |  |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Major construction activities last month were the floor slab placement, installation of roofing system, and exterior metal panels, and layout for interior partitions and MEP trim out. Once roof system is completed and exterior doors are installed (expected in mid-December), the facility will move to a "weathered in" condition and interior construction can move forward at a more rapid pace. Majority of final non-MILCON fitout work is now under contract; only about $160K of IT related work is not under contract as yet. Majority of increase in contract amount is due to unforeseen site conditions and extreme weather at key points in the construction schedule.
2014-11-30 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction |  | KOREA, SOUTH | DIA10-001 | FOB-K Renovation of Two Buildings to Include Administrative and SCIF Spaces |  | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd. |  | 4360 | 5050 | 2012-04-09 |  | 2013-10-09 | 2013-10-17 | 100% |  |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project in process of closeout.
2014-11-30 | 2013 | DISA | Major Military Construction |  | GERMANY | 13DISA01 | DISA Europe Facility Upgrae | [14 empty] | PA: $2.224M. Awaiting USACE to schedule Design Kick Off Meeting.
2014-11-30 | 2013 | DISA | Major Military Construction |  | USA | VDYDS97032 | Construction New New DISA CONUS Facility Scott AFB |  | 2013-05-24 | 2013-09-30 | River Sity Corporation, LLC | W912QR-13-0032 | 65994 | 65994 | 2014-03-01 |  | 2014-12-30 | 2016-03-01 |  |  |  | PA: $77.515M. Three (3) separate contracts: Soil Remediation $1.34M completed Feb 14; Construction $66M and Demolition of Bldg 3189 - TBD.
2014-11-30 | 2014 | DISA | Major Military Construction | HAWAII | USA | 14DISA01 | DISA Pacific Facility Upgrade | [14 empty] | PA: $2.615M. NAVFAC preparing RFP for Design.
2014-11-30 | 2008 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INC #1 - NAV SUP Fleet Logistics Center, Point Loma San Diego |  | 2008-02-20 | 2008-09-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-11-30 | 2010 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) - NAV SUP Fleet Logistics Center, Point Loma San Diego |  | 2008-02-20 | 2011-03-22 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-11-30 | 2010 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC0908 | Replace Jet Fuel Storage Complex - Jacksonville ANG |  | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | W912EP-10-C-0023 | 7909 | 9988 | 2010-04-27 | 2014-04-10 | 2011-09-20 | 2014-09-30 | 99%
2014-11-30 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | KOREA, SOUTH | DESC0907 | Hydrant Fuel System - Osan AB |  | 2010-01-12 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844 | 19441 | 2010-08-27 | 2015-02-02 | 2013-11-18 | 2014-11-15 | 93%
2014-11-30 | 2011 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) - Pt. Loma |  | 2008-02-20 | 2011-03-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-11-30 | 2011 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX0802 | Replace Headquarters Facility - New Cumberland |  | 2011-11-23 | 2012-08-17 | Walsh Construction | W912DR-12-C-011 | 80775 | 82555 | 2012-08-30 | 2016-02-29 | 2015-09-18 | 2016-01-20 | 63%
2014-11-30 | 2011 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC0909 | Replace Fuel Pier - Craney Island |  | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | N40085-11-C-0001 | 28815 | 32208 | 2012-11-26 | 2015-06-20 | 2014-07-03 | 2015-03-31 | 85% | -9428 |  | Rescinded by OSD 23 Mar 12
2014-11-30 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC0503 | Hydrant Fuel System - Misawa AB |  | 2012-05-12 | 2012-09-22 | Tokyo Construction Co., Ltd. | W912HV-12-C-0013 | 25204 | 25425 | 2013-02-01 | 2015-06-20 | 2015-02-01 | 2015-03-01 | 84%
2014-11-30 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | UNITED KINGDOM | DESC0905 | Replace Hydrant Fuel System - RAF Mildenhall |  | 2011-04-19 | 2011-12-06 | Spiecapag | DEUSFMIL/13232 | 12535.429 | 12535 | 2011-12-09 | 2014-04-25 | 2013-03-14 | 2014-05-02 | 99%
2014-11-30 | 2012 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC1103 | Replace Hydrant Fuel System - Davis Montham AFB |  | 2012-05-04 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 18252 | 19125 | 2012-11-13 | 2015-02-02 | 2014-11-03 | 2014-12-03 | 99%
2014-11-30 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1205 | Replace Fuel Facilities - San Clemente Is. |  | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453 | 27610 | 2013-02-28 | 2015-03-11 | 2015-03-24 | 2015-07-01 | 69% | 10000 | FY09 Germersheim | 2853 Reprogramming
2014-11-30 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma |  | 2008-02-20 | 2012-03-29 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08C-7501 | 15512 | 164864 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-11-30 | 2012 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1102 | Public Safety Facility - Tracy |  | 2012-03-06 | 2012-07-16 | MASCON, INC | W91238-12-C-0021 | 14615 | 15091 | 2012-08-29 | 2014-12-05 | 2014-03-24 | 2014-11-08 | 94%
2014-11-30 | 2012 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESI1101 | Alter Warehouse Space - JB PH Hickam |  | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | N62478-11-D-4042/0004 | 5500 | 6430 | 2012-08-13 | 2014-09-30 | 2013-06-14 | 2014-04-29 | 99%
2014-11-30 | 2012 | DLA Defense Energy Support Center | Major Military Construction | MASSACHUSETTS | UNITED STATES | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB |  | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 24480 | 25378 | 2013-06-18 | 2016-02-08 | 2016-02-02 | 2016-02-08 | 46% | 4500 | FY09 Hill, Hunter & Germersheim | 2853 Reprogramming
2014-11-30 | 2012 | DLA Defense Supply Center Columbus | Major Military Construction | OHIO | UNITED STATES | DSCC1201 | Security Enhancements - Columbus |  | 2012-02-19 | 2012-05-04 | Pinnacle Construction Development Group | W912QR-12-C-0031 | 8550 | 10318 | 2012-06-07 | 2014-09-15 | 2013-09-23 | 2014-12-24 | 95%
2014-11-30 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1203 | Upgrade Access Control Points - New Cumberland |  | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 16327 | 16327 | 2014-02-04 | 2016-03-21 | 2016-03-21 | 2016-03-21 | 6%
2014-11-30 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1202 | Replace General Purpose Warehouse - New Cumberland |  | 2012-09-17 | 2013-11-20 | Corothers Construction Inc. | W912DR-14-C-0005 | 24622 | 24622 | 2014-01-14 | 2015-10-23 | 2015-07-29 | 2015-07-29 | 46% | 3802 | FY 10 Duluth, FY11 Osan | 2853 Reprogramming
2014-11-30 | 2012 | DLA Defense Supply Center Philadelphia | Major Military Construction | PENNSYLVANIA | UNITED STATES | DSCP1201 | Upgrade HVAC System - Philadelphia |  | 2012-03-28 | 2012-06-01 | WU & Associates, Inc. | N40085-10-D-9451 | 4775 | 7240 | 2012-06-14 | 2014-04-29 | 2013-07-17 | 2014-06-06 | 99%
2014-11-30 | 2012 | DLA Defense Energy Support Center | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DESC1101 | Replace Fuel Storage Facility - Charleston AFB |  | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | N694501-12-C-1757 | 26700 | 26485 | 2012-11-30 | 2014-12-30 | 2014-07-21 | 2014-11-26 | 90% | 5132 | FY10 Pt Loma, FY12 JB PH-Hickam & Barksdale | 2853 Reprogramming
2014-11-30 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WEST VIRGINIA | UNITED STATES | DESC12S1 | Replace Hydrant Fuel System - Camp Dawson |  | 2012-04-26 | 2012-07-05 | Kinley Construction Company | W9128F-10D-0052 | 1930 | 1945 | 2012-07-03 | 2015-04-13 | 2013-12-05 | 2014-04-30 | 99%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC13S4 | Replace Truck Unload Facility - Yuma |  | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322 | 1322 | 2013-09-30 | 2015-08-04 | 2014-08-03 | 2015-08-03 | 6% | 400 | FY12 Eielson | 2853 Reprogramming
2014-11-30 | 2013 | DLA Defense Reutilization and Marketing Service | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | DRMS12U2 | Warehouse 6 Distribution - Tracy |  | 2013-05-01 | 2013-05-15 | Kinley Construction Company | W91238-10-D0036 | 925 | 925 | 2013-06-01 | 2014-10-18 | 2013-12-05 | 2013-12-25 | 99%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1304 | Replace Fuel Storage - Edwards AFB |  | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513 | 19661 | 2013-11-20 | 2017-03-17 | 2016-10-18 | 2017-12-07 | 26%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC 1306 | Replace Fuel Pier - Pt Loma |  | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378 | 66378 | 2014-01-15 | 2017-10-14 | 2017-10-14 | 2017-10-15 | 20%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | DELAWARE | UNITED STATES | DESC1305 | Replace Truck Off-Load Facility - Dover AFB |  | 2013-07-31 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800 | 1800 | 2013-12-06 | 2015-04-28 | 2015-02-27 | 2015-04-28 | 7%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1391 | Construct Fuel Storage Facility - Hurlburt AFB |  | 2013-01-13 | 2013-08-01 | Nova Group Inc. | W91278-13-C1001 | 15952 | 15952 | 2013-10-31 | 2015-12-15 | 2015-09-14 | 2015-12-15 | 38%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC1203 | Replace Fuel Pier - GTMO |  | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366 | 36366 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 21%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC13S3 | Replace Truck Loading Facility - GTMO |  | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961 | 1961 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 20%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | GUAM | GUAM | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB |  | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 52364 | 52364 | 2014-06-30 | 2016-05-11 | 2016-02-06 | 2016-05-11 | 0%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | LOUISIANA | UNITED STATES | DESC1390 | Upgrade Pumphouse - Barksdale AFB |  | 2012-10-30 | 2013-08-13 | Environmental Management Resources | N69450-10-D-0787 | 4311 | 4311 | 2013-09-09 | 2015-02-26 | 2015-02-26 | 2015-02-26 | 66%
2014-11-30 | 2013 | DLA Defense Energy Support Center | Major Military Construction | NORTH CAROLINA | UNITED STATES | DESC13S1 | Replace Transfer Fuel Line to Pump House #2 - Seymour Johnson |  | 2013-02-27 | 2013-07-09 | Shaw Environmental & Infrastructure, Inc. | W9128F-10-D-0073 | 1494 | 1542 | 2013-07-25 | 2014-10-13 | 2014-04-18 | 2014-11-09 | 95%
2014-11-30 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1301 | Replace Communications Building - New Cumberland |  | 2014-04-16 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 6800 | 6800 | 2014-10-10 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 0%
2014-11-30 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland |  | 2013-08-01 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9600 | 9600 | 2014-07-28 | 2016-03-06 | 2016-01-21 | 2016-01-04 | 1% | 5000 | FY10 Pt Loma, GTMO & Souda Bay; FY11 Pt Loma | 2853 Reprogramming
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC14U1 | Upgrades to Fuel Pier for Fire Protection - Pt Loma |  | 2014-06-01 | 2014-07-01 | CB&I Federal Services LLC | N62583-09-D-0130 TO-027 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0%
2014-11-30 | 2014 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1404 | General Purpose Warehouse - Tracy |  | 2014-06-23 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 1994 | 1994 | 2014-06-30 | 2016-04-04 | 2015-11-15 | 2016-06-03 | 0%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City |  | 2014-03-28 | 2014-04-24 | Gilbane Federal | N62583-09-D-0129 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 2%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1402 | Replace Fuel Pipeline - Jacksonville |  | 2014-01-16 | 2014-04-17 | Industrial Power Systems | N69450-14-C-1255 | 5438 | 5438 | 2014-06-30 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 1%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC1504 | Upgrade Fuel Island - Hunter AAF |  | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0001 | 13407 | 13407 | 2014-09-19 | 2016-03-12 | 2016-03-12 | 2016-03-11 | 0%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC14S2 | Replace Ground Vehicle Fueling Facility - Moody AFB |  | 2014-03-18 | 2014-04-14 | Pond Constructors Inc. | W9128F-14-D-0051 | 3780 | 3780 | 2014-05-15 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 6% |  |  | Additional Funds from FY12 Eielson
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC11U2 | Replace Ground Vehicle Fueling Facility - Atsugi |  | 2014-05-02 | 2014-07-29 | Ichibo Co. Ltd | W912HV-14-C-0002 | 1994 | 1994 | 2014-09-12 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW JERSEY | UNITED STATES | DESC1501 | Replace Fuel Distribution Components, JB McGuire Dix Lakehurst |  | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637 | 8637 | 2014-10-30 | 2016-06-15 | 2016-06-15 | 2016-06-16 | 0%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NORTH DAKOTA | UNITED STATES | DESC1107 | Replace Fuel Pipeline - Minot AFB |  | 2014-02-28 | 2014-06-13 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4092 | 4092 | 2014-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 0%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1561 | Replace Refueler Parking, Altus AFB |  | 2014-03-10 | 2014-06-12 | Rockford Corporation | W9128F-10-D-0050 | 1917 | 1917 | 2014-07-11 | 2015-09-17 | 2015-09-17 | 2015-09-17 | 0%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB |  | 2014-06-09 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0070 | 32060 | 32060 | 2014-12-01 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 0%
2014-11-30 | 2014 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island |  | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749 | 8749 | 2014-11-30 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0%
2014-11-30 | 2007 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | DSO701 | Replace Ft Knox High School |  | 2007-04-03 | 2007-08-31 | BartonMarlow Company | W912QR-07-C-0059 / 2593359 | 16050 | 16149.241 | 2007-09-17 | 2009-10-08 | 2009-03-10 | 2009-12-04 | 99%
2014-11-30 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School |  | 2012-03-02 |  | Federal Republic of Germany | W912GB-12-C-0008 / 17387653 | 70600.7618 | 70600.7618 |  |  |  |  | 0%
2014-11-30 | 2010 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM 856 07 | New Elementary School |  | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764 | 20538.226 | 2012-08-01 | 2014-08-01 | 2013-12-14 | 2014-08-08 | 98%
2014-11-30 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) |  | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | W912GB-08-C-0046 / 14328568 | 15509.459 | 17705.0096 | 2011-05-09 | 2013-09-13 | 2013-01-19 | 2013-09-25 | 99%
2014-11-30 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46694.9233 | 48009.6099 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 59%
2014-11-30 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513.9133 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 59%
2014-11-30 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 59%
2014-11-30 | 2010 | DoD Education Activity | Major Military Construction |  | BELGIUM | EUR 8318 09 | Replace School (SHAPE ES) |  | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414.6336 | 32854 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 99%
2014-11-30 | [8 empty] | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652.1853 | 1719.1947 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
2014-11-30 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School ( Boblingen HS) |  | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869.3221 | 43600 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 61%
2014-11-30 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 61%
2014-11-30 | [8 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292.8744 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 61%
2014-11-30 | 2011 | DoD Education Activity | Major Military Construction | NEW YORK | UNITED STATES | AM2455205 | Construct Addition and Renovate West Point MS |  | 2011-07-18 | 2011-10-20 | Bernard Associates | W912DS-12-C-0001 / 25312318 | 23974 | 26098 | 2011-11-28 | 2014-03-17 | 2014-09-28 | 2014-03-17 | 99%
2014-11-30 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) |  | 2012-04-18 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260 | 26929 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 99%
2014-11-30 | [8 empty] | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843 | 6002 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
2014-11-30 | [8 empty] | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28674 | 28948 | 2012-08-01 |  | 2015-01-13 | 2014-12-19 | 87%
2014-11-30 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM8193 01 | Replace Elementary School (Antilles ES) |  | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968 | 51394 | 2012-07-18 |  | 2014-04-19 | 2015-04-30 | 56%
2014-11-30 | 2011 | DoD Education Activity | Major Military Construction | VIRGINIA | UNITED STATES | AM2455206 | Replace/Consolidate Elementary Schools |  | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297 | 43397 | 2012-09-29 |  | 2014-09-30 | 2015-06-01 | 78%
2014-11-30 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM100801 | Replace Elementary School (Murray ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121826 | 14851 | 16356 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 99%
2014-11-30 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AMD02051 | Replace Elementary School ( McNair ES) |  | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121890 | 16413 | 17049 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 99%
2014-11-30 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB |  | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | W912HV-13-C-0002 / 29312081 | 9644 | 9723 | 2013-03-26 |  | 2015-07-25 | 2015-10-18 | 87%
2014-11-30 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00053 | Replace Elementary/Middle School (Ansbach EMS) |  | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 575 | 575 | 2013-10-28 |  | 2015-03-12 | 2015-05-29 | 32%
2014-11-30 | [8 empty] | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11783.7717 | 11856 | 2013-10-28 |  | 2015-03-12 | 2015-05-29 | 32%
2014-11-30 | 2012 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00020 | Replace Elementary School (Osan ES) |  | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187 | 29847 | 2013-09-30 |  | 2015-12-09 | 2016-03-01 | 20%
2014-11-30 | 2013 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00023 | Replace McBride Elementary School |  | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987 | 32987 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 20%
2014-11-30 | [8 empty] | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2013-12-11 |  | 2015-12-11 | 2016-01-16 | 20%
2014-11-30 | 2013 | DoD Education Activity | Major Military Construction | MASSACHUSETTS | UNITED STATES | AM00027 | Replace Hanscom Middle School |  | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 31687 | 31994 | 2014-02-11 |  | 2016-04-21 | 2016-08-19 | 21%
2014-11-30 | 2013 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00028 | Replace Barkley Elementary School |  | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39362 | 39373 | 2014-03-27 |  | 2015-12-17 | 2016-03-15 | 10%
2014-11-30 | 2012 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00026 | Replace Kingsolver/Pierce School |  | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685 | 32821 | 2014-03-11 |  | 2015-11-11 | 2016-01-30 | 9%
2014-11-30 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School |  | 2014-09-30 | 2014-03-07 | Federal Republic of Germany | W912GB-12-C-0007 / 33867035 | 0 | 0 | 2014-03-24 | 2014-08-11 | 2014-08-21 | 2014-08-30 | 12%
2014-11-30 | [8 empty] | 2014-09-30 | 2014-06-20 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 662 | 662 | 2014-09-30 |  | 2014-12-02 | 2015-01-31 | 12%
2014-11-30 | [8 empty] | 2014-09-30 |  | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 48926.0169 | 48954.4549 |  |  | 2017-04-22 | 2017-05-22 | 0%
2014-11-30 | 2012 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00025 | Replace Delalio Elementary School |  | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339 | 23372 | 2014-02-24 | 2016-06-01 | 2016-06-01 | 2017-05-20 | 21% |  |  | The occupancy date 1 Jun 16 is for the BOD of the school. This is the completion of Phase 1 of the project. The school can be occupied at this time. The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2014-11-30 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School |  | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475 | 1475 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-11-30 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469 | 2469 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-11-30 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612 | 4612 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-11-30 | [8 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418 | 62418 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 2%
2014-11-30 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00062 | Netzaberg Middle School Addition |  | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 283 | 283 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 22%
2014-11-30 | [8 empty] | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366 | 5401 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 22%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00024 | Faith Middle School Addition |  | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4897 | 4897 | 2014-10-28 |  | 2016-01-21 | 2016-04-20 | 0%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00040 | Replace Marshall Elementary School |  | 2014-05-09 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 34748 | 34795 | 2014-08-06 |  | 2016-03-28 | 2016-05-27 | 8%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00038 | Diamond Elementary School Replacement |  | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40073 | 40073 | 2014-10-15 |  | 2016-09-14 | 2016-12-13 | 1%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00018 | Daegu Middle/High School Replacement |  | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28954 | 28954 | 2014-09-29 |  | 2016-10-03 | 2016-12-10 | 0%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00030 | Replace Zukeran Elementary School |  | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476 | 95476 | 2014-10-31 |  | 2016-11-30 | 2017-02-18 | 0%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00050 | White Elementary School Replacement |  | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791 | 31791 |  |  | 2016-10-18 | 2017-01-16 | 0%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00034 | Replace Fort Campbell High School |  | 2014-06-20 | 2014-10-31 | Walsh Group Ventures | W912QR-15-C-0001 | 55931 | 55931 |  |  | 2017-04-29 | 2017-04-29 | 0%
2014-11-30 | 2014 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00031 | Pope Holbrook Elementary School |  | 2014-09-09 | 2014-11-26 | SAUER Incorporated | W91278-12-D-0039 | 32124 | 32124 |  |  | 2016-11-15 | 2016-11-15 | 0%
2014-11-30 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P646 | DSS Headquarters Addition |  | 2012-09-21 | 2013-03-29 | Hensel Phelps Construction Co. |  | 25149 | 28406 | 2013-04-30 | 2014-09-26 | 2014-07-22 | 2014-09-25 | 99% |  |  | [Solicitation/Advertise Date: Phase I - 21-Sep-2012 Phase II - 20-Dec-2012]
2014-11-30 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P659 | Defense Access Road Improvements-Telegraph Rd |  | 2013-01-22 | 2013-07-15 | Shirley Contracting Company, LLC |  | 2967 | 2967 | 2013-08-01 |  | 2014-08-01 | 2014-12-19 | 72% |  |  | This project is being managed and funded via FHWA. [Solicitation/Advertise Date: Phase I - 22-Jan-2013 Phase II - 04-Apr-2013]
2014-11-30 | 2009 | Missile Defense Agency | Unspecified Minor Military Construction |  | TURKEY | 638 | European Phased Adaptive Approach, Phase I Radar Site |  | 2011-09-15 | 2011-10-19 | EMTA INSAAT TAAHUT VE TICARET A.S. | W912GB-09-D-0069 | 1885 | 1900 | 2011-10-26 | 2013-10-28 | 2011-12-31 | 2013-11-15 | 100%
2014-11-30 | 2009 | Missile Defense Agency | Unspecified Minor Military Construction | ALASKA | UNITED STATES | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping |  | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | W911KB-10-D-0004 | 1564 | 1207 | 2013-03-22 | 2013-07-03 | 2013-06-30 | 2013-07-03 | 100%
2014-11-30 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction | ALASKA | UNITED STATES | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping |  | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | W911KB-10-D-0004 | 1564 | 243 | 2013-03-22 | 2013-07-03 | 2013-06-30 | 2013-07-03 | 100%
2014-11-30 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction |  | MARSHALL ISLANDS | 655 | Missile Test Vehicle Storage Facility |  | 2014-03-24 | 2014-05-09 | Arctic Slope Regional Corporation (ASRC) | W912DY-14-D-0042-0001 | 1832 | 1832 | 2014-06-17 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 82%
2014-11-30 | 2010 | Missile Defense Agency | Major Military Construction | VIRGINIA | UNITED STATES | 609 | Aegis BMD Facility Expansion |  | 2010-03-23 | 2010-06-30 | Sauer Incorporated | N40080-10D-0490 | 18813 | 18748 | 2010-07-15 | 2012-10-12 | 2012-10-31 | 2012-10-31 | 100% | 5700 | P&D Funds | Reprogrammed to P&D for AAMDSC, Romania project. Project has multiple Asset Identifiers
2014-11-30 | 2010 | Missile Defense Agency | Major Military Construction | HAWAII | UNITED STATES | 627 | Aegis Ashore Missile Defense Test Complex |  | 2011-06-30 | 2011-08-03 | TOMCO CORP. | N62478-10-D-4024 | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 100% |  |  | Clearing and Grubbing Only
2014-11-30 | [8 empty] | 2012-01-19 | 2012-06-04 | URS GROUP, INC | N62742-09-D-1174 | 59616 | 69657 | 2012-07-04 | 2013-08-29 | 2013-09-12 | 2013-11-07 | 100% |  |  | GMAC Construction - awaiting Interim 1354
2014-11-30 | 2012 | Missile Defense Agency | Major Military Construction | ALABAMA | UNITED STATES | 633 | Von Braun Complex Phase IV |  | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | W91278-12-C-0017 | 51330 | 59842 | 2012-07-10 | 2014-06-26 | 2014-07-10 | 2014-10-15 | 100%
2014-11-30 | 2013 | Missile Defense Agency | Major Military Construction | NEW YORK | UNITED STATES | 639 | In-Flight Interceptor Data Terminal Complex |  | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584 | 15270 | 2013-08-10 |  | 2014-11-28 | 2014-12-26 | 96% |  |  | Awaiting Interim 1354
2014-11-30 | 2013 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 |  | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 81785 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 50% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2014-11-30 | 2014 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 646 | Aegis Ashore Missile Defense System Complex, Incr #2 | 630 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 28946 | 2013-07-31 |  | 2015-08-30 | 2016-02-11 | 50% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2014-11-30 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 634 | BMDS Upgrade Early Warning Radar (UEWR) |  | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300 | 13300 | 2014-07-07 |  | 2016-01-06 | 2016-01-06 | 28% |  |  | Awaiting Interim 1354
2014-11-30 | 2014 | Missile Defense Agency | Major Military Construction |  | JAPAN | 648 | AN/TPY-2 Radar Site |  | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991 | 12991 | 2014-05-27 |  | 2015-01-09 | 2015-01-09 | 82% |  |  | Site Identifier is pending as this is a new Installation; awaiting Interim 1354
2014-11-30 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) |  | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838 | 42838 | 2014-05-27 |  | 2016-05-31 | 2016-05-31 | 5% |  |  | Construction suspended for Winter; Awaiting Interim 1354
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146136 | BACHELOR ENLISTED QUARTERS |  | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | N4008511C4026 AWD | 42882 | 42014 | 2011-06-16 | 2015-03-31 | 2013-07-07 |  | 82%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146148 | MISSILE MAGAZINE |  | 2010-10-21 | 2011-06-02 | SAUER, INC. | N4008511C4010 P00003 | 4779 | 4779 | 2011-06-16 | 2014-01-23 | 2012-07-10 |  | 97%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146164 | MARINER'S BAY LAND ACQUISITION BOGUE |  |  | 2011-07-01 | NAVY STANDARD DOCUMENT | N4008509RP00103 | 4002 | 3706 | 2011-07-15 |  |  |  | 93%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146176 | STATION INFRASTRUCTURE UPGRADES |  | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | N4008510D0261 0003 | 5850 | 7300 | 2011-06-15 | 2013-10-10 | 2012-11-25 | 2013-10-10 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | N6247310D5480 0012 | 9928 | 9373 | 2011-06-17 | 2012-06-15 | 2012-06-17 |  | 98%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264541 | ADDITION, MCU RESEARCH CENTER |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 31343 | 29407 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2015-01-02 | 97% | -3531 | Sequestration Reprogramming
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 |  | 2011-06-20 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 45465 | 34560 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 30% | -8039 | Sequestration Reprogramming
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL |  | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | N6274209D1174 JU01 | 34087 | 31012 | 2011-10-14 | 2013-09-26 | 2013-08-09 | 2014-04-30 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264615 | SNCO ACADEMIC FACILITY ADDITION |  | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | N4008010D0493 0002 | 6836 | 6730 | 2011-07-04 | 2013-07-22 | 2012-12-21 |  | 96%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318006 | PHYSICAL FITNESS CENTER, CAMP SMITH |  | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | N6274209D1171 HC01 | 28891 | 28105 | 2011-06-30 | 2014-04-03 | 2013-03-07 |  | 96%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318816 | WATERFRONT OPERATIONS FACILITY |  | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 0006 | 16634 | 15083 | 2011-07-14 | 2015-01-30 | 2013-11-16 |  | 79%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318858 | BACHELOR ENLISTED QUARTERS |  | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6247811C1492 AWD | 62691 | 60611 | 2011-09-14 | 2015-03-31 | 2014-08-21 | 2014-12-11 | 92% | -17925 | N60191527, N60191582, Sequestration Reprogramming
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811014 | TRUCK COMPANY OPERATIONS COMPLEX |  | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | N6247311C0405 AWD | 52425 | 50438 | 2011-10-06 | 2015-06-03 | 2013-09-21 | 2015-06-03 | 89%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811043A | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | M006811043 | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | N6247310C5011 PC000001 | 29295 | 25314 | 2010-11-12 | 2015-02-17 | 2012-10-12 | 2015-08-21 | 52%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811044 | CONVEYANCE/WATER TREATMENT |  | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | N6247312C5033 AWD | 98236 | 83152 | 2012-10-13 | 2016-12-06 | 2016-01-13 | 2016-01-13 | 31%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811109 | BACHELOR ENLISTED QUARTERS, LAS FLORES |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 36173 | 33961 | 2011-10-13 | 2014-06-05 | 2013-10-13 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811113 | BACHELOR ENLISTED QUARTERS, 24 AREA |  | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 41889 | 39164 | 2011-10-13 | 2014-06-05 | 2013-10-13 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811200 | MARINE CORPS ENERGY INITIATIVE |  | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | N6247310D5483 0003 | 9779 | 9567 | 2011-08-09 | 2013-06-21 | 2012-08-04 | 2014-01-16 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681310 | SMALL ARMS MAGAZINE, EDSON RANGE |  | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | N6247309D1618 0004 | 3760 | 3188 | 2011-06-21 | 2014-10-27 | 2012-07-06 | 2015-01-21 | 85%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169420 | PHYSICAL FITNESS CENTER, BEAUFORT |  | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | N6945011C1760 AWD | 14780 | 14868 | 2011-09-21 | 2013-05-24 | 2013-06-08 | 2013-07-16 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169444 | TRAINING AND SIMULATOR FACILITY |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 40940 | 38701 | 2011-06-20 | 2014-06-17 | 2014-03-11 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169454 | F-35B AIRCRAFT HANGAR FOR FRS-2 |  | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 45398 | 45872 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 100%
2014-11-30 | 2011 | Marine Corps Reserve | Military Family Housing Improvement |  | JAPAN | M626130501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 |  | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | N4008411C5504 AWD | 11626 | 11102 | 2011-10-06 | 2013-02-28 | 2013-01-14 | 2013-02-28 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974447A | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 30492 | 29300 | 2011-06-23 | 2013-12-05 | 2012-10-08 |  | 98%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) |  | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 47715 | 46237 | 2011-06-23 | 2013-12-05 | 2012-10-08 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974533 | SIMULATOR FACILITY (JSF) |  | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0002 | 26438 | 23252 | 2011-06-17 | 2013-03-05 | 2012-06-02 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974546 | UTILITY UPGRADES (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 40106 | 36761 | 2011-06-21 | 2013-06-14 | 2012-07-08 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) |  | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0002 | 19793 | 16188 | 2011-08-10 | 2012-12-14 | 2012-07-25 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974578 | VAN PAD RELOCATION (JSF) |  | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | N6247309D1653 0003 | 15045 | 14670 | 2011-09-26 | 2013-01-22 | 2012-09-11 | 2012-09-11 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) |  | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 54843 | 54497 | 2011-06-21 | 2013-06-14 | 2012-07-08 |  | 93%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC |  | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | N4008510D5329 0002 | 12906 | 12849 | 2011-06-16 | 2015-02-06 | 2012-12-01 |  | 94%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011034 | 2ND INTEL BN OPERATIONS COMPLEX |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 79767 | 80482 | 2011-07-13 | 2015-04-30 | 2014-02-28 | 2014-12-15 | 94%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO |  | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 32625 | 30659 | 2011-07-13 | 2015-04-30 | 2014-02-28 | 2014-12-15 | 93%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP |  | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | N4008510D0259 0007 | 6613 | 6017 | 2011-07-11 | 2013-05-13 | 2012-08-20 |  | 92%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 43950 | 40294 | 2011-07-13 | 2015-04-11 | 2013-07-13 | 2013-07-13 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 40236 | 38214 | 2011-09-14 | 2015-02-15 | 2013-10-08 | 2014-06-24 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY |  | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 39788 | 37917 | 2011-09-14 | 2015-02-15 | 2013-10-08 |  | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011256 | MESS HALL ADDITION, COURTHOUSE BAY |  | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0006 | 1499 | 1379 | 2011-06-16 | 2012-11-25 | 2012-11-25 |  | 98%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011264 | UTILITY EXPANSION, HADNOT POINT |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 55206 | 55212 | 2011-10-10 | 2014-09-16 | 2013-10-22 |  | 92%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011265 | UTILITY EXPANSION, FRENCH CREEK |  | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 54795 | 46483 | 2011-10-10 | 2014-09-16 | 2013-10-22 |  | 97%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011267 | MESS HALL, FRENCH CREEK |  | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | N4008511C4022 AWD | 24316 | 17444 | 2011-06-16 | 2014-03-07 | 2013-02-06 |  | 65%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE |  | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | N4008511C4008 AWD | 54720 | 55088 | 2011-09-13 | 2015-03-31 | 2013-09-07 |  | 95%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4021 AWD | 43568 | 40944 | 2011-06-16 | 2015-01-04 | 2013-08-30 | 2015-01-04 | 99%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON |  | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4020 AWD | 46005 | 42198 | 2011-06-16 | 2014-08-29 | 2013-08-13 | 2014-04-14 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH |  | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 49005 | 44550 | 2011-07-13 | 2015-03-02 | 2013-07-13 | 2015-04-11 | 97%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011323 | ARMORY II MEF, WALLACE CREEK |  | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | N4008511C4001 P00004 | 5941 | 5402 | 2011-12-20 | 2015-04-11 | 2013-07-13 | 2015-04-11 | 99% | -4148 | M00681159
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011400 | MARINE CORPS ENERGY INITIATIVE |  | 2010-10-08 | 2011-05-31 | URS-IAP LLC | N6247006D6009 0016-02 | 8868 | 8147 | 2011-06-14 | 2012-12-06 | 2012-09-27 |  | 98%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001683 | HANGAR |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62154 | 59440 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 93%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001687 | MV-22 MAINTENANCE HANGAR (HMLA) |  | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62617 | 59662 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 92%
2014-11-30 | 2011 | Marine Corps Active | Military Family Housing Improvement | DISTRICT OF COLUMBIA | UNITED STATES | M670291101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 |  | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0001-07 | 41 | 39 | 2011-01-28 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 100%
2014-11-30 | 2011 | Marine Corps Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | M67399092 | TANK VEHICLE MAINTENANCE FACILITY |  | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | N6247309D1615 0041 | 6458 | 6168 | 2011-10-06 | 2013-03-11 | 2012-09-21 | 2013-03-28 | 99.9%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE |  | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | N6247310C5007 PC000001 | 51987 | 51426 | 2011-06-17 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604109 | CNAT/FRS AVIATION TRAINING AND BEQ |  | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0434 AWD | 51999 | 45733 | 2011-09-26 | 2014-06-23 | 2014-01-08 |  | 98% | -11300 | N61151162, Sequestration Reprogramming
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604111 | MALS-39 MAINTENANCE HANGAR EXPANSION |  | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | N6247310D5409 0003 | 47061 | 33366 | 2011-07-06 | 2013-10-29 | 2013-03-13 |  | 86%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695005 | PAINT AND BLAST FACILITY |  | 2011-04-29 | 2011-09-16 | SAUER, INC. | N6945009D1277 0005 | 20345 | 19808 | 2011-09-30 | 2014-03-10 | 2013-05-16 |  | 97%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695012 | CONTAINER STAGING AND LOADING LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3380 | 2529 | 2011-06-17 | 2013-12-05 | 2013-12-05 |  | 73%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695017 | HARDSTAND EXTENSION |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 12623 | 7904 | 2011-06-17 | 2013-12-05 | 2013-12-05 |  | 94%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695022 | CONSOLIDATED WAREHOUSE FACILITY |  | 2010-11-22 | 2011-06-03 | SAUER, INC. | N6945009D1277 0003 | 13295 | 11139 | 2011-06-17 | 2013-12-20 | 2012-07-27 | 2013-12-20 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695023 | WASHRACK EXPANSION |  | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | N6945011D1259 0002 | 8877 | 8449 | 2011-06-15 | 2013-06-10 | 2012-11-19 |  | 96%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695024 | CONTAINER STORAGE LOT |  | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3702 | 3369 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 100%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865152 | PARKING APRON/TAXIWAY EXPANSION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 32816 | 35427 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | -28591 | N50092499, N60191527, Design, N47608561
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865185 | HANGAR 4 ADDITION |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 27121 | 27749 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | -4000 | M00681159, Design
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865192 | GTF-HANGAR MODIFICATION (HMT-302) |  | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 56417 | 54528 | 2011-10-04 | 2014-09-19 | 2014-09-19 |  | 99% | -30605 | N50092499, Design
2014-11-30 | 2011 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | M68479060 | MARINE CORPS RESERVE CENTER |  | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0005 | 14630 | 14194 | 2011-10-11 | 2014-04-15 | 2013-02-08 | 2014-03-01 | 100%
2014-11-30 | 2011 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | N00206477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY |  | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | N6945011C0756 AWD | 13604 | 14491 | 2011-06-17 | 2014-05-07 | 2013-06-07 | 2014-02-12 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245327 | BERTHING PIER 12 REPL & DREDGING |  | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | N6247311C2850 AWD | 99132 | 90215 | 2011-10-13 | 2013-10-22 | 2013-10-22 |  | 88% | -1813 | N61151162
2014-11-30 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245405 | BACHELOR QUARTERS HOMEPORT ASHORE |  | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247311C2804 AWD | 72294 | 69777 | 2011-10-14 | 2013-12-03 | 2013-10-23 |  | 99% | -3179 | N42237100
2014-11-30 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246750 | ROTARY HANGAR |  | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | N6247312C1406 P00001 | 64063 | 63857 | 2012-02-14 | 2013-12-10 | 2012-04-16 | 2014-03-11 | 100% | -1557 | N42237100
2014-11-30 | 2011 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411068 | ELECTROMAGNETIC SENSOR FACILITY |  | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | N4008511C7231 AWD | 24394 | 26541 | 2011-08-23 | 2014-03-24 | 2013-08-22 |  | 97%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | N32414203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES |  | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | N4008512C5002 AWD | 1951 | 1838 | 2012-03-16 | 2012-08-28 | 2012-09-13 | 2012-09-13 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443516A | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | N32443516 | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | N4008510C3006 P00003 | 68459 | 66000 | 2011-04-14 | 2015-10-02 | 2014-11-22 | 2015-10-02 | 72%
2014-11-30 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A219 | GENERAL WAREHOUSE |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 7716 | 7755 | 2012-04-16 | 2014-10-31 | 2013-12-26 |  | 82%
2014-11-30 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A912 | PAVE EXTERNAL ROADS |  | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 3107 | 2761 | 2012-04-16 | 2014-10-31 | 2013-12-26 |  | 82%
2014-11-30 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237601 | SECURITY ENCLAVE AND VEHICLE BARRIER |  | 2011-12-13 | 2012-03-16 | SAUER, INC. | N6945009D1277 0007 | 37278 | 39684 | 2012-03-30 | 2013-09-07 | 2013-09-07 |  | 92% | -5445 | Sequestration Reprogramming
2014-11-30 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237620 | WATERFRONT EMERGENCY GENERATORS |  | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | N6945010D1271 0003 | 15010 | 16822 | 2011-09-02 | 2013-05-13 | 2013-05-13 | 2015-02-20 | 97%
2014-11-30 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC |  | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | N4008011C0154 AWD | 33033 | 34715 | 2011-06-16 | 2013-07-31 | 2012-07-30 |  | 99%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY |  | 2011-05-26 | 2011-08-03 | JESSICO, INC | N4008511C3026 AWD | 2085 | 1989 | 2011-08-17 | 2012-11-13 | 2012-09-30 |  | 98%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG |  | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008512C7000 AWD | 1725 | 1616 | 2011-11-18 | 2013-05-08 | 2012-07-21 | 2013-05-31 | 100%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N57095101 | ROAD IMPROVEMENTS CAMP ALLEN AREA |  | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | N4008509D5027 0003-PC000002 | 1381 | 1326 | 2011-02-28 | 2012-01-27 | 2011-09-21 | 2012-01-27 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N60042260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  |  | 2011-09-29 | NAVY STANDARD DOCUMENT | N6247311RP00189 | 1421 | 1658 | 2011-10-13 |  |  |  | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | ALABAMA | UNITED STATES | N60508266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD |  | 2012-07-05 | 2012-09-28 | HEAD, INC. | N6945012C0760 AWD | 29901 | 26546 | 2012-10-12 | 2014-09-28 | 2014-09-28 | 2014-12-24 | 81%
2014-11-30 | 2011 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N61007015 | CALIBRATION FACILITY LAND ACQUISITION |  |  | 2011-12-31 | NAVY STANDARD DOCUMENT | N6945011RP00148 | 3149 | 3080 | 2012-01-14 |  |  |  | 100%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054012 | CONSTRUCT NACCC ADDITION |  | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | N4008410D0014 0003 | 1380 | 1256 | 2011-06-24 | 2012-04-20 | 2012-04-13 |  | 96%
2014-11-30 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER |  | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | N4008411C0129 AWD | 17378 | 16915 | 2011-07-15 | 2013-01-17 | 2012-12-03 | 2013-01-20 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction |  | JAPAN | N61057203 | AVIATION SIMULATOR TRAINING FACILITY |  | 2010-12-09 | 2011-07-29 | NAVY STANDARD DOCUMENT | N6274211MP00014 | 6764 | 6442 | 2011-08-12 | 2013-11-13 | 2013-11-13 |  | 95%
2014-11-30 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151162 | AGILE CHEMICAL FACILITY PHASE 2 |  | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | N4008012C2001 AWD | 34869 | 36120 | 2012-08-24 | 2015-06-26 | 2014-06-16 | 2015-06-26 | 67%
2014-11-30 | 2011 | Marine Corps Active | Major Military Construction |  | GUAM | N61755204A | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | N61755204 | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | N4019210D2803 0006 | 21579 | 16525 | 2012-12-12 | 2014-09-29 | 2014-06-19 |  | 77%
2014-11-30 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE |  | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008511D6585 0001 | 1395 | 1273 | 2011-06-28 | 2012-11-07 | 2012-06-18 | 2012-11-07 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688862 | PIER 1 UPGRADES TO BERTH USNS COMFORT |  | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | N4008511C0020 AWD | 3659 | 2953 | 2011-08-09 | 2012-09-18 | 2012-08-09 |  | 79% | -6185 | M00681159, N42237100
2014-11-30 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N627351102 | WHOLEHOUSE IMPROVEMENT |  | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | N4008411C0006 AWD | 8127 | 6990 | 2011-07-10 | 2013-01-18 | 2012-10-17 | 2013-02-14 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813005 | JOINT POW/MIA ACCOUNTING, USPACOM |  | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274211C1300 AWD | 95540 | 83528 | 2011-06-20 | 2014-11-24 | 2013-07-05 |  | 87%
2014-11-30 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE |  | 2011-02-04 | 2011-06-24 | FOPCO, INC | N6247810D4019 0006 | 7856 | 9024 | 2011-07-08 | 2013-06-03 | 2012-08-15 |  | 99%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) |  | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | N6247810D4020 0014 | 1559 | 1446 | 2011-10-03 | 2013-03-01 | 2012-12-24 | 2013-03-01 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction |  | SPAIN | N62863897 | AIR TRAFFIC CONTROL TOWER |  | 2012-01-13 | 2012-06-15 | SACYR SA | N3319112C0603 AWD | 19080 | 15666 | 2012-06-29 | 2015-04-15 | 2014-09-03 | 2015-01-04 | 67% | -2052 | N42237100
2014-11-30 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY |  | 2012-04-12 | 2012-08-17 | NAVY STANDARD DOCUMENT | N6247012MPE0064 | 41151 | 38523 | 2012-08-31 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 47% | -15471 | Sequestration Reprogramming
2014-11-30 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005954 | WATERFRONT DEVELOPMENT, PHASE 3 |  | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT | N6247012MPE0005 | 40713 | 40237 | 2012-03-14 | 2014-11-26 | 2014-11-26 |  | 84% | -19865 | Sequestration Reprogramming
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042331 | WATER WELL |  | 2011-01-11 | 2011-09-30 | EPC CORPORATION | N6247310D5415 0012 | 2713 | 2887 | 2011-10-14 | 2013-11-22 | 2012-10-01 | 2013-05-21 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436843 | CSDS-5 LABORATORY EXPANSION PHASE ! |  | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | N4425510D5006 0005 | 16042 | 16448 | 2011-06-17 | 2013-09-24 | 2012-10-15 |  | 88%
2014-11-30 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 14315 | 14812 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-05-15 | 100%
2014-11-30 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436973F | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | N63402973 | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | N4425508C6003 PC000094 | 20026 | 19450 | 2010-11-24 | 2012-06-01 | 2011-11-08 |  | 92%
2014-11-30 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436987 | EMERGENCY GENERATOR, LIMITED AREA |  | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 11275 | 10432 | 2011-06-17 | 2013-07-10 | 2013-06-26 |  | 97%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING |  | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | N4008506D6009 0008 | 928 | 950 | 2011-07-04 | 2012-04-16 | 2012-01-26 | 2012-04-30 | 100%
2014-11-30 | 2011 | Navy Reserve | Major Military Construction | VIRGINIA | UNITED STATES | N69212743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX |  | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008509D5019 0003 | 15431 | 17554 | 2011-06-17 | 2013-10-18 | 2013-04-27 | 2014-10-18 | 100%
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | N69213206 | CONSTRUCT DISPATCH CENTER |  | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | N4008510D9451 0005 | 1630 | 1633 | 2011-12-01 | 2013-03-26 | 2013-01-25 | 2013-03-29 | 100%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY |  | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0003 | 14067 | 17408 | 2012-03-29 | 2014-04-29 | 2013-08-14 |  | 94%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR |  | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0020 | 11118 | 11221 | 2012-09-25 | 2014-10-10 | 2014-03-28 |  | 99%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 |  | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222 | 23827 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 37%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION |  | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | N4008010D0497 0011 | 6555 | 7003 | 2012-08-10 | 2014-09-26 | 2013-09-05 | 2014-12-30 | 76%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264611 | BACHELOR ENLISTED QUARTERS |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 32910 | 31667 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-03-18 | 71%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264612 | ENLISTED DINING FACILITY |  | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 5028 | 5137 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-03-18 | 91%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264621 | EMBASSY SECURITY GROUP FACILITIES |  | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081 | 25378 | 2013-03-14 | 2015-08-15 | 2015-03-15 | 2015-03-25 | 45%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264632 | ACADEMIC INSTRUCTION FACILITY |  | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 60736 | 60203 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2015-01-02 | 95% | -2502 | N47608561
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318822 | MCAS OPERATIONS COMPLEX |  | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 HC01 | 52970 | 51415 | 2012-05-02 | 2014-12-29 | 2014-03-17 | 2014-12-29 | 83%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE |  | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0002-PC000002 | 11746 | 9512 | 2012-04-06 | 2013-08-05 | 2013-01-21 |  | 88% | -760 | N00246909
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811040 | INTERSECTION BRIDGE AND IMPROVEMENTS |  | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | N6247309D1606 0009 | 11432 | 13971 | 2012-09-07 | 2014-05-23 | 2013-09-27 |  | 97%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811045 | NEW POTABLE WATER CONVEYANCE |  | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242 | 62016 | 2012-10-12 | 2016-12-21 | 2016-03-31 | 2016-03-31 | 33% | -16682 | N684691400
2014-11-30 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811046 | NORTH AREA WASTE WATER CONVEYANCE |  | 2014-08-28 | 2014-11-25 | ORION CONSTRUCTION CORPORATION | N6247310D5419 0012 | 75135 | 42482 | 2014-12-09 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 0%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681532 | ARMORY, 1ST MARINE DIVISION |  | 2012-04-23 | 2012-08-31 | A&D GC INC | N6247309D1658 0006 | 11201 | 10463 | 2012-09-14 | 2014-04-23 | 2013-12-24 |  | 99%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169442 | VERTICAL LANDING PADS FOR F-35B |  | 2011-12-06 | 2012-03-30 | HEAD, INC. | N6945012C1758 AWD | 18987 | 18046 | 2012-04-13 | 2013-10-21 | 2013-08-07 |  | 95%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204925 | DIP TANK CLEANING FACILITY |  | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | N6247309D1616 0009 | 7970 | 7879 | 2012-04-04 | 2014-09-18 | 2013-09-27 |  | 92%
2014-11-30 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 |  | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | N4008412D6501 0002 | 13357 | 12685 | 2012-08-13 | 2013-12-13 | 2013-11-23 | 2013-12-14 | 100%
2014-11-30 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626131001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 |  | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | N4008412D6501 0004 | 11335 | 10876 | 2012-08-14 | 2015-02-02 | 2014-12-20 | 2015-02-02 | 74.79%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974535 | AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | N6247308D8617 0004 | 32048 | 31780 | 2012-09-20 | 2014-08-06 | 2014-07-07 | 2015-01-01 | 99% | -5983 | N684691400
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) |  | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0003 | 79917 | 78061 | 2012-04-03 | 2014-06-24 | 2014-05-20 |  | 98%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974575 | AUXILIARY LANDING FIELD (JSF) |  | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | N6247312C1802 AWD | 29475 | 28521 | 2012-07-09 | 2014-02-21 | 2013-06-25 |  | 94% | -5128 | N42237636
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001030 | SQUAD BATTLE COURSE |  | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0003 | 16292 | 14381 | 2012-07-05 | 2014-12-01 | 2014-05-17 |  | 83%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER |  | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | N4008512C7719 AWD | 74707 | 72332 | 2012-05-14 | 2015-03-12 | 2014-07-24 | 2015-02-19 | 90%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK |  | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101 | 26020 | 2012-07-13 | 2014-12-15 | 2014-07-29 |  | 96%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011383 | BASE ENTRY POINT AND ROAD |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235 | 62533 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 69%
2014-11-30 | 2012 | Marine Corps Active | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | M670011425 | OVERHEAD RANGE BAFFLE SYSTEM |  | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008511D8026 0008 | 2297 | 2215 | 2013-03-06 | 2014-12-30 | 2014-04-17 |  | 96%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001705 | AIRCRAFT MAINTENANCE HANGAR AND APRON |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 57582 | 64265 | 2012-06-12 | 2015-02-19 | 2014-07-07 | 2015-02-19 | 98%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001710 | ORDNANCE LOADING AREA ADDITION |  | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 7768 | 7376 | 2012-06-12 | 2015-02-19 | 2014-07-07 | 2015-02-19 | 90%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA |  | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819 | 20055 | 2012-08-27 | 2016-02-15 | 2014-09-02 | 2016-05-03 | 19%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399212 | CHILD DEVELOPMENT CENTER |  | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | N6247310D5412 0006 | 21313 | 20429 | 2012-06-19 | 2015-05-19 | 2013-12-12 | 2015-05-19 | 38%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399541 | MULTI-PURPOSE BUILDING ADDITION |  | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | N6247309D1655 0003 | 15610 | 13793 | 2012-10-11 | 2014-04-20 | 2014-04-20 |  | 47%
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604114 | MV-22 DOUBLE HANGAR REPLACEMENT |  | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0004 | 40539 | 38834 | 2012-08-03 | 2015-12-14 | 2015-08-10 | 2015-08-10 | 44% | -6761 | N684691400
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604116 | MV-22 AVIATION PAVEMENT |  | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | N6247309D1605 0012 | 14938 | 9645 | 2012-07-26 | 2015-03-30 | 2014-01-03 |  | 72% | -856 | N684691400
2014-11-30 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604117 | MV-22 AVIATION FUEL STORAGE |  | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | N6247007D7000 FZN7 | 7437 | 7216 | 2013-11-21 |  | 2013-10-07 | 2015-10-07 | 29%
2014-11-30 | 2012 | Marine Corps Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  |  | 2012-01-04 |  |  | 0 | 45 | 2012-01-18 |  | 2012-01-31 | 2012-01-31 | 100% |  |  | Awarded by Other Agency
2014-11-30 | 2012 | Marine Corps Reserve | Major Military Construction | TENNESSEE | UNITED STATES | M68479030 | RESERVE CENTER TRAINING CENTER - MEMPHIS |  | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | N4008313C0019 AWD | 9006 | 8500 | 2013-04-19 | 2015-01-26 | 2014-10-11 | 2015-01-15 | 68.75%
2014-11-30 | 2012 | Navy Active | Major Military Construction | ILLINOIS | UNITED STATES | N00128816 | DECENTRALIZE STEAM SYSTEM |  | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491 | 62556 | 2012-06-27 | 2015-11-06 | 2015-11-06 | 2015-11-06 | 60%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N00204791 | HVAC JOINT AVIATION SURVIVAL TRAINING |  | 2012-07-25 | 2012-09-29 | R L BURNS INC. | N6945012C6343 AWD | 2038 | 1975 | 2012-10-13 | 2013-12-19 | 2013-08-08 | 2013-08-08 | 100%
2014-11-30 | 2012 | Marine Corps Reserve | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | N00206501 | MILITARY WORKING DOG FACILITY |  | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | N6945013C5571 AWD | 1286 | 1237 | 2013-08-29 | 2014-06-20 | 2014-05-22 | 2014-06-20 | 100%
2014-11-30 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207153 | BAMS UAS OPERATOR TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 2851 | 2936 | 2012-07-09 | 2014-03-24 | 2013-12-17 |  | 96% | -1321 | N42237100
2014-11-30 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207624 | P-8A TRAINING FACILITY |  | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 14194 | 13885 | 2012-07-09 | 2014-03-24 | 2013-12-17 |  | 96% | -11437 | N42237636, N42237100
2014-11-30 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246705 | FITNESS CENTER, NORTH ISLAND |  | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | N6247310D5409 0013 | 46630 | 42554 | 2012-08-21 | 2015-07-27 | 2015-03-16 | 2015-07-27 | 72%
2014-11-30 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND |  | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977 | 55669 | 2012-07-17 | 2015-07-09 | 2015-03-30 | 2015-07-09 | 77%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY |  | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | N6247311D0067 0004 | 1816 | 1714 | 2013-02-21 | 2014-10-17 | 2014-01-31 |  | 98%
2014-11-30 | 2012 | Navy Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414860 | ARMED FORCES RESERVE CENTER, PITTSBURGH |  | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | N4008312C0005 AWD | 12033 | 12339 | 2012-08-14 | 2014-05-31 | 2014-02-06 | 2014-05-31 | 100%
2014-11-30 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443383 | CONTROLLED INDUSTRIAL FACILITY |  | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576 | 32343 | 2012-06-14 | 2015-07-31 | 2014-09-28 | 2015-03-23 | 34% | -7621 | N684691400
2014-11-30 | 2012 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE |  | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167 | 36608 | 2014-05-01 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 4%
2014-11-30 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 |  | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49890 | 47015 | 2014-07-14 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 6%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092199 | MSRON FOUR BOAT STORAGE BUILDING |  | 2012-10-31 | 2012-12-14 | JESSICO, INC | N4008511D3021 0008 | 970 | 938 | 2012-12-28 | 2013-11-15 | 2013-11-08 | 2013-11-15 | 100%
2014-11-30 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N50092499 | POWER DISTRIBUTION UPGRADES |  | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | N4008512C1704 AWD | 29520 | 28098 | 2012-10-08 | 2014-11-21 | 2014-10-09 |  | 93%
2014-11-30 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N57095197 | DECENTRALIZE STEAM SYSTEM |  | 2012-04-17 | 2012-09-20 | SAUER, INC. | N4008509D5026 0004 | 27161 | 26583 | 2012-10-04 | 2015-03-09 | 2015-05-08 | 2015-05-08 | 79%
2014-11-30 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS |  | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599 | 17914 | 2012-10-11 | 2015-04-01 | 2014-10-12 | 2015-01-01 | 63%
2014-11-30 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS |  | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | N6945012C0757 AWD | 7518 | 9913 | 2012-08-29 | 2014-02-21 | 2014-02-21 |  | 25%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241294 | CONNECT TO KINGSVILLE WATER SYSTEM |  | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | N6945010D0776 0002 | 1658 | 1549 | 2012-10-08 | 2014-03-21 | 2014-03-21 |  | 96%
2014-11-30 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE |  | 2012-02-17 | 2012-06-07 | NAVY STANDARD DOCUMENT | N6247012MPS0048 | 18810 | 20581 | 2012-06-21 | 2015-04-14 | 2014-12-30 | 2015-04-14 | 73%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61014851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION |  | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | N6247314C2801 AWD | 1916 | 1871 | 2014-01-02 | 2014-12-31 | 2014-10-17 | 2014-12-31 | 47%
2014-11-30 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) |  | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | N4008412C0108 AWD | 19730 | 18773 | 2012-08-01 | 2014-01-13 | 2014-01-13 | 2014-01-13 | 100%
2014-11-30 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 |  | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | N4008412C0109 AWD | 9033 | 9094 | 2012-08-22 | 2015-01-11 | 2014-10-07 | 2015-01-11 | 77.1%
2014-11-30 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR |  | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | N4008412C8325 AWD | 5990 | 5654 | 2012-10-10 | 2013-11-22 | 2013-08-26 | 2013-11-22 | 100%
2014-11-30 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) |  | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | N4008412C0004 AWD | 17540 | 14942 | 2012-08-29 | 2014-07-01 | 2013-12-09 | 2014-07-01 | 100%
2014-11-30 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N61064400 | NORTH LOOP ELECTRICAL REPLACEMENT |  | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | N6247811D4046 0005 | 6498 | 5905 | 2012-03-29 | 2013-12-24 | 2014-01-02 | 2014-12-31 | 88% | -2776 | N42237100
2014-11-30 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151222 | DECENTRALIZE STEAM SYSTEM |  | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984 | 68674 | 2012-10-12 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 81%
2014-11-30 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688123 | BACHELOR QUARTERS, HOMEPORT ASHORE |  | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | N4008512C4572 AWD | 74854 | 72209 | 2012-09-14 | 2015-05-31 | 2014-09-13 | 2015-03-26 | 84% | -3084 | N684691400
2014-11-30 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY |  | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | N6247810D4022 0019 | 7708 | 7642 | 2012-04-19 | 2014-11-09 | 2013-11-16 |  | 98%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863708 | CONSTRUCT LCAC BEACH ACCESS RAMP |  | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | N3319110D0219 0009 | 1751 | 1411 | 2013-10-13 | 2014-06-20 | 2014-05-28 |  | 97%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 |  | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | N6247312C3410 AWD | 1980 | 1878 | 2012-09-12 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 100%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT |  | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | N6247312C3413 AWD | 2000 | 1896 | 2012-10-12 | 2014-03-05 | 2013-09-26 |  | 96%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63406563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 |  | 2012-06-20 | 2012-09-28 | NOVA R M F | N6247312D0245 0003 | 1939 | 1875 | 2012-10-12 | 2014-06-23 | 2013-09-27 | 2014-07-01 | 100%
2014-11-30 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 |  | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | N4425510D5019 0002 | 13341 | 10555 | 2012-06-08 | 2013-06-27 | 2013-12-24 |  | 88%
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436839 | RENOVATE LOWER BASE FIRE STATION |  | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | N4425509D4007 0017 | 1389 | 1327 | 2012-09-14 | 2013-11-13 | 2013-08-31 |  | 99%
2014-11-30 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436913 | EHW SECURITY FORCE FACILITY |  | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | N4425512C3007 AWD | 13485 | 13667 | 2012-02-14 | 2014-06-11 | 2013-08-08 |  | 75% | -7933 | N684691400
2014-11-30 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436985 | WRA VEHICLE BARRIERS |  | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | N4425510D5008 0012 | 9338 | 8948 | 2012-02-24 | 2013-12-11 | 2013-12-10 |  | 85% | -7587 | N42237636
2014-11-30 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 |  | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714 | 78002 | 2012-05-23 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 92%
2014-11-30 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N68469110 | REPLACE CONDEMNED COATINGS LABORATORY |  | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0019 | 3805 | 3998 | 2012-09-11 | 2014-04-24 | 2013-08-28 |  | 99%
2014-11-30 | 2012 | Navy Active | Major Military Construction |  | DIEGO GARCIA | N68539184 | POTABLE WATER PLANT MODERNIZATION |  | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101 | 28232 | 2013-01-04 | 2015-08-26 | 2015-07-30 | 2015-08-26 | 74%
2014-11-30 | 2012 | Navy Reserve | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212543 | NAVELSG RESERVE FORCES MARSHALLING YARDS |  | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | N4008511D6588 0006 | 738 | 747 | 2013-01-30 | 2013-10-23 | 2014-01-21 |  | 95%
2014-11-30 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232559 | E-2D AIRCREW TRAINING FACILITY |  | 2012-03-21 | 2012-06-29 | ALLEN ENGINEERING CONTRACTOR, INC | N6247309D1658 0012 | 13210 | 15680 | 2012-07-13 | 2014-06-25 | 2013-10-07 |  | 94%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND |  | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091 | 27567 | 2013-09-19 | 2016-02-24 | 2016-01-18 | 2016-02-24 | 28%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146601 | ARMORY |  | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0006 | 11782 | 11291 | 2013-09-19 | 2015-04-20 | 2015-04-08 | 2015-04-20 | 60%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243313 | ENTRY CONTROL POINT (GATE 5) |  | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974 | 10298 | 2014-01-03 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 11%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M00263382 | FRONT GATE AT/FP IMPROVMENTS |  | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513 | 10893 | 2013-10-30 | 2015-10-11 | 2015-04-12 | 2015-10-11 | 21%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 |  | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462 | 28694 | 2013-10-07 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 13%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264644 | WEAPONS TRAINING BATALLION MESS HALL |  | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168 | 12604 | 2013-09-18 | 2015-06-30 | 2015-04-22 | 2015-04-22 | 26%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318904 | MV-22 HANGAR AND INFRASTRUCTURE |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 63056 | 55982 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 24%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318905 | AIRCRAFT STAGING AREA |  | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 11118 | 7008 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 30%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811176 | SAN JACINTO ROAD EXTENSION |  | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428 | 4269 | 2014-10-08 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 1%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169427 | GROUND SUPPORT EQUIPMENT SHOP |  | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | N6945013D1761 0001 | 10936 | 10661 | 2013-08-22 | 2015-01-16 | 2014-08-07 | 2014-12-12 | 57%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169456 | SIMULATED LHD FLIGHT DECK |  | 2012-08-27 | 2013-06-26 | HEAD, INC. | N6945013C1773 AWD | 12302 | 11951 | 2013-07-10 | 2014-11-28 | 2014-07-11 |  | 93%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169465 | AIRCRAFT MAINTENANCE HANGAR |  | 2014-08-06 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643 | 36401 | 2014-08-29 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 1%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169472 | AIRFIELD SECURITY UPGRADES |  | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | N6945013C1772 AWD | 11043 | 12576 | 2013-07-15 | 2014-10-28 | 2014-03-28 |  | 89%
2014-11-30 | 2013 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 |  | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | N4008414C5500 AWD | 17551 | 16715 | 2014-06-22 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 0%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613995 | MAINTENANCE HANGAR IMPROVEMENTS |  | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT | N6274214MP00027 | 4947 | 4926 | 2014-06-06 | 2015-06-14 | 2015-06-14 | 2015-06-14 | 0%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH |  | 2014-04-07 | 2014-07-25 | NAVY STANDARD DOCUMENT | N6274214MP00039 | 6304 | 6304 | 2014-08-08 | 2015-09-24 | 2015-09-24 | 2015-09-24 | 0%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974378 | SECURITY OPERATIONS COMPLEX |  | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316 | 13478 | 2013-11-14 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 6%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974566 | COMBAT AIRCRAFT LOADING APRON |  | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247309D1603 0013 | 12671 | 11791 | 2013-10-11 | 2015-03-02 | 2014-09-22 | 2015-03-02 | 31%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001003 | STAFF NCO ACADEMY FACILITIES |  | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260 | 27824 | 2013-09-19 | 2015-11-08 | 2015-09-01 | 2015-11-08 | 34%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011384 | BASE ACCESS AND ROAD, PHASE 3 |  | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666 | 28713 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 52%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001711 | PERSONNEL ADMINISTRATION CENTER |  | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0018 | 6449 | 5394 | 2013-09-20 | 2015-07-06 | 2015-07-06 | 2015-07-06 | 54%
2014-11-30 | 2013 | Marine Corps Active | Unspecified Minor Military Construction |  | JAPAN | M67400305 | DEMOLISH 45 HOUSING UNITS, KISHABA HOUSING |  | 2013-07-10 | 2014-09-25 | NAVY STANDARD DOCUMENT | N6274214MP00043 | 1729 | 1719 | 2014-10-09 | 2015-06-29 | 2015-06-29 | 2015-06-29 | 0%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604113 | MV-22 AVIATION SIMULATOR BUILDING |  | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | N6247309D1619 0008 | 4380 | 4083 | 2013-06-27 | 2014-09-18 | 2014-09-21 |  | 98%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865181 | HANGAR 5 RENOVATIONS & ADDITION |  | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0002 | 13634 | 12826 | 2013-09-27 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 8%
2014-11-30 | 2013 | Marine Corps Reserve | Major Military Construction | NEW YORK | UNITED STATES | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY |  | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911 | 4764 | 2013-09-19 | 2015-11-04 | 2014-12-04 | 2014-12-04 | 14.38%
2014-11-30 | 2013 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207655 | BAMS MISSION CONTROL COMPLEX |  | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | N6945013C1257 AWD | 18180 | 17997 | 2013-08-28 | 2014-12-27 | 2014-12-27 | 2015-02-15 | 36%
2014-11-30 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245500 | LCS TRAINING FACILITY |  | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553 | 40296 | 2013-10-14 | 2015-10-24 | 2015-10-24 | 2016-01-09 | 26% | -10760 | N42237100
2014-11-30 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246909 | H-60S SIMULATOR TRAINING FACILITY |  | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088 | 2830 | 2014-03-14 | 2015-03-15 | 2015-03-15 | 2015-03-15 | 9%
2014-11-30 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620245 | EA-18G FLIGHT SIMULATOR FACILITY |  | 2012-08-16 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0009 | 5679 | 5916 | 2013-06-27 | 2014-12-25 | 2014-11-25 | 2015-01-27 | 87%
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction | OREGON | UNITED STATES | N00620246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY |  | 2013-07-26 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | N4425513C7005 AWD | 1120 | 1072 | 2013-10-14 | 2014-09-30 | 2014-09-30 | 2014-12-19 | 75%
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | N32411056 | VPT TEST FACILITY |  | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | N4008510D9450 0006 | 2332 | 2328 | 2013-03-28 | 2013-11-21 | 2013-10-31 |  | 99%
2014-11-30 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE |  | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374 | 26278 | 2013-12-11 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 16%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction |  | GUAM | N41557101A | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 | N41557101 | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | N6274210D1309 JQ01 | 24305 | 19184 | 2013-08-21 | 2015-12-15 | 2015-07-12 | 2015-12-15 | 33%
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N47609003 | EOD/TEU RANGE SUPPORT FACILITY |  | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | N6247313D4608 0007 | 1896 | 1764 | 2014-06-27 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 7%
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 |  | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008513C7711 AWD | 1925 | 1900 | 2013-03-14 | 2013-09-12 | 2013-08-30 |  | 99%
2014-11-30 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191513 | A SCHOOL BARRACKS |  | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430 | 29157 | 2013-11-14 | 2015-12-30 | 2015-12-16 | 2015-12-30 | 17% | -5604 | N42237100
2014-11-30 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191582 | UNDERSEA SURVEILLANCE SCIF FACILITY |  | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0003 | 4129 | 4836 | 2012-12-03 | 2014-06-25 | 2013-11-29 |  | 99%
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241288 | WASTEWATER SYSTEM |  | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | N6945014C0763 AWD | 1790 | 1645 | 2014-04-11 | 2015-03-27 | 2015-03-27 | 2015-03-27 | 47%
2014-11-30 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 |  | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791 | 7305 | 2014-07-29 | 2016-02-21 | 2016-02-21 | 2016-02-21 | 0%
2014-11-30 | 2013 | Navy Active | Major Military Construction |  | JAPAN | N61056353 | BACHELOR QUARTERS |  | 2013-01-24 | 2013-09-27 | NAVY STANDARD DOCUMENT | N6274213MP00015 | 5627 | 5521 | 2013-10-11 | 2015-02-02 | 2015-01-05 | 2015-02-02 | 25%
2014-11-30 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES |  | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | N4008414C8401 AWD | 12958 | 12065 | 2013-12-15 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 14.9%
2014-11-30 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB |  | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447 | 27601 | 2013-10-14 | 2016-04-17 | 2016-04-17 | 2016-06-16 | 22%
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction |  | SINGAPORE | N61077123 | TEMPORARY LCS SUSTAINMENT FACILITY |  | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | N4008413C9001 AWD | 755 | 768 | 2012-12-20 | 2014-01-15 | 2013-03-10 |  | 93%
2014-11-30 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY |  | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0007 | 14130 | 13483 | 2013-09-02 | 2015-03-12 | 2015-03-12 | 2015-05-01 | 56%
2014-11-30 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151372 | PHYSICAL FITNESS CENTER |  | 2012-12-12 | 2013-09-27 | C.E.R. INC. | N4008010D0302 0021 | 11409 | 10677 | 2013-10-11 | 2015-05-02 | 2015-05-02 | 2015-05-02 | 25%
2014-11-30 | 2013 | Navy Active | Military Family Housing Improvement |  | GUAM | N617551301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE |  | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 JQ02 | 26805 | 25377 | 2013-09-26 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 40.77%
2014-11-30 | 2013 | Navy Active | Major Military Construction |  | ROMANIA | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX |  | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT | N6247014MPE0025 | 40018 | 36389 | 2014-05-14 |  |  |  | 7%
2014-11-30 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863709 | GENERAL PURPOSE WAREHOUSE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 2446 | 1908 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 42%
2014-11-30 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863710 | HIGH EXPLOSIVE MAGAZINE |  | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 5849 | 5109 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 38%
2014-11-30 | 2013 | Navy Active | Major Military Construction | MISSISSIPPI | UNITED STATES | N63043317 | DINING FACILITY |  | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851 | 9278 | 2013-12-31 | 2015-10-09 | 2015-10-09 | 2015-10-09 | 17%
2014-11-30 | 2013 | Navy Active | Major Military Construction |  | GREECE | N66691907 | AIRCRAFT PARKING APRON EXPANSION |  | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPAQOLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663 | 11219 | 2014-07-25 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 4%
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436857 | FLOATING LABORATORY, MOORING DOLPHINS |  | 2013-01-16 | 2013-05-17 | NOVA GROUP INC | N4425510D5019 0003 | 3406 | 3115 | 2013-05-31 |  |  |  | 100%
2014-11-30 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990A | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | N68436990 | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 280041 | 238238 | 2012-11-15 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 63%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212984 | REGIMENTAL HEADQUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028 | 10655 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-08-14 | 37%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212985 | BACHELOR ENLISTED QUARTERS |  | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418 | 17605 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-08-14 | 30%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212986 | MOTOR TRANSPORTATION FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 5841 | 5659 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 52%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212987 | SUPPLY WAREHOUSE FACILITY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 6987 | 6635 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 53%
2014-11-30 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212989 | ARMORY |  | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 3653 | 3453 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 78%
2014-11-30 | 2013 | Navy Active | Major Military Construction | NEW JERSEY | UNITED STATES | N69213237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION |  | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | N4008513C3513 AWD | 34005 | 33534 | 2013-09-17 | 2014-11-27 | 2014-11-27 | 2015-01-24 | 88%
2014-11-30 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232900 | BAMS MAINTENANCE TRAINING FACILITY |  | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301 | 8719 | 2013-09-10 | 2014-11-21 | 2014-11-21 | 2015-05-01 | 8%
2014-11-30 | 2013 | Navy Reserve | Major Military Construction | TEXAS | UNITED STATES | N83447047 | COMMERCIAL VEHICLE INSPECTION SITE |  | 2013-01-22 | 2013-09-12 | KOMADA, LLC | N6945013D1767 0001 | 6894 | 6601 | 2013-09-26 | 2015-03-02 | 2014-11-06 | 2014-12-17 | 35.39%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318852 | 3RD BATTALION COMPLEX |  | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407 | 17348 | 2014-09-19 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 0%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318864 | AIRCRAFT MAINTENANCE EXPANSION |  | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | N6274214C1315 AWD | 16968 | 15196 | 2014-04-30 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 9%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION |  | 2014-02-17 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720 | 15145 | 2014-10-14 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 0%
2014-11-30 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 |  | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545 | 15632 | 2014-10-13 | 2016-02-02 | 2016-02-02 | 2016-02-02 | 0%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011353 | LANDFILL, PHASE 4 |  | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529 | 13776 | 2014-09-08 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 10%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312 | 13160 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 4%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001726 | REGIONAL COMMUNICATION STATION |  | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159 | 10019 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 3%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY |  | 2013-12-06 | 2014-09-10 | BLUEFORGE, LLC | N6945014D1271 0001 | 14685 | 14300 | 2014-09-24 | 2016-01-25 | 2016-01-25 | 2016-01-25 | 0%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004954 | CERS DISPATCH FACILITY |  | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | N6945012D1769 0005 | 1248 | 1157 | 2014-06-16 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 23%
2014-11-30 | 2014 | Marine Corps Reserve | Major Military Construction | MISSOURI | UNITED STATES | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY |  | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019 | 15845 | 2014-09-05 | 2016-02-23 | 2016-02-23 | 2016-02-23 | 0.7617%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction |  | JAPAN | M67400201 | AIRFIELD SECURITY UPGRADES |  | 2013-11-08 | 2014-04-18 | NAVY STANDARD DOCUMENT | N6274214MP00024 | 2881 | 2861 | 2014-05-02 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 4%
2014-11-30 | 2014 | Navy Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611407 | SITE IMPROVEMENTS - GENERAL OFFICERS QUARTERS A |  |  | 2014-09-30 | QUALITY SUPPORT SERVICES, INC. | N4008314D1014 0003 | 75 | 64 | 2014-10-14 |  | 2014-11-30 | 2015-03-31 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION |  | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573 | 5992 | 2014-10-10 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS |  | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151 | 13396 | 2014-08-29 | 2016-01-07 | 2016-01-07 | 2016-01-07 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND |  | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904 | 8407 | 2014-08-18 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620239 | EA-18G FACILITY IMPROVEMENTS |  | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5004 AWD | 29692 | 25168 | 2014-09-08 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620251 | P-8A HANGAR AND TRAINING FACILITIES |  | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5002 AWD | 84889 | 78957 | 2014-08-04 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 1%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N00620257 | HANGAR 11 MODIFICATIONS FOR SEARCH AND RESCUE |  | 2014-06-20 | 2014-09-02 | RORE, INC. | N4425514C8012 | 1424 | 1376 | 2014-09-16 |  |  |  | 28%
2014-11-30 | 2014 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411103 | HEWITT HALL RESEARCH CENTER |  | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319 | 12780 | 2014-08-14 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 1%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A227 | ARMORY |  | 2014-03-17 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492 | 4178 | 2014-08-08 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 0%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A917 | CRITICAL POWER FOR BULDING 200 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1120 | 1120 | 2014-06-05 |  |  |  | 100%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A918 | CRITICAL POWER FOR BUILDING T-130 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1175 | 1175 | 2014-06-05 |  |  |  | 100%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A919 | CRITICAL POWER FOR BLDGS 111, 113 AND 115 |  |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC | N6247006D6007 0002 | 1064 | 1065 | 2014-06-05 |  |  |  | 100%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A921 | UNACCOMPANIED HOUSING |  | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714 | 19531 | 2014-10-15 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 1%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction |  | GUAM | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) |  | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820 | 57162 | 2014-05-21 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 1%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | GUAM | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR |  | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710 | 48381 | 2014-04-10 | 2016-04-25 | 2016-04-25 | 2016-05-27 | 6%
2014-11-30 | 2014 | Marine Corps Active | Major Military Construction |  | GUAM | N41557J200 | NORTH RAMP UTILITIES II |  | 2014-04-11 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 AWD | 53014 | 47725 | 2014-10-31 | 2016-11-04 | 2016-09-02 | 2016-09-02 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY |  | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249 | 119854 | 2014-09-03 | 2018-06-20 | 2018-06-20 | 2018-04-08 | 3%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS |  | 2014-08-11 | 2014-09-30 | REILLY CONSTRUCTION, INC | N4008014D3014 AWD | 1453 | 1358 | 2014-10-14 | 2015-04-14 | 2015-05-26 |  | 0%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092662 | EOD ESU TWO EXPEDITIONARY LOGISTICS OVERHAUL WAREHOUSE |  | 2014-05-09 | 2014-08-06 | DOYON MANAGEMENT SERVICES, LLC | N4008514D2102 0001 | 1020 | 231 | 2014-08-20 | 2014-11-21 | 2014-11-21 |  | 6%
2014-11-30 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION |  | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0006 | 11446 | 10677 | 2014-09-30 | 2016-10-25 | 2016-10-25 | 2016-10-25 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201425 | LCS LOGISTICS SUPPORT FACILITY |  | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | N6945013D1765 0002 | 15842 | 14932 | 2014-06-13 | 2015-11-26 | 2015-11-26 | 2015-11-28 | 12%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | JAPAN | N61054011 | COMMUNICATIONS SYSTEM UPGRADE |  | 2014-05-02 | 2014-09-19 | NAVY STANDARD DOCUMENT | N6274214MP00028 | 9458 | 9458 | 2014-10-03 | 2016-08-16 | 2016-08-16 | 2016-08-16 | 0%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61057221 | HELO ALFS TEST ROOM, BUILDING 194 |  | 2014-06-12 | 2014-08-06 | NIHON MECCS CO., LTD. | N4008414C8302 AWD | 890 | 812 | 2014-08-20 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 0%
2014-11-30 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) |  | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799 | 21589 | 2014-10-14 |  | 2016-01-01 | 2016-01-01 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | GUAM | N61755425 | MODULAR STORAGE MAGAZINE |  | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865 | 45199 | 2014-05-26 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 3%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | GUAM | N61755518 | X-RAY WHARF IMPROVEMENTS |  | 2014-01-10 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085 | 42581 | 2014-06-17 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 3%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | GUAM | N61755566 | EMERGENT REPAIR FACILITY EXPANSION |  | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860 | 27568 | 2014-04-24 | 2016-05-12 | 2016-05-12 | 2016-05-12 | 5%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction |  | GUAM | N61755630 | HARDEN ELECTRICAL DISTRIBUTION LINE (POLARIS PT ROAD) |  | 2014-07-01 | 2014-09-30 | P&S CONSTRUCTION, INC. | N4019210D2804 0019 | 2000 | 1912 | 2014-10-14 | 2015-05-19 |  |  | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | GUAM | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY |  | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170 | 14318 | 2014-04-03 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 26%
2014-11-30 | 2014 | Navy Active | Major Military Construction |  | GUAM | N61755638 | SIERRA WHARF IMPROVEMENTS |  | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | N4019210D2808 0009 | 1462 | 1209 | 2014-06-13 | 2015-03-26 | 2015-03-26 | 2015-03-26 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 |  | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365 | 1113 | 2014-07-14 | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813058 | ROCKFALL PROTECTION AT RED HILL |  | 2014-09-24 | 2014-11-24 | TALION CONSTRUCTION, LLC | N6247813D4007 0031 | 2810 | 2615 | 2014-12-08 | 2016-05-18 | 2016-05-18 |  | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813270 | DRYDOCK WATERFRONT FACILITY |  | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355 | 20180 | 2014-03-03 | 2015-12-11 | 2015-12-11 | 2015-12-11 | 4%
2014-11-30 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) |  | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970 | 29387 | 2014-07-14 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 1%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863733 | PROVIDE ELECTROMAGNETIC CALIBRATION COMPLEX |  | 2014-08-29 | 2014-09-19 | NEWIMAR SA | N3319110D1801 0283 | 1144 | 711 | 2014-10-03 | 2015-08-21 |  |  | 5%
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042376 | VFA-94 HANGAR ALTERATIONS |  | 2014-08-27 | 2014-09-27 | COPPERTOP LEDCOR JV | N6247313D4608 0014 | 1839 | 1650 | 2014-10-11 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 |  | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179 | 10307 | 2014-08-01 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 1%
2014-11-30 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990B | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | N68436990 | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 | 24880 | 13754 | 2014-01-14 |  |  |  | 0%
2014-11-30 | 2014 | Navy Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | N684691400 | NAVSEA HQ RESTORATION |  | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | N6247013D6019 JU01 | 48905 | 48129 | 2014-02-14 | 2015-01-31 |  | 2015-01-31 | 78%
2014-11-30 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232281 | AIRCRAFT ENGINE TEST PADS |  | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | N6247309D1657 0016 | 6106 | 5718 | 2014-06-26 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 6%
2014-11-30 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232599 | UNACCOMPANIED HOUSING CONVERSION (PORT HUENEME) |  |  | 2014-11-24 | NAVY STANDARD DOCUMENT | N6247314RP00165 | 33594 | 25645 | 2014-12-08 |  |  |  | 100%
2014-11-30 | 2014 | Navy Active | Major Military Construction | OKLAHOMA | UNITED STATES | N83447136 | TACAMO E-6B HANGAR |  | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19401 | 18478 | 2014-10-14 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 0%
2014-11-30 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | MISSOURI | UNITED STATES | NGA021 | Data Ctr West #1 Power & Cooling Upgrade |  | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors |  | 8202 | 11198 | 2012-08-06 | 2014-01-21 | 2013-08-06 | 2015-01-31 | 99% |  |  | Technology Center Third Floor Fit-out - project period of performance extended to 31 January 2015
2014-11-30 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | NGA013 | Technology Center Third Floor Fit-out |  | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 32387 | 39495 | 2012-11-02 | 2014-05-30 | 2014-01-02 | 2015-01-31 | 99% | 1905-05-28 | NGA021 | Data Ctr West #1 Power & Cooling Upgrade - project period of performance extended to 31 January 2015
2014-11-30 | 2007 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES |  | Infrastructure Increments 1-3; NGA HQ's | [8 empty] | 2011-09-15 | 2013-06-15 | 2014-12-31 | 99% |  |  | [Removed "Various" from Solicitation Date, Award Date, Start Date, and Prime Contract Recipient (Company Name)]
2014-11-30 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 65416 | NGA Headquarters, SCIF, All Phases |  | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 1181439 | 1398710 | 2007-09-06 | 2011-04-19 | 2011-12-22 | 2014-12-31 | 99%
2014-11-30 | 2009 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060 | 13760 | 2010-09-21 | 2013-01-17 | 2013-01-17 | 2014-04-18 | 99%
2014-11-30 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) |  | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223 | 124671 | 2010-09-21 | 2014-05-13 | 2014-04-18 |  | 93% | 37500 |  | Contract Completion date has not been negotiated yet
2014-11-30 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) |  | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443 | 4544 | 2010-09-09 | 2012-06-29 | 2011-09-26 | 2012-06-29 | 100%
2014-11-30 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) |  | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253 | 5702 | 2013-03-07 | 2014-09-30 | 2014-03-07 | 2014-12-09 | 98%
2014-11-30 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17781 | Tordella Chilled Water Backup Storage |  | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700 | 11700 | 2010-06-30 | 2012-05-30 | 2011-08-20 | 2012-05-30 | 100%
2014-11-30 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17782 | R&E Chilled Water Backup Storage |  | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200 | 3200 | 2011-11-07 | 2014-10-31 | 2013-07-13 | 2015-02-27 | 78%
2014-11-30 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18052 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566 | 8257 | 2011-03-31 | 2014-05-14 | 2013-02-01 | 2014-05-14 | 100%
2014-11-30 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18053 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095 | 16448 | 2012-01-31 | 2014-05-31 | 2013-02-01 | 2014-05-31 | 100%
2014-11-30 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18054 | Power & Cooling Infrastructure Upgrade |  | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085 | 7316 | 2012-11-30 | 2014-08-31 | 2013-02-01 | 2014-08-31 | 92% |  |  | Commissioning of system completed November 26, 2014.
2014-11-30 | 2011 | National Security Agency | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 22573 | Classified location |  | 2012-08-15 | 2012-09-30 | Kaseman |  | 12000 | 21500 | 2012-12-01 | 2013-10-01 | 2013-09-30 | 2014-03-15 | 100%
2014-11-30 | [8 empty] | 2012-08-01 | 2012-09-21 | Hardline |  | 12000 | 12000 | 2012-09-25 | 2012-09-15 | 2013-04-04 | 2013-04-04 | 100% |  |  | Placed in service 01-Oct-2013
2014-11-30 | [8 empty] | 2012-07-01 | 2012-07-30 | PAE |  | 200 | 200 | 2012-08-15 | 2012-09-15 | 2012-08-30 | 2012-08-30 | 100% |  |  | Placed in service 01-Oct-2013
2014-11-30 | 2011 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17866 | North Campus Electrical Utility Plant (NCEUP) |  | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900 | 132488 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-01-16 | 98% | 50100 | Mountainview
2014-11-30 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 | MOD II |  | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657 | 8867 | 2012-05-30 | 2014-03-03 | 2014-01-30 | 2015-01-16 | 100%
2014-11-30 | [6 empty] | MOD II (Phase 2) |  | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620 | 2657 | 2013-11-26 | 2014-09-30 | 2014-02-28 | 2014-04-28 | 98%
2014-11-30 | [6 empty] | Whitelaw Wedge |  | 2012-04-26 | 2012-06-18 | JAAT | W912HN-10-D-0063 | 15315 | 16526 | 2012-07-18 | 2014-07-09 | 30-Ja n-14 | 2014-10-23 | 95%
2014-11-30 | 2012 | National Security Agency | Major Military Construction | COLORADO | UNITED STATES | 23051 | Mountainview |  | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975 | 125410 | 2012-11-02 | 2015-07-22 | 2015-05-03 | 2015-05-28 | 85%
2014-11-30 | [6 empty] | Mountainview |  | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621 | 5621 | 2013-10-13 |  | 2014-02-14 | 2015-09-30 | 100%
2014-11-30 | 2012 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 24649 | High Performance Computing Center 2 |  | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589 | 591568 | 2013-03-12 | 2015-09-30 | 2015-09-16 | 2015-09-30 | 68%
2014-11-30 | 2013 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 26170 | East Campus Building 1 |  | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91866 | 92192 | 2013-10-24 | 2016-01-05 | 2015-10-16 | 2015-10-16 | 10%
2014-11-30 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | 61772 | Operations Complex |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30155148 | 16751 | 17554.9517 | 2012-01-31 |  | 2013-04-25 | 2014-12-31 | 97%
2014-11-30 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033003 | Vehicle Maintenance Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30136034 | 4575 | 5123.2845 | 2012-01-31 |  | 2013-04-25 | 2015-03-15 | 97%
2014-11-30 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033005 | Storage Facility |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154837 | 3603 | 3766.2116 | 2012-01-31 |  | 2013-04-25 | 2014-12-31 | 97%
2014-11-30 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033019 | Air Operations Center |  | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154494 | 2931 | 3078.5666 | 2012-01-31 | 2014-11-12 | 2013-04-25 | 2014-12-31 | 97%
2014-11-30 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64484 | Operations Additions |  | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | W912HN-11-C-0010 / 29379991 | 13388 | 15184.2497 | 2011-08-25 |  | 2014-06-10 | 2015-05-08 | 91%
2014-11-30 | 2011 | Special Operations Command | Major Military Construction | GEORGIA | UNITED STATES | 65395 | Company Support Facility |  | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391.578 | 15637.173 | 2011-12-27 | 2014-05-30 | 2013-06-19 | 2014-07-31 | 99%
2014-11-30 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 66362 | C4 Facility - JSOC |  | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | W912HN-12-C-0009 / 29381338 | 41446 | 44322.4218 | 2012-06-14 |  | 2014-01-31 | 2015-06-16 | 99%
2014-11-30 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69573 | Admin/Company Operations |  | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN-10-D-0058 / 29381912 | 8487 | 9166 | 2011-10-27 | 2013-11-21 | 2013-04-18 | 2014-01-23 | 99%
2014-11-30 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063049 | Hangar / AMU (MC-130J) |  | 2011-05-13 | 2011-09-09 | Speegle Construction | W912PP-11-C-0029 / 30594756 | 19432 | 20310.9637 | 2011-10-11 | 2014-05-02 | 2013-12-01 | 2014-05-02 | 99%
2014-11-30 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063052A | Operations & Training Complex (3rd UAS) |  | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13613.73 | 13829.0421 | 2012-09-06 | 2014-06-03 | 2013-07-17 | 2014-06-03 | 99% | 7132 | 66362
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60272 | Communications Training Complex (SWCS) |  | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN-10-D-0049 / 29371639 | 8290.317 | 8469.8948 |  |  | 2014-03-06 | 2015-02-02 | 93%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60821 | Squadron Headquarters Addition |  | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN-10-D-0060 / 29389201 | 10605 | 10918.0428 |  |  | 2014-06-06 | 2015-05-15 | 92%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66598 | Rotary Wing Hangar |  | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350 | 35208.168 |  |  | 2014-02-15 | 2015-04-15 | 93%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69458 | Battalion Operations Complex |  | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772.305 | 16772.305 |  |  | 2014-06-03 | 2015-03-15 | 64%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69758 | Brigade Headquarters |  | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 15649.974 | 16280.6264 |  |  | 2014-05-08 | 2015-05-09 | 47%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525.847 | 18617.616 |  |  | 2014-05-01 | 2015-03-01 | 87%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters |  | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41071297 | 4506.8515 | 4506.8515 |  | 2014-05-01 | 2015-03-01 | 2015-03-01 | 87%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 76363 | Company Operations Facility |  | 2012-04-18 | 2012-08-30 | Adept-Absher 1 Joint Venture | W912DW-12-C-0037 / 27917342 | 18751 | 18626.363 | 2014-06-20 | 2014-06-20 | 2014-04-01 | 2014-06-21 | 99%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76364 | Battalion Operations Facility |  | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201.3031 | 33435.0071 |  |  | 2014-08-26 | 2015-06-01 | 75%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76366 | Company Operations Facility (GSTB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673.727 | 15674.302 |  |  | 2015-09-12 | 2016-04-26 | 79%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76371 | Company Operations Facility (GSB) |  | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092.801 | 17142.71 |  |  | 2015-09-12 | 2016-04-26 | 79%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 76374 | MH-47 Hangar |  | 2011-11-28 | 2012-05-07 | Hensel Phelps Construction Co. | W912QR-12-C-0035 / 28427841 | 32450 | 33728.627 | 2014-08-27 | 2014-08-27 | 2014-03-23 | 2014-08-29 | 99%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073014 | SOF C-130 Sq Ops Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 25127091 | 7413 | 7874.8241 | 2014-07-11 | 2014-07-11 | 2014-02-22 | 2014-07-11 | 99%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073018 | SOF C-130 Wash Rack Hangar |  | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | W912PP-12-C-0025 / 30667913 | 9329 | 9703.7394 | 2014-09-09 | 2014-09-09 | 2014-04-10 | 2014-08-29 | 99%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073021 | SOF AMXS Facility |  | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | W912PP-12-C-0033 / 25138433 | 14700 | 14966.2684 | 2013-01-10 | 2014-09-22 | 2014-12-22 | 2014-09-19 | 99%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083012A | SOF Hangar/AMU |  | 2012-04-20 | 2012-08-31 | Hensel Phelps | W912PP-12-C-0027 / 30858121 | 28160 | 29105.547 | 2012-10-24 |  | 2014-12-23 | 2014-09-07 | 98%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083016 | SOF Squadron Operations Facility |  | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 28791332 | 10615 | 11040 | 2012-11-09 | 2014-05-30 | 2015-01-06 | 2014-05-30 | 99% | 2293 | CZQZ063035
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV103011 | SOF Simulator Facility |  | 2012-05-01 | 2012-08-09 | Barlovento LLC. | W91278-10-D-0072 | 5551 | 5543 | 2012-09-13 | 2014-07-18 | 2013-12-24 | 2014-07-18 | 99%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1049 | Range 130 Support Projects |  | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129 | 8130 | 2013-06-03 |  | 2014-11-13 | 2014-11-13 | 11%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1174 | MWD Facility |  | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | N6247311D0068 #0003 | 3075 | 3302 | 2012-10-03 | 2014-11-14 | 2014-03-23 | 2014-11-14 | 67%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-164 | Logistics Support Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727 | 11727 | 2012-12-09 |  | 2014-07-24 | 2014-07-24 | 75%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-473 | SEAL Team Operations Facility |  | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366 | 23366 | 2014-08-13 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 29%
2014-11-30 | 2012 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-504 | SOF Operational Vehicle Storage Facility (6UMC) |  | 2013-03-12 | 2013-05-23 | Richard Brady & Associates, Inc. | N4008511D6591 #0010 | 1660 | 1660 | 2013-12-03 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 83%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | ALASKA | UNITED STATES | P-531 | Cold Weather Maritime Training Facility |  | 2012-04-30 | 2012-09-27 | Alutiiq Diversified Service, LLC | N4425512C3011 | 17449 | 17449 | 2014-03-04 |  | 2015-04-15 | 2015-04-15 | 95%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-769 | Building Renovation |  | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022 | 3022 | 2013-01-02 | 2014-08-27 | 2014-06-27 | 2014-10-26 | 97%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-826 | Military Working Dog Facility |  | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139 | 4139 | 2012-12-09 |  | 2014-07-24 | 2014-07-24 | 99%
2014-11-30 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH043055 | SOF Training Facility |  | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN-10-D-0063 / 25189640 | 4773.799 | 4752.7374 | 2012-05-31 | 2014-10-29 | 2013-11-22 | 2014-10-19 | 99%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | ARIZONA | UNITED STATES | 53542 | Parachute Training Facility |  | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546.92 | 6546.92 | 2014-11-09 |  | 2016-05-09 | 2016-05-09 | 0%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 65052 | Medical Support Addition |  | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199.999 | 3283.4702 | 2013-10-16 |  | 2015-08-25 | 2015-04-17 | 69%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66597 | Landgraf Hangar Extension |  | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384.894 | 3384.894 | 2014-04-29 |  | 2015-10-21 | 2015-11-20 | 10%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287a | Battalion Operations Complex |  | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907.435 | 30907.435 | 2013-10-09 |  | 2015-05-13 | 2015-10-24 | 30%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287b | Battalion Operations Complex |  |  | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404 | 21201 |  |  |  |  | 0%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69382 | Civil Affairs Battalion Complex |  | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816 | 25816 | 2013-10-16 |  | 2015-08-14 | 2014-12-15 | 28%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 69447 | Group Support Battalion Detachment |  | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123.1802 | 22183.1802 | 2014-04-14 |  | 2016-02-13 | 2016-02-13 | 7%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69493 | Sustainment Bde Headquarters |  | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085 | 23085 | 2014-06-18 |  | 2016-05-02 | 2016-05-02 | 3%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 76367 | SOF Battalion Operations Complex |  | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441 | 36461 |  |  | 2016-06-16 | 2016-07-20 | 1%
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 79655 | SOF Training Facility (4UMC) |  | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | W912PM-13-C-0003 | 1592 | 1592 | 2013-06-18 |  | 2014-10-15 | 2014-10-16 | 37%
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 80233 | SOF Live-Fire Training Tower (6UMC) |  | 2013-06-16 | 2014-01-22 | Trend Construction, Inc. | W912HN-12-D-0030-DQ04 | 1531.7653 | 1531.7653 | 2014-02-12 |  | 2015-05-15 | 2015-07-17 | 17%
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81483 | Mtn Climb/Rappel Tower (5UMC) |  | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F-13-C-0006 | 1513 | 1628 | 2013-09-20 |  | 2014-10-15 | 2014-09-15 | 99%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083013 | Combat Parking Apron |  | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP-14-C-0014 / 32077093 | 19481.9877 | 19476.9387 | 2014-06-13 |  | 2015-08-13 | 2015-11-22 | 22%
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NEW MEXICO | UNITED STATES | CZQZ100221 | Parachute Drying Tower (3 UMC) |  | 2014-03-06 | 2014-07-01 | Speegle Construction | W912PP-14-C-0017 / 39136021 | 1547 | 1547 | 2014-07-28 |  | 2015-05-24 | 2015-05-24 | 12%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTFA113004 | SOF AvFID Ops and MX Facilities |  | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942.3 | 29974.109 | 2013-11-05 |  | 2016-12-01 | 2016-12-25 | 21%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | NVZR083702 | Joint Special Operations University Facility |  | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753.0246 | 24836.9926 | 2013-11-04 |  | 2015-09-15 | 2015-06-28 | 17%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1218 | Marine Battalion Company/Team Facilities |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46370 | 2014-02-20 |  | 2016-03-01 | 2016-01-18 | 33%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1393 | Survival Evasion Resistance Escape Trng Fac |  | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46370 | 2014-02-20 |  | 2016-01-18 | 2016-01-18 | 33%
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1410 | SOF EOD Expansion (1UMC) |  | 2013-09-04 | 2013-09-26 | Quadrant Construction, Inc | N4008510D0261 #0017 | 1566 | 1566 | 2013-10-15 |  | 2014-09-22 | 2014-09-22 | 81%
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1450 | Fires Platoon Storage Facility (7UMC) |  | 2013-12-20 | 2014-02-13 | Quadrant Construction, Inc | N4008510D0261 #0019 | 1459.25 | 1469 | 2014-03-13 |  | 2014-12-13 | 2014-12-10 | 45%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-165 | CS/CSS Support Facility |  | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351 | 9344 | 2014-10-06 |  | 2015-09-09 | 2015-11-26 | 43%
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-564 | NSWG-4 Paraloft Addition (2UMC) |  | 2013-06-14 | 2013-09-27 | Royce Homeland JV, LLC | N4008512D6305 #0005 | 1308 | 1319 | 2013-10-15 |  | 2014-12-31 | 2014-12-31 | 72%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-876 | Indoor Dynamic Shooting Facility |  |  | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290 | 24290 |  |  | 2016-10-01 | 2016-10-01 | 0%
2014-11-30 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-888 | Close Quarters Combat Range, Phase II |  |  | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489 | 12489 |  |  | 2016-09-30 | 2016-09-30 | 0%
2014-11-30 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 61064 | SOF Upgrade Training Facility |  | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951 | 13951 | 2014-11-17 |  | 2016-08-18 | 2016-08-18 | 0%
2014-11-30 | 2014 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 69446 | Group Support Battalion Detachment |  | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083.965 | 15083.965 |  |  | 2016-02-18 | 2016-02-08 | 1%
2014-11-30 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76375 | Civil Affairs Battalion Annexes |  | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358 | 27358 | 2014-11-14 |  | 2016-07-12 | 2016-07-12 | 0%
2014-11-30 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76376 | Language and Cultural Center |  |  | 2014-12-02 | Archer Western Contractors, LLC | W91278-11-D-0073-DQ02 | 51696.6683 | 51696.6683 |  |  |  |  | 0% | 0
2014-11-30 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 79438 | Combat Medic Skills Sustainment Course Bldg |  | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193.631 | 7193.631 |  |  | 2016-08-01 | 2016-08-01 | 0%
2014-11-30 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV083002 | Add/Alter Operations Facility |  | 2014-05-26 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048.867 | 7048.867 |  |  | 2016-08-03 | 2016-05-24 | 0%
2014-11-30 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1391 | SOF Sustainment Training Complex |  | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333 #0004 | 27546.924 | 27546.924 |  |  | 2016-09-02 | 2016-09-02 | 2%
2014-11-30 | 2014 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1469 | MSOB Support Facilities |  | 2014-08-20 | 2014-09-30 | Quadrant Construction, Inc | N4008510D0261/0022 | 1751.362 | 1751.362 |  |  | 2015-09-25 | 2015-09-25 | 0%
2014-10-31 | 2010 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Upgrade Electrical System |  | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power |  | 23269 | 23269 | 2013-11-07 | 2015-02-05 | 2015-02-05 | 2015-02-05 | 2% | 4719 | PERC-$437, Fuel Storage Fac-$200, Secondary UPS-$300, FY11 P&D-$3,782 | Design/Build - 100% design in progress
2014-10-31 | 2010 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Secondary UPS |  | 2010-06-16 | 2010-09-27 | Iron Bridge Construction |  | 5192 | 7515 | 2010-09-27 | 2013-07-31 | 2012-02-29 | 2014-07-30 | 99% | 0 |  | Closeout in progress
2014-10-31 | 2011 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Power Plant Modernization Phase 3 (WPP) |  | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. |  | 43594 | 43741453 | 2013-04-22 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 18% | -4001 |  | Project at 100% design, funds absconded by sequester
2014-10-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Metro Entrance Facility/Visitor Screening Facility |  | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. |  | 5609 | 5609 | 2013-11-01 | 2015-06-01 | 2015-06-01 | 2015-06-01 | 13% | 0 |  | Design/Build - Not affected by sequester
2014-10-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Secure Access Lane (SAL) |  | 2011-08-08 | 2013-09-30 | Ikhana,LLC |  | 5454 | 5454 | 2013-11-01 | 2015-05-01 | 2015-05-01 | 2015-05-01 | 4% | 0 |  | Award Contract Base Bid Items 28 Sep 2013; All options, for DIACAP $31,093, Perimeter Fence and 3 Vehicle Gates $138,693 and Public Rest Room (OPA funded) $447,766 awarded; NTP estimated by 1 Feb 2013. 510 cds contract duration.
2014-10-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Heliport Control Tower/Fire Station | [12 empty] | 0 |  | In 35% design.
2014-10-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Memorial Plaza | [12 empty] | 0 |  | Design contract award 26SEP13. NTP 1 Nov13. Design 8 mos/Construct 12mos. Contract duration 540 cds

## DETAILED EXPENDITURES
Data as of Date | Fiscal Year | Component | Appropriation Fund Type | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Current Expenditure Amount ($000) | Remarks
2014-11-30 | 2006 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773.86 | 281956.1925 | 281662.7882
2014-11-30 | 2006 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782.96 | 26874.615 | 26317.8729
2014-11-30 | 2006 | Air Force Active | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 63753.948 | 58353.2036 | 57468.177
2014-11-30 | 2006 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 1530 | 0 | 0
2014-11-30 | 2006 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15769.71 | 15283.0716 | 15073.8774
2014-11-30 | 2006 | Air Force Reserve | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289.57 | 5289.1201 | 5289.1201
2014-11-30 | 2006 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960 | 3959.9996 | 3959.9996
2014-11-30 | 2006 | Air National Guard | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006 | 28020.5334 | 28018.597
2014-11-30 | 2006 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882 | 6882 | 6882
2014-11-30 | 2007 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232 | 329307.8469 | 329275.2804
2014-11-30 | 2007 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12896.1514 | 12604.7155
2014-11-30 | 2007 | Air Force Active | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 74021 | 72937.1538 | 72092.6194
2014-11-30 | 2007 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 2225 | 2206.9737 | 2206.9737
2014-11-30 | 2007 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14163.2777 | 14163.2777
2014-11-30 | 2007 | Air Force Reserve | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109 | 5072.4629 | 5072.4629
2014-11-30 | 2007 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477 | 4476.9716 | 4476.9716
2014-11-30 | 2007 | Air National Guard | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050 | 19043.34 | 19043.3394
2014-11-30 | 2007 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000 | 5999.9999 | 5999.9999
2014-11-30 | 2008 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 259262 | 238598.4841 | 226658.0233
2014-11-30 | 2008 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12161.823 | 12161.823
2014-11-30 | 2008 | Air Force Active | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 30148 | 29576.7563 | 29188.6112
2014-11-30 | 2008 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 21054 | 13130.6247 | 13130.6247
2014-11-30 | 2008 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14081.4775 | 13525.7208
2014-11-30 | 2008 | Air Force Reserve | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300 | 5270.7978 | 5270.7978
2014-11-30 | 2008 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909 | 4909 | 4909
2014-11-30 | 2008 | Air National Guard | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721 | 10619.0353 | 10619.0353
2014-11-30 | 2008 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184 | 14183.984 | 14168.9847
2014-11-30 | 2009 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513.728 | 207293.8625 | 161500.8332
2014-11-30 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 592614 | 592503 | 592503
2014-11-30 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - P.L. 111-5) | 16455 | 16455 | 16455
2014-11-30 | 2009 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703 | 7593.62 | 7524.9478
2014-11-30 | 2009 | Air Force Active | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105196.1872 | 103703.1322 | 102132.2969
2014-11-30 | 2009 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14860.6296 | 13914.1803
2014-11-30 | 2009 | Air Force Reserve | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165 | 6133.5834 | 6123.2565
2014-11-30 | 2009 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443 | 5442.927 | 5442.927
2014-11-30 | 2009 | Air National Guard | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056 | 19056 | 18944.6009
2014-11-30 | 2009 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243 | 34163.725 | 33881.6744
2014-11-30 | 2010 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558 | 59491.5566 | 59488.5618
2014-11-30 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 529950 | 510499 | 508545
2014-11-30 | 2010 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302 | 1440.5783 | 1396.5783
2014-11-30 | 2010 | Air Force Active | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 87562 | 87228.7968 | 84305.1398
2014-11-30 | 2010 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 25223 | 21494.5143 | 21462.048
2014-11-30 | 2010 | Air Force Active | Unspecified Minor Military Construction [UMMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 12086.3123 | 11595.7213
2014-11-30 | 2010 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000 | 19867.8576 | 19777.0132
2014-11-30 | 2010 | Air Force Reserve | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139 | 8001.7193 | 2737.5076
2014-11-30 | 2010 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 752.8898 | 752.8898 | 752.8898
2014-11-30 | 2010 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 47.1102 | 47.1102 | 0
2014-11-30 | 2010 | Air National Guard | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670.441 | 19575.2809 | 19260.3631
2014-11-30 | 2010 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913.559 | 44557.567 | 35584.605
2014-11-30 | 2011 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192.95 | 53397.0155 | 35209.278
2014-11-30 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 544423 | 514090 | 512405
2014-11-30 | 2011 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153 | 3921.568 | 3915.9807
2014-11-30 | 2011 | Air Force Active | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 63903.328 | 60020.7265 | 56326.9269
2014-11-30 | 2011 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 2622 | 1854.0467 | 1854.0467
2014-11-30 | 2011 | Air Force Active | Unspecified Minor Military Construction [UMMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 49584 | 39032.518 | 24567.598
2014-11-30 | 2011 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17964 | 17502.4646 | 16932.6922
2014-11-30 | 2011 | Air Force Reserve | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649.694 | 1521.061 | 1521.061
2014-11-30 | 2011 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2745.819 | 2728.9494 | 2651.5972
2014-11-30 | 2011 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7.663 | 7.663 | 0
2014-11-30 | 2011 | Air National Guard | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195.572 | 8638.9962 | 8562.9303
2014-11-30 | 2011 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984 | 7710.1992 | 5505.3658
2014-11-30 | 2012 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407 | 21828.4723 | 20942.1487
2014-11-30 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 448449 | 434239 | 427974
2014-11-30 | 2012 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056 | 4018.8178 | 3999.8629
2014-11-30 | 2012 | Air Force Active | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 78413 | 69272.5196 | 62583.1316
2014-11-30 | 2012 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000 | 19483.3001 | 13663.4308
2014-11-30 | 2012 | Air Force Reserve | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200 | 2019.067 | 1299.3891
2014-11-30 | 2012 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4594.3732 | 4216.3096 | 2898.2323
2014-11-30 | 2012 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 839.6268 | 839.6268 | 0
2014-11-30 | 2012 | Air National Guard | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225 | 12010.566 | 11005.7954
2014-11-30 | 2012 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000 | 6806.3957 | 4693.4132
2014-11-30 | 2013 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936.577 | 2534.3422 | 859.1682
2014-11-30 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 468443 | 445332 | 390073
2014-11-30 | 2013 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3951.846 | 0 | 0
2014-11-30 | 2013 | Air Force Active | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 410.408 | 367.934 | 119.7052
2014-11-30 | 2013 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14467.9945 | 3991.1429 | 1523.4505
2014-11-30 | 2013 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875.201 | 1402.152 | 468.4011
2014-11-30 | 2013 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1641.761 | 0 | 0
2014-11-30 | 2013 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 355.6 | 355.6 | 0
2014-11-30 | 2013 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994.721 | 3421.4572 | 2235.0777
2014-11-30 | 2013 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892.214 | 3162.1387 | 390.1944
2014-11-30 | 2014 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093 | 40753.6909 | 66.3957
2014-11-30 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 417511 | 316399 | 157671
2014-11-30 | 2014 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267 | 0 | 0
2014-11-30 | 2014 | Air Force Active | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314 | 9618.0972 | 6060.9745
2014-11-30 | 2014 | Air Force Active | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448 | 0 | 0
2014-11-30 | 2014 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229 | 0 | 0
2014-11-30 | 2014 | Air Force Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530 | 0 | 0
2014-11-30 | 2014 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400 | 5076.2151 | 223.3822
2014-11-30 | 2014 | Air National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000 | 594.4725 | 0
2014-11-30 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000 | 24000
2014-11-30 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000 | 25000
2014-11-30 | 2011 | Army Active | Host Nation Support | $29,944 Appropriated + $13,000 ATR | 42944 | 42932 | 42899
2014-11-30 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR + $9,000 ATR | 36000 | 35030 | 33770
2014-11-30 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954 | 33668 | 32302
2014-11-30 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000 | 22682 | 21224
2014-11-30 | 2009 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 21855 | 21855 | 21855
2014-11-30 | 2010 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 28393 | 28392 | 28387
2014-11-30 | 2011 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 37328 | 37328 | 37311
2014-11-30 | 2012 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 34342 | 34265 | 34263
2014-11-30 | 2013 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 28124 | 27973 | 27855
2014-11-30 | 2014 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 21949 | 21645 | 14610
2014-11-30 | 2015 | Army Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Army Family Housing O&M | 3000 | 1754 | 673
2014-11-30 | 2010 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 60100 | 14055 | 14043
2014-11-30 | 2011 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 78330 | 1274 | 1274
2014-11-30 | 2009 | Army Active | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 218891 | 216315
2014-11-30 | 2009 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 576 | 576 | 524
2014-11-30 | 2010 | Army Active | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250434 | 246718
2014-11-30 | 2010 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 3936 | 3935 | 2503
2014-11-30 | 2011 | Army Active | Planning and Design | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 308676 | 262991 | 255953
2014-11-30 | 2011 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 2036 | 1990 | 1367
2014-11-30 | 2012 | Army Active | Planning and Design | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 191445 | 177765
2014-11-30 | 2012 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 7897 | 6908 | 6374
2014-11-30 | 2013 | Army Active | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46112 | 45100 | 39818
2014-11-30 | 2013 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 4635 | 89 | 89
2014-11-30 | 2014 | Army Active | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575 | 27011 | 21327
2014-11-30 | 2014 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 4408 | 0 | 0
2014-11-30 | 2009 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28750 | 28232 | 25954
2014-11-30 | 2010 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 31250 | 31149 | 29659
2014-11-30 | 2011 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 28704 | 26450 | 26312
2014-11-30 | 2012 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 20000 | 19043 | 18580
2014-11-30 | 2013 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 23775 | 14713
2014-11-30 | 2014 | Army Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 21961 | 1971
2014-11-30 | 2009 | Army National Guard | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 60944 | 60943 | 60943 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2009 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 21880 | 21880 | 21880 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 47210 | 47210 | 47210 | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2010 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 36905 | 36905 | 36905 | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Planning and Design | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25604 | 24287 | 24287 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2011 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14215 | 11220 | 11220 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Planning and Design | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191 | 17086 | 17086 | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2012 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14149 | 11784 | 11784 | PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Planning and Design | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17 | 2407 | 1771 | 1771 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2014-11-30 | 2013 | Army National Guard | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25748 | 2971 | 2971 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2013 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14562 | 14254 | 14254 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-11-30 | 2014 | Army National Guard | Planning and Design | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930 | 2431 | 2431 | PL 113-76 P&D Recission
2014-11-30 | 2014 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 12240 | 1398 | 1398
2014-11-30 | 2012 | Defense Finance and Accounting Service | Planning and Design | Investigation and Design | 1992 | 748 | 709
2014-11-30 | 2013 | Defense Finance and Accounting Service | Unspecified Minor Military Construction [UMMC] | Construction | 15404 | 12903 | 3059
2014-11-30 | 2009 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 3979 | 3979 | 3979
2014-11-30 | 2010 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4018 | 3984 | 3950
2014-11-30 | 2011 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4673 | 2696 | 2377
2014-11-30 | 2012 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 5930 | 4750 | 4708
2014-11-30 | 2013 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 4608 | 3401 | 828
2014-11-30 | 2014 | Defense Health Agency | Unspecified Minor Military Construction [UMMC] | UMC Projects | 9578 | 1854 | 1309
2014-11-30 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Parking Garage Replacement | 1498 | 461 |  | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $416K (CORRECTED AMOUNT) obligated as CAT I. Contract awarded on 23 September 2014.
2014-11-30 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Chilled Water Project for Data Center | 125 |  |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.
2014-11-30 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Cooling Tower for Data Center | 105 |  |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.
2014-11-30 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for UPS for Data Center Installation | 120 | 120 |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 100% design completed.
2014-11-30 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for Construction of JUIAF RDF | 1195 | 1195 |  | $1,195 obligated as CAT I acceptance. Design complete.
2014-11-30 | 2013 | DISA | Construction - Major Military Construction |  | 2224 |  |  | DISA Europe Facility Upgrades
2014-11-30 | 2013 | DISA | Construction - Major Military Construction |  | 77515 | 62283 |  | Construct New DISA Facility Scott AFB
2014-11-30 | 2014 | DISA | Construction - Major Military Construction |  | 2616 |  |  | DISA Pacific Facility Upgrade
2014-11-30 | 2009 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2009 to 2013 | 4338 | 4334 | 4334
2014-11-30 | 2009 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2009 to 2010 | 4093 | 4027 | 4027
2014-11-30 | 2010 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2010 to 2015 | 12548 | 12446 | 12446
2014-11-30 | 2010 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2010 to 2014 | 4078 | 4078 | 4078
2014-11-30 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2012 to 2016 | 36093 | 35951 | 35951
2014-11-30 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2011 to 2014 | 4968 | 3996 | 3996
2014-11-30 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of project from 2012 to 2016 | 34331 | 34330 | 34330
2014-11-30 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] | For minor construction projects from 2012 to 2014 | 6312 | 5431 | 5431
2014-11-30 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of project from 2014 to 2017 | 18308 | 10301 | 10301
2014-11-30 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Military Construction [UMMC] |  | 6686 | 0 | 0
2014-11-30 | 2008 | DoD Education Activity | Planning and Design | Design Efforts FY09 RCI MILCON projects | 3298 | 3348 | 3295 | RCI-Residential Communities Initiative
2014-11-30 | 2008 | DoD Education Activity | Planning and Design | Design efforts for FY 08/09/ 10/11/12 MILCON projects | 1863 | 1863 | 1863
2014-11-30 | 2009 | DoD Education Activity | Planning and Design | Design Efforts FY09 RCI MILCON projects | 1830 | 1830 | 1830
2014-11-30 | 2009 | DoD Education Activity | Planning and Design | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 5000 | 5000 | 5000
2014-11-30 | 2009 | DoD Education Activity | Planning and Design | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 6793 | 6793 | 5414
2014-11-30 | 2010 | DoD Education Activity | Planning and Design | Design efforts for FY 10/11/ 12/13 MILCON projects | 8829 | 8829 | 8717 | Reflects Sequestration Reduction
2014-11-30 | 2011 | DoD Education Activity | Planning and Design | Design efforts for FY 11/12/ 13 MILCON projects | 7840 | 7840 | 7840
2014-11-30 | 2011 | DoD Education Activity | Planning and Design | Design efforts for FY 11/12/13 MILCON projects | 70826 | 70826 | 53991 | Reflects Sequestration Reduction
2014-11-30 | 2012 | DoD Education Activity | Planning and Design | Design efforts for FY 12/13 MILCON projects | 64551 | 64465 | 45356 | Reflects Sequestration Reduction
2014-11-30 | 2013 | DoD Education Activity | Planning and Design | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 73424 | 24160 | Reflects Sequestration Reduction
2014-11-30 | 2014 | DoD Education Activity | Planning and Design | Design efforts for FY 14/15/16/17 MILCON projects | 75905 | 0
2014-11-30 | 2009 | DoD Education Activity | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5 | 4 | 4 | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2014-11-30 | 2013 | DoD Education Activity | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 3771 | 0 |  | Reflects Sequestration Reduction
2014-11-30 | 2014 | DoD Education Activity | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5409 | 0
2014-11-30 | 2007 | Missile Defense Agency | Planning and Design | Design MDA 609 - Aegis-BMD Facility Expansion, Dahlgren, VA. | 770 | 770 | 770 | Completed RFP for design-build (D-B) project.
2014-11-30 | 2009 | Missile Defense Agency | Planning and Design | Design MDA FY10-FY13 MILCON Projects | 14848 | 14839 | 14839 | Supports design of the Aegis Ashore Test Complex, East Coast Comm site, Aegis Ashore Romania site, UEWR Modifications at Clear AFS, AK and completes RFP for D-B Von Braun Complex, Phase IV.
2014-11-30 | 2010 | Missile Defense Agency | Planning and Design | Design MDA FY12-13 MILCON Projects | 7698 | 7698 | 7698 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, UEWR Modifications at Clear AFS, AK, and EUCOM Radar site. Includes $5,700,000 reprogrammed from MILCON.
2014-11-30 | 2011 | Missile Defense Agency | Planning and Design | Design MDA FY15-16 MILCON Projects | 1186 | 1186 | 0 | Funds tranferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2014-11-30 | 2012 | Missile Defense Agency | Planning and Design | Design MDA FY13-14 MILCON Projects | 8368 | 8368 | 8124 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2014-11-30 | 2013 | Missile Defense Agency | Planning and Design | Design MDA FY13-14 MILCON Projects | 4191 | 4191 | 3835 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-11-30 | 2014 | Missile Defense Agency | Planning and Design | Design MDA FY14-16 MILCON Projects | 10891 | 7816 | 5198 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-11-30 | 2009 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY12/13 | 3317 | 3117 | 3117 | Obligated funds support the EUCOM Radar Site. EUCOM work which resumed on 6 May 2013. Additional obligation of funds supports the Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping project at Fort Greely, AK
2014-11-30 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY13/14 | 2243 | 2038 | 422 | Supports the R&C Piping project at Fort Greely, AK and the Storage Facility, Meck Island. $1.186M transferred to DHA in April 2014 for swap of FY11 P&D funds. $205K returned to OSD in Sep 2014.
2014-11-30 | 2014 | Missile Defense Agency | Unspecified Minor Military Construction [UMMC] | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000 | 155 | 2 | Supports the Storage Facility, Meck Island project.
2014-11-30 | 2011 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 136314 | 136310 | 125065 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2012 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 83943 | 83693 | 79639 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2013 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 96888 | 86792 | 55736 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2014 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638 | 43583 | 33730 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2015 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 16684 | 4288 | 4267 | Appropriated Amount reflects funds allocated to date only. [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2011 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20757 | 20064 | 18673 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2012 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 20919 | 19774 | 17809 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2013 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 15612 | 13270 | 5932 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2014 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 19740 | 8415 | 0 | [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2015 | Navy Active | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 3582 | 0 | 0 | Appropriated Amount reflects funds allocated to date only. [Replaced" Navy-MC active" with "Navy Active" from the pick list for the Component field.]
2014-11-30 | 2011 | Navy Active | Planning and Design | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 2340 | 2229 | 2229
2014-11-30 | 2012 | Navy Active | Planning and Design | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2447 | 2377 | 2367
2014-11-30 | 2013 | Navy Active | Planning and Design | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609 | 682 | 641
2014-11-30 | 2014 | Navy Active | Planning and Design | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975 | 0 | 0
2014-11-30 | 2015 | Navy Active | Planning and Design | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2014-11-30 | 2011 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 853 | 744 | 741
2014-11-30 | 2012 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719 | 566 | 566
2014-11-30 | 2013 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455 | 419 | 378
2014-11-30 | 2014 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463 | 0 | 0
2014-11-30 | 2015 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2014-11-30 | 2011 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1854 | 1854 | 1854 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2012 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478 | 2148 | 2148 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2013 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995 | 1994 | 1991 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2014 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2540 | 425 | 405 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2015 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15 [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2011 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 2194 | 1632 | 1548 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2012 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 1947 | 1237 | 1171 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2013 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2014 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2015 | Navy Reserve | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | No funds yet allocated for FY15 [Replaced" Navy-MC res" with "Navy Reserve" from the pick list for the Component field.]
2014-11-30 | 2011 | Navy Active | Improvements | Military Family Housing Improvement | 27773 | 24966 | 24900
2014-11-30 | 2012 | Navy Active | Improvements | Military Family Housing Improvement | 68661 | 48120 | 43710
2014-11-30 | 2013 | Navy Active | Improvements | Military Family Housing Improvement | 42739 | 24278 | 886
2014-11-30 | 2014 | Navy Active | Improvements | Military Family Housing Improvement | 44716 | 28894 | 0
2014-11-30 | 2015 | Navy Active | Improvements | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2014-11-30 | 2011 | Marine Corps Active | Improvements | Military Family Housing Improvement | 11087 | 10771 | 10771
2014-11-30 | 2012 | Marine Corps Active | Improvements | Military Family Housing Improvement | 25327 | 23561 | 20842
2014-11-30 | 2013 | Marine Corps Active | Improvements | Military Family Housing Improvement | 17441 | 16715 | 0
2014-11-30 | 2014 | Marine Corps Active | Improvements | Military Family Housing Improvement | 24253 | 15632 | 0
2014-11-30 | 2015 | Marine Corps Active | Improvements | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2014-11-30 | 2010 | National Security Agency | Planning and Design | Generators 10 & 11 | 440 | 440 |  | MIPR 12-045 from MHS to AFCEC, $240K moved from Power & Cooling
2014-11-30 | 2010 | Special Operations Command | Planning and Design | MILCON Design Work | 4344 | 4331
2014-11-30 | 2011 | Special Operations Command | Planning and Design | MILCON Design Work | 26469 | 24853
2014-11-30 | 2012 | Special Operations Command | Planning and Design | MILCON Design Work | 30308 | 27508
2014-11-30 | 2013 | Special Operations Command | Planning and Design | MILCON Design Work | 25454 | 13300
2014-11-30 | 2014 | Special Operations Command | Planning and Design | MILCON Design Work | 36866 | 4481
2014-11-30 | 2010 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 6011 | 6010
2014-11-30 | 2011 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 7531 | 7526
2014-11-30 | 2012 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 8487 | 7997
2014-11-30 | 2013 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 9216 | 8694
2014-11-30 | 2014 | Special Operations Command | Unspecified Minor Military Construction [UMMC] | Construction Costs for UMC Projects | 5170 | 982