## PROJECTS
Data as of Date | Fiscal Year | Component | Construction Project Type | State | Country | Project Number | Project Title | Solicitation Date | Award Date | Prime Contract Recipient (Company Name) | Prime Contract Number | Original Contract Amount ($000) | Current Contract Obligation ($000) | Start Date | Placed-In-Service Date | Original Completion Date | Current Completion Date | Percent Complete | Diverted Funds Amount ($000) | Diverted Funds Recipient Project | Remarks
2014-11-05 | 2006 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR064009 | Improve Family Housing, Ph C | 2007-08-01 | 2007-12-06 | Bilfinger Berger | C 04-1006BB | 1801.8135 | 1893.4955 | 2007-12-17 |  | 2008-07-13 | 2013-02-22 | 99%
[8 empty] | 2007-08-01 | 2007-12-06 | OBG | C 04-1006OBG | 1118.3451 | 1171.5011 | 2007-12-17 |  | 2007-12-06
2014-11-05 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALDA053001B | Multi-Aircraft Maintenance Hanger | 2007-11-05 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 15238.069 | 16847.5048 | 2011-03-01 |  | 2011-10-11 | 2015-07-31 | 99%
2014-11-05 | 2008 | Air Force Active | Major Military Construction |  | QATAR | ALUA073008A | Facility Replacements | 2008-12-17 | 2010-04-19 | Rizzani de Eccher (USA) Inc. | W912ER10C0026 | 26244.838 | 28675.3487 | 2011-03-01 |  | 2011-10-11 | 2015-01-15 | 99%
2014-11-05 | 2008 | Air Force Active | Military Family Housing Improvement |  | GERMANY | TYFR084014 | Improve Family Housing, Ph E | 2012-08-21 | 2013-05-17 | MICKAN | C07-1003 | 4638.8202 | 5011.6997 | 2013-07-08 |  | 2014-05-02 | 2014-12-31 | 85%
2014-11-05 | 2008 | Air Force Active | Military Family Housing Improvement |  | TURKEY | LJYC084001 | Improve Family Housing 515 Units | 2009-04-14 | 2009-09-30 | EMTA-ILCI Joint Venture | W912GB09C0068 | 41970.0225 | 42315.6545 | 2012-03-08 |  | 2012-08-15 | 2015-07-19 | 37%
2014-11-05 | 2009 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS093002 | CNS Addition To Child Development Center (Cdc) B8210 | 2009-07-14 | 2009-08-31 | MAPCO, Inc. | W9126G09D00340002 | 5913.251 | 6604.8908 | 2009-10-15 | 2012-11-27 | 2011-02-27 | 2014-12-30 | 95%
[8 empty] | 2013-04-15 | 2013-06-15 | JSR | FA301612D00050008 | 366.5141 | 366.5141 | 2013-07-15 |  | 2013-12-27
2014-11-05 | 2009 | Air Force Active | Unspecified Minor Military Construction |  | TURKEY | AKNR041053 | CNS Replace Asf Admin Bldg 2621 | 2011-02-22 | 2011-09-23 | MATOC Contractor | W912GB09D00690007 | 1367.06 | 1367.06 | 2012-02-15 |  | 2012-09-17 | 2015-02-01 | 13%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083007 | Repair Central Heat And Power Plant Boilers, Phase 1 | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 28616.5445 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT033003 | Consol Communications Facility | 2010-06-30 | 2010-09-21 | Rand Enterprised Inc | W912BU10C0039 | 10248.94 | 11773.483 | 2011-01-03 | 2014-09-12 | 2013-09-20 | 2015-09-01 | 95%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA061726 | F-35 POL Ops Facility | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | W9127810C0074 | 4309 | 4446.688 | 2010-10-07 | 2013-09-30 | 2011-06-09 | 2014-10-31 | 99%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073902 | F-35 Hydrant Refueling System Phase 1 | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | W9127810C0074 | 9452 | 10286.6766 | 2010-10-07 | 2013-10-30 | 2011-06-09 | 2014-10-31 | 99%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073904 | F-35 JP-8 Flightline Fillstands | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc | W9127810C0074 | 3217 | 3422.26 | 2010-10-07 | 2013-10-30 | 2011-06-09 | 2014-10-31 | 99%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | FTFA073905 | F-35 JP-8 West Side Bulk Fuel Tank Upgrades | 2010-03-25 | 2010-06-09 | Mid Eastern Builders, Inc. | W9127810C0074 | 1464 | 1494.199 | 2010-10-07 | 2013-10-30 | 2011-06-09 | 2014-12-31 | 99%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | NVZR033702 | Consolidated Communications Facility | 2010-05-19 | 2010-07-07 | Carothers Construction | W9127807D00260003 | 16517.735 | 16824.4072 | 2010-08-11 | 2013-05-25 | 2013-06-21 | 2013-10-23 | 90%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD063003 | Ground Control Tower | 2010-08-13 | 2012-08-08 | RORE/ITSI JV LLC | N6274209D1186HC08 | 7379.329 | 7423.376 | 2013-02-20 |  | 2014-01-30 | 2015-01-16 | 76%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | AJXF063009 | Replace Munitions Storage Area | 2010-02-03 | 2011-04-15 | CHARTER ENVIRONMENTAL, INC. | FA890306D85030003 | 10464.83 | 10753.2604 | 2011-06-23 |  | 2013-03-05 | 2015-03-09 | 89%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG081001 | Land Acquisition North & South Boundaries | 2012-05-09 | 2012-09-12 | In-House Work Force-NWK | PN-329217-LAWAFB | 3474.5 | 3474.5 | 2012-09-12 |  | 2014-03-06 | 2014-11-28 | 85%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | MONTANA | UNITED STATES | NZAS003000A | Upgrade Weapons Storage Area | 2012-04-23 | 2012-11-28 | RSCI | W912DW13C0013 | 9474.72 | 9462.564 | 2013-12-09 |  | 2014-10-19 | 2015-02-28 | 46%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | XTLF033303 | Control Tower | 2010-05-26 | 2010-09-03 | Innovative Technical Solutions | W9126G08D0085DS01 | 8849.633 | 9518.0403 | 2010-10-05 |  | 2012-01-11 | 2014-12-04 | 84%
2014-11-05 | 2010 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R2 | Recruit Dormitory 2, Phase 2 | 2009-12-23 | 2010-04-20 | M&H Enterprises, dba Martin-Harris Construction | W9126G10C0021 | 41573.312 | 52088.9967 | 2010-05-20 | 2013-04-10 | 2012-05-23 | 2014-10-30 | 99%
[8 empty] | 2010-10-29 | 2011-01-28 | Federal Pogram Integrators, LLC with JSR Inc. | W9126G11C0009 | 6662.534 | 7474.996 | 2011-02-28 | 2013-04-10 | 2012-12-29
[8 empty] | 2012-02-15 | 2012-02-15 | American Eagle Protective Services Corp. | W9126G12C00170001 | 97.8389 | 86.71 | 2012-03-01 | 2013-04-10 | 2013-01-31
[8 empty] | 2013-06-18 | 2013-08-12 | JSR Incorporated | FA304713D00130003B | 227.6075 | 234.4318 | 2013-09-12 |  | 2014-12-31
[8 empty] | 2013-08-28 | 2013-08-29 | JSR Incorporated | W9126G12D00180022 | 98.6814 | 98.6814 | 2013-09-29 |  | 2014-01-25
2014-11-05 | 2010 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S1 | Basic Military Training Satellite Classroom/Dining Facility | 2009-11-19 | 2010-02-11 | Lyda Swinerton Builders, Inc. | W9126G10C0017 | 23483.61 | 25785.2822 | 2010-02-11 | 2012-10-31 | 2011-12-26 | 2015-09-30 | 99%
[8 empty] | 2010-05-14 | 2010-06-11 | Federal Pogram Integrators, LLC - JSR Inc. | W9126G10C0072 | 1409.452 | 1601.6059 | 2010-06-11 | 2012-10-31 | 2011-06-03
[8 empty] | 2014-09-19 | 2014-09-30 | Gideon Contracting, LLC | W9126G12C0024 | 60.931 | 60.931 | 2014-09-30 |  | 2015-09-29
2014-11-05 | 2010 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | MUHJ053008 | West & Lasalle Gates Force Protection/Access | 2010-04-07 | 2010-06-25 | Jordan/Versar, LLC | W9123608D00560006 | 7185.824 | 8498.0821 | 2010-07-07 | 2013-07-19 | 2011-12-17 | 2015-09-03 | 99%
2014-11-05 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006A | Blatchford-Preston Complex Ph II | 2010-06-03 | 2010-12-16 | Rizanni De Eccher, Joint Venture | W912ER11C0001 | 35758.85 | 37149.4231 | 2011-01-21 |  | 2013-02-03 | 2014-12-15 | 95%
2014-11-05 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA103001 | Construct Network Control Center | 2011-11-30 | 2012-07-05 | FNG-PAT Joint Venture LLC, Detroit, MI | W912ER12C0028 | 2579.93 | 3160.1562 | 2012-08-19 |  | 2013-09-08 | 2014-12-15 | 76%
2014-11-05 | 2010 | Air Force Active | Major Military Construction |  | QATAR | ALUA107000 | Coalition Compound Billeting | 2011-12-22 | 2012-04-16 | AMEC Environmental and Infrastructure, Inc. | W912ER11D00020003 | 45272.835 | 44968.0368 | 2012-06-05 |  | 2014-03-17 | 2015-03-16 | 76%
2014-11-05 | 2010 | Air Force Active | Major Military Construction |  | TURKEY | LJYC003006 | Consolidated Community Center | 2010-02-22 | 2010-03-31 | EMTA INSAAT Taah. ve Tic. A.S. | W912GB09D00690003 | 7880.644 | 8179.6972 | 2013-01-15 |  | 2011-09-22 | 2015-01-04 | 46%
2014-11-05 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100031 | Construct Maintenance Operations Center And Command Post | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1671.642 | 1986.1406 | 2011-09-19 |  | 2012-01-31 | 2015-03-31 | 93%
2014-11-05 | 2010 | Air Force Active | Major Military Construction |  | UNITED ARAB EMIRATES | DHAF100120 | Construct SatCom Facility | 2010-10-28 | 2011-05-06 | Lakeshore Engineering Services, Inc. | W912ER11C0039 | 1136.701 | 1184.0301 | 2011-09-19 |  | 2011-01-31 | 2015-03-31 | 93%
2014-11-05 | 2010 | Air Force Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | XDAT073008 | Construct Military Working Dog & Supporting Facility | 2011-07-25 | 2011-09-28 | IE PACIFIC INC | N62473-07-D-2008 | 1620 | 1620 | 2012-02-27 | 2013-02-21 | 2012-09-27 | 2013-02-22 | 99%
[8 empty] | 2014-07-18 | 2014-07-18 | CREW MW | FA442710D01022058 | 71.771 | 71.771 | 2014-07-18 |  | 2014-09-16
2014-11-05 | 2010 | Air National Guard | Major Military Construction | COLORADO | UNITED STATES | CRWU019119 | ADAL Weapon Release Facility | 2010-05-28 | 2010-09-23 | Tower One Construction Company | W912LC10C00010000 | 3.025 | 3.649 | 2010-10-27 | 2012-02-09 | 2011-08-23 | 2014-05-26 | 99%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | KANSAS | UNITED STATES | PRQE089032 | TFI - Upgrade DCGS Facilities | 2010-05-11 | 2010-08-04 | Key Construction Company | W912JC10C00040000 | 8.223 | 9.068 | 2010-08-16 | 2011-11-21 | 2011-08-16 | 2013-11-01 | 99%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | MAINE | UNITED STATES | FKNN089019 | Replace Aircraft Maintenance Hangar and Shops | 2009-09-29 | 2010-05-12 | Sheridan Corp | W912JD10C00010000 | 15.064 | 17.786 | 2010-11-05 | 2012-08-01 | 2012-11-24 | 2013-03-28 | 98% | 2200 | KNMD109501;
2014-11-05 | 2010 | Air National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | SPBN019136 | Replace Ops and Training /ADAL DGS | 2010-07-16 | 2010-09-27 | P&S Construction | W912SV10R0040 | 2.487 | 3.12 | 2010-11-01 | 2013-06-17 | 2011-10-27 | 2013-07-31 | 50%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | JTVE099057 | Force Protection Measures - Relocate Base Entrance | 2012-08-15 | 2012-09-27 | Gottfried Contracting | W9127Q09D00090005 | 3.823 | 4.11 | 2012-10-10 | 2014-06-30 | 2013-06-24 | 2014-06-30 | 56%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | MISSOURI | UNITED STATES | ULYB099003 | Add to Fire Station | 2009-09-23 | 2009-09-23 | Lee Grover Construction | W912NS1022102 | 0.293 | 0.358 | 2009-09-23 | 2014-04-30 | 2012-08-29 | 2014-05-30 | 99%
[8 empty] | 2010-03-01 | 2010-07-25 | Lee Grover Constrution | W912NS08D00100014 | 5.709 | 6.678 | 2010-08-04 | 2013-08-05 | 2011-07-30
2014-11-05 | 2010 | Air National Guard | Major Military Construction | NEBRASKA | UNITED STATES | NGCB079069 | Joint Forces Operations Center - ANG Share | 2009-11-13 | 2010-02-17 | Hausmann Construction, Inc. | W912430422013 | 1.306 | 1.5 | 2010-02-18 | 2012-09-17 | 2011-09-16 | 2012-09-17 | 98% |  |  | This projects uses a state contract executed through a Military Construction Cooperative Agreement (MCCA).
2014-11-05 | 2010 | Air National Guard | Major Military Construction | NEVADA | UNITED STATES | UCTL919637 | Replace Fire Station | 2010-07-27 | 2010-09-07 | Gilbane Building Company | W9124X10C0003 | 9.263 | 10.246 | 2010-09-23 | 2011-12-25 | 2012-03-21 | 2012-09-30 | 99%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | NEW HAMPSHIRE | UNITED STATES | SZCQ089023 | Replace Squadron Operations Facilities | 2011-03-09 | 2011-09-19 | NUTMEG Companies, Inc. | W912TF11C05030000 | 10.752 | 11.906 | 2011-10-24 | 2013-11-13 | 2013-02-15 | 2014-03-14 | 98%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | NEW YORK | UNITED STATES | FPBB069168 | Reaper LRE Beddown | 2012-07-27 | 2012-10-17 | Black Horse Group | W912PQ12D00130003 | 3.155 | 3.252 | 2012-10-17 | 2014-06-16 | 2013-11-11 | 2014-06-16 | 99%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | TENNESSEE | UNITED STATES | PYKL009136 | Base Civil Engineer Maintenance and Training Facilities | 2010-07-14 | 2010-09-21 | Chris Wood Construction Co, Inc. | W912L710C00170000 | 6.069 | 7.366 | 2010-10-19 | 2012-10-31 | 2012-10-18 | 2014-06-30 | 98%
2014-11-05 | 2010 | Air National Guard | Major Military Construction | WYOMING | UNITED STATES | DPEZ019148A | Add to Squadron Operations | 2011-02-04 | 2011-06-02 | Various Contractors | W912L311F00200000 | 0.975 | 1.303 | 2011-06-02 | 2011-08-01 | 2011-11-28 | 2014-01-31 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | ALASKA | UNITED STATES | FTQW009192 | Add to Communications Training Facility | 2012-11-07 | 2012-12-27 | G2 Construction | W91ZRU10D00150003 | 1.448 | 1.695 | 2013-01-24 | 2014-02-19 | 2014-01-24 | 2014-06-30 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | CYQL099005 | DRBS Storage Facility | 2012-10-01 | 2013-02-11 | Sweat, LLC | W911YN13C00010000 | 1.143 | 1.143 | 2013-02-11 | 2014-05-15 | 2013-11-08 | 2014-02-15 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | XDQU109096 | CRTC Squadron Operation Addition | 2012-11-13 | 2012-12-27 | Holland and Holland, Inc. | W912JM10D00010005 | 1.209 | 1.363 | 2013-01-17 | 2014-01-31 | 2014-01-17 | 2014-07-31 | 98%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | IOWA | UNITED STATES | VSSB069014 | Add To Security Forces Facility | 2013-06-19 | 2013-08-05 | H&R Construction | W912LP12D00010002 | 1.304 | 1.377 | 2013-08-15 | 2014-02-19 | 2013-08-15 | 2014-06-04 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | PJMS119034 | A10 Flight Simulator Facility | 2012-11-01 | 2013-01-08 | SAF, Inc. | W912K612R2016 | 1.818 | 1.994 | 2013-01-24 | 2014-06-04 | 2014-03-26 | 2014-06-30 | 94%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | MXRD089075 | Joint Forces Operations Center- ANG Share | 2010-02-10 | 2010-05-27 | CTA Constr | W912SV10C01010000 | 1.5 | 1.5 | 2010-05-27 | 2012-10-01 | 2010-05-27 | 2011-11-29 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | MICHIGAN | UNITED STATES | TDVG072909A | Replace Classroom Training Facilities | 2012-11-15 | 2012-12-27 | Meridan Contracting Services, LLC | W912JB09D20030013 | 1.437 | 1.608 | 2013-03-25 | 2014-01-10 | 2013-08-24 | 2014-04-10 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | NEBRASKA | UNITED STATES | NGCB109082 | Alter Base Entry Complex | 2012-10-30 | 2012-12-27 | American Contracting, LLC | W9124313B00010002 | 1.297 | 1.404 | 2013-01-23 | 2014-02-23 | 2014-01-23 | 2014-02-24 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | TWLR099087 | C-130 Parking Apron | 2013-04-08 | 2013-11-01 | TRAC Builders | W912LD11D00250004 | 1.6 | 1.688 | 2013-12-12 | 2014-09-11 | 2013-12-12 | 2014-09-11 | 42%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | TENNESSEE | UNITED STATES | BKTZ139025 | Convert RPA Interim SCIF, B720 | 2013-05-08 | 2013-06-20 | Codell Construction Company | W912L710D00060021 | 1.651 | 1.811 | 2013-07-01 | 2014-04-28 | 2014-04-16 | 2014-06-13 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | DDPM109901 | Add to Civil Engineering Facility | 2012-08-19 | 2012-11-21 | Triune-Beck JV | W912L111d00120200 | 1.479 | 1.544 | 2013-02-12 | 2014-06-13 | 2014-06-03 | 2014-06-13 | 90%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | DDPM119026 | Multi Use Training Facility | 2012-08-19 | 2012-11-21 | Tribune-Beck JV | W912L111d00120043 | 1.697 | 1.785 | 2013-02-12 | 2014-06-13 | 2013-11-30 | 2014-06-13 | 90%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | KELL099067 | F-16 Mission Training Center (Flight Sim) Facility | 2010-05-13 | 2011-09-28 | HJD Capital Electric, Inc | W912L111C0033 | 1.578 | 1.685 | 2011-09-30 | 2013-02-28 | 2012-09-29 | 2013-02-28 | 99%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | TEXAS | UNITED STATES | FPBD109001 | Add to Vehicle Maintenance Facility | 2013-06-05 | 2013-12-26 | Mirador Enterprise, Inc | W912L111D00090008 | 1.4 | 1.45 | 2014-01-06 |  | 2015-01-06 | 2015-01-25 | 22%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | LYBH079028 | BCE Pavements and Grounds Facility | 2013-02-19 | 2013-06-14 | Wycliffe Enterprises, Inc | W912L812D00080002 | 0.899 | 0.93 | 2013-07-09 | 2014-05-30 | 2014-04-05 | 2014-05-30 | 43%
2014-11-05 | 2010 | Air National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | LYBH119145 | Convert Hangar 107 for Aeromedical Relocation | 2013-07-02 | 2013-09-03 | Wycliffe Inc | W912L812D00080003 | 1.743 | 1.826 | 2013-09-16 | 2014-07-31 | 2014-10-03 | 2014-08-15 | 46%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083008 | Repair Central Heat And Power Plant Boiler | 2010-07-12 | 2011-06-02 | Haskell Corporation | W911KB11C0009 | 26981.132 | 30243.0655 | 2011-06-17 |  | 2015-01-12 | 2015-10-11 | 77%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV063501 | AMARG Hangar | 2010-12-08 | 2011-07-28 | Okland Const. Co. Salt Lake City, UT | W912PL11C0007 | 22282.136 | 23098.357 | 2011-09-12 | 2014-08-22 | 2013-07-17 | 2015-01-30 | 95%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV113002 | HC-130J Aerial Cargo Facility | 2011-02-03 | 2011-09-21 | Streeter-Summit JV Desoto/TX | W912PL11C0011 | 7223 | 7526.036 | 2011-11-09 | 2014-08-12 | 2013-03-14 | 2015-01-23 | 96% | 2000 | YWHG111005;
2014-11-05 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093000 | F-35 Academic Training Center | 2012-04-18 | 2012-08-30 | Archer Western Contractors | W912PL12C0017 | 43347.122 | 46730.2939 | 2012-11-05 |  | 2014-01-31 | 2014-11-14 | 94%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093001 | F-35 Squadron Ops Facility | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | W912PL12C0027 | 9108.814 | 9246.9817 | 2012-10-09 | 2014-01-06 | 2013-09-10 | 2014-10-31 | 99%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | COLORADO | UNITED STATES | XQPZ084017 | Const Center For Character & Leadership Development | 2012-06-06 | 2012-09-27 | Environmental Chemical Corp. | FA890306D85110091 | 24995.5 | 25002.256 | 2013-01-15 |  | 2014-06-12 | 2015-04-30 | 65%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | DELAWARE | UNITED STATES | FJXT113001 | C-5M/C-17 Maintenance Training Facility, Ph 2 | 2011-03-09 | 2011-08-02 | Asset Group, Incorporated, Oklahoma City, Oklahoma | W912BU11C0024 | 2951.817 | 2950.318 | 2012-07-02 | 2014-05-12 | 2012-08-01 | 2014-10-31 | 96%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | BXUR105000 | Joint Air Defense Operations Center | 2011-03-02 | 2011-08-05 | Sauer Inc. | N4008010D04900003 | 11978 | 14044.6439 | 2011-08-05 | 2014-02-14 | 2013-01-06 | 2014-05-14 | 98%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | SXHT053001 | Air Force Technical Applications Center | 2010-11-04 | 2011-06-03 | Hensel Phelps | W9127811C0014 | 141231.0449 | 146030.7225 | 2011-07-06 | 2014-03-03 | 2015-12-02 | 2015-12-02 | 98%
[8 empty] | 2013-09-27 | 2014-02-03 | CDA Solutions | FA252114C0001 | 99.768 | 99.768 | 2014-02-13 |  | 2014-08-02
2014-11-05 | 2011 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB025502 | Weapons Load Crew Training Facility | 2010-10-22 | 2011-08-03 | Pacific - Tech - Sauer JV | N6945011C1754 | 14996 | 16332.5158 | 2011-08-03 | 2014-08-28 | 2013-01-24 | 2014-10-31 | 99%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC113102 | UAS Airfield Fire/Crash Rescue Station | 2010-12-10 | 2011-06-29 | Jaynes Corporation | W912PL11C0004 | 7345.225 | 7423.225 | 2012-06-15 | 2014-09-30 | 2013-06-18 | 2014-11-25 | 99%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ093004 | UAS Squadron Ops Facility | 2011-04-27 | 2011-10-11 | Speegle Construction Inc | W912PP12C0003 | 11031.27 | 11268.5664 | 2012-02-16 |  | 2013-12-09 | 2014-06-03 | 99% | 3000 | YWHG111005;
2014-11-05 | 2011 | Air Force Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX913001P1 | Civil Engineer Complex (TFI) - Phase 1 | 2011-01-20 | 2011-06-03 | Sauer, Inc. | N6945009D12740008 | 11649 | 12333.8989 | 2011-06-03 |  | 2012-12-10 | 2014-03-13 | 95%
2014-11-05 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R3 | Recruit Dormitories Phase 3 | 2010-12-06 | 2011-09-20 | Satterfield & Pontikes Const Inc. | W9126G11C0024 | 45885.001 | 46354.6403 | 2011-09-20 |  | 2013-10-31 | 2014-12-30 | 98% | 4894 | KRSM103011;
[8 empty] | 2011-09-02 | 2011-11-08 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 95.464 | 95.464 | 2011-11-08 |  | 2011-12-08
[8 empty] | 2012-05-09 | 2012-05-29 | Raba-Kistner Consultants | PNASA1205700 | 1.8889 | 1.8889 | 2012-05-29 |  | 2012-06-09
[8 empty] | 2012-05-09 | 2012-08-09 | Federal Pogram Integrators, LLC - JSR Inc. | W912BV11C0038 | 6886.921 | 7267.8431 | 2012-08-09 |  | 2014-04-04
[8 empty] | 2012-09-06 | 2012-10-19 | Federal Program Integrators, LLC with JSR Inc. | W9126G11C0009 | 175.3584 | 175.3584 | 2012-10-19 |  | 2013-06-01
[8 empty] | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06
[8 empty] | 2012-02-15 | 2014-06-25 | American Eagle Protective Services Corp. | W9126G12C0017 | 97.8954 | 97.8954 | 2014-06-25 |  | 2015-01-31
[8 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00190007 | 1792.428 | 1792.428 | 2014-10-10 |  | 2015-09-05
2014-11-05 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737S2 | BMT Satellite Classrooms/Dining Facility No.2 | 2011-02-25 | 2011-06-30 | Kellogg Brown & Root Svs, Inc. | W9126G11C0027 | 25985.138 | 27504.8574 | 2011-09-05 |  | 2013-04-20 | 2014-11-10 | 97%
[8 empty] | 2012-12-12 | 2013-06-03 | Federal Pogram Integrators, LLC - JSR Inc. | W9126G13C0098 | 334.244 | 152.927 | 2013-06-03 |  | 2014-01-18
[8 empty] | 2012-02-15 | 2014-01-16 | American Eagle Protective Services Corporation | W9126G12C0017 | 97.8954 | 202.0082 | 2014-01-16 |  | 2015-01-31
2014-11-05 | 2011 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS093737V | BMT Visitors Reception Center | 2011-05-09 | 2011-09-23 | Environment Chemical Corporation (ECC) | FA890306D85110085 | 21500.479 | 21664.63 | 2012-09-19 | 2014-04-09 | 2013-09-22 | 2014-12-28 | 97%
[8 empty] | 2014-08-14 | 2014-11-10 | Red Cedar Enterprises, Inc. | W9126G14D00190007 | 498.711 | 498.711 | 2014-12-10 |  | 2015-02-10
2014-11-05 | 2011 | Air Force Active | Major Military Construction |  | ITALY | ASHE083011 | Air Support Operations Squadron (ASOS) Facility | 2011-08-29 | 2011-09-29 | Bilfinger Berger SE | N33191-07-D-0211 | 7174.1698 | 7895.7036 | 2011-12-16 |  | 2013-06-20 | 2014-09-15 | 65% | 1453 | KRSM103011;
2014-11-05 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA073006B | Blatchford-Preston Complex, Phase III | 2011-09-08 | 2012-03-26 | AMEC Environment and Infrastructure, Inc. | W912ER11D00020002 | 34177.236 | 34649.116 | 2012-09-27 |  | 2014-05-15 | 2015-09-30 | 39%
2014-11-05 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA103012 | Construct Tactical Ramp/Vehicle Maintenance Facility | 2013-01-28 | 2013-06-21 | American International Contractors Inc (Arlington, VA) | W912ER11D00010007 | 40848 | 40848 | 2013-08-07 |  | 2015-08-30 | 2015-09-16 | 1%
2014-11-05 | 2011 | Air Force Active | Major Military Construction |  | QATAR | ALUA113001 | Theater Communications Facility | 2011-11-30 | 2012-05-02 | FNG-PAT JV LLC, Detroit, MI | W912ER12C0028 | 9912.5671 | 10408.1954 | 2012-06-01 |  | 2014-04-02 | 2014-11-29 | 57%
2014-11-05 | 2011 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ114127 | Improve Family Housing, Ph 11 | 2011-05-09 | 2012-02-24 | Obayashi Corporation (Fukuoka, Japan) | FA527012C0001 | 64621.7601 | 65174.5107 | 2012-10-24 |  | 2015-08-27 | 2015-11-08 | 69%
[8 empty] | 2011-05-09 | 2012-07-01 | Environmental Science Corp (Chiyoda-Ku/Japan) *ArchTestDigs* | FA5270-12-P-0058 | 50.1855 | 50.1855 | 2012-10-24 |  | 2012-07-01
[8 empty] | 2011-05-09 | 2012-07-31 | Pioneering Technology Corp(Mississauga L4Z1S6) *Appl SafeT* | FA5270-12-P-0080 | 72.2669 | 72.2669 | 2012-10-24 |  | 2012-07-31
[8 empty] | 2011-05-09 | 2012-09-12 | Capitol Supply Inc (Sunrise, FL) **Appliances** | FA5270-12-FA-045 | 319.4136 | 319.4136 | 2012-10-24 |  | 2012-09-12
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | TYFR106261 | PL-1 Security Measures For Communications Compound | 2013-09-17 | 2013-11-13 | Mikan | C11-4014 | 1840.2888 | 1840.2888 | 2014-01-22 |  | 2014-08-10 | 2015-01-30 | 21%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | GERMANY | VYHK113003 | Catch Basin For Waste Water Treatment | 2012-04-16 | 2012-07-31 | UVB BITBURG | 113003 | 1762.2 | 1762.2 | 2012-10-01 |  | 2013-03-28 | 2014-10-30 | 90%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA110032 | Fuel Truck Parking | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1730.623 | 1730.623 | 2013-08-15 |  | 2014-11-08 | 2014-12-08 | 42%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113002 | Fuels Laboratory | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1557.438 | 1557.438 | 2013-08-15 |  | 2014-11-08 | 2014-12-08 | 42%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113005 | C-17 Spare Parts Facility | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1572.399 | 1572.399 | 2013-08-15 |  | 2014-11-08 | 2014-12-08 | 42%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113006 | High Mast Lighting | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1573.056 | 1573.056 | 2013-08-15 |  | 2014-11-08 | 2014-12-08 | 42%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113009 | Entry Control Point | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 615.612 | 615.612 | 2013-08-15 |  | 2014-11-08 | 2014-12-08 | 42%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113010 | Cryogenics Facility | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1216.4 | 1216.4 | 2013-08-15 |  | 2014-11-08 | 2014-12-08 | 42%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113012 | ELRS Storage Facility | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1615.533 | 1615.533 | 2013-08-15 |  | 2014-11-08 | 2014-12-08 | 42%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120037 | Clinic | 2013-07-18 | 2013-09-27 | Al Badeel General Contracting (Abu Dhab,i UAE) | W912BU13C0060 | 1514.583 | 1514.583 | 2014-09-29 |  | 2015-01-20 | 2015-06-24 | 5%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF120057 | Fire Protection Water Storage | 2013-07-19 | 2013-09-30 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912BU13C0055 | 1120.38 | 1120.38 | 2014-09-15 |  | 2014-11-24 | 2015-04-03 | 22%
2014-11-05 | 2011 | Air Force Active | Unspecified Minor Military Construction |  | UNITED ARAB EMIRATES | DHAF124001 | EOD Facility | 2013-07-18 | 2014-06-20 | Al Badeel General Contracting (Abu Dhabi, UAE) | W912ER14C0014 | 1044.893 | 1044.893 | 2014-08-08 |  | 2015-08-14 | 2015-09-28 | 2% |  |  | Original contract terminated for default
2014-11-05 | 2011 | Air National Guard | Major Military Construction | ALABAMA | UNITED STATES | FAKZ959574 | Fuel Cell and Corrosion Control Hangar | 2011-03-15 | 2011-07-22 | Lord and Son Constrution, Inc | W912JA11C0005 | 7.249 | 7.783 | 2011-10-12 | 2013-11-01 | 2013-01-22 | 2014-04-30 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | ARIZONA | UNITED STATES | HFHA069130 | TFI - Predator LRE Beddown | 2012-01-07 | 2013-03-15 | Ace Engineering, Inc. | W912L213C0001 | 9.434 | 10.25 | 2013-04-08 | 2014-07-02 | 2014-06-02 | 2014-06-02 | 62%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | DELAWARE | UNITED STATES | JLWS079103 | Joint Forces Operations Center - ANG Share | 2011-06-29 | 2011-09-16 | Vigil Contracting, Inc. | W912L511B0001 | 1.134 | 1.164 | 2011-12-12 | 2014-01-31 | 2013-06-09 | 2014-01-31 | 98%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | FLORIDA | UNITED STATES | LSGA029009A | Security Forces Training Facility | 2010-11-12 | 2011-06-06 | Americaan Patriot Construction -IMC, LLC | W911YN11C00030000 | 3.909 | 4.2 | 2011-08-05 | 2013-04-08 | 2012-12-03 | 2014-08-29 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069209 | TFI - F-22 Hangar, Squadron Operations and AMU | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | W912J611C00020000 | 37.11 | 43.051 | 2011-07-15 | 2014-01-10 | 2013-07-14 | 2014-04-08 | 98% | 2001 | KNMD069215;
2014-11-05 | 2011 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069215 | TFI - F-22 Upgrade Munitions Complex | 2012-01-11 | 2012-05-24 | Nan Inc. | W912J612C00010000 | 17.142 | 20.85 | 2012-06-14 | 2014-03-14 | 2013-12-11 | 2014-03-31 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD109500 | TFI - F-22 Beddown Infrastructure Support | 2011-01-04 | 2011-06-28 | Fed Con 1 - JV (Watts and Bullrush) | W912J611C00020000 | 5.155 | 6.794 | 2011-08-15 | 2014-01-10 | 2013-07-14 | 2013-11-23 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | ILLINOIS | UNITED STATES | DCFT069059 | TFI - cNAF Beddown - Upgrade Facilities | 2010-12-15 | 2012-04-26 | JM Industrial Supply, Inc. | W91SMC12C00030000 | 13.733 | 15.077 | 2012-06-01 | 2014-02-21 | 2013-03-20 | 2014-02-21 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | MARYLAND | UNITED STATES | PJMS909928 | Replace Operations and Medical Training Facility | 2011-08-17 | 2011-09-28 | Costello Construction of MD, Inc. | W912K611C0016 | 11.802 | 13.263 | 2012-07-20 | 2014-02-28 | 2013-10-18 | 2014-07-15 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | NEW YORK | UNITED STATES | FPBB109013 | TFI - Reaper Infrastructure Support | 2012-07-27 | 2012-10-17 | Black Horse Group | W912PQ12D00130003 | 2.04 | 2.196 | 2012-10-17 | 2014-06-16 | 2013-10-12 | 2014-06-16 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | NEW YORK | UNITED STATES | WHAY089079 | Base Defense Group Beddown | 2011-07-30 | 2011-09-23 | APS Contractors Inc | W912PQ11B00040004 | 13.401 | 14.451 | 2011-10-13 | 2014-05-15 | 2013-05-05 | 2014-06-30 | 95%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | NORTH CAROLINA | UNITED STATES | WEFM089029 | Upgrade ASOS Facilities | 2011-04-19 | 2011-08-26 | DOT Construction | W9124209D00010904 | 1.66 | 1.873 | 2011-10-24 | 2013-03-25 | 2012-07-21 | 2014-06-07 | 99%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | TENNESSEE | UNITED STATES | BKTZ069078 | TFI- Renovate Intel Squadron Facilities | 2013-09-20 | 2013-11-21 | Codell Construction Company | W912L710D00060037 | 6.074 | 6.592 | 2013-12-02 | 2014-09-29 | 2014-10-17 | 2014-10-17 | 0%
2014-11-05 | 2011 | Air National Guard | Major Military Construction | TEXAS | UNITED STATES | FWJH069194 | TFI - Alter UAV Maintenance Hangar (Bldg 1382) | 2012-01-06 | 2012-06-14 | LeeTex Construction | W912L112C0012 | 5.038 | 5.938 | 2012-07-23 | 2014-07-01 | 2013-07-23 | 2014-07-01 | 93%
2014-11-05 | 2011 | Air National Guard | Unspecified Minor Military Construction | HAWAII | UNITED STATES | KNMD109032 | TFI- F-22 Beddown- Add to Communication Facility | 2012-01-04 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C00030000 | 1.695 | 1.952 | 2012-06-17 | 2014-04-15 | 2014-06-07 | 2014-08-17 | 99%
2014-11-05 | 2011 | Air National Guard | Unspecified Minor Military Construction | WYOMING | UNITED STATES | DPEZ089083 | Relocate ROSC | 2011-07-18 | 2012-04-11 | Recco, Inc. | W912L312C0003 | 1.636 | 1.953 | 2012-04-25 | 2013-07-31 | 2012-10-22 | 2014-06-30 | 99%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FTQW083005 | Dormitory (168 RM) | 2014-03-25 | 2014-08-13 | Absher-Bether JV | W911KB14C0024 | 33061.944 | 33061.944 | 2014-08-26 |  | 2016-08-02 | 2016-08-15 | 2%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | ALASKA | UNITED STATES | FXSB061561 | Brigade Combat Team (Light) Complex, (480 RM) | 2011-11-14 | 2012-06-07 | Kiewit Building Group, Inc. ; Omaha, NE | W911KB12C0011 | 53805.3 | 56108.943 | 2012-06-19 |  | 2014-06-19 | 2015-03-16 | 66% | 19165 | ALUA073006B; YWHG111005; WWYK143004A; ZHTV053302;
[8 empty] | 2011-11-14 | 2012-06-12 | ASRC Civil Construction LLC ; Anchorage, AK | FA500012D00030006 | 3230.2925 | 3230.2925 | 2012-06-26 |  | 2013-09-27
[8 empty] | 2011-11-14 | 2012-06-19 | Frawner Corporation ; Anchorage, AK | FA500011D00020009 | 4978.8077 | 4978.8077 | 2012-06-26 |  | 2013-08-28
[8 empty] | 2011-11-14 | 2012-06-22 | Advanced Blasting Services, LLC ; Wasilla, AK | W911KB12C0018 | 1874.106 | 2191.91 | 2012-07-02 |  | 2012-11-20
[8 empty] | 2011-11-14 | 2012-07-27 | Honeywell Inc. Morristown, NJ | DACA8797D00640008 | 1799.2288 | 1799.2288 | 2012-07-27 |  | 2013-01-23
2014-11-05 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV103006P1 | EC-130H Simulator/Training Operations | 2012-04-10 | 2012-09-13 | Record Steel and Construction, Inc Meridian, ID | W912PL12C0011 | 14347.6 | 14438.88 | 2013-02-10 | 2014-08-28 | 2014-03-07 | 2015-01-23 | 99% | 4333 | WWYK143004A; LKTC093101;
2014-11-05 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | FBNV123002 | HC-130J Joint Use Fuel Cell | 2012-03-14 | 2012-09-20 | Creative Times, Inc / Ogden / Utah | W912PL12C0018 | 12361 | 12415.286 | 2013-01-10 |  | 2014-03-14 | 2014-11-15 | 86%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120010 | F-35 ADAL Aircraft Maintenance Unit | 2012-04-26 | 2012-09-10 | RENEW-MASON & HANGER JV | W912PL12C0027 | 4781.113 | 4980.026 | 2012-10-09 | 2014-01-06 | 2013-09-10 | 2014-12-31 | 99%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | AETC120011 | F-35 Squad Ops/AMU 2 | 2012-06-07 | 2013-03-07 | Speegle Construction Inc, Niceville, FL | W912PL13C0006 | 12358.5 | 12799.937 | 2013-10-08 |  | 2014-08-29 | 2014-12-16 | 80%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | AJJY983202 | Air Freight Terminal Complex | 2012-02-17 | 2012-06-29 | DCK-ECC Pacific Guam, LLC | N6274210D1308JQ01 | 30047.253 | 32363.6898 | 2012-07-18 |  | 2014-05-14 | 2015-03-02 | 85%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | GUAM | GUAM | SAKW059101 | PRTC - Red Horse Cantonment Operations Facility | 2011-12-30 | 2012-04-28 | Pacific West Builders | N4019210D28100003 | 9490.73 | 9433.61 | 2012-05-14 | 2014-08-15 | 2013-10-07 | 2014-11-21 | 99% | 2100 | ZHTV053302;
2014-11-05 | 2012 | Air Force Active | Major Military Construction | LOUISIANA | UNITED STATES | AWUB105002 | Mission Support Group Complex | 2011-11-30 | 2012-03-26 | Gaskins Construction Company | N6945009D12700002 | 17998 | 18551.6272 | 2012-03-26 |  | 2013-09-17 | 2014-11-14 | 99%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG071005 | WSA Security Control Facility | 2011-11-23 | 2012-02-27 | Carlson Constructors | W912DQ11D40160002 | 4172.6 | 4300.1692 | 2012-03-16 | 2014-08-15 | 2013-08-20 | 2015-08-15 | 98%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111005 | Force Support Squadron Facility | 2012-06-01 | 2012-08-23 | Titan Construction Organizatio | W912DQ11D40150001 | 5388.481 | 5625.923 | 2012-09-10 | 2013-09-30 | 2013-09-10 | 2014-11-14 | 99%
[8 empty] | 2013-08-23 | 2013-12-18 | Mack Mechanical, Inc. | W912DQ14C4000 | 1814.472 | 1886.816 | 2014-01-27 |  | 2014-09-24
2014-11-05 | 2012 | Air Force Active | Major Military Construction | NEBRASKA | UNITED STATES | SGBP100904C | USSTRATCOM Replacement Facility - Incr 1 | 2011-08-02 | 2012-08-16 | KiewitPhelps JV Omaha NE | W9128F12C0023 | 102754.426 | 102442.3087 | 2012-10-15 |  | 2016-08-15 | 2016-09-12 | 29%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103003 | Communications Network Control Center | 2011-11-17 | 2012-04-24 | A4 Construction | W912PL12C0008 | 9326.701 | 9525.511 | 2012-12-01 | 2014-05-01 | 2014-04-24 | 2014-12-15 | 95% | 800 | ZHTV053302;
2014-11-05 | 2012 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103010 | F-35 Add/Alter Engine Shop | 2011-11-17 | 2012-05-24 | Au Authum KI, Inc | W912PL10D01090001 | 1866.78 | 1866.78 | 2014-01-15 | 2014-09-02 | 2014-09-11 | 2014-11-21 | 99% | 572 | WWYK143004A;
2014-11-05 | 2012 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV093108 | AFNWC Sustainment Center | 2012-01-04 | 2012-06-12 | KL House Construction/Albuqueque/nm | W912PP12C0016 | 21110 | 21507.2863 | 2012-07-09 |  | 2014-04-03 | 2014-12-15 | 98% | 1100 | ZHTV053302;
2014-11-05 | 2012 | Air Force Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH083003 | C-130 Flight Simulator | 2012-02-06 | 2012-06-20 | JAAAT Technical Services LLC | W912HN10D00630003 | 4630 | 4712.131 | 2013-04-30 |  | 2013-12-12 | 2014-12-29 | 86%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092012 | B-52 Two-Bay Phase Maintenance Dock | 2012-01-17 | 2012-04-19 | PCL Construction Services, Inc. | W9128F12C0013 | 32123.257 | 33407.635 | 2012-05-22 |  | 2014-09-06 | 2014-12-14 | 95%
2014-11-05 | 2012 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083737R4 | BMT Recruit Dormitory, Phase IV | 2013-03-18 | 2013-06-03 | Federal Program Integrators, LLC with JSR Inc. | W9126G13C0098 | 91.85 | 91.85 | 2013-06-03 |  | 2013-11-06 | 2015-01-11 | 57%
[8 empty] | 2011-12-16 | 2013-07-17 | Spawglass Contractors Inc. | W9126G12C0023 | 50528.593 | 52100.097 | 2013-07-17 |  | 2014-11-26
[8 empty] | 2014-08-14 | 2014-10-10 | Red Cedar Enterprises, Inc. | W9126G14D00J190007 | 6732.163 | 7301.64 | 2014-10-10 |  | 2016-01-03
2014-11-05 | 2012 | Air Force Active | Major Military Construction | VIRGINIA | UNITED STATES | WACC120007 | AIT Barracks Complex, Ph 2 | 2012-01-19 | 2012-09-27 | Purcell Construction Corp | W9123608D00140003 | 33915.149 | 34107.6364 | 2012-10-15 |  | 2014-09-19 | 2014-11-19 | 98% | 10112 | WWYK143004A; LKTC093101; ZHTV053302;
2014-11-05 | 2012 | Air Force Active | Major Military Construction | WASHINGTON | UNITED STATES | GJKZ860009 | Wing Headquarters | 2011-12-05 | 2012-04-25 | Jackson Controactor Grp, Inc, Missoula, MT | W912DW12C0030 | 11957.25 | 12236.213 | 2013-03-18 | 2014-03-07 | 2013-12-26 | 2014-11-10 | 96%
2014-11-05 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17001 | Aircraft Apron/Taxiway And Maintenance Shelters | 2012-01-12 | 2012-05-02 | United Infrastructure Projects | N3319109D01200011 | 6740.135 | 6640.535 | 2012-05-15 | 2014-02-02 | 2013-01-27 | 2014-11-30 | 99%
2014-11-05 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17002 | Combat Aircraft Loading Area | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 43421 | 43728.4594 | 2012-12-24 |  | 2013-12-26 | 2015-03-12 | 49%
2014-11-05 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17003 | Parallel Taxiway Extension | 2012-04-30 | 2012-09-10 | CH2MHill-METAG JV | N6247012C2008 | 10521.53 | 10521.53 | 2012-12-24 |  | 2014-05-03 | 2015-04-23 | 31%
2014-11-05 | 2012 | Air Force Active | Major Military Construction |  | DJIBOUTI | USAFE17004 | Expeditionary Lodging | 2012-05-30 | 2012-09-26 | Tetra Tech EC, Inc. | N3319112C0614 | 26587.915 | 27299.359 | 2013-03-15 |  | 2014-03-20 | 2015-01-09 | 86%
2014-11-05 | 2012 | Air Force Active | Major Military Construction |  | GERMANY | TYFR063017 | Dormitory (192 RM) | 2012-03-29 | 2012-05-24 | LBB (EBC AWD) | W912GB11C0013 | 29541.6935 | 29541.6935 | 2014-07-01 |  | 2013-11-15 | 2015-09-15 | 1% | 1624 | WWYK143004A; ZHTV053302;
2014-11-05 | 2012 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103033 | Dormitory (72 PN) | 2011-12-05 | 2012-05-11 | MTHojgaard | W912DS12C0012 | 27935.945 | 27907.4832 | 2012-06-13 | 2014-09-26 | 2014-05-01 | 2014-10-17 | 99%
2014-11-05 | 2012 | Air Force Active | Major Military Construction |  | ITALY | ASHE163000 | Child Development Center Addition | 2012-06-06 | 2012-09-30 | Collodetto Angelo Costruzioni | N3319112R06220002 | 890.2326 | 910.2126 | 2013-04-01 |  | 2013-12-29 | 2014-07-17 | 80%
2014-11-05 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ124285 | Improve Family Housing Infrastructure, Ph 1 | 2012-05-11 | 2012-11-06 | American Engineering Corporation-Ginowan City, Okinawa, JAP | FA527013C0006 | 17706.6686 | 17706.6686 | 2013-06-04 |  | 2015-10-13 | 2015-11-20 | 58%
2014-11-05 | 2012 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA124002 | Improve MFH Infrastructure, Phase 1 | 2012-01-05 | 2012-05-04 | Hibiya Engineering, Ltd | W912HV12C0003 | 19550.171 | 20009.1332 | 2012-07-31 |  | 2014-10-21 | 2014-11-13 | 96%
2014-11-05 | 2012 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | AGGN123002P | Communications Network Control Center Consolidation | 2013-03-22 | 2013-12-23 | Kothane Enterprises | FA441914C0101 | 1619.1715 | 1619.1715 | 2014-03-10 |  | 2014-10-03 | 2014-12-19 | 46%
2014-11-05 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113026 | C-130 Aircraft Maintenance Unit | 2013-04-22 | 2013-08-15 | PAT USA, Inc. | W912ER13C0027 | 1511.518 | 1511.518 | 2013-09-12 |  | 2014-11-08 | 2015-04-07 | 23%
2014-11-05 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113027 | Air Defense Artillery Maintenance Facility | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1265.194 | 1265.194 | 2013-08-28 |  | 2014-08-19 | 2015-06-19 | 21%
2014-11-05 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113032 | Precision Measurement Equipment Laboratory | 2013-02-22 | 2013-06-10 | Gulf Supplies and Construction Services | W912ER13C0023 | 1403.744 | 1409.0421 | 2013-08-28 |  | 2014-12-02 | 2015-07-24 | 21%
2014-11-05 | 2012 | Air Force Active | Unspecified Minor Military Construction |  | QATAR | ALUA113034 | AFOSI Regional And Local Facility | 2013-02-22 | 2013-07-23 | Gulf Supplies & Commercial Services | W912ER13C0023 | 1214.606 | 1214.606 | 2013-08-28 |  | 2015-01-14 | 2015-02-19 | 21%
2014-11-05 | 2012 | Air Force Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | PDPG020143 | Construct New Airfield Control Tower, B1295 & Base Op'S B395 | 2012-03-16 | 2012-07-26 | Flintco, LLC. | W912QR12C0048 | 16915 | 17335.163 | 2012-08-22 | 2014-06-23 | 2014-12-16 | 2015-01-22 | 98%
2014-11-05 | 2012 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ120572 | Vehicle Maintenance Facility | 2013-01-04 | 2014-08-22 | Oddo Construction Services | FA667014C0002 | 2087.131 | 2087.131 | 2014-09-22 |  | 2016-02-13 | 2017-02-28 | 2%
2014-11-05 | 2012 | Air Force Reserve | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DKFX079003 | Red Horse Readiness And Training Facility | 2012-02-08 | 2012-07-13 | IKHANA | N6945012C1760 | 8149 | 9004.77 | 2012-07-13 |  | 2013-07-13 | 2014-12-15 | 92%
2014-11-05 | 2012 | Air Force Reserve | Unspecified Minor Military Construction | UTAH | UNITED STATES | KRSM099001 | Fire Station #4 Annex | 2013-06-11 | 2013-09-25 | Grand Enterprises, LLC | FA820112D00250004 | 1322.061 | 1392.139 | 2013-10-11 | 2014-08-22 | 2014-05-28 | 2014-11-01 | 98%
2014-11-05 | 2012 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY029154 | Wing Operations and Training Facility | 2012-07-27 | 2012-09-26 | SM Construction | W912LA12C00080000 | 4.96 | 5.48 | 2012-12-03 | 2014-06-16 | 2013-12-03 | 2014-06-13 | 95%
2014-11-05 | 2012 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | QMSN019029 | Replace Pararescue Training Facility | 2012-08-05 | 2012-09-26 | Flintco Construction | W912LA12C7025 | 25.161 | 27.749 | 2013-01-10 | 2014-08-15 | 2014-04-10 | 2014-08-14 | 74%
2014-11-05 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069212 | TFI - F-22 Flight Simulator Facility | 2012-01-20 | 2012-06-12 | HAKO PLUMBING, INC. | W912J612C00030000 | 18.842 | 21.659 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 81%
2014-11-05 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069213 | TFI - F-22 Weapons Load Crew Training Facility | 2012-01-20 | 2012-06-12 | HAKO PLUMBING INC | W912J612C00030000 | 6.473 | 7.944 | 2012-06-17 | 2014-06-07 | 2014-06-07 | 2014-06-07 | 75%
2014-11-05 | 2012 | Air National Guard | Major Military Construction | HAWAII | UNITED STATES | KNMD069216 | TFI - F-22 Combat Aircraft Parking Apron | 2012-01-04 | 2012-07-13 | Cutting Edge Concrete Services Inc. | W9128A12C00070000 | 9.682 | 10.875 | 2012-08-08 | 2013-11-18 | 2013-08-08 | 2015-03-29 | 70%
[8 empty] | 2013-03-04 | 2013-09-12 | Nan, Inc | W912J613C00060000 | 2 | 2 | 2013-09-30 |  | 2015-03-29
2014-11-05 | 2012 | Air National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | SPBN079047 | TFI - cNAF Beddown - Upgrade Facilities | 2013-05-08 | 2013-08-29 | Maron Construction Co. | W912SV13C00030000 | 7.919 | 8.226 | 2013-09-24 |  | 2013-09-28 | 2015-02-11 | 26%
2014-11-05 | 2012 | Air National Guard | Major Military Construction | OHIO | UNITED STATES | WAAR109001 | Alter Predator Operations Center Facility | 2012-08-17 | 2012-09-26 | UTS-DAG Construction Co., LLC | W9136412C00460000 | 5.296 | 7.09 | 2012-12-05 | 2013-10-31 | 2013-11-01 | 2014-06-15 | 99%
2014-11-05 | 2012 | Air National Guard | Unspecified Minor Military Construction | ALASKA | UNITED STATES | FXSB121354 | Construct Aerospace Support Equipment Storage Facility | 2013-07-31 | 2013-09-27 | H. Watt & Scott | W91ZRU10D00060011 | 1.088 | 1.088 | 2013-10-02 | 2014-08-24 | 2014-03-01 | 2014-08-24 | 20%
2014-11-05 | 2012 | Air National Guard | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | XDQU129062 | Vehicle Maintenance Addition | 2012-05-24 | 2012-08-17 | Tyler Construction Group, Inc. | W912JM10D00040001 | 1.5 | 1.5 | 2012-08-17 | 2013-09-30 | 2013-02-13 | 2014-05-31 | 99%
2014-11-05 | 2012 | Air National Guard | Unspecified Minor Military Construction | MAINE | UNITED STATES | FKNN049094 | Pavements and Grounds Facility | 2012-05-16 | 2012-09-12 | Cornerstone Construction | W912JD11D00070003 | 1.277 | 1.329 | 2012-09-19 | 2013-11-25 | 2013-03-18 | 2014-07-01 | 99%
2014-11-05 | 2012 | Air National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | AXQD119004 | Add to and Alter Survival Equipment Shop | 2013-04-10 | 2013-07-12 | Cornerstone Construction Svs | W912SV10D00080004 | 1.19 | 1.241 | 2013-07-16 | 2014-05-23 | 2014-02-07 | 2014-05-30 | 95%
2014-11-05 | 2012 | Air National Guard | Unspecified Minor Military Construction | OHIO | UNITED STATES | WAAR129078 | Relocate Main Gate | 2013-06-13 | 2013-08-14 | Lewaro/Butt JV | W9136413D00050002 | 1.713 | 1.884 | 2013-08-27 | 2014-05-22 | 2014-03-12 | 2014-05-22 | 84%
2014-11-05 | 2012 | Air National Guard | Unspecified Minor Military Construction | OREGON | UNITED STATES | KJAQ119031 | Addition Squadron Operations Facility | 2013-10-08 | 2014-01-29 | Anthem Builders, Inc | W912JV14C00020000 | 1.678 | 1.76 | 2014-03-12 |  | 2014-11-10 | 2014-12-19 | 12%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK103006 | C-130J Fuel Systems Maintenance Hangar | 2012-11-15 | 2013-06-25 | The Ross Group | W9127S13C6002 | 20869 | 20869 | 2013-07-23 |  | 2015-06-25 | 2015-07-23 | 36%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | ARKANSAS | UNITED STATES | NKAK113005 | C-130J Flight Simulator Addition | 2014-07-09 | 2014-09-24 | Alesssi Keys Construction | W9127S14C0011 | 4218.503 | 4218.503 | 2014-10-24 |  | 2015-09-24 | 2015-10-26 | 1%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY133001 | Civil Engineer Administration/Operations Facility | 2014-02-19 | 2014-06-10 | Macnak Korte Group LLC, Lakewood, WA | W9123814C0039 | 15947.269 | 15947.269 | 2014-07-09 |  | 2016-03-01 | 2016-03-30 | 2%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | FLORIDA | UNITED STATES | XLWU103002 | F-22 Add/Alt Hangar For Low Observable/Composite Repair | 2013-01-09 | 2013-05-31 | Barlovento | W9127810D00780006 | 13298.609 | 13356.965 | 2013-08-21 |  | 2015-05-21 | 2015-02-11 | 74%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | QSEU103008 | HC-130J Simulator Facility | 2012-12-07 | 2013-06-28 | IBKI, Inc. Choctaw, MS | W912HN13C0011 | 7692.387 | 7805.965 | 2013-08-12 |  | 2014-11-20 | 2015-04-15 | 92%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | GEORGIA | UNITED STATES | ACC123184 | Air Support Operations Center | 2013-03-14 | 2013-09-24 | Better Built Construction Serv | W912HN10D00530003 | 6458 | 6458 | 2013-11-07 |  | 2015-03-18 | 2015-05-01 | 17%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC133101 | RPA Mission Complex Physical Protection System | 2014-02-25 | 2014-07-24 | Cobblestone Construction | W912PL14C0012 | 10643.42 | 10643.42 | 2014-08-19 |  | 2015-07-24 | 2015-09-01 | 2%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | KWRD123004 | MQ-9 Maintenance Hangar | 2013-03-01 | 2013-06-17 | HEW-Phelps | W912PP13C0019 | 20620 | 20726.768 | 2013-08-30 |  | 2015-03-09 | 2014-12-30 | 92%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092011 | B-52 Add/Alter Munitions Age Facility | 2012-11-19 | 2013-05-31 | Rolac Contracting, Inc. | W9128F13C0008 | 4376.727 | 4260.351 | 2013-06-19 |  | 2014-11-22 | 2014-12-11 | 48%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | MPLS083008 | Dormitory (96 Rm) | 2013-04-04 | 2013-09-13 | Earthworks Mortensen JV | W9126G13C0016 | 17170.185 | 17170.185 | 2014-03-15 |  | 2015-03-07 | 2015-06-25 | 18%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103012 | F-35 Adal Hangar 45W/AMU | 2013-07-22 | 2013-12-20 | Creative Times, Inc., Ogden, UT | W912PL14C0005 | 6781 | 6934.456 | 2014-01-27 |  | 2015-06-13 | 2015-08-15 | 19%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103030 | F-35A Modular Storage Magazines | 2012-08-08 | 2013-12-17 | Zumwalt Construction, Inc. | W9123811D00260006 | 2028.458 | 2033.5187 | 2014-01-27 |  | 2015-06-10 | 2015-10-25 | 9%
2014-11-05 | 2013 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM113028 | F-35 Adal Building 118 For Flight Simulator | 2012-08-08 | 2013-12-17 | Creative Times, Inc. (CTI) | W9123811D00240002 | 3878.926 | 3888.2676 | 2014-01-29 |  | 2015-02-15 | 2015-04-30 | 26%
2014-11-05 | 2013 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103032 | Dormitory (48 Pn) | 2012-12-14 | 2013-05-31 | Pilegaard-Henriksen | W912DS13C0030 | 23031.649 | 23031.649 | 2013-08-15 |  | 2015-05-21 | 2015-07-29 | 43%
2014-11-05 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ134286 | Improve Family Housing Infrastructure, Ph 2 | 2013-01-17 | 2013-07-18 | Tokyu Construction Co., Ltd. (Tokyo, Japan) | W912HV13C0004 | 14698.0727 | 14787.5107 | 2013-08-29 |  | 2015-10-16 | 2016-01-04 | 19%
2014-11-05 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA133001P2 | Improve Family Housing, Ph 2 | 2013-05-16 | 2013-09-30 | Nishimatsu Construction Co., Ltd | FZ520513C0005 | 13989.4156 | 13746.0243 | 2013-10-29 |  | 2015-05-23 | 2015-05-22 | 63%
2014-11-05 | 2013 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA134001 | Improve Mfh Infrastructure, Phase 2 | 2013-04-24 | 2013-09-28 | Tokyu Construction Co., Ltd | FZ520513C0006 | 15336.739 | 14803.5238 | 2013-10-23 |  | 2015-08-29 | 2015-08-31 | 34%
2014-11-05 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | FBNV133500 | T-10 Engine Test Cell (AMARG) | 2013-11-13 | 2014-07-08 | J.I. GARCIA CONSTRUCTION | W912PL10D0110 | 1795 | 1795 | 2014-08-12 |  | 2015-05-04 | 2015-08-04 | 10%
2014-11-05 | 2013 | Air Force Active | Unspecified Minor Military Construction | ARKANSAS | UNITED STATES | NKAK113003 | C130J Propeller Repair Training Facility | 2013-11-19 | 2014-02-21 | HGL Construction | FA446011D00075014 | 727 | 727 | 2014-06-20 |  | 2015-02-21 | 2015-02-20 | 1%
2014-11-05 | 2013 | Air Force Active | Unspecified Minor Military Construction | OKLAHOMA | UNITED STATES | WWYK120123A | Correct Life Safety Code Deficiencies, Bldg 282 | 2013-03-06 | 2013-05-23 | Southwind Construction | W912BV12D00180003 | 1525.212 | 1525.212 | 2013-06-07 |  | 2015-07-19 | 2015-08-03 | 66%
2014-11-05 | 2013 | Air Force Reserve | Major Military Construction | NEW YORK | UNITED STATES | RVKQ099095 | Flight Simulator Facility | 2013-12-16 | 2014-03-27 | SCMS, LLC | W912QR14C0012 | 5242.986 | 5242.986 | 2014-08-05 |  | 2015-09-18 | 2016-01-15 | 2%
2014-11-05 | 2013 | Air Force Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | KYJM129022 | Add Simulator Bay, Building 191 | 2013-06-07 | 2013-09-23 | CCI | W9127810D001180020 | 1552.029 | 1591.6019 | 2013-12-16 |  | 2014-07-07 | 2015-01-23 | 65%
2014-11-05 | 2013 | Air National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | HAYW109006 | F-15 Conversion | 2013-08-23 | 2013-09-27 | RS Morris Construction | W912LA11D00180010 | 3.747 | 4.055 | 2013-11-01 |  | 2015-01-25 | 2015-06-23 | 0%
[8 empty] | 2013-08-23 | 2013-09-30 | RS Morris Cosntruction | W912LA11D00180011 | 2.402 | 2.575 | 2013-11-01 |  | 2015-01-25
2014-11-05 | 2013 | Air National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV119001 | Alter Target Intelligence Facility | 2013-05-22 | 2013-10-10 | K.L. HOUSE CONSTRUCTION CO. | W912J314C10010000 | 4.569 | 5.026 | 2014-01-27 |  | 2015-01-27 | 2015-02-23 | 13%
2014-11-05 | 2013 | Air National Guard | Major Military Construction | WYOMING | UNITED STATES | DPEZ089017 | C-130 Flight Simulator Training Facility | 2013-08-28 | 2013-09-27 | Faith Enterprises | W912L313D0003 | 5.062 | 5.294 | 2013-09-27 |  | 2015-03-21 | 2015-03-21 | 5%
2014-11-05 | 2013 | Air National Guard | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | FJRP079016 | BCE pavements and Grounds Facility | 2013-12-23 | 2014-04-07 | Showalter Construction | W9124209D0013N908 | 1.22 | 1.258 | 2014-06-01 |  | 2015-03-03 | 2015-03-28 | 1%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093007 | Construct Addition, Field Training Facility, B936 | 2013-11-15 | 2014-03-28 | Candelaria Corp | W912PL10D01080004 | 4699.907 | 4699.907 | 2014-04-23 |  | 2015-06-11 | 2015-07-07 | 7%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | ARIZONA | UNITED STATES | NUEX093011 | Construct Squadron Operations/Aircraft Maintenance Unit (#3) | 2013-11-22 | 2014-05-21 | Okland Construction Company | W912PL14C0007 | 15513.636 | 15513.636 | 2014-06-24 |  | 2016-01-11 | 2016-02-14 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | CALIFORNIA | UNITED STATES | BAEY143000 | Distributed Common Ground Station (DCGS) Operations Facility | 2014-04-22 | 2014-08-07 | Swinerton Builders,Arvada,CO | W9123814C0046 | 53699.643 | 53699.643 | 2014-08-27 |  | 2016-10-15 | 2017-02-21 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | GUAM | UNITED STATES | AJJY143760 | Hardened Structures For POL Fuel Systems | 2014-07-30 | 2014-10-07 | P&S Construction Inc. | N4019210D28040020 | 17907.7 | 17907.7 | 2014-12-01 |  | 2016-03-30 | 2017-04-15 | 1%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | GUAM | UNITED STATES | AJJY153011 | Guam Strike Tactical Missile Maintenance Facility | 2014-01-07 | 2014-09-29 | AIC International, Inc. | N6274214C1318 | 6177.269 | 6177.269 | 2014-10-24 |  | 2016-07-20 | 2016-07-20 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | HAWAII | UNITED STATES | KNMD142222 | C-17 Modernize Hangar 35, Docks 1 and 2 | 2013-11-18 | 2014-06-17 | SRB International LLC | N6274214C1312 | 2699 | 2699 | 2014-08-21 |  | 2015-05-08 | 2015-06-07 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145117 | KC-46A 2-Bay Corrosion/Fuel Hangar | 2014-02-14 | 2014-05-22 | Archer Western Aviation Part | W912DQ14C4006 | 63924.5 | 63924.5 | 2014-06-24 |  | 2015-12-03 | 2017-01-05 | 4% | 10500 | SGBP100904C;
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145136 | KC-46A Alter Apron Fuels Distribution Systems | 2014-03-13 | 2014-05-28 | MEB General Contractors, INC | W912DQ14C4010 | 8100.5 | 8100.5 | 2014-09-02 |  | 2015-11-19 | 2015-12-17 | 13% | 2500 | SGBP100904C;
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145137 | KC-46A Alter Miscellaneous Facilities | 2014-03-10 | 2014-06-27 | Red Cedar Enterprises, Inc | W912DQ13D40010002 | 838.705 | 838.705 | 2014-07-12 |  | 2015-02-22 | 2015-03-14 | 53%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145138 | KC-46A Alter Aircraft Parking Apron | 2014-03-03 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 976 | 976 | 2014-08-18 |  | 2017-02-06 | 2016-06-24 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE145142 | KC-46A 1-Bay Maintenance Hangar | 2014-02-14 | 2014-05-23 | Archer Western Aviation Part | W912DQ14C4006 | 25200 | 25200 | 2014-09-19 |  | 2016-12-18 | 2016-05-27 | 1% | 3000 | SGBP100904C;
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155119 | KC-46A 3-Bay General Purpose Maintenance Hangar | 2014-02-14 | 2014-05-23 | Archer Western Aviation Partn | W912DQ14C4006 | 53959 | 53959 | 2014-06-24 |  | 2015-11-24 | 2017-05-27 | 2% | 19000 | SGBP100904C;
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KANSAS | UNITED STATES | PRQE155122 | KC-46A Pipeline Student Dormitory (48PN) | 2014-03-24 | 2014-09-23 | PentaCon | W912DQ14C4021 | 7306.162 | 7306.162 | 2014-10-30 |  | 2015-09-23 | 2015-10-01 | 1%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | KENTUCKY | UNITED STATES | ACC123183 | Air Support Operations Center | 2014-01-24 | 2014-08-21 | MACNAK Korte Group | W912QR14C0027 | 7143.462 | 7143.462 | 2014-09-29 |  | 2016-02-13 | 2015-12-13 | 1%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | MARYLAND | UNITED STATES | PAYZ130011 | U.S. Cyber Command Joint Operations Center | 2012-09-11 | 2014-03-27 | Hensel Phelps | W912DR14C0016 | 57000 | 57000 | 2014-07-07 |  | 2016-03-26 | 2017-04-13 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | MISSOURI | UNITED STATES | YWHG111010 | WSA: Construct Two New MOP Igloos | 2013-12-13 | 2014-05-14 | Record Steel And Construction | W912DQ14C4005 | 3817.7 | 3817.7 | 2014-08-11 |  | 2015-09-06 | 2015-11-13 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | LKTC073101 | Land Acquisition | 2014-07-18 | 2014-09-02 | USACE | W81EYN42417577 | 11.45 | 11.45 | 2014-09-02 |  | 2014-12-01 | 2016-03-15 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF083002 | Dormitory | 2014-01-27 | 2014-06-04 | Macnac-Korte | W912PL14C0003 | 30381 | 30381 | 2014-08-05 |  | 2016-08-22 | 2016-07-15 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103005 | F-35A ADAL AME Storage Facility | 2013-12-13 | 2014-07-24 | RCDS Contractors | W912PL10D0113 | 4829.984 | 4829.984 | 2014-08-27 |  | 2016-01-15 | 2015-08-15 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103006 | F-35A Parts Store | 2013-12-12 | 2014-06-04 | Sybrant Candelaria | W912PL10D00970005 | 6974.014 | 6974.014 | 2014-08-15 |  | 2015-12-01 | 2015-09-01 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF103009 | F-35A Add/Alter Fuel Cell Hangar | 2013-12-16 | 2014-05-21 | TeeHee Straub | W912PL10D00960002 | 8066 | 8066 | 2014-06-24 |  | 2015-11-12 | 2015-09-01 | 5%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEVADA | UNITED STATES | RKMF113005 | RPA Weapons School | 2013-12-20 | 2014-06-11 | RSCI | W912PL14C0008 | 14922.7 | 14922.7 | 2014-08-12 |  | 2016-05-31 | 2016-07-15 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073050 | Dormitory (144 Rm) | 2013-11-20 | 2014-06-30 | MACNAK Korte Team LLC, Lakewood, Washington | W912PP14C0020 | 19224.874 | 19224.874 | 2014-07-10 |  | 2016-07-07 | 2015-07-15 | 1%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NEW MEXICO | UNITED STATES | MHMV103105B | Nuclear Systems Wing & Sustainment Center Ph 2 | 2013-10-24 | 2014-07-24 | K.L. House Construction | W912PP14C0016 | 21285.5 | 21285.5 | 2014-08-25 |  | 2016-09-30 | 2016-02-08 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | NORTH DAKOTA | UNITED STATES | QJVF092013 | B-52 Munitions Storage Igloos | 2014-01-24 | 2014-06-09 | Raass Brother's Inc. | W9128F14C0009 | 9540.27 | 9540.27 | 2014-07-15 |  | 2015-12-01 | 2015-09-21 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143001 | KC-46A FTU Renovate Facility For 97 OG & 97 MXTS | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 1164.308 | 1164.308 | 2014-07-30 |  | 2015-12-08 | 2015-03-12 | 5%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143002 | KC-46A FTU ADAL Sq Ops/Amu | 2014-02-05 | 2014-06-16 | The Ross Grp Construction Corp | W912BV10D20140006 | 7111.892 | 7111.892 | 2014-07-02 |  | 2015-12-08 | 2015-12-17 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143003 | KC-46A FTU Fuselage Trainer Phase 1 | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 5645.2 | 5645.2 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | OKLAHOMA | UNITED STATES | AGGN143004 | KC-46A FTU Ftc Simulator Facility Phase 1 | 2014-01-23 | 2014-06-05 | The Ross Group Construction Corporation | W912BV14C0015 | 11000 | 11000 | 2014-06-19 |  | 2015-09-08 | 2015-10-12 | 2%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | TEXAS | UNITED STATES | AETC176870 | Construct New BAK 12/14 Aircraft Arresting Syst At Rwy 3-21 | 2013-10-22 | 2014-04-22 | Head, Inc/Columbus/Ohio | W9127S14C6000 | 3265.367 | 3265.367 | 2014-05-15 |  | 2015-05-17 | 2015-06-09 | 22%
2014-11-05 | 2014 | Air Force Active | Major Military Construction | UTAH | UNITED STATES | KRSM103011 | F-35 ADAL Hangar 45E/AMU | 2013-07-22 | 2014-04-10 | CTI | W912PL14C0005 | 6587 | 8797.06 | 2014-05-20 |  | 2015-10-02 | 2015-10-15 | 19%
2014-11-05 | 2014 | Air Force Active | Major Military Construction |  | GREENLAND | WWCX103028 | Consolidated Vehicle Maint And Pavements & Grounds Facility | 2014-02-12 | 2014-07-21 | Per Aarsleff | W912DS14C0016 | 39817.6089 | 39817.6089 | 2014-08-19 |  | 2016-07-10 | 2016-06-17 | 2%
2014-11-05 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | LXEZ144287 | Improve MFH Infrastructure, Phase 3 | 2014-01-15 | 2014-06-30 | WITCO Industries Ltd (Stearley-Water&Sewer) | W912HV12D00020006 | 6288.6807 | 6288.6807 | 2014-08-15 |  | 2016-01-07 | 2016-01-07 | 3%
[8 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Kishaba-Water&Sewer)) | W912HV12D00030005 | 4202.136 | 4202.136 | 2014-07-23 |  | 2014-06-30
[8 empty] | 2014-01-15 | 2014-06-30 | Sumitomo Heavy Industries, Ltd (Plaza-Electrical) | W912HV12D00030006 | 2473.4496 | 2473.4496 | 2014-08-06 |  | 2015-09-10
2014-11-05 | 2014 | Air Force Active | Military Family Housing Improvement |  | JAPAN | QKKA144002 | Improve MFH Infrastructure, Phase 3 | 2014-04-04 | 2014-09-27 | Sanken Setsubi Kogyo Co., Ltd/Tokyo, Japan | W912HV14C0016 | 25302.11 | 25302.11 | 2014-10-30 |  | 2016-12-05 | 2016-12-24 | 1%
2014-11-05 | 2014 | Air Force Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | QSEU123003 | Add HC-130J Aircraft Maintenance Unit Facility | 2014-02-28 | 2014-07-29 | Artesian Construction Co. | FA483014D00040001 | 1547.47 | 1547.47 | 2014-11-24 |  | 2015-07-29 | 2015-11-23 | 1%
2014-11-05 | 2014 | Air National Guard | Unspecified Minor Military Construction | SOUTH CAROLINA | UNITED STATES | PSTE129092 | Construct North Overrun | 2013-10-22 | 2014-02-11 | Carolina Siteworks | W912420930003S401 | 1.702 | 1.78 | 2014-03-11 |  | 2014-12-24 | 2014-12-31 | 2%
2014-10-31 | 2008 | Army Active | Military Construction [Major] | LOUISIANA | UNITED STATES | 54785 | Child Development Center | 2010-12-13 | 2011-08-05 | ASSET Group, Inc. | W9127S-11-C-6011 | 7835.188 | 7946.4612 | 2011-09-23 |  | 2013-01-25 | 2014-11-30 | 87.6% | 2750 | 68772
2014-10-31 | 2008 | Army Active | Military Construction [Major] |  | KOREA, SOUTH | 58784 | Barracks Complex | 2012-02-02 | 2012-09-17 | ECC International, LLC (ECC) | W912UM-12-C-0058 | 32468.604 | 35207.0311 | 2012-09-17 |  | 2014-09-07 | 2015-06-09 | 79.09% | 28300 | 55313, 59557, 59804, 60045, 60151, 60241, 61148, 61355, 61873, 62077, 63662, 64143, 64903, 65795, 65796, 67038, 67169, 68458, 68763, 68769, 68784, 68840, 68847, 68863, 68877, 70979
2014-10-31 | 2009 | Army Active | Military Construction [Major] | NEW JERSEY | UNITED STATES | 66725 | Ballistic Evaluation Facility Ph 1 | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 7201.728 | 7660.728 | 2012-12-04 |  | 2014-06-04 | 2014-12-01 | 49.11%
2014-10-31 | 2009 | Army Reserve | Military Construction [Major] | NEW YORK | UNITED STATES | 67579 | Add/Alt Army Reserve Center | 2009-02-19 | 2009-06-18 | E. W. Howell Company, Inc. | W912QR-09-C-0040 | 15041.2 | 16141.3502 | 2009-07-21 |  | 2011-07-11 | 2014-10-31 | 99%
2014-10-31 | 2009 | Army Active | Military Construction [Major] |  | AFGHANISTAN | 72125 | SOF Alpha Ramp Facilities | 2012-04-04 | 2012-08-23 | Prime Projects Int'l (Const) Limited | W912ER-12-C-0040 | 5739 | 8416 | 2012-09-27 |  | 2013-08-13 | 2014-03-01 | 89%
2014-10-31 | 2010 | Army Active | Military Construction [Major] | NEW JERSEY | UNITED STATES | 66726 | Ballistic Evaluation Facility, Ph 2 | 2012-05-11 | 2012-09-28 | APS Contracting Inc. | W912DS-12-C-0030 | 8757.272 | 8954.263 | 2012-12-04 |  | 2014-06-04 | 2015-02-28 | 59.57%
2014-10-31 | 2010 | Army Reserve | Military Construction [Major] | PENNSYLVANIA | UNITED STATES | 69430 | Army Reserve Center/Land | 2011-07-28 | 2011-09-29 | Lobar Inc. | W912QR-11-C-0062 | 18272 | 18791.879 | 2012-01-18 |  | 2013-11-08 | 2015-03-23 | 69.53%
2014-10-31 | 2010 | Army Reserve | Military Construction [Major] | FLORIDA | UNITED STATES | 69471 | Army Reserve Center/Land | 2011-07-05 | 2012-04-02 | Blackhawk-Jamco, A SDVOB Joint Venture | W912QR-12-C-0022 | 16009 | 16319.55 | 2012-05-22 |  | 2013-09-24 | 2015-03-21 | 72.67%
2014-10-31 | 2010 | Army Reserve | Military Construction [Major] | PUERTO RICO | PUERTO RICO | 69568 | Army Reserve Center/Land | 2011-06-16 | 2011-09-22 | RBC Construction Coporation | W912QR-11-C-0046 | 12356.39 | 12640.4564 | 2011-11-15 |  | 2013-08-06 | 2014-12-31 | 98.08%
2014-10-31 | 2010 | Army Active | Military Construction [Major] |  | KUWAIT | 71485 | APS Warehouses | 2013-06-21 | 2013-09-27 | Contrack International, Inc. | W912ER-13-C-0032 | 49412.74 | 54675.778 | 2013-10-25 |  | 2015-03-25 | 2015-03-25 | 15.16%
2014-10-31 | 2010 | Army Active | Military Construction [Major] |  | KUWAIT | 71485 | APS Warehouses | 2013-11-06 | 2014-04-03 | Contrack International, Inc. |  | 6749.291 | 6749.291 | 2014-05-08 |  | 2015-10-30 | 2015-10-30 | 6%
2014-10-31 | 2010 | Army Active | Military Construction [Major] |  | AFGHANISTAN | 72477 | USFOR-A Headquarters & Housing | 2011-03-28 | 2011-08-05 | Contrack International Inc. | W912ER-11-C-0049 | 47160.85 | 32446.0654 | 2011-09-09 |  | 2013-12-07 | 2014-11-10 | 95.04%
2014-10-31 | 2010 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 74408 | Ft Lewis-McChord AFB Joint Access | 2013-02-12 | 2013-08-29 | TSS-Garco Joint Venture | W912DW-13-C-0040 | 7327 | 7645.264 | 2013-09-25 |  | 2015-01-28 | 2015-01-28 | 56%
2014-10-31 | 2010 | Army Reserve | Military Construction [Major] | TEXAS | UNITED STATES | 75110 | Tactical Equipment Maintenance Facility | 2011-10-04 | 2012-01-26 | Leetex Construction LLC | W912QR-12-C-0010 | 9433.577 | 9433.577 | 2012-04-05 |  | 2013-09-12 | 2014-12-18 | 93.2%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 52269 | Barracks | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders | W9128A-11-C-0016 | 23984.24 | 24851.344 | 2011-10-17 |  | 2014-07-16 | 2015-02-11 | 94.33%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 52269 | Barracks | 2011-04-28 | 2011-09-20 | Nan, Inc. dba Ocean House Builders |  | 1329.054 | 16467.087 | 2011-10-17 |  | 2014-07-16 | 2015-02-11 | 94.36%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 56024 | Flood Mitigation | 2012-06-29 | 2012-09-25 | Nan, Inc | W9128A-12-C-0019 | 21105.273 | 21809.982 | 2012-10-17 |  | 2014-10-14 | 2015-06-30 | 58.45%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | NEW YORK | UNITED STATES | 59044 | Science Facility, Ph 2 | 2011-06-23 | 2011-09-30 | Walsh Construction Company II L.L.C. | W912DS-11-C-0023 | 105270 | 112995.901 | 2011-11-17 |  | 2015-11-14 | 2016-01-29 | 82.12%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | GERMANY | 59434 | Physical Fitness Center | 2010-12-01 | 2011-08-12 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0040 | 13513.2866 | 14054.3115 | 2012-11-30 |  | 2014-11-15 | 2014-11-28 | 81.1%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | GERMANY | 59434 | Physical Fitness Center | 2012-06-15 | 2012-11-01 | Staatliches Hochbauamt Nurnberg II |  | 969.0413 | 1109.3938 | 2012-11-30 |  | 2014-11-15 | 2014-11-28 | 61.24%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | GERMANY | 60555 | Information Processing Center | 2010-12-16 | 2012-05-14 | Hessisches Baumanagement Wiesbaden | W912GB-08-C-0005 | 27799.1141 | 31738.9806 | 2012-06-18 |  | 2014-06-01 | 2014-12-19 | 95.13%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | HONDURAS | 61383 | Barracks | 2011-05-18 | 2011-08-25 | Contracting, Consulting, Engineering, LLC | W91278-11-C-0028 | 15146.5804 | 15633.3629 | 2012-01-10 |  | 2014-01-09 | 2014-09-24 | 95.83%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | VIRGINIA | UNITED STATES | 61453 | Replace Fire Station | 2012-08-06 | 2013-05-23 | TMG SERVICES, INC. Linda Frazier | W912DR-13-C-0030 | 6189 | 6378.06 | 2013-06-05 |  | 2014-11-27 | 2015-05-15 | 41.57% | 2580 | 68961
2014-10-31 | 2011 | Army Active | Military Construction [Major] | CALIFORNIA | UNITED STATES | 63015 | Satellite Communications Facility | 2011-01-07 | 2014-09-03 | Watts Constructors, LLC | W912PP-08-C-0019 | 38914.5 | 38914.5 | 2014-09-19 |  | 2016-06-30 | 2016-06-30 | 0% | 12900 | 73686
2014-10-31 | 2011 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 64760 | Training Aids Center | 2012-06-29 | 2012-09-19 | SRB International LLC | W9128A-12-C-0013 | 13310.008 | 13309.7969 | 2012-10-31 |  | 2014-08-17 | 2015-01-07 | 82.67%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 65650 | Command and Control Facility, Ph 1 | 2011-11-04 | 2012-02-28 | Niking Corporation | W9128A-12-C-0003 | 46780 | 48939.101 | 2012-04-03 |  | 2014-04-23 | 2015-06-30 | 82.36%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | GERMANY | 66834 | Vehicle Maintenance Shop | 2010-12-01 | 2011-06-16 | Staatliches Hochbauamt Nurnberg II | W912GB-09-C-0030 | 15984.7877 | 17308.6172 | 2011-12-12 |  | 2013-12-18 | 2015-05-31 | 87.62%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | GERMANY | 68074 | Construct New ACP | 2013-11-15 | 2014-03-04 | Hessisches Baumanagement Wiesbaden |  | 6303.8821 | 7097.5946 | 2014-03-05 |  | 2014-12-12 | 2014-12-12 | 75.57%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | GERMANY | 68866 | Sensitive Compartmented Information Fac | 2012-05-22 | 2013-01-23 | ECC International LLC | W912GB-13-C-0003 | 87011.483 | 89200.6517 | 2013-02-22 |  | 2015-09-19 | 2015-10-31 | 18.2% | 33782 | 65714, 68822, 69936
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | GERMANY | 68866 | Sensitive Compartmented Information Fac |  | 2013-02-04 | OBG Hochbau GmbH & Co. KG |  | 7198.2416 | 7716.9736 | 2014-07-09 |  | 2014-10-07 | 2014-11-10 | 96.16%
2014-10-31 | 2011 | Army Reserve | Military Construction [Major] | TEXAS | UNITED STATES | 69421 | Army Reserve Center/Land | 2012-01-10 | 2012-07-24 | Highmark Construction Company, LLC | W912QR-12-C-0047 | 4454 | 4454 | 2012-08-21 |  | 2014-03-21 | 2015-08-30 | 6.31%
2014-10-31 | 2011 | Army Reserve | Military Construction [Major] | NEW YORK | UNITED STATES | 69599 | Army Reserve Center/Land | 2012-07-25 | 2012-09-25 | J. Kokolakis Contracting, Inc. | W912QR-12-C-0057 | 12353.9 | 12873.5 | 2012-10-25 |  | 2014-04-03 | 2014-11-28 | 99%
2014-10-31 | 2011 | Army Reserve | Military Construction [Major] | IOWA | UNITED STATES | 70654 | Army Reserve Center | 2011-11-15 | 2012-03-14 | The Vertex Companies | W912QR-12-C-0014 | 8931.622 | 8999.53 | 2012-04-09 |  | 2013-08-12 | 2014-12-15 | 94.65%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 71462 | Battalion Complex | 2011-01-24 | 2011-09-30 | JAMA Constructors | W912HN-11-D-0035 | 6572.777 | 8448.4512 | 2012-07-30 |  | 2014-01-21 | 2015-01-05 | 89.68%
2014-10-31 | 2011 | Army Active | Military Construction [Major] |  | AFGHANISTAN | 71604 | Eastside Utilities Infrastructure | 2012-05-30 | 2012-09-04 | ANHAM-ICSS Joint Venture | W912ER-11-D-0003 | 26826.989 | 24722.776 | 2012-10-18 |  | 2014-06-05 | 2015-01-31 | 56.86%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 71639 | Brigade Complex | 2012-12-19 | 2013-09-30 | Bristol General Contractors, LLC |  | 15175 | 15225 | 2013-11-06 |  | 2015-01-30 | 2015-03-19 | 21%
2014-10-31 | 2011 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 72854 | Regional Logistic Support Complex | 2011-05-02 | 2011-09-26 | Garco Construction, Inc. | W912DW-13-C-0020 | 36247 | 37009.146 | 2013-02-13 |  | 2014-08-07 | 2014-08-07 | 87.91%
2014-10-31 | 2011 | Army Reserve | Military Construction [Major] | FLORIDA | UNITED STATES | 74220 | Army Reserve Center/Land | 2011-05-19 | 2011-09-23 | Liberty Mutual Insurance Company | W912QR-11-C-0048 | 8807.148 | 8793.328 | 2011-10-21 |  | 2013-03-24 | 2014-11-13 | 97.13%
2014-10-31 | 2011 | Army Reserve | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 74731 | Training Exercise Warehouse | 2011-08-19 | 2012-07-13 | Total Team Construction Services | W912QR-12-C-0042 | 1612.061 | 1612.773 | 2012-09-11 |  | 2013-08-07 | 2014-10-30 | 88.87%
2014-10-31 | 2011 | Army Active | Unspecified Minor Military Construction | OHIO | UNITED STATES | 74757 | Fire Alarm System | 2012-01-19 | 2012-08-06 | Custom Mechanical Systems, Corp | W912QR-12-C-0050 | 1763.338 | 1782.2016 | 2012-09-05 |  | 2013-08-01 | 2015-03-20 | 78.89%
2014-10-31 | 2011 | Army Reserve | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 79128 | DEPMEDS | 2013-03-26 | 2013-09-30 | Imperial Construction | W912QR-13-C-0046 | 1560.895 | 1652.152 | 2013-10-11 |  | 2014-09-26 | 2014-12-15 | 68.93%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | OKLAHOMA | UNITED STATES | 1235 | Physical Fitness Facility | 2012-01-05 | 2012-06-19 | Grahams Construction Inc. | W912DY-11-D-0040 | 23138.91 | 23149.051 | 2012-07-12 |  | 2014-04-10 | 2015-03-06 | 64.46%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | KANSAS | UNITED STATES | 2728 | Physical Fitness Facility | 2011-12-09 | 2014-07-02 | Zieson Construction Co. |  | 727.389 | 727.389 | 2015-03-13 |  | 2016-03-12 | 2016-03-12 | 0%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. | W9126G-13-C-0005 | 8603 | 9101.83 | 2013-01-24 |  | 2014-07-18 | 2015-04-14 | 54.65% | 3900 | 65745
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 5034 | Vehicle Maintenance Facility | 2012-10-22 | 2012-12-27 | Anthony & Gordon Construction Co. Inc. |  | 4150 | 4150 | 2013-01-24 |  | 2014-07-18 | 2015-04-14 | 27.23%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | LOUISIANA | UNITED STATES | 17220 | Fire Station | 2012-04-03 | 2013-09-25 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 12622.8 | 12644.8 | 2013-11-06 |  | 2015-11-11 | 2015-11-11 | 15.36% | 5000 | 65745
2014-10-31 | 2012 | Army Active | Military Construction [Major] | OKLAHOMA | UNITED STATES | 20697 | Chapel | 2012-01-27 | 2012-08-30 | Liberty Mutual Insurance Company | W912BV-12-C-0018 | 12999.823 | 13082.662 | 2012-09-20 |  | 2014-01-28 | 2015-04-30 | 46.97%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | NORTH CAROLINA | UNITED STATES | 43335 | NCO Academy | 2012-05-08 | 2012-07-30 | Caddell Construction CO., INC | W912HN-10-D-0044 | 34647 | 34719.9415 | 2012-10-03 |  | 2014-07-15 | 2014-09-28 | 99.45%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | UTAH | UNITED STATES | 55823 | Life Sciences Test Facility Addition | 2012-04-12 | 2012-07-26 | Big-D Construction Corp | W91238-12-C-0024 | 22608.566 | 29440.871 | 2012-08-29 |  | 2015-02-15 | 2015-12-03 | 74.15%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | GERMANY | 55985 | Chapel | 2012-01-10 | 2012-03-15 | Bauamt Amberg-Sulzbach | W912GB-06-C-0005 | 15915.6532 | 16173.2402 | 2013-11-21 |  | 2016-03-23 | 2016-03-23 | 18.57%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | CALIFORNIA | UNITED STATES | 56425 | General Instruction Building | 2012-08-20 | 2012-09-29 | Souza Construction, Inc. | W91238-10-D-0010 | 2996 | 3163.422 | 2012-11-06 |  | 2013-11-06 | 2015-01-01 | 98.46%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | VIRGINIA | UNITED STATES | 57508 | Information Dominance Center, Ph 1 | 2013-03-15 | 2013-07-22 | Hensel Phelps Construction Co. | W912DR-13-C-0035 | 39700.01 | 40645.4345 | 2013-08-19 |  | 2015-03-12 | 2015-04-24 | 57.53%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | GERMANY | 57594 | Satellite Communications Center | 2012-03-12 | 2012-03-28 | JV PGWM SATCOM | W912GB-14-C-0003 | 27565.3511 | 27600.2975 | 2014-03-14 |  | 2015-12-14 | 2015-12-14 | 8.721%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 58046 | Operational Readiness Training Cplx, Ph 1 | 2012-06-29 | 2013-04-01 | TSS-Garco Joint Venture | W912DW-12-C-0043 | 16416 | 16268.76 | 2013-05-21 |  | 2014-11-12 | 2015-03-25 | 46.4%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | OKLAHOMA | UNITED STATES | 58207 | Railroad Tracks | 2011-11-29 | 2012-03-26 | McAlester Contract | W44XGQ80956921 | 6323.7745 | 6323.7745 | 2012-05-09 |  | 2013-10-06 | 2014-09-15 | 100%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | GERMANY | 58925 | Satellite Communications Center | 2012-03-12 | 2014-09-05 | JV PGWM SATCOM | W912GB-14-C-0037 | 29010.1333 | 29010.1333 | 2014-10-16 |  | 2016-08-01 | 2016-08-01 | 0% | 6000 | 71485
2014-10-31 | 2012 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 59581 | Centralized Wash Facility | 2011-10-13 | 2012-01-27 | Watts Constructors, LLC | W9128A-12-C-0001 | 28300 | 29972.039 | 2012-02-08 |  | 2013-12-14 | 2014-11-14 | 96.34%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | ALASKA | UNITED STATES | 61515 | Physical Fitness Facility | 2011-10-19 | 2012-11-07 | Bristol General Contractors, LLC | W911KB-13-C-0002 | 21813.389 | 22240.075 | 2013-03-16 |  | 2014-12-06 | 2015-07-01 | 35%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | CALIFORNIA | UNITED STATES | 62657 | Water Treatment Plant | 2012-05-21 | 2012-09-12 | CDM CONSTRUCTORS INC. | W912PL-12-C-0022 | 100112.66 | 99541.018 | 2012-10-19 |  | 2015-10-19 | 2016-01-05 | 57.57%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | SOUTH CAROLINA | UNITED STATES | 62955 | Trainee Barracks Complex, Ph 2 | 2012-02-22 | 2012-03-28 | CLARK CONSTRUCTION GROUP LLC | W9126G-11-D-0049 | 44267 | 48060.634 | 2012-07-23 |  | 2014-01-14 | 2014-11-06 | 97.28%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 64014 | Battalion Complex | 2013-07-29 | 2013-09-26 | MEGEN Construction Company, Inc. |  | 7295 | 3293 | 2013-10-15 |  | 2015-04-08 | 2015-04-08 | 43%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | LOUISIANA | UNITED STATES | 64415 | Brigade Complex | 2011-12-16 | 2012-08-17 | The Ross Group Construction Corporation | W9126G-09-D-0101 | 11856.9 | 12236.1292 | 2012-10-09 |  | 2014-04-02 | 2014-11-19 | 89.47%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | LOUISIANA | UNITED STATES | 64415 | Brigade Complex | 2012-02-21 | 2012-03-23 | Blackhawk Ventures, LLC |  | 10283 | 10964.2248 | 2012-05-15 |  | 2013-11-06 | 2014-12-19 | 92.66%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | MARYLAND | UNITED STATES | 64939 | Applied Instruction Facility | 2012-06-20 | 2012-09-24 | Grimberg/Amatea JV | W912DR-12-C-0023 | 30554 | 30965.465 | 2012-11-20 |  | 2014-11-20 | 2015-01-08 | 80.93%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 64967 | Child Development Center | 2011-10-06 | 2012-02-27 | 57 Builders, Ltd. | W9128A-12-C-0002 | 9573.118 | 10193.638 | 2012-03-23 |  | 2013-12-13 | 2015-02-28 | 82.13%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex | 2012-01-05 | 2012-07-20 | AMG & Satterfield & Pontikes, a JV | W9126G-12-C-0043 | 38503 | 39614.9008 | 2012-09-05 |  | 2014-07-28 | 2014-11-24 | 66.83%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 65374 | Operational Readiness Training Complex | 2012-07-19 | 2013-01-07 | Turner Strategic Technologies, LLC |  | 8195.202 | 8267.659 | 2013-03-08 |  | 2014-11-28 | 2014-12-15 | 77.1%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | MARYLAND | UNITED STATES | 65755 | Brigade Complex | 2012-05-01 | 2012-10-30 | Skanska USA Building Inc. | W912DR-13-C-0002 | 30761.85 | 32254 | 2012-12-12 |  | 2015-12-12 | 2016-06-02 | 59.69% | 3500 | 34129, 52856, 64797, 65138, 69167, 69999, 71539
2014-10-31 | 2012 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 66206 | Infrastructure, Ph 1 | 2012-08-18 | 2013-01-25 | CeSight Joint Venture | W912DW-13-C-0024 | 13775.4 | 14557.3098 | 2013-03-04 |  | 2014-08-26 | 2015-03-20 | 90.45%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 66691 | Maneuver Systems Sustainment Ctr, Ph 3 | 2011-12-24 | 2012-03-23 | GCC McCarthy Joint Venture IV | W9126G-12-C-0015 | 40532.114 | 40793.3202 | 2012-04-24 |  | 2014-04-24 | 2015-07-10 | 66.59%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | ALASKA | UNITED STATES | 67113 | Aviation Complex, Ph 3A | 2011-07-15 | 2012-06-07 | Watterson Construction Company | W911KB-12-C-0008 | 70591 | 71470.343 | 2012-06-14 |  | 2014-08-03 | 2014-12-15 | 97% | 27000 | 68962, 71539
2014-10-31 | 2012 | Army Reserve | Military Construction [Major] | NORTH CAROLINA | UNITED STATES | 67466 | Army Reserve Center/Land | 2012-05-16 | 2012-09-18 | IKHANA, LL | W912QR-12-C-0055 | 15942 | 15977.219 | 2012-10-10 |  | 2014-03-19 | 2015-05-05 | 66.71%
2014-10-31 | 2012 | Army Reserve | Military Construction [Major] | COLORADO | UNITED STATES | 67658 | Army Reserve Center | 2011-11-29 | 2012-04-16 | Liberty Mutual Insurance Company | W912QR-12-C-0028 | 10450.922 | 10580.378 | 2012-05-11 |  | 2013-10-18 | 2015-03-01 | 78.24%
2014-10-31 | 2012 | Army Reserve | Military Construction [Major] | ILLINOIS | UNITED STATES | 67713 | Army Reserve Center | 2012-07-31 | 2012-09-27 | Accel/Pacific J.V. | W912QR-12-C-0068 | 13312 | 14525.3652 | 2012-10-18 |  | 2014-07-10 | 2015-05-18 | 68.58%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 68993 | Electronics Maintenance Facility | 2011-12-17 | 2013-09-20 | Venegas Engineering & Management Construction Company |  | 5117.965 | 5117.965 | 2012-08-08 |  | 2014-05-05 | 2014-12-30 | 97.76%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 69286 | Infrastructure | 2011-09-16 | 2012-07-26 | Venegas Engineering & Management Construction Company | W9126G-12-C-0044 | 9008.411 | 8732.566 | 2012-08-20 |  | 2013-09-13 | 2014-12-30 | 97.56%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 69489 | Combat Aviation Brigade Complex, Ph 1 | 2012-01-24 | 2012-06-29 | David Boland, Inc. | W9128A-12-C-0009 | 54772 | 55653.653 | 2012-07-30 |  | 2015-05-27 | 2015-06-11 | 50.39%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | KENTUCKY | UNITED STATES | 69501 | Unmanned Aerial Vehicle Maintenance Hangar | 2011-12-16 | 2012-09-27 | Archer Western Federal JV | W912QR-12-C-0058 | 40397 | 42215.481 | 2012-11-05 |  | 2014-09-06 | 2014-12-03 | 95.46%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | GERMANY | 69614 | Barracks | 2012-03-02 | 2012-03-15 | Staatliches Hochbauamt Amberg | W912GB-10-C-0043 | 17523.1242 | 17752.2228 | 2013-03-27 |  | 2014-12-31 | 2014-11-26 | 79.04%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 69828 | Unmanned Aerial Vehicle Maintenance Hangar | 2013-07-16 | 2014-05-29 | JAM-MAP JV | W9126G-14-C-0016 | 8829.807 | 8829.807 | 2014-08-27 |  | 2016-01-04 | 2016-01-18 | 0%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar | 2013-08-26 | 2014-01-07 | Law Company, Inc. | W912DQ-14-C-4003 | 20078.9 | 20089.068 | 2014-02-06 |  | 2015-07-31 | 2015-07-31 | 23.08%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | KANSAS | UNITED STATES | 69834 | Unmanned Aerial Vehicle Maintenance Hangar | 2012-05-01 | 2012-11-01 | Arch Insurance Company |  | 5932.641 | 6058.041 | 2012-12-11 |  | 2014-03-16 | 2014-12-31 | 77.3%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | AFGHANISTAN | 71569 | Westside Utilities Infrastructure | 2012-08-24 | 2012-11-15 | Contrack International Inc. | W912ER-11-D-0009 | 11924.059 | 10017.2264 | 2012-12-12 |  | 2014-03-07 | 2014-08-02 | 95.7%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 9669.4345 | 10104.662 | 2012-06-22 |  | 2013-12-14 | 2014-09-11 | 86.85%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 71682 | Vehicle Maintenance Facility | 2011-12-19 | 2013-12-04 | STREETER-SUMMIT JV 1, LLC |  | 5786.309 | 5786.309 | 2014-01-15 |  | 2015-01-25 | 2015-02-14 | 32.96%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | KOREA, SOUTH | 72650 | Barracks | 2011-11-10 | 2012-02-24 | Samsung C&T Corporation | W912UM-12-C-0012 | 27592.9923 | 28582.68 | 2012-02-24 |  | 2015-12-05 | 2015-10-07 | 48.48%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | KOREA, SOUTH | 72650 | Barracks | 2011-11-28 | 2012-02-27 | Hanmi C&E Co., LTD. |  | 63.7852 | 4.2522 | 2012-02-27 |  | 2015-10-31 | 2015-10-31 | 100%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | AFGHANISTAN | 74067 | Construct Drainage System, Ph 3 | 2012-04-27 | 2012-08-15 | ANHAM-ICSS JV | W912ER-11-D-0003 | 19902.989 | 20833.6265 | 2012-10-09 |  | 2014-06-01 | 2014-10-31 | 83.01%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | KOREA, SOUTH | 76235 | Barracks Complex | 2012-02-02 | 2012-04-06 | Fine Construction Co., Ltd. | W912UM-12-C-0022 | 28609.5284 | 29357.0725 | 2012-04-06 |  | 2014-06-22 | 2014-11-23 | 93.81%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 76768 | Aviation Complex, Ph 1B | 2013-12-04 | 2014-04-08 | Glen/Mar Construction, Inc. |  | 4771.02 | 4810.946 | 2014-05-21 |  | 2015-05-21 | 2015-05-31 | 5.272%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility | 2011-12-19 | 2012-03-30 | Alutiiq Diversified Services, LLC | W9126G-12-C-0018 | 7472.9455 | 7802.2463 | 2012-06-22 |  | 2013-12-14 | 2014-08-31 | 84.45%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 77187 | Vehicle Maintenance Facility | 2011-12-19 | 2013-12-04 | STREETER-SUMMIT JV 1, LLC |  | 5378.708 | 4774.586 | 2014-01-15 |  | 2015-07-09 | 2015-07-29 | 99%
2014-10-31 | 2012 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77306 | Aircraft Maintenance Hangar | 2012-01-17 | 2013-05-02 | M.A. Mortenson Company dba Mortenson Construction |  | 2669.032 | 2920.134 | 2013-05-31 |  | 2015-02-08 | 2015-02-08 | 85.25%
2014-10-31 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78505 | Family Housing New Construction | 2012-04-06 | 2012-05-04 | Staatliches Hochbauamt Amberg |  | 13548.8862 | 13638.7798 | 2013-08-07 |  | 2015-09-14 | 2015-11-05 | 37.41%
2014-10-31 | 2012 | Army Active | Military Family Housing |  | GERMANY | 78506 | Family Housing New Construction | 2012-04-10 | 2012-05-04 | Bauamt Amberg-Sulzbach |  | 12815.485 | 12850.7815 | 2013-09-30 |  | 2015-08-11 | 2015-08-11 | 40.93%
2014-10-31 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 78841 | Family Housing Improvements | 2012-05-15 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0018 | 20428.5583 | 20922.1831 | 2012-10-15 |  | 2018-10-29 | 2018-11-25 | 36.57%
2014-10-31 | 2012 | Army Active | Military Family Housing Improvement |  | GERMANY | 79097 | Family Housing Improvements | 2012-05-12 | 2012-09-13 | Klebl GmbH | W912GB-12-C-0017 | 17917.1392 | 18722.9467 | 2012-10-15 |  | 2018-04-02 | 2018-04-02 | 28.17%
2014-10-31 | 2012 | Army Active | Military Construction [Major] |  | TURKEY | 79749 | Forward Operating Site | 2012-06-15 | 2012-08-17 | EMTA INSAAT A.S | W912GB-12-D-0033 | 12129.1464 | 12151.695 | 2013-12-05 |  | 2015-04-29 | 2015-07-31 | 28.13%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 | 2013-07-17 | 2013-09-30 | Purcell Construction Corporation | W91236-13-C-0064 | 46650 | 46659.0739 | 2013-10-15 |  | 2015-10-15 | 2015-10-15 | 42.49%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | VIRGINIA | UNITED STATES | 33771 | Adv Individual Training Barracks Cplx, Ph2 | 2013-07-17 | 2014-09-03 | VISTA Construction LLC |  | 4055.4 | 4055.4 | 2014-09-16 |  | 2015-09-16 | 2015-12-08 | 0%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | NEW JERSEY | UNITED STATES | 51519 | Ballistic Evaluation Center | 2013-05-16 | 2013-09-25 | Benard Associates, Inc. | W912DS-13-C-0049 | 5959 | 6325.204 | 2013-10-23 |  | 2015-02-15 | 2015-01-16 | 57.69%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 | 2013-04-11 | 2013-08-15 | Caddell Construction Co. (DE), LLC | W912DQ-13-C-4024 | 33360 | 33360 | 2013-09-12 |  | 2015-09-12 | 2015-09-12 | 59.24%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | MISSOURI | UNITED STATES | 54489 | Trainee Barracks Complex 3, Ph 2 | 2013-01-18 | 2013-05-31 | Donald Maggi, Inc. |  | 11711 | 11753.8238 | 2013-06-25 |  | 2014-12-17 | 2014-12-17 | 85.43%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | GEORGIA | UNITED STATES | 57794 | Digital Multipurpose Training Range | 2012-12-26 | 2013-05-10 | Caddell Construction Co. (DE), LLC | W912HN-10-D-0044 | 19523 | 19579.518 | 2014-02-04 |  | 2015-04-30 | 2015-04-30 | 32.78%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | SOUTH CAROLINA | UNITED STATES | 58970 | Trainee Barracks Complex 2, Ph 2 | 2013-04-29 | 2013-10-30 | ACC Construction Co., Inc | W912HP-14-C-0003 | 21786.027 | 21850.968 | 2013-12-04 |  | 2015-05-28 | 2015-06-07 | 38.72%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 59626 | Digital Multipurpose Training Range | 2013-05-31 | 2013-08-23 | NEU Security Services, LLC | W9128F-13-C-0016 | 14080 | 15393.603 | 2013-09-18 |  | 2015-03-12 | 2015-05-01 | 45.98%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex | 2012-12-06 | 2014-02-06 | Sundt Construction Inc. | W912QR-14-C-0007 | 25750 | 25750 | 2014-03-04 |  | 2015-08-26 | 2015-08-26 | 23.41%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | KENTUCKY | UNITED STATES | 61810 | Battalion Headquarters Complex | 2012-12-06 | 2013-05-29 | Orocon-Carothers JV1 |  | 23450.6124 | 23758.4884 | 2013-07-15 |  | 2014-12-07 | 2014-12-30 | 87.77%
2014-10-31 | 2013 | Army Active | Military Construction [Major] |  | JAPAN | 62783 | Satellite Communications Facility | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. | W912HV-14-C-0007 | 6488.2629 | 6488.2629 | 2014-11-21 |  | 2021-06-09 | 2021-06-09 | 0% | 24810 | 36113, 61562, 64474, 66441, 69999, 71472, 71485, 72242
2014-10-31 | 2013 | Army Active | Military Construction [Major] |  | JAPAN | 62783 | Satellite Communications Facility | 2013-03-26 | 2014-09-18 | Prime Projects International Japan Co., Ltd. |  | 61071.4985 | 61071.4985 | 2014-11-21 |  | 2021-06-09 | 2021-06-09 | 0%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | MISSOURI | UNITED STATES | 65679 | Vehicle Maintenance Shop | 2013-01-30 | 2013-06-03 | ACC Construction Co., Inc. | W912DQ-13-C-4011 | 18726.852 | 19105.258 | 2013-06-27 |  | 2015-04-08 | 2015-04-18 | 67.4%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 66023 | Automated Infantry Platoon Battle Course | 2014-02-11 | 2014-06-23 | Goodfellow Bros., Inc. | W9128A-14-C-0005 | 27345 | 27345 | 2014-07-08 |  | 2016-09-09 | 2016-09-09 | 0%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | MISSOURI | UNITED STATES | 66099 | Battalion Complex Facilities | 2012-12-19 | 2013-06-03 | MW Builders, Inc. | W912HN-11-D-0035 | 13687 | 14211.071 | 2013-07-01 |  | 2014-12-23 | 2015-01-11 | 81.53%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | GEORGIA | UNITED STATES | 67017 | Multipurpose Machine Gun Range | 2012-11-19 | 2013-05-16 | Bristol Environmental Remediation Service | W912DY-12-D-0053 | 6483.273 | 6528.523 | 2013-07-11 |  | 2014-08-05 | 2014-09-27 | 93.89%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 67545 | Convoy Live Fire Range | 2013-05-16 | 2013-08-22 | Vet Industrial Inc. | W912DW-10-D-1021 | 4990.675 | 5406.016 | 2013-09-10 |  | 2015-01-03 | 2015-01-03 | 91.16%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | ILLINOIS | UNITED STATES | 67659 | Army Reserve Center | 2013-04-29 | 2013-08-22 | Accel/Pacific Joint Venture | W912QR-13-C-0024 | 21575 | 22583.9084 | 2014-01-13 |  | 2015-11-04 | 2015-12-31 | 20.16%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | NEVADA | UNITED STATES | 67660 | Army Reserve Center/AMSA | 2012-12-28 | 2013-06-12 | MACNAK Korte Team LLC | W912QR-13-C-0014 | 16436.543 | 16787.8853 | 2013-07-10 |  | 2015-05-01 | 2015-05-01 | 66.36%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | WISCONSIN | UNITED STATES | 67689 | Central Issue Facility | 2013-01-28 | 2013-06-14 | KEPA-TCI JV LLC | W912QR-13-C-0016 | 9302.203 | 9461.4485 | 2013-07-08 |  | 2014-11-10 | 2015-04-04 | 47.09%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | WASHINGTON | UNITED STATES | 67715 | Army Reserve Center | 2013-02-25 | 2013-06-13 | S.M. Wilson & Co. | W912QR-13-C-0017 | 31219 | 31246.96 | 2013-07-11 |  | 2015-08-30 | 2015-08-30 | 52.56%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | MARYLAND | UNITED STATES | 68077 | Add/Alt Army Reserve Center | 2013-12-20 | 2014-06-26 | Arriba Corporation | W912QR-14-C-0023 | 7890.05 | 7890.05 | 2014-07-30 |  | 2016-05-30 | 2016-05-30 | 0%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 71120 | Training Aids Center | 2013-03-08 | 2013-09-04 | PENTACON, LLC | W912DY-12-D-0030 | 21912 | 22001.757 | 2013-10-17 |  | 2015-04-10 | 2015-05-25 | 21.32%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | CALIFORNIA | UNITED STATES | 71482 | ORTC | 2012-09-25 | 2014-02-06 | Sauer Incorporated | W912QR-14-C-0006 | 56000.64 | 61736.64 | 2014-03-19 |  | 2016-05-17 | 2016-05-17 | 4.826%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | NEW JERSEY | UNITED STATES | 71675 | Flight Equipment Complex | 2013-05-02 | 2013-11-21 | The Bedwell Company | W912DS-14-C-0004 | 42751 | 42814.595 | 2014-01-15 |  | 2016-01-15 | 2016-03-10 | 22.24%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | NEW JERSEY | UNITED STATES | 71720 | Automated Infantry Squad Battle Course | 2012-12-13 | 2013-06-28 | Eastern Construction & Electric, Inc. | W912QR-13-C-0015 | 3093.8904 | 3311.1024 | 2013-07-17 |  | 2014-07-17 | 2014-12-15 | 81.49%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | WISCONSIN | UNITED STATES | 71997 | Dining Facility | 2013-01-22 | 2013-08-23 | TCI Architects Engineers Contractor Inc. | W912QR-13-C-0026 | 7738.253 | 7762.7936 | 2013-10-02 |  | 2015-02-04 | 2015-03-25 | 22.49%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | WISCONSIN | UNITED STATES | 72088 | ECS TEMF | 2013-01-24 | 2013-06-13 | KEPA-TCI JV LLC | W912QR-13-C-0018 | 19021.6 | 19127.14 | 2013-07-08 |  | 2015-06-08 | 2015-06-08 | 37.75%
2014-10-31 | 2013 | Army Reserve | Military Construction [Major] | CALIFORNIA | UNITED STATES | 72160 | UPH Barracks | 2013-03-28 | 2013-08-27 | Pre Con Industries, Inc. | W912QR-13-C-0027 | 4384.284 | 4379.148 | 2013-11-18 |  | 2014-11-03 | 2015-01-05 | 51.53%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | GEORGIA | UNITED STATES | 73008 | Unmanned Aerial Vehicle Complex | 2013-03-22 | 2013-08-15 | Caddell Construction CO. (DE), LLC | W912HN-10-D-0044 | 20726 | 21007.716 | 2013-11-06 |  | 2015-03-01 | 2015-03-08 | 45.07%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 75165 | Waste Water Treatment Plant | 2013-01-15 | 2014-01-16 | CDM Constructors Inc. | W912DW-14-C-0002 | 77476.628 | 77926.828 | 2014-03-03 |  | 2016-03-02 | 2016-03-02 | 19.98%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | CALIFORNIA | UNITED STATES | 76086 | Lightning Protection System | 2014-01-23 | 2014-09-04 | Hal Hays Construction Inc. | W91238-14-C-0050 | 3072 | 3072 | 2014-09-16 |  | 2015-12-30 | 2015-12-30 | 0%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | CALIFORNIA | UNITED STATES | 76091 | Engineering/Housing Maintenance Shop | 2014-05-15 | 2014-09-18 | Federal Solutions Group | W91238-14-C-0051 | 3211.6056 | 3211.6056 | 2014-10-08 |  | 2015-11-12 | 2015-11-12 | 0%
2014-10-31 | 2013 | Army Active | Military Construction [Major] |  | KOREA, SOUTH | 76196 | Battalion Headquarters Complex | 2013-02-01 | 2013-05-14 | Hyosung Corporation | W912UM-13-C-0021 | 25852.7608 | 28686.0028 | 2013-05-14 |  | 2015-06-09 | 2016-05-01 | 22.8%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | KENTUCKY | UNITED STATES | 76239 | Unmanned Aerial Vehicle Complex | 2012-11-13 | 2013-05-31 | Archer Western Federal JV | W912QR-13-C-0012 | 16983 | 17359.385 | 2013-06-25 |  | 2015-04-26 | 2015-04-26 | 85.42%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 76586 | Barracks | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 30717.476 | 30993.561 | 2013-07-23 |  | 2015-09-01 | 2015-11-21 | 47.78%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 76587 | Barracks | 2013-02-06 | 2013-07-11 | Nan, Inc. dba Ocean House Builders | W9128A-13-C-0001 | 37410.03 | 37733.657 | 2013-07-23 |  | 2015-09-01 | 2015-11-21 | 47.71%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | HAWAII | UNITED STATES | 76903 | Combat Aviation Brigade Barracks | 2012-11-26 | 2014-05-13 | Nan-Samsung, LLC | W9128A-14-C-0002 | 69749.203 | 69749.203 | 2014-06-26 |  | 2017-01-13 | 2017-01-13 | 0%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | GEORGIA | UNITED STATES | 77416 | Ground Source Heat Transfer System | 2013-04-04 | 2013-05-29 | R. C. Construction Co., Inc. | W912HN-10-D-0058 | 8295 | 8464.6715 | 2013-07-12 |  | 2015-01-03 | 2015-01-03 | 94%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | NEW YORK | UNITED STATES | 79933 | Cadet Barracks | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 72000 | 72259.616 | 2013-08-26 |  | 2016-08-30 | 2016-10-28 | 46.66%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction | MISSOURI | UNITED STATES | 79980 | WATER SUPPLY/TREATMENT BUILDING, POTABLE | 2013-05-17 | 2014-08-19 | Huffman Construction, LLC |  | 1437.6 | 1423.518 | 2013-09-23 |  | 2014-06-20 | 2014-11-30 | 81.81%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | NORTH CAROLINA | UNITED STATES | 80066 | Controlled Humidity Warehouse, Installatio | 2012-11-16 | 2013-09-20 | Tyler Construction Co., INC | W912HN-10-D-0060 | 6726.987 | 6769.3467 | 2013-11-06 |  | 2015-03-01 | 2015-04-08 | 43.99% | 8600 | 62955
2014-10-31 | 2013 | Army Active | Military Construction [Major] | NORTH CAROLINA | UNITED STATES | 80087 | Storage Building, General Purpose | 2012-07-16 | 2013-03-22 | Tyler Construction Group, Inc. | W912HN-10-D-0060 | 9037.592 | 9003.526 | 2013-04-18 |  | 2014-08-11 | 2015-01-19 | 67.95% | 12600 | 76235
2014-10-31 | 2013 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex | 2013-04-25 | 2013-08-15 | J&S Construction Company, Inc | W9126G-13-C-0039 | 11491.27 | 11423.509 | 2013-10-07 |  | 2015-05-30 | 2015-06-01 | 46.82%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 80113 | Unmanned Aerial Vehicle Complex | 2013-03-12 | 2014-05-29 | JAM-MAP JV |  | 5994.434 | 5994.434 | 2014-08-27 |  | 2016-01-04 | 2016-01-04 | 46.25%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar | 2012-12-12 | 2013-06-17 | VETCO Contracting Services, LLC | W912DS-09-D-0007 | 26825.868 | 27139.258 | 2013-06-27 |  | 2015-06-17 | 2015-06-17 | 30.44%
2014-10-31 | 2013 | Army Active | Military Construction [Major] | NEW YORK | UNITED STATES | 80246 | Aircraft Maintenance Hangar | 2012-12-12 | 2013-11-25 | VETCO Contracting Services, LLC |  | 21577.777 | 21559.066 | 2013-07-02 |  | 2015-06-22 | 2015-09-20 | 15%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80317 | WATER DISTRIBUTION LINES, POTABLE | 2013-08-14 | 2013-11-26 | FLBE, INC. | W912DR-14-C-0006 | 1790.839 | 1790.839 | 2014-01-13 |  | 2014-09-10 | 2014-12-10 | 5.982%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction | UTAH | UNITED STATES | 81106 | POLICE/MP STATION | 2013-06-11 | 2013-09-27 | Zumwalt Construction, Inc. | W91238-11-D-0026 | 1768.28 | 1768.28 | 2013-10-18 |  | 2014-12-17 | 2015-03-23 | 22.06%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 81320 | STORAGE BUILDING, GENERAL PURPOSE, INSTALL | 2013-08-08 | 2013-09-26 | Northcon, Inc. | W912DW-13-C-0047 | 1380.171 | 1380.171 | 2013-10-28 |  | 2014-10-28 | 2014-10-28 | 68.9%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | 81367 | EXPLOSIVES RECEIVING/SERVICE BUILDING, DEP | 2013-12-18 | 2014-04-16 | Cyber Professional Solution Corp | W912PL-14-C-0006 | 1783.729 | 1783.729 | 2014-05-08 |  | 2015-05-08 | 2015-05-08 | 55.47%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 81431 | ADMINISTRATIVE BUILDING, GENERAL PURPOSE | 2013-08-15 | 2014-06-17 | PORTICO SERVICES, LLC | W912DR-14-C-0028 | 1793.105 | 1798.8087 | 2014-07-15 |  | 2015-03-12 | 2015-03-12 | 18.25%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction |  | MARSHALL ISLANDS | 81462 | DIESEL OIL/JP8 STORAGE, ABOVE GROUND, BULK | 2014-08-21 | 2014-09-30 | Nan Inc | W9128A-12-D-0012 | 1555.718 | 1555.718 | 2014-10-28 |  | 2015-08-24 | 2015-08-24 | 0%
2014-10-31 | 2013 | Army Active | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | 81515 | CIDC FIELD OPERATIONS BUILDING | 2013-05-21 | 2013-09-29 | Guyco, Inc. | W9126G-09-D-0095 | 1784.466 | 1779.289 | 2013-12-04 |  | 2014-12-04 | 2014-12-04 | 74.72%
2014-10-31 | 2013 | Army Reserve | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 81597 | AMSA Addition/Alteration | 2013-08-27 | 2013-09-30 | FutureNet Group, Inc. | W912QR-13-D-0023 | 1379.863 | 1393.566 | 2013-10-09 |  | 2014-09-24 | 2014-12-31 | 35.12%
2014-10-31 | 2013 | Army Reserve | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 82067 | Unheated Storage Building | 2013-07-23 | 2013-12-05 | Komada, LLC | W912QR-14-C-0003 | 1626.125 | 1637.251 | 2013-12-23 |  | 2014-12-23 | 2014-12-15 | 88.95%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | VIRGINIA | UNITED STATES | 53584 | Adv Individual Training Barracks Cplx, Ph3 | 2014-05-13 | 2014-09-18 | Purcell Construction Corporation | W91236-14-C-0046 | 40036.48 | 40036.48 | 2014-10-09 |  | 2017-07-05 | 2018-06-15 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 54106 | Automated Multipurpose Machine Gun Range | 2013-12-24 | 2014-05-28 | TSS-Garco Joint Venture | W912DW-14-C-0012 | 7716 | 7716 | 2014-11-10 |  | 2015-12-06 | 2015-12-06 | 0%
2014-10-31 | 2014 | Army Reserve | Military Construction [Major] | NEW JERSEY | UNITED STATES | 65277 | Consolidated Dining Facility | 2014-01-09 | 2014-03-31 | Boro Developers, Inc. d.b.a. Boro Construction | W912QR-14-C-0015 | 10798.9 | 10798.9 | 2014-04-23 |  | 2015-09-30 | 2015-09-30 | 3.385%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex | 2013-08-28 | 2014-05-07 | Silver Mountain Construction, LLC | W911KB-14-C-0008 | 14180.4971 | 14180.4971 | 2014-05-15 |  | 2016-02-04 | 2016-04-19 | 9%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | ALASKA | UNITED STATES | 67116 | Aviation Battalion Complex | 2013-08-28 | 2014-04-14 | Arctic-American JV |  | 16180.297 | 16127.286 | 2014-04-23 |  | 2015-10-15 | 2015-12-16 | 29%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | NORTH CAROLINA | UNITED STATES | 69624 | Command and Control Facility | 2014-06-10 | 2014-07-21 | Brantley Construction Services, LLC | W912HN-10-D-0056 | 4720.25 | 4726.269 | 2014-08-27 |  | 2015-08-27 | 2015-08-27 | 4.037%
2014-10-31 | 2014 | Army Reserve | Military Construction [Major] | NEW JERSEY | UNITED STATES | 69669 | Central Issue Facility | 2014-01-31 | 2014-06-05 | Ranco Construction, Inc. | W912QR-14-C-0021 | 8783.22 | 8783.22 | 2014-07-07 |  | 2015-12-14 | 2015-12-14 | 0.8239%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 71221 | Fire Station | 2014-03-28 | 2014-07-24 | Mountain West Precast Concrete | W9128F-14-C-0022 | 11542.275 | 11811.525 | 2014-08-27 |  | 2016-02-18 | 2016-02-18 | 0.5233%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | MISSOURI | UNITED STATES | 71502 | Adv Individual Training Barracks Cplx, Ph1 | 2014-03-06 | 2014-07-10 | MW Builders, Inc. | W912DQ-14-C-4009 | 47777 | 48102.675 | 2014-08-05 |  | 2016-08-04 | 2016-08-04 | 3.289%
2014-10-31 | 2014 | Army Reserve | Military Construction [Major] | NEW JERSEY | UNITED STATES | 71769 | Modified Record Fire Range | 2014-08-06 | 2014-09-30 | RACC/ Nelcorp JV | W912QR-14-C-0060 | 4653 | 4653 |  |  | 2016-04-22 | 2016-04-22 | 0%
2014-10-31 | 2014 | Army Reserve | Military Construction [Major] | NORTH CAROLINA | UNITED STATES | 71900 | Army Reserve Center | 2014-07-29 | 2014-09-30 | ACC Construction Co Inc. | W912QR-14-C-0054 | 22129.201 | 22129.201 |  |  | 2016-09-29 | 2016-09-29 | 0%
2014-10-31 | 2014 | Army Reserve | Military Construction [Major] | WISCONSIN | UNITED STATES | 71999 | NCO Academy Dining Facility | 2013-12-12 | 2014-03-31 | Wilson Brigadier Joint Venture | W912QR-14-C-0013 | 5900 | 5900 | 2014-04-22 |  | 2015-08-25 | 2015-08-25 | 15.19%
2014-10-31 | 2014 | Army Reserve | Military Construction [Major] | CALIFORNIA | UNITED STATES | 72284 | TASS Training Center (TTC) | 2014-08-13 | 2014-09-30 | Bara Infoware Inc. | W912QR-14-C-0053 | 16186.7042 | 16186.7042 |  |  | 2016-09-13 | 2016-09-13 | 0%
2014-10-31 | 2014 | Army Active | Military Family Housing | WISCONSIN | UNITED STATES | 74861 | Family Housing New Construction | 2014-03-04 | 2014-07-31 | Carlson Constructors Corporation | W9128F-14-C-0050 | 21862.0909 | 21862.0909 | 2014-08-20 |  | 2016-08-09 | 2016-08-09 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | KANSAS | UNITED STATES | 76024 | Simulations Center | 2014-02-28 | 2014-07-02 | Carothers Construction, Inc. | W912DQ-14-C-4008 | 15630 | 15630 | 2014-09-02 |  | 2016-02-24 | 2016-02-24 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar | 2013-08-30 | 2014-06-18 | UNIT COMPANY | W911KB-14-C-0021 | 25546.7 | 25546.7 | 2014-06-30 |  | 2016-03-21 | 2016-09-02 | 2.482%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | ALASKA | UNITED STATES | 76601 | Aviation Storage Hangar | 2013-08-30 | 2014-04-10 | Tunista Construction, LLC |  | 9525 | 9486.903 | 2014-04-25 |  | 2015-10-16 | 2015-12-18 | 7%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar | 2014-06-25 | 2014-08-26 | Archer Western Federal JV | W912DW-14-C-0023 | 36998 | 36998 | 2014-09-23 |  | 2016-03-16 | 2016-03-16 | 0.5662%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | WASHINGTON | UNITED STATES | 76777 | Aircraft Maintenance Hangar | 2014-05-19 | 2014-09-03 | The Renew Group, Inc. |  | 1106.039 | 1106.039 | 2014-10-24 |  | 2015-04-22 | 2015-04-22 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77262 | Headquarters Building | 2014-02-28 | 2014-07-15 | Mirador Enterprises, Inc. | W9128F-14-C-0020 | 17165.0006 | 17165.0006 | 2014-08-21 |  | 2016-02-12 | 2016-02-12 | 0.6049%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77262 | Headquarters Building | 2014-03-11 | 2014-08-28 | Medvolt, LLC |  | 13195.378 | 13195.378 | 2014-10-08 |  | 2016-03-31 | 2016-03-31 | 1.1%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar | 2014-05-22 | 2014-08-07 | Swinerton Builders | W9128F-14-C-0031 | 56720.967 | 56720.967 | 2014-09-02 |  | 2016-08-22 | 2016-08-22 | 0.7123%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77304 | Aircraft Maintenance Hangar | 2014-05-22 | 2014-09-04 | SEK JV |  | 3339.182 | 3339.182 | 2014-10-20 |  | 2015-10-20 | 2015-10-20 | 11.37%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar | 2014-07-09 | 2014-09-12 | David Boland, Inc. | W9128F-14-C-0068 | 50585 | 50585 | 2014-10-06 |  | 2016-05-28 | 2016-05-28 | 0.6472%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77405 | Aircraft Maintenance Hangar | 2014-07-09 | 2014-06-19 | Swinerton Builders |  | 4214.264 | 4214.264 | 2014-07-22 |  | 2015-08-17 | 2015-08-17 | 3.649%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | FLORIDA | UNITED STATES | 77539 | Automated Sniper Field Fire Range | 2014-07-17 | 2014-09-26 | Barlovento LLC | W91278-10-D-0072 | 4201.077 | 4201.077 |  |  | 2015-12-15 | 2015-12-15 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 77885 | Runway | 2014-03-10 | 2014-06-12 | Federal Contracting Inc dba Bryan Construction | W9128F-14-C-0012 | 9832.807 | 9957.184 | 2014-07-01 |  | 2015-07-01 | 2015-07-01 | 9.51%
2014-10-31 | 2014 | Army Active | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 77980 | Cantonment Area, Roads, Paved | 2014-08-12 | 2014-09-16 | FutureNet Group, Inc. | W912QR-09-D-0050 | 1635.599 | 1635.599 | 2014-09-24 |  | 2015-08-20 | 2015-08-20 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | KENTUCKY | UNITED STATES | 78778 | Battlefield Weather Support Facility | 2013-12-24 | 2014-06-18 | TJC Engineering | W912QR-14-C-0018 | 4275.114 | 4275.114 | 2014-06-27 |  | 2015-08-21 | 2015-08-21 | 2.105%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | COLORADO | UNITED STATES | 79618 | Simulator Building | 2014-04-11 | 2014-07-21 | Mirador Enterprises, Inc. | W9128F-14-C-0021 | 8440 | 8440 | 2014-08-20 |  | 2016-02-11 | 2016-02-11 | 0.6844%
2014-10-31 | 2014 | Army Active | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 79679 | Materials Analysis Lab | 2014-02-03 | 2014-06-10 | Au' Authum Ki, Inc | W912PL-10-D-0109 | 2983.983 | 2983.983 | 2014-07-28 |  | 2015-02-23 | 2015-02-23 | 1.171%
2014-10-31 | 2014 | Army Active | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 80477 | Fragmentation Simulation Lab | 2013-04-22 | 2013-12-13 | The Clement Group, L.L.C. | W91278-11-D-0029 | 2341.157 | 2336.275 | 2014-01-23 |  | 2015-07-17 | 2015-07-17 | 19.79%
2014-10-31 | 2014 | Army Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80919 | Underground Electric Lines | 2014-08-12 | 2014-09-29 | Glen/Mar Construction, Inc. | W912DW-14-C-0029 | 1544.779 | 1544.779 | 2014-10-29 |  | 2015-10-29 | 2015-10-29 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | TEXAS | UNITED STATES | 81155 | Unmanned Aerial Vehicle Complex | 2014-05-02 | 2014-07-24 | Archer Western Federal JV | W9126G-14-C-0039 | 30197 | 30197 |  |  | 2016-04-23 | 2016-04-23 | 0%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | NEW YORK | UNITED STATES | 81186 | Cadet Barracks, Incr 2 | 2012-11-06 | 2013-08-08 | Walsh Construction Company II, LLC | W912DS-13-C-0032 | 40000 | 40041.208 | 2013-08-26 |  | 2016-07-08 | 2016-07-08 | 100%
2014-10-31 | 2014 | Army Active | Military Construction [Major] | MARYLAND | UNITED STATES | 81875 | Operations and Maintenance Facilities | 2013-12-02 | 2014-05-12 | Edifice-Schlosser JV, LLC | W912DR-14-C-0017 | 17891 | 19162.237 | 2014-05-23 |  | 2015-03-19 | 2015-04-29 | 25.81%
2014-10-31 | 2014 | Army Active | Unspecified Minor Military Construction |  | MARSHALL ISLANDS | 82371 | Power Plant Facility 994 | 2014-09-28 | 2014-09-30 | San Juan Construction, Inc. | W9128A-12-D-0010 | 1596.834 | 1596.834 | 2014-10-28 |  | 2015-08-24 | 2015-08-24 | 0%
2014-10-31 | 2014 | Army Active | Unspecified Minor Military Construction | GEORGIA | UNITED STATES | 85260 | Secure Operations Center | 2014-07-09 | 2014-09-30 | Kaiserkane, Inc. | W912HN-14-C-0022 | 1724.858 | 1724.858 | 2014-10-29 |  | 2015-10-29 | 2015-10-29 | 0%
2014-10-31 | 1905-07-04 | Army Active | Military Construction [Major] | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 79652 | Radar Security and Support Facilities | 2014-07-14 | 2014-07-28 | American Int'l Contractors Inc |  | 1366.6 | 1366.6 | 2014-07-29 |  | 2014-11-30 | 2014-11-30 | 82%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001004 | MOTOR TRANSPORTATION/COMM MAINTENANCE FAC | 2011-03-03 | 2011-06-02 | DCK NORTH AMERICA, LLC | N4008510D5329 0002 | 12906 | 12849 | 2011-06-16 | 2015-01-06 | 2012-12-01 | 2014-01-15 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695005 | PAINT AND BLAST FACILITY | 2011-04-29 | 2011-09-16 | SAUER, INC. | N6945009D1277 0005 | 20345 | 19808 | 2011-09-30 | 2014-03-10 | 2013-05-16 | 2014-01-24 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813005 | JOINT POW/MIA ACCOUNTING, USPACOM | 2010-10-13 | 2011-06-06 | NAN INC. DBAOCEAN HOUSE BUILDERS | N6274211C1300 AWD | 95540 | 83521 | 2011-06-20 | 2014-11-24 | 2013-07-05 | 2014-10-02 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318006 | PHYSICAL FITNESS CENTER, CAMP SMITH | 2011-01-06 | 2011-06-16 | AMEC - NAN JOINT VENTURE | N6274209D1171 HC01 | 28891 | 28102 | 2011-06-30 | 2014-04-03 | 2013-03-07 | 2014-04-04 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695012 | CONTAINER STAGING AND LOADING LOT | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3380 | 2529 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811014 | TRUCK COMPANY OPERATIONS COMPLEX | 2011-06-06 | 2011-09-22 | STRAUB-DRIVER A JOINT VENTURE | N6247311C0405 AWD | 52425 | 48972 | 2011-10-06 | 2015-06-03 | 2013-09-21 | 2013-10-06 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N61007015 | CALIBRATION FACILITY LAND ACQUISITION |  | 2011-12-31 | Land Acquisition |  | 3149 | 3080 | 2012-01-14 |  |  |  | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695017 | HARDSTAND EXTENSION | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 12623 | 7904 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695022 | CONSOLIDATED WAREHOUSE FACILITY | 2010-11-22 | 2011-06-03 | SAUER, INC. | N6945009D1277 0003 | 13295 | 11139 | 2011-06-17 | 2013-12-20 | 2012-07-27 | 2013-12-20 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695023 | WASHRACK EXPANSION | 2011-03-03 | 2011-06-01 | BARLOVENTO L.L.C. | N6945011D1259 0002 | 8877 | 8449 | 2011-06-15 | 2013-06-10 | 2012-11-19 | 2013-06-30 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | FLORIDA | UNITED STATES | M67695024 | CONTAINER STORAGE LOT | 2010-11-26 | 2011-06-03 | MCCARTHY IMPROVEMENT COMPANY | N6945011C1255 AWD | 3702 | 3369 | 2011-06-17 | 2013-12-05 | 2013-12-05 | 2013-12-05 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813056 | CENTER FOR DISASTER MANAGEMENT/HUMANITARIAN ASSISTANCE | 2011-02-04 | 2011-06-24 | FOPCO, INC | N6247810D4019 0006 | 7856 | 9024 | 2011-07-08 | 2013-06-03 | 2012-08-15 | 2013-04-30 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411068 | ELECTROMAGNETIC SENSOR FACILITY | 2011-03-16 | 2011-08-09 | SUFFOLK CONSTRUCTION CO INC | N4008511C7231 AWD | 24394 | 26540 | 2011-08-23 | 2014-03-24 | 2013-08-22 | 2014-09-26 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011034 | 2ND INTEL BN OPERATIONS COMPLEX | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 79767 | 80479 | 2011-07-13 | 2014-12-15 | 2014-02-28 | 2014-12-15 | 92%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811043A | NORTH REGION TERTIARY TREATMENT PLANT INC 2 OF 2 | 2010-10-29 | 2010-10-29 | CDM-FILANC JV | N6247310C5011 PC000001 | 29295 | 25269 | 2010-11-12 | 2015-02-17 | 2012-10-12 | 2015-08-21 | 51%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811044 | CONVEYANCE/WATER TREATMENT | 2012-06-20 | 2012-09-29 | CH2M HILL CONSTRUCTORS, INC. | N6247312C5033 AWD | 98236 | 82663 | 2012-10-13 | 2016-12-06 | 2016-01-13 | 2016-01-13 | 29%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604109 | CNAT/FRS AVIATION TRAINING AND BEQ | 2011-05-11 | 2011-09-12 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0434 AWD | 51999 | 45733 | 2011-09-26 | 2014-06-23 | 2014-01-08 | 2014-06-23 | 100% | -11300 | N61151162, Sequestration Reprogramming
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811109 | BACHELOR ENLISTED QUARTERS, LAS FLORES | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 36173 | 33960 | 2011-10-13 | 2014-06-05 | 2013-10-13 | 2014-10-17 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604111 | MALS-39 MAINTENANCE HANGAR EXPANSION | 2011-03-31 | 2011-06-22 | RQ CONSTRUCTION, LLC | N6247310D5409 0003 | 47061 | 33362 | 2011-07-06 | 2013-10-29 | 2013-03-13 | 2013-10-29 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811113 | BACHELOR ENLISTED QUARTERS, 24 AREA | 2011-06-23 | 2011-09-29 | HARPER CONSTRUCTION COMPANY, INC | N6247311C0406 AWD | 41889 | 39164 | 2011-10-13 | 2014-06-05 | 2013-10-13 | 2014-10-17 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811200 | MARINE CORPS ENERGY INITIATIVE | 2011-04-20 | 2011-07-26 | STRONGHOLD ENGINEERING INC | N6247310D5483 0003 | 9779 | 9567 | 2011-08-09 | 2013-06-21 | 2012-08-04 | 2014-01-16 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011240 | MAINTENANCE/OPS COMPLEX, 2ND ANGLICO | 2011-02-23 | 2011-06-29 | UNIVERSAL CONSTRUCTION COMPANY INC.DBA TURNER/UNIVERSAL | N4008511C4000 AWD | 32625 | 30659 | 2011-07-13 | 2014-12-15 | 2014-02-28 | 2014-12-15 | 93%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011246 | EOD ADDITION, 2ND MARINE LOGISTICS GROUP | 2011-05-18 | 2011-06-27 | JOYCE & ASSOCIATES CONSTRUCTION INC | N4008510D0259 0007 | 6613 | 6013 | 2011-07-11 | 2013-05-13 | 2012-08-20 | 2013-07-31 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011249 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 43950 | 40294 | 2011-07-13 | 2015-03-02 | 2013-07-13 | 2015-04-11 | 99%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011251 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 40236 | 38214 | 2011-09-14 | 2015-02-15 | 2013-10-08 | 2014-06-24 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011254 | BACHELOR ENLISTED QUARTERS, COURTHOUSE BAY | 2011-05-10 | 2011-08-31 | HARPER CONSTRUCTION COMPANY, INC | N4008511C4009 AWD | 39788 | 37917 | 2011-09-14 | 2015-02-15 | 2013-10-08 | 2014-06-24 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011256 | MESS HALL ADDITION, COURTHOUSE BAY | 2010-12-21 | 2011-06-02 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0006 | 1499 | 1379 | 2011-06-16 | 2012-11-25 | 2012-11-25 | 2012-11-25 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011264 | UTILITY EXPANSION, HADNOT POINT | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 55206 | 55212 | 2011-10-10 | 2014-09-16 | 2013-10-22 | 2014-07-31 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011265 | UTILITY EXPANSION, FRENCH CREEK | 2011-07-15 | 2011-09-26 | S. T. WOOTEN CORPORATION | N4008511C4030 AWD | 54795 | 46483 | 2011-10-10 | 2014-09-16 | 2013-10-22 | 2014-07-31 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011267 | MESS HALL, FRENCH CREEK | 2010-12-08 | 2011-06-02 | ENVIRO AGSCIENCE, INC | N4008511C4022 AWD | 24316 | 17444 | 2011-06-16 | 2014-03-07 | 2013-02-06 | 2013-10-25 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011286 | BACHELOR ENLISTED QUARTERS, RIFLE RANGE | 2011-04-29 | 2011-08-30 | BALFOUR BEATTY CONSTRUCTION, LLCBALFOUR BEATTY CONSTRUCTION | N4008511C4008 AWD | 54720 | 55079 | 2011-09-13 | 2015-02-01 | 2013-09-07 | 2014-03-22 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681310 | SMALL ARMS MAGAZINE, EDSON RANGE | 2011-03-30 | 2011-06-07 | KOO CONSTRUCTION INC | N6247309D1618 0004 | 3760 | 3164 | 2011-06-21 | 2014-10-27 | 2012-07-06 | 2014-09-26 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011317 | BACHELOR ENLISTED QUARTERS, FRENCH CREEK | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4021 AWD | 43568 | 40943 | 2011-06-16 | 2015-01-04 | 2013-08-30 | 2015-01-04 | 98.83%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011319 | BACHELOR ENLISTED QUARTERS, CAMP JOHNSON | 2011-02-04 | 2011-06-02 | ANDALE-SUNDT, A JOINT VENTURE | N4008511C4020 AWD | 46005 | 42198 | 2011-06-16 | 2014-08-29 | 2013-08-13 | 2014-04-14 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011322 | BACHELOR ENLISTED QUARTERS, WALLACE CREEK NORTH | 2011-02-24 | 2011-06-29 | RQ/BRASFIELD GORRIE JV | N4008511C4001 AWD | 49005 | 44548 | 2011-07-13 | 2015-03-02 | 2013-07-13 | 2015-04-11 | 96%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011323 | ARMORY II MEF, WALLACE CREEK | 2011-02-24 | 2011-12-06 | RQ/BRASFIELD GORRIE JV | N4008511C4001 P00004 | 5941 | 5401 | 2011-12-20 | 2015-03-02 | 2013-07-13 | 2015-04-11 | 97% | -4148 | M00681159
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146136 | BACHELOR ENLISTED QUARTERS | 2010-12-01 | 2011-06-02 | KISAQ-RQ 8A 2 JV | N4008511C4026 AWD | 42882 | 42013 | 2011-06-16 | 2015-02-25 | 2013-07-07 | 2014-05-07 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011400 | MARINE CORPS ENERGY INITIATIVE | 2010-10-08 | 2011-05-31 | URS-IAP LLC | N6247006D6009 0016-02 | 8868 | 8147 | 2011-06-14 | 2012-12-06 | 2012-09-27 | 2012-12-31 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146148 | MISSILE MAGAZINE | 2010-10-21 | 2011-06-02 | SAUER, INC. | N4008511C4010 P00003 | 4779 | 4779 | 2011-06-16 | 2014-01-23 | 2012-07-10 | 2013-11-04 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865152 | PARKING APRON/TAXIWAY EXPANSION | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 32816 | 35427 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 100% | -28591 | N50092499, N60191527, Design, N47608561
2014-10-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151162 | AGILE CHEMICAL FACILITY PHASE 2 | 2011-09-07 | 2012-08-10 | JOHN C. GRIMBERG CO., INC. | N4008012C2001 AWD | 34869 | 36116 | 2012-08-24 | 2015-06-26 | 2014-06-16 | 2015-06-26 | 64%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399163 | BACHELOR ENLISTED QUARTERS/PARKING STRUCTURE | 2010-07-02 | 2011-06-03 | STRAUB MARTIN A JOINT VENTURE | N6247310C5007 PC000001 | 51987 | 51426 | 2011-06-17 | 2014-04-24 | 2012-10-12 | 2013-06-17 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146164 | MARINER'S BAY LAND ACQUISITION BOGUE |  | 2011-07-01 | Land Acquisition |  | 4002 | 3706 | 2011-07-15 |  |  |  | 93%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146176 | STATION INFRASTRUCTURE UPGRADES | 2011-02-02 | 2011-06-01 | QUADRANT CONSTRUCTION, INC | N4008510D0261 0003 | 5850 | 7300 | 2011-06-15 | 2013-10-10 | 2012-11-25 | 2013-10-10 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865185 | HANGAR 4 ADDITION | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 27121 | 27749 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 100% | -4000 | M00681159, Design
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865192 | GTF-HANGAR MODIFICATION (HMT-302) | 2011-06-14 | 2011-09-20 | HENSEL PHELPS GRANITE HANGAR JOINT | N6247311C0401 AWD | 56417 | 54528 | 2011-10-04 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 100% | -30605 | N50092499, Design
2014-10-31 | 2011 | Navy Active | Major Military Construction |  | JAPAN | N61057203 | AVIATION SIMULATOR TRAINING FACILITY | 2010-12-09 | 2011-07-29 |  |  | 6764 | 6442 | 2011-08-12 | 2013-11-13 | 2013-11-13 | 2013-11-13 | 100% |  |  | Awarded by Other Agency
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N61755204A | APRA HARBOR WHARF IMPROVEMENT, INC 2 OF 2 | 2012-09-28 | 2012-11-28 | OVERLAND FEDERAL, LLC | N4019210D2803 0006 | 21579 | 16523 | 2012-12-12 | 2014-09-29 | 2014-06-19 | 2014-09-30 | 99.59%
2014-10-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A219 | GENERAL WAREHOUSE | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 7716 | 7640 | 2012-04-16 | 2014-10-31 | 2013-12-26 | 2014-08-24 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N60042260 | LAND ACQUISITION OF PARCEL 52-A & 52-C |  | 2011-09-29 | Land Acquisition |  | 1421 | 1658 | 2011-10-13 |  |  |  | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608263 | BROAD AREA MARITIME SURVEILLANCE T&E FAC | 2010-10-08 | 2011-06-02 | HENSEL PHELPS CONSTRUCTION CO. | N4008011C0154 AWD | 33033 | 34715 | 2011-06-16 | 2013-07-31 | 2012-07-30 | 2014-07-16 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | ALABAMA | UNITED STATES | N60508266 | PROVIDE T-6 SOLO CAPABLE OUTLYING LANDING FIELD | 2012-07-05 | 2012-09-28 | HEAD, INC. | N6945012C0760 AWD | 29901 | 25753 | 2012-10-12 | 2014-09-28 | 2014-09-28 | 2014-11-26 | 70%
2014-10-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245327 | BERTHING PIER 12 REPL & DREDGING | 2011-08-05 | 2011-09-29 | MANSON CONSTRUCTION CO | N6247311C2850 AWD | 99132 | 90207 | 2011-10-13 | 2013-10-22 | 2013-10-22 | 2014-03-11 | 100% | -1813 | N61151162
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243400 | MARINE CORPS ENERGY INITIATIVE | 2010-11-19 | 2011-06-03 | DYNALECTRIC COMPANY INC | N6247310D5480 0012 | 9928 | 9373 | 2011-06-17 | 2012-06-15 | 2012-06-17 | 2012-07-11 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245405 | BACHELOR QUARTERS HOMEPORT ASHORE | 2011-08-23 | 2011-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247311C2804 AWD | 72294 | 69777 | 2011-10-14 | 2013-12-03 | 2013-10-23 | 2013-12-03 | 100% | -3179 | N42237100
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169420 | PHYSICAL FITNESS CENTER, BEAUFORT | 2011-04-01 | 2011-09-07 | HIGHTOWER CONSTRUCTION CO., INC. | N6945011C1760 AWD | 14780 | 14868 | 2011-09-21 | 2013-05-24 | 2013-06-08 | 2013-07-16 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169444 | TRAINING AND SIMULATOR FACILITY | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 40940 | 38701 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974447A | AIRCRAFT MAINTENANCE HANGAR (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 30492 | 29300 | 2011-06-23 | 2013-12-05 | 2012-10-08 | 2013-10-15 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169454 | F-35B AIRCRAFT HANGAR FOR FRS-2 | 2010-10-25 | 2011-06-06 | HENSEL PHELPS CONSTRUCTION CO | N6945011C1756 AWD | 45398 | 45872 | 2011-06-20 | 2014-06-17 | 2014-03-11 | 2014-06-09 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974460 | AIRCRAFT MAINTENANCE HANGAR, PHASE 2 (JSF) | 2010-10-15 | 2011-06-09 | DCK/TTEC, LLC | N6274209D1172 FZN1 | 47715 | 46237 | 2011-06-23 | 2013-12-05 | 2012-10-08 | 2013-10-15 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443516A | SHIP REPAIR PIER REPLACEMENT INC 2 OF 2 | 2010-05-27 | 2011-03-31 | SKANSKA USA CIVIL SOUTHEAST INC | N4008510C3006 P00003 | 68459 | 66000 | 2011-04-14 | 2015-10-02 | 2014-11-22 | 2015-10-02 | 71%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974533 | SIMULATOR FACILITY (JSF) | 2011-01-07 | 2011-06-03 | SUNDT CONSTRUCTION, INC. | N6247310D5408 0002 | 26438 | 23252 | 2011-06-17 | 2013-04-19 | 2012-06-02 | 2013-04-19 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264541 | ADDITION, MCU RESEARCH CENTER | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 31343 | 29406 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2015-01-02 | 96% | -3531 | Sequestration Reprogramming
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974546 | UTILITY UPGRADES (JSF) | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 40106 | 36761 | 2011-06-21 | 2013-06-14 | 2012-07-08 | 2013-06-14 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264566 | STUDENT QUARTERS, THE BASIC SCHOOL, PHASE 5 | 2011-06-20 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 45465 | 34444 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 23.41% | -8039 | Sequestration Reprogramming
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974573 | INTERMEDIATE MAINT ACTIVITY FACILITY (JSF) | 2011-03-31 | 2011-07-27 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0002 | 19793 | 16188 | 2011-08-10 | 2012-12-14 | 2012-07-25 | 2012-12-14 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974578 | VAN PAD RELOCATION (JSF) | 2011-07-19 | 2011-09-12 | BILBRO CONSTRUCTION COMPANY | N6247309D1653 0003 | 15045 | 14670 | 2011-09-26 | 2013-01-22 | 2012-09-11 | 2012-09-11 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974583 | COMMUNICATION INFRASTRUCTURE UPGRADE (JSF) | 2010-10-27 | 2011-06-07 | DCK/TTEC, LLC | N6274209D1172 FZN0 | 54843 | 54497 | 2011-06-21 | 2013-06-14 | 2012-07-08 | 2013-06-14 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264599 | BACHELOR ENLISTED QUARTERS, THE BASIC SCHOOL | 2011-04-15 | 2011-09-30 | URS GROUP, INC. | N6274209D1174 JU01 | 34087 | 31012 | 2011-10-14 | 2013-09-26 | 2013-08-09 | 2014-04-30 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237601 | SECURITY ENCLAVE AND VEHICLE BARRIER | 2011-12-13 | 2012-03-16 | SAUER, INC. | N6945009D1277 0007 | 37278 | 39573 | 2012-03-30 | 2013-09-07 | 2013-09-07 | 2014-09-30 | 99.59% | -5445 | Sequestration Reprogramming
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264615 | SNCO ACADEMIC FACILITY ADDITION | 2011-02-09 | 2011-06-20 | TTEC-TESORO JOINT VENTURE | N4008010D0493 0002 | 6836 | 6730 | 2011-07-04 | 2013-07-22 | 2012-12-21 | 2013-05-31 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237620 | WATERFRONT EMERGENCY GENERATORS | 2011-05-06 | 2011-08-19 | CMS CORP/TOLTEST JV IV | N6945010D1271 0003 | 15010 | 16815 | 2011-09-02 | 2013-05-13 | 2013-05-13 | 2014-10-09 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001683 | HANGAR | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62154 | 58251 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 91.42%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001687 | MV-22 MAINTENANCE HANGAR (HMLA) | 2010-08-31 | 2011-06-03 | THE HASKELL COMPANY | N4008511C4019 AWD | 62617 | 59661 | 2011-06-17 | 2015-03-17 | 2013-11-29 | 2015-03-17 | 90.61%
2014-10-31 | 2011 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246750 | ROTARY HANGAR | 2011-05-16 | 2012-01-31 | HENSEL PHELPS CONSTRUCTION CO | N6247312C1406 P00001 | 64063 | 63857 | 2012-02-14 | 2013-12-10 | 2012-04-16 | 2014-03-11 | 100% | -1557 | N42237100
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318816 | WATERFRONT OPERATIONS FACILITY | 2011-02-07 | 2011-06-30 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 0006 | 16634 | 15092 | 2011-07-14 | 2015-01-30 | 2013-11-16 | 2014-04-14 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688828 | DDG 1000 UPGRADES TO PIERS 9 AND 10 UPGRADE | 2010-12-13 | 2011-06-14 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008511D6585 0001 | 1395 | 1273 | 2011-06-28 | 2012-11-07 | 2012-06-18 | 2012-11-07 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436843 | CSDS-5 LABORATORY EXPANSION PHASE ! | 2011-01-31 | 2011-06-03 | SAN JUAN CONSTRUCTION INC | N4425510D5006 0005 | 16042 | 16448 | 2011-06-17 | 2013-09-24 | 2012-10-15 | 2014-04-04 | 100%
2014-10-31 | 2011 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318858 | BACHELOR ENLISTED QUARTERS | 2011-02-18 | 2011-08-31 | HAWAIIAN DREDGING CONTRUCTIONCOMPANY INC | N6247811C1492 AWD | 62691 | 60599 | 2011-09-14 | 2015-03-31 | 2014-08-21 | 2014-12-11 | 92% | -17925 | N60191527, N60191582, Sequestration Reprogramming
2014-10-31 | 2011 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688862 | PIER 1 UPGRADES TO BERTH USNS COMFORT | 2011-04-22 | 2011-07-26 | W.F. MAGANN CORPORATION | N4008511C0020 AWD | 3659 | 2953 | 2011-08-09 | 2012-09-18 | 2012-08-09 | 2012-09-28 | 100% | -6185 | M00681159, N42237100
2014-10-31 | 2011 | Navy Active | Major Military Construction |  | SPAIN | N62863897 | AIR TRAFFIC CONTROL TOWER | 2012-01-13 | 2012-06-15 | SACYR SA | N3319112C0603 AWD | 19080 | 15665 | 2012-06-29 | 2015-09-30 | 2014-09-03 | 2015-01-04 | 62% | -2052 | N42237100
2014-10-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005908 | CONSOLIDATED OPERATIONS & SUPPORT FACILITY | 2012-04-12 | 2012-08-17 | NAVY STANDARD DOCUMENT |  | 41151 | 38522 | 2012-08-31 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 48% | -15471 | Sequestration Reprogramming
2014-10-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436910 | WATERFRONT RESTRICTED AREA EMERGENCY POWER | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 14315 | 14812 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-05-15 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A912 | PAVE EXTERNAL ROADS | 2011-10-19 | 2012-04-02 | ECC MEZZ LLC | N3319112C0620 AWD | 3107 | 2658 | 2012-04-16 | 2014-10-31 | 2013-12-26 | 2014-08-24 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction |  | BAHRAIN | N63005954 | WATERFRONT DEVELOPMENT, PHASE 3 | 2011-06-30 | 2012-02-29 | NAVY STANDARD DOCUMENT |  | 40713 | 40237 | 2012-03-14 | 2014-11-26 | 2014-11-26 | 2014-11-26 | 83.61% | -19865 | Sequestration Reprogramming
2014-10-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436973F | LIMITED AREA PRODUCTION/STRG CMPLX INC 7 OF 7 | 2006-11-20 | 2010-11-10 | KIEWIT-GENERAL, A JOINT VENTURE | N4425508C6003 PC000094 | 20026 | 19450 | 2010-11-24 | 2012-06-01 | 2011-11-08 | 2012-10-29 | 100%
2014-10-31 | 2011 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436987 | EMERGENCY GENERATOR, LIMITED AREA | 2010-11-18 | 2011-06-03 | WALSH CONSTRUCTIONCOMPANY OF ILLINOIS | N4425511C9011 AWD | 11275 | 10432 | 2011-06-17 | 2013-07-10 | 2013-06-26 | 2014-05-15 | 100%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001030 | SQUAD BATTLE COURSE | 2012-05-01 | 2012-06-21 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0003 | 16292 | 14381 | 2012-07-05 | 2014-12-01 | 2014-05-17 | 2014-09-22 | 100%
2014-10-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813041 | NAVY INFORMATION OPERATIONS COMMAND FES FACILITY | 2011-10-26 | 2012-04-05 | RAASS BROTHERS INC. | N6247810D4022 0019 | 7708 | 7642 | 2012-04-19 | 2014-11-09 | 2013-11-16 | 2014-11-09 | 98%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811037 | INDIVIDUAL EQUIPMENT ISSUE WAREHOUSE | 2011-07-28 | 2012-03-23 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0002-PC000002 | 11746 | 9512 | 2012-04-06 | 2013-08-05 | 2013-01-21 | 2013-08-05 | 100% | -760 | N00246909
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811040 | INTERSECTION BRIDGE AND IMPROVEMENTS | 2012-06-25 | 2012-08-24 | REYES CONSTRUCTION INC | N6247309D1606 0009 | 11432 | 13971 | 2012-09-07 | 2014-05-23 | 2013-09-27 | 2014-06-24 | 100%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811045 | NEW POTABLE WATER CONVEYANCE | 2012-06-18 | 2012-09-28 | FILANC-ORION JOINT VENTURE | N6247312C5032 AWD | 85242 | 61529 | 2012-10-12 | 2016-12-21 | 2016-03-31 | 2016-03-31 | 26% | -16682 | N684691400
2014-10-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N68469110 | REPLACE CONDEMNED COATINGS LABORATORY | 2012-07-03 | 2012-08-28 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0019 | 3805 | 3998 | 2012-09-11 | 2014-04-24 | 2013-08-28 | 2014-05-30 | 100%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604114 | MV-22 DOUBLE HANGAR REPLACEMENT | 2012-03-19 | 2012-07-20 | BALFOUR BEATTY CONSTRUCTION, LLC | N6247310D5407 0004 | 40539 | 38828 | 2012-08-03 | 2015-12-14 | 2015-08-10 | 2015-08-10 | 40% | -6761 | N684691400
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604116 | MV-22 AVIATION PAVEMENT | 2012-04-12 | 2012-07-12 | PAVE-TECH INC | N6247309D1605 0012 | 14938 | 9643 | 2012-07-26 | 2015-03-30 | 2014-01-03 | 2014-02-27 | 100% | -856 | N684691400
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604117 | MV-22 AVIATION FUEL STORAGE | 2013-08-01 | 2013-11-07 | WESTON SOLUTIONS, INC | N6247007D7000 FZN7 | 7437 | 7215 | 2013-11-21 |  |  | 2015-10-07 | 28%
2014-10-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688123 | BACHELOR QUARTERS, HOMEPORT ASHORE | 2012-02-07 | 2012-08-31 | CLARK CONSTRUCTION GROUP LLC | N4008512C4572 AWD | 74854 | 72185 | 2012-09-14 | 2015-05-31 | 2014-09-13 | 2015-03-26 | 79% | -3084 | N684691400
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011253 | 2D COMBAT ENGINEER MAINTENANCE/OPS CENTER | 2012-01-12 | 2012-04-30 | RQ CONSTRUCTION, LLC | N4008512C7719 AWD | 74707 | 72366 | 2012-05-14 | 2015-03-12 | 2014-07-24 | 2015-02-19 | 87%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001138 | BACHELOR ENLISTED QUARTERS , WALLACE CREEK | 2012-03-30 | 2012-06-29 | HOMELAND CONTRACTING CORP | N4008512C7704 AWD | 26101 | 26038 | 2012-07-13 | 2014-12-15 | 2014-07-29 | 2014-08-30 | 100%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011383 | BASE ENTRY POINT AND ROAD | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 64235 | 61342 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 67.12%
2014-10-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207153 | BAMS UAS OPERATOR TRAINING FACILITY | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 2851 | 2936 | 2012-07-09 | 2014-03-24 | 2013-12-17 | 2014-04-09 | 100% | -1321 | N42237100
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399177 | MULTI-USE OPERATIONAL FITNESS AREA | 2012-04-19 | 2012-08-13 | T. B. PENICK & SONS, INC. | N6247309D1651 0004 | 18819 | 20049 | 2012-08-27 | 2016-02-15 | 2014-09-02 | 2016-02-15 | 18.69%
2014-10-31 | 2012 | Navy Active | Major Military Construction |  | DIEGO GARCIA | N68539184 | POTABLE WATER PLANT MODERNIZATION | 2012-10-25 | 2012-12-21 | G4S-SJC, LLC | N4008413C0001 AWD | 30101 | 28232 | 2013-01-04 | 2015-08-26 | 2015-07-30 | 2015-08-26 | 69.35%
2014-10-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N57095197 | DECENTRALIZE STEAM SYSTEM | 2012-04-17 | 2012-09-20 | SAUER, INC. | N4008509D5026 0004 | 27161 | 26580 | 2012-10-04 | 2015-03-09 | 2015-05-08 | 2015-05-08 | 79%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399212 | CHILD DEVELOPMENT CENTER | 2012-02-10 | 2012-06-05 | T. B. PENICK & SONS, INC. | N6247310D5412 0006 | 21313 | 20423 | 2012-06-19 | 2015-05-19 | 2013-12-12 | 2015-05-19 | 32%
2014-10-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N61151222 | DECENTRALIZE STEAM SYSTEM | 2012-01-24 | 2012-09-28 | CLARK/BELL, A JOINT VENTURE | N4008012C0151 AWD | 69984 | 68673 | 2012-10-12 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 77%
2014-10-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443383 | CONTROLLED INDUSTRIAL FACILITY | 2012-02-14 | 2012-05-31 | MEB GENERAL CONTRACTORS, INC. | N4008512C4554 AWD | 60576 | 32021 | 2012-06-14 | 2015-07-31 | 2014-09-28 | 2015-03-23 | 34.16% | -7621 | N684691400
2014-10-31 | 2012 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N61064400 | NORTH LOOP ELECTRICAL REPLACEMENT | 2011-11-14 | 2012-03-15 | SUMO-NAN JV II LLC | N6247811D4046 0005 | 6498 | 5879 | 2012-03-29 | 2013-12-24 | 2014-01-02 | 2014-01-02 | 100% | -2776 | N42237100
2014-10-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436419 | INTEGRATED DRY DOCK WATER TREATMENT FAC, PHASE 1 | 2012-03-05 | 2012-05-25 | NOVA GROUP INC | N4425510D5019 0002 | 13341 | 10555 | 2012-06-08 | 2013-06-27 | 2013-12-24 | 2014-11-10 | 88.99%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169442 | VERTICAL LANDING PADS FOR F-35B | 2011-12-06 | 2012-03-30 | HEAD, INC. | N6945012C1758 AWD | 18987 | 18045 | 2012-04-13 | 2013-10-21 | 2013-08-07 | 2013-09-27 | 100%
2014-10-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N50092499 | POWER DISTRIBUTION UPGRADES | 2012-07-10 | 2012-09-24 | DRISKILL, J. C., INC. | N4008512C1704 AWD | 29520 | 28095 | 2012-10-08 | 2014-11-21 | 2014-10-09 | 2014-11-23 | 93.07%
2014-10-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201503 | MASSEY AVENUE CORRIDOR IMPROVEMENTS | 2012-04-03 | 2012-08-15 | TMG SERVICES, INC | N6945012C0757 AWD | 7518 | 9913 | 2012-08-29 | 2014-02-21 | 2014-02-21 | 2014-02-18 | 100%
2014-10-31 | 2012 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191527 | SOF PERIMETER SECURITY & MAIN ENTRY IMPROVEMENTS | 2012-06-15 | 2012-09-27 | TESORO CORPORATION | N4008509D5027 0005 | 18599 | 17872 | 2012-10-11 | 2015-04-01 | 2014-10-12 | 2014-12-02 | 62.89%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00681532 | ARMORY, 1ST MARINE DIVISION | 2012-04-23 | 2012-08-31 | A&D GC INC | N6247309D1658 0006 | 11201 | 10462 | 2012-09-14 | 2014-04-23 | 2013-12-24 | 2013-12-24 | 100%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974535 | AIRCRAFT MAINTENANCE HANGAR (JSF) | 2012-07-16 | 2012-09-06 | HARPER CONSTRUCTION COMPANY, INC | N6247308D8617 0004 | 32048 | 31722 | 2012-09-20 | 2014-08-06 | 2014-07-07 | 2014-11-03 | 96% | -5983 | N684691400
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67399541 | MULTI-PURPOSE BUILDING ADDITION | 2012-04-04 | 2012-09-27 | KOO CONSTRUCTION INC | N6247309D1655 0003 | 15610 | 13362 | 2012-10-11 | 2014-04-20 | 2014-04-20 | 2014-04-20 | 100%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264543 | WASTE WATER TREATMENT PLANT, CAMPT UPSHUR | 2012-06-28 | 2012-09-11 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0020 | 11118 | 11221 | 2012-09-25 | 2014-10-10 | 2014-03-28 | 2014-10-10 | 100%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974545 | DOUBLE AIRCRAFT MAINTENANCE HANGAR (JSF) | 2011-11-30 | 2012-03-20 | HARPER CONSTRUCTION COMPANY, INC | N6247310D5406 0003 | 79917 | 78060 | 2012-04-03 | 2014-06-24 | 2014-05-20 | 2014-10-24 | 100%
2014-10-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232559 | E-2D AIRCREW TRAINING FACILITY | 2012-03-21 | 2012-06-29 | ALLEN ENGINEERING CONTRACTOR, INC | N6247309D1658 0012 | 13210 | 15569 | 2012-07-13 | 2014-06-25 | 2013-10-07 | 2014-09-23 | 100%
2014-10-31 | 2012 | Navy Active | Major Military Construction | MARYLAND | UNITED STATES | N47608561 | AIRCRAFT PROTOTYPE FACILITY, PHASE 2 | 2011-10-14 | 2014-06-30 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0008 | 49890 | 46753 | 2014-07-14 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2.421%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264567 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 6 | 2011-10-05 | 2012-11-30 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 AWD | 27222 | 23826 | 2012-12-14 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 31.23%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264571 | REALIGN PURVIS RD/RUSSELL RD INTERSECTION | 2012-03-27 | 2012-07-27 | CORINTHIAN CONTRACTORS, INC | N4008010D0497 0011 | 6555 | 7003 | 2012-08-10 | 2014-09-26 | 2013-09-05 | 2014-12-30 | 75%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974575 | AUXILIARY LANDING FIELD (JSF) | 2012-04-16 | 2012-06-25 | SUNDT CONSTRUCTION, INC. | N6247312C1802 AWD | 29475 | 28481 | 2012-07-09 | 2014-02-21 | 2013-06-25 | 2014-01-31 | 100% | -5128 | N42237636
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264611 | BACHELOR ENLISTED QUARTERS | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 32910 | 31666 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-03-18 | 71%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264612 | ENLISTED DINING FACILITY | 2012-04-26 | 2012-09-29 | WHITING-TURNER CONTRACTING CO | N4008010D0494 0008 | 5028 | 5137 | 2012-10-13 | 2015-01-13 | 2014-10-16 | 2015-03-18 | 91%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264621 | EMBASSY SECURITY GROUP FACILITIES | 2012-09-14 | 2013-02-28 | ARGO SYSTEMS, LLC | N4008013C0002 AWD | 26081 | 25376 | 2013-03-14 | 2015-08-15 | 2015-03-15 | 2015-03-25 | 45%
2014-10-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207624 | P-8A TRAINING FACILITY | 2012-02-15 | 2012-06-25 | ELKINS CONSTRUCTORS, INC. | N6945012C1256 AWD | 14194 | 13885 | 2012-07-09 | 2014-03-24 | 2013-12-17 | 2014-04-09 | 100% | -11437 | N42237636, N42237100
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264632 | ACADEMIC INSTRUCTION FACILITY | 2012-05-21 | 2012-09-25 | CDM SMITH/COAKLEY WILLIAMS, JV | N4008012C0006 AWD | 60736 | 60203 | 2012-10-09 | 2015-01-02 | 2014-08-16 | 2015-01-02 | 94% | -2502 | N47608561
2014-10-31 | 2012 | Navy Active | Major Military Construction | GEORGIA | UNITED STATES | N42237636 | WATERFRONT RESTRICTED AREA LAND/WATER INTERFACE | 2012-08-22 | 2014-04-17 | CADDELL CONSTRUCTION COMPANY, INC. | N6945009D1279 0002 | 53167 | 36608 | 2014-05-01 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001705 | AIRCRAFT MAINTENANCE HANGAR AND APRON | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 57582 | 64265 | 2012-06-12 | 2015-02-19 | 2014-07-07 | 2015-02-19 | 97%
2014-10-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246705 | FITNESS CENTER, NORTH ISLAND | 2012-01-12 | 2012-08-07 | RQ CONSTRUCTION, LLC | N6247310D5409 0013 | 46630 | 42554 | 2012-08-21 | 2015-03-16 | 2015-03-16 | 2015-07-27 | 66%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001710 | ORDNANCE LOADING AREA ADDITION | 2012-01-25 | 2012-05-29 | M A MORTENSON COMPANY | N4008512C7722 AWD | 7768 | 7376 | 2012-06-12 | 2015-02-19 | 2014-07-07 | 2015-02-19 | 90%
2014-10-31 | 2012 | Navy Active | Major Military Construction | ILLINOIS | UNITED STATES | N00128816 | DECENTRALIZE STEAM SYSTEM | 2011-12-22 | 2012-06-13 | KROESCHELL ESG LLC, JV | N4008312C0016 AWD | 89491 | 62551 | 2012-06-27 | 2015-11-06 | 2015-11-06 | 2015-11-06 | 58%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318822 | MCAS OPERATIONS COMPLEX | 2011-10-18 | 2012-04-18 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 HC01 | 52970 | 51288 | 2012-05-02 | 2014-12-29 | 2014-03-17 | 2014-12-29 | 85%
2014-10-31 | 2012 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246880 | ROTARY AIRCRAFT DEPOT MAINTENANCE FAC, NORTH ISLAND | 2012-04-24 | 2012-07-03 | RQ CONSTRUCTION, LLC | N6247310D5409 0011 | 56977 | 55662 | 2012-07-17 | 2015-03-30 | 2015-03-30 | 2015-07-09 | 69%
2014-10-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436913 | EHW SECURITY FORCE FACILITY | 2011-09-20 | 2012-01-31 | LCC-MZT TEAM IV | N4425512C3007 AWD | 13485 | 13663 | 2012-02-14 | 2014-06-11 | 2013-08-08 | 2014-02-16 | 100% | -7933 | N684691400
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M62204925 | DIP TANK CLEANING FACILITY | 2011-11-10 | 2012-03-21 | HAL HAYS CONSTRUCTION INC | N6247309D1616 0009 | 7970 | 7879 | 2012-04-04 | 2013-09-27 | 2013-09-27 | 2014-04-09 | 100%
2014-10-31 | 2012 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60508927 | APPLIED INSTRUCTION FACILITIES, EOD COURSE | 2012-02-17 | 2012-06-07 |  |  | 18810 | 20581 | 2012-06-21 | 2014-12-30 | 2014-12-30 | 2014-12-30 | 73% |  |  | Awarded by Other Agency
2014-10-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436985 | WRA VEHICLE BARRIERS | 2011-08-01 | 2012-02-10 | WASHINGTON PATRIOT CONSTRUCTION LLC | N4425510D5008 0012 | 9338 | 8948 | 2012-02-24 | 2013-12-11 | 2013-12-10 | 2014-06-30 | 100% | -7587 | N42237636
2014-10-31 | 2012 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990 | EXPLOSIVES HANDLING WHARF #2 INC 1 OF 4 | 2011-12-13 | 2012-05-09 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 AWD | 81714 | 78002 | 2012-05-23 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 92.07%
2014-10-31 | 2012 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146991 | H-1 HELICOPTER GEARBOX REPAIR & TEST FACILITY | 2011-12-22 | 2012-03-15 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0003 | 14067 | 17176 | 2012-03-29 | 2014-04-29 | 2013-08-14 | 2014-10-15 | 100%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001003 | STAFF NCO ACADEMY FACILITIES | 2012-11-30 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0007 | 29260 | 27821 | 2013-09-19 | 2015-11-08 | 2015-09-01 | 2015-11-08 | 33%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557101A | NORTH RAMP PARKING (Andersen AFB) INC 2 OF 2 | 2013-01-25 | 2013-08-07 | GUAM MACC BUILDERS A JV | N6274210D1309 JQ01 | 24305 | 19109 | 2013-08-21 | 2015-12-15 | 2015-07-12 | 2015-12-15 | 33%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67604113 | MV-22 AVIATION SIMULATOR BUILDING | 2012-12-19 | 2013-06-13 | VANDER WERFF, PETER CONSTRUCTION | N6247309D1619 0008 | 4380 | 4081 | 2013-06-27 | 2014-09-18 | 2014-09-21 | 2014-09-21 | 100%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M006811176 | SAN JACINTO ROAD EXTENSION | 2014-08-28 | 2014-09-24 | HAL HAYS CONSTRUCTION INC | N6247312D0258 0022 | 5428 | 4269 | 2014-10-08 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 0%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011384 | BASE ACCESS AND ROAD, PHASE 3 | 2011-12-28 | 2012-04-03 | DRAGADOS USA, INC. | N4008512C7714 AWD | 28666 | 28654 | 2012-04-17 | 2016-09-14 | 2015-04-18 | 2016-09-14 | 49.85%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146163 | MARINE AIR SUPPORT SQUADRON COMPOUND | 2013-03-05 | 2013-09-05 | MITCHELL INDUSTRIAL CONTRACTORS INC/BRASFIELD & GORRIE, LLC JOINT VENT | N4008513C6015 AWD | 29091 | 27562 | 2013-09-19 | 2016-02-24 | 2016-01-18 | 2016-02-24 | 25.92%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M67865181 | HANGAR 5 RENOVATIONS & ADDITION | 2013-02-28 | 2013-09-13 | SOLTEK PACIFIC CONSTRUCTION CO | N6247310D5411 0002 | 13634 | 12823 | 2013-09-27 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 7.347%
2014-10-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N61065229 | STRATEGIC SYSTEMS WEAPONS EVALUATION TEST LAB | 2013-02-28 | 2013-09-30 | HENSEL PHELPS CONSTRUCTION CO | N6247310D5405 0003 | 29447 | 27595 | 2013-10-14 | 2016-04-17 | 2016-04-17 | 2016-06-16 | 16%
2014-10-31 | 2013 | Navy Active | Major Military Construction | NEW JERSEY | UNITED STATES | N69213237 | COMBAT SYSTEM ENGEINEERING BUILDING ADDITION | 2012-10-17 | 2013-09-03 | HENSEL PHELPS CONSTRUCTION CO. | N4008513C3513 AWD | 34005 | 33510 | 2013-09-17 | 2014-11-27 | 2014-11-27 | 2015-01-24 | 78%
2014-10-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620245 | EA-18G FLIGHT SIMULATOR FACILITY | 2012-08-16 | 2013-06-13 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0009 | 5679 | 5915 | 2013-06-27 | 2014-12-25 | 2014-11-25 | 2015-01-27 | 87%
2014-10-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151290 | CRUISE/DESTROYER UPGRADE TRAINING FACILITY | 2013-04-02 | 2013-08-19 | JOHN C. GRIMBERG CO., INC. | N4008010D0492 0007 | 14130 | 13462 | 2013-09-02 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 49%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | CALIFORNIA | UNITED STATES | M00243313 | ENTRY CONTROL POINT (GATE 5) | 2013-03-15 | 2013-12-20 | A&D GC INC | N6247309D1658 0013 | 10974 | 10293 | 2014-01-03 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 10%
2014-10-31 | 2013 | Navy Active | Major Military Construction | MISSISSIPPI | UNITED STATES | N63043317 | DINING FACILITY | 2012-11-20 | 2013-12-17 | JCON GROUP, CORP | N6945014D0754 0001 | 9851 | 9274 | 2013-12-31 | 2015-10-09 | 2015-10-09 | 2015-10-09 | 15.03%
2014-10-31 | 2013 | Navy Active | Major Military Construction |  | JAPAN | N61056353 | BACHELOR QUARTERS | 2013-01-24 | 2013-09-27 |  |  | 5627 | 5521 | 2013-10-11 | 2015-02-02 | 2015-01-05 | 2015-02-02 | 25% |  |  | Awarded by Other Agency
2014-10-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N61151372 | PHYSICAL FITNESS CENTER | 2012-12-12 | 2013-09-27 | C.E.R. INC. | N4008010D0302 0021 | 11409 | 10676 | 2013-10-11 | 2015-05-02 | 2015-05-02 | 2015-05-02 | 25.38%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974378 | SECURITY OPERATIONS COMPLEX | 2012-10-16 | 2013-10-31 | I E PACIFIC INC | N6247309D1657 0007 | 14316 | 13474 | 2013-11-14 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 4.956%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M00263382 | FRONT GATE AT/FP IMPROVMENTS | 2013-04-29 | 2013-10-16 | FUTURENET, GROUP, INC. | N6945014C1757 AWD | 11513 | 10931 | 2013-10-30 | 2015-10-11 | 2015-04-12 | 2015-10-11 | 17%
2014-10-31 | 2013 | Navy Active | Major Military Construction |  | ROMANIA | N62590400 | AEGIS ASHORE MISSILE DEFENSE COMPLEX | 2013-10-25 | 2014-04-30 | NAVY STANDARD DOCUMENT |  | 40018 | 36389 | 2014-05-14 |  |  |  | 7%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169427 | GROUND SUPPORT EQUIPMENT SHOP | 2012-12-03 | 2013-08-08 | BRADY-FLUOR, LLC | N6945013D1761 0001 | 10936 | 10803 | 2013-08-22 | 2014-12-12 | 2014-08-07 | 2014-12-12 | 56.67%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169456 | SIMULATED LHD FLIGHT DECK | 2012-08-27 | 2013-06-26 | HEAD, INC. | N6945013C1773 AWD | 12302 | 11957 | 2013-07-10 | 2014-11-28 | 2014-07-11 | 2014-10-05 | 100%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169465 | AIRCRAFT MAINTENANCE HANGAR | 2014-08-06 | 2014-08-15 | CAROTHERS CONSTRUCTION INC | N6945014D1266 0001 | 39643 | 36371 | 2014-08-29 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 0.9721%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | M60169472 | AIRFIELD SECURITY UPGRADES | 2012-10-31 | 2013-07-01 | HITT CONTRACTING INC. | N6945013C1772 AWD | 11043 | 12550 | 2013-07-15 | 2014-10-28 | 2014-03-28 | 2014-10-28 | 100%
2014-10-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00245500 | LCS TRAINING FACILITY | 2013-06-18 | 2013-09-30 | M A MORTENSON COMPANY | N6247313C4206 AWD | 45553 | 40294 | 2013-10-14 | 2015-10-24 | 2015-10-24 | 2016-01-09 | 22% | -10760 | N42237100
2014-10-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191513 | A SCHOOL BARRACKS | 2012-08-20 | 2013-10-31 | SAUER, INC. | N4008509D5026 0005 | 31430 | 29153 | 2013-11-14 | 2015-12-30 | 2015-12-16 | 2015-12-30 | 16% | -5604 | N42237100
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264562 | THE BASIC SCHOOL STUDENT QUARTERS, PHASE 7 | 2012-07-25 | 2013-09-23 | HARPER CONSTRUCTION COMPANY, INC | N4008013C0001 A00001 | 30462 | 28693 | 2013-10-07 | 2017-09-18 | 2016-11-06 | 2016-11-06 | 4.805%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | ARIZONA | UNITED STATES | M62974566 | COMBAT AIRCRAFT LOADING APRON | 2013-07-16 | 2013-09-27 | BALDI BROS INC201 CALIFORNIA AVENUE | N6247309D1603 0013 | 12671 | 11789 | 2013-10-11 | 2015-03-02 | 2014-09-22 | 2015-03-02 | 31.28%
2014-10-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191582 | UNDERSEA SURVEILLANCE SCIF FACILITY | 2012-08-31 | 2012-11-19 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0003 | 4129 | 4834 | 2012-12-03 | 2014-06-25 | 2013-11-29 | 2014-06-27 | 100%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M00146601 | ARMORY | 2013-04-15 | 2013-09-05 | WHITING-TURNER CONTRACTING CO | N4008510D5330 0006 | 11782 | 11275 | 2013-09-19 | 2015-04-20 | 2015-04-08 | 2015-04-20 | 59.34%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | M00264644 | WEAPONS TRAINING BATALLION MESS HALL | 2013-02-22 | 2013-09-04 | C.E.R. INC. | N4008010D0302 0020 | 13168 | 12604 | 2013-09-18 | 2015-06-30 | 2015-04-22 | 2015-04-22 | 26%
2014-10-31 | 2013 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207655 | BAMS MISSION CONTROL COMPLEX | 2013-01-18 | 2013-08-14 | WHITESELL-GREEN, INC. | N6945013C1257 AWD | 18180 | 17991 | 2013-08-28 | 2014-12-27 | 2014-12-27 | 2015-02-15 | 36%
2014-10-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863709 | GENERAL PURPOSE WAREHOUSE | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 2446 | 1908 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 38%
2014-10-31 | 2013 | Navy Active | Major Military Construction |  | SPAIN | N62863710 | HIGH EXPLOSIVE MAGAZINE | 2013-04-18 | 2013-08-23 | ACCIONA INFRAESTRUCTURAS | N6247013C3014 AWD | 5849 | 5109 | 2013-09-06 | 2015-03-20 | 2015-03-20 | 2015-03-20 | 36%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001711 | PERSONNEL ADMINISTRATION CENTER | 2013-01-14 | 2013-09-06 | DANIEL AND DANIELS CONSTRUCTIONCOMPANY INC | N4008510D0262 0018 | 6449 | 5392 | 2013-09-20 | 2015-07-06 | 2015-07-06 | 2015-07-06 | 48%
2014-10-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232900 | BAMS MAINTENANCE TRAINING FACILITY | 2013-05-28 | 2013-08-27 | A&D GC INC | N6247309D1658 0008 | 10301 | 8718 | 2013-09-10 | 2014-11-21 | 2014-11-21 | 2015-05-01 | 7.862%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318904 | MV-22 HANGAR AND INFRASTRUCTURE | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 63056 | 55902 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 24%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318905 | AIRCRAFT STAGING AREA | 2012-11-28 | 2013-12-17 | WATTS CONTRACK A JV | N6274214C1327 AWD | 11118 | 7005 | 2013-12-31 | 2015-12-31 | 2015-09-10 | 2015-09-10 | 29%
2014-10-31 | 2013 | Navy Active | Major Military Construction |  | GREECE | N66691907 | AIRCRAFT PARKING APRON EXPANSION | 2013-07-12 | 2014-07-11 | SOCIEDAD ESPAQOLA DE MONTAJESINDUSTRIALES S.A.Y EIFFAGE INFRAEST | N6247014C3012 AWD | 14663 | 11219 | 2014-07-25 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 4%
2014-10-31 | 2013 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246909 | H-60S SIMULATOR TRAINING FACILITY | 2012-12-12 | 2014-02-28 | PACIFIC WEST BUILDERS | N6247311D0020 0008 | 3088 | 2843 | 2014-03-14 | 2015-03-15 | 2015-03-15 | 2015-03-15 | 5.342%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212984 | REGIMENTAL HEADQUARTERS | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 11028 | 10654 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-08-14 | 37.18%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212985 | BACHELOR ENLISTED QUARTERS | 2012-12-17 | 2013-08-30 | ARCHER WESTERN CONTRACTORS, LTD | N4008508D9739 0006 | 18418 | 17603 | 2013-09-13 | 2015-06-26 | 2015-06-26 | 2015-08-14 | 29.61%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212986 | MOTOR TRANSPORTATION FACILITY | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 5841 | 5654 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 50.61%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212987 | SUPPLY WAREHOUSE FACILITY | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 6987 | 6634 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 51.55%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction | VIRGINIA | UNITED STATES | N69212989 | ARMORY | 2013-05-21 | 2013-08-30 | HOURIGAN CONSTRUCTION CORPORATION | N4008508D9738 0004 | 3653 | 3452 | 2013-09-13 | 2015-04-19 | 2015-03-23 | 2015-04-19 | 78.16%
2014-10-31 | 2013 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990A | EXPLOSIVE HANDLING WHARF #2, INC 2 OF 4 | 2011-12-13 | 2012-11-01 | EHW CONSTRUCTORS, A JOINT VENTURE | N4425512C3008 P00001 | 280041 | 227251 | 2012-11-15 | 2016-01-09 | 2016-01-09 | 2016-01-09 | 70%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613995 | MAINTENANCE HANGAR IMPROVEMENTS | 2014-03-05 | 2014-05-23 | NAVY STANDARD DOCUMENT |  | 4947 | 4926 | 2014-06-06 | 2015-06-14 | 2015-06-14 | 2015-06-14 | 0%
2014-10-31 | 2013 | Marine Corps Active | Major Military Construction |  | JAPAN | M62613996 | VERTICAL TAKE-OFF AND LANDING PAD NORTH | 2014-04-07 | 2014-07-25 |  |  | 6304 | 6304 | 2014-08-08 | 2015-09-24 | 2015-09-24 | 2015-09-24 | 0% |  |  | Awarded by Other Agency
2014-10-31 | 2013 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N32443998 | DRYDOCK 8 ELECTRICAL DISTRIBUTION UPGRADE | 2013-07-31 | 2013-11-27 | HELIX ELECTRIC, INC. | N4008514C8106 AWD | 28374 | 26274 | 2013-12-11 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 11%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557J200 | NORTH RAMP UTILITIES II | 2014-04-11 | 2014-10-17 | CORE TECH-AMEC, JV | N6274215C1329 AWD | 53014 | 47295 | 2014-10-31 | 2016-11-04 | 2016-09-02 | 2016-09-02 | 0%
2014-10-31 | 2014 | Navy Active | Major Military Construction |  | JAPAN | N61054011 | COMMUNICATIONS SYSTEM UPGRADE | 2014-05-02 | 2014-09-19 |  |  | 9458 | 9458 | 2014-10-03 | 2016-08-16 | 2016-08-16 | 2016-08-16 | 0% |  |  | Awarded by Other Agency
2014-10-31 | 2014 | Navy Active | Major Military Construction | SOUTH CAROLINA | UNITED STATES | N42237100 | NUCLEAR POWER OPERATION TRAINING FACILITY | 2014-01-10 | 2014-08-20 | CADDELL CONSTRUCTION CO. (DE), LLC | N6945014C1756 AWD | 128249 | 119372 | 2014-09-03 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2%
2014-10-31 | 2014 | Navy Active | Major Military Construction | RHODE ISLAND | UNITED STATES | N32411103 | HEWITT HALL RESEARCH CENTER | 2014-05-01 | 2014-07-31 | H.V. COLLINS COMPANY | N4008514C5221 AWD | 13319 | 12622 | 2014-08-14 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 1%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | GUAM | GUAM | N41557109 | AIRCRAFT MAINTENANCE HANGAR (NORTH RAMP) | 2014-02-04 | 2014-05-07 | DCK-ECC PACIFIC GUAM, LLC | N6274210D1308 0002 | 62820 | 57147 | 2014-05-21 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 1.116%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M670011353 | LANDFILL, PHASE 4 | 2014-05-13 | 2014-08-25 | GLOVER CONSTRUCTION COMPANY INC | N4008514C8400 AWD | 17529 | 13776 | 2014-09-08 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 1%
2014-10-31 | 2014 | Navy Active | Major Military Construction | OKLAHOMA | UNITED STATES | N83447136 | TACAMO E-6B HANGAR | 2013-10-03 | 2014-09-30 | HGL CONSTRUCTION INC | N6945014C1770 AWD | 19401 | 18478 | 2014-10-14 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 0%
2014-10-31 | 2014 | Navy Active | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | N684691400 | NAVSEA HQ RESTORATION | 2013-12-12 | 2014-01-31 | CH2M HILL CONSTRUCTORS, INC. | N6247013D6019 AWD | 48905 | 47693 | 2014-02-14 |  |  |  | 61%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction |  | JAPAN | M67400201 | AIRFIELD SECURITY UPGRADES | 2013-11-08 | 2014-04-18 |  |  | 2881 | 2861 | 2014-05-02 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 4% |  |  | Awarded by Other Agency
2014-10-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A227 | ARMORY | 2014-03-17 | 2014-07-25 | JV SKE DJIBOUTI MACC | N3319113D0841 0003 | 4492 | 4178 | 2014-08-08 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 0%
2014-10-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620239 | EA-18G FACILITY IMPROVEMENTS | 2014-02-10 | 2014-08-25 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5004 AWD | 29692 | 25160 | 2014-09-08 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 0.01972%
2014-10-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N00620251 | P-8A HANGAR AND TRAINING FACILITIES | 2014-01-20 | 2014-07-21 | KORTE CONSTRUCTION COMPANY DBAKORTE COMPANY, THE | N4425514C5002 AWD | 84889 | 78860 | 2014-08-04 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 0.03442%
2014-10-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813270 | DRYDOCK WATERFRONT FACILITY | 2013-12-05 | 2014-02-17 | WATTS-HEALY TIBBITTS A JV | N6247809D4019 KB03 | 22355 | 19955 | 2014-03-03 | 2015-12-11 | 2015-12-11 | 2015-12-11 | 3%
2014-10-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N69232281 | AIRCRAFT ENGINE TEST PADS | 2014-03-31 | 2014-06-12 | I E PACIFIC INC | N6247309D1657 0016 | 6106 | 5717 | 2014-06-26 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 1%
2014-10-31 | 2014 | Navy Active | Major Military Construction | HAWAII | UNITED STATES | N62813320 | SUBMARINE PRODUCTION SUPPORT FAC (PHNSY&IMF) | 2014-04-09 | 2014-06-30 | HENSEL PHELPS CONSTRUCTION CO. | N6274214C1304 AWD | 33970 | 29387 | 2014-07-14 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 1%
2014-10-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436420 | INTEGRATED WATER TREATMENT SYS DRY DOCKS 3 | 2013-12-19 | 2014-07-18 | WATTS CONSTRUCTORS, LLC | N4425514C5000 AWD | 12179 | 10307 | 2014-08-01 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 1%
2014-10-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N60201425 | LCS LOGISTICS SUPPORT FACILITY | 2014-02-14 | 2014-05-30 | LEEBCOR SERVICES LLC | N6945013D1765 0002 | 15842 | 14860 | 2014-06-13 | 2015-11-26 | 2015-11-26 | 2015-11-28 | 3%
2014-10-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755425 | MODULAR STORAGE MAGAZINE | 2013-12-30 | 2014-05-12 | GUAM MACC BUILDERS A JV | N6274210D1309 0005 | 54865 | 45197 | 2014-05-26 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 3%
2014-10-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N62688500 | PIER 11 POWER UPGRADES FOR CVN-78 | 2014-03-28 | 2014-06-30 | SYNCON, LLC | N4008514D8152 0001 | 1365 | 1111 | 2014-07-14 | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2%
2014-10-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755518 | X-RAY WHARF IMPROVEMENTS | 2014-01-10 | 2014-06-03 | GUAM MACC BUILDERS A JV | N6274210D1309 0006 | 53085 | 42570 | 2014-06-17 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2.802%
2014-10-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755566 | EMERGENT REPAIR FACILITY EXPANSION | 2013-12-06 | 2014-04-10 | GUAM MACC BUILDERS A JV | N6274210D1309 0004 | 35860 | 27566 | 2014-04-24 | 2016-05-12 | 2016-05-12 | 2016-05-12 | 5%
2014-10-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N41557625 | BAMS FORWARD OPERATIONAL AND MAINTENANCE HANGAR | 2013-11-06 | 2014-03-27 | GUAM MACC BUILDERS A JV | N6274210D1309 0003 | 57710 | 48462 | 2014-04-10 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 6%
2014-10-31 | 2014 | Navy Active | Major Military Construction | GUAM | UNITED STATES | N61755637 | DEHUMIDIFIED SUPPLY STORAGE FACILITY | 2013-12-16 | 2014-03-20 | BULLTRACK-WATTS, A JOINT VENTURE | N4019210D2801 KB01 | 17170 | 14312 | 2014-04-03 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 14%
2014-10-31 | 2014 | Navy Active | Major Military Construction | GUAM | GUAM | N61755638 | SIERRA WHARF IMPROVEMENTS | 2014-03-10 | 2014-05-30 | FARGO PACIFIC INC. | N4019210D2808 0009 | 1462 | 1209 | 2014-06-13 | 2015-03-26 | 2015-03-26 | 2015-03-26 | 0.01034%
2014-10-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00207659 | P-8A TRAINING & PARKING APRON EXPANSION | 2014-03-31 | 2014-09-26 | ARCHER WESTERN CONSTRUCTION, LLC | N6945014C1261 AWD | 10573 | 5992 | 2014-10-10 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 0%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001676 | CH-53K MAINTENANCE TRAINING FACILITY | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 14312 | 13034 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2.663%
2014-10-31 | 2014 | Navy Active | Major Military Construction | FLORIDA | UNITED STATES | N00213678 | AIRCRAFT CRASH/RESCUE & FIRE HEADQUARTERS | 2014-05-08 | 2014-08-15 | DRACE ANDERSON JOINT VENTURE | N6945013D1762 0002 | 14151 |  | 2014-08-29 | 2016-01-07 | 2016-01-07 | 2016-01-07 | 0%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | NORTH CAROLINA | UNITED STATES | M67001726 | REGIONAL COMMUNICATION STATION | 2014-02-20 | 2014-05-30 | WALBRIDGE ALDINGER COMPANY, INC. | N4008510D5331 0005 | 20159 | 10018 | 2014-06-13 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 1.893%
2014-10-31 | 2014 | Navy Active | Major Military Construction | VIRGINIA | UNITED STATES | N60191815 | AERIAL TARGET OPERATION CONSOLIDATION | 2014-04-29 | 2014-09-16 | WALBRIDGE ALDINGER COMPANY, INC. |  | 11446 | 10676 | 2014-09-30 | 2016-10-25 |  | 2016-10-25 | 0%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318852 | 3RD BATTALION COMPLEX | 2014-02-07 | 2014-09-05 | DAWSON-HAWAIIAN BUILDERS I | N6274214C1310 AWD | 21407 | 17348 | 2014-09-19 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 0%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318864 | AIRCRAFT MAINTENANCE EXPANSION | 2014-01-10 | 2014-04-16 | FTSI PHELPS JOINT VENTURE | N6274214C1315 AWD | 16968 | 15194 | 2014-04-30 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 7%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | HAWAII | UNITED STATES | M00318884 | AVIATION SIMULATOR MODERNIZATION/ADDITION | 2014-02-17 | 2014-09-30 | ALLIED PACIFIC BUILDERS INC | N6274214C1300 AWD | 17720 | 14957 | 2014-10-14 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 0%
2014-10-31 | 2014 | Navy Active | Major Military Construction |  | DJIBOUTI | N3379A921 | UNACCOMPANIED HOUSING | 2014-04-22 | 2014-10-01 | B.L. HARBERT INTERNATIONAL, L.L.C. | N6247015C5000 AWD | 20714 | 19527 | 2014-10-15 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 0%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004934 | WEAPONS STORAGE AND INSPECTION FACILITY | 2013-12-06 | 2014-09-10 | BLUEFORGE, LLC | N6945014D1271 0001 | 14685 | 14300 | 2014-09-24 | 2016-01-25 | 2016-01-25 | 2016-01-25 | 0%
2014-10-31 | 2014 | Marine Corps Active | Major Military Construction | GEORGIA | UNITED STATES | M67004954 | CERS DISPATCH FACILITY | 2013-12-11 | 2014-06-02 | ARTESIAN CONTRACTING CO INC | N6945012D1769 0005 | 1248 | 1157 | 2014-06-16 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 16%
2014-10-31 | 2014 | Navy Active | Major Military Construction | CALIFORNIA | UNITED STATES | N00246957 | H-60 TRAINER FACILITY, NAS NORTH ISLAND | 2014-03-31 | 2014-08-04 | I E PACIFIC INC | N6247309D1657 0018 | 8904 | 8407 | 2014-08-18 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 0.4623%
2014-10-31 | 2014 | Navy Active | Major Military Construction | WASHINGTON | UNITED STATES | N68436990B | EXPLOSIVE HANDLING WHARF #2 (BANGOR) INC 3 OF 4 | 2011-12-13 | 2013-12-31 | EHW CONSTRUCTORS, A JOINT VENTURE |  | 24880 | 13751 | 2014-01-14 |  |  |  | 0.04763%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61054012 | CONSTRUCT NACCC ADDITION | 2011-01-26 | 2011-06-10 | SUMIYOKO MITOMO JV | N4008410D0014 0003 | 1380 | 1256 | 2011-06-24 | 2012-04-20 | 2012-04-13 | 2012-04-20 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | HAWAII | UNITED STATES | N62813071 | INSTALL EMERGENCY NOTIFICATION & ALARM SYSTEM (RED HILL) | 2011-07-19 | 2011-09-19 | ENVIRONET, INC. | N6247810D4020 0014 | 1559 | 1446 | 2011-10-03 | 2013-03-01 | 2012-12-24 | 2013-03-01 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N57095101 | ROAD IMPROVEMENTS CAMP ALLEN AREA | 2010-06-24 | 2011-02-14 | TESORO CORPORATION | N4008509D5027 0003-PC000002 | 1381 | 1326 | 2011-02-28 | 2012-01-27 | 2011-09-21 | 2012-01-27 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092201 | RIVERINE SQUADRON TWO BOAT & VEHICLE MAINTENANCE FACILITY | 2011-05-26 | 2011-08-03 | JESSICO, INC | N4008511C3026 AWD | 2085 | 1989 | 2011-08-17 | 2012-11-13 | 2012-09-30 | 2012-11-13 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212202 | RIVERINE SQUADRON THREE BOAT STORAGE BUILDING | 2011-04-19 | 2011-06-20 | THR ENTERPRISES, INC. | N4008506D6009 0008 | 928 | 950 | 2011-07-04 | 2012-04-16 | 2012-01-26 | 2012-04-30 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | N32414203 | EMERGENCY EGRESS FOR NFPC BRIDGE CRANES | 2011-10-12 | 2012-03-02 | FREITAS CONSTRUCTION CORPORATION | N4008512C5002 AWD | 1951 | 1838 | 2012-03-16 | 2012-08-28 | 2012-09-13 | 2012-09-13 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | NEW JERSEY | UNITED STATES | N69213206 | CONSTRUCT DISPATCH CENTER | 2011-09-16 | 2011-11-17 | WU & ASSOCIATES INC | N4008510D9451 0005 | 1630 | 1633 | 2011-12-01 | 2013-03-26 | 2013-01-25 | 2013-03-29 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092242 | ELECTRICAL UPGRADES TO PIERS 16, 17, AND DOGLEG | 2011-08-18 | 2011-11-04 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008512C7000 AWD | 1725 | 1616 | 2011-11-18 | 2013-05-08 | 2012-07-21 | 2013-05-31 | 100%
2014-10-31 | 2011 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042331 | WATER WELL | 2011-01-11 | 2011-09-30 | EPC CORPORATION | N6247310D5415 0012 | 2713 | 2887 | 2011-10-14 | 2013-11-22 | 2012-10-01 | 2013-05-21 | 100%
2014-10-31 | 2012 | Marine Corps Active | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | M670011425 | OVERHEAD RANGE BAFFLE SYSTEM | 2012-12-17 | 2013-02-20 | MILITARY & FEDERAL CONSTRUCTION CO,INC. | N4008511D8026 0008 | 2297 | 2173 | 2013-03-06 | 2014-11-21 | 2014-04-17 | 2014-04-17 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092199 | MSRON FOUR BOAT STORAGE BUILDING | 2012-10-31 | 2012-12-14 | JESSICO, INC | N4008511D3021 0008 | 970 | 938 | 2012-12-28 | 2013-11-15 | 2013-11-08 | 2013-11-15 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241294 | CONNECT TO KINGSVILLE WATER SYSTEM | 2012-07-10 | 2012-09-24 | GLOBAL ENGINEERING & CONSTRUCTION,LLC | N6945010D0776 0002 | 1658 | 1549 | 2012-10-08 | 2014-03-21 | 2014-03-21 | 2014-08-25 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042363 | MAINTENANCE HANGAR SPACE FOR NEW SAR IN FY13 | 2012-06-08 | 2012-08-29 | T SIMONS CO INC | N6247312C3410 AWD | 1980 | 1878 | 2012-09-12 | 2013-08-29 | 2013-08-29 | 2013-08-29 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042364 | HANGAR 1 ALTERATIONS FOR F/A 18 REALIGNMENT | 2012-08-17 | 2012-09-28 | ANDERSON BURTON CONSTRUCTION, INC. | N6247312C3413 AWD | 2000 | 1896 | 2012-10-12 | 2014-03-05 | 2013-09-26 | 2014-03-05 | 100%
2014-10-31 | 2012 | Marine Corps Reserve | Unspecified Minor Military Construction | LOUISIANA | UNITED STATES | N00206501 | MILITARY WORKING DOG FACILITY | 2013-03-27 | 2013-08-15 | DRACE CONSTRUCTION CORP. | N6945013C5571 AWD | 1286 | 1226 | 2013-08-29 | 2014-06-20 | 2014-05-22 | 2014-06-20 | 100%
2014-10-31 | 2012 | Navy Reserve | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N69212543 | NAVELSG RESERVE FORCES MARSHALLING YARDS | 2012-11-05 | 2013-01-16 | OCEAN CONSTRUCTION SERVICES | N4008511D6588 0006 | 738 | 747 | 2013-01-30 | 2013-10-23 | 2014-01-21 | 2014-01-21 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63406563 | PURE WATER DIST SYS PIERS 5000, 5002 & 5003 | 2012-06-20 | 2012-09-28 | NOVA R M F | N6247312D0245 0003 | 1939 | 1875 | 2012-10-12 | 2014-06-23 | 2013-09-27 | 2014-07-01 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863708 | CONSTRUCT LCAC BEACH ACCESS RAMP | 2013-06-19 | 2013-09-29 | SOCIEDAD ESPANOLA DE MONTAJES INDUSTRIALES, S.A. DBA SEMI, S.A. | N3319110D0219 0009 | 1751 | 1411 | 2013-10-13 | 2014-06-20 | 2014-05-28 | 2014-06-20 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | N00204791 | HVAC JOINT AVIATION SURVIVAL TRAINING | 2012-07-25 | 2012-09-29 | R L BURNS INC. | N6945012C6343 AWD | 2038 | 1975 | 2012-10-13 | 2013-12-19 | 2013-08-08 | 2013-08-08 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436839 | RENOVATE LOWER BASE FIRE STATION | 2012-05-31 | 2012-08-31 | PERFORMANCE SYSTEMS INC. | N4425509D4007 0017 | 1389 | 1326 | 2012-09-14 | 2013-11-13 | 2013-08-31 | 2013-11-22 | 100%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N61014851 | JOINST ISR & CYBER WARFARE SCIF EXPANSION | 2013-11-01 | 2013-12-19 | M E AVILA CONSTRUCTION CORPORATION | N6247314C2801 AWD | 1916 | 1871 | 2014-01-02 | 2014-12-31 | 2014-10-17 | 2014-12-31 | 15%
2014-10-31 | 2012 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N00246896 | MESG-1 CONSOLIDATED BOAT MAINTENANCE FACILITY | 2012-12-07 | 2013-02-07 | NEI CONTRACTING AND ENGINEERING INC | N6247311D0067 0004 | 1816 | 1714 | 2013-02-21 | 2014-10-17 | 2014-01-31 | 2014-10-17 | 100%
2014-10-31 | 2013 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N47609003 | EOD/TEU RANGE SUPPORT FACILITY | 2014-03-07 | 2014-06-13 | COPPERTOP LEDCOR JV | N6247313D4608 0007 | 1896 | 1764 | 2014-06-27 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 6.612%
2014-10-31 | 2013 | Navy Active | Unspecified Minor Military Construction | RHODE ISLAND | UNITED STATES | N32411056 | VPT TEST FACILITY | 2012-07-30 | 2013-03-14 | P&S CONSTRUCTION, INC. | N4008510D9450 0006 | 2332 | 2325 | 2013-03-28 | 2013-11-21 | 2013-10-31 | 2013-12-13 | 100%
2014-10-31 | 2013 | Navy Active | Unspecified Minor Military Construction |  | SINGAPORE | N61077123 | TEMPORARY LCS SUSTAINMENT FACILITY | 2012-11-21 | 2012-12-06 | PAE SINGAPORE PTE LTD. | N4008413C9001 AWD | 755 | 768 | 2012-12-20 | 2014-01-15 | 2013-03-10 | 2013-03-10 | 100%
2014-10-31 | 2013 | Navy Active | Unspecified Minor Military Construction | OREGON | UNITED STATES | N00620246 | RANGE OPERATIONS/EMERGENCY MEDICAL FACILITY | 2013-07-26 | 2013-09-30 | EAGLE RIVER DEVELOPMENT LLC | N4425513C7005 AWD | 1120 | 1075 | 2013-10-14 | 2014-09-30 | 2014-09-30 | 2014-12-19 | 65%
2014-10-31 | 2013 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092255 | FIELD CARRIER LANDING PRACTICE DECK FOR E2/C2 | 2012-12-10 | 2013-02-28 | CONSTRUCTION DEVELOPMENT SERVICES5900 E VIRGINIA BEACH BLVD | N4008513C7711 AWD | 1925 | 1900 | 2013-03-14 | 2013-09-12 | 2013-08-30 | 2013-09-29 | 100%
2014-10-31 | 2013 | Navy Active | Unspecified Minor Military Construction | TEXAS | UNITED STATES | N60241288 | WASTEWATER SYSTEM | 2013-10-02 | 2014-03-28 | DAKOTA MEYER ENTERPRISES, INC. | N6945014C0763 AWD | 1790 | 1644 | 2014-04-11 | 2015-03-27 | 2015-03-27 | 2015-03-27 | 34%
2014-10-31 | 2013 | Marine Corps Active | Unspecified Minor Military Construction |  | JAPAN | M67400305 | DEMOLISH 45 HOUSING UNITS, KISHABA HOUSING | 2013-07-10 | 2014-09-25 |  |  | 1729 | 1719 | 2014-10-09 | 2015-06-29 | 2015-06-29 | 2015-06-29 | 0% |  |  | Awarded by Other Agency
2014-10-31 | 2013 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N68436857 | FLOATING LABORATORY, MOORING DOLPHINS | 2013-01-16 | 2013-05-17 | NOVA GROUP INC |  | 3406 | 3114 | 2013-05-31 |  |  |  | 98.91%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | JAPAN | N61057221 | HELO ALFS TEST ROOM, BUILDING 194 | 2014-06-12 | 2014-08-06 | NIHON MECCS CO., LTD. | N4008414C8302 AWD | 890 | 812 | 2014-08-20 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 0%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | N00620257 | HANGAR 11 MODIFICATIONS FOR SEARCH AND RESCUE | 2014-06-20 | 2014-09-02 | RORE, INC. |  | 1424 | 1375 | 2014-09-16 |  |  |  | 0%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | N63042376 | VFA-94 HANGAR ALTERATIONS | 2014-08-27 | 2014-09-27 | COPPERTOP LEDCOR JV | N6247313D4608 0014 | 1839 | 1650 | 2014-10-11 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 0%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction | GUAM | GUAM | N61755630 | HARDEN ELECTRICAL DISTRIBUTION LINE (POLARIS PT ROAD) | 2014-07-01 | 2014-09-30 | P&S CONSTRUCTION, INC. |  | 2000 | 1912 | 2014-10-14 | 2015-05-19 |  |  | 0%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | N50092662 | EOD ESU TWO EXPEDITIONARY LOGISTICS OVERHAUL WAREHOUSE | 2014-05-09 | 2014-08-06 | DOYON MANAGEMENT SERVICES, LLC | N4008514D2102 0001 | 1020 | 231 | 2014-08-20 | 2014-11-21 | 2014-11-21 | 2014-11-21 | 0.02945%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | SPAIN | N62863733 | PROVIDE ELECTROMAGNETIC CALIBRATION COMPLEX | 2014-08-29 | 2014-09-19 | NAVY STANDARD DOCUMENT | N3319110D1801 *X478 | 1144 | 707 | 2014-10-03 | 2015-08-21 |  | 2014-11-22 | 1%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | N47608262 | SITE AND UTILITIES FOR BAMS-D TFS | 2014-08-11 | 2014-09-30 | REILLY CONSTRUCTION, INC | N4008014D3014 AWD | 1453 | 1358 | 2014-10-14 | 2015-04-14 | 2015-05-26 | 2015-05-26 | 0%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A917 | CRITICAL POWER FOR BULDING 200 |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC |  | 1120 | 1120 | 2014-06-05 |  |  |  | 100%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A918 | CRITICAL POWER FOR BUILDING T-130 |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC |  | 1175 | 1175 | 2014-06-05 |  |  |  | 100%
2014-10-31 | 2014 | Navy Active | Unspecified Minor Military Construction |  | DJIBOUTI | N3379A919 | CRITICAL POWER FOR BLDGS 111, 113 AND 115 |  | 2014-05-22 | ATLANTIC CONTINGENCY CONSTRUCTION, LLC |  | 1064 | 1065 | 2014-06-05 |  |  |  | 100%
2014-10-31 | 2011 | Marine Corps Reserve | Major Military Construction | CALIFORNIA | UNITED STATES | M67399092 | TANK VEHICLE MAINTENANCE FACILITY | 2011-06-22 | 2011-09-22 | HALBERT CONSTRUCTION | N6247309D1615 0041 | 6458 | 6168 | 2011-10-06 | 2013-03-11 | 2012-09-21 | 2013-03-28 | 100%
2014-10-31 | 2011 | Marine Corps Reserve | Major Military Construction | WASHINGTON | UNITED STATES | M68479060 | MARINE CORPS RESERVE CENTER | 2011-07-21 | 2011-09-27 | ADVANCED TECHNOLOGY CONSTRUCTION | N4425510D5004 0005 | 14630 | 14191 | 2011-10-11 | 2014-04-15 | 2013-02-08 | 2014-03-01 | 100%
2014-10-31 | 2012 | Marine Corps Reserve | Major Military Construction | TENNESSEE | UNITED STATES | M68479030 | RESERVE CENTER TRAINING CENTER - MEMPHIS | 2012-10-26 | 2013-04-05 | LEEBCOR SERVICES LLC | N4008313C0019 AWD | 9006 | 8460 | 2013-04-19 | 2015-01-08 | 2014-10-11 | 2014-10-11 | 100%
2014-10-31 | 2013 | Marine Corps Reserve | Major Military Construction | NEW YORK | UNITED STATES | M68479130 | VEHICLE MAINTENANCE FAC - BROOKLYN NY | 2012-12-07 | 2013-09-05 | CCI SOLUTIONS, LLC | N4008513D8006 F270 | 4911 | 4762 | 2013-09-19 | 2015-11-04 | 2014-12-04 | 2014-12-04 | 14.36%
2014-10-31 | 2014 | Marine Corps Reserve | Major Military Construction | MISSOURI | UNITED STATES | M67386139 | RESERVE CENTER & ADMINISTRATIVE FACILITY | 2014-04-18 | 2014-08-22 | OLD VETERAN CONSTRUCTION, INC. | N6945013D1766 0002 | 17019 | 15843 | 2014-09-05 | 2016-02-23 | 2016-02-23 | 2016-02-23 | 0.001512%
2014-10-31 | 2011 | Navy Reserve | Major Military Construction | LOUISIANA | UNITED STATES | N00206477 | CONSTRUCT JOINT AIR TRAFFIC CONTROL FACILITY | 2011-02-14 | 2011-06-03 | J. KOKOLAKIS CONTRACTING, INC. | N6945011C0756 AWD | 13604 | 14490 | 2011-06-17 | 2014-05-07 | 2013-06-07 | 2014-02-12 | 100%
2014-10-31 | 2011 | Navy Reserve | Major Military Construction | VIRGINIA | UNITED STATES | N69212743 | NAVY ORD CARGO LOGISTICS TRAINING COMPLEX | 2010-09-22 | 2011-06-03 | BALLARD, S.B., INC.DBA S.B. BALLARD CONSTRUCTION CO. | N4008509D5019 0003 | 15431 | 17554 | 2011-06-17 | 2013-10-18 | 2013-04-27 | 2014-10-18 | 100%
2014-10-31 | 2012 | Navy Reserve | Major Military Construction | PENNSYLVANIA | UNITED STATES | N32414860 | ARMED FORCES RESERVE CENTER, PITTSBURGH | 2011-12-08 | 2012-07-31 | CPM-PJD MPA JV | N4008312C0005 AWD | 12033 | 12328 | 2012-08-14 | 2014-05-31 | 2014-02-06 | 2014-05-31 | 100%
2014-10-31 | 2013 | Navy Reserve | Major Military Construction | TEXAS | UNITED STATES | N83447047 | COMMERCIAL VEHICLE INSPECTION SITE | 2013-01-22 | 2013-09-12 | KOMADA, LLC | N6945013D1767 0001 | 6894 | 6576 | 2013-09-26 | 2014-12-17 | 2014-11-06 | 2014-12-17 | 18.5%
2014-10-31 | 2011 | Marine Corps Active | Military Family Housing Improvement | DISTRICT OF COLUMBIA | UNITED STATES | M670291101 | REPLACE INTERIOR PASSENGER LIFT QUARTERS #6 | 2010-03-18 | 2011-01-14 | G-W MANAGEMENT SERVICES, LLC | N4008010D0498 0001-07 | 41 | 39 | 2011-01-28 | 2011-05-12 | 2011-05-13 | 2011-08-31 | 100%
2014-10-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130601 | WHOLEHOUSE REVITALIZATION MIDRISE 955 | 2012-05-10 | 2012-07-30 | NIPPO CORPORATION | N4008412D6501 0002 | 13357 | 12685 | 2012-08-13 | 2013-12-13 | 2013-11-23 | 2013-12-14 | 100%
2014-10-31 | 2012 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626131001 | REVITALIZE NORTH SIDE TOWNHOUSES, PHASE 1 | 2012-05-10 | 2012-07-31 | NIPPO CORPORATION | N4008412D6501 0004 | 11335 | 10876 | 2012-08-14 | 2015-02-02 | 2014-12-20 | 2015-02-02 | 74.79%
2014-10-31 | 2012 | Marine Corps Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611201 | INSTALL SECURITY ALARM SYSTEMS QUARTERS A (GFOQ) |  | 2012-01-04 |  |  | 0 | 45 | 2012-01-18 |  |  |  | 100% |  |  | Awarded by Other Agency
2014-10-31 | 2013 | Marine Corps Active | Military Family Housing Improvement |  | JAPAN | M626130901 | WHOLE HOUSE REVITALIZATION MIDRISE 589 | 2013-11-04 | 2014-06-08 | NISHIMATSU CONSTRUCTION CO.,LTD | N4008414C5500 AWD | 17551 | 16715 | 2014-06-22 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 0%
2014-10-31 | 2011 | Marine Corps Reserve | Military Family Housing Improvement |  | JAPAN | M626130501 | WHOLEHOUSE REVITALIZATION MIDRISE 906 | 2011-05-26 | 2011-09-22 | PENTA-OCEAN CONSTRUCTION CO.,LTD. | N4008411C5504 AWD | 11626 | 11102 | 2011-10-06 | 2013-02-28 | 2013-01-14 | 2013-02-28 | 100%
2014-10-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541101 | WHOLEHOUSE REVITALIZATION - SAKURA TOWER | 2011-04-08 | 2011-07-01 | NIPPO CORPORATION | N4008411C0129 AWD | 17378 | 16915 | 2011-07-15 | 2013-01-17 | 2012-12-03 | 2013-01-20 | 100%
2014-10-31 | 2011 | Navy Active | Military Family Housing Improvement |  | JAPAN | N627351102 | WHOLEHOUSE IMPROVEMENT | 2010-10-08 | 2011-06-26 | NIPPO CORPORATION | N4008411C0006 AWD | 8127 | 6990 | 2011-07-10 | 2013-01-18 | 2012-10-17 | 2013-02-14 | 100%
2014-10-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541201 | WHOLEHOUSE REVITALIZATION, HIMAWARI HEIGHTS HI RISE (4309) | 2012-04-23 | 2012-07-18 | NIPPO CORPORATION | N4008412C0108 AWD | 19730 | 18773 | 2012-08-01 | 2014-01-13 | 2014-01-13 | 2014-01-13 | 100%
2014-10-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541202 | WHOLEHOUSE REVITALIZATION, TOWNHOUSES, PHASE 1 | 2012-04-24 | 2012-08-08 | NIPPO CORPORATION | N4008412C0109 AWD | 9033 | 9094 | 2012-08-22 | 2015-01-11 | 2014-10-07 | 2015-01-11 | 77.1%
2014-10-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571201 | CONVERSION, ON-BASE HIGH RISE (3042) FROM 2 BR TO 4 BR | 2012-05-03 | 2012-09-26 | ICHIBO CO., LTD. | N4008412C8325 AWD | 5990 | 5654 | 2012-10-10 | 2013-11-22 | 2013-08-26 | 2013-11-22 | 100%
2014-10-31 | 2012 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571202 | WHOLEHOUSE REVITALIZATION, HIGH RISE (BLDG 3050) | 2012-03-23 | 2012-08-15 | NIPPO CORPORATION | N4008412C0004 AWD | 17540 | 14942 | 2012-08-29 | 2014-07-01 | 2013-12-09 | 2014-07-01 | 100%
2014-10-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610541305 | WHOLE HOUSE REVITALIZATION PHASE 2 OF 2 | 2013-05-02 | 2014-07-15 | MECCS-URAYASU JV | N4008414C0107 AWD | 7791 | 7305 | 2014-07-29 | 2016-02-21 | 2016-02-21 | 2016-02-21 | 0%
2014-10-31 | 2013 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610571302 | REVITALIZATION OF FAMILY HOUSING TOWNHOMES | 2013-05-10 | 2013-12-01 | NIHON MECCS CO., LTD. | N4008414C8401 AWD | 12958 | 12065 | 2013-12-15 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 14.9%
2014-10-31 | 2013 | Navy Active | Military Family Housing Improvement | GUAM | GUAM | N617551301 | WHOLE HOUSE REVITALIZATION PHASE 1 AT LOCKWOOD TERRACE | 2013-03-08 | 2013-09-12 | PERINI/NORTON A JOINT VENTURE | N6274210D1312 JQ02 | 26805 | 25136 | 2013-09-26 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 29.36%
2014-10-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | M626131403 | WHOLEHOUSE REVITALIZATION, MIDRISE 655 | 2014-08-08 | 2014-09-29 | NIPPO CORPORATION | N4008414C0012 AWD | 16545 | 15632 | 2014-10-13 | 2016-02-02 | 2016-02-02 | 2016-02-02 | 0%
2014-10-31 | 2014 | Navy Active | Military Family Housing Improvement | LOUISIANA | UNITED STATES | M678611407 | SITE IMPROVEMENTS - GENERAL OFFICERS QUARTERS A |  | 2014-09-30 | QUALITY SUPPORT SERVICES, INC. | N4008314D1014 0003 | 75 | 64 | 2014-10-14 |  | 2014-11-30 | 2014-11-30 | 0%
2014-10-31 | 2014 | Navy Active | Military Family Housing Improvement |  | JAPAN | N610581401 | W/H REVITALIZATION - BARA TOWER (#5035) | 2014-07-02 | 2014-09-30 | NIPPO CORPORATION | N4008414R0002 AWD | 22799 | 21589 | 2014-10-14 |  |  |  | 0%
2014-10-31 | 2009 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010154 | Multipurpose Machine Gun Range | 2009-04-28 | 2009-05-05 | HDH General Contractors, Inc. |  | 2671 | 1636 | 2009-05-11 | 2011-11-21 | 2011-11-16 | 2011-11-16 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | GEORGIA | UNITED STATES | 130109 | Armed Forces Reserve Center | 2009-09-09 | 2009-09-09 | New South Construction Company, Inc. | 41100-044-0000070579 | 36015 | 27900 | 2009-09-21 | 2011-11-01 | 2011-04-11 | 2013-09-24 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230070 | Regional Training Institute, PH 1 | 2009-04-08 | 2009-04-16 | Nickerson & O'Day, Inc. | 230070-D | 18713 | 14314 | 2009-05-18 | 2011-06-13 | 2011-06-13 | 2011-06-13 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | MARYLAND | UNITED STATES | 240189 | Army Aviation Support Facility, Add/Alt | 2009-05-05 | 2009-09-28 | Tetra-Tech Facilities Construction, LLC | W912K6-09-C-0002 | 27603 | 27193 | 2010-03-01 | 2012-06-01 | 2010-09-27 | 2012-06-30 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Project has claim with ASBC and claim has not been finalized, schedule to go to trial in Oct 15
2014-10-31 | 2009 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260212 | Infrantry Squad Battle Course | 2009-08-19 | 2009-09-02 | The Garrison Company |  | 2000 | 2167 | 2009-09-07 | 2010-06-30 | 2010-05-18 | 2010-05-18 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270260 | Readiness Center | 2009-08-04 | 2009-08-07 | Holte/Graham, JV | W912LM-09-C-0005 | 13390 | 12529 | 2009-08-10 | 2011-12-01 | 2010-12-14 | 2013-05-31 | 99% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320069 | Readiness Center | 2011-10-27 | 2012-06-01 | Nevada State Public Works | W9124X-11-2-2001 | 11246 | 7762 | 2012-06-11 | 2013-04-30 | 2013-07-12 | 2013-03-27 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011) (Closeout procedures are in progress)
2014-10-31 | 2009 | Army National Guard | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 320152 | Paint Booth | 2009-06-04 | 2009-09-01 | Nevada State Public Works | Nevada State Public Works | 1500 | 1075 | 2009-09-16 | 2012-05-24 | 2012-05-21 | 2012-05-21 | 100% | 0 |  | Congressionally Directed
2014-10-31 | 2009 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360191 | Maneauver Area Training and Equipment Site, PH 3 | 2009-09-04 | 2009-09-30 | Beardsley Design Associates | DAHA30-00-0009 | 10879 | 9544 | 2010-03-10 | 2012-09-30 | 2011-03-09 | 2013-04-11 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Unspecified Minor Military Construction | OHIO | UNITED STATES | 390270 | Ravenna TTB Utilities | 2009-12-15 | 2010-01-28 | Portage County Water Resources Department |  | 1600 | 1600 | 2011-11-01 | 2012-02-22 | 2012-01-30 | 2012-12-06 | 100% | 0
2014-10-31 | 2009 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420511 | Readiness Center, Add/Alt | 2011-08-31 | 2011-09-15 | Lobar Incorporated | DGS 961-20.1 | 6117 | 5738 | 2011-09-26 | 2013-08-15 | 2012-10-30 | 2014-12-31 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | RHODE ISLAND | UNITED STATES | 440039 | Army Aviation Support Facility, Add/Alt (additional funds for FY08 project) | 2008-07-09 | 2008-09-25 | Bacon Construction Co., Inc. | W912LD-08-C-0036 | 4848 | 4150 | 2009-01-09 | 2012-01-06 | 2011-01-09 | 2014-07-31 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460077 | Armed Forces Reserve Center | 2009-03-31 | 2009-04-17 | J Scull Construction | W912MM-04-2-2001 | 28762 | 27822 | 2010-04-05 | 2011-06-24 | 2011-11-14 | 2011-11-14 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460132 | Barracks/Dining/Admin & Parking Complex, PH1 | 2009-06-11 | 2009-06-24 | J Scull Construction | W912-MM-09-2-2001 | 12765 | 11645 | 2009-08-10 | 2011-03-02 | 2010-12-15 | 2010-12-15 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | TENNESSEE | UNITED STATES | 470043 | Readiness Center | 2009-09-16 | 2009-09-25 | Sain Construction Co. | W912L7-09-C-0008 | 8787 | 7706 | 2009-10-01 | 2011-09-15 | 2011-01-21 | 2011-07-05 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490101 | Ammunition Supply Point | 2009-09-17 | 2009-09-18 | Creative Times Inc. |  | 13843 | 12045 | 2009-09-21 | 2011-07-30 | 2010-10-01 | 2010-10-01 | 100% | 2358 | 540205 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530012 | Readiness Center | 2009-09-11 | 2009-09-11 | Wade Perrow Construction, LLC | W912K3-09-C-0001 | 30265 | 24954 | 2009-09-12 | 2011-07-28 | 2011-01-31 | 2011-01-31 | 100% | 0 |  | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540105 | Joint Interagency Training Education Center, PH 1 | 2009-09-25 | 2009-09-25 | The Whiting-Turner Contracting Company | DEFK10003 | 69711 | 72200 | 2009-10-01 | 2011-09-30 | 2011-09-28 | 2014-09-30 | 99% | 0 |  | Emerging Requirement, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Generator work being completed
2014-10-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540205 | Access Control Point | 2009-09-25 | 2009-09-25 | DanHill Construction | DEFK13007 | 3823 | 3694 | 2013-05-01 | 2013-12-16 | 2013-12-11 | 2014-02-28 | 100% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Formal Reprogramming $2,358 funds from FY09 project savings {PN: 490101}, PM Assigned
2014-10-31 | 2009 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540206 | Multi-Purpose Building, PH II | 2009-09-24 | 2009-09-28 | Rycon Construction Inc. | DEFK10004 | 4755 | 4624 | 2010-02-01 | 2010-08-30 | 2010-08-26 | 2013-03-31 | 99% | 0 |  | Congressional Add, PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011), Final Settlement Actions - PM to complete upon execution
2014-10-31 | 2009 | Army National Guard | Unspecified Minor Military Construction | WEST VIRGINIA | UNITED STATES | 540208 | Tri-State Armory Addition | 2009-04-24 | 2009-09-23 | Neighborgall Construction Company |  | 2000 | 2000 | 2009-10-01 | 2010-08-11 | 2010-07-16 | 2010-08-31 | 100% | 0 |  | Congressionally Directed, PM Assigned
2014-10-31 | 2010 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010279 | Urban Assault Course | 2010-09-06 | 2010-09-10 | Baggette Construction, Inc. | AC-10-C-0045-S | 2980 | 2396 | 2010-12-01 | 2011-10-11 | 2011-08-08 | 2011-08-08 | 95% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040227 | Combat Pistol Qualification Course | 2010-06-14 | 2010-06-15 | Norquay Construction | M10-0015 | 2964 | 1867 | 2010-06-28 | 2011-07-15 | 2010-12-31 | 2010-12-31 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060115 | Readiness Center, PH 1 | 2010-09-21 | 2010-09-24 | Bethel Services, Inc. | W912LA-10-C-0009 | 30711 | 23127 | 2010-11-15 | 2013-10-07 | 2012-02-06 | 2014-10-31 | 97% | 2900 | 390263 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,505)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | GUAM | GUAM | 140300 | Readiness Center | 2010-03-05 | 2010-03-08 | Commander, NAVFAC Pacific | N40192-10-C-1335 | 20766 | 20797 | 2010-05-03 | 2012-04-12 | 2012-03-05 | 2012-03-05 | 95% | 3000 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($20,537)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170611 | Readiness Center, Add/Alt | 2010-09-17 | 2010-09-22 | Capital Development Board | W91SMC-10-2-2001-100 | 5560 | 4319 | 2010-10-18 | 2012-03-31 | 2011-09-14 | 2011-09-14 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011) Completed (Pending dispute resolution w/State for paperwork)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210291 | Readiness Center | 2010-06-07 | 2010-08-16 | A & K Construction Company, Inc. | CT2 785 1000000319 1 | 10483 | 10024 | 2010-08-23 | 2012-04-14 | 2011-08-28 | 2011-08-28 | 100% | 0 |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | MAINE | UNITED STATES | 230114 | Regional Training Institute, PH II | 2010-08-11 | 2010-09-21 | Nickerson & O'Day, Inc. | 230070-D | 15464 | 14399 | 2010-09-21 | 2012-08-17 | 2012-07-21 | 2014-01-31 | 100% | 0 |  | Programmatic Plus Up, PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250087 | Armed Forces Reserve Center (JFHQ) | 2010-06-07 | 2010-06-25 | CTA Construction | CTA Base Bid | 27595 | 26247 | 2010-07-12 | 2012-01-15 | 2011-10-19 | 2014-04-30 | 100% | 2000 | 060413 | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260213 | Organizational Maintenance Shop (ADRS) | 2010-08-04 | 2010-09-22 | LD Dosca Associates, Inc. | W912JB-09-D-2014 | 7722 | 7419 | 2010-10-01 | 2012-03-01 | 2011-10-18 | 2011-10-18 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270261 | Readiness Center, PH 2 | 2010-08-30 | 2010-09-07 | MAVCON | W912LM-10-C-0003 | 3079 | 2855 | 2010-09-27 | 2012-05-01 | 2011-07-18 | 2013-05-31 | 100% | 3500 | 530035 | PL 112-25 (Budget Control Act, 2011)/2853 Notification ($3,184)
2014-10-31 | 2010 | Army National Guard | Unspecified Minor Military Construction | MINNESOTA | UNITED STATES | 270263 | CST, Add/Alt | 2011-08-09 | 2011-08-19 | LS Black Constructors | W912LM-10-D-0004 | 1954 | 1897 | 2011-09-12 | 2012-11-20 | 2012-08-24 | 2013-12-20 | 100% | 0
2014-10-31 | 2010 | Army National Guard | Major Military Construction | NEVADA | UNITED STATES | 320197 | Renewable Energy Sustainable Projects | 2010-09-21 | 2010-09-24 | Ray Heating Products Inc. | W9124X-10-2-2001 | 1997 | 1899 | 2010-10-04 | 2011-10-26 | 2011-04-04 | 2011-04-04 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | NEW MEXICO | UNITED STATES | 350043 | Army Aviation Support Facility | 2010-06-29 | 2010-07-02 | PCL Construction Services Inc. | W912PP-10-C-0022 | 35577 | 31835 | 2010-09-13 | 2012-03-20 | 2011-09-14 | 2011-09-14 | 100% | 3300 | 080067 | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410120 | Readiness Center | 2010-09-14 | 2010-09-21 | Lease Crutcher Lewis | 410120D002 | 12093 | 11893 | 2010-10-08 | 2012-09-01 | 2012-12-01 | 2012-12-01 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | OREGON | UNITED STATES | 410820 | Water Supply Company | 2010-09-10 | 2010-09-21 | Hoffman Construction Company | 410820D002 | 3369 | 3368 | 2010-10-01 | 2011-08-01 | 2011-10-02 | 2011-10-02 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | UNITED STATES | 436019 | Urban Assault Course | 2009-12-01 | 2010-09-29 | Remex Co. | W912LR-10-B-0001 | 1669 | 1846 | 2010-10-01 | 2011-10-03 | 2011-09-23 | 2011-09-23 | 100% | 0 |  | Congressionally Directed
2014-10-31 | 2010 | Air National Guard | Major Military Construction | SOUTH DAKOTA | UNITED STATES | 460141 | Joint Force HQ Readiness Center, Supplemental | 2010-08-26 | 2010-09-03 | J. Scull Construction Services, Inc. | W912MM-09-2-2003 | 5308 | 5257 | 2010-09-27 | 2012-04-14 | 2012-04-14 | 2012-04-14 | 100% | 2500 | 530035 | Congressional Add, PL 112-25 (Budget Control Act, 2011)/2853 Notification ($5,705), Delays in getting LEED Certification, State holding funds from A-E for this. Tentative submission date is May 2015
2014-10-31 | 2010 | Army National Guard | Major Military Construction | VIRGINIA | UNITED STATES | 510302 | Regional Training Institute, PH 2 | 2010-01-27 | 2010-02-26 | Barton Marlow Company | W91236-08-C-0079-P00001 | 31946 | 30249 | 2010-07-01 | 2011-07-06 | 2012-09-10 | 2012-08-01 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2010 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED KINGDOM | 540217 | Readiness Center Addition/Life Safety Upgrades | 2010-09-24 | 2010-09-26 | Hayslett Construction Company | DEFK11013 | 1073 | 1135 | 2010-10-01 | 2011-10-21 | 2011-09-18 | 2011-09-18 | 100% | 0 |  | Congressional Add, PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | ARIZONA | UNITED STATES | 040023 | Readiness Center | 2011-08-01 | 2011-09-01 | Haydon Building Corporation-Tem | M11-31 | 16446 | 16320 | 2011-09-19 | 2013-03-19 | 2012-12-14 | 2013-03-19 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | COLORADO | UNITED STATES | 080202 | Readiness Center | 2011-08-05 | 2011-08-16 | AP Mountain States | 080202 - Adolfson & Peterson Construction | 7485 | 7469 | 2011-12-01 | 2012-11-01 | 2012-10-19 | 2012-10-19 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-10-31 | 2011 | Army National Guard | Major Military Construction | GUAM | UNITED STATES | 140001 | Combined Support Maintenance Shop, Ph 1 | 2011-05-31 | 2011-09-01 | NAVFAC Pacific | N40192-10-D-2801-0004 | 18961 | 19300 | 2011-09-12 | 2013-04-19 | 2012-04-20 | 2012-04-20 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011), Final closeout in progress
2014-10-31 | 2010 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160122 | Tactical Unmanned Aircraft System Facility | 2011-05-23 | 2011-08-02 | Construction Inc, Moutain Home | W912J7-11-C-0001 | 6258 | 5477 | 2011-09-13 | 2013-11-14 | 2013-10-22 | 2013-11-14 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210034 | Readiness Center | 2011-08-31 | 2011-09-16 | D.W. Wilburn | CT2 785 1200000063 1 | 19426 | 18776 | 2011-11-09 | 2013-05-29 | 2013-03-01 | 2013-05-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220114 | Readiness Center | 2011-06-23 | 2011-08-08 | Walton Construction Co., LLC. | LA11-C-125 | 27676 | 22524 | 2011-08-29 | 2013-09-03 | 2013-01-14 | 2013-08-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)/2853 Notification ($19,308)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260207 | Combined Arms Collective Training Facility | 2011-06-22 | 2011-08-18 | Saylor Construction LLC | Y11261 | 18799 | 13823 | 2011-09-20 | 2013-04-05 | 2012-03-09 | 2013-11-18 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270096 | Infantry Squad Battle Course | 2011-06-28 | 2011-07-01 | Eagle Construction Company, Inc. | EAG010025 | 4226 | 2232 | 2011-11-01 | 2013-02-15 | 2012-07-06 | 2013-02-15 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593 being reviewed)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270267 | Tactical Unmanned Aircraft System Facility | 2011-07-21 | 2011-08-08 | Donlar Construction Company | DON050003 | 4413 | 3544 | 2012-04-03 | 2012-12-13 | 2012-10-27 | 2012-12-13 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | NEBRASKA | UNITED STATES | 310110 | Readiness Center, Add/Alt | 2011-08-16 | 2011-08-19 | Kingery Construction Company | EastCampus-CONSTR-KINGERY-01 | 3293 | 3339 | 2011-10-01 | 2013-05-06 | 2012-11-06 | 2013-04-29 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | NORTH DAKOTA | UNITED STATES | 380014 | Readiness Center, Add/Alt | 2011-06-15 | 2011-06-22 | Comstock Construction, Inc. | AGND11-30 | 11174 | 11743 | 2011-08-08 | 2012-09-11 | 2012-07-15 | 2013-02-26 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480267 | Combat Pistol/Military Pistol Qualification Course | 2011-04-06 | 2011-09-12 | Unified Services of Texas, Inc. | TX11-ENG-10 | 2477 | 1962 | 2011-09-26 | 2012-10-31 | 2012-03-31 | 2012-10-31 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2011 | Army National Guard | Major Military Construction | TEXAS | UNITED STATES | 480290 | Urban Assault Course | 2011-08-25 | 2011-09-12 | Gaeke Construction Co., Inc. | TX11-ENG-06 | 2581 | 2172 | 2011-11-01 | 2013-01-21 | 2012-08-20 | 2013-08-01 | 100% | 0 |  | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2012 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120193 | Live Fire Shoot House | 2012-04-10 | 2012-04-27 | STG Contracting Group | 120193 LFSH Construction | 3099 | 2556 | 2012-05-21 | 2013-03-04 | 2013-10-28 | 2013-04-19 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2012 | Army National Guard | Unspecified Minor Military Construction | NEW HAMPSHIRE | UNITED STATES | 330052 | Readiness Center, add/Alt | 2012-08-27 | 2012-09-04 | Turnstone Corporation | 330052-GC | 1947 | 1943 | 2012-10-07 | 2013-07-29 | 2013-08-13 | 2013-08-13 | 100% | 0 |  | (Closeout procedures are in progress)
2014-10-31 | 2012 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490618 | Multi-Purpose Machine Gun Range | 2012-09-06 | 2012-09-27 | Cracar Construction | W911YP-12-C-0007 | 6498 | 6577 | 2012-12-01 | 2014-01-06 | 2013-10-28 | 2013-10-28 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2012 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560702 | Readiness Center | 2012-04-27 | 2012-04-18 | Hensel Phelps | 12014512201 | 8898 | 10342 | 2012-12-01 | 2013-06-17 | 2013-10-28 | 2013-06-17 | 100% | 0 |  | PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | 0110007 | National Guard Readiness Center | 2013-09-24 | 2013-09-26 | Butler Construction Company, LLC. | AC-13-B-0051-S | 1920 | 1891 | 2014-02-03 | 2015-04-24 | 2015-04-24 | 2014-10-01 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 010278 | Live Fire Shoot House | 2013-08-01 | 2013-08-23 | Hurst Construction, LLC | AC-13-C-0052-S | 5223 | 5382 | 2013-09-23 | 2014-08-15 | 2014-08-15 | 2014-08-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | ARIZONA | UNITED STATES | 040669 | Underground Electrical Lines | 2013-09-23 | 2014-04-04 | Ludvik Electric | M13-0037 | 2000 | 1833 | 2014-05-05 | 2014-10-31 | 2014-10-31 | 2014-10-31 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050139 | Field Maintenance Shop | 2013-06-17 | 2013-07-10 | Tycor Construction, LLC | 9751312 | 6577 | 5231 | 2013-08-30 | 2014-10-27 | 2014-10-01 | 2014-10-01 | 94% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | CALIFORNIA | UNITED STATES | 060413 | Maneuver Area Training & Equipment Site Ph 3 | 2013-08-01 | 2013-09-20 | Cox Construction Co. | W912LA-13-C-0003 | 31793 | 30449 | 2013-10-21 | 2014-10-01 | 2014-10-01 | 2015-09-30 | 67% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $7,612 funds from FY10 project savings {PNs: 180145 (1,500), 320143 ($3,112), 250087 ($2,000) & 160120 ($1,000)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090043 | Combined Support Maintenance Shop | 2013-06-25 | 2013-08-27 | Whiting Turner | W91ZRS-13-C-0002 | 30951 | 29441 | 2014-04-26 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 20% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | CONNECTICUT | UNITED STATES | 090115 | RIP RAP | 2014-08-28 | 2014-09-11 | Nutmeg Companies, Inc. | W91ZRS-12-D-0026-0005 | 3600 | 1292 | 2014-09-22 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 0% | 0 |  | 11 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 450252)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | DELAWARE | UNITED STATES | 100010 | Regional Training Institute Ph1 | 2013-06-28 | 2013-07-05 | EDIS Company | 40452 | 5319 | 5225 | 2013-09-23 | 2014-10-20 | 2014-10-01 | 2014-11-30 | 65% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120102 | Readiness Center | 2013-09-11 | 2013-09-18 | Munilla Construction Management (MCM) | 120102 Construction-MCM | 19345 | 20932 | 2014-03-03 | 2015-02-20 | 2015-02-20 | 2015-09-03 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120192 | Upgrade: Combined Arms Collective Training Facility | 2013-06-07 | 2013-06-25 | Thomas May Construction Company | 120192 Construction | 8705 | 6452 | 2013-10-04 | 2014-10-20 | 2014-10-01 | 2014-10-01 | 2% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 120228 | Ready Building | 2013-09-05 | 2013-09-10 | Halfacre Construction Company | 120228 SOD-C Ready D-B Halfacre | 1939 | 1920 | 2013-10-14 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | GUAM | GUAM | 140040 | JFHQ Ph 4 | 2013-08-22 | 2013-09-24 | NAVFAC Pacific | N40192-10-D-2800 | 8221 | 8089 | 2013-10-21 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | HAWAII | UNITED STATES | 150023 | Army Aviation Support Facility Ph1 | 2013-11-13 | 2014-09-11 | USPFO - HI | W912J6-14-R-00001 | 35078 | 33472 | 2014-09-22 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprgramming $7,996 funds from FY11 project savings {PNs: 200063 ($4,000) & 200090 ($3,996)}
2014-10-31 | 2013 | Army National Guard | Major Military Construction | IDAHO | UNITED STATES | 160100 | ORTC (Barracks) Ph2 | 2013-06-27 | 2013-09-27 | Trainor Enterprises | W912J7-13-C-0001 | 38692 | 37607 | 2013-10-07 | 2014-08-01 | 2014-08-01 | 2015-12-10 | 34% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180106 | Field Maintenance Shop | 2013-09-24 | 2013-09-24 | Gamong Construction | MDI-SAB-14-C-0002 | 8705 | 8481 | 2014-07-21 | 2014-12-25 | 2014-12-25 | 2015-05-30 | 40% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | INDIANA | UNITED STATES | 180144 | Armed Forces Reserve Center Add/Alt | 2013-09-20 | 2013-09-20 | Ziolkowski Construction | MDI-SAB-14-C-0001 | 20311 | 22016 | 2014-04-21 | 2015-05-29 | 2015-08-23 | 2015-05-29 | 21% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | IOWA | UNITED STATES | 190142 | Urban Assault Course | 2013-05-29 | 2013-06-07 | Rochon Corporation of Iowa | C751SI088 | 2902 | 2545 | 2013-08-09 | 2014-05-30 | 2014-04-30 | 2014-08-25 | 100% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | KANSAS | UNITED STATES | 200102 | Taxiway, Ramp & Hangar Alterations | 2013-05-21 | 2013-06-14 | Senne & Co | CONSTRUCTION | 9188 | 8405 | 2013-07-22 | 2014-05-02 | 2014-10-01 | 2014-07-04 | 70% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | KANSAS | UNITED STATES | 200127 | Water Distribution Lines, Portable | 2013-09-16 | 2013-09-24 | Harbin Construction | W912JC-12-D-5308 | 1440 | 1445 | 2014-04-07 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 75% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | KENTUCKY | UNITED STATES | 210001 | Army Aviation Support Facility | 2013-05-17 | 2013-06-04 | DW Wilburn | CT2 1300000269 | 30953 | 26217 | 2013-07-08 | 2014-11-10 | 2014-10-01 | 2014-10-01 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220241 | National Guard Readiness Center | 2014-09-05 | 2014-09-15 | Holly and Smith Architects | LA15-C-005 | 9300 | 8937 | 2014-09-22 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 0% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $4,400 - PN: 450252, $4,900 - PN: 450353 )
2014-10-31 | 2013 | Army National Guard | Major Military Construction | LOUISIANA | UNITED STATES | 220243 | Jackson Barracks Billeting Replacement | 2013-07-25 | 2014-07-25 | Gibbs Construction | LA06-C-081 | 5700 | 3817 | 2014-07-25 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 0% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, $3,000 - PN: 450252, $2,700 - PN: 450353)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 240194 | Combat Pistol/MP Firearms Qualification Course | 2013-09-26 | 2013-09-27 | W M Schlosser | 001B4400150 | 1920 | 1740 | 2014-04-21 | 2014-09-22 | 2014-09-22 | 2014-09-22 | 1% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250065 | Unit Training Equipment Site | 2013-06-19 | 2013-11-01 | Nauset Construction Corp. | W912SV-13-R-0001 | 21279 | 21202 | 2014-04-07 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | MASSACHUSETTS | UNITED STATES | 250196 | Water Well, Non-Potable | 2013-05-09 | 2013-05-17 | Corps of Engineers, New England District | DESIGN-250196-USACES | 2000 | 1838 | 2013-06-03 | 2013-12-02 | 2013-12-01 | 2013-12-01 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270236 | Scout Reconnaissance Range | 2013-08-26 | 2013-09-23 | Eagle Construction Company, Inc. | EAGLE - SWIFT 67879 | 16443 | 13235 | 2013-09-23 | 2015-08-01 | 2015-10-01 | 2016-01-01 | 50% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270238 | Readiness Center | 2013-08-08 | 2013-08-14 | LS Black Constructors | W912LM-13-C-0007 | 16443 | 17496 | 2013-09-30 | 2015-10-15 | 2015-10-15 | 2015-10-28 | 29% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290176 | Regional Training Institute | 2013-07-26 | 2013-08-01 | KCI Construction Company | T1203-01B | 17410 | 15704 | 2013-12-09 | 2015-02-28 | 2015-02-28 | 2015-07-21 | 60% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290215 | Readiness Center Add/Alt | 2013-09-10 | 2013-09-17 | Larrison Construction Inc. | T1206-01 | 1837 | 1857 | 2013-09-30 | 2014-05-27 | 2014-06-30 | 2014-06-30 | 100% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290216 | Readiness Center Add/Alt | 2013-06-02 | 2013-08-09 | Branco Enterprises | T1205-01B | 793 | 819 | 2014-09-23 | 2014-06-20 | 2014-05-09 | 2014-08-15 | 100% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290217 | Readiness Center Add/Alt | 2013-07-31 | 2013-08-05 | Zoellner Construction Co, Inc. | T1204-04 | 677 | 525 | 2013-10-21 | 2014-05-19 | 2014-02-14 | 2014-05-19 | 100% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011) (NGB 593)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | MONTANA | UNITED STATES | 300032 | Readiness Center | 2013-05-29 | 2013-06-07 | Jackson Contractor Group, Inc. |  | 10693 | 12421 | 2013-07-08 | 2014-12-15 | 2015-01-09 | 2015-01-21 | 78% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340110 | Regional Training Institute | 2013-06-17 | 2013-09-30 | Dobco, Inc. | SG301 | 32885 | 31977 | 2014-10-15 | 2016-08-01 | 2016-02-12 | 2016-07-12 | 5% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | NEW JERSEY | UNITED STATES | 340130 | Communication Lines and Ductbank, Underground | 2014-09-19 | 2014-09-26 | Rome Management Associates, LLC | W912KN-13-D-0029 | 2228 | 1393 | 2014-10-03 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 0% | 0 |  | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380053 | National Guard Vehicle Maintenance Shop Addition | 2014-09-24 | 2014-10-02 | Smithco Inc. | AGND14-52 | 1950 | 2000 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | NORTH DAKOTA | UNITED STATES | 380123 | RIP RAP | 2013-09-24 | 2013-12-02 | Close Construction Company | AGND14-01 | 2000 | 1889 | 2013-12-09 | 2014-08-30 | 2014-08-30 | 2014-11-07 | 6% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390230 | Readiness Center | 2013-04-01 | 2013-05-03 | Barton Marlow Company | Construction ADJ-090001 | 11607 | 8726 | 2013-08-01 | 2014-01-10 | 2013-12-01 | 2014-11-18 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Air National Guard | Major Military Construction | OHIO | UNITED STATES | 390256 | Field Maintenance Shop Add/Alt | 2013-06-07 | 2013-09-19 | Henderson Contractors, Inc. | W91364-13-Q-0003 | 1998 | 2943 | 2013-11-04 | 2014-10-28 | 2014-07-02 | 2014-12-01 | 95% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390263 | Hutments | 2014-05-12 | 2014-07-09 | USPFO - OH | USPFO - OH | 2900 | 2662 | 2014-07-16 | 2015-06-15 | 2015-06-15 | 2015-06-15 | 35% | 0 |  | 11 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10, PN: 060115)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | OKLAHOMA | UNITED STATES | 400066 | Operations Readiness Training Complex | 2013-08-20 | 2013-08-29 | Semi-USA | 13231 | 29185 | 27536 | 2013-10-25 | 2014-10-01 | 2014-10-01 | 2016-02-22 | 19% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $5,004 funds from FY11 project savings (PN: 200090)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PENNSYLVANIA | UNITED STATES | 420542 | Controlled Access Secure Facility | 2014-07-09 | 2014-10-24 | Miller Bros. Construction, Inc. | W912KC-14-R-0005 | 1825 | 1896 | 2014-10-30 | 2015-11-13 | 2015-11-13 | 2015-11-13 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430081 | Readiness Center (JFHQ) | 2013-06-27 | 2013-09-26 | R B Construction Group Inc. | W912LR-13-C-0001 | 18294 | 17448 | 2014-03-03 | 2015-09-18 | 2015-09-18 | 2015-09-25 | 23% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $3,786 funds from FY10 project savings {PNs: 370897 ($2,856) & 130077 ($1,300)}
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | PUERTO RICO | PUERTO RICO | 430622 | Sanitary Sewer | 2014-04-04 | 2014-08-27 | Integrated Construction Services, Inc. | W912LR-14-B-2005 | 1535 | 1897 | 2014-09-15 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430804 | Refill Station Building | 2013-06-25 | 2013-09-20 | Design Build S E | 430804 | 2128 | 2577 | 2013-10-28 | 2015-05-08 | 2015-05-08 | 2015-05-08 | 0% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430806 | Readiness Center | 2013-06-06 | 2013-09-26 | Design Build S E | 430806 | 3675 | 3643 | 2014-02-10 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 0% | 0 |  | Grow the Army, PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490076 | BEQ Facility (Regional Training Institute) | 2013-06-06 | 2013-07-23 | Okland Construction Co. Inc. | 137861 | 14508 | 15729 | 2013-08-12 | 2014-11-10 | 2014-10-01 | 2014-11-30 | 75% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | UTAH | UNITED STATES | 490444 | Regional Training Institute Ph2 | 2013-06-13 | 2013-07-30 | Jacobsen Construction Company | 137862 | 28772 | 28259 | 2013-08-26 | 2014-09-30 | 2014-09-30 | 2015-03-30 | 72% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)/2853 Notification & Formal Reprogramming $8,461 funds from FY11 project savings (PN: 200063)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | UTAH | UNITED STATES | 490803 | Unheated Aircraft Storage Hangar | 2013-11-06 | 2014-07-18 | Keller Construction Inc. | 147589 | 2000 | 1889 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 0% | 0
2014-10-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530015 | Readiness Center | 2013-07-29 | 2013-08-01 | US Army Corp of Engineers (Seattle) | USACE Construction Contract | 33853 | 30257 | 2013-09-23 | 2015-10-26 | 2015-08-20 | 2015-08-27 | 19% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | WASHINGTON | UNITED STATES | 530035 | National Guard Readiness Center | 2014-08-15 | 2014-08-20 | Absher Construction | Absher Construction | 26000 | 23740 | 2014-10-06 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 0% | 0 |  | 10 USC 2854, Restoration or Replacement of Damaged or Destroyed Facilities (Funds reprogrammed from FY10 -$3,000 - PN: 140300, $3,500M - PN: 270261, $6,000 - PN: 280308, $4,500 - PN: 450353, $2,500 - PN: 460141 and from FY11 - $6,500 - PN: 050163)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | WEST VIRGINIA | UNITED STATES | 540075 | Readiness Center | 2013-09-13 | 2013-09-18 | Paramount Builders LLC | DEFK14000 | 13734 | 14988 | 2014-04-07 | 2015-09-11 | 2015-09-11 | 2015-09-11 | 0% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Major Military Construction | WISCONSIN | UNITED STATES | 550142 | Field Maintenance Shop | 2013-08-09 | 2013-09-10 | Ellis Stone Construction Company | NGB-47-13-C-0005 | 9673 | 9180 | 2013-10-28 | 2014-10-01 | 2014-10-01 | 2015-04-15 | 25% | 0 |  | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction | WISCONSIN | UNITED STATES | 550161 | National Guard Readiness Center Addition | 2013-09-24 | 2013-09-25 | Miron Construction | NGB-47-13-C-0009 | 1920 | 909 | 2013-12-12 | 2014-09-01 | 2015-07-01 | 2014-08-01 | 80% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | ALABAMA | UNITED STATES | 011014 | National Guard Readiness Center Add/Alt | 2014-08-14 | 2014-08-19 | Carmon Construction, Inc. | AC-14-C-0045-S | 4000 | 3756 | 2014-10-06 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | ARKANSAS | UNITED STATES | 050182 | Scout REECE Gunnery Complex | 2014-03-20 | 2014-09-03 | SSI Incorporated | W912JF-14-B-0001 | 21000 | 16758 | 2014-10-20 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | FLORIDA | UNITED STATES | 120195 | Ready Building | 2014-02-19 | 2014-03-11 | J. Kokolakis Contracting, Inc. | 120195 D-B Kokolakis | 5700 | 5300 | 2014-04-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170033 | National Guard Readiness Center | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2004-100 | 14000 | 16000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | ILLINOIS | UNITED STATES | 170127 | Aircraft Maintenance Hangar | 2014-06-11 | 2014-06-27 | George Scollitt Construction Co. | W91SMC-14-2-2003-100 | 28000 | 30000 | 2014-07-21 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | MASSACHUSETTS | UNITED STATES | 250095 | Enlisted Barracks, Transient Training Addition | 2014-07-21 | 2014-09-18 | Nutmeg Company | W912SV-14-C-0008 | 19000 | 20559 | 2014-09-15 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | MICHIGAN | UNITED STATES | 260051 | Enlisted Barracks, Transient Training | 2014-06-15 | 2014-06-27 | Aspen Contracting, Inc. | Y14290 | 17000 | 17398 | 2014-08-11 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | MINNESOTA | UNITED STATES | 270014 | National Guard Readiness Center | 2014-09-09 | 2014-09-12 | CM Construction Company, Inc. | 835457 | 17000 | 17943 | 2014-09-29 | 2016-04-09 | 2016-04-09 | 2016-04-09 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Unspecified Minor Military Construction | MISSISSIPPI | UNITED STATES | 281305 | Raw Sewage Lagoon and Oxidation Pond | 2014-09-24 | 2014-09-26 | Miller Enterprises | 01 Construction | 1950 | 1039 | 2014-09-30 | 2005-04-30 | 2015-04-30 | 2015-04-30 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280272 | National Guard Readiness Center | 2014-06-17 | 2014-06-26 | D.N.P., Incorporated | NGB-22-14-C-0003-S | 4500 | 4718 | 2014-07-14 | 2015-10-01 | 2015-10-01 | 2015-10-01 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | MISSISSIPPI | UNITED STATES | 280423 | Water Supply/Treatment Building, Potable | 2014-07-01 | 2014-07-15 | Larry J. Sumrall Contractors | NGB22-14-C-0005-S | 3000 | 2581 | 2014-08-15 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290191 | National Guard Vehicle Maintenance Shop | 2014-04-24 | 2014-04-29 | Sircal Contracting Inc. | T1227-01C | 9100 | 7188 | 2015-05-12 | 2012-04-30 | 2015-07-31 | 2014-05-19 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | MISSOURI | UNITED STATES | 290221 | Aircraft Maintenance Hangar | 2014-06-26 | 2014-07-10 | Global Environmental, Inc. | W912NS-14-R-1000 | 5000 | 4399 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 2015-06-26 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | NEW YORK | UNITED STATES | 360161 | National Guard Readiness Center Alteration | 2014-09-17 | 2014-09-30 | Design Resources Group Architects, A.I.A, Inc. | State Contract MILCON 5th Avenue | 31000 | 27714 | 2014-10-20 | 2016-05-30 | 2016-05-30 | 2016-05-30 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | OHIO | UNITED STATES | 390292 | Sanitary Sewer | 2014-04-04 | 2014-09-04 | USPFO - OH | W91364-13-D-0003 | 5200 | 4974 | 2014-09-08 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 30% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | PENNSYLVANIA | UNITED STATES | 420051 | Aircraft Maintenance Instructional Building | 2014-08-29 | 2014-09-25 | Senate Builders & Const Manager | W912KC-14-C-0006 | 40000 | 31940 | 2014-10-20 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | PUERTO RICO | PUERTO RICO | 430070 | Maneuver Area Training & Equipment Site Addition | 2014-03-03 | 2014-08-26 | Maglez Engineering and Contractor Corp | W912LR-14-B-20003 | 5600 | 4418 | 2014-09-15 | 2015-05-30 | 2015-05-30 | 2015-05-30 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450131 | National Guard Vehicle Maintenance Shop | 2014-09-19 | 2014-09-23 | Hendrick Construction, Inc. | 460003 | 13000 | 12400 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 450283 | National Guard Readiness Center | 2014-09-19 | 2014-09-25 | Hendrick Construction, Inc. | 460003 | 13000 | 12401 | 2014-10-06 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 0% | 0
2014-10-31 | 2014 | Army National Guard | Major Military Construction | WYOMING | UNITED STATES | 560081 | National Guard Readiness Center | 2013-12-16 | 2014-03-11 | Layton Construction Company, Inc. | 13002900601 | 10200 | 9748 | 2013-10-10 | 2015-03-31 | 2015-03-31 | 2015-08-31 | 25% | 0
2014-10-31 | 2013 | Defense Finance and Accounting Service | Major Military Construction | TEXAS | UNITED STATES | 80230 | DFAS Administration Building | 2013-04-24 | 2013-07-30 | US Army COE Guyco, INC | Contract No. W9127S-09-D-6006 | 12903 |  | 2013-09-11 | 2015-09-05 | 2015-03-05 | 2015-04-05 | 19%
2014-10-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 77620 | Fisher House Utility Upgrade | 2010-03-01 | 2010-05-04 | NICC JV LLC | N40080 08 D 0305 DO 0816 | 180 | 180 | 2010-05-30 | 2010-10-19 | 2010-08-09 | 2010-08-09 | 100% |  |  | Financially closed
2014-10-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 78145 | Satellite Pharmacy (Corry Station) | 2011-08-17 | 2011-10-20 | American Contractor & Technology, Inc | N69450 12 C 6323 | 1236 | 1321 | 2011-12-01 | 2013-04-01 | 2012-09-18 | 2013-04-01 | 100% |  |  | Project is not financially closed.
2014-10-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 79923 | LRC Extension | 2011-09-12 | 2011-09-29 | Grunley/Growel JV, LLC | N40080 06 D 0004 DO 9001 | 694 | 799 | 2011-12-21 | 2012-10-19 | 2012-06-22 | 2012-08-10 | 100% |  |  | Financially closed
2014-10-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 75132 | Joint Navy-VA Project |  | 2013-09-27 | Billy W. Jarrett Const Co Inc | N62470 13 MPS 0046 | 1797 | 1899 |  |  | 2014-10-15 | 2014-10-15 |  |  |  | Funds transferred from NAVFAC to VA to execute. Project is not financially closed out.
2014-10-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81004 | Site Development, NiCOE | 2012-05-16 | 2012-06-05 | Sunland Builders, Inc | N40085 09 D 9027 DO 0026 | 1363 | 1450 | 2012-08-01 | 2013-08-12 | 2013-08-29 | 2013-08-29 | 100% |  |  | Project is not financially closed.
2014-10-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction |  | GUANTANAMO BAY NAVAL BASE | 82095 | Veterinary Treatment Facility Alterations
2014-10-31 | 2008 | Defense Health Agency | Unspecified Minor Military Construction | DELAWARE | UNITED STATES | 69371 | Bio-Environmental Engineering Facility | 2009-05-12 | 2009-08-21 | Ventresca Brothers |  | 1354 | 1374 | 2009-09-08 | 2011-01-19 | 2010-09-10 | 2010-09-30 | 100% |  |  | Final payment made 20 July 2012. Contract is closed. Financial closeout complete.
2014-10-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 74085 | Medical Admin Annex | 2010-06-22 | 2010-09-28 | John Bowman, Inc |  | 1757 | 1810 | 2010-10-20 | 2011-01-19 | 2011-08-01 | 2011-07-29 | 100% |  |  | Project completed and closed. DD1354 information requested. Looking into best source to provide DHA w/transfer documents.
2014-10-31 | 2009 | Defense Health Agency | Unspecified Minor Military Construction |  | GERMANY | 68974 | Computer Operations Center | 2011-02-01 | 2011-04-22 | Federal Republic of Germany |  | 1950 | 1950 | 2011-05-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100% |  |  | Project compeleted.
2014-10-31 | [7 empty] | 2011-01-08 | 2011-03-14 | Wayss & Freytag |  | 1572 | 1548 | 2013-04-11 | 2011-12-09 | 2011-01-31 | 2011-12-09 | 100%
2014-10-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | MARYLAND | UNITED STATES | 77342 | Bldg 509 Alteration of Medical Laboratory | 2010-12-17 | 2011-01-28 | Odyssey International, Inc |  | 3294 | 3690 | 2011-02-16 | 2011-09-15 | 2011-09-15 | 2011-08-15 | 100% |  |  | Undelivered orders/commitments ($36,173) returned. Preparation for fiscal closeout.
2014-10-31 | 2010 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 77216 | Flight Medicine Addition | 2010-08-10 | 2010-09-30 | Synergy Systems, Inc |  | 1679 | 1694 | 2010-10-27 | 2012-02-16 | 2011-11-18 | 2011-11-18 | 100% |  |  | 1 Feb 13 - Customer has taken occupancy of the building. Project closed.
2014-10-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction | NEVADA | UNITED STATES | 80093 | Medical Ed. & Training Facility | 2012-03-01 | 2012-05-31 | Synergy Systems, Inc |  | 1698 | 1982 | 2012-08-14 | 2014-09-10 | 2013-11-14 | 2014-08-24 | 100% |  |  | AT/FP Modification was negotiated on 27 Sept 2013 with 72 calendar day extension. Revised Final Design completed 15 JAN 14. Physical Construction to start FEB 2014. Preconstruction Meeting held 31 JAN 2014. Physical Construction (mobilization) started FEB 2014. BOD 11 AUG 2014. Project Complete. The field office is currently working with the contractor on punch list items. Some of punch list items might require the shut down at least 10 hours to the Mike O'Callaghan Federal Medical Center so the contractor can repair a shutter in the switch gear. Coordination for the shutdown between the affected departments is in progress. The field office is trying to see if it can happen before the 31 December to minimize the impact to the patients.
2014-10-31 | 2011 | Defense Health Agency | Unspecified Minor Military Construction |  | JAPAN | 78853 | New Clinic Addition | 2015-06-15 | 2015-08-14 | [11 empty] | There is a chance there will be no bids after repackage...FY11 funds expire 30 Sep 2015. Construction schedule will coincide with SRM project (PN74868) Phase 2 schedule (complete Dec '15) to connect new utilities from the UMC addition project to the SRM existing clinic and avoid any mold growth in the addition area if left unoccupied for several months. Solicitation issued 9 May 14 via RFP (DBB) vice IFB due to recent bid busts on other POJ projects. Unfortunately, no bids were received on the bid opening date of 11 Jul 14. On 29 Jul 14, District met with one of the two contractors who had displayed interest but did not submit a proposal. Several reasons for deciding to not submit a proposal, including not being able to propose an amount below the stat limit, inflation due to 2020 Olympics and reconstruction after the Great Tsunami of March 2011. District met with MEDDAC reps on 15 Aug and discussed de-scoping the project, e.g., changing from a raised slab to a slab-on-grade. A mod to the A-E contract will be awarded in Nov 14 to de-scope the project. Project will be re-solicited. The eventual construction contract will utilize FY11 funds, for which the budget foreign currency exchange rate (101.9517 yen/$) is favorable versus subsequent fiscal years (< 92 yen/$). It’s important that the contract is awarded NLT end FY15. Scope Reduction plan: a. Delete the following functions: 1) Toilet (customers and end-users) will use toilets in main clinic. 2) Mask Fit Testing - this function will remain at the current Preventive Medicine building. b. Reduce the following areas in size: 1) Sub-waiting area - will utilize the Clinic's waiting area, but need access into new corridor. 2) Classroom. c. Reduce scope of the Pergola to a Torii Gate (insert as a bid option). d. Change Wellness Center to Community Health Nurse - this is not de-scoping but changing of a function. e. Construction methods: 1) Provide a slab on grade in lieu of a raised slab. 2) Changing design of roofing system to match the same type being installed for the SRM project (PN74868). 3) Provide only one staging area for contractor. 4) Eliminate cherry blossom tree (80+ years old) salvaging. 5) Delete air barrier testing. 6) Eliminate sound testing for Sound Booth Room - wall construction should provide for adequate sound transmission through walls. 7) Stub-out for plumbing from new SRM toilets for new sinks in Clinic Addition. 8) Delete plumbing fixtures in new classroom (move new Community Health Nurse & Public Health Nurse to that location since the SRM contains plumbing along that wall which is near the new toilets for the SRM project. 9) Relocate electrical closet to location near the new SRM electrical room (Grid Line 1-A).
2014-10-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | KENTUCKY | UNITED STATES | 81247 | Site Dev in Support of NiCOE | 2012-08-15 | 2012-09-28 | GKK |  | 1589 | 1638 | 2012-10-28 | 2014-07-30 | 2014-01-03 | 2014-07-15 | 99% |  |  | Contractor has completed deficiencies listed during the Final Inspection. Currently awaiting the Contractor's final billing with the signed ENG 93 and Release of Claims. Anticipate Final Payment to occur before the end of September.
2014-10-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | 80792 | Site Development, NiCOE |  | 2012-07-30 | Dominion Virginia Power, American Water Operations and Maintenance, Inc., and Defense Telecommunication Service |  |  | 1690 |  | 2013-06-30 |  |  | 100% |  |  | Project required no USACE Contract or Administration. Funds MIPR'ed to Garrison. Work executed via FBVA contract. 100% complete. BOD achieved 30 June 2013. Received invoice from DLA rep who manages American Water (water & wastewater) showing that they were paid in full, don't have a separate document from American Water that is a Release of Claims. Received from DPW a copy of a "Project Completion Form" sent by Dominion Virginia Power (electricity). PM was told this is what DPW requires from DVP when a project is complete. Received the last "Release of Claims" from NEC/ITA/Verizon with the statement, "All, I attached the MIPR Acceptance Form for the NICOE Building 1259. NEC was provided $68,141.25 to install the Outside Plant Copper and Fiber Cables. NEC/ITA/Verizon Federal completed the installation July 2013. No further funding required." Project Fiscal Closeout Ongoing.
2014-10-31 | 2012 | Defense Health Agency | Unspecified Minor Military Construction | WASHINGTON | UNITED STATES | 80094 | Veterinary Clinic | 2012-08-03 | 2012-09-29 | Synergy Systems, Inc | W912BV-12-C-0030 | 2021 | 2022 | 2013-10-03 | 2014-12-05 | 2015-10-01 | 2015-03-05 | 67% |  |  | Interior MEP (mechanical, electrical, plumbing) is complete: HVAC ducting installed and ready for insulation; Electrical contractor is currently pulling conductors; Rough-in plumbing has been pressure checked. Drywall installed, taping, fire chalking, and mud complete with final sanding underway. Concrete sidewalks are cast, sealed, and forms stripped. Asphalt parking lot to be paved week of 29 SEP. Communications systems installation to begin the week of 29 SEP. Contractor submitted REA for a waterline they broke during excavation for sewer connection. Basis of case is that waterline was not located within 24" of the utility locate markings. Initial meeting held, and challenges were answered by contractor, revised amount is $26k but still appears unreasonable. Additional discussions are being scheduled. DB
2014-10-31 | 2013 | Defense Health Agency | Unspecified Minor Military Construction | FLORIDA | UNITED STATES | 82358 | Veterinary Clinic Replacement | 2014-03-26 | 2015-06-30 | [6 empty] | 2016-05-30 |  |  |  |  | PA is $1.5M and CWE is $1.98M. PDT will identify acceptable cost reduction measures. Once a confidence level is established that the requirements of the RFP have been adjusted to achieve the target CWE, a revised solicitation will be issued to the SWL SB Medical MATOC pool and proposals requested. SAM will develop a schedule and budget to complete this proposed action which can begin in Oct 14 if funding is available. New projected award date is 30 Jun 15.
2014-10-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | DELAWARE | UNITED STATES | 86204 | Medical Warehouse Add/Alt | [8 empty] | 2016-06-16 | 2016-06-16 | 0% |  |  | Design Build admin space.
2014-10-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 81631 | NiCOE Satellite, Infrastructure Support | 2014-03-21 | 2014-06-18 | [6 empty] | 2015-04-24 | 2015-04-24 | 10%
2014-10-31 | 2014 | Defense Health Agency | Unspecified Minor Military Construction | TEXAS | UNITED STATES | 81706 | NiCOE Satellite, Infrastructure Support | 2014-08-01 | 2014-08-21 | [11 empty] | DB. Construction to start 25 Oct. SWF to provide other dates on next submission.
2014-10-31 | 2010 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 401V | Traffic Mitigation Increment 1 | 2010-03-05 | 2010-05-10 | Clark/Balfour Beatty, JV, Gates N&S Wood Drive | N40080 10 C 1504 | 9512 | 10848 | 2010-07-01 | 2011-08-15 | 2011-07-31 | 2011-08-15 | 100% |  |  | Authorization of Project is financially closed.
2014-10-31 | 2011 |  |  |  |  | 401V | Traffic Mitigation Increment 1 | 2010-03-16 | 2010-06-21 | Whiting-Turner, University Road & Perimeter Road/Palmer Road | N40080 10 C 1505 | 8800 | 10291 | 2010-07-01 | 2011-08-15 | 2011-08-31 | 2011-08-23 | 100%
2014-10-31 | 2011 |  |  |  |  | 401A | Traffic Mitigation Increment 2 | 2010-11-14 | 2011-04-21 | RMA Land Construction Inc, Gates Gunnell & Grier | N62742 09 D 1185 | 5572 | 5982 |  | 2012-09-02 | 2012-12-06 | 2012-11-26 | 100%
2014-10-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 005V | Medical Center Add/Alt, Inc 1 | 2007-08-27 | 2008-03-03 | Clark/Balfour Beatty, JV | N40080 08 C 0007 | 757737 | 774314 | 2008-07-01 | 2010-08-01 | 2011-07-31 | 2012-09-15 | 100% |  |  | Actively working to close - invoices and deobligations
2014-10-31 | [5 empty] | 005A | Medical Center Add/Alt, Inc 2 |  |  |  | N40080 08 C 0007
2014-10-31 | [5 empty] | 005B | Medical Center Add/Alt, Inc 3 |  |  |  | N40080 08 C 0007
2014-10-31 | [5 empty] | 005B | Medical Center Add/Alt, Congressional Notification |  |  |  | N40080 08 C 0007
2014-10-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MISSISSIPPI | UNITED STATES | 478V | Community Hospital | 2009-04-01 | 2009-11-10 | W.G. Yates & Sons Construction Co. | N69450 10 C 0763 | 38252 | 42256 | 2010-01-01 | 2012-02-25 | 2011-09-11 | 2012-10-11 | 100% |  |  | Not financially closed. Final invoicing for equipment - working with DLA.
2014-10-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 020V | Site Utility Infra Upgrade for NiCOE | 2008-07-08 | 2008-12-22 | Turner Construction Company | N40080 09 C 1502 | 7295 | 7371 | 2009-01-01 | 2010-03-29 | 2010-03-06 | 2010-04-30 | 100% |  |  | Project is financially closed.
2014-10-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 796V | Supt Fac for WTC Admin Ctr (BQ/Dining) | 2009-04-01 | 2009-08-26 | Whiting-Turner | N40080 09 C 0018 | 117555 | 126445 | 2010-02-01 | 2011-07-13 | 2011-05-31 | 2011-09-11 | 100% |  |  | Project is financially closed.
2014-10-31 | 2008 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 701V | Consolidation of Administration Spaces (WTU Admin), Inc 1 | 2009-04-01 | 2009-08-26 | Whiting-Turner | N40080 09 C 0018 | 68529 | 78196 | 2010-02-01 | 2011-08-01 | 2011-08-01 | 2011-09-11 | 100% |  |  | Project is financially closed.
2014-10-31 | 2009 |  |  |  |  | 701A | Consolidation of Administration Spaces (WTU Admin), Inc 2 |  |  |  | N40080 09 C 0018
2014-10-31 | 2007 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64238 | Hopsital Replacement, Inc 1 | 2007-06-12 | 2007-09-28 | Turner/Gilbane JV |  | 649025 | 9428 | 2007-10-11 | 2011-08-01 | 2011-03-01 | 2012-01-31 | 100% |  |  | Claim pending for approx $10.6M. T/G has indicated that the claim will be withdrawn. NAO fwded Withdrawal and Release of Claim to T/G 25 Sep; DCAA Audit negotiations were successful. Bi-lateral mod and final release to be sent to T/G by 15 Oct. Currently retaining $4M until DCAA audit is finally resolved. Do not anticipate the final settlement to exceed current contract amount. One remaining MIPR to MEDCOM needs a contract de-obligation of $332K (DLA action). Weekly call with MEDCOM to track progress.
2014-10-31 | [5 empty] | 64238 | Hopsital Replacement, Inc 2 |  | 2008-04-04 |  |  |  | 376782
2014-10-31 | [5 empty] | 65676 | Hopsital Replacement, Inc 3 |  | 2008-12-23 |  |  |  | 241353
2014-10-31 | [5 empty] | 69865 | Hopsital Replacement, Inc 4 |  | 2010-01-23 |  |  |  | 119266
2014-10-31 | [5 empty] | 77071 | Hopsital Replacement, Inc 5 |  | 2010-10-20 |  |  |  | 211800
2014-10-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64179 | San Antonio Regional MEDCEN, Inc 1 | 2008-08-15 | 2008-07-31 | Clark/Hunt Construction |  | 107589 | 135926 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 99% |  |  | There are still actions on-going that will prevent close-out: 1. There are Department of Labor Investigations on going on some of Clark-Hunt Invoices. Resolution period to be determined. Clark-Hunt was the construction contractor. 2. Firm EYAK Technology, Inc payments have been suspended. They provided the telephones for the project. Throughout USACE invoices from EYAK Technology, Inc continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. USACE does not expect this matter to be resolved by the Department of Justice during FY 2014. The status is unchanged. The SWF invoices continue to be considered as part of monies owed USACE and are covered by a Contracting Officer's Demand of monies owed USACE. I do not expect this matter to be resolved by the Department of Justice during FY 2014. - Per USACE CT Office 3. TEAM Integrated Services Task Orders. Last DCAA audit is estimated to be completed 31 Dec 2015.
2014-10-31 | 2009 |  |  |  |  | 64180 | San Antonio Regional MEDCEN, Inc 2 |  |  |  |  | 265100 | 279273
2014-10-31 | 2010 |  |  |  |  | 69840 | San Antonio Regional MEDCEN, Inc 3 |  |  |  |  | 13748 | 243943
2014-10-31 | 2011 |  |  |  |  | 70990 | San Antonio Regional MEDCEN, Inc 4 |  |  |  |  | 37554 | 85520
2014-10-31 | 2008 | Defense Health Agency | Base Realignment and Closures | TEXAS | UNITED STATES | 64188 | Health Clinic | 2008-02-01 | 2008-06-03 | Satterfield & Pontikes Construction |  | 33382 | 37382 | 2008-06-30 | 2010-05-17 | 2010-05-10 | 2010-05-10 | 99% |  |  | Construction 100% Complete. REA was paid and all remaining funds were returned to the customer on the project. There is a small dispute between the USACE labor reviewers and the sub as to the amount of restitution owed to employees. Both agree that it is due; the difference in the numbers is approximately $80k. This has been transferred to DOL for their action at the request of the contractor.
2014-10-31 | 2010 | Defense Health Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 64241 | Dental Clinic | 2009-09-16 | 2010-05-04 | Forrester Construction Company |  | 7541 | 8818 | 2010-05-18 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | NAB received 0516 BRAC Consolidated funding, executed the Global Settlement Modification, paid Final Invoice, and received Release of Claims from Contractor. Construction Contract and Project in Close Out Phase. Fiscal Closeout is scheduled, and tracking for 28 Nov 2014.
2014-10-31 | 2009 | Defense Health Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | 64156 | USAMRICD Replacement, Inc 1 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC | W912DR-09-C-0052 | 14398 | 16018.3843 | 2010-03-15 | 2014-11-24 | 2013-06-01 | 2014-12-22 | 99% |  |  | (10/30/14) PDT (USACE/HFPA/ICD) coordinating for partial BOD of administrative spaces in Bldgs A/B/C for 24 Nov 14, with follow on remaining BOD on 22 Dec 14 for remainder of spaces. Contractor continues to struggle with comissioning activities, significantly impacting schedule & timeline for final acceptance of equipment/systems. DHA On-Site Quarterly scheduled for 08 October 2014. (Historical data: Project reprogrammed through ACSIM as a BTR 02/27/13. Increase = $1.699M. No new BRAC obligations post 15 Sept 2011. Expenditure of BRAC funds will occur on mandatory changes through completion of project.) Split funded with DODM. NAB will provide financial close out date.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | GUAM | GUAM | 65270 | Hospital Replacement, Inc 1 | 2010-03-19 | 2010-09-30 | Watts Webcor Obayashi A JV | N62742 10 C 1304 | 158133 | 165418 | 2010-11-01 | 2014-03-18 | 2014-10-15 | 2015-03-27 | 96% | 19460 |  | 93% complete is 100% of the hospital completion. The remaining 7% is the demo of the existing facility. Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2014-10-31 | 2011 |  |  |  |  | 65271 | Hospital Replacement, Inc 2 (Not Funded) | [13 empty] | Cancelled due to funds not being necessary
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77154 | Ambulatory Care Center, Inc 1 | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 197804 | 137444 | 2013-03-01 | 2016-12-06 | 2016-12-06 | 2017-11-08 | 39% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K
2014-10-31 | 2014 |  |  |  |  | 81291 | Ambulatory Care Center, Inc 2 | [5 empty] | 66430 | [7 empty] | DHA issued $76,200,000 of FY14 MILCON dollars to NAVFAC for ACC, Inc 2, JB Andrews on 3/11/14
2014-10-31 | 2017 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES |  | Medical Center Add/Alt, Inc 1
2014-10-31 | 2018 | [5 empty] | Medical Center Add/Alt, Inc 2
2014-10-31 | 2019 | [5 empty] | Medical Center Add/Alt, Inc 3
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 65731 | USAMRICD Replacement, Inc 1 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 6887.87 | 7070.1979 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC
2014-10-31 | 2009 |  |  |  |  | 65731 | USAMRICD Replacement, Inc 1 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 12000 | 12658 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | Tier 2 P2 shows ESP $6,956,749; Main Building $21,759,697; NOTE: $6,840 for ESP award w/Balance on BRAC. $9,000 recinded as a result of Sequestration (04/29/13).
2014-10-31 | 2010 |  |  |  |  | 67180 | USAMRICD Replacement, Inc 2 | 2009-01-07 | 2009-04-08 | Total Engineering for Site Package | W912DR-09-C-0030 | 461.47 | 824.7486 | 2009-08-19 | 2010-08-31 | 2010-08-08 | 2010-08-31 | 100%
2014-10-31 | [7 empty] | 2010-08-01 | 2010-08-23 | BGE for Gas Line Contract |  | 280.922 | 280.922 | 2010-10-01 | 2011-10-01 | 2011-09-30 | 2011-09-30 | 100%
2014-10-31 | [7 empty] | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 100375 | 103745.3283 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | Main Building $142,857,143 FY10 Increment Awarded at $100,375,000 on 5 Mar 10 ($109,567,007 funded per D. Pritchett 17 Mar 10 email)
2014-10-31 | 2011 |  |  |  |  | 67181 | USAMRICD Replacement, Inc 3 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 94608 | 96044.5065 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | Full FY11 MILCON increment placed against contract.
2014-10-31 | 2012 |  |  |  |  | 67182 | USAMRICD Replacement, Inc 4 | 2009-02-25 | 2009-08-14 | Clark Construction Group, LLC (Contract for main building) | W912DR-09-C-0052 | 7915.345 | 26535.742 | 2010-03-15 | 2014-11-01 | 2013-06-01 | 2014-12-22 | 99% |  |  | (10/30/14) PDT (USACE/HFPA/ICD) coordinating for partial BOD of administrative spaces in Bldgs A/B/C for 24 Nov 14, with follow on remaining BOD on 22 Dec 14 for remainder of spaces. Contractor continues to struggle with comissioning activities, significantly impacting schedule & timeline for final acceptance of equipment/systems. DHA On-Site Quarterly scheduled for 08 October 2014. (Historical data: Project reprogrammed through ACSIM as a BTR 02/27/13. Increase = $1.699M. No new BRAC obligations post 15 Sept 2011. Expenditure of BRAC funds will occur on mandatory changes through completion of project.) Split funded with DODM. NAB will provide financial close out date.
2014-10-31 | 2007 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 58395 | USAMRIID Replacement Stage I, Increment 1 | 2007-06-30 | 2007-09-29 | Cont #1 - Offiste San Sewer & Storm (James Construction) | W912DR-07-C-0070 | 2657 | 2657 | 2007-10-12 | 2008-07-23 | 2008-06-13 | 2008-06-08 | 99% |  |  | Work complete. Contracts closed.
2014-10-31 | [6 empty] | USAMRIID Replacement Stage I, Increment 1 | 2008-01-10 | 2008-08-01 | Cont #2 - Storm Lat 1&3A (James Construction) | W912DR-08-C-0038 | 1472 | 1472 | 2008-08-19 | 2009-03-03 | 2009-02-15 | 2009-02-13 | 99% |  |  | Work complete. Contracts closed.
2014-10-31 | [6 empty] | USAMRIID Replacement Stage I, Increment 1 | 2008-05-01 | 2009-09-28 | Cont #3 - IMP Pond (James Corporation) | W912DR-08-C-0078 | 706 | 706 | 2009-10-15 | 2010-04-13 | 2010-04-13 | 2010-04-13 | 99% |  |  | Work complete. Contracts closed.
2014-10-31 | [6 empty] | USAMRIID Replacement Stage I, Increment 1 | 2008-01-10 | 2008-09-25 | Cont #4 - Early Site/Utility (Grunley/Goel JVA LLC) | W912DR-08-C-0053 | 2465 | 2465 | 2008-12-05 | 2009-07-24 | 2009-07-24 | 2009-07-24 | 99% |  |  | Work complete. Contracts closed.
2014-10-31 | [6 empty] | USAMRIID Replacement Stage I, Increment 1 | N/A (SSP Mod) | 2008-07-15 | Con# 7 - SSP Equipment (John C. Grimberg Co., Inc.) | W912DR-08-C-0016 | 2866 | 2866 | 2008-07-15 | 2013-12-06 | 2011-05-06 | 2013-10-31 | 99% | 2289 |  | Work being accomplished by contract modification to USAMRIID Steam Sterilization Plant project (FY 06, DODM, Army PN 059215). BOD/completion dates shown are for that project. *** Need to add Contract #7 line items for FY 10/11 funding. FY 10: original contract amount ($496,221) and current contract/total obligation ($524,505.60). FY 11: original contract amount ($603,803) and current contract/total obligation ($638,219.77). DHA provided $800K of reprogrammed FY10 MILCON funds from the Blood Donor Center, Ft. Benning project to the FY07 SSP project via 0$FAD on 3/4/14.
2014-10-31 | 2010 | [5 empty] | USAMRIID Replacement Stage I, Increment 4 |  |  |  | W912DR-08-C-0016 | 496 | 525 | [7 empty] | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2014-10-31 | 2011 | [5 empty] | USAMRIID Replacement Stage I, Increment 5 |  |  |  | W912DR-08-C-0016 | 603 | 638 | [7 empty] | Line added to show correct FYI funds usage. Work was accomplished by contract modification to USAMRIID Steam Sterilization Plant (FY06, DODM, PN 059215). BOD/completion dates are shown for that project.
2014-10-31 | 2007 | [5 empty] | USAMRIID Replacement, Incr 1 | 2008-08-14 | 2009-03-27 | Cont # 5 - USAMRIID Replacement Stage I, Phase I (Manhattan/Torcon JV) | W912DR-09-C-0026 | 15736 | 16161 | 2009-06-01 | 2017-07-01 | 2014-05-31 | 2014-10-21 | 94% |  |  | % Complete (Scheduled/Actual): 99/94 Phase I - MTJV contract increments are fully funded. Systems commissioning activities underway. T&E change under negotiation. Primary facility BOD is changed to 1 Jul 17 due to fire in BSL-4 area. Work continues in unaffected areas of the facility. FY07, FY08, FY10, and FY11 funds fully obligated. Project has consumed original 5% contingency, but has $15M remaining for certification. Two-phase occupancy acceptance planned - Jun 2016 for admin, BSL2, and BSL3 suites, July 2017 for BSL4.
2014-10-31 | 2008 |  |  |  |  | 63418 | USAMRIID Replacement, Incr 2 |  |  |  | W912DR-09-C-0026 | 131264 | 138491 | [7 empty] | Phase I - FY 08 (note corrected PN)
2014-10-31 | 2009 |  |  |  |  | 63419 | USAMRIID Replacement, Incr 3 |  |  |  | W912DR-09-C-0026 | 185526 | 185630 | [7 empty] | Phase I - FY 09 UPDATE JUN 13: PA decremented due to sequestration.
2014-10-31 | 2010 |  |  |  |  | 63420 | USAMRIID Replacement, Incr 4 |  |  |  | W912DR-09-C-0026 | 94000 | 100180 | [7 empty] | Phase I - FY 10 UPDATE JUN 13: PA decremented due to sequestration.
2014-10-31 | 2011 |  |  |  |  | 65324 | USAMRIID Replacement, Incr 5 |  |  |  | W912DR-09-C-0026 | 13497 | 12893 | [7 empty] | Phase I - FY 11 (note - previous report inadvertently included the contract 7 value - the amount has been corrected to avoid doublecounting)
2014-10-31 | 2012 |  |  |  |  | 71101 | USAMRIID Replacement, Incr 6 |  |  |  | W912DR-09-C-0026 | 66955 | 83767 | [7 empty] | Phase I - FY 12. UPDATE JUN 13: PA decremented due to sequestration.
2014-10-31 | 2013 |  |  |  |  | 78210 | USAMRIID Replacement, Incr 7 |  |  |  | W912DR-09-C-0026 | 0 | 0 | [7 empty] | Utilities, DDC, amd related costs associated with Contract # 5 for primary facility. UPDATE JUN 13: PA decremented due to sequestration.
2014-10-31 | 2014 |  |  |  |  | 78211 | USAMRIID Replacement, Incr 8 | 2015-01-22 | 2015-05-29 | Cont # 6 (North Parking) (TBD) |  |  | 0 | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | CENAB in-house resources completing design. RTA date for North Parking adjusted to 16 Jan 15 and schedule readjusted to reflect delay to leave government trailer complex on site for replacement contract. Contract solicitation will include NIBC Fence - Ph II (FY 11 DODM).
2014-10-31 | [6 empty] | USAMRIID Replacement, Incr 8 | 2017-04-01 | 2017-08-01 | Cont # 8 (South Parking/Demolition) (TBD) |  |  | 0 | 2019-08-22 | 2020-10-21 | 2020-08-22 | 2020-10-31 | 0% |  |  | Notional schedule shown; dependent on CDC/DA Safety certification of USAMRIID primary facility and vacation/decommissioniung of existing buildings 1408/1412/1414/1415. Due to delay in main contract, projections for award are moved out 2 years.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72481 | Fort Bliss Hospital Repl, Incr 1 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV |  | 7782 | 11366 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 19% |  |  | •Construction Progress: Sch. 26% Act. 22% : Based on Accepted Recovery Schedule the Contractor is working to the late finish parameters. •Structural steel and concrete decking activities continue at the Hospital on 1st, 2nd and 3rd floors and are currently the main critical path items. •Roof Decking on the Cup continues with slab on grade & CMU wall construction. •Drill piers for canopies and other ancillary structures continue. •Roof for thermal storage water tank continues. •Clinics: tie/grade beams being constructed •Rotunda: tie/grade beams being constructed . Next IPR /Principles Quarterly Meeting has been scheduled for 4 Dec 2014 in conjunction with the topping off ceremony. Contractor must pospone topping off ceremony.
2014-10-31 | [7 empty] | 2011-04-11 | 2011-07-27 | Sundt Construction, Inc. - Infrastructure |  | 39345 | 47508 | 2011-11-02 | 2013-10-12 | 2013-08-13 | 2013-08-29 | 99% |  |  | Construction 100% Complete
2014-10-31 | [7 empty] | 2011-03-25 | 2011-06-17 | Janco - Water Tower |  | 10488 | 10635 | 2011-08-23 | 2012-12-31 | 2012-07-05 | 2012-08-20 | 99% |  |  | Construction 100% Complete
2014-10-31 | [7 empty] | 2012-03-16 | 2012-07-19 | VEMAC - Parking Pkg A |  | 3848 | 3879 | 2012-08-28 | 2013-10-17 | 2013-06-19 | 2013-06-11 | 99% |  |  | Construction 100% Complete
2014-10-31 | [7 empty] | 2013-02-19 | 2014-07-25 | El Paso Water Utility |  | 3960 | 2800 | 2014-07-30 | 2015-07-15 | 2014-09-28 | 2015-08-06 | 0% |  |  | A pre-construction meeting was held on October 2nd at EPWU. The NTP is still pending due to a minor insurance requirement but is expected to be issued this week, most likely October 9th. The contractor is planning on mobilizing on the 13th. EPWU will also be providing a copy of the preliminary construction schedule once they receive it. Contract time is scheduled to commence October 10th. Final Completion has been revised to August 6, 2015.
2014-10-31 | [7 empty] | 2012-02-08 | 2012-09-04 | El Paso Electrical Substation |  | 4047 | 4047 | 2012-09-04 | 2015-09-16 | 2014-01-04 | 2014-01-04 | 99% |  |  | All work was completed on 6 Jan 2014. The utility company final invoice was processed on 5 May 2014.
2014-10-31 | [9 empty] | Temp Electric Contract |  | 46 | 46 |  |  |  |  | 100% |  |  | Temp power costs.
2014-10-31 | 2011 |  |  |  |  | 77251 | Fort Bliss Hospital Repl, Incr 2 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV |  | 68076 | 68076 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 19%
2014-10-31 | 2012 |  |  |  |  | 72786 | Fort Bliss Hospital Repl, Incr 3 | 2012-08-07 | 2013-01-29 | Hospital Const. Contract Award, CM JV |  | 69851 | 72931 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 19%
2014-10-31 | 2013 |  |  |  |  | 76558 | Fort Bliss Hospital Repl, Incr 4 | 2012-08-07 | 2013-01-29 | Hospital Contract |  | 79914 | 160491 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 19%
2014-10-31 | [7 empty] | 2013-08-08 | 2013-09-13 | Helipad |  | 1540 | 657 | 2013-10-21 | 2014-11-24 | 2014-10-24 | 2014-10-24 | 75% |  |  | Helipad Construction Progress: Sch. 75% Act. 75%: •Asphalt for the outer helipad buffer zone was completed on 11 Sep 14. •The Contractor is Working on the lighting installation. •USACE has provided a copy of the Helipad package to El Paso International for review. El Paso International completed their review on 24 Sep 14 with no exceptions found except that furhter coordination would be required for the operational flight patterns. A pre-final inspection has been scheduled for 24 Oct 14.
2014-10-31 | [8 empty] | 2014-07-25 | El Paso Water Utility Pmt 2 / Sewer Contract |  | 479 | 479 | [7 empty] | The contract that was awarded on 25 July 2014 to CMD Endeavors for $3.4M was disqualified by EPWU based on document verification. The contract was subsequently awarded to Danny Sander Construction in the amount of $4,048,948. The contract completion date remains 10 Aug 2015. PM will be submitting a funds request in order to process a mod to contracting for the delta in the funding provided to EPWU. The delta is $769,528 . This action drove up the HQCWE Number.
2014-10-31 | [7 empty] | TBD (NOTES) | 2015-02-15 | Parking Pkg B |  | 5562 | [5 empty] | 0% |  |  | Parking Package “B”:(small business- LPTA) Est. Award: $5.5M •Solicitation Package is complete. •Proposed Award Date: 15 Feb 15
2014-10-31 | 2014 |  |  |  |  | 77293 | Fort Bliss Hospital Repl, Incr 5 | 2012-08-07 | 2013-01-29 | Hospital Contract |  | 198148 | 77700 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 19%
2014-10-31 | [7 empty] | 2014-10-20 | 2014-12-10 | ACPs |  | 24755 |  | 2014-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 0% |  |  | ACP Package: (small business-Best Value) Est. Award: $24.7M •Solicitation package is complete. •Proposed Award Date: 10 Dec 14
2014-10-31 | [8 empty] | 2015-03-30 | CAT E Equipment |  | 33125 | [5 empty] | 0% |  |  | No update this reporting period.
2014-10-31 | 2015 |  |  |  |  | 81047 | Fort Bliss Hospital Repl, Incr 6 | 2012-08-07 | 2013-01-29 | Hospital Contract |  | 225199 | 0 | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 19%
2014-10-31 | [7 empty] | 2015-03-30 | 2016-03-28 | Landscaping |  | 22616 |  | 2015-07-30 | 2016-07-30 | 2016-07-30 | 2016-07-30 | 0% |  |  | Landscaping Package: (small business-LPTA) Est. Award: $22.7M •Solicitation package is complete. •Proposed Award Date: 28 Mar 16 with a potential early award in May of 2016.
2014-10-31 | 2016 |  |  |  |  | 81408 | Fort Bliss Hospital Repl, Incr 7 | 2012-08-07 | 2013-01-29 | Hospital Contract |  | 56858 |  | 2013-05-29 | 2017-04-03 | 2016-11-26 | 2016-11-28 | 19%
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72754 | Ambulatory Care Center Phase 3, Inc 1 | 2012-05-09 | 2012-09-21 | Skanska USA Building Inc |  | 76038 | 75519 | 2012-11-01 | 2015-06-30 | 2014-07-29 | 2015-04-17 | 81% |  |  | Construction Progress: Sch. 81% Act. 81%. Above Threshold Reprogramming (ATR) action for phase 3 was approved and funds are at USACE HQ. Headquarters has released $10M to SWF to replenish CAT-E and fund current Mods. Negotiated mods have been within estimates...expect to finish project within the funds provided.
2014-10-31 | 2013 |  |  |  |  | 80793 | Ambulatory Care Center Phase 3, Inc 2 | 2012-05-09 | 2013-06-03 | Skanska USA Building Inc |  | 16319 | 21250
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction |  | GERMANY | 76007 | Medical Center Replacement, Incr 1 |  | 2012-03-15 | Environmental Compensation |  | 15042 | 1731 | 2014-01-13 |  | 2021-07-20 |  | 5% |  |  | German government solicitation and award dates to German industry are estimated. [Constr Oblig to FRG 3/15/2012]
2014-10-31 | 2012 | [7 empty] | 2012-03-15 | Lot 1 Temporary Construction Fence |  | 260 | 260 | 2014-01-20 |  | 2014-04-04 | 2014-04-04 | 100% |  |  | Construction completed April 2014 [Constr Oblig to FRG 3/15/2012]
2014-10-31 | 2012 | [7 empty] | 2012-03-15 | Lot 2.1 Demolition, Site Clearing |  | 1099 | 1099 | 2014-06-16 | 2014-08-29 | 2014-10-29 | 2014-12-12 | 60% |  |  | Contractor mobilized 16 June 2014. Fourteen bunkers have been uncovered and are being removed. Removal of the material is slower htan expected as the construction gate along L369 is not yet operational. [Constr Oblig to FRG 3/15/2012]
2014-10-31 | 2012 | [7 empty] | 2012-03-15 | Lot 2.2 Mass Grading |  | 20158 |  | 2014-11-15 | 2015-11-17 | 2015-11-17 |  | 0% |  |  | 100% P&S received 28 July 14 and approved 7 Aug 14. Estimated German government solicitation and award dates to German industry are are as follows: Construction award: Sep 2014; Construction start in Oct 2014. [Constr Oblig to FRG 3/15/2012]
2014-10-31 | 2012 | [7 empty] | 2012-03-15 | Transformers/Substation |  | 19557 |  | 2015-01-21 | 2016-11-10 | 2016-12-10 |  | 0% |  |  | FRG to solicit in est. 2QFY15. German government solicitation and award dates to German industry are estimated. [Constr Oblig to FRG 3/15/2012]
2014-10-31 | 2012 |  |  |  |  | 76007 |  |  | 2012-03-15 | Lot 3.9 Site Security |  | 6215 | 6215 | 2015-01-01 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 0% |  |  | Contract for overall site security. Contract will run through the end of construction. [Constr Oblig to FRG 3/15/2012]
2014-10-31 | 2013 |  |  |  |  | 72661 | Medical Center Replacement, Incr 2 |  | 8/27/2013 | Lot 3.1 Construction Preparatory Measures |  | 26097 |  | 2015-02-01 | 2015-12-30 | 2015-10-20 | 2015-12-30 | 0% |  |  | ABG3 mod accepting final design and requesting tender action sent on 23 Sep 2014; package awaiting solicitation pending resolve of water/supply/ redundancy/ hygiene discussions. Anticipated to be released for solicitation late Nov 2014. [Constr Oblig to FRG 8/27/2013]
2014-10-31 | 2013 | [7 empty] | 8/27/2013 | Lot 4 Access Control Point, Bridge, External Roadways |  | 54539 |  | 2015-09-21 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Currently at 35% design. German government solicitation and award dates to German industry are estimated. [Constr Oblig to FRG 8/27/2013]
2014-10-31 | 2014 |  |  |  |  | 72662 | Medical Center Replacement, Incr 3 |  | 2015-03-01 | Lot 5.1 Parking Structures, Campus Roadways |  | 59043 |  | 2016-06-17 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Included in MedCen 20% design. EUD provided letter authorizing the design kickoff, currently targeted for Nov 2014. German government solicitation and award dates to German industry are estimated. [Constr Obligation to FRG est. Mar 2015]
2014-10-31 | 2015 |  |  |  |  | 76872 | Medical Center Replacement, Incr 4/5 |  | 2016-03-01 | Medical Center (Bed Tower, D&T, Clinics, Admin) |  | 635222 |  | 2019-02-12 | 2022-11-08 | 2021-12-08 |  | 0% |  |  | US led 20% MedCen final design submitted 2 Aug 2013. USACE is transitioning design to German government. German govt AE target selection date is est. Dec 2014 for follow-on 20-100% design. German government solicitation and award dates to German industry are estimated. Note must be updated. Admin now apart of Med Ctr. [Constr Oblig Est. Mar 16]
2014-10-31 | 2017 |  |  |  |  | 81410 | Medical Center Replacement, Incr 6 |  | 2017-03-01 | Lot 5.2 Central Utility Plants, Helipads |  | 55874 |  | 2017-03-06 | 2021-11-17 | 2021-12-17 |  | 0% |  |  | Pending funding profile determinations, currently estimated for construction obligation in FY15. German government solicitation and award dates to German industry are TBD. [Constr Oblig Est. Mar 17]
2014-10-31 | 2017 |  |  |  |  | 81412 | Medical Center Replacement, Incr 6 |  |  | CAT E/F Equipment |  | 29261
2014-10-31 | 2007 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 52330 | Clinic Replacement, Inc 1 | 2007-02-16 | 2007-07-19 | Caddell Construction Co, Inc |  | 40902 | 45600 | 2007-09-04 | 2009-09-11 | 2009-12-17 | 2011-06-05 | 100% |  |  | BOD for Phase 1 (the Addition) was 8 Jun 09. BOD for PH 2 (Alteration) was 27 Mar 10. PH 3 (Alteration) is on-going, mod for replacing AHU-7 was negotiated and will extended completion date to 16 Sep 10. Proposal from MATOC contractor to perform BASH, standpipes, extra sidewalks pending.
2014-10-31 | 2008 |  |  |  |  | 67647 | Clinic Replacement, Inc 2 |  |  | Caddell Construction Co, Inc |  | 32890 | 42183 | [7 empty] | Clinic turned over to Cust 11 Sep 2009. Since, AFCEE requested add fire sprinkler hose standpipes and more exterior sidewalks per fire marshall's interpretaion of fire code, AF has requested different flooring in places, AF requested retention pond revisions for BASH. Design A-E providing designs and cost estimates. Est CWE $43.129K. Will update as estimates arrive.
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65028 | Federal Healthcare Facility | 2007-10-01 | 2008-02-27 | Flannery Fire Protection | N40083 08 C 0069 | 6782 | 7382 | 2008-04-01 | 2009-09-02 | 2009-09-02 | 2009-09-02 | 100% |  |  | Project is financially closed.
2014-10-31 | [7 empty] | 2008-02-22 | 2008-06-17 | Walsh Construction Company of Illinois | N40083 08 C 0059 | 71567 | 75921 | 2008-08-01 | 2010-10-01 | 2010-08-27 | 2010-09-27
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71857 | Hospital Addition | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 31112 | 32791 | 2010-12-03 | 2013-07-15 | 2013-01-12 | 2013-07-15 | 100% | 3486 |  | Funds used for FY00 Settlement, Ft. Wainwright. Residual activity on project funding items.
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 53577 | Environ. Prev. Med Unit 2 Replacement | 2008-10-31 | 2009-03-31 | Virtexo Corporation | N40085 09 D 5033 DO 0002 | 5951 | 6558 | 2009-05-01 | 2010-10-15 | 2010-05-04 | 2010-09-08 | 100% |  |  | Project is financially closed.
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 64809 | Pharacare Addition/Alteration | 2007-09-27 | 2008-02-29 | J2 Engineering, Inc |  | 3381 | 3489 | 2008-03-24 | 2009-03-24 | 2009-03-24 | 2009-03-24 | 100%
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70235 | Hospital Replacement (w/FY09 BRAC PN 65081) | 2009-04-08 | 2009-09-28 | Turner Construction Company |  | 230018 | 274362.982 | 2009-10-22 | 2014-05-19 | 2013-02-03 | 2014-05-19 | 99% |  |  | Contract awarded on 28 Sep 09. Received GAO protests from the two non-selecteed firms on 5 Nov 09. Contractor Terminated for Convenience on 24 Mar 10. Amended solicitation for remaining offerors on 5 May 10. Contract with Turner reinstated 5 Aug 10. Contractor on schedule; inspections and punch-outs continue. Contingencies at District: $1,585,759. Ribbon cutting held 7 Nov 2014.
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | KANSAS | UNITED STATES | 47298 | Hospital Replacement | 2009-02-06 | 2009-09-30 | Balfour Beatty / Walton JV | W912DQ-09-C-4024 | 324110 | 282778 | 2010-05-03 | 2015-07-01 | 2013-07-23 | 2015-01-30 | 97% |  |  | 10/23/2014 Fort Riley Replacement Hospital. a. Current CCD: 13 May 2014 b. Placement: 97% actual vs. 100% scheduled (as of August's pay estimate). c. Construction in progress: Logic changes to multiple air handlers work has been completed and TAB/commissioning has restarted (with some adjustments still being made to the logic); site work in the healing garden area has been started with initial concrete placements made to receive flagstone; completing the healing garden site work first pushes the testing of the atrium curtain walls to about 10 Dec; expansion joint continues on both sides of the building but is now expected to extend into Oct due to their sub not having some transition joints which will require modification and/or refabrication; roofing subcontractor has completed replacing wet materials on the high roof; Pre-final Inspections have been suspended since 29 Sep (meeting with BWJV this week to discuss the way forward). d. Contractor's Schedule: Schedule not accepted as of November 2012 update. Schedule updates are being analyzed by NIBS and rejected. e. Estimated Completion: USACE estimated completion is 30 Jan 2015, but the Contractor will not finish by this date if he is unable to mobilize more resources to complete work. There will likely be a need to have some overlap of the Hospital IO&T and IMF contractors and final Integrated Systems Commissioning and Final Inspections. The contractor exceeded the required completion date of 13 May 2014. Liquidated damages are being withheld at $16,500 per calendar day. Corporate/senior manager engagement continues. IBA back on site testing windows, but several areas have not been repaired to allow retesting of the windows that previously failed, nor are they prepared to do the outside chamber test to verify head conditions (scheduled to come back in 2 weeks). Next HFPA update and Council of Colonels meeting is scheduled for 18 Nov 2014.
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 63864 | Health Clinic Add/Alt | 2008-05-15 | 2008-08-04 | Bette & Cring, LLC |  | 27483 | 35963 | 2008-11-07 | 2012-12-01 | 2011-02-18 | 2013-12-12 | 99% |  |  | closeout documents being processed
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 17153 | Health Clinic Replacement | 2008-02-15 | 2008-05-08 | Guyco, Inc. |  | 5214 | 5430 | 2008-05-08 | 2009-11-18 | 2009-11-16 | 2010-03-17 | 100% |  |  | BOD was 2 Aug 10. Ribboncutting held 28 Sep 10.
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69626 | Burn Rehabilitation Center | 2007-12-21 | 2008-07-31 | Clark/Hunt, A Joint Venture |  | 18512 | 19120 | 2008-08-21 | 2011-08-15 | 2011-07-15 | 2013-05-01 | 100% |  |  | Part of SAMMC-N (Part of 4TH Floor in Tower): BRU is turned over and in use, contract closeout ongoing. Project will show 100% when final payments are made. SWF provide new closeout date!!!!
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 64473 | Medical/Dental Clinic | 2008-07-29 | 2008-09-18 | The Korte Company |  | 17497 | 18181 | 2008-09-30 | 2010-03-17 | 2010-02-20 | 2010-03-17 | 100% | 1885 |  | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2014-10-31 | 2008 | Defense Health Agency | Major Military Construction |  | GERMANY | 52332 | Medical Clinic Replacement | 2008-05-05 | 2008-08-29 | Federal Republic of Germany |  | 25929 | 26866 | 2008-08-29 | 2011-10-08 | 2012-05-15 | 2012-07-13 | 100% |  |  | Project is 100% complete with ABG7 signed 13 Jul '12. Ribbon cutting event 07 Sep '12. The contractor is in the process of filing a claim through the host nation for an amount in excess of 3.5M Euro. This issue will take several years to resolve through the German court system. Final close out cannot be completed until then. NAU will provide details on the claim.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 71653 | Hospital Replacement (ARRA) | 2010-06-11 | 2010-09-01 | Clark/McCarthy, JV | N62473 10 C 0001 | 418039 | 425895 | 2010-12-03 | 2013-10-17 | 2014-01-07 | 2014-01-07 | 100% |  |  | Multiple residual closeout issues.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 971B | Hospital Alteration (ARRA) | 2009-09-09 | 2009-12-18 | Brasfield & Gorrie, LLC | N69450 10 C 1258 | 8000 | 13282 | 2010-01-20 | 2011-12-11 | 2011-12-11 | 2011-12-11 | 100% |  |  | Project is financially closed.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 75585 | Vision Center of Excellence | 2010-02-17 | 2010-06-25 | Clark / Balfour Beatty, JV | N40080 10 C 1506 | 3900 | 3900 | 2011-03-01 | 2011-07-21 | 2011-07-31 | 2011-07-31 | 100% |  |  | Project is financially closed.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 73599 | Hospital Renovation & MRI Addition (Cong Add) | 2010-06-30 | 2010-09-27 | W.M. Jordan Company, Inc | N40085 10 C 5305 | 26178 | 28244 | 2010-12-03 | 2014-04-01 | 2015-01-02 | 2015-03-04 | 85% |  |  | Active Project.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | GUAM GU | GUAM | 55918 | Central Utility Plant | 2009-03-15 | 2009-09-15 | PDI - HSW JV | N62742 09 C 1308 | 13034 | 13672 | 2009-10-01 | 2011-06-22 | 2011-02-07 | 2011-06-22 | 100% |  |  | Residual closeout issues.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 70350 | Hospital Alteration (ARRA) | 2011-07-26 | 2011-09-15 | Federal Contracting DBA Bryan Construction |  | 15929 | 20393 | 2011-11-08 | 2014-03-23 | 2013-11-27 | 2014-01-21 | 99% |  |  | Awaiting completion of as-builts. Additional funds returned.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 70354 | Hospital Replacement (Supplemental) | 2011-12-19 | 2012-05-09 | Turner Construction Company |  | 159834 | 163146 | 2012-05-30 | 2017-07-25 | 2015-03-16 | 2016-11-15 | 17% |  |  | A Partial suspension of work associated with the water tank has been instituted for a period of 120 days which will most likely be expanded as an engineering solution is generated. The Designer of Record is urgently working on an engineering solution to be presented to CDPH. The USACE Medical Center of Expertise (MCX) has approved the change but will evaluate the final design. Final cvosts and Time impacts are dependent upon the final appproved design. All other activities not encumbered by ECBs continue. DHA provided $15M of the $56M required. All changes are mandatory engineering changes. The team continues to work towards resolution of engineering changes while remaining cognizant of schedule impacts. Steps to mitigate schedule and cost impacts are being evaluated as part of an ongoing process to identify and reduce risk in the change management process. All unencumbered work activities are proceeding.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 64709 | Satellite Pharmacy | 2009-03-04 | 2009-05-21 | Liberty-Mass II |  | 1963 | 2014 | 2009-07-01 | 2010-09-03 | 2010-09-09 | 2010-09-09 | 100% |  |  | Project closed. All remaining distgrict funds were returned on 1 Apr 11. DD1354 requested. Looking into the best source for DHA to acquire final DD1354's.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 79845 | Eglin Hospital Alteration (ARRA) | 2011-07-01 | 2011-09-23 | JE Dunn Construction |  | 51133 | 59375 | 2011-10-31 | 2015-03-12 | 2014-11-06 | 2016-01-26 | 93% |  |  | Current total obligations shown in column P are for ARRA MILCON only. Current completion percentage is 93%. Obligated ARRA MILCON amount $63,928,736.13/Disbursed Amount $60,120,086.24. Required completion date 8-Dec-14/Scheduled completion 26-Jan-15. Schedule analysis shows contractor is 48 days behind schedule. Contract including all currently identified modifications is at 99.58% of PA. Unknown extent of mold, rust and unforseen site conditions of areas to be renovated present a moderate to high risk that mandatory modifications will exceed PA. CT/PET initial proposal excessive. CT/PET RFP reissued and and received 17-Sep-14. Parts of scope still under discussion with AF medical comands. This date may be extended, area under partial suspension of work due to CT/PET equipment hold by AF. Surgery Suite Phase 3, Lab phase 1, B2794 Command Office, ENT, Plastics and new coffee shop under construction. Contractor has submitted requests for equitable adjustment. Currently there are no outstanding funds requests. $560K REA is being discussed. Lessons Learned is being developed.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 65080 | Consolidated Troop Medical Clinic | 2008-11-12 | 2009-02-25 | Mathis and Sons, Inc |  | 2983 | 3084 | 2009-03-16 | 2010-05-07 | 2010-03-16 | 2010-05-07 | 100% |  |  | Construction complete. Project financially complete.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 64573 | Medical / Dental Clinic | 2008-12-10 | 2009-05-26 | The Korte Company |  | 14342 | 14700 | 2009-05-22 | 2011-03-30 | 2011-05-15 | 2011-03-30 | 100% | 5367 |  | NTP was 11 Jun 09 // BOD is 01 Jun 2011; FAD 10-0012-04323 28 Jan 10 increased construction funds by $454,808 (from $17,178,439 to $17,633,247). Returned $500,000. Fiscal Closeout 31 Oct 13. $1.5M diverted to Wright Patterson Hospital Renovation PN72722 on August 26, 2013 by DHA.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 59987 | Primary Care Clinic Add/Alt |  | 2009-07-15 | MAXFour Weitz JV |  | 13627 | 14503 | 2009-08-24 | 2011-07-28 | 2011-05-30 | 2011-07-28 | 100% | 1500 |  | Project closed.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 59220 | Hospital Add/Alt (Supplemental) | 2011-06-10 | 2011-09-28 | Travelers/Gilbane Bldg. Co. | W912DS-11-C-0016 | 28500 | 29108 | 2011-10-26 | 2015-06-01 | 2014-03-03 | 2015-05-26 | 66% |  |  | Project substantial completion was extended out to 31 Mar 2015 by the TOA. Takeover Contractor working on improving delivery date for curtain wall glass with subcontractor. Electrical sub contractor continues work on permanent power installation. Electrical tie in work completed on 10/3/14 and 10/6/14. Air Vapor Barrier installation is ongoing. Drywall installation started on 2nd floor. History: T4D 10 Jan 2014. Surety NTP 15 Aug 2014.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 72722 | Hospital Renovation (Supplemental) | 2011-06-16 | 2011-09-29 | Walsh Butt Joint Venture |  | 76944 | 85004 | 2011-10-25 | 2015-03-18 | 2014-09-09 | 2015-03-18 | 90% |  |  | Large dollar changes prompted a funding request for an additional $4.88M. $4M delivered on 18 Jun 14 and Logistics/Facilities back in contract. All user requested changes to be approved by DHA. Mandatory mods being approved by DHA was causing delays. Kitchen and the impact to putting Logistics/Facilities back in have been negotiated. The new contract completion date is 18 March 2015. BOD will also be 18 March 2015. 31 of 34 departments will be in full use and possession by Air Force on 10 Dec 14. Projections are the project will finish well within the $4.88M funds.
2014-10-31 | [6 empty] | Tree Cutting | 2011-03-07 | 2011-03-20 | A1 Tree Service |  | 9.6 | 9.6 | 2011-03-20 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 100% |  |  | Tree Cutting contract awarded for risk mitigation: avoidance of Indiana Bat - cutting ban (Apr - Oct). This facilitated getting the Swing Space and Contractor lay down area cleared without potential delays of environmental (endangered species) mitigation.
2014-10-31 | [6 empty] | Swing Space | 2011-04-11 | 2011-06-17 | Custom Mechanical Systems Corp |  | 5578.1 | 5578 | 2011-07-01 | 2011-12-05 | 2014-09-27 | 2014-09-27 | 98% |  |  | Swing Space awarded for risk mitigation: avoidance of delays in removation execution due to construction of transition space for phasing. Swing Space is BOD and contract is now in lease period.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 62189 | Medical / Dental Clinic Replacement | 2008-10-27 | 2009-04-03 | Hensel Phelps |  | 47615 | 51375 | 2009-06-01 | 2012-06-04 | 2011-10-26 | 2012-02-09 | 98% |  |  | Medical/Dental Clinic: 98% complete, BOD for new clinic met Monday the 4th of Jun with BOD for entire project of 11 Nov 12. Demolition of existing Clinic scheduled to begin 20 Aug 2012. Ribbon-cutting took place 29 June 2012.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 74650 | Hospital Replacement, Phase 1 & 2 (100% ARRA) | 2010-02-16 | 2010-09-10 | Balfour Beatty-McCarthy |  | 529989 | 554921 | 2010-11-08 | 2015-03-01 | 2014-05-31 | 2014-12-21 | 85% |  |  | CUP: Generator, boiler, and fuel system testing ongoing. Clinics: West- Furniture move-in completed; equipment installing beginning; North- Furniture move-in expected to begin by mid October. South- interior work continues at various stages. Hospital- interior work at various stages continue; MEP in IBS areas; HVAC undergoing pre-functional testing; preparing to install MRI; elevator install continues. Garages- electrical rough-in, structural steel for elevators, and stair erection continue. Progressive Collapse Claim has been negotiated and awarded as of 18 Apr 14. New CCD is 10 Oct 14; however, the contractor is not expected to be complete until 4 Nov 14. The BOD has been moved due to production and schedule management issues by the general contractor. This will allow the contractor to finalize commissioning and any remaining punch list items while transitioning activities are ongoing by the hospital staff.
2014-10-31 | [5 empty] | 74728 | Hospital Replacement, Electrical Funding (100% ARRA) | 2010-05-21 | 2010-06-11 | RMA Land Construction, Inc., Infrastructure, Electrical Distribution & Telecomm |  | 9698 | 10156 | 2010-07-20 | 2012-09-20 | 2012-07-26 | 2012-09-20 | 100% |  |  | Construction 100% Complete
2014-10-31 | [5 empty] | 74650 | Sanitary Sewer | 2010-01-07 | 2010-04-15 | American Water Ops & Mtc, Sanitary Sewer |  | 10225 | 11445 | 2010-06-15 | 2012-06-02 | 2012-02-25 | 2012-05-02 | 100% |  |  | Construction 100% Complete
2014-10-31 | [6 empty] | Relocation of Gas & Electric Utilities | 2010-02-12 | 2010-03-08 | TTG Utilities, LP, Relocation of Gas & Electric Utilities |  | 301 | 301 | 2010-04-05 | 2010-06-30 | 2010-05-30 | 2010-06-07 | 100% |  |  | Construction 100% Complete
2014-10-31 | [6 empty] | Demolition of Hood Stadium | 2010-03-26 | 2010-06-02 | Charter Environmental, Inc., Demolition of Hood Stadium |  | 1040 | 1040 | 2010-06-18 | 2010-10-05 | 2010-10-18 | 2010-10-04 | 100% |  |  | Construction 100% Complete
2014-10-31 | [6 empty] | New Stadium | 2010-02-16 | 2010-07-28 | RMA Land Construction, Inc. New Stadium |  | 17290 | 15383 | 2011-01-06 | 2013-12-15 | 2012-06-29 | 2013-12-15 | 99% |  |  | Contractor working on additional punchlist items and close out documentation.
2014-10-31 | 2009 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 53341 | Medical Instruction Facility | 2008-11-13 | 2009-02-20 | Innovative Technology Solutions, Inc |  | 10432 | 15334 | 2010-01-27 | 2012-08-14 | 2010-06-02 | 2010-11-12 | 100% | -1539 |  | Revoke $1,538,899.27 of FY09 DODM Const Funds from HQ USACE (see Line 3 attached MS Excel Summary) from FY09, PN53341, Medical Instruction Facility, Fort Sam Houston, TX. This project is 'Fiscally Complete' and these funds are no longer required at HQ USACE.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 71550 | Medical/Dental Clinic Replacement | 2010-06-16 | 2010-12-14 | Vinci Construction UK |  | 13098 | 12421 | 2010-12-14 | 2013-10-12 | 2012-08-10 | 2012-08-10 | 100% |  |  | Estimated financial closure: 31 Dec 2014
2014-10-31 | [6 empty] | Medical/Dental Clinic Replacement - Sidewalk | 2013-04-05 | 2013-06-15 | VolterFitzpatrick |  | 68 | 68 | 2013-07-01 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 100%
2014-10-31 | [6 empty] | Medical/Dental Clinic Replacement - Entrance Door Amendments | 2014-08-20 | 2014-08-25 | Vinci Facilities |  | 69 | 69 | 2014-11-27 | [6 empty] | DIO cannot close main project until this local order is complete.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | ALASKA | UNITED STATES | 71310 | Aeromedical Services/Mental Health Clinic | 2009-09-18 | 2010-02-25 | Davis Constructors & Engineers, Inc. |  | 19839 | 20258 | 2010-03-11 | 2011-11-29 | 2011-10-15 | 2011-11-29 | 100% | -577 |  | Project closeout occurred 18 June 2012.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | ALASKA | UNITED STATES | 69805 | Health Clinic Add/Alt | 2009-11-30 | 2010-02-10 | Bristol Design Build Services LLC |  | 3087 | 3140 | 2010-02-22 | 2011-03-18 | 2011-05-23 | 2011-03-18 | 100% |  |  | Project closeout occurred 19 Apr 2012.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 69295 | Health and Dental Clinics | 2010-04-26 | 2010-09-23 | Korte Construction Company |  | 17616 | 18171 | 2010-10-20 | 2012-02-27 | 2012-02-13 | 2012-02-27 | 100% |  |  | Project closed.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 64481 | Blood Donor Center Replacement | 2009-11-05 | 2010-09-24 | IAP-Leopardo |  | 7792 | 7904 | 2010-11-12 | 2012-08-05 | 2012-05-05 | 2012-05-05 | 100% | -3185 |  | Project is Financially Complete. DHA provided $800K of reprogrammed FY10 MILCON funds from the Blood Donor Center, Ft. Benning project to the FY07 SSP project via 0$FAD on 3/4/14. Contingencies at District: $0
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 71620 | Dental Clinic | 2009-12-23 | 2010-03-31 | EJS Contracting, Inc. |  | 2549 | 2619 | 2010-04-28 | 2011-03-11 | 2011-04-28 | 2011-03-11 | 100% | -168 |  | NTP issued on 28 April 2010. FAD 11-0012-01830, 16 Nov 10, $54,040, additional construction funds. Project Financially complete.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70481 | Health and Dental Clinics | 2009-11-25 | 2010-09-30 | Brafield & Gorrie, LLC |  | 9742 | 10101 | 2010-10-21 | 2012-06-04 | 2012-03-22 | 2012-03-22 | 100% | -818 |  | D/B contract awarded 30 Sep 10. Bid savings withdrawn by DHA. Construction Complete. Contingencies at District: $0
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70557 | Health Clinic Addition/Alteration | 2010-04-12 | 2010-09-27 | Charpie-Korte Joint Venture |  | 4018 | 4034 | 2010-09-30 | 2011-06-30 | 2012-02-05 | 2011-06-30 | 100% | -2278 |  | Project was Closed Out at LRL - 20 Mar 12 (A) . Any remaining funds may be returned. DHA moved $785K of FY10 bid savings from the Health Clinic, Ft. Campbell project to Boundary Gate, Nalin Pond, project at Ft. Detrick, MD on 3/4/14.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61401 | Boundary Gate at Nallin Pond | 2010-08-24 | 2010-12-17 | John C. Grimberg Co. Inc. | W912DR-11-C-0008 | 9075 | 10119 | 2011-01-12 | 2014-12-05 | 2013-01-10 | 2014-11-14 | 90% | 785 |  | % Complete (Scheduled/Actual): 93/91 Intersection work underway . BOD is 5 Dec 14. All pending modifications/REAs are settled. Remaining contg is $33k. Project is current within Congressional authority (NTE $12.692M).
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 61536 | Emergency Service Center | 2010-02-23 | 2010-06-24 | John C. Grimberg Co. Inc. | W912DR-10-C-0087 | 13478 | 13858 | 2010-07-19 | 2013-05-23 | 2012-09-16 | 2013-05-23 | 100% |  |  | BOD achieved 23 May 13. Final punchlist item complete. Reviewing payroll documentation prior to processing final pay. No additional contingency required. Expected to closeout March 2015..
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67948 | NIBC Truck Inspection Station & Road | 2010-09-02 | 2010-10-29 | CFM Engineering | W912DR-11-C-0002 | 2880 | 3132 | 2010-12-15 | 2012-07-05 | 2011-12-15 | 2012-07-05 | 99% |  |  | PDT is currently planning for project fiscal closeout (19 Dec 14) to include dates for all remaining activities.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 64153 | Dental Clinic Addition/Alteration | 2009-10-20 | 2010-07-02 | TMG Services |  | 3890 | 4319 | 2010-07-22 | 2012-03-19 | 2012-01-13 | 2012-03-15 | 100% | -712 |  | Project closed. DD1354 requested. Looking into best source for DHA to acquire transfer document.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64244 | Consolidated Health Clinic | 2009-10-28 | 2010-09-30 | Korte Construction Company |  | 15313 | 16186 | 2010-10-21 | 2012-10-26 | 2012-05-18 | 2012-10-26 | 100% | -6655 |  | D/B contract awarded 30 Sep 10. Construction complete. Contingencies at District: $133,264.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69353 | Behavioral Health Clinic (NDAA 2011 change to BHC) | 2009-12-23 | 2011-04-20 | Hensel-Phelps Const. Co. |  | 14725 | 15287 | 2011-05-13 | 2012-11-15 | 2012-10-12 | 2012-11-15 | 100% | -458 |  | PBD from MCA. Awarded for Construction 20 Apr 2011. Construction complete. Contingencies at District: $0.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 69711 | Dental Clinic | 2009-11-03 | 2010-06-16 | The Korte Company |  | 8199 | 8199 | 2010-07-30 | 2012-03-04 | 2012-01-04 | 2012-01-04 | 100% | -1016 |  | Project Financially Closed 20-MAR-2013
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 69294 | Health and Dental Clinics | 2010-02-17 | 2010-11-17 | LEC-CMS, LP |  | 12743 | 13018 | 2011-02-07 | 2012-08-20 | 2012-05-22 | 2012-12-31 | 99% | -3280 |  | Further CCD Slip did not to affect BOD. User requested Changes being negotiated. BIM Model and final pay app expected Dec 2013. SWF to provide a new close out date shortly.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 71318 | Dental Clinic Replacement | 2009-10-28 | 2010-02-26 | J E Dunn Construction Company |  | 22680 | 23591 | 2010-04-06 | 2012-04-30 | 2012-01-06 | 2012-09-01 | 99% | -3144.239 |  | Contract Complete 1 Spet 12. Waiting on payroll issues to be resolved before we can close out financially. SWF to provide a New close out date shortly. Retainage being held.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 70343 | Health and Dental Clinic Additions | 2009-12-04 | 2010-03-24 | Vet Industrial of Bremerton, WA |  | 7219 | 7583 | 2010-04-19 | 2011-05-13 | 2011-05-07 | 2011-05-02 | 100% | -2109 |  | Project complete/closed. DD1354 requested. Looking into best source for DHA to acquire transfer documents.
2014-10-31 | 2010 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72430 | Ambulatory Care Center, Phase 1 B | 2010-06-11 | 2010-08-19 | J E Dunn Construction Company (Bldg 1 & CEP) |  | 41566 | 45105 | 2010-10-04 | 2013-11-19 | 2013-02-20 | 2013-08-30 | 99% |  |  | Building 1 is complete and turned over to the Air Force. BOD is 19 Nov 13. Interim DD 1354 has been signed by BCE 5 Dec 13. Closeout Correction and verification of punchlist deficiencies continues. Contractor working stone issue.
2014-10-31 | [6 empty] | Ambulatory Care Center, Phase 1 A | 2010-06-11 | 2010-08-31 | J E Dunn Construction Company (Parking Structure & Temp Parking) |  | 23216 | 24153 | 2010-10-04 | 2012-12-13 | 2012-02-26 | 2012-11-30 | 99% |  |  | Phase 1A consisting of a multi-story parking garage and a Central Energy Plant is complete and turned over to the Air Force. BOD 13 Dec 2012. Parking garage stone header failure repair under evaulation by SWF Structural Engineering. Awaiting installation of type A1 and A2 signage.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77116 | NNMC Parking Expansion | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 14030 | 14392 | 2012-06-18 | 2013-12-02 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77115 | Transient Wounded Warrior Lodging | 2011-05-03 | 2011-09-30 | DCK/TTEC, LLC | N62742 09 D 1172 DO JU01 | 48133 | 48829 | 2012-06-18 | 2014-05-27 | 2014-02-02 | 2014-07-18 | 100% |  |  | Single contract award for both Parking Expansion and Transient Wounded Warrior Lodging, so completion dates for parking garage are not reflective of actual completion.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 70482 | Health Clinic Addition/Alteration | 2010-11-19 | 2011-06-03 | McCarthy Building Companies |  | 23050 | 26519 | 2011-06-21 | 2013-11-29 | 2013-06-20 | 2014-05-06 | 100% |  |  | The contract completion date has passed. Commissioning underway. The IO&T contract has began and the building is currently under joint occupancy. Contingencies at District: $884,709. Will return funds ASAP. New close out date to be provided. Commissioning complete.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MASSACHUSETTS | UNITED STATES | 71634 | Mental Health Clinic Addition | 2011-11-04 | 2011-12-23 | Watermark Environmental, Inc. | W912WJ-12-C-0002 | 2790 | 2790 | 2012-05-18 | 2013-02-16 | 2013-01-16 | 2013-03-01 | 99% |  |  | Contract substantially complete 16 Feb, Customer move-in complete. AS-Built issues have been resolved and they are not complete. 1354 was submitted to the customer for signature. 1354 issues with the Customer have been resolved. An A-E contract needs to be modified to deobligate an unused task. 1354 will be signed once the AE contract is closed out and the costs for doing so are included on the 1354. Mod request is into NAE Contracting. Mod to be awarded in Oct.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 73360 | Consolidated Logistics Facility | 2011-02-18 | 2011-06-30 | Arrow Kinsley JV II | W912DR-11-C-0029 | 19869 | 19957 | 2011-07-21 | 2014-12-05 | 2014-01-06 | 2014-11-14 | 99% |  |  | % Complete (Scheduled/Actual): 99/99 1354 signed 7 Oct 14. Punchlist item completion by mid Nov 14. Furniture delivery and install for both CONLOG buildings is delayed pending receipt of MEDCOM funding; anticipating install Feb 2015.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 62886 | Information Services Facility Expansion | 2011-09-21 | 2012-01-27 | Tatitlek Construction Services, Inc. | W912DR-12-C-0004 | 4270 | 4626 | 2012-03-19 | 2015-02-10 | 2013-11-09 | 2014-12-12 | 75% | 232 |  | % Complete (Scheduled/Actual): 80/75. Building interior being painted. Furniture contract awarded for installation 20 Jan 15. NEC personnel will continue to function in existing, compressed space until new facility is available. Below Threshold Reprogramming (BTR) of $232K from Health and Dental Clinics, White Sands to Information Services Facility, Ft. Detrick, MD executed on May 6, 2014.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67949 | NIBC Security Fending and Equipment | 2011-08-19 | 2012-02-14 | Cont #1 (Segment 1) (Rich Moe Enterprises, LLC) | W912DR-12-C-0001 | 1701 | 1701 | 2012-04-02 | 2013-04-01 | 2013-04-02 | 2013-04-01 | 100% |  |  | Construction contract closeout underway.
2014-10-31 | [7 empty] | 2015-02-13 | 2015-05-29 | Cont #2 (Segment 2) (TBD) |  |  |  | 2015-06-27 | 2016-11-04 | 2016-09-05 | 2016-09-05 | 0% |  |  | 95% design under review. RTA date for Fence Segment 2 is 31 Jan 15. Contract solicitation will include USAMRIID Replacement North Parking which establishes overall site contours for fence construction. Combine with RID.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67953 | Supplemental Water Storage | 2011-02-18 | 2011-06-20 | FutureNet Group | W912DR-11-C-0028 | 3468 | 3944 | 2011-07-20 | 2015-01-15 | 2012-11-01 | 2014-05-30 | 93% | 263 |  | % Complete (Scheduled/Actual): 100/93 Contractor having difficulty completing pump facility. LD's being assessed. BOD now re-adjusted to 15 Jan 15 due to contractor performance and need to secure final MDE water system connection permit.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 67951 | Water Treatment Plant Repair | 2011-08-12 | 2012-12-17 | Grimberg / Amatea GC JV | W912DR-13-C-0007 | 14308 | 15378 | 2013-01-14 | 2015-04-30 | 2014-07-08 | 2014-11-17 | 83% | 5000 |  | % Complete (Scheduled/Actual): 92/83 BOD slipped due to city sewer connection and contractor performance. Potential ATR…details to follow.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 70472 | Health and Dental Clinic | 2010-11-02 | 2011-07-22 | Charpie-Korte Dsn-Bld JV S.B. L.L. |  | 14837 | 15067 | 2011-08-18 | 2013-04-26 | 2013-03-30 | 2013-08-02 | 99% | -1095 |  | Clinic Construction Virtually Complete. Landscaping Items are finishing up and Punch List remain to be completed. Final Payment scheduled for 13 Dec 2013, Project clousout scheduled for Feb 2014. DHA reprogrammed FY11 MILCON funds @ $600k from Health and Dental Clinic, White Sands to Fort Detrick Water Treatment Plant on 3/13/14.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 72752 | Ambulatory Care Center Phase 2 | 2011-05-20 | 2011-09-28 | SKANSKA USA Building Inc. |  | 80558 | 91793 | 2011-12-02 | 2015-03-15 | 2013-10-01 | 2015-02-03 | 96% |  |  | PH 2 Construction Progress: Sch. 95% Act. 95% with BOD of 15 Mar 2015. Includes Buildings A, B & C. Above ceiling MEP inspection is underway. Finish flooring and polishing the terrazzo tile is underway. Contractor developing punchlist at all exterior elevations. Central Energy Plant generator systems installation is underway. Red Zone meeting #6 was held on 2 Oct 2014. 10 days were added to the Phase 2 Contract as the result of two mandatory modifications. The revised construction completion date is 10 Jan 15. The BOD remains 15 Mar 15. Funds being used to help end state of project.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 71251 | Dental Clinic Replacement | 2009-09-16 | 2011-05-17 | Forrester Construction Company |  | 2832 | 3185 | 2011-05-17 | 2012-09-25 | 2011-09-10 | 2012-12-06 | 100% |  |  | Project Complete. Paid Final Invoice, and received Release of Claims from Contractor. Construction Contract and Project now in Close Out Phase. Fiscal Closeout is scheduled, and tracking for 28 Nov 2014, along with Project # 64241.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction | WASHINGTON | UNITED STATES | 47344 | Preventive Medicine Facility | 2011-05-03 | 2011-09-13 | Charpie-Korte Group LLC |  | 7230 | 7676 | 2011-10-14 | 2013-02-28 | 2013-02-28 | 2013-02-28 | 100% |  |  | Project closed.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66693 | Health/Dental Clinic Replacement | 2013-07-09 | 2013-09-30 | Federal Republic of Germany |  | 34294 | 34376 | 2014-02-03 | 2016-06-11 | 2015-08-22 | 2016-04-12 | 20% |  |  | Construction started on 03 Feb '14 IAW the schedule. Construction completion: 20%. Current work includes: Concrete roof slab is ongoing. Exterior window prep and install is ongoing. Cast in place concrete wall install for the 2nd Flr is substantially complete. Foundation work for the mechanical enclosure is ongoing. Parking lot curbstone and gutter install to begin end of October. Close out expected within 2 years of completing construction.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction |  | GERMANY | 66588 | Health Clinic Add/Alt | 2012-11-07 | 2013-03-18 | Federal Republic of Germany |  | 32103 | 32103 | 2013-04-08 | 04 Oct '16 | 2016-04-12 | 04 Sep '16 | 54% |  |  | 20OCT14 CONSTRUCTION STATUS: - Mech/Elect rough-in work continues; installing cable trays, fire sprinkler piping, plumbing,ductwork, and comms on 1st & 2nd floors. - Erecting walls and door frames, 1st & 2nd floors. - Continue installation of exterior facade; including exterior facade work on rooftop mechanical room. - Asphalt top course placed on Phases 1 & 2 parking areas, and new access road. - Construction of new lobby between existing and new Health Clinics ongoing. - Working building perimeter fire lane.
2014-10-31 | 2011 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 51740 | Health/Dental Clinic Replacement | 2011-05-13 | 2011-08-26 | Ilsung Construction Co., Ltd. |  | 9821 | 10169 | 2011-08-26 | 2014-04-23 | 2013-05-13 | 2014-04-23 | 100% |  |  | New health/dental clinic building transferred 16 May 13. Existing health clinic is being retained by the DPW at their request. Existing dental clinic demolished 19 Mar 14. Project BOD is actualized at 23 Apr 14. POF discussed the ribbon cutting ceremony with HFPO (LTC Marsh) who responded that the 65th MED BDE is conducting the ceremony and will issue invitations. As of 4 Aug 14, no ceremony date has been set. Delay was due to deficiencies, however, all have been corrected as of 22 Jul 14. The Carroll Dental Clinic OIC and NCOIC were in the lead for the ceremony, however, per HFPO, preparations for a ceremony does not appear to be occurring. Total project BOD (incl demo) was actualized at 23 Apr 14. Final payment on the construction contract was disbursed 27 Aug 14.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction |  | UNITED KINGDOM | 72727 | Medical/Dental Clinic Replacement | 2013-02-21 | 2013-09-24 | Vinci Construction UK Ltd |  | 11958 | 11958 | 2014-05-06 | 2015-07-31 | 2015-10-30 | 2015-10-30 | 25% | 13060 |  | Reprogrammed $13.06M from Lackland Ph 2 to RAF Croughton; New groundwork subcontractor started on site 30 June 14.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 65030 | Naval Hospital Great Lakes Health Clinic Demolition | 2011-10-18 | 2012-06-08 | Brandenburg Industrial Svc Co | N40083 12 C 0001 | 5835 | 6195 | 2012-09-12 | 2014-04-21 | 2013-09-13 | 2014-08-08 | 100% | -3994
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 79554 | Child Development Center | 2012-05-31 | 2012-09-13 | Whiting Turner Contracting Co | N4008010D0494 DO 0005 | 14200 | 14457 | 2013-03-01 | 2014-04-07 | 2014-02-22 | 2014-06-02 | 100%
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71408 | Dental Clinic Replacement | 2012-05-18 | 2012-10-29 | Manhattan Hunt JV | N40080 13 C 0151 | 18371 | 19488 | 2013-03-01 | 2016-12-06 | 2016-09-29 | 2017-01-28 | 0% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | MISSISSIPPI | UNITED STATES | 71503 | Branch Health Clinic | 2012-03-22 | 2012-07-25 | Satterfield & Pontikes Constr, Inc | N69450 12 C 0754 | 19096 | 19758 | 2012-09-01 | 2014-09-09 | 2014-09-09 | 2015-05-22 | 77% |  |  | Single Contract for both ACC & Dental. Total contract award IAO $214,801K.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | FLORIDA | UNITED STATES | 70597 | Medical Clinic | 2012-02-10 | 2012-08-27 | BL Harbert International, LLC |  | 8897 | 9123 | 2012-10-17 | 2015-01-05 | 2014-10-07 | 2014-10-07 | 97% |  |  | Contingencies at District available for obligation : $122,390 Project on schedule no issues. SAM must provide a new completion date.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | GEORGIA | UNITED STATES | 72292 | Hospital Addition/Alteration Phase 2 | 2012-03-06 | 2012-09-18 | McCarthy Building Companies, Inc. |  | 37778 | 43730 | 2012-10-15 | 2017-03-23 | 2016-10-14 | 2017-02-14 | 60% |  |  | Design error (for exterior precast panels) required work stoppage to remove, redesign, & replace the panels. 145 days were added to the emergency dept interim milestone & 83 days to overall project completion. Modification to add medical air was issued unilaterally and could impact schedule. Contingencies at district: $650,762. Potential AE Liabilities.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 70438 | Hospital Addition/Alteration | 2011-09-28 | 2012-05-14 | M.A. Mortenson Company (DBA: Mortenson Construction) |  | 43466 | 45898 | 2012-08-22 | 2015-05-23 | 2015-02-21 | 2015-03-25 | 79% |  |  | Curtain Wall - Flood Event Issue: Work continues to move forward with the KTR's Alternate Design. The exterior enclosure work has commenced at all locations with the framing and sheathing finishing up in all locations and air barrier to begin shortly. Still waiting to see a claim/REA from the Contractor that shows the cost impact due to the Curtain Wall issue. 21 2 day delay. Claim could cause an ATR if KO approves current amount of about $5M.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 70351 | Hospital Alteration | 2012-02-22 | 2012-08-10 | The Robins & Morton Group |  | 22400 | 23219 | 2012-09-13 | 2014-09-30 | 2014-06-23 | 2015-12-04 | 56% |  |  | Contractor behind schedule 73%. 6th floor final completed; 5th floor final completed; 3rd floor final completed; 4th floor pre-final completed. Contingencies at District: $272,903. SAS to provide new BOD. Marginal rating issued to contractor.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70580 | Dental Clinic Addition /Alteration | 2012-08-02 | 2012-12-10 | Structural Associates Inc. |  | 4370 | 4370 | 2013-01-09 | 2015-04-09 | 2015-01-09 | 2015-01-09 | 98% |  |  | Completing punch list item. Commissioning of systems underway.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 70579 | Medical Clinic (SFCC) | 2012-10-05 | 2013-02-13 | Structural Associates. Inc. |  | 8934 | 8934 | 2013-03-15 | 2015-06-11 | 2015-03-11 | 2015-03-11 | 82% |  |  | Continue interior framing and drywall installation. Continue rough-in of electrical, mech., plumbing, fire protection. Site work and installation of sewer line underway.
2014-10-31 | 2012 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 51969 | Hospital Nutrition Care Department Add/Alt | 2011-12-19 | 2012-08-29 | JE Dunn Construction Company |  | 28291 | 26991 | 2012-10-02 | 2015-02-26 | 2014-10-30 | 2015-04-13 | 59% |  |  | Project RFP included a detailed equipment list prepared by AE1 which included the statement “For Information Only,” permitting the contractor to deviate from the equipment list, resulting in a design which changed the meal preparation and distribution operations and increased staffing. Health Facilities Planning Agency (HFPA) requested a redesign to eliminate these problems. The re-design resulted in a delay, slipping the construction completion date 283 days.The contractor's estimate was $1.5M greater than the government's. Negotiations concluded on 4 April without the contractor and government in agreement. The government issued a unilateral contract modification 9 April 14. *The contractor has filed seven claims regarding this issue on 31 Sep 14, totaling $1,370,385. Total available contingency is currently $2,667,364. - KO reviewing claims for merit. * Increase Energy Efficiency (CLIN0013, Contract Option 5; $418,419.00). Option awarded with contract and requires increase in efficiency from 40% to 50%. KTR unable to meet the requirement; requested partial compensation. Request unsupported by field office and SWF staff engineers. Payment denied by ACO. KTR continues to pursue claim.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | CALIFORNIA | UNITED STATES | 72808 | Medical Clinic Replacement | 2013-07-25 | 2013-12-27 | T.B. Penick & Sons, Inc | N62473 10 D 5412 DO 0007 | 18703 | 18703 | 2014-02-28 | 2015-04-16 | 2015-03-16 | 2015-03-16 | 13%
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 78143 | Navy Drug Lab Replacement | 2013-01-14 | 2013-08-22 | Blinderman Constr Co | N40083 13 C 0003 | 14864 | 14757 | 2013-11-08 | 2015-02-15 | 2015-01-15 | 2015-04-18 | 74%
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 71507 | Branch Health Clinic Replacement | 2013-02-28 | 2013-12-18 | Turner Construction Co | N40080 14 C 0154 | 41408 | 41451 | 2014-04-30 | 2016-04-04 | 2015-10-15 | 2015-11-18 | 14% |  |  | Groundbreaking is the 18 April 2014.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80307 | Implement Base Installation Appearance Plan | 2013-04-23 | 2013-09-27 | Allen & Shariff | N40080 10 D 0496 DO 0021 | 4898 | 4608 | 2014-04-01 | 2015-03-17 | 2015-03-31 | 2015-06-15 | 3%
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities - Dosimetry Award | 2013-07-25 | 2012-09-12 | G-W Management Servicxes Inc | N40080 10 D 0498 DO 0025 | 5286 | 5217 | 2013-10-15 | 2014-04-04 | 2013-12-13 | 2014-03-25 | 100%
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80306 | Temporary Facilities | 2014-03-15 | No Entry | [11 empty] | On hold per DHA
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80308 | Electrical Utility Upgrades | 2013-08-15 | 2014-07-15 | Walsh Construction Company II LLC | N40080 14 C 0158 | 26947 | 26947 |  |  | 2016-02-12 | 2016-02-12 | 0% | 19460 |  | Reprogrammed $19,460 in FY10 MILCON funds from NAVHOSP Guam for FY13 Bethesda Electrical and Cooling Towers project on 7 Jul 2014.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 78144 | Medical Clinic Addition | 2013-02-01 | 2013-06-10 | Homeland Contracting Corp | N40085 13 C 6003 | 14354 | 14586 | 2013-10-08 | 2015-03-31 | 2015-03-17 | 2015-07-08 | 66%
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | SOUTH CAROLINA | UNITED STATES | 71317 | Medical Clinic Replacement | 2013-02-22 | 2013-06-14 | Walsh Federal, LLC | N69450 13 C 1756 | 38744 | 39938 | 2013-12-06 | 2017-10-08 | 2016-12-30 | 2017-08-16 | 26%
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 78146 | Veterinarian Facility | 2013-05-31 | 2013-09-27 | Kenmar-Gaskins JV | N40085 13 D 7772 DO 0001 | 7254 | 7333 | 2014-02-28 | 2015-05-15 | 2014-12-06 | 2015-06-22 | 32%
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 51639 | USARIEM Replacement High Altitude Research Lab | 2015-07-30 | 2015-12-31 | [11 empty] | Received Code 7 Directive on 26 Jun 14. PM met with stakeholders the week of 28 Jul 14 to discuss the way forward and develop the revised design schedule. The most significant action impacting project completion will likely be the preparation of NEPA documents by the City of Colorado Springs. Will need Funds authorization extension.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | ILLINOIS | UNITED STATES | 72718 | Medical Logistics Warehouse Replacement | 2012-10-18 | 2013-06-18 | R&W Builders |  | 2215.9 | 2215.9 | 2013-07-01 | 2014-07-30 | 2014-04-27 | 2014-07-23 | 95% |  |  | Project awarded 18 Jun 13, NTP issued 1 Jul 13. A contract time extension for weather delays was issued due to adverse weather conditions. Contingency balance available: $44,318 Potential UCRs: 0001- Emergency Generator Connection Point 0002- Humidity Control in Open Bay. 0003- Walk-In Cooler Contingency Reserve: $66,477
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | MISSOURI | UNITED STATES | 71679 | Dental Clinic | 2012-10-18 | 2013-07-31 | Macnak-Korte Joint Venture |  | 10687 | 10687 | 2013-12-02 | 2015-04-29 | 2015-02-19 | 2015-02-19 | 76% |  |  | Design/Scope: Design-Build / Primary Facilities include the dental clinic (30 chairs), outdoor troop shelter and building information systems. Also includes demolition of nine buildings. End users are IET soldiers. Construction: Brick work is 100% complete, roofing is 100% complete; mechanical, electrical, plumbing (MEP) rough-in is 99%, drywall and insulation is 99%. Troop shelter is installed on the South East corner, Entry parking is striped and light poles 100% installed. Back service entrance construction is complete. Final grading and landscape is ongoing (80%), sod being placed (80%). Windows are in, exterior doors are installed. Fiber optic cable has been pulled through manholes and tested for 100% conductivity. Schedule: On schedule. LEED: Silver required (solar panels for domestic hot water and solar light tubing). Time Growth: None to date FISD: Included in contract completion date (19 Feb, 2015).
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71325 | Medical Clinic Replacement | 2012-11-30 | 2013-09-16 | Heery International, Inc., 999 Peachtree Street, NE, Suite 300, Atlanta, GA 30309-3915 |  | 45536 | 47116 | 2013-10-24 | 2017-07-21 | 2016-04-30 | 2016-10-23 | 10% |  |  | Awarded 13 Sep 2013. NTP 24 Oct 2013. Final design underway. Contractor has begun mobilitzing to start site work. Contingencies at District: $697,507.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77979 | Medical/Dental Clinic Replacement | 2013-09-03 | 2014-03-27 | JE DUNN + HWA |  | 47044 | 47044 | 2014-04-28 | 2018-02-22 | 2017-10-25 | 2017-10-25 | 0% |  |  | Award made 27 March 2014. Questions raised about UST and abandoned housing debris and utilities on site 09 May 14. USACE Albq proposed courses of action and fowarded to DHA on 20 May 14. On 28 May 14 DHA directed characterization of buried debris using AF O&M funds, and hold on giving the contractor (JE Dunn) NTP. On 25 July USACE was notified that the Base CE excavated approximately 90% of the new clinic footprint and removed approximately 400 feet of A-C water line. On 30 July, it was determined that a ground-pentrating radar survey was no longer recommended. On 31 July it was decided to proceed with issuing NTP to the D-B contractor. NTP was issued 12 August. Project Kickoff/Design Charrette will occur 16-19 September. Request for Equitable Adjustment for Gov't delay after award submitted by Contractor on 21 AUG 14. IGE for REA completed. Follow-up interviews with Med Group staff scheduled for 12 & 13 Nov.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction | NEW YORK | UNITED STATES | 73776 | Soldier Specality Care Clinic | 2012-11-15 | 2013-12-18 | Structural Associates |  | 11163 | 11163 | 2014-01-06 | 2016-04-05 | 2016-01-06 | 2016-01-06 | 18% |  |  | Site work and underground Utility installation continues. Contractor has started construction of the building foundation. Final revisions being made to building design.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72420 | Medical/Dental Clinic Addition | 2012-12-26 | 2013-06-05 | Yuil Engineering & Construction Co., Ltd. |  | 8544 | 8708 | 2013-06-05 | 2015-05-16 | 2015-02-25 | 2015-03-22 | 63% |  |  | Contingency Amounts: District $64,710; HQ Mgmt $140,121. 25 days have been added to the CCD for several MODs to date. A user requested change to the DIPC (Dental Instrument Processing Center) area resulted in much discussion between Corps and DHA over process. Clarification ongoing between District, MX and DHA.
2014-10-31 | 2013 | Defense Health Agency | Major Military Construction |  | KOREA, SOUTH | 72419 | Hospital Addition/Alteration | 2013-07-26 | 2013-09-26 | Seohee Construction Co., Ltd. |  | 22361 | 22325 | 2013-09-26 | 2017-10-23 | 2017-08-08 | 2017-08-08 | 17% |  |  | Contingency Amounts: District $372,486; HQ Mgmt $787,958. Completed formwork for beam & slab of the upper level. Completed the electrical conduit pipe installation. Demolished the Bus Stop Concrete Structure & concrete retaining wall and curb. Phase "0" under progress: connection of existing sprinkler pipes (Area "B")
2014-10-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80904 | Mechanical & Electrical Improvements | 2014-01-30 | 2015-01-27
2014-10-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 80913 | Parking Garage | 2014-05-30 | 2014-09-24 | John C. Grimberg Co. Inc. | N40080 10 D 0492 DO 0009 | 15835 | 15835 |  |  | 2016-04-16 | 2016-04-16 | 0%
2014-10-31 | 2014 | Defense Health Agency | Major Military Construction | KENTUCKY | UNITED STATES | 71511 | Ambulatory Care Center | [13 empty] | Code 8 Received 30 April 2014, project is cancelled
2014-10-31 | 2014 | Defense Health Agency | Major Military Construction | MARYLAND | UNITED STATES | 77000 | Public Health Command Laboratory Replacement | 2014-03-24 | 2015-04-30 | [8 empty] | 0% |  |  | (UPDATE: 10/30/14): Project currently unawardable and undergoing Source Selection coordination (Procurement Sensitive). Source selection boards reconvened week of 06 October 2014. Briefing to DHA scheduled for 18 Nov 14. Projected contract award 30 Apr 15 subject to change pending coordination of Congressional reprogramming timeline.
2014-10-31 | 2014 | Defense Health Agency | Major Military Construction | NEW MEXICO | UNITED STATES | 77922 | Medical Clinic Replacement | 2014-02-25 | 2014-08-20 | Gilbane |  | 45629 | 45629 | 2014-10-27 | 2018-06-12 | 2018-01-30 | 2018-01-30 | 0% | 23279 |  | Bids were opened 18 Apr 14. SSEB convened 21 Apr to 02 May. Tech Report completed 23 May 14. Requested ATA 29 May. Awaiting PARC review of award package. Award date will slip further if authority to award and funds are not provided by 18 June 2014. Reprogrammed $1.9M from Medical Clinic Replacement, Holloman, AFB, NM to FY14 Hyperbaric Addition at San Antonio, TX on 24 Jun 14. Funds received 29 Jul. PARC reviewed package and held telecom 1 Aug. Responding to PARC comments by 8 Aug. Award of contract August 19, 2014. (Contract No. W9127S-13-D-6000 DM01). This was a DB Best Value Task Order awarded utilizing the Little Rock District National MATOC. (Contractor is Gilbane Federal Joint Venture, San Antonio, TX Award Amount: $45,629,836.00. Reprogrammed $1.9M from Medical Clinic Replacement, Holloman, AFB, NM to FY14 Hyperbaric Addition at San Antonio, TX on 24 Jun 14. Scheduled the 'Pre-Work' conference and D-B Kickoff meeting / Design Charrette in October. 'Pre-Work' conference and D-B Kickoff meeting / Design Charrette held 28-31 October 2014.
2014-10-31 | 2014 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81340 | SAMMC Hyperbaric Facility Addition | 2014-03-17 | 2014-06-30 | Gilbane |  | 11289 | 11289 | 2015-07-10 | 2016-12-28 | 2016-09-30 | 2016-09-30 | 0% | 1900 |  | Contract awarded to Gilbane on 30-Jun-14. July 29th Pre-Con held. Directive provide in May 2013 increasing PA to $12.6M. Code A issued on 17 Mar 2014. Reprogrammed $1.9M from Medical Clinic Replacement, Holloman, AFB, NM to FY14 Hyperbaric Addition at San Antonio, TX on 24 Jun 14. *A requirement for on-call and on-site explosive safety personnel for different phases of excavation was identified late in the RFP solicitation phase and not included in the base contract. Discussions with the installation and AFCEC have taken place and an agreement on roles and responsibilities should be completed by 22 Sep. Funding should be OMA. *10 Jul 15: Anticipated construction start. Site being checked for UXO.
2014-10-31 | 2014 | Defense Health Agency | Major Military Construction |  | BAHRAIN | 81436 | Medical/Dental Clinic Replacement | 2015-04-15 | 2015-08-15 | [11 empty] | 5 Nov 14 - The D-B package is complete and on the shelf pending advertisement in Apr 2015 and Award in Aug 2015. This award schedule is being driven by site availability, upon completion of an on-going MCN project, the P908 Operations and Support Facilities, scheduled for completion in July 2016. TAM is planning award of the D-B contract for the Medical/Dental Clinic in Aug 2015 with a one year design period before the contractor begins construction in Aug 2016. The project CWE is $43,823,020; this CWE is up-to-date as of completion of the 35% design that will be included in the D-B RFP, and takes into account the projected award date of 15 Aug 15. TAM will have the AE re-validate this estimate upon completion of a design code refresh and BCOE review of the RFP package prior to advertisement in April. On 17 Oct 14, TAM-PM met with DHA (CAPT Berchtold) and provided a status update of project milestones and progress on construction of P908.
2014-10-31 | 2015 | Defense Health Agency | Major Military Construction | COLORADO | UNITED STATES | 72414 | Dental Clinic Replacement | 2014-12-30 | 2015-03-30 | [11 empty] | Final draft RFP submittal review complete. Revising RFP to follow the last template.
2014-10-31 | 2015 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81423 | Medical Clinic Replacement (Reid Clinic) | 2015-01-20 | 2015-06-10 | [5 empty] | 2017-12-31 |  | 2017-08-31 |  |  |  | 6 Aug 14 - Negotiations for AE1 completed: $946,487.69 14 Aug 14: AE1 Award and NTP 28 Aug 14: Contractor Kick-off Meeting 8 - 12 Sep 14: AE1 Site Investigation and Land Survey 22-26 Sep 14: AE1 Design Charrette 06-10 Oct 14: Topographic survey 31 Oct 14: 35% Submittal RFP Jan 2015, award June 2015. MATOC has 2 poor performing contractors. Will discuss acquisition strategy.
2014-10-31 | 2015 | Defense Health Agency | Major Military Construction | VIRGINIA | UNITED STATES | 81430 | Hospital Add/CUP Replacement | 2015-07-09 | 2015-12-15 | [11 empty] | Received Code 7 on 16 Oct 13. Orginal scheduled AE1 contract award date was 30-APR-14. Actual award on 02-SEP-14. Primary cause for delay in award of the AE1 was conflicting scope requirements and level of design for the D-B RFP between DHA and the MX. The AE1 PoP to RTA provides an Advertise date of 01 June 2015. The construction contract will also include turnkey FFE and medical equipment. Thus increasing the procurement to > $50M. FY15 award is considered high risk due to the potential for an extended period (multiple rounds of discussion) for review of D-B contract proposals
2014-10-31 | 2016 | Defense Health Agency | Major Military Construction | HAWAII | UNITED STATES | 78150 | Medical Clinic Replacement
2014-10-31 | 2016 | Defense Health Agency | Major Military Construction | HAWAII | UNITED STATES | 80412 | Health/ Dental Clinic Add/ Alt Phase 1 (Parking Structure) | 2015-10-20 | 2016-03-14 |  |  |  |  | 2016-04-12 | 2017-12-05 |  |  | 0% |  |  | DHA issued DA memo dated 29 Jul 13 for phase 1 with PA of $140.3M. On 16 Oct 13, DHA approved split strategy to award design-bid-build contract for parking structure, and a design-build contract for the clinic. DHA DA memo dated 30 Jun 14 provided revised 1391 and new PA $126.2M. Parking design Charrette conducted 29 Aug 14. Clinic A-E design contractor selected, award is projected in Nov 14. ISSUES: Project scope has evolved. Design time was lost. Environmental concerns limit building height due to the location in a historic district.
2014-10-31 | [6 empty] | Health/ Dental Clinic Add/ Alt Phase 1 (Clinic) | 2015-12-10 | 2016-08-05 |  |  |  |  | 2016-09-06 | 2017-06-22 |  |  | 0%
2014-10-31 | 2016 | Defense Health Agency | Major Military Construction | OHIO | UNITED STATES | 71642 | Satellite Pharmacy Replacement | [13 empty] | Code 7 received. DA dated Jan 14 moved project to FY16. Expect CWE to reach $7M due to increase in CY and new criteria on fire pumps. Complete scrub of all design criteria and RFP documents will be required.
2014-10-31 | 2016 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 81422 | Ambulatory Care Center Phase 4 | [13 empty] | AF is currently updating DD1391 from 2008 vintage to include HazMat and other costs. New design authorization code (Code 6) and P&D funds request will likely be the ensuing action upon receipt of revised DD1391. SWF to provide acquisition plan ASAP.
2014-10-31 | 2016 | Defense Health Agency | Major Military Construction |  | GERMANY | 77986 | Dental/ Medical Clinic Replacement | 2016-01-27 | 2016-06-30 | [11 empty] | Code 3 received from DHA on 26 July 2013. July 2013. 1391 amount PA has been reduced from $37M to $35M effective 08 June'14.. Presentation to DHA was held on 21 May 2014 in Washington. 20% design completed and transferred to the German government. The German AE is on board and the transition meeting was held on 28 May 2014. Started 35% design 25 July 2014; 35% submittal due first week of Dec 2014. On schedule for a June 2016 award to industry. Awaiting guidance on BIM decision. Request DHA to provide guidance.
2014-10-31 | 2017 | Defense Health Agency | Major Military Construction | OKLAHOMA | UNITED STATES | 72742 | Medical Clinic Replacement
2014-10-31 | 2017 | Defense Health Agency | Major Military Construction | TEXAS | UNITED STATES | 67402 | Blood Donor Center Replacement | 2015-01-15 | 2015-06-25 | [11 empty] | Project is now in the FY17 DOD Medical POM and is currently Design Code 5, Deferred. SWF/SWD have not authority to expend P&D Funds on any design activity
2014-10-31 | 2017 | Defense Health Agency | Major Military Construction |  | GERMANY | 77139 | Behavioral Health Clinic Addition/Alteration | [13 empty] | Code 3 anticipated Jan 2015.
2014-10-31 | 2008 | Defense Intelligence Agency | Major Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | 154207 | Emergency Backup Water System | 2009-08-03 | 2009-09-30 | AKIMA Construction Services, LLC |  | 1012 | 1012 | 2009-10-03 | 2012-01-20 | 2011-09-16 |  | 100% |  |  | Approp. - $1,012
2014-10-31 | 2010 | Defense Intelligence Agency | Major Military Construction | ALABAMA | USA | DIA10-002 | Replace MSIC Explosive Ordinance Exploitation (EOE) Complex | 2011-12-14 | 2012-06-14 | Southeast Cherokee Construction Company |  | 12000 | 12003 | 2012-07-20 |  | 2014-01-20 | 2014-05-21 | 100% |  |  | Approp. - $12,000. Bid Base amount $10,191,600. Notice to Proceed issued on 12 July 2012. Official BOD was 26 August 2014. Several minor and two significant punch list items remain to be resolved. A separate completion date will be provided upon execution of a change order for correcting the emergency lighting/life safety deficiency at Pods B and C.
2014-10-31 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction |  | KOREA, SOUTH | DIA10-001 | FOB-K Renovation of Two Buildings to Include Administrative and SCIF Spaces | 2011-07-21 | 2012-04-09 | SEONG BO Construction Co, Ltd. |  | 4360 | 5050 | 2012-04-09 |  | 2013-10-09 | 2013-10-17 | 100% |  |  | Reprogramming action completed and MIPR HHM402-2-0273 (for FY10 $690K) added to the current contract obligation. Contract awarded and Notice to Proceed (NTP) issued 09 April 2012. Final inspection scheduled October 2013. Base contract completed 17 October 2013. DD Form 1354 completed. Project in process of closeout.
2014-10-31 | 2010 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA11-002 | JBAB Paving of Gravel Parking Lot | 2011-02-11 | 2011-07-05 | Grunley/Goel Joint Venture |  | 2984 | 2819 | 2011-07-20 | 2012-07-25 | 2012-07-18 | 2012-07-25 | 99% | 700 |  | Approp. $2994 - reprogramming action completed and MIPR HHM402-2-0273 for $690k deducted from current contract obligation. Beneficial Occupancy Date (BOD) was 25 July 2012. Received As-Built drawings. Still awaiting final DD Form 1354 and closeout.
2014-10-31 | 2012 | Defense Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | DIA12000005 | Construction of Remote Delivery Facility (RDF) Meeting SCIF Standards | 2013-08-21 | 2013-09-25 | Heard Construction |  | 10758 | 6058 | 2013-10-10 |  |  | 2014-11-27 | 30% |  |  | Approp. - $10,758; CAT I Reimbursable acceptance received on 17 Dec 2012. In Jun 2013 notification of scope reduction signed IAW Title 10USC2853. $4.7M returned to DIA in May 2013. Major construction activities last month were the erection of the structural steel and pre-cast panels, completing the sewer tie-in from the Facility to the Station's main line and installing the roof decking. Significant contractor activities planned this month are the placing of the concrete slab inside the Facility, beginning the storm drain on the south side of the facility and starting the roof insulation/waterproofing.
2014-10-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000001 | DIAC Parking Garage Replacement | [5 empty] | 739156 |  |  |  |  | 0% |  |  | Approp. - $13,645 - $793,156 CAT I obligated. NAVFAC Gold Team awarded the A/E contract in June 2013. Conducted the Design Charette on 18 July 2013. First NCPC, CFO and SHPO review conducted on 2 August 2013. Contract awarded on 23 September 2014. Preliminary concept review currently underway.
2014-10-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000003 | DIAC Chilled Water Project for Data Center | [13 empty] | Approp. - $1,121 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-10-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000003 | DIAC Cooling Tower for Data Center | [13 empty] | Approp. - $941 - NAVFAC awarded the design contract 30 Jan 2013. Preliminary estimates indicate project costs exceed programmed amounts.DIA initiated reprogramming actions.
2014-10-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | DISTRICT OF COLUMBIA | UNITED STATES | DIA12000002 | Uninterrupted Power Supply (UPS) for Data Center | [5 empty] | 1200 | [7 empty] | Approp. - $1,076 - NAVFAC awarded the design contract 30 Jan 2013. Estimates indicate project costs exceed programmed amounts. DIA initiated reprogramming actions.
2014-10-31 | 2012 | Defense Intelligence Agency | Unspecified Minor Military Construction | ALABAMA | UNITED STATES | ECIP 120001 | Chiller Plant Operation |  | 2013-08-08 | Honeywell |  | 997 | 1071 | 2013-08-21 |  | 2014-08-08 | 2014-11-30 | 78% |  |  | Approp. - $1,200 - Project awarded August 2013. Kickoff meeting held 5 September 2013. All VFDs and field component sensors (flows, temperatures) have been installed. Optimization controls programming commissioning has slipped to mid-December. Training will be video-recorded per contract modification.
2014-10-31 | 2012 | Defense Information Systems Agency | Major Military Construction | ILLINOIS | UNITED STATES | 68120` | Construct New Facility Scott AFB - Design |  | 2012-05-01 | Burns & McDonnell |  |  |  | 2012-05-01 |  | 2013-05-31 | 2013-05-31 | 100% |  |  | Design completed May2013.
2014-10-31 | 2011 | Defense Information Systems Agency | Major Military Construction | ILLINOIS | UNITED STATES | DISA10-01 | Field Command Facility Upgrade | 2011-08-11 | 2011-09-30 | DWG & Associates |  | 1194 | 924.1 | 2011-10-26 | 2012-12-21 | 2012-09-19 | 2012-11-30 | 100% | -300 |  | Programmed Amount $1.385M. Awaiting final invoice from contractor. USACE advised of S&A Leakage for $8.92.
2014-10-31 | 2010 | Defense Information Systems Agency | Major Military Construction | HAWAII | UNITED STATES | DISA10-02 | Pacific Operations Facility Upgrade | 2010-08-30 | 2010-12-16 | Bulltrack-Watts (Joint Venture) |  | 12624 | 17212.464 | 2010-12-16 | 2013-04-22 | 2010-12-16 | 2013-04-22 | 100% | 300 |  | Programmed Amount: $9.6M. Contract Award: $12,624,500 included MILCON ($8.478M) + options for O&M ($2.765M) and Procurement ($1.380M) funded items. Final Project Costs: MILCON: $9.932M; O&M: $6.845M; Procurement: $1.5M. Awaiting final invoice from the contractor. No change.
2014-10-31 | 2012 | Defense Information Systems Agency | Major Military Construction |  | GERMANY | DISA10-03 | DISA Europe Facility Upgrades | 2013-01-22 | 1 May 13 (construction) | Way SS & Freytag Ingenieurbau AG |  | 1387.3 | 1387.3 | 2013-05-16 | 2014-01-11 | 2013-12-11 |  | 100% |  |  | Project descoped .25%. Sprinkler System. Unforeseen requirement to add double sprinkler heads due to false ceiling and additional water tank. Modification for paralleling switchgearr and extending the canopy over building entrance. Available funds to be used. Site pre-work started 16 Sept 13. Testing of generator and paralleling gear conducted 10 Dec 13. Scheduled slipped due to modification to etrance/foyer. Project completed 28 Feb 14 pending punchlist items. DISA Europe has requested mod to contract for additional thermostat on lower level of building for a/c in utility room, realign fire alarm cabling and entrance signage. Funding available. Received proposals for thermostat, signage and realigning fire alarm cabling. Approved signage and cabling proposals. Cost for thermostat is extremely high and needed for the additional is a nice to have. Thermostat proposal cancelled. The fire alarm cabling realignment completed. The signage to be installed 8 Oct 14. Project closed. Awaiting final invoices.
2014-10-31 | 2013 | Defense Information Systems Agency | Major Military Construction |  | GERMANY | DISA13-01 | DISA Europe Facility- Replace/Upgrade UPS and Paralleling Gear | [10 empty] | 0 | 0 |  | Revised Programmed Amount: $2.224M based on Sequestration Budget Cut. Intial PA: $2.413M Provided USACE SOW. USACE pursuing "indirect" contract for project execution..
2014-10-31 | 2014 | Defense Information Systems Agency | Major Military Construction | HAWAII | UNITED STATES | DISA14-01 | DISA Pacific Facility Upgrade | [10 empty] | 0 | 0 |  | Programmed Amount: $2.615M. Developed Statement of Work for redundant chiller which will work in conjunction with Navy's Energy Project (replacement of 2 existing chillers). A chiller load study conducted Apr 2014. The Navy's FY14 MILCON Energy Project ($2.019M) will replace two existing DISA PAC chillers. Contract awarded 15 Jul 2014. FNavy desing underway 65% review end of Nov 2014. Funding for development of RFP and in-house support $150K pending in DISA Comptroller Office.
2014-10-31 | 2008 | Defense Information Systems Agency | Base Realignment and Closures | MARYLAND | UNITED STATES | DISA 853 | DISA Headquarters, Inc 1 | 2007-10-11 | 2008-02-29 | Hensel Phelps Construction Company |  | 369605 | 176436 | 2008-04-16 | 2011-01-08 | 2011-04-15 | 2010-11-30 | 100% |  |  | Incrementally Funded for FY09
2014-10-31 | [6 empty] | DISA Headquarters, Inc 2 | 2007-10-11 | 2008-02-29 | Hensel Phelps Contruction Company |  | 369605 | 130128 | 2008-04-16 | 2011-01-29 | 2011-04-15 | 2010-11-30 | 100% |  |  | Incrementally Funded for FY09
2014-10-31 | [6 empty] | DISA Headquarters, Inc 3 | 2007-10-11 | 2008-02-29 | Hensel Phelps Construction Company |  | 369605 | 131662 | 2008-04-16 | 2011-02-19 | 2011-04-15 | 2011-01-24 | 100% |  |  | Incrementally Funded for FY10
2014-10-31 | 2013 | Defense Information Systems Agency | Major Military Construction | ILLINOIS | UNITED STATES | VDYDS97032 | Construct New Facility Scott AFB - Soil Remediation | 2013-04-05 | 2013-06-27 | Plexus Scientific Corp. |  | 1339.17 | 1339 | 2013-10-02 | N/A | 2013-11-23 | 2014-02-01 | 100% |  |  | Soil Remediation Contract Award Amount: $1.339,170.73 + USACE fees $161,333.27 = $1,500,504. Internal approvals from EPA, site Installation and State requirements coordinated. Phase IV & V excavation completed. USACE reviewing Plexus (contractor) responses to Illinois EPA comments. Final modification to adjust quantities will result in approximately $500K credit to Government. Contractor has submitted a $435K Request for Equitable Adjustment. USACE reviewing for merit. Final payment for this project will not be made until the final reports are approved. USACE has completed final agreement on quantities for the CLINs and corresponding mod. Environmental has completed the initial review of the revised REA. The draft evaluation is that the REA should be denied in full for no merit. NOTE: This is just a draft evaluation and is SUBJECT TO CHANGE as the rest of the team finishes reviewing the REA and a final decision is rendered. A credit mod for approximately $500K is also still pending.
2014-10-31 | [6 empty] | Construct New Facility Scott AFB - Facility Construction | 2013-05-24 | 2013-09-30 | River City |  | 66994 | 66994 | 2013-12-02 | 2016-05-30 | 2015-12-30 | 2016-03-01 | 36% | 0 |  | Revised PA: $77.515M Construction Contract Award: $66,994 on 30 Sept 13 to River City Construction (RCC). Construction Contract does not include the demo of Bldg 3189. This will be a separate contract. Contractor provided NTP letter issued on 9 Oct 13. Groundbreaking Ceremony: 13 Nov 13. Contruction Kickoff/Partnering Session: 14 Nov 13. As noted above Soil Remediation project impacted construction contractor having full access to site, 3 Dec 13 per contract, due to remediation delays (56 days). Construction contractor had full access to site 3 Feb 14, te. Communications Summit scheduled 18/19 Nov 14. Senior Advisory Group session scheduled 11 Dec 14. Overall project is 36% complete. Progress made: Grade beams 100% complete Slab on decks 68% complete Structural steel erection/detailing is approx. 99% complete Underground rough-ins 99% complete.. Move-in scheduled Jun-Sept 2016. -
2014-10-31 | [6 empty] | Construct New Facility Scott AFB - Demo of Bldg 3189 | [10 empty] | 0 | 0 |  | Estimated Contract Award FY16
2014-10-31 | 2008 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INC #1 - NAV SUP Fleet Logistiecs Center, Point Loma San Diego | 2008-02-20 | 2008-09-30 | Nova Group Inc. - Underground Construction Company - AJV | N62473-08-C-7501 | 52443 | 52443 | 2008-10-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-10-31 | 2008 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX0702 | Replace Central Heat Plant - New Cumberland | 2008-07-14 | 2008-09-28 | John C. Grimber Company | W912DR-08-C-0047 | 19757 | 20611 | 2008-11-30 | 2011-10-21 | 2011-07-21 | 2012-10-21 | 100%
2014-10-31 | 2009 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1002 | Replace General Purpose Warehouse - San Joaquin at Tracy | 11-Nov-08 | 11-Mar-09 | Whiting Turner Contracting Co. | W91238-09-C-0003 | 29345 | 30469 | 2009-04-02 | 2012-01-05 | 2012-03-17 | 2013-03-20 | 100% | -6558 |  | Rescinded per PL 111-117
2014-10-31 | 2009 | DLA Defense Distribution Center | Major Military Construction | FLORIDA | UNITED STATES | DESC0801 | Replace Fuel Storage Tanks - NAV Sup Fleet Logistics Center Jacksonville | 11-Mar-09 | 22-Sep-09 | Mid Eastern Builders INC | N69450-09-C-1261 | 22226 | 22640 | 2009-10-30 | 2012-12-31 | 2012-09-22 | 2012-12-15 | 100% | -9000 |  | Rescinded per PL 111-117
2014-10-31 | 2009 | DLA Defense Distribution Center | Major Military Construction |  | GERMANY | DDCX0904 | Logistics Distribution Center - Germersheim | 2010-02-12 | 2010-05-18 | Wolf & Muller Regionalbau GmbH & Co. / Petter Gross GmbH & Co. | W912GB-07-C-0018 | 36800 | 22649 | 2010-06-16 | 2012-01-25 | 2012-01-04 | 2012-01-04 | 100% | -10400 |  | Rescinded by OSD 24 May 11
2014-10-31 | 2009 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESC0808 | Replace Fuel Pipeline - JB PH Hickam | 2009-05-01 | 2009-06-12 | Watts Construction LLC | N62742-09-C-1302 | 17336 | 24695 | 2009-07-12 | 2014-05-30 | 2011-07-12 | 2014-05-30 | 100% | -5300 |  | Rescinded per PL 111-117
2014-10-31 | 2009 | DLA Defense Energy Support Center | Major Military Construction | NEW MEXICO | UNITED STATES | DESC0802 | Replace Fuel Storage Tanks - Kirtland AFB | 2009-04-06 | 2009-08-20 | Kinley Construction | W012PP-09-C-0025 | 7355 | 7762 | 2009-10-14 | 2011-05-13 | 2011-06-11 | 2011-06-11 | 100% | -5900 |  | Rescinded per PL 111-117
2014-10-31 | 2009 | DLA Defense Energy Support Center | Major Military Construction | UTAH | UNITED STATES | DESC0608 |  | 2009-01-29 | 2009-05-22 | Rockford Corp | W91238-09-C-0010 | 14636 | 15416 | 2009-06-18 | 2011-04-21 | 2011-05-13 | 2011-05-13 | 100% | -3000 |  | Rescinded by 0SD 24 May 11A
2014-10-31 | 2009 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC0703 | Replace Fuel Storage Tanks - Craney Island | 2009-04-01 | 2009-07-31 | Mid Eastern Builders INC | N40085-09-C-5037 | 36371 | 38331 | 2009-09-03 | 2012-12-29 | 2012-08-29 | 2013-09-30 | 100%
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#2 (of 4 Increments) - NAV SUP Fleet Logistiecs Center, Point Loma San Diego | 2008-02-20 | 2011-03-22 | Nova Group Inc - Underground Construction Company - AJV | N62473-08-C-7501 | 79509 | 131952 | 2011-03-22 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0803 | Replace Fuel Distribution System - Travis AFB | 2010-11-10 | 2011-02-18 | Kinley Construction | N62473-11-C-2401 | 12637 | 14208 | 2011-05-10 | 2013-05-20 | 2012-08-26 | 2013-08-31 | 100%
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC0908 | Replace Jet Fuel Storage Complex - Jacksonville ANG | 2009-10-29 | 2010-02-26 | Reliable Contracting Group | W912EP-10-C-0023 | 7909 | 9988 | 2010-04-27 | 2014-04-10 | 2011-09-20 | 2014-09-30 | 99% | -1900 |  | Rescinded by 0SD 18 May 11A
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | MINNESOTA | UNITED STATES | DESC1002 | Replace Jet Fuel Storage Complex - Duluth ANG | 2010-03-10 | 2010-07-16 | Talon Industries Inc. | W9128F-10-C-0051 | 11195 | 11195 | 2010-08-30 | 2012-01-12 | 2011-11-01 | 2012-01-09 | 100% | -2000 |  | Rescinded by 0SD 18 May 11A
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction | NORTH CAROLINA | UNITED STATES | DESC11S3 | Replace Pump Station - MCAS New River | 2010-02-20 | 2010-09-29 | North State Mechanical Inc. | N40085-09-D-5341 | 947 | 1047 | 2011-01-15 | 2012-11-16 | 2011-12-08 | 2012-08-10 | 100%
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC0904 | Replace Fuel Storage Tank - GTMO | 2010-01-19 | 2010-05-27 | Toltest, Inc | N69450-08-D-1283 | 8594 | 8658 | 2010-05-27 | 2011-11-28 | 2012-11-28 | 2012-11-28 | 100% | -2200 |  | Rescinded by 0SD 18 May 11A
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | GREECE | DESC0707 | Fuel Tanks and Pipeline Replacement - Souda Bay | 2010-01-29 | 2010-09-30 | AKTORS, S.A. | N33191-10-C-0214 | 19667 | 21060 | 2010-01-12 | 2013-07-06 | 2012-07-09 | 2013-07-06 | 100% | -8250 |  | Rescinded by 0SD 18 May 11A
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | KOREA, SOUTH | DESC0907 | Hydrant Fuel System - Osan AB | 2010-01-12 | 2010-04-16 | Namwha Construction Co. | W912UM-10-C-0013 | 17844 | 19441 | 2010-08-27 | 2015-02-02 | 2013-11-18 | 2014-11-15 | 93% | -2789 |  | Rescinded by 0SD 18 May 11A
2014-10-31 | 2010 | DLA Defense Energy Support Center | Major Military Construction |  | UNITED KINGDOM | DESC0910 | Connect Fuel Tank to Distribution Pipeline - RAF Mildenhall | 2010-04-23 | 2010-09-16 | Entrepose Industrial Services | QFQE063003 | 3300 | 3300 | 2011-03-07 | 2013-03-04 | 2011-08-18 | 2011-12-16 | 100%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities incr#3 (of 4 Increments) - Pt. Loma | 2008-02-20 | 2011-03-30 | Nova Group Inc - Underground Construction Company - AJV | N62473-08-C-7501 | 17400 | 149352 | 2011-03-30 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC10S4 | Aircraft Direct Fueling Station - Pt. Magu | 2011-04-29 | 2011-06-30 | RORE, INC. | N62473-11-C-2822 | 2553 | 2733 | 2011-07-30 | 2013-06-07 | 2012-07-15 | 2013-06-07 | 100%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | DESC11U1 | Truck Offload Facility - Edwards AFB | 2012-03-16 | 2012-07-12 | Kinley Construction Company | W9128F-10-D-0052 | 1019 | 1019 | 2012-07-26 | 2013-09-30 | 2013-09-30 | 2013-08-31 | 100%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC11S4 | Fuel Unload Facility - Hunter AAF | 2011-06-03 | 2011-09-15 | Ponds Constructors, Inc | W9128F-10-D-0051 | 1199 | 1398 | 2011-10-26 | 2013-12-30 | 2012-10-31 | 2013-12-30 | 100% | -980 |  | Rescinded by OSD 23 Mar 12A
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESC1190 | Alter Fuel Storage Tanks - JB PH Hickam | 2011-01-03 | 2011-05-26 | Reliable Contracting Group, LLC | W9128A-11-C-0009 | 7584 | 8078 | 2011-06-22 | 2012-12-17 | 2012-12-13 | 2013-08-30 | 100%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | IDAHO | UNITED STATES | DESC1113 | Replace Fuel Storage Tanks - Mt. Home AFB | 2011-03-30 | 2011-09-02 | Garco Construction, Inc. | W912DW-11-C-0013 | 16480 | 17158 | 2011-10-12 | 2014-05-28 | 2012-04-12 | 2014-07-27 | 100% | -8380 |  | Rescinded by OSD 23 Mar 12A
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | MARYLAND | UNITED STATES | DESC1003 | Replace Fuel Storage and Distribution Facilities - Andrews AFB | 2011-05-15 | 2011-10-31 | MEB General Contractors | N40080-12-C-2004 | 7971 | 8470 | 2011-11-21 | 2013-10-16 | 2013-05-03 | 2013-10-16 | 100% | -4872 |  | Rescinded by OSD 23 Mar 12A
2014-10-31 | 2011 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX0802 | Replace Headquarters Facility - New Cumberland | 2011-11-23 | 2012-08-17 | Walsh Construction | W912DR-12-C-011 | 80775 | 82555 | 2012-08-30 | 2016-02-29 | 2015-09-18 | 2016-01-20 | 63%
2014-10-31 | 2011 | DLA Defense Supply Center Columbus | Major Military Construction | OHIO | UNITED STATES | DSCC0802 | Replace Public Safety Facility - Colombus | 2011-04-04 | 2011-10-21 | Industria Paschen Group JV | W912QR-12-C-0001 | 5883 | 6197 | 2011-11-10 | 2013-03-01 | 2013-03-21 | 2014-05-29 | 100%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction | VIRGINIA | UNITED STATES | DESC0909 | Replace Fuel Pier - Craney Island | 2010-10-20 | 2011-09-12 | Mclean Contracting Company | N40085-11-C-0001 | 28815 | 32208 | 2012-11-26 | 2015-06-20 | 2014-07-03 | 2015-03-31 | 85% | -9428 |  | Rescinded by OSD 23 Mar 12
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC11S1 | Install Fuel Filter/Separators - Kadena AB | 2010-10-07 | 2011-06-27 | Nippo Corporation | W912HV-11-C-002 | 1175 | 1175 | 2011-07-13 | 2012-11-09 | 2012-10-27 | 2012-10-27 | 100%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC0503 | Hydrant Fuel System - Misawa AB | 2012-05-12 | 2012-09-22 | Tokyo Construction Co., Ltd. | W912HV-12-C-0013 | 25204 | 25425 | 2013-02-01 | 2015-06-20 | 2015-02-01 | 2015-03-01 | 84%
2014-10-31 | 2011 | DLA Defense Energy Support Center | Major Military Construction |  | UNITED KINGDOM | DESC0905 | Replace Hydrant Fuel System - RAF Mildenhall | 2011-04-19 | 2011-12-06 | Spiecapag | DEUSFMIL/13232 | 12535.429 | 12535 | 2011-12-09 | 2014-04-25 | 2013-03-14 | 2014-05-02 | 99%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | ALASKA | UNITED STATES | DESC1108 | Upgrade Rail Line - Eielson AFB | 2012-02-29 | 2012-07-06 | G2 Construction, Inc. | W911KB-12-C-0015 | 12210 | 12407 | 2012-07-16 | 2013-12-08 | 2013-12-05 | 2014-07-16 | 100%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC1103 | Replace Hydrant Fuel System - Davis Monthan AFB | 2012-05-04 | 2012-09-25 | Nova Group Inc. | W912PL-12-C-0029 | 18252 | 19125 | 2012-11-13 | 2015-02-02 | 2014-11-03 | 2014-12-03 | 99%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1205 | Replace Fuel Facilities - San Clemente Is. | 2012-05-15 | 2013-02-15 | Structural Associates Inc. | N62473-13-C-4213 | 27453 | 27610 | 2013-02-28 | 2015-03-11 | 2015-03-24 | 2015-07-01 | 69% | 10000 | FY09 Germersheim | 2853 Reprogramming
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC0704 | Replace Fuel Storage Facilities INCR#4 (of 4 Increments) - Pt. Loma | 2008-02-20 | 2012-03-29 | Nova Group Inc - Underground Construction Company - AJV | N62473-08C-7501 | 15512 | 164864 | 2012-03-29 | 2014-01-17 | 2013-09-23 | 2014-02-28 | 99%
2014-10-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1102 | Public Safety Facility - Tracy | 2012-03-06 | 2012-07-16 | MASCON, INC | W91238-12-C-0021 | 14615 | 15091 | 2012-08-29 | 2014-12-05 | 2014-03-24 | 2014-11-08 | 94%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC12S3 | Truck Load/Unload Facility - Whiting Field | 2012-01-13 | 2012-03-21 | Weston Solutions Inc. | N62583-09-D-0131 | 2500 | 3167 | 2012-03-21 | 2014-02-21 | 2013-03-24 | 2014-09-19 | 100%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESC12S5 | Upgrade Refueler Parking Area - JB PH Hickam | 2011-10-21 | 2012-03-13 | RAASS Brothers INC | N62473-13-C-4213 | 5079 | 5681 | 2012-08-05 | 2013-09-26 | 2013-04-09 | 2013-09-26 | 100%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | HAWAII | UNITED STATES | DESI1101 | Alter Warehouse Space - JB PH Hickam | 2012-01-11 | 2012-03-30 | GSI-ASI JV, LLC | N62478-11-D-4042/0004 | 5500 | 6430 | 2012-08-13 | 2014-09-30 | 2013-06-14 | 2014-04-29 | 99%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | LOUISIANA | UNITED STATES | DESC1106 | Hydrant Fuel System - Barksdale AFB | 2011-10-04 | 2012-01-30 | Thrash Commercial Contractors INC | N69450-10-D-0788/0002 | 4687 | 5470 | 2012-02-28 | 2013-08-02 | 2013-03-14 | 2013-08-16 | 100%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | MASSACHUSETTS | UNITED STATES | DESC1102 | Upgrade Hydrant Fuel System - Westover ARB | 2012-07-12 | 2013-05-28 | Structural Associates Inc. | W912WJ-13-C-0004 | 24480 | 25378 | 2013-06-18 | 2016-02-08 | 2016-02-02 | 2016-02-08 | 46% | 4500 | FY09 Hill, Hunter & Germersheim | 2853 Reprogramming
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | MISSISSIPPI | UNITED STATES | DESC11S2 | Replace Refueler Parking Facility - Columbus AFB | 2012-02-14 | 2012-04-30 | Reliable Contracting Group, LLC | W9128F-10-D-0053 | 2360 | 2424 | 2012-06-07 | 2013-06-18 | 2013-06-18 | 2013-06-18 | 100%
2014-10-31 | 2012 | DLA Defense Supply Center Columbus | Major Military Construction | OHIO | UNITED STATES | DSCC1201 | Security Enhancements - Columbus | 2012-02-19 | 2012-05-04 | Pinnacle Construction Development Group | W912QR-12-C-0031 | 8550 | 10318 | 2012-06-07 | 2014-09-15 | 2013-09-23 | 2014-12-24 | 95%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1201 | Replace Fuel Transfer Pipeline - Altus AFB | 2012-03-26 | 2012-09-17 | Reliable Contracting Group, LLC | W912BV-12-C-0024 | 8856 | 8671 | 2012-10-17 | 2013-12-23 | 2014-03-01 | 2013-12-23 | 100%
2014-10-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1203 | Upgrade Access Control Points - New Cumberland | 2013-04-17 | 2013-09-30 | The Matthews Group | W912DR-13-C-0054 | 16327 | 16327 | 2014-02-04 | 2016-03-21 | 2016-03-21 | 2016-03-21 | 6%
2014-10-31 | 2012 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1202 | Replace General Purpose Warehouse - New Cumberland | 2012-09-17 | 2013-11-20 | Corothers Constuction Inc | W912DR-14-C-0005 | 24622 | 24622 | 2014-01-14 | 2015-10-23 | 2015-07-29 | 2015-07-29 | 46% | 3802 | FY 10 Duluth, FY11 Osan | 2853 Reprogramming
2014-10-31 | 2012 | DLA Defense Supply Center Philadelphia | Major Military Construction | PENNSYLVANIA | UNITED STATES | DSCP1201 | Upgrade HVAC System - Philadelphia | 2012-03-28 | 2012-06-01 | WU & Associates, Inc | N40085-10-D-9451 | 4775 | 7240 | 2012-06-14 | 2014-04-29 | 2013-07-17 | 2014-06-06 | 99%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | SOUTH CAROLINA | UNITED STATES | DESC1101 | Replace Fuel Storage Facility - Charleston AFB | 2012-01-09 | 2012-09-28 | MEB General Contractors Inc. | N694501-12-C-1757 | 26700 | 26485 | 2012-11-30 | 2014-12-30 | 2014-07-21 | 2014-11-26 | 90% | 5132 | FY10 Pt Loma, FY12 JB PH-Hickam & Barksdale | 2853 Reprogrammin
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1004 | Replace Hydrant Fuel System - McChord AFB | 2011-10-28 | 2012-02-02 | Garco Construction, Inc. | W912DW-12-C-0016 | 10217 | 10660 | 2012-02-27 | 2013-09-24 | 2013-05-17 | 2013-09-30 | 100%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1104 | Replace Fuel Pipeline - Whidbey Island | 2012-03-20 | 2013-02-28 | Talon Industries Inc. | N44255-13-C-4005 | 16984 | 17506 | 2013-02-28 | 2014-08-01 | 2014-08-30 | 2014-11-05 | 100%
2014-10-31 | 2012 | DLA Defense Energy Support Center | Major Military Construction | WEST VIRGINIA | UNITED STATES | DESC12S1 | Replace Hydrant Fuel System - Camp Dawson | 2012-04-26 | 2012-07-05 | Kinley Construction Company | W9128F-10D-0052 | 1930 | 1945 | 2012-07-03 | 2015-04-13 | 2013-12-05 | 2014-04-30 | 99%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | ARIZONA | UNITED STATES | DESC13S4 | Replace Truck Unload Facility - Yuma | 2012-11-01 | 2013-08-08 | Richard Brady & Associates, Inc. | N62473-13-C-4612 | 1322 | 1322 | 2013-09-30 | 2015-08-04 | 2014-08-03 | 2015-08-03 | 6% | 400 | FY12 Eielson | 2853 Reprogramming
2014-10-31 | 2013 | DLA Defense Reutilization and Marketing Service | Unspecified Minor Military Construction | CALIFORNIA | UNITED STATES | DRMS12U2 | Warehouse 6 Distribution - Tracy | 2013-05-01 | 2013-05-15 | Kinley Construction Company | W91238-10-D0036 | 925 | 925 | 2013-06-01 | 2014-10-18 | 2013-12-05 | 2013-12-25 | 100%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC1304 | Replace Fuel Storage - Edwards AFB | 2013-05-23 | 2013-09-27 | Nova Group Inc. | W912PL-13-C-0012 | 19513 | 19661 | 2013-11-20 | 2017-03-17 | 2016-10-18 | 2017-12-07 | 26%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC 1306 | Replace Fuel Pier - Pt Loma | 2013-06-20 | 2013-09-30 | Nova Shimmick Joint Venture | N62473-13-C-4215 | 66378 | 66378 | 2014-01-15 | 2017-10-14 | 2017-10-14 | 2017-10-15 | 20%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | DELAWARE | UNITED STATES | DESC1305 | Replace Truck Off-Load Facility - Dover AFB | 2013-07-31 | 2013-09-26 | Reliable Contracting Group, LLC | W9128F-09-R-0083 | 1800 | 1800 | 2013-12-06 | 2015-04-28 | 2015-02-27 | 2015-04-28 | 7%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1391 | Construct Fuel Storage Facility - Hurlburt AFB | 2013-01-13 | 2013-08-01 | Nova Group Inc | W91278-13-C1001 | 15952 | 15952 | 2013-10-31 | 2015-12-15 | 2015-09-14 | 2015-12-15 | 38%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC1203 | Replace Fuel Pier - GTMO | 2013-08-23 | 2013-10-03 | URS Group | N62742-09-D-1174 | 36366 | 36366 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 21%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction |  | GUANTANAMO BAY NAVAL BASE | DESC13S3 | Replace Truck Loading Facility - GTMO | 2013-08-23 | 2013-10-03 | URS Group | N69450-13-C1260 | 1961 | 1961 | 2013-10-28 | 2015-09-28 | 2015-10-28 | 2015-10-28 | 20%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | GUAM | GUAM | DESC1303 | Upgrade Fuel Pipeline - Andersen AFB | 2013-06-20 | 2013-12-21 | Nova Underground Joint Venture | N40192-14-C-1300 | 4311 | 4311 | 2013-09-09 | 2015-02-26 | 2015-02-26 | 2015-02-26 | 66%
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | LOUISIANA | UNITED STATES | DESC1390 | Upgrade Pumphouse - Barksdale AFB | 2012-10-30 | 2013-08-13 | Environmental Management Resources | N69450-10-D-0787
2014-10-31 | 2013 | DLA Defense Energy Support Center | Major Military Construction | NORTH CAROLINA | UNITED STATES | DESC13S1 | Replace Transfer Fuel Line to Pump House #2 - Seymour Johnson | 2013-02-27 | 2013-07-09 | Shaw Environmental & Infrastructure, Inc | W9128F-10-D-0073 | 1494 | 1542 | 2013-07-25 | 2014-10-13 | 2014-04-18 | 2014-11-09 | 95%
2014-10-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1301 | Replace Communications Building - New Cumberland | 2014-04-16 | 2014-09-19 | Orocon - Carothers JV2 | W912DR-14-C-0035 | 6800 | 6800 | 2014-10-10 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 0%
2014-10-31 | 2013 | DLA Defense Distribution Center | Major Military Construction | PENNSYLVANIA | UNITED STATES | DDCX1303 | Replace Sewage Treatment Plant - New Cumberland | 2013-08-01 | 2014-06-27 | Johnston Construction Company | W912DR-14-C-0029 | 9600 | 9600 | 2014-07-28 | 2016-03-06 | 2016-01-21 | 2016-01-04 | 1% | 5000 | FY10 Pt Loma, GTMO & Souda Bay; FY11 Pt Loma | 2853 Reprogramming
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | CALIFORNIA | UNITED STATES | DESC14U1 | Upgrades to Fuel Pier for Fire Protection - Pt Loma | 2014-06-01 | 2014-07-01 | CB&I Federal Services LLC | N62583-09-D-0130 TO-027 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0%
2014-10-31 | 2014 | DLA Defense Distribution Center | Major Military Construction | CALIFORNIA | UNITED STATES | DDCX1404 | General Purpose Warehouse - Tracy | 2014-06-23 | 2014-09-05 | Gilbane Federal | W91238-14-C-0049 | 1994 | 1994 | 2014-06-30 | 2016-04-04 | 2015-11-15 | 2016-06-03 | 0%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC11U2 | Replace Ground Vehicle Fueling Facility - Panama City | 2014-03-28 | 2014-04-24 | Gelbane Federal | N62583-09-D-0129 | 1994 | 1994 | 2014-06-30 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 2%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | FLORIDA | UNITED STATES | DESC1402 | [5 empty] | 5438 | 5438 | 2014-06-30 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 1%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC1504 | Upgrade Fuel Island - Hunter AAF | 2014-06-10 | 2014-09-05 | Nova Group Inc. Underground Construction | W912HN-14-C-0001 | 13407 | 13407 | 2014-09-19 | 2016-03-12 | 2016-03-12 | 2016-03-11 | 0%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | GEORGIA | UNITED STATES | DESC14S2 | Replace Ground Vehicle Fueling Facility - Moody AFB | 2014-03-18 | 2014-04-14 | Pond Constructors Inc | W9128F-14-D-0051 | 3780 | 3780 | 2014-05-15 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 6% |  |  | Additional Funds from FY12 Eielson
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction |  | JAPAN | DESC11U2 | Replace Ground Vehicle Fueling Facility - Atsugi | 2014-05-02 | 2014-07-29 | Ichibo Co. Ltd | W912HV-14-C-0002 | 1994 | 1994 | 2014-09-12 | 2015-11-15 | 2015-11-15 | 2015-11-15 | 0%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NEW JERSEY | UNITED STATES | DESC1501 | Replace Fuel Distribution Componenets, JB McGurie Dix Lakehurst | 2014-07-08 | 2014-09-30 | Eastern Construction & Electric | W912DS-14-C-0030 | 8637 | 8637 | 2014-10-30 | 2016-06-15 | 2016-06-15 | 2016-06-16 | 0%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | NORTH DAKOTA | UNITED STATES | DESC1107 | Replace Fuel Pipeline - Minot AFB | 2014-02-28 | 2014-06-13 | Reliable Contracting Group, LLC | W9128F-14-C-0013 | 4092 | 4092 | 2014-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 0%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1561 | Replace Refueler Parking, Altus AFB | 2014-03-10 | 2014-06-12 | Rockford Corporation | W9128F-10-D-0050 | 1917 | 1917 | 2014-07-11 | 2015-09-17 | 2015-09-17 | 2015-09-17 | 0%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | OKLAHOMA | UNITED STATES | DESC1502 | Replace Fuel Distribution Facilities, Tinker AFB | 2014-06-09 | 2014-10-21 | Nova Group Inc. | W912BV-15-C-0070 | 32060 | 32060 | 2014-12-01 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 0%
2014-10-31 | 2014 | DLA Defense Energy Support Center | Major Military Construction | WASHINGTON | UNITED STATES | DESC1405 | Replace Fuel Pier Breakwater, Whidbey Island | 2014-07-09 | 2014-09-30 | Manson Construction Co. | N44255-14-D-9004 | 8749 | 8749 | 2014-11-30 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 0%
2014-10-31 | 2007 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | DSO701 | Replace Ft Knox High School | 2007-04-03 | 2007-08-31 | BartonMarlow Company | W912QR-07-C-0059 / 2593359 | 16050 | 16149.241 | 2007-09-17 | 2009-10-08 | 2009-03-10 | 2009-12-04 | 99%
2014-10-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR826708 | FY10 DoDDS EUR826708 Kaiserslautern High School | 2012-03-02 |  | Federal Republic of Germany | W912GB-12-C-0008 / 17387653 | 70600.7618 | 70600.7618 |  |  |  |  | 0%
2014-10-31 | 2010 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM 856 07 | New Elementary School | 2011-02-25 | 2011-06-03 | Sauer, Inc. d/b/a Sauer Southeast | W91278-07-D-0030 / 16648126 | 19764 | 20538.226 | 2012-08-01 | 2014-08-01 | 2013-12-14 | 2014-08-08 | 98%
2014-10-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8197 02 | Multi-Purpose Room, Bus Area & Sports Fields (Kaiserslautern Complex) | 2010-09-27 | 2011-03-15 | LBB Kaiserslautern | W912GB-08-C-0046 / 14328568 | 15509.459 | 17705.0096 | 2011-05-09 | 2013-09-13 | 2013-01-19 | 2013-09-25 | 99%
2014-10-31 | 2010 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8320 03 | Replace School (Boblingen ES) | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 17287571 | 46694.9233 | 48009.6099 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 50%
2014-10-31 | [7 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 36343223 | 0 | 513.9133 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 50%
2014-10-31 | [7 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0014 / 40873377 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-30 | 50%
2014-10-31 | 2010 | DoD Education Activity | Major Military Construction |  | BELGIUM | EUR 8318 09 | Replace School (SHAPE ES) | 2011-07-07 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238110 | 31414.6336 | 32686.4652 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 95%
2014-10-31 | [7 empty] | 2011-07-07 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36147376 | 1652.1853 | 1719.1947 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
2014-10-31 | 2011 | DoD Education Activity | Major Military Construction |  | GERMANY | EUR 8268 02 | Replace School ( Boblingen HS) | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 24348244 | 41869.3221 | 43498.3308 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 46%
2014-10-31 | [7 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 40873376 | 0 | 0 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 46%
2014-10-31 | [7 empty] | 2013-03-11 | 2013-07-15 | Staatliches Hochbauamt Reutlingen | W912GB-10-C-0015 / 43326728 | 0 | 292.8744 | 2013-07-29 |  | 2015-04-30 | 2015-06-29 | 46%
2014-10-31 | 2011 | DoD Education Activity | Major Military Construction | NEW YORK | UNITED STATES | AM2455205 | Construct Addition and Renovate West Point MS | 2011-07-18 | 2011-10-20 | Bernard Associates | W912DS-12-C-0001 / 25312318 | 23974 | 26098 | 2011-11-28 | 2014-03-17 | 2014-09-28 | 2014-03-17 | 99%
2014-10-31 | 2011 | DoD Education Activity | Major Military Construction |  | BELGIUM | D9124-1 | Replace Schools (SHAPE MS/HS) | 2012-04-18 | 2011-12-09 | Besix SA | W912GB-12-C-0001 / 18238151 | 26260 | 26929 | 2012-01-18 | 2014-07-04 | 2014-04-17 | 2014-07-04 | 95%
2014-10-31 | [7 empty] | 2012-04-18 | 2012-06-18 | Wayss & Freytag Ingenieurbal | W912GB-11-D-0035 / 36069514 | 5843 | 6002 | 2012-07-05 | 2012-12-05 | 2015-07-23 | 2013-01-04 | 95%
2014-10-31 | [7 empty] | 2012-04-18 | 2012-07-20 | association besix-cmc jv | W912GB-12-C-0013 / 33888490 | 28674 | 28774 | 2012-08-01 |  | 2015-01-13 | 2014-12-19 | 83%
2014-10-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM8193 01 | Replace Elementary School (Antilles ES) | 2012-03-16 | 2012-06-12 | Gilbane Building Company | W912EP-12-C-0015 / 21176983 | 50968 | 51394 | 2012-07-18 |  | 2014-04-19 | 2015-04-30 | 50%
2014-10-31 | 2011 | DoD Education Activity | Major Military Construction | VIRGINIA | UNITED STATES | AM2455206 | Replace/Consolidate Elementary Schools | 2012-06-29 | 2012-09-29 | Homeland Contracting Corp. | N4008012C0007 | 42297 | 43397 | 2012-09-29 |  | 2014-09-30 | 2015-06-01 | 78%
2014-10-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM100801 | Replace Elementary School (Murray ES) | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121826 | 14851 | 16356 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 98%
2014-10-31 | 2011 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AMD02051 | Replace Elementary School ( McNair ES) | 2012-05-24 | 2012-08-15 | Brasfield & Gorrie, LLC | W912HN-10-D-0046 / 21121890 | 16413 | 17049 | 2012-09-12 | 2014-08-25 | 2014-04-03 | 2014-07-15 | 98%
2014-10-31 | 2012 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00019 | OTH PA00019 Replace Temp Classroom Bldg, JK Mendel ES, Yokota AB | 2012-10-26 | 2013-02-27 | Hibiya Engineering, Ltd. | W912HV-13-C-0002 / 29312081 | 9644 | 9719 | 2013-03-26 |  | 2015-07-25 | 2015-10-18 | 87%
2014-10-31 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00053 | Replace Elementary/Middle School (Ansbach EMS) | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 42039612 | 575 | 575 | 2013-10-28 |  | 2015-03-12 | 2015-05-29 | 22%
2014-10-31 | [7 empty] | 2013-06-07 | 2013-09-26 | Staatliches Hochbauamt Nurnberg II | W912GB-11-C-0025 / 27244046 | 11783.7717 | 11831.8322 | 2013-10-28 |  | 2015-03-12 | 2015-05-29 | 22%
2014-10-31 | 2012 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00020 | Replace Elementary School (Osan ES) | 2013-06-07 | 2013-09-30 | Ilsung Construction Co., Ltd. | W912UM-13-C-0031 / 32048435 | 29187 | 29764 | 2013-09-30 |  | 2015-12-09 | 2015-03-01 | 16%
2014-10-31 | 2013 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00023 | Replace McBride Elementary School | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 27629446 | 32987 | 32987 | 2013-12-11 |  | 2015-12-11 | 2016-01-18 | 15%
2014-10-31 | [7 empty] | 2013-03-14 | 2013-11-08 | Caddell Construction CO., INC | W912HN-10-D-0044 / 42130927 | 0 | 0 | 2013-12-11 |  | 2015-12-11 | 2016-01-18 | 15%
2014-10-31 | 2013 | DoD Education Activity | Major Military Construction | MASSACHUSETTS | UNITED STATES | AM00027 | Replace Hanscom Middle School | 2012-10-31 | 2013-12-20 | J&J Contractors & Engineers, Inc. | W912WJ-14-C-0007 / 27163388 | 31687 | 31994 | 2014-02-11 |  | 2016-04-21 | 2016-08-19 | 17%
2014-10-31 | 2013 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00028 | Replace Barkley Elementary School | 2013-03-14 | 2013-11-27 | SBH Services & CORE Construction JV II, of Gallatin, Tennessee | W912QR-14-C-0001 / 33717591 | 39362 | 39371 | 2014-03-27 |  | 2015-12-17 | 2016-03-15 | 7%
2014-10-31 | 2012 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00026 | Replace Kingsolver/Pierce School | 2013-03-04 | 2014-02-21 | AWA Wilson JV | W912QR-14-C-0010 / 26828267 | 32685 | 32828 | 2014-03-11 |  | 2015-11-11 | 2016-01-30 | 6%
2014-10-31 | 2013 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00043 | Replace Wiesbaden High School | 2014-09-30 | 2014-03-07 | Federal Republic of Germany | W912GB-12-C-0007 / 33867035 | 0 | 0 | 2014-03-24 | 2014-08-11 | 2014-08-21 | 2014-08-30 | 5%
2014-10-31 | [7 empty] | 2014-09-30 | 2014-06-20 | Federal Republic of Germany | W912GB-12-C-0007 / 33867015 | 662 | 662 | 2014-09-30 |  | 2014-12-02 | 2015-01-31 | 5%
2014-10-31 | [7 empty] | 2014-09-30 |  | Federal Republic of Germany | W912GB-12-C-0007 / 33866995 | 48926.0169 | 48954.4549 |  |  | 2017-04-22 | 2017-05-22 | 0%
2014-10-31 | 2012 | DoD Education Activity | Major Military Construction | NORTH CAROLINA | UNITED STATES | AM00025 | Replace Delalio Elementary School | 2013-04-04 | 2014-02-24 | United Builders Group/Sundt | N4008514C8409 | 23339 | 23372 | 2014-02-24 | 2016-06-01 | 2016-06-01 | 2017-05-20 | 21% |  |  | The occupancy date 1 Jun 16 is for the BOD of the school. This is the completion of Phase 1 of the project. The school can be occupied at this time. The 20 May 17 date is the completion of Phase 2, which includes demo of the old school, construction of the bus loop, parking lot, and misc sitework items in the footprint of the school. The entire contract will be completed in May 17.
2014-10-31 | 2013 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00033 | Replace Bob Hope & Amelia Earhart Elementary School | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004/32154717 | 1475 | 1475 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0%
2014-10-31 | [7 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853644 | 2469 | 2469 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0%
2014-10-31 | [7 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853642 | 4612 | 4612 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0%
2014-10-31 | [7 empty] | 2013-06-13 | 2014-06-18 | TOA Gilbane JV | W912HV-14-C-0004 / 44853645 | 62418 | 62418 | 2014-07-07 |  | 2016-10-24 | 2017-01-01 | 0%
2014-10-31 | 2012 | DoD Education Activity | Major Military Construction |  | GERMANY | EU00062 | Netzaberg Middle School Addition | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/44939183 | 283 | 283 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 16%
2014-10-31 | [7 empty] | 2014-03-19 | 2014-05-21 | Bauamnt Amberg-Sulzbach | W912GB-11-C-0022/27240065 | 5366 | 5401 | 2014-06-05 |  | 2015-09-26 | 2015-11-10 | 16%
2014-10-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00024 | Faith Middle School Addition | 2014-06-19 | 2014-08-23 | Team Construction LLC A JV of Mil Fed/WT | W912HN-10-D-0068/30272172 | 4897 | 4897 |  |  | 2016-01-21 | 2016-01-21 | 0%
2014-10-31 | 2014 | DoD Education Activity | Major Military Construction | KENTUCKY | UNITED STATES | AM00040 | Replace Marshall Elementary School | 2014-05-08 | 2014-07-17 | Walsh Federal JV | W912QR-14-C-0025/33717848 | 34748 | 34773 | 2014-08-06 |  | 2016-03-28 | 2016-05-27 | 5%
2014-10-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00038 | Diamond Elementary School Replacement | 2014-07-22 | 2014-09-10 | Archer Western Contractors LLC | W91278-11-D-0073/34282229 | 40073 | 40073 |  |  | 2016-09-14 | 2016-09-14 | 0%
2014-10-31 | 2014 | DoD Education Activity | Major Military Construction |  | KOREA, SOUTH | PA00018 | Daegu Middle/High School Replacement | 2014-08-01 | 2014-09-26 | eTEC Engr. & Const. Ltd | W912UM-14-C-0027/35411026 | 28954 | 28954 | 2014-09-29 |  | 2016-10-03 | 2016-12-10 | 0%
2014-10-31 | 2014 | DoD Education Activity | Major Military Construction |  | JAPAN | PA00030 | Replace Zukeran Elementary School | 2013-06-19 | 2014-09-26 | Obayashi Corporation | W912HV-14-C-0015/25756668 | 95476 | 95476 | 2014-10-23 |  | 2016-11-22 | 2017-02-10 | 0%
2014-10-31 | 2014 | DoD Education Activity | Major Military Construction | GEORGIA | UNITED STATES | AM00050 | White Elementary School Replacement | 2014-06-19 | 2014-09-27 | Carothers Construction Inc | W91278-12-D-0037/30329012 | 31791 | 31791 |  |  | 2016-08-26 | 2016-08-26 | 0%
2014-10-31 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P646 | DSS Headquarters Addition | 2012-09-21 | 2013-03-29 | Hensel Phelps Construction Co. |  | 25149 | 28248 | 2013-04-30 | 2014-09-26 | 2014-07-22 | 2014-09-25 | 99% |  |  | [Solicitation/Advertise Date: Phase I - 21-Sep-2012 Phase II - 20-Dec-2012]
2014-10-31 | 2012 | Defense Security Service | Major Military Construction | VIRGINIA | UNITED STATES | P659 | Defense Access Road Improvements-Telegraph Rd | 2013-01-22 | 2013-07-15 | Shirley Contracting Company, LLC |  | 2967 | 2967 | 2013-08-01 |  | 2014-08-01 | 2014-12-19 | 72% |  |  | This project is being managed and funded via FHWA. [Solicitation/Advertise Date: Phase I - 22-Jan-2013 Phase II - 04-Apr-2013]
2014-10-31 | 2009 | Missile Defense Agency | Unspecified Minor Military Construction |  | TURKEY | 638 | European Phased Adaptive Approach, Phase I Radar Site | 2011-09-15 | 2011-10-19 | EMTA INSAAT TAAHUT VE TICARET A.S. | W912GB-09-D-0069 | 1885 | 1900 | 2011-10-26 | 2013-10-28 | 2011-12-31 | 2013-11-15 | 100%
2014-10-31 | 2009 | Missile Defense Agency | Unspecified Minor Military Construction | ALASKA | UNITED STATES | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | W911KB-10-D-0004 | 1564 | 1207 | 2013-03-22 | 2013-07-03 | 2013-06-30 | 2013-07-03 | 100%
2014-10-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction | ALASKA | UNITED STATES | 647 | Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping | 2013-02-01 | 2013-03-21 | Marsh Creek, LLC | W911KB-10-D-0004 | 1564 | 243 | 2013-03-22 | 2013-07-03 | 2013-06-30 | 2013-07-03 | 100%
2014-10-31 | 2010 | Missile Defense Agency | Unspecified Minor Military Construction |  | MARSHALL ISLANDS | 655 | Missile Test Vehicle Storage Facility | 2014-03-24 | 2014-05-09 | Arctic Slope Regional Corporation (ASRC) | W912DY-14-D-0042-0001 | 1832 | 1832 | 2014-06-17 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 66%
2014-10-31 | 2010 | Missile Defense Agency | Major Military Construction | VIRGINIA | UNITED STATES | 609 | Aegis BMD Facility Expansion | 2010-03-23 | 2010-06-30 | Sauer Incorporated | N40080-10D-0490 | 18813 | 18748 | 2010-07-15 | 2012-10-12 | 2012-10-31 | 2012-10-31 | 100% | 5700 | P&D Funds | Reprogrammed to P&D for AAMDSC, Romania project
2014-10-31 | 2010 | Missile Defense Agency | Major Military Construction | HAWAII | UNITED STATES | 627 | Aegis Ashore Missile Defense Test Complex | 2011-06-30 | 2011-08-03 | TOMCO CORP. | N62478-10-D-4024 | 294 | 294 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-11-18 | 100% |  |  | Clearing and Grubbing Only
2014-10-31 | [7 empty] | 2012-01-19 | 2012-06-04 | URS GROUP, INC | N62742-09-D-1174 | 59616 | 69657 | 2012-07-04 | 2013-08-29 | 2013-09-12 | 2013-11-07 | 100% |  |  | GMAC Construction - awaiting Interim 1354; Placed-in-Service date is estimated
2014-10-31 | 2012 | Missile Defense Agency | Major Military Construction | ALABAMA | UNITED STATES | 633 | Von Braun Complex Phase IV | 2012-02-06 | 2012-06-18 | Universal Construction Co., Inc. d/b/a Turner Universal | W91278-12-C-0017 | 51330 | 59842 | 2012-07-10 | 2014-06-26 | 2014-07-10 | 2014-10-15 | 100%
2014-10-31 | 2013 | Missile Defense Agency | Major Military Construction | NEW YORK | UNITED STATES | 639 | In-Flight Interceptor Data Terminal Complex | 2013-03-14 | 2013-06-07 | Black Horse Group, LLC | W912DS-09-D-0004 | 12584 | 15270 | 2013-08-10 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 90% |  |  | Awaiting Interim 1354; Placed-in-Service date is estimated
2014-10-31 | 2013 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 630 | Aegis Ashore Missile Defense System Complex, Incr #1 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 81785 | 2013-07-31 | 2015-02-13 | 2015-08-30 | 2015-09-20 | 45% |  |  | Asset Identifier is pending as this is a new Installation; awaiting Interim 1354; Placed-in-Service date is estimated
2014-10-31 | 2014 | Missile Defense Agency | Major Military Construction |  | ROMANIA | 636 | Aegis Ashore Missile Defense System Complex, Incr #2 | 2013-02-08 | 2013-07-09 | Kellogg Brown & Root Services, Inc, | W912GB-13-R-0003 | 118300 | 28946 | 2013-07-31 | 2015-02-13 | 2015-08-30 | 2015-09-20 | 45% |  |  | Asset Identifier is pending as this is a new Installation; awaiting Interim 1354; Placed-in-Service date is estimated
2014-10-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 634 | BMDS Upgrade Early Warning Radar (UEWR) | 2014-01-22 | 2014-04-04 | Alutiiq General Contractor, LLC | W911KB-14-C-0011 | 13300 | 13300 | 2014-07-07 | 2016-01-06 | 2017-05-31 | 2017-05-31 | 19% |  |  | Awaiting Interim 1354; Placed-in-Service date is estimated
2014-10-31 | 2014 | Missile Defense Agency | Major Military Construction |  | JAPAN | 648 | AN/TPY-2 Radar Site | 2014-02-21 | 2014-05-02 | MIRAIT.T-ACTY J.V. | W912HV-14-D-0005 | 12991 | 12991 | 2014-05-27 | 2015-01-09 | 2015-01-09 | 2015-01-09 | 72% |  |  | Asset Identifier is pending as this is a new Installation; awaiting Interim 1354; Placed-in-Service date is estimated
2014-10-31 | 2014 | Missile Defense Agency | Major Military Construction | ALASKA | UNITED STATES | 649 | Mechanical-Electrical Building (MEB) Missile Field 1 (MF1) | 2014-01-23 | 2014-05-16 | Watterson Construction Company | W911KB-14-R-0008 | 42838 | 42838 | 2014-05-27 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 5% |  |  | Awaiting Interim 1354; Placed-in-Service date is estimated
2014-10-31 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | MISSOURI | UNITED STATES | NGA021 | Data Ctr West #1 Power & Cooling Upgrade | 2012-04-19 | 2012-07-05 | Facility Defense Consultants d/b/a Hanke Constructors |  | 8202 | 11198 | 2012-08-06 | 2014-01-21 | 2013-08-06 | 2014-12-30 | 99%
2014-10-31 | 2012 | National Geospatial-Intelligence Agency | Major Military Construction | VIRGINIA | UNITED STATES | NGA013 | Technology Center Third Floor Fit-out | 2012-06-05 | 2012-09-24 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 32387 | 39495 | 2012-11-02 | 2014-05-30 | 2014-01-02 | 2015-01-16 | 99% | 1975 | NGA021
2014-10-31 | 2007 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES |  | Infrastructure Increments 1-3; NGA HQ's | [7 empty] | 2011-09-15 | 2013-06-15 | 2014-12-31 | 99% |  |  | Water tank & CDC infrastructure contract continues [Various Solicitation Date, Award Date, and Start Date.]
2014-10-31 | 2008 | National Geospatial-Intelligence Agency | Base Realignment and Closures | VIRGINIA | UNITED STATES | 65416 | NGA Headquarters, SCIF, All Phases | 2007-06-01 | 2007-08-10 | Clark/Balfour Beatty-NCE, A Joint Venture |  | 1181439 | 1398710 | 2007-09-06 | 2011-04-19 | 2011-12-22 | 2014-12-31 | 99% |  |  | Close-out efforts are on-going
2014-10-31 | 2009 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21120 | South Campus Electrical Utility Plant SCEUP (Phase 1) | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 12060 | 13760 | 2010-09-21 | 2013-01-17 | 2013-01-17 | 2014-04-18 | 99%
2014-10-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17872 | South Campus Electrical Utility Plant SCEUP (Phase 2) | 2010-05-03 | 2010-08-30 | Clark/McDean | W912DR-10-C-0033 | 113223 | 124647 | 2010-09-21 | 2014-05-13 | 2014-04-18 | 2014-12-15 | 92% | 37500 |  | Contract Completion date has not been negotiated yet
2014-10-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 21372 | NSAW Vehicle Entrance Barrier (VCP-6) | 2009-05-04 | 2010-08-26 | Goels/Grunley | W912DR-10-C-0035 | 4443 | 4544 | 2010-09-09 | 2012-06-29 | 2011-09-26 | 2012-06-29 | 100%
2014-10-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 25047 | NSAW Vehicle Entrance Barrier (VCP-2) | 2012-10-17 | 2013-02-19 | District Veterans Contracting | W912DR-13-C-0021 | 5253 | 5657 | 2013-03-07 | 2014-09-30 | 2014-03-07 | 2014-11-21 | 96.6%
2014-10-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17781 | Tordella Chilled Water Backup Storage | 2009-08-24 | 2010-06-24 | Northern Tiaga Venture, LLC Inc. (NTVI) | W912DR-10-C-0079 | 11700 | 11700 | 2010-06-30 | 2012-05-30 | 2011-08-20 | 2012-05-30 | 100%
2014-10-31 | 2010 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17782 | R&E Chilled Water Backup Storage | 2011-05-31 | 2011-08-30 | Walsh Construction Company | W912DR-11-C-0034 | 3200 | 3200 | 2011-11-07 | 2014-10-31 | 2013-07-13 | 2015-02-27 | 78%
2014-10-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18052 | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2011-03-15 | NPGL | MWHL10-3001 | 7566 | 8257 | 2011-03-31 | 2014-05-14 | 2013-02-01 | 2014-05-14 | 100%
2014-10-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18053 | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2012-02-15 | IUS | MWHL10-3001 | 16095 | 16448 | 2012-01-31 | 2014-05-31 | 2013-02-01 | 2014-05-31 | 100%
2014-10-31 | 2010 | National Security Agency | Major Military Construction |  | UNITED KINGDOM | 18054 | Power & Cooling Infrastructure Upgrade | 2010-03-01 | 2012-08-12 | Balfour Beaty Engineering Services | MWHL10-3001 | 7085 | 7316 | 2012-11-30 | 2014-08-31 | 2013-02-01 | 2014-08-31 | 92%
2014-10-31 | 2011 | National Security Agency | Major Military Construction | CLASSIFIED LOCATION | WORLDWIDE CLASSIFIED | 22573 | Classified location | 2012-08-15 | 2012-09-30 | Kaseman | NA | 12000 | 21500 | 2012-12-01 | 2013-10-01 | 2013-09-30 | 2014-03-15 | 99%
2014-10-31 | [7 empty] | 2012-08-01 | 2012-09-21 | Hardline | NA | 12000 | 12000 | 2012-09-25 | 2012-09-15 | 2013-04-04 | 2013-04-04 | 100%
2014-10-31 | [7 empty] | 2012-07-01 | 2012-07-30 | PAE | NA | 200 | 200 | 2012-08-15 | 2012-09-15 | 2012-08-30 | 2012-08-30 | 100%
2014-10-31 | 2011 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 17866 | North Campus Electrical Utility Plant (NCEUP) | 2011-06-10 | 2011-09-16 | Hensel Phelps Construction Company | W912DR-11-C-0036 | 125900 | 132254 | 2011-10-04 | 2014-11-30 | 2014-11-30 | 2015-01-16 | 98% | 50100 | Mountainview
2014-10-31 | 2011 | National Security Agency | Major Military Construction | GEORGIA | UNITED STATES | 20489 | MOD II | 2011-12-23 | 2013-06-01 | Brantley Co. | W912HN-10-D-0056 | 7657 | 8867 | 2012-05-30 | 2014-03-03 | 2014-01-30 | 2015-01-16 | 100%
2014-10-31 | [6 empty] | MOD II (Phase 2) | 2013-10-07 | 2013-11-20 | Brantley Co. | W912HN-10-D-0056 | 2620 | 2657 | 2013-11-26 | 2014-09-30 | 2014-02-28 | 2014-04-28 | 98%
2014-10-31 | [6 empty] | Whitelaw Wedge | 2012-04-26 | 2012-06-18 | JAAT | W912HN-10-D-0063 | 15315 | 16526 | 2012-07-18 | 2014-07-09 | 30-Ja n-14 | 2014-10-23 | 95%
2014-10-31 | 2012 | National Security Agency | Major Military Construction | COLORADO | UNITED STATES | 23051 | Mountainview | 2012-02-17 | 2012-09-26 | Hensel Phelps Construction Company | W912DR-12-C-0019 | 116975 | 125035 | 2012-11-02 | 2015-07-22 | 2015-05-03 | 2015-05-26 | 78%
2014-10-31 | [6 empty] | Mountainview | 2012-02-14 | 2013-09-29 | Xcel Power Feed | W912DR-12-F-0081 | 5621 | 5621 | 2013-10-13 |  | 2014-02-14 | 2015-09-30 | 100%
2014-10-31 | 2012 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 24649 | High Performance Computing Center 2 | 2012-05-01 | 2013-02-26 | Hensel Phelps/Kiewit Joint Venture | W912DR-13-C-0005 | 564589 | 591254 | 2013-03-12 | 2015-09-30 | 2015-09-16 | 2015-09-30 | 62%
2014-10-31 | 2013 | National Security Agency | Major Military Construction | MARYLAND | UNITED STATES | 26170 | East Campus Building 1 | 2009-12-18 | 2010-09-24 | Walsh Federal, LLC | W912DR-13-C-0038 | 91866 | 92192 | 2013-10-24 | 2016-01-05 | 2015-10-16 | 2015-10-16 | 10%
2014-10-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | 61772 | Operations Complex | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30155148 | 16751 | 17554.9517 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 98%
2014-10-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033003 | Vehicle Maintenance Facility | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30136034 | 4575 | 5123.2845 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 98%
2014-10-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033005 | Storage Facility | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154837 | 3603 | 3766.2116 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 98%
2014-10-31 | 2008 | Special Operations Command | Major Military Construction |  | QATAR | AFSOC033019 | Air Operations Center | 2011-05-12 | 2012-01-04 | Contrack International, Inc. | W912ER-12-C-0011 / 30154494 | 2931 | 3078.5666 | 2012-01-31 | 2014-10-30 | 2013-04-24 | 2014-09-01 | 98%
2014-10-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 64484 | Operations Additions | 2012-03-21 | 2011-07-21 | Pacific Tech Sauer J.V. | W912HN-11-C-0010 / 29379991 | 13388 | 15184.2497 | 2011-08-25 | 2015-05-08 | 2014-06-10 | 2014-12-09 | 89%
2014-10-31 | 2011 | Special Operations Command | Major Military Construction | GEORGIA | UNITED STATES | 65395 | Company Support Facility | 2011-06-27 | 2011-09-19 | JAAAT Technical Services, LLC | W912HN-10-D-0057 / 22193150 | 15391.578 | 15637.173 | 2011-12-27 | 2014-07-31 | 2013-06-12 | 2014-07-31 | 98%
2014-10-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 66362 | C4 Facility - JSOC | 2011-04-08 | 2012-05-30 | Western Contractors, LLC | W912HN-12-C-0009 / 29381338 | 41446 | 44322.4218 | 2012-06-14 | 2015-05-05 | 2014-06-26 | 2014-11-06 | 99%
2014-10-31 | 2011 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69573 | Admin/Company Operations | 2010-09-08 | 2011-09-26 | R.C. Construction Co., Inc. | W912HN-10-D-0058 / 29381912 | 8487 | 9166 | 2011-10-27 | 2013-11-21 | 2013-04-18 | 2014-01-23 | 99%
2014-10-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063049 | Hangar / AMU (MC-130J) | 2011-05-13 | 2011-09-09 | Speegle Construction | W912PP-11-C-0029 / 30594756 | 19432 | 20310.9637 | 2011-10-11 | 2014-05-09 | 2013-10-30 | 2014-05-15 | 99%
2014-10-31 | 2011 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ063052A | Operations & Training Complex (3rd UAS) | 2011-04-15 | 2011-10-26 | Speegle Construction | W912PP-12-C-0003 / 30509923 | 13613.73 | 13723.6304 | 2012-09-06 | 2014-06-03 | 2013-07-17 | 2014-06-03 | 99% | 7132 | 66362
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60272 | Communications Training Complex (SWCS) | 2012-04-11 | 2012-07-24 | GSC Construction, Inc. | W912HN-10-D-0049 / 29371639 | 8290.317 | 8469.8948 | 2012-09-12 | 2015-01-05 | 2013-08-23 | 2014-10-31 | 87%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 60821 | Squadron Headquarters Addition | 2012-02-02 | 2012-04-27 | Tyler Construction Group, Inc. | W912HN-10-D-0060 / 29389201 | 10605 | 10909.0208 | 2012-06-06 | 2014-12-09 | 2013-12-09 | 2014-10-10 | 86%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66598 | Rotary Wing Hangar | 2011-11-28 | 2012-03-30 | Caddell/Whitesell-Green, a Joint Venture | W912QR-12-C-0020 / 28424662 | 34350 | 35203.168 | 2012-04-16 | 2014-11-14 | 2014-02-28 | 2014-10-31 | 93%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69458 | Battalion Operations Complex | 2012-05-01 | 2012-09-18 | Alutiiq Manufacturing Contractors, LLC | W912HN-10-D-0055 / 29389100 | 16772.305 | 16772.305 | 2012-12-10 | 2015-01-15 | 2014-06-03 | 2014-12-15 | 74%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69758 | Brigade Headquarters | 2012-05-09 | 2012-09-17 | JAAAT Technical Services, LLC | W912HN-10-D-0063 / 29372058 | 15649.974 | 16272.7394 | 2012-11-14 | 2015-05-09 | 2014-05-08 | 2015-03-10 | 42%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 71224 | Group Headquarters | 2012-06-06 | 2012-09-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 29371956 | 18525.847 | 18434.374 | 2012-11-07 | 2015-01-17 | 2014-06-20 | 2014-12-18 | 71%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | WASHINGTON | UNITED STATES | 76363 | Company Operations Facility | 2012-04-18 | 2012-08-30 | Adept-Absher 1 Joint Venture | W912DW-12-C-0037 / 27917342 | 18751 | 18626.363 | 2012-10-09 | 2014-06-21 | 2014-04-22 | 2014-06-20 | 99%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76364 | Battalion Operations Facility | 2012-06-20 | 2012-10-25 | Engineering Design Technologies, Inc. | W912HN-11-D-0002 / 41209106 | 32201.3031 | 31942.4871 | 2012-10-25 | 2015-06-01 | 2014-07-28 | 2015-01-08 | 70%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76366 | Company Operations Facility (GSTB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653126 | 14673.727 | 15674.302 | 2012-09-12 | 2016-04-26 | 2014-06-27 | 2016-01-27 | 75%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | 76371 | Company Operations Facility (GSB) | 2012-03-23 | 2012-07-24 | B.L. Harbert International, LLC | W91278-11-D-0068 / 36653120 | 17092.801 | 17142.71 | 2012-09-12 | 2016-04-26 | 2013-09-30 | 2016-01-27 | 75%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76373 | Administrative Annex | 2012-03-01 | 2012-06-21 | GSC Construction, Inc. | W912HN-10-D-0049 / 29372426 | 9771.161 | 11158.1058 | 2012-08-15 | 2014-10-31 | 2013-12-10 | 2014-09-29 | 99%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 76374 | MH-47 Hangar | 2011-11-28 | 2012-05-07 | Hensel Phelps Construction Co. | W912QR-12-C-0035 / 28427841 | 32450 | 33728.627 | 2012-05-22 | 2014-08-29 | 2014-03-23 | 2014-10-31 | 99%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073014 | SOF C-130 Sq Ops Facility | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 25127091 | 7413 | 7874.8241 | 2012-11-09 | 2014-07-11 | 2015-01-06 | 2014-08-10 | 99%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073018 | SOF C-130 Wash Rack Hangar | 2012-05-30 | 2012-08-27 | Solis Constructors, Inc. | W912PP-12-C-0025 / 30667913 | 9329 | 9714.6074 | 2012-11-16 | 2014-08-29 | 2014-07-18 | 2014-08-26 | 99%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ073021 | SOF AMXS Facility | 2012-04-12 | 2012-09-12 | K.L. House Construction CO | W912PP-12-C-0033 / 25138433 | 14700 | 14966.2684 | 2013-01-10 | 2014-09-22 | 2014-12-22 | 2014-09-19 | 99%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083012 | SOF Hangar/AMU | 2012-04-20 | 2012-08-31 | Hensel Phelps | W912PP-12-C-0027 / 30858121 | 28160 | 29105.547 | 2012-10-24 | 2015-01-05 | 2014-12-23 | 2014-09-07 | 98%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083016 | SOF Squadron Operations Facility | 2012-05-25 | 2012-10-26 | Bradbury Stamm Construction, Inc. | W912PP-13-C-0002 / 28791332 | 10615 | 11040 | 2012-11-09 | 2014-05-30 | 2015-01-06 | 2014-05-30 | 99% | 2293 | CZQZ063035
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV103011 | SOF Simulator Facility | 2012-05-01 | 2012-08-09 | Barlovento LLC. | W91278-10-D-0072 | 5551 | 5543 | 2012-09-13 | 2014-07-18 | 2013-12-24 | 2014-07-18 | 99%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1049 | Range 130 Support Projects | 2012-11-08 | 2013-02-06 | Reyes Construction, Inc | N6247309D1648 #0003 | 8129 | 8130 | 2013-06-03 | 2015-07-22 | 2014-11-13 | 2014-11-13 | 11%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-1174 | MWD Facility | 2012-05-21 | 2012-09-06 | Dimensions Construction, Inc. | N6247311D0068 #0003 | 3075 | 3302 | 2012-10-03 | 2014-11-14 | 2014-03-23 | 2014-11-14 | 67%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-164 | Logistics Support Facility | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 11727 | 11727 | 2012-12-09 | 2015-03-02 | 2014-07-24 | 2014-07-24 | 67%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-473 | SEAL Team Operations Facility | 2012-12-04 | 2013-09-27 | Hourigan Construction Corporation | N4008508D9738 #0005 | 23366 | 23366 | 2014-08-13 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 9%
2014-10-31 | 2012 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-504 | SOF Operational Vehicle Storage Facility (6UMC) | 2013-03-12 | 2013-05-23 | Richard Brady & Associates, Inc. | N4008511D6591 #0010 | 1660 | 1660 | 2013-12-03 | 2014-10-20 | 2014-10-20 | 2014-10-20 | 74%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | ALASKA | UNITED STATES | P-531 | Cold Weather Maritime Training Facility | 2012-04-30 | 2012-09-27 | Alutiiq Diversified Service, LLC | N4425512C3011 | 17449 | 17449 | 2014-03-04 | 2015-05-06 | 2015-04-15 | 2015-04-15 | 56%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-769 | Building Renovation | 2012-09-24 | 2012-12-19 | NOAH Enterprises, Inc. | N4008511D6590 #0007 | 3022 | 3441 | 2013-01-02 | 2014-08-27 | 2014-06-27 | 2014-06-27 | 81%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-826 | Military Working Dog Facility | 2012-08-01 | 2012-11-26 | Hourigan Construction Corp | N4008508D9738 #0002 | 4139 | 4139 | 2012-12-09 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 67%
2014-10-31 | 2012 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | TMKH043055 | SOF Training Facility | 2012-01-31 | 2012-04-24 | JAAAT Technical. Services, LLC | W912HN-10-D-0063 / 25189640 | 4773.799 | 4752.7374 | 2012-05-31 | 2014-10-29 | 2013-11-22 | 2014-10-19 | 99%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | ARIZONA | UNITED STATES | 53542 | Parachute Training Facility | 2014-05-22 | 2014-09-25 | Au Authum Ki, Inc | W912PL-14-C-0020 / 29636881 | 6546.92 | 6546.92 | 2014-11-09 | 2016-05-09 | 2016-05-09 | 2016-05-09 | 0%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 65052 | Medical Support Addition | 2013-08-06 | 2013-09-23 | SFL + A Architects, PA | W912HN-11-D-0003 / 33745717 | 3199.999 | 3283.4702 | 2013-10-16 | 2015-04-02 | 2015-08-25 | 2014-12-03 | 51%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 66597 | Landgraf Hangar Extension | 2013-06-10 | 2014-04-15 | FLW - TJC Joint Venture | W912QR-14-C-0019 / 33711891 | 3384.894 | 3384.894 | 2014-04-29 | 2015-11-20 | 2015-10-21 | 2015-10-21 | 8%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69287 | Battalion Operations Complex | 2013-06-03 | 2013-09-17 | Archer Western Contractors, LLC | W91278-11-D-0073 / 33746026 | 30907.435 | 30907.435 | 2013-10-09 | 2015-10-24 | 2015-05-13 | 2015-07-26 | 26%
2014-10-31 | [8 empty] | 2014-09-27 | Sauer Incorporated | W91278-11-D-0067 | 15404 | 15404 |  |  |  |  | 0%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69382 | Civil Affairs Battalion Complex | 2013-05-31 | 2013-09-27 | Caddell Construction CO. (DE), LLC | W91278-11-D-0066 / 33745841 | 25816 | 25816 | 2013-10-16 | 2014-12-15 | 2015-08-14 | 2014-12-15 | 28%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | KENTUCKY | UNITED STATES | 69447 | Group Support Battalion Detachment | 2013-06-13 | 2014-03-31 | United Builders Group-Sundt, A Joint Venture | W912QR-14-C-0016 / 33711787 | 22123.1802 | 22183.1802 | 2014-04-14 | 2016-04-13 | 2016-02-13 | 2016-02-13 | 7%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 69493 | Sustainment Bde Headquarters | 2013-06-27 | 2014-04-17 | Polote Corporation | W912HN-10-D-0061 / 33745939 | 23085 | 23085 | 2014-06-18 | 2016-10-14 | 2016-05-02 | 2016-05-02 | 3%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 76367 | SOF Battalion Operations Complex | 2013-07-18 | 2014-07-17 | Watts Constructors, LLC | W9128F-14-C-0024 / 34494853 | 36441 | 36461 |  | 2016-09-18 | 2016-06-16 | 2016-07-20 | 1%
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 79655 | SOF Training Facility (4UMC) | 2012-09-01 | 2013-06-18 | Daniels & Daniels Construction Co. Inc. | W912PM-13-C-0003 | 1592 | 1592 | 2013-06-18 | 2014-10-29 | 2014-10-15 | 2014-10-16 | 37%
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | 80233 | SOF Live-Fire Training Tower (6UMC) | 2013-06-16 | 2014-01-22 | Trend Construction, Inc. | W912HN-12-D-0030-DQ04 | 1531.7653 | 1531.7653 | 2014-02-12 | 2015-10-15 | 2015-05-15 | 2015-07-17 | 17%
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | COLORADO | UNITED STATES | 81483 | Mtn Climb/Rappel Tower (5UMC) | 2013-06-28 | 2013-09-11 | TIMUS - NASCO, JV | W9128F-13-C-0006 | 1513 | 1628 | 2013-09-20 | 2014-11-14 | 2014-10-15 | 2014-09-15 | 99%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | NEW MEXICO | UNITED STATES | CZQZ083013 | Combat Parking Apron | 2013-07-12 | 2014-05-22 | Okland Geneva Joint Venture | W912PP-14-C-0014 / 32077093 | 19481.9877 | 19476.9387 | 2014-06-13 | 2016-02-20 | 2015-08-13 | 2015-11-22 | 22%
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NEW MEXICO | UNITED STATES | CZQZ100221 | Parachute Drying Tower (3 UMC) | 2014-03-06 | 2014-07-01 | Speegle Construction | W912PP-14-C-0017 / 39136021 | 1547 | 1547 | 2014-07-28 | 2015-05-24 | 2015-05-24 | 2015-05-24 | 12%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTFA113004 | SOF AvFID Ops and MX Facilities | 2013-05-07 | 2013-09-20 | Carothers Construction Inc | W91278-12-D-0037 / 34392390 | 29942.3 | 29974.109 | 2013-11-05 | 2017-03-25 | 2016-12-01 | 2016-12-25 | 21%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | NVZR083702 | Joint Special Operations University Facility | 2013-07-03 | 2013-09-18 | W.G. Yates & Sons Construction Company | W91278-12-D-0040 / 30057576 | 24753.0246 | 24836.9926 | 2013-11-04 | 2015-09-26 | 2015-09-15 | 2015-06-28 | 17%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1218 | Marine Battalion Company/Team Facilities | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46370 | 2014-02-20 | 2016-01-18 | 2016-03-01 | 2016-01-18 | 24%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1393 | Survival Evasion Resistance Escape Trng Fac | 2013-06-11 | 2013-09-18 | RQ-DPR Construction Joint Venture | N4008513C6000 | 46370 | 46370 | 2014-02-20 | 2016-02-25 | 2016-01-18 | 2016-01-18 | 24%
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1410 | SOF EOD Expansion (1UMC) | 2013-09-04 | 2013-09-26 | Quadrant Construction, Inc | N4008510D0261 #0017 | 1566 | 1566 | 2013-10-15 | 2014-09-22 | 2014-09-22 | 2014-09-22 | 61%
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1450 | Fires Platoon Storage Facility (7UMC) | 2013-12-20 | 2014-02-13 | Quadrant Construction, Inc | N4008510D0261 #0019 | 1459.25 | 1459.25 | 2014-03-13 | 2014-12-10 | 2014-12-13 | 2014-12-10 | 17%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | VIRGINIA | UNITED STATES | P-165 | CS/CSS Support Facility | 2013-05-16 | 2013-09-24 | Leebcor Services LLC | N4008512D6304 #0003 | 9351 | 9344 | 2014-10-06 | 2015-11-27 | 2015-09-09 | 2015-11-26 | 14%
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Military Construction | VIRGINIA | UNITED STATES | P-564 | NSWG-4 Paraloft Addition (2UMC) | 2013-06-14 | 2013-09-27 | Royce Homeland JV, LLC | N4008512D6305 #0005 | 1308 | 1320 | 2013-10-15 | 2014-12-31 | 2014-12-31 | 2014-12-31 | 24%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-876 | Indoor Dynamic Shooting Facility |  | 2014-09-26 | RQ Construction | N6247310D5409 #0015 | 24290 | 24290 |  | 2016-10-01 | 2016-10-01 | 2016-10-01 | 0%
2014-10-31 | 2013 | Special Operations Command | Major Military Construction | CALIFORNIA | UNITED STATES | P-888 | Close Quarters Combat Range, Phase II |  | 2014-09-30 | K.O.O. Construction | N6247309D1655 #0005 | 12489 | 12489 |  | 2016-09-30 | 2016-09-30 | 2016-09-30 | 0%
2014-10-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 61064 | SOF Upgrade Training Facility | 2014-07-18 | 2014-10-06 | The Clement Group, LLC | W91278-11-D-0029-DQ02 A | 13951 | 13951 | 2014-11-17 | 2016-10-13 | 2016-08-18 | 2016-08-18 | 0%
2014-10-31 | 2014 | Special Operations Command | Major Military Construction | COLORADO | UNITED STATES | 69446 | Group Support Battalion Detachment | 2014-02-28 | 2014-07-24 | Federal Contracting Inc. dba Bryan Construction | W9128F-14-C-0030 / 39010820 | 15083.965 | 15083.965 |  | 2016-04-08 | 2016-02-18 | 2016-02-08 | 1%
2014-10-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 76375 | Civil Affairs Battalion Annexes | 2014-04-22 | 2014-09-29 | Carothers Construction, Inc. | W91278-11-D-0062-DQ01 | 27358 | 27358 | 2014-11-14 | 2016-08-08 | 2016-07-12 | 2016-07-12 | 0%
2014-10-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | 79438 | Combat Medic Skills Sustainment Course Bldg | 2014-04-02 | 2014-08-28 | The Clement Group, LLC | W91278-11-D-0029 / 38691146 | 7193.631 | 7193.631 |  | 2016-10-13 | 2016-08-01 | 2016-08-01 | 0%
2014-10-31 | 2014 | Special Operations Command | Major Military Construction | FLORIDA | UNITED STATES | FTEV083002 | Add/Alter Operations Facility | 2014-05-26 | 2014-07-30 | Barlovento, LLC | W91278-10-D-0072 / 45056975 | 7048.867 | 7048.867 |  | 2016-08-22 | 2016-08-03 | 2016-05-24 | 0%
2014-10-31 | 2014 | Special Operations Command | Major Military Construction | NORTH CAROLINA | UNITED STATES | P-1391 | SOF Sustainment Training Complex | 2014-05-29 | 2014-08-29 | DRP Hardin Construction - WGI Joint Venture Inc | N4008510D5333 #0004 | 27546.924 | 27546.924 |  | 2016-09-02 | 2016-09-02 | 2016-09-02 | 0%
2014-10-31 | 2014 | Special Operations Command | Unspecified Minor Military Construction | NORTH CAROLINA | UNITED STATES | P-1469 | MSOB Support Facilities | 2014-08-20 | 2014-09-30 | Quadrant Construction, Inc | N4008510D0261/0022 | 1751.362 | 1751.362 |  | 2015-10-14 | 2015-09-25 | 2015-09-25 | 0%
2014-10-31 | 2010 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Upgrade Electrical System | 2013-07-15 | 2013-09-30 | Portico - 8A and Dominion Virginia Power |  | 23269 | 23269 | 2013-11-07 | 2015-02-05 | 2015-02-05 | 2015-02-05 | 2% | 4719 | PERC-$437, Fuel Storage Fac-$200, Secondary UPS-$300, FY11 P&D-$3,782 | Design/Build - 100% design in progress
2014-10-31 | 2010 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Secondary UPS | 2010-06-16 | 2010-09-27 | Iron Bridge Construction |  | 5192 | 7515 | 2010-09-27 | 2013-07-31 | 2012-02-29 | 2014-07-30 | 99% | 0 |  | Closeout in progress
2014-10-31 | 2011 | Washington Headquarters Services | Major Military Construction | PENNSYLVANIA | UNITED STATES |  | Power Plant Modernization Phase 3 (WPP) | 2011-12-09 | 2013-04-09 | Grunley Construction Company, Inc. |  | 43594 | 43741453 | 2013-04-22 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 18% | -4001 |  | Project at 100% design, funds absconded by sequester
2014-10-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Metro Entrance Facility/Visitor Screening Facility | 2012-01-10 | 2013-09-30 | The Matthews Group, Inc. |  | 5609 | 5609 | 2013-11-01 | 2015-06-01 | 2015-06-01 | 2015-06-01 | 13% | 0 |  | Design/Build - Not affected by sequester
2014-10-31 | 2011 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Secure Access Lane (SAL) | 2011-08-08 | 2013-09-30 | Ikhana,LLC |  | 5454 | 5454 | 2013-11-01 | 2015-05-01 | 2015-05-01 | 2015-05-01 | 4% | 0 |  | Award Contract Base Bid Items 28 Sep 2013; All options, for DIACAP $31,093, Perimeter Fence and 3 Vehicle Gates $138,693 and Public Rest Room (OPA funded) $447,766 awarded; NTP estimated by 1 Feb 2013. 510 cds contract duration.
2014-10-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Heliport Control Tower/Fire Station | [11 empty] | 0 |  | In 35% design.
2014-10-31 | 2012 | Washington Headquarters Services | Major Military Construction | VIRGINIA | UNITED STATES |  | Pentagon Memorial Plaza | [11 empty] | 0 |  | Design contract award 26SEP13. NTP 1 Nov13. Design 8 mos/Construct 12mos. Contract duration 540 cds

## DETAILED EXPENDITURES
Data as of Date | Fiscal Year | Component | Appropriation Fund Type | Use of funds | Appropriated Amount ($000) | Current Obligated Amount ($000) | Current Expenditure Amount ($000) | Remarks
2014-10-31 | 2006 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 292773.86 | 281956.1925 | 281662.7882
2014-10-31 | 2006 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY07 MILCON; design of FY06 non-PB projects if any; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 27782.96 | 26874.615 | 26317.8729
2014-10-31 | 2006 | Air Force Active | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 63753.948 | 58353.2259 | 57468.177
2014-10-31 | 2006 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 1530 | 0 | 0
2014-10-31 | 2006 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15769.71 | 15283.0716 | 15073.8774
2014-10-31 | 2006 | Air Force Reserve | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 5289.57 | 5289.1201 | 5289.1201
2014-10-31 | 2006 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 3960 | 3959.9996 | 3959.9996
2014-10-31 | 2006 | Air National Guard | Planning and Design | Complete design of FY07 MILCON; design of FY06 Congressional Inserts; start design of FY08 MILCON; fund Congressionally directed designs. | 30006 | 28020.5334 | 28018.597
2014-10-31 | 2006 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6882 | 6882 | 6882
2014-10-31 | 2007 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 385232 | 329307.8469 | 329275.2804
2014-10-31 | 2007 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY08 MILCON; design of FY07 non-PB projects if any; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 13064 | 12896.1514 | 12604.7155
2014-10-31 | 2007 | Air Force Active | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 74021 | 72929.498 | 72084.9635
2014-10-31 | 2007 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 2225 | 2206.9737 | 2206.9737
2014-10-31 | 2007 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14163.2777 | 14163.2777
2014-10-31 | 2007 | Air Force Reserve | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 5109 | 5072.4629 | 5072.4629
2014-10-31 | 2007 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4477 | 4476.9716 | 4476.9716
2014-10-31 | 2007 | Air National Guard | Planning and Design | Complete design of FY08 MILCON; design of FY07 Congressional Inserts; start design of FY09 MILCON; fund Congressionally directed designs. | 19050 | 19043.34 | 19043.3394
2014-10-31 | 2007 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 6000 | 5999.9999 | 5999.9999
2014-10-31 | 2008 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 259262 | 238598.4841 | 225514.1635
2014-10-31 | 2008 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY09 MILCON; design of FY08 non-PB projects if any; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 12210 | 12161.823 | 12161.823
2014-10-31 | 2008 | Air Force Active | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 30148 | 29576.7563 | 29188.6112
2014-10-31 | 2008 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Global War on Terror (GWOT) | 21054 | 13130.6247 | 13130.6247
2014-10-31 | 2008 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14081.4775 | 13525.7208
2014-10-31 | 2008 | Air Force Reserve | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 5300 | 5270.7978 | 5270.7978
2014-10-31 | 2008 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4909 | 4909 | 4909
2014-10-31 | 2008 | Air National Guard | Planning and Design | Complete design of FY09 MILCON; design of FY08 Congressional Inserts; start design of FY10 MILCON; fund Congressionally directed designs. | 10721 | 10619.0353 | 10619.0353
2014-10-31 | 2008 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14184 | 14183.984 | 14168.9847
2014-10-31 | 2009 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 253513.728 | 207293.8625 | 156853.4973
30-Sep'2014 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 592614 | 592503 | 592503
30-Sep'2014 | 2009 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Supplemental appropriations for MFH Operations and Maintenance provided by the American Recovery and Reinvestment Act of 2009 (ARRA - P.L. 111-5) | 16455 | 16455 | 16455
2014-10-31 | 2009 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY10 MILCON; design of FY09 non-PB projects if any; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 7703 | 7593.62 | 7524.9478
2014-10-31 | 2009 | Air Force Active | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 105196.1872 | 103703.1322 | 102007.8409
2014-10-31 | 2009 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 14860.6296 | 13471.8023
2014-10-31 | 2009 | Air Force Reserve | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 6165 | 6133.5834 | 6123.2565
2014-10-31 | 2009 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5443 | 5442.927 | 5442.9269
2014-10-31 | 2009 | Air National Guard | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs. | 19056 | 19056 | 18944.6009
2014-10-31 | 2009 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 34243 | 34163.725 | 33607.2174
2014-10-31 | 2010 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 61558 | 59491.5566 | 59482.774
30-Sep'2014 | 2010 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 529950 | 510499 | 508545
2014-10-31 | 2010 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY11 MILCON; design of FY10 non-PB projects if any; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4302 | 1440.5783 | 1396.5783
2014-10-31 | 2010 | Air Force Active | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 87562 | 87221.6096 | 84360.8805
2014-10-31 | 2010 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 25223 | 21494.5143 | 21462.048
2014-10-31 | 2010 | Air Force Active | Unspecified Minor Construction [UMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 15000 | 12086.3123 | 11595.7213
2014-10-31 | 2010 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000 | 19867.8576 | 19775.4277
2014-10-31 | 2010 | Air Force Reserve | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 8139 | 8001.7193 | 2584.2846
2014-10-31 | 2010 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 752.8898 | 752.8898 | 752.8898
2014-10-31 | 2010 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 47.1102 | 47.1102 | 0
2014-10-31 | 2010 | Air National Guard | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs. | 19670.441 | 19575.2809 | 19169.9508
2014-10-31 | 2010 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 44913.559 | 44560.8417 | 34539.5102
2014-10-31 | 2011 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72192.95 | 53397.0155 | 32313.7458
30-Sep'2014 | 2011 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 544423 | 514090 | 512405
2014-10-31 | 2011 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY12 MILCON; design of FY11 non-PB projects if any; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4153 | 3921.568 | 3910.1778
2014-10-31 | 2011 | Air Force Active | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 63903.328 | 59837.9835 | 56169.2409
2014-10-31 | 2011 | Air Force Active | Planning and Design | Design for MILCON Projects Supporting the Overseas Contingency Operations (OCO) | 2622 | 1854.0467 | 1854.0467
2014-10-31 | 2011 | Air Force Active | Unspecified Minor Construction [UMC] | (OCO) Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 49584 | 39021.0266 | 24215.1656
2014-10-31 | 2011 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 17964 | 17502.4646 | 16775.2846
2014-10-31 | 2011 | Air Force Reserve | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 1649.694 | 1521.061 | 1521.061
2014-10-31 | 2011 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 2745.819 | 2728.9494 | 2647.8331
2014-10-31 | 2011 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7.663 | 7.663 | 0
2014-10-31 | 2011 | Air National Guard | Planning and Design | Complete design of FY12 MILCON; start design of FY13 MILCON; fund Congressionally directed designs. | 9195.572 | 8638.9962 | 8562.4803
2014-10-31 | 2011 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 7984 | 7709.7134 | 5187.8783
2014-10-31 | 2012 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 53407 | 21828.4723 | 20650.0662
30-Sep'2014 | 2012 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 448449 | 434239 | 427974
2014-10-31 | 2012 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY13 MILCON; design of FY12 non-PB projects if any; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4056 | 4009.0975 | 3990.1426
2014-10-31 | 2012 | Air Force Active | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 78413 | 68485.5932 | 61581.2793
2014-10-31 | 2012 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20000 | 19483.3001 | 13126.605
2014-10-31 | 2012 | Air Force Reserve | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 2200 | 2013.2783 | 1293.6004
2014-10-31 | 2012 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 4594.3732 | 4216.3096 | 2670.2922
2014-10-31 | 2012 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 839.6268 | 839.6268 | 0
2014-10-31 | 2012 | Air National Guard | Planning and Design | Complete design of FY13 MILCON; start design of FY14 MILCON; fund Congressionally directed designs. | 12225 | 12010.566 | 10906.6524
2014-10-31 | 2012 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 9000 | 6804.5925 | 4674.7965
2014-10-31 | 2013 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 73936.577 | 2489.7258 | 812.3365
30-Sep'2014 | 2013 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 468443 | 445332 | 390073
2014-10-31 | 2013 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 3951.846 | 0 | 0
2014-10-31 | 2013 | Air Force Active | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 410.408 | 367.934 | 82.9861
2014-10-31 | 2013 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 14467.9945 | 3991.1429 | 1523.4505
2014-10-31 | 2013 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2875.201 | 1186.4955 | 446.7891
2014-10-31 | 2013 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1641.761 | 0 | 0
2014-10-31 | 2013 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 355.6 | 355.6 | 0
2014-10-31 | 2013 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 3994.721 | 3421.4572 | 2042.1083
2014-10-31 | 2013 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 5892.214 | 3159.4379 | 168.5935
2014-10-31 | 2014 | Air Force Active | Improvements | Military family housing projects to improve existing military family housing units and ancillary family housing support facilities pursuant to 10 USC 2825. | 72093 | 40753.6909 | 66.3957
30-Sep'2014 | 2014 | Air Force Active | Military Family Housing - Operations and Maintenance [MFH O&M] | Approved Air Force program for all MFH Operations and Maintenance accounts supporting Air Force Military Family Housing | 417511 | 316399 | 157671
2014-10-31 | 2014 | Air Force Active | Planning and Design | Complete design of Active AF Military Family Housing FY15 MILCON; design of FY14 non-PB projects if any; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements | 4267 | 0 | 0
2014-10-31 | 2014 | Air Force Active | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES Cost Engineering; fund misc Air Staff & MAJCOM design requirements; Overseas Contingency Operations | 11314 | 9380.2623 | 4336.5621
2014-10-31 | 2014 | Air Force Active | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 20448 | 0 | 0
2014-10-31 | 2014 | Air Force Reserve | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 2229 | 0 | 0
2014-10-31 | 2014 | Air Force Reserve | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 1530 | 0 | 0
2014-10-31 | 2014 | Air National Guard | Planning and Design | Complete design of FY15 MILCON; start design of FY16 MILCON; fund Congressionally directed designs. | 13400 | 4017.111 | 171.3387
2014-10-31 | 2014 | Air National Guard | Unspecified Minor Construction [UMC] | Unspecified minor military construction projects with an approved cost not exceeding the minor construciton thresholds specified in 10 USC 2805(a). | 13000 | 594.4725 | 0
2014-10-31 | 2009 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 24000 | 24000 | 24000
2014-10-31 | 2010 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 25000 | 25000 | 25000
2014-10-31 | 2011 | Army Active | Host Nation Support | $29,944 Appropriated + $13,000 ATR | 42944 | 42932 | 42899
2014-10-31 | 2012 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. $25,500 Appropriated + $1,500 BTR + $9,000 ATR | 36000 | 34700 | 33318
2014-10-31 | 2013 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 33954 | 33632 | 32239
2014-10-31 | 2014 | Army Active | Host Nation Support | Funding used to represent US interests during the planning, design, and construction of projects funded by foreign governments, when US Forces are the sole or primary users. | 23000 | 22618 | 21103
2014-10-31 | 2009 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 21855 | 21855 | 21855
2014-10-31 | 2010 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 28393 | 28392 | 28387
2014-10-31 | 2011 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 37328 | 37328 | 37311
2014-10-31 | 2012 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 34342 | 34266 | 34263
2014-10-31 | 2013 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 28124 | 27974 | 27854
2014-10-31 | 2014 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 21949 | 21645 | 12823
2014-10-31 | 2015 | Army Active | Military Family Housing O&M | Army Family Housing O&M | 3000 | 673 | 311
2014-10-31 | 2010 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 60100 | 14055 | 14054
2014-10-31 | 2011 | Army Active | Overseas Contingency Operations [OCO] | Unspecified Minor Construction for Projects < $2.M | 78330 | 1274 | 1274
2014-10-31 | 2009 | Army Active | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 222766 | 218891 | 216315
2014-10-31 | 2009 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 576 | 576 | 524
2014-10-31 | 2010 | Army Active | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 252499 | 250436 | 246715
2014-10-31 | 2010 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 3936 | 3935 | 2225
2014-10-31 | 2011 | Army Active | Planning and Design | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 308676 | 262955 | 255836
2014-10-31 | 2011 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 2036 | 1990 | 1308
2014-10-31 | 2012 | Army Active | Planning and Design | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 229741 | 190743 | 176068
2014-10-31 | 2012 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 7897 | 6475 | 5939
2014-10-31 | 2013 | Army Active | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 46112 | 44846 | 39513
2014-10-31 | 2013 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 4635 | 78 | 78
2014-10-31 | 2014 | Army Active | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed design; fund PACES cost engineering; fund other design requirements. | 41575 | 24483 | 18979
2014-10-31 | 2014 | Army Active | Planning and Design | Army Family Housing Construction for Projects | 4408 | 0 | 0
2014-10-31 | 2009 | Army Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction for Projects < $2.M | 28750 | 28232 | 25954
2014-10-31 | 2010 | Army Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction for Projects < $2.M | 31250 | 31149 | 29615
2014-10-31 | 2011 | Army Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction for Projects < $2.M | 28704 | 26450 | 26309
2014-10-31 | 2012 | Army Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction for Projects < $2.M | 20000 | 19043 | 18580
2014-10-31 | 2013 | Army Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 23727 | 14065
2014-10-31 | 2014 | Army Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction for Projects < $2.M | 25000 | 21940 | 1307
2014-10-31 | 2011 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 136314 | 136313 | 124618
2014-10-31 | 2012 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 83943 | 83943 | 79637
2014-10-31 | 2013 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 96888 | 80733 | 53411
2014-10-31 | 2014 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 80638 | 35657 | 32899
2014-10-31 | 2015 | Navy Active | Planning and Design | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 16684 | 39 | 13 | Appropriated Amount reflects funds allocated to date only.
2014-10-31 | 2011 | Navy Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 20757 | 20063 | 18650
2014-10-31 | 2012 | Navy Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 20919 | 19733 | 17676
2014-10-31 | 2013 | Navy Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 15612 | 13264 | 5009
2014-10-31 | 2014 | Navy Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 19740 | 5800 | 0
2014-10-31 | 2015 | Navy Active | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 3582 | 0 | 0 | Appropriated Amount reflects funds allocated to date only.
2014-10-31 | 2011 | Navy Active | Planning and Design | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 2340 | 2229 | 2229
2014-10-31 | 2012 | Navy Active | Planning and Design | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2447 | 2377 | 2367
2014-10-31 | 2013 | Navy Active | Planning and Design | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 3609 | 682 | 641
2014-10-31 | 2014 | Navy Active | Planning and Design | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 3975 | 0 | 0
2014-10-31 | 2015 | Navy Active | Planning and Design | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2014-10-31 | 2011 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 853 | 744 | 741
2014-10-31 | 2012 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 719 | 566 | 566
2014-10-31 | 2013 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 455 | 419 | 358
2014-10-31 | 2014 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 463 | 0 | 0
2014-10-31 | 2015 | Marine Corps Active | Planning and Design | Family Housing Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2014-10-31 | 2011 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs | 1854 | 1854 | 1854
2014-10-31 | 2012 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs | 2478 | 2148 | 2148
2014-10-31 | 2013 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs | 1995 | 1993 | 1990
2014-10-31 | 2014 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs | 2540 | 315 | 295
2014-10-31 | 2015 | Navy Reserve | Planning and Design | Navy and Marine Corps MCON: Complete design of FY16 MILCON; design of FY15 Congressional Inserts; start design of FY17 MILCON; fund Congressionally directed designs | 0 | 0 | 0 | No funds yet allocated for FY15
2014-10-31 | 2011 | Navy Reserve | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 2194 | 1632 | 1548
2014-10-31 | 2012 | Navy Reserve | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 1947 | 1226 | 1161
2014-10-31 | 2013 | Navy Reserve | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0
2014-10-31 | 2014 | Navy Reserve | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0
2014-10-31 | 2015 | Navy Reserve | Unspecified Minor Construction [UMC] | Unspecified Minor Construction [UMC] | 0 | 0 | 0 | No funds yet allocated for FY15
2014-10-31 | 2011 | Navy Active | Improvements | Military Family Housing Improvement | 27773 | 24966 | 24900
2014-10-31 | 2012 | Navy Active | Improvements | Military Family Housing Improvement | 68661 | 48116 | 40808
2014-10-31 | 2013 | Navy Active | Improvements | Military Family Housing Improvement | 42739 | 24041 | 884
2014-10-31 | 2014 | Navy Active | Improvements | Military Family Housing Improvement | 44716 | 28894 | 0
2014-10-31 | 2015 | Navy Active | Improvements | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2014-10-31 | 2011 | Marine Corps Active | Improvements | Military Family Housing Improvement | 11087 | 10771 | 10771
2014-10-31 | 2012 | Marine Corps Active | Improvements | Military Family Housing Improvement | 25327 | 23561 | 20842
2014-10-31 | 2013 | Marine Corps Active | Improvements | Military Family Housing Improvement | 17441 | 16715 | 0
2014-10-31 | 2014 | Marine Corps Active | Improvements | Military Family Housing Improvement | 24253 | 15632 | 0
2014-10-31 | 2015 | Marine Corps Active | Improvements | Military Family Housing Improvement | 0 | 0 | 0 | No funds yet allocated for FY15
2014-10-31 | 2009 | Army National Guard | Planning and Design | Complete design of FY10 MILCON; design of FY09 Congressional Inserts; start design of FY11 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 60944 | 60943 | 60943 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2009 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 21880 | 21880 | 21880 | PL 111-117 Rescission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Planning and Design | Complete design of FY11 MILCON; design of FY10 Congressional Inserts; start design of FY12 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 47210 | 47210 | 47210 | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2010 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 36905 | 36905 | 36905 | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2011 | Army National Guard | Planning and Design | Complete design of FY12 MILCON; design of FY11 Congressional Inserts; start design of FY13 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25604 | 24287 | 24287 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2011 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14215 | 11220 | 11220 | PL 112-10 SEC 1119 (a) 0.2% Recission & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2012 | Army National Guard | Planning and Design | Complete design of FY13 MILCON; design of FY12 Congressional Inserts; start design of FY14 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 20191 | 17086 | 17086 | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2012 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14149 | 11784 | 11784 | PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Planning and Design | Complete design of FY13 Hurricane Sandy remain in effect until 30 Sep 17 | 2407 | 1771 | 1771 | PL 113-2 Disaster Relief Appropriations Act, 2013 & PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013)
2014-10-31 | 2013 | Army National Guard | Planning and Design | Complete design of FY14 MILCON; design of FY13 Congressional Inserts; start design of FY15 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 25748 | 2971 | 2971 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2013 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 14562 | 14254 | 14254 | PL 113-6 (Consolidated and Further Continuing Appropriations Act, 2013) & PL 112-25 (Budget Control Act, 2011)
2014-10-31 | 2014 | Army National Guard | Planning and Design | Complete design of FY15 MILCON; design of FY14 Congressional Inserts; start design of FY16 MILCON; fund Congressionally directed designs; fund PACES cost engineering; fund other design requirements. | 22930 | 2431 | 2431 | PL 113-76 P&D Recission
2014-10-31 | 2014 | Army National Guard | Unspecified Minor Military Construction [UMMC] | Unspecified Minor Military Construction for projects < $2M | 12240 | 1398 | 1398
2014-10-31 | 2009 | Defense Health Agency | Unspecified Minor Construction [UMC] | UMC Projects | 3979 | 3979 | 3979
2014-10-31 | 2010 | Defense Health Agency | Unspecified Minor Construction [UMC] | UMC Projects | 5547 | 3984 | 3942
2014-10-31 | 2011 | Defense Health Agency | Unspecified Minor Construction [UMC] | UMC Projects | 4673 | 2722 | 2394
2014-10-31 | 2012 | Defense Health Agency | Unspecified Minor Construction [UMC] | UMC Projects | 5930 | 4751 | 4706
2014-10-31 | 2013 | Defense Health Agency | Unspecified Minor Construction [UMC] | UMC Projects | 4608 | 2980 | 164
2014-10-31 | 2014 | Defense Health Agency | Unspecified Minor Construction [UMC] | UMC Projects | 9578 | 554 | 0
2014-10-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Parking Garage Replacement | 1498 | 461 |  | Planning and Design (P&D) Directive forwarded to NAVFAC end of May. $416K (CORRECTED AMOUNT) obligated as CAT I. Contract awarded on 23 September 2014.
2014-10-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Chilled Water Project for Data Center | 125 |  |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.
2014-10-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for DIAC Cooling Tower for Data Center | 105 |  |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 35% design completed.
2014-10-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for UPS for Data Center Installation | 120 | 120 |  | Planning and Design (P&D) Directive forwarded to NAVFAC. Funds sent to NAVFAC. Design Contract awarded on 30 January 2013. 100% design completed.
2014-10-31 | 2012 | Defense Intelligence Agency | Planning and Design | P&D for Construction of JUIAF RDF | 1195 | 1195 |  | $1,195 obligated as CAT I acceptance. Design complete.
2014-10-31 | 2010 | Defense Information Systems Agency | Military Family Housing - Operations and Maintenance [MFH O&M] | Replace raised floor and clean and seal, bldg 2340 |  | 903.6 |  | 97% complete
2014-10-31 | 2009 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2009 to 2013 | 4338 | 4334 | 4334
2014-10-31 | 2009 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Construction [UMC] | For minor construction projects from 2009 to 2010 | 4093 | 4027 | 4027
2014-10-31 | 2010 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2010 to 2015 | 12548 | 12446 | 12446
2014-10-31 | 2010 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Construction [UMC] | For minor construction projects from 2010 to 2014 | 4078 | 4078 | 4078
2014-10-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of projects from 2012 to 2016 | 36093 | 35951 | 35951
2014-10-31 | 2011 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Construction [UMC] | For minor construction projects from 2011 to 2014 | 4968 | 3996 | 3996
2014-10-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of project from 2012 to 2016 | 34331 | 34330 | 34330
2014-10-31 | 2012 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Construction [UMC] | For minor construction projects from 2012 to 2014 | 6312 | 5431 | 5431
2014-10-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Planning and Design | For design of project from 2014 to 2017 | 18308 | 10301 | 10301
2014-10-31 | 2013 | Defense Logistics Agency – Other (HQ, etc) | Unspecified Minor Construction [UMC] |  | 6686 | 0 | 0
2014-10-31 | 2008 | DoD Education Activity | Planning and Design | Design Efforts FY09 RCI MILCON projects | 3400 | 3348 |  | RCI-Residential Communities Initiative
2014-10-31 | 2008 | DoD Education Activity | Planning and Design | Design efforts for FY 08/09/ 10/11/12 MILCON projects | 1891 | 1891
2014-10-31 | 2009 | DoD Education Activity | Planning and Design | Design Efforts FY09 RCI MILCON projects | 1830 | 1830
2014-10-31 | 2009 | DoD Education Activity | Planning and Design | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 5000 | 5000
2014-10-31 | 2009 | DoD Education Activity | Planning and Design | Design efforts for FY 09/10/ 11/12/13 MILCON projects | 7000 | 7000
2014-10-31 | 2010 | DoD Education Activity | Planning and Design | Design efforts for FY 10/11/ 12/13 MILCON projects | 8830 | 8830 |  | Reflects Sequestration Reduction
2014-10-31 | 2011 | DoD Education Activity | Planning and Design | Design efforts for FY 11/12/ 13 MILCON projects | 7840 | 7840
2014-10-31 | 2011 | DoD Education Activity | Planning and Design | Design efforts for FY 11/12/13 MILCON projects | 70841 | 70826 |  | Reflects Sequestration Reduction
2014-10-31 | 2012 | DoD Education Activity | Planning and Design | Design efforts for FY 12/13 MILCON projects | 64551 | 63815 |  | Reflects Sequestration Reduction
2014-10-31 | 2013 | DoD Education Activity | Planning and Design | Design efforts for FY 13/14/15/16 MILCON projects | 97290 | 69731 |  | Reflects Sequestration Reduction
2014-10-31 | 2014 | DoD Education Activity | Planning and Design | Design efforts for FY 14/15/16/17 MILCON projects | 75905 | 0
2014-10-31 | 2008 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 666 | 0
2014-10-31 | 2009 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 382 | 4 |  | $4K for lost claim settlement, FY88 Multi-Purpose Room, Spangdahlem High School,
2014-10-31 | 2010 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 6275 | 6275 |  | Reflects Sequestration Reduction
2014-10-31 | 2011 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 3217 | 3217
2014-10-31 | 2013 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 3771 | 0 |  | Reflects Sequestration Reduction
2014-10-31 | 2014 | DoD Education Activity | Unspecified Military Minor Construction [UMMC] | Unspecified Minor Construction for projects < $2.M | 5409 | 0
2014-10-31 | 2007 | Missile Defense Agency | Planning and Design | Design MDA 609 - Aegis-BMD Facility Expansion, Dahlgren, VA. | 770 | 770 | 770 | Completed RFP for design-build (D-B) project.
2014-10-31 | 2009 | Missile Defense Agency | Planning and Design | Design MDA FY10-FY13 MILCON Projects | 14848 | 14839 | 14839 | Supports design of the Aegis Ashore Test Complex, East Coast Comm site, Aegis Ashore Romania site, UEWR Modifications at Clear AFS, AK and completes RFP for D-B Von Braun Complex, Phase IV.
2014-10-31 | 2010 | Missile Defense Agency | Planning and Design | Design MDA FY12-13 MILCON Projects | 7698 | 7698 | 7698 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, UEWR Modifications at Clear AFS, AK, and EUCOM Radar site. Includes $5,700,000 reprogrammed from MILCON.
2014-10-31 | 2011 | Missile Defense Agency | Planning and Design | Design MDA FY15-16 MILCON Projects | 1186 | 1186 | 0 | Funds tranferred from DHA in April 2014; supports design of the Aegis Ashore Poland site
2014-10-31 | 2012 | Missile Defense Agency | Planning and Design | Design MDA FY13-14 MILCON Projects | 8368 | 8368 | 8108 | Supports design of the Aegis Ashore Romania site, East Coast Comm site, and the UEWR Modifications at Clear AFS, AK .
2014-10-31 | 2013 | Missile Defense Agency | Planning and Design | Design MDA FY13-14 MILCON Projects | 4191 | 4191 | 3804 | Supports design of the East Coast Comm site, UEWR Modifications at Clear AFS, AK, AN/TPY-2 Radar Site, PACOM, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-10-31 | 2014 | Missile Defense Agency | Planning and Design | Design MDA FY14-16 MILCON Projects | 10891 | 7816 | 1718 | Supports design of the East Coast Comm site, AN/TPY-2 Radar Site, PACOM, Storage Facility, Meck Island, Aegis Ashore Poland site, and RFP development for Mechanical-Electrical Building, MF1, Fort Greely, AK.
2014-10-31 | 2009 | Missile Defense Agency | Unspecified Minor Construction [UMC] | Used for accomplishing urgent unforeseen construction projects in FY12/13 | 3317 | 3117 | 3117 | Obligated funds support the EUCOM Radar Site. EUCOM work which resumed on 6 May 2013. Additional obligation of funds supports the Readiness & Control (R&C) Facility Redundant Chilled Water Distribution Piping project at Fort Greely, AK
2014-10-31 | 2010 | Missile Defense Agency | Unspecified Minor Construction [UMC] | Used for accomplishing urgent unforeseen construction projects in FY13/14 | 2243 | 2038 | 422 | Supports the R&C Piping project at Fort Greely, AK and the Storage Facility, Meck Island. $1.186M transferred to DHA in April 2014 for swap of FY11 P&D funds. $205K returned to OSD in Sep 2014.
2014-10-31 | 2014 | Missile Defense Agency | Unspecified Minor Construction [UMC] | Used for accomplishing urgent unforeseen construction projects in FY14/15 | 2000 | 155 | 0 | Supports the Storage Facility, Meck Island project.
2014-10-31 | 2010 | National Security Agency | Planning and Design | Generators 10 & 11 | 440 | 440 |  | MIPR 12-045 from MHS to AFCEC, $240K moved from Power & Cooling
2014-10-31 | 2010 | Special Operations Command | Planning and Design | MILCON Design Work | 4344 | 4331
2014-10-31 | 2011 | Special Operations Command | Planning and Design | MILCON Design Work | 26469 | 24853
2014-10-31 | 2012 | Special Operations Command | Planning and Design | MILCON Design Work | 30308 | 27452
2014-10-31 | 2013 | Special Operations Command | Planning and Design | MILCON Design Work | 25454 | 12978
2014-10-31 | 2014 | Special Operations Command | Planning and Design | MILCON Design Work | 36866 | 0
2014-10-31 | 2010 | Special Operations Command | Unspecified Minor Construction [UMC] | Construction Costs for UMC Projects | 6011 | 6010
2014-10-31 | 2011 | Special Operations Command | Unspecified Minor Construction [UMC] | Construction Costs for UMC Projects | 7531 | 7526
2014-10-31 | 2012 | Special Operations Command | Unspecified Minor Construction [UMC] | Construction Costs for UMC Projects | 8487 | 8002
2014-10-31 | 2013 | Special Operations Command | Unspecified Minor Construction [UMC] | Construction Costs for UMC Projects | 9216 | 7965
2014-10-31 | 2014 | Special Operations Command | Unspecified Minor Construction [UMC] | Construction Costs for UMC Projects | 5170 | 0